## revised (On-Going) (hidden)
PROVINCE OF DAVAO DEL NORTE
ACCOMPLISHMENT REPORT
FOR THE MONTH OF APRIL 2018
SECTOR: ECONOMIC (INFRASTRUCTURE DEV'T. PROGRAM)
OFFICE/AGENCY: PROVINCIAL ENGINEER'S OFFICE
AREA: 1ST ENGINEERING DISTRICT - ON-GOING PROJECTS
Name of Project |  |  |  | Type | Physical | Mode | PROJECT DATA | [5 empty] | Financial (000) |  | Physical Accomplishment |  |  |  | Employment |  | REMARKS
|  |  |  | of | Target | of | a) Project Cost |  | a) Date A lot. Rel. |  | d) # of days suspended |  | a) Program |  | a) Planned |  | c) Actual |  | Generated
|  |  |  | Project | (Descrip | Impl. | b) Project Engineer |  | b) Date Started |  | e) # of days extended |  | b) Allotment |  | b) Revised |  | d) Slippage |  | a) # of Persons
|  |  |  | (Location) | tion) |  | c) Implementor |  | c)Target Compl. Date |  | f) Date completed |  | c) Disbursement | [5 empty] | b) Man-days
I. | PROJECTS UNDER THE CONTINUING APPROPRIATION | [21 empty] | 893809.45
| A. | Supplemental Budget # 1 CY 2012
1. Purchase, Const. & Impv't. of
|  | Gov't. Facilities (8918) | [18 empty] | Investigation/inspecton of priority projects
|  | 1.1 Repair & Maintenance of Various |  | Road |  | Admin | a) | 1,000,000.00 | [12 empty] | See project listed below
|  | Local Roads & Drainage |  |  |  |  | b) | Paraguya/Matuguinas
|  | (Provincewide) |  |  |  |  | c) | PEO
|  | a. | Installation of 48"ø at Purok 2 Crossing | Road |  | Admin | a) | 106,190.55 | a) | 111/11/16 | d) | - | a) | 106,190.55 | a) | - | c) | - | a) | - | On-going
|  |  | Highway, Canatan |  |  |  | b) | Salido | b) | 04/23/18 | e) | - | b) | 106,190.55 | b) | - | d) | - | b) | -
[7 empty] | c) | PEO | c) | 05/01/18 | f) | - | c) | -
|  | 2. Various of Water System Project (Provincewide) | [18 empty] | Investigation/inspecton of priority projects
[6 empty] | Admin | a) | 264000 | [12 empty] | See project listed below
[7 empty] | b) | Foronda
[7 empty] | c) | PEO
|  | 2.1 | Rehabilitation of Water Supply System | Water |  | Admin | a) | 165000 | a) | - | d) | - | a) | - | a) | - | c) | - | a) | - | For implementation
|  |  | (Davao del Norte Hospital - Kapalong Zone) |  |  |  | b) | - | b) | - | e) | - | b) | - | b) | - | d) | - | b) | -
[7 empty] | c) | PEO | c) | - | f) | - | c) | -
| B. | SEF (Special Educational Fund) CY 2012
|  | 1. Const./Comp. of Various Sch.Bldgs./Struct./ |  | Bldgs. |  | Admin | a) | 129,631.55 | [12 empty] | Investigation/inspecton of priority projects
|  | Fac. |  |  |  |  | b) | Foronda/Ababon | [12 empty] | ( Priority list c/o deped)
[7 empty] | c) | PEO
| C. | 5% Calamity Fund CY 2013 | [18 empty] | Investigation/inspecton of priority projects
|  | 1. Prevention and Mitigation |  | Road |  | Admin | a) | 5,932,420.00 | [12 empty] | See project listed below
|  | 1.1 Impv't. Roads and Drainages |  |  |  |  | b) | Paraguya/Matuguinas | [12 empty] | balance as of March CY 2018 P 400,000.00
[7 empty] | c) | PEO
|  | a.) | Impv't. of Suaon-Gupitan | Road |  | Admin | a) | 2,900,000.00 | a) | 09/19/17 | d) | - | a) | 2,900,000.00 | a) | 56.07% | c) | 47.53% | a) | 26 | Suspended dated 02/19/18
[7 empty] | b) | Gone | b) | 10/16/17 | e) | - | b) | 2,900,000.00 | b) | - | d) | -8.54% | b) | 442
[7 empty] | c) | PEO | c) | 03/13/18 | f) |  | c) | 1,289,025.00
| D. | 20% Development Fund CY 2014
|  | 1. Rural Electrification Project |  | Elect. |  | Admin | a) | 1,000,000.00 | [12 empty] | Investigation/inspecton of priority projects
|  | (Provincewide) |  |  |  |  | b) | Lu | [12 empty] | balance as of March CY 2018 P 103,706.09
[7 empty] | c) | PEO
| E. | 5% Calamity Fund CY 2014
1. Prevention and Mitigation
|  | 1.1 Impv't. of Roads and Drainages |  |  |  |  | a) | 7,090,168.00 | [12 empty] | See project listed below
[7 empty] | b) | Paraguya/Matuguinas | [12 empty] | balance as of March CY 2018 P 494,802.00
[7 empty] | c) | PEO
|  | 1.2 Impv't. of Bridges and Cross drainages |  | Cross |  | Admin | a) | 3,000,000.00 | [12 empty] | See project listed below
|  |  |  | Drainage |  |  | b) | Paraguya/Matuguinas
[7 empty] | c) | PEO
|  | a.) | Impv't. of One Lane-48"ø RCPC Along | Cross |  | Admin | a) | 217,000.00 | a) | - | d) | - | a) | 217,000.00 | a) | - | c) | - | a) | - | For implementation
|  |  | New Corella-Sto. Niño-Macgum-Prov'l. Road | Drainage |  |  | b) | Paraguya | b) | - | e) | - | b) | 217,000.00 | b) | - | d) | - | b) | -
[7 empty] | c) | PEO | c) | - | f) |  | c) | 41,901.00
| F. | 20% Development Fund CY 2015
|  | 1. Various of Water System Project (Provincewide) |  | Water | - | Admin | a) | 2,000,000.00 | [12 empty] | Investigation/Inspection of priority projects
|  |  |  | System |  |  | b) | Foronda/Ababon
[7 empty] | c) | PEO
|  | 1.1 | Improvement of Potable Water System, | rivers |  | Admin | a) | 450,000.00 | a) | - | d) | - | a) | 450,000.00 | a) | 45.36% | c) | 46.00% | a) | 7 | On-going
|  |  | 2nd Light Armored Troops Headquarter, |  |  |  | b) | Diosanta | b) | 04/04/18 | e) | - | b) | 450,000.00 | b) | - | d) |  | b) | 280
|  |  | CGMTY Sr., Brgy. Tuburan, Mawab |  |  |  | c) | PEO | c) | 05/31/18 | f) |  | c)
|  | 2. Rural Electrification |  | Elect. |  | Admin | a) | 1,000,000.00 | [12 empty] | See projects listed below
|  | (Provincewide) |  |  |  |  | b) | Lu | [12 empty] | Balance as of April CY 2018 P 825,000.00
[7 empty] | c) | PEO
|  | 2.1 | Installation of Distribution Transformer | rivers |  | Admin | a) | 362,614.83 | a) | - | d) | - | a) | 362,614.83 | a) | - | c) | - | a) | - | For implementation
|  |  | and Electrical Wirings at 10th |  |  |  | b) | Lu | b) | - | e) | - | b) | 362,614.83 | b) | - | d) |  | b) | -
|  |  | Infatry (AGILA), Division, PHIL. Army, Tuburan |  |  |  | c) | PEO | c) | - | f) |  | c)
|  | 3. Counterpart to Special Projecs |  | Roads |  | Admin | a) | 5,000,000.00 | [12 empty] | Investigation/inspection of piority projects
[7 empty] | b) | Foronda/Ababon
[7 empty] | c) | PEO
| G. | 5% Calamity Fund CY 2015
1. Prevention and Mitigation
|  | 1.1 Revitment of Dike and Slope Protection |  | rivers |  | Admin | a) | 3,325,000.00 | [12 empty] | See project listed below
[7 empty] | b) | Paraguya/Matuguinas | [12 empty] | balance as of March CY 2018 P 2,223,687.49
[7 empty] | c) | PEO
|  | a.) | Inst. Of Suaon-Gupitan, Slope Protection | rivers |  | Admin | a) | 2,041,000.00 | a) | 04/03/17 | d) | - | a) | 2,041,000.00 | a) | 53.50% | c) | 63.45% | a) | 22 | On-going
|  |  | (Part of 3.325M) |  |  |  | b) | Gone | b) | 02/16/18 | e) | - | b) | 2,041,000.00 | b) | - | d) | 9.95% | b) | 374
[7 empty] | c) | PEO | c) | 05/28/18 | f) |  | c) | 281190
2. Rehabilitation and Recovery
|  | 2.1. Rehab. Of infrastructures projects affected |  |  |  | Admin | a) | 5,000,000.00 | [12 empty] | Investigation/inspecton of priority projects
|  | by recent calamity |  |  |  |  | b) | Paraguya/Matuguinas
[7 empty] | c) | PEO
| H. | Supplemental Budget # 5 CY 2015
1. Purchased, Const. & Imprv't. of Gov't. Facilities (8918)
|  | a) Const./Imprvt. Drainage/Canal Linings |  | Drainage/ |  | Admin | a) | 2,500,000.00 | [12 empty] | See project listed below
|  |  |  | Canal Lining |  |  | b) | Foronda
[7 empty] | c) | PEO
|  | a.1 | Improvement of Public Cemetery | Cemetery |  | Contract | a) | 500,000.00 | a) | 03/05/16 | d) | - | a) | 500,000.00 | a) | 100.00% | c) | 45.00% | a) | 8 | On-going
|  |  | Brgy. Linao, San Isidro |  |  |  | b) | - | b) | 10/17/18 | e) | - | b) | 500,000.00 | b) | - | d) | - | b) | 136
[7 empty] | c) | JB Lazan | c) |  | f) | - | c) | -
|  | 2. Purchased, Const. & Imprv't. of Gov't. Facilities (3918) |  |  |  |  | a) | 130,000,000.00 | [12 empty] | See projects listed below
[7 empty] | b) | Foronda
[7 empty] | c) | PEO
|  | 2.1 | Upgrading of of DNSTC (Commercial Bldg.) | Bldg. |  | Contract | a) | 29,999,981.00 | a) | CY 2015 | d) | - | a) | 29,999,981.00 | a) | 100.00% | c) | 98.449% | a) | - | Suspended as of February 14, 2018.
|  |  | Sports Complex Center, Mankilam |  |  |  | b) | Escurzon | b) | 10/28/16 | e) | 161 WD | b) | 29,999,981.00 | b) | 98.12% | d) | -2.12% | b) | - | Waiting for the approval of the Bldg. Electricaol
[7 empty] | c) | PEO | c) | 02/15/17 | f) |  | c) | 4,499,997.15 | [6 empty] | permit application from OBO.
| I. | Trust Fund
1. PAMANA-DILG CY 2014
|  | 1.1 Construction of Biga Bridges, Kapalong |  | Road | - | Contract | a) | 24959503.45 | a) | CY 2014 | d) | - | a) | 24959503.45 | a) | 16.21% | c) | 8.91% | a) | - | Suspended
[7 empty] | b) | Limpo | b) | 07/01/16 | e) | - | b) | 24959503.45 | b) | - | d) | -7.3% | b) | -
[7 empty] | c) | Dvo. Rock Mixer | c) | 10/21/18 | f) | - | c) | 37,439,255.18
|  | 1.2 Road Rehabilitation/Improvement of Prk. 3, |  | Road | - | Contract | a) | 50,500,288.95 | a) | CY 2014 | d) | - | a) | 50,500,288.95 | a) | 94.80% | c) | 75.66% | a) | 22 | On-going
|  | Palma Gil-Prk.2 (side 2), Sto. Niño-Mahayahay-Tugas- |  |  |  |  | b) | Dadula | b) | 07/07/16 | e) | - | b) | 50,500,288.95 | b) | 88.74% | d) | -13.08% | b) | 374
|  | Nanaga Road, with 1 -unit, 40 ln.m PSCG Bridge, |  |  |  |  | c) | Puregold | c) | 03/12/18 | f) | - | c) | 7,575,009.962
Kapalong
2. PRDP CY 2015
|  | 2.1 Rehab. New Visayas-Binancian |  | Roads | 7.84 kms. | Contract. | a) | 86,500,370.47 | a) | CY 2014 | d) | 226 CD | a) | 86,500,370.47 | a) | 100.00% | c) | 79.08% | a) | 36 | On-going
|  | Asuncion. Davao del Norte |  |  |  |  | b) | Medalla | b) | 10/18/15 | e) | 189 CD | b) | 86,500,370.47 | b) | 88.97% | d) | -9.89% | b) | 900 | Approved variation order P 7,668,482.11
|  | (Provincial Counterpart: 1.205830M) |  |  |  |  | c) | Dvo. Rock Mixer | c) | 05/06/18 | f) | - | c) | 11,824,783.15
|  | 2.2 Rehab. Of Sto. Niño-Igangon FMR |  | Roads | 8.93 kms. | Contract. | a) | 74,173,694.50 | a) | CY 2015 | d) | - | a) | 74,173,694.50 | a) | 100.00% | c) | 95.00% | a) | 20 | On-going
|  | San Isidro, Davao del Norte |  |  |  |  | b) | Fabiala | b) | 03/21/16 | e) | 175 CD | b) | 74,173,694.50 | b) | - | d) | -5% | b) | 480
[7 empty] | c) | Monolitic Const./R.R Seismundo | c) | 04/07/18 | f) | - | c) | 12,272,507.70
|  | 2.3 Rehab. Of Capungagan-Boundary San |  | Roads | 10.6 kms. | Contract. | a) | 108,303,841.70 | a) | CY 2015 | d) | 140 CD | a) | 108,303,841.70 | a) | 100.00% | c) | 27.435% | a) | 15 | On-going
|  | Miguel FMR, Kapalong, Davao del Norte |  |  |  |  | b) | Nasol | b) | 04/06/16 | e) | 298 CD | b) | 108,303,841.70 | b) | 36.35% | d) | -8.915% | b) | 155 | Increase of contract price due to variation order & extra work
[7 empty] | c) | VICLAO | c) | 06/04/19 | f) | - | c) | 15496681.452 | [6 empty] | (P 4,992,633.27)
|  | 2.4 Rehab. Of Pob.-Limbaan-Suawon-Macgum |  | Roads | 8.93 kms./ | Contract. | a) | 190,253,491.98 | a) | CY 2015 | d) | - | a) | 190,253,491.98 | a) | 69.798% | c) | 26.646% | a) | 40 | On-going
|  | FMR w/ Bridge, New Corella, Davao del Norte |  |  | 42 ln.m |  | b) | Madrigal | b) | 04/08/16 | e) | 133 CD | b) | 190,253,491.98 | b) | 38.312% | d) | -11.67% | b) | 880 | Partially suspended (Bridge 1) dated 03/09/18
[7 empty] | c) | Dvo. Rock Mixer | c) | 06/01/19 | f) | - | c) | 28538091.3
3. KALSADA CY 2016
|  | 3.1 Improvement of Km. 9 Sagayen-Sawata Provincial |  | Roads | 9.09497km. | Contract. | a) | 60,329,230.72 | a) | CY 2015 | d) | - | a) | 60,329,230.72 | a) | 99.50% | c) | 35.74% | a) | 31 | On-going
|  | San Isidro, Davao del Norte |  |  |  |  | b) | Limpo | b) | 08/26/16 | e) | 73 CD | b) | 60,329,230.72 | b) | 72.55% | d) | -36.81% | b) | 837
|  | (Part of 60.329230.72M) (Contract Cost: P 43.597322.62M) |  |  |  |  | c) | ARN Builders. Inc. | c) | 04/21/18 | f) | - | c) | 6,539,598.39
(SB # 1 CY 2016 P 12.270446M)
| J. | 20% Development Fund CY 2016
|  | 1. Various of Water System Project (Provincewide) |  | Water | - | Admin | a) | 2,000,000.00 | [12 empty] | Investigation/Inspection of priority projects
|  |  |  | System |  |  | b) | Foronda/Ababon | [12 empty] | Balance as of March CY 2018 P 2,264,000.00
[7 empty] | c) | PEO
|  | 2. Counterpart to Special Projects (Provincewide) |  | Road | - | Admin | a) | 55,000,000.00 | [12 empty] | Investigation/Inspection of priority projects
[7 empty] | b) | Foronda
[7 empty] | c) | PEO
|  | 3. Const./Rehab./Comp. of Various Gov't. Bldgs. |  | Bldgs. | - | Admin | a) | 13,516,919.00 | [12 empty] | See projects listed below
|  | Struct., Fac. (Provincewide) |  |  |  |  | b) | Foronda
[7 empty] | c) | PEO
|  | 3.1 | Const. of Recreation Facilities Area Camp. | Bldgs. | - | Admin | a) | 52,088.00 | a) | - | d) | - | a) | 52,088.00 | a) | - | c) | - | a) | - | For implementation
|  |  | Gen. Manuel T. Yan Sr. Tuburan, Mawab |  |  |  | b) | - | b) | - | e) | - | b) | 52,088.00 | b) | - | d) | - | b) | -
[7 empty] | c) | PEO | c) | - | f) | - | c) | -
|  | 4. Rural Electrification (Provincewide) |  | Electrification |  | Admin | a) | 2,000,000.00 | [12 empty] | Investigation/Inspection of priority projects
[7 empty] | b) | Lu | [12 empty] | Balance as of March CY 2018 P 1,674,000.00
[7 empty] | c) | PEO
| K. | 5% Calamity Fund CY 2016
1. Prevention and Mitigation
|  | 1.1 | Revitment of Dike and Slope Protection | rivers |  | Admin | a) | 3,325,000.00 | [12 empty] | See project listed below
[7 empty] | b) | Paraguya/Matuguinas
[7 empty] | c) | PEO
|  | a | Prop. Slope Protection of Libuganon River |  |  | Admin | a) | 3,325,000.00 | a) | 03/06/17 | d) | - | a) | 3,325,000.00 | a) | - | c) | - | a) | - | For implementation
|  |  | Along Kapalong-Mabantao-Florida |  |  |  | b) | Paraguya/Matuguinas | b) | - | e) | - | b) | 3,325,000.00 | b) | - | d) | - | b) | -
|  |  | Provincial Road Ph.I (Capungagan- |  |  |  | c) | PEO | c) | - | f) | - | c) | 944,090.00
Mabantao Portion)
|  | 1.2 | Improvement of Bridges and Cross Drainage | Roads |  | Admin | a) | 2,900,000.00 | [12 empty] | Investigation/Inspection of priority projects
[7 empty] | b) | Paraguya/Matuguinas
[7 empty] | c) | PEO
|  | a | Rehab./Impv't. of Tungol Bridge Approach ''A" |  |  | Admin | a) | 2,900,000.00 | a) | 12/20/16 | d) | - | a) | 2,900,000.00 | a) | 91.14% | c) | 91.14% | a) | - | Suspended dated 12/08/17
|  |  | Along Kapalong-Mabantao-Florida Road |  |  |  | b) | Gone | b) | 09/18/17 | e) | - | b) | 2,900,000.00 | b) | - | d) | - | b) | -
[7 empty] | c) | PEO | c) | 01/04/18 | f) | - | c) | 1,300,630.32
| L. | SEF(Special Education Fund)-SUPPLEMENTAL BUDGET # 1 CY 2016
|  | 1 | Fabrication and Installation of Signage, | Ground |  | Admin | a) | 100,000.00 | a) | 10/15/17 | d) | - | a) | 100,000.00 | a) | - | c) | - | a) | - | For implementation
|  |  | DEPED, Mankilam, Tagum City |  |  |  | b) | - | b) | - | e) | - | b) | 100,000.00 | b) | - | d) | - | b) | -
[7 empty] | c) | PEO | c) | - | f) | - | c) | -
| M. | Supplemental Budget # 2 CY 2016 - PSWDO
|  | 1 | Ground Development at Women Dev't. Center | Ground |  | Admin | a) | 2,000,000.00 | a) | 09/16/17 | d) | - | a) | 2,000,000.00 | a) | - | c) | - | a) | - | Revision of POW (Concrete blocks Fabrication)
|  |  | New Corella, DDN |  |  |  | b) | - | b) | - | e) | - | b) | 2,000,000.00 | b) | - | d) | - | b) | -
[7 empty] | c) | PEO | c) | - | f) | - | c) | -
| N. | Trust Fund
1. PCF-Performance Challenge Fund-DILG
|  | 1.1 | Const./Rehab./Compl. Of Various Gov't. bldgs. | Bldgs. | - | Admin | a) | 4,000,000.00 | a) | CY 2016 | d) | - | a) | 4,000,000.00 | a) | 33.50% | c) | 34.25% | a) | 25 | On-going
|  |  | Structure and Fac. (Const. Of MPB and Perimeter |  |  |  | b) | Pasiona/Escurzon | b) | 02/15/18 | e) | - | b) | 4,000,000.00 | b) | - | d) | 0.75% | b) | 425
|  |  | Fence @ DAVNOR Senior High School |  |  |  | c) | PEO | c) | 10/15/18 | f) | - | c) | -
and Citizen Dev't. Compund),Mankilam
2. PRDP CY 2016
|  | 2.1 | Rehab. Of Sonlon-Camansa FMR, | Bldgs. | - | Admin | a) | 143,483,158.94 | a) | - | d) | - | a) | 143,483,158.94 | a) | - | c) | - | a) | - | For compliance of enabling documents and PRDP -
|  |  | Asuncion, Davao del Norte |  |  |  | b) | - | b) | - | e) | - | b) | 143,483,158.94 | b) | - | d) | - | b) | - | RPAB review and endorsement on March 20, 2018
[7 empty] | c) | PEO | c) | - | f) | - | c) | -
3. PAMANA-DILG CY 2016
|  | 3.1 | Construction of Civic Center, Madaum, Tagum City | Bldgs. | - | Contract | a) | 3,000,000.00 | a) | CY 2016 | d) | - | a) | 3,000,000.00 | a) | 24.94% | c) | 30.74% | a) | 10 | On-going
[7 empty] | b) | Escurzon | b) | 01/28/18 | e) | - | b) | 3,000,000.00 | b) | - | d) | 5.8% | b) | 170
[7 empty] | c) | SANTHONY | c) | 09/24/18 | f) | - | c)
|  | 3.2 | Construction of Civic Center, San Isidro, Tagum City | Bldgs. | - | Admin | a) | 2,000,000.00 | a) | CY 2016 | d) | - | a) | 2,000,000.00 | a) | - | c) | - | a) | - | Re-bidding
[7 empty] | b) | - | b) | 01/28/18 | e) | - | b) | 2,000,000.00 | b) | - | d) | - | b) | -
[7 empty] | c) | By Contract | c) | 09/24/18 | f) | - | c)
| O. | 20% Development Fund CY 2017 |  | Road Maintenance | KM |  | a) | 34562000.01
Road ID |  | 1. Repair & Maint. Of Various Prov'l. Roads and Bridges |  |  | 525.3 |  | b) | CY 2017 | [12 empty] | See list of Provincial Roads
[7 empty] | c) | Contract/CBRMC
11DAN
|  | Sta. Felomina-San Roque |  | Road Maintenance | 7.68 | CBRMC | a) | 86000 | a) | 01/06/17 | d) | - | a) | 86000 | a) | 33.33% | c) | 33.33% | a) |  | On-going
008 | [6 empty] | b) | Garcia | b) | 08/23/17 | e) | - | b) | 86000 | b) |  | d) |  | b)
[7 empty] | c) | STA. FELOMINA FARMERS | c) | 05/22/18 | f) | - | c)
|  | Semong-Palma Gil |  | Road Maintenance | 2.73 | MBC | a) | 140853.52 | a) | 01/06/17 | d) | - | a) | 140853.52 | a) | 68.13% | c) | 68.13% | a) |  | On-going
018 | [6 empty] | b) | Fabian | b) | 08/31/17 | e) | - | b) | 140853.52 | b) |  | d) |  | b)
[7 empty] | c) | MAG CORP. | c) | 05/31/18 | f) | - | c)
|  |  |  | Road Maintenance | 14.04 | CBRMC | a) | 144379.12 | a) | 01/04/17 | d) | - | a) | 55,810,000.00 | a) | 58.997% | c) | 58.997% | a) | - | On-going
009 |  | Jct. Sagayen-Sonlon |  |  |  |  | b) | Garcia | b) | 11/03/17 | e) | - | b) | 55,810,000.00 | b) | - | d) | - | b) | -
[7 empty] | c) | THE BEST VEGETABLE | c) | 03/30/18 | f) | - | c)
|  | Angelo - Dagohoy |  | Road Maintenance | 2.19 | MBC | a) | 98,590.119 | a) | 01/06/17 | d) | - | a) | 98,590.119 | a) | 58.997% | c) | 58.997% | a) |  | On-going
021 | [6 empty] | b) | Fabian | b) | 08/31/17 | e) | - | b) | 98,590.119 | b) |  | d) |  | b)
[7 empty] | c) | MAG CORP. | c) | 05/31/18 | f) | - | c)
|  | Sto. Niño - Daligdigon - Paiton |  | Road Maintenance | 11.6 | MBA | a) | 1046706.59 | a) | 01/03/18 | d) | - | a) | 1046706.59 | a) | 67.04% | c) | 67.04% | a) | - | On-going
023 | [6 empty] | b) | Fabian | b) | 08/31/17 | e) | - | b) | 1046706.59 | b) | - | d) | - | b) | -
[7 empty] | c) | Admin | c) | 05/31/18 | f) | - | c) | -
|  | Jct. New Boholano - New Loon (Revised) |  | Road Maintenance | 4.77 | CBRMC | a) | 82806.67 | a) | 01/04/17 | d) | - | a) | 82806.67 | a) | 66.67% | c) | 66.67% | a) |  | On-going
031 | [6 empty] | b) | Garcia | b) | 08/29/17 | e) | - | b) | 82806.67 | b) |  | d) |  | b)
[7 empty] | c) | NEW LOON FARMERS ASSOC. | c) | 05/28/18 | f) | - | c) | 3,000.00
|  | Florida-Suaon-Jct. Gupitan (Revised) |  | Road Maintenance | 15.57 | CBRMC | a) | 282388 | a) | 01/04/17 | d) | - | a) | 282388 | a) | 65.07% | c) | 65.07% | a) |  | On-going
032 | [6 empty] | b) | Garcia | b) | 08/16/17 | e) | - | b) | 282388 | b) |  | d) |  | b)
[7 empty] | c) | SUOAN UPLAND REFORESTRATION FARMERS | c) | 05/15/18 | f) | - | c)
|  | Sta. Fe-Mambing (Revised) |  | Road Maintenance | 10.96 | CBRMC | a) | 179473.9 | a) | 01/04/17 | d) | - | a) | 179473.9 | a) | 46.04% | c) | 46.04% | a) |  | On-going
046 | [6 empty] | b) | Garcia | b) | 08/22/17 | e) | - | b) | 179473.9 | b) |  | d) |  | b)
[7 empty] | c) | BUCARAN FARMERS | c) | 08/21/18 | f) | - | c)
|  | Limbaan-Sta. Fe-El Salvador (Revised) |  | Road Maintenance | 18.82 | CBRMC | a) | 322729.8 | a) | 01/04/17 | d) | - | a) | 322729.8 | a) | 66.67% | c) | 66.67% | a) |  | On-going
047 | [6 empty] | b) | Garcia | b) | 08/22/17 | e) | - | b) | 322729.8 | b) |  | d) |  | b)
[7 empty] | c) | BUCARAN FARMERS | c) | 05/21/18 | f) | - | c)
|  | Carcor - Patrocenio - Jct. Bayabas (Revised) |  | Road Maintenance | 14.68 | CBRMC | a) | 255850.7 | a) | 01/04/17 | d) | - | a) | 255850.7 | a) | 63.01% | c) | 63.01% | a) |  | On-going
057 | [6 empty] | b) | Garcia | b) | 08/15/17 | e) | - | b) | 255850.7 | b) |  | d) |  | b)
[7 empty] | c) | MOTOR OPERATORS DRIVERS ASSOC. | c) | 05/14/18 | f) | - | c)
|  | Carcor - Jct. Kauswagan (Revised) |  | Road Maintenance | 4.32 | MBC | a) | 373118.29 | a) | 01/04/17 | d) | - | a) | 373118.29 | a) | 70.32% | c) | 70.32% | a) |  | On-going
060 | [6 empty] | b) | Fabian | b) | 08/31/17 | e) | - | b) | 373118.29 | b) |  | d) |  | b)
[7 empty] | c) | MAG CORP. | c) | 05/31/18 | f) | - | c)
|  | Del Pilar - Prk. 9 Bagsak - San Jose |  | Road Maintenance | 4.99 | MBC | a) | 441410 | a) | 01/04/17 | d) | - | a) | 441410 | a) | 68.45% | c) | 68.45% | a) |  | On-going
061 | [6 empty] | b) | Fabian | b) | 08/31/17 | e) | - | b) | 441410 | b) |  | d) |  | b)
[7 empty] | c) | MAG CORP. | c) | 05/31/18 | f) | - | c)
|  | Del Pilar - El Unido |  | Road Maintenance | 1.32 | MBC | a) | 81857.8 | a) | 01/04/17 | d) | - | a) | 81857.8 | a) | 74.15% | c) | 74.15% | a) |  | On-going
062 | [6 empty] | b) | Fabian | b) | 08/31/17 | e) | - | b) | 81857.8 | b) |  | d) |  | b)
[7 empty] | c) | MAG CORP. | c) | 05/31/18 | f) | - | c)
|  | New Bohol - Jct. El Unido |  | Road Maintenance | 2.12 | MBC | a) | 190033.85 | a) | 01/04/17 | d) | - | a) | 190033.85 | a) | 55.93% | c) | 55.93% | a) |  | On-going
065 | [6 empty] | b) | Fabian | b) | 08/31/17 | e) | - | b) | 190033.85 | b) |  | d) |  | b)
[7 empty] | c) | MAG CORP. | c) | 05/31/18 | f) | - | c)
|  | New Corella - El Unido - Jct. Mesaoy |  | Road Maintenance | 8.63 | MBC | a) | 756773.87 | a) | 01/04/17 | d) | - | a) | 756773.87 | a) | 61.62% | c) | 61.62% | a) |  | On-going
066 | [6 empty] | b) | Fabian | b) | 08/31/17 | e) | - | b) | 756773.87 | b) |  | d) |  | b)
[7 empty] | c) | MAG CORP. | c) | 05/31/18 | f) | - | c)
|  | Jct. San Juan - Jct. Mesaoy (Revised) |  | Road Maintenance | 1.82 | MBC | a) | 184134.16 | a) | 01/04/17 | d) | - | a) | 184134.16 | a) | 61.98% | c) | 61.98% | a) |  | On-going
068 | [6 empty] | b) | Fabian | b) | 08/31/17 | e) | - | b) | 184134.16 | b) |  | d) |  | b)
[7 empty] | c) | MAG CORP. | c) | 05/31/18 | f) | - | c)
|  | Bdry. Tagum - Baca - New Corella (Revised) |  | Road Maintenance | 13.01 | CBRMC | a) | 137500 | a) | 01/04/17 | d) | - | a) | 137500 | a) | 68.63% | c) | 68.63% | a) |  | On-going
071 | [6 empty] | b) | Garcia | b) | 06/15/17 | e) | - | b) | 137500 | b) |  | d) |  | b)
[7 empty] | c) | DURIAN DACUDAO ASSOC. | c) | 12/31/17 | f) | - | c)
|  | 2. Const./Rehab./Comp. of Various Gov't. Bldgs. |  | Bldgs. | - | Admin | a) | 9,000,000.00 | [12 empty] | Investigation/Inspection of priority projects
|  | Struct., Fac. (Provincewide) |  |  |  |  | b) | Foronda/Ababon | [12 empty] | Balance as of March CY 2018 P 5,530,000.00
[7 empty] | c) | PEO
|  | 2.1 | Upgrading of DDNSTC Fencing and |  |  | Admin | a) | 2270000 | a) | 09/16/17 | d) | - | a) | 2270000 | a) | 47.37% | c) | 49.71% | a) | - | On-going
|  |  | Pavement (Commercial Building), |  |  |  | b) | Pasiona | b) | 04/02/18 | e) | - | b) | 2270000 | b) | - | d) | +2.34% | b) | -
|  |  | Sports Center, Mankilam, Tagum City |  |  |  | c) | PEO | c) | 05/31/18 | f) | - | c) | -
|  | 3. Various of Water System Project (Provincewide) |  | Water | - | Admin | a) | 5,000,000.00 | [12 empty] | Investigation/Inspection of priority projects
|  |  |  | System |  |  | b) | Foronda/Ababon | [12 empty] | Balance as of March CY 2018 P 5,000,000.00
[7 empty] | c) | PEO
|  | 4. Counterpart to Special Projects (Provincewide) |  | Road | - | Admin | a) | 55,810,000.00 | [12 empty] | Investigation/Inspection of priority projects
[7 empty] | b) | Foronda/Ababon
[7 empty] | c) | PEO
|  | 5. Rural Electrification (Provincewide) |  | Electrification |  | Admin | a) | 5,000,000.00 | [12 empty] | Investigation/Inspection of priority projects
[7 empty] | b) | Lu
[7 empty] | c) | PEO
6. Residential Care Facilities - PSWDO
|  | 6.1 | Expansion of Residential Fac. For Minors | Bldgs. |  | Admin | a) | 1,500,000.00 | a) | 09/16/17 | d) | - | a) | 1,500,000.00 | a) | 79.47% | c) | 77.34% | a) | 11 | On-going
|  |  | Ph.II, New Corella |  |  |  | b) | Gone | b) | 01/29/17 | e) | - | b) | 1,500,000.00 | b) | - | d) | -2.13% | b) | 187
[7 empty] | c) | PEO | c) | 06/07/18 | f) | - | c) | -
| P. | 5% Calamity Fund CY 2017
1. Prevention and Mitigation
|  | 1.1 Revitment of Dike and Slope Protection |  | rivers |  | Admin | a) | 3,025,000.00 | [12 empty] | See project listed below
[7 empty] | b) | Paraguya/Matuguinas
[7 empty] | c) | PEO
|  | a | Prop. Slope Protection of Libuganon River |  |  | Admin | a) | 1,741,000.00 | a) | 03/06/17 | d) | - | a) | 1,741,000.00 | a) | - | c) | - | a) | - | For implementation
|  |  | Along Kapalong-Mabantao-Florida |  |  |  | b) | - | b) | - | e) | - | b) | 1,741,000.00 | b) | - | d) | - | b) | -
|  |  | Provincial Road Ph.I (Capungagan- |  |  |  | c) | PEO | c) | - | f) | - | c) | -
Mabantao Portion)
|  | b | Inst. Of Suaon-Gupitan Slope Protection |  |  | Admin | a) | 1,284,000.00 | a) | 03/29/17 | d) | - | a) | 1,284,000.00 | a) | 35.07% | c) | 29.32% | a) | 22 | On-going
|  |  | (Part of 3.325M) |  |  |  | b) | Gone | b) | 02/16/18 | e) | - | b) | 1,284,000.00 | b) | - | d) | -5.75% | b) | 374
[7 empty] | c) | PEO | c) | 05/28/18 | f) | - | c) | -
|  | 1.2 Improvement of roads and canal |  | rivers |  | Admin | a) | 3,000,000.00 | [12 empty] | Investigation/Inspection of priority projects
[7 empty] | b) | Paraguya/Matuguinas
[7 empty] | c) | PEO
|  | a | Rehab./Impv't. of Cross Drainage Along |  |  | Admin | a) | 800,000.00 | a) | - | d) | - | a) | 800,000.00 | a) | - | c) | - | a) | - | For implementation
|  |  | Florida-Suaon Jct. Gupitan Provincial |  |  |  | b) | - | b) | - | e) | - | b) | 800,000.00 | b) | - | d) | - | b) | -
|  |  | Road (with Canal), Kapalong |  |  |  | c) | PEO | c) | - | f) | - | c) | -
|  | 1.3 Improvement of bridges and cross drainage |  | rivers |  | Admin | a) | 3,500,000.00 | [12 empty] | Investigation/Inspection of priority projects
[7 empty] | b) | Paraguya/Matuguinas
[7 empty] | c) | PEO
| Q. | PSWDO-ANNUAL BUDGET CY 2017
|  | (Const. in Progress Bldgs & Other Struct.) |  | Bldgs. |  | Admin | a) | 3,500,000.00 | [12 empty] | See projects listed below
[7 empty] | b) | Paraguya/Matuguinas
[7 empty] | c) | PEO
|  | 1.1 | Completion/Repair of Day Care Center, | Bldgs. |  | Admin | a) | 300,000.00 | a) | - | d) | - | a) | 300,000.00 | a) | 16.85% | c) | 17.00% | a) | - | On-going
|  |  | San Vicente, Asuncion |  |  |  | b) | - | b) | 04/16/18 | e) | - | b) | 300,000.00 | b) | - | d) | 0.15% | b) | -
[7 empty] | c) | PEO | c) | 06/15/18 | f) | - | c) | -
|  | 1.2 | Completion/Repair of Day Care Center, | Bldgs. |  | Admin | a) | 300,000.00 | a) | - | d) | - | a) | 300,000.00 | a) | - | c) | - | a) | - | waiting for the delivery of materials
|  |  | Sta. Fe, New Corella |  |  |  | b) | - | b) | - | e) | - | b) | 300,000.00 | b) | - | d) | - | b) | -
[7 empty] | c) | PEO | c) | - | f) | - | c) | -
|  | 1.3 | Construction of 1 Unit Day Care Center, | Bldgs. |  | Admin | a) | 1,000,000.00 | a) | - | d) | - | a) | 1,000,000.00 | a) | - | c) | - | a) | - | waiting for the delivery of materials
|  |  | El Salvador, New Corella |  |  |  | b) | - | b) | - | e) | - | b) | 1,000,000.00 | b) | - | d) | - | b) | -
[7 empty] | c) | PEO | c) | - | f) | - | c) | -
| R. | SEF(Special Education Fund)-ANNUAL BUDGET CY 2017
|  | 1. Const./Impv't./Compl. Of School Bldgs., Struc. & Fac. |  | Bldgs. |  | Admin | a) | 4,055,000.00 | [12 empty] | See projects listed below
[7 empty] | b) | Foronda/Ababon
[7 empty] | c) | PEO
|  | 1.1 | Construction of Covered Court at Maniki ES, Kapalong | Bldgs. |  | Admin | a) | 3,041,000.00 | a) | 05/26/17 | d) | - | a) | 3,041,000.00 | a) | 15.60% | c) | 16.21% | a) | 15 | On-going
|  |  | Kapalong |  |  |  | b) | Avila | b) | 03/01/18 | e) | - | b) | 3,041,000.00 | b) | - | d) | 0.61% | b) | 255
[7 empty] | c) | PEO | c) | 07/31/18 | f) | - | c) | 1,699,648.00
|  | 1.2 | Const./impv't. of 5-Classroom Ph. 2, New Corella, | Bldgs. |  | Admin | a) | 554,662.99 | a) | - | d) | - | a) | 554,662.99 | a) | - | c) | - | a) | - | Waiting for the complete delivery of materials
|  |  | Central ES |  |  |  | b) | - | b) | - | e) | - | b) | 554,662.99 | b) | - | d) | - | b) | -
[7 empty] | c) | PEO | c) | - | f) | - | c) | -
| S. | SEF(Special Education Fund)-SUPPLEMENTAL BUDGET # 1 CY 2017
|  | 1. Const./Impv't./Compl. Of School Bldgs., Struc. & Fac. |  | Bldgs. |  | Admin | a) | 3,300,000.00 | [12 empty] | See projects listed below
[7 empty] | b) | Foronda
[7 empty] | c) | PEO
|  | 1.1 | Construction of 1 unit School Building, | Bldgs. |  | Admin | a) | 1100000 | a) | 02/21/18 | d) | - | a) | 1100000 | a) | - | c) | - | a) | - | Waiting for the complete delivery of materials
|  |  | Dagohoy ES, Talaingod |  |  |  | b) | - | b) | - | e) | - | b) | 1100000 | b) | - | d) | - | b) | -
[7 empty] | c) | PEO | c) | - | f) | - | c) | -
|  | 1.2 | Construction of 1 unit School Building | Bldgs. |  | Admin | a) | 1100000 | a) | 02/21/18 | d) | - | a) | 1100000 | a) | - | c) | - | a) | - | PO on process
|  |  | Lumabag, Talaingod |  |  |  | b) | - | b) | - | e) | - | b) | 1100000 | b) | - | d) | - | b) | -
[7 empty] | c) | PEO | c) | - | f) | - | c) | -
|  | 1.3 | Construction of 1 unit School Building | Bldgs. |  | Admin | a) | 1100000 | a) | 02/21/18 | d) | - | a) | 1100000 | a) | - | c) | - | a) | - | PO on process
|  |  | Mangguangan ES, Mambing New Corella |  |  |  | b) | - | b) | - | e) | - | b) | 1100000 | b) | - | d) | - | b) | -
[7 empty] | c) | PEO | c) | - | f) | - | c) | -
| T. | Supplemental Budget # 3 CY 2017
|  | 1. Disaster Rehabilitation & Recovery |  | Bldgs. |  | Admin | a) | 8,292,611.00 | [12 empty] | See project listed below
[7 empty] | b) | Paraguya/Matuguinas
[7 empty] | c) | PEO
|  | 1.1 | Rehabilitation of Capungagan-Boundary San Miguel | Bldgs. |  | Admin | a) | 3,132,611.00 | a) | 09/19/17 | d) | 22 CD | a) | 3,132,611.00 | a) | 17.48% | c) | 15.59% | a) | - | Resume dated April 2, 2018
|  |  | FMR (Road Re-alignment)(Revised) |  |  |  | b) | Gone | b) | 12/01/17 | e) | - | b) | 3,132,611.00 | b) | - | d) | -1.89% | b) | - | On-going
[7 empty] | c) | PEO | c) | 07/08/18 | f) | - | c) | 1,207,781.20
2. Purchased, Const. & Imprv't. of Gov't. Facilities (8918)
a) Const./Compl./Imprvt. of Various Gov't. Bldgs.
Structures & Facilities
|  | 1.1 | Improvement of Barangay Hall, | Bldgs. |  | Contract/ | a) | 500000 | a) | 11/29/17 | d) | - | a) | 500000 | a) | - | c) | - | a) | - | PR on process
|  |  | Brgy. Magdum, Tagum |  |  |  | b) | - | b) | - | e) | - | b) | 500000 | b) | - | d) | - | b) | -
[7 empty] | c) | PEO | c) | - | f) | - | c) | -
|  | 1.2 | Rehabilitation of Sawata Gymnasium, | Bldgs. |  | Contract/ | a) | 500000 | a) | 11/29/17 | d) | - | a) | 500000 | a) | - | c) | - | a) | - | PR on process
|  |  | San Isidro |  |  |  | b) | - | b) | - | e) | - | b) | 500000 | b) | - | d) | - | b) | -
[7 empty] | c) | PEO | c) | - | f) | - | c) | -
|  | 1.3 | Const. of Brgy. Stage, Linao, San Isidro | Bldgs. |  | Contract/ | a) | 500000 | a) | 11/29/17 | d) | - | a) | 500000 | a) | - | c) | - | a) | - | PR on process
[7 empty] | b) | - | b) | - | e) | - | b) | 500000 | b) | - | d) | - | b) | -
[7 empty] | c) | PEO | c) | - | f) | - | c) | -
|  | 1.4 | Improvement of Barangay hall Preimeter | Bldgs. |  | Contract/ | a) | 500000 | a) | - | d) | - | a) | 500000 | a) | - | c) | - | a) | - | PO on process
|  |  | Fence, Brgy. Dakudao, San Isidro |  |  |  | b) | - | b) | - | e) | - | b) | 500000 | b) | - | d) | - | b) | -
[7 empty] | c) | PEO | c) | - | f) | - | c) | -
|  | 1.5 | Const. of Cvd. Court, Datu Balong,San Isidro | Bldgs. |  | Contract/ | a) | 500000 | a) | - | d) | - | a) | 500000 | a) | - | c) | - | a) | - | PR on process
[7 empty] | b) | - | b) | - | e) | - | b) | 500000 | b) | - | d) | - | b) | -
[7 empty] | c) | PEO | c) | - | f) | - | c) | -
|  | 1.6 | Completion of Multi-Purpose Building | Bldgs. |  | Contract/ | a) | 500000 | a) | - | d) | - | a) | 500000 | a) | - | c) | - | a) | - | PR on process
|  |  | Kipalili, San isidro |  |  |  | b) | - | b) | - | e) | - | b) | 500000 | b) | - | d) | - | b) | -
[7 empty] | c) | PEO | c) | - | f) | - | c) | -
|  | 1.7 | Improvement of Covered Court (Bleachers | Bldgs. |  | Contract/ | a) | 500000 | a) | - | d) | - | a) | 500000 | a) | - | c) | - | a) | - | PR on process
|  |  | with Roofing), Libuton, San Isidro |  |  |  | b) | - | b) | - | e) | - | b) | 500000 | b) | - | d) | - | b) | -
[7 empty] | c) | PEO | c) | - | f) | - | c) | -
|  | 1.8 | Improvement of Gabuyan Covered Court, | Bldgs. |  | Barangay | a) | 500000 | a) | 12/07/17 | d) | - | a) | 500000 | a) | - | c) | - | a) | - | Fund transfer on process
|  |  | Brgy. Gabuyan, Kapalong |  |  |  | b) | - | b) | - | e) | - | b) | 500000 | b) | - | d) | - | b) | -
[7 empty] | c) | PEO | c) | - | f) | - | c) | -
|  | 1.9 | Construction of Concrete Bleacher, | Bldgs. |  | Barangay | a) | 500000 | a) | - | d) | - | a) | 500000 | a) | - | c) | - | a) | - | Check for advice with ChecK No. 2445012
|  |  | Brgy. Tiburcia, Kapalong |  |  |  | b) | - | b) | - | e) | - | b) | 500000 | b) | - | d) | - | b) | -
[7 empty] | c) | PEO | c) | - | f) | - | c) | -
|  | 2 | Improvement of Covered Court, | Bldgs. |  | Barangay | a) | 500000 | a) | 12/07/17 | d) | - | a) | 500000 | a) | - | c) | - | a) | - | Fund transfer on process
|  |  | Brgy. Pag-Asa, kapalong |  |  |  | b) | - | b) | - | e) | - | b) | 500000 | b) | - | d) | - | b) | -
[7 empty] | c) | PEO | c) | - | f) | - | c) | -
|  | 2.1 | Covered Court Bleacher, | Bldgs. |  | Barangay | a) | 500000 | a) | - | d) | - | a) | 500000 | a) | - | c) | - | a) | - | Fund transfer on process
|  |  | Brgy. Katipunan, Kapalong |  |  |  | b) | - | b) | - | e) | - | b) | 500000 | b) | - | d) | - | b) | -
[7 empty] | c) | PEO | c) | - | f) | - | c) | -
|  | 2.2 | Completion of Covered Court/Gym, | Bldgs. |  | Barangay | a) | 500000 | a) | 12/28/17 | d) | - | a) | 500000 | a) | - | c) | - | a) | - | Fund transfer on process
|  |  | Mambing, New Corella |  |  |  | b) | - | b) | - | e) | - | b) | 500000 | b) | - | d) | - | b) | -
[7 empty] | c) | PEO | c) | - | f) | - | c) | -
|  | 2.3 | Barangay Hall, New Sambog, New Corella | Bldgs. |  | Barangay | a) | 500000 | a) | - | d) | - | a) | 500000 | a) | - | c) | - | a) | - | Fund transfer on process
[7 empty] | b) | - | b) | - | e) | - | b) | 500000 | b) | - | d) | - | b) | -
[7 empty] | c) | PEO | c) | - | f) | - | c) | -
|  | 2.4 | Construction of Concrete Fence of | Bldgs. |  | Barangay | a) | 500000 | a) | 12/28/17 | d) | - | a) | 500000 | a) | - | c) | - | a) | - | Fund transfer on process
|  |  | Lataban ES, Del Monte, New Corella |  |  |  | b) | - | b) | - | e) | - | b) | 500000 | b) | - | d) | - | b) | -
[7 empty] | c) | PEO | c) | - | f) | - | c) | -
|  | 2.5 | Construction of Stage, Canocotan, | Bldgs. |  | Contract/ | a) | 500000 | a) | 12/28/17 | d) | - | a) | 500000 | a) | - | c) | - | a) | - | PR on process
|  |  | Tagum City |  |  |  | b) | - | b) | - | e) | - | b) | 500000 | b) | - | d) | - | b) | -
[7 empty] | c) | PEO | c) | - | f) | - | c) | -
|  | 2.6 | Const. of Intake Box & Water | Bldgs. |  | Contract/ | a) | 500000 | a) | 12/28/17 | d) | - | a) | 500000 | a) | - | c) | - | a) | - | PR on process
|  |  | Impdng, Monte Dujali, |  |  |  | b) | - | b) | - | e) | - | b) | 500000 | b) | - | d) | - | b) | -
[7 empty] | c) | PEO | c) | - | f) | - | c) | -
|  | 2.8 | Construction of Guidance Office, | Bldgs. |  | Barangay | a) | 350000 | a) | 12/28/17 | d) | - | a) | 350000 | a) | - | c) | - | a) | - | Check for advice with ChecK No. 2445324
|  |  | Bunawan ES, Brgy. Semong, Kapalong |  |  |  | b) | - | b) | - | e) | - | b) | 350000 | b) | - | d) | - | b) | -
[7 empty] | c) | PEO | c) | - | f) | - | c) | -
|  | 3 | Const. of Cvd. Court Ph. 1, Sta. Filomena, | Bldgs. |  | Barangay | a) | 500000 | a) | 12/29/17 | d) | - | a) | 500000 | a) | - | c) | - | a) | - | Fund already transferred at Municipality of
|  |  | Asuncion |  |  |  | b) | - | b) | - | e) | - | b) | 500000 | b) | - | d) | - | b) | - | Asuncion with ChecK No. 2445177
[7 empty] | c) | PEO | c) | - | f) | - | c) | - | [6 empty] | Date released 03/19/18
|  | 3.1 | Impvt. of Brgy. Hall/Cvd. Court, Buclad, | Bldgs. |  | Barangay | a) | 500000 | a) | 12/28/17 | d) | - | a) | 500000 | a) | - | c) | - | a) | - | Fund transfer on process
|  |  | Asuncion |  |  |  | b) | - | b) | - | e) | - | b) | 500000 | b) | - | d) | - | b) | -
[7 empty] | c) | PEO | c) | - | f) | - | c) | -
|  | 3.2 | Const. of MP Pavement, Florida, Kapalong | Bldgs. |  | Barangay | a) | 500000 | a) | 12/29/17 | d) | - | a) | 500000 | a) | - | c) | - | a) | - | Check for advice with ChecK No. 2445175
[7 empty] | b) | - | b) | - | e) | - | b) | 500000 | b) | - | d) | - | b) | -
[7 empty] | c) | PEO | c) | - | f) | - | c) | -
|  | 3.3 | Fabrication of Bleachers, New Cortes, New Corella | Bldgs. |  | Barangay | a) | 500000 | a) | 12/28/17 | d) | - | a) | 500000 | a) | - | c) | - | a) | - | Fund transfer on process
[7 empty] | b) | - | b) | - | e) | - | b) | 500000 | b) | - | d) | - | b) | -
[7 empty] | c) | PEO | c) | - | f) | - | c) | -
|  | 3.4 | Renov. of Brgy. Hall., Patrocenio, New Corella | Bldgs. |  | Barangay | a) | 500000 | a) | 12/20/17 | d) | - | a) | 500000 | a) | - | c) | - | a) | - | Fund transfer on process
[7 empty] | b) | - | b) | - | e) | - | b) | 500000 | b) | - | d) | - | b) | -
[7 empty] | c) | PEO | c) | - | f) | - | c) | -
|  | 3.5 | Completion of Magatos E/S Perimeter | Bldgs. |  | Barangay | a) | 500000 | a) | 12/28/17 | d) | - | a) | 500000 | a) | - | c) | - | a) | - | Fund already transferred at Municipality of
|  |  | Fence, Asuncion |  |  |  | b) | - | b) | - | e) | - | b) | 500000 | b) | - | d) | - | b) | - | Asuncion with ChecK No. 2445178
[7 empty] | c) | PEO | c) | - | f) | - | c) | - | [6 empty] | Date released 03/19/18
|  | b) Water System Development Projects |  | Bldgs. |  | Admin/ | [14 empty] | See projects listed below
Contract/
Barangay
|  | 1.1 | Rehabilitation of Potable Water System, | Bldgs. |  | Contract | a) | 500000 | a) | 12/28/17 | d) | - | a) | 500000 | a) | - | c) | - | a) | - | PR on process
|  |  | Brgy. San Miguel, San Isidro |  |  |  | b) | - | b) | - | e) | - | b) | 500000 | b) | - | d) | - | b) | -
[7 empty] | c) | PEO | c) | - | f) | - | c) | -
|  | 1.2 | Inst. Of Mainline Pipe for PWS, | Bldgs. |  | Barangay | a) | 500000 | a) | 12/07/17 | d) | - | a) | 500000 | a) | - | c) | - | a) | - | Check for advice with ChecK No. 2445011
|  |  | Brgy. Mabantao, Kapalong |  |  |  | b) | - | b) | - | e) | - | b) | 500000 | b) | - | d) | - | b) | -
[7 empty] | c) | PEO | c) | - | f) | - | c) | -
|  | 1.3 | Rehabilitation of Potable Water System, | Bldgs. |  | Barangay | a) | 500000 | a) | 12/28/17 | d) | - | a) | 500000 | a) | - | c) | - | a) | - | Fund already transferred at Municipality of
|  |  | New Loon, Asuncion |  |  |  | b) | - | b) | - | e) | - | b) | 500000 | b) | - | d) | - | b) | - | Asuncion with ChecK No. 2445175
[7 empty] | c) | PEO | c) | - | f) | - | c) | - | [6 empty] | Date released 03/19/18
|  | 1.4 | Construction of Water Reservoir & | Bldgs. |  | Contract | a) | 500000 | a) | 12/28/17 | d) | - | a) | 500000 | a) | - | c) | - | a) | - | Fund already transferred at Municipality of
|  |  | Purchase of P.E. Pipes, Sagayen |  |  |  | b) | - | b) | - | e) | - | b) | 500000 | b) | - | d) | - | b) | - | Asuncion with ChecK No. 2445174
[7 empty] | c) | PEO | c) | - | f) | - | c) | - | [6 empty] | Date released 03/19/18
|  | c) Roads |  | Bldgs. |  | Admin/ | [14 empty] | See projects listed below
Contract
|  | 1.1 | Repair of Solar Dryer, Purok 5, | Bldgs. |  | Barangay | a) | 150000 | a) | 12/28/17 | d) | - | a) | 150000 | a) | - | c) | - | a) | - | Waiting to Municipality of Kapalong to claim | CHECK RELEASE 04/18/18
|  |  | Brgy. Semong, Kapalong |  |  |  | b) | - | b) | - | e) | - | b) | 150000 | b) | - | d) | - | b) | - | the check with check No. 2445324
[7 empty] | c) | PEO | c) | - | f) | - | c) | -
|  | 1.2 | FMR 0.50 Km. at Brgy. Site, Sonlon, Asuncion | Bldgs. |  | Barangay | a) | 500000 | a) | 12/28/17 | d) | - | a) | 500000 | a) | - | c) | - | a) | - | Fund already transferred at Municipality of
[7 empty] | b) | - | b) | - | e) | - | b) | 500000 | b) | - | d) | - | b) | - | Asuncion with ChecK No. 2445173
[7 empty] | c) | PEO | c) | - | f) | - | c) | - | [6 empty] | Date released 03/19/18
|  | 1.3 | Road Rehab. @ P1-5, Sta Fe, New Corella | Bldgs. |  | Barangay | a) | 500000 | a) | 12/28/17 | d) | - | a) | 500000 | a) | - | c) | - | a) | - | Fund tranfer on process
[7 empty] | b) | - | b) | - | e) | - | b) | 500000 | b) | - | d) | - | b) | -
[7 empty] | c) | PEO | c) | - | f) | - | c) | -
|  | d) Rural Electrification |  | Bldgs. |  | Admin/ | [14 empty] | See projects listed below
Contract/
Barangay
|  | 1.1 | Electrification @ P1A-P5A, Palma Gil, Talaingod | Bldgs. |  | Barangay | a) | 500000 | a) | 12/28/17 | d) | - | a) | 500000 | a) | - | c) | - | a) | - | Fund tranfer on process
[7 empty] | b) | - | b) | - | e) | - | b) | 500000 | b) | - | d) | - | b) | -
[7 empty] | c) | PEO | c) | - | f) | - | c) | -
| U. | Trust Fund
1. CMGP (Conditional Matching Grant to Provinces)
|  | 1.1 | Road Upgrading km.9 sagayen-Sawata | Bldgs. | 10.20 km | Admin | a) | 153568795.26 | a) | CY 2017 | d) | - | a) | 153568795.26 | a) | - | c) | - | a) | - | Waiting for final validation
|  |  | (Sagayen-Jct. San Miguel Section) |  |  |  | b) | Pasiona/Escurzon | b) | - | e) | - | b) | 153568795.26 | b) | - | d) | - | b) | -
[7 empty] | c) | PEO | c) | - | f) | - | c) | -
|  | 1.2 | Road Upgrading of Dagohoy - Daligdigon | Bldgs. | 3.33 km | Admin | a) | 58048310.68 | a) | CY 2017 | d) | - | a) | 58048310.68 | a) | 11.035% | c) | 7.034% | a) | - | On-going
|  |  | Provincial Road |  |  |  | b) | Fabiala | b) | 01/05/18 | e) | - | b) | 58048310.68 | b) | - | d) | -4.001% | b) | -
[7 empty] | c) | PEO | c) | 09/07/18 | f) | - | c) | -
II. PROJECTS UNDER THE CURRENT APPROPRIATION | [5 empty] | Admin
A. 20% Development Fund CY 2018 |  |  |  | Road Maintenance | KM | Contract | a) | 36268943 | a) | 01/03/18 | d) | - | a) | 36268943 | a) | 7.51% | c) | 9.14% | a) | 46 | See list of Provincial Roads
Road ID |  | 1. Repair & Maint. Of Various Prov'l. Roads and Bridges |  |  | 525.3 | CBRMC | b) | Paraguya | b) | 01/03/18 | e) | - | b) | 36268943 | b) | - | d) | - | b) | 920
[6 empty] | Contract with CBRMC | c) | PEO/Contract/CBRMC | c) | 12/31/18 | f) | - | c)
11DAN
|  | Jct. Highway Magatos - New Bantayan |  | Road Maintenance | 7.1 | MBA | a) | 418937.54 | a) | 01/03/18 | d) | - | a) | 418937.54 | a) | 66.51% | c) | 66.51% | a) | 14 | On-going
001 | [6 empty] | b) | Pilotos | b) | 01/16/18 | e) | - | b) | 418937.54 | b) | - | d) | - | b) | 20
[7 empty] | c) | Admin | c) | 12/31/18 | f) | - | c) | 295552
|  | Jct. Highway Magatos - New Bantayan |  | Road Maintenance | 7.1 | CBRMC | a) | 252637.44 | a) | 01/03/18 | d) | - | a) | 252637.44 | a) | - | c) | - | a) | - | Procurement on process
001 | [6 empty] | b) | Garcia | b) | - | e) | - | b) | 252637.44 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | f) | - | c)
|  | Magatos-Bdry Pagsabangan |  | Road Maintenance | 8.33 | MBA | a) | 787918.25 | a) | 01/03/18 | d) | - | a) | 787918.25 | a) | - | c) | - | a) | - | Schedule for 2nd Quarter
002 | [6 empty] | b) | Pilotos | b) | - | e) | - | b) | 787918.25 | b) | - | d) | - | b) | -
[7 empty] | c) | Admin | c) | - | f) | - | c)
|  | Ilog-New Bantayan |  | Road Maintenance | 2.68 | MBA | a) | 258988.12 | a) | 01/03/18 | d) | - | a) | 258988.12 | a) | - | c) | - | a) | - | Schedule for 2nd Quarter
003 | [6 empty] | b) | Pilotos | b) | - | e) | - | b) | 258988.12 | b) | - | d) | - | b) | -
[7 empty] | c) | Admin | c) | - | f) | - | c)
|  | Asuncion-New Alegria-Bdry. Cuambogan |  | Road Maintenance | 6.66 | MBA | a) | 520844.38 | a) | 01/03/18 | d) | - | a) | 520844.38 | a) | 42.6% | c) | 42.6% | a) | 14 | On-going
004 | [6 empty] | b) | Pilotos | b) | 01/16/18 | e) | - | b) | 520844.38 | b) | - | d) | - | b) | 30
[7 empty] | c) | Admin | c) | 12/31/18 | f) | - | c) | 61922.05
|  |  |  | Road Maintenance | 7.93 | MBA | a) | 824313.93 | a) | 01/03/18 | d) | - | a) | 824313.93 | a) | 38.28% | c) | 38.28% | a) | 14 | On-going
005 |  | Asuncion -Monte Carlo-Del Pilar |  |  |  |  | b) | Pilotos | b) | 01/16/18 | e) | - | b) | 824313.93 | b) | - | d) | - | b) | 30
[7 empty] | c) | Admin | c) | 12/31/18 | f) | - | c) | 90,625.01
|  |  |  | Road Maintenance | 7.93 | CBRMC | a) | 266051.82 | a) | 01/03/18 | d) | - | a) | 795747.7 | a) | - | c) | - | a) | - | Procurement on process
005 |  | Asuncion -Monte Carlo-Del Pilar |  |  |  |  | b) | Garcia | b) | - | e) | - | b) | 795747.7 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | f) | - | c)
|  |  |  | Road Maintenance | 4.85 | MBA | a) | 314877.28 | a) | 01/03/18 | d) | - | a) | 314877.28 | a) | 34.11% | c) | 34.11% | a) | 14 | On-going
006 |  | Jct. Highway Canatan-Jct. Highway Magatos |  |  |  |  | b) | Pilotos | b) | 01/03/18 | e) | - | b) | 314877.28 | b) | - | d) | - | b) | 30
[7 empty] | c) | Admin | c) | 12/31/18 | f) | - | c) | 108682.23
|  |  |  | Road Maintenance | 4.85 | CBRMC | a) | 176386.91 | a) | 01/03/18 | d) | - | a) | 178322.84 | a) | - | c) | - | a) | - | Procurement on process
006 |  | Jct. Highway Canatan-Jct. Highway Magatos |  |  |  |  | b) | Garcia | b) | - | e) | - | b) | 178322.84 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | f) | - | c)
|  |  |  | Road Maintenance | 4.34 | MBA | a) | 370785.06 | a) | 01/03/18 | d) | - | a) | 370785.06 | a) | - | c) | - | a) | - | Schedule for 2nd Quarter
007 |  | Jct. Highway Cantan-Doñatan |  |  |  |  | b) | Pilotos | b) | - | e) | - | b) | 370785.06 | b) | - | d) | - | b) | -
[7 empty] | c) | Admin | c) | - | f) | - | c) | -
|  |  |  | Road Maintenance | 7.68 | MBA | a) | 464855.67 | a) | 01/03/18 | d) | - | a) | 464855.67 | a) | - | c) | - | a) | - | Schedule for 2nd Quarter
008 |  | Sta. Felomina-San Roque |  |  |  |  | b) | Pilotos | b) | - | e) | - | b) | 464855.67 | b) | - | d) | - | b) | -
[7 empty] | c) | Admin | c) | - | f) | - | c) | -
|  |  |  | Road Maintenance | 7.68 | CBRMC | a) | 261580.36 | a) | 01/03/18 | d) | - | a) | 118631.69 | a) | - | c) | - | a) | - | Procurement on process
008 |  | Sta. Felomina-San Roque |  |  |  |  | b) | Garcia | b) | - | e) | - | b) | 118631.69 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | f) | - | c)
|  |  |  | Road Maintenance | 14.04 | MBA | a) | 852654.3 | a) | 01/03/18 | d) | - | a) | 852654.3 | a) | 60.60% | c) | 60.60% | a) | 14 | On-going
009 |  | Jct. Sagayen-Sonlon |  |  |  |  | b) | Pilotos | b) | 03/16/18 | e) | - | b) | 852654.3 | b) | - | d) | - | b) | 30
[7 empty] | c) | Admin | c) | 12/31/18 | f) | - | c) | 66318.9
|  |  |  | Road Maintenance | 14.04 | CBRMC | a) | 469503.22 | a) | 01/03/18 | d) | - | a) | 209009.02 | a) | - | c) | - | a) | - | Procurement on process
009 |  | Jct. Sagayen-Sonlon |  |  |  |  | b) | Garcia | b) | - | e) | - | b) | 209009.02 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | f) | - | c)
|  |  |  | Road Maintenance | 11.6 | MBA | a) | 991038.41 | a) | 01/03/18 | d) | - | a) | 991038.41 | a) | - | c) | - | a) | - | Schedule for 2nd Quarter
010 |  | Saug-Sonlon-Bdy Longanapan |  |  |  |  | b) | Pilotos | b) | - | e) | - | b) | 991038.41 | b) | - | d) | - | b) | -
[7 empty] | c) | Admin | c) | - | f) | - | c) | -
|  |  |  | Road Maintenance | 2.99 | MBA | a) | 112001.5 | a) | 01/03/18 | d) | - | a) | 112001.5 | a) | 47.30% | c) | 47.30% | a) | 14 | On-going
011 |  | Jct. New Visayas-Buan |  |  |  |  | b) | Pilotos | b) | 02/01/18 | e) | - | b) | 112001.5 | b) | - | d) | - | b) | 28
[7 empty] | c) | Admin | c) | 12/31/18 | f) | - | c) | 1500
|  |  |  | Road Maintenance | 2.99 | CBRMC | a) | 125200.86 | a) | 01/03/18 | d) | - | a) | 43510.49 | a) | - | c) | - | a) | - | Procurement on process
011 |  | Jct. New Visayas-Buan |  |  |  |  | b) | Garcia | b) | - | e) | - | b) | 43510.49 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | f) | - | c)
|  |  |  | Road Maintenance | 7.07 | MBA | a) | 586189.45 | a) | 01/03/18 | d) | - | a) | 586189.45 | a) | - | c) | - | a) | - | Schedule for 3rd Quarter
012 |  | Sonlon-New Visayas-Camansa |  |  |  |  | b) | Pilotos | b) | - | e) | - | b) | 586189.45 | b) | - | d) | - | b) | -
[7 empty] | c) | Admin | c) | - | f) | - | c) | -
|  | Pamacaun-Lasang-Banate |  | Road Maintenance | 4.11 | MBA | a) | 326054.08 | a) | 01/03/18 | d) | - | a) | 326054.08 | a) | - | c) | - | a) | - | Schedule for 3rd Quarter
015 | [6 empty] | b) | Pilotos | b) | - | e) | - | b) | 326054.08 | b) | - | d) | - | b) | -
[7 empty] | c) | Admin | c) | - | f) | - | c) | -
|  | Kapalong-Mabantao-Florida |  | Road Maintenance | 12.13 | MBA | a) | 1124267.17 | a) | 01/03/18 | d) | - | a) | 1124267.17 | a) | 60.54% | c) | 60.54% | a) | 14 | On-going
016 | [6 empty] | b) | Pilotos | b) | 01/03/18 | e) | - | b) | 1124267.17 | b) | - | d) | - | b) | 30
[7 empty] | c) | Admin | c) | 12/31/18 | f) | - | c) | -
|  | Semong-Palma Gil |  | Road Maintenance | 2.73 | MBA | a) | 258225.31 | a) | 01/03/18 | d) | - | a) | 258225.31 | a) | - | c) | - | a) | - | Schedule for 2nd Quarter
018 | [6 empty] | b) | Pilotos | b) | - | e) | - | b) | 258225.31 | b) | - | d) | - | b) | -
[7 empty] | c) | Admin | c) | - | f) | - | c) | -
|  | Sto. Niño - Palma Gil - Sitio Opao |  | Road Maintenance | 5.99 | MBA | a) | 231202.12 | a) | 01/03/18 | d) | - | a) | 231202.12 | a) | - | c) | - | a) | - | Schedule for 2nd Quarter
019 | [6 empty] | b) | Pilotos | b) | - | e) | - | b) | 231202.12 | b) | - | d) | - | b) | -
[7 empty] | c) | Admin | c) | - | f) | - | c) | -
|  | Angelo - Dagohoy |  | Road Maintenance | 2.19 | MBA | a) | 147008.1 | a) | 01/03/18 | d) | - | a) | 147008.1 | a) | - | c) | - | a) | - | Schedule for 3rd Quarter
021 | [6 empty] | b) | Pilotos | b) | - | e) | - | b) | 147008.1 | b) | - | d) | - | b) | -
[7 empty] | c) | Admin | c) | - | f) | - | c) | -
|  | Daligdigon - Lumabag |  | Road Maintenance | 2.82 | MBA | a) | 206507.02 | a) | 01/03/18 | d) | - | a) | 206507.02 | a) | - | c) | - | a) | - | Schedule for 4th Quarter
022 | [6 empty] | b) | Pilotos | b) | - | e) | - | b) | 206507.02 | b) | - | d) | - | b) | -
[7 empty] | c) | Admin | c) | - | f) | - | c) | -
|  | Sto. Niño - Daligdigon - Paiton |  | Road Maintenance | 11.6 | MBA | a) | 1046706.59 | a) | 01/03/18 | d) | - | a) | 1046706.59 | a) | - | c) | - | a) | - | Schedule for 2nd Quarter
023 | [6 empty] | b) | Pilotos | b) | - | e) | - | b) | 1046706.59 | b) | - | d) | - | b) | -
[7 empty] | c) | Admin | c) | - | f) | - | c) | -
|  | Jct. Paiton-Mibolo |  | Road Maintenance | 23.9 | MBA | a) | 1385562.01 | a) | 01/03/18 | d) | - | a) | 1385562.01 | a) | - | c) | - | a) | - | Schedule for 2nd Quarter
024 | [6 empty] | b) | Pilotos | b) | - | e) | - | b) | 1385562.01 | b) | - | d) | - | b) | -
[7 empty] | c) | Admin | c) | - | f) | - | c) | -
|  | Jct. Sampao-Bdry. Mamacao |  | Road Maintenance | 4.98 | MBA | a) | 425463.04 | a) | 01/03/18 | d) | - | a) | 425463.04 | a) | 30.60% | c) | 30.60% | a) | 14 | On-going
025 | [6 empty] | b) | Pilotos | b) | 03/16/18 | e) | - | b) | 425463.04 | b) | - | d) | - | b) | 30
[7 empty] | c) | Admin | c) | 12/31/18 | f) | - | c) | -
|  | Jct. Sampao-Bdry. Mamacao |  | Road Maintenance | 4.98 | CBRMC | a) | 192272.75 | a) | 01/03/18 | d) | - | a) | 41054.25 | a) | - | c) | - | a) | - | Procurement on process
025 | [6 empty] | b) | Garcia | b) | - | e) | - | b) | 41054.25 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | f) | - | c)
|  | Jct. Highway Luna-Mamacao-Narra |  | Road Maintenance | 9.17 | MBA | a) | 882018.08 | a) | 01/03/18 | d) | - | a) | 882018.08 | a) | 33.61% | c) | 33.61% | a) | 14 | On-going
026 | [6 empty] | b) | Pilotos | b) | 03/16/18 | e) | - | b) | 882018.08 | b) | - | d) | - | b) | 30
[7 empty] | c) | Admin | c) | 12/31/18 | f) | - | c) | -
|  | Jct. Highway Luna-Mamacao-Narra |  | Road Maintenance | 9.17 | CBRMC | a) | 348773.82 | a) | 01/03/18 | d) | - | a) | 981915.24 | a) | - | c) | - | a) | - | Procurement on process
026 | [6 empty] | b) | Garcia | b) | - | e) | - | b) | 981915.24 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | f) | - | c)
|  | Jct. Gabuyan-Katipunan-Bucana |  | Road Maintenance | 5.89 | MBA | a) | 557123.47 | a) | 01/03/18 | d) | - | a) | 557123.47 | a) | - | c) | - | a) | - | Schedule for 2nd Quarter
027 | [6 empty] | b) | Pilotos | b) | - | e) | - | b) | 557123.47 | b) | - | d) | - | b) | -
[7 empty] | c) | Admin | c) | - | f) | - | c) | -
|  | Capungagan-Mabuhay-Pandulian |  | Road Maintenance | 5.57 | MBA | a) | 526855.3 | a) | 01/03/18 | d) | - | a) | 526855.3 | a) | 30.49% | c) | 30.49% | a) | 14 | On-going
028 | [6 empty] | b) | Pilotos | b) | 02/01/18 | e) | - | b) | 526855.3 | b) | - | d) | - | b) | 28
[7 empty] | c) | Admin | c) | 12/31/18 | f) | - | c) | -
|  | Florida - New Boholano |  | Road Maintenance | 2.54 | MBA | a) | 188321.71 | a) | 01/03/18 | d) | - | a) | 188321.71 | a) | - | c) | - | a) | - | Schedule for 3rd Quarter
030 | [6 empty] | b) | Pilotos | b) | - | e) | - | b) | 188321.71 | b) | - | d) | - | b) | -
[7 empty] | c) | Admin | c) | - | f) | - | c) | -
|  | Jct. New Boholano - New Loon |  | Road Maintenance | 4.77 | MBA | a) | 407,,521.83 | a) | 01/03/18 | d) | - | a) | 407,,521.83 | a) | - | c) | - | a) | - | Schedule for 2nd Quarter
031 | [6 empty] | b) | Pilotos | b) | - | e) | - | b) | 407,,521.83 | b) | - | d) | - | b) | -
[7 empty] | c) | Admin | c) | - | f) | - | c) | -
|  | Jct. New Boholano - New Loon |  | Road Maintenance | 4.77 | CBRMC | a) | 172151.18 | a) | 01/03/18 | d) | - | a) | 517683.31 | a) | - | c) | - | a) | - | Procurement on process
031 | [6 empty] | b) | Garcia | b) | - | e) | - | b) | 517683.31 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | f) | - | c)
|  | Florida-Suaon-Jct. Gupitan |  | Road Maintenance | 15.57 | MBA | a) | 1326319.39 | a) | 01/03/18 | d) | - | a) | 1326319.39 | a) | - | c) | - | a) | - | Schedule for 2nd Quarter
032 | [6 empty] | b) | Pilotos | b) | - | e) | - | b) | 1326319.39 | b) | - | d) | - | b) | -
[7 empty] | c) | Admin | c) | - | f) | - | c) | -
|  | Florida-Suaon-Jct. Gupitan |  | Road Maintenance | 15.57 | CBRMC | a) | 482917.59 | a) | 01/03/18 | d) | - | a) | 104718.1 | a) | - | c) | - | a) | - | Procurement on process
032 | [6 empty] | b) | Garcia | b) | - | e) | - | b) | 104718.1 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | f) | - | c)
|  | Km. 15, Kipalili-New Loon |  | Road Maintenance | 6.93 | MBA | a) | 795747.7 | a) | 01/03/18 | d) | - | a) | 795747.7 | a) | 20.57% | c) | 20.57% | a) | 14 | On-going
034 | [6 empty] | b) | Pilotos | b) | 01/16/18 | e) | - | b) | 795747.7 | b) | - | d) | - | b) | 30
[7 empty] | c) | Admin | c) | 12/31/18 | f) | - | c) | 4045.8
|  | Km. 15, Kipalili-New Loon |  | Road Maintenance | 6.93 | CBRMC | a) | 239223.07 | a) | 01/03/18 | d) | - | a) | 525933.83 | a) | - | c) | - | a) | - | Procurement on process
034 | [6 empty] | b) | Garcia | b) | - | e) | - | b) | 525933.83 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | f) | - | c)
|  | Jct. Suaon-Libuton |  | Road Maintenance | 7.26 | MBA | a) | 178322.84 | a) | 01/03/18 | d) | - | a) | 178322.84 | a) | - | c) | - | a) | - | Schedule for 4th Quarter
035 | [6 empty] | b) | Pilotos | b) | - | e) | - | b) | 178322.84 | b) | - | d) | - | b) | -
[7 empty] | c) | Admin | c) | - | f) | - | c) | -
|  | Jct. Dacudao - Mabuhay |  | Road Maintenance | 4.43 | MBA | a) | 256821.75 | a) | 01/03/18 | d) | - | a) | 256821.75 | a) | - | c) | - | a) | - | Schedule for 2nd Quarter
036 | [6 empty] | b) | Pilotos | b) | - | e) | - | b) | 256821.75 | b) | - | d) | - | b) | -
[7 empty] | c) | Admin | c) | - | f) | - | c) | -
|  | Monte Dujali-Gupitan |  | Road Maintenance | 4.58 | MBA | a) | 305183.69 | a) | 01/03/18 | d) | - | a) | 305183.69 | a) | - | c) | - | a) | - | Schedule for 3rd Quarter
037 | [6 empty] | b) | Pilotos | b) | - | e) | - | b) | 305183.69 | b) | - | d) | - | b) | -
[7 empty] | c) | Admin | c) | - | f) | - | c) | -
|  | Jct. Patel-Langan |  | Road Maintenance | 1.62 | MBA | a) | 118631.69 | a) | 01/03/18 | d) | - | a) | 118631.69 | a) | - | c) | - | a) | - | Schedule for 3rd Quarter
038 | [6 empty] | b) | Pilotos | b) | - | e) | - | b) | 118631.69 | b) | - | d) | - | b) | -
[7 empty] | c) | Admin | c) | - | f) | - | c) | -
|  | Datu Balong - Pinamuno |  | Road Maintenance | 2.74 | MBA | a) | 209009.02 | a) | 01/03/18 | d) | - | a) | 209009.02 | a) | - | c) | - | a) | - | Schedule for 2nd Quarter
040 | [6 empty] | b) | Pilotos | b) | - | e) | - | b) | 209009.02 | b) | - | d) | - | b) | -
[7 empty] | c) | Admin | c) | - | f) | - | c) | -
|  | Sawata - Mamangan - Pinamuno |  | Road Maintenance | 14.48 | MBA | a) | 1385195.86 | a) | 01/03/18 | d) | - | a) | 1385195.86 | a) | 28.93% | c) | 28.93% | a) | 14 | On-going
041 | [6 empty] | b) | Pilotos | b) | 02/01/18 | e) | - | b) | 1385195.86 | b) | - | d) | - | b) | 28 days
[7 empty] | c) | Admin | c) | 12/31/18 | f) | - | c) | -
|  | Sawata - Mamangan - Pinamuno |  | Road Maintenance | 14.48 | CBRMC | a) | 476210.4 | a) | 01/03/18 | d) | - | a) | 110271.33 | a) | - | c) | - | a) | - | Procurement on process
041 | [6 empty] | b) | Garcia | b) | - | e) | - | b) | 110271.33 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | f) | - | c)
|  | Jct. Sawata - Bdry. Binasbas |  | Road Maintenance | 0.46 | MBA | a) | 43510.49 | a) | 01/03/18 | d) | - | a) | 43510.49 | a) | - | c) | - | a) | - | Schedule for 2nd Quarter
043 | [6 empty] | b) | Pilotos | b) | - | e) | - | b) | 43510.49 | b) | - | d) | - | b) | -
[7 empty] | c) | Admin | c) | - | f) | - | c) | -
|  | New Corella-Sto. Niño -Macgum |  | Road Maintenance | 17.11 | MBA | a) | 1618401.11 | a) | 01/03/18 | d) | - | a) | 1618401.11 | a) | 75.92% | c) | 75.92% | a) | 14 | On-going
044 | [6 empty] | b) | Pilotos | b) | 01/03/18 | e) | - | b) | 1618401.11 | b) | - | d) | - | b) | 30
[7 empty] | c) | Admin | c) | 12/31/18 | f) | - | c) | 343037.49
|  | New Corella-Sto. Niño -Macgum |  | Road Maintenance | 17.11 | CBRMC | a) | 403504.52 | a) | 01/03/18 | d) | - | a) | 403601 | a) | - | c) | - | a) | - | Procurement on process
044 | [6 empty] | b) | Garcia | b) | - | e) | - | b) | 403601 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | f) | - | c)
|  | Tagaytay-Buan |  | Road Maintenance | 4.92 | MBA | a) | 411903.39 | a) | 01/03/18 | d) | - | a) | 411903.39 | a) | 40.54% | c) | 40.54% | a) | 14 | On-going
045 | [6 empty] | b) | Pilotos | b) | 01/03/18 | e) | - | b) | 411903.39 | b) | - | d) | - | b) | 30
[7 empty] | c) | Admin | c) | 12/31/18 | f) | - | c) | 21027.67
|  | Tagaytay-Buan |  | Road Maintenance | 4.92 | CBRMC | a) | 187801.29 | a) | 01/03/18 | d) | - | a) | 187801.29 | a) | - | c) | - | a) | - | Procurement on process
045 | [6 empty] | b) | Garcia | b) | - | e) | - | b) | 187801.29 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | f) | - | c)
|  | Sta. Fe-Mambing |  | Road Maintenance | 10.96 | MBA | a) | 869477.54 | a) | 01/03/18 | d) | - | a) | 869477.54 | a) | - | c) | - | a) | - | Schedule for 2nd Quarter
046 | [6 empty] | b) | Pilotos | b) | - | e) | - | b) | 869477.54 | b) | - | d) | - | b) | -
[7 empty] | c) | Admin | c) | - | f) | - | c) | -
|  | Sta. Fe-Mambing |  | Road Maintenance | 10.96 | CBRMC | a) | 342066.63 | a) | 01/03/18 | d) | - | a) | 97761.3 | a) | - | c) | - | a) | - | Letter sent to BAC for cancellation
046 | [6 empty] | b) | Garcia | b) | - | e) | - | b) | 97761.3 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | f) | - | c)
|  | Limbaan-Sta. Fe-El Salvador |  | Road Maintenance | 18.82 | MBA | a) | 2136176.96 | a) | 01/03/18 | d) | - | a) | 2136176.96 | a) | - | c) | - | a) | - | Schedule for 2nd Quarter
047 | [6 empty] | b) | Pilotos | b) | - | e) | - | b) | 2136176.96 | b) | - | d) | - | b) | -
[7 empty] | c) | Admin | c) | - | f) | - | c) | -
|  | Limbaan-Sta. Fe-El Salvador |  | Road Maintenance | 18.82 | CBRMC | a) | 574582.51 | a) | 01/03/18 | d) | - | a) | 10000000 | a) | - | c) | - | a) | - | Letter sent to BAC for cancellation
047 | [6 empty] | b) | Garcia | b) | - | e) | - | b) | 10000000 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | f) | - | c)
|  | New Corella-Saug |  | Road Maintenance | 12.52 | MBA | a) | 1443622.27 | a) | 01/03/18 | d) | - | a) | 1443622.27 | a) | 71.43% | c) | 71.43% | a) | 14 | On-going
048 | [6 empty] | b) | Pilotos | b) | 01/03/18 | e) | - | b) | 1443622.27 | b) | - | d) | - | b) | 30
[7 empty] | c) | Admin | c) | 12/31/18 | f) | - | c) | 21027.67
|  | New Corella-Saug |  | Road Maintenance | 12.52 | CBRMC | a) | 393408.41 | a) | 01/03/18 | d) | - | a) | 13523124 | a) | - | c) | - | a) | - | Procurement on process
048 | [6 empty] | b) | Garcia | b) | - | e) | - | b) | 13523124 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | f) | - | c)
|  | Limbaan-Sto. Niño |  | Road Maintenance | 3.19 | MBA | a) | 272535.56 | a) | 01/03/18 | d) | - | a) | 272535.56 | a) | - | c) | - | a) | - | Schedule for 3rd Quarter
049 | [6 empty] | b) | Pilotos | b) | - | e) | - | b) | 272535.56 | b) | - | d) | - | b) | -
[7 empty] | c) | Admin | c) | - | f) | - | c) | -
|  | Jct. Monte Calo-Upper Cabaywa-Canatan |  | Road Maintenance | 4.61 | MBA | a) | 407582.85 | a) | 01/03/18 | d) | - | a) | 407582.85 | a) | - | c) | - | a) | - | Schedule for 2nd Quarter
050 | [6 empty] | b) | Pilotos | b) | - | e) | - | b) | 407582.85 | b) | - | d) | - | b) | -
[7 empty] | c) | Admin | c) | - | f) | - | c) | -
|  | Jct. Monte Calo-Upper Cabaywa-Canatan |  | Road Maintenance | 4.61 | CBRMC | a) | 172151.18 | a) | 01/03/18 | d) | - | a) | 0 | a) | - | c) | - | a) | - | Procurement on process
050 | [6 empty] | b) | Garcia | b) | - | e) | - | b) | 0 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | f) | - | c)
|  | Del Pilar - Jct. Silangan |  | Road Maintenance | 4.17 | MBA | a) | 394432.07 | a) | 01/03/18 | d) | - | a) | 394432.07 | a) | 12.06% | c) | 12.06% | a) | 14 | On-going
051 | [6 empty] | b) | Pilotos | b) | 03/16/18 | e) | - | b) | 394432.07 | b) | - | d) | - | b) | 30
[7 empty] | c) | Admin | c) | 12/31/18 | f) | - | c) | -
|  | Del Pilar - Jct. Silangan |  | Road Maintenance | 4.17 | CBRMC | a) | 138615.24 | a) | 01/03/18 | d) | - | a) | - | a) | - | c) | - | a) | - | Procurement on process
051 | [6 empty] | b) | Garcia | b) | - | e) | - | b) | - | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | f) | - | c)
|  | New Corella - New Sambog - Silangan |  | Road Maintenance | 5.1 | MBA | a) | 438766.39 | a) | 01/03/18 | d) | - | a) | 438766.39 | a) | 19.42% | c) | 19.42% | a) | 14 | On-going
052 | [6 empty] | b) | Pilotos | b) | 01/03/18 | e) | - | b) | 438766.39 | b) | - | d) | - | b) | 30
[7 empty] | c) | Admin | c) | 12/31/18 | f) | - | c) | 21027.67
|  | New Corella - New Sambog - Silangan |  | Road Maintenance | 5.1 | CBRMC | a) | 136379.51 | a) | 01/03/18 | d) | - | a) | - | a) | - | c) | - | a) | - | Procurement on process
052 | [6 empty] | b) | Garcia | b) | - | e) | - | b) | - | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | f) | - | c)
|  | Pob. New Corella - Prk. 10 Pob. |  | Road Maintenance | 1.3 | MBA | a) | 41054.25 | a) | 01/03/18 | d) | - | a) | 41054.25 | a) | - | c) | - | a) | - | Schedule for 4th Quarter
053 | [6 empty] | b) | Pilotos | b) | - | e) | - | b) | 41054.25 | b) | - | d) | - | b) | -
[7 empty] | c) | Admin | c) | - | f) | - | c) | -
|  | Prk. 7 Pob. - Jct. New Sambog |  | Road Maintenance | 2.54 | MBA | a) | 288304.3 | a) | 01/03/18 | d) | - | a) | 288304.3 | a) | - | c) | - | a) | - | Schedule for 4th Quarter
054 | [6 empty] | b) | Pilotos | b) | - | e) | - | b) | 288304.3 | b) | - | d) | - | b) | -
[7 empty] | c) | Admin | c) | - | f) | - | c) | -
|  | New Corella - Guadalupe - Del Monte |  | Road Maintenance | 14.05 | MBA | a) | 981915.24 | a) | 01/03/18 | d) | - | a) | 981915.24 | a) | 9.11% | c) | 9.11% | a) | 14 | On-going
055 | [6 empty] | b) | Pilotos | b) | 02/01/18 | e) | - | b) | 981915.24 | b) | - | d) | - | b) | 30
[7 empty] | c) | Admin | c) | 12/31/18 | f) | - | c) | 76216.23
|  | New Corella - Guadalupe - Del Monte |  | Road Maintenance | 14.05 | CBRMC | a) | 465031.76 | a) | 01/03/18 | d) | - | a) | 0 | a) | - | c) | - | a) | - | Procurement on process
055 | [6 empty] | b) | Garcia | b) | - | e) | - | b) | 0 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | f) | - | c)
|  | Sta. Fe - Del Monte |  | Road Maintenance | 3.34 | MBA | a) | 142675.36 | a) | 01/03/18 | d) | - | a) | 142675.36 | a) | 20.04% | c) | 20.04% | a) | 14 | On-going
056 | [6 empty] | b) | Pilotos | b) | 02/01/18 | e) | - | b) | 142675.36 | b) | - | d) | - | b) | 28
[7 empty] | c) | Admin | c) | 12/31/18 | f) | - | c) | -
|  | Sta. Fe - Del Monte |  | Road Maintenance | 3.34 | CBRMC | a) | 91664.91 | a) | 01/03/18 | d) | - | a) | 0 | a) | - | c) | - | a) | - | Procurement on process
056 | [6 empty] | b) | Garcia | b) | - | e) | - | b) | 0 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | f) | - | c)
|  | Carcor - Patrocenio - Jct. Bayabas |  | Road Maintenance | 14.68 | MBA | a) | 2136176.96 | a) | 01/03/18 | d) | - | a) | 2136176.96 | a) | - | c) | - | a) | - | Schedule for 2nd Quarter
057 | [6 empty] | b) | Pilotos | b) | - | e) | - | b) | 2136176.96 | b) | - | d) | - | b) | -
[7 empty] | c) | Admin | c) | - | f) | - | c) | -
|  | Carcor - Patrocenio - Jct. Bayabas |  | Road Maintenance | 14.68 | CBRMC | a) | 404667.06 | a) | 01/03/18 | d) | - | a) | 0 | a) | - | c) | - | a) | - | Procurement on process
057 | [6 empty] | b) | Garcia | b) | - | e) | - | b) | 0 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | f) | - | c)
|  | New Corella - New Bohol |  | Road Maintenance | 11.54 | MBA | a) | 718832.38 | a) | 01/03/18 | d) | - | a) | 718832.38 | a) | 75.34% | c) | 75.34% | a) | 14 | On-going
058 | [6 empty] | b) | Pilotos | b) | 02/01/18 | e) | - | b) | 718832.38 | b) | - | d) | - | b) | 30
[7 empty] | c) | Admin | c) | 12/31/18 | f) | - | c) | 1500
|  | New Corella - New Bohol |  | Road Maintenance | 11.54 | CBRMC | a) | 176386.91 | a) | 01/03/18 | d) | - | a) | 0 | a) | - | c) | - | a) | - | Procurement on process
058 | [6 empty] | b) | Garcia | b) | - | e) | - | b) | 0 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | f) | - | c)
|  | Jct. Carcor - Prk. 9 Bagsak |  | Road Maintenance | 2.5 | MBA | a) | 198329.73 | a) | 01/03/18 | d) | - | a) | 198329.73 | a) | - | c) | - | a) | - | Schedule for 4th Quarter
059 | [6 empty] | b) | Pilotos | b) | - | e) | - | b) | 198329.73 | b) | - | d) | - | b) | -
[7 empty] | c) | Admin | c) | - | f) | - | c) | -
|  | Carcor - Jct. Kauswagan |  | Road Maintenance | 4.32 | MBA | a) | 411256.53 | a) | 01/03/18 | d) | - | a) | 411256.53 | a) | 51.34% | c) | 51.34% | a) | 14 | On-going
060 | [6 empty] | b) | Pilotos | b) | 03/16/18 | e) | - | b) | 411256.53 | b) | - | d) | - | b) | 30
[7 empty] | c) | Admin | c) | 12/31/18 | f) | - | c) | -
|  | Del Pilar - Prk. 9 Bagsak - San Jose |  | Road Maintenance | 4.99 | MBA | a) | 517683.31 | a) | 01/03/18 | d) | - | a) | 517683.31 | a) | - | c) | - | a) | - | Schedule for 2nd Quarter
061 | [6 empty] | b) | Pilotos | b) | - | e) | - | b) | 517683.31 | b) | - | d) | - | b) | -
[7 empty] | c) | Admin | c) | - | f) | - | c) | -
|  | Del Pilar - Prk. 9 Bagsak - San Jose |  | Road Maintenance | 4.99 | CBRMC | a) | 198979.93 | a) | 01/03/18 | d) | - | a) | 0 | a) | - | c) | - | a) | - | Procurement on process
061 | [6 empty] | b) | Garcia | b) | - | e) | - | b) | 0 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | f) | - | c)
|  | Del Pilar - El Unido |  | Road Maintenance | 1.32 | MBA | a) | 104718.1 | a) | 01/03/18 | d) | - | a) | 104718.1 | a) | - | c) | - | a) | - | Schedule for 2nd Quarter
062 | [6 empty] | b) | Pilotos | b) | - | e) | - | b) | 104718.1 | b) | - | d) | - | b) | -
[7 empty] | c) | Admin | c) | - | f) | - | c) | -
|  | San Juan - New Talisay |  | Road Maintenance | 5.13 | MBA | a) | 525933.83 | a) | 01/03/18 | d) | - | a) | 525933.83 | a) | - | c) | - | a) | - | Schedule for 4th Quarter
063 | [6 empty] | b) | Pilotos | b) | - | e) | - | b) | 525933.83 | b) | - | d) | - | b) | -
[7 empty] | c) | Admin | c) | - | f) | - | c) | -
|  | New Bohol - Jct. El Unido |  | Road Maintenance | 2.12 | MBA | a) | 149632.15 | a) | 01/03/18 | d) | - | a) | 149632.15 | a) | - | c) | - | a) | - | Schedule for 2nd Quarter
065 | [6 empty] | b) | Pilotos | b) | - | e) | - | b) | 149632.15 | b) | - | d) | - | b) | -
[7 empty] | c) | Admin | c) | - | f) | - | c) | -
|  | New Bohol - Jct. El Unido |  | Road Maintenance | 2.12 | CBRMC | a) | 91664.91 | a) | 01/03/18 | d) | - | a) | 0 | a) | - | c) | - | a) | - | Procurement on process
065 | [6 empty] | b) | Garcia | b) | - | e) | - | b) | 0 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | f) | - | c)
|  | New Corella - El Unido - Jct. Mesaoy |  | Road Maintenance | 8.63 | MBA | a) | 816294.66 | a) | 01/03/18 | d) | - | a) | 816294.66 | a) | - | c) | - | a) | - | Schedule for 2nd Quarter
066 | [6 empty] | b) | Pilotos | b) | - | e) | - | b) | 816294.66 | b) | - | d) | - | b) | -
[7 empty] | c) | Admin | c) | - | f) | - | c) | -
|  | New Corella - El Unido - Jct. Mesaoy |  | Road Maintenance | 8.63 | CBRMC | a) | 185565.56 | a) | 01/03/18 | d) | - | a) | 0 | a) | - | c) | - | a) | - | Procurement on process
066 | [6 empty] | b) | Garcia | b) | - | e) | - | b) | 0 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | f) | - | c)
|  | Mesaoy - Dasing |  | Road Maintenance | 1.39 | MBA | a) | 110271.33 | a) | 01/03/18 | d) | - | a) | 110271.33 | a) | 25.19% | c) | 25.19% | a) | 14 | On-going
067 | [6 empty] | b) | Pilotos | b) | 03/01/18 | e) | - | b) | 110271.33 | b) | - | d) | - | b) | 30
[7 empty] | c) | Admin | c) | 12/31/18 | f) | - | c) | -
|  | Mesaoy - Dasing |  | Road Maintenance | 1.39 | CBRMC | a) | 53657.51 | a) | 01/03/18 | d) | - | a) | 0 | a) | - | c) | - | a) | - | Procurement on process
067 | [6 empty] | b) | Garcia | b) | - | e) | - | b) | 0 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | f) | - | c)
|  | Jct. San Juan - Jct. Mesaoy |  | Road Maintenance | 1.82 | MBA | a) | 186588.61 | a) | 01/03/18 | d) | - | a) | 186588.61 | a) | - | c) | - | a) | - | Schedule for 3rd Quarter
068 | [6 empty] | b) | Pilotos | b) | - | e) | - | b) | 186588.61 | b) | - | d) | - | b) | -
[7 empty] | c) | Admin | c) | - | f) | - | c) | -
|  | Mesaoy - Jct. Mahayahay |  | Road Maintenance | 4.6 | MBA | a) | 403601 | a) | 01/03/18 | d) | - | a) | 403601 | a) | 45.14% | c) | 45.14% | a) | 14 | On-going
069 | [6 empty] | b) | Pilotos | b) | 03/01/18 | e) | - | b) | 403601 | b) | - | d) | - | b) | 30
[7 empty] | c) | Admin | c) | 12/31/18 | f) | - | c) | -
|  | Mesaoy - Jct. Mahayahay |  | Road Maintenance | 4.6 | CBRMC | a) | 156265.34 | a) | 01/03/18 | d) | - | a) | 0 | a) | - | c) | - | a) | - | Procurement on process
069 | [6 empty] | b) | Garcia | b) | - | e) | - | b) | 0 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | f) | - | c)
|  | Mesaoy - New Bohol |  | Road Maintenance | 5.36 | MBA | a) | 512850.17 | a) | 01/03/18 | d) | - | a) | 512850.17 | a) | 37.98% | c) | 37.98% | a) | 14 | On-going
070 | [6 empty] | b) | Pilotos | b) | 01/03/18 | e) | - | b) | 512850.17 | b) | - | d) | - | b) | 30
[7 empty] | c) | Admin | c) | 12/31/18 | f) | - | c) | -
|  | Mesaoy - New Bohol |  | Road Maintenance | 5.36 | CBRMC | a) | 205687.12 | a) | 01/03/18 | d) | - | a) | 0 | a) | - | c) | - | a) | - | Procurement on process
070 | [6 empty] | b) | Garcia | b) | - | e) | - | b) | 0 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | f) | - | c)
|  | Bdry. Tagum - Baca - New Corella |  | Road Maintenance | 13.01 | MBA | a) | 2136176.96 | a) | 01/03/18 | d) | - | a) | 2136176.96 | a) | - | c) | - | a) | - | Schedule for 2nd Quarter
071 | [6 empty] | b) | Pilotos | b) | - | e) | - | b) | 2136176.96 | b) | - | d) | - | b) | -
[7 empty] | c) | Admin | c) | - | f) | - | c) | -
|  | Bdry. Tagum - Baca - New Corella |  | Road Maintenance | 13.01 | CBRMC | a) | 192145.12 | a) | 01/03/18 | d) | - | a) | 0 | a) | - | c) | - | a) | - | Procurement on process
071 | [6 empty] | b) | Garcia | b) | - | e) | - | b) | 0 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | f) | - | c)
|  | Prk. Maunlom-Prk. 6 Maunlom |  | Road Maintenance | 3.56 | MBA | a) | 97761.3 | a) | 01/03/18 | d) | - | a) | 97761.3 | a) | 32.18% | c) | 32.18% | a) | 14 | On-going
147 | [6 empty] | b) | Pilotos | b) | 03/01/18 | e) | - | b) | 97761.3 | b) | - | d) | - | b) | 30
[7 empty] | c) | Admin | c) | 12/31/18 | f) | - | c) | -
|  | 2. Repair & Maint. Of Various Local Roads |  | Road | - | Admin | a) | 5000000 | [12 empty] | Investigation/Inspection of priority projects
|  | and Drainages |  |  |  |  | b) | Paraguya
[7 empty] | c) | Admin
|  | 2.1 | Rehabilitation of Magugpo South, Brgy. | #REF! |  | #REF! | a) | 75211.96 | a) | 04/02/18 | d) | - | a) | 75211.96 | a) | 50.00% | c) | 50.00% | a) | - | On-going
|  |  | Tagum City |  |  |  | b) | Matildo/Ongking | b) | 02/24/18 | e) | - | b) | 75211.96 | b) | - | d) | - | b) | -
[7 empty] | c) | Admin | c) | 05/01/18 | f) | - | c) | -
|  | 2.2 | Rehabilitation of Cuambogan, Brgy. Road, | #REF! |  | #REF! | a) | 90500.31 | a) | 04/02/18 | d) | - | a) | 90500.31 | a) | - | c) | - | a) | - | For implementation
|  |  | Tagum City |  |  |  | b) | Matildo/Ongking | b) | - | e) | - | b) | 90500.31 | b) | - | d) | - | b) | -
[7 empty] | c) | Admin | c) | - | f) | - | c) | -
|  | 2.3 | Rehabilitation of Magugpo North Brgy. | #REF! |  | #REF! | a) | 77252.31 | a) | 04/02/18 | d) | - | a) | 77252.31 | a) | - | c) | - | a) | - | For implementation
|  |  | Road, Tagum City |  |  |  | b) | Matildo/Ongking | b) | - | e) | - | b) | 77252.31 | b) | - | d) | - | b) | -
[7 empty] | c) | Admin | c) | - | f) | - | c) | -
|  | 2.4 | Rehabilitation of Visayan Brgy. Road, | #REF! |  | #REF! | a) | 90500.31 | a) | 04/02/18 | d) | - | a) | 90500.31 | a) | - | c) | - | a) | - | For implementation
|  |  | Tagum City |  |  |  | b) | Matildo/Ongking | b) | - | e) | - | b) | 90500.31 | b) | - | d) | - | b) | -
[7 empty] | c) | Admin | c) | - | f) | - | c) | -
|  | 2.5 | Rehabilitation of Mankilam-B,Brgy. Road, | #REF! |  | #REF! | a) | 77252.31 | a) | 04/02/18 | d) | - | a) | 77252.31 | a) | - | c) | - | a) | - | For implementation
|  |  | Tagum City |  |  |  | b) | Matildo/Ongking | b) | - | e) | - | b) | 77252.31 | b) | - | d) | - | b) | -
[7 empty] | c) | Admin | c) | - | f) | - | c) | -
|  | 2.6 | Rehabilitation of Busaon,Brgy. Road, | #REF! |  | #REF! | a) | 90500.31 | a) | 04/02/18 | d) | - | a) | 90500.31 | a) | - | c) | - | a) | - | For implementation
|  |  | Tagum City |  |  |  | b) | Matildo/Ongking | b) | - | e) | - | b) | 90500.31 | b) | - | d) | - | b) | -
[7 empty] | c) | Admin | c) | - | f) | - | c) | -
|  | 2.7 | Rehabilitation of Canocotan-B,Brgy. Road, | #REF! |  | #REF! | a) | 77252.31 | a) | 04/02/18 | d) | - | a) | 77252.31 | a) | - | c) | - | a) | - | For implementation
|  |  | Tagum City |  |  |  | b) | Matildo/Ongking | b) | - | e) | - | b) | 77252.31 | b) | - | d) | - | b) | -
[7 empty] | c) | Admin | c) | - | f) | - | c) | -
|  | 2.8 | Rehabilitation of Canocotan-A,Brgy. Road, | #REF! |  | #REF! | a) | 77252.31 | a) | 04/02/18 | d) | - | a) | 77252.31 | a) | - | c) | - | a) | - | For implementation
|  |  | Tagum City |  |  |  | b) | Matildo/Ongking | b) | - | e) | - | b) | 77252.31 | b) | - | d) | - | b) | -
[7 empty] | c) | Admin | c) | - | f) | - | c) | -
|  | 2.9 | Rehabilitation of San Agustin,Brgy. Road, | #REF! |  | #REF! | a) | 90500.31 | a) | 04/02/18 | d) | - | a) | 90500.31 | a) | - | c) | - | a) | - | For implementation
|  |  | Tagum City |  |  |  | b) | Matildo/Ongking | b) | - | e) | - | b) | 90500.31 | b) | - | d) | - | b) | -
[7 empty] | c) | Admin | c) | - | f) | - | c) | -
|  | 3 | Rehabilitation of New balamban,Brgy. Road, | #REF! |  | #REF! | a) | 90500.31 | a) | 04/02/18 | d) | - | a) | 90500.31 | a) | - | c) | - | a) | - | For implementation
|  |  | Tagum City |  |  |  | b) | Matildo/Ongking | b) | - | e) | - | b) | 90500.31 | b) | - | d) | - | b) | -
[7 empty] | c) | Admin | c) | - | f) | - | c) | -
|  | 3.1 | Rehabilitation of Mankilam-A,Brgy. Road, | #REF! |  | #REF! | a) | 77252.31 | a) | 04/02/18 | d) | - | a) | 77252.31 | a) | - | c) | - | a) | - | For implementation
|  |  | Tagum City |  |  |  | b) | Matildo/Ongking | b) | - | e) | - | b) | 77252.31 | b) | - | d) | - | b) | -
[7 empty] | c) | Admin | c) | - | f) | - | c) | -
|  | 3.2 | Rehabilitation of La Filipina,Brgy. Road | #REF! |  | #REF! | a) | 90500.31 | a) | 04/02/18 | d) | - | a) | 90500.31 | a) | - | c) | - | a) | - | For implementation
|  |  | , Tagum City |  |  |  | b) | Matildo/Ongking | b) | - | e) | - | b) | 90500.31 | b) | - | d) | - | b) | -
[7 empty] | c) | Admin | c) | - | f) | - | c) | -
|  | 3. Various of Water System Project (Provincewide) |  | Water | - | Admin | a) | 10000000 | [12 empty] | Investigation/Inspection of priority projects
|  |  |  | System |  |  | b) | Foronda/Misa
[7 empty] | c) | Admin
|  | 4. Counterpart to Special Projects (Provincewide) |  | Road | - | Admin | a) | 67415000 | [12 empty] | Investigation/Inspection of priority projects
[7 empty] | b) | Foronda
[7 empty] | c) | Admin
|  | 5. Const./Rehab./Comp. of Various Gov't. Bldgs. |  | Bldgs. | - | Admin | a) | 13523124 | [12 empty] | Investigation/Inspection of priority projects
|  | Struct., Fac. (Provincewide) |  |  |  |  | b) | Foronda
[7 empty] | c) | Admin
|  | 5.1 | Repair/Rehab. Of Covered Court, Brgy. Limbaan, | Bldgs. |  | Admin | a) | 500000 | a) | - | d) | - | a) | 500000 | a) | - | c) | - | a) | - | PR on process
|  |  | New Corella |  |  |  | b) | - | b) | - | e) | - | b) | 500000 | b) | - | d) | - | b) | -
[7 empty] | c) | Admin | c) | - | f) | - | c) | -
|  | 6. Rural Electrification (Provincewide) |  | Electrification |  | Admin | a) | 5000000 | [12 empty] | Investigation/Inspection of priority projects
[7 empty] | b) | Foronda/Misa
[7 empty] | c) | Admin
| B. | 5% Calamity Fund CY 2018
1. Prevention and Mitigation
|  | 1.1 Desiltation/Excavation of rivers and creeks |  | rivers |  | Admin | a) | 3000000 | [12 empty] | Investigation/Inspection of priority projects
[7 empty] | b) | -
[7 empty] | c) | Admin
|  | 1.2 Revitment of Dike and Slope Protection |  | Dike |  | Admin | a) | 3000000 | [12 empty] | Investigation/Inspection of priority projects
[7 empty] | b) | -
[7 empty] | c) | Admin
|  | 1.3 Improvement of roads and canal |  | roads/canals |  | Admin | a) | 3000000 | [12 empty] | Investigation/Inspection of priority projects
[7 empty] | b) | -
[7 empty] | c) | Admin
|  | a. | Rehab./Improvement of Km. 9 Sagayen- | roads/canals |  | Admin | a) | 500000 | a) | 04/18/18 | d) | - | a) | 500000 | a) | - | c) | - | a) | - | PR on process
|  |  | Sawata |  |  |  | b) | - | b) | - | e) | - | b) | 500000 | b) | - | d) | - | b) | -
[7 empty] | c) | Admin | c) | - | f) | - | c) | -
|  | 1.4 Improvement of bridges and cross drainage |  | bridges/drainage |  | Admin | a) | 3000000 | [12 empty] | Investigation/Inspection of priority projects
[7 empty] | b) | -
[7 empty] | c) | Admin
|  | 2. Rehabilitation and Recovery |  | roads |  | Admin | a) | 2026000 | [12 empty] | Investigation/Inspection of priority projects
[7 empty] | b) | -
[7 empty] | c) | Admin
| C. | SEF(Special Education Fund)-ANNUAL BUDGET CY 2018
|  | 1. Const./Impv't./Compl. Of School Bldgs., Struc. & Fac. |  | Bldgs. |  | Admin | a) | 2055000 | [12 empty] | Investigation/Inspection of priority projects
[7 empty] | b) | -
[7 empty] | c) | Admin

## Completed(Central)
PROVINCE OF DAVAO DEL NORTE
ACCOMPLISHMENT REPORT
1ST QUARTER REPORT CY 2020
SECTOR: ECONOMIC (INFRASTRUCTURE DEV'T. PROGRAM)
OFFICE/AGENCY: PROVINCIAL ENGINEER'S OFFICE
AREA: 1ST AND 2ND ENGINEERING DISTRICT - COMPLETED PROJECTS
Name of Project |  |  |  | Type | Physical | Mode | PROJECT DATA | [5 empty] | Financial (000) |  | Physical Accomplishment |  |  |  | Employment |  | REMARKS
|  |  |  | of | Target | of | a) Project Cost |  | a) | Date A lot. Rel. | e) | # of days suspended | a) Program |  | a) Planned |  | c) Actual |  | Generated
|  |  |  | Project | (Descrip | Impl. | b) Project Engineer |  | b) | Date Started | f) | # of days extended | b) Allotment |  | b) Revised |  | d) Slippage |  | a) # of Persons | # of Persons
|  |  |  | (Location) | tion) |  | c) Implementor |  | c) | Target Compl. Date | g) | Date completed | c) Disbursement | [5 empty] | b) | Man-days
[7 empty] | d) Duration |  | d) | Revised Compl. Date
I. | PROJECTS UNDER THE CONTINUING APPROPRIATION | [20 empty] | AC |  | 893809.45
|  | SLRF 2015 | [6 empty] | a) |  | e) | 65 days | a) |  | a) | 100% | c) | 100% | a) | 3 | Completed as per POW, Financial Documents on Process | 2
|  | Rehab. of Jct. Highway-Tuganay-Anibongan-BE Dujali-Kinamayan Provincial Road (Furtheranace) |  | Slope protection | - | - | a) | 1911175.99 | b) | 2019-02-18 | f) | 47 days | b) |  | b) |  | d) | 0% | b) | 60 |  | 2
[7 empty] | b) | Balbastro | c) | 2019-09-21 | g) | 9/21/2019 | c) | [8 empty] | 2
[7 empty] | c) | Admin | d) | [12 empty] | 2
[7 empty] | d) | - | [13 empty] | 2
| A. | Trust Fund | [19 empty] | FS
|  | 1. PRDP | [19 empty] | FS
|  | 1.1 Construction of Dalisay Potable Water System |  | Water System | 162 Households | Contract. | a) | 4664033.76 | a) | CY 2014 | e) | - | a) | 4664033.76 | a) | 100.00% | c) | 100.00% | a) | 3 | Completed as per physical accomplishment | 1
[7 empty] | b) | Estorco | b) | 2018-01-29 | f) | 39 CD | b) | 4664033.76 | b) | 100.00% | d) | - | b) | 3 |  | 1
[7 empty] | c) | Ancor Water Resources | c) | 2018-07-23 | g) | 2020-02-11 | c) | 3731227.01 | [7 empty] | 1
[7 empty] | d) | 188 CD | d) | 2020-02-11 | [11 empty] | FS
|  | 1.2. Construction of Kasilak Potable Water System |  | Water System | 252 Households | Contract. | a) | 7046856.27 | a) | CY 2014 | e) |  | a) | 7046856.27 | a) | 100.00% | c) | 100.00% | a) | 3 | Completed as per physical accomplishment. Financial documents still on process | 1
[7 empty] | b) | Estorco | b) | 2018-01-29 | f) | 72 CD | b) | 7046856.27 | b) | 100.00% | d) | - | b) | 3 |  | 1
[7 empty] | c) | Ancor Water Resources | c) | 2018-09-24 | g) | 2020-02-18 | c) | 5637485.016 | [7 empty] | 1
[7 empty] | d) | 188 CD | d) | 2020-02-18 | [11 empty] | 1
|  | 2. KALSADA CY 2015 | [19 empty] | 1
|  |  | Improvement of Km. 9 Sagayen-Sawata Provincial San Isidro, Davao del Norte | Road | 6667.54 m | Admin | a) | 33401544.78 | a) | CY 2015 | d) | - | a) | 33401544.78 | a) | 100% | c) | 100% | a) | 30 | Original contract terminated due to very poor performance of the contractor.The contract cost P 47,213,478.31. Completed as per physical accomplishment. Financial documents still on process | 1
|  | 2.1 |  |  |  |  | b) | Limpo | b) | 2018-10-16 | e) |  | b) | 33401544.78 | b) | 100% | d) | - | b) | 900 |  | 1
[7 empty] | c) | PEO | c) | 2019-09-14 | f) | 2019-12-27 | c) | 32,733518.38 | [7 empty] | 1
[7 empty] | d) | 334 CD | d) | 2019-12-27 | [11 empty] | AC
| B. | 20% Development Fund CY 2016 | [19 empty] | AC
|  | 1. Rural Electrification (Provincewide) |  | Elect. |  | Admin | a) | 5000000 | [12 empty] | See project listed below | AC
[7 empty] | b) | Foronda/Ababon | [13 empty] | 1
[7 empty] | c) | Admin
[7 empty] | d) | -
|  | 1.1 | Electrification expansion to Purok 7, Brgy. Guilon, samal Dist. IGCS | Elect. |  | Contract | a) | 1,537,404.57 | a) | 2019-02-04 | e) | - | a) | 1,537,404.57 | a) | 100% | c) | 100% | a) | - | Completed as per physical accomplishment. Financial documents still on process
[7 empty] | b) | Lu | b) | 2019-10-31 | f) | - | b) | 1,537,404.57 | b) | - | d) | - | b) | -
[7 empty] | c) | LR Eng'g Services | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
| C. | 20% Development Fund CY 2017
|  | 1. Rural Electrification (Provincewide) |  | Elect. | km. | Admin/Contract | a) | 5000000 | [12 empty] | See project listed below
[7 empty] | b) | Foronda
[7 empty] | c) | -
[7 empty] | d) | -
|  |  | Electrification of Purok 1-4, Sta. Cruz, New Corella | Elect. | km. | Admin/Contract | a) | 2,500,000.00 | a) | 2019-02-04 | e) | - | a) | 2,500,000.00 | a) | 100% | c) | 100% | a) | 10 | Completed as per physical accomplishment. Financial documents still on process
|  | 1.1 |  |  |  |  | b) | Lu | b) | 2019-11-04 | f) | - | b) | 2,500,000.00 | b) | - | d) | - | b) | 310
[7 empty] | c) | LR ENG'G. | c) | 2020-01-24 | g) | 2020-01-24 | c) | -
[7 empty] | d) | 120 CD | d) | -
Road ID |  | 2. Repair/Maintenance of Provincial Roads & Bridges |  | Road Maintenance | KM | MBA | a) | 41465029 | a) | 2019-01-03 | [10 empty] | See list of Provincial Roads
[5 empty] | 109.55 |  | b) | Paraguya | b) | 2019-01-03
11DAN | [6 empty] | c) | PEO | c) | 2019-12-31
[7 empty] | d) | 261 days | d) | -
|  | Kapalong - Mabantao - Florida |  | Road Rehabilitation | 7.86 | MBA | a) | 1231000 | a) | 2019-01-31 | e) | - | a) | 1231000 | a) | 100% | c) | 100% | a) | - | Completed as per physical accomplishment. Financial documents still on process
016 | [6 empty] | b) | Lumapat | b) | 2019-10-01 | f) | 78 WD | b) | 1231000 | b) | - | d) | - | b) | -
[7 empty] | c) | PEO | c) | 2019-10-29 | g) | 2020-01-15 | c) | -
[7 empty] | d) | 107 CD | d) | 2020-01-15
| D. | 20% Development Fund CY 2018
|  | 1. Const./Rehab./Comp. of Various Gov't. Bldgs. |  | Bldgs. | - | Admin | a) | 13523124 | [12 empty] | See project listed below
|  | Struct., Fac. (Provincewide) |  |  |  |  | b) | Foronda
[7 empty] | c) | Admin
[7 empty] | d) | -
|  | 1.1 | Repair/Rehab. Of PEO Building (2nd District), Carmen | Bldgs. |  | Admin | a) | 2250000 | a) | 08/10/18 | e) | - | a) | 2250000 | a) | 100% | c) | 100% | a) | 16 | Completed as per physical accomplishment. Financial documents still on process
[7 empty] | b) | Andoy | b) | 02/18/19 | f) | 99 | b) | 2250000 | b) | - | d) | - | b) | 352
[7 empty] | c) | Admin | c) | 08/23/19 | g) | 12/13/2019 | c) | 2247549.05
[7 empty] | d) | - | d) | 2019-11-30
| E. | GENERAL FUND PROPER CY 2018
STIMULUS PROJECTS
ASUNCION
|  |  | Const. of Bleachers and Canopy, Canatan, Asuncion | Bldg. | sq.m | MLGU | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | 100% | c) | 100% | a) | - | Fund transfer ; COMPLETED - PCR & other completion documents for submission c/o Engr. Quajao
|  | 1 |  |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | 500000
[7 empty] | d) | - | d) | -
|  |  | Const. of Canopy, Camoning, Asuncion | Bldg. | sq.m | MLGU | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | 100% | c) | 100% | a) | - | Fund transfer ; COMPLETED - PCR & other completion documents for submission c/o Engr. Quajao
|  | 2 |  |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | 500000
[7 empty] | d) | - | d) | -
|  |  | Construction of Covered Court, San Vicente, Asuncion | Court. | sq.m | MLGU | a) | 500000 | a) | 2018-06-05 | e) | - | a) | 500000 | a) | 100% | c) | 100% | a) | - | Fund transfer ; COMPLETED - PCR & other completion documents for submission c/o Engr. Quajao
|  | 3 |  |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | 500000
[7 empty] | d) | - | d) | -
|  |  | Const. of MP Hall, Rizal ES, Binancian, Asuncion | Bldg. | sq.m | MLGU | a) | 1250000 | a) | 2019-02-04 | e) | - | a) | 1250000 | a) | 100% | c) | 100% | a) | - | Fund transfer ; COMPLETED - PCR & other completion documents for submission c/o Engr. Quajao
|  | 4 |  |  |  |  | b) | - | b) | 2019-06-18 | f) | - | b) | 1250000 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | 1250000
[7 empty] | d) | - | d) | -
|  |  | Const. of MP Hall, Liguyon ES, Binancian, Asuncion | Bldg. | sq.m | MLGU | a) | 1250000 | a) | 2019-02-04 | e) | - | a) | 1250000 | a) | 100% | c) | 100% | a) | - | Fund transfer ; COMPLETED - PCR & other completion documents for submission c/o Engr. Quajao
|  | 5 |  |  |  |  | b) | - | b) | 2019-06-16 | f) | - | b) | 1250000 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | 1250000
[7 empty] | d) |  | d)
NEW CORELLA
|  |  | Const. of Concrete Bleachers, Sta. Cruz,New Corella | Bleacher | sq.m | MLGU | a) | 500000 | a) | 2018-06-04 | e) | - | a) | 500000 | a) | 100% | c) | 100% | a) | - | Fund transfer ; COMPLETED - PCR & other completion documents for submission
|  | 6 |  |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | 500000
[7 empty] | d) | - | d) | -
|  |  | Completion of Mini GYM at Prk. 2, San Roque, New Corella | Gym | sq.m | MLGU | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | 100% | c) | 100% | a) | - | Fund transfer ; COMPLETED - PCR & other completion documents for submission
|  | 7 |  |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | 500000
[7 empty] | d) | - | d) | -
|  |  | Completion of Covered Court, Sto. Niño, New Corella | Court. | sq.m | MLGU | a) | 500000 | a) |  | e) | - | a) | 500000 | a) | 100% | c) | 100% | a) | - | Fund transfer ; COMPLETED - PCR & other completion documents for submission
|  | 8 |  |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | 500000
[7 empty] | d) | - | d) | -
|  |  | Construction of Public Market, Suawon, New Corella | Bldg. | sq.m | MLGU | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | 100% | c) | 100% | a) | - | Fund transfer ; COMPLETED - PCR & other completion documents for submission
|  | 9 |  |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | 500000
[7 empty] | d) | - | d) | -
|  |  | Construction of Concrete Line Drainage at Prk. 10 to Prk. 6, Del Pilar, New Corella | Drainage | sq.m | MLGU | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | 100% | c) | 100% | a) | - | Fund transfer ; COMPLETED - PCR & other completion documents for submission |  | AC
|  | 10 |  |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | AC
[7 empty] | c) | - | c) | - | g) | - | c) | 500000 | [8 empty] | AC
[7 empty] | d) | - | d) | -
|  |  | Construction of Stage with Comfort Rooms at Mesaoy Mini-Gym, Mesaoy, New Corella | Stage | sq.m | MLGU | a) | 500000 | a) | 2018-07-05 | e) | - | a) | 500000 | a) | 100% | c) | 100% | a) | - | Fund transfer ; COMPLETED - PCR & other completion documents for submission
|  | 11 |  |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | 500000
[7 empty] | d) | - | d) | -
|  | SAN ISIDRO |  |  |  |  | a) | 500000 | a) | -
|  | 1 | Rehabilitation & Flooring of Gymnasium Basketball Court, Mamangan, San Isidro | Court. | sq.m | Admin | a) | 500000 | a) | - | e) | - | a) | 500000 | [6 empty] | Completed as per physical accomplishment. Financial documents still on process
[7 empty] | b) | Ambrosio | b) | 2019-11-18 | f) | - | b) | 500000 | a) | 100% | c) | 100% | a) | -
|  | 12 |  |  |  |  | c) | PEO | c) | 2020-01-31 | g) | 2020-01-31 | c) | 500000 | b) | - | d) | - | b) | -
[7 empty] | d) | 74 CD | d) | -
TAGUM CITY
|  |  | Rehab. of Evacuation Center, Madaum, Tagum City | Bldg. | sq.m | Admin | a) | 500000 | a) | 2019-01-14 | e) | - | a) | 500000 | a) | 100% | c) | 100% | a) | 7 | Completed as per physical accomplishment. Financial documents still on process
|  | 13 |  |  |  |  | b) | Juan, Z | b) | 2019-11-18 | f) | 8 CD | b) | 500000 | b) | - | d) | - | b) | 161
[7 empty] | c) | PEO | c) | 2020-01-16 | g) | 2020-01-24 | c) | -
[7 empty] | d) | 60 CD | d) | 2020-01-24
IGCS
|  |  | Completion of Kasilak Day Care Center, Sta. Cruz, IGCS | Bldg. |  | Admin | a) | 500000 | a) | 2018-07-05 | e) | - | a) | 500000 | a) | 100.00% | c) | 100.00% | a) | - | Completed as per physical accomplishment. Financial documents still on process
|  | 14 |  |  |  |  | b) | Porras | b) | 2019-05-20 | f) | 136 CD | b) | 500000 | b) | - | d) | - | b) | -
[7 empty] | c) | PEO | c) | 2019-07-17 | g) |  | c) | -
[7 empty] | d) | 60 CD | d)
|  |  | Concreting of Brgy. Road from Prk. 1 to Prk. 2, Villarica, ICGS | Road | km | Contract | a) | 500000 | a) | 2019-01-14 | e) | - | a) | 500000 | a) | 100.00% | c) | 100.00% | a) | - | Completed as per physical accomplishment. Financial documents still on process
|  | 15 |  |  |  |  | b) | Porras | b) | 2019-11-19 | f) | 33 CD | b) | 500000 | b) | - | d) | - | b) | -
[7 empty] | c) | J-One Builders | c) | 2019-12-19 | g) | 2020-01-20 | c) | -
[7 empty] | d) | - | d) | -
|  |  | Const. of Concrete Fence of New Brgy. Site San Isidro, IGACOS | Bldg |  | - | a) | 500000 | a) |  | e) | - | a) | 500000 | a) | 100% | c) | 100% | a) | - | Completed as per physical accomplishment. Financial documents still on process
|  | 16 |  |  |  |  | b) | Andoy | b) | 2019-05-20 | f) | 136 | b) | 500000 | b) | - | d) | - | b) | -
[7 empty] | c) | Admin | c) | 2019-07-17 | g) | 2019-11-30 | c) | -
[7 empty] | d) | 60 | d) | 2019-11-30
| D. | 5% Calamity Fund CY 2018
1. Prevention and Mitigation
|  | 1.1 Improvement of Roads, Drainage & Canals |  | roads/canals | ln.m | Admin | a) | 3000000 | [12 empty] | Investigation/Inspection of priority projects.
[7 empty] | b) | -
[7 empty] | c) | PEO
[7 empty] | d) | -
|  |  | Rehab./Impv't. of Sonlon-Longanapan Road | road | km | Admin | a) | 1,500,000.00 | a) | 2019-03-12 | e) | - | a) | 1,500,000.00 | a) | 100% | c) | 100% | a) | 18 | Completed as per physical accomplishment. Financial documents still on process
|  | 1.1.1 |  |  |  |  | b) | Bataler | b) | 2019-09-16 | f) | 27 CD | b) | 1,500,000.00 | b) | - | d) | - | b) | 558
[7 empty] | c) | PEO | c) | 2019-10-18 | g) | 2020-02-29 | c) | 1400000
[7 empty] | d) | - | d) | 2020-02-29
| E. | 20% DEVELOPMENT FUND CY 2019 | [7 empty] | -
| 1. Various Government Buildings and Facilities Development Project (Provincewide) |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of recipients | Bldgs. | Admin/Contract | a) | 27000000 | [12 empty] | See projects listed below
[7 empty] | b) | Medalla
[7 empty] | c) | PEO
[7 empty] | d) | -
|  | Repair of Dacudao Health Center, Dacudao, San Isidro |  | Bldgs. | 49.80 sq.m | Admin | a) | 1000000 | a) | 2019-05-29 | e) | - | a) | 1000000 | a) | 100% | c) | 100% | a) | 8 | Completed as per physical accomplishment. Financial documents still on process
1.1 | [6 empty] | b) | Aclaracion | b) | 2019-08-05 | f) | - | b) | 1000000 | b) | - | d) | - | b) | 176
[7 empty] | c) | PEO | c) | 2019-10-15 | g) | - | c) | 850000
[7 empty] | d) | 76 CD | d) | 2019-12-26
|  | Const. of Quail House (PDNSC Ext. Campus), Sto. Niño, Talaingod |  | Bldg. | 63 sq.m | Households | a) | 750000 | a) | 2019-03-12 | e) | - | a) | 750000 | a) | 100% | c) | 100% | a) | 7 | On-going
1.2 | [6 empty] | b) | Dadula | b) | 2019-12-02 | f) | - | b) | 750000 | b) | - | d) | - | b) | 175
[7 empty] | c) | c) | c) | 2019-02-03 | g) | 2020-03-31 | c) | 750000
[7 empty] | d) | 70 CD | d) | 2020-03-31
STIMULUS PROJECTS
|  | Concreting of FMR, New Santiago, Asuncion |  | Road | km | MLGU | a) | 2500000 | a) | 2019-05-21 | e) | - | a) | 2500000 | a) | 100% | c) | 100% | a) | - | COMPLETED - PCR & other completion documents for submission c/o Engr. Cuajao
1.1 | [6 empty] | b) | - | b) | - | f) | - | b) | 2500000 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | 2500000
[7 empty] | d) | - | d) | -
|  | Installation of Bleacher for the Brgy. Gym, Concepcion, Asuncion |  | Bldg | sq.m | MLGU | a) | 1000000 | a) | - | e) | - | a) | 1000000 | a) | 100% | c) | 100% | a) | - | COMPLETED - PCR & other completion documents for submission c/o Engr. Cuajao
1.2 | [6 empty] | b) | - | b) | - | f) | - | b) | 1000000 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | 1000000
[7 empty] | d) | - | d) | -
Road ID |  | 1. Repair/Maintenance of Provincial Roads & Bridges |  | Road Maintenance | 109.55 km | MBA | a) | 41465029 | [12 empty] | See list of Provincial Roads
[7 empty] | b) | Paraguya
11DAN | [6 empty] | c) | PEO
[7 empty] | d) | 261 days
|  | Jct. Sawata - Bdry. Binasbas |  | Road Rehabilitation | 0.46 | MBA | a) | 500000 | a) | 2019-06-19 | e) | - | a) | 500000 | a) | 100.00% | c) | 100.00% | a) | - | Completed as per physical accomplishment. Financial documents still on process
043 | [6 empty] | b) | Pilotos | b) | 2020-02-03 | f) | - | b) | 500000 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | 2020-03-30 | g) | 2020-03-30 | c) | -
[7 empty] | d) | - | d) | -
| F. | GENERAL FUND CY 2019
[6 empty] | Admin | a) | 46740177 | [12 empty] | See list of Provincial Roads
Road ID |  | 1. Maintenance of Various Provincial Roads and Bridges at District II |  | Road Maintenance | 115.620 km |  | b) | Paraguya
[7 empty] | c) | PEO
11DAN
[7 empty] | d) | 261 days
|  | Dalisay - Mabuhay |  | Road Rehabilitation | 3.25 | MBA | a) | 1000000 | a) | 2019-05-16 | e) | - | a) | 1000000 | a) | 100% | c) | 100% | a) | 10 | Completed as per physical accomplishment. Financial documents still on process
102 | [6 empty] | b) | Gamad/Clar | b) | 2019-06-17 | f) | 166 CD | b) | 1000000 | b) | 100% | d) | - | b) | 50
[7 empty] | c) | Admin | c) | 2019-10-15 | g) | 2020-02-29 | c)
[7 empty] | d) | - | d) | 2020-02-29
|  | Cabay-angan - Esperanza |  | Road Rehabilitation | 5.37 | MBA | a) | 1300000 | a) | 2019-05-16 | e) | - | a) | 1300000 | a) | 100% | c) | 100% | a) | 9 | Completed as per physical accomplishment. Financial documents still on process
110 | [6 empty] | b) | Gamad/Clar | b) | 2019-06-17 | f) | - | b) | 1300000 | b) | - | d) | - | b) | 45
[7 empty] | c) | PEO | c) | 2019-10-15 | g) | 2020-02-15 | c)
[7 empty] | d) | - | d) | 2020-02-29
|  | Kinamayan - Moslog - Mahayag |  | Road Rehabilitation | 3.23 | MBA | a) | 1000000 | a) | 2019-05-16 | e) | - | a) | 1000000 | a) | 100% | c) | 100% | a) | 10 | Completed as per physical accomplishment. Financial documents still on process
124 | [6 empty] | b) | Gamad | b) | 2019-06-27 | f) | 35 CD | b) | 1000000 | b) | 100% | d) | - | b) | 50
[7 empty] | c) | PEO | c) | 2019-09-24 | g) | 2020-02-29 | c)
[7 empty] | d) | - | d) | 2020-02-29
|  | Kimamon - Lunga-og - Talomo |  | Road Rehabilitation | 5.99 | MBA | a) | 1800000 | a) | 2019-05-20 | e) | - | a) | 1800000 | a) | 100% | c) | 100% | a) | 9 | Completed as per physical accomplishment. Financial documents still on process
144 | [6 empty] | b) | Gamad/Piad | b) | 2019-06-17 | f) | 77 CD | b) | 1800000 | b) | 100% | d) | - | b) | 6
[7 empty] | c) | PEO | c) | 2019-09-16 | g) | 2020-02-15 | c) | 1800000
[7 empty] | d) | - | d) | 2020-02-20
2. Various Government Buildings and Facilities Development Project (Provincewide) |  |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of recipients | - | Admin/Contract | a) | 27000000 | [12 empty] | See projects listed below
[7 empty] | b) | Medalla
[7 empty] | c) | PEO
[7 empty] | d) | -
|  | Completion of Perimeter Steel Fence @ Lunga-og E/S, Brgy. Lunga-og, Sto. Tomas |  | Fence | sq.m | 0 | a) | 1630000 | a) | 2019-01-17 | e) | - | a) | 1630000 | a) | 100% | c) | 100% | a) | 10 | Completed as per physical accomplishment. Financial documents still on process
| 2.1 | [5 empty] | b) | Azotes | b) | 2019-10-16 | f) | - | b) | 1630000 | b) | - | d) | - | b) | 220
[7 empty] | c) | PEO | c) | 2020-03-03 | g) | 2020-02-29 | c) | 1185633.74
[7 empty] | d) | - | d) | -
3. Stimulus Projects for Various Barangays |  |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | sq.m | Admin/Contract | a) | 41500000 | [12 empty] | See projects listed below
[7 empty] | b) | Medalla
[7 empty] | c) | PEO
[7 empty] | d) | -
IGCS
3.1 |  | Rehab. Of Multi-Purpose Hall, Aundanao, IGCS |  | Bldg. | - | Admin | a) | 500000 | a) | 2019-03-18 | e) | - | a) | 500000 | a) | 100% | c) | 100% | a) | 4 | Completed as per physical accomplishment. Financial documents still on process
[7 empty] | b) | Porras | b) | 2019-11-18 | f) | 64 CD | b) | 500000 | b) | 100% | d) | - | b) | 22
[7 empty] | c) | PEO | c) | 2019-12-27 | g) | 2020-02-29 | c) | -
[7 empty] | d) | 60 CD | d) | 2020-02-29
D. 5% CALAMITY FUND CY 2019
|  | Desiltation/Excavation of rivers and creeks |  | creeks and canals deislted | ln.m | Admin/Contract | a) | 3000000 | [12 empty] | See project listed below
| 1 | [5 empty] | b) | Paraguya
[7 empty] | c) | PEO
[7 empty] | d) | -
|  |  | Desiltation of Mactan River Ph. II | Desiltation | ln.m | Admin | a) | 500000 | a) | 2019-08-08 | e) | - | a) | 500000 | a) | 100% | c) | 100% | a) | 5 | Completed as per physical accomplishment. Financial documents still on process
|  | 1.1 |  |  |  |  | b) | Toquero | b) | 2019-07-29 | f) | - | b) | 500000 | b) | - | d) | - | b) | 40
[7 empty] | c) | PEO | c) | 2019-09-27 | g) | 2019-09-27 | c) | -
[7 empty] | d) | 60 C.D | d) | -
|  | Improvement of roads, drainage and canal |  | Protection dikes/slope protection | - | - | a) | 3000000 |  |  |  | - | [8 empty] | See project listed below
| 2 | [5 empty] | b) | Paraguya
[7 empty] | c) | PEO
[7 empty] | d) | -
|  |  | Repair/Rehab of Drainage System & Ground Gravelling at Kimamon NHS | Road | ln.m | Admin | a) | 464833 | a) | - | e) | - | a) | 464833 | a) | 100.00% | c) | 100.00% | a) | 5 | Completed as per physical accomplishment. Financial documents still on process
|  | 2.1 |  |  |  |  | b) | Azotes | b) | 2019-09-16 | f) | - | b) | 464833 | b) | - | d) | - | b) | 110
[7 empty] | c) | Admin | c) | 2019-10-10 | g) | 2019-10-10 | c) | -
[7 empty] | d) | - | d) | -
E. SUPPLEMENTAL BUDGET NO. 1 CY 2019
|  |  | Repair maintenance of OPD, Pharmacy building, DDNH - CZ Compound | Bldg. | sq.m | Admin | a) | 100000 | a) | - | e) | - | a) | 100000 | a) | 100.00% | c) | 100.00% | a) | 5 | Completed as per physical accomplishment. Financial documents still on process
|  | 1 |  |  |  |  | b) | Estorco | b) | 2019-06-14 | f) | - | b) | 100000 | b) | - | d) | - | b) | 110
[7 empty] | c) | Admin | c) | 2019-06-28 | g) | 2019-06-28 | c) | -
[7 empty] | d) | - | d) | -
|  |  | Rehab/ Impvt of Prk 1 - Prk 2 Sitio Pawas Provincial Road |  | - | - | [14 empty] | Completed as per physical accomplishment. Financial documents still on process
|  |  |  | creeks and canals deislted |  |  | a) | 1500000 | a) | 7/23/2019 | e) |  | a) | 1500000 | a) | 100% | c) | 100% | a) | 3
|  | 2 |  |  |  |  | b) | Sanchez | b) | 8/5/2019 | f) | 124 | b) | 1500000 | b) | - | d) | - | b) | 135
[7 empty] | c) | Admin | c) | 9/28/2019 | g) | 1/30/2020 | c)
[7 empty] | d) | 55 | d) | 1/30/2020
F. | SUPPLEMENTAL BUDGET NO. 4 CY 2019
| 1 | PURCHASE OF INSTRUMENT |  | Geo Resistivity | - | - | a) | 6567412 | a) | - | e) | - | a) | 6567412 | a) | - | c) | - | a) | - | Already delivered last december 16, 2019. Financial documents still on process
|  | 1.1 | Purchase of Geo Resistivity Instrument |  |  |  | b) | - | b) | - | f) | - | b) | 6567412 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
G. | TRUST FUND
1. OPPAP-PAMANA
1. SOLAR DRYER
|  |  | Post Harvest Facilities (Corn Mill, Solar Dryer, Corn Sheller), Sitio Butay, Palma Gil, Talaingod, Davao del Norte | Bldg. | sq.m | Admin | a) | 1850000 | a) | CY 2019 | e) | - | a) | 1850000 | a) | 100.00% | c) | 100.00% | a) | 11 | Completed as per physical accomplishment. Financial documents still on process
|  | 1.1 |  |  |  |  | b) | Dadula | b) | July 16, 2019 | f) | 123 CD | b) | 1850000 | b) | - | d) |  | b) | 246
[7 empty] | c) | PEO | c) | Nov. 13, 2019 | g) | 2020-03-31 | c) | 636952.94
[7 empty] | d) | 243 CD | d) | 2020-03-15
2. WATER SYSTEM
|  |  | Upgrading of Existing PWS Level II in Sitio Langan, Gupitan, Kapalong | PWS | Households | Admin | a) | 2500000 | a) | 2019-11-16 | e) |  | a) | 2500000 | a) | 100.00% | c) | 100.00% | a) | 6 | Completed as per physical accomplishment. Financial documents still on process
|  | 2.1 |  |  |  |  | b) | kabingue | b) | 2019-11-16 | f) | 30 CD | b) | 2500000 | b) | - | d) | - | b) | 150
[7 empty] | c) | PEO | c) | 2020-02-27 | g) | 2020-03-28 | c) | 2000000
[7 empty] | d) | 169 CD | d) | 2020-03-28
|  |  | Construction of PWS Level II, Sitio Upper Dulyan, Palma Gil, Talaingod | PWS | Households | Admin | a) | 1000000 | a) | 2019-11-12 | e) | - | a) | 1000000 | a) | 100.00% | c) | 100.00% | a) | 9 | Completed as per physical accomplishment. Financial documents still on process
|  | 2.2 |  |  |  |  | b) | kabingue | b) | 2019-12-12 | f) | 40 CD | b) | 1000000 | b) | - | d) | - | b) | 138
[7 empty] | c) | PEO | c) | 2020-02-19 | g) | 2020-03-30 | c)
[7 empty] | d) | 100 CD | d) | 2020-03-30
2. PROJECTS FOR PROVINCIAL VETERINARY OFFICE
CONTRACT PACKAGE
|  |  | Establishment of Multiplier Farm Project Sto. Niño, Talaingod | Bldg. | sq.m | Contract | a) | 500000 | a) | CY 2019 | e) | - | a) | 500000 | a) | 100% | c) | 100% | a) | - | Completed as per physical accomplishment. Financial documents still on process
|  | 2.1 |  |  |  |  | b) | Dadula | b) | 2020-03-10 | f) | - | b) | 500000 | b) | - | d) | - | b) | -
[7 empty] | c) | Alphabel | c) | 2020-03-15 | g) | 2020-03-15 | c) | -
[7 empty] | d) |  | d) | -
|  |  | Establishment of Multiplier Farm (Poultry House) Project Sto. Niño, Talaingod | Bldg. | sq.m | Contract | a) | 1000000 | a) | CY 2019 | e) | - | a) | 1000000 | a) | 100% | c) | 100% | a) | - | Completed as per physical accomplishment. Financial documents still on process
|  | 2.2 |  |  |  |  | b) | Dadula | b) | 2020-03-10 | f) | - | b) | 1000000 | b) | - | d) | - | b) | -
[7 empty] | c) | Alphabel | c) | 2020-03-15 | g) | 2020-03-15 | c) | -
[7 empty] | d) |  | d) | -
Formulas:
Date A lot. Rel. = [Date A lot. Rel., row above]
Date completed = [Date A lot. Rel., row below]
Date completed = [Date A lot. Rel.]

## On-going(Central)
PROVINCE OF DAVAO DEL NORTE
ACCOMPLISHMENT REPORT
1ST QUARTER REPORT CY 2020
SECTOR: ECONOMIC (INFRASTRUCTURE DEV'T. PROGRAM)
OFFICE/AGENCY: PROVINCIAL ENGINEER'S OFFICE
AREA: AREA: 1ST AND 2ND ENGINEERING DISTRICT - ON-GOING PROJECTS
| Name of Project |  |  |  |  | Type | Physical | Mode | PROJECT DATA | [5 empty] | Financial (000) |  | Physical Accomplishment |  |  |  | Employment |  | REMARKS
[6 empty] | of | Target | of | a) Project Cost |  | a) | Date A lot. Rel. | e) | # of days suspended | a) Program |  | a) Planned |  | c) Actual |  | Generated
[6 empty] | Project | (Descrip | Impl. | b) Project Engineer |  | b) | Date Started | f) | # of days extended | b) Allotment |  | b) Revised |  | d) Slippage |  | a) # of Persons | # of Persons
[6 empty] | (Location) | tion) |  | c) Implementor |  | c) | Target Compl. Date | g) | Date completed | c) Disbursement | [5 empty] | b) | Man-days
[9 empty] | d) Duration |  | d) | Revised Compl. Date
| I. | PROJECTS UNDER THE CONTINUING APPROPRIATION | [21 empty] | AC |  |  |  | 893809.45
|  |  | SLRF 2015 | [7 empty] | a) |  | e) | 65 days | a) |  | a) | 100% | c) | 100% | a) | 3 | Completed as per POW, Financial Documents on Process | 2
|  |  | Rehab. of Jct. Highway-Tuganay-Anibongan-BE Dujali-Kinamayan Provincial Road (Furtheranace) |  |  | Slope protection | - | - | a) | 1911175.99 | b) | 2019-02-18 | f) | 47 days | b) |  | b) |  | d) | 0% | b) | 60 |  | 2
[9 empty] | b) | Balbastro | c) | 2019-09-21 | g) | 9/21/2019 | c) | [8 empty] | 2
[9 empty] | c) | Admin | d) | [12 empty] | 2
[9 empty] | d) | - | [13 empty] | 2
| A. | Supplemental Budget # 1 CY 2015 | [21 empty] | FS
|  |  | 1. Proposed Davao del Norte Tourism Billboard |  |  | Billboard |  | Admin | a) | 756,400.00 | a) | 05/06/15 | e) | - | a) | 756,400.00 | a) | 11.78% | c) | 11.78% | a) | - | delay due to change location & design code. For AIP amendment from Panabo City to Gov't Center, Mankilam | FS
|  |  | Brgy. Lasang, Panabo City | [5 empty] | b) | Porras | b) | 03/30/15 | f) | - | b) | 756,400.00 | b) | - | d) | - | b) | - |  | FS
[9 empty] | c) | PEO | c) | 05/10/15 | g) | - | c) | 332,087.30 | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
| B. | 20% Development Fund CY 2017 | [21 empty] | 1 | 1 | Asuncion | Red
|  | 1. STIMULUS PROJECTS CY 2017 | [21 empty] | 1 | 2 | B.E. Dujali | Yellow
|  | ASUNCION | [21 empty] | FS | 3 | Carmen | Blue
|  |  | 1 | Construction of Water Reservoir & Purchase of P.E. Pipelines, Sagayen, Asuncion |  | Water System | Households | MLGU | a) | 500000 | a) | 2017-12-28 | e) | - | a) | 500000 | a) | 90.00% | c) | 90.00% | a) | - | Suspended due to non availability of water source during drilling.Find another location. Fund already transferred at Municipality of Asuncion with ChecK No. 2445174 and OR # 9238468, | 1 | 4 | Kapalong | Pink
[9 empty] | b) | - | b) | 2018-11-15 | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 1 | 5 | New Corella | Gray
[9 empty] | c) | MEO | c) | - | g) | - | c) | - | [7 empty] | 1 | 6 | San Isidro | Orange
[9 empty] | d) | - | d) | - | [11 empty] | 1 | 7 | Sto Tomas | Sky Blue
|  |  | NEW CORELLA | [20 empty] | FS | 8 | Talaingod | Violet
|  |  |  | Road Rehabilitation at Prk. 1-Prk. 5, Sta. Fe, New Corella |  | Road | km. | MLGU | a) | 500000 | a) | 2017-11-29 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Fund already transferred at Municipality of New Corella with ChecK No. 2445213 and OR # 8592072, dated March 13, 2018. Waiting for availability of Bulldozer | 1 | 9 | Panabo City | Brown
|  |  | 2 | [5 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 1 | 10 | IGACOS | Yellow Green
[9 empty] | c) | MEO | c) | - | g) | - | c) | - | [7 empty] | 1 | 11 | Tagum City | Green
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | TALAINGOD | [20 empty] | 1
|  |  |  | Const. of Covered Court Bleacher, Palma Gil, Talaingod |  | Court | sq.m | MLGU | a) | 500000 | a) | 2017-12-28 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | (Fund already transferred at Municipality of Talaingod with ChecK No. 2445181 and OR # 7955667, dated March 16, 2018 . Amended from Electrification @ Prk. 1A-Prk. 5A) | 1
|  |  | 3 | [5 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 1
[9 empty] | c) |  | c) | - | g) | - | c) | - | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  | 2. Const./Rehab./Comp. of Various Gov't. Bldgs. |  |  |  | Bldgs. | sq.m | Admin/Contract | a) | 9,000,000.00 | [12 empty] | Investigation/Inspection of priority projects | 1
|  | Struct., Fac. (Provincewide) | [6 empty] | b) | Foronda/Ababon | [13 empty] | 1
[9 empty] | c) | PEO | [13 empty] | 1
[9 empty] | d) | - | [13 empty] | 1
|  |  |  | Rehab. Of PEO Training Center, (PDPM),Mankilam, Tagum City, (Part of P803,000.00)(20% DF CY 2018-P326,124.00) |  | Bldgs. | sq.m | Admin | a) | 476,876.00 | a) | 2019-02-12 | e) | - | a) | 476,876.00 | a) | 99.00% | c) | 99.00% | a) | 3 | Suspended (additional PR for Elect. Mat.) dated March 9, 2020 | 1
|  |  | 2.1 | [5 empty] | b) | Chua | b) | 2019-11-04 | f) | - | b) | 476,876.00 | b) | - | d) | - | b) | 57 |  | 1
[9 empty] | c) | PEO | c) | 2020-01-17 | g) | - | c) | 407,521.70 | [7 empty] | 1
[9 empty] | d) | 50 WD | d) | 2020-03-15 | [11 empty] | 1
|  | 3. GROUND DEVELOPMENT | [21 empty] | 1
|  |  | 3.1 | Ground Development and landscape @ PDRRMD, Gov't. Center, Mankilam, Tagum City |  | Ground Dev't. | km. | Admin | a) | 1000000 | a) | 2019-03-19 | e) | - | a) | 1000000 | a) | 75.24% | c) | 75.24% | a) | 8 | Suspended (Waiting for the complete delivery of materials) dated March 2, 2020 | 1
[9 empty] | b) | Juan | b) | 2019-11-04 | f) | - | b) | 1000000 | b) | - | d) | - | b) | 152 |  | 1
[9 empty] | c) | PEO | c) | 2020-02-29 | g) | - | c) | 752400 | [7 empty] | 1
[9 empty] | d) | 118 CD | d) | - | [11 empty] | 1
| C. | Supplemental Budget # 4 CY 2017 | [21 empty] | 1
|  |  |  | Upgrading of DDNSTC (Basketball/Voleyball MP Covered Court),Sports Center, Mankilam, Tagum City |  | Covered | 2252.69 sq.m | Contract | a) | 99992356.64 | a) | 2018-10-16 | e) | - | a) | 99992356.64 | a) | 100% | c) | 67.5% | a) | 10 | On-going (Time extension for verification) | FS
|  |  | 1 | [5 empty] | b) | Daral | b) | 2018-07-17 | f) | 20 CD | b) | 99992356.64 | b) | - | d) | -32.5% | b) | 310 |  | 1
[9 empty] | c) | YBC | c) | 2019-07-11 | g) | - | c) | 18, 280, 402.33 | [7 empty] | 1
[9 empty] | d) | 360 CD | d) | 2020-02-02 | [11 empty] | 1
| D. | Trust Fund 2014 | [21 empty] | 1
|  |  | 1. PAMANA-DILG CY 2014 | [20 empty] | 2
|  |  |  | Construction of Biga Bridges, Kapalong (Original Contract Cost: P 24,959,503.45; Variation Order: P 4,067,412.00) |  | Road | 2-18ln.m | Contract | a) | 29026915.45 | a) | CY 2014 | e) | 48 CD | a) | 29026915.45 | a) | 100.00% | c) | 85.37% | a) | 8 | Suspended due to RROW dated Dec. 13, 2019 | 2
|  |  | 1.1 | [5 empty] | b) | Limpo | b) | 2016-07-01 | f) | - | b) | 29026915.45 | b) | 99.7% | d) | -14.33% | b) | 290 |  | 2
[9 empty] | c) | Dvo. Rock Mixer | c) | 2018-07-30 | g) | - | c) | 18,489,834.55 | [7 empty] | 2
[9 empty] | d) | 880 CD | d) | 2020-03-25 | [11 empty] | AC
| D. | Trust Fund 2015 | [21 empty] | AC
|  |  | 1. PRDP CY 2014 | [20 empty] | 2
|  |  |  | Rehab. of Esperanza-Pob. Sto. Tomas, FMR, DDN |  | Road | 12.77399 km | Contract. | a) | 117,410,426.30 | a) | CY 2014 | e) | - | a) | 117,410,426.30 | a) | 100% | c) | 87.82% | a) | 20 | On-going (Waiting for approve Variation order for billing) | AC
|  |  | 1.1 | [5 empty] | b) | Palero | b) | 2017-03-22 | f) | - | b) | 117,410,426.30 | b) | 95.53% | d) | -7.705% | b) | 600 |  | AC
[9 empty] | c) | Alzam | c) | 2019-07-22 | g) | - | c) | 113,335,769.31 | [7 empty] | AC
[9 empty] | d) | 853 CD | d) | - | [11 empty] | 1
| E. | Trust Fund 2015 | [21 empty] | 1
|  |  | 1. PRDP CY 2015 | [20 empty] | 1
|  |  |  | Rehab. Of Capungagan-Boundary San Miguel FMR, Kapalong, Davao del Norte |  | Road | 10.6 kms. | Contract. | a) | 108,303,841.70 | a) | CY 2015 | e) | 140 CD | a) | 108,303,841.70 | a) | 100.00% | c) | 93.8% | a) | 38 | On-going, Increase of Project Cost due to Variation Order with Extra Work. (Php 4,992,591.29) | 1
|  |  | 1.1 | [5 empty] | b) | Nasol | b) | 2016-04-06 | f) | 634 | b) | 108,303,841.70 | b) | 97.28% | d) | -3.48% | b) | 1140 |  | 1
[9 empty] | c) | VICLAO | c) | 2017-03-26 | g) | - | c) | 60,050,673.93 | [7 empty] | 1
[9 empty] | d) | 1410 | d) | 2020-02-14 | [11 empty] | 1
|  |  |  | Rehab. Of Pob.-Limbaan-Suawon-Macgum FMR w/ Bridge, New Corella, Davao del Norte |  | Road | 15.01 kms./42 ln.m | Contract. | a) | 205,202,114.16 | a) | CY 2015 | e) | 229 CD | a) | 205,202,114.16 | a) | 100.00% | c) | 77.49% | a) | 40 | Increase of Project Cost due to Variation Order Php 14,948,622.18, Partial suspension due to soft soil from sta. 8+000 - 10+000 | 1
|  |  | 1.2 | [5 empty] | b) | Madrigal | b) | 2016-04-08 | f) | 490 CD | b) | 205,202,114.16 | b) | 83.77% | d) | -6.282% | b) | 1200 |  | 1
[9 empty] | c) | Dvo. Rock Mixer | c) | 2019-01-18 | g) | - | c) | 141497191.47 | [7 empty] | 1
[9 empty] | d) | 1529 CD | d) | 2020-08-15 | [11 empty] | 1
|  |  |  | Rehab. Of Sonlon - Camansa FMR Asuncion, Davao del Norte |  | Road | 10.23 km. | Contract. | a) | 215,125,015.81 | a) | 2018-09-18 | e) |  | a) | 215,125,015.81 | a) | 39.51% | c) | 31.6% | a) | 30 | On-going | 1
[9 empty] | b) | Fabiala | b) | 2019-05-28 | f) |  | b) | 215,125,015.81 | b) | - | d) | -7.91% | b) | 780 |  | FS
|  |  | 1.3 | [5 empty] | c) | Three w/Builders, Inc/Davao Rock Mixer Enterprises (JV) | c) | 2020-12-31 | g) | - | c) | 40,523,099.23 | [7 empty] | 1
[9 empty] | d) | 384 CD | d) | - | [11 empty] | 1
| F. | Trust Fund 2016 | [21 empty] | 1 | 1 | Asuncion | Red
|  |  | 1. PRDP CY 2016 | [20 empty] | 1 | 2 | B.E. Dujali | Yellow
|  |  |  | Cacao Production and Beans Marketing, Capungagan, Kapalong, Davao del Norte |  | Bldg. | 3610 sq.m | Contract. | a) | 5873626.8 | a) | CY 2016 | e) | - | a) | 5873626.8 | a) | 100% | c) | 91.09% | a) |  | Suspended due to modification of Detailed Design of mechanical Drier dated November 23, 2019 | FS
|  |  | 1.1 | [5 empty] | b) | Delos Reyes | b) | 2019-03-19 | f) | - | b) | 5873626.8 | b) | - | d) | -8.905% | b) |  |  | 1
[9 empty] | c) | MICAH CONST. & SUPPLY | c) | 2019-11-23 | g) | - | c) | 4698901.44 | [7 empty] | 1
[9 empty] | d) | 250 CD | d) | - | [11 empty] | 1
|  |  |  | Improvement of New Corella Nursery with Organic Input Production & Common Facility, Davao del Norte |  | Bldg. | 1901.00 sq.m | Contract. | a) | 9,889,628.45 | a) | CY 2016 | e) | 222 CD | a) | 9,889,628.45 | a) | 80.36% | c) | 46.3% | a) | 10 | On-going; Resumption date: August 27, 2019 | 1
|  |  | 1.2 | [5 empty] | b) | Delos Reyes/Cabañero | b) | 2019-01-17 | f) | - | b) | 9,889,628.45 | b) | 49.99% | d) | -3.684% | b) | 250 |  | FS
[9 empty] | c) | SOUTH IRONROCK CORPORATION | c) | 2019-11-23 | g) | - | c) | - | [7 empty] | AC
[9 empty] | d) | 514 CD | d) | 2020-06-18 | [11 empty] | 1
|  |  |  | Improvement of Sto. Tomas Production Center with Common Facility, Sto. Tomas |  | Bldg. | 1901 sq.m | Contract. | a) | 9825000 | a) | CY 2014 | f) | - | b) |  | a) |  | c) |  | a) |  | Suspended due to land unsettlement | 1
|  |  | 1.3 | [5 empty] | b) | Azotes | b) | 2018-01-29 | g) | - | c) | - | b) |  | d) |  | b) |  | Revised POW and DED On-going
[9 empty] | c) | Manantan | c) | 2018-09-24 | [11 empty] | 1
[9 empty] | d) | 330 C.D | d) | 2018-12-05 | [11 empty] | FS
| G. | Trust Fund 2017 | [21 empty] | AC
|  |  | 1. CMGP (Conditional Matching Grant to Provinces) | [20 empty] | 1
|  |  |  | Road Upgrading km.9 sagayen-Sawata (Sagayen-Jct. San Miguel Section) |  | Road | 10.20 km | Contract | a) | 139,761,975.14 | a) | CY 2017 | e) | - | a) | 139,761,975.14 | a) | 94.44% | c) | 94.44% | a) | 28 | On-going (Suspended dated January 28, 2019) | 1
|  |  | 1.1 | [5 empty] | b) | Avila | b) | 2018-10-01 | f) | 209 CD | b) | 139,761,975.14 | b) | - | d) | - | b) | 11170 |  | 1
[9 empty] | c) | Legacy Const. Corp. | c) | 2019-08-22 | g) | - | c) | 63100753.7 | [7 empty] | 1
[9 empty] | d) | 326 CD | d) | 2020-03-18 | [11 empty] | 1
|  | C.5 | 2. QRF - Trust Fund | [20 empty] | 1
|  |  |  | Rehab. Of Saug Bridge of Slope Protection |  | Slope | 356.40 cu.m | Admin | a) | 4,850,000.00 | a) | 2018-05-25 | e) | 371 CD | a) | 4,850,000.00 | a) | 45.49% | c) | 40.31% | a) | 17 | On-going (Resumption February 3, 2020, Suspended dated January 28, 2019) | AC
|  |  | 2.1 | [5 empty] | b) | Gone | b) | 2019-01-03 | f) | - | b) | 4,850,000.00 | b) | - | d) | -5.18% | b) | 306 |  | 1
[9 empty] | c) | PEO | c) | 2019-03-25 | g) | - | c) | 1628912.92 | [7 empty] | 1
[9 empty] | d) | 82 CD | d) | 2020-05-02 | [11 empty] | 1
|  |  |  | Re-channeling of BIGA River with Earth Dike and Slope Protection, Brgy. Gupitan, Kaplaong |  | Slope | 0.9 km | Contract | a) | 12,100,000.00 | a) | 2018-07-20 | e) | - | a) | 12,100,000.00 | a) | 8.30% | c) | 3.36% | a) | 4 | Suspended dated March 25, 2019 due to Road Right of Way (RROW) | 1
|  |  | 2.2 | [5 empty] | b) | Limpo | b) | 2019-02-22 | f) | - | b) | 12,100,000.00 | b) |  | d) | -4.94% | b) | 120 |  | 1
[9 empty] | c) | Alpha & Omega | c) | 2019-06-11 | g) | - | c) | - | [7 empty] | 1
[9 empty] | d) | 110 CD | d) | [12 empty] | 1
| H. | 20% Development Fund CY 2016 | [21 empty] | 1
|  |  | 1. Rural Electrification (Provincewide) |  |  | Elect. | km | Admin | a) | 5000000 | [12 empty] | See projects listed below | FS
[9 empty] | b) | Foronda/Ababon | [13 empty] | AC
[9 empty] | c) | Admin | [13 empty] | 1
[9 empty] | d) | - | [13 empty] | 1
|  |  | 1.1 | Inst. of transformer and accessories, |  | Elect. | Households | Admin | a) | 150,000.00 | a) | 2018-07-31 | e) | - | a) | 150,000.00 | a) | - | c) | - | a) | - | Purchase Order # 2019103228 - Transformer | 1
|  |  |  | Brgy. Kinawitnon |  |  |  |  | b) | - | b) | - | f) | - | b) | 150,000.00 | b) | - | d) | - | b) | - | Purchase Order # 2019102931 - Billboard | 1
[9 empty] | c) | - | c) | - | g) | - | c) | - | [6 empty] | Purchase Order # 2019103227 - Lumber | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | 1.2 | Rural Electrification at brgy. Sta. Cruz, |  | Elect. | Households | Contract | a) | 2000000 | a) | - | e) | - | a) | 2000000 | a) | - | c) | - | a) | - | Delay due to slow action of Daneco for staking. c/o Engr. Kim
|  |  |  | talikud, Samal |  |  |  |  | b) | - | b) | - | f) | - | b) | 2000000 | b) | - | d) | - | b) | -
[9 empty] | c) | Admin | c) | - | g) | - | c) | -
[9 empty] | d) | - | d) | -
|  |  | 2. Const./Rehab./Comp. of Various Gov't. Bldgs. |  |  | Bldgs./ | sq.m | Admin | a) | 9,000,000.00 | [12 empty] | See project listed below
|  |  | Struct., Fac. (Provincewide) | [5 empty] | b) | Foronda/Ababon | [13 empty] | 1
[9 empty] | c) | PEO | [13 empty] | 1
|  |  | 2.1 | Construction of Provincial Training Center |  | Fence | sq.m | Admin | a) | 940,000.00 | a) | 2017-09-19 | e) | - | a) | 940,000.00 | a) | 68.00% | c) | 75.00% | a) | - | Temporarily suspended 4/23/18 due to undemolished structures of illegal settlers | 1
|  |  |  | Compound Fence, Kinawitnon, Babak |  |  |  |  | b) | Pacquiao | b) | 2018-03-12 | f) | - | b) | 940,000.00 | b) | - | d) | - | b) | -
|  |  |  | District, IGCS |  |  |  |  | c) | PEO | c) | 2018-06-19 | g) | - | c) | 933,418.80 | [7 empty] | FS
[9 empty] | d) | - | d) | - | [11 empty] | 1
| I. | 20% Development Fund CY 2017 | [21 empty] | 1
|  |  | STIMULUS PROJECTS | [20 empty] | 1
|  |  | PANABO CITY | [20 empty] | 1
|  |  |  | Const of Market Stall/Building, Consolacion, Panabo City |  | Bldg. | sq.m | MLGU | a) | 500000 | a) | 2017-12-28 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Fund transfer to LGU- 3/28/2019 with check no.2574928 and OR no. 0166514 - Issued warning for Termination of the Contract | 1
|  |  | 1 | [5 empty] | b) | - | b) | 2019-05-28 | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 1
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  |  | Rehab. Of Multi-Purpose Hall (Covered Court), Upper Licanan, Panabo City |  | Footbridge | sq.m | MLGU | a) | 500000 | a) | 2017-12-28 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Fund transfer to LGU- 3/28/2019 with check no.2574927 and OR no. 0166516 - Delivery of Materials on process | 1
|  |  | 2 | [5 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 1
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  |  | Impv't. of Multi-Purpose Gym, Kauswagan, Panabo City |  | GYM | sq.m | MLGU | a) | 500000 | a) | 2019-02-04 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Fund transfer to LGU- 3/28/2019 with check no.2574942 and OR no. 0166515 - procurement on process for bidding 8/5/2019 | 1
|  |  | 3 | [5 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 1
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | AC
|  |  |  | Const. of MP Bldg. w/ Electrical installation, San Roque, Panabo City |  | Bldg. | sq.m | MLGU | a) | 500000 | a) | 2018-01-31 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Fund transfer to LGU- 3/28/2019 with check no. 2574942 and OR no 01665515 - procurement on process | AC
|  |  | 4 | [5 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | AC
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  |  | Const. of Multi-Purpose Bldg.,Cacao, Panabo City |  | Bldg. | sq.m | MLGU | a) | 300000 | a) | 2017-12-19 | e) | - | a) | 300000 | a) | - | c) | - | a) | - | Issued warning for termination of the contract | 1
|  |  | 5 | [5 empty] | b) | - | b) | 2018-12-14 | f) | - | b) | 300000 | b) | - | d) | - | b) | - |  | 1
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 1 | 21512501.501
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  |  | Const. of Multi-Purpose Bldg. @ A.O. Floriendo National Highschool, Panabo City |  | Bldg. | sq.m | MLGU | a) | 500000 | a) | 2017-12-19 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Fund transfer to LGU- 3/28/2019 with check no. 2574939 and OR no. 0166518 - Materials Delivered. Construction on-going | 2
|  |  | 6 | [5 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 2
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | -
STO. TOMAS
|  |  |  | Const. of Concrete Drainage Canal, Kimamon, Panabo City |  | Drainage | ln.m | MLGU | a) | 500000 | a) | 2017-12-19 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For Implementation
|  |  | 7 | [5 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | AC
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | AC
[9 empty] | d) | - | d) | - | [11 empty] | AC
|  |  | IGACOS | [20 empty] | 1
|  |  |  | Impv't. of Brgy. Street Electrification at Brgy. Anonang, IGCS |  | Elect. | Households |  | a) | 500000 | a) | 2017-11-28 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Verified at PBO 7/18/2019 that fund is not available. Proposed priority project for 2020\ | 1
|  |  | 8 | [5 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 1
[9 empty] | c) | PEO | c) | - | g) | - | c) | - | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | AC
| J. | Trust Fund 2017 | [21 empty] | AC
|  |  | 1. OPPAP-PAMANA | [20 empty] | AC
|  |  | 1.1 | Const. of Trading Post, Storage Building |  | Bldg. | sq.m | Contract | a) | 3,975,000.00 | a) | CY 2017 | e) | - | a) | 3,975,000.00 | a) | - | c) | - | a) | - | Abstract 1220194004 (Tagum Builders) | AC
|  |  |  | with (1) unit Hauling Truck, Brgy. Pandapan |  |  |  |  | b) | - | b) | - | f) | - | b) | 3,975,000.00 | b) | - | d) | - | b) | - | PO # 2019102828 - Truck | AC
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | AC
[9 empty] | d) | - | [13 empty] | 1
|  |  | 1.2 | Const. of Trading Post, Storage Building |  | Bldg. |  | Contract | a) | 3,975,000.00 | a) | CY 2017 | e) | - | a) | 3,975,000.00 | a) | 24.85% | c) | 30.8% | a) | 10 | On-going | 2
|  |  |  | with (1) unit Hauling Truck, Prk. Ramihan |  |  |  |  | b) | Azotes | b) | 2019-11-21 | f) | - | b) | 3,975,000.00 | b) | - | d) | 5.95% | b) | 260 |  | 2
|  |  |  | Datu Abdul, Panabo City |  |  |  |  | c) | Ultra Core | c) | 2019-04-05 | g) | - | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
[6 empty] | - | - | - | a) | 4000000 | a) | CY 2018 | e) | - | a) | 4000000 | a) | - | c) | - | a) | - | For bidding | AC
|  |  | 1.3 | Trading Post, Storage and Hauling Truck Libuak, Island Garden City of Samal (IGACOS) |  |  |  |  | b) | - | b) | - | f) | - | b) | 4000000 | b) | - | d) | - | b) | - |  | AC
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | AC
` | [8 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | 1.4 | Construction of Tribal Hall, Sto. Tomas |  | Bldg. |  | Admin | a) | 500000 | a) | CY 2018 | e) | - | a) | 500000 | a) | 100% | c) | 89.5% | a) | 7 | Suspended June 28, 2019. Waiting for the delivery of JO Materials | 1
[9 empty] | b) | Roque | b) | 2019-05-22 | f) | - | b) | 500000 | b) | - | d) | -10.5% | b) | 110 |  | 1
[9 empty] | c) | Admin | c) | 2019-07-31 | g) | - | c) | - | [7 empty] | 1
[9 empty] | d) | 70 CD | d) | - | [11 empty] | 1
|  |  | 1.5 | Agricultural Productivity Support Project- |  | - |  | - | a) | 1500000 | a) | - | e) | - | a) | 1500000 | a) | - | c) | - | a) | - | For bidding | 2
|  |  |  | Fishing Equipment, Tambo, IGACOS |  |  |  |  | b) | - | b) | - | f) | - | b) | 1500000 | b) | - | d) | - | b) | - |  | 2
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| K. | 20% Development Fund CY 2018 | [21 empty] | AC
|  |  | 1. Various of Water System (Provincewide) |  |  | Water System | sq.m | Admin/Contract | a) | 10000000 | [12 empty] | Investigation/Inspection of priority projects | AC
[9 empty] | b) | Foronda/Misa | [13 empty] | AC
[9 empty] | c) | PEO | [13 empty] | AC
[9 empty] | d) | - | [13 empty] | FS
|  |  | 1.1 Conduct of geo-resistivty/drillig test of proposed site |  |  | geo-resistivty/drillig | Ft. | Admin | a) | 250000 | [12 empty] | See list of projects | AC
[9 empty] | b) | Diosanta | [13 empty] | AC
[9 empty] | c) | PEO | [13 empty] | 1
[9 empty] | d) | - | [13 empty] | 1
|  |  |  | Const. of PWS Linao, San Isidro |  | geo-resistivty/drillig | Ft. | Admin | a) | 62000 | a) |  | e) |  | a) | 62000 | a) |  | a) |  | a) |  | For implementation | 1
|  |  | a. | [5 empty] | b) | - | b) | - | f) | - | b) | 62000 | b) | - | d) | - | b) | - |  | 1
[9 empty] | c) | PEO | c) | - | g) | - | c) | - | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  |  | Const. of PWS Mamalian, San Isidro |  | geo-resistivty/drillig | Ft. | Admin | a) | 62000 | a) | - | e) | - | a) | 62000 | a) | - | c) | - | a) | - | For declaration of savings because the spring water source is not feasible for development. | 1
|  |  | b. | [5 empty] | b) | - | b) | - | f) | - | b) | 62000 | b) | - | d) | - | b) | - |  | 1
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  |  | Const. of PWS Sagayen, San Isidro |  | geo-resistivty/drillig | Ft. | Admin | a) | 62000 | a) | - | e) | - | a) | 62000 | a) | - | c) | - | a) | - | For implementation | 1
|  |  | c. | [5 empty] | b) | - | b) | - | f) | - | b) | 62000 | b) | - | d) | - | b) | - |  | 1
[9 empty] | c) | PEO | c) | - | g) | - | c) | - | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | 2. Construction of Water System Projects in Component LGUs |  |  | Water System | sq.m | Admin/Contract | a) | 9750000 | [12 empty] | See list of projects | 1
[9 empty] | b) | Diosanta | [13 empty] | 1
[9 empty] | c) | PEO | [13 empty] | ?
[9 empty] | d) | - | [13 empty] | 1
|  |  |  | Installation of potable water System at Purok Nangka, Pandapan, Tagum City |  | Water System | Households | Admin | a) | 1125000 | a) | - | e) | - | a) | 1125000 | a) | - | c) | - | a) | - | Waiting for deed of donation. Follow-up letter was already issued | 1
|  |  | 2.1 | [5 empty] | b) | - | b) | - | f) | - | b) | 1125000 | b) | - | d) | - | b) | - |  | 1
[9 empty] | c) | PEO | c) | - | g) | - | c) | - | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  |  | Rehab./Impv't. of San Vicente Water System, Asuncion |  | Water System | Households | Admin | a) | 1125000 | a) | 2018-10-26 | e) | - | a) | 1125000 | a) | - | c) | - | a) | - | Abstract # 0220190484 still draft | 1
|  |  | 2.2 | [5 empty] | b) | - | b) | - | f) | - | b) | 1125000 | b) | - | d) | - | b) | - |  | 1
[9 empty] | c) | PEO | c) | - | g) | - | c) | - | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  |  | Water System at brgy. Malativas, Panabo City |  | Water System | Households | Admin | a) | 1250000 | a) | - | e) | - | a) | 1250000 | a) | - | c) | - | a) | - | For preparation of POW & Plan c/o PDPM - POSSIBLE TRANSFER OF SITE SUBJECT FOR TRANSFER OF LOCATION . NO DEED OF DONATION | 1
|  |  | 2.3 | [5 empty] | b) | - | b) | - | f) | - | b) | 1250000 | b) | - | d) | - | b) | - |  | 1
[9 empty] | c) | Admin | c) | - | g) | - | c) | - | [7 empty] | 1
[9 empty] | d) | - | d) | -
|  |  |  | Const. of Potable Water System at Brgy. Tibungol, Panabo City |  | Water System | Households | Admin | a) | 1250000 | a) | 2018-11-21 | e) | - | a) | 1250000 | a) | 2.13% | c) | 0.76% | a) | 3 | Suspended dated February 19, 2020 undelivered hardware materials (Supplier refused to deliver. Letter already submitted to BAC.) | 1
|  |  | 2.4 | [5 empty] | b) | Andoy | b) | 2020-01-20 | f) | - | b) | 1250000 | b) | - | d) | -1.37% | b) | 15 |  | 1
[9 empty] | c) | Admin | c) | 2020-04-15 | g) | - | c) | - | [7 empty] | 1
[9 empty] | d) | 76 C.D | d) | - | [11 empty] | 1
|  |  |  | Potable Water System at Brgy. San Remegio Kaputian (Level II WS), Samal |  | Water System | Households | Admin | a) | 3625000 | a) | 2018-10-25 | e) | - | a) | 3625000 | a) | 100% | c) | 74.56% | a) | 4 | On-going | 1
|  |  | 2.5 | [5 empty] | b) | Diosanta | b) | 2019-07-16 | f) | 89 CD | b) | 3625000 | b) | 72.04% | d) | 2.52% | b) | 88 |  | 1
[9 empty] | c) | Admin | c) | 2020-02-01 | g) | - | c) | 2702800 | [7 empty] | AC
[9 empty] | d) | 200 C.D | d) | 2020-04-30 | [11 empty] | 1
|  |  | 3. Counterpart to Special Projects (Provincewide) |  |  | Road | km. | Contract | a) | 67415000 | [12 empty] | Investigation/Inspection of priority projects | 1
[9 empty] | b) | Foronda | [13 empty] | 1
[9 empty] | c) | PEO | [13 empty] | 1
[9 empty] | d) | -
|  |  | 3.1 | Rehab. Of Sonlon-Camansa FMR, Asuncion, Davao del Norte (PRDP Counterpart : 193,612,514.23) |  | Road | 10.230 km | Contract | a) | 21,512,501.5 | a) | 2018-09-18 | e) |  | a) | 21,512,501.5 | a) | 39.51% | c) | 31.6% | a) | 30 | On-going
[9 empty] | b) | Fabiala | b) | 2019-05-28 | f) | - | b) | 21,512,501.5 | b) | - | d) | -7.91% | b) | 690
[9 empty] | c) | Three w/Builders, Inc/Davao Rock Mixer Enterprises (JV) | c) | 2020-12-31 | g) | - | c) | 4,502,566.58
[9 empty] | d) | 384 CD | d) | -
|  |  |  | Impvt. of Km. 9 Sagayen - Sawata Provincial Road Phase II |  | Road | 1.303 km. | Admin | a.) 7,742,775.95 |  | a) | 2019-01-31 |  |  | a) | 7427725.95 | a) | 45% | c) | 35.05% | a) | 6 | Suspended dated March 6, 2020 due to delay delivery of materials
|  |  | 3.2 | [5 empty] | b.) Kenny |  | b) | 2019-09-09 |  |  | b) | 7427725.95 | b) | - | d) | - | b) | 138 |  | 1
[9 empty] | c) | PEO | c) | 2020-03-27 |  |  | c) | 2603417.9455 | [7 empty] | 1
[9 empty] | d) | 200 CD | d) | - | [11 empty] | 1
|  |  | 4. Const./Rehab./Comp. of Various Gov't. Bldgs.Struct., Fac. (Provincewide) |  |  | Bldgs. | sq. | Admin/Contract | a) | 13523124 | [12 empty] | Investigation/Inspection of priority projects | 1
[9 empty] | b) | Foronda | [13 empty] | 1
[9 empty] | c) | PEO | [13 empty] | AC
[9 empty] | d) | - | [13 empty] | 1
|  |  | 4.1 | Rehab. Of PEO Training Center, (PDPM),Mankilam, Tagum City (Part of P803,000.00)(20% DF CY 2017-P476,876.00) |  | Bldg. | 85 sq. m | Admin | a) | 476876 | a) | 2019-02-12 | e) | - | a) | 476876 | a) | 100% | c) | 99% | a) | 3 | suspended due to additional materials for electrical works | 1
[9 empty] | b) | Chua | b) | 2019-11-04 | f) | 57 CD | b) | 476876 | b) | - | d) | -1% | b) | 57 |  | 1
[9 empty] | c) | PEO | c) | 2019-01-17 | g) | - | c) | 472107.24 | [7 empty] | 1
[9 empty] | d) | 50 WD | d) | 2020-03-15
|  |  | 4.2 | Construction of IP Tribal Council of Women at Brgy. Camansa, Asuncion |  | Bldg. | sq. m | Admin | a) | 560,000.00 | a) | - | e) | - | a) | 560,000.00 | a) | - | c) | - | a) | - | Purchase Request # 20032714 | 1
[9 empty] | b) | - | b) | - | f) | - | b) | 560,000.00 | b) | - | d) | - | b) | - |  | 1
[9 empty] | c) | PEO | c) | - | g) | - | c) | - | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | 5. Rural Electrification (Provincewide) |  |  | Elect. | Households | Contract | a) | 5000000 | [12 empty] | Investigation/Inspection of priority projects | 1
[9 empty] | b) | Kim Pao Lu | [13 empty] | 1
[9 empty] | c) | PEO | [13 empty] | 1
[9 empty] | d) | - | [13 empty] | 1
|  |  | 5.1 | Rural Electrification at Del Monte, New Corella |  | Elect. | Households | Contract | a) | 1000000 | a) | - | e) | - | a) | 1000000 | a) | - | c) | - | a) | - | Purchase Request #2001259 (On process ) | 1
[9 empty] | b) | - | b) | - | f) | - | b) | 1000000 | b) | - | d) | - | b) | - |  | 1
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | 5.2 | Const. of Distribution Line in Sitio Prk. 1,3,4, 11 and 7, Camansa, Asuncion |  | Elect. | Households | Contract | a) | 4000000 | a) | - | e) | - | a) | 4000000 | a) | - | c) | - | a) | - | Purchase Request # 19093670 (On process ) | 1
[9 empty] | b) | - | b) | - | f) | - | b) | 4000000 | b) | - | d) | - | b) | - |  | 1
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | AC
[9 empty] | d) | - | d) | - | [11 empty] | 1
| L. | GENERAL FUND PROPER CY 2018 | [21 empty] | 1
|  |  | STIMULUS PROJECTS | [20 empty] | 1
|  |  | ASUNCION | [20 empty] | 1
|  |  | 1 | Const. of Potable water System at Prk. 6, New Santiago, Asuncion |  | Water System | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Amended in AIP 3rd revision CY 2019 increasing the amount to complete the project For plan preparation c/o Amamio | 1
[9 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | AC
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | AC
[9 empty] | d) | - | d) | - | [11 empty] | AC
|  |  | TAGUM CITY | [20 empty] | AC
|  |  | 2 | Completion of GYM Bleacher w/ Electrification, Pagsabangan, Tagum City |  | Bleacher | km | MLGU | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For implementation but the project was implemented by the brgy. Waiting for resolution to change priority Alloted March 12, 2019
[9 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 1 | 1
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | 3 | Construction of Drainage Canal, Libuganon, Tagum City |  | Drainage | ln.m | Admin | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For implementation | 1
[9 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 1
[9 empty] | c) | PEO | c) | - | g) | - | c) | - | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | KAPALONG | [20 empty] | 1
|  |  | 4 | Construction of Bleacher, Mamacao, Kapalong |  | Bleacher | sq.m | Admin | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | 62.51% | c) | 62.51% | a) | 7 | On-going | 1 | Const. of MP Hall, Rizal ES, Binancian, Asuncion
[9 empty] | b) | Ambrosio | b) | 2020-02-05 | f) | - | b) | 500000 | b) | - | d) | - | b) | 75 |  | AC
[9 empty] | c) | PEO | c) | 2020-04-19 | g) | - | c) | - | [7 empty] | AC
[9 empty] | d) | 75 CD | d) | - | [11 empty] | 1
|  |  | 5 | Construction of Concrete Perimeter Fence, Luna, Kapalaong |  | Fence | sq.m | Contract | a) | 500000 | a) | 2019-06-28 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For implementation | AC
[9 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 1
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | 6 | Completion of Brgy. Health Center, Maniki, Kapalong |  | Bldg. | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For amendment.To submit a new resolution for another priority project which is the Const. of Multi-Purpose Pavement but the propose site is not is donated because the previous project Completion of Brgy. Health Center was funded by the LGU of Kapalong | 1
[9 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 1
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | TALAINGOD | [20 empty] | 1
|  |  | 7 | Grouted Riprap on Embankment |  | Riprap | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Plan and POW on process c/o PDPM | FS
|  |  |  | Sto. Ñino, Talaingod |  |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | AC
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | AC
[9 empty] | d) | - | d) | -
|  |  | 8 | Barangay Hall Improvement, Dagohoy, |  | Bldg. | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For amendment to Construction of Retaining Wall as per recommendation by Engr. Misa during site re-evaluation. Plan & POW completed.Resolution from the Brgy. Council to support the amendment c/o Engr. Canillada
|  |  |  | Talaingod |  |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | -
[9 empty] | c) | - | c) | - | g) | - | c) | -
[9 empty] | d) | - | d) | -
|  |  |  | Construction of 2 Classroom Building Datu Jose Libayao NHS Ext, Natulian, Palma Gil, Talaingod |  | Bldg. | - | - | a) | 2000000 | a) | - | e) | - | a) |  | a) | - | c) | - | a) | - | Post Qualification on process | FS
|  |  | 9 | [5 empty] | b) | - | b) | - | f) | - | b) |  | b) | - | d) | - | b) | - |  | AC
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | CARMEN | [19 empty] | Plan and POW Approval on process | 1
|  |  | 10 | Completion of Evacuation Center Building, |  | Bldg. |  | Contract | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - |  | 1
|  |  |  | San Isidro, Carmen |  |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 1
[9 empty] | c) | Contract | c) | - | g) | - | c) | - | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | PANABO CITY | [19 empty] | Purchase Order # 2020010028 (RLHV Design & Build) | 1
|  |  | 11 | Const. of Perimeter Fence of Day Care Center 1 |  | Bldg. |  | Contract | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - |  | FS
|  |  |  | Nanyo, Panabo City |  |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | AC
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | 12 | Impv't. of Brgy. Road Covered Court, Malativas, Panabo City |  | Court | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Alloted - May 29, 2019, Additional Funding of 500,000.00,SB no. 4 CY 2019 | 1
[9 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 1
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | AC
|  |  | 13 | Rehab. Of Multi-Purpose Gym & Facililies Maduao, Panabo City |  | Gym | sq.m | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Purchase Request # 20032056 | 1
[9 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 1
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | 14 | Const. of Multi-Purpose Bldg. Sto. Nino, Panabo City |  | Bldg. | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Plan and POW on process c/o PDPM | 1
[9 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 1
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | 15 | Completion of Canopy at DAPCO Covered Court, Dapco, Panabo City |  | Court | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Purchase Request on process | AC
[9 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 1
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | 16 | Perimeter Fence of Day Care Center I & II, Nanyo, Panabo City |  | Bldg. | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For inspection by PDPM for PLAN and POW as of 7/19/2019 | 1
[9 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 1
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | IGCS | [20 empty] | 1
|  |  | 17 | Impv't. of Brgy. Water System, Pichon, IGCS |  | Water |  | Admin | a) | 500000 | a) | 2018-05-31 | e) | - | a) | 500000 | a) | 100% | c) | 83.5% | a) | 5 | On-going/ Time extension on process | 1
|  |  |  | (Construction of Elevated Tank) |  | System |  |  | b) | Andoy | b) | 2020-01-13 | f) | - | b) | 500000 | b) | - | d) | -16.5% | b) | 110 |  | AC
[9 empty] | c) | Admin | c) | 2020-03-13 | g) | - | c) | 423575.63 | [7 empty] | 1
[9 empty] | d) | 80 | d) | - | [11 empty] | 1
|  |  | 18 | Powerline Expansion Project, Cogon, IGACOS |  | Water |  | Contract | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Waiting for NTP | 1
[6 empty] | System |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | AC
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | 19 | Water System From Prk. 6 - Prk. 2 - Prk. 5A, |  | Water |  | Admin | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For Implementation | 1
|  |  |  | Tagbay, IGCS |  | System |  |  | b) | Pacquiao | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 1
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | 20 | Powerline Expansion Project, Tambo, IGCS |  | Elect. |  | Contract | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Purchase Request # 19083312 | 1
[9 empty] | b) | Porras | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 1
[9 empty] | c) | Admin | c) | - | g) | - | c) | - | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | 21 | Improvement of Barangay Hall, |  | Bldg. |  | Admin | a) | 500000 | a) |  | e) | - | a) | 500000 | a) | - | c) | - | a) | - | By Contract and change to admin due to unforeseen activities because it’s a repair (For revision of POW) | 1
|  |  |  | Penaplata, IGCS |  |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 1
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | AC
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | 22 | Electrification of Sitio Baongon-Diamond- |  | Elect. |  | - | a) | 500000 | a) |  | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Purchase Order # 20200100002 (3E Electrical Sales & Services) | 1
|  |  |  | Mansanitas, Dadatan, IGCS |  |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 1
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | 23 | Drilling of Water System, |  | Water |  | - | a) | 500000 | a) |  | e) | - | a) | 500000 | a) | - | c) | - | a) | - | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | 1
|  |  |  | Linusotan, IGCS |  | System |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 1
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | FS
| M. | SUPPLEMENTAL BUDGET # 1 CY 2018 | [21 empty] | 1
|  | M. | Const. in Progress - Infrastructure Assets (Rehabilitation of Various Provincial Roads) |  |  | road | km | Admin | a) | 6,000,000.00 | [12 empty] | See list of Provincial Roads | 1
|  | 1 | [6 empty] | b) | Paraguya | [13 empty] | 1
[9 empty] | c) | PEO | [13 empty] | 1
[9 empty] | d) | - | [13 empty] | 1
|  |  |  | Mesaoy - Jct. Mahayahay |  | road | km | Admin | a) | 1,534,000.00 | a) | 2018-07-19 | e) | - | a) | 1,534,000.00 | a) | 60% | c) | 60% | a) | - | Suspended as of Dec. 27, 2018 (For clarification regarding the cancellation of PO # 2018082439)
|  |  | 1.1 | [5 empty] | b) | Paraguya | b) | 2018-11-16 | f) | - | b) | 1,534,000.00 | b) | - | d) | - | b) | -
[9 empty] | c) | PEO | c) | 2018-12-15 | g) | - | c) | 920400
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | Const./Compl./Impv't. of Various Gov't. Bldgs., Structures & Facilities (Const. in Progress - Bldgs. & Other Structures | [20 empty] | 1
|  | 2 | [21 empty] | 1
1
|  |  |  | Const. of DDN Hospital Carmen Zone Annex Bldg. |  | Bldg. | sq.m | Admin | a) | 5,500,000.00 | a) | - | e) | - | a) | 5,500,000.00 | a) | - | c) | - | a) | - | Winning Bidder - Digos Constrak Corp. | 1
|  |  | 2.1 | [5 empty] | b) | Estorco | b) | - | f) | - | b) | 5,500,000.00 | b) | - | d) | - | b) | - |  | 1
[9 empty] | c) | PEO | c) | - | g) | - | c) | - | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
| N. | SUPPLEMENTAL BUDGET # 2 CY 2018 | [21 empty] | 1
|  |  | 1 Const./Compl./Impv't. of Various Gov't. Bldgs., Structures & Facilities (Const. in Progress - Bldgs. & Other Structures | [20 empty] | 1
1
1
|  |  |  | Const./Impv't. of DDN Hospital Kapalong Zone |  | Bldg. | sq.m | Contract | a) | 5,000,000.00 | a) | 2018-09-04 | e) | - | a) | 5,000,000.00 | a) | 88.30% | c) | 90.47% | a) | 6 | On-going | 1
|  |  | 1.1 | [5 empty] | b) | Ambrosio | b) | 2019-11-02 | f) | - | b) | 5,000,000.00 | b) | - | d) | +2.17% | b) | 150 |  | 1
[9 empty] | c) | MAG CORP. | c) | 2020-04-30 | g) | - | c) | 4523500 | [7 empty] | 1
[9 empty] | d) | 220 CD | d) | - | [11 empty] | 1
|  |  |  | Compl. Of Bahay Pag-Asa for Minors, New Corella |  | Bldg. | sq.m | Admin | a) | 3,450,000.00 | a) | - | e) | - | a) | 3,450,000.00 | a) | - | c) | - | a) | - | For implementation | 1
|  |  | 1.2 | [5 empty] | b) | - | b) | - | f) | - | b) | 3,450,000.00 | b) | - | d) | - | b) | - |  | 1
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  |  | Const. of Add'l. 2nd Level Multi-Purpose HalI, PGSO warehouse,Bldg., Mankilam |  | Bldg. | sq.m | Contract | a) | 7,592,588.00 | a) | - | e) | - | a) | 7,592,588.00 | a) | - | c) | - | a) | - | PO # 2020020808 (F2 Construction) | 1
|  |  | 1.3 | [5 empty] | b) | - | b) | - | f) | - | b) | 7,592,588.00 | b) | - | d) | - | b) | - |  | 1
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
| O. | SUPPLEMENTAL BUDGET # 5 CY 2018 | [21 empty] | 1 | 4
|  |  | STIMULUS CY 2018 | [20 empty] | 1 | 4
|  |  |  | Rehab./Impv't. of MP Bldg. (Gym), Napungas, Asuncion |  | GYM | sq.m | - | a) | 500000 | a) | 2019-02-04 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | PR # 20010252 | 1 | 4
|  |  | 1 | [5 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 1 | 4
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 1 | 4
[9 empty] | d) | - | d) | - | [11 empty] | 1 | 4
| P. | SPECIAL EDUCATION FUND (SEF) | [21 empty] | 1 | 4
|  |  | ANNUAL BUDGET CY 2018 | [20 empty] | 1 | 4
|  |  |  | Division School Improvement (Davao del Norte DEPED Training Center), Tagum City |  | Bldg. | sq.m | Admin | a) | 1250000 | a) | 2019-02-04 | e) | - | a) | 1250000 | a) | 69.01% | c) | 55.37% | a) | 16 | On-going | 1 | 4
|  |  | 1 | [5 empty] | b) | Japay/Quirant | b) | 2019-11-26 | f) | - | b) | 1250000 | b) | - | d) | -13.64% | b) | 320 |  | 1 | 4
[9 empty] | c) | Admin | c) | 2020-05-03 | g) | - | c) | 692125 | [7 empty] | 1 | 4
[9 empty] | d) | 160 CD | d) | - | [11 empty] | 1 | 4
| Q. | OPPAP-PAMANA | [21 empty] | 1
|  |  | 1. PROCESSING AND BAGSAKAN CENTER | [20 empty] | 1
|  |  |  | Const. of Processing and Bagsakan Center, Brgy. Dagohoy, Talaingod |  | Bldg. | sq.m | Contract | a) | 2500000 | a) | 2019-11-25 | e) | - | a) | 2500000 | a) | 55.61% | c) | 68.72% | a) | 8 | On going. | 1
|  |  | 1.1 | [5 empty] | b) | Dadula | b) | 2019-11-25 | f) | - | b) | 2500000 | b) | - | d) | +13.11% | b) | 200 |  | 1
[9 empty] | c) | RLHV | c) | 2020-04-10 | g) | - | c) | 375000 | [8 empty] | 4
[9 empty] | d) | 145 CD | d) | - | [11 empty] | AC
|  |  | 2. SOLAR DRYER | [20 empty] | AC
|  |  |  | Post Harvest Facilities (Corn Mill, Solar Dryer, Corn Sheller), Kapalong, Davao del Norte |  | Bldg. | sq.m | Contract | a) | 1500000 | a) | 2019-11-18 | e) | - | a) | 1500000 | a) | 90.94% | c) | 90.94% | a) | 7 | On-going. | AC
|  |  | 2.1 | [5 empty] | b) | Ambrosio | b) | 2019-11-18 | f) | - | b) | 1500000 | b) | - | d) | - | b) | 175 |  | 1
[9 empty] | c) | PEO | c) | 2020-02-26 | g) | - | c) | 1114654.45 | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | 4. WATER SYSTEM | [20 empty] | 1
|  |  |  | Construction of PWS Level II in Purok 7-A and 7-B, Capungagan, Kapalong |  | PWS | Households | Admin | a) | 1760000 | a) | 2019-11-25 | e) | - | a) | 1760000 | a) | 100% | c) | 70.19% | a) | 5 | On-going | 1
|  |  | 4.1 | [5 empty] | b) | Kabinge | b) | 2019-11-25 | f) | 44 CD | b) | 1760000 | b) | 93.05% | d) | -22.86% | b) | 125 |  | 1
[9 empty] | c) | PEO | c) | 2020-03-20 | g) | - | c) | 1235344 | [7 empty] | 1
[9 empty] | d) | 116 CD | d) | 2020-04-19 | [11 empty] | 1
|  |  |  | Construction of PWS Level II in Purok 2, Pag-Asa, kapalong |  | PWS | Households | Admin | a) | 2310000 | a) | 2019-11-25 | e) | - | a) | 2310000 | a) | 78.00% | c) | 49.086% | a) | 9 | On-going | 1
|  |  | 4.2 | [5 empty] | b) | Dadula | b) | 2019-12-16 | f) | 45 CD | b) | 2310000 | b) | - | d) | -28.91% | b) | 138 |  | 1
[9 empty] | c) | PEO | c) | 2020-04-14 | g) | - | c) | 1133886.6 | [7 empty] | 1
[9 empty] | d) | 115 CD | d) | - | [11 empty] | 1
|  |  | 5. CATTLE PRODUCTION | [20 empty] | 1
|  |  |  | Cattle Production- Brgy. Tiburcia, Gupitan and Semong, Kapalong |  | Bldg. | - | - | a) | 1500000 | a) | - | e) | - | a) | 1500000 | a) | - | c) | - | a) | - | For cancellation. A letter was sent to OPAPP last Dec 2018 requesting to allow us to reduce the number of cattle but we are still hoping that there would be a supplier will bid | 1
|  |  | 5.1 | [5 empty] | b) | - | b) | - | f) | - | b) | 1500000 | b) | - | d) | - | b) | - |  | 1
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  |  | Cattle Production, Brgy. Palma Gil, Brgy. Sto. Nino, Brgy. Dagohoy, Talaingod, Davao del Norte |  | Bldg. | - | - | a) | 1500000 | a) | - | e) | - | a) | 1500000 | a) | - | c) | - | a) | - | For cancellation. A letter was sent to OPAPP last Dec 2018 requesting to allow us to reduce the number of cattle but we are still hoping that there would be a supplier will bid | 2
|  | c | 5.2 | [5 empty] | b) | - | b) | - | f) | - | b) | 1500000 | b) | - | d) | - | b) | - |  | AC
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | AC
[9 empty] | d) | - | d) | - | [11 empty] | AC
|  |  | 6. RICE MILL FOR UPLAND RICE | [20 empty] | 1
|  |  |  | Rice Mill for Upland Rice, Palma Gil, Talaingod |  | Rice Mill | sq.m | Admin | a) | 1000000 | a) | - | e) | - | a) | 1000000 | a) | - | c) | - | a) | - | For implementation | 1
|  |  | 6.1 | [5 empty] | b) | - | b) | - | f) | - | b) | 1000000 | b) | - | d) | - | b) | - |  | 1
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
| R. | QUICK RESPOND FUND CY 2016 | [21 empty] | 1
|  |  | 1 | Rehab. Of Slope Protection of Libuganon River Along Kapalong - Mabantao - Florida Prov'l. Road Phase I |  | Road | km | - | a) | 900000 | a) | - | e) | - | a) | 900000 | a) | - | c) | - | a) | - | For AIP Amendment | 1
[9 empty] | b) | - | b) | - | f) | - | b) | 900000 | b) | - | d) | - | b) | -
[9 empty] | c) | - | c) | - | g) | - | c) | -
[9 empty] | d) | - | d) | - | [11 empty] | 1
| S. | 20% DEVELOPMENT FUND CY 2019 | [21 empty] | 1
| Road ID |  | 1. Repair/Maintenance of Provincial Roads & Bridges 1 |  |  | Road Maintenance | 109.55 km | MBA | a) | 41465029 | a) | 2019-01-03 | [10 empty] | See list of Provincial Roads | 1
[9 empty] | b) | Paraguya | b) | 2019-01-03 | [11 empty] | 1
| 11DAN | [7 empty] | c) | PEO | c) | 2019-12-31 | [11 empty] | 1
[9 empty] | d) | 261 days | d) | - | [11 empty] | 1
|  |  | Jct. Highway Canatan - Doña Andrea |  |  | Road Rehabilitation | 4.34 | Admin | a) | 2000000 | a) | 2019-06-12 | e) | - | a) | 2000000 | a) | - | c) | - | a) | - | For implementation | 1
| 007 | [7 empty] | b) | Gone | b) | - | f) | - | b) | 2000000 | b) | - | d) | - | b) | - |  | 1
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | Pamacaun - Lasang Banate |  |  | Road Rehabilitation | 4.34 | Admin | a) | 2000000 | a) | 2019-06-27 | e) | - | a) | 2000000 | a) | - | c) | - | a) | - | For implementation | 1
| 015 | [7 empty] | b) | Gone | b) | - | f) | - | b) | 2000000 | b) | - | d) | - | b) | - | Waiting for the delivery of geo-grid | 1
[9 empty] | c) | - | c) | - | g) | - | c) | - | [6 empty] | materials. An approved request letter
[9 empty] | d) | - | d) | - | [10 empty] | dated Dec. 3, 2019 for the extension of 50 days from Provincial Administrator Engr. Rabanoz is on file | 1
|  |  | Sto. Niño - Palma Gil - Sitio Opao |  |  | Road Rehabilitation | 11.6 | Admin | a) | 1901000 | a) | 2019-06-19 | e) | - | a) | 1901000 | a) | - | c) | - | a) | - | NTP not yet serve to Tagum Construct because they have not yet complied with the construction safety requirement | 1
| 019 | [7 empty] | b) | Lumapat | b) | - | f) | - | b) | 1901000 | b) | - | d) | - | b) | - |  | 1
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | Sto. Niño - Daligdigon - Paiton |  |  | Road Rehabilitation | 11.6 | Admin | a) | 3000000 | a) | 2019-10-03 | e) | - | a) | 3000000 | a) | 2.19% | c) | 3.98% | a) | - | On-going | 1
| 023 | [7 empty] | b) | Lumapat | b) | 2020-01-16 | f) | - | b) | 3000000 | b) | - | d) | +1.79% | b) | - |  | 1
[9 empty] | c) | - | c) | 2020-05-14 | g) | - | c) | 119400 | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | Jct. Paiton - Mibolo |  |  | Road Rehabilitation | 23.9 | Admin | a) | 6000000 | a) | 2019-03-25 | e) | - | a) | 6000000 | a) | 21.05% | c) | 21.05% | a) | - | Temporary suspended because the materials for the box culvert procurement on process wth PO # 2019061674 | 1
| 024 | [7 empty] | b) | Lumapat | b) | Aug.1, 2019 | f) | - | b) | 6000000 | b) | - | d) | 0% | b) | - |  | 1
[9 empty] | c) | PEO | c) | 2020-03-15 | g) | - | c) | 1263000 | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | Monte Dujali - Gupitan |  |  | Road Rehabilitation | 4.58 | Admin | a) | 1200000 | a) | 2019-12-06 | e) | - | a) | 1200000 | a) | 40.45% | c) | 40.45% | a) | 8 | On-going | 1
| 037 | [7 empty] | b) | Bacaron | b) | 2020-01-31 | f) | - | b) | 1200000 | b) | - | d) | - | b) | 240 |  | 1
[9 empty] | c) | PEO | c) | 2020-03-31 | g) | - | c) | 485400 | [7 empty] | 1
[9 empty] | d) | 61 CD | d) | - | [11 empty] | 1
|  |  | New Corella - Saug |  |  | Road Rehabilitation | 12.52 | 63 sq.m | a) | 6500000 | a) | 2019-03-12 | e) | - | a) | 6500000 | a) | 80.5% | c) | 80.5% | a) | 19 | On-going (Resumption: February 3, 2020) | 1
| 048 | [7 empty] | b) | Pilotos | b) | 2019-03-26 | f) | - | b) | 6500000 | b) | - | d) | - | b) | 570 |  | 1
[9 empty] | c) | PEO | c) | 2019-12-31 | g) | - | c) | 5232500 | [7 empty] | 2
[9 empty] | d) | - | d) | 2020-04-23 | [11 empty] | AC
|  |  | Jct. Monte Carlo - Upper Cabaywa - Canatan |  |  | Road Rehabilitation | 4.61 | 63 sq.m | a) | 8838000 | a) | 2019-01-31 | e) | - | a) | 8838000 | a) | 89.5% | c) | 89.5% | a) | 19 | On -going 90% accomplished. The target date of completion was Dec. 31, 2019, for process time extension request | AC
| 050 | [7 empty] | b) | Garcia | b) | 2019-03-26 | f) | - | b) | 8838000 | b) | - | d) | 0% | b) | 570 |  | AC
[9 empty] | c) | PEO | c) | 2019-12-31 | g) | - | c) | 7910010 | [7 empty] | AC
[9 empty] | d) | - | d) | - | [11 empty] | 1
[8 empty] | Admin | a) | 46740177 | [12 empty] | See list of Provincial Roads | 1
| Road ID |  | Maintenance of Various Provincial Roads and Bridges at District 2 |  |  | Road Maintenance | 115.620 km |  | b) | Paraguya | [13 empty] | 1
[9 empty] | c) | PEO | [13 empty] | 1
| 11DAN | [22 empty] | 1
[9 empty] | d) | 261 days | [13 empty] | 1
|  |  | Jct. Highway Sto. Niño - Cebulano |  |  | Road Rehabilitation | 2.09 | MBA | a) | 1045000 | a) | 2019-01-03 | e) | 120 CD | a) | 1045000 | a) | 80% | c) | 80% | a) | 6 |  | 1
| 072 | [7 empty] | b) | Obar/ Nasol | b) | 2019-05-21 | f) |  | b) | 1045000 | b) | - | d) | - | b) | 132 | On-going
[9 empty] | c) | PEO | c) | 2019-10-04 | g) | - | c) | - | [6 empty] | Time extension on-process | AC
[9 empty] | d) | - | d) | 2020-02-21 | [11 empty] | 1
|  |  | Basa - Tubod |  |  | Road Rehabilitation | 1.56 | MBA | a) | 1000000 | a) | 2019-01-03 | e) | - | a) | 1000000 | a) | 100% | c) | 1.675% | a) | 3 | On-going | 1
| 076 | [7 empty] | b) | PIAD | b) | 2019-11-11 | f) | - | b) | 1000000 | b) | 51.68% | d) | -50.01% | b) | 30 |  | 1
[9 empty] | c) | Admin | c) | 2020-03-19 | g) | - | c) | [8 empty] | 1
[9 empty] | d) | 120 | d) | - | [11 empty] | 1
|  |  | Tubod - Pilar |  |  | Road Rehabilitation | 1.55 | MBA | a) | 16000000 | a) | 2019-11-26 | e) | - | a) | 16000000 | a) | 11.51% | c) | 14.52% | a) | 7 | On-going | 1
| 077 | [7 empty] | b) | Agang | b) | 2019-12-18 | f) | - | b) | 16000000 | b) | - | d) | 3.01% | b) | 210 |  | 1
[9 empty] | c) | Admin | c) | 2020-11-05 | g) | - | c) | 4046971.2 | [7 empty] | 1
[9 empty] | d) | 323 C.D | d) | - | [11 empty] | 1
|  |  | Sitio Malaga - Tibulao |  |  | Road Rehabilitation | 3.22 | MBA | a) | 1000000 | a) | 2019-01-03 | e) | - | a) | 1000000 | a) | 67.81% | c) | 24.5% | a) | 5 | On-going/ Lack of manpower | 1
| 103 | [7 empty] | b) | Obar | b) | 2019-11-11 | f) | - | b) | 1000000 | b) | - | d) | -43.31% | b) | 110
[9 empty] | c) | Admin | c) | 2020-02-09 | g) | - | c) | [8 empty] | AC
[9 empty] | d) | 90 | d) | - | [11 empty] | 1
|  |  | Dujali - Tanglaw |  |  | Road Rehabilitation | 3.6 | MBA | a) | 2075000 | a) | 2019-01-03 | e) | - | a) | 2075000 | a) | 2.89% | c) | 3.2% | a) | 4 | On-going | 1
| 104 | [7 empty] | b) | Balbastro | b) | 2019-12-28 | f) | - | b) | 2075000 | b) | - | d) | 0.31% | b) | - |  | 1
` | [8 empty] | c) | Admin | c) | 2020-04-16 | g) | - | c) | [8 empty] | 1
[9 empty] | d) | 110 | d) | -
|  |  | San Miguel - Libertad |  |  | Road Rehabilitation | 6.2 | MBA | a) | 1240000 | a) | 2019-01-03 | e) | - | a) | 1240000 | a) | 59.41% | c) | 59.41% | a) | 9 | On-going | AC
| 121 | [7 empty] | b) | Gamad | b) | 2019-06-17 | f) | 30 | b) | 1240000 | b) | - | d) | - | b) | 36 |  | 1
[9 empty] | c) | - | c) | 2019-10-31 | g) | - | c) | [8 empty] | 1
[9 empty] | d) | - | d) | 2020-02-29 | [11 empty] | 1
|  |  | Bacali - Casig-ang - Libertad |  |  | Road Rehabilitation | 4.7 | MBA | a) | 940000 | a) | 2019-06-07 | e) | - | a) | 940000 | a) | 62.1% | c) | 62% | a) | 9 | On-going | 1
| 123 | [7 empty] | b) | Gamad | b) | 2019-06-27 | f) | 35 | b) | 940000 | b) | - | d) | - | b) | 36 |  | 1
[9 empty] | c) | Admin | c) | 2019-09-15 | g) | - | c) | [8 empty] | 1
[9 empty] | d) | 80 C.D | d) | 2020-02-29 | [11 empty] | 1
|  |  | San Miguel - Moslog - Kinamayan |  |  | Road Rehabilitation | 2.9 | MBA | a) | 1000000 | a) | 2019-05-20 | e) | - | a) | 1000000 | a) | 100% | c) | 80% | a) | 6 | On-going | 1
| 125 | [7 empty] | b) | Gamad | b) | 2019-06-17 | f) | 29 | b) | 1000000 | b) | 73.59% | d) | 6.41% | b) | 30 |  | 1
[9 empty] | c) | - | c) | 2019-09-16 | g) | - | c) | [8 empty] | 1
[9 empty] | d) | - | d) | 2020-02-29 | [11 empty] | 1
|  |  | Mugas - Lanatad |  |  | Road Rehabilitation | 1.53 | MBA | a) | 500000 | a) | 2019-01-03 | e) | 90 | a) | 500000 | a) | 100% | c) | 57.06% | a) | 4 | Resume 11/11/2019 | 1
| 131 | [7 empty] | b) | Balbastro | b) | 2019-08-05 | f) | - | b) | 500000 | b) | - | d) |  | b) | 104 |  | 1
[9 empty] | c) | Admin | c) | 2019-10-06 | g) | - | c) | [8 empty] | 1
[9 empty] | d) | 60 C.D | d) | 2020-02-29 | [11 empty] | 1
|  |  | New Katipunan - Pantaron |  |  | Road Rehabilitation | 1.96 | MBA | a) | 395000 | a) | 2019-01-03 | e) | - | a) | 395000 | a) | 60% | c) | 60% | a) | 4 | On-going | 1
| 134 | [7 empty] | b) | Gamad/Clar | b) | 2019-12-27 | f) | - | b) | 395000 | b) | - | d) | - | b) | 24 | Waiting for approved time extension | 1
[9 empty] | c) | - | c) | 2020-02-25 | g) | - | c) | [8 empty] | 1
[9 empty] | d) | 60 | d) | - | [11 empty] | 1
|  |  | Fd. Rd. 2 - Sto. Tomas - Magwawa |  |  | Road Rehabilitation | 10.21 | MBA | a) | 3575000 | a) | 2019-01-03 | e) | - | a) | 3575000 | a) | 70% | c) | 60.22% | a) | 16 | On-going | 1
| 137 | [7 empty] | b) | Sanchez | b) | 2019-08-27 | f) | - | b) | 3575000 | b) | - | d) | -9.78% | b) | 112 |  | 1
[9 empty] | c) | Admin | c) | 2020-01-24 | g) | - | c) | [8 empty] | 1
[9 empty] | d) | 150 C.D | d) | - | [11 empty] | 1
|  |  | Jct. Highway - Tanglaw |  |  | Road Rehabilitation | 3.98 | MBA | a) | 1100000 | a) | 2019-05-16 | e) | - | a) | 1100000 | a) | 100% | c) | 85% | a) | 10 | On going | 1
| 142 | [7 empty] | b) | Gamad/Clar | b) | 2019-06-17 | f) | 29 CD | b) | 1100000 | b) | 73.59% | d) | 11.41% | b) | 50 |  | 1
[9 empty] | c) | PEO | c) | 2019-09-16 | g) | - | c) | [8 empty] | 1
[9 empty] | d) | - | d) | 2020-02-29 | [11 empty] | 1
|  |  | Bdry. Tagum - Crossing Kinamayan Sto. Tomas |  |  | Road Rehabilitation | 0.75 | MBA | a) | 3700000 | a) | 2019-01-03 | e) | - | a) | 3700000 | a) | 40% | c) | 40% | a) | 3 | On-going
| 146 | [7 empty] | b) | Gamad/Clar | b) | 2019-12-27 | f) | - | b) | 3700000 | b) | - | d) | - | b) | 66
[9 empty] | c) | - | c) | 2020-04-25 | g) | - | c) | [8 empty] | 1
[9 empty] | d) | 120 | d) | - | [11 empty] | 1
|  | Road Rehabilitation of Provincial Roads | [21 empty] | 1
|  |  | 1. Rehab.of Dujali - Balisong - Magupising Provincial Road |  |  | Road Rehabilitation | 19.16 | MBA | a) | 1280000 | a) |  | e) | - | a) | 1280000 | a) | 100% | c) | 39.41% | a) | 12 | On-going | 1
[9 empty] | b) | Mellomida | b) | 2019-12-02 | f) | - | b) | 1280000 | b) | 86.5% | d) | -47.09% | b) | 900 | Negative slippage due to delay approved P.o for hardware | 1
[9 empty] | c) | Admin | c) | 2019-01-15 | g) |  | c) | 14331.6 | [6 empty] | materials | 1
[9 empty] | d) | 45 CD | d) | - | [11 empty] | 1
|  |  | 2. Fr. Rd. 3 - San Jose |  |  | Road Rehabilitation | 4.55 | Admin | a) |  | a) |  | e) | - | a) |  | a) |  | c) |  | a) |  | POW on process | 1
[9 empty] | b) |  | b) |  | f) | - | b) |  | b) |  | d) |  | b) |  |  | 1
[9 empty] | c) |  | c) |  | g) |  | c) | [8 empty] | 1
[9 empty] | d) |  | d) | [12 empty] | 1
|  |  | 3. Lower Asuncion - Upper Asuncion |  |  | Road Rehabilitation | 1.02 | Admin | a) | 8000000 | a) |  | e) | - | a) |  | a) |  | c) |  | a) |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | 1
[9 empty] | b) |  | b) |  | f) | - | b) |  | b) |  | d) |  | b) |  |  | 1
[9 empty] | c) |  | c) |  | g) |  | c) | [8 empty] | 1
[9 empty] | d) |  | d) | [12 empty] | 1
|  |  | 4. Jct. Highway - Carmen - Mangalcal - Tubod |  |  | Road Rehabilitation | 11.34 | Admin | a) |  | a) |  | e) | - | a) |  | a) |  | c) |  | a) |  | POW on process | 1
[9 empty] | b) |  | b) |  | f) | - | b) |  | b) |  | d) |  | b) |  |  | 1
[9 empty] | c) |  | c) |  | g) |  | c) | [8 empty] | 1
[9 empty] | d) |  | d) | [12 empty] | 1
|  |  | 5. Tuganay - Taba |  |  | Road Rehabilitation | 4.27 | Admin | a) |  | a) |  | e) | - | a) |  | a) |  | c) |  | a) |  | POW on process | 1
[9 empty] | b) |  | b) |  | f) | - | b) |  | b) |  | d) |  | b) |  |  | AC
[9 empty] | c) |  | c) |  | g) |  | c) | [8 empty] | 1
[9 empty] | d) |  | d) | [12 empty] | 1
|  |  | 6. Jct. Highway - Ising - Magsaysay |  |  | Road Rehabilitation | 10.84 | Admin | a) | 6000000 | a) |  | e) | - | a) |  | a) |  | c) |  | a) |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | 1
[9 empty] | b) |  | b) |  | f) | - | b) |  | b) |  | d) |  | b) |  |  | 1
[9 empty] | c) |  | c) |  | g) |  | c) | [8 empty] | 1
[9 empty] | d) |  | d) | [12 empty] | 1
|  |  | 7. Jct. Highway - Guadalupe - Bdry. Tagum |  |  | Road Rehabilitation | 7.9 | Admin | a) |  | a) |  | e) | - | a) |  | a) |  | c) |  | a) |  | POW on process | 1
[9 empty] | b) |  | b) |  | f) | - | b) |  | b) |  | d) |  | b) |  |  | 1
[9 empty] | c) |  | c) |  | g) |  | c) | [8 empty] | 1
[9 empty] | d) |  | d) | [12 empty] | 1
|  |  | 8. Sitio Malaga - Tibulao |  |  | Road Rehabilitation | 3.22 | Admin | a) |  | a) |  | e) | - | a) |  | a) |  | c) |  | a) |  | POW on process | 1
[9 empty] | b) |  | b) |  | f) | - | b) |  | b) |  | d) |  | b) |  |  | 2
[9 empty] | c) |  | c) |  | g) |  | c) | [8 empty] | AC
[9 empty] | d) |  | d) | [12 empty] | AC
|  |  | 9. Prk. 5 RJS - Prk 6 New Casay |  |  | Road Rehabilitation | 2.73 | Admin | a) |  | a) |  | e) | - | a) |  | a) |  | c) |  | a) |  | POW on process | AC
[9 empty] | b) |  | b) |  | f) | - | b) |  | b) |  | d) |  | b) |  |  | AC
[9 empty] | c) |  | c) |  | g) |  | c) | [8 empty] | 1
[9 empty] | d) |  | d) | [12 empty] | 1
|  |  | 10. Dujali - Pawas - San Vicente |  |  | Road Rehabilitation | 4.42 | Admin | a) |  | a) |  | e) | - | a) |  | a) |  | c) |  | a) |  | POW on process | 1
[9 empty] | b) |  | b) |  | f) | - | b) |  | b) |  | d) |  | b) |  |  | 1
[9 empty] | c) |  | c) |  | g) |  | c) | [8 empty] | 1
[9 empty] | d) |  | d) | [12 empty] | 1
|  |  | 11. Los Amigos 1 - Esperanza - Los Amigos 2 |  |  | Road Rehabilitation | 3.59 | Admin | a) | 19200000 | a) |  | e) | - | a) |  | a) |  | c) |  | a) |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | 1
[9 empty] | b) |  | b) |  | f) | - | b) |  | b) |  | d) |  | b) |  |  | AC
[9 empty] | c) |  | c) |  | g) |  | c) | [8 empty] | FS
[9 empty] | d) |  | d) | [12 empty] | AC
|  |  | 12. San Miguel - Crossing Kinamayan |  |  | Road Rehabilitation | 2.8 | Admin | a) |  | a) |  | e) | - | a) |  | a) |  | c) |  | a) |  | POW on process | AC
[9 empty] | b) |  | b) |  | f) | - | b) |  | b) |  | d) |  | b) |  |  | AC
[9 empty] | c) |  | c) |  | g) |  | c) | [8 empty] | 1
[9 empty] | d) |  | d) | [12 empty] | 1
|  |  | 13. Fd Rd 2 - Sto. Tomas - Magwawa |  |  | Road Rehabilitation | 10.21 | Admin | a) |  | a) |  | e) | - | a) |  | a) |  | c) |  | a) |  | POW on process | 1
[9 empty] | b) |  | b) |  | f) | - | b) |  | b) |  | d) |  | b) |  |  | 1
[9 empty] | c) |  | c) |  | g) |  | c)
[9 empty] | d) |  | d) | [12 empty] | AC
|  |  | 14. Menzi - Balagunan - Tulalian |  |  | Road Rehabilitation | 10.63 | Admin | a) | 3720500 | a) |  | e) | - | a) |  | a) |  | c) |  | a) |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | AC
[9 empty] | b) |  | b) |  | f) | - | b) |  | b) |  | d) |  | b) |  |  | AC
[9 empty] | c) |  | c) |  | g) |  | c) | [8 empty] | AC
[9 empty] | d) |  | d) | [12 empty] | AC
|  |  | 15. Jct. Bdry. Tagum - Talomo |  |  | Road Rehabilitation | 12.01 | Admin | a) |  | a) |  | e) | - | a) |  | a) |  | c) |  | a) |  | POW on process | AC
[9 empty] | b) |  | b) |  | f) | - | b) |  | b) |  | d) |  | b) |  |  | AC
[9 empty] | c) |  | c) |  | g) |  | c) | [8 empty] | AC
[9 empty] | d) |  | d) | [12 empty] | AC
|  |  | 16. Rehab. of Anibongan-Salvacion-Cabay-angan Provincial Road with Drainage |  |  | Road Drainage rehabiliated | - | - | a) | 2000000 | a) | 2019-01-14 | e) | - | a) | 2000000 | a) | 89.8% | c) | 89.8% | a) | 1 | On going | AC
[9 empty] | b) | Toquero | b) | 5/22/2019 | f) | 149 | b) | 2000000 | b) | - | d) | - | b) | 4 |  | AC
[9 empty] | c) | PEO | c) | 2019-08-04 | g) | - | c) | [8 empty] | AC
[9 empty] | d) | 75 C.D | d) | 12/31/2019
| 2. Various of Local Roads & Drainage Development Project (Provincewide) |  |  |  |  | Road Drainage rehabiliated | km. | Admin | a) | 15000000 | [12 empty] | See projects listed below | AC
[9 empty] | b) | Paraguya | [13 empty] | AC
[9 empty] | c) | PEO | [13 empty] | AC
[9 empty] | d) | - | [13 empty] | AC
|  |  | Rehab./Impv't. of San Juan-New Talisay Provincial Road with Drainage |  |  | Road Drainage rehabiliated | km. | Admin | a) | 1000000 | a) | - | e) | - | a) | 1000000 | a) | - | c) | - | a) | - | For implementation | AC
| 2.1 | [7 empty] | b) | - | b) | - | f) | - | b) | 1000000 | b) | - | d) | - | b) | - |  | 1
[9 empty] | c) | PEO | c) | - | g) | - | c) | - | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | Repair/Rehab. Of Concrete Road Jct. Suaon-Libuton, Kapalong |  |  | Road Drainage rehabiliated | km. | Admin | a) | 1000000 | a) | - | e) | - | a) | 1000000 | a) | - | c) | - | a) | - | For NTP | AC
| 2.2 | [7 empty] | b) | - | b) | - | f) | - | b) | 1000000 | b) | - | d) | - | b) | - |  | AC
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | AC
[9 empty] | d) | - | d) | - | [11 empty] | AC
|  |  | Impv't. of Cross Drainage along Saug-Sonlon-Bdry. Longanapan |  |  | Road Drainage rehabiliated | ln.m | Admin | a) | 3000000 | a) | - | e) | - | a) | 3000000 | a) | - | c) | - | a) | - | For implementation | AC
| 2.3 | [7 empty] | b) | - | b) | - | f) | - | b) | 3000000 | b) | - | d) | - | b) | - |  | 1
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | Rehab./Impv't. of Sto. Niño-Palma Gil-Sitio Opao Provincial Road with Drainage |  |  | Road Drainage rehabiliated | ln.m | Contract | a) | 3000000 | a) | - | e) | - | a) | 3000000 | a) | - | c) | - | a) | - | PO # 2019113329 (Tagum Constrak Corp.)
| 2.4 | [7 empty] | b) | - | b) | - | f) | - | b) | 3000000 | b) | - | d) | - | b) | - |  | AC
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | AC
[9 empty] | d) | - | d) | - | [11 empty] | AC
|  |  | Rehab. Of Dujali-Pawas-San Vicente Provincial Road |  |  | Road Drainage rehabiliated | km | Admin | a) | 2000000 | a) | - | e) | - | a) | 1102900 | a) | 20% | c) | 50% | a) | - | On-going | AC
| 2.5 | [7 empty] | b) | Toquero | b) | 2019-11-04 | f) | - | b) | 2000000 | b) | - | d) | - | b) | - |  | 1
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | Rehab./Impv't. of Jct. highway Ising-Magsaysay Provincial Road with Drainage |  |  | Road Drainage rehabiliated | km | Admin | a) | 1500000 | a) | 2019-01-16 | e) | - | a) | 1500000 | a) | - | c) | - | a) | - | Revised POW for approval - Jan. 7, 2020 Revision was made due to scarcity of boulders changing from stone masonry to concrete masonry | 1
| 2.6 | [7 empty] | b) | Toquero | b) | - | f) | - | b) | 1500000 | b) | - | d) | - | b) | - |  | 1
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
| 3. Various Water System Development Project (Provincewide) |  |  |  |  | Water System projects | km | Admin | a) | 9750000 | [12 empty] | See projects listed below (Note: 1.3M declared savings funded to other Water System Projects-AIP 2nd revision CY 2019) | AC
[9 empty] | b) | Varon/Imboy | [13 empty] | FS
[9 empty] | c) | PEO | [13 empty] | AC
[9 empty] | d) | - | [13 empty] | 1
| 3.1 | Construction of Water System Projects | [21 empty] | 1
1
|  |  | Construction of PWS, Bgry. Linao, San Isidro |  |  | Water System | Households | Admin | a) | 500000 | a) | 2019-06-19 | e) | - | a) | 500000 | a) | 22.01% | c) | 22.01% | a) | 4 | On-going | 1
| 3.1.1 | [7 empty] | b) | Aclaracion | b) | 2020-02-24 | f) | - | b) | 500000 | b) | - | d) | -4.00% | b) | 88 |  | 1
[9 empty] | c) | PEO | c) | 2020-04-23 | g) | - | c) | 110050 | [7 empty] | 1
[9 empty] | d) | 60 CD | d) | - | [11 empty] | 1
|  |  | Construction of PWS, Brgy. Datu Balong, San Isidro |  |  | Water System | - | Admin | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For declaration of savings because the spring water source is not feasible for development | 1
| 3.1.2 | [7 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | AC
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | Construction of PWS, Brgy. Sagayen, San Isidro |  |  | Water System | Households | Contract | a) | 500000 | a) | 2019-09-10 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Re-bid PR # 1908-3071 | 1
| 3.1.3 | [7 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 1
[9 empty] | c) | PEO | c) | - | g) | - | c) | - | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | Installation of Shallow Tube Wells & Const. of Machinery Shed |  |  | Water System | - | Admin | a) | 1600000 | a) | - | e) | - | a) | 1600000 | a) | - | c) | - | a) | - | Amended from- Procurement of materials for the installation of Shallow Tube Wells for Irrigation & Const. of Machinery Shed for storage of open surface pump for PAGRO. POW revision on going due to the revision of plan to suit the amount allocated. | 1
| 3.1.4 | [7 empty] | b) | - | b) | - | f) | - | b) | 1600000 | b) | - | d) | - | b) | -
[9 empty] | c) | PEO | c) | - | g) | - | c) | - | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | Impv't. of Potable Water System, Consolacion, Panabo City |  |  | Water System Projects | Households | - | a) | 500000 | a) | 2019-06-28 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | 1
| 3.1.5 | [7 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 1
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | AC
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | Impv't. of Potable Water System, Tagbitan-ag, Samal Dist. |  |  | Water System Projects | Households | - | a) | 500000 | a) | 2019-06-19 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For implementation | 1
| 3.1.6 | [7 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 1
[9 empty] | c) | - | c) | - | g) | - | c) | -
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | Impv't. of Potable Water System, San Antonio, babak, IGCS |  |  | Water System Projects | - | - | a) | 500000 | a) | 2019-06-25 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | 1
| 3.1.7 | [7 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 1
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | Impv't. of Potable Water System, Mambago-A, IGCS |  |  | Water System Projects | Households | - | a) | 500000 | a) | 2019-09-10 | e) | - | a) | 500000 | a) | - | c) | - | a) | - |  | 1
| 3.1.8 | [7 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - | For Implementation | 1
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | Construction of PWS, Brgy. Buenavista, Panabo City |  |  | Water System Projects | - | - | a) | 500000 | a) | June 19 ,2019 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For implementation | 1
| 3.1.9 | [7 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 1
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | Construction of PWS, Brgy. Brgy. Kiotoy, Panabo City |  |  | Water System Projects | Households | Contract | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | 1
| 3.1.6 | [7 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 1
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | Construction of PWS, Brgy. Linusotan, Talikud, District, IGCS |  |  | Water System Projects | Households | - | a) | 1300000 | a) | 2019-10-23 | e) | - | a) | 1300000 | a) | - | c) | - | a) | - | Procurement on process | 1
| 3.1.7 | [7 empty] | b) | - | b) | - | f) | - | b) | 1300000 | b) | - | d) | - | b) | -
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | Rehab. of PWS, Brgy. San Miguel, Babak, IGCS |  |  | Water System Projects | Households | Contract | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | 1
| 3.1.8 | [7 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 1
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | Construction of PWS, Brgy. Cacao, Panabo City |  |  | Water System Projects | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For cancellation. Purchase of Geo-resistivity equipment but procurement still on process | 1
| 3.1.9 | [7 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | -
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | Rehabilitation of Potable Water System, Brgy. Pangubatan, kaputian Dist. IGCS |  |  | Water System Projects | Households | Contract | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Purchase Order # 19093434 | 1
| 3.2.0 | [7 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 1
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | AC
[9 empty] | d) | - | d) | - | [11 empty] | 1
| 4. Various Government Buildings and Facilities Development Project (Provincewide) |  |  |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of recipients | - | Admin | a) | 27000000 | [12 empty] | See projects listed below | 1
[9 empty] | b) | Medalla | [13 empty] | 1
[9 empty] | c) | PEO
[9 empty] | d) | - | [13 empty] | 1
|  |  | Repair Bay of Disaster Quick Response Equipment @ PEO Compound, Gov't. Center, Mankilam, Tagum City |  |  | Bldg. | 66 sq.m | Admin | a) | 1000000 | a) | 2019-01-31 | e) | - | a) | 1000000 | a) | 64.77% | c) | 64.77% | a) | 5 | On-going | 1
|  | 4.1 | [6 empty] | b) | Chua/Mucas | b) | 2019-12-02 | f) | - | b) | 1000000 | b) | - | d) | - | b) | 95 |  | 1
[9 empty] | c) | PEO | c) | 2020-04-19 | g) | - | c) | 647700 | [7 empty] | 1
[9 empty] | d) | 140 CD | d) | - | [11 empty] | 1
|  |  | Repair/Impv't. of Municipal Triball Hall, New Corella |  |  | Bldg. | sq.m | Admin | a) | 1500000 | a) |  | e) | - | a) | 1500000 | a) | 10.95% | c) | 10.95% | a) | 5 | On-going | 1
| 4.2 | [7 empty] | b) | Cahayag | b) | 2020-03-02 | f) | - | b) | 1500000 | b) | - | d) |  | b) | 95 |  | 1
[9 empty] | c) | PEO | c) | 2020-06-12 | g) | - | c) | - | [7 empty] | 1
[9 empty] | d) | 103 CD | d) | - | [11 empty] | 1
|  |  | Const. of Multi-Purpose Hall Center (Cultural Heritage in Ancestral Domain of Ata-Manobo) |  |  | Bldg. | sq.m | Admin | a) | 3000000 | a) | - | e) | - | a) | 3000000 | a) | - | c) | - | a) | - | Fund re-aligned to GIDAS projects | 1
| 4.3 | [7 empty] | b) | - | b) | - | f) | - | b) | 3000000 | b) | - | d) | - | b) | - |  | 1
[9 empty] | c) | - | c) | - | g) | - | c) | -
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | Const. of IP Women's Multi-{Purpose Bldg.), Cabidiangan, Sto. Niño, Talaingod |  |  | Bldg. | - | Admin | a) | 2000000 | a) | 2019-05-15 | e) | - | a) | 2000000 | a) | - | c) | - | a) | - | Final abstract #0320200897 (Alpebel Builders) | 1
| 4.4 | [7 empty] | b) | - | b) | - | f) | - | b) | 2000000 | b) | - | d) | - | b) | - |  | 1
[9 empty] | c) | PEO | c) | - | g) | - | c) | - | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | Extension of PAGRO Training Center & Ground Dev't., Gov't. Center, Mankilam, Tagum City |  |  | Bldg. | sq.m | Admin | a) | 1000000 | a) | 2019-07-26 | e) | - | a) | 1000000 | a) | 26.76% | c) | 26.76% | a) | 5 | On-going | 1
| 4.5 | [7 empty] | b) | Chua/Mugas | b) | 2020-02-03 | f) | - | b) | 1000000 | b) | - | d) | - | b) | 57 |  | 1
[9 empty] | c) | PEO | c) | 2020-04-23 | g) | - | c) | -
[9 empty] | d) | 80 CD | d) | - | [11 empty] | FS
|  |  | Construction of Abilidad Training Center, Gov't. Center, Mankilam, Tagum City |  |  | Bldg. | - | - | a) | 7000000 | a) | - | e) | - | a) | 7000000 | a) | - | c) | - | a) | - | Fund re-aligned to GIDAS projects | AC
| 4.6 | [7 empty] | b) | - | b) |  | f) | - | b) | 7000000 | b) | - | d) | - | b) | - |  | AC
[9 empty] | c) | PEO | c) | - | g) | - | c) | - | [7 empty] | AC
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | Const. of 1 CL Bldg. @ Suawon ES, New Corella |  |  | Bldg. | 82.65 sq.m | Admin | a) | 1000000 | a) | 2020-06-07 | e) | - | a) | 1000000 | a) | 50.90% | c) | 50.90% | a) | 7 | On-going | AC
| 4.7 | [7 empty] | b) | Miraflor | b) | 2019-12-09 | f) | - | b) | 1000000 | b) |  | d) | - | b) | 147 |  | AC
[9 empty] | c) | PEO | c) | 2020-04-21 | g) | - | c) | 509000 | [7 empty] | 1
[9 empty] | d) | 135 CD | d) | - | [11 empty] | 1
|  |  | Const. of Municipal Tribal Hall, San Isidro |  |  | Bldg. | 42.00 sq.m | Admin | a) | 500000 | a) | 2019-01-15 | e) | - | a) | 500000 | a) | 81.44% | c) | 81.44% | a) | 8 | On-going | 1
| 4.8 | [7 empty] | b) | Aclaracion | b) | 2019-12-02 | f) | - | b) | 500000 | b) |  | d) | - | b) | 176 |  | 2
[9 empty] | c) | PEO | c) | 2020-02-19 | g) | - | c) | 407200 | [7 empty] | AC
[9 empty] | d) | 80 CD | d) | - | [11 empty] | 1
|  |  | Const. of Perimeter Fence at Sto. Niño Naeco Integrated School w/ Tugas Extension, Sto. Niño, Talaingod |  |  | Bldg. | sq.m | Admin | a) | 2000000 | a) | 2019-06-19 | e) | - | a) | 2000000 | a) | 87.65% | c) | 13.55% | a) | - | On-going | 1
|  | 4.9 | [6 empty] | b) | Torrecampo | b) | 2020-03-02 | f) | - | b) | 2000000 | b) | - | d) | - | b) | - |  | 1
[9 empty] | c) | PEO | c) | 2020-06-09 | g) | - | c) | - | [7 empty] | 1
[9 empty] | d) | 100 CD | d) | - | [11 empty] | 1
|  |  | Const. of DDN Hospital Carmen Zone Annex Bldg. Phase 2, |  |  | Bldg. | - | Contract | a) | 3620000 | a) | 2019-06-28 | e) | - | a) | 3620000 | a) | - | c) | - | a) | - | For implementation (Winning Bidder - Digos Constrak Corp.) | 1
|  | 5 | [6 empty] | b) | - | b) | - | f) | - | b) | 3620000 | b) | - | d) | - | b) | - |  | 1
[9 empty] | c) | Digos Constrak Corp/ | c) | - | g) | - | c) | - | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
| 5. Stimulus Projects for Various Barangays |  |  |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | Admin | a) | 41500000 | [12 empty] | See projects listed below | 1
[9 empty] | b) | Medalla | [13 empty] | 1
[9 empty] | c) | PEO | [13 empty] | 1
[9 empty] | d) | - | [13 empty] | 1
| ASUNCION | [22 empty] | 1
|  |  | Rehab. Of Multi-Purpose Hall, New Bantayan, Asuncion |  |  | Bldg. | sq.m | Admin | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | (Fund transferred to LGU.c /o Engr. Lilibeth Cuajao) | 1
| 1 | [7 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 1
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
| NEW CORELLA | [22 empty] | 1
|  |  | Construction of Multi-Purpose Hall, El Salvador, New Corella |  |  | Bldg. | sq.m | MLGU | a) | 500000 | a) |  | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Fund transferred to LGU March 23, 2019 c/o Engr. Dugoldugol | 1
| 2 | [7 empty] | b) | - | b) |  | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 1
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | Concreting of Drainage Canal , Pob., New Corella |  |  | Drainage | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Amended to Const. of 2 Storey Multi-Purpose Hall phase 3 (Brgy. Hall),Pob., New Corella (AIP 3rd revision CY 2019 / SB No. 4 CY 2019 | 1
| 3 | [7 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 1
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | Rehab. Of Multi-Purpose Hall, Cabidianan, New Corella |  |  | Bldg. | sq.m | MLGU | a) | 500000 | a) | 2019-02-20 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Fund transferred to LGU c/o Engr. Dugoldugol | 2
| 4 | [7 empty] | b) |  | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 2
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | Brgy. Electrification (Centro Gupitan), Gupitan, Talaingod |  |  | Elect. | - | MLGU | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Re-aligned to other stimulus projects that need additional funds to complete since the amount can not complete the project. Recommended for exact fund that can complete the project. | 2
| 5 | [7 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 1
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
| TAGUM CITY | [22 empty] | 1
|  |  | Rehab. of Evacuation Center, Magugpo Poblacion, Tagum City |  |  | Bldg. | - | - | a) | 500000 | a) |  | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Amended in the AIP 3rd revision CY 2019 /SB No. 4 CY 2019 changing the total project cost to P600,000.00 | 2
| 6 | [7 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 2
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | Const. of Water System, San Agustin, Tagum City |  |  | Water System | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Re-aligned to other stimulus projects that need additional funds since there is no deed of donation for the proposed site. | 2
| 7 | [7 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | AC
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | Const. of Brgy. Health Center, Magugpo South, Tagum City |  |  | Bldg. | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Amended in the AIP 3rd revision CY 2019 /SB No. 4 CY 2019 changing the total project cost to P1,550,000.00 | 2
| 8 | [7 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 2
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | FS
[9 empty] | d) | - | d) | - | [11 empty] | AC
|  |  | Const. of Women Livelihood Center, San Isidro, Tagum City |  |  | Bldg. | sq.m | Admin | a) | 500000 | a) | 2019-05-29 | e) | - | a) | 500000 | a) | 68.79% | c) | 68.79% | a) | 5 | On -going | AC
| 9 | [7 empty] | b) | Juan | b) | 2020-01-02 | f) | 27 CD | b) | 500000 | b) | - | d) | - | b) | 95 |  | AC
[9 empty] | c) | PEO | c) | 2020-03-21 | g) |  | c) | 343950 | [7 empty] | AC
[9 empty] | d) | 80 CD | d) | 2020-03-16 | [11 empty] | 1
|  |  | Rehab. Of Brgy. Health Center, Apokon, Tagum City |  |  | Bldg. | - | - | a) | 500000 | a) | 2019-03-25 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For implementation (The brgy. council agreed not to pursue with the project if it will not be completed and needs additional funds) | 1
| 10 | [7 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 1
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | Rehab. of Evacuation Center, Mankilam, Tagum City |  |  | Bldg. | - | - | a) | 500000 | a) | 2019-03-25 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For implementation | 1
| 11 | [7 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 1
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | AC
|  | CONTRACT PACKAGE | [21 empty] | 2
|  |  | Rehab. of Evacuation Center, New Balambam, Tagum City |  |  | Bldg. | sq.m | Contract | a) | 500000 | a) | 2019-09-10 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Final abstract #0320200899 (JJR Construction & Supply) | 2
| 12 | [7 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 2
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | Rehab. Of Multi-Purpose Hall, Cuambogan, Tagum City |  |  | Bldg. | sq.m | Contract | a) | 500000 | a) | 2019-09-10 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Purchase Order # 19083071 (Post Qualification on process) | 2
| 13 | [7 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 1
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | Completion of Evacuation Center, Nueva Fuerza, Tagum City |  |  | Bldg. | sq.m | Contract | a) | 500000 | a) | 2019-09-10 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Purchase Order # 19083071 (Post Qualification on process) | 1
| 14 | [7 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 1
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | Completion. of Water System , Busaon, Tagum City |  |  | Water System | Households | Contract | a) | 500000 | a) | 2019-09-10 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For implementation | 1
| 15 | [7 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 1
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | AC
[9 empty] | d) | - | d) | - | [11 empty] | AC
|  |  | Const. of Drainage Canal, Bincungan, Tagum City |  |  | Drainage | sq.m | Contract | a) | 500000 | a) | 2019-09-10 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Purchase Order # 19083071 (Post Qualification on process) | AC
| 16 | [7 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | AC
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | AC
|  |  | Rehab. of Evacuation Center, Magugpo North, Tagum City |  |  | Bldg. | sq.m | Contract | a) | 500000 | a) | 2019-09-10 | e) | - | a) | 500000 | a) | - | c) | - | a) |  | Purchase Order # 19083071 (Post Qualification on process) | 1
| 17 | [7 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 1
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 2
| SAN ISIDRO | [22 empty] | 1
|  |  | Rehab. Of Multi-Purpose Hall , Sto. Niño, San Isidro |  |  | Bldg. | 182 sq.m | Admin | a) | 500000 | a) | 2019-02-20 | e) | - | a) | 500000 | a) | 93.00% | c) | 93.00% | a) | 6 | On-going | 1
| 18 | [7 empty] | b) | Aclaracion | b) | 2020-01-02 | f) | - | b) | 500000 | b) | - | d) | - | b) | 132 |  | AC
[9 empty] | c) | PEO | c) | 2020-02-19 | g) | - | c) | 465000 | [7 empty] | 1
[9 empty] | d) | 45 CD | d) | - | [11 empty] | 1
|  |  | Rehab. Of Water System at Purok Cabang & Mangga , Pinamuno, San Isidro |  |  | Water System | Households | Contract | a) | 500000 | a) | 2019-12-06 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Purchase Order # 2020010025 (RLHV) | 1
| 19 | [7 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 1
[9 empty] | c) | - | c) | - | g) | - | c) | -
[9 empty] | d) | - | d) | - | [11 empty] | FS
|  |  | Rehab. Of Water System , Igangon, San Isidro |  |  | Water System | Households | Contract | a) | 500000 | a) | 2019-05-29 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For implementation | AC
| 20 | [7 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 1
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | FS
| CARMEN | [22 empty] | AC
|  |  | Const. of Multi-Purpose Hall, La Paz, Carmen |  |  | Bldg. | - | - | a) | 500000 | a) | 2019-02-20 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Fund transferred to LGU March 28, 2019 | 1
| 21 | [7 empty] | b) | - | b) | 2019-08-16 | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 1
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | Const. of Evacuation Center Ph. 3, Sto. Niño, Carmen |  |  | Bldg. | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Amended in the AIP 3rd revision CY 2019/ SB No. 4 CY 2019 changing the location to Purok !-c, Sto. Nino since the previous location was implemented by DPWH | 1
| 22 | [7 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 1
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
| 23 |  | Const. of Multi-Purpose Hall, Mangalcal, Carmen |  |  | Bldg. | - | - | a) | 500000 | a) | 2019-02-20 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Fund transfer to LGU Carmen, 3/28/2019 with check no. 2574953 and OR no. 0118982 | AC
[9 empty] | b) | - | b) | 2019-09-16 | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 1
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
| 24 |  | Rehab. of Multi-Purpose Hall, Guadalupe, Carmen |  |  | Bldg. | - | - | a) | 500000 | a) | 2019-02-20 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Fund transferred to LGU March 28, 2019
[9 empty] | b) | - | b) | 2019-08-15 | f) | - | b) | 500000 | b) | - | d) | - | b) | -
[9 empty] | c) | - | c) | 2019-11-13 | g) | - | c) | -
[9 empty] | d) | - | d) | -
| 25 |  | Const. of Multi-Purpose Hall, Mabuhay, Carmen |  |  | Bldg. | - | - | a) | 500000 | a) | 2019-02-20 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Fund transfer to LGU Carmen, 3/28/2019 with check no. 2574925 and OR no. 0118984
[9 empty] | b) | - | b) | 2019-08-16 | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | AC |  |  |  | 893809.45
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | FS
[9 empty] | d) | - | d) | -
| 26 |  | Const. Canal Lining , Mabaus, Carmen |  |  | Canal lining | - | - | a) | 500000 | a) | 2019-02-20 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Fund transferred to LGU March 28, 2019 | FS
[9 empty] | b) | - | b) |  | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | AC
[9 empty] | c) | - | c) |  | g) | - | c) | - | [7 empty] | AC
[9 empty] | d) | - | d) | - | [11 empty] | AC
| 27 |  | Rehab. Of Evacuation Center, Alejal, Carmen |  |  | Bldg. | - | - | a) | 500000 | a) | 2019-02-20 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Fund transfer to LGU Carmen, 3/28/2019 with check no.2574949 and OR no. 0118991 | AC
[9 empty] | b) | - | b) | 2019-08-16 | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | AC
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
| 28 |  | Compl. Of Evacuation Center, Tuganay, Carmen |  |  | Bldg. | - | - | a) | 500000 | a) | 2019-02-20 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Fund transfer to LGU Carmen, 3/28/2019 with check no. 2574947 and OR no. 0118995 | 1
[9 empty] | b) | - | b) | 2019-08-16 | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | AC
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
| 29 |  | Const. of Multi-Purpose hall, Ising, Carmen |  |  | Bldg. | - | - | a) | 500000 | a) | 2019-02-20 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Fund transferred to LGU March 28, 2019 | 1
[9 empty] | b) | - | b) |  | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | AC
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
| 30 |  | Rehab. of Multi-Purpose hall, Cebulano, Carmen |  |  | Bldg. | - | - | a) | 500000 | a) | 2019-02-20 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Fund transferred to LGU March 28, 2019 | 1
[9 empty] | b) | - | b) | 2019-08-16 | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | AC
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
| PANABO CITY | [22 empty] | 1
| 31 |  | Rehab. Of Multi-Purpose Hall, Kasilak, Panabo City |  |  | Bldg. | - | Contract | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Purchase Request # 19115111 | AC
[9 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 1
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
| 32 |  | Rehab. Of Multi-Purpose Hall, New Malitbog, Panabo City |  |  | Bldg. | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Amended in AIP 3rd revsion CY 2019 to change the project to Construction of Potable Water System because the original project will be funded by LGU, Panabo City (Brgy. resolution no. 25 series of 2019 dated Aug. 13, 2019 submitted) | AC
[9 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 1
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 1
1
AC
[9 empty] | d) | - | d) | - | [11 empty] | 1
| 33 |  | Desilting of Canal, New Pandan, Panabo City |  |  | Canal lining | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | 1
[9 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 1
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | AC
[9 empty] | d) | - | d) | - | [11 empty] | 1
| 34 |  | Const. Of Multi-Purpose Hall, Waterfall, Panabo City |  |  | Bldg. | - | Contract | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Purchase Request # 19125303 | 1
[9 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 1
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | AC
[9 empty] | d) | - | d) | - | [11 empty] | 1
| 35 |  | Concreting of Brgy. Road @ Prk. Guyabano, Cagangohan, Panabo City |  |  | Road | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Amended in AIP 3rd revision to change the project to Rehab of Evacuation Center because the original project has no deed of donation.(Brgy. resolution no 41 series of 2019 dated Aug. 16, 2019 submitted | 1
[9 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 1
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | AC
1
[9 empty] | d) | - | d) | - | [11 empty] | 1
| 36 |  | Rehab. Of Evacuation Center, J.P. Laurel, Panabo City |  |  | Bldg. | - | Contract | a) | 500000 | a) | 2019-10-23 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Purchase Order # 2020031248 | 1
` | [8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | AC
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
| 37 |  | Const. Of Multi-Purpose Hall, Buenavista, Panabo City |  |  | Bldg. | - | Contract | a) | 500000 | a) | 2019-10-18 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Purchase Order # 2020031248 | 1
[9 empty] | b) | - | b) | - | f) |  | b) | 500000 | b) | - | d) | - | b) | - |  | AC
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
| 38 |  | Rehab. Of Multi-Purpose Hall, San Francisco, Panabo City |  |  | Bldg. | - | Contract | a) | 500000 | a) | 2019-10-18 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Purchase Order # 2020031248 | 1
` | [8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | AC
[9 empty] | c) | - | c) | - | g) |  | c) | - | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
| 39 |  | Rehab. Of Evacuation Center, Datu Abdul Dadia, Panabo City |  |  | Bldg. | - | Contract | a) | 500000 | a) | 2019-10-18 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Purchase Order # 2020031248 | 1
[9 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | AC
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
| 40 |  | Impv't./Beautification of Brgy. Grounds, Quezon, Panabo City |  |  | Ground Dev't. | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Re aligned to other stimulus projects that needs additional funding | 1
` | [8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | AC
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
| 41 |  | Const. of Women Livelihood Center Bldg. , Gredu, Panabo City |  |  | Bldg. | - | - | a) | 500000 | a) | 2019-03-28 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Fund transfer to LGU - 3/28/2019 with check no. 2574926 and OR no. 0166517 - March 28, 2019 | 1
[9 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | AC
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
| 42 |  | Const. of Canal Lining at Purok 5, Salvacion, Panabo City |  |  | Bldg. | - | Contract | a) | 500000 | a) | 2019-10-18 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Purchase Request # 19104835 | 1
` | [8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | AC
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
| 43 |  | Rehab. Of Health Center, New Visayas, Panabo City |  |  | Bldg. | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Re aligned to other stimulus projects that needs additional funding | 1
[9 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | AC
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
| 44 |  | Rehab. Of Multi-Purpose Hall, Little Panay, Panabo City |  |  | Bldg. | - | Contract | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Purchase Request # 19125320 | 1
` | [8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | AC
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
| 45 |  | Rehab. Of Brgy. Health Center, Dalisay, Panabo City |  |  | Bldg. | - | Contract | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Purchase Request # 19125279 | 1
[9 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | AC
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
| 46 |  | Const. of Multi-Purpose Hall, Southern Davao, Panabo City |  |  | Bldg. | - | Contract | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Purchase Request # 19125279 | 1
` | [8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | AC
[9 empty] | c) | - | c) | - | g) |  | c) | - | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
| STO. TOMAS | [22 empty] | 1
| 47 |  | Rehab. Of Evacuation Center, Casig-ang, Sto. Tomas |  |  | Bldg. | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | POW preparation on-going c/o Engr. Uy | AC
[9 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 1
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
` | 48 |  | Const. of Brgy. Tibal-og Health Center, Tibal-og, Sto. Tomas |  |  | Bldg. | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | POW preparation completed amounting t oP1,550,000.00. To request for additional funds in order to complete the project to be functional | AC
[9 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 1
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
| 49 |  | Compl.of Brgy. Public Market, La Libertad, Sto. Tomas |  |  | Bldg. | - | - | a) | 500000 | a) |  | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Fund transfer to LGU - 6/26/219 with check no. 2575131 and OR no. 0557457 Completed/ PCR for submission by LGU | AC
[9 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 1
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
` | 50 |  | Rehab. Of Evacuation Center, New Visayas, Sto. Tomas |  |  | Bldg. | - | - | a) | 500000 | a) |  | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Fund transfer to LGU - 6/26/219 with check no. 2575132 and OR no. 0557455 For implementation | AC
[9 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 1
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
| 51 |  | Rehab. Of Multi-Purpose Hall, San Vicente, Sto. Tomas |  |  | Bldg. | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Fund transferred to LGU July 5, 2019 | AC
[9 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 1
[9 empty] | c) | - | c) | - | g) |  | c) | - | [7 empty] | 1
[9 empty] | d) | - | d) | - |  | - | [9 empty] | 1
` | 52 |  | Rehab. Of Multi-Purpose Hall, Salvacion, Sto. Tomas |  |  | Bldg. | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | AC
[9 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 1
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
| 53 |  | Rehab. Of Multi-Purpose Hall, Pantaron, Sto. Tomas |  |  | Bldg. | - | - | a) | 500000 | a) |  | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Amended in AIP 3rd revision CY 2019 / SB No. 4 CY 2019 increasing the project cost to P550,000.00 | AC
[9 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 1
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
` | 54 |  | Rehab. Of Multi-Purpose Hall, Magwawa, Sto. Tomas |  |  | Bldg. | sq.m | Contract | a) | 500000 | a) | June 19 2019 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Purchase Request # 19115111 | AC
[9 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 1
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
| 55 |  | Compl. Of Multi-Purpose Hall, San Jose, Sto. Tomas |  |  | Bldg. | - | - | a) | 500000 | a) |  | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Amended in AIP 3rd revision CY 2019 / SB No. 4 CY 2019 increasing the project cost to P600,000.00 | AC
[9 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 1
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
` | 56 |  | Const. of Evacuation Center, Bobongon, Sto. Tomas |  |  | Bldg. | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Re aligned to other stimulus projects that needs additional funding | AC
[9 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 1
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
| 57 |  | Rehab. Of Brgy. Road, Lunga-og, Sto. Tomas |  |  | Bldg. | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Amended in AIP 3rd revision CY 2019 / SB No. 4 CY 2019 increasing the project cost to P600,000.00 | AC
[9 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 1
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
` | 58 |  | Rehab. Of Multi-Purpose Hall, New Katipunan, Sto. Tomas |  |  | Bldg. | sq.m | Contract | a) | 500000 | a) | 2019-06-07 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Purchase Request # 19125279 | AC
[9 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 1
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
| 59 |  | Rehab. Of Multi-Purpose Hall, San Miguel, Sto. Tomas |  |  | Bldg. | sq.m | Contract | a) | 500000 | a) | 2019-06-07 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Purchase Request # 19115111 | AC
[9 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 1
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
` | 60 |  | Rehab. Of Multi-Purpose Hall, Talomo, Sto. Tomas |  |  | Bldg. | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Fund transfer to LGU - 6/26/2019 with check no. 2575130 and OR no. 0557456 For implementation | AC
[9 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 1
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
| IGCS | [22 empty] | AC
| 61 |  | Concreting of Brgy. Road From Prk. 3 to Prk. 5, Catagman, IGCS |  |  | Road | km | Contract | a) | 500000 | a) | 2019-01-14 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For implementation | 1
[9 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 1
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 1
` | [8 empty] | d) | - | d) | - | [11 empty] | AC
| 62 |  | Rehab. Of Multi-Purpose Hall, San Jose, IGCS |  |  | Bldg. | sq.m | Admin | a) | 500000 | a) | 2019-03-25 | e) | - | a) | 500000 | a) | 81.4% | c) | 90.47% | a) | 3 | On- going | 1
[9 empty] | b) | Porras | b) | 2019-01-02 | f) | - | b) | 500000 | b) | - | d) | 9.07% | b) | 44 |  | 1
[9 empty] | c) | PEO | c) | 2020-03-22 | g) | - | c) | - | [7 empty] | 1
[9 empty] | d) | 80 CD | d) | - | [11 empty] | AC
| 63 |  | Electrification at Sitio Trinidad, Bandera, IGCS |  |  | Elect. | Households | Contract | a) | 500000 | a) | 2019-03-25 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Purchase Request # 19031251 | 1
[9 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 1
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 1
` | [8 empty] | d) | - | d) | - | [11 empty] | AC
| 64 |  | Rehab. Of Multi-Purpose Hall, Del Monte, IGCS |  |  | Bldg. | - | Admin | a) | 500000 | a) | 2019-05-29 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Pending/ activity undertaken by DPWH | 1
[9 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 1
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | AC
| 65 |  | Electrification at Upper Purok Rosal, Tagbaobo, IGCS |  |  | Elect. | Households | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Purchase Order # 2020010002 (3E Electrical Sales & Services) | 1
[9 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 1
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 1
` | [8 empty] | d) | - | d) | - | [11 empty] | AC
| 66 |  | Const. Of Multi-Purpose Hall, Mambago-B, IGCS |  |  | Bldg. | sq.m | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | 100% | c) | 97.59% | a) | 5 | On-going/ Time extension on process | 1
[9 empty] | b) | Roque | b) | 2019-10-18 | f) | 64 CD | b) | 500000 | b) | 99.48% | d) | -1.89% | b) | 22 |  | 1
[9 empty] | c) | PEO | c) | 2019-12-27 | g) | - | c) | - | [7 empty] | 1
[9 empty] | d) | 60 CD | d) | 2020-03-29 | [11 empty] | AC
| 67 |  | Const. Of Multi-Purpose Hall, San Antonio, IGCS |  |  | Bldg. | sq.m | - | a) | 500000 | a) | 2019-06-19 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For implementation Proposed date started 3/24/2020 | 1
[9 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 1
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 1
` | [8 empty] | d) | - | d) | - | [11 empty] | AC
| 68 |  | Rehab. Of Water System Intake Box and Pipeline, Pangubatan, IGCS |  |  | Water System | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Plan and Pow completed. Waiting of deed of donation | 1
[9 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 1
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | AC
| 69 |  | Const. Of Multi-Purpose Hall, Cogon (Talicud), IGCS |  |  | Bldg. | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For implementation | 1
[9 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 1
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 1
` | [8 empty] | d) | - | d) | - | [11 empty] | AC
| 70 |  | Installation of Pipelines, Libertad, IGCS |  |  | Water System | Households | - | a) | 500000 | a) | 2019-03-25 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For implementation | 1
[9 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 1
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | AC
| 71 |  | Rehab. Of Evacuation Center, Libuak, IGCS |  |  | Bldg. | - | - | a) | 500000 | a) | 2019-05-29 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For implementation | 1
[9 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 1
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 1
` | [8 empty] | d) | - | d) | - | [11 empty] | AC
| 72 |  | Const. of Water System Project, Pob. Kaputian, IGCS |  |  | Water System | Households | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For implementation | 1
[9 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 1
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | AC
| 73 |  | Rehab. Of Potable Water System, San Isidro, Babak, IGCS |  |  | Water System | Households | - | a) | 500000 | a) | 2019-06-19 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For implementation | 1
[9 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 1
[9 empty] | c) | - | c) | - | g) |  | c) | - | [7 empty] | 1
` | [8 empty] | d) | - | d) | - | [11 empty] | AC
| 74 |  | Rehab. Of Potable Water System, San Miguel, IGCS |  |  | Water System | Households | - | a) | 500000 | a) | 2019-02-28 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For implementation | 1
[9 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 1
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | AC
| 75 |  | Const. of Water System Ph.II, San Remegio, IGCS |  |  | Water System | Households | - | a) | 500000 | a) | 2019-05-29 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For implementation | 1
[9 empty] | b) | Porras | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 1
[9 empty] | c) | Admin | c) | - | g) | - | c) | - | [7 empty] | 1
` | [8 empty] | d) | - | d) | - | [11 empty] | AC
| 76 |  | Electrificatio at Prk. 1,3,4, 6,7 & 8, Licup, IGCS |  |  | Elect. | Households | - | a) | 500000 | a) | 2019-02-20 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For implementation | 1
[9 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 1
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | AC
| 6. Rural Electrification Project (Provincewide) |  |  |  |  | Powerlines/posts installed & rehabilitated | Households | - | a) | 5000000 | [12 empty] | See projects listed below | 1
[9 empty] | b) | Kim Pao Lu | [13 empty] | 1
[9 empty] | c) | - | [13 empty] | 1
` | [8 empty] | d) | - | [13 empty] | AC
|  |  | Rural Electrification , Del Monte, New Corella |  |  | Elect. | - | - | a) | 3000000 | a) | - | e) | - | a) | 3000000 | a) | - | c) | - | a) | - | For implementation | 1
| 6.1 | [7 empty] | b) | P.Bueno | b) | - | f) | - | b) | 3000000 | b) | - | d) | - | b) | - |  | 1
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | AC
|  |  | Rural Electrification at St. Bundok, San Roque, New Corella |  |  | Elect. | - | - | a) | 1000000 | a) | - | e) | - | a) | 1000000 | a) | - | c) | - | a) | - | Draft abstract # 0320201453 | 1
| 6.2 | [7 empty] | b) | P.Bueno | b) | - | f) | - | b) | 1000000 | b) | - | d) | - | b) | - |  | 1
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 1
` | [8 empty] | d) | - | d) | - | [11 empty] | AC
|  |  | Rural Electrification at Sitio Sagrada, Pob. Kaputian, IGCS |  |  | Elect. | Households | - | a) | 1000000 | a) | - | e) | - | a) | 1000000 | a) | - | c) | - | a) | - | Purchase Request # 19031251 | 1
|  | 6.3 | [6 empty] | b) | P.Bueno | b) | - | f) | - | b) | 1000000 | b) | - | d) | - | b) | - |  | 1
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | AC
| 7. Social Welfare and Development |  |  |  |  | Bldg. | sq.m | - | a) | 1090666.4 | [12 empty] | See projects listed below | 1
[9 empty] | b) | Kim Pao Lu | [13 empty] | 1
[9 empty] | c) | - | [13 empty] | 1
` | [8 empty] | d) | - | [13 empty] | AC
|  | 7.1 RESIDENTIAL CARE FACILITIES | [21 empty] | 1
|  |  | Construction of Multi-Purpose Covered Court/Evacuation, Bahay Pag-Asa, New Corella |  |  | Bldg. | sq.m | Admin | a) | 2500000 | a) | 2019-06-19 | e) | - | a) | 2500000 | a) | 48.65% | c) | 48.65% | a) | 12 | On-going | 1
| a | [7 empty] | b) | Mayang | b) | 2019-12-02 | f) | - | b) | 2500000 | b) | - | d) | - | b) | 360 |  | 1
[9 empty] | c) | PEO | c) | 2020-03-09 | g) | - | c) | - | [7 empty] | AC
[9 empty] | d) | 135 CD | d) | - | [11 empty] | 1
|  |  | Const. of Multi-Purpose Covered Court/Evacuation Center |  |  | Bldg. | sq.m | - | a) | 1090666.4 | a) | - | e) | - | a) | 1090666.4 | a) | - | c) | - | a) | - | POW and Plan on-going | 1
| b | [7 empty] | b) | - | b) | - | f) | - | b) | 1090666.4 | b) | - | d) | - | b) | - |  | 1
` | [8 empty] | c) | PEO | c) | - | g) | - | c) | - | [7 empty] | AC
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  | 7.2 CONST. OF SHELTERED WORKSHOP FAC. FOR PWD'S AND ELDERLY | [21 empty] | 1
|  |  | Const. in Progress - Bldgs. And Other Structures |  |  | Bldg. | sq.m | - | a) | 2500000 | a) | - | e) | - | a) | 2500000 | a) | - | c) | - | a) | - | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | 1
| a | [7 empty] | b) | - | b) | - | f) | - | b) | 2500000 | b) | - | d) | - | b) | -
[9 empty] | c) | PEO | c) | - | g) | - | c) | -
` | [8 empty] | d) | - | d) | - | [11 empty] | AC
| T. | 5% CALAMITY FUND CY 2019 | [21 empty] | 1
|  | DISASTER PREVENTION AND MITIGATION | [21 empty] | 1
|  | Flood Control and Slope Protection | [21 empty] | 1
| 1 |  | Desiltation/Excavation of rivers and creeks |  |  | creeks and canals deislted | km | Admin | a) | 3000000 | [12 empty] | See project listed below | AC
[9 empty] | b) | Paraguya | [13 empty] | 1
[9 empty] | c) | PEO | [13 empty] | 1
[9 empty] | d) | - | [13 empty] | 1
|  |  | 1.1 | Desilting of Limbaan Creek, New Corella |  | creeks and canals deislted | ln.m | Admin | a) | 2000000 | a) | - | e) | - | a) | 2000000 | a) | - | c) | - | a) | - | Purchase Order # 2019124324 - Digos Constrak; PO # 2019124231 - Diocesan | AC
[9 empty] | b) | - | b) | - | f) | - | b) | 2000000 | b) | - | d) | - | b) | - |  | 1
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
` | 2 |  | Revitment of Dike and Slope Proection |  |  | Protection dikes/slope protection | ln.m | Admin | a) | 3000000 | [12 empty] | See project listed below | AC
[9 empty] | b) | - | [13 empty] | 1
[9 empty] | c) | - | [13 empty] | 1
[9 empty] | d) | - | [13 empty] | 1
|  |  | 2.1 | Slope Protection Along Kapalong-Mabantao, Florida |  | creeks and canals deislted | - | - | a) | 1000000 | a) | - | e) | - | a) | 1000000 | a) | - | c) | - | a) | - | For cancellation funded to DPWH. Budget Transferred to 5% Calamity Fund- Rehab and Recovery | AC
[9 empty] | b) | - | b) | - | f) | - | b) | 1000000 | b) | - | d) | - | b) | - |  | 1
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
` |  |  |  | Repair/Rehab. Of Upper Tuganay Dike |  | creeks and canals deislted | - | - | a) | 1000000 | a) | 2019-08-15 | e) | - | a) | 1000000 | a) | 60% | c) | 70% | a) | 9 | On-going | AC
|  |  | 2.2 | [5 empty] | b) | Toquero | b) | 2019-08-19 | f) | - | b) | 1000000 | b) | - | d) |  | b) | 80 | Embankment formation Dike | 1
[9 empty] | c) | Admin | c) | 2019-09-29 | g) |  | c) | - | [6 empty] | enhancement | 1
[9 empty] | d) | 59 C.D | d) | - | [10 empty] | Time Extension on process | 1
| 3 |  | Improvement of bridges and cross drainage |  |  | bridge and cross drainage rehab./improved # of sq.m riprapped, culverts replaced | - | - | a) | 3000000 | [12 empty] | See projects listed below | AC
[9 empty] | b) | Paraguya | [13 empty] | 1
[9 empty] | c) | PEO | [13 empty] | 1
[9 empty] | d) | - | [13 empty] | 1
` |  |  | 3.1 | Impv't. of Jct. New Boholano - New Loon Cross Drainage |  | Drainage | - | - | a) | 2000000 | a) | - | e) | - | a) | 2000000 | a) | - | c) | - | a) | - | POW preparation on going c/o PEO-PDPM. Insufficient budget to complete required works for the project | AC
[9 empty] | b) | - | b) | - | f) | - | b) | 2000000 | b) | - | d) | - | b) | - |  | 1
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | 3.2 | Impv't. of Jct. Saug-Sonlon-Bdry. Longanapan Cross Drainage |  | Road | - | - | a) | 1000000 | a) | - | e) | - | a) | 1000000 | a) | - | c) | - | a) | - | For implementation | AC
[9 empty] | b) | - | b) | - | f) | - | b) | 1000000 | b) | - | d) | - | b) | - |  | 1
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | Improvement of roads, drainage and canal |  |  | Protection dikes/slope protection | - | - | a) | 3000000 |  |  |  | - | [8 empty] | See project listed below | 1
|  | 4 | [6 empty] | b) | Paraguya | [13 empty] | 1
[9 empty] | c) | PEO | [13 empty] | 1
[9 empty] | d) | - | [13 empty] | AC
|  |  |  | Rehab./Impv't. of Prk. 1 - Prk. 2 Sitio Pawas Provincial Road |  | Road | km | Admin | a) | 1500000 | a) | 2019-07-23 | e) | - | a) | 1500000 | a) | 17.14% | c) | 1.18% | a) | 2 | On-going | 1
|  |  | 4.1 | [5 empty] | b) | Sanchez | b) | 2019-08-05 | f) |  | b) | 1500000 | b) | - | d) | -15.96% | b) | 10 |  | 1
` | [8 empty] | c) | Admin | c) | 2019-09-28 | g) |  | c) | - | [7 empty] | AC
[9 empty] | d) | 55 | d) | - | [11 empty] | 1
|  | DISASTER REHABILITATION & RECOVERY PROGRAM Building Back Better Project | [21 empty] | 1
|  | 1. Repairs & Maintenance- Infrastructure Assets | [21 empty] | AC
|  |  |  | Disiltation of Tagum Creek |  | Creek | ln.m | Admin | a) | 2000000 | a) | - | e) | - | a) | 2000000 | a) | - | c) | - | a) | - | Waiting for the delivery of materials | 1
|  |  | 1.1 | [5 empty] | b) | - | b) | - | f) | - | b) | 2000000 | b) | - | d) | - | b) | - |  | 1
` | [8 empty] | c) | PEO | c) | - | g) | - | c) | - | [7 empty] | AC
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  | 2. Property, Plant and Equipmen Construction in Progress- Infrastructure Assets | [21 empty] | 1
|  | ■ |  | Rehabilitation of Pamacaun-Lasang-Banate Provincial Road |  | Road | km | Admin | a) | 1500000 | a) | - | e) | - | a) | 1500000 | a) | - | c) | - | a) | - | For implementation | 1
|  |  | 2.1 | [5 empty] | b) | - | b) | - | f) | - | b) | 1500000 | b) | - | d) | - | b) | - |  | 1
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
` |  | ■ |  | Rehabilitation of Del Pilar Jct. Silangan |  | Road | km | Admin | a) | 1500000 | a) | 2019-07-26 | e) | - | a) | 1500000 | a) | 58.87% | c) | 53.11% | a) | 4 | On-going | AC
|  |  | 2.2 | [5 empty] | b) | Gone | b) | 2020-02-17 | f) | - | b) | 1500000 | b) | - | d) | -5.76% | b) | 40 |  | 1
[9 empty] | c) | PEO | c) | 2020-03-27 | g) | - | c) | - | [7 empty] | 1
[9 empty] | d) | 120 CD | d) | - | [11 empty] | 1
|  | ■ |  | Installation of 72" dia RCPC x 4M at San Agustin ES |  | Drainage | ln.m | Admin | a) | 350000 | a) | - | e) | - | a) | 350000 | a) | - | c) | - | a) | - | POW on process | AC
|  |  | 2.3 | [5 empty] | b) | - | b) | - | f) | - | b) | 350000 | b) | - | d) | - | b) | - |  | 1
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
` |  | ■ |  | Rehabilitation of Libuganon River along Kapalong Mabantao-Florida Provincial Road |  | Road | km | Admin | a) | 900000 | a) | - | e) | - | a) | 900000 | a) | - | c) | - | a) | - | For implementation | AC
|  |  | 2.4 | [5 empty] | b) | - | b) | - | f) | - | b) | 900000 | b) | - | d) | - | b) | - |  | 1
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  | ■ |  | Rehabilitation of Mesaoy-Jct. Mahayahay Road |  | Road | km | Admin | a) | 1000000 | a) | - | e) | - | a) | 1000000 | a) | - | c) | - | a) | - | For implementation | AC
|  |  | 2.5 | [5 empty] | b) | - | b) | - | f) | - | b) | 1000000 | b) | - | d) | - | b) | - |  | 1
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
` |  | ■ |  | Rehabilitation of Sta. Fe- Mambing Road & Slope Protection |  | Road | km | Admin | a) | 1320000 | a) | - | e) | - | a) | 1320000 | a) | - | c) | - | a) | - | Materials RE-PR | AC
|  |  | 2.6 | [5 empty] | b) | - | b) | - | f) | - | b) | 1320000 | b) | - | d) | - | b) | - |  | 1
[9 empty] | c) | - | c) | - | g) |  | c) | - | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  | ■ |  | Rehabilitation of Canal Lining and Slope Protection at San Agustin E/S, San Agustin, Tagum City |  | Drainage | ln.m | Admin | a) | 350000 | a) | - | e) | - | a) | 350000 | a) | - | c) | - | a) | - | Pending due to for cancellation of previous project. | AC
|  |  | 2.7 | [5 empty] | b) | - | b) | - | f) | - | b) | 350000 | b) | - | d) | - | b) | - |  | 1
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
` | CALAMITY/ OPLAN CANAL | [21 empty] | On-going | AC
|  |  |  | Repair of Damaged Drainage/ Creek along Abucay Creek |  |  | - | - | a) | 1320000 | a) |  | e) |  | a) |  | a) | 100% | c) | 85% | a) |  |  | 1
|  |  | 1 | [5 empty] | b) | Ganaba | b) | 2019-10-01 | f) |  | b) |  | b) |  | d) |  | b) |  |  | 1
[9 empty] | c) | Admin | c) | 2019-12-02 | g) |  | c) | [8 empty] | 1
[9 empty] | d) | 65 C.D | d) | 2019-12-31 | [11 empty] | AC
|  |  |  | Repair of Damaged Drainage Creek along Panabo River |  |  |  |  | a) | 665000 | a) |  | e) |  | a) |  | a) | 15.3% | c) | 15.3% | a) |  | On-going | 1
|  |  | 2 | [5 empty] | b) | Alconera | b) | 2019-11-15 | f) |  | b) |  | b) |  | d) |  | b) |  |  | 1
[9 empty] | c) | Admin | c) | 2020-01-27 | g) |  | c) | [8 empty] | 1
` | [8 empty] | d) | 73 C.D | d) | [12 empty] | AC
|  |  |  | Repair of Damaged Drainage/Creek along Tuganay-Ising River |  |  |  |  | a) | 1540500 | a) |  | e) |  | a) |  | a) | 25.6% | c) | 23.6% | a) | 3 | On-going | 1
|  |  | 3 | [5 empty] | b) | Ganaba | b) | 2019-11-15 | f) |  | b) |  | b) |  | d) | -2% | b) | 66 |  | 1
[9 empty] | c) | Admin | c) | 2020-05-15 | g) |  | c) | [8 empty] | 1
[9 empty] | d) | 182 C.D | d) | [12 empty] | AC
|  |  |  | Repair of Damaged Drainage/ Creeks along San Miguel NIA Road |  |  |  |  | a) | 470000 | a) |  | e) |  | a) |  | a) | 80% | c) | 80% | a) | 3 | On-going | 1
|  |  | 4 | [5 empty] | b) | Nasol | b) |  | f) |  | b) |  | b) |  | d) |  | b) | 66 |  | 1
[9 empty] | c) | Admin | c) |  | g) |  | c) | [8 empty] | 1
` | [8 empty] | d) |  | d) | [12 empty] | AC
|  |  |  | Repair of Damaged Drainage/ Creeks along Sadpodon Creek |  |  |  |  | a) | 470000 | a) |  | e) |  | a) |  | a) |  | c) |  | a) |  | For implementation | 1
|  |  | 5 | [5 empty] | b) |  | b) |  | f) |  | b) |  | b) |  | d) |  | b) |  |  | 1
[9 empty] | c) | Admin | c) |  | g) |  | c) | [8 empty] | 1
[9 empty] | d) |  | d) | [12 empty] | AC
| U. | SUPPLEMENTAL BUDGET NO. 1 CY 2019 | [21 empty] | 1
|  | 1. 8918/Purchase / Const. / Compl./ Imprvt. Of Various Gov'y Bldgs, Structures & Facilities - General Fund Proper | [21 empty] | 1
|  |  |  | Purchase of Lot for Cemetery, Cambanogoy, Asuncion |  | Land | - | - | a) | 1500000 | a) | - | e) | - | a) | 1500000 | a) | - | c) | - | a) | - | Documents for fund transfer to be complied by the LGUs. Letter sent dated June 18, 2019 | 1
` |  |  | 1 | [5 empty] | b) | - | b) | - | f) | - | b) | 1500000 | b) | - | d) | - | b) | - |  | AC
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  |  | Purchase of Lot for Cemetery, San Roque, New Corella |  | Land | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Documents for fund transfer to be complied by the LGUs. Letter sent dated June 18, 2019 | 1
|  |  | 2 | [5 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | AC
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  | 2. 8918/Stimulus Projects for Various Barangays. Const. in Progress - Bldgs & Other Structure | [21 empty] | 1
` |  |  |  | Rehab/Impvt of Gymnasium, Sagayen, Asuncion |  | Bldg | sq.m | - | a) | 1500000 | a) | - | e) | - | a) | 1500000 | a) | - | c) | - | a) | - | Final Abstract # 0320200900 (Alpebel Builders & Supply Corp.) | AC
|  |  | 1 | [5 empty] | b) | - | b) | - | f) | - | b) | 1500000 | b) | - | d) | - | b) | - |  | 1
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
| V. | LOCALLY FUDNDED PROGRAM/PROJECT - 20% Development Fund | [21 empty] | AC
|  | 1. Infrastructure Development Program 8918/ Stimulus Projects | [21 empty] | 1
|  | for Various Barangays Property, Plant and Equipment - Land | [21 empty] | 1
|  |  |  | Purchase of Lot for Resettlement Site, New Sambog, New Corella |  | Land | - | - | a) | 1500000 | a) | - | e) | - | a) | 1500000 | a) | - | c) |  | a) | - | for fund transfer. Waiting for LGU documents. Liquidation of previous fund transfer for the water system project of LGU. | 1
|  |  | 1 | [5 empty] | b) | - | b) | - | f) | - | b) | 1500000 | b) | - | d) | - | b) | - |  | FS
[9 empty] | c) | - | c) | - | g) | - | c) | -
[9 empty] | d) | - | d) | -
2. Property, Plant and Equipment - Construction in Progress-Infrastructure Assets
|  |  |  | Installation of Street Lights at Prk 1,2,3,4, Sagayen, Asuncion |  | Elect. | Households | - | a) | 1000000 | a) | - | e) | - | a) | 1000000 | a) | - | c) |  | a) | - | Purchase Order # 2019113377 (Tagum Builders)
|  |  | 2.1 | [5 empty] | b) | - | b) | - | f) | - | b) | 1000000 | b) | - | d) | - | b) | -
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  |  | Rehab/Imprvt. Of FMR, Prk 3,7, & 8, Concepcion, Asuncion |  | Road | km | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) |  | a) | - | Waiting for equipment availability as of Feb. 5, 2020 report submitted by Engr. Cuajao | 1
|  |  | 2.2 | [5 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 1
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  |  | Farm to Market Road, San Jose, New Corella |  | Road | - | - | a) | 2000000 | a) | - | e) | - | a) | 2000000 | a) | - | c) | - | a) | - | Plan Preparation on process c/o PDPM | 1
|  |  | 2.3 | [5 empty] | b) | - | b) | - | f) | - | b) | 2000000 | b) | - | d) | - | b) | - |  | 1
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  |  | Const. of Water System, New Sambog, New Corella |  | Water System | Households | MLGU | a) | 1000000 | a) | - | e) | - | a) | 1000000 | a) | - | c) | - | a) | - | Fund transferred to LGU | 1
|  |  | 2.4 | [5 empty] | b) | - | b) | - | f) | - | b) | 1000000 | b) | - | d) | - | b) | - |  | 1
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | FS
[9 empty] | d) | - | d) | - | [11 empty] | AC
|  |  |  | Const. of Drainage Canal from Prk. 3, 1-A, 2-A to Prk 1-B, Brgy Site (Ph. 2), Limbaan, New Corella |  | Flood Control - Drainage | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | POW preparation on going c/o PDPM | AC
|  |  | 2.5 | [5 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | AC
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | AC
[9 empty] | d) | - | d) | -
` |  |  |  | Const. of FMR from Prk 1 to Sitio Magsaysay via Pundol & Prk 4, Patrocenio, New Corella |  | Road | - | - | a) | 2000000 | a) | - | e) | - | a) | 2000000 | a) | - | c) | - | a) | - | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | AC
|  |  | 2.6 | [5 empty] | b) | - | b) | - | f) | - | b) | 2000000 | b) | - | d) | - | b) | - |  | 1
[9 empty] | c) | - | c) | - | g) |  | c) | - | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
` |  |  |  | Const. of Multi-Purpose Pavement, San Jose, New Corella |  | Bldgs | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | POW approved but allotment not yet requested waiting for deed of donation c/o Engr. Canillada | AC
|  |  | 2.7 | [5 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 1
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
` |  | 3. Const. in Progress - Bldgs & Other Structures | [21 empty] | AC
|  |  |  | Const. of Multipurpose Covered Court, Buan, Asuncion |  | Covered Court | sq.m | MLGU | a) | 2500000 | a) | 2019-06-26 | e) | - | a) | 2500000 | a) | - | c) | - | a) | - | Fund transferred to LGU | 1
|  |  | 3.1 | [5 empty] | b) | - | b) | - | f) | - | b) | 2500000 | b) | - | d) | - | b) | - |  | 1
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 1
` | [8 empty] | d) | - | d) | - | [11 empty] | AC
|  |  |  | Const. of Multipurpose Covered Court, Pamacaun, Asuncion |  | Covered Court | sq.m | MLGU | a) | 2500000 | a) | 2019-05-29 | e) | - | a) | 2500000 | a) | - | c) |  | a) | - | Fund transferred to LGU | 1
|  |  | 3.2 | [5 empty] | b) | - | b) | - | f) | - | b) | 2500000 | b) | - | d) | - | b) | - |  | 1
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 1
` | [8 empty] | d) | - | d) | - | [11 empty] | AC
|  |  |  | Const. of 2 Storey Multi purpose Hall Ph.2 (Brgy. Hall) , Poblacion, New Corella |  | Bldgs | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | 1
|  |  | 3.3 | [5 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 1
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 1
` | [8 empty] | d) | - | d) | - | [11 empty] | AC
|  |  |  | Rehab. Of Multi-Purpose Hall (Evacuation Ctr.) Limbaan, New Corella |  | Bldgs | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | POW for revision. Change to Contract | 1
|  |  | 3.4 | [5 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 1
[9 empty] | c) | - | c) | - | g) |  | c) | - | [7 empty] | 1
` | [8 empty] | d) | - | d) | - | [11 empty] | AC
|  |  |  | Expansion of Multi-Purpose Hall ( Brgy. Hall), Patrocenio, New Corella |  | Bldgs | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Purchase Order # 2020020796 (JJR Construction) | 1
|  |  | 3.5 | [5 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 1
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 1
[9 empty] | d) | - | d) | -
` | W. | SUPPLEMENTAL BUDGET NO. 3 CY 2019 | [21 empty] | AC
|  | LOCALLY FUNDED PROGRAM/PROJECTS- 20% DEVELOPMENT FUND | [21 empty] | 1
|  | INFRASTRUCTURE DEVELOPMENT PROGRAM | [21 empty] | 1
|  | 1. 8918/ Various Local Roads & Drainage Development Project Construction in Progress- Infrastructure Assets | [21 empty] | 1
` |  | ■ |  | Repair/Rehabil;itation of Concrete R.d. Jct. Suaon-Libuton Kapalong |  | Road | - | - | a) | 1000000 | a) | - | e) | - | a) | 1000000 | a) | - | c) | - | a) | - | For implementation | AC
|  |  | 1.1 | [5 empty] | b) | - | b) | - | f) | - | b) | 1000000 | b) | - | d) | - | b) | - |  | 1
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
` |  | ■ |  | Rehabilitation of Dujali-Pawas-San Vicente Provincial Road, B.E. Dujali |  | Road | km | - | a) | 2000000 | a) | - | e) | - | a) | 2000000 | a) | - | c) | - | a) | - | The amount was reduced to P1,102,900.00 | AC
|  |  | 1.2 | [5 empty] | b) | - | b) | - | f) | - | b) | 2000000 | b) | - | d) | - | b) | - |  | 1
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
` |  | ■ |  | Repair/Rehabil;itation of Concrete R.d. Jct. Suaon-Libuton Kapalong |  | Road | km | - | a) | 1000000 | a) | - | e) | - | a) | 1000000 | a) | - | c) | - | a) | - | For implementation | AC
|  |  | 1.3 | [5 empty] | b) | - | b) | - | f) | - | b) | 1000000 | b) | - | d) | - | b) | - |  | 1
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
2. 8918/ VariousWater System Development Project Construction in Progress- Infrastructure Assets
|  | ■ |  | Rehabilitation of Water System in PEEDO-LPRRC, Brgy. Poblacion, New Corella |  | Water System | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Purchase Order # 2020010009 (ANCOR Water Resources)
|  |  | 2.1 | [5 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | -
[9 empty] | c) | - | c) | - | g) |  | c) | -
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  | ■ |  | Improvement of Potable Water System at Brgy. Mambago- A, Samal District, IGACOS |  | Water System | Households | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | (Amended in the AIP 2nd Revision to change the location from Peñaplata to Samal District) PO approved September 2, 2019 | 1
|  |  | 2.2 | [5 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 1
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  | ■ |  | Rehabilitation of Potable Water System at Brgy. San Miguel, Samal District, IGACOS |  | Water System | Households | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For implementation | 1
|  |  | 2.3 | [5 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 1
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  | ■ |  | Construction of Potable Water System at Brgy.Linusotan, Kaputian District, IGACOS |  | Water System | Households | - | a) | 1300000 | a) | - | e) | - | a) | 1300000 | a) | - | c) | - | a) | - | (Additional 800,000.00 from Const. of PWS in purok 2, Pag-asa, Kapalong which was funded by OPAPP CY 2018) (amended) For allotment- October 15, 2019 | 1
|  |  | 2.4 | [5 empty] | b) | - | b) | - | f) | - | b) | 1300000 | b) | - | d) | - | b) | - |  | 1
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  | DISASTER REHABILITATION & RECOVERY PROGRAM Building Back Better Project | [21 empty] | 1
|  | 1. Repairs & Maintenance- Infrastructure Assets | [21 empty] | 1
|  | ■ |  | Disiltation of Mactan River (Ph. II) |  | Desiltation | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | PLAN AND POW on process c/o PEO-PDPM | 1
|  |  | 1.2 | [5 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 2
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  | 2. Property, Plant and Equipmen Construction in Progress- Infrastructure Assets | [21 empty] | 1
|  |  |  | Rehabilitation of Dujali-Balisong-Magupising Provincial Road |  | Road | km | Admin | a) | 1280000 | a) | - | e) | - | a) | 1280000 | a) | 100% | c) | 6.48% | a) | - | On-going | 2
|  | 2.1 | [6 empty] | b) | Mellomida | b) | 2019-12-02 | f) | 20 CD | b) | 1280000 | b) | 97.61% | d) | -91.13% | b) | - |  | 1
[9 empty] | c) | PEO | c) | 2020-02-03 | g) | - | c) | - | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
| X. | SUPPLEMENTAL BUDGET NO. 4 CY 2019
INFRASTRUCTURE DEVELOPMENT PROGRAM
LOCALLY FUNDED PROGRAMS/ PROJECTS GENERAL FUND PROPER
|  | 1 | PEACE AND ORDER PROGRAM/1914 Construction in Progress- Land Improvements | [20 empty] | 2
|  | ■ |  | Provincial Livestock & Poultry Multiplier Farm Road Network Construction, Sitio Salawao, Sto. Niño, Talaingod |  | Poultry | - | - | a) | 5500000 | a) | - | e) | - | a) | 5500000 | a) | - | c) | - | a) | - | Purchase Order # 2020010084, 2020010095 | 1
[9 empty] | b) | - | b) | - | f) | - | b) | 5500000 | b) | - | d) | - | b) | - |  | 1
|  |  | 1.1 | [5 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  | ■ |  | Proposed Road Opening of Tawinian-Tapayanon Road Section |  | Road | km | Admin | a) | 10000000 | a) | 2019-11-15 | e) | - | a) | 10000000 | a) | 18.48% | c) | 18.48% | a) | 5 | On-going | 1
|  |  | 1.2 | [5 empty] | b) | Garcia | b) | 2019-11-18 | f) | - | b) | 10000000 | b) | - | d) | - | b) | 319 |  | 1
[9 empty] | c) | PEO | c) | 2020-09-18 | g) | - | c) | - | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  | ■ |  | Rehabilitation of San Jose- Sitio Mahayahay-Magwawa Provincial Road, Sro. Tomas |  | Road | - | - | a) | 1000000 | a) | - | e) | - | a) | 1000000 | a) | - | c) | - | a) | - | POW preparation on-going c/o South District | 1
|  |  | 1.3 | [5 empty] | b) | - | b) | - | f) | - | b) | 1000000 | b) | - | d) | - | b) | - |  | 1
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  | 2 | 8918/ Various Government Buildigs & Facilities Development Project Construction in Progress- Land Improvements | [20 empty] | 1
|  | ■ |  | Completion of Brgy. Health Center, Maniki, Kapalong |  | Bldg. | - | - | a) | 627000 | a) | - | e) | - | a) | 627000 | a) | - | c) | - | a) | - | PROJECT Was funded by LGU, Kapalong
|  |  | 2.1 | [5 empty] | b) | - | b) | - | f) | - | b) | 627000 | b) | - | d) | - | b) | - |  | 1
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  | 3. 8918/ Various Local Roads and Drainaige Development Project Construction in Progress- Infrastructure Assets | [21 empty] | 1
|  | ■ |  | Rehabilitation of Local Roads at Dalisay-Manay Road Section, Panabo City |  | Road | - | - | a) | 246100 | a) | - | e) | - | a) | 246100 | a) | - | c) | - | a) | - | For implementation | 1
|  |  | 3.1 | [5 empty] | b) | - | b) | - | f) | - | b) | 246100 | b) | - | d) | - | b) | - |  | 2
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  | ■ |  | Rehabilitation of Local Roads at Sta. Cruz-Jct. Tagpore-Buenavista Raod Section, Panabo City |  | Road | - | - | a) | 431000 | a) | - | e) | - | a) | 431000 | a) | - | c) | - | a) | - | For implementation | 1
|  |  | 3.2 | [5 empty] | b) | - | b) | - | f) | - | b) | 431000 | b) | - | d) | - | b) | - |  | 2
[9 empty] | c) | - | c) | - | g) |  | c) | - | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  | ■ |  | Rehabilitation of Local Roads at Taba-Bucana Road Section, Taba, Carmen |  | Road | - | - | a) | 220000 | a) | - | e) | - | a) | 220000 | a) | - | c) | - | a) | - | For implementation | 1
|  |  | 3.3 | [5 empty] | b) | - | b) | - | f) | - | b) | 220000 | b) | - | d) | - | b) | - |  | 2
[9 empty] | c) | - | c) | - | g) | - | c) | -
[9 empty] | d) | - | d) | -
|  | 4 | 8918/ Stimulus Projects for Various Barangays Construction in Progress- Infrastructure Assets
|  | ■ |  | Construction of Potable Water System at Purok 6, New Santiago, Asuncion |  | Water System | Households | contract | a) | 1000000 | a) | - | e) | - | a) | 1000000 | a) | - | c) | - | a) | - | Change of POW to Contract
|  |  | 4.1 | [5 empty] | b) | - | b) | - | f) | - | b) | 1000000 | b) | - | d) | - | b) | -
[9 empty] | c) | - | c) | - | g) | - | c) | -
[9 empty] | d) | - | d) | -
|  | ■ |  | Construction of Children's Playground with Amenities, Poblacion, New Corella |  | Bldg. | sq.m | Admin | a) | 2500000 | a) | - | e) | - | a) | 2500000 | a) | 28.94% | c) | 28.94% | a) | 10 | On-going
|  |  | 4.2 | [5 empty] | b) | Mayang | b) | 2019-11-25 | f) | - | b) | 2500000 | b) | - | d) | - | b) | 290
[9 empty] | c) | - | c) | 2020-03-03 | g) | - | c) | 723500
[9 empty] | d) | - | d) | -
|  | ■ |  | Concreting of Brgy. Road Canal, Dujali, B.E. Dujali |  | Road | - | contract | a) | 650000 | a) | - | e) | - | a) | 650000 | a) | - | c) | - | a) | - | For implementation
|  |  | 4.3 | [5 empty] | b) | - | b) | - | f) | - | b) | 650000 | b) | - | d) | - | b) | - |  | 1
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  | ■ |  | Desilting and Conretign of Drainage-Main Collector Canal, New Casay, B.E. Dujali |  | Desiltation | - | contract | a) | 650000 | a) | - | e) | - | a) | 650000 | a) | - | c) | - | a) | - | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | 1
|  |  | 4.4 | [5 empty] | b) | - | b) | - | f) | - | b) | 650000 | b) | - | d) | - | b) | - |  | 1
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  | ■ |  | Concreting of Drainage, Tanglaw, B.E., Dujali |  | Drainage | - | contract | a) | 1200000 | a) | - | e) | - | a) | 1200000 | a) | - | c) | - | a) | - | For implementation | 1
|  |  | 4.5 | [5 empty] | b) | - | b) | - | f) | - | b) | 1200000 | b) | - | d) | - | b) | - |  | 1
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  |  | Construction of Potable Water System, New Malitbog, Panabo City |  | Water System | Households | contract | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | 1
|  |  | 4.6 | [5 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 1
[9 empty] | c) | - | c) | - | g) | - | c) | -
[9 empty] | d) | - | d) | -
|  | ■ |  | Construction of Water System Project, Poblacion Kaputian, Samal |  | Water System | Households | contract | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For implementation
|  |  | 4.7 | [5 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | -
[9 empty] | c) | - | c) | - | g) | - | c) | -
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  | ■ |  | Construction of Canal Lining at Prk. 5, Salvacion, Panabo City |  |  |  | contract | a) | 600000 | a) | - | e) | - | a) | 600000 | a) | - | c) | - | a) | - | For implementation | 1
|  |  | 4.8 | [5 empty] | b) | - | b) | - | f) | - | b) | 600000 | b) | - | d) | - | b) | - |  | 1
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | FS
[9 empty] | d) | - | d) | -
|  | ■ |  | Rehabilitation of Brgy. Road at Lunga-og. Sto. Tomas |  |  |  | contract | a) | 600000 | a) | - | e) | - | a) | 600000 | a) | - | c) | - | a) | - | For implementation
|  |  | 4.9 | [5 empty] | b) | - | b) | - | f) | - | b) | 600000 | b) | - | d) | - | b) | -
[9 empty] | c) | - | c) | - | g) | - | c) | -
[9 empty] | d) | - | d) | -
|  | 5 | 8918/ Stimulus Projects for Various Barangays Construction in Progress- Bldgs. & Other Structures
|  | ■ |  | Rehabilitation of Evacuation Center at Magugpo Pob., Tagum City |  | Bldg. | sq.m | - | a) | 600000 | a) | - | e) | - | a) | 600000 | a) | - | c) | - | a) | - | Purchase Order # 2020020796 (JJR Construction)
|  |  | 5.1 | [5 empty] | b) | - | b) | - | f) | - | b) | 600000 | b) | - | d) | - | b) | -
[9 empty] | c) | - | c) | - | g) | - | c) | -
[9 empty] | d) | - | d) | -
|  | ■ |  | Construction of Brgy. Health Center at Magugpo South, Tagum City |  | Bldg. | sq.m | - | a) | 1550000 | a) | - | e) | - | a) | 1550000 | a) | - | c) | - | a) | - | Purchase Order # 20022150 (On-process)
|  |  | 5.2 | [5 empty] | b) | - | b) | - | f) | - | b) | 1550000 | b) | - | d) | - | b) | - |  | FS
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | FS
[9 empty] | d) | - | d) | -
|  | ■ |  | Construction of Evacuation Center at Purok 1-C Brgy. Sto. Niño, Carmen |  |  |  | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For implementation
|  |  | 5.3 | [5 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | -
[9 empty] | c) | - | c) | - | g) |  | c) | -
[9 empty] | d) | - | d) | -
|  | ■ |  | Construction of Multi-Purpose Hall, Waterfall, Panabo City |  |  |  | - | a) | 1050000 | a) | - | e) | - | a) | 1050000 | a) | - | c) | - | a) | - | For implementation
|  |  | 5.4 | [5 empty] | b) | - | b) | - | f) | - | b) | 1050000 | b) | - | d) | - | b) | -
[9 empty] | c) | - | c) | - | g) | - | c) | -
[9 empty] | d) | - | d) | -
|  |  |  | Rehabilitation of Multi-Purpose Hall, San Francisco, Panabo City |  |  |  | - | a) | 600000 | a) | - | e) | - | a) | 600000 | a) | - | c) | - | a) | - | For implementation
|  |  | 5.5 | [5 empty] | b) | - | b) | - | f) | - | b) | 600000 | b) | - | d) | - | b) | -
[9 empty] | c) | - | c) | - | g) | - | c) | -
[9 empty] | d) | - | d) | -
|  | ■ |  | Rehabilitation of Evacuation Center at Datu Abdul Dadia, Panabo City |  |  |  | - | a) | 650000 | a) | - | e) | - | a) | 650000 | a) | - | c) | - | a) | - | For implementation
|  |  | 5.6 | [5 empty] | b) | - | b) | - | f) | - | b) | 650000 | b) | - | d) | - | b) | -
[9 empty] | c) | - | c) | - | g) | - | c) | -
[9 empty] | d) | - | d) | -
|  |  |  | Construction of Multi-Purpose Hall, Buenavista, Panabo City |  |  |  | - | a) | 1050000 | a) | - | e) | - | a) | 1050000 | a) | - | c) | - | a) | - | For implementation
|  |  | 5.7 | [5 empty] | b) | - | b) | - | f) | - | b) | 1050000 | b) | - | d) | - | b) | -
[9 empty] | c) | - | c) | - | g) | - | c) | -
[9 empty] | d) | - | d) | -
|  |  |  | Rehabilitation of Multi-Purpose Hall, Llittle Panay, Panabo City |  |  |  | - | a) | 550000 | a) | - | e) | - | a) | 550000 | a) | - | c) | - | a) | - | For implementation
|  |  | 5.8 | [5 empty] | b) | - | b) | - | f) | - | b) | 550000 | b) | - | d) | - | b) | -
[9 empty] | c) | - | c) | - | g) | - | c) | -
[9 empty] | d) | - | d) | -
|  |  |  | Rehabilitation of Multi-Purpose Hall, Pantaron, Sto. Tomas |  |  |  | - | a) | 550000 | a) | - | e) | - | a) | 550000 | a) | - | c) | - | a) | - | For implementation
|  |  | 5.9 | [5 empty] | b) | - | b) | - | f) | - | b) | 550000 | b) | - | d) | - | b) | -
[9 empty] | c) | - | c) | - | g) | - | c) | -
[9 empty] | d) | - | d) | -
|  | ■ |  | Rehabilitation of Multi-Purpose Hall, Salvacion, Sto. Tomas |  |  |  | - | a) | 1000000 | a) | - | e) | - | a) | 1000000 | a) | - | c) | - | a) | - | POW preparation on-going c/o PDPM
|  |  | 6 | [5 empty] | b) | - | b) | - | f) | - | b) | 1000000 | b) | - | d) | - | b) | -
[9 empty] | c) | - | c) | - | g) | - | c) | -
[9 empty] | d) | - | d) | -
|  |  |  | Completion of Multi-Purpose Hall, San Jose, Sto. Tomas |  |  |  | - | a) | 600000 | a) | - | e) | - | a) | 600000 | a) | - | c) | - | a) | - | For implementation
|  |  | 6.1 | [5 empty] | b) | - | b) | - | f) | - | b) | 600000 | b) | - | d) | - | b) | -
[9 empty] | c) | - | c) | - | g) | - | c) | -
[9 empty] | d) | - | d) | -
|  |  |  | Rehabilitation of Multi-Purpose Hall, Kasilak, Panabo City |  |  |  | - | a) | 650000 | a) | - | e) | - | a) | 650000 | a) | - | c) | - | a) | - | For implementation
|  |  | 6.2 | [5 empty] | b) | - | b) | - | f) | - | b) | 650000 | b) | - | d) | - | b) | -
[9 empty] | c) | - | c) | - | g) |  | c) | -
[9 empty] | d) | - | d) | -
|  |  |  | Rehabilitation of Brgy. Health Center, Dalisay, Panabo City |  |  |  | - | a) | 550000 | a) | - | e) | - | a) | 550000 | a) | - | c) | - | a) | - | For implementation
|  |  | 6.3 | [5 empty] | b) | - | b) | - | f) | - | b) | 550000 | b) | - | d) | - | b) | -
[9 empty] | c) | - | c) | - | g) | - | c) | -
[9 empty] | d) | - | d) | -
|  |  |  | Rehabilitation of Evacuation Center, Kiotoy, Panabo City |  |  |  | - | a) | 650000 | a) | - | e) | - | a) | 650000 | a) | - | c) | - | a) | - | For implementation
|  |  | 6.4 | [5 empty] | b) | - | b) | - | f) | - | b) | 650000 | b) | - | d) | - | b) | -
[9 empty] | c) | - | c) | - | g) | - | c) | -
[9 empty] | d) | - | d) | -
|  |  |  | Rehabilitation of Evacuation Center, Cagangohan, Panabo City |  |  |  | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Purchase Request # 19125279
|  |  | 6.5 | [5 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | -
[9 empty] | c) | - | c) | - | g) | - | c) | -
[9 empty] | d) | - | d) | -
|  |  |  | Rehabilitation of Multi-Purpose Bldg. (Brgy. Hall) Tagpopongan, IGACOS |  |  |  | - | a) | 174460.33 | a) | - | e) | - | a) | 174460.33 | a) | - | c) | - | a) | - | Procurement on process
|  |  | 6.6 | [5 empty] | b) | - | b) | - | f) | - | b) | 174460.33 | b) | - | d) | - | b) | -
[9 empty] | c) | - | c) | - | g) | - | c) | -
[9 empty] | d) | - | d) | -
|  | 6 | INFRASTRUCTURE DEVELOPMENT PROGRAM
|  | ■ |  | Improvement of Km. 9 Sagayen-Sawata Provincial Road, San Isidro, Ph. II |  | Road | km | Admin | a) | 4591029 | a) |  | e) | - | a) | 4591029 | a) | 45% | c) | 35.05% | a) | 6 | On-going
|  |  | 6.1 | [5 empty] | b) | Limpo | b) | 2019-09-09 | f) | - | b) | 4591029 | b) | - | d) | - | b) | 138
[9 empty] | c) | PEO | c) | 2020-03-27 | g) | - | c) | 1609155.6645
[9 empty] | d) | 200 CD | d) | -
|  | ■ |  | Construction of Multi-Purpose Building, Balagunan, Sto. Tomas |  | Bldg. | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For implementation
|  |  | 6.2 | [5 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | -
[9 empty] | c) | - | c) | - | g) | - | c) | -
[9 empty] | d) | - | d) | -
| Y. | TRUST FUND 2019
1. CMGP 2019
|  | ■ |  | Road Upgrading of Kapalong - Mabantao - Florida Road with Bridge Component |  | Concreting | km. | Contract | a) | 15,435,008.00 | a) | CY 2019 | e) | 30 CD | a) | 15,435,008.00 | a) | 89.92% | c) | 63.1% | a) | 19 | On-going
|  |  | 1.1 | [5 empty] | b) | Japay/Quirante | b) | 2019-10-16 | f) | 20 CD | b) | 15,435,008.00 | b) | 66.67% | d) |  | b) | 551
[9 empty] | c) | LEGACY | c) | 2020-03-10 | g) | - | c) | 6,174,003.20
[9 empty] | d) | 147 CD | d) | 2020-04-24
|  | ■ |  | Road Upgrading of Sto Nino - Kabankalan - La Paz Provincial Road, Carmen |  |  |  | - | a) | 44461624.67 | a) | CY 2019 | e) | - | a) | 44561687 | a) | 32.2% | c) | 65.03% | a) | 42 | On-going
|  |  | 1.2 | [5 empty] | b) | Comidoy | b) | 2019-10-07 | f) | - | b) | 44561687 | b) | - | d) | 32.83% | b) | 610
[9 empty] | c) | GP & H CONST. | c) | 2020-05-15 | g) | - | c) | 6,684,253.05
[9 empty] | d) | 222 C.D | d)
|  | ■ |  | Road Upgrading of Jct Highway - Sto Nino - La Paz - San Vicenter Provincial Road, Carmen |  |  |  | - | a) | 80481331.34 | a) | CY 2019 | e) | - | a) | 80481331.34 | a) | 77.27% | c) | 78.31% | a) | 40 | On-going
|  |  | 1.3 | [5 empty] | b) | Fernandez | b) | 2019-10-07 | f) | - | b) | 80481331.34 | b) | - | d) | 1.04% | b) | 660
[9 empty] | c) | Tagum Builders | c) | 2020-06-22 | g) | - | c) | 45,481,609.97
[9 empty] | d) | 259 C.D | d)
2. PROJECTS FOR PROVINCIAL VETERINARY OFFICE
|  | ■ |  | Poultry House and Training Center Sto. Niño, Talaingod |  | Bldg. | sq.m | Contract | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Final Abstract # 012020012 (Alpebel Builders & Supply Corp.)
|  |  | 2.1 | [5 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | -
[9 empty] | c) | - | c) | - | g) | - | c) | -
[9 empty] | d) | - | d) | -
| II. | PROJECTS UNDER THE CURRENT APPROPRIATION
| A. | GENERAL FUND CY 2020
INFRASTRUCTURE DEVELOPMENT PROGRAMS
| Road ID |  | 1. Repair/Maintenance of Provincial Roads & Bridges 1 |  |  | Road Maintenance | KM | MBA | a) | 21409737 | a) | 2020-01-02 | [10 empty] | See lists of Provincial Roads
[7 empty] | 14.084 |  | b) | Paraguya | b) | 2020-01-02
| 11DAN | [7 empty] | c) | PEO | c) | 2020-12-31
[11 empty] | d) | -
[9 empty] | d) | 261 days | d) | -
|  |  | Jct. Highway Magatos - New Bantayan |  |  | Road Maintenance | 7.1 | Admin | a) | 564839.9739 | a) | 2020-01-02 | e) | - | a) | 564839.9739 | a) | 11.61% | c) | 11.61% | a) | 17 | On-going
| 001 | [7 empty] | b) | Crucio | b) | 2020-01-02 | f) | - | b) | 564839.9739 | b) | - | d) | - | b) | 374
[9 empty] | c) | PEO | c) | 2020-12-31 | g) | - | c) | 57334.17
[9 empty] | d) | 365 CD | d) | -
|  |  | Jct. Highway Magatos - New Bantayan |  |  | CBRMC | 7.1 | Contract | a) | 230737.1976 | a) | - | e) | - | a) | 230737.1976 | a) | - | c) | - | a) | - | Purchase Request # 19125305 (On process)
| 001 | [7 empty] | b) | - | b) | - | f) | - | b) | 230737.1976 | b) | - | d) | - | b) | -
[9 empty] | c) | - | c) | - | g) | - | c) | -
[9 empty] | d) | - | d) | -
|  |  | Magatos - Bdry. Pagsabangan |  |  | Road Maintenance | 8.33 | Admin | a) | 653221.626 | a) | 2020-01-02 | e) | - | a) | 653221.626 | a) | 10.67% | c) | 10.67% | a) | 17 | On-going
| 002 | [7 empty] | b) | Crucio | b) | 2020-01-02 | f) | - | b) | 653221.626 | b) | - | d) | - | b) | 374
[9 empty] | c) | PEO | c) | 2020-12-31 | g) | - | c) | 71713.44
[9 empty] | d) | 365 CD | d) | -
|  |  | Magatos - Bdry. Pagsabangan |  |  | CBRMC | 8.33 | Contract | a) | 280,180.88 | a) | - | e) | - | a) | 280,180.88 | a) | - | c) | - | a) | - | Purchase Request # 19125306 (On process)
| 002 | [7 empty] | b) | - | b) | - | f) | - | b) | 280,180.88 | b) | - | d) | - | b) | -
[9 empty] | c) | - | c) | - | g) | - | c) | -
[9 empty] | d) | - | d) | -
|  |  | Ilog - New Bantayan |  |  | Road Maintenance | 2.68 | Admin | a) | 236174.847 | a) | 2020-01-02 | e) | - | a) | 236174.847 | a) | 7.92% | c) | 7.92% | a) | 17 | On-going
| 003 | [7 empty] | b) | Crucio | b) | 2020-01-02 | f) | - | b) | 236174.847 | b) | - | d) | - | b) | 374
[9 empty] | c) | PEO | c) | 2020-12-31 | g) | - | c) | 22629.74
[9 empty] | d) | 365 CD | d) | -
|  |  | Ilog - New Bantayan |  |  | CBRMC | 2.68 | Contract | a) | 70633.836 | a) | - | e) | - | a) | 70633.836 | a) | - | c) | - | a) | - | Purchase Request # 19125307 (On process)
| 003 | [7 empty] | b) | - | b) | - | f) | - | b) | 70633.836 | b) | - | d) | - | b) | -
[9 empty] | c) | - | c) | - | g) | - | c) | -
[9 empty] | d) | - | d) | -
|  |  | Asuncion - Monte Carlo - Del Pilar |  |  | Road Maintenance | 9.93 | Admin | a) | 716344.9167 | a) | 2020-01-02 | e) | - | a) | 716344.9167 | a) | 12.33% | c) | 12.33% | a) | 17 | On-going
| 005 | [7 empty] | b) | Crucio | b) | 2020-01-02 | f) | - | b) | 716344.9167 | b) | - | d) | - | b) | 374
[9 empty] | c) | PEO | c) | 2020-12-31 | g) | - | c) | 84301.23
[9 empty] | d) | 365 CD | d) | -
|  |  | Asuncion - Monte Carlo - Del Pilar |  |  | CBRMC | 9.93 | Contract | a) | 360232.5636 | a) | - | e) | - | a) | 360232.5636 | a) | - | c) | - | a) | - | Purchase Request # 19125308 (On process)
| 005 | [7 empty] | b) | - | b) | - | f) | - | b) | 360232.5636 | b) | - | d) | - | b) | -
[9 empty] | c) | - | c) | - | g) | - | c) | -
[9 empty] | d) | - | d) | -
|  |  | Jct. Highway Canatan - Magatos |  |  | Road Maintenance | 4.85 | Admin | a) | 391296.517 | a) | 2020-01-02 | e) | - | a) | 391296.517 | a) | 10.67% | c) | 10.67% | a) | 17 | On-going
| 006 | [7 empty] | b) | Crucio | b) | 2020-01-02 | f) | - | b) | 391296.517 | b) | - | d) | - | b) | 374
[9 empty] | c) | PEO | c) | 2020-12-31 | g) | - | c) | 33056.21
[9 empty] | d) | 365 CD | d) | -
|  |  | Jct. Highway Canatan - Magatos |  |  | CBRMC | 4.85 | Contract | a) | 164812.284 | a) | - | e) | - | a) | 164812.284 | a) | - | c) | - | a) | - | Purchase Request # 19125309 (On process)
| 006 | [7 empty] | b) | - | b) | - | f) | - | b) | 164812.284 | b) | - | d) | - | b) | -
[9 empty] | c) | - | c) | - | g) | - | c) | -
[9 empty] | d) | - | d) | -
|  |  | Saug - Sonlon - Bdry. Longanapan |  |  | Road Maintenance | 11.6 | Admin | a) | 1102041.4797 | a) | 2020-01-02 | e) | - | a) | 1102041.4797 | a) | 10.67% | c) | 10.67% | a) | 17 | On-going
| 010 | [7 empty] | b) | Crucio | b) | 2020-01-02 | f) | - | b) | 1102041.4797 | b) | - | d) | - | b) | 374
[9 empty] | c) | PEO | c) | 2020-12-31 | g) | - | c) | 83166.18
[9 empty] | d) | 365 CD | d) | -
|  |  | Saug - Sonlon - Bdry. Longanapan |  |  | CBRMC | bahay | Contract | a) | 197774.7408 | a) | - | e) | - | a) | 197774.7408 | a) | - | c) | - | a) | - | Purchase Request # 19125310 (On process)
| 010 | [7 empty] | b) | - | b) | - | f) | - | b) | 197774.7408 | b) | - | d) | - | b) | -
[9 empty] | c) | - | c) | - | g) | - | c) | -
[9 empty] | d) | - | d) | -
|  |  | Jct. New Visayas - Buan |  |  | Road Maintenance | 2.99 | Admin | a) | 134598.4525 | a) | 2020-01-02 | e) | - | a) | 134598.4525 | a) | 7.72% | c) | 7.72% | a) | 17 | On-going
| 011 | [7 empty] | b) | Crucio | b) | 2020-01-02 | f) | - | b) | 134598.4525 | b) | - | d) | - | b) | 374
[9 empty] | c) | PEO | c) | 2020-12-31 | g) | - | c) | 10391.0005
[9 empty] | d) | 365 CD | d) | -
|  |  | Jct. New Visayas - Buan |  |  | CBRMC | 2.99 | Contract | a) | 124786.4436 | a) | - | e) | - | a) | 124786.4436 | a) | - | c) | - | a) | - | Purchase Request # 19125311 (On process)
| 011 | [7 empty] | b) | - | b) | - | f) | - | b) | 124786.4436 | b) | - | d) | - | b) | -
[9 empty] | c) | - | c) | - | g) | - | c) | -
[9 empty] | d) | - | d) | -
|  |  | San Vicente - Butay |  |  | Road Maintenance | 7.52 | Admin | a) | 579541.5407 | a) | 2020-01-02 | e) | - | a) | 579541.5407 | a) | 12.46% | c) | 12.46% | a) | 17 | On-going
| 013 | [7 empty] | b) | Crucio | b) | 2020-01-02 | f) | - | b) | 579541.5407 | b) | - | d) | - | b) | 374
[9 empty] | c) | PEO | c) | 2020-12-31 | g) | - | c) | 72210.876
[9 empty] | d) | 365 CD | d) | -
|  |  | San Vicente - Butay |  |  | CBRMC | 7.52 | Contract | a) | 235446.12 | a) | - | e) | - | a) | 235446.12 | a) | - | c) | - | a) | - | Purchase Request # 19125312 (On process)
| 013 | [7 empty] | b) | - | b) | - | f) | - | b) | 235446.12 | b) | - | d) | - | b) | -
[9 empty] | c) | - | c) | - | g) | - | c) | -
[9 empty] | d) | - | d) | -
|  |  | Jct. Highway Doña Andrea - Capungagan |  |  | Road Maintenance | 8.7 | Admin | a) | 675845.5865 | a) | 2020-01-02 | e) | - | a) | 675845.5865 | a) | 7.41% | c) | 7.41% | a) | 17 | On-going
| 014 | [7 empty] | b) | Crucio | b) | 2020-01-02 | f) | - | b) | 675845.5865 | b) | - | d) | - | b) | 374
[9 empty] | c) | PEO | c) | 2020-12-31 | g) | - | c) | 50080.158
[9 empty] | d) | 365 CD | d) | -
|  |  | Jct. Highway Doña Andrea - Capungagan |  |  | CBRMC | 8.7 | Contract | a) | 299016.5724 | a) | - | e) | - | a) | 299016.5724 | a) | - | c) | - | a) | - | Purchase Request # 19125313 (On process)
| 014 | [7 empty] | b) | - | b) | - | f) | - | b) | 299016.5724 | b) | - | d) | - | b) | -
[9 empty] | c) | - | c) | - | g) | - | c) | -
[9 empty] | d) | - | d) | -
|  |  | Pamacaun - Lasang - Banate |  |  | Road Maintenance | 4.11 | Admin | a) | 180747.1933 | a) | 2020-01-02 | e) | - | a) | 180747.1933 | a) | 8.6% | c) | 8.6% | a) | 17 | On-going
| 015 | [7 empty] | b) | Crucio | b) | 2020-01-02 | f) | - | b) | 180747.1933 | b) | - | d) | - | b) | 374
[9 empty] | c) | PEO | c) | 2020-12-31 | g) | - | c) | 15544.2586
[9 empty] | d) | 365 CD | d) | -
|  |  | Pamacaun - Lasang - Banate |  |  | CBRMC | 4.11 | Contract | a) | 129495.366 | a) | - | e) | - | a) | 129495.366 | a) | - | c) | - | a) | - | Purchase Request # 19125314 (On process)
| 015 | [7 empty] | b) | - | b) | - | f) | - | b) | 129495.366 | b) | - | d) | - | b) | -
[9 empty] | c) | - | c) | - | g) | - | c) | -
[9 empty] | d) | - | d) | -
|  |  | Semong - Palma Gil |  |  | Road Maintenance | 2.73 | Admin | a) | 198604.0889 | a) | 2020-01-02 | e) | - | a) | 198604.0889 | a) | 11.45% | c) | 11.45% | a) | 17 | On-going
| 018 | [7 empty] | b) | Crucio | b) | 2020-01-02 | f) | - | b) | 198604.0889 | b) | - | d) | - | b) | 374
[9 empty] | c) | PEO | c) | 2020-12-31 | g) | - | c) | 22740.1682
[9 empty] | d) | 365 CD | d) | -
|  |  | Semong - Palma Gil |  |  | CBRMC | 2.73 | Contract | a) | 77697.2196 | a) | - | e) | - | a) | 77697.2196 | a) | - | c) | - | a) | - | Purchase Request # 19125315 (On process)
| 018 | [7 empty] | b) | - | b) | - | f) | - | b) | 77697.2196 | b) | - | d) | - | b) | -
[9 empty] | c) | - | c) | - | g) | - | c) | -
[9 empty] | d) | - | d) | -
|  |  | Daligdigon-Dagohoy |  |  | Road Maintenance | 3.34 | Admin | a) | 84129.1818 | a) | 2020-01-02 | e) | - | a) | 84129.1818 | a) | 8.6% | c) | 8.6% | a) | 17 | On-going
| 020 | [7 empty] | b) | Crucio | b) | 2020-01-02 | f) | - | b) | 84129.1818 | b) | - | d) | - | b) | 374
[9 empty] | c) | PEO | c) | 2020-12-31 | g) | - | c) | 7235.1096
[9 empty] | d) | 365 CD | d) | -
|  |  | Daligdigon-Dagohoy |  |  | CBRMC | 3.34 | Contract | a) | 77697.2196 | a) | - | e) | - | a) | 77697.2196 | a) | - | c) | - | a) | - | Purchase Request # 19125315 (On process)
| 020 | [7 empty] | b) | - | b) | - | f) | - | b) | 77697.2196 | b) | - | d) | - | b) | -
[9 empty] | c) | - | c) | - | g) | - | c) | -
[9 empty] | d) | - | d) | -
|  |  | Angelo - Dagohoy |  |  | Road Maintenance | 2.19 | Admin | a) | 27260.2474 | a) | 2020-01-02 | e) | - | a) | 27260.2474 | a) | - | c) | - | a) | - | For implementation
| 021 | [7 empty] | b) | Crucio | b) | - | f) | - | b) | 27260.2474 | b) | - | d) | - | b) | -
[9 empty] | c) | PEO | c) | - | g) | - | c) | -
[9 empty] | d) |  | d) | -
|  |  | Angelo - Dagohoy |  |  | CBRMC | 2.19 | Contract | a) | 40025.8404 | a) | - | e) | - | a) | 40025.8404 | a) | - | c) | - | a) | - | Purchase Request # 19125317 (On process)
| 021 | [7 empty] | b) | - | b) | - | f) | - | b) | 40025.8404 | b) | - | d) | - | b) | -
[9 empty] | c) | - | c) | - | g) | - | c) | -
[9 empty] | d) | - | d) | -
|  |  | Jct. Sampao - Bdry. Mamacao |  |  | Road Maintenance | 4.98 | Admin | a) | 325083.1184 | a) | 2020-01-02 | e) | - | a) | 325083.1184 | a) | 9.3% | c) | 9.3% | a) | 17 | On-going
| 025 | [7 empty] | b) | Crucio | b) | 2020-01-02 | f) | - | b) | 325083.1184 | b) | - | d) | - | b) | 374
[9 empty] | c) | PEO | c) | 2020-12-31 | g) | - | c) | 30232.73
[9 empty] | d) | 365 CD | d) | -
|  |  | Jct. Sampao - Bdry. Mamacao |  |  | CBRMC | 4.98 | Contract | a) | 178939.0512 | a) | - | e) | - | a) | 178939.0512 | a) | - | c) | - | a) | - | Purchase Request # 19125318 (On process)
| 025 | [7 empty] | b) | - | b) | - | f) | - | b) | 178939.0512 | b) | - | d) | - | b) | -
[9 empty] | c) | - | c) | - | g) | - | c) | -
[9 empty] | d) | - | d) | -
|  |  | Jct. Highway - Luna - Mamacao - Narra |  |  | Road Maintenance | 9.17 | Admin | a) | 361826.1515 | a) | 2020-01-02 | e) | - | a) | 361826.1515 | a) | 6.2% | c) | 6.2% | a) | 17 | On-going
| 026 | [7 empty] | b) | Crucio | b) | 2020-01-02 | f) | - | b) | 361826.1515 | b) | - | d) | - | b) | 374
[9 empty] | c) | PEO | c) | 2020-12-31 | g) | - | c) | 22433.2214
[9 empty] | d) | 365 CD | d) | -
|  |  | Jct. Highway - Luna - Mamacao - Narra |  |  | CBRMC | 9.17 | Contract | a) | 393195.0204 | a) | - | e) | - | a) | 393195.0204 | a) | - | c) | - | a) | - | Purchase Request # 19125337 (On process)
| 026 | [7 empty] | b) | - | b) | - | f) | - | b) | 393195.0204 | b) | - | d) | - | b) | -
[9 empty] | c) | - | c) | - | g) | - | c) | -
[9 empty] | d) | - | d) | -
|  |  | Jct. Gabuyan - Katipunan - Bucana |  |  | Road Maintenance | 5.89 | Admin | a) | 485762.7577 | a) | 2020-01-02 | e) | - | a) | 485762.7577 | a) | 7.86% | c) | 7.86% | a) | 17 | On-going
| 027 | [7 empty] | b) | Crucio | b) | 2020-01-02 | f) | - | b) | 485762.7577 | b) | - | d) | - | b) | 374
[9 empty] | c) | PEO | c) | 2020-12-31 | g) | - | c) | 38180.9528
[9 empty] | d) | 365 CD | d) | -
|  |  | Jct. Gabuyan - Katipunan - Bucana |  |  | CBRMC | 5.89 | Contract | a) | 174230.1288 | a) | - | e) | - | a) | 174230.1288 | a) | - | c) | - | a) | - | Purchase Request # 19125338 (On process)
| 027 | [7 empty] | b) | - | b) | - | f) | - | b) | 174230.1288 | b) | - | d) | - | b) | -
[9 empty] | c) | - | c) | - | g) | - | c) | -
[9 empty] | d) | - | d) | -
|  |  | Capungagan - Mabuhay - Pandulian |  |  | Road Maintenance | 5.57 | Admin | a) | 468741.4542 | a) | 2020-01-02 | e) | - | a) | 468741.4542 | a) | 5.14% | c) | 5.14% | a) | 17 | On-going
| 028 | [7 empty] | b) | Crucio | b) | 2020-01-02 | f) | - | b) | 468741.4542 | b) | - | d) | - | b) | 374
[9 empty] | c) | PEO | c) | 2020-12-31 | g) | - | c) | 24093.3107
[9 empty] | d) | 365 CD | d) | -
|  |  | Capungagan - Mabuhay - Pandulian |  |  | CBRMC | 5.57 | Contract | a) | 155394.4392 | a) | - | e) | - | a) | 155394.4392 | a) | - | c) | - | a) | - | Purchase Request # 19125339 (On process)
| 028 | [7 empty] | b) | - | b) | - | f) | - | b) | 155394.4392 | b) | - | d) | - | b) | -
[9 empty] | c) | - | c) | - | g) | - | c) | -
[9 empty] | d) | - | d) | -
|  |  | Km. 15, Kipalili - New Loon |  |  | Road Maintenance | 6.93 | Admin | a) | 490709.8742 | a) | 2020-01-02 | e) | - | a) | 490709.8742 | a) | 8.86% | c) | 8.86% | a) | 17 | On-going
| 034 | [7 empty] | b) | Crucio | b) | 2020-01-02 | f) | - | b) | 490709.8742 | b) | - | d) | - | b) | 374
[9 empty] | c) | PEO | c) | 2020-12-31 | g) | - | c) | 43476.8949
[9 empty] | d) | 365 CD | d) | -
|  |  | Km. 15, Kipalili - New Loon |  |  | CBRMC | 6.93 | Contract | a) | 296662.1112 | a) | - | e) | - | a) | 296662.1112 | a) | - | c) | - | a) | - | Purchase Request # 19125340 (On process)
| 034 | [7 empty] | b) | - | b) | - | f) | - | b) | 296662.1112 | b) | - | d) | - | b) | -
[9 empty] | c) | - | c) | - | g) | - | c) | -
[9 empty] | d) | - | d) | -
|  |  | Jct. Suaon - Libuton |  |  | Road Maintenance | 7.26 | Admin | a) | 60919.7962 | a) | 2020-01-02 | e) | - | a) | 60919.7962 | a) | 7.12% | c) | 7.12% | a) | 17 | On-going
| 035 | [7 empty] | b) | Crucio | b) | 2020-01-02 | f) | - | b) | 60919.7962 | b) | - | d) | - | b) | 374
[9 empty] | c) | PEO | c) | 2020-12-31 | g) | - | c) | 4337.4895
[9 empty] | d) | 365 CD | d) | -
|  |  | Jct. Suaon - Libuton |  |  | CBRMC | 7.26 | Contract | a) | 96532.9092 | a) | - | e) | - | a) | 96532.9092 | a) | - | c) | - | a) | - | Purchase Request # 19125341 (On process)
| 035 | [7 empty] | b) | - | b) | - | f) | - | b) | 96532.9092 | b) | - | d) | - | b) | -
[9 empty] | c) | - | c) | - | g) | - | c) | -
[9 empty] | d) | - | d) | -
|  |  | Monte Dujali - Gupitan |  |  | Road Maintenance | 4.58 | Admin | a) | 224727.1648 | a) | 2020-01-02 | e) | - | a) | 224727.1648 | a) | 11.08% | c) | 11.08% | a) | 17 | On-going
| 037 | [7 empty] | b) | Crucio | b) | 2020-01-02 | f) | - | b) | 224727.1648 | b) | - | d) | - | b) | 374
[9 empty] | c) | PEO | c) | 2020-12-31 | g) | - | c) | 24899.7699
[9 empty] | d) | 365 CD | d) | -
|  |  | Monte Dujali - Gupitan |  |  | CBRMC | 4.58 | Contract | a) | 134204.2884 | a) | - | e) | - | a) | 134204.2884 | a) | - | c) | - | a) | - | Purchase Request # 19125342 (On process)
| 037 | [7 empty] | b) | - | b) | - | f) | - | b) | 134204.2884 | b) | - | d) | - | b) | -
[9 empty] | c) | - | c) | - | g) | - | c) | -
[9 empty] | d) | - | d) | -
|  |  | Sawata - Mamangan - Pinamuno |  |  | Road Maintenance | 14.48 | Admin | a) | 1113791.2481 | a) | 2020-01-02 | e) | - | a) | 1113791.2481 | a) | 6.35% | c) | 6.35% | a) | 17 | On-going
| 041 | [7 empty] | b) | Crucio | b) | 2020-01-02 | f) | - | b) | 1113791.2481 | b) | - | d) | - | b) | 374
[9 empty] | c) | PEO | c) | 2020-12-31 | g) | - | c) | 70725.7443
[9 empty] | d) | 365 CD | d) | -
|  |  | Sawata - Mamangan - Pinamuno |  |  | CBRMC | 14.48 | Contract | a) | 522690.3864 | a) | - | e) | - | a) | 522690.3864 | a) | - | c) | - | a) | - | Purchase Request # 19125343 (On process)
| 041 | [7 empty] | b) | - | b) | - | f) | - | b) | 522690.3864 | b) | - | d) | - | b) | -
[9 empty] | c) | - | c) | - | g) | - | c) | -
[9 empty] | d) | - | d) | -
|  |  | Igangon - Sawata |  |  | Road Maintenance | 9.66 | Admin | a) | 111771.1255 | a) | 2020-01-02 | e) | - | a) | 111771.1255 | a) | 8.74% | c) | 8.74% | a) | 17 | On-going
| 042 | [7 empty] | b) | Crucio | b) | 2020-01-02 | f) | - | b) | 111771.1255 | b) | - | d) | - | b) | 374
[9 empty] | c) | PEO | c) | 2020-12-31 | g) | - | c) | 9768.7964
[9 empty] | d) | 365 CD | d) | -
|  |  | Igangon - Sawata |  |  | CBRMC | 9.66 | Contract | a) | 202483.6632 | a) | - | e) | - | a) | 202483.6632 | a) | - | c) | - | a) | - | Purchase Request # 19125344 (On process)
| 042 | [7 empty] | b) | - | b) | - | f) | - | b) | 202483.6632 | b) | - | d) | - | b) | -
[9 empty] | c) | - | c) | - | g) | - | c) | -
[9 empty] | d) | - | d) | -
|  |  | Jct. Sawata - Bdry. Binasbas |  |  | Road Maintenance | 0.46 | Admin | a) | 27720.5682 | a) | 2020-01-02 | e) | - | a) | 27720.5682 | a) | 10.3% | c) | 10.3% | a) | 17 | On-going
| 043 | [7 empty] | b) | Crucio | b) | 2020-01-02 | f) | - | b) | 27720.5682 | b) | - | d) | - | b) | 374
[9 empty] | c) | PEO | c) | 2020-12-31 | g) | - | c) | 2855.2185
[9 empty] | d) | 365 CD | d) | -
|  |  | Jct. Sawata - Bdry. Binasbas |  |  | CBRMC | 0.46 | Contract | a) | 18835.6896 | a) | - | e) | - | a) | 18835.6896 | a) | - | c) | - | a) | - | Purchase Request # 19125345 (On process)
| 043 | [7 empty] | b) | - | b) | - | f) | - | b) | 18835.6896 | b) | - | d) | - | b) | -
[9 empty] | c) | - | c) | - | g) | - | c) | -
[9 empty] | d) | - | d) | -
|  |  | Tagaytay - Buan |  |  | Road Maintenance | 4.92 | Admin | a) | 378553.2244 | a) | 2020-01-02 | e) | - | a) | 378553.2244 | a) | 11.67% | c) | 11.67% | a) | 17 | On-going
| 045 | [7 empty] | b) | Crucio | b) | 2020-01-02 | f) | - | b) | 378553.2244 | b) | - | d) | - | b) | 374
[9 empty] | c) | PEO | c) | 2020-12-31 | g) | - | c) | 44177.1613
[9 empty] | d) | 365 CD | d) | -
|  |  | Tagaytay - Buan |  |  | CBRMC | 4.92 | Contract | a) | 174230.1288 | a) | - | e) | - | a) | 174230.1288 | a) | - | c) | - | a) | - | Purchase Request # 19125346 (On process)
| 045 | [7 empty] | b) | - | b) | - | f) | - | b) | 174230.1288 | b) | - | d) | - | b) | -
[9 empty] | c) | - | c) | - | g) | - | c) | -
[9 empty] | d) | - | d) | -
|  |  | Limbaan - Sto. Niño |  |  | Road Maintenance | 3.19 | Admin | a) | 195716.6763 | a) | 2020-01-02 | e) | - | a) | 195716.6763 | a) | 6.90% | c) | 6.90% | a) | 17 | On-going
| 049 | [7 empty] | b) | Crucio | b) | 2020-01-02 | f) | - | b) | 195716.6763 | b) | - | d) | - | b) | 374
[9 empty] | c) | PEO | c) | 2020-12-31 | g) | - | c) | 13504.4507
[9 empty] | d) | 365 CD | d) | -
|  |  | Limbaan - Sto. Niño |  |  | CBRMC | 3.19 | Contract | a) | 127140.9048 | a) | - | e) | - | a) | 127140.9048 | a) | - | c) | - | a) | - | Purchase Request # 20010072 (On process)
| 049 | [7 empty] | b) | - | b) | - | f) | - | b) | 127140.9048 | b) | - | d) | - | b) | -
[9 empty] | c) | - | c) | - | g) | - | c) | -
[9 empty] | d) | - | d) | -
|  |  | Jct. Monte Carlo - Upper Cabaywa - Canatan |  |  | Road Maintenance | 4.61 | Admin | a) | 285065.7818 | a) | 2020-01-02 | e) | - | a) | 285065.7818 | a) | 10.98% | c) | 10.98% | a) | 17 | On-going
| 050 | [7 empty] | b) | Crucio | b) | 2020-01-02 | f) | - | b) | 285065.7818 | b) | - | d) | - | b) | 374
[9 empty] | c) | PEO | c) | 2020-12-31 | g) | - | c) | 31300.2228
[9 empty] | d) | 365 CD | d) | -
|  |  | Jct. Monte Carlo - Upper Cabaywa - Canatan |  |  | CBRMC | 4.61 | Contract | a) | 197774.7408 | a) | - | e) | - | a) | 197774.7408 | a) | - | c) | - | a) | - | Purchase Request # 20010074 (On process)
| 050 | [7 empty] | b) | - | b) | - | f) | - | b) | 197774.7408 | b) | - | d) | - | b) | -
[9 empty] | c) | - | c) | - | g) | - | c) | -
[9 empty] | d) | - | d) | -
|  |  | Del Pilar - Jct. Silangan |  |  | Road Maintenance | 4.17 | Admin | a) | 337766.1689 | a) | 2020-01-02 | e) | - | a) | 337766.1689 | a) | 5.54% | c) | 5.54% | a) | 17 | On-going
| 051 | [7 empty] | b) | Crucio | b) | 2020-01-02 | f) | - | b) | 337766.1689 | b) | - | d) | - | b) | 374
[9 empty] | c) | PEO | c) | 2020-12-31 | g) | - | c) | 18712.2458
[9 empty] | d) | 365 CD | d) | -
|  |  | Del Pilar - Jct. Silangan |  |  | CBRMC | 4.17 | Contract | a) | 129495.366 | a) | - | e) | - | a) | 129495.366 | a) | - | c) | - | a) | - | Purchase Request # 20010093 (On process)
| 051 | [7 empty] | b) | - | b) | - | f) | - | b) | 129495.366 | b) | - | d) | - | b) | -
[9 empty] | c) | - | c) | - | g) | - | c) | -
[9 empty] | d) | - | d) | -
|  |  | New Corella - New Sambog - Silangan |  |  | Road Maintenance | 5.1 | Admin | a) | 371450.8414 | a) | 2020-01-02 | e) | - | a) | 371450.8414 | a) | 8.7% | c) | 8.7% | a) | 17 | On-going
| 052 | [7 empty] | b) | Crucio | b) | 2020-01-02 | f) | - | b) | 371450.8414 | b) | - | d) | - | b) | 374
[9 empty] | c) | PEO | c) | 2020-12-31 | g) | - | c) | 32316.2232
[9 empty] | d) | 365 CD | d) | -
|  |  | New Corella - New Sambog - Silangan |  |  | CBRMC | 5.1 | Contract | a) | 148331.0556 | a) | - | e) | - | a) | 148331.0556 | a) | - | c) | - | a) | - | Purchase Request # 20010095 (On process)
| 052 | [7 empty] | b) | - | b) | - | f) | - | b) | 148331.0556 | b) | - | d) | - | b) | -
[9 empty] | c) | - | c) | - | g) | - | c) | -
[9 empty] | d) | - | d) | -
|  |  | Pob. New Corella - Prk. 10 Pob. |  |  | Road Maintenance | 1.3 | Admin | a) | 28149.3653 | a) | 2020-01-02 | e) | - | a) | 28149.3653 | a) | 13.38% | c) | 13.38% | a) | 17 | On-going
| 053 | [7 empty] | b) |  | b) |  | f) | - | b) | 28149.3653 | b) | - | d) | - | b) | 374
[9 empty] | c) | PEO | c) | - | g) | - | c) | -
[9 empty] | d) | - | d) | -
|  |  | Pob. New Corella - Prk. 10 Pob. |  |  | CBRMC | 1.3 | Contract | a) | 21190.1508 | a) | - | e) | - | a) | 21190.1508 | a) | - | c) | - | a) | - | Purchase Request # 20010155 (On process)
| 053 | [7 empty] | b) | - | b) | - | f) | - | b) | 21190.1508 | b) | - | d) | - | b) | -
[9 empty] | c) | - | c) | - | g) | - | c) | -
[9 empty] | d) | - | d) | -
|  |  | Prk. 7 Pob. - Jct. New Sambog |  |  | Road Maintenance | 2.54 | Admin | a) | 171600.7916 | a) | 2020-01-02 | e) | - | a) | 171600.7916 | a) | 6.92% | c) | 6.92% | a) | 17 | On-going
| 054 | [7 empty] | b) | Crucio | b) | 2020-01-02 | f) | - | b) | 171600.7916 | b) | - | d) | - | b) | 374
[9 empty] | c) | PEO | c) | 2020-12-31 | g) | - | c) | 11874.7748
[9 empty] | d) | 365 CD | d) | -
|  |  | Prk. 7 Pob. - Jct. New Sambog |  |  | CBRMC | 2.54 | Contract | a) | 113014.1376 | a) | - | e) | - | a) | 113014.1376 | a) | - | c) | - | a) | - | Purchase Request # 20010158 (On process)
| 054 | [7 empty] | b) | - | b) | - | f) | - | b) | 113014.1376 | b) | - | d) | - | b) | -
[9 empty] | c) | - | c) | - | g) | - | c) | -
[9 empty] | d) | - | d) | -
|  |  | Sta. Fe - Del Monte |  |  | Road Maintenance | 3.34 | Admin | a) | 93676.7241 | a) | 2020-01-02 | e) | - | a) | 93676.7241 | a) | 11.64% | c) | 11.64% | a) | 17 | On-going
| 056 | [7 empty] | b) | Crucio | b) | 2020-01-02 | f) | - | b) | 93676.7241 | b) | - | d) | - | b) | 374
[9 empty] | c) | PEO | c) | 2020-12-31 | g) | - | c) | 10903.9707
[9 empty] | d) | 365 CD | d) | -
|  |  | Sta. Fe - Del Monte |  |  | CBRMC | 3.34 | Contract | a) | 75342.7584 | a) | - | e) | - | a) | 75342.7584 | a) | - | c) | - | a) | - | Purchase Request # 20010160 (On process)
| 056 | [7 empty] | b) | - | b) | - | f) | - | b) | 75342.7584 | b) | - | d) | - | b) | -
[9 empty] | c) | - | c) | - | g) | - | c) | -
[9 empty] | d) | - | d) | -
|  |  | New Corella - New Bohol |  |  | Road Maintenance | 11.54 | Admin | a) | 300034.9027 | a) | 2020-01-02 | e) | - | a) | 300034.9027 | a) | 11.09% | c) | 11.09% | a) | 17 | On-going
| 058 | [7 empty] | b) | Crucio | b) | 2020-01-02 | f) | - | b) | 300034.9027 | b) | - | d) | - | b) | 374
[9 empty] | c) | PEO | c) | 2020-12-31 | g) | - | c) | 33273.8707
[9 empty] | d) | 365 CD | d) | -
|  |  | New Corella - New Bohol |  |  | CBRMC | 11.54 | Contract | a) | 221319.3528 | a) | - | e) | - | a) | 221319.3528 | a) | - | c) | - | a) | - | Purchase Request # 20010221 (On process)
| 058 | [7 empty] | b) | - | b) | - | f) | - | b) | 221319.3528 | b) | - | d) | - | b) | -
[9 empty] | c) | - | c) | - | g) | - | c) | -
[9 empty] | d) | - | d) | -
|  |  | Jct. Carcor - Prk. 9 Bagsak |  |  | Road Maintenance | 2.5 | Admin | a) | 161961.791 | a) | 2020-01-02 | e) | - | a) | 161961.791 | a) | 8.06% | c) | 8.06% | a) | 17 | On-going
| 059 | [7 empty] | b) | Crucio | b) | 2020-01-02 | f) | - | b) | 161961.791 | b) | - | d) | - | b) | 374
[9 empty] | c) | PEO | c) | 2020-12-31 | g) | - | c) | 13054.1204
[9 empty] | d) | 365 CD | d) | -
|  |  | Jct. Carcor - Prk. 9 Bagsak |  |  | CBRMC | 2.5 | Contract | a) | 72988.2972 | a) | - | e) | - | a) | 72988.2972 | a) | - | c) | - | a) | - | Purchase Request # 20010223 (On process)
| 059 | [7 empty] | b) | - | b) | - | f) | - | b) | 72988.2972 | b) | - | d) | - | b) | -
[9 empty] | c) | - | c) | - | g) | - | c) | -
[9 empty] | d) | - | d) | -
|  |  | Carcor - Jct. Kauswagan |  |  | Road Maintenance | 4.32 | Admin | a) | 304751.9237 | a) | 2020-01-02 | e) | - | a) | 304751.9237 | a) | 13.63% | c) | 13.63% | a) | 17 | On-going
| 060 | [7 empty] | b) | Crucio | b) | 2020-01-02 | f) | - | b) | 304751.9237 | b) | - | d) | - | b) | 374
[9 empty] | c) | PEO | c) | 2020-12-31 | g) | - | c) | 41537.6872
[9 empty] | d) | 365 CD | d) | -
|  |  | Carcor - Jct. Kauswagan |  |  | CBRMC | 4.32 | Contract | a) | 101241.8316 | a) | - | e) | - | a) | 101241.8316 | a) | - | c) | - | a) | - | Purchase Request # 20010262 (On process)
| 060 | [7 empty] | b) | - | b) | - | f) | - | b) | 101241.8316 | b) | - | d) | - | b) | -
[9 empty] | c) | - | c) | - | g) | - | c) | -
[9 empty] | d) | - | d) | -
|  |  | Del Pilar - Prk. 9 Bagsak - San Jose |  |  | Road Maintenance | 4.32 | Admin | a) | 253106.9161 | a) | 2020-01-02 | e) | - | a) | 253106.9161 | a) | 7.88% | c) | 7.88% | a) | 17 | On-going
| 061 | [7 empty] | b) | Crucio | b) | 2020-01-02 | f) | - | b) | 253106.9161 | b) | - | d) | - | b) | 374
[9 empty] | c) | PEO | c) | 2020-12-31 | g) | - | c) | 19944.825
[9 empty] | d) | 365 CD | d) | -
|  |  | Del Pilar - Prk. 9 Bagsak - San Jose |  |  | CBRMC | 4.32 | Contract | a) | 251927.3484 | a) | - | e) | - | a) | 251927.3484 | a) | - | c) | - | a) | - | Purchase Request # 20010264 (On process)
| 061 | [7 empty] | b) | - | b) | - | f) | - | b) | 251927.3484 | b) | - | d) | - | b) | -
[9 empty] | c) | - | c) | - | g) | - | c) | -
[9 empty] | d) | - | d) | -
|  |  | Del Pilar - El Unido |  |  | Road Maintenance | 1.32 | Admin | a) | 84027.808 | a) | 2020-01-02 | e) | - | a) | 84027.808 | a) | 10.78% | c) | 10.78% | a) | 17 | On-going
| 062 | [7 empty] | b) | Crucio | b) | 2020-01-02 | f) | - | b) | 84027.808 | b) | - | d) | - | b) | 374
[9 empty] | c) | PEO | c) | 2020-12-31 | g) | - | c) | 9058.1977
[9 empty] | d) | 365 CD | d) | -
|  |  | Del Pilar - El Unido |  |  | CBRMC | 1.32 | Contract | a) | 40025.8404 | a) | - | e) | - | a) | 40025.8404 | a) | - | c) | - | a) | - | Purchase Request # 20010265 (On process)
| 062 | [7 empty] | b) | - | b) | - | f) | - | b) | 40025.8404 | b) | - | d) | - | b) | -
[9 empty] | c) | - | c) | - | g) | - | c) | -
[9 empty] | d) | - | d) | -
|  |  | San Juan - New Talisay |  |  | Road Maintenance | 5.13 | Admin | a) | 442982.6933 | a) | 2020-01-02 | e) | - | a) | 442982.6933 | a) | 13.42% | c) | 13.42% | a) | 17 | On-going
| 063 | [7 empty] | b) | Crucio | b) | 2020-01-02 | f) | - | b) | 442982.6933 | b) | - | d) | - | b) | 374
[9 empty] | c) | PEO | c) | 2020-12-31 | g) | - | c) | 59448.2774
[9 empty] | d) | 365 CD | d) | -
|  |  | San Juan - New Talisay |  |  | CBRMC | 5.13 | Contract | a) | 131849.8272 | a) | - | e) | - | a) | 131849.8272 | a) | - | c) | - | a) | - | Purchase Request # 20010267 (On process)
| 063 | [7 empty] | b) | - | b) | - | f) | - | b) | 131849.8272 | b) | - | d) | - | b) | -
[9 empty] | c) | - | c) | - | g) | - | c) | -
[9 empty] | d) | - | d) | -
|  |  | San Juan - Kauswagan - New Cortez |  |  | Road Maintenance | 3.22 | Admin | a) | 60690.1506 | a) | 2020-01-02 | e) | - | a) | 60690.1506 | a) | 5.26% | c) | 5.26% | a) | 17 | On-going
| 064 | [7 empty] | b) | Crucio | b) | 2020-01-02 | f) | - | b) | 60690.1506 | b) | - | d) | - | b) | 374
[9 empty] | c) | PEO | c) | 2020-12-31 | g) | - | c) | 3192.3019
[9 empty] | d) | 365 CD | d) | -
|  |  | San Juan - Kauswagan - New Cortez |  |  | CBRMC | 3.22 | Contract | a) | 68279.3748 | a) | - | e) | - | a) | 68279.3748 | a) | - | c) | - | a) | - | Procurement on process
| 064 | [7 empty] | b) | - | b) | - | f) | - | b) | 68279.3748 | b) | - | d) | - | b) | -
[9 empty] | c) | - | c) | - | g) | - | c) | 8108.51
[9 empty] | d) | - | d) | -
|  |  | New Bohol - Jct. El Unido |  |  | Road Maintenance | 2.12 | Admin | a) | 111335.8968 | a) | 2020-01-02 | e) | - | a) | 111335.8968 | a) | 8.16% | c) | 8.16% | a) | 17 | On-going
| 065 | [7 empty] | b) | Crucio | b) | 2020-01-02 | f) | - | b) | 111335.8968 | b) | - | d) | - | b) | 374
[9 empty] | c) | PEO | c) | 2020-12-31 | g) | - | c) | 9085.0092
[9 empty] | d) | 365 CD | d) | -
|  |  | New Bohol - Jct. El Unido |  |  | CBRMC | 2.12 | Contract | a) | 65924.9136 | a) | - | e) | - | a) | 65924.9136 | a) | - | c) | - | a) | - | Purchase Request # 20010275 (On process)
| 065 | [7 empty] | b) | - | b) | - | f) | - | b) | 65924.9136 | b) | - | d) | - | b) | -
[9 empty] | c) | - | c) | - | g) | - | c) | -
[9 empty] | d) | - | d) | -
|  |  | New Corella - El Unido - Jct. Mesaoy |  |  | Road Maintenance | 8.63 | Admin | a) | 542859.5597 | a) | 2020-01-02 | e) | - | a) | 542859.5597 | a) | 3.48% | c) | 3.48% | a) | 17 | On-going
| 066 | [7 empty] | b) | Crucio | b) | 2020-01-02 | f) | - | b) | 542859.5597 | b) | - | d) | - | b) | 374
[9 empty] | c) | PEO | c) | 2020-12-31 | g) | - | c) | 18891.5127
[9 empty] | d) | 365 CD | d) | -
|  |  | New Corella - El Unido - Jct. Mesaoy |  |  | CBRMC | 8.63 | Contract | a) | 249572.8872 | a) | - | e) | - | a) | 249572.8872 | a) | - | c) | - | a) | - | Purchase Request # 20010291 (On process)
| 066 | [7 empty] | b) | - | b) | - | f) | - | b) | 249572.8872 | b) | - | d) | - | b) | -
[9 empty] | c) | - | c) | - | g) | - | c) | -
[9 empty] | d) | - | d) | -
|  |  | Mesaoy - Dasing |  |  | Road Maintenance | 1.39 | Admin | a) | 76479.645 | a) | 2020-01-02 | e) | - | a) | 76479.645 | a) | 7.01% | c) | 7.01% | a) | 17 | On-going
| 067 | [7 empty] | b) | Crucio | b) | 2020-01-02 | f) | - | b) | 76479.645 | b) | - | d) | - | b) | 374
[9 empty] | c) | PEO | c) | 2020-12-31 | g) | - | c) | 5361.2231
[9 empty] | d) | 365 CD | d) | -
|  |  | Mesaoy - Dasing |  |  | CBRMC | 1.39 | Contract | a) | 54152.6076 | a) | - | e) | - | a) | 54152.6076 | a) | - | c) | - | a) | - | Purchase Request # 20010294 (On process)
| 067 | [7 empty] | b) | - | b) | - | f) | - | b) | 54152.6076 | b) | - | d) | - | b) | -
[9 empty] | c) | - | c) | - | g) | - | c) | -
[9 empty] | d) | - | d) | -
|  |  | Jct. San Juan - Jct. Mesaoy |  |  | Road Maintenance | 1.82 | Admin | a) | 135657.3072 | a) | 2020-01-02 | e) | - | a) | 135657.3072 | a) | 7.32% | c) | 7.32% | a) | 17 | On-going
| 068 | [7 empty] | b) | Crucio | b) | 2020-01-02 | f) | - | b) | 135657.3072 | b) | - | d) | - | b) | 374
[9 empty] | c) | PEO | c) | 2020-12-31 | g) | - | c) | 9930.1149
[9 empty] | d) | 365 CD | d) | -
|  |  | Jct. San Juan - Jct. Mesaoy |  |  | CBRMC | 1.82 | Contract | a) | 68279.3748 | a) | - | e) | - | a) | 68279.3748 | a) | - | c) | - | a) | - | Purchase Request # 20010294 (On process)
| 068 | [7 empty] | b) | - | b) | - | f) | - | b) | 68279.3748 | b) | - | d) | - | b) | -
[9 empty] | c) | - | c) | - | g) | - | c) | -
[9 empty] | d) | - | d) | -
|  |  | Mesaoy - New Bohol |  |  | Road Maintenance | 5.36 | Admin | a) | 404322.6481 | a) | 2020-01-02 | e) | - | a) | 404322.6481 | a) | 6.37% | c) | 6.37% | a) | 17 | On-going
| 070 | [7 empty] | b) | Crucio | b) | 2020-01-02 | f) | - | b) | 404322.6481 | b) | - | d) | - | b) | 374
[9 empty] | c) | PEO | c) | 2020-12-31 | g) | - | c) | 25755.3527
[9 empty] | d) | 365 CD | d) | -
|  |  | Mesaoy - New Bohol |  |  | CBRMC | 5.36 | Contract | a) | 261345.1932 | a) | - | e) | - | a) | 261345.1932 | a) | - | c) | - | a) | - | Purchase Request # 20010298 (On process)
| 070 | [7 empty] | b) | - | b) | - | f) | - | b) | 261345.1932 | b) | - | d) | - | b) | -
[9 empty] | c) | - | c) | - | g) | - | c) | -
[9 empty] | d) | - | d) | -
|  |  | Prk. 1, Maunlom-Prk. 6 Maunlom Road |  |  | Road Maintenance | 3.56 | Admin | a) | 49887.4041 | a) | 2020-01-02 | e) | - | a) | 49887.4041 | a) | 7.34% | c) | 7.34% | a) | 17 | On-going
| 147 | [7 empty] | b) |  | b) |  | f) | - | b) | 49887.4041 | b) | - | d) | - | b) | 374
[9 empty] | c) | PEO | c) | - | g) | - | c) | 3661.7355
[9 empty] | d) | - | d) | -
|  |  | Prk. 1, Maunlom-Prk. 6 Maunlom Road |  |  | CBRMC | 3.56 | Contract | a) | 65924.9136 | a) | - | e) | - | a) | 65924.9136 | a) | - | c) | - | a) | - | Purchase Request # 20010302 (On process)
| 147 | [7 empty] | b) | - | b) | - | f) | - | b) | 65924.9136 | b) | - | d) | - | b) | -
[9 empty] | c) | - | c) | - | g) | - | c) | -
[9 empty] | d) | - | d) | -
|  |  | New Visayas - Binancian |  |  | Road Maintenance | 7.774 | Admin | a) | 62394.7204 | a) | 2020-01-02 | e) | - | a) | 62394.7204 | a) | 3.47% | c) | 3.47% | a) | 17 | On-going
| 149 | [7 empty] | b) |  | b) |  | f) | - | b) | 62394.7204 | b) | - | d) | - | b) | 374
[9 empty] | c) | PEO | c) | - | g) | - | c) | 2165.0968
[9 empty] | d) | - | d) | -
|  |  | New Visayas - Binancian |  |  | CBRMC | 7.774 | Contract | a) | 134204.2884 | a) | - | e) | - | a) | 134204.2884 | a) | - | c) | - | a) | - | Purchase Request # 20010305 (On process)
| 149 | [7 empty] | b) | - | b) | - | f) | - | b) | 134204.2884 | b) | - | d) | - | b) | -
[9 empty] | c) | - | c) | - | g) | - | c) | -
[9 empty] | d) | - | d) | -
|  |  | Datu Balong - Prk. Mamalian |  |  | Road Maintenance | 3.46 | Admin | a) | 45089.8864 | a) | 2020-01-02 | e) | - | a) | 45089.8864 | a) | 3.47% | c) | 3.47% | a) | 17 | On-going
| 150 | [7 empty] | b) |  | b) |  | f) | - | b) | 45089.8864 | b) | - | d) | - | b) | 374
[9 empty] | c) | PEO | c) | - | g) | - | c) | 1564.6191
[9 empty] | d) | - | d) | -
|  |  | Datu Balong - Prk. Mamalian |  |  | CBRMC | 3.46 | Contract | a) | 61215.9912 | a) | - | e) | - | a) | 61215.9912 | a) | - | c) | - | a) | - | Purchase Request # 20010306 (On process)
| 150 | [7 empty] | b) | - | b) | - | f) | - | b) | 61215.9912 | b) | - | d) | - | b) | -
[9 empty] | c) | - | c) | - | g) | - | c) | -
[9 empty] | d) | - | d) | -
| Road ID |  | 2. Maintenance Of Various Prov'l. Roads and Bridges 2 |  |  |  | 288.26 |  | a) | 11801752 | [12 empty] | See list of Provincial Roads
[9 empty] | b) | Matuguinas
| 11DAN | [7 empty] | c) | PEO
[9 empty] | d) | 261 days
|  |  | Cebulano - Mangalcal |  |  | Road Maintenance | 4.17 | MBA | a) | 134,672.70 | a) | 2020-01-02 | e) | 134,672.70 | a) |  | a) | 14% | c) | 20% | a) | 64 | On-going
| 073 | [7 empty] | b) | Gamad/Clar | b) | 2020-01-02 | f) | 134,672.70 | b) |  | b) |  | d) |  | b) | 1280
[9 empty] | c) | Admin | c) | 2020-12-31 | g) |  | c)
[9 empty] | d) | 1 year | d)
|  |  | Cebulano - Mangalcal |  |  | Road Maintenance | 4.17 | CBRMC | a) | 131,004.66 | a) |  | e) | 131,004.66 | a) |  | a) |  | c) |  | a) |  | Purchase Order # 2020030966 (Brgy. Mangalcal Women's Household)
| 073 | [7 empty] | b) | Maligro | b) |  | f) | 131,004.66 | b) |  | b) |  | d) |  | b)
[9 empty] | c) |  | c) |  | g) |  | c)
[9 empty] | d) | 6 months | d)
|  |  | Tubod - basa - Mangalcal |  |  | Road Maintenance | 3.93 | MBA | a) | 143530.25 | a) | 2020-01-02 | e) | 143530.25 | a) |  | a) | 16% | c) | 20% | a) | 3 | On-going
| 074 | [7 empty] | b) | Gamad/Clar | b) | 2020-01-02 | f) | 143530.25 | b) |  | b) |  | d) |  | b) | 66
[9 empty] | c) | Admin | c) | 2020-12-31 | g) |  | c)
[9 empty] | d) | 1 year | d) |  | `
|  |  | Tubod - basa - Mangalcal |  |  | Road Maintenance | 3.93 | CBRMC | a) | 106,856.33 | a) |  | e) | 106,856.33 | a) |  | a) |  | c) |  | a) |  | Purchase Order # 2020030985 (Tubod Centro Lower Irrigator's Association)
| 074 | [7 empty] | b) | Maligro | b) |  | f) | 106,856.33 | b) |  | b) |  | d) |  | b)
[9 empty] | c) |  | c) |  | g) |  | c)
[9 empty] | d) | 6 months | d)
|  |  | Upper Mangalcal - Lower Mangalcal |  |  | Road Maintenance | 2.43 | MBA | a) | 82,374.21 | a) | 2020-01-02 | e) | 82,374.21 | a) |  | a) | 16% | c) | 20% | a) | 3 | On-going
| 078 | [7 empty] | b) | Gamad/Clar | b) | 2020-01-02 | f) | 82,374.21 | b) |  | b) |  | d) |  | b) | 66
[9 empty] | c) | Admin | c) | 2020-12-31 | g) |  | c)
[9 empty] | d) | 1 year | d)
|  |  | Upper Mangalcal - Lower Mangalcal |  |  | Road Maintenance | 2.43 | CBRMC | a) | 72444.97 | a) |  | e) | 72444.97 | a) |  | a) |  | c) |  | a) |  | Purchase Order # 2020030948 (Brgy. Mangalcal Women's Homebased Association)
| 078 | [7 empty] | b) | Maligro | b) |  | f) | 72444.97 | b) |  | b) |  | d) |  | b)
[9 empty] | c) |  | c) |  | g) |  | c)
[9 empty] | d) | 6 months | d)
|  |  | Cebulano - Loceta |  |  | Road Maintenance |  | MBA | a) | 72051.43 | a) | 2020-01-02 | e) | 72051.43 | a) |  | a) | 16% | c) | 20% | a) | 3 | On-going
| 079 | [7 empty] | b) | Gamad/Clar | b) | 2020-01-02 | f) | 72051.43 | b) |  | b) |  | d) |  | b) | 66
[9 empty] | c) | Admin | c) | 2020-12-31 | g) |  | c)
[9 empty] | d) | 1 year | d)
|  |  | Cebulano - Loceta |  |  | Road Maintenance |  | CBRMC | a) | 47089.26 | a) |  | e) | 47089.26 | a) |  | a) |  | c) |  | a) |  | Purchase Order # 2020030965 (Brgy. Mangalcal Women's Homebased Association)
| 079 | [7 empty] | b) | Maligro | b) |  | f) | 47089.26 | b) |  | b) |  | d) |  | b)
[9 empty] | c) |  | c) |  | g) |  | c)
[9 empty] | d) | 6 months | d)
|  |  | Jct. Highway Carmen - Mangalcal - Tubod |  |  | Road Maintenance | 11.34 | MBA | a) | 462895.06 | a) | 2020-01-02 | e) | 462895.06 | a) |  | a) | 16% | c) | 17% | a) | 4 | On-going
| 082 | [7 empty] | b) | Gamad/Clar | b) | 2020-01-02 | f) | 462895.06 | b) |  | b) |  | d) |  | b) | 88
[9 empty] | c) | Admin | c) | 2020-12-31 | g) |  | c)
[9 empty] | d) | 1 year | d)
|  |  | Jct. Highway Carmen - Mangalcal - Tubod |  |  | Road Maintenance | 11.34 | CBRMC | a) | 259594.46 | a) |  | e) | 259594.46 | a) |  | a) |  | c) |  | a) |  | Abstract # 0320201443
| 082 | [7 empty] | b) | Maligro | b) |  | f) | 259594.46 | b) |  | b) |  | d) |  | b)
[9 empty] | c) |  | c) |  | g) |  | c)
[9 empty] | d) | 6 months | d)
|  |  | Ising - Sadpodon - Taba - Dila -Dila |  |  | Road Maintenance | 5.68 | MBA | a) | 226651.27 | a) | 2020-01-02 | e) | 226651.27 | a) |  | a) | 16% | c) | 16% | a) | 3
| 086 | [7 empty] | b) | Gamad/Clar | b) | 2020-01-02 | f) | 226651.27 | b) |  | b) |  | d) |  | b) | 66 | On-going
[9 empty] | c) | Admin | c) | 2020-12-31 | g) |  | c)
[9 empty] | d) | 1 year | d)
|  |  | Ising - Sadpodon - Taba - Dila -Dila |  |  | Road Maintenance | 5.68 | CBRMC | a) | 135230.61 | a) |  | e) | 135230.61 | a) |  | a) |  | c) |  | a) |  | Abstract # 0320201448
| 086 | [7 empty] | b) | Maligro | b) |  | f) | 135230.61 | b) |  | b) |  | d) |  | b)
[9 empty] | c) |  | c) |  | g) |  | c)
[9 empty] | d) | 6 months | d)
|  |  | Tuganay - taba |  |  | Road Maintenance | 4.27 | MBA | a) | 169418.15 | a) | 2020-01-02 | e) | 169418.15 | a) |  | a) | 15% | c) | 16% | a) | 3 | On-going
| 087 | [7 empty] | b) | Gamad/Clar | b) | 2020-01-02 | f) | 169418.15 | b) |  | b) |  | d) |  | b) | 66
[9 empty] | c) | Admin | c) | 2020-12-31 | g) |  | c)
[9 empty] | d) | 1 year | d)
|  |  | Tuganay - taba |  |  | Road Maintenance | 4.27 | CBRMC | a) | 102630.37 | a) |  | e) | 102630.37 | a) |  | a) |  | c) |  | a) |  | Abstract # 0320201446
| 087 | [7 empty] | b) | Maligro | b) |  | f) | 102630.37 | b) |  | b) |  | d) |  | b)
[9 empty] | c) |  | c) |  | g) |  | c)
[9 empty] | d) | 6 months | d)
|  |  | Jct. Highway Tuganay - Taba |  |  | Road Maintenance | 4.4 | MBA | a) | 222375.04 | a) | 2020-01-02 | e) | 222375.04 | a) |  | a) | 16% | c) | 16% | a) | 3 | On-going
| 088 | [7 empty] | b) | Gamad/Clar | b) | 2020-01-02 | f) | 222375.04 | b) |  | b) |  | d) |  | b) | 66
[9 empty] | c) | Admin | c) | 2020-12-31 | g) |  | c)
[9 empty] | d) | 1 year | d)
|  |  | Jct. Highway Tuganay - Taba |  |  | Road Maintenance | 4.4 | CBRMC | a) | 57955.99 | a) |  | e) | 57955.99 | a) |  | a) |  | c) |  | a) |  | Purchase Order # 2020030976 (Ezra Christian Minsitry For Peace, Inc.)
| 088 | [7 empty] | b) | Maligro | b) |  | f) | 57955.99 | b) |  | b) |  | d) |  | b)
[9 empty] | c) |  | c) |  | g) |  | c)
[9 empty] | d) | 6 months | d)
|  |  | Jct. Highway Ising - Magsaysay |  |  | Road Maintenance | 10.84 | MBA | a) | 478128.48 | a) | 2020-01-02 | e) | 478128.48 | a) |  | a) | 15% | c) | 16% | a) | 3 | On-going
| 089 | [7 empty] | b) | Gamad/Clar | b) | 2020-01-02 | f) | 478128.48 | b) |  | b) |  | d) |  | b) | 66
[9 empty] | c) | Admin | c) | 2020-12-31 | g) |  | c)
[9 empty] | d) |  | d)
|  |  | Jct. Highway Ising - Magsaysay |  |  | Road Maintenance | 10.84 | CBRMC | a) | 212505.24 | a) |  | e) | 212505.24 | a) |  | a) |  | c) |  | a) |  | Purchase Order # 2020030969 (School in the Air Integrated Farmer's Associiation)
| 089 | [7 empty] | b) | Maligro | b) |  | f) | 212505.24 | b) |  | b) |  | d) |  | b)
[9 empty] | c) |  | c) |  | g) |  | c)
[9 empty] | d) | 6 months | d)
|  |  | Maligaya - New Camiling |  |  | Road Maintenance |  | MBA | a) | 51790.26 | a) | 2020-01-02 | e) | 51790.26 | a) |  | a) | 16% | c) | 16% | a) | 3 | On-going
| 090 | [7 empty] | b) | Gamad/Clar | b) | 2020-01-02 | f) | 51790.26 | b) |  | b) |  | d) |  | b) | 66
[9 empty] | c) | Admin | c) | 2020-12-31 | g) |  | c)
[9 empty] | d) | 1 year | d)
|  |  | Maligaya - New Camiling |  |  | Road Maintenance |  | CBRMC | a) | 83915.44 | a) |  | e) | 83915.44 | a) |  | a) |  | c) |  | a) |  | Purchase Order # 2020030967 (School in the Air Integrated Farmer's Associiation)
| 090 | [7 empty] | b) | Maligro | b) |  | f) | 83915.44 | b) |  | b) |  | d) |  | b)
[9 empty] | c) |  | c) |  | g) |  | c)
[9 empty] | d) | 9 months | d)
|  |  | New Camiling - Alejal - Lower Magsaysay |  |  | Road Maintenance | 6.73 | MBA | a) | 277852.05 | a) | 2020-01-02 | e) | 277852.05 | a) |  | a) | 16% | c) | 16% | a) | 3 | On-going
| 091 | [7 empty] | b) | Gamad/Clar | b) | 2020-01-02 | f) | 277852.05 | b) |  | b) |  | d) |  | b) | 66
[9 empty] | c) | Admin | c) | 2020-12-31 | g) |  | c)
[9 empty] | d) | 1 year | d)
|  |  | New Camiling - Alejal - Lower Magsaysay |  |  | Road Maintenance | 6.73 | CBRMC | a) | 150927.01 | a) |  | e) | 150927.01 | a) |  | a) |  | c) |  | a) |  | Purchase Order # 2020030970 (School in the Air Integrated Farmer's Associiation)
| 091 | [7 empty] | b) | Maligro | b) |  | f) | 150927.01 | b) |  | b) |  | d) |  | b)
[9 empty] | c) |  | c) |  | g) |  | c)
[9 empty] | d) | 6 months | d)
|  |  | Jct. highway Tuganay - Anibongan |  |  | Road Maintenance | 3.66 | MBA | a) | 139609.7 | a) | 2020-01-02 | e) | 139609.7 | a) |  | a) | 15% | c) | 16% | a) | 4 | On-going
| 094 | [7 empty] | b) | Gamad/Clar | b) | 2020-01-02 | f) | 139609.7 | b) |  | b) |  | d) |  | b) | 88
[9 empty] | c) | Admin | c) | 2020-12-31 | g) |  | c)
[9 empty] | d) | 1 year | d)
|  |  | Jct. highway Tuganay - Anibongan |  |  | Road Maintenance | 3.66 | CBRMC | a) | 93574.75 | a) |  | e) | 93574.75 | a) |  | a) |  | c) |  | a) |  | Purchase Order # 2020030977 (Ezra Christian Minsitry For Peace, Inc.)
| 094 | [7 empty] | b) | Maligro | b) |  | f) | 93574.75 | b) |  | b) |  | d) |  | b)
[9 empty] | c) |  | c) |  | g) |  | c)
[9 empty] | d) | 6 months | d)
|  |  | Anibongan - Guadalupe |  |  | Road Maintenance | 2.48 | MBA | a) | 85559.79 | a) | 2020-01-02 | e) | 85559.79 | a) |  | a) | 16% | c) | 17% | a) | 4 | On-going
| 095 | [7 empty] | b) | Gamad/Clar | b) | 2020-01-02 | f) | 85559.79 | b) |  | b) |  | d) |  | b) | 78
[9 empty] | c) | Admin | c) | 2020-12-31 | g) |  | c)
[9 empty] | d) | 1 year | d)
|  |  | Anibongan - Guadalupe |  |  | Road Maintenance | 2.48 | CBRMC | a) | 72444.97 | a) |  | e) | 72444.97 | a) |  | a) |  | c) |  | a) |  | Abstract # 0320201444
| 095 | [7 empty] | b) | Maligro | b) |  | f) | 72444.97 | b) |  | b) |  | d) |  | b)
[9 empty] | c) |  | c) |  | g) |  | c)
[9 empty] | d) | 6 months | d)
|  |  | Tuganay - Anibongan - San Isidro |  |  | Road Maintenance | 7.22 | MBA | a) | 344085.79 | a) | 2020-01-02 | e) | 344085.79 | a) |  | a) | 16% | c) | 17% | a) | 3 | On-going
| 096 | [7 empty] | b) | Gamad/Clar | b) | 2020-01-02 | f) | 344085.79 | b) |  | b) |  | d) |  | b) | 66
[9 empty] | c) | Admin | c) | 2020-12-31 | g) |  | c)
[9 empty] | d) | 1 year | d)
|  |  | Tuganay - Anibongan - San Isidro |  |  | Road Maintenance | 7.22 | CBRMC | a) | 115911.95 | a) |  | e) | 115911.95 | a) |  | a) |  | c) |  | a) |  | Purchase Order # 2020030975 (Ezra Christian Minsitry For Peace, Inc.)
| 096 | [7 empty] | b) | Maligro | b) |  | f) | 115911.95 | b) |  | b) |  | d) |  | b)
[9 empty] | c) |  | c) |  | g) |  | c)
[9 empty] | d) | 6 months | d)
|  |  | Jct. Anibongan - Prk. 2, 7, 5, San Isidro |  |  | Road Maintenance | 3.14 | MBA | a) | 89575.84 | a) | 2020-01-02 | e) | 89575.84 | a) |  | a) | 16% | c) | 17% | a) | 4 | On-going
| 097 | [7 empty] | b) | Gamad/Clar | b) | 2020-01-02 | f) | 89575.84 | b) |  | b) |  | d) |  | b) | 88
[9 empty] | c) | Admin | c) | 2020-12-31 | g) |  | c)
[9 empty] | d) | 1 year | d)
|  |  | Jct. Anibongan - Prk. 2, 7, 5, San Isidro |  |  | Road Maintenance | 3.14 | CBRMC | a) | 110478.58 | a) |  | e) | 110478.58 | a) |  | a) |  | c) |  | a) |  | Abstract # 0320201404
| 097 | [7 empty] | b) | Maligro | b) |  | f) | 110478.58 | b) |  | b) |  | d) |  | b)
[9 empty] | c) |  | c) |  | g) |  | c)
[9 empty] | d) | 6 months | d)
|  |  | Anibongan - Salvacion - Cabay-angan |  |  | Road Maintenance | 6.93 | MBA | a) | 279123.9 | a) | 2020-01-02 | e) | 279123.9 | a) |  | a) | 16% | c) | 18% | a) | 4 | On-going
| 098 | [7 empty] | b) | Gamad/Clar | b) | 2020-01-02 | f) | 279123.9 | b) |  | b) |  | d) |  | b) | 88
[9 empty] | c) | Admin | c) | 2020-12-31 | g) |  | c)
[9 empty] | d) |  | d)
|  |  | Anibongan - Salvacion - Cabay-angan |  |  | Road Maintenance | 6.93 | CBRMC | a) | 162397.48 | a) |  | e) | 162397.48 | a) |  | a) |  | c) |  | a) |  | Abstract # 0320201409
| 098 | [7 empty] | b) | Maligro | b) |  | f) | 162397.48 | b) |  | b) |  | d) |  | b)
[9 empty] | c) |  | c) |  | g) |  | c)
[9 empty] | d) | 6 months | d)
|  |  | Mabaus - Cabay - angan |  |  | Road Maintenance |  | MBA | a) | 113320.9 | a) | 2020-01-02 | e) | 113320.9 | a) |  | a) | 16% | c) | 18% | a) | 3 | On-going
| 099 | [7 empty] | b) | Gamad/Clar | b) | 2020-01-02 | f) | 113320.9 | b) |  | b) |  | d) |  | b) | 66
[9 empty] | c) | Admin | c) | 2020-12-31 | g) |  | c)
[9 empty] | d) |  | d)
|  |  | Mabaus - Cabay - angan |  |  | Road Maintenance |  | CBRMC | a) | 90556.21 | a) |  | e) | 90556.21 | a) |  | a) |  | c) |  | a)
| 099 | [7 empty] | b) | Maligro | b) |  | f) | 90556.21 | b) |  | b) |  | d) |  | b) |  | Bidding on process
[9 empty] | c) |  | c) |  | g) |  | c)
[9 empty] | d) | 6 months | d)
|  |  | Jct. Highway Guadalupe - Bdry. Tagum |  |  | Road Maintenance | 7.9 | MBA | a) | 517780.87 | a) | 2020-01-02 | e) | 517780.87 | a) |  | a) | 16% | c) | 18% | a) | 3 | On-going
| 101 | [7 empty] | b) | Gamad/Clar | b) | 2020-01-02 | f) | 517780.87 | b) |  | b) |  | d) |  | b) | 66
[9 empty] | c) | Admin | c) | 2020-12-31 | g) |  | c)
[9 empty] | d) | 9 months | d)
|  |  | Jct. Highway Guadalupe - Bdry. Tagum |  |  | Road Maintenance | 7.9 | CBRMC | a) | 231823.89 | a) |  | e) | 231823.89 | a) |  | a) |  | c) |  | a)
| 101 | [7 empty] | b) | Maligro | b) |  | f) | 231823.89 | b) |  | b) |  | d) |  | b) |  | Bidding on process
[9 empty] | c) |  | c) |  | g) |  | c)
[9 empty] | d) | 6 months | d)
|  |  | Dujali - Tanglaw |  |  | Road Maintenance |  | MBA | a) | 135183.27 | a) | 2020-01-02 | e) | 135183.27 | a) |  | a) | 15% | c) | 15% | a) | 3 | On-going
| 104 | [7 empty] | b) | Gamad/Clar | b) | 2020-01-02 | f) | 135183.27 | b) |  | b) |  | d) |  | b) | 66
[9 empty] | c) | Admin | c) | 2020-12-31 | g) |  | c)
[9 empty] | d) |  | d)
|  |  | Dujali - Tanglaw |  |  | Road Maintenance |  | CBRMC | a) | 94178.48 | a) |  | e) | 94178.48 | a) |  | a) |  | c) |  | a) |  | Purchase Order # 2020030948 (Dujali Poblacion Farmer's Irrigator's Association, Inc.)
| 104 | [7 empty] | b) | Maligro | b) |  | f) | 94178.48 | b) |  | b) |  | d) |  | b)
[9 empty] | c) |  | c) |  | g) |  | c)
[9 empty] | d) | 6 months | d)
|  |  | Poblacion Dujali - Prk. 8 Dujali |  |  | Road Maintenance | 8.2 | MBA | a) | 329064 | a) | 2020-01-02 | e) | 329064 | a) |  | a) | 15% | c) | 16% | a) | 3 | On-going
| 105 | [7 empty] | b) | Gamad/Clar | b) | 2020-01-02 | f) | 329064 | b) |  | b) |  | d) |  | b) | 66
[9 empty] | c) | Admin | c) | 2020-12-31 | g) |  | c)
[9 empty] | d) |  | d)
|  |  | Poblacion Dujali - Prk. 8 Dujali |  |  | Road Maintenance | 8.2 | CBRMC | a) | 193371.11 | a) |  | e) | 193371.11 | a) |  | a) |  | c) |  | a) |  | Purchase Order # 2020030981 (Dujali Poblacion Farmer's Irrigator's Association, Inc.)
| 105 | [7 empty] | b) | Maligro | b) |  | f) | 193371.11 | b) |  | b) |  | d) |  | b)
[9 empty] | c) |  | c) |  | g) |  | c)
[9 empty] | d) | 6 months | d)
|  |  | Dujali - San Isidro |  |  | Road Maintenance | 3 | MBA | a) | 112652.73 | a) | 2020-01-02 | e) | 112652.73 | a) |  | a) | 8% | c) | 10% | a) | 3 | On-going
| 107 | [7 empty] | b) | Gamad/Clar | b) | 2020-01-02 | f) | 112652.73 | b) |  | b) |  | d) | 2% | b) | 66
[9 empty] | c) | Admin | c) | 2020-12-31 | g) |  | c)
[9 empty] | d) |  | d)
|  |  | Dujali - San Isidro |  |  | Road Maintenance | 3 | CBRMC | a) | 78482.06 | a) |  | e) | 78482.06 | a) |  | a) |  | c) |  | a) |  | Abstract # 0320201451
| 107 | [7 empty] | b) | Maligro | b) |  | f) | 78482.06 | b) |  | b) |  | d) |  | b)
[9 empty] | c) |  | c) |  | g) |  | c)
[9 empty] | d) | 6 months | d)
|  |  | New Casay - Bugtong Talisay |  |  | Road Maintenance |  | MBA | a) | 74294.5 | a) | 2020-01-02 | e) | 74294.5 | a) |  | a) | 6% | c) | 10% | a) | 4 | On-going
| 108 | [7 empty] | b) | Gamad/Clar | b) | 2020-01-02 | f) | 74294.5 | b) |  | b) |  | d) | 4% | b) | 88
[9 empty] | c) | Admin | c) | 2020-12-31 | g) |  | c)
[9 empty] | d) | 1 year | d)
|  |  | New Casay - Bugtong Talisay |  |  | Road Maintenance |  | CBRMC | a) | 64596.78 | a) |  | e) | 64596.78 | a) |  | a) |  | c) |  | a)
| 108 | [7 empty] | b) | Maligro | b) |  | f) | 64596.78 | b) |  | b) |  | d) |  | b) |  | Bidded 2/20/2020
[9 empty] | c) |  | c) |  | g) |  | c)
[9 empty] | d) | 6 months | d)
|  |  | Dujali - Balisong - Magupising |  |  | Road Maintenance | 5.52 | MBA | a) | 235776.07 | a) | 2020-01-02 | e) | 235776.07 | a) |  | a) | 8% | c) | 7% | a) | 3 | On-going
| 113 | [7 empty] | b) | Gamad/Clar | b) | 2020-01-02 | f) | 235776.07 | b) |  | b) |  | d) | -1% | b) | 22
[9 empty] | c) | Admin | c) | 2020-12-31 | g) |  | c)
[9 empty] | d) | 1 year | d)
|  |  | Dujali - Balisong - Magupising |  |  | Road Maintenance | 5.52 | CBRMC | a) | 115911.95 | a) |  | e) | 115911.95 | a) |  | a) |  | c) |  | a) |  | Purchase Order # 2020030978 (Dujali Poblacion Farmer's Irrigator's Association, Inc.)
| 113 | [7 empty] | b) | Maligro | b) |  | f) | 115911.95 | b) |  | b) |  | d) |  | b)
[9 empty] | c) |  | c) |  | g) |  | c)
[9 empty] | d) | 9 months | d)
|  |  | Dujali - Pawas - San Vicente |  |  | Road Maintenance | 4.42 | MBA | a) | 141544.99 | a) | 2020-01-02 | e) | 141544.99 | a) |  | a) | 8% | c) | 7% | a) | 3 | On-going
| 117 | [7 empty] | b) | Gamad/Clar | b) | 2020-01-02 | f) | 141544.99 | b) |  | b) |  | d) | -1% | b) | 22
[9 empty] | c) | Admin | c) | 2020-12-31 | g) |  | c)
[9 empty] | d) | 1 year | d)
|  |  | Dujali - Pawas - San Vicente |  |  | Road Maintenance | 4.42 | CBRMC | a) | 140060.27 | a) |  | e) | 140060.27 | a) |  | a) |  | c) |  | a) |  | Bidding on process
| 117 | [7 empty] | b) | Maligro | b) |  | f) | 140060.27 | b) |  | b) |  | d) |  | b)
[9 empty] | c) |  | c) |  | g) |  | c)
[9 empty] | d) | 6 months | d)
|  |  | Jct. Salvacion - San Vicente - Cabay-angan |  |  | Road Maintenance | 3.45 | MBA | a) | 168583.81 | a) | 2020-01-02 | e) | 168583.81 | a) |  | a) | 10% | c) | 8% | a) | 3 | On-going
| 118 | [7 empty] | b) | Gamad/Clar | b) | 2020-01-02 | f) | 168583.81 | b) |  | b) |  | d) | -2% | b) | 60
[9 empty] | c) | Admin | c) | 2020-12-31 | g) |  | c)
[9 empty] | d) | 9 months | d)
|  |  | Jct. Salvacion - San Vicente - Cabay-angan |  |  | Road Maintenance | 3.45 | CBRMC | a) | 158775.23 | a) |  | e) | 158775.23 | a) |  | a) |  | c) |  | a) |  | Bidding on process
| 118 | [7 empty] | b) | Maligro | b) |  | f) | 158775.23 | b) |  | b) |  | d) |  | b)
[9 empty] | c) |  | c) |  | g) |  | c)
[9 empty] | d) | 6 months | d)
|  |  | Bacali - Casig-ang - Libertad |  |  | Road Maintenance |  | MBA | a) | 167836.14 | a) | 2020-01-02 | e) | 167836.14 | a) |  | a) | 10% | c) | 9% | a) | 3 | On-going
| 123 | [7 empty] | b) | Gamad/Clar | b) | 2020-01-02 | f) | 167836.14 | b) |  | b) |  | d) | -1% | b) | 60
[9 empty] | c) | Admin | c) | 2020-12-31 | g) |  | c)
[9 empty] | d) | 1 year | d)
|  |  | Bacali - Casig-ang - Libertad |  |  | Road Maintenance |  | CBRMC | a) | 131608.37 | a) |  | e) | 131608.37 | a) |  | a) |  | c) |  | a) |  | Bidding on process
| 123 | [7 empty] | b) | Maligro | b) |  | f) | 131608.37 | b) |  | b) |  | d) |  | b)
[9 empty] | c) |  | c) |  | g) |  | c)
[9 empty] | d) | 6 months | d)
|  |  | Kinamayan - Moslog - Mahayag |  |  | Road Maintenance |  | MBA | a) | 114628.54 | a) | 2020-01-02 | e) | 114628.54 | a) |  | a) | 10% | c) | 8% | a) | 3 | On-going
| 124 | [7 empty] | b) | Gamad/Clar | b) | 2020-01-02 | f) | 114628.54 | b) |  | b) |  | d) | -2% | b) | 66
[9 empty] | c) | Admin | c) | 2020-12-31 | g) |  | c)
[9 empty] | d) | 1 year | d)
|  |  | Kinamayan - Moslog - Mahayag |  |  | Road Maintenance |  | CBRMC | a) | 91159.92 | a) |  | e) | 91159.92 | a) |  | a) |  | c) |  | a)
| 124 | [7 empty] | b) | Maligro | b) |  | f) | 91159.92 | b) |  | b) |  | d) |  | b) |  | Bidding on process
[9 empty] | c) |  | c) |  | g) |  | c)
[9 empty] | d) | 6 months | d)
|  |  | Kinamayan - Lunga-og |  |  | Road Maintenance |  | MBA | a) | 100416.26 | a) | 2020-01-02 | e) | 100416.26 | a) |  | a) | 10% | c) | 8% | a) | 3 | On-going
| 126 | [7 empty] | b) | Gamad/Clar | b) | 2020-01-02 | f) | 100416.26 | b) |  | b) |  | d) | -2% | b) | 66
[9 empty] | c) | Admin | c) | 2020-12-31 | g) |  | c)
[9 empty] | d) | 1 year | d)
|  |  | Kinamayan - Lunga-og |  |  | Road Maintenance |  | CBRMC | a) | 64596.78 | a) |  | e) | 64596.78 | a) |  | a) |  | c) |  | a) |  | Purchase Order # 2020030971 (Lunga-og Tribal Association)
| 126 | [7 empty] | b) | Maligro | b) |  | f) | 64596.78 | b) |  | b) |  | d) |  | b)
[9 empty] | c) |  | c) |  | g) |  | c)
[9 empty] | d) | 6 months | d)
|  |  | Prk. Apitong - Upper Balisong - Dalisay |  |  | Road Maintenance | 4.6 | MBA | a) | 150598.24 | a) | 2020-01-02 | e) | 150598.24 | a) |  | a) | 10% | c) | 9% | a) | 3 | On-going
| 128 | [7 empty] | b) | Gamad/Clar | b) | 2020-01-02 | f) | 150598.24 | b) |  | b) |  | d) | -1% | b) | 60
[9 empty] | c) | Admin | c) | 2020-12-31 | g) |  | c)
[9 empty] | d) | 1 year | d)
|  |  | Prk. Apitong - Upper Balisong - Dalisay |  |  | Road Maintenance | 4.6 | CBRMC | a) | 142475.11 | a) |  | e) | 142475.11 | a) |  | a) |  | c) |  | a) |  | Purchase Order # 2020030946 (Lunga-og Tribal Association)
| 128 | [7 empty] | b) | Maligro | b) |  | f) | 142475.11 | b) |  | b) |  | d) |  | b)
[9 empty] | c) |  | c) |  | g) |  | c)
[9 empty] | d) | 6 months | d)
|  |  | Los Amigos 1 - Esperanza - Los Amigos 2 |  |  | Road Maintenance | 3.59 | MBA | a) | 97116.27 | a) | 2020-01-02 | e) | 97116.27 | a) |  | a) | 10% | c) | 12% | a) | 4 | On-going
| 130 | [7 empty] | b) | Gamad/Clar | b) | 2020-01-02 | f) | 97116.27 | b) |  | b) |  | d) | 2% | b) | 88
[9 empty] | c) | Admin | c) | 2020-12-31 | g) |  | c)
[9 empty] | d) | 1 year | d)
|  |  | Los Amigos 1 - Esperanza - Los Amigos 2 |  |  | Road Maintenance | 3.59 | CBRMC | a) | 131608.37 | a) |  | e) | 131608.37 | a) |  | a) |  | c) |  | a) |  | Abstract # 0320201348
| 130 | [7 empty] | b) | Maligro | b) |  | f) | 131608.37 | b) |  | b) |  | d) |  | b)
[9 empty] | c) |  | c) |  | g) |  | c)
[9 empty] | d) | 6 months | d)
|  |  | Mugas - Lanatad |  |  | Road Maintenance |  | MBA | a) | 65482.21 | a) | 2020-01-02 | e) | 65482.21 | a) |  | a) | 2% | c) | 3% | a) | 3 | On-going
| 131 | [7 empty] | b) | Gamad/Clar | b) | 2020-01-02 | f) | 65482.21 | b) |  | b) |  | d) | 1% | b) | 12
[9 empty] | c) | Admin | c) | 2020-12-31 | g) |  | c)
[9 empty] | d) |  | d)
|  |  | Mugas - Lanatad |  |  | Road Maintenance |  | CBRMC | a) | 31996.54 | a) |  | e) | 31996.54 | a) |  | a) |  | c) |  | a) |  | Purchase Order # 2020030961 (Katipunan Pantaron Irrigator's Association)
| 131 | [7 empty] | b) | Maligro | b) |  | f) | 31996.54 | b) |  | b) |  | d) |  | b)
[9 empty] | c) |  | c) |  | g) |  | c)
[9 empty] | d) | 6 months | d)
|  |  | Mugas - Lunga-og |  |  | Road Maintenance | 2.68 | MBA | a) | 96490.97 | a) | 2020-01-02 | e) | 96490.97 | a) |  | a) | 5% | c) | 3% | a) | 3 | On-going
| 132 | [7 empty] | b) | Gamad/Clar | b) | 2020-01-02 | f) | 96490.97 | b) |  | b) |  | d) | -2% | b) | 20
[9 empty] | c) | Admin | c) | 2020-12-31 | g) |  | c)
[9 empty] | d) |  | d)
|  |  | Mugas - Lunga-og |  |  | Road Maintenance | 2.68 | CBRMC | a) | 74256.11 | a) |  | e) | 74256.11 | a) |  | a) |  | c) |  | a) |  | Purchase Order # 2020030947 (Lunga-og Tribal Association)
| 132 | [7 empty] | b) | Maligro | b) |  | f) | 74256.11 | b) |  | b) |  | d) |  | b)
[9 empty] | c) |  | c) |  | g) |  | c)
[9 empty] | d) | 6 months | d)
|  |  | New Katipunan - Pantaron |  |  | Road Maintenance |  | MBA | a) | 71748.41 | a) | 2020-01-02 | e) | 71748.41 | a) |  | a) | 6% | c) | 3% | a) | 2 | On-going
| 134 | [7 empty] | b) | Gamad/Clar | b) | 2020-01-02 | f) | 71748.41 | b) |  | b) |  | d) | -3% | b) | 20
[9 empty] | c) | Admin | c) | 2020-12-31 | g) |  | c)
[9 empty] | d) |  | d)
|  |  | New Katipunan - Pantaron |  |  | Road Maintenance |  | CBRMC | a) | 53126.32 | a) |  | e) | 53126.32 | a) |  | a) |  | c) |  | a) |  | Purchase Order # 2020030964 (Katipunan Pantaron Irrigator's Association)
| 134 | [7 empty] | b) | Maligro | b) |  | f) | 53126.32 | b) |  | b) |  | d) |  | b)
[9 empty] | c) |  | c) |  | g) |  | c)
[9 empty] | d) | 6 months | d)
|  |  | Sto. Tomas - Bdry. Mamacao |  |  | Road Maintenance | 4.9 | MBA | a) | 195671.17 | a) | 2020-01-02 | e) | 195671.17 | a) |  | a) | 8% | c) | 6% | a) | 3 | On-going
| 135 | [7 empty] | b) | Gamad/Clar | b) | 2020-01-02 | f) | 195671.17 | b) |  | b) |  | d) | -2% | b) | 33
[9 empty] | c) | Admin | c) | 2020-12-31 | g) |  | c)
[9 empty] | d) |  | d)
|  |  | Sto. Tomas - Bdry. Mamacao |  |  | Road Maintenance | 4.9 | CBRMC | a) | 116515.66 | a) |  | e) | 116515.66 | a) |  | a) |  | c) |  | a) |  | Abstract # 0320301351
| 135 | [7 empty] | b) | Maligro | b) |  | f) | 116515.66 | b) |  | b) |  | d) |  | b)
[9 empty] | c) |  | c) |  | g) |  | c)
[9 empty] | d) | 6 months | d)
|  |  | Fd. Rd. 3 - San Jose |  |  | Road Maintenance | 4.55 | MBA | a) | 176994.35 | a) | 2020-01-02 | e) | 176994.35 | a) |  | a) | 6% | c) | 2% | a) | 2 | On-going
| 136 | [7 empty] | b) | Gamad/Clar | b) | 2020-01-02 | f) | 176994.35 | b) |  | b) |  | d) | -4% | b) | 10
[9 empty] | c) | Admin | c) | 2020-12-31 | g) |  | c)
[9 empty] | d) |  | d)
|  |  | Fd. Rd. 3 - San Jose |  |  | Road Maintenance | 4.55 | CBRMC | a) | 112893.42 | a) |  | e) | 112893.42 | a) |  | a) |  | c) |  | a) |  | Purchase Order # 2020030974 (Brgy. San Jose Upland Farmer's Assocaition)
| 136 | [7 empty] | b) | Maligro | b) |  | f) | 112893.42 | b) |  | b) |  | d) |  | b)
[9 empty] | c) |  | c) |  | g) |  | c)
[9 empty] | d) | 6 months | d)
|  |  | Nafco - Bobongon |  |  | Road Maintenance |  | MBA | a) | 89179.68 | a) | 2020-01-02 | e) | 89179.68 | a) |  | a) | 8% | c) | 7% | a) | 3 | On-going
| 139 | [7 empty] | b) | Gamad/Clar | b) | 2020-01-02 | f) | 89179.68 | b) |  | b) |  | d) | -15% | b) | 56
[9 empty] | c) | Admin | c) | 2020-12-31 | g) |  | c)
[9 empty] | d) |  | d)
|  |  | Nafco - Bobongon |  |  | Road Maintenance |  | CBRMC | a) | 80293.17 | a) |  | e) | 80293.17 | a) |  | a) |  | c) |  | a) |  | Purchase Order # 2020030968 (Bobongon Rural Waterworks & Sanitation Association, Inc.)
| 139 | [7 empty] | b) | Maligro | b) |  | f) | 80293.17 | b) |  | b) |  | d) |  | b)
[9 empty] | c) |  | c) |  | g) |  | c)
[9 empty] | d) | 6 months | d)
|  |  | Bdry. Tagum - Crossing Kinamayan Sto. Tomas |  |  | Road Maintenance |  | MBA | a) | 790874.1 | a) | 2020-01-02 | e) | 790874.1 | a) |  | a) | 8% | c) | 10% | a) | 3 | On-going
| 146 | [7 empty] | b) | Gamad/Clar | b) | 2020-01-02 | f) | 790874.1 | b) |  | b) |  | d) | 2% | b) | 66
[9 empty] | c) | Admin | c) | 2020-12-31 | g) |  | c)
[9 empty] | d) |  | d)
|  |  | Bdry. Tagum - Crossing Kinamayan Sto. Tomas |  |  | Road Maintenance |  | CBRMC | a) | 429840.12 | a) |  | e) | 429840.12 | a) |  | a) |  | c) |  | a) |  | Abstract 0320201447
| 146 | [7 empty] | b) | Maligro | b) |  | f) | 429840.12 | b) |  | b) |  | d) |  | b)
[9 empty] | c) |  | c) |  | g) |  | c)
[9 empty] | d) | 9 months | d)
|  |  | San Jose - Sitio Mahayahay, Magwawa |  |  | Road Maintenance | 0.84 | MBA | a) | 22943.54 | a) | 2020-01-02 | e) | 22943.54 | a) |  | a) | 15% | c) | 15% | a) | 3 | On-going
| 151 | [7 empty] | b) | Gamad/Clar | b) | 2020-01-02 | f) | 22943.54 | b) |  | b) |  | d) |  | b) | 60
[9 empty] | c) | Admin | c) | 2020-12-31 | g) |  | c)
[9 empty] | d) | - | d)
|  |  | San Jose - Sitio Mahayahay, Magwawa |  |  | Road Maintenance | 0.84 | CBRMC | a) | 30789.12 | a) |  | e) | 30789.12 | a) |  | a) |  | c) |  | a) |  | Purchase Order # 2020030972 (Brgy. San Jose Upland Farmer's Assocaition)
| 151 | [7 empty] | b) | Maligro | b) |  | f) | 30789.12 | b) |  | b) |  | d) |  | b) | 10
[9 empty] | c) |  | c) |  | g) |  | c)
[9 empty] | d) | 9 months | d)
|  | B. | 20% Development Fund CY 2020
PEACE AND ORDER PROGRAM
|  | 1. Rural Electrification Project |  |  |  | Rural Electrification to cater the needs of brgys. | - | Admin/Contract | a) | 6500000 | [12 empty] | See projects listed below
[9 empty] | b) | -
[9 empty] | c) | -
[9 empty] | d) | -
|  | ■ | Rural Electrification at RAMADA Compound Purok Sto. Niño, Brgy. Cuambogan, Tagum City |  |  | Elect. | - | - | a) | 1000000 | a) | - | e) | - | a) | 1000000 | a) | - | c) | - | a) | - | For preparation of POW and Plans
|  | 1.1 | [6 empty] | b) | - | b) | - | f) | - | b) | 1000000 | b) | - | d) | - | b) | -
[9 empty] | c) | - | c) | - | g) | - | c) | -
[9 empty] | d) | - | d) | -
|  | ■ | Rural Electrification at Lower Camansa Purok 5 nad Purok 6, Brgy. Camansa, Asuncion |  |  | Elect. | - | - | a) | 3000000 | a) | - | e) | - | a) | 3000000 | a) | - | c) | - | a) | - | For preparation of POW and Plans
|  | 1.2 | [6 empty] | b) | - | b) | - | f) | - | b) | 3000000 | b) | - | d) | - | b) | -
[9 empty] | c) | - | c) | - | g) | - | c) | -
[9 empty] | d) | - | d) | -
|  | ■ | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. |  |  | Elect. | - | - | a) | 1000000 | a) | - | e) | - | a) | 1000000 | a) | - | c) | - | a) | - | For preparation of POW and Plans
|  | 1.3 | [6 empty] | b) | - | b) | - | f) | - | b) | 1000000 | b) | - | d) | - | b) | -
[9 empty] | c) | - | c) | - | g) | - | c) | -
[9 empty] | d) | - | d) | -
|  | ■ | Completion of Single Phase Line at Purok 6 and Purok 7, Brgy. Cogon, Babak Distirct, IGACOS |  |  | Rural Electrification to cater the needs of brgys. | - | - | a) | 1000000 | a) | - | e) | - | a) | 1000000 | a) | - | c) | - | a) | - | For preparation of POW and Plans
|  | 1.4 | [6 empty] | b) | - | b) | - | f) | - | b) | 1000000 | b) | - | d) | - | b) | -
[9 empty] | c) | - | c) | - | g) | - | c) | -
[9 empty] | d) | - | d) | -
|  | ■ | Completion of Single Phase Line at Purok Perlas, Brgy. Sta. Cruz, Talicud (Day Care Center), IGACOS |  |  | Rural Electrification to cater the needs of brgys. | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For preparation of POW and Plans
|  | 1.5 | [6 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | -
[9 empty] | c) | - | c) | - | g) | - | c) | -
[9 empty] | d) | - | d) | -
| Road ID | 2. Rehabilitation of Provincial Roads & Bridges |  |  |  | Road Maintenance | KM | MBA | a) | 85047000 | a) | 2020-01-02 | e) | - | a) | 85047000 | a) | - | c) | - | a) | 46 | See list of Provincial Roads
[7 empty] | 54 |  | b) | Paraguya | b) | 2020-01-02 | f) | - | b) | 85047000 | b) | - | d) | - | b) | 920
| 11DAN | [7 empty] | c) | PEO | c) | 2020-12-31 | g) | - | c) | -
[11 empty] | d) | -
[9 empty] | d) | 261 days | d) | -
PEACE AND ORDER PROGRAM
|  |  | Sta. Felomina - San Roque |  |  | Road Rehabilitaion | 7.68 | Admin | a) | 2304000 | a) | - | e) | - | a) | 2304000 | a) | - | c) | - | a) | - | POW on process
| 008 | [7 empty] | b) |  | b) | - | f) | - | b) | 2304000 | b) | - | d) | - | b) | -
[9 empty] | c) | PEO | c) | - | g) | - | c) | -
[9 empty] | d) | - | d) | -
|  |  | Sto. Niño - Palma Gil - Sitio Opao |  |  | Road Rehabilitaion | 5.99 | Admin | a) | 1797000 | a) |  | e) | - | a) | 1797000 | a) | - | c) | - | a) | - | POW on process
| 019 | [7 empty] | b) |  | b) |  | f) | - | b) | 1797000 | b) | - | d) | - | b) | -
[9 empty] | c) | PEO | c) | - | g) | - | c) | -
[9 empty] | d) | - | d) | -
|  |  | Sto. Niño - Daligdigon - Paiton |  |  | Road Rehabilitaion | 11.6 | Admin | a) | 3480000 | a) |  | e) | - | a) | 3480000 | a) | - | c) | - | a) | - | POW on process
| 023 | [7 empty] | b) |  | b) |  | f) | - | b) | 3480000 | b) | - | d) | - | b) | -
[9 empty] | c) | PEO | c) | - | g) | - | c) | -
[9 empty] | d) | - | d) | -
|  |  | Jct. Paiton - Mibolo |  |  | Road Rehabilitaion | 23.9 | Admin | a) | 7170000 | a) |  | e) | - | a) | 7170000 | a) | - | c) | - | a) | - | POW on process
| 024 | [7 empty] | b) |  | b) |  | f) | - | b) | 7170000 | b) | - | d) | - | b) | -
[9 empty] | c) | PEO | c) | - | g) | - | c) | -
[9 empty] | d) | - | d) | -
|  |  | Florida - Suaon - Jct. Gupitan |  |  | Road Rehabilitaion | 15.57 | Admin | a) | 4671000 | a) |  | e) | - | a) | 4671000 | a) | - | c) | - | a) | - | POW on process
| 032 | [7 empty] | b) |  | b) |  | f) | - | b) | 4671000 | b) | - | d) | - | b) | -
[9 empty] | c) | PEO | c) | - | g) | - | c) | -
[9 empty] | d) | - | d) | -
|  |  | Datu Balong - Pinamuno |  |  | Road Rehabilitaion | 2.74 | Admin | a) | 822000 | a) |  | e) | - | a) | 822000 | a) | - | c) | - | a) | - | POW on process
| 040 | [7 empty] | b) |  | b) |  | f) | - | b) | 822000 | b) | - | d) | - | b) | -
[9 empty] | c) | PEO | c) | - | g) | - | c) | -
[9 empty] | d) | - | d) | -
|  |  | New Corella - Saug |  |  | Road Rehabilitaion | 12.52 | Admin | a) | 20571000 | a) |  | e) | - | a) | 20571000 | a) | - | c) | - | a) | - | POW on process
| 048 | [7 empty] | b) |  | b) |  | f) | - | b) | 20571000 | b) | - | d) | - | b) | -
[9 empty] | c) | PEO | c) | - | g) | - | c) | -
[9 empty] | d) | - | d) | -
INFRASTRUCTURE DEVELOPMENT PROGRAMS
|  |  | Jct. Highway Canatan - Doña Andrea |  |  | Road Rehabilitaion | 4.34 | Admin | a) | 1302000 | a) |  | e) | - | a) | 1302000 | a) | - | c) | - | a) | - | POW on process
| 007 | [7 empty] | b) |  | b) |  | f) | - | b) | 1302000 | b) | - | d) | - | b) | -
[9 empty] | c) | PEO | c) | - | g) | - | c) | -
[9 empty] | d) | - | d) | -
|  |  | Florida - New Boholano |  |  | Road Rehabilitaion | 2.54 | Admin | a) | 762000 | a) |  | e) | - | a) | 762000 | a) | - | c) | - | a) | - | POW on process
| 030 | [7 empty] | b) |  | b) |  | f) | - | b) | 762000 | b) | - | d) | - | b) | -
[9 empty] | c) | PEO | c) | - | g) | - | c) | -
[9 empty] | d) | - | d) | -
|  |  | Jct. New Boholano - New Loon |  |  | Road Rehabilitaion | 4.77 | Admin | a) | 1431000 | a) |  | e) | - | a) | 1431000 | a) | - | c) | - | a) | - | POW on process
| 031 | [7 empty] | b) |  | b) |  | f) | - | b) | 1431000 | b) | - | d) | - | b) | -
[9 empty] | c) | PEO | c) | - | g) | - | c) | -
[9 empty] | d) | - | d) | -
|  |  | Mesaoy - Jct. Mahayahay |  |  | Road Rehabilitaion | 4.6 | Admin | a) | 1380000 | a) |  | e) | - | a) | 1380000 | a) | - | c) | - | a) | - | POW on process
| 069 | [7 empty] | b) |  | b) |  | f) | - | b) | 1380000 | b) | - | d) | - | b) | -
[9 empty] | c) | PEO | c) | - | g) | - | c) | -
[9 empty] | d) | - | d) | -
|  |  | Lower Asuncion - Upper Asuncion |  |  | Road Rehabilitaion | KM | Admin | a) | 1302000 | a) |  | e) | - | a) | 1302000 | a) | - | c) | - | a) | - | Plan On-going
| 007 | [7 empty] | b) |  | b) |  | f) | - | b) | 1302000 | b) | - | d) | - | b) | -
[9 empty] | c) | PEO | c) | - | g) | - | c) | -
[9 empty] | d) | - | d) | -
|  |  | Jct. Highway - Carmen - Mangalcal - Tubod |  |  | Road Rehabilitaion | KM | Admin | a) | 1323000 | a) | - | e) | - | a) | 1323000 | a) | - | c) | - | a) | - | Plan On-going
| 030 | [7 empty] | b) |  | b) | - | f) | - | b) | 1323000 | b) | - | d) | - | b) | -
[9 empty] | c) | PEO | c) | - | g) | - | c) | -
[9 empty] | d) | - | d) | -
|  |  | Tuganay - Taba |  |  | Road Rehabilitaion | KM | Admin | a) | 1431000 | a) |  | e) | - | a) | 1431000 | a) | - | c) | - | a) | - | Plan On-going
| 031 | [7 empty] | b) |  | b) |  | f) | - | b) | 1431000 | b) | - | d) | - | b) | -
[9 empty] | c) | PEO | c) | - | g) | - | c) | -
[9 empty] | d) | - | d) | -
|  |  | Jct. Highway - Ising - Magsaysay |  |  | Road Rehabilitaion | KM | Admin | a) | 6000000 | a) | - | e) | - | a) | 6000000 | a) | - | c) | - | a) | - | Plan On-going
| 069 | [7 empty] | b) |  | b) | - | f) | - | b) | 6000000 | b) | - | d) | - | b) | -
[9 empty] | c) | PEO | c) | - | g) | - | c) | -
[9 empty] | d) | - | d) | -
|  |  | Jct. Highway - Guadalupe - Bdry. Tagum |  |  | Road Rehabilitaion | KM | Admin | a) | 910000 | a) | - | e) | - | a) | 910000 | a) | - | c) | - | a) | -
| 069 | [7 empty] | b) |  | b) | - | f) | - | b) | 910000 | b) | - | d) | - | b) | -
[9 empty] | c) | PEO | c) | - | g) | - | c) | -
[9 empty] | d) | - | d) | -
|  |  | Sitio Malaga - Tibulao |  |  | Road Rehabilitaion | KM | Admin | a) | 350000 | a) | - | e) | - | a) | 350000 | a) | - | c) | - | a) | - | Plan On-going
| 069 | [7 empty] | b) |  | b) | - | f) | - | b) | 350000 | b) | - | d) | - | b) | -
[9 empty] | c) | PEO | c) | - | g) | - | c) | -
[9 empty] | d) | - | d) | -
|  |  | Prk. 5 RJS - Prk. 6 New Casay |  |  | Road Rehabilitaion | KM | Admin | a) | 350000 | a) | - | e) | - | a) | 350000 | a) | - | c) | - | a) | - | Plan On-going
| 069 | [7 empty] | b) |  | b) | - | f) | - | b) | 350000 | b) | - | d) | - | b) | -
[9 empty] | c) | PEO | c) | - | g) | - | c) | -
[9 empty] | d) | - | d) | -
|  |  | Dujali - Pawas - San Vicente |  |  | Road Rehabilitaion | KM | Admin | a) | 350000 | a) | - | e) | - | a) | 350000 | a) | - | c) | - | a) | - | Plan On-going
| 069 | [7 empty] | b) |  | b) | - | f) | - | b) | 350000 | b) | - | d) | - | b) | -
[9 empty] | c) | PEO | c) | - | g) | - | c) | -
[9 empty] | d) | - | d) | -
|  |  | Los Amigos 1 - Esperanza - Los Amigos 2 |  |  | Road Rehabilitaion | KM | Admin | a) | 350000 | a) | - | e) | - | a) | 350000 | a) | - | c) | - | a) | - | Plan On-going
| 069 | [7 empty] | b) |  | b) | - | f) | - | b) | 350000 | b) | - | d) | - | b) | -
[9 empty] | c) | PEO | c) | - | g) | - | c) | -
[9 empty] | d) | - | d) | -
|  |  | San Miguel - Crossing Kinamayan |  |  | Road Rehabilitaion | KM | Admin | a) | 19200000 | a) | - | e) | - | a) | 19200000 | a) | - | c) | - | a) | - | Plan On-going
| 069 | [7 empty] | b) |  | b) | - | f) | - | b) | 19200000 | b) | - | d) | - | b) | -
[9 empty] | c) | PEO | c) | - | g) | - | c) | -
[9 empty] | d) | - | d) | -
|  |  | Fd. Rd. 2 - Sto. Tomas - Magwawa |  |  | Road Rehabilitaion | KM | Admin | a) | 350000 | a) | - | e) | - | a) | 350000 | a) | - | c) | - | a) | - | Plan On-going
| 069 | [7 empty] | b) |  | b) | - | f) | - | b) | 350000 | b) | - | d) | - | b) | -
[9 empty] | c) | PEO | c) | - | g) | - | c) | -
[9 empty] | d) | - | d) | -
|  |  | Menzi - Balagunan - Tulalian |  |  | Road Rehabilitaion | KM | Admin | a) | 3720500 | a) | - | e) | - | a) | 3720500 | a) | - | c) | - | a) | - | Plan On-going
| 069 | [7 empty] | b) |  | b) | - | f) | - | b) | 3720500 | b) | - | d) | - | b) | -
[9 empty] | c) | PEO | c) | - | g) | - | c) | -
[9 empty] | d) | - | d) | -
|  |  | Jct,. Bdry. Tagum- Talomo |  |  | Road Rehabilitaion | KM | Admin | a) | 3720500 | a) | - | e) | - | a) | 3720500 | a) | - | c) | - | a) | - | Plan On-going
| 069 | [7 empty] | b) |  | b) | - | f) | - | b) | 3720500 | b) | - | d) | - | b) | -
[9 empty] | c) | PEO | c) | - | g) | - | c) | -
[9 empty] | d) | - | d) | -
|  | 3. Various Local Roads & Drainage Dev't. Project |  |  |  | Rehabilitaion |  | - | a) | 27700002 | a) | [11 empty] | See projects listed below
[9 empty] | b) |  | b)
[9 empty] | c) | PEO | c) | -
[9 empty] | d) | - | d)
|  | ■ | Rehab. Of Various Locl Roads @ Tagum City |  |  | Rehabilitaion | km. | - | a) | 2518182 | a) |  | e) | - | a) | 2518182 | a) | - | c) | - | a) | - | POW on process
|  | 2.1 | [6 empty] | b) |  | b) |  | f) | - | b) | 2518182 | b) | - | d) | - | b) | -
[9 empty] | c) | PEO | c) | - | g) | - | c) | -
[9 empty] | d) | - | d) | -
|  | ■ | Rehab. Of Various Locl Roads @ Asuncion |  |  | Rehabilitaion | km. | - | a) | 2518182 | a) |  | e) | - | a) | 2518182 | a) | - | c) | - | a) | - | POW on process
|  | 2.2 | [6 empty] | b) |  | b) |  | f) | - | b) | 2518182 | b) | - | d) | - | b) | -
[9 empty] | c) | PEO | c) | - | g) | - | c) | -
[9 empty] | d) | - | d) | -
|  | ■ | Rehab. Of Various Locl Roads @ Kapalong |  |  | Rehabilitaion | km. | - | a) | 2518182 | a) |  | e) | - | a) | 2518182 | a) | - | c) | - | a) | - | POW on process
|  | 2.3 | [6 empty] | b) |  | b) |  | f) | - | b) | 2518182 | b) | - | d) | - | b) | -
[9 empty] | c) | PEO | c) | - | g) | - | c) | -
[9 empty] | d) | - | d) | -
|  | ■ | Rehab. Of Various Locl Roads @ New Corella |  |  | Rehabilitaion | km. | - | a) | 2518182 | a) |  | e) | - | a) | 2518182 | a) | - | c) | - | a) | - | POW on process
|  | 2.4 | [6 empty] | b) |  | b) |  | f) | - | b) | 2518182 | b) | - | d) | - | b) | -
[9 empty] | c) | PEO | c) | - | g) | - | c) | -
[9 empty] | d) | - | d) | -
|  | ■ | Rehab. Of Various Locl Roads @ San Isidro |  |  | Rehabilitaion | km. | - | a) | 2518182 | a) |  | e) | - | a) | 2518182 | a) | - | c) | - | a) | - | POW on process
|  | 2.5 | [6 empty] | b) |  | b) |  | f) | - | b) | 2518182 | b) | - | d) | - | b) | -
[9 empty] | c) | PEO | c) | - | g) | - | c) | -
[9 empty] | d) | - | d) | -
|  | ■ | Rehab. Of Various Local Roads @ Talaingod |  |  | Rehabilitaion | km. | - | a) | 2518182 | a) |  | e) | - | a) | 2518182 | a) | - | c) | - | a) | - | POW on process
|  | 2.6 | [6 empty] | b) |  | b) |  | f) | - | b) | 2518182 | b) | - | d) | - | b) | -
[9 empty] | c) | PEO | c) | - | g) | - | c) | -
[9 empty] | d) | - | d) | -
|  | ■ | Rehab. Of Various Local Roads @ Island Garden City of Samal |  |  | Rehabilitaion |  | - | a) | 2518182 | a) | - | e) | - | a) | 2518182 | a) | - | c) | - | a) | - | Plan On-going
|  | 3.1 | [6 empty] | b) | - | b) | - | f) | - | b) | 2518182 | b) | - | d) | - | b) | -
[9 empty] | c) | - | c) | - | g) | - | c) | -
[9 empty] | d) | - | d) | -
|  | ■ | Rehab. Of Various Local Roads @ Panabo City |  |  | Rehabilitaion |  | - | a) | 2518182 | a) | - | e) | - | a) | 2518182 | a) | - | c) | - | a) | - | Abstract # 0420201633 - Billboard; Abstract 0520201661 - hardware
|  | 3.2 | [6 empty] | b) | - | b) | - | f) | - | b) | 2518182 | b) | - | d) | - | b) | -
[9 empty] | c) | - | c) | - | g) | - | c) | -
[9 empty] | d) | - | d) | -
|  | ■ | Rehab. Of Various Local Roads @ B.E Dujali |  |  | Rehabilitaion |  | - | a) | 2518182 | a) | - | e) | - | a) | 2518182 | a) | - | c) | - | a) | - | Purchase Request # 20053256 - Hardware; PR # 20053255 - Billboard
|  | 3.3 | [6 empty] | b) | - | b) | - | f) | - | b) | 2518182 | b) | - | d) | - | b) | -
[9 empty] | c) | - | c) | - | g) | - | c) | -
[9 empty] | d) | - | d) | -
|  | ■ | Rehab. Of Various Local Roads @ Carmen |  |  | Rehabilitaion |  | - | a) | 2518182 | a) | - | e) | - | a) | 2518182 | a) | - | c) | - | a) | - | Abstract # 0420201633 - Billboard; Abstract 0520201661 - hardware
|  | 3.4 | [6 empty] | b) | - | b) | - | f) | - | b) | 2518182 | b) | - | d) | - | b) | -
[9 empty] | c) | - | c) | - | g) | - | c) | -
[9 empty] | d) | - | d) | -
|  | ■ | Rehab. Of Various Local Roads @ Sto. Tomas |  |  | Rehabilitaion |  | - | a) | 2518182 | a) | - | e) | - | a) | 2518182 | a) | - | c) | - | a) | - | Plan On-going
|  | 3.5 | [6 empty] | b) | - | b) | - | f) | - | b) | 2518182 | b) | - | d) | - | b) | -
[9 empty] | c) | - | c) | - | g) | - | c) | -
[9 empty] | d) | - | d) | -
|  | 4. Various Government Buildings and Facilities Development Project |  |  |  | Various Bldgs./Facilities | km. | - | a) | 26790000 | a) | [11 empty] | See projects listed below
[9 empty] | b) |  | b)
[9 empty] | c) | PEO | c) | -
[9 empty] | d) | - | d)
|  | ■ | Construction of DAVNOR Tech-Vocational Center, Government Center, Mankilam, Tagum City |  |  | Various Bldgs./Facilities | sq.m | - | a) | 8000000 | a) |  | e) | - | a) | 8000000 | a) | - | c) | - | a) | - | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
|  | 4.1 | [6 empty] | b) |  | b) |  | f) | - | b) | 8000000 | b) | - | d) | - | b) | -
[9 empty] | c) | PEO | c) | - | g) | - | c) | -
[9 empty] | d) | - | d) | -
|  | ■ | Improvement of PSWDO Bodega Government Cente, Mankilam, Tagu City |  |  | Various Bldgs./Facilities | sq.m | - | a) | 1000000 | a) |  | e) | - | a) | 1000000 | a) | - | c) | - | a) | - | POW and Plans on-going
|  | 4.2 | [6 empty] | b) |  | b) |  | f) | - | b) | 1000000 | b) | - | d) | - | b) | -
[9 empty] | c) | PEO | c) | - | g) | - | c) | -
[9 empty] | d) | - | d) | -
|  | ■ | Renovation/Improvement of MAFAMCO Consumer's Bldg., Brgy. Mamangan, San Isidro |  |  | Various Bldgs./Facilities | sq.m | Contract | a) | 800000 | a) |  | e) | - | a) | 800000 | a) | - | c) | - | a) | - | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
|  | 4.3 | [6 empty] | b) |  | b) |  | f) | - | b) | 800000 | b) | - | d) | - | b) | -
[9 empty] | c) | - | c) | - | g) | - | c) | -
[9 empty] | d) | - | d) | -
|  | ■ | Construction of IP Council of Women Training Center, Camansa Kamadi District, Asuncion |  |  | Various Bldgs./Facilities | sq.m | - | a) | 500000 | a) |  | e) | - | a) | 500000 | a) | - | c) | - | a) | - | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
|  | 4.4 | [6 empty] | b) |  | b) |  | f) | - | b) | 500000 | b) | - | d) | - | b) | -
[9 empty] | c) | PEO | c) | - | g) | - | c) | -
[9 empty] | d) | - | d) | -
|  | ■ | Construction of one(1) unit School Building at Cabidianan E/S, New Corella |  |  | Various Bldgs./Facilities | sq.m | Contract | a) | 1300000 | a) |  | e) | - | a) | 1300000 | a) | - | c) | - | a) | - | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
|  | 4.5 | [6 empty] | b) |  | b) |  | f) | - | b) | 1300000 | b) | - | d) | - | b) | -
[9 empty] | c) | - | c) | - | g) | - | c) | -
[9 empty] | d) | - | d) | -
|  | ■ | Construction of one(1) unit School Building at Kamansi Integrated School, Florida, kapalong |  |  | Various Bldgs./Facilities | sq.m | Contract | a) | 1300000 | a) |  | e) | - | a) | 1300000 | a) | - | c) | - | a) | - | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
|  | 4.6 | [6 empty] | b) |  | b) |  | f) | - | b) | 1300000 | b) | - | d) | - | b) | -
[9 empty] | c) | - | c) | - | g) | - | c) | -
[9 empty] | d) | - | d) | -
|  | ■ | Construction of one(1) unit School Building at Magatos E/S, Magatos, Asuncion |  |  | Various Bldgs./Facilities | sq.m | Contract | a) | 1300000 | a) |  | e) | - | a) | 1300000 | a) | - | c) | - | a) | - | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
|  | 4.7 | [6 empty] | b) |  | b) |  | f) | - | b) | 1300000 | b) | - | d) | - | b) | -
[9 empty] | c) | - | c) | - | g) | - | c) | -
[9 empty] | d) | - | d) | -
|  | ■ | Construction of one(1) unit School Building at Sta Cruz E/S, New Corella |  |  | Various Bldgs./Facilities | sq.m | - | a) | 1300000 | a) |  | e) | - | a) | 1300000 | a) | - | c) | - | a) | - | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
|  | 4.8 | [6 empty] | b) |  | b) |  | f) | - | b) | 1300000 | b) | - | d) | - | b) | -
[9 empty] | c) | PEO | c) | - | g) | - | c) | -
[9 empty] | d) | - | d) | -
CONTRACT PACKAGE
|  | ■ | Construction of Municipal Triball Hall, Asuncion |  |  | Various Bldgs./Facilities | sq.m | Contract | a) | 500000 | a) |  | e) | - | a) | 500000 | a) | - | c) | - | a) | - | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
|  | 4.9 | [6 empty] | b) |  | b) |  | f) | - | b) | 500000 | b) | - | d) | - | b) | -
[9 empty] | c) | - | c) | - | g) | - | c) | -
[9 empty] | d) | - | d) | -
|  | ■ | Construction of Municipal Triball Hall, Kapalong |  |  | Various Bldgs./Facilities | sq.m | Contract | a) | 500000 | a) |  | e) | - | a) | 500000 | a) | - | c) | - | a) | - | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
|  | 5 | [6 empty] | b) |  | b) |  | f) | - | b) | 500000 | b) | - | d) | - | b) | -
[9 empty] | c) | - | c) | - | g) | - | c) | -
[9 empty] | d) | - | d) | -
|  | ■ | Construction of Municipal Triball Hall, Talaingod |  |  | Various Bldgs./Facilities | sq.m | - | a) | 500000 | a) |  | e) | - | a) | 500000 | a) | - | c) | - | a) | - | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
|  | 5.1 | [6 empty] | b) |  | b) |  | f) | - | b) | 500000 | b) | - | d) | - | b) | -
[9 empty] | c) | PEO | c) | - | g) | - | c) | -
[9 empty] | d) | - | d) | -
|  | ■ | Construction of Commercial Building at Kinawitnon, IGACOS, Babak |  |  | Various Bldgs./Facilities |  | - | a) | 2000000 | a) | - | e) | - | a) | 2000000 | a) | - | c) | - | a) | - | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
|  | 5.2 | [6 empty] | b) | - | b) | - | f) | - | b) | 2000000 | b) | - | d) | - | b) | -
[9 empty] | c) | - | c) | - | g) | - | c) | -
[9 empty] | d) | - | d) | -
|  | ■ | Improvement of Provincial Engineer's Office 2nd District Office Phase 2, Carmen |  |  | Various Bldgs./Facilities |  | - | a) | 1590000 | a) | - | e) | - | a) | 1590000 | a) | - | c) | - | a) | - | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
|  | 5.3 | [6 empty] | b) | - | b) | - | f) | - | b) | 1590000 | b) | - | d) | - | b) | -
[9 empty] | c) | - | c) | - | g) | - | c) | -
[9 empty] | d) | - | d) | -
|  | ■ | Construction of DDN hospital Carmen Zone Annex Building Phase 3, Carmen |  |  | Various Bldgs./Facilities |  | - | a) | 800000 | a) | - | e) | - | a) | 800000 | a) | - | c) | - | a) | - | Purchase Request # 20021473
|  | 5.4 | [6 empty] | b) | - | b) | - | f) | - | b) | 800000 | b) | - | d) | - | b) | -
[9 empty] | c) | - | c) | - | g) | - | c) | -
[9 empty] | d) | - | d) | -
|  | ■ | Construction of Municipal Triball Hall, B.E. Dujali |  |  | Various Bldgs./Facilities |  | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
|  | 5.6 | [6 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | -
[9 empty] | c) | - | c) | - | g) | - | c) | -
[9 empty] | d) | - | d) | -
|  | ■ | Construction of Municipal Triball Hall, Sto. Tomas |  |  | Various Bldgs./Facilities |  | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
|  | 5.7 | [6 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | -
[9 empty] | c) | - | c) | - | g) | - | c) | -
[9 empty] | d) | - | d) | -
|  | ■ | Construction of Fence at Tulalian National High School, Tulalian, Sto. Tomas |  |  | Various Bldgs./Facilities |  | - | a) | 1500000 | a) | - | e) | - | a) | 1500000 | a) | - | c) | - | a) | - | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
|  | 5.8 | [6 empty] | b) | - | b) | - | f) | - | b) | 1500000 | b) | - | d) | - | b) | -
|  | . | [6 empty] | c) | - | c) | - | g) | - | c) | -
[9 empty] | d) | - | d) | -
|  | ■ | Construction of Two(2) Classroom at Tibulao Elem. School, Tibulao, Carmen |  |  | Various Bldgs./Facilities |  | - | a) | 2900000 | a) | - | e) | - | a) | 2900000 | a) | - | c) | - | a) | - | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
|  | 5.9 | [6 empty] | b) | - | b) | - | f) | - | b) | 2900000 | b) | - | d) | - | b) | -
[9 empty] | c) | - | c) | - | g) | - | c) | -
[9 empty] | d) | - | d) | -
| C. | 5% CALAMITY FUND CY 2020
DISASTER PREVENTION AND MITIGATION PROGRAM
I. FLOOD CONTROL AND SLOPE PROTECTION PROJECT
|  | Desiltation/Excavation of Rivers & Creeks |  |  |  | Desiltation/Excavation |  | - | a) | 6630206 | [12 empty] | See projects listed below
| 1 | [7 empty] | b) | Matuguinas
[9 empty] | c) | PEO
[9 empty] | d) | -
|  |  | Improvement and Desiltation of Camoning Creek |  |  | Desiltation/Excavation |  | - | a) | 2500000 | a) | - | e) | - | a) | 2500000 | a) | - | c) | - | a) | - | Abstract # 0520201658
|  | 1.1 | [6 empty] | b) | - | b) | - | f) | - | b) | 2500000 | b) | - | d) | - | b) | -
[9 empty] | c) | PEO | c) | - | g) | - | c) | -
[9 empty] | d) | - | d) | -
|  |  | Improvement and Desiltation of Ising Creek |  |  | Desiltation/Excavation |  | - | a) | 2000000 | a) | - | e) | - | a) | 2000000 | a) | - | c) | - | a) | - | Abstract # 0420201637; 0520201662
|  | 1.2 | [6 empty] | b) | - | b) | - | f) | - | b) | 2000000 | b) | - | d) | - | b) | -
[9 empty] | c) | PEO | c) | - | g) | - | c) | -
[9 empty] | d) | - | d) | -
|  |  | Desiltation of Buhang Creek, Anibongan, Carmen |  |  | Desiltation/Excavation |  | - | a) | 2130206 | a) | - | e) | - | a) | 2130206 | a) | - | c) | - | a) | - | Abstract # 0520201657; 0420201626
|  | 1.3 | [6 empty] | b) | - | b) | - | f) | - | b) | 2130206 | b) | - | d) | - | b) | -
[9 empty] | c) | - | c) | - | g) | - | c) | -
[9 empty] | d) | - | d) | -
| 2 | Revetment of Dike and Slope Protection
|  |  | Rehab./Impv't. of Sto. Niño-Daligdigon-Paiton |  |  | Rehab./Impv't. | km. | - | a) | 1000000 | a) |  | e) | - | a) | 1000000 | a) | - | c) | - | a) | - | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
|  | 2.1 | [6 empty] | b) |  | b) |  | f) | - | b) | 1000000 | b) | - | d) | - | b) | -
[9 empty] | c) | PEO | c) | - | g) | - | c) | -
[9 empty] | d) | - | d) | -
|  |  | Rehab./Impv't. of San Miguel - Moslog - Kinamayan, Sto. Tomas |  |  | Rehab./Impv't. |  | - | a) | 1000000 | a) | - | e) | - | a) | 1000000 | a) | - | c) | - | a) | - | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
|  | 2.2 | [6 empty] | b) | - | b) | - | f) | - | b) | 1000000 | b) | - | d) | - | b) | -
[9 empty] | c) | PEO | c) | - | g) | - | c) | -
[9 empty] | d) | - | d) | -
|  | Improvement of Roads, Drainage and Canal |  |  |  | Rehab./Impv't. |  | - | a) | 1000000 | [12 empty] | See projects listed below
| 3 | [7 empty] | b) | Matuguinas
[9 empty] | c) | PEO
[9 empty] | d) | -
|  |  | Improvement of Mangalcal to Diamond Creek Farm to Market Road Opening |  |  | Rehab./Impv't. |  | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
|  | 3.1 | [6 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | -
[9 empty] | c) | - | c) | - | g) | - | c) | -
[9 empty] | d) | - | d) | -
|  |  | Improvement of Mabaus - Salvacion Provincial Road Continuing Road Opening |  |  | Rehab./Impv't. |  | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Plan On-going
|  | 3.2 | [6 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | -
[9 empty] | c) | - | c) | - | g) | - | c) | -
[9 empty] | d) | - | d) | -
| 4 | Improvement of Bridges and Cross Drainage
|  |  | Improvement of Saug-Sonlon-Bdry. Longanapan |  |  | Rehab./Impv't. | km. | - | a) | 1000000 | a) |  | e) | - | a) | 1000000 | a) | - | c) | - | a) | - | For preparation of POW and Plans
|  | 4,.1 | [6 empty] | b) |  | b) |  | f) | - | b) | 1000000 | b) | - | d) | - | b) | -
[9 empty] | c) | PEO | c) | - | g) | - | c) | -
[9 empty] | d) | - | d) | -
|  |  | Single Barrel Box Culvert at Mangalcal-Diamond Creek, Brgy. Mangalcal, Carmen |  |  | Rehab./Impv't. |  | - | a) | 2000000 | a) | - | e) | - | a) | 2000000 | a) | - | c) | - | a) | - | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
|  | 4.2 | [6 empty] | b) | - | b) | - | f) | - | b) | 2000000 | b) | - | d) | - | b) | -
[9 empty] | c) | - | c) | - | g) | - | c) | -
[9 empty] | d) | - | d) | -
| D. | SPECIAL EDUCATION FUND - ANNUAL BUDGET CY 2020
|  | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. | [20 empty] | See projects listed below
| 1 |  |  |  |  | Const./Impv't./Compl. |  | - | a) | 4500000
[9 empty] | b) | -
[9 empty] | c) | -
[9 empty] | d) | -
|  |  | Const. of 1 Classroom @ Mankay Integrated School, Gupitan, kapalong |  |  | Bldg. | sq.m | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For preparation of POW and Plans
|  | 1.1 | [6 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | -
[9 empty] | c) | - | c) | - | g) | - | c) | -
[9 empty] | d) | - | d) | -
|  |  | Const. of 1 Classroom @ Luno-luno ES, Gupitan, kapalong |  |  | Bldg. | sq.m | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For preparation of POW and Plans
|  | 1.2 | [6 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | -
[9 empty] | c) | - | c) | - | g) | - | c) | -
[9 empty] | d) | - | d) | -
|  |  | Const. of 1 Classroom @ Kamunuan ES, Gupitan, kapalong |  |  | Bldg. | sq.m | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For preparation of POW and Plans
|  | 1.3 | [6 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | -
[9 empty] | c) | - | c) | - | g) | - | c) | -
[9 empty] | d) | - | d) | -
|  |  | Const. of 1 Classroom @ Tawinian ES, Gupitan, kapalong |  |  | Bldg. | sq.m | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For preparation of POW and Plans
|  | 1.4 | [6 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | -
[9 empty] | c) | - | c) | - | g) | - | c) | -
[9 empty] | d) | - | d) | -
|  |  | Const. of 1 Classroom @ Aninipot ES, Gupitan, kapalong |  |  | Bldg. | sq.m | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For preparation of POW and Plans
|  | 1.5 | [6 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | -
[9 empty] | c) | - | c) | - | g) | - | c) | -
[9 empty] | d) | - | d) | -
|  |  | Const. of 1 Classroom @ Moling ES, Gupitan, kapalong |  |  | Bldg. | sq.m | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For preparation of POW and Plans
|  | 1.6 | [6 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | -
[9 empty] | c) | - | c) | - | g) | - | c) | -
[9 empty] | d) | - | d) | -
|  |  | Const. of 1 Classroom @ Mangga ES, Magwawa, Sto. Tomas |  |  | Bldg. | sq.m | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For preparation of POW and Plans
|  | 1.7 | [6 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | -
[9 empty] | c) | - | c) | - | g) | - | c) | -
[9 empty] | d) | - | d) | -
|  |  | Const. of 1 Classroom @ Lomondong ES, Dagohoy, Talaingod |  |  | Bldg. | sq.m | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For preparation of POW and Plans
|  | 1.8 | [6 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | -
[9 empty] | c) | - | c) | - | g) | - | c) | -
[9 empty] | d) | - | d) | -
|  |  | Const. of 1 Classroom @ Malapanit ES, Sto. Niño, Talaingod |  |  | Bldg. | sq.m | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For preparation of POW and Plans
|  | 1.9 | [6 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | -
[9 empty] | c) | - | c) | - | g) | - | c) | -
[9 empty] | d) | - | d) | -
| E. | SOCIAL WELFARE AND DEVELOPMENT
|  | 1. CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) |  |  |  | Bldg. | sq.m | Admin/Contract | a) | 11000000 | [12 empty] | See list of projects
[9 empty] | b) | -
[9 empty] | c) | -
[9 empty] | d) | -
|  |  | Const. of Day Care Center, Limbaan, New Corella |  |  | Bldg. | sq.m | - | a) | 1000000 | a) | - | e) | - | a) | 1000000 | a) | - | c) | - | a) | - | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
|  | 1.1 | [6 empty] | b) | - | b) | - | f) | - | b) | 1000000 | b) | - | d) | - | b) | -
[9 empty] | c) | - | c) | - | g) | - | c) | -
[9 empty] | d) | - | d) | -
|  |  | Const. of Day Care Center, Gabuyan, kapalong |  |  | Bldg. | sq.m | - | a) | 1000000 | a) | - | e) | - | a) | 1000000 | a) | - | c) | - | a) | - | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
|  | 1.2 | [6 empty] | b) | - | b) | - | f) | - | b) | 1000000 | b) | - | d) | - | b) | -
[9 empty] | c) | - | c) | - | g) | - | c) | -
[9 empty] | d) | - | d) | -
|  |  | Compl./Rep. Day Care Center,Canatan, Asuncion |  |  | Bldg. | sq.m | - | a) | 300000 | a) | - | e) | - | a) | 300000 | a) | - | c) | - | a) | - | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
|  | 1.3 | [6 empty] | b) | - | b) | - | f) | - | b) | 300000 | b) | - | d) | - | b) | -
[9 empty] | c) | - | c) | - | g) | - | c) | -
[9 empty] | d) | - | d) | -
|  |  | Compl./Rep. Day Care Center,Cambanogoy, Asuncion |  |  | Bldg. | sq.m | - | a) | 300000 | a) | - | e) | - | a) | 300000 | a) | - | c) | - | a) | - | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
|  | 1.4 | [6 empty] | b) | - | b) | - | f) | - | b) | 300000 | b) | - | d) | - | b) | -
[9 empty] | c) | - | c) | - | g) | - | c) | -
[9 empty] | d) | - | d) | -
|  |  | Compl./Rep. Day Care Center,Gabuyan, kapalong |  |  | Bldg. | sq.m | - | a) | 600000 | a) | - | e) | - | a) | 600000 | a) | - | c) | - | a) | - | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
|  | 1.5 | [6 empty] | b) | - | b) | - | f) | - | b) | 600000 | b) | - | d) | - | b) | -
[9 empty] | c) | - | c) | - | g) | - | c) | -
[9 empty] | d) | - | d) | -
|  |  | Compl./Rep. Day Care Center,New Sambog, New Corella |  |  | Bldg. | sq.m | - | a) | 300000 | a) | - | e) | - | a) | 300000 | a) | - | c) | - | a) | - | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
|  | 1.6 | [6 empty] | b) | - | b) | - | f) | - | b) | 300000 | b) | - | d) | - | b) | -
[9 empty] | c) | - | c) | - | g) | - | c) | -
[9 empty] | d) | - | d) | -
|  |  | Compl./Rep. Day Care Center, Cabidianan, New Corella |  |  | Bldg. | sq.m | - | a) | 300000 | a) | - | e) | - | a) | 300000 | a) | - | c) | - | a) | - | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
|  | 1.7 | [6 empty] | b) | - | b) | - | f) | - | b) | 300000 | b) | - | d) | - | b) | -
[9 empty] | c) | - | c) | - | g) | - | c) | -
[9 empty] | d) | - | d) | -
|  |  | Compl./Rep. Day Care Center, Igangon, San Isidro |  |  | Bldg. | sq.m | - | a) | 300000 | a) | - | e) | - | a) | 300000 | a) | - | c) | - | a) | - | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
|  | 1.8 | [6 empty] | b) | - | b) | - | f) | - | b) | 300000 | b) | - | d) | - | b) | -
[9 empty] | c) | - | c) | - | g) | - | c) | -
[9 empty] | d) | - | d) | -
|  |  | Compl./Rep. Day Care Center, Madaum, Tagum City |  |  | Bldg. | sq.m | - | a) | 300000 | a) | - | e) | - | a) | 300000 | a) | - | c) | - | a) | - | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
|  | 1.9 | [6 empty] | b) | - | b) | - | f) | - | b) | 300000 | b) | - | d) | - | b) | -
[9 empty] | c) | - | c) | - | g) | - | c) | -
[9 empty] | d) | - | d) | -
|  |  | Compl./Rep. Day Care Center, Apokon, Tagum City |  |  | Bldg. | sq.m | - | a) | 300000 | a) | - | e) | - | a) | 300000 | a) | - | c) | - | a) | - | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
|  | 2 | [6 empty] | b) | - | b) | - | f) | - | b) | 300000 | b) | - | d) | - | b) | -
[9 empty] | c) | - | c) | - | g) | - | c) | -
[9 empty] | d) | - | d) | -
|  |  | Compl./Rep. Day Care Center, Sto. Niño, Talaingod |  |  | Bldg. | sq.m | - | a) | 300000 | a) | - | e) | - | a) | 300000 | a) | - | c) | - | a) | - | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
|  | 2.1 | [6 empty] | b) | - | b) | - | f) | - | b) | 300000 | b) | - | d) | - | b) | -
[9 empty] | c) | - | c) | - | g) | - | c) | -
[9 empty] | d) | - | d) | -
|  |  | Const. of Day Care Center, JP Laurel, Panabo City |  |  | Bldg. | sq.m | - | a) | 1000000 | a) | - | e) | - | a) | 1000000 | a) | - | c) | - | a) | - | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
|  | 2.2 | [6 empty] | b) | - | b) | - | f) | - | b) | 1000000 | b) | - | d) | - | b) | -
[9 empty] | c) | - | c) | - | g) | - | c) | -
[9 empty] | d) | - | d) | -
|  |  | Const. of Day Care Center, Dujali, B.E. Dujali |  |  | Bldg. | sq.m | - | a) | 1000000 | a) | - | e) | - | a) | 1000000 | a) | - | c) | - | a) | - | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
|  | 2.3 | [6 empty] | b) | - | b) | - | f) | - | b) | 1000000 | b) | - | d) | - | b) | -
[9 empty] | c) | - | c) | - | g) | - | c) | -
[9 empty] | d) | - | d) | -
|  |  | Const. of Day Care Center, Tibal-og, Sto Tomas |  |  | Bldg. | sq.m | - | a) | 1000000 | a) | - | e) | - | a) | 1000000 | a) | - | c) | - | a) | - | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
|  | 2.4 | [6 empty] | b) | - | b) | - | f) | - | b) | 1000000 | b) | - | d) | - | b) | -
[9 empty] | c) | - | c) | - | g) | - | c) | -
[9 empty] | d) | - | d) | -
|  |  | Compl./Rep. Day Care Center, Cabay-angan, B.E. Dujali |  |  | Bldg. | sq.m | - | a) | 300000 | a) | - | e) | - | a) | 300000 | a) | - | c) | - | a) | - | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
|  | 2.5 | [6 empty] | b) | - | b) | - | f) | - | b) | 300000 | b) | - | d) | - | b) | -
[9 empty] | c) | - | c) | - | g) | - | c) | -
[9 empty] | d) | - | d) | -
|  |  | Compl./Rep. Day Care Center, Tanglaw, B.E. Dujali |  |  | Bldg. | sq.m | - | a) | 300000 | a) | - | e) | - | a) | 300000 | a) | - | c) | - | a) | - | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
|  | 2.6 | [6 empty] | b) | - | b) | - | f) | - | b) | 300000 | b) | - | d) | - | b) | -
[9 empty] | c) | - | c) | - | g) | - | c) | -
[9 empty] | d) | - | d) | -
|  |  | Compl./Rep. Day Care Center, Salvacion, Carmen |  |  | Bldg. |  | - | a) | 300000 | a) | - | e) | - | a) | 300000 | a) | - | c) | - | a) | - | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
|  | 2.7 | [6 empty] | b) | - | b) | - | f) | - | b) | 300000 | b) | - | d) | - | b) | -
[9 empty] | c) | - | c) | - | g) | - | c) | -
[9 empty] | d) | - | d) | -
|  |  | Compl./Rep. Day Care Center, San Agustin, IGCS |  |  | Bldg. | sq.m | - | a) | 300000 | a) | - | e) | - | a) | 300000 | a) | - | c) | - | a) | - | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
|  | 2.8 | [6 empty] | b) | - | b) | - | f) | - | b) | 300000 | b) | - | d) | - | b) | -
[9 empty] | c) | - | c) | - | g) | - | c) | -
[9 empty] | d) | - | d) | -
|  |  | Compl./Rep. Day Care Center, Toril, IGCS |  |  | Bldg. | sq.m | - | a) | 300000 | a) | - | e) | - | a) | 300000 | a) | - | c) | - | a) | - | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
|  | 2.9 | [6 empty] | b) | - | b) | - | f) | - | b) | 300000 | b) | - | d) | - | b) | -
[9 empty] | c) | - | c) | - | g) | - | c) | -
[9 empty] | d) | - | d) | -
|  |  | Compl./Rep. Day Care Center, Tibal-og, Sto. Tomas |  |  | Bldg. | sq.m | - | a) | 600000 | a) | - | e) | - | a) | 600000 | a) | - | c) | - | a) | - | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
|  | 3 | [6 empty] | b) | - | b) | - | f) | - | b) | 600000 | b) | - | d) | - | b) | -
[9 empty] | c) | - | c) | - | g) | - | c) | -
[9 empty] | d) | - | d) | -
|  |  | Compl./Rep. Day Care Center, Talomo, Sto. Tomas |  |  | Bldg. | sq.m | - | a) | 300000 | a) | - | e) | - | a) | 300000 | a) | - | c) | - | a) | - | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
|  | 3.1 | [6 empty] | b) | - | b) | - | f) | - | b) | 300000 | b) | - | d) | - | b) | -
[9 empty] | c) | - | c) | - | g) | - | c) | -
[9 empty] | d) | - | d) | -
|  |  | Compl./Rep. Day Care Center, Kinamayan, Sto. Tomas |  |  | Bldg. | sq.m | - | a) | 300000 | a) | - | e) | - | a) | 300000 | a) | - | c) | - | a) | - | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
|  | 3.2 | [6 empty] | b) | - | b) | - | f) | - | b) | 300000 | b) | - | d) | - | b) | -
[9 empty] | c) | - | c) | - | g) | - | c) | -
[9 empty] | d) | - | d) | -
|  |  | Compl./Rep. Day Care Center, La Libertad, Sto. Tomas |  |  | Bldg. | sq.m | - | a) | 300000 | a) | - | e) | - | a) | 300000 | a) | - | c) | - | a) | - | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
|  | 3.3 | [6 empty] | b) | - | b) | - | f) | - | b) | 300000 | b) | - | d) | - | b) | -
[9 empty] | c) | - | c) | - | g) | - | c) | -
[9 empty] | d) | - | d) | -
[5 empty] | GF- GENERAL FUND | [11 empty] | TF - TRUST FUND (NATIONAL FUNDED PROJECT)
[5 empty] | 20% DF - 20% DEV'T. FUND | [11 empty] | a) SLRF - Special Local Road Fund
[5 empty] | 5% CF - 5% CALAMITY FUND | [11 empty] | b) KALSADA - Konkreto at Ayos na Lansangan Tungo sa Pangkalahatang Kaunlaran
[5 empty] | CO - CAPITAL OUTLAY | [11 empty] | c) PRDP - Philippine Rural Development Projects
[5 empty] | CONG. FUND - CONGRESSIONAL FUND | [11 empty] | d) SELAP - Support to Emergency and Livelihood Assistance Project
[5 empty] | SEF - SPECIAL EDUCATIONAL UFND | [11 empty] | e) PAMANA - Payapa at Masaganang Pamayanan
f) CBRMC - Community Based Road Maintenance Contracting
g) MBC - Maintenance by Contract
h) PCF-Performance Challenge Fund-DILG
i) FMRDP - Farm to Market Road
j.) CMGP - Conditional Grant to Provinces
k.) OPAPP - Office of the President Adviser on the Peace Process
l.) LGSF-AM - Local Government Support Fund Assistance to Municipalities
|  |  | Prepared by: |  |  |  | Checked | [5 empty] | Noted | [6 empty] | Recommending Approval
|  |  | RETCHIE A. DE LOS REYES |  |  |  | ELISA A. BARCENA | [5 empty] | JIVELLYN B. CO | [6 empty] | GLENN A. OLANDRIA
|  |  | Engineer II |  |  |  | Engineer IV- Engineering Dist 1, Area Engineer | [5 empty] | Asst. PG-Department Head | [6 empty] | Provincial Engineer
Formulas:
Date A lot. Rel. = +[Date A lot. Rel., row above]+200
Date A lot. Rel. = [Date A lot. Rel., row above]

## Completed (South) (hidden)
PROVINCE OF DAVAO DEL NORTE
ACCOMPLISHMENT REPORT
FOR THE MONTH OF FEBRUARY 2020
SECTOR: ECONOMIC (INFRASTRUCTURE DEV'T. PROGRAM)
OFFICE/AGENCY: PROVINCIAL ENGINEER'S OFFICE
AREA: 2ND ENGINEERING DISTRICT - COMPLETED PROJECTS
Name of Project |  |  |  | Type | Physical | Mode | PROJECT DATA | [5 empty] | Financial (000) |  | Physical Accomplishment |  |  |  | Employment |  | REMARKS
|  |  |  | of | Target | of | a) Project Cost |  | a) | Date A lot. Rel. | e) | # of days suspended | a) Program |  | a) Planned |  | c) Actual |  | Generated
|  |  |  | Project | (Descrip | Impl. | b) Project Engineer |  | b) | Date Started | f) | # of days extended | b) Allotment |  | b) Revised |  | d) Slippage |  | a) # of Persons | # of Persons
|  |  |  | (Location) | tion) |  | c) Implementor |  | c) | Target Compl. Date | g) | Date completed | c) Disbursement | [5 empty] | b) | Man-days
[7 empty] | d) Duration |  | d) | Revised Compl. Date
I. | PROJECTS UNDER THE CONTINUING APPROPRIATION | [20 empty] | AC | 893809.45
|  | SLRF 2015 | [6 empty] | a) |  | e) | 65 days | a) |  | a) | 100% | c) | 100% | a) | 3 | Completed as per POW, Financial Documents on Process | 2
|  | Rehab. of Jct. Highway-Tuganay-Anibongan-BE Dujali-Kinamayan Provincial Road (Furtheranace) |  | Slope protection | - | - | a) | 1911175.99 | b) | 2019-02-18 | f) | 47 days | b) |  | b) |  | d) | 0% | b) | 60 |  | 2
[7 empty] | b) | Balbastro | c) | 2019-09-21 | g) | 9/21/2019 | c) | [8 empty] | 2
[7 empty] | c) | Admin | d) | [12 empty] | 2
[7 empty] | d) | - | [13 empty] | 2
| A. | 20% Development Fund CY 2016 | [19 empty] | FS
|  | 1. Water System Development Projects |  | Water |  | Admin | a) | 2000000 | [12 empty] | See project listed below | AC
|  |  |  | System |  |  | b) | - | [13 empty] | AC
[7 empty] | c) | PEO | [13 empty] | AC
d)
|  |  | Development of Deepwell Source and Install. Of Pipelines, Licup, samal Dist. IGACOS (Previously Deepwell Drilling at Licup) | Water | Households | Admin | a) | 645,000.00 | a) | 2018-11-08 | e) | - | a) | 645,000.00 | a) | 100.00% | c) | 100.00% | a) | 4 | Completed as per physical accomplishment. Financial documents still on process | 2
|  |  |  | System |  |  | b) | Diosanta | b) | 2019-03-01 | f) | 66 CD | b) | 645,000.00 | b) | - | d) | - | b) | 100 |  | 2
|  | 1.1 |  |  |  |  | c) | PEO | c) | 2019-05-10 | g) | 2019-07-15 | c) | 619,200.00 | [7 empty] | 2
[7 empty] | d) | 70 CD | d) | 2019-07-15 | [11 empty] | 2
| B. | GENERAL FUND PROPER CY 2018
STIMULUS PROJECTS
|  | 1 | Completion of Kasilak Day Care Center, Sta. Cruz, IGCS | Bldg. |  | Admin | a) | 500000 | a) | 2018-07-05 | e) | - | a) | 500000 | a) | 100.00% | c) | 100.00% | a) | - | Completed as per physical accomplishment. Financial documents still on process
[7 empty] | b) | Porras | b) | 2019-05-20 | f) | 136 CD | b) | 500000 | b) | - | d) | - | b) | -
[7 empty] | c) | PEO | c) | 2019-07-17 | g) |  | c) | -
[7 empty] | d) | 60 CD | d)
| M. | GENERAL FUND CY 2019
1. Stimulus Projects for Various Barangays |  |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | sq.m | 0 | a) | 41500000 | [12 empty] | See projects listed below
[7 empty] | b) | Medalla
[7 empty] | c) | PEO
[7 empty] | d) | -
IGCS
5.52 |  | Concreting of Brgy. Road from Prk. 1 to Prk. 2, Villarica, ICGS |  | Road | km | Contract | a) | 500000 | a) | 2019-01-14 | e) | - | a) | 500000 | a) | 100.00% | c) | 100.00% | a) | - | Completed as per physical accomplishment. Financial documents still on process
[7 empty] | b) | Porras | b) | 2019-11-19 | f) | 33 CD | b) | 500000 | b) | - | d) | - | b) | -
[7 empty] | c) | J-One Builders | c) | 2019-12-19 | g) | 2020-01-20 | c) | -
[7 empty] | d) | - | d) | -
C. 5% CALAMITY FUND CY 2019
| Desiltation/Excavation of rivers and creeks |  |  | creeks and canals deislted | ln.m | Admin/Contract | a) | 3000000 | [12 empty] | See project listed below
1 | [6 empty] | b) | Paraguya
[7 empty] | c) | PEO
[7 empty] | d) | -
|  | Desiltation of Mactan River Ph. II |  | Desiltation | ln.m | Admin | a) | 500000 | a) | 2019-08-08 | e) | - | a) | 500000 | a) | 100% | c) | 100% | a) | 5 | Completed as per physical accomplishment. Financial documents still on process
| 1.1 | [5 empty] | b) | Toquero | b) | 2019-07-29 | f) | - | b) | 500000 | b) | - | d) | - | b) | 40
[7 empty] | c) | PEO | c) | 2019-09-27 | g) | - | c) | -
[7 empty] | d) | 60 C.D | d) | -
| Improvement of roads, drainage and canal |  |  | Protection dikes/slope protection | - | - | a) | 3000000 |  |  |  | - | [8 empty] | See project listed below
2 | [6 empty] | b) | Paraguya
[7 empty] | c) | PEO
[7 empty] | d) | -
|  | Repair/Rehab of Drainage System & Ground Gravelling at Kimamon NHS |  | Road | ln.m | Admin | a) | 464833 | a) | - | e) | - | a) | 464833 | a) | 100.00% | c) | 100.00% | a) | 5 | Completed as per physical accomplishment. Financial documents still on process
| 2.1 | [5 empty] | b) | Azotes | b) | 2019-09-16 | f) | - | b) | 464833 | b) | - | d) | - | b) | 110
[7 empty] | c) | Admin | c) | 2019-10-10 | g) | 2019-10-10 | c) | -
[7 empty] | d) | - | d) | -
D. | SUPPLEMENTAL BUDGET NO. 1 CY 2019 | [20 empty] | 1
|  | Repair maintenance of OPD, Pharmacy building, DDNH - CZ Compound |  | Bldg. | sq.m | Admin | a) | 100000 | a) | - | e) | - | a) | 100000 | a) | 100.00% | c) | 100.00% | a) | 5 | Completed as per physical accomplishment. Financial documents still on process | 2
| 1 | [5 empty] | b) | Estorco | b) | 2019-06-14 | f) | - | b) | 100000 | b) | - | d) | - | b) | 110 |  | 2
[7 empty] | c) | Admin | c) | 2019-06-28 | g) | 2019-06-28 | c) | - | [7 empty] | 2
[7 empty] | d) | - | d) | - | [11 empty] | AC
Formulas:
Date completed = [Date A lot. Rel., row below]

## On-going(South) (hidden)
PROVINCE OF DAVAO DEL NORTE
ACCOMPLISHMENT REPORT
FOR THE MONTH OF FEBRUARY 2020
SECTOR: ECONOMIC (INFRASTRUCTURE DEV'T. PROGRAM)
OFFICE/AGENCY: PROVINCIAL ENGINEER'S OFFICE
AREA: 2ND ENGINEERING DISTRICT - ON-GOING PROJECTS
| Name of Project |  |  |  |  | Type | Physical | Mode | PROJECT DATA | [5 empty] | Financial (000) |  | Physical Accomplishment |  |  |  | Employment |  | REMARKS
[6 empty] | of | Target | of | a) Project Cost |  | a) | Date A lot. Rel. | e) | # of days suspended | a) Program |  | a) Planned |  | c) Actual |  | Generated
[6 empty] | Project | (Descrip | Impl. | b) Project Engineer |  | b) | Date Started | f) | # of days extended | b) Allotment |  | b) Revised |  | d) Slippage |  | a) # of Persons | # of Persons
[6 empty] | (Location) | tion) |  | c) Implementor |  | c) | Target Compl. Date | g) | Date completed | c) Disbursement | [5 empty] | b) | Man-days
[9 empty] | d) Duration |  | d) | Revised Compl. Date
| I. | PROJECTS UNDER THE CONTINUING APPROPRIATION | [21 empty] | AC |  | 893809.45
|  | A. | Supplemental Budget # 1 CY 2015 | [20 empty] | 2
|  |  | 1. Proposed Davao del Norte Tourism Billboard, Brgy. Lasang, Panabo City |  |  | Billboard | sq.m | Admin | a) | 756,400.00 | a) | 2015-05-06 | e) | - | a) | 756,400.00 | a) | 11.78% | c) | 11.78% | a) | - | delay due to change location & design code. For AIP amendment from Panabo City to Gov't Center, Mankilam | 2
[9 empty] | b) | Porras | b) | 2015-03-30 | f) | - | b) | 756,400.00 | b) | - | d) | - | b) | - |  | 2
[9 empty] | c) | PEO | c) | 2015-05-10 | g) | - | c) | 332,087.30 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  | B. | Supplemental Budget # 5 CY 2015 | [20 empty] | FS
|  |  | 1. Purchased, Const. & Imprv't. of Gov't. Facilities (8918) |  |  |  | sq.m | Admin | [14 empty] | See projects listed below | AC
|  |  | a) Const./Compl./Imprvt. of Various Gov't. Bldgs. Structures & Facilities |  |  | Bldgs. |  |  | a) | 38,000,000.00 | [13 empty] | AC
[9 empty] | b) | Imboy | [13 empty] | AC
[9 empty] | c) | PEO | [13 empty] | AC
|  |  |  | Const. of Multi-Purpose Bldg. Magsaysay, Carmen |  | Court | sq.m | MLGU | a) | 500000 | a) | 2016-03-05 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For cancellation since the project was already undertaken by Davao Light & no back up cash since it is part of the loan with LBP | 2
|  |  | 1 | [5 empty] | b) | CY 2015 | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 2
[9 empty] | c) | PEO | c) | - | g) | - | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  |  | Improvement of Covered Court, Brgy. San Isidro, Carmen |  | Court | sq.m | MLGU | a) | 500000 | a) | 2016-03-05 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For cancellation since the project was already undertaken by Davao Light & no back up cash since it is part of the loan with LBP | 2
|  |  | 2 | [5 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 2
[9 empty] | c) | PEO | c) | - | g) | - | c) | [8 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  |  | Construction of 1 Bay Covered Court, Brgy. Bobongon, Sto. Tomas |  | Court | sq.m | MLGU | a) | 500000 | a) | 2016-03-08 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For cancellation since the project was already undertaken by Davao Light & no back up cash since it is part of the loan with LBP | 2
|  |  | 3 | [5 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 2
[9 empty] | c) | PEO | c) | - | g) | - | c) | [8 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  |  | Construction of Multi-Purpose Building, Brgy. New Visayas, Sto. Tomas |  | Bldg. | sq.m | MLGU | a) | 500000 | a) | 2016-03-05 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For cancellation since the project was already undertaken by Davao Light & no back up cash since it is part of the loan with LBP | 2
|  |  | 4 | [5 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 2
[9 empty] | c) | PEO | c) | - | g) | - | c) | [8 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  |  | Improvement of Brgy. Hall, Brgy. Tulalian, Sto. Tomas |  | Bldg. | sq.m | MLGU | a) | 500000 | a) | 2016-03-05 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For cancellation since the project was already undertaken by Davao Light & no back up cash since it is part of the loan with LBP | 2
|  |  | 5 | [5 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 2
[9 empty] | c) | PEO | c) | - | g) | - | c) | [8 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  |  | Construction of Market Stall, Brgy. La Libertad, Sto. Tomas |  | Market Stall | sq.m | MLGU | a) | 500000 | a) | 2016-03-05 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For cancellation since the project was already undertaken by Davao Light & no back up cash since it is part of the loan with LBP | 2
|  |  | 6 | [5 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 2
[9 empty] | c) | PEO | c) | - | g) | - | c) | [8 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  |  | Const. of Covered Court Bleacher w/ Roofing, Brgy. Cabay-angan, B.E. Dujali |  | Court | sq.m | MLGU | a) | 500000 | a) | 2016-03-05 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For cancellation since the project was already undertaken by Davao Light & no back up cash since it is part of the loan with LBP | 2
|  |  | 7 | [5 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 2
[9 empty] | c) | PEO | c) | - | g) | - | c) | [8 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  | C. | Trust Fund | [20 empty] | FS
|  |  | 1. PRDP | [20 empty] | AC
|  |  |  | Rehab. of Esperanza-Pob. Sto. Tomas, |  | Road | 12.77399 km | Contract. | a) | 117,410,426.30 | a) | CY 2014 | e) | - | a) | 117,410,426.30 | a) | 100% | c) | 89.82% | a) | 20 | On-going . Request for time extension on process. Waiting for approval of variation order for billing | 2
|  |  | 1.1 | [5 empty] | b) | Palero | b) | 2017-03-22 | f) | - | b) | 117,410,426.30 | b) | 96% | d) | -6.179% | b) | 600 |  | 2
[9 empty] | c) | Alzam | c) | 2019-07-22 | g) | - | c) | 113,335,769.31 | [7 empty] | 2
[9 empty] | d) | 853 CD | d) | - | [11 empty] | 2
|  |  |  | Construction of Dalisay Potable Water System |  | Water System | 162 Households | Contract. | a) | 4664033.76 | a) | CY 2014 | e) | - | a) | 4664033.76 | a) | 100.00% | c) | 82.88% | a) | 3 | On-going (resumption dated January 31, 2020) | 2
|  |  | 1.2 | [5 empty] | b) | Estorco | b) | 2018-01-29 | f) | 39 CD | b) | 4664033.76 | b) | 87.94% | d) | -5.06% | b) | 3 |  | 2
[9 empty] | c) | Ancor Water Resources | c) | 2018-07-23 | g) | - | c) | 3731227.01 | [7 empty] | 2
[9 empty] | d) | 188 CD | d) | 2020-02-11 | [11 empty] | 2
|  |  |  | Construction of Kasilak Potable Water System |  | Water System | 252 Households | Contract. | a) | 7046856.27 | a) | CY 2014 | e) | 72 CD | a) | 7046856.27 | a) | 100.00% | c) | 87.38% | a) | 3 | On-going (resumption dated January 31, 2020) | 2
|  |  | 1.3 | [5 empty] | b) | Estorco | b) | 2018-01-29 | f) | - | b) | 7046856.27 | b) | 83.53% | d) | +3.850% | b) | 3 |  | 2
[9 empty] | c) | Ancor Water Resources | c) | 2018-09-24 | g) | - | c) | 5637485.016 | [7 empty] | 2
[9 empty] | d) | 188 CD | d) | 2020-02-18 | [11 empty] | 2
|  |  |  | Improvement of Sto. Tomas Production Center with Common Facility |  | Bldg. | 1901 sq.m | Contract. | a) | 9825000 | a) | CY 2014 | e) | 72 CD | a) |  | a) |  | c) |  | a) |  | Suspended due to land issue | 2
|  |  | 1.4 | [5 empty] | b) | Azotes | b) | 2018-01-29 | f) | - | b) |  | b) |  | d) |  | b) |  |  | 2
[9 empty] | c) | Manantan | c) | 2018-09-24 | g) | - | c) | - | [7 empty] | 2
[9 empty] | d) | 330 C.D | d) | 2018-12-05 | [11 empty] | 2
|  |  | SLRF 2015 | [7 empty] | a) |  | e) | 65 days | a) |  | a) | 100% | c) | 100% | a) | 3 | Completed as per POW, Financial Documents on Process | 2
|  |  | Rehab. of Jct. Highway-Tuganay-Anibongan-BE Dujali-Kinamayan Provincial Road (Furtheranace) |  |  | Slope protection | - | - | a) | 1911175.99 | b) | 2019-02-18 | f) | 47 days | b) |  | b) |  | d) | 0% | b) | 60 |  | 2
[9 empty] | b) | Balbastro | c) | 2019-09-21 | g) | 9/21/2019 | c) | [8 empty] | 2
[9 empty] | c) | Admin | d) | [12 empty] | 2
[9 empty] | d) | - | [13 empty] | 2
|  | D. | 20% Development Fund CY 2016 | [20 empty] | FS
|  |  | 1. Rural Electrification (Provincewide) |  |  | Elect. | km | Admin | a) | 5000000 | [12 empty] | See projects listed below | AC
[9 empty] | b) | Foronda/Ababon | [13 empty] | AC
[9 empty] | c) | Admin | [13 empty] | AC
[9 empty] | d) | - | [13 empty] | AC
|  |  |  | Inst. of transformer and accessories, Brgy. Kinawitnon |  | Elect. | Households | Admin | a) | 150,000.00 | a) | 2018-07-31 | e) | - | a) | 150,000.00 | a) | - | c) | - | a) | - | For PR - c/o Engr Kim Pao Lu | 2
|  |  | 1.1 | [5 empty] | b) | - | b) | - | f) | - | b) | 150,000.00 | b) | - | d) | - | b) | - |  | 2
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  |  | Electrification expansion to Purok 7, Brgy. Guilon, samal Dist. IGCS |  | Elect. | Households | Admin | a) | 1,537,404.57 | a) | 2019-02-04 | e) | - | a) | 1,537,404.57 | a) | - | c) | - | a) | - | Waiting for NTP - c/o Engr Kim Pao Lu | 2
|  |  | 1.2 | [5 empty] | b) | - | b) | - | f) | - | b) | 1,537,404.57 | b) | - | d) | - | b) | - |  | 2
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  |  | Rural Electrification at brgy. Sta. Cruz, |  | Elect. | Households | Contract | a) | 2000000 | a) | - | e) | - | a) | 2000000 | a) | - | c) | - | a) | - | Delay due to action of Daneco for staking. c/o Engr. Kim | 2
|  |  | 1.3 | [5 empty] | b) | - | b) | - | f) | - | b) | 2000000 | b) | - | d) | - | b) | - |  | 2
[9 empty] | c) | Admin | c) | - | g) | - | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | 2. Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) |  |  | Bldgs./ | sq.m | Admin | a) | 9,000,000.00 | [12 empty] | See project listed below | AC
[9 empty] | b) | Foronda/Ababon | [13 empty] | AC
[9 empty] | c) | PEO | [13 empty] | AC
|  |  |  | 2.1 Construction of Provincial Training Center, Compound Fence, Kinawitnon, Babak District, IGCS |  | Fence | sq.m | Admin | a) | 940,000.00 | a) | 2017-09-19 | e) | - | a) | 940,000.00 | a) | 68.00% | c) | 75.00% | a) | - | Temporarily suspended 4/23/18 due to undemolished structures of illegal settlers | 2
[9 empty] | b) | Pacquiao | b) | 2018-03-12 | f) | - | b) | 940,000.00 | b) | - | d) | - | b) | - |  | 2
[9 empty] | c) | PEO | c) | 2018-06-19 | g) | - | c) | 933,418.80 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  | E. | 20% Development Fund CY 2017 | [20 empty] | FS
|  |  | STIMULUS PROJECTS CY 2017 | [20 empty] | FS
|  |  | CARMEN | [19 empty] | Declared as savings, forwarded to 2020 priority list of projects | AC
|  |  |  | 1. Construction of Concrete Pavement, Tibulao, Carmen |  | Pavement | - | - | a) | 500000 | a) | 2018-03-16 | e) | - | a) | 500000 | a) | - | c) | - | a) | - |  | 2
[9 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 2
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | 2 | Construction of Evaluation Center at Prk. 1, |  | Bldg. |  | Barangay | a) | 500000 | a) | 12/28/17 | e) | - | a) | 500000 | a) | - | c) | 100% | a) | - | Completed | 2
|  |  |  | Asuncion, Carmen |  |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 2
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  |  | 2. Evacuation Center, Anibongan, Carmen |  | Bldg. | - | - | a) | 500000 | a) | 2018-03-16 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Declared as savings, forwarded to 2020 priority list of projects | 2
[9 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 2
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  |  | 3. Const. of Canal Lining @ Brgy. Site, Tubod, Carmen |  | Canal | - | - | a) | 500000 | a) | 2018-03-16 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Declared as savings, forwarded to 2020 priority list of projects | 2
[9 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 2
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  |  | 4. Rehab./Impv't. of Minda Brgy. Hall, Minda, Carmen |  | Bldg. | - | - | a) | 500000 | a) | 2018-05-10 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Declared as savings, forwarded to 2020 priority list of projects | 2
[9 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 2
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | PANABO CITY | [20 empty] | AC
|  |  |  | 1. Const of Market Stall/Building, Consolacion, Panabo City |  | Bldg. | sq.m | MLGU | a) | 500000 | a) | 2017-12-28 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Fund transfer to LGU- 3/28/2019 with check no.2574928 and OR no. 0166514 - Issued warning for Termination of the Contract | 2
[9 empty] | b) | - | b) | 2019-05-28 | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 2
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  |  | 2. Rehab. Of Multi-Purpose Hall (Covered Court), Upper Licanan, Panabo City |  | Footbridge | sq.m | MLGU | a) | 500000 | a) | 2017-12-28 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Fund transfer to LGU- 3/28/2019 with check no.2574927 and OR no. 0166516 - Delivery of Materials on process | 2
[9 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 2
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  |  | 3. Impv't. of Multi-Purpose Gym, Kauswagan, Panabo City |  | GYM | sq.m | MLGU | a) | 500000 | a) | 2019-02-04 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Fund transfer to LGU- 3/28/2019 with check no.2574942 and OR no. 0166515 - procurement on process for bidding 8/5/2019 | 2
[9 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 2
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  |  | 4. Const. of MP Bldg. w/ Electrical installation, San Roque, Panabo City |  | Bldg. | sq.m | MLGU | a) | 500000 | a) | 2018-01-31 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Fund transfer to LGU- 3/28/2019 with check no. 2574942 and OR no 01665515 - procurement on process | 2
[9 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 2
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | 14 | Const. of Multi-Purpose Bldg. (Back Stage/Office), San Nicolas, |  | Bldg. |  | Barangay | a) | 500000 | a) | 12/28/17 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Completed based on POW. Financial Documents on process | 2
|  |  |  | San Nicolas, Panabo City |  |  |  |  | b) | - | b) | 5/21/2019 | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 2
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  |  | 5. Const. of Multi-Purpose Bldg.,Cacao, Panabo City |  | Bldg. | sq.m | MLGU | a) | 300000 | a) | 2017-12-19 | e) | - | a) | 300000 | a) | - | c) | - | a) | - | Issued warning for termination of the contract | 2
[9 empty] | b) | - | b) | 2018-12-14 | f) | - | b) | 300000 | b) | - | d) | - | b) | - |  | 2
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  |  | 6. Const. of Multi-Purpose Bldg. @ A.O. Floriendo National Highschool, Panabo City |  | Bldg. | sq.m | MLGU | a) | 500000 | a) | 2017-12-19 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Fund transfer to LGU- 3/28/2019 with check no. 2574939 and OR no. 0166518 - Materials Delivered. Construction on-going | 2
[9 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 2
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | STO. TOMAS | [20 empty] | AC
|  |  |  | 1. Renov. Of Brgy. Hall, Esperanza, Panabo City |  | Bldg. | sq.m | MLGU | a) | 500000 | a) | 2017-12-28 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Declared as savings, forwarded to 2020 priority list of projects | 2
[9 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 2
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  |  | 2. Const. of Concrete Drainage Canal, Kimamon, Panabo City |  | Drainage | ln.m | MLGU | a) | 500000 | a) | 2017-12-19 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | On-going | 2
[9 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 2
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | IGACOS | [20 empty] | AC
|  |  | 1 | Electrification of Prk. 4 & 6, Brgy. Toril, IGCS |  | Elect. |  |  | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | No abstract | 2
[9 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 2
[9 empty] | c) | PEO | c) | - | g) | - | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  |  | 1. Impv't. of Brgy. Street Electrification at Brgy. Anonang, IGCS |  | Elect. | Households |  | a) | 500000 | a) | 2017-11-28 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Verified at PBO 7/18/2019 that fund is not available. Proposed priority project for 2020\ | 2
[9 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 2
[9 empty] | c) | PEO | c) | - | g) | - | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | 3 | Impv't of Brgy. Hall, Tagpopongan |  |  |  |  | a) | 500000 | a) | 11/28/17 | e) | 259 | a) | 500000 | a) | - | c) | 100% | a) | - | Completed based on POW. Financial Documents on process | 2
|  |  |  | IGACOS |  |  |  |  | b) | Roque | b) | 9/17/2018 | f) | 30 | b) | 500000 | b) | - | d) | - | b) | - |  | 2
[9 empty] | c) | PEO | c) | 12/30/2018 | g) | - | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | 10/15/2019 | [11 empty] | 2
|  | F. | SDH IGCS - CONST. IN PROGRESS - BLGS. CY 2017 | [20 empty] | AC
|  |  | 1 | Construction Perimeter Fence Ph.II (Hospital |  | Fence |  | Admin | a) | 1,305,000.00 | a) | 11/10/17 | e) | 392 | a) | 1,305,000.00 | a) | 100% | c) | 100% | a) | 4 | Completed based on POW. Financial Documents on process | AC
|  |  |  | Compound) Samal District Hospital, IGCS |  |  |  |  | b) | Porras | b) | 03/12/18 | f) | 45 | b) | 1,305,000.00 | b) | - | d) | 1% | b) | 30 |  | AC
[9 empty] | c) | PEO | c) | 06/19/18 | g) | - | c) | 958,597.98 | [7 empty] | AC
[9 empty] | d) | - | d) | [12 empty] | AC
|  | F. | Trust Fund 2017 | [20 empty] | FS
|  | 8 |  | Road Upgrading of Dagohoy - Daligdigon |  | Road | 2.532 km | Contract | a) | 58048310.68 | a) | CY 2017 | e) | - | a) | 58048310.68 | a) | 100.00% | c) | 100% | a) | 16 | Completed as per Physical Accomplishment, Financial Documents on Process | 1 | 1
|  |  |  | Provincial Road |  |  |  |  | b) | Fabiala | b) | 01/05/18 | f) | 205 CD | b) | 58048310.68 | b) | - | d) | 0% | b) | 480 |  | 1
[9 empty] | c) | PUREGOLD | c) | 11/18/18 | g) | - | c) | 29,572,637.70 | [7 empty] | 1
[9 empty] | d) | 246 CD | d) | 03/31/19 | [11 empty] | 1
|  |  |  | Impv’t. of Maligaya-New Camiling Prov’l. |  | Conc. | 2.13 km | Contract. | a) | 50101614.08 | a) | CY 2017 | e) | 76 CD | a) | 57385680 | a) | 100.00% | c) | 100% | a) | 21 | Completed based on POW. Financial Documents on process | 2
|  |  |  | Road w/ Bridge Component,Carmen |  |  |  |  | b) | Mellomida | b) | 12/18/17 | f) | 209 CD | b) | 57385680 | b) | 100% | d) | 0% | b) | 147 |  | 2
[9 empty] | c) | PUREGOLD CONST. | c) | 02/15/19 | g) | - | c) | 36005452 | [7 empty] | 2
[9 empty] | d) | 376 CD | d) | 07/31/19 | [11 empty] | 2
|  |  |  | Road Upgrading of FDR. Rd.3 – |  | Conc. | 10.359 km | Contract. | a) | 119901954.82 | a) | CY 2017 | e) | 47 CD | a) | 119901954.82 | a) | 100.00% | c) | 100% | a) | 10 | Completed based on POW, Financial Documents on Process | 2
|  |  |  | Kimamon – Luna Provincial Road, |  |  |  |  | b) | Comidoy | a) | 12/29/17 | f) | 198 CD | b) | 119901954.82 | b) | 100% | d) | 100% | b) | 220 |  | 2
|  |  |  | Sto. Tomas |  |  |  |  | c) | GP & H CONST. | c) | 12/12/18 | g) | - | c) | 119901954.82 | [7 empty] | 2
[9 empty] | d) | 326 CD | d) | 2019-07-29 | [11 empty] | 2
|  |  |  | Road Upgrading of Anahaw-Maligaya |  | Conc. | 5.18 km | Contract. | a) | 78,228,121.56 | a) | CY 2017 | e) | - | a) | 78,228,121.56 | a) | 100.00% | c) | 100% | a) | 30 | 100% as of August 31, 2019 | 2
|  |  |  | Provincial Road, Carmen |  |  |  |  | b) | Fernandez | b) | 12/24/17 | f) | 306 CD | b) | 78,228,121.56 | b) | 100% | d) | 0% | b) | 660 | Subject for liquidated damages | 2
[9 empty] | c) | MONOLITHIC CONST. | c) | 03/31/19 | g) | - | c) | 76,214,361.38 | [7 empty] | 2
[9 empty] | d) | 210 CD | d) | 2019-06-05 | [11 empty] | 2
|  |  | 1. OPPAP-PAMANA | [20 empty] | AC
|  |  |  | 1.2 Const. of Trading Post, Storage Building with (1) unit Hauling Truck, Prk. Ramihan Datu Abdul, Panabo City |  | Bldg. | sq.m | Contract | a) | 3,975,000.00 | a) | CY 2017 | e) | - | a) | 3,975,000.00 | a) | - | c) | 7.81% | a) | - | On-going | 2
[9 empty] | b) | Azotes | b) | 2019-11-21 | f) | - | b) | 3,975,000.00 | b) | - | d) | - | b) | - |  | 2
[9 empty] | c) | Ultra Core | c) | 2019-04-05 | g) | - | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  |  | 1.2 Construction of Tribal Hall, Sto. Tomas |  | Bldg. | sq.m | Admin | a) | 500000 | a) | CY 2018 | e) | - | a) | 500000 | a) | 100% | c) | 89.5% | a) | 7 | Suspended 6/28/2019, Suspended due to Delivery of Materials J.O, For time extension | 2
[9 empty] | b) | Roque | b) | 2019-05-22 | f) | - | b) | 500000 | b) | - | d) | 0.79% | b) | 110 |  | 2
[9 empty] | c) | Admin | c) | 2019-07-31 | g) | - | c) | - | [7 empty] | 2
[9 empty] | d) | 70 CD | d) | - | [11 empty] | 2
|  | 8 | 1.1 | Construction of 1 unit School Building |  | Bldg. |  | Admin | a) | 1100000 | a) | 02/19/18 | e) | - | a) | 1100000 | a) | 100 | c) | 100 | a) | 6 | Completed based on POW. Financial Documents on process | 1
|  |  |  | Lumabag, Talaingod |  |  |  |  | b) | Dadula | b) | 03/20/19 | f) | 27 CD | b) | 1100000 | b) |  | d) |  | b) | 30 |  | 1
[9 empty] | c) | PEO | c) | 05/19/19 | g) | 06/30/2019 | c) | 595230.5 | [7 empty] | 1
[9 empty] | d) | 60 CD | d) | - | [11 empty] | 1
|  | G. | 20% Development Fund CY 2018 | [20 empty] | FS
|  |  | 1. Repair & Maint. Of Various Local Roads and Drainages |  |  | Road | km. | Admin | a) | 5000000 | [12 empty] | See projects listed below | AC
[9 empty] | b) | [14 empty] | AC
[9 empty] | c) | Admin | [13 empty] | AC
[9 empty] | d) | - | [13 empty] | AC
|  |  | 1.1 | Rehabilitation of Brgy. San Antonio Barangay Road, IGACOS |  | Road | km. | Admin | a) | 130000 | a) | 04/13/18 | e) | - | a) | 130000 | a) | - | c) | - | a) | - | Proposed priority project for 2020 | 2
[9 empty] | b) | Porras/Pacquiao | b) | - | f) | - | b) | 130000 | b) | - | d) | - | b) | - |  | 2
[9 empty] | c) | PEO | c) | - | g) | - | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | 1.2 | Rehabilitation of Brgy. Peñaplata Barangay |  | Road |  | Admin | a) | 139000 | a) | 04/25/18 | e) | 66 CD | a) | 139000 | a) | 100% | c) | 100 | a) | 1 | Completed 8/31/2019 | 2
|  |  |  | Road, IGACOS |  |  |  |  | b) | Porras/Pacquiao | b) | 8/16/2019 | f) | 225 CD | b) | 139000 | b) | - | d) | - | b) | 1 |  | 2
[9 empty] | c) | PEO | c) | 8/31/2019 | g) | - | c) | 139000 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | 1.3 | Rehabilitation of Brgy. Adecor Barangay |  | Road |  | Admin | a) | 138000 | a) | 04/25/18 | e) | 66 CD | a) | 138000 | a) | 60.00% | c) | 60.00% | a) | - | Completed as per POW. Financial Documents on process | 2
|  |  |  | Road, IGACOS |  |  |  |  | b) | Porras/Pacquiao | b) | 10/18/18 | f) | 225 CD | b) | 138000 | b) | - | d) | - | b) | - |  | 2
[9 empty] | c) | PEO | c) | 10/27/19 | g) | - | c) | 111,872.00 | [7 empty] | 2
[9 empty] | d) | - | d) | 10/15/2019 | [11 empty] | 2
|  |  | 1.4 | Rehabilitation of Brgy. Pob. Kaputian |  | Road |  | Admin | a) | 138000 | a) | 04/25/18 | e) | - | a) | 138000 | a) | 100% | c) | 100% | a) | 4 |  | 2
|  |  |  | Barangay Road, IGACOS |  |  |  |  | b) | Porras/Pacquiao | b) | 2019-08-08 | f) | - | b) | 138000 | b) | - | d) | - | b) | 36 | Completed Sept. 22, 2019 | 2
[9 empty] | c) | PEO | c) | 9/22/2019 | g) | 9/22/2019 | c) | - | [7 empty] | 2
[9 empty] | d) | 6/13/19 | d) | - | [11 empty] | 2
|  |  | 2.2 Construction of Water System Projects in Component LGUs |  |  | Water System | Households | Admin/Contract | a) | 9750000 | [12 empty] | See list of projects | AC
[9 empty] | b) | Diosanta | [13 empty] | AC
[9 empty] | c) | PEO | [13 empty] | AC
[9 empty] | d) | - | [13 empty] | AC
|  |  |  | Impv't. of Water System, Brgy. Poblacion |  | Water |  | Admin | a) | 1250000 | a) | 08/24/18 | e) | - | a) | 1250000 | a) | 100% | c) | 85.39% | a) | 8 | Completed (contract by Zular3-Az) September 15, 2019 | 2
|  |  |  | Kaputian (Level II) |  | system |  |  | b) | Porras | b) | 05/3/19 | f) | - | b) | 1250000 | b) | - | d) | -14.61 | b) | 160 |  | 2
[9 empty] | c) | Contract | c) | 08/30/19 | g) | 09/15/2019 | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  |  | 2.2.3 Water System at brgy. Malativas, Panabo City |  | Water System | Households | Admin | a) | 1250000 | a) | - | e) | - | a) | 1250000 | a) | - | c) | - | a) | - | For preparation of POW & Plan c/o PDPM - POSSIBLE TRANSFER OF SITE SUBJECT FOR TRANSFER OF LOCATION . NO DEED OF DONATION | 2
[9 empty] | b) | - | b) | - | f) | - | b) | 1250000 | b) | - | d) | - | b) | - |  | 2
[9 empty] | c) | Admin | c) | - | g) | - | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  |  | 2.2.4 Const. of Potable Water System at Brgy. Tibungol, Panabo City |  | Water System | Households | Admin | a) | 1250000 | a) | 2018-11-21 | e) | - | a) | 1250000 | a) | - | c) | - | a) | - | for implementation | 2
[9 empty] | b) | - | b) | - | f) | - | b) | 1250000 | b) | - | d) | - | b) | - |  | 2
[9 empty] | c) | Admin | c) | - | g) | - | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  |  | 2.2.5 Potable Water System at Brgy. San Remegio Kaputian (Level II WS), Samal |  | Water System | Households | Admin | a) | 3625000 | a) | 2018-10-25 | e) | - | a) | 3625000 | a) | 100% | c) | 74.56% | a) | 4 | On-going | 2
[9 empty] | b) | Diosanta | b) | 2019-07-16 | f) | 99 CD | b) | 3625000 | b) | 72.04% | d) | +2.52% | b) | 88 |  | 2
[9 empty] | c) | Admin | c) | 2020-01-22 | g) | - | c) | - | [7 empty] | 2
[9 empty] | d) | 280 CD | d) | 2020-04-30 | [11 empty] | 2
|  | 11 | 4.3 | Construction of Multi-Purpose Bldg. |  | #REF! | 303.75 sq.m | #REF! | a) | 6748000 | a) | 12/11/18 | e) | - | a) | 6748000 | a) |  | c) | 100% | a) | 25 | Completed | 1
|  |  |  | (PENRO Building), Mankilam, Tagum City |  |  |  |  | b) | Pasiona/Juan | b) | 10/16/18 | f) | 109 | b) | 6748000 | b) | - | d) |  | b) | 750 |  | 1
|  |  |  | (Part of 8,548,000.00) |  |  |  |  | c) | PEO | c) | 9/13/2019 | g) | - | c) | 6560497.45 | [7 empty] | 1
|  |  |  | (P1,800,000.00 - SB # 3 CY 2017) |  |  |  |  | d) | 256 CD | d) | 06/30/19 | [11 empty] | 1
|  | 3 | 4.4 | Repair/Rehab. Of PEO Building (2nd District), Carmen |  | #REF! |  | Admin | a) | 2250000 | a) | 08/10/18 | e) | - | a) | 2250000 | a) | 100% | c) | 100% | a) | 18 | Completed based on POW. Financial Documents on process | 2
[9 empty] | b) | Andoy | b) | 02/18/19 | f) | - | b) | 2250000 | b) | - | d) | 0% | b) | 138 |  | 2
[9 empty] | c) | Admin | c) | 08/23/19 | g) | - | c) | 1577344.8 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  | H. | GENERAL FUND PROPER CY 2018 | [20 empty] | FS
|  |  | STIMULUS PROJECTS | [20 empty] | AC
|  |  | CARMEN | [19 empty] | Plan and POW Approval on process | AC
|  |  | 1 | Completion of Evacuation Center Building, San Isidro, Carmen |  | Bldg. | - | Admin | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - |  | 2
[9 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 2
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | PANABO CITY | [19 empty] | Amended from Const. of New Brgy. Stage due to funding of Phase 1 by the LGU. Plan and POW on process c/o PDPM | AC
|  |  | 1 | Const. of New Brgy. Stage, Phase II San Pedro, Panabo City |  | Stage | - | Admin | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - |  | 2
[9 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 2
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | 2 | Impv't. of Brgy. Road Covered Court, Malativas, Panabo City |  | Court | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Alloted - May 29, 2019, Additional Funding of 500,000.00,SB no. 4 cy 2019 for Allotment Nov 25, 2019 | 2
[9 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 2
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | 3 | Rehab. Of Multi-Purpose Gym & Facililies Maduao, Panabo City |  | Gym | sq.m | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Request for Allotment on process | 2
[9 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 2
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | 4 | Const. of Multi-Purpose Bldg. Sto. Nino, Panabo City |  | Bldg. | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Plan and POW on process c/o PDPM | 2
[9 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 2
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | 5 | Completion of Canopy at DAPCO Covered Court, Dapco, Panabo City |  | Court | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For Plan preparation by PDPM August 5, 2019 | 2
[9 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 2
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | 6 | Perimeter Fence of Day Care Center I & II, Nanyo, Panabo City |  | Bldg. | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For inspection by PDPM for PLAN and POW as of 7/19/2019 | 2
[9 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 2
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | STO. TOMAS | [19 empty] | For amendment in the AIP 3rd revision | AC
|  |  | 1 | Const. of Multi-Purpose Bldg./Compl. Of Covered Court Canopy, Balagunan, Sto. Tomas |  | Bldg. | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - |  | 2
[9 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 2
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | 2 | Const. of Perimeter Fence of Kinamayan Integ,. School, Kinamayan, Sto. Tomas |  | Fence | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Inspected by PDPM for POW and POW July 31, 2019 | 2
[9 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 2
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | B.E. DUJALI | [20 empty] | AC
|  |  | 1 | Concreting of Brgy. Road Canal, Dujali, B.E. Dujali |  | Road | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For inspection by PDPM for PLAN and POW as of 7/19/2019 | 2
[9 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 2
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | 2 | Concreting of Drainage, Tanglaw, B.E. Dujali |  | Drainage | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For inspection by PDPM for PLAN and POW as of 7/19/2019 | 2
[9 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 2
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | 3 | Const. of Bleacher w/ Canopy (Ph.II) and Upgrading of Flooring, Cabay-angan, B.E. Dujali |  | Bleacher | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Check for pick-up as of July 5, 2019 with check no. 0135071 | 2
[9 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 2
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | 4 | Desilting and Concreting of Drainage-main Collector Canal, New Casay, B.E. Dujali |  | Drainage | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For inspection by PDPM for PLAN and POW as of 7/19/2019 | 2
[9 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 2
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | 5 | Const. of Brgy. Multi-Purpose Covered Court, Magupising, B.E. Dujali |  | Covered Court | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For inspection by PDPM for PLAN and POW as of 7/19/2019 | 2
[9 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 2
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | IGCS | [20 empty] | AC
|  |  | 1 | Impv't. of Brgy. Water System, Pichon, IGCS |  | Water System | - | Admin | a) | 500000 | a) | 2018-05-31 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | PR # | 2
[9 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 2
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | 2 | Powerline Expansion Project, Cogon, IGACOS |  | Elect. | - | Contract | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | PR # | 2
[9 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 2
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | 3 | Water System From Prk. 6 - Prk. 2 - Prk. 5A, Tagbay, IGCS |  | Water System | - | Admin | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | PR # | 2
[9 empty] | b) | Pacquiao | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 2
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | 4 | Rehab of Multipurpose Hall, Tagdaliao IGACOS |  | Bldg. | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | proposed realignedment due to project ovelap | 2
[9 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 2
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | 5 | Electrification Project, Kanaan, IGACOS |  | Elect. | Households | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For DANECO staking | 2
[9 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 2
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | 7 | Powerline Expansion Project, Tambo, IGCS |  | Elect. | Households | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Procurement of Materials on process | 2
[9 empty] | b) | Porras | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 2
[9 empty] | c) | Admin | c) | - | g) | - | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | 9 | Construction of Multipurpose Pavement Penaplata, IGCS |  | Bldg. | - | - | a) | 500000 | a) |  | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Amended from Improvement of Brgy Hall due to change Brgy. Priority. Resolution No. 70 series of 2019 dated July 18, 2019. For allotment | 2
[9 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 2
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | 10 | Const. of Concrete fence of New Brgy. Site, San Isidro, IGCS |  | Fence | - | - | a) | 500000 | a) |  | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For Implementation | 2
[9 empty] | b) | Porras | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 2
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | [12 empty] | 2
|  |  | 11 | Electrification of Sitio Baongon-Diamond-Mansanitas, Dadatan, IGCS |  | Elect. | Households | - | a) | 500000 | a) |  | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Procurement on process | 2
[9 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 2
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | 12 | Drilling of Water System,Linusotan, IGCS |  | Water System | - | - | a) | 500000 | a) |  | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For amendment. This project scope of work was included on a separate project titled Construction of Potable Water System at Linusotan, IGACOS. | 2
[9 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 2
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  | I. | 5% Calamity Fund CY 2018 | [20 empty] | 2
|  |  | 1. Prevention and Mitigation | [20 empty] | 2
|  |  | 1.1 Improvement of bridges and cross drainage |  |  | bridges/drainage | - | - | a) | 3000000 | [12 empty] | Declared as savings | 1 | 1
[9 empty] | b) | - | [13 empty] | 1
[9 empty] | c) | PEO | [13 empty] | 1
[9 empty] | d) | - | [13 empty] | 1
|  |  | 1.1.1 | Impv't. of Mabaus Cross Drainage |  | Drainage | - | - | a) | 3,000,000.00 | a) | - | e) | - | a) | 3,000,000.00 | a) | - | c) | - | a) | - | Preparation of POW & Plan c/o PDPM | AC
[9 empty] | b) | - | b) | - | f) | - | b) | 3,000,000.00 | b) | - | d) | - | b) | - |  | AC
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | AC
[9 empty] | d) | - | d) | - | [11 empty] | AC
|  | J. | SUPPLEMENTAL BUDGET # 2 CY 2018 | [20 empty] | 2
|  |  | 1 Const./Compl./Impv't. of Various Gov't. Bldgs., Structures & Facilities (Const. in Progress - Bldgs. & Other Structures | [20 empty] | 2
2
2
|  |  | 1.1 | Const. of DDN Hospital Carmen Zone Annex Bldg. |  | Bldg. | sq.m | Admin | a) | 5,500,000.00 | a) | - | e) | - | a) | 5,500,000.00 | a) | - | c) | - | a) | - | PR ON PROCESS 6/11/2019 | FS
[9 empty] | b) | Estorco | b) | - | f) | - | b) | 5,500,000.00 | b) | - | d) | - | b) | - |  | AC
[9 empty] | c) | PEO | c) | - | g) | - | c) | - | [7 empty] | AC
[9 empty] | d) | - | d) | - | [11 empty] | AC
|  | L. | OPPAP-PAMANA | [20 empty] | 1
|  |  | 1. TRADING POST STORAGE | [20 empty] | 1
|  |  | 1.1 | Trading Post, Storage and Hauling Truck, Purok Ramihan, Datu Abdul, Panabo City |  | Bldg. | sq.m | Contract | a) | 4000000 | a) | CY 2018 | e) | - | a) | 4000000 | a) | 3.74% | c) | 1.91% | a) | - | On-going | 1
[9 empty] | b) | Azotes | b) | 2019-11-21 | f) | - | b) | 4000000 | b) | - | d) | - | b) | - |  | 1
[9 empty] | c) | UltraCore | c) | 2020-04-05 | g) | - | c) | - | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | 1.2 | Trading Post, Storage and Hauling Truck Libuak, Island Garden City of Samal (IGACOS) |  | - | - | - | a) | 4000000 | a) | CY 2018 | e) | - | a) | 4000000 | a) | - | c) | - | a) | - | For bidding | 1
[9 empty] | b) | - | b) | - | f) | - | b) | 4000000 | b) | - | d) | - | b) | - |  | 1
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | FS
|  |  | 2. AGRICULTURAL PRODUCTIVITY SUPPORT PROJECT | [20 empty] | AC
|  |  | 2.1 | Agricultural Productivity Support Project-Fishing Equipment, Tambo, IGACOS |  | - | - | - | a) | 1500000 | a) | - | e) | - | a) | 1500000 | a) | - | c) | - | a) | - | For bidding | 1
[9 empty] | b) | - | b) | - | f) | - | b) | 1500000 | b) | - | d) | - | b) | - |  | 1
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  | M. | GENERAL FUND CY 2019 | [20 empty] | 2
[8 empty] | Admin | a) | 46740177 | [12 empty] | See list of Provincial Roads
| Road ID |  | Maintenance of Various Provincial Roads and Bridges at District 1 |  |  | Road Maintenance | 115.620 km |  | b) | Paraguya | [13 empty] | 2
[9 empty] | c) | PEO | [13 empty] | 2
| 11DAN | [22 empty] | 2
[9 empty] | d) | 261 days | [13 empty] | 2
|  |  | Magatos-Bdry Pagsabangan |  |  | Road Maintenance | 8.33 | MBA | a) | 328740.25 | a) | 01/03/19 | e) | - | a) | 328740.25 | a) | 100% | c) | 100% | a) | 15 | Completed | FS
| 002 | [7 empty] | b) | Crucio | b) | 01/03/19 | f) | - | b) | 328740.25 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 207258.49 | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | Magatos-Bdry Pagsabangan |  |  | Road Maintenance | 8.33 | CBRMC | a) | 270763.53 | a) | 01/03/19 | e) | - | a) | 270763.53 | a) | 100% | c) | 100% | a) | 16 | Completed | 1
| 002 | [7 empty] | b) | Crucio | b) | 03/22/19 | f) | - | b) | 270763.53 | b) | - | d) | - | b) | 450 |  | AP
[9 empty] | c) | CALAFA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | FS
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | AC
|  |  | Ilog-New Bantayan |  |  | Road Maintenance | 2.68 | MBA | a) | 131131.39 | a) | 01/03/19 | e) | - | a) | 131131.39 | a) | 100% | c) | 100% | a) | 15 | Completed | AC
| 003 | [7 empty] | b) | Crucio | b) | 01/16/19 | f) | - | b) | 131131.39 | b) | - | d) | - | b) | 450 |  | AC
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 49,316.69 | [7 empty] | AC | 4
[9 empty] | d) | - | d) | - | [11 empty] | 1 | 4
|  |  | Ilog-New Bantayan |  |  | Road Maintenance | 2.68 | CBRMC | a) | 65925.03 | a) | 01/03/19 | e) | - | a) | 65925.03 | a) | 100% | c) | 100% | a) | 16 | Completed | 1 | 4
| 003 | [7 empty] | b) | Crucio | b) | 03/22/19 | f) | - | b) | 65925.03 | b) | - | d) | - | b) | 450 |  | 1 | 4
[9 empty] | c) | CALAFA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1 | 4
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1 | 4
|  |  | Asuncion -Monte Carlo-Del Pilar |  |  | Road Maintenance | 9.93 | MBA | a) | 474102.88 | a) | 01/03/19 | e) | - | a) | 474102.88 | a) | 100% | c) | 100% | a) | 15 | Completed | 1 | 4
| 005 | [7 empty] | b) | Crucio | b) | 01/03/19 | f) | - | b) | 474102.88 | b) | - | d) | - | b) | 450 |  | 1 | 4
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 240274.49 | [7 empty] | 1 | 4
[9 empty] | d) | - | d) | - | [11 empty] | 1 | 4
|  |  | Asuncion -Monte Carlo-Del Pilar |  |  | Road Maintenance | 9.93 | CBRMC | a) | 355524.28 | a) | 01/03/19 | e) | - | a) | 355524.28 | a) | 100% | c) | 100% | a) | 16 | Completed | 1 | 4
| 005 | [7 empty] | b) | Crucio | b) | 03/22/19 | f) | - | b) | 355524.28 | b) | - | d) | - | b) | 450 |  | 1 | 4
[9 empty] | c) | MAHAYAHAY IFA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1 | 4
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1 | 4
|  |  | Jct. Highway Canatan-Jct. Highway Magatos |  |  | Road Maintenance | 4.85 | MBA | a) | 209808.59 | a) | 01/03/19 | e) | - | a) | 209808.59 | a) | 100% | c) | 100% | a) | 15 | Completed | 1 | 4
| 006 | [7 empty] | b) | Crucio | b) | 02/18/19 | f) | - | b) | 209808.59 | b) | - | d) | - | b) | 450 |  | 1 | 4
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 80652.8 | [7 empty] | 1 | 4
[9 empty] | d) | - | d) | - | [11 empty] | 1 | 4
|  |  | Jct. Highway Canatan-Jct. Highway Magatos |  |  | Road Maintenance | 4.85 | CBRMC | a) | 162458.12 | a) | 01/03/19 | e) | - | a) | 162458.12 | a) | 100% | c) | 100% | a) | 16 | Completed | 1 | 4
| 006 | [7 empty] | b) | Crucio | b) | 03/22/19 | f) | - | b) | 162458.12 | b) | - | d) | - | b) | 450 |  | 1 | 4
[9 empty] | c) | CAMODA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1 | 4
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1 | 4
[24 empty] | 1 | 4
|  |  | Sta. Felomina-San Roque |  |  | Road Maintenance | 7.68 | MBA | a) | 147439.63 | a) | 01/03/19 | e) | - | a) | 147439.63 | a) | 100% | c) | 100% | a) | 15 | Completed | 1 | 4
| 008 | [7 empty] | b) | Crucio | b) | 01/16/19 | f) | - | b) | 147439.63 | b) | - | d) | - | b) | 450 |  | 1 | 4
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 63806.67 | [7 empty] | 1 | 4
[9 empty] | d) | - | d) | - | [11 empty] | 1 | 4
|  |  | Sta. Felomina-San Roque |  |  | Road Maintenance | 7.68 | CBRMC | a) | 261345.67 | a) | 01/03/19 | e) | - | a) | 261345.67 | a) | 100% | c) | 100% | a) | 16 | Completed | 1 | 4
| 008 | [7 empty] | b) | Crucio | b) | 03/25/19 | f) | - | b) | 261345.67 | b) | - | d) | - | b) | 450 |  |  | 4
[9 empty] | c) | STAFFA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1 | 4
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1 | 4
|  |  | Saug-Sonlon-Bdy Longanapan |  |  | Road Maintenance | 11.6 | MBA | a) | 568486.36 | a) | 01/03/19 | e) | - | a) | 568486.36 | a) | 100% | c) | 100% | a) | 15 | Completed | 1 | 4
| 010 | [7 empty] | b) | Crucio | b) | 01/16/19 | f) | - | b) | 568486.36 | b) | - | d) | - | b) | 450 |  | 1 | 4
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 262900.22 | [7 empty] | 1 | 4
[9 empty] | d) | - | d) | - | [11 empty] | 1 | 4
|  |  | Saug-Sonlon-Bdy Longanapan |  |  | Road Maintenance | 11.6 | CBRMC | a) | 185565.56 | a) | 01/03/19 | e) | - | a) | 185565.56 | a) | 100% | c) | 100% | a) | 16 | Completed | 1 | 4
| 010 | [7 empty] | b) | Crucio | b) | 03/26/19 | f) | - | b) | 185565.56 | b) | - | d) | - | b) | 450 |  | 1 | 4
[9 empty] | c) | BINANCIAN LIVESTOCK AFA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1 | 4
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1 | 4
|  |  | Jct. New Visayas-Buan |  |  | Road Maintenance | 2.99 | MBA | a) | 79238.27 | a) | 01/03/19 | e) | - | a) | 79238.27 | a) | 100% | c) | 100% | a) | 15 | Completed | 1 | 4
| 011 | [7 empty] | b) | Crucio | b) | 02/18/19 | f) | - | b) | 79238.27 | b) | - | d) | - | b) | 450 |  | 1 | 4
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 14682.85 | [8 empty] | 4
[9 empty] | d) | - | d) | - | [11 empty] | 1 | 4
|  |  | Jct. New Visayas-Buan |  |  | Road Maintenance | 2.99 | CBRMC | a) | 101242.01 | a) | 01/03/19 | e) | - | a) | 101242.01 | a) | 100% | c) | 100% | a) | 16 | Completed | 1 | 4
| 011 | [7 empty] | b) | Crucio | b) | 03/22/19 | f) | - | b) | 101242.01 | b) | - | d) | - | b) | 450 |  | 1 | 4
[9 empty] | c) | BUAN IFA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1 | 4
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1 | 4
|  |  | San Vicente - Butay |  |  | Road Maintenance | 7.52 | MBA | a) | 209624.2 | a) | 01/03/19 | e) | - | a) | 209624.2 | a) | 100% | c) | 100% | a) | 15 | Completed | 1 | 4
| 013 | [7 empty] | b) | Crucio | b) | 02/18/19 | f) | - | b) | 209624.2 | b) | - | d) | - | b) | 450 |  | 1 | 4
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 56,080.29 | [7 empty] | 1 | 4
[9 empty] | d) | - | d) | - | [11 empty] | 1 | 4
|  |  | San Vicente - Butay |  |  | Road Maintenance | 7.52 | CBRMC | a) | 227205.88 | a) | 01/03/19 | e) | - | a) | 227205.88 | a) | 100% | c) | 100% | a) | 16 | Completed | 1 | 4
| 013 | [7 empty] | b) | Crucio | b) | 03/27/19 | f) | - | b) | 227205.88 | b) | - | d) | - | b) | 450 |  | 1 | 4
[9 empty] | c) | SVMODA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1 | 4
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1 | 4
|  |  | Jct. Highway Doña Andrea - Capungagan |  |  | Road Maintenance | 8.7 | MBA | a) | 230835.16 | a) | 01/03/19 | e) | - | a) | 230835.16 | a) | 100% | c) | 100% | a) | 15 | Completed | 1 | 4
| 014 | [7 empty] | b) | Crucio | b) | 02/18/19 | f) | - | b) | 230835.16 | b) | - | d) | - | b) | 450 |  | 1 | 4
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 60,629.26 | [7 empty] | 1 | 4
[9 empty] | d) | - | d) | - | [11 empty] | 1 | 4
[24 empty] | 1 | 4
|  |  | Jct. Highway Doña Andrea - Capungagan |  |  | Road Maintenance | 8.7 | CBRMC | a) | 294308.14 | a) | 01/03/19 | e) | - | a) | 294308.14 | a) | 100% | c) | 100% | a) | 16 | Completed | 1 | 4
| 014 | [7 empty] | b) | Crucio | b) | 03/28/19 | f) | - | b) | 294308.14 | b) | - | d) | - | b) | 450 |  | 1 | 4
[9 empty] | c) | CAPUNGAGAN MPC | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1 | 4
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1 | 4
|  |  | Semong-Palma Gil |  |  | Road Maintenance | 2.73 | MBA | a) | 147289.98 | a) | 01/03/19 | e) | - | a) | 147289.98 | a) | 100% | c) | 100% | a) | 15 | Completed | 1 | 4
| 018 | [7 empty] | b) | Crucio | b) | 02/18/19 | f) | - | b) | 147289.98 | b) | - | d) | - | b) | 450 |  | 1 | 4
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 71745.43 | [7 empty] | 1 | 4
[9 empty] | d) | - | d) | - | [11 empty] | 1 | 4
[24 empty] | 1 | 4
[24 empty] | 1 | 4
[24 empty] | 1 | 4
|  |  | Semong-Palma Gil |  |  | Road Maintenance | 2.73 | CBRMC | a) | 49186.05 | a) | 01/03/19 | e) | - | a) | 49186.05 | a) | 100% | c) | 100% | a) | 16 | Completed | 1 | 4
| 018 | [7 empty] | b) | Crucio | b) | 03/22/19 | f) | - | b) | 49186.05 | b) | - | d) | - | b) | 450 |  | 1 | 4
[9 empty] | c) | PALMA GIL FA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1 | 4
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1 | 4
|  |  | Daligdigon - Dagohoy |  |  | Road Maintenance | 3.34 | MBA | a) | 148835.45 | a) | 01/03/19 | e) | - | a) | 148835.45 | a) | 100% | c) | 100% | a) | - | Completed | 1 | 4
| 020 | [7 empty] | b) | Crucio | b) | - | f) | - | b) | 148835.45 | b) | - | d) | - | b) | - |  | 1 | 4
[9 empty] | c) | PEO | c) | - | g) | 2019-12-31 | c) | - | [7 empty] | 1 | 4
[9 empty] | d) | - | d) | - | [12 empty] | 4
|  |  | Daligdigon - Dagohoy |  |  | Road Maintenance | 3.34 | CBRMC | a) | 68279.5 | a) | 01/03/19 | e) | - | a) | 68279.5 | a) | 100% | c) | 100% | a) | 16 | Completed | 1 | 4
| 020 | [7 empty] | b) | Crucio | b) | 03/22/19 | f) | - | b) | 68279.5 | b) | - | d) | - | b) | 450 |  | 1 | 4
[9 empty] | c) | PALMA GIL FA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1 | 4
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1 | 4
|  |  | Jct. Sampao-Bdry. Mamacao |  |  | Road Maintenance | 4.98 | MBA | a) | 154200.78 | a) | 01/03/19 | e) | - | a) | 154200.78 | a) | 100% | c) | 100% | a) | 15 | Completed | 1 | 4
| 025 | [7 empty] | b) | Crucio | b) | 02/18/19 | f) | - | b) | 154200.78 | b) | - | d) | - | b) | 450 |  | 1 | 4
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 24,296.87 | [7 empty] | 1 | 4
[9 empty] | d) | - | d) | - | [11 empty] | 1 | 4
|  |  | Jct. Sampao-Bdry. Mamacao |  |  | Road Maintenance | 4.98 | CBRMC | a) | 169521.51 | a) | 01/03/19 | e) | - | a) | 169521.51 | a) | 100% | c) | 100% | a) | 16 | Completed |  | 4
| 025 | [7 empty] | b) | Crucio | b) | 03/26/19 | f) | - | b) | 169521.51 | b) | - | d) | - | b) | 450 |  |  | 4
[9 empty] | c) | AMS KAPALONG | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [8 empty] | 4
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1 | 4
|  |  | Jct. Highway Luna-Mamacao-Narra |  |  | Road Maintenance | 9.17 | MBA | a) | 357957.66 | a) | 01/03/19 | e) | - | a) | 357957.66 | a) | 100% | c) | 100% | a) | 15 | Completed | 1 | 4
| 026 | [7 empty] | b) | Crucio | b) | 02/18/19 | f) | - | b) | 357957.66 | b) | - | d) | - | b) | 450 |  | 1 | 4
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 127,996.16 | [7 empty] | 1 | 4
[9 empty] | d) | - | d) | - | [11 empty] | 1 | 4
|  |  | Jct. Highway Luna-Mamacao-Narra |  |  | Road Maintenance | 9.17 | CBRMC | a) | 313143.91 | a) | 01/03/19 | e) | - | a) | 313143.91 | a) | 100% | c) | 100% | a) | 16 | Completed | 1 | 4
| 026 | [7 empty] | b) | Crucio | b) | 03/26/19 | f) | - | b) | 313143.91 | b) | - | d) | - | b) | 450 |  | 1 | 4
[9 empty] | c) | AMS KAPALONG | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1 | 4
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1 | 4
|  |  | Jct. Gabuyan-Katipunan-Bucana |  |  | Road Maintenance | 5.89 | MBA | a) | 294403.23 | a) | 01/03/19 | e) | - | a) | 294403.23 | a) | 100% | c) | 100% | a) | 15 | Completed | 1 | 4
| 027 | [7 empty] | b) | Crucio | b) | 02/18/19 | f) | - | b) | 294403.23 | b) | - | d) | - | b) | 450 |  | 1 | 4
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 126,179.97 | [7 empty] | 1 | 4
[9 empty] | d) | - | d) | - | [11 empty] | 1 | 4
|  |  | Jct. Gabuyan-Katipunan-Bucana |  |  | Road Maintenance | 5.89 | CBRMC | a) | 129495.6 | a) | 01/03/19 | e) | - | a) | 129495.6 | a) | 100% | c) | 100% | a) | 16 | Completed | 1 | 4
| 027 | [7 empty] | b) | Crucio | b) | 03/26/19 | f) | - | b) | 129495.6 | b) | - | d) | - | b) | 450 |  | 1 | 4
[9 empty] | c) | MANGULIBAS FA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1 | 4
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1 | 4
|  |  | Capungagan-Mabuhay-Pandulian |  |  | Road Maintenance | 5.57 | MBA | a) | 294917.73 | a) | 01/03/19 | e) | - | a) | 294917.73 | a) | 100% | c) | 100% | a) | 15 | Completed | 1 | 4
| 028 | [7 empty] | b) | Crucio | b) | 02/18/19 | f) | - | b) | 294917.73 | b) | - | d) | - | b) | 450 |  | 1 | 4
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1 | 4
[9 empty] | d) | - | d) | - | [11 empty] | 1 | 4
[24 empty] | 1 | 4
|  |  | Capungagan-Mabuhay-Pandulian |  |  | Road Maintenance | 5.57 | CBRMC | a) | 105950.95 | a) | 01/03/19 | e) | - | a) | 105950.95 | a) | 100% | c) | 100% | a) | 16 | Completed | 1 | 4
| 028 | [7 empty] | b) | Crucio | b) | 03/28/19 | f) | - | b) | 105950.95 | b) | - | d) | - | b) | 450 |  | 1 | 4
[9 empty] | c) | CAPUNGAGAN MPC | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1 | 4
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1 | 4
|  |  | Florida - New Boholano |  |  | Road Maintenance | 2.54 | MBA | a) | 95863.17 | a) | 01/03/19 | e) | - | a) | 95863.17 | a) | 100% | c) | 100% | a) | 15 | Completed | 1 | 4
| 030 | [7 empty] | b) | Crucio | b) | 02/18/19 | f) | - | b) | 95863.17 | b) | - | d) | - | b) | 450 |  | 1 | 4
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 31,418.99 | [7 empty] | 1 | 4
[9 empty] | d) | - | d) | - | [11 empty] | 1 | 4
|  |  | Florida - New Boholano |  |  | Road Maintenance | 2.54 | CBRMC | a) | 47425.27 | a) | 01/03/19 | e) | - | a) | 47425.27 | a) | 100% | c) | 100% | a) | 16 | Completed | 1 | 4
| 030 | [7 empty] | b) | Crucio | b) | 03/28/19 | f) | - | b) | 47425.27 | b) | - | d) | - | b) | 450 |  | 1 | 4
[9 empty] | c) | SUPRA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1 | 4
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1 | 4
|  |  | Jct. New Boholano - New Loon |  |  | Road Maintenance | 4.77 | MBA | a) | 140549.84 | a) | 01/03/19 | e) | - | a) | 140549.84 | a) | 100% | c) | 100% | a) | 15 | Completed | 1 | 4
| 031 | [7 empty] | b) | Crucio | b) | 02/18/19 | f) | - | b) | 140549.84 | b) | - | d) | - | b) | 450 |  | 1 | 4
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 40,056.38 | [7 empty] | 1 | 4
[9 empty] | d) | - | d) | - | [11 empty] | 1 | 4
[24 empty] | 1 | 4
|  |  | Jct. New Boholano - New Loon |  |  | Road Maintenance | 4.77 | CBRMC | a) | 169521.51 | a) | 01/03/19 | e) | - | a) | 169521.51 | a) | 100% | c) | 100% | a) | 16 | Completed | 1 | 4
| 031 | [7 empty] | b) | Crucio | b) | 03/28/19 | f) | - | b) | 169521.51 | b) | - | d) | - | b) | 450 |  |  | 4
[9 empty] | c) | NEW LOON FA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1 | 4
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1 | 4
|  |  | Florida-Suaon-Jct. Gupitan |  |  | Road Maintenance | 15.57 | MBA | a) | 707038.05 | a) | 01/03/19 | e) | - | a) | 707038.05 | a) | 100% | c) | 100% | a) | 15 | Completed | 1 | 4
| 032 | [7 empty] | b) | Crucio | b) | 01/16/19 | f) | - | b) | 707038.05 | b) | - | d) | - | b) | 450 |  | 1 | 4
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 226,.062.60 | [7 empty] | 1 | 4
[9 empty] | d) | - | d) | - | [11 empty] | 1 | 4
|  |  | Florida-Suaon-Jct. Gupitan |  |  | Road Maintenance | 15.57 | CBRMC | a) | 419094.85 | a) | 01/03/19 | e) | - | a) | 419094.85 | a) | 100% | c) | 100% | a) | 16 | Completed | 1 | 4
| 032 | [7 empty] | b) | Crucio | b) | 03/28/19 | f) | - | b) | 419094.85 | b) | - | d) | - | b) | 450 |  | 1 | 4
[9 empty] | c) | SUPRA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1 | 4
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1 | 4
|  |  | Km. 15, Kipalili-New Loon |  |  | Road Maintenance | 6.93 | MBA | a) | 367659.97 | a) | 01/03/19 | e) | - | a) | 367659.97 | a) | 100% | c) | 100% | a) | 15 | Completed | 1 | 4
| 034 | [7 empty] | b) | Crucio | b) | 02/01/19 | f) | - | b) | 367659.97 | b) | - | d) | - | b) | 450 |  | 1 | 4
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 112,175.78 | [7 empty] | 1 | 4
[9 empty] | d) | - | d) | - | [11 empty] | 1 | 4
|  |  | Km. 15, Kipalili-New Loon |  |  | Road Maintenance | 6.93 | CBRMC | a) | 237801.01 | a) | 01/03/19 | e) | - | a) | 237801.01 | a) | 100% | c) | 100% | a) | 16 | Completed | 1 | 4
| 034 | [7 empty] | b) | Crucio | b) | 03/26/19 | f) | - | b) | 237801.01 | b) | - | d) | - | b) | 480 |  |  | 4
[9 empty] | c) | KIPALILI FA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1 | 4
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1 | 4
|  |  | Jct. Suaon-Libuton |  |  | Road Maintenance | 7.26 | MBA | a) | 44015.68 | a) | 01/03/19 | e) | - | a) | 44015.68 | a) | 100% | c) | 100% | a) | 15 | Completed | 1 | 4
| 035 | [7 empty] | b) | Crucio | b) | 01/16/19 | f) | - | b) | 44015.68 | b) | - | d) | - | b) | 450 |  | 1 | 4
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 24,980.86 | [7 empty] | 1 | 4
[9 empty] | d) | - | d) | - | [11 empty] | 1 | 4
|  |  | Jct. Suaon-Libuton |  |  | Road Maintenance | 7.26 | CBRMC | a) | 91664.91 | a) | 01/03/19 | e) | - | a) | 91664.91 | a) | 100% | c) | 100% | a) | 16 | Completed | 1 | 4
| 035 | [7 empty] | b) | Crucio | b) | 03/22/19 | f) | - | b) | 91664.91 | b) | - | d) | - | b) | 480 |  | 1 | 4
[9 empty] | c) | AALLI | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1 | 4
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1 | 4
[24 empty] | 1 | 4
|  |  | Datu Balong - Pinamuno |  |  | Road Maintenance | 2.74 | MBA | a) | 95458.24 | a) | 01/03/19 | e) | - | a) | 95458.24 | a) | 100% | c) | 100% | a) | 15 | Completed | 1 | 4
| 040 | [7 empty] | b) | Crucio | b) | 03/01/19 | f) | - | b) | 95458.24 | b) | - | d) | - | b) | 450 |  | 1 | 4
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 12,625.00 | [7 empty] | 1 | 4
[9 empty] | d) | - | d) | - | [11 empty] | 1 | 4
|  |  | Datu Balong - Pinamuno |  |  | Road Maintenance | 2.74 | CBRMC | a) | 63570.57 | a) | 01/03/19 | e) | - | a) | 63570.57 | a) | 100% | c) | 100% | a) | 16 | Completed | 1 | 4
| 040 | [7 empty] | b) | Crucio | b) | 03/28/19 | f) | - | b) | 63570.57 | b) | - | d) | - | b) | 480 |  | 1 | 4
[9 empty] | c) | DATU BALONG FA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1 | 4
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1 | 4
|  |  | Sawata - Mamangan - Pinamuno |  |  | Road Maintenance | 14.48 | MBA | a) | 545390.17 | a) | 01/03/19 | e) | - | a) | 545390.17 | a) | 100% | c) | 100% | a) | 15 | Completed | 1 | 4
| 041 | [7 empty] | b) | Crucio | b) | 02/01/19 | f) | - | b) | 545390.17 | b) | - | d) | - | b) | 450 |  |  | 4
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 196,076.60 | [7 empty] | 1 | 4
[9 empty] | d) | - | d) | - | [11 empty] | 1 | 4
|  |  | Sawata - Mamangan - Pinamuno |  |  | Road Maintenance | 14.48 | CBRMC | a) | 508564.54 | a) | 01/03/19 | e) | - | a) | 508564.54 | a) | 100% | c) | 100% | a) | 16 | Completed | 1 | 4
| 041 | [7 empty] | b) | Crucio | b) | 03/22/19 | f) | - | b) | 508564.54 | b) | - | d) | - | b) | 480 |  | 1 | 4
[9 empty] | c) | SAWATA DFA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1 | 4
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1 | 4
|  |  | Igangon - Sawata |  |  | Road Maintenance | 9.66 | MBA | a) | 497447.77 | a) | 01/03/19 | e) | - | a) | 497447.77 | a) | 100% | c) | 100% | a) | 15 | Completed | 1 | 4
| 042 | [7 empty] | b) | Crucio | b) | 02/01/19 | f) | - | b) | 497447.77 | b) | - | d) | - | b) | 450 |  | 1 | 4
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [8 empty] | 4
[9 empty] | d) | - | d) | - | [11 empty] | 1 | 4
|  |  | Igangon - Sawata |  |  | Road Maintenance | 9.66 | CBRMC | a) | 197775.1 | a) | 01/03/19 | e) | - | a) | 197775.1 | a) | 100% | c) | 100% | a) | 16 | Completed | 1 | 4
| 042 | [7 empty] | b) | Crucio | b) | 03/22/19 | f) | - | b) | 197775.1 | b) | - | d) | - | b) | 480 |  | 1 | 4
[9 empty] | c) | SAWATA DFA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1 | 4
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1 | 4
[24 empty] | 1 | 4
[24 empty] | 1 | 4
|  |  | New Corella - Sto. Niño - Macgum |  |  | Road Maintenance | 17.11 | MBA | a) | 606294.08 | a) | 01/03/19 | e) | - | a) | 606294.08 | a) | 100% | c) | 100% | a) | 15 | Completed | 1 | 4
| 044 | [7 empty] | b) | Crucio | b) | 01/03/19 | f) | - | b) | 606294.08 | b) | - | d) | - | b) | 450 |  | 1 | 4
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 246,619.77 | [7 empty] | 1 | 4
[9 empty] | d) | - | d) | - | [11 empty] | 1 | 4
|  |  | New Corella - Sto. Niño - Macgum |  |  | Road Maintenance | 17.11 | CBRMC | a) | 308434.97 | a) | 01/03/19 | e) | - | a) | 308434.97 | a) | 100% | c) | 100% | a) | 16 | Completed | 1 | 4
| 044 | [7 empty] | b) | Crucio | b) | 03/26/19 | f) | - | b) | 308434.97 | b) | - | d) | - | b) | 480 |  | 1 | 4
[9 empty] | c) | SAN ISIDRO FA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1 | 4
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1 | 4
|  |  | Tagaytay - Buan |  |  | Road Maintenance | 4.92 | MBA | a) | 173197.37 | a) | 01/03/19 | e) | - | a) | 173197.37 | a) | 100% | c) | 100% | a) | 15 | Completed | 1 | 4
| 045 | [7 empty] | b) | Crucio | b) | 03/18/19 | f) | - | b) | 173197.37 | b) | - | d) | - | b) | 450 |  | 1 | 4
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 26254.58 | [7 empty] | 1 | 4
[9 empty] | d) | - | d) | - | [11 empty] | 1 | 4
|  |  | Tagaytay - Buan |  |  | Road Maintenance | 4.92 | CBRMC | a) | 131850.07 | a) | 01/03/19 | e) | - | a) | 131850.07 | a) | 100% | c) | 100% | a) | 16 | Completed | 1 | 4
| 045 | [7 empty] | b) | Crucio | b) | 03/22/19 | f) | - | b) | 131850.07 | b) | - | d) | - | b) | 480 |  | 1 | 4
[9 empty] | c) | BUAN IFA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1 | 4
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1 | 4
|  |  | limbaan - Sto. Niño |  |  | Road Maintenance | 3.19 | MBA | a) | 153706.77 | a) | 01/03/19 | e) | - | a) | 153706.77 | a) | 100% | c) | 100% | a) | 15 | Completed |  | 4
| 049 | [7 empty] | b) | Crucio | b) | 03/01/19 | f) | - | b) | 153706.77 | b) | - | d) | - | b) | 450 |  |  | 4
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 32534.49 | [7 empty] | 1 | 4
[9 empty] | d) | - | d) | - | [11 empty] | 1 | 4
|  |  | limbaan - Sto. Niño |  |  | Road Maintenance | 3.19 | CBRMC | a) | 53657.51 | a) | 01/03/19 | e) | - | a) | 53657.51 | a) | 100% | c) | 100% | a) | - | Completed | 1 | 4
| 049 | [7 empty] | b) | Crucio | b) | - | f) | - | b) | 53657.51 | b) | - | d) | - | b) | - |  | 1 | 4
[9 empty] | c) | - | c) | - | g) | 2019-12-31 | c) | - | [7 empty] | 1 | 4
[9 empty] | d) | - | d) | - | [11 empty] | 1 | 4
|  |  | Del Pilar - Jct. Silangan |  |  | Road Maintenance | 4.17 | MBA | a) | 187097.4 | a) | 01/03/19 | e) | - | a) | 187097.4 | a) | 100% | c) | 100% | a) | 15 | Completed | 1 | 4
| 051 | [7 empty] | b) | Crucio | b) | 03/18/19 | f) | - | b) | 187097.4 | b) | - | d) | - | b) | 450 |  | 1 | 4
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 94181.74 | [7 empty] | 1 | 4
[9 empty] | d) | - | d) | - | [11 empty] | 1 | 4
|  |  | Del Pilar - Jct. Silangan |  |  | Road Maintenance | 4.17 | CBRMC | a) | 113014.34 | a) | 01/03/19 | e) | - | a) | 113014.34 | a) | 100% | c) | 100% | a) | 16 | Completed | 1 | 4
| 051 | [7 empty] | b) | Crucio | b) | 03/26/19 | f) | - | b) | 113014.34 | b) | - | d) | - | b) | 480 |  | 1 | 4
[9 empty] | c) | DURIAN DACUDAO | c) | 12/31/19 | g) | - | c) | - | [7 empty] | 1 | 4
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1 | 4
|  |  | New Corella - New Sambog - Silangan |  |  | Road Maintenance | 5.1 | MBA | a) | 201994.35 | a) | 01/03/19 | e) | - | a) | 201994.35 | a) | 100% | c) | 100% | a) | 15 | Completed | 1 | 4
| 052 | [7 empty] | b) | Crucio | b) | 03/01/19 | f) | - | b) | 201994.35 | b) | - | d) | - | b) | 450 |  | 1 | 4
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 63402.48 | [7 empty] | 1 | 4
[9 empty] | d) | - | d) | - | [11 empty] | 1 | 4
|  |  | New Corella - New Sambog - Silangan |  |  | Road Maintenance | 5.1 | CBRMC | a) | 131850.07 | a) | 01/03/19 | e) | - | a) | 131850.07 | a) | 100% | c) | 100% | a) | 16 | Completed | 1 | 4
| 052 | [7 empty] | b) | Crucio | b) | 03/26/19 | f) | - | b) | 131850.07 | b) | - | d) | - | b) | 480 |  | 1 | 4
[9 empty] | c) | DURIAN DACUDAO | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1 | 4
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1 | 4
|  |  | Sta. Fe - Del Monte |  |  | Road Maintenance | 3.34 | MBA | a) | 37923.51 | a) | 01/03/19 | e) | - | a) | 37923.51 | a) | 100% | c) | 100% | a) | 15 | Completed | 1 | 4
| 056 | [7 empty] | b) | Crucio | b) | 03/18/19 | f) | - | b) | 37923.51 | b) | - | d) | - | b) | 450 |  | 1 | 4
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 36595.13 | [7 empty] | 1 | 4
[9 empty] | d) | - | d) | - | [11 empty] | 1 | 4
|  |  | Sta. Fe - Del Monte |  |  | Road Maintenance | 3.34 | CBRMC | a) | 70633.96 | a) | 01/03/19 | e) | - | a) | 70633.96 | a) | 100% | c) | 100% | a) | 16 | Completed | 1 | 4
| 056 | [7 empty] | b) | Crucio | b) | 03/21/19 | f) | - | b) | 70633.96 | b) | - | d) | - | b) | 480 |  | 1 | 4
[9 empty] | c) | DEL MONTE CACAO | c) | 12/31/19 | g) | 2019-12-31 | c) | 4,872.18 | [7 empty] | 1 | 4
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1 | 4
|  |  | New Corella - New Bohol |  |  | Road Maintenance | 11.54 | MBA | a) | 356226.67 | a) | 01/03/19 | e) | - | a) | 356226.67 | a) | 100% | c) | 100% | a) | 15 | Completed | 1 | 4
| 058 | [7 empty] | b) | Crucio | b) | 02/01/19 | f) | - | b) | 356226.67 | b) | - | d) | - | b) | 450 |  | 1 | 4
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 110,982.71 | [7 empty] | 1 | 4
[9 empty] | d) | - | d) | - | [11 empty] | 1 | 4
|  |  | New Corella - New Bohol |  |  | Road Maintenance | 11.54 | CBRMC | a) | 190711.7 | a) | 01/03/19 | e) | - | a) | 190711.7 | a) | 100% | c) | 100% | a) | 16 | Completed | 1 | 4
| 058 | [7 empty] | b) | Crucio | b) | 03/22/19 | f) | - | b) | 190711.7 | b) | - | d) | - | b) | 480 |  | 1 | 4
[9 empty] | c) | SAN JOSE COCONUT | c) | 12/31/19 | g) | 2019-12-31 | c) | 5,847.18 | [7 empty] | 1 | 4
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1 | 4
[24 empty] | 1 | 4
[24 empty] | 1 | 4
|  |  | Jct. Carcor - Prk. 9 Bagsak |  |  | Road Maintenance | 2.5 | MBA | a) | 108618.49 | a) | 01/03/19 | e) | - | a) | 108618.49 | a) | 100% | c. | 100% | a) | 15 | Completed | 1 | 4
| 059 | [7 empty] | b) | Crucio | b) | 03/01/19 | f) | - | b) | 108618.49 | b) | - | d) |  | b) | 480 |  | 1 | 4
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 79952.88 | [7 empty] | 1 | 4
[9 empty] | d) | - | d) | - | [11 empty] | 1 | 4
[24 empty] | 1 | 4
[24 empty] | 1 | 4
[24 empty] | 1 | 4
|  |  | Jct. Carcor - Prk. 9 Bagsak |  |  | Road Maintenance | 2.5 | CBRMC | a) | 42284.76 | a) | 01/03/19 | e) | - | a) | 42284.76 | a) | 100% | c) | 100% | a) | 16 | Completed | 1 | 4
| 059 | [7 empty] | b) | Crucio | b) | 03/22/19 | f) | - | b) | 42284.76 | b) | - | d) | - | b) | 480 |  |  | 4
[9 empty] | c) | CARCOR MOTOR | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1 | 4
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1 | 4
|  |  | Carcor - Jct. Kauswagan |  |  | Road Maintenance | 4.32 | MBA | a) | 264514.71 | a) | 01/03/19 | e) | - | a) | 264514.71 | a) | 100% | c) | 100% | a) | 15 | Completed | 1 | 4
| 060 | [7 empty] | b) | Crucio | b) | 03/18/19 | f) | - | b) | 264514.71 | b) | - | d) |  | b) | 450 |  | 1 | 4
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 80733.11 | [7 empty] | 1 | 4
[9 empty] | d) | - | d) | - | [11 empty] | 1 | 4
|  |  | Carcor - Jct. Kauswagan |  |  | Road Maintenance | 4.32 | CBRMC | a) | 48398.27 | a) | 01/03/19 | e) | - | a) | 48398.27 | a) | 100% | c) | 100% | a) | 16 | Completed | 1 | 4
| 060 | [7 empty] | b) | Crucio | b) | 03/22/19 | f) | - | b) | 48398.27 | b) | - | d) | - | b) | 480 |  | 1 | 4
[9 empty] | c) | CARCOR MOTOR | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [8 empty] | 4
[9 empty] | d) | 3 quarters | d) | -
|  |  | Del Pilar - Prk 9 Bagsak - San Jose |  |  | Road Maintenance | 4.99 | MBA | a) | 170215.76 | a) | 01/03/19 | e) | - | a) | 170215.76 | a) | 100% | c) | 100% | a) | 15 | Completed | 1 | 4
| 061 | [7 empty] | b) | Crucio | b) | 03/01/19 | f) | - | b) | 170215.76 | b) | - | d) | - | b) | 450 |  | 1 | 4
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 87595.63 | [7 empty] | 1 | 4
[9 empty] | d) | - | d) | - | [11 empty] | 1 | 4
|  |  | Del Pilar - Prk 9 Bagsak - San Jose |  |  | Road Maintenance | 4.99 | CBRMC | a) | 223674.22 | a) | 01/03/19 | e) | - | a) | 223674.22 | a) | 100% | c) | 100% | a) | 16 | Completed |  | 4
| 061 | [7 empty] | b) | Crucio | b) | 03/22/19 | f) | - | b) | 223674.22 | b) | - | d) | - | b) | 480 |  |  | 4
[9 empty] | c) | SAN JOSE COCONUT | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [8 empty] | 4
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1 | 4
|  |  | San Juan - New Talisay |  |  | Road Maintenance | 5.13 | MBA | a) | 306261.25 | a) | 01/03/19 | e) | - | a) | 306261.25 | a) | 100% | c) | 100% | a) | 15 | Completed | 1 | 4
| 063 | [7 empty] | b) | Crucio | b) | 02/01/19 | f) | - | b) | 306261.25 | b) | - | d) | - | b) | 450 |  | 1 | 4
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 85123.48 | [7 empty] | 1 | 4
[9 empty] | d) | - | d) | - | [11 empty] | 1 | 4
|  |  | San Juan - New Talisay |  |  | Road Maintenance | 5.13 | CBRMC | a) | 93906.31 | a) | 01/03/19 | e) | - | a) | 93906.31 | a) | 100% | c) | 100% | a) | 16 | Completed | 1 | 4
| 063 | [7 empty] | b) | Crucio | b) | 03/26/19 | f) | - | b) | 93906.31 | b) | - | d) | - | b) | 480 |  | 1 | 4
[9 empty] | c) | NEW TALISAY IAWA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [8 empty] | 4
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1 | 4
|  |  | San Juan - kauswagan - New Cortez |  |  | Road Maintenance | 3.22 | MBA | a) | 187879.04 | a) | 01/03/19 | e) | - | a) | 187879.04 | a) | 100% | c) | 100% | a) | 15 | Completed | 1 | 4
| 064 | [7 empty] | b) | Crucio | b) | 03/18/19 | f) | - | b) | 187879.04 | b) | - | d) | - | b) | 450 |  | 1 | 4
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 3,025.00 | [7 empty] | 1 | 4
[9 empty] | d) | - | d) | - | [11 empty] | 1 | 4
[24 empty] | 1 | 4
[24 empty] | 1 | 4
|  |  | San Juan - kauswagan - New Cortez |  |  | Road Maintenance | 3.22 | CBRMC | a) | 63298.26 | a) | 01/03/19 | e) | - | a) | 63298.26 | a) | 100% | c) | 100% | a) | 16 | Completed | 1 | 4
| 064 | [7 empty] | b) | Crucio | b) | 03/22/19 | f) | - | b) | 63298.26 | b) | - | d) | - | b) | 480 |  | 1 | 4
[9 empty] | c) | SAN JOSE COCONUT | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1 | 4
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1 | 4
|  |  | New Bohol - Jct. El Unido |  |  | Road Maintenance | 2.12 | MBA | a) | 54989.06 | a) | 01/03/19 | e) | - | a) | 54989.06 | a) | 100% | c) | 100% | a) | 15 | Completed | 1 | 4
| 065 | [7 empty] | b) | Crucio | b) | 03/01/19 | f) | - | b) | 54989.06 | b) | - | d) | - | b) | 450 |  | 1 | 4
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 21021.99 | [7 empty] | 1 | 4
[9 empty] | d) | - | d) | - | [11 empty] | 1 | 4
|  |  | New Bohol - Jct. El Unido |  |  | Road Maintenance | 2.12 | CBRMC | a) | 58861.64 | a) | 01/03/19 | e) | - | a) | 58861.64 | a) | 100% | c) | 100% | a) | 16 | Completed |  | 4
| 065 | [7 empty] | b) | Crucio | b) | 03/26/19 | f) | - | b) | 58861.64 | b) | - | d) | - | b) | 480 |  | 1 | 4
[9 empty] | c) | MANDISKAB TRIBAL | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1 | 4
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1 | 4
[24 empty] | 1 | 4
[24 empty] | 1 | 4
|  |  | New Corella - El unido - Jct. Mesaoy |  |  | Road Maintenance | 8.63 | MBA | a) | 388002.46 | a) | 01/03/19 | e) | - | a) | 388002.46 | a) | 100% | c) | 100% | a) | 15 | Completed | 1 | 4
| 066 | [7 empty] | b) | Crucio | b) | 02/11/19 | f) | - | b) | 388002.46 | b) | - | d) | - | b) | 450 |  | 1 | 4
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 58142.76 | [8 empty] | 4
[9 empty] | d) | - | d) | - | [12 empty] | 4
|  |  | New Corella - El unido - Jct. Mesaoy |  |  | Road Maintenance | 8.63 | CBRMC | a) | 233092.08 | a) | 01/03/19 | e) | - | a) | 233092.08 | a) | 100% | c) | 100% | a) | 16 | Completed |  | 4
| 066 | [7 empty] | b) | Crucio | b) | 03/26/19 | f) | - | b) | 233092.08 | b) | - | d) | - | b) | 480 |  | 1 | 4
[9 empty] | c) | MANDISKAB TRIBAL | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1 | 4
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1 | 4
|  |  | Mesaoy - Dasing |  |  | Road Maintenance | 1.39 | MBA | a) | 29749.5 | a) | 01/03/19 | e) | - | a) | 29749.5 | a) | 100% | c) | 100% | a) | 15 | Completed |  | 4
| 067 | [7 empty] | b) | Crucio | b) | 03/18/19 | f) | - | b) | 29749.5 | b) | - | d) | - | b) | 450 |  | 1 | 4
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 10000 | [7 empty] | 1 | 4
[9 empty] | d) | - | d) | - | [11 empty] | 1 | 4
|  |  | Mesaoy - Dasing |  |  | Road Maintenance | 1.39 | CBRMC | a) | 54152.71 | a) | 01/03/19 | e) | - | a) | 54152.71 | a) | 100% | c) | 100% | a) | 16 | Completed | 1 | 4
| 067 | [7 empty] | b) | Crucio | b) | 03/26/19 | f) | - | b) | 54152.71 | b) | - | d) | - | b) | 480 |  | 1 | 4
[9 empty] | c) | MANDISKAB TRIBAL | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1 | 4
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1 | 4
|  |  | Jct. San Juan - Jct. Mesaoy |  |  | Road Maintenance | 1.82 | MBA | a) | 106788.95 | a) | 01/03/19 | e) | - | a) | 106788.95 | a) | 100% | c) | 100% | a) | 15 | Completed | 1 | 4
| 068 | [7 empty] | b) | Crucio | b) | 03/01/19 | f) | - | b) | 106788.95 | b) | - | d) | - | b) | 450 |  |  | 4
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 17502.68 | [8 empty] | 4
[9 empty] | d) | - | d) | - | [11 empty] | 1 | 4
|  |  | Jct. San Juan - Jct. Mesaoy |  |  | Road Maintenance | 1.82 | CBRMC | a) | 35180.83 | a) | 01/03/19 | e) | - | a) | 35180.83 | a) | 100% | c) | 100% | a) | 16 | Completed | 1 | 4
| 068 | [7 empty] | b) | Crucio | b) | 03/26/19 | f) | - | b) | 35180.83 | b) | - | d) | - | b) | 480 |  | 1 | 4
[9 empty] | c) | MANDISKAB TRIBAL | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1 | 4
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1 | 4
|  |  | Mesaoy - Jct. Mahayahay |  |  | Road Maintenance | 4.6 | MBA | a) | 146984.46 | a) | 01/03/19 | e) | - | a) | 146984.46 | a) | 100% | c) | 100% | a) | 15 | Completed | 1 | 4
| 069 | [7 empty] | b) | Crucio | b) | 03/18/19 | f) | - | b) | 146984.46 | b) | - | d) | - | b) | 450 |  | 1 | 4
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 7618.27 | [7 empty] | 1 | 4
[9 empty] | d) | - | d) | - | [11 empty] | 1 | 4
|  |  | Mesaoy - Jct. Mahayahay |  |  | Road Maintenance | 4.6 | CBRMC | a) | 160103.65 | a) | 01/03/19 | e) | - | a) | 160103.65 | a) | 100% | c) | 100% | a) | 16 | Completed | 1 | 4
| 069 | [7 empty] | b) | Crucio | b) | 03/22/19 | f) | - | b) | 160103.65 | b) | - | d) | - | b) | 480 |  | 1 | 4
[9 empty] | c) | MAHAYAHAY IFA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1 | 4
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1 | 4
[24 empty] | 1 | 4
[24 empty] | 1 | 4
|  |  | Mesaoy - New bohol |  |  | Road Maintenance | 5.36 | MBA | a) | 165361.13 | a) | 01/03/19 | e) | - | a) | 165361.13 | a) | 100% | c) | 100% | a) | 15 | Completed | 1 | 4
| 070 | [7 empty] | b) | Crucio | b) | 03/01/19 | f) | - | b) | 165361.13 | b) | - | d) | - | b) | 480 |  | 1 | 4
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 2543.9 | [7 empty] | 1 | 4
[9 empty] | d) | - | d) | - | [11 empty] | 1 | 4
|  |  | Mesaoy - New bohol |  |  | Road Maintenance | 5.36 | CBRMC | a) | 224851.45 | a) | 01/03/19 | e) | - | a) | 224851.45 | a) | 100% | c) | 100% | a) | 16 | Completed | 1 | 4
| 070 | [7 empty] | b) | Crucio | b) | 03/26/19 | f) | - | b) | 224851.45 | b) | - | d) | - | b) | 480 |  | 1 | 4
[9 empty] | c) | MANDISKAB TRIBAL | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1 | 4
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1 | 4
|  |  | Bdry. Tagum - Baca - New Corella |  |  | Road Maintenance | 13.01 | MBA | a) | 217182.9 | a) | 01/03/19 | e) | - | a) | 217182.9 | a) | 100% | c) | 100% | a) | 15 | Completed | 1 | 4
| 071 | [7 empty] | b) | Crucio | b) | 03/18/19 | f) | - | b) | 217182.9 | b) | - | d) | - | b) | 450 |  | 1 | 4
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 19550 | [7 empty] | 1 | 4
[9 empty] | d) | - | d) | - | [11 empty] | 1 | 4
|  |  | Bdry. Tagum - Baca - New Corella |  |  | Road Maintenance | 13.01 | CBRMC | a) | 214256.36 | a) | 01/03/19 | e) | - | a) | 214256.36 | a) | 100% | c) | 100% | a) | 16 | Completed |  | 4
| 071 | [7 empty] | b) | Crucio | b) | 03/26/19 | f) | - | b) | 214256.36 | b) | - | d) | - | b) | 480 |  | 1 | 4
[9 empty] | c) | DURIAN DACUDAO | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1 | 4
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1 | 4
|  |  | Prk. 1, Maunlom - Prk. 6 Maunlom Road |  |  | Road Maintenance | 3.56 | MBA | a) | 150912.87 | a) | 01/03/19 | e) | - | a) | 150912.87 | a) | 100% | c) | 100% | a) | 15 | Completed |  | 4
| 147 | [7 empty] | b) | Crucio | b) | 03/01/19 | f) | - | b) | 150912.87 | b) | - | d) | - | b) | 450 |  |  | 4
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 23025 | [8 empty] | 4
[9 empty] | d) | - | d) | - | [11 empty] | 1 | 4
|  |  | Prk. 1, Maunlom - Prk. 6 Maunlom Road |  |  | Road Maintenance | 3.56 | CBRMC | a) | 63973.36 | a) | 01/03/19 | e) | - | a) | 63973.36 | a) | 100% | c) | 100% | a) | 16 | Completed | 1 | 4
| 147 | [7 empty] | b) | Crucio | b) | 03/22/19 | f) | - | b) | 63973.36 | b) | - | d) | - | b) | 480 |  | 1 | 4
[9 empty] | c) | THE BEST VEGETABLE | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [8 empty] | 4
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1 | 4
[24 empty] | 1 | 4
|  |  | New Visayas - Binancian |  |  | Road Maintenance | 7.77 | MBA | a) | 14814.34 | a) | 01/03/19 | e) | - | a) | 14814.34 | a) | 100% | c) | 100% | a) | 15 | Completed | 1 | 4
| 149 | [7 empty] | b) | Crucio | b) | 03/18/19 | f) | - | b) | 14814.34 | b) | - | d) | - | b) | 450 |  | 1 | 4
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 5,000.00 | [7 empty] | 1 | 4
[9 empty] | d) | - | d) | - | [11 empty] | 1 | 4
|  |  | New Visayas - Binancian |  |  | Road Maintenance | 7.77 | CBRMC | a) | 129495.6 | a) | 01/03/19 | e) | - | a) | 129495.6 | a) | 100% | c) | 100% | a) | 16 | Completed | 1 | 4
| 149 | [7 empty] | b) | Crucio | b) | 03/22/19 | f) | - | b) | 129495.6 | b) | - | d) | - | b) | 480 |  | 1 | 4
[9 empty] | c) | BUAN IFA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1 | 4
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1 | 4
|  |  | Datu Balong - Prk. Mamalian |  |  | Road Maintenance | 3.46 | MBA | a) | 117454.89 | a) | 01/03/19 | e) | - | a) | 117454.89 | a) | 100% | c) | 39.37% | a) | 15 | Completed | 1 | 4
| 150 | [7 empty] | b) | Crucio | b) | 03/18/19 | f) | - | b) | 117454.89 | b) | - | d) | - | b) | 450 |  | 1 | 4
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 10115 | [7 empty] | 1 | 4
[9 empty] | d) | - | d) | - | [11 empty] | 1 | 4
|  |  | Datu Balong - Prk. Mamalian |  |  | Road Maintenance | 3.46 | CBRMC | a) | 59264.42 | a) | 01/03/19 | e) | - | a) | 59264.42 | a) | 100% | c) | 100% | a) | 16 | Completed | 1 | 4
| 150 | [7 empty] | b) | Crucio | b) | 03/28/19 | f) | - | b) | 59264.42 | b) | - | d) | - | b) | 480 |  | 1 | 4
[9 empty] | c) | DATU BALONG FA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1 | 4
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1 | 4
[24 empty] | 1 | 4
[24 empty] | 1 | 4
44
[24 empty] | 1 | 4
[24 empty] | 1 | 4
[24 empty] | 1 | 4
[24 empty] | 1 | 4
[24 empty] | 1 | 4
[24 empty] | 1 | 4
[24 empty] | 1 | 4
[24 empty] | 1 | 4
| A.2 GENERAL FUND CY 2019 |  |  |  |  | Road Maintenance | KM | MBA/CBRMC | a) | 11,618,834.00 | a) | 01/03/19 | e) | - | a) | 11,618,834.00 | a) | 66% | c) | 66% | a) | 42 | See list of Provincial Roads | 1 | 4
| Road ID |  | 1. Maintenance Of Various Prov'l. Roads and Bridges Dist 2 |  |  |  | 288.26 |  | b) | Matuguinas | b) | 01/03/19 | f) | - | b) | 11,618,834.00 | b) | - | d) | - | b) | 924 |  | 1 | 4
[9 empty] | c) | PEO/CBRMC | c) | 12/31/19 | g) | - | c) | - | [7 empty] | 1 | 4
| 11DAN | [9 empty] | d) | - | [11 empty] | 1 | 4
[9 empty] | d) | 261 days | d) | - | [11 empty] | 1 | 4
|  |  | Cebulano - Mangalcal |  |  | Road Maintenance | 4.17 | MBA | a) | 142161.87 | a) | 01/03/19 | e) | - | a) | 142161.87 | a) | 100% | c) | 100% | a) | 9 | Completed | 1 | 4
|  | 073 | [6 empty] | b) | Clar | b) | 2019-01-15 | f) | - | b) | 142161.87 | b) | - | d) | - | b) | 18 |  | 1 | 4
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 118,609.29 | [8 empty] | 4
[9 empty] | d) | - | d) | - | [12 empty] | 4
|  |  | Tubod - basa - Mangalcal |  |  | Road Maintenance | 3.93 | MBA | a) | 156875.9 | a) | 01/03/19 | e) | - | a) | 156875.9 | a) | 100% | c) | 100% | a) | 9 | Completed |  | 4
| 074 | [7 empty] | b) | Clar | b) | 2019-01-15 | f) | - | b) | 156875.9 | b) | - | d) | - | b) | 18 |  |  | 4
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 143,372.65 | [8 empty] | 4
[9 empty] | d) | - | d) | - | [12 empty] | 4
|  |  | Upper Mangalcal - Lower Mangalcal |  |  | Road Maintenance | 2.43 | 0 | a) | 79237.14 | a) | 01/03/19 | e) | - | a) | 79237.14 | a) | 100% | c) | 100% | a) | 9 | Completed |  | 4
| 078 | [7 empty] | b) | Clar | b) | 2019-01-14 | f) | - | b) | 79237.14 | b) | - | d) | - | b) | 27 |  |  | 4
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 69,430.97 | [8 empty] | 4
[9 empty] | d) | - | d) | - | [12 empty] | 4
|  |  | Jct. Highway Carmen - Mangalcal - Tubod |  |  | Road Maintenance | 11.34 | MBA | a) | 463135.67 | a) | 01/03/19 | e) | - | a) | 463135.67 | a) | 100% | c) | 100% | a) | 9 | Completed |  | 4
| 082 | [7 empty] | b) | Clar | b) | 01/10/19 | f) | - | b) | 463135.67 | b) | - | d) | - | b) | 45
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 170,106.43 | [7 empty] | FS
[9 empty] | d) | - | d) | - | [11 empty] | AC
|  |  | Jct. Highway Carmen - Mangalcal - Tubod |  |  | Road Maintenance | 11.34 | 0 | a) | 253557.37 | a) | 01/03/19 | e) | - | a) | 253557.37 | a) | 100% | c) | 100% | a) | 10 | Completed | AC
| 082 | [7 empty] | b) | Maligro | b) | 03/25/19 | f) | - | b) | 253557.37 | b) | - | d) | - | b) | 40 |  | AC
[9 empty] | c) | TUBOD CENTRO LOWER IRRIGATORS ASSOCIATION | c) | 09/25/19 | g) | 2019-12-31 | c) | - | [7 empty] | AC | 4
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 2 | 4
|  |  | Jct. Highway Sto. Niño - Kabanlakan - La Paz |  |  | Road Maintenance | 2.13 | MBA | a) | 76067.88 | a) | 01/03/19 | e) | - | a) | 76067.88 | a) | 100% | c) | 100% | a) | 9 | Completed | 2 | 4
| 084 | [7 empty] | b) | Clar | b) | 01/10/19 | f) | - | b) | 76067.88 | b) | - | d) | - | b) | 45 |  | 2 | 4
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 66,477.91 | [7 empty] | 2 | 4
[9 empty] | d) | - | d) | - | [11 empty] | 2 | 4
|  |  | Ising - Sto Niño |  |  | Road Maintenance | 2.07 | 0 | a) | 82413.14 | a) | 01/03/19 | e) | - | a) | 82413.14 | a) | 100% | c) | 100% | a) | 5 | Completed | 2 | 4
| 085 | [7 empty] | b) | Clar | b) | 01/17/19 | f) | - | b) | 82413.14 | b) | - | d) | - | b) | 15 |  | 2 | 4
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 27,093.24 | [7 empty] | 2 | 4
[9 empty] | d) | - | d) | - | [11 empty] | 2 | 4
|  |  | Ising - Sadpodon - Taba - Dila -Dila |  |  | Road Maintenance | 5.68 | MBA | a) | 248941.33 | a) | 01/03/19 | e) | - | a) | 248941.33 | a) | 100% | c) | 100% | a) | 9 | Completed | 2 | 4
| 086 | [7 empty] | b) | Clar | b) | 01/12/19 | f) | - | b) | 248941.33 | b) | - | d) | - | b) | 27 |  | 2 | 4
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 82,329.02 | [7 empty] | 2 | 4
[9 empty] | d) | - | d) | - |  |  |  | . | [7 empty] | 2 | 4
[24 empty] | 2 | 4
|  |  | Tuganay - taba |  |  | Road Maintenance | 4.27 | 0 | a) | 291377.9 | a) | 01/03/19 | e) | - | a) | 291377.9 | a) | 70% | c) | 70% | a) | 9 | Completed | 2 | 4
| 087 | [7 empty] | b) | Clar | b) | 01/09/19 | f) | - | b) | 291377.9 | b) | - | d) | - | b) | 27 |  | 2 | 4
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 12/31/2019 | c) | 238,412.28 | [7 empty] | 2 | 4
[9 empty] | d) | - | d) | - | [11 empty] | 2 | 4
|  |  | Jct. Highway Tuganay - Taba |  |  | Road Maintenance | 4.4 | MBA | a) | 32972.82 | a) | 01/03/19 | e) | - | a) | 32972.82 | a) | 65% | c) | 65% | a) | 9 | Completed | 2 | 4
| 088 | [7 empty] | b) | Clar | b) | 01/22/19 | f) | - | b) | 32972.82 | b) | - | d) | - | b) | 18 |  | 2 | 4
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 12/31/2019 | c) | 22,639.09 | [7 empty] | 2 | 4
[9 empty] | d) | - | d) | - | [11 empty] | 2 | 4
|  |  | Jct. Highway Ising - Magsaysay |  |  | Road Maintenance | 10.84 | 0 | a) | 417818.12 | a) | 01/03/19 | e) | - | a) | 417818.12 | a) | 60% | c) | 60% | a) | 10 | Completed | 2 | 4
| 089 | [7 empty] | b) | Clar | b) | 01/22/19 | f) | - | b) | 417818.12 | b) | - | d) | - | b) | 50 |  | 2 | 4
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 12/31/2019 | c) | 313,488.39 | [7 empty] | 2 | 4
[9 empty] | d) | - | d) | - | [11 empty] | 2 | 4
[24 empty] | 2 | 4
[24 empty] | 2 | 4
[24 empty] | 2 | 4
|  |  | New Camiling - Alejal - Lower Magsaysay |  |  | Road Maintenance | 6.73 | MBA | a) | 240878.08 | a) | 01/03/19 | e) | - | a) | 240878.08 | a) | 80% | c) | 80% | a) | 4 | Completed | 2 | 4
| 091 | [7 empty] | b) | Clar | b) | 01/22/19 | f) | - | b) | 240878.08 | b) | - | d) | - | b) | 20 |  | 2 | 4
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 12/31/2019 | c) | - | [7 empty] | 2 | 4
[9 empty] | d) | - | d) | - | [12 empty] | 4
|  |  | Jct. highway Tuganay - Anibongan |  |  | Road Maintenance | 3.66 | 0 | a) | 150684.44 | a) | 01/03/19 | e) | - | a) | 150684.44 | a) | 100% | c) | 100% | a) | 6 | Completed | 2 | 4
| 094 | [7 empty] | b) | Clar | b) | 01/22/19 | f) | - | b) | 150684.44 | b) | - | d) | - | b) | 18 |  | 2 | 4
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 12/31/2019 | c) | - | [7 empty] | 2 | 4
[9 empty] | d) | - | d) | - | [11 empty] | 2 | 4
|  |  | Anibongan - Guadalupe |  |  | Road Maintenance | 2.48 | MBA | a) | 91325.06 | a) | 01/03/19 | e) | - | a) | 91325.06 | a) | 100% | c) | 100% | a) | 9 | Completed | 2 | 4
| 095 | [7 empty] | b) | Clar | b) | 01/23/19 | f) | - | b) | 91325.06 | b) | - | d) | - | b) | 18 |  | 2 | 4
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 12/31/2019 | c) | - | [7 empty] | 2 | 4
[9 empty] | d) | - | d) | - | [11 empty] | 2 | 4
|  |  | Tuganay - Anibongan - San Isidro |  |  | Road Maintenance | 7.22 | 0 | a) | 139979.8 | a) | 01/03/19 | e) | - | a) | 139979.8 | a) | 100% | c) | 100% | a) | 9 | Completed | 2 | 4
| 096 | [7 empty] | b) | Clar | b) | 01/24/19 | f) | - | b) | 139979.8 | b) | - | d) | - | b) | 36 |  | 2 | 4
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 12/31/2019 | c) | 1890.37 | [7 empty] | 2 | 4
[9 empty] | d) | - | d) | - | [12 empty] | 4
|  |  | Jct. Anibongan - Prk. 2, 7, 5, San Isidro |  |  | Road Maintenance | 3.14 | MBA | a) | 104378.03 | a) | 01/03/19 | e) | - | a) | 104378.03 | a) | 100% | c) | 100% | a) | 10 | Completed |  | 4
| 097 | [7 empty] | b) | Clar | b) | 01/24/19 | f) | - | b) | 104378.03 | b) | - | d) | - | b) | 20 |  |  | 4
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 12/31/2019 | c) | 56,087.50 | [7 empty] | 2 | 4
[9 empty] | d) | - | d) | - | [11 empty] | 2 | 4
|  |  | Anibongan - Salvacion - Cabay-angan |  |  | Road Maintenance | 6.93 | 0 | a) | 415461.61 | a) | 01/03/19 | e) | - | a) | 415461.61 | a) | 100% | c) | 100% | a) | 9 | Completed | 2 | 4
| 098 | [7 empty] | b) | Clar | b) | 01/25/19 | f) | - | b) | 415461.61 | b) | - | d) | - | b) | 45 |  | 2 | 4
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 12/31/2019 | c) | - | [7 empty] | 2 | 4
[9 empty] | d) | - | d) | - | [11 empty] | 2 | 4
|  |  | Jct. Highway Guadalupe - Bdry. Tagum |  |  | Road Maintenance | 7.9 | MBA | a) | 456131.09 | a) | 01/03/19 | e) | - | a) | 456131.09 | a) | 100% | c) | 100% | a) | 9 | Completed | 2 | 4
| 101 | [7 empty] | b) | Clar | b) | 01/25/19 | f) | - | b) | 456131.09 | b) | - | d) | - | b) | 18 |  | 2 | 4
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 12/31/2019 | c) | - | [7 empty] | 2 | 4
[9 empty] | d) | - | d) | - | [11 empty] | 2 | 4
|  |  | Jct. Highway Guadalupe - Bdry. Tagum |  |  | Road Maintenance | 7.9 | 0 | a) | 228201.66 | a) | 01/03/19 | e) | - | a) | 228201.66 | a) | 100% | c) | 100% | a) | 8 | Completed | 2 | 4
| 101 | [7 empty] | b) | Maligro | b) | 03/25/19 | f) | - | b) | 228201.66 | b) | - | d) | - | b) | 40 |  | 2 | 4
[9 empty] | c) | LAMPIA PAG-ASA IRRIGATORS ASSOCIATION, INC. | c) | 12/25/19 | g) | 12/31/2019 | c) | - | [7 empty] | 2 | 4
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 2 | 4
|  |  | Poblacion Dujali - Prk. 8 Dujali |  |  | Road Maintenance | 8.2 | MBA | a) | 285600.05 | a) | 01/03/19 | e) | - | a) | 285600.05 | a) | 100% | c) | 100% | a) | 10 | Completed | 2 | 4
| 105 | [7 empty] | b) | Clar | b) | 01/28/19 | f) | - | b) | 285600.05 | b) | - | d) | - | b) | 50 |  | 2 | 4
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 12/31/2019 | c) | - | [7 empty] | 2 | 4
[9 empty] | d) | - | d) | - | [11 empty] | 2 | 4
|  |  | Dujali - San Isidro |  |  | Road Maintenance | 3 | 0 | a) | 130319.3 | a) | 01/03/19 | e) | - | a) | 130319.3 | a) | 100% | c) | 100% | a) | 8 | Completed | 2 | 4
| 107 | [7 empty] | b) | Gamad | b) | 01/28/19 | f) | - | b) | 130319.3 | b) | - | d) | - | b) | 30 |  | 2 | 4
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 12/31/2019 | c) | 45,943.12 | [7 empty] | 2 | 4
[9 empty] | d) | - | d) | - | [11 empty] | 2 | 4
|  |  | Prk. 5, RJS - Prk. 6 New Casay |  |  | Road Maintenance | 2.73 | MBA | a) | 235277 | a) | 01/03/19 | e) | - | a) | 235277 | a) | 100% | c) | 100% | a) | 2 | Completed | 2 | 4
| 109 | [7 empty] | b) | Gamad | b) | 01/28/19 | f) | - | b) | 235277 | b) | - | d) | - | b) | 6 |  | 2 | 4
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 12/31/2019 | c) | 90,745.35 | [7 empty] | 2 | 4
[9 empty] | d) | - | d) | - | [11 empty] | 2 | 4
|  |  | Prk. 5 - Prk. 1 Pawas Dujali |  |  | Road Maintenance | 2.18 | 0 | a) | 76067.68 | a) | 01/03/19 | e) | - | a) | 76067.68 | a) | 100% | c) | 100% | a) | 10 | Completed | 2 | 4
| 112 | [7 empty] | b) | Gamad | b) | 01/18/19 | f) | - | b) | 76067.68 | b) | - | d) | - | b) | 20 |  | 2 | 4
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 12/31/2019 | c) | 40,112.50 | [7 empty] | 2 | 4
[9 empty] | d) | - | d) | - | [11 empty] | 2 | 4
|  |  | Dujali - Balisong - Magupising |  |  | Road Maintenance | 5.52 | MBA | a) | 260591.93 | a) | 01/03/19 | e) | - | a) | 260591.93 | a) | 100% | c) | 100% | a) | 4 | Completed | 2 | 4
| 113 | [7 empty] | b) | Gamad | b) | 01/09/19 | f) | - | b) | 260591.93 | b) | - | d) | - | b) | 8 |  | 2 | 4
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 12/31/2019 | c) | - | [7 empty] | 2 | 4
[9 empty] | d) | - | d) | - | [11 empty] | 2 | 4
[24 empty] | 2 | 4
[24 empty] | 2 | 4
[24 empty] | 2 | 4
|  |  | Dujali - Pawas - San Vicente |  |  | Road Maintenance | 4.42 | 0 | a) | 139536.42 | a) | 01/03/19 | e) | - | a) | 139536.42 | a) | 100% | c) | 100% | a) | 10 | Completed | 2 | 4
| 117 | [7 empty] | b) | Gamad | b) | 01/22/19 | f) | - | b) | 139536.42 | b) | - | d) | - | b) | 18 |  | 2 | 4
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 12/31/2019 | c) | 52,133.86 | [7 empty] | 2 | 4
[9 empty] | d) | - | d) | - | [11 empty] | 2 | 4
|  |  | Jct. Salvacion - San Vicente - Cabay-angan |  |  | Road Maintenance | 3.45 | MBA | a) | 247460.9 | a) | 01/03/19 | e) | - | a) | 247460.9 | a) | 100% | c) | 100% | a) | 10 | Completed | 2 | 4
| 118 | [7 empty] | b) | Gamad | b) | 01/23/19 | f) | - | b) | 247460.9 | b) | - | d) | - | b) | 18 |  | 2 | 4
[9 empty] | c) | PEO | c) | 02/31/19 | g) | 12/31/2019 | c) | 151,887.50 | [7 empty] | 2 | 4
[9 empty] | d) | - | d) | - | [11 empty] | 2 | 4
|  |  | Jct. Salvacion - San Vicente - Cabay-angan |  |  | Road Maintenance | 3.45 | 0 | a) | 152134.44 | a) | 01/03/19 | e) | - | a) | 152134.44 | a) | 100% | c) | 100% | a) | 8 | Completed | 2 | 4
| 118 | [7 empty] | b) | Gamad | b) | 03/26/19 | f) | - | b) | 152134.44 | b) | - | d) | - | b) | 36 |  | 2 | 4
[9 empty] | c) | BALISONG SAN VICENTE IRRIGATORS ASSOCIATION | c) | 12/26/19 | g) | 12/31/2019 | c) | [8 empty] | 2 | 4
[9 empty] | d) | 3 quarters | d) | - | [10 empty] | Completed | 2 | 4
|  |  | Dujali - San Miguel |  |  | Road Maintenance | 3.95 | MBA | a) | 101202.04 | a) | 01/03/19 | e) | - | a) | 101202.04 | a) | 80% | c) | 90% | a) | 11 |  | 2 | 4
| 119 | [7 empty] | b) | Gamad | b) | 01/10/19 | f) | - | b) | 101202.04 | b) | - | d) | - | b) | 22 |  | 2 | 4
[9 empty] | c) | PEO | c) | 12/31/19 | g) | - | c) | 90,350.03 | [7 empty] | 2 | 4
[9 empty] | d) | - | d) | - | [12 empty] | 4
|  |  | San Miguel - Casig-ang |  |  | Road Maintenance | 2.55 | 0 | a) | 79237.14 | a) | 01/03/19 | e) | - | a) | 79237.14 | a) | 100% | c) | 100% | a) | 10 | Completed |  | 4
| 122 | [7 empty] | b) | Gamad | b) | 01/24/19 | f) | - | b) | 79237.14 | b) | - | d) | - | b) | 10 |  |  | 4
[9 empty] | c) | BALISONG SAN VICENTE IRRIGATORS ASSOCIATION | c) | 12/31/19 | g) | 12/31/2019 | c) | 40,112.50 | [7 empty] | 2 | 4
[9 empty] | d) | - | d) | - | [11 empty] | 2 | 4
|  |  | Prk. Magsaysay - Lunga-og - Dalisay |  |  | Road Maintenance | 2.81 | MBA | a) | 79762.14 | a) | 01/03/19 | e) | - | a) | 79762.14 | a) | 100% | c) | 100% | a) | 8 | Completed | 2 | 4
| 127 | [7 empty] | b) | Gamad | b) | 01/30/19 | f) | - | b) | 79762.14 | b) | - | d) | - | b) | 8 |  | 2 | 4
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 12/31/2019 | c) | 40,612.50 | [7 empty] | 2 | 4
[9 empty] | d) | - | d) | - | [11 empty] | 2 | 4
|  |  | Prk. Apitong - Upper Balisong - Dalisay |  |  | Road Maintenance | 4.6 | 0 | a) | 137846.03 | a) | 01/03/19 | e) | - | a) | 137846.03 | a) | 100% | c) | 100% | a) | 8 | Completed | 2 | 4
| 128 | [7 empty] | b) | Gamad | b) | 01/31/19 | f) | - | b) | 137846.03 | b) | - | d) | - | b) | 8 |  | 2 | 4
[9 empty] | c) | BALISONG SAN VICENTE IRRIGATORS ASSOCIATION | c) | 12/31/19 | g) | 12/31/2019 | c) | - | [7 empty] | 2 | 4
[9 empty] | d) | - | d) | - | [11 empty] | 2 | 4
|  |  | Sitio Paradise - Magkakaisa - Esperanza |  |  | Road Maintenance | 1.75 | MBA | a) | 66552.75 | a) | 01/03/19 | e) | - | a) | 66552.75 | a) | 100% | c) | 100% | a) | 8 | Completed | 2 | 4
| 129 | [7 empty] | b) | 79762.14 | b) | 01/22/19 | f) | - | b) | 66552.75 | b) | - | d) | - | b) | 8 |  | 2 | 4
[9 empty] | c) | Gamad | c) | 12/31/19 | g) | 12/31/2019 | c) | 22,246.26 | [7 empty] | 2 | 4
[9 empty] | d) | - | d) | - | [11 empty] | 2 | 4
|  |  | Los Amigos 1 - Esperanza - Los Amigos 2 |  |  | Road Maintenance | 3.59 | 0 | a) | 101202.04 | a) | 01/03/19 | e) | - | a) | 101202.04 | a) | 100% | c) | 100% | a) | 10 | Completed | 2 | 4
| 130 | [7 empty] | b) | Gamad | b) | 01/24/19 | f) | - | b) | 101202.04 | b) | - | d) | - | b) | 20 |  | 2 | 4
[9 empty] | c) | BALISONG SAN VICENTE IRRIGATORS ASSOCIATION | c) | 12/31/19 | g) | 12/31/2019 | c) | 50,837.50 | [7 empty] | 2 | 4
[9 empty] | d) | - | d) | - | [11 empty] | 2 | 4
|  |  | Mugas - Lunga-og |  |  | Road Maintenance | 2.68 | MBA | a) | 66552.75 | a) | 01/03/19 | e) | - | a) | 91,693.64 | a) | 100% | c) | 100% | a) | 6 | Completed | 2 | 4
| 132 | [7 empty] | b) | 79762.14 | b) | 01/17/19 | f) | - | b) | 91,693.64 | b) | - | d) | - | b) | 24 |  | 2 | 4
[9 empty] | c) | Gamad | c) | 12/31/19 | g) | 12/31/2019 | c) | 50,837.50 | [7 empty] | 2 | 4
[9 empty] | d) | - | d) | - | [11 empty] | 2 | 4
|  |  | Pantaron - Mugas |  |  | Road Maintenance | 3.35 | 0 | a) | 101202.04 | a) | 01/03/19 | e) | - | a) | 101202.04 | a) | 100% | c) | 100% | a) | 9 | Completed | 2 | 4
| 133 | [7 empty] | b) | Gamad | b) | 01/23/19 | f) | - | b) | 101202.04 | b) | - | d) | - | b) | 18 |  | 2 | 4
[9 empty] | c) | BALISONG SAN VICENTE IRRIGATORS ASSOCIATION | c) | 12/31/19 | g) | 12/31/2019 | c) | 90,349.93 | [7 empty] | 2 | 4
[9 empty] | d) | - | d) | - | [11 empty] | 2 | 4
|  |  | Sto. Tomas - Bdry. Mamacao |  |  | Road Maintenance | 4.9 | MBA | a) | 110710.44 | a) | 01/03/19 | e) | - | a) | 110710.44 | a) | 100% | c) | 100% | a) | 10 | Completed | 2 | 4
| 135 | [7 empty] | b) | 79762.14 | b) | 01/21/19 | f) | - | b) | 110710.44 | b) | - | d) | - | b) | 40 |  | 2 | 4
[9 empty] | c) | Gamad | c) | 12/31/19 | g) | 12/31/2019 | c) | 50,837.50 | [7 empty] | 2 | 4
[9 empty] | d) | - | d) | - | [11 empty] | 2 | 4
|  |  | Fd. Rd. 3 - San Jose |  |  | Road Maintenance | 4.55 | 0 | a) | 147367.49 | a) | 01/03/19 | e) | - | a) | 147367.49 | a) | 100% | c) | 100% | a) | 10 | Completed | 2 | 4
| 136 | [7 empty] | b) | Gamad | b) | 01/25/19 | f) | - | b) | 147367.49 | b) | - | d) | - | b) | 30 |  | 2 | 4
[9 empty] | c) | BALISONG SAN VICENTE IRRIGATORS ASSOCIATION | c) | 12/31/19 | g) | 12/31/2019 | c) | 56,174.69 | [7 empty] | 2 | 4
[9 empty] | d) | - | d) | - | [11 empty] | 2 | 4
[24 empty] | 2 | 4
[24 empty] | 2 | 4
|  |  | Menzi - balagunan - Tulalian |  |  | Road Maintenance | 10.63 | MBA | a) | 520167.79 | a) | 01/03/19 | e) | - | a) | 520167.79 | a) | 100% | c) | 100% | a) | 6 | Completed | 2 | 4
| 138 | [7 empty] | b) | 79762.14 | b) | 01/07/19 | f) | - | b) | 520167.79 | b) | - | d) | - | b) | 18 |  | 2 | 4
[9 empty] | c) | Gamad | c) | 12/31/19 | g) | 12/31/2019 | c) | 204,850.57 | [7 empty] | 2 | 4
[9 empty] | d) | - | d) | - | [11 empty] | 2 | 4
|  |  | Jct. Bdry. Tagum - Talomo |  |  | Road Maintenance | 12.01 | 0 | a) | 407429.19 | a) | 01/03/19 | e) | - | a) | 407429.19 | a) | 100% | c) | 100% | a) | 10 | Completed | 2 | 4
| 145 | [7 empty] | b) | Gamad | b) | 01/11/19 | f) | - | b) | 407429.19 | b) | - | d) | - | b) | 50 |  | 2 | 4
[9 empty] | c) | BALISONG SAN VICENTE IRRIGATORS ASSOCIATION | c) | 12/31/19 | g) | 12/31/2019 | c) | 168,544.84 | [7 empty] | 2 | 4
[9 empty] | d) | - | d) | - | [11 empty] | 2 | 4
|  |  | San Jose - Sitio Mahayahay, Magwawa |  |  | Road Maintenance | 0.84 | MBA | a) | 7919.35 | a) | 01/03/19 | e) | - | a) | 7919.35 | a) | 100% | c) | 100% | a) | 2 | Completed | 2 | 4
| 151 | [7 empty] | b) | 79762.14 | b) | 01/16/19 | f) | - | b) | 7919.35 | b) | - | d) | - | b) | 8 |  | 2 | 4
[9 empty] | c) | Gamad | c) | 12/31/19 | g) | 12/31/2019 | c) | 1,509.27 | [7 empty] | 2 | 4
[9 empty] | d) | - | d) | - | [11 empty] | 2 | 4
[24 empty] | 2 | 4
[24 empty] | 2 | 4
[24 empty] | 2 | 4
[24 empty] | 2 | 4
4
4
[24 empty] | 2 | 4
[24 empty] | 2 | 4
[24 empty] | 2 | 4
[24 empty] | 2 | 4
[24 empty] | 2 | 4
[24 empty] | 2 | 4
[24 empty] | 2 | 4
[24 empty] | 2 | 4
[24 empty] | 2 | 4
[24 empty] | 2 | 4
[24 empty] | 2 | 4
[24 empty] | 2 | 4
|  | M. | 20% DEVELOPMENT FUND CY 2019
| Road ID |  | 1. Rehabilitation Of Various Prov'l. Roads and Bridges Dist 2 |  |  | Road Rehabilitation | KM | Admin | a) | 46740117 | [12 empty] | See list of Provincial Roads
[7 empty] | 115.62 |  | b) | Matuguinas
| 11DAN | [7 empty] | c) | PEO
[9 empty] | d) | 261 days
|  |  | Jct. Highway Sto. Niño - Cebulano |  |  | Road Rehabilitation | 2.09 | Admin | a) | 1045000 | a) | 2019-03-18 | e) | - | a) | 1045000 | a) | 20% | c) | 20% | a) | 11 | On-going
| 072 | [7 empty] | b) | Obar | b) | 2019-05-21 | f) | - | b) | 1045000 | b) | - | d) | - | b) | 55
[9 empty] | c) | PEO | c) | 2020-02-02 | g) | - | c) | -
[9 empty] | d) | - | d) | -
[6 empty] | Road Rehabilitation |  |  | a.) 515,000.00 |  | a.) 03/12/19 |  |  |  | a.) 515,000.00
|  |  | Jct. Highway -Tubod - Bagong Silang | [5 empty] | b.) Clar |  | b.) March 18, 2019 |  |  |  | b.) 515,000.00 | [7 empty] | Completed
g.) June 15, 2019
|  |  | Basa - Tubod |  |  | Road Rehabilitation | 1.56 | Admin | a) | 1000000 | a) | 2019-06-19 | e) | - | a) | 1000000 | a) | - | c) | - | a) | - | On-going
| 076 | [7 empty] | b) | Piad | b) | 2019-11-11 | f) | - | b) | 1000000 | b) | - | d) | - | b) | -
[9 empty] | c) | - | c) | 2020-03-09 | g) | - | c) | -
[9 empty] | d) | - | d) | -
|  |  | Jct. Highway Sto. Niño - Cebulano |  |  | Road Rehabilitation | 2.09 | Admin | a) | 1045000 | a) | 2019-03-18 | e) | - | a) | 1045000 | a) | 20.00% | c) | 20.00% | a) | 11 | On-going | FS
| 072 | [7 empty] | b) | Obar | b) | 2019-05-21 | f) | - | b) | 1045000 | b) | - | d) | - | b) | 55
[9 empty] | c) | PEO | c) | 2020-02-02 | g) | - | c) | - | [7 empty] | AC
[9 empty] | d) | - | d) | - | [11 empty] | AC
|  |  | Basa - Tubod |  |  | Road Rehabilitation | 1.56 | Admin | a) | 1000000 | a) | 2019-06-19 | e) | - | a) | 1000000 | a) | 93.00% | c) | 5.00% | a) | 5 | On-going | FS
| 76 | [7 empty] | b) | Piad | b) | 2019-11-11 | f) | - | b) | 1000000 | b) | - | d) | - | b) | 30
[9 empty] | c) | PEO | c) | 2020-03-19 | g) | - | c) | - | [7 empty] | AC
[9 empty] | d) | - | d) | - | [11 empty] | AC
|  |  | Tubod - Pilar |  |  | Road Rehabilitation | 1.55 | Admin | a) | 16000000 | a) | 06/19/19 & 12/9/19 | e) | - | a) | 16000000 | a) | - | c) | - | a) | - | On-going | FS
| 077 | [7 empty] | b) | Gamad/Clar | b) | 2019-12-18 | f) | - | b) | 16000000 | b) | - | d) | - | b) | -
[9 empty] | c) | PEO | c) | 2020-11-05 | g) | - | c) | - | [7 empty] | AC
[9 empty] | d) | - | d) | - | [11 empty] | AC
|  |  | Dalisay - Mabuhay |  |  | Road Rehabilitation | 1.55 | Admin | a) | 16000000 | a) | 2019-03-16 | e) | - | a) | 16000000 | a) | 80.00% | c) | 80.00% | a) | 10 | On-going | FS
| 102 | [7 empty] | b) | Gamad/Clar | b) | 2019-06-17 | f) | - | b) | 16000000 | b) | - | d) | - | b) | 20
[9 empty] | c) | PEO | c) | 2019-12-29 | g) | - | c) | - | [7 empty] | AC
[9 empty] | d) | - | d) | - | [11 empty] | AC
|  |  | Sitio Malaga - Tibulao |  |  | Road Rehabilitation | 3.22 | Admin | a) | 1000000 | a) | 2019-06-25 | e) | - | a) | 1000000 | a) | - | c) | - | a) | - | On-going | FS
| 103 | [7 empty] | b) | Gamad/Clar | b) | 2020-11-11 | f) | - | b) | 1000000 | b) | - | d) | - | b) | -
[9 empty] | c) | PEO | c) | 2020-02-09 | g) | - | c) | - | [7 empty] | AC
[9 empty] | d) | - | d) | - | [11 empty] | AC
|  |  | Dujali - Tanglaw |  |  | Road Rehabilitation | 3.6 | Admin | a) | 2075000 | a) | 2019-10-03 | e) | - | a) | 2075000 | a) | - | c) | - | a) | - | On-going | FS
| 104 | [7 empty] | b) | Balbastro | b) | 2019-12-28 | f) | - | b) | 2075000 | b) | - | d) | - | b) | -
[9 empty] | c) | PEO | c) | 2020-04-16 | g) | - | c) | - | [7 empty] | AC
[9 empty] | d) | - | d) | - | [11 empty] | AC
|  |  | Cabay-angan - Esperanza |  |  | Road Rehabilitation | 3.25 | Admin | a) | 1000000 | a) | 2019-05-16 | e) | - | a) | 1000000 | a) | 80% | c) | 80% | a) | 9 | On- going | 2
| 110 | [7 empty] | b) | Gamad/Clar | b) | 2019-06-17 | f) | - | b) | 1000000 | b) | - | d) | - | b) | 36 |  | 2
[9 empty] | c) | PEO | c) | 2019-12-29 | g) | - | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | [12 empty] | 2
|  |  | San Miguel -Libertad Provincial Road |  |  | Road Rehabilitation | 6.2 | Admin | a) | 1240000 | a) | 2019-05-29 | e) | - | a) | 1240000 | a) | 59.41% | c) | 59.41% | a) | 9 | On-going | 2
| 121 | [7 empty] | b) | Gamad | b) | 2019-06-17 | f) |  | b) | 1240000 | b) | - | d) | - | b) | 36 |  | 2
[9 empty] | c) | PEO | c) | 2020-02-29 | g) | - | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | Bacali - Casig-ang - Libertad |  |  | Road Rehabilitation | 4.7 | Admin | a) | 940000 | a) | 2019-06-07 | e) | - | a) | 940000 | a) | 80% | c) | 80% | a) | 9 | On-going | 2
| 123 | [7 empty] | b) | Gamad | b) | 2019-06-27 | f) | 35 CD | b) | 940000 | b) | - | d) | - | b) | 36 |  | 2
[9 empty] | c) | Admin | c) | 2020-02-29 | g) | - | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | Kinamayan - Moslog - Mahayag |  |  | Road Rehabilitation | 3.23 | Admin | a) | 1000000 | a) | 2019-05-20 | e) | - | a) | 1000000 | a) | 80% | c) | 80% | a) | 10 | On going | 2
| 124 | [7 empty] | b) | Gamad | b) | 2019-06-27 | f) | 29 CD | b) | 1000000 | b) | - | d) | - | b) | 20 |  | 2
[9 empty] | c) | PEO | c) | 2020-02-29 | g) | - | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | San Miguel - Moslog - Kinamayan |  |  | Road Rehabilitation | 2.9 | Admin | a) | 1000000 | a) | 2019-05-20 | e) | - | a) | 1000000 | a) | 80% | c) | 80% | a) | 6 | On-going | 2
| 125 | [7 empty] | b) | Gamad | b) | 2019-06-27 | f) | 29 CD | b) | 1000000 | b) | - | d) | - | b) | 24 |  | 2
[9 empty] | c) | PEO | c) | 2020-02-29 | g) | - | c) | - | [7 empty] | 2 | 4
[9 empty] | d) | - | d) | - | [11 empty] | 2 | 4
|  |  | Mugas - Lanatad |  |  | Road Rehabilitation | 1.53 | Admin | a) | 500000 | a) |  | e) | - | a) | 500000 | a) | - | c) | - | a) | - | On-going | 2
| 131 | [7 empty] | b) | Balbastro | b) | 2019-08-05 | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 2
[9 empty] | c) | PEO | c) | 2020-02-20 | g) | - | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | New Katipunan - Pantaron |  |  | Road Rehabilitation | 1.96 | Admin | a) | 395000 | a) | 2019-03-12 | e) | - | a) | 395000 | a) | - | c) | - | a) | - | On-going | 2
| 134 | [7 empty] | b) | Gamad/Clar | b) | 2019-12-27 | f) | - | b) | 395000 | b) | - | d) | - | b) | - |  | 2
[9 empty] | c) | PEO | c) | 2020-02-25 | g) | - | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | Fd. Rd. 2 - Sto. Tomas - Magwawa |  |  | Road Rehabilitation | 10.21 | Admin | a) | 3575000 | a) | June `19, 2019 | e) | - | a) | 3575000 | a) | 40% | c) | 40% | a) | - | On-going | 2
| 137 | [7 empty] | b) | Gamad/Clar | b) | 2019-08-27 | f) | - | b) | 3575000 | b) | - | d) | - | b) | - |  | 2
[9 empty] | c) | PEO | c) | 2020-01-24 | g) | - | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | Jct. Highway - Tanglaw |  |  | Road Rehabilitation | 3.98 | Admin | a) | 1100000 | a) | 2019-05-16 | e) | - | a) | 1100000 | a) | 85% | c) | 85% | a) | 10 | On-going | 2
| 142 | [7 empty] | b) | Gamad/Clar | b) | 2019-06-17 | f) | 29 CD | b) | 1100000 | b) | - | d) | - | b) | 20 |  | 2
[9 empty] | c) | PEO | c) | 2020-02-29 | g) | - | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | Kimamon - Lunga-og - Talomo |  |  | Road Rehabilitation | 5.99 | Admin | a) | 1800000 | a) | 2019-05-20 | e) | - | a) | 1800000 | a) | 73.31% | c) | 73.31% | a) | 9 | On-going | 2
| 144 | [7 empty] | b) | Gamad | b) | 2019-06-17 | f) | - | b) | 1800000 | b) | - | d) | - | b) | 6 |  | 2
[9 empty] | c) | PEO | c) | 2020-02-27 | g) | - | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | Bdry. Tagum - Crossing Kinamayan Sto. Tomas |  |  | Road Rehabilitation | 0.75 | Admin | a) | 3700000 | a) | 2019-12-06 | e) | - | a) | 3700000 | a) | - | c) | - | a) | - | On-going | 2
| 146 | [7 empty] | b) | Gamad/Clar | b) | 2019-12-27 | f) | - | b) | 3700000 | b) | - | d) | - | b) | - |  | 2
[9 empty] | c) | PEO | c) | 2020-04-25 | g) | - | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 2. Various of Local Roads & Drainage Development Project (Provincewide) |  |  |  |  | Road Drainage rehabiliated | km | Admin | a) | 15000000 | [12 empty] | See projects listed below | 2
[9 empty] | b) | Paraguya | [13 empty] | 2
[9 empty] | c) | PEO | [13 empty] | 2
[9 empty] | d) | - | [13 empty] | 2
|  |  | Rehab. Of Dujali-Pawas-San Vicente Provincial Road |  |  | Road Drainage rehabiliated | km | Admin | a) | 1102900 | a) | 2019-08-05 | e) | - | a) | 1102900 | a) | - | c) | - | a) | - | Project title was amended in the 2nd AIP revision deleting drainage.The project amount was reduced from P2,000,000.00 to P1,102,900.00 to fund new projects that was inlcuded in the AIP 3rd revision CY 2019 /SB No. 4 CY 2019.On-going | 2
| 2.1 | [7 empty] | b) | - | b) | - | f) | - | b) | 1102900 | b) | - | d) | - | b) | - |  | 2
[9 empty] | c) | PEO | c) | - | g) | - | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | Rehab./Impv't. of Jct. highway Ising-Magsaysay Provincial Road with Drainage |  |  | Road Drainage rehabiliated | km | Admin | a) | 1500000 | a) | 2019-01-16 | e) | - | a) | 1500000 | a) | - | c) | - | a) | - | Revised POW for approval - Jan. 7, 2020 Revision was made due to scarcity of boulders changing from stone masonry to concrete masonry | 2
| 2.2 | [7 empty] | b) | Toquero | b) | - | f) | - | b) | 1500000 | b) | - | d) | - | b) | - |  | 2
[9 empty] | c) | PEO | c) | - | g) | - | c) | - | [7 empty] | 2 | 4
[9 empty] | d) | - | d) | - | [11 empty] | 2 | 4
| 3. Various Water System Development Project (Provincewide) |  |  |  |  | Water System projects | Households | Admin | a) | 9750000 | [12 empty] | See projects listed below | AC
[9 empty] | b) | Medalla/Imboy | [13 empty] | AC
[9 empty] | c) | PEO | [13 empty] | 1 | 4
[9 empty] | d) | - | [13 empty] | 2 | 4
| 3.1 | Construction of Water System Projects | [21 empty] | 2 | 4
[24 empty] | 2 | 4
|  |  | Impv't. of Potable Water System, Consolacion, Panabo City |  |  | Water System Projects | Households | - | a) | 500000 | a) | 2019-06-28 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Sched of bidding Dec 27, 2019 | 2
| 3.1.1 | [7 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 2
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | Impv't. of Potable Water System, Tagbitan-ag, Samal Dist. |  |  | Water System Projects | Households | - | a) | 500000 | a) | 2019-06-19 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For implementation | 2
| 3.1.2 | [7 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 2
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | Impv't. of Potable Water System, San Antonio, babak, IGCS |  |  | Water System Projects | - | - | a) | 500000 | a) | 2019-06-25 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For implementation |  | 4
| 3.1.3 | [7 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 2 | 4
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 2 | 4
[9 empty] | d) | - | d) | - | [11 empty] | 2 | 4
|  |  | Impv't. of Potable Water System, Mambago-A, IGCS |  |  | Water System Projects | Households | - | a) | 500000 | a) | 2019-09-10 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | (Amended in the AIP 2nd Revision to change the location from Peñaplata to Samal District) For implementation | 2
| 3.1.4 | [7 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | AC
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | AC
[9 empty] | d) | - | d) | - | [11 empty] | AC
|  |  | Construction of PWS, Brgy. Buenavista, Panabo City |  |  | Water System Projects | - | - | a) | 500000 | a) | June 19 ,2019 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For implementation | AC
| 3.1.5 | [7 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | AC
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | Construction of PWS, Brgy. Brgy. Kiotoy, Panabo City |  |  | Water System Projects | Households | Contract | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Waiting for geo-resistivity equipment since the activity is drilling works | 2
| 3.1.6 | [7 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 2
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | Construction of PWS, Brgy. Linusotan, Talikud, District, IGCS |  |  | Water System Projects | Households | - | a) | 1300000 | a) | 2019-10-23 | e) | - | a) | 1300000 | a) | - | c) | - | a) | - | (Additional 800,000.00 from Const. of PWS in purok 2, Pag-asa, Kapalong which was funded by OPAPP CY 2018) (amended Sched of bidding Dec 27, 2019) | 2
| 3.1.7 | [7 empty] | b) | - | b) | - | f) | - | b) | 1300000 | b) | - | d) | - | b) | - |  | 2
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | Rehab. of PWS, Brgy. San Miguel, Babak, IGCS |  |  | Water System Projects | Households | Contract | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For amendment indicating phase 2 since the project title is the same with stimulus project and same amount. | 2
| 3.1.8 | [7 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 2
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | Construction of PWS, Brgy. Cacao, Panabo City |  |  | Water System Projects | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For cancellation. Purchase of Geo-resistivity equipment but procurement still on process | 2
| 3.1.9 | [7 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 2
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | Rehabilitation of Potable Water System, Brgy. Pangubatan, kaputian Dist. IGCS |  |  | Water System Projects | Households | Contract | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For allotment June 24, 2019 | 2
| 3.1.10 | [7 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 2
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 3.2 | Conduct of Geo-resistivity/drilling Test of Proposed Site |  |  |  | Geo-resistivity/drilling test conducted | - | - | a) | 250000 | [12 empty] | See projects listed below | 2
[9 empty] | b) | - | [13 empty] | 2
[9 empty] | c) | PEO | [13 empty] | 2
[9 empty] | d) | - | [13 empty] | 2
|  |  | Construction of PWS, Brgy. Kiotoy, Panabo City |  |  | Geo-resistivity/drilling test conducted | - | - | a) | 62500 | a) | - | e) | - | a) | 62500 | a) | - | c) | - | a) | - | For cancellation due to the purchase of geo-resistivity equipment | 2
| 3.2.1 | [7 empty] | b) | - | b) | - | f) | - | b) | 62500 | b) | - | d) | - | b) | - |  | 2
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | Construction of PWS, Brgy. Linosutan, Talikud, IGCS |  |  | Geo-resistivity/drilling test conducted | - | - | a) | 62500 | a) | - | e) | - | a) | 62500 | a) | - | c) | - | a) | - | For cancellation due to the purchase of geo-resistivity equipment | 2
| 3.2.2 | [7 empty] | b) | - | b) | - | f) | - | b) | 62500 | b) | - | d) | - | b) | - |  | 2
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | Construction of PWS, Brgy. San Miguel, Samal, IGCS |  |  | Geo-resistivity/drilling test conducted | - | - | a) | 62500 | a) | - | e) | - | a) | 62500 | a) | - | c) | - | a) | - | For cancellation due to the purchase of geo-resistivity equipment | 2
| 3.2.3 | [7 empty] | b) | - | b) | - | f) | - | b) | 62500 | b) | - | d) | - | b) | - |  | 2
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | Construction of PWS, Cacao, Panabo City |  |  | Geo-resistivity/drilling test conducted | - | - | a) | 62500 | a) | - | e) | - | a) | 62500 | a) | - | c) | - | a) | - | For cancellation due to the purchase of geo-resistivity equipment | 2
|  | 3.2.4 | [6 empty] | b) | - | b) | - | f) | - | b) | 62500 | b) | - | d) | - | b) | - |  | 2
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | AC
| 4. Various Government Buildings and Facilities Development Project (Provincewide) |  |  |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of recipients | - | Admin/Contract | a) | 27000000 | [12 empty] | See projects listed below | AC
[9 empty] | b) | Medalla | [13 empty] | AC
[9 empty] | c) | PEO | [13 empty] | AC
[9 empty] | d) | - | [13 empty] | 2
|  |  | Const. of 1 CL Bldg. @ Suawon ES, New Corella |  |  | Bldg. | sq.m | Admin | a) | 1000000 | a) | - | e) | - | a) | 1000000 | a) | - | c) | - | a) | - | On-going | 2
|  | 4.1 | [6 empty] | b) | - | b) | Nov. 19, 2019 | f) | - | b) | 1000000 | b) |  | d) | - | b) | - |  | 2
[9 empty] | c) | PEO | c) | - | g) | - | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | Const. of Municipal Tribal Hall, San Isidro |  |  | Bldg. | sq.m | Admin | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For implementation | 2
|  | 4.2 | [6 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 2
[9 empty] | c) | PEO | c) | - | g) | - | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | Const. of Quail House (PDNSC Ext. Campus), Sto. Niño, Talaingod |  |  | Bldg. | sq.m | Admin | a) | 750000 | a) | - | e) | - | a) | 750000 | a) | - | c) | - | a) | - | On-going | 2
|  | 4.3 | [6 empty] | b) | - | b) | - | f) | - | b) | 750000 | b) | - | d) | - | b) | - |  | 2
[9 empty] | c) | PEO | c) | - | g) | - | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | Completion of Perimeter Steel Fence @ Lunga-og E/S, Brgy. Lunga-og, Sto. Tomas |  |  | Fence | sq.m | Admin | a) | 1630000 | a) | 2019-01-17 | e) | - | a) | 1630000 | a) | 55.12% | c) | 46.28% | a) | 10 | On-going | 2
|  | 4.4 | [6 empty] | b) | Azotes | b) | 2019-10-16 | f) | - | b) | 1630000 | b) | - | d) | -8.84% | b) | 220 |  | 2
[9 empty] | c) | PEO | c) | 2020-03-03 | g) | - | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | AC
|  |  | Const. of DDN Hospital Carmen Zone Annex Bldg. Phase 2, |  |  | Bldg. | - | Contract | a) | 3620000 | a) | 2019-06-28 | e) | - | a) | 3620000 | a) | - | c) | - | a) | - | For implementation | AC
|  | 4.5 | [6 empty] | b) | - | b) | - | f) | - | b) | 3620000 | b) | - | d) | - | b) | - |  | AC
[9 empty] | c) | Digos Constrak Corp/ | c) | - | g) | - | c) | - | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
| 5. Stimulus Projects for Various Barangays |  |  |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | sq.m | Admin | a) | 41500000 | [12 empty] | See projects listed below | 1
[9 empty] | b) | Medalla | [13 empty] | 1
[9 empty] | c) | PEO | [13 empty] | 1
[9 empty] | d) | - | [13 empty] | 1
| CARMEN | [22 empty] | 1
| 5.1 |  | Const. of Multi-Purpose Hall, La Paz, Carmen |  |  | Bldg. | - | - | a) | 500000 | a) | 2019-02-20 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Fund transferred to LGU March 28, 2019 | 1
[9 empty] | b) | - | b) | 2019-08-16 | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 1
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
| 5.2 |  | Const. of Evacuation Center Ph. 3, Sto. Niño, Carmen |  |  | Bldg. | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Amended in the AIP 3rd revision CY 2019/ SB No. 4 CY 2019 changing the location to Purok !-c, Sto. Nino since the previous location was implemented by DPWH | 1
[9 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 1
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 5.3 |  | Const. of Multi-Purpose Hall, Mangalcal, Carmen |  |  | Bldg. | - | - | a) | 500000 | a) | 2019-02-20 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Fund transfer to LGU Carmen, 3/28/2019 with check no. 2574953 and OR no. 0118982 | 2
[9 empty] | b) | - | b) | 2019-09-16 | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 2
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 5.4 |  | Rehab. of Multi-Purpose Hall, Guadalupe, Carmen |  |  | Bldg. | - | - | a) | 500000 | a) | 2019-02-20 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Fund transferred to LGU March 28, 2019 | 2
[9 empty] | b) | - | b) | 2019-08-15 | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 2
[9 empty] | c) | - | c) | 2019-11-13 | g) | - | c) | - | [7 empty] | AC
[9 empty] | d) | - | d) | - | [11 empty] | AC
| 5.5 |  | Const. of Multi-Purpose Hall, Mabuhay, Carmen |  |  | Bldg. | - | - | a) | 500000 | a) | 2019-02-20 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Fund transfer to LGU Carmen, 3/28/2019 with check no. 2574925 and OR no. 0118984 | AC
[9 empty] | b) | - | b) | 2019-08-16 | f) | - | b) | 500000 | b) | - | d) | - | b) | -
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | AC
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 5.6 |  | Const. Canal Lining , Mabaus, Carmen |  |  | Canal lining | - | - | a) | 500000 | a) | 2019-02-20 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Fund transferred to LGU March 28, 2019 | 2
[9 empty] | b) | - | b) |  | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 2
[9 empty] | c) | - | c) |  | g) | - | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 5.7 |  | Rehab. Of Evacuation Center, Alejal, Carmen |  |  | Bldg. | - | - | a) | 500000 | a) | 2019-02-20 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Fund transfer to LGU Carmen, 3/28/2019 with check no.2574949 and OR no. 0118991 | 2
[9 empty] | b) | - | b) | 2019-08-16 | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 2
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 5.8 |  | Compl. Of Evacuation Center, Tuganay, Carmen |  |  | Bldg. | - | - | a) | 500000 | a) | 2019-02-20 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Fund transfer to LGU Carmen, 3/28/2019 with check no. 2574947 and OR no. 0118995 | 2
[9 empty] | b) | - | b) | 2019-08-16 | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 2
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 5.9 |  | Const. of Multi-Purpose hall, Ising, Carmen |  |  | Bldg. | - | - | a) | 500000 | a) | 2019-02-20 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Fund transferred to LGU March 28, 2019 | 2
[9 empty] | b) | - | b) |  | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 2
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 5.1 |  | Rehab. of Multi-Purpose hall, Cebulano, Carmen |  |  | Bldg. | - | - | a) | 500000 | a) | 2019-02-20 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Fund transferred to LGU March 28, 2019 | 2
[9 empty] | b) | - | b) | 2019-08-16 | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 2
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| PANABO CITY | [22 empty] | 2
| 5.11 |  | Rehab. Of Multi-Purpose Hall, Kasilak, Panabo City |  |  | Bldg. | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Amended in AIP 3rd revison CY 2019/ SB No. 4 CY 2019 increasing the project cost to P650,000.00 | 2
[9 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 2
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 5.12 |  | Rehab. Of Multi-Purpose Hall, New Malitbog, Panabo City |  |  | Bldg. | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Amended in AIP 3rd revsion CY 2019 to change the project to Construction of Potable Water System because the original project will be funded by LGU, Panabo City (Brgy. resolution no. 25 series of 2019 dated Aug. 13, 2019 submitted) | 2
[9 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 2
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 2
2
2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 5.13 |  | Desilting of Canal, New Pandan, Panabo City |  |  | Canal lining | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For re inspection to add length for desilting c/o Engr. Canillada Plan prepared can not consume the allocated amount of P500,000.00 for desilting works. | 2
[9 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 2
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 5.14 |  | Const. Of Multi-Purpose Hall, Waterfall, Panabo City |  |  | Bldg. | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For allotment. Sept. 27, 2019 | 2
[9 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 2
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | -
| 5.15 |  | Concreting of Brgy. Road @ Prk. Guyabano, Cagangohan, Panabo City |  |  | Road | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Amended in AIP 3rd revision to change the project to Rehab of Evacuation Center because the original project has no deed of donation.(Brgy. resolution no 41 series of 2019 dated Aug. 16, 2019 submitted | AC
[9 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 2
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 2
2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 5.16 |  | Rehab. Of Evacuation Center, J.P. Laurel, Panabo City |  |  | Bldg. | - | - | a) | 500000 | a) | 2019-10-23 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Sched. Of bidding Dec. 27, 2019 | 2
[9 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 2
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | -
| 5.17 |  | Const. Of Multi-Purpose Hall, Buenavista, Panabo City |  |  | Bldg. | - | - | a) | 500000 | a) | 2019-10-18 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Sched. Of bidding Dec. 27, 2019
[9 empty] | b) | - | b) | - | f) |  | b) | 500000 | b) | - | d) | - | b) | - |  | 2
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 5.18 |  | Rehab. Of Multi-Purpose Hall, San Francisco, Panabo City |  |  | Bldg. | - | - | a) | 500000 | a) | 2019-10-18 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Sched. Of bidding Dec. 27, 2019 | 2
[9 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 2
[9 empty] | c) | - | c) | - | g) |  | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 5.19 |  | Rehab. Of Evacuation Center, Datu Abdul Dadia, Panabo City |  |  | Bldg. | - | - | a) | 500000 | a) | 2019-10-18 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Sched. Of bidding Dec. 27, 2019 | 2
[9 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 2
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 5.2 |  | Impv't./Beautification of Brgy. Grounds, Quezon, Panabo City |  |  | Ground Dev't. | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Re aligned to other stimulus projects that needs additional funding | 2
[9 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | -
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 5.21 |  | Const. of Women Livelihood Center Bldg. , Gredu, Panabo City |  |  | Bldg. | - | - | a) | 500000 | a) | 2019-03-28 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Fund transfer to LGU - 3/28/2019 with check no. 2574926 and OR no. 0166517 - March 28, 2019 | 2
[9 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 2
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 5.23 |  | Const. of Canal Lining at Purok 5, Salvacion, Panabo City |  |  | Bldg. | - | - | a) | 500000 | a) | 2019-10-18 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Procurement on process | 2
[9 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 2
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 5.24 |  | Rehab. Of Health Center, New Visayas, Panabo City |  |  | Bldg. | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Re aligned to other stimulus projects that needs additional funding | 2
[9 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 2
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 5.25 |  | Rehab. Of Multi-Purpose Hall, Little Panay, Panabo City |  |  | Bldg. | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For allotment Dec. 11, 2019 | 2
[9 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 2
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 5.26 |  | Rehab. Of Brgy. Health Center, Dalisay, Panabo City |  |  | Bldg. | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For allotment Dec. 4, 2019 | 2
[9 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 2
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 5.27 |  | Const. of Multi-Purpose Hall, Southern Davao, Panabo City |  |  | Bldg. | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For allotment Dec. 3, 2019 | 2
[9 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 2
[9 empty] | c) | - | c) | - | g) |  | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| STO. TOMAS | [22 empty] | 2
| 5.28 |  | Rehab. Of Evacuation Center, Casig-ang, Sto. Tomas |  |  | Bldg. | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | POW preparation on-going c/o Engr. Uy | 2
[9 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 2
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 5.29 |  | Const. of Brgy. Tibal-og Health Center, Tibal-og, Sto. Tomas |  |  | Bldg. | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | POW preparation completed amounting t oP1,550,000.00. To request for additional funds in order to complete the project to be functional | 2
[9 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 2
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - |  | Nov. 30, 2019 | [9 empty] | 2
| 5.3 |  | Compl.of Brgy. Public Market, La Libertad, Sto. Tomas |  |  | Bldg. | - | - | a) | 500000 | a) |  | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Fund transfer to LGU - 6/26/219 with check no. 2575131 and OR no. 0557457 Completed/ PCR for submission by LGU | 2
[9 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 2
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 5.31 |  | Rehab. Of Evacuation Center, New Visayas, Sto. Tomas |  |  | Bldg. | - | - | a) | 500000 | a) |  | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Fund transfer to LGU - 6/26/219 with check no. 2575132 and OR no. 0557455 For implementation | 2
[9 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 2
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 5.32 |  | Rehab. Of Multi-Purpose Hall, San Vicente, Sto. Tomas |  |  | Bldg. | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Fund transferred to LGU July 5, 2019 On -going | 2
[9 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | -
[9 empty] | c) | - | c) | - | g) |  | c) | - | [7 empty] | AC
[9 empty] | d) | - | d) | - |  | - | [9 empty] | 2
| 5.33 |  | Rehab. Of Multi-Purpose Hall, Salvacion, Sto. Tomas |  |  | Bldg. | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Amended in AIP 3rd revision CY 2019 /SB No. 4 CY 2019increasing the project cost to P1,000,000.00 | 2
[9 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 2
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 5.34 |  | Rehab. Of Multi-Purpose Hall, Pantaron, Sto. Tomas |  |  | Bldg. | - | - | a) | 500000 | a) |  | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Amended in AIP 3rd revision CY 2019 / SB No. 4 CY 2019 increasing the project cost to P550,000.00 | 2
[9 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 2
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 5.35 |  | Rehab. Of Multi-Purpose Hall, Magwawa, Sto. Tomas |  |  | Bldg. | sq.m | Contract | a) | 500000 | a) | June 19 2019 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Procurement on process | 2
[9 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 2
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 5.36 |  | Compl. Of Multi-Purpose Hall, San Jose, Sto. Tomas |  |  | Bldg. | - | - | a) | 500000 | a) |  | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Amended in AIP 3rd revision CY 2019 / SB No. 4 CY 2019 increasing the project cost to P600,000.00 | 2
[9 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 2
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 5.37 |  | Const. of Evacuation Center, Bobongon, Sto. Tomas |  |  | Bldg. | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Re aligned to other stimulus projects that needs additional funding | 2
[9 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 2
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 5.38 |  | Rehab. Of Brgy. Road, Lunga-og, Sto. Tomas |  |  | Bldg. | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Amended in AIP 3rd revision CY 2019 / SB No. 4 CY 2019 increasing the project cost to P600,000.00 | 2
[9 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 2
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 5.39 |  | Rehab. Of Multi-Purpose Hall, New Katipunan, Sto. Tomas |  |  | Bldg. | sq.m | Contract | a) | 500000 | a) | 2019-06-07 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Procurement on process | 2
[9 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 2
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 5.4 |  | Rehab. Of Multi-Purpose Hall, San Miguel, Sto. Tomas |  |  | Bldg. | sq.m | Contract | a) | 500000 | a) | 2019-06-07 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Procurement on process | 2
[9 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 2
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 5.41 |  | Rehab. Of Multi-Purpose Hall, Talomo, Sto. Tomas |  |  | Bldg. | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Fund transfer to LGU - 6/26/2019 with check no. 2575130 and OR no. 0557456 For implementation | 2
[9 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 2
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| IGCS | [22 empty] | 2
| 5.43 |  | Concreting of Brgy. Road From Prk. 3 to Prk. 5, Catagman, IGCS |  |  | Road | km | Contract | a) | 500000 | a) | 2019-01-14 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For implementation | 2
[9 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 2
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 5.44 |  | Rehab. Of Multi-Purpose Hall, San Jose, IGCS |  |  | Bldg. | sq.m | Admin | a) | 500000 | a) | 2019-03-25 | e) | - | a) | 500000 | a) | 33.24% | c) | 21.15% | a) | - | On- going | 2
[9 empty] | b) | Pacquiao | b) | 2019-01-02 | f) | - | b) | 500000 | b) | - | d) | -12.09% | b) | - |  | 2
[9 empty] | c) | PEO | c) | 2020-03-22 | g) | - | c) | - | [7 empty] | 2
[9 empty] | d) | 80 CD | d) | - | [11 empty] | 2
| 5.45 |  | Electrification at Sitio Trinidad, Bandera, IGCS |  |  | Elect. | Households | - | a) | 500000 | a) | 2019-03-25 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Procurement on process | 2
[9 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 2
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 5.47 |  | Rehab. Of Multi-Purpose Hall, Del Monte, IGCS |  |  | Bldg. | - | Admin | a) | 500000 | a) | 2019-05-29 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Pending/ activity undertaken by DPWH | 2 | 4
[9 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 2 | 4
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 5.48 |  | Rehab. Of Multi-Purpose Hall, Aundanao, IGCS |  |  | Bldg. | - | Admin | a) | 500000 | a) | 2019-03-18 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | On -going | 2
[9 empty] | b) | Porras | b) | 2019-11-18 | f) | 64 CD | b) | 500000 | b) | - | d) | - | b) | - |  | 2
[9 empty] | c) | PEO | c) | 2019-12-27 | g) | - | c) | - | [7 empty] | 2
[9 empty] | d) | 60 CD | d) | 2020-02-29 | [11 empty] | 2
| 5.49 |  | Electrification at Upper Purok Rosal, Tagbaobo, IGCS |  |  | Elect. | Households | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Procurement on process. No Abastract | 2
[9 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 2
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 5.5 |  | Const. Of Multi-Purpose Hall, Mambago-B, IGCS |  |  | Bldg. | sq.m | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | 100.00% | c) | 87.51% | a) | 4 | On -going | 2
[9 empty] | b) | Roque | b) | 2019-10-18 | f) | 64 CD | b) | 500000 | b) | 91.44% | d) | -3.93% | b) | 88 |  | 2
[9 empty] | c) | PEO | c) | 2019-12-27 | g) | - | c) | - | [7 empty] | 2 | 4
[9 empty] | d) | 60 CD | d) | 2020-03-29 | [11 empty] | 2 | 4
| 5.51 |  | Const. Of Multi-Purpose Hall, San Antonio, IGCS |  |  | Bldg. | sq.m | - | a) | 500000 | a) | 2019-06-19 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For implementation | 2 | 4
[9 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 2 | 4
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 5.52 |  | Rehab. Of Water System Intake Box and Pipeline, Pangubatan, IGCS |  |  | Water System | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Plan and Pow completed. Waiting of deed of donation | 2 | 4
[9 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 2 | 4
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 5.53 |  | Const. Of Multi-Purpose Hall, Cogon (Talicud), IGCS |  |  | Bldg. | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Procurement on process. For rebidding Dec. 12, 2019 | 2
[9 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 2
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 5.54 |  | Installation of Pipelines, Libertad, IGCS |  |  | Water System | Households | - | a) | 500000 | a) | 2019-03-25 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For implementation | 2
[9 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 2
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 5.55 |  | Rehab. Of Evacuation Center, Libuak, IGCS |  |  | Bldg. | - | - | a) | 500000 | a) | 2019-05-29 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For implementation | 2
[9 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 2
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 5.56 |  | Const. of Water System Project, Pob. Kaputian, IGCS |  |  | Water System | Households | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | for Allotment | 2
[9 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 2
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 5.57 |  | Rehab. Of Potable Water System, San Isidro, Babak, IGCS |  |  | Water System | Households | - | a) | 500000 | a) | 2019-06-19 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For implementation | 2
[9 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 2
[9 empty] | c) | - | c) | - | g) |  | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 5.58 |  | Rehab. Of Potable Water System, San Miguel, IGCS |  |  | Water System | Households | - | a) | 500000 | a) | 2019-02-28 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For implementation | 2
[9 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 2
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 5.59 |  | Const. of Water System Ph.II, San Remegio, IGCS |  |  | Water System | Households | - | a) | 500000 | a) | 2019-05-29 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For implementation | 2
[9 empty] | b) | Porras | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 2
[9 empty] | c) | Admin | c) | - | g) | - | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 6 |  | Electrificatio at Prk. 1,3,4, 6,7 & 8, Licup, IGCS |  |  | Elect. | Households | - | a) | 500000 | a) | 2019-02-20 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Procurement of materials on process | 2
[9 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 2
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 6. Rural Electrification Project (Provincewide) |  |  |  |  | Powerlines/posts installed & rehabilitated | Households | - | a) | 5000000 | [12 empty] | See projects listed below | 2
[9 empty] | b) | Kim Pao Lu | [13 empty] | 2
[9 empty] | c) | - | [13 empty] | 2
[9 empty] | d) | - | [13 empty] | 2
|  |  | Rural Electrification at Pob. Kaputian, (St. Sagrada) IGCS |  |  | Elect. | Households | - | a) | 1000000 | a) | - | e) | - | a) | 1000000 | a) | - | c) | - | a) | - | Procurement on process | 2
|  | 6.1 | [6 empty] | b) | P.Bueno | b) | - | f) | - | b) | 1000000 | b) | - | d) | - | b) | - |  | 2
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| C. 5% CALAMITY FUND CY 2019 | [22 empty] | 2
|  | Revitment of Dike and Slope Proection |  |  |  | Protection dikes/slope protection | - | - | a) | 3000000 | [12 empty] | See projects listed below | 2
| 1 | [7 empty] | b) | -
[9 empty] | c) | - | [13 empty] | 2
[9 empty] | d) | - | [13 empty] | 2
|  |  | Repair/Rehab. Of Upper Tuganay Dike |  |  | creeks and canals deislted | - | - | a) | 1000000 | a) | 2019-08-15 | e) | - | a) | 1000000 | a) | 50.00% | c) | 60% | a) | 9 | On-going | 2
|  | 1.1 | [6 empty] | b) | Toquero | b) | 2019-08-19 | f) | - | b) | 1000000 | b) | - | d) |  | b) | 80 |  | 2
[9 empty] | c) | Admin | c) | 2019-09-29 | g) |  | c) | - | [7 empty] | 2
[9 empty] | d) | 59 C.D | d) | - | [11 empty] | 2
|  | Improvement of roads, drainage and canal |  |  |  | Protection dikes/slope protection | - | - | a) | 3000000 |  |  |  | - | [8 empty] | See project listed below | 2
| 2 | [7 empty] | b) | Paraguya | [13 empty] | 2
[9 empty] | c) | PEO | [13 empty] | 2
[9 empty] | d) | - | [13 empty] | 2
|  |  | Rehab./Impv't. of Prk. 1 - Prk. 2 Sitio Pawas Provincial Road |  |  | Road | km | Admin | a) | 1500000 | a) | 2019-07-23 | e) | - | a) | 1500000 | a) | 17.14% | c) | 1.18% | a) | 2 | On-going | 2
|  | 2.1 | [6 empty] | b) | Sanchez | b) | 2019-08-05 | f) |  | b) | 1500000 | b) | - | d) | -15.96% | b) | 10 |  | AC
[9 empty] | c) | Admin | c) | 2019-09-28 | g) |  | c) | - | [7 empty] | AC
[9 empty] | d) | 55 | d) | - | [11 empty] | AC
| E. | SUPPLEMENTAL BUDGET NO. 3 CY 2019 | [21 empty] | FS
|  | LOCALLY FUNDED PROGRAM/PROJECTS- 20% DEVELOPMENT FUND | [21 empty] | AC
|  | INFRASTRUCTURE DEVELOPMENT PROGRAM | [21 empty] | AC
|  | 1. 8918/ Various Local Roads & Drainage Development Project Construction in Progress- Infrastructure Assets | [21 empty] | AC
|  | ■ | Rehabilitation of Dujali-Pawas-San Vicente Provincial Road, B.E. Dujali |  |  | Road | km | - | a) | 2000000 | a) | - | e) | - | a) | 2000000 | a) | - | c) | - | a) | - | The amount was reduced to P1,102,900.00 | 1
|  | 1.1 | [6 empty] | b) | - | b) | - | f) | - | b) | 2000000 | b) | - | d) | - | b) | - |  | 1
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  | ■ | Repair/Rehabil;itation of Concrete R.d. Jct. Suaon-Libuton Kapalong |  |  | Road | km | - | a) | 1000000 | a) | - | e) | - | a) | 1000000 | a) | - | c) | - | a) | - | For implementation | AC
|  | 1.2 | [6 empty] | b) | - | b) | - | f) | - | b) | 1000000 | b) | - | d) | - | b) | - |  | AC
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | AC
[9 empty] | d) | - | d) | - | [11 empty] | AC
|  | 2. 8918/ VariousWater System Development Project Construction in Progress- Infrastructure Assets | [21 empty] | 1
|  | ■ | Improvement of Potable Water System at Brgy. Mambago- A, Samal District, IGACOS |  |  | Water System | Households | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | (Amended in the AIP 2nd Revision to change the location from Peñaplata to Samal District) PO approved September 2, 2019 | 2
|  | 2.1 | [6 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 2
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  | ■ | Rehabilitation of Potable Water System at Brgy. San Miguel, Samal District, IGACOS |  |  | Water System | Households | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - |  | AC
|  | 2.2 | [6 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | AC
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | AC
[9 empty] | d) | - | d) | - | [11 empty] | AC
|  | ■ | Construction of Potable Water System at Brgy.Linusotan, Kaputian District, IGACOS |  |  | Water System | Households | - | a) | 1300000 | a) | - | e) | - | a) | 1300000 | a) | - | c) | - | a) | - | (Additional 800,000.00 from Const. of PWS in purok 2, Pag-asa, Kapalong which was funded by OPAPP CY 2018) (amended) For allotment- October 15, 2019 | 2
|  | 2.3 | [6 empty] | b) | - | b) | - | f) | - | b) | 1300000 | b) | - | d) | - | b) | - |  | 2
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  | ■ | Rehabilitation of Water System in PEEDO-LPRRC, Brgy. Poblacion, New Corella |  |  | Water System | Households | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For allotment- October 15, 2019 | 2
|  | 2.4 | [6 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 2
[9 empty] | c) | - | c) | - | g) |  | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  | DISASTER REHABILITATION & RECOVERY PROGRAM Building Back Better Project | [21 empty] | AC
|  | 1. Repairs & Maintenance- Infrastructure Assets | [21 empty] | AC
|  | ■ | Disiltation of Tagum Creek |  |  | Desiltation | - | - | a) | 2000000 | a) | - | e) | - | a) | 2000000 | a) | - | c) | - | a) | - | PLAN AND POW on process c/o PEO-PDPM | 2
|  | 1.1 | [6 empty] | b) | - | b) | - | f) | - | b) | 2000000 | b) | - | d) | - | b) | - |  | 2
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | -
|  | ■ | Disiltation of Mactan River (Ph. II) |  |  | Desiltation | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | PLAN AND POW on process c/o PEO-PDPM | FS
|  | 1.2 | [6 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | AC
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | AC
[9 empty] | d) | - | d) | - | [11 empty] | AC
|  | 2. Property, Plant and Equipmen Construction in Progress- Infrastructure Assets | [21 empty] | 2
|  |  | Rehabilitation of Dujali-Balisong-Magupising Provincial Road |  |  | Road | km | Admin | a) | 1280000 | a) | - | e) | - | a) | 1280000 | a) | 100% | c) | 6.48% | a) | - | On-going | 2
|  | 2.1 | [6 empty] | b) | Mellomida | b) | 2019-12-02 | f) | 20 CD | b) | 1280000 | b) | 97.61% | d) | -91.13% | b) | - |  | 2
[9 empty] | c) | PEO | c) | 2020-02-03 | g) | - | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 1
| F. | SUPPLEMENTAL BUDGET NO. 4 CY 2019 | [21 empty] | 1
|  | 1. PEACE AND ORDER PROGRAM/1914 Construction in Progress- Land Improvements | [21 empty] | 2
|  | ■ | Rehabilitation of San Jose- Sitio Mahayahay-Magwawa Provincial Road, Sro. Tomas |  |  | Road | - | - | a) | 1000000 | a) | - | e) | - | a) | 1000000 | a) | - | c) | - | a) | - | POW preparation on-going c/o South District | 2
|  | 1.1 | [6 empty] | b) | - | b) | - | f) | - | b) | 1000000 | b) | - | d) | - | b) | - |  | 2
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  | 2. 8918/ Various Government Buildigs & Facilities Development Project Construction in Progress- Land Improvements | [21 empty] | 2
|  | ■ | Construction of Perimeter Fence of Day Care Center I Nanyo, Panabo City |  |  | Fence | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Sched of bidding Dec. 27, 2019 | 2
|  | 2.1 | [6 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 2
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  | ■ | Construction of Multi-Purpose Building, Balagunan, Sto. Tomas |  |  | Bldg. | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For allotment Dec .3, 2019 | 2
|  | 2.2 | [6 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 2
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  | 3. 8918/ Various Local Roads and Drainaige Development Project Construction in Progress- Infrastructure Assets | [21 empty] | AC
|  | ■ | Rehabilitation of Local Roads at Dalisay-Manay Road Section, Panabo City |  |  | Road | - | - | a) | 246100 | a) | - | e) | - | a) | 246100 | a) | - | c) | - | a) | - |  | 1
|  | 3.1 | [6 empty] | b) | - | b) | - | f) | - | b) | 246100 | b) | - | d) | - | b) | - |  | 1
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  | ■ | Rehabilitation of Local Roads at Sta. Cruz-Jct. Tagpore-Buenavista Raod Section, Panabo City |  |  | Road | - | - | a) | 431000 | a) | - | e) | - | a) | 431000 | a) | - | c) | - | a) | - |  | 2
|  | 3.2 | [6 empty] | b) | - | b) | - | f) | - | b) | 431000 | b) | - | d) | - | b) | - |  | 2
[9 empty] | c) | - | c) | - | g) |  | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  | ■ | Rehabilitation of Local Roads at Taba-Bucana Road Section, Taba, Carmen |  |  | Road | - | - | a) | 220000 | a) | - | e) | - | a) | 220000 | a) | - | c) | - | a) | - |  | 1
|  | 3.3 | [6 empty] | b) | - | b) | - | f) | - | b) | 220000 | b) | - | d) | - | b) | - |  | 1
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  | 2. 8918/ Stimulus Projects for Various Barangays Construction in Progress- Infrastructure Assets | [21 empty] | 1
|  | ■ | Concreting of Brgy. Road Canal, Dujali, B.E. Dujali |  |  | Road | - | contract | a) | 650000 | a) | - | e) | - | a) | 650000 | a) | - | c) | - | a) | - | Alloted Oct. 18, 2019 Procurement on process | FS
|  | 2.1 | [6 empty] | b) | - | b) | - | f) | - | b) | 650000 | b) | - | d) | - | b) | - |  | AC
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | AC
[9 empty] | d) | - | d) | - | [11 empty] | AC
|  | ■ | Desilting and Conretign of Drainage-Main Collector Canal, New Casay, B.E. Dujali |  |  | Desiltation | - | contract | a) | 650000 | a) | - | e) | - | a) | 650000 | a) | - | c) | - | a) | - | For allotment - Sept. 27, 2019 | 1
|  | 2.2 | [6 empty] | b) | - | b) | - | f) | - | b) | 650000 | b) | - | d) | - | b) | - |  | 2
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  | ■ | Concreting of Drainage, Tanglaw, B.E., Dujali |  |  | Drainage | - | contract | a) | 1200000 | a) | - | e) | - | a) | 1200000 | a) | - | c) | - | a) | - | For allotment Sept. 19, 2019 | 2
|  | 2.3 | [6 empty] | b) | - | b) | - | f) | - | b) | 1200000 | b) | - | d) | - | b) | - |  | AC
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  | ■ | Construction of Potable Water System, New Malitbog, Panabo City |  |  | Water System | Households | contract | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For re-inspection and plan revision in order to reflect in the plan the complete details for the project to be functional.P500,000.00 covers only drilling activity | 2
|  | 2.4 | [6 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 2
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  | ■ | Construction of Water System Project, Poblacion Kaputian, Samal |  |  | Water System | Households | contract | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Alloted Oct 17, 2019. Procurement on process | 2
|  | 2.5 | [6 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 1
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | AC
[9 empty] | d) | - | d) | - | [11 empty] | AC
|  | ■ | Construction of Canal Lining at Prk. 5, Salvacion, Panabo City |  |  |  |  | contract | a) | 600000 | a) | - | e) | - | a) | 600000 | a) | - | c) | - | a) | - | Alloted Oct. 18, 2019 Procurement on process | 1
|  | 2.6 | [6 empty] | b) | - | b) | - | f) | - | b) | 600000 | b) | - | d) | - | b) | - |  | AC
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  | ■ | Rehabilitation of Brgy. Road at Lunga-og. Sto. Tomas |  |  |  |  | contract | a) | 600000 | a) | - | e) | - | a) | 600000 | a) | - | c) | - | a) | - | For allotment Sept. 19, 2019 | 2
|  | 2.7 | [6 empty] | b) | - | b) | - | f) | - | b) | 600000 | b) | - | d) | - | b) | - |  | 2
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  | 3. 8918/ Stimulus Projects for Various Barangays Construction in Progress- Bldgs. & Other Structures | [21 empty] | 2
|  | ■ | Construction of Evacuation Center at Purok 1-C Brgy. Sto. Niño, Carmen |  |  |  |  | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For allotment Dec. 3, 2019 | 2
|  | 3.1 | [6 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 2
[9 empty] | c) | - | c) | - | g) |  | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  | ■ | Construction of Multi-Purpose Hall, Waterfall, Panabo City |  |  |  |  | - | a) | 1050000 | a) | - | e) | - | a) | 1050000 | a) | - | c) | - | a) | - | For allotment | 2
|  | 3.2 | [6 empty] | b) | - | b) | - | f) | - | b) | 1050000 | b) | - | d) | - | b) | - |  | 2
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  | ■ | Rehabilitation of Multi-Purpose Hall, San Francisco, Panabo City |  |  |  |  | - | a) | 600000 | a) | - | e) | - | a) | 600000 | a) | - | c) | - | a) | - | Alloted Oct. 18, 2019 Procurement on process | 2
|  | 3.3 | [6 empty] | b) | - | b) | - | f) | - | b) | 600000 | b) | - | d) | - | b) | - |  | 2
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  | ■ | Rehabilitation of Evacuation Center at Datu Abdul Dadia, Panabo City |  |  |  |  | - | a) | 650000 | a) | - | e) | - | a) | 650000 | a) | - | c) | - | a) | - | Sched of bidding -Dec 27, 2019 | 2
|  | 3.4 | [6 empty] | b) | - | b) | - | f) | - | b) | 650000 | b) | - | d) | - | b) | - |  | 2
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  | ■ | Construction of Multi-Purpose Hall, Buenavista, Panabo City |  |  |  |  | - | a) | 1050000 | a) | - | e) | - | a) | 1050000 | a) | - | c) | - | a) | - | Sched of bidding -Dec 27, 2019 | 2
|  | 3.5 | [6 empty] | b) | - | b) | - | f) | - | b) | 1050000 | b) | - | d) | - | b) | - |  | 2
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  | ■ | Rehabilitation of Multi-Purpose Hall, Llittle Panay, Panabo City |  |  |  |  | - | a) | 550000 | a) | - | e) | - | a) | 550000 | a) | - | c) | - | a) | - | For allotment Dec. 11, 2019 | 2
|  | 3.6 | [6 empty] | b) | - | b) | - | f) | - | b) | 550000 | b) | - | d) | - | b) | - |  | 2
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  | ■ | Rehabilitation of Multi-Purpose Hall, Pantaron, Sto. Tomas |  |  |  |  | - | a) | 550000 | a) | - | e) | - | a) | 550000 | a) | - | c) | - | a) | - | Alloted Oct. 18, 2019 Procurement on process | 2
|  | 3.7 | [6 empty] | b) | - | b) | - | f) | - | b) | 550000 | b) | - | d) | - | b) | - |  | 2
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  | ■ | Rehabilitation of Multi-Purpose Hall, Salvacion, Sto. Tomas |  |  |  |  | - | a) | 1000000 | a) | - | e) | - | a) | 1000000 | a) | - | c) | - | a) | - | POW preparation on-going c/o PDPM | 2
|  | 3.8 | [6 empty] | b) | - | b) | - | f) | - | b) | 1000000 | b) | - | d) | - | b) | - |  | 2
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  | ■ | Completion of Multi-Purpose Hall, San Jose, Sto. Tomas |  |  |  |  | - | a) | 600000 | a) | - | e) | - | a) | 600000 | a) | - | c) | - | a) | - | Alloted Nov. 15, 2019 Procurement on process | 2
|  | 3.9 | [6 empty] | b) | - | b) | - | f) | - | b) | 600000 | b) | - | d) | - | b) | - |  | 1
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  | ■ | Rehabilitation of Multi-Purpose Hall, Kasilak, Panabo City |  |  |  |  | - | a) | 650000 | a) | - | e) | - | a) | 650000 | a) | - | c) | - | a) | - | Alloted Nov. 15, 2019 Procurement on process | 2
|  | 4 | [6 empty] | b) | - | b) | - | f) | - | b) | 650000 | b) | - | d) | - | b) | - |  | 2
[9 empty] | c) | - | c) | - | g) |  | c) | - | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  | ■ | Rehabilitation of Brgy. Health Center, Dalisay, Panabo City |  |  |  |  | - | a) | 550000 | a) | - | e) | - | a) | 550000 | a) | - | c) | - | a) | - | For allotment Dec. 4, 2019 | 2
|  | 4.1 | [6 empty] | b) | - | b) | - | f) | - | b) | 550000 | b) | - | d) | - | b) | - |  | 2
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  | ■ | Rehabilitation of Evacuation Center, Kiotoy, Panabo City |  |  |  |  | - | a) | 650000 | a) | - | e) | - | a) | 650000 | a) | - | c) | - | a) | - | Sched of bidding Dec 27, 2019 | 2
|  | 4.2 | [6 empty] | b) | - | b) | - | f) | - | b) | 650000 | b) | - | d) | - | b) | - |  | 2
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  | ■ | Rehabilitation of Evacuation Center, Cagangohan, Panabo City |  |  |  |  | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | POW for approval Nov. 5, 2019 | 2
|  | 4.3 | [6 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 2
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  | ■ | Rehabilitation of Multi-Purpose Bldg. (Brgy. Hall) Tagpopongan, IGACOS |  |  |  |  | - | a) | 174460.33 | a) | - | e) | - | a) | 174460.33 | a) | - | c) | - | a) | - | For allotment Nov. 5, 2019 | 2
|  | 4.4 | [6 empty] | b) | - | b) | - | f) | - | b) | 174460.33 | b) | - | d) | - | b) | - |  | 2
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| G. | TRUST FUND | [21 empty] | 2
|  | 1. CMGP 2019 | [21 empty] | 2
|  | ■ | Road Upgrading of Sto Nino - Kabankalan - La Paz Provincial Road, Carmen |  |  |  |  | - | a) | 44461624.67 | a) | CY 2019 | e) | - | a) | 44561687 | a) | 11.69% | c) | 47.56% | a) | 42 | On-going | 2
|  | 1.1 | [6 empty] | b) | Comidoy | b) | 2019-10-07 | f) | - | b) | 44561687 | b) | - | d) | 35.87% | b) | 610 |  | 2
[9 empty] | c) | GP & H CONST. | c) | 2020-05-15 | g) | - | c) | - | [7 empty] | 2
[9 empty] | d) | 222 C.D | d) | [12 empty] | 2
|  | ■ | Road Upgrading of Jct Highway - Sto Nino - La Paz - San Vicenter Provincial Road, Carmen |  |  |  |  | - | a) | 80481331.34 | a) | CY 2019 | e) | - | a) | 80481331.34 | a) | 22.77% | c) | 33.12% | a) | 40 | On-going | 2
|  | 1.2 | [6 empty] | b) | Fernandez | b) | 2019-10-07 | f) | - | b) | 80481331.34 | b) | - | d) | 10.35% | b) | 660 |  | 2
[9 empty] | c) | Tagum Builders | c) | 2020-06-22 | g) | - | c) | 26653002.4999 | [7 empty] | 2
[9 empty] | d) | 259 C.D | d) | [12 empty] | 2
| II. | PROJECTS UNDER THE CURRENT APPROPRIATION | [21 empty] | 2
| A. | GENERAL FUND CY 2020 | [21 empty] | 2
| INFRASTRUCTURE DEVELOPMENT PROGRAMS | [22 empty] | 2
| Road ID |  | 1. Repair/Maintenance of Provincial Roads & Bridges |  |  | Road Maintenance | KM | MBA | a) | 11801752 | a) | 2020-01-02 | [10 empty] | See list of Provincial Roads | 2
[7 empty] | 283.38 |  | b) | Paraguya | b) | 2020-01-02 | [11 empty] | 2
| 11DAN | [7 empty] | c) | PEO | c) | 2020-12-31 | [11 empty] | 2
[9 empty] | d) | 261 days | d) | - | [11 empty] | 2
|  |  | CEBULANO - MANGALCAL |  |  | Road Maintenance | 7.1 | Admin | a) | 134672.7 | a) | 2020-01-02 | e) | - | a) | 134672.7 | a) | - | c) | - | a) | - | On-going | 2
| 073 | [7 empty] | b) |  | b) |  | f) | - | b) | 134672.7 | b) | - | d) | - | b) | - |  | 2
[9 empty] | c) | PEO | c) | - | g) | - | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | CEBULANO - MANGALCAL |  |  | CBRMC | 7.1 | Contract | a) | 131004.66 | a) | - | e) | - | a) | 131004.66 | a) | - | c) | - | a) | - |  | 2
| 073 | [7 empty] | b) | - | b) | - | f) | - | b) | 131004.66 | b) | - | d) | - | b) | -
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | TUBOD - BASA - MANGALCAL |  |  | Road Maintenance | 8.33 | Admin | a) | 143530.25 | a) | 2020-01-02 | e) | - | a) | 143530.25 | a) | - | c) | - | a) | - | On-going | 2
| 074 | [7 empty] | b) |  | b) |  | f) | - | b) | 143530.25 | b) | - | d) | - | b) | - |  | 2
[9 empty] | c) | PEO | c) | - | g) | - | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | TUBOD - BASA - MANGALCAL |  |  | CBRMC | 8.33 | Contract | a) | 106856.33 | a) | - | e) | - | a) | 106856.33 | a) | - | c) | - | a) | - |  | 2
| 074 | [7 empty] | b) |  | b) | - | f) | - | b) | 106856.33 | b) | - | d) | - | b) | - |  | 2
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | UPPER MANGALCAL - LOWER MANGALCAL |  |  | Road Maintenance | 2.68 | Admin | a) | 82374.21 | a) | 2020-01-02 | e) | - | a) | 82374.21 | a) | - | c) | - | a) | - | On-going | 2
| 078 | [7 empty] | b) |  | b) |  | f) | - | b) | 82374.21 | b) | - | d) | - | b) | - |  | 1
[9 empty] | c) | PEO | c) | - | g) | - | c) | -
[9 empty] | d) | - | d) | -
|  |  | UPPER MANGALCAL - LOWER MANGALCAL |  |  | CBRMC | 2.68 | Contract | a) | 72444.97 | a) | - | e) | - | a) | 72444.97 | a) | - | c) | - | a) | - |  | 2
| 078 | [7 empty] | b) | - | b) | - | f) | - | b) | 72444.97 | b) | - | d) | - | b) | - |  | 2
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | CEBULANO - LOCETA |  |  | Road Maintenance | 9.93 | Admin | a) | 72051.43 | a) | 2020-01-02 | e) | - | a) | 72051.43 | a) | - | c) | - | a) | - | On-going
| 079 | [7 empty] | b) |  | b) |  | f) | - | b) | 72051.43 | b) | - | d) | - | b) | -
[9 empty] | c) | PEO | c) | - | g) | - | c) | -
[9 empty] | d) | - | d) | - | [11 empty] | AC |  | 893809.45
|  |  | CEBULANO - LOCETA |  |  | CBRMC | 9.93 | Contract | a) | 47089.26 | a) | - | e) | - | a) | 47089.26 | a) | - | c) | - | a) | - |  | FS
| 079 | [7 empty] | b) | - | b) | - | f) | - | b) | 47089.26 | b) | - | d) | - | b) | -
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | FS
[9 empty] | d) | - | d) | - | [11 empty] | AC
|  |  | JCT. HIGHWAY CARMEN - MANGALCAL - TUBOD |  |  | Road Maintenance | 4.85 | Admin | a) | 462895.06 | a) | 2020-01-02 | e) | - | a) | 462895.06 | a) | - | c) | - | a) | - | On-going | AC
| 082 | [7 empty] | b) |  | b) |  | f) | - | b) | 462895.06 | b) | - | d) | - | b) | - |  | AC
[9 empty] | c) | PEO | c) | - | g) | - | c) | - | [7 empty] | AC
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | JCT. HIGHWAY CARMEN - MANGALCAL - TUBOD |  |  | CBRMC | 4.85 | Contract | a) | 259594.46 | a) | - | e) | - | a) | 259594.46 | a) | - | c) | - | a) | - |  | 1
| 082 | [7 empty] | b) | - | b) | - | f) | - | b) | 259594.46 | b) | - | d) | - | b) | - |  | 1
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | AC
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | ISING - SADPODON - TABA - DILADILA |  |  | Road Maintenance | 11.6 | Admin | a) | 226651.27 | a) | 2020-01-02 | e) | - | a) | 226651.27 | a) | - | c) | - | a) | - | On-going | 1
| 086 | [7 empty] | b) |  | b) |  | f) | - | b) | 226651.27 | b) | - | d) | - | b) | - |  | 1
[9 empty] | c) | PEO | c) | - | g) | - | c) | - | [7 empty] | AC
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | ISING - SADPODON - TABA - DILADILA |  |  | CBRMC | 11.6 | Contract | a) | 135230.61 | a) | - | e) | - | a) | 135230.61 | a) | - | c) | - | a) | - |  | 1
| 086 | [7 empty] | b) | - | b) | - | f) | - | b) | 135230.61 | b) | - | d) | - | b) | - |  | 1
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | AC
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | TUGANAY - TABA |  |  | Road Maintenance | 2.99 | Admin | a) | 169418.15 | a) | 2020-01-02 | e) | - | a) | 169418.15 | a) | - | c) | - | a) | - | On-going | 1
| 087 | [7 empty] | b) |  | b) |  | f) | - | b) | 169418.15 | b) | - | d) | - | b) | - |  | 1
[9 empty] | c) | PEO | c) | - | g) | - | c) | - | [7 empty] | AC
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | TUGANAY - TABA |  |  | CBRMC | 2.99 | Contract | a) | 102630.37 | a) | - | e) | - | a) | 102630.37 | a) | - | c) | - | a) | - |  | 1
| 087 | [7 empty] | b) | - | b) | - | f) | - | b) | 102630.37 | b) | - | d) | - | b) | - |  | 1
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | AC
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | JCT. HIGHWAY TUGANAY - TABA |  |  | Road Maintenance | 7.52 | Admin | a) | 222375.04 | a) | 2020-01-02 | e) | - | a) | 222375.04 | a) | - | c) | - | a) | - | On-going | 1
| 088 | [7 empty] | b) |  | b) |  | f) | - | b) | 222375.04 | b) | - | d) | - | b) | - |  | 1
[9 empty] | c) | PEO | c) | - | g) | - | c) | - | [7 empty] | AC
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | JCT. HIGHWAY TUGANAY - TABA |  |  | CBRMC | 7.52 | Contract | a) | 57955.99 | a) | - | e) | - | a) | 57955.99 | a) | - | c) | - | a) | - |  | 1
| 088 | [7 empty] | b) | - | b) | - | f) | - | b) | 57955.99 | b) | - | d) | - | b) | - |  | 1
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | AC
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | JCT HIGHWAY - ISING - MAGSAYSAY |  |  | Road Maintenance | 8.7 | Admin | a) | 478128.48 | a) | 2020-01-02 | e) | - | a) | 478128.48 | a) | - | c) | - | a) | - | On-going | 1
| 089 | [7 empty] | b) |  | b) |  | f) | - | b) | 478128.48 | b) | - | d) | - | b) | - |  | 1
[9 empty] | c) | PEO | c) | - | g) | - | c) | - | [7 empty] | AC
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | JCT HIGHWAY - ISING - MAGSAYSAY |  |  | CBRMC | 8.7 | Contract | a) | 212505.24 | a) | - | e) | - | a) | 212505.24 | a) | - | c) | - | a) | - |  | 1
| 089 | [7 empty] | b) | - | b) | - | f) | - | b) | 212505.24 | b) | - | d) | - | b) | - |  | 1
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | AC
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | MALIGAYA - NEW CAMILING |  |  | Road Maintenance | 4.11 | Admin | a) | 51790.26 | a) | 2020-01-02 | e) | - | a) | 51790.26 | a) | - | c) | - | a) | - | On-going | 1
| 090 | [7 empty] | b) |  | b) |  | f) | - | b) | 51790.26 | b) | - | d) | - | b) | - |  | 1
` | [8 empty] | c) | PEO | c) | - | g) | - | c) | - | [7 empty] | AC
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | MALIGAYA - NEW CAMILING |  |  | CBRMC | 4.11 | Contract | a) | 83915.44 | a) | - | e) | - | a) | 83915.44 | a) | - | c) | - | a) | - |  | 1
| 090 | [7 empty] | b) | - | b) | - | f) | - | b) | 83915.44 | b) | - | d) | - | b) | - |  | 1
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | AC
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | NEW CAMILING - ALEJAL - LOWER MAGSAYSAY |  |  | Road Maintenance | 2.73 | Admin | a) | 277852.05 | a) | 2020-01-02 | e) | - | a) | 277852.05 | a) | - | c) | - | a) | - | On-going | 1
| 091 | [7 empty] | b) |  | b) |  | f) | - | b) | 277852.05 | b) | - | d) | - | b) | - |  | 1
` | [8 empty] | c) | PEO | c) | - | g) | - | c) | - | [7 empty] | AC
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | NEW CAMILING - ALEJAL - LOWER MAGSAYSAY |  |  | CBRMC | 2.73 | Contract | a) | 150927.01 | a) | - | e) | - | a) | 150927.01 | a) | - | c) | - | a) | - |  | 1
| 091 | [7 empty] | b) | - | b) | - | f) | - | b) | 150927.01 | b) | - | d) | - | b) | - |  | 1
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | AC
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | JCT. HIGHWAY - TUGANAY - ANIBONGAN |  |  | Road Maintenance | 3.34 | Admin | a) | 139609.7 | a) | 2020-01-02 | e) | - | a) | 139609.7 | a) | - | c) | - | a) | - | On-going | 1
| 094 | [7 empty] | b) |  | b) |  | f) | - | b) | 139609.7 | b) | - | d) | - | b) | - |  | 1
` | [8 empty] | c) | PEO | c) | - | g) | - | c) | - | [7 empty] | AC
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | JCT. HIGHWAY - TUGANAY - ANIBONGAN |  |  | CBRMC | 3.34 | Contract | a) | 93574.75 | a) | - | e) | - | a) | 93574.75 | a) | - | c) | - | a) | - |  | 1
| 094 | [7 empty] | b) | - | b) | - | f) | - | b) | 93574.75 | b) | - | d) | - | b) | - |  | 1
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | AC
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | ANIBONGAN - GUADALUPE |  |  | Road Maintenance | 2.19 | Admin | a) | 85559.79 | a) | 2020-01-02 | e) | - | a) | 85559.79 | a) | - | c) | - | a) | - | On-going | 1
| 095 | [7 empty] | b) |  | b) |  | f) | - | b) | 85559.79 | b) | - | d) | - | b) | - |  | 1
` | [8 empty] | c) | PEO | c) | - | g) | - | c) | - | [7 empty] | AC
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | ANIBONGAN - GUADALUPE |  |  | CBRMC | 2.19 | Contract | a) | 72444.97 | a) | - | e) | - | a) | 72444.97 | a) | - | c) | - | a) | - |  | 1
| 095 | [7 empty] | b) | - | b) | - | f) | - | b) | 72444.97 | b) | - | d) | - | b) | - |  | 1
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | AC
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | TUGANAY - ANIBONGAN - SAN ISIDRO |  |  | Road Maintenance | 4.98 | Admin | a) | 344085.79 | a) | 2020-01-02 | e) | - | a) | 344085.79 | a) | - | c) | - | a) | - | On-going | 1
| 096 | [7 empty] | b) |  | b) |  | f) | - | b) | 344085.79 | b) | - | d) | - | b) | - |  | 1
` | [8 empty] | c) | PEO | c) | - | g) | - | c) | - | [7 empty] | AC
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | TUGANAY - ANIBONGAN - SAN ISIDRO |  |  | CBRMC | 4.98 | Contract | a) | 115911.95 | a) | - | e) | - | a) | 115911.95 | a) | - | c) | - | a) | - |  | 1
| 096 | [7 empty] | b) | - | b) | - | f) | - | b) | 115911.95 | b) | - | d) | - | b) | - |  | 1
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | AC
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | JCT. ANIBONGAN - PRK. 2, 7, 5 SAN ISIDRO |  |  | Road Maintenance | 9.17 | Admin | a) | 89575.84 | a) | 2020-01-02 | e) | - | a) | 89575.84 | a) | - | c) | - | a) | - | On-going | 1
| 097 | [7 empty] | b) |  | b) |  | f) | - | b) | 89575.84 | b) | - | d) | - | b) | - |  | 1
` | [8 empty] | c) | PEO | c) | - | g) | - | c) | - | [7 empty] | AC
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | JCT. ANIBONGAN - PRK. 2, 7, 5 SAN ISIDRO |  |  | CBRMC | 9.17 | Contract | a) | 110478.58 | a) | - | e) | - | a) | 110478.58 | a) | - | c) | - | a) | - |  | 1
| 097 | [7 empty] | b) | - | b) | - | f) | - | b) | 110478.58 | b) | - | d) | - | b) | - |  | 1
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | AC
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | ANIBONGAN - SALVACION - CABAY-ANGAN |  |  | Road Maintenance | 5.89 | Admin | a) | 279123.9 | a) | 2020-01-02 | e) | - | a) | 279123.9 | a) | - | c) | - | a) | - | On-going | 1
| 098 | [7 empty] | b) |  | b) |  | f) | - | b) | 279123.9 | b) | - | d) | - | b) | - |  | 1
` | [8 empty] | c) | PEO | c) | - | g) | - | c) | - | [7 empty] | AC
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | ANIBONGAN - SALVACION - CABAY-ANGAN |  |  | CBRMC | 5.89 | Contract | a) | 162397.48 | a) | - | e) | - | a) | 162397.48 | a) | - | c) | - | a) | - |  | 1
| 098 | [7 empty] | b) | - | b) | - | f) | - | b) | 162397.48 | b) | - | d) | - | b) | - |  | 1
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | AC
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | MABAUS - CABAY-ANGAN |  |  | Road Maintenance | 5.57 | Admin | a) | 113320.9 | a) | 2020-01-02 | e) | - | a) | 113320.9 | a) | - | c) | - | a) | - | On-going | 1
| 099 | [7 empty] | b) |  | b) |  | f) | - | b) | 113320.9 | b) | - | d) | - | b) | - |  | 1
` | [8 empty] | c) | PEO | c) | - | g) | - | c) | - | [7 empty] | AC
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | MABAUS - CABAY-ANGAN |  |  | CBRMC | 5.57 | Contract | a) | 90556.21 | a) | - | e) | - | a) | 90556.21 | a) | - | c) | - | a) | - |  | 1
| 099 | [7 empty] | b) | - | b) | - | f) | - | b) | 90556.21 | b) | - | d) | - | b) | - |  | 1
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | AC
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | JCT. HIGHWAY GUADALUPE - BDRY. TAGUM |  |  | Road Maintenance | 6.93 | Admin | a) | 517780.87 | a) | 2020-01-02 | e) | - | a) | 517780.87 | a) | - | c) | - | a) | - | On-going | 1
| 101 | [7 empty] | b) |  | b) |  | f) | - | b) | 517780.87 | b) | - | d) | - | b) | - |  | 1
` | [8 empty] | c) | PEO | c) | - | g) | - | c) | - | [7 empty] | AC
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | JCT. HIGHWAY GUADALUPE - BDRY. TAGUM |  |  | CBRMC | 6.93 | Contract | a) | 231823.89 | a) | - | e) | - | a) | 231823.89 | a) | - | c) | - | a) | - |  | 1
| 101 | [7 empty] | b) | - | b) | - | f) | - | b) | 231823.89 | b) | - | d) | - | b) | - |  | 1
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | AC
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | DUJALI - TANGLAW |  |  | Road Maintenance | 7.26 | Admin | a) | 135183.27 | a) | 2020-01-02 | e) | - | a) | 135183.27 | a) | - | c) | - | a) | - | On-going | 1
| 104 | [7 empty] | b) |  | b) |  | f) | - | b) | 135183.27 | b) | - | d) | - | b) | - |  | 1
` | [8 empty] | c) | PEO | c) | - | g) | - | c) | - | [7 empty] | AC
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | DUJALI - TANGLAW |  |  | CBRMC | 7.26 | Contract | a) | 94178.48 | a) | - | e) | - | a) | 94178.48 | a) | - | c) | - | a) | - |  | 1
| 104 | [7 empty] | b) | - | b) | - | f) | - | b) | 94178.48 | b) | - | d) | - | b) | - |  | 1
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | AC
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | POBLACION DUJALI - PRK. 8 DUJALI |  |  | Road Maintenance | 4.58 | Admin | a) | 329064 | a) | 2020-01-02 | e) | - | a) | 329064 | a) | - | c) | - | a) | - | On-going | 1
| 105 | [7 empty] | b) |  | b) |  | f) | - | b) | 329064 | b) | - | d) | - | b) | - |  | 1
` | [8 empty] | c) | PEO | c) | - | g) | - | c) | - | [7 empty] | AC
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | POBLACION DUJALI - PRK. 8 DUJALI |  |  | CBRMC | 4.58 | Contract | a) | 193371.11 | a) | - | e) | - | a) | 193371.11 | a) | - | c) | - | a) | - |  | 1
| 105 | [7 empty] | b) | - | b) | - | f) | - | b) | 193371.11 | b) | - | d) | - | b) | - |  | 1
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | AC
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | DUJALI - SAN ISIDRO |  |  | Road Maintenance | 14.48 | Admin | a) | 112652.73 | a) | 2020-01-02 | e) | - | a) | 112652.73 | a) | - | c) | - | a) | - | On-going | 1
| 107 | [7 empty] | b) |  | b) |  | f) | - | b) | 112652.73 | b) | - | d) | - | b) | - |  | 1
` | [8 empty] | c) | PEO | c) | - | g) | - | c) | - | [7 empty] | AC
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | DUJALI - SAN ISIDRO |  |  | CBRMC | 14.48 | Contract | a) | 78482.06 | a) | - | e) | - | a) | 78482.06 | a) | - | c) | - | a) | - |  | 1
| 107 | [7 empty] | b) | - | b) | - | f) | - | b) | 78482.06 | b) | - | d) | - | b) | - |  | 1
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | AC
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | NEW CASAY - BUGTONG TALISAY |  |  | Road Maintenance | 9.66 | Admin | a) | 74294.5 | a) | 2020-01-02 | e) | - | a) | 74294.5 | a) | - | c) | - | a) | - | On-going | 1
| 108 | [7 empty] | b) |  | b) |  | f) | - | b) | 74294.5 | b) | - | d) | - | b) | - |  | 1
` | [8 empty] | c) | PEO | c) | - | g) | - | c) | - | [7 empty] | AC
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | NEW CASAY - BUGTONG TALISAY |  |  | CBRMC | 9.66 | Contract | a) | 64596.78 | a) | - | e) | - | a) | 64596.78 | a) | - | c) | - | a) | - |  | 1
| 108 | [7 empty] | b) | - | b) | - | f) | - | b) | 64596.78 | b) | - | d) | - | b) | - |  | 1
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | AC
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | DUJALI - BALISONG - MAGUPISING |  |  | Road Maintenance | 0.46 | Admin | a) | 235776.07 | a) | 2020-01-02 | e) | - | a) | 235776.07 | a) | - | c) | - | a) | - | On-going | 1
| 113 | [7 empty] | b) |  | b) |  | f) | - | b) | 235776.07 | b) | - | d) | - | b) | - |  | 1
` | [8 empty] | c) | PEO | c) | - | g) | - | c) | - | [7 empty] | AC
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | DUJALI - BALISONG - MAGUPISING |  |  | CBRMC | 0.46 | Contract | a) | 115911.95 | a) | - | e) | - | a) | 115911.95 | a) | - | c) | - | a) | - |  | 1
| 113 | [7 empty] | b) | - | b) | - | f) | - | b) | 115911.95 | b) | - | d) | - | b) | - |  | 1
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | AC
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | DUJALI - PAWAS - SAN VICENTE |  |  | Road Maintenance | 4.92 | Admin | a) | 141544.99 | a) | 2020-01-02 | e) | - | a) | 141544.99 | a) | - | c) | - | a) | - | On-going | 1
| 117 | [7 empty] | b) |  | b) |  | f) | - | b) | 141544.99 | b) | - | d) | - | b) | - |  | 1
` | [8 empty] | c) | PEO | c) | - | g) | - | c) | - | [7 empty] | AC
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | DUJALI - PAWAS - SAN VICENTE |  |  | CBRMC | 4.92 | Contract | a) | 140060.27 | a) | - | e) | - | a) | 140060.27 | a) | - | c) | - | a) | - |  | 1
| 117 | [7 empty] | b) | - | b) | - | f) | - | b) | 140060.27 | b) | - | d) | - | b) | - |  | 1
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | AC
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | JCT. SALVACION - SAN VICENTE - CABAY-ANGAN |  |  | Road Maintenance | 3.19 | Admin | a) | 168583.81 | a) | 2020-01-02 | e) | - | a) | 168583.81 | a) | - | c) | - | a) | - | On-going | 1
| 118 | [7 empty] | b) |  | b) |  | f) | - | b) | 168583.81 | b) | - | d) | - | b) | - |  | 1
` | [8 empty] | c) | PEO | c) | - | g) | - | c) | - | [7 empty] | AC
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | JCT. SALVACION - SAN VICENTE - CABAY-ANGAN |  |  | CBRMC | 3.19 | Contract | a) | 158775.23 | a) | - | e) | - | a) | 158775.23 | a) | - | c) | - | a) | - |  | 1
| 118 | [7 empty] | b) | - | b) | - | f) | - | b) | 158775.23 | b) | - | d) | - | b) | - |  | 1
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | AC
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | BACALI - CASIG-ANG - LIBERTAD |  |  | Road Maintenance | 4.61 | Admin | a) | 167836.14 | a) | 2020-01-02 | e) | - | a) | 167836.14 | a) | - | c) | - | a) | - | On-going | 1
| 123 | [7 empty] | b) |  | b) |  | f) | - | b) | 167836.14 | b) | - | d) | - | b) | - |  | 1
` | [8 empty] | c) | PEO | c) | - | g) | - | c) | - | [7 empty] | AC
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | BACALI - CASIG-ANG - LIBERTAD |  |  | CBRMC | 4.61 | Contract | a) | 131608.37 | a) | - | e) | - | a) | 131608.37 | a) | - | c) | - | a) | - |  | 1
| 123 | [7 empty] | b) | - | b) | - | f) | - | b) | 131608.37 | b) | - | d) | - | b) | - |  | 1
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | AC
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | KINAMAYAN - MOSLOG - MAHAYAG |  |  | Road Maintenance | 4.17 | Admin | a) | 114628.54 | a) | 2020-01-02 | e) | - | a) | 114628.54 | a) | - | c) | - | a) | - | On-going | 1
| 124 | [7 empty] | b) |  | b) |  | f) | - | b) | 114628.54 | b) | - | d) | - | b) | - |  | 1
` | [8 empty] | c) | PEO | c) | - | g) | - | c) | - | [7 empty] | AC
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | KINAMAYAN - MOSLOG - MAHAYAG |  |  | CBRMC | 4.17 | Contract | a) | 91159.92 | a) | - | e) | - | a) | 91159.92 | a) | - | c) | - | a) | - |  | 1
| 124 | [7 empty] | b) | - | b) | - | f) | - | b) | 91159.92 | b) | - | d) | - | b) | - |  | 1
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | AC
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | KINAMAYAN - LUNGA-OG |  |  | Road Maintenance | 5.1 | Admin | a) | 100416.26 | a) | 2020-01-02 | e) | - | a) | 100416.26 | a) | - | c) | - | a) | - | On-going | 1
| 126 | [7 empty] | b) |  | b) |  | f) | - | b) | 100416.26 | b) | - | d) | - | b) | - |  | 1
` | [8 empty] | c) | PEO | c) | - | g) | - | c) | - | [7 empty] | AC
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | KINAMAYAN - LUNGA-OG |  |  | CBRMC | 5.1 | Contract | a) | 64596.78 | a) | - | e) | - | a) | 64596.78 | a) | - | c) | - | a) | - |  | 1
| 126 | [7 empty] | b) | - | b) | - | f) | - | b) | 64596.78 | b) | - | d) | - | b) | - |  | 1
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | AC
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | PRK. APITONG - UPPER BALISONG - DALISAY |  |  | Road Maintenance | 1.3 | Admin | a) | 150598.24 | a) | 2020-01-02 | e) | - | a) | 150598.24 | a) | - | c) | - | a) | - | On-going | 1
| 128 | [7 empty] | b) |  | b) |  | f) | - | b) | 150598.24 | b) | - | d) | - | b) | - |  | 1
` | [8 empty] | c) | PEO | c) | - | g) | - | c) | - | [7 empty] | AC
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | PRK. APITONG - UPPER BALISONG - DALISAY |  |  | CBRMC | 1.3 | Contract | a) | 142475.11 | a) | - | e) | - | a) | 142475.11 | a) | - | c) | - | a) | - |  | 1
| 128 | [7 empty] | b) | - | b) | - | f) | - | b) | 142475.11 | b) | - | d) | - | b) | - |  | 1
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | AC
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | LOS AMIGOS 1 - ESPERANZA - LOS AMIGOS 2 |  |  | Road Maintenance | 2.54 | Admin | a) | 97116.27 | a) | 2020-01-02 | e) | - | a) | 97116.27 | a) | - | c) | - | a) | - | On-going | 1
| 130 | [7 empty] | b) |  | b) |  | f) | - | b) | 97116.27 | b) | - | d) | - | b) | - |  | 1
` | [8 empty] | c) | PEO | c) | - | g) | - | c) | - | [7 empty] | AC
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | LOS AMIGOS 1 - ESPERANZA - LOS AMIGOS 2 |  |  | CBRMC | 2.54 | Contract | a) | 131608.37 | a) | - | e) | - | a) | 131608.37 | a) | - | c) | - | a) | - |  | 1
| 130 | [7 empty] | b) | - | b) | - | f) | - | b) | 131608.37 | b) | - | d) | - | b) | - |  | 1
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | AC
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | MUGAS - LANATAD |  |  | Road Maintenance | 3.34 | Admin | a) | 65482.21 | a) | 2020-01-02 | e) | - | a) | 65482.21 | a) | - | c) | - | a) | - | On-going | 1
| 131 | [7 empty] | b) |  | b) |  | f) | - | b) | 65482.21 | b) | - | d) | - | b) | - |  | 1
` | [8 empty] | c) | PEO | c) | - | g) | - | c) | - | [7 empty] | AC
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | MUGAS - LANATAD |  |  | CBRMC | 3.34 | Contract | a) | 31996.54 | a) | - | e) | - | a) | 31996.54 | a) | - | c) | - | a) | - |  | 1
| 131 | [7 empty] | b) | - | b) | - | f) | - | b) | 31996.54 | b) | - | d) | - | b) | - |  | 1
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | AC
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | MUGAS - LUNGA-OG |  |  | Road Maintenance | 11.54 | Admin | a) | 96490.97 | a) | 2020-01-02 | e) | - | a) | 96490.97 | a) | - | c) | - | a) | - | On-going | 1
| 132 | [7 empty] | b) |  | b) |  | f) | - | b) | 96490.97 | b) | - | d) | - | b) | - |  | 1
` | [8 empty] | c) | PEO | c) | - | g) | - | c) | - | [7 empty] | AC
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | MUGAS - LUNGA-OG |  |  | CBRMC | 11.54 | Contract | a) | 74256.11 | a) | - | e) | - | a) | 74256.11 | a) | - | c) | - | a) | - |  | 1
| 132 | [7 empty] | b) | - | b) | - | f) | - | b) | 74256.11 | b) | - | d) | - | b) | - |  | 1
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | AC
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | NEW KATIPUNAN - PANTARON |  |  | Road Maintenance | 2.5 | Admin | a) | 71748.41 | a) | 2020-01-02 | e) | - | a) | 71748.41 | a) | - | c) | - | a) | - | On-going | 1
| 134 | [7 empty] | b) |  | b) |  | f) | - | b) | 71748.41 | b) | - | d) | - | b) | - |  | 1
` | [8 empty] | c) | PEO | c) | - | g) | - | c) | - | [7 empty] | AC
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | NEW KATIPUNAN - PANTARON |  |  | CBRMC | 2.5 | Contract | a) | 53126.32 | a) | - | e) | - | a) | 53126.32 | a) | - | c) | - | a) | - |  | 1
| 134 | [7 empty] | b) | - | b) | - | f) | - | b) | 53126.32 | b) | - | d) | - | b) | - |  | 1
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | AC
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | STO. TOMAS - BDRY. MAMACAO |  |  | Road Maintenance | 4.32 | Admin | a) | 195671.17 | a) | 2020-01-02 | e) | - | a) | 195671.17 | a) | - | c) | - | a) | - | On-going | 1
| 135 | [7 empty] | b) |  | b) |  | f) | - | b) | 195671.17 | b) | - | d) | - | b) | - |  | 1
` | [8 empty] | c) | PEO | c) | - | g) | - | c) | - | [7 empty] | AC
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | STO. TOMAS - BDRY. MAMACAO |  |  | CBRMC | 4.32 | Contract | a) | 116515.66 | a) | - | e) | - | a) | 116515.66 | a) | - | c) | - | a) | - |  | 1
| 135 | [7 empty] | b) | - | b) | - | f) | - | b) | 116515.66 | b) | - | d) | - | b) | - |  | 1
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | AC
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | FD. RD. 3 - SAN JOSE |  |  | Road Maintenance | 4.32 | Admin | a) | 176994.35 | a) | 2020-01-02 | e) | - | a) | 176994.35 | a) | - | c) | - | a) | - | On-going | 1
| 136 | [7 empty] | b) |  | b) |  | f) | - | b) | 176994.35 | b) | - | d) | - | b) | - |  | 1
` | [8 empty] | c) | PEO | c) | - | g) | - | c) | - | [7 empty] | AC
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | FD. RD. 3 - SAN JOSE |  |  | CBRMC | 4.32 | Contract | a) | 112893.42 | a) | - | e) | - | a) | 112893.42 | a) | - | c) | - | a) | - |  | 1
| 136 | [7 empty] | b) | - | b) | - | f) | - | b) | 112893.42 | b) | - | d) | - | b) | - |  | 1
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | AC
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | NAFCO - BOBONGON |  |  | Road Maintenance | 1.32 | Admin | a) | 89179.68 | a) | 2020-01-02 | e) | - | a) | 89179.68 | a) | - | c) | - | a) | - | On-going | 1
| 139 | [7 empty] | b) |  | b) |  | f) | - | b) | 89179.68 | b) | - | d) | - | b) | - |  | 1
` | [8 empty] | c) | PEO | c) | - | g) | - | c) | - | [7 empty] | AC
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | NAFCO - BOBONGON |  |  | CBRMC | 1.32 | Contract | a) | 80293.17 | a) | - | e) | - | a) | 80293.17 | a) | - | c) | - | a) | - |  | 1
| 139 | [7 empty] | b) | - | b) | - | f) | - | b) | 80293.17 | b) | - | d) | - | b) | - |  | 1
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | AC
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | BDRY. TAGUM - CROSSING KINAMAYAN - STO. TOMAS |  |  | Road Maintenance | 5.13 | Admin | a) | 790874.1 | a) | 2020-01-02 | e) | - | a) | 790874.1 | a) | - | c) | - | a) | - | On-going | 1
| 146 | [7 empty] | b) |  | b) |  | f) | - | b) | 790874.1 | b) | - | d) | - | b) | - |  | 1
` | [8 empty] | c) | PEO | c) | - | g) | - | c) | - | [7 empty] | AC
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | BDRY. TAGUM - CROSSING KINAMAYAN - STO. TOMAS |  |  | CBRMC | 5.13 | Contract | a) | 429840.12 | a) | - | e) | - | a) | 429840.12 | a) | - | c) | - | a) | - |  | 1
| 146 | [7 empty] | b) | - | b) | - | f) | - | b) | 429840.12 | b) | - | d) | - | b) | - |  | 1
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | AC
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | SAN JOSE - SITIO MAHAYAHAY, MAGWAWA |  |  | Road Maintenance | 3.22 | Admin | a) | 22943.54 | a) | 2020-01-02 | e) | - | a) | 22943.54 | a) | - | c) | - | a) | - | On-going | 1
| 151 | [7 empty] | b) |  | b) |  | f) | - | b) | 22943.54 | b) | - | d) | - | b) | - |  | 1
` | [8 empty] | c) | PEO | c) | - | g) | - | c) | - | [7 empty] | AC
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | SAN JOSE - SITIO MAHAYAHAY, MAGWAWA |  |  | CBRMC | 3.22 | Contract | a) | 30789.12 | a) | - | e) | - | a) | 30789.12 | a) | - | c) | - | a) | - |  | 1
| 151 | [7 empty] | b) | - | b) | - | f) | - | b) | 30789.12 | b) | - | d) | - | b) | - |  | 1
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | AC
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  | B. | 20% Development Fund CY 2020 | [20 empty] | 1
| PEACE AND ORDER PROGRAM | [22 empty] | 1
` |  | 1. Rural Electrification Project |  |  |  | Rural Electrification to cater the needs of brgys. | - | - | a) | 1500000 | [12 empty] | See projects listed below | AC
[9 empty] | b) | - | [13 empty] | 1
[9 empty] | c) | - | [13 empty] | 1
[9 empty] | d) | - | [13 empty] | 1
|  | ■ | Completion of Single Phase Line at Purok 6 and Purok 7, Brgy. Cogon, Babak Distirct, IGACOS |  |  | Rural Electrification to cater the needs of brgys. | - | - | a) | 1000000 | a) | - | e) | - | a) | 1000000 | a) | - | c) | - | a) | - |  | AC
|  | 1.1 | [6 empty] | b) | - | b) | - | f) | - | b) | 1000000 | b) | - | d) | - | b) | - |  | 1
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
` |  | ■ | Completion of Single Phase Line at Purok Perlas, Brgy. Sta. Cruz, Talicud (Day Care Center), IGACOS |  |  | Rural Electrification to cater the needs of brgys. | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - |  | AC
|  | 1.2 | [6 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 1
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
| Road ID | 2. Rehabilitation of Provincial Roads & Bridges |  |  |  | Road Maintenance | KM | MBA | a) | 47357000 | a) |  | e) | - | a) | 47357000 | a) | - | c) | - | a) | 46 | See list of Provincial Roads | AC
[9 empty] | b) | Matuguinas | b) |  | f) | - | b) | 47357000 | b) | - | d) | - | b) | 920 |  | 1
| 11DAN | [7 empty] | c) | PEO | c) |  | g) | - | c) | - | [7 empty] | 1
[9 empty] | d) | 261 days | d) | - | [11 empty] | 1
` | PEACE AND ORDER PROGRAM | [22 empty] | AC
|  |  | Fr. Rd. 3 - San Jose |  |  | Road Rehabilitaion | KM | Admin | a) | 8000000 | a) |  | e) | - | a) | 8000000 | a) | - | c) | - | a) | - |  | 1
| 008 | [7 empty] | b) |  | b) |  | f) | - | b) | 8000000 | b) | - | d) | - | b) | - |  | 1
[9 empty] | c) | PEO | c) | - | g) | - | c) | - | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | AC
| INFRASTRUCTURE DEVELOPMENT PROGRAMS | [22 empty] | 1
|  |  | Lower Asuncion - Upper Asuncion |  |  | Road Rehabilitaion | KM | Admin | a) | 1302000 | a) |  | e) | - | a) | 1302000 | a) | - | c) | - | a) | - |  | 1
| 007 | [7 empty] | b) |  | b) |  | f) | - | b) | 1302000 | b) | - | d) | - | b) | - |  | 1
` | [8 empty] | c) | PEO | c) | - | g) | - | c) | - | [7 empty] | AC
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | Jct. Highway - Carmen - Mangalcal - Tubod |  |  | Road Rehabilitaion | KM | Admin | a) | 1323000 | a) | - | e) | - | a) | 1323000 | a) | - | c) | - | a) | - |  | 1
| 030 | [7 empty] | b) |  | b) | - | f) | - | b) | 1323000 | b) | - | d) | - | b) | - |  | 1
[9 empty] | c) | PEO | c) | - | g) | - | c) | - | [7 empty] | AC
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | Tuganay - Taba |  |  | Road Rehabilitaion | KM | Admin | a) | 1431000 | a) |  | e) | - | a) | 1431000 | a) | - | c) | - | a) | - |  | 1
| 031 | [7 empty] | b) |  | b) |  | f) | - | b) | 1431000 | b) | - | d) | - | b) | - |  | 1
[9 empty] | c) | PEO | c) | - | g) | - | c) | - | [7 empty] | FS
[9 empty] | d) | - | d) | -
|  |  | Jct. Highway - Ising - Magsaysay |  |  | Road Rehabilitaion | KM | Admin | a) | 6000000 | a) | - | e) | - | a) | 6000000 | a) | - | c) | - | a) | -
| 069 | [7 empty] | b) |  | b) | - | f) | - | b) | 6000000 | b) | - | d) | - | b) | -
[9 empty] | c) | PEO | c) | - | g) | - | c) | -
[9 empty] | d) | - | d) | -
|  |  | Jct. Highway - Guadalupe - Bdry. Tagum |  |  | Road Rehabilitaion | KM | Admin | a) | 910000 | a) | - | e) | - | a) | 910000 | a) | - | c) | - | a) | - |  | 2
| 069 | [7 empty] | b) |  | b) | - | f) | - | b) | 910000 | b) | - | d) | - | b) | - |  | 1
[9 empty] | c) | PEO | c) | - | g) | - | c) | - | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | Sitio Malaga - Tibulao |  |  | Road Rehabilitaion | KM | Admin | a) | 350000 | a) | - | e) | - | a) | 350000 | a) | - | c) | - | a) | - |  | 2
| 069 | [7 empty] | b) |  | b) | - | f) | - | b) | 350000 | b) | - | d) | - | b) | - |  | 1
[9 empty] | c) | PEO | c) | - | g) | - | c) | - | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | Prk. 5 RJS - Prk. 6 New Casay |  |  | Road Rehabilitaion | KM | Admin | a) | 350000 | a) | - | e) | - | a) | 350000 | a) | - | c) | - | a) | - |  | FS
| 069 | [7 empty] | b) |  | b) | - | f) | - | b) | 350000 | b) | - | d) | - | b) | - |  | AC
[9 empty] | c) | PEO | c) | - | g) | - | c) | - | [7 empty] | AC
[9 empty] | d) | - | d) | - | [11 empty] | AC
|  |  | Dujali - Pawas - San Vicente |  |  | Road Rehabilitaion | KM | Admin | a) | 350000 | a) | - | e) | - | a) | 350000 | a) | - | c) | - | a) | -
` | 069 | [7 empty] | b) |  | b) | - | f) | - | b) | 350000 | b) | - | d) | - | b) | - |  | AC
[9 empty] | c) | PEO | c) | - | g) | - | c) | - | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | Los Amigos 1 - Esperanza - Los Amigos 2 |  |  | Road Rehabilitaion | KM | Admin | a) | 350000 | a) | - | e) | - | a) | 350000 | a) | - | c) | - | a) | - |  | 1
| 069 | [7 empty] | b) |  | b) | - | f) | - | b) | 350000 | b) | - | d) | - | b) | -
` | [8 empty] | c) | PEO | c) | - | g) | - | c) | - | [7 empty] | AC
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | San Miguel - Crossing Kinamayan |  |  | Road Rehabilitaion | KM | Admin | a) | 19200000 | a) | - | e) | - | a) | 19200000 | a) | - | c) | - | a) | - |  | 1
| 069 | [7 empty] | b) |  | b) | - | f) | - | b) | 19200000 | b) | - | d) | - | b) | - |  | 1
` | [8 empty] | c) | PEO | c) | - | g) | - | c) | - | [7 empty] | AC
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | Fd. Rd. 2 - Sto. Tomas - Magwawa |  |  | Road Rehabilitaion | KM | Admin | a) | 350000 | a) | - | e) | - | a) | 350000 | a) | - | c) | - | a) | - |  | 1
| 069 | [7 empty] | b) |  | b) | - | f) | - | b) | 350000 | b) | - | d) | - | b) | - |  | 1
` | [8 empty] | c) | PEO | c) | - | g) | - | c) | - | [7 empty] | AC
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | Menzi - Balagunan - Tulalian |  |  | Road Rehabilitaion | KM | Admin | a) | 3720500 | a) | - | e) | - | a) | 3720500 | a) | - | c) | - | a) | - |  | 1
| 069 | [7 empty] | b) |  | b) | - | f) | - | b) | 3720500 | b) | - | d) | - | b) | - |  | 1
` | [8 empty] | c) | PEO | c) | - | g) | - | c) | - | [7 empty] | AC
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | Jct,. Bdry. Tagum- Talomo |  |  | Road Rehabilitaion | KM | Admin | a) | 3720500 | a) | - | e) | - | a) | 3720500 | a) | - | c) | - | a) | - |  | 1
| 069 | [7 empty] | b) |  | b) | - | f) | - | b) | 3720500 | b) | - | d) | - | b) | - |  | 1
` | [8 empty] | c) | PEO | c) | - | g) | - | c) | - | [7 empty] | AC
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  | 3. Various Local Roads & Drainage Dev't. Project |  |  |  | Rehabilitaion |  | - | a) | 12590910 | a) |  | e) | - | a) | - | a) |  | c) |  | a) | - | See projects listed below | 1
[9 empty] | b) |  | b) |  | f) | - | b) | - | b) | - | d) |  | b) | - |  | 1
` | [8 empty] | c) |  | c) |  | g) | - | c) | - | [7 empty] | AC
[9 empty] | d) |  | d) | [12 empty] | 1
|  | ■ | Rehab. Of Various Local Roads @ Island Garden City of Samal |  |  | Rehabilitaion |  | - | a) | 2518182 | a) | - | e) | - | a) | 2518182 | a) | - | c) | - | a) | - | Plan On-going | 1
|  | 3.1 | [6 empty] | b) | - | b) | - | f) | - | b) | 2518182 | b) | - | d) | - | b) | - |  | 1
` | [8 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | AC
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  | ■ | Rehab. Of Various Local Roads @ Panabo City |  |  | Rehabilitaion |  | - | a) | 2518182 | a) | - | e) | - | a) | 2518182 | a) | - | c) | - | a) | - | Plan On-going | 1
|  | 3.2 | [6 empty] | b) | - | b) | - | f) | - | b) | 2518182 | b) | - | d) | - | b) | - |  | 1
` | [8 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | AC
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  | ■ | Rehab. Of Various Local Roads @ B.E Dujali |  |  | Rehabilitaion |  | - | a) | 2518182 | a) | - | e) | - | a) | 2518182 | a) | - | c) | - | a) | - | Plan On-going | 1
|  | 3.3 | [6 empty] | b) | - | b) | - | f) | - | b) | 2518182 | b) | - | d) | - | b) | - |  | 1
` | [8 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | AC
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  | ■ | Rehab. Of Various Local Roads @ Carmen |  |  | Rehabilitaion |  | - | a) | 2518182 | a) | - | e) | - | a) | 2518182 | a) | - | c) | - | a) | - | Plan On-going | 1
|  | 3.4 | [6 empty] | b) | - | b) | - | f) | - | b) | 2518182 | b) | - | d) | - | b) | - |  | 1
` | [8 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | AC
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  | ■ | Rehab. Of Various Local Roads @ Sto. Tomas |  |  | Rehabilitaion |  | - | a) | 2518182 | a) | - | e) | - | a) | 2518182 | a) | - | c) | - | a) | - | Plan On-going | 1
|  | 3.5 | [6 empty] | b) | - | b) | - | f) | - | b) | 2518182 | b) | - | d) | - | b) | - |  | 1
` | [8 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | AC
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  | 4. Various Government Buildings and Facilities Development Project |  |  |  | Various Bldgs./Facilities |  | - | a) | 10290000 | [12 empty] | See projects listed below | 1
[9 empty] | b) | [14 empty] | 1
` | [8 empty] | c) | [14 empty] | AC
[9 empty] | d) | [14 empty] | 1
|  | ■ | Construction of Commercial Building at Kinawitnon, IGACOS, Babak |  |  | Various Bldgs./Facilities |  | - | a) | 2000000 | a) | - | e) | - | a) | 2000000 | a) | - | c) | - | a) | - | Plan On-going | 1
|  | 4.1 | [6 empty] | b) | - | b) | - | f) | - | b) | 2000000 | b) | - | d) | - | b) | - |  | 1
` | [8 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | AC
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  | ■ | Improvement of Provincial Engineer's Office 2nd District Office Phase 2, Carmen |  |  | Various Bldgs./Facilities |  | - | a) | 1590000 | a) | - | e) | - | a) | 1590000 | a) | - | c) | - | a) | - | Plan On-going | 1
|  | 4.2 | [6 empty] | b) | - | b) | - | f) | - | b) | 1590000 | b) | - | d) | - | b) | - |  | 1
[9 empty] | c) | - | c) | - | g) | - | c) | -
[9 empty] | d) | - | d) | -
|  | ■ | Construction of DDN hospital Carmen Zone Annex Building Phase 3, Carmen |  |  | Various Bldgs./Facilities |  | - | a) | 800000 | a) | - | e) | - | a) | 800000 | a) | - | c) | - | a) | - | Plan On-going
|  | 4.3 | [6 empty] | b) | - | b) | - | f) | - | b) | 800000 | b) | - | d) | - | b) | -
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  | ■ | Construction of IP Council of Women Training Center, Camansa Kamadi District, Asuncion |  |  | Various Bldgs./Facilities |  | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Plan On-going | 1
|  | 4.4 | [6 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 1
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  | ■ | Construction of Municipal Triball Hall, B.E. Dujali |  |  | Various Bldgs./Facilities |  | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Plan On-going | 1
|  | 4.5 | [6 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 1
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  | ■ | Construction of Municipal Triball Hall, Sto. Tomas |  |  | Various Bldgs./Facilities |  | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Plan On-going | 1
|  | 4.6 | [6 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 1
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  | ■ | Construction of Fence at Tulalian National High School, Tulalian, Sto. Tomas |  |  | Various Bldgs./Facilities |  | - | a) | 1500000 | a) | - | e) | - | a) | 1500000 | a) | - | c) | - | a) | - | Plan On-going | 1
|  | 4.7 | [6 empty] | b) | - | b) | - | f) | - | b) | 1500000 | b) | - | d) | - | b) | - |  | 1
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  | ■ | Construction of Two(2) Classroom at Tibulao Elem. School, Tibulao, Carmen |  |  | Various Bldgs./Facilities |  | - | a) | 2900000 | a) | - | e) | - | a) | 2900000 | a) | - | c) | - | a) | - | Plan On-going | 1
|  | 4.8 | [6 empty] | b) | - | b) | - | f) | - | b) | 2900000 | b) | - | d) | - | b) | - |  | 1
[9 empty] | c) | - | c) | - | g) | - | c) | -
[9 empty] | d) | - | d) | -
| C. | 5% CALAMITY FUND CY 2020
DISASTER PREVENTION AND MITIGATION PROGRAM
| I. FLOOD CONTROL AND SLOPE PROTECTION PROJECT | [22 empty] | 2
|  | Desiltation/Excavation of Rivers & Creeks |  |  |  | Desiltation/Excavation |  | - | a) | 6630206 | [12 empty] | See projects listed below | 1
| 1 | [7 empty] | b) | Matuguinas | [13 empty] | 1
[9 empty] | c) | PEO | [13 empty] | 1
[9 empty] | d) | - | [13 empty] | 2
|  |  | Improvement and Desiltation of Camoning Creek |  |  | Desiltation/Excavation |  | - | a) | 2500000 | a) | - | e) | - | a) | 2500000 | a) | - | c) | - | a) | - | Plan On-going | 1
|  | 1.1 | [6 empty] | b) | - | b) | - | f) | - | b) | 2500000 | b) | - | d) | - | b) | - |  | 1
[9 empty] | c) | PEO | c) | - | g) | - | c) | - | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | Improvement and Desiltation of Ising Creek |  |  | Desiltation/Excavation |  | - | a) | 2000000 | a) | - | e) | - | a) | 2000000 | a) | - | c) | - | a) | - | Plan On-going | 1
|  | 1.2 | [6 empty] | b) | - | b) | - | f) | - | b) | 2000000 | b) | - | d) | - | b) | - |  | 1
[9 empty] | c) | PEO | c) | - | g) | - | c) | - | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | Desiltation of Buhang Creek, Anibongan, Carmen |  |  | Desiltation/Excavation |  | - | a) | 2130206 | a) | - | e) | - | a) | 2130206 | a) | - | c) | - | a) | - | Plan On-going | 1
|  | 1.3 | [6 empty] | b) | - | b) | - | f) | - | b) | 2130206 | b) | - | d) | - | b) | - |  | 1
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  | Revetment of Dike and Slope Protection |  |  |  | Rehab./Impv't. |  |  | a) | 1000000 | [12 empty] | See project listed below | 1
| 2 | [7 empty] | b) | Matuguinas | [13 empty] | 1
[9 empty] | c) | PEO | [13 empty] | 1
[9 empty] | d) | - | [13 empty] | 2
|  |  | Rehab./Impv't. of San Miguel - Moslog - Kinamayan, Sto. Tomas |  |  | Rehab./Impv't. |  | - | a) | 1000000 | a) | - | e) | - | a) | 1000000 | a) | - | c) | - | a) | - | Plan On-going | 1
|  | 1.1 | [6 empty] | b) | - | b) | - | f) | - | b) | 1000000 | b) | - | d) | - | b) | - |  | 1
[9 empty] | c) | PEO | c) | - | g) | - | c) | - | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  | Improvement of Roads, Drainage and Canal |  |  |  | Rehab./Impv't. |  | - | a) | 1000000 | [12 empty] | See projects listed below | 1
| 3 | [7 empty] | b) | Matuguinas | [13 empty] | 1
[9 empty] | c) | PEO | [13 empty] | 1
[9 empty] | d) | - | [13 empty] | 2
|  |  | Improvement of Mangalcal to Diamond Creek Farm to Market Road Opening |  |  | Rehab./Impv't. |  | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Plan On-going | 1
|  | 1.1 | [6 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 1
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | FS
|  |  | Improvement of Mabaus - Salvacion Provincial Road Continuing Road Opening |  |  | Rehab./Impv't. |  | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Plan On-going
|  | 1.2 | [6 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | -
[9 empty] | c) | - | c) | - | g) | - | c) | -
[9 empty] | d) | - | d) | -
| 2 | Improvement of Bridges and Cross Drainage |  |  |  | Impv't. |  | - | a) | 2000000 | [12 empty] | See project listed below
[9 empty] | b) | Matuguinas
[9 empty] | c) | PEO
[9 empty] | d) | -
|  |  | Single Barrel Box Culvert at Mangalcal-Diamond Creek, Brgy. Mangalcal, Carmen |  |  | Rehab./Impv't. |  | - | a) | 2000000 | a) | - | e) | - | a) | 2000000 | a) | - | c) | - | a) | - | Plan On-going
|  | 1.1 | [6 empty] | b) | - | b) | - | f) | - | b) | 2000000 | b) | - | d) | - | b) | -
[9 empty] | c) | - | c) | - | g) | - | c) | -
[9 empty] | d) | - | d) | -
| E. | SOCIAL WELFARE AND DEVELOPMENT
|  | 1. CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) |  |  |  | Bldg. | sq.m | Admin/Contract | a) | 6000000 | [12 empty] | See list of projects
[9 empty] | b) | -
[9 empty] | c) | -
[9 empty] | d) | -
|  |  | Const. of Day Care Center, JP Laurel, Panabo City |  |  | Bldg. | sq.m | - | a) | 1000000 | a) | - | e) | - | a) | 1000000 | a) | - | c) | - | a) | - | For preparation of POW and Plans
|  | 1.1 | [6 empty] | b) | - | b) | - | f) | - | b) | 1000000 | b) | - | d) | - | b) | -
[9 empty] | c) | - | c) | - | g) | - | c) | -
[9 empty] | d) | - | d) | -
|  |  | Const. of Day Care Center, Dujali, B.E. Dujali |  |  | Bldg. | sq.m | - | a) | 1000000 | a) | - | e) | - | a) | 1000000 | a) | - | c) | - | a) | - | For preparation of POW and Plans
|  | 1.2 | [6 empty] | b) | - | b) | - | f) | - | b) | 1000000 | b) | - | d) | - | b) | -
[9 empty] | c) | - | c) | - | g) | - | c) | -
[9 empty] | d) | - | d) | -
|  |  | Const. of Day Care Center, Tibal-og, Sto Tomas |  |  | Bldg. | sq.m | - | a) | 1000000 | a) | - | e) | - | a) | 1000000 | a) | - | c) | - | a) | - | For preparation of POW and Plans
|  | 1.3 | [6 empty] | b) | - | b) | - | f) | - | b) | 1000000 | b) | - | d) | - | b) | -
[9 empty] | c) | - | c) | - | g) | - | c) | -
[9 empty] | d) | - | d) | -
|  |  | Compl./Rep. Day Care Center, Cabay-angan, B.E. Dujali |  |  | Bldg. | sq.m | - | a) | 300000 | a) | - | e) | - | a) | 300000 | a) | - | c) | - | a) | - | For preparation of POW and Plans
|  | 1.4 | [6 empty] | b) | - | b) | - | f) | - | b) | 300000 | b) | - | d) | - | b) | -
[9 empty] | c) | - | c) | - | g) | - | c) | -
[9 empty] | d) | - | d) | -
|  |  | Compl./Rep. Day Care Center, Tanglaw, B.E. Dujali |  |  | Bldg. | sq.m | - | a) | 300000 | a) | - | e) | - | a) | 300000 | a) | - | c) | - | a) | - | For preparation of POW and Plans
|  | 1.5 | [6 empty] | b) | - | b) | - | f) | - | b) | 300000 | b) | - | d) | - | b) | -
[9 empty] | c) | - | c) | - | g) | - | c) | -
[9 empty] | d) | - | d) | -
|  |  | Compl./Rep. Day Care Center, Salvacion, Carmen |  |  | Bldg. | sq.m | - | a) | 300000 | a) | - | e) | - | a) | 300000 | a) | - | c) | - | a) | - | For preparation of POW and Plans
|  | 1.6 | [6 empty] | b) | - | b) | - | f) | - | b) | 300000 | b) | - | d) | - | b) | -
[9 empty] | c) | - | c) | - | g) | - | c) | -
[9 empty] | d) | - | d) | -
|  |  | Compl./Rep. Day Care Center, San Agustin, IGCS |  |  | Bldg. | sq.m | - | a) | 300000 | a) | - | e) | - | a) | 300000 | a) | - | c) | - | a) | - | For preparation of POW and Plans
|  | 1.7 | [6 empty] | b) | - | b) | - | f) | - | b) | 300000 | b) | - | d) | - | b) | -
[9 empty] | c) | - | c) | - | g) | - | c) | -
[9 empty] | d) | - | d) | -
|  |  | Compl./Rep. Day Care Center, Toril, IGCS |  |  | Bldg. | sq.m | - | a) | 300000 | a) | - | e) | - | a) | 300000 | a) | - | c) | - | a) | - | For preparation of POW and Plans
|  | 1.8 | [6 empty] | b) | - | b) | - | f) | - | b) | 300000 | b) | - | d) | - | b) | -
[9 empty] | c) | - | c) | - | g) | - | c) | -
[9 empty] | d) | - | d) | -
|  |  | Compl./Rep. Day Care Center, Tibal-og, Sto. Tomas |  |  | Bldg. | sq.m | - | a) | 600000 | a) | - | e) | - | a) | 600000 | a) | - | c) | - | a) | - | For preparation of POW and Plans
|  | 1.9 | [6 empty] | b) | - | b) | - | f) | - | b) | 600000 | b) | - | d) | - | b) | -
[9 empty] | c) | - | c) | - | g) | - | c) | -
[9 empty] | d) | - | d) | -
|  |  | Compl./Rep. Day Care Center, Talomo, Sto. Tomas |  |  | Bldg. | sq.m | - | a) | 300000 | a) | - | e) | - | a) | 300000 | a) | - | c) | - | a) | - | For preparation of POW and Plans
|  | 2 | [6 empty] | b) | - | b) | - | f) | - | b) | 300000 | b) | - | d) | - | b) | -
[9 empty] | c) | - | c) | - | g) | - | c) | -
[9 empty] | d) | - | d) | -
|  |  | Compl./Rep. Day Care Center, Kinamayan, Sto. Tomas |  |  | Bldg. | sq.m | - | a) | 300000 | a) | - | e) | - | a) | 300000 | a) | - | c) | - | a) | - | For preparation of POW and Plans
|  | 2.1 | [6 empty] | b) | - | b) | - | f) | - | b) | 300000 | b) | - | d) | - | b) | -
[9 empty] | c) | - | c) | - | g) | - | c) | -
[9 empty] | d) | - | d) | -
|  |  | Compl./Rep. Day Care Center, La Libertad, Sto. Tomas |  |  | Bldg. | sq.m | - | a) | 300000 | a) | - | e) | - | a) | 300000 | a) | - | c) | - | a) | - | For preparation of POW and Plans
|  | 2.2 | [6 empty] | b) | - | b) | - | f) | - | b) | 300000 | b) | - | d) | - | b) | -
[9 empty] | c) | - | c) | - | g) | - | c) | -
[9 empty] | d) | - | d) | -
|  |  | Mark | Municipality/City |  | Color
|  |  | 1 | Asuncion |  | Red
|  |  | 2 | B.E. Dujali |  | Yellow
|  | GF- GENERAL FUND | 3 | Carmen |  | Blue | [10 empty] | TF - TRUST FUND (NATIONAL FUNDED PROJECT)
|  | 20% DF - 20% DEV'T. FUND | 4 | Kapalong |  | Pink | [10 empty] | a) SLRF - Special Local Road Fund
|  | 5% CF - 5% CALAMITY FUND | 5 | New Corella |  | Gray | [10 empty] | b) KALSADA - Konkreto at Ayos na Lansangan Tungo sa Pangkalahatang Kaunlaran
|  | CO - CAPITAL OUTLAY | 6 | San Isidro |  | Orange | [10 empty] | c) PRDP - Philippine Rural Development Projects
|  | CONG. FUND - CONGRESSIONAL FUND | 7 | Sto Tomas |  | Sky Blue | [10 empty] | d) SELAP - Support to Emergency and Livelihood Assistance Project
|  |  | 8 | Talaingod |  | Violet | [10 empty] | e) PAMANA - Payapa at Masaganang Pamayanan
|  | SEF - SPECIAL EDUCATIONAL UFND | 9 | Panabo City |  | Brown | [10 empty] | f) CBRMC - Community Based Road Maintenance Contracting
|  |  | 10 | IGACOS |  | Yellow Green | [10 empty] | g) MBC - Maintenance by Contract
|  |  | 11 | Tagum City |  | Green | [10 empty] | h) PCF-Performance Challenge Fund-DILG
i) FMRDP - Farm to Market Road
j.) CMGP - Conditional Grant to Provinces
k.) OPAPP - Office of the President Adviser on the Peace Process
l.) LGSF-AM - Local Government Support Fund Assistance to Municipalities
| Prepared by: |  |  |  | Checked | [12 empty] | Recommending Approval
Noted
| GILBERT G. MAMBULAO JR |  |  |  | ELISA A. BARCENA | TESSIE G. ABABON | [9 empty] | JIVELLYN B. CO | [5 empty] | GLENN A. OLANDRIA
| Engineer II |  |  |  | Engineer IV- Engineering Dist 1, Area Engineer |  | Engineer IV-Engineering Dist 2, Area Engineer | [9 empty] | Asst. PG-Department Head |  |  |  |  | Provincial Engineer
AMELITA TIMBAL
| Engineer I |  |  |  | EDWIN S. MISA |  |  |  | MARILOU A. FORONDA
[5 empty] | Engineer IV- PDPM Division Head |  |  |  | Engineer IV- QC Division Head
Formulas:
Date A lot. Rel. = [Date A lot. Rel., row above]

## Annual 2019_Completed Dist 1 (hidden)
PROVINCE OF DAVAO DEL NORTE
ACCOMPLISHMENT REPORT
Annual 2019
SECTOR: ECONOMIC (INFRASTRUCTURE DEV'T. PROGRAM)
OFFICE/AGENCY: PROVINCIAL ENGINEER'S OFFICE
COMPLETED PROJECTS Dist 1
| Name of Project |  |  |  |  | Type | Physical | Mode | PROJECT DATA | [5 empty] | Financial (000) |  | Physical Accomplishment |  |  |  | Employment |  | REMARKS
[6 empty] | of | Target | of | a) Project Cost |  | a) Date A lot. Rel. |  | e) # of days suspended |  | a) Program |  | a) Planned |  | c) Actual |  | Generated
[6 empty] | Project | (Descrip | Impl. | b) Project Engineer |  | b) Date Started |  | f) # of days extended |  | b) Allotment |  | b) Revised |  | d) Slippage |  | a) # of Persons
[6 empty] | (Location) | tion) |  | c) Implementor |  | c)Target Compl. Date |  | g) Date completed |  | c) Disbursement | [5 empty] | b) Man-days
[9 empty] | d) Duration |  | d) Revised Compl. Date
| I. | PROJECTS UNDER THE CONTINUING APPROPRIATION | [21 empty] | AP | 893809.45
|  | A. | TRUST FUND | [20 empty] | AC
|  |  | DILG FUND CY 2016 | [20 empty] | AC
|  |  | 1.1 | 1.1 Improvement of DILG Building, Gov't. |  | Bldg. | 400 sq.m | Contract | a) | 5000000 | a) | CY 2016 | e) | 35 days | a) | 5000000 | a) | 100.00% | c) | 100.00% | a) | 8 | Completed as per physical accomplishment. | 1
|  |  |  | Center, Mankilam, Tagum City |  |  |  |  | b) | Pasiona | b) | 06/01/18 | f) | - | b) | 5000000 | b) | - | d) | - | b) | 240 | Financial documents still on process | 1
[9 empty] | c) | PEO | c) | 12/31/18 | g) | 03/31/19 | c) | 4,786,995.44 | [7 empty] | 1
[9 empty] | d) | 249 CD | d) | 03/30/19 | [11 empty] | 1
|  |  | KALSADA CY 2016 | [20 empty] | AC
|  |  | 1.1 Upgrading of Prk. Narafil – Barangay |  |  | Road | 2.03 | Contract. | a) | 51420795.98 | a) | CY 2016 | e) | - | a) | 51420795.98 | a) | 100.00% | c) | 100.00% | a) | 12 | Completed as per physical accomplishment. | 2
|  |  | Site Magupising Provincial Road | [5 empty] | b) | Andoy | b) | 04/18/18 | f) | 178 CD | b) | 51420795.98 | b) | - | d) | - | b) | 336 | Financial documents still on process | 2
|  |  | (Part of 60.329230.72M) (Contract Cost: P 43.597322.62M) | [5 empty] | c) | DCP | c) | 12/20/18 | g) | 05/07/19 | c) | 46,279,283.18 | [7 empty] | 2
[9 empty] | d) | 247 CD | d) | 05/07/19 | [11 empty] | 2
AC
|  |  | PAMANA-DILG CY 2016 | [20 empty] | AC
|  |  |  | Construction of Civic Center, San Isidro, |  | Bldg. | - | Admin | a) | 2,000,000.00 | a) | CY 2016 | e) | 40 CD | a) | 2,000,000.00 | a) | 100.00% | c) | 100.00% | a) | 8 | Completed as per physical accomplishment. | 1
|  |  |  | Tagum City |  |  |  |  | b) | Escurzon | b) | 7/5/2018 | f) | - | b) | 2,000,000.00 | b) | - | d) | - | b) | 240 | Financial documents still on process | 1
[9 empty] | c) | MAG Carp. | c) | 12/06/18 | g) | 01/15/19 | c) | - | [7 empty] | 1
[9 empty] | d) | 155 CD | d) | 01/15/19 | [11 empty] | 1
|  | A. | OPPAP-PAMANA | [20 empty] | AC
|  |  | Construction of Processing and Bagsakan Center |  |  | Bldg. | 300 sq.m | Contract | a) | 2500000 | a) | 08/15/18 | e) | - | a) | 2500000 | a) | 100.00% | c) | 100% | a) | 6 | Completed as per physical accomplishment. | 1
|  |  | Brgy. Palma Gil, Talaingod | [5 empty] | b) | Dadula | b) | 02/02/19 | f) | 35 CD | b) | 2500000 | b) |  | d) |  | b) | 180 | Financial documents still on process | 1
[9 empty] | c) | Alpha & Omega | c) | 05/12/19 | g) | 07/19/2019 | c) | [8 empty] | 1
[9 empty] | d) | 100 CD | d) | - | [11 empty] | 1
|  | B. | 20% Development Fund CY 2015 | [20 empty] | AC
|  |  | Improvement of Potable Water System Level II, |  |  | Water |  | Admin | a) | 1,125,000.00 | a) | 08/31/17 | e) | 222 CD | a) | 1,125,000.00 | a) | 100.00% | c) | 100% | a) | 4 | Completed 7/2/2019 as per physical accomplishment. Financial Documents still on process | 2
|  |  | Toril, IGCS |  |  | System |  |  | b) | Porras | b) | 02/19/18 | f) | 83 CD | b) | 1,125,000.00 | b) | - | d) | 0% | b) | 12 |  | 2
[9 empty] | c) | PEO | c) | 06/29/18 | g) | 7/2/2019 | c) | 1,009,555.97 | [7 empty] | 2
[9 empty] | d) |  | d) | 04/30/19 | [11 empty] | 2
|  | C. | 20% Development Fund CY 2016 | [20 empty] | AC
|  |  | 1. Water System Development Projects | [20 empty] | AC
|  | (Provincewide) | [21 empty] | AC
|  |  |  | Improvement of Potable Water System Level II, |  | Water |  | Admin | a) | 525,000.00 | a) | 08/31/17 | e) | 222 CD | a) | 525,000.00 | a) | 100% | c) | 100% | a) | 4 | Completed 7/2/2019 as per physical accomplishment. Financial Documents still on process | 2
|  |  |  | Toril, IGCS |  | System |  |  | b) | Porras | b) | 02/19/18 | f) | 83 CD | b) | 525,000.00 | b) | - | d) | 0% | b) | 12 |  | 2
[9 empty] | c) | PEO | c) | 06/29/18 | g) | 7/2/2019 | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | 04/30/19 | [11 empty] | 2
|  |  | 3. Const./Rehab./Comp. of Various Gov't. Bldgs. |  |  | Bldgs./ | - | Admin | a) | 9,000,000.00 | [13 empty] | AC
|  |  | Struct., Fac. (Provincewide) |  |  | Fence |  |  | b) | Foronda/Ababon | [13 empty] | AC
[9 empty] | c) | PEO | [13 empty] | AC
|  |  |  | Const./Impv't./Renov. Of DAVNOR Pharmacy |  | Bldg. |  | Admin | a) | 500,000.00 | a) | 08/10/18 | e) | 92 | a) | 500,000.00 | a) | 100% | c) | 100% | a) | 45 | Completed 6/28/2019 as per physical accomplishment. Financial documents still on process | 2
|  |  |  | Building, DDNH-CZ Compound |  |  |  |  | b) | Estorco | b) | 01/14/19 | f) | - | b) | 500,000.00 | b) | 100% | d) | 0% | b) | 3 |  | 2
|  |  |  | (Carmen District Hospital) |  |  |  |  | c) | Admin | c) | 03/26/19 | g) | 06/28/2019 | c) | 415,227.26 | [7 empty] | 2
[11 empty] | d) | 2019-06-28 | [11 empty] | 2
|  |  | SLRF 2015 | [7 empty] | a) |  | e) | 65 days | a) |  | a) | 100% | c) | 100% | a) | 3 | Completed as per POW, Financial Documents on Process | AC
|  |  | Rehab. of Jct. Highway-Tuganay-Anibongan-BE Dujali-Kinamayan Provincial Road (Furtheranace) |  |  | Slope protection | - | - | a) | 1911175.99 | b) | 2019-02-18 | f) | 47 days | b) |  | b) |  | d) | 0% | b) | 60 |  | 2
[9 empty] | b) | Balbastro | c) | 2019-09-21 | g) | 9/21/2019 | c) | [8 empty] | 2
[9 empty] | c) | Admin | d) | [12 empty] | 2
[9 empty] | d) | - | [13 empty] | 2
|  |  | TRUST FUND 2017 | [20 empty] | AC
|  |  | Conditional Matching Grant to Provinces (CMGP) | [20 empty] | AC
|  |  |  | Road Upgrading of FDR. Rd.3 – |  | Conc. | 10.359 km | Contract. | a) | 119901954.82 | a) | CY 2017 | e) | 47 CD | a) | 119901954.82 | a) | 100.00% | c) | 100% | a) | 10 | Completed based on POW, Financial Documents on Process | 2
|  |  |  | Kimamon – Luna Provincial Road, |  |  |  |  | b) | Comidoy | a) | 12/29/17 | f) | 198 CD | b) | 119901954.82 | b) | 100% | d) | 100% | b) | 220 |  | 2
|  |  |  | Sto. Tomas |  |  |  |  | c) | GP & H CONST. | c) | 12/12/18 | g) | - | c) | 119901954.82 | [7 empty] | 2
[9 empty] | d) | 326 CD | d) | 2019-07-29 | [11 empty] | 2
|  |  |  | Road Upgrading of Anahaw-Maligaya |  | Conc. | 5.18 km | Contract. | a) | 78,228,121.56 | a) | CY 2017 | e) | - | a) | 78,228,121.56 | a) | 100.00% | c) | 100% | a) | 30 | Completed based on POW, Financial Documents on Process | 2
|  |  |  | Provincial Road, Carmen |  |  |  |  | b) | Fernandez | b) | 12/24/17 | f) | 306 CD | b) | 78,228,121.56 | b) | 100% | d) | 0% | b) | 660 |  | 2
[9 empty] | c) | MONOLITHIC CONST. | c) | 03/31/19 | g) | - | c) | 76,214,361.38 | [7 empty] | 2
[9 empty] | d) | 210 CD | d) | 2019-06-05 | [11 empty] | 2
4 |  | 8 |  | Road Upgrading of Dagohoy - Daligdigon |  | Road | 2.532 km | Contract | a) | 58048310.68 | a) | CY 2017 | e) | - | a) | 58048310.68 | a) | 100.00% | c) | 100% | a) | 16 | Completed as per Physical Accomplishment, Financial Documents on Process | 1
4 |  |  |  | Provincial Road |  |  |  |  | b) | Fabiala | b) | 01/05/18 | f) | 205 CD | b) | 58048310.68 | b) | - | d) | 0% | b) | 480 |  | 1
4 | [8 empty] | c) | PUREGOLD | c) | 11/18/18 | g) | - | c) | 29,572,637.70 | [7 empty] | 1
4 | [8 empty] | d) | 246 CD | d) | 03/31/19 | [11 empty] | 1
4 |  |  |  | Impv’t. of Maligaya-New Camiling Prov’l. |  | Conc. | 2.13 km | Contract. | a) | 50101614.08 | a) | CY 2017 | e) | 76 CD | a) | 57385680 | a) | 100.00% | c) | 100% | a) | 21 | Completed based on POW. Financial Documents on process | 2
4 |  |  |  | Road w/ Bridge Component,Carmen |  |  |  |  | b) | Mellomida | b) | 12/18/17 | f) | 209 CD | b) | 57385680 | b) | 100% | d) | 0% | b) | 147 |  | 2
4 | [8 empty] | c) | PUREGOLD CONST. | c) | 02/15/19 | g) | - | c) | 36005452 | [7 empty] | 2
4 | [8 empty] | d) | 376 CD | d) | 07/31/19 | [11 empty] | 2
|  |  | OPPAP PAMANA | [20 empty] | AC
|  |  | Tribal Hall | [20 empty] | AC
|  |  |  | Construction of Tribal Hall |  | Bldg. |  | Admin | a) | 500000 | a) | CY 2018 | e) | - | a) | 500000 | a) | 100% | c) | 100% | a) | 5 | Completed as per Physical Accomplishment. Financial Documents on process | 1
|  |  |  | Brgy. Gupitan, Kapalong |  |  |  |  | b) | Ambrocio | b) | 2/22/2019 | f) | - | b) | 500000 | b) | - | d) | 0% | b) | 150 |  | 1
[9 empty] | c) | PEO | c) | 5/22/2019 | g) | - | c) | - | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | Processing and Bagsakan Center | [20 empty] | AC
|  |  |  | Const. of Processing and Bagsakan Center, |  | Bldg. | 300 sq.m | Contract | a) | 2500000 | a) | 08/29/18 | e) | - | a) | 2500000 | a) | 100% | c) | 100% | a) | 6 | Completed as per Physical Accomplishment. Financial Documents on process | 1
|  |  |  | Brgy. Gupitan, Kapalong, Davao del Norte |  |  |  |  | b) | Ambrucio | b) | 02/12/19 | f) | - | b) | 2500000 | b) | - | d) | 0% | b) | 180 |  | 1
[9 empty] | c) | Alpha & Omega | c) | 05/12/19 | g) | - | c) | 156000 | [7 empty] | 1
[9 empty] | d) | 120 CD | d) | - | [11 empty] | 1
|  |  |  | Construction of Processing and Bagsakan Center |  | Bldg. | 300 sq.m | Contract | a) | 2500000 | a) | 08/15/18 | e) | - | a) | 2500000 | a) | 100.00% | c) | 100% | a) | 6 | Completed as per physical accomplishment. | 1
|  |  |  | Brgy. Palma Gil, Talaingod |  |  |  |  | b) | Dadula | b) | 02/02/19 | f) | 35 CD | b) | 2500000 | b) |  | d) |  | b) | 180 | Financial documents still on process | 1
[9 empty] | c) | Alpha & Omega | c) | 05/12/19 | g) | 07/19/2019 | c) | [8 empty] | 1
[9 empty] | d) | 100 CD | d) | - | [11 empty] | 1
|  | D. | 20% Development Fund CY 2017 | [20 empty] | AC
|  |  | STIMULUS PROJECTS CY 2017 | [20 empty] | AC
|  |  | TAGUM CITY | [20 empty] | AC
|  |  |  | Impv't. of Magdum Barangay Hall, |  | Bldgs. |  | Admin | a) | 500000 | a) | 11/29/17 | e) | - | a) | 500000 | a) | 100.00% | c) | 100.00% | a) | 6 | Completed as per physical accomplishment. | 1
|  |  |  | Magdum, Tagum City |  |  |  |  | b) | Pasiona | b) | 04/23/18 | f) | 10 CD | b) | 500000 | b) | - | d) | - | b) | 108 | Financial documents still on process | 1
[9 empty] | c) | PEO | c) | 06/11/18 | g) | 06/21/18 | c) | 484028 | [7 empty] | 1
[9 empty] | d) | 50 CD | d) | 06/21/18 | [11 empty] | 1
|  |  |  | Const. Stage, Canocotan, Tagum City |  | Bldgs. |  | Contract | a) | 500000 | a) | 12/28/17 | e) | - | a) | 500000 | a) | 100.00% | c) | 100.00% | a) | 7 | Completed as per physical accomplishment. | 1
[9 empty] | b) | Escurzon | b) | 06/01/18 | f) | - | b) | 500000 | b) | - | d) | - | b) | 140 | Financial documents still on process | 1
[9 empty] | c) | FT Construction | c) | 07/15/18 | g) | 08/22/18 | c) | 457128.95 | [7 empty] | 1
[9 empty] | d) | 45 CD | d) | - | [11 empty] | 1
|  |  |  | Construction of Bleachers and Firewall |  | Bldgs. |  | Contract | a) | 500000 | a) | 06/05/18 | e) | - | a) | 500000 | a) | 100.00% | c) | 100.00% | a) | 6 | Completed as per physical accomplishment. | 1
|  |  |  | for the GYM, Magugpo West, Tagum City |  |  |  |  | b) | Medalla | b) | 09/13/18 | f) | - | b) | 500000 | b) | - | d) | - | b) | 180 | Financial documents still on process | 1
[9 empty] | c) | RLHV | c) | 11/08/18 | g) | 11/08/18 | c) | 473595.97 | [7 empty] | 1
[9 empty] | d) | 60 CD | d) | - | [11 empty] | 1
|  |  |  | Const. of 1 Bay Span Covered Court, |  | Court | 96 sq.m | Contract | a) | 500000 | a) | 06/05/18 | e) | - | a) | 500000 | a) | 100.00% | c) | 100.00% | a) | 5 | Completed as per physical accomplishment. | 1
|  |  |  | Brgy. La Filipina, Tagum City |  |  |  |  | b) | Medalla | b) | 12/10/18 | f) | - | b) | 500000 | b) | - | d) | - | b) | 150 | Financial documents still on process | 1
[9 empty] | c) | FT Const. | c) | 01/29/19 | g) | 04/12/19 | c) | - | [7 empty] | 1
[9 empty] | d) | 50 CD | d) | - | [11 empty] | 1
|  |  | SAN ISIDRO | [20 empty] | AC
|  |  |  | Rehab. Of Sawata Gymnasiun, San Isidro |  | Bldgs. |  | Contract | a) | 500000 | a) | 11/29/17 | e) | - | a) | 500000 | a) | 100.00% | c) | 100.00% | a) | 6 | Completed as per physical accomplishment. | 1
[9 empty] | b) | Escurzon | b) | 01/06/18 | f) | 15 CD | b) | 500000 | b) | - | d) | - | b) | 180 | Financial documents still on process | 1
[9 empty] | c) | FT Construction | c) | 05/07/18 | g) | 07/25/18 | c) | 474,700.57 | [7 empty] | 1
[9 empty] | d) | 35 CD | d) | 07/20/18 | [11 empty] | 1
|  |  |  | Compl. Of Pipeline Level II, Brgy. San Miguel, |  | Bldgs. |  | Contract | a) | 500000 | a) | 12/28/17 | e) | - | a) | 500000 | a) | 100.00% | c) | 100.00% | a) | 5 | Completed as per physical accomplishment. | 1
|  |  |  | San Isidro |  |  |  |  | b) | Diosanta | b) | 05/25/18 | f) | 28 CD | b) | 500000 | b) | - | d) | - | b) | 100 | Financial documents still on process | 1
[9 empty] | c) | ZULAR - AZ Const. & Supply | c) | 06/07/18 | g) | 07/25/18 | c) | 479116.61 | [7 empty] | 1
[9 empty] | d) | 24 CD | d) | 07/05/18 | [11 empty] | 1
|  |  |  | Const. of Covered Court, Datu Balong, |  | Bldgs. |  | Contract | a) | 500000 | a) | 11/29/17 | e) | - | a) | 500000 | a) | 100.00% | c) | 100.00% | a) | 5 | Completed as per physical accomplishment. | 1
|  |  |  | San Isidro |  |  |  |  | b) | Escurzon | b) | 01/06/18 | f) | - | b) | 500000 | b) | - | d) | - | b) | 90 | Financial documents still on process | 1
[9 empty] | c) | FT Construction | c) | 07/10/18 | g) | 08/31/18 | c) | 472019.86 | [7 empty] | 1
[9 empty] | d) | 40 CD | d) | - | [11 empty] | 1
|  |  |  | Const. of Brgy. Stage, Linao, San Isidro |  | Bldgs. |  | Contract | a) | 500000 | a) | 11/29/17 | e) | - | a) | 500000 | a) | 100.00% | c) | 100.00% | a) | 12 | Completed as per physical accomplishment. | 1
[9 empty] | b) | Escurzon | b) | 01/06/18 | f) | 15 CD | b) | 500000 | b) | - | d) | - | b) | 216 | Financial documents still on process | 1
[9 empty] | c) | FT Construction | c) | 05/07/18 | g) | 09/03/18 | c) | 465500 | [7 empty] | 1
[9 empty] | d) | 45 CD | d) | 07/15/18 | [11 empty] | 1
|  |  |  | Const. of Potable Water System, Monte |  | Bldgs. |  | Contract | a) | 500000 | a) | 12/28/17 | e) | - | a) | 500000 | a) | 100.00% | c) | 100.00% | a) | 6 | Completed as per physical accomplishment. | 1
|  |  |  | Dujali, San Isidro |  |  |  |  | b) | Escurzon | b) | 01/06/18 | f) | 20 CD | b) | 500000 | b) | - | d) | - | b) | 180 | Financial documents still on process | 1
[9 empty] | c) | FT Construction | c) | 07/30/18 | g) | 09/07/18 | c) | 470612.51 | [7 empty] | 1
[9 empty] | d) | 60 CD | d) | 08/25/18 | [11 empty] | 1
|  |  |  | Const. of Covered Court , Libuton, San Isidro |  | Bldgs. |  | Contract | a) | 500000 | a) | 11/29/17 | e) | - | a) | 500000 | a) | 100.00% | c) | 100.00% | a) | 6 | Completed as per physical accomplishment. | 1
[9 empty] | b) | Escurzon | b) | 01/06/18 | f) | - | b) | 500000 | b) | - | d) | - | b) | 180 | Financial documents still on process | 1
[9 empty] | c) | FT Construction | c) | 07/15/18 | g) | 08/22/18 | c) | 476716.56 | [7 empty] | 1
[9 empty] | d) | 45 CD | d) | - | [11 empty] | 1
|  |  |  | Improvement of Barangay Hall Perimeter |  | Bldgs. |  | Contract | a) | 500000 | a) | 11/29/17 | e) | - | a) | 500000 | a) | 100.00% | c) | 100.00% | a) | 6 | Completed as per physical accomplishment. | 1
|  |  |  | Fence, Brgy. Dakudao, San Isidro |  |  |  |  | b) | Escurzon | b) | 06/01/18 | f) | 26 CD | b) | 500000 | b) | - | d) | - | b) | 180 | Financial documents still on process | 1
[9 empty] | c) | FT Const. | c) | 07/30/18 | g) | 09/04/18 | c) | '468,532.48 | [7 empty] | 1
[9 empty] | d) | 60 CD | d) | 08/25/18 | [11 empty] | 1
|  |  | ASUNCION | [20 empty] | AC
|  |  |  | Completion of Magatos E/S Perimeter |  | Bldgs. |  | MEO | a) | 500000 | a) | 12/28/17 | e) | - | a) | 500000 | a) | 100.00% | c) | 100.00% | a) | 19 | Completed as per physical accomplishment | 1
|  |  |  | Fence, Asuncion |  |  |  |  | b) | Inquillon | b) | 06/01/18 | f) | - | b) | 500000 | b) | - | d) | - | b) | 426 | - Fund transferred at Municipality of Asuncion | 1
[9 empty] | c) | MEO | c) | 07/30/17 | g) | 07/30/17 | c) | 500000 | [6 empty] | with ChecK No. 2445178 and OR # 9238462, | 1
[9 empty] | d) | - | d) | - | [10 empty] | dated March 16, 2018 | 1
|  |  |  | Const. of Covered Court Ph.1, Camansa, |  | Bldgs. |  | MEO | a) | 500000 | a) | 12/19/17 | e) | - | a) | 500000 | a) | 100.00% | c) | 100.00% | a) | 15 | Completed as per physical accomplishment. | 1
|  |  |  | Asuncion |  |  |  |  | b) | Inquillon | b) | 05/16/18 | f) | - | b) | 500000 | b) | - | d) | - | b) | 399 | - Fund transferred at Municipality of Asuncion | 1
[9 empty] | c) | MEO | c) | 09/15/18 | g) | 07/15/18 | c) | 500000 | [6 empty] | with ChecK No. 2445090 and OR # 8975230, | 1
[9 empty] | d) | - | d) | - | [10 empty] | dated February 5, 2018 | 1
|  |  |  | FMR 0.5km at Brgy. Site, Sonlon, |  | Bldgs. |  | MEO | a) | 500000 | a) | 12/28/17 | e) | - | a) | 500000 | a) | 100.00% | c) | 100.00% | a) | 12 | Completed as per physical accomplishment. (Fund already transferred at Municipality of Asuncion with ChecK No. 2445173 and OR # 9238463, dated March 16, 2018) | 1
|  |  |  | Asuncion |  |  |  |  | b) | Inquillon | b) | 2018-06-18 | f) | - | b) | 500000 | b) | - | d) | - | b) | 156 |  | 1
[9 empty] | c) | MEO | c) | 08/15/18 | g) | 08/10/18 | c) | 500000 | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  |  | Const. of Covered Court Ph. 1, Sta. |  | Bldgs. |  | MEO | a) | 500000 | a) | 12/28/17 | e) | - | a) | 500000 | a) | 100.00% | c) | 100.00% | a) | 13 | Completed as per physical accomplishment | 1
|  |  |  | Felomina, Asuncion |  |  |  |  | b) | Inquillon | b) | 06/18/18 | f) | - | b) | 500000 | b) | - | d) | - | b) | 426 | - Fund transferred at Municipality of Asuncion | 1
[9 empty] | c) | MEO | c) | 08/15/18 | g) | 08/05/18 | c) | 500000 | [6 empty] | with ChecK No. 2445177 and OR # 9238464, | 1
[9 empty] | d) | - | d) | - | [10 empty] | dated March 16, 2018 | 1
|  |  |  | Impv't. of Brgy. Facilities, Buclad, Asuncion |  | Bldgs. |  | MEO | a) | 500000 | a) | 12/19/17 | e) | - | a) | 500000 | a) | 100.00% | c) | 100.00% | a) | 12 | Completed as per physical accomplishment. (Fund already transferred at Municipality of Asuncion with ChecK No. 2445032 and OR # 8975234, dated February 5, 2018) | 1
[9 empty] | b) | Inquillon | b) | 04/30/18 | f) | - | b) | 500000 | b) | - | d) | - | b) | 364 |  | 1
[9 empty] | c) | MEO | c) | 07/30/18 | g) | 2018-06-30 | c) | 500000 | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  |  | Impv't. of Brgy. Hall, Cabaywa, Asuncion |  | Bldgs. |  | MEO | a) | 500000 | a) | 12/19/17 | e) | - | a) | 500000 | a) | 100.00% | c) | 100.00% | a) | 11 | Completed as per physical accomplishment. | 1
[9 empty] | b) | Inquillon | b) | 05/18/18 | f) | - | b) | 500000 | b) | - | d) | - | b) | 358 | - Fund transferred at Municipality of Asuncion | 1
[9 empty] | c) | MEO | c) | 08/16/18 | g) | 07/02/18 | c) | - | [6 empty] | with ChecK No. 2445031 and OR # 8975233, | 1
[9 empty] | d) | - | d) | - | [10 empty] | dated February 5, 2018 | 1
|  |  |  | Impv't. of Multi-Purpose Bldg., Napungas |  | Bldgs. |  | MEO | a) | 500000 | a) | 12/28/17 | e) | - | a) | 500000 | a) | 100.00% | c) | 100.00% | a) | 14 | Completed as per physical accomplishment. (Fund already transferred at Municipality of Asuncion with ChecK No. 2445147 and OR # 8975232, dated February 5, 2018) | 1
|  |  |  | Asuncion |  |  |  |  | b) | Inquillon | b) | 06/16/18 | f) | - | b) | 500000 | b) | - | d) | - | b) | 207 |  | 1
[9 empty] | c) | MEO | c) | 07/30/18 | g) | 07/30/18 | c) | 500000 | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  |  | Construction of Multi-Purpose Stage, |  | Bldgs. |  | MEO | a) | 500000 | a) | 12/19/17 | e) | - | a) | 500000 | a) | 100.00% | c) | 100.00% | a) | 18 | Completed as per physical accomplishment. (Fund already transferred at Municipality of Asuncion with ChecK No. 2445030 and OR # 8975231, dated February 5, 2018 (Compl: Aug. 16, 2018) | 1
|  |  |  | Binancian, Asuncion |  |  |  |  | b) | Inquillo | b) | 05/18/18 | f) | - | b) | 500000 | b) | - | d) | - | b) | 396 |  | 1
[9 empty] | c) | MEO | c) | 08/16/18 | g) | 08/16/18 | c) | 500000 | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  |  | Construction of Covered Court Ph. 1, |  | Bldgs. |  | MEO | a) | 500000 | a) | 02/06/18 | e) | - | a) | 500000 | a) | 100.00% | c) | 100.00% | a) | 14 | Completed as per physical accomplishment | 1
|  |  |  | Buan, Asuncion |  |  |  |  | b) | Inquillo | b) | 06/01/18 | f) | - | b) | 500000 | b) | - | d) | - | b) | 430 | - Fund transferred at Municipality of Asuncion | 1
[9 empty] | c) | MEO | c) | 08/30/18 | g) | 07/30/18 | c) | 500000 | [6 empty] | with ChecK No. 2445282 and OR # 9238466, | 1
[9 empty] | d) | - | d) | - | [10 empty] | dated March 16, 2018. | 1
|  |  |  | Construction of Nutrition Bldg. Ph. 1, |  | Bldgs. |  | MEO | a) | 500000 | a) | 12/20/17 | e) | - | a) | 500000 | a) | 100.00% | c) | 100.00% | a) | 9 | Completed as per physical accomplishment | 1
|  |  |  | Cambanogoy, Asuncion |  |  |  |  | b) | Inquillo | b) | 07/16/18 | f) | - | b) | 500000 | b) | - | d) | - | b) | 135 | - Fund transferred at Municipality of Asuncion with | 1
[9 empty] | c) | MEO | c) | 08/14/18 | g) | 11/15/18 | c) | 500000 | [6 empty] | ChecK No. 24465176 and OR # 9238465, | 1
[9 empty] | d) | - | d) | - | [10 empty] | dated March 16, 2018 | 1
|  |  |  | Rehab. Of 2 Inches Pipelines of Water System |  | Bldgs. |  | MEO | a) | 500000 | a) | 12/28/17 | e) | - | a) | 500000 | a) | 100.00% | c) | 100.00% | a) | 12 | Completed as per physical accomplishment | 1
|  |  |  | at Prk. 1, New Loon, Asuncion |  |  |  |  | b) | Inquillo | b) | 08/05/18 | f) | - | b) | 500000 | b) | - | d) | - | b) | 180 | -Fund transferred at Municipality of Asuncion with | 1
[9 empty] | c) | MEO | c) | 11/15/18 | g) | 11/15/18 | c) | 500000 | [6 empty] | ChecK No. 2445175 and OR # 9238467, | 1
[9 empty] | d) | - | d) | - | [10 empty] | dated March 16, 2018 | 1
|  |  | NEW CORELLA | [20 empty] | 1
|  |  |  | Fabrication of Bleachers, New Cortez, |  | Bldgs. |  | MEO | a) | 500000 | a) | 12/28/17 | e) | - | a) | 500000 | a) | 100.00% | c) | 100.00% | a) | - | Completed as per physical accomplishment. (Fund already transferred at Municipality of New Corella with ChecK No. 2445146 and OR # 8592069, dated March 13, 2018) | 1
|  |  |  | New Corella |  |  |  |  | b) | Inquillo & Dogoldogol | b) | 06/15/18 | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 1
[9 empty] | c) | MEO | c) | 07/31/18 | g) | 07/31/18 | c) | 500000 | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  |  | Renov./Impv't. Of Brgy. Hall, New Sambog, |  | Bldgs. |  | MEO | a) | 500000 | a) | 12/19/17 | e) | - | a) | 500000 | a) | 100.00% | c) | 100.00% | a) | - | Completed as per physical accomplishment. (Fund already transferred at Municipality of New Corella with ChecK No. 2445023 and OR # 8592070, dated March 13, 2018) | 1
|  |  |  | New Corella |  |  |  |  | b) | - | b) | 07/01/18 | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 1
[9 empty] | c) | MEO | c) | 08/15/18 | g) | 08/15/18 | c) | - | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  |  | Rehab. Of Potable Water in Prk. 2,3,3A, |  | Bldgs. |  | MEO | a) | 500000 | a) | 02/19/18 | e) | - | a) | 500000 | a) | 100.00% | c) | 100.00% | a) | - | Completed as per physical accomplishment.Fund already transferred at Municipality of New Corella with ChecK No. 2445320 and OR # 8592073, dated March 13, 2018 | 1
|  |  |  | 3B & 6, Macgum, New Corella |  |  |  |  | b) | - | b) | 08/15/18 | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 1
[9 empty] | c) | MEO | c) | - | g) | 11/19/18 | c) | 500000 | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  |  | Renov./Impv't. of Brgy. Hall, Patrocenio, |  | Bldgs. |  | MEO | a) | 500000 | a) | 12/20/17 | e) | - | a) | 500000 | a) | 100.00% | c) | 100.00% | a) | - | Completed as per physical accomplishment | 1
|  |  |  | New Corella |  |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - | - Fund transferred at Municipality of New Corella | 1
[9 empty] | c) | MEO | c) | - | g) | 11/19/18 | c) | 500000 | [6 empty] | with ChecK No. 2445022 and OR # 8592071, | 1
[9 empty] | d) |  | d) | - | [10 empty] | dated March 13, 2018 | 1
|  |  |  | Impv't. of Covered Court, New Bohol, |  | Bldgs. |  | Barangay | a) | 500000 | a) | 02/13/8 | e) | - | a) | 500000 | a) | 100.00% | c) | 100.00% | a) | - | Completed as per physical accomplishment.Fund already transferred at Municipality of New Corella with ChecK No. 2445321 and OR # 8592075, dated March 13, 2018 | 1
|  |  |  | New Corella |  |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 1
[9 empty] | c) | - | c) | - | g) | 08/15/18 | c) | 500000 | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  |  | Construction of Multi-Purpose Bldg., |  | Bldgs. |  | MEO | a) | 500000 | a) | 02/06/18 | e) | - | a) | 500000 | a) | 100.00% | c) | 100.00% | a) | - | Completed as per physical accomplishment.Fund already transferred at Municipality of New Corella ChecK No. 2445281 with and OR # 8592076, dated March 13, 2018 | 1
|  |  |  | San Jose, New Corella |  |  |  |  | b) | - | b) | 08/05/18 | f) | - | b) | 500000 | b) |  | d) | - | b) | - |  | 1
[9 empty] | c) | MEO | c) | 02/28/19 | g) | 02/28/19 | c) | 500000 | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  |  | Construction of 1 CL School Bldg., |  | Bldg. |  | Barangay | a) | 500000 | a) | 12/28/17 | e) | - | a) | 500000 | a) | 100.00% | c) | 100.00% | a) | - | Completed as per physical accomplishment.Fund already transferred at Municipality of New Corella with ChecK No. 2445183 and OR # 8592077, dated March 13, 2018 | 1
|  |  |  | Mambing, New Corella |  |  |  |  | b) | - | b) | 2018-01-06 | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 1
[9 empty] | c) | MEO | c) | 7/15/2018 | g) | 7/15/2018 | c) | - | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | SAN ISIDRO | [20 empty] | AC
|  |  |  | Rehab. Of Sawata Gymnasiun, San Isidro |  | Bldgs. |  | Contract | a) | 500000 | a) | 11/29/17 | e) | - | a) | 500000 | a) | 100.00% | c) | 100.00% | a) | - | Completed as per physical accomplishment. | 1
[9 empty] | b) | Escurzon | b) | 01/06/18 | f) | 15 CD | b) | 500000 | b) | - | d) | - | b) | - | Financial documents still on process | 1
[9 empty] | c) | FT Construction | c) | 05/07/18 | g) | 07/25/18 | c) | 474,700.57 | [7 empty] | 1
[9 empty] | d) | 35 CD | d) | 07/20/18 | [11 empty] | 1
|  |  |  | Compl. Of Pipeline Level II, Brgy. San Miguel, |  | Water |  | Contract | a) | 500000 | a) | 12/28/17 | e) | - | a) | 500000 | a) | 100.00% | c) | 100.00% | a) | 5 | Completed as per physical accomplishment. | 1
|  |  |  | San Isidro |  |  |  |  | b) | Diosanta | b) | 05/25/18 | f) | 28 CD | b) | 500000 | b) | - | d) | - | b) | 100 | Financial documents still on process | 1
[9 empty] | c) | ZULAR - AZ Const. & Supply | c) | 06/07/18 | g) | 07/25/18 | c) | 478500 | [7 empty] | 1
[9 empty] | d) | 24 CD | d) | 07/05/18 | [11 empty] | 1
|  |  |  | Const. of Covered Court, Datu Balong, |  | Bldgs. |  | Contract | a) | 500000 | a) | 11/29/17 | e) | - | a) | 500000 | a) | 100.00% | c) | 100.00% | a) | 5 | Completed as per physical accomplishment. | 1
|  |  |  | San Isidro |  |  |  |  | b) | Escurzon | b) | 01/06/18 | f) | - | b) | 500000 | b) | - | d) | - | b) | 90 | Financial documents still on process | 1
[9 empty] | c) | FT Construction | c) | 07/10/18 | g) | 08/31/18 | c) | 472019.86 | [7 empty] | 1
[9 empty] | d) | 40 CD | d) | - | [11 empty] | 1
|  |  |  | Const. of Brgy. Stage, Linao, San Isidro |  | Bldgs. |  | Contract | a) | 500000 | a) | 11/29/17 | e) | - | a) | 500000 | a) | 100.00% | c) | 100.00% | a) | 12 | Completed as per physical accomplishment. | 1
[9 empty] | b) | Escurzon | b) | 01/06/18 | f) | 15 CD | b) | 500000 | b) | - | d) | - | b) | 216 | Financial documents still on process | 1
[9 empty] | c) | FT Construction | c) | 05/07/18 | g) | 09/03/18 | c) | 495500 | [7 empty] | 1
[9 empty] | d) | 45 CD | d) | 07/15/18 | [11 empty] | 1
|  |  |  | Const. of Potable Water System, Monte |  | Water |  | Contract | a) | 500000 | a) | 12/28/17 | e) | - | a) | 500000 | a) | 100.00% | c) | 100.00% | a) | 6 | Completed as per physical accomplishment. | 1
|  |  |  | Dujali, San Isidro |  |  |  |  | b) | Escurzon | b) | 01/06/18 | f) | 20 CD | b) | 500000 | b) | - | d) | - | b) | 180 | Financial documents still on process | 1
[9 empty] | c) | FT Construction | c) | 07/30/18 | g) | 09/07/18 | c) | 472977.4 | [7 empty] | 1
[9 empty] | d) | 60 CD | d) | 08/25/18 | [11 empty] | 1
|  |  |  | Const. of Covered Court , Libuton, San Isidro |  | bldgs. |  | Contract | a) | 500000 | a) | 11/29/17 | e) | - | a) | 500000 | a) | 100.00% | c) | 100.00% | a) | 6 | Completed as per physical accomplishment. | 1
[9 empty] | b) | Escurzon | b) | 01/06/18 | f) | - | b) | 500000 | b) | - | d) | - | b) | 180 | Financial documents still on process | 1
[9 empty] | c) | FT Construction | c) | 07/15/18 | g) | 08/22/18 | c) | 476716.56 | [7 empty] | 1
[9 empty] | d) | 45 CD | d) | - | [11 empty] | 1
|  |  |  | Improvement of Barangay Hall Perimeter |  | Fence |  | Contract | a) | 500000 | a) | 11/29/17 | e) | - | a) | 500000 | a) | 100.00% | c) | 100.00% | a) | 6 | Completed as per physical accomplishment. | 1
|  |  |  | Fence, Brgy. Dakudao, San Isidro |  |  |  |  | b) | Escurzon | b) | 01/06/18 | f) | - | b) | 500000 | b) | - | d) | - | b) | 180 | Financial documents still on process | 1
[9 empty] | c) | FT Construction | c) | 07/30/18 | g) | 08/25/18 | c) | 468532.48 | [7 empty] | 1
[9 empty] | d) | 60 CD | d) | 08/25/18 | [11 empty] | 1
1
|  |  |  | Completion of Multi-Purpose Building |  | Bldg. |  | Contract | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | 100.00% | c) | 100.00% | a) | 6 | Completed as per physical accomplishment. | 1
|  |  |  | Kipalili, San isidro |  |  |  |  | b) | Obero | b) | 12/03/18 | f) | - | b) | 500000 | b) | - | d) | - | b) | 180 | Financial documents still on process | 1
[9 empty] | c) | RLHV | c) | 01/05/19 | g) | 08/22/18 | c) | 459201 | [7 empty] | 1
[9 empty] | d) | 30 CD | d) | - | [11 empty] | 1
|  |  | IGACOS | [20 empty] | AC
|  |  |  | Rehab. of Water System, Sion, IGACOS |  | Water |  | Admin | a) | 500000 | a) | 12/01/17 | e) | - | a) | 500000 | a) | 100.00% | c) | 100.00% | a) | - | Completed as per physical accomplishment. | 2
[6 empty] | System |  |  | b) | Diosanta | b) | 08/24/18 | f) | - | b) | 500000 | b) | - | d) | - | b) | - | Financial documents still on process | 2
[9 empty] | c) | PEO | c) | 09/28/18 | g) | 09/28/18 | c) | 425,192.30 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  |  | Impvt. of MP Gym, San Agustin, IGACOS |  | Bldgs. |  | Contract | a) | 500000 | a) | 12/01/17 | d) | - | a) | 500000 | a) | 100% | c) | 100% | a) | - | Completed as per physical accomplishment. | 2
[9 empty] | b) | Porras | b) | 2018-04-26 | e) | - | b) | 500000 | b) | - | d) | - | b) | - | Financial documents still on process | 2
[9 empty] | c) | SILJURE | c) | 2018-06-06 | f) | 06/01/18 | c) | 443364.85 | [7 empty] | 2
[9 empty] | d) | 42 CD | d) | - | [11 empty] | 2
|  |  |  | Conc. of Brgy. Road, Camudmud, IGACOS |  | Road |  | Contract | a) | 500000 | a) | 11/29/17 | d) | - | a) | 500000 | a) | 100% | c) | 100% | a) | 5 | Completed as per physical accomplishment. | 2
[9 empty] | b) | Pacquio | b) | 2018-04-26 | e) | 16 days | b) | 500000 | b) | - | d) | - | b) | 30 | Financial documents still on process | 2
[9 empty] | c) | SILJURE | c) | 2018-06-11 | f) | 2018-06-11 | c) | 467128.2 | [7 empty] | 2
[9 empty] | d) | 30 CD | d) | - | [11 empty] | 2
|  |  |  | Impvt of Evacuation Center, |  | Bldg. |  | Admin | a) | 500000 | a) | 12/01/17 | e) | - | a) | 500000 | a) | 100.00% | c) | 100.00% | a) | 8 | Completed as per physical accomplishment. | 2
|  |  |  | Brgy. Balet, IGACOS |  |  |  |  | b) | Porras | b) | 05/01/19 | f) | - | b) | 500000 | b) | - | d) | - | b) | 160 | Financial documents still on process | 2
[9 empty] | c) | PEO | c) | 06/12/19 | g) | 06/06/19 | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | CARMEN | [20 empty] | AC
2
|  |  |  | Compl. Of Evacuation Ctr. Bldg. Taba, Carmen |  | Bldg. |  | Barangay | a) | 500000 | a) | 12/19/17 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Completed 9/19/2018 as per physical accomplishment. Financial documents still on process | 2
[9 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 2
[9 empty] | c) | - | c) | - | g) | 9/19/2018 | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  |  | Const. of Multi-Purpose Stage @ Prk. 2, |  | Bldg. |  | Barangay | a) | 500000 | a) | 12/19/17 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Completed as per physical accomplishment. Financial documents still on process | 2
|  |  |  | Salvacion, Carmen |  |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 2
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  |  | Const. of Multi-Purpose Bldg., |  | Bldg. |  | Barangay | a) | 500000 | a) | 12/28/17 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Completed 9/19/2018 as per physical accomplishment. Financial documents still on process | 2
|  |  |  | Magsaysay, Carmen |  |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 2
[9 empty] | c) | - | c) | - | g) | 9/19/2018 | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  |  | Compl. Of Covered Court/Stage, |  | Court |  | Barangay | a) | 500000 | a) | 12/28/17 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Completed 9/19/2018 as per physical accomplishment. Financial documents still on process | 2
|  |  |  | New Camiling, Carmen |  |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 2
[9 empty] | c) | - | c) | - | g) | 9/19/2018 | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
4 |  |  |  | Construction of Evaluation Center at Prk. 1, |  | Bldg. |  | Barangay | a) | 500000 | a) | 12/28/17 | e) | - | a) | 500000 | a) | - | c) | 100% | a) | - | Completed | 2
4 |  |  |  | Asuncion, Carmen |  |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 2
4 | [8 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 2
4 | [8 empty] | d) | - | d) | - | [11 empty] | 2
AC
|  |  | PANABO CITY | [20 empty] | AC
2
|  |  |  | Brgy. Covered Court Fencing, Sta. Cruz, |  | Court |  | Barangay | a) | 500000 | a) | 12/28/17 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Completed 6/10/2019 as per physical accomplishment. Financial documents still on process | 2
|  |  |  | Panabo CIty |  |  |  |  | b) | - | b) | 5/15/2019 | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 2
[9 empty] | c) | - | c) | 6/10/2019 | g) | - | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  |  | Const. of Multi-Purpose Bldg., Katualan, |  | Bldg. |  | Barangay | a) | 500000 | a) | 12/19/17 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Completed 10/12/2018 as per physical accomplishment. Financial documents still on process | 2
|  |  |  | Panabo CIty |  |  |  |  | b) | - | b) | 9/20/2018 | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 2
[9 empty] | c) | - | c) | 10/12/2018 | g) | - | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  |  | Const. of Covered Court Bleacher, Katipunan, |  | Bleacher |  | Barangay | a) | 500000 | a) | 12/19/17 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Completed as per physical accomplishment. Financial documents still on process | 2
|  |  |  | Panabo CIty |  |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 2
[9 empty] | c) | - | c) | - | g) | 6/10/2018 | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  |  | Const. of Brgy. Gymnasium, Mabunao, |  | Gym |  | Barangay | a) | 500000 | a) | 12/28/17 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Completed as per physical accomplishment. Financial documents still on process | 2
|  |  |  | Panabo CIty |  |  |  |  | b) | - | b) | 3/11/2019 | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 2
[9 empty] | c) | - | c) | 4/10/2019 | g) | 4/10/2019 | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
2
2
|  |  |  | Completion of Footbridge at Prk. 1, Tibungol, |  | Footbridge |  | Barangay | a) | 500000 | a) | 12/28/17 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Completed as per physical accomplishment. Financial documents still on process | 2
|  |  |  | Panabo CIty |  |  |  |  | b) | - | b) | 12/13/2018 | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 2
[9 empty] | c) | - | c) | 2/11/2019 | g) | 2/11/2019 | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  |  | Const. of Multi-Purpose Bldg., Lower Panaga, |  | Bldg. |  | Barangay | a) | 500000 | a) | 12/07/17 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Completed as per physical accomplishment. Financial documents still on process | 2
|  |  |  | Panabo CIty |  |  |  |  | b) | - | b) | 10/1/2018 | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 2
[9 empty] | c) | - | c) | 11/30/2018 | g) | 11/30/2018 | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  |  | Completion of Bleachers @ Brgy. GYM, |  | Gym |  | Barangay | a) | 500000 | a) | 12/28/17 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Completed as per physical accomplishment. Financial documents still on process | 2
|  |  |  | Sindaton, Panabo City |  |  |  |  | b) | - | b) | 10/1/2018 | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 2
[9 empty] | c) | - | c) | 10/31/2018 | g) | 10/31/2018 | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  |  | Const. of Concrete Pavement, |  | Pavement |  | Barangay | a) | 500000 | a) | 12/07/17 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Completed as per physical accomplishment. Financial documents still on process | 2
|  |  |  | San Vicente, Panabo City |  |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 2
[9 empty] | c) | - | c) | - | g) | 5/15/2019 | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  |  | Const. of Stage @ Prk. 3, Tagpore, |  | Stage |  | Barangay | a) | 500000 | a) | 12/19/17 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Completed as per physical accomplishment. Financial documents still on process | 2
|  |  |  | Panabo City |  |  |  |  | b) | - | b) | 7/18/2018 | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 2
[9 empty] | c) | - | c) | 9/14/2018 | g) | 9/14/2018 | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  |  | Const. of Bleachres @ Brgy. Manay GYM, |  | Gym |  | Barangay | a) | 500000 | a) | 12/19/17 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Completed as per physical accomplishment. Financial documents still on process | 2
|  |  |  | Manay, Panabo City |  |  |  |  | b) | - | b) | 12/6/2018 | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 2
[9 empty] | c) | - | c) | 12/15/2018 | g) | 12/15/2018 | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  |  | Const. of MP Bldg. w/ Electrical installation, |  | Bldg. |  | Barangay | a) | 500000 | a) | 01/31/18 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Completed as per physical accomplishment. Financial documents still on process | 2
|  |  |  | San Roque, Panabo City |  |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 2
[9 empty] | c) | - | c) | - | g) | 06/10/2019 | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
AC
|  |  | STO TOMAS | [20 empty] | AC
|  |  |  | Const. of Violence Against Women and |  | Bldg. |  | Barangay | a) | 500000 | a) | 12/07/17 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Completed as per physical accomplishment. Financial documents still on process | 2
|  |  |  | Children Center, Tulalian |  |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 2
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | Const./Rehab./Comp. of Various Gov't. Bldgs. |  |  | Bldg. | - | Admin | a) | 9,000,000.00 | [12 empty] | Investigation/Inspection of priority projects | 2
|  |  | Struct., Fac. (Provincewide) | [5 empty] | b) | Foronda/Ababon | [13 empty] | 2
[9 empty] | c) | PEO | [13 empty] | 2
[9 empty] | d) | - | [13 empty] | 2
|  |  |  | Repair/Rehab. Of PEO Building |  | Bldg. |  | Admin | a) | 1,800,000.00 | a) | 07/31/18 | e) | - | a) | 1,800,000.00 | a) | 62.23% | c) | 100% | a) | 5 | Completed based on POW. Financial Documents on process | 1
|  |  |  | (Motorpool),Mankilam, Tagum City |  |  |  |  | b) | Chua | b) | 03/04/19 | f) | - | b) | 1,800,000.00 | b) | - | d) | 37.77% | b) | 105 |  | 1
[9 empty] | c) | PEO | c) | 08/10/19 | g) | - | c) | 1481510.07 | [7 empty] | 1
[9 empty] | d) | 160 CD | d) | - | [11 empty] | 1
|  |  |  | Construction of BSP Building Extension |  | Bldg. |  | Admin | a) | 500000 | a) | 08/21/18 | e) | 79 CD | a) | 500000 | a) | 100% | c) | 100% | a) | 6 | Completed | 1
|  |  |  | Mankilam, Tagum City |  |  |  |  | b) | Quirante | b) | 01/16/19 | f) | 15 CD | b) | 500000 | b) | - | d) | - | b) | 180 |  | 1
[9 empty] | c) | PEO | c) | 03/16/19 | g) | 06/21/19 | c) | 434,145.73 | [7 empty] | 1
[9 empty] | d) | 75 CD | d) | 03/31/19 | [11 empty] | 1
|  |  |  | Repair/Rehab. Of PEO Building |  | Bldg. | 96 sq.m | Admin | a) | 1,073,124.00 | a) | 06/11/18 | e) | - | a) | 1,073,124.00 | a) | 100.00% | c) | 100.00% | a) | 14 | Completed as per physical accomplishment. | 1
|  |  |  | (PEO Warehouse),Mankilam, |  |  |  |  | b) | Chua | b) | 12/03/18 | f) | - | b) | 1,073,124.00 | b) | - | d) | - | b) | 420 | Financial documents still on process | 1
|  |  |  | Tagum City |  |  |  |  | c) | PEO | c) | 06/15/19 | g) | 05/15/19 | c) | 1,042,097.32 | [7 empty] | 1
[9 empty] | d) | 189 CD | d) | - | [11 empty] | 1
|  |  |  | Construction of GSP Building Extension |  | Bldg. |  | Admin | a) | 500,000.00 | a) | 07/20/18 | e) | 44 cd | a) | 500,000.00 | a) | 100.00% | c) | 100.00% | a) | 8 | Completed as per physical accomplishment. | 1
|  |  |  | Mankilam, Tagum City |  |  |  |  | b) | Quirante | b) | 01/03/19 | f) | 15 CD | b) | 500,000.00 | b) | - | d) | - | b) | 240 | Financial documents still on process | 1
[9 empty] | c) | PEO | c) | 03/03/19 | g) | 05/03/19 | c) | 447,660.03 | [7 empty] | 1
[9 empty] | d) | 75 CD | d) | 03/17/19 | [11 empty] | 1
4 |  |  | 2.3 | Improvement of Garciaville Day Care |  | Bldg. |  | Admin | a) | 330,000.00 | a) | 11/06/18 | e) | - | a) | 330,000.00 | a) |  | c) | 100% | a) | 3 | Completed based on POW. Financial Documents on process | 1
4 |  | 11 |  | Center, Mankilam, Tagum City |  |  |  |  | b) | - | b) | 09/02/19 | f) | - | b) | 330,000.00 | b) | - | d) |  | b) | 90 |  | 1
4 | [8 empty] | c) | PEO | c) | 10/11/19 | g) | - | c) | - | [7 empty] | 1
4 | [8 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | Rural Electrification (Provincewide) |  |  | Elect. |  | Admin | a) | 5000000 | [12 empty] | See projects listed below | AC
[9 empty] | b) | Foronda/Misa | [13 empty] | AC
[9 empty] | c) | Admin | [13 empty] | AC
[9 empty] | d) | - | [13 empty] | AC
|  |  |  | Inst. Of distribution transformation & |  | Elect. |  | Admin | a) | 500,000.00 | a) | 06/27/18 | e) | - | a) | 500,000.00 | a) | 100.00% | c) | 100.00% | a) | - | Completed as per physical accomplishment. | 1
|  |  |  | Electrical Wirings, 10th Infantry |  |  |  |  | b) | Lu | b) | 12/17/18 | f) | 15 WD | b) | 500,000.00 | b) | - | d) | - | b) | - | Financial documents still on process | 1
|  |  |  | (Agila) Division PA, Tuburan Mawab |  |  |  |  | c) | PEO | c) | 01/15/18 | g) | 01/31/19 | c) | - | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
4 |  | F. | SDH IGCS - CONST. IN PROGRESS - BLGS. CY 2017 | [20 empty] | 2
4 |  |  | 1 | Construction Perimeter Fence Ph.II (Hospital |  | Fence |  | Admin | a) | 1,305,000.00 | a) | 11/10/17 | e) | 392 | a) | 1,305,000.00 | a) | 100% | c) | 100% | a) | 4 | Completed based on POW. Financial Documents on process | 2
4 |  |  |  | Compound) Samal District Hospital, IGCS |  |  |  |  | b) | Porras | b) | 03/12/18 | f) | 45 | b) | 1,305,000.00 | b) | - | d) | 1% | b) | 30 |  | 2
4 | [8 empty] | c) | PEO | c) | 06/19/18 | g) | - | c) | 958,597.98 | [7 empty] | 2
4 | [8 empty] | d) | - | d) | [12 empty] | 2
4 |  | C.5 | LDRRM - Trust Fund | [20 empty] | AC
4 |  | 5 | 1. Construction of Slope Protection and Concrete Pavement along Sta. Fe Mambing Road Section |  |  | Slope |  | Admin | a) | 1,853,000.00 | a) | 11/28/18 | e) |  | a) | 1,853,000.00 | a) | 100% | c) | 100% | a) | 16 | Completed based on POW. Financial Documents on process | 1
4 | [8 empty] | b) | Gone | b) | 12/03/18 | f) | 108 CD | b) | 1,853,000.00 | b) | - | d) |  | b) | 144 |  | 1
4 | [8 empty] | c) | PEO | c) | 02/28/19 | g) | 10/30/2019 | c) | 742252.72 | [7 empty] | 1
4 | [8 empty] | d) | 86 CD | d) | 06/15/2019 | [11 empty] | 1
4 |  | 1 | 3. Rehab. Of Canatan Bridge Slope Protection |  |  | Slope | 395 sq.m. | Contract | a) | 9200000 | a) | 06/20/2018 | e) | - | a) | 9200000 | a) | 100% | c) | 100% | a) | - | Completed | 1
4 |  |  | Brgy. Canatan, Asuncion | [5 empty] | b) | Aclaracion | b) | 02/11/2019 | f) | 35 CD | b) | 9200000 | b) | 100% | d) | 0% | b) | - |  | 1
4 | [8 empty] | c) | J-One Builders | c) | 04/12/2019 | g) | 05/31/2019 | c) | 7222021.59 | [7 empty] | 1
4 | [8 empty] | d) | 60 CD | d) | 05/01/2019 | [11 empty] | 1
4 |  | 5 | 5. Const. of Cabidianan Bridge Slope Protection, Brgy. Cabidianan, New Corella |  |  | Slope |  | Admin | a) | 3590000 | a) | 07/18/18 | e) | - | a) | 3590000 | a) | 100% | c) | 100% | a) | 8 | Completed based on POW. Financial Documents on process | 1
4 | [8 empty] | b) | Gone | b) | 6/17/19 | f) | - | b) | 3590000 | b) |  | d) |  | b) | 80 |  | 1
4 | [8 empty] | c) | PEO | c) | 8/20/19 | g) | - | c) | 1929823.4 | [7 empty] | 1
4 | [8 empty] | d) | 65 CD | d) | - | [11 empty] | 1
|  | D. | SEF(Special Education Fund)-SUPPLEMENTAL BUDGET # 1 CY 2017 | [20 empty] | AC
|  |  | 1. Const./Impv't./Compl. Of School Bldgs., Struc. & Fac. |  |  | Bldgs. |  | Admin | a) | 3,300,000.00 | [12 empty] | See projects listed below | AC
[9 empty] | b) | Foronda | [13 empty] | AC
[9 empty] | c) | PEO | [13 empty] | AC
[9 empty] | d) | - | [13 empty] | AC
4 |  | 8 | 1.1 | Construction of 1 unit School Building |  | Bldg. |  | Admin | a) | 1100000 | a) | 02/19/18 | e) | - | a) | 1100000 | a) | 100 | c) | 100 | a) | 6 | Completed based on POW. Financial Documents on process | 1
4 |  |  |  | Lumabag, Talaingod |  |  |  |  | b) | Dadula | b) | 03/20/19 | f) | 27 CD | b) | 1100000 | b) |  | d) |  | b) | 30 |  | 1
4 | [8 empty] | c) | PEO | c) | 05/19/19 | g) | 06/30/2019 | c) | 595230.5 | [7 empty] | 1
4 | [8 empty] | d) | 60 CD | d) | - | [11 empty] | 1
|  | E. Supplemental Budget No. 5 CY 2015 | [21 empty] | AC
|  |  | Purchased, Const & Impvt of Govt Facilities (8918) | [20 empty] | AC
|  |  | a. Const/Coml/Impvt of Various Govt. Bldgs Structures | [20 empty] | AC
|  |  | & Facilities | [20 empty] | AC
2
|  |  | Impv't. of Brgy. Hall at |  |  | Bldg. |  | Admin | a) | 500000 | a) | 03/31/17 | e) | 182 CD | a) | 500000 | a) | 100% | c) | 100% | a) | 10 | Completed 7/17/2019 as per physical accomplishment. Financial Documents still on process | 2
|  |  | Brgy. Tagpopongan, Babak Dist., IGCS | [5 empty] | b) | Andoy | b) | 09/17/18 | f) | - | b) | 500000 | b) | - | d) | 0% | b) | 55 |  | 2
[9 empty] | c) | PEO | c) | 12/25/18 | g) | 7/14/2019 | c) | 356,352.61 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | Completion of Multi-Purpose Building |  |  | Bldg. |  | Admin | a) | 500000 | a) | 03/08/16 | e) | - | a) | 500000 | a) | 100% | c) | 100% | a) | 8 | Completed 5/31/2019 as per physical accomplishment. Financial documents still on process | 2
|  |  | Brgy. San Jose, Sto. Tomas | [5 empty] | b) | Roque | b) | 02/14/17 | f) | - | b) | 500000 | b) | - | d) | - | b) | 80 |  | 2
[9 empty] | c) | PEO | c) | 04/27/17 | g) | 15/07/2019 | c) | 484,175.83 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | Completion of Covered Court 1 Bay |  |  | Court |  | Admin | a) | 500000 | a) | 03/07/16 | e) | - | a) | 500000 | a) | 100.00% | c) | 100% | a) | 8 | Completed 7/5/2019 as per physical accomplishment. Financial documents still on process | 2
|  |  | Brgy. Lunga-og, Sto. Tomas | [5 empty] | b) | Roque | b) | 02/14/17 | f) | 54 CD | b) | 500000 | b) | - | d) | - | b) | 80 |  | 2
[9 empty] | c) | PEO | c) | 06/20/17 | g) | - | c) | 473,542.40 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  | D. | LDRRM - Trust Fund 2018 | [20 empty] | AC
|  |  |  | Const. of Single Barrel 4.0m x 4.0m RCDG, Mangalcal, Carmen |  | RCDG |  | Admin | a) | 1,822,000.00 | a) | CY 2013 | e) | - | a) | 1,822,000.00 | a) | 100.00% | c) | 100.00% | a) | 12 | Completed as per physical accomplishment. | 2
|  |  | 1 | [5 empty] | b) | Foronda | b) | 11/05/18 | f) | 92 CD | b) | 1,822,000.00 | b) | - | d) | - | b) | 72 | Financial documents still on process | 2
[9 empty] | c) | PEO | c) | 2019-01-03 | g) | 04/06/19 | c) | 1,822,000.00 | [7 empty] | 2
[9 empty] | d) | 65 CD | d) | 04/06/19 | [11 empty] | 2
2
|  |  |  | Rehabilitation of Protection Dike Along Poblacion-Prk. 8, Dujali, Brgy. Tanglaw, B.E. Dujali |  | Dike |  | Admin | a) | 1,180,000.00 | a) | CY 2013 | e) | - | a) | 1,180,000.00 | a) | 100.00% | c) | 100.00% | a) | 5 | Completed as per physical accomplishment. | 2
|  |  | 2 | [5 empty] | b) | Toquero | b) | 02/15/19 | f) | - | b) | 1,180,000.00 | b) | - | d) | - | b) | 50 | Financial documents still on process | 2
[9 empty] | c) | PEO | c) | 04/02/19 | g) | - | c) | 74,338.28 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  |  | Rehab. Of New Camiling-alejal-Lower Magsaysay Provincial Road |  | RCDG |  | Admin | a) | 1,428,917.00 | a) | 08/02/18 | e) | - | a) | 1,428,917.00 | a) | 100.00% | c) | 100.00% | a) | 5 | Completed as per physical accomplishment. | 2
|  |  | 3 | [5 empty] | b) | Toquero | b) | 12/01/18 | f) | - | b) | 1,428,917.00 | b) | - | d) | - | b) | 50 | Financial documents still on process | 2
[9 empty] | c) | PEO | c) | 01/01/19 | g) | - | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
AC
|  |  | 20% Development Fund 2018 | [20 empty] | AC
[6 empty] | Road Maintenance | KM | [16 empty] | AC
| Road ID |  | Repair & Maint. Of Various Prov'l. Roads and Bridges CY 2018 |  |  |  | 525.3 | Admin | a) | 27893753 | a) | 01/01/18 | e) | - | a) | 27893753 | a) | 100.00% | c) | 100% | a) | 32 | Completed as per physical accomplishment. | AC
[8 empty] | /CBRMC | b) | Matuguinas | b) | 01/01/18 | f) | - | b) | 27893753 | b) | - | d) | - | b) | 2044 | Financial documents still on process | AC
| 11DAN | [7 empty] | c) | PEO//CBRMC | c) | 2018-12-31 | g) | 2018-12-31 | c) | 15,163,482.97 | [6 empty] | See list of Provincial Roads | AC
[9 empty] | d) | - | d) | - | [11 empty] | AC
| 11 |  | Cebulano-Mangalcal Road |  |  | Road | 4.17 | Admin | a) | 239434.4 | a) | 01/01/18 | e) | - | a) | 239434.4 | a) | 100.00% | c) | 100% | a) | 10 | Completed as per physical accomplishment. | 2
| DAN | [7 empty] | b) | Gamad/Maligro | b) | 01/08/18 | f) | - | b) | 239434.4 | b) | - | d) | - | b) | 30 | Financial documents still on process | 2
| 073 | [7 empty] | c) | PEO | c) | 2018-12-31 | g) | 2018-12-31 | c) | 236,699.57 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Cebulano-Mangalcal Road |  |  | Road | 4.17 | CBRMC | a) | 178024.03 | a) | 01/01/18 | e) | - | a) | 178024.03 | a) | 100.00% | c) | 100% | a) | 2 | Completed as per physical accomplishment. | 2
| DAN | [7 empty] | b) | Gamad/Maligro | b) | 2018-05-03 | f) | - | b) | 178024.03 | b) | - | d) | - | b) | 4 | Financial documents still on process | 2
| 073 | [7 empty] | c) | Brgy. Mangalcal Women's Homebased Workers Association | c) | 2019-02-03 | g) | 2019-02-03 | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Tubod-Basa-Mangalcal Road |  |  | Road | 3.93 | Admin | a) | 217304.13 | a) | 01/01/18 | e) | - | a) | 217304.13 | a) | 100.00% | c) | 100% | a) | 1 | Completed as per physical accomplishment. | 2
| DAN | [7 empty] | b) | Gamad/Maligro | b) | 01/08/18 | f) | - | b) | 217304.13 | b) | - | d) | - | b) | 3 | Financial documents still on process | 2
| 074 | [7 empty] | c) | PEO | c) | 2018-12-31 | g) | 2018-12-31 | c) | 212,336.25 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Basa-Tubod Road |  |  | Road | 1.56 | Admin | a) | 153509.11 | a) | 01/01/18 | e) | - | a) | 153509.11 | a) | 100.00% | c) | 100% | a) | 12 | Completed as per physical accomplishment. | 2
| DAN | [7 empty] | b) | Gamad/Maligro | b) | 01/04/18 | f) | - | b) | 153509.11 | b) | - | d) | - | b) | 36 | Financial documents still on process | 2
| 076 | [7 empty] | c) | PEO | c) | 2018-12-31 | g) | 2018-12-31 | c) | 153,509.11 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Tubod-Pilar Road |  |  | Road | 1.55 | Admin | a) | 140507.18 | a) | 01/01/18 | e) | - | a) | 140507.18 | a) | 100.00% | c) | 100% | a) | 12 | Completed as per physical accomplishment. | 2
| DAN | [7 empty] | b) | Gamad/Maligro | b) | 02/12/18 | f) | - | b) | 140507.18 | b) | - | d) | - | b) | 36 | Financial documents still on process | 2
| 077 | [7 empty] | c) | PEO | c) | 2018-12-31 | g) | 2018-12-31 | c) | 140,507.18 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Upper Mangalcal-Lower Mangalcal |  |  | Road | 2.43 | Admin | a) | 149291.32 | a) | 01/01/18 | e) | - | a) | 149291.32 | a) | 100.00% | c) | 100% | a) | 10 | Completed as per physical accomplishment. | 2
| DAN |  | Road | [5 empty] | b) | Gamad/Maligro | b) | 02/12/18 | f) | - | b) | 149291.32 | b) | - | d) | - | b) | 30 | Financial documents still on process | 2
| 078 | [7 empty] | c) | PEO | c) | 2018-12-31 | g) | 2018-12-31 | c) | 143,316.91 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Upper Mangalcal-Lower Mangalcal |  |  | Road | 2.43 | CBRMC | a) | 89828.64 | a) | 01/01/18 | e) | - | a) | 89828.64 | a) | 100.00% | c) | 100% | a) | 2 | Completed as per physical accomplishment. | 2
| DAN |  | Road | [5 empty] | b) | Gamad/Maligro | b) | 2018-05-03 | f) | - | b) | 89828.64 | b) | - | d) | - | b) | 4 | Financial documents still on process | 2
| 078 | [7 empty] | c) | Brgy. Mangalcal Women's Homebased Workers Association | c) | 2019-02-03 | g) | 2019-02-03 | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Cebulano-Loceta Road |  |  | Road | 1.87 | Admin | a) | 166206.3 | a) | 01/01/18 | e) | - | a) | 166206.3 | a) | 100.00% | c) | 100% | a) | 10 | Completed as per physical accomplishment. | 2
| DAN | [7 empty] | b) | Gamad/Maligro | b) | 01/04/18 | f) | - | b) | 166206.3 | b) | - | d) | - | b) | 30 | Financial documents still on process | 2
| 079 | [7 empty] | c) | PEO | c) | 2018-12-31 | g) | 2018-12-31 | c) | 165,088.85 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Loceta-Lower Mangalcal Road |  |  | Road | 2.07 | Admin | a) | 121918.96 | a) | 01/01/18 | e) | - | a) | 121918.96 | a) | 100.00% | c) | 100% | a) | 12 | Completed as per physical accomplishment. | 2
| DAN | [7 empty] | b) | Gamad/Maligro | b) | 01/04/18 | f) | - | b) | 121918.96 | b) | - | d) | - | b) | 36 | Financial documents still on process | 2
| 080 | [7 empty] | c) | PEO | c) | 2018-12-31 | g) | 2018-12-31 | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Lower Asuncion-Upper Asuncion Road |  |  | Road | 1.02 | Admin | a) | 90657.98 | a) | 01/01/18 | e) | - | a) | 90657.98 | a) | 100.00% | c) | 100% | a) | 12 | Completed as per physical accomplishment. | 2
| DAN | [7 empty] | b) | Gamad/Maligro | b) | 01/04/18 | f) | - | b) | 90657.98 | b) | - | d) | - | b) | 36 | Financial documents still on process | 2
| 081 | [7 empty] | c) | PEO | c) | 2018-12-31 | g) | 2018-12-31 | c) | 90,657.98 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Jct.Highway-Carmen-Mangalcal-Tubod |  |  | Road | 11.34 | Admin | a) | 888986.6 | a) | 01/01/18 | e) | - | a) | 888986.6 | a) | 100.00% | c) | 100% | a) | 8 | Completed as per physical accomplishment. | 2
| DAN |  | Road | [5 empty] | b) | Gamad/Maligro | b) | 01/04/18 | f) | - | b) | 888986.6 | b) | - | d) | - | b) | 40 | Financial documents still on process | 2
| 082 | [7 empty] | c) | PEO | c) | 2018-12-31 | g) | 2018-12-31 | c) | 698,903.80 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Jct.Highway-Sto.Niño-La Paz-San |  |  | Road | 6.08 | Admin | a) | 458781.46 | a) | 01/01/18 | e) | - | a) | 458781.46 | a) | 100.00% | c) | 100% | a) | 8 | Completed as per physical accomplishment. | 2
| DAN |  | Vicente Road | [5 empty] | b) | Gamad/Maligro | b) | 01/03/18 | f) | - | b) | 458781.46 | b) | - | d) | - | b) | 40 | Financial documents still on process | 2
| 083 | [7 empty] | c) | PEO | c) | 2018-12-31 | g) | 2018-12-31 | c) | 458,781.46 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Jct.Highway-Sto.Niño-Kabankalan- |  |  | Road | 2.13 | Admin | a) | 127936.58 | a) | 01/01/18 | e) | - | a) | 127936.58 | a) | 100.00% | c) | 100% | a) | 10 | Completed as per physical accomplishment. | 2
| DAN |  | La Paz Road | [5 empty] | b) | Gamad/Maligro | b) | 01/08/18 | f) | - | b) | 127936.58 | b) | - | d) | - | b) | 50 | Financial documents still on process | 2
| 084 | [7 empty] | c) | PEO | c) | 2018-12-31 | g) | 2018-12-31 | c) | 15,535.28 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Jct.Highway-Sto.Niño-Kabankalan- |  |  | Road | 2.13 | CBRMC | a) | 81662.4 | a) | 01/01/18 | e) | - | a) | 81662.4 | a) | 100.00% | c) | 100% | a) | 1 | Completed as per physical accomplishment. | 2
| DAN |  | La Paz Road | [5 empty] | b) | Gamad/Maligro | b) | 01/08/18 | f) | - | b) | 81662.4 | b) | - | d) | - | b) | 1 | Financial documents still on process | 2
| 084 | [7 empty] | c) | Taba Coconut Farmers Association | c) | 2018-12-31 | g) | 2018-12-31 | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Ising-Sto.Niño Road |  |  | Road | 2.07 | Admin | a) | 107208.18 | a) | 01/01/18 | e) | - | a) | 107208.18 | a) | 100.00% | c) | 100% | a) | 12 | Completed as per physical accomplishment. | 2
| DAN | [7 empty] | b) | Gamad/Maligro | b) | 01/03/18 | f) | - | b) | 107208.18 | b) | - | d) | - | b) | 36 | Financial documents still on process | 2
| 085 | [7 empty] | c) | PEO | c) | 2018-12-31 | g) | 2018-12-31 | c) | 107,151.22 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Ising-Sto.Niño Road |  |  | Road | 2.07 | CBRMC | a) | 101261.38 | a) | 01/01/18 | e) | - | a) | 101261.38 | a) | 100.00% | c) | 100% | a) | 1 | Completed as per physical accomplishment. | 2
| DAN | [7 empty] | b) | Gamad/Maligro | b) | 06/22/18 | f) | - | b) | 101261.38 | b) | - | d) | - | b) | 1 | Financial documents still on process | 2
| 085 | [7 empty] | c) | Taba Coconut Farmers Association | c) | 04/21/19 | g) | 12/31/18 | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Ising-Sadpodon-Taba-Diladila Road |  |  | Road | 5.68 | Admin | a) | 263421.11 | a) | 01/01/18 | e) | - | a) | 263421.11 | a) | 100.00% | c) | 100% | a) | 8 | Completed as per physical accomplishment. | 2
| DAN | [7 empty] | b) | Gamad/Maligro | b) | 01/03/18 | f) | - | b) | 263421.11 | b) | - | d) | - | b) | 24 | Financial documents still on process | 2
| 086 | [7 empty] | c) | PEO | c) | 2018-12-31 | g) | 2018-12-31 | c) | 261,318.46 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Ising-Sadpodon-Taba-Diladila Road |  |  | Road | 5.68 | CBRMC | a) | 175301.95 | a) | 01/01/18 | e) | - | a) | 175301.95 | a) | 100.00% | c) | 100% | a) | 2 | Completed as per physical accomplishment. | 2
| DAN | [7 empty] | b) | Gamad/Maligro | b) | 04/26/18 | f) | - | b) | 175301.95 | b) | - | d) | - | b) | 6 | Financial documents still on process | 2
| 086 | [7 empty] | c) | Taba Coconut Farmers Association | c) | 2019-01-26 | g) | 12/31/18 | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Tuganay-Taba Road |  |  | Road | 4.27 | CBRMC | a) | 140549.33 | a) | 01/01/18 | e) | - | a) | 140549.33 | a) | 100.00% | c) | 100% | a) | 2 | Completed as per physical accomplishment. | 2
| DAN | [7 empty] | b) | Gamad/Maligro | b) | 04/26/18 | f) | - | b) | 140549.33 | b) | - | d) | - | b) | 4 | Financial documents still on process | 2
| 087 | [7 empty] | c) | Taba Coconut Farmers Association | c) | 2019-01-26 | g) | 12/31/18 | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Jct. Highway-Tuganay-Taba Road |  |  | Road | 4.4 | Admin | a) | 137256.7 | a) | 01/01/18 | e) | - | a) | 137256.7 | a) | 100.00% | c) | 100% | a) | 8 | Completed as per physical accomplishment. | 2
| DAN | [7 empty] | b) | Gamad/Maligro | b) | 02/12/18 | f) | - | b) | 137256.7 | b) | - | d) | - | b) | 16 | Financial documents still on process | 2
| 088 | [7 empty] | c) | PEO | c) | 2018-12-31 | g) | 2018-12-31 | c) | 128,871.12 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Jct.Highway-Ising-Magsaysay Road |  |  | Road | 10.84 | Admin | a) | 736262 | a) | 01/01/18 | e) | - | a) | 736262 | a) | 100.00% | c) | 100% | a) | 8 | Completed as per physical accomplishment. | 2
| DAN | [7 empty] | b) | Gamad/Maligro | b) | 02/12/18 | f) | - | b) | 736262 | b) | - | d) | - | b) | 24 | Financial documents still on process | 2
| 089 | [7 empty] | c) | PEO | c) | 2018-12-31 | g) | 2018-12-31 | c) | 735,525.71 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Jct.Highway-Ising-Magsaysay Road |  |  | Road | 10.84 | CBRMC | a) | 222121.73 | a) | 01/01/18 | e) | - | a) | 222121.73 | a) | 100.00% | c) | 100% | a) | - | Completed as per physical accomplishment. | 2
| DAN | [7 empty] | b) | Gamad/Maligro | b) | 02/12/18 | f) | - | b) | 222121.73 | b) | - | d) | - | b) | - | Financial documents still on process | 2
| 089 | [7 empty] | c) | School on the Air Integrated Farmers Association | c) | 2018-12-31 | g) | 2018-12-31 | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Maligaya-New Camiling Road |  |  | Road | 2.13 | Admin | a) | 208418.14 | a) | 01/01/18 | e) | - | a) | 208418.14 | a) | 100.00% | c) | 100% | a) | 10 | Completed as per physical accomplishment. | 2
| DAN | [7 empty] | b) | Gamad/Maligro | b) | 02/12/18 | f) | - | b) | 208418.14 | b) | - | d) | - | b) | 12 | Financial documents still on process | 2
| 090 | [7 empty] | c) | PEO | c) | 2018-12-31 | g) | 2018-12-31 | c) | 194,652.04 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | New Camiling-Alejal-Lower Magsaysay |  |  | Road | 6.73 | Admin | a) | 393838.9 | a) | 01/01/18 | e) | - | a) | 393838.9 | a) | 100.00% | c) | 100% | a) | 12 | Completed as per physical accomplishment. | 2
| DAN |  | Road | [5 empty] | b) | Gamad/Maligro | b) | 02/12/18 | f) | - | b) | 393838.9 | b) | - | d) | - | b) | 48 | Financial documents still on process | 2
| 091 | [7 empty] | c) | PEO | c) | 2018-12-31 | g) | 2018-12-31 | c) | 236,036.98 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | New Camiling-Alejal-Lower Magsaysay |  |  | Road | 6.73 | CBRMC | a) | 209055.74 | a) | 01/01/18 | e) | - | a) | 209055.74 | a) | 100.00% | c) | 100% | a) | 2 | Completed as per physical accomplishment. | 2
| DAN |  | Road | [5 empty] | b) | Gamad/Maligro | b) | 05/04/18 | f) | - | b) | 209055.74 | b) | - | d) | - | b) | 2 | Financial documents still on process | 2
| 091 | [7 empty] | c) | School on the Air Integrated Farmers Association | c) | 02/04/19 | g) | 12/31/18 | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Anahaw-Maligaya Road |  |  | Road | 4.8 | Admin | a) | 328333.3 | a) | 01/01/18 | e) | - | a) | 328333.3 | a) | 100.00% | c) | 100% | a) |  | Completed as per physical accomplishment. | 2
| DAN | [7 empty] | b) | Gamad/Maligro | b) | 01/08/18 | f) | - | b) | 328333.3 | b) | - | d) | - | b) |  | Financial documents still on process | 2
| 093 | [7 empty] | c) | PEO | c) | 2018-12-31 | g) | 2018-12-31 | c) | 154,062.27 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Jct.Highway-Tuganay-Anibongan Road |  |  | Road | 3.66 | Admin | a) | 192897.9 | a) | 01/01/18 | e) | - | a) | 192897.9 | a) | 100.00% | c) | 100% | a) | 10 | Completed as per physical accomplishment. | 2
| DAN | [7 empty] | b) | Gamad/Maligro | b) | 01/04/18 | f) | - | b) | 192897.9 | b) | - | d) | - | b) | 20 | Financial documents still on process | 2
| 094 | [7 empty] | c) | PEO | c) | 2018-12-31 | g) | 2018-12-31 | c) | 176,119.23 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Jct.Highway-Tuganay-Anibongan Road |  |  | Road | 3.66 | CBRMC | a) | 97994.88 | a) | 01/01/18 | e) | - | a) | 97994.88 | a) | 100.00% | c) | 100% | a) |  | Completed as per physical accomplishment. | 2
| DAN | [7 empty] | b) | Gamad/Maligro | b) | 05/04/18 | f) | - | b) | 97994.88 | b) | - | d) | - | b) |  | Financial documents still on process | 2
| 094 | [7 empty] | c) | EZRA | c) | 02/04/19 | g) | 12/31/18 | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Anibongan-Guadalupe Road |  |  | Road | 2.48 | Admin | a) | 144312.93 | a) | 01/01/18 | e) | - | a) | 144312.93 | a) | 100.00% | c) | 100% | a) |  | Completed as per physical accomplishment. | 2
| DAN | [7 empty] | b) | Gamad/Maligro | b) | 01/04/18 | f) | - | b) | 144312.93 | b) | - | d) | - | b) |  | Financial documents still on process | 2
| 095 | [7 empty] | c) | PEO | c) | 2018-12-31 | g) | 2018-12-31 | c) | 113,396.19 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Anibongan-Guadalupe Road |  |  | Road | 2.48 | CBRMC | a) | 78395.9 | a) | 01/01/18 | e) | - | a) | 78395.9 | a) | 100.00% | c) | 100% | a) | - | Completed as per physical accomplishment. | 2
| DAN | [7 empty] | b) | Gamad/Maligro | b) | 05/04/18 | f) | - | b) | 78395.9 | b) | - | d) | - | b) | - | Financial documents still on process | 2
| 095 | [7 empty] | c) | - | c) | 02/04/19 | g) | 12/31/18 | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Tuganay-Anibongan-San Isidro Road |  |  | Road | 7.22 | Admin | a) | 219455.18 | a) | 01/01/18 | e) | - | a) | 219455.18 | a) | 100.00% | c) | 100% | a) | 12 | Completed as per physical accomplishment. | 2
| DAN | [7 empty] | b) | Gamad/Maligro | b) | 01/04/18 | f) | - | b) | 219455.18 | b) | - | d) | - | b) | 24 | Financial documents still on process | 2
| 096 | [7 empty] | c) | PEO | c) | 2018-12-31 | g) | 2018-12-31 | c) | 209,407.75 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Jct.Anibongan P2,7,5-San Isidro Road |  |  | Road | 3.14 | Admin | a) | 110524.22 | a) | 01/01/18 | e) | - | a) | 110524.22 | a) | 100.00% | c) | 100% | a) | 12 | Completed as per physical accomplishment. | 2
| DAN | [7 empty] | b) | Gamad/Maligro | b) | 01/04/18 | f) | - | b) | 110524.22 | b) | - | d) | - | b) | 24 | Financial documents still on process | 2
| 097 | [7 empty] | c) | PEO | c) | 2018-12-31 | g) | 2018-12-31 | c) | 80,736.78 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Anibongan-Salvacion-Cabay-angan |  |  | Road | 6.93 | Admin | a) | 517149.14 | a) | 01/01/18 | e) | - | a) | 517149.14 | a) | 100.00% | c) | 100% | a) | 10 | Completed as per physical accomplishment. | 2
| DAN |  | Road | [5 empty] | b) | Gamad/Maligro | b) | 02/12/18 | f) | - | b) | 517149.14 | b) | - | d) | - | b) | 20 | Financial documents still on process | 2
| 098 | [7 empty] | c) | PEO | c) | 2018-12-31 | g) | 2018-12-31 | c) | 358,470.30 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Mabaus-Cabay-angan Road |  |  | Road | 3.2 | Admin | a) | 284417.14 | a) | 01/01/18 | e) | - | a) | 284417.14 | a) | 100.00% | c) | 100% | a) |  | Completed as per physical accomplishment. | 2
| DAN | [7 empty] | b) | Gamad/Maligro | b) | 01/08/18 | f) | - | b) | 284417.14 | b) | - | d) | - | b) |  | Financial documents still on process | 2
| 099 | [7 empty] | c) | PEO | c) | 2018-12-31 | g) | 2018-12-31 | c) | 277,092.31 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Mabaus-Salvacion Road |  |  | Road | 1.38 | Admin | a) | 105132.79 | a) | 01/01/18 | e) | - | a) | 105132.79 | a) | 100.00% | c) | 100% | a) |  | Completed as per physical accomplishment. | 2
| DAN | [7 empty] | b) | Gamad/Maligro | b) | 02/12/18 | f) | - | b) | 105132.79 | b) | - | d) | - | b) |  | Financial documents still on process | 2
| 100 | [7 empty] | c) | PEO | c) | 2018-12-31 | g) | 2018-12-31 | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Jct.Highway-Guadalupe-Bdry.Tagum |  |  | Road | 7.9 | Admin | a) | 574863.11 | a) | 01/01/18 | e) | - | a) | 574863.11 | a) | 100.00% | c) | 100% | a) | 10 | Completed as per physical accomplishment. | 2
| DAN |  | Road | [5 empty] | b) | Gamad/Maligro | b) | 02/16/18 | f) | - | b) | 574863.11 | b) | - | d) | - | b) | 70 | Financial documents still on process | 2
| 101 | [7 empty] | c) | PEO | c) | 2018-12-31 | g) | 2018-12-31 | c) | 301,160.92 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Dalisay-Mabuhay Road |  |  | Road | 3.25 | Admin | a) | 319810.65 | a) | 01/01/18 | e) | - | a) | 319810.65 | a) | 100.00% | c) | 100% | a) | 8 | Completed as per physical accomplishment. | 2
| DAN | [7 empty] | b) | Gamad/Maligro | b) | 02/12/18 | f) | - | b) | 319810.65 | b) | - | d) | - | b) | 24 | Financial documents still on process | 2
| 102 | [7 empty] | c) | PEO | c) | 2018-12-31 | g) | 2018-12-31 | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Sitio Malaga-Tibulao Road |  |  | Road | 3.22 | Admin | a) | 255531.08 | a) | 01/01/18 | e) | - | a) | 255531.08 | a) | 100.00% | c) | 100% | a) |  | Completed as per physical accomplishment. | 2
| DAN | [7 empty] | b) | Gamad/Maligro | b) | 02/16/18 | f) | - | b) | 255531.08 | b) | - | d) | - | b) |  | Financial documents still on process | 2
| 103 | [7 empty] | c) | PEO | c) | 2018-12-31 | g) | 2018-12-31 | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Dujali-Tanglaw Road |  |  | Road | 3.6 | Admin | a) | 280441.08 | a) | 01/01/18 | e) | - | a) | 280441.08 | a) | 100.00% | c) | 100% | a) |  | Completed as per physical accomplishment. | 2
| DAN | [7 empty] | b) | Gamad/Maligro | b) | 01/08/18 | f) | - | b) | 280441.08 | b) | - | d) | - | b) |  | Financial documents still on process | 2
| 104 | [7 empty] | c) | PEO | c) | 2018-12-31 | g) | 2018-12-31 | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Poblacion Dujali-Prk.8, Dujali Road |  |  | Road | 8.2 | Admin | a) | 577861.87 | a) | 01/01/18 | e) | - | a) | 577861.87 | a) | 100.00% | c) | 100% | a) | 22 | Completed as per physical accomplishment. | 2
| DAN | [7 empty] | b) | Gamad/Maligro | b) | 01/04/18 | f) | - | b) | 577861.87 | b) | - | d) | - | b) | 66 | Financial documents still on process | 2
| 105 | [7 empty] | c) | PEO | c) | 2018-12-31 | g) | 2018-12-31 | c) | 350,004.70 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Poblacion Dujali-Prk.8, Dujali Road |  |  | Road | 8.2 | CBRMC | a) | 226152.24 | a) | 01/01/18 | e) | - | a) | 226152.24 | a) | 100.00% | c) | 100% | a) | - | Completed as per physical accomplishment. | 2
| DAN | [7 empty] | b) | Gamad/Maligro | b) | 01/08/18 | f) | - | b) | 226152.24 | b) | - | d) | - | b) | - | Financial documents still on process | 2
| 105 | [7 empty] | c) | Duajli Pob. Farmers Irrigators | c) | 2018-12-31 | g) | 12/31/18 | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Dujali-San Isidro Road |  |  | Road | 3 | Admin | a) | 349588.79 | a) | 01/01/18 | e) | - | a) | 349588.79 | a) | 100.00% | c) | 100% | a) | 5 | Completed as per physical accomplishment. | 2
| DAN | [7 empty] | b) | Gamad/Maligro | b) | 01/08/18 | f) | - | b) | 349588.79 | b) | - | d) | - | b) | 20 | Financial documents still on process | 2
| 107 | [7 empty] | c) | PEO | c) | 2018-12-31 | g) | 2018-12-31 | c) | 278,882.34 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Dujali-San Isidro Road |  |  | Road | 3 | CBRMC | a) | 71862.91 | a) | 01/01/18 | e) | - | a) | 71862.91 | a) | 100.00% | c) | 100% | a) | - | Completed as per physical accomplishment. | 2
| DAN | [7 empty] | b) | Gamad/Maligro | b) | 10/26/18 | f) | - | b) | 71862.91 | b) | - | d) | - | b) | - | Financial documents still on process | 2
| 107 | [7 empty] | c) |  | c) | 12/31/18 | g) | 12/31/18 | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | New Casay-Bugtong Talisay Road |  |  | Road | 2.18 | Admin | a) | 222469.81 | a) | 01/01/18 | e) | - | a) | 222469.81 | a) | 100.00% | c) | 100% | a) | 8 | Completed as per physical accomplishment. | 2
| DAN | [7 empty] | b) | Gamad/Maligro | b) | 01/08/18 | f) | - | b) | 222469.81 | b) | - | d) | - | b) | 24 | Financial documents still on process | 2
| 108 | [7 empty] | c) | PEO | c) | 2018-12-31 | g) | 2018-12-31 | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Prk.5 RJS-Prk.6 New Casay Road |  |  | Road | 2.73 | Admin | a) | 107717.9 | a) | 01/01/18 | e) | - | a) | 107717.9 | a) | 100.00% | c) | 100% | a) | 12 | Completed as per physical accomplishment. | 2
| DAN | [7 empty] | b) | Gamad/Maligro | b) | 02/12/18 | f) | - | b) | 107717.9 | b) | - | d) | - | b) | 36 | Financial documents still on process | 2
| 109 | [7 empty] | c) | PEO | c) | 2018-12-31 | g) | 2018-12-31 | c) | 106,464.30 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Prk.5 RJS-Prk.6 New Casay Road |  |  | Road | 2.73 | CBRMC | a) | 117593.86 | a) | 01/01/18 | e) | - | a) | 117593.86 | a) | 100.00% | c) | 100% | a) | 2 | Completed as per physical accomplishment. | 2
| DAN | [7 empty] | b) | Gamad/Maligro | b) | 05/07/18 | f) | - | b) | 117593.86 | b) | - | d) | - | b) | 2 | Financial documents still on process | 2
| 109 | [7 empty] | c) | MANCIIA | c) | 02/07/19 | g) | 12/31/18 | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Cabay-angan-Esperanza Road |  |  | Road | 5.37 | Admin | a) | 537948.48 | a) | 01/01/18 | e) | - | a) | 537948.48 | a) | 100.00% | c) | 100% | a) | 12 | Completed as per physical accomplishment. | 2
| DAN | [7 empty] | b) | Gamad/Maligro | b) | 01/04/18 | f) | - | b) | 537948.48 | b) | - | d) | - | b) | 36 | Financial documents still on process | 2
| 110 | [7 empty] | c) | PEO | c) | 2018-12-31 | g) | 2018-12-31 | c) | 479,947.45 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Prk.6 Cabay-angan-Esti Road |  |  | Road | 1.08 | Admin | a) | 90911.93 | a) | 01/01/18 | e) | - | a) | 90911.93 | a) | 100.00% | c) | 100% | a) | 12 | Completed as per physical accomplishment. | 2
| DAN | [7 empty] | b) | Gamad/Maligro | b) | 01/03/18 | f) | - | b) | 90911.93 | b) | - | d) | - | b) | 36 | Financial documents still on process | 2
| 111 | [7 empty] | c) | PEO | c) | 2018-12-31 | g) | 2018-12-31 | c) | 90,911.93 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Prk.5-Prk.1 Pawas, Dujali Road |  |  | Road | 2.18 | Admin | a) | 56566.39 | a) | 01/01/18 | e) | - | a) | 56566.39 | a) | 100.00% | c) | 100% | a) | 12 | Completed as per physical accomplishment. | 2
| DAN | [7 empty] | b) | Gamad/Maligro | b) | 01/03/18 | f) | - | b) | 56566.39 | b) | - | d) | - | b) | 36 | Financial documents still on process | 2
| 112 | [7 empty] | c) | PEO | c) | 2018-12-31 | g) | 2018-12-31 | c) | 54,346.01 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Prk.5-Prk.1 Pawas, Dujali Road |  |  | Road | 2.18 | CBRMC | a) | 137192.83 | a) | 01/01/18 | e) | - | a) | 137192.83 | a) | 100.00% | c) | 100% | a) | 5 | Completed as per physical accomplishment. | 2
| DAN | [7 empty] | b) | Gamad/Maligro | b) | 05/02/18 | f) | - | b) | 137192.83 | b) | - | d) | - | b) | 30 | Financial documents still on process | 2
| 112 | [7 empty] | c) | MANCIIA | c) | 02/02/19 | g) | 12/31/18 | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Dujali-Balisong-Magupising Road |  |  | Road | 5.52 | Admin | a) | 400494.66 | a) | 01/01/18 | e) | - | a) | 400494.66 | a) | 100.00% | c) | 100% | a) | 8 | Completed as per physical accomplishment. | 2
| DAN | [7 empty] | b) | Gamad/Maligro | b) | 01/03/18 | f) | - | b) | 400494.66 | b) | - | d) | - | b) | 24 | Financial documents still on process | 2
| 113 | [7 empty] | c) | PEO | c) | 2018-12-31 | g) | 2018-12-31 | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Prk.Narafil-Brgy. Site Magupising Road |  |  | Road | 2.08 | Admin | a) | 96860.19 | a) | 01/01/18 | e) | - | a) | 96860.19 | a) | 100.00% | c) | 100% | a) | 8 | Completed as per physical accomplishment. | 2
| DAN | [7 empty] | b) | Gamad/Maligro | b) | 01/03/18 | f) | - | b) | 96860.19 | b) | - | d) | - | b) | 8 | Financial documents still on process | 2
| 114 | [7 empty] | c) | PEO | c) | 12/31/18 | g) | 12/31/18 | c) | 33,963.32 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Dujali-Sitio Pawas Road |  |  | Road | 1.25 | Admin | a) | 230,810.21 | a) | 01/01/18 | e) | - | a) | 230,810.21 | a) | 100.00% | c) | 100% | a) |  | Completed as per physical accomplishment. | 2
| DAN | [7 empty] | b) | Gamad/Maligro | b) | 01/03/18 | f) | - | b) | 230,810.21 | b) | - | d) | - | b) |  | Financial documents still on process | 2
| 115 | [7 empty] | c) | PEO | c) | 12/31/18 | g) | 12/31/18 | c) | 230,657.28 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Prk.1-Prk.2, Sitio Pawas Road |  |  | Road | 1.4 | Admin | a) | 109068.92 | a) | 01/01/18 | e) | - | a) | 109068.92 | a) | 100.00% | c) | 100% | a) |  | Completed as per physical accomplishment. | 2
| DAN | [7 empty] | b) | Gamad/Maligro | b) | 02/12/18 | f) | - | b) | 109068.92 | b) | - | d) | - | b) |  | Financial documents still on process | 2
| 116 | [7 empty] | c) | PEO | c) | 12/31/18 | g) | 12/31/18 | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Dujali-Pawas-San Vicente Road |  |  | Road | 4.42 | Admin | a) | 103164.72 | a) | 01/01/18 | e) | - | a) | 103164.72 | a) | 100.00% | c) | 100% | a) | 12 | Completed as per physical accomplishment. | 2
| DAN | [7 empty] | b) | Gamad/Maligro | b) | 01/04/18 | f) | - | b) | 103164.72 | b) | - | d) | - | b) | 48 | Financial documents still on process | 2
| 117 | [7 empty] | c) | PEO | c) | 12/31/18 | g) | 12/31/18 | c) | 72,378.03 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Dujali-Pawas-San Vicente Road |  |  | Road | 4.42 | CBRMC | a) | 212322.24 | a) | 01/01/18 | e) | - | a) | 212322.24 | a) | 100.00% | c) | 100% | a) | 2 | Completed as per physical accomplishment. | 2
| DAN | [7 empty] | b) | Gamad/Maligro | b) | 05/07/18 | f) | - | b) | 212322.24 | b) | - | d) | - | b) | 24 | Financial documents still on process | 2
| 117 | [7 empty] | c) | Balisong San Vicente Irrigator's Association | c) | 02/07/19 | g) | 12/31/18 | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Jct.Salvacion-San Vicente-Cabay-angan |  |  | Road | 3.45 | Admin | a) | 205564.46 | a) | 01/01/18 | e) | - | a) | 205564.46 | a) | 100.00% | c) | 100% | a) | 12 | Completed as per physical accomplishment. | 2
| DAN |  | Road | [5 empty] | b) | Gamad/Maligro | b) | 01/03/18 | f) | - | b) | 205564.46 | b) | - | d) | - | b) | 48 | Financial documents still on process | 2
| 118 | [7 empty] | c) | PEO | c) | 12/31/18 | g) | 12/31/18 | c) | 202,565.93 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Jct.Salvacion-San Vicente-Cabay-angan |  |  | Road | 3.45 | CBRMC | a) | 133926.34 | a) | 01/01/18 | e) | - | a) | 133926.34 | a) | 100.00% | c) | 100% | a) | 2 | Completed as per physical accomplishment. | 2
| DAN |  | Road | [5 empty] | b) | Gamad/Maligro | b) | 05/07/18 | f) | - | b) | 133926.34 | b) | - | d) | - | b) | 4 | Financial documents still on process | 2
| 118 | [7 empty] | c) | Balisong San Vicente Irrigator's Association | c) | 02/07/19 | g) | 12/31/18 | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Dujali-San Miguel Road |  |  | Road | 3.95 | Admin | a) | 254671.37 | a) | 01/01/18 | e) | - | a) | 254671.37 | a) | 100.00% | c) | 100% | a) | 12 | Completed as per physical accomplishment. | 2
| DAN | [7 empty] | b) | Gamad/Maligro | b) | 02/16/18 | f) | - | b) | 254671.37 | b) | - | d) | - | b) | 60 | Financial documents still on process | 2
| 119 | [7 empty] | c) | PEO | c) | 2018-12-31 | g) | 2018-12-31 | c) | 247,867.31 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Dujali-San Miguel Road |  |  | Road | 3.95 | CBRMC | a) | 133926.34 | a) | 01/01/18 | e) | - | a) | 133926.34 | a) | 100.00% | c) | 100% | a) | - | Completed as per physical accomplishment. | 2
| DAN | [7 empty] | b) | Gamad/Maligro | b) | 01/03/18 | f) | - | b) | 133926.34 | b) | - | d) | - | b) | - | Financial documents still on process | 2
| 119 | [7 empty] | c) | Duajli Pob. Farmers Irrigator | c) | 12/31/18 | g) | 12/31/18 | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | San Miguel-Crossing Kinamayan Road |  |  | Road | 2.8 | Admin | a) | 71231.27 | a) | 01/01/18 | e) | - | a) | 71231.27 | a) | 100.00% | c) | 100% | a) |  | Completed as per physical accomplishment. | 2
| DAN | [7 empty] | b) | Gamad/Maligro | b) | 01/03/18 | f) | - | b) | 71231.27 | b) | - | d) | - | b) |  | Financial documents still on process | 2
| 120 | [7 empty] | c) | PEO | c) | 2018-12-31 | g) | 2018-12-31 | c) | 71,190.34 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | San Miguel-Libertad Road |  |  | Road | 6.2 | Admin | a) | 588705.52 | a) | 01/01/18 | e) | - | a) | 588705.52 | a) | 100.00% | c) | 100% | a) | 12 | Completed as per physical accomplishment. | 2
| DAN | [7 empty] | b) | Gamad/Maligro | b) | 01/03/18 | f) | - | b) | 588705.52 | b) | - | d) | - | b) | 36 | Financial documents still on process | 2
| 121 | [7 empty] | c) | PEO | c) | 2018-12-31 | g) | 2018-12-31 | c) | 574,308.39 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | San Miguel-Casig-ang Road |  |  | Road | 2.55 | Admin | a) | 175798.95 | a) | 01/01/18 | e) | - | a) | 175798.95 | a) | 100.00% | c) | 100% | a) | 12 | Completed as per physical accomplishment. | 2
| DAN | [7 empty] | b) | Gamad/Maligro | b) | 02/16/18 | f) | - | b) | 175798.95 | b) | - | d) | - | b) | 36 | Financial documents still on process | 2
| 122 | [7 empty] | c) | PEO | c) | 2018-12-31 | g) | 2018-12-31 | c) | 147,453.47 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | San Miguel-Casig-ang Road |  |  | Road | 2.55 | CBRMC | a) | 75129.41 | a) | 01/01/18 | e) | - | a) | 75129.41 | a) | 100.00% | c) | 100% | a) | - | Completed as per physical accomplishment. | 2
| DAN | [7 empty] | b) | Gamad/Maligro | b) | 01/03/18 | f) | - | b) | 75129.41 | b) | - | d) | - | b) | - | Financial documents still on process | 2
| 122 | [7 empty] | c) | KCIA | c) | 2018-12-31 | g) | 2018-12-31 | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Bacali-Casig-ang-Libertad Road |  |  | Road | 4.7 | Admin | a) | 446623.9 | a) | 01/01/18 | e) | - | a) | 446623.9 | a) | 100.00% | c) | 100% | a) |  | Completed as per physical accomplishment. | 2
| DAN | [7 empty] | b) | Gamad/Maligro | b) | 01/22/18 | f) | - | b) | 446623.9 | b) | - | d) | - | b) |  | Financial documents still on process | 2
| 123 | [7 empty] | c) | PEO | c) | 2018-12-31 | g) | 2018-12-31 | c) | 69,420.84 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Kinamayan-Moslog-Mahayag Road |  |  | Road | 3.23 | Admin | a) | 166223.27 | a) | 01/01/18 | e) | - | a) | 166223.27 | a) | 100.00% | c) | 100% | a) | 3 | Completed as per physical accomplishment. | 2
| DAN | [7 empty] | b) | Gamad/Maligro | b) | 02/12/18 | f) | - | b) | 166223.27 | b) | - | d) | - | b) | 12 | Financial documents still on process | 2
| 124 | [7 empty] | c) | PEO | c) | 2018-12-31 | g) | 2018-12-31 | c) | 147,526.53 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Kinamayan-Moslog-Mahayag Road |  |  | Road | 3.23 | CBRMC | a) | 120860.35 | a) | 01/01/18 | e) | - | a) | 120860.35 | a) | 100.00% | c) | 100% | a) | - | Completed as per physical accomplishment. | 2
| DAN | [7 empty] | b) | Gamad/Maligro | b) | 01/22/18 | f) | - | b) | 120860.35 | b) | - | d) | - | b) | - | Financial documents still on process | 2
| 124 | [7 empty] | c) | PAMIA | c) | 2018-12-31 | g) | 2018-12-31 | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | San Miguel-Moslog-Kinamayan Road |  |  | Road | 2.9 | Admin | a) | 202520.29 | a) | 01/01/18 | e) | - | a) | 202520.29 | a) | 100.00% | c) | 100% | a) | 10 | Completed as per physical accomplishment. | 2
| DAN | [7 empty] | b) | Gamad/Maligro | b) | 01/04/18 | f) | - | b) | 202520.29 | b) | - | d) | - | b) | 30 | Financial documents still on process | 2
| 125 | [7 empty] | c) | PEO | c) | 2018-12-31 | g) | 2018-12-31 | c) | 70,425.06 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Kinamayan-Lunga-og Road |  |  | Road | 2.59 | Admin | a) | 254864.48 | a) | 01/01/18 | e) | - | a) | 254864.48 | a) | 100.00% | c) | 100% | a) | 10 | Completed as per physical accomplishment. | 2
| DAN | [7 empty] | b) | Gamad/Maligro | b) | 01/03/18 | f) | - | b) | 254864.48 | b) | - | d) | - | b) | 30 | Financial documents still on process | 2
| 126 | [7 empty] | c) | PEO | c) | 2018-12-31 | g) | 2018-12-31 | c) | 248,573.64 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Prk.Magsaysay-Lunga-og-Dalisay Road |  |  | Road | 2.81 | Admin | a) | 152386.36 | a) | 01/01/18 | e) | - | a) | 152386.36 | a) | 100.00% | c) | 100% | a) |  | Completed as per physical accomplishment. | 2
| DAN | [7 empty] | b) | Gamad/Maligro | b) | 01/03/18 | f) | - | b) | 152386.36 | b) | - | d) | - | b) |  | Financial documents still on process | 2
| 127 | [7 empty] | c) | PEO | c) | 2018-12-31 | g) | 2018-12-31 | c) | 130,525.88 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Prk.Magsaysay-Lunga-og-Dalisay Road |  |  | Road | 2.81 | CBRMC | a) | 124126.85 | a) | 01/01/18 | e) | - | a) | 124126.85 | a) | 100.00% | c) | 100% | a) | 2 | Completed as per physical accomplishment. | 2
| DAN | [7 empty] | b) | Gamad/Maligro | b) | 05/07/18 | f) | - | b) | 124126.85 | b) | - | d) | - | b) | 2 | Financial documents still on process | 2
| 127 | [7 empty] | c) | Lunga-og Tribal Association | c) | 02/07/19 | g) | 12/31/18 | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Prk.Apitong-Upper Balisong-Dalisay |  |  | Road | 4.6 | Admin | a) | 200531.56 | a) | 01/01/18 | e) | - | a) | 200531.56 | a) | 100.00% | c) | 100% | a) | 12 | Completed as per physical accomplishment. | 2
| DAN |  | Road | [5 empty] | b) | Gamad/Maligro | b) | 01/03/18 | f) | - | b) | 200531.56 | b) | - | d) | - | b) | 36 | Financial documents still on process | 2
| 128 | [7 empty] | c) | PEO | c) | 2018-12-31 | g) | 2018-12-31 | c) | 200,041.98 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Prk.Apitong-Upper Balisong-Dalisay |  |  | Road | 4.6 | CBRMC | a) | 182923.78 | a) | 01/01/18 | e) | - | a) | 182923.78 | a) | 100.00% | c) | 100% | a) | 2 | Completed as per physical accomplishment. | 2
| DAN |  | Road | [5 empty] | b) | Gamad/Maligro | b) | 05/07/18 | f) | - | b) | 182923.78 | b) | - | d) | - | b) | 2 | Financial documents still on process | 2
| 128 | [7 empty] | c) | Lunga-og Tribal Association | c) | 02/07/19 | g) | 12/31/18 | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Sitio Paradise-Magkakaisa-Esperanza |  |  | Road | 1.75 | Admin | a) | 67345.26 | a) | 01/01/18 | e) | - | a) | 67345.26 | a) | 100.00% | c) | 100% | a) | 10 | Completed as per physical accomplishment. | 2
| DAN |  | Road | [5 empty] | b) | Gamad/Maligro | b) | 01/04/18 | f) | - | b) | 67345.26 | b) | - | d) | - | b) | 20 | Financial documents still on process | 2
| 129 | [7 empty] | c) | PEO | c) | 2018-12-31 | g) | 2018-12-31 | c) | 58,485.82 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Sitio Paradise-Magkakaisa-Esperanza |  |  | Road | 1.75 | CBRMC | a) | 88195.39 | a) | 01/01/18 | e) | - | a) | 88195.39 | a) | 100.00% | c) | 100% | a) | 2 | Completed as per physical accomplishment. | 2
| DAN |  | Road | [5 empty] | b) | Gamad/Maligro | b) | 05/09/18 | f) | - | b) | 88195.39 | b) | - | d) | - | b) | 4 | Financial documents still on process | 2
| 129 | [7 empty] | c) | Los Amigos Group of Women & Farmers Association | c) | 02/09/19 | g) | 12/31/18 | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Los Amigos 1-Esperanza-Los Amigos 2 |  |  | Road | 3.59 | Admin | a) | 129623.79 | a) | 01/01/18 | e) | - | a) | 129623.79 | a) | 100.00% | c) | 100% | a) |  | Completed as per physical accomplishment. | 2
| DAN |  | Road | [5 empty] | b) | Gamad/Maligro | b) | 01/04/18 | f) | - | b) | 129623.79 | b) | - | d) | - | b) |  | Financial documents still on process | 2
| 130 | [7 empty] | c) | PEO | c) | 2018-12-31 | g) | 2018-12-31 | c) | 113,391.65 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Los Amigos 1-Esperanza-Los Amigos 2 |  |  | Road | 3.59 | CBRMC | a) | 189456.77 | a) | 01/01/18 | e) | - | a) | 189456.77 | a) | 100.00% | c) | 100% | a) | 2 | Completed as per physical accomplishment. | 2
| DAN |  | Road | [5 empty] | b) | Gamad/Maligro | b) | 05/09/18 | f) | - | b) | 189456.77 | b) | - | d) | - | b) | 2 | Financial documents still on process | 2
| 130 | [7 empty] | c) | Los Amigos Group of Women & Farmers Association | c) | 02/09/19 | g) | 12/31/18 | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Mugas-Lanatad Road |  |  | Road | 1.53 | Admin | a) | 153098.12 | a) | 01/01/18 | e) | - | a) | 153098.12 | a) | 100.00% | c) | 100% | a) |  | Completed as per physical accomplishment. | 2
| DAN | [7 empty] | b) | Gamad/Maligro | b) | 01/22/18 | f) | - | b) | 153098.12 | b) | - | d) | - | b) |  | Financial documents still on process | 2
| 131 | [7 empty] | c) | PEO | c) | 2018-12-31 | g) | 2018-12-31 | c) | 130,993.26 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Mugas-Lunga-og Road |  |  | Road | 2.68 | Admin | a) | 128090.03 | a) | 01/01/18 | e) | - | a) | 128090.03 | a) | 100.00% | c) | 100% | a) | 12 | Completed as per physical accomplishment. | 2
| DAN | [7 empty] | b) | Gamad/Maligro | b) | 02/16/18 | f) | - | b) | 128090.03 | b) | - | d) | - | b) | 60 | Financial documents still on process | 2
| 132 | [7 empty] | c) | PEO | c) | 2018-12-31 | g) | 2018-12-31 | c) | 119,702.20 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Mugas-Lunga-og Road |  |  | Road | 2.68 | CBRMC | a) | 93095.14 | a) | 01/01/18 | e) | - | a) | 93095.14 | a) | 100.00% | c) | 100% | a) | 2 | Completed as per physical accomplishment. | 2
| DAN | [7 empty] | b) | Gamad/Maligro | b) | 05/07/18 | f) | - | b) | 93095.14 | b) | - | d) | - | b) | 2 | Financial documents still on process | 2
| 132 | [7 empty] | c) | Lunga-og Tribal Association | c) | 02/07/19 | g) | 12/31/18 | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Pantaron-Mugas Road |  |  | Road | 3.35 | Admin | a) | 198806.74 | a) | 01/01/18 | e) | - | a) | 198806.74 | a) | 100.00% | c) | 100% | a) | 12 | Completed as per physical accomplishment. | 2
| DAN | [7 empty] | b) | Gamad/Maligro | b) | 02/12/18 | f) | - | b) | 198806.74 | b) | - | d) | - | b) | 36 | Financial documents still on process | 2
| 133 | [7 empty] | c) | PEO | c) | 2018-12-31 | g) | 2018-12-31 | c) | 152,359.49 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Pantaron-Mugas Road |  |  | Road | 3.35 | CBRMC | a) | 137192.83 | a) | 01/01/18 | e) | - | a) | 137192.83 | a) | 100.00% | c) | 100% | a) | - | Completed as per physical accomplishment. | 2
| DAN | [7 empty] | b) | Gamad/Maligro | b) | 01/22/18 | f) | - | b) | 137192.83 | b) | - | d) | - | b) | - | Financial documents still on process | 2
| 133 | [7 empty] | c) | Katipunan Pantaron Irrigators Assoc. | c) | 2018-12-31 | g) | 12/31/18 | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | New Katipunan-Pantaron Road |  |  | Road | 1.96 | Admin | a) | 192870.42 | a) | 01/01/18 | e) | - | a) | 192870.42 | a) | 100.00% | c) | 100% | a) | 3 | Completed as per physical accomplishment. | 2
| DAN | [7 empty] | b) | Gamad/Maligro | b) | 01/04/18 | f) | - | b) | 192870.42 | b) | - | d) | - | b) | 12 | Financial documents still on process | 2
| 134 | [7 empty] | c) | PEO | c) | 12/31/18 | g) | 12/31/18 | c) | 51,000.00 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Sto.Tomas-Bdry.Mamacao Road |  |  | Road | 4.9 | Admin | a) | 328576.02 | a) | 01/01/18 | e) | - | a) | 328576.02 | a) | 100.00% | c) | 100% | a) | 6 | Completed as per physical accomplishment. | 2
| DAN | [7 empty] | b) | Gamad/Maligro | b) | 01/22/18 | f) | - | b) | 328576.02 | b) | - | d) | - | b) | 36 | Financial documents still on process | 2
| 135 | [7 empty] | c) | PEO | c) | 12/31/18 | g) | 12/31/18 | c) | 191,558.02 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Sto.Tomas-Bdry.Mamacao Road |  |  | Road | 4.9 | CBRMC | a) | 163324.8 | a) | 01/01/18 | e) | - | a) | 163324.8 | a) | 100.00% | c) | 100% | a) | 2 | Completed as per physical accomplishment. | 2
| DAN | [7 empty] | b) | Gamad/Maligro | b) | 04/19/18 | f) | - | b) | 163324.8 | b) | - | d) | - | b) | 6 | Financial documents still on process | 2
| 135 | [7 empty] | c) | Poblacion Tibal-og Tribal Assoc | c) | 01/19/19 | g) | 12/31/18 | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Fd.Rd.3-San Jose Road |  |  | Road | 4.55 | Admin | a) | 251487.26 | a) | 01/01/18 | e) | - | a) | 251487.26 | a) | 100.00% | c) | 100% | a) | 12 | Completed as per physical accomplishment. | 2
| DAN | [7 empty] | b) | Gamad/Maligro | b) | 02/16/18 | f) | - | b) | 251487.26 | b) | - | d) | - | b) | 36 | Financial documents still on process | 2
| 136 | [7 empty] | c) | PEO | c) | 12/31/18 | g) | 12/31/18 | c) | 193,902.25 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Fd.Rd.3-San Jose Road |  |  | Road | 4.55 | CBRMC | a) | 140459.33 | a) | 01/01/18 | e) | - | a) | 140459.33 | a) | 100.00% | c) | 100% | a) | 2 | Completed as per physical accomplishment. | 2
| DAN | [7 empty] | b) | Gamad/Maligro | b) | 05/30/18 | f) | 05/30/18 | b) | 140459.33 | b) | - | d) | - | b) | 2 | Financial documents still on process | 2
| 136 | [7 empty] | c) | Brgy. San Jose Upland Farmers Assoc of Sto. Tomas, DDN, inc | c) |  | g) | - | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Fd.Rd.2-Sto.Tomas-Magwawa Road |  |  | Road | 10.21 | Admin | a) | 438,0.37.15 | a) | 01/01/18 | e) | - | a) | 438,0.37.15 | a) | 100.00% | c) | 100% | a) | 6 | Completed as per physical accomplishment. | 2
| DAN | [7 empty] | b) | Gamad/Maligro | b) | 01/22/18 | f) | - | b) | 438,0.37.15 | b) | - | d) | - | b) | 36 | Financial documents still on process | 2
| 137 | [7 empty] | c) | PEO | c) | 2018-12-31 | g) | 2018-12-31 | c) | 148,575.00 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Menzi-Balagunan-Tulalian Road |  |  | Road | 10.63 | Admin | a) | 631810.16 | a) | 01/01/18 | e) | - | a) | 631810.16 | a) | 100.00% | c) | 100% | a) | 12 | Completed as per physical accomplishment. | 2
| DAN | [7 empty] | b) | Gamad/Maligro | b) | 01/04/18 | f) | - | b) | 631810.16 | b) | - | d) | - | b) | 120 | Financial documents still on process | 2
| 138 | [7 empty] | c) | PEO | c) | 2018-12-31 | g) | 2018-12-31 | c) | 490,290.55 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Menzi-Balagunan-Tulalian Road |  |  | Road | 10.63 | CBRMC | a) | 382180.03 | a) | 01/01/18 | e) | - | a) | 382180.03 | a) | 100.00% | c) | 100% | a) | - | Completed as per physical accomplishment. | 2
| DAN | [7 empty] | b) | Gamad/Maligro | b) | 06/18/18 | f) | - | b) | 382180.03 | b) | - | d) | - | b) | - | Financial documents still on process | 2
| 138 | [7 empty] | c) | - | c) | 03/17/18 | g) | 03/17/18 | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | NAFCO-Bobongon Road |  |  | Road | 2.66 | Admin | a) | 261752.71 | a) | 01/01/18 | e) | - | a) | 261752.71 | a) | 100.00% | c) | 100% | a) | 14 | Completed as per physical accomplishment. | 2
| DAN | [7 empty] | b) | Gamad/Maligro | b) | 01/08/18 | f) | - | b) | 261752.71 | b) | - | d) | - | b) | 140 | Financial documents still on process | 2
| 139 | [7 empty] | c) | PEO | c) | 2018-12-31 | g) | 2018-12-31 | c) | 255,107.41 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Jct.Highway-Tanglaw Road |  |  | Road | 3.98 | Admin | a) | 369464.93 | a) | 01/01/18 | e) | - | a) | 369464.93 | a) | 100.00% | c) | 100% | a) |  | Completed as per physical accomplishment. | 2
| DAN | [7 empty] | b) | Gamad/Maligro | b) | 02/16/18 | f) | - | b) | 369464.93 | b) | - | d) | - | b) |  | Financial documents still on process | 2
| 142 | [7 empty] | c) | PEO | c) | 2018-12-31 | g) | 2018-12-31 | c) | 40,667.20 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Fd.Rd.3-Kimamon-Luna Road |  |  | Road | 11.76 | Admin | a) | 1073416.56 | a) | 01/01/18 | e) | - | a) | 1073416.56 | a) | 100.00% | c) | 100% | a) |  | Completed as per physical accomplishment. | 2
| DAN | [7 empty] | b) | Gamad/Maligro | b) | 01/04/18 | f) | - | b) | 1073416.56 | b) | - | d) | - | b) |  | Financial documents still on process | 2
| 143 | [7 empty] | c) | PEO | c) | 2018-12-31 | g) | 2018-12-31 | c) | 183,025.00 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Kimamon-Lunga-og-Talomo Road |  |  | Road | 5.99 | Admin | a) | 565379.82 | a) | 01/01/18 | e) | - | a) | 565379.82 | a) | 100.00% | c) | 100% | a) | 14 | Completed as per physical accomplishment. | 2
| DAN | [7 empty] | b) | Gamad/Maligro | b) | 01/03/18 | f) | - | b) | 565379.82 | b) | - | d) | - | b) | 140 | Financial documents still on process | 2
| 144 | [7 empty] | c) | PEO | c) | 2018-12-31 | g) | 2018-12-31 | c) | 555,350.22 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Jct.Bdry.Tagum-Talomo Road |  |  | Road | 12.01 | Admin | a) | 766269.09 | a) | 01/01/18 | e) | - | a) | 766269.09 | a) | 100.00% | c) | 100% | a) | 14 | Completed as per physical accomplishment. | 2
| DAN | [7 empty] | b) | Gamad/Maligro | b) | 01/03/18 | f) | - | b) | 766269.09 | b) | - | d) | - | b) | 140 | Financial documents still on process | 2
| 145 | [7 empty] | c) | PEO | c) | 2018-12-31 | g) | 2018-12-31 | c) | 759,363.83 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Jct.Bdry.Tagum-Talomo Road |  |  | Road | 12.01 | CBRMC | a) | 306326.59 | a) | 01/01/18 | e) | - | a) | 306326.59 | a) | 100.00% | c) | 100% | a) | - | Completed as per physical accomplishment. | 2
| DAN | [7 empty] | b) | Gamad/Maligro | b) | 11/28/18/ | f) | - | b) | 306326.59 | b) | - | d) | - | b) | - | Financial documents still on process | 2
| 145 | [7 empty] | c) | - | c) | 01/31/19 | g) | 12/27/18 | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Bdry.Tagum-Crossing Kinamayan- |  |  | Road | 19.16 | Admin | a) | 1499919.84 | a) | 01/01/18 | e) | - | a) | 1499919.84 | a) | 100.00% | c) | 100% | a) | 3 | Completed as per physical accomplishment. | 2
| DAN |  | Sto.Tomas Road | [5 empty] | b) | Gamad/Maligro | b) | 01/22/18 | f) | - | b) | 1499919.84 | b) | - | d) | - | b) | 12 | Financial documents still on process | 2
| 146 | [7 empty] | c) | PEO | c) | 2018-12-31 | g) | 2018-12-31 | c) | 956,472.04 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Prk.Daisy-Prk.Narafil Road |  |  | Road | 0.75 | Admin | a) | 11982.88 | a) | 01/01/18 | e) | - | a) | 11982.88 | a) | 100.00% | c) | 100% | a) |  | Completed as per physical accomplishment. | 2
| DAN | [7 empty] | b) | Gamad/Maligro | b) | 01/03/18 | f) | - | b) | 11982.88 | b) | - | d) | - | b) |  | Financial documents still on process | 2
| 148 | [7 empty] | c) | PEO | c) | 2018-12-31 | g) | 2018-12-31 | c) | 8,711.22 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Tuganay - Anibongan - San Isidro Road |  |  | Road | 6.73 | CBRMC | a) | 52,000.00 | a) | 01/01/18 | e) | - | a) | 52,000.00 | a) | 100.00% | c) | 100% | a) | 2 | Completed as per physical accomplishment. | 2
| DAN | [7 empty] | b) | Gamad/Maligro | b) | 11/19/18 | f) | - | b) | 52,000.00 | b) | - | d) | - | b) | 2 | Financial documents still on process | 2
| 091 | [7 empty] | c) | EZRA | c) | 02/04/19 | g) | 12/11/18 | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Dujali - Balisong - Magupising Road |  |  | Road | 6.73 | CBRMC | a) | 29,398.46 | a) | 01/01/18 | e) | - | a) | 29,398.46 | a) | 100.00% | c) | 100% | a) | 2 | Completed as per physical accomplishment. | 2
| DAN | [7 empty] | b) | Gamad/Maligro | b) | 05/04/18 | f) | - | b) | 29,398.46 | b) | - | d) | - | b) | 2 | Financial documents still on process | 2
| 091 | [7 empty] | c) | Duajli Pob. Farmers Irrigators | c) | 02/04/19 | g) | 12/11/18 | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
AC
|  |  | Rehabilitation / Improvement Of Various Local |  |  | Road | - | Admin | a) | 5000000 | [12 empty] | See projects listed below | AC
|  |  | Roads and Drainages | [5 empty] | b) | Paraguya | [13 empty] | AC
[9 empty] | c) | Admin | [13 empty] | AC
[9 empty] | d) | - | [13 empty] | AC
|  |  |  | Rehabilitation of Brgy. Tagbay Barangay |  | Road |  | Admin | a) | 138000 | a) | 04/25/18 | e) | - | a) | 138000 | a) | 100.00% | c) | 100.00% | a) | - | Completed as per physical accomplishment. | 2
|  |  |  | Road, IGACOS |  |  |  |  | b) | Porras/Pacquiao | b) | 12/05/18 | f) | - | b) | 138000 | b) | - | d) | - | b) | - | Financial documents still on process | 2
[9 empty] | c) | PEO | c) | 12/07/18 | g) | 12/07/18 | c) | - | [7 empty] | 2
[9 empty] | d) | - | [13 empty] | 2
|  |  |  | Rehabilitation of Brgy. San Jose Barangay |  | Road |  | Admin | a) | 138000 | a) | 04/25/18 | e) | - | a) | 138000 | a) | 100.00% | c) | 100.00% | a) | - | Completed as per physical accomplishment. | 2
|  |  |  | Road, IGACOS |  |  |  |  | b) | Porras/Pacquiao | b) | 10/27/18 | f) | - | b) | 138000 | b) | - | d) | - | b) | - | Financial documents still on process | 2
[9 empty] | c) | PEO | c) | 10/31/18 | g) | 10/31/18 | c) | - | [7 empty] | 2
[9 empty] | d) | - | [13 empty] | 2
|  |  |  | Rehabilitation of Brgy. Guilon Barangay |  | Road |  | Admin | a) | 138000 | a) | 04/25/18 | e) | - | a) | 138000 | a) | 100.00% | c) | 100.00% | a) | 3 | Completed as per physical accomplishment. | 2
|  |  |  | Road, IGACOS |  |  |  |  | b) | Porras/Pacquiao | b) | 01/10/19 | f) | - | b) | 138000 | b) | - | d) | - | b) | 30 | Financial documents still on process | 2
[9 empty] | c) | PEO | c) | 01/19/19 | g) | - | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  |  | Rehabilitation of Brgy. Del Monte Barangay |  | Road |  | Admin | a) | 138000 | a) | 04/25/18 | e) | - | a) | 138000 | a) | 100.00% | c) | 100.00% | a) | - | Completed as per physical accomplishment. | 2
|  |  |  | Road, IGACOS |  |  |  |  | b) | Porras/Pacquiao | b) | 12/12/18 | f) | - | b) | 138000 | b) | - | d) | - | b) | - | Financial documents still on process | 2
[9 empty] | c) | PEO | c) | 01/08/19 | g) | - | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  |  | Rehabilitation of Brgy. Tagbitan-ag |  | Road |  | Admin | a) | 138000 | a) | 04/25/18 | e) | 61 CD | a) | 138000 | a) | 100% | c) | 100% | a) | 5 | Completed as per physical accomplishment. | 2
|  |  |  | Barangay Road, IGACOS |  |  |  |  | b) | Porras/Pacquiao | b) | 02/15/19 | f) | 30 WD | b) | 138000 | b) | - | d) | - | b) | 45 | Financial documents still on process | 2
[9 empty] | c) | PEO | c) | 02/24/19 | g) | 03/15/19 | c) | 127356.84 | [7 empty] | 2
[9 empty] | d) | - | d) | 03/15/19 | [11 empty] | 2
|  |  |  | Rehabilitation of Brgy. Peñaplata Barangay |  | Road |  | Admin | a) | 139000 | a) | 04/25/18 | e) | 66 CD | a) | 139000 | a) | 100% | c) | 100 | a) | 1 | Completed 8/31/2019 | 2
|  |  |  | Road, IGACOS |  |  |  |  | b) | Porras/Pacquiao | b) | 8/16/2019 | f) | 225 CD | b) | 139000 | b) | - | d) | - | b) | 1 |  | 2
[9 empty] | c) | PEO | c) | 8/31/2019 | g) | - | c) | 139000 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  |  | Rehabilitation of Brgy. Pob. Kaputian |  | Road |  | Admin | a) | 138000 | a) | 04/25/18 | e) | - | a) | 138000 | a) | 100% | c) | 100% | a) | 4 |  | 2
|  |  |  | Barangay Road, IGACOS |  |  |  |  | b) | Porras/Pacquiao | b) | 2019-08-08 | f) | - | b) | 138000 | b) | - | d) | - | b) | 36 | Completed Sept. 22, 2019 | 2
[9 empty] | c) | PEO | c) | 9/22/2019 | g) | 9/22/2019 | c) | - | [7 empty] | 2
[9 empty] | d) | 6/13/19 | d) | - | [11 empty] | 2
|  |  |  | Rehabilitation of Brgy. Sto. NIño Barangay |  | Road |  | Admin | a) | 130000 | a) | 04/13/18 | e) | - | a) | 130000 | a) | 100.00% | c) | 100.00% | a) | 3 | Completed as per physical accomplishment. | 2
|  |  |  | Road, IGACOS |  |  |  |  | b) | Porras/Pacquiao | b) | 03/07/19 | f) | - | b) | 130000 | b) | - | d) | - | b) | 30 | Financial documents still on process | 2
[9 empty] | c) | PEO | c) | 03/16/19 | g) | 03/15/19 | c) | 107,972.00 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  |  | Rehabilitation of Brgy.Licup Barangay |  | Road |  | Admin | a) | 139000 | a) | 04/25/18 | e) | - | a) | 139000 | a) | 100.00% | c) | 100.00% | a) | 5 | Completed as per physical accomplishment. | 2
|  |  |  | Road, IGACOS |  |  |  |  | b) | Porras/Pacquiao | b) | 03/21/19 | f) | - | b) | 139000 | b) | - | d) | - | b) | 100 | Financial documents still on process | 2
[9 empty] | c) | PEO | c) | 03/29/19 | g) | 03/29/19 | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  |  | Rehabilitation of Brgy. Aundanao Barangay |  | Road |  | Admin | a) | 138000 | a) | 04/25/18 | e) | - | a) | 138000 | a) | 100.00% | c) | 100.00% | a) | 6 | Completed as per physical accomplishment. | 2
|  |  |  | Road, IGACOS |  |  |  |  | b) | Porras/Pacquiao | b) | 04/01/19 | f) | - | b) | 138000 | b) | - | d) | - | b) | 12 | Financial documents still on process | 2
[9 empty] | c) | PEO | c) | 04/09/19 | g) | 04/12/19 | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
4 |  |  |  | Rehabilitation of Brgy. Adecor Barangay |  | Road |  | Admin | a) | 138000 | a) | 04/25/18 | e) | 66 CD | a) | 138000 | a) | 60.00% | c) | 60.00% | a) | - | Completed as per POW. Financial Documents on process | 2
4 |  |  |  | Road, IGACOS |  |  |  |  | b) | Porras/Pacquiao | b) | 10/18/18 | f) | 225 CD | b) | 138000 | b) | - | d) | - | b) | - |  | 2
4 | [8 empty] | c) | PEO | c) | 10/27/19 | g) | - | c) | 111,872.00 | [7 empty] | 2
4 | [8 empty] | d) | - | d) | 10/15/2019 | [11 empty] | 2
|  |  | Water System Development Project | [20 empty] | AC
|  |  | Construction of Water System Projects in Component LGU's | [20 empty] | AC
|  |  |  | Impv't. of Water System, Brgy. Poblacion |  | Water |  | Admin | a) | 1250000 | a) | 08/24/18 | e) | - | a) | 1250000 | a) | 100% | c) | 85.39% | a) | 8 | Completed (contract by Zular3-Az) September 15, 2019 | AC
|  |  |  | Kaputian (Level II) |  | system |  |  | b) | Porras | b) | 05/3/19 | f) | - | b) | 1250000 | b) | - | d) | -14.61 | b) | 160 |  | AC
[9 empty] | c) | Contract | c) | 08/30/19 | g) | 09/15/2019 | c) | - | [7 empty] | AC
[9 empty] | d) | - | d) | - | [11 empty] | AC
|  |  | Const./Rehab./Comp. of Various Gov't. Bldgs. |  |  | Bldgs. | - | Admin | a) | 13523124 | [12 empty] | Investigation/Inspection of priority projects | AC
|  |  | Struct., Fac. (Provincewide) | [5 empty] | b) | Foronda | [13 empty] | AC
[9 empty] | c) | Admin | [13 empty] | AC
[9 empty] | d) | - | [13 empty] | AC
|  |  |  | Completion of PVO Bldg. (PVO Penthouse), |  | Bldgs. |  | Admin | a) | 1,500,000.00 | a) | 04/02/18 | e) | - | a) | 1,500,000.00 | a) | 100.00% | c) | 100.00% | a) | - | Completed as per physical accomplishment. | 1
|  |  |  | Gov't. Center, Mankilam |  |  |  |  | b) | Pasiona | b) | 09/03/18 | f) | - | b) | 1,500,000.00 | b) | - | d) | - | b) | - | Financial documents still on process | 1
[9 empty] | c) | Admin | c) | 12/01/18 | g) | 01/15/19 | c) | 1,052,849.49 | [7 empty] | 1
[9 empty] | d) | 90 CD | d) | - | [11 empty] | 1
1
|  |  |  | Construction of Multi-Purpose Bldg. |  | Bldg | 303.75 sq.m | Admin | a) | 6748000 | a) | 12/11/18 | e) | - | a) | 6748000 | a) |  | c) | 100% | a) | 25 | Completed | 1
|  |  |  | (PENRO Building), Mankilam, Tagum City |  |  |  |  | b) | Pasiona/Juan | b) | 10/16/18 | f) | 109 | b) | 6748000 | b) | - | d) |  | b) | 750 |  | 1
|  |  |  | (Part of 8,548,000.00) |  |  |  |  | c) | PEO | c) | 9/13/2019 | g) | - | c) | 6560497.45 | [7 empty] | 1
|  |  |  | (P1,800,000.00 - SB # 3 CY 2017) |  |  |  |  | d) | 256 CD | d) | 06/30/19 | [11 empty] | 1
4 |  |  |  | Repair/Rehab. Of PEO Building (2nd District), Carmen |  | Bldg |  | Admin | a) | 2250000 | a) | 08/10/18 | e) | - | a) | 2250000 | a) | 100% | c) | 100% | a) | 18 | Completed based on POW. Financial Documents on process | 2
4 | [8 empty] | b) | Andoy | b) | 02/18/19 | f) | - | b) | 2250000 | b) | - | d) | 0% | b) | 138 |  | 2
4 | [8 empty] | c) | Admin | c) | 08/23/19 | g) | - | c) | 1577344.8 | [7 empty] | 2
4 | [8 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | STIMULUS PROJECTS | [20 empty] | AC
|  |  | TAGUM CITY | [20 empty] | AC
|  |  |  | Construction of Brgy. GYM Bleacher, |  | Bleacher |  | Contract | a) | 500000 | a) | 06/05/18 | e) | - | a) | 500000 | a) | 100.00% | c) | 100.00% | a) | - | Completed as per physical accomplishment. | 1
|  |  |  | Pandapan, Tagum City |  |  |  |  | b) | Mayang | b) | 11/16/18 | f) | - | b) | 500000 | b) | - | d) | - | b) | - | Financial documents still on process | 1
[9 empty] | c) | FT Const. | c) | 01/15/19 | g) | 01/31/19 | c) | 417608 | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  |  | Repair of Brgy. Hall, San Miguel, |  | Bldg. |  | Admin | a) | 500000 | a) | 10/26/18 | e) | 13 | a) | 500000 | a) | 100% | c) | 100% | a) | 4 | Completed as per physical accomplishment. | 1
|  |  |  | Tagum City |  |  |  |  | b) | Mayang | b) | 03/04/19 | f) | 8 days | b) | 500000 | b) | - | d) | 0% | b) | 88 | Financial documents still on process | 1
[9 empty] | c) | Admin | c) | 05/23/19 | g) | 6/14/19 | c) | 411,905.79 | [7 empty] | 1
[9 empty] | d) | 50 CD | d) | - | [11 empty] | 1
4 |  |  |  | Completion of Two Storey Multi-Purpose |  | Bldg. |  | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | 100% | c) | 100% | a) | 5 | Completed based on Physical Accomplishment. Financial Documents on process | 1
4 |  |  |  | Building, Magugpo East, Tagum City |  |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | 0% | b) | 110 |  | 1
4 | [8 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 1
4 | [8 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | IGCS | [20 empty] | AC
|  |  | 1 | 1 | Const. of Public Toilet at Guilon, IGCS | Bldg. |  | Admin | a) | 500000 | a) | 07/05/18 | e) | - | a) | 500000 | a) | 100.00% | c) | 100% | a) | - | Completed as per physical accomplishment. | 2
[9 empty] | b) | - | b) | 12/31/17 | f) | - | b) | 500000 | b) | - | d) | - | b) | - | Financial documents still on process | 2
[9 empty] | c) | - | c) | 10/19/18 | g) | 10/19/18 | c) | 403,637.34 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | 2 | 2 | Impv't. of Brgy. Hall, Cawag, IGCS | Bldg. |  | Admin | a) | 500000 | a) | 07/19/18 | e) | - | a) | 500000 | a) | 100.00% | c) | 100.00% | a) | - | Completed as per physical accomplishment. | 2
[9 empty] | b) | Porras | b) | 09/04/18 | f) | - | b) | 500000 | b) | - | d) | - | b) | - | Financial documents still on process | 2
[9 empty] | c) | Admin | c) | 12/12/18 | g) | 12/12/18 | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | 3 | 3 | Improvement of Brgy. Hall, Kinawitnon, | Bldg. |  | Admin | a) | 500000 | a) | 07/05/18 | e) | - | a) | 500000 | a) | 100.00% | c) | 100.00% | a) | - | Completed as per physical accomplishment. | 2
[5 empty] | IGCS |  |  |  | b) | Roque | b) | 10/24/18 | f) | 19 days | b) | 500000 | b) | - | d) | - | b) | - | Financial documents still on process | 2
[9 empty] | c) | PEO | c) | 11/11/19 | g) | 01/11/19 | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | 4 | 4 | Const. of New Brgy. Hall, Adecor, IGCS | Bldg. |  | Contract | a) | 500000 | a) | 10/16/18 | e) | - | a) | 500000 | a) | 100.00% | c) | 100.00% | a) | - | Completed as per physical accomplishment. | 2
[9 empty] | b) | Porras | b) | 02/21/19 | f) | - | b) | 500000 | b) | - | d) | - | b) | - | Financial documents still on process | 2
[9 empty] | c) | Ecomixed | c) | 03/03/19 | g) | 03/03/19 | c) | 475414.3 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | 5 | 5 | Impv't. of Multi-Purpose Bldg. | Bldg. |  | Admin | a) | 500000 | a) | 07/05/18 | e) | - | a) | 500000 | a) | 100.00% | c) | 100.00% | a) | 7 | Completed as per physical accomplishment. | 2
[5 empty] | (Covered Court), Tagbitan-ag, IGCS |  |  |  | b) | Porras | b) | 12/31/17 | f) | - | b) | 500000 | b) | - | d) | - | b) | 35 | Financial documents still on process | 2
[9 empty] | c) | PEO | c) | 10/19/18 | g) | 03/08/19 | c) | 494,673.25 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
4 |  | L. | 5% Calamity Fund CY 2018 | [20 empty] | AC
4 |  |  | 1. Prevention and Mitigation | [20 empty] | AC
4 |  |  | 1.1 Desiltation/Excavation of rivers and creeks |  |  | rivers |  | Admin | a) | 3000000 | [12 empty] | Investigation/Inspection of priority projects | AC
4 | [8 empty] | b) | - | [13 empty] | AC
4 | [8 empty] | c) | PEO | [13 empty] | AC
4 | [8 empty] | d) | - | [13 empty] | AC
4 | [23 empty] | 1
4 |  |  | 1.1.1. | Improvement and Desiltation of Tagum Creek (Phase I and Phase II) |  | Creek |  | Admin | a) | 2,000,000.00 | a) | 11/06/18 | e) | - | a) | 2,000,000.00 | a) | 100% | c) | 100% | a) | 5 | Completed | 1
4 | [8 empty] | b) | Mayang | b) | 03/22/19 | f) | - | b) | 2,000,000.00 | b) | - | d) | 0% | b) | 110 |  | 1
4 | [8 empty] | c) | PEO | c) | 10/31/19 | g) | - | c) | - | [7 empty] | 1
4 | [8 empty] | d) | 224 CD | d) | - | [11 empty] | 1
|  | E. | SUPPLEMENTAL BUDGET # 1 CY 2018 | [5 empty] | a) | 6,000,000.00 | [12 empty] | See list of Provincial Roads | AC
|  |  | 1 Const./Impv't./Compl. Of School Buildings, | [20 empty] | AC
|  |  | Structures & Facilities | [20 empty] | AC
|  |  |  | Completion of Carmen Central E/S Gym |  | Gym |  | Admin | a) | 1000000 | a) | 07/31/18 | e) | - | a) | 1000000 | a) | 100.00% | c) | 100.00% | a) | 10 | Completed as per physical accomplishment. | 2
[9 empty] | b) | Estorco | b) | 12/07/18 | f) | - | b) | 1000000 | b) | - | d) | - | b) | 300 | Financial documents still on process | 2
[9 empty] | c) | PEO | c) | 04/19/19 | g) | - | c) | 818,875.12 | [7 empty] | 2
[9 empty] | d) | 130 CD | d) | - | [11 empty] | 2
|  |  |  | Const. of Dujali E/S Gym |  | Gym |  | Admin | a) | 2,109,662.99 | a) | 07/05/18 | e) | - | a) | 2,109,662.99 | a) | 100.00% | c) | 100.00% | a) | 4 | Completed as per physical accomplishment. | 2
[9 empty] | b) | Azotes | b) | 12/07/18 | f) | - | b) | 2,109,662.99 | b) | - | d) | - | b) | 88 | Financial documents still on process | 2
[9 empty] | c) | PEO | c) | 04/15/19 | g) | 04/01/19 | c) | 1,712,249.72 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | 1 Const. in Progress - Infrastructure | [5 empty] | b) | Paraguya | [13 empty] | AC
|  |  | Assets (Rehabilitation of Various | [5 empty] | c) | PEO | [13 empty] | AC
|  |  | Provincial Roads) | [5 empty] | d) | - | [13 empty] | AC
|  |  | 3 | a. | New Corella - New Sambog - Silangan | Road |  | Admin | a) | 2,095,000.00 | a) | 07/19/18 | e) | 71 CD | a) | 2,095,000.00 | a) | 100.00% | c) | 100.00% | a) | 3 | Completed as per physical accomplishment. | 1
[9 empty] | b) | Salido | b) | 10/08/18 | f) | 53 CD | b) | 2,095,000.00 | b) | - | d) | - | b) | 90 | Financial documents still on process | 1
[9 empty] | c) | PEO | c) | 11/07/18 | g) | 03/19/19 | c) | - | [7 empty] | 1
[9 empty] | d) | - | d) | 03/19/19 | [11 empty] | 1
|  |  | 1 | b | Bacali - Casig-ang - Libertad | Road |  | Admin | a) | 1,081,410.00 | a) | 07/31/18 | e) | - | a) | 1,081,410.00 | a) | 100.00% | c) | 100.00% | a) | - | Completed as per physical accomplishment. | 2
[9 empty] | b) | Toquero | b) | 10/23/18 | f) | - | b) | 1,081,410.00 | b) | - | d) | - | b) | - | Financial documents still on process | 2
[9 empty] | c) | PEO | c) | 11/30/18 | g) | 11/30/18 | c) | - | [7 empty] | 2
[9 empty] | d) | Admin | d) | - | [11 empty] | 2
|  |  | 1 | c | San Miguel - Moslog - Kinamayan | Road |  | Admin | a) | 704,740.00 | a) | 08/02/18 | e) | - | a) | 704,740.00 | a) | 100.00% | c) | 100.00% | a) | - | Completed as per physical accomplishment. | 2
[9 empty] | b) | Gamad | b) | 11/05/18 | f) | - | b) | 704,740.00 | b) | - | d) | - | b) | - | Financial documents still on process | 2
[9 empty] | c) | PEO | c) | 01/12/19 | g) | 01/12/19 | c) | - | [7 empty] | 2
[9 empty] | d) |  | d) | - | [11 empty] | 2
4 |  |  | OPPAP-PAMANA | [20 empty] | AC
|  |  | 1. Tribal Hall | [20 empty] | AC
|  |  |  | Construction of Tribal Hall, B.E. Dujali |  | Bldg. |  | Admin | a) | 500000 | a) | CY 2018 | e) | - | a) | 500000 | a) | 100% | c) | 100% | a) | 4 | Completed 5/31/2019 as per physical accomplishment. Financial Documents still on process | 2
[9 empty] | b) | Azotes | b) | 03/21/19 | f) | - | b) | 500000 | b) | - | d) | 0% | b) | 104 |  | 2
[9 empty] | c) | PEO | c) | 8/06/2019 | g) | 5/31/2019 | c) | 479480 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
1
1
|  |  |  | Construction of PWS Level II in Purok JBL and Salawao, |  | PWS |  | Admin | a) | 1000000 | a) | 08/15/18 | e) | - | a) | 1000000 | a) | 100.00% | c) | 100.00% | a) | 14 | Completed as per physical accomplishment. | 1
|  |  |  | Santo Niño, Talaingod |  |  |  |  | b) | Diosanta | b) | 12/17/18 | f) | 19 days | b) | 1000000 | b) | - | d) | - | b) | 420 | Financial documents still on process | 1
[9 empty] | c) | PEO | c) | 02/24/19 | g) | 03/15/19 | c) | 560706.67 | [7 empty] | 1
[9 empty] | d) | 89 CD | d) | 03/15/19 | [11 empty] | 1
4 |  | 4 |  | Upgrading of Existing PWS Level II in Sitio Patel 2, Gupitan, Kapalong |  | PWS |  | Admin | a) | 2500000 | a) | 8/14/2019 | e) | - | a) | 2500000 | a) |  | c) | 100% | a) | - | Completed as per Physical Accomplishment. Financial Documents on process | 1
4 | [8 empty] | b) | Diosanta | b) | 3/25/2019 | f) | - | b) | 2500000 | b) |  | d) |  | b) | - |  | 1
4 | [8 empty] | c) | PEO | c) | 7/19/2019 | g) | 09/30/2019 | c) | - | [7 empty] | 1
4 | [8 empty] | d) | - | d) | - | [11 empty] | 1
4 |  | R. | LOCAL GOVERNMENT SUPPORT FUND (LGSF) CY 2018 | [20 empty] | AC
4 |  |  | 1 | Road Upgrading of San Vicente - Butay Provincial Road |  | Road |  | Contract | a) | 19949581.18 | a) | CY 2018 | e) | - | a) | 19949581.18 | a) | 100% | c) | 100% | a) | 18 | Completed as per Physical Accomplishment. Financial Documents on process | 1
4 | [8 empty] | b) | Aclaracion | b) | 11/19/18 | f) | 28 CD | b) | 19949581.18 | b) | 100% | d) | 0% | b) | 396 |  | 1
4 | [8 empty] | c) | Alpha & Omega | c) | 06/08/19 | g) | 06/26/2019 | c) | 9,685,667.31 | [7 empty] | 1
4 | [8 empty] | d) | 202 CD | d) | 07/06/19 | [11 empty] | 1
|  | F. | Supplemental Budget No. 2 CY 2018 | [20 empty] | AC
|  |  | Const/Coml/Impvt of Various Gov't Bldgs., Structures | [20 empty] | AC
|  |  | & Facilities (Const. in Progress - Bldgs and Other Structures) | [20 empty] | AC
AC
|  |  |  | Const. of Provincial Training Center, Ph.II, |  | Bldg. |  | Admin | a) | 1,250,000.00 | a) | 07/05/18 | e) | - | a) | 1,250,000.00 | a) | 100.00% | c) | 100% | a) | 10 | Completed 6/28/2019 as per physical accomplishment. Financial Documents still on process | 2
|  |  |  | Brgy. Kinawitnon, IGACOS |  |  |  |  | b) | Porras | b) | 11/05/18 | f) | 63 CD | b) | 1,250,000.00 | b) | 100.00% | d) | 0% | b) | 200 |  | 2
[9 empty] | c) | PEO | c) | 12/23/18 | g) | 06/28/2019 | c) | 860,218.02 | [7 empty] | 2
[9 empty] | d) | 177 CD | d) | 04/30/19 | [11 empty] | 2
|  |  |  | Upgrading of DAGOEMC Multi-Purpose |  | Bldg. |  | - | a) | 3,000,000.00 | a) | 09/04/18 | e) | - | a) | 3,000,000.00 | a) | 30.28% | c) | 30.28% | a) | 7 | Completed as per physical accomplishment. | 1
|  |  |  | Bldg., Mankilam |  |  |  |  | b) | Chua | b) | 03/04/19 | f) | - | b) | 3,000,000.00 | b) | - | d) | +0.36% | b) | 210 | Financial documents still on process | 1
[9 empty] | c) | PEO | c) | 07/26/19 | g) | - | c) | 1,537,217.00 | [7 empty] | 1
[9 empty] | d) | 145 CD | d) | - | [11 empty] | 1
|  |  |  | Const. of 1 Unit Triball Hall, Brgy. Carcor, |  | Bldg. | 86.40 sq.m | Admin | a) | 680,000.00 | a) | 11/22/18 | e) | - | a) | 680,000.00 | a) | 100.00% | c) | 100.00% | a) | 16 | Completed as per physical accomplishment. | 1
|  |  |  | New Corella |  |  |  |  | b) | Gone | b) | 02/01/19 | f) | 14 CD | b) | 680,000.00 | b) | - | d) | - | b) | 160 | Financial documents still on process | 1
[9 empty] | c) | PEO | c) | 04/01/19 | g) | 04/15/19 | c) | 551,946.14 | [7 empty] | 1
[9 empty] | d) | - | d) | 04/15/19 | [11 empty] | 1
|  |  |  | Const/Compl. Of Fence at bahay |  | Fence |  | - | a) | 2,500,000.00 | a) | 08/28/18 | e) | - | a) | 2,500,000.00 | a) | 100.00% | c) | 100.00% | a) | 17 | Completed as per physical accomplishment. | 1
|  |  |  | Pag-Asa for Minors, New Corella |  |  |  |  | b) | Gone | b) | 01/19/19 | f) | 20 CD | b) | 2,500,000.00 | b) | - | d) | - | b) | 323 | Financial documents still on process | 1
[9 empty] | c) | PEO | c) | 03/06/19 | g) | 05/25/19 | c) | 2,150,422.85 | [7 empty] | 1
[9 empty] | d) | 110 CD | d) | 05/25/19 | [11 empty] | 1
|  |  | 2 Infastructure Augmentation Project (Provincial Counterpart for PRDP Project) | [20 empty] | AC
AC
|  |  |  | Rehab. Of Capungagan-Bdy. San Miguel |  | Road |  | Admin | a) | 4,990,000.000 | a) | 07/20/18 | e) | - | a) | 4,990,000.000 | a) | 100.00% | c) | 100.00% | a) | 6 | Completed as per physical accomplishment. | 1
|  |  |  | FMR (Variation Order) |  |  |  |  | b) | Avila | b) | 08/23/18 | f) | 86 CD | b) | 4,990,000.000 | b) | - | d) | - | b) | 180 | Financial documents still on process | 1
[9 empty] | c) | PEO | c) | 01/13/19 | g) | 03/30/19 | c) | 4879151.58 | [7 empty] | 1
[9 empty] | d) | 134 CD | d) | 03/30/19 | [11 empty] | 1
| II. PROJECTS UNDER THE CURRENT APPROPRIATION CY 2019 | [22 empty] | AP
| A.1 GENERAL FUND CY 2019 | [6 empty] | MBA/CBRMC | a) | 18127866 | a) | 01/03/19 | e) | - | a) | 18127866 | a) | 83.63 | c) | 83.83 | a) | 46 | See list of Provincial Roads | AP
| Road ID |  | Maintenance of Various Provincial Roads and Bridges at District 1 |  |  | Road Maintenance | KM |  | b) | Paraguya | b) | 01/03/19 | f) | - | b) | 18127866 | b) | - | d) | - | b) | 920 |  | FS
[7 empty] | 288.26 |  | c) | PEO/CBRMC | c) | 12/31/19 | g) | - | c) | - | [7 empty] | AC
| 11DAN | [9 empty] | d) | - | [11 empty] | AC
[9 empty] | d) | 261 days | d) | - | [11 empty] | AC
|  |  | Jct. Highway Magatos - New Bantayan |  |  | Road Maintenance | 7.1 | MBA | a) | 287307.39 | a) | 01/03/19 | e) | - | a) | 287307.39 | a) | 100% | c) | 100% | a) | 15 | Completed | AC
| 001 | [7 empty] | b) | Crucio | b) | 01/16/19 | f) | - | b) | 287307.39 | b) | - | d) | - | b) | 480 |  | 1
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 118693.58 | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | Jct. Highway Magatos - New Bantayan |  |  | Road Maintenance | 7.1 | CBRMC | a) | 223674.22 | a) | 01/03/19 | e) | - | a) | 223674.22 | a) | 100% | c) | 100% | a) | 16 | Completed | 1
| 001 | [7 empty] | b) | Crucio | b) | 3/22/19 | f) | - | b) | 223674.22 | b) | - | d) | - | b) | 480 |  | 1
[9 empty] | c) | CALAFA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
|  |  | Magatos-Bdry Pagsabangan |  |  | Road Maintenance | 8.33 | MBA | a) | 328740.25 | a) | 01/03/19 | e) | - | a) | 328740.25 | a) | 100% | c) | 100% | a) | 15 | Completed | 1
| 002 | [7 empty] | b) | Crucio | b) | 01/03/19 | f) | - | b) | 328740.25 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 207258.49 | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | Magatos-Bdry Pagsabangan |  |  | Road Maintenance | 8.33 | CBRMC | a) | 270763.53 | a) | 01/03/19 | e) | - | a) | 270763.53 | a) | 100% | c) | 100% | a) | 16 | Completed | 1
| 002 | [7 empty] | b) | Crucio | b) | 03/22/19 | f) | - | b) | 270763.53 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | CALAFA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
|  |  | Ilog-New Bantayan |  |  | Road Maintenance | 2.68 | MBA | a) | 131131.39 | a) | 01/03/19 | e) | - | a) | 131131.39 | a) | 100% | c) | 100% | a) | 15 | Completed | 1
| 003 | [7 empty] | b) | Crucio | b) | 01/16/19 | f) | - | b) | 131131.39 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 49,316.69 | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | Ilog-New Bantayan |  |  | Road Maintenance | 2.68 | CBRMC | a) | 65925.03 | a) | 01/03/19 | e) | - | a) | 65925.03 | a) | 100% | c) | 100% | a) | 16 | Completed | 1
| 003 | [7 empty] | b) | Crucio | b) | 03/22/19 | f) | - | b) | 65925.03 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | CALAFA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
|  |  | Asuncion -Monte Carlo-Del Pilar |  |  | Road Maintenance | 9.93 | MBA | a) | 474102.88 | a) | 01/03/19 | e) | - | a) | 474102.88 | a) | 100% | c) | 100% | a) | 15 | Completed | 1
| 005 | [7 empty] | b) | Crucio | b) | 01/03/19 | f) | - | b) | 474102.88 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 240274.49 | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | Asuncion -Monte Carlo-Del Pilar |  |  | Road Maintenance | 9.93 | CBRMC | a) | 355524.28 | a) | 01/03/19 | e) | - | a) | 355524.28 | a) | 100% | c) | 100% | a) | 16 | Completed
| 005 | [7 empty] | b) | Crucio | b) | 03/22/19 | f) | - | b) | 355524.28 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | MAHAYAHAY IFA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
|  |  | Jct. Highway Canatan-Jct. Highway Magatos |  |  | Road Maintenance | 4.85 | MBA | a) | 209808.59 | a) | 01/03/19 | e) | - | a) | 209808.59 | a) | 100% | c) | 100% | a) | 15 | Completed | 1
| 006 | [7 empty] | b) | Crucio | b) | 02/18/19 | f) | - | b) | 209808.59 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 80652.8 | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | Jct. Highway Canatan-Jct. Highway Magatos |  |  | Road Maintenance | 4.85 | CBRMC | a) | 162458.12 | a) | 01/03/19 | e) | - | a) | 162458.12 | a) | 100% | c) | 100% | a) | 16 | Completed | 1
| 006 | [7 empty] | b) | Crucio | b) | 03/22/19 | f) | - | b) | 162458.12 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | CAMODA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
1
|  |  | Sta. Felomina-San Roque |  |  | Road Maintenance | 7.68 | MBA | a) | 147439.63 | a) | 01/03/19 | e) | - | a) | 147439.63 | a) | 100% | c) | 100% | a) | 15 | Completed
| 008 | [7 empty] | b) | Crucio | b) | 01/16/19 | f) | - | b) | 147439.63 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 63806.67 | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | Sta. Felomina-San Roque |  |  | Road Maintenance | 7.68 | CBRMC | a) | 261345.67 | a) | 01/03/19 | e) | - | a) | 261345.67 | a) | 100% | c) | 100% | a) | 16 | Completed | 1
| 008 | [7 empty] | b) | Crucio | b) | 03/25/19 | f) | - | b) | 261345.67 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | STAFFA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
|  |  | Saug-Sonlon-Bdy Longanapan |  |  | Road Maintenance | 11.6 | MBA | a) | 568486.36 | a) | 01/03/19 | e) | - | a) | 568486.36 | a) | 100% | c) | 100% | a) | 15 | Completed | 1
| 010 | [7 empty] | b) | Crucio | b) | 01/16/19 | f) | - | b) | 568486.36 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 262900.22 | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | Saug-Sonlon-Bdy Longanapan |  |  | Road Maintenance | 11.6 | CBRMC | a) | 185565.56 | a) | 01/03/19 | e) | - | a) | 185565.56 | a) | 100% | c) | 100% | a) | 16 | Completed | 1
| 010 | [7 empty] | b) | Crucio | b) | 03/26/19 | f) | - | b) | 185565.56 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | BINANCIAN LIVESTOCK AFA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
|  |  | Jct. New Visayas-Buan |  |  | Road Maintenance | 2.99 | MBA | a) | 79238.27 | a) | 01/03/19 | e) | - | a) | 79238.27 | a) | 100% | c) | 100% | a) | 15 | Completed | 1
| 011 | [7 empty] | b) | Crucio | b) | 02/18/19 | f) | - | b) | 79238.27 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 14682.85 | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | Jct. New Visayas-Buan |  |  | Road Maintenance | 2.99 | CBRMC | a) | 101242.01 | a) | 01/03/19 | e) | - | a) | 101242.01 | a) | 100% | c) | 100% | a) | 16 | Completed | 1
| 011 | [7 empty] | b) | Crucio | b) | 03/22/19 | f) | - | b) | 101242.01 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | BUAN IFA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
|  |  | San Vicente - Butay |  |  | Road Maintenance | 7.52 | MBA | a) | 209624.2 | a) | 01/03/19 | e) | - | a) | 209624.2 | a) | 100% | c) | 100% | a) | 15 | Completed | 1
| 013 | [7 empty] | b) | Crucio | b) | 02/18/19 | f) | - | b) | 209624.2 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 56,080.29 | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | San Vicente - Butay |  |  | Road Maintenance | 7.52 | CBRMC | a) | 227205.88 | a) | 01/03/19 | e) | - | a) | 227205.88 | a) | 100% | c) | 100% | a) | 16 | Completed | 1
| 013 | [7 empty] | b) | Crucio | b) | 03/27/19 | f) | - | b) | 227205.88 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | SVMODA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
|  |  | Jct. Highway Doña Andrea - Capungagan |  |  | Road Maintenance | 8.7 | MBA | a) | 230835.16 | a) | 01/03/19 | e) | - | a) | 230835.16 | a) | 100% | c) | 100% | a) | 15 | Completed | 1
| 014 | [7 empty] | b) | Crucio | b) | 02/18/19 | f) | - | b) | 230835.16 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 60,629.26 | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
1
|  |  | Jct. Highway Doña Andrea - Capungagan |  |  | Road Maintenance | 8.7 | CBRMC | a) | 294308.14 | a) | 01/03/19 | e) | - | a) | 294308.14 | a) | 100% | c) | 100% | a) | 16 | Completed
| 014 | [7 empty] | b) | Crucio | b) | 03/28/19 | f) | - | b) | 294308.14 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | CAPUNGAGAN MPC | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
|  |  | Semong-Palma Gil |  |  | Road Maintenance | 2.73 | MBA | a) | 147289.98 | a) | 01/03/19 | e) | - | a) | 147289.98 | a) | 100% | c) | 100% | a) | 15 | Completed | 1
| 018 | [7 empty] | b) | Crucio | b) | 02/18/19 | f) | - | b) | 147289.98 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 71745.43 | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
1
|  |  | Semong-Palma Gil |  |  | Road Maintenance | 2.73 | CBRMC | a) | 49186.05 | a) | 01/03/19 | e) | - | a) | 49186.05 | a) | 100% | c) | 100% | a) | 16 | Completed
| 018 | [7 empty] | b) | Crucio | b) | 03/22/19 | f) | - | b) | 49186.05 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | PALMA GIL FA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
|  |  | Daligdigon - Dagohoy |  |  | Road Maintenance | 3.34 | MBA | a) | 148835.45 | a) | 01/03/19 | e) | - | a) | 148835.45 | a) | 100% | c) | 100% | a) | - | Completed | 1
| 020 | [7 empty] | b) | Crucio | b) | - | f) | - | b) | 148835.45 | b) | - | d) | - | b) | - |  | 1
[9 empty] | c) | PEO | c) | - | g) | 2019-12-31 | c) | - | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | Daligdigon - Dagohoy |  |  | Road Maintenance | 3.34 | CBRMC | a) | 68279.5 | a) | 01/03/19 | e) | - | a) | 68279.5 | a) | 100% | c) | 100% | a) | 16 | Completed | 1
| 020 | [7 empty] | b) | Crucio | b) | 03/22/19 | f) | - | b) | 68279.5 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | PALMA GIL FA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
|  |  | Jct. Sampao-Bdry. Mamacao |  |  | Road Maintenance | 4.98 | MBA | a) | 154200.78 | a) | 01/03/19 | e) | - | a) | 154200.78 | a) | 100% | c) | 100% | a) | 15 | Completed | 1
| 025 | [7 empty] | b) | Crucio | b) | 02/18/19 | f) | - | b) | 154200.78 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 24,296.87 | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | Jct. Sampao-Bdry. Mamacao |  |  | Road Maintenance | 4.98 | CBRMC | a) | 169521.51 | a) | 01/03/19 | e) | - | a) | 169521.51 | a) | 100% | c) | 100% | a) | 16 | Completed | 1
| 025 | [7 empty] | b) | Crucio | b) | 03/26/19 | f) | - | b) | 169521.51 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | AMS KAPALONG | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
|  |  | Jct. Highway Luna-Mamacao-Narra |  |  | Road Maintenance | 9.17 | MBA | a) | 357957.66 | a) | 01/03/19 | e) | - | a) | 357957.66 | a) | 100% | c) | 100% | a) | 15 | Completed | 1
| 026 | [7 empty] | b) | Crucio | b) | 02/18/19 | f) | - | b) | 357957.66 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 127,996.16 | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | Jct. Highway Luna-Mamacao-Narra |  |  | Road Maintenance | 9.17 | CBRMC | a) | 313143.91 | a) | 01/03/19 | e) | - | a) | 313143.91 | a) | 100% | c) | 100% | a) | 16 | Completed | 1
| 026 | [7 empty] | b) | Crucio | b) | 03/26/19 | f) | - | b) | 313143.91 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | AMS KAPALONG | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
|  |  | Jct. Gabuyan-Katipunan-Bucana |  |  | Road Maintenance | 5.89 | MBA | a) | 294403.23 | a) | 01/03/19 | e) | - | a) | 294403.23 | a) | 100% | c) | 100% | a) | 15 | Completed | 1
| 027 | [7 empty] | b) | Crucio | b) | 02/18/19 | f) | - | b) | 294403.23 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 126,179.97 | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | Jct. Gabuyan-Katipunan-Bucana |  |  | Road Maintenance | 5.89 | CBRMC | a) | 129495.6 | a) | 01/03/19 | e) | - | a) | 129495.6 | a) | 100% | c) | 100% | a) | 16 | Completed | 1
| 027 | [7 empty] | b) | Crucio | b) | 03/26/19 | f) | - | b) | 129495.6 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | MANGULIBAS FA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
|  |  | Capungagan-Mabuhay-Pandulian |  |  | Road Maintenance | 5.57 | MBA | a) | 294917.73 | a) | 01/03/19 | e) | - | a) | 294917.73 | a) | 100% | c) | 100% | a) | 15 | Completed | 1
| 028 | [7 empty] | b) | Crucio | b) | 02/18/19 | f) | - | b) | 294917.73 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
1
|  |  | Capungagan-Mabuhay-Pandulian |  |  | Road Maintenance | 5.57 | CBRMC | a) | 105950.95 | a) | 01/03/19 | e) | - | a) | 105950.95 | a) | 100% | c) | 100% | a) | 16 | Completed
| 028 | [7 empty] | b) | Crucio | b) | 03/28/19 | f) | - | b) | 105950.95 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | CAPUNGAGAN MPC | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
|  |  | Florida - New Boholano |  |  | Road Maintenance | 2.54 | MBA | a) | 95863.17 | a) | 01/03/19 | e) | - | a) | 95863.17 | a) | 100% | c) | 100% | a) | 15 | Completed | 1
| 030 | [7 empty] | b) | Crucio | b) | 02/18/19 | f) | - | b) | 95863.17 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 31,418.99 | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | Florida - New Boholano |  |  | Road Maintenance | 2.54 | CBRMC | a) | 47425.27 | a) | 01/03/19 | e) | - | a) | 47425.27 | a) | 100% | c) | 100% | a) | 16 | Completed | 1
| 030 | [7 empty] | b) | Crucio | b) | 03/28/19 | f) | - | b) | 47425.27 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | SUPRA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
|  |  | Jct. New Boholano - New Loon |  |  | Road Maintenance | 4.77 | MBA | a) | 140549.84 | a) | 01/03/19 | e) | - | a) | 140549.84 | a) | 100% | c) | 100% | a) | 15 | Completed | 1
| 031 | [7 empty] | b) | Crucio | b) | 02/18/19 | f) | - | b) | 140549.84 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 40,056.38 | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | Jct. New Boholano - New Loon |  |  | Road Maintenance | 4.77 | CBRMC | a) | 169521.51 | a) | 01/03/19 | e) | - | a) | 169521.51 | a) | 100% | c) | 100% | a) | 16 | Completed | 1
| 031 | [7 empty] | b) | Crucio | b) | 03/28/19 | f) | - | b) | 169521.51 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | NEW LOON FA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
|  |  | Florida-Suaon-Jct. Gupitan |  |  | Road Maintenance | 15.57 | MBA | a) | 707038.05 | a) | 01/03/19 | e) | - | a) | 707038.05 | a) | 100% | c) | 100% | a) | 15 | Completed | 1
| 032 | [7 empty] | b) | Crucio | b) | 01/16/19 | f) | - | b) | 707038.05 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 226,.062.60 | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | Florida-Suaon-Jct. Gupitan |  |  | Road Maintenance | 15.57 | CBRMC | a) | 419094.85 | a) | 01/03/19 | e) | - | a) | 419094.85 | a) | 100% | c) | 100% | a) | 16 | Completed | 1
| 032 | [7 empty] | b) | Crucio | b) | 03/28/19 | f) | - | b) | 419094.85 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | SUPRA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
|  |  | Km. 15, Kipalili-New Loon |  |  | Road Maintenance | 6.93 | MBA | a) | 367659.97 | a) | 01/03/19 | e) | - | a) | 367659.97 | a) | 100% | c) | 100% | a) | 15 | Completed | 1
| 034 | [7 empty] | b) | Crucio | b) | 02/01/19 | f) | - | b) | 367659.97 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 112,175.78 | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | Km. 15, Kipalili-New Loon |  |  | Road Maintenance | 6.93 | CBRMC | a) | 237801.01 | a) | 01/03/19 | e) | - | a) | 237801.01 | a) | 100% | c) | 100% | a) | 16 | Completed | 1
| 034 | [7 empty] | b) | Crucio | b) | 03/26/19 | f) | - | b) | 237801.01 | b) | - | d) | - | b) | 480 |  | 1
[9 empty] | c) | KIPALILI FA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
|  |  | Jct. Suaon-Libuton |  |  | Road Maintenance | 7.26 | MBA | a) | 44015.68 | a) | 01/03/19 | e) | - | a) | 44015.68 | a) | 100% | c) | 100% | a) | 15 | Completed
| 035 | [7 empty] | b) | Crucio | b) | 01/16/19 | f) | - | b) | 44015.68 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 24,980.86 | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | Jct. Suaon-Libuton |  |  | Road Maintenance | 7.26 | CBRMC | a) | 91664.91 | a) | 01/03/19 | e) | - | a) | 91664.91 | a) | 100% | c) | 100% | a) | 16 | Completed | 1
| 035 | [7 empty] | b) | Crucio | b) | 03/22/19 | f) | - | b) | 91664.91 | b) | - | d) | - | b) | 480 |  | 1
[9 empty] | c) | AALLI | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
1
|  |  | Datu Balong - Pinamuno |  |  | Road Maintenance | 2.74 | MBA | a) | 95458.24 | a) | 01/03/19 | e) | - | a) | 95458.24 | a) | 100% | c) | 100% | a) | 15 | Completed
| 040 | [7 empty] | b) | Crucio | b) | 03/01/19 | f) | - | b) | 95458.24 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 12,625.00 | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | Datu Balong - Pinamuno |  |  | Road Maintenance | 2.74 | CBRMC | a) | 63570.57 | a) | 01/03/19 | e) | - | a) | 63570.57 | a) | 100% | c) | 100% | a) | 16 | Completed | 1
| 040 | [7 empty] | b) | Crucio | b) | 03/28/19 | f) | - | b) | 63570.57 | b) | - | d) | - | b) | 480 |  | 1
[9 empty] | c) | DATU BALONG FA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
|  |  | Sawata - Mamangan - Pinamuno |  |  | Road Maintenance | 14.48 | MBA | a) | 545390.17 | a) | 01/03/19 | e) | - | a) | 545390.17 | a) | 100% | c) | 100% | a) | 15 | Completed | 1
| 041 | [7 empty] | b) | Crucio | b) | 02/01/19 | f) | - | b) | 545390.17 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 196,076.60 | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | Sawata - Mamangan - Pinamuno |  |  | Road Maintenance | 14.48 | CBRMC | a) | 508564.54 | a) | 01/03/19 | e) | - | a) | 508564.54 | a) | 100% | c) | 100% | a) | 16 | Completed | 1
| 041 | [7 empty] | b) | Crucio | b) | 03/22/19 | f) | - | b) | 508564.54 | b) | - | d) | - | b) | 480 |  | 1
[9 empty] | c) | SAWATA DFA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
|  |  | Igangon - Sawata |  |  | Road Maintenance | 9.66 | MBA | a) | 497447.77 | a) | 01/03/19 | e) | - | a) | 497447.77 | a) | 100% | c) | 100% | a) | 15 | Completed | 1
| 042 | [7 empty] | b) | Crucio | b) | 02/01/19 | f) | - | b) | 497447.77 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | Igangon - Sawata |  |  | Road Maintenance | 9.66 | CBRMC | a) | 197775.1 | a) | 01/03/19 | e) | - | a) | 197775.1 | a) | 100% | c) | 100% | a) | 16 | Completed | 1
| 042 | [7 empty] | b) | Crucio | b) | 03/22/19 | f) | - | b) | 197775.1 | b) | - | d) | - | b) | 480 |  | 1
[9 empty] | c) | SAWATA DFA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
|  |  | New Corella - Sto. Niño - Macgum |  |  | Road Maintenance | 17.11 | MBA | a) | 606294.08 | a) | 01/03/19 | e) | - | a) | 606294.08 | a) | 100% | c) | 100% | a) | 15 | Completed | 1
| 044 | [7 empty] | b) | Crucio | b) | 01/03/19 | f) | - | b) | 606294.08 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 246,619.77 | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | New Corella - Sto. Niño - Macgum |  |  | Road Maintenance | 17.11 | CBRMC | a) | 308434.97 | a) | 01/03/19 | e) | - | a) | 308434.97 | a) | 100% | c) | 100% | a) | 16 | Completed | 1
| 044 | [7 empty] | b) | Crucio | b) | 03/26/19 | f) | - | b) | 308434.97 | b) | - | d) | - | b) | 480 |  | 1
[9 empty] | c) | SAN ISIDRO FA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
|  |  | Tagaytay - Buan |  |  | Road Maintenance | 4.92 | MBA | a) | 173197.37 | a) | 01/03/19 | e) | - | a) | 173197.37 | a) | 100% | c) | 100% | a) | 15 | Completed | 1
| 045 | [7 empty] | b) | Crucio | b) | 03/18/19 | f) | - | b) | 173197.37 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 26254.58 | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | Tagaytay - Buan |  |  | Road Maintenance | 4.92 | CBRMC | a) | 131850.07 | a) | 01/03/19 | e) | - | a) | 131850.07 | a) | 100% | c) | 100% | a) | 16 | Completed | 1
| 045 | [7 empty] | b) | Crucio | b) | 03/22/19 | f) | - | b) | 131850.07 | b) | - | d) | - | b) | 480 |  | 1
[9 empty] | c) | BUAN IFA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
|  |  | limbaan - Sto. Niño |  |  | Road Maintenance | 3.19 | MBA | a) | 153706.77 | a) | 01/03/19 | e) | - | a) | 153706.77 | a) | 100% | c) | 100% | a) | 15 | Completed | 1
| 049 | [7 empty] | b) | Crucio | b) | 03/01/19 | f) | - | b) | 153706.77 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 32534.49 | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | limbaan - Sto. Niño |  |  | Road Maintenance | 3.19 | CBRMC | a) | 53657.51 | a) | 01/03/19 | e) | - | a) | 53657.51 | a) | 100% | c) | 100% | a) | - | Completed | 1
| 049 | [7 empty] | b) | Crucio | b) | - | f) | - | b) | 53657.51 | b) | - | d) | - | b) | - |  | 1
[9 empty] | c) | - | c) | - | g) | 2019-12-31 | c) | - | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | Del Pilar - Jct. Silangan |  |  | Road Maintenance | 4.17 | MBA | a) | 187097.4 | a) | 01/03/19 | e) | - | a) | 187097.4 | a) | 100% | c) | 100% | a) | 15 | Completed | 1
| 051 | [7 empty] | b) | Crucio | b) | 03/18/19 | f) | - | b) | 187097.4 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 94181.74 | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | Del Pilar - Jct. Silangan |  |  | Road Maintenance | 4.17 | CBRMC | a) | 113014.34 | a) | 01/03/19 | e) | - | a) | 113014.34 | a) | 100% | c) | 100% | a) | 16 | Completed | 1
| 051 | [7 empty] | b) | Crucio | b) | 03/26/19 | f) | - | b) | 113014.34 | b) | - | d) | - | b) | 480 |  | 1
[9 empty] | c) | DURIAN DACUDAO | c) | 12/31/19 | g) | - | c) | - | [7 empty] | 1
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
|  |  | New Corella - New Sambog - Silangan |  |  | Road Maintenance | 5.1 | MBA | a) | 201994.35 | a) | 01/03/19 | e) | - | a) | 201994.35 | a) | 100% | c) | 100% | a) | 15 | Completed | 1
| 052 | [7 empty] | b) | Crucio | b) | 03/01/19 | f) | - | b) | 201994.35 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 63402.48 | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | New Corella - New Sambog - Silangan |  |  | Road Maintenance | 5.1 | CBRMC | a) | 131850.07 | a) | 01/03/19 | e) | - | a) | 131850.07 | a) | 100% | c) | 100% | a) | 16 | Completed | 1
| 052 | [7 empty] | b) | Crucio | b) | 03/26/19 | f) | - | b) | 131850.07 | b) | - | d) | - | b) | 480 |  | 1
[9 empty] | c) | DURIAN DACUDAO | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
|  |  | Sta. Fe - Del Monte |  |  | Road Maintenance | 3.34 | MBA | a) | 37923.51 | a) | 01/03/19 | e) | - | a) | 37923.51 | a) | 100% | c) | 100% | a) | 15 | Completed | 1
| 056 | [7 empty] | b) | Crucio | b) | 03/18/19 | f) | - | b) | 37923.51 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 36595.13 | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | Sta. Fe - Del Monte |  |  | Road Maintenance | 3.34 | CBRMC | a) | 70633.96 | a) | 01/03/19 | e) | - | a) | 70633.96 | a) | 100% | c) | 100% | a) | 16 | Completed | 1
| 056 | [7 empty] | b) | Crucio | b) | 03/21/19 | f) | - | b) | 70633.96 | b) | - | d) | - | b) | 480 |  | 1
[9 empty] | c) | DEL MONTE CACAO | c) | 12/31/19 | g) | 2019-12-31 | c) | 4,872.18 | [7 empty] | 1
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
|  |  | New Corella - New Bohol |  |  | Road Maintenance | 11.54 | MBA | a) | 356226.67 | a) | 01/03/19 | e) | - | a) | 356226.67 | a) | 100% | c) | 100% | a) | 15 | Completed
| 058 | [7 empty] | b) | Crucio | b) | 02/01/19 | f) | - | b) | 356226.67 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 110,982.71 | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | New Corella - New Bohol |  |  | Road Maintenance | 11.54 | CBRMC | a) | 190711.7 | a) | 01/03/19 | e) | - | a) | 190711.7 | a) | 100% | c) | 100% | a) | 16 | Completed | 1
| 058 | [7 empty] | b) | Crucio | b) | 03/22/19 | f) | - | b) | 190711.7 | b) | - | d) | - | b) | 480 |  | 1
[9 empty] | c) | SAN JOSE COCONUT | c) | 12/31/19 | g) | 2019-12-31 | c) | 5,847.18 | [7 empty] | 1
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
1
|  |  | Jct. Carcor - Prk. 9 Bagsak |  |  | Road Maintenance | 2.5 | MBA | a) | 108618.49 | a) | 01/03/19 | e) | - | a) | 108618.49 | a) | 100% | c. | 100% | a) | 15 | Completed
| 059 | [7 empty] | b) | Crucio | b) | 03/01/19 | f) | - | b) | 108618.49 | b) | - | d) |  | b) | 480 |  | 1
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 79952.88 | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
1
|  |  | Jct. Carcor - Prk. 9 Bagsak |  |  | Road Maintenance | 2.5 | CBRMC | a) | 42284.76 | a) | 01/03/19 | e) | - | a) | 42284.76 | a) | 100% | c) | 100% | a) | 16 | Completed
| 059 | [7 empty] | b) | Crucio | b) | 03/22/19 | f) | - | b) | 42284.76 | b) | - | d) | - | b) | 480 |  | 1
[9 empty] | c) | CARCOR MOTOR | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
|  |  | Carcor - Jct. Kauswagan |  |  | Road Maintenance | 4.32 | MBA | a) | 264514.71 | a) | 01/03/19 | e) | - | a) | 264514.71 | a) | 100% | c) | 100% | a) | 15 | Completed | 1
| 060 | [7 empty] | b) | Crucio | b) | 03/18/19 | f) | - | b) | 264514.71 | b) | - | d) |  | b) | 450 |  | 1
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 80733.11 | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | Carcor - Jct. Kauswagan |  |  | Road Maintenance | 4.32 | CBRMC | a) | 48398.27 | a) | 01/03/19 | e) | - | a) | 48398.27 | a) | 100% | c) | 100% | a) | 16 | Completed
| 060 | [7 empty] | b) | Crucio | b) | 03/22/19 | f) | - | b) | 48398.27 | b) | - | d) | - | b) | 480 |  | 1
[9 empty] | c) | CARCOR MOTOR | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
|  |  | Del Pilar - Prk 9 Bagsak - San Jose |  |  | Road Maintenance | 4.99 | MBA | a) | 170215.76 | a) | 01/03/19 | e) | - | a) | 170215.76 | a) | 100% | c) | 100% | a) | 15 | Completed | 1
| 061 | [7 empty] | b) | Crucio | b) | 03/01/19 | f) | - | b) | 170215.76 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 87595.63 | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | Del Pilar - Prk 9 Bagsak - San Jose |  |  | Road Maintenance | 4.99 | CBRMC | a) | 223674.22 | a) | 01/03/19 | e) | - | a) | 223674.22 | a) | 100% | c) | 100% | a) | 16 | Completed | 1
| 061 | [7 empty] | b) | Crucio | b) | 03/22/19 | f) | - | b) | 223674.22 | b) | - | d) | - | b) | 480 |  | 1
[9 empty] | c) | SAN JOSE COCONUT | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
|  |  | San Juan - New Talisay |  |  | Road Maintenance | 5.13 | MBA | a) | 306261.25 | a) | 01/03/19 | e) | - | a) | 306261.25 | a) | 100% | c) | 100% | a) | 15 | Completed | 1
| 063 | [7 empty] | b) | Crucio | b) | 02/01/19 | f) | - | b) | 306261.25 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 85123.48 | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | San Juan - New Talisay |  |  | Road Maintenance | 5.13 | CBRMC | a) | 93906.31 | a) | 01/03/19 | e) | - | a) | 93906.31 | a) | 100% | c) | 100% | a) | 16 | Completed
| 063 | [7 empty] | b) | Crucio | b) | 03/26/19 | f) | - | b) | 93906.31 | b) | - | d) | - | b) | 480 |  | 1
[9 empty] | c) | NEW TALISAY IAWA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
|  |  | San Juan - kauswagan - New Cortez |  |  | Road Maintenance | 3.22 | MBA | a) | 187879.04 | a) | 01/03/19 | e) | - | a) | 187879.04 | a) | 100% | c) | 100% | a) | 15 | Completed | 1
| 064 | [7 empty] | b) | Crucio | b) | 03/18/19 | f) | - | b) | 187879.04 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 3,025.00 | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | San Juan - kauswagan - New Cortez |  |  | Road Maintenance | 3.22 | CBRMC | a) | 63298.26 | a) | 01/03/19 | e) | - | a) | 63298.26 | a) | 100% | c) | 100% | a) | 16 | Completed
| 064 | [7 empty] | b) | Crucio | b) | 03/22/19 | f) | - | b) | 63298.26 | b) | - | d) | - | b) | 480 |  | 1
[9 empty] | c) | SAN JOSE COCONUT | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
|  |  | New Bohol - Jct. El Unido |  |  | Road Maintenance | 2.12 | MBA | a) | 54989.06 | a) | 01/03/19 | e) | - | a) | 54989.06 | a) | 100% | c) | 100% | a) | 15 | Completed
| 065 | [7 empty] | b) | Crucio | b) | 03/01/19 | f) | - | b) | 54989.06 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 21021.99 | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | New Bohol - Jct. El Unido |  |  | Road Maintenance | 2.12 | CBRMC | a) | 58861.64 | a) | 01/03/19 | e) | - | a) | 58861.64 | a) | 100% | c) | 100% | a) | 16 | Completed | 1
| 065 | [7 empty] | b) | Crucio | b) | 03/26/19 | f) | - | b) | 58861.64 | b) | - | d) | - | b) | 480 |  | 1
[9 empty] | c) | MANDISKAB TRIBAL | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
1
|  |  | New Corella - El unido - Jct. Mesaoy |  |  | Road Maintenance | 8.63 | MBA | a) | 388002.46 | a) | 01/03/19 | e) | - | a) | 388002.46 | a) | 100% | c) | 100% | a) | 15 | Completed
| 066 | [7 empty] | b) | Crucio | b) | 02/11/19 | f) | - | b) | 388002.46 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 58142.76 | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | New Corella - El unido - Jct. Mesaoy |  |  | Road Maintenance | 8.63 | CBRMC | a) | 233092.08 | a) | 01/03/19 | e) | - | a) | 233092.08 | a) | 100% | c) | 100% | a) | 16 | Completed | 1
| 066 | [7 empty] | b) | Crucio | b) | 03/26/19 | f) | - | b) | 233092.08 | b) | - | d) | - | b) | 480 |  | 1
[9 empty] | c) | MANDISKAB TRIBAL | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
|  |  | Mesaoy - Dasing |  |  | Road Maintenance | 1.39 | MBA | a) | 29749.5 | a) | 01/03/19 | e) | - | a) | 29749.5 | a) | 100% | c) | 100% | a) | 15 | Completed | 1
| 067 | [7 empty] | b) | Crucio | b) | 03/18/19 | f) | - | b) | 29749.5 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 10000 | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | Mesaoy - Dasing |  |  | Road Maintenance | 1.39 | CBRMC | a) | 54152.71 | a) | 01/03/19 | e) | - | a) | 54152.71 | a) | 100% | c) | 100% | a) | 16 | Completed | 1
| 067 | [7 empty] | b) | Crucio | b) | 03/26/19 | f) | - | b) | 54152.71 | b) | - | d) | - | b) | 480 |  | 1
[9 empty] | c) | MANDISKAB TRIBAL | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
|  |  | Jct. San Juan - Jct. Mesaoy |  |  | Road Maintenance | 1.82 | MBA | a) | 106788.95 | a) | 01/03/19 | e) | - | a) | 106788.95 | a) | 100% | c) | 100% | a) | 15 | Completed | 1
| 068 | [7 empty] | b) | Crucio | b) | 03/01/19 | f) | - | b) | 106788.95 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 17502.68 | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | Jct. San Juan - Jct. Mesaoy |  |  | Road Maintenance | 1.82 | CBRMC | a) | 35180.83 | a) | 01/03/19 | e) | - | a) | 35180.83 | a) | 100% | c) | 100% | a) | 16 | Completed | 1
| 068 | [7 empty] | b) | Crucio | b) | 03/26/19 | f) | - | b) | 35180.83 | b) | - | d) | - | b) | 480 |  | 1
[9 empty] | c) | MANDISKAB TRIBAL | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
|  |  | Mesaoy - Jct. Mahayahay |  |  | Road Maintenance | 4.6 | MBA | a) | 146984.46 | a) | 01/03/19 | e) | - | a) | 146984.46 | a) | 100% | c) | 100% | a) | 15 | Completed | 1
| 069 | [7 empty] | b) | Crucio | b) | 03/18/19 | f) | - | b) | 146984.46 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 7618.27 | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | Mesaoy - Jct. Mahayahay |  |  | Road Maintenance | 4.6 | CBRMC | a) | 160103.65 | a) | 01/03/19 | e) | - | a) | 160103.65 | a) | 100% | c) | 100% | a) | 16 | Completed
| 069 | [7 empty] | b) | Crucio | b) | 03/22/19 | f) | - | b) | 160103.65 | b) | - | d) | - | b) | 480 |  | 1
[9 empty] | c) | MAHAYAHAY IFA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
|  |  | Mesaoy - New bohol |  |  | Road Maintenance | 5.36 | MBA | a) | 165361.13 | a) | 01/03/19 | e) | - | a) | 165361.13 | a) | 100% | c) | 100% | a) | 15 | Completed
| 070 | [7 empty] | b) | Crucio | b) | 03/01/19 | f) | - | b) | 165361.13 | b) | - | d) | - | b) | 480 |  | 1
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 2543.9 | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | Mesaoy - New bohol |  |  | Road Maintenance | 5.36 | CBRMC | a) | 224851.45 | a) | 01/03/19 | e) | - | a) | 224851.45 | a) | 100% | c) | 100% | a) | 16 | Completed
| 070 | [7 empty] | b) | Crucio | b) | 03/26/19 | f) | - | b) | 224851.45 | b) | - | d) | - | b) | 480 |  | 1
[9 empty] | c) | MANDISKAB TRIBAL | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
|  |  | Bdry. Tagum - Baca - New Corella |  |  | Road Maintenance | 13.01 | MBA | a) | 217182.9 | a) | 01/03/19 | e) | - | a) | 217182.9 | a) | 100% | c) | 100% | a) | 15 | Completed | 1
| 071 | [7 empty] | b) | Crucio | b) | 03/18/19 | f) | - | b) | 217182.9 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 19550 | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | Bdry. Tagum - Baca - New Corella |  |  | Road Maintenance | 13.01 | CBRMC | a) | 214256.36 | a) | 01/03/19 | e) | - | a) | 214256.36 | a) | 100% | c) | 100% | a) | 16 | Completed | 1
| 071 | [7 empty] | b) | Crucio | b) | 03/26/19 | f) | - | b) | 214256.36 | b) | - | d) | - | b) | 480 |  | 1
[9 empty] | c) | DURIAN DACUDAO | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
|  |  | Prk. 1, Maunlom - Prk. 6 Maunlom Road |  |  | Road Maintenance | 3.56 | MBA | a) | 150912.87 | a) | 01/03/19 | e) | - | a) | 150912.87 | a) | 100% | c) | 100% | a) | 15 | Completed | 1
| 147 | [7 empty] | b) | Crucio | b) | 03/01/19 | f) | - | b) | 150912.87 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 23025 | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | Prk. 1, Maunlom - Prk. 6 Maunlom Road |  |  | Road Maintenance | 3.56 | CBRMC | a) | 63973.36 | a) | 01/03/19 | e) | - | a) | 63973.36 | a) | 100% | c) | 100% | a) | 16 | Completed | 1
| 147 | [7 empty] | b) | Crucio | b) | 03/22/19 | f) | - | b) | 63973.36 | b) | - | d) | - | b) | 480 |  | 1
[9 empty] | c) | THE BEST VEGETABLE | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
1
|  |  | New Visayas - Binancian |  |  | Road Maintenance | 7.77 | MBA | a) | 14814.34 | a) | 01/03/19 | e) | - | a) | 14814.34 | a) | 100% | c) | 100% | a) | 15 | Completed
| 149 | [7 empty] | b) | Crucio | b) | 03/18/19 | f) | - | b) | 14814.34 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 5,000.00 | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | New Visayas - Binancian |  |  | Road Maintenance | 7.77 | CBRMC | a) | 129495.6 | a) | 01/03/19 | e) | - | a) | 129495.6 | a) | 100% | c) | 100% | a) | 16 | Completed | 1
| 149 | [7 empty] | b) | Crucio | b) | 03/22/19 | f) | - | b) | 129495.6 | b) | - | d) | - | b) | 480 |  | 1
[9 empty] | c) | BUAN IFA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
|  |  | Datu Balong - Prk. Mamalian |  |  | Road Maintenance | 3.46 | MBA | a) | 117454.89 | a) | 01/03/19 | e) | - | a) | 117454.89 | a) | 100% | c) | 39.37% | a) | 15 | Completed | 1
| 150 | [7 empty] | b) | Crucio | b) | 03/18/19 | f) | - | b) | 117454.89 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 10115 | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | Datu Balong - Prk. Mamalian |  |  | Road Maintenance | 3.46 | CBRMC | a) | 59264.42 | a) | 01/03/19 | e) | - | a) | 59264.42 | a) | 100% | c) | 100% | a) | 16 | Completed | 1
| 150 | [7 empty] | b) | Crucio | b) | 03/28/19 | f) | - | b) | 59264.42 | b) | - | d) | - | b) | 480 |  | 1
[9 empty] | c) | DATU BALONG FA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
| A.2 GENERAL FUND CY 2019 |  |  |  |  | Road Maintenance | KM | MBA/CBRMC | a) | 11,618,834.00 | a) | 01/03/19 | e) | - | a) | 11,618,834.00 | a) | 66% | c) | 66% | a) | 42 | See list of Provincial Roads
| Road ID |  | 1. Maintenance Of Various Prov'l. Roads and Bridges Dist 2 |  |  |  | 288.26 |  | b) | Matuguinas | b) | 01/03/19 | f) | - | b) | 11,618,834.00 | b) | - | d) | - | b) | 924 |  | FS
[9 empty] | c) | PEO/CBRMC | c) | 12/31/19 | g) | - | c) | - | [7 empty] | AC
| 11DAN | [9 empty] | d) | - | [11 empty] | AC
[9 empty] | d) | 261 days | d) | - | [11 empty] | AC
|  |  | Cebulano - Mangalcal |  |  | Road Maintenance | 4.17 | MBA | a) | 142161.87 | a) | 01/03/19 | e) | - | a) | 142161.87 | a) | 100% | c) | 100% | a) | 9 | Completed | AC
|  | 073 | [6 empty] | b) | Clar | b) | 2019-01-15 | f) | - | b) | 142161.87 | b) | - | d) | - | b) | 18 |  | 2
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 118,609.29 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | Tubod - basa - Mangalcal |  |  | Road Maintenance | 3.93 | MBA | a) | 156875.9 | a) | 01/03/19 | e) | - | a) | 156875.9 | a) | 100% | c) | 100% | a) | 9 | Completed | 2
| 074 | [7 empty] | b) | Clar | b) | 2019-01-15 | f) | - | b) | 156875.9 | b) | - | d) | - | b) | 18 |  | 2
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 143,372.65 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | Upper Mangalcal - Lower Mangalcal |  |  | Road Maintenance | 2.43 | CBRMC | a) | 79237.14 | a) | 01/03/19 | e) | - | a) | 79237.14 | a) | 100% | c) | 100% | a) | 9 | Completed | 2
| 078 | [7 empty] | b) | Clar | b) | 2019-01-14 | f) | - | b) | 79237.14 | b) | - | d) | - | b) | 27 |  | 2
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 69,430.97 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | Jct. Highway Carmen - Mangalcal - Tubod |  |  | Road Maintenance | 11.34 | MBA | a) | 463135.67 | a) | 01/03/19 | e) | - | a) | 463135.67 | a) | 100% | c) | 100% | a) | 9 | Completed | 2
| 082 | [7 empty] | b) | Clar | b) | 01/10/19 | f) | - | b) | 463135.67 | b) | - | d) | - | b) | 45 |  | 2
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 170,106.43 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | Jct. Highway Carmen - Mangalcal - Tubod |  |  | Road Maintenance | 11.34 | CBRMC | a) | 253557.37 | a) | 01/03/19 | e) | - | a) | 253557.37 | a) | 100% | c) | 100% | a) | 10 | Completed | 2
| 082 | [7 empty] | b) | Maligro | b) | 03/25/19 | f) | - | b) | 253557.37 | b) | - | d) | - | b) | 40 |  | 2
[9 empty] | c) | TUBOD CENTRO LOWER IRRIGATORS ASSOCIATION | c) | 09/25/19 | g) | 2019-12-31 | c) | - | [7 empty] | 2
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 2
|  |  | Jct. Highway Sto. Niño - Kabanlakan - La Paz |  |  | Road Maintenance | 2.13 | MBA | a) | 76067.88 | a) | 01/03/19 | e) | - | a) | 76067.88 | a) | 100% | c) | 100% | a) | 9 | Completed | 2
| 084 | [7 empty] | b) | Clar | b) | 01/10/19 | f) | - | b) | 76067.88 | b) | - | d) | - | b) | 45 |  | 2
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 66,477.91 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | Ising - Sto Niño |  |  | Road Maintenance | 2.07 | CBRMC | a) | 82413.14 | a) | 01/03/19 | e) | - | a) | 82413.14 | a) | 100% | c) | 100% | a) | 5 | Completed | 2
| 085 | [7 empty] | b) | Clar | b) | 01/17/19 | f) | - | b) | 82413.14 | b) | - | d) | - | b) | 15 |  | 2
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 27,093.24 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | Ising - Sadpodon - Taba - Dila -Dila |  |  | Road Maintenance | 5.68 | MBA | a) | 248941.33 | a) | 01/03/19 | e) | - | a) | 248941.33 | a) | 100% | c) | 100% | a) | 9 | Completed | 2
| 086 | [7 empty] | b) | Clar | b) | 01/12/19 | f) | - | b) | 248941.33 | b) | - | d) | - | b) | 27 |  | 2
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 82,329.02 | [7 empty] | 2
[9 empty] | d) | - | d) | - |  |  |  | . | [7 empty] | 2
2
|  |  | Tuganay - taba |  |  | Road Maintenance | 4.27 | CBRMC | a) | 291377.9 | a) | 01/03/19 | e) | - | a) | 291377.9 | a) | 70% | c) | 70% | a) | 9 | Completed
| 087 | [7 empty] | b) | Clar | b) | 01/09/19 | f) | - | b) | 291377.9 | b) | - | d) | - | b) | 27 |  | 2
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 12/31/2019 | c) | 238,412.28 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | Jct. Highway Tuganay - Taba |  |  | Road Maintenance | 4.4 | MBA | a) | 32972.82 | a) | 01/03/19 | e) | - | a) | 32972.82 | a) | 65% | c) | 65% | a) | 9 | Completed | 2
| 088 | [7 empty] | b) | Clar | b) | 01/22/19 | f) | - | b) | 32972.82 | b) | - | d) | - | b) | 18 |  | 2
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 12/31/2019 | c) | 22,639.09 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | Jct. Highway Ising - Magsaysay |  |  | Road Maintenance | 10.84 | CBRMC | a) | 417818.12 | a) | 01/03/19 | e) | - | a) | 417818.12 | a) | 60% | c) | 60% | a) | 10 | Completed | 2
| 089 | [7 empty] | b) | Clar | b) | 01/22/19 | f) | - | b) | 417818.12 | b) | - | d) | - | b) | 50 |  | 2
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 12/31/2019 | c) | 313,488.39 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | New Camiling - Alejal - Lower Magsaysay |  |  | Road Maintenance | 6.73 | MBA | a) | 240878.08 | a) | 01/03/19 | e) | - | a) | 240878.08 | a) | 80% | c) | 80% | a) | 4 | Completed | 2
| 091 | [7 empty] | b) | Clar | b) | 01/22/19 | f) | - | b) | 240878.08 | b) | - | d) | - | b) | 20 |  | 2
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 12/31/2019 | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | Jct. highway Tuganay - Anibongan |  |  | Road Maintenance | 3.66 | CBRMC | a) | 150684.44 | a) | 01/03/19 | e) | - | a) | 150684.44 | a) | 100% | c) | 100% | a) | 6 | Completed | 2
| 094 | [7 empty] | b) | Clar | b) | 01/22/19 | f) | - | b) | 150684.44 | b) | - | d) | - | b) | 18 |  | 2
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 12/31/2019 | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | Anibongan - Guadalupe |  |  | Road Maintenance | 2.48 | MBA | a) | 91325.06 | a) | 01/03/19 | e) | - | a) | 91325.06 | a) | 100% | c) | 100% | a) | 9 | Completed | 2
| 095 | [7 empty] | b) | Clar | b) | 01/23/19 | f) | - | b) | 91325.06 | b) | - | d) | - | b) | 18 |  | 2
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 12/31/2019 | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | Tuganay - Anibongan - San Isidro |  |  | Road Maintenance | 7.22 | CBRMC | a) | 139979.8 | a) | 01/03/19 | e) | - | a) | 139979.8 | a) | 100% | c) | 100% | a) | 9 | Completed | 2
| 096 | [7 empty] | b) | Clar | b) | 01/24/19 | f) | - | b) | 139979.8 | b) | - | d) | - | b) | 36 |  | 2
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 12/31/2019 | c) | 1890.37 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | Jct. Anibongan - Prk. 2, 7, 5, San Isidro |  |  | Road Maintenance | 3.14 | MBA | a) | 104378.03 | a) | 01/03/19 | e) | - | a) | 104378.03 | a) | 100% | c) | 100% | a) | 10 | Completed | 2
| 097 | [7 empty] | b) | Clar | b) | 01/24/19 | f) | - | b) | 104378.03 | b) | - | d) | - | b) | 20 |  | 2
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 12/31/2019 | c) | 56,087.50 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | Anibongan - Salvacion - Cabay-angan |  |  | Road Maintenance | 6.93 | CBRMC | a) | 415461.61 | a) | 01/03/19 | e) | - | a) | 415461.61 | a) | 100% | c) | 100% | a) | 9 | Completed | 2
| 098 | [7 empty] | b) | Clar | b) | 01/25/19 | f) | - | b) | 415461.61 | b) | - | d) | - | b) | 45 |  | 2
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 12/31/2019 | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | Jct. Highway Guadalupe - Bdry. Tagum |  |  | Road Maintenance | 7.9 | MBA | a) | 456131.09 | a) | 01/03/19 | e) | - | a) | 456131.09 | a) | 100% | c) | 100% | a) | 9 | Completed | 2
| 101 | [7 empty] | b) | Clar | b) | 01/25/19 | f) | - | b) | 456131.09 | b) | - | d) | - | b) | 18 |  | 2
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 12/31/2019 | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | Jct. Highway Guadalupe - Bdry. Tagum |  |  | Road Maintenance | 7.9 | CBRMC | a) | 228201.66 | a) | 01/03/19 | e) | - | a) | 228201.66 | a) | 100% | c) | 100% | a) | 8 | Completed | 2
| 101 | [7 empty] | b) | Maligro | b) | 03/25/19 | f) | - | b) | 228201.66 | b) | - | d) | - | b) | 40 |  | 2
[9 empty] | c) | LAMPIA PAG-ASA IRRIGATORS ASSOCIATION, INC. | c) | 12/25/19 | g) | 12/31/2019 | c) | - | [7 empty] | 2
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 2
|  |  | Poblacion Dujali - Prk. 8 Dujali |  |  | Road Maintenance | 8.2 | MBA | a) | 285600.05 | a) | 01/03/19 | e) | - | a) | 285600.05 | a) | 100% | c) | 100% | a) | 10 | Completed | 2
| 105 | [7 empty] | b) | Clar | b) | 01/28/19 | f) | - | b) | 285600.05 | b) | - | d) | - | b) | 50 |  | 2
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 12/31/2019 | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | Dujali - San Isidro |  |  | Road Maintenance | 3 | CBRMC | a) | 130319.3 | a) | 01/03/19 | e) | - | a) | 130319.3 | a) | 100% | c) | 100% | a) | 8 | Completed | 2
| 107 | [7 empty] | b) | Gamad | b) | 01/28/19 | f) | - | b) | 130319.3 | b) | - | d) | - | b) | 30 |  | 2
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 12/31/2019 | c) | 45,943.12 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | Prk. 5, RJS - Prk. 6 New Casay |  |  | Road Maintenance | 2.73 | MBA | a) | 235277 | a) | 01/03/19 | e) | - | a) | 235277 | a) | 100% | c) | 100% | a) | 2 | Completed | 2
| 109 | [7 empty] | b) | Gamad | b) | 01/28/19 | f) | - | b) | 235277 | b) | - | d) | - | b) | 6 |  | 2
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 12/31/2019 | c) | 90,745.35 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | Prk. 5 - Prk. 1 Pawas Dujali |  |  | Road Maintenance | 2.18 | CBRMC | a) | 76067.68 | a) | 01/03/19 | e) | - | a) | 76067.68 | a) | 100% | c) | 100% | a) | 10 | Completed | 2
| 112 | [7 empty] | b) | Gamad | b) | 01/18/19 | f) | - | b) | 76067.68 | b) | - | d) | - | b) | 20 |  | 2
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 12/31/2019 | c) | 40,112.50 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | Dujali - Balisong - Magupising |  |  | Road Maintenance | 5.52 | MBA | a) | 260591.93 | a) | 01/03/19 | e) | - | a) | 260591.93 | a) | 100% | c) | 100% | a) | 4 | Completed | 2
| 113 | [7 empty] | b) | Gamad | b) | 01/09/19 | f) | - | b) | 260591.93 | b) | - | d) | - | b) | 8 |  | 2
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 12/31/2019 | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | Dujali - Pawas - San Vicente |  |  | Road Maintenance | 4.42 | CBRMC | a) | 139536.42 | a) | 01/03/19 | e) | - | a) | 139536.42 | a) | 100% | c) | 100% | a) | 10 | Completed | 2
| 117 | [7 empty] | b) | Gamad | b) | 01/22/19 | f) | - | b) | 139536.42 | b) | - | d) | - | b) | 18 |  | 2
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 12/31/2019 | c) | 52,133.86 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | Jct. Salvacion - San Vicente - Cabay-angan |  |  | Road Maintenance | 3.45 | MBA | a) | 247460.9 | a) | 01/03/19 | e) | - | a) | 247460.9 | a) | 100% | c) | 100% | a) | 10 | Completed | 2
| 118 | [7 empty] | b) | Gamad | b) | 01/23/19 | f) | - | b) | 247460.9 | b) | - | d) | - | b) | 18 |  | 2
[9 empty] | c) | PEO | c) | 02/31/19 | g) | 12/31/2019 | c) | 151,887.50 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | Jct. Salvacion - San Vicente - Cabay-angan |  |  | Road Maintenance | 3.45 | CBRMC | a) | 152134.44 | a) | 01/03/19 | e) | - | a) | 152134.44 | a) | 100% | c) | 100% | a) | 8 | Completed | 2
| 118 | [7 empty] | b) | Gamad | b) | 03/26/19 | f) | - | b) | 152134.44 | b) | - | d) | - | b) | 36 |  | 2
[9 empty] | c) | BALISONG SAN VICENTE IRRIGATORS ASSOCIATION | c) | 12/26/19 | g) | 12/31/2019 | c) | [8 empty] | 2
[9 empty] | d) | 3 quarters | d) | - | [10 empty] | Completed | 2
|  |  | Dujali - San Miguel |  |  | Road Maintenance | 3.95 | MBA | a) | 101202.04 | a) | 01/03/19 | e) | - | a) | 101202.04 | a) | 80% | c) | 90% | a) | 11 |  | 2
| 119 | [7 empty] | b) | Gamad | b) | 01/10/19 | f) | - | b) | 101202.04 | b) | - | d) | - | b) | 22 |  | 2
[9 empty] | c) | PEO | c) | 12/31/19 | g) | - | c) | 90,350.03 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | San Miguel - Casig-ang |  |  | Road Maintenance | 2.55 | CBRMC | a) | 79237.14 | a) | 01/03/19 | e) | - | a) | 79237.14 | a) | 100% | c) | 100% | a) | 10 | Completed | 2
| 122 | [7 empty] | b) | Gamad | b) | 01/24/19 | f) | - | b) | 79237.14 | b) | - | d) | - | b) | 10 |  | 2
[9 empty] | c) | BALISONG SAN VICENTE IRRIGATORS ASSOCIATION | c) | 12/31/19 | g) | 12/31/2019 | c) | 40,112.50 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | Prk. Magsaysay - Lunga-og - Dalisay |  |  | Road Maintenance | 2.81 | MBA | a) | 79762.14 | a) | 01/03/19 | e) | - | a) | 79762.14 | a) | 100% | c) | 100% | a) | 8 | Completed | 2
| 127 | [7 empty] | b) | Gamad | b) | 01/30/19 | f) | - | b) | 79762.14 | b) | - | d) | - | b) | 8 |  | 2
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 12/31/2019 | c) | 40,612.50 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | Prk. Apitong - Upper Balisong - Dalisay |  |  | Road Maintenance | 4.6 | CBRMC | a) | 137846.03 | a) | 01/03/19 | e) | - | a) | 137846.03 | a) | 100% | c) | 100% | a) | 8 | Completed | 2
| 128 | [7 empty] | b) | Gamad | b) | 01/31/19 | f) | - | b) | 137846.03 | b) | - | d) | - | b) | 8 |  | 2
[9 empty] | c) | BALISONG SAN VICENTE IRRIGATORS ASSOCIATION | c) | 12/31/19 | g) | 12/31/2019 | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | Sitio Paradise - Magkakaisa - Esperanza |  |  | Road Maintenance | 1.75 | MBA | a) | 66552.75 | a) | 01/03/19 | e) | - | a) | 66552.75 | a) | 100% | c) | 100% | a) | 8 | Completed | 2
| 129 | [7 empty] | b) | 79762.14 | b) | 01/22/19 | f) | - | b) | 66552.75 | b) | - | d) | - | b) | 8 |  | 2
[9 empty] | c) | Gamad | c) | 12/31/19 | g) | 12/31/2019 | c) | 22,246.26 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | Los Amigos 1 - Esperanza - Los Amigos 2 |  |  | Road Maintenance | 3.59 | CBRMC | a) | 101202.04 | a) | 01/03/19 | e) | - | a) | 101202.04 | a) | 100% | c) | 100% | a) | 10 | Completed | 2
| 130 | [7 empty] | b) | Gamad | b) | 01/24/19 | f) | - | b) | 101202.04 | b) | - | d) | - | b) | 20 |  | 2
[9 empty] | c) | BALISONG SAN VICENTE IRRIGATORS ASSOCIATION | c) | 12/31/19 | g) | 12/31/2019 | c) | 50,837.50 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | Mugas - Lunga-og |  |  | Road Maintenance | 2.68 | MBA | a) | 66552.75 | a) | 01/03/19 | e) | - | a) | 91,693.64 | a) | 100% | c) | 100% | a) | 6 | Completed | 2
| 132 | [7 empty] | b) | 79762.14 | b) | 01/17/19 | f) | - | b) | 91,693.64 | b) | - | d) | - | b) | 24 |  | 2
[9 empty] | c) | Gamad | c) | 12/31/19 | g) | 12/31/2019 | c) | 50,837.50 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | Pantaron - Mugas |  |  | Road Maintenance | 3.35 | CBRMC | a) | 101202.04 | a) | 01/03/19 | e) | - | a) | 101202.04 | a) | 100% | c) | 100% | a) | 9 | Completed | 2
| 133 | [7 empty] | b) | Gamad | b) | 01/23/19 | f) | - | b) | 101202.04 | b) | - | d) | - | b) | 18 |  | 2
[9 empty] | c) | BALISONG SAN VICENTE IRRIGATORS ASSOCIATION | c) | 12/31/19 | g) | 12/31/2019 | c) | 90,349.93 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | Sto. Tomas - Bdry. Mamacao |  |  | Road Maintenance | 4.9 | MBA | a) | 110710.44 | a) | 01/03/19 | e) | - | a) | 110710.44 | a) | 100% | c) | 100% | a) | 10 | Completed | 2
| 135 | [7 empty] | b) | 79762.14 | b) | 01/21/19 | f) | - | b) | 110710.44 | b) | - | d) | - | b) | 40 |  | 2
[9 empty] | c) | Gamad | c) | 12/31/19 | g) | 12/31/2019 | c) | 50,837.50 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | Fd. Rd. 3 - San Jose |  |  | Road Maintenance | 4.55 | CBRMC | a) | 147367.49 | a) | 01/03/19 | e) | - | a) | 147367.49 | a) | 100% | c) | 100% | a) | 10 | Completed | 2
| 136 | [7 empty] | b) | Gamad | b) | 01/25/19 | f) | - | b) | 147367.49 | b) | - | d) | - | b) | 30 |  | 2
[9 empty] | c) | BALISONG SAN VICENTE IRRIGATORS ASSOCIATION | c) | 12/31/19 | g) | 12/31/2019 | c) | 56,174.69 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | Menzi - balagunan - Tulalian |  |  | Road Maintenance | 10.63 | MBA | a) | 520167.79 | a) | 01/03/19 | e) | - | a) | 520167.79 | a) | 100% | c) | 100% | a) | 6 | Completed | 2
| 138 | [7 empty] | b) | 79762.14 | b) | 01/07/19 | f) | - | b) | 520167.79 | b) | - | d) | - | b) | 18 |  | 2
[9 empty] | c) | Gamad | c) | 12/31/19 | g) | 12/31/2019 | c) | 204,850.57 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | Jct. Bdry. Tagum - Talomo |  |  | Road Maintenance | 12.01 | CBRMC | a) | 407429.19 | a) | 01/03/19 | e) | - | a) | 407429.19 | a) | 100% | c) | 100% | a) | 10 | Completed | 2
| 145 | [7 empty] | b) | Gamad | b) | 01/11/19 | f) | - | b) | 407429.19 | b) | - | d) | - | b) | 50 |  | 2
[9 empty] | c) | BALISONG SAN VICENTE IRRIGATORS ASSOCIATION | c) | 12/31/19 | g) | 12/31/2019 | c) | 168,544.84 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | San Jose - Sitio Mahayahay, Magwawa |  |  | Road Maintenance | 0.84 | MBA | a) | 7919.35 | a) | 01/03/19 | e) | - | a) | 7919.35 | a) | 100% | c) | 100% | a) | 2 | Completed | 2
| 151 | [7 empty] | b) | 79762.14 | b) | 01/16/19 | f) | - | b) | 7919.35 | b) | - | d) | - | b) | 8 |  | 2
[9 empty] | c) | Gamad | c) | 12/31/19 | g) | 12/31/2019 | c) | 1,509.27 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| B. 20% DEVELOPMENT FUND CY 2019 | [22 empty] | FS
| Road ID |  | 1. Rehabilitation Of Various Prov'l. Roads and Bridges Dist. 1 |  |  | Road Rehabilitation | KM | MBA | a) | 41465029 | a) | 01/03/19 | e) | - | a) | 41465029 | a) | - | c) | - | a) | 46 | See list of Provincial Roads | FS
[7 empty] | 109.55 |  | b) | Paraguya | b) | 01/03/19 | f) | - | b) | 41465029 | b) | - | d) | - | b) | 920 |  | AC
| 11DAN | [7 empty] | c) | PEO | c) | 12/31/19 | g) | - | c) | - | [7 empty] | AC
[11 empty] | d) | - | [11 empty] | AC
[9 empty] | d) | 261 days | d) | - | [11 empty] | AC
[6 empty] | Road Rehabilitation |  |  | a. )P 500,000.00 |  | a.) 01/31/19 |  |  |  | a.) 500,000.00 | [8 empty] | 1
|  |  | Purok 10 Pob. Road, New Corella | [7 empty] | b.) Feb. 16, 2019 |  |  |  | b.) 500,000.00 | [7 empty] | Completed
g.) Feb. 28, 2019
[6 empty] | Road Rehabilitation |  |  | a.)1,815,000.00 |  | a.) 01/31/19 |  |  |  | a.) 1,815,000.00
|  |  | Purok 7 Pob- Jct. New Sambog | [7 empty] | b.)March 1, 2019 |  |  |  | b.) 1,815,000.00 | [7 empty] | Completed
g.) May 15, 2019
[6 empty] | Road Rehabilitation |  |  | a.) 1,389,000.00 |  | a.) 01/31/19 |  |  |  | a.) 1,389,000.00 | [7 empty] | Completed with a savings of P303,898.08 furtherance and is for implementation
|  |  | Del Pilar- El Unido Road | [5 empty] | b.) Fabian |  | b.) March 18,2019 |  |  |  | a.) 1,389,000.00
g.) May 8, 2019
SUPPLEMENTAL BUDGET NO 4 CY 2019 / CONTINUING APPROPRIATION
[9 empty] | a.) 7,742,775.95 | [5 empty] | a.) 7,742,775.95 | [7 empty] | Waiting for the delivery of materials
|  |  | Impvt. of Km. 9 Sagayen - Sawata Provincial Road Phase II | [5 empty] | b.) Kenny | [5 empty] | b.) 7,742,775.95
| Road ID |  | 1. Rehabilitation Of Various Prov'l. Roads and Bridges Dist 2 |  |  | Road Rehabilitation | KM | Admin | a) | 46740117 | a) | 01/03/19 | [10 empty] | See list of Provincial Roads
[7 empty] | 115.62 |  | b) | Matuguinas | b) | - | [11 empty] | AC
| 11DAN | [7 empty] | c) | PEO | c) | - | [11 empty] | AC
[11 empty] | d) | - | [11 empty] | AC
[9 empty] | d) | 261 days | d) | - | [11 empty] | AC
[6 empty] | Road Rehabilitation |  |  | a.) 515,000.00 |  | a.) 03/12/19 |  |  |  | a.) 515,000.00 | [8 empty] | 2
|  |  | Jct. Highway -Tubod - Bagong Silang | [5 empty] | b.) Clar |  | b.) March 18, 2019 |  |  |  | b.) 515,000.00 | [7 empty] | Completed
g.) June 15, 2019
[6 empty] | Road Rehabilitation |  |  | a.) 390,000.00 |  | a.) 03/12/19 |  |  |  | a.) 390,000.00 | [8 empty] | 2
|  |  | Cebulano- Luceta | [5 empty] | b.) Clar |  | b.) March 8, 2019 |  |  |  | b.) 390,000.00 | [7 empty] | Completed
g.) June 15, 2019
[6 empty] | Road Rehabilitation |  |  | a.) 295,000.00 |  | a.) 03/12/19 |  |  |  | a.) 295,000.00
|  |  | Lower Asuncion - Upper Asuncion | [5 empty] | b.) Clar |  | b.) March 18, 2019 |  |  |  | b.) 295,000.00 | [7 empty] | Completed
g.) June 15, 2019
[6 empty] | Road Rehabilitation |  |  | a.) 1,220,000.00 |  | a.) 03/12/19 |  |  |  | a.) 1,220,000.00
|  |  | Jct. Highway - Sto. Nino - La Paz - San Vicente | [5 empty] | b.)Obar |  | b.) March 18, 2019 |  |  |  | b.) 1,220,000.00 | [7 empty] | Completed
g.) Sept. 30, 2019
|  |  | Alejal - Alemag |  |  | Road Rehabilitation | 1.79 |  | a) | 970000 | a) | 2019-03-18 | e) | - | a) | 970000 | a) | 100% | c) | 100% | a) | 7 | Completed. Financially completed
| 092 | [7 empty] | b) | Gamad/Clar | b) | 2019-05-20 | f) | - | b) | 970000 | b) | 100 | d) | 0% | b) | 20 |  | 2
[9 empty] | c) | - | c) | 2019-09-12 | g) | Sept. 30, 2019 | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
[6 empty] | Road Rehabilitation |  |  | a.) 640,000.00 |  | a.) 03/12/19 |  |  |  | a.) 640,000.00 | [8 empty] | 2
|  |  | Mabaus - Cabay -angan | [5 empty] | b.)Clar |  | b.) Maech 18, 2019 |  |  |  | a.) 640,000.00 | [7 empty] | Completed
g.) July 30, 2019
[6 empty] | Road Rehabilitation |  |  | a.) 280,000.00 |  | a.) 03/12/19 |  |  |  | a.) 280,000.00
|  |  | Mabaus - Salvacion | [5 empty] | b.)Clar |  | b.) March 18, 2019 |  |  |  | a.) 280,000.00
[13 empty] | g.) June 30, 2019 | [9 empty] | Completed
|  |  | Dujali - New Casay |  |  |  | 3.2 | Admin | a) | 640000 | a) | 2019-05-16 | e) | - | a) | 640000 | a) | 100% | c) | 100% | a) | 10 |  | 2
| 106 | [7 empty] | b) | Gamad/Clar | b) | 2019-06-17 | f) | 40 | b) | 640000 | b) |  | d) | - | b) | 40 | Completed | 2
[9 empty] | c) | - | c) |  | g) | 10/15/2019 | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
[6 empty] | Road Rehabilitation |  |  | a.) 450,000.00 |  | a.) 03/12/19 |  |  |  | a.) 450,000.00 | [8 empty] | 2
|  |  | New Casay - Bugtong Talisay | [5 empty] | b.)Clar |  | b.) March 18, 2019 |  |  |  | a.) 450,000.00 | [7 empty] | Completed
g.)June 30, 2019
[6 empty] | Road Rehabilitation |  |  | a.)220,000.00 |  | a.) 03/12/19 |  |  |  | a.)220,000.00 |  | a.) 100 % |  | c.)100% |  |  |  |  | 2
|  |  | Purok 6 Cabay-angan - Esti | [5 empty] | b.) Gamad |  | b.) March 18, 2019 |  |  |  | a.)220,000.00 | [7 empty] | Completed
g.) June 30, 2019
[6 empty] | Road Rehabilitation |  |  | a.)250,000.00 |  | a.) March 12, 2019 | [5 empty] | a.) 100 % |  | c.)100%
|  |  | Dujali - Sitio Pawas | [5 empty] | b.) Gamad |  | b.) March 18, 2019 | [11 empty] | Completed
g.) Jun 30, 2019
[6 empty] | Road Rehabilitation |  |  | a.) 280,000.00 |  | a.) March 12, 2019 | [5 empty] | a.) 100 % |  | c.)100%
|  |  | Purok 1 to Purok 2 Sitio Pawas | [6 empty] | b.) Gamad | b.) March 18, 2019 | [11 empty] | Completed
g.) Jun 30, 2019
|  |  | San Miguel - Crossing Kinamayan |  |  | Road Rehabilitation | 2.8 | Admin | a) | 560000 | a) | 2019-06-25 | e) | - | a) | 560000 | a.) 100 % |  | c.)100% |  | a) | -
| 120 | [7 empty] | b) | Nasol | b) | Sept. 19, 2019 | f) | - | b) | 560000 | b) | - | d) | - | b) | - | Completed | 2
[9 empty] | c) | - | c) | - | g) | Nov. 30, 2019 | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | Kinamayan - Lunga-og |  |  | Road Rehabilitation | 2.59 | Admin | a) | 520000 | a) | 2019-03-18 | e) | - | a) | 520000 | a) | 100% | c) | 100% | a) | 9 | Completed | 2
| 126 | [7 empty] | b) | Gamad/Clar | b) | 5/202/019 | f) | - | b) | 520000 | b) | - | d) | - | b) | 36 |  | 2
[9 empty] | c) | - | c) |  | g) | Sept. 30, 2019 | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
[9 empty] | a.) 540,000.00 |  | a.) March 12, 2019 |  |  |  | a.) 540,000.00 |  | a.)100% |  | c.)100% |  |  |  | Completed
|  |  | Nafco - Bobongon |  |  | Road Rehabilitation |  |  | b. Gamad |  | b.) march 18, 2019 |  |  |  | b.) 540,000.00
g.) June 30, 2019
2
|  |  | Prk. Narafil - Prk. Daisy Magupising |  |  | Road Rehabilitation | 19.16 | Admin | a) | 300117 | a) | 2019-06-25 | e) | - | a) | 300117 | a) | 100% | c) | 100% | a) | - | Completed | 2
| 148 | [7 empty] | b) | Gamad/Clar | b) | Sept. 16, 2019 | f) | - | b) | 300117 | b) | - | d) | - | b) | - |  | 2
[9 empty] | c) | - | c) | - | g) | Oct. 18, 2019 | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 2. Various of Local Roads & Drainage Development Project (Provincewide) |  |  |  |  | Road Drainage rehabiliated |  | Admin | a) | 15000000 | [12 empty] | See projects listed below | 2
[9 empty] | b) | Paraguya | [13 empty] | AC
[9 empty] | c) | PEO | [13 empty] | AC
[9 empty] | d) | - | [13 empty] | AC
|  |  | Rehab. of Anibongan-Salvacion-Cabay-angan Provincial Road with Drainage |  |  | Road Drainage rehabiliated | - | - | a) | 2000000 | a) | 2019-01-14 | e) | - | a) | 2000000 | a) | 100% | c) | 100% | a) | 1 | Completed | 2
| 2.1 | [7 empty] | b) | Toquero | b) | 2019-05-22 | f) | - | b) | 2000000 | b) | - | d) | - | b) | 4 | Fiancial obligation still on process | 2
[9 empty] | c) | PEO | c) | 2019-08-04 | g) | Dec. 31, 2019 | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | Rehab./Impv't. of Sto. Tomas-Bdry. Mamacao Provincial Road |  |  | Road Drainage rehabiliated | - | Admin | a) | 1500000 | a) | 2019-01-14 | e) | - | a) | 1500000 | a) | 100% | c) | 100% | a) | - | Completed Financial obligation on process
| 2.4 | [7 empty] | b) | Toquero | b) | 2019-05-31 | f) | 60 | b) | 1500000 | b) | - | d) | - | b) | - |  | 2
[9 empty] | c) | PEO | c) | 2019-07-15 | g) | Dec. 31, 2019 | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 4. Various Government Buildings and Facilities Development Project (Provincewide) |  |  |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of recipients | - | Admin | a) | 27000000 | [12 empty] | See projects listed below | 2
[9 empty] | b) | Medalla | [13 empty] | AC
[9 empty] | c) | PEO | [13 empty] | AC
[9 empty] | d) | - | [13 empty] | AC
|  |  | Const. of GYM Bleacher at Suaybaguio Rina, Elem. School |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of recipients | - | #REF! | a) | 1000000 | a) | - | e) | - | a) | 1000000 | a) | 100% | c) | 100% | a) | - | Completed | 1
|  | 11 | [6 empty] | b) | Mayang | b) | 6/3/2019 | f) | - | b) | 1000000 | b) | 64 | d) | 0% | b) | - |  | 1
[9 empty] | c) | PEO | c) | 8/01/2019 | g) |  | c) | - | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
| 5. Stimulus Projects for Various Barangays a. 20% Development Fund CY 2019 |  |  |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | Admin | a) | 41500000 | [12 empty] | See projects listed below | 2
[9 empty] | b) | Medalla | [13 empty] | AC
[9 empty] | c) | PEO | [13 empty] | AC
[9 empty] | d) | - | [13 empty] | AC
AC
| IGCS | [22 empty] | 2
| 5.42 |  | Rehab. Of Health Center, Aumbay, IGCS |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) | Feb. 28, 2019 | e) | - | a) | 500000 | a) |  | c) | 48.32% | a) | 3 | Completed Financial obligation on process | AC
[9 empty] | b) | Pacquiao | b) | 7/10/2019 | f) | - | b) | 500000 | b) | - | d) |  | b) | 15 |  | 2
[9 empty] | c) | Admin | c) | 10/7/2019 | g) | - | c) | - | [7 empty] | 2
[9 empty] | d) | 90 CD | d) | - | [11 empty] | 2
| 5.46 |  | Rehab. Of Brgy. Health Center, Mambago-A, IGCS |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) | Feb. 28, 2019 | e) | - | a) | 500000 | a) |  | c) | 75.61% | a) | 3 | Completed Financial obligation on process | 2
[9 empty] | b) | Ganaba | b) | 07/2019 | f) | - | b) | 500000 | b) |  | d) |  | b) | 15 |  | 2
[9 empty] | c) | Admin | c) | 8/23/2019 | g) | - | c) | - | [7 empty] | 2
[9 empty] | d) | 45 CD | d) | - | [11 empty] | 2
| 6. Rural Electrification Project (Provincewide) |  |  |  |  | Powerlines/posts installed & rehabilitated | - | - | a) | 5000000 | [12 empty] | See projects listed below | 2
[9 empty] | b) | Kim Pao Lu | [13 empty] | AC
[9 empty] | c) | - | [13 empty] | AC
[9 empty] | d) | - | [13 empty] | AC
C. 5% CALAMITY FUND CY 2019
| 3 |  | Improvement of roads, drainage and canal |  |  | Protection dikes/slope protection | - | - | a) | 3000000 | [12 empty] | See projects listed below | 2
[9 empty] | b) | Paraguya | [13 empty] | AC
[9 empty] | c) | PEO | [13 empty] | AC
[9 empty] | d) | - | [13 empty] | AC
| a. |  | Rehab./Impv't. of New Casay-Bugtong Talisay Provincial Road (Ph.II) |  |  | creeks and canRoads/Draiange/canals rehab/improved | - | - | a) | 500000 | a) | 2019-03-12 | e) | - | a) | 500000 | a) | 100% | c) | 100% | a) | 12 | Completed | AC
[9 empty] | b) | Toquero | b) | 2019-05-30 | f) | - | b) | 500000 | b) | - | d) | - | b) | 120 |  | 2
[9 empty] | c) | Admin | c) | 2019-07-30 | g) |  | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | Mark | Municipality/City |  | Color
|  |  | 1 | Asuncion |  | Red | [17 empty] | 0.3375
|  |  | 2 | B.E. Dujali |  | Yellow | [17 empty] | 3.0375
|  |  | 3 | Carmen |  | Blue | [7 empty] | GF- GENERAL FUND |  |  | TF - TRUST FUND (NATIONAL FUNDED PROJECT)
|  |  | 4 | Kapalong |  | Pink | [7 empty] | 20% DF - 20% DEV'T. FUND |  |  | a) SLRF - Special Local Road Fund
|  |  | 5 | New Corella |  | Gray | [7 empty] | 5% CF - 5% CALAMITY FUND |  |  | b) KALSADA - Konkreto at Ayos na Lansangan Tungo sa Pangkalahatang Kaunlaran
|  |  | 6 | San Isidro |  | Orange | [7 empty] | CO - CAPITAL OUTLAY |  |  | c) PRDP - Philippine Rural Development Projects
|  |  | 7 | Sto Tomas |  | Sky Blue | [7 empty] | CONG. FUND - CONGRESSIONAL FUND |  |  | d) SELAP - Support to Emergency and Livelihood Assistance Project
|  |  | 8 | Talaingod |  | Violet | [10 empty] | e) PAMANA - Payapa at Masaganang Pamayanan
|  |  | 9 | Panabo City |  | Brown | [7 empty] | SEF - SPECIAL EDUCATIONAL UFND |  |  | f) CBRMC - Community Based Road Maintenance Contracting
|  |  | 10 | IGACOS |  | Yellow Green | [10 empty] | g) MBC - Maintenance by Contract
|  |  | 11 | Tagum City |  | Green | [10 empty] | h) PCF-Performance Challenge Fund-DILG
i) FMRDP - Farm to Market Road
j.) CMGP - Conditional Grant to Provinces
k.) OPAPP - Office of the President Adviser on the Peace Process
l.) LGSF-AM - Local Government Support Fund Assistance to Municipalities
| Prepared by: |  |  |  | Checked | [12 empty] | Recommending Approval
Noted
| GILBERT G. MAMBULAO JR |  |  |  | ELISA A. BARCENA | [10 empty] | JIVELLYN B. CO | [5 empty] | GLENN A. OLANDRIA
| Engineer II |  |  |  | Engineer IV- Engineering Dist 1, Area Engineer | [11 empty] | Asst. PG-Department Head |  |  |  |  | Provincial Engineer
[5 empty] | EDWIN S. MISA |  |  |  | MARILOU A. FORONDA
[5 empty] | Engineer IV- PDPM Division Head |  |  |  | Engineer IV- QC Division Head

## Annual On going 2019_Dist1 (hidden)
PROVINCE OF DAVAO DEL NORTE
ACCOMPLISHMENT REPORT
Annual 2019
SECTOR: ECONOMIC (INFRASTRUCTURE DEV'T. PROGRAM)
OFFICE/AGENCY: PROVINCIAL ENGINEER'S OFFICE
ON-GOING PROJECTS DISTRICT 1
Name of Project |  |  |  |  | Type | Physical | Mode | PROJECT DATA | [5 empty] | Financial (000) |  | Physical Accomplishment |  |  |  | Employment |  | REMARKS
[5 empty] | of | Target | of | a) Project Cost |  | a) | Date A lot. Rel. | e) | # of days suspended | a) Program |  | a) Planned |  | c) Actual |  | Generated
[5 empty] | Project | (Descrip | Impl. | b) Project Engineer |  | b) | Date Started | f) | # of days extended | b) Allotment |  | b) Revised |  | d) Slippage |  | a) # of Persons | # of Persons
[5 empty] | (Location) | tion) |  | c) Implementor |  | c) | Target Compl. Date | g) | Date completed | c) Disbursement | [5 empty] | b) | Man-days
[8 empty] | d) Duration |  | d) | Revised Compl. Date
I. | PROJECTS UNDER THE CONTINUING APPROPRIATION | [22 empty] | AC |  |  |  | 893809.45
| A. | Supplemental Budget # 1 CY 2015 | [19 empty] | delay due to change location & design code. For AIP amendment from Panabo City to Gov't Center, Mankilam |  | 2
|  | 1. Proposed Davao del Norte Tourism Billboard |  |  | Billboard |  | Admin | a) | 756,400.00 | a) | 05/06/15 | e) | - | a) | 756,400.00 | a) | 11.78% | c) | 11.78% | a) | - |  |  | 2
|  | Brgy. Lasang, Panabo City | [5 empty] | b) | Porras | b) | 03/30/15 | f) | - | b) | 756,400.00 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | PEO | c) | 05/10/15 | g) | - | c) | 332,087.30 | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
| B. | Supplemental Budget # 5 CY 2015 | [21 empty] | FS
|  | 1. Purchased, Const. & Imprv't. of Gov't. Facilities (8918) | [19 empty] | See projects listed below |  | AC
|  | a) Const./Compl./Imprvt. of Various Gov't. Bldgs. |  |  | Bldgs. |  | Admin | a) | 38,000,000.00 | [14 empty] | AC
|  | Structures & Facilities | [5 empty] | b) | Imboy | [14 empty] | AC
[8 empty] | c) | PEO | [14 empty] | AC
|  | 4.) Const. of Multi-Purpose Bldg. Magsaysay, Carmen |  |  | Court |  | - | a) | 500000 | a) | 03/05/16 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For cancellation since the project was already undertaken by Davao Light & no back up cash since it is part of the loan with LBP |  | 2
[8 empty] | b) | CY 2015 | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | PEO | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | 5.) Improvement of Covered Court |  |  | Court |  | - | a) | 500000 | a) | 03/05/16 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For cancellation since the project was already undertaken by Davao Light & no back up cash since it is part of the loan with LBP |  | 2
|  | Brgy. San Isidro, Carmen | [5 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | PEO | c) | - | g) | - | c) | [9 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | 6.) Construction of 1 Bay Covered Court |  |  | Court |  | - | a) | 500000 | a) | 03/08/16 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For cancellation since the project was already undertaken by Davao Light & no back up cash since it is part of the loan with LBP |  | 2
|  | Brgy. Bobongon, Sto. Tomas | [5 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | PEO | c) | - | g) | - | c) | [9 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | 7.) Construction of Multi-Purpose Building |  |  | Bldg. |  |  | a) | 500000 | a) | 03/05/16 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For cancellation since the project was already undertaken by Davao Light & no back up cash since it is part of the loan with LBP |  | 2
|  | Brgy. New Visayas, Sto. Tomas |  |  |  |  | - | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | PEO | c) | - | g) | - | c) | [9 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | 8.) Improvement of Brgy. Hall |  |  | Bldg. |  |  | a) | 500000 | a) | 03/05/16 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For cancellation since the project was already undertaken by Davao Light & no back up cash since it is part of the loan with LBP |  | 2
|  | Brgy. Tulalian, Sto. Tomas |  |  |  |  | - | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | PEO | c) | - | g) | - | c) | [9 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | 9.) Construction of Market Stall |  |  | Market |  |  | a) | 500000 | a) | 03/05/16 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For cancellation since the project was already undertaken by Davao Light & no back up cash since it is part of the loan with LBP |  | 2
|  | Brgy. La Libertad, Sto. Tomas |  |  | Stall |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[7 empty] | - | c) | PEO | c) | - | g) | - | c) | [9 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | 10.) Const. of Covered Court Bleacher w/ Roofing |  |  | Court |  |  | a) | 500000 | a) | 03/05/16 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For cancellation since the project was already undertaken by Davao Light & no back up cash since it is part of the loan with LBP |  | 2
|  | Brgy. Cabay-angan, B.E. Dujali |  |  |  |  | - | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | PEO | c) | - | g) | - | c) | [9 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
| C. | Trust Fund | [21 empty] | FS
|  | 1. PRDP | [21 empty] | AC
|  | 1.1 Rehab. of Esperanza-Pob. Sto. Tomas, |  |  | Road | 12.774 | Contract. | a) | 117,410,426.30 | a) | CY 2014 | e) | - | a) | 117,410,426.30 | a) | 100% | c) | 89.82% | a) | 20 | On-going . Request for time extension on process. Waiting for approval of variation order for billing |  | 2
|  | FMR, DDN | [5 empty] | b) | Palero | b) | 03/22/17 | f) | - | b) | 117,410,426.30 | b) | 96% | d) | -6.179% | b) | 600 |  |  | 2
[8 empty] | c) | Alzam | c) | 07/22/19 | g) | - | c) | 113,335,769.31 | [8 empty] | 2
[8 empty] | d) | 853 CD | d) | - | [12 empty] | 2
|  | 1.2 Construction of Dalisay Potable Water System |  |  | Water | - | Contract. | a) | 4664033.76 | a) | CY 2014 | e) | - | a) | 4664033.76 | a) | 100.00% | c) | 82.88% | a) | - | for resumption |  | 2
[5 empty] | System |  |  | b) | Estorco | b) | 01/29/18 | f) | 39 CD | b) | 4664033.76 | b) | 87.94% | d) | -5.06% | b) | - |  |  | 2
[8 empty] | c) | Ancor Water Resources | c) | 07/23/18 | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | 188 CD | d) | 08/31/18 | [12 empty] | 2
|  | 1.3. Construction of Kasilak Potable Water System |  |  | Water | - | Contract. | a) | 7046856.27 | a) | CY 2014 | e) | 72 CD | a) | 7046856.27 | a) | 100.00% | c) | 87.38% | a) | - | for resumption |  | 2
[5 empty] | System |  |  | b) | Estorco | b) | 01/29/18 | f) | - | b) | 7046856.27 | b) | 83.53% | d) | +3.850% | b) | - |  |  | 2
[8 empty] | c) | Ancor Water Resources | c) | 09/24/18 | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | 188 CD | d) | 12/05/18 | [12 empty] | 2
2
|  | 1.4. Improvement of Sto. Tomas Production Center with Common Facility |  |  | Building |  | Contract. | a) | 9825000 | a) | CY 2014 | e) | 72 CD | a) |  | a) |  | c) |  | a) |  | Suspended due to land issue |  | 2
[8 empty] | b) | Azotes | b) | 01/29/18 | f) | - | b) |  | b) |  | d) |  | b) |  |  |  | 2
[8 empty] | c) | Manantan | c) | 09/24/18 | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | 330 C.D | d) | 12/05/18 | [12 empty] | 2
2
|  | SLRF 2015 | [7 empty] | a) |  | e) | 65 days | a) |  | a) | 100% | c) | 100% | a) | 3 | Completed as per POW, Financial Documents on Process |  | 2
|  | Rehab. of Jct. Highway-Tuganay-Anibongan-BE Dujali-Kinamayan Provincial Road (Furtheranace) |  |  | Slope protection | - | - | a) | 1911175.99 | b) | 2019-02-18 | f) | 47 days | b) |  | b) |  | d) | 0% | b) | 60 |  |  | 2
[8 empty] | b) | Balbastro | c) | 2019-09-21 | g) | 9/21/2019 | c) | [9 empty] | 2
[8 empty] | c) | Admin | d) | [13 empty] | 2
[8 empty] | d) | - | [14 empty] | 2
| D. | 20% Development Fund CY 2016 | [21 empty] | FS
|  | 1. Water System Development Projects |  |  | Water |  | Admin | a) | 2000000 | [12 empty] | See project listed below |  | AC
|  | (Provincewide) |  |  | System |  |  | b) | - | [14 empty] | AC
[8 empty] | c) | PEO | [14 empty] | AC
|  | b. | Development of Deepwell Source and Install. Of |  | Water |  | Admin | a) | 645,000.00 | a) | 11/08/18 | e) | - | a) | 645,000.00 | a) | 82.76% | c) | 72.89% | a) | 4 | drilling works completed 7/15/2019 but insufficient water source |  | 2
|  |  | Pipelines, Licup, samal Dist. IGACOS |  | System |  |  | b) | Diosanta | b) | 03/01/19 | f) | - | b) | 645,000.00 | b) | - | d) | -9.87% | b) | 100 |  |  | 2
|  |  | (Previously Deepwell Drilling at Licup) |  |  |  |  | c) | PEO | c) | 05/10/19 | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | 2. Rural Electrification (Provincewide) |  |  | Elect. |  | Admin | a) | 5000000 | [12 empty] | See projects listed below |  | AC
[8 empty] | b) | Foronda/Ababon | [14 empty] | AC
[8 empty] | c) | Admin | [14 empty] | AC
[8 empty] | d) | - | [14 empty] | AC
|  | 2.1 | Inst. of transformer and accessories, |  | Elect. |  | Admin | a) | 150,000.00 | a) | 07/31/18 | e) | - | a) | 150,000.00 | a) | - | c) | - | a) | - | For PR - c/o Engr Kim Pao Lu |  | 2
|  |  | Brgy. Kinawitnon |  |  |  |  | b) | - | b) | - | f) | - | b) | 150,000.00 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | 2.2 | Electrification expansion to Purok 7, |  | Elect. |  | Admin | a) | 1,537,404.57 | a) | 02/04/19 | e) | - | a) | 1,537,404.57 | a) | - | c) | - | a) | - | Waiting for NTP - c/o Engr Kim Pao Lu |  | 2
|  |  | Brgy. Guilon, samal Dist. IGCS |  |  |  |  | b) | - | b) | - | f) | - | b) | 1,537,404.57 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | 2.3 | Rural Electrification at brgy. Sta. Cruz, |  | Elect. |  | Contract | a) | 2000000 | a) | - | e) | - | a) | 2000000 | a) | - | c) | - | a) | - | Delay due to action of Daneco for staking. c/o Engr. Kim |  | 2
|  |  | talikud, Samal |  |  |  |  | b) | - | b) | - | f) | - | b) | 2000000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | Admin | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | 3. Const./Rehab./Comp. of Various Gov't. Bldgs. |  |  | Bldgs./ | - | Admin | a) | 9,000,000.00 | [12 empty] | See project listed below |  | AC
|  | Struct., Fac. (Provincewide) |  |  | Fence |  |  | b) | Foronda/Ababon | [14 empty] | AC
[8 empty] | c) | PEO | [14 empty] | AC
|  | 2.1 | Construction of Provincial Training Center |  | Fence |  | Admin | a) | 940,000.00 | a) | 09/19/17 | e) | - | a) | 940,000.00 | a) | 68.00% | c) | 75.00% | a) | - | Temporarily suspended 4/23/18 due to undemolished structures of illegal settlers |  | 2
|  |  | Compound Fence, Kinawitnon, Babak |  |  |  |  | b) | Pacquiao | b) | 03/12/18 | f) | - | b) | 940,000.00 | b) | - | d) | - | b) | - |  |  | 2
|  |  | District, IGCS |  |  |  |  | c) | PEO | c) | 06/19/18 | g) | - | c) | 933,418.80 | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
| A.4 | 20% Development Fund CY 2017 | [21 empty] | FS
|  | STIMULUS PROJECTS CY 2017 | [21 empty] | FS
|  | ASUNCION | [21 empty] | FS
|  | 1 | Construction of Water Reservoir & |  | Water |  | MEO | a) | 500000 | a) | 12/28/17 | e) | - | a) | 500000 | a) | 90.00% | c) | 90.00% | a) | - | Suspended due to non availability of water source during drilling.Find another location. Fund already transferred at Municipality of Asuncion with ChecK No. 2445174 and OR # 9238468, |  | 1
| 1 |  | Purchase of P.E. Pipelines, Sagayen, |  | System |  |  | b) | - | b) | 11/15/18 | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
|  |  | Asuncion |  |  |  |  | c) | MEO | c) | - | g) | - | c) | - | [8 empty] | 1 | 1 | Asuncion | Red
[8 empty] | d) | - | d) | - | [12 empty] | 1 | 2 | B.E. Dujali | Yellow
|  | NEW CORELLA | [21 empty] | FS | 3 | Carmen | Blue
| 5 | 1 | Road Rehabilitation at Prk. 1-Prk. 5, |  | Road |  | MEO | a) | 500000 | a) | 11/29/17 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Fund already transferred at Municipality of New Corella with ChecK No. 2445213 and OR # 8592072, dated March 13, 2018. Waiting for availability of Bulldozer |  | 1 | 4 | Kapalong | Pink
|  |  | Sta. Fe, New Corella |  |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1 | 5 | New Corella | Gray
[8 empty] | c) | MEO | c) | - | g) | - | c) | - | [8 empty] | 1 | 6 | San Isidro | Orange
[8 empty] | d) | - | d) | - | [12 empty] | 1 | 7 | Sto Tomas | Sky Blue
|  | TAGUM CITY | [21 empty] | FS | 8 | Talaingod | Violet
| 11 | 1 | Construction of Multi-Purpose GYM at |  | Bldg. |  | - | a) | 500000 | a) | 11/29/17 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For AIP amendment due to change of priority.Last priority recommended was Const. of Drainage (Box Culvert) at Purok Sampaguita but funded and implemented by the City of Tagum.Waiting for new project priority |  | 1 | 9 | Panabo City | Brown
|  |  | Mangga E/S, Visayan Village, Tagum City |  |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1 | 10 | IGACOS | Yellow Green
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1 | 11 | Tagum City | Green
[8 empty] | d) | - | d) | - | [12 empty] | 1
|  | KAPALONG | [21 empty] | FS
| 4 | 1 | Impv't. of Brgy. Hall, Sua-on, Kapalong |  | Bldg. |  | - | a) | 500000 | a) | 02/13/18 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For AIP Amendment |  | 1
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| 4 | 2 | Construction of Solar Drier, Semong, |  | Solar |  | - | a) | 500,000.00 | a) | 12/28/17 | e) | - | a) | 500,000.00 | a) | - | c) | - | a) | - | For AIP Amendment |  | 1
|  |  | Kapalong |  | Drier |  |  | b) | - | b) | - | f) | - | b) | 500,000.00 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| 4 | 3 | Construction of Multi-Purpose Pavement, |  | MPP |  | - | a) | 500000 | a) | 12/28/17 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For AIP Amendment |  | 1
|  |  | Florida, Kapalong |  |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| 4 | 4 | Construction of Concrete Bleacher, |  | Bleacher |  | - | a) | 500000 | a) | 12/07/17 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For AIP Amendment |  | 1
|  |  | Tiburcia, Kapalong |  |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
| 4 | 5 | Mainline Pipes for PWS, Mabantao, |  | Water |  | - | a) | 500000 | a) | 12/07/17 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | To change priority but not yet submitted new resolution c/o Engr. Amamio. Note: Previous project was funded by LGU |  | 1
|  |  | kapalong |  | System |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| 4 | 6 | Impv't. of Covered Court, Pag-Asa, |  | Court |  | - | a) | 500000 | a) | 12/07/17 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For AIP Amendment |  | 1
|  |  | Kapalong |  |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| 4 | 7 | Covered Court Bleacher, Katipunan, |  | Bleacher |  | - | a) | 500000 | a) | 12/07/17 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For AIP Amendment |  | 1
|  |  | Kapalong |  |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| 4 | 8 | Improvement of Gabuyan Covered Court, |  | Court |  | Admin | a) | 500000 | a) | 12/07/17 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For AIP Amendment |  | 1
|  |  | Brgy. Gabuyan, Kapalong |  |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | PEO | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| A.4 | 20% Development Fund CY 2017 | [21 empty] | FS
| 4 | 9 | Ground Development and Landscape |  | Fence |  | Admin | a) | 1000000 | a) | ,11/4/2019 | e) | - | a) | 1000000 | a) | - | c) | 21.38 | a) | - | On-going |  | 1
[8 empty] | b) | - | b) | 01/31/2020 | f) | - | b) | 1000000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | PEO | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | 89 CD | d) | - | [12 empty] | 1
|  | TALAINGOD | [21 empty] | FS
| 8 | 1 | Const. of Covered Court Bleacher. |  | Elect. |  | Barangay | a) | 500000 | a) | 12/28/17 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Fund already transferred at Municipality of Talaingod with ChecK No. 2445181 and OR # 7955667, dated March 16, 2018 . Amended from Electrification @ Prk. 1A-Prk. 5A |  | 1
|  |  | Palma Gil, Talaingod |  |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) |  | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
|  | CARMEN | [19 empty] | declared as savings, forwarded to 2020 priority list of projects |  | AC
|  | 1 | Construction of Concrete Pavement |  | Pavement |  | Barangay | a) | 500000 | a) | 03/16/18 | e) | - | a) | 500000 | a) | - | c) | - | a) | - |  |  | 2
|  |  | Tibulao, Carmen |  |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | 2 | Construction of Evaluation Center at Prk. 1, |  | Bldg. |  | Barangay | a) | 500000 | a) | 12/28/17 | e) | - | a) | 500000 | a) | - | c) | 100% | a) | - | Completed |  | 2
|  |  | Asuncion, Carmen |  |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | 5 | Evacuation Center, Anibongan, Carmen |  | Bldg. |  | Barangay | a) | 500000 | a) | 03/16/18 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | declared as savings, forwarded to 2020 priority list of projects |  | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | 7 | Const. of Canal Lining @ Brgy. Site, |  | Canal |  | - | a) | 500000 | a) | 03/16/18 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | declared as savings, forwarded to 2020 priority list of projects |  | 2
|  |  | Tubod, Carmen |  | Lining |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | 9 | Rehab./Impv't. of Minda Brgy. Hall, |  | Bldg. |  | Barangay | a) | 500000 | a) | 05/10/18 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | declared as savings, forwarded to 2020 priority list of projects |  | 2
|  |  | Minda, Carmen |  |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | PANABO CITY | [21 empty] | AC
|  | 1 | Const of Market Stall/Building, Consolacion, |  | Bldg. |  | Barangay | a) | 500000 | a) | 12/28/17 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Fund transfer to LGU- 3/28/2019 with check no.2574928 and OR no. 0166514 - Issued warning for Termination of the Contract |  | 2
|  |  | Panabo CIty |  |  |  |  | b) | - | b) | 5/28/2019 | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | 2 | Rehab. Of Multi-Purpose Hall (Covered Court), |  | Footbridge |  | Barangay | a) | 500000 | a) | 12/28/17 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Fund transfer to LGU- 3/28/2019 with check no.2574927 and OR no. 0166516 - Delivery of Materials on process |  | 2
|  |  | Upper Licanan, Panabo City |  |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | 5 | Impv't. of Multi-Purpose Gym, Kauswagan, |  | GYM |  | Barangay | a) | 500000 | a) | 02/04/19 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Fund transfer to LGU- 3/28/2019 with check no.2574942 and OR no. 0166515 - procurement on process for bidding 8/5/2019 |  | 2
|  |  | Panabo CIty |  |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | 9 | Const. of MP Bldg. w/ Electrical installation, |  | Bldg. |  | Barangay | a) | 500000 | a) | 01/31/18 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Fund transfer to LGU- 3/28/2019 with check no. 2574942 and OR no 01665515 - procurement on process |  | 2
|  |  | San Roque, Panabo City |  |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | 14 | Const. of Multi-Purpose Bldg. (Back Stage/Office), San Nicolas, |  | Bldg. |  | Barangay | a) | 500000 | a) | 12/28/17 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Completed based on POW. Financial Documents on process |  | 2
|  |  | San Nicolas, Panabo City |  |  |  |  | b) | - | b) | 5/21/2019 | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | 16 | Const. of Multi-Purpose Bldg., |  | Bldg. |  | Barangay | a) | 300000 | a) | 12/19/17 | e) | - | a) | 300000 | a) | - | c) | - | a) | - | Issued warning for termination of the contract |  | 2
|  |  | Cacao, Panabo City |  |  |  |  | b) | - | b) | 12/14/2018 | f) | - | b) | 300000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | 17 | Const. of Multi-Purpose Bldg. @ A.O. Floriendo |  | Bldg. |  | Barangay | a) | 500000 | a) | 12/19/17 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Fund transfer to LGU- 3/28/2019 with check no. 2574939 and OR no. 0166518 - Materials Delivered. Construction on-going |  | 2
|  |  | National Highschool, Panabo City |  |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | STO. TOMAS | [21 empty] | AC
|  | 1 | Renov. Of Brgy. Hall, Esperanza, |  | Bldg. |  | - | a) | 500000 | a) | 12/28/17 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | declared as savings, forwarded to 2020 priority list of projects |  | 2
|  |  | Panabo City |  |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | 2 | Const. of Concrete Drainage Canal, Kimamon, |  | Drainage |  | Barangay | a) | 500000 | a) | 12/19/17 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | on-going |  | 2
|  |  | Panabo City |  |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | IGACOS | [21 empty] | AC
|  | 1 | Electrification of Prk. 4 & 6, Brgy. Toril, IGCS |  | Elect. |  |  | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | No abstract |  | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | PEO | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | 2 | Impv't. of Brgy. Street Electrification at |  | Elect. |  |  | a) | 500000 | a) | 11/28/17 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Verified at PBO 7/18/2019 that fund is not available. Proposed priority project for 2020\ |  | 2
|  |  | Brgy. Anonang, IGCS |  |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | PEO | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | 3 | Impv't of Brgy. Hall, Tagpopongan |  |  |  |  | a) | 500000 | a) | 11/28/17 | e) | 259 | a) | 500000 | a) | - | c) | 100% | a) | - | Completed based on POW. Financial Documents on process |  | 2
|  |  | IGACOS |  |  |  |  | b) | Roque | b) | 9/17/2018 | f) | 30 | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | PEO | c) | 12/30/2018 | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | 10/15/2019 | [12 empty] | 2
| F. | SDH IGCS - CONST. IN PROGRESS - BLGS. CY 2017 | [21 empty] | AC
|  | 1 | Construction Perimeter Fence Ph.II (Hospital |  | Fence |  | Admin | a) | 1,305,000.00 | a) | 11/10/17 | e) | 392 | a) | 1,305,000.00 | a) | 100% | c) | 100% | a) | 4 | Completed based on POW. Financial Documents on process |  | AC
|  |  | Compound) Samal District Hospital, IGCS |  |  |  |  | b) | Porras | b) | 03/12/18 | f) | 45 | b) | 1,305,000.00 | b) | - | d) | 1% | b) | 30 |  |  | AC
[8 empty] | c) | PEO | c) | 06/19/18 | g) | - | c) | 958,597.98 | [8 empty] | AC
[8 empty] | d) | - | d) | [13 empty] | AC
|  | 2. Const./Rehab./Comp. of Various Gov't. Bldgs. |  |  | Bldg. | - | Admin | a) | 9,000,000.00 | [12 empty] | Investigation/Inspection of priority projects |  | 2
|  | Struct., Fac. (Provincewide) | [5 empty] | b) | Foronda/Ababon | [14 empty] | AC
[8 empty] | c) | PEO | [14 empty] | AC
[8 empty] | d) | - | [14 empty] | AC
| 11 | 2.1 | Rehab. Of PEO Training Center |  | Bldg. |  | Admin | a) | 476,876.00 | a) | 02/12/19 | e) | - | a) | 476,876.00 | a) | 22.82% | c) | 22.82% | a) | 8 | On-going |  | 1
|  |  | (PDPM),Mankilam, Tagum City |  |  |  |  | b) | Chua | b) | 2019-04-11 | f) | - | b) | 476,876.00 | b) | - | d) | 0% | b) | - |  |  | 1
|  |  | (Part of P803,000.00)(20% DF CY 2018-P326,124.00) |  |  |  |  | c) | PEO | c) | 01/17/19 | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
|  | 2.2 | Repair/Rehab. Of PEO Building |  | Bldg. |  | Admin | a) | 1,800,000.00 | a) | 07/31/18 | e) | - | a) | 1,800,000.00 | a) | 62.23% | c) | 100% | a) | 5 | Completed based on POW. Financial Documents on process |  | 1
| 11 |  | (Motorpool),Mankilam, Tagum City |  |  |  |  | b) | Chua | b) | 03/04/19 | f) | - | b) | 1,800,000.00 | b) | - | d) | 37.77% | b) | 105 |  |  | 1
[8 empty] | c) | PEO | c) | 08/10/19 | g) | - | c) | 1481510.07 | [8 empty] | 1
[8 empty] | d) | 160 CD | d) | - | [12 empty] | 1
|  | 2.3 | Improvement of Garciaville Day Care |  | Bldg. |  | Admin | a) | 330,000.00 | a) | 11/06/18 | e) | - | a) | 330,000.00 | a) |  | c) | 100% | a) | 3 | Completed based on POW. Financial Documents on process |  | 1
| 11 |  | Center, Mankilam, Tagum City |  |  |  |  | b) | - | b) | 09/02/19 | f) | - | b) | 330,000.00 | b) | - | d) |  | b) | 90 |  |  | 1
[8 empty] | c) | PEO | c) | 10/11/19 | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
|  | 3. Rural Electrification (Provincewide) |  |  | Elect. |  | - | a) | 5000000 | [12 empty] | See projects listed below |  | AC
[8 empty] | b) | Foronda | [14 empty] | AC
[8 empty] | c) | - | [14 empty] | AC
[8 empty] | d) | - | [14 empty] | AC
|  | 3.1 | Electrification of Purok 1-4, Sta. Cruz, |  | Elect. |  | Admin | a) | 2,500,000.00 | a) | 02/04/19 | e) | - | a) | 2,500,000.00 | a) | 10% | c) | 12% | a) | - | On-going |  | 1
| 5 |  | New Corella |  |  |  |  | b) | - | b) | - | f) | - | b) | 2,500,000.00 | b) | - | d) | 2% | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| B.3 | Supplemental Budget # 4 CY 2017 | [21 empty] | FS
| 11 | 1 | Upgrading of DDNSTC (Basketball/Voleyball |  | Covered | 2252.69 sq.m | Contract | a) | 99992356.64 | a) | 10/16/18 | e) | - | a) | 99992356.64 | a) | 100% | c) | 72.6% | a) | 5 | On-going |  | 1
|  |  | MP Covered Court),Sports Center, Mankilam, |  | Court |  |  | b) | Escurzon | b) | 07/17/18 | f) | 20 CD | b) | 99992356.64 | b) | - | d) | -27.4% | b) | 150 |  |  | 1
|  |  | Tagum City |  |  |  |  | c) | YBC | c) | 07/11/19 | g) | - | c) | 18, 280, 402.33 | [8 empty] | 1
[8 empty] | d) | 360 CD | d) | 07/31/19 | [12 empty] | 1
| C.1 | Trust Fund 2014 | [21 empty] | FS
|  | 1. PAMANA-DILG CY 2014 | [21 empty] | AC
| 4 | 1.1 Construction of Biga Bridges, Kapalong |  |  | Road | 2-18ln.m | Contract | a) | 24959503.45 | a) | CY 2014 | e) | 304 CD | a) | 24959503.45 | a) | 100.00% | c) | 85.37% | a) | 8 | On-going |  | 1
[8 empty] | b) | Limpo | b) | 07/01/16 | f) | - | b) | 24959503.45 | b) | 99.7% | d) | -14.33% | b) | 290 |  |  | 1
[8 empty] | c) | Dvo. Rock Mixer | c) | 07/30/18 | g) | - | c) | 37,439,255.18 | [6 empty] | Issued warning letter & submit catch-up plan |  | 1
[8 empty] | d) | 880 CD | d) | 09/27/19 | [12 empty] | 1
| 4 | 1.2 Road Rehabilitation/Improvement of Prk. 3, |  |  | Road | 13.60 kms | Contract | a) | 50,500,288.95 | a) | CY 2014 | e) | - | a) | 50,500,288.95 | a) | 100.00% | c) | 100% | a) | 25 | Completed based on Physical Accomplishment. Financial Document on process |  | 1
|  | Palma Gil-Prk.2 (side 2), Sto. Niño-Mahayahay-Tugas- | [5 empty] | b) | Dadula | b) | 07/07/16 | f) | 398 CD | b) | 50,500,288.95 | b) | 100% | d) | 0% | b) | 750 |  |  | 1
|  | Nanaga Road, with 1 -unit, 40 ln.m PSCG Bridge, |  |  |  | 40 ln.m |  | c) | Puregold | c) | 03/12/18 | g) | - | c) | 41424313.06 | [8 empty] | 1
|  | Kapalong | [5 empty] | d) | 1011 CD | d) | 04/14/19 | [12 empty] | 1
| C.2 | Trust Fund 2015 | [21 empty] | FS
|  | 1. PRDP CY 2015 | [21 empty] | AC
| 4 | 1.1 Rehab. Of Capungagan-Boundary San |  |  | Road | 10.6 kms. | Contract. | a) | 108,303,841.70 | a) | CY 2015 | e) | 140 CD | a) | 108,303,841.70 | a) | 100.00% | c) | 93.23% | a) | 38 | On-going |  | 1
|  | Miguel FMR, Kapalong, Davao del Norte | [5 empty] | b) | Nasol | b) | 04/06/16 | f) | 634 | b) | 108,303,841.70 | b) | 96.05% | d) | -2.82% | b) | 1140 | Increase of Project Cost due to Variation Order with |  | 1
[8 empty] | c) | VICLAO | c) | 03/26/17 | g) | - | c) | 38,212,432.90 | [6 empty] | Extra Work. (Php 4,992,591.29) |  | 1
[8 empty] | d) | 1352 | d) | 12/18/2019 | [12 empty] | 1
| 5 | 1.2 Rehab. Of Pob.-Limbaan-Suawon-Macgum |  |  | Road | 15.01 kms./ | Contract. | a) | 205,202,114.16 | a) | CY 2015 | e) | 229 CD | a) | 205,202,114.16 | a) | 100.00% | c) | 71.41% | a) | 40 | On-going |  | 1
|  | FMR w/ Bridge, New Corella, Davao del Norte |  |  |  | 42 ln.m |  | b) | Madrigal | b) | 04/08/16 | f) | 490 CD | b) | 205,202,114.16 | b) | 82.51% | d) | -11.1% | b) | 1200 | Increase of Project Cost due to Variation Order Php 14,948,622.18 |  | 1
[8 empty] | c) | Dvo. Rock Mixer | c) | 01/18/19 | g) | - | c) | 28538091.3 | [8 empty] | 1
[8 empty] | d) | 1529CD | d) | 06/14/20 | [10 empty] | Partial suspension due to soft soil from sta. 8+000 - 10+000 |  | 1
| 1 | 1.3 Rehab. Of Sonlon - Camansa FMR |  |  | Road |  | Contract. | a) | 215125015.81 | a) | 9/18/2018 | e) |  | a) | 215125015.81 | a) | 24.63% | c) | 23% | a) | 30 | On-going |  | 1
|  | Asuncion, Davao del Norte | [5 empty] | b) | Fabiala | b) | 5/28/2019 | f) |  | b) | 215125015.81 | b) |  | d) | -1.63% | b) | 780 |  |  | 1
[8 empty] | c) | Three w/Builders, Inc? Davao Rock Mixer Enterprises (JV) | c) | 12/31/2020 | g) | - | c) | [9 empty] | 1
[8 empty] | d) | 1529CD | d) | 06/14/20 | [12 empty] | 1
|  | 2. KALSADA CY 2015 | [21 empty] | AC
| 6 | 2.1 Improvement of Km. 9 Sagayen-Sawata Provincial |  |  | Road | 3177 ln.m m | Contract | a) | 47213478.31 | a) | CY 2015 | d) | - | a) | 47213478.31 | a) | 100.00% | c) | 37.556% | a) |  | Contract Terminated |  | 1
|  | San Isidro, Davao del Norte | [5 empty] | b) | Limpo | b) | 08/26/16 | e) |  | b) | 47213478.31 | b) | 86.25% | d) | -48.69% | b) |  |  |  | 1
[8 empty] | c) | Arn Builders | c) | 04/21/18 | f) | - | c) | 24931805.19 | [8 empty] | 1
[8 empty] | d) |  | d) | [13 empty] | 1
| 6 | 2.2 Improvement of Km. 9 Sagayen-Sawata Provincial |  |  | Road | 6667.54 m | Admin | a) | 33401544.78 | a) | CY 2015 | d) | - | a) | 33401544.78 | a) | 51.85% | c) | 94.66% | a) | 30 | Original contract terminated due to very poor performance |  | 1
|  | San Isidro, Davao del Norte | [5 empty] | b) | Limpo | b) | 10/16/18 | e) |  | b) | 33401544.78 | b) | 95.76% | d) | -8.05% | b) | 900 | of the contractor.The contract cost P 47,213,478.31. |  | 1
[8 empty] | c) | PEO | c) | 09/14/19 | f) | - | c) | 19,943,597.92 | [6 empty] | On-going |  | 1
[8 empty] | d) | 334 CD | d) | [13 empty] | 1
| C.3 | Trust Fund 2016 | [21 empty] | FS
|  | 1. PRDP CY 2016 | [21 empty] | AC
| 4 | 1.1 | Cacao Production and Beans Marketing, |  | Bldg. | - | Contract. | a) | 5873626.8 | a) | CY 2016 | e) | - | a) | 5873626.8 | a) | 90.86% | c) | 84.06% | a) | 9 | On-going |  | 1
|  |  | Capungagan, Kapalong, Davao del Norte |  |  |  |  | b) | Delos Reyes | b) | 03/19/19 | f) | - | b) | 5873626.8 | b) | - | d) | -6.798% | b) | 63 | Suspension Letter on process due to |  | 1
[8 empty] | c) | MICAH CONST. & SUPPLY | c) | 11/23/19 | g) | - | c) | - | [6 empty] | modification of Detailed Design of |  | 1
[8 empty] | d) | 250 CD | d) | - | [10 empty] | mechanical Drier |  | 1
| C.4 | Trust Fund 2017 | [21 empty] | FS
|  | 1. CMGP (Conditional Matching Grant to Provinces) | [21 empty] | AC
| 6 |  | Road Upgrading km.9 sagayen-Sawata |  | Road | 10.20 km | Contract | a) | 139,761,975.14 | a) | CY 2017 | e) | - | a) | 139,761,975.14 | a) | 93.839 | c) | 93.27 | a) | 28 | On-going |  | 1
|  |  | (Sagayen-Jct. San Miguel Section) |  |  |  |  | b) | Avila | b) | 10/01/18 | f) | - | b) | 139,761,975.14 | b) | - | d) | -0.569 | b) | 11170 |  |  | 1
[8 empty] | c) | Legacy Const. Corp. | c) | 08/22/19 | g) | - | c) | 63100753.7 | [8 empty] | 1
[8 empty] | d) | 326 CD | d) | - | [12 empty] | 1
| 8 |  | Road Upgrading of Dagohoy - Daligdigon |  | Road | 2.532 km | Contract | a) | 58048310.68 | a) | CY 2017 | e) | - | a) | 58048310.68 | a) | 100.00% | c) | 100% | a) | 16 | Completed as per Physical Accomplishment, Financial Documents on Process |  | 1 | 1
|  |  | Provincial Road |  |  |  |  | b) | Fabiala | b) | 01/05/18 | f) | 205 CD | b) | 58048310.68 | b) | - | d) | 0% | b) | 480 |  |  | 1
[8 empty] | c) | PUREGOLD | c) | 11/18/18 | g) | - | c) | 29,572,637.70 | [8 empty] | 1
[8 empty] | d) | 246 CD | d) | 03/31/19 | [12 empty] | 1
|  |  | Impv’t. of Maligaya-New Camiling Prov’l. |  | Conc. | 2.13 km | Contract. | a) | 50101614.08 | a) | CY 2017 | e) | 76 CD | a) | 57385680 | a) | 100.00% | c) | 100% | a) | 21 | Completed based on POW. Financial Documents on process |  | 2
|  |  | Road w/ Bridge Component,Carmen |  |  |  |  | b) | Mellomida | b) | 12/18/17 | f) | 209 CD | b) | 57385680 | b) | 100% | d) | 0% | b) | 147 |  |  | 2
[8 empty] | c) | PUREGOLD CONST. | c) | 02/15/19 | g) | - | c) | 36005452 | [8 empty] | 2
[8 empty] | d) | 376 CD | d) | 07/31/19 | [12 empty] | 2
|  |  | Road Upgrading of FDR. Rd.3 – |  | Conc. | 10.359 km | Contract. | a) | 119901954.82 | a) | CY 2017 | e) | 47 CD | a) | 119901954.82 | a) | 100.00% | c) | 100% | a) | 10 | Completed based on POW, Financial Documents on Process |  | 2
|  |  | Kimamon – Luna Provincial Road, |  |  |  |  | b) | Comidoy | a) | 12/29/17 | f) | 198 CD | b) | 119901954.82 | b) | 100% | d) | 100% | b) | 220 |  |  | 2
|  |  | Sto. Tomas |  |  |  |  | c) | GP & H CONST. | c) | 12/12/18 | g) | - | c) | 119901954.82 | [8 empty] | 2
[8 empty] | d) | 326 CD | d) | 2019-07-29 | [12 empty] | 2
|  |  | Road Upgrading of Anahaw-Maligaya |  | Conc. | 5.18 km | Contract. | a) | 78,228,121.56 | a) | CY 2017 | e) | - | a) | 78,228,121.56 | a) | 100.00% | c) | 100% | a) | 30 | 100% as of August 31, 2019 |  | 2
|  |  | Provincial Road, Carmen |  |  |  |  | b) | Fernandez | b) | 12/24/17 | f) | 306 CD | b) | 78,228,121.56 | b) | 100% | d) | 0% | b) | 660 | Subject for liquidated damages |  | 2
[8 empty] | c) | MONOLITHIC CONST. | c) | 03/31/19 | g) | - | c) | 76,214,361.38 | [8 empty] | 2
[8 empty] | d) | 210 CD | d) | 2019-06-05 | [12 empty] | 2
|  | 2. OPPAP-PAMANA | [21 empty] | AC
1
| 11 | 2.2 | Const. of Trading Post, Storage Building |  | Bldg. |  | Contract | a) | 3,975,000.00 | a) | CY 2017 | e) | - | a) | 3,975,000.00 | a) | - | c) | - | a) | - | Rebidding |  | 1
|  |  | with (1) unit Hauling Truck, Brgy. Pandapan |  |  |  |  | b) | - | b) | - | f) | - | b) | 3,975,000.00 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
|  | 2.1 | Const. of Trading Post, Storage Building |  | Bldg. |  | Contract | a) | 3,975,000.00 | a) | CY 2017 | e) | - | a) | 3,975,000.00 | a) | - | c) | - | a) | - | c/o Engr. Rickris Fernandez |  | 2
|  |  | with (1) unit Hauling Truck, Prk. Ramihan |  |  |  |  | b) | - | b) | - | f) | - | b) | 3,975,000.00 | b) | - | d) | - | b) | - |  |  | 2
|  |  | Datu Abdul, Panabo City |  |  |  |  | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | 2.2 | Construction of Tribal Hall, Sto. Tomas |  | Bldg. |  | Admin | a) | 500000 | a) | CY 2018 | e) | - | a) | 500000 | a) | 100% | c) | 89.5% | a) | 7 | Suspended 6/28/2019, Suspended due to Delivery of Materials J.O, For time extension |  | 2
[8 empty] | b) | Roque | b) | 2019-05-22 | f) | - | b) | 500000 | b) | - | d) | 0.79% | b) | 110 |  |  | 2
[8 empty] | c) | - | c) | 2019-07-31 | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
| C.5 | LDRRM - Trust Fund | [21 empty] | FS
| 5 | 1. Construction of Slope Protection and Concrete Pavement along Sta. Fe Mambing Road Section |  |  | Slope |  | Admin | a) | 1,853,000.00 | a) | 11/28/18 | e) |  | a) | 1,853,000.00 | a) | 100% | c) | 100% | a) | 16 | Completed based on POW. Financial Documents on process |  | 1
[8 empty] | b) | Gone | b) | 12/03/18 | f) | 108 CD | b) | 1,853,000.00 | b) | - | d) |  | b) | 144 |  |  | 1
[8 empty] | c) | PEO | c) | 02/28/19 | g) | 10/30/2019 | c) | 742252.72 | [8 empty] | 1
[8 empty] | d) | 86 CD | d) | 06/15/2019 | [12 empty] | 1
| 5 | 2. Rehab. Of Saug Bridge of Slope Protection |  |  | Slope |  | Admin | a) | 4,850,000.00 | a) | 05/25/18 | e) | - | a) | 4,850,000.00 | a) | 23.60% | c) | 9.60% | a) | - | Suspended dated 01/28/19 |  | 1
[8 empty] | b) | Gone | b) | 01/03/19 | f) | - | b) | 4,850,000.00 | b) |  | d) | -14% | b) | - |  |  | 1
[8 empty] | c) | PEO | c) | 03/25/19 | g) | - | c) | 1628912.92 | [8 empty] | 1
[8 empty] | d) | 82 CD | d) | - | [12 empty] | 1
| 1 | 3. Rehab. Of Canatan Bridge Slope Protection |  |  | Slope | 395 sq.m. | Contract | a) | 9200000 | a) | 06/20/2018 | e) | - | a) | 9200000 | a) | 100% | c) | 100% | a) | - | Completed |  | 1 | 1
|  | Brgy. Canatan, Asuncion | [5 empty] | b) | Aclaracion | b) | 02/11/2019 | f) | 35 CD | b) | 9200000 | b) | 100% | d) | 0% | b) | - |  |  | 1
[8 empty] | c) | J-One Builders | c) | 04/12/2019 | g) | 05/31/2019 | c) | 7222021.59 | [8 empty] | 1
[8 empty] | d) | 60 CD | d) | 05/01/2019 | [12 empty] | 1
| 4 | 4. Re-channeling of BIGA River with Earth Dike and Slope Protection, Brgy. Gupitan, Kaplaong |  |  | Dike/Slope |  | Contract | a) | 12,100,000.00 | a) | 07/20/18 | e) | - | a) | 12,100,000.00 | a) | 8.30% | c) | 3.36% | a) | 4 | Suspended dated March 25, 2019 |  | 1
[8 empty] | b) | Limpo | b) | 02/22/19 | f) | - | b) | 12,100,000.00 | b) |  | d) | -4.94% | b) | 120 | Due to boundary conflict. |  | 1
[8 empty] | c) | Alpha & Omega | c) | 06/11/19 | g) | - | c) | - | [6 empty] | Waiting for the decision from the Bureau of Land |  | 1
[8 empty] | d) | 110 CD | d) | 9/23/2019 | [12 empty] | 1
| 5 | 5. Const. of Cabidianan Bridge Slope Protection, Brgy. Cabidianan, New Corella |  |  | Slope |  | Admin | a) | 3590000 | a) | 07/18/18 | e) | - | a) | 3590000 | a) | 100% | c) | 100% | a) | 8 | Completed based on POW. Financial Documents on process |  | 1
[8 empty] | b) | Gone | b) | 6/17/19 | f) | - | b) | 3590000 | b) |  | d) |  | b) | 80 |  |  | 1
[8 empty] | c) | PEO | c) | 8/20/19 | g) | - | c) | 1929823.4 | [8 empty] | 1
[8 empty] | d) | 65 CD | d) | - | [12 empty] | 1
| D. | SEF(Special Education Fund)-SUPPLEMENTAL BUDGET # 1 CY 2017 | [21 empty] | FS
|  | 1. Const./Impv't./Compl. Of School Bldgs., Struc. & Fac. |  |  | Bldgs. |  | Admin | a) | 3,300,000.00 | [12 empty] | See projects listed below |  | AC
[8 empty] | b) | Foronda | [14 empty] | AC
[8 empty] | c) | PEO | [14 empty] | AC
[8 empty] | d) | - | [14 empty] | AC
| 8 | 1.1 | Construction of 1 unit School Building |  | Bldg. |  | Admin | a) | 1100000 | a) | 02/19/18 | e) | - | a) | 1100000 | a) | 100 | c) | 100 | a) | 6 | Completed based on POW. Financial Documents on process |  | 1
|  |  | Lumabag, Talaingod |  |  |  |  | b) | Dadula | b) | 03/20/19 | f) | 27 CD | b) | 1100000 | b) |  | d) |  | b) | 30 |  |  | 1
[8 empty] | c) | PEO | c) | 05/19/19 | g) | 06/30/2019 | c) | 595230.5 | [8 empty] | 1
[8 empty] | d) | 60 CD | d) | - | [12 empty] | 1
F. 20% Development Fund CY 2018 | [23 empty] | FS
|  | 1. Repair & Maint. Of Various Local Roads |  |  | Road | - | Admin | a) | 5000000 | [12 empty] | See projects listed below |  | AC
|  | and Drainages | [5 empty] | b) | [15 empty] | AC
[8 empty] | c) | Admin | [14 empty] | AC
[8 empty] | d) | - | [14 empty] | AC
|  | 1.1 | Rehabilitation of Brgy. San Antonio |  | Road |  | Admin | a) | 130000 | a) | 04/13/18 | e) | - | a) | 130000 | a) | - | c) | - | a) | - | Proposed priority project for 2020 |  | 2
|  |  | Barangay Road, IGACOS |  |  |  |  | b) | Porras/Pacquiao | b) | - | f) | - | b) | 130000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | PEO | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | 1.2 | Rehabilitation of Brgy. Peñaplata Barangay |  | Road |  | Admin | a) | 139000 | a) | 04/25/18 | e) | 66 CD | a) | 139000 | a) | 100% | c) | 100 | a) | 1 | Completed 8/31/2019 |  | 2
|  |  | Road, IGACOS |  |  |  |  | b) | Porras/Pacquiao | b) | 8/16/2019 | f) | 225 CD | b) | 139000 | b) | - | d) | - | b) | 1 |  |  | 2
[8 empty] | c) | PEO | c) | 8/31/2019 | g) | - | c) | 139000 | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | 1.3 | Rehabilitation of Brgy. Adecor Barangay |  | Road |  | Admin | a) | 138000 | a) | 04/25/18 | e) | 66 CD | a) | 138000 | a) | 60.00% | c) | 60.00% | a) | - | Completed as per POW. Financial Documents on process |  | 2
|  |  | Road, IGACOS |  |  |  |  | b) | Porras/Pacquiao | b) | 10/18/18 | f) | 225 CD | b) | 138000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | PEO | c) | 10/27/19 | g) | - | c) | 111,872.00 | [8 empty] | 2
[8 empty] | d) | - | d) | 10/15/2019 | [12 empty] | 2
|  | 1.4 | Rehabilitation of Brgy. Pob. Kaputian |  | Road |  | Admin | a) | 138000 | a) | 04/25/18 | e) | - | a) | 138000 | a) | 100% | c) | 100% | a) | 4 |  |  | 2
|  |  | Barangay Road, IGACOS |  |  |  |  | b) | Porras/Pacquiao | b) | 2019-08-08 | f) | - | b) | 138000 | b) | - | d) | - | b) | 36 | Completed Sept. 22, 2019 |  | 2
[8 empty] | c) | PEO | c) | 9/22/2019 | g) | 9/22/2019 | c) | - | [8 empty] | 2
[8 empty] | d) | 6/13/19 | d) | - | [12 empty] | 2
|  | 2. Various of Water System Project (Provincewide) |  |  | Water | - | - | a) | 10000000 | [12 empty] | Investigation/Inspection of priority projects |  | AC
[5 empty] | System |  |  | b) | Foronda/Misa | [14 empty] | AC
[8 empty] | c) | PEO | [14 empty] | AC
[8 empty] | d) | - | [14 empty] | AC
|  | 2.1 | Conduct of geo-resistivity/drilling test |  | Geo- | - | - | a) | 250000 | [12 empty] | See list of projects |  | AC
|  |  | of proposed site |  | resistivity |  |  | b) | Diosanta | [14 empty] | AC
[8 empty] | c) | - | [14 empty] | AC
[8 empty] | d) | - | [14 empty] | AC
| 6 |  | 2.1.1 Const. of PWS Linao, San Isidro |  | Water | - | - | a) | 62000 | a) | - | e) | - | a) | 62000 | a) | - | c) | - | a) | - | PO approved September 2, 2019 |  | 1
[5 empty] | System |  |  | b) | - | b) | - | f) | - | b) | 62000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| 6 |  | 2.1.2 Const. of PWS Mamalian, San Isidro |  | Water | - | - | a) | 62000 | a) | - | e) | - | a) | 62000 | a) | - | c) | - | a) | - | For declaration of savings because the spring water source is not feasible for development. |  | 1
[5 empty] | System |  |  | b) | - | b) | - | f) | - | b) | 62000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| 6 |  | 2.1.3 Const. of PWS Sagayen, San Isidro |  | Water | - | - | a) | 62000 | a) | - | e) | - | a) | 62000 | a) | - | c) | - | a) | - | Waiting for the geo-resistivty equipment. |  | 1
[5 empty] | System |  |  | b) | - | b) | - | f) | - | b) | 62000 | b) | - | d) | - | b) | - | (Geo-resistivty equipment PR on process) |  | 1
[8 empty] | c) | PEO | c) | - | g) | - | c) | - | [6 empty] | Aug. 13, 2019 |  | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
|  | 2.2 | Construction of Water System Projects |  | Water | - | - | a) | 9750000 | [12 empty] | See list of projects |  | AC
|  |  | in Component LGUs |  | System |  |  | b) | Diosanta | [14 empty] | AC
[8 empty] | c) | PEO | [14 empty] | AC
[8 empty] | d) | - | [14 empty] | AC
| 11 |  | Installation of potable water System at Purok |  | Water | - | - | a) | 1125000 | a) | - | e) | - | a) | 1125000 | a) | - | c) | - | a) | - | Waiting for deed of donation. Follow-up letter was already issued |  | 1
|  |  | Nangka, Pandapan, Tagum City |  | System |  |  | b) | - | b) | - | f) | - | b) | 1125000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | PEO | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| 1 |  | Rehab./Impv't. of San Vicente |  | Water | - | - | a) | 1125000 | a) | 10/26/18 | e) | - | a) | 1125000 | a) | - | c) | - | a) | - | PO on process |  | 1
|  |  | Water System, Asuncion |  | System |  |  | b) | - | b) | - | f) | - | b) | 1125000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | PEO | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
|  |  | Impv't. of Water System, Brgy. Poblacion |  | Water |  | Admin | a) | 1250000 | a) | 08/24/18 | e) | - | a) | 1250000 | a) | 100% | c) | 85.39% | a) | 8 | Completed (contract by Zular3-Az) September 15, 2019 |  | 2
|  |  | Kaputian (Level II) |  | system |  |  | b) | Porras | b) | 05/3/19 | f) | - | b) | 1250000 | b) | - | d) | -14.61 | b) | 160 |  |  | 2
[8 empty] | c) | Contract | c) | 08/30/19 | g) | 09/15/2019 | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  |  | Water System at brgy. Malativas, |  | Water |  | Admin | a) | 1250000 | a) | - | e) | - | a) | 1250000 | a) | - | c) | - | a) | - | For preparation of POW & Plan c/o PDPM - POSSIBLE TRANSFER OF SITE SUBJECT FOR TRANSFER OF LOCATION . NO DEED OF DONATION |  | 2
|  |  | Panabo City |  | system |  |  | b) | - | b) | - | f) | - | b) | 1250000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | Admin | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  |  | Const. of Potable Water System at |  | Water |  | Admin | a) | 1250000 | a) | 11/21/18 | e) | - | a) | 1250000 | a) | - | c) | - | a) | - | for implementation |  | 2
|  |  | Brgy. Tibungol, Panabo City |  | system |  |  | b) | - | b) | - | f) | - | b) | 1250000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | Admin | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  |  | Potable Water System at Brgy. San |  | Water |  | Admin | a) | 3625000 | a) | 10/25/18 | e) | - | a) | 3625000 | a) | 49.51% | c) | 54.96% | a) | 3 | On-going |  | 2
|  |  | Remegio Kaputian (Level II WS), Samal |  | system |  |  | b) | Diosanta | b) | 7/16/2019 | f) | - | b) | 3625000 | b) | - | d) | 4.62 | b) | 20 |  |  | 2
[8 empty] | c) | Admin | c) | 12/2019 | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | 3. Counterpart to Special Projects (Provincewide) |  |  | Road | - | Contract | a) | 67415000 | [12 empty] | Investigation/Inspection of priority projects |  | AC
[8 empty] | b) | Foronda | [14 empty] | AC
[8 empty] | c) | PEO | [14 empty] | AC
[8 empty] | d) | - | [14 empty] | AC
| 1 | 3.1 | Rehab. Of Sonlon-Camansa FMR, |  | Road | - | Contract | a) | 21512501.501 | a) | 09/18/18 | e) | - | a) | 21512501.501 | a) | 9.332% | c) | 6.249% | a) | - | On-going |  | 1
|  |  | Asuncion, Davao del Norte |  |  |  |  | b) | Fabiala | b) | 5/28/2019 | f) | - | b) | 21512501.501 | b) | - | d) | -3.083% | b) | - |  |  | 1
|  |  | (PRDP Counterpart : 193,612,514.23) |  |  |  |  | c) | - | c) | 12/31/2020 | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) |  | d) | - | [12 empty] | 1
|  | 4. Const./Rehab./Comp. of Various Gov't. Bldgs. |  |  | Bldgs. | - | Admin | a) | 13523124 | [12 empty] | Investigation/Inspection of priority projects |  | AC
|  | Struct., Fac. (Provincewide) | [5 empty] | b) | Foronda | [14 empty] | AC
[8 empty] | c) | PEO | [14 empty] | AC
[8 empty] | d) | - | [14 empty] | AC
| 11 | 4.1 | Rehab. Of PEO Training Center |  | Bldg. |  | Admin | a) | 476876 | a) | 02/12/19 | e) | - | a) | 476876 | a) | - | c) | 9.17% | a) | - | On-going |  | 1
|  |  | (PDPM),Mankilam, Tagum City |  |  |  |  | b) | Chua | b) | - | f) | - | b) | 476876 | b) | - | d) | - | b) | - |  |  | 1
|  |  | (Part of P803,000.00)(20% DF CY 2017-P476,876.00) |  |  |  |  | c) | PEO | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| 1 | 4.2 | Construction of IP Tribal Council of |  | Bldg. |  | Admin | a) | 560,000.00 | a) | - | e) | - | a) | 560,000.00 | a) | - | c) | - | a) | - | POW & Plan for approval |  | 1
|  |  | Women at Brgy. Camansa, Asuncion |  |  |  |  | b) | - | b) | - | f) | - | b) | 560,000.00 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | PEO | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| 11 | 4.3 | Construction of Multi-Purpose Bldg. |  | Bldg. | 303.75 sq.m | Admin | a) | 6748000 | a) | 12/11/18 | e) | - | a) | 6748000 | a) |  | c) | 100% | a) | 25 | Completed |  | 1
|  |  | (PENRO Building), Mankilam, Tagum City |  |  |  |  | b) | Pasiona/Juan | b) | 10/16/18 | f) | 109 | b) | 6748000 | b) | - | d) |  | b) | 750 |  |  | 1
|  |  | (Part of 8,548,000.00) |  |  |  |  | c) | PEO | c) | 9/13/2019 | g) | - | c) | 6560497.45 | [8 empty] | 1
|  |  | (P1,800,000.00 - SB # 3 CY 2017) |  |  |  |  | d) | 256 CD | d) | 06/30/19 | [12 empty] | 1
| 3 | 4.4 | Repair/Rehab. Of PEO Building (2nd District), Carmen |  | Bldg. |  | Admin | a) | 2250000 | a) | 08/10/18 | e) | - | a) | 2250000 | a) | 100% | c) | 100% | a) | 18 | Completed based on POW. Financial Documents on process |  | 2
[8 empty] | b) | Andoy | b) | 02/18/19 | f) | - | b) | 2250000 | b) | - | d) | 0% | b) | 138 |  |  | 2
[8 empty] | c) | Admin | c) | 08/23/19 | g) | - | c) | 1577344.8 | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | 5. Rural Electrification (Provincewide) |  |  | Elect. |  | Admin | a) | 5000000 | [12 empty] | See projects listed below |  | AC
[8 empty] | b) | Kim Pao Lu | [14 empty] | AC
[8 empty] | c) | PEO | [14 empty] | AC
[8 empty] | d) | - | [14 empty] | AC
| 5 | 5.1 | Rural Electrification at Del Monte, |  | Elect. |  | Admin | a) | 1000000 | a) | - | e) | - | a) | 1000000 | a) | - | c) | - | a) | - | Revised POW for Approval. Change of Implementation Mode from Admin to Contract 9/6/2019 |  | 1
|  |  | New Corella |  |  |  |  | b) | - | b) | - | f) | - | b) | 1000000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| 1 | 5.2 | Const. of Distribution Line in Sitio Prk. 1,3,4, |  | Elect. |  | Admin | a) | 4000000 | a) | 11/06/18 | e) | - | a) | 4000000 | a) | - | c) | - | a) | - | For PR |  | 1
|  |  | 11 and 7, Camansa, asuncion |  |  |  |  | b) | - | b) | - | f) | - | b) | 4000000 | b) | - | d) | - | b) | - | Revised POW from Admin to Contract |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
A. 20% Development Fund CY 2018 | K. | GENERAL FUND PROPER CY 2018 | [21 empty] | FS
|  | STIMULUS PROJECTS | [21 empty] | AC
|  | ASUNCION | [21 empty] | AC
| 1 | 1 | Const. of Bleachers and Canopy, |  | Bldg. |  | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Procurement on Process |  | 1
|  |  | Canatan, Asuncion |  |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| 1 | 2 | Const. of Potable water System at Prk. 6, |  | Water |  | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Inspected – Aug. 6, 2019 For plan preparation c/o Amamio |  | 1
|  |  | New Santiago, Asuncion |  | System |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| 1 | 3 | Const. of Canopy, Camoning, Asuncion |  | Bldg. |  | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | P.O. on process |  | 1
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| 1 | 4 | Completion of Electrification at Prk. 10 |  | Elect. |  | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Proposed for future funding. Insufficient Budget to complete the project |  | 1
|  |  | & Prk. 9, Doña Andrea, Asuncion |  |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| 1 | 5 | Construction of Covered Court, |  | Court |  | - | a) | 500000 | a) | 06/05/18 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | for Fund Transfer |  | 1
|  |  | San Vicente, Asuncion |  |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| 1 | 6 | Const. Of Multi-purpose covered court Phase 2 |  | landscaping |  | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Amended from Landscaping and Beautification of Brgy. Ground to fund completion of priority project. Plan and POW for approval |  | 1
|  |  | Brgy. Ground, Pamacaun, Asuncion |  |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
|  | NEW CORELLA | [21 empty] | AC
| 5 | 1 | Const. of Concrete Bleachers, Sta. Cruz, |  | Bleacher |  | - | a) | 500000 | a) | 06/04/18 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Fund transferred to LGU - May 23, 2019 with check no. 0133011 and OR no. 9232849. On going |  | 1
|  |  | New Corella |  |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| 5 | 2 | Completion of Mini GYM at Prk. 2, |  | GYM |  | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Fund transferred to LGU - May 23, 2019 with check no. 0133010 and OR no. 9232850. On going |  | 1
|  |  | San Roque, New Corella |  |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| 5 | 3 | Completion of Covered Court, Sto. Niño, |  | Court |  | - | a) | 500000 | a) |  | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Fund transferred to LGU - May 23, 2019 with check no. 0133012 and OR no. 9232848. On going |  | 1
|  |  | New Corella |  |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| 5 | 4 | Construction of Public Market, Suawon, |  | Bldg. |  | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Fund transferred to LGU - May 23, 2019 with check no. 0133014 and OR no. 9232846. On going |  | 1
|  |  | New Corella |  |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| 5 | 5 | Construction of Concrete Line Drainage at |  | Drainage |  | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Fund transferred to LGU - May 23, 2019 with Check No. 2575058 and OR No. 0342801. On going |  | 1
|  |  | Prk. 10 to Prk. 6, Del Pilar, New Corella |  |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| 5 | 6 | Construction of Stage with Comfort Rooms |  | Bldg. |  | - | a) | 500000 | a) | 07/05/18 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Fund transferred to LGU - May 23, 2019 with check no. 0133013 and OR no. 9232847. On going |  | 1
|  |  | at Mesaoy Mini-Gym, Mesaoy, New Corella |  |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
|  | TAGUM CITY | [21 empty] | AC
| 11 | 2 | Completion of Two Storey Multi-Purpose |  | Bldg. |  | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | 100% | c) | 100% | a) | 5 | Completed based on Physical Accomplishment. Financial Documents on process |  | 1
|  |  | Building, Magugpo East, Tagum City |  |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | 0% | b) | 110 |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| 11 | 3 | Completion of GYM Bleacher w/ |  | Bleacher |  | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | for implementation |  | 1
|  |  | Electrification, Pagsabangan, Tagum City |  |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| 11 | 4 | Construction of Drainage Canal, |  | Drainage |  | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Waiting for delivery of materials |  | 1
|  |  | Libuganon, Tagum City |  |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
|  | KAPALONG | [21 empty] | AC
| 4 | 1 | Construction of Bleacher, Mamacao, |  | Bleacher |  | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Procurement of Materials on process |  | 1
|  |  | Kapalong |  |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| 4 | 2 | Improvement of Capungagan GYM Stage, |  | Stage |  | - | a) | 500000 | a) | 06/05/18 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Re-aligned to proposed project for CY 2020. |  | 1
|  |  | Capungagan, Kapalong |  |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| 4 | 3 | Construction of Concrete Perimeter Fence, |  | Fence |  | Contract | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Procurement of Materials on process |  | 1
|  |  | Luna, Kapalaong |  |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| 4 | 4 | Construction of 1 Unit 2 Classroom |  | Bldg. |  | Contract | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Needs additional funds to complete the project |  | 1
|  |  | School Bldg. at Sampao, kapalong |  |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| 4 | 5 | Completion of Brgy. Health Center, Maniki, |  | Bldg. |  | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Waiting for on-going works funded by other agency to complete. |  | 1
|  |  | Kapalong |  |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
|  | SAN ISIDRO | [21 empty] | AC
| 6 | 1 | Improvement of Water System, Sabangan, |  | Water |  | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | To change priority but not yet submitted new resolution c/o Engr. Amamio |  | 1
|  |  | San Isidro |  | System |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| 6 | 2 | Rehabilitation & Flooring of Gymnasium |  | Court |  | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | 37% | c) | 42% | a) | - | On-going |  | 1
|  |  | Basketball Court, Mamangan, San Isidro |  |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | 5% | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
|  | TALAINGOD | [21 empty] | AC
| 8 | 1 | Grouted Riprap on Embankment |  | Riprap |  | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Plan and POW on process c/o PDPM |  | 1
|  |  | Sto. Ñino, Talaingod |  |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| 8 | 2 | Barangay Hall Improvement, Dagohoy, |  | Bldg. |  | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Plan and POW on process c/o PDPM |  | 1
|  |  | Talaingod |  |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| 8 | 3 | Construction of 2 Classroom Building Datu Jose |  | Bldg. |  | - | a) | 2000000 | a) | - | e) | - | a) |  | a) | - | c) | - | a) | - |  |  | 1
|  |  | Libayao NHS Ext, |  |  |  |  | b) | - | b) | - | f) | - | b) |  | b) | - | d) | - | b) | - |  |  | 1
|  |  | Natulian, Palma Gil, Talaingod |  |  |  |  | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
|  | CARMEN | [19 empty] | Plan and POW Approval on process |  | AC
|  | 1 | Completion of Evacuation Center Building, |  | Bldg. |  | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - |  |  | 2
|  |  | San Isidro, Carmen |  |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | PANABO CITY | [19 empty] | Amended from Const. of New Brgy. Stage due to funding of Phase 1 by the LGU. Plan and POW on process c/o PDPM |  | AC
|  | 1 | Const. of New Brgy. Stage, Phase II |  | Stage |  | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - |  |  | 2
|  |  | San Pedro, Panabo City |  |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | 2 | Impv't. of Brgy. Road Covered Court, |  | Court |  | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Alloted - May 29, 2019, Additional Funding of 500,000.00,SB no. 4 cy 2019 for Allotment Nov 25, 2019 |  | 2
|  |  | Malativas, Panabo City |  |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | 3 | Rehab. Of Multi-Purpose Gym & Facililies |  | Gym |  | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Request for Allotment on process |  | 2
|  |  | Maduao, Panabo City |  |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | 4 | Const. of Multi-Purpose Bldg. |  | Bldg. |  | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Plan and POW on process c/o PDPM |  | 2
|  |  | Sto. Nino, Panabo City |  |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | 5 | Completion of Canopy at DAPCO Covered |  | Court |  | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For Plan preparation by PDPM August 5, 2019 |  | 2
|  |  | Court, Dapco, Panabo City |  |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | 6 | Perimeter Fence of Day Care Center I & II, |  | Bldg. |  | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For inspection by PDPM for PLAN and POW as of 7/19/2019 |  | 2
|  |  | Nanyo, Panabo City |  |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | STO. TOMAS | [19 empty] | For amendment in the AIP 3rd revision |  | AC
|  | 1 | Const. of Multi-Purpose Bldg./Compl. Of |  | Bldg. |  | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - |  |  | 2
|  |  | Covered Court Canopy, Balagunan, |  |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
|  |  | Sto. Tomas |  |  |  |  | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | 2 | Const. of Perimeter Fence of Kinamayan |  | Fence |  | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Inspected by PDPM for POW and POW July 31, 2019 |  | 2
|  |  | Integ,. School, Kinamayan, Sto. Tomas |  |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | B.E. DUJALI | [21 empty] | AC
|  | 1 | Concreting of Brgy. Road Canal, |  | Road |  | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For inspection by PDPM for PLAN and POW as of 7/19/2019 |  | 2
|  |  | Dujali, B.E. Dujali |  |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | 2 | Concreting of Drainage, Tanglaw, |  | Drainage |  | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For inspection by PDPM for PLAN and POW as of 7/19/2019 |  | 2
|  |  | B.E. Dujali |  |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | 3 | Const. of Bleacher w/ Canopy (Ph.II) and |  | Bleacher |  | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Check for pick-up as of July 5, 2019 with check no. 0135071 |  | 2
|  |  | Upgrading of Flooring, Cabay-angan, B.E. Dujali |  |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | 4 | Desilting and Concreting of Drainage-main |  | Bleacher |  | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For inspection by PDPM for PLAN and POW as of 7/19/2019 |  | 2
|  |  | Collector Canal, New Casay, B.E. Dujali |  |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | 5 | Const. of Brgy. Multi-Purpose Covered Court, |  | Bleacher |  | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For inspection by PDPM for PLAN and POW as of 7/19/2019 |  | 2
|  |  | Magupising, B.E. Dujali |  |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | IGCS | [21 empty] | AC
|  | 1 | Impv't. of Brgy. Water System, Pichon, IGCS |  | Water |  | Admin | a) | 500000 | a) | 05/31/18 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For Implementation |  | 2
[5 empty] | System |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | 2 | Powerline Expansion Project, Cogon, IGACOS |  | Water |  | Contract | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For Implementation. |  | 2
[5 empty] | System |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | 3 | Water System From Prk. 6 - Prk. 2 - Prk. 5A, |  | Water |  | Admin | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For Implementation |  | 2
|  |  | Tagbay, IGCS |  | System |  |  | b) | Pacquiao | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | 4 | Rehab of Multipurpose Hall, Tagdaliao |  | Bldg. |  | Admin | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | proposed realignement due to project ovelap |  | 2
|  |  | IGACOS |  |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | 5 | Electrification Project, Kanaan, IGACOS |  | Elect. |  | Admin | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For DANECO staking |  | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | 7 | Powerline Expansion Project, Tambo, IGCS |  | Elect. |  | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Procurement of Materials on process |  | 2
[8 empty] | b) | Porras | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | Admin | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | 9 | Construction of Multipurpose Pavement |  | Bldg. |  | Admin | a) | 500000 | a) |  | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Amended from Improvement of Brgy Hall due to change Brgy. Priority. Resolution No. 70 series of 2019 dated July 18, 2019. For allotment |  | 2
|  |  | Penaplata, IGCS |  |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | 10 | Completion of Kasilak Day Care Center, |  | Bldg. |  | Admin | a) | 500000 | a) | 07/05/18 | e) | - | a) | 500000 | a) | 93.04% | c) | 86.15% | a) | - | On-going |  | 2
|  |  | Sta. Cruz, IGCS |  |  |  |  | b) | Porras | b) | 5/20/2019 | f) | - | b) | 500000 | b) | - | d) | -6.89% | b) | - |  |  | 2
[8 empty] | c) | - | c) | 7/17/2019 | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | 11/30/2019 | [12 empty] | 2
|  | 11 | Const. of Concrete fence of New Brgy. Site, |  | Fence |  | - | a) | 500000 | a) |  | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For Implementation |  | 2
|  |  | San Isidro, IGCS |  |  |  |  | b) | Porras | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | [13 empty] | 2
|  | 12 | Electrification of Sitio Baongon-Diamond- |  | Elect. |  | - | a) | 500000 | a) |  | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Procurement on process |  | 2
|  |  | Mansanitas, Dadatan, IGCS |  |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | 13 | Drilling of Water System, |  | Water |  | - | a) | 500000 | a) |  | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For amendment. This project scope of work was included on a separate project titled Construction of Potable Water System at Linusotan, IGACOS. |  | 2
|  |  | Linusotan, IGCS |  | System |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
| L. | 5% Calamity Fund CY 2018 | [21 empty] | FS
|  | 1. Prevention and Mitigation | [21 empty] | AC
|  | 1.1 Desiltation/Excavation of rivers and creeks |  |  | rivers |  | Admin | a) | 3000000 | [12 empty] | Investigation/Inspection of priority projects |  | AC
[8 empty] | b) | - | [14 empty] | AC
[8 empty] | c) | PEO | [14 empty] | AC
[8 empty] | d) | - | [14 empty] | AC
| 11 | 1.1.1. | Improvement and Desiltation of Tagum Creek (Phase I and Phase II) |  | Creek |  | Admin | a) | 2,000,000.00 | a) | 11/06/18 | e) | - | a) | 2,000,000.00 | a) | 100% | c) | 100% | a) | 5 | Completed |  | 1 | 1
[8 empty] | b) | Mayang | b) | 03/22/19 | f) | - | b) | 2,000,000.00 | b) | - | d) | 0% | b) | 110 |  |  | 1
[8 empty] | c) | PEO | c) | 10/31/19 | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | 224 CD | d) | - | [12 empty] | 1
|  | 1.2 Improvement of Roads, Drainage & Canals |  |  | roads/canals |  | Admin | a) | 3000000 | [12 empty] | Investigation/Inspection of priority projects. |  | AC
[8 empty] | b) | - | [12 empty] | Declared as savings |  | AC
[8 empty] | c) | PEO | [14 empty] | AC
[8 empty] | d) | - | [14 empty] | AC
| 1 | 1.2.1 | Rehab./Impv't. of Sonlon-Longanapan Road |  | road |  | Admin | a) | 1,500,000.00 | a) | - | e) | - | a) | 1,500,000.00 | a) | 47.32% | c) | 20.57% | a) | - | On going |  | 1
[8 empty] | b) | - | b) | - | f) | - | b) | 1,500,000.00 | b) | - | d) | -26.75% | b) | - |  |  | 1
[8 empty] | c) | PEO | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
|  | 1.3 Improvement of bridges and cross drainage |  |  | bridges/drainage |  | Admin | a) | 3000000 | [12 empty] | Declared as savings |  | AC
[8 empty] | b) | - | [14 empty] | AC
[8 empty] | c) | PEO | [14 empty] | AC
[8 empty] | d) | - | [14 empty] | AC
|  | a. | Impv't. of Mabaus Cross Drainage |  | Drainage |  | Admin | a) | 3,000,000.00 | a) | - | e) | - | a) | 3,000,000.00 | a) | - | c) | - | a) | - | Preparation of POW & Plan c/o PDPM |  | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 3,000,000.00 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | 1.4 Revitment of Dike and Slope Protection |  |  | Dike |  | Admin | a) | 3000000 | [12 empty] | See project listed below |  | AC
[8 empty] | b) | - | [14 empty] | AC
[8 empty] | c) | Admin | [14 empty] | AC
[8 empty] | d) | - | [14 empty] | AC
|  | a. | Rehab. Of Dujali-Pawas-San Vicente RDCG-Abutment A&B (Embankment) - Riprapping A&B @ Both Side |  | Dike |  | Admin | a) | 3,000,000.00 | a) | 11/06/18 | e) | - | a) | 3,000,000.00 | a) | 100.00% | c) | 98.47% | a) | 10 | Suspended 9/23/2019 |  | 2
[8 empty] | b) | Sanchez | b) | 02/18/19 | f) | 145 | b) | 3,000,000.00 | b) | 88.56% | d) | -1.53% | b) | 70 |  |  | 2
[8 empty] | c) | PEO | c) | 05/08/19 | g) | - | c) | 2263892.44 | [8 empty] | 2
[8 empty] | d) | - | d) | 9/30/2019 | [12 empty] | 2
|  | 2. Rehabilitation and Recovery |  |  | roads |  | Admin | a) | 2026000 | [12 empty] | Declared as savings |  | AC
[8 empty] | b) | - | [14 empty] | AC
[8 empty] | c) | PEO | [14 empty] | AC
[8 empty] | d) | - | [14 empty] | AC
| M. | SUPPLEMENTAL BUDGET # 1 CY 2018 | [5 empty] | a) | 6,000,000.00 | [12 empty] | See list of Provincial Roads |  | FS
|  | 1 Const. in Progress - Infrastructure | [5 empty] | b) | Paraguya | [14 empty] | AC
|  | Assets (Rehabilitation of Various | [5 empty] | c) | PEO | [14 empty] | AC
|  | Provincial Roads) | [5 empty] | d) | - | [14 empty] | AC
| 5 | 1 | Mesaoy - Jct. Mahayahay |  | Road |  | Admin | a) | 1,534,000.00 | a) | 07/19/18 | e) | - | a) | 1,534,000.00 | a) | 60% | c) | 60% | a) | - | Suspended as of Dec. 27, 2018 |  | 1
[8 empty] | b) | Salido | b) | 11/16/18 | f) | - | b) | 1,534,000.00 | b) | - | d) | - | b) | - | Cancellation of PO # 2018082439 and RE-PR |  | 1
[8 empty] | c) | PEO | c) | 12/15/18 | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| 5 | 2 | Del Pilar - Jct. Silangan |  | Road |  | Admin | a) | 1,795,000.00 | a) | 07/19/18 | e) | - | a) | 1,795,000.00 | a) | 73.00% | c) | 73.00% | a) | 14 | On-going |  | 1
[8 empty] | b) | Salido | b) | 10/16/18 | f) | - | b) | 1,795,000.00 | b) | - | d) | - | b) | 30 | Suspended as of January 4, 2019 |  | 1
[8 empty] | c) | PEO | c) | 11/20/18 | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| N. | SUPPLEMENTAL BUDGET # 2 CY 2018 | [21 empty] | FS
|  | 1 Const./Compl./Impv't. of Various Gov't. | [21 empty] | AC
|  | Bldgs., Structures & Facilities (Const. in | [21 empty] | AC
|  | Progress - Bldgs. & Other Structures | [21 empty] | AC
| 4 |  | Const./Impv't. of DDN Hospital |  | Bldg. |  | - | a) | 5,000,000.00 | a) | - | e) | - | a) | 5,000,000.00 | a) | - | c) | 40% | a) | - | On-going |  | 1
|  |  | Kapalong Zone |  |  |  |  | b) | - | b) | - | f) | - | b) | 5,000,000.00 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
|  |  | Const. of DDN Hospital Carmen Zone |  | Bldg. |  | Admin | a) | 5,500,000.00 | a) | - | e) | - | a) | 5,500,000.00 | a) | - | c) | - | a) | - | PR ON PROCESS 6/11/2019 |  | 2
|  |  | Annex Bldg. |  |  |  |  | b) | Estorco | b) | - | f) | - | b) | 5,500,000.00 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | PEO | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
| 5 |  | Compl. Of Bahay Pag-Asa for Minors, |  | Bldg. |  | - | a) | 3,000,000.00 | a) | - | e) | - | a) | 3,000,000.00 | a) | - | c) | - | a) | - | Waiting for Delivery of Materials |  | 1
|  |  | New Corella |  |  |  |  | b) | - | b) | - | f) | - | b) | 3,000,000.00 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| 11 |  | Upgrading of DAGOEMC Muti-Purpose Bldg. |  | Bldg. |  | - | a) | 3,000,000.00 | a) | 09/04/2018 | e) | - | a) | 3,000,000.00 | a) | 30.28% | c) | 56.97% | a) | 7 | On-going |  | 1
|  |  | Mankilam |  |  |  |  | b) | Chua | b) | 03/04/2019 | f) | - | b) | 3,000,000.00 | b) | - | d) | - | b) | 210 |  |  | 1
[8 empty] | c) | PEO | c) | 07/26/2019 | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | 145 CD | d) | - | [12 empty] | 1
| 11 |  | Const. of Add'l. 2nd Level Multi-Purpose |  | Bldg. |  | - | a) | 7,592,588.00 | a) | - | e) | - | a) | 7,592,588.00 | a) | - | c) | - | a) | - | Preparation of POW & Plan c/o PDPM. |  | 1
|  |  | HalI, PGSO warehouse,Bldg., Mankilam |  |  |  |  | b) | - | b) | - | f) | - | b) | 7,592,588.00 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| O. | SUPPLEMENTAL BUDGET # 4 CY 2018 | [21 empty] | FS
| 11 | 1 | Construction of Multi-Purpose Bldg. (PENRO Building) |  | Bldg. | 303.75 sq.m | Admin | a) | 1800000 | a) | 06/11/18 | e) | - | a) | 1800000 | a) | 100% | c) | 100% | a) | 25 | Completed as per Physical accomplishment. Financial Documents on process |  | 1
[8 empty] | b) | Pasiona/Juan | b) | 10/16/18 | f) | 111 | b) | 1800000 | b) | - | d) | 0% | b) | 750 |  |  | 1
|  |  | (Part of P8,548,000.00)(P1,800,000.00 - |  |  |  |  | c) | PEO | c) | 09/10/19 | g) | 09/13/19 | c) | 6129861.34 | [8 empty] | 1
|  |  | SB # 4 CY 2018) |  |  |  |  | d) | 222 CD | d) | 06/30/19 | [12 empty] | 1
| P. | SUPPLEMENTAL BUDGET # 5 CY 2018 | [21 empty] | FS
|  | STIMULUS CY 2018 | [21 empty] | AC
| 1 | 1 | Const. of MP Hall, Rizal ES, Binancian, |  | Bldg. |  | - | a) | 1250000 | a) | 02/04/19 | e) | - | a) | 1250000 | a) | - | c) | 80% | a) | - | On-going |  | 1
|  |  | Asuncion |  |  |  |  | b) | - | b) | 06/18/2019 | f) | - | b) | 1250000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| 1 | 2 | Const. of MP Hall, Liguyon ES, Binancian, |  | Bldg. |  | - | a) | 1250000 | a) | 02/04/19 | e) | - | a) | 1250000 | a) | - | c) | 80% | a) | - | On-going |  | 1
|  |  | Asuncion |  |  |  |  | b) | - | b) | 06/16/2019 | f) | - | b) | 1250000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| 1 | 3 | Rehab./Impv't. of MP Bldg. (Gym), Napungas, |  | GYM |  | - | a) | 500000 | a) | 02/04/19 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Plan and POW on process |  | 1
|  |  | Asuncion |  |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| Q. | OPPAP-PAMANA | [21 empty] | FS
|  | 1. TRIBAL HALL | [21 empty] | AC
| 4 | 1.1 | Construction of Tribal Hall |  | Bldg. |  | Admin | a) | 500000 | a) | CY 2018 | e) | - | a) | 500000 | a) | 100% | c) | 100% | a) | 5 | Completed as per Physical Accomplishment. Financial Documents on process |  | 1
|  |  | Brgy. Gupitan, Kapalong |  |  |  |  | b) | Ambrocio | b) | 2/22/2019 | f) | - | b) | 500000 | b) | - | d) | 0% | b) | 150 |  |  | 1
[8 empty] | c) | PEO | c) | 5/22/2019 | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
|  | 2. PROCESSING AND BAGSAKAN CENTER | [21 empty] | AC
| 8 | 2.1 | Const. of Processing and Bagsakan Center, |  | Bldg. |  | Contract | a) | 2500000 | a) | - | e) | - | a) | 2500000 | a) | - | c) | 4% | a) | - | On going. |  | 1
|  |  | Brgy. Dagohoy, Talaingod |  |  |  |  | b) | - | b) | - | f) | - | b) | 2500000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| 4 | 2.2 | Const. of Processing and Bagsakan Center, |  | Bldg. | 300 sq.m | Contract | a) | 2500000 | a) | 08/29/18 | e) | - | a) | 2500000 | a) | 100% | c) | 100% | a) | 6 | Completed as per Physical Accomplishment. Financial Documents on process |  | 1
|  |  | Brgy. Gupitan, Kapalong, Davao del Norte |  |  |  |  | b) | Ambrucio | b) | 02/12/19 | f) | - | b) | 2500000 | b) | - | d) | 0% | b) | 180 |  |  | 1
[8 empty] | c) | Alpha & Omega | c) | 05/12/19 | g) | - | c) | 156000 | [8 empty] | 1
[8 empty] | d) | 120 CD | d) | - | [12 empty] | 1
|  | 3. SOLAR DRYER | [21 empty] | AC
| 4 | 3.1 | Post Harvest Facilities (Corn Mill, Solar Dryer, |  | Bldg. |  | Contract | a) | 1500000 | a) | - | e) | - | a) | 1500000 | a) | 10% | c) | 15% | a) | - | on-going. |  | 1
|  |  | Corn Sheller), Kapalong, Davao del Norte |  |  |  |  | b) | - | b) | - | f) | - | b) | 1500000 | b) | - | d) | 5% | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | 391970.93 | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| 8 | 3.2 | Post Harvest Facilities (Corn Mill, Solar Dryer, Corn Sheller), Sitio Butay, Palma Gil, Talaingod, Davao del Norte |  | Bldg. |  | Admin | a) |  | a) | - | e) | - | a) | 1850000 | a) |  | c) | 79.14% | a) | 11 | on-going |  | 1
[8 empty] | b) | Dadula | b) | July 16, 2019 | f) | - | b) | 1850000 | b) | - | d) |  | b) | 246 |  |  | 1
[8 empty] | c) | - | c) | Nov. 13, 2019 | g) | - | c) | [9 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
|  | 4. TRADING POST STORAGE | [21 empty] | AC
| 11 |  | Trading Post, Storage and Hauling Truck, Pandapan, Tagum City |  | Bldg. |  | Contract | a) | 4000000 | a) | - | e) | - | a) | 4000000 | a) | - | c) | - | a) | - | Re-bidding |  | 1
[8 empty] | b) | - | b) | - | f) | - | b) | 4000000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
|  |  | Trading Post, Storage and Hauling Truck, Purok Ramihan, Datu Abdul, Panabo City |  | Bldg. |  | - | a) | 4000000 | a) | CY 2018 | e) | - | a) | 4000000 | a) | 3.74% | c) | 1.91% | a) | - | On-going |  | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 4000000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  |  | Trading Post, Storage and Hauling Truck Libuak, Island Garden City of Samal (IGACOS) |  | Bldg. |  | - | a) | 4000000 | a) | CY 2018 | e) | - | a) | 4000000 | a) | - | c) | - | a) | - | For verification of beneficiary |  | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 4000000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | 5. WATER SYSTEM | [21 empty] | AC
| 4 |  | Upgrading of Existing PWS Level II in Sitio Langan, Gupitan, Kapalong |  | PWS |  | Admin | a) | 2500000 | a) |  | e) |  | a) | 2500000 | a) | 31.24% | c) | 32.67% | a) |  | On-going |  | 1
[8 empty] | b) |  | b) | 11/16/2019 | f) |  | b) | 2500000 | b) | - | d) | 1.43% | b) |  |  |  | 1
[8 empty] | c) |  | c) | 02/27/2020 | g) | - | c) | [9 empty] | 1
[8 empty] | d) |  | d) | - | [12 empty] | 1
| 4 |  | Upgrading of Existing PWS Level II in Sitio Patel 2, Gupitan, Kapalong |  | PWS |  | Admin | a) | 2500000 | a) | 8/14/2019 | e) | - | a) | 2500000 | a) |  | c) | 100% | a) | - | Completed as per Physical Accomplishment. Financial Documents on process |  | 1
[8 empty] | b) | Diosanta | b) | 3/25/2019 | f) | - | b) | 2500000 | b) |  | d) |  | b) | - |  |  | 1
[8 empty] | c) | PEO | c) | 7/19/2019 | g) | 09/30/2019 | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| 4 |  | Construction of PWS Level II in Purok 7-A and 7-B, Capungagan, Kapalong |  | PWS |  | Admin | a) | 1000000 | a) | 11/25/2019 | e) | - | a) | 1000000 | a) | - | c) | 5% | a) | - | On-going |  | 1
[8 empty] | b) | Kabinge | b) | - | f) | - | b) | 1000000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | PEO | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| 4 |  | Construction of PWS Level II in Purok 2, Pag-asa, Kapalong |  | PWS |  | Admin | a) | 1000000 | a) | 11/12/18 | e) | - | a) | 1000000 | a) | - | c) | - | a) | - | Declared savings in the AIP 2nd Revision to fund for the Construction of PWS in Brgy. Linusotan, Kaputian District, IGACOS (Project was funded by OPAPP CY 2018) |  | 1
[8 empty] | b) | - | b) | - | f) | - | b) | 1000000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| 8 |  | Construction of PWS Level II in Sitio Upper Dulyan, Palma Gil, Talaingod, DDN |  | PWS |  | Admin | a) | 1000000 | a) | - | e) | - | a) | 1000000 | a) | - | c) | 5% | a) | - | On going |  | 1
[8 empty] | b) | Kabinge | b) | - | f) |  | b) | 1000000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | PEO | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
|  | 6. CATTLE PRODUCTION | [21 empty] | AC
| 4 |  | Cattle Production- Brgy. Tiburcia, Gupitan and Semong, Kapalong |  | Bldg. |  | Admin | a) | 1500000 | a) | - | e) | - | a) | 1500000 | a) | - | c) | - | a) | - | For cancellation. A letter was sent to OPAPP last Dec 2018 requesting to allow us to reduce the number of cattle but we are still hoping that there would be a supplier will bid |  | 1
[8 empty] | b) | - | b) | - | f) | - | b) | 1500000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| 8 |  | Cattle Production, Brgy. Palma Gil, Brgy. Sto. Nino, Brgy. Dagohoy, Talaingod, Davao del Norte |  | Bldg. |  | Admin | a) | 1500000 | a) | - | e) | - | a) | 1500000 | a) | - | c) | - | a) | - | For cancellation. A letter was sent to OPAPP last Dec 2018 requesting to allow us to reduce the number of cattle but we are still hoping that there would be a supplier will bid |  | 1
[8 empty] | b) | - | b) | - | f) | - | b) | 1500000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
|  | 7. RICE MILL FOR UPLAND RICE | [21 empty] | AC
| 8 |  | Rice Mill for Upland Rice, Palma Gil, Talaingod |  | Bldg. |  | Admin | a) | 1000000 | a) | - | e) | - | a) | 1000000 | a) | 31.93% | c) | 31.93% | a) | - | No Approved P.O. |  | 1
[8 empty] | b) | - | b) | - | f) | - | b) | 1000000 | b) | - | d) | 0% | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| 4 |  | Rice Mill for Upland Rice,Gupitan, Kapalong |  | Bldg. |  | Admin | a) | 1000000 | a) | - | e) | - | a) | 1000000 | a) | 100% | c) | 100% | a) | - | Completed |  | 1
[8 empty] | b) | Ambrucio | b) | 6/17/2019 | f) | - | b) | 1000000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
|  | 8. AGRICULTURAL PRODUCTIVITY SUPPORT PROJECT | [21 empty] | AC
|  |  | Agricultural Productivity Support Project- |  | - |  | - | a) | 1500000 | a) | - | e) | - | a) | 1500000 | a) | - | c) | - | a) | - | For verification of beneficiary |  | 2
|  |  | Fishing Equipment, Tambo, IGACOS |  |  |  |  | b) | - | b) | - | f) | - | b) | 1500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
| R. | LOCAL GOVERNMENT SUPPORT FUND (LGSF) CY 2018 | [21 empty] | FS
| 1 | 1 | Road Upgrading of San Vicente - Butay Provincial Road |  | Road |  | Contract | a) | 19949581.18 | a) | CY 2018 | e) | - | a) | 19949581.18 | a) | 100% | c) | 100% | a) | 18 | Completed as per Physical Accomplishment. Financial Documents on process |  | 1
[8 empty] | b) | Aclaracion | b) | 11/19/18 | f) | 28 CD | b) | 19949581.18 | b) | 100% | d) | 0% | b) | 396 |  |  | 1
[8 empty] | c) | Alpha & Omega | c) | 06/08/19 | g) | 06/26/2019 | c) | 9,685,667.31 | [8 empty] | 1
[8 empty] | d) | 202 CD | d) | 07/06/19 | [12 empty] | 1
| S. | QUICK RESPOND FUND CY 2016 | [21 empty] | FS
| 4 | 1 | Rehab. Of Slope Protection of Libuganon River Along Kapalong - Mabantao - Florida Prov'l. Road Phase I |  | Road |  | - | a) | 900000 | a) | - | e) | - | a) | 900000 | a) | - | c) | - | a) | - | For AIP Amendment |  | 1
[8 empty] | b) | - | b) | - | f) | - | b) | 900000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
II. PROJECTS UNDER THE CURRENT APPROPRIATION CY 2019
A.1 GENERAL FUND CY 2019 | [6 empty] | MBA/CBRMC | a) | 18127866 | a) | 01/03/19 | e) | - | a) | 18127866 | a) | 83.63 | c) | 83.83 | a) | 46 | See list of Provincial Roads |  | AP
Road ID |  | Maintenance of Various Provincial Roads and Bridges at District 1 |  |  | Road Maintenance | KM |  | b) | Paraguya | b) | 01/03/19 | f) | - | b) | 18127866 | b) | - | d) | - | b) | 920 |  |  | FS
[6 empty] | 288.26 |  | c) | PEO/CBRMC | c) | 12/31/19 | g) | - | c) | - | [8 empty] | AC
11DAN | [9 empty] | d) | - | [12 empty] | AC
[8 empty] | d) | 261 days | d) | - | [12 empty] | AC
|  | Jct. Highway Magatos - New Bantayan |  |  | Road Maintenance | 7.1 | MBA | a) | 287307.39 | a) | 01/03/19 | e) | - | a) | 287307.39 | a) | 100% | c) | 100% | a) | 15 | Completed |  | AC | 4
001 | [7 empty] | b) | Crucio | b) | 01/16/19 | f) | - | b) | 287307.39 | b) | - | d) | - | b) | 480 |  |  | 1 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 118693.58 | [8 empty] | 1 | 4
[8 empty] | d) | - | d) | - | [12 empty] | 1 | 4
|  | Jct. Highway Magatos - New Bantayan |  |  | Road Maintenance | 7.1 | CBRMC | a) | 223674.22 | a) | 01/03/19 | e) | - | a) | 223674.22 | a) | 100% | c) | 100% | a) | 16 | Completed |  | 1 | 4
001 | [7 empty] | b) | Crucio | b) | 3/22/19 | f) | - | b) | 223674.22 | b) | - | d) | - | b) | 480 |  |  | 1 | 4
[8 empty] | c) | CALAFA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [8 empty] | 1 | 4
[8 empty] | d) | 3 quarters | d) | - | [12 empty] | 1 | 4
|  | Magatos-Bdry Pagsabangan |  |  | Road Maintenance | 8.33 | MBA | a) | 328740.25 | a) | 01/03/19 | e) | - | a) | 328740.25 | a) | 100% | c) | 100% | a) | 15 | Completed |  | 1 | 4
002 | [7 empty] | b) | Crucio | b) | 01/03/19 | f) | - | b) | 328740.25 | b) | - | d) | - | b) | 450 |  |  | 1 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 207258.49 | [8 empty] | 1 | 4
[8 empty] | d) | - | d) | - | [12 empty] | 1 | 4
|  | Magatos-Bdry Pagsabangan |  |  | Road Maintenance | 8.33 | CBRMC | a) | 270763.53 | a) | 01/03/19 | e) | - | a) | 270763.53 | a) | 100% | c) | 100% | a) | 16 | Completed |  | 1 | 4
002 | [7 empty] | b) | Crucio | b) | 03/22/19 | f) | - | b) | 270763.53 | b) | - | d) | - | b) | 450 |  |  | 1 | 4
[8 empty] | c) | CALAFA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [8 empty] | 1 | 4
[8 empty] | d) | 3 quarters | d) | - | [12 empty] | 1 | 4
|  | Ilog-New Bantayan |  |  | Road Maintenance | 2.68 | MBA | a) | 131131.39 | a) | 01/03/19 | e) | - | a) | 131131.39 | a) | 100% | c) | 100% | a) | 15 | Completed |  | 1 | 4
003 | [7 empty] | b) | Crucio | b) | 01/16/19 | f) | - | b) | 131131.39 | b) | - | d) | - | b) | 450 |  |  | 1 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 49,316.69 | [8 empty] | 1 | 4
[8 empty] | d) | - | d) | - | [12 empty] | 1 | 4
|  | Ilog-New Bantayan |  |  | Road Maintenance | 2.68 | CBRMC | a) | 65925.03 | a) | 01/03/19 | e) | - | a) | 65925.03 | a) | 100% | c) | 100% | a) | 16 | Completed |  | 1 | 4
003 | [7 empty] | b) | Crucio | b) | 03/22/19 | f) | - | b) | 65925.03 | b) | - | d) | - | b) | 450 |  |  | 1 | 4
[8 empty] | c) | CALAFA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [8 empty] | 1 | 4
[8 empty] | d) | 3 quarters | d) | - | [12 empty] | 1 | 4
|  | Asuncion -Monte Carlo-Del Pilar |  |  | Road Maintenance | 9.93 | MBA | a) | 474102.88 | a) | 01/03/19 | e) | - | a) | 474102.88 | a) | 100% | c) | 100% | a) | 15 | Completed |  | 1 | 4
005 | [7 empty] | b) | Crucio | b) | 01/03/19 | f) | - | b) | 474102.88 | b) | - | d) | - | b) | 450 |  |  | 1 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 240274.49 | [8 empty] | 1 | 4
[8 empty] | d) | - | d) | - | [12 empty] | 1 | 4
|  | Asuncion -Monte Carlo-Del Pilar |  |  | Road Maintenance | 9.93 | CBRMC | a) | 355524.28 | a) | 01/03/19 | e) | - | a) | 355524.28 | a) | 100% | c) | 100% | a) | 16 | Completed |  |  | 4
005 | [7 empty] | b) | Crucio | b) | 03/22/19 | f) | - | b) | 355524.28 | b) | - | d) | - | b) | 450 |  |  | 1 | 4
[8 empty] | c) | MAHAYAHAY IFA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [8 empty] | 1 | 4
[8 empty] | d) | 3 quarters | d) | - | [12 empty] | 1 | 4
|  | Jct. Highway Canatan-Jct. Highway Magatos |  |  | Road Maintenance | 4.85 | MBA | a) | 209808.59 | a) | 01/03/19 | e) | - | a) | 209808.59 | a) | 100% | c) | 100% | a) | 15 | Completed |  | 1 | 4
006 | [7 empty] | b) | Crucio | b) | 02/18/19 | f) | - | b) | 209808.59 | b) | - | d) | - | b) | 450 |  |  | 1 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 80652.8 | [8 empty] | 1 | 4
[8 empty] | d) | - | d) | - | [12 empty] | 1 | 4
|  | Jct. Highway Canatan-Jct. Highway Magatos |  |  | Road Maintenance | 4.85 | CBRMC | a) | 162458.12 | a) | 01/03/19 | e) | - | a) | 162458.12 | a) | 100% | c) | 100% | a) | 16 | Completed |  | 1 | 4
006 | [7 empty] | b) | Crucio | b) | 03/22/19 | f) | - | b) | 162458.12 | b) | - | d) | - | b) | 450 |  |  | 1 | 4
[8 empty] | c) | CAMODA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [8 empty] | 1 | 4
[8 empty] | d) | 3 quarters | d) | - | [12 empty] | 1 | 4
[24 empty] | 1 | 4
|  | Sta. Felomina-San Roque |  |  | Road Maintenance | 7.68 | MBA | a) | 147439.63 | a) | 01/03/19 | e) | - | a) | 147439.63 | a) | 100% | c) | 100% | a) | 15 | Completed |  |  | 4
008 | [7 empty] | b) | Crucio | b) | 01/16/19 | f) | - | b) | 147439.63 | b) | - | d) | - | b) | 450 |  |  | 1 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 63806.67 | [8 empty] | 1 | 4
[8 empty] | d) | - | d) | - | [12 empty] | 1 | 4
|  | Sta. Felomina-San Roque |  |  | Road Maintenance | 7.68 | CBRMC | a) | 261345.67 | a) | 01/03/19 | e) | - | a) | 261345.67 | a) | 100% | c) | 100% | a) | 16 | Completed |  | 1 | 4
008 | [7 empty] | b) | Crucio | b) | 03/25/19 | f) | - | b) | 261345.67 | b) | - | d) | - | b) | 450 |  |  | 1 | 4
[8 empty] | c) | STAFFA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [8 empty] | 1 | 4
[8 empty] | d) | 3 quarters | d) | - | [12 empty] | 1 | 4
|  | Saug-Sonlon-Bdy Longanapan |  |  | Road Maintenance | 11.6 | MBA | a) | 568486.36 | a) | 01/03/19 | e) | - | a) | 568486.36 | a) | 100% | c) | 100% | a) | 15 | Completed |  | 1 | 4
010 | [7 empty] | b) | Crucio | b) | 01/16/19 | f) | - | b) | 568486.36 | b) | - | d) | - | b) | 450 |  |  | 1 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 262900.22 | [8 empty] | 1 | 4
[8 empty] | d) | - | d) | - | [12 empty] | 1 | 4
|  | Saug-Sonlon-Bdy Longanapan |  |  | Road Maintenance | 11.6 | CBRMC | a) | 185565.56 | a) | 01/03/19 | e) | - | a) | 185565.56 | a) | 100% | c) | 100% | a) | 16 | Completed |  | 1 | 4
010 | [7 empty] | b) | Crucio | b) | 03/26/19 | f) | - | b) | 185565.56 | b) | - | d) | - | b) | 450 |  |  | 1 | 4
[8 empty] | c) | BINANCIAN LIVESTOCK AFA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [8 empty] | 1 | 4
[8 empty] | d) | 3 quarters | d) | - | [12 empty] | 1 | 4
|  | Jct. New Visayas-Buan |  |  | Road Maintenance | 2.99 | MBA | a) | 79238.27 | a) | 01/03/19 | e) | - | a) | 79238.27 | a) | 100% | c) | 100% | a) | 15 | Completed |  | 1 | 4
011 | [7 empty] | b) | Crucio | b) | 02/18/19 | f) | - | b) | 79238.27 | b) | - | d) | - | b) | 450 |  |  | 1 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 14682.85 | [8 empty] | 1 | 4
[8 empty] | d) | - | d) | - | [12 empty] | 1 | 4
|  | Jct. New Visayas-Buan |  |  | Road Maintenance | 2.99 | CBRMC | a) | 101242.01 | a) | 01/03/19 | e) | - | a) | 101242.01 | a) | 100% | c) | 100% | a) | 16 | Completed |  | 1 | 4
011 | [7 empty] | b) | Crucio | b) | 03/22/19 | f) | - | b) | 101242.01 | b) | - | d) | - | b) | 450 |  |  | 1 | 4
[8 empty] | c) | BUAN IFA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [8 empty] | 1 | 4
[8 empty] | d) | 3 quarters | d) | - | [12 empty] | 1 | 4
|  | San Vicente - Butay |  |  | Road Maintenance | 7.52 | MBA | a) | 209624.2 | a) | 01/03/19 | e) | - | a) | 209624.2 | a) | 100% | c) | 100% | a) | 15 | Completed |  | 1 | 4
013 | [7 empty] | b) | Crucio | b) | 02/18/19 | f) | - | b) | 209624.2 | b) | - | d) | - | b) | 450 |  |  | 1 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 56,080.29 | [8 empty] | 1 | 4
[8 empty] | d) | - | d) | - | [12 empty] | 1 | 4
|  | San Vicente - Butay |  |  | Road Maintenance | 7.52 | CBRMC | a) | 227205.88 | a) | 01/03/19 | e) | - | a) | 227205.88 | a) | 100% | c) | 100% | a) | 16 | Completed |  | 1 | 4
013 | [7 empty] | b) | Crucio | b) | 03/27/19 | f) | - | b) | 227205.88 | b) | - | d) | - | b) | 450 |  |  | 1 | 4
[8 empty] | c) | SVMODA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [8 empty] | 1 | 4
[8 empty] | d) | 3 quarters | d) | - | [12 empty] | 1 | 4
|  | Jct. Highway Doña Andrea - Capungagan |  |  | Road Maintenance | 8.7 | MBA | a) | 230835.16 | a) | 01/03/19 | e) | - | a) | 230835.16 | a) | 100% | c) | 100% | a) | 15 | Completed |  | 1 | 4
014 | [7 empty] | b) | Crucio | b) | 02/18/19 | f) | - | b) | 230835.16 | b) | - | d) | - | b) | 450 |  |  | 1 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 60,629.26 | [8 empty] | 1 | 4
[8 empty] | d) | - | d) | - | [12 empty] | 1 | 4
[24 empty] | 1 | 4
|  | Jct. Highway Doña Andrea - Capungagan |  |  | Road Maintenance | 8.7 | CBRMC | a) | 294308.14 | a) | 01/03/19 | e) | - | a) | 294308.14 | a) | 100% | c) | 100% | a) | 16 | Completed |  |  | 4
014 | [7 empty] | b) | Crucio | b) | 03/28/19 | f) | - | b) | 294308.14 | b) | - | d) | - | b) | 450 |  |  | 1 | 4
[8 empty] | c) | CAPUNGAGAN MPC | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [8 empty] | 1 | 4
[8 empty] | d) | 3 quarters | d) | - | [12 empty] | 1 | 4
|  | Semong-Palma Gil |  |  | Road Maintenance | 2.73 | MBA | a) | 147289.98 | a) | 01/03/19 | e) | - | a) | 147289.98 | a) | 100% | c) | 100% | a) | 15 | Completed |  | 1 | 4
018 | [7 empty] | b) | Crucio | b) | 02/18/19 | f) | - | b) | 147289.98 | b) | - | d) | - | b) | 450 |  |  | 1 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 71745.43 | [8 empty] | 1 | 4
[8 empty] | d) | - | d) | - | [12 empty] | 1 | 4
[24 empty] | 1 | 4
4
4
|  | Semong-Palma Gil |  |  | Road Maintenance | 2.73 | CBRMC | a) | 49186.05 | a) | 01/03/19 | e) | - | a) | 49186.05 | a) | 100% | c) | 100% | a) | 16 | Completed |  |  | 4
018 | [7 empty] | b) | Crucio | b) | 03/22/19 | f) | - | b) | 49186.05 | b) | - | d) | - | b) | 450 |  |  | 1 | 4
[8 empty] | c) | PALMA GIL FA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [8 empty] | 1 | 4
[8 empty] | d) | 3 quarters | d) | - | [12 empty] | 1 | 4
|  | Daligdigon - Dagohoy |  |  | Road Maintenance | 3.34 | MBA | a) | 148835.45 | a) | 01/03/19 | e) | - | a) | 148835.45 | a) | 100% | c) | 100% | a) | - | Completed |  | 1 | 4
020 | [7 empty] | b) | Crucio | b) | - | f) | - | b) | 148835.45 | b) | - | d) | - | b) | - |  |  | 1 | 4
[8 empty] | c) | PEO | c) | - | g) | 2019-12-31 | c) | - | [8 empty] | 1 | 4
[8 empty] | d) | - | d) | - | [12 empty] | 1 | 4
|  | Daligdigon - Dagohoy |  |  | Road Maintenance | 3.34 | CBRMC | a) | 68279.5 | a) | 01/03/19 | e) | - | a) | 68279.5 | a) | 100% | c) | 100% | a) | 16 | Completed |  | 1 | 4
020 | [7 empty] | b) | Crucio | b) | 03/22/19 | f) | - | b) | 68279.5 | b) | - | d) | - | b) | 450 |  |  | 1 | 4
[8 empty] | c) | PALMA GIL FA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [8 empty] | 1 | 4
[8 empty] | d) | 3 quarters | d) | - | [12 empty] | 1 | 4
|  | Jct. Sampao-Bdry. Mamacao |  |  | Road Maintenance | 4.98 | MBA | a) | 154200.78 | a) | 01/03/19 | e) | - | a) | 154200.78 | a) | 100% | c) | 100% | a) | 15 | Completed |  | 1 | 4
025 | [7 empty] | b) | Crucio | b) | 02/18/19 | f) | - | b) | 154200.78 | b) | - | d) | - | b) | 450 |  |  | 1 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 24,296.87 | [8 empty] | 1 | 4
[8 empty] | d) | - | d) | - | [12 empty] | 1 | 4
|  | Jct. Sampao-Bdry. Mamacao |  |  | Road Maintenance | 4.98 | CBRMC | a) | 169521.51 | a) | 01/03/19 | e) | - | a) | 169521.51 | a) | 100% | c) | 100% | a) | 16 | Completed |  | 1 | 4
025 | [7 empty] | b) | Crucio | b) | 03/26/19 | f) | - | b) | 169521.51 | b) | - | d) | - | b) | 450 |  |  | 1 | 4
[8 empty] | c) | AMS KAPALONG | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [8 empty] | 1 | 4
[8 empty] | d) | 3 quarters | d) | - | [12 empty] | 1 | 4
|  | Jct. Highway Luna-Mamacao-Narra |  |  | Road Maintenance | 9.17 | MBA | a) | 357957.66 | a) | 01/03/19 | e) | - | a) | 357957.66 | a) | 100% | c) | 100% | a) | 15 | Completed |  | 1 | 4
026 | [7 empty] | b) | Crucio | b) | 02/18/19 | f) | - | b) | 357957.66 | b) | - | d) | - | b) | 450 |  |  | 1 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 127,996.16 | [8 empty] | 1 | 4
[8 empty] | d) | - | d) | - | [12 empty] | 1 | 4
|  | Jct. Highway Luna-Mamacao-Narra |  |  | Road Maintenance | 9.17 | CBRMC | a) | 313143.91 | a) | 01/03/19 | e) | - | a) | 313143.91 | a) | 100% | c) | 100% | a) | 16 | Completed |  | 1 | 4
026 | [7 empty] | b) | Crucio | b) | 03/26/19 | f) | - | b) | 313143.91 | b) | - | d) | - | b) | 450 |  |  | 1 | 4
[8 empty] | c) | AMS KAPALONG | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [8 empty] | 1 | 4
[8 empty] | d) | 3 quarters | d) | - | [12 empty] | 1 | 4
|  | Jct. Gabuyan-Katipunan-Bucana |  |  | Road Maintenance | 5.89 | MBA | a) | 294403.23 | a) | 01/03/19 | e) | - | a) | 294403.23 | a) | 100% | c) | 100% | a) | 15 | Completed |  | 1 | 4
027 | [7 empty] | b) | Crucio | b) | 02/18/19 | f) | - | b) | 294403.23 | b) | - | d) | - | b) | 450 |  |  | 1 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 126,179.97 | [8 empty] | 1 | 4
[8 empty] | d) | - | d) | - | [12 empty] | 1 | 4
|  | Jct. Gabuyan-Katipunan-Bucana |  |  | Road Maintenance | 5.89 | CBRMC | a) | 129495.6 | a) | 01/03/19 | e) | - | a) | 129495.6 | a) | 100% | c) | 100% | a) | 16 | Completed |  | 1 | 4
027 | [7 empty] | b) | Crucio | b) | 03/26/19 | f) | - | b) | 129495.6 | b) | - | d) | - | b) | 450 |  |  | 1 | 4
[8 empty] | c) | MANGULIBAS FA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [8 empty] | 1 | 4
[8 empty] | d) | 3 quarters | d) | - | [12 empty] | 1 | 4
|  | Capungagan-Mabuhay-Pandulian |  |  | Road Maintenance | 5.57 | MBA | a) | 294917.73 | a) | 01/03/19 | e) | - | a) | 294917.73 | a) | 100% | c) | 100% | a) | 15 | Completed |  | 1 | 4
028 | [7 empty] | b) | Crucio | b) | 02/18/19 | f) | - | b) | 294917.73 | b) | - | d) | - | b) | 450 |  |  | 1 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [8 empty] | 1 | 4
[8 empty] | d) | - | d) | - | [12 empty] | 1 | 4
[24 empty] | 1 | 4
|  | Capungagan-Mabuhay-Pandulian |  |  | Road Maintenance | 5.57 | CBRMC | a) | 105950.95 | a) | 01/03/19 | e) | - | a) | 105950.95 | a) | 100% | c) | 100% | a) | 16 | Completed |  |  | 4
028 | [7 empty] | b) | Crucio | b) | 03/28/19 | f) | - | b) | 105950.95 | b) | - | d) | - | b) | 450 |  |  | 1 | 4
[8 empty] | c) | CAPUNGAGAN MPC | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [8 empty] | 1 | 4
[8 empty] | d) | 3 quarters | d) | - | [12 empty] | 1 | 4
|  | Florida - New Boholano |  |  | Road Maintenance | 2.54 | MBA | a) | 95863.17 | a) | 01/03/19 | e) | - | a) | 95863.17 | a) | 100% | c) | 100% | a) | 15 | Completed |  | 1 | 4
030 | [7 empty] | b) | Crucio | b) | 02/18/19 | f) | - | b) | 95863.17 | b) | - | d) | - | b) | 450 |  |  | 1 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 31,418.99 | [8 empty] | 1 | 4
[8 empty] | d) | - | d) | - | [12 empty] | 1 | 4
|  | Florida - New Boholano |  |  | Road Maintenance | 2.54 | CBRMC | a) | 47425.27 | a) | 01/03/19 | e) | - | a) | 47425.27 | a) | 100% | c) | 100% | a) | 16 | Completed |  | 1 | 4
030 | [7 empty] | b) | Crucio | b) | 03/28/19 | f) | - | b) | 47425.27 | b) | - | d) | - | b) | 450 |  |  | 1 | 4
[8 empty] | c) | SUPRA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [8 empty] | 1 | 4
[8 empty] | d) | 3 quarters | d) | - | [12 empty] | 1 | 4
|  | Jct. New Boholano - New Loon |  |  | Road Maintenance | 4.77 | MBA | a) | 140549.84 | a) | 01/03/19 | e) | - | a) | 140549.84 | a) | 100% | c) | 100% | a) | 15 | Completed |  | 1 | 4
031 | [7 empty] | b) | Crucio | b) | 02/18/19 | f) | - | b) | 140549.84 | b) | - | d) | - | b) | 450 |  |  | 1 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 40,056.38 | [8 empty] | 1 | 4
[8 empty] | d) | - | d) | - | [12 empty] | 1 | 4
4
|  | Jct. New Boholano - New Loon |  |  | Road Maintenance | 4.77 | CBRMC | a) | 169521.51 | a) | 01/03/19 | e) | - | a) | 169521.51 | a) | 100% | c) | 100% | a) | 16 | Completed |  | 1 | 4
031 | [7 empty] | b) | Crucio | b) | 03/28/19 | f) | - | b) | 169521.51 | b) | - | d) | - | b) | 450 |  |  | 1 | 4
[8 empty] | c) | NEW LOON FA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [8 empty] | 1 | 4
[8 empty] | d) | 3 quarters | d) | - | [12 empty] | 1 | 4
|  | Florida-Suaon-Jct. Gupitan |  |  | Road Maintenance | 15.57 | MBA | a) | 707038.05 | a) | 01/03/19 | e) | - | a) | 707038.05 | a) | 100% | c) | 100% | a) | 15 | Completed |  | 1 | 4
032 | [7 empty] | b) | Crucio | b) | 01/16/19 | f) | - | b) | 707038.05 | b) | - | d) | - | b) | 450 |  |  | 1 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 226,.062.60 | [8 empty] | 1 | 4
[8 empty] | d) | - | d) | - | [12 empty] | 1 | 4
|  | Florida-Suaon-Jct. Gupitan |  |  | Road Maintenance | 15.57 | CBRMC | a) | 419094.85 | a) | 01/03/19 | e) | - | a) | 419094.85 | a) | 100% | c) | 100% | a) | 16 | Completed |  | 1 | 4
032 | [7 empty] | b) | Crucio | b) | 03/28/19 | f) | - | b) | 419094.85 | b) | - | d) | - | b) | 450 |  |  | 1 | 4
[8 empty] | c) | SUPRA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [8 empty] | 1 | 4
[8 empty] | d) | 3 quarters | d) | - | [12 empty] | 1 | 4
|  | Km. 15, Kipalili-New Loon |  |  | Road Maintenance | 6.93 | MBA | a) | 367659.97 | a) | 01/03/19 | e) | - | a) | 367659.97 | a) | 100% | c) | 100% | a) | 15 | Completed |  | 1 | 4
034 | [7 empty] | b) | Crucio | b) | 02/01/19 | f) | - | b) | 367659.97 | b) | - | d) | - | b) | 450 |  |  | 1 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 112,175.78 | [8 empty] | 1 | 4
[8 empty] | d) | - | d) | - | [12 empty] | 1 | 4
|  | Km. 15, Kipalili-New Loon |  |  | Road Maintenance | 6.93 | CBRMC | a) | 237801.01 | a) | 01/03/19 | e) | - | a) | 237801.01 | a) | 100% | c) | 100% | a) | 16 | Completed |  | 1 | 4
034 | [7 empty] | b) | Crucio | b) | 03/26/19 | f) | - | b) | 237801.01 | b) | - | d) | - | b) | 480 |  |  | 1 | 4
[8 empty] | c) | KIPALILI FA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [8 empty] | 1 | 4
[8 empty] | d) | 3 quarters | d) | - | [12 empty] | 1 | 4
|  | Jct. Suaon-Libuton |  |  | Road Maintenance | 7.26 | MBA | a) | 44015.68 | a) | 01/03/19 | e) | - | a) | 44015.68 | a) | 100% | c) | 100% | a) | 15 | Completed |  |  | 4
035 | [7 empty] | b) | Crucio | b) | 01/16/19 | f) | - | b) | 44015.68 | b) | - | d) | - | b) | 450 |  |  | 1 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 24,980.86 | [8 empty] | 1 | 4
[8 empty] | d) | - | d) | - | [12 empty] | 1 | 4
|  | Jct. Suaon-Libuton |  |  | Road Maintenance | 7.26 | CBRMC | a) | 91664.91 | a) | 01/03/19 | e) | - | a) | 91664.91 | a) | 100% | c) | 100% | a) | 16 | Completed |  | 1 | 4
035 | [7 empty] | b) | Crucio | b) | 03/22/19 | f) | - | b) | 91664.91 | b) | - | d) | - | b) | 480 |  |  | 1 | 4
[8 empty] | c) | AALLI | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [8 empty] | 1 | 4
[8 empty] | d) | 3 quarters | d) | - | [12 empty] | 1 | 4
[24 empty] | 1 | 4
|  | Datu Balong - Pinamuno |  |  | Road Maintenance | 2.74 | MBA | a) | 95458.24 | a) | 01/03/19 | e) | - | a) | 95458.24 | a) | 100% | c) | 100% | a) | 15 | Completed |  |  | 4
040 | [7 empty] | b) | Crucio | b) | 03/01/19 | f) | - | b) | 95458.24 | b) | - | d) | - | b) | 450 |  |  | 1 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 12,625.00 | [8 empty] | 1 | 4
[8 empty] | d) | - | d) | - | [12 empty] | 1 | 4
|  | Datu Balong - Pinamuno |  |  | Road Maintenance | 2.74 | CBRMC | a) | 63570.57 | a) | 01/03/19 | e) | - | a) | 63570.57 | a) | 100% | c) | 100% | a) | 16 | Completed |  | 1 | 4
040 | [7 empty] | b) | Crucio | b) | 03/28/19 | f) | - | b) | 63570.57 | b) | - | d) | - | b) | 480 |  |  | 1 | 4
[8 empty] | c) | DATU BALONG FA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [8 empty] | 1 | 4
[8 empty] | d) | 3 quarters | d) | - | [12 empty] | 1 | 4
|  | Sawata - Mamangan - Pinamuno |  |  | Road Maintenance | 14.48 | MBA | a) | 545390.17 | a) | 01/03/19 | e) | - | a) | 545390.17 | a) | 100% | c) | 100% | a) | 15 | Completed |  | 1 | 4
041 | [7 empty] | b) | Crucio | b) | 02/01/19 | f) | - | b) | 545390.17 | b) | - | d) | - | b) | 450 |  |  | 1 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 196,076.60 | [8 empty] | 1 | 4
[8 empty] | d) | - | d) | - | [12 empty] | 1 | 4
|  | Sawata - Mamangan - Pinamuno |  |  | Road Maintenance | 14.48 | CBRMC | a) | 508564.54 | a) | 01/03/19 | e) | - | a) | 508564.54 | a) | 100% | c) | 100% | a) | 16 | Completed |  | 1 | 4
041 | [7 empty] | b) | Crucio | b) | 03/22/19 | f) | - | b) | 508564.54 | b) | - | d) | - | b) | 480 |  |  | 1 | 4
[8 empty] | c) | SAWATA DFA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [8 empty] | 1 | 4
[8 empty] | d) | 3 quarters | d) | - | [12 empty] | 1 | 4
|  | Igangon - Sawata |  |  | Road Maintenance | 9.66 | MBA | a) | 497447.77 | a) | 01/03/19 | e) | - | a) | 497447.77 | a) | 100% | c) | 100% | a) | 15 | Completed |  | 1 | 4
042 | [7 empty] | b) | Crucio | b) | 02/01/19 | f) | - | b) | 497447.77 | b) | - | d) | - | b) | 450 |  |  | 1 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [8 empty] | 1 | 4
[8 empty] | d) | - | d) | - | [12 empty] | 1 | 4
|  | Igangon - Sawata |  |  | Road Maintenance | 9.66 | CBRMC | a) | 197775.1 | a) | 01/03/19 | e) | - | a) | 197775.1 | a) | 100% | c) | 100% | a) | 16 | Completed |  | 1 | 4
042 | [7 empty] | b) | Crucio | b) | 03/22/19 | f) | - | b) | 197775.1 | b) | - | d) | - | b) | 480 |  |  | 1 | 4
[8 empty] | c) | SAWATA DFA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [8 empty] | 1 | 4
[8 empty] | d) | 3 quarters | d) | - | [12 empty] | 1 | 4
4
4
|  | New Corella - Sto. Niño - Macgum |  |  | Road Maintenance | 17.11 | MBA | a) | 606294.08 | a) | 01/03/19 | e) | - | a) | 606294.08 | a) | 100% | c) | 100% | a) | 15 | Completed |  | 1 | 4
044 | [7 empty] | b) | Crucio | b) | 01/03/19 | f) | - | b) | 606294.08 | b) | - | d) | - | b) | 450 |  |  | 1 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 246,619.77 | [8 empty] | 1 | 4
[8 empty] | d) | - | d) | - | [12 empty] | 1 | 4
|  | New Corella - Sto. Niño - Macgum |  |  | Road Maintenance | 17.11 | CBRMC | a) | 308434.97 | a) | 01/03/19 | e) | - | a) | 308434.97 | a) | 100% | c) | 100% | a) | 16 | Completed |  | 1 | 4
044 | [7 empty] | b) | Crucio | b) | 03/26/19 | f) | - | b) | 308434.97 | b) | - | d) | - | b) | 480 |  |  | 1 | 4
[8 empty] | c) | SAN ISIDRO FA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [8 empty] | 1 | 4
[8 empty] | d) | 3 quarters | d) | - | [12 empty] | 1 | 4
|  | Tagaytay - Buan |  |  | Road Maintenance | 4.92 | MBA | a) | 173197.37 | a) | 01/03/19 | e) | - | a) | 173197.37 | a) | 100% | c) | 100% | a) | 15 | Completed |  | 1 | 4
045 | [7 empty] | b) | Crucio | b) | 03/18/19 | f) | - | b) | 173197.37 | b) | - | d) | - | b) | 450 |  |  | 1 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 26254.58 | [8 empty] | 1 | 4
[8 empty] | d) | - | d) | - | [12 empty] | 1 | 4
|  | Tagaytay - Buan |  |  | Road Maintenance | 4.92 | CBRMC | a) | 131850.07 | a) | 01/03/19 | e) | - | a) | 131850.07 | a) | 100% | c) | 100% | a) | 16 | Completed |  | 1 | 4
045 | [7 empty] | b) | Crucio | b) | 03/22/19 | f) | - | b) | 131850.07 | b) | - | d) | - | b) | 480 |  |  | 1 | 4
[8 empty] | c) | BUAN IFA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [8 empty] | 1 | 4
[8 empty] | d) | 3 quarters | d) | - | [12 empty] | 1 | 4
|  | limbaan - Sto. Niño |  |  | Road Maintenance | 3.19 | MBA | a) | 153706.77 | a) | 01/03/19 | e) | - | a) | 153706.77 | a) | 100% | c) | 100% | a) | 15 | Completed |  | 1 | 4
049 | [7 empty] | b) | Crucio | b) | 03/01/19 | f) | - | b) | 153706.77 | b) | - | d) | - | b) | 450 |  |  | 1 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 32534.49 | [8 empty] | 1 | 4
[8 empty] | d) | - | d) | - | [12 empty] | 1 | 4
|  | limbaan - Sto. Niño |  |  | Road Maintenance | 3.19 | CBRMC | a) | 53657.51 | a) | 01/03/19 | e) | - | a) | 53657.51 | a) | 100% | c) | 100% | a) | - | Completed |  | 1 | 4
049 | [7 empty] | b) | Crucio | b) | - | f) | - | b) | 53657.51 | b) | - | d) | - | b) | - |  |  | 1 | 4
[8 empty] | c) | - | c) | - | g) | 2019-12-31 | c) | - | [8 empty] | 1 | 4
[8 empty] | d) | - | d) | - | [12 empty] | 1 | 4
|  | Del Pilar - Jct. Silangan |  |  | Road Maintenance | 4.17 | MBA | a) | 187097.4 | a) | 01/03/19 | e) | - | a) | 187097.4 | a) | 100% | c) | 100% | a) | 15 | Completed |  | 1 | 4
051 | [7 empty] | b) | Crucio | b) | 03/18/19 | f) | - | b) | 187097.4 | b) | - | d) | - | b) | 450 |  |  | 1 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 94181.74 | [8 empty] | 1 | 4
[8 empty] | d) | - | d) | - | [12 empty] | 1 | 4
|  | Del Pilar - Jct. Silangan |  |  | Road Maintenance | 4.17 | CBRMC | a) | 113014.34 | a) | 01/03/19 | e) | - | a) | 113014.34 | a) | 100% | c) | 100% | a) | 16 | Completed |  | 1 | 4
051 | [7 empty] | b) | Crucio | b) | 03/26/19 | f) | - | b) | 113014.34 | b) | - | d) | - | b) | 480 |  |  | 1 | 4
[8 empty] | c) | DURIAN DACUDAO | c) | 12/31/19 | g) | - | c) | - | [8 empty] | 1 | 4
[8 empty] | d) | 3 quarters | d) | - | [12 empty] | 1 | 4
|  | New Corella - New Sambog - Silangan |  |  | Road Maintenance | 5.1 | MBA | a) | 201994.35 | a) | 01/03/19 | e) | - | a) | 201994.35 | a) | 100% | c) | 100% | a) | 15 | Completed |  | 1 | 4
052 | [7 empty] | b) | Crucio | b) | 03/01/19 | f) | - | b) | 201994.35 | b) | - | d) | - | b) | 450 |  |  | 1 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 63402.48 | [8 empty] | 1 | 4
[8 empty] | d) | - | d) | - | [12 empty] | 1 | 4
|  | New Corella - New Sambog - Silangan |  |  | Road Maintenance | 5.1 | CBRMC | a) | 131850.07 | a) | 01/03/19 | e) | - | a) | 131850.07 | a) | 100% | c) | 100% | a) | 16 | Completed |  | 1 | 4
052 | [7 empty] | b) | Crucio | b) | 03/26/19 | f) | - | b) | 131850.07 | b) | - | d) | - | b) | 480 |  |  | 1 | 4
[8 empty] | c) | DURIAN DACUDAO | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [8 empty] | 1 | 4
[8 empty] | d) | 3 quarters | d) | - | [12 empty] | 1 | 4
|  | Sta. Fe - Del Monte |  |  | Road Maintenance | 3.34 | MBA | a) | 37923.51 | a) | 01/03/19 | e) | - | a) | 37923.51 | a) | 100% | c) | 100% | a) | 15 | Completed |  | 1 | 4
056 | [7 empty] | b) | Crucio | b) | 03/18/19 | f) | - | b) | 37923.51 | b) | - | d) | - | b) | 450 |  |  | 1 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 36595.13 | [8 empty] | 1 | 4
[8 empty] | d) | - | d) | - | [12 empty] | 1 | 4
|  | Sta. Fe - Del Monte |  |  | Road Maintenance | 3.34 | CBRMC | a) | 70633.96 | a) | 01/03/19 | e) | - | a) | 70633.96 | a) | 100% | c) | 100% | a) | 16 | Completed |  | 1 | 4
056 | [7 empty] | b) | Crucio | b) | 03/21/19 | f) | - | b) | 70633.96 | b) | - | d) | - | b) | 480 |  |  | 1 | 4
[8 empty] | c) | DEL MONTE CACAO | c) | 12/31/19 | g) | 2019-12-31 | c) | 4,872.18 | [8 empty] | 1 | 4
[8 empty] | d) | 3 quarters | d) | - | [12 empty] | 1 | 4
|  | New Corella - New Bohol |  |  | Road Maintenance | 11.54 | MBA | a) | 356226.67 | a) | 01/03/19 | e) | - | a) | 356226.67 | a) | 100% | c) | 100% | a) | 15 | Completed |  |  | 4
058 | [7 empty] | b) | Crucio | b) | 02/01/19 | f) | - | b) | 356226.67 | b) | - | d) | - | b) | 450 |  |  | 1 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 110,982.71 | [8 empty] | 1 | 4
[8 empty] | d) | - | d) | - | [12 empty] | 1 | 4
|  | New Corella - New Bohol |  |  | Road Maintenance | 11.54 | CBRMC | a) | 190711.7 | a) | 01/03/19 | e) | - | a) | 190711.7 | a) | 100% | c) | 100% | a) | 16 | Completed |  | 1 | 4
058 | [7 empty] | b) | Crucio | b) | 03/22/19 | f) | - | b) | 190711.7 | b) | - | d) | - | b) | 480 |  |  | 1 | 4
[8 empty] | c) | SAN JOSE COCONUT | c) | 12/31/19 | g) | 2019-12-31 | c) | 5,847.18 | [8 empty] | 1 | 4
[8 empty] | d) | 3 quarters | d) | - | [12 empty] | 1 | 4
[24 empty] | 1 | 4
4
|  | Jct. Carcor - Prk. 9 Bagsak |  |  | Road Maintenance | 2.5 | MBA | a) | 108618.49 | a) | 01/03/19 | e) | - | a) | 108618.49 | a) | 100% | c. | 100% | a) | 15 | Completed
059 | [7 empty] | b) | Crucio | b) | 03/01/19 | f) | - | b) | 108618.49 | b) | - | d) |  | b) | 480 |  |  | 1 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 79952.88 | [8 empty] | 1 | 4
[8 empty] | d) | - | d) | - | [12 empty] | 1 | 4
[24 empty] | 1 | 4
4
4
|  | Jct. Carcor - Prk. 9 Bagsak |  |  | Road Maintenance | 2.5 | CBRMC | a) | 42284.76 | a) | 01/03/19 | e) | - | a) | 42284.76 | a) | 100% | c) | 100% | a) | 16 | Completed |  |  | 4
059 | [7 empty] | b) | Crucio | b) | 03/22/19 | f) | - | b) | 42284.76 | b) | - | d) | - | b) | 480 |  |  | 1 | 4
[8 empty] | c) | CARCOR MOTOR | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [8 empty] | 1 | 4
[8 empty] | d) | 3 quarters | d) | - | [12 empty] | 1 | 4
|  | Carcor - Jct. Kauswagan |  |  | Road Maintenance | 4.32 | MBA | a) | 264514.71 | a) | 01/03/19 | e) | - | a) | 264514.71 | a) | 100% | c) | 100% | a) | 15 | Completed |  | 1 | 4
060 | [7 empty] | b) | Crucio | b) | 03/18/19 | f) | - | b) | 264514.71 | b) | - | d) |  | b) | 450 |  |  | 1 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 80733.11 | [8 empty] | 1 | 4
[8 empty] | d) | - | d) | - | [12 empty] | 1 | 4
|  | Carcor - Jct. Kauswagan |  |  | Road Maintenance | 4.32 | CBRMC | a) | 48398.27 | a) | 01/03/19 | e) | - | a) | 48398.27 | a) | 100% | c) | 100% | a) | 16 | Completed |  |  | 4
060 | [7 empty] | b) | Crucio | b) | 03/22/19 | f) | - | b) | 48398.27 | b) | - | d) | - | b) | 480 |  |  | 1 | 4
[8 empty] | c) | CARCOR MOTOR | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [8 empty] | 1 | 4
[8 empty] | d) | 3 quarters | d) | - | [12 empty] | 1 | 4
|  | Del Pilar - Prk 9 Bagsak - San Jose |  |  | Road Maintenance | 4.99 | MBA | a) | 170215.76 | a) | 01/03/19 | e) | - | a) | 170215.76 | a) | 100% | c) | 100% | a) | 15 | Completed |  | 1 | 4
061 | [7 empty] | b) | Crucio | b) | 03/01/19 | f) | - | b) | 170215.76 | b) | - | d) | - | b) | 450 |  |  | 1 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 87595.63 | [8 empty] | 1 | 4
[8 empty] | d) | - | d) | - | [12 empty] | 1 | 4
|  | Del Pilar - Prk 9 Bagsak - San Jose |  |  | Road Maintenance | 4.99 | CBRMC | a) | 223674.22 | a) | 01/03/19 | e) | - | a) | 223674.22 | a) | 100% | c) | 100% | a) | 16 | Completed |  | 1 | 4
061 | [7 empty] | b) | Crucio | b) | 03/22/19 | f) | - | b) | 223674.22 | b) | - | d) | - | b) | 480 |  |  | 1 | 4
[8 empty] | c) | SAN JOSE COCONUT | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [8 empty] | 1 | 4
[8 empty] | d) | 3 quarters | d) | - | [12 empty] | 1 | 4
|  | San Juan - New Talisay |  |  | Road Maintenance | 5.13 | MBA | a) | 306261.25 | a) | 01/03/19 | e) | - | a) | 306261.25 | a) | 100% | c) | 100% | a) | 15 | Completed |  | 1 | 4
063 | [7 empty] | b) | Crucio | b) | 02/01/19 | f) | - | b) | 306261.25 | b) | - | d) | - | b) | 450 |  |  | 1 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 85123.48 | [8 empty] | 1 | 4
[8 empty] | d) | - | d) | - | [12 empty] | 1 | 4
|  | San Juan - New Talisay |  |  | Road Maintenance | 5.13 | CBRMC | a) | 93906.31 | a) | 01/03/19 | e) | - | a) | 93906.31 | a) | 100% | c) | 100% | a) | 16 | Completed |  |  | 4
063 | [7 empty] | b) | Crucio | b) | 03/26/19 | f) | - | b) | 93906.31 | b) | - | d) | - | b) | 480 |  |  | 1 | 4
[8 empty] | c) | NEW TALISAY IAWA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [8 empty] | 1 | 4
[8 empty] | d) | 3 quarters | d) | - | [12 empty] | 1 | 4
|  | San Juan - kauswagan - New Cortez |  |  | Road Maintenance | 3.22 | MBA | a) | 187879.04 | a) | 01/03/19 | e) | - | a) | 187879.04 | a) | 100% | c) | 100% | a) | 15 | Completed |  | 1 | 4
064 | [7 empty] | b) | Crucio | b) | 03/18/19 | f) | - | b) | 187879.04 | b) | - | d) | - | b) | 450 |  |  | 1 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 3,025.00 | [8 empty] | 1 | 4
[8 empty] | d) | - | d) | - | [12 empty] | 1 | 4
4
4
|  | San Juan - kauswagan - New Cortez |  |  | Road Maintenance | 3.22 | CBRMC | a) | 63298.26 | a) | 01/03/19 | e) | - | a) | 63298.26 | a) | 100% | c) | 100% | a) | 16 | Completed |  |  | 4
064 | [7 empty] | b) | Crucio | b) | 03/22/19 | f) | - | b) | 63298.26 | b) | - | d) | - | b) | 480 |  |  | 1 | 4
[8 empty] | c) | SAN JOSE COCONUT | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [8 empty] | 1 | 4
[8 empty] | d) | 3 quarters | d) | - | [12 empty] | 1 | 4
|  | New Bohol - Jct. El Unido |  |  | Road Maintenance | 2.12 | MBA | a) | 54989.06 | a) | 01/03/19 | e) | - | a) | 54989.06 | a) | 100% | c) | 100% | a) | 15 | Completed |  |  | 4
065 | [7 empty] | b) | Crucio | b) | 03/01/19 | f) | - | b) | 54989.06 | b) | - | d) | - | b) | 450 |  |  | 1 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 21021.99 | [8 empty] | 1 | 4
[8 empty] | d) | - | d) | - | [12 empty] | 1 | 4
|  | New Bohol - Jct. El Unido |  |  | Road Maintenance | 2.12 | CBRMC | a) | 58861.64 | a) | 01/03/19 | e) | - | a) | 58861.64 | a) | 100% | c) | 100% | a) | 16 | Completed |  | 1 | 4
065 | [7 empty] | b) | Crucio | b) | 03/26/19 | f) | - | b) | 58861.64 | b) | - | d) | - | b) | 480 |  |  | 1 | 4
[8 empty] | c) | MANDISKAB TRIBAL | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [8 empty] | 1 | 4
[8 empty] | d) | 3 quarters | d) | - | [12 empty] | 1 | 4
[24 empty] | 1 | 4
4
|  | New Corella - El unido - Jct. Mesaoy |  |  | Road Maintenance | 8.63 | MBA | a) | 388002.46 | a) | 01/03/19 | e) | - | a) | 388002.46 | a) | 100% | c) | 100% | a) | 15 | Completed |  |  | 4
066 | [7 empty] | b) | Crucio | b) | 02/11/19 | f) | - | b) | 388002.46 | b) | - | d) | - | b) | 450 |  |  | 1 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 58142.76 | [8 empty] | 1 | 4
[8 empty] | d) | - | d) | - | [12 empty] | 1 | 4
|  | New Corella - El unido - Jct. Mesaoy |  |  | Road Maintenance | 8.63 | CBRMC | a) | 233092.08 | a) | 01/03/19 | e) | - | a) | 233092.08 | a) | 100% | c) | 100% | a) | 16 | Completed |  | 1 | 4
066 | [7 empty] | b) | Crucio | b) | 03/26/19 | f) | - | b) | 233092.08 | b) | - | d) | - | b) | 480 |  |  | 1 | 4
[8 empty] | c) | MANDISKAB TRIBAL | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [8 empty] | 1 | 4
[8 empty] | d) | 3 quarters | d) | - | [12 empty] | 1 | 4
|  | Mesaoy - Dasing |  |  | Road Maintenance | 1.39 | MBA | a) | 29749.5 | a) | 01/03/19 | e) | - | a) | 29749.5 | a) | 100% | c) | 100% | a) | 15 | Completed |  | 1 | 4
067 | [7 empty] | b) | Crucio | b) | 03/18/19 | f) | - | b) | 29749.5 | b) | - | d) | - | b) | 450 |  |  | 1 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 10000 | [8 empty] | 1 | 4
[8 empty] | d) | - | d) | - | [12 empty] | 1 | 4
|  | Mesaoy - Dasing |  |  | Road Maintenance | 1.39 | CBRMC | a) | 54152.71 | a) | 01/03/19 | e) | - | a) | 54152.71 | a) | 100% | c) | 100% | a) | 16 | Completed |  | 1 | 4
067 | [7 empty] | b) | Crucio | b) | 03/26/19 | f) | - | b) | 54152.71 | b) | - | d) | - | b) | 480 |  |  | 1 | 4
[8 empty] | c) | MANDISKAB TRIBAL | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [8 empty] | 1 | 4
[8 empty] | d) | 3 quarters | d) | - | [12 empty] | 1 | 4
|  | Jct. San Juan - Jct. Mesaoy |  |  | Road Maintenance | 1.82 | MBA | a) | 106788.95 | a) | 01/03/19 | e) | - | a) | 106788.95 | a) | 100% | c) | 100% | a) | 15 | Completed |  | 1 | 4
068 | [7 empty] | b) | Crucio | b) | 03/01/19 | f) | - | b) | 106788.95 | b) | - | d) | - | b) | 450 |  |  | 1 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 17502.68 | [8 empty] | 1 | 4
[8 empty] | d) | - | d) | - | [12 empty] | 1 | 4
|  | Jct. San Juan - Jct. Mesaoy |  |  | Road Maintenance | 1.82 | CBRMC | a) | 35180.83 | a) | 01/03/19 | e) | - | a) | 35180.83 | a) | 100% | c) | 100% | a) | 16 | Completed |  | 1 | 4
068 | [7 empty] | b) | Crucio | b) | 03/26/19 | f) | - | b) | 35180.83 | b) | - | d) | - | b) | 480 |  |  | 1 | 4
[8 empty] | c) | MANDISKAB TRIBAL | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [8 empty] | 1 | 4
[8 empty] | d) | 3 quarters | d) | - | [12 empty] | 1 | 4
|  | Mesaoy - Jct. Mahayahay |  |  | Road Maintenance | 4.6 | MBA | a) | 146984.46 | a) | 01/03/19 | e) | - | a) | 146984.46 | a) | 100% | c) | 100% | a) | 15 | Completed |  | 1 | 4
069 | [7 empty] | b) | Crucio | b) | 03/18/19 | f) | - | b) | 146984.46 | b) | - | d) | - | b) | 450 |  |  | 1 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 7618.27 | [8 empty] | 1 | 4
[8 empty] | d) | - | d) | - | [12 empty] | 1 | 4
|  | Mesaoy - Jct. Mahayahay |  |  | Road Maintenance | 4.6 | CBRMC | a) | 160103.65 | a) | 01/03/19 | e) | - | a) | 160103.65 | a) | 100% | c) | 100% | a) | 16 | Completed |  |  | 4
069 | [7 empty] | b) | Crucio | b) | 03/22/19 | f) | - | b) | 160103.65 | b) | - | d) | - | b) | 480 |  |  | 1 | 4
[8 empty] | c) | MAHAYAHAY IFA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [8 empty] | 1 | 4
[8 empty] | d) | 3 quarters | d) | - | [12 empty] | 1 | 4
4
4
|  | Mesaoy - New bohol |  |  | Road Maintenance | 5.36 | MBA | a) | 165361.13 | a) | 01/03/19 | e) | - | a) | 165361.13 | a) | 100% | c) | 100% | a) | 15 | Completed |  |  | 4
070 | [7 empty] | b) | Crucio | b) | 03/01/19 | f) | - | b) | 165361.13 | b) | - | d) | - | b) | 480 |  |  | 1 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 2543.9 | [8 empty] | 1 | 4
[8 empty] | d) | - | d) | - | [12 empty] | 1 | 4
|  | Mesaoy - New bohol |  |  | Road Maintenance | 5.36 | CBRMC | a) | 224851.45 | a) | 01/03/19 | e) | - | a) | 224851.45 | a) | 100% | c) | 100% | a) | 16 | Completed |  |  | 4
070 | [7 empty] | b) | Crucio | b) | 03/26/19 | f) | - | b) | 224851.45 | b) | - | d) | - | b) | 480 |  |  | 1 | 4
[8 empty] | c) | MANDISKAB TRIBAL | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [8 empty] | 1 | 4
[8 empty] | d) | 3 quarters | d) | - | [12 empty] | 1 | 4
|  | Bdry. Tagum - Baca - New Corella |  |  | Road Maintenance | 13.01 | MBA | a) | 217182.9 | a) | 01/03/19 | e) | - | a) | 217182.9 | a) | 100% | c) | 100% | a) | 15 | Completed |  | 1 | 4
071 | [7 empty] | b) | Crucio | b) | 03/18/19 | f) | - | b) | 217182.9 | b) | - | d) | - | b) | 450 |  |  | 1 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 19550 | [8 empty] | 1 | 4
[8 empty] | d) | - | d) | - | [12 empty] | 1 | 4
|  | Bdry. Tagum - Baca - New Corella |  |  | Road Maintenance | 13.01 | CBRMC | a) | 214256.36 | a) | 01/03/19 | e) | - | a) | 214256.36 | a) | 100% | c) | 100% | a) | 16 | Completed |  | 1 | 4
071 | [7 empty] | b) | Crucio | b) | 03/26/19 | f) | - | b) | 214256.36 | b) | - | d) | - | b) | 480 |  |  | 1 | 4
[8 empty] | c) | DURIAN DACUDAO | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [8 empty] | 1 | 4
[8 empty] | d) | 3 quarters | d) | - | [12 empty] | 1 | 4
|  | Prk. 1, Maunlom - Prk. 6 Maunlom Road |  |  | Road Maintenance | 3.56 | MBA | a) | 150912.87 | a) | 01/03/19 | e) | - | a) | 150912.87 | a) | 100% | c) | 100% | a) | 15 | Completed |  | 1 | 4
147 | [7 empty] | b) | Crucio | b) | 03/01/19 | f) | - | b) | 150912.87 | b) | - | d) | - | b) | 450 |  |  | 1 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 23025 | [8 empty] | 1 | 4
[8 empty] | d) | - | d) | - | [12 empty] | 1 | 4
|  | Prk. 1, Maunlom - Prk. 6 Maunlom Road |  |  | Road Maintenance | 3.56 | CBRMC | a) | 63973.36 | a) | 01/03/19 | e) | - | a) | 63973.36 | a) | 100% | c) | 100% | a) | 16 | Completed |  | 1 | 4
147 | [7 empty] | b) | Crucio | b) | 03/22/19 | f) | - | b) | 63973.36 | b) | - | d) | - | b) | 480 |  |  | 1 | 4
[8 empty] | c) | THE BEST VEGETABLE | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [8 empty] | 1 | 4
[8 empty] | d) | 3 quarters | d) | - | [12 empty] | 1 | 4
[24 empty] | 1 | 4
|  | New Visayas - Binancian |  |  | Road Maintenance | 7.77 | MBA | a) | 14814.34 | a) | 01/03/19 | e) | - | a) | 14814.34 | a) | 100% | c) | 100% | a) | 15 | Completed |  |  | 44
149 | [7 empty] | b) | Crucio | b) | 03/18/19 | f) | - | b) | 14814.34 | b) | - | d) | - | b) | 450 |  |  | 1 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 5,000.00 | [8 empty] | 1 | 4
[8 empty] | d) | - | d) | - | [12 empty] | 1 | 4
|  | New Visayas - Binancian |  |  | Road Maintenance | 7.77 | CBRMC | a) | 129495.6 | a) | 01/03/19 | e) | - | a) | 129495.6 | a) | 100% | c) | 100% | a) | 16 | Completed |  | 1 | 4
149 | [7 empty] | b) | Crucio | b) | 03/22/19 | f) | - | b) | 129495.6 | b) | - | d) | - | b) | 480 |  |  | 1 | 4
[8 empty] | c) | BUAN IFA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [8 empty] | 1 | 4
[8 empty] | d) | 3 quarters | d) | - | [12 empty] | 1 | 4
|  | Datu Balong - Prk. Mamalian |  |  | Road Maintenance | 3.46 | MBA | a) | 117454.89 | a) | 01/03/19 | e) | - | a) | 117454.89 | a) | 100% | c) | 39.37% | a) | 15 | Completed |  | 1 | 4
150 | [7 empty] | b) | Crucio | b) | 03/18/19 | f) | - | b) | 117454.89 | b) | - | d) | - | b) | 450 |  |  | 1 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 10115 | [8 empty] | 1 | 4
[8 empty] | d) | - | d) | - | [12 empty] | 1 | 4
|  | Datu Balong - Prk. Mamalian |  |  | Road Maintenance | 3.46 | CBRMC | a) | 59264.42 | a) | 01/03/19 | e) | - | a) | 59264.42 | a) | 100% | c) | 100% | a) | 16 | Completed |  | 1 | 4
150 | [7 empty] | b) | Crucio | b) | 03/28/19 | f) | - | b) | 59264.42 | b) | - | d) | - | b) | 480 |  |  | 1 | 4
[8 empty] | c) | DATU BALONG FA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [8 empty] | 1 | 4
[8 empty] | d) | 3 quarters | d) | - | [12 empty] | 1 | 4
4
4
4
4
4
4
4
4
4
4
4
A.2 GENERAL FUND CY 2019 |  |  |  |  | Road Maintenance | KM | MBA/CBRMC | a) | 11,618,834.00 | a) | 01/03/19 | e) | - | a) | 11,618,834.00 | a) | 66% | c) | 66% | a) | 42 | See list of Provincial Roads
Road ID |  | 1. Maintenance Of Various Prov'l. Roads and Bridges Dist 2 |  |  |  | 288.26 |  | b) | Matuguinas | b) | 01/03/19 | f) | - | b) | 11,618,834.00 | b) | - | d) | - | b) | 924 |  |  | FS
[8 empty] | c) | PEO/CBRMC | c) | 12/31/19 | g) | - | c) | - | [8 empty] | AC
11DAN | [9 empty] | d) | - | [12 empty] | AC
[8 empty] | d) | 261 days | d) | - | [12 empty] | AC
|  | Cebulano - Mangalcal |  |  | Road Maintenance | 4.17 | MBA | a) | 142161.87 | a) | 01/03/19 | e) | - | a) | 142161.87 | a) | 100% | c) | 100% | a) | 9 | Completed |  | AC | 4
| 073 | [6 empty] | b) | Clar | b) | 2019-01-15 | f) | - | b) | 142161.87 | b) | - | d) | - | b) | 18 |  |  | 2 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 118,609.29 | [8 empty] | 2 | 4
[8 empty] | d) | - | d) | - | [12 empty] | 2 | 4
|  | Tubod - basa - Mangalcal |  |  | Road Maintenance | 3.93 | MBA | a) | 156875.9 | a) | 01/03/19 | e) | - | a) | 156875.9 | a) | 100% | c) | 100% | a) | 9 | Completed |  | 2 | 4
074 | [7 empty] | b) | Clar | b) | 2019-01-15 | f) | - | b) | 156875.9 | b) | - | d) | - | b) | 18 |  |  | 2 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 143,372.65 | [8 empty] | 2 | 4
[8 empty] | d) | - | d) | - | [12 empty] | 2 | 4
|  | Upper Mangalcal - Lower Mangalcal |  |  | Road Maintenance | 2.43 | 0 | a) | 79237.14 | a) | 01/03/19 | e) | - | a) | 79237.14 | a) | 100% | c) | 100% | a) | 9 | Completed |  | 2 | 4
078 | [7 empty] | b) | Clar | b) | 2019-01-14 | f) | - | b) | 79237.14 | b) | - | d) | - | b) | 27 |  |  | 2 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 69,430.97 | [8 empty] | 2 | 4
[8 empty] | d) | - | d) | - | [12 empty] | 2 | 4
|  | Jct. Highway Carmen - Mangalcal - Tubod |  |  | Road Maintenance | 11.34 | MBA | a) | 463135.67 | a) | 01/03/19 | e) | - | a) | 463135.67 | a) | 100% | c) | 100% | a) | 9 | Completed |  | 2 | 4
082 | [7 empty] | b) | Clar | b) | 01/10/19 | f) | - | b) | 463135.67 | b) | - | d) | - | b) | 45 |  |  | 2 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 170,106.43 | [8 empty] | 2 | 4
[8 empty] | d) | - | d) | - | [12 empty] | 2 | 4
|  | Jct. Highway Carmen - Mangalcal - Tubod |  |  | Road Maintenance | 11.34 | 0 | a) | 253557.37 | a) | 01/03/19 | e) | - | a) | 253557.37 | a) | 100% | c) | 100% | a) | 10 | Completed |  | 2 | 4
082 | [7 empty] | b) | Maligro | b) | 03/25/19 | f) | - | b) | 253557.37 | b) | - | d) | - | b) | 40 |  |  | 2 | 4
[8 empty] | c) | TUBOD CENTRO LOWER IRRIGATORS ASSOCIATION | c) | 09/25/19 | g) | 2019-12-31 | c) | - | [8 empty] | 2 | 4
[8 empty] | d) | 3 quarters | d) | - | [12 empty] | 2 | 4
|  | Jct. Highway Sto. Niño - Kabanlakan - La Paz |  |  | Road Maintenance | 2.13 | MBA | a) | 76067.88 | a) | 01/03/19 | e) | - | a) | 76067.88 | a) | 100% | c) | 100% | a) | 9 | Completed |  | 2 | 4
084 | [7 empty] | b) | Clar | b) | 01/10/19 | f) | - | b) | 76067.88 | b) | - | d) | - | b) | 45 |  |  | 2 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 66,477.91 | [8 empty] | 2 | 4
[8 empty] | d) | - | d) | - | [12 empty] | 2 | 4
|  | Ising - Sto Niño |  |  | Road Maintenance | 2.07 | 0 | a) | 82413.14 | a) | 01/03/19 | e) | - | a) | 82413.14 | a) | 100% | c) | 100% | a) | 5 | Completed |  | 2 | 4
085 | [7 empty] | b) | Clar | b) | 01/17/19 | f) | - | b) | 82413.14 | b) | - | d) | - | b) | 15 |  |  | 2 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 27,093.24 | [8 empty] | 2 | 4
[8 empty] | d) | - | d) | - | [12 empty] | 2 | 4
|  | Ising - Sadpodon - Taba - Dila -Dila |  |  | Road Maintenance | 5.68 | MBA | a) | 248941.33 | a) | 01/03/19 | e) | - | a) | 248941.33 | a) | 100% | c) | 100% | a) | 9 | Completed |  | 2 | 4
086 | [7 empty] | b) | Clar | b) | 01/12/19 | f) | - | b) | 248941.33 | b) | - | d) | - | b) | 27 |  |  | 2 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 82,329.02 | [8 empty] | 2 | 4
[8 empty] | d) | - | d) | - |  |  |  | . | [8 empty] | 2 | 4
[24 empty] | 2 | 4
|  | Tuganay - taba |  |  | Road Maintenance | 4.27 | 0 | a) | 291377.9 | a) | 01/03/19 | e) | - | a) | 291377.9 | a) | 70% | c) | 70% | a) | 9 | Completed |  |  | 4
087 | [7 empty] | b) | Clar | b) | 01/09/19 | f) | - | b) | 291377.9 | b) | - | d) | - | b) | 27 |  |  | 2 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 12/31/2019 | c) | 238,412.28 | [8 empty] | 2 | 4
[8 empty] | d) | - | d) | - | [12 empty] | 2 | 4
|  | Jct. Highway Tuganay - Taba |  |  | Road Maintenance | 4.4 | MBA | a) | 32972.82 | a) | 01/03/19 | e) | - | a) | 32972.82 | a) | 65% | c) | 65% | a) | 9 | Completed |  | 2 | 4
088 | [7 empty] | b) | Clar | b) | 01/22/19 | f) | - | b) | 32972.82 | b) | - | d) | - | b) | 18 |  |  | 2 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 12/31/2019 | c) | 22,639.09 | [8 empty] | 2 | 4
[8 empty] | d) | - | d) | - | [12 empty] | 2 | 4
|  | Jct. Highway Ising - Magsaysay |  |  | Road Maintenance | 10.84 | 0 | a) | 417818.12 | a) | 01/03/19 | e) | - | a) | 417818.12 | a) | 60% | c) | 60% | a) | 10 | Completed |  | 2 | 4
089 | [7 empty] | b) | Clar | b) | 01/22/19 | f) | - | b) | 417818.12 | b) | - | d) | - | b) | 50 |  |  | 2 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 12/31/2019 | c) | 313,488.39 | [8 empty] | 2 | 4
[8 empty] | d) | - | d) | - | [12 empty] | 2 | 4
4
4
4
|  | New Camiling - Alejal - Lower Magsaysay |  |  | Road Maintenance | 6.73 | MBA | a) | 240878.08 | a) | 01/03/19 | e) | - | a) | 240878.08 | a) | 80% | c) | 80% | a) | 4 | Completed |  | 2 | 4
091 | [7 empty] | b) | Clar | b) | 01/22/19 | f) | - | b) | 240878.08 | b) | - | d) | - | b) | 20 |  |  | 2 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 12/31/2019 | c) | - | [8 empty] | 2 | 4
[8 empty] | d) | - | d) | - | [12 empty] | 2 | 4
|  | Jct. highway Tuganay - Anibongan |  |  | Road Maintenance | 3.66 | 0 | a) | 150684.44 | a) | 01/03/19 | e) | - | a) | 150684.44 | a) | 100% | c) | 100% | a) | 6 | Completed |  | 2 | 4
094 | [7 empty] | b) | Clar | b) | 01/22/19 | f) | - | b) | 150684.44 | b) | - | d) | - | b) | 18 |  |  | 2 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 12/31/2019 | c) | - | [8 empty] | 2 | 4
[8 empty] | d) | - | d) | - | [12 empty] | 2 | 4
|  | Anibongan - Guadalupe |  |  | Road Maintenance | 2.48 | MBA | a) | 91325.06 | a) | 01/03/19 | e) | - | a) | 91325.06 | a) | 100% | c) | 100% | a) | 9 | Completed |  | 2 | 4
095 | [7 empty] | b) | Clar | b) | 01/23/19 | f) | - | b) | 91325.06 | b) | - | d) | - | b) | 18 |  |  | 2 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 12/31/2019 | c) | - | [8 empty] | 2 | 4
[8 empty] | d) | - | d) | - | [12 empty] | 2 | 4
|  | Tuganay - Anibongan - San Isidro |  |  | Road Maintenance | 7.22 | 0 | a) | 139979.8 | a) | 01/03/19 | e) | - | a) | 139979.8 | a) | 100% | c) | 100% | a) | 9 | Completed |  | 2 | 4
096 | [7 empty] | b) | Clar | b) | 01/24/19 | f) | - | b) | 139979.8 | b) | - | d) | - | b) | 36 |  |  | 2 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 12/31/2019 | c) | 1890.37 | [8 empty] | 2 | 4
[8 empty] | d) | - | d) | - | [12 empty] | 2 | 4
|  | Jct. Anibongan - Prk. 2, 7, 5, San Isidro |  |  | Road Maintenance | 3.14 | MBA | a) | 104378.03 | a) | 01/03/19 | e) | - | a) | 104378.03 | a) | 100% | c) | 100% | a) | 10 | Completed |  | 2 | 4
097 | [7 empty] | b) | Clar | b) | 01/24/19 | f) | - | b) | 104378.03 | b) | - | d) | - | b) | 20 |  |  | 2 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 12/31/2019 | c) | 56,087.50 | [8 empty] | 2 | 4
[8 empty] | d) | - | d) | - | [12 empty] | 2 | 4
|  | Anibongan - Salvacion - Cabay-angan |  |  | Road Maintenance | 6.93 | 0 | a) | 415461.61 | a) | 01/03/19 | e) | - | a) | 415461.61 | a) | 100% | c) | 100% | a) | 9 | Completed |  | 2 | 4
098 | [7 empty] | b) | Clar | b) | 01/25/19 | f) | - | b) | 415461.61 | b) | - | d) | - | b) | 45 |  |  | 2 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 12/31/2019 | c) | - | [8 empty] | 2 | 4
[8 empty] | d) | - | d) | - | [12 empty] | 2 | 4
|  | Jct. Highway Guadalupe - Bdry. Tagum |  |  | Road Maintenance | 7.9 | MBA | a) | 456131.09 | a) | 01/03/19 | e) | - | a) | 456131.09 | a) | 100% | c) | 100% | a) | 9 | Completed |  | 2 | 4
101 | [7 empty] | b) | Clar | b) | 01/25/19 | f) | - | b) | 456131.09 | b) | - | d) | - | b) | 18 |  |  | 2 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 12/31/2019 | c) | - | [8 empty] | 2 | 4
[8 empty] | d) | - | d) | - | [12 empty] | 2 | 4
|  | Jct. Highway Guadalupe - Bdry. Tagum |  |  | Road Maintenance | 7.9 | 0 | a) | 228201.66 | a) | 01/03/19 | e) | - | a) | 228201.66 | a) | 100% | c) | 100% | a) | 8 | Completed |  | 2 | 4
101 | [7 empty] | b) | Maligro | b) | 03/25/19 | f) | - | b) | 228201.66 | b) | - | d) | - | b) | 40 |  |  | 2 | 4
[8 empty] | c) | LAMPIA PAG-ASA IRRIGATORS ASSOCIATION, INC. | c) | 12/25/19 | g) | 12/31/2019 | c) | - | [8 empty] | 2 | 4
[8 empty] | d) | 3 quarters | d) | - | [12 empty] | 2 | 4
|  | Poblacion Dujali - Prk. 8 Dujali |  |  | Road Maintenance | 8.2 | MBA | a) | 285600.05 | a) | 01/03/19 | e) | - | a) | 285600.05 | a) | 100% | c) | 100% | a) | 10 | Completed |  | 2 | 4
105 | [7 empty] | b) | Clar | b) | 01/28/19 | f) | - | b) | 285600.05 | b) | - | d) | - | b) | 50 |  |  | 2 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 12/31/2019 | c) | - | [8 empty] | 2 | 4
[8 empty] | d) | - | d) | - | [12 empty] | 2 | 4
|  | Dujali - San Isidro |  |  | Road Maintenance | 3 | 0 | a) | 130319.3 | a) | 01/03/19 | e) | - | a) | 130319.3 | a) | 100% | c) | 100% | a) | 8 | Completed |  | 2 | 4
107 | [7 empty] | b) | Gamad | b) | 01/28/19 | f) | - | b) | 130319.3 | b) | - | d) | - | b) | 30 |  |  | 2 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 12/31/2019 | c) | 45,943.12 | [8 empty] | 2 | 4
[8 empty] | d) | - | d) | - | [12 empty] | 2 | 4
|  | Prk. 5, RJS - Prk. 6 New Casay |  |  | Road Maintenance | 2.73 | MBA | a) | 235277 | a) | 01/03/19 | e) | - | a) | 235277 | a) | 100% | c) | 100% | a) | 2 | Completed |  | 2 | 4
109 | [7 empty] | b) | Gamad | b) | 01/28/19 | f) | - | b) | 235277 | b) | - | d) | - | b) | 6 |  |  | 2 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 12/31/2019 | c) | 90,745.35 | [8 empty] | 2 | 4
[8 empty] | d) | - | d) | - | [12 empty] | 2 | 4
|  | Prk. 5 - Prk. 1 Pawas Dujali |  |  | Road Maintenance | 2.18 | 0 | a) | 76067.68 | a) | 01/03/19 | e) | - | a) | 76067.68 | a) | 100% | c) | 100% | a) | 10 | Completed |  | 2 | 4
112 | [7 empty] | b) | Gamad | b) | 01/18/19 | f) | - | b) | 76067.68 | b) | - | d) | - | b) | 20 |  |  | 2 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 12/31/2019 | c) | 40,112.50 | [8 empty] | 2 | 4
[8 empty] | d) | - | d) | - | [12 empty] | 2 | 4
|  | Dujali - Balisong - Magupising |  |  | Road Maintenance | 5.52 | MBA | a) | 260591.93 | a) | 01/03/19 | e) | - | a) | 260591.93 | a) | 100% | c) | 100% | a) | 4 | Completed |  | 2 | 4
113 | [7 empty] | b) | Gamad | b) | 01/09/19 | f) | - | b) | 260591.93 | b) | - | d) | - | b) | 8 |  |  | 2 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 12/31/2019 | c) | - | [8 empty] | 2 | 4
[8 empty] | d) | - | d) | - | [12 empty] | 2 | 4
4
4
4
|  | Dujali - Pawas - San Vicente |  |  | Road Maintenance | 4.42 | 0 | a) | 139536.42 | a) | 01/03/19 | e) | - | a) | 139536.42 | a) | 100% | c) | 100% | a) | 10 | Completed |  | 2 | 4
117 | [7 empty] | b) | Gamad | b) | 01/22/19 | f) | - | b) | 139536.42 | b) | - | d) | - | b) | 18 |  |  | 2 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 12/31/2019 | c) | 52,133.86 | [8 empty] | 2 | 4
[8 empty] | d) | - | d) | - | [12 empty] | 2 | 4
|  | Jct. Salvacion - San Vicente - Cabay-angan |  |  | Road Maintenance | 3.45 | MBA | a) | 247460.9 | a) | 01/03/19 | e) | - | a) | 247460.9 | a) | 100% | c) | 100% | a) | 10 | Completed |  | 2 | 4
118 | [7 empty] | b) | Gamad | b) | 01/23/19 | f) | - | b) | 247460.9 | b) | - | d) | - | b) | 18 |  |  | 2 | 4
[8 empty] | c) | PEO | c) | 02/31/19 | g) | 12/31/2019 | c) | 151,887.50 | [8 empty] | 2 | 4
[8 empty] | d) | - | d) | - | [12 empty] | 2 | 4
|  | Jct. Salvacion - San Vicente - Cabay-angan |  |  | Road Maintenance | 3.45 | 0 | a) | 152134.44 | a) | 01/03/19 | e) | - | a) | 152134.44 | a) | 100% | c) | 100% | a) | 8 | Completed |  | 2 | 4
118 | [7 empty] | b) | Gamad | b) | 03/26/19 | f) | - | b) | 152134.44 | b) | - | d) | - | b) | 36 |  |  | 2 | 4
[8 empty] | c) | BALISONG SAN VICENTE IRRIGATORS ASSOCIATION | c) | 12/26/19 | g) | 12/31/2019 | c) | [9 empty] | 2 | 4
[8 empty] | d) | 3 quarters | d) | - | [10 empty] | Completed |  | 2 | 4
|  | Dujali - San Miguel |  |  | Road Maintenance | 3.95 | MBA | a) | 101202.04 | a) | 01/03/19 | e) | - | a) | 101202.04 | a) | 80% | c) | 90% | a) | 11 |  |  | 2 | 4
119 | [7 empty] | b) | Gamad | b) | 01/10/19 | f) | - | b) | 101202.04 | b) | - | d) | - | b) | 22 |  |  | 2 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | - | c) | 90,350.03 | [8 empty] | 2 | 4
[8 empty] | d) | - | d) | - | [12 empty] | 2 | 4
|  | San Miguel - Casig-ang |  |  | Road Maintenance | 2.55 | 0 | a) | 79237.14 | a) | 01/03/19 | e) | - | a) | 79237.14 | a) | 100% | c) | 100% | a) | 10 | Completed |  | 2 | 4
122 | [7 empty] | b) | Gamad | b) | 01/24/19 | f) | - | b) | 79237.14 | b) | - | d) | - | b) | 10 |  |  | 2 | 4
[8 empty] | c) | BALISONG SAN VICENTE IRRIGATORS ASSOCIATION | c) | 12/31/19 | g) | 12/31/2019 | c) | 40,112.50 | [8 empty] | 2 | 4
[8 empty] | d) | - | d) | - | [12 empty] | 2 | 4
|  | Prk. Magsaysay - Lunga-og - Dalisay |  |  | Road Maintenance | 2.81 | MBA | a) | 79762.14 | a) | 01/03/19 | e) | - | a) | 79762.14 | a) | 100% | c) | 100% | a) | 8 | Completed |  | 2 | 4
127 | [7 empty] | b) | Gamad | b) | 01/30/19 | f) | - | b) | 79762.14 | b) | - | d) | - | b) | 8 |  |  | 2 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 12/31/2019 | c) | 40,612.50 | [8 empty] | 2 | 4
[8 empty] | d) | - | d) | - | [12 empty] | 2 | 4
|  | Prk. Apitong - Upper Balisong - Dalisay |  |  | Road Maintenance | 4.6 | 0 | a) | 137846.03 | a) | 01/03/19 | e) | - | a) | 137846.03 | a) | 100% | c) | 100% | a) | 8 | Completed |  | 2 | 4
128 | [7 empty] | b) | Gamad | b) | 01/31/19 | f) | - | b) | 137846.03 | b) | - | d) | - | b) | 8 |  |  | 2 | 4
[8 empty] | c) | BALISONG SAN VICENTE IRRIGATORS ASSOCIATION | c) | 12/31/19 | g) | 12/31/2019 | c) | - | [8 empty] | 2 | 4
[8 empty] | d) | - | d) | - | [12 empty] | 2 | 4
|  | Sitio Paradise - Magkakaisa - Esperanza |  |  | Road Maintenance | 1.75 | MBA | a) | 66552.75 | a) | 01/03/19 | e) | - | a) | 66552.75 | a) | 100% | c) | 100% | a) | 8 | Completed |  | 2 | 4
129 | [7 empty] | b) | 79762.14 | b) | 01/22/19 | f) | - | b) | 66552.75 | b) | - | d) | - | b) | 8 |  |  | 2 | 4
[8 empty] | c) | Gamad | c) | 12/31/19 | g) | 12/31/2019 | c) | 22,246.26 | [8 empty] | 2 | 4
[8 empty] | d) | - | d) | - | [12 empty] | 2 | 4
|  | Los Amigos 1 - Esperanza - Los Amigos 2 |  |  | Road Maintenance | 3.59 | 0 | a) | 101202.04 | a) | 01/03/19 | e) | - | a) | 101202.04 | a) | 100% | c) | 100% | a) | 10 | Completed |  | 2 | 4
130 | [7 empty] | b) | Gamad | b) | 01/24/19 | f) | - | b) | 101202.04 | b) | - | d) | - | b) | 20 |  |  | 2 | 4
[8 empty] | c) | BALISONG SAN VICENTE IRRIGATORS ASSOCIATION | c) | 12/31/19 | g) | 12/31/2019 | c) | 50,837.50 | [8 empty] | 2 | 4
[8 empty] | d) | - | d) | - | [12 empty] | 2 | 4
|  | Mugas - Lunga-og |  |  | Road Maintenance | 2.68 | MBA | a) | 66552.75 | a) | 01/03/19 | e) | - | a) | 91,693.64 | a) | 100% | c) | 100% | a) | 6 | Completed |  | 2 | 4
132 | [7 empty] | b) | 79762.14 | b) | 01/17/19 | f) | - | b) | 91,693.64 | b) | - | d) | - | b) | 24 |  |  | 2 | 4
[8 empty] | c) | Gamad | c) | 12/31/19 | g) | 12/31/2019 | c) | 50,837.50 | [8 empty] | 2 | 4
[8 empty] | d) | - | d) | - | [12 empty] | 2 | 4
|  | Pantaron - Mugas |  |  | Road Maintenance | 3.35 | 0 | a) | 101202.04 | a) | 01/03/19 | e) | - | a) | 101202.04 | a) | 100% | c) | 100% | a) | 9 | Completed |  | 2 | 4
133 | [7 empty] | b) | Gamad | b) | 01/23/19 | f) | - | b) | 101202.04 | b) | - | d) | - | b) | 18 |  |  | 2 | 4
[8 empty] | c) | BALISONG SAN VICENTE IRRIGATORS ASSOCIATION | c) | 12/31/19 | g) | 12/31/2019 | c) | 90,349.93 | [8 empty] | 2 | 4
[8 empty] | d) | - | d) | - | [12 empty] | 2 | 4
|  | Sto. Tomas - Bdry. Mamacao |  |  | Road Maintenance | 4.9 | MBA | a) | 110710.44 | a) | 01/03/19 | e) | - | a) | 110710.44 | a) | 100% | c) | 100% | a) | 10 | Completed |  | 2 | 4
135 | [7 empty] | b) | 79762.14 | b) | 01/21/19 | f) | - | b) | 110710.44 | b) | - | d) | - | b) | 40 |  |  | 2 | 4
[8 empty] | c) | Gamad | c) | 12/31/19 | g) | 12/31/2019 | c) | 50,837.50 | [8 empty] | 2 | 4
[8 empty] | d) | - | d) | - | [12 empty] | 2 | 4
|  | Fd. Rd. 3 - San Jose |  |  | Road Maintenance | 4.55 | 0 | a) | 147367.49 | a) | 01/03/19 | e) | - | a) | 147367.49 | a) | 100% | c) | 100% | a) | 10 | Completed |  | 2 | 4
136 | [7 empty] | b) | Gamad | b) | 01/25/19 | f) | - | b) | 147367.49 | b) | - | d) | - | b) | 30 |  |  | 2 | 4
[8 empty] | c) | BALISONG SAN VICENTE IRRIGATORS ASSOCIATION | c) | 12/31/19 | g) | 12/31/2019 | c) | 56,174.69 | [8 empty] | 2 | 4
[8 empty] | d) | - | d) | - | [12 empty] | 2 | 4
4
4
|  | Menzi - balagunan - Tulalian |  |  | Road Maintenance | 10.63 | MBA | a) | 520167.79 | a) | 01/03/19 | e) | - | a) | 520167.79 | a) | 100% | c) | 100% | a) | 6 | Completed |  | 2 | 4
138 | [7 empty] | b) | 79762.14 | b) | 01/07/19 | f) | - | b) | 520167.79 | b) | - | d) | - | b) | 18 |  |  | 2 | 4
[8 empty] | c) | Gamad | c) | 12/31/19 | g) | 12/31/2019 | c) | 204,850.57 | [8 empty] | 2 | 4
[8 empty] | d) | - | d) | - | [12 empty] | 2 | 4
|  | Jct. Bdry. Tagum - Talomo |  |  | Road Maintenance | 12.01 | 0 | a) | 407429.19 | a) | 01/03/19 | e) | - | a) | 407429.19 | a) | 100% | c) | 100% | a) | 10 | Completed |  | 2 | 4
145 | [7 empty] | b) | Gamad | b) | 01/11/19 | f) | - | b) | 407429.19 | b) | - | d) | - | b) | 50 |  |  | 2 | 4
[8 empty] | c) | BALISONG SAN VICENTE IRRIGATORS ASSOCIATION | c) | 12/31/19 | g) | 12/31/2019 | c) | 168,544.84 | [8 empty] | 2 | 4
[8 empty] | d) | - | d) | - | [12 empty] | 2 | 4
|  | San Jose - Sitio Mahayahay, Magwawa |  |  | Road Maintenance | 0.84 | MBA | a) | 7919.35 | a) | 01/03/19 | e) | - | a) | 7919.35 | a) | 100% | c) | 100% | a) | 2 | Completed |  | 2 | 4
151 | [7 empty] | b) | 79762.14 | b) | 01/16/19 | f) | - | b) | 7919.35 | b) | - | d) | - | b) | 8 |  |  | 2 | 4
[8 empty] | c) | Gamad | c) | 12/31/19 | g) | 12/31/2019 | c) | 1,509.27 | [8 empty] | 2 | 4
[8 empty] | d) | - | d) | - | [12 empty] | 2 | 4
B. 20% DEVELOPMENT FUND CY 2019 | [23 empty] | FS
[5 empty] | Type | Physical | Mode | PROJECT DATA | [6 empty] | Financial (000) | Physical Accompl;ishment |  |  |  | Employment
|  | Name of Project |  |  | of | Target | of | a.)Project Cost |  | a.)Date A lot. Rel. |  | e.)# of days |  |  | a.) Program | a.) Planned |  | c.) Actual |  | Generated # |  |  | REMRRKS
[5 empty] | Project | (Discrip tion) | Impl. | b.)Project Engineer |  | b.)Date Started |  |  | suspended |  | b.)Allotment | b.) Revised |  | d.) Slippage |  | a.) Persons
[7 empty] | MBA / | c.)Implementor |  | c.)Target Compl. |  | f.) # of days extended |  |  | c.)Disbursement |  |  |  |  | b.) Man-days
[7 empty] | CBRMC |  |  |  | Date | g.)Date Completed
Road ID |  | 1. Rehabilitation Of Various Prov'l. Roads and Bridges Dist. 1 |  |  | Road Rehabilitation | KM | MBA | a) | 41465029 | a) | 01/03/19 | e) | - | a) | 41465029 | a) | - | c) | - | a) | 46 | See list of Provincial Roads |  | FS
[6 empty] | 109.55 |  | b) | Paraguya | b) | 01/03/19 | f) | - | b) | 41465029 | b) | - | d) | - | b) | 920 |  |  | AC
11DAN | [7 empty] | c) | PEO | c) | 12/31/19 | g) | - | c) | - | [8 empty] | AC
[10 empty] | d) | - | [12 empty] | AC
[8 empty] | d) | 261 days | d) | - | [12 empty] | AC
|  | Jct. Highway Canatan - Doña Andrea |  |  | Road Rehabilitation | 4.34 | Admin | a) | 2,000,000.00 | a) | 2019-12-06 | e) | - | a) | 2,000,000.00 | a) | - | c) | - | a) | - | For implementation |  | AC
007 | [7 empty] | b) | MJ / Kinanahan | b) | - | f) | - | b) | 2,000,000.00 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
|  | Pamacaun - Lasang Banate |  |  | Road Rehabilitation | 4.34 | Admin | a) | 2000000 | a) | 2019-06-27 | e) | - | a) | 2000000 | a) | - | c) | - | a) | - | For implementation |  | 1
015 | [7 empty] | b) | Gone | b) | - | f) | - | b) | 2000000 | b) | - | d) | - | b) | - | Waiting for the delivery of geo-grid |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [6 empty] | materials. An approved request letter |  | 1
[8 empty] | d) | - | d) | - | [10 empty] | dated Dec. 3, 2019 for the extension of 50 days from Provincial Administrator Engr. Rabanoz is on file |  | 1
|  | Kapalong - Mabantao - Florida |  |  | Road Rehabilitation | 7.86 | Admin | a) | 1231000 | a) | 2019-01-31 | e) | - | a) | 1231000 | a) | 70.98% | c) | 70.98% | a) | - | Waiting for the availability of the long arm backhoe |  | 1
016 | [7 empty] | b) | Aparece | b) | - | f) | - | b) | 1231000 | b) | - | d) | 0% | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
|  | Jct. Highway Gabuyan - Semong - Dagohoy |  |  | Road Rehabilitation | 6.97 | Admin | a) | 2492000 | a) | 01/03/19 | e) | - | a) | 2492000 | a) | - | c) | - | a) | - | Re-aligned to Impvt of km.9 Sagayen - Sawata Provincial Road Phase II ( AIP 3rd revision CY 2019 / SB no.4, 2019) |  | 1
017 | [7 empty] | b) |  | b) | - | f) | - | b) | 2492000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
|  | Sto. Niño - Palma Gil - Sitio Opao |  |  | Road Rehabilitation | 11.6 | Admin | a) | 1901000 | a) | 2019-06-19 | e) | - | a) | 1901000 | a) | - | c) | - | a) | - | NTP not yet serve to Tagum Builders because they have not yet complied with the construction safety requirement |  | 1
019 | [7 empty] | b) | Lumapat | b) | - | f) | - | b) | 1901000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
|  | Daligdigon - Lumabag |  |  | Road Rehabilitation | 11.6 | Admin | a) | 680000 | a) | 01/03/19 | e) | - | a) | 680000 | a) | - | c) | - | a) | - | Re-aligned to Impvt of km.9 Sagayen - Sawata Provincial Road Phase II ( AIP 3rd revision CY 2019 / SB no.4, 2019) |  | 1
022 | [7 empty] | b) |  | b) | - | f) | - | b) | 680000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
|  | Sto. Niño - Daligdigon - Paiton |  |  | Road Rehabilitation | 11.6 | Admin | a) | 3000000 | a) | 2019-10-03 | e) | - | a) | 3000000 | a) | - | c) | - | a) | - | Temporary suspended, materials for re-PR |  | 1
023 | [7 empty] | b) | Crucio | b) | - | f) | - | b) | 3000000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
|  | Jct. Paiton - Mibolo |  |  | Road Rehabilitation | 23.9 | Admin | a) | 6000000 | a) | 2019-03-25 | e) | - | a) | 6000000 | a) | 21.05% | c) | 21.05% | a) | - | 22% as of Nov. 30, 2019 Temporary suspended because the materials for the box culvert was re-PR |  | 1
024 | [7 empty] | b) | Lumapat | b) | Aug.1, 2019 | f) | - | b) | 6000000 | b) | - | d) | 0% | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
|  | Monte Dujali - Gupitan |  |  | Road Rehabilitation | 4.58 | Admin | a) | 1200000 | a) | 2019-12-06 | e) | - | a) | 1200000 | a) | - | c) | - | a) | - |  |  | 1
037 | [7 empty] | b) | MJ/Kinanahan | b) | - | f) | - | b) | 1200000 | b) | - | d) | - | b) | - | For implementation |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
|  | Jct. Sawata - Bdry. Binasbas |  |  | Road Rehabilitation | 0.46 | Admin | a) | 500000 | a) | 2019-06-19 | e) | - | a) | 500000 | a) | - | c) | - | a) | - |  |  | 1
043 | [7 empty] | b) | MJ/Kinanahan | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - | For implementation |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
|  | New Corella - Saug |  |  | Road Rehabilitation | 12.52 | Admin | a) | 6500000 | a) | 2019-03-12 | e) | - | a) | 6500000 | a) | 29.54% | c) | 29.54% | a) | 19 | Temporary suspended because the equipmenta were pulled out to fast track the implementation of Km. 9 Sagayen- Sawata Provincial Road (CMGP) |  | 1
048 | [7 empty] | b) | MJ/Kinanahan | b) | 03/26/19 | f) | - | b) | 6500000 | b) | - | d) | - | b) | 570 |  |  | 1
[8 empty] | c) | PEO | c) | 12/31/19 | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
|  | Jct. Monte Carlo - Upper Cabaywa - Canatan |  |  | Road Rehabilitation | 4.61 | Admin | a) | 8838000 | a) | 2019-01-31 | e) | - | a) | 8838000 | a) | 89.5% | c) | 89.5% | a) | 19 | On -going 90% accomplished. The target date of completion was Dec. 31, 2019, for process time extension request |  | 1
050 | [7 empty] | b) | Garcia | b) | 03/26/19 | f) | - | b) | 8838000 | b) | - | d) | 0% | b) | 570 |  |  | 1
[8 empty] | c) | PEO | c) | 12/31/19 | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
[5 empty] | Road Rehabilitation |  |  | a. )P 500,000.00 |  | a.) 01/31/19 |  |  |  | a.) 500,000.00 | [9 empty] | 1 | 4
|  | Purok 10 Pob. Road, New Corella | [7 empty] | b.) Feb. 16, 2019 |  |  |  | b.) 500,000.00 | [7 empty] | Completed |  | 1 | 4
[12 empty] | g.) Feb. 28, 2019 | [11 empty] | 1 | 4
[24 empty] | 1 | 4
[5 empty] | Road Rehabilitation |  |  | a.)1,815,000.00 |  | a.) 01/31/19 |  |  |  | a.) 1,815,000.00 | [9 empty] | 1 | 4
|  | Purok 7 Pob- Jct. New Sambog | [7 empty] | b.)March 1, 2019 |  |  |  | b.) 1,815,000.00 | [7 empty] | Completed |  | 1 | 4
[12 empty] | g.) May 15, 2019 | [11 empty] | 1 | 4
[24 empty] | 1 | 4
[5 empty] | Road Rehabilitation |  |  | a.) 1,389,000.00 |  | a.) 01/31/19 |  |  |  | a.) 1,389,000.00 | [7 empty] | Completed with a savings of P303,898.08 furtherance and is for implementation |  | 1 | 4
|  | Del Pilar- El Unido Road | [5 empty] | b.) Fabian |  | b.) March 18,2019 |  |  |  | a.) 1,389,000.00 | [9 empty] | 1 | 4
[12 empty] | g.) May 8, 2019 | [11 empty] | 1 | 4
[24 empty] | 1 | 4
|  | Bdry. Tagum - Baca - New Corella |  |  | Road Rehabilitation | 13.01 | Admin | a) | 1419029 | a) | 01/03/19 | e) | - | a) | 1419029 | a) | - | c) | - | a) | - | Re-aligned to Impvt of km.9 Sagayen Sawata Provincial Road Phase II (SB. No. 4 CY 2019) |  | 1
071 | [7 empty] | b) | Crucio | b) | - | f) | - | b) | 1419029 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
1
1
|  | SUPPLEMENTAL BUDGET NO 4 CY 2019 / CONTINUING APPROPRIATION | [21 empty] | AC
AC
[8 empty] | a.) 7,742,775.95 | [5 empty] | a.) 7,742,775.95 | [7 empty] | Waiting for the delivery of materials |  | 1
|  | Impvt. of Km. 9 Sagayen - Sawata Provincial Road Phase II | [5 empty] | b.) Kenny | [5 empty] | b.) 7,742,775.95 | [9 empty] | 1
1
1
Road ID |  | 1. Rehabilitation Of Various Prov'l. Roads and Bridges Dist 2 |  |  | Road Rehabilitation | KM | Admin | a) | 46740117 | a) | 01/03/19 | [10 empty] | See list of Provincial Roads
[6 empty] | 115.62 |  | b) | Matuguinas | b) | - | [12 empty] | AC
11DAN | [7 empty] | c) | PEO | c) | - | [12 empty] | AC
[10 empty] | d) | - | [12 empty] | AC
[8 empty] | d) | 261 days | d) | - | [12 empty] | AC
|  | Jct. Highway Sto. Niño - Cebulano |  |  | Road Rehabilitation | 2.09 | Admin | a) | 1045000 | a) | 2019-03-18 | e) | - | a) | 1045000 | a) | 20% | c) | 20% | a) | 11 | On-going |  | AC
072 | [7 empty] | b) | Obar | b) | 2019-05-21 | f) | - | b) | 1045000 | b) | - | d) | - | b) | 55 |  |  | 2
[8 empty] | c) | PEO | c) | 2020-02-02 | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
[5 empty] | Road Rehabilitation |  |  | a.) 515,000.00 |  | a.) 03/12/19 |  |  |  | a.) 515,000.00 | [9 empty] | 2
|  | Jct. Highway -Tubod - Bagong Silang | [5 empty] | b.) Clar |  | b.) March 18, 2019 |  |  |  | b.) 515,000.00 | [7 empty] | Completed |  | 2
[12 empty] | g.) June 15, 2019 | [11 empty] | 2
2
|  | Basa - Tubod |  |  | Road Rehabilitation | 1.56 | Admin | a) | 1000000 | a) | 2019-06-19 | e) | - | a) | 1000000 | a) | - | c) | - | a) | - |  |  | 2
076 | [7 empty] | b) | Piad | b) | Nov. 11, 2019 | f) | - | b) | 1000000 | b) | - | d) | - | b) | - | On-going |  | 2
[8 empty] | c) | - | c) | 2020-03-09 | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | Tubod - Pilar |  |  | Road Rehabilitation | 1.55 | Admin | a) | 16000000 | a) | 06/19/19 & 12/9/19 | e) | - | a) | 16000000 | a) | - | c) | - | a) | - | On-going |  | 2
077 | [7 empty] | b) | Gamad/Clar | b) | Dec. 18, 2019 | f) | - | b) | 16000000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | Nov. 5, 2020 | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
[5 empty] | Road Rehabilitation |  |  | a.) 390,000.00 |  | a.) 03/12/19 |  |  |  | a.) 390,000.00 | [9 empty] | 2 | 4
|  | Cebulano- Luceta | [5 empty] | b.) Clar |  | b.) March 8, 2019 |  |  |  | b.) 390,000.00 | [7 empty] | Completed |  | 2 | 4
[12 empty] | g.) June 15, 2019 | [11 empty] | 2 | 4
[24 empty] | 2 | 4
[5 empty] | Road Rehabilitation |  |  | a.) 295,000.00 |  | a.) 03/12/19 |  |  |  | a.) 295,000.00 | [9 empty] | 2 | 4
|  | Lower Asuncion - Upper Asuncion | [5 empty] | b.) Clar |  | b.) March 18, 2019 |  |  |  | b.) 295,000.00 | [7 empty] | Completed |  | 2 | 4
[12 empty] | g.) June 15, 2019 | [11 empty] | 2 | 4
[24 empty] | 2 | 4
[5 empty] | Road Rehabilitation |  |  | a.) 1,220,000.00 |  | a.) 03/12/19 |  |  |  | a.) 1,220,000.00 | [9 empty] | 2
|  | Jct. Highway - Sto. Nino - La Paz - San Vicente | [5 empty] | b.)Obar |  | b.) March 18, 2019 |  |  |  | b.) 1,220,000.00 | [7 empty] | Completed |  | 2
[12 empty] | g.) Sept. 30, 2019 | [11 empty] | 2
2
|  | Alejal - Alemag |  |  | Road Rehabilitation | 1.79 |  | a) | 970000 | a) | 2019-03-18 | e) | - | a) | 970000 | a) | 100% | c) | 100% | a) | 7 | Completed. Financially completed |  | 2
092 | [7 empty] | b) | Gamad/Clar | b) | 2019-05-20 | f) | - | b) | 970000 | b) | 100 | d) | 0% | b) | 20 |  |  | 2
[8 empty] | c) | - | c) | 2019-09-12 | g) | Sept. 30, 2019 | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
[5 empty] | Road Rehabilitation |  |  | a.) 640,000.00 |  | a.) 03/12/19 |  |  |  | a.) 640,000.00 | [9 empty] | 2
|  | Mabaus - Cabay -angan | [5 empty] | b.)Clar |  | b.) Maech 18, 2019 |  |  |  | a.) 640,000.00 | [7 empty] | Completed |  | 2
[12 empty] | g.) July 30, 2019 | [11 empty] | 2
2
[5 empty] | Road Rehabilitation |  |  | a.) 280,000.00 |  | a.) 03/12/19 |  |  |  | a.) 280,000.00 | [9 empty] | 2
|  | Mabaus - Salvacion | [5 empty] | b.)Clar |  | b.) March 18, 2019 |  |  |  | a.) 280,000.00 | [9 empty] | 2
[12 empty] | g.) June 30, 2019 | [9 empty] | Completed |  | 2
2
|  | Dalisay - Mabuhay |  |  | Road Rehabilitation | 3.25 | Admin | a) | 1000000 | a) | 2019-05-16 | e) | - | a) | 1000000 | a) | 80% | c) | 80% | a) | 10 |  |  | 2
102 | [7 empty] | b) | Gamad/Clar | b) | 2019-06-17 | f) |  | b) | 1000000 | b) |  | d) | 0% | b) | 20 | On-going |  | 2
[8 empty] | c) | - | c) | 2/29,2019 | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | Sitio Malaga - Tibulao |  |  | Road Rehabilitation | 3.22 | Admin | a) | 1000000 | a) | 2019-06-25 | e) | - | a) | 1000000 | a) | - | c) | - | a) | - |  |  | 2
103 | [7 empty] | b) | Gamad/Clar | b) | Nov. 11, 2019 | f) | - | b) | 1000000 | b) | - | d) | - | b) | - | On-going |  | 2
[8 empty] | c) | - | c) | Feb. 9, 2020 | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | Dujali - Tanglaw |  |  | Road Rehabilitation | 3.6 | Admin | a) | 2075000 | a) | 2019-10-03 | e) | - | a) | 2075000 | a) | - | c) | - | a) | - |  |  | 2
104 | [7 empty] | b) | Balbastro | b) | Dec. 28, 2019 | f) | - | b) | 2075000 | b) | - | d) | - | b) | - | On-going |  | 2
[8 empty] | c) | - | c) | Apr. 16, 2020 | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | Dujali - New Casay |  |  |  | 3.2 | Admin | a) | 640000 | a) | 2019-05-16 | e) | - | a) | 640000 | a) | 100% | c) | 100% | a) | 10 |  |  | 2 | 4
106 | [7 empty] | b) | Gamad/Clar | b) | 2019-06-17 | f) | 40 | b) | 640000 | b) |  | d) | - | b) | 40 | Completed |  | 2 | 4
[8 empty] | c) | - | c) |  | g) | 10/15/2019 | c) | - | [8 empty] | 2 | 4
[8 empty] | d) | - | d) | - | [12 empty] | 2 | 4
[5 empty] | Road Rehabilitation |  |  | a.) 450,000.00 |  | a.) 03/12/19 |  |  |  | a.) 450,000.00 | [9 empty] | 2
|  | New Casay - Bugtong Talisay | [5 empty] | b.)Clar |  | b.) March 18, 2019 |  |  |  | a.) 450,000.00 | [7 empty] | Completed |  | 2
[12 empty] | g.)June 30, 2019 | [11 empty] | 2
2
|  | Cabay-angan - Esperanza |  |  | Road Rehabilitation | 5.37 | Admin | a) | 1300000 | a) | 2019-05-16 | e) | - | a) | 1300000 | a) | 80% | c) | 80% | a) | 9 |  |  | 2
110 | [7 empty] | b) | Gamad/Clar | b) | 2019-06-17 | f) | - | b) | 1300000 | b) | - | d) | - | b) | 36 | On- going |  | 2
[8 empty] | c) | PEO | c) | Feb. 29, 2020 | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | [13 empty] | 2
[5 empty] | Road Rehabilitation |  |  | a.)220,000.00 |  | a.) 03/12/19 |  |  |  | a.)220,000.00 |  | a.) 100 % |  | c.)100% | [5 empty] | 2
|  | Purok 6 Cabay-angan - Esti | [5 empty] | b.) Gamad |  | b.) March 18, 2019 |  |  |  | a.)220,000.00 | [7 empty] | Completed |  | 2
[12 empty] | g.) June 30, 2019 | [11 empty] | 2
2
[5 empty] | Road Rehabilitation |  |  | a.)250,000.00 |  | a.) March 12, 2019 | [5 empty] | a.) 100 % |  | c.)100% | [5 empty] | 2
|  | Dujali - Sitio Pawas | [5 empty] | b.) Gamad |  | b.) March 18, 2019 | [11 empty] | Completed |  | 2
[12 empty] | g.) Jun 30, 2019 | [11 empty] | 2
2
[5 empty] | Road Rehabilitation |  |  | a.) 280,000.00 |  | a.) March 12, 2019 | [5 empty] | a.) 100 % |  | c.)100% | [5 empty] | 2
|  | Purok 1 to Purok 2 Sitio Pawas | [6 empty] | b.) Gamad | b.) March 18, 2019 | [11 empty] | Completed |  | 2
[12 empty] | g.) Jun 30, 2019 | [11 empty] | 2
2
|  | San Miguel - Crossing Kinamayan |  |  | Road Rehabilitation | 2.8 | Admin | a) | 560000 | a) | 2019-06-25 | e) | - | a) | 560000 | a.) 100 % |  | c.)100% |  | a) | - |  |  | 2 | 4
120 | [7 empty] | b) | Nasol | b) | Sept. 19, 2019 | f) | - | b) | 560000 | b) | - | d) | - | b) | - | Completed |  | 2 | 4
[8 empty] | c) | - | c) | - | g) | Nov. 30, 2019 | c) | - | [8 empty] | 2 | 4
[8 empty] | d) | - | d) | - | [12 empty] | 2 | 4
|  | San Miguel -Libertad Provincial Road |  |  | Road Rehabilitation | 6.2 | Admin | a) | 1240000 | a) | 2019-05-29 | e) | - | a) | 1240000 | a) | 59.41% | c) | 59.41% | a) | 9 |  |  | 2
121 | [7 empty] | b) | Gamad | b) | 2019-06-17 | f) |  | b) | 1240000 | b) | - | d) | - | b) | 36 | On-going |  | 2
[8 empty] | c) | - | c) | Feb. 29, 2020 | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | Bacali - Casig-ang - Libertad |  |  | Road Rehabilitation | 4.7 | Admin | a) | 940000 | a) | 2019-06-07 | e) | - | a) | 940000 | a) | 80% | c) | 80% | a) | 9 | On-going |  | 2
123 | [7 empty] | b) | Gamad | b) | 2019-06-27 | f) | 35 | b) | 940000 | b) | - | d) | - | b) | 36 |  |  | 2
[8 empty] | c) | Admin | c) | Feb. 29, 2020 | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | Kinamayan - Moslog - Mahayag |  |  | Road Rehabilitation | 3.23 | Admin | a) | 1000000 | a) | 2019-05-20 | e) | - | a) | 1000000 | a) | 80% | c) | 80% | a) | 10 | On going |  | 2
124 | [7 empty] | b) | Gamad | b) | 2019-06-27 | f) | 29 | b) | 1000000 | b) | - | d) | - | b) | 20 |  |  | 2
[8 empty] | c) | PEO | c) | Feb. 29, 2020 | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | San Miguel - Moslog - Kinamayan |  |  | Road Rehabilitation | 2.9 | Admin | a) | 1000000 | a) | 2019-05-20 | e) | - | a) | 1000000 | a) | 80% | c) | 80% | a) | 6 | On-going |  | 2
125 | [7 empty] | b) | Gamad | b) | 2019-06-27 | f) | 29 | b) | 1000000 | b) | - | d) | - | b) | 24 |  |  | 2
[8 empty] | c) | - | c) | Feb. 29, 2020 | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | Kinamayan - Lunga-og |  |  | Road Rehabilitation | 2.59 | Admin | a) | 520000 | a) | 2019-03-18 | e) | - | a) | 520000 | a) | 100% | c) | 100% | a) | 9 | Completed |  | 2
126 | [7 empty] | b) | Gamad/Clar | b) | 5/202/019 | f) | - | b) | 520000 | b) | - | d) | - | b) | 36 |  |  | 2
[8 empty] | c) | - | c) |  | g) | Sept. 30, 2019 | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | Mugas - Lanatad |  |  | Road Rehabilitation | 1.53 | Admin | a) | 500000 | a) |  | e) | - | a) | 500000 | a) | - | c) | - | a) | - | On-going |  | 2
131 | [7 empty] | b) | Balbastro | b) | 8/5/2019 | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | Feb. 20, 2020 | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | New Katipunan - Pantaron |  |  | Road Rehabilitation | 1.96 | Admin | a) | 395000 | a) | 2019-03-12 | e) | - | a) | 395000 | a) | - | c) | - | a) | - |  |  | 2
134 | [7 empty] | b) | Gamad/Clar | b) | Dec. 27, 2019 | f) | - | b) | 395000 | b) | - | d) | - | b) | - | On-going |  | 2
[8 empty] | c) | - | c) | Feb. 25, 2020 | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | Fd. Rd. 2 - Sto. Tomas - Magwawa |  |  | Road Rehabilitation | 10.21 | Admin | a) | 3575000 | a) | June `19, 2019 | e) | - | a) | 3575000 | a) | 40% | c) | 40% | a) | - |  |  | 2
137 | [7 empty] | b) | Gamad/Clar | b) | Aug. 27, 2019 | f) | - | b) | 3575000 | b) | - | d) | - | b) | - | On-going |  | 2
[8 empty] | c) | - | c) | 2020-01-24 | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
[8 empty] | a.) 540,000.00 |  | a.) March 12, 2019 |  |  |  | a.) 540,000.00 |  | a.)100% |  | c.)100% |  |  |  | Completed |  | 2
|  | Nafco - Bobongon |  |  | Road Rehabilitation |  |  | b. Gamad |  | b.) march 18, 2019 |  |  |  | b.) 540,000.00 | [9 empty] | 2
[12 empty] | g.) June 30, 2019 | [11 empty] | 2
2
2
|  | Jct. Highway - Tanglaw |  |  | Road Rehabilitation | 3.98 | Admin | a) | 1100000 | a) | 2019-05-16 | e) | - | a) | 1100000 | a) | 85% | c) | 85% | a) | 10 | On going |  | 2
142 | [7 empty] | b) | Gamad/Clar | b) | 2019-06-17 | f) | 29 | b) | 1100000 | b) | - | d) | - | b) | 20 |  |  | 2
[8 empty] | c) | PEO | c) | Feb. 29, 2020 | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | Kimamon - Lunga-og - Talomo |  |  | Road Rehabilitation | 5.99 | Admin | a) | 1800000 | a) | 5/202019 | e) | - | a) | 1800000 | a) | 73.31% | c) | 73.31% | a) | 9 | on -going |  | 2
144 | [7 empty] | b) | Gamad | b) | 2019-06-17 | f) | - | b) | 1800000 | b) | - | d) | - | b) | 6 |  |  | 2
[8 empty] | c) | PEO | c) | Feb. 27, 2020 | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | Bdry. Tagum - Crossing Kinamayan Sto. Tomas |  |  | Road Rehabilitation | 0.75 | Admin | a) | 3700000 | a) | Dec. 6, 2019 | e) | - | a) | 3700000 | a) | - | c) | - | a) | - | On-going |  | 2
146 | [7 empty] | b) | Gamad/Clar | b) | Dec. 27, 2019 | f) | - | b) | 3700000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | 2020-04-25 | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | Prk. Narafil - Prk. Daisy Magupising |  |  | Road Rehabilitation | 19.16 | Admin | a) | 300117 | a) | 2019-06-25 | e) | - | a) | 300117 | a) | 100% | c) | 100% | a) | - | Completed |  | 2 | 4
148 | [7 empty] | b) | Gamad/Clar | b) | Sept. 16, 2019 | f) | - | b) | 300117 | b) | - | d) | - | b) | - |  |  | 2 | 4
[8 empty] | c) | - | c) | - | g) | Oct. 18, 2019 | c) | - | [8 empty] | 2 | 4
[8 empty] | d) | - | d) | - | [12 empty] | 2 | 4
2. Various of Local Roads & Drainage Development Project (Provincewide) |  |  |  |  | Road Drainage rehabiliated |  | Admin | a) | 15000000 | [12 empty] | See projects listed below |  | 2
[8 empty] | b) | Paraguya | [14 empty] | AC
[8 empty] | c) | PEO | [14 empty] | AC
[8 empty] | d) | - | [14 empty] | AC
At District 1
|  | Rehab./Impv't. of San Juan-New Talisay Provincial Road with Drainage |  |  | Road Drainage rehabiliated | - | Admin | a) | 1000000 | a) | Feb. 10, 2019 | e) | - | a) | 1000000 | a) | - | c) | 60$ | a) | - | On-going. |  | AC
2.1 | [7 empty] | b) | MJ | b) | - | f) | - | b) | 1000000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | PEO | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| 6 | Repair/Rehab. Of Concrete Road Jct. Suaon-Libuton, Kapalong |  |  | Road Drainage rehabiliated | - | Admin | a) | 1000000 | a) | 2019-07-03 | e) | - | a) | 1000000 | a) | - | c) | - | a) | - | For implementation Waiting for the availability of the backhoe |  | 1
2.2 | [7 empty] | b) | Aparece | b) | - | f) | - | b) | 1000000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| 1 | Impv't. of Cross Drainage along Saug-Sonlon-Bdry. Longanapan |  |  | Road Drainage rehabiliated | - | Admin | a) | 3000000 | a) | Feb. 10, 2019 | e) | - | a) | 3000000 | a) | - | c) | 58% | a) | - | Suspended from Nov. 18, 2019 to Jan 5, 2020.Resume jan. 6, 2020 |  | 1
2.3 | [7 empty] | b) | Bataller | b.) Aug. 1, 2019 | Aug. 1, 2019 | f) | - | b) | 3000000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| 8 | Rehab./Impv't. of Sto. Niño-Palma Gil-Sitio Opao Provincial Road with Drainage |  |  | Road Drainage rehabiliated | - | Admin | a) | 3000000 | a) | 2019-05-29 | e) | - | a) | 3000000 | a) | - | c) | - | a) | - | NTP not yet serve to Tagum Builders because they have not yet complied with the construction safety requirement |  | 1
2.4 | [7 empty] | b) | Lumapat | b) | - | f) | - | b) | 3000000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
|  | Rehab. of Anibongan-Salvacion-Cabay-angan Provincial Road with Drainage |  |  | Road Drainage rehabiliated | - | - | a) | 2000000 | a) | 2019-01-14 | e) | - | a) | 2000000 | a) | 100% | c) | 100% | a) | 1 | Completed |  | 1 | 4
2.1 | [7 empty] | b) | Toquero | b) | 2019-05-22 | f) | - | b) | 2000000 | b) | - | d) | - | b) | 4 | Fiancial obligation still on process |  | 2 | 4
[8 empty] | c) | PEO | c) | 2019-08-04 | g) | Dec. 31, 2019 | c) | - | [8 empty] | 2 | 4
[8 empty] | d) | - | d) | - | [12 empty] | 2 | 4
|  | Rehab. Of Dujali-Pawas-San Vicente Provincial Road |  |  | Road Drainage rehabiliated | - | - | a) | 1102900 | a) | Aug. 5, 2019 | e) | - | a) | 1102900 | a) | - | c) | - | a) | - | Project title was amended in the 2nd AIP revision deleting drainage. The project amount was reduced from P2,000,000.00 to P1,102,900.00 to fund new projects that was inlcuded in the AIP 3rd revision CY 2019 /SB No. 4 CY 2019 On. going |  | 2
2.2 | [7 empty] | b) | Toquero | b) | - | f) | - | b) | 1102900 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | PEO | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | Rehab./Impv't. of Jct. highway Ising-Magsaysay Provincial Road with Drainage |  |  | Road Drainage rehabiliated | - | - | a) | 1500000 | a) | Jan. 16, 2019 | e) | - | a) | 1500000 | a) | - | c) | - | a) | - | Revised POW for approval - Jan. 7, 2020 Revision was made due to scarcity of boulders changing from stone masonry to concrete masonry |  | 2
2.3 | [7 empty] | b) | Toquero | b) | - | f) | - | b) | 1500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | PEO | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | Rehab./Impv't. of Sto. Tomas-Bdry. Mamacao Provincial Road |  |  | Road Drainage rehabiliated | - | - | a) | 1500000 | a) | 2019-01-14 | e) | - | a) | 1500000 | a) | 100% | c) | 100% | a) | - | Completed Financial obligation on process |  |  | 4
2.4 | [7 empty] | b) | Toquero | b) | 2019-05-31 | f) | 60 | b) | 1500000 | b) | - | d) | - | b) | - |  |  | 2 | 4
[8 empty] | c) | PEO | c) | 2019-07-15 | g) | Dec. 31, 2019 | c) | - | [8 empty] | 2 | 4
[8 empty] | d) | - | d) | - | [12 empty] | 2 | 4
| SUPPLEMENTAL BUDGET NO. 4 CY 2019 | [22 empty] | AC
AC
[10 empty] | a.) Nov. 27, 2019 | [13 empty] | 2
| 2.5 | Rehab of Local Roads at Dalisay - Manay Road Section, | [19 empty] | Completed |  | 2
|  | Panabo City | [19 empty] | Financial obligation on process |  | 2
2
| 2.6 | Rehab. of Local Roads at Sta. Cruz- jct. Tagpore- Buenavista | [7 empty] | a.) Nov. 27, 2019 | [11 empty] | Completed |  | 2
|  | Road Section, panabo City | [19 empty] | Financial obligation on process |  | 2
2
| 2.7 | Rehab. of Local Roads at Taba - Bucana Road Section | [7 empty] | a.) | Nov. 27, 2019 | [10 empty] | Financial obligation on process |  | 2
2
2
3. Various Water System Development Project (Provincewide) |  |  |  |  | Water System projects | - | Admin | a) | 9750000 | [12 empty] | See projects listed below |  | 2
[8 empty] | b) | Medalla/Imboy | [14 empty] | AC
[8 empty] | c) | PEO | [14 empty] | AC
[8 empty] | d) | - | [14 empty] | AC
3.1 |  | Construction of Water System Projects | [21 empty] | AC
AC
| 6 | Construction of PWS, Bgry. Linao, San Isidro |  |  | Water System Projects | - | Admin | a) | 500000 | a) | 06/19/19 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For implementation |  | AC
3.1.1 | [7 empty] | b) | Aclaracion | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| 6 | Construction of PWS, Brgy. Datu Balong, San Isidro |  |  | Water System Projects | - | Admin | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For declaration of savings because the spring water source is not feasible for development |  | 1
3.1.2 | [7 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| 6 | Construction of PWS, Brgy. Sagayen, San Isidro |  |  | Water System Projects | - | Admin | a) | 500000 | a) | 2019-09-10 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Procurement on process |  | 1
3.1.3 | [7 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| 4 | Construction of PWS, Brgy. Purok 7-A and B, Brgy. Capungagan, kapalong |  |  | Water System Projects | - | Admin | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | The project was funded by OPAPP CY 2018. Fund re-aligned to new project Rehab. of Water System in PEEDO- LPRRC, Pob. New Corella (AIP 2nd revision CY 2019 |  | 1
3.1.4 | [7 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| 4 | Construction of PWS Purok 2, Brgy. Pag-Asa, kapalong |  |  | Water System Projects | - | Admin | a) | 800000 | a) | - | e) | - | a) | 800000 | a) | - | c) | - | a) | - | The project was funded by OPAPP CY 2018. Fund re-aligned and added to Construction of PWS in Brgy. Linosutan, kaputian Dist, IGACOS (AIP 2nd revision CY 2019) |  | 1
3.1.5 | [7 empty] | b) | - | b) | - | f) | - | b) | 800000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| 11 | Installation of Shallow Tube Wells & Const. of Machinery Shed |  |  | Water System Projects | - | Admin | a) | 1600000 | a) | - | e) | - | a) | 1600000 | a) | - | c) | - | a) | - | POW for review |  | 1
3.1.6 | [7 empty] | b) | - | b) | - | f) | - | b) | 1600000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
|  | Impv't. of Potable Water System, Consolacion, Panabo City |  |  | Water System Projects | - | - | a) | 500000 | a) | 2019-06-28 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Sched of bidding Dec 27, 2019 |  | 1
3.1.7 | [7 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | Impv't. of Potable Water System, Tagbitan-ag, Samal Dist. |  |  | Water System Projects | - | - | a) | 500000 | a) | 2019-06-19 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For implementation |  | 2
3.1.8 | [7 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | Impv't. of Potable Water System, San Antonio, babak, IGCS |  |  | Water System Projects | - | - | a) | 500000 | a) | 2019-06-25 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For implementation |  | 2
3.1.9 | [7 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | Impv't. of Potable Water System, Mambago-A, IGCS |  |  | Water System Projects | - | - | a) | 500000 | a) | Sept. 10, 2019 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | (Amended in the AIP 2nd Revision to change the location from Peñaplata to Samal District) For implementation |  | 2
3.1.10 | [7 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | Construction of PWS, Brgy. Buenavista, Panabo City |  |  | Water System Projects | - | - | a) | 500000 | a) | June 19 ,2019 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For implementation |  | 2
3.1.11 | [7 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | Construction of PWS, Brgy. Brgy. Kiotoy, Panabo City |  |  | Water System Projects | - | Contract | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Waiting for geo-resistivity equipment since the activity is drilling works |  | 2
3.1.12 | [7 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | Construction of PWS, Brgy. Linusotan, Talikud, District, IGCS |  |  | Water System Projects | - | - | a) | 500,000 + 800,000.00 | a) | Oct. 23, 2019 | e) | - | a) | 500,000 + 800,000.00 | a) | - | c) | - | a) | - | (Additional 800,000.00 from Const. of PWS in purok 2, Pag-asa, Kapalong which was funded by OPAPP CY 2018) (amended Sched of bidding Dec 27, 2019 |  | 2
3.1.13 | [7 empty] | b) | - | b) | - | f) | - | b) | 500,000 + 800,000.00 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | Rehab. of PWS, Brgy. San Miguel, Babak, IGCS |  |  | Water System Projects | - |  | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For amendment indicating phase 2 since the project title is the same with stimulus project and same amount. |  | 2
3.1.14 | [7 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | Construction of PWS, Brgy. Cacao, Panabo City |  |  | Water System Projects | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For cancellation. Purchase of Geo-resistivity equipment but procurement still on process |  | 2
3.1.15 | [7 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | Rehabilitation of Potable Water System, Brgy. Pangubatan, kaputian Dist. IGCS |  |  | Water System Projects | - |  | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For allotment June 24, 2019 |  | 2
3.1.16 | [7 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | Conduct of Geo-resistivity/drilling Test of Proposed Site |  |  | Geo-resistivity/drilling test conducted | - | - | a) | 250000 | [12 empty] | See projects listed below |  | 2
3.1 | [7 empty] | b) | - | [14 empty] | AC
[8 empty] | c) | - | [14 empty] | AC
[8 empty] | d) | - | [14 empty] | AC
|  | Construction of PWS, Brgy. Kiotoy, Panabo City |  |  | Geo-resistivity/drilling test conducted | - | - | a) | 62500 | a) | - | e) | - | a) | 62500 | a) | - | c) | - | a) | - | For cancellation due to the purchase of geo-resistivity equipment |  | AC
a. | [7 empty] | b) | - | b) | - | f) | - | b) | 62500 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | Construction of PWS, Brgy. Linosutan, Talikud, IGCS |  |  | Geo-resistivity/drilling test conducted | - | - | a) | 62500 | a) | - | e) | - | a) | 62500 | a) | - | c) | - | a) | - |  |  | 2
b. | [7 empty] | b) | - | b) | - | f) | - | b) | 62500 | b) | - | d) | - | b) | - | For cancellation due to the purchase of geo-resistivity equipment |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | Construction of PWS, Brgy. San Miguel, Samal, IGCS |  |  | Geo-resistivity/drilling test conducted | - | - | a) | 62500 | a) | - | e) | - | a) | 62500 | a) | - | c) | - | a) | - | For cancellation due to the purchase of geo-resistivity equipment |  | 2
c. | [7 empty] | b) | - | b) | - | f) | - | b) | 62500 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | Construction of PWS, Cacao, Panabo City |  |  | Geo-resistivity/drilling test conducted | - | - | a) | 62500 | a) | - | e) | - | a) | 62500 | a) | - | c) | - | a) | - |  |  | 2
d. | [7 empty] | b) | - | b) | - | f) | - | b) | 62500 | b) | - | d) | - | b) | - | For cancellation due to the purchase of geo-resistivity equipment |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
4. Various Government Buildings and Facilities Development Project (Provincewide) |  |  |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of recipients | - | Admin | a) | 27000000 | [12 empty] | See projects listed below |  | 2
[8 empty] | b) | Medalla | [14 empty] | AC
[8 empty] | c) | PEO | [14 empty] | AC
[8 empty] | d) | - | [14 empty] | AC
|  | Repair Bay of Disaster Quick Response Equipment @ PEO Compound, Gov't. Center, Mankilam, Tagum City |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of recipients | - | Admin | a) | 1000000 | a) | 2019-01-31 | e) | - | a) | 1000000 | a) | - | c) | 46.28% | a) | - | On-going |  | AC
| 11 | [6 empty] | b) | Azotes | b) | Oct. 16, 2019 | f) | - | b) | 1000000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
|  | Repair/Impv't. of Municipal Triball Hall, New Corella |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of recipients | - | Admin | a) | 1500000 | a) | - | e) | - | a) | 1500000 | a) | - | c) | - | a) | - | For allotment June 24, 2019 |  | 1
| 5 | [6 empty] | b) | - | b) | - | f) | - | b) | 1500000 | b) | - | d) | - | b) | - | PO on process |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
|  | Const. of GYM Bleacher at Suaybaguio Rina, Elem. School |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of recipients | - | Admin | a) | 1000000 | a) | - | e) | - | a) | 1000000 | a) | 100% | c) | 100% | a) | - | Completed |  | 1
| 11 | [6 empty] | b) | Mayang | b) | 6/3/2019 | f) | - | b) | 1000000 | b) | 64 | d) | 0% | b) | - |  |  | 1
[8 empty] | c) | PEO | c) | 8/01/2019 | g) |  | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
|  | Repair of Dacudao Health Center, Dacudao, San Isidro |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of recipients | - | Admin | a) | 1000000 | a) | - | e) | - | a) | 1000000 | a) |  | c) | 93.13% | a) | 5 | On going |  | 1
| 6 | [6 empty] | b) | Aclaracion | b) | - | f) | - | b) | 1000000 | b) | - | d) |  | b) | 110 |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
|  | Const. of Perimeter Fence at Sto. Niño NASECO Integrated School with Tugas Ext., Sto. Niño, Talaingod |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of recipients | - | Admin | a) | 1000000 | a) | - | e) | - | a) | 1000000 | a) | - | c) | - | a) | - | For implementation |  | 1
| 8 | [6 empty] | b) | - | b) | - | f) | - | b) | 1000000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
|  | Const. of Multi-Purpose Hall Center (Cultural Heritage in Ancestral Domain of Ata-Manobo) |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of recipients | - | Admin | a) | 3000000 | a) | - | e) | - | a) | 3000000 | a) | - | c) | - | a) | - | Fund re-aligned to GIDAS projects |  | 1
| 8 | [6 empty] | b) | - | b) | - | f) | - | b) | 3000000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | PEO | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
|  | Const. of IP Women's Multi-{Purpose Bldg.), Cabidiangan, Sto. Niño, Talaingod |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of recipients | - | Admin | a) | 2000000 | a) | 2019-05-15 | e) | - | a) | 2000000 | a) | - | c) | - | a) | - | For re-bidding |  | 1
| 8 | [6 empty] | b) | - | b) | - | f) | - | b) | 2000000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
|  | Extension of PAGRO Training Center & Ground Dev't., Gov't. Center, Mankilam, Tagum City |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of recipients | - | Admin | a) | 1000000 | a) | - | e) | - | a) | 1000000 | a) | - | c) | - | a) | - | For allotment- June 24,2019 Abstract on process
| 11 | [6 empty] | b) | - | b) | - | f) | - | b) | 1000000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | PEO | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
|  | Construction of Abilidad Training Center, Gov't. Center, Mankilam, Tagum City |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of recipients | - | Admin | a) | 7000000 | a) | - | e) | - | a) | 7000000 | a) | - | c) | - | a) | - | Fund re-aligned to GIDAS projects |  | 1
| 11 | [6 empty] | b) | - | b) |  | f) | - | b) | 7000000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
|  | Const. of 1 CL Bldg. @ Suawon ES, New Corella |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of recipients | - | Admin | a) | 1000000 | a) | - | e) | - | a) | 1000000 | a) | - | c) | - | a) | - | On-going |  | 1
[8 empty] | b) | - | b) | Nov. 19, 2019 | f) | - | b) | 1000000 | b) |  | d) | - | b) | - |  |  | 1
| 5 | [6 empty] | c) | PEO | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
|  | Const. of Municipal Tribal Hall, San Isidro |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of recipients | - | Admin | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For implementation |  | 1
| 6 | [6 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
|  | Const. of Quail House (PDNSC Ext. Campus), Sto. Niño, Talaingod |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of recipients | - | Admin | a) | 750000 | a) | - | e) | - | a) | 750000 | a) | - | c) | - | a) | - | On-going |  | 1
| 8 | [6 empty] | b) | - | b) | - | f) | - | b) | 750000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | PEO | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
|  | Completion of Perimeter Steel Fence @ Lunga-og E/S, Brgy. Lunga-og, Sto. Tomas |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of recipients | - | Admin | a) | 1630000 | a) | 01/17/19 | e) | - | a) | 1630000 | a) | - | c) | 46.28% | a) | - | On-going |  | 1
[8 empty] | b) | Azotes | b) | - | f) | - | b) | 1630000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | PEO | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | Const. of DDN Hospital Carmen Zone Annex Bldg. Phase 2, |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of recipients | - | Contract | a) | 3620000 | a) | 2019-06-28 | e) | - | a) | 3620000 | a) | - | c) | - | a) | - | For implementation |  | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 3620000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | Digos Constrak Corp/ | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
5. Stimulus Projects for Various Barangays a. 20% Development Fund CY 2019 |  |  |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | Admin | a) | 41500000 | [12 empty] | See projects listed below |  | 2
[8 empty] | b) | Medalla | [14 empty] | AC
[8 empty] | c) | PEO | [14 empty] | AC
[8 empty] | d) | - | [14 empty] | AC
AC
5.1 |  | Rehab. Of FMR at Prk. 1,3,4 & 7, Concepcion, Asuncion |  |  | Road Rehabilitation to cater the needs of brgys. | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Re-aligned to Const. of Children's Playground with Amenities at Pob. New Corella (AIP 3rd Revision CY 2019 / SB No. 4 CY 2019 |  | AC
| 1 | [6 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
5.2 |  | Rehab. Of Multi-Purpose Hall, New Bantayan, Asuncion |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | 35% | a) | - | Fund transferred to LGU on - going c /o Engr. Lilibeth Cuajao |  | 1
| 1 | [6 empty] | b) | - | b) | 2019-11-02 | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
1
NEW CORELLA
5.3 |  | Construction of Multi-Purpose Hall, El Salvador, New Corella |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) | 2019-05-23 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Fund transferred to LGU March 23, 2019 c/o Engr. Dugoldugol |  | AC
[8 empty] | b) | - | b) | 2019-09-16 | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
| 5 | [6 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
5.4 |  | Concreting of Drainage Canal , Pob., New Corella |  |  | Const. of Drainage Canal to cater the needs of brgys. | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Amended to Const. of 2 Storey Multi-Purpose Hall phase 3 (Brgy. Hall),Pob., New Corella (AIP 3rd revision CY 2019 / SB No. 4 CY 2019 |  | 1
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
| 5 | [6 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
5.5 |  | Rehab. Of Multi-Purpose Hall, Cabidianan, New Corella |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) | 02/20/19 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Fund transferred to LGU c/o Engr. Dugoldugol |  | 1
[8 empty] | b) |  | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
| 5 | [6 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
5.6 |  | Const. of Canal Lining, Limbaan, New Corella |  |  | Const. of Drainage Canal to cater the needs of brgys. | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Fund transferred to LGU c/o Engr. Dugoldugol Completed - Nov. 8, 2019 / PCR for submission |  | 1
[8 empty] | b) | - | b) | 2019-09-06 | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
| 5 | [6 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
1
TALAINGOD
5.7 |  | Brgy. Electrification (Centro Gupitan), Gupitan, Talaingod |  |  | Rural Electrification to cater the needs of brgys. | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Re-aligned to other stimulus projects that need additional funds to complete since the amount can not complete the project. Recommended for exact fund that can complete the project. |  | AC
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
| 8 | [6 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
TAGUM CITY
5.8 |  | Rehab. of Evacuation Center, Madaum, Tagum City |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | Admin | a) | 500000 | a) | 01/14/19 | e) | - | a) | 500000 | a) | 17.17% | c) | 17.17 | a) | - | On going |  | AC
| 11 | [6 empty] | b) | Juan, Z | b) | Nov. 18, 2019 | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | PEO | c) | Jan. 16, 2019 | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | 60 CD | d) | - | [12 empty] | 1
5.9 |  | Rehab. of Evacuation Center, Magugpo Poblacion, Tagum City |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. |  | Contract | a) | 500000 | a) |  | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Amended in the AIP 3rd revision CY 2019 /SB No. 4 CY 2019 changing the total project cost to P600,000.00 |  | 1
| 11 | [6 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
5.1 |  | Rehab. of Evacuation Center, New Balambam, Tagum City |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. |  | Contract | a) | 500000 | a) | 2019-09-10 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Procurement on process |  | 1
| 11 | [6 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
5.11 |  | Rehab. Of Multi-Purpose Hall, Cuambogan, Tagum City |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. |  | Contract | a) | 500000 | a) | 2019-09-10 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Procurement on process |  | 1
| 11 | [6 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
5.12 |  | Completion of Evacuation Center, Nueva Fuerza, Tagum City |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. |  | Contract | a) | 500000 | a) | 2019-09-10 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Procurement on process |  | 1
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
| 11 | [6 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
5.13 |  | Const. of Water System, San Agustin, Tagum City |  |  | Const. of Water System to cater the needs of brgys. | - | Contract | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Re-aligned to other stimulus projects that need additional funds since there is no deed of donation for the proposed site. |  | 1
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
| 11 | [6 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
5.14 |  | Const. of Brgy. Health Center, Magugpo South, Tagum City |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Amended in the AIP 3rd revision CY 2019 /SB No. 4 CY 2019 changing the total project cost to P1,550,000.00 |  | 1
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
| 11 | [6 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
5.15 |  | Const. of Women Livelihood Center, San Isidro, Tagum City |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) | 2019-05-29 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | On -going |  | 1
[8 empty] | b) | - | b) | Jan. 2, 2020 | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
| 11 | [6 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
5.16 |  | Completion. of Water System , Busaon, Tagum City |  |  | Const. of Water System to cater the needs of brgys. |  | Contract | a) | 500000 | a) | Sept. 10, 2019 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Procurement on process |  | 1
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
| 11 | [6 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
5.17 |  | Rehab. Of Brgy. Health Center, Apokon, Tagum City |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | admin | a) | 500000 | a) | 2019-03-25 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For implementation (The brgy. council agreed not to pursue with the project if it will not be completed and needs additional funds) |  | 1
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
| 11 | [6 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
5.18 |  | Const. of Drainage Canal, Bincungan, Tagum City |  |  | Const. of Drainage Canal to cater the needs of brgys. |  | Contract | a) | 500000 | a) | Sept. 10, 2019 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Procurement on process |  | 1
| 11 | [6 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
5.19 |  | Rehab. of Evacuation Center, Mankilam, Tagum City |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) | 2019-03-25 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For implementation |  | 1
| 11 | [6 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
|  | Rehab. of Evacuation Center, Magugpo North, Tagum City |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. |  | Contract | a) | 500000 | a) | Sept. 10, 2019 | e) | - | a) | 500000 | a) | - | c) | - | a) |  | Procurement on process |  | 1
5.2 | 11 | [6 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
1
SAN ISIDRO
|  | Rehab. Of Multi-Purpose Hall , Sto. Niño, San Isidro |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | Admin | a) | 500000 | a) | 02/20/19 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | POW was revised to increase the cost for windows and approved Dec. 6, 2019 PR on process |  | AC
5.21 | 6 | [6 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
|  | Rehab. Of Water System at Purok Cabang & Mangga , Pinamuno, San Isidro |  |  | Const. of Water System to cater the needs of brgys. |  | Contract | a) | 500000 | a) | Dec. 6, 2019 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Sched. Of bidding Dec. 27, 2019 |  | 1
5.22 | 6 | [6 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
|  | Rehab. Of Water System , Igangon, San Isidro |  |  | Const. of Water System to cater the needs of brgys. | - | - | a) | 500000 | a) | 2019-05-29 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For implementation |  | 1
5.23 | 6 | [6 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
1
CARMEN |  |  |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys.
5.1 |  | Const. of Multi-Purpose Hall, La Paz, Carmen |  |  |  | - | - | a) | 500000 | a) | 02/20/19 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Fund transferred to LGU March 28, 2019 |  | AC
[8 empty] | b) | - | b) | Aug. 16, 2019 | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
5.2 |  | Const. of Evacuation Center Ph. 3, Sto. Niño, Carmen |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Amended in the AIP 3rd revision CY 2019/ SB No. 4 CY 2019 changing the location to Purok !-c, Sto. Nino since the previous location was implemented by DPWH |  | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
5.3 |  | Const. of Multi-Purpose Hall, Mangalcal, Carmen |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) | 02/20/19 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Fund transfer to LGU Carmen, 3/28/2019 with check no. 2574953 and OR no. 0118982 |  | 2
[8 empty] | b) | - | b) | Sept. 16, 2019 | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
5.4 |  | Rehab. of Multi-Purpose Hall, Guadalupe, Carmen |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) | 02/20/19 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Fund transferred to LGU March 28, 2019 |  | 2
[8 empty] | b) | - | b) | 8/15/2019 | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | 11/13/2019 | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
5.5 |  | Const. of Multi-Purpose Hall, Mabuhay, Carmen |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) | 02/20/19 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Fund transfer to LGU Carmen, 3/28/2019 with check no. 2574925 and OR no. 0118984 |  | 2
[8 empty] | b) | - | b) | Aug. 16, 2019 | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
5.6 |  | Const. Canal Lining , Mabaus, Carmen |  |  | Const. of Canal Lining to cater the needs of brgys. | - | - | a) | 500000 | a) | 02/20/19 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Fund transferred to LGU March 28, 2019 |  | 2
[8 empty] | b) | - | b) |  | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) |  | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
5.7 |  | Rehab. Of Evacuation Center, Alejal, Carmen |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) | 02/20/19 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Fund transfer to LGU Carmen, 3/28/2019 with check no.2574949 and OR no. 0118991 |  | 2
[8 empty] | b) | - | b) | Aug. 16, 2019 | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
5.8 |  | Compl. Of Evacuation Center, Tuganay, Carmen |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) | 02/20/19 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Fund transfer to LGU Carmen, 3/28/2019 with check no. 2574947 and OR no. 0118995 |  | 2
[8 empty] | b) | - | b) | Aug. 16, 2019 | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
5.9 |  | Const. of Multi-Purpose hall, Ising, Carmen |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) | 02/20/19 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Fund transferred to LGU March 28, 2019 |  | 2
[8 empty] | b) | - | b) |  | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
5.1 |  | Rehab. of Multi-Purpose hall, Cebulano, Carmen |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) | 02/20/19 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Fund transferred to LGU March 28, 2019 |  | 2
[8 empty] | b) | - | b) | Aug. 16, 2019 | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
2
PANABO CITY
5.11 |  | Rehab. Of Multi-Purpose Hall, Kasilak, Panabo City |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Amended in AIP 3rd revison CY 2019/ SB No. 4 CY 2019 increasing the project cost to P650,000.00 |  | AC
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
5.12 |  | Rehab. Of Multi-Purpose Hall, New Malitbog, Panabo City |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Amended in AIP 3rd revsion CY 2019 to change the project to Construction of Potable Water System because the original project will be funded by LGU, Panabo City (Brgy. resolution no. 25 series of 2019 dated Aug. 13, 2019 submitted) |  | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
2
[8 empty] | d) | - | d) | -
5.13 |  | Desilting of Canal, New Pandan, Panabo City |  |  | Const. of Drianage Canal to cater the needs of brgys. | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For re inspection to add length for desilting c/o Engr. Canillada Plan prepared can not consume the allocated amount of P500,000.00 for desilting works. |  | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
5.14 |  | Const. Of Multi-Purpose Hall, Waterfall, Panabo City |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For allotment. Sept. 27, 2019 |  | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
5.15 |  | Concreting of Brgy. Road @ Prk. Guyabano, Cagangohan, Panabo City |  |  | Road Concreting to cater the needs of brgys. | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Amended in AIP 3rd revision to change the project to Rehab of Evacuation Center because the original project has no deed of donation.(Brgy. resolution no 41 series of 2019 dated Aug. 16, 2019 submitted |  | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
2
[8 empty] | d) | - | d) | -
5.16 |  | Rehab. Of Evacuation Center, J.P. Laurel, Panabo City |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) | Oct. 23, 2019 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Sched. Of bidding Dec. 27, 2019 |  | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
5.17 |  | Const. Of Multi-Purpose Hall, Buenavista, Panabo City |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) | Oct. 18, 2019 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Sched. Of bidding Dec. 27, 2019 |  | 2
[8 empty] | b) | - | b) | - | f) |  | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
5.18 |  | Rehab. Of Multi-Purpose Hall, San Francisco, Panabo City |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) | Oct. 18, 2019 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Sched. Of bidding Dec. 27, 2019 |  | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) |  | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
-
5.19 |  | Rehab. Of Evacuation Center, Datu Abdul Dadia, Panabo City |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) | Oct. 18, 2019 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Sched. Of bidding Dec. 27, 2019 |  | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
5.2 |  | Impv't./Beautification of Brgy. Grounds, Quezon, Panabo City |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Re aligned to other stimulus projects that needs additional funding |  | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
5.21 |  | Const. of Women Livelihood Center Bldg. , Gredu, Panabo City |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) | 2019-03-28 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Fund transfer to LGU - 3/28/2019 with check no. 2574926 and OR no. 0166517 - March 28, 2019 |  | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
5.23 |  | Const. of Canal Lining at Purok 5, Salvacion, Panabo City |  |  | Const. of Drainage Canal to cater the needs of brgys. | - | - | a) | 500000 | a) | Oct. 18, 2019 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Procurement on process |  | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
5.24 |  | Rehab. Of Health Center, New Visayas, Panabo City |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Re aligned to other stimulus projects that needs additional funding |  | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
5.25 |  | Rehab. Of Multi-Purpose Hall, Little Panay, Panabo City |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For allotment Dec. 11, 2019 |  | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
5.26 |  | Rehab. Of Brgy. Health Center, Dalisay, Panabo City |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For allotment Dec. 4, 2019 |  | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
5.27 |  | Const. of Multi-Purpose Hall, Southern Davao, Panabo City |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For allotment Dec. 3, 2019 |  | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) |  | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
2
-
STO. TOMAS
5.28 |  | Rehab. Of Evacuation Center, Casig-ang, Sto. Tomas |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | POW preparation on-going c/o Engr. Uy |  | AC
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
5.29 |  | Const. of Brgy. Tibal-og Health Center, Tibal-og, Sto. Tomas |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | POW preparation completed amounting t oP1,550,000.00. To request for additional funds in order to complete the project to be functional |  | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - |  | Nov. 30, 2019 | [10 empty] | 2
5.3 |  | Compl.of Brgy. Public Market, La Libertad, Sto. Tomas |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) |  | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Fund transfer to LGU - 6/26/219 with check no. 2575131 and OR no. 0557457 Completed/ PCR for submission by LGU |  | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
5.31 |  | Rehab. Of Evacuation Center, New Visayas, Sto. Tomas |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) |  | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Fund transfer to LGU - 6/26/219 with check no. 2575132 and OR no. 0557455 For implementation |  | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
5.32 |  | Rehab. Of Multi-Purpose Hall, San Vicente, Sto. Tomas |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Fund transferred to LGU July 5, 2019 On -going |  | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) |  | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - |  | - | [10 empty] | 2
5.33 |  | Rehab. Of Multi-Purpose Hall, Salvacion, Sto. Tomas |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Amended in AIP 3rd revision CY 2019 /SB No. 4 CY 2019increasing the project cost to P1,000,000.00 |  | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
5.34 |  | Rehab. Of Multi-Purpose Hall, Pantaron, Sto. Tomas |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) |  | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Amended in AIP 3rd revision CY 2019 / SB No. 4 CY 2019 increasing the project cost to P550,000.00 |  | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
5.35 |  | Rehab. Of Multi-Purpose Hall, Magwawa, Sto. Tomas |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | Contract | a) | 500000 | a) | June 19 2019 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Procurement on process |  | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
5.36 |  | Compl. Of Multi-Purpose Hall, San Jose, Sto. Tomas |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) |  | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Amended in AIP 3rd revision CY 2019 / SB No. 4 CY 2019 increasing the project cost to P600,000.00 |  | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
5.37 |  | Const. of Evacuation Center, Bobongon, Sto. Tomas |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Re aligned to other stimulus projects that needs additional funding |  | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
5.38 |  | Rehab. Of Brgy. Road, Lunga-og, Sto. Tomas |  |  | Road Rehabilitation to cater the needs of brgys. | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Amended in AIP 3rd revision CY 2019 / SB No. 4 CY 2019 increasing the project cost to P600,000.00 |  | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
5.39 |  | Rehab. Of Multi-Purpose Hall, New Katipunan, Sto. Tomas |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | Contract | a) | 500000 | a) | 2019-06-07 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Procurement on process |  | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
5.4 |  | Rehab. Of Multi-Purpose Hall, San Miguel, Sto. Tomas |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | Contract | a) | 500000 | a) | 2019-06-07 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Procurement on process |  | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
5.41 |  | Rehab. Of Multi-Purpose Hall, Talomo, Sto. Tomas |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Fund transfer to LGU - 6/26/2019 with check no. 2575130 and OR no. 0557456 For implementation |  | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
IGCS | [23 empty] | 2 | 4
5.42 |  | Rehab. Of Health Center, Aumbay, IGCS |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) | Feb. 28, 2019 | e) | - | a) | 500000 | a) |  | c) | 48.32% | a) | 3 | Completed Financial obligation on process |  | AC | 4
[8 empty] | b) | Pacquiao | b) | 7/10/2019 | f) | - | b) | 500000 | b) | - | d) |  | b) | 15 |  |  | 2 | 4
[8 empty] | c) | Admin | c) | 10/7/2019 | g) | - | c) | - | [8 empty] | 2 | 4
[8 empty] | d) | 90 CD | d) | - | [12 empty] | 2 | 4
5.43 |  | Concreting of Brgy. Road From Prk. 3 to Prk. 5, Catagman, IGCS |  |  | Road Concreting to cater the needs of brgys. | - | Contract | a) | 500000 | a) | Jan. 14, 2019 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For implementation |  | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
5.44 |  | Rehab. Of Multi-Purpose Hall, San Jose, IGCS |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | Admin | a) | 500000 | a) | 2019-03-25 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | On- going |  | 2
[8 empty] | b) | Pacquiao | b) | Jan. 2, 2019 | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
5.45 |  | Elctrification at Sitio Trinidad, Bandera, IGCS |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) | 2019-03-25 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Procurement on process |  | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
5.46 |  | Rehab. Of Brgy. Health Center, Mambago-A, IGCS |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) | Feb. 28, 2019 | e) | - | a) | 500000 | a) |  | c) | 75.61% | a) | 3 | Completed Financial obligation on process |  | 2 | 4
[8 empty] | b) | Ganaba | b) | 07/2019 | f) | - | b) | 500000 | b) |  | d) |  | b) | 15 |  |  | 2 | 4
[8 empty] | c) | Admin | c) | 8/23/2019 | g) | - | c) | - | [8 empty] | 2 | 4
[8 empty] | d) | 45 CD | d) | - | [12 empty] | 2 | 4
5.47 |  | Rehab. Of Multi-Purpose Hall, Del Monte, IGCS |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | Admin | a) | 500000 | a) | 2019-05-29 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Pending/ activity undertaken by DPWH |  | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
5.48 |  | Rehab. Of Multi-Purpose Hall, Aundanao, IGCS |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | Admin | a) | 500000 | a) | 2019-03-18 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | On -going |  | 2
[8 empty] | b) | Porras | b) | Nov. 18, 2019 | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
5.49 |  | Electrification at Upper Purok Rosal, Tagbaobo, IGCS |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Procurement on process. No Abastract |  | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
5.5 |  | Const. Of Multi-Purpose Hall, Mambago-B, IGCS |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For implementation |  | 2
[8 empty] | b) | Roque | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
5.51 |  | Const. Of Multi-Purpose Hall, San Antonio, IGCS |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) | 2019-06-19 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For implementation |  | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
5.52 |  | Concreting of Brgy. Road from Prk. 1 to Prk. 2, Villarica, ICGS |  |  | Road Concreting to cater the needs of brgys. | - | Contract | a) | 500000 | a) | Jan. 14, 2019 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For implementation |  | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
5.53 |  | Rehab. Of Water System Intake Box and Pipeline, Pangubatan, IGCS |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Plan and Pow completed. Waiting of deed of donation |  | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
5.54 |  | Const. Of Multi-Purpose Hall, Cogon (Talicud), IGCS |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Procurement on process. For rebidding Dec. 12, 2019 |  | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
5.55 |  | Installation of Pipelines, Libertad, IGCS |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) | 2019-03-25 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For implementation |  | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
5.56 |  | Rehab. Of Evacuation Center, Libuak, IGCS |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) | 2019-05-29 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For implementation |  | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
5.57 |  | Const. of Water System Project, Pob. Kaputian, IGCS |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | for Allotment |  | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
2
5.58 |  | Rehab. Of Potable Water System, San Isidro, Babak, IGCS |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) | 2019-06-19 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For implementation
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) |  | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
5.59 |  | Rehab. Of Potable Water System, San Miguel, IGCS |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) | Feb. 28, 2019 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For implementation |  | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
5.6 |  | Const. of Water System Ph.II, San Remegio, IGCS |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) | 2019-05-29 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For implementation |  | 2
[8 empty] | b) | Porras | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | Admin | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
5.61 |  | Electrificatio at Prk. 1,3,4, 6,7 & 8, Licup, IGCS |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) | 02/20/19 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Procurement of materials on process |  | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
6. Rural Electrification Project (Provincewide) |  |  |  |  | Powerlines/posts installed & rehabilitated | - | - | a) | 5000000 | [12 empty] | See projects listed below |  | 2
[8 empty] | b) | Kim Pao Lu | [14 empty] | AC
[8 empty] | c) | - | [14 empty] | AC
[8 empty] | d) | - | [14 empty] | AC
|  | Rural Electrification , Del Monte, New Corella |  |  | Powerlines/posts installed & rehabilitated | - | - | a) | 3000000 | a) | - | e) | - | a) | 3000000 | a) | - | c) | - | a) | - | For implementation |  | AC
[8 empty] | b) | P.Bueno | b) | - | f) | - | b) | 3000000 | b) | - | d) | - | b) | - |  |  | 1
6.1 | 5 | [6 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
|  | Rural Electrification at St. Bundok, San Roque, New Corella |  |  | Powerlines/posts installed & rehabilitated | - | - | a) | 1000000 | a) | - | e) | - | a) | 1000000 | a) | - | c) | - | a) | - | For allotment- Dec. 3, 2019 |  | 1
[8 empty] | b) | P.Bueno | b) | - | f) | - | b) | 1000000 | b) | - | d) | - | b) | - |  |  | 1
6.2 | 5 | [6 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
|  | Rural Electrification at Pob. Kaputian, (St. Sagrada) IGCS |  |  | Powerlines/posts installed & rehabilitated | - | - | a) | 1000000 | a) | - | e) | - | a) | 1000000 | a) | - | c) | - | a) | - | Procurement on process |  | 1
[8 empty] | b) | P.Bueno | b) | - | f) | - | b) | 1000000 | b) | - | d) | - | b) | - |  |  | 2
6.3 | 10 | [6 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
2
C. 5% CALAMITY FUND CY 2019 | [23 empty] | AC
1 |  | Desiltation/Excavation of rivers and creeks |  |  | creeks and canals deislted | - | - | a) | 3000000 | [12 empty] | See project listed below |  | FS
[8 empty] | b) | Paraguya | [14 empty] | AC
[8 empty] | c) | PEO | [14 empty] | AC
[8 empty] | d) | - | [14 empty] | AC
|  | 1.1 | Desilting of Limbaan Creek, New Corella |  | creeks and canals deislted | - | - | a) | 2000000 | a) | - | e) | - | a) | 2000000 | a) | - | c) | - | a) | - | POW preparation on going |  | AC
| 5 | [6 empty] | b) | - | b) | - | f) | - | b) | 2000000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
1
a. |  | Desiltation of Mactan River Ph. II |  |  | creeks and canals deislted | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | on-going |  | 1
[8 empty] | b) | Toquero | b) | 7/29/2019 | f) | - | b) | 500000 | b) | - | d) | - | b) | - | TIME EXTENSION PROCESS |  | 1
[8 empty] | c) | Admin | c) | 9/27/2019 | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | 60 C.D | d) | - | [12 empty] | 1
2 |  | Revitment of Dike and Slope Proection |  |  | Protection dikes/slope protection | - | - | a) | 3000000 | [12 empty] | See projects listed below |  | AC
[8 empty] | b) | - | [14 empty] | AC
[8 empty] | c) | - | [14 empty] | AC
[8 empty] | d) | - | [14 empty] | AC
|  | 2.1 | Slope Protection Along Kapalong-Mabantao, Florida |  | creeks and canals deislted | - | - | a) | 1000000 | a) | - | e) | - | a) | 1000000 | a) | - | c) | - | a) | - | For cancellation funded to DPWH. Budget Transferred to |  | AC
| 4 | [6 empty] | b) | - | b) | - | f) | - | b) | 1000000 | b) | - | d) | - | b) | - | 5% Calamity Fund- Rehab and Recovery |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
b. |  | Repair/Rehab. Of Upper Tuganay Dike |  |  | creeks and canals deislted | - | - | a) | 1000000 | a) | - | e) | - | a) | 1000000 | a) | - | c) | - | a) | - | ON-GOING |  | 1
[8 empty] | b) | Toquero | b) | 8/19/2019 | f) | - | b) | 1000000 | b) | - | d) |  | b) | - | TIME EXTENSION PROCESS |  | 2
[8 empty] | c) | Admin | c) | 9/29/2019 | g) |  | c) | - | [8 empty] | 2
[8 empty] | d) | 59 C.D | d) | - | [12 empty] | 2
3 |  | Improvement of roads, drainage and canal |  |  | Protection dikes/slope protection | - | - | a) | 3000000 |  |  |  | - | [8 empty] | See projects listed below |  | 2
[8 empty] | b) | Paraguya | [14 empty] | AC
[8 empty] | c) | PEO | [14 empty] | AC
[8 empty] | d) | - | [14 empty] | AC
a. |  | Rehab./Impv't. of New Casay-Bugtong Talisay Provincial Road (Ph.II) |  |  | creeks and canRoads/Draiange/canals rehab/improved | - | - | a) | 500000 | a) | 2019-03-12 | e) |  | a) | 500000 | a) | 100% | c) | 100% | a) | 12 | Completed |  | AC
[8 empty] | b) | Toquero | b) | 2019-05-30 | f) |  | b) | 500000 | b) | - | d) | - | b) | 120 |  |  | 2
[8 empty] | c) | Admin | c) | 2019-07-30 | g) | 7/30/2019 | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
b. |  | Rehab./Impv't. of Prk. 1 - Prk. 2 Sitio Pawas Provincial Road |  |  | creeks and canRoads/Draiange/canals rehab/improved | - | - | a) | 1500000 | a) | 7/23/2019 | e) | - | a) | 1500000 | a) | 17.14% | c) | 1.18% | a) | 2 |  |  | 2
[8 empty] | b) | Sanchez | b) | 8/05/2019 | f) |  | b) | 1500000 | b) | - | d) | -15.96% | b) | 10 | On-going |  | 2
[8 empty] | c) | Admin | c) | 9/28/2019 | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | 55 | d) | - | [12 empty] | 2
c. |  | Repair/Rehab of Drainage System & Ground Gravelling at Kimamon NHS |  |  | creeks and canRoads/Draiange/canals rehab/improved | - | - | a) | 464833 | a) | - | e) | - | a) | 464833 | a) |  | c) | [5 empty] | 2
[8 empty] | b) | Azotes | b) | - | f) | - | b) | 464833 | b) |  | d) | [5 empty] | 2
[8 empty] | c) | Admin | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
2
4 |  | Improvement of bridges and cross drainage |  |  | bridge and cross drainage rehab./improved # of sq.m riprapped, culverts replaced | - | - | a) | 3000000 | [12 empty] | See projects listed below
[8 empty] | b) | Paraguya | [14 empty] | AC
[8 empty] | c) | PEO | [14 empty] | AC
[8 empty] | d) | - | [14 empty] | AC
|  | 4.1 | Impv't. of Jct. New Boholano - New Loon Cross Drainage |  | creeks and canRoads/Draiange/canals rehab/improved | - | - | a) | 2000000 | a) | - | e) | - | a) | 2000000 | a) | - | c) | - | a) | - | POW preparation on going c/o PEO-PDPM. Insufficient budget to complete required works for the project |  | AC
| 1 | [6 empty] | b) | - | b) | - | f) | - | b) | 2000000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
|  | 4.2 | Impv't. of Jct. Saug-Sonlon-Bdry. Longanapan Cross Drainage |  | creeks and canRoads/Draiange/canals rehab/improved |  | - | a) | 1000000 | a) | - | e) | - | a) | 1000000 | a) | - | c) | - | a) | - | Waiting for the delivery of Materials |  | 1
| 1 | [6 empty] | b) | - | b) | - | f) | - | b) | 1000000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
D. | SUPPLEMENTAL BUDGET NO. 1 CY 2019 | [22 empty] | AC
| 8918/Purchase / Const. / Compl./ Imprvt. Of Various Gov'y Bldgs, Structures & Facilities - General Fund Proper | [22 empty] | FS
| ■ | Purchase of Lot for Cemetery, Cambanogoy, Asuncion |  |  | Land |  | - | a) | 1500000 | a) | - | e) | - | a) | 1500000 | a) | - | c) | - | a) | - | Documents for fund transfer to be complied by the LGUs. Letter sent dated June 18, 2019 |  | AC
| 1 | [6 empty] | b) | - | b) | - | f) | - | b) | 1500000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| ■ | Purchase of Lot for Cemetery, San Roque, New Corella |  |  | Land |  | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Documents for fund transfer to be complied by the LGUs. Letter sent dated June 18, 2019 |  | 1
| 5 | [6 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| 8918/Stimulus Projects for Various Barangays. Const. in Progress - Bldgs & Other Structure | [22 empty] | 1
| ■ | Rehab/Impvt of Gymnasium, Sagayen, Asuncion |  |  | Bldg |  | - | a) | 1500000 | a) | - | e) | - | a) | 1500000 | a) | - | c) | - | a) | - | for allotment - Sept 19, 2019 |  | AC
| 1 | [6 empty] | b) | - | b) | - | f) | - | b) | 1500000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| ■ | Installation of Bleacher for the Brgy. Gym, Concepcion, Asuncion |  |  | Bldg |  | - | a) | 1000000 | a) | - | e) | - | a) | 1000000 | a) | - | c) | 30% | a) | - | On-going |  | 1
| 1 | [6 empty] | b) | - | b) | - | f) | - | b) | 1000000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
LOCALLY FUDNDED PROGRAM/PROJECT - 20% Development Fund
| Infrastructure Development Program | [22 empty] | AC
| 8918/ Stimulus Projects for Various Barangays | [22 empty] | AC
| Property, Plant and Equipment - Land | [22 empty] | AC
| ■ | Purchase of Lot for Resettlement Site, New Sambog, New Corella |  |  | Land |  | - | a) | 1500000 | a) | - | e) | - | a) | 1500000 | a) | - | c) |  | a) | - | for fund transfer. Waiting for LGU documents. Liquidation of previous fund transfer for the water system project of LGU. |  | AC
| 5 | [6 empty] | b) | - | b) | - | f) | - | b) | 1500000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| Property, Plant and Equipment - Construction in Progress-Infrastructure Assets | [22 empty] | 1
| ■ | Installation of Street Lights at Prk 1,2,3,4, Sagayen, Asuncion |  |  | Electrification |  | - | a) | 1000000 | a) | - | e) | - | a) | 1000000 | a) | - | c) |  | a) | - | PO on process |  | AC
| 1 | [6 empty] | b) | - | b) | - | f) | - | b) | 1000000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
1
| ■ | Rehab/Imprvt. Of FMR, Prk 3,7, & 8, Concepcion, Asuncion |  |  | Road |  | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) |  | a) | - | Procurement of Materials on process
| 1 | [6 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| ■ | Rural Electrification Project, Purok 6, Concepcion, Asuncion |  |  | Electrification |  | - | a) | 1000000 | a) | - | e) | - | a) | 1000000 | a) | - | c) |  | a) | - | . Re-aligned Fund allocation to Construction of Children Playground withAmenities at Pob., New Corella |  | 1
| 1 | [6 empty] | b) | - | b) | - | f) | - | b) | 1000000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| ■ | Concreting of FMR, New Santiago, Asuncion |  |  | Road |  | - | a) | 2500000 | a) | 2019-05-21 | e) | - | a) | 2500000 | a) | - | c) | 30% | a) | - | Fund transferred to LGU |  | 1
| 1 | [6 empty] | b) | - | b) | - | f) | - | b) | 2500000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| ■ | Rural Electrification Project, Purok 5-8, Napungas, Asuncion |  |  | Electrification |  | - | a) | 1500000 | a) | - | e) | - | a) | 1500000 | a) | - | c) | - | a) | - | . Re-aligned Fund allocation to Construction of Children Playground withAmenities at Pob., New Corella |  | 1
| 1 | [6 empty] | b) | - | b) | - | f) | - | b) | 1500000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| ■ | Farm to Market Road, San Jose, New Corella |  |  | Road |  | - | a) | 2000000 | a) | - | e) | - | a) | 2000000 | a) | - | c) | - | a) | - | Plan Preparation on process c/o PDPM |  | 1
| 5 | [6 empty] | b) | - | b) | - | f) | - | b) | 2000000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| ■ | Const. of Water System, New Sambog, New Corella |  |  | Water System Projects |  | - | a) | 1000000 | a) | - | e) | - | a) | 1000000 | a) | - | c) | - | a) | - | Fund transferred to LGU
| 5 | [6 empty] | b) | - | b) | - | f) | - | b) | 1000000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| ■ | Const. of Drainage Canal from Prk. 3, 1-A, 2-A to Prk 1-B, Brgy Site (Ph. 2), Limbaan, New Corella |  |  | Flood Control - Drainage |  | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | POW preparation on going c/o PDPM |  | 1
| 5 | [6 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| ■ | Const. of FMR from Prk 1 to Sitio Magsaysay via Pundol & Prk 4, Patrocenio, New Corella |  |  | Road |  | - | a) | 2000000 | a) | - | e) | - | a) | 2000000 | a) | - | c) | - | a) | - | POW preparation on going c/o PDPM |  | 1
| 5 | [6 empty] | b) | - | b) | - | f) | - | b) | 2000000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) |  | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| ■ | Const. of Multi-Purpose Pavement, San Jose, New Corella |  |  | Bldgs |  | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | POW approved but allotment not yet requested waiting for deed of donation c/o Engr. Canillada
| 5 | [6 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| Const. in Progress - Bldgs & Other Structures | [22 empty] | 1
| ■ | Rehab/Impvt of Multi-Purpose Bldg, SCFA, Napungas, Asuncion |  |  | Bldgs |  | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Fund re-aligned to fund stimulus projects that need additional funding. ( AIP 3rd revision CY 2019) |  | AC
| 1 | [6 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
1
| ■ | Const. of Multipurpose Covered Court, Buan, Asuncion |  |  | Bldgs |  | - | a) | 2500000 | a) | 2019-06-26 | e) | - | a) | 2500000 | a) | - | c) | - | a) | - | Fund transferred to LGU
| 1 | [6 empty] | b) | - | b) | - | f) | - | b) | 2500000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| ■ | Const. of Multipurpose Covered Court, Pamacaun, Asuncion |  |  | Bldgs |  | - | a) | 2500000 | a) | 2019-05-29 | e) | - | a) | 2500000 | a) | - | c) | 30% | a) | - | Fund transferred to LGU |  | 1
| 1 | [6 empty] | b) | - | b) | - | f) | - | b) | 2500000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| ■ | Const. of 2 Storey Multipurpose Hall Ph.2 (Brgy. Hall) , Poblacion, New Corella |  |  | Bldgs |  | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Plan preparation on -going c/o PDPM |  | 1
| 5 | [6 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| ■ | Rehab. Of Multi-Purpose Hall (Evacuation Ctr.) Limbaan, New Corella |  |  | Bldgs |  | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For allotment - Nov. 5, 2019
| 5 | [6 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) |  | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| ■ | Expansion of Multi-Purpose Hall ( Brgy. Hall), Patrocenio, New Corella |  |  | Bldgs |  | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Sched of bidding Dec 27 , 2019 |  | 1
| 5 | [6 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
MOOE 2019 | [9 empty] | a) |  | e) |  | a) |  | a) |  | c) |  | a) |  | For approval of POW and Plan |  | 1
|  | Repair maintenance of OPD, Pharmacy building, DDNH - CZ Compound |  |  | Renovation | - | - | a) | 100000 | b) |  | f) |  | b) |  | b) |  | d) |  | b) |  |  |  | AC
[8 empty] | b) | Estorco | c) |  | g) |  | c) | [9 empty] | 2
[8 empty] | c) | Admin | d) | [13 empty] | 2
[8 empty] | d) | - | [14 empty] | 2
E. | SUPPLEMENTAL BUDGET NO. 3 CY 2019
| LOCALLY FUNDED PROGRAM/PROJECTS- 20% DEVELOPMENT FUND | [22 empty] | FS
| INFRASTRUCTURE DEVELOPMENT PROGRAM | [22 empty] | AC
| 8918/ Various Local Roads & Drainage Development Project Construction in Progress- Infrastructure Assets | [22 empty] | AC
| ■ | Rehabilitation of Dujali-Pawas-San Vicente Provincial Road, B.E. Dujali |  |  | Road |  | - | a) | 2000000 | a) | - | e) | - | a) | 2000000 | a) | - | c) | - | a) | - | The amount was reduced to P1,102,900.00 |  | AC
[8 empty] | b) | - | b) | - | f) | - | b) | 2000000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
| ■ | Repair/Rehabil;itation of Concrete R.d. Jct. Suaon-Libuton Kapalong |  |  | Road |  | - | a) | 1000000 | a) | - | e) | - | a) | 1000000 | a) | - | c) | - | a) | - | For implementation |  | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 1000000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| 8918/ VariousWater System Development Project Construction in Progress- Infrastructure Assets | [22 empty] | 1
| ■ | Improvement of Potable Water System at Brgy. Mambago- A, Samal District, IGACOS |  |  | Water System |  | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | (Amended in the AIP 2nd Revision to change the location from Peñaplata to Samal District) PO approved September 2, 2019 |  | AC
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
| ■ | Rehabilitation of Potable Water System at Brgy. San Miguel, Samal District, IGACOS |  |  | Water System |  | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - |  |  | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
| ■ | Construction of Potable Water System at Brgy.Linusotan, Kaputian District, IGACOS |  |  | Water System |  | - | a) | 1300000 | a) | - | e) | - | a) | 1300000 | a) | - | c) | - | a) | - | (Additional 800,000.00 from Const. of PWS in purok 2, Pag-asa, Kapalong which was funded by OPAPP CY 2018) (amended) For allotment- October 15, 2019 |  | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 1300000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
| ■ | Rehabilitation of Water System in PEEDO-LPRRC, Brgy. Poblacion, New Corella |  |  | Water System |  | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For allotment- October 15, 2019 |  | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) |  | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
| 8918/ Stimulus Projects for Various Brgys.- District 1 Construction in Progress- Infrastructure Assets | [22 empty] | 2
| ■ | Construction of Water System at Brgy. San Agustin, Tagum City |  |  | Water System |  | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Declared as savings to add to stimulus projects that need additional fund No deed of donation |  | AC
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
| DISASTER REHABILITATION & RECOVERY PROGRAM Building Back Better Project | [22 empty] | 2
| Repairs & Maintenance- Infrastructure Assets | [22 empty] | AC
| ■ | Disilation of Tagum Creek |  |  |  |  | - | a) | 2000000 | a) | - | e) | - | a) | 2000000 | a) | - | c) | - | a) | - | PLAN AND POW on process c/o PEO-PDPM |  | AC
[8 empty] | b) | - | b) | - | f) | - | b) | 2000000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| ■ | Disilation of Mactan River (Ph. II) |  |  |  |  | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | PLAN AND POW on process c/o PEO-PDPM |  | 1
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
| Property, Plant and Equipmen Construction in Progress- Infrastructure Assets | [22 empty] | 2
| ■ | Rehabilitation of Pamacaun-Lasang-Banate Provincial Road |  |  |  |  | - | a) | 1500000 | a) | - | e) | - | a) | 1500000 | a) | - | c) | - | a) | - |  |  | AC
[8 empty] | b) | - | b) | - | f) | - | b) | 1500000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| ■ | Rehabilitation of Del Pilar Jct. Silangan |  |  |  |  | - | a) | 1500000 | a) | - | e) | - | a) | 1500000 | a) | - | c) | - | a) | - |  |  | 1
[8 empty] | b) | - | b) | - | f) | - | b) | 1500000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| ■ | Installation of 72" dia RCPC x 4M at San Agustin ES |  |  |  |  | - | a) | 350000 | a) | - | e) | - | a) | 350000 | a) | - | c) | - | a) | - |  |  | 1
[8 empty] | b) | - | b) | - | f) | - | b) | 350000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| ■ | Rehabilitation of Libuganon River along Kapalong Mabantao-Florida Provincial Road |  |  |  |  | - | a) | 900000 | a) | - | e) | - | a) | 900000 | a) | - | c) | - | a) | - |  |  | 1
[8 empty] | b) | - | b) | - | f) | - | b) | 900000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| ■ | Rehabilitation of Mesaoy-Jct. Mahayahay Road |  |  |  |  | - | a) | 1000000 | a) | - | e) | - | a) | 1000000 | a) | - | c) | - | a) | - |  |  | 1
[8 empty] | b) | - | b) | - | f) | - | b) | 1000000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| ■ | Rehabilitation of Dujali-Balisong-Magupising Provincial Road |  |  |  |  | - | a) | 1280000 | a) | - | e) | - | a) | 1280000 | a) | - | c) | - | a) | - |  |  | 1
[8 empty] | b) | - | b) | - | f) | - | b) | 1280000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| ■ | Rehabilitation of Sta. Fe- Mambing Road & Slope Protection |  |  |  |  | - | a) | 1320000 | a) | - | e) | - | a) | 1320000 | a) | - | c) | - | a) | - |  |  | 1
[8 empty] | b) | - | b) | - | f) | - | b) | 1320000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) |  | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
F. | SUPPLEMENTAL BUDGET NO. 4 CY 2019 | [22 empty] | 1
| INFRASTRUCTURE DEVELOPMENT PROGRAM | [22 empty] | FS
| LOCALLY FUNDED PROGRAMS/ PROJECTS GENERAL FUND PROPER | [22 empty] | AC
AC
| PEACE AND ORDER PROGRAM/1914 Construction in Progress- Land Improvements | [22 empty] | AC
| ■ | Provincial Livestock & Poultry Multiplier Farm Road Network Construction, Sitio Salawao, Sto. Niño, Talaingod |  |  |  |  | - | a) | 5500000 | a) | - | e) | - | a) | 5500000 | a) | - | c) | - | a) | - | For allotment Nov. 22, 2019 |  | AC
[8 empty] | b) | - | b) | - | f) | - | b) | 5500000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| ■ | Proposed Road Opening of Tawinian-Tapayanon Road Section |  |  |  |  | - | a) | 10000000 | a) | - | e) | - | a) | 10000000 | a) | - | c) | - | a) | - | Alloted- Dec. 6, 2019 |  | 1
[8 empty] | b) | - | b) | - | f) | - | b) | 10000000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| ■ | Rehabilitation of San Jose- Sitio Mahayahay-Magwawa Provincial Road, Sro. Tomas |  |  |  |  | - | a) | 1000000 | a) | - | e) | - | a) | 1000000 | a) | - | c) | - | a) | - | POW preparation on-going c/o South District |  | 1
[8 empty] | b) | - | b) | - | f) | - | b) | 1000000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
| 8918/ Various Government Buildigs & Facilities Development Project Construction in Progress- Land Improvements | [22 empty] | 2
| ■ | Construction of Perimeter Fence of Day Care Center I Nanyo, Panabo City |  |  |  |  | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Sched of bidding Dec. 27, 2019 |  | AC
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
| ■ | Construction of Multi-Purpose Building, Balagunan, Sto. Tomas |  |  |  |  | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For allotment Dec .3, 2019 |  | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
| ■ | Completion of Brgy. Health Center, Maniki, Kapalong |  |  |  |  | - | a) | 627000 | a) | - | e) | - | a) | 627000 | a) | - | c) | - | a) | - | PROJECT Was funded by LGU, Kapalong |  | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 627000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| INFRASTRUCTURE DEVELOPMENT PROGRAM | [22 empty] | 1
| LOCALLY FUNDED PROGRAMS/ PROJECTS 20% DEVELOPMENT FUND | [22 empty] | AC
AC
| 8918/ Rehabilitation of Various Provincial Roads, District 1 Construction in Progress- Infrastructure Assets | [22 empty] | AC
| ■ | Improvement of Km. 9 Sagayen-Sawata Provincial Road, San Isidro, Ph. 2 |  |  |  |  | - | a) | 4591029 | a) | - | e) | - | a) | 4591029 | a) | - | c) | - | a) | - |  |  | AC
[8 empty] | b) | - | b) | - | f) | - | b) | 4591029 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| 8918/ Various Local Roads and Drainaige Development Project Construction in Progress- Infrastructure Assets | [22 empty] | 1
| ■ | Rehabilitation of Local Roads at Dalisay-Manay Road Section, Panabo City |  |  |  |  | - | a) | 246100 | a) | - | e) | - | a) | 246100 | a) | - | c) | - | a) | - |  |  | AC
[8 empty] | b) | - | b) | - | f) | - | b) | 246100 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
| ■ | Rehabilitation of Local Roads at Sta. Cruz-Jct. Tagpore-Buenavista Raod Section, Panabo City |  |  |  |  | - | a) | 431000 | a) | - | e) | - | a) | 431000 | a) | - | c) | - | a) | - |  |  | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 431000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) |  | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
-
| ■ | Rehabilitation of Local Roads at Taba-Bucana Road Section, Taba, Carmen |  |  |  |  | - | a) | 220000 | a) | - | e) | - | a) | 220000 | a) | - | c) | - | a) | - |  |  | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 220000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
| 8918/ Stimulus Projects for Various Barangays Construction in Progress- Infrastructure Assets | [22 empty] | 2
| ■ | Construction of Potable Water System at Purok 6, New Santiago, Asuncion |  |  |  |  | contract | a) | 1000000 | a) | - | e) | - | a) | 1000000 | a) | - | c) | - | a) | - | For allotment Nov. 6, 2019 |  | AC
[8 empty] | b) | - | b) | - | f) | - | b) | 1000000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
| ■ | Concreting of Brgy. Road Canal, Dujali, B.E. Dujali |  |  |  |  | contract | a) | 650000 | a) | - | e) | - | a) | 650000 | a) | - | c) | - | a) | - | Alloted Oct. 18, 2019 Procurement on process |  | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 650000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
| ■ | Desilting and Conretign of Drainage-Main Collector Canal, New Casay, B.E. Dujali |  |  |  |  | contract | a) | 650000 | a) | - | e) | - | a) | 650000 | a) | - | c) | - | a) | - | For allotment - Sept. 27, 2019 |  | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 650000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
| ■ | Concreting of Drainage, Tanglaw, B.E., Dujali |  |  |  |  | contract | a) | 1200000 | a) | - | e) | - | a) | 1200000 | a) | - | c) | - | a) | - | For allotment Sept. 19, 2019 |  | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 1200000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
| ■ | Construction of Potable Water System, New Malitbog, Panabo City |  |  |  |  | contract | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For re-inspection and plan revision in order to reflect in the plan the complete details for the project to be functional.P500,000.00 covers only drilling activity |  | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
| ■ | Construction of Water System Project, Poblacion Kaputian, Samal |  |  |  |  | contract | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Alloted Oct 17, 2019 Procurement on process |  | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
| ■ | Construction of Canal Linign at Prk. 5, Salvacion, Panabo City |  |  |  |  | contract | a) | 600000 | a) | - | e) | - | a) | 600000 | a) | - | c) | - | a) | - | Alloted Oct. 18, 2019 Procurement on process |  | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 600000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
| ■ | Rehabilitation of Brgy. Road at Lunga-og. Sto. Tomas |  |  |  |  | contract | a) | 600000 | a) | - | e) | - | a) | 600000 | a) | - | c) | - | a) | - | For allotment Sept. 19, 2019 |  | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 600000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
| ■ | Construction of Children's Playground with Amenities, Poblacion, New Corella |  |  |  | Admin | contract | a) | 2500000 | a) | - | e) | - | a) | 2500000 | a) | - | c) | - | a) | - | Allotment Dec. 3, 2019 Procurement on process |  | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 2500000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| 8918/ Stimulus Projects for Various Barangays Construction in Progress- Bldgs. & Other Structures | [22 empty] | 1
| ■ | Construction of 2 Storey Multi-Purpose Hall Ph. 3 (Brgy. Hall), oblacion, New Corella |  |  |  |  | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Plan preparation on-going c/o PDPM |  | AC
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| ■ | Construction of Evacuation Center at Purok 1-C Brgy. Sto. Niño, Carmen |  |  |  |  | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For allotment Dec. 3, 2019 |  | 1
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) |  | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
| ■ | Rehabilitation of Evacuation Center at Magugpo Pob., Tagum City |  |  |  |  | - | a) | 600000 | a) | - | e) | - | a) | 600000 | a) | - | c) | - | a) | - | Sched of bidding Dec 27, 2019 |  | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 600000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| ■ | Construction of Brgy. Health Center at Magugpo South, Tagum City |  |  |  |  | - | a) | 1550000 | a) | - | e) | - | a) | 1550000 | a) | - | c) | - | a) | - | Allotd Nov. 15, 2019 Procurement on process |  | 1
[8 empty] | b) | - | b) | - | f) | - | b) | 1550000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
1
| ■ | Rehabilitation of Mulit-Purpose Building (Evacuation Center), Limbaan, New Corella |  |  |  |  | - | a) | 600000 | a) | - | e) | - | a) | 600000 | a) | - | c) | - | a) | - | For allotment nov. 5, 2019
[8 empty] | b) | - | b) | - | f) | - | b) | 600000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| ■ | Expansion of Multi-Purpose Hall ( Brgy. Hall), Patrocenio, New Corella |  |  |  |  | - | a) | 650000 | a) | - | e) | - | a) | 650000 | a) | - | c) | - | a) | - | Alloted Oct. 18, 2019 Procurement on process |  | 1
[8 empty] | b) | - | b) | - | f) | - | b) | 650000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| ■ | Construction of Multi-Purpose Hall, Waterfall, Panabo City |  |  |  |  | - | a) | 1050000 | a) | - | e) | - | a) | 1050000 | a) | - | c) | - | a) | - | For allotment |  | 1
[8 empty] | b) | - | b) | - | f) | - | b) | 1050000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
| ■ | Rehabilitation of Multi-Purpose Hall, San Francisco, Panabo City |  |  |  |  | - | a) | 600000 | a) | - | e) | - | a) | 600000 | a) | - | c) | - | a) | - | Alloted Oct. 18, 2019 Procurement on process |  | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 600000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
| ■ | Rehabilitation of Evacuation Center at Datu Abdul Dadia, Panabo City |  |  |  |  | - | a) | 650000 | a) | - | e) | - | a) | 650000 | a) | - | c) | - | a) | - | Sched of bidding -Dec 27, 2019 |  | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 650000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
| ■ | Construction of Multi-Purpose Hall, Buenavista, Panabo City |  |  |  |  | - | a) | 1050000 | a) | - | e) | - | a) | 1050000 | a) | - | c) | - | a) | - | Sched of bidding -Dec 27, 2019 |  | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 1050000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
| ■ | Rehabilitation of Multi-Purpose Hall, Llittle Panay, Panabo City |  |  |  |  | - | a) | 550000 | a) | - | e) | - | a) | 550000 | a) | - | c) | - | a) | - | For allotment Dec. 11, 2019 |  | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 550000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
| ■ | Rehabilitation of Multi-Purpose Hall, Pantaron, Sto. Tomas |  |  |  |  | - | a) | 550000 | a) | - | e) | - | a) | 550000 | a) | - | c) | - | a) | - | Alloted Oct. 18, 2019 Procurement on process |  | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 550000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
| ■ | Rehabilitation of Multi-Purpose Hall, Salvacion, Sto. Tomas |  |  |  |  | - | a) | 1000000 | a) | - | e) | - | a) | 1000000 | a) | - | c) | - | a) | - | POW preparation on-going c/o PDPM |  | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 1000000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
| ■ | Completion of Multi-Purpose Hall, San Jose, Sto. Tomas |  |  |  |  | - | a) | 600000 | a) | - | e) | - | a) | 600000 | a) | - | c) | - | a) | - | Alloted Nov. 15, 2019 Procurement on process |  | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 600000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
| ■ | Rehabilitation of Multi-Purpose Hall, Kasilak, Panabo City |  |  |  |  | - | a) | 650000 | a) | - | e) | - | a) | 650000 | a) | - | c) | - | a) | - | Alloted Nov. 15, 2019 Procurement on process |  | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 650000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) |  | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
| ■ | Rehabilitation of Brgy. Health Center, Dalisay, Panabo City |  |  |  |  | - | a) | 550000 | a) | - | e) | - | a) | 550000 | a) | - | c) | - | a) | - | For allotment Dec. 4, 2019 |  | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 550000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
2
| ■ | Rehabilitation of Evacuation Center, Kiotoy, Panabo City |  |  |  |  | - | a) | 650000 | a) | - | e) | - | a) | 650000 | a) | - | c) | - | a) | - | Sched of bidding Dec 27, 2019
[8 empty] | b) | - | b) | - | f) | - | b) | 650000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
| ■ | Rehabilitation of Evacuation Center, Cagangohan, Panabo City |  |  |  |  | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | POW for approval Nov. 5, 2019 |  | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
| ■ | Rehabilitation of Multi-Purpose Bldg. (Brgy. Hall) Tagpopongan, IGACOS |  |  |  |  | - | a) | 174460.33 | a) | - | e) | - | a) | 174460.33 | a) | - | c) | - | a) | - | For allotment Nov. 5, 2019 |  | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 174460.33 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
| 5% CALAMITY FUND | [22 empty] | 2
| DISASTER REHABILITATION & RECOVERY PROGRAM Building Back Better Project | [22 empty] | FS
| ■ | Rehabilitation of Canal Lining and Slope Protection at San Agustin E/S, San Agustin, Tagum City |  |  |  |  | - | a) | 350000 | a) | - | e) | - | a) | 350000 | a) | - | c) | - | a) | - |  |  | AC
[8 empty] | b) | - | b) | - | f) | - | b) | 350000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| TRUST FUND 2019 | [22 empty] | 1
| PROJECTS FOR PROVINCIAL VETERINARY OFFICE | [22 empty] | FS
| ■ | Poultry House and Training Center Sto. Niño, Talaingod |  |  |  |  | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - |  |  | AC
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
|  | Establishment of Multiplier Farm Project Sto. Niño, Talaingod |  |  |  |  | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - |  |  | 1
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| INFRASTRUCTURE DEVELOPMENT PROGRAM | [22 empty] | 1
| ■ | Purchase of Geo Resistivity Instrument |  |  |  |  | - | a) | 6567412 | a) | - | e) | - | a) | 6567412 | a) | - | c) | - | a) | - | Waiting for delivery of instrument |  | AC
[8 empty] | b) | - | b) | - | f) | - | b) | 6567412 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
CMGP 2019
| ■ | Road Upgrading of Sto Nino - Kabankalan - La Paz Provincial Road, Carmen |  |  |  |  | - | a) | 44461624.67 | a) |  | e) | - | a) | - | a) | 4.3% | c) | 34.23% | a) | 30 | On-going
[8 empty] | b) | Comidoy | b) | 10/7/2019 | f) | - | b) | - | b) | - | d) | 29.93% | b) | 610 |  |  | 2
[8 empty] | c) | GP & H CONST. | c) | 5/15/2020 | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | 222 C.D | d) | [13 empty] | 2
| ■ | Road Upgrading of Jct Highway - Sto Nino - La Paz - San Vicenter Provincial Road, Carmen |  |  |  |  | - | a) | 80481331.34 | a) |  | e) | - | a) | - | a) | 22.77% | c) | 33.12% | a) | - | On-going |  | 2
[8 empty] | b) | Fernandez | b) | 10/7/2019 | f) | - | b) | - | b) | - | d) | 10.35% | b) | -
[8 empty] | c) | Tagum Builders | c) | 6/22/2020 | g) | - | c) | -
[8 empty] | d) | 259 C.D | d)
| ■ | Road Upgrading of Kapalong - Mabantao - Florida Road with Bridge Component |  |  |  |  | - | a) | 15890000 | a) |  | e) | - | a) | - | a) |  | c) |  | a) | -
[8 empty] | b) |  | b) |  | f) | - | b) | - | b) | - | d) |  | b) | -
[8 empty] | c) |  | c) |  | g) | - | c) | -
[8 empty] | d) |  | d)
|  | Mark | Municipality/City |  | Color
|  | 1 | Asuncion |  | Red
|  | 2 | B.E. Dujali |  | Yellow
| GF- GENERAL FUND | 3 | Carmen |  | Blue | [10 empty] | TF - TRUST FUND (NATIONAL FUNDED PROJECT)
| 20% DF - 20% DEV'T. FUND | 4 | Kapalong |  | Pink | [10 empty] | a) SLRF - Special Local Road Fund
| 5% CF - 5% CALAMITY FUND | 5 | New Corella |  | Gray | [10 empty] | b) KALSADA - Konkreto at Ayos na Lansangan Tungo sa Pangkalahatang Kaunlaran
| CO - CAPITAL OUTLAY | 6 | San Isidro |  | Orange | [10 empty] | c) PRDP - Philippine Rural Development Projects
| CONG. FUND - CONGRESSIONAL FUND | 7 | Sto Tomas |  | Sky Blue | [10 empty] | d) SELAP - Support to Emergency and Livelihood Assistance Project
|  | 8 | Talaingod |  | Violet | [10 empty] | e) PAMANA - Payapa at Masaganang Pamayanan
| SEF - SPECIAL EDUCATIONAL UFND | 9 | Panabo City |  | Brown | [10 empty] | f) CBRMC - Community Based Road Maintenance Contracting
|  | 10 | IGACOS |  | Yellow Green | [10 empty] | g) MBC - Maintenance by Contract
|  | 11 | Tagum City |  | Green | [10 empty] | h) PCF-Performance Challenge Fund-DILG
i) FMRDP - Farm to Market Road
j.) CMGP - Conditional Grant to Provinces
k.) OPAPP - Office of the President Adviser on the Peace Process
l.) LGSF-AM - Local Government Support Fund Assistance to Municipalities
Prepared by: |  |  |  | Checked | [12 empty] | Recommending Approval
Noted
GILBERT G. MAMBULAO JR |  |  |  | ELISA A. BARCENA | [10 empty] | JIVELLYN B. CO | [5 empty] | GLENN A. OLANDRIA
Engineer II |  |  |  | Engineer IV- Engineering Dist 1, Area Engineer | [11 empty] | Asst. PG-Department Head |  |  |  |  | Provincial Engineer
|  |  |  | EDWIN S. MISA |  |  |  | MARILOU A. FORONDA
|  |  |  | Engineer IV- PDPM Division Head |  |  |  | Engineer IV- QC Division Head

## Annual On going 2019_Dist2 (hidden)
PROVINCE OF DAVAO DEL NORTE
ACCOMPLISHMENT REPORT
Annual 2019
SECTOR: ECONOMIC (INFRASTRUCTURE DEV'T. PROGRAM)
OFFICE/AGENCY: PROVINCIAL ENGINEER'S OFFICE
ON-GOING PROJECTS DISTRICT Dist 2
Name of Project |  |  |  |  | Type | Physical | Mode | PROJECT DATA | [5 empty] | Financial (000) |  | Physical Accomplishment |  |  |  | Employment |  | REMARKS
[5 empty] | of | Target | of | a) Project Cost |  | a) | Date A lot. Rel. | e) | # of days suspended | a) Program |  | a) Planned |  | c) Actual |  | Generated
[5 empty] | Project | (Descrip | Impl. | b) Project Engineer |  | b) | Date Started | f) | # of days extended | b) Allotment |  | b) Revised |  | d) Slippage |  | a) # of Persons | # of Persons
[5 empty] | (Location) | tion) |  | c) Implementor |  | c) | Target Compl. Date | g) | Date completed | c) Disbursement | [5 empty] | b) | Man-days
[8 empty] | d) Duration |  | d) | Revised Compl. Date
I. | PROJECTS UNDER THE CONTINUING APPROPRIATION | [22 empty] | AC |  |  |  | 893809.45
| A. | Supplemental Budget # 1 CY 2015 | [19 empty] | delay due to change location & design code. For AIP amendment from Panabo City to Gov't Center, Mankilam |  | 2
|  | 1. Proposed Davao del Norte Tourism Billboard |  |  | Billboard |  | Admin | a) | 756,400.00 | a) | 05/06/15 | e) | - | a) | 756,400.00 | a) | 11.78% | c) | 11.78% | a) | - |  |  | 2
|  | Brgy. Lasang, Panabo City | [5 empty] | b) | Porras | b) | 03/30/15 | f) | - | b) | 756,400.00 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | PEO | c) | 05/10/15 | g) | - | c) | 332,087.30 | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
| B. | Supplemental Budget # 5 CY 2015 | [21 empty] | FS
|  | 1. Purchased, Const. & Imprv't. of Gov't. Facilities (8918) | [19 empty] | See projects listed below |  | AC
|  | a) Const./Compl./Imprvt. of Various Gov't. Bldgs. |  |  | Bldgs. |  | Admin | a) | 38,000,000.00 | [14 empty] | AC
|  | Structures & Facilities | [5 empty] | b) | Imboy | [14 empty] | AC
[8 empty] | c) | PEO | [14 empty] | AC
|  | 4.) Const. of Multi-Purpose Bldg. Magsaysay, Carmen |  |  | Court |  | - | a) | 500000 | a) | 03/05/16 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For cancellation since the project was already undertaken by Davao Light & no back up cash since it is part of the loan with LBP |  | 2
[8 empty] | b) | CY 2015 | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | PEO | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | 5.) Improvement of Covered Court |  |  | Court |  | - | a) | 500000 | a) | 03/05/16 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For cancellation since the project was already undertaken by Davao Light & no back up cash since it is part of the loan with LBP |  | 2
|  | Brgy. San Isidro, Carmen | [5 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | PEO | c) | - | g) | - | c) | [9 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | 6.) Construction of 1 Bay Covered Court |  |  | Court |  | - | a) | 500000 | a) | 03/08/16 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For cancellation since the project was already undertaken by Davao Light & no back up cash since it is part of the loan with LBP |  | 2
|  | Brgy. Bobongon, Sto. Tomas | [5 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | PEO | c) | - | g) | - | c) | [9 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | 7.) Construction of Multi-Purpose Building |  |  | Bldg. |  |  | a) | 500000 | a) | 03/05/16 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For cancellation since the project was already undertaken by Davao Light & no back up cash since it is part of the loan with LBP |  | 2
|  | Brgy. New Visayas, Sto. Tomas |  |  |  |  | - | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | PEO | c) | - | g) | - | c) | [9 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | 8.) Improvement of Brgy. Hall |  |  | Bldg. |  |  | a) | 500000 | a) | 03/05/16 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For cancellation since the project was already undertaken by Davao Light & no back up cash since it is part of the loan with LBP |  | 2
|  | Brgy. Tulalian, Sto. Tomas |  |  |  |  | - | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | PEO | c) | - | g) | - | c) | [9 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | 9.) Construction of Market Stall |  |  | Market |  |  | a) | 500000 | a) | 03/05/16 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For cancellation since the project was already undertaken by Davao Light & no back up cash since it is part of the loan with LBP |  | 2
|  | Brgy. La Libertad, Sto. Tomas |  |  | Stall |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[7 empty] | - | c) | PEO | c) | - | g) | - | c) | [9 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | 10.) Const. of Covered Court Bleacher w/ Roofing |  |  | Court |  |  | a) | 500000 | a) | 03/05/16 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For cancellation since the project was already undertaken by Davao Light & no back up cash since it is part of the loan with LBP |  | 2
|  | Brgy. Cabay-angan, B.E. Dujali |  |  |  |  | - | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | PEO | c) | - | g) | - | c) | [9 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
| C. | Trust Fund | [21 empty] | FS
|  | 1. PRDP | [21 empty] | AC
|  | 1.1 Rehab. of Esperanza-Pob. Sto. Tomas, |  |  | Road | 12.774 | Contract. | a) | 117,410,426.30 | a) | CY 2014 | e) | - | a) | 117,410,426.30 | a) | 100% | c) | 89.82% | a) | 20 | On-going . Request for time extension on process. Waiting for approval of variation order for billing |  | 2
|  | FMR, DDN | [5 empty] | b) | Palero | b) | 03/22/17 | f) | - | b) | 117,410,426.30 | b) | 96% | d) | -6.179% | b) | 600 |  |  | 2
[8 empty] | c) | Alzam | c) | 07/22/19 | g) | - | c) | 113,335,769.31 | [8 empty] | 2
[8 empty] | d) | 853 CD | d) | - | [12 empty] | 2
|  | 1.2 Construction of Dalisay Potable Water System |  |  | Water | - | Contract. | a) | 4664033.76 | a) | CY 2014 | e) | - | a) | 4664033.76 | a) | 100.00% | c) | 82.88% | a) | - | for resumption |  | 2
[5 empty] | System |  |  | b) | Estorco | b) | 01/29/18 | f) | 39 CD | b) | 4664033.76 | b) | 87.94% | d) | -5.06% | b) | - |  |  | 2
[8 empty] | c) | Ancor Water Resources | c) | 07/23/18 | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | 188 CD | d) | 08/31/18 | [12 empty] | 2
|  | 1.3. Construction of Kasilak Potable Water System |  |  | Water | - | Contract. | a) | 7046856.27 | a) | CY 2014 | e) | 72 CD | a) | 7046856.27 | a) | 100.00% | c) | 87.38% | a) | - | for resumption |  | 2
[5 empty] | System |  |  | b) | Estorco | b) | 01/29/18 | f) | - | b) | 7046856.27 | b) | 83.53% | d) | +3.850% | b) | - |  |  | 2
[8 empty] | c) | Ancor Water Resources | c) | 09/24/18 | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | 188 CD | d) | 12/05/18 | [12 empty] | 2
2
|  | 1.4. Improvement of Sto. Tomas Production Center with Common Facility |  |  | Building |  | Contract. | a) | 9825000 | a) | CY 2014 | e) | 72 CD | a) |  | a) |  | c) |  | a) |  | Suspended due to land issue |  | 2
[8 empty] | b) | Azotes | b) | 01/29/18 | f) | - | b) |  | b) |  | d) |  | b) |  |  |  | 2
[8 empty] | c) | Manantan | c) | 09/24/18 | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | 330 C.D | d) | 12/05/18 | [12 empty] | 2
2
|  | SLRF 2015 | [7 empty] | a) |  | e) | 65 days | a) |  | a) | 100% | c) | 100% | a) | 3 | Completed as per POW, Financial Documents on Process |  | 2
|  | Rehab. of Jct. Highway-Tuganay-Anibongan-BE Dujali-Kinamayan Provincial Road (Furtheranace) |  |  | Slope protection | - | - | a) | 1911175.99 | b) | 2019-02-18 | f) | 47 days | b) |  | b) |  | d) | 0% | b) | 60 |  |  | 2
[8 empty] | b) | Balbastro | c) | 2019-09-21 | g) | 9/21/2019 | c) | [9 empty] | 2
[8 empty] | c) | Admin | d) | [13 empty] | 2
[8 empty] | d) | - | [14 empty] | 2
| D. | 20% Development Fund CY 2016 | [21 empty] | FS
|  | 1. Water System Development Projects |  |  | Water |  | Admin | a) | 2000000 | [12 empty] | See project listed below |  | AC
|  | (Provincewide) |  |  | System |  |  | b) | - | [14 empty] | AC
[8 empty] | c) | PEO | [14 empty] | AC
|  | b. | Development of Deepwell Source and Install. Of |  | Water |  | Admin | a) | 645,000.00 | a) | 11/08/18 | e) | - | a) | 645,000.00 | a) | 82.76% | c) | 72.89% | a) | 4 | drilling works completed 7/15/2019 but insufficient water source |  | 2
|  |  | Pipelines, Licup, samal Dist. IGACOS |  | System |  |  | b) | Diosanta | b) | 03/01/19 | f) | - | b) | 645,000.00 | b) | - | d) | -9.87% | b) | 100 |  |  | 2
|  |  | (Previously Deepwell Drilling at Licup) |  |  |  |  | c) | PEO | c) | 05/10/19 | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | 2. Rural Electrification (Provincewide) |  |  | Elect. |  | Admin | a) | 5000000 | [12 empty] | See projects listed below |  | AC
[8 empty] | b) | Foronda/Ababon | [14 empty] | AC
[8 empty] | c) | Admin | [14 empty] | AC
[8 empty] | d) | - | [14 empty] | AC
|  | 2.1 | Inst. of transformer and accessories, |  | Elect. |  | Admin | a) | 150,000.00 | a) | 07/31/18 | e) | - | a) | 150,000.00 | a) | - | c) | - | a) | - | For PR - c/o Engr Kim Pao Lu |  | 2
|  |  | Brgy. Kinawitnon |  |  |  |  | b) | - | b) | - | f) | - | b) | 150,000.00 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | 2.2 | Electrification expansion to Purok 7, |  | Elect. |  | Admin | a) | 1,537,404.57 | a) | 02/04/19 | e) | - | a) | 1,537,404.57 | a) | - | c) | - | a) | - | Waiting for NTP - c/o Engr Kim Pao Lu |  | 2
|  |  | Brgy. Guilon, samal Dist. IGCS |  |  |  |  | b) | - | b) | - | f) | - | b) | 1,537,404.57 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | 2.3 | Rural Electrification at brgy. Sta. Cruz, |  | Elect. |  | Contract | a) | 2000000 | a) | - | e) | - | a) | 2000000 | a) | - | c) | - | a) | - | Delay due to action of Daneco for staking. c/o Engr. Kim |  | 2
|  |  | talikud, Samal |  |  |  |  | b) | - | b) | - | f) | - | b) | 2000000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | Admin | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | 3. Const./Rehab./Comp. of Various Gov't. Bldgs. |  |  | Bldgs./ | - | Admin | a) | 9,000,000.00 | [12 empty] | See project listed below |  | AC
|  | Struct., Fac. (Provincewide) |  |  | Fence |  |  | b) | Foronda/Ababon | [14 empty] | AC
[8 empty] | c) | PEO | [14 empty] | AC
|  | 2.1 | Construction of Provincial Training Center |  | Fence |  | Admin | a) | 940,000.00 | a) | 09/19/17 | e) | - | a) | 940,000.00 | a) | 68.00% | c) | 75.00% | a) | - | Temporarily suspended 4/23/18 due to undemolished structures of illegal settlers |  | 2
|  |  | Compound Fence, Kinawitnon, Babak |  |  |  |  | b) | Pacquiao | b) | 03/12/18 | f) | - | b) | 940,000.00 | b) | - | d) | - | b) | - |  |  | 2
|  |  | District, IGCS |  |  |  |  | c) | PEO | c) | 06/19/18 | g) | - | c) | 933,418.80 | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
| A.4 | 20% Development Fund CY 2017 | [21 empty] | FS
|  | STIMULUS PROJECTS CY 2017 | [21 empty] | FS
|  | ASUNCION | [21 empty] | FS
|  | 1 | Construction of Water Reservoir & |  | Water |  | MEO | a) | 500000 | a) | 12/28/17 | e) | - | a) | 500000 | a) | 90.00% | c) | 90.00% | a) | - | Suspended due to non availability of water source during drilling.Find another location. Fund already transferred at Municipality of Asuncion with ChecK No. 2445174 and OR # 9238468, |  | 1
| 1 |  | Purchase of P.E. Pipelines, Sagayen, |  | System |  |  | b) | - | b) | 11/15/18 | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
|  |  | Asuncion |  |  |  |  | c) | MEO | c) | - | g) | - | c) | - | [8 empty] | 1 | 1 | Asuncion | Red
[8 empty] | d) | - | d) | - | [12 empty] | 1 | 2 | B.E. Dujali | Yellow
|  | NEW CORELLA | [21 empty] | FS | 3 | Carmen | Blue
| 5 | 1 | Road Rehabilitation at Prk. 1-Prk. 5, |  | Road |  | MEO | a) | 500000 | a) | 11/29/17 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Fund already transferred at Municipality of New Corella with ChecK No. 2445213 and OR # 8592072, dated March 13, 2018. Waiting for availability of Bulldozer |  | 1 | 4 | Kapalong | Pink
|  |  | Sta. Fe, New Corella |  |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1 | 5 | New Corella | Gray
[8 empty] | c) | MEO | c) | - | g) | - | c) | - | [8 empty] | 1 | 6 | San Isidro | Orange
[8 empty] | d) | - | d) | - | [12 empty] | 1 | 7 | Sto Tomas | Sky Blue
|  | TAGUM CITY | [21 empty] | FS | 8 | Talaingod | Violet
| 11 | 1 | Construction of Multi-Purpose GYM at |  | Bldg. |  | - | a) | 500000 | a) | 11/29/17 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For AIP amendment due to change of priority.Last priority recommended was Const. of Drainage (Box Culvert) at Purok Sampaguita but funded and implemented by the City of Tagum.Waiting for new project priority |  | 1 | 9 | Panabo City | Brown
|  |  | Mangga E/S, Visayan Village, Tagum City |  |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1 | 10 | IGACOS | Yellow Green
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1 | 11 | Tagum City | Green
[8 empty] | d) | - | d) | - | [12 empty] | 1
|  | KAPALONG | [21 empty] | FS
| 4 | 1 | Impv't. of Brgy. Hall, Sua-on, Kapalong |  | Bldg. |  | - | a) | 500000 | a) | 02/13/18 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For AIP Amendment |  | 1
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| 4 | 2 | Construction of Solar Drier, Semong, |  | Solar |  | - | a) | 500,000.00 | a) | 12/28/17 | e) | - | a) | 500,000.00 | a) | - | c) | - | a) | - | For AIP Amendment |  | 1
|  |  | Kapalong |  | Drier |  |  | b) | - | b) | - | f) | - | b) | 500,000.00 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| 4 | 3 | Construction of Multi-Purpose Pavement, |  | MPP |  | - | a) | 500000 | a) | 12/28/17 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For AIP Amendment |  | 1
|  |  | Florida, Kapalong |  |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| 4 | 4 | Construction of Concrete Bleacher, |  | Bleacher |  | - | a) | 500000 | a) | 12/07/17 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For AIP Amendment |  | 1
|  |  | Tiburcia, Kapalong |  |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
| 4 | 5 | Mainline Pipes for PWS, Mabantao, |  | Water |  | - | a) | 500000 | a) | 12/07/17 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | To change priority but not yet submitted new resolution c/o Engr. Amamio. Note: Previous project was funded by LGU |  | 1
|  |  | kapalong |  | System |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| 4 | 6 | Impv't. of Covered Court, Pag-Asa, |  | Court |  | - | a) | 500000 | a) | 12/07/17 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For AIP Amendment |  | 1
|  |  | Kapalong |  |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| 4 | 7 | Covered Court Bleacher, Katipunan, |  | Bleacher |  | - | a) | 500000 | a) | 12/07/17 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For AIP Amendment |  | 1
|  |  | Kapalong |  |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| 4 | 8 | Improvement of Gabuyan Covered Court, |  | Court |  | Admin | a) | 500000 | a) | 12/07/17 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For AIP Amendment |  | 1
|  |  | Brgy. Gabuyan, Kapalong |  |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | PEO | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| A.4 | 20% Development Fund CY 2017 | [21 empty] | FS
| 4 | 9 | Ground Development and Landscape |  | Fence |  | Admin | a) | 1000000 | a) | ,11/4/2019 | e) | - | a) | 1000000 | a) | - | c) | 21.38 | a) | - | On-going |  | 1
[8 empty] | b) | - | b) | 01/31/2020 | f) | - | b) | 1000000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | PEO | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | 89 CD | d) | - | [12 empty] | 1
|  | TALAINGOD | [21 empty] | FS
| 8 | 1 | Const. of Covered Court Bleacher. |  | Elect. |  | Barangay | a) | 500000 | a) | 12/28/17 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Fund already transferred at Municipality of Talaingod with ChecK No. 2445181 and OR # 7955667, dated March 16, 2018 . Amended from Electrification @ Prk. 1A-Prk. 5A |  | 1
|  |  | Palma Gil, Talaingod |  |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) |  | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
|  | CARMEN | [19 empty] | declared as savings, forwarded to 2020 priority list of projects |  | AC
|  | 1 | Construction of Concrete Pavement |  | Pavement |  | Barangay | a) | 500000 | a) | 03/16/18 | e) | - | a) | 500000 | a) | - | c) | - | a) | - |  |  | 2
|  |  | Tibulao, Carmen |  |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | 2 | Construction of Evaluation Center at Prk. 1, |  | Bldg. |  | Barangay | a) | 500000 | a) | 12/28/17 | e) | - | a) | 500000 | a) | - | c) | 100% | a) | - | Completed |  | 2
|  |  | Asuncion, Carmen |  |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | 5 | Evacuation Center, Anibongan, Carmen |  | Bldg. |  | Barangay | a) | 500000 | a) | 03/16/18 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | declared as savings, forwarded to 2020 priority list of projects |  | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | 7 | Const. of Canal Lining @ Brgy. Site, |  | Canal |  | - | a) | 500000 | a) | 03/16/18 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | declared as savings, forwarded to 2020 priority list of projects |  | 2
|  |  | Tubod, Carmen |  | Lining |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | 9 | Rehab./Impv't. of Minda Brgy. Hall, |  | Bldg. |  | Barangay | a) | 500000 | a) | 05/10/18 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | declared as savings, forwarded to 2020 priority list of projects |  | 2
|  |  | Minda, Carmen |  |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | PANABO CITY | [21 empty] | AC
|  | 1 | Const of Market Stall/Building, Consolacion, |  | Bldg. |  | Barangay | a) | 500000 | a) | 12/28/17 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Fund transfer to LGU- 3/28/2019 with check no.2574928 and OR no. 0166514 - Issued warning for Termination of the Contract |  | 2
|  |  | Panabo CIty |  |  |  |  | b) | - | b) | 5/28/2019 | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | 2 | Rehab. Of Multi-Purpose Hall (Covered Court), |  | Footbridge |  | Barangay | a) | 500000 | a) | 12/28/17 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Fund transfer to LGU- 3/28/2019 with check no.2574927 and OR no. 0166516 - Delivery of Materials on process |  | 2
|  |  | Upper Licanan, Panabo City |  |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | 5 | Impv't. of Multi-Purpose Gym, Kauswagan, |  | GYM |  | Barangay | a) | 500000 | a) | 02/04/19 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Fund transfer to LGU- 3/28/2019 with check no.2574942 and OR no. 0166515 - procurement on process for bidding 8/5/2019 |  | 2
|  |  | Panabo CIty |  |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | 9 | Const. of MP Bldg. w/ Electrical installation, |  | Bldg. |  | Barangay | a) | 500000 | a) | 01/31/18 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Fund transfer to LGU- 3/28/2019 with check no. 2574942 and OR no 01665515 - procurement on process |  | 2
|  |  | San Roque, Panabo City |  |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | 14 | Const. of Multi-Purpose Bldg. (Back Stage/Office), San Nicolas, |  | Bldg. |  | Barangay | a) | 500000 | a) | 12/28/17 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Completed based on POW. Financial Documents on process |  | 2
|  |  | San Nicolas, Panabo City |  |  |  |  | b) | - | b) | 5/21/2019 | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | 16 | Const. of Multi-Purpose Bldg., |  | Bldg. |  | Barangay | a) | 300000 | a) | 12/19/17 | e) | - | a) | 300000 | a) | - | c) | - | a) | - | Issued warning for termination of the contract |  | 2
|  |  | Cacao, Panabo City |  |  |  |  | b) | - | b) | 12/14/2018 | f) | - | b) | 300000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | 17 | Const. of Multi-Purpose Bldg. @ A.O. Floriendo |  | Bldg. |  | Barangay | a) | 500000 | a) | 12/19/17 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Fund transfer to LGU- 3/28/2019 with check no. 2574939 and OR no. 0166518 - Materials Delivered. Construction on-going |  | 2
|  |  | National Highschool, Panabo City |  |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | STO. TOMAS | [21 empty] | AC
|  | 1 | Renov. Of Brgy. Hall, Esperanza, |  | Bldg. |  | - | a) | 500000 | a) | 12/28/17 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | declared as savings, forwarded to 2020 priority list of projects |  | 2
|  |  | Panabo City |  |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | 2 | Const. of Concrete Drainage Canal, Kimamon, |  | Drainage |  | Barangay | a) | 500000 | a) | 12/19/17 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | on-going |  | 2
|  |  | Panabo City |  |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | IGACOS | [21 empty] | AC
|  | 1 | Electrification of Prk. 4 & 6, Brgy. Toril, IGCS |  | Elect. |  |  | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | No abstract |  | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | PEO | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | 2 | Impv't. of Brgy. Street Electrification at |  | Elect. |  |  | a) | 500000 | a) | 11/28/17 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Verified at PBO 7/18/2019 that fund is not available. Proposed priority project for 2020\ |  | 2
|  |  | Brgy. Anonang, IGCS |  |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | PEO | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | 3 | Impv't of Brgy. Hall, Tagpopongan |  |  |  |  | a) | 500000 | a) | 11/28/17 | e) | 259 | a) | 500000 | a) | - | c) | 100% | a) | - | Completed based on POW. Financial Documents on process |  | 2
|  |  | IGACOS |  |  |  |  | b) | Roque | b) | 9/17/2018 | f) | 30 | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | PEO | c) | 12/30/2018 | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | 10/15/2019 | [12 empty] | 2
| F. | SDH IGCS - CONST. IN PROGRESS - BLGS. CY 2017 | [21 empty] | AC
|  | 1 | Construction Perimeter Fence Ph.II (Hospital |  | Fence |  | Admin | a) | 1,305,000.00 | a) | 11/10/17 | e) | 392 | a) | 1,305,000.00 | a) | 100% | c) | 100% | a) | 4 | Completed based on POW. Financial Documents on process |  | AC
|  |  | Compound) Samal District Hospital, IGCS |  |  |  |  | b) | Porras | b) | 03/12/18 | f) | 45 | b) | 1,305,000.00 | b) | - | d) | 1% | b) | 30 |  |  | AC
[8 empty] | c) | PEO | c) | 06/19/18 | g) | - | c) | 958,597.98 | [8 empty] | AC
[8 empty] | d) | - | d) | [13 empty] | AC
|  | 2. Const./Rehab./Comp. of Various Gov't. Bldgs. |  |  | Bldg. | - | Admin | a) | 9,000,000.00 | [12 empty] | Investigation/Inspection of priority projects |  | 2
|  | Struct., Fac. (Provincewide) | [5 empty] | b) | Foronda/Ababon | [14 empty] | AC
[8 empty] | c) | PEO | [14 empty] | AC
[8 empty] | d) | - | [14 empty] | AC
| 11 | 2.1 | Rehab. Of PEO Training Center |  | Bldg. |  | Admin | a) | 476,876.00 | a) | 02/12/19 | e) | - | a) | 476,876.00 | a) | 22.82% | c) | 22.82% | a) | 8 | On-going |  | 1
|  |  | (PDPM),Mankilam, Tagum City |  |  |  |  | b) | Chua | b) | 2019-04-11 | f) | - | b) | 476,876.00 | b) | - | d) | 0% | b) | - |  |  | 1
|  |  | (Part of P803,000.00)(20% DF CY 2018-P326,124.00) |  |  |  |  | c) | PEO | c) | 01/17/19 | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
|  | 2.2 | Repair/Rehab. Of PEO Building |  | Bldg. |  | Admin | a) | 1,800,000.00 | a) | 07/31/18 | e) | - | a) | 1,800,000.00 | a) | 62.23% | c) | 100% | a) | 5 | Completed based on POW. Financial Documents on process |  | 1
| 11 |  | (Motorpool),Mankilam, Tagum City |  |  |  |  | b) | Chua | b) | 03/04/19 | f) | - | b) | 1,800,000.00 | b) | - | d) | 37.77% | b) | 105 |  |  | 1
[8 empty] | c) | PEO | c) | 08/10/19 | g) | - | c) | 1481510.07 | [8 empty] | 1
[8 empty] | d) | 160 CD | d) | - | [12 empty] | 1
|  | 2.3 | Improvement of Garciaville Day Care |  | Bldg. |  | Admin | a) | 330,000.00 | a) | 11/06/18 | e) | - | a) | 330,000.00 | a) |  | c) | 100% | a) | 3 | Completed based on POW. Financial Documents on process |  | 1
| 11 |  | Center, Mankilam, Tagum City |  |  |  |  | b) | - | b) | 09/02/19 | f) | - | b) | 330,000.00 | b) | - | d) |  | b) | 90 |  |  | 1
[8 empty] | c) | PEO | c) | 10/11/19 | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
|  | 3. Rural Electrification (Provincewide) |  |  | Elect. |  | - | a) | 5000000 | [12 empty] | See projects listed below |  | AC
[8 empty] | b) | Foronda | [14 empty] | AC
[8 empty] | c) | - | [14 empty] | AC
[8 empty] | d) | - | [14 empty] | AC
|  | 3.1 | Electrification of Purok 1-4, Sta. Cruz, |  | Elect. |  | Admin | a) | 2,500,000.00 | a) | 02/04/19 | e) | - | a) | 2,500,000.00 | a) | 10% | c) | 12% | a) | - | On-going |  | 1
| 5 |  | New Corella |  |  |  |  | b) | - | b) | - | f) | - | b) | 2,500,000.00 | b) | - | d) | 2% | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| B.3 | Supplemental Budget # 4 CY 2017 | [21 empty] | FS
| 11 | 1 | Upgrading of DDNSTC (Basketball/Voleyball |  | Covered | 2252.69 sq.m | Contract | a) | 99992356.64 | a) | 10/16/18 | e) | - | a) | 99992356.64 | a) | 100% | c) | 72.6% | a) | 5 | On-going |  | 1
|  |  | MP Covered Court),Sports Center, Mankilam, |  | Court |  |  | b) | Escurzon | b) | 07/17/18 | f) | 20 CD | b) | 99992356.64 | b) | - | d) | -27.4% | b) | 150 |  |  | 1
|  |  | Tagum City |  |  |  |  | c) | YBC | c) | 07/11/19 | g) | - | c) | 18, 280, 402.33 | [8 empty] | 1
[8 empty] | d) | 360 CD | d) | 07/31/19 | [12 empty] | 1
| C.1 | Trust Fund 2014 | [21 empty] | FS
|  | 1. PAMANA-DILG CY 2014 | [21 empty] | AC
| 4 | 1.1 Construction of Biga Bridges, Kapalong |  |  | Road | 2-18ln.m | Contract | a) | 24959503.45 | a) | CY 2014 | e) | 304 CD | a) | 24959503.45 | a) | 100.00% | c) | 85.37% | a) | 8 | On-going |  | 1
[8 empty] | b) | Limpo | b) | 07/01/16 | f) | - | b) | 24959503.45 | b) | 99.7% | d) | -14.33% | b) | 290 |  |  | 1
[8 empty] | c) | Dvo. Rock Mixer | c) | 07/30/18 | g) | - | c) | 37,439,255.18 | [6 empty] | Issued warning letter & submit catch-up plan |  | 1
[8 empty] | d) | 880 CD | d) | 09/27/19 | [12 empty] | 1
| 4 | 1.2 Road Rehabilitation/Improvement of Prk. 3, |  |  | Road | 13.60 kms | Contract | a) | 50,500,288.95 | a) | CY 2014 | e) | - | a) | 50,500,288.95 | a) | 100.00% | c) | 100% | a) | 25 | Completed based on Physical Accomplishment. Financial Document on process |  | 1
|  | Palma Gil-Prk.2 (side 2), Sto. Niño-Mahayahay-Tugas- | [5 empty] | b) | Dadula | b) | 07/07/16 | f) | 398 CD | b) | 50,500,288.95 | b) | 100% | d) | 0% | b) | 750 |  |  | 1
|  | Nanaga Road, with 1 -unit, 40 ln.m PSCG Bridge, |  |  |  | 40 ln.m |  | c) | Puregold | c) | 03/12/18 | g) | - | c) | 41424313.06 | [8 empty] | 1
|  | Kapalong | [5 empty] | d) | 1011 CD | d) | 04/14/19 | [12 empty] | 1
| C.2 | Trust Fund 2015 | [21 empty] | FS
|  | 1. PRDP CY 2015 | [21 empty] | AC
| 4 | 1.1 Rehab. Of Capungagan-Boundary San |  |  | Road | 10.6 kms. | Contract. | a) | 108,303,841.70 | a) | CY 2015 | e) | 140 CD | a) | 108,303,841.70 | a) | 100.00% | c) | 93.23% | a) | 38 | On-going |  | 1
|  | Miguel FMR, Kapalong, Davao del Norte | [5 empty] | b) | Nasol | b) | 04/06/16 | f) | 634 | b) | 108,303,841.70 | b) | 96.05% | d) | -2.82% | b) | 1140 | Increase of Project Cost due to Variation Order with |  | 1
[8 empty] | c) | VICLAO | c) | 03/26/17 | g) | - | c) | 38,212,432.90 | [6 empty] | Extra Work. (Php 4,992,591.29) |  | 1
[8 empty] | d) | 1352 | d) | 12/18/2019 | [12 empty] | 1
| 5 | 1.2 Rehab. Of Pob.-Limbaan-Suawon-Macgum |  |  | Road | 15.01 kms./ | Contract. | a) | 205,202,114.16 | a) | CY 2015 | e) | 229 CD | a) | 205,202,114.16 | a) | 100.00% | c) | 71.41% | a) | 40 | On-going |  | 1
|  | FMR w/ Bridge, New Corella, Davao del Norte |  |  |  | 42 ln.m |  | b) | Madrigal | b) | 04/08/16 | f) | 490 CD | b) | 205,202,114.16 | b) | 82.51% | d) | -11.1% | b) | 1200 | Increase of Project Cost due to Variation Order Php 14,948,622.18 |  | 1
[8 empty] | c) | Dvo. Rock Mixer | c) | 01/18/19 | g) | - | c) | 28538091.3 | [8 empty] | 1
[8 empty] | d) | 1529CD | d) | 06/14/20 | [10 empty] | Partial suspension due to soft soil from sta. 8+000 - 10+000 |  | 1
| 1 | 1.3 Rehab. Of Sonlon - Camansa FMR |  |  | Road |  | Contract. | a) | 215125015.81 | a) | 9/18/2018 | e) |  | a) | 215125015.81 | a) | 24.63% | c) | 23% | a) | 30 | On-going |  | 1
|  | Asuncion, Davao del Norte | [5 empty] | b) | Fabiala | b) | 5/28/2019 | f) |  | b) | 215125015.81 | b) |  | d) | -1.63% | b) | 780 |  |  | 1
[8 empty] | c) | Three w/Builders, Inc? Davao Rock Mixer Enterprises (JV) | c) | 12/31/2020 | g) | - | c) | [9 empty] | 1
[8 empty] | d) | 1529CD | d) | 06/14/20 | [12 empty] | 1
|  | 2. KALSADA CY 2015 | [21 empty] | AC
| 6 | 2.1 Improvement of Km. 9 Sagayen-Sawata Provincial |  |  | Road | 3177 ln.m m | Contract | a) | 47213478.31 | a) | CY 2015 | d) | - | a) | 47213478.31 | a) | 100.00% | c) | 37.556% | a) |  | Contract Terminated |  | 1
|  | San Isidro, Davao del Norte | [5 empty] | b) | Limpo | b) | 08/26/16 | e) |  | b) | 47213478.31 | b) | 86.25% | d) | -48.69% | b) |  |  |  | 1
[8 empty] | c) | Arn Builders | c) | 04/21/18 | f) | - | c) | 24931805.19 | [8 empty] | 1
[8 empty] | d) |  | d) | [13 empty] | 1
| 6 | 2.2 Improvement of Km. 9 Sagayen-Sawata Provincial |  |  | Road | 6667.54 m | Admin | a) | 33401544.78 | a) | CY 2015 | d) | - | a) | 33401544.78 | a) | 51.85% | c) | 94.66% | a) | 30 | Original contract terminated due to very poor performance |  | 1
|  | San Isidro, Davao del Norte | [5 empty] | b) | Limpo | b) | 10/16/18 | e) |  | b) | 33401544.78 | b) | 95.76% | d) | -8.05% | b) | 900 | of the contractor.The contract cost P 47,213,478.31. |  | 1
[8 empty] | c) | PEO | c) | 09/14/19 | f) | - | c) | 19,943,597.92 | [6 empty] | On-going |  | 1
[8 empty] | d) | 334 CD | d) | [13 empty] | 1
| C.3 | Trust Fund 2016 | [21 empty] | FS
|  | 1. PRDP CY 2016 | [21 empty] | AC
| 4 | 1.1 | Cacao Production and Beans Marketing, |  | Bldg. | - | Contract. | a) | 5873626.8 | a) | CY 2016 | e) | - | a) | 5873626.8 | a) | 90.86% | c) | 84.06% | a) | 9 | On-going |  | 1
|  |  | Capungagan, Kapalong, Davao del Norte |  |  |  |  | b) | Delos Reyes | b) | 03/19/19 | f) | - | b) | 5873626.8 | b) | - | d) | -6.798% | b) | 63 | Suspension Letter on process due to |  | 1
[8 empty] | c) | MICAH CONST. & SUPPLY | c) | 11/23/19 | g) | - | c) | - | [6 empty] | modification of Detailed Design of |  | 1
[8 empty] | d) | 250 CD | d) | - | [10 empty] | mechanical Drier |  | 1
| C.4 | Trust Fund 2017 | [21 empty] | FS
|  | 1. CMGP (Conditional Matching Grant to Provinces) | [21 empty] | AC
| 6 |  | Road Upgrading km.9 sagayen-Sawata |  | Road | 10.20 km | Contract | a) | 139,761,975.14 | a) | CY 2017 | e) | - | a) | 139,761,975.14 | a) | 93.839 | c) | 93.27 | a) | 28 | On-going |  | 1
|  |  | (Sagayen-Jct. San Miguel Section) |  |  |  |  | b) | Avila | b) | 10/01/18 | f) | - | b) | 139,761,975.14 | b) | - | d) | -0.569 | b) | 11170 |  |  | 1
[8 empty] | c) | Legacy Const. Corp. | c) | 08/22/19 | g) | - | c) | 63100753.7 | [8 empty] | 1
[8 empty] | d) | 326 CD | d) | - | [12 empty] | 1
| 8 |  | Road Upgrading of Dagohoy - Daligdigon |  | Road | 2.532 km | Contract | a) | 58048310.68 | a) | CY 2017 | e) | - | a) | 58048310.68 | a) | 100.00% | c) | 100% | a) | 16 | Completed as per Physical Accomplishment, Financial Documents on Process |  | 1 | 1
|  |  | Provincial Road |  |  |  |  | b) | Fabiala | b) | 01/05/18 | f) | 205 CD | b) | 58048310.68 | b) | - | d) | 0% | b) | 480 |  |  | 1
[8 empty] | c) | PUREGOLD | c) | 11/18/18 | g) | - | c) | 29,572,637.70 | [8 empty] | 1
[8 empty] | d) | 246 CD | d) | 03/31/19 | [12 empty] | 1
|  |  | Impv’t. of Maligaya-New Camiling Prov’l. |  | Conc. | 2.13 km | Contract. | a) | 50101614.08 | a) | CY 2017 | e) | 76 CD | a) | 57385680 | a) | 100.00% | c) | 100% | a) | 21 | Completed based on POW. Financial Documents on process |  | 2
|  |  | Road w/ Bridge Component,Carmen |  |  |  |  | b) | Mellomida | b) | 12/18/17 | f) | 209 CD | b) | 57385680 | b) | 100% | d) | 0% | b) | 147 |  |  | 2
[8 empty] | c) | PUREGOLD CONST. | c) | 02/15/19 | g) | - | c) | 36005452 | [8 empty] | 2
[8 empty] | d) | 376 CD | d) | 07/31/19 | [12 empty] | 2
|  |  | Road Upgrading of FDR. Rd.3 – |  | Conc. | 10.359 km | Contract. | a) | 119901954.82 | a) | CY 2017 | e) | 47 CD | a) | 119901954.82 | a) | 100.00% | c) | 100% | a) | 10 | Completed based on POW, Financial Documents on Process |  | 2
|  |  | Kimamon – Luna Provincial Road, |  |  |  |  | b) | Comidoy | a) | 12/29/17 | f) | 198 CD | b) | 119901954.82 | b) | 100% | d) | 100% | b) | 220 |  |  | 2
|  |  | Sto. Tomas |  |  |  |  | c) | GP & H CONST. | c) | 12/12/18 | g) | - | c) | 119901954.82 | [8 empty] | 2
[8 empty] | d) | 326 CD | d) | 2019-07-29 | [12 empty] | 2
|  |  | Road Upgrading of Anahaw-Maligaya |  | Conc. | 5.18 km | Contract. | a) | 78,228,121.56 | a) | CY 2017 | e) | - | a) | 78,228,121.56 | a) | 100.00% | c) | 100% | a) | 30 | 100% as of August 31, 2019 |  | 2
|  |  | Provincial Road, Carmen |  |  |  |  | b) | Fernandez | b) | 12/24/17 | f) | 306 CD | b) | 78,228,121.56 | b) | 100% | d) | 0% | b) | 660 | Subject for liquidated damages |  | 2
[8 empty] | c) | MONOLITHIC CONST. | c) | 03/31/19 | g) | - | c) | 76,214,361.38 | [8 empty] | 2
[8 empty] | d) | 210 CD | d) | 2019-06-05 | [12 empty] | 2
|  | 2. OPPAP-PAMANA | [21 empty] | AC
1
| 11 | 2.2 | Const. of Trading Post, Storage Building |  | Bldg. |  | Contract | a) | 3,975,000.00 | a) | CY 2017 | e) | - | a) | 3,975,000.00 | a) | - | c) | - | a) | - | Rebidding |  | 1
|  |  | with (1) unit Hauling Truck, Brgy. Pandapan |  |  |  |  | b) | - | b) | - | f) | - | b) | 3,975,000.00 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
|  | 2.1 | Const. of Trading Post, Storage Building |  | Bldg. |  | Contract | a) | 3,975,000.00 | a) | CY 2017 | e) | - | a) | 3,975,000.00 | a) | - | c) | - | a) | - | c/o Engr. Rickris Fernandez |  | 2
|  |  | with (1) unit Hauling Truck, Prk. Ramihan |  |  |  |  | b) | - | b) | - | f) | - | b) | 3,975,000.00 | b) | - | d) | - | b) | - |  |  | 2
|  |  | Datu Abdul, Panabo City |  |  |  |  | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | 2.2 | Construction of Tribal Hall, Sto. Tomas |  | Bldg. |  | Admin | a) | 500000 | a) | CY 2018 | e) | - | a) | 500000 | a) | 100% | c) | 89.5% | a) | 7 | Suspended 6/28/2019, Suspended due to Delivery of Materials J.O, For time extension |  | 2
[8 empty] | b) | Roque | b) | 2019-05-22 | f) | - | b) | 500000 | b) | - | d) | 0.79% | b) | 110 |  |  | 2
[8 empty] | c) | - | c) | 2019-07-31 | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
| C.5 | LDRRM - Trust Fund | [21 empty] | FS
| 5 | 1. Construction of Slope Protection and Concrete Pavement along Sta. Fe Mambing Road Section |  |  | Slope |  | Admin | a) | 1,853,000.00 | a) | 11/28/18 | e) |  | a) | 1,853,000.00 | a) | 100% | c) | 100% | a) | 16 | Completed based on POW. Financial Documents on process |  | 1
[8 empty] | b) | Gone | b) | 12/03/18 | f) | 108 CD | b) | 1,853,000.00 | b) | - | d) |  | b) | 144 |  |  | 1
[8 empty] | c) | PEO | c) | 02/28/19 | g) | 10/30/2019 | c) | 742252.72 | [8 empty] | 1
[8 empty] | d) | 86 CD | d) | 06/15/2019 | [12 empty] | 1
| 5 | 2. Rehab. Of Saug Bridge of Slope Protection |  |  | Slope |  | Admin | a) | 4,850,000.00 | a) | 05/25/18 | e) | - | a) | 4,850,000.00 | a) | 23.60% | c) | 9.60% | a) | - | Suspended dated 01/28/19 |  | 1
[8 empty] | b) | Gone | b) | 01/03/19 | f) | - | b) | 4,850,000.00 | b) |  | d) | -14% | b) | - |  |  | 1
[8 empty] | c) | PEO | c) | 03/25/19 | g) | - | c) | 1628912.92 | [8 empty] | 1
[8 empty] | d) | 82 CD | d) | - | [12 empty] | 1
| 1 | 3. Rehab. Of Canatan Bridge Slope Protection |  |  | Slope | 395 sq.m. | Contract | a) | 9200000 | a) | 06/20/2018 | e) | - | a) | 9200000 | a) | 100% | c) | 100% | a) | - | Completed |  | 1 | 1
|  | Brgy. Canatan, Asuncion | [5 empty] | b) | Aclaracion | b) | 02/11/2019 | f) | 35 CD | b) | 9200000 | b) | 100% | d) | 0% | b) | - |  |  | 1
[8 empty] | c) | J-One Builders | c) | 04/12/2019 | g) | 05/31/2019 | c) | 7222021.59 | [8 empty] | 1
[8 empty] | d) | 60 CD | d) | 05/01/2019 | [12 empty] | 1
| 4 | 4. Re-channeling of BIGA River with Earth Dike and Slope Protection, Brgy. Gupitan, Kaplaong |  |  | Dike/Slope |  | Contract | a) | 12,100,000.00 | a) | 07/20/18 | e) | - | a) | 12,100,000.00 | a) | 8.30% | c) | 3.36% | a) | 4 | Suspended dated March 25, 2019 |  | 1
[8 empty] | b) | Limpo | b) | 02/22/19 | f) | - | b) | 12,100,000.00 | b) |  | d) | -4.94% | b) | 120 | Due to boundary conflict. |  | 1
[8 empty] | c) | Alpha & Omega | c) | 06/11/19 | g) | - | c) | - | [6 empty] | Waiting for the decision from the Bureau of Land |  | 1
[8 empty] | d) | 110 CD | d) | 9/23/2019 | [12 empty] | 1
| 5 | 5. Const. of Cabidianan Bridge Slope Protection, Brgy. Cabidianan, New Corella |  |  | Slope |  | Admin | a) | 3590000 | a) | 07/18/18 | e) | - | a) | 3590000 | a) | 100% | c) | 100% | a) | 8 | Completed based on POW. Financial Documents on process |  | 1
[8 empty] | b) | Gone | b) | 6/17/19 | f) | - | b) | 3590000 | b) |  | d) |  | b) | 80 |  |  | 1
[8 empty] | c) | PEO | c) | 8/20/19 | g) | - | c) | 1929823.4 | [8 empty] | 1
[8 empty] | d) | 65 CD | d) | - | [12 empty] | 1
| D. | SEF(Special Education Fund)-SUPPLEMENTAL BUDGET # 1 CY 2017 | [21 empty] | FS
|  | 1. Const./Impv't./Compl. Of School Bldgs., Struc. & Fac. |  |  | Bldgs. |  | Admin | a) | 3,300,000.00 | [12 empty] | See projects listed below |  | AC
[8 empty] | b) | Foronda | [14 empty] | AC
[8 empty] | c) | PEO | [14 empty] | AC
[8 empty] | d) | - | [14 empty] | AC
| 8 | 1.1 | Construction of 1 unit School Building |  | Bldg. |  | Admin | a) | 1100000 | a) | 02/19/18 | e) | - | a) | 1100000 | a) | 100 | c) | 100 | a) | 6 | Completed based on POW. Financial Documents on process |  | 1
|  |  | Lumabag, Talaingod |  |  |  |  | b) | Dadula | b) | 03/20/19 | f) | 27 CD | b) | 1100000 | b) |  | d) |  | b) | 30 |  |  | 1
[8 empty] | c) | PEO | c) | 05/19/19 | g) | 06/30/2019 | c) | 595230.5 | [8 empty] | 1
[8 empty] | d) | 60 CD | d) | - | [12 empty] | 1
F. 20% Development Fund CY 2018 | [23 empty] | FS
|  | 1. Repair & Maint. Of Various Local Roads |  |  | Road | - | Admin | a) | 5000000 | [12 empty] | See projects listed below |  | AC
|  | and Drainages | [5 empty] | b) | [15 empty] | AC
[8 empty] | c) | Admin | [14 empty] | AC
[8 empty] | d) | - | [14 empty] | AC
|  | 1.1 | Rehabilitation of Brgy. San Antonio |  | Road |  | Admin | a) | 130000 | a) | 04/13/18 | e) | - | a) | 130000 | a) | - | c) | - | a) | - | Proposed priority project for 2020 |  | 2
|  |  | Barangay Road, IGACOS |  |  |  |  | b) | Porras/Pacquiao | b) | - | f) | - | b) | 130000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | PEO | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | 1.2 | Rehabilitation of Brgy. Peñaplata Barangay |  | Road |  | Admin | a) | 139000 | a) | 04/25/18 | e) | 66 CD | a) | 139000 | a) | 100% | c) | 100 | a) | 1 | Completed 8/31/2019 |  | 2
|  |  | Road, IGACOS |  |  |  |  | b) | Porras/Pacquiao | b) | 8/16/2019 | f) | 225 CD | b) | 139000 | b) | - | d) | - | b) | 1 |  |  | 2
[8 empty] | c) | PEO | c) | 8/31/2019 | g) | - | c) | 139000 | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | 1.3 | Rehabilitation of Brgy. Adecor Barangay |  | Road |  | Admin | a) | 138000 | a) | 04/25/18 | e) | 66 CD | a) | 138000 | a) | 60.00% | c) | 60.00% | a) | - | Completed as per POW. Financial Documents on process |  | 2
|  |  | Road, IGACOS |  |  |  |  | b) | Porras/Pacquiao | b) | 10/18/18 | f) | 225 CD | b) | 138000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | PEO | c) | 10/27/19 | g) | - | c) | 111,872.00 | [8 empty] | 2
[8 empty] | d) | - | d) | 10/15/2019 | [12 empty] | 2
|  | 1.4 | Rehabilitation of Brgy. Pob. Kaputian |  | Road |  | Admin | a) | 138000 | a) | 04/25/18 | e) | - | a) | 138000 | a) | 100% | c) | 100% | a) | 4 |  |  | 2
|  |  | Barangay Road, IGACOS |  |  |  |  | b) | Porras/Pacquiao | b) | 2019-08-08 | f) | - | b) | 138000 | b) | - | d) | - | b) | 36 | Completed Sept. 22, 2019 |  | 2
[8 empty] | c) | PEO | c) | 9/22/2019 | g) | 9/22/2019 | c) | - | [8 empty] | 2
[8 empty] | d) | 6/13/19 | d) | - | [12 empty] | 2
|  | 2. Various of Water System Project (Provincewide) |  |  | Water | - | - | a) | 10000000 | [12 empty] | Investigation/Inspection of priority projects |  | AC
[5 empty] | System |  |  | b) | Foronda/Misa | [14 empty] | AC
[8 empty] | c) | PEO | [14 empty] | AC
[8 empty] | d) | - | [14 empty] | AC
|  | 2.1 | Conduct of geo-resistivity/drilling test |  | Geo- | - | - | a) | 250000 | [12 empty] | See list of projects |  | AC
|  |  | of proposed site |  | resistivity |  |  | b) | Diosanta | [14 empty] | AC
[8 empty] | c) | - | [14 empty] | AC
[8 empty] | d) | - | [14 empty] | AC
| 6 |  | 2.1.1 Const. of PWS Linao, San Isidro |  | Water | - | - | a) | 62000 | a) | - | e) | - | a) | 62000 | a) | - | c) | - | a) | - | PO approved September 2, 2019 |  | 1
[5 empty] | System |  |  | b) | - | b) | - | f) | - | b) | 62000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| 6 |  | 2.1.2 Const. of PWS Mamalian, San Isidro |  | Water | - | - | a) | 62000 | a) | - | e) | - | a) | 62000 | a) | - | c) | - | a) | - | For declaration of savings because the spring water source is not feasible for development. |  | 1
[5 empty] | System |  |  | b) | - | b) | - | f) | - | b) | 62000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| 6 |  | 2.1.3 Const. of PWS Sagayen, San Isidro |  | Water | - | - | a) | 62000 | a) | - | e) | - | a) | 62000 | a) | - | c) | - | a) | - | Waiting for the geo-resistivty equipment. |  | 1
[5 empty] | System |  |  | b) | - | b) | - | f) | - | b) | 62000 | b) | - | d) | - | b) | - | (Geo-resistivty equipment PR on process) |  | 1
[8 empty] | c) | PEO | c) | - | g) | - | c) | - | [6 empty] | Aug. 13, 2019 |  | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
|  | 2.2 | Construction of Water System Projects |  | Water | - | - | a) | 9750000 | [12 empty] | See list of projects |  | AC
|  |  | in Component LGUs |  | System |  |  | b) | Diosanta | [14 empty] | AC
[8 empty] | c) | PEO | [14 empty] | AC
[8 empty] | d) | - | [14 empty] | AC
| 11 |  | Installation of potable water System at Purok |  | Water | - | - | a) | 1125000 | a) | - | e) | - | a) | 1125000 | a) | - | c) | - | a) | - | Waiting for deed of donation. Follow-up letter was already issued |  | 1
|  |  | Nangka, Pandapan, Tagum City |  | System |  |  | b) | - | b) | - | f) | - | b) | 1125000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | PEO | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| 1 |  | Rehab./Impv't. of San Vicente |  | Water | - | - | a) | 1125000 | a) | 10/26/18 | e) | - | a) | 1125000 | a) | - | c) | - | a) | - | PO on process |  | 1
|  |  | Water System, Asuncion |  | System |  |  | b) | - | b) | - | f) | - | b) | 1125000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | PEO | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
|  |  | Impv't. of Water System, Brgy. Poblacion |  | Water |  | Admin | a) | 1250000 | a) | 08/24/18 | e) | - | a) | 1250000 | a) | 100% | c) | 85.39% | a) | 8 | Completed (contract by Zular3-Az) September 15, 2019 |  | 2
|  |  | Kaputian (Level II) |  | system |  |  | b) | Porras | b) | 05/3/19 | f) | - | b) | 1250000 | b) | - | d) | -14.61 | b) | 160 |  |  | 2
[8 empty] | c) | Contract | c) | 08/30/19 | g) | 09/15/2019 | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  |  | Water System at brgy. Malativas, |  | Water |  | Admin | a) | 1250000 | a) | - | e) | - | a) | 1250000 | a) | - | c) | - | a) | - | For preparation of POW & Plan c/o PDPM - POSSIBLE TRANSFER OF SITE SUBJECT FOR TRANSFER OF LOCATION . NO DEED OF DONATION |  | 2
|  |  | Panabo City |  | system |  |  | b) | - | b) | - | f) | - | b) | 1250000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | Admin | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  |  | Const. of Potable Water System at |  | Water |  | Admin | a) | 1250000 | a) | 11/21/18 | e) | - | a) | 1250000 | a) | - | c) | - | a) | - | for implementation |  | 2
|  |  | Brgy. Tibungol, Panabo City |  | system |  |  | b) | - | b) | - | f) | - | b) | 1250000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | Admin | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  |  | Potable Water System at Brgy. San |  | Water |  | Admin | a) | 3625000 | a) | 10/25/18 | e) | - | a) | 3625000 | a) | 49.51% | c) | 54.96% | a) | 3 | On-going |  | 2
|  |  | Remegio Kaputian (Level II WS), Samal |  | system |  |  | b) | Diosanta | b) | 7/16/2019 | f) | - | b) | 3625000 | b) | - | d) | 4.62 | b) | 20 |  |  | 2
[8 empty] | c) | Admin | c) | 12/2019 | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | 3. Counterpart to Special Projects (Provincewide) |  |  | Road | - | Contract | a) | 67415000 | [12 empty] | Investigation/Inspection of priority projects |  | AC
[8 empty] | b) | Foronda | [14 empty] | AC
[8 empty] | c) | PEO | [14 empty] | AC
[8 empty] | d) | - | [14 empty] | AC
| 1 | 3.1 | Rehab. Of Sonlon-Camansa FMR, |  | Road | - | Contract | a) | 21512501.501 | a) | 09/18/18 | e) | - | a) | 21512501.501 | a) | 9.332% | c) | 6.249% | a) | - | On-going |  | 1
|  |  | Asuncion, Davao del Norte |  |  |  |  | b) | Fabiala | b) | 5/28/2019 | f) | - | b) | 21512501.501 | b) | - | d) | -3.083% | b) | - |  |  | 1
|  |  | (PRDP Counterpart : 193,612,514.23) |  |  |  |  | c) | - | c) | 12/31/2020 | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) |  | d) | - | [12 empty] | 1
|  | 4. Const./Rehab./Comp. of Various Gov't. Bldgs. |  |  | Bldgs. | - | Admin | a) | 13523124 | [12 empty] | Investigation/Inspection of priority projects |  | AC
|  | Struct., Fac. (Provincewide) | [5 empty] | b) | Foronda | [14 empty] | AC
[8 empty] | c) | PEO | [14 empty] | AC
[8 empty] | d) | - | [14 empty] | AC
| 11 | 4.1 | Rehab. Of PEO Training Center |  | Bldg. |  | Admin | a) | 476876 | a) | 02/12/19 | e) | - | a) | 476876 | a) | - | c) | 9.17% | a) | - | On-going |  | 1
|  |  | (PDPM),Mankilam, Tagum City |  |  |  |  | b) | Chua | b) | - | f) | - | b) | 476876 | b) | - | d) | - | b) | - |  |  | 1
|  |  | (Part of P803,000.00)(20% DF CY 2017-P476,876.00) |  |  |  |  | c) | PEO | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| 1 | 4.2 | Construction of IP Tribal Council of |  | Bldg. |  | Admin | a) | 560,000.00 | a) | - | e) | - | a) | 560,000.00 | a) | - | c) | - | a) | - | POW & Plan for approval |  | 1
|  |  | Women at Brgy. Camansa, Asuncion |  |  |  |  | b) | - | b) | - | f) | - | b) | 560,000.00 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | PEO | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| 11 | 4.3 | Construction of Multi-Purpose Bldg. |  | Bldg. | 303.75 sq.m | Admin | a) | 6748000 | a) | 12/11/18 | e) | - | a) | 6748000 | a) |  | c) | 100% | a) | 25 | Completed |  | 1
|  |  | (PENRO Building), Mankilam, Tagum City |  |  |  |  | b) | Pasiona/Juan | b) | 10/16/18 | f) | 109 | b) | 6748000 | b) | - | d) |  | b) | 750 |  |  | 1
|  |  | (Part of 8,548,000.00) |  |  |  |  | c) | PEO | c) | 9/13/2019 | g) | - | c) | 6560497.45 | [8 empty] | 1
|  |  | (P1,800,000.00 - SB # 3 CY 2017) |  |  |  |  | d) | 256 CD | d) | 06/30/19 | [12 empty] | 1
| 3 | 4.4 | Repair/Rehab. Of PEO Building (2nd District), Carmen |  | Bldg. |  | Admin | a) | 2250000 | a) | 08/10/18 | e) | - | a) | 2250000 | a) | 100% | c) | 100% | a) | 18 | Completed based on POW. Financial Documents on process |  | 2
[8 empty] | b) | Andoy | b) | 02/18/19 | f) | - | b) | 2250000 | b) | - | d) | 0% | b) | 138 |  |  | 2
[8 empty] | c) | Admin | c) | 08/23/19 | g) | - | c) | 1577344.8 | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | 5. Rural Electrification (Provincewide) |  |  | Elect. |  | Admin | a) | 5000000 | [12 empty] | See projects listed below |  | AC
[8 empty] | b) | Kim Pao Lu | [14 empty] | AC
[8 empty] | c) | PEO | [14 empty] | AC
[8 empty] | d) | - | [14 empty] | AC
| 5 | 5.1 | Rural Electrification at Del Monte, |  | Elect. |  | Admin | a) | 1000000 | a) | - | e) | - | a) | 1000000 | a) | - | c) | - | a) | - | Revised POW for Approval. Change of Implementation Mode from Admin to Contract 9/6/2019 |  | 1
|  |  | New Corella |  |  |  |  | b) | - | b) | - | f) | - | b) | 1000000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| 1 | 5.2 | Const. of Distribution Line in Sitio Prk. 1,3,4, |  | Elect. |  | Admin | a) | 4000000 | a) | 11/06/18 | e) | - | a) | 4000000 | a) | - | c) | - | a) | - | For PR |  | 1
|  |  | 11 and 7, Camansa, asuncion |  |  |  |  | b) | - | b) | - | f) | - | b) | 4000000 | b) | - | d) | - | b) | - | Revised POW from Admin to Contract |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
A. 20% Development Fund CY 2018 | K. | GENERAL FUND PROPER CY 2018 | [21 empty] | FS
|  | STIMULUS PROJECTS | [21 empty] | AC
|  | ASUNCION | [21 empty] | AC
| 1 | 1 | Const. of Bleachers and Canopy, |  | Bldg. |  | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Procurement on Process |  | 1
|  |  | Canatan, Asuncion |  |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| 1 | 2 | Const. of Potable water System at Prk. 6, |  | Water |  | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Inspected – Aug. 6, 2019 For plan preparation c/o Amamio |  | 1
|  |  | New Santiago, Asuncion |  | System |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| 1 | 3 | Const. of Canopy, Camoning, Asuncion |  | Bldg. |  | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | P.O. on process |  | 1
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| 1 | 4 | Completion of Electrification at Prk. 10 |  | Elect. |  | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Proposed for future funding. Insufficient Budget to complete the project |  | 1
|  |  | & Prk. 9, Doña Andrea, Asuncion |  |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| 1 | 5 | Construction of Covered Court, |  | Court |  | - | a) | 500000 | a) | 06/05/18 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | for Fund Transfer |  | 1
|  |  | San Vicente, Asuncion |  |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| 1 | 6 | Const. Of Multi-purpose covered court Phase 2 |  | landscaping |  | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Amended from Landscaping and Beautification of Brgy. Ground to fund completion of priority project. Plan and POW for approval |  | 1
|  |  | Brgy. Ground, Pamacaun, Asuncion |  |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
|  | NEW CORELLA | [21 empty] | AC
| 5 | 1 | Const. of Concrete Bleachers, Sta. Cruz, |  | Bleacher |  | - | a) | 500000 | a) | 06/04/18 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Fund transferred to LGU - May 23, 2019 with check no. 0133011 and OR no. 9232849. On going |  | 1
|  |  | New Corella |  |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| 5 | 2 | Completion of Mini GYM at Prk. 2, |  | GYM |  | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Fund transferred to LGU - May 23, 2019 with check no. 0133010 and OR no. 9232850. On going |  | 1
|  |  | San Roque, New Corella |  |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| 5 | 3 | Completion of Covered Court, Sto. Niño, |  | Court |  | - | a) | 500000 | a) |  | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Fund transferred to LGU - May 23, 2019 with check no. 0133012 and OR no. 9232848. On going |  | 1
|  |  | New Corella |  |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| 5 | 4 | Construction of Public Market, Suawon, |  | Bldg. |  | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Fund transferred to LGU - May 23, 2019 with check no. 0133014 and OR no. 9232846. On going |  | 1
|  |  | New Corella |  |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| 5 | 5 | Construction of Concrete Line Drainage at |  | Drainage |  | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Fund transferred to LGU - May 23, 2019 with Check No. 2575058 and OR No. 0342801. On going |  | 1
|  |  | Prk. 10 to Prk. 6, Del Pilar, New Corella |  |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| 5 | 6 | Construction of Stage with Comfort Rooms |  | Bldg. |  | - | a) | 500000 | a) | 07/05/18 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Fund transferred to LGU - May 23, 2019 with check no. 0133013 and OR no. 9232847. On going |  | 1
|  |  | at Mesaoy Mini-Gym, Mesaoy, New Corella |  |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
|  | TAGUM CITY | [21 empty] | AC
| 11 | 2 | Completion of Two Storey Multi-Purpose |  | Bldg. |  | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | 100% | c) | 100% | a) | 5 | Completed based on Physical Accomplishment. Financial Documents on process |  | 1
|  |  | Building, Magugpo East, Tagum City |  |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | 0% | b) | 110 |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| 11 | 3 | Completion of GYM Bleacher w/ |  | Bleacher |  | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | for implementation |  | 1
|  |  | Electrification, Pagsabangan, Tagum City |  |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| 11 | 4 | Construction of Drainage Canal, |  | Drainage |  | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Waiting for delivery of materials |  | 1
|  |  | Libuganon, Tagum City |  |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
|  | KAPALONG | [21 empty] | AC
| 4 | 1 | Construction of Bleacher, Mamacao, |  | Bleacher |  | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Procurement of Materials on process |  | 1
|  |  | Kapalong |  |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| 4 | 2 | Improvement of Capungagan GYM Stage, |  | Stage |  | - | a) | 500000 | a) | 06/05/18 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Re-aligned to proposed project for CY 2020. |  | 1
|  |  | Capungagan, Kapalong |  |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| 4 | 3 | Construction of Concrete Perimeter Fence, |  | Fence |  | Contract | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Procurement of Materials on process |  | 1
|  |  | Luna, Kapalaong |  |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| 4 | 4 | Construction of 1 Unit 2 Classroom |  | Bldg. |  | Contract | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Needs additional funds to complete the project |  | 1
|  |  | School Bldg. at Sampao, kapalong |  |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| 4 | 5 | Completion of Brgy. Health Center, Maniki, |  | Bldg. |  | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Waiting for on-going works funded by other agency to complete. |  | 1
|  |  | Kapalong |  |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
|  | SAN ISIDRO | [21 empty] | AC
| 6 | 1 | Improvement of Water System, Sabangan, |  | Water |  | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | To change priority but not yet submitted new resolution c/o Engr. Amamio |  | 1
|  |  | San Isidro |  | System |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| 6 | 2 | Rehabilitation & Flooring of Gymnasium |  | Court |  | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | 37% | c) | 42% | a) | - | On-going |  | 1
|  |  | Basketball Court, Mamangan, San Isidro |  |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | 5% | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
|  | TALAINGOD | [21 empty] | AC
| 8 | 1 | Grouted Riprap on Embankment |  | Riprap |  | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Plan and POW on process c/o PDPM |  | 1
|  |  | Sto. Ñino, Talaingod |  |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| 8 | 2 | Barangay Hall Improvement, Dagohoy, |  | Bldg. |  | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Plan and POW on process c/o PDPM |  | 1
|  |  | Talaingod |  |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| 8 | 3 | Construction of 2 Classroom Building Datu Jose |  | Bldg. |  | - | a) | 2000000 | a) | - | e) | - | a) |  | a) | - | c) | - | a) | - |  |  | 1
|  |  | Libayao NHS Ext, |  |  |  |  | b) | - | b) | - | f) | - | b) |  | b) | - | d) | - | b) | - |  |  | 1
|  |  | Natulian, Palma Gil, Talaingod |  |  |  |  | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
|  | CARMEN | [19 empty] | Plan and POW Approval on process |  | AC
|  | 1 | Completion of Evacuation Center Building, |  | Bldg. |  | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - |  |  | 2
|  |  | San Isidro, Carmen |  |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | PANABO CITY | [19 empty] | Amended from Const. of New Brgy. Stage due to funding of Phase 1 by the LGU. Plan and POW on process c/o PDPM |  | AC
|  | 1 | Const. of New Brgy. Stage, Phase II |  | Stage |  | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - |  |  | 2
|  |  | San Pedro, Panabo City |  |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | 2 | Impv't. of Brgy. Road Covered Court, |  | Court |  | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Alloted - May 29, 2019, Additional Funding of 500,000.00,SB no. 4 cy 2019 for Allotment Nov 25, 2019 |  | 2
|  |  | Malativas, Panabo City |  |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | 3 | Rehab. Of Multi-Purpose Gym & Facililies |  | Gym |  | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Request for Allotment on process |  | 2
|  |  | Maduao, Panabo City |  |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | 4 | Const. of Multi-Purpose Bldg. |  | Bldg. |  | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Plan and POW on process c/o PDPM |  | 2
|  |  | Sto. Nino, Panabo City |  |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | 5 | Completion of Canopy at DAPCO Covered |  | Court |  | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For Plan preparation by PDPM August 5, 2019 |  | 2
|  |  | Court, Dapco, Panabo City |  |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | 6 | Perimeter Fence of Day Care Center I & II, |  | Bldg. |  | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For inspection by PDPM for PLAN and POW as of 7/19/2019 |  | 2
|  |  | Nanyo, Panabo City |  |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | STO. TOMAS | [19 empty] | For amendment in the AIP 3rd revision |  | AC
|  | 1 | Const. of Multi-Purpose Bldg./Compl. Of |  | Bldg. |  | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - |  |  | 2
|  |  | Covered Court Canopy, Balagunan, |  |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
|  |  | Sto. Tomas |  |  |  |  | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | 2 | Const. of Perimeter Fence of Kinamayan |  | Fence |  | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Inspected by PDPM for POW and POW July 31, 2019 |  | 2
|  |  | Integ,. School, Kinamayan, Sto. Tomas |  |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | B.E. DUJALI | [21 empty] | AC
|  | 1 | Concreting of Brgy. Road Canal, |  | Road |  | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For inspection by PDPM for PLAN and POW as of 7/19/2019 |  | 2
|  |  | Dujali, B.E. Dujali |  |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | 2 | Concreting of Drainage, Tanglaw, |  | Drainage |  | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For inspection by PDPM for PLAN and POW as of 7/19/2019 |  | 2
|  |  | B.E. Dujali |  |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | 3 | Const. of Bleacher w/ Canopy (Ph.II) and |  | Bleacher |  | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Check for pick-up as of July 5, 2019 with check no. 0135071 |  | 2
|  |  | Upgrading of Flooring, Cabay-angan, B.E. Dujali |  |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | 4 | Desilting and Concreting of Drainage-main |  | Bleacher |  | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For inspection by PDPM for PLAN and POW as of 7/19/2019 |  | 2
|  |  | Collector Canal, New Casay, B.E. Dujali |  |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | 5 | Const. of Brgy. Multi-Purpose Covered Court, |  | Bleacher |  | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For inspection by PDPM for PLAN and POW as of 7/19/2019 |  | 2
|  |  | Magupising, B.E. Dujali |  |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | IGCS | [21 empty] | AC
|  | 1 | Impv't. of Brgy. Water System, Pichon, IGCS |  | Water |  | Admin | a) | 500000 | a) | 05/31/18 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For Implementation |  | 2
[5 empty] | System |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | 2 | Powerline Expansion Project, Cogon, IGACOS |  | Water |  | Contract | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For Implementation. |  | 2
[5 empty] | System |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | 3 | Water System From Prk. 6 - Prk. 2 - Prk. 5A, |  | Water |  | Admin | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For Implementation |  | 2
|  |  | Tagbay, IGCS |  | System |  |  | b) | Pacquiao | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | 4 | Rehab of Multipurpose Hall, Tagdaliao |  | Bldg. |  | Admin | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | proposed realignement due to project ovelap |  | 2
|  |  | IGACOS |  |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | 5 | Electrification Project, Kanaan, IGACOS |  | Elect. |  | Admin | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For DANECO staking |  | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | 7 | Powerline Expansion Project, Tambo, IGCS |  | Elect. |  | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Procurement of Materials on process |  | 2
[8 empty] | b) | Porras | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | Admin | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | 9 | Construction of Multipurpose Pavement |  | Bldg. |  | Admin | a) | 500000 | a) |  | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Amended from Improvement of Brgy Hall due to change Brgy. Priority. Resolution No. 70 series of 2019 dated July 18, 2019. For allotment |  | 2
|  |  | Penaplata, IGCS |  |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | 10 | Completion of Kasilak Day Care Center, |  | Bldg. |  | Admin | a) | 500000 | a) | 07/05/18 | e) | - | a) | 500000 | a) | 93.04% | c) | 86.15% | a) | - | On-going |  | 2
|  |  | Sta. Cruz, IGCS |  |  |  |  | b) | Porras | b) | 5/20/2019 | f) | - | b) | 500000 | b) | - | d) | -6.89% | b) | - |  |  | 2
[8 empty] | c) | - | c) | 7/17/2019 | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | 11/30/2019 | [12 empty] | 2
|  | 11 | Const. of Concrete fence of New Brgy. Site, |  | Fence |  | - | a) | 500000 | a) |  | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For Implementation |  | 2
|  |  | San Isidro, IGCS |  |  |  |  | b) | Porras | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | [13 empty] | 2
|  | 12 | Electrification of Sitio Baongon-Diamond- |  | Elect. |  | - | a) | 500000 | a) |  | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Procurement on process |  | 2
|  |  | Mansanitas, Dadatan, IGCS |  |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | 13 | Drilling of Water System, |  | Water |  | - | a) | 500000 | a) |  | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For amendment. This project scope of work was included on a separate project titled Construction of Potable Water System at Linusotan, IGACOS. |  | 2
|  |  | Linusotan, IGCS |  | System |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
| L. | 5% Calamity Fund CY 2018 | [21 empty] | FS
|  | 1. Prevention and Mitigation | [21 empty] | AC
|  | 1.1 Desiltation/Excavation of rivers and creeks |  |  | rivers |  | Admin | a) | 3000000 | [12 empty] | Investigation/Inspection of priority projects |  | AC
[8 empty] | b) | - | [14 empty] | AC
[8 empty] | c) | PEO | [14 empty] | AC
[8 empty] | d) | - | [14 empty] | AC
| 11 | 1.1.1. | Improvement and Desiltation of Tagum Creek (Phase I and Phase II) |  | Creek |  | Admin | a) | 2,000,000.00 | a) | 11/06/18 | e) | - | a) | 2,000,000.00 | a) | 100% | c) | 100% | a) | 5 | Completed |  | 1 | 1
[8 empty] | b) | Mayang | b) | 03/22/19 | f) | - | b) | 2,000,000.00 | b) | - | d) | 0% | b) | 110 |  |  | 1
[8 empty] | c) | PEO | c) | 10/31/19 | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | 224 CD | d) | - | [12 empty] | 1
|  | 1.2 Improvement of Roads, Drainage & Canals |  |  | roads/canals |  | Admin | a) | 3000000 | [12 empty] | Investigation/Inspection of priority projects. |  | AC
[8 empty] | b) | - | [12 empty] | Declared as savings |  | AC
[8 empty] | c) | PEO | [14 empty] | AC
[8 empty] | d) | - | [14 empty] | AC
| 1 | 1.2.1 | Rehab./Impv't. of Sonlon-Longanapan Road |  | road |  | Admin | a) | 1,500,000.00 | a) | - | e) | - | a) | 1,500,000.00 | a) | 47.32% | c) | 20.57% | a) | - | On going |  | 1
[8 empty] | b) | - | b) | - | f) | - | b) | 1,500,000.00 | b) | - | d) | -26.75% | b) | - |  |  | 1
[8 empty] | c) | PEO | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
|  | 1.3 Improvement of bridges and cross drainage |  |  | bridges/drainage |  | Admin | a) | 3000000 | [12 empty] | Declared as savings |  | AC
[8 empty] | b) | - | [14 empty] | AC
[8 empty] | c) | PEO | [14 empty] | AC
[8 empty] | d) | - | [14 empty] | AC
|  | a. | Impv't. of Mabaus Cross Drainage |  | Drainage |  | Admin | a) | 3,000,000.00 | a) | - | e) | - | a) | 3,000,000.00 | a) | - | c) | - | a) | - | Preparation of POW & Plan c/o PDPM |  | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 3,000,000.00 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | 1.4 Revitment of Dike and Slope Protection |  |  | Dike |  | Admin | a) | 3000000 | [12 empty] | See project listed below |  | AC
[8 empty] | b) | - | [14 empty] | AC
[8 empty] | c) | Admin | [14 empty] | AC
[8 empty] | d) | - | [14 empty] | AC
|  | a. | Rehab. Of Dujali-Pawas-San Vicente RDCG-Abutment A&B (Embankment) - Riprapping A&B @ Both Side |  | Dike |  | Admin | a) | 3,000,000.00 | a) | 11/06/18 | e) | - | a) | 3,000,000.00 | a) | 100.00% | c) | 98.47% | a) | 10 | Suspended 9/23/2019 |  | 2
[8 empty] | b) | Sanchez | b) | 02/18/19 | f) | 145 | b) | 3,000,000.00 | b) | 88.56% | d) | -1.53% | b) | 70 |  |  | 2
[8 empty] | c) | PEO | c) | 05/08/19 | g) | - | c) | 2263892.44 | [8 empty] | 2
[8 empty] | d) | - | d) | 9/30/2019 | [12 empty] | 2
|  | 2. Rehabilitation and Recovery |  |  | roads |  | Admin | a) | 2026000 | [12 empty] | Declared as savings |  | AC
[8 empty] | b) | - | [14 empty] | AC
[8 empty] | c) | PEO | [14 empty] | AC
[8 empty] | d) | - | [14 empty] | AC
| M. | SUPPLEMENTAL BUDGET # 1 CY 2018 | [5 empty] | a) | 6,000,000.00 | [12 empty] | See list of Provincial Roads |  | FS
|  | 1 Const. in Progress - Infrastructure | [5 empty] | b) | Paraguya | [14 empty] | AC
|  | Assets (Rehabilitation of Various | [5 empty] | c) | PEO | [14 empty] | AC
|  | Provincial Roads) | [5 empty] | d) | - | [14 empty] | AC
| 5 | 1 | Mesaoy - Jct. Mahayahay |  | Road |  | Admin | a) | 1,534,000.00 | a) | 07/19/18 | e) | - | a) | 1,534,000.00 | a) | 60% | c) | 60% | a) | - | Suspended as of Dec. 27, 2018 |  | 1
[8 empty] | b) | Salido | b) | 11/16/18 | f) | - | b) | 1,534,000.00 | b) | - | d) | - | b) | - | Cancellation of PO # 2018082439 and RE-PR |  | 1
[8 empty] | c) | PEO | c) | 12/15/18 | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| 5 | 2 | Del Pilar - Jct. Silangan |  | Road |  | Admin | a) | 1,795,000.00 | a) | 07/19/18 | e) | - | a) | 1,795,000.00 | a) | 73.00% | c) | 73.00% | a) | 14 | On-going |  | 1
[8 empty] | b) | Salido | b) | 10/16/18 | f) | - | b) | 1,795,000.00 | b) | - | d) | - | b) | 30 | Suspended as of January 4, 2019 |  | 1
[8 empty] | c) | PEO | c) | 11/20/18 | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| N. | SUPPLEMENTAL BUDGET # 2 CY 2018 | [21 empty] | FS
|  | 1 Const./Compl./Impv't. of Various Gov't. | [21 empty] | AC
|  | Bldgs., Structures & Facilities (Const. in | [21 empty] | AC
|  | Progress - Bldgs. & Other Structures | [21 empty] | AC
| 4 |  | Const./Impv't. of DDN Hospital |  | Bldg. |  | - | a) | 5,000,000.00 | a) | - | e) | - | a) | 5,000,000.00 | a) | - | c) | 40% | a) | - | On-going |  | 1
|  |  | Kapalong Zone |  |  |  |  | b) | - | b) | - | f) | - | b) | 5,000,000.00 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
|  |  | Const. of DDN Hospital Carmen Zone |  | Bldg. |  | Admin | a) | 5,500,000.00 | a) | - | e) | - | a) | 5,500,000.00 | a) | - | c) | - | a) | - | PR ON PROCESS 6/11/2019 |  | 2
|  |  | Annex Bldg. |  |  |  |  | b) | Estorco | b) | - | f) | - | b) | 5,500,000.00 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | PEO | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
| 5 |  | Compl. Of Bahay Pag-Asa for Minors, |  | Bldg. |  | - | a) | 3,000,000.00 | a) | - | e) | - | a) | 3,000,000.00 | a) | - | c) | - | a) | - | Waiting for Delivery of Materials |  | 1
|  |  | New Corella |  |  |  |  | b) | - | b) | - | f) | - | b) | 3,000,000.00 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| 11 |  | Upgrading of DAGOEMC Muti-Purpose Bldg. |  | Bldg. |  | - | a) | 3,000,000.00 | a) | 09/04/2018 | e) | - | a) | 3,000,000.00 | a) | 30.28% | c) | 56.97% | a) | 7 | On-going |  | 1
|  |  | Mankilam |  |  |  |  | b) | Chua | b) | 03/04/2019 | f) | - | b) | 3,000,000.00 | b) | - | d) | - | b) | 210 |  |  | 1
[8 empty] | c) | PEO | c) | 07/26/2019 | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | 145 CD | d) | - | [12 empty] | 1
| 11 |  | Const. of Add'l. 2nd Level Multi-Purpose |  | Bldg. |  | - | a) | 7,592,588.00 | a) | - | e) | - | a) | 7,592,588.00 | a) | - | c) | - | a) | - | Preparation of POW & Plan c/o PDPM. |  | 1
|  |  | HalI, PGSO warehouse,Bldg., Mankilam |  |  |  |  | b) | - | b) | - | f) | - | b) | 7,592,588.00 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| O. | SUPPLEMENTAL BUDGET # 4 CY 2018 | [21 empty] | FS
| 11 | 1 | Construction of Multi-Purpose Bldg. (PENRO Building) |  | Bldg. | 303.75 sq.m | Admin | a) | 1800000 | a) | 06/11/18 | e) | - | a) | 1800000 | a) | 100% | c) | 100% | a) | 25 | Completed as per Physical accomplishment. Financial Documents on process |  | 1
[8 empty] | b) | Pasiona/Juan | b) | 10/16/18 | f) | 111 | b) | 1800000 | b) | - | d) | 0% | b) | 750 |  |  | 1
|  |  | (Part of P8,548,000.00)(P1,800,000.00 - |  |  |  |  | c) | PEO | c) | 09/10/19 | g) | 09/13/19 | c) | 6129861.34 | [8 empty] | 1
|  |  | SB # 4 CY 2018) |  |  |  |  | d) | 222 CD | d) | 06/30/19 | [12 empty] | 1
| P. | SUPPLEMENTAL BUDGET # 5 CY 2018 | [21 empty] | FS
|  | STIMULUS CY 2018 | [21 empty] | AC
| 1 | 1 | Const. of MP Hall, Rizal ES, Binancian, |  | Bldg. |  | - | a) | 1250000 | a) | 02/04/19 | e) | - | a) | 1250000 | a) | - | c) | 80% | a) | - | On-going |  | 1
|  |  | Asuncion |  |  |  |  | b) | - | b) | 06/18/2019 | f) | - | b) | 1250000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| 1 | 2 | Const. of MP Hall, Liguyon ES, Binancian, |  | Bldg. |  | - | a) | 1250000 | a) | 02/04/19 | e) | - | a) | 1250000 | a) | - | c) | 80% | a) | - | On-going |  | 1
|  |  | Asuncion |  |  |  |  | b) | - | b) | 06/16/2019 | f) | - | b) | 1250000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| 1 | 3 | Rehab./Impv't. of MP Bldg. (Gym), Napungas, |  | GYM |  | - | a) | 500000 | a) | 02/04/19 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Plan and POW on process |  | 1
|  |  | Asuncion |  |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| Q. | OPPAP-PAMANA | [21 empty] | FS
|  | 1. TRIBAL HALL | [21 empty] | AC
| 4 | 1.1 | Construction of Tribal Hall |  | Bldg. |  | Admin | a) | 500000 | a) | CY 2018 | e) | - | a) | 500000 | a) | 100% | c) | 100% | a) | 5 | Completed as per Physical Accomplishment. Financial Documents on process |  | 1
|  |  | Brgy. Gupitan, Kapalong |  |  |  |  | b) | Ambrocio | b) | 2/22/2019 | f) | - | b) | 500000 | b) | - | d) | 0% | b) | 150 |  |  | 1
[8 empty] | c) | PEO | c) | 5/22/2019 | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
|  | 2. PROCESSING AND BAGSAKAN CENTER | [21 empty] | AC
| 8 | 2.1 | Const. of Processing and Bagsakan Center, |  | Bldg. |  | Contract | a) | 2500000 | a) | - | e) | - | a) | 2500000 | a) | - | c) | 4% | a) | - | On going. |  | 1
|  |  | Brgy. Dagohoy, Talaingod |  |  |  |  | b) | - | b) | - | f) | - | b) | 2500000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| 4 | 2.2 | Const. of Processing and Bagsakan Center, |  | Bldg. | 300 sq.m | Contract | a) | 2500000 | a) | 08/29/18 | e) | - | a) | 2500000 | a) | 100% | c) | 100% | a) | 6 | Completed as per Physical Accomplishment. Financial Documents on process |  | 1
|  |  | Brgy. Gupitan, Kapalong, Davao del Norte |  |  |  |  | b) | Ambrucio | b) | 02/12/19 | f) | - | b) | 2500000 | b) | - | d) | 0% | b) | 180 |  |  | 1
[8 empty] | c) | Alpha & Omega | c) | 05/12/19 | g) | - | c) | 156000 | [8 empty] | 1
[8 empty] | d) | 120 CD | d) | - | [12 empty] | 1
|  | 3. SOLAR DRYER | [21 empty] | AC
| 4 | 3.1 | Post Harvest Facilities (Corn Mill, Solar Dryer, |  | Bldg. |  | Contract | a) | 1500000 | a) | - | e) | - | a) | 1500000 | a) | 10% | c) | 15% | a) | - | on-going. |  | 1
|  |  | Corn Sheller), Kapalong, Davao del Norte |  |  |  |  | b) | - | b) | - | f) | - | b) | 1500000 | b) | - | d) | 5% | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | 391970.93 | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| 8 | 3.2 | Post Harvest Facilities (Corn Mill, Solar Dryer, Corn Sheller), Sitio Butay, Palma Gil, Talaingod, Davao del Norte |  | Bldg. |  | Admin | a) |  | a) | - | e) | - | a) | 1850000 | a) |  | c) | 79.14% | a) | 11 | on-going |  | 1
[8 empty] | b) | Dadula | b) | July 16, 2019 | f) | - | b) | 1850000 | b) | - | d) |  | b) | 246 |  |  | 1
[8 empty] | c) | - | c) | Nov. 13, 2019 | g) | - | c) | [9 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
|  | 4. TRADING POST STORAGE | [21 empty] | AC
| 11 |  | Trading Post, Storage and Hauling Truck, Pandapan, Tagum City |  | Bldg. |  | Contract | a) | 4000000 | a) | - | e) | - | a) | 4000000 | a) | - | c) | - | a) | - | Re-bidding |  | 1
[8 empty] | b) | - | b) | - | f) | - | b) | 4000000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
|  |  | Trading Post, Storage and Hauling Truck, Purok Ramihan, Datu Abdul, Panabo City |  | Bldg. |  | - | a) | 4000000 | a) | CY 2018 | e) | - | a) | 4000000 | a) | 3.74% | c) | 1.91% | a) | - | On-going |  | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 4000000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  |  | Trading Post, Storage and Hauling Truck Libuak, Island Garden City of Samal (IGACOS) |  | Bldg. |  | - | a) | 4000000 | a) | CY 2018 | e) | - | a) | 4000000 | a) | - | c) | - | a) | - | For verification of beneficiary |  | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 4000000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | 5. WATER SYSTEM | [21 empty] | AC
| 4 |  | Upgrading of Existing PWS Level II in Sitio Langan, Gupitan, Kapalong |  | PWS |  | Admin | a) | 2500000 | a) |  | e) |  | a) | 2500000 | a) | 31.24% | c) | 32.67% | a) |  | On-going |  | 1
[8 empty] | b) |  | b) | 11/16/2019 | f) |  | b) | 2500000 | b) | - | d) | 1.43% | b) |  |  |  | 1
[8 empty] | c) |  | c) | 02/27/2020 | g) | - | c) | [9 empty] | 1
[8 empty] | d) |  | d) | - | [12 empty] | 1
| 4 |  | Upgrading of Existing PWS Level II in Sitio Patel 2, Gupitan, Kapalong |  | PWS |  | Admin | a) | 2500000 | a) | 8/14/2019 | e) | - | a) | 2500000 | a) |  | c) | 100% | a) | - | Completed as per Physical Accomplishment. Financial Documents on process |  | 1
[8 empty] | b) | Diosanta | b) | 3/25/2019 | f) | - | b) | 2500000 | b) |  | d) |  | b) | - |  |  | 1
[8 empty] | c) | PEO | c) | 7/19/2019 | g) | 09/30/2019 | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| 4 |  | Construction of PWS Level II in Purok 7-A and 7-B, Capungagan, Kapalong |  | PWS |  | Admin | a) | 1000000 | a) | 11/25/2019 | e) | - | a) | 1000000 | a) | - | c) | 5% | a) | - | On-going |  | 1
[8 empty] | b) | Kabinge | b) | - | f) | - | b) | 1000000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | PEO | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| 4 |  | Construction of PWS Level II in Purok 2, Pag-asa, Kapalong |  | PWS |  | Admin | a) | 1000000 | a) | 11/12/18 | e) | - | a) | 1000000 | a) | - | c) | - | a) | - | Declared savings in the AIP 2nd Revision to fund for the Construction of PWS in Brgy. Linusotan, Kaputian District, IGACOS (Project was funded by OPAPP CY 2018) |  | 1
[8 empty] | b) | - | b) | - | f) | - | b) | 1000000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| 8 |  | Construction of PWS Level II in Sitio Upper Dulyan, Palma Gil, Talaingod, DDN |  | PWS |  | Admin | a) | 1000000 | a) | - | e) | - | a) | 1000000 | a) | - | c) | 5% | a) | - | On going |  | 1
[8 empty] | b) | Kabinge | b) | - | f) |  | b) | 1000000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | PEO | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
|  | 6. CATTLE PRODUCTION | [21 empty] | AC
| 4 |  | Cattle Production- Brgy. Tiburcia, Gupitan and Semong, Kapalong |  | Bldg. |  | Admin | a) | 1500000 | a) | - | e) | - | a) | 1500000 | a) | - | c) | - | a) | - | For cancellation. A letter was sent to OPAPP last Dec 2018 requesting to allow us to reduce the number of cattle but we are still hoping that there would be a supplier will bid |  | 1
[8 empty] | b) | - | b) | - | f) | - | b) | 1500000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| 8 |  | Cattle Production, Brgy. Palma Gil, Brgy. Sto. Nino, Brgy. Dagohoy, Talaingod, Davao del Norte |  | Bldg. |  | Admin | a) | 1500000 | a) | - | e) | - | a) | 1500000 | a) | - | c) | - | a) | - | For cancellation. A letter was sent to OPAPP last Dec 2018 requesting to allow us to reduce the number of cattle but we are still hoping that there would be a supplier will bid |  | 1
[8 empty] | b) | - | b) | - | f) | - | b) | 1500000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
|  | 7. RICE MILL FOR UPLAND RICE | [21 empty] | AC
| 8 |  | Rice Mill for Upland Rice, Palma Gil, Talaingod |  | Bldg. |  | Admin | a) | 1000000 | a) | - | e) | - | a) | 1000000 | a) | 31.93% | c) | 31.93% | a) | - | No Approved P.O. |  | 1
[8 empty] | b) | - | b) | - | f) | - | b) | 1000000 | b) | - | d) | 0% | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| 4 |  | Rice Mill for Upland Rice,Gupitan, Kapalong |  | Bldg. |  | Admin | a) | 1000000 | a) | - | e) | - | a) | 1000000 | a) | 100% | c) | 100% | a) | - | Completed |  | 1
[8 empty] | b) | Ambrucio | b) | 6/17/2019 | f) | - | b) | 1000000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
|  | 8. AGRICULTURAL PRODUCTIVITY SUPPORT PROJECT | [21 empty] | AC
|  |  | Agricultural Productivity Support Project- |  | - |  | - | a) | 1500000 | a) | - | e) | - | a) | 1500000 | a) | - | c) | - | a) | - | For verification of beneficiary |  | 2
|  |  | Fishing Equipment, Tambo, IGACOS |  |  |  |  | b) | - | b) | - | f) | - | b) | 1500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
| R. | LOCAL GOVERNMENT SUPPORT FUND (LGSF) CY 2018 | [21 empty] | FS
| 1 | 1 | Road Upgrading of San Vicente - Butay Provincial Road |  | Road |  | Contract | a) | 19949581.18 | a) | CY 2018 | e) | - | a) | 19949581.18 | a) | 100% | c) | 100% | a) | 18 | Completed as per Physical Accomplishment. Financial Documents on process |  | 1
[8 empty] | b) | Aclaracion | b) | 11/19/18 | f) | 28 CD | b) | 19949581.18 | b) | 100% | d) | 0% | b) | 396 |  |  | 1
[8 empty] | c) | Alpha & Omega | c) | 06/08/19 | g) | 06/26/2019 | c) | 9,685,667.31 | [8 empty] | 1
[8 empty] | d) | 202 CD | d) | 07/06/19 | [12 empty] | 1
| S. | QUICK RESPOND FUND CY 2016 | [21 empty] | FS
| 4 | 1 | Rehab. Of Slope Protection of Libuganon River Along Kapalong - Mabantao - Florida Prov'l. Road Phase I |  | Road |  | - | a) | 900000 | a) | - | e) | - | a) | 900000 | a) | - | c) | - | a) | - | For AIP Amendment |  | 1
[8 empty] | b) | - | b) | - | f) | - | b) | 900000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
II. PROJECTS UNDER THE CURRENT APPROPRIATION CY 2019
A.1 GENERAL FUND CY 2019 | [6 empty] | MBA/CBRMC | a) | 18127866 | a) | 01/03/19 | e) | - | a) | 18127866 | a) | 83.63 | c) | 83.83 | a) | 46 | See list of Provincial Roads |  | AP
Road ID |  | Maintenance of Various Provincial Roads and Bridges at District 1 |  |  | Road Maintenance | KM |  | b) | Paraguya | b) | 01/03/19 | f) | - | b) | 18127866 | b) | - | d) | - | b) | 920 |  |  | FS
[6 empty] | 288.26 |  | c) | PEO/CBRMC | c) | 12/31/19 | g) | - | c) | - | [8 empty] | AC
11DAN | [9 empty] | d) | - | [12 empty] | AC
[8 empty] | d) | 261 days | d) | - | [12 empty] | AC
|  | Jct. Highway Magatos - New Bantayan |  |  | Road Maintenance | 7.1 | MBA | a) | 287307.39 | a) | 01/03/19 | e) | - | a) | 287307.39 | a) | 100% | c) | 100% | a) | 15 | Completed |  | AC | 4
001 | [7 empty] | b) | Crucio | b) | 01/16/19 | f) | - | b) | 287307.39 | b) | - | d) | - | b) | 480 |  |  | 1 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 118693.58 | [8 empty] | 1 | 4
[8 empty] | d) | - | d) | - | [12 empty] | 1 | 4
|  | Jct. Highway Magatos - New Bantayan |  |  | Road Maintenance | 7.1 | CBRMC | a) | 223674.22 | a) | 01/03/19 | e) | - | a) | 223674.22 | a) | 100% | c) | 100% | a) | 16 | Completed |  | 1 | 4
001 | [7 empty] | b) | Crucio | b) | 3/22/19 | f) | - | b) | 223674.22 | b) | - | d) | - | b) | 480 |  |  | 1 | 4
[8 empty] | c) | CALAFA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [8 empty] | 1 | 4
[8 empty] | d) | 3 quarters | d) | - | [12 empty] | 1 | 4
|  | Magatos-Bdry Pagsabangan |  |  | Road Maintenance | 8.33 | MBA | a) | 328740.25 | a) | 01/03/19 | e) | - | a) | 328740.25 | a) | 100% | c) | 100% | a) | 15 | Completed |  | 1 | 4
002 | [7 empty] | b) | Crucio | b) | 01/03/19 | f) | - | b) | 328740.25 | b) | - | d) | - | b) | 450 |  |  | 1 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 207258.49 | [8 empty] | 1 | 4
[8 empty] | d) | - | d) | - | [12 empty] | 1 | 4
|  | Magatos-Bdry Pagsabangan |  |  | Road Maintenance | 8.33 | CBRMC | a) | 270763.53 | a) | 01/03/19 | e) | - | a) | 270763.53 | a) | 100% | c) | 100% | a) | 16 | Completed |  | 1 | 4
002 | [7 empty] | b) | Crucio | b) | 03/22/19 | f) | - | b) | 270763.53 | b) | - | d) | - | b) | 450 |  |  | 1 | 4
[8 empty] | c) | CALAFA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [8 empty] | 1 | 4
[8 empty] | d) | 3 quarters | d) | - | [12 empty] | 1 | 4
|  | Ilog-New Bantayan |  |  | Road Maintenance | 2.68 | MBA | a) | 131131.39 | a) | 01/03/19 | e) | - | a) | 131131.39 | a) | 100% | c) | 100% | a) | 15 | Completed |  | 1 | 4
003 | [7 empty] | b) | Crucio | b) | 01/16/19 | f) | - | b) | 131131.39 | b) | - | d) | - | b) | 450 |  |  | 1 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 49,316.69 | [8 empty] | 1 | 4
[8 empty] | d) | - | d) | - | [12 empty] | 1 | 4
|  | Ilog-New Bantayan |  |  | Road Maintenance | 2.68 | CBRMC | a) | 65925.03 | a) | 01/03/19 | e) | - | a) | 65925.03 | a) | 100% | c) | 100% | a) | 16 | Completed |  | 1 | 4
003 | [7 empty] | b) | Crucio | b) | 03/22/19 | f) | - | b) | 65925.03 | b) | - | d) | - | b) | 450 |  |  | 1 | 4
[8 empty] | c) | CALAFA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [8 empty] | 1 | 4
[8 empty] | d) | 3 quarters | d) | - | [12 empty] | 1 | 4
|  | Asuncion -Monte Carlo-Del Pilar |  |  | Road Maintenance | 9.93 | MBA | a) | 474102.88 | a) | 01/03/19 | e) | - | a) | 474102.88 | a) | 100% | c) | 100% | a) | 15 | Completed |  | 1 | 4
005 | [7 empty] | b) | Crucio | b) | 01/03/19 | f) | - | b) | 474102.88 | b) | - | d) | - | b) | 450 |  |  | 1 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 240274.49 | [8 empty] | 1 | 4
[8 empty] | d) | - | d) | - | [12 empty] | 1 | 4
|  | Asuncion -Monte Carlo-Del Pilar |  |  | Road Maintenance | 9.93 | CBRMC | a) | 355524.28 | a) | 01/03/19 | e) | - | a) | 355524.28 | a) | 100% | c) | 100% | a) | 16 | Completed |  |  | 4
005 | [7 empty] | b) | Crucio | b) | 03/22/19 | f) | - | b) | 355524.28 | b) | - | d) | - | b) | 450 |  |  | 1 | 4
[8 empty] | c) | MAHAYAHAY IFA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [8 empty] | 1 | 4
[8 empty] | d) | 3 quarters | d) | - | [12 empty] | 1 | 4
|  | Jct. Highway Canatan-Jct. Highway Magatos |  |  | Road Maintenance | 4.85 | MBA | a) | 209808.59 | a) | 01/03/19 | e) | - | a) | 209808.59 | a) | 100% | c) | 100% | a) | 15 | Completed |  | 1 | 4
006 | [7 empty] | b) | Crucio | b) | 02/18/19 | f) | - | b) | 209808.59 | b) | - | d) | - | b) | 450 |  |  | 1 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 80652.8 | [8 empty] | 1 | 4
[8 empty] | d) | - | d) | - | [12 empty] | 1 | 4
|  | Jct. Highway Canatan-Jct. Highway Magatos |  |  | Road Maintenance | 4.85 | CBRMC | a) | 162458.12 | a) | 01/03/19 | e) | - | a) | 162458.12 | a) | 100% | c) | 100% | a) | 16 | Completed |  | 1 | 4
006 | [7 empty] | b) | Crucio | b) | 03/22/19 | f) | - | b) | 162458.12 | b) | - | d) | - | b) | 450 |  |  | 1 | 4
[8 empty] | c) | CAMODA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [8 empty] | 1 | 4
[8 empty] | d) | 3 quarters | d) | - | [12 empty] | 1 | 4
[24 empty] | 1 | 4
|  | Sta. Felomina-San Roque |  |  | Road Maintenance | 7.68 | MBA | a) | 147439.63 | a) | 01/03/19 | e) | - | a) | 147439.63 | a) | 100% | c) | 100% | a) | 15 | Completed |  |  | 4
008 | [7 empty] | b) | Crucio | b) | 01/16/19 | f) | - | b) | 147439.63 | b) | - | d) | - | b) | 450 |  |  | 1 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 63806.67 | [8 empty] | 1 | 4
[8 empty] | d) | - | d) | - | [12 empty] | 1 | 4
|  | Sta. Felomina-San Roque |  |  | Road Maintenance | 7.68 | CBRMC | a) | 261345.67 | a) | 01/03/19 | e) | - | a) | 261345.67 | a) | 100% | c) | 100% | a) | 16 | Completed |  | 1 | 4
008 | [7 empty] | b) | Crucio | b) | 03/25/19 | f) | - | b) | 261345.67 | b) | - | d) | - | b) | 450 |  |  | 1 | 4
[8 empty] | c) | STAFFA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [8 empty] | 1 | 4
[8 empty] | d) | 3 quarters | d) | - | [12 empty] | 1 | 4
|  | Saug-Sonlon-Bdy Longanapan |  |  | Road Maintenance | 11.6 | MBA | a) | 568486.36 | a) | 01/03/19 | e) | - | a) | 568486.36 | a) | 100% | c) | 100% | a) | 15 | Completed |  | 1 | 4
010 | [7 empty] | b) | Crucio | b) | 01/16/19 | f) | - | b) | 568486.36 | b) | - | d) | - | b) | 450 |  |  | 1 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 262900.22 | [8 empty] | 1 | 4
[8 empty] | d) | - | d) | - | [12 empty] | 1 | 4
|  | Saug-Sonlon-Bdy Longanapan |  |  | Road Maintenance | 11.6 | CBRMC | a) | 185565.56 | a) | 01/03/19 | e) | - | a) | 185565.56 | a) | 100% | c) | 100% | a) | 16 | Completed |  | 1 | 4
010 | [7 empty] | b) | Crucio | b) | 03/26/19 | f) | - | b) | 185565.56 | b) | - | d) | - | b) | 450 |  |  | 1 | 4
[8 empty] | c) | BINANCIAN LIVESTOCK AFA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [8 empty] | 1 | 4
[8 empty] | d) | 3 quarters | d) | - | [12 empty] | 1 | 4
|  | Jct. New Visayas-Buan |  |  | Road Maintenance | 2.99 | MBA | a) | 79238.27 | a) | 01/03/19 | e) | - | a) | 79238.27 | a) | 100% | c) | 100% | a) | 15 | Completed |  | 1 | 4
011 | [7 empty] | b) | Crucio | b) | 02/18/19 | f) | - | b) | 79238.27 | b) | - | d) | - | b) | 450 |  |  | 1 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 14682.85 | [8 empty] | 1 | 4
[8 empty] | d) | - | d) | - | [12 empty] | 1 | 4
|  | Jct. New Visayas-Buan |  |  | Road Maintenance | 2.99 | CBRMC | a) | 101242.01 | a) | 01/03/19 | e) | - | a) | 101242.01 | a) | 100% | c) | 100% | a) | 16 | Completed |  | 1 | 4
011 | [7 empty] | b) | Crucio | b) | 03/22/19 | f) | - | b) | 101242.01 | b) | - | d) | - | b) | 450 |  |  | 1 | 4
[8 empty] | c) | BUAN IFA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [8 empty] | 1 | 4
[8 empty] | d) | 3 quarters | d) | - | [12 empty] | 1 | 4
|  | San Vicente - Butay |  |  | Road Maintenance | 7.52 | MBA | a) | 209624.2 | a) | 01/03/19 | e) | - | a) | 209624.2 | a) | 100% | c) | 100% | a) | 15 | Completed |  | 1 | 4
013 | [7 empty] | b) | Crucio | b) | 02/18/19 | f) | - | b) | 209624.2 | b) | - | d) | - | b) | 450 |  |  | 1 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 56,080.29 | [8 empty] | 1 | 4
[8 empty] | d) | - | d) | - | [12 empty] | 1 | 4
|  | San Vicente - Butay |  |  | Road Maintenance | 7.52 | CBRMC | a) | 227205.88 | a) | 01/03/19 | e) | - | a) | 227205.88 | a) | 100% | c) | 100% | a) | 16 | Completed |  | 1 | 4
013 | [7 empty] | b) | Crucio | b) | 03/27/19 | f) | - | b) | 227205.88 | b) | - | d) | - | b) | 450 |  |  | 1 | 4
[8 empty] | c) | SVMODA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [8 empty] | 1 | 4
[8 empty] | d) | 3 quarters | d) | - | [12 empty] | 1 | 4
|  | Jct. Highway Doña Andrea - Capungagan |  |  | Road Maintenance | 8.7 | MBA | a) | 230835.16 | a) | 01/03/19 | e) | - | a) | 230835.16 | a) | 100% | c) | 100% | a) | 15 | Completed |  | 1 | 4
014 | [7 empty] | b) | Crucio | b) | 02/18/19 | f) | - | b) | 230835.16 | b) | - | d) | - | b) | 450 |  |  | 1 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 60,629.26 | [8 empty] | 1 | 4
[8 empty] | d) | - | d) | - | [12 empty] | 1 | 4
[24 empty] | 1 | 4
|  | Jct. Highway Doña Andrea - Capungagan |  |  | Road Maintenance | 8.7 | CBRMC | a) | 294308.14 | a) | 01/03/19 | e) | - | a) | 294308.14 | a) | 100% | c) | 100% | a) | 16 | Completed |  |  | 4
014 | [7 empty] | b) | Crucio | b) | 03/28/19 | f) | - | b) | 294308.14 | b) | - | d) | - | b) | 450 |  |  | 1 | 4
[8 empty] | c) | CAPUNGAGAN MPC | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [8 empty] | 1 | 4
[8 empty] | d) | 3 quarters | d) | - | [12 empty] | 1 | 4
|  | Semong-Palma Gil |  |  | Road Maintenance | 2.73 | MBA | a) | 147289.98 | a) | 01/03/19 | e) | - | a) | 147289.98 | a) | 100% | c) | 100% | a) | 15 | Completed |  | 1 | 4
018 | [7 empty] | b) | Crucio | b) | 02/18/19 | f) | - | b) | 147289.98 | b) | - | d) | - | b) | 450 |  |  | 1 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 71745.43 | [8 empty] | 1 | 4
[8 empty] | d) | - | d) | - | [12 empty] | 1 | 4
[24 empty] | 1 | 4
4
4
|  | Semong-Palma Gil |  |  | Road Maintenance | 2.73 | CBRMC | a) | 49186.05 | a) | 01/03/19 | e) | - | a) | 49186.05 | a) | 100% | c) | 100% | a) | 16 | Completed |  |  | 4
018 | [7 empty] | b) | Crucio | b) | 03/22/19 | f) | - | b) | 49186.05 | b) | - | d) | - | b) | 450 |  |  | 1 | 4
[8 empty] | c) | PALMA GIL FA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [8 empty] | 1 | 4
[8 empty] | d) | 3 quarters | d) | - | [12 empty] | 1 | 4
|  | Daligdigon - Dagohoy |  |  | Road Maintenance | 3.34 | MBA | a) | 148835.45 | a) | 01/03/19 | e) | - | a) | 148835.45 | a) | 100% | c) | 100% | a) | - | Completed |  | 1 | 4
020 | [7 empty] | b) | Crucio | b) | - | f) | - | b) | 148835.45 | b) | - | d) | - | b) | - |  |  | 1 | 4
[8 empty] | c) | PEO | c) | - | g) | 2019-12-31 | c) | - | [8 empty] | 1 | 4
[8 empty] | d) | - | d) | - | [12 empty] | 1 | 4
|  | Daligdigon - Dagohoy |  |  | Road Maintenance | 3.34 | CBRMC | a) | 68279.5 | a) | 01/03/19 | e) | - | a) | 68279.5 | a) | 100% | c) | 100% | a) | 16 | Completed |  | 1 | 4
020 | [7 empty] | b) | Crucio | b) | 03/22/19 | f) | - | b) | 68279.5 | b) | - | d) | - | b) | 450 |  |  | 1 | 4
[8 empty] | c) | PALMA GIL FA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [8 empty] | 1 | 4
[8 empty] | d) | 3 quarters | d) | - | [12 empty] | 1 | 4
|  | Jct. Sampao-Bdry. Mamacao |  |  | Road Maintenance | 4.98 | MBA | a) | 154200.78 | a) | 01/03/19 | e) | - | a) | 154200.78 | a) | 100% | c) | 100% | a) | 15 | Completed |  | 1 | 4
025 | [7 empty] | b) | Crucio | b) | 02/18/19 | f) | - | b) | 154200.78 | b) | - | d) | - | b) | 450 |  |  | 1 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 24,296.87 | [8 empty] | 1 | 4
[8 empty] | d) | - | d) | - | [12 empty] | 1 | 4
|  | Jct. Sampao-Bdry. Mamacao |  |  | Road Maintenance | 4.98 | CBRMC | a) | 169521.51 | a) | 01/03/19 | e) | - | a) | 169521.51 | a) | 100% | c) | 100% | a) | 16 | Completed |  | 1 | 4
025 | [7 empty] | b) | Crucio | b) | 03/26/19 | f) | - | b) | 169521.51 | b) | - | d) | - | b) | 450 |  |  | 1 | 4
[8 empty] | c) | AMS KAPALONG | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [8 empty] | 1 | 4
[8 empty] | d) | 3 quarters | d) | - | [12 empty] | 1 | 4
|  | Jct. Highway Luna-Mamacao-Narra |  |  | Road Maintenance | 9.17 | MBA | a) | 357957.66 | a) | 01/03/19 | e) | - | a) | 357957.66 | a) | 100% | c) | 100% | a) | 15 | Completed |  | 1 | 4
026 | [7 empty] | b) | Crucio | b) | 02/18/19 | f) | - | b) | 357957.66 | b) | - | d) | - | b) | 450 |  |  | 1 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 127,996.16 | [8 empty] | 1 | 4
[8 empty] | d) | - | d) | - | [12 empty] | 1 | 4
|  | Jct. Highway Luna-Mamacao-Narra |  |  | Road Maintenance | 9.17 | CBRMC | a) | 313143.91 | a) | 01/03/19 | e) | - | a) | 313143.91 | a) | 100% | c) | 100% | a) | 16 | Completed |  | 1 | 4
026 | [7 empty] | b) | Crucio | b) | 03/26/19 | f) | - | b) | 313143.91 | b) | - | d) | - | b) | 450 |  |  | 1 | 4
[8 empty] | c) | AMS KAPALONG | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [8 empty] | 1 | 4
[8 empty] | d) | 3 quarters | d) | - | [12 empty] | 1 | 4
|  | Jct. Gabuyan-Katipunan-Bucana |  |  | Road Maintenance | 5.89 | MBA | a) | 294403.23 | a) | 01/03/19 | e) | - | a) | 294403.23 | a) | 100% | c) | 100% | a) | 15 | Completed |  | 1 | 4
027 | [7 empty] | b) | Crucio | b) | 02/18/19 | f) | - | b) | 294403.23 | b) | - | d) | - | b) | 450 |  |  | 1 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 126,179.97 | [8 empty] | 1 | 4
[8 empty] | d) | - | d) | - | [12 empty] | 1 | 4
|  | Jct. Gabuyan-Katipunan-Bucana |  |  | Road Maintenance | 5.89 | CBRMC | a) | 129495.6 | a) | 01/03/19 | e) | - | a) | 129495.6 | a) | 100% | c) | 100% | a) | 16 | Completed |  | 1 | 4
027 | [7 empty] | b) | Crucio | b) | 03/26/19 | f) | - | b) | 129495.6 | b) | - | d) | - | b) | 450 |  |  | 1 | 4
[8 empty] | c) | MANGULIBAS FA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [8 empty] | 1 | 4
[8 empty] | d) | 3 quarters | d) | - | [12 empty] | 1 | 4
|  | Capungagan-Mabuhay-Pandulian |  |  | Road Maintenance | 5.57 | MBA | a) | 294917.73 | a) | 01/03/19 | e) | - | a) | 294917.73 | a) | 100% | c) | 100% | a) | 15 | Completed |  | 1 | 4
028 | [7 empty] | b) | Crucio | b) | 02/18/19 | f) | - | b) | 294917.73 | b) | - | d) | - | b) | 450 |  |  | 1 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [8 empty] | 1 | 4
[8 empty] | d) | - | d) | - | [12 empty] | 1 | 4
[24 empty] | 1 | 4
|  | Capungagan-Mabuhay-Pandulian |  |  | Road Maintenance | 5.57 | CBRMC | a) | 105950.95 | a) | 01/03/19 | e) | - | a) | 105950.95 | a) | 100% | c) | 100% | a) | 16 | Completed |  |  | 4
028 | [7 empty] | b) | Crucio | b) | 03/28/19 | f) | - | b) | 105950.95 | b) | - | d) | - | b) | 450 |  |  | 1 | 4
[8 empty] | c) | CAPUNGAGAN MPC | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [8 empty] | 1 | 4
[8 empty] | d) | 3 quarters | d) | - | [12 empty] | 1 | 4
|  | Florida - New Boholano |  |  | Road Maintenance | 2.54 | MBA | a) | 95863.17 | a) | 01/03/19 | e) | - | a) | 95863.17 | a) | 100% | c) | 100% | a) | 15 | Completed |  | 1 | 4
030 | [7 empty] | b) | Crucio | b) | 02/18/19 | f) | - | b) | 95863.17 | b) | - | d) | - | b) | 450 |  |  | 1 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 31,418.99 | [8 empty] | 1 | 4
[8 empty] | d) | - | d) | - | [12 empty] | 1 | 4
|  | Florida - New Boholano |  |  | Road Maintenance | 2.54 | CBRMC | a) | 47425.27 | a) | 01/03/19 | e) | - | a) | 47425.27 | a) | 100% | c) | 100% | a) | 16 | Completed |  | 1 | 4
030 | [7 empty] | b) | Crucio | b) | 03/28/19 | f) | - | b) | 47425.27 | b) | - | d) | - | b) | 450 |  |  | 1 | 4
[8 empty] | c) | SUPRA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [8 empty] | 1 | 4
[8 empty] | d) | 3 quarters | d) | - | [12 empty] | 1 | 4
|  | Jct. New Boholano - New Loon |  |  | Road Maintenance | 4.77 | MBA | a) | 140549.84 | a) | 01/03/19 | e) | - | a) | 140549.84 | a) | 100% | c) | 100% | a) | 15 | Completed |  | 1 | 4
031 | [7 empty] | b) | Crucio | b) | 02/18/19 | f) | - | b) | 140549.84 | b) | - | d) | - | b) | 450 |  |  | 1 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 40,056.38 | [8 empty] | 1 | 4
[8 empty] | d) | - | d) | - | [12 empty] | 1 | 4
4
|  | Jct. New Boholano - New Loon |  |  | Road Maintenance | 4.77 | CBRMC | a) | 169521.51 | a) | 01/03/19 | e) | - | a) | 169521.51 | a) | 100% | c) | 100% | a) | 16 | Completed |  | 1 | 4
031 | [7 empty] | b) | Crucio | b) | 03/28/19 | f) | - | b) | 169521.51 | b) | - | d) | - | b) | 450 |  |  | 1 | 4
[8 empty] | c) | NEW LOON FA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [8 empty] | 1 | 4
[8 empty] | d) | 3 quarters | d) | - | [12 empty] | 1 | 4
|  | Florida-Suaon-Jct. Gupitan |  |  | Road Maintenance | 15.57 | MBA | a) | 707038.05 | a) | 01/03/19 | e) | - | a) | 707038.05 | a) | 100% | c) | 100% | a) | 15 | Completed |  | 1 | 4
032 | [7 empty] | b) | Crucio | b) | 01/16/19 | f) | - | b) | 707038.05 | b) | - | d) | - | b) | 450 |  |  | 1 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 226,.062.60 | [8 empty] | 1 | 4
[8 empty] | d) | - | d) | - | [12 empty] | 1 | 4
|  | Florida-Suaon-Jct. Gupitan |  |  | Road Maintenance | 15.57 | CBRMC | a) | 419094.85 | a) | 01/03/19 | e) | - | a) | 419094.85 | a) | 100% | c) | 100% | a) | 16 | Completed |  | 1 | 4
032 | [7 empty] | b) | Crucio | b) | 03/28/19 | f) | - | b) | 419094.85 | b) | - | d) | - | b) | 450 |  |  | 1 | 4
[8 empty] | c) | SUPRA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [8 empty] | 1 | 4
[8 empty] | d) | 3 quarters | d) | - | [12 empty] | 1 | 4
|  | Km. 15, Kipalili-New Loon |  |  | Road Maintenance | 6.93 | MBA | a) | 367659.97 | a) | 01/03/19 | e) | - | a) | 367659.97 | a) | 100% | c) | 100% | a) | 15 | Completed |  | 1 | 4
034 | [7 empty] | b) | Crucio | b) | 02/01/19 | f) | - | b) | 367659.97 | b) | - | d) | - | b) | 450 |  |  | 1 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 112,175.78 | [8 empty] | 1 | 4
[8 empty] | d) | - | d) | - | [12 empty] | 1 | 4
|  | Km. 15, Kipalili-New Loon |  |  | Road Maintenance | 6.93 | CBRMC | a) | 237801.01 | a) | 01/03/19 | e) | - | a) | 237801.01 | a) | 100% | c) | 100% | a) | 16 | Completed |  | 1 | 4
034 | [7 empty] | b) | Crucio | b) | 03/26/19 | f) | - | b) | 237801.01 | b) | - | d) | - | b) | 480 |  |  | 1 | 4
[8 empty] | c) | KIPALILI FA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [8 empty] | 1 | 4
[8 empty] | d) | 3 quarters | d) | - | [12 empty] | 1 | 4
|  | Jct. Suaon-Libuton |  |  | Road Maintenance | 7.26 | MBA | a) | 44015.68 | a) | 01/03/19 | e) | - | a) | 44015.68 | a) | 100% | c) | 100% | a) | 15 | Completed |  |  | 4
035 | [7 empty] | b) | Crucio | b) | 01/16/19 | f) | - | b) | 44015.68 | b) | - | d) | - | b) | 450 |  |  | 1 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 24,980.86 | [8 empty] | 1 | 4
[8 empty] | d) | - | d) | - | [12 empty] | 1 | 4
|  | Jct. Suaon-Libuton |  |  | Road Maintenance | 7.26 | CBRMC | a) | 91664.91 | a) | 01/03/19 | e) | - | a) | 91664.91 | a) | 100% | c) | 100% | a) | 16 | Completed |  | 1 | 4
035 | [7 empty] | b) | Crucio | b) | 03/22/19 | f) | - | b) | 91664.91 | b) | - | d) | - | b) | 480 |  |  | 1 | 4
[8 empty] | c) | AALLI | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [8 empty] | 1 | 4
[8 empty] | d) | 3 quarters | d) | - | [12 empty] | 1 | 4
[24 empty] | 1 | 4
|  | Datu Balong - Pinamuno |  |  | Road Maintenance | 2.74 | MBA | a) | 95458.24 | a) | 01/03/19 | e) | - | a) | 95458.24 | a) | 100% | c) | 100% | a) | 15 | Completed |  |  | 4
040 | [7 empty] | b) | Crucio | b) | 03/01/19 | f) | - | b) | 95458.24 | b) | - | d) | - | b) | 450 |  |  | 1 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 12,625.00 | [8 empty] | 1 | 4
[8 empty] | d) | - | d) | - | [12 empty] | 1 | 4
|  | Datu Balong - Pinamuno |  |  | Road Maintenance | 2.74 | CBRMC | a) | 63570.57 | a) | 01/03/19 | e) | - | a) | 63570.57 | a) | 100% | c) | 100% | a) | 16 | Completed |  | 1 | 4
040 | [7 empty] | b) | Crucio | b) | 03/28/19 | f) | - | b) | 63570.57 | b) | - | d) | - | b) | 480 |  |  | 1 | 4
[8 empty] | c) | DATU BALONG FA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [8 empty] | 1 | 4
[8 empty] | d) | 3 quarters | d) | - | [12 empty] | 1 | 4
|  | Sawata - Mamangan - Pinamuno |  |  | Road Maintenance | 14.48 | MBA | a) | 545390.17 | a) | 01/03/19 | e) | - | a) | 545390.17 | a) | 100% | c) | 100% | a) | 15 | Completed |  | 1 | 4
041 | [7 empty] | b) | Crucio | b) | 02/01/19 | f) | - | b) | 545390.17 | b) | - | d) | - | b) | 450 |  |  | 1 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 196,076.60 | [8 empty] | 1 | 4
[8 empty] | d) | - | d) | - | [12 empty] | 1 | 4
|  | Sawata - Mamangan - Pinamuno |  |  | Road Maintenance | 14.48 | CBRMC | a) | 508564.54 | a) | 01/03/19 | e) | - | a) | 508564.54 | a) | 100% | c) | 100% | a) | 16 | Completed |  | 1 | 4
041 | [7 empty] | b) | Crucio | b) | 03/22/19 | f) | - | b) | 508564.54 | b) | - | d) | - | b) | 480 |  |  | 1 | 4
[8 empty] | c) | SAWATA DFA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [8 empty] | 1 | 4
[8 empty] | d) | 3 quarters | d) | - | [12 empty] | 1 | 4
|  | Igangon - Sawata |  |  | Road Maintenance | 9.66 | MBA | a) | 497447.77 | a) | 01/03/19 | e) | - | a) | 497447.77 | a) | 100% | c) | 100% | a) | 15 | Completed |  | 1 | 4
042 | [7 empty] | b) | Crucio | b) | 02/01/19 | f) | - | b) | 497447.77 | b) | - | d) | - | b) | 450 |  |  | 1 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [8 empty] | 1 | 4
[8 empty] | d) | - | d) | - | [12 empty] | 1 | 4
|  | Igangon - Sawata |  |  | Road Maintenance | 9.66 | CBRMC | a) | 197775.1 | a) | 01/03/19 | e) | - | a) | 197775.1 | a) | 100% | c) | 100% | a) | 16 | Completed |  | 1 | 4
042 | [7 empty] | b) | Crucio | b) | 03/22/19 | f) | - | b) | 197775.1 | b) | - | d) | - | b) | 480 |  |  | 1 | 4
[8 empty] | c) | SAWATA DFA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [8 empty] | 1 | 4
[8 empty] | d) | 3 quarters | d) | - | [12 empty] | 1 | 4
4
4
|  | New Corella - Sto. Niño - Macgum |  |  | Road Maintenance | 17.11 | MBA | a) | 606294.08 | a) | 01/03/19 | e) | - | a) | 606294.08 | a) | 100% | c) | 100% | a) | 15 | Completed |  | 1 | 4
044 | [7 empty] | b) | Crucio | b) | 01/03/19 | f) | - | b) | 606294.08 | b) | - | d) | - | b) | 450 |  |  | 1 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 246,619.77 | [8 empty] | 1 | 4
[8 empty] | d) | - | d) | - | [12 empty] | 1 | 4
|  | New Corella - Sto. Niño - Macgum |  |  | Road Maintenance | 17.11 | CBRMC | a) | 308434.97 | a) | 01/03/19 | e) | - | a) | 308434.97 | a) | 100% | c) | 100% | a) | 16 | Completed |  | 1 | 4
044 | [7 empty] | b) | Crucio | b) | 03/26/19 | f) | - | b) | 308434.97 | b) | - | d) | - | b) | 480 |  |  | 1 | 4
[8 empty] | c) | SAN ISIDRO FA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [8 empty] | 1 | 4
[8 empty] | d) | 3 quarters | d) | - | [12 empty] | 1 | 4
|  | Tagaytay - Buan |  |  | Road Maintenance | 4.92 | MBA | a) | 173197.37 | a) | 01/03/19 | e) | - | a) | 173197.37 | a) | 100% | c) | 100% | a) | 15 | Completed |  | 1 | 4
045 | [7 empty] | b) | Crucio | b) | 03/18/19 | f) | - | b) | 173197.37 | b) | - | d) | - | b) | 450 |  |  | 1 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 26254.58 | [8 empty] | 1 | 4
[8 empty] | d) | - | d) | - | [12 empty] | 1 | 4
|  | Tagaytay - Buan |  |  | Road Maintenance | 4.92 | CBRMC | a) | 131850.07 | a) | 01/03/19 | e) | - | a) | 131850.07 | a) | 100% | c) | 100% | a) | 16 | Completed |  | 1 | 4
045 | [7 empty] | b) | Crucio | b) | 03/22/19 | f) | - | b) | 131850.07 | b) | - | d) | - | b) | 480 |  |  | 1 | 4
[8 empty] | c) | BUAN IFA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [8 empty] | 1 | 4
[8 empty] | d) | 3 quarters | d) | - | [12 empty] | 1 | 4
|  | limbaan - Sto. Niño |  |  | Road Maintenance | 3.19 | MBA | a) | 153706.77 | a) | 01/03/19 | e) | - | a) | 153706.77 | a) | 100% | c) | 100% | a) | 15 | Completed |  | 1 | 4
049 | [7 empty] | b) | Crucio | b) | 03/01/19 | f) | - | b) | 153706.77 | b) | - | d) | - | b) | 450 |  |  | 1 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 32534.49 | [8 empty] | 1 | 4
[8 empty] | d) | - | d) | - | [12 empty] | 1 | 4
|  | limbaan - Sto. Niño |  |  | Road Maintenance | 3.19 | CBRMC | a) | 53657.51 | a) | 01/03/19 | e) | - | a) | 53657.51 | a) | 100% | c) | 100% | a) | - | Completed |  | 1 | 4
049 | [7 empty] | b) | Crucio | b) | - | f) | - | b) | 53657.51 | b) | - | d) | - | b) | - |  |  | 1 | 4
[8 empty] | c) | - | c) | - | g) | 2019-12-31 | c) | - | [8 empty] | 1 | 4
[8 empty] | d) | - | d) | - | [12 empty] | 1 | 4
|  | Del Pilar - Jct. Silangan |  |  | Road Maintenance | 4.17 | MBA | a) | 187097.4 | a) | 01/03/19 | e) | - | a) | 187097.4 | a) | 100% | c) | 100% | a) | 15 | Completed |  | 1 | 4
051 | [7 empty] | b) | Crucio | b) | 03/18/19 | f) | - | b) | 187097.4 | b) | - | d) | - | b) | 450 |  |  | 1 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 94181.74 | [8 empty] | 1 | 4
[8 empty] | d) | - | d) | - | [12 empty] | 1 | 4
|  | Del Pilar - Jct. Silangan |  |  | Road Maintenance | 4.17 | CBRMC | a) | 113014.34 | a) | 01/03/19 | e) | - | a) | 113014.34 | a) | 100% | c) | 100% | a) | 16 | Completed |  | 1 | 4
051 | [7 empty] | b) | Crucio | b) | 03/26/19 | f) | - | b) | 113014.34 | b) | - | d) | - | b) | 480 |  |  | 1 | 4
[8 empty] | c) | DURIAN DACUDAO | c) | 12/31/19 | g) | - | c) | - | [8 empty] | 1 | 4
[8 empty] | d) | 3 quarters | d) | - | [12 empty] | 1 | 4
|  | New Corella - New Sambog - Silangan |  |  | Road Maintenance | 5.1 | MBA | a) | 201994.35 | a) | 01/03/19 | e) | - | a) | 201994.35 | a) | 100% | c) | 100% | a) | 15 | Completed |  | 1 | 4
052 | [7 empty] | b) | Crucio | b) | 03/01/19 | f) | - | b) | 201994.35 | b) | - | d) | - | b) | 450 |  |  | 1 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 63402.48 | [8 empty] | 1 | 4
[8 empty] | d) | - | d) | - | [12 empty] | 1 | 4
|  | New Corella - New Sambog - Silangan |  |  | Road Maintenance | 5.1 | CBRMC | a) | 131850.07 | a) | 01/03/19 | e) | - | a) | 131850.07 | a) | 100% | c) | 100% | a) | 16 | Completed |  | 1 | 4
052 | [7 empty] | b) | Crucio | b) | 03/26/19 | f) | - | b) | 131850.07 | b) | - | d) | - | b) | 480 |  |  | 1 | 4
[8 empty] | c) | DURIAN DACUDAO | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [8 empty] | 1 | 4
[8 empty] | d) | 3 quarters | d) | - | [12 empty] | 1 | 4
|  | Sta. Fe - Del Monte |  |  | Road Maintenance | 3.34 | MBA | a) | 37923.51 | a) | 01/03/19 | e) | - | a) | 37923.51 | a) | 100% | c) | 100% | a) | 15 | Completed |  | 1 | 4
056 | [7 empty] | b) | Crucio | b) | 03/18/19 | f) | - | b) | 37923.51 | b) | - | d) | - | b) | 450 |  |  | 1 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 36595.13 | [8 empty] | 1 | 4
[8 empty] | d) | - | d) | - | [12 empty] | 1 | 4
|  | Sta. Fe - Del Monte |  |  | Road Maintenance | 3.34 | CBRMC | a) | 70633.96 | a) | 01/03/19 | e) | - | a) | 70633.96 | a) | 100% | c) | 100% | a) | 16 | Completed |  | 1 | 4
056 | [7 empty] | b) | Crucio | b) | 03/21/19 | f) | - | b) | 70633.96 | b) | - | d) | - | b) | 480 |  |  | 1 | 4
[8 empty] | c) | DEL MONTE CACAO | c) | 12/31/19 | g) | 2019-12-31 | c) | 4,872.18 | [8 empty] | 1 | 4
[8 empty] | d) | 3 quarters | d) | - | [12 empty] | 1 | 4
|  | New Corella - New Bohol |  |  | Road Maintenance | 11.54 | MBA | a) | 356226.67 | a) | 01/03/19 | e) | - | a) | 356226.67 | a) | 100% | c) | 100% | a) | 15 | Completed |  |  | 4
058 | [7 empty] | b) | Crucio | b) | 02/01/19 | f) | - | b) | 356226.67 | b) | - | d) | - | b) | 450 |  |  | 1 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 110,982.71 | [8 empty] | 1 | 4
[8 empty] | d) | - | d) | - | [12 empty] | 1 | 4
|  | New Corella - New Bohol |  |  | Road Maintenance | 11.54 | CBRMC | a) | 190711.7 | a) | 01/03/19 | e) | - | a) | 190711.7 | a) | 100% | c) | 100% | a) | 16 | Completed |  | 1 | 4
058 | [7 empty] | b) | Crucio | b) | 03/22/19 | f) | - | b) | 190711.7 | b) | - | d) | - | b) | 480 |  |  | 1 | 4
[8 empty] | c) | SAN JOSE COCONUT | c) | 12/31/19 | g) | 2019-12-31 | c) | 5,847.18 | [8 empty] | 1 | 4
[8 empty] | d) | 3 quarters | d) | - | [12 empty] | 1 | 4
[24 empty] | 1 | 4
4
|  | Jct. Carcor - Prk. 9 Bagsak |  |  | Road Maintenance | 2.5 | MBA | a) | 108618.49 | a) | 01/03/19 | e) | - | a) | 108618.49 | a) | 100% | c. | 100% | a) | 15 | Completed
059 | [7 empty] | b) | Crucio | b) | 03/01/19 | f) | - | b) | 108618.49 | b) | - | d) |  | b) | 480 |  |  | 1 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 79952.88 | [8 empty] | 1 | 4
[8 empty] | d) | - | d) | - | [12 empty] | 1 | 4
[24 empty] | 1 | 4
4
4
|  | Jct. Carcor - Prk. 9 Bagsak |  |  | Road Maintenance | 2.5 | CBRMC | a) | 42284.76 | a) | 01/03/19 | e) | - | a) | 42284.76 | a) | 100% | c) | 100% | a) | 16 | Completed |  |  | 4
059 | [7 empty] | b) | Crucio | b) | 03/22/19 | f) | - | b) | 42284.76 | b) | - | d) | - | b) | 480 |  |  | 1 | 4
[8 empty] | c) | CARCOR MOTOR | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [8 empty] | 1 | 4
[8 empty] | d) | 3 quarters | d) | - | [12 empty] | 1 | 4
|  | Carcor - Jct. Kauswagan |  |  | Road Maintenance | 4.32 | MBA | a) | 264514.71 | a) | 01/03/19 | e) | - | a) | 264514.71 | a) | 100% | c) | 100% | a) | 15 | Completed |  | 1 | 4
060 | [7 empty] | b) | Crucio | b) | 03/18/19 | f) | - | b) | 264514.71 | b) | - | d) |  | b) | 450 |  |  | 1 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 80733.11 | [8 empty] | 1 | 4
[8 empty] | d) | - | d) | - | [12 empty] | 1 | 4
|  | Carcor - Jct. Kauswagan |  |  | Road Maintenance | 4.32 | CBRMC | a) | 48398.27 | a) | 01/03/19 | e) | - | a) | 48398.27 | a) | 100% | c) | 100% | a) | 16 | Completed |  |  | 4
060 | [7 empty] | b) | Crucio | b) | 03/22/19 | f) | - | b) | 48398.27 | b) | - | d) | - | b) | 480 |  |  | 1 | 4
[8 empty] | c) | CARCOR MOTOR | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [8 empty] | 1 | 4
[8 empty] | d) | 3 quarters | d) | - | [12 empty] | 1 | 4
|  | Del Pilar - Prk 9 Bagsak - San Jose |  |  | Road Maintenance | 4.99 | MBA | a) | 170215.76 | a) | 01/03/19 | e) | - | a) | 170215.76 | a) | 100% | c) | 100% | a) | 15 | Completed |  | 1 | 4
061 | [7 empty] | b) | Crucio | b) | 03/01/19 | f) | - | b) | 170215.76 | b) | - | d) | - | b) | 450 |  |  | 1 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 87595.63 | [8 empty] | 1 | 4
[8 empty] | d) | - | d) | - | [12 empty] | 1 | 4
|  | Del Pilar - Prk 9 Bagsak - San Jose |  |  | Road Maintenance | 4.99 | CBRMC | a) | 223674.22 | a) | 01/03/19 | e) | - | a) | 223674.22 | a) | 100% | c) | 100% | a) | 16 | Completed |  | 1 | 4
061 | [7 empty] | b) | Crucio | b) | 03/22/19 | f) | - | b) | 223674.22 | b) | - | d) | - | b) | 480 |  |  | 1 | 4
[8 empty] | c) | SAN JOSE COCONUT | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [8 empty] | 1 | 4
[8 empty] | d) | 3 quarters | d) | - | [12 empty] | 1 | 4
|  | San Juan - New Talisay |  |  | Road Maintenance | 5.13 | MBA | a) | 306261.25 | a) | 01/03/19 | e) | - | a) | 306261.25 | a) | 100% | c) | 100% | a) | 15 | Completed |  | 1 | 4
063 | [7 empty] | b) | Crucio | b) | 02/01/19 | f) | - | b) | 306261.25 | b) | - | d) | - | b) | 450 |  |  | 1 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 85123.48 | [8 empty] | 1 | 4
[8 empty] | d) | - | d) | - | [12 empty] | 1 | 4
|  | San Juan - New Talisay |  |  | Road Maintenance | 5.13 | CBRMC | a) | 93906.31 | a) | 01/03/19 | e) | - | a) | 93906.31 | a) | 100% | c) | 100% | a) | 16 | Completed |  |  | 4
063 | [7 empty] | b) | Crucio | b) | 03/26/19 | f) | - | b) | 93906.31 | b) | - | d) | - | b) | 480 |  |  | 1 | 4
[8 empty] | c) | NEW TALISAY IAWA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [8 empty] | 1 | 4
[8 empty] | d) | 3 quarters | d) | - | [12 empty] | 1 | 4
|  | San Juan - kauswagan - New Cortez |  |  | Road Maintenance | 3.22 | MBA | a) | 187879.04 | a) | 01/03/19 | e) | - | a) | 187879.04 | a) | 100% | c) | 100% | a) | 15 | Completed |  | 1 | 4
064 | [7 empty] | b) | Crucio | b) | 03/18/19 | f) | - | b) | 187879.04 | b) | - | d) | - | b) | 450 |  |  | 1 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 3,025.00 | [8 empty] | 1 | 4
[8 empty] | d) | - | d) | - | [12 empty] | 1 | 4
4
4
|  | San Juan - kauswagan - New Cortez |  |  | Road Maintenance | 3.22 | CBRMC | a) | 63298.26 | a) | 01/03/19 | e) | - | a) | 63298.26 | a) | 100% | c) | 100% | a) | 16 | Completed |  |  | 4
064 | [7 empty] | b) | Crucio | b) | 03/22/19 | f) | - | b) | 63298.26 | b) | - | d) | - | b) | 480 |  |  | 1 | 4
[8 empty] | c) | SAN JOSE COCONUT | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [8 empty] | 1 | 4
[8 empty] | d) | 3 quarters | d) | - | [12 empty] | 1 | 4
|  | New Bohol - Jct. El Unido |  |  | Road Maintenance | 2.12 | MBA | a) | 54989.06 | a) | 01/03/19 | e) | - | a) | 54989.06 | a) | 100% | c) | 100% | a) | 15 | Completed |  |  | 4
065 | [7 empty] | b) | Crucio | b) | 03/01/19 | f) | - | b) | 54989.06 | b) | - | d) | - | b) | 450 |  |  | 1 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 21021.99 | [8 empty] | 1 | 4
[8 empty] | d) | - | d) | - | [12 empty] | 1 | 4
|  | New Bohol - Jct. El Unido |  |  | Road Maintenance | 2.12 | CBRMC | a) | 58861.64 | a) | 01/03/19 | e) | - | a) | 58861.64 | a) | 100% | c) | 100% | a) | 16 | Completed |  | 1 | 4
065 | [7 empty] | b) | Crucio | b) | 03/26/19 | f) | - | b) | 58861.64 | b) | - | d) | - | b) | 480 |  |  | 1 | 4
[8 empty] | c) | MANDISKAB TRIBAL | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [8 empty] | 1 | 4
[8 empty] | d) | 3 quarters | d) | - | [12 empty] | 1 | 4
[24 empty] | 1 | 4
4
|  | New Corella - El unido - Jct. Mesaoy |  |  | Road Maintenance | 8.63 | MBA | a) | 388002.46 | a) | 01/03/19 | e) | - | a) | 388002.46 | a) | 100% | c) | 100% | a) | 15 | Completed |  |  | 4
066 | [7 empty] | b) | Crucio | b) | 02/11/19 | f) | - | b) | 388002.46 | b) | - | d) | - | b) | 450 |  |  | 1 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 58142.76 | [8 empty] | 1 | 4
[8 empty] | d) | - | d) | - | [12 empty] | 1 | 4
|  | New Corella - El unido - Jct. Mesaoy |  |  | Road Maintenance | 8.63 | CBRMC | a) | 233092.08 | a) | 01/03/19 | e) | - | a) | 233092.08 | a) | 100% | c) | 100% | a) | 16 | Completed |  | 1 | 4
066 | [7 empty] | b) | Crucio | b) | 03/26/19 | f) | - | b) | 233092.08 | b) | - | d) | - | b) | 480 |  |  | 1 | 4
[8 empty] | c) | MANDISKAB TRIBAL | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [8 empty] | 1 | 4
[8 empty] | d) | 3 quarters | d) | - | [12 empty] | 1 | 4
|  | Mesaoy - Dasing |  |  | Road Maintenance | 1.39 | MBA | a) | 29749.5 | a) | 01/03/19 | e) | - | a) | 29749.5 | a) | 100% | c) | 100% | a) | 15 | Completed |  | 1 | 4
067 | [7 empty] | b) | Crucio | b) | 03/18/19 | f) | - | b) | 29749.5 | b) | - | d) | - | b) | 450 |  |  | 1 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 10000 | [8 empty] | 1 | 4
[8 empty] | d) | - | d) | - | [12 empty] | 1 | 4
|  | Mesaoy - Dasing |  |  | Road Maintenance | 1.39 | CBRMC | a) | 54152.71 | a) | 01/03/19 | e) | - | a) | 54152.71 | a) | 100% | c) | 100% | a) | 16 | Completed |  | 1 | 4
067 | [7 empty] | b) | Crucio | b) | 03/26/19 | f) | - | b) | 54152.71 | b) | - | d) | - | b) | 480 |  |  | 1 | 4
[8 empty] | c) | MANDISKAB TRIBAL | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [8 empty] | 1 | 4
[8 empty] | d) | 3 quarters | d) | - | [12 empty] | 1 | 4
|  | Jct. San Juan - Jct. Mesaoy |  |  | Road Maintenance | 1.82 | MBA | a) | 106788.95 | a) | 01/03/19 | e) | - | a) | 106788.95 | a) | 100% | c) | 100% | a) | 15 | Completed |  | 1 | 4
068 | [7 empty] | b) | Crucio | b) | 03/01/19 | f) | - | b) | 106788.95 | b) | - | d) | - | b) | 450 |  |  | 1 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 17502.68 | [8 empty] | 1 | 4
[8 empty] | d) | - | d) | - | [12 empty] | 1 | 4
|  | Jct. San Juan - Jct. Mesaoy |  |  | Road Maintenance | 1.82 | CBRMC | a) | 35180.83 | a) | 01/03/19 | e) | - | a) | 35180.83 | a) | 100% | c) | 100% | a) | 16 | Completed |  | 1 | 4
068 | [7 empty] | b) | Crucio | b) | 03/26/19 | f) | - | b) | 35180.83 | b) | - | d) | - | b) | 480 |  |  | 1 | 4
[8 empty] | c) | MANDISKAB TRIBAL | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [8 empty] | 1 | 4
[8 empty] | d) | 3 quarters | d) | - | [12 empty] | 1 | 4
|  | Mesaoy - Jct. Mahayahay |  |  | Road Maintenance | 4.6 | MBA | a) | 146984.46 | a) | 01/03/19 | e) | - | a) | 146984.46 | a) | 100% | c) | 100% | a) | 15 | Completed |  | 1 | 4
069 | [7 empty] | b) | Crucio | b) | 03/18/19 | f) | - | b) | 146984.46 | b) | - | d) | - | b) | 450 |  |  | 1 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 7618.27 | [8 empty] | 1 | 4
[8 empty] | d) | - | d) | - | [12 empty] | 1 | 4
|  | Mesaoy - Jct. Mahayahay |  |  | Road Maintenance | 4.6 | CBRMC | a) | 160103.65 | a) | 01/03/19 | e) | - | a) | 160103.65 | a) | 100% | c) | 100% | a) | 16 | Completed |  |  | 4
069 | [7 empty] | b) | Crucio | b) | 03/22/19 | f) | - | b) | 160103.65 | b) | - | d) | - | b) | 480 |  |  | 1 | 4
[8 empty] | c) | MAHAYAHAY IFA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [8 empty] | 1 | 4
[8 empty] | d) | 3 quarters | d) | - | [12 empty] | 1 | 4
4
4
|  | Mesaoy - New bohol |  |  | Road Maintenance | 5.36 | MBA | a) | 165361.13 | a) | 01/03/19 | e) | - | a) | 165361.13 | a) | 100% | c) | 100% | a) | 15 | Completed |  |  | 4
070 | [7 empty] | b) | Crucio | b) | 03/01/19 | f) | - | b) | 165361.13 | b) | - | d) | - | b) | 480 |  |  | 1 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 2543.9 | [8 empty] | 1 | 4
[8 empty] | d) | - | d) | - | [12 empty] | 1 | 4
|  | Mesaoy - New bohol |  |  | Road Maintenance | 5.36 | CBRMC | a) | 224851.45 | a) | 01/03/19 | e) | - | a) | 224851.45 | a) | 100% | c) | 100% | a) | 16 | Completed |  |  | 4
070 | [7 empty] | b) | Crucio | b) | 03/26/19 | f) | - | b) | 224851.45 | b) | - | d) | - | b) | 480 |  |  | 1 | 4
[8 empty] | c) | MANDISKAB TRIBAL | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [8 empty] | 1 | 4
[8 empty] | d) | 3 quarters | d) | - | [12 empty] | 1 | 4
|  | Bdry. Tagum - Baca - New Corella |  |  | Road Maintenance | 13.01 | MBA | a) | 217182.9 | a) | 01/03/19 | e) | - | a) | 217182.9 | a) | 100% | c) | 100% | a) | 15 | Completed |  | 1 | 4
071 | [7 empty] | b) | Crucio | b) | 03/18/19 | f) | - | b) | 217182.9 | b) | - | d) | - | b) | 450 |  |  | 1 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 19550 | [8 empty] | 1 | 4
[8 empty] | d) | - | d) | - | [12 empty] | 1 | 4
|  | Bdry. Tagum - Baca - New Corella |  |  | Road Maintenance | 13.01 | CBRMC | a) | 214256.36 | a) | 01/03/19 | e) | - | a) | 214256.36 | a) | 100% | c) | 100% | a) | 16 | Completed |  | 1 | 4
071 | [7 empty] | b) | Crucio | b) | 03/26/19 | f) | - | b) | 214256.36 | b) | - | d) | - | b) | 480 |  |  | 1 | 4
[8 empty] | c) | DURIAN DACUDAO | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [8 empty] | 1 | 4
[8 empty] | d) | 3 quarters | d) | - | [12 empty] | 1 | 4
|  | Prk. 1, Maunlom - Prk. 6 Maunlom Road |  |  | Road Maintenance | 3.56 | MBA | a) | 150912.87 | a) | 01/03/19 | e) | - | a) | 150912.87 | a) | 100% | c) | 100% | a) | 15 | Completed |  | 1 | 4
147 | [7 empty] | b) | Crucio | b) | 03/01/19 | f) | - | b) | 150912.87 | b) | - | d) | - | b) | 450 |  |  | 1 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 23025 | [8 empty] | 1 | 4
[8 empty] | d) | - | d) | - | [12 empty] | 1 | 4
|  | Prk. 1, Maunlom - Prk. 6 Maunlom Road |  |  | Road Maintenance | 3.56 | CBRMC | a) | 63973.36 | a) | 01/03/19 | e) | - | a) | 63973.36 | a) | 100% | c) | 100% | a) | 16 | Completed |  | 1 | 4
147 | [7 empty] | b) | Crucio | b) | 03/22/19 | f) | - | b) | 63973.36 | b) | - | d) | - | b) | 480 |  |  | 1 | 4
[8 empty] | c) | THE BEST VEGETABLE | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [8 empty] | 1 | 4
[8 empty] | d) | 3 quarters | d) | - | [12 empty] | 1 | 4
[24 empty] | 1 | 4
|  | New Visayas - Binancian |  |  | Road Maintenance | 7.77 | MBA | a) | 14814.34 | a) | 01/03/19 | e) | - | a) | 14814.34 | a) | 100% | c) | 100% | a) | 15 | Completed |  |  | 44
149 | [7 empty] | b) | Crucio | b) | 03/18/19 | f) | - | b) | 14814.34 | b) | - | d) | - | b) | 450 |  |  | 1 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 5,000.00 | [8 empty] | 1 | 4
[8 empty] | d) | - | d) | - | [12 empty] | 1 | 4
|  | New Visayas - Binancian |  |  | Road Maintenance | 7.77 | CBRMC | a) | 129495.6 | a) | 01/03/19 | e) | - | a) | 129495.6 | a) | 100% | c) | 100% | a) | 16 | Completed |  | 1 | 4
149 | [7 empty] | b) | Crucio | b) | 03/22/19 | f) | - | b) | 129495.6 | b) | - | d) | - | b) | 480 |  |  | 1 | 4
[8 empty] | c) | BUAN IFA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [8 empty] | 1 | 4
[8 empty] | d) | 3 quarters | d) | - | [12 empty] | 1 | 4
|  | Datu Balong - Prk. Mamalian |  |  | Road Maintenance | 3.46 | MBA | a) | 117454.89 | a) | 01/03/19 | e) | - | a) | 117454.89 | a) | 100% | c) | 39.37% | a) | 15 | Completed |  | 1 | 4
150 | [7 empty] | b) | Crucio | b) | 03/18/19 | f) | - | b) | 117454.89 | b) | - | d) | - | b) | 450 |  |  | 1 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 10115 | [8 empty] | 1 | 4
[8 empty] | d) | - | d) | - | [12 empty] | 1 | 4
|  | Datu Balong - Prk. Mamalian |  |  | Road Maintenance | 3.46 | CBRMC | a) | 59264.42 | a) | 01/03/19 | e) | - | a) | 59264.42 | a) | 100% | c) | 100% | a) | 16 | Completed |  | 1 | 4
150 | [7 empty] | b) | Crucio | b) | 03/28/19 | f) | - | b) | 59264.42 | b) | - | d) | - | b) | 480 |  |  | 1 | 4
[8 empty] | c) | DATU BALONG FA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [8 empty] | 1 | 4
[8 empty] | d) | 3 quarters | d) | - | [12 empty] | 1 | 4
4
4
4
4
4
4
4
4
4
4
4
A.2 GENERAL FUND CY 2019 |  |  |  |  | Road Maintenance | KM | MBA/CBRMC | a) | 11,618,834.00 | a) | 01/03/19 | e) | - | a) | 11,618,834.00 | a) | 66% | c) | 66% | a) | 42 | See list of Provincial Roads
Road ID |  | 1. Maintenance Of Various Prov'l. Roads and Bridges Dist 2 |  |  |  | 288.26 |  | b) | Matuguinas | b) | 01/03/19 | f) | - | b) | 11,618,834.00 | b) | - | d) | - | b) | 924 |  |  | FS
[8 empty] | c) | PEO/CBRMC | c) | 12/31/19 | g) | - | c) | - | [8 empty] | AC
11DAN | [9 empty] | d) | - | [12 empty] | AC
[8 empty] | d) | 261 days | d) | - | [12 empty] | AC
|  | Cebulano - Mangalcal |  |  | Road Maintenance | 4.17 | MBA | a) | 142161.87 | a) | 01/03/19 | e) | - | a) | 142161.87 | a) | 100% | c) | 100% | a) | 9 | Completed |  | AC | 4
| 073 | [6 empty] | b) | Clar | b) | 2019-01-15 | f) | - | b) | 142161.87 | b) | - | d) | - | b) | 18 |  |  | 2 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 118,609.29 | [8 empty] | 2 | 4
[8 empty] | d) | - | d) | - | [12 empty] | 2 | 4
|  | Tubod - basa - Mangalcal |  |  | Road Maintenance | 3.93 | MBA | a) | 156875.9 | a) | 01/03/19 | e) | - | a) | 156875.9 | a) | 100% | c) | 100% | a) | 9 | Completed |  | 2 | 4
074 | [7 empty] | b) | Clar | b) | 2019-01-15 | f) | - | b) | 156875.9 | b) | - | d) | - | b) | 18 |  |  | 2 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 143,372.65 | [8 empty] | 2 | 4
[8 empty] | d) | - | d) | - | [12 empty] | 2 | 4
|  | Upper Mangalcal - Lower Mangalcal |  |  | Road Maintenance | 2.43 | 0 | a) | 79237.14 | a) | 01/03/19 | e) | - | a) | 79237.14 | a) | 100% | c) | 100% | a) | 9 | Completed |  | 2 | 4
078 | [7 empty] | b) | Clar | b) | 2019-01-14 | f) | - | b) | 79237.14 | b) | - | d) | - | b) | 27 |  |  | 2 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 69,430.97 | [8 empty] | 2 | 4
[8 empty] | d) | - | d) | - | [12 empty] | 2 | 4
|  | Jct. Highway Carmen - Mangalcal - Tubod |  |  | Road Maintenance | 11.34 | MBA | a) | 463135.67 | a) | 01/03/19 | e) | - | a) | 463135.67 | a) | 100% | c) | 100% | a) | 9 | Completed |  | 2 | 4
082 | [7 empty] | b) | Clar | b) | 01/10/19 | f) | - | b) | 463135.67 | b) | - | d) | - | b) | 45 |  |  | 2 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 170,106.43 | [8 empty] | 2 | 4
[8 empty] | d) | - | d) | - | [12 empty] | 2 | 4
|  | Jct. Highway Carmen - Mangalcal - Tubod |  |  | Road Maintenance | 11.34 | 0 | a) | 253557.37 | a) | 01/03/19 | e) | - | a) | 253557.37 | a) | 100% | c) | 100% | a) | 10 | Completed |  | 2 | 4
082 | [7 empty] | b) | Maligro | b) | 03/25/19 | f) | - | b) | 253557.37 | b) | - | d) | - | b) | 40 |  |  | 2 | 4
[8 empty] | c) | TUBOD CENTRO LOWER IRRIGATORS ASSOCIATION | c) | 09/25/19 | g) | 2019-12-31 | c) | - | [8 empty] | 2 | 4
[8 empty] | d) | 3 quarters | d) | - | [12 empty] | 2 | 4
|  | Jct. Highway Sto. Niño - Kabanlakan - La Paz |  |  | Road Maintenance | 2.13 | MBA | a) | 76067.88 | a) | 01/03/19 | e) | - | a) | 76067.88 | a) | 100% | c) | 100% | a) | 9 | Completed |  | 2 | 4
084 | [7 empty] | b) | Clar | b) | 01/10/19 | f) | - | b) | 76067.88 | b) | - | d) | - | b) | 45 |  |  | 2 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 66,477.91 | [8 empty] | 2 | 4
[8 empty] | d) | - | d) | - | [12 empty] | 2 | 4
|  | Ising - Sto Niño |  |  | Road Maintenance | 2.07 | 0 | a) | 82413.14 | a) | 01/03/19 | e) | - | a) | 82413.14 | a) | 100% | c) | 100% | a) | 5 | Completed |  | 2 | 4
085 | [7 empty] | b) | Clar | b) | 01/17/19 | f) | - | b) | 82413.14 | b) | - | d) | - | b) | 15 |  |  | 2 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 27,093.24 | [8 empty] | 2 | 4
[8 empty] | d) | - | d) | - | [12 empty] | 2 | 4
|  | Ising - Sadpodon - Taba - Dila -Dila |  |  | Road Maintenance | 5.68 | MBA | a) | 248941.33 | a) | 01/03/19 | e) | - | a) | 248941.33 | a) | 100% | c) | 100% | a) | 9 | Completed |  | 2 | 4
086 | [7 empty] | b) | Clar | b) | 01/12/19 | f) | - | b) | 248941.33 | b) | - | d) | - | b) | 27 |  |  | 2 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 82,329.02 | [8 empty] | 2 | 4
[8 empty] | d) | - | d) | - |  |  |  | . | [8 empty] | 2 | 4
[24 empty] | 2 | 4
|  | Tuganay - taba |  |  | Road Maintenance | 4.27 | 0 | a) | 291377.9 | a) | 01/03/19 | e) | - | a) | 291377.9 | a) | 70% | c) | 70% | a) | 9 | Completed |  |  | 4
087 | [7 empty] | b) | Clar | b) | 01/09/19 | f) | - | b) | 291377.9 | b) | - | d) | - | b) | 27 |  |  | 2 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 12/31/2019 | c) | 238,412.28 | [8 empty] | 2 | 4
[8 empty] | d) | - | d) | - | [12 empty] | 2 | 4
|  | Jct. Highway Tuganay - Taba |  |  | Road Maintenance | 4.4 | MBA | a) | 32972.82 | a) | 01/03/19 | e) | - | a) | 32972.82 | a) | 65% | c) | 65% | a) | 9 | Completed |  | 2 | 4
088 | [7 empty] | b) | Clar | b) | 01/22/19 | f) | - | b) | 32972.82 | b) | - | d) | - | b) | 18 |  |  | 2 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 12/31/2019 | c) | 22,639.09 | [8 empty] | 2 | 4
[8 empty] | d) | - | d) | - | [12 empty] | 2 | 4
|  | Jct. Highway Ising - Magsaysay |  |  | Road Maintenance | 10.84 | 0 | a) | 417818.12 | a) | 01/03/19 | e) | - | a) | 417818.12 | a) | 60% | c) | 60% | a) | 10 | Completed |  | 2 | 4
089 | [7 empty] | b) | Clar | b) | 01/22/19 | f) | - | b) | 417818.12 | b) | - | d) | - | b) | 50 |  |  | 2 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 12/31/2019 | c) | 313,488.39 | [8 empty] | 2 | 4
[8 empty] | d) | - | d) | - | [12 empty] | 2 | 4
4
4
4
|  | New Camiling - Alejal - Lower Magsaysay |  |  | Road Maintenance | 6.73 | MBA | a) | 240878.08 | a) | 01/03/19 | e) | - | a) | 240878.08 | a) | 80% | c) | 80% | a) | 4 | Completed |  | 2 | 4
091 | [7 empty] | b) | Clar | b) | 01/22/19 | f) | - | b) | 240878.08 | b) | - | d) | - | b) | 20 |  |  | 2 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 12/31/2019 | c) | - | [8 empty] | 2 | 4
[8 empty] | d) | - | d) | - | [12 empty] | 2 | 4
|  | Jct. highway Tuganay - Anibongan |  |  | Road Maintenance | 3.66 | 0 | a) | 150684.44 | a) | 01/03/19 | e) | - | a) | 150684.44 | a) | 100% | c) | 100% | a) | 6 | Completed |  | 2 | 4
094 | [7 empty] | b) | Clar | b) | 01/22/19 | f) | - | b) | 150684.44 | b) | - | d) | - | b) | 18 |  |  | 2 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 12/31/2019 | c) | - | [8 empty] | 2 | 4
[8 empty] | d) | - | d) | - | [12 empty] | 2 | 4
|  | Anibongan - Guadalupe |  |  | Road Maintenance | 2.48 | MBA | a) | 91325.06 | a) | 01/03/19 | e) | - | a) | 91325.06 | a) | 100% | c) | 100% | a) | 9 | Completed |  | 2 | 4
095 | [7 empty] | b) | Clar | b) | 01/23/19 | f) | - | b) | 91325.06 | b) | - | d) | - | b) | 18 |  |  | 2 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 12/31/2019 | c) | - | [8 empty] | 2 | 4
[8 empty] | d) | - | d) | - | [12 empty] | 2 | 4
|  | Tuganay - Anibongan - San Isidro |  |  | Road Maintenance | 7.22 | 0 | a) | 139979.8 | a) | 01/03/19 | e) | - | a) | 139979.8 | a) | 100% | c) | 100% | a) | 9 | Completed |  | 2 | 4
096 | [7 empty] | b) | Clar | b) | 01/24/19 | f) | - | b) | 139979.8 | b) | - | d) | - | b) | 36 |  |  | 2 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 12/31/2019 | c) | 1890.37 | [8 empty] | 2 | 4
[8 empty] | d) | - | d) | - | [12 empty] | 2 | 4
|  | Jct. Anibongan - Prk. 2, 7, 5, San Isidro |  |  | Road Maintenance | 3.14 | MBA | a) | 104378.03 | a) | 01/03/19 | e) | - | a) | 104378.03 | a) | 100% | c) | 100% | a) | 10 | Completed |  | 2 | 4
097 | [7 empty] | b) | Clar | b) | 01/24/19 | f) | - | b) | 104378.03 | b) | - | d) | - | b) | 20 |  |  | 2 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 12/31/2019 | c) | 56,087.50 | [8 empty] | 2 | 4
[8 empty] | d) | - | d) | - | [12 empty] | 2 | 4
|  | Anibongan - Salvacion - Cabay-angan |  |  | Road Maintenance | 6.93 | 0 | a) | 415461.61 | a) | 01/03/19 | e) | - | a) | 415461.61 | a) | 100% | c) | 100% | a) | 9 | Completed |  | 2 | 4
098 | [7 empty] | b) | Clar | b) | 01/25/19 | f) | - | b) | 415461.61 | b) | - | d) | - | b) | 45 |  |  | 2 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 12/31/2019 | c) | - | [8 empty] | 2 | 4
[8 empty] | d) | - | d) | - | [12 empty] | 2 | 4
|  | Jct. Highway Guadalupe - Bdry. Tagum |  |  | Road Maintenance | 7.9 | MBA | a) | 456131.09 | a) | 01/03/19 | e) | - | a) | 456131.09 | a) | 100% | c) | 100% | a) | 9 | Completed |  | 2 | 4
101 | [7 empty] | b) | Clar | b) | 01/25/19 | f) | - | b) | 456131.09 | b) | - | d) | - | b) | 18 |  |  | 2 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 12/31/2019 | c) | - | [8 empty] | 2 | 4
[8 empty] | d) | - | d) | - | [12 empty] | 2 | 4
|  | Jct. Highway Guadalupe - Bdry. Tagum |  |  | Road Maintenance | 7.9 | 0 | a) | 228201.66 | a) | 01/03/19 | e) | - | a) | 228201.66 | a) | 100% | c) | 100% | a) | 8 | Completed |  | 2 | 4
101 | [7 empty] | b) | Maligro | b) | 03/25/19 | f) | - | b) | 228201.66 | b) | - | d) | - | b) | 40 |  |  | 2 | 4
[8 empty] | c) | LAMPIA PAG-ASA IRRIGATORS ASSOCIATION, INC. | c) | 12/25/19 | g) | 12/31/2019 | c) | - | [8 empty] | 2 | 4
[8 empty] | d) | 3 quarters | d) | - | [12 empty] | 2 | 4
|  | Poblacion Dujali - Prk. 8 Dujali |  |  | Road Maintenance | 8.2 | MBA | a) | 285600.05 | a) | 01/03/19 | e) | - | a) | 285600.05 | a) | 100% | c) | 100% | a) | 10 | Completed |  | 2 | 4
105 | [7 empty] | b) | Clar | b) | 01/28/19 | f) | - | b) | 285600.05 | b) | - | d) | - | b) | 50 |  |  | 2 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 12/31/2019 | c) | - | [8 empty] | 2 | 4
[8 empty] | d) | - | d) | - | [12 empty] | 2 | 4
|  | Dujali - San Isidro |  |  | Road Maintenance | 3 | 0 | a) | 130319.3 | a) | 01/03/19 | e) | - | a) | 130319.3 | a) | 100% | c) | 100% | a) | 8 | Completed |  | 2 | 4
107 | [7 empty] | b) | Gamad | b) | 01/28/19 | f) | - | b) | 130319.3 | b) | - | d) | - | b) | 30 |  |  | 2 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 12/31/2019 | c) | 45,943.12 | [8 empty] | 2 | 4
[8 empty] | d) | - | d) | - | [12 empty] | 2 | 4
|  | Prk. 5, RJS - Prk. 6 New Casay |  |  | Road Maintenance | 2.73 | MBA | a) | 235277 | a) | 01/03/19 | e) | - | a) | 235277 | a) | 100% | c) | 100% | a) | 2 | Completed |  | 2 | 4
109 | [7 empty] | b) | Gamad | b) | 01/28/19 | f) | - | b) | 235277 | b) | - | d) | - | b) | 6 |  |  | 2 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 12/31/2019 | c) | 90,745.35 | [8 empty] | 2 | 4
[8 empty] | d) | - | d) | - | [12 empty] | 2 | 4
|  | Prk. 5 - Prk. 1 Pawas Dujali |  |  | Road Maintenance | 2.18 | 0 | a) | 76067.68 | a) | 01/03/19 | e) | - | a) | 76067.68 | a) | 100% | c) | 100% | a) | 10 | Completed |  | 2 | 4
112 | [7 empty] | b) | Gamad | b) | 01/18/19 | f) | - | b) | 76067.68 | b) | - | d) | - | b) | 20 |  |  | 2 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 12/31/2019 | c) | 40,112.50 | [8 empty] | 2 | 4
[8 empty] | d) | - | d) | - | [12 empty] | 2 | 4
|  | Dujali - Balisong - Magupising |  |  | Road Maintenance | 5.52 | MBA | a) | 260591.93 | a) | 01/03/19 | e) | - | a) | 260591.93 | a) | 100% | c) | 100% | a) | 4 | Completed |  | 2 | 4
113 | [7 empty] | b) | Gamad | b) | 01/09/19 | f) | - | b) | 260591.93 | b) | - | d) | - | b) | 8 |  |  | 2 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 12/31/2019 | c) | - | [8 empty] | 2 | 4
[8 empty] | d) | - | d) | - | [12 empty] | 2 | 4
4
4
4
|  | Dujali - Pawas - San Vicente |  |  | Road Maintenance | 4.42 | 0 | a) | 139536.42 | a) | 01/03/19 | e) | - | a) | 139536.42 | a) | 100% | c) | 100% | a) | 10 | Completed |  | 2 | 4
117 | [7 empty] | b) | Gamad | b) | 01/22/19 | f) | - | b) | 139536.42 | b) | - | d) | - | b) | 18 |  |  | 2 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 12/31/2019 | c) | 52,133.86 | [8 empty] | 2 | 4
[8 empty] | d) | - | d) | - | [12 empty] | 2 | 4
|  | Jct. Salvacion - San Vicente - Cabay-angan |  |  | Road Maintenance | 3.45 | MBA | a) | 247460.9 | a) | 01/03/19 | e) | - | a) | 247460.9 | a) | 100% | c) | 100% | a) | 10 | Completed |  | 2 | 4
118 | [7 empty] | b) | Gamad | b) | 01/23/19 | f) | - | b) | 247460.9 | b) | - | d) | - | b) | 18 |  |  | 2 | 4
[8 empty] | c) | PEO | c) | 02/31/19 | g) | 12/31/2019 | c) | 151,887.50 | [8 empty] | 2 | 4
[8 empty] | d) | - | d) | - | [12 empty] | 2 | 4
|  | Jct. Salvacion - San Vicente - Cabay-angan |  |  | Road Maintenance | 3.45 | 0 | a) | 152134.44 | a) | 01/03/19 | e) | - | a) | 152134.44 | a) | 100% | c) | 100% | a) | 8 | Completed |  | 2 | 4
118 | [7 empty] | b) | Gamad | b) | 03/26/19 | f) | - | b) | 152134.44 | b) | - | d) | - | b) | 36 |  |  | 2 | 4
[8 empty] | c) | BALISONG SAN VICENTE IRRIGATORS ASSOCIATION | c) | 12/26/19 | g) | 12/31/2019 | c) | [9 empty] | 2 | 4
[8 empty] | d) | 3 quarters | d) | - | [10 empty] | Completed |  | 2 | 4
|  | Dujali - San Miguel |  |  | Road Maintenance | 3.95 | MBA | a) | 101202.04 | a) | 01/03/19 | e) | - | a) | 101202.04 | a) | 80% | c) | 90% | a) | 11 |  |  | 2 | 4
119 | [7 empty] | b) | Gamad | b) | 01/10/19 | f) | - | b) | 101202.04 | b) | - | d) | - | b) | 22 |  |  | 2 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | - | c) | 90,350.03 | [8 empty] | 2 | 4
[8 empty] | d) | - | d) | - | [12 empty] | 2 | 4
|  | San Miguel - Casig-ang |  |  | Road Maintenance | 2.55 | 0 | a) | 79237.14 | a) | 01/03/19 | e) | - | a) | 79237.14 | a) | 100% | c) | 100% | a) | 10 | Completed |  | 2 | 4
122 | [7 empty] | b) | Gamad | b) | 01/24/19 | f) | - | b) | 79237.14 | b) | - | d) | - | b) | 10 |  |  | 2 | 4
[8 empty] | c) | BALISONG SAN VICENTE IRRIGATORS ASSOCIATION | c) | 12/31/19 | g) | 12/31/2019 | c) | 40,112.50 | [8 empty] | 2 | 4
[8 empty] | d) | - | d) | - | [12 empty] | 2 | 4
|  | Prk. Magsaysay - Lunga-og - Dalisay |  |  | Road Maintenance | 2.81 | MBA | a) | 79762.14 | a) | 01/03/19 | e) | - | a) | 79762.14 | a) | 100% | c) | 100% | a) | 8 | Completed |  | 2 | 4
127 | [7 empty] | b) | Gamad | b) | 01/30/19 | f) | - | b) | 79762.14 | b) | - | d) | - | b) | 8 |  |  | 2 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 12/31/2019 | c) | 40,612.50 | [8 empty] | 2 | 4
[8 empty] | d) | - | d) | - | [12 empty] | 2 | 4
|  | Prk. Apitong - Upper Balisong - Dalisay |  |  | Road Maintenance | 4.6 | 0 | a) | 137846.03 | a) | 01/03/19 | e) | - | a) | 137846.03 | a) | 100% | c) | 100% | a) | 8 | Completed |  | 2 | 4
128 | [7 empty] | b) | Gamad | b) | 01/31/19 | f) | - | b) | 137846.03 | b) | - | d) | - | b) | 8 |  |  | 2 | 4
[8 empty] | c) | BALISONG SAN VICENTE IRRIGATORS ASSOCIATION | c) | 12/31/19 | g) | 12/31/2019 | c) | - | [8 empty] | 2 | 4
[8 empty] | d) | - | d) | - | [12 empty] | 2 | 4
|  | Sitio Paradise - Magkakaisa - Esperanza |  |  | Road Maintenance | 1.75 | MBA | a) | 66552.75 | a) | 01/03/19 | e) | - | a) | 66552.75 | a) | 100% | c) | 100% | a) | 8 | Completed |  | 2 | 4
129 | [7 empty] | b) | 79762.14 | b) | 01/22/19 | f) | - | b) | 66552.75 | b) | - | d) | - | b) | 8 |  |  | 2 | 4
[8 empty] | c) | Gamad | c) | 12/31/19 | g) | 12/31/2019 | c) | 22,246.26 | [8 empty] | 2 | 4
[8 empty] | d) | - | d) | - | [12 empty] | 2 | 4
|  | Los Amigos 1 - Esperanza - Los Amigos 2 |  |  | Road Maintenance | 3.59 | 0 | a) | 101202.04 | a) | 01/03/19 | e) | - | a) | 101202.04 | a) | 100% | c) | 100% | a) | 10 | Completed |  | 2 | 4
130 | [7 empty] | b) | Gamad | b) | 01/24/19 | f) | - | b) | 101202.04 | b) | - | d) | - | b) | 20 |  |  | 2 | 4
[8 empty] | c) | BALISONG SAN VICENTE IRRIGATORS ASSOCIATION | c) | 12/31/19 | g) | 12/31/2019 | c) | 50,837.50 | [8 empty] | 2 | 4
[8 empty] | d) | - | d) | - | [12 empty] | 2 | 4
|  | Mugas - Lunga-og |  |  | Road Maintenance | 2.68 | MBA | a) | 66552.75 | a) | 01/03/19 | e) | - | a) | 91,693.64 | a) | 100% | c) | 100% | a) | 6 | Completed |  | 2 | 4
132 | [7 empty] | b) | 79762.14 | b) | 01/17/19 | f) | - | b) | 91,693.64 | b) | - | d) | - | b) | 24 |  |  | 2 | 4
[8 empty] | c) | Gamad | c) | 12/31/19 | g) | 12/31/2019 | c) | 50,837.50 | [8 empty] | 2 | 4
[8 empty] | d) | - | d) | - | [12 empty] | 2 | 4
|  | Pantaron - Mugas |  |  | Road Maintenance | 3.35 | 0 | a) | 101202.04 | a) | 01/03/19 | e) | - | a) | 101202.04 | a) | 100% | c) | 100% | a) | 9 | Completed |  | 2 | 4
133 | [7 empty] | b) | Gamad | b) | 01/23/19 | f) | - | b) | 101202.04 | b) | - | d) | - | b) | 18 |  |  | 2 | 4
[8 empty] | c) | BALISONG SAN VICENTE IRRIGATORS ASSOCIATION | c) | 12/31/19 | g) | 12/31/2019 | c) | 90,349.93 | [8 empty] | 2 | 4
[8 empty] | d) | - | d) | - | [12 empty] | 2 | 4
|  | Sto. Tomas - Bdry. Mamacao |  |  | Road Maintenance | 4.9 | MBA | a) | 110710.44 | a) | 01/03/19 | e) | - | a) | 110710.44 | a) | 100% | c) | 100% | a) | 10 | Completed |  | 2 | 4
135 | [7 empty] | b) | 79762.14 | b) | 01/21/19 | f) | - | b) | 110710.44 | b) | - | d) | - | b) | 40 |  |  | 2 | 4
[8 empty] | c) | Gamad | c) | 12/31/19 | g) | 12/31/2019 | c) | 50,837.50 | [8 empty] | 2 | 4
[8 empty] | d) | - | d) | - | [12 empty] | 2 | 4
|  | Fd. Rd. 3 - San Jose |  |  | Road Maintenance | 4.55 | 0 | a) | 147367.49 | a) | 01/03/19 | e) | - | a) | 147367.49 | a) | 100% | c) | 100% | a) | 10 | Completed |  | 2 | 4
136 | [7 empty] | b) | Gamad | b) | 01/25/19 | f) | - | b) | 147367.49 | b) | - | d) | - | b) | 30 |  |  | 2 | 4
[8 empty] | c) | BALISONG SAN VICENTE IRRIGATORS ASSOCIATION | c) | 12/31/19 | g) | 12/31/2019 | c) | 56,174.69 | [8 empty] | 2 | 4
[8 empty] | d) | - | d) | - | [12 empty] | 2 | 4
4
4
|  | Menzi - balagunan - Tulalian |  |  | Road Maintenance | 10.63 | MBA | a) | 520167.79 | a) | 01/03/19 | e) | - | a) | 520167.79 | a) | 100% | c) | 100% | a) | 6 | Completed |  | 2 | 4
138 | [7 empty] | b) | 79762.14 | b) | 01/07/19 | f) | - | b) | 520167.79 | b) | - | d) | - | b) | 18 |  |  | 2 | 4
[8 empty] | c) | Gamad | c) | 12/31/19 | g) | 12/31/2019 | c) | 204,850.57 | [8 empty] | 2 | 4
[8 empty] | d) | - | d) | - | [12 empty] | 2 | 4
|  | Jct. Bdry. Tagum - Talomo |  |  | Road Maintenance | 12.01 | 0 | a) | 407429.19 | a) | 01/03/19 | e) | - | a) | 407429.19 | a) | 100% | c) | 100% | a) | 10 | Completed |  | 2 | 4
145 | [7 empty] | b) | Gamad | b) | 01/11/19 | f) | - | b) | 407429.19 | b) | - | d) | - | b) | 50 |  |  | 2 | 4
[8 empty] | c) | BALISONG SAN VICENTE IRRIGATORS ASSOCIATION | c) | 12/31/19 | g) | 12/31/2019 | c) | 168,544.84 | [8 empty] | 2 | 4
[8 empty] | d) | - | d) | - | [12 empty] | 2 | 4
|  | San Jose - Sitio Mahayahay, Magwawa |  |  | Road Maintenance | 0.84 | MBA | a) | 7919.35 | a) | 01/03/19 | e) | - | a) | 7919.35 | a) | 100% | c) | 100% | a) | 2 | Completed |  | 2 | 4
151 | [7 empty] | b) | 79762.14 | b) | 01/16/19 | f) | - | b) | 7919.35 | b) | - | d) | - | b) | 8 |  |  | 2 | 4
[8 empty] | c) | Gamad | c) | 12/31/19 | g) | 12/31/2019 | c) | 1,509.27 | [8 empty] | 2 | 4
[8 empty] | d) | - | d) | - | [12 empty] | 2 | 4
B. 20% DEVELOPMENT FUND CY 2019 | [23 empty] | FS
[5 empty] | Type | Physical | Mode | PROJECT DATA | [6 empty] | Financial (000) | Physical Accompl;ishment |  |  |  | Employment
|  | Name of Project |  |  | of | Target | of | a.)Project Cost |  | a.)Date A lot. Rel. |  | e.)# of days |  |  | a.) Program | a.) Planned |  | c.) Actual |  | Generated # |  |  | REMRRKS
[5 empty] | Project | (Discrip tion) | Impl. | b.)Project Engineer |  | b.)Date Started |  |  | suspended |  | b.)Allotment | b.) Revised |  | d.) Slippage |  | a.) Persons
[7 empty] | MBA / | c.)Implementor |  | c.)Target Compl. |  | f.) # of days extended |  |  | c.)Disbursement |  |  |  |  | b.) Man-days
[7 empty] | CBRMC |  |  |  | Date | g.)Date Completed
Road ID |  | 1. Rehabilitation Of Various Prov'l. Roads and Bridges Dist. 1 |  |  | Road Rehabilitation | KM | MBA | a) | 41465029 | a) | 01/03/19 | e) | - | a) | 41465029 | a) | - | c) | - | a) | 46 | See list of Provincial Roads |  | FS
[6 empty] | 109.55 |  | b) | Paraguya | b) | 01/03/19 | f) | - | b) | 41465029 | b) | - | d) | - | b) | 920 |  |  | AC
11DAN | [7 empty] | c) | PEO | c) | 12/31/19 | g) | - | c) | - | [8 empty] | AC
[10 empty] | d) | - | [12 empty] | AC
[8 empty] | d) | 261 days | d) | - | [12 empty] | AC
|  | Jct. Highway Canatan - Doña Andrea |  |  | Road Rehabilitation | 4.34 | Admin | a) | 2,000,000.00 | a) | 2019-12-06 | e) | - | a) | 2,000,000.00 | a) | - | c) | - | a) | - | For implementation |  | AC
007 | [7 empty] | b) | MJ / Kinanahan | b) | - | f) | - | b) | 2,000,000.00 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
|  | Pamacaun - Lasang Banate |  |  | Road Rehabilitation | 4.34 | Admin | a) | 2000000 | a) | 2019-06-27 | e) | - | a) | 2000000 | a) | - | c) | - | a) | - | For implementation |  | 1
015 | [7 empty] | b) | Gone | b) | - | f) | - | b) | 2000000 | b) | - | d) | - | b) | - | Waiting for the delivery of geo-grid |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [6 empty] | materials. An approved request letter |  | 1
[8 empty] | d) | - | d) | - | [10 empty] | dated Dec. 3, 2019 for the extension of 50 days from Provincial Administrator Engr. Rabanoz is on file |  | 1
|  | Kapalong - Mabantao - Florida |  |  | Road Rehabilitation | 7.86 | Admin | a) | 1231000 | a) | 2019-01-31 | e) | - | a) | 1231000 | a) | 70.98% | c) | 70.98% | a) | - | Waiting for the availability of the long arm backhoe |  | 1
016 | [7 empty] | b) | Aparece | b) | - | f) | - | b) | 1231000 | b) | - | d) | 0% | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
|  | Jct. Highway Gabuyan - Semong - Dagohoy |  |  | Road Rehabilitation | 6.97 | Admin | a) | 2492000 | a) | 01/03/19 | e) | - | a) | 2492000 | a) | - | c) | - | a) | - | Re-aligned to Impvt of km.9 Sagayen - Sawata Provincial Road Phase II ( AIP 3rd revision CY 2019 / SB no.4, 2019) |  | 1
017 | [7 empty] | b) |  | b) | - | f) | - | b) | 2492000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
|  | Sto. Niño - Palma Gil - Sitio Opao |  |  | Road Rehabilitation | 11.6 | Admin | a) | 1901000 | a) | 2019-06-19 | e) | - | a) | 1901000 | a) | - | c) | - | a) | - | NTP not yet serve to Tagum Builders because they have not yet complied with the construction safety requirement |  | 1
019 | [7 empty] | b) | Lumapat | b) | - | f) | - | b) | 1901000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
|  | Daligdigon - Lumabag |  |  | Road Rehabilitation | 11.6 | Admin | a) | 680000 | a) | 01/03/19 | e) | - | a) | 680000 | a) | - | c) | - | a) | - | Re-aligned to Impvt of km.9 Sagayen - Sawata Provincial Road Phase II ( AIP 3rd revision CY 2019 / SB no.4, 2019) |  | 1
022 | [7 empty] | b) |  | b) | - | f) | - | b) | 680000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
|  | Sto. Niño - Daligdigon - Paiton |  |  | Road Rehabilitation | 11.6 | Admin | a) | 3000000 | a) | 2019-10-03 | e) | - | a) | 3000000 | a) | - | c) | - | a) | - | Temporary suspended, materials for re-PR |  | 1
023 | [7 empty] | b) | Crucio | b) | - | f) | - | b) | 3000000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
|  | Jct. Paiton - Mibolo |  |  | Road Rehabilitation | 23.9 | Admin | a) | 6000000 | a) | 2019-03-25 | e) | - | a) | 6000000 | a) | 21.05% | c) | 21.05% | a) | - | 22% as of Nov. 30, 2019 Temporary suspended because the materials for the box culvert was re-PR |  | 1
024 | [7 empty] | b) | Lumapat | b) | Aug.1, 2019 | f) | - | b) | 6000000 | b) | - | d) | 0% | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
|  | Monte Dujali - Gupitan |  |  | Road Rehabilitation | 4.58 | Admin | a) | 1200000 | a) | 2019-12-06 | e) | - | a) | 1200000 | a) | - | c) | - | a) | - |  |  | 1
037 | [7 empty] | b) | MJ/Kinanahan | b) | - | f) | - | b) | 1200000 | b) | - | d) | - | b) | - | For implementation |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
|  | Jct. Sawata - Bdry. Binasbas |  |  | Road Rehabilitation | 0.46 | Admin | a) | 500000 | a) | 2019-06-19 | e) | - | a) | 500000 | a) | - | c) | - | a) | - |  |  | 1
043 | [7 empty] | b) | MJ/Kinanahan | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - | For implementation |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
|  | New Corella - Saug |  |  | Road Rehabilitation | 12.52 | Admin | a) | 6500000 | a) | 2019-03-12 | e) | - | a) | 6500000 | a) | 29.54% | c) | 29.54% | a) | 19 | Temporary suspended because the equipmenta were pulled out to fast track the implementation of Km. 9 Sagayen- Sawata Provincial Road (CMGP) |  | 1
048 | [7 empty] | b) | MJ/Kinanahan | b) | 03/26/19 | f) | - | b) | 6500000 | b) | - | d) | - | b) | 570 |  |  | 1
[8 empty] | c) | PEO | c) | 12/31/19 | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
|  | Jct. Monte Carlo - Upper Cabaywa - Canatan |  |  | Road Rehabilitation | 4.61 | Admin | a) | 8838000 | a) | 2019-01-31 | e) | - | a) | 8838000 | a) | 89.5% | c) | 89.5% | a) | 19 | On -going 90% accomplished. The target date of completion was Dec. 31, 2019, for process time extension request |  | 1
050 | [7 empty] | b) | Garcia | b) | 03/26/19 | f) | - | b) | 8838000 | b) | - | d) | 0% | b) | 570 |  |  | 1
[8 empty] | c) | PEO | c) | 12/31/19 | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
[5 empty] | Road Rehabilitation |  |  | a. )P 500,000.00 |  | a.) 01/31/19 |  |  |  | a.) 500,000.00 | [9 empty] | 1 | 4
|  | Purok 10 Pob. Road, New Corella | [7 empty] | b.) Feb. 16, 2019 |  |  |  | b.) 500,000.00 | [7 empty] | Completed |  | 1 | 4
[12 empty] | g.) Feb. 28, 2019 | [11 empty] | 1 | 4
[24 empty] | 1 | 4
[5 empty] | Road Rehabilitation |  |  | a.)1,815,000.00 |  | a.) 01/31/19 |  |  |  | a.) 1,815,000.00 | [9 empty] | 1 | 4
|  | Purok 7 Pob- Jct. New Sambog | [7 empty] | b.)March 1, 2019 |  |  |  | b.) 1,815,000.00 | [7 empty] | Completed |  | 1 | 4
[12 empty] | g.) May 15, 2019 | [11 empty] | 1 | 4
[24 empty] | 1 | 4
[5 empty] | Road Rehabilitation |  |  | a.) 1,389,000.00 |  | a.) 01/31/19 |  |  |  | a.) 1,389,000.00 | [7 empty] | Completed with a savings of P303,898.08 furtherance and is for implementation |  | 1 | 4
|  | Del Pilar- El Unido Road | [5 empty] | b.) Fabian |  | b.) March 18,2019 |  |  |  | a.) 1,389,000.00 | [9 empty] | 1 | 4
[12 empty] | g.) May 8, 2019 | [11 empty] | 1 | 4
[24 empty] | 1 | 4
|  | Bdry. Tagum - Baca - New Corella |  |  | Road Rehabilitation | 13.01 | Admin | a) | 1419029 | a) | 01/03/19 | e) | - | a) | 1419029 | a) | - | c) | - | a) | - | Re-aligned to Impvt of km.9 Sagayen Sawata Provincial Road Phase II (SB. No. 4 CY 2019) |  | 1
071 | [7 empty] | b) | Crucio | b) | - | f) | - | b) | 1419029 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
1
1
|  | SUPPLEMENTAL BUDGET NO 4 CY 2019 / CONTINUING APPROPRIATION | [21 empty] | AC
AC
[8 empty] | a.) 7,742,775.95 | [5 empty] | a.) 7,742,775.95 | [7 empty] | Waiting for the delivery of materials |  | 1
|  | Impvt. of Km. 9 Sagayen - Sawata Provincial Road Phase II | [5 empty] | b.) Kenny | [5 empty] | b.) 7,742,775.95 | [9 empty] | 1
1
1
Road ID |  | 1. Rehabilitation Of Various Prov'l. Roads and Bridges Dist 2 |  |  | Road Rehabilitation | KM | Admin | a) | 46740117 | a) | 01/03/19 | [10 empty] | See list of Provincial Roads
[6 empty] | 115.62 |  | b) | Matuguinas | b) | - | [12 empty] | AC
11DAN | [7 empty] | c) | PEO | c) | - | [12 empty] | AC
[10 empty] | d) | - | [12 empty] | AC
[8 empty] | d) | 261 days | d) | - | [12 empty] | AC
|  | Jct. Highway Sto. Niño - Cebulano |  |  | Road Rehabilitation | 2.09 | Admin | a) | 1045000 | a) | 2019-03-18 | e) | - | a) | 1045000 | a) | 20% | c) | 20% | a) | 11 | On-going |  | AC
072 | [7 empty] | b) | Obar | b) | 2019-05-21 | f) | - | b) | 1045000 | b) | - | d) | - | b) | 55 |  |  | 2
[8 empty] | c) | PEO | c) | 2020-02-02 | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
[5 empty] | Road Rehabilitation |  |  | a.) 515,000.00 |  | a.) 03/12/19 |  |  |  | a.) 515,000.00 | [9 empty] | 2
|  | Jct. Highway -Tubod - Bagong Silang | [5 empty] | b.) Clar |  | b.) March 18, 2019 |  |  |  | b.) 515,000.00 | [7 empty] | Completed |  | 2
[12 empty] | g.) June 15, 2019 | [11 empty] | 2
2
|  | Basa - Tubod |  |  | Road Rehabilitation | 1.56 | Admin | a) | 1000000 | a) | 2019-06-19 | e) | - | a) | 1000000 | a) | - | c) | - | a) | - |  |  | 2
076 | [7 empty] | b) | Piad | b) | Nov. 11, 2019 | f) | - | b) | 1000000 | b) | - | d) | - | b) | - | On-going |  | 2
[8 empty] | c) | - | c) | 2020-03-09 | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | Tubod - Pilar |  |  | Road Rehabilitation | 1.55 | Admin | a) | 16000000 | a) | 06/19/19 & 12/9/19 | e) | - | a) | 16000000 | a) | - | c) | - | a) | - | On-going |  | 2
077 | [7 empty] | b) | Gamad/Clar | b) | Dec. 18, 2019 | f) | - | b) | 16000000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | Nov. 5, 2020 | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
[5 empty] | Road Rehabilitation |  |  | a.) 390,000.00 |  | a.) 03/12/19 |  |  |  | a.) 390,000.00 | [9 empty] | 2 | 4
|  | Cebulano- Luceta | [5 empty] | b.) Clar |  | b.) March 8, 2019 |  |  |  | b.) 390,000.00 | [7 empty] | Completed |  | 2 | 4
[12 empty] | g.) June 15, 2019 | [11 empty] | 2 | 4
[24 empty] | 2 | 4
[5 empty] | Road Rehabilitation |  |  | a.) 295,000.00 |  | a.) 03/12/19 |  |  |  | a.) 295,000.00 | [9 empty] | 2 | 4
|  | Lower Asuncion - Upper Asuncion | [5 empty] | b.) Clar |  | b.) March 18, 2019 |  |  |  | b.) 295,000.00 | [7 empty] | Completed |  | 2 | 4
[12 empty] | g.) June 15, 2019 | [11 empty] | 2 | 4
[24 empty] | 2 | 4
[5 empty] | Road Rehabilitation |  |  | a.) 1,220,000.00 |  | a.) 03/12/19 |  |  |  | a.) 1,220,000.00 | [9 empty] | 2
|  | Jct. Highway - Sto. Nino - La Paz - San Vicente | [5 empty] | b.)Obar |  | b.) March 18, 2019 |  |  |  | b.) 1,220,000.00 | [7 empty] | Completed |  | 2
[12 empty] | g.) Sept. 30, 2019 | [11 empty] | 2
2
|  | Alejal - Alemag |  |  | Road Rehabilitation | 1.79 |  | a) | 970000 | a) | 2019-03-18 | e) | - | a) | 970000 | a) | 100% | c) | 100% | a) | 7 | Completed. Financially completed |  | 2
092 | [7 empty] | b) | Gamad/Clar | b) | 2019-05-20 | f) | - | b) | 970000 | b) | 100 | d) | 0% | b) | 20 |  |  | 2
[8 empty] | c) | - | c) | 2019-09-12 | g) | Sept. 30, 2019 | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
[5 empty] | Road Rehabilitation |  |  | a.) 640,000.00 |  | a.) 03/12/19 |  |  |  | a.) 640,000.00 | [9 empty] | 2
|  | Mabaus - Cabay -angan | [5 empty] | b.)Clar |  | b.) Maech 18, 2019 |  |  |  | a.) 640,000.00 | [7 empty] | Completed |  | 2
[12 empty] | g.) July 30, 2019 | [11 empty] | 2
2
[5 empty] | Road Rehabilitation |  |  | a.) 280,000.00 |  | a.) 03/12/19 |  |  |  | a.) 280,000.00 | [9 empty] | 2
|  | Mabaus - Salvacion | [5 empty] | b.)Clar |  | b.) March 18, 2019 |  |  |  | a.) 280,000.00 | [9 empty] | 2
[12 empty] | g.) June 30, 2019 | [9 empty] | Completed |  | 2
2
|  | Dalisay - Mabuhay |  |  | Road Rehabilitation | 3.25 | Admin | a) | 1000000 | a) | 2019-05-16 | e) | - | a) | 1000000 | a) | 80% | c) | 80% | a) | 10 |  |  | 2
102 | [7 empty] | b) | Gamad/Clar | b) | 2019-06-17 | f) |  | b) | 1000000 | b) |  | d) | 0% | b) | 20 | On-going |  | 2
[8 empty] | c) | - | c) | 2/29,2019 | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | Sitio Malaga - Tibulao |  |  | Road Rehabilitation | 3.22 | Admin | a) | 1000000 | a) | 2019-06-25 | e) | - | a) | 1000000 | a) | - | c) | - | a) | - |  |  | 2
103 | [7 empty] | b) | Gamad/Clar | b) | Nov. 11, 2019 | f) | - | b) | 1000000 | b) | - | d) | - | b) | - | On-going |  | 2
[8 empty] | c) | - | c) | Feb. 9, 2020 | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | Dujali - Tanglaw |  |  | Road Rehabilitation | 3.6 | Admin | a) | 2075000 | a) | 2019-10-03 | e) | - | a) | 2075000 | a) | - | c) | - | a) | - |  |  | 2
104 | [7 empty] | b) | Balbastro | b) | Dec. 28, 2019 | f) | - | b) | 2075000 | b) | - | d) | - | b) | - | On-going |  | 2
[8 empty] | c) | - | c) | Apr. 16, 2020 | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | Dujali - New Casay |  |  |  | 3.2 | Admin | a) | 640000 | a) | 2019-05-16 | e) | - | a) | 640000 | a) | 100% | c) | 100% | a) | 10 |  |  | 2 | 4
106 | [7 empty] | b) | Gamad/Clar | b) | 2019-06-17 | f) | 40 | b) | 640000 | b) |  | d) | - | b) | 40 | Completed |  | 2 | 4
[8 empty] | c) | - | c) |  | g) | 10/15/2019 | c) | - | [8 empty] | 2 | 4
[8 empty] | d) | - | d) | - | [12 empty] | 2 | 4
[5 empty] | Road Rehabilitation |  |  | a.) 450,000.00 |  | a.) 03/12/19 |  |  |  | a.) 450,000.00 | [9 empty] | 2
|  | New Casay - Bugtong Talisay | [5 empty] | b.)Clar |  | b.) March 18, 2019 |  |  |  | a.) 450,000.00 | [7 empty] | Completed |  | 2
[12 empty] | g.)June 30, 2019 | [11 empty] | 2
2
|  | Cabay-angan - Esperanza |  |  | Road Rehabilitation | 5.37 | Admin | a) | 1300000 | a) | 2019-05-16 | e) | - | a) | 1300000 | a) | 80% | c) | 80% | a) | 9 |  |  | 2
110 | [7 empty] | b) | Gamad/Clar | b) | 2019-06-17 | f) | - | b) | 1300000 | b) | - | d) | - | b) | 36 | On- going |  | 2
[8 empty] | c) | PEO | c) | Feb. 29, 2020 | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | [13 empty] | 2
[5 empty] | Road Rehabilitation |  |  | a.)220,000.00 |  | a.) 03/12/19 |  |  |  | a.)220,000.00 |  | a.) 100 % |  | c.)100% | [5 empty] | 2
|  | Purok 6 Cabay-angan - Esti | [5 empty] | b.) Gamad |  | b.) March 18, 2019 |  |  |  | a.)220,000.00 | [7 empty] | Completed |  | 2
[12 empty] | g.) June 30, 2019 | [11 empty] | 2
2
[5 empty] | Road Rehabilitation |  |  | a.)250,000.00 |  | a.) March 12, 2019 | [5 empty] | a.) 100 % |  | c.)100% | [5 empty] | 2
|  | Dujali - Sitio Pawas | [5 empty] | b.) Gamad |  | b.) March 18, 2019 | [11 empty] | Completed |  | 2
[12 empty] | g.) Jun 30, 2019 | [11 empty] | 2
2
[5 empty] | Road Rehabilitation |  |  | a.) 280,000.00 |  | a.) March 12, 2019 | [5 empty] | a.) 100 % |  | c.)100% | [5 empty] | 2
|  | Purok 1 to Purok 2 Sitio Pawas | [6 empty] | b.) Gamad | b.) March 18, 2019 | [11 empty] | Completed |  | 2
[12 empty] | g.) Jun 30, 2019 | [11 empty] | 2
2
|  | San Miguel - Crossing Kinamayan |  |  | Road Rehabilitation | 2.8 | Admin | a) | 560000 | a) | 2019-06-25 | e) | - | a) | 560000 | a.) 100 % |  | c.)100% |  | a) | - |  |  | 2 | 4
120 | [7 empty] | b) | Nasol | b) | Sept. 19, 2019 | f) | - | b) | 560000 | b) | - | d) | - | b) | - | Completed |  | 2 | 4
[8 empty] | c) | - | c) | - | g) | Nov. 30, 2019 | c) | - | [8 empty] | 2 | 4
[8 empty] | d) | - | d) | - | [12 empty] | 2 | 4
|  | San Miguel -Libertad Provincial Road |  |  | Road Rehabilitation | 6.2 | Admin | a) | 1240000 | a) | 2019-05-29 | e) | - | a) | 1240000 | a) | 59.41% | c) | 59.41% | a) | 9 |  |  | 2
121 | [7 empty] | b) | Gamad | b) | 2019-06-17 | f) |  | b) | 1240000 | b) | - | d) | - | b) | 36 | On-going |  | 2
[8 empty] | c) | - | c) | Feb. 29, 2020 | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | Bacali - Casig-ang - Libertad |  |  | Road Rehabilitation | 4.7 | Admin | a) | 940000 | a) | 2019-06-07 | e) | - | a) | 940000 | a) | 80% | c) | 80% | a) | 9 | On-going |  | 2
123 | [7 empty] | b) | Gamad | b) | 2019-06-27 | f) | 35 | b) | 940000 | b) | - | d) | - | b) | 36 |  |  | 2
[8 empty] | c) | Admin | c) | Feb. 29, 2020 | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | Kinamayan - Moslog - Mahayag |  |  | Road Rehabilitation | 3.23 | Admin | a) | 1000000 | a) | 2019-05-20 | e) | - | a) | 1000000 | a) | 80% | c) | 80% | a) | 10 | On going |  | 2
124 | [7 empty] | b) | Gamad | b) | 2019-06-27 | f) | 29 | b) | 1000000 | b) | - | d) | - | b) | 20 |  |  | 2
[8 empty] | c) | PEO | c) | Feb. 29, 2020 | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | San Miguel - Moslog - Kinamayan |  |  | Road Rehabilitation | 2.9 | Admin | a) | 1000000 | a) | 2019-05-20 | e) | - | a) | 1000000 | a) | 80% | c) | 80% | a) | 6 | On-going |  | 2
125 | [7 empty] | b) | Gamad | b) | 2019-06-27 | f) | 29 | b) | 1000000 | b) | - | d) | - | b) | 24 |  |  | 2
[8 empty] | c) | - | c) | Feb. 29, 2020 | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | Kinamayan - Lunga-og |  |  | Road Rehabilitation | 2.59 | Admin | a) | 520000 | a) | 2019-03-18 | e) | - | a) | 520000 | a) | 100% | c) | 100% | a) | 9 | Completed |  | 2
126 | [7 empty] | b) | Gamad/Clar | b) | 5/202/019 | f) | - | b) | 520000 | b) | - | d) | - | b) | 36 |  |  | 2
[8 empty] | c) | - | c) |  | g) | Sept. 30, 2019 | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | Mugas - Lanatad |  |  | Road Rehabilitation | 1.53 | Admin | a) | 500000 | a) |  | e) | - | a) | 500000 | a) | - | c) | - | a) | - | On-going |  | 2
131 | [7 empty] | b) | Balbastro | b) | 8/5/2019 | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | Feb. 20, 2020 | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | New Katipunan - Pantaron |  |  | Road Rehabilitation | 1.96 | Admin | a) | 395000 | a) | 2019-03-12 | e) | - | a) | 395000 | a) | - | c) | - | a) | - |  |  | 2
134 | [7 empty] | b) | Gamad/Clar | b) | Dec. 27, 2019 | f) | - | b) | 395000 | b) | - | d) | - | b) | - | On-going |  | 2
[8 empty] | c) | - | c) | Feb. 25, 2020 | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | Fd. Rd. 2 - Sto. Tomas - Magwawa |  |  | Road Rehabilitation | 10.21 | Admin | a) | 3575000 | a) | June `19, 2019 | e) | - | a) | 3575000 | a) | 40% | c) | 40% | a) | - |  |  | 2
137 | [7 empty] | b) | Gamad/Clar | b) | Aug. 27, 2019 | f) | - | b) | 3575000 | b) | - | d) | - | b) | - | On-going |  | 2
[8 empty] | c) | - | c) | 2020-01-24 | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
[8 empty] | a.) 540,000.00 |  | a.) March 12, 2019 |  |  |  | a.) 540,000.00 |  | a.)100% |  | c.)100% |  |  |  | Completed |  | 2
|  | Nafco - Bobongon |  |  | Road Rehabilitation |  |  | b. Gamad |  | b.) march 18, 2019 |  |  |  | b.) 540,000.00 | [9 empty] | 2
[12 empty] | g.) June 30, 2019 | [11 empty] | 2
2
2
|  | Jct. Highway - Tanglaw |  |  | Road Rehabilitation | 3.98 | Admin | a) | 1100000 | a) | 2019-05-16 | e) | - | a) | 1100000 | a) | 85% | c) | 85% | a) | 10 | On going |  | 2
142 | [7 empty] | b) | Gamad/Clar | b) | 2019-06-17 | f) | 29 | b) | 1100000 | b) | - | d) | - | b) | 20 |  |  | 2
[8 empty] | c) | PEO | c) | Feb. 29, 2020 | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | Kimamon - Lunga-og - Talomo |  |  | Road Rehabilitation | 5.99 | Admin | a) | 1800000 | a) | 5/202019 | e) | - | a) | 1800000 | a) | 73.31% | c) | 73.31% | a) | 9 | on -going |  | 2
144 | [7 empty] | b) | Gamad | b) | 2019-06-17 | f) | - | b) | 1800000 | b) | - | d) | - | b) | 6 |  |  | 2
[8 empty] | c) | PEO | c) | Feb. 27, 2020 | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | Bdry. Tagum - Crossing Kinamayan Sto. Tomas |  |  | Road Rehabilitation | 0.75 | Admin | a) | 3700000 | a) | Dec. 6, 2019 | e) | - | a) | 3700000 | a) | - | c) | - | a) | - | On-going |  | 2
146 | [7 empty] | b) | Gamad/Clar | b) | Dec. 27, 2019 | f) | - | b) | 3700000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | 2020-04-25 | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | Prk. Narafil - Prk. Daisy Magupising |  |  | Road Rehabilitation | 19.16 | Admin | a) | 300117 | a) | 2019-06-25 | e) | - | a) | 300117 | a) | 100% | c) | 100% | a) | - | Completed |  | 2 | 4
148 | [7 empty] | b) | Gamad/Clar | b) | Sept. 16, 2019 | f) | - | b) | 300117 | b) | - | d) | - | b) | - |  |  | 2 | 4
[8 empty] | c) | - | c) | - | g) | Oct. 18, 2019 | c) | - | [8 empty] | 2 | 4
[8 empty] | d) | - | d) | - | [12 empty] | 2 | 4
2. Various of Local Roads & Drainage Development Project (Provincewide) |  |  |  |  | Road Drainage rehabiliated |  | Admin | a) | 15000000 | [12 empty] | See projects listed below |  | 2
[8 empty] | b) | Paraguya | [14 empty] | AC
[8 empty] | c) | PEO | [14 empty] | AC
[8 empty] | d) | - | [14 empty] | AC
At District 1
|  | Rehab./Impv't. of San Juan-New Talisay Provincial Road with Drainage |  |  | Road Drainage rehabiliated | - | Admin | a) | 1000000 | a) | Feb. 10, 2019 | e) | - | a) | 1000000 | a) | - | c) | 60$ | a) | - | On-going. |  | AC
2.1 | [7 empty] | b) | MJ | b) | - | f) | - | b) | 1000000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | PEO | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| 6 | Repair/Rehab. Of Concrete Road Jct. Suaon-Libuton, Kapalong |  |  | Road Drainage rehabiliated | - | Admin | a) | 1000000 | a) | 2019-07-03 | e) | - | a) | 1000000 | a) | - | c) | - | a) | - | For implementation Waiting for the availability of the backhoe |  | 1
2.2 | [7 empty] | b) | Aparece | b) | - | f) | - | b) | 1000000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| 1 | Impv't. of Cross Drainage along Saug-Sonlon-Bdry. Longanapan |  |  | Road Drainage rehabiliated | - | Admin | a) | 3000000 | a) | Feb. 10, 2019 | e) | - | a) | 3000000 | a) | - | c) | 58% | a) | - | Suspended from Nov. 18, 2019 to Jan 5, 2020.Resume jan. 6, 2020 |  | 1
2.3 | [7 empty] | b) | Bataller | b.) Aug. 1, 2019 | Aug. 1, 2019 | f) | - | b) | 3000000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| 8 | Rehab./Impv't. of Sto. Niño-Palma Gil-Sitio Opao Provincial Road with Drainage |  |  | Road Drainage rehabiliated | - | Admin | a) | 3000000 | a) | 2019-05-29 | e) | - | a) | 3000000 | a) | - | c) | - | a) | - | NTP not yet serve to Tagum Builders because they have not yet complied with the construction safety requirement |  | 1
2.4 | [7 empty] | b) | Lumapat | b) | - | f) | - | b) | 3000000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
|  | Rehab. of Anibongan-Salvacion-Cabay-angan Provincial Road with Drainage |  |  | Road Drainage rehabiliated | - | - | a) | 2000000 | a) | 2019-01-14 | e) | - | a) | 2000000 | a) | 100% | c) | 100% | a) | 1 | Completed |  | 1 | 4
2.1 | [7 empty] | b) | Toquero | b) | 2019-05-22 | f) | - | b) | 2000000 | b) | - | d) | - | b) | 4 | Fiancial obligation still on process |  | 2 | 4
[8 empty] | c) | PEO | c) | 2019-08-04 | g) | Dec. 31, 2019 | c) | - | [8 empty] | 2 | 4
[8 empty] | d) | - | d) | - | [12 empty] | 2 | 4
|  | Rehab. Of Dujali-Pawas-San Vicente Provincial Road |  |  | Road Drainage rehabiliated | - | - | a) | 1102900 | a) | Aug. 5, 2019 | e) | - | a) | 1102900 | a) | - | c) | - | a) | - | Project title was amended in the 2nd AIP revision deleting drainage. The project amount was reduced from P2,000,000.00 to P1,102,900.00 to fund new projects that was inlcuded in the AIP 3rd revision CY 2019 /SB No. 4 CY 2019 On. going |  | 2
2.2 | [7 empty] | b) | Toquero | b) | - | f) | - | b) | 1102900 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | PEO | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | Rehab./Impv't. of Jct. highway Ising-Magsaysay Provincial Road with Drainage |  |  | Road Drainage rehabiliated | - | - | a) | 1500000 | a) | Jan. 16, 2019 | e) | - | a) | 1500000 | a) | - | c) | - | a) | - | Revised POW for approval - Jan. 7, 2020 Revision was made due to scarcity of boulders changing from stone masonry to concrete masonry |  | 2
2.3 | [7 empty] | b) | Toquero | b) | - | f) | - | b) | 1500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | PEO | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | Rehab./Impv't. of Sto. Tomas-Bdry. Mamacao Provincial Road |  |  | Road Drainage rehabiliated | - | - | a) | 1500000 | a) | 2019-01-14 | e) | - | a) | 1500000 | a) | 100% | c) | 100% | a) | - | Completed Financial obligation on process |  |  | 4
2.4 | [7 empty] | b) | Toquero | b) | 2019-05-31 | f) | 60 | b) | 1500000 | b) | - | d) | - | b) | - |  |  | 2 | 4
[8 empty] | c) | PEO | c) | 2019-07-15 | g) | Dec. 31, 2019 | c) | - | [8 empty] | 2 | 4
[8 empty] | d) | - | d) | - | [12 empty] | 2 | 4
| SUPPLEMENTAL BUDGET NO. 4 CY 2019 | [22 empty] | AC
AC
[10 empty] | a.) Nov. 27, 2019 | [13 empty] | 2
| 2.5 | Rehab of Local Roads at Dalisay - Manay Road Section, | [19 empty] | Completed |  | 2
|  | Panabo City | [19 empty] | Financial obligation on process |  | 2
2
| 2.6 | Rehab. of Local Roads at Sta. Cruz- jct. Tagpore- Buenavista | [7 empty] | a.) Nov. 27, 2019 | [11 empty] | Completed |  | 2
|  | Road Section, panabo City | [19 empty] | Financial obligation on process |  | 2
2
| 2.7 | Rehab. of Local Roads at Taba - Bucana Road Section | [7 empty] | a.) | Nov. 27, 2019 | [10 empty] | Financial obligation on process |  | 2
2
2
3. Various Water System Development Project (Provincewide) |  |  |  |  | Water System projects | - | Admin | a) | 9750000 | [12 empty] | See projects listed below |  | 2
[8 empty] | b) | Medalla/Imboy | [14 empty] | AC
[8 empty] | c) | PEO | [14 empty] | AC
[8 empty] | d) | - | [14 empty] | AC
3.1 |  | Construction of Water System Projects | [21 empty] | AC
AC
| 6 | Construction of PWS, Bgry. Linao, San Isidro |  |  | Water System Projects | - | Admin | a) | 500000 | a) | 06/19/19 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For implementation |  | AC
3.1.1 | [7 empty] | b) | Aclaracion | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| 6 | Construction of PWS, Brgy. Datu Balong, San Isidro |  |  | Water System Projects | - | Admin | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For declaration of savings because the spring water source is not feasible for development |  | 1
3.1.2 | [7 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| 6 | Construction of PWS, Brgy. Sagayen, San Isidro |  |  | Water System Projects | - | Admin | a) | 500000 | a) | 2019-09-10 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Procurement on process |  | 1
3.1.3 | [7 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| 4 | Construction of PWS, Brgy. Purok 7-A and B, Brgy. Capungagan, kapalong |  |  | Water System Projects | - | Admin | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | The project was funded by OPAPP CY 2018. Fund re-aligned to new project Rehab. of Water System in PEEDO- LPRRC, Pob. New Corella (AIP 2nd revision CY 2019 |  | 1
3.1.4 | [7 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| 4 | Construction of PWS Purok 2, Brgy. Pag-Asa, kapalong |  |  | Water System Projects | - | Admin | a) | 800000 | a) | - | e) | - | a) | 800000 | a) | - | c) | - | a) | - | The project was funded by OPAPP CY 2018. Fund re-aligned and added to Construction of PWS in Brgy. Linosutan, kaputian Dist, IGACOS (AIP 2nd revision CY 2019) |  | 1
3.1.5 | [7 empty] | b) | - | b) | - | f) | - | b) | 800000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| 11 | Installation of Shallow Tube Wells & Const. of Machinery Shed |  |  | Water System Projects | - | Admin | a) | 1600000 | a) | - | e) | - | a) | 1600000 | a) | - | c) | - | a) | - | POW for review |  | 1
3.1.6 | [7 empty] | b) | - | b) | - | f) | - | b) | 1600000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
|  | Impv't. of Potable Water System, Consolacion, Panabo City |  |  | Water System Projects | - | - | a) | 500000 | a) | 2019-06-28 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Sched of bidding Dec 27, 2019 |  | 1
3.1.7 | [7 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | Impv't. of Potable Water System, Tagbitan-ag, Samal Dist. |  |  | Water System Projects | - | - | a) | 500000 | a) | 2019-06-19 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For implementation |  | 2
3.1.8 | [7 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | Impv't. of Potable Water System, San Antonio, babak, IGCS |  |  | Water System Projects | - | - | a) | 500000 | a) | 2019-06-25 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For implementation |  | 2
3.1.9 | [7 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | Impv't. of Potable Water System, Mambago-A, IGCS |  |  | Water System Projects | - | - | a) | 500000 | a) | Sept. 10, 2019 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | (Amended in the AIP 2nd Revision to change the location from Peñaplata to Samal District) For implementation |  | 2
3.1.10 | [7 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | Construction of PWS, Brgy. Buenavista, Panabo City |  |  | Water System Projects | - | - | a) | 500000 | a) | June 19 ,2019 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For implementation |  | 2
3.1.11 | [7 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | Construction of PWS, Brgy. Brgy. Kiotoy, Panabo City |  |  | Water System Projects | - | Contract | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Waiting for geo-resistivity equipment since the activity is drilling works |  | 2
3.1.12 | [7 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | Construction of PWS, Brgy. Linusotan, Talikud, District, IGCS |  |  | Water System Projects | - | - | a) | 500,000 + 800,000.00 | a) | Oct. 23, 2019 | e) | - | a) | 500,000 + 800,000.00 | a) | - | c) | - | a) | - | (Additional 800,000.00 from Const. of PWS in purok 2, Pag-asa, Kapalong which was funded by OPAPP CY 2018) (amended Sched of bidding Dec 27, 2019 |  | 2
3.1.13 | [7 empty] | b) | - | b) | - | f) | - | b) | 500,000 + 800,000.00 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | Rehab. of PWS, Brgy. San Miguel, Babak, IGCS |  |  | Water System Projects | - |  | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For amendment indicating phase 2 since the project title is the same with stimulus project and same amount. |  | 2
3.1.14 | [7 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | Construction of PWS, Brgy. Cacao, Panabo City |  |  | Water System Projects | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For cancellation. Purchase of Geo-resistivity equipment but procurement still on process |  | 2
3.1.15 | [7 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | Rehabilitation of Potable Water System, Brgy. Pangubatan, kaputian Dist. IGCS |  |  | Water System Projects | - |  | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For allotment June 24, 2019 |  | 2
3.1.16 | [7 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | Conduct of Geo-resistivity/drilling Test of Proposed Site |  |  | Geo-resistivity/drilling test conducted | - | - | a) | 250000 | [12 empty] | See projects listed below |  | 2
3.1 | [7 empty] | b) | - | [14 empty] | AC
[8 empty] | c) | - | [14 empty] | AC
[8 empty] | d) | - | [14 empty] | AC
|  | Construction of PWS, Brgy. Kiotoy, Panabo City |  |  | Geo-resistivity/drilling test conducted | - | - | a) | 62500 | a) | - | e) | - | a) | 62500 | a) | - | c) | - | a) | - | For cancellation due to the purchase of geo-resistivity equipment |  | AC
a. | [7 empty] | b) | - | b) | - | f) | - | b) | 62500 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | Construction of PWS, Brgy. Linosutan, Talikud, IGCS |  |  | Geo-resistivity/drilling test conducted | - | - | a) | 62500 | a) | - | e) | - | a) | 62500 | a) | - | c) | - | a) | - |  |  | 2
b. | [7 empty] | b) | - | b) | - | f) | - | b) | 62500 | b) | - | d) | - | b) | - | For cancellation due to the purchase of geo-resistivity equipment |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | Construction of PWS, Brgy. San Miguel, Samal, IGCS |  |  | Geo-resistivity/drilling test conducted | - | - | a) | 62500 | a) | - | e) | - | a) | 62500 | a) | - | c) | - | a) | - | For cancellation due to the purchase of geo-resistivity equipment |  | 2
c. | [7 empty] | b) | - | b) | - | f) | - | b) | 62500 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | Construction of PWS, Cacao, Panabo City |  |  | Geo-resistivity/drilling test conducted | - | - | a) | 62500 | a) | - | e) | - | a) | 62500 | a) | - | c) | - | a) | - |  |  | 2
d. | [7 empty] | b) | - | b) | - | f) | - | b) | 62500 | b) | - | d) | - | b) | - | For cancellation due to the purchase of geo-resistivity equipment |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
4. Various Government Buildings and Facilities Development Project (Provincewide) |  |  |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of recipients | - | Admin | a) | 27000000 | [12 empty] | See projects listed below |  | 2
[8 empty] | b) | Medalla | [14 empty] | AC
[8 empty] | c) | PEO | [14 empty] | AC
[8 empty] | d) | - | [14 empty] | AC
|  | Repair Bay of Disaster Quick Response Equipment @ PEO Compound, Gov't. Center, Mankilam, Tagum City |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of recipients | - | Admin | a) | 1000000 | a) | 2019-01-31 | e) | - | a) | 1000000 | a) | - | c) | 46.28% | a) | - | On-going |  | AC
| 11 | [6 empty] | b) | Azotes | b) | Oct. 16, 2019 | f) | - | b) | 1000000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
|  | Repair/Impv't. of Municipal Triball Hall, New Corella |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of recipients | - | Admin | a) | 1500000 | a) | - | e) | - | a) | 1500000 | a) | - | c) | - | a) | - | For allotment June 24, 2019 |  | 1
| 5 | [6 empty] | b) | - | b) | - | f) | - | b) | 1500000 | b) | - | d) | - | b) | - | PO on process |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
|  | Const. of GYM Bleacher at Suaybaguio Rina, Elem. School |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of recipients | - | Admin | a) | 1000000 | a) | - | e) | - | a) | 1000000 | a) | 100% | c) | 100% | a) | - | Completed |  | 1
| 11 | [6 empty] | b) | Mayang | b) | 6/3/2019 | f) | - | b) | 1000000 | b) | 64 | d) | 0% | b) | - |  |  | 1
[8 empty] | c) | PEO | c) | 8/01/2019 | g) |  | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
|  | Repair of Dacudao Health Center, Dacudao, San Isidro |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of recipients | - | Admin | a) | 1000000 | a) | - | e) | - | a) | 1000000 | a) |  | c) | 93.13% | a) | 5 | On going |  | 1
| 6 | [6 empty] | b) | Aclaracion | b) | - | f) | - | b) | 1000000 | b) | - | d) |  | b) | 110 |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
|  | Const. of Perimeter Fence at Sto. Niño NASECO Integrated School with Tugas Ext., Sto. Niño, Talaingod |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of recipients | - | Admin | a) | 1000000 | a) | - | e) | - | a) | 1000000 | a) | - | c) | - | a) | - | For implementation |  | 1
| 8 | [6 empty] | b) | - | b) | - | f) | - | b) | 1000000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
|  | Const. of Multi-Purpose Hall Center (Cultural Heritage in Ancestral Domain of Ata-Manobo) |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of recipients | - | Admin | a) | 3000000 | a) | - | e) | - | a) | 3000000 | a) | - | c) | - | a) | - | Fund re-aligned to GIDAS projects |  | 1
| 8 | [6 empty] | b) | - | b) | - | f) | - | b) | 3000000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | PEO | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
|  | Const. of IP Women's Multi-{Purpose Bldg.), Cabidiangan, Sto. Niño, Talaingod |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of recipients | - | Admin | a) | 2000000 | a) | 2019-05-15 | e) | - | a) | 2000000 | a) | - | c) | - | a) | - | For re-bidding |  | 1
| 8 | [6 empty] | b) | - | b) | - | f) | - | b) | 2000000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
|  | Extension of PAGRO Training Center & Ground Dev't., Gov't. Center, Mankilam, Tagum City |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of recipients | - | Admin | a) | 1000000 | a) | - | e) | - | a) | 1000000 | a) | - | c) | - | a) | - | For allotment- June 24,2019 Abstract on process
| 11 | [6 empty] | b) | - | b) | - | f) | - | b) | 1000000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | PEO | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
|  | Construction of Abilidad Training Center, Gov't. Center, Mankilam, Tagum City |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of recipients | - | Admin | a) | 7000000 | a) | - | e) | - | a) | 7000000 | a) | - | c) | - | a) | - | Fund re-aligned to GIDAS projects |  | 1
| 11 | [6 empty] | b) | - | b) |  | f) | - | b) | 7000000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
|  | Const. of 1 CL Bldg. @ Suawon ES, New Corella |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of recipients | - | Admin | a) | 1000000 | a) | - | e) | - | a) | 1000000 | a) | - | c) | - | a) | - | On-going |  | 1
[8 empty] | b) | - | b) | Nov. 19, 2019 | f) | - | b) | 1000000 | b) |  | d) | - | b) | - |  |  | 1
| 5 | [6 empty] | c) | PEO | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
|  | Const. of Municipal Tribal Hall, San Isidro |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of recipients | - | Admin | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For implementation |  | 1
| 6 | [6 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
|  | Const. of Quail House (PDNSC Ext. Campus), Sto. Niño, Talaingod |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of recipients | - | Admin | a) | 750000 | a) | - | e) | - | a) | 750000 | a) | - | c) | - | a) | - | On-going |  | 1
| 8 | [6 empty] | b) | - | b) | - | f) | - | b) | 750000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | PEO | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
|  | Completion of Perimeter Steel Fence @ Lunga-og E/S, Brgy. Lunga-og, Sto. Tomas |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of recipients | - | Admin | a) | 1630000 | a) | 01/17/19 | e) | - | a) | 1630000 | a) | - | c) | 46.28% | a) | - | On-going |  | 1
[8 empty] | b) | Azotes | b) | - | f) | - | b) | 1630000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | PEO | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | Const. of DDN Hospital Carmen Zone Annex Bldg. Phase 2, |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of recipients | - | Contract | a) | 3620000 | a) | 2019-06-28 | e) | - | a) | 3620000 | a) | - | c) | - | a) | - | For implementation |  | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 3620000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | Digos Constrak Corp/ | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
5. Stimulus Projects for Various Barangays a. 20% Development Fund CY 2019 |  |  |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | Admin | a) | 41500000 | [12 empty] | See projects listed below |  | 2
[8 empty] | b) | Medalla | [14 empty] | AC
[8 empty] | c) | PEO | [14 empty] | AC
[8 empty] | d) | - | [14 empty] | AC
AC
5.1 |  | Rehab. Of FMR at Prk. 1,3,4 & 7, Concepcion, Asuncion |  |  | Road Rehabilitation to cater the needs of brgys. | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Re-aligned to Const. of Children's Playground with Amenities at Pob. New Corella (AIP 3rd Revision CY 2019 / SB No. 4 CY 2019 |  | AC
| 1 | [6 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
5.2 |  | Rehab. Of Multi-Purpose Hall, New Bantayan, Asuncion |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | 35% | a) | - | Fund transferred to LGU on - going c /o Engr. Lilibeth Cuajao |  | 1
| 1 | [6 empty] | b) | - | b) | 2019-11-02 | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
1
NEW CORELLA
5.3 |  | Construction of Multi-Purpose Hall, El Salvador, New Corella |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) | 2019-05-23 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Fund transferred to LGU March 23, 2019 c/o Engr. Dugoldugol |  | AC
[8 empty] | b) | - | b) | 2019-09-16 | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
| 5 | [6 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
5.4 |  | Concreting of Drainage Canal , Pob., New Corella |  |  | Const. of Drainage Canal to cater the needs of brgys. | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Amended to Const. of 2 Storey Multi-Purpose Hall phase 3 (Brgy. Hall),Pob., New Corella (AIP 3rd revision CY 2019 / SB No. 4 CY 2019 |  | 1
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
| 5 | [6 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
5.5 |  | Rehab. Of Multi-Purpose Hall, Cabidianan, New Corella |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) | 02/20/19 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Fund transferred to LGU c/o Engr. Dugoldugol |  | 1
[8 empty] | b) |  | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
| 5 | [6 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
5.6 |  | Const. of Canal Lining, Limbaan, New Corella |  |  | Const. of Drainage Canal to cater the needs of brgys. | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Fund transferred to LGU c/o Engr. Dugoldugol Completed - Nov. 8, 2019 / PCR for submission |  | 1
[8 empty] | b) | - | b) | 2019-09-06 | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
| 5 | [6 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
1
TALAINGOD
5.7 |  | Brgy. Electrification (Centro Gupitan), Gupitan, Talaingod |  |  | Rural Electrification to cater the needs of brgys. | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Re-aligned to other stimulus projects that need additional funds to complete since the amount can not complete the project. Recommended for exact fund that can complete the project. |  | AC
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
| 8 | [6 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
TAGUM CITY
5.8 |  | Rehab. of Evacuation Center, Madaum, Tagum City |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | Admin | a) | 500000 | a) | 01/14/19 | e) | - | a) | 500000 | a) | 17.17% | c) | 17.17 | a) | - | On going |  | AC
| 11 | [6 empty] | b) | Juan, Z | b) | Nov. 18, 2019 | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | PEO | c) | Jan. 16, 2019 | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | 60 CD | d) | - | [12 empty] | 1
5.9 |  | Rehab. of Evacuation Center, Magugpo Poblacion, Tagum City |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. |  | Contract | a) | 500000 | a) |  | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Amended in the AIP 3rd revision CY 2019 /SB No. 4 CY 2019 changing the total project cost to P600,000.00 |  | 1
| 11 | [6 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
5.1 |  | Rehab. of Evacuation Center, New Balambam, Tagum City |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. |  | Contract | a) | 500000 | a) | 2019-09-10 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Procurement on process |  | 1
| 11 | [6 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
5.11 |  | Rehab. Of Multi-Purpose Hall, Cuambogan, Tagum City |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. |  | Contract | a) | 500000 | a) | 2019-09-10 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Procurement on process |  | 1
| 11 | [6 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
5.12 |  | Completion of Evacuation Center, Nueva Fuerza, Tagum City |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. |  | Contract | a) | 500000 | a) | 2019-09-10 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Procurement on process |  | 1
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
| 11 | [6 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
5.13 |  | Const. of Water System, San Agustin, Tagum City |  |  | Const. of Water System to cater the needs of brgys. | - | Contract | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Re-aligned to other stimulus projects that need additional funds since there is no deed of donation for the proposed site. |  | 1
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
| 11 | [6 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
5.14 |  | Const. of Brgy. Health Center, Magugpo South, Tagum City |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Amended in the AIP 3rd revision CY 2019 /SB No. 4 CY 2019 changing the total project cost to P1,550,000.00 |  | 1
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
| 11 | [6 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
5.15 |  | Const. of Women Livelihood Center, San Isidro, Tagum City |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) | 2019-05-29 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | On -going |  | 1
[8 empty] | b) | - | b) | Jan. 2, 2020 | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
| 11 | [6 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
5.16 |  | Completion. of Water System , Busaon, Tagum City |  |  | Const. of Water System to cater the needs of brgys. |  | Contract | a) | 500000 | a) | Sept. 10, 2019 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Procurement on process |  | 1
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
| 11 | [6 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
5.17 |  | Rehab. Of Brgy. Health Center, Apokon, Tagum City |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | admin | a) | 500000 | a) | 2019-03-25 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For implementation (The brgy. council agreed not to pursue with the project if it will not be completed and needs additional funds) |  | 1
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
| 11 | [6 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
5.18 |  | Const. of Drainage Canal, Bincungan, Tagum City |  |  | Const. of Drainage Canal to cater the needs of brgys. |  | Contract | a) | 500000 | a) | Sept. 10, 2019 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Procurement on process |  | 1
| 11 | [6 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
5.19 |  | Rehab. of Evacuation Center, Mankilam, Tagum City |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) | 2019-03-25 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For implementation |  | 1
| 11 | [6 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
|  | Rehab. of Evacuation Center, Magugpo North, Tagum City |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. |  | Contract | a) | 500000 | a) | Sept. 10, 2019 | e) | - | a) | 500000 | a) | - | c) | - | a) |  | Procurement on process |  | 1
5.2 | 11 | [6 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
1
SAN ISIDRO
|  | Rehab. Of Multi-Purpose Hall , Sto. Niño, San Isidro |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | Admin | a) | 500000 | a) | 02/20/19 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | POW was revised to increase the cost for windows and approved Dec. 6, 2019 PR on process |  | AC
5.21 | 6 | [6 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
|  | Rehab. Of Water System at Purok Cabang & Mangga , Pinamuno, San Isidro |  |  | Const. of Water System to cater the needs of brgys. |  | Contract | a) | 500000 | a) | Dec. 6, 2019 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Sched. Of bidding Dec. 27, 2019 |  | 1
5.22 | 6 | [6 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
|  | Rehab. Of Water System , Igangon, San Isidro |  |  | Const. of Water System to cater the needs of brgys. | - | - | a) | 500000 | a) | 2019-05-29 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For implementation |  | 1
5.23 | 6 | [6 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
1
CARMEN |  |  |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys.
5.1 |  | Const. of Multi-Purpose Hall, La Paz, Carmen |  |  |  | - | - | a) | 500000 | a) | 02/20/19 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Fund transferred to LGU March 28, 2019 |  | AC
[8 empty] | b) | - | b) | Aug. 16, 2019 | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
5.2 |  | Const. of Evacuation Center Ph. 3, Sto. Niño, Carmen |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Amended in the AIP 3rd revision CY 2019/ SB No. 4 CY 2019 changing the location to Purok !-c, Sto. Nino since the previous location was implemented by DPWH |  | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
5.3 |  | Const. of Multi-Purpose Hall, Mangalcal, Carmen |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) | 02/20/19 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Fund transfer to LGU Carmen, 3/28/2019 with check no. 2574953 and OR no. 0118982 |  | 2
[8 empty] | b) | - | b) | Sept. 16, 2019 | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
5.4 |  | Rehab. of Multi-Purpose Hall, Guadalupe, Carmen |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) | 02/20/19 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Fund transferred to LGU March 28, 2019 |  | 2
[8 empty] | b) | - | b) | 8/15/2019 | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | 11/13/2019 | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
5.5 |  | Const. of Multi-Purpose Hall, Mabuhay, Carmen |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) | 02/20/19 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Fund transfer to LGU Carmen, 3/28/2019 with check no. 2574925 and OR no. 0118984 |  | 2
[8 empty] | b) | - | b) | Aug. 16, 2019 | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
5.6 |  | Const. Canal Lining , Mabaus, Carmen |  |  | Const. of Canal Lining to cater the needs of brgys. | - | - | a) | 500000 | a) | 02/20/19 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Fund transferred to LGU March 28, 2019 |  | 2
[8 empty] | b) | - | b) |  | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) |  | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
5.7 |  | Rehab. Of Evacuation Center, Alejal, Carmen |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) | 02/20/19 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Fund transfer to LGU Carmen, 3/28/2019 with check no.2574949 and OR no. 0118991 |  | 2
[8 empty] | b) | - | b) | Aug. 16, 2019 | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
5.8 |  | Compl. Of Evacuation Center, Tuganay, Carmen |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) | 02/20/19 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Fund transfer to LGU Carmen, 3/28/2019 with check no. 2574947 and OR no. 0118995 |  | 2
[8 empty] | b) | - | b) | Aug. 16, 2019 | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
5.9 |  | Const. of Multi-Purpose hall, Ising, Carmen |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) | 02/20/19 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Fund transferred to LGU March 28, 2019 |  | 2
[8 empty] | b) | - | b) |  | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
5.1 |  | Rehab. of Multi-Purpose hall, Cebulano, Carmen |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) | 02/20/19 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Fund transferred to LGU March 28, 2019 |  | 2
[8 empty] | b) | - | b) | Aug. 16, 2019 | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
2
PANABO CITY
5.11 |  | Rehab. Of Multi-Purpose Hall, Kasilak, Panabo City |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Amended in AIP 3rd revison CY 2019/ SB No. 4 CY 2019 increasing the project cost to P650,000.00 |  | AC
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
5.12 |  | Rehab. Of Multi-Purpose Hall, New Malitbog, Panabo City |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Amended in AIP 3rd revsion CY 2019 to change the project to Construction of Potable Water System because the original project will be funded by LGU, Panabo City (Brgy. resolution no. 25 series of 2019 dated Aug. 13, 2019 submitted) |  | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
2
[8 empty] | d) | - | d) | -
5.13 |  | Desilting of Canal, New Pandan, Panabo City |  |  | Const. of Drianage Canal to cater the needs of brgys. | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For re inspection to add length for desilting c/o Engr. Canillada Plan prepared can not consume the allocated amount of P500,000.00 for desilting works. |  | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
5.14 |  | Const. Of Multi-Purpose Hall, Waterfall, Panabo City |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For allotment. Sept. 27, 2019 |  | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
5.15 |  | Concreting of Brgy. Road @ Prk. Guyabano, Cagangohan, Panabo City |  |  | Road Concreting to cater the needs of brgys. | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Amended in AIP 3rd revision to change the project to Rehab of Evacuation Center because the original project has no deed of donation.(Brgy. resolution no 41 series of 2019 dated Aug. 16, 2019 submitted |  | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
2
[8 empty] | d) | - | d) | -
5.16 |  | Rehab. Of Evacuation Center, J.P. Laurel, Panabo City |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) | Oct. 23, 2019 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Sched. Of bidding Dec. 27, 2019 |  | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
5.17 |  | Const. Of Multi-Purpose Hall, Buenavista, Panabo City |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) | Oct. 18, 2019 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Sched. Of bidding Dec. 27, 2019 |  | 2
[8 empty] | b) | - | b) | - | f) |  | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
5.18 |  | Rehab. Of Multi-Purpose Hall, San Francisco, Panabo City |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) | Oct. 18, 2019 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Sched. Of bidding Dec. 27, 2019 |  | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) |  | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
-
5.19 |  | Rehab. Of Evacuation Center, Datu Abdul Dadia, Panabo City |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) | Oct. 18, 2019 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Sched. Of bidding Dec. 27, 2019 |  | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
5.2 |  | Impv't./Beautification of Brgy. Grounds, Quezon, Panabo City |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Re aligned to other stimulus projects that needs additional funding |  | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
5.21 |  | Const. of Women Livelihood Center Bldg. , Gredu, Panabo City |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) | 2019-03-28 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Fund transfer to LGU - 3/28/2019 with check no. 2574926 and OR no. 0166517 - March 28, 2019 |  | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
5.23 |  | Const. of Canal Lining at Purok 5, Salvacion, Panabo City |  |  | Const. of Drainage Canal to cater the needs of brgys. | - | - | a) | 500000 | a) | Oct. 18, 2019 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Procurement on process |  | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
5.24 |  | Rehab. Of Health Center, New Visayas, Panabo City |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Re aligned to other stimulus projects that needs additional funding |  | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
5.25 |  | Rehab. Of Multi-Purpose Hall, Little Panay, Panabo City |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For allotment Dec. 11, 2019 |  | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
5.26 |  | Rehab. Of Brgy. Health Center, Dalisay, Panabo City |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For allotment Dec. 4, 2019 |  | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
5.27 |  | Const. of Multi-Purpose Hall, Southern Davao, Panabo City |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For allotment Dec. 3, 2019 |  | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) |  | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
2
-
STO. TOMAS
5.28 |  | Rehab. Of Evacuation Center, Casig-ang, Sto. Tomas |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | POW preparation on-going c/o Engr. Uy |  | AC
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
5.29 |  | Const. of Brgy. Tibal-og Health Center, Tibal-og, Sto. Tomas |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | POW preparation completed amounting t oP1,550,000.00. To request for additional funds in order to complete the project to be functional |  | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - |  | Nov. 30, 2019 | [10 empty] | 2
5.3 |  | Compl.of Brgy. Public Market, La Libertad, Sto. Tomas |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) |  | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Fund transfer to LGU - 6/26/219 with check no. 2575131 and OR no. 0557457 Completed/ PCR for submission by LGU |  | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
5.31 |  | Rehab. Of Evacuation Center, New Visayas, Sto. Tomas |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) |  | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Fund transfer to LGU - 6/26/219 with check no. 2575132 and OR no. 0557455 For implementation |  | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
5.32 |  | Rehab. Of Multi-Purpose Hall, San Vicente, Sto. Tomas |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Fund transferred to LGU July 5, 2019 On -going |  | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) |  | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - |  | - | [10 empty] | 2
5.33 |  | Rehab. Of Multi-Purpose Hall, Salvacion, Sto. Tomas |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Amended in AIP 3rd revision CY 2019 /SB No. 4 CY 2019increasing the project cost to P1,000,000.00 |  | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
5.34 |  | Rehab. Of Multi-Purpose Hall, Pantaron, Sto. Tomas |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) |  | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Amended in AIP 3rd revision CY 2019 / SB No. 4 CY 2019 increasing the project cost to P550,000.00 |  | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
5.35 |  | Rehab. Of Multi-Purpose Hall, Magwawa, Sto. Tomas |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | Contract | a) | 500000 | a) | June 19 2019 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Procurement on process |  | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
5.36 |  | Compl. Of Multi-Purpose Hall, San Jose, Sto. Tomas |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) |  | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Amended in AIP 3rd revision CY 2019 / SB No. 4 CY 2019 increasing the project cost to P600,000.00 |  | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
5.37 |  | Const. of Evacuation Center, Bobongon, Sto. Tomas |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Re aligned to other stimulus projects that needs additional funding |  | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
5.38 |  | Rehab. Of Brgy. Road, Lunga-og, Sto. Tomas |  |  | Road Rehabilitation to cater the needs of brgys. | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Amended in AIP 3rd revision CY 2019 / SB No. 4 CY 2019 increasing the project cost to P600,000.00 |  | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
5.39 |  | Rehab. Of Multi-Purpose Hall, New Katipunan, Sto. Tomas |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | Contract | a) | 500000 | a) | 2019-06-07 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Procurement on process |  | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
5.4 |  | Rehab. Of Multi-Purpose Hall, San Miguel, Sto. Tomas |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | Contract | a) | 500000 | a) | 2019-06-07 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Procurement on process |  | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
5.41 |  | Rehab. Of Multi-Purpose Hall, Talomo, Sto. Tomas |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Fund transfer to LGU - 6/26/2019 with check no. 2575130 and OR no. 0557456 For implementation |  | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
IGCS | [23 empty] | 2 | 4
5.42 |  | Rehab. Of Health Center, Aumbay, IGCS |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) | Feb. 28, 2019 | e) | - | a) | 500000 | a) |  | c) | 48.32% | a) | 3 | Completed Financial obligation on process |  | AC | 4
[8 empty] | b) | Pacquiao | b) | 7/10/2019 | f) | - | b) | 500000 | b) | - | d) |  | b) | 15 |  |  | 2 | 4
[8 empty] | c) | Admin | c) | 10/7/2019 | g) | - | c) | - | [8 empty] | 2 | 4
[8 empty] | d) | 90 CD | d) | - | [12 empty] | 2 | 4
5.43 |  | Concreting of Brgy. Road From Prk. 3 to Prk. 5, Catagman, IGCS |  |  | Road Concreting to cater the needs of brgys. | - | Contract | a) | 500000 | a) | Jan. 14, 2019 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For implementation |  | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
5.44 |  | Rehab. Of Multi-Purpose Hall, San Jose, IGCS |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | Admin | a) | 500000 | a) | 2019-03-25 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | On- going |  | 2
[8 empty] | b) | Pacquiao | b) | Jan. 2, 2019 | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
5.45 |  | Elctrification at Sitio Trinidad, Bandera, IGCS |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) | 2019-03-25 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Procurement on process |  | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
5.46 |  | Rehab. Of Brgy. Health Center, Mambago-A, IGCS |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) | Feb. 28, 2019 | e) | - | a) | 500000 | a) |  | c) | 75.61% | a) | 3 | Completed Financial obligation on process |  | 2 | 4
[8 empty] | b) | Ganaba | b) | 07/2019 | f) | - | b) | 500000 | b) |  | d) |  | b) | 15 |  |  | 2 | 4
[8 empty] | c) | Admin | c) | 8/23/2019 | g) | - | c) | - | [8 empty] | 2 | 4
[8 empty] | d) | 45 CD | d) | - | [12 empty] | 2 | 4
5.47 |  | Rehab. Of Multi-Purpose Hall, Del Monte, IGCS |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | Admin | a) | 500000 | a) | 2019-05-29 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Pending/ activity undertaken by DPWH |  | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
5.48 |  | Rehab. Of Multi-Purpose Hall, Aundanao, IGCS |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | Admin | a) | 500000 | a) | 2019-03-18 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | On -going |  | 2
[8 empty] | b) | Porras | b) | Nov. 18, 2019 | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
5.49 |  | Electrification at Upper Purok Rosal, Tagbaobo, IGCS |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Procurement on process. No Abastract |  | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
5.5 |  | Const. Of Multi-Purpose Hall, Mambago-B, IGCS |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For implementation |  | 2
[8 empty] | b) | Roque | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
5.51 |  | Const. Of Multi-Purpose Hall, San Antonio, IGCS |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) | 2019-06-19 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For implementation |  | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
5.52 |  | Concreting of Brgy. Road from Prk. 1 to Prk. 2, Villarica, ICGS |  |  | Road Concreting to cater the needs of brgys. | - | Contract | a) | 500000 | a) | Jan. 14, 2019 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For implementation |  | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
5.53 |  | Rehab. Of Water System Intake Box and Pipeline, Pangubatan, IGCS |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Plan and Pow completed. Waiting of deed of donation |  | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
5.54 |  | Const. Of Multi-Purpose Hall, Cogon (Talicud), IGCS |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Procurement on process. For rebidding Dec. 12, 2019 |  | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
5.55 |  | Installation of Pipelines, Libertad, IGCS |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) | 2019-03-25 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For implementation |  | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
5.56 |  | Rehab. Of Evacuation Center, Libuak, IGCS |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) | 2019-05-29 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For implementation |  | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
5.57 |  | Const. of Water System Project, Pob. Kaputian, IGCS |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | for Allotment |  | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
2
5.58 |  | Rehab. Of Potable Water System, San Isidro, Babak, IGCS |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) | 2019-06-19 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For implementation
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) |  | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
5.59 |  | Rehab. Of Potable Water System, San Miguel, IGCS |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) | Feb. 28, 2019 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For implementation |  | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
5.6 |  | Const. of Water System Ph.II, San Remegio, IGCS |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) | 2019-05-29 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For implementation |  | 2
[8 empty] | b) | Porras | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | Admin | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
5.61 |  | Electrificatio at Prk. 1,3,4, 6,7 & 8, Licup, IGCS |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) | 02/20/19 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Procurement of materials on process |  | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
6. Rural Electrification Project (Provincewide) |  |  |  |  | Powerlines/posts installed & rehabilitated | - | - | a) | 5000000 | [12 empty] | See projects listed below |  | 2
[8 empty] | b) | Kim Pao Lu | [14 empty] | AC
[8 empty] | c) | - | [14 empty] | AC
[8 empty] | d) | - | [14 empty] | AC
|  | Rural Electrification , Del Monte, New Corella |  |  | Powerlines/posts installed & rehabilitated | - | - | a) | 3000000 | a) | - | e) | - | a) | 3000000 | a) | - | c) | - | a) | - | For implementation |  | AC
[8 empty] | b) | P.Bueno | b) | - | f) | - | b) | 3000000 | b) | - | d) | - | b) | - |  |  | 1
6.1 | 5 | [6 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
|  | Rural Electrification at St. Bundok, San Roque, New Corella |  |  | Powerlines/posts installed & rehabilitated | - | - | a) | 1000000 | a) | - | e) | - | a) | 1000000 | a) | - | c) | - | a) | - | For allotment- Dec. 3, 2019 |  | 1
[8 empty] | b) | P.Bueno | b) | - | f) | - | b) | 1000000 | b) | - | d) | - | b) | - |  |  | 1
6.2 | 5 | [6 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
|  | Rural Electrification at Pob. Kaputian, (St. Sagrada) IGCS |  |  | Powerlines/posts installed & rehabilitated | - | - | a) | 1000000 | a) | - | e) | - | a) | 1000000 | a) | - | c) | - | a) | - | Procurement on process |  | 1
[8 empty] | b) | P.Bueno | b) | - | f) | - | b) | 1000000 | b) | - | d) | - | b) | - |  |  | 2
6.3 | 10 | [6 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
2
C. 5% CALAMITY FUND CY 2019 | [23 empty] | AC
1 |  | Desiltation/Excavation of rivers and creeks |  |  | creeks and canals deislted | - | - | a) | 3000000 | [12 empty] | See project listed below |  | FS
[8 empty] | b) | Paraguya | [14 empty] | AC
[8 empty] | c) | PEO | [14 empty] | AC
[8 empty] | d) | - | [14 empty] | AC
|  | 1.1 | Desilting of Limbaan Creek, New Corella |  | creeks and canals deislted | - | - | a) | 2000000 | a) | - | e) | - | a) | 2000000 | a) | - | c) | - | a) | - | POW preparation on going |  | AC
| 5 | [6 empty] | b) | - | b) | - | f) | - | b) | 2000000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
1
a. |  | Desiltation of Mactan River Ph. II |  |  | creeks and canals deislted | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | on-going |  | 1
[8 empty] | b) | Toquero | b) | 7/29/2019 | f) | - | b) | 500000 | b) | - | d) | - | b) | - | TIME EXTENSION PROCESS |  | 1
[8 empty] | c) | Admin | c) | 9/27/2019 | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | 60 C.D | d) | - | [12 empty] | 1
2 |  | Revitment of Dike and Slope Proection |  |  | Protection dikes/slope protection | - | - | a) | 3000000 | [12 empty] | See projects listed below |  | AC
[8 empty] | b) | - | [14 empty] | AC
[8 empty] | c) | - | [14 empty] | AC
[8 empty] | d) | - | [14 empty] | AC
|  | 2.1 | Slope Protection Along Kapalong-Mabantao, Florida |  | creeks and canals deislted | - | - | a) | 1000000 | a) | - | e) | - | a) | 1000000 | a) | - | c) | - | a) | - | For cancellation funded to DPWH. Budget Transferred to |  | AC
| 4 | [6 empty] | b) | - | b) | - | f) | - | b) | 1000000 | b) | - | d) | - | b) | - | 5% Calamity Fund- Rehab and Recovery |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
b. |  | Repair/Rehab. Of Upper Tuganay Dike |  |  | creeks and canals deislted | - | - | a) | 1000000 | a) | - | e) | - | a) | 1000000 | a) | - | c) | - | a) | - | ON-GOING |  | 1
[8 empty] | b) | Toquero | b) | 8/19/2019 | f) | - | b) | 1000000 | b) | - | d) |  | b) | - | TIME EXTENSION PROCESS |  | 2
[8 empty] | c) | Admin | c) | 9/29/2019 | g) |  | c) | - | [8 empty] | 2
[8 empty] | d) | 59 C.D | d) | - | [12 empty] | 2
3 |  | Improvement of roads, drainage and canal |  |  | Protection dikes/slope protection | - | - | a) | 3000000 |  |  |  | - | [8 empty] | See projects listed below |  | 2
[8 empty] | b) | Paraguya | [14 empty] | AC
[8 empty] | c) | PEO | [14 empty] | AC
[8 empty] | d) | - | [14 empty] | AC
a. |  | Rehab./Impv't. of New Casay-Bugtong Talisay Provincial Road (Ph.II) |  |  | creeks and canRoads/Draiange/canals rehab/improved | - | - | a) | 500000 | a) | 2019-03-12 | e) |  | a) | 500000 | a) | 100% | c) | 100% | a) | 12 | Completed |  | AC
[8 empty] | b) | Toquero | b) | 2019-05-30 | f) |  | b) | 500000 | b) | - | d) | - | b) | 120 |  |  | 2
[8 empty] | c) | Admin | c) | 2019-07-30 | g) | 7/30/2019 | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
b. |  | Rehab./Impv't. of Prk. 1 - Prk. 2 Sitio Pawas Provincial Road |  |  | creeks and canRoads/Draiange/canals rehab/improved | - | - | a) | 1500000 | a) | 7/23/2019 | e) | - | a) | 1500000 | a) | 17.14% | c) | 1.18% | a) | 2 |  |  | 2
[8 empty] | b) | Sanchez | b) | 8/05/2019 | f) |  | b) | 1500000 | b) | - | d) | -15.96% | b) | 10 | On-going |  | 2
[8 empty] | c) | Admin | c) | 9/28/2019 | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | 55 | d) | - | [12 empty] | 2
c. |  | Repair/Rehab of Drainage System & Ground Gravelling at Kimamon NHS |  |  | creeks and canRoads/Draiange/canals rehab/improved | - | - | a) | 464833 | a) | - | e) | - | a) | 464833 | a) |  | c) | [5 empty] | 2
[8 empty] | b) | Azotes | b) | - | f) | - | b) | 464833 | b) |  | d) | [5 empty] | 2
[8 empty] | c) | Admin | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
2
4 |  | Improvement of bridges and cross drainage |  |  | bridge and cross drainage rehab./improved # of sq.m riprapped, culverts replaced | - | - | a) | 3000000 | [12 empty] | See projects listed below
[8 empty] | b) | Paraguya | [14 empty] | AC
[8 empty] | c) | PEO | [14 empty] | AC
[8 empty] | d) | - | [14 empty] | AC
|  | 4.1 | Impv't. of Jct. New Boholano - New Loon Cross Drainage |  | creeks and canRoads/Draiange/canals rehab/improved | - | - | a) | 2000000 | a) | - | e) | - | a) | 2000000 | a) | - | c) | - | a) | - | POW preparation on going c/o PEO-PDPM. Insufficient budget to complete required works for the project |  | AC
| 1 | [6 empty] | b) | - | b) | - | f) | - | b) | 2000000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
|  | 4.2 | Impv't. of Jct. Saug-Sonlon-Bdry. Longanapan Cross Drainage |  | creeks and canRoads/Draiange/canals rehab/improved |  | - | a) | 1000000 | a) | - | e) | - | a) | 1000000 | a) | - | c) | - | a) | - | Waiting for the delivery of Materials |  | 1
| 1 | [6 empty] | b) | - | b) | - | f) | - | b) | 1000000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
D. | SUPPLEMENTAL BUDGET NO. 1 CY 2019 | [22 empty] | AC
| 8918/Purchase / Const. / Compl./ Imprvt. Of Various Gov'y Bldgs, Structures & Facilities - General Fund Proper | [22 empty] | FS
| ■ | Purchase of Lot for Cemetery, Cambanogoy, Asuncion |  |  | Land |  | - | a) | 1500000 | a) | - | e) | - | a) | 1500000 | a) | - | c) | - | a) | - | Documents for fund transfer to be complied by the LGUs. Letter sent dated June 18, 2019 |  | AC
| 1 | [6 empty] | b) | - | b) | - | f) | - | b) | 1500000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| ■ | Purchase of Lot for Cemetery, San Roque, New Corella |  |  | Land |  | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Documents for fund transfer to be complied by the LGUs. Letter sent dated June 18, 2019 |  | 1
| 5 | [6 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| 8918/Stimulus Projects for Various Barangays. Const. in Progress - Bldgs & Other Structure | [22 empty] | 1
| ■ | Rehab/Impvt of Gymnasium, Sagayen, Asuncion |  |  | Bldg |  | - | a) | 1500000 | a) | - | e) | - | a) | 1500000 | a) | - | c) | - | a) | - | for allotment - Sept 19, 2019 |  | AC
| 1 | [6 empty] | b) | - | b) | - | f) | - | b) | 1500000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| ■ | Installation of Bleacher for the Brgy. Gym, Concepcion, Asuncion |  |  | Bldg |  | - | a) | 1000000 | a) | - | e) | - | a) | 1000000 | a) | - | c) | 30% | a) | - | On-going |  | 1
| 1 | [6 empty] | b) | - | b) | - | f) | - | b) | 1000000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
LOCALLY FUDNDED PROGRAM/PROJECT - 20% Development Fund
| Infrastructure Development Program | [22 empty] | AC
| 8918/ Stimulus Projects for Various Barangays | [22 empty] | AC
| Property, Plant and Equipment - Land | [22 empty] | AC
| ■ | Purchase of Lot for Resettlement Site, New Sambog, New Corella |  |  | Land |  | - | a) | 1500000 | a) | - | e) | - | a) | 1500000 | a) | - | c) |  | a) | - | for fund transfer. Waiting for LGU documents. Liquidation of previous fund transfer for the water system project of LGU. |  | AC
| 5 | [6 empty] | b) | - | b) | - | f) | - | b) | 1500000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| Property, Plant and Equipment - Construction in Progress-Infrastructure Assets | [22 empty] | 1
| ■ | Installation of Street Lights at Prk 1,2,3,4, Sagayen, Asuncion |  |  | Electrification |  | - | a) | 1000000 | a) | - | e) | - | a) | 1000000 | a) | - | c) |  | a) | - | PO on process |  | AC
| 1 | [6 empty] | b) | - | b) | - | f) | - | b) | 1000000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
1
| ■ | Rehab/Imprvt. Of FMR, Prk 3,7, & 8, Concepcion, Asuncion |  |  | Road |  | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) |  | a) | - | Procurement of Materials on process
| 1 | [6 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| ■ | Rural Electrification Project, Purok 6, Concepcion, Asuncion |  |  | Electrification |  | - | a) | 1000000 | a) | - | e) | - | a) | 1000000 | a) | - | c) |  | a) | - | . Re-aligned Fund allocation to Construction of Children Playground withAmenities at Pob., New Corella |  | 1
| 1 | [6 empty] | b) | - | b) | - | f) | - | b) | 1000000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| ■ | Concreting of FMR, New Santiago, Asuncion |  |  | Road |  | - | a) | 2500000 | a) | 2019-05-21 | e) | - | a) | 2500000 | a) | - | c) | 30% | a) | - | Fund transferred to LGU |  | 1
| 1 | [6 empty] | b) | - | b) | - | f) | - | b) | 2500000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| ■ | Rural Electrification Project, Purok 5-8, Napungas, Asuncion |  |  | Electrification |  | - | a) | 1500000 | a) | - | e) | - | a) | 1500000 | a) | - | c) | - | a) | - | . Re-aligned Fund allocation to Construction of Children Playground withAmenities at Pob., New Corella |  | 1
| 1 | [6 empty] | b) | - | b) | - | f) | - | b) | 1500000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| ■ | Farm to Market Road, San Jose, New Corella |  |  | Road |  | - | a) | 2000000 | a) | - | e) | - | a) | 2000000 | a) | - | c) | - | a) | - | Plan Preparation on process c/o PDPM |  | 1
| 5 | [6 empty] | b) | - | b) | - | f) | - | b) | 2000000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| ■ | Const. of Water System, New Sambog, New Corella |  |  | Water System Projects |  | - | a) | 1000000 | a) | - | e) | - | a) | 1000000 | a) | - | c) | - | a) | - | Fund transferred to LGU
| 5 | [6 empty] | b) | - | b) | - | f) | - | b) | 1000000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| ■ | Const. of Drainage Canal from Prk. 3, 1-A, 2-A to Prk 1-B, Brgy Site (Ph. 2), Limbaan, New Corella |  |  | Flood Control - Drainage |  | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | POW preparation on going c/o PDPM |  | 1
| 5 | [6 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| ■ | Const. of FMR from Prk 1 to Sitio Magsaysay via Pundol & Prk 4, Patrocenio, New Corella |  |  | Road |  | - | a) | 2000000 | a) | - | e) | - | a) | 2000000 | a) | - | c) | - | a) | - | POW preparation on going c/o PDPM |  | 1
| 5 | [6 empty] | b) | - | b) | - | f) | - | b) | 2000000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) |  | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| ■ | Const. of Multi-Purpose Pavement, San Jose, New Corella |  |  | Bldgs |  | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | POW approved but allotment not yet requested waiting for deed of donation c/o Engr. Canillada
| 5 | [6 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| Const. in Progress - Bldgs & Other Structures | [22 empty] | 1
| ■ | Rehab/Impvt of Multi-Purpose Bldg, SCFA, Napungas, Asuncion |  |  | Bldgs |  | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Fund re-aligned to fund stimulus projects that need additional funding. ( AIP 3rd revision CY 2019) |  | AC
| 1 | [6 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
1
| ■ | Const. of Multipurpose Covered Court, Buan, Asuncion |  |  | Bldgs |  | - | a) | 2500000 | a) | 2019-06-26 | e) | - | a) | 2500000 | a) | - | c) | - | a) | - | Fund transferred to LGU
| 1 | [6 empty] | b) | - | b) | - | f) | - | b) | 2500000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| ■ | Const. of Multipurpose Covered Court, Pamacaun, Asuncion |  |  | Bldgs |  | - | a) | 2500000 | a) | 2019-05-29 | e) | - | a) | 2500000 | a) | - | c) | 30% | a) | - | Fund transferred to LGU |  | 1
| 1 | [6 empty] | b) | - | b) | - | f) | - | b) | 2500000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| ■ | Const. of 2 Storey Multipurpose Hall Ph.2 (Brgy. Hall) , Poblacion, New Corella |  |  | Bldgs |  | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Plan preparation on -going c/o PDPM |  | 1
| 5 | [6 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| ■ | Rehab. Of Multi-Purpose Hall (Evacuation Ctr.) Limbaan, New Corella |  |  | Bldgs |  | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For allotment - Nov. 5, 2019
| 5 | [6 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) |  | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| ■ | Expansion of Multi-Purpose Hall ( Brgy. Hall), Patrocenio, New Corella |  |  | Bldgs |  | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Sched of bidding Dec 27 , 2019 |  | 1
| 5 | [6 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
MOOE 2019 | [9 empty] | a) |  | e) |  | a) |  | a) |  | c) |  | a) |  | For approval of POW and Plan |  | 1
|  | Repair maintenance of OPD, Pharmacy building, DDNH - CZ Compound |  |  | Renovation | - | - | a) | 100000 | b) |  | f) |  | b) |  | b) |  | d) |  | b) |  |  |  | AC
[8 empty] | b) | Estorco | c) |  | g) |  | c) | [9 empty] | 2
[8 empty] | c) | Admin | d) | [13 empty] | 2
[8 empty] | d) | - | [14 empty] | 2
E. | SUPPLEMENTAL BUDGET NO. 3 CY 2019
| LOCALLY FUNDED PROGRAM/PROJECTS- 20% DEVELOPMENT FUND | [22 empty] | FS
| INFRASTRUCTURE DEVELOPMENT PROGRAM | [22 empty] | AC
| 8918/ Various Local Roads & Drainage Development Project Construction in Progress- Infrastructure Assets | [22 empty] | AC
| ■ | Rehabilitation of Dujali-Pawas-San Vicente Provincial Road, B.E. Dujali |  |  | Road |  | - | a) | 2000000 | a) | - | e) | - | a) | 2000000 | a) | - | c) | - | a) | - | The amount was reduced to P1,102,900.00 |  | AC
[8 empty] | b) | - | b) | - | f) | - | b) | 2000000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
| ■ | Repair/Rehabil;itation of Concrete R.d. Jct. Suaon-Libuton Kapalong |  |  | Road |  | - | a) | 1000000 | a) | - | e) | - | a) | 1000000 | a) | - | c) | - | a) | - | For implementation |  | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 1000000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| 8918/ VariousWater System Development Project Construction in Progress- Infrastructure Assets | [22 empty] | 1
| ■ | Improvement of Potable Water System at Brgy. Mambago- A, Samal District, IGACOS |  |  | Water System |  | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | (Amended in the AIP 2nd Revision to change the location from Peñaplata to Samal District) PO approved September 2, 2019 |  | AC
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
| ■ | Rehabilitation of Potable Water System at Brgy. San Miguel, Samal District, IGACOS |  |  | Water System |  | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - |  |  | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
| ■ | Construction of Potable Water System at Brgy.Linusotan, Kaputian District, IGACOS |  |  | Water System |  | - | a) | 1300000 | a) | - | e) | - | a) | 1300000 | a) | - | c) | - | a) | - | (Additional 800,000.00 from Const. of PWS in purok 2, Pag-asa, Kapalong which was funded by OPAPP CY 2018) (amended) For allotment- October 15, 2019 |  | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 1300000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
| ■ | Rehabilitation of Water System in PEEDO-LPRRC, Brgy. Poblacion, New Corella |  |  | Water System |  | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For allotment- October 15, 2019 |  | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) |  | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
| 8918/ Stimulus Projects for Various Brgys.- District 1 Construction in Progress- Infrastructure Assets | [22 empty] | 2
| ■ | Construction of Water System at Brgy. San Agustin, Tagum City |  |  | Water System |  | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Declared as savings to add to stimulus projects that need additional fund No deed of donation |  | AC
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
| DISASTER REHABILITATION & RECOVERY PROGRAM Building Back Better Project | [22 empty] | 2
| Repairs & Maintenance- Infrastructure Assets | [22 empty] | AC
| ■ | Disilation of Tagum Creek |  |  |  |  | - | a) | 2000000 | a) | - | e) | - | a) | 2000000 | a) | - | c) | - | a) | - | PLAN AND POW on process c/o PEO-PDPM |  | AC
[8 empty] | b) | - | b) | - | f) | - | b) | 2000000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| ■ | Disilation of Mactan River (Ph. II) |  |  |  |  | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | PLAN AND POW on process c/o PEO-PDPM |  | 1
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
| Property, Plant and Equipmen Construction in Progress- Infrastructure Assets | [22 empty] | 2
| ■ | Rehabilitation of Pamacaun-Lasang-Banate Provincial Road |  |  |  |  | - | a) | 1500000 | a) | - | e) | - | a) | 1500000 | a) | - | c) | - | a) | - |  |  | AC
[8 empty] | b) | - | b) | - | f) | - | b) | 1500000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| ■ | Rehabilitation of Del Pilar Jct. Silangan |  |  |  |  | - | a) | 1500000 | a) | - | e) | - | a) | 1500000 | a) | - | c) | - | a) | - |  |  | 1
[8 empty] | b) | - | b) | - | f) | - | b) | 1500000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| ■ | Installation of 72" dia RCPC x 4M at San Agustin ES |  |  |  |  | - | a) | 350000 | a) | - | e) | - | a) | 350000 | a) | - | c) | - | a) | - |  |  | 1
[8 empty] | b) | - | b) | - | f) | - | b) | 350000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| ■ | Rehabilitation of Libuganon River along Kapalong Mabantao-Florida Provincial Road |  |  |  |  | - | a) | 900000 | a) | - | e) | - | a) | 900000 | a) | - | c) | - | a) | - |  |  | 1
[8 empty] | b) | - | b) | - | f) | - | b) | 900000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| ■ | Rehabilitation of Mesaoy-Jct. Mahayahay Road |  |  |  |  | - | a) | 1000000 | a) | - | e) | - | a) | 1000000 | a) | - | c) | - | a) | - |  |  | 1
[8 empty] | b) | - | b) | - | f) | - | b) | 1000000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| ■ | Rehabilitation of Dujali-Balisong-Magupising Provincial Road |  |  |  |  | - | a) | 1280000 | a) | - | e) | - | a) | 1280000 | a) | - | c) | - | a) | - |  |  | 1
[8 empty] | b) | - | b) | - | f) | - | b) | 1280000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| ■ | Rehabilitation of Sta. Fe- Mambing Road & Slope Protection |  |  |  |  | - | a) | 1320000 | a) | - | e) | - | a) | 1320000 | a) | - | c) | - | a) | - |  |  | 1
[8 empty] | b) | - | b) | - | f) | - | b) | 1320000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) |  | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
F. | SUPPLEMENTAL BUDGET NO. 4 CY 2019 | [22 empty] | 1
| INFRASTRUCTURE DEVELOPMENT PROGRAM | [22 empty] | FS
| LOCALLY FUNDED PROGRAMS/ PROJECTS GENERAL FUND PROPER | [22 empty] | AC
AC
| PEACE AND ORDER PROGRAM/1914 Construction in Progress- Land Improvements | [22 empty] | AC
| ■ | Provincial Livestock & Poultry Multiplier Farm Road Network Construction, Sitio Salawao, Sto. Niño, Talaingod |  |  |  |  | - | a) | 5500000 | a) | - | e) | - | a) | 5500000 | a) | - | c) | - | a) | - | For allotment Nov. 22, 2019 |  | AC
[8 empty] | b) | - | b) | - | f) | - | b) | 5500000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| ■ | Proposed Road Opening of Tawinian-Tapayanon Road Section |  |  |  |  | - | a) | 10000000 | a) | - | e) | - | a) | 10000000 | a) | - | c) | - | a) | - | Alloted- Dec. 6, 2019 |  | 1
[8 empty] | b) | - | b) | - | f) | - | b) | 10000000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| ■ | Rehabilitation of San Jose- Sitio Mahayahay-Magwawa Provincial Road, Sro. Tomas |  |  |  |  | - | a) | 1000000 | a) | - | e) | - | a) | 1000000 | a) | - | c) | - | a) | - | POW preparation on-going c/o South District |  | 1
[8 empty] | b) | - | b) | - | f) | - | b) | 1000000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
| 8918/ Various Government Buildigs & Facilities Development Project Construction in Progress- Land Improvements | [22 empty] | 2
| ■ | Construction of Perimeter Fence of Day Care Center I Nanyo, Panabo City |  |  |  |  | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Sched of bidding Dec. 27, 2019 |  | AC
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
| ■ | Construction of Multi-Purpose Building, Balagunan, Sto. Tomas |  |  |  |  | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For allotment Dec .3, 2019 |  | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
| ■ | Completion of Brgy. Health Center, Maniki, Kapalong |  |  |  |  | - | a) | 627000 | a) | - | e) | - | a) | 627000 | a) | - | c) | - | a) | - | PROJECT Was funded by LGU, Kapalong |  | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 627000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| INFRASTRUCTURE DEVELOPMENT PROGRAM | [22 empty] | 1
| LOCALLY FUNDED PROGRAMS/ PROJECTS 20% DEVELOPMENT FUND | [22 empty] | AC
AC
| 8918/ Rehabilitation of Various Provincial Roads, District 1 Construction in Progress- Infrastructure Assets | [22 empty] | AC
| ■ | Improvement of Km. 9 Sagayen-Sawata Provincial Road, San Isidro, Ph. 2 |  |  |  |  | - | a) | 4591029 | a) | - | e) | - | a) | 4591029 | a) | - | c) | - | a) | - |  |  | AC
[8 empty] | b) | - | b) | - | f) | - | b) | 4591029 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| 8918/ Various Local Roads and Drainaige Development Project Construction in Progress- Infrastructure Assets | [22 empty] | 1
| ■ | Rehabilitation of Local Roads at Dalisay-Manay Road Section, Panabo City |  |  |  |  | - | a) | 246100 | a) | - | e) | - | a) | 246100 | a) | - | c) | - | a) | - |  |  | AC
[8 empty] | b) | - | b) | - | f) | - | b) | 246100 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
| ■ | Rehabilitation of Local Roads at Sta. Cruz-Jct. Tagpore-Buenavista Raod Section, Panabo City |  |  |  |  | - | a) | 431000 | a) | - | e) | - | a) | 431000 | a) | - | c) | - | a) | - |  |  | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 431000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) |  | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
-
| ■ | Rehabilitation of Local Roads at Taba-Bucana Road Section, Taba, Carmen |  |  |  |  | - | a) | 220000 | a) | - | e) | - | a) | 220000 | a) | - | c) | - | a) | - |  |  | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 220000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
| 8918/ Stimulus Projects for Various Barangays Construction in Progress- Infrastructure Assets | [22 empty] | 2
| ■ | Construction of Potable Water System at Purok 6, New Santiago, Asuncion |  |  |  |  | contract | a) | 1000000 | a) | - | e) | - | a) | 1000000 | a) | - | c) | - | a) | - | For allotment Nov. 6, 2019 |  | AC
[8 empty] | b) | - | b) | - | f) | - | b) | 1000000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
| ■ | Concreting of Brgy. Road Canal, Dujali, B.E. Dujali |  |  |  |  | contract | a) | 650000 | a) | - | e) | - | a) | 650000 | a) | - | c) | - | a) | - | Alloted Oct. 18, 2019 Procurement on process |  | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 650000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
| ■ | Desilting and Conretign of Drainage-Main Collector Canal, New Casay, B.E. Dujali |  |  |  |  | contract | a) | 650000 | a) | - | e) | - | a) | 650000 | a) | - | c) | - | a) | - | For allotment - Sept. 27, 2019 |  | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 650000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
| ■ | Concreting of Drainage, Tanglaw, B.E., Dujali |  |  |  |  | contract | a) | 1200000 | a) | - | e) | - | a) | 1200000 | a) | - | c) | - | a) | - | For allotment Sept. 19, 2019 |  | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 1200000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
| ■ | Construction of Potable Water System, New Malitbog, Panabo City |  |  |  |  | contract | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For re-inspection and plan revision in order to reflect in the plan the complete details for the project to be functional.P500,000.00 covers only drilling activity |  | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
| ■ | Construction of Water System Project, Poblacion Kaputian, Samal |  |  |  |  | contract | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Alloted Oct 17, 2019 Procurement on process |  | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
| ■ | Construction of Canal Linign at Prk. 5, Salvacion, Panabo City |  |  |  |  | contract | a) | 600000 | a) | - | e) | - | a) | 600000 | a) | - | c) | - | a) | - | Alloted Oct. 18, 2019 Procurement on process |  | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 600000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
| ■ | Rehabilitation of Brgy. Road at Lunga-og. Sto. Tomas |  |  |  |  | contract | a) | 600000 | a) | - | e) | - | a) | 600000 | a) | - | c) | - | a) | - | For allotment Sept. 19, 2019 |  | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 600000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
| ■ | Construction of Children's Playground with Amenities, Poblacion, New Corella |  |  |  | Admin | contract | a) | 2500000 | a) | - | e) | - | a) | 2500000 | a) | - | c) | - | a) | - | Allotment Dec. 3, 2019 Procurement on process |  | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 2500000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| 8918/ Stimulus Projects for Various Barangays Construction in Progress- Bldgs. & Other Structures | [22 empty] | 1
| ■ | Construction of 2 Storey Multi-Purpose Hall Ph. 3 (Brgy. Hall), oblacion, New Corella |  |  |  |  | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Plan preparation on-going c/o PDPM |  | AC
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| ■ | Construction of Evacuation Center at Purok 1-C Brgy. Sto. Niño, Carmen |  |  |  |  | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For allotment Dec. 3, 2019 |  | 1
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) |  | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
| ■ | Rehabilitation of Evacuation Center at Magugpo Pob., Tagum City |  |  |  |  | - | a) | 600000 | a) | - | e) | - | a) | 600000 | a) | - | c) | - | a) | - | Sched of bidding Dec 27, 2019 |  | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 600000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| ■ | Construction of Brgy. Health Center at Magugpo South, Tagum City |  |  |  |  | - | a) | 1550000 | a) | - | e) | - | a) | 1550000 | a) | - | c) | - | a) | - | Allotd Nov. 15, 2019 Procurement on process |  | 1
[8 empty] | b) | - | b) | - | f) | - | b) | 1550000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
1
| ■ | Rehabilitation of Mulit-Purpose Building (Evacuation Center), Limbaan, New Corella |  |  |  |  | - | a) | 600000 | a) | - | e) | - | a) | 600000 | a) | - | c) | - | a) | - | For allotment nov. 5, 2019
[8 empty] | b) | - | b) | - | f) | - | b) | 600000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| ■ | Expansion of Multi-Purpose Hall ( Brgy. Hall), Patrocenio, New Corella |  |  |  |  | - | a) | 650000 | a) | - | e) | - | a) | 650000 | a) | - | c) | - | a) | - | Alloted Oct. 18, 2019 Procurement on process |  | 1
[8 empty] | b) | - | b) | - | f) | - | b) | 650000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| ■ | Construction of Multi-Purpose Hall, Waterfall, Panabo City |  |  |  |  | - | a) | 1050000 | a) | - | e) | - | a) | 1050000 | a) | - | c) | - | a) | - | For allotment |  | 1
[8 empty] | b) | - | b) | - | f) | - | b) | 1050000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
| ■ | Rehabilitation of Multi-Purpose Hall, San Francisco, Panabo City |  |  |  |  | - | a) | 600000 | a) | - | e) | - | a) | 600000 | a) | - | c) | - | a) | - | Alloted Oct. 18, 2019 Procurement on process |  | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 600000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
| ■ | Rehabilitation of Evacuation Center at Datu Abdul Dadia, Panabo City |  |  |  |  | - | a) | 650000 | a) | - | e) | - | a) | 650000 | a) | - | c) | - | a) | - | Sched of bidding -Dec 27, 2019 |  | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 650000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
| ■ | Construction of Multi-Purpose Hall, Buenavista, Panabo City |  |  |  |  | - | a) | 1050000 | a) | - | e) | - | a) | 1050000 | a) | - | c) | - | a) | - | Sched of bidding -Dec 27, 2019 |  | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 1050000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
| ■ | Rehabilitation of Multi-Purpose Hall, Llittle Panay, Panabo City |  |  |  |  | - | a) | 550000 | a) | - | e) | - | a) | 550000 | a) | - | c) | - | a) | - | For allotment Dec. 11, 2019 |  | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 550000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
| ■ | Rehabilitation of Multi-Purpose Hall, Pantaron, Sto. Tomas |  |  |  |  | - | a) | 550000 | a) | - | e) | - | a) | 550000 | a) | - | c) | - | a) | - | Alloted Oct. 18, 2019 Procurement on process |  | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 550000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
| ■ | Rehabilitation of Multi-Purpose Hall, Salvacion, Sto. Tomas |  |  |  |  | - | a) | 1000000 | a) | - | e) | - | a) | 1000000 | a) | - | c) | - | a) | - | POW preparation on-going c/o PDPM |  | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 1000000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
| ■ | Completion of Multi-Purpose Hall, San Jose, Sto. Tomas |  |  |  |  | - | a) | 600000 | a) | - | e) | - | a) | 600000 | a) | - | c) | - | a) | - | Alloted Nov. 15, 2019 Procurement on process |  | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 600000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
| ■ | Rehabilitation of Multi-Purpose Hall, Kasilak, Panabo City |  |  |  |  | - | a) | 650000 | a) | - | e) | - | a) | 650000 | a) | - | c) | - | a) | - | Alloted Nov. 15, 2019 Procurement on process |  | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 650000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) |  | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
| ■ | Rehabilitation of Brgy. Health Center, Dalisay, Panabo City |  |  |  |  | - | a) | 550000 | a) | - | e) | - | a) | 550000 | a) | - | c) | - | a) | - | For allotment Dec. 4, 2019 |  | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 550000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
2
| ■ | Rehabilitation of Evacuation Center, Kiotoy, Panabo City |  |  |  |  | - | a) | 650000 | a) | - | e) | - | a) | 650000 | a) | - | c) | - | a) | - | Sched of bidding Dec 27, 2019
[8 empty] | b) | - | b) | - | f) | - | b) | 650000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
| ■ | Rehabilitation of Evacuation Center, Cagangohan, Panabo City |  |  |  |  | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | POW for approval Nov. 5, 2019 |  | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
| ■ | Rehabilitation of Multi-Purpose Bldg. (Brgy. Hall) Tagpopongan, IGACOS |  |  |  |  | - | a) | 174460.33 | a) | - | e) | - | a) | 174460.33 | a) | - | c) | - | a) | - | For allotment Nov. 5, 2019 |  | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 174460.33 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
| 5% CALAMITY FUND | [22 empty] | 2
| DISASTER REHABILITATION & RECOVERY PROGRAM Building Back Better Project | [22 empty] | FS
| ■ | Rehabilitation of Canal Lining and Slope Protection at San Agustin E/S, San Agustin, Tagum City |  |  |  |  | - | a) | 350000 | a) | - | e) | - | a) | 350000 | a) | - | c) | - | a) | - |  |  | AC
[8 empty] | b) | - | b) | - | f) | - | b) | 350000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| TRUST FUND 2019 | [22 empty] | 1
| PROJECTS FOR PROVINCIAL VETERINARY OFFICE | [22 empty] | FS
| ■ | Poultry House and Training Center Sto. Niño, Talaingod |  |  |  |  | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - |  |  | AC
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
|  | Establishment of Multiplier Farm Project Sto. Niño, Talaingod |  |  |  |  | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - |  |  | 1
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| INFRASTRUCTURE DEVELOPMENT PROGRAM | [22 empty] | 1
| ■ | Purchase of Geo Resistivity Instrument |  |  |  |  | - | a) | 6567412 | a) | - | e) | - | a) | 6567412 | a) | - | c) | - | a) | - | Waiting for delivery of instrument |  | AC
[8 empty] | b) | - | b) | - | f) | - | b) | 6567412 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
CMGP 2019
| ■ | Road Upgrading of Sto Nino - Kabankalan - La Paz Provincial Road, Carmen |  |  |  |  | - | a) | 44461624.67 | a) |  | e) | - | a) | - | a) | 4.3% | c) | 34.23% | a) | 30 | On-going
[8 empty] | b) | Comidoy | b) | 10/7/2019 | f) | - | b) | - | b) | - | d) | 29.93% | b) | 610 |  |  | 2
[8 empty] | c) | GP & H CONST. | c) | 5/15/2020 | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | 222 C.D | d) | [13 empty] | 2
| ■ | Road Upgrading of Jct Highway - Sto Nino - La Paz - San Vicenter Provincial Road, Carmen |  |  |  |  | - | a) | 80481331.34 | a) |  | e) | - | a) | - | a) | 22.77% | c) | 33.12% | a) | - | On-going |  | 2
[8 empty] | b) | Fernandez | b) | 10/7/2019 | f) | - | b) | - | b) | - | d) | 10.35% | b) | -
[8 empty] | c) | Tagum Builders | c) | 6/22/2020 | g) | - | c) | -
[8 empty] | d) | 259 C.D | d)
| ■ | Road Upgrading of Kapalong - Mabantao - Florida Road with Bridge Component |  |  |  |  | - | a) | 15890000 | a) |  | e) | - | a) | - | a) |  | c) |  | a) | -
[8 empty] | b) |  | b) |  | f) | - | b) | - | b) | - | d) |  | b) | -
[8 empty] | c) |  | c) |  | g) | - | c) | -
[8 empty] | d) |  | d)
|  | Mark | Municipality/City |  | Color
|  | 1 | Asuncion |  | Red
|  | 2 | B.E. Dujali |  | Yellow
| GF- GENERAL FUND | 3 | Carmen |  | Blue | [10 empty] | TF - TRUST FUND (NATIONAL FUNDED PROJECT)
| 20% DF - 20% DEV'T. FUND | 4 | Kapalong |  | Pink | [10 empty] | a) SLRF - Special Local Road Fund
| 5% CF - 5% CALAMITY FUND | 5 | New Corella |  | Gray | [10 empty] | b) KALSADA - Konkreto at Ayos na Lansangan Tungo sa Pangkalahatang Kaunlaran
| CO - CAPITAL OUTLAY | 6 | San Isidro |  | Orange | [10 empty] | c) PRDP - Philippine Rural Development Projects
| CONG. FUND - CONGRESSIONAL FUND | 7 | Sto Tomas |  | Sky Blue | [10 empty] | d) SELAP - Support to Emergency and Livelihood Assistance Project
|  | 8 | Talaingod |  | Violet | [10 empty] | e) PAMANA - Payapa at Masaganang Pamayanan
| SEF - SPECIAL EDUCATIONAL UFND | 9 | Panabo City |  | Brown | [10 empty] | f) CBRMC - Community Based Road Maintenance Contracting
|  | 10 | IGACOS |  | Yellow Green | [10 empty] | g) MBC - Maintenance by Contract
|  | 11 | Tagum City |  | Green | [10 empty] | h) PCF-Performance Challenge Fund-DILG
i) FMRDP - Farm to Market Road
j.) CMGP - Conditional Grant to Provinces
k.) OPAPP - Office of the President Adviser on the Peace Process
l.) LGSF-AM - Local Government Support Fund Assistance to Municipalities
Prepared by: |  |  |  | Checked | [12 empty] | Recommending Approval
Noted
GILBERT G. MAMBULAO JR |  |  |  | ELISA A. BARCENA | TESSIE G. ABABON | [9 empty] | JIVELLYN B. CO | [5 empty] | GLENN A. OLANDRIA
Engineer II |  |  |  | Engineer IV- Engineering Dist 1, Area Engineer |  | Engineer IV-Engineering Dist 2, Area Engineer | [9 empty] | Asst. PG-Department Head |  |  |  |  | Provincial Engineer
AMELITA TIMBAL
Engineer I |  |  |  | EDWIN S. MISA |  |  |  | MARILOU A. FORONDA
|  |  |  | Engineer IV- PDPM Division Head |  |  |  | Engineer IV- QC Division Head

## Annual 2019_Completed (hidden)
PROVINCE OF DAVAO DEL NORTE
ACCOMPLISHMENT REPORT
Annual 2019
SECTOR: ECONOMIC (INFRASTRUCTURE DEV'T. PROGRAM)
OFFICE/AGENCY: PROVINCIAL ENGINEER'S OFFICE
COMPLETED PROJECTS
| Name of Project |  |  |  |  | Type | Physical | Mode | PROJECT DATA | [5 empty] | Financial (000) |  | Physical Accomplishment |  |  |  | Employment |  | REMARKS
[6 empty] | of | Target | of | a) Project Cost |  | a) Date A lot. Rel. |  | e) # of days suspended |  | a) Program |  | a) Planned |  | c) Actual |  | Generated
[6 empty] | Project | (Descrip | Impl. | b) Project Engineer |  | b) Date Started |  | f) # of days extended |  | b) Allotment |  | b) Revised |  | d) Slippage |  | a) # of Persons
[6 empty] | (Location) | tion) |  | c) Implementor |  | c)Target Compl. Date |  | g) Date completed |  | c) Disbursement | [5 empty] | b) Man-days
[9 empty] | d) Duration |  | d) Revised Compl. Date
| I. | PROJECTS UNDER THE CONTINUING APPROPRIATION | [21 empty] | AP | 893809.45
|  | A. | TRUST FUND | [20 empty] | AC
|  |  | DILG FUND CY 2016 | [20 empty] | AC
|  |  | 1.1 | 1.1 Improvement of DILG Building, Gov't. |  | Bldg. | 400 sq.m | Contract | a) | 5000000 | a) | CY 2016 | e) | 35 days | a) | 5000000 | a) | 100.00% | c) | 100.00% | a) | 8 | Completed as per physical accomplishment. | 1
|  |  |  | Center, Mankilam, Tagum City |  |  |  |  | b) | Pasiona | b) | 06/01/18 | f) | - | b) | 5000000 | b) | - | d) | - | b) | 240 | Financial documents still on process | 1
[9 empty] | c) | PEO | c) | 12/31/18 | g) | 03/31/19 | c) | 4,786,995.44 | [7 empty] | 1
[9 empty] | d) | 249 CD | d) | 03/30/19 | [11 empty] | 1
|  |  | KALSADA CY 2016 | [20 empty] | AC
|  |  | 1.1 Upgrading of Prk. Narafil – Barangay |  |  | Road | 2.03 | Contract. | a) | 51420795.98 | a) | CY 2016 | e) | - | a) | 51420795.98 | a) | 100.00% | c) | 100.00% | a) | 12 | Completed as per physical accomplishment. | 2
|  |  | Site Magupising Provincial Road | [5 empty] | b) | Andoy | b) | 04/18/18 | f) | 178 CD | b) | 51420795.98 | b) | - | d) | - | b) | 336 | Financial documents still on process | 2
|  |  | (Part of 60.329230.72M) (Contract Cost: P 43.597322.62M) | [5 empty] | c) | DCP | c) | 12/20/18 | g) | 05/07/19 | c) | 46,279,283.18 | [7 empty] | 2
[9 empty] | d) | 247 CD | d) | 05/07/19 | [11 empty] | 2
AC
|  |  | PAMANA-DILG CY 2016 | [20 empty] | AC
|  |  |  | Construction of Civic Center, San Isidro, |  | Bldg. | - | Admin | a) | 2,000,000.00 | a) | CY 2016 | e) | 40 CD | a) | 2,000,000.00 | a) | 100.00% | c) | 100.00% | a) | 8 | Completed as per physical accomplishment. | 1
|  |  |  | Tagum City |  |  |  |  | b) | Escurzon | b) | 7/5/2018 | f) | - | b) | 2,000,000.00 | b) | - | d) | - | b) | 240 | Financial documents still on process | 1
[9 empty] | c) | MAG Carp. | c) | 12/06/18 | g) | 01/15/19 | c) | - | [7 empty] | 1
[9 empty] | d) | 155 CD | d) | 01/15/19 | [11 empty] | 1
|  | A. | OPPAP-PAMANA | [20 empty] | AC
|  |  | Construction of Processing and Bagsakan Center |  |  | Bldg. | 300 sq.m | Contract | a) | 2500000 | a) | 08/15/18 | e) | - | a) | 2500000 | a) | 100.00% | c) | 100% | a) | 6 | Completed as per physical accomplishment. | 1
|  |  | Brgy. Palma Gil, Talaingod | [5 empty] | b) | Dadula | b) | 02/02/19 | f) | 35 CD | b) | 2500000 | b) |  | d) |  | b) | 180 | Financial documents still on process | 1
[9 empty] | c) | Alpha & Omega | c) | 05/12/19 | g) | 07/19/2019 | c) | [8 empty] | 1
[9 empty] | d) | 100 CD | d) | - | [11 empty] | 1
|  | B. | 20% Development Fund CY 2015 | [20 empty] | AC
|  |  | Improvement of Potable Water System Level II, |  |  | Water |  | Admin | a) | 1,125,000.00 | a) | 08/31/17 | e) | 222 CD | a) | 1,125,000.00 | a) | 100.00% | c) | 100% | a) | 4 | Completed 7/2/2019 as per physical accomplishment. Financial Documents still on process | 2
|  |  | Toril, IGCS |  |  | System |  |  | b) | Porras | b) | 02/19/18 | f) | 83 CD | b) | 1,125,000.00 | b) | - | d) | 0% | b) | 12 |  | 2
[9 empty] | c) | PEO | c) | 06/29/18 | g) | 7/2/2019 | c) | 1,009,555.97 | [7 empty] | 2
[9 empty] | d) |  | d) | 04/30/19 | [11 empty] | 2
|  | C. | 20% Development Fund CY 2016 | [20 empty] | AC
|  |  | 1. Water System Development Projects | [20 empty] | AC
|  | (Provincewide) | [21 empty] | AC
|  |  |  | Improvement of Potable Water System Level II, |  | Water |  | Admin | a) | 525,000.00 | a) | 08/31/17 | e) | 222 CD | a) | 525,000.00 | a) | 100% | c) | 100% | a) | 4 | Completed 7/2/2019 as per physical accomplishment. Financial Documents still on process | 2
|  |  |  | Toril, IGCS |  | System |  |  | b) | Porras | b) | 02/19/18 | f) | 83 CD | b) | 525,000.00 | b) | - | d) | 0% | b) | 12 |  | 2
[9 empty] | c) | PEO | c) | 06/29/18 | g) | 7/2/2019 | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | 04/30/19 | [11 empty] | 2
|  |  | 3. Const./Rehab./Comp. of Various Gov't. Bldgs. |  |  | Bldgs./ | - | Admin | a) | 9,000,000.00 | [13 empty] | AC
|  |  | Struct., Fac. (Provincewide) |  |  | Fence |  |  | b) | Foronda/Ababon | [13 empty] | AC
[9 empty] | c) | PEO | [13 empty] | AC
|  |  |  | Const./Impv't./Renov. Of DAVNOR Pharmacy |  | Bldg. |  | Admin | a) | 500,000.00 | a) | 08/10/18 | e) | 92 | a) | 500,000.00 | a) | 100% | c) | 100% | a) | 45 | Completed 6/28/2019 as per physical accomplishment. Financial documents still on process | 2
|  |  |  | Building, DDNH-CZ Compound |  |  |  |  | b) | Estorco | b) | 01/14/19 | f) | - | b) | 500,000.00 | b) | 100% | d) | 0% | b) | 3 |  | 2
|  |  |  | (Carmen District Hospital) |  |  |  |  | c) | Admin | c) | 03/26/19 | g) | 06/28/2019 | c) | 415,227.26 | [7 empty] | 2
[11 empty] | d) | 2019-06-28 | [11 empty] | 2
|  |  | SLRF 2015 | [7 empty] | a) |  | e) | 65 days | a) |  | a) | 100% | c) | 100% | a) | 3 | Completed as per POW, Financial Documents on Process | AC
|  |  | Rehab. of Jct. Highway-Tuganay-Anibongan-BE Dujali-Kinamayan Provincial Road (Furtheranace) |  |  | Slope protection | - | - | a) | 1911175.99 | b) | 2019-02-18 | f) | 47 days | b) |  | b) |  | d) | 0% | b) | 60 |  | 2
[9 empty] | b) | Balbastro | c) | 2019-09-21 | g) | 9/21/2019 | c) | [8 empty] | 2
[9 empty] | c) | Admin | d) | [12 empty] | 2
[9 empty] | d) | - | [13 empty] | 2
|  |  | TRUST FUND 2017 | [20 empty] | AC
|  |  | Conditional Matching Grant to Provinces (CMGP) | [20 empty] | AC
|  |  |  | Road Upgrading of FDR. Rd.3 – |  | Conc. | 10.359 km | Contract. | a) | 119901954.82 | a) | CY 2017 | e) | 47 CD | a) | 119901954.82 | a) | 100.00% | c) | 100% | a) | 10 | Completed based on POW, Financial Documents on Process | 2
|  |  |  | Kimamon – Luna Provincial Road, |  |  |  |  | b) | Comidoy | a) | 12/29/17 | f) | 198 CD | b) | 119901954.82 | b) | 100% | d) | 100% | b) | 220 |  | 2
|  |  |  | Sto. Tomas |  |  |  |  | c) | GP & H CONST. | c) | 12/12/18 | g) | - | c) | 119901954.82 | [7 empty] | 2
[9 empty] | d) | 326 CD | d) | 2019-07-29 | [11 empty] | 2
|  |  |  | Road Upgrading of Anahaw-Maligaya |  | Conc. | 5.18 km | Contract. | a) | 78,228,121.56 | a) | CY 2017 | e) | - | a) | 78,228,121.56 | a) | 100.00% | c) | 100% | a) | 30 | Completed based on POW, Financial Documents on Process | 2
|  |  |  | Provincial Road, Carmen |  |  |  |  | b) | Fernandez | b) | 12/24/17 | f) | 306 CD | b) | 78,228,121.56 | b) | 100% | d) | 0% | b) | 660 |  | 2
[9 empty] | c) | MONOLITHIC CONST. | c) | 03/31/19 | g) | - | c) | 76,214,361.38 | [7 empty] | 2
[9 empty] | d) | 210 CD | d) | 2019-06-05 | [11 empty] | 2
4 |  | 8 |  | Road Upgrading of Dagohoy - Daligdigon |  | Road | 2.532 km | Contract | a) | 58048310.68 | a) | CY 2017 | e) | - | a) | 58048310.68 | a) | 100.00% | c) | 100% | a) | 16 | Completed as per Physical Accomplishment, Financial Documents on Process | 1
4 |  |  |  | Provincial Road |  |  |  |  | b) | Fabiala | b) | 01/05/18 | f) | 205 CD | b) | 58048310.68 | b) | - | d) | 0% | b) | 480 |  | 1
4 | [8 empty] | c) | PUREGOLD | c) | 11/18/18 | g) | - | c) | 29,572,637.70 | [7 empty] | 1
4 | [8 empty] | d) | 246 CD | d) | 03/31/19 | [11 empty] | 1
4 |  |  |  | Impv’t. of Maligaya-New Camiling Prov’l. |  | Conc. | 2.13 km | Contract. | a) | 50101614.08 | a) | CY 2017 | e) | 76 CD | a) | 57385680 | a) | 100.00% | c) | 100% | a) | 21 | Completed based on POW. Financial Documents on process | 2
4 |  |  |  | Road w/ Bridge Component,Carmen |  |  |  |  | b) | Mellomida | b) | 12/18/17 | f) | 209 CD | b) | 57385680 | b) | 100% | d) | 0% | b) | 147 |  | 2
4 | [8 empty] | c) | PUREGOLD CONST. | c) | 02/15/19 | g) | - | c) | 36005452 | [7 empty] | 2
4 | [8 empty] | d) | 376 CD | d) | 07/31/19 | [11 empty] | 2
|  |  | OPPAP PAMANA | [20 empty] | AC
|  |  | Tribal Hall | [20 empty] | AC
|  |  |  | Construction of Tribal Hall |  | Bldg. |  | Admin | a) | 500000 | a) | CY 2018 | e) | - | a) | 500000 | a) | 100% | c) | 100% | a) | 5 | Completed as per Physical Accomplishment. Financial Documents on process | 1
|  |  |  | Brgy. Gupitan, Kapalong |  |  |  |  | b) | Ambrocio | b) | 2/22/2019 | f) | - | b) | 500000 | b) | - | d) | 0% | b) | 150 |  | 1
[9 empty] | c) | PEO | c) | 5/22/2019 | g) | - | c) | - | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | Processing and Bagsakan Center | [20 empty] | AC
|  |  |  | Const. of Processing and Bagsakan Center, |  | Bldg. | 300 sq.m | Contract | a) | 2500000 | a) | 08/29/18 | e) | - | a) | 2500000 | a) | 100% | c) | 100% | a) | 6 | Completed as per Physical Accomplishment. Financial Documents on process | 1
|  |  |  | Brgy. Gupitan, Kapalong, Davao del Norte |  |  |  |  | b) | Ambrucio | b) | 02/12/19 | f) | - | b) | 2500000 | b) | - | d) | 0% | b) | 180 |  | 1
[9 empty] | c) | Alpha & Omega | c) | 05/12/19 | g) | - | c) | 156000 | [7 empty] | 1
[9 empty] | d) | 120 CD | d) | - | [11 empty] | 1
|  |  |  | Construction of Processing and Bagsakan Center |  | Bldg. | 300 sq.m | Contract | a) | 2500000 | a) | 08/15/18 | e) | - | a) | 2500000 | a) | 100.00% | c) | 100% | a) | 6 | Completed as per physical accomplishment. | 1
|  |  |  | Brgy. Palma Gil, Talaingod |  |  |  |  | b) | Dadula | b) | 02/02/19 | f) | 35 CD | b) | 2500000 | b) |  | d) |  | b) | 180 | Financial documents still on process | 1
[9 empty] | c) | Alpha & Omega | c) | 05/12/19 | g) | 07/19/2019 | c) | [8 empty] | 1
[9 empty] | d) | 100 CD | d) | - | [11 empty] | 1
|  | D. | 20% Development Fund CY 2017 | [20 empty] | AC
|  |  | STIMULUS PROJECTS CY 2017 | [20 empty] | AC
|  |  | TAGUM CITY | [20 empty] | AC
|  |  |  | Impv't. of Magdum Barangay Hall, |  | Bldgs. |  | Admin | a) | 500000 | a) | 11/29/17 | e) | - | a) | 500000 | a) | 100.00% | c) | 100.00% | a) | 6 | Completed as per physical accomplishment. | 1
|  |  |  | Magdum, Tagum City |  |  |  |  | b) | Pasiona | b) | 04/23/18 | f) | 10 CD | b) | 500000 | b) | - | d) | - | b) | 108 | Financial documents still on process | 1
[9 empty] | c) | PEO | c) | 06/11/18 | g) | 06/21/18 | c) | 484028 | [7 empty] | 1
[9 empty] | d) | 50 CD | d) | 06/21/18 | [11 empty] | 1
|  |  |  | Const. Stage, Canocotan, Tagum City |  | Bldgs. |  | Contract | a) | 500000 | a) | 12/28/17 | e) | - | a) | 500000 | a) | 100.00% | c) | 100.00% | a) | 7 | Completed as per physical accomplishment. | 1
[9 empty] | b) | Escurzon | b) | 06/01/18 | f) | - | b) | 500000 | b) | - | d) | - | b) | 140 | Financial documents still on process | 1
[9 empty] | c) | FT Construction | c) | 07/15/18 | g) | 08/22/18 | c) | 457128.95 | [7 empty] | 1
[9 empty] | d) | 45 CD | d) | - | [11 empty] | 1
|  |  |  | Construction of Bleachers and Firewall |  | Bldgs. |  | Contract | a) | 500000 | a) | 06/05/18 | e) | - | a) | 500000 | a) | 100.00% | c) | 100.00% | a) | 6 | Completed as per physical accomplishment. | 1
|  |  |  | for the GYM, Magugpo West, Tagum City |  |  |  |  | b) | Medalla | b) | 09/13/18 | f) | - | b) | 500000 | b) | - | d) | - | b) | 180 | Financial documents still on process | 1
[9 empty] | c) | RLHV | c) | 11/08/18 | g) | 11/08/18 | c) | 473595.97 | [7 empty] | 1
[9 empty] | d) | 60 CD | d) | - | [11 empty] | 1
|  |  |  | Const. of 1 Bay Span Covered Court, |  | Court | 96 sq.m | Contract | a) | 500000 | a) | 06/05/18 | e) | - | a) | 500000 | a) | 100.00% | c) | 100.00% | a) | 5 | Completed as per physical accomplishment. | 1
|  |  |  | Brgy. La Filipina, Tagum City |  |  |  |  | b) | Medalla | b) | 12/10/18 | f) | - | b) | 500000 | b) | - | d) | - | b) | 150 | Financial documents still on process | 1
[9 empty] | c) | FT Const. | c) | 01/29/19 | g) | 04/12/19 | c) | - | [7 empty] | 1
[9 empty] | d) | 50 CD | d) | - | [11 empty] | 1
|  |  | SAN ISIDRO | [20 empty] | AC
|  |  |  | Rehab. Of Sawata Gymnasiun, San Isidro |  | Bldgs. |  | Contract | a) | 500000 | a) | 11/29/17 | e) | - | a) | 500000 | a) | 100.00% | c) | 100.00% | a) | 6 | Completed as per physical accomplishment. | 1
[9 empty] | b) | Escurzon | b) | 01/06/18 | f) | 15 CD | b) | 500000 | b) | - | d) | - | b) | 180 | Financial documents still on process | 1
[9 empty] | c) | FT Construction | c) | 05/07/18 | g) | 07/25/18 | c) | 474,700.57 | [7 empty] | 1
[9 empty] | d) | 35 CD | d) | 07/20/18 | [11 empty] | 1
|  |  |  | Compl. Of Pipeline Level II, Brgy. San Miguel, |  | Bldgs. |  | Contract | a) | 500000 | a) | 12/28/17 | e) | - | a) | 500000 | a) | 100.00% | c) | 100.00% | a) | 5 | Completed as per physical accomplishment. | 1
|  |  |  | San Isidro |  |  |  |  | b) | Diosanta | b) | 05/25/18 | f) | 28 CD | b) | 500000 | b) | - | d) | - | b) | 100 | Financial documents still on process | 1
[9 empty] | c) | ZULAR - AZ Const. & Supply | c) | 06/07/18 | g) | 07/25/18 | c) | 479116.61 | [7 empty] | 1
[9 empty] | d) | 24 CD | d) | 07/05/18 | [11 empty] | 1
|  |  |  | Const. of Covered Court, Datu Balong, |  | Bldgs. |  | Contract | a) | 500000 | a) | 11/29/17 | e) | - | a) | 500000 | a) | 100.00% | c) | 100.00% | a) | 5 | Completed as per physical accomplishment. | 1
|  |  |  | San Isidro |  |  |  |  | b) | Escurzon | b) | 01/06/18 | f) | - | b) | 500000 | b) | - | d) | - | b) | 90 | Financial documents still on process | 1
[9 empty] | c) | FT Construction | c) | 07/10/18 | g) | 08/31/18 | c) | 472019.86 | [7 empty] | 1
[9 empty] | d) | 40 CD | d) | - | [11 empty] | 1
|  |  |  | Const. of Brgy. Stage, Linao, San Isidro |  | Bldgs. |  | Contract | a) | 500000 | a) | 11/29/17 | e) | - | a) | 500000 | a) | 100.00% | c) | 100.00% | a) | 12 | Completed as per physical accomplishment. | 1
[9 empty] | b) | Escurzon | b) | 01/06/18 | f) | 15 CD | b) | 500000 | b) | - | d) | - | b) | 216 | Financial documents still on process | 1
[9 empty] | c) | FT Construction | c) | 05/07/18 | g) | 09/03/18 | c) | 465500 | [7 empty] | 1
[9 empty] | d) | 45 CD | d) | 07/15/18 | [11 empty] | 1
|  |  |  | Const. of Potable Water System, Monte |  | Bldgs. |  | Contract | a) | 500000 | a) | 12/28/17 | e) | - | a) | 500000 | a) | 100.00% | c) | 100.00% | a) | 6 | Completed as per physical accomplishment. | 1
|  |  |  | Dujali, San Isidro |  |  |  |  | b) | Escurzon | b) | 01/06/18 | f) | 20 CD | b) | 500000 | b) | - | d) | - | b) | 180 | Financial documents still on process | 1
[9 empty] | c) | FT Construction | c) | 07/30/18 | g) | 09/07/18 | c) | 470612.51 | [7 empty] | 1
[9 empty] | d) | 60 CD | d) | 08/25/18 | [11 empty] | 1
|  |  |  | Const. of Covered Court , Libuton, San Isidro |  | Bldgs. |  | Contract | a) | 500000 | a) | 11/29/17 | e) | - | a) | 500000 | a) | 100.00% | c) | 100.00% | a) | 6 | Completed as per physical accomplishment. | 1
[9 empty] | b) | Escurzon | b) | 01/06/18 | f) | - | b) | 500000 | b) | - | d) | - | b) | 180 | Financial documents still on process | 1
[9 empty] | c) | FT Construction | c) | 07/15/18 | g) | 08/22/18 | c) | 476716.56 | [7 empty] | 1
[9 empty] | d) | 45 CD | d) | - | [11 empty] | 1
|  |  |  | Improvement of Barangay Hall Perimeter |  | Bldgs. |  | Contract | a) | 500000 | a) | 11/29/17 | e) | - | a) | 500000 | a) | 100.00% | c) | 100.00% | a) | 6 | Completed as per physical accomplishment. | 1
|  |  |  | Fence, Brgy. Dakudao, San Isidro |  |  |  |  | b) | Escurzon | b) | 06/01/18 | f) | 26 CD | b) | 500000 | b) | - | d) | - | b) | 180 | Financial documents still on process | 1
[9 empty] | c) | FT Const. | c) | 07/30/18 | g) | 09/04/18 | c) | '468,532.48 | [7 empty] | 1
[9 empty] | d) | 60 CD | d) | 08/25/18 | [11 empty] | 1
|  |  | ASUNCION | [20 empty] | AC
|  |  |  | Completion of Magatos E/S Perimeter |  | Bldgs. |  | MEO | a) | 500000 | a) | 12/28/17 | e) | - | a) | 500000 | a) | 100.00% | c) | 100.00% | a) | 19 | Completed as per physical accomplishment | 1
|  |  |  | Fence, Asuncion |  |  |  |  | b) | Inquillon | b) | 06/01/18 | f) | - | b) | 500000 | b) | - | d) | - | b) | 426 | - Fund transferred at Municipality of Asuncion | 1
[9 empty] | c) | MEO | c) | 07/30/17 | g) | 07/30/17 | c) | 500000 | [6 empty] | with ChecK No. 2445178 and OR # 9238462, | 1
[9 empty] | d) | - | d) | - | [10 empty] | dated March 16, 2018 | 1
|  |  |  | Const. of Covered Court Ph.1, Camansa, |  | Bldgs. |  | MEO | a) | 500000 | a) | 12/19/17 | e) | - | a) | 500000 | a) | 100.00% | c) | 100.00% | a) | 15 | Completed as per physical accomplishment. | 1
|  |  |  | Asuncion |  |  |  |  | b) | Inquillon | b) | 05/16/18 | f) | - | b) | 500000 | b) | - | d) | - | b) | 399 | - Fund transferred at Municipality of Asuncion | 1
[9 empty] | c) | MEO | c) | 09/15/18 | g) | 07/15/18 | c) | 500000 | [6 empty] | with ChecK No. 2445090 and OR # 8975230, | 1
[9 empty] | d) | - | d) | - | [10 empty] | dated February 5, 2018 | 1
|  |  |  | FMR 0.5km at Brgy. Site, Sonlon, |  | Bldgs. |  | MEO | a) | 500000 | a) | 12/28/17 | e) | - | a) | 500000 | a) | 100.00% | c) | 100.00% | a) | 12 | Completed as per physical accomplishment. (Fund already transferred at Municipality of Asuncion with ChecK No. 2445173 and OR # 9238463, dated March 16, 2018) | 1
|  |  |  | Asuncion |  |  |  |  | b) | Inquillon | b) | 2018-06-18 | f) | - | b) | 500000 | b) | - | d) | - | b) | 156 |  | 1
[9 empty] | c) | MEO | c) | 08/15/18 | g) | 08/10/18 | c) | 500000 | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  |  | Const. of Covered Court Ph. 1, Sta. |  | Bldgs. |  | MEO | a) | 500000 | a) | 12/28/17 | e) | - | a) | 500000 | a) | 100.00% | c) | 100.00% | a) | 13 | Completed as per physical accomplishment | 1
|  |  |  | Felomina, Asuncion |  |  |  |  | b) | Inquillon | b) | 06/18/18 | f) | - | b) | 500000 | b) | - | d) | - | b) | 426 | - Fund transferred at Municipality of Asuncion | 1
[9 empty] | c) | MEO | c) | 08/15/18 | g) | 08/05/18 | c) | 500000 | [6 empty] | with ChecK No. 2445177 and OR # 9238464, | 1
[9 empty] | d) | - | d) | - | [10 empty] | dated March 16, 2018 | 1
|  |  |  | Impv't. of Brgy. Facilities, Buclad, Asuncion |  | Bldgs. |  | MEO | a) | 500000 | a) | 12/19/17 | e) | - | a) | 500000 | a) | 100.00% | c) | 100.00% | a) | 12 | Completed as per physical accomplishment. (Fund already transferred at Municipality of Asuncion with ChecK No. 2445032 and OR # 8975234, dated February 5, 2018) | 1
[9 empty] | b) | Inquillon | b) | 04/30/18 | f) | - | b) | 500000 | b) | - | d) | - | b) | 364 |  | 1
[9 empty] | c) | MEO | c) | 07/30/18 | g) | 2018-06-30 | c) | 500000 | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  |  | Impv't. of Brgy. Hall, Cabaywa, Asuncion |  | Bldgs. |  | MEO | a) | 500000 | a) | 12/19/17 | e) | - | a) | 500000 | a) | 100.00% | c) | 100.00% | a) | 11 | Completed as per physical accomplishment. | 1
[9 empty] | b) | Inquillon | b) | 05/18/18 | f) | - | b) | 500000 | b) | - | d) | - | b) | 358 | - Fund transferred at Municipality of Asuncion | 1
[9 empty] | c) | MEO | c) | 08/16/18 | g) | 07/02/18 | c) | - | [6 empty] | with ChecK No. 2445031 and OR # 8975233, | 1
[9 empty] | d) | - | d) | - | [10 empty] | dated February 5, 2018 | 1
|  |  |  | Impv't. of Multi-Purpose Bldg., Napungas |  | Bldgs. |  | MEO | a) | 500000 | a) | 12/28/17 | e) | - | a) | 500000 | a) | 100.00% | c) | 100.00% | a) | 14 | Completed as per physical accomplishment. (Fund already transferred at Municipality of Asuncion with ChecK No. 2445147 and OR # 8975232, dated February 5, 2018) | 1
|  |  |  | Asuncion |  |  |  |  | b) | Inquillon | b) | 06/16/18 | f) | - | b) | 500000 | b) | - | d) | - | b) | 207 |  | 1
[9 empty] | c) | MEO | c) | 07/30/18 | g) | 07/30/18 | c) | 500000 | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  |  | Construction of Multi-Purpose Stage, |  | Bldgs. |  | MEO | a) | 500000 | a) | 12/19/17 | e) | - | a) | 500000 | a) | 100.00% | c) | 100.00% | a) | 18 | Completed as per physical accomplishment. (Fund already transferred at Municipality of Asuncion with ChecK No. 2445030 and OR # 8975231, dated February 5, 2018 (Compl: Aug. 16, 2018) | 1
|  |  |  | Binancian, Asuncion |  |  |  |  | b) | Inquillo | b) | 05/18/18 | f) | - | b) | 500000 | b) | - | d) | - | b) | 396 |  | 1
[9 empty] | c) | MEO | c) | 08/16/18 | g) | 08/16/18 | c) | 500000 | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  |  | Construction of Covered Court Ph. 1, |  | Bldgs. |  | MEO | a) | 500000 | a) | 02/06/18 | e) | - | a) | 500000 | a) | 100.00% | c) | 100.00% | a) | 14 | Completed as per physical accomplishment | 1
|  |  |  | Buan, Asuncion |  |  |  |  | b) | Inquillo | b) | 06/01/18 | f) | - | b) | 500000 | b) | - | d) | - | b) | 430 | - Fund transferred at Municipality of Asuncion | 1
[9 empty] | c) | MEO | c) | 08/30/18 | g) | 07/30/18 | c) | 500000 | [6 empty] | with ChecK No. 2445282 and OR # 9238466, | 1
[9 empty] | d) | - | d) | - | [10 empty] | dated March 16, 2018. | 1
|  |  |  | Construction of Nutrition Bldg. Ph. 1, |  | Bldgs. |  | MEO | a) | 500000 | a) | 12/20/17 | e) | - | a) | 500000 | a) | 100.00% | c) | 100.00% | a) | 9 | Completed as per physical accomplishment | 1
|  |  |  | Cambanogoy, Asuncion |  |  |  |  | b) | Inquillo | b) | 07/16/18 | f) | - | b) | 500000 | b) | - | d) | - | b) | 135 | - Fund transferred at Municipality of Asuncion with | 1
[9 empty] | c) | MEO | c) | 08/14/18 | g) | 11/15/18 | c) | 500000 | [6 empty] | ChecK No. 24465176 and OR # 9238465, | 1
[9 empty] | d) | - | d) | - | [10 empty] | dated March 16, 2018 | 1
|  |  |  | Rehab. Of 2 Inches Pipelines of Water System |  | Bldgs. |  | MEO | a) | 500000 | a) | 12/28/17 | e) | - | a) | 500000 | a) | 100.00% | c) | 100.00% | a) | 12 | Completed as per physical accomplishment | 1
|  |  |  | at Prk. 1, New Loon, Asuncion |  |  |  |  | b) | Inquillo | b) | 08/05/18 | f) | - | b) | 500000 | b) | - | d) | - | b) | 180 | -Fund transferred at Municipality of Asuncion with | 1
[9 empty] | c) | MEO | c) | 11/15/18 | g) | 11/15/18 | c) | 500000 | [6 empty] | ChecK No. 2445175 and OR # 9238467, | 1
[9 empty] | d) | - | d) | - | [10 empty] | dated March 16, 2018 | 1
|  |  | NEW CORELLA | [20 empty] | 1
|  |  |  | Fabrication of Bleachers, New Cortez, |  | Bldgs. |  | MEO | a) | 500000 | a) | 12/28/17 | e) | - | a) | 500000 | a) | 100.00% | c) | 100.00% | a) | - | Completed as per physical accomplishment. (Fund already transferred at Municipality of New Corella with ChecK No. 2445146 and OR # 8592069, dated March 13, 2018) | 1
|  |  |  | New Corella |  |  |  |  | b) | Inquillo & Dogoldogol | b) | 06/15/18 | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 1
[9 empty] | c) | MEO | c) | 07/31/18 | g) | 07/31/18 | c) | 500000 | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  |  | Renov./Impv't. Of Brgy. Hall, New Sambog, |  | Bldgs. |  | MEO | a) | 500000 | a) | 12/19/17 | e) | - | a) | 500000 | a) | 100.00% | c) | 100.00% | a) | - | Completed as per physical accomplishment. (Fund already transferred at Municipality of New Corella with ChecK No. 2445023 and OR # 8592070, dated March 13, 2018) | 1
|  |  |  | New Corella |  |  |  |  | b) | - | b) | 07/01/18 | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 1
[9 empty] | c) | MEO | c) | 08/15/18 | g) | 08/15/18 | c) | - | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  |  | Rehab. Of Potable Water in Prk. 2,3,3A, |  | Bldgs. |  | MEO | a) | 500000 | a) | 02/19/18 | e) | - | a) | 500000 | a) | 100.00% | c) | 100.00% | a) | - | Completed as per physical accomplishment.Fund already transferred at Municipality of New Corella with ChecK No. 2445320 and OR # 8592073, dated March 13, 2018 | 1
|  |  |  | 3B & 6, Macgum, New Corella |  |  |  |  | b) | - | b) | 08/15/18 | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 1
[9 empty] | c) | MEO | c) | - | g) | 11/19/18 | c) | 500000 | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  |  | Renov./Impv't. of Brgy. Hall, Patrocenio, |  | Bldgs. |  | MEO | a) | 500000 | a) | 12/20/17 | e) | - | a) | 500000 | a) | 100.00% | c) | 100.00% | a) | - | Completed as per physical accomplishment | 1
|  |  |  | New Corella |  |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - | - Fund transferred at Municipality of New Corella | 1
[9 empty] | c) | MEO | c) | - | g) | 11/19/18 | c) | 500000 | [6 empty] | with ChecK No. 2445022 and OR # 8592071, | 1
[9 empty] | d) |  | d) | - | [10 empty] | dated March 13, 2018 | 1
|  |  |  | Impv't. of Covered Court, New Bohol, |  | Bldgs. |  | Barangay | a) | 500000 | a) | 02/13/8 | e) | - | a) | 500000 | a) | 100.00% | c) | 100.00% | a) | - | Completed as per physical accomplishment.Fund already transferred at Municipality of New Corella with ChecK No. 2445321 and OR # 8592075, dated March 13, 2018 | 1
|  |  |  | New Corella |  |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 1
[9 empty] | c) | - | c) | - | g) | 08/15/18 | c) | 500000 | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  |  | Construction of Multi-Purpose Bldg., |  | Bldgs. |  | MEO | a) | 500000 | a) | 02/06/18 | e) | - | a) | 500000 | a) | 100.00% | c) | 100.00% | a) | - | Completed as per physical accomplishment.Fund already transferred at Municipality of New Corella ChecK No. 2445281 with and OR # 8592076, dated March 13, 2018 | 1
|  |  |  | San Jose, New Corella |  |  |  |  | b) | - | b) | 08/05/18 | f) | - | b) | 500000 | b) |  | d) | - | b) | - |  | 1
[9 empty] | c) | MEO | c) | 02/28/19 | g) | 02/28/19 | c) | 500000 | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  |  | Construction of 1 CL School Bldg., |  | Bldg. |  | Barangay | a) | 500000 | a) | 12/28/17 | e) | - | a) | 500000 | a) | 100.00% | c) | 100.00% | a) | - | Completed as per physical accomplishment.Fund already transferred at Municipality of New Corella with ChecK No. 2445183 and OR # 8592077, dated March 13, 2018 | 1
|  |  |  | Mambing, New Corella |  |  |  |  | b) | - | b) | 2018-01-06 | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 1
[9 empty] | c) | MEO | c) | 7/15/2018 | g) | 7/15/2018 | c) | - | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | SAN ISIDRO | [20 empty] | AC
|  |  |  | Rehab. Of Sawata Gymnasiun, San Isidro |  | Bldgs. |  | Contract | a) | 500000 | a) | 11/29/17 | e) | - | a) | 500000 | a) | 100.00% | c) | 100.00% | a) | - | Completed as per physical accomplishment. | 1
[9 empty] | b) | Escurzon | b) | 01/06/18 | f) | 15 CD | b) | 500000 | b) | - | d) | - | b) | - | Financial documents still on process | 1
[9 empty] | c) | FT Construction | c) | 05/07/18 | g) | 07/25/18 | c) | 474,700.57 | [7 empty] | 1
[9 empty] | d) | 35 CD | d) | 07/20/18 | [11 empty] | 1
|  |  |  | Compl. Of Pipeline Level II, Brgy. San Miguel, |  | Water |  | Contract | a) | 500000 | a) | 12/28/17 | e) | - | a) | 500000 | a) | 100.00% | c) | 100.00% | a) | 5 | Completed as per physical accomplishment. | 1
|  |  |  | San Isidro |  |  |  |  | b) | Diosanta | b) | 05/25/18 | f) | 28 CD | b) | 500000 | b) | - | d) | - | b) | 100 | Financial documents still on process | 1
[9 empty] | c) | ZULAR - AZ Const. & Supply | c) | 06/07/18 | g) | 07/25/18 | c) | 478500 | [7 empty] | 1
[9 empty] | d) | 24 CD | d) | 07/05/18 | [11 empty] | 1
|  |  |  | Const. of Covered Court, Datu Balong, |  | Bldgs. |  | Contract | a) | 500000 | a) | 11/29/17 | e) | - | a) | 500000 | a) | 100.00% | c) | 100.00% | a) | 5 | Completed as per physical accomplishment. | 1
|  |  |  | San Isidro |  |  |  |  | b) | Escurzon | b) | 01/06/18 | f) | - | b) | 500000 | b) | - | d) | - | b) | 90 | Financial documents still on process | 1
[9 empty] | c) | FT Construction | c) | 07/10/18 | g) | 08/31/18 | c) | 472019.86 | [7 empty] | 1
[9 empty] | d) | 40 CD | d) | - | [11 empty] | 1
|  |  |  | Const. of Brgy. Stage, Linao, San Isidro |  | Bldgs. |  | Contract | a) | 500000 | a) | 11/29/17 | e) | - | a) | 500000 | a) | 100.00% | c) | 100.00% | a) | 12 | Completed as per physical accomplishment. | 1
[9 empty] | b) | Escurzon | b) | 01/06/18 | f) | 15 CD | b) | 500000 | b) | - | d) | - | b) | 216 | Financial documents still on process | 1
[9 empty] | c) | FT Construction | c) | 05/07/18 | g) | 09/03/18 | c) | 495500 | [7 empty] | 1
[9 empty] | d) | 45 CD | d) | 07/15/18 | [11 empty] | 1
|  |  |  | Const. of Potable Water System, Monte |  | Water |  | Contract | a) | 500000 | a) | 12/28/17 | e) | - | a) | 500000 | a) | 100.00% | c) | 100.00% | a) | 6 | Completed as per physical accomplishment. | 1
|  |  |  | Dujali, San Isidro |  |  |  |  | b) | Escurzon | b) | 01/06/18 | f) | 20 CD | b) | 500000 | b) | - | d) | - | b) | 180 | Financial documents still on process | 1
[9 empty] | c) | FT Construction | c) | 07/30/18 | g) | 09/07/18 | c) | 472977.4 | [7 empty] | 1
[9 empty] | d) | 60 CD | d) | 08/25/18 | [11 empty] | 1
|  |  |  | Const. of Covered Court , Libuton, San Isidro |  | bldgs. |  | Contract | a) | 500000 | a) | 11/29/17 | e) | - | a) | 500000 | a) | 100.00% | c) | 100.00% | a) | 6 | Completed as per physical accomplishment. | 1
[9 empty] | b) | Escurzon | b) | 01/06/18 | f) | - | b) | 500000 | b) | - | d) | - | b) | 180 | Financial documents still on process | 1
[9 empty] | c) | FT Construction | c) | 07/15/18 | g) | 08/22/18 | c) | 476716.56 | [7 empty] | 1
[9 empty] | d) | 45 CD | d) | - | [11 empty] | 1
|  |  |  | Improvement of Barangay Hall Perimeter |  | Fence |  | Contract | a) | 500000 | a) | 11/29/17 | e) | - | a) | 500000 | a) | 100.00% | c) | 100.00% | a) | 6 | Completed as per physical accomplishment. | 1
|  |  |  | Fence, Brgy. Dakudao, San Isidro |  |  |  |  | b) | Escurzon | b) | 01/06/18 | f) | - | b) | 500000 | b) | - | d) | - | b) | 180 | Financial documents still on process | 1
[9 empty] | c) | FT Construction | c) | 07/30/18 | g) | 08/25/18 | c) | 468532.48 | [7 empty] | 1
[9 empty] | d) | 60 CD | d) | 08/25/18 | [11 empty] | 1
1
|  |  |  | Completion of Multi-Purpose Building |  | Bldg. |  | Contract | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | 100.00% | c) | 100.00% | a) | 6 | Completed as per physical accomplishment. | 1
|  |  |  | Kipalili, San isidro |  |  |  |  | b) | Obero | b) | 12/03/18 | f) | - | b) | 500000 | b) | - | d) | - | b) | 180 | Financial documents still on process | 1
[9 empty] | c) | RLHV | c) | 01/05/19 | g) | 08/22/18 | c) | 459201 | [7 empty] | 1
[9 empty] | d) | 30 CD | d) | - | [11 empty] | 1
|  |  | IGACOS | [20 empty] | AC
|  |  |  | Rehab. of Water System, Sion, IGACOS |  | Water |  | Admin | a) | 500000 | a) | 12/01/17 | e) | - | a) | 500000 | a) | 100.00% | c) | 100.00% | a) | - | Completed as per physical accomplishment. | 2
[6 empty] | System |  |  | b) | Diosanta | b) | 08/24/18 | f) | - | b) | 500000 | b) | - | d) | - | b) | - | Financial documents still on process | 2
[9 empty] | c) | PEO | c) | 09/28/18 | g) | 09/28/18 | c) | 425,192.30 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  |  | Impvt. of MP Gym, San Agustin, IGACOS |  | Bldgs. |  | Contract | a) | 500000 | a) | 12/01/17 | d) | - | a) | 500000 | a) | 100% | c) | 100% | a) | - | Completed as per physical accomplishment. | 2
[9 empty] | b) | Porras | b) | 2018-04-26 | e) | - | b) | 500000 | b) | - | d) | - | b) | - | Financial documents still on process | 2
[9 empty] | c) | SILJURE | c) | 2018-06-06 | f) | 06/01/18 | c) | 443364.85 | [7 empty] | 2
[9 empty] | d) | 42 CD | d) | - | [11 empty] | 2
|  |  |  | Conc. of Brgy. Road, Camudmud, IGACOS |  | Road |  | Contract | a) | 500000 | a) | 11/29/17 | d) | - | a) | 500000 | a) | 100% | c) | 100% | a) | 5 | Completed as per physical accomplishment. | 2
[9 empty] | b) | Pacquio | b) | 2018-04-26 | e) | 16 days | b) | 500000 | b) | - | d) | - | b) | 30 | Financial documents still on process | 2
[9 empty] | c) | SILJURE | c) | 2018-06-11 | f) | 2018-06-11 | c) | 467128.2 | [7 empty] | 2
[9 empty] | d) | 30 CD | d) | - | [11 empty] | 2
|  |  |  | Impvt of Evacuation Center, |  | Bldg. |  | Admin | a) | 500000 | a) | 12/01/17 | e) | - | a) | 500000 | a) | 100.00% | c) | 100.00% | a) | 8 | Completed as per physical accomplishment. | 2
|  |  |  | Brgy. Balet, IGACOS |  |  |  |  | b) | Porras | b) | 05/01/19 | f) | - | b) | 500000 | b) | - | d) | - | b) | 160 | Financial documents still on process | 2
[9 empty] | c) | PEO | c) | 06/12/19 | g) | 06/06/19 | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | CARMEN | [20 empty] | AC
2
|  |  |  | Compl. Of Evacuation Ctr. Bldg. Taba, Carmen |  | Bldg. |  | Barangay | a) | 500000 | a) | 12/19/17 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Completed 9/19/2018 as per physical accomplishment. Financial documents still on process | 2
[9 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 2
[9 empty] | c) | - | c) | - | g) | 9/19/2018 | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  |  | Const. of Multi-Purpose Stage @ Prk. 2, |  | Bldg. |  | Barangay | a) | 500000 | a) | 12/19/17 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Completed as per physical accomplishment. Financial documents still on process | 2
|  |  |  | Salvacion, Carmen |  |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 2
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  |  | Const. of Multi-Purpose Bldg., |  | Bldg. |  | Barangay | a) | 500000 | a) | 12/28/17 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Completed 9/19/2018 as per physical accomplishment. Financial documents still on process | 2
|  |  |  | Magsaysay, Carmen |  |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 2
[9 empty] | c) | - | c) | - | g) | 9/19/2018 | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  |  | Compl. Of Covered Court/Stage, |  | Court |  | Barangay | a) | 500000 | a) | 12/28/17 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Completed 9/19/2018 as per physical accomplishment. Financial documents still on process | 2
|  |  |  | New Camiling, Carmen |  |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 2
[9 empty] | c) | - | c) | - | g) | 9/19/2018 | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
4 |  |  |  | Construction of Evaluation Center at Prk. 1, |  | Bldg. |  | Barangay | a) | 500000 | a) | 12/28/17 | e) | - | a) | 500000 | a) | - | c) | 100% | a) | - | Completed | 2
4 |  |  |  | Asuncion, Carmen |  |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 2
4 | [8 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 2
4 | [8 empty] | d) | - | d) | - | [11 empty] | 2
AC
|  |  | PANABO CITY | [20 empty] | AC
2
|  |  |  | Brgy. Covered Court Fencing, Sta. Cruz, |  | Court |  | Barangay | a) | 500000 | a) | 12/28/17 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Completed 6/10/2019 as per physical accomplishment. Financial documents still on process | 2
|  |  |  | Panabo CIty |  |  |  |  | b) | - | b) | 5/15/2019 | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 2
[9 empty] | c) | - | c) | 6/10/2019 | g) | - | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  |  | Const. of Multi-Purpose Bldg., Katualan, |  | Bldg. |  | Barangay | a) | 500000 | a) | 12/19/17 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Completed 10/12/2018 as per physical accomplishment. Financial documents still on process | 2
|  |  |  | Panabo CIty |  |  |  |  | b) | - | b) | 9/20/2018 | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 2
[9 empty] | c) | - | c) | 10/12/2018 | g) | - | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  |  | Const. of Covered Court Bleacher, Katipunan, |  | Bleacher |  | Barangay | a) | 500000 | a) | 12/19/17 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Completed as per physical accomplishment. Financial documents still on process | 2
|  |  |  | Panabo CIty |  |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 2
[9 empty] | c) | - | c) | - | g) | 6/10/2018 | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  |  | Const. of Brgy. Gymnasium, Mabunao, |  | Gym |  | Barangay | a) | 500000 | a) | 12/28/17 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Completed as per physical accomplishment. Financial documents still on process | 2
|  |  |  | Panabo CIty |  |  |  |  | b) | - | b) | 3/11/2019 | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 2
[9 empty] | c) | - | c) | 4/10/2019 | g) | 4/10/2019 | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
2
2
|  |  |  | Completion of Footbridge at Prk. 1, Tibungol, |  | Footbridge |  | Barangay | a) | 500000 | a) | 12/28/17 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Completed as per physical accomplishment. Financial documents still on process | 2
|  |  |  | Panabo CIty |  |  |  |  | b) | - | b) | 12/13/2018 | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 2
[9 empty] | c) | - | c) | 2/11/2019 | g) | 2/11/2019 | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  |  | Const. of Multi-Purpose Bldg., Lower Panaga, |  | Bldg. |  | Barangay | a) | 500000 | a) | 12/07/17 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Completed as per physical accomplishment. Financial documents still on process | 2
|  |  |  | Panabo CIty |  |  |  |  | b) | - | b) | 10/1/2018 | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 2
[9 empty] | c) | - | c) | 11/30/2018 | g) | 11/30/2018 | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  |  | Completion of Bleachers @ Brgy. GYM, |  | Gym |  | Barangay | a) | 500000 | a) | 12/28/17 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Completed as per physical accomplishment. Financial documents still on process | 2
|  |  |  | Sindaton, Panabo City |  |  |  |  | b) | - | b) | 10/1/2018 | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 2
[9 empty] | c) | - | c) | 10/31/2018 | g) | 10/31/2018 | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  |  | Const. of Concrete Pavement, |  | Pavement |  | Barangay | a) | 500000 | a) | 12/07/17 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Completed as per physical accomplishment. Financial documents still on process | 2
|  |  |  | San Vicente, Panabo City |  |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 2
[9 empty] | c) | - | c) | - | g) | 5/15/2019 | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  |  | Const. of Stage @ Prk. 3, Tagpore, |  | Stage |  | Barangay | a) | 500000 | a) | 12/19/17 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Completed as per physical accomplishment. Financial documents still on process | 2
|  |  |  | Panabo City |  |  |  |  | b) | - | b) | 7/18/2018 | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 2
[9 empty] | c) | - | c) | 9/14/2018 | g) | 9/14/2018 | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  |  | Const. of Bleachres @ Brgy. Manay GYM, |  | Gym |  | Barangay | a) | 500000 | a) | 12/19/17 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Completed as per physical accomplishment. Financial documents still on process | 2
|  |  |  | Manay, Panabo City |  |  |  |  | b) | - | b) | 12/6/2018 | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 2
[9 empty] | c) | - | c) | 12/15/2018 | g) | 12/15/2018 | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  |  | Const. of MP Bldg. w/ Electrical installation, |  | Bldg. |  | Barangay | a) | 500000 | a) | 01/31/18 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Completed as per physical accomplishment. Financial documents still on process | 2
|  |  |  | San Roque, Panabo City |  |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 2
[9 empty] | c) | - | c) | - | g) | 06/10/2019 | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
AC
|  |  | STO TOMAS | [20 empty] | AC
|  |  |  | Const. of Violence Against Women and |  | Bldg. |  | Barangay | a) | 500000 | a) | 12/07/17 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Completed as per physical accomplishment. Financial documents still on process | 2
|  |  |  | Children Center, Tulalian |  |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 2
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | Const./Rehab./Comp. of Various Gov't. Bldgs. |  |  | Bldg. | - | Admin | a) | 9,000,000.00 | [12 empty] | Investigation/Inspection of priority projects | 2
|  |  | Struct., Fac. (Provincewide) | [5 empty] | b) | Foronda/Ababon | [13 empty] | 2
[9 empty] | c) | PEO | [13 empty] | 2
[9 empty] | d) | - | [13 empty] | 2
|  |  |  | Repair/Rehab. Of PEO Building |  | Bldg. |  | Admin | a) | 1,800,000.00 | a) | 07/31/18 | e) | - | a) | 1,800,000.00 | a) | 62.23% | c) | 100% | a) | 5 | Completed based on POW. Financial Documents on process | 1
|  |  |  | (Motorpool),Mankilam, Tagum City |  |  |  |  | b) | Chua | b) | 03/04/19 | f) | - | b) | 1,800,000.00 | b) | - | d) | 37.77% | b) | 105 |  | 1
[9 empty] | c) | PEO | c) | 08/10/19 | g) | - | c) | 1481510.07 | [7 empty] | 1
[9 empty] | d) | 160 CD | d) | - | [11 empty] | 1
|  |  |  | Construction of BSP Building Extension |  | Bldg. |  | Admin | a) | 500000 | a) | 08/21/18 | e) | 79 CD | a) | 500000 | a) | 100% | c) | 100% | a) | 6 | Completed | 1
|  |  |  | Mankilam, Tagum City |  |  |  |  | b) | Quirante | b) | 01/16/19 | f) | 15 CD | b) | 500000 | b) | - | d) | - | b) | 180 |  | 1
[9 empty] | c) | PEO | c) | 03/16/19 | g) | 06/21/19 | c) | 434,145.73 | [7 empty] | 1
[9 empty] | d) | 75 CD | d) | 03/31/19 | [11 empty] | 1
|  |  |  | Repair/Rehab. Of PEO Building |  | Bldg. | 96 sq.m | Admin | a) | 1,073,124.00 | a) | 06/11/18 | e) | - | a) | 1,073,124.00 | a) | 100.00% | c) | 100.00% | a) | 14 | Completed as per physical accomplishment. | 1
|  |  |  | (PEO Warehouse),Mankilam, |  |  |  |  | b) | Chua | b) | 12/03/18 | f) | - | b) | 1,073,124.00 | b) | - | d) | - | b) | 420 | Financial documents still on process | 1
|  |  |  | Tagum City |  |  |  |  | c) | PEO | c) | 06/15/19 | g) | 05/15/19 | c) | 1,042,097.32 | [7 empty] | 1
[9 empty] | d) | 189 CD | d) | - | [11 empty] | 1
|  |  |  | Construction of GSP Building Extension |  | Bldg. |  | Admin | a) | 500,000.00 | a) | 07/20/18 | e) | 44 cd | a) | 500,000.00 | a) | 100.00% | c) | 100.00% | a) | 8 | Completed as per physical accomplishment. | 1
|  |  |  | Mankilam, Tagum City |  |  |  |  | b) | Quirante | b) | 01/03/19 | f) | 15 CD | b) | 500,000.00 | b) | - | d) | - | b) | 240 | Financial documents still on process | 1
[9 empty] | c) | PEO | c) | 03/03/19 | g) | 05/03/19 | c) | 447,660.03 | [7 empty] | 1
[9 empty] | d) | 75 CD | d) | 03/17/19 | [11 empty] | 1
4 |  |  | 2.3 | Improvement of Garciaville Day Care |  | Bldg. |  | Admin | a) | 330,000.00 | a) | 11/06/18 | e) | - | a) | 330,000.00 | a) |  | c) | 100% | a) | 3 | Completed based on POW. Financial Documents on process | 1
4 |  | 11 |  | Center, Mankilam, Tagum City |  |  |  |  | b) | - | b) | 09/02/19 | f) | - | b) | 330,000.00 | b) | - | d) |  | b) | 90 |  | 1
4 | [8 empty] | c) | PEO | c) | 10/11/19 | g) | - | c) | - | [7 empty] | 1
4 | [8 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | Rural Electrification (Provincewide) |  |  | Elect. |  | Admin | a) | 5000000 | [12 empty] | See projects listed below | AC
[9 empty] | b) | Foronda/Misa | [13 empty] | AC
[9 empty] | c) | Admin | [13 empty] | AC
[9 empty] | d) | - | [13 empty] | AC
|  |  |  | Inst. Of distribution transformation & |  | Elect. |  | Admin | a) | 500,000.00 | a) | 06/27/18 | e) | - | a) | 500,000.00 | a) | 100.00% | c) | 100.00% | a) | - | Completed as per physical accomplishment. | 1
|  |  |  | Electrical Wirings, 10th Infantry |  |  |  |  | b) | Lu | b) | 12/17/18 | f) | 15 WD | b) | 500,000.00 | b) | - | d) | - | b) | - | Financial documents still on process | 1
|  |  |  | (Agila) Division PA, Tuburan Mawab |  |  |  |  | c) | PEO | c) | 01/15/18 | g) | 01/31/19 | c) | - | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
4 |  | F. | SDH IGCS - CONST. IN PROGRESS - BLGS. CY 2017 | [20 empty] | 2
4 |  |  | 1 | Construction Perimeter Fence Ph.II (Hospital |  | Fence |  | Admin | a) | 1,305,000.00 | a) | 11/10/17 | e) | 392 | a) | 1,305,000.00 | a) | 100% | c) | 100% | a) | 4 | Completed based on POW. Financial Documents on process | 2
4 |  |  |  | Compound) Samal District Hospital, IGCS |  |  |  |  | b) | Porras | b) | 03/12/18 | f) | 45 | b) | 1,305,000.00 | b) | - | d) | 1% | b) | 30 |  | 2
4 | [8 empty] | c) | PEO | c) | 06/19/18 | g) | - | c) | 958,597.98 | [7 empty] | 2
4 | [8 empty] | d) | - | d) | [12 empty] | 2
4 |  | C.5 | LDRRM - Trust Fund | [20 empty] | AC
4 |  | 5 | 1. Construction of Slope Protection and Concrete Pavement along Sta. Fe Mambing Road Section |  |  | Slope |  | Admin | a) | 1,853,000.00 | a) | 11/28/18 | e) |  | a) | 1,853,000.00 | a) | 100% | c) | 100% | a) | 16 | Completed based on POW. Financial Documents on process | 1
4 | [8 empty] | b) | Gone | b) | 12/03/18 | f) | 108 CD | b) | 1,853,000.00 | b) | - | d) |  | b) | 144 |  | 1
4 | [8 empty] | c) | PEO | c) | 02/28/19 | g) | 10/30/2019 | c) | 742252.72 | [7 empty] | 1
4 | [8 empty] | d) | 86 CD | d) | 06/15/2019 | [11 empty] | 1
4 |  | 1 | 3. Rehab. Of Canatan Bridge Slope Protection |  |  | Slope | 395 sq.m. | Contract | a) | 9200000 | a) | 06/20/2018 | e) | - | a) | 9200000 | a) | 100% | c) | 100% | a) | - | Completed | 1
4 |  |  | Brgy. Canatan, Asuncion | [5 empty] | b) | Aclaracion | b) | 02/11/2019 | f) | 35 CD | b) | 9200000 | b) | 100% | d) | 0% | b) | - |  | 1
4 | [8 empty] | c) | J-One Builders | c) | 04/12/2019 | g) | 05/31/2019 | c) | 7222021.59 | [7 empty] | 1
4 | [8 empty] | d) | 60 CD | d) | 05/01/2019 | [11 empty] | 1
4 |  | 5 | 5. Const. of Cabidianan Bridge Slope Protection, Brgy. Cabidianan, New Corella |  |  | Slope |  | Admin | a) | 3590000 | a) | 07/18/18 | e) | - | a) | 3590000 | a) | 100% | c) | 100% | a) | 8 | Completed based on POW. Financial Documents on process | 1
4 | [8 empty] | b) | Gone | b) | 6/17/19 | f) | - | b) | 3590000 | b) |  | d) |  | b) | 80 |  | 1
4 | [8 empty] | c) | PEO | c) | 8/20/19 | g) | - | c) | 1929823.4 | [7 empty] | 1
4 | [8 empty] | d) | 65 CD | d) | - | [11 empty] | 1
|  | D. | SEF(Special Education Fund)-SUPPLEMENTAL BUDGET # 1 CY 2017 | [20 empty] | AC
|  |  | 1. Const./Impv't./Compl. Of School Bldgs., Struc. & Fac. |  |  | Bldgs. |  | Admin | a) | 3,300,000.00 | [12 empty] | See projects listed below | AC
[9 empty] | b) | Foronda | [13 empty] | AC
[9 empty] | c) | PEO | [13 empty] | AC
[9 empty] | d) | - | [13 empty] | AC
4 |  | 8 | 1.1 | Construction of 1 unit School Building |  | Bldg. |  | Admin | a) | 1100000 | a) | 02/19/18 | e) | - | a) | 1100000 | a) | 100 | c) | 100 | a) | 6 | Completed based on POW. Financial Documents on process | 1
4 |  |  |  | Lumabag, Talaingod |  |  |  |  | b) | Dadula | b) | 03/20/19 | f) | 27 CD | b) | 1100000 | b) |  | d) |  | b) | 30 |  | 1
4 | [8 empty] | c) | PEO | c) | 05/19/19 | g) | 06/30/2019 | c) | 595230.5 | [7 empty] | 1
4 | [8 empty] | d) | 60 CD | d) | - | [11 empty] | 1
|  | E. Supplemental Budget No. 5 CY 2015 | [21 empty] | AC
|  |  | Purchased, Const & Impvt of Govt Facilities (8918) | [20 empty] | AC
|  |  | a. Const/Coml/Impvt of Various Govt. Bldgs Structures | [20 empty] | AC
|  |  | & Facilities | [20 empty] | AC
2
|  |  | Impv't. of Brgy. Hall at |  |  | Bldg. |  | Admin | a) | 500000 | a) | 03/31/17 | e) | 182 CD | a) | 500000 | a) | 100% | c) | 100% | a) | 10 | Completed 7/17/2019 as per physical accomplishment. Financial Documents still on process | 2
|  |  | Brgy. Tagpopongan, Babak Dist., IGCS | [5 empty] | b) | Andoy | b) | 09/17/18 | f) | - | b) | 500000 | b) | - | d) | 0% | b) | 55 |  | 2
[9 empty] | c) | PEO | c) | 12/25/18 | g) | 7/14/2019 | c) | 356,352.61 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | Completion of Multi-Purpose Building |  |  | Bldg. |  | Admin | a) | 500000 | a) | 03/08/16 | e) | - | a) | 500000 | a) | 100% | c) | 100% | a) | 8 | Completed 5/31/2019 as per physical accomplishment. Financial documents still on process | 2
|  |  | Brgy. San Jose, Sto. Tomas | [5 empty] | b) | Roque | b) | 02/14/17 | f) | - | b) | 500000 | b) | - | d) | - | b) | 80 |  | 2
[9 empty] | c) | PEO | c) | 04/27/17 | g) | 15/07/2019 | c) | 484,175.83 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | Completion of Covered Court 1 Bay |  |  | Court |  | Admin | a) | 500000 | a) | 03/07/16 | e) | - | a) | 500000 | a) | 100.00% | c) | 100% | a) | 8 | Completed 7/5/2019 as per physical accomplishment. Financial documents still on process | 2
|  |  | Brgy. Lunga-og, Sto. Tomas | [5 empty] | b) | Roque | b) | 02/14/17 | f) | 54 CD | b) | 500000 | b) | - | d) | - | b) | 80 |  | 2
[9 empty] | c) | PEO | c) | 06/20/17 | g) | - | c) | 473,542.40 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  | D. | LDRRM - Trust Fund 2018 | [20 empty] | AC
|  |  |  | Const. of Single Barrel 4.0m x 4.0m RCDG, Mangalcal, Carmen |  | RCDG |  | Admin | a) | 1,822,000.00 | a) | CY 2013 | e) | - | a) | 1,822,000.00 | a) | 100.00% | c) | 100.00% | a) | 12 | Completed as per physical accomplishment. | 2
|  |  | 1 | [5 empty] | b) | Foronda | b) | 11/05/18 | f) | 92 CD | b) | 1,822,000.00 | b) | - | d) | - | b) | 72 | Financial documents still on process | 2
[9 empty] | c) | PEO | c) | 2019-01-03 | g) | 04/06/19 | c) | 1,822,000.00 | [7 empty] | 2
[9 empty] | d) | 65 CD | d) | 04/06/19 | [11 empty] | 2
2
|  |  |  | Rehabilitation of Protection Dike Along Poblacion-Prk. 8, Dujali, Brgy. Tanglaw, B.E. Dujali |  | Dike |  | Admin | a) | 1,180,000.00 | a) | CY 2013 | e) | - | a) | 1,180,000.00 | a) | 100.00% | c) | 100.00% | a) | 5 | Completed as per physical accomplishment. | 2
|  |  | 2 | [5 empty] | b) | Toquero | b) | 02/15/19 | f) | - | b) | 1,180,000.00 | b) | - | d) | - | b) | 50 | Financial documents still on process | 2
[9 empty] | c) | PEO | c) | 04/02/19 | g) | - | c) | 74,338.28 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  |  | Rehab. Of New Camiling-alejal-Lower Magsaysay Provincial Road |  | RCDG |  | Admin | a) | 1,428,917.00 | a) | 08/02/18 | e) | - | a) | 1,428,917.00 | a) | 100.00% | c) | 100.00% | a) | 5 | Completed as per physical accomplishment. | 2
|  |  | 3 | [5 empty] | b) | Toquero | b) | 12/01/18 | f) | - | b) | 1,428,917.00 | b) | - | d) | - | b) | 50 | Financial documents still on process | 2
[9 empty] | c) | PEO | c) | 01/01/19 | g) | - | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
AC
|  |  | 20% Development Fund 2018 | [20 empty] | AC
[6 empty] | Road Maintenance | KM | [16 empty] | AC
| Road ID |  | Repair & Maint. Of Various Prov'l. Roads and Bridges CY 2018 |  |  |  | 525.3 | Admin | a) | 27893753 | a) | 01/01/18 | e) | - | a) | 27893753 | a) | 100.00% | c) | 100% | a) | 32 | Completed as per physical accomplishment. | AC
[8 empty] | /CBRMC | b) | Matuguinas | b) | 01/01/18 | f) | - | b) | 27893753 | b) | - | d) | - | b) | 2044 | Financial documents still on process | AC
| 11DAN | [7 empty] | c) | PEO//CBRMC | c) | 2018-12-31 | g) | 2018-12-31 | c) | 15,163,482.97 | [6 empty] | See list of Provincial Roads | AC
[9 empty] | d) | - | d) | - | [11 empty] | AC
| 11 |  | Cebulano-Mangalcal Road |  |  | Road | 4.17 | Admin | a) | 239434.4 | a) | 01/01/18 | e) | - | a) | 239434.4 | a) | 100.00% | c) | 100% | a) | 10 | Completed as per physical accomplishment. | 2
| DAN | [7 empty] | b) | Gamad/Maligro | b) | 01/08/18 | f) | - | b) | 239434.4 | b) | - | d) | - | b) | 30 | Financial documents still on process | 2
| 073 | [7 empty] | c) | PEO | c) | 2018-12-31 | g) | 2018-12-31 | c) | 236,699.57 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Cebulano-Mangalcal Road |  |  | Road | 4.17 | CBRMC | a) | 178024.03 | a) | 01/01/18 | e) | - | a) | 178024.03 | a) | 100.00% | c) | 100% | a) | 2 | Completed as per physical accomplishment. | 2
| DAN | [7 empty] | b) | Gamad/Maligro | b) | 2018-05-03 | f) | - | b) | 178024.03 | b) | - | d) | - | b) | 4 | Financial documents still on process | 2
| 073 | [7 empty] | c) | Brgy. Mangalcal Women's Homebased Workers Association | c) | 2019-02-03 | g) | 2019-02-03 | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Tubod-Basa-Mangalcal Road |  |  | Road | 3.93 | Admin | a) | 217304.13 | a) | 01/01/18 | e) | - | a) | 217304.13 | a) | 100.00% | c) | 100% | a) | 1 | Completed as per physical accomplishment. | 2
| DAN | [7 empty] | b) | Gamad/Maligro | b) | 01/08/18 | f) | - | b) | 217304.13 | b) | - | d) | - | b) | 3 | Financial documents still on process | 2
| 074 | [7 empty] | c) | PEO | c) | 2018-12-31 | g) | 2018-12-31 | c) | 212,336.25 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Basa-Tubod Road |  |  | Road | 1.56 | Admin | a) | 153509.11 | a) | 01/01/18 | e) | - | a) | 153509.11 | a) | 100.00% | c) | 100% | a) | 12 | Completed as per physical accomplishment. | 2
| DAN | [7 empty] | b) | Gamad/Maligro | b) | 01/04/18 | f) | - | b) | 153509.11 | b) | - | d) | - | b) | 36 | Financial documents still on process | 2
| 076 | [7 empty] | c) | PEO | c) | 2018-12-31 | g) | 2018-12-31 | c) | 153,509.11 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Tubod-Pilar Road |  |  | Road | 1.55 | Admin | a) | 140507.18 | a) | 01/01/18 | e) | - | a) | 140507.18 | a) | 100.00% | c) | 100% | a) | 12 | Completed as per physical accomplishment. | 2
| DAN | [7 empty] | b) | Gamad/Maligro | b) | 02/12/18 | f) | - | b) | 140507.18 | b) | - | d) | - | b) | 36 | Financial documents still on process | 2
| 077 | [7 empty] | c) | PEO | c) | 2018-12-31 | g) | 2018-12-31 | c) | 140,507.18 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Upper Mangalcal-Lower Mangalcal |  |  | Road | 2.43 | Admin | a) | 149291.32 | a) | 01/01/18 | e) | - | a) | 149291.32 | a) | 100.00% | c) | 100% | a) | 10 | Completed as per physical accomplishment. | 2
| DAN |  | Road | [5 empty] | b) | Gamad/Maligro | b) | 02/12/18 | f) | - | b) | 149291.32 | b) | - | d) | - | b) | 30 | Financial documents still on process | 2
| 078 | [7 empty] | c) | PEO | c) | 2018-12-31 | g) | 2018-12-31 | c) | 143,316.91 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Upper Mangalcal-Lower Mangalcal |  |  | Road | 2.43 | CBRMC | a) | 89828.64 | a) | 01/01/18 | e) | - | a) | 89828.64 | a) | 100.00% | c) | 100% | a) | 2 | Completed as per physical accomplishment. | 2
| DAN |  | Road | [5 empty] | b) | Gamad/Maligro | b) | 2018-05-03 | f) | - | b) | 89828.64 | b) | - | d) | - | b) | 4 | Financial documents still on process | 2
| 078 | [7 empty] | c) | Brgy. Mangalcal Women's Homebased Workers Association | c) | 2019-02-03 | g) | 2019-02-03 | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Cebulano-Loceta Road |  |  | Road | 1.87 | Admin | a) | 166206.3 | a) | 01/01/18 | e) | - | a) | 166206.3 | a) | 100.00% | c) | 100% | a) | 10 | Completed as per physical accomplishment. | 2
| DAN | [7 empty] | b) | Gamad/Maligro | b) | 01/04/18 | f) | - | b) | 166206.3 | b) | - | d) | - | b) | 30 | Financial documents still on process | 2
| 079 | [7 empty] | c) | PEO | c) | 2018-12-31 | g) | 2018-12-31 | c) | 165,088.85 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Loceta-Lower Mangalcal Road |  |  | Road | 2.07 | Admin | a) | 121918.96 | a) | 01/01/18 | e) | - | a) | 121918.96 | a) | 100.00% | c) | 100% | a) | 12 | Completed as per physical accomplishment. | 2
| DAN | [7 empty] | b) | Gamad/Maligro | b) | 01/04/18 | f) | - | b) | 121918.96 | b) | - | d) | - | b) | 36 | Financial documents still on process | 2
| 080 | [7 empty] | c) | PEO | c) | 2018-12-31 | g) | 2018-12-31 | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Lower Asuncion-Upper Asuncion Road |  |  | Road | 1.02 | Admin | a) | 90657.98 | a) | 01/01/18 | e) | - | a) | 90657.98 | a) | 100.00% | c) | 100% | a) | 12 | Completed as per physical accomplishment. | 2
| DAN | [7 empty] | b) | Gamad/Maligro | b) | 01/04/18 | f) | - | b) | 90657.98 | b) | - | d) | - | b) | 36 | Financial documents still on process | 2
| 081 | [7 empty] | c) | PEO | c) | 2018-12-31 | g) | 2018-12-31 | c) | 90,657.98 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Jct.Highway-Carmen-Mangalcal-Tubod |  |  | Road | 11.34 | Admin | a) | 888986.6 | a) | 01/01/18 | e) | - | a) | 888986.6 | a) | 100.00% | c) | 100% | a) | 8 | Completed as per physical accomplishment. | 2
| DAN |  | Road | [5 empty] | b) | Gamad/Maligro | b) | 01/04/18 | f) | - | b) | 888986.6 | b) | - | d) | - | b) | 40 | Financial documents still on process | 2
| 082 | [7 empty] | c) | PEO | c) | 2018-12-31 | g) | 2018-12-31 | c) | 698,903.80 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Jct.Highway-Sto.Niño-La Paz-San |  |  | Road | 6.08 | Admin | a) | 458781.46 | a) | 01/01/18 | e) | - | a) | 458781.46 | a) | 100.00% | c) | 100% | a) | 8 | Completed as per physical accomplishment. | 2
| DAN |  | Vicente Road | [5 empty] | b) | Gamad/Maligro | b) | 01/03/18 | f) | - | b) | 458781.46 | b) | - | d) | - | b) | 40 | Financial documents still on process | 2
| 083 | [7 empty] | c) | PEO | c) | 2018-12-31 | g) | 2018-12-31 | c) | 458,781.46 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Jct.Highway-Sto.Niño-Kabankalan- |  |  | Road | 2.13 | Admin | a) | 127936.58 | a) | 01/01/18 | e) | - | a) | 127936.58 | a) | 100.00% | c) | 100% | a) | 10 | Completed as per physical accomplishment. | 2
| DAN |  | La Paz Road | [5 empty] | b) | Gamad/Maligro | b) | 01/08/18 | f) | - | b) | 127936.58 | b) | - | d) | - | b) | 50 | Financial documents still on process | 2
| 084 | [7 empty] | c) | PEO | c) | 2018-12-31 | g) | 2018-12-31 | c) | 15,535.28 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Jct.Highway-Sto.Niño-Kabankalan- |  |  | Road | 2.13 | CBRMC | a) | 81662.4 | a) | 01/01/18 | e) | - | a) | 81662.4 | a) | 100.00% | c) | 100% | a) | 1 | Completed as per physical accomplishment. | 2
| DAN |  | La Paz Road | [5 empty] | b) | Gamad/Maligro | b) | 01/08/18 | f) | - | b) | 81662.4 | b) | - | d) | - | b) | 1 | Financial documents still on process | 2
| 084 | [7 empty] | c) | Taba Coconut Farmers Association | c) | 2018-12-31 | g) | 2018-12-31 | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Ising-Sto.Niño Road |  |  | Road | 2.07 | Admin | a) | 107208.18 | a) | 01/01/18 | e) | - | a) | 107208.18 | a) | 100.00% | c) | 100% | a) | 12 | Completed as per physical accomplishment. | 2
| DAN | [7 empty] | b) | Gamad/Maligro | b) | 01/03/18 | f) | - | b) | 107208.18 | b) | - | d) | - | b) | 36 | Financial documents still on process | 2
| 085 | [7 empty] | c) | PEO | c) | 2018-12-31 | g) | 2018-12-31 | c) | 107,151.22 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Ising-Sto.Niño Road |  |  | Road | 2.07 | CBRMC | a) | 101261.38 | a) | 01/01/18 | e) | - | a) | 101261.38 | a) | 100.00% | c) | 100% | a) | 1 | Completed as per physical accomplishment. | 2
| DAN | [7 empty] | b) | Gamad/Maligro | b) | 06/22/18 | f) | - | b) | 101261.38 | b) | - | d) | - | b) | 1 | Financial documents still on process | 2
| 085 | [7 empty] | c) | Taba Coconut Farmers Association | c) | 04/21/19 | g) | 12/31/18 | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Ising-Sadpodon-Taba-Diladila Road |  |  | Road | 5.68 | Admin | a) | 263421.11 | a) | 01/01/18 | e) | - | a) | 263421.11 | a) | 100.00% | c) | 100% | a) | 8 | Completed as per physical accomplishment. | 2
| DAN | [7 empty] | b) | Gamad/Maligro | b) | 01/03/18 | f) | - | b) | 263421.11 | b) | - | d) | - | b) | 24 | Financial documents still on process | 2
| 086 | [7 empty] | c) | PEO | c) | 2018-12-31 | g) | 2018-12-31 | c) | 261,318.46 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Ising-Sadpodon-Taba-Diladila Road |  |  | Road | 5.68 | CBRMC | a) | 175301.95 | a) | 01/01/18 | e) | - | a) | 175301.95 | a) | 100.00% | c) | 100% | a) | 2 | Completed as per physical accomplishment. | 2
| DAN | [7 empty] | b) | Gamad/Maligro | b) | 04/26/18 | f) | - | b) | 175301.95 | b) | - | d) | - | b) | 6 | Financial documents still on process | 2
| 086 | [7 empty] | c) | Taba Coconut Farmers Association | c) | 2019-01-26 | g) | 12/31/18 | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Tuganay-Taba Road |  |  | Road | 4.27 | CBRMC | a) | 140549.33 | a) | 01/01/18 | e) | - | a) | 140549.33 | a) | 100.00% | c) | 100% | a) | 2 | Completed as per physical accomplishment. | 2
| DAN | [7 empty] | b) | Gamad/Maligro | b) | 04/26/18 | f) | - | b) | 140549.33 | b) | - | d) | - | b) | 4 | Financial documents still on process | 2
| 087 | [7 empty] | c) | Taba Coconut Farmers Association | c) | 2019-01-26 | g) | 12/31/18 | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Jct. Highway-Tuganay-Taba Road |  |  | Road | 4.4 | Admin | a) | 137256.7 | a) | 01/01/18 | e) | - | a) | 137256.7 | a) | 100.00% | c) | 100% | a) | 8 | Completed as per physical accomplishment. | 2
| DAN | [7 empty] | b) | Gamad/Maligro | b) | 02/12/18 | f) | - | b) | 137256.7 | b) | - | d) | - | b) | 16 | Financial documents still on process | 2
| 088 | [7 empty] | c) | PEO | c) | 2018-12-31 | g) | 2018-12-31 | c) | 128,871.12 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Jct.Highway-Ising-Magsaysay Road |  |  | Road | 10.84 | Admin | a) | 736262 | a) | 01/01/18 | e) | - | a) | 736262 | a) | 100.00% | c) | 100% | a) | 8 | Completed as per physical accomplishment. | 2
| DAN | [7 empty] | b) | Gamad/Maligro | b) | 02/12/18 | f) | - | b) | 736262 | b) | - | d) | - | b) | 24 | Financial documents still on process | 2
| 089 | [7 empty] | c) | PEO | c) | 2018-12-31 | g) | 2018-12-31 | c) | 735,525.71 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Jct.Highway-Ising-Magsaysay Road |  |  | Road | 10.84 | CBRMC | a) | 222121.73 | a) | 01/01/18 | e) | - | a) | 222121.73 | a) | 100.00% | c) | 100% | a) | - | Completed as per physical accomplishment. | 2
| DAN | [7 empty] | b) | Gamad/Maligro | b) | 02/12/18 | f) | - | b) | 222121.73 | b) | - | d) | - | b) | - | Financial documents still on process | 2
| 089 | [7 empty] | c) | School on the Air Integrated Farmers Association | c) | 2018-12-31 | g) | 2018-12-31 | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Maligaya-New Camiling Road |  |  | Road | 2.13 | Admin | a) | 208418.14 | a) | 01/01/18 | e) | - | a) | 208418.14 | a) | 100.00% | c) | 100% | a) | 10 | Completed as per physical accomplishment. | 2
| DAN | [7 empty] | b) | Gamad/Maligro | b) | 02/12/18 | f) | - | b) | 208418.14 | b) | - | d) | - | b) | 12 | Financial documents still on process | 2
| 090 | [7 empty] | c) | PEO | c) | 2018-12-31 | g) | 2018-12-31 | c) | 194,652.04 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | New Camiling-Alejal-Lower Magsaysay |  |  | Road | 6.73 | Admin | a) | 393838.9 | a) | 01/01/18 | e) | - | a) | 393838.9 | a) | 100.00% | c) | 100% | a) | 12 | Completed as per physical accomplishment. | 2
| DAN |  | Road | [5 empty] | b) | Gamad/Maligro | b) | 02/12/18 | f) | - | b) | 393838.9 | b) | - | d) | - | b) | 48 | Financial documents still on process | 2
| 091 | [7 empty] | c) | PEO | c) | 2018-12-31 | g) | 2018-12-31 | c) | 236,036.98 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | New Camiling-Alejal-Lower Magsaysay |  |  | Road | 6.73 | CBRMC | a) | 209055.74 | a) | 01/01/18 | e) | - | a) | 209055.74 | a) | 100.00% | c) | 100% | a) | 2 | Completed as per physical accomplishment. | 2
| DAN |  | Road | [5 empty] | b) | Gamad/Maligro | b) | 05/04/18 | f) | - | b) | 209055.74 | b) | - | d) | - | b) | 2 | Financial documents still on process | 2
| 091 | [7 empty] | c) | School on the Air Integrated Farmers Association | c) | 02/04/19 | g) | 12/31/18 | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Anahaw-Maligaya Road |  |  | Road | 4.8 | Admin | a) | 328333.3 | a) | 01/01/18 | e) | - | a) | 328333.3 | a) | 100.00% | c) | 100% | a) |  | Completed as per physical accomplishment. | 2
| DAN | [7 empty] | b) | Gamad/Maligro | b) | 01/08/18 | f) | - | b) | 328333.3 | b) | - | d) | - | b) |  | Financial documents still on process | 2
| 093 | [7 empty] | c) | PEO | c) | 2018-12-31 | g) | 2018-12-31 | c) | 154,062.27 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Jct.Highway-Tuganay-Anibongan Road |  |  | Road | 3.66 | Admin | a) | 192897.9 | a) | 01/01/18 | e) | - | a) | 192897.9 | a) | 100.00% | c) | 100% | a) | 10 | Completed as per physical accomplishment. | 2
| DAN | [7 empty] | b) | Gamad/Maligro | b) | 01/04/18 | f) | - | b) | 192897.9 | b) | - | d) | - | b) | 20 | Financial documents still on process | 2
| 094 | [7 empty] | c) | PEO | c) | 2018-12-31 | g) | 2018-12-31 | c) | 176,119.23 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Jct.Highway-Tuganay-Anibongan Road |  |  | Road | 3.66 | CBRMC | a) | 97994.88 | a) | 01/01/18 | e) | - | a) | 97994.88 | a) | 100.00% | c) | 100% | a) |  | Completed as per physical accomplishment. | 2
| DAN | [7 empty] | b) | Gamad/Maligro | b) | 05/04/18 | f) | - | b) | 97994.88 | b) | - | d) | - | b) |  | Financial documents still on process | 2
| 094 | [7 empty] | c) | EZRA | c) | 02/04/19 | g) | 12/31/18 | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Anibongan-Guadalupe Road |  |  | Road | 2.48 | Admin | a) | 144312.93 | a) | 01/01/18 | e) | - | a) | 144312.93 | a) | 100.00% | c) | 100% | a) |  | Completed as per physical accomplishment. | 2
| DAN | [7 empty] | b) | Gamad/Maligro | b) | 01/04/18 | f) | - | b) | 144312.93 | b) | - | d) | - | b) |  | Financial documents still on process | 2
| 095 | [7 empty] | c) | PEO | c) | 2018-12-31 | g) | 2018-12-31 | c) | 113,396.19 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Anibongan-Guadalupe Road |  |  | Road | 2.48 | CBRMC | a) | 78395.9 | a) | 01/01/18 | e) | - | a) | 78395.9 | a) | 100.00% | c) | 100% | a) | - | Completed as per physical accomplishment. | 2
| DAN | [7 empty] | b) | Gamad/Maligro | b) | 05/04/18 | f) | - | b) | 78395.9 | b) | - | d) | - | b) | - | Financial documents still on process | 2
| 095 | [7 empty] | c) | - | c) | 02/04/19 | g) | 12/31/18 | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Tuganay-Anibongan-San Isidro Road |  |  | Road | 7.22 | Admin | a) | 219455.18 | a) | 01/01/18 | e) | - | a) | 219455.18 | a) | 100.00% | c) | 100% | a) | 12 | Completed as per physical accomplishment. | 2
| DAN | [7 empty] | b) | Gamad/Maligro | b) | 01/04/18 | f) | - | b) | 219455.18 | b) | - | d) | - | b) | 24 | Financial documents still on process | 2
| 096 | [7 empty] | c) | PEO | c) | 2018-12-31 | g) | 2018-12-31 | c) | 209,407.75 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Jct.Anibongan P2,7,5-San Isidro Road |  |  | Road | 3.14 | Admin | a) | 110524.22 | a) | 01/01/18 | e) | - | a) | 110524.22 | a) | 100.00% | c) | 100% | a) | 12 | Completed as per physical accomplishment. | 2
| DAN | [7 empty] | b) | Gamad/Maligro | b) | 01/04/18 | f) | - | b) | 110524.22 | b) | - | d) | - | b) | 24 | Financial documents still on process | 2
| 097 | [7 empty] | c) | PEO | c) | 2018-12-31 | g) | 2018-12-31 | c) | 80,736.78 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Anibongan-Salvacion-Cabay-angan |  |  | Road | 6.93 | Admin | a) | 517149.14 | a) | 01/01/18 | e) | - | a) | 517149.14 | a) | 100.00% | c) | 100% | a) | 10 | Completed as per physical accomplishment. | 2
| DAN |  | Road | [5 empty] | b) | Gamad/Maligro | b) | 02/12/18 | f) | - | b) | 517149.14 | b) | - | d) | - | b) | 20 | Financial documents still on process | 2
| 098 | [7 empty] | c) | PEO | c) | 2018-12-31 | g) | 2018-12-31 | c) | 358,470.30 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Mabaus-Cabay-angan Road |  |  | Road | 3.2 | Admin | a) | 284417.14 | a) | 01/01/18 | e) | - | a) | 284417.14 | a) | 100.00% | c) | 100% | a) |  | Completed as per physical accomplishment. | 2
| DAN | [7 empty] | b) | Gamad/Maligro | b) | 01/08/18 | f) | - | b) | 284417.14 | b) | - | d) | - | b) |  | Financial documents still on process | 2
| 099 | [7 empty] | c) | PEO | c) | 2018-12-31 | g) | 2018-12-31 | c) | 277,092.31 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Mabaus-Salvacion Road |  |  | Road | 1.38 | Admin | a) | 105132.79 | a) | 01/01/18 | e) | - | a) | 105132.79 | a) | 100.00% | c) | 100% | a) |  | Completed as per physical accomplishment. | 2
| DAN | [7 empty] | b) | Gamad/Maligro | b) | 02/12/18 | f) | - | b) | 105132.79 | b) | - | d) | - | b) |  | Financial documents still on process | 2
| 100 | [7 empty] | c) | PEO | c) | 2018-12-31 | g) | 2018-12-31 | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Jct.Highway-Guadalupe-Bdry.Tagum |  |  | Road | 7.9 | Admin | a) | 574863.11 | a) | 01/01/18 | e) | - | a) | 574863.11 | a) | 100.00% | c) | 100% | a) | 10 | Completed as per physical accomplishment. | 2
| DAN |  | Road | [5 empty] | b) | Gamad/Maligro | b) | 02/16/18 | f) | - | b) | 574863.11 | b) | - | d) | - | b) | 70 | Financial documents still on process | 2
| 101 | [7 empty] | c) | PEO | c) | 2018-12-31 | g) | 2018-12-31 | c) | 301,160.92 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Dalisay-Mabuhay Road |  |  | Road | 3.25 | Admin | a) | 319810.65 | a) | 01/01/18 | e) | - | a) | 319810.65 | a) | 100.00% | c) | 100% | a) | 8 | Completed as per physical accomplishment. | 2
| DAN | [7 empty] | b) | Gamad/Maligro | b) | 02/12/18 | f) | - | b) | 319810.65 | b) | - | d) | - | b) | 24 | Financial documents still on process | 2
| 102 | [7 empty] | c) | PEO | c) | 2018-12-31 | g) | 2018-12-31 | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Sitio Malaga-Tibulao Road |  |  | Road | 3.22 | Admin | a) | 255531.08 | a) | 01/01/18 | e) | - | a) | 255531.08 | a) | 100.00% | c) | 100% | a) |  | Completed as per physical accomplishment. | 2
| DAN | [7 empty] | b) | Gamad/Maligro | b) | 02/16/18 | f) | - | b) | 255531.08 | b) | - | d) | - | b) |  | Financial documents still on process | 2
| 103 | [7 empty] | c) | PEO | c) | 2018-12-31 | g) | 2018-12-31 | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Dujali-Tanglaw Road |  |  | Road | 3.6 | Admin | a) | 280441.08 | a) | 01/01/18 | e) | - | a) | 280441.08 | a) | 100.00% | c) | 100% | a) |  | Completed as per physical accomplishment. | 2
| DAN | [7 empty] | b) | Gamad/Maligro | b) | 01/08/18 | f) | - | b) | 280441.08 | b) | - | d) | - | b) |  | Financial documents still on process | 2
| 104 | [7 empty] | c) | PEO | c) | 2018-12-31 | g) | 2018-12-31 | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Poblacion Dujali-Prk.8, Dujali Road |  |  | Road | 8.2 | Admin | a) | 577861.87 | a) | 01/01/18 | e) | - | a) | 577861.87 | a) | 100.00% | c) | 100% | a) | 22 | Completed as per physical accomplishment. | 2
| DAN | [7 empty] | b) | Gamad/Maligro | b) | 01/04/18 | f) | - | b) | 577861.87 | b) | - | d) | - | b) | 66 | Financial documents still on process | 2
| 105 | [7 empty] | c) | PEO | c) | 2018-12-31 | g) | 2018-12-31 | c) | 350,004.70 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Poblacion Dujali-Prk.8, Dujali Road |  |  | Road | 8.2 | CBRMC | a) | 226152.24 | a) | 01/01/18 | e) | - | a) | 226152.24 | a) | 100.00% | c) | 100% | a) | - | Completed as per physical accomplishment. | 2
| DAN | [7 empty] | b) | Gamad/Maligro | b) | 01/08/18 | f) | - | b) | 226152.24 | b) | - | d) | - | b) | - | Financial documents still on process | 2
| 105 | [7 empty] | c) | Duajli Pob. Farmers Irrigators | c) | 2018-12-31 | g) | 12/31/18 | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Dujali-San Isidro Road |  |  | Road | 3 | Admin | a) | 349588.79 | a) | 01/01/18 | e) | - | a) | 349588.79 | a) | 100.00% | c) | 100% | a) | 5 | Completed as per physical accomplishment. | 2
| DAN | [7 empty] | b) | Gamad/Maligro | b) | 01/08/18 | f) | - | b) | 349588.79 | b) | - | d) | - | b) | 20 | Financial documents still on process | 2
| 107 | [7 empty] | c) | PEO | c) | 2018-12-31 | g) | 2018-12-31 | c) | 278,882.34 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Dujali-San Isidro Road |  |  | Road | 3 | CBRMC | a) | 71862.91 | a) | 01/01/18 | e) | - | a) | 71862.91 | a) | 100.00% | c) | 100% | a) | - | Completed as per physical accomplishment. | 2
| DAN | [7 empty] | b) | Gamad/Maligro | b) | 10/26/18 | f) | - | b) | 71862.91 | b) | - | d) | - | b) | - | Financial documents still on process | 2
| 107 | [7 empty] | c) |  | c) | 12/31/18 | g) | 12/31/18 | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | New Casay-Bugtong Talisay Road |  |  | Road | 2.18 | Admin | a) | 222469.81 | a) | 01/01/18 | e) | - | a) | 222469.81 | a) | 100.00% | c) | 100% | a) | 8 | Completed as per physical accomplishment. | 2
| DAN | [7 empty] | b) | Gamad/Maligro | b) | 01/08/18 | f) | - | b) | 222469.81 | b) | - | d) | - | b) | 24 | Financial documents still on process | 2
| 108 | [7 empty] | c) | PEO | c) | 2018-12-31 | g) | 2018-12-31 | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Prk.5 RJS-Prk.6 New Casay Road |  |  | Road | 2.73 | Admin | a) | 107717.9 | a) | 01/01/18 | e) | - | a) | 107717.9 | a) | 100.00% | c) | 100% | a) | 12 | Completed as per physical accomplishment. | 2
| DAN | [7 empty] | b) | Gamad/Maligro | b) | 02/12/18 | f) | - | b) | 107717.9 | b) | - | d) | - | b) | 36 | Financial documents still on process | 2
| 109 | [7 empty] | c) | PEO | c) | 2018-12-31 | g) | 2018-12-31 | c) | 106,464.30 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Prk.5 RJS-Prk.6 New Casay Road |  |  | Road | 2.73 | CBRMC | a) | 117593.86 | a) | 01/01/18 | e) | - | a) | 117593.86 | a) | 100.00% | c) | 100% | a) | 2 | Completed as per physical accomplishment. | 2
| DAN | [7 empty] | b) | Gamad/Maligro | b) | 05/07/18 | f) | - | b) | 117593.86 | b) | - | d) | - | b) | 2 | Financial documents still on process | 2
| 109 | [7 empty] | c) | MANCIIA | c) | 02/07/19 | g) | 12/31/18 | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Cabay-angan-Esperanza Road |  |  | Road | 5.37 | Admin | a) | 537948.48 | a) | 01/01/18 | e) | - | a) | 537948.48 | a) | 100.00% | c) | 100% | a) | 12 | Completed as per physical accomplishment. | 2
| DAN | [7 empty] | b) | Gamad/Maligro | b) | 01/04/18 | f) | - | b) | 537948.48 | b) | - | d) | - | b) | 36 | Financial documents still on process | 2
| 110 | [7 empty] | c) | PEO | c) | 2018-12-31 | g) | 2018-12-31 | c) | 479,947.45 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Prk.6 Cabay-angan-Esti Road |  |  | Road | 1.08 | Admin | a) | 90911.93 | a) | 01/01/18 | e) | - | a) | 90911.93 | a) | 100.00% | c) | 100% | a) | 12 | Completed as per physical accomplishment. | 2
| DAN | [7 empty] | b) | Gamad/Maligro | b) | 01/03/18 | f) | - | b) | 90911.93 | b) | - | d) | - | b) | 36 | Financial documents still on process | 2
| 111 | [7 empty] | c) | PEO | c) | 2018-12-31 | g) | 2018-12-31 | c) | 90,911.93 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Prk.5-Prk.1 Pawas, Dujali Road |  |  | Road | 2.18 | Admin | a) | 56566.39 | a) | 01/01/18 | e) | - | a) | 56566.39 | a) | 100.00% | c) | 100% | a) | 12 | Completed as per physical accomplishment. | 2
| DAN | [7 empty] | b) | Gamad/Maligro | b) | 01/03/18 | f) | - | b) | 56566.39 | b) | - | d) | - | b) | 36 | Financial documents still on process | 2
| 112 | [7 empty] | c) | PEO | c) | 2018-12-31 | g) | 2018-12-31 | c) | 54,346.01 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Prk.5-Prk.1 Pawas, Dujali Road |  |  | Road | 2.18 | CBRMC | a) | 137192.83 | a) | 01/01/18 | e) | - | a) | 137192.83 | a) | 100.00% | c) | 100% | a) | 5 | Completed as per physical accomplishment. | 2
| DAN | [7 empty] | b) | Gamad/Maligro | b) | 05/02/18 | f) | - | b) | 137192.83 | b) | - | d) | - | b) | 30 | Financial documents still on process | 2
| 112 | [7 empty] | c) | MANCIIA | c) | 02/02/19 | g) | 12/31/18 | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Dujali-Balisong-Magupising Road |  |  | Road | 5.52 | Admin | a) | 400494.66 | a) | 01/01/18 | e) | - | a) | 400494.66 | a) | 100.00% | c) | 100% | a) | 8 | Completed as per physical accomplishment. | 2
| DAN | [7 empty] | b) | Gamad/Maligro | b) | 01/03/18 | f) | - | b) | 400494.66 | b) | - | d) | - | b) | 24 | Financial documents still on process | 2
| 113 | [7 empty] | c) | PEO | c) | 2018-12-31 | g) | 2018-12-31 | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Prk.Narafil-Brgy. Site Magupising Road |  |  | Road | 2.08 | Admin | a) | 96860.19 | a) | 01/01/18 | e) | - | a) | 96860.19 | a) | 100.00% | c) | 100% | a) | 8 | Completed as per physical accomplishment. | 2
| DAN | [7 empty] | b) | Gamad/Maligro | b) | 01/03/18 | f) | - | b) | 96860.19 | b) | - | d) | - | b) | 8 | Financial documents still on process | 2
| 114 | [7 empty] | c) | PEO | c) | 12/31/18 | g) | 12/31/18 | c) | 33,963.32 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Dujali-Sitio Pawas Road |  |  | Road | 1.25 | Admin | a) | 230,810.21 | a) | 01/01/18 | e) | - | a) | 230,810.21 | a) | 100.00% | c) | 100% | a) |  | Completed as per physical accomplishment. | 2
| DAN | [7 empty] | b) | Gamad/Maligro | b) | 01/03/18 | f) | - | b) | 230,810.21 | b) | - | d) | - | b) |  | Financial documents still on process | 2
| 115 | [7 empty] | c) | PEO | c) | 12/31/18 | g) | 12/31/18 | c) | 230,657.28 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Prk.1-Prk.2, Sitio Pawas Road |  |  | Road | 1.4 | Admin | a) | 109068.92 | a) | 01/01/18 | e) | - | a) | 109068.92 | a) | 100.00% | c) | 100% | a) |  | Completed as per physical accomplishment. | 2
| DAN | [7 empty] | b) | Gamad/Maligro | b) | 02/12/18 | f) | - | b) | 109068.92 | b) | - | d) | - | b) |  | Financial documents still on process | 2
| 116 | [7 empty] | c) | PEO | c) | 12/31/18 | g) | 12/31/18 | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Dujali-Pawas-San Vicente Road |  |  | Road | 4.42 | Admin | a) | 103164.72 | a) | 01/01/18 | e) | - | a) | 103164.72 | a) | 100.00% | c) | 100% | a) | 12 | Completed as per physical accomplishment. | 2
| DAN | [7 empty] | b) | Gamad/Maligro | b) | 01/04/18 | f) | - | b) | 103164.72 | b) | - | d) | - | b) | 48 | Financial documents still on process | 2
| 117 | [7 empty] | c) | PEO | c) | 12/31/18 | g) | 12/31/18 | c) | 72,378.03 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Dujali-Pawas-San Vicente Road |  |  | Road | 4.42 | CBRMC | a) | 212322.24 | a) | 01/01/18 | e) | - | a) | 212322.24 | a) | 100.00% | c) | 100% | a) | 2 | Completed as per physical accomplishment. | 2
| DAN | [7 empty] | b) | Gamad/Maligro | b) | 05/07/18 | f) | - | b) | 212322.24 | b) | - | d) | - | b) | 24 | Financial documents still on process | 2
| 117 | [7 empty] | c) | Balisong San Vicente Irrigator's Association | c) | 02/07/19 | g) | 12/31/18 | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Jct.Salvacion-San Vicente-Cabay-angan |  |  | Road | 3.45 | Admin | a) | 205564.46 | a) | 01/01/18 | e) | - | a) | 205564.46 | a) | 100.00% | c) | 100% | a) | 12 | Completed as per physical accomplishment. | 2
| DAN |  | Road | [5 empty] | b) | Gamad/Maligro | b) | 01/03/18 | f) | - | b) | 205564.46 | b) | - | d) | - | b) | 48 | Financial documents still on process | 2
| 118 | [7 empty] | c) | PEO | c) | 12/31/18 | g) | 12/31/18 | c) | 202,565.93 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Jct.Salvacion-San Vicente-Cabay-angan |  |  | Road | 3.45 | CBRMC | a) | 133926.34 | a) | 01/01/18 | e) | - | a) | 133926.34 | a) | 100.00% | c) | 100% | a) | 2 | Completed as per physical accomplishment. | 2
| DAN |  | Road | [5 empty] | b) | Gamad/Maligro | b) | 05/07/18 | f) | - | b) | 133926.34 | b) | - | d) | - | b) | 4 | Financial documents still on process | 2
| 118 | [7 empty] | c) | Balisong San Vicente Irrigator's Association | c) | 02/07/19 | g) | 12/31/18 | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Dujali-San Miguel Road |  |  | Road | 3.95 | Admin | a) | 254671.37 | a) | 01/01/18 | e) | - | a) | 254671.37 | a) | 100.00% | c) | 100% | a) | 12 | Completed as per physical accomplishment. | 2
| DAN | [7 empty] | b) | Gamad/Maligro | b) | 02/16/18 | f) | - | b) | 254671.37 | b) | - | d) | - | b) | 60 | Financial documents still on process | 2
| 119 | [7 empty] | c) | PEO | c) | 2018-12-31 | g) | 2018-12-31 | c) | 247,867.31 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Dujali-San Miguel Road |  |  | Road | 3.95 | CBRMC | a) | 133926.34 | a) | 01/01/18 | e) | - | a) | 133926.34 | a) | 100.00% | c) | 100% | a) | - | Completed as per physical accomplishment. | 2
| DAN | [7 empty] | b) | Gamad/Maligro | b) | 01/03/18 | f) | - | b) | 133926.34 | b) | - | d) | - | b) | - | Financial documents still on process | 2
| 119 | [7 empty] | c) | Duajli Pob. Farmers Irrigator | c) | 12/31/18 | g) | 12/31/18 | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | San Miguel-Crossing Kinamayan Road |  |  | Road | 2.8 | Admin | a) | 71231.27 | a) | 01/01/18 | e) | - | a) | 71231.27 | a) | 100.00% | c) | 100% | a) |  | Completed as per physical accomplishment. | 2
| DAN | [7 empty] | b) | Gamad/Maligro | b) | 01/03/18 | f) | - | b) | 71231.27 | b) | - | d) | - | b) |  | Financial documents still on process | 2
| 120 | [7 empty] | c) | PEO | c) | 2018-12-31 | g) | 2018-12-31 | c) | 71,190.34 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | San Miguel-Libertad Road |  |  | Road | 6.2 | Admin | a) | 588705.52 | a) | 01/01/18 | e) | - | a) | 588705.52 | a) | 100.00% | c) | 100% | a) | 12 | Completed as per physical accomplishment. | 2
| DAN | [7 empty] | b) | Gamad/Maligro | b) | 01/03/18 | f) | - | b) | 588705.52 | b) | - | d) | - | b) | 36 | Financial documents still on process | 2
| 121 | [7 empty] | c) | PEO | c) | 2018-12-31 | g) | 2018-12-31 | c) | 574,308.39 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | San Miguel-Casig-ang Road |  |  | Road | 2.55 | Admin | a) | 175798.95 | a) | 01/01/18 | e) | - | a) | 175798.95 | a) | 100.00% | c) | 100% | a) | 12 | Completed as per physical accomplishment. | 2
| DAN | [7 empty] | b) | Gamad/Maligro | b) | 02/16/18 | f) | - | b) | 175798.95 | b) | - | d) | - | b) | 36 | Financial documents still on process | 2
| 122 | [7 empty] | c) | PEO | c) | 2018-12-31 | g) | 2018-12-31 | c) | 147,453.47 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | San Miguel-Casig-ang Road |  |  | Road | 2.55 | CBRMC | a) | 75129.41 | a) | 01/01/18 | e) | - | a) | 75129.41 | a) | 100.00% | c) | 100% | a) | - | Completed as per physical accomplishment. | 2
| DAN | [7 empty] | b) | Gamad/Maligro | b) | 01/03/18 | f) | - | b) | 75129.41 | b) | - | d) | - | b) | - | Financial documents still on process | 2
| 122 | [7 empty] | c) | KCIA | c) | 2018-12-31 | g) | 2018-12-31 | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Bacali-Casig-ang-Libertad Road |  |  | Road | 4.7 | Admin | a) | 446623.9 | a) | 01/01/18 | e) | - | a) | 446623.9 | a) | 100.00% | c) | 100% | a) |  | Completed as per physical accomplishment. | 2
| DAN | [7 empty] | b) | Gamad/Maligro | b) | 01/22/18 | f) | - | b) | 446623.9 | b) | - | d) | - | b) |  | Financial documents still on process | 2
| 123 | [7 empty] | c) | PEO | c) | 2018-12-31 | g) | 2018-12-31 | c) | 69,420.84 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Kinamayan-Moslog-Mahayag Road |  |  | Road | 3.23 | Admin | a) | 166223.27 | a) | 01/01/18 | e) | - | a) | 166223.27 | a) | 100.00% | c) | 100% | a) | 3 | Completed as per physical accomplishment. | 2
| DAN | [7 empty] | b) | Gamad/Maligro | b) | 02/12/18 | f) | - | b) | 166223.27 | b) | - | d) | - | b) | 12 | Financial documents still on process | 2
| 124 | [7 empty] | c) | PEO | c) | 2018-12-31 | g) | 2018-12-31 | c) | 147,526.53 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Kinamayan-Moslog-Mahayag Road |  |  | Road | 3.23 | CBRMC | a) | 120860.35 | a) | 01/01/18 | e) | - | a) | 120860.35 | a) | 100.00% | c) | 100% | a) | - | Completed as per physical accomplishment. | 2
| DAN | [7 empty] | b) | Gamad/Maligro | b) | 01/22/18 | f) | - | b) | 120860.35 | b) | - | d) | - | b) | - | Financial documents still on process | 2
| 124 | [7 empty] | c) | PAMIA | c) | 2018-12-31 | g) | 2018-12-31 | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | San Miguel-Moslog-Kinamayan Road |  |  | Road | 2.9 | Admin | a) | 202520.29 | a) | 01/01/18 | e) | - | a) | 202520.29 | a) | 100.00% | c) | 100% | a) | 10 | Completed as per physical accomplishment. | 2
| DAN | [7 empty] | b) | Gamad/Maligro | b) | 01/04/18 | f) | - | b) | 202520.29 | b) | - | d) | - | b) | 30 | Financial documents still on process | 2
| 125 | [7 empty] | c) | PEO | c) | 2018-12-31 | g) | 2018-12-31 | c) | 70,425.06 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Kinamayan-Lunga-og Road |  |  | Road | 2.59 | Admin | a) | 254864.48 | a) | 01/01/18 | e) | - | a) | 254864.48 | a) | 100.00% | c) | 100% | a) | 10 | Completed as per physical accomplishment. | 2
| DAN | [7 empty] | b) | Gamad/Maligro | b) | 01/03/18 | f) | - | b) | 254864.48 | b) | - | d) | - | b) | 30 | Financial documents still on process | 2
| 126 | [7 empty] | c) | PEO | c) | 2018-12-31 | g) | 2018-12-31 | c) | 248,573.64 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Prk.Magsaysay-Lunga-og-Dalisay Road |  |  | Road | 2.81 | Admin | a) | 152386.36 | a) | 01/01/18 | e) | - | a) | 152386.36 | a) | 100.00% | c) | 100% | a) |  | Completed as per physical accomplishment. | 2
| DAN | [7 empty] | b) | Gamad/Maligro | b) | 01/03/18 | f) | - | b) | 152386.36 | b) | - | d) | - | b) |  | Financial documents still on process | 2
| 127 | [7 empty] | c) | PEO | c) | 2018-12-31 | g) | 2018-12-31 | c) | 130,525.88 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Prk.Magsaysay-Lunga-og-Dalisay Road |  |  | Road | 2.81 | CBRMC | a) | 124126.85 | a) | 01/01/18 | e) | - | a) | 124126.85 | a) | 100.00% | c) | 100% | a) | 2 | Completed as per physical accomplishment. | 2
| DAN | [7 empty] | b) | Gamad/Maligro | b) | 05/07/18 | f) | - | b) | 124126.85 | b) | - | d) | - | b) | 2 | Financial documents still on process | 2
| 127 | [7 empty] | c) | Lunga-og Tribal Association | c) | 02/07/19 | g) | 12/31/18 | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Prk.Apitong-Upper Balisong-Dalisay |  |  | Road | 4.6 | Admin | a) | 200531.56 | a) | 01/01/18 | e) | - | a) | 200531.56 | a) | 100.00% | c) | 100% | a) | 12 | Completed as per physical accomplishment. | 2
| DAN |  | Road | [5 empty] | b) | Gamad/Maligro | b) | 01/03/18 | f) | - | b) | 200531.56 | b) | - | d) | - | b) | 36 | Financial documents still on process | 2
| 128 | [7 empty] | c) | PEO | c) | 2018-12-31 | g) | 2018-12-31 | c) | 200,041.98 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Prk.Apitong-Upper Balisong-Dalisay |  |  | Road | 4.6 | CBRMC | a) | 182923.78 | a) | 01/01/18 | e) | - | a) | 182923.78 | a) | 100.00% | c) | 100% | a) | 2 | Completed as per physical accomplishment. | 2
| DAN |  | Road | [5 empty] | b) | Gamad/Maligro | b) | 05/07/18 | f) | - | b) | 182923.78 | b) | - | d) | - | b) | 2 | Financial documents still on process | 2
| 128 | [7 empty] | c) | Lunga-og Tribal Association | c) | 02/07/19 | g) | 12/31/18 | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Sitio Paradise-Magkakaisa-Esperanza |  |  | Road | 1.75 | Admin | a) | 67345.26 | a) | 01/01/18 | e) | - | a) | 67345.26 | a) | 100.00% | c) | 100% | a) | 10 | Completed as per physical accomplishment. | 2
| DAN |  | Road | [5 empty] | b) | Gamad/Maligro | b) | 01/04/18 | f) | - | b) | 67345.26 | b) | - | d) | - | b) | 20 | Financial documents still on process | 2
| 129 | [7 empty] | c) | PEO | c) | 2018-12-31 | g) | 2018-12-31 | c) | 58,485.82 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Sitio Paradise-Magkakaisa-Esperanza |  |  | Road | 1.75 | CBRMC | a) | 88195.39 | a) | 01/01/18 | e) | - | a) | 88195.39 | a) | 100.00% | c) | 100% | a) | 2 | Completed as per physical accomplishment. | 2
| DAN |  | Road | [5 empty] | b) | Gamad/Maligro | b) | 05/09/18 | f) | - | b) | 88195.39 | b) | - | d) | - | b) | 4 | Financial documents still on process | 2
| 129 | [7 empty] | c) | Los Amigos Group of Women & Farmers Association | c) | 02/09/19 | g) | 12/31/18 | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Los Amigos 1-Esperanza-Los Amigos 2 |  |  | Road | 3.59 | Admin | a) | 129623.79 | a) | 01/01/18 | e) | - | a) | 129623.79 | a) | 100.00% | c) | 100% | a) |  | Completed as per physical accomplishment. | 2
| DAN |  | Road | [5 empty] | b) | Gamad/Maligro | b) | 01/04/18 | f) | - | b) | 129623.79 | b) | - | d) | - | b) |  | Financial documents still on process | 2
| 130 | [7 empty] | c) | PEO | c) | 2018-12-31 | g) | 2018-12-31 | c) | 113,391.65 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Los Amigos 1-Esperanza-Los Amigos 2 |  |  | Road | 3.59 | CBRMC | a) | 189456.77 | a) | 01/01/18 | e) | - | a) | 189456.77 | a) | 100.00% | c) | 100% | a) | 2 | Completed as per physical accomplishment. | 2
| DAN |  | Road | [5 empty] | b) | Gamad/Maligro | b) | 05/09/18 | f) | - | b) | 189456.77 | b) | - | d) | - | b) | 2 | Financial documents still on process | 2
| 130 | [7 empty] | c) | Los Amigos Group of Women & Farmers Association | c) | 02/09/19 | g) | 12/31/18 | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Mugas-Lanatad Road |  |  | Road | 1.53 | Admin | a) | 153098.12 | a) | 01/01/18 | e) | - | a) | 153098.12 | a) | 100.00% | c) | 100% | a) |  | Completed as per physical accomplishment. | 2
| DAN | [7 empty] | b) | Gamad/Maligro | b) | 01/22/18 | f) | - | b) | 153098.12 | b) | - | d) | - | b) |  | Financial documents still on process | 2
| 131 | [7 empty] | c) | PEO | c) | 2018-12-31 | g) | 2018-12-31 | c) | 130,993.26 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Mugas-Lunga-og Road |  |  | Road | 2.68 | Admin | a) | 128090.03 | a) | 01/01/18 | e) | - | a) | 128090.03 | a) | 100.00% | c) | 100% | a) | 12 | Completed as per physical accomplishment. | 2
| DAN | [7 empty] | b) | Gamad/Maligro | b) | 02/16/18 | f) | - | b) | 128090.03 | b) | - | d) | - | b) | 60 | Financial documents still on process | 2
| 132 | [7 empty] | c) | PEO | c) | 2018-12-31 | g) | 2018-12-31 | c) | 119,702.20 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Mugas-Lunga-og Road |  |  | Road | 2.68 | CBRMC | a) | 93095.14 | a) | 01/01/18 | e) | - | a) | 93095.14 | a) | 100.00% | c) | 100% | a) | 2 | Completed as per physical accomplishment. | 2
| DAN | [7 empty] | b) | Gamad/Maligro | b) | 05/07/18 | f) | - | b) | 93095.14 | b) | - | d) | - | b) | 2 | Financial documents still on process | 2
| 132 | [7 empty] | c) | Lunga-og Tribal Association | c) | 02/07/19 | g) | 12/31/18 | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Pantaron-Mugas Road |  |  | Road | 3.35 | Admin | a) | 198806.74 | a) | 01/01/18 | e) | - | a) | 198806.74 | a) | 100.00% | c) | 100% | a) | 12 | Completed as per physical accomplishment. | 2
| DAN | [7 empty] | b) | Gamad/Maligro | b) | 02/12/18 | f) | - | b) | 198806.74 | b) | - | d) | - | b) | 36 | Financial documents still on process | 2
| 133 | [7 empty] | c) | PEO | c) | 2018-12-31 | g) | 2018-12-31 | c) | 152,359.49 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Pantaron-Mugas Road |  |  | Road | 3.35 | CBRMC | a) | 137192.83 | a) | 01/01/18 | e) | - | a) | 137192.83 | a) | 100.00% | c) | 100% | a) | - | Completed as per physical accomplishment. | 2
| DAN | [7 empty] | b) | Gamad/Maligro | b) | 01/22/18 | f) | - | b) | 137192.83 | b) | - | d) | - | b) | - | Financial documents still on process | 2
| 133 | [7 empty] | c) | Katipunan Pantaron Irrigators Assoc. | c) | 2018-12-31 | g) | 12/31/18 | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | New Katipunan-Pantaron Road |  |  | Road | 1.96 | Admin | a) | 192870.42 | a) | 01/01/18 | e) | - | a) | 192870.42 | a) | 100.00% | c) | 100% | a) | 3 | Completed as per physical accomplishment. | 2
| DAN | [7 empty] | b) | Gamad/Maligro | b) | 01/04/18 | f) | - | b) | 192870.42 | b) | - | d) | - | b) | 12 | Financial documents still on process | 2
| 134 | [7 empty] | c) | PEO | c) | 12/31/18 | g) | 12/31/18 | c) | 51,000.00 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Sto.Tomas-Bdry.Mamacao Road |  |  | Road | 4.9 | Admin | a) | 328576.02 | a) | 01/01/18 | e) | - | a) | 328576.02 | a) | 100.00% | c) | 100% | a) | 6 | Completed as per physical accomplishment. | 2
| DAN | [7 empty] | b) | Gamad/Maligro | b) | 01/22/18 | f) | - | b) | 328576.02 | b) | - | d) | - | b) | 36 | Financial documents still on process | 2
| 135 | [7 empty] | c) | PEO | c) | 12/31/18 | g) | 12/31/18 | c) | 191,558.02 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Sto.Tomas-Bdry.Mamacao Road |  |  | Road | 4.9 | CBRMC | a) | 163324.8 | a) | 01/01/18 | e) | - | a) | 163324.8 | a) | 100.00% | c) | 100% | a) | 2 | Completed as per physical accomplishment. | 2
| DAN | [7 empty] | b) | Gamad/Maligro | b) | 04/19/18 | f) | - | b) | 163324.8 | b) | - | d) | - | b) | 6 | Financial documents still on process | 2
| 135 | [7 empty] | c) | Poblacion Tibal-og Tribal Assoc | c) | 01/19/19 | g) | 12/31/18 | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Fd.Rd.3-San Jose Road |  |  | Road | 4.55 | Admin | a) | 251487.26 | a) | 01/01/18 | e) | - | a) | 251487.26 | a) | 100.00% | c) | 100% | a) | 12 | Completed as per physical accomplishment. | 2
| DAN | [7 empty] | b) | Gamad/Maligro | b) | 02/16/18 | f) | - | b) | 251487.26 | b) | - | d) | - | b) | 36 | Financial documents still on process | 2
| 136 | [7 empty] | c) | PEO | c) | 12/31/18 | g) | 12/31/18 | c) | 193,902.25 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Fd.Rd.3-San Jose Road |  |  | Road | 4.55 | CBRMC | a) | 140459.33 | a) | 01/01/18 | e) | - | a) | 140459.33 | a) | 100.00% | c) | 100% | a) | 2 | Completed as per physical accomplishment. | 2
| DAN | [7 empty] | b) | Gamad/Maligro | b) | 05/30/18 | f) | 05/30/18 | b) | 140459.33 | b) | - | d) | - | b) | 2 | Financial documents still on process | 2
| 136 | [7 empty] | c) | Brgy. San Jose Upland Farmers Assoc of Sto. Tomas, DDN, inc | c) |  | g) | - | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Fd.Rd.2-Sto.Tomas-Magwawa Road |  |  | Road | 10.21 | Admin | a) | 438,0.37.15 | a) | 01/01/18 | e) | - | a) | 438,0.37.15 | a) | 100.00% | c) | 100% | a) | 6 | Completed as per physical accomplishment. | 2
| DAN | [7 empty] | b) | Gamad/Maligro | b) | 01/22/18 | f) | - | b) | 438,0.37.15 | b) | - | d) | - | b) | 36 | Financial documents still on process | 2
| 137 | [7 empty] | c) | PEO | c) | 2018-12-31 | g) | 2018-12-31 | c) | 148,575.00 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Menzi-Balagunan-Tulalian Road |  |  | Road | 10.63 | Admin | a) | 631810.16 | a) | 01/01/18 | e) | - | a) | 631810.16 | a) | 100.00% | c) | 100% | a) | 12 | Completed as per physical accomplishment. | 2
| DAN | [7 empty] | b) | Gamad/Maligro | b) | 01/04/18 | f) | - | b) | 631810.16 | b) | - | d) | - | b) | 120 | Financial documents still on process | 2
| 138 | [7 empty] | c) | PEO | c) | 2018-12-31 | g) | 2018-12-31 | c) | 490,290.55 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Menzi-Balagunan-Tulalian Road |  |  | Road | 10.63 | CBRMC | a) | 382180.03 | a) | 01/01/18 | e) | - | a) | 382180.03 | a) | 100.00% | c) | 100% | a) | - | Completed as per physical accomplishment. | 2
| DAN | [7 empty] | b) | Gamad/Maligro | b) | 06/18/18 | f) | - | b) | 382180.03 | b) | - | d) | - | b) | - | Financial documents still on process | 2
| 138 | [7 empty] | c) | - | c) | 03/17/18 | g) | 03/17/18 | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | NAFCO-Bobongon Road |  |  | Road | 2.66 | Admin | a) | 261752.71 | a) | 01/01/18 | e) | - | a) | 261752.71 | a) | 100.00% | c) | 100% | a) | 14 | Completed as per physical accomplishment. | 2
| DAN | [7 empty] | b) | Gamad/Maligro | b) | 01/08/18 | f) | - | b) | 261752.71 | b) | - | d) | - | b) | 140 | Financial documents still on process | 2
| 139 | [7 empty] | c) | PEO | c) | 2018-12-31 | g) | 2018-12-31 | c) | 255,107.41 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Jct.Highway-Tanglaw Road |  |  | Road | 3.98 | Admin | a) | 369464.93 | a) | 01/01/18 | e) | - | a) | 369464.93 | a) | 100.00% | c) | 100% | a) |  | Completed as per physical accomplishment. | 2
| DAN | [7 empty] | b) | Gamad/Maligro | b) | 02/16/18 | f) | - | b) | 369464.93 | b) | - | d) | - | b) |  | Financial documents still on process | 2
| 142 | [7 empty] | c) | PEO | c) | 2018-12-31 | g) | 2018-12-31 | c) | 40,667.20 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Fd.Rd.3-Kimamon-Luna Road |  |  | Road | 11.76 | Admin | a) | 1073416.56 | a) | 01/01/18 | e) | - | a) | 1073416.56 | a) | 100.00% | c) | 100% | a) |  | Completed as per physical accomplishment. | 2
| DAN | [7 empty] | b) | Gamad/Maligro | b) | 01/04/18 | f) | - | b) | 1073416.56 | b) | - | d) | - | b) |  | Financial documents still on process | 2
| 143 | [7 empty] | c) | PEO | c) | 2018-12-31 | g) | 2018-12-31 | c) | 183,025.00 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Kimamon-Lunga-og-Talomo Road |  |  | Road | 5.99 | Admin | a) | 565379.82 | a) | 01/01/18 | e) | - | a) | 565379.82 | a) | 100.00% | c) | 100% | a) | 14 | Completed as per physical accomplishment. | 2
| DAN | [7 empty] | b) | Gamad/Maligro | b) | 01/03/18 | f) | - | b) | 565379.82 | b) | - | d) | - | b) | 140 | Financial documents still on process | 2
| 144 | [7 empty] | c) | PEO | c) | 2018-12-31 | g) | 2018-12-31 | c) | 555,350.22 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Jct.Bdry.Tagum-Talomo Road |  |  | Road | 12.01 | Admin | a) | 766269.09 | a) | 01/01/18 | e) | - | a) | 766269.09 | a) | 100.00% | c) | 100% | a) | 14 | Completed as per physical accomplishment. | 2
| DAN | [7 empty] | b) | Gamad/Maligro | b) | 01/03/18 | f) | - | b) | 766269.09 | b) | - | d) | - | b) | 140 | Financial documents still on process | 2
| 145 | [7 empty] | c) | PEO | c) | 2018-12-31 | g) | 2018-12-31 | c) | 759,363.83 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Jct.Bdry.Tagum-Talomo Road |  |  | Road | 12.01 | CBRMC | a) | 306326.59 | a) | 01/01/18 | e) | - | a) | 306326.59 | a) | 100.00% | c) | 100% | a) | - | Completed as per physical accomplishment. | 2
| DAN | [7 empty] | b) | Gamad/Maligro | b) | 11/28/18/ | f) | - | b) | 306326.59 | b) | - | d) | - | b) | - | Financial documents still on process | 2
| 145 | [7 empty] | c) | - | c) | 01/31/19 | g) | 12/27/18 | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Bdry.Tagum-Crossing Kinamayan- |  |  | Road | 19.16 | Admin | a) | 1499919.84 | a) | 01/01/18 | e) | - | a) | 1499919.84 | a) | 100.00% | c) | 100% | a) | 3 | Completed as per physical accomplishment. | 2
| DAN |  | Sto.Tomas Road | [5 empty] | b) | Gamad/Maligro | b) | 01/22/18 | f) | - | b) | 1499919.84 | b) | - | d) | - | b) | 12 | Financial documents still on process | 2
| 146 | [7 empty] | c) | PEO | c) | 2018-12-31 | g) | 2018-12-31 | c) | 956,472.04 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Prk.Daisy-Prk.Narafil Road |  |  | Road | 0.75 | Admin | a) | 11982.88 | a) | 01/01/18 | e) | - | a) | 11982.88 | a) | 100.00% | c) | 100% | a) |  | Completed as per physical accomplishment. | 2
| DAN | [7 empty] | b) | Gamad/Maligro | b) | 01/03/18 | f) | - | b) | 11982.88 | b) | - | d) | - | b) |  | Financial documents still on process | 2
| 148 | [7 empty] | c) | PEO | c) | 2018-12-31 | g) | 2018-12-31 | c) | 8,711.22 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Tuganay - Anibongan - San Isidro Road |  |  | Road | 6.73 | CBRMC | a) | 52,000.00 | a) | 01/01/18 | e) | - | a) | 52,000.00 | a) | 100.00% | c) | 100% | a) | 2 | Completed as per physical accomplishment. | 2
| DAN | [7 empty] | b) | Gamad/Maligro | b) | 11/19/18 | f) | - | b) | 52,000.00 | b) | - | d) | - | b) | 2 | Financial documents still on process | 2
| 091 | [7 empty] | c) | EZRA | c) | 02/04/19 | g) | 12/11/18 | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Dujali - Balisong - Magupising Road |  |  | Road | 6.73 | CBRMC | a) | 29,398.46 | a) | 01/01/18 | e) | - | a) | 29,398.46 | a) | 100.00% | c) | 100% | a) | 2 | Completed as per physical accomplishment. | 2
| DAN | [7 empty] | b) | Gamad/Maligro | b) | 05/04/18 | f) | - | b) | 29,398.46 | b) | - | d) | - | b) | 2 | Financial documents still on process | 2
| 091 | [7 empty] | c) | Duajli Pob. Farmers Irrigators | c) | 02/04/19 | g) | 12/11/18 | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
AC
|  |  | Rehabilitation / Improvement Of Various Local |  |  | Road | - | Admin | a) | 5000000 | [12 empty] | See projects listed below | AC
|  |  | Roads and Drainages | [5 empty] | b) | Paraguya | [13 empty] | AC
[9 empty] | c) | Admin | [13 empty] | AC
[9 empty] | d) | - | [13 empty] | AC
|  |  |  | Rehabilitation of Brgy. Tagbay Barangay |  | Road |  | Admin | a) | 138000 | a) | 04/25/18 | e) | - | a) | 138000 | a) | 100.00% | c) | 100.00% | a) | - | Completed as per physical accomplishment. | 2
|  |  |  | Road, IGACOS |  |  |  |  | b) | Porras/Pacquiao | b) | 12/05/18 | f) | - | b) | 138000 | b) | - | d) | - | b) | - | Financial documents still on process | 2
[9 empty] | c) | PEO | c) | 12/07/18 | g) | 12/07/18 | c) | - | [7 empty] | 2
[9 empty] | d) | - | [13 empty] | 2
|  |  |  | Rehabilitation of Brgy. San Jose Barangay |  | Road |  | Admin | a) | 138000 | a) | 04/25/18 | e) | - | a) | 138000 | a) | 100.00% | c) | 100.00% | a) | - | Completed as per physical accomplishment. | 2
|  |  |  | Road, IGACOS |  |  |  |  | b) | Porras/Pacquiao | b) | 10/27/18 | f) | - | b) | 138000 | b) | - | d) | - | b) | - | Financial documents still on process | 2
[9 empty] | c) | PEO | c) | 10/31/18 | g) | 10/31/18 | c) | - | [7 empty] | 2
[9 empty] | d) | - | [13 empty] | 2
|  |  |  | Rehabilitation of Brgy. Guilon Barangay |  | Road |  | Admin | a) | 138000 | a) | 04/25/18 | e) | - | a) | 138000 | a) | 100.00% | c) | 100.00% | a) | 3 | Completed as per physical accomplishment. | 2
|  |  |  | Road, IGACOS |  |  |  |  | b) | Porras/Pacquiao | b) | 01/10/19 | f) | - | b) | 138000 | b) | - | d) | - | b) | 30 | Financial documents still on process | 2
[9 empty] | c) | PEO | c) | 01/19/19 | g) | - | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  |  | Rehabilitation of Brgy. Del Monte Barangay |  | Road |  | Admin | a) | 138000 | a) | 04/25/18 | e) | - | a) | 138000 | a) | 100.00% | c) | 100.00% | a) | - | Completed as per physical accomplishment. | 2
|  |  |  | Road, IGACOS |  |  |  |  | b) | Porras/Pacquiao | b) | 12/12/18 | f) | - | b) | 138000 | b) | - | d) | - | b) | - | Financial documents still on process | 2
[9 empty] | c) | PEO | c) | 01/08/19 | g) | - | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  |  | Rehabilitation of Brgy. Tagbitan-ag |  | Road |  | Admin | a) | 138000 | a) | 04/25/18 | e) | 61 CD | a) | 138000 | a) | 100% | c) | 100% | a) | 5 | Completed as per physical accomplishment. | 2
|  |  |  | Barangay Road, IGACOS |  |  |  |  | b) | Porras/Pacquiao | b) | 02/15/19 | f) | 30 WD | b) | 138000 | b) | - | d) | - | b) | 45 | Financial documents still on process | 2
[9 empty] | c) | PEO | c) | 02/24/19 | g) | 03/15/19 | c) | 127356.84 | [7 empty] | 2
[9 empty] | d) | - | d) | 03/15/19 | [11 empty] | 2
|  |  |  | Rehabilitation of Brgy. Peñaplata Barangay |  | Road |  | Admin | a) | 139000 | a) | 04/25/18 | e) | 66 CD | a) | 139000 | a) | 100% | c) | 100 | a) | 1 | Completed 8/31/2019 | 2
|  |  |  | Road, IGACOS |  |  |  |  | b) | Porras/Pacquiao | b) | 8/16/2019 | f) | 225 CD | b) | 139000 | b) | - | d) | - | b) | 1 |  | 2
[9 empty] | c) | PEO | c) | 8/31/2019 | g) | - | c) | 139000 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  |  | Rehabilitation of Brgy. Pob. Kaputian |  | Road |  | Admin | a) | 138000 | a) | 04/25/18 | e) | - | a) | 138000 | a) | 100% | c) | 100% | a) | 4 |  | 2
|  |  |  | Barangay Road, IGACOS |  |  |  |  | b) | Porras/Pacquiao | b) | 2019-08-08 | f) | - | b) | 138000 | b) | - | d) | - | b) | 36 | Completed Sept. 22, 2019 | 2
[9 empty] | c) | PEO | c) | 9/22/2019 | g) | 9/22/2019 | c) | - | [7 empty] | 2
[9 empty] | d) | 6/13/19 | d) | - | [11 empty] | 2
|  |  |  | Rehabilitation of Brgy. Sto. NIño Barangay |  | Road |  | Admin | a) | 130000 | a) | 04/13/18 | e) | - | a) | 130000 | a) | 100.00% | c) | 100.00% | a) | 3 | Completed as per physical accomplishment. | 2
|  |  |  | Road, IGACOS |  |  |  |  | b) | Porras/Pacquiao | b) | 03/07/19 | f) | - | b) | 130000 | b) | - | d) | - | b) | 30 | Financial documents still on process | 2
[9 empty] | c) | PEO | c) | 03/16/19 | g) | 03/15/19 | c) | 107,972.00 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  |  | Rehabilitation of Brgy.Licup Barangay |  | Road |  | Admin | a) | 139000 | a) | 04/25/18 | e) | - | a) | 139000 | a) | 100.00% | c) | 100.00% | a) | 5 | Completed as per physical accomplishment. | 2
|  |  |  | Road, IGACOS |  |  |  |  | b) | Porras/Pacquiao | b) | 03/21/19 | f) | - | b) | 139000 | b) | - | d) | - | b) | 100 | Financial documents still on process | 2
[9 empty] | c) | PEO | c) | 03/29/19 | g) | 03/29/19 | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  |  | Rehabilitation of Brgy. Aundanao Barangay |  | Road |  | Admin | a) | 138000 | a) | 04/25/18 | e) | - | a) | 138000 | a) | 100.00% | c) | 100.00% | a) | 6 | Completed as per physical accomplishment. | 2
|  |  |  | Road, IGACOS |  |  |  |  | b) | Porras/Pacquiao | b) | 04/01/19 | f) | - | b) | 138000 | b) | - | d) | - | b) | 12 | Financial documents still on process | 2
[9 empty] | c) | PEO | c) | 04/09/19 | g) | 04/12/19 | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
4 |  |  |  | Rehabilitation of Brgy. Adecor Barangay |  | Road |  | Admin | a) | 138000 | a) | 04/25/18 | e) | 66 CD | a) | 138000 | a) | 60.00% | c) | 60.00% | a) | - | Completed as per POW. Financial Documents on process | 2
4 |  |  |  | Road, IGACOS |  |  |  |  | b) | Porras/Pacquiao | b) | 10/18/18 | f) | 225 CD | b) | 138000 | b) | - | d) | - | b) | - |  | 2
4 | [8 empty] | c) | PEO | c) | 10/27/19 | g) | - | c) | 111,872.00 | [7 empty] | 2
4 | [8 empty] | d) | - | d) | 10/15/2019 | [11 empty] | 2
|  |  | Water System Development Project | [20 empty] | AC
|  |  | Construction of Water System Projects in Component LGU's | [20 empty] | AC
|  |  |  | Impv't. of Water System, Brgy. Poblacion |  | Water |  | Admin | a) | 1250000 | a) | 08/24/18 | e) | - | a) | 1250000 | a) | 100% | c) | 85.39% | a) | 8 | Completed (contract by Zular3-Az) September 15, 2019 | AC
|  |  |  | Kaputian (Level II) |  | system |  |  | b) | Porras | b) | 05/3/19 | f) | - | b) | 1250000 | b) | - | d) | -14.61 | b) | 160 |  | AC
[9 empty] | c) | Contract | c) | 08/30/19 | g) | 09/15/2019 | c) | - | [7 empty] | AC
[9 empty] | d) | - | d) | - | [11 empty] | AC
|  |  | Const./Rehab./Comp. of Various Gov't. Bldgs. |  |  | Bldgs. | - | Admin | a) | 13523124 | [12 empty] | Investigation/Inspection of priority projects | AC
|  |  | Struct., Fac. (Provincewide) | [5 empty] | b) | Foronda | [13 empty] | AC
[9 empty] | c) | Admin | [13 empty] | AC
[9 empty] | d) | - | [13 empty] | AC
|  |  |  | Completion of PVO Bldg. (PVO Penthouse), |  | Bldgs. |  | Admin | a) | 1,500,000.00 | a) | 04/02/18 | e) | - | a) | 1,500,000.00 | a) | 100.00% | c) | 100.00% | a) | - | Completed as per physical accomplishment. | 1
|  |  |  | Gov't. Center, Mankilam |  |  |  |  | b) | Pasiona | b) | 09/03/18 | f) | - | b) | 1,500,000.00 | b) | - | d) | - | b) | - | Financial documents still on process | 1
[9 empty] | c) | Admin | c) | 12/01/18 | g) | 01/15/19 | c) | 1,052,849.49 | [7 empty] | 1
[9 empty] | d) | 90 CD | d) | - | [11 empty] | 1
1
|  |  |  | Construction of Multi-Purpose Bldg. |  | Bldg | 303.75 sq.m | Admin | a) | 6748000 | a) | 12/11/18 | e) | - | a) | 6748000 | a) |  | c) | 100% | a) | 25 | Completed | 1
|  |  |  | (PENRO Building), Mankilam, Tagum City |  |  |  |  | b) | Pasiona/Juan | b) | 10/16/18 | f) | 109 | b) | 6748000 | b) | - | d) |  | b) | 750 |  | 1
|  |  |  | (Part of 8,548,000.00) |  |  |  |  | c) | PEO | c) | 9/13/2019 | g) | - | c) | 6560497.45 | [7 empty] | 1
|  |  |  | (P1,800,000.00 - SB # 3 CY 2017) |  |  |  |  | d) | 256 CD | d) | 06/30/19 | [11 empty] | 1
4 |  |  |  | Repair/Rehab. Of PEO Building (2nd District), Carmen |  | Bldg |  | Admin | a) | 2250000 | a) | 08/10/18 | e) | - | a) | 2250000 | a) | 100% | c) | 100% | a) | 18 | Completed based on POW. Financial Documents on process | 2
4 | [8 empty] | b) | Andoy | b) | 02/18/19 | f) | - | b) | 2250000 | b) | - | d) | 0% | b) | 138 |  | 2
4 | [8 empty] | c) | Admin | c) | 08/23/19 | g) | - | c) | 1577344.8 | [7 empty] | 2
4 | [8 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | STIMULUS PROJECTS | [20 empty] | AC
|  |  | TAGUM CITY | [20 empty] | AC
|  |  |  | Construction of Brgy. GYM Bleacher, |  | Bleacher |  | Contract | a) | 500000 | a) | 06/05/18 | e) | - | a) | 500000 | a) | 100.00% | c) | 100.00% | a) | - | Completed as per physical accomplishment. | 1
|  |  |  | Pandapan, Tagum City |  |  |  |  | b) | Mayang | b) | 11/16/18 | f) | - | b) | 500000 | b) | - | d) | - | b) | - | Financial documents still on process | 1
[9 empty] | c) | FT Const. | c) | 01/15/19 | g) | 01/31/19 | c) | 417608 | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  |  | Repair of Brgy. Hall, San Miguel, |  | Bldg. |  | Admin | a) | 500000 | a) | 10/26/18 | e) | 13 | a) | 500000 | a) | 100% | c) | 100% | a) | 4 | Completed as per physical accomplishment. | 1
|  |  |  | Tagum City |  |  |  |  | b) | Mayang | b) | 03/04/19 | f) | 8 days | b) | 500000 | b) | - | d) | 0% | b) | 88 | Financial documents still on process | 1
[9 empty] | c) | Admin | c) | 05/23/19 | g) | 6/14/19 | c) | 411,905.79 | [7 empty] | 1
[9 empty] | d) | 50 CD | d) | - | [11 empty] | 1
4 |  |  |  | Completion of Two Storey Multi-Purpose |  | Bldg. |  | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | 100% | c) | 100% | a) | 5 | Completed based on Physical Accomplishment. Financial Documents on process | 1
4 |  |  |  | Building, Magugpo East, Tagum City |  |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | 0% | b) | 110 |  | 1
4 | [8 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 1
4 | [8 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | IGCS | [20 empty] | AC
|  |  | 1 | 1 | Const. of Public Toilet at Guilon, IGCS | Bldg. |  | Admin | a) | 500000 | a) | 07/05/18 | e) | - | a) | 500000 | a) | 100.00% | c) | 100% | a) | - | Completed as per physical accomplishment. | 2
[9 empty] | b) | - | b) | 12/31/17 | f) | - | b) | 500000 | b) | - | d) | - | b) | - | Financial documents still on process | 2
[9 empty] | c) | - | c) | 10/19/18 | g) | 10/19/18 | c) | 403,637.34 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | 2 | 2 | Impv't. of Brgy. Hall, Cawag, IGCS | Bldg. |  | Admin | a) | 500000 | a) | 07/19/18 | e) | - | a) | 500000 | a) | 100.00% | c) | 100.00% | a) | - | Completed as per physical accomplishment. | 2
[9 empty] | b) | Porras | b) | 09/04/18 | f) | - | b) | 500000 | b) | - | d) | - | b) | - | Financial documents still on process | 2
[9 empty] | c) | Admin | c) | 12/12/18 | g) | 12/12/18 | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | 3 | 3 | Improvement of Brgy. Hall, Kinawitnon, | Bldg. |  | Admin | a) | 500000 | a) | 07/05/18 | e) | - | a) | 500000 | a) | 100.00% | c) | 100.00% | a) | - | Completed as per physical accomplishment. | 2
[5 empty] | IGCS |  |  |  | b) | Roque | b) | 10/24/18 | f) | 19 days | b) | 500000 | b) | - | d) | - | b) | - | Financial documents still on process | 2
[9 empty] | c) | PEO | c) | 11/11/19 | g) | 01/11/19 | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | 4 | 4 | Const. of New Brgy. Hall, Adecor, IGCS | Bldg. |  | Contract | a) | 500000 | a) | 10/16/18 | e) | - | a) | 500000 | a) | 100.00% | c) | 100.00% | a) | - | Completed as per physical accomplishment. | 2
[9 empty] | b) | Porras | b) | 02/21/19 | f) | - | b) | 500000 | b) | - | d) | - | b) | - | Financial documents still on process | 2
[9 empty] | c) | Ecomixed | c) | 03/03/19 | g) | 03/03/19 | c) | 475414.3 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | 5 | 5 | Impv't. of Multi-Purpose Bldg. | Bldg. |  | Admin | a) | 500000 | a) | 07/05/18 | e) | - | a) | 500000 | a) | 100.00% | c) | 100.00% | a) | 7 | Completed as per physical accomplishment. | 2
[5 empty] | (Covered Court), Tagbitan-ag, IGCS |  |  |  | b) | Porras | b) | 12/31/17 | f) | - | b) | 500000 | b) | - | d) | - | b) | 35 | Financial documents still on process | 2
[9 empty] | c) | PEO | c) | 10/19/18 | g) | 03/08/19 | c) | 494,673.25 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
4 |  | L. | 5% Calamity Fund CY 2018 | [20 empty] | AC
4 |  |  | 1. Prevention and Mitigation | [20 empty] | AC
4 |  |  | 1.1 Desiltation/Excavation of rivers and creeks |  |  | rivers |  | Admin | a) | 3000000 | [12 empty] | Investigation/Inspection of priority projects | AC
4 | [8 empty] | b) | - | [13 empty] | AC
4 | [8 empty] | c) | PEO | [13 empty] | AC
4 | [8 empty] | d) | - | [13 empty] | AC
4 | [23 empty] | 1
4 |  |  | 1.1.1. | Improvement and Desiltation of Tagum Creek (Phase I and Phase II) |  | Creek |  | Admin | a) | 2,000,000.00 | a) | 11/06/18 | e) | - | a) | 2,000,000.00 | a) | 100% | c) | 100% | a) | 5 | Completed | 1
4 | [8 empty] | b) | Mayang | b) | 03/22/19 | f) | - | b) | 2,000,000.00 | b) | - | d) | 0% | b) | 110 |  | 1
4 | [8 empty] | c) | PEO | c) | 10/31/19 | g) | - | c) | - | [7 empty] | 1
4 | [8 empty] | d) | 224 CD | d) | - | [11 empty] | 1
|  | E. | SUPPLEMENTAL BUDGET # 1 CY 2018 | [5 empty] | a) | 6,000,000.00 | [12 empty] | See list of Provincial Roads | AC
|  |  | 1 Const./Impv't./Compl. Of School Buildings, | [20 empty] | AC
|  |  | Structures & Facilities | [20 empty] | AC
|  |  |  | Completion of Carmen Central E/S Gym |  | Gym |  | Admin | a) | 1000000 | a) | 07/31/18 | e) | - | a) | 1000000 | a) | 100.00% | c) | 100.00% | a) | 10 | Completed as per physical accomplishment. | 2
[9 empty] | b) | Estorco | b) | 12/07/18 | f) | - | b) | 1000000 | b) | - | d) | - | b) | 300 | Financial documents still on process | 2
[9 empty] | c) | PEO | c) | 04/19/19 | g) | - | c) | 818,875.12 | [7 empty] | 2
[9 empty] | d) | 130 CD | d) | - | [11 empty] | 2
|  |  |  | Const. of Dujali E/S Gym |  | Gym |  | Admin | a) | 2,109,662.99 | a) | 07/05/18 | e) | - | a) | 2,109,662.99 | a) | 100.00% | c) | 100.00% | a) | 4 | Completed as per physical accomplishment. | 2
[9 empty] | b) | Azotes | b) | 12/07/18 | f) | - | b) | 2,109,662.99 | b) | - | d) | - | b) | 88 | Financial documents still on process | 2
[9 empty] | c) | PEO | c) | 04/15/19 | g) | 04/01/19 | c) | 1,712,249.72 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | 1 Const. in Progress - Infrastructure | [5 empty] | b) | Paraguya | [13 empty] | AC
|  |  | Assets (Rehabilitation of Various | [5 empty] | c) | PEO | [13 empty] | AC
|  |  | Provincial Roads) | [5 empty] | d) | - | [13 empty] | AC
|  |  | 3 | a. | New Corella - New Sambog - Silangan | Road |  | Admin | a) | 2,095,000.00 | a) | 07/19/18 | e) | 71 CD | a) | 2,095,000.00 | a) | 100.00% | c) | 100.00% | a) | 3 | Completed as per physical accomplishment. | 1
[9 empty] | b) | Salido | b) | 10/08/18 | f) | 53 CD | b) | 2,095,000.00 | b) | - | d) | - | b) | 90 | Financial documents still on process | 1
[9 empty] | c) | PEO | c) | 11/07/18 | g) | 03/19/19 | c) | - | [7 empty] | 1
[9 empty] | d) | - | d) | 03/19/19 | [11 empty] | 1
|  |  | 1 | b | Bacali - Casig-ang - Libertad | Road |  | Admin | a) | 1,081,410.00 | a) | 07/31/18 | e) | - | a) | 1,081,410.00 | a) | 100.00% | c) | 100.00% | a) | - | Completed as per physical accomplishment. | 2
[9 empty] | b) | Toquero | b) | 10/23/18 | f) | - | b) | 1,081,410.00 | b) | - | d) | - | b) | - | Financial documents still on process | 2
[9 empty] | c) | PEO | c) | 11/30/18 | g) | 11/30/18 | c) | - | [7 empty] | 2
[9 empty] | d) | Admin | d) | - | [11 empty] | 2
|  |  | 1 | c | San Miguel - Moslog - Kinamayan | Road |  | Admin | a) | 704,740.00 | a) | 08/02/18 | e) | - | a) | 704,740.00 | a) | 100.00% | c) | 100.00% | a) | - | Completed as per physical accomplishment. | 2
[9 empty] | b) | Gamad | b) | 11/05/18 | f) | - | b) | 704,740.00 | b) | - | d) | - | b) | - | Financial documents still on process | 2
[9 empty] | c) | PEO | c) | 01/12/19 | g) | 01/12/19 | c) | - | [7 empty] | 2
[9 empty] | d) |  | d) | - | [11 empty] | 2
4 |  |  | OPPAP-PAMANA | [20 empty] | AC
|  |  | 1. Tribal Hall | [20 empty] | AC
|  |  |  | Construction of Tribal Hall, B.E. Dujali |  | Bldg. |  | Admin | a) | 500000 | a) | CY 2018 | e) | - | a) | 500000 | a) | 100% | c) | 100% | a) | 4 | Completed 5/31/2019 as per physical accomplishment. Financial Documents still on process | 2
[9 empty] | b) | Azotes | b) | 03/21/19 | f) | - | b) | 500000 | b) | - | d) | 0% | b) | 104 |  | 2
[9 empty] | c) | PEO | c) | 8/06/2019 | g) | 5/31/2019 | c) | 479480 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
1
1
|  |  |  | Construction of PWS Level II in Purok JBL and Salawao, |  | PWS |  | Admin | a) | 1000000 | a) | 08/15/18 | e) | - | a) | 1000000 | a) | 100.00% | c) | 100.00% | a) | 14 | Completed as per physical accomplishment. | 1
|  |  |  | Santo Niño, Talaingod |  |  |  |  | b) | Diosanta | b) | 12/17/18 | f) | 19 days | b) | 1000000 | b) | - | d) | - | b) | 420 | Financial documents still on process | 1
[9 empty] | c) | PEO | c) | 02/24/19 | g) | 03/15/19 | c) | 560706.67 | [7 empty] | 1
[9 empty] | d) | 89 CD | d) | 03/15/19 | [11 empty] | 1
4 |  | 4 |  | Upgrading of Existing PWS Level II in Sitio Patel 2, Gupitan, Kapalong |  | PWS |  | Admin | a) | 2500000 | a) | 8/14/2019 | e) | - | a) | 2500000 | a) |  | c) | 100% | a) | - | Completed as per Physical Accomplishment. Financial Documents on process | 1
4 | [8 empty] | b) | Diosanta | b) | 3/25/2019 | f) | - | b) | 2500000 | b) |  | d) |  | b) | - |  | 1
4 | [8 empty] | c) | PEO | c) | 7/19/2019 | g) | 09/30/2019 | c) | - | [7 empty] | 1
4 | [8 empty] | d) | - | d) | - | [11 empty] | 1
4 |  | R. | LOCAL GOVERNMENT SUPPORT FUND (LGSF) CY 2018 | [20 empty] | AC
4 |  |  | 1 | Road Upgrading of San Vicente - Butay Provincial Road |  | Road |  | Contract | a) | 19949581.18 | a) | CY 2018 | e) | - | a) | 19949581.18 | a) | 100% | c) | 100% | a) | 18 | Completed as per Physical Accomplishment. Financial Documents on process | 1
4 | [8 empty] | b) | Aclaracion | b) | 11/19/18 | f) | 28 CD | b) | 19949581.18 | b) | 100% | d) | 0% | b) | 396 |  | 1
4 | [8 empty] | c) | Alpha & Omega | c) | 06/08/19 | g) | 06/26/2019 | c) | 9,685,667.31 | [7 empty] | 1
4 | [8 empty] | d) | 202 CD | d) | 07/06/19 | [11 empty] | 1
|  | F. | Supplemental Budget No. 2 CY 2018 | [20 empty] | AC
|  |  | Const/Coml/Impvt of Various Gov't Bldgs., Structures | [20 empty] | AC
|  |  | & Facilities (Const. in Progress - Bldgs and Other Structures) | [20 empty] | AC
AC
|  |  |  | Const. of Provincial Training Center, Ph.II, |  | Bldg. |  | Admin | a) | 1,250,000.00 | a) | 07/05/18 | e) | - | a) | 1,250,000.00 | a) | 100.00% | c) | 100% | a) | 10 | Completed 6/28/2019 as per physical accomplishment. Financial Documents still on process | 2
|  |  |  | Brgy. Kinawitnon, IGACOS |  |  |  |  | b) | Porras | b) | 11/05/18 | f) | 63 CD | b) | 1,250,000.00 | b) | 100.00% | d) | 0% | b) | 200 |  | 2
[9 empty] | c) | PEO | c) | 12/23/18 | g) | 06/28/2019 | c) | 860,218.02 | [7 empty] | 2
[9 empty] | d) | 177 CD | d) | 04/30/19 | [11 empty] | 2
|  |  |  | Upgrading of DAGOEMC Multi-Purpose |  | Bldg. |  | - | a) | 3,000,000.00 | a) | 09/04/18 | e) | - | a) | 3,000,000.00 | a) | 30.28% | c) | 30.28% | a) | 7 | Completed as per physical accomplishment. | 1
|  |  |  | Bldg., Mankilam |  |  |  |  | b) | Chua | b) | 03/04/19 | f) | - | b) | 3,000,000.00 | b) | - | d) | +0.36% | b) | 210 | Financial documents still on process | 1
[9 empty] | c) | PEO | c) | 07/26/19 | g) | - | c) | 1,537,217.00 | [7 empty] | 1
[9 empty] | d) | 145 CD | d) | - | [11 empty] | 1
|  |  |  | Const. of 1 Unit Triball Hall, Brgy. Carcor, |  | Bldg. | 86.40 sq.m | Admin | a) | 680,000.00 | a) | 11/22/18 | e) | - | a) | 680,000.00 | a) | 100.00% | c) | 100.00% | a) | 16 | Completed as per physical accomplishment. | 1
|  |  |  | New Corella |  |  |  |  | b) | Gone | b) | 02/01/19 | f) | 14 CD | b) | 680,000.00 | b) | - | d) | - | b) | 160 | Financial documents still on process | 1
[9 empty] | c) | PEO | c) | 04/01/19 | g) | 04/15/19 | c) | 551,946.14 | [7 empty] | 1
[9 empty] | d) | - | d) | 04/15/19 | [11 empty] | 1
|  |  |  | Const/Compl. Of Fence at bahay |  | Fence |  | - | a) | 2,500,000.00 | a) | 08/28/18 | e) | - | a) | 2,500,000.00 | a) | 100.00% | c) | 100.00% | a) | 17 | Completed as per physical accomplishment. | 1
|  |  |  | Pag-Asa for Minors, New Corella |  |  |  |  | b) | Gone | b) | 01/19/19 | f) | 20 CD | b) | 2,500,000.00 | b) | - | d) | - | b) | 323 | Financial documents still on process | 1
[9 empty] | c) | PEO | c) | 03/06/19 | g) | 05/25/19 | c) | 2,150,422.85 | [7 empty] | 1
[9 empty] | d) | 110 CD | d) | 05/25/19 | [11 empty] | 1
|  |  | 2 Infastructure Augmentation Project (Provincial Counterpart for PRDP Project) | [20 empty] | AC
AC
|  |  |  | Rehab. Of Capungagan-Bdy. San Miguel |  | Road |  | Admin | a) | 4,990,000.000 | a) | 07/20/18 | e) | - | a) | 4,990,000.000 | a) | 100.00% | c) | 100.00% | a) | 6 | Completed as per physical accomplishment. | 1
|  |  |  | FMR (Variation Order) |  |  |  |  | b) | Avila | b) | 08/23/18 | f) | 86 CD | b) | 4,990,000.000 | b) | - | d) | - | b) | 180 | Financial documents still on process | 1
[9 empty] | c) | PEO | c) | 01/13/19 | g) | 03/30/19 | c) | 4879151.58 | [7 empty] | 1
[9 empty] | d) | 134 CD | d) | 03/30/19 | [11 empty] | 1
| II. PROJECTS UNDER THE CURRENT APPROPRIATION CY 2019 | [22 empty] | AP
| A.1 GENERAL FUND CY 2019 | [6 empty] | MBA/CBRMC | a) | 18127866 | a) | 01/03/19 | e) | - | a) | 18127866 | a) | 83.63 | c) | 83.83 | a) | 46 | See list of Provincial Roads | AP
| Road ID |  | Maintenance of Various Provincial Roads and Bridges at District 1 |  |  | Road Maintenance | KM |  | b) | Paraguya | b) | 01/03/19 | f) | - | b) | 18127866 | b) | - | d) | - | b) | 920 |  | FS
[7 empty] | 288.26 |  | c) | PEO/CBRMC | c) | 12/31/19 | g) | - | c) | - | [7 empty] | AC
| 11DAN | [9 empty] | d) | - | [11 empty] | AC
[9 empty] | d) | 261 days | d) | - | [11 empty] | AC
|  |  | Jct. Highway Magatos - New Bantayan |  |  | Road Maintenance | 7.1 | MBA | a) | 287307.39 | a) | 01/03/19 | e) | - | a) | 287307.39 | a) | 100% | c) | 100% | a) | 15 | Completed | AC
| 001 | [7 empty] | b) | Crucio | b) | 01/16/19 | f) | - | b) | 287307.39 | b) | - | d) | - | b) | 480 |  | 1
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 118693.58 | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | Jct. Highway Magatos - New Bantayan |  |  | Road Maintenance | 7.1 | CBRMC | a) | 223674.22 | a) | 01/03/19 | e) | - | a) | 223674.22 | a) | 100% | c) | 100% | a) | 16 | Completed | 1
| 001 | [7 empty] | b) | Crucio | b) | 3/22/19 | f) | - | b) | 223674.22 | b) | - | d) | - | b) | 480 |  | 1
[9 empty] | c) | CALAFA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
|  |  | Magatos-Bdry Pagsabangan |  |  | Road Maintenance | 8.33 | MBA | a) | 328740.25 | a) | 01/03/19 | e) | - | a) | 328740.25 | a) | 100% | c) | 100% | a) | 15 | Completed | 1
| 002 | [7 empty] | b) | Crucio | b) | 01/03/19 | f) | - | b) | 328740.25 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 207258.49 | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | Magatos-Bdry Pagsabangan |  |  | Road Maintenance | 8.33 | CBRMC | a) | 270763.53 | a) | 01/03/19 | e) | - | a) | 270763.53 | a) | 100% | c) | 100% | a) | 16 | Completed | 1
| 002 | [7 empty] | b) | Crucio | b) | 03/22/19 | f) | - | b) | 270763.53 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | CALAFA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
|  |  | Ilog-New Bantayan |  |  | Road Maintenance | 2.68 | MBA | a) | 131131.39 | a) | 01/03/19 | e) | - | a) | 131131.39 | a) | 100% | c) | 100% | a) | 15 | Completed | 1
| 003 | [7 empty] | b) | Crucio | b) | 01/16/19 | f) | - | b) | 131131.39 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 49,316.69 | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | Ilog-New Bantayan |  |  | Road Maintenance | 2.68 | CBRMC | a) | 65925.03 | a) | 01/03/19 | e) | - | a) | 65925.03 | a) | 100% | c) | 100% | a) | 16 | Completed | 1
| 003 | [7 empty] | b) | Crucio | b) | 03/22/19 | f) | - | b) | 65925.03 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | CALAFA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
|  |  | Asuncion -Monte Carlo-Del Pilar |  |  | Road Maintenance | 9.93 | MBA | a) | 474102.88 | a) | 01/03/19 | e) | - | a) | 474102.88 | a) | 100% | c) | 100% | a) | 15 | Completed | 1
| 005 | [7 empty] | b) | Crucio | b) | 01/03/19 | f) | - | b) | 474102.88 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 240274.49 | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | Asuncion -Monte Carlo-Del Pilar |  |  | Road Maintenance | 9.93 | CBRMC | a) | 355524.28 | a) | 01/03/19 | e) | - | a) | 355524.28 | a) | 100% | c) | 100% | a) | 16 | Completed
| 005 | [7 empty] | b) | Crucio | b) | 03/22/19 | f) | - | b) | 355524.28 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | MAHAYAHAY IFA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
|  |  | Jct. Highway Canatan-Jct. Highway Magatos |  |  | Road Maintenance | 4.85 | MBA | a) | 209808.59 | a) | 01/03/19 | e) | - | a) | 209808.59 | a) | 100% | c) | 100% | a) | 15 | Completed | 1
| 006 | [7 empty] | b) | Crucio | b) | 02/18/19 | f) | - | b) | 209808.59 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 80652.8 | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | Jct. Highway Canatan-Jct. Highway Magatos |  |  | Road Maintenance | 4.85 | CBRMC | a) | 162458.12 | a) | 01/03/19 | e) | - | a) | 162458.12 | a) | 100% | c) | 100% | a) | 16 | Completed | 1
| 006 | [7 empty] | b) | Crucio | b) | 03/22/19 | f) | - | b) | 162458.12 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | CAMODA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
1
|  |  | Sta. Felomina-San Roque |  |  | Road Maintenance | 7.68 | MBA | a) | 147439.63 | a) | 01/03/19 | e) | - | a) | 147439.63 | a) | 100% | c) | 100% | a) | 15 | Completed
| 008 | [7 empty] | b) | Crucio | b) | 01/16/19 | f) | - | b) | 147439.63 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 63806.67 | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | Sta. Felomina-San Roque |  |  | Road Maintenance | 7.68 | CBRMC | a) | 261345.67 | a) | 01/03/19 | e) | - | a) | 261345.67 | a) | 100% | c) | 100% | a) | 16 | Completed | 1
| 008 | [7 empty] | b) | Crucio | b) | 03/25/19 | f) | - | b) | 261345.67 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | STAFFA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
|  |  | Saug-Sonlon-Bdy Longanapan |  |  | Road Maintenance | 11.6 | MBA | a) | 568486.36 | a) | 01/03/19 | e) | - | a) | 568486.36 | a) | 100% | c) | 100% | a) | 15 | Completed | 1
| 010 | [7 empty] | b) | Crucio | b) | 01/16/19 | f) | - | b) | 568486.36 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 262900.22 | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | Saug-Sonlon-Bdy Longanapan |  |  | Road Maintenance | 11.6 | CBRMC | a) | 185565.56 | a) | 01/03/19 | e) | - | a) | 185565.56 | a) | 100% | c) | 100% | a) | 16 | Completed | 1
| 010 | [7 empty] | b) | Crucio | b) | 03/26/19 | f) | - | b) | 185565.56 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | BINANCIAN LIVESTOCK AFA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
|  |  | Jct. New Visayas-Buan |  |  | Road Maintenance | 2.99 | MBA | a) | 79238.27 | a) | 01/03/19 | e) | - | a) | 79238.27 | a) | 100% | c) | 100% | a) | 15 | Completed | 1
| 011 | [7 empty] | b) | Crucio | b) | 02/18/19 | f) | - | b) | 79238.27 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 14682.85 | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | Jct. New Visayas-Buan |  |  | Road Maintenance | 2.99 | CBRMC | a) | 101242.01 | a) | 01/03/19 | e) | - | a) | 101242.01 | a) | 100% | c) | 100% | a) | 16 | Completed | 1
| 011 | [7 empty] | b) | Crucio | b) | 03/22/19 | f) | - | b) | 101242.01 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | BUAN IFA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
|  |  | San Vicente - Butay |  |  | Road Maintenance | 7.52 | MBA | a) | 209624.2 | a) | 01/03/19 | e) | - | a) | 209624.2 | a) | 100% | c) | 100% | a) | 15 | Completed | 1
| 013 | [7 empty] | b) | Crucio | b) | 02/18/19 | f) | - | b) | 209624.2 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 56,080.29 | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | San Vicente - Butay |  |  | Road Maintenance | 7.52 | CBRMC | a) | 227205.88 | a) | 01/03/19 | e) | - | a) | 227205.88 | a) | 100% | c) | 100% | a) | 16 | Completed | 1
| 013 | [7 empty] | b) | Crucio | b) | 03/27/19 | f) | - | b) | 227205.88 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | SVMODA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
|  |  | Jct. Highway Doña Andrea - Capungagan |  |  | Road Maintenance | 8.7 | MBA | a) | 230835.16 | a) | 01/03/19 | e) | - | a) | 230835.16 | a) | 100% | c) | 100% | a) | 15 | Completed | 1
| 014 | [7 empty] | b) | Crucio | b) | 02/18/19 | f) | - | b) | 230835.16 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 60,629.26 | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
1
|  |  | Jct. Highway Doña Andrea - Capungagan |  |  | Road Maintenance | 8.7 | CBRMC | a) | 294308.14 | a) | 01/03/19 | e) | - | a) | 294308.14 | a) | 100% | c) | 100% | a) | 16 | Completed
| 014 | [7 empty] | b) | Crucio | b) | 03/28/19 | f) | - | b) | 294308.14 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | CAPUNGAGAN MPC | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
|  |  | Semong-Palma Gil |  |  | Road Maintenance | 2.73 | MBA | a) | 147289.98 | a) | 01/03/19 | e) | - | a) | 147289.98 | a) | 100% | c) | 100% | a) | 15 | Completed | 1
| 018 | [7 empty] | b) | Crucio | b) | 02/18/19 | f) | - | b) | 147289.98 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 71745.43 | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
1
|  |  | Semong-Palma Gil |  |  | Road Maintenance | 2.73 | CBRMC | a) | 49186.05 | a) | 01/03/19 | e) | - | a) | 49186.05 | a) | 100% | c) | 100% | a) | 16 | Completed
| 018 | [7 empty] | b) | Crucio | b) | 03/22/19 | f) | - | b) | 49186.05 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | PALMA GIL FA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
|  |  | Daligdigon - Dagohoy |  |  | Road Maintenance | 3.34 | MBA | a) | 148835.45 | a) | 01/03/19 | e) | - | a) | 148835.45 | a) | 100% | c) | 100% | a) | - | Completed | 1
| 020 | [7 empty] | b) | Crucio | b) | - | f) | - | b) | 148835.45 | b) | - | d) | - | b) | - |  | 1
[9 empty] | c) | PEO | c) | - | g) | 2019-12-31 | c) | - | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | Daligdigon - Dagohoy |  |  | Road Maintenance | 3.34 | CBRMC | a) | 68279.5 | a) | 01/03/19 | e) | - | a) | 68279.5 | a) | 100% | c) | 100% | a) | 16 | Completed | 1
| 020 | [7 empty] | b) | Crucio | b) | 03/22/19 | f) | - | b) | 68279.5 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | PALMA GIL FA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
|  |  | Jct. Sampao-Bdry. Mamacao |  |  | Road Maintenance | 4.98 | MBA | a) | 154200.78 | a) | 01/03/19 | e) | - | a) | 154200.78 | a) | 100% | c) | 100% | a) | 15 | Completed | 1
| 025 | [7 empty] | b) | Crucio | b) | 02/18/19 | f) | - | b) | 154200.78 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 24,296.87 | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | Jct. Sampao-Bdry. Mamacao |  |  | Road Maintenance | 4.98 | CBRMC | a) | 169521.51 | a) | 01/03/19 | e) | - | a) | 169521.51 | a) | 100% | c) | 100% | a) | 16 | Completed | 1
| 025 | [7 empty] | b) | Crucio | b) | 03/26/19 | f) | - | b) | 169521.51 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | AMS KAPALONG | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
|  |  | Jct. Highway Luna-Mamacao-Narra |  |  | Road Maintenance | 9.17 | MBA | a) | 357957.66 | a) | 01/03/19 | e) | - | a) | 357957.66 | a) | 100% | c) | 100% | a) | 15 | Completed | 1
| 026 | [7 empty] | b) | Crucio | b) | 02/18/19 | f) | - | b) | 357957.66 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 127,996.16 | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | Jct. Highway Luna-Mamacao-Narra |  |  | Road Maintenance | 9.17 | CBRMC | a) | 313143.91 | a) | 01/03/19 | e) | - | a) | 313143.91 | a) | 100% | c) | 100% | a) | 16 | Completed | 1
| 026 | [7 empty] | b) | Crucio | b) | 03/26/19 | f) | - | b) | 313143.91 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | AMS KAPALONG | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
|  |  | Jct. Gabuyan-Katipunan-Bucana |  |  | Road Maintenance | 5.89 | MBA | a) | 294403.23 | a) | 01/03/19 | e) | - | a) | 294403.23 | a) | 100% | c) | 100% | a) | 15 | Completed | 1
| 027 | [7 empty] | b) | Crucio | b) | 02/18/19 | f) | - | b) | 294403.23 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 126,179.97 | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | Jct. Gabuyan-Katipunan-Bucana |  |  | Road Maintenance | 5.89 | CBRMC | a) | 129495.6 | a) | 01/03/19 | e) | - | a) | 129495.6 | a) | 100% | c) | 100% | a) | 16 | Completed | 1
| 027 | [7 empty] | b) | Crucio | b) | 03/26/19 | f) | - | b) | 129495.6 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | MANGULIBAS FA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
|  |  | Capungagan-Mabuhay-Pandulian |  |  | Road Maintenance | 5.57 | MBA | a) | 294917.73 | a) | 01/03/19 | e) | - | a) | 294917.73 | a) | 100% | c) | 100% | a) | 15 | Completed | 1
| 028 | [7 empty] | b) | Crucio | b) | 02/18/19 | f) | - | b) | 294917.73 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
1
|  |  | Capungagan-Mabuhay-Pandulian |  |  | Road Maintenance | 5.57 | CBRMC | a) | 105950.95 | a) | 01/03/19 | e) | - | a) | 105950.95 | a) | 100% | c) | 100% | a) | 16 | Completed
| 028 | [7 empty] | b) | Crucio | b) | 03/28/19 | f) | - | b) | 105950.95 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | CAPUNGAGAN MPC | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
|  |  | Florida - New Boholano |  |  | Road Maintenance | 2.54 | MBA | a) | 95863.17 | a) | 01/03/19 | e) | - | a) | 95863.17 | a) | 100% | c) | 100% | a) | 15 | Completed | 1
| 030 | [7 empty] | b) | Crucio | b) | 02/18/19 | f) | - | b) | 95863.17 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 31,418.99 | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | Florida - New Boholano |  |  | Road Maintenance | 2.54 | CBRMC | a) | 47425.27 | a) | 01/03/19 | e) | - | a) | 47425.27 | a) | 100% | c) | 100% | a) | 16 | Completed | 1
| 030 | [7 empty] | b) | Crucio | b) | 03/28/19 | f) | - | b) | 47425.27 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | SUPRA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
|  |  | Jct. New Boholano - New Loon |  |  | Road Maintenance | 4.77 | MBA | a) | 140549.84 | a) | 01/03/19 | e) | - | a) | 140549.84 | a) | 100% | c) | 100% | a) | 15 | Completed | 1
| 031 | [7 empty] | b) | Crucio | b) | 02/18/19 | f) | - | b) | 140549.84 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 40,056.38 | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | Jct. New Boholano - New Loon |  |  | Road Maintenance | 4.77 | CBRMC | a) | 169521.51 | a) | 01/03/19 | e) | - | a) | 169521.51 | a) | 100% | c) | 100% | a) | 16 | Completed | 1
| 031 | [7 empty] | b) | Crucio | b) | 03/28/19 | f) | - | b) | 169521.51 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | NEW LOON FA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
|  |  | Florida-Suaon-Jct. Gupitan |  |  | Road Maintenance | 15.57 | MBA | a) | 707038.05 | a) | 01/03/19 | e) | - | a) | 707038.05 | a) | 100% | c) | 100% | a) | 15 | Completed | 1
| 032 | [7 empty] | b) | Crucio | b) | 01/16/19 | f) | - | b) | 707038.05 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 226,.062.60 | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | Florida-Suaon-Jct. Gupitan |  |  | Road Maintenance | 15.57 | CBRMC | a) | 419094.85 | a) | 01/03/19 | e) | - | a) | 419094.85 | a) | 100% | c) | 100% | a) | 16 | Completed | 1
| 032 | [7 empty] | b) | Crucio | b) | 03/28/19 | f) | - | b) | 419094.85 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | SUPRA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
|  |  | Km. 15, Kipalili-New Loon |  |  | Road Maintenance | 6.93 | MBA | a) | 367659.97 | a) | 01/03/19 | e) | - | a) | 367659.97 | a) | 100% | c) | 100% | a) | 15 | Completed | 1
| 034 | [7 empty] | b) | Crucio | b) | 02/01/19 | f) | - | b) | 367659.97 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 112,175.78 | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | Km. 15, Kipalili-New Loon |  |  | Road Maintenance | 6.93 | CBRMC | a) | 237801.01 | a) | 01/03/19 | e) | - | a) | 237801.01 | a) | 100% | c) | 100% | a) | 16 | Completed | 1
| 034 | [7 empty] | b) | Crucio | b) | 03/26/19 | f) | - | b) | 237801.01 | b) | - | d) | - | b) | 480 |  | 1
[9 empty] | c) | KIPALILI FA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
|  |  | Jct. Suaon-Libuton |  |  | Road Maintenance | 7.26 | MBA | a) | 44015.68 | a) | 01/03/19 | e) | - | a) | 44015.68 | a) | 100% | c) | 100% | a) | 15 | Completed
| 035 | [7 empty] | b) | Crucio | b) | 01/16/19 | f) | - | b) | 44015.68 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 24,980.86 | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | Jct. Suaon-Libuton |  |  | Road Maintenance | 7.26 | CBRMC | a) | 91664.91 | a) | 01/03/19 | e) | - | a) | 91664.91 | a) | 100% | c) | 100% | a) | 16 | Completed | 1
| 035 | [7 empty] | b) | Crucio | b) | 03/22/19 | f) | - | b) | 91664.91 | b) | - | d) | - | b) | 480 |  | 1
[9 empty] | c) | AALLI | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
1
|  |  | Datu Balong - Pinamuno |  |  | Road Maintenance | 2.74 | MBA | a) | 95458.24 | a) | 01/03/19 | e) | - | a) | 95458.24 | a) | 100% | c) | 100% | a) | 15 | Completed
| 040 | [7 empty] | b) | Crucio | b) | 03/01/19 | f) | - | b) | 95458.24 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 12,625.00 | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | Datu Balong - Pinamuno |  |  | Road Maintenance | 2.74 | CBRMC | a) | 63570.57 | a) | 01/03/19 | e) | - | a) | 63570.57 | a) | 100% | c) | 100% | a) | 16 | Completed | 1
| 040 | [7 empty] | b) | Crucio | b) | 03/28/19 | f) | - | b) | 63570.57 | b) | - | d) | - | b) | 480 |  | 1
[9 empty] | c) | DATU BALONG FA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
|  |  | Sawata - Mamangan - Pinamuno |  |  | Road Maintenance | 14.48 | MBA | a) | 545390.17 | a) | 01/03/19 | e) | - | a) | 545390.17 | a) | 100% | c) | 100% | a) | 15 | Completed | 1
| 041 | [7 empty] | b) | Crucio | b) | 02/01/19 | f) | - | b) | 545390.17 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 196,076.60 | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | Sawata - Mamangan - Pinamuno |  |  | Road Maintenance | 14.48 | CBRMC | a) | 508564.54 | a) | 01/03/19 | e) | - | a) | 508564.54 | a) | 100% | c) | 100% | a) | 16 | Completed | 1
| 041 | [7 empty] | b) | Crucio | b) | 03/22/19 | f) | - | b) | 508564.54 | b) | - | d) | - | b) | 480 |  | 1
[9 empty] | c) | SAWATA DFA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
|  |  | Igangon - Sawata |  |  | Road Maintenance | 9.66 | MBA | a) | 497447.77 | a) | 01/03/19 | e) | - | a) | 497447.77 | a) | 100% | c) | 100% | a) | 15 | Completed | 1
| 042 | [7 empty] | b) | Crucio | b) | 02/01/19 | f) | - | b) | 497447.77 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | Igangon - Sawata |  |  | Road Maintenance | 9.66 | CBRMC | a) | 197775.1 | a) | 01/03/19 | e) | - | a) | 197775.1 | a) | 100% | c) | 100% | a) | 16 | Completed | 1
| 042 | [7 empty] | b) | Crucio | b) | 03/22/19 | f) | - | b) | 197775.1 | b) | - | d) | - | b) | 480 |  | 1
[9 empty] | c) | SAWATA DFA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
|  |  | New Corella - Sto. Niño - Macgum |  |  | Road Maintenance | 17.11 | MBA | a) | 606294.08 | a) | 01/03/19 | e) | - | a) | 606294.08 | a) | 100% | c) | 100% | a) | 15 | Completed | 1
| 044 | [7 empty] | b) | Crucio | b) | 01/03/19 | f) | - | b) | 606294.08 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 246,619.77 | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | New Corella - Sto. Niño - Macgum |  |  | Road Maintenance | 17.11 | CBRMC | a) | 308434.97 | a) | 01/03/19 | e) | - | a) | 308434.97 | a) | 100% | c) | 100% | a) | 16 | Completed | 1
| 044 | [7 empty] | b) | Crucio | b) | 03/26/19 | f) | - | b) | 308434.97 | b) | - | d) | - | b) | 480 |  | 1
[9 empty] | c) | SAN ISIDRO FA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
|  |  | Tagaytay - Buan |  |  | Road Maintenance | 4.92 | MBA | a) | 173197.37 | a) | 01/03/19 | e) | - | a) | 173197.37 | a) | 100% | c) | 100% | a) | 15 | Completed | 1
| 045 | [7 empty] | b) | Crucio | b) | 03/18/19 | f) | - | b) | 173197.37 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 26254.58 | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | Tagaytay - Buan |  |  | Road Maintenance | 4.92 | CBRMC | a) | 131850.07 | a) | 01/03/19 | e) | - | a) | 131850.07 | a) | 100% | c) | 100% | a) | 16 | Completed | 1
| 045 | [7 empty] | b) | Crucio | b) | 03/22/19 | f) | - | b) | 131850.07 | b) | - | d) | - | b) | 480 |  | 1
[9 empty] | c) | BUAN IFA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
|  |  | limbaan - Sto. Niño |  |  | Road Maintenance | 3.19 | MBA | a) | 153706.77 | a) | 01/03/19 | e) | - | a) | 153706.77 | a) | 100% | c) | 100% | a) | 15 | Completed | 1
| 049 | [7 empty] | b) | Crucio | b) | 03/01/19 | f) | - | b) | 153706.77 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 32534.49 | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | limbaan - Sto. Niño |  |  | Road Maintenance | 3.19 | CBRMC | a) | 53657.51 | a) | 01/03/19 | e) | - | a) | 53657.51 | a) | 100% | c) | 100% | a) | - | Completed | 1
| 049 | [7 empty] | b) | Crucio | b) | - | f) | - | b) | 53657.51 | b) | - | d) | - | b) | - |  | 1
[9 empty] | c) | - | c) | - | g) | 2019-12-31 | c) | - | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | Del Pilar - Jct. Silangan |  |  | Road Maintenance | 4.17 | MBA | a) | 187097.4 | a) | 01/03/19 | e) | - | a) | 187097.4 | a) | 100% | c) | 100% | a) | 15 | Completed | 1
| 051 | [7 empty] | b) | Crucio | b) | 03/18/19 | f) | - | b) | 187097.4 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 94181.74 | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | Del Pilar - Jct. Silangan |  |  | Road Maintenance | 4.17 | CBRMC | a) | 113014.34 | a) | 01/03/19 | e) | - | a) | 113014.34 | a) | 100% | c) | 100% | a) | 16 | Completed | 1
| 051 | [7 empty] | b) | Crucio | b) | 03/26/19 | f) | - | b) | 113014.34 | b) | - | d) | - | b) | 480 |  | 1
[9 empty] | c) | DURIAN DACUDAO | c) | 12/31/19 | g) | - | c) | - | [7 empty] | 1
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
|  |  | New Corella - New Sambog - Silangan |  |  | Road Maintenance | 5.1 | MBA | a) | 201994.35 | a) | 01/03/19 | e) | - | a) | 201994.35 | a) | 100% | c) | 100% | a) | 15 | Completed | 1
| 052 | [7 empty] | b) | Crucio | b) | 03/01/19 | f) | - | b) | 201994.35 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 63402.48 | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | New Corella - New Sambog - Silangan |  |  | Road Maintenance | 5.1 | CBRMC | a) | 131850.07 | a) | 01/03/19 | e) | - | a) | 131850.07 | a) | 100% | c) | 100% | a) | 16 | Completed | 1
| 052 | [7 empty] | b) | Crucio | b) | 03/26/19 | f) | - | b) | 131850.07 | b) | - | d) | - | b) | 480 |  | 1
[9 empty] | c) | DURIAN DACUDAO | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
|  |  | Sta. Fe - Del Monte |  |  | Road Maintenance | 3.34 | MBA | a) | 37923.51 | a) | 01/03/19 | e) | - | a) | 37923.51 | a) | 100% | c) | 100% | a) | 15 | Completed | 1
| 056 | [7 empty] | b) | Crucio | b) | 03/18/19 | f) | - | b) | 37923.51 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 36595.13 | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | Sta. Fe - Del Monte |  |  | Road Maintenance | 3.34 | CBRMC | a) | 70633.96 | a) | 01/03/19 | e) | - | a) | 70633.96 | a) | 100% | c) | 100% | a) | 16 | Completed | 1
| 056 | [7 empty] | b) | Crucio | b) | 03/21/19 | f) | - | b) | 70633.96 | b) | - | d) | - | b) | 480 |  | 1
[9 empty] | c) | DEL MONTE CACAO | c) | 12/31/19 | g) | 2019-12-31 | c) | 4,872.18 | [7 empty] | 1
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
|  |  | New Corella - New Bohol |  |  | Road Maintenance | 11.54 | MBA | a) | 356226.67 | a) | 01/03/19 | e) | - | a) | 356226.67 | a) | 100% | c) | 100% | a) | 15 | Completed
| 058 | [7 empty] | b) | Crucio | b) | 02/01/19 | f) | - | b) | 356226.67 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 110,982.71 | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | New Corella - New Bohol |  |  | Road Maintenance | 11.54 | CBRMC | a) | 190711.7 | a) | 01/03/19 | e) | - | a) | 190711.7 | a) | 100% | c) | 100% | a) | 16 | Completed | 1
| 058 | [7 empty] | b) | Crucio | b) | 03/22/19 | f) | - | b) | 190711.7 | b) | - | d) | - | b) | 480 |  | 1
[9 empty] | c) | SAN JOSE COCONUT | c) | 12/31/19 | g) | 2019-12-31 | c) | 5,847.18 | [7 empty] | 1
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
1
|  |  | Jct. Carcor - Prk. 9 Bagsak |  |  | Road Maintenance | 2.5 | MBA | a) | 108618.49 | a) | 01/03/19 | e) | - | a) | 108618.49 | a) | 100% | c. | 100% | a) | 15 | Completed
| 059 | [7 empty] | b) | Crucio | b) | 03/01/19 | f) | - | b) | 108618.49 | b) | - | d) |  | b) | 480 |  | 1
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 79952.88 | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
1
|  |  | Jct. Carcor - Prk. 9 Bagsak |  |  | Road Maintenance | 2.5 | CBRMC | a) | 42284.76 | a) | 01/03/19 | e) | - | a) | 42284.76 | a) | 100% | c) | 100% | a) | 16 | Completed
| 059 | [7 empty] | b) | Crucio | b) | 03/22/19 | f) | - | b) | 42284.76 | b) | - | d) | - | b) | 480 |  | 1
[9 empty] | c) | CARCOR MOTOR | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
|  |  | Carcor - Jct. Kauswagan |  |  | Road Maintenance | 4.32 | MBA | a) | 264514.71 | a) | 01/03/19 | e) | - | a) | 264514.71 | a) | 100% | c) | 100% | a) | 15 | Completed | 1
| 060 | [7 empty] | b) | Crucio | b) | 03/18/19 | f) | - | b) | 264514.71 | b) | - | d) |  | b) | 450 |  | 1
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 80733.11 | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | Carcor - Jct. Kauswagan |  |  | Road Maintenance | 4.32 | CBRMC | a) | 48398.27 | a) | 01/03/19 | e) | - | a) | 48398.27 | a) | 100% | c) | 100% | a) | 16 | Completed
| 060 | [7 empty] | b) | Crucio | b) | 03/22/19 | f) | - | b) | 48398.27 | b) | - | d) | - | b) | 480 |  | 1
[9 empty] | c) | CARCOR MOTOR | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
|  |  | Del Pilar - Prk 9 Bagsak - San Jose |  |  | Road Maintenance | 4.99 | MBA | a) | 170215.76 | a) | 01/03/19 | e) | - | a) | 170215.76 | a) | 100% | c) | 100% | a) | 15 | Completed | 1
| 061 | [7 empty] | b) | Crucio | b) | 03/01/19 | f) | - | b) | 170215.76 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 87595.63 | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | Del Pilar - Prk 9 Bagsak - San Jose |  |  | Road Maintenance | 4.99 | CBRMC | a) | 223674.22 | a) | 01/03/19 | e) | - | a) | 223674.22 | a) | 100% | c) | 100% | a) | 16 | Completed | 1
| 061 | [7 empty] | b) | Crucio | b) | 03/22/19 | f) | - | b) | 223674.22 | b) | - | d) | - | b) | 480 |  | 1
[9 empty] | c) | SAN JOSE COCONUT | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
|  |  | San Juan - New Talisay |  |  | Road Maintenance | 5.13 | MBA | a) | 306261.25 | a) | 01/03/19 | e) | - | a) | 306261.25 | a) | 100% | c) | 100% | a) | 15 | Completed | 1
| 063 | [7 empty] | b) | Crucio | b) | 02/01/19 | f) | - | b) | 306261.25 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 85123.48 | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | San Juan - New Talisay |  |  | Road Maintenance | 5.13 | CBRMC | a) | 93906.31 | a) | 01/03/19 | e) | - | a) | 93906.31 | a) | 100% | c) | 100% | a) | 16 | Completed
| 063 | [7 empty] | b) | Crucio | b) | 03/26/19 | f) | - | b) | 93906.31 | b) | - | d) | - | b) | 480 |  | 1
[9 empty] | c) | NEW TALISAY IAWA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
|  |  | San Juan - kauswagan - New Cortez |  |  | Road Maintenance | 3.22 | MBA | a) | 187879.04 | a) | 01/03/19 | e) | - | a) | 187879.04 | a) | 100% | c) | 100% | a) | 15 | Completed | 1
| 064 | [7 empty] | b) | Crucio | b) | 03/18/19 | f) | - | b) | 187879.04 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 3,025.00 | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | San Juan - kauswagan - New Cortez |  |  | Road Maintenance | 3.22 | CBRMC | a) | 63298.26 | a) | 01/03/19 | e) | - | a) | 63298.26 | a) | 100% | c) | 100% | a) | 16 | Completed
| 064 | [7 empty] | b) | Crucio | b) | 03/22/19 | f) | - | b) | 63298.26 | b) | - | d) | - | b) | 480 |  | 1
[9 empty] | c) | SAN JOSE COCONUT | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
|  |  | New Bohol - Jct. El Unido |  |  | Road Maintenance | 2.12 | MBA | a) | 54989.06 | a) | 01/03/19 | e) | - | a) | 54989.06 | a) | 100% | c) | 100% | a) | 15 | Completed
| 065 | [7 empty] | b) | Crucio | b) | 03/01/19 | f) | - | b) | 54989.06 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 21021.99 | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | New Bohol - Jct. El Unido |  |  | Road Maintenance | 2.12 | CBRMC | a) | 58861.64 | a) | 01/03/19 | e) | - | a) | 58861.64 | a) | 100% | c) | 100% | a) | 16 | Completed | 1
| 065 | [7 empty] | b) | Crucio | b) | 03/26/19 | f) | - | b) | 58861.64 | b) | - | d) | - | b) | 480 |  | 1
[9 empty] | c) | MANDISKAB TRIBAL | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
1
|  |  | New Corella - El unido - Jct. Mesaoy |  |  | Road Maintenance | 8.63 | MBA | a) | 388002.46 | a) | 01/03/19 | e) | - | a) | 388002.46 | a) | 100% | c) | 100% | a) | 15 | Completed
| 066 | [7 empty] | b) | Crucio | b) | 02/11/19 | f) | - | b) | 388002.46 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 58142.76 | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | New Corella - El unido - Jct. Mesaoy |  |  | Road Maintenance | 8.63 | CBRMC | a) | 233092.08 | a) | 01/03/19 | e) | - | a) | 233092.08 | a) | 100% | c) | 100% | a) | 16 | Completed | 1
| 066 | [7 empty] | b) | Crucio | b) | 03/26/19 | f) | - | b) | 233092.08 | b) | - | d) | - | b) | 480 |  | 1
[9 empty] | c) | MANDISKAB TRIBAL | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
|  |  | Mesaoy - Dasing |  |  | Road Maintenance | 1.39 | MBA | a) | 29749.5 | a) | 01/03/19 | e) | - | a) | 29749.5 | a) | 100% | c) | 100% | a) | 15 | Completed | 1
| 067 | [7 empty] | b) | Crucio | b) | 03/18/19 | f) | - | b) | 29749.5 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 10000 | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | Mesaoy - Dasing |  |  | Road Maintenance | 1.39 | CBRMC | a) | 54152.71 | a) | 01/03/19 | e) | - | a) | 54152.71 | a) | 100% | c) | 100% | a) | 16 | Completed | 1
| 067 | [7 empty] | b) | Crucio | b) | 03/26/19 | f) | - | b) | 54152.71 | b) | - | d) | - | b) | 480 |  | 1
[9 empty] | c) | MANDISKAB TRIBAL | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
|  |  | Jct. San Juan - Jct. Mesaoy |  |  | Road Maintenance | 1.82 | MBA | a) | 106788.95 | a) | 01/03/19 | e) | - | a) | 106788.95 | a) | 100% | c) | 100% | a) | 15 | Completed | 1
| 068 | [7 empty] | b) | Crucio | b) | 03/01/19 | f) | - | b) | 106788.95 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 17502.68 | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | Jct. San Juan - Jct. Mesaoy |  |  | Road Maintenance | 1.82 | CBRMC | a) | 35180.83 | a) | 01/03/19 | e) | - | a) | 35180.83 | a) | 100% | c) | 100% | a) | 16 | Completed | 1
| 068 | [7 empty] | b) | Crucio | b) | 03/26/19 | f) | - | b) | 35180.83 | b) | - | d) | - | b) | 480 |  | 1
[9 empty] | c) | MANDISKAB TRIBAL | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
|  |  | Mesaoy - Jct. Mahayahay |  |  | Road Maintenance | 4.6 | MBA | a) | 146984.46 | a) | 01/03/19 | e) | - | a) | 146984.46 | a) | 100% | c) | 100% | a) | 15 | Completed | 1
| 069 | [7 empty] | b) | Crucio | b) | 03/18/19 | f) | - | b) | 146984.46 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 7618.27 | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | Mesaoy - Jct. Mahayahay |  |  | Road Maintenance | 4.6 | CBRMC | a) | 160103.65 | a) | 01/03/19 | e) | - | a) | 160103.65 | a) | 100% | c) | 100% | a) | 16 | Completed
| 069 | [7 empty] | b) | Crucio | b) | 03/22/19 | f) | - | b) | 160103.65 | b) | - | d) | - | b) | 480 |  | 1
[9 empty] | c) | MAHAYAHAY IFA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
|  |  | Mesaoy - New bohol |  |  | Road Maintenance | 5.36 | MBA | a) | 165361.13 | a) | 01/03/19 | e) | - | a) | 165361.13 | a) | 100% | c) | 100% | a) | 15 | Completed
| 070 | [7 empty] | b) | Crucio | b) | 03/01/19 | f) | - | b) | 165361.13 | b) | - | d) | - | b) | 480 |  | 1
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 2543.9 | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | Mesaoy - New bohol |  |  | Road Maintenance | 5.36 | CBRMC | a) | 224851.45 | a) | 01/03/19 | e) | - | a) | 224851.45 | a) | 100% | c) | 100% | a) | 16 | Completed
| 070 | [7 empty] | b) | Crucio | b) | 03/26/19 | f) | - | b) | 224851.45 | b) | - | d) | - | b) | 480 |  | 1
[9 empty] | c) | MANDISKAB TRIBAL | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
|  |  | Bdry. Tagum - Baca - New Corella |  |  | Road Maintenance | 13.01 | MBA | a) | 217182.9 | a) | 01/03/19 | e) | - | a) | 217182.9 | a) | 100% | c) | 100% | a) | 15 | Completed | 1
| 071 | [7 empty] | b) | Crucio | b) | 03/18/19 | f) | - | b) | 217182.9 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 19550 | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | Bdry. Tagum - Baca - New Corella |  |  | Road Maintenance | 13.01 | CBRMC | a) | 214256.36 | a) | 01/03/19 | e) | - | a) | 214256.36 | a) | 100% | c) | 100% | a) | 16 | Completed | 1
| 071 | [7 empty] | b) | Crucio | b) | 03/26/19 | f) | - | b) | 214256.36 | b) | - | d) | - | b) | 480 |  | 1
[9 empty] | c) | DURIAN DACUDAO | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
|  |  | Prk. 1, Maunlom - Prk. 6 Maunlom Road |  |  | Road Maintenance | 3.56 | MBA | a) | 150912.87 | a) | 01/03/19 | e) | - | a) | 150912.87 | a) | 100% | c) | 100% | a) | 15 | Completed | 1
| 147 | [7 empty] | b) | Crucio | b) | 03/01/19 | f) | - | b) | 150912.87 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 23025 | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | Prk. 1, Maunlom - Prk. 6 Maunlom Road |  |  | Road Maintenance | 3.56 | CBRMC | a) | 63973.36 | a) | 01/03/19 | e) | - | a) | 63973.36 | a) | 100% | c) | 100% | a) | 16 | Completed | 1
| 147 | [7 empty] | b) | Crucio | b) | 03/22/19 | f) | - | b) | 63973.36 | b) | - | d) | - | b) | 480 |  | 1
[9 empty] | c) | THE BEST VEGETABLE | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
1
|  |  | New Visayas - Binancian |  |  | Road Maintenance | 7.77 | MBA | a) | 14814.34 | a) | 01/03/19 | e) | - | a) | 14814.34 | a) | 100% | c) | 100% | a) | 15 | Completed
| 149 | [7 empty] | b) | Crucio | b) | 03/18/19 | f) | - | b) | 14814.34 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 5,000.00 | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | New Visayas - Binancian |  |  | Road Maintenance | 7.77 | CBRMC | a) | 129495.6 | a) | 01/03/19 | e) | - | a) | 129495.6 | a) | 100% | c) | 100% | a) | 16 | Completed | 1
| 149 | [7 empty] | b) | Crucio | b) | 03/22/19 | f) | - | b) | 129495.6 | b) | - | d) | - | b) | 480 |  | 1
[9 empty] | c) | BUAN IFA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
|  |  | Datu Balong - Prk. Mamalian |  |  | Road Maintenance | 3.46 | MBA | a) | 117454.89 | a) | 01/03/19 | e) | - | a) | 117454.89 | a) | 100% | c) | 39.37% | a) | 15 | Completed | 1
| 150 | [7 empty] | b) | Crucio | b) | 03/18/19 | f) | - | b) | 117454.89 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 10115 | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | Datu Balong - Prk. Mamalian |  |  | Road Maintenance | 3.46 | CBRMC | a) | 59264.42 | a) | 01/03/19 | e) | - | a) | 59264.42 | a) | 100% | c) | 100% | a) | 16 | Completed | 1
| 150 | [7 empty] | b) | Crucio | b) | 03/28/19 | f) | - | b) | 59264.42 | b) | - | d) | - | b) | 480 |  | 1
[9 empty] | c) | DATU BALONG FA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
| A.2 GENERAL FUND CY 2019 |  |  |  |  | Road Maintenance | KM | MBA/CBRMC | a) | 11,618,834.00 | a) | 01/03/19 | e) | - | a) | 11,618,834.00 | a) | 66% | c) | 66% | a) | 42 | See list of Provincial Roads
| Road ID |  | 1. Maintenance Of Various Prov'l. Roads and Bridges Dist 2 |  |  |  | 288.26 |  | b) | Matuguinas | b) | 01/03/19 | f) | - | b) | 11,618,834.00 | b) | - | d) | - | b) | 924 |  | FS
[9 empty] | c) | PEO/CBRMC | c) | 12/31/19 | g) | - | c) | - | [7 empty] | AC
| 11DAN | [9 empty] | d) | - | [11 empty] | AC
[9 empty] | d) | 261 days | d) | - | [11 empty] | AC
|  |  | Cebulano - Mangalcal |  |  | Road Maintenance | 4.17 | MBA | a) | 142161.87 | a) | 01/03/19 | e) | - | a) | 142161.87 | a) | 100% | c) | 100% | a) | 9 | Completed | AC
|  | 073 | [6 empty] | b) | Clar | b) | 2019-01-15 | f) | - | b) | 142161.87 | b) | - | d) | - | b) | 18 |  | 2
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 118,609.29 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | Tubod - basa - Mangalcal |  |  | Road Maintenance | 3.93 | MBA | a) | 156875.9 | a) | 01/03/19 | e) | - | a) | 156875.9 | a) | 100% | c) | 100% | a) | 9 | Completed | 2
| 074 | [7 empty] | b) | Clar | b) | 2019-01-15 | f) | - | b) | 156875.9 | b) | - | d) | - | b) | 18 |  | 2
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 143,372.65 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | Upper Mangalcal - Lower Mangalcal |  |  | Road Maintenance | 2.43 | CBRMC | a) | 79237.14 | a) | 01/03/19 | e) | - | a) | 79237.14 | a) | 100% | c) | 100% | a) | 9 | Completed | 2
| 078 | [7 empty] | b) | Clar | b) | 2019-01-14 | f) | - | b) | 79237.14 | b) | - | d) | - | b) | 27 |  | 2
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 69,430.97 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | Jct. Highway Carmen - Mangalcal - Tubod |  |  | Road Maintenance | 11.34 | MBA | a) | 463135.67 | a) | 01/03/19 | e) | - | a) | 463135.67 | a) | 100% | c) | 100% | a) | 9 | Completed | 2
| 082 | [7 empty] | b) | Clar | b) | 01/10/19 | f) | - | b) | 463135.67 | b) | - | d) | - | b) | 45 |  | 2
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 170,106.43 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | Jct. Highway Carmen - Mangalcal - Tubod |  |  | Road Maintenance | 11.34 | CBRMC | a) | 253557.37 | a) | 01/03/19 | e) | - | a) | 253557.37 | a) | 100% | c) | 100% | a) | 10 | Completed | 2
| 082 | [7 empty] | b) | Maligro | b) | 03/25/19 | f) | - | b) | 253557.37 | b) | - | d) | - | b) | 40 |  | 2
[9 empty] | c) | TUBOD CENTRO LOWER IRRIGATORS ASSOCIATION | c) | 09/25/19 | g) | 2019-12-31 | c) | - | [7 empty] | 2
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 2
|  |  | Jct. Highway Sto. Niño - Kabanlakan - La Paz |  |  | Road Maintenance | 2.13 | MBA | a) | 76067.88 | a) | 01/03/19 | e) | - | a) | 76067.88 | a) | 100% | c) | 100% | a) | 9 | Completed | 2
| 084 | [7 empty] | b) | Clar | b) | 01/10/19 | f) | - | b) | 76067.88 | b) | - | d) | - | b) | 45 |  | 2
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 66,477.91 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | Ising - Sto Niño |  |  | Road Maintenance | 2.07 | CBRMC | a) | 82413.14 | a) | 01/03/19 | e) | - | a) | 82413.14 | a) | 100% | c) | 100% | a) | 5 | Completed | 2
| 085 | [7 empty] | b) | Clar | b) | 01/17/19 | f) | - | b) | 82413.14 | b) | - | d) | - | b) | 15 |  | 2
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 27,093.24 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | Ising - Sadpodon - Taba - Dila -Dila |  |  | Road Maintenance | 5.68 | MBA | a) | 248941.33 | a) | 01/03/19 | e) | - | a) | 248941.33 | a) | 100% | c) | 100% | a) | 9 | Completed | 2
| 086 | [7 empty] | b) | Clar | b) | 01/12/19 | f) | - | b) | 248941.33 | b) | - | d) | - | b) | 27 |  | 2
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 82,329.02 | [7 empty] | 2
[9 empty] | d) | - | d) | - |  |  |  | . | [7 empty] | 2
2
|  |  | Tuganay - taba |  |  | Road Maintenance | 4.27 | CBRMC | a) | 291377.9 | a) | 01/03/19 | e) | - | a) | 291377.9 | a) | 70% | c) | 70% | a) | 9 | Completed
| 087 | [7 empty] | b) | Clar | b) | 01/09/19 | f) | - | b) | 291377.9 | b) | - | d) | - | b) | 27 |  | 2
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 12/31/2019 | c) | 238,412.28 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | Jct. Highway Tuganay - Taba |  |  | Road Maintenance | 4.4 | MBA | a) | 32972.82 | a) | 01/03/19 | e) | - | a) | 32972.82 | a) | 65% | c) | 65% | a) | 9 | Completed | 2
| 088 | [7 empty] | b) | Clar | b) | 01/22/19 | f) | - | b) | 32972.82 | b) | - | d) | - | b) | 18 |  | 2
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 12/31/2019 | c) | 22,639.09 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | Jct. Highway Ising - Magsaysay |  |  | Road Maintenance | 10.84 | CBRMC | a) | 417818.12 | a) | 01/03/19 | e) | - | a) | 417818.12 | a) | 60% | c) | 60% | a) | 10 | Completed | 2
| 089 | [7 empty] | b) | Clar | b) | 01/22/19 | f) | - | b) | 417818.12 | b) | - | d) | - | b) | 50 |  | 2
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 12/31/2019 | c) | 313,488.39 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | New Camiling - Alejal - Lower Magsaysay |  |  | Road Maintenance | 6.73 | MBA | a) | 240878.08 | a) | 01/03/19 | e) | - | a) | 240878.08 | a) | 80% | c) | 80% | a) | 4 | Completed | 2
| 091 | [7 empty] | b) | Clar | b) | 01/22/19 | f) | - | b) | 240878.08 | b) | - | d) | - | b) | 20 |  | 2
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 12/31/2019 | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | Jct. highway Tuganay - Anibongan |  |  | Road Maintenance | 3.66 | CBRMC | a) | 150684.44 | a) | 01/03/19 | e) | - | a) | 150684.44 | a) | 100% | c) | 100% | a) | 6 | Completed | 2
| 094 | [7 empty] | b) | Clar | b) | 01/22/19 | f) | - | b) | 150684.44 | b) | - | d) | - | b) | 18 |  | 2
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 12/31/2019 | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | Anibongan - Guadalupe |  |  | Road Maintenance | 2.48 | MBA | a) | 91325.06 | a) | 01/03/19 | e) | - | a) | 91325.06 | a) | 100% | c) | 100% | a) | 9 | Completed | 2
| 095 | [7 empty] | b) | Clar | b) | 01/23/19 | f) | - | b) | 91325.06 | b) | - | d) | - | b) | 18 |  | 2
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 12/31/2019 | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | Tuganay - Anibongan - San Isidro |  |  | Road Maintenance | 7.22 | CBRMC | a) | 139979.8 | a) | 01/03/19 | e) | - | a) | 139979.8 | a) | 100% | c) | 100% | a) | 9 | Completed | 2
| 096 | [7 empty] | b) | Clar | b) | 01/24/19 | f) | - | b) | 139979.8 | b) | - | d) | - | b) | 36 |  | 2
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 12/31/2019 | c) | 1890.37 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | Jct. Anibongan - Prk. 2, 7, 5, San Isidro |  |  | Road Maintenance | 3.14 | MBA | a) | 104378.03 | a) | 01/03/19 | e) | - | a) | 104378.03 | a) | 100% | c) | 100% | a) | 10 | Completed | 2
| 097 | [7 empty] | b) | Clar | b) | 01/24/19 | f) | - | b) | 104378.03 | b) | - | d) | - | b) | 20 |  | 2
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 12/31/2019 | c) | 56,087.50 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | Anibongan - Salvacion - Cabay-angan |  |  | Road Maintenance | 6.93 | CBRMC | a) | 415461.61 | a) | 01/03/19 | e) | - | a) | 415461.61 | a) | 100% | c) | 100% | a) | 9 | Completed | 2
| 098 | [7 empty] | b) | Clar | b) | 01/25/19 | f) | - | b) | 415461.61 | b) | - | d) | - | b) | 45 |  | 2
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 12/31/2019 | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | Jct. Highway Guadalupe - Bdry. Tagum |  |  | Road Maintenance | 7.9 | MBA | a) | 456131.09 | a) | 01/03/19 | e) | - | a) | 456131.09 | a) | 100% | c) | 100% | a) | 9 | Completed | 2
| 101 | [7 empty] | b) | Clar | b) | 01/25/19 | f) | - | b) | 456131.09 | b) | - | d) | - | b) | 18 |  | 2
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 12/31/2019 | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | Jct. Highway Guadalupe - Bdry. Tagum |  |  | Road Maintenance | 7.9 | CBRMC | a) | 228201.66 | a) | 01/03/19 | e) | - | a) | 228201.66 | a) | 100% | c) | 100% | a) | 8 | Completed | 2
| 101 | [7 empty] | b) | Maligro | b) | 03/25/19 | f) | - | b) | 228201.66 | b) | - | d) | - | b) | 40 |  | 2
[9 empty] | c) | LAMPIA PAG-ASA IRRIGATORS ASSOCIATION, INC. | c) | 12/25/19 | g) | 12/31/2019 | c) | - | [7 empty] | 2
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 2
|  |  | Poblacion Dujali - Prk. 8 Dujali |  |  | Road Maintenance | 8.2 | MBA | a) | 285600.05 | a) | 01/03/19 | e) | - | a) | 285600.05 | a) | 100% | c) | 100% | a) | 10 | Completed | 2
| 105 | [7 empty] | b) | Clar | b) | 01/28/19 | f) | - | b) | 285600.05 | b) | - | d) | - | b) | 50 |  | 2
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 12/31/2019 | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | Dujali - San Isidro |  |  | Road Maintenance | 3 | CBRMC | a) | 130319.3 | a) | 01/03/19 | e) | - | a) | 130319.3 | a) | 100% | c) | 100% | a) | 8 | Completed | 2
| 107 | [7 empty] | b) | Gamad | b) | 01/28/19 | f) | - | b) | 130319.3 | b) | - | d) | - | b) | 30 |  | 2
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 12/31/2019 | c) | 45,943.12 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | Prk. 5, RJS - Prk. 6 New Casay |  |  | Road Maintenance | 2.73 | MBA | a) | 235277 | a) | 01/03/19 | e) | - | a) | 235277 | a) | 100% | c) | 100% | a) | 2 | Completed | 2
| 109 | [7 empty] | b) | Gamad | b) | 01/28/19 | f) | - | b) | 235277 | b) | - | d) | - | b) | 6 |  | 2
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 12/31/2019 | c) | 90,745.35 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | Prk. 5 - Prk. 1 Pawas Dujali |  |  | Road Maintenance | 2.18 | CBRMC | a) | 76067.68 | a) | 01/03/19 | e) | - | a) | 76067.68 | a) | 100% | c) | 100% | a) | 10 | Completed | 2
| 112 | [7 empty] | b) | Gamad | b) | 01/18/19 | f) | - | b) | 76067.68 | b) | - | d) | - | b) | 20 |  | 2
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 12/31/2019 | c) | 40,112.50 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | Dujali - Balisong - Magupising |  |  | Road Maintenance | 5.52 | MBA | a) | 260591.93 | a) | 01/03/19 | e) | - | a) | 260591.93 | a) | 100% | c) | 100% | a) | 4 | Completed | 2
| 113 | [7 empty] | b) | Gamad | b) | 01/09/19 | f) | - | b) | 260591.93 | b) | - | d) | - | b) | 8 |  | 2
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 12/31/2019 | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | Dujali - Pawas - San Vicente |  |  | Road Maintenance | 4.42 | CBRMC | a) | 139536.42 | a) | 01/03/19 | e) | - | a) | 139536.42 | a) | 100% | c) | 100% | a) | 10 | Completed | 2
| 117 | [7 empty] | b) | Gamad | b) | 01/22/19 | f) | - | b) | 139536.42 | b) | - | d) | - | b) | 18 |  | 2
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 12/31/2019 | c) | 52,133.86 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | Jct. Salvacion - San Vicente - Cabay-angan |  |  | Road Maintenance | 3.45 | MBA | a) | 247460.9 | a) | 01/03/19 | e) | - | a) | 247460.9 | a) | 100% | c) | 100% | a) | 10 | Completed | 2
| 118 | [7 empty] | b) | Gamad | b) | 01/23/19 | f) | - | b) | 247460.9 | b) | - | d) | - | b) | 18 |  | 2
[9 empty] | c) | PEO | c) | 02/31/19 | g) | 12/31/2019 | c) | 151,887.50 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | Jct. Salvacion - San Vicente - Cabay-angan |  |  | Road Maintenance | 3.45 | CBRMC | a) | 152134.44 | a) | 01/03/19 | e) | - | a) | 152134.44 | a) | 100% | c) | 100% | a) | 8 | Completed | 2
| 118 | [7 empty] | b) | Gamad | b) | 03/26/19 | f) | - | b) | 152134.44 | b) | - | d) | - | b) | 36 |  | 2
[9 empty] | c) | BALISONG SAN VICENTE IRRIGATORS ASSOCIATION | c) | 12/26/19 | g) | 12/31/2019 | c) | [8 empty] | 2
[9 empty] | d) | 3 quarters | d) | - | [10 empty] | Completed | 2
|  |  | Dujali - San Miguel |  |  | Road Maintenance | 3.95 | MBA | a) | 101202.04 | a) | 01/03/19 | e) | - | a) | 101202.04 | a) | 80% | c) | 90% | a) | 11 |  | 2
| 119 | [7 empty] | b) | Gamad | b) | 01/10/19 | f) | - | b) | 101202.04 | b) | - | d) | - | b) | 22 |  | 2
[9 empty] | c) | PEO | c) | 12/31/19 | g) | - | c) | 90,350.03 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | San Miguel - Casig-ang |  |  | Road Maintenance | 2.55 | CBRMC | a) | 79237.14 | a) | 01/03/19 | e) | - | a) | 79237.14 | a) | 100% | c) | 100% | a) | 10 | Completed | 2
| 122 | [7 empty] | b) | Gamad | b) | 01/24/19 | f) | - | b) | 79237.14 | b) | - | d) | - | b) | 10 |  | 2
[9 empty] | c) | BALISONG SAN VICENTE IRRIGATORS ASSOCIATION | c) | 12/31/19 | g) | 12/31/2019 | c) | 40,112.50 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | Prk. Magsaysay - Lunga-og - Dalisay |  |  | Road Maintenance | 2.81 | MBA | a) | 79762.14 | a) | 01/03/19 | e) | - | a) | 79762.14 | a) | 100% | c) | 100% | a) | 8 | Completed | 2
| 127 | [7 empty] | b) | Gamad | b) | 01/30/19 | f) | - | b) | 79762.14 | b) | - | d) | - | b) | 8 |  | 2
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 12/31/2019 | c) | 40,612.50 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | Prk. Apitong - Upper Balisong - Dalisay |  |  | Road Maintenance | 4.6 | CBRMC | a) | 137846.03 | a) | 01/03/19 | e) | - | a) | 137846.03 | a) | 100% | c) | 100% | a) | 8 | Completed | 2
| 128 | [7 empty] | b) | Gamad | b) | 01/31/19 | f) | - | b) | 137846.03 | b) | - | d) | - | b) | 8 |  | 2
[9 empty] | c) | BALISONG SAN VICENTE IRRIGATORS ASSOCIATION | c) | 12/31/19 | g) | 12/31/2019 | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | Sitio Paradise - Magkakaisa - Esperanza |  |  | Road Maintenance | 1.75 | MBA | a) | 66552.75 | a) | 01/03/19 | e) | - | a) | 66552.75 | a) | 100% | c) | 100% | a) | 8 | Completed | 2
| 129 | [7 empty] | b) | 79762.14 | b) | 01/22/19 | f) | - | b) | 66552.75 | b) | - | d) | - | b) | 8 |  | 2
[9 empty] | c) | Gamad | c) | 12/31/19 | g) | 12/31/2019 | c) | 22,246.26 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | Los Amigos 1 - Esperanza - Los Amigos 2 |  |  | Road Maintenance | 3.59 | CBRMC | a) | 101202.04 | a) | 01/03/19 | e) | - | a) | 101202.04 | a) | 100% | c) | 100% | a) | 10 | Completed | 2
| 130 | [7 empty] | b) | Gamad | b) | 01/24/19 | f) | - | b) | 101202.04 | b) | - | d) | - | b) | 20 |  | 2
[9 empty] | c) | BALISONG SAN VICENTE IRRIGATORS ASSOCIATION | c) | 12/31/19 | g) | 12/31/2019 | c) | 50,837.50 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | Mugas - Lunga-og |  |  | Road Maintenance | 2.68 | MBA | a) | 66552.75 | a) | 01/03/19 | e) | - | a) | 91,693.64 | a) | 100% | c) | 100% | a) | 6 | Completed | 2
| 132 | [7 empty] | b) | 79762.14 | b) | 01/17/19 | f) | - | b) | 91,693.64 | b) | - | d) | - | b) | 24 |  | 2
[9 empty] | c) | Gamad | c) | 12/31/19 | g) | 12/31/2019 | c) | 50,837.50 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | Pantaron - Mugas |  |  | Road Maintenance | 3.35 | CBRMC | a) | 101202.04 | a) | 01/03/19 | e) | - | a) | 101202.04 | a) | 100% | c) | 100% | a) | 9 | Completed | 2
| 133 | [7 empty] | b) | Gamad | b) | 01/23/19 | f) | - | b) | 101202.04 | b) | - | d) | - | b) | 18 |  | 2
[9 empty] | c) | BALISONG SAN VICENTE IRRIGATORS ASSOCIATION | c) | 12/31/19 | g) | 12/31/2019 | c) | 90,349.93 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | Sto. Tomas - Bdry. Mamacao |  |  | Road Maintenance | 4.9 | MBA | a) | 110710.44 | a) | 01/03/19 | e) | - | a) | 110710.44 | a) | 100% | c) | 100% | a) | 10 | Completed | 2
| 135 | [7 empty] | b) | 79762.14 | b) | 01/21/19 | f) | - | b) | 110710.44 | b) | - | d) | - | b) | 40 |  | 2
[9 empty] | c) | Gamad | c) | 12/31/19 | g) | 12/31/2019 | c) | 50,837.50 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | Fd. Rd. 3 - San Jose |  |  | Road Maintenance | 4.55 | CBRMC | a) | 147367.49 | a) | 01/03/19 | e) | - | a) | 147367.49 | a) | 100% | c) | 100% | a) | 10 | Completed | 2
| 136 | [7 empty] | b) | Gamad | b) | 01/25/19 | f) | - | b) | 147367.49 | b) | - | d) | - | b) | 30 |  | 2
[9 empty] | c) | BALISONG SAN VICENTE IRRIGATORS ASSOCIATION | c) | 12/31/19 | g) | 12/31/2019 | c) | 56,174.69 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | Menzi - balagunan - Tulalian |  |  | Road Maintenance | 10.63 | MBA | a) | 520167.79 | a) | 01/03/19 | e) | - | a) | 520167.79 | a) | 100% | c) | 100% | a) | 6 | Completed | 2
| 138 | [7 empty] | b) | 79762.14 | b) | 01/07/19 | f) | - | b) | 520167.79 | b) | - | d) | - | b) | 18 |  | 2
[9 empty] | c) | Gamad | c) | 12/31/19 | g) | 12/31/2019 | c) | 204,850.57 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | Jct. Bdry. Tagum - Talomo |  |  | Road Maintenance | 12.01 | CBRMC | a) | 407429.19 | a) | 01/03/19 | e) | - | a) | 407429.19 | a) | 100% | c) | 100% | a) | 10 | Completed | 2
| 145 | [7 empty] | b) | Gamad | b) | 01/11/19 | f) | - | b) | 407429.19 | b) | - | d) | - | b) | 50 |  | 2
[9 empty] | c) | BALISONG SAN VICENTE IRRIGATORS ASSOCIATION | c) | 12/31/19 | g) | 12/31/2019 | c) | 168,544.84 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | San Jose - Sitio Mahayahay, Magwawa |  |  | Road Maintenance | 0.84 | MBA | a) | 7919.35 | a) | 01/03/19 | e) | - | a) | 7919.35 | a) | 100% | c) | 100% | a) | 2 | Completed | 2
| 151 | [7 empty] | b) | 79762.14 | b) | 01/16/19 | f) | - | b) | 7919.35 | b) | - | d) | - | b) | 8 |  | 2
[9 empty] | c) | Gamad | c) | 12/31/19 | g) | 12/31/2019 | c) | 1,509.27 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| B. 20% DEVELOPMENT FUND CY 2019 | [22 empty] | FS
| Road ID |  | 1. Rehabilitation Of Various Prov'l. Roads and Bridges Dist. 1 |  |  | Road Rehabilitation | KM | MBA | a) | 41465029 | a) | 01/03/19 | e) | - | a) | 41465029 | a) | - | c) | - | a) | 46 | See list of Provincial Roads | FS
[7 empty] | 109.55 |  | b) | Paraguya | b) | 01/03/19 | f) | - | b) | 41465029 | b) | - | d) | - | b) | 920 |  | AC
| 11DAN | [7 empty] | c) | PEO | c) | 12/31/19 | g) | - | c) | - | [7 empty] | AC
[11 empty] | d) | - | [11 empty] | AC
[9 empty] | d) | 261 days | d) | - | [11 empty] | AC
[6 empty] | Road Rehabilitation |  |  | a. )P 500,000.00 |  | a.) 01/31/19 |  |  |  | a.) 500,000.00 | [8 empty] | 1
|  |  | Purok 10 Pob. Road, New Corella | [7 empty] | b.) Feb. 16, 2019 |  |  |  | b.) 500,000.00 | [7 empty] | Completed
g.) Feb. 28, 2019
[6 empty] | Road Rehabilitation |  |  | a.)1,815,000.00 |  | a.) 01/31/19 |  |  |  | a.) 1,815,000.00
|  |  | Purok 7 Pob- Jct. New Sambog | [7 empty] | b.)March 1, 2019 |  |  |  | b.) 1,815,000.00 | [7 empty] | Completed
g.) May 15, 2019
[6 empty] | Road Rehabilitation |  |  | a.) 1,389,000.00 |  | a.) 01/31/19 |  |  |  | a.) 1,389,000.00 | [7 empty] | Completed with a savings of P303,898.08 furtherance and is for implementation
|  |  | Del Pilar- El Unido Road | [5 empty] | b.) Fabian |  | b.) March 18,2019 |  |  |  | a.) 1,389,000.00
g.) May 8, 2019
SUPPLEMENTAL BUDGET NO 4 CY 2019 / CONTINUING APPROPRIATION
[9 empty] | a.) 7,742,775.95 | [5 empty] | a.) 7,742,775.95 | [7 empty] | Waiting for the delivery of materials
|  |  | Impvt. of Km. 9 Sagayen - Sawata Provincial Road Phase II | [5 empty] | b.) Kenny | [5 empty] | b.) 7,742,775.95
| Road ID |  | 1. Rehabilitation Of Various Prov'l. Roads and Bridges Dist 2 |  |  | Road Rehabilitation | KM | Admin | a) | 46740117 | a) | 01/03/19 | [10 empty] | See list of Provincial Roads
[7 empty] | 115.62 |  | b) | Matuguinas | b) | - | [11 empty] | AC
| 11DAN | [7 empty] | c) | PEO | c) | - | [11 empty] | AC
[11 empty] | d) | - | [11 empty] | AC
[9 empty] | d) | 261 days | d) | - | [11 empty] | AC
[6 empty] | Road Rehabilitation |  |  | a.) 515,000.00 |  | a.) 03/12/19 |  |  |  | a.) 515,000.00 | [8 empty] | 2
|  |  | Jct. Highway -Tubod - Bagong Silang | [5 empty] | b.) Clar |  | b.) March 18, 2019 |  |  |  | b.) 515,000.00 | [7 empty] | Completed
g.) June 15, 2019
[6 empty] | Road Rehabilitation |  |  | a.) 390,000.00 |  | a.) 03/12/19 |  |  |  | a.) 390,000.00 | [8 empty] | 2
|  |  | Cebulano- Luceta | [5 empty] | b.) Clar |  | b.) March 8, 2019 |  |  |  | b.) 390,000.00 | [7 empty] | Completed
g.) June 15, 2019
[6 empty] | Road Rehabilitation |  |  | a.) 295,000.00 |  | a.) 03/12/19 |  |  |  | a.) 295,000.00
|  |  | Lower Asuncion - Upper Asuncion | [5 empty] | b.) Clar |  | b.) March 18, 2019 |  |  |  | b.) 295,000.00 | [7 empty] | Completed
g.) June 15, 2019
[6 empty] | Road Rehabilitation |  |  | a.) 1,220,000.00 |  | a.) 03/12/19 |  |  |  | a.) 1,220,000.00
|  |  | Jct. Highway - Sto. Nino - La Paz - San Vicente | [5 empty] | b.)Obar |  | b.) March 18, 2019 |  |  |  | b.) 1,220,000.00 | [7 empty] | Completed
g.) Sept. 30, 2019
|  |  | Alejal - Alemag |  |  | Road Rehabilitation | 1.79 |  | a) | 970000 | a) | 2019-03-18 | e) | - | a) | 970000 | a) | 100% | c) | 100% | a) | 7 | Completed. Financially completed
| 092 | [7 empty] | b) | Gamad/Clar | b) | 2019-05-20 | f) | - | b) | 970000 | b) | 100 | d) | 0% | b) | 20 |  | 2
[9 empty] | c) | - | c) | 2019-09-12 | g) | Sept. 30, 2019 | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
[6 empty] | Road Rehabilitation |  |  | a.) 640,000.00 |  | a.) 03/12/19 |  |  |  | a.) 640,000.00 | [8 empty] | 2
|  |  | Mabaus - Cabay -angan | [5 empty] | b.)Clar |  | b.) Maech 18, 2019 |  |  |  | a.) 640,000.00 | [7 empty] | Completed
g.) July 30, 2019
[6 empty] | Road Rehabilitation |  |  | a.) 280,000.00 |  | a.) 03/12/19 |  |  |  | a.) 280,000.00
|  |  | Mabaus - Salvacion | [5 empty] | b.)Clar |  | b.) March 18, 2019 |  |  |  | a.) 280,000.00
[13 empty] | g.) June 30, 2019 | [9 empty] | Completed
|  |  | Dujali - New Casay |  |  |  | 3.2 | Admin | a) | 640000 | a) | 2019-05-16 | e) | - | a) | 640000 | a) | 100% | c) | 100% | a) | 10 |  | 2
| 106 | [7 empty] | b) | Gamad/Clar | b) | 2019-06-17 | f) | 40 | b) | 640000 | b) |  | d) | - | b) | 40 | Completed | 2
[9 empty] | c) | - | c) |  | g) | 10/15/2019 | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
[6 empty] | Road Rehabilitation |  |  | a.) 450,000.00 |  | a.) 03/12/19 |  |  |  | a.) 450,000.00 | [8 empty] | 2
|  |  | New Casay - Bugtong Talisay | [5 empty] | b.)Clar |  | b.) March 18, 2019 |  |  |  | a.) 450,000.00 | [7 empty] | Completed
g.)June 30, 2019
[6 empty] | Road Rehabilitation |  |  | a.)220,000.00 |  | a.) 03/12/19 |  |  |  | a.)220,000.00 |  | a.) 100 % |  | c.)100% |  |  |  |  | 2
|  |  | Purok 6 Cabay-angan - Esti | [5 empty] | b.) Gamad |  | b.) March 18, 2019 |  |  |  | a.)220,000.00 | [7 empty] | Completed
g.) June 30, 2019
[6 empty] | Road Rehabilitation |  |  | a.)250,000.00 |  | a.) March 12, 2019 | [5 empty] | a.) 100 % |  | c.)100%
|  |  | Dujali - Sitio Pawas | [5 empty] | b.) Gamad |  | b.) March 18, 2019 | [11 empty] | Completed
g.) Jun 30, 2019
[6 empty] | Road Rehabilitation |  |  | a.) 280,000.00 |  | a.) March 12, 2019 | [5 empty] | a.) 100 % |  | c.)100%
|  |  | Purok 1 to Purok 2 Sitio Pawas | [6 empty] | b.) Gamad | b.) March 18, 2019 | [11 empty] | Completed
g.) Jun 30, 2019
|  |  | San Miguel - Crossing Kinamayan |  |  | Road Rehabilitation | 2.8 | Admin | a) | 560000 | a) | 2019-06-25 | e) | - | a) | 560000 | a.) 100 % |  | c.)100% |  | a) | -
| 120 | [7 empty] | b) | Nasol | b) | Sept. 19, 2019 | f) | - | b) | 560000 | b) | - | d) | - | b) | - | Completed | 2
[9 empty] | c) | - | c) | - | g) | Nov. 30, 2019 | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | Kinamayan - Lunga-og |  |  | Road Rehabilitation | 2.59 | Admin | a) | 520000 | a) | 2019-03-18 | e) | - | a) | 520000 | a) | 100% | c) | 100% | a) | 9 | Completed | 2
| 126 | [7 empty] | b) | Gamad/Clar | b) | 5/202/019 | f) | - | b) | 520000 | b) | - | d) | - | b) | 36 |  | 2
[9 empty] | c) | - | c) |  | g) | Sept. 30, 2019 | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
[9 empty] | a.) 540,000.00 |  | a.) March 12, 2019 |  |  |  | a.) 540,000.00 |  | a.)100% |  | c.)100% |  |  |  | Completed
|  |  | Nafco - Bobongon |  |  | Road Rehabilitation |  |  | b. Gamad |  | b.) march 18, 2019 |  |  |  | b.) 540,000.00
g.) June 30, 2019
2
|  |  | Prk. Narafil - Prk. Daisy Magupising |  |  | Road Rehabilitation | 19.16 | Admin | a) | 300117 | a) | 2019-06-25 | e) | - | a) | 300117 | a) | 100% | c) | 100% | a) | - | Completed | 2
| 148 | [7 empty] | b) | Gamad/Clar | b) | Sept. 16, 2019 | f) | - | b) | 300117 | b) | - | d) | - | b) | - |  | 2
[9 empty] | c) | - | c) | - | g) | Oct. 18, 2019 | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 2. Various of Local Roads & Drainage Development Project (Provincewide) |  |  |  |  | Road Drainage rehabiliated |  | Admin | a) | 15000000 | [12 empty] | See projects listed below | 2
[9 empty] | b) | Paraguya | [13 empty] | AC
[9 empty] | c) | PEO | [13 empty] | AC
[9 empty] | d) | - | [13 empty] | AC
|  |  | Rehab. of Anibongan-Salvacion-Cabay-angan Provincial Road with Drainage |  |  | Road Drainage rehabiliated | - | - | a) | 2000000 | a) | 2019-01-14 | e) | - | a) | 2000000 | a) | 100% | c) | 100% | a) | 1 | Completed | 2
| 2.1 | [7 empty] | b) | Toquero | b) | 2019-05-22 | f) | - | b) | 2000000 | b) | - | d) | - | b) | 4 | Fiancial obligation still on process | 2
[9 empty] | c) | PEO | c) | 2019-08-04 | g) | Dec. 31, 2019 | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | Rehab./Impv't. of Sto. Tomas-Bdry. Mamacao Provincial Road |  |  | Road Drainage rehabiliated | - | Admin | a) | 1500000 | a) | 2019-01-14 | e) | - | a) | 1500000 | a) | 100% | c) | 100% | a) | - | Completed Financial obligation on process
| 2.4 | [7 empty] | b) | Toquero | b) | 2019-05-31 | f) | 60 | b) | 1500000 | b) | - | d) | - | b) | - |  | 2
[9 empty] | c) | PEO | c) | 2019-07-15 | g) | Dec. 31, 2019 | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 4. Various Government Buildings and Facilities Development Project (Provincewide) |  |  |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of recipients | - | Admin | a) | 27000000 | [12 empty] | See projects listed below | 2
[9 empty] | b) | Medalla | [13 empty] | AC
[9 empty] | c) | PEO | [13 empty] | AC
[9 empty] | d) | - | [13 empty] | AC
|  |  | Const. of GYM Bleacher at Suaybaguio Rina, Elem. School |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of recipients | - | #REF! | a) | 1000000 | a) | - | e) | - | a) | 1000000 | a) | 100% | c) | 100% | a) | - | Completed | 1
|  | 11 | [6 empty] | b) | Mayang | b) | 6/3/2019 | f) | - | b) | 1000000 | b) | 64 | d) | 0% | b) | - |  | 1
[9 empty] | c) | PEO | c) | 8/01/2019 | g) |  | c) | - | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
| 5. Stimulus Projects for Various Barangays a. 20% Development Fund CY 2019 |  |  |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | Admin | a) | 41500000 | [12 empty] | See projects listed below | 2
[9 empty] | b) | Medalla | [13 empty] | AC
[9 empty] | c) | PEO | [13 empty] | AC
[9 empty] | d) | - | [13 empty] | AC
AC
| IGCS | [22 empty] | 2
| 5.42 |  | Rehab. Of Health Center, Aumbay, IGCS |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) | Feb. 28, 2019 | e) | - | a) | 500000 | a) |  | c) | 48.32% | a) | 3 | Completed Financial obligation on process | AC
[9 empty] | b) | Pacquiao | b) | 7/10/2019 | f) | - | b) | 500000 | b) | - | d) |  | b) | 15 |  | 2
[9 empty] | c) | Admin | c) | 10/7/2019 | g) | - | c) | - | [7 empty] | 2
[9 empty] | d) | 90 CD | d) | - | [11 empty] | 2
| 5.46 |  | Rehab. Of Brgy. Health Center, Mambago-A, IGCS |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) | Feb. 28, 2019 | e) | - | a) | 500000 | a) |  | c) | 75.61% | a) | 3 | Completed Financial obligation on process | 2
[9 empty] | b) | Ganaba | b) | 07/2019 | f) | - | b) | 500000 | b) |  | d) |  | b) | 15 |  | 2
[9 empty] | c) | Admin | c) | 8/23/2019 | g) | - | c) | - | [7 empty] | 2
[9 empty] | d) | 45 CD | d) | - | [11 empty] | 2
| 6. Rural Electrification Project (Provincewide) |  |  |  |  | Powerlines/posts installed & rehabilitated | - | - | a) | 5000000 | [12 empty] | See projects listed below | 2
[9 empty] | b) | Kim Pao Lu | [13 empty] | AC
[9 empty] | c) | - | [13 empty] | AC
[9 empty] | d) | - | [13 empty] | AC
C. 5% CALAMITY FUND CY 2019
| 3 |  | Improvement of roads, drainage and canal |  |  | Protection dikes/slope protection | - | - | a) | 3000000 | [12 empty] | See projects listed below | 2
[9 empty] | b) | Paraguya | [13 empty] | AC
[9 empty] | c) | PEO | [13 empty] | AC
[9 empty] | d) | - | [13 empty] | AC
| a. |  | Rehab./Impv't. of New Casay-Bugtong Talisay Provincial Road (Ph.II) |  |  | creeks and canRoads/Draiange/canals rehab/improved | - | - | a) | 500000 | a) | 2019-03-12 | e) | - | a) | 500000 | a) | 100% | c) | 100% | a) | 12 | Completed | AC
[9 empty] | b) | Toquero | b) | 2019-05-30 | f) | - | b) | 500000 | b) | - | d) | - | b) | 120 |  | 2
[9 empty] | c) | Admin | c) | 2019-07-30 | g) |  | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | Mark | Municipality/City |  | Color
|  |  | 1 | Asuncion |  | Red
|  |  | 2 | B.E. Dujali |  | Yellow
|  | GF- GENERAL FUND | 3 | Carmen |  | Blue | [10 empty] | TF - TRUST FUND (NATIONAL FUNDED PROJECT)
|  | 20% DF - 20% DEV'T. FUND | 4 | Kapalong |  | Pink | [10 empty] | a) SLRF - Special Local Road Fund
|  | 5% CF - 5% CALAMITY FUND | 5 | New Corella |  | Gray | [10 empty] | b) KALSADA - Konkreto at Ayos na Lansangan Tungo sa Pangkalahatang Kaunlaran
|  | CO - CAPITAL OUTLAY | 6 | San Isidro |  | Orange | [10 empty] | c) PRDP - Philippine Rural Development Projects
|  | CONG. FUND - CONGRESSIONAL FUND | 7 | Sto Tomas |  | Sky Blue | [10 empty] | d) SELAP - Support to Emergency and Livelihood Assistance Project
|  |  | 8 | Talaingod |  | Violet | [10 empty] | e) PAMANA - Payapa at Masaganang Pamayanan
|  | SEF - SPECIAL EDUCATIONAL UFND | 9 | Panabo City |  | Brown | [10 empty] | f) CBRMC - Community Based Road Maintenance Contracting
|  |  | 10 | IGACOS |  | Yellow Green | [10 empty] | g) MBC - Maintenance by Contract
|  |  | 11 | Tagum City |  | Green | [10 empty] | h) PCF-Performance Challenge Fund-DILG
i) FMRDP - Farm to Market Road
j.) CMGP - Conditional Grant to Provinces
k.) OPAPP - Office of the President Adviser on the Peace Process
l.) LGSF-AM - Local Government Support Fund Assistance to Municipalities
| Prepared by: |  |  |  | Checked | [12 empty] | Recommending Approval
Noted
| GILBERT G. MAMBULAO JR |  |  |  | ELISA A. BARCENA | TESSIE G. ABABON | [9 empty] | JIVELLYN B. CO | [5 empty] | GLENN A. OLANDRIA
| Engineer II |  |  |  | Engineer IV- Engineering Dist 1, Area Engineer |  | Engineer IV-Engineering Dist 2, Area Engineer | [9 empty] | Asst. PG-Department Head |  |  |  |  | Provincial Engineer
[5 empty] | EDWIN S. MISA |  |  |  | MARILOU A. FORONDA
[5 empty] | Engineer IV- PDPM Division Head |  |  |  | Engineer IV- QC Division Head

## Completed_4th Quarter (hidden)
PROVINCE OF DAVAO DEL NORTE
ACCOMPLISHMENT REPORT
4th Quarter 2019
SECTOR: ECONOMIC (INFRASTRUCTURE DEV'T. PROGRAM)
OFFICE/AGENCY: PROVINCIAL ENGINEER'S OFFICE
roads | bldg | fc | ws |  | COMPLETED PROJECTS
[5 empty] | Name of Project |  |  |  |  | Type | Physical | Mode | PROJECT DATA | [5 empty] | Financial (000) |  | Physical Accomplishment |  |  |  | Employment |  | REMARKS
[10 empty] | of | Target | of | a) Project Cost |  | a) Date A lot. Rel. |  | e) # of days suspended |  | a) Program |  | a) Planned |  | c) Actual |  | Generated
[10 empty] | Project | (Descrip | Impl. | b) Project Engineer |  | b) Date Started |  | f) # of days extended |  | b) Allotment |  | b) Revised |  | d) Slippage |  | a) # of Persons
[10 empty] | (Location) | tion) |  | c) Implementor |  | c)Target Compl. Date |  | g) Date completed |  | c) Disbursement | [5 empty] | b) Man-days
[13 empty] | d) Duration |  | d) Revised Compl. Date
[5 empty] | I. | PROJECTS UNDER THE CONTINUING APPROPRIATION | [21 empty] | AC | 893809.45
[7 empty] | TRUST FUND 2017 | [20 empty] | AC
[7 empty] | Conditional Matching Grant to Provinces (CMGP) | [20 empty] | AC
1 |  |  |  | 4 |  | 8 |  | Road Upgrading of Dagohoy - Daligdigon |  | Road | 2.532 km | Contract | a) | 58048310.68 | a) | CY 2017 | e) | - | a) | 58048310.68 | a) | 100.00% | c) | 100% | a) | 16 | Completed as per Physical Accomplishment, Financial Documents on Process | 1
|  |  |  | 4 |  |  |  | Provincial Road |  |  |  |  | b) | Fabiala | b) | 01/05/18 | f) | 205 CD | b) | 58048310.68 | b) | - | d) | 0% | b) | 480 |  | 1
|  |  |  | 4 | [8 empty] | c) | PUREGOLD | c) | 11/18/18 | g) | - | c) | 29,572,637.70 | [7 empty] | 1
|  |  |  | 4 | [8 empty] | d) | 246 CD | d) | 03/31/19 | [11 empty] | 1
1 |  |  |  | 4 |  |  |  | Impv’t. of Maligaya-New Camiling Prov’l. |  | Conc. | 2.13 km | Contract. | a) | 50101614.08 | a) | CY 2017 | e) | 76 CD | a) | 57385680 | a) | 100.00% | c) | 100% | a) | 21 | Completed based on POW. Financial Documents on process | 2
|  |  |  | 4 |  |  |  | Road w/ Bridge Component,Carmen |  |  |  |  | b) | Mellomida | b) | 12/18/17 | f) | 209 CD | b) | 57385680 | b) | 100% | d) | 0% | b) | 147 |  | 2
|  |  |  | 4 | [8 empty] | c) | PUREGOLD CONST. | c) | 02/15/19 | g) | - | c) | 36005452 | [7 empty] | 2
|  |  |  | 4 | [8 empty] | d) | 376 CD | d) | 07/31/19 | [11 empty] | 2
[6 empty] | D. | 20% Development Fund CY 2017 | [20 empty] | AC
[7 empty] | STIMULUS PROJECTS CY 2017 | [20 empty] | AC
[7 empty] | CARMEN | [20 empty] | AC
| 1 |  |  | 4 |  |  |  | Construction of Evaluation Center at Prk. 1, |  | Bldg. |  | Barangay | a) | 500000 | a) | 12/28/17 | e) | - | a) | 500000 | a) | - | c) | 100% | a) | - | Completed | 1
|  |  |  | 4 |  |  |  | Asuncion, Carmen |  |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 1
|  |  |  | 4 | [8 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 1
|  |  |  | 4 | [8 empty] | d) | - | d) | - | [11 empty] | 1
[7 empty] | Const./Rehab./Comp. of Various Gov't. Bldgs. |  |  | Bldg. | - | Admin | a) | 9,000,000.00 | [12 empty] | Investigation/Inspection of priority projects | AC
[7 empty] | Struct., Fac. (Provincewide) | [5 empty] | b) | Foronda/Ababon | [13 empty] | AC
[13 empty] | c) | PEO | [13 empty] | AC
[13 empty] | d) | - | [13 empty] | AC
| 1 |  |  | 4 |  |  | 2.3 | Improvement of Garciaville Day Care |  | Bldg. |  | Admin | a) | 330,000.00 | a) | 11/06/18 | e) | - | a) | 330,000.00 | a) |  | c) | 100% | a) | 3 | Completed based on POW. Financial Documents on process | 1
|  |  |  | 4 |  | 11 |  | Center, Mankilam, Tagum City |  |  |  |  | b) | - | b) | 09/02/19 | f) | - | b) | 330,000.00 | b) | - | d) |  | b) | 90 |  | 1
|  |  |  | 4 | [8 empty] | c) | PEO | c) | 10/11/19 | g) | - | c) | - | [7 empty] | 1
|  |  |  | 4 | [8 empty] | d) | - | d) | - | [11 empty] | 1
|  |  |  | 4 |  | F. | SDH IGCS - CONST. IN PROGRESS - BLGS. CY 2017 | [20 empty] | 2
| 1 |  |  | 4 |  |  | 1 | Construction Perimeter Fence Ph.II (Hospital |  | Fence |  | Admin | a) | 1,305,000.00 | a) | 11/10/17 | e) | 392 | a) | 1,305,000.00 | a) | 100% | c) | 100% | a) | 4 | Completed based on POW. Financial Documents on process | 2
|  |  |  | 4 |  |  |  | Compound) Samal District Hospital, IGCS |  |  |  |  | b) | Porras | b) | 03/12/18 | f) | 45 | b) | 1,305,000.00 | b) | - | d) | 1% | b) | 30 |  | 2
|  |  |  | 4 | [8 empty] | c) | PEO | c) | 06/19/18 | g) | - | c) | 958,597.98 | [7 empty] | 2
|  |  |  | 4 | [8 empty] | d) | - | d) | [12 empty] | 2
|  |  |  | 4 |  | C.5 | LDRRM - Trust Fund | [20 empty] | AC
|  | 1 |  | 4 |  | 5 | 1. Construction of Slope Protection and Concrete Pavement along Sta. Fe Mambing Road Section |  |  | Slope |  | Admin | a) | 1,853,000.00 | a) | 11/28/18 | e) |  | a) | 1,853,000.00 | a) | 100% | c) | 100% | a) | 16 | Completed based on POW. Financial Documents on process | 1
|  |  |  | 4 | [8 empty] | b) | Gone | b) | 12/03/18 | f) | 108 CD | b) | 1,853,000.00 | b) | - | d) |  | b) | 144 |  | 1
|  |  |  | 4 | [8 empty] | c) | PEO | c) | 02/28/19 | g) | 10/30/2019 | c) | 742252.72 | [7 empty] | 1
|  |  |  | 4 | [8 empty] | d) | 86 CD | d) | 06/15/2019 | [11 empty] | 1
|  | 1 |  | 4 |  | 1 | 3. Rehab. Of Canatan Bridge Slope Protection |  |  | Slope | 395 sq.m. | Contract | a) | 9200000 | a) | 06/20/2018 | e) | - | a) | 9200000 | a) | 100% | c) | 100% | a) | - | Completed | 1
|  |  |  | 4 |  |  | Brgy. Canatan, Asuncion | [5 empty] | b) | Aclaracion | b) | 02/11/2019 | f) | 35 CD | b) | 9200000 | b) | 100% | d) | 0% | b) | - |  | 1
|  |  |  | 4 | [8 empty] | c) | J-One Builders | c) | 04/12/2019 | g) | 05/31/2019 | c) | 7222021.59 | [7 empty] | 1
|  |  |  | 4 | [8 empty] | d) | 60 CD | d) | 05/01/2019 | [11 empty] | 1
|  | 1 |  | 4 |  | 5 | 5. Const. of Cabidianan Bridge Slope Protection, Brgy. Cabidianan, New Corella |  |  | Slope |  | Admin | a) | 3590000 | a) | 07/18/18 | e) | - | a) | 3590000 | a) | 100% | c) | 100% | a) | 8 | Completed based on POW. Financial Documents on process | 1
|  |  |  | 4 | [8 empty] | b) | Gone | b) | 6/17/19 | f) | - | b) | 3590000 | b) |  | d) |  | b) | 80 |  | 1
|  |  |  | 4 | [8 empty] | c) | PEO | c) | 8/20/19 | g) | - | c) | 1929823.4 | [7 empty] | 1
|  |  |  | 4 | [8 empty] | d) | 65 CD | d) | - | [11 empty] | 1
[6 empty] | D. | SEF(Special Education Fund)-SUPPLEMENTAL BUDGET # 1 CY 2017 | [20 empty] | AC
[7 empty] | 1. Const./Impv't./Compl. Of School Bldgs., Struc. & Fac. |  |  | Bldgs. |  | Admin | a) | 3,300,000.00 | [12 empty] | See projects listed below | 1
[13 empty] | b) | Foronda | [13 empty] | 1
[13 empty] | c) | PEO | [13 empty] | 1
[13 empty] | d) | - | [13 empty] | 1
| 1 |  |  | 4 |  | 8 | 1.1 | Construction of 1 unit School Building |  | Bldg. |  | Admin | a) | 1100000 | a) | 02/19/18 | e) | - | a) | 1100000 | a) | 100 | c) | 100 | a) | 6 | Completed based on POW. Financial Documents on process | 1
|  |  |  | 4 |  |  |  | Lumabag, Talaingod |  |  |  |  | b) | Dadula | b) | 03/20/19 | f) | 27 CD | b) | 1100000 | b) |  | d) |  | b) | 30 |  | 1
|  |  |  | 4 | [8 empty] | c) | PEO | c) | 05/19/19 | g) | 06/30/2019 | c) | 595230.5 | [7 empty] | 1
|  |  |  | 4 | [8 empty] | d) | 60 CD | d) | - | [11 empty] | 1
AC
[7 empty] | Rehabilitation / Improvement Of Various Local |  |  | Road | - | Admin | a) | 5000000 | [12 empty] | See projects listed below | AC
[7 empty] | Roads and Drainages | [5 empty] | b) | Paraguya | [13 empty] | AC
[13 empty] | c) | Admin | [13 empty] | AC
[13 empty] | d) | - | [13 empty] | AC
1 |  |  |  | 4 |  |  |  | Rehabilitation of Brgy. Adecor Barangay |  | Road |  | Admin | a) | 138000 | a) | 04/25/18 | e) | 66 CD | a) | 138000 | a) | 60.00% | c) | 60.00% | a) | - | Completed as per POW. Financial Documents on process | 2
|  |  |  | 4 |  |  |  | Road, IGACOS |  |  |  |  | b) | Porras/Pacquiao | b) | 10/18/18 | f) | 225 CD | b) | 138000 | b) | - | d) | - | b) | - |  | 2
|  |  |  | 4 | [8 empty] | c) | PEO | c) | 10/27/19 | g) | - | c) | 111,872.00 | [7 empty] | 2
|  |  |  | 4 | [8 empty] | d) | - | d) | 10/15/2019 | [11 empty] | 2
[7 empty] | Const./Rehab./Comp. of Various Gov't. Bldgs. |  |  | Bldgs. | - | Admin | a) | 13523124 | [12 empty] | Investigation/Inspection of priority projects | AC
[7 empty] | Struct., Fac. (Provincewide) | [5 empty] | b) | Foronda | [13 empty] | AC
[13 empty] | c) | Admin | [13 empty] | AC
[13 empty] | d) | - | [13 empty] | AC
| 1 |  |  | 4 |  |  |  | Repair/Rehab. Of PEO Building (2nd District), Carmen |  | Bldg |  | Admin | a) | 2250000 | a) | 08/10/18 | e) | - | a) | 2250000 | a) | 100% | c) | 100% | a) | 18 | Completed based on POW. Financial Documents on process | 2
|  |  |  | 4 | [8 empty] | b) | Andoy | b) | 02/18/19 | f) | - | b) | 2250000 | b) | - | d) | 0% | b) | 138 |  | 2
|  |  |  | 4 | [8 empty] | c) | Admin | c) | 08/23/19 | g) | - | c) | 1577344.8 | [7 empty] | 2
|  |  |  | 4 | [8 empty] | d) | - | d) | - | [11 empty] | 2
[7 empty] | STIMULUS PROJECTS | [20 empty] | AC
[7 empty] | TAGUM CITY | [20 empty] | AC
| 1 |  |  | 4 |  |  |  | Completion of Two Storey Multi-Purpose |  | Bldg. |  | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | 100% | c) | 100% | a) | 5 | Completed based on Physical Accomplishment. Financial Documents on process | 1
|  |  |  | 4 |  |  |  | Building, Magugpo East, Tagum City |  |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | 0% | b) | 110 |  | 1
|  |  |  | 4 | [8 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 1
|  |  |  | 4 | [8 empty] | d) | - | d) | - | [11 empty] | 1
|  |  |  | 4 |  | L. | 5% Calamity Fund CY 2018 | [20 empty] | AC
|  |  |  | 4 |  |  | 1. Prevention and Mitigation | [20 empty] | AC
|  | 1 |  | 4 |  |  | 1.1 Desiltation/Excavation of rivers and creeks |  |  | rivers |  | Admin | a) | 3000000 | [12 empty] | Investigation/Inspection of priority projects | AC
|  |  |  | 4 | [8 empty] | b) | - | [13 empty] | AC
|  |  |  | 4 | [8 empty] | c) | PEO | [13 empty] | AC
|  |  |  | 4 | [8 empty] | d) | - | [13 empty] | AC
|  |  |  | 4 | [23 empty] | 1
|  | 1 |  | 4 |  |  | 1.1.1. | Improvement and Desiltation of Tagum Creek (Phase I and Phase II) |  | Creek |  | Admin | a) | 2,000,000.00 | a) | 11/06/18 | e) | - | a) | 2,000,000.00 | a) | 100% | c) | 100% | a) | 5 | Completed | 1
|  |  |  | 4 | [8 empty] | b) | Mayang | b) | 03/22/19 | f) | - | b) | 2,000,000.00 | b) | - | d) | 0% | b) | 110 |  | 1
|  |  |  | 4 | [8 empty] | c) | PEO | c) | 10/31/19 | g) | - | c) | - | [7 empty] | 1
|  |  |  | 4 | [8 empty] | d) | 224 CD | d) | - | [11 empty] | 1
|  |  |  | 4 |  |  | OPPAP-PAMANA | [20 empty] | AC
|  |  | 1 | 4 |  | 4 |  | Upgrading of Existing PWS Level II in Sitio Patel 2, Gupitan, Kapalong |  | PWS |  | Admin | a) | 2500000 | a) | 8/14/2019 | e) | - | a) | 2500000 | a) |  | c) | 100% | a) | - | Completed as per Physical Accomplishment. Financial Documents on process | 1
|  |  |  | 4 | [8 empty] | b) | Diosanta | b) | 3/25/2019 | f) | - | b) | 2500000 | b) |  | d) |  | b) | - |  | 1
|  |  |  | 4 | [8 empty] | c) | PEO | c) | 7/19/2019 | g) | 09/30/2019 | c) | - | [7 empty] | 1
|  |  |  | 4 | [8 empty] | d) | - | d) | - | [11 empty] | 1
|  |  |  | 4 |  | R. | LOCAL GOVERNMENT SUPPORT FUND (LGSF) CY 2018 | [20 empty] | AC
1 |  |  |  | 4 |  |  | 1 | Road Upgrading of San Vicente - Butay Provincial Road |  | Road |  | Contract | a) | 19949581.18 | a) | CY 2018 | e) | - | a) | 19949581.18 | a) | 100% | c) | 100% | a) | 18 | Completed as per Physical Accomplishment. Financial Documents on process | 1
|  |  |  | 4 | [8 empty] | b) | Aclaracion | b) | 11/19/18 | f) | 28 CD | b) | 19949581.18 | b) | 100% | d) | 0% | b) | 396 |  | 1
|  |  |  | 4 | [8 empty] | c) | Alpha & Omega | c) | 06/08/19 | g) | 06/26/2019 | c) | 9,685,667.31 | [7 empty] | 1
|  |  |  | 4 | [8 empty] | d) | 202 CD | d) | 07/06/19 | [11 empty] | 1
[5 empty] | II. PROJECTS UNDER THE CURRENT APPROPRIATION CY 2019 | [22 empty] | AP
[5 empty] | A.1 GENERAL FUND CY 2019 | [6 empty] | MBA/CBRMC | a) | 18127866 | a) | 01/03/19 | e) | - | a) | 18127866 | a) | 83.63 | c) | 83.83 | a) | 46 | See list of Provincial Roads | AP
[5 empty] | Road ID |  | Maintenance of Various Provincial Roads and Bridges at District 1 |  |  | Road Maintenance | KM |  | b) | Paraguya | b) | 01/03/19 | f) | - | b) | 18127866 | b) | - | d) | - | b) | 920 |  | FS
[11 empty] | 288.26 |  | c) | PEO/CBRMC | c) | 12/31/19 | g) | - | c) | - | [7 empty] | AC
[5 empty] | 11DAN | [9 empty] | d) | - | [11 empty] | AC
[13 empty] | d) | 261 days | d) | - | [11 empty] | AC
[7 empty] | Jct. Highway Magatos - New Bantayan |  |  | Road Maintenance | 7.1 | MBA | a) | 287307.39 | a) | 01/03/19 | e) | - | a) | 287307.39 | a) | 100% | c) | 100% | a) | 15 | Completed | AC
[5 empty] | 001 | [7 empty] | b) | Crucio | b) | 01/16/19 | f) | - | b) | 287307.39 | b) | - | d) | - | b) | 480 |  | 1
[13 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 118693.58 | [7 empty] | 1
[13 empty] | d) | - | d) | - | [11 empty] | 1
[7 empty] | Jct. Highway Magatos - New Bantayan |  |  | Road Maintenance | 7.1 | CBRMC | a) | 223674.22 | a) | 01/03/19 | e) | - | a) | 223674.22 | a) | 100% | c) | 100% | a) | 16 | Completed | 1
[5 empty] | 001 | [7 empty] | b) | Crucio | b) | 3/22/19 | f) | - | b) | 223674.22 | b) | - | d) | - | b) | 480 |  | 1
[13 empty] | c) | CALAFA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1
[13 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
[7 empty] | Magatos-Bdry Pagsabangan |  |  | Road Maintenance | 8.33 | MBA | a) | 328740.25 | a) | 01/03/19 | e) | - | a) | 328740.25 | a) | 100% | c) | 100% | a) | 15 | Completed | 1
[5 empty] | 002 | [7 empty] | b) | Crucio | b) | 01/03/19 | f) | - | b) | 328740.25 | b) | - | d) | - | b) | 450 |  | 1
[13 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 207258.49 | [7 empty] | 1
[13 empty] | d) | - | d) | - | [11 empty] | 1
[7 empty] | Magatos-Bdry Pagsabangan |  |  | Road Maintenance | 8.33 | CBRMC | a) | 270763.53 | a) | 01/03/19 | e) | - | a) | 270763.53 | a) | 100% | c) | 100% | a) | 16 | Completed | 1
[5 empty] | 002 | [7 empty] | b) | Crucio | b) | 03/22/19 | f) | - | b) | 270763.53 | b) | - | d) | - | b) | 450 |  | 1
[13 empty] | c) | CALAFA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1
[13 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
[7 empty] | Ilog-New Bantayan |  |  | Road Maintenance | 2.68 | MBA | a) | 131131.39 | a) | 01/03/19 | e) | - | a) | 131131.39 | a) | 100% | c) | 100% | a) | 15 | Completed | 1
[5 empty] | 003 | [7 empty] | b) | Crucio | b) | 01/16/19 | f) | - | b) | 131131.39 | b) | - | d) | - | b) | 450 |  | 1
[13 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 49,316.69 | [7 empty] | 1
[13 empty] | d) | - | d) | - | [11 empty] | 1
[7 empty] | Ilog-New Bantayan |  |  | Road Maintenance | 2.68 | CBRMC | a) | 65925.03 | a) | 01/03/19 | e) | - | a) | 65925.03 | a) | 100% | c) | 100% | a) | 16 | Completed | 1
[5 empty] | 003 | [7 empty] | b) | Crucio | b) | 03/22/19 | f) | - | b) | 65925.03 | b) | - | d) | - | b) | 450 |  | 1
[13 empty] | c) | CALAFA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1
[13 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
[7 empty] | Asuncion -Monte Carlo-Del Pilar |  |  | Road Maintenance | 9.93 | MBA | a) | 474102.88 | a) | 01/03/19 | e) | - | a) | 474102.88 | a) | 100% | c) | 100% | a) | 15 | Completed | 1
[5 empty] | 005 | [7 empty] | b) | Crucio | b) | 01/03/19 | f) | - | b) | 474102.88 | b) | - | d) | - | b) | 450 |  | 1
[13 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 240274.49 | [7 empty] | 1
[13 empty] | d) | - | d) | - | [11 empty] | 1
[7 empty] | Asuncion -Monte Carlo-Del Pilar |  |  | Road Maintenance | 9.93 | CBRMC | a) | 355524.28 | a) | 01/03/19 | e) | - | a) | 355524.28 | a) | 100% | c) | 100% | a) | 16 | Completed
[5 empty] | 005 | [7 empty] | b) | Crucio | b) | 03/22/19 | f) | - | b) | 355524.28 | b) | - | d) | - | b) | 450 |  | 1
[13 empty] | c) | MAHAYAHAY IFA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1
[13 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
[7 empty] | Jct. Highway Canatan-Jct. Highway Magatos |  |  | Road Maintenance | 4.85 | MBA | a) | 209808.59 | a) | 01/03/19 | e) | - | a) | 209808.59 | a) | 100% | c) | 100% | a) | 15 | Completed | 1
[5 empty] | 006 | [7 empty] | b) | Crucio | b) | 02/18/19 | f) | - | b) | 209808.59 | b) | - | d) | - | b) | 450 |  | 1
[13 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 80652.8 | [7 empty] | 1
[13 empty] | d) | - | d) | - | [11 empty] | 1
[7 empty] | Jct. Highway Canatan-Jct. Highway Magatos |  |  | Road Maintenance | 4.85 | CBRMC | a) | 162458.12 | a) | 01/03/19 | e) | - | a) | 162458.12 | a) | 100% | c) | 100% | a) | 16 | Completed | 1
[5 empty] | 006 | [7 empty] | b) | Crucio | b) | 03/22/19 | f) | - | b) | 162458.12 | b) | - | d) | - | b) | 450 |  | 1
[13 empty] | c) | CAMODA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1
[13 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
1
[7 empty] | Sta. Felomina-San Roque |  |  | Road Maintenance | 7.68 | MBA | a) | 147439.63 | a) | 01/03/19 | e) | - | a) | 147439.63 | a) | 100% | c) | 100% | a) | 15 | Completed
[5 empty] | 008 | [7 empty] | b) | Crucio | b) | 01/16/19 | f) | - | b) | 147439.63 | b) | - | d) | - | b) | 450 |  | 1
[13 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 63806.67 | [7 empty] | 1
[13 empty] | d) | - | d) | - | [11 empty] | 1
[7 empty] | Sta. Felomina-San Roque |  |  | Road Maintenance | 7.68 | CBRMC | a) | 261345.67 | a) | 01/03/19 | e) | - | a) | 261345.67 | a) | 100% | c) | 100% | a) | 16 | Completed | 1
[5 empty] | 008 | [7 empty] | b) | Crucio | b) | 03/25/19 | f) | - | b) | 261345.67 | b) | - | d) | - | b) | 450 |  | 1
[13 empty] | c) | STAFFA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1
[13 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
[7 empty] | Saug-Sonlon-Bdy Longanapan |  |  | Road Maintenance | 11.6 | MBA | a) | 568486.36 | a) | 01/03/19 | e) | - | a) | 568486.36 | a) | 100% | c) | 100% | a) | 15 | Completed | 1
[5 empty] | 010 | [7 empty] | b) | Crucio | b) | 01/16/19 | f) | - | b) | 568486.36 | b) | - | d) | - | b) | 450 |  | 1
[13 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 262900.22 | [7 empty] | 1
[13 empty] | d) | - | d) | - | [11 empty] | 1
[7 empty] | Saug-Sonlon-Bdy Longanapan |  |  | Road Maintenance | 11.6 | CBRMC | a) | 185565.56 | a) | 01/03/19 | e) | - | a) | 185565.56 | a) | 100% | c) | 100% | a) | 16 | Completed | 1
[5 empty] | 010 | [7 empty] | b) | Crucio | b) | 03/26/19 | f) | - | b) | 185565.56 | b) | - | d) | - | b) | 450 |  | 1
[13 empty] | c) | BINANCIAN LIVESTOCK AFA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1
[13 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
[7 empty] | Jct. New Visayas-Buan |  |  | Road Maintenance | 2.99 | MBA | a) | 79238.27 | a) | 01/03/19 | e) | - | a) | 79238.27 | a) | 100% | c) | 100% | a) | 15 | Completed | 1
[5 empty] | 011 | [7 empty] | b) | Crucio | b) | 02/18/19 | f) | - | b) | 79238.27 | b) | - | d) | - | b) | 450 |  | 1
[13 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 14682.85 | [7 empty] | 1
[13 empty] | d) | - | d) | - | [11 empty] | 1
[7 empty] | Jct. New Visayas-Buan |  |  | Road Maintenance | 2.99 | CBRMC | a) | 101242.01 | a) | 01/03/19 | e) | - | a) | 101242.01 | a) | 100% | c) | 100% | a) | 16 | Completed | 1
[5 empty] | 011 | [7 empty] | b) | Crucio | b) | 03/22/19 | f) | - | b) | 101242.01 | b) | - | d) | - | b) | 450 |  | 1
[13 empty] | c) | BUAN IFA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1
[13 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
[7 empty] | San Vicente - Butay |  |  | Road Maintenance | 7.52 | MBA | a) | 209624.2 | a) | 01/03/19 | e) | - | a) | 209624.2 | a) | 100% | c) | 100% | a) | 15 | Completed | 1
[5 empty] | 013 | [7 empty] | b) | Crucio | b) | 02/18/19 | f) | - | b) | 209624.2 | b) | - | d) | - | b) | 450 |  | 1
[13 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 56,080.29 | [7 empty] | 1
[13 empty] | d) | - | d) | - | [11 empty] | 1
[7 empty] | San Vicente - Butay |  |  | Road Maintenance | 7.52 | CBRMC | a) | 227205.88 | a) | 01/03/19 | e) | - | a) | 227205.88 | a) | 100% | c) | 100% | a) | 16 | Completed | 1
[5 empty] | 013 | [7 empty] | b) | Crucio | b) | 03/27/19 | f) | - | b) | 227205.88 | b) | - | d) | - | b) | 450 |  | 1
[13 empty] | c) | SVMODA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1
[13 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
[7 empty] | Jct. Highway Doña Andrea - Capungagan |  |  | Road Maintenance | 8.7 | MBA | a) | 230835.16 | a) | 01/03/19 | e) | - | a) | 230835.16 | a) | 100% | c) | 100% | a) | 15 | Completed | 1
[5 empty] | 014 | [7 empty] | b) | Crucio | b) | 02/18/19 | f) | - | b) | 230835.16 | b) | - | d) | - | b) | 450 |  | 1
[13 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 60,629.26 | [7 empty] | 1
[13 empty] | d) | - | d) | - | [11 empty] | 1
1
[7 empty] | Jct. Highway Doña Andrea - Capungagan |  |  | Road Maintenance | 8.7 | CBRMC | a) | 294308.14 | a) | 01/03/19 | e) | - | a) | 294308.14 | a) | 100% | c) | 100% | a) | 16 | Completed
[5 empty] | 014 | [7 empty] | b) | Crucio | b) | 03/28/19 | f) | - | b) | 294308.14 | b) | - | d) | - | b) | 450 |  | 1
[13 empty] | c) | CAPUNGAGAN MPC | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1
[13 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
[7 empty] | Semong-Palma Gil |  |  | Road Maintenance | 2.73 | MBA | a) | 147289.98 | a) | 01/03/19 | e) | - | a) | 147289.98 | a) | 100% | c) | 100% | a) | 15 | Completed | 1
[5 empty] | 018 | [7 empty] | b) | Crucio | b) | 02/18/19 | f) | - | b) | 147289.98 | b) | - | d) | - | b) | 450 |  | 1
[13 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 71745.43 | [7 empty] | 1
[13 empty] | d) | - | d) | - | [11 empty] | 1
1
[7 empty] | Semong-Palma Gil |  |  | Road Maintenance | 2.73 | CBRMC | a) | 49186.05 | a) | 01/03/19 | e) | - | a) | 49186.05 | a) | 100% | c) | 100% | a) | 16 | Completed
[5 empty] | 018 | [7 empty] | b) | Crucio | b) | 03/22/19 | f) | - | b) | 49186.05 | b) | - | d) | - | b) | 450 |  | 1
[13 empty] | c) | PALMA GIL FA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1
[13 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
[7 empty] | Daligdigon - Dagohoy |  |  | Road Maintenance | 3.34 | MBA | a) | 148835.45 | a) | 01/03/19 | e) | - | a) | 148835.45 | a) | 100% | c) | 100% | a) | - | Completed | 1
[5 empty] | 020 | [7 empty] | b) | Crucio | b) | - | f) | - | b) | 148835.45 | b) | - | d) | - | b) | - |  | 1
[13 empty] | c) | PEO | c) | - | g) | 2019-12-31 | c) | - | [7 empty] | 1
[13 empty] | d) | - | d) | - | [11 empty] | 1
[7 empty] | Daligdigon - Dagohoy |  |  | Road Maintenance | 3.34 | CBRMC | a) | 68279.5 | a) | 01/03/19 | e) | - | a) | 68279.5 | a) | 100% | c) | 100% | a) | 16 | Completed | 1
[5 empty] | 020 | [7 empty] | b) | Crucio | b) | 03/22/19 | f) | - | b) | 68279.5 | b) | - | d) | - | b) | 450 |  | 1
[13 empty] | c) | PALMA GIL FA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1
[13 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
[7 empty] | Jct. Sampao-Bdry. Mamacao |  |  | Road Maintenance | 4.98 | MBA | a) | 154200.78 | a) | 01/03/19 | e) | - | a) | 154200.78 | a) | 100% | c) | 100% | a) | 15 | Completed | 1
[5 empty] | 025 | [7 empty] | b) | Crucio | b) | 02/18/19 | f) | - | b) | 154200.78 | b) | - | d) | - | b) | 450 |  | 1
[13 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 24,296.87 | [7 empty] | 1
[13 empty] | d) | - | d) | - | [11 empty] | 1
[7 empty] | Jct. Sampao-Bdry. Mamacao |  |  | Road Maintenance | 4.98 | CBRMC | a) | 169521.51 | a) | 01/03/19 | e) | - | a) | 169521.51 | a) | 100% | c) | 100% | a) | 16 | Completed | 1
[5 empty] | 025 | [7 empty] | b) | Crucio | b) | 03/26/19 | f) | - | b) | 169521.51 | b) | - | d) | - | b) | 450 |  | 1
[13 empty] | c) | AMS KAPALONG | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1
[13 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
[7 empty] | Jct. Highway Luna-Mamacao-Narra |  |  | Road Maintenance | 9.17 | MBA | a) | 357957.66 | a) | 01/03/19 | e) | - | a) | 357957.66 | a) | 100% | c) | 100% | a) | 15 | Completed | 1
[5 empty] | 026 | [7 empty] | b) | Crucio | b) | 02/18/19 | f) | - | b) | 357957.66 | b) | - | d) | - | b) | 450 |  | 1
[13 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 127,996.16 | [7 empty] | 1
[13 empty] | d) | - | d) | - | [11 empty] | 1
[7 empty] | Jct. Highway Luna-Mamacao-Narra |  |  | Road Maintenance | 9.17 | CBRMC | a) | 313143.91 | a) | 01/03/19 | e) | - | a) | 313143.91 | a) | 100% | c) | 100% | a) | 16 | Completed | 1
[5 empty] | 026 | [7 empty] | b) | Crucio | b) | 03/26/19 | f) | - | b) | 313143.91 | b) | - | d) | - | b) | 450 |  | 1
[13 empty] | c) | AMS KAPALONG | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1
[13 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
[7 empty] | Jct. Gabuyan-Katipunan-Bucana |  |  | Road Maintenance | 5.89 | MBA | a) | 294403.23 | a) | 01/03/19 | e) | - | a) | 294403.23 | a) | 100% | c) | 100% | a) | 15 | Completed | 1
[5 empty] | 027 | [7 empty] | b) | Crucio | b) | 02/18/19 | f) | - | b) | 294403.23 | b) | - | d) | - | b) | 450 |  | 1
[13 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 126,179.97 | [7 empty] | 1
[13 empty] | d) | - | d) | - | [11 empty] | 1
[7 empty] | Jct. Gabuyan-Katipunan-Bucana |  |  | Road Maintenance | 5.89 | CBRMC | a) | 129495.6 | a) | 01/03/19 | e) | - | a) | 129495.6 | a) | 100% | c) | 100% | a) | 16 | Completed | 1
[5 empty] | 027 | [7 empty] | b) | Crucio | b) | 03/26/19 | f) | - | b) | 129495.6 | b) | - | d) | - | b) | 450 |  | 1
[13 empty] | c) | MANGULIBAS FA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1
[13 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
[7 empty] | Capungagan-Mabuhay-Pandulian |  |  | Road Maintenance | 5.57 | MBA | a) | 294917.73 | a) | 01/03/19 | e) | - | a) | 294917.73 | a) | 100% | c) | 100% | a) | 15 | Completed | 1
[5 empty] | 028 | [7 empty] | b) | Crucio | b) | 02/18/19 | f) | - | b) | 294917.73 | b) | - | d) | - | b) | 450 |  | 1
[13 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1
[13 empty] | d) | - | d) | - | [11 empty] | 1
1
[7 empty] | Capungagan-Mabuhay-Pandulian |  |  | Road Maintenance | 5.57 | CBRMC | a) | 105950.95 | a) | 01/03/19 | e) | - | a) | 105950.95 | a) | 100% | c) | 100% | a) | 16 | Completed
[5 empty] | 028 | [7 empty] | b) | Crucio | b) | 03/28/19 | f) | - | b) | 105950.95 | b) | - | d) | - | b) | 450 |  | 1
[13 empty] | c) | CAPUNGAGAN MPC | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1
[13 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
[7 empty] | Florida - New Boholano |  |  | Road Maintenance | 2.54 | MBA | a) | 95863.17 | a) | 01/03/19 | e) | - | a) | 95863.17 | a) | 100% | c) | 100% | a) | 15 | Completed | 1
[5 empty] | 030 | [7 empty] | b) | Crucio | b) | 02/18/19 | f) | - | b) | 95863.17 | b) | - | d) | - | b) | 450 |  | 1
[13 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 31,418.99 | [7 empty] | 1
[13 empty] | d) | - | d) | - | [11 empty] | 1
[7 empty] | Florida - New Boholano |  |  | Road Maintenance | 2.54 | CBRMC | a) | 47425.27 | a) | 01/03/19 | e) | - | a) | 47425.27 | a) | 100% | c) | 100% | a) | 16 | Completed | 1
[5 empty] | 030 | [7 empty] | b) | Crucio | b) | 03/28/19 | f) | - | b) | 47425.27 | b) | - | d) | - | b) | 450 |  | 1
[13 empty] | c) | SUPRA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1
[13 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
[7 empty] | Jct. New Boholano - New Loon |  |  | Road Maintenance | 4.77 | MBA | a) | 140549.84 | a) | 01/03/19 | e) | - | a) | 140549.84 | a) | 100% | c) | 100% | a) | 15 | Completed | 1
[5 empty] | 031 | [7 empty] | b) | Crucio | b) | 02/18/19 | f) | - | b) | 140549.84 | b) | - | d) | - | b) | 450 |  | 1
[13 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 40,056.38 | [7 empty] | 1
[13 empty] | d) | - | d) | - | [11 empty] | 1
[7 empty] | Jct. New Boholano - New Loon |  |  | Road Maintenance | 4.77 | CBRMC | a) | 169521.51 | a) | 01/03/19 | e) | - | a) | 169521.51 | a) | 100% | c) | 100% | a) | 16 | Completed | 1
[5 empty] | 031 | [7 empty] | b) | Crucio | b) | 03/28/19 | f) | - | b) | 169521.51 | b) | - | d) | - | b) | 450 |  | 1
[13 empty] | c) | NEW LOON FA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1
[13 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
[7 empty] | Florida-Suaon-Jct. Gupitan |  |  | Road Maintenance | 15.57 | MBA | a) | 707038.05 | a) | 01/03/19 | e) | - | a) | 707038.05 | a) | 100% | c) | 100% | a) | 15 | Completed | 1
[5 empty] | 032 | [7 empty] | b) | Crucio | b) | 01/16/19 | f) | - | b) | 707038.05 | b) | - | d) | - | b) | 450 |  | 1
[13 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 226,.062.60 | [7 empty] | 1
[13 empty] | d) | - | d) | - | [11 empty] | 1
[7 empty] | Florida-Suaon-Jct. Gupitan |  |  | Road Maintenance | 15.57 | CBRMC | a) | 419094.85 | a) | 01/03/19 | e) | - | a) | 419094.85 | a) | 100% | c) | 100% | a) | 16 | Completed | 1
[5 empty] | 032 | [7 empty] | b) | Crucio | b) | 03/28/19 | f) | - | b) | 419094.85 | b) | - | d) | - | b) | 450 |  | 1
[13 empty] | c) | SUPRA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1
[13 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
[7 empty] | Km. 15, Kipalili-New Loon |  |  | Road Maintenance | 6.93 | MBA | a) | 367659.97 | a) | 01/03/19 | e) | - | a) | 367659.97 | a) | 100% | c) | 100% | a) | 15 | Completed | 1
[5 empty] | 034 | [7 empty] | b) | Crucio | b) | 02/01/19 | f) | - | b) | 367659.97 | b) | - | d) | - | b) | 450 |  | 1
[13 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 112,175.78 | [7 empty] | 1
[13 empty] | d) | - | d) | - | [11 empty] | 1
[7 empty] | Km. 15, Kipalili-New Loon |  |  | Road Maintenance | 6.93 | CBRMC | a) | 237801.01 | a) | 01/03/19 | e) | - | a) | 237801.01 | a) | 100% | c) | 100% | a) | 16 | Completed | 1
[5 empty] | 034 | [7 empty] | b) | Crucio | b) | 03/26/19 | f) | - | b) | 237801.01 | b) | - | d) | - | b) | 480 |  | 1
[13 empty] | c) | KIPALILI FA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1
[13 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
[7 empty] | Jct. Suaon-Libuton |  |  | Road Maintenance | 7.26 | MBA | a) | 44015.68 | a) | 01/03/19 | e) | - | a) | 44015.68 | a) | 100% | c) | 100% | a) | 15 | Completed
[5 empty] | 035 | [7 empty] | b) | Crucio | b) | 01/16/19 | f) | - | b) | 44015.68 | b) | - | d) | - | b) | 450 |  | 1
[13 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 24,980.86 | [7 empty] | 1
[13 empty] | d) | - | d) | - | [11 empty] | 1
[7 empty] | Jct. Suaon-Libuton |  |  | Road Maintenance | 7.26 | CBRMC | a) | 91664.91 | a) | 01/03/19 | e) | - | a) | 91664.91 | a) | 100% | c) | 100% | a) | 16 | Completed | 1
[5 empty] | 035 | [7 empty] | b) | Crucio | b) | 03/22/19 | f) | - | b) | 91664.91 | b) | - | d) | - | b) | 480 |  | 1
[13 empty] | c) | AALLI | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1
[13 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
1
[7 empty] | Datu Balong - Pinamuno |  |  | Road Maintenance | 2.74 | MBA | a) | 95458.24 | a) | 01/03/19 | e) | - | a) | 95458.24 | a) | 100% | c) | 100% | a) | 15 | Completed
[5 empty] | 040 | [7 empty] | b) | Crucio | b) | 03/01/19 | f) | - | b) | 95458.24 | b) | - | d) | - | b) | 450 |  | 1
[13 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 12,625.00 | [7 empty] | 1
[13 empty] | d) | - | d) | - | [11 empty] | 1
[7 empty] | Datu Balong - Pinamuno |  |  | Road Maintenance | 2.74 | CBRMC | a) | 63570.57 | a) | 01/03/19 | e) | - | a) | 63570.57 | a) | 100% | c) | 100% | a) | 16 | Completed | 1
[5 empty] | 040 | [7 empty] | b) | Crucio | b) | 03/28/19 | f) | - | b) | 63570.57 | b) | - | d) | - | b) | 480 |  | 1
[13 empty] | c) | DATU BALONG FA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1
[13 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
[7 empty] | Sawata - Mamangan - Pinamuno |  |  | Road Maintenance | 14.48 | MBA | a) | 545390.17 | a) | 01/03/19 | e) | - | a) | 545390.17 | a) | 100% | c) | 100% | a) | 15 | Completed | 1
[5 empty] | 041 | [7 empty] | b) | Crucio | b) | 02/01/19 | f) | - | b) | 545390.17 | b) | - | d) | - | b) | 450 |  | 1
[13 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 196,076.60 | [7 empty] | 1
[13 empty] | d) | - | d) | - | [11 empty] | 1
[7 empty] | Sawata - Mamangan - Pinamuno |  |  | Road Maintenance | 14.48 | CBRMC | a) | 508564.54 | a) | 01/03/19 | e) | - | a) | 508564.54 | a) | 100% | c) | 100% | a) | 16 | Completed | 1
[5 empty] | 041 | [7 empty] | b) | Crucio | b) | 03/22/19 | f) | - | b) | 508564.54 | b) | - | d) | - | b) | 480 |  | 1
[13 empty] | c) | SAWATA DFA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1
[13 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
[7 empty] | Igangon - Sawata |  |  | Road Maintenance | 9.66 | MBA | a) | 497447.77 | a) | 01/03/19 | e) | - | a) | 497447.77 | a) | 100% | c) | 100% | a) | 15 | Completed | 1
[5 empty] | 042 | [7 empty] | b) | Crucio | b) | 02/01/19 | f) | - | b) | 497447.77 | b) | - | d) | - | b) | 450 |  | 1
[13 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1
[13 empty] | d) | - | d) | - | [11 empty] | 1
[7 empty] | Igangon - Sawata |  |  | Road Maintenance | 9.66 | CBRMC | a) | 197775.1 | a) | 01/03/19 | e) | - | a) | 197775.1 | a) | 100% | c) | 100% | a) | 16 | Completed | 1
[5 empty] | 042 | [7 empty] | b) | Crucio | b) | 03/22/19 | f) | - | b) | 197775.1 | b) | - | d) | - | b) | 480 |  | 1
[13 empty] | c) | SAWATA DFA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1
[13 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
[7 empty] | New Corella - Sto. Niño - Macgum |  |  | Road Maintenance | 17.11 | MBA | a) | 606294.08 | a) | 01/03/19 | e) | - | a) | 606294.08 | a) | 100% | c) | 100% | a) | 15 | Completed | 1
[5 empty] | 044 | [7 empty] | b) | Crucio | b) | 01/03/19 | f) | - | b) | 606294.08 | b) | - | d) | - | b) | 450 |  | 1
[13 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 246,619.77 | [7 empty] | 1
[13 empty] | d) | - | d) | - | [11 empty] | 1
[7 empty] | New Corella - Sto. Niño - Macgum |  |  | Road Maintenance | 17.11 | CBRMC | a) | 308434.97 | a) | 01/03/19 | e) | - | a) | 308434.97 | a) | 100% | c) | 100% | a) | 16 | Completed | 1
[5 empty] | 044 | [7 empty] | b) | Crucio | b) | 03/26/19 | f) | - | b) | 308434.97 | b) | - | d) | - | b) | 480 |  | 1
[13 empty] | c) | SAN ISIDRO FA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1
[13 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
[7 empty] | Tagaytay - Buan |  |  | Road Maintenance | 4.92 | MBA | a) | 173197.37 | a) | 01/03/19 | e) | - | a) | 173197.37 | a) | 100% | c) | 100% | a) | 15 | Completed | 1
[5 empty] | 045 | [7 empty] | b) | Crucio | b) | 03/18/19 | f) | - | b) | 173197.37 | b) | - | d) | - | b) | 450 |  | 1
[13 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 26254.58 | [7 empty] | 1
[13 empty] | d) | - | d) | - | [11 empty] | 1
[7 empty] | Tagaytay - Buan |  |  | Road Maintenance | 4.92 | CBRMC | a) | 131850.07 | a) | 01/03/19 | e) | - | a) | 131850.07 | a) | 100% | c) | 100% | a) | 16 | Completed | 1
[5 empty] | 045 | [7 empty] | b) | Crucio | b) | 03/22/19 | f) | - | b) | 131850.07 | b) | - | d) | - | b) | 480 |  | 1
[13 empty] | c) | BUAN IFA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1
[13 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
[7 empty] | limbaan - Sto. Niño |  |  | Road Maintenance | 3.19 | MBA | a) | 153706.77 | a) | 01/03/19 | e) | - | a) | 153706.77 | a) | 100% | c) | 100% | a) | 15 | Completed | 1
[5 empty] | 049 | [7 empty] | b) | Crucio | b) | 03/01/19 | f) | - | b) | 153706.77 | b) | - | d) | - | b) | 450 |  | 1
[13 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 32534.49 | [7 empty] | 1
[13 empty] | d) | - | d) | - | [11 empty] | 1
[7 empty] | limbaan - Sto. Niño |  |  | Road Maintenance | 3.19 | CBRMC | a) | 53657.51 | a) | 01/03/19 | e) | - | a) | 53657.51 | a) | 100% | c) | 100% | a) | - | Completed | 1
[5 empty] | 049 | [7 empty] | b) | Crucio | b) | - | f) | - | b) | 53657.51 | b) | - | d) | - | b) | - |  | 1
[13 empty] | c) | - | c) | - | g) | 2019-12-31 | c) | - | [7 empty] | 1
[13 empty] | d) | - | d) | - | [11 empty] | 1
[7 empty] | Del Pilar - Jct. Silangan |  |  | Road Maintenance | 4.17 | MBA | a) | 187097.4 | a) | 01/03/19 | e) | - | a) | 187097.4 | a) | 100% | c) | 100% | a) | 15 | Completed | 1
[5 empty] | 051 | [7 empty] | b) | Crucio | b) | 03/18/19 | f) | - | b) | 187097.4 | b) | - | d) | - | b) | 450 |  | 1
[13 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 94181.74 | [7 empty] | 1
[13 empty] | d) | - | d) | - | [11 empty] | 1
[7 empty] | Del Pilar - Jct. Silangan |  |  | Road Maintenance | 4.17 | CBRMC | a) | 113014.34 | a) | 01/03/19 | e) | - | a) | 113014.34 | a) | 100% | c) | 100% | a) | 16 | Completed | 1
[5 empty] | 051 | [7 empty] | b) | Crucio | b) | 03/26/19 | f) | - | b) | 113014.34 | b) | - | d) | - | b) | 480 |  | 1
[13 empty] | c) | DURIAN DACUDAO | c) | 12/31/19 | g) | - | c) | - | [7 empty] | 1
[13 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
[7 empty] | New Corella - New Sambog - Silangan |  |  | Road Maintenance | 5.1 | MBA | a) | 201994.35 | a) | 01/03/19 | e) | - | a) | 201994.35 | a) | 100% | c) | 100% | a) | 15 | Completed | 1
[5 empty] | 052 | [7 empty] | b) | Crucio | b) | 03/01/19 | f) | - | b) | 201994.35 | b) | - | d) | - | b) | 450 |  | 1
[13 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 63402.48 | [7 empty] | 1
[13 empty] | d) | - | d) | - | [11 empty] | 1
[7 empty] | New Corella - New Sambog - Silangan |  |  | Road Maintenance | 5.1 | CBRMC | a) | 131850.07 | a) | 01/03/19 | e) | - | a) | 131850.07 | a) | 100% | c) | 100% | a) | 16 | Completed | 1
[5 empty] | 052 | [7 empty] | b) | Crucio | b) | 03/26/19 | f) | - | b) | 131850.07 | b) | - | d) | - | b) | 480 |  | 1
[13 empty] | c) | DURIAN DACUDAO | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1
[13 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
[7 empty] | Sta. Fe - Del Monte |  |  | Road Maintenance | 3.34 | MBA | a) | 37923.51 | a) | 01/03/19 | e) | - | a) | 37923.51 | a) | 100% | c) | 100% | a) | 15 | Completed | 1
[5 empty] | 056 | [7 empty] | b) | Crucio | b) | 03/18/19 | f) | - | b) | 37923.51 | b) | - | d) | - | b) | 450 |  | 1
[13 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 36595.13 | [7 empty] | 1
[13 empty] | d) | - | d) | - | [11 empty] | 1
[7 empty] | Sta. Fe - Del Monte |  |  | Road Maintenance | 3.34 | CBRMC | a) | 70633.96 | a) | 01/03/19 | e) | - | a) | 70633.96 | a) | 100% | c) | 100% | a) | 16 | Completed | 1
[5 empty] | 056 | [7 empty] | b) | Crucio | b) | 03/21/19 | f) | - | b) | 70633.96 | b) | - | d) | - | b) | 480 |  | 1
[13 empty] | c) | DEL MONTE CACAO | c) | 12/31/19 | g) | 2019-12-31 | c) | 4,872.18 | [7 empty] | 1
[13 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
[7 empty] | New Corella - New Bohol |  |  | Road Maintenance | 11.54 | MBA | a) | 356226.67 | a) | 01/03/19 | e) | - | a) | 356226.67 | a) | 100% | c) | 100% | a) | 15 | Completed
[5 empty] | 058 | [7 empty] | b) | Crucio | b) | 02/01/19 | f) | - | b) | 356226.67 | b) | - | d) | - | b) | 450 |  | 1
[13 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 110,982.71 | [7 empty] | 1
[13 empty] | d) | - | d) | - | [11 empty] | 1
[7 empty] | New Corella - New Bohol |  |  | Road Maintenance | 11.54 | CBRMC | a) | 190711.7 | a) | 01/03/19 | e) | - | a) | 190711.7 | a) | 100% | c) | 100% | a) | 16 | Completed | 1
[5 empty] | 058 | [7 empty] | b) | Crucio | b) | 03/22/19 | f) | - | b) | 190711.7 | b) | - | d) | - | b) | 480 |  | 1
[13 empty] | c) | SAN JOSE COCONUT | c) | 12/31/19 | g) | 2019-12-31 | c) | 5,847.18 | [7 empty] | 1
[13 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
1
[7 empty] | Jct. Carcor - Prk. 9 Bagsak |  |  | Road Maintenance | 2.5 | MBA | a) | 108618.49 | a) | 01/03/19 | e) | - | a) | 108618.49 | a) | 100% | c. | 100% | a) | 15 | Completed
[5 empty] | 059 | [7 empty] | b) | Crucio | b) | 03/01/19 | f) | - | b) | 108618.49 | b) | - | d) |  | b) | 480 |  | 1
[13 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 79952.88 | [7 empty] | 1
[13 empty] | d) | - | d) | - | [11 empty] | 1
1
[7 empty] | Jct. Carcor - Prk. 9 Bagsak |  |  | Road Maintenance | 2.5 | CBRMC | a) | 42284.76 | a) | 01/03/19 | e) | - | a) | 42284.76 | a) | 100% | c) | 100% | a) | 16 | Completed
[5 empty] | 059 | [7 empty] | b) | Crucio | b) | 03/22/19 | f) | - | b) | 42284.76 | b) | - | d) | - | b) | 480 |  | 1
[13 empty] | c) | CARCOR MOTOR | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1
[13 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
[7 empty] | Carcor - Jct. Kauswagan |  |  | Road Maintenance | 4.32 | MBA | a) | 264514.71 | a) | 01/03/19 | e) | - | a) | 264514.71 | a) | 100% | c) | 100% | a) | 15 | Completed | 1
[5 empty] | 060 | [7 empty] | b) | Crucio | b) | 03/18/19 | f) | - | b) | 264514.71 | b) | - | d) |  | b) | 450 |  | 1
[13 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 80733.11 | [7 empty] | 1
[13 empty] | d) | - | d) | - | [11 empty] | 1
[7 empty] | Carcor - Jct. Kauswagan |  |  | Road Maintenance | 4.32 | CBRMC | a) | 48398.27 | a) | 01/03/19 | e) | - | a) | 48398.27 | a) | 100% | c) | 100% | a) | 16 | Completed
[5 empty] | 060 | [7 empty] | b) | Crucio | b) | 03/22/19 | f) | - | b) | 48398.27 | b) | - | d) | - | b) | 480 |  | 1
[13 empty] | c) | CARCOR MOTOR | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1
[13 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
[7 empty] | Del Pilar - Prk 9 Bagsak - San Jose |  |  | Road Maintenance | 4.99 | MBA | a) | 170215.76 | a) | 01/03/19 | e) | - | a) | 170215.76 | a) | 100% | c) | 100% | a) | 15 | Completed | 1
[5 empty] | 061 | [7 empty] | b) | Crucio | b) | 03/01/19 | f) | - | b) | 170215.76 | b) | - | d) | - | b) | 450 |  | 1
[13 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 87595.63 | [7 empty] | 1
[13 empty] | d) | - | d) | - | [11 empty] | 1
[7 empty] | Del Pilar - Prk 9 Bagsak - San Jose |  |  | Road Maintenance | 4.99 | CBRMC | a) | 223674.22 | a) | 01/03/19 | e) | - | a) | 223674.22 | a) | 100% | c) | 100% | a) | 16 | Completed | 1
[5 empty] | 061 | [7 empty] | b) | Crucio | b) | 03/22/19 | f) | - | b) | 223674.22 | b) | - | d) | - | b) | 480 |  | 1
[13 empty] | c) | SAN JOSE COCONUT | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1
[13 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
[7 empty] | San Juan - New Talisay |  |  | Road Maintenance | 5.13 | MBA | a) | 306261.25 | a) | 01/03/19 | e) | - | a) | 306261.25 | a) | 100% | c) | 100% | a) | 15 | Completed | 1
[5 empty] | 063 | [7 empty] | b) | Crucio | b) | 02/01/19 | f) | - | b) | 306261.25 | b) | - | d) | - | b) | 450 |  | 1
[13 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 85123.48 | [7 empty] | 1
[13 empty] | d) | - | d) | - | [11 empty] | 1
[7 empty] | San Juan - New Talisay |  |  | Road Maintenance | 5.13 | CBRMC | a) | 93906.31 | a) | 01/03/19 | e) | - | a) | 93906.31 | a) | 100% | c) | 100% | a) | 16 | Completed
[5 empty] | 063 | [7 empty] | b) | Crucio | b) | 03/26/19 | f) | - | b) | 93906.31 | b) | - | d) | - | b) | 480 |  | 1
[13 empty] | c) | NEW TALISAY IAWA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1
[13 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
[7 empty] | San Juan - kauswagan - New Cortez |  |  | Road Maintenance | 3.22 | MBA | a) | 187879.04 | a) | 01/03/19 | e) | - | a) | 187879.04 | a) | 100% | c) | 100% | a) | 15 | Completed | 1
[5 empty] | 064 | [7 empty] | b) | Crucio | b) | 03/18/19 | f) | - | b) | 187879.04 | b) | - | d) | - | b) | 450 |  | 1
[13 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 3,025.00 | [7 empty] | 1
[13 empty] | d) | - | d) | - | [11 empty] | 1
[7 empty] | San Juan - kauswagan - New Cortez |  |  | Road Maintenance | 3.22 | CBRMC | a) | 63298.26 | a) | 01/03/19 | e) | - | a) | 63298.26 | a) | 100% | c) | 100% | a) | 16 | Completed
[5 empty] | 064 | [7 empty] | b) | Crucio | b) | 03/22/19 | f) | - | b) | 63298.26 | b) | - | d) | - | b) | 480 |  | 1
[13 empty] | c) | SAN JOSE COCONUT | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1
[13 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
[7 empty] | New Bohol - Jct. El Unido |  |  | Road Maintenance | 2.12 | MBA | a) | 54989.06 | a) | 01/03/19 | e) | - | a) | 54989.06 | a) | 100% | c) | 100% | a) | 15 | Completed
[5 empty] | 065 | [7 empty] | b) | Crucio | b) | 03/01/19 | f) | - | b) | 54989.06 | b) | - | d) | - | b) | 450 |  | 1
[13 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 21021.99 | [7 empty] | 1
[13 empty] | d) | - | d) | - | [11 empty] | 1
[7 empty] | New Bohol - Jct. El Unido |  |  | Road Maintenance | 2.12 | CBRMC | a) | 58861.64 | a) | 01/03/19 | e) | - | a) | 58861.64 | a) | 100% | c) | 100% | a) | 16 | Completed | 1
[5 empty] | 065 | [7 empty] | b) | Crucio | b) | 03/26/19 | f) | - | b) | 58861.64 | b) | - | d) | - | b) | 480 |  | 1
[13 empty] | c) | MANDISKAB TRIBAL | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1
[13 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
1
[7 empty] | New Corella - El unido - Jct. Mesaoy |  |  | Road Maintenance | 8.63 | MBA | a) | 388002.46 | a) | 01/03/19 | e) | - | a) | 388002.46 | a) | 100% | c) | 100% | a) | 15 | Completed
[5 empty] | 066 | [7 empty] | b) | Crucio | b) | 02/11/19 | f) | - | b) | 388002.46 | b) | - | d) | - | b) | 450 |  | 1
[13 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 58142.76 | [7 empty] | 1
[13 empty] | d) | - | d) | - | [11 empty] | 1
[7 empty] | New Corella - El unido - Jct. Mesaoy |  |  | Road Maintenance | 8.63 | CBRMC | a) | 233092.08 | a) | 01/03/19 | e) | - | a) | 233092.08 | a) | 100% | c) | 100% | a) | 16 | Completed | 1
[5 empty] | 066 | [7 empty] | b) | Crucio | b) | 03/26/19 | f) | - | b) | 233092.08 | b) | - | d) | - | b) | 480 |  | 1
[13 empty] | c) | MANDISKAB TRIBAL | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1
[13 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
[7 empty] | Mesaoy - Dasing |  |  | Road Maintenance | 1.39 | MBA | a) | 29749.5 | a) | 01/03/19 | e) | - | a) | 29749.5 | a) | 100% | c) | 100% | a) | 15 | Completed | 1
[5 empty] | 067 | [7 empty] | b) | Crucio | b) | 03/18/19 | f) | - | b) | 29749.5 | b) | - | d) | - | b) | 450 |  | 1
[13 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 10000 | [7 empty] | 1
[13 empty] | d) | - | d) | - | [11 empty] | 1
[7 empty] | Mesaoy - Dasing |  |  | Road Maintenance | 1.39 | CBRMC | a) | 54152.71 | a) | 01/03/19 | e) | - | a) | 54152.71 | a) | 100% | c) | 100% | a) | 16 | Completed | 1
[5 empty] | 067 | [7 empty] | b) | Crucio | b) | 03/26/19 | f) | - | b) | 54152.71 | b) | - | d) | - | b) | 480 |  | 1
[13 empty] | c) | MANDISKAB TRIBAL | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1
[13 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
[7 empty] | Jct. San Juan - Jct. Mesaoy |  |  | Road Maintenance | 1.82 | MBA | a) | 106788.95 | a) | 01/03/19 | e) | - | a) | 106788.95 | a) | 100% | c) | 100% | a) | 15 | Completed | 1
[5 empty] | 068 | [7 empty] | b) | Crucio | b) | 03/01/19 | f) | - | b) | 106788.95 | b) | - | d) | - | b) | 450 |  | 1
[13 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 17502.68 | [7 empty] | 1
[13 empty] | d) | - | d) | - | [11 empty] | 1
[7 empty] | Jct. San Juan - Jct. Mesaoy |  |  | Road Maintenance | 1.82 | CBRMC | a) | 35180.83 | a) | 01/03/19 | e) | - | a) | 35180.83 | a) | 100% | c) | 100% | a) | 16 | Completed | 1
[5 empty] | 068 | [7 empty] | b) | Crucio | b) | 03/26/19 | f) | - | b) | 35180.83 | b) | - | d) | - | b) | 480 |  | 1
[13 empty] | c) | MANDISKAB TRIBAL | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1
[13 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
[7 empty] | Mesaoy - Jct. Mahayahay |  |  | Road Maintenance | 4.6 | MBA | a) | 146984.46 | a) | 01/03/19 | e) | - | a) | 146984.46 | a) | 100% | c) | 100% | a) | 15 | Completed | 1
[5 empty] | 069 | [7 empty] | b) | Crucio | b) | 03/18/19 | f) | - | b) | 146984.46 | b) | - | d) | - | b) | 450 |  | 1
[13 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 7618.27 | [7 empty] | 1
[13 empty] | d) | - | d) | - | [11 empty] | 1
[7 empty] | Mesaoy - Jct. Mahayahay |  |  | Road Maintenance | 4.6 | CBRMC | a) | 160103.65 | a) | 01/03/19 | e) | - | a) | 160103.65 | a) | 100% | c) | 100% | a) | 16 | Completed
[5 empty] | 069 | [7 empty] | b) | Crucio | b) | 03/22/19 | f) | - | b) | 160103.65 | b) | - | d) | - | b) | 480 |  | 1
[13 empty] | c) | MAHAYAHAY IFA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1
[13 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
[7 empty] | Mesaoy - New bohol |  |  | Road Maintenance | 5.36 | MBA | a) | 165361.13 | a) | 01/03/19 | e) | - | a) | 165361.13 | a) | 100% | c) | 100% | a) | 15 | Completed
[5 empty] | 070 | [7 empty] | b) | Crucio | b) | 03/01/19 | f) | - | b) | 165361.13 | b) | - | d) | - | b) | 480 |  | 1
[13 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 2543.9 | [7 empty] | 1
[13 empty] | d) | - | d) | - | [11 empty] | 1
[7 empty] | Mesaoy - New bohol |  |  | Road Maintenance | 5.36 | CBRMC | a) | 224851.45 | a) | 01/03/19 | e) | - | a) | 224851.45 | a) | 100% | c) | 100% | a) | 16 | Completed
[5 empty] | 070 | [7 empty] | b) | Crucio | b) | 03/26/19 | f) | - | b) | 224851.45 | b) | - | d) | - | b) | 480 |  | 1
[13 empty] | c) | MANDISKAB TRIBAL | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1
[13 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
[7 empty] | Bdry. Tagum - Baca - New Corella |  |  | Road Maintenance | 13.01 | MBA | a) | 217182.9 | a) | 01/03/19 | e) | - | a) | 217182.9 | a) | 100% | c) | 100% | a) | 15 | Completed | 1
[5 empty] | 071 | [7 empty] | b) | Crucio | b) | 03/18/19 | f) | - | b) | 217182.9 | b) | - | d) | - | b) | 450 |  | 1
[13 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 19550 | [7 empty] | 1
[13 empty] | d) | - | d) | - | [11 empty] | 1
[7 empty] | Bdry. Tagum - Baca - New Corella |  |  | Road Maintenance | 13.01 | CBRMC | a) | 214256.36 | a) | 01/03/19 | e) | - | a) | 214256.36 | a) | 100% | c) | 100% | a) | 16 | Completed | 1
[5 empty] | 071 | [7 empty] | b) | Crucio | b) | 03/26/19 | f) | - | b) | 214256.36 | b) | - | d) | - | b) | 480 |  | 1
[13 empty] | c) | DURIAN DACUDAO | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1
[13 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
[7 empty] | Prk. 1, Maunlom - Prk. 6 Maunlom Road |  |  | Road Maintenance | 3.56 | MBA | a) | 150912.87 | a) | 01/03/19 | e) | - | a) | 150912.87 | a) | 100% | c) | 100% | a) | 15 | Completed | 1
[5 empty] | 147 | [7 empty] | b) | Crucio | b) | 03/01/19 | f) | - | b) | 150912.87 | b) | - | d) | - | b) | 450 |  | 1
[13 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 23025 | [7 empty] | 1
[13 empty] | d) | - | d) | - | [11 empty] | 1
[7 empty] | Prk. 1, Maunlom - Prk. 6 Maunlom Road |  |  | Road Maintenance | 3.56 | CBRMC | a) | 63973.36 | a) | 01/03/19 | e) | - | a) | 63973.36 | a) | 100% | c) | 100% | a) | 16 | Completed | 1
[5 empty] | 147 | [7 empty] | b) | Crucio | b) | 03/22/19 | f) | - | b) | 63973.36 | b) | - | d) | - | b) | 480 |  | 1
[13 empty] | c) | THE BEST VEGETABLE | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1
[13 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
1
[7 empty] | New Visayas - Binancian |  |  | Road Maintenance | 7.77 | MBA | a) | 14814.34 | a) | 01/03/19 | e) | - | a) | 14814.34 | a) | 100% | c) | 100% | a) | 15 | Completed
[5 empty] | 149 | [7 empty] | b) | Crucio | b) | 03/18/19 | f) | - | b) | 14814.34 | b) | - | d) | - | b) | 450 |  | 1
[13 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 5,000.00 | [7 empty] | 1
[13 empty] | d) | - | d) | - | [11 empty] | 1
[7 empty] | New Visayas - Binancian |  |  | Road Maintenance | 7.77 | CBRMC | a) | 129495.6 | a) | 01/03/19 | e) | - | a) | 129495.6 | a) | 100% | c) | 100% | a) | 16 | Completed | 1
[5 empty] | 149 | [7 empty] | b) | Crucio | b) | 03/22/19 | f) | - | b) | 129495.6 | b) | - | d) | - | b) | 480 |  | 1
[13 empty] | c) | BUAN IFA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1
[13 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
[7 empty] | Datu Balong - Prk. Mamalian |  |  | Road Maintenance | 3.46 | MBA | a) | 117454.89 | a) | 01/03/19 | e) | - | a) | 117454.89 | a) | 100% | c) | 39.37% | a) | 15 | Completed | 1
[5 empty] | 150 | [7 empty] | b) | Crucio | b) | 03/18/19 | f) | - | b) | 117454.89 | b) | - | d) | - | b) | 450 |  | 1
[13 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 10115 | [7 empty] | 1
[13 empty] | d) | - | d) | - | [11 empty] | 1
[7 empty] | Datu Balong - Prk. Mamalian |  |  | Road Maintenance | 3.46 | CBRMC | a) | 59264.42 | a) | 01/03/19 | e) | - | a) | 59264.42 | a) | 100% | c) | 100% | a) | 16 | Completed | 1
[5 empty] | 150 | [7 empty] | b) | Crucio | b) | 03/28/19 | f) | - | b) | 59264.42 | b) | - | d) | - | b) | 480 |  | 1
[13 empty] | c) | DATU BALONG FA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1
[13 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
[5 empty] | A.2 GENERAL FUND CY 2019 |  |  |  |  | Road Maintenance | KM | MBA/CBRMC | a) | 11,618,834.00 | a) | 01/03/19 | e) | - | a) | 11,618,834.00 | a) | 66% | c) | 66% | a) | 42 | See list of Provincial Roads
[5 empty] | Road ID |  | 1. Maintenance Of Various Prov'l. Roads and Bridges Dist 2 |  |  |  | 288.26 |  | b) | Matuguinas | b) | 01/03/19 | f) | - | b) | 11,618,834.00 | b) | - | d) | - | b) | 924 |  | FS
[13 empty] | c) | PEO/CBRMC | c) | 12/31/19 | g) | - | c) | - | [7 empty] | AC
[5 empty] | 11DAN | [9 empty] | d) | - | [11 empty] | AC
[13 empty] | d) | 261 days | d) | - | [11 empty] | AC
[7 empty] | Cebulano - Mangalcal |  |  | Road Maintenance | 4.17 | MBA | a) | 142161.87 | a) | 01/03/19 | e) | - | a) | 142161.87 | a) | 100% | c) | 100% | a) | 9 | Completed | AC
[6 empty] | 073 | [6 empty] | b) | Clar | b) | 2019-01-15 | f) | - | b) | 142161.87 | b) | - | d) | - | b) | 18 |  | 2
[13 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 118,609.29 | [7 empty] | 2
[13 empty] | d) | - | d) | - | [11 empty] | 2
[7 empty] | Tubod - basa - Mangalcal |  |  | Road Maintenance | 3.93 | MBA | a) | 156875.9 | a) | 01/03/19 | e) | - | a) | 156875.9 | a) | 100% | c) | 100% | a) | 9 | Completed | 2
[5 empty] | 074 | [7 empty] | b) | Clar | b) | 2019-01-15 | f) | - | b) | 156875.9 | b) | - | d) | - | b) | 18 |  | 2
[13 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 143,372.65 | [7 empty] | 2
[13 empty] | d) | - | d) | - | [11 empty] | 2
[7 empty] | Upper Mangalcal - Lower Mangalcal |  |  | Road Maintenance | 2.43 | CBRMC | a) | 79237.14 | a) | 01/03/19 | e) | - | a) | 79237.14 | a) | 100% | c) | 100% | a) | 9 | Completed | 2
[5 empty] | 078 | [7 empty] | b) | Clar | b) | 2019-01-14 | f) | - | b) | 79237.14 | b) | - | d) | - | b) | 27 |  | 2
[13 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 69,430.97 | [7 empty] | 2
[13 empty] | d) | - | d) | - | [11 empty] | 2
[7 empty] | Jct. Highway Carmen - Mangalcal - Tubod |  |  | Road Maintenance | 11.34 | MBA | a) | 463135.67 | a) | 01/03/19 | e) | - | a) | 463135.67 | a) | 100% | c) | 100% | a) | 9 | Completed | 2
[5 empty] | 082 | [7 empty] | b) | Clar | b) | 01/10/19 | f) | - | b) | 463135.67 | b) | - | d) | - | b) | 45 |  | 2
[13 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 170,106.43 | [7 empty] | 2
[13 empty] | d) | - | d) | - | [11 empty] | 2
[7 empty] | Jct. Highway Carmen - Mangalcal - Tubod |  |  | Road Maintenance | 11.34 | CBRMC | a) | 253557.37 | a) | 01/03/19 | e) | - | a) | 253557.37 | a) | 100% | c) | 100% | a) | 10 | Completed | 2
[5 empty] | 082 | [7 empty] | b) | Maligro | b) | 03/25/19 | f) | - | b) | 253557.37 | b) | - | d) | - | b) | 40 |  | 2
[13 empty] | c) | TUBOD CENTRO LOWER IRRIGATORS ASSOCIATION | c) | 09/25/19 | g) | 2019-12-31 | c) | - | [7 empty] | 2
[13 empty] | d) | 3 quarters | d) | - | [11 empty] | 2
[7 empty] | Jct. Highway Sto. Niño - Kabanlakan - La Paz |  |  | Road Maintenance | 2.13 | MBA | a) | 76067.88 | a) | 01/03/19 | e) | - | a) | 76067.88 | a) | 100% | c) | 100% | a) | 9 | Completed | 2
[5 empty] | 084 | [7 empty] | b) | Clar | b) | 01/10/19 | f) | - | b) | 76067.88 | b) | - | d) | - | b) | 45 |  | 2
[13 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 66,477.91 | [7 empty] | 2
[13 empty] | d) | - | d) | - | [11 empty] | 2
[7 empty] | Ising - Sto Niño |  |  | Road Maintenance | 2.07 | CBRMC | a) | 82413.14 | a) | 01/03/19 | e) | - | a) | 82413.14 | a) | 100% | c) | 100% | a) | 5 | Completed | 2
[5 empty] | 085 | [7 empty] | b) | Clar | b) | 01/17/19 | f) | - | b) | 82413.14 | b) | - | d) | - | b) | 15 |  | 2
[13 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 27,093.24 | [7 empty] | 2
[13 empty] | d) | - | d) | - | [11 empty] | 2
[7 empty] | Ising - Sadpodon - Taba - Dila -Dila |  |  | Road Maintenance | 5.68 | MBA | a) | 248941.33 | a) | 01/03/19 | e) | - | a) | 248941.33 | a) | 100% | c) | 100% | a) | 9 | Completed | 2
[5 empty] | 086 | [7 empty] | b) | Clar | b) | 01/12/19 | f) | - | b) | 248941.33 | b) | - | d) | - | b) | 27 |  | 2
[13 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 82,329.02 | [7 empty] | 2
[13 empty] | d) | - | d) | - |  |  |  | . | [7 empty] | 2
2
[7 empty] | Tuganay - taba |  |  | Road Maintenance | 4.27 | CBRMC | a) | 291377.9 | a) | 01/03/19 | e) | - | a) | 291377.9 | a) | 70% | c) | 70% | a) | 9 | Completed
[5 empty] | 087 | [7 empty] | b) | Clar | b) | 01/09/19 | f) | - | b) | 291377.9 | b) | - | d) | - | b) | 27 |  | 2
[13 empty] | c) | PEO | c) | 12/31/19 | g) | 12/31/2019 | c) | 238,412.28 | [7 empty] | 2
[13 empty] | d) | - | d) | - | [11 empty] | 2
[7 empty] | Jct. Highway Tuganay - Taba |  |  | Road Maintenance | 4.4 | MBA | a) | 32972.82 | a) | 01/03/19 | e) | - | a) | 32972.82 | a) | 65% | c) | 65% | a) | 9 | Completed | 2
[5 empty] | 088 | [7 empty] | b) | Clar | b) | 01/22/19 | f) | - | b) | 32972.82 | b) | - | d) | - | b) | 18 |  | 2
[13 empty] | c) | PEO | c) | 12/31/19 | g) | 12/31/2019 | c) | 22,639.09 | [7 empty] | 2
[13 empty] | d) | - | d) | - | [11 empty] | 2
[7 empty] | Jct. Highway Ising - Magsaysay |  |  | Road Maintenance | 10.84 | CBRMC | a) | 417818.12 | a) | 01/03/19 | e) | - | a) | 417818.12 | a) | 60% | c) | 60% | a) | 10 | Completed | 2
[5 empty] | 089 | [7 empty] | b) | Clar | b) | 01/22/19 | f) | - | b) | 417818.12 | b) | - | d) | - | b) | 50 |  | 2
[13 empty] | c) | PEO | c) | 12/31/19 | g) | 12/31/2019 | c) | 313,488.39 | [7 empty] | 2
[13 empty] | d) | - | d) | - | [11 empty] | 2
[7 empty] | New Camiling - Alejal - Lower Magsaysay |  |  | Road Maintenance | 6.73 | MBA | a) | 240878.08 | a) | 01/03/19 | e) | - | a) | 240878.08 | a) | 80% | c) | 80% | a) | 4 | Completed | 2
[5 empty] | 091 | [7 empty] | b) | Clar | b) | 01/22/19 | f) | - | b) | 240878.08 | b) | - | d) | - | b) | 20 |  | 2
[13 empty] | c) | PEO | c) | 12/31/19 | g) | 12/31/2019 | c) | - | [7 empty] | 2
[13 empty] | d) | - | d) | - | [11 empty] | 2
[7 empty] | Jct. highway Tuganay - Anibongan |  |  | Road Maintenance | 3.66 | CBRMC | a) | 150684.44 | a) | 01/03/19 | e) | - | a) | 150684.44 | a) | 100% | c) | 100% | a) | 6 | Completed | 2
[5 empty] | 094 | [7 empty] | b) | Clar | b) | 01/22/19 | f) | - | b) | 150684.44 | b) | - | d) | - | b) | 18 |  | 2
[13 empty] | c) | PEO | c) | 12/31/19 | g) | 12/31/2019 | c) | - | [7 empty] | 2
[13 empty] | d) | - | d) | - | [11 empty] | 2
[7 empty] | Anibongan - Guadalupe |  |  | Road Maintenance | 2.48 | MBA | a) | 91325.06 | a) | 01/03/19 | e) | - | a) | 91325.06 | a) | 100% | c) | 100% | a) | 9 | Completed | 2
[5 empty] | 095 | [7 empty] | b) | Clar | b) | 01/23/19 | f) | - | b) | 91325.06 | b) | - | d) | - | b) | 18 |  | 2
[13 empty] | c) | PEO | c) | 12/31/19 | g) | 12/31/2019 | c) | - | [7 empty] | 2
[13 empty] | d) | - | d) | - | [11 empty] | 2
[7 empty] | Tuganay - Anibongan - San Isidro |  |  | Road Maintenance | 7.22 | CBRMC | a) | 139979.8 | a) | 01/03/19 | e) | - | a) | 139979.8 | a) | 100% | c) | 100% | a) | 9 | Completed | 2
[5 empty] | 096 | [7 empty] | b) | Clar | b) | 01/24/19 | f) | - | b) | 139979.8 | b) | - | d) | - | b) | 36 |  | 2
[13 empty] | c) | PEO | c) | 12/31/19 | g) | 12/31/2019 | c) | 1890.37 | [7 empty] | 2
[13 empty] | d) | - | d) | - | [11 empty] | 2
[7 empty] | Jct. Anibongan - Prk. 2, 7, 5, San Isidro |  |  | Road Maintenance | 3.14 | MBA | a) | 104378.03 | a) | 01/03/19 | e) | - | a) | 104378.03 | a) | 100% | c) | 100% | a) | 10 | Completed | 2
[5 empty] | 097 | [7 empty] | b) | Clar | b) | 01/24/19 | f) | - | b) | 104378.03 | b) | - | d) | - | b) | 20 |  | 2
[13 empty] | c) | PEO | c) | 12/31/19 | g) | 12/31/2019 | c) | 56,087.50 | [7 empty] | 2
[13 empty] | d) | - | d) | - | [11 empty] | 2
[7 empty] | Anibongan - Salvacion - Cabay-angan |  |  | Road Maintenance | 6.93 | CBRMC | a) | 415461.61 | a) | 01/03/19 | e) | - | a) | 415461.61 | a) | 100% | c) | 100% | a) | 9 | Completed | 2
[5 empty] | 098 | [7 empty] | b) | Clar | b) | 01/25/19 | f) | - | b) | 415461.61 | b) | - | d) | - | b) | 45 |  | 2
[13 empty] | c) | PEO | c) | 12/31/19 | g) | 12/31/2019 | c) | - | [7 empty] | 2
[13 empty] | d) | - | d) | - | [11 empty] | 2
[7 empty] | Jct. Highway Guadalupe - Bdry. Tagum |  |  | Road Maintenance | 7.9 | MBA | a) | 456131.09 | a) | 01/03/19 | e) | - | a) | 456131.09 | a) | 100% | c) | 100% | a) | 9 | Completed | 2
[5 empty] | 101 | [7 empty] | b) | Clar | b) | 01/25/19 | f) | - | b) | 456131.09 | b) | - | d) | - | b) | 18 |  | 2
[13 empty] | c) | PEO | c) | 12/31/19 | g) | 12/31/2019 | c) | - | [7 empty] | 2
[13 empty] | d) | - | d) | - | [11 empty] | 2
[7 empty] | Jct. Highway Guadalupe - Bdry. Tagum |  |  | Road Maintenance | 7.9 | CBRMC | a) | 228201.66 | a) | 01/03/19 | e) | - | a) | 228201.66 | a) | 100% | c) | 100% | a) | 8 | Completed | 2
[5 empty] | 101 | [7 empty] | b) | Maligro | b) | 03/25/19 | f) | - | b) | 228201.66 | b) | - | d) | - | b) | 40 |  | 2
[13 empty] | c) | LAMPIA PAG-ASA IRRIGATORS ASSOCIATION, INC. | c) | 12/25/19 | g) | 12/31/2019 | c) | - | [7 empty] | 2
[13 empty] | d) | 3 quarters | d) | - | [11 empty] | 2
[7 empty] | Poblacion Dujali - Prk. 8 Dujali |  |  | Road Maintenance | 8.2 | MBA | a) | 285600.05 | a) | 01/03/19 | e) | - | a) | 285600.05 | a) | 100% | c) | 100% | a) | 10 | Completed | 2
[5 empty] | 105 | [7 empty] | b) | Clar | b) | 01/28/19 | f) | - | b) | 285600.05 | b) | - | d) | - | b) | 50 |  | 2
[13 empty] | c) | PEO | c) | 12/31/19 | g) | 12/31/2019 | c) | - | [7 empty] | 2
[13 empty] | d) | - | d) | - | [11 empty] | 2
[7 empty] | Dujali - San Isidro |  |  | Road Maintenance | 3 | CBRMC | a) | 130319.3 | a) | 01/03/19 | e) | - | a) | 130319.3 | a) | 100% | c) | 100% | a) | 8 | Completed | 2
[5 empty] | 107 | [7 empty] | b) | Gamad | b) | 01/28/19 | f) | - | b) | 130319.3 | b) | - | d) | - | b) | 30 |  | 2
[13 empty] | c) | PEO | c) | 12/31/19 | g) | 12/31/2019 | c) | 45,943.12 | [7 empty] | 2
[13 empty] | d) | - | d) | - | [11 empty] | 2
[7 empty] | Prk. 5, RJS - Prk. 6 New Casay |  |  | Road Maintenance | 2.73 | MBA | a) | 235277 | a) | 01/03/19 | e) | - | a) | 235277 | a) | 100% | c) | 100% | a) | 2 | Completed | 2
[5 empty] | 109 | [7 empty] | b) | Gamad | b) | 01/28/19 | f) | - | b) | 235277 | b) | - | d) | - | b) | 6 |  | 2
[13 empty] | c) | PEO | c) | 12/31/19 | g) | 12/31/2019 | c) | 90,745.35 | [7 empty] | 2
[13 empty] | d) | - | d) | - | [11 empty] | 2
[7 empty] | Prk. 5 - Prk. 1 Pawas Dujali |  |  | Road Maintenance | 2.18 | CBRMC | a) | 76067.68 | a) | 01/03/19 | e) | - | a) | 76067.68 | a) | 100% | c) | 100% | a) | 10 | Completed | 2
[5 empty] | 112 | [7 empty] | b) | Gamad | b) | 01/18/19 | f) | - | b) | 76067.68 | b) | - | d) | - | b) | 20 |  | 2
[13 empty] | c) | PEO | c) | 12/31/19 | g) | 12/31/2019 | c) | 40,112.50 | [7 empty] | 2
[13 empty] | d) | - | d) | - | [11 empty] | 2
[7 empty] | Dujali - Balisong - Magupising |  |  | Road Maintenance | 5.52 | MBA | a) | 260591.93 | a) | 01/03/19 | e) | - | a) | 260591.93 | a) | 100% | c) | 100% | a) | 4 | Completed | 2
[5 empty] | 113 | [7 empty] | b) | Gamad | b) | 01/09/19 | f) | - | b) | 260591.93 | b) | - | d) | - | b) | 8 |  | 2
[13 empty] | c) | PEO | c) | 12/31/19 | g) | 12/31/2019 | c) | - | [7 empty] | 2
[13 empty] | d) | - | d) | - | [11 empty] | 2
[7 empty] | Dujali - Pawas - San Vicente |  |  | Road Maintenance | 4.42 | CBRMC | a) | 139536.42 | a) | 01/03/19 | e) | - | a) | 139536.42 | a) | 100% | c) | 100% | a) | 10 | Completed | 2
[5 empty] | 117 | [7 empty] | b) | Gamad | b) | 01/22/19 | f) | - | b) | 139536.42 | b) | - | d) | - | b) | 18 |  | 2
[13 empty] | c) | PEO | c) | 12/31/19 | g) | 12/31/2019 | c) | 52,133.86 | [7 empty] | 2
[13 empty] | d) | - | d) | - | [11 empty] | 2
[7 empty] | Jct. Salvacion - San Vicente - Cabay-angan |  |  | Road Maintenance | 3.45 | MBA | a) | 247460.9 | a) | 01/03/19 | e) | - | a) | 247460.9 | a) | 100% | c) | 100% | a) | 10 | Completed | 2
[5 empty] | 118 | [7 empty] | b) | Gamad | b) | 01/23/19 | f) | - | b) | 247460.9 | b) | - | d) | - | b) | 18 |  | 2
[13 empty] | c) | PEO | c) | 02/31/19 | g) | 12/31/2019 | c) | 151,887.50 | [7 empty] | 2
[13 empty] | d) | - | d) | - | [11 empty] | 2
[7 empty] | Jct. Salvacion - San Vicente - Cabay-angan |  |  | Road Maintenance | 3.45 | CBRMC | a) | 152134.44 | a) | 01/03/19 | e) | - | a) | 152134.44 | a) | 100% | c) | 100% | a) | 8 | Completed | 2
[5 empty] | 118 | [7 empty] | b) | Gamad | b) | 03/26/19 | f) | - | b) | 152134.44 | b) | - | d) | - | b) | 36 |  | 2
[13 empty] | c) | BALISONG SAN VICENTE IRRIGATORS ASSOCIATION | c) | 12/26/19 | g) | 12/31/2019 | c) | [8 empty] | 2
[13 empty] | d) | 3 quarters | d) | - | [10 empty] | Completed | 2
[7 empty] | Dujali - San Miguel |  |  | Road Maintenance | 3.95 | MBA | a) | 101202.04 | a) | 01/03/19 | e) | - | a) | 101202.04 | a) | 80% | c) | 90% | a) | 11 |  | 2
[5 empty] | 119 | [7 empty] | b) | Gamad | b) | 01/10/19 | f) | - | b) | 101202.04 | b) | - | d) | - | b) | 22 |  | 2
[13 empty] | c) | PEO | c) | 12/31/19 | g) | - | c) | 90,350.03 | [7 empty] | 2
[13 empty] | d) | - | d) | - | [11 empty] | 2
[7 empty] | San Miguel - Casig-ang |  |  | Road Maintenance | 2.55 | CBRMC | a) | 79237.14 | a) | 01/03/19 | e) | - | a) | 79237.14 | a) | 100% | c) | 100% | a) | 10 | Completed | 2
[5 empty] | 122 | [7 empty] | b) | Gamad | b) | 01/24/19 | f) | - | b) | 79237.14 | b) | - | d) | - | b) | 10 |  | 2
[13 empty] | c) | BALISONG SAN VICENTE IRRIGATORS ASSOCIATION | c) | 12/31/19 | g) | 12/31/2019 | c) | 40,112.50 | [7 empty] | 2
[13 empty] | d) | - | d) | - | [11 empty] | 2
[7 empty] | Prk. Magsaysay - Lunga-og - Dalisay |  |  | Road Maintenance | 2.81 | MBA | a) | 79762.14 | a) | 01/03/19 | e) | - | a) | 79762.14 | a) | 100% | c) | 100% | a) | 8 | Completed | 2
[5 empty] | 127 | [7 empty] | b) | Gamad | b) | 01/30/19 | f) | - | b) | 79762.14 | b) | - | d) | - | b) | 8 |  | 2
[13 empty] | c) | PEO | c) | 12/31/19 | g) | 12/31/2019 | c) | 40,612.50 | [7 empty] | 2
[13 empty] | d) | - | d) | - | [11 empty] | 2
[7 empty] | Prk. Apitong - Upper Balisong - Dalisay |  |  | Road Maintenance | 4.6 | CBRMC | a) | 137846.03 | a) | 01/03/19 | e) | - | a) | 137846.03 | a) | 100% | c) | 100% | a) | 8 | Completed | 2
[5 empty] | 128 | [7 empty] | b) | Gamad | b) | 01/31/19 | f) | - | b) | 137846.03 | b) | - | d) | - | b) | 8 |  | 2
[13 empty] | c) | BALISONG SAN VICENTE IRRIGATORS ASSOCIATION | c) | 12/31/19 | g) | 12/31/2019 | c) | - | [7 empty] | 2
[13 empty] | d) | - | d) | - | [11 empty] | 2
[7 empty] | Sitio Paradise - Magkakaisa - Esperanza |  |  | Road Maintenance | 1.75 | MBA | a) | 66552.75 | a) | 01/03/19 | e) | - | a) | 66552.75 | a) | 100% | c) | 100% | a) | 8 | Completed | 2
[5 empty] | 129 | [7 empty] | b) | 79762.14 | b) | 01/22/19 | f) | - | b) | 66552.75 | b) | - | d) | - | b) | 8 |  | 2
[13 empty] | c) | Gamad | c) | 12/31/19 | g) | 12/31/2019 | c) | 22,246.26 | [7 empty] | 2
[13 empty] | d) | - | d) | - | [11 empty] | 2
[7 empty] | Los Amigos 1 - Esperanza - Los Amigos 2 |  |  | Road Maintenance | 3.59 | CBRMC | a) | 101202.04 | a) | 01/03/19 | e) | - | a) | 101202.04 | a) | 100% | c) | 100% | a) | 10 | Completed | 2
[5 empty] | 130 | [7 empty] | b) | Gamad | b) | 01/24/19 | f) | - | b) | 101202.04 | b) | - | d) | - | b) | 20 |  | 2
[13 empty] | c) | BALISONG SAN VICENTE IRRIGATORS ASSOCIATION | c) | 12/31/19 | g) | 12/31/2019 | c) | 50,837.50 | [7 empty] | 2
[13 empty] | d) | - | d) | - | [11 empty] | 2
[7 empty] | Mugas - Lunga-og |  |  | Road Maintenance | 2.68 | MBA | a) | 66552.75 | a) | 01/03/19 | e) | - | a) | 91,693.64 | a) | 100% | c) | 100% | a) | 6 | Completed | 2
[5 empty] | 132 | [7 empty] | b) | 79762.14 | b) | 01/17/19 | f) | - | b) | 91,693.64 | b) | - | d) | - | b) | 24 |  | 2
[13 empty] | c) | Gamad | c) | 12/31/19 | g) | 12/31/2019 | c) | 50,837.50 | [7 empty] | 2
[13 empty] | d) | - | d) | - | [11 empty] | 2
[7 empty] | Pantaron - Mugas |  |  | Road Maintenance | 3.35 | CBRMC | a) | 101202.04 | a) | 01/03/19 | e) | - | a) | 101202.04 | a) | 100% | c) | 100% | a) | 9 | Completed | 2
[5 empty] | 133 | [7 empty] | b) | Gamad | b) | 01/23/19 | f) | - | b) | 101202.04 | b) | - | d) | - | b) | 18 |  | 2
[13 empty] | c) | BALISONG SAN VICENTE IRRIGATORS ASSOCIATION | c) | 12/31/19 | g) | 12/31/2019 | c) | 90,349.93 | [7 empty] | 2
[13 empty] | d) | - | d) | - | [11 empty] | 2
[7 empty] | Sto. Tomas - Bdry. Mamacao |  |  | Road Maintenance | 4.9 | MBA | a) | 110710.44 | a) | 01/03/19 | e) | - | a) | 110710.44 | a) | 100% | c) | 100% | a) | 10 | Completed | 2
[5 empty] | 135 | [7 empty] | b) | 79762.14 | b) | 01/21/19 | f) | - | b) | 110710.44 | b) | - | d) | - | b) | 40 |  | 2
[13 empty] | c) | Gamad | c) | 12/31/19 | g) | 12/31/2019 | c) | 50,837.50 | [7 empty] | 2
[13 empty] | d) | - | d) | - | [11 empty] | 2
[7 empty] | Fd. Rd. 3 - San Jose |  |  | Road Maintenance | 4.55 | CBRMC | a) | 147367.49 | a) | 01/03/19 | e) | - | a) | 147367.49 | a) | 100% | c) | 100% | a) | 10 | Completed | 2
[5 empty] | 136 | [7 empty] | b) | Gamad | b) | 01/25/19 | f) | - | b) | 147367.49 | b) | - | d) | - | b) | 30 |  | 2
[13 empty] | c) | BALISONG SAN VICENTE IRRIGATORS ASSOCIATION | c) | 12/31/19 | g) | 12/31/2019 | c) | 56,174.69 | [7 empty] | 2
[13 empty] | d) | - | d) | - | [11 empty] | 2
[7 empty] | Menzi - balagunan - Tulalian |  |  | Road Maintenance | 10.63 | MBA | a) | 520167.79 | a) | 01/03/19 | e) | - | a) | 520167.79 | a) | 100% | c) | 100% | a) | 6 | Completed | 2
[5 empty] | 138 | [7 empty] | b) | 79762.14 | b) | 01/07/19 | f) | - | b) | 520167.79 | b) | - | d) | - | b) | 18 |  | 2
[13 empty] | c) | Gamad | c) | 12/31/19 | g) | 12/31/2019 | c) | 204,850.57 | [7 empty] | 2
[13 empty] | d) | - | d) | - | [11 empty] | 2
[7 empty] | Jct. Bdry. Tagum - Talomo |  |  | Road Maintenance | 12.01 | CBRMC | a) | 407429.19 | a) | 01/03/19 | e) | - | a) | 407429.19 | a) | 100% | c) | 100% | a) | 10 | Completed | 2
[5 empty] | 145 | [7 empty] | b) | Gamad | b) | 01/11/19 | f) | - | b) | 407429.19 | b) | - | d) | - | b) | 50 |  | 2
[13 empty] | c) | BALISONG SAN VICENTE IRRIGATORS ASSOCIATION | c) | 12/31/19 | g) | 12/31/2019 | c) | 168,544.84 | [7 empty] | 2
[13 empty] | d) | - | d) | - | [11 empty] | 2
[7 empty] | San Jose - Sitio Mahayahay, Magwawa |  |  | Road Maintenance | 0.84 | MBA | a) | 7919.35 | a) | 01/03/19 | e) | - | a) | 7919.35 | a) | 100% | c) | 100% | a) | 2 | Completed | 2
[5 empty] | 151 | [7 empty] | b) | 79762.14 | b) | 01/16/19 | f) | - | b) | 7919.35 | b) | - | d) | - | b) | 8 |  | 2
[13 empty] | c) | Gamad | c) | 12/31/19 | g) | 12/31/2019 | c) | 1,509.27 | [7 empty] | 2
[13 empty] | d) | - | d) | - | [11 empty] | 2
[5 empty] | B. 20% DEVELOPMENT FUND CY 2019 | [22 empty] | FS
[5 empty] | Road ID |  | 1. Rehabilitation Of Various Prov'l. Roads and Bridges Dist. 1 |  |  | Road Rehabilitation | KM | MBA | a) | 41465029 | a) | 01/03/19 | e) | - | a) | 41465029 | a) | - | c) | - | a) | 46 | See list of Provincial Roads | FS
[11 empty] | 109.55 |  | b) | Paraguya | b) | 01/03/19 | f) | - | b) | 41465029 | b) | - | d) | - | b) | 920 |  | AC
[5 empty] | 11DAN | [7 empty] | c) | PEO | c) | 12/31/19 | g) | - | c) | - | [7 empty] | AC
[15 empty] | d) | - | [11 empty] | AC
[13 empty] | d) | 261 days | d) | - | [11 empty] | AC
[10 empty] | Road Rehabilitation |  |  | a. )P 500,000.00 |  | a.) 01/31/19 |  |  |  | a.) 500,000.00 | [8 empty] | 1
1 | [6 empty] | Purok 10 Pob. Road, New Corella | [7 empty] | b.) Feb. 16, 2019 |  |  |  | b.) 500,000.00 | [7 empty] | Completed | 1
[17 empty] | g.) Feb. 28, 2019 | [10 empty] | 1
1
[10 empty] | Road Rehabilitation |  |  | a.)1,815,000.00 |  | a.) 01/31/19 |  |  |  | a.) 1,815,000.00 | [8 empty] | 1
1 | [6 empty] | Purok 7 Pob- Jct. New Sambog | [7 empty] | b.)March 1, 2019 |  |  |  | b.) 1,815,000.00 | [7 empty] | Completed | 1
[17 empty] | g.) May 15, 2019 | [10 empty] | 1
1
[10 empty] | Road Rehabilitation |  |  | a.) 1,389,000.00 |  | a.) 01/31/19 |  |  |  | a.) 1,389,000.00 | [7 empty] | Completed with a savings of P303,898.08 furtherance and is for implementation | 1
1 | [6 empty] | Del Pilar- El Unido Road | [5 empty] | b.) Fabian |  | b.) March 18,2019 |  |  |  | a.) 1,389,000.00 | [8 empty] | 1
[17 empty] | g.) May 8, 2019 | [10 empty] | 1
[7 empty] | SUPPLEMENTAL BUDGET NO 4 CY 2019 / CONTINUING APPROPRIATION | [20 empty] | AC
AC
[13 empty] | a.) 7,742,775.95 | [5 empty] | a.) 7,742,775.95 | [7 empty] | Waiting for the delivery of materials | 1
1 | [6 empty] | Impvt. of Km. 9 Sagayen - Sawata Provincial Road Phase II | [5 empty] | b.) Kenny | [5 empty] | b.) 7,742,775.95 | [8 empty] | 1
1
1
[5 empty] | Road ID |  | 1. Rehabilitation Of Various Prov'l. Roads and Bridges Dist 2 |  |  | Road Rehabilitation | KM | Admin | a) | 46740117 | a) | 01/03/19 | [10 empty] | See list of Provincial Roads | AC
[11 empty] | 115.62 |  | b) | Matuguinas | b) | - | [11 empty] | AC
[5 empty] | 11DAN | [7 empty] | c) | PEO | c) | - | [11 empty] | AC
[15 empty] | d) | - | [11 empty] | AC
[13 empty] | d) | 261 days | d) | - | [11 empty] | AC
[10 empty] | Road Rehabilitation |  |  | a.) 515,000.00 |  | a.) 03/12/19 |  |  |  | a.) 515,000.00 | [8 empty] | 2
1 | [6 empty] | Jct. Highway -Tubod - Bagong Silang | [5 empty] | b.) Clar |  | b.) March 18, 2019 |  |  |  | b.) 515,000.00 | [7 empty] | Completed | 2
[17 empty] | g.) June 15, 2019 | [10 empty] | 2
2
[10 empty] | Road Rehabilitation |  |  | a.) 390,000.00 |  | a.) 03/12/19 |  |  |  | a.) 390,000.00 | [8 empty] | 2
1 | [6 empty] | Cebulano- Luceta | [5 empty] | b.) Clar |  | b.) March 8, 2019 |  |  |  | b.) 390,000.00 | [7 empty] | Completed | 2
[17 empty] | g.) June 15, 2019 | [10 empty] | 2
2
[10 empty] | Road Rehabilitation |  |  | a.) 295,000.00 |  | a.) 03/12/19 |  |  |  | a.) 295,000.00 | [8 empty] | 2
1 | [6 empty] | Lower Asuncion - Upper Asuncion | [5 empty] | b.) Clar |  | b.) March 18, 2019 |  |  |  | b.) 295,000.00 | [7 empty] | Completed | 2
[17 empty] | g.) June 15, 2019 | [10 empty] | 2
2
[10 empty] | Road Rehabilitation |  |  | a.) 1,220,000.00 |  | a.) 03/12/19 |  |  |  | a.) 1,220,000.00 | [8 empty] | 2
1 | [6 empty] | Jct. Highway - Sto. Nino - La Paz - San Vicente | [5 empty] | b.)Obar |  | b.) March 18, 2019 |  |  |  | b.) 1,220,000.00 | [7 empty] | Completed | 2
[17 empty] | g.) Sept. 30, 2019 | [10 empty] | 2
2
[7 empty] | Alejal - Alemag |  |  | Road Rehabilitation | 1.79 |  | a) | 970000 | a) | 2019-03-18 | e) | - | a) | 970000 | a) | 100% | c) | 100% | a) | 7 | Completed. Financially completed | 2
1 |  |  |  |  | 092 | [7 empty] | b) | Gamad/Clar | b) | 2019-05-20 | f) | - | b) | 970000 | b) | 100 | d) | 0% | b) | 20 |  | 2
[13 empty] | c) | - | c) | 2019-09-12 | g) | Sept. 30, 2019 | c) | - | [7 empty] | 2
[13 empty] | d) | - | d) | - | [11 empty] | 2
[10 empty] | Road Rehabilitation |  |  | a.) 640,000.00 |  | a.) 03/12/19 |  |  |  | a.) 640,000.00 | [8 empty] | 2
1 | [6 empty] | Mabaus - Cabay -angan | [5 empty] | b.)Clar |  | b.) Maech 18, 2019 |  |  |  | a.) 640,000.00 | [7 empty] | Completed | 2
[17 empty] | g.) July 30, 2019 | [10 empty] | 2
2
[10 empty] | Road Rehabilitation |  |  | a.) 280,000.00 |  | a.) 03/12/19 |  |  |  | a.) 280,000.00 | [8 empty] | 2
1 | [6 empty] | Mabaus - Salvacion | [5 empty] | b.)Clar |  | b.) March 18, 2019 |  |  |  | a.) 280,000.00 | [8 empty] | 2
[17 empty] | g.) June 30, 2019 | [9 empty] | Completed | 2
2
[7 empty] | Dujali - New Casay |  |  |  | 3.2 | Admin | a) | 640000 | a) | 2019-05-16 | e) | - | a) | 640000 | a) | 100% | c) | 100% | a) | 10 |  | 2
1 |  |  |  |  | 106 | [7 empty] | b) | Gamad/Clar | b) | 2019-06-17 | f) | 40 | b) | 640000 | b) |  | d) | - | b) | 40 | Completed | 2
[13 empty] | c) | - | c) |  | g) | 10/15/2019 | c) | - | [7 empty] | 2
[13 empty] | d) | - | d) | - | [11 empty] | 2
[10 empty] | Road Rehabilitation |  |  | a.) 450,000.00 |  | a.) 03/12/19 |  |  |  | a.) 450,000.00 | [8 empty] | 2
1 | [6 empty] | New Casay - Bugtong Talisay | [5 empty] | b.)Clar |  | b.) March 18, 2019 |  |  |  | a.) 450,000.00 | [7 empty] | Completed | 2
[17 empty] | g.)June 30, 2019 | [10 empty] | 2
2
[10 empty] | Road Rehabilitation |  |  | a.)220,000.00 |  | a.) 03/12/19 |  |  |  | a.)220,000.00 |  | a.) 100 % |  | c.)100% |  |  |  |  | 2
1 | [6 empty] | Purok 6 Cabay-angan - Esti | [5 empty] | b.) Gamad |  | b.) March 18, 2019 |  |  |  | a.)220,000.00 | [7 empty] | Completed | 2
[17 empty] | g.) June 30, 2019 | [10 empty] | 2
2
[10 empty] | Road Rehabilitation |  |  | a.)250,000.00 |  | a.) March 12, 2019 | [5 empty] | a.) 100 % |  | c.)100% |  |  |  |  | 2
1 | [6 empty] | Dujali - Sitio Pawas | [5 empty] | b.) Gamad |  | b.) March 18, 2019 | [11 empty] | Completed | 2
[17 empty] | g.) Jun 30, 2019 | [10 empty] | 2
2
[10 empty] | Road Rehabilitation |  |  | a.) 280,000.00 |  | a.) March 12, 2019 | [5 empty] | a.) 100 % |  | c.)100% |  |  |  |  | 2
1 | [6 empty] | Purok 1 to Purok 2 Sitio Pawas | [6 empty] | b.) Gamad | b.) March 18, 2019 | [11 empty] | Completed | 2
[17 empty] | g.) Jun 30, 2019 | [10 empty] | 2
2
[7 empty] | San Miguel - Crossing Kinamayan |  |  | Road Rehabilitation | 2.8 | Admin | a) | 560000 | a) | 2019-06-25 | e) | - | a) | 560000 | a.) 100 % |  | c.)100% |  | a) | - |  | 2
1 |  |  |  |  | 120 | [7 empty] | b) | Nasol | b) | Sept. 19, 2019 | f) | - | b) | 560000 | b) | - | d) | - | b) | - | Completed | 2
[13 empty] | c) | - | c) | - | g) | Nov. 30, 2019 | c) | - | [7 empty] | 2
[13 empty] | d) | - | d) | - | [11 empty] | 2
[7 empty] | Kinamayan - Lunga-og |  |  | Road Rehabilitation | 2.59 | Admin | a) | 520000 | a) | 2019-03-18 | e) | - | a) | 520000 | a) | 100% | c) | 100% | a) | 9 | Completed | 2
1 |  |  |  |  | 126 | [7 empty] | b) | Gamad/Clar | b) | 5/202/019 | f) | - | b) | 520000 | b) | - | d) | - | b) | 36 |  | 2
[13 empty] | c) | - | c) |  | g) | Sept. 30, 2019 | c) | - | [7 empty] | 2
[13 empty] | d) | - | d) | - | [11 empty] | 2
[13 empty] | a.) 540,000.00 |  | a.) March 12, 2019 |  |  |  | a.) 540,000.00 |  | a.)100% |  | c.)100% |  |  |  | Completed | 2
1 | [6 empty] | Nafco - Bobongon |  |  | Road Rehabilitation |  |  | b. Gamad |  | b.) march 18, 2019 |  |  |  | b.) 540,000.00 | [8 empty] | 2
[17 empty] | g.) June 30, 2019 | [10 empty] | 2
2
2
[7 empty] | Prk. Narafil - Prk. Daisy Magupising |  |  | Road Rehabilitation | 19.16 | Admin | a) | 300117 | a) | 2019-06-25 | e) | - | a) | 300117 | a) | 100% | c) | 100% | a) | - | Completed | 2
1 |  |  |  |  | 148 | [7 empty] | b) | Gamad/Clar | b) | Sept. 16, 2019 | f) | - | b) | 300117 | b) | - | d) | - | b) | - |  | 2
[13 empty] | c) | - | c) | - | g) | Oct. 18, 2019 | c) | - | [7 empty] | 2
[13 empty] | d) | - | d) | - | [11 empty] | 2
[5 empty] | 2. Various of Local Roads & Drainage Development Project (Provincewide) |  |  |  |  | Road Drainage rehabiliated |  | Admin | a) | 15000000 | [12 empty] | See projects listed below | 2
[13 empty] | b) | Paraguya | [13 empty] | AC
[13 empty] | c) | PEO | [13 empty] | AC
[13 empty] | d) | - | [13 empty] | AC
[7 empty] | Rehab. of Anibongan-Salvacion-Cabay-angan Provincial Road with Drainage |  |  | Road Drainage rehabiliated | - | - | a) | 2000000 | a) | 2019-01-14 | e) | - | a) | 2000000 | a) | 100% | c) | 100% | a) | 1 | Completed | 2
1 |  |  |  |  | 2.1 | [7 empty] | b) | Toquero | b) | 2019-05-22 | f) | - | b) | 2000000 | b) | - | d) | - | b) | 4 | Fiancial obligation still on process | 2
[13 empty] | c) | PEO | c) | 2019-08-04 | g) | Dec. 31, 2019 | c) | - | [7 empty] | 2
[13 empty] | d) | - | d) | - | [11 empty] | 2
[7 empty] | Rehab./Impv't. of Sto. Tomas-Bdry. Mamacao Provincial Road |  |  | Road Drainage rehabiliated | - | Admin | a) | 1500000 | a) | 2019-01-14 | e) | - | a) | 1500000 | a) | 100% | c) | 100% | a) | - | Completed Financial obligation on process
1 |  |  |  |  | 2.4 | [7 empty] | b) | Toquero | b) | 2019-05-31 | f) | 60 | b) | 1500000 | b) | - | d) | - | b) | - |  | 2
[13 empty] | c) | PEO | c) | 2019-07-15 | g) | Dec. 31, 2019 | c) | - | [7 empty] | 2
[13 empty] | d) | - | d) | - | [11 empty] | 2
[5 empty] | 4. Various Government Buildings and Facilities Development Project (Provincewide) |  |  |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of recipients | - | Admin | a) | 27000000 | [12 empty] | See projects listed below | 2
[13 empty] | b) | Medalla | [13 empty] | AC
[13 empty] | c) | PEO | [13 empty] | AC
[13 empty] | d) | - | [13 empty] | AC
[7 empty] | Const. of GYM Bleacher at Suaybaguio Rina, Elem. School |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of recipients | - | #REF! | a) | 1000000 | a) | - | e) | - | a) | 1000000 | a) | 100% | c) | 100% | a) | - | Completed | 1
| 1 |  |  |  |  | 11 | [6 empty] | b) | Mayang | b) | 6/3/2019 | f) | - | b) | 1000000 | b) | 64 | d) | 0% | b) | - |  | 1
[13 empty] | c) | PEO | c) | 8/01/2019 | g) |  | c) | - | [7 empty] | 1
[13 empty] | d) | - | d) | - | [11 empty] | 1
[5 empty] | 5. Stimulus Projects for Various Barangays a. 20% Development Fund CY 2019 |  |  |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | Admin | a) | 41500000 | [12 empty] | See projects listed below | 2
[13 empty] | b) | Medalla | [13 empty] | AC
[13 empty] | c) | PEO | [13 empty] | AC
[13 empty] | d) | - | [13 empty] | AC
AC
[5 empty] | IGCS | [22 empty] | 2
[5 empty] | 5.42 |  | Rehab. Of Health Center, Aumbay, IGCS |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) | Feb. 28, 2019 | e) | - | a) | 500000 | a) |  | c) | 48.32% | a) | 3 | Completed Financial obligation on process | AC
| 1 | [11 empty] | b) | Pacquiao | b) | 7/10/2019 | f) | - | b) | 500000 | b) | - | d) |  | b) | 15 |  | 2
[13 empty] | c) | Admin | c) | 10/7/2019 | g) | - | c) | - | [7 empty] | 2
[13 empty] | d) | 90 CD | d) | - | [11 empty] | 2
[5 empty] | 5.46 |  | Rehab. Of Brgy. Health Center, Mambago-A, IGCS |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) | Feb. 28, 2019 | e) | - | a) | 500000 | a) |  | c) | 75.61% | a) | 3 | Completed Financial obligation on process | 2
| 1 | [11 empty] | b) | Ganaba | b) | 07/2019 | f) | - | b) | 500000 | b) |  | d) |  | b) | 15 |  | 2
[13 empty] | c) | Admin | c) | 8/23/2019 | g) | - | c) | - | [7 empty] | 2
[13 empty] | d) | 45 CD | d) | - | [11 empty] | 2
[5 empty] | 6. Rural Electrification Project (Provincewide) |  |  |  |  | Powerlines/posts installed & rehabilitated | - | - | a) | 5000000 | [12 empty] | See projects listed below | 2
[13 empty] | b) | Kim Pao Lu | [13 empty] | AC
[13 empty] | c) | - | [13 empty] | AC
[13 empty] | d) | - | [13 empty] | AC
C. 5% CALAMITY FUND CY 2019
[5 empty] | 3 |  | Improvement of roads, drainage and canal |  |  | Protection dikes/slope protection | - | - | a) | 3000000 | [12 empty] | See projects listed below | 2
[13 empty] | b) | Paraguya | [13 empty] | AC
[13 empty] | c) | PEO | [13 empty] | AC
[13 empty] | d) | - | [13 empty] | AC
[5 empty] | a. |  | Rehab./Impv't. of New Casay-Bugtong Talisay Provincial Road (Ph.II) |  |  | creeks and canRoads/Draiange/canals rehab/improved | - | - | a) | 500000 | a) | 2019-03-12 | e) | - | a) | 500000 | a) | 100% | c) | 100% | a) | 12 | Completed | AC
1 | [12 empty] | b) | Toquero | b) | 2019-05-30 | f) | - | b) | 500000 | b) | - | d) | - | b) | 120 |  | 2
[13 empty] | c) | Admin | c) | 2019-07-30 | g) |  | c) | - | [7 empty] | 2
[13 empty] | d) | - | d) | - | [11 empty] | 2
27 | 9 | 5 | 1
[7 empty] | Mark | Municipality/City |  | Color
[7 empty] | 1 | Asuncion |  | Red
[7 empty] | 2 | B.E. Dujali |  | Yellow
[6 empty] | GF- GENERAL FUND | 3 | Carmen |  | Blue | [10 empty] | TF - TRUST FUND (NATIONAL FUNDED PROJECT)
[6 empty] | 20% DF - 20% DEV'T. FUND | 4 | Kapalong |  | Pink | [10 empty] | a) SLRF - Special Local Road Fund
[6 empty] | 5% CF - 5% CALAMITY FUND | 5 | New Corella |  | Gray | [10 empty] | b) KALSADA - Konkreto at Ayos na Lansangan Tungo sa Pangkalahatang Kaunlaran
[6 empty] | CO - CAPITAL OUTLAY | 6 | San Isidro |  | Orange | [10 empty] | c) PRDP - Philippine Rural Development Projects
[6 empty] | CONG. FUND - CONGRESSIONAL FUND | 7 | Sto Tomas |  | Sky Blue | [10 empty] | d) SELAP - Support to Emergency and Livelihood Assistance Project
[7 empty] | 8 | Talaingod |  | Violet | [10 empty] | e) PAMANA - Payapa at Masaganang Pamayanan
[6 empty] | SEF - SPECIAL EDUCATIONAL UFND | 9 | Panabo City |  | Brown | [10 empty] | f) CBRMC - Community Based Road Maintenance Contracting
[7 empty] | 10 | IGACOS |  | Yellow Green | [10 empty] | g) MBC - Maintenance by Contract
[7 empty] | 11 | Tagum City |  | Green | [10 empty] | h) PCF-Performance Challenge Fund-DILG
i) FMRDP - Farm to Market Road
j.) CMGP - Conditional Grant to Provinces
k.) OPAPP - Office of the President Adviser on the Peace Process
l.) LGSF-AM - Local Government Support Fund Assistance to Municipalities
[5 empty] | Prepared by: |  |  |  | Checked | [12 empty] | Recommending Approval
Noted
[5 empty] | GILBERT G. MAMBULAO JR |  |  |  | ELISA A. BARCENA | TESSIE G. ABABON | [9 empty] | JIVELLYN B. CO | [5 empty] | GLENN A. OLANDRIA
[5 empty] | Engineer II |  |  |  | Engineer IV- Engineering Dist 1, Area Engineer |  | Engineer IV-Engineering Dist 2, Area Engineer | [9 empty] | Asst. PG-Department Head |  |  |  |  | Provincial Engineer
[9 empty] | EDWIN S. MISA |  |  |  | MARILOU A. FORONDA
[9 empty] | Engineer IV- PDPM Division Head |  |  |  | Engineer IV- QC Division Head

## On-going(South) COV (hidden)
PROVINCE OF DAVAO DEL NORTE
ACCOMPLISHMENT REPORT
FOR THE MONTH OF FEBRUARY 2020
SECTOR: ECONOMIC (INFRASTRUCTURE DEV'T. PROGRAM)
OFFICE/AGENCY: PROVINCIAL ENGINEER'S OFFICE
AREA: 2ND ENGINEERING DISTRICT - ON-GOING PROJECTS
| Name of Project |  |  |  | Type | Physical | Mode | PROJECT DATA | [5 empty] | Financial (000) |  | Physical Accomplishment |  |  |  | Employment |  | REMARKS
[5 empty] | of | Target | of | a) Project Cost |  | a) | Date A lot. Rel. | e) | # of days suspended | a) Program |  | a) Planned |  | c) Actual |  | Generated
[5 empty] | Project | (Descrip | Impl. | b) Project Engineer |  | b) | Date Started | f) | # of days extended | b) Allotment |  | b) Revised |  | d) Slippage |  | a) # of Persons | # of Persons
[5 empty] | (Location) | tion) |  | c) Implementor |  | c) | Target Compl. Date | g) | Date completed | c) Disbursement | [5 empty] | b) | Man-days
[8 empty] | d) Duration |  | d) | Revised Compl. Date
| I. | PROJECTS UNDER THE CONTINUING APPROPRIATION | [20 empty] | AC |  | 893809.45
|  | A. | Supplemental Budget # 1 CY 2015 | [19 empty] | 2
|  | C. | Trust Fund | [19 empty] | FS
|  |  | 1. PRDP | [19 empty] | AC
|  |  |  | Rehab. of Esperanza-Pob. Sto. Tomas, | Road | 12.774 | Contract. | a) | 117,410,426.30 | a) | CY 2014 | e) | - | a) | 117,410,426.30 | a) | 100% | c) | 89.82% | a) | 20 | On-going . Request for time extension on process. Waiting for approval of variation order for billing | 2
|  |  | 1.1 |  |  |  |  | b) | Palero | b) | 2017-03-22 | f) | - | b) | 117,410,426.30 | b) | 96% | d) | -6.179% | b) | 600 |  | 2
[8 empty] | c) | Alzam | c) | 2019-07-22 | g) | - | c) | 113,335,769.31 | [7 empty] | 2
[8 empty] | d) | 853 CD | d) | - | [11 empty] | 2
|  |  | SLRF 2015 | [6 empty] | a) |  | e) | 65 days | a) |  | a) | 100% | c) | 100% | a) | 3 | Completed as per POW, Financial Documents on Process | 2
|  |  | Rehab. of Jct. Highway-Tuganay-Anibongan-BE Dujali-Kinamayan Provincial Road (Furtheranace) |  | Slope protection | - | - | a) | 1911175.99 | b) | 2019-02-18 | f) | 47 days | b) |  | b) |  | d) | 0% | b) | 60 |  | 2
[8 empty] | b) | Balbastro | c) | 2019-09-21 | g) | 9/21/2019 | c) | [8 empty] | 2
[8 empty] | c) | Admin | d) | [12 empty] | 2
[8 empty] | d) | - | [13 empty] | 2
|  | D. | 20% Development Fund CY 2016 | [19 empty] | FS
|  |  | 1. Water System Development Projects |  | Water |  | Admin | a) | 2000000 | [12 empty] | See project listed below | AC
[5 empty] | System |  |  | b) | - | [13 empty] | AC
[8 empty] | c) | PEO | [13 empty] | AC
d)
|  |  |  | Development of Deepwell Source and Install. Of Pipelines, Licup, samal Dist. IGACOS (Previously Deepwell Drilling at Licup) | Water |  | Admin | a) | 645,000.00 | a) | 2018-11-08 | e) | - | a) | 645,000.00 | a) | 82.76% | c) | 72.89% | a) | 4 | drilling works completed 7/15/2019 but insufficient water source | 2
[5 empty] | System |  |  | b) | Diosanta | b) | 2019-03-01 | f) | - | b) | 645,000.00 | b) | - | d) | -9.87% | b) | 100 |  | 2
|  |  | 1.1 |  |  |  |  | c) | PEO | c) | 2019-05-10 | g) | - | c) | - | [7 empty] | 2
[8 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | 3. Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) |  | Bldgs./ | - | Admin | a) | 9,000,000.00 | [12 empty] | See project listed below | AC
[5 empty] | Fence |  |  | b) | Foronda/Ababon | [13 empty] | AC
[8 empty] | c) | PEO | [13 empty] | AC
|  |  |  | 3.1 Construction of Provincial Training Center, Compound Fence, Kinawitnon, Babak District, IGCS | Fence |  | Admin | a) | 940,000.00 | a) | 2017-09-19 | e) | - | a) | 940,000.00 | a) | 68.00% | c) | 75.00% | a) | - | Temporarily suspended 4/23/18 due to undemolished structures of illegal settlers | 2
[8 empty] | b) | Pacquiao | b) | 2018-03-12 | f) | - | b) | 940,000.00 | b) | - | d) | - | b) | - |  | 2
[8 empty] | c) | PEO | c) | 2018-06-19 | g) | - | c) | 933,418.80 | [7 empty] | 2
[8 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | 3 | Impv't of Brgy. Hall, Tagpopongan |  |  |  | a) | 500000 | a) | 11/28/17 | e) | 259 | a) | 500000 | a) | - | c) | 100% | a) | - | Completed based on POW. Financial Documents on process | 2
|  |  |  | IGACOS |  |  |  | b) | Roque | b) | 9/17/2018 | f) | 30 | b) | 500000 | b) | - | d) | - | b) | - |  | 2
[8 empty] | c) | PEO | c) | 12/30/2018 | g) | - | c) | - | [7 empty] | 2
[8 empty] | d) | - | d) | 10/15/2019 | [11 empty] | 2
|  | F. | SDH IGCS - CONST. IN PROGRESS - BLGS. CY 2017 | [19 empty] | AC
|  |  | 1 | Construction Perimeter Fence Ph.II (Hospital | Fence |  | Admin | a) | 1,305,000.00 | a) | 11/10/17 | e) | 392 | a) | 1,305,000.00 | a) | 100% | c) | 100% | a) | 4 | Completed based on POW. Financial Documents on process | AC
|  |  |  | Compound) Samal District Hospital, IGCS |  |  |  | b) | Porras | b) | 03/12/18 | f) | 45 | b) | 1,305,000.00 | b) | - | d) | 1% | b) | 30 |  | AC
[8 empty] | c) | PEO | c) | 06/19/18 | g) | - | c) | 958,597.98 | [7 empty] | AC
[8 empty] | d) | - | d) | [12 empty] | AC
|  | F. | Trust Fund 2017 | [19 empty] | FS
|  | 8 |  | Road Upgrading of Dagohoy - Daligdigon | Road | 2.532 km | Contract | a) | 58048310.68 | a) | CY 2017 | e) | - | a) | 58048310.68 | a) | 100.00% | c) | 100% | a) | 16 | Completed as per Physical Accomplishment, Financial Documents on Process | 1 | 1
|  |  |  | Provincial Road |  |  |  | b) | Fabiala | b) | 01/05/18 | f) | 205 CD | b) | 58048310.68 | b) | - | d) | 0% | b) | 480 |  | 1
[8 empty] | c) | PUREGOLD | c) | 11/18/18 | g) | - | c) | 29,572,637.70 | [7 empty] | 1
[8 empty] | d) | 246 CD | d) | 03/31/19 | [11 empty] | 1
|  |  |  | Impv’t. of Maligaya-New Camiling Prov’l. | Conc. | 2.13 km | Contract. | a) | 50101614.08 | a) | CY 2017 | e) | 76 CD | a) | 57385680 | a) | 100.00% | c) | 100% | a) | 21 | Completed based on POW. Financial Documents on process | 2
|  |  |  | Road w/ Bridge Component,Carmen |  |  |  | b) | Mellomida | b) | 12/18/17 | f) | 209 CD | b) | 57385680 | b) | 100% | d) | 0% | b) | 147 |  | 2
[8 empty] | c) | PUREGOLD CONST. | c) | 02/15/19 | g) | - | c) | 36005452 | [7 empty] | 2
[8 empty] | d) | 376 CD | d) | 07/31/19 | [11 empty] | 2
|  |  |  | Road Upgrading of FDR. Rd.3 – | Conc. | 10.359 km | Contract. | a) | 119901954.82 | a) | CY 2017 | e) | 47 CD | a) | 119901954.82 | a) | 100.00% | c) | 100% | a) | 10 | Completed based on POW, Financial Documents on Process | 2
|  |  |  | Kimamon – Luna Provincial Road, |  |  |  | b) | Comidoy | a) | 12/29/17 | f) | 198 CD | b) | 119901954.82 | b) | 100% | d) | 100% | b) | 220 |  | 2
|  |  |  | Sto. Tomas |  |  |  | c) | GP & H CONST. | c) | 12/12/18 | g) | - | c) | 119901954.82 | [7 empty] | 2
[8 empty] | d) | 326 CD | d) | 2019-07-29 | [11 empty] | 2
|  |  |  | Road Upgrading of Anahaw-Maligaya | Conc. | 5.18 km | Contract. | a) | 78,228,121.56 | a) | CY 2017 | e) | - | a) | 78,228,121.56 | a) | 100.00% | c) | 100% | a) | 30 | 100% as of August 31, 2019 | 2
|  |  |  | Provincial Road, Carmen |  |  |  | b) | Fernandez | b) | 12/24/17 | f) | 306 CD | b) | 78,228,121.56 | b) | 100% | d) | 0% | b) | 660 | Subject for liquidated damages | 2
[8 empty] | c) | MONOLITHIC CONST. | c) | 03/31/19 | g) | - | c) | 76,214,361.38 | [7 empty] | 2
[8 empty] | d) | 210 CD | d) | 2019-06-05 | [11 empty] | 2
|  |  | 1. OPPAP-PAMANA | [19 empty] | AC
|  |  |  | 1.2 Const. of Trading Post, Storage Building with (1) unit Hauling Truck, Prk. Ramihan Datu Abdul, Panabo City | Bldg. |  | Contract | a) | 3,975,000.00 | a) | CY 2017 | e) | - | a) | 3,975,000.00 | a) | - | c) | 7.81% | a) | - | On-going | 2
[8 empty] | b) | - | b) | 2019-11-21 | f) | - | b) | 3,975,000.00 | b) | - | d) | - | b) | - |  | 2
[8 empty] | c) | - | c) | 2019-04-05 | g) | - | c) | - | [7 empty] | 2
[8 empty] | d) | - | d) | - | [11 empty] | 2
|  |  |  | 1.2 Construction of Tribal Hall, Sto. Tomas | Bldg. |  | Admin | a) | 500000 | a) | CY 2018 | e) | - | a) | 500000 | a) | 100% | c) | 89.5% | a) | 7 | Suspended 6/28/2019, Suspended due to Delivery of Materials J.O, For time extension | 2
[8 empty] | b) | Roque | b) | 2019-05-22 | f) | - | b) | 500000 | b) | - | d) | 0.79% | b) | 110 |  | 2
[8 empty] | c) | - | c) | 2019-07-31 | g) | - | c) | - | [7 empty] | 2
[8 empty] | d) | - | d) | - | [11 empty] | 2
|  | 8 | 1.1 | Construction of 1 unit School Building | Bldg. |  | Admin | a) | 1100000 | a) | 02/19/18 | e) | - | a) | 1100000 | a) | 100 | c) | 100 | a) | 6 | Completed based on POW. Financial Documents on process | 1
|  |  |  | Lumabag, Talaingod |  |  |  | b) | Dadula | b) | 03/20/19 | f) | 27 CD | b) | 1100000 | b) |  | d) |  | b) | 30 |  | 1
[8 empty] | c) | PEO | c) | 05/19/19 | g) | 06/30/2019 | c) | 595230.5 | [7 empty] | 1
[8 empty] | d) | 60 CD | d) | - | [11 empty] | 1
|  | G. | 20% Development Fund CY 2018 | [19 empty] | FS
|  |  | 1.2 | Rehabilitation of Brgy. Peñaplata Barangay | Road |  | Admin | a) | 139000 | a) | 04/25/18 | e) | 66 CD | a) | 139000 | a) | 100% | c) | 100 | a) | 1 | Completed 8/31/2019 | 2
|  |  |  | Road, IGACOS |  |  |  | b) | Porras/Pacquiao | b) | 8/16/2019 | f) | 225 CD | b) | 139000 | b) | - | d) | - | b) | 1 |  | 2
[8 empty] | c) | PEO | c) | 8/31/2019 | g) | - | c) | 139000 | [7 empty] | 2
[8 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | 1.3 | Rehabilitation of Brgy. Adecor Barangay | Road |  | Admin | a) | 138000 | a) | 04/25/18 | e) | 66 CD | a) | 138000 | a) | 60.00% | c) | 60.00% | a) | - | Completed as per POW. Financial Documents on process | 2
|  |  |  | Road, IGACOS |  |  |  | b) | Porras/Pacquiao | b) | 10/18/18 | f) | 225 CD | b) | 138000 | b) | - | d) | - | b) | - |  | 2
[8 empty] | c) | PEO | c) | 10/27/19 | g) | - | c) | 111,872.00 | [7 empty] | 2
[8 empty] | d) | - | d) | 10/15/2019 | [11 empty] | 2
|  |  | 1.4 | Rehabilitation of Brgy. Pob. Kaputian | Road |  | Admin | a) | 138000 | a) | 04/25/18 | e) | - | a) | 138000 | a) | 100% | c) | 100% | a) | 4 |  | 2
|  |  |  | Barangay Road, IGACOS |  |  |  | b) | Porras/Pacquiao | b) | 2019-08-08 | f) | - | b) | 138000 | b) | - | d) | - | b) | 36 | Completed Sept. 22, 2019 | 2
[8 empty] | c) | PEO | c) | 9/22/2019 | g) | 9/22/2019 | c) | - | [7 empty] | 2
[8 empty] | d) | 6/13/19 | d) | - | [11 empty] | 2
|  |  | 2.2 Construction of Water System Projects in Component LGUs |  | Water | - | - | a) | 9750000 | [12 empty] | See list of projects | AC
[5 empty] | System |  |  | b) | Diosanta | [13 empty] | AC
[8 empty] | c) | PEO | [13 empty] | AC
[8 empty] | d) | - | [13 empty] | AC
|  |  |  | Impv't. of Water System, Brgy. Poblacion | Water |  | Admin | a) | 1250000 | a) | 08/24/18 | e) | - | a) | 1250000 | a) | 100% | c) | 85.39% | a) | 8 | Completed (contract by Zular3-Az) September 15, 2019 | 2
|  |  |  | Kaputian (Level II) | system |  |  | b) | Porras | b) | 05/3/19 | f) | - | b) | 1250000 | b) | - | d) | -14.61 | b) | 160 |  | 2
[8 empty] | c) | Contract | c) | 08/30/19 | g) | 09/15/2019 | c) | - | [7 empty] | 2
[8 empty] | d) | - | d) | - | [11 empty] | 2
|  |  |  | 2.2.5 Potable Water System at Brgy. San Remegio Kaputian (Level II WS), Samal | Water |  | #REF! | a) | 3625000 | a) | 2018-10-25 | e) | - | a) | 3625000 | a) | 49.51% | c) | 54.96% | a) | 3 | On-going | 2
[5 empty] | system |  |  | b) | Diosanta | b) | 2019-07-16 | f) | - | b) | 3625000 | b) | - | d) | 4.62 | b) | 20 |  | 2
[8 empty] | c) | Admin | c) | 2019-12-01 | g) | - | c) | - | [7 empty] | 2
[8 empty] | d) | - | d) | - | [11 empty] | 2
|  | 11 | 4.3 | Construction of Multi-Purpose Bldg. | #REF! | 303.75 sq.m | #REF! | a) | 6748000 | a) | 12/11/18 | e) | - | a) | 6748000 | a) |  | c) | 100% | a) | 25 | Completed | 1
|  |  |  | (PENRO Building), Mankilam, Tagum City |  |  |  | b) | Pasiona/Juan | b) | 10/16/18 | f) | 109 | b) | 6748000 | b) | - | d) |  | b) | 750 |  | 1
|  |  |  | (Part of 8,548,000.00) |  |  |  | c) | PEO | c) | 9/13/2019 | g) | - | c) | 6560497.45 | [7 empty] | 1
|  |  |  | (P1,800,000.00 - SB # 3 CY 2017) |  |  |  | d) | 256 CD | d) | 06/30/19 | [11 empty] | 1
|  | 3 | 4.4 | Repair/Rehab. Of PEO Building (2nd District), Carmen | #REF! |  | Admin | a) | 2250000 | a) | 08/10/18 | e) | - | a) | 2250000 | a) | 100% | c) | 100% | a) | 18 | Completed based on POW. Financial Documents on process | 2
[8 empty] | b) | Andoy | b) | 02/18/19 | f) | - | b) | 2250000 | b) | - | d) | 0% | b) | 138 |  | 2
[8 empty] | c) | Admin | c) | 08/23/19 | g) | - | c) | 1577344.8 | [7 empty] | 2
[8 empty] | d) | - | d) | - | [11 empty] | 2
|  | H. | GENERAL FUND PROPER CY 2018 | [19 empty] | FS
|  |  | STIMULUS PROJECTS | [19 empty] | AC
|  |  | CARMEN | [18 empty] | Plan and POW Approval on process | AC
|  |  | 1 | Completion of Evacuation Center Building, San Isidro, Carmen | Bldg. |  | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - |  | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 2
[8 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | PANABO CITY | [18 empty] | Amended from Const. of New Brgy. Stage due to funding of Phase 1 by the LGU. Plan and POW on process c/o PDPM | AC
|  |  | 1 | Const. of New Brgy. Stage, Phase II San Pedro, Panabo City | Stage |  | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - |  | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 2
[8 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | 2 | Impv't. of Brgy. Road Covered Court, Malativas, Panabo City | Court |  | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Alloted - May 29, 2019, Additional Funding of 500,000.00,SB no. 4 cy 2019 for Allotment Nov 25, 2019 | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 2
[8 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | 3 | Rehab. Of Multi-Purpose Gym & Facililies Maduao, Panabo City | Gym |  | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Request for Allotment on process | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 2
[8 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | 4 | Const. of Multi-Purpose Bldg. Sto. Nino, Panabo City | Bldg. |  | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Plan and POW on process c/o PDPM | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 2
[8 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | 5 | Completion of Canopy at DAPCO Covered Court, Dapco, Panabo City | Court |  | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For Plan preparation by PDPM August 5, 2019 | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 2
[8 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | 6 | Perimeter Fence of Day Care Center I & II, Nanyo, Panabo City | Bldg. |  | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For inspection by PDPM for PLAN and POW as of 7/19/2019 | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 2
[8 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | STO. TOMAS | [18 empty] | For amendment in the AIP 3rd revision | AC
|  |  | 1 | Const. of Multi-Purpose Bldg./Compl. Of Covered Court Canopy, Balagunan, Sto. Tomas | Bldg. |  | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - |  | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 2
[8 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | 2 | Const. of Perimeter Fence of Kinamayan Integ,. School, Kinamayan, Sto. Tomas | Fence |  | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Inspected by PDPM for POW and POW July 31, 2019 | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 2
[8 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | B.E. DUJALI | [19 empty] | AC
|  |  | 1 | Concreting of Brgy. Road Canal, Dujali, B.E. Dujali | Road |  | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For inspection by PDPM for PLAN and POW as of 7/19/2019 | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 2
[8 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | 2 | Concreting of Drainage, Tanglaw, B.E. Dujali | Drainage |  | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For inspection by PDPM for PLAN and POW as of 7/19/2019 | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 2
[8 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | 3 | Const. of Bleacher w/ Canopy (Ph.II) and Upgrading of Flooring, Cabay-angan, B.E. Dujali | Bleacher |  | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Check for pick-up as of July 5, 2019 with check no. 0135071 | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 2
[8 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | 4 | Desilting and Concreting of Drainage-main Collector Canal, New Casay, B.E. Dujali | Bleacher |  | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For inspection by PDPM for PLAN and POW as of 7/19/2019 | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 2
[8 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | 5 | Const. of Brgy. Multi-Purpose Covered Court, Magupising, B.E. Dujali | Bleacher |  | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For inspection by PDPM for PLAN and POW as of 7/19/2019 | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 2
[8 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | IGCS | [19 empty] | AC
|  |  | 1 | Impv't. of Brgy. Water System, Pichon, IGCS | Water |  | Admin | a) | 500000 | a) | 2018-05-31 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For Implementation | 2
[5 empty] | System |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 2
[8 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | 2 | Powerline Expansion Project, Cogon, IGACOS | Water |  | Contract | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For Implementation. | 2
[5 empty] | System |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 2
[8 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | 3 | Water System From Prk. 6 - Prk. 2 - Prk. 5A, Tagbay, IGCS | Water |  | Admin | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For Implementation | 2
[5 empty] | System |  |  | b) | Pacquiao | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 2
[8 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | 4 | Rehab of Multipurpose Hall, Tagdaliao IGACOS | Bldg. |  | Admin | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | proposed realignement due to project ovelap | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 2
[8 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | 5 | Electrification Project, Kanaan, IGACOS | Elect. |  | Admin | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For DANECO staking | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 2
[8 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | 7 | Powerline Expansion Project, Tambo, IGCS | Elect. |  | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Procurement of Materials on process | 2
[8 empty] | b) | Porras | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 2
[8 empty] | c) | Admin | c) | - | g) | - | c) | - | [7 empty] | 2
[8 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | 9 | Construction of Multipurpose Pavement Penaplata, IGCS | Bldg. |  | Admin | a) | 500000 | a) |  | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Amended from Improvement of Brgy Hall due to change Brgy. Priority. Resolution No. 70 series of 2019 dated July 18, 2019. For allotment | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 2
[8 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | 10 | Completion of Kasilak Day Care Center, Sta. Cruz, IGCS | Bldg. |  | Admin | a) | 500000 | a) | 2018-07-05 | e) | - | a) | 500000 | a) | 93.04% | c) | 86.15% | a) | - | On-going | 2
[8 empty] | b) | Porras | b) | 2019-05-20 | f) | - | b) | 500000 | b) | - | d) | -6.89% | b) | - |  | 2
[8 empty] | c) | - | c) | 2019-07-17 | g) | - | c) | - | [7 empty] | 2
[8 empty] | d) | - | d) | 2019-11-30 | [11 empty] | 2
|  |  | 11 | Const. of Concrete fence of New Brgy. Site, San Isidro, IGCS | Fence |  | - | a) | 500000 | a) |  | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For Implementation | 2
[8 empty] | b) | Porras | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 2
[8 empty] | d) | - | d) | [12 empty] | 2
|  |  | 12 | Electrification of Sitio Baongon-Diamond-Mansanitas, Dadatan, IGCS | Elect. |  | - | a) | 500000 | a) |  | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Procurement on process | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 2
[8 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | 13 | Drilling of Water System,Linusotan, IGCS | Water |  | - | a) | 500000 | a) |  | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For amendment. This project scope of work was included on a separate project titled Construction of Potable Water System at Linusotan, IGACOS. | 2
[5 empty] | System |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 2
[8 empty] | d) | - | d) | - | [11 empty] | 2
|  | I. | 5% Calamity Fund CY 2018 | [19 empty] | FS
|  |  | 1. Prevention and Mitigation | [19 empty] | AC
|  | 11 | 1.1.1. | Improvement and Desiltation of Tagum Creek (Phase I and Phase II) | Creek |  | #REF! | a) | 2,000,000.00 | a) | 11/06/18 | e) | - | a) | 2,000,000.00 | a) | 100% | c) | 100% | a) | 5 | Completed | 1 | 1
[8 empty] | b) | Mayang | b) | 03/22/19 | f) | - | b) | 2,000,000.00 | b) | - | d) | 0% | b) | 110 |  | 1
[8 empty] | c) | PEO | c) | 10/31/19 | g) | - | c) | - | [7 empty] | 1
[8 empty] | d) | 224 CD | d) | - | [11 empty] | 1
|  |  | 1.1 Improvement of bridges and cross drainage |  | bridges/drainage |  | Admin | a) | 3000000 | [12 empty] | Declared as savings | AC
[8 empty] | b) | - | [13 empty] | AC
[8 empty] | c) | PEO | [13 empty] | AC
[8 empty] | d) | - | [13 empty] | AC
|  |  | 1.1.1 | Impv't. of Mabaus Cross Drainage | Drainage |  | Admin | a) | 3,000,000.00 | a) | - | e) | - | a) | 3,000,000.00 | a) | - | c) | - | a) | - | Preparation of POW & Plan c/o PDPM | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 3,000,000.00 | b) | - | d) | - | b) | - |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 2
[8 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | 1.2 Revitment of Dike and Slope Protection |  | Dike |  | Admin | a) | 3000000 | [12 empty] | See project listed below | AC
[8 empty] | b) | - | [13 empty] | AC
[8 empty] | c) | Admin | [13 empty] | AC
[8 empty] | d) | - | [13 empty] | AC
|  |  | 1.2.1 | Rehab. Of Dujali-Pawas-San Vicente RDCG-Abutment A&B (Embankment) - Riprapping A&B @ Both Side | Dike |  | Admin | a) | 3,000,000.00 | a) | 2018-11-06 | e) | - | a) | 3,000,000.00 | a) | 100.00% | c) | 98.47% | a) | 10 | Suspended 9/23/2019 | 2
[8 empty] | b) | Sanchez | b) | 2019-02-18 | f) | 145 CD | b) | 3,000,000.00 | b) | 88.56% | d) | -1.53% | b) | 70 |  | 2
[8 empty] | c) | PEO | c) | 2019-05-08 | g) | - | c) | 2263892.44 | [7 empty] | 2
[8 empty] | d) | - | d) | 2019-09-30 | [11 empty] | 2
|  | L. | OPPAP-PAMANA | [19 empty] | FS
|  |  | 1. TRIBAL HALL | [19 empty] | AC
|  | 4 | 1.1 | Construction of Tribal Hall | Bldg. |  | Admin | a) | 500000 | a) | CY 2018 | e) | - | a) | 500000 | a) | 100% | c) | 100% | a) | 5 | Completed as per Physical Accomplishment. Financial Documents on process | 1
|  |  |  | Brgy. Gupitan, Kapalong |  |  |  | b) | Ambrocio | b) | 2/22/2019 | f) | - | b) | 500000 | b) | - | d) | 0% | b) | 150 |  | 1
[8 empty] | c) | PEO | c) | 5/22/2019 | g) | - | c) | - | [7 empty] | 1
[8 empty] | d) | - | d) | - | [11 empty] | 1
|  | 4 | 2.2 | Const. of Processing and Bagsakan Center, | Bldg. | 300 sq.m | Contract | a) | 2500000 | a) | 08/29/18 | e) | - | a) | 2500000 | a) | 100% | c) | 100% | a) | 6 | Completed as per Physical Accomplishment. Financial Documents on process | 1
|  |  |  | Brgy. Gupitan, Kapalong, Davao del Norte |  |  |  | b) | Ambrucio | b) | 02/12/19 | f) | - | b) | 2500000 | b) | - | d) | 0% | b) | 180 |  | 1
[8 empty] | c) | Alpha & Omega | c) | 05/12/19 | g) | - | c) | 156000 | [7 empty] | 1
[8 empty] | d) | 120 CD | d) | - | [11 empty] | 1
|  |  | 1. TRADING POST STORAGE | [19 empty] | AC
|  |  | 1.1 | Trading Post, Storage and Hauling Truck, Purok Ramihan, Datu Abdul, Panabo City | Bldg. |  | - | a) | 4000000 | a) | CY 2018 | e) | - | a) | 4000000 | a) | 3.74% | c) | 1.91% | a) | - | On-going | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 4000000 | b) | - | d) | - | b) | - |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 2
[8 empty] | d) | - | d) | - | [11 empty] | 2
|  | R. | LOCAL GOVERNMENT SUPPORT FUND (LGSF) CY 2018 | [19 empty] | FS
|  | 1 | 1 | Road Upgrading of San Vicente - Butay Provincial Road | Road |  | Contract | a) | 19949581.18 | a) | CY 2018 | e) | - | a) | 19949581.18 | a) | 100% | c) | 100% | a) | 18 | Completed as per Physical Accomplishment. Financial Documents on process | 1
[8 empty] | b) | Aclaracion | b) | 11/19/18 | f) | 28 CD | b) | 19949581.18 | b) | 100% | d) | 0% | b) | 396 |  | 1
[8 empty] | c) | Alpha & Omega | c) | 06/08/19 | g) | 06/26/2019 | c) | 9,685,667.31 | [7 empty] | 1
[8 empty] | d) | 202 CD | d) | 07/06/19 | [11 empty] | 1
| A.1 GENERAL FUND CY 2019 | [5 empty] | MBA/CBRMC | a) | 18127866 | a) | 01/03/19 | e) | - | a) | 18127866 | a) | 83.63 | c) | 83.83 | a) | 46 | See list of Provincial Roads | AP
| Road ID |  | Maintenance of Various Provincial Roads and Bridges at District 1 |  | Road Maintenance | KM |  | b) | Paraguya | b) | 01/03/19 | f) | - | b) | 18127866 | b) | - | d) | - | b) | 920 |  | FS
[6 empty] | 288.26 |  | c) | PEO/CBRMC | c) | 12/31/19 | g) | - | c) | - | [7 empty] | AC
| 11DAN | [8 empty] | d) | - | [11 empty] | AC
[8 empty] | d) | 261 days | d) | - | [11 empty] | AC
|  |  | Jct. Highway Magatos - New Bantayan |  | Road Maintenance | 7.1 | MBA | a) | 287307.39 | a) | 01/03/19 | e) | - | a) | 287307.39 | a) | 100% | c) | 100% | a) | 15 | Completed | AC | 4
| 001 | [6 empty] | b) | Crucio | b) | 01/16/19 | f) | - | b) | 287307.39 | b) | - | d) | - | b) | 480 |  | 1 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 118693.58 | [7 empty] | 1 | 4
[8 empty] | d) | - | d) | - | [11 empty] | 1 | 4
|  |  | Jct. Highway Magatos - New Bantayan |  | Road Maintenance | 7.1 | CBRMC | a) | 223674.22 | a) | 01/03/19 | e) | - | a) | 223674.22 | a) | 100% | c) | 100% | a) | 16 | Completed | 1 | 4
| 001 | [6 empty] | b) | Crucio | b) | 3/22/19 | f) | - | b) | 223674.22 | b) | - | d) | - | b) | 480 |  | 1 | 4
[8 empty] | c) | CALAFA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1 | 4
[8 empty] | d) | 3 quarters | d) | - | [11 empty] | 1 | 4
|  |  | Magatos-Bdry Pagsabangan |  | Road Maintenance | 8.33 | MBA | a) | 328740.25 | a) | 01/03/19 | e) | - | a) | 328740.25 | a) | 100% | c) | 100% | a) | 15 | Completed | 1 | 4
| 002 | [6 empty] | b) | Crucio | b) | 01/03/19 | f) | - | b) | 328740.25 | b) | - | d) | - | b) | 450 |  | 1 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 207258.49 | [7 empty] | 1 | 4
[8 empty] | d) | - | d) | - | [11 empty] | 1 | 4
|  |  | Magatos-Bdry Pagsabangan |  | Road Maintenance | 8.33 | CBRMC | a) | 270763.53 | a) | 01/03/19 | e) | - | a) | 270763.53 | a) | 100% | c) | 100% | a) | 16 | Completed | 1 | 4
| 002 | [6 empty] | b) | Crucio | b) | 03/22/19 | f) | - | b) | 270763.53 | b) | - | d) | - | b) | 450 |  | 1 | 4
[8 empty] | c) | CALAFA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1 | 4
[8 empty] | d) | 3 quarters | d) | - | [11 empty] | 1 | 4
|  |  | Ilog-New Bantayan |  | Road Maintenance | 2.68 | MBA | a) | 131131.39 | a) | 01/03/19 | e) | - | a) | 131131.39 | a) | 100% | c) | 100% | a) | 15 | Completed | 1 | 4
| 003 | [6 empty] | b) | Crucio | b) | 01/16/19 | f) | - | b) | 131131.39 | b) | - | d) | - | b) | 450 |  | 1 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 49,316.69 | [7 empty] | 1 | 4
[8 empty] | d) | - | d) | - | [11 empty] | 1 | 4
|  |  | Ilog-New Bantayan |  | Road Maintenance | 2.68 | CBRMC | a) | 65925.03 | a) | 01/03/19 | e) | - | a) | 65925.03 | a) | 100% | c) | 100% | a) | 16 | Completed | 1 | 4
| 003 | [6 empty] | b) | Crucio | b) | 03/22/19 | f) | - | b) | 65925.03 | b) | - | d) | - | b) | 450 |  | 1 | 4
[8 empty] | c) | CALAFA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1 | 4
[8 empty] | d) | 3 quarters | d) | - | [11 empty] | 1 | 4
|  |  | Asuncion -Monte Carlo-Del Pilar |  | Road Maintenance | 9.93 | MBA | a) | 474102.88 | a) | 01/03/19 | e) | - | a) | 474102.88 | a) | 100% | c) | 100% | a) | 15 | Completed | 1 | 4
| 005 | [6 empty] | b) | Crucio | b) | 01/03/19 | f) | - | b) | 474102.88 | b) | - | d) | - | b) | 450 |  | 1 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 240274.49 | [7 empty] | 1 | 4
[8 empty] | d) | - | d) | - | [11 empty] | 1 | 4
|  |  | Asuncion -Monte Carlo-Del Pilar |  | Road Maintenance | 9.93 | CBRMC | a) | 355524.28 | a) | 01/03/19 | e) | - | a) | 355524.28 | a) | 100% | c) | 100% | a) | 16 | Completed |  | 4
| 005 | [6 empty] | b) | Crucio | b) | 03/22/19 | f) | - | b) | 355524.28 | b) | - | d) | - | b) | 450 |  | 1 | 4
[8 empty] | c) | MAHAYAHAY IFA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1 | 4
[8 empty] | d) | 3 quarters | d) | - | [11 empty] | 1 | 4
|  |  | Jct. Highway Canatan-Jct. Highway Magatos |  | Road Maintenance | 4.85 | MBA | a) | 209808.59 | a) | 01/03/19 | e) | - | a) | 209808.59 | a) | 100% | c) | 100% | a) | 15 | Completed | 1 | 4
| 006 | [6 empty] | b) | Crucio | b) | 02/18/19 | f) | - | b) | 209808.59 | b) | - | d) | - | b) | 450 |  | 1 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 80652.8 | [7 empty] | 1 | 4
[8 empty] | d) | - | d) | - | [11 empty] | 1 | 4
|  |  | Jct. Highway Canatan-Jct. Highway Magatos |  | Road Maintenance | 4.85 | CBRMC | a) | 162458.12 | a) | 01/03/19 | e) | - | a) | 162458.12 | a) | 100% | c) | 100% | a) | 16 | Completed | 1 | 4
| 006 | [6 empty] | b) | Crucio | b) | 03/22/19 | f) | - | b) | 162458.12 | b) | - | d) | - | b) | 450 |  | 1 | 4
[8 empty] | c) | CAMODA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1 | 4
[8 empty] | d) | 3 quarters | d) | - | [11 empty] | 1 | 4
[23 empty] | 1 | 4
|  |  | Sta. Felomina-San Roque |  | Road Maintenance | 7.68 | MBA | a) | 147439.63 | a) | 01/03/19 | e) | - | a) | 147439.63 | a) | 100% | c) | 100% | a) | 15 | Completed |  | 4
| 008 | [6 empty] | b) | Crucio | b) | 01/16/19 | f) | - | b) | 147439.63 | b) | - | d) | - | b) | 450 |  | 1 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 63806.67 | [7 empty] | 1 | 4
[8 empty] | d) | - | d) | - | [11 empty] | 1 | 4
|  |  | Sta. Felomina-San Roque |  | Road Maintenance | 7.68 | CBRMC | a) | 261345.67 | a) | 01/03/19 | e) | - | a) | 261345.67 | a) | 100% | c) | 100% | a) | 16 | Completed | 1 | 4
| 008 | [6 empty] | b) | Crucio | b) | 03/25/19 | f) | - | b) | 261345.67 | b) | - | d) | - | b) | 450 |  | 1 | 4
[8 empty] | c) | STAFFA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1 | 4
[8 empty] | d) | 3 quarters | d) | - | [11 empty] | 1 | 4
|  |  | Saug-Sonlon-Bdy Longanapan |  | Road Maintenance | 11.6 | MBA | a) | 568486.36 | a) | 01/03/19 | e) | - | a) | 568486.36 | a) | 100% | c) | 100% | a) | 15 | Completed | 1 | 4
| 010 | [6 empty] | b) | Crucio | b) | 01/16/19 | f) | - | b) | 568486.36 | b) | - | d) | - | b) | 450 |  | 1 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 262900.22 | [7 empty] | 1 | 4
[8 empty] | d) | - | d) | - | [11 empty] | 1 | 4
|  |  | Saug-Sonlon-Bdy Longanapan |  | Road Maintenance | 11.6 | CBRMC | a) | 185565.56 | a) | 01/03/19 | e) | - | a) | 185565.56 | a) | 100% | c) | 100% | a) | 16 | Completed | 1 | 4
| 010 | [6 empty] | b) | Crucio | b) | 03/26/19 | f) | - | b) | 185565.56 | b) | - | d) | - | b) | 450 |  | 1 | 4
[8 empty] | c) | BINANCIAN LIVESTOCK AFA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1 | 4
[8 empty] | d) | 3 quarters | d) | - | [11 empty] | 1 | 4
|  |  | Jct. New Visayas-Buan |  | Road Maintenance | 2.99 | MBA | a) | 79238.27 | a) | 01/03/19 | e) | - | a) | 79238.27 | a) | 100% | c) | 100% | a) | 15 | Completed | 1 | 4
| 011 | [6 empty] | b) | Crucio | b) | 02/18/19 | f) | - | b) | 79238.27 | b) | - | d) | - | b) | 450 |  | 1 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 14682.85 | [7 empty] | 1 | 4
[8 empty] | d) | - | d) | - | [11 empty] | 1 | 4
|  |  | Jct. New Visayas-Buan |  | Road Maintenance | 2.99 | CBRMC | a) | 101242.01 | a) | 01/03/19 | e) | - | a) | 101242.01 | a) | 100% | c) | 100% | a) | 16 | Completed | 1 | 4
| 011 | [6 empty] | b) | Crucio | b) | 03/22/19 | f) | - | b) | 101242.01 | b) | - | d) | - | b) | 450 |  | 1 | 4
[8 empty] | c) | BUAN IFA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1 | 4
[8 empty] | d) | 3 quarters | d) | - | [11 empty] | 1 | 4
|  |  | San Vicente - Butay |  | Road Maintenance | 7.52 | MBA | a) | 209624.2 | a) | 01/03/19 | e) | - | a) | 209624.2 | a) | 100% | c) | 100% | a) | 15 | Completed | 1 | 4
| 013 | [6 empty] | b) | Crucio | b) | 02/18/19 | f) | - | b) | 209624.2 | b) | - | d) | - | b) | 450 |  | 1 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 56,080.29 | [7 empty] | 1 | 4
[8 empty] | d) | - | d) | - | [11 empty] | 1 | 4
|  |  | San Vicente - Butay |  | Road Maintenance | 7.52 | CBRMC | a) | 227205.88 | a) | 01/03/19 | e) | - | a) | 227205.88 | a) | 100% | c) | 100% | a) | 16 | Completed | 1 | 4
| 013 | [6 empty] | b) | Crucio | b) | 03/27/19 | f) | - | b) | 227205.88 | b) | - | d) | - | b) | 450 |  | 1 | 4
[8 empty] | c) | SVMODA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1 | 4
[8 empty] | d) | 3 quarters | d) | - | [11 empty] | 1 | 4
|  |  | Jct. Highway Doña Andrea - Capungagan |  | Road Maintenance | 8.7 | MBA | a) | 230835.16 | a) | 01/03/19 | e) | - | a) | 230835.16 | a) | 100% | c) | 100% | a) | 15 | Completed | 1 | 4
| 014 | [6 empty] | b) | Crucio | b) | 02/18/19 | f) | - | b) | 230835.16 | b) | - | d) | - | b) | 450 |  | 1 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 60,629.26 | [7 empty] | 1 | 4
[8 empty] | d) | - | d) | - | [11 empty] | 1 | 4
[23 empty] | 1 | 4
|  |  | Jct. Highway Doña Andrea - Capungagan |  | Road Maintenance | 8.7 | CBRMC | a) | 294308.14 | a) | 01/03/19 | e) | - | a) | 294308.14 | a) | 100% | c) | 100% | a) | 16 | Completed |  | 4
| 014 | [6 empty] | b) | Crucio | b) | 03/28/19 | f) | - | b) | 294308.14 | b) | - | d) | - | b) | 450 |  | 1 | 4
[8 empty] | c) | CAPUNGAGAN MPC | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1 | 4
[8 empty] | d) | 3 quarters | d) | - | [11 empty] | 1 | 4
|  |  | Semong-Palma Gil |  | Road Maintenance | 2.73 | MBA | a) | 147289.98 | a) | 01/03/19 | e) | - | a) | 147289.98 | a) | 100% | c) | 100% | a) | 15 | Completed | 1 | 4
| 018 | [6 empty] | b) | Crucio | b) | 02/18/19 | f) | - | b) | 147289.98 | b) | - | d) | - | b) | 450 |  | 1 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 71745.43 | [7 empty] | 1 | 4
[8 empty] | d) | - | d) | - | [11 empty] | 1 | 4
[23 empty] | 1 | 4
4
4
|  |  | Semong-Palma Gil |  | Road Maintenance | 2.73 | CBRMC | a) | 49186.05 | a) | 01/03/19 | e) | - | a) | 49186.05 | a) | 100% | c) | 100% | a) | 16 | Completed |  | 4
| 018 | [6 empty] | b) | Crucio | b) | 03/22/19 | f) | - | b) | 49186.05 | b) | - | d) | - | b) | 450 |  | 1 | 4
[8 empty] | c) | PALMA GIL FA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1 | 4
[8 empty] | d) | 3 quarters | d) | - | [11 empty] | 1 | 4
|  |  | Daligdigon - Dagohoy |  | Road Maintenance | 3.34 | MBA | a) | 148835.45 | a) | 01/03/19 | e) | - | a) | 148835.45 | a) | 100% | c) | 100% | a) | - | Completed | 1 | 4
| 020 | [6 empty] | b) | Crucio | b) | - | f) | - | b) | 148835.45 | b) | - | d) | - | b) | - |  | 1 | 4
[8 empty] | c) | PEO | c) | - | g) | 2019-12-31 | c) | - | [7 empty] | 1 | 4
[8 empty] | d) | - | d) | - | [11 empty] | 1 | 4
|  |  | Daligdigon - Dagohoy |  | Road Maintenance | 3.34 | CBRMC | a) | 68279.5 | a) | 01/03/19 | e) | - | a) | 68279.5 | a) | 100% | c) | 100% | a) | 16 | Completed | 1 | 4
| 020 | [6 empty] | b) | Crucio | b) | 03/22/19 | f) | - | b) | 68279.5 | b) | - | d) | - | b) | 450 |  | 1 | 4
[8 empty] | c) | PALMA GIL FA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1 | 4
[8 empty] | d) | 3 quarters | d) | - | [11 empty] | 1 | 4
|  |  | Jct. Sampao-Bdry. Mamacao |  | Road Maintenance | 4.98 | MBA | a) | 154200.78 | a) | 01/03/19 | e) | - | a) | 154200.78 | a) | 100% | c) | 100% | a) | 15 | Completed | 1 | 4
| 025 | [6 empty] | b) | Crucio | b) | 02/18/19 | f) | - | b) | 154200.78 | b) | - | d) | - | b) | 450 |  | 1 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 24,296.87 | [7 empty] | 1 | 4
[8 empty] | d) | - | d) | - | [11 empty] | 1 | 4
|  |  | Jct. Sampao-Bdry. Mamacao |  | Road Maintenance | 4.98 | CBRMC | a) | 169521.51 | a) | 01/03/19 | e) | - | a) | 169521.51 | a) | 100% | c) | 100% | a) | 16 | Completed | 1 | 4
| 025 | [6 empty] | b) | Crucio | b) | 03/26/19 | f) | - | b) | 169521.51 | b) | - | d) | - | b) | 450 |  | 1 | 4
[8 empty] | c) | AMS KAPALONG | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1 | 4
[8 empty] | d) | 3 quarters | d) | - | [11 empty] | 1 | 4
|  |  | Jct. Highway Luna-Mamacao-Narra |  | Road Maintenance | 9.17 | MBA | a) | 357957.66 | a) | 01/03/19 | e) | - | a) | 357957.66 | a) | 100% | c) | 100% | a) | 15 | Completed | 1 | 4
| 026 | [6 empty] | b) | Crucio | b) | 02/18/19 | f) | - | b) | 357957.66 | b) | - | d) | - | b) | 450 |  | 1 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 127,996.16 | [7 empty] | 1 | 4
[8 empty] | d) | - | d) | - | [11 empty] | 1 | 4
|  |  | Jct. Highway Luna-Mamacao-Narra |  | Road Maintenance | 9.17 | CBRMC | a) | 313143.91 | a) | 01/03/19 | e) | - | a) | 313143.91 | a) | 100% | c) | 100% | a) | 16 | Completed | 1 | 4
| 026 | [6 empty] | b) | Crucio | b) | 03/26/19 | f) | - | b) | 313143.91 | b) | - | d) | - | b) | 450 |  | 1 | 4
[8 empty] | c) | AMS KAPALONG | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1 | 4
[8 empty] | d) | 3 quarters | d) | - | [11 empty] | 1 | 4
|  |  | Jct. Gabuyan-Katipunan-Bucana |  | Road Maintenance | 5.89 | MBA | a) | 294403.23 | a) | 01/03/19 | e) | - | a) | 294403.23 | a) | 100% | c) | 100% | a) | 15 | Completed | 1 | 4
| 027 | [6 empty] | b) | Crucio | b) | 02/18/19 | f) | - | b) | 294403.23 | b) | - | d) | - | b) | 450 |  | 1 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 126,179.97 | [7 empty] | 1 | 4
[8 empty] | d) | - | d) | - | [11 empty] | 1 | 4
|  |  | Jct. Gabuyan-Katipunan-Bucana |  | Road Maintenance | 5.89 | CBRMC | a) | 129495.6 | a) | 01/03/19 | e) | - | a) | 129495.6 | a) | 100% | c) | 100% | a) | 16 | Completed | 1 | 4
| 027 | [6 empty] | b) | Crucio | b) | 03/26/19 | f) | - | b) | 129495.6 | b) | - | d) | - | b) | 450 |  | 1 | 4
[8 empty] | c) | MANGULIBAS FA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1 | 4
[8 empty] | d) | 3 quarters | d) | - | [11 empty] | 1 | 4
|  |  | Capungagan-Mabuhay-Pandulian |  | Road Maintenance | 5.57 | MBA | a) | 294917.73 | a) | 01/03/19 | e) | - | a) | 294917.73 | a) | 100% | c) | 100% | a) | 15 | Completed | 1 | 4
| 028 | [6 empty] | b) | Crucio | b) | 02/18/19 | f) | - | b) | 294917.73 | b) | - | d) | - | b) | 450 |  | 1 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1 | 4
[8 empty] | d) | - | d) | - | [11 empty] | 1 | 4
[23 empty] | 1 | 4
|  |  | Capungagan-Mabuhay-Pandulian |  | Road Maintenance | 5.57 | CBRMC | a) | 105950.95 | a) | 01/03/19 | e) | - | a) | 105950.95 | a) | 100% | c) | 100% | a) | 16 | Completed |  | 4
| 028 | [6 empty] | b) | Crucio | b) | 03/28/19 | f) | - | b) | 105950.95 | b) | - | d) | - | b) | 450 |  | 1 | 4
[8 empty] | c) | CAPUNGAGAN MPC | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1 | 4
[8 empty] | d) | 3 quarters | d) | - | [11 empty] | 1 | 4
|  |  | Florida - New Boholano |  | Road Maintenance | 2.54 | MBA | a) | 95863.17 | a) | 01/03/19 | e) | - | a) | 95863.17 | a) | 100% | c) | 100% | a) | 15 | Completed | 1 | 4
| 030 | [6 empty] | b) | Crucio | b) | 02/18/19 | f) | - | b) | 95863.17 | b) | - | d) | - | b) | 450 |  | 1 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 31,418.99 | [7 empty] | 1 | 4
[8 empty] | d) | - | d) | - | [11 empty] | 1 | 4
|  |  | Florida - New Boholano |  | Road Maintenance | 2.54 | CBRMC | a) | 47425.27 | a) | 01/03/19 | e) | - | a) | 47425.27 | a) | 100% | c) | 100% | a) | 16 | Completed | 1 | 4
| 030 | [6 empty] | b) | Crucio | b) | 03/28/19 | f) | - | b) | 47425.27 | b) | - | d) | - | b) | 450 |  | 1 | 4
[8 empty] | c) | SUPRA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1 | 4
[8 empty] | d) | 3 quarters | d) | - | [11 empty] | 1 | 4
|  |  | Jct. New Boholano - New Loon |  | Road Maintenance | 4.77 | MBA | a) | 140549.84 | a) | 01/03/19 | e) | - | a) | 140549.84 | a) | 100% | c) | 100% | a) | 15 | Completed | 1 | 4
| 031 | [6 empty] | b) | Crucio | b) | 02/18/19 | f) | - | b) | 140549.84 | b) | - | d) | - | b) | 450 |  | 1 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 40,056.38 | [7 empty] | 1 | 4
[8 empty] | d) | - | d) | - | [11 empty] | 1 | 4
4
|  |  | Jct. New Boholano - New Loon |  | Road Maintenance | 4.77 | CBRMC | a) | 169521.51 | a) | 01/03/19 | e) | - | a) | 169521.51 | a) | 100% | c) | 100% | a) | 16 | Completed | 1 | 4
| 031 | [6 empty] | b) | Crucio | b) | 03/28/19 | f) | - | b) | 169521.51 | b) | - | d) | - | b) | 450 |  | 1 | 4
[8 empty] | c) | NEW LOON FA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1 | 4
[8 empty] | d) | 3 quarters | d) | - | [11 empty] | 1 | 4
|  |  | Florida-Suaon-Jct. Gupitan |  | Road Maintenance | 15.57 | MBA | a) | 707038.05 | a) | 01/03/19 | e) | - | a) | 707038.05 | a) | 100% | c) | 100% | a) | 15 | Completed | 1 | 4
| 032 | [6 empty] | b) | Crucio | b) | 01/16/19 | f) | - | b) | 707038.05 | b) | - | d) | - | b) | 450 |  | 1 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 226,.062.60 | [7 empty] | 1 | 4
[8 empty] | d) | - | d) | - | [11 empty] | 1 | 4
|  |  | Florida-Suaon-Jct. Gupitan |  | Road Maintenance | 15.57 | CBRMC | a) | 419094.85 | a) | 01/03/19 | e) | - | a) | 419094.85 | a) | 100% | c) | 100% | a) | 16 | Completed | 1 | 4
| 032 | [6 empty] | b) | Crucio | b) | 03/28/19 | f) | - | b) | 419094.85 | b) | - | d) | - | b) | 450 |  | 1 | 4
[8 empty] | c) | SUPRA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1 | 4
[8 empty] | d) | 3 quarters | d) | - | [11 empty] | 1 | 4
|  |  | Km. 15, Kipalili-New Loon |  | Road Maintenance | 6.93 | MBA | a) | 367659.97 | a) | 01/03/19 | e) | - | a) | 367659.97 | a) | 100% | c) | 100% | a) | 15 | Completed | 1 | 4
| 034 | [6 empty] | b) | Crucio | b) | 02/01/19 | f) | - | b) | 367659.97 | b) | - | d) | - | b) | 450 |  | 1 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 112,175.78 | [7 empty] | 1 | 4
[8 empty] | d) | - | d) | - | [11 empty] | 1 | 4
|  |  | Km. 15, Kipalili-New Loon |  | Road Maintenance | 6.93 | CBRMC | a) | 237801.01 | a) | 01/03/19 | e) | - | a) | 237801.01 | a) | 100% | c) | 100% | a) | 16 | Completed | 1 | 4
| 034 | [6 empty] | b) | Crucio | b) | 03/26/19 | f) | - | b) | 237801.01 | b) | - | d) | - | b) | 480 |  | 1 | 4
[8 empty] | c) | KIPALILI FA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1 | 4
[8 empty] | d) | 3 quarters | d) | - | [11 empty] | 1 | 4
|  |  | Jct. Suaon-Libuton |  | Road Maintenance | 7.26 | MBA | a) | 44015.68 | a) | 01/03/19 | e) | - | a) | 44015.68 | a) | 100% | c) | 100% | a) | 15 | Completed |  | 4
| 035 | [6 empty] | b) | Crucio | b) | 01/16/19 | f) | - | b) | 44015.68 | b) | - | d) | - | b) | 450 |  | 1 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 24,980.86 | [7 empty] | 1 | 4
[8 empty] | d) | - | d) | - | [11 empty] | 1 | 4
|  |  | Jct. Suaon-Libuton |  | Road Maintenance | 7.26 | CBRMC | a) | 91664.91 | a) | 01/03/19 | e) | - | a) | 91664.91 | a) | 100% | c) | 100% | a) | 16 | Completed | 1 | 4
| 035 | [6 empty] | b) | Crucio | b) | 03/22/19 | f) | - | b) | 91664.91 | b) | - | d) | - | b) | 480 |  | 1 | 4
[8 empty] | c) | AALLI | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1 | 4
[8 empty] | d) | 3 quarters | d) | - | [11 empty] | 1 | 4
[23 empty] | 1 | 4
|  |  | Datu Balong - Pinamuno |  | Road Maintenance | 2.74 | MBA | a) | 95458.24 | a) | 01/03/19 | e) | - | a) | 95458.24 | a) | 100% | c) | 100% | a) | 15 | Completed |  | 4
| 040 | [6 empty] | b) | Crucio | b) | 03/01/19 | f) | - | b) | 95458.24 | b) | - | d) | - | b) | 450 |  | 1 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 12,625.00 | [7 empty] | 1 | 4
[8 empty] | d) | - | d) | - | [11 empty] | 1 | 4
|  |  | Datu Balong - Pinamuno |  | Road Maintenance | 2.74 | CBRMC | a) | 63570.57 | a) | 01/03/19 | e) | - | a) | 63570.57 | a) | 100% | c) | 100% | a) | 16 | Completed | 1 | 4
| 040 | [6 empty] | b) | Crucio | b) | 03/28/19 | f) | - | b) | 63570.57 | b) | - | d) | - | b) | 480 |  | 1 | 4
[8 empty] | c) | DATU BALONG FA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1 | 4
[8 empty] | d) | 3 quarters | d) | - | [11 empty] | 1 | 4
|  |  | Sawata - Mamangan - Pinamuno |  | Road Maintenance | 14.48 | MBA | a) | 545390.17 | a) | 01/03/19 | e) | - | a) | 545390.17 | a) | 100% | c) | 100% | a) | 15 | Completed | 1 | 4
| 041 | [6 empty] | b) | Crucio | b) | 02/01/19 | f) | - | b) | 545390.17 | b) | - | d) | - | b) | 450 |  | 1 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 196,076.60 | [7 empty] | 1 | 4
[8 empty] | d) | - | d) | - | [11 empty] | 1 | 4
|  |  | Sawata - Mamangan - Pinamuno |  | Road Maintenance | 14.48 | CBRMC | a) | 508564.54 | a) | 01/03/19 | e) | - | a) | 508564.54 | a) | 100% | c) | 100% | a) | 16 | Completed | 1 | 4
| 041 | [6 empty] | b) | Crucio | b) | 03/22/19 | f) | - | b) | 508564.54 | b) | - | d) | - | b) | 480 |  | 1 | 4
[8 empty] | c) | SAWATA DFA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1 | 4
[8 empty] | d) | 3 quarters | d) | - | [11 empty] | 1 | 4
|  |  | Igangon - Sawata |  | Road Maintenance | 9.66 | MBA | a) | 497447.77 | a) | 01/03/19 | e) | - | a) | 497447.77 | a) | 100% | c) | 100% | a) | 15 | Completed | 1 | 4
| 042 | [6 empty] | b) | Crucio | b) | 02/01/19 | f) | - | b) | 497447.77 | b) | - | d) | - | b) | 450 |  | 1 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1 | 4
[8 empty] | d) | - | d) | - | [11 empty] | 1 | 4
|  |  | Igangon - Sawata |  | Road Maintenance | 9.66 | CBRMC | a) | 197775.1 | a) | 01/03/19 | e) | - | a) | 197775.1 | a) | 100% | c) | 100% | a) | 16 | Completed | 1 | 4
| 042 | [6 empty] | b) | Crucio | b) | 03/22/19 | f) | - | b) | 197775.1 | b) | - | d) | - | b) | 480 |  | 1 | 4
[8 empty] | c) | SAWATA DFA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1 | 4
[8 empty] | d) | 3 quarters | d) | - | [11 empty] | 1 | 4
4
4
|  |  | New Corella - Sto. Niño - Macgum |  | Road Maintenance | 17.11 | MBA | a) | 606294.08 | a) | 01/03/19 | e) | - | a) | 606294.08 | a) | 100% | c) | 100% | a) | 15 | Completed | 1 | 4
| 044 | [6 empty] | b) | Crucio | b) | 01/03/19 | f) | - | b) | 606294.08 | b) | - | d) | - | b) | 450 |  | 1 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 246,619.77 | [7 empty] | 1 | 4
[8 empty] | d) | - | d) | - | [11 empty] | 1 | 4
|  |  | New Corella - Sto. Niño - Macgum |  | Road Maintenance | 17.11 | CBRMC | a) | 308434.97 | a) | 01/03/19 | e) | - | a) | 308434.97 | a) | 100% | c) | 100% | a) | 16 | Completed | 1 | 4
| 044 | [6 empty] | b) | Crucio | b) | 03/26/19 | f) | - | b) | 308434.97 | b) | - | d) | - | b) | 480 |  | 1 | 4
[8 empty] | c) | SAN ISIDRO FA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1 | 4
[8 empty] | d) | 3 quarters | d) | - | [11 empty] | 1 | 4
|  |  | Tagaytay - Buan |  | Road Maintenance | 4.92 | MBA | a) | 173197.37 | a) | 01/03/19 | e) | - | a) | 173197.37 | a) | 100% | c) | 100% | a) | 15 | Completed | 1 | 4
| 045 | [6 empty] | b) | Crucio | b) | 03/18/19 | f) | - | b) | 173197.37 | b) | - | d) | - | b) | 450 |  | 1 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 26254.58 | [7 empty] | 1 | 4
[8 empty] | d) | - | d) | - | [11 empty] | 1 | 4
|  |  | Tagaytay - Buan |  | Road Maintenance | 4.92 | CBRMC | a) | 131850.07 | a) | 01/03/19 | e) | - | a) | 131850.07 | a) | 100% | c) | 100% | a) | 16 | Completed | 1 | 4
| 045 | [6 empty] | b) | Crucio | b) | 03/22/19 | f) | - | b) | 131850.07 | b) | - | d) | - | b) | 480 |  | 1 | 4
[8 empty] | c) | BUAN IFA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1 | 4
[8 empty] | d) | 3 quarters | d) | - | [11 empty] | 1 | 4
|  |  | limbaan - Sto. Niño |  | Road Maintenance | 3.19 | MBA | a) | 153706.77 | a) | 01/03/19 | e) | - | a) | 153706.77 | a) | 100% | c) | 100% | a) | 15 | Completed | 1 | 4
| 049 | [6 empty] | b) | Crucio | b) | 03/01/19 | f) | - | b) | 153706.77 | b) | - | d) | - | b) | 450 |  | 1 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 32534.49 | [7 empty] | 1 | 4
[8 empty] | d) | - | d) | - | [11 empty] | 1 | 4
|  |  | limbaan - Sto. Niño |  | Road Maintenance | 3.19 | CBRMC | a) | 53657.51 | a) | 01/03/19 | e) | - | a) | 53657.51 | a) | 100% | c) | 100% | a) | - | Completed | 1 | 4
| 049 | [6 empty] | b) | Crucio | b) | - | f) | - | b) | 53657.51 | b) | - | d) | - | b) | - |  | 1 | 4
[8 empty] | c) | - | c) | - | g) | 2019-12-31 | c) | - | [7 empty] | 1 | 4
[8 empty] | d) | - | d) | - | [11 empty] | 1 | 4
|  |  | Del Pilar - Jct. Silangan |  | Road Maintenance | 4.17 | MBA | a) | 187097.4 | a) | 01/03/19 | e) | - | a) | 187097.4 | a) | 100% | c) | 100% | a) | 15 | Completed | 1 | 4
| 051 | [6 empty] | b) | Crucio | b) | 03/18/19 | f) | - | b) | 187097.4 | b) | - | d) | - | b) | 450 |  | 1 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 94181.74 | [7 empty] | 1 | 4
[8 empty] | d) | - | d) | - | [11 empty] | 1 | 4
|  |  | Del Pilar - Jct. Silangan |  | Road Maintenance | 4.17 | CBRMC | a) | 113014.34 | a) | 01/03/19 | e) | - | a) | 113014.34 | a) | 100% | c) | 100% | a) | 16 | Completed | 1 | 4
| 051 | [6 empty] | b) | Crucio | b) | 03/26/19 | f) | - | b) | 113014.34 | b) | - | d) | - | b) | 480 |  | 1 | 4
[8 empty] | c) | DURIAN DACUDAO | c) | 12/31/19 | g) | - | c) | - | [7 empty] | 1 | 4
[8 empty] | d) | 3 quarters | d) | - | [11 empty] | 1 | 4
|  |  | New Corella - New Sambog - Silangan |  | Road Maintenance | 5.1 | MBA | a) | 201994.35 | a) | 01/03/19 | e) | - | a) | 201994.35 | a) | 100% | c) | 100% | a) | 15 | Completed | 1 | 4
| 052 | [6 empty] | b) | Crucio | b) | 03/01/19 | f) | - | b) | 201994.35 | b) | - | d) | - | b) | 450 |  | 1 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 63402.48 | [7 empty] | 1 | 4
[8 empty] | d) | - | d) | - | [11 empty] | 1 | 4
|  |  | New Corella - New Sambog - Silangan |  | Road Maintenance | 5.1 | CBRMC | a) | 131850.07 | a) | 01/03/19 | e) | - | a) | 131850.07 | a) | 100% | c) | 100% | a) | 16 | Completed | 1 | 4
| 052 | [6 empty] | b) | Crucio | b) | 03/26/19 | f) | - | b) | 131850.07 | b) | - | d) | - | b) | 480 |  | 1 | 4
[8 empty] | c) | DURIAN DACUDAO | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1 | 4
[8 empty] | d) | 3 quarters | d) | - | [11 empty] | 1 | 4
|  |  | Sta. Fe - Del Monte |  | Road Maintenance | 3.34 | MBA | a) | 37923.51 | a) | 01/03/19 | e) | - | a) | 37923.51 | a) | 100% | c) | 100% | a) | 15 | Completed | 1 | 4
| 056 | [6 empty] | b) | Crucio | b) | 03/18/19 | f) | - | b) | 37923.51 | b) | - | d) | - | b) | 450 |  | 1 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 36595.13 | [7 empty] | 1 | 4
[8 empty] | d) | - | d) | - | [11 empty] | 1 | 4
|  |  | Sta. Fe - Del Monte |  | Road Maintenance | 3.34 | CBRMC | a) | 70633.96 | a) | 01/03/19 | e) | - | a) | 70633.96 | a) | 100% | c) | 100% | a) | 16 | Completed | 1 | 4
| 056 | [6 empty] | b) | Crucio | b) | 03/21/19 | f) | - | b) | 70633.96 | b) | - | d) | - | b) | 480 |  | 1 | 4
[8 empty] | c) | DEL MONTE CACAO | c) | 12/31/19 | g) | 2019-12-31 | c) | 4,872.18 | [7 empty] | 1 | 4
[8 empty] | d) | 3 quarters | d) | - | [11 empty] | 1 | 4
|  |  | New Corella - New Bohol |  | Road Maintenance | 11.54 | MBA | a) | 356226.67 | a) | 01/03/19 | e) | - | a) | 356226.67 | a) | 100% | c) | 100% | a) | 15 | Completed |  | 4
| 058 | [6 empty] | b) | Crucio | b) | 02/01/19 | f) | - | b) | 356226.67 | b) | - | d) | - | b) | 450 |  | 1 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 110,982.71 | [7 empty] | 1 | 4
[8 empty] | d) | - | d) | - | [11 empty] | 1 | 4
|  |  | New Corella - New Bohol |  | Road Maintenance | 11.54 | CBRMC | a) | 190711.7 | a) | 01/03/19 | e) | - | a) | 190711.7 | a) | 100% | c) | 100% | a) | 16 | Completed | 1 | 4
| 058 | [6 empty] | b) | Crucio | b) | 03/22/19 | f) | - | b) | 190711.7 | b) | - | d) | - | b) | 480 |  | 1 | 4
[8 empty] | c) | SAN JOSE COCONUT | c) | 12/31/19 | g) | 2019-12-31 | c) | 5,847.18 | [7 empty] | 1 | 4
[8 empty] | d) | 3 quarters | d) | - | [11 empty] | 1 | 4
[23 empty] | 1 | 4
4
|  |  | Jct. Carcor - Prk. 9 Bagsak |  | Road Maintenance | 2.5 | MBA | a) | 108618.49 | a) | 01/03/19 | e) | - | a) | 108618.49 | a) | 100% | c. | 100% | a) | 15 | Completed
| 059 | [6 empty] | b) | Crucio | b) | 03/01/19 | f) | - | b) | 108618.49 | b) | - | d) |  | b) | 480 |  | 1 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 79952.88 | [7 empty] | 1 | 4
[8 empty] | d) | - | d) | - | [11 empty] | 1 | 4
[23 empty] | 1 | 4
4
4
|  |  | Jct. Carcor - Prk. 9 Bagsak |  | Road Maintenance | 2.5 | CBRMC | a) | 42284.76 | a) | 01/03/19 | e) | - | a) | 42284.76 | a) | 100% | c) | 100% | a) | 16 | Completed |  | 4
| 059 | [6 empty] | b) | Crucio | b) | 03/22/19 | f) | - | b) | 42284.76 | b) | - | d) | - | b) | 480 |  | 1 | 4
[8 empty] | c) | CARCOR MOTOR | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1 | 4
[8 empty] | d) | 3 quarters | d) | - | [11 empty] | 1 | 4
|  |  | Carcor - Jct. Kauswagan |  | Road Maintenance | 4.32 | MBA | a) | 264514.71 | a) | 01/03/19 | e) | - | a) | 264514.71 | a) | 100% | c) | 100% | a) | 15 | Completed | 1 | 4
| 060 | [6 empty] | b) | Crucio | b) | 03/18/19 | f) | - | b) | 264514.71 | b) | - | d) |  | b) | 450 |  | 1 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 80733.11 | [7 empty] | 1 | 4
[8 empty] | d) | - | d) | - | [11 empty] | 1 | 4
|  |  | Carcor - Jct. Kauswagan |  | Road Maintenance | 4.32 | CBRMC | a) | 48398.27 | a) | 01/03/19 | e) | - | a) | 48398.27 | a) | 100% | c) | 100% | a) | 16 | Completed |  | 4
| 060 | [6 empty] | b) | Crucio | b) | 03/22/19 | f) | - | b) | 48398.27 | b) | - | d) | - | b) | 480 |  | 1 | 4
[8 empty] | c) | CARCOR MOTOR | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1 | 4
[8 empty] | d) | 3 quarters | d) | - | [11 empty] | 1 | 4
|  |  | Del Pilar - Prk 9 Bagsak - San Jose |  | Road Maintenance | 4.99 | MBA | a) | 170215.76 | a) | 01/03/19 | e) | - | a) | 170215.76 | a) | 100% | c) | 100% | a) | 15 | Completed | 1 | 4
| 061 | [6 empty] | b) | Crucio | b) | 03/01/19 | f) | - | b) | 170215.76 | b) | - | d) | - | b) | 450 |  | 1 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 87595.63 | [7 empty] | 1 | 4
[8 empty] | d) | - | d) | - | [11 empty] | 1 | 4
|  |  | Del Pilar - Prk 9 Bagsak - San Jose |  | Road Maintenance | 4.99 | CBRMC | a) | 223674.22 | a) | 01/03/19 | e) | - | a) | 223674.22 | a) | 100% | c) | 100% | a) | 16 | Completed | 1 | 4
| 061 | [6 empty] | b) | Crucio | b) | 03/22/19 | f) | - | b) | 223674.22 | b) | - | d) | - | b) | 480 |  | 1 | 4
[8 empty] | c) | SAN JOSE COCONUT | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1 | 4
[8 empty] | d) | 3 quarters | d) | - | [11 empty] | 1 | 4
|  |  | San Juan - New Talisay |  | Road Maintenance | 5.13 | MBA | a) | 306261.25 | a) | 01/03/19 | e) | - | a) | 306261.25 | a) | 100% | c) | 100% | a) | 15 | Completed | 1 | 4
| 063 | [6 empty] | b) | Crucio | b) | 02/01/19 | f) | - | b) | 306261.25 | b) | - | d) | - | b) | 450 |  | 1 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 85123.48 | [7 empty] | 1 | 4
[8 empty] | d) | - | d) | - | [11 empty] | 1 | 4
|  |  | San Juan - New Talisay |  | Road Maintenance | 5.13 | CBRMC | a) | 93906.31 | a) | 01/03/19 | e) | - | a) | 93906.31 | a) | 100% | c) | 100% | a) | 16 | Completed |  | 4
| 063 | [6 empty] | b) | Crucio | b) | 03/26/19 | f) | - | b) | 93906.31 | b) | - | d) | - | b) | 480 |  | 1 | 4
[8 empty] | c) | NEW TALISAY IAWA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1 | 4
[8 empty] | d) | 3 quarters | d) | - | [11 empty] | 1 | 4
|  |  | San Juan - kauswagan - New Cortez |  | Road Maintenance | 3.22 | MBA | a) | 187879.04 | a) | 01/03/19 | e) | - | a) | 187879.04 | a) | 100% | c) | 100% | a) | 15 | Completed | 1 | 4
| 064 | [6 empty] | b) | Crucio | b) | 03/18/19 | f) | - | b) | 187879.04 | b) | - | d) | - | b) | 450 |  | 1 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 3,025.00 | [7 empty] | 1 | 4
[8 empty] | d) | - | d) | - | [11 empty] | 1 | 4
4
4
|  |  | San Juan - kauswagan - New Cortez |  | Road Maintenance | 3.22 | CBRMC | a) | 63298.26 | a) | 01/03/19 | e) | - | a) | 63298.26 | a) | 100% | c) | 100% | a) | 16 | Completed |  | 4
| 064 | [6 empty] | b) | Crucio | b) | 03/22/19 | f) | - | b) | 63298.26 | b) | - | d) | - | b) | 480 |  | 1 | 4
[8 empty] | c) | SAN JOSE COCONUT | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1 | 4
[8 empty] | d) | 3 quarters | d) | - | [11 empty] | 1 | 4
|  |  | New Bohol - Jct. El Unido |  | Road Maintenance | 2.12 | MBA | a) | 54989.06 | a) | 01/03/19 | e) | - | a) | 54989.06 | a) | 100% | c) | 100% | a) | 15 | Completed |  | 4
| 065 | [6 empty] | b) | Crucio | b) | 03/01/19 | f) | - | b) | 54989.06 | b) | - | d) | - | b) | 450 |  | 1 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 21021.99 | [7 empty] | 1 | 4
[8 empty] | d) | - | d) | - | [11 empty] | 1 | 4
|  |  | New Bohol - Jct. El Unido |  | Road Maintenance | 2.12 | CBRMC | a) | 58861.64 | a) | 01/03/19 | e) | - | a) | 58861.64 | a) | 100% | c) | 100% | a) | 16 | Completed | 1 | 4
| 065 | [6 empty] | b) | Crucio | b) | 03/26/19 | f) | - | b) | 58861.64 | b) | - | d) | - | b) | 480 |  | 1 | 4
[8 empty] | c) | MANDISKAB TRIBAL | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1 | 4
[8 empty] | d) | 3 quarters | d) | - | [11 empty] | 1 | 4
[23 empty] | 1 | 4
4
|  |  | New Corella - El unido - Jct. Mesaoy |  | Road Maintenance | 8.63 | MBA | a) | 388002.46 | a) | 01/03/19 | e) | - | a) | 388002.46 | a) | 100% | c) | 100% | a) | 15 | Completed |  | 4
| 066 | [6 empty] | b) | Crucio | b) | 02/11/19 | f) | - | b) | 388002.46 | b) | - | d) | - | b) | 450 |  | 1 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 58142.76 | [7 empty] | 1 | 4
[8 empty] | d) | - | d) | - | [11 empty] | 1 | 4
|  |  | New Corella - El unido - Jct. Mesaoy |  | Road Maintenance | 8.63 | CBRMC | a) | 233092.08 | a) | 01/03/19 | e) | - | a) | 233092.08 | a) | 100% | c) | 100% | a) | 16 | Completed | 1 | 4
| 066 | [6 empty] | b) | Crucio | b) | 03/26/19 | f) | - | b) | 233092.08 | b) | - | d) | - | b) | 480 |  | 1 | 4
[8 empty] | c) | MANDISKAB TRIBAL | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1 | 4
[8 empty] | d) | 3 quarters | d) | - | [11 empty] | 1 | 4
|  |  | Mesaoy - Dasing |  | Road Maintenance | 1.39 | MBA | a) | 29749.5 | a) | 01/03/19 | e) | - | a) | 29749.5 | a) | 100% | c) | 100% | a) | 15 | Completed | 1 | 4
| 067 | [6 empty] | b) | Crucio | b) | 03/18/19 | f) | - | b) | 29749.5 | b) | - | d) | - | b) | 450 |  | 1 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 10000 | [7 empty] | 1 | 4
[8 empty] | d) | - | d) | - | [11 empty] | 1 | 4
|  |  | Mesaoy - Dasing |  | Road Maintenance | 1.39 | CBRMC | a) | 54152.71 | a) | 01/03/19 | e) | - | a) | 54152.71 | a) | 100% | c) | 100% | a) | 16 | Completed | 1 | 4
| 067 | [6 empty] | b) | Crucio | b) | 03/26/19 | f) | - | b) | 54152.71 | b) | - | d) | - | b) | 480 |  | 1 | 4
[8 empty] | c) | MANDISKAB TRIBAL | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1 | 4
[8 empty] | d) | 3 quarters | d) | - | [11 empty] | 1 | 4
|  |  | Jct. San Juan - Jct. Mesaoy |  | Road Maintenance | 1.82 | MBA | a) | 106788.95 | a) | 01/03/19 | e) | - | a) | 106788.95 | a) | 100% | c) | 100% | a) | 15 | Completed | 1 | 4
| 068 | [6 empty] | b) | Crucio | b) | 03/01/19 | f) | - | b) | 106788.95 | b) | - | d) | - | b) | 450 |  | 1 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 17502.68 | [7 empty] | 1 | 4
[8 empty] | d) | - | d) | - | [11 empty] | 1 | 4
|  |  | Jct. San Juan - Jct. Mesaoy |  | Road Maintenance | 1.82 | CBRMC | a) | 35180.83 | a) | 01/03/19 | e) | - | a) | 35180.83 | a) | 100% | c) | 100% | a) | 16 | Completed | 1 | 4
| 068 | [6 empty] | b) | Crucio | b) | 03/26/19 | f) | - | b) | 35180.83 | b) | - | d) | - | b) | 480 |  | 1 | 4
[8 empty] | c) | MANDISKAB TRIBAL | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1 | 4
[8 empty] | d) | 3 quarters | d) | - | [11 empty] | 1 | 4
|  |  | Mesaoy - Jct. Mahayahay |  | Road Maintenance | 4.6 | MBA | a) | 146984.46 | a) | 01/03/19 | e) | - | a) | 146984.46 | a) | 100% | c) | 100% | a) | 15 | Completed | 1 | 4
| 069 | [6 empty] | b) | Crucio | b) | 03/18/19 | f) | - | b) | 146984.46 | b) | - | d) | - | b) | 450 |  | 1 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 7618.27 | [7 empty] | 1 | 4
[8 empty] | d) | - | d) | - | [11 empty] | 1 | 4
|  |  | Mesaoy - Jct. Mahayahay |  | Road Maintenance | 4.6 | CBRMC | a) | 160103.65 | a) | 01/03/19 | e) | - | a) | 160103.65 | a) | 100% | c) | 100% | a) | 16 | Completed |  | 4
| 069 | [6 empty] | b) | Crucio | b) | 03/22/19 | f) | - | b) | 160103.65 | b) | - | d) | - | b) | 480 |  | 1 | 4
[8 empty] | c) | MAHAYAHAY IFA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1 | 4
[8 empty] | d) | 3 quarters | d) | - | [11 empty] | 1 | 4
4
4
|  |  | Mesaoy - New bohol |  | Road Maintenance | 5.36 | MBA | a) | 165361.13 | a) | 01/03/19 | e) | - | a) | 165361.13 | a) | 100% | c) | 100% | a) | 15 | Completed |  | 4
| 070 | [6 empty] | b) | Crucio | b) | 03/01/19 | f) | - | b) | 165361.13 | b) | - | d) | - | b) | 480 |  | 1 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 2543.9 | [7 empty] | 1 | 4
[8 empty] | d) | - | d) | - | [11 empty] | 1 | 4
|  |  | Mesaoy - New bohol |  | Road Maintenance | 5.36 | CBRMC | a) | 224851.45 | a) | 01/03/19 | e) | - | a) | 224851.45 | a) | 100% | c) | 100% | a) | 16 | Completed |  | 4
| 070 | [6 empty] | b) | Crucio | b) | 03/26/19 | f) | - | b) | 224851.45 | b) | - | d) | - | b) | 480 |  | 1 | 4
[8 empty] | c) | MANDISKAB TRIBAL | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1 | 4
[8 empty] | d) | 3 quarters | d) | - | [11 empty] | 1 | 4
|  |  | Bdry. Tagum - Baca - New Corella |  | Road Maintenance | 13.01 | MBA | a) | 217182.9 | a) | 01/03/19 | e) | - | a) | 217182.9 | a) | 100% | c) | 100% | a) | 15 | Completed | 1 | 4
| 071 | [6 empty] | b) | Crucio | b) | 03/18/19 | f) | - | b) | 217182.9 | b) | - | d) | - | b) | 450 |  | 1 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 19550 | [7 empty] | 1 | 4
[8 empty] | d) | - | d) | - | [11 empty] | 1 | 4
|  |  | Bdry. Tagum - Baca - New Corella |  | Road Maintenance | 13.01 | CBRMC | a) | 214256.36 | a) | 01/03/19 | e) | - | a) | 214256.36 | a) | 100% | c) | 100% | a) | 16 | Completed | 1 | 4
| 071 | [6 empty] | b) | Crucio | b) | 03/26/19 | f) | - | b) | 214256.36 | b) | - | d) | - | b) | 480 |  | 1 | 4
[8 empty] | c) | DURIAN DACUDAO | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1 | 4
[8 empty] | d) | 3 quarters | d) | - | [11 empty] | 1 | 4
|  |  | Prk. 1, Maunlom - Prk. 6 Maunlom Road |  | Road Maintenance | 3.56 | MBA | a) | 150912.87 | a) | 01/03/19 | e) | - | a) | 150912.87 | a) | 100% | c) | 100% | a) | 15 | Completed | 1 | 4
| 147 | [6 empty] | b) | Crucio | b) | 03/01/19 | f) | - | b) | 150912.87 | b) | - | d) | - | b) | 450 |  | 1 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 23025 | [7 empty] | 1 | 4
[8 empty] | d) | - | d) | - | [11 empty] | 1 | 4
|  |  | Prk. 1, Maunlom - Prk. 6 Maunlom Road |  | Road Maintenance | 3.56 | CBRMC | a) | 63973.36 | a) | 01/03/19 | e) | - | a) | 63973.36 | a) | 100% | c) | 100% | a) | 16 | Completed | 1 | 4
| 147 | [6 empty] | b) | Crucio | b) | 03/22/19 | f) | - | b) | 63973.36 | b) | - | d) | - | b) | 480 |  | 1 | 4
[8 empty] | c) | THE BEST VEGETABLE | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1 | 4
[8 empty] | d) | 3 quarters | d) | - | [11 empty] | 1 | 4
[23 empty] | 1 | 4
|  |  | New Visayas - Binancian |  | Road Maintenance | 7.77 | MBA | a) | 14814.34 | a) | 01/03/19 | e) | - | a) | 14814.34 | a) | 100% | c) | 100% | a) | 15 | Completed |  | 44
| 149 | [6 empty] | b) | Crucio | b) | 03/18/19 | f) | - | b) | 14814.34 | b) | - | d) | - | b) | 450 |  | 1 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 5,000.00 | [7 empty] | 1 | 4
[8 empty] | d) | - | d) | - | [11 empty] | 1 | 4
|  |  | New Visayas - Binancian |  | Road Maintenance | 7.77 | CBRMC | a) | 129495.6 | a) | 01/03/19 | e) | - | a) | 129495.6 | a) | 100% | c) | 100% | a) | 16 | Completed | 1 | 4
| 149 | [6 empty] | b) | Crucio | b) | 03/22/19 | f) | - | b) | 129495.6 | b) | - | d) | - | b) | 480 |  | 1 | 4
[8 empty] | c) | BUAN IFA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1 | 4
[8 empty] | d) | 3 quarters | d) | - | [11 empty] | 1 | 4
|  |  | Datu Balong - Prk. Mamalian |  | Road Maintenance | 3.46 | MBA | a) | 117454.89 | a) | 01/03/19 | e) | - | a) | 117454.89 | a) | 100% | c) | 39.37% | a) | 15 | Completed | 1 | 4
| 150 | [6 empty] | b) | Crucio | b) | 03/18/19 | f) | - | b) | 117454.89 | b) | - | d) | - | b) | 450 |  | 1 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 10115 | [7 empty] | 1 | 4
[8 empty] | d) | - | d) | - | [11 empty] | 1 | 4
|  |  | Datu Balong - Prk. Mamalian |  | Road Maintenance | 3.46 | CBRMC | a) | 59264.42 | a) | 01/03/19 | e) | - | a) | 59264.42 | a) | 100% | c) | 100% | a) | 16 | Completed | 1 | 4
| 150 | [6 empty] | b) | Crucio | b) | 03/28/19 | f) | - | b) | 59264.42 | b) | - | d) | - | b) | 480 |  | 1 | 4
[8 empty] | c) | DATU BALONG FA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1 | 4
[8 empty] | d) | 3 quarters | d) | - | [11 empty] | 1 | 4
4
4
4
4
4
4
4
4
4
4
4
| A.2 GENERAL FUND CY 2019 |  |  |  | Road Maintenance | KM | MBA/CBRMC | a) | 11,618,834.00 | a) | 01/03/19 | e) | - | a) | 11,618,834.00 | a) | 66% | c) | 66% | a) | 42 | See list of Provincial Roads
| Road ID |  | 1. Maintenance Of Various Prov'l. Roads and Bridges Dist 2 |  |  | 288.26 |  | b) | Matuguinas | b) | 01/03/19 | f) | - | b) | 11,618,834.00 | b) | - | d) | - | b) | 924 |  | FS
[8 empty] | c) | PEO/CBRMC | c) | 12/31/19 | g) | - | c) | - | [7 empty] | AC
| 11DAN | [8 empty] | d) | - | [11 empty] | AC
[8 empty] | d) | 261 days | d) | - | [11 empty] | AC
|  |  | Cebulano - Mangalcal |  | Road Maintenance | 4.17 | MBA | a) | 142161.87 | a) | 01/03/19 | e) | - | a) | 142161.87 | a) | 100% | c) | 100% | a) | 9 | Completed | AC | 4
|  | 073 | [5 empty] | b) | Clar | b) | 2019-01-15 | f) | - | b) | 142161.87 | b) | - | d) | - | b) | 18 |  | 2 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 118,609.29 | [7 empty] | 2 | 4
[8 empty] | d) | - | d) | - | [11 empty] | 2 | 4
|  |  | Tubod - basa - Mangalcal |  | Road Maintenance | 3.93 | MBA | a) | 156875.9 | a) | 01/03/19 | e) | - | a) | 156875.9 | a) | 100% | c) | 100% | a) | 9 | Completed | 2 | 4
| 074 | [6 empty] | b) | Clar | b) | 2019-01-15 | f) | - | b) | 156875.9 | b) | - | d) | - | b) | 18 |  | 2 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 143,372.65 | [7 empty] | 2 | 4
[8 empty] | d) | - | d) | - | [11 empty] | 2 | 4
|  |  | Upper Mangalcal - Lower Mangalcal |  | Road Maintenance | 2.43 | 0 | a) | 79237.14 | a) | 01/03/19 | e) | - | a) | 79237.14 | a) | 100% | c) | 100% | a) | 9 | Completed | 2 | 4
| 078 | [6 empty] | b) | Clar | b) | 2019-01-14 | f) | - | b) | 79237.14 | b) | - | d) | - | b) | 27 |  | 2 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 69,430.97 | [7 empty] | 2 | 4
[8 empty] | d) | - | d) | - | [11 empty] | 2 | 4
|  |  | Jct. Highway Carmen - Mangalcal - Tubod |  | Road Maintenance | 11.34 | MBA | a) | 463135.67 | a) | 01/03/19 | e) | - | a) | 463135.67 | a) | 100% | c) | 100% | a) | 9 | Completed | 2 | 4
| 082 | [6 empty] | b) | Clar | b) | 01/10/19 | f) | - | b) | 463135.67 | b) | - | d) | - | b) | 45 |  | 2 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 170,106.43 | [7 empty] | 2 | 4
[8 empty] | d) | - | d) | - | [11 empty] | 2 | 4
|  |  | Jct. Highway Carmen - Mangalcal - Tubod |  | Road Maintenance | 11.34 | 0 | a) | 253557.37 | a) | 01/03/19 | e) | - | a) | 253557.37 | a) | 100% | c) | 100% | a) | 10 | Completed | 2 | 4
| 082 | [6 empty] | b) | Maligro | b) | 03/25/19 | f) | - | b) | 253557.37 | b) | - | d) | - | b) | 40 |  | 2 | 4
[8 empty] | c) | TUBOD CENTRO LOWER IRRIGATORS ASSOCIATION | c) | 09/25/19 | g) | 2019-12-31 | c) | - | [7 empty] | 2 | 4
[8 empty] | d) | 3 quarters | d) | - | [11 empty] | 2 | 4
|  |  | Jct. Highway Sto. Niño - Kabanlakan - La Paz |  | Road Maintenance | 2.13 | MBA | a) | 76067.88 | a) | 01/03/19 | e) | - | a) | 76067.88 | a) | 100% | c) | 100% | a) | 9 | Completed | 2 | 4
| 084 | [6 empty] | b) | Clar | b) | 01/10/19 | f) | - | b) | 76067.88 | b) | - | d) | - | b) | 45 |  | 2 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 66,477.91 | [7 empty] | 2 | 4
[8 empty] | d) | - | d) | - | [11 empty] | 2 | 4
|  |  | Ising - Sto Niño |  | Road Maintenance | 2.07 | 0 | a) | 82413.14 | a) | 01/03/19 | e) | - | a) | 82413.14 | a) | 100% | c) | 100% | a) | 5 | Completed | 2 | 4
| 085 | [6 empty] | b) | Clar | b) | 01/17/19 | f) | - | b) | 82413.14 | b) | - | d) | - | b) | 15 |  | 2 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 27,093.24 | [7 empty] | 2 | 4
[8 empty] | d) | - | d) | - | [11 empty] | 2 | 4
|  |  | Ising - Sadpodon - Taba - Dila -Dila |  | Road Maintenance | 5.68 | MBA | a) | 248941.33 | a) | 01/03/19 | e) | - | a) | 248941.33 | a) | 100% | c) | 100% | a) | 9 | Completed | 2 | 4
| 086 | [6 empty] | b) | Clar | b) | 01/12/19 | f) | - | b) | 248941.33 | b) | - | d) | - | b) | 27 |  | 2 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 82,329.02 | [7 empty] | 2 | 4
[8 empty] | d) | - | d) | - |  |  |  | . | [7 empty] | 2 | 4
[23 empty] | 2 | 4
|  |  | Tuganay - taba |  | Road Maintenance | 4.27 | 0 | a) | 291377.9 | a) | 01/03/19 | e) | - | a) | 291377.9 | a) | 70% | c) | 70% | a) | 9 | Completed |  | 4
| 087 | [6 empty] | b) | Clar | b) | 01/09/19 | f) | - | b) | 291377.9 | b) | - | d) | - | b) | 27 |  | 2 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 12/31/2019 | c) | 238,412.28 | [7 empty] | 2 | 4
[8 empty] | d) | - | d) | - | [11 empty] | 2 | 4
|  |  | Jct. Highway Tuganay - Taba |  | Road Maintenance | 4.4 | MBA | a) | 32972.82 | a) | 01/03/19 | e) | - | a) | 32972.82 | a) | 65% | c) | 65% | a) | 9 | Completed | 2 | 4
| 088 | [6 empty] | b) | Clar | b) | 01/22/19 | f) | - | b) | 32972.82 | b) | - | d) | - | b) | 18 |  | 2 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 12/31/2019 | c) | 22,639.09 | [7 empty] | 2 | 4
[8 empty] | d) | - | d) | - | [11 empty] | 2 | 4
|  |  | Jct. Highway Ising - Magsaysay |  | Road Maintenance | 10.84 | 0 | a) | 417818.12 | a) | 01/03/19 | e) | - | a) | 417818.12 | a) | 60% | c) | 60% | a) | 10 | Completed | 2 | 4
| 089 | [6 empty] | b) | Clar | b) | 01/22/19 | f) | - | b) | 417818.12 | b) | - | d) | - | b) | 50 |  | 2 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 12/31/2019 | c) | 313,488.39 | [7 empty] | 2 | 4
[8 empty] | d) | - | d) | - | [11 empty] | 2 | 4
4
4
4
|  |  | New Camiling - Alejal - Lower Magsaysay |  | Road Maintenance | 6.73 | MBA | a) | 240878.08 | a) | 01/03/19 | e) | - | a) | 240878.08 | a) | 80% | c) | 80% | a) | 4 | Completed | 2 | 4
| 091 | [6 empty] | b) | Clar | b) | 01/22/19 | f) | - | b) | 240878.08 | b) | - | d) | - | b) | 20 |  | 2 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 12/31/2019 | c) | - | [7 empty] | 2 | 4
[8 empty] | d) | - | d) | - | [11 empty] | 2 | 4
|  |  | Jct. highway Tuganay - Anibongan |  | Road Maintenance | 3.66 | 0 | a) | 150684.44 | a) | 01/03/19 | e) | - | a) | 150684.44 | a) | 100% | c) | 100% | a) | 6 | Completed | 2 | 4
| 094 | [6 empty] | b) | Clar | b) | 01/22/19 | f) | - | b) | 150684.44 | b) | - | d) | - | b) | 18 |  | 2 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 12/31/2019 | c) | - | [7 empty] | 2 | 4
[8 empty] | d) | - | d) | - | [11 empty] | 2 | 4
|  |  | Anibongan - Guadalupe |  | Road Maintenance | 2.48 | MBA | a) | 91325.06 | a) | 01/03/19 | e) | - | a) | 91325.06 | a) | 100% | c) | 100% | a) | 9 | Completed | 2 | 4
| 095 | [6 empty] | b) | Clar | b) | 01/23/19 | f) | - | b) | 91325.06 | b) | - | d) | - | b) | 18 |  | 2 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 12/31/2019 | c) | - | [7 empty] | 2 | 4
[8 empty] | d) | - | d) | - | [11 empty] | 2 | 4
|  |  | Tuganay - Anibongan - San Isidro |  | Road Maintenance | 7.22 | 0 | a) | 139979.8 | a) | 01/03/19 | e) | - | a) | 139979.8 | a) | 100% | c) | 100% | a) | 9 | Completed | 2 | 4
| 096 | [6 empty] | b) | Clar | b) | 01/24/19 | f) | - | b) | 139979.8 | b) | - | d) | - | b) | 36 |  | 2 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 12/31/2019 | c) | 1890.37 | [7 empty] | 2 | 4
[8 empty] | d) | - | d) | - | [11 empty] | 2 | 4
|  |  | Jct. Anibongan - Prk. 2, 7, 5, San Isidro |  | Road Maintenance | 3.14 | MBA | a) | 104378.03 | a) | 01/03/19 | e) | - | a) | 104378.03 | a) | 100% | c) | 100% | a) | 10 | Completed | 2 | 4
| 097 | [6 empty] | b) | Clar | b) | 01/24/19 | f) | - | b) | 104378.03 | b) | - | d) | - | b) | 20 |  | 2 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 12/31/2019 | c) | 56,087.50 | [7 empty] | 2 | 4
[8 empty] | d) | - | d) | - | [11 empty] | 2 | 4
|  |  | Anibongan - Salvacion - Cabay-angan |  | Road Maintenance | 6.93 | 0 | a) | 415461.61 | a) | 01/03/19 | e) | - | a) | 415461.61 | a) | 100% | c) | 100% | a) | 9 | Completed | 2 | 4
| 098 | [6 empty] | b) | Clar | b) | 01/25/19 | f) | - | b) | 415461.61 | b) | - | d) | - | b) | 45 |  | 2 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 12/31/2019 | c) | - | [7 empty] | 2 | 4
[8 empty] | d) | - | d) | - | [11 empty] | 2 | 4
|  |  | Jct. Highway Guadalupe - Bdry. Tagum |  | Road Maintenance | 7.9 | MBA | a) | 456131.09 | a) | 01/03/19 | e) | - | a) | 456131.09 | a) | 100% | c) | 100% | a) | 9 | Completed | 2 | 4
| 101 | [6 empty] | b) | Clar | b) | 01/25/19 | f) | - | b) | 456131.09 | b) | - | d) | - | b) | 18 |  | 2 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 12/31/2019 | c) | - | [7 empty] | 2 | 4
[8 empty] | d) | - | d) | - | [11 empty] | 2 | 4
|  |  | Jct. Highway Guadalupe - Bdry. Tagum |  | Road Maintenance | 7.9 | 0 | a) | 228201.66 | a) | 01/03/19 | e) | - | a) | 228201.66 | a) | 100% | c) | 100% | a) | 8 | Completed | 2 | 4
| 101 | [6 empty] | b) | Maligro | b) | 03/25/19 | f) | - | b) | 228201.66 | b) | - | d) | - | b) | 40 |  | 2 | 4
[8 empty] | c) | LAMPIA PAG-ASA IRRIGATORS ASSOCIATION, INC. | c) | 12/25/19 | g) | 12/31/2019 | c) | - | [7 empty] | 2 | 4
[8 empty] | d) | 3 quarters | d) | - | [11 empty] | 2 | 4
|  |  | Poblacion Dujali - Prk. 8 Dujali |  | Road Maintenance | 8.2 | MBA | a) | 285600.05 | a) | 01/03/19 | e) | - | a) | 285600.05 | a) | 100% | c) | 100% | a) | 10 | Completed | 2 | 4
| 105 | [6 empty] | b) | Clar | b) | 01/28/19 | f) | - | b) | 285600.05 | b) | - | d) | - | b) | 50 |  | 2 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 12/31/2019 | c) | - | [7 empty] | 2 | 4
[8 empty] | d) | - | d) | - | [11 empty] | 2 | 4
|  |  | Dujali - San Isidro |  | Road Maintenance | 3 | 0 | a) | 130319.3 | a) | 01/03/19 | e) | - | a) | 130319.3 | a) | 100% | c) | 100% | a) | 8 | Completed | 2 | 4
| 107 | [6 empty] | b) | Gamad | b) | 01/28/19 | f) | - | b) | 130319.3 | b) | - | d) | - | b) | 30 |  | 2 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 12/31/2019 | c) | 45,943.12 | [7 empty] | 2 | 4
[8 empty] | d) | - | d) | - | [11 empty] | 2 | 4
|  |  | Prk. 5, RJS - Prk. 6 New Casay |  | Road Maintenance | 2.73 | MBA | a) | 235277 | a) | 01/03/19 | e) | - | a) | 235277 | a) | 100% | c) | 100% | a) | 2 | Completed | 2 | 4
| 109 | [6 empty] | b) | Gamad | b) | 01/28/19 | f) | - | b) | 235277 | b) | - | d) | - | b) | 6 |  | 2 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 12/31/2019 | c) | 90,745.35 | [7 empty] | 2 | 4
[8 empty] | d) | - | d) | - | [11 empty] | 2 | 4
|  |  | Prk. 5 - Prk. 1 Pawas Dujali |  | Road Maintenance | 2.18 | 0 | a) | 76067.68 | a) | 01/03/19 | e) | - | a) | 76067.68 | a) | 100% | c) | 100% | a) | 10 | Completed | 2 | 4
| 112 | [6 empty] | b) | Gamad | b) | 01/18/19 | f) | - | b) | 76067.68 | b) | - | d) | - | b) | 20 |  | 2 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 12/31/2019 | c) | 40,112.50 | [7 empty] | 2 | 4
[8 empty] | d) | - | d) | - | [11 empty] | 2 | 4
|  |  | Dujali - Balisong - Magupising |  | Road Maintenance | 5.52 | MBA | a) | 260591.93 | a) | 01/03/19 | e) | - | a) | 260591.93 | a) | 100% | c) | 100% | a) | 4 | Completed | 2 | 4
| 113 | [6 empty] | b) | Gamad | b) | 01/09/19 | f) | - | b) | 260591.93 | b) | - | d) | - | b) | 8 |  | 2 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 12/31/2019 | c) | - | [7 empty] | 2 | 4
[8 empty] | d) | - | d) | - | [11 empty] | 2 | 4
4
4
4
|  |  | Dujali - Pawas - San Vicente |  | Road Maintenance | 4.42 | 0 | a) | 139536.42 | a) | 01/03/19 | e) | - | a) | 139536.42 | a) | 100% | c) | 100% | a) | 10 | Completed | 2 | 4
| 117 | [6 empty] | b) | Gamad | b) | 01/22/19 | f) | - | b) | 139536.42 | b) | - | d) | - | b) | 18 |  | 2 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 12/31/2019 | c) | 52,133.86 | [7 empty] | 2 | 4
[8 empty] | d) | - | d) | - | [11 empty] | 2 | 4
|  |  | Jct. Salvacion - San Vicente - Cabay-angan |  | Road Maintenance | 3.45 | MBA | a) | 247460.9 | a) | 01/03/19 | e) | - | a) | 247460.9 | a) | 100% | c) | 100% | a) | 10 | Completed | 2 | 4
| 118 | [6 empty] | b) | Gamad | b) | 01/23/19 | f) | - | b) | 247460.9 | b) | - | d) | - | b) | 18 |  | 2 | 4
[8 empty] | c) | PEO | c) | 02/31/19 | g) | 12/31/2019 | c) | 151,887.50 | [7 empty] | 2 | 4
[8 empty] | d) | - | d) | - | [11 empty] | 2 | 4
|  |  | Jct. Salvacion - San Vicente - Cabay-angan |  | Road Maintenance | 3.45 | 0 | a) | 152134.44 | a) | 01/03/19 | e) | - | a) | 152134.44 | a) | 100% | c) | 100% | a) | 8 | Completed | 2 | 4
| 118 | [6 empty] | b) | Gamad | b) | 03/26/19 | f) | - | b) | 152134.44 | b) | - | d) | - | b) | 36 |  | 2 | 4
[8 empty] | c) | BALISONG SAN VICENTE IRRIGATORS ASSOCIATION | c) | 12/26/19 | g) | 12/31/2019 | c) | [8 empty] | 2 | 4
[8 empty] | d) | 3 quarters | d) | - | [10 empty] | Completed | 2 | 4
|  |  | Dujali - San Miguel |  | Road Maintenance | 3.95 | MBA | a) | 101202.04 | a) | 01/03/19 | e) | - | a) | 101202.04 | a) | 80% | c) | 90% | a) | 11 |  | 2 | 4
| 119 | [6 empty] | b) | Gamad | b) | 01/10/19 | f) | - | b) | 101202.04 | b) | - | d) | - | b) | 22 |  | 2 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | - | c) | 90,350.03 | [7 empty] | 2 | 4
[8 empty] | d) | - | d) | - | [11 empty] | 2 | 4
|  |  | San Miguel - Casig-ang |  | Road Maintenance | 2.55 | 0 | a) | 79237.14 | a) | 01/03/19 | e) | - | a) | 79237.14 | a) | 100% | c) | 100% | a) | 10 | Completed | 2 | 4
| 122 | [6 empty] | b) | Gamad | b) | 01/24/19 | f) | - | b) | 79237.14 | b) | - | d) | - | b) | 10 |  | 2 | 4
[8 empty] | c) | BALISONG SAN VICENTE IRRIGATORS ASSOCIATION | c) | 12/31/19 | g) | 12/31/2019 | c) | 40,112.50 | [7 empty] | 2 | 4
[8 empty] | d) | - | d) | - | [11 empty] | 2 | 4
|  |  | Prk. Magsaysay - Lunga-og - Dalisay |  | Road Maintenance | 2.81 | MBA | a) | 79762.14 | a) | 01/03/19 | e) | - | a) | 79762.14 | a) | 100% | c) | 100% | a) | 8 | Completed | 2 | 4
| 127 | [6 empty] | b) | Gamad | b) | 01/30/19 | f) | - | b) | 79762.14 | b) | - | d) | - | b) | 8 |  | 2 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 12/31/2019 | c) | 40,612.50 | [7 empty] | 2 | 4
[8 empty] | d) | - | d) | - | [11 empty] | 2 | 4
|  |  | Prk. Apitong - Upper Balisong - Dalisay |  | Road Maintenance | 4.6 | 0 | a) | 137846.03 | a) | 01/03/19 | e) | - | a) | 137846.03 | a) | 100% | c) | 100% | a) | 8 | Completed | 2 | 4
| 128 | [6 empty] | b) | Gamad | b) | 01/31/19 | f) | - | b) | 137846.03 | b) | - | d) | - | b) | 8 |  | 2 | 4
[8 empty] | c) | BALISONG SAN VICENTE IRRIGATORS ASSOCIATION | c) | 12/31/19 | g) | 12/31/2019 | c) | - | [7 empty] | 2 | 4
[8 empty] | d) | - | d) | - | [11 empty] | 2 | 4
|  |  | Sitio Paradise - Magkakaisa - Esperanza |  | Road Maintenance | 1.75 | MBA | a) | 66552.75 | a) | 01/03/19 | e) | - | a) | 66552.75 | a) | 100% | c) | 100% | a) | 8 | Completed | 2 | 4
| 129 | [6 empty] | b) | 79762.14 | b) | 01/22/19 | f) | - | b) | 66552.75 | b) | - | d) | - | b) | 8 |  | 2 | 4
[8 empty] | c) | Gamad | c) | 12/31/19 | g) | 12/31/2019 | c) | 22,246.26 | [7 empty] | 2 | 4
[8 empty] | d) | - | d) | - | [11 empty] | 2 | 4
|  |  | Los Amigos 1 - Esperanza - Los Amigos 2 |  | Road Maintenance | 3.59 | 0 | a) | 101202.04 | a) | 01/03/19 | e) | - | a) | 101202.04 | a) | 100% | c) | 100% | a) | 10 | Completed | 2 | 4
| 130 | [6 empty] | b) | Gamad | b) | 01/24/19 | f) | - | b) | 101202.04 | b) | - | d) | - | b) | 20 |  | 2 | 4
[8 empty] | c) | BALISONG SAN VICENTE IRRIGATORS ASSOCIATION | c) | 12/31/19 | g) | 12/31/2019 | c) | 50,837.50 | [7 empty] | 2 | 4
[8 empty] | d) | - | d) | - | [11 empty] | 2 | 4
|  |  | Mugas - Lunga-og |  | Road Maintenance | 2.68 | MBA | a) | 66552.75 | a) | 01/03/19 | e) | - | a) | 91,693.64 | a) | 100% | c) | 100% | a) | 6 | Completed | 2 | 4
| 132 | [6 empty] | b) | 79762.14 | b) | 01/17/19 | f) | - | b) | 91,693.64 | b) | - | d) | - | b) | 24 |  | 2 | 4
[8 empty] | c) | Gamad | c) | 12/31/19 | g) | 12/31/2019 | c) | 50,837.50 | [7 empty] | 2 | 4
[8 empty] | d) | - | d) | - | [11 empty] | 2 | 4
|  |  | Pantaron - Mugas |  | Road Maintenance | 3.35 | 0 | a) | 101202.04 | a) | 01/03/19 | e) | - | a) | 101202.04 | a) | 100% | c) | 100% | a) | 9 | Completed | 2 | 4
| 133 | [6 empty] | b) | Gamad | b) | 01/23/19 | f) | - | b) | 101202.04 | b) | - | d) | - | b) | 18 |  | 2 | 4
[8 empty] | c) | BALISONG SAN VICENTE IRRIGATORS ASSOCIATION | c) | 12/31/19 | g) | 12/31/2019 | c) | 90,349.93 | [7 empty] | 2 | 4
[8 empty] | d) | - | d) | - | [11 empty] | 2 | 4
|  |  | Sto. Tomas - Bdry. Mamacao |  | Road Maintenance | 4.9 | MBA | a) | 110710.44 | a) | 01/03/19 | e) | - | a) | 110710.44 | a) | 100% | c) | 100% | a) | 10 | Completed | 2 | 4
| 135 | [6 empty] | b) | 79762.14 | b) | 01/21/19 | f) | - | b) | 110710.44 | b) | - | d) | - | b) | 40 |  | 2 | 4
[8 empty] | c) | Gamad | c) | 12/31/19 | g) | 12/31/2019 | c) | 50,837.50 | [7 empty] | 2 | 4
[8 empty] | d) | - | d) | - | [11 empty] | 2 | 4
|  |  | Fd. Rd. 3 - San Jose |  | Road Maintenance | 4.55 | 0 | a) | 147367.49 | a) | 01/03/19 | e) | - | a) | 147367.49 | a) | 100% | c) | 100% | a) | 10 | Completed | 2 | 4
| 136 | [6 empty] | b) | Gamad | b) | 01/25/19 | f) | - | b) | 147367.49 | b) | - | d) | - | b) | 30 |  | 2 | 4
[8 empty] | c) | BALISONG SAN VICENTE IRRIGATORS ASSOCIATION | c) | 12/31/19 | g) | 12/31/2019 | c) | 56,174.69 | [7 empty] | 2 | 4
[8 empty] | d) | - | d) | - | [11 empty] | 2 | 4
4
4
|  |  | Menzi - balagunan - Tulalian |  | Road Maintenance | 10.63 | MBA | a) | 520167.79 | a) | 01/03/19 | e) | - | a) | 520167.79 | a) | 100% | c) | 100% | a) | 6 | Completed | 2 | 4
| 138 | [6 empty] | b) | 79762.14 | b) | 01/07/19 | f) | - | b) | 520167.79 | b) | - | d) | - | b) | 18 |  | 2 | 4
[8 empty] | c) | Gamad | c) | 12/31/19 | g) | 12/31/2019 | c) | 204,850.57 | [7 empty] | 2 | 4
[8 empty] | d) | - | d) | - | [11 empty] | 2 | 4
|  |  | Jct. Bdry. Tagum - Talomo |  | Road Maintenance | 12.01 | 0 | a) | 407429.19 | a) | 01/03/19 | e) | - | a) | 407429.19 | a) | 100% | c) | 100% | a) | 10 | Completed | 2 | 4
| 145 | [6 empty] | b) | Gamad | b) | 01/11/19 | f) | - | b) | 407429.19 | b) | - | d) | - | b) | 50 |  | 2 | 4
[8 empty] | c) | BALISONG SAN VICENTE IRRIGATORS ASSOCIATION | c) | 12/31/19 | g) | 12/31/2019 | c) | 168,544.84 | [7 empty] | 2 | 4
[8 empty] | d) | - | d) | - | [11 empty] | 2 | 4
|  |  | San Jose - Sitio Mahayahay, Magwawa |  | Road Maintenance | 0.84 | MBA | a) | 7919.35 | a) | 01/03/19 | e) | - | a) | 7919.35 | a) | 100% | c) | 100% | a) | 2 | Completed | 2 | 4
| 151 | [6 empty] | b) | 79762.14 | b) | 01/16/19 | f) | - | b) | 7919.35 | b) | - | d) | - | b) | 8 |  | 2 | 4
[8 empty] | c) | Gamad | c) | 12/31/19 | g) | 12/31/2019 | c) | 1,509.27 | [7 empty] | 2 | 4
[8 empty] | d) | - | d) | - | [11 empty] | 2 | 4
|  | M. | 20% DEVELOPMENT FUND CY 2019 | [19 empty] | FS
| Road ID |  | 1. Rehabilitation Of Various Prov'l. Roads and Bridges Dist 2 |  | Road Rehabilitation | KM | Admin | a) | 46740117 | [12 empty] | See list of Provincial Roads
[6 empty] | 115.62 |  | b) | Matuguinas | [13 empty] | AC
| 11DAN | [6 empty] | c) | PEO | [13 empty] | AC
AC
[8 empty] | d) | 261 days | [13 empty] | AC
|  |  | Jct. Highway Sto. Niño - Cebulano |  | Road Rehabilitation | 2.09 | Admin | a) | 1045000 | a) | 2019-03-18 | e) | - | a) | 1045000 | a) | 20% | c) | 20% | a) | 11 | On-going | AC
| 072 | [6 empty] | b) | Obar | b) | 2019-05-21 | f) | - | b) | 1045000 | b) | - | d) | - | b) | 55 |  | 2
[8 empty] | c) | PEO | c) | 2020-02-02 | g) | - | c) | - | [7 empty] | 2
[8 empty] | d) | - | d) | - | [11 empty] | 2
[5 empty] | Road Rehabilitation |  |  | a.) 515,000.00 |  | a.) 03/12/19 |  |  |  | a.) 515,000.00 | [8 empty] | 2
|  |  | Jct. Highway -Tubod - Bagong Silang |  |  |  |  | b.) Clar |  | b.) March 18, 2019 |  |  |  | b.) 515,000.00 | [7 empty] | Completed | 2
[12 empty] | g.) June 15, 2019 | [10 empty] | 2
2
|  |  | Basa - Tubod |  | Road Rehabilitation | 1.56 | Admin | a) | 1000000 | a) | 2019-06-19 | e) | - | a) | 1000000 | a) | - | c) | - | a) | - | On-going | 2
| 076 | [6 empty] | b) | Piad | b) | 2019-11-11 | f) | - | b) | 1000000 | b) | - | d) | - | b) | - |  | 2
[8 empty] | c) | - | c) | 2020-03-09 | g) | - | c) | - | [7 empty] | 2
[8 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | Tubod - Pilar |  | Road Rehabilitation | 1.55 | Admin | a) | 16000000 | a) | 06/19/19 & 12/9/19 | e) | - | a) | 16000000 | a) | - | c) | - | a) | - | On-going | 2
| 077 | [6 empty] | b) | Gamad/Clar | b) | 2019-12-18 | f) | - | b) | 16000000 | b) | - | d) | - | b) | - |  | 2
[8 empty] | c) | - | c) | 2020-11-05 | g) | - | c) | - | [7 empty] | 2
[8 empty] | d) | - | d) | - | [11 empty] | 2
[5 empty] | Road Rehabilitation |  |  | a.) 390,000.00 |  | a.) 03/12/19 |  |  |  | a.) 390,000.00 | [8 empty] | 2 | 4
|  |  | Cebulano- Luceta |  |  |  |  | b.) Clar |  | b.) March 8, 2019 |  |  |  | b.) 390,000.00 | [7 empty] | Completed | 2 | 4
[12 empty] | g.) June 15, 2019 | [10 empty] | 2 | 4
[23 empty] | 2 | 4
[5 empty] | Road Rehabilitation |  |  | a.) 295,000.00 |  | a.) 03/12/19 |  |  |  | a.) 295,000.00 | [8 empty] | 2 | 4
|  |  | Lower Asuncion - Upper Asuncion |  |  |  |  | b.) Clar |  | b.) March 18, 2019 |  |  |  | b.) 295,000.00 | [7 empty] | Completed | 2 | 4
[12 empty] | g.) June 15, 2019 | [10 empty] | 2 | 4
[23 empty] | 2 | 4
[5 empty] | Road Rehabilitation |  |  | a.) 1,220,000.00 |  | a.) 03/12/19 |  |  |  | a.) 1,220,000.00 | [8 empty] | 2
|  |  | Jct. Highway - Sto. Nino - La Paz - San Vicente |  |  |  |  | b.)Obar |  | b.) March 18, 2019 |  |  |  | b.) 1,220,000.00 | [7 empty] | Completed | 2
[12 empty] | g.) Sept. 30, 2019 | [10 empty] | 2
2
|  |  | Alejal - Alemag |  | Road Rehabilitation | 1.79 |  | a) | 970000 | a) | 2019-03-18 | e) | - | a) | 970000 | a) | 100% | c) | 100% | a) | 7 | Completed. Financially completed | 2
| 092 | [6 empty] | b) | Gamad/Clar | b) | 2019-05-20 | f) | - | b) | 970000 | b) | 100 | d) | 0% | b) | 20 |  | 2
[8 empty] | c) | - | c) | 2019-09-12 | g) | Sept. 30, 2019 | c) | - | [7 empty] | 2
[8 empty] | d) | - | d) | - | [11 empty] | 2
[5 empty] | Road Rehabilitation |  |  | a.) 640,000.00 |  | a.) 03/12/19 |  |  |  | a.) 640,000.00 | [8 empty] | 2
|  |  | Mabaus - Cabay -angan |  |  |  |  | b.)Clar |  | b.) Maech 18, 2019 |  |  |  | a.) 640,000.00 | [7 empty] | Completed | 2
[12 empty] | g.) July 30, 2019 | [10 empty] | 2
2
[5 empty] | Road Rehabilitation |  |  | a.) 280,000.00 |  | a.) 03/12/19 |  |  |  | a.) 280,000.00 | [8 empty] | 2
|  |  | Mabaus - Salvacion |  |  |  |  | b.)Clar |  | b.) March 18, 2019 |  |  |  | a.) 280,000.00 | [8 empty] | 2
[12 empty] | g.) June 30, 2019 | [9 empty] | Completed | 2
2
|  |  | Dalisay - Mabuhay |  | Road Rehabilitation | 3.25 | Admin | a) | 1000000 | a) | 2019-05-16 | e) | - | a) | 1000000 | a) | 80% | c) | 80% | a) | 10 | On-going | 2
| 102 | [6 empty] | b) | Gamad/Clar | b) | 2019-06-17 | f) |  | b) | 1000000 | b) |  | d) | - | b) | 20 |  | 2
[8 empty] | c) | - | c) | 2019-12-29 | g) | - | c) | - | [7 empty] | 2
[8 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | Sitio Malaga - Tibulao |  | Road Rehabilitation | 3.22 | Admin | a) | 1000000 | a) | 2019-06-25 | e) | - | a) | 1000000 | a) | - | c) | - | a) | - | On-going | 2
| 103 | [6 empty] | b) | Gamad/Clar | b) | 2020-11-11 | f) | - | b) | 1000000 | b) | - | d) | - | b) | - |  | 2
[8 empty] | c) | - | c) | 2020-02-09 | g) | - | c) | - | [7 empty] | 2
[8 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | Dujali - Tanglaw |  | Road Rehabilitation | 3.6 | Admin | a) | 2075000 | a) | 2019-10-03 | e) | - | a) | 2075000 | a) | - | c) | - | a) | - | On-going | 2
| 104 | [6 empty] | b) | Balbastro | b) | 2019-12-28 | f) | - | b) | 2075000 | b) | - | d) | - | b) | - |  | 2
[8 empty] | c) | - | c) | 2020-04-16 | g) | - | c) | - | [7 empty] | 2
[8 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | Dujali - New Casay |  |  | 3.2 | Admin | a) | 640000 | a) | 2019-05-16 | e) | - | a) | 640000 | a) | 100% | c) | 100% | a) | 10 |  | 2 | 4
| 106 | [6 empty] | b) | Gamad/Clar | b) | 2019-06-17 | f) | 40 | b) | 640000 | b) |  | d) | - | b) | 40 | Completed | 2 | 4
[8 empty] | c) | - | c) |  | g) | 10/15/2019 | c) | - | [7 empty] | 2 | 4
[8 empty] | d) | - | d) | - | [11 empty] | 2 | 4
[5 empty] | Road Rehabilitation |  |  | a.) 450,000.00 |  | a.) 03/12/19 |  |  |  | a.) 450,000.00 | [8 empty] | 2
|  |  | New Casay - Bugtong Talisay |  |  |  |  | b.)Clar |  | b.) March 18, 2019 |  |  |  | a.) 450,000.00 | [7 empty] | Completed | 2
[12 empty] | g.)June 30, 2019 | [10 empty] | 2
2
|  |  | Cabay-angan - Esperanza |  | Road Rehabilitation | 5.37 | Admin | a) | 1300000 | a) | 2019-05-16 | e) | - | a) | 1300000 | a) | 80% | c) | 80% | a) | 9 | On- going | 2
| 110 | [6 empty] | b) | Gamad/Clar | b) | 2019-06-17 | f) | - | b) | 1300000 | b) | - | d) | - | b) | 36 |  | 2
[8 empty] | c) | PEO | c) | 2020-02-29 | g) | - | c) | - | [7 empty] | 2
[8 empty] | d) | - | d) | [12 empty] | 2
[5 empty] | Road Rehabilitation |  |  | a.)220,000.00 |  | a.) 03/12/19 |  |  |  | a.)220,000.00 |  | a.) 100 % |  | c.)100% |  |  |  |  | 2
|  |  | Purok 6 Cabay-angan - Esti |  |  |  |  | b.) Gamad |  | b.) March 18, 2019 |  |  |  | a.)220,000.00 | [7 empty] | Completed | 2
[12 empty] | g.) June 30, 2019 | [10 empty] | 2
2
[5 empty] | Road Rehabilitation |  |  | a.)250,000.00 |  | a.) March 12, 2019 | [5 empty] | a.) 100 % |  | c.)100% |  |  |  |  | 2
|  |  | Dujali - Sitio Pawas |  |  |  |  | b.) Gamad |  | b.) March 18, 2019 | [11 empty] | Completed | 2
[12 empty] | g.) Jun 30, 2019 | [10 empty] | 2
2
[5 empty] | Road Rehabilitation |  |  | a.) 280,000.00 |  | a.) March 12, 2019 | [5 empty] | a.) 100 % |  | c.)100% |  |  |  |  | 2
|  |  | Purok 1 to Purok 2 Sitio Pawas | [5 empty] | b.) Gamad | b.) March 18, 2019 | [11 empty] | Completed | 2
[12 empty] | g.) Jun 30, 2019 | [10 empty] | 2
2
|  |  | San Miguel - Crossing Kinamayan |  | Road Rehabilitation | 2.8 | Admin | a) | 560000 | a) | 2019-06-25 | e) | - | a) | 560000 | a.) 100 % |  | c.)100% |  | a) | - |  | 2 | 4
| 120 | [6 empty] | b) | Nasol | b) | Sept. 19, 2019 | f) | - | b) | 560000 | b) | - | d) | - | b) | - | Completed | 2 | 4
[8 empty] | c) | - | c) | - | g) | Nov. 30, 2019 | c) | - | [7 empty] | 2 | 4
[8 empty] | d) | - | d) | - | [11 empty] | 2 | 4
|  |  | San Miguel -Libertad Provincial Road |  | Road Rehabilitation | 6.2 | Admin | a) | 1240000 | a) | 2019-05-29 | e) | - | a) | 1240000 | a) | 59.41% | c) | 59.41% | a) | 9 | On-going | 2
| 121 | [6 empty] | b) | Gamad | b) | 2019-06-17 | f) |  | b) | 1240000 | b) | - | d) | - | b) | 36 |  | 2
[8 empty] | c) | - | c) | 2020-02-29 | g) | - | c) | - | [7 empty] | 2
[8 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | Bacali - Casig-ang - Libertad |  | Road Rehabilitation | 4.7 | Admin | a) | 940000 | a) | 2019-06-07 | e) | - | a) | 940000 | a) | 80% | c) | 80% | a) | 9 | On-going | 2
| 123 | [6 empty] | b) | Gamad | b) | 2019-06-27 | f) | 35 CD | b) | 940000 | b) | - | d) | - | b) | 36 |  | 2
[8 empty] | c) | Admin | c) | 2020-02-29 | g) | - | c) | - | [7 empty] | 2
[8 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | Kinamayan - Moslog - Mahayag |  | Road Rehabilitation | 3.23 | Admin | a) | 1000000 | a) | 2019-05-20 | e) | - | a) | 1000000 | a) | 80% | c) | 80% | a) | 10 | On going | 2
| 124 | [6 empty] | b) | Gamad | b) | 2019-06-27 | f) | 29 CD | b) | 1000000 | b) | - | d) | - | b) | 20 |  | 2
[8 empty] | c) | PEO | c) | 2020-02-29 | g) | - | c) | - | [7 empty] | 2
[8 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | San Miguel - Moslog - Kinamayan |  | Road Rehabilitation | 2.9 | Admin | a) | 1000000 | a) | 2019-05-20 | e) | - | a) | 1000000 | a) | 80% | c) | 80% | a) | 6 | On-going | 2
| 125 | [6 empty] | b) | Gamad | b) | 2019-06-27 | f) | 29 CD | b) | 1000000 | b) | - | d) | - | b) | 24 |  | 2
[8 empty] | c) | - | c) | 2020-02-29 | g) | - | c) | - | [7 empty] | 2
[8 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | Kinamayan - Lunga-og |  | Road Rehabilitation | 2.59 | Admin | a) | 520000 | a) | 2019-03-18 | e) | - | a) | 520000 | a) | 100% | c) | 100% | a) | 9 | Completed | 2
| 126 | [6 empty] | b) | Gamad/Clar | b) | 5/202/019 | f) | - | b) | 520000 | b) | - | d) | - | b) | 36 |  | 2
[8 empty] | c) | - | c) |  | g) | Sept. 30, 2019 | c) | - | [7 empty] | 2
[8 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | Mugas - Lanatad |  | Road Rehabilitation | 1.53 | Admin | a) | 500000 | a) |  | e) | - | a) | 500000 | a) | - | c) | - | a) | - | On-going | 2
| 131 | [6 empty] | b) | Balbastro | b) | 2019-08-05 | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 2
[8 empty] | c) | - | c) | 2020-02-20 | g) | - | c) | - | [7 empty] | 2
[8 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | New Katipunan - Pantaron |  | Road Rehabilitation | 1.96 | Admin | a) | 395000 | a) | 2019-03-12 | e) | - | a) | 395000 | a) | - | c) | - | a) | - | On-going | 2
| 134 | [6 empty] | b) | Gamad/Clar | b) | 2019-12-27 | f) | - | b) | 395000 | b) | - | d) | - | b) | - |  | 2
[8 empty] | c) | - | c) | 2020-02-25 | g) | - | c) | - | [7 empty] | 2
[8 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | Fd. Rd. 2 - Sto. Tomas - Magwawa |  | Road Rehabilitation | 10.21 | Admin | a) | 3575000 | a) | June `19, 2019 | e) | - | a) | 3575000 | a) | 40% | c) | 40% | a) | - | On-going | 2
| 137 | [6 empty] | b) | Gamad/Clar | b) | 2019-08-27 | f) | - | b) | 3575000 | b) | - | d) | - | b) | - |  | 2
[8 empty] | c) | - | c) | 2020-01-24 | g) | - | c) | - | [7 empty] | 2
[8 empty] | d) | - | d) | - | [11 empty] | 2
[8 empty] | a.) 540,000.00 |  | a.) March 12, 2019 |  |  |  | a.) 540,000.00 |  | a.)100% |  | c.)100% |  |  |  | Completed | 2
|  |  | Nafco - Bobongon |  | Road Rehabilitation |  |  | b. Gamad |  | b.) march 18, 2019 |  |  |  | b.) 540,000.00 | [8 empty] | 2
[12 empty] | g.) June 30, 2019 | [10 empty] | 2
2
2
|  |  | Jct. Highway - Tanglaw |  | Road Rehabilitation | 3.98 | Admin | a) | 1100000 | a) | 2019-05-16 | e) | - | a) | 1100000 | a) | 85% | c) | 85% | a) | 10 | On-going | 2
| 142 | [6 empty] | b) | Gamad/Clar | b) | 2019-06-17 | f) | 29 CD | b) | 1100000 | b) | - | d) | - | b) | 20 |  | 2
[8 empty] | c) | PEO | c) | 2020-02-29 | g) | - | c) | - | [7 empty] | 2
[8 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | Kimamon - Lunga-og - Talomo |  | Road Rehabilitation | 5.99 | Admin | a) | 1800000 | a) | 2019-05-20 | e) | - | a) | 1800000 | a) | 73.31% | c) | 73.31% | a) | 9 | On-going | 2
| 144 | [6 empty] | b) | Gamad | b) | 2019-06-17 | f) | - | b) | 1800000 | b) | - | d) | - | b) | 6 |  | 2
[8 empty] | c) | PEO | c) | 2020-02-27 | g) | - | c) | - | [7 empty] | 2
[8 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | Bdry. Tagum - Crossing Kinamayan Sto. Tomas |  | Road Rehabilitation | 0.75 | Admin | a) | 3700000 | a) | 2019-12-06 | e) | - | a) | 3700000 | a) | - | c) | - | a) | - | On-going | 2
| 146 | [6 empty] | b) | Gamad/Clar | b) | 2019-12-27 | f) | - | b) | 3700000 | b) | - | d) | - | b) | - |  | 2
[8 empty] | c) | - | c) | 2020-04-25 | g) | - | c) | - | [7 empty] | 2
[8 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | Prk. Narafil - Prk. Daisy Magupising |  | Road Rehabilitation | 19.16 | Admin | a) | 300117 | a) | 2019-06-25 | e) | - | a) | 300117 | a) | 100% | c) | 100% | a) | - | Completed | 2 | 4
| 148 | [6 empty] | b) | Gamad/Clar | b) | Sept. 16, 2019 | f) | - | b) | 300117 | b) | - | d) | - | b) | - |  | 2 | 4
[8 empty] | c) | - | c) | - | g) | Oct. 18, 2019 | c) | - | [7 empty] | 2 | 4
[8 empty] | d) | - | d) | - | [11 empty] | 2 | 4
| 4. Various Government Buildings and Facilities Development Project (Provincewide) |  |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of recipients | - | Admin | a) | 27000000 | [12 empty] | See projects listed below | 2
[8 empty] | b) | Medalla | [13 empty] | AC
[8 empty] | c) | PEO | [13 empty] | AC
[8 empty] | d) | - | [13 empty] | AC
|  |  | Const. of 1 CL Bldg. @ Suawon ES, New Corella |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of recipients | - | Admin | a) | 1000000 | a) | - | e) | - | a) | 1000000 | a) | - | c) | - | a) | - | On-going | 1
|  | 4.1 | [5 empty] | b) | - | b) | Nov. 19, 2019 | f) | - | b) | 1000000 | b) |  | d) | - | b) | - |  | 1
[8 empty] | c) | PEO | c) | - | g) | - | c) | - | [7 empty] | 1
[8 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | Const. of Municipal Tribal Hall, San Isidro |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of recipients | - | Admin | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For implementation | 1
|  | 4.2 | [5 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 1
[8 empty] | c) | PEO | c) | - | g) | - | c) | - | [7 empty] | 1
[8 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | Const. of Quail House (PDNSC Ext. Campus), Sto. Niño, Talaingod |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of recipients | - | Admin | a) | 750000 | a) | - | e) | - | a) | 750000 | a) | - | c) | - | a) | - | On-going | 1
|  | 4.3 | [5 empty] | b) | - | b) | - | f) | - | b) | 750000 | b) | - | d) | - | b) | - |  | 1
[8 empty] | c) | PEO | c) | - | g) | - | c) | - | [7 empty] | 1
[8 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | Completion of Perimeter Steel Fence @ Lunga-og E/S, Brgy. Lunga-og, Sto. Tomas |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of recipients | - | Admin | a) | 1630000 | a) | 2019-01-17 | e) | - | a) | 1630000 | a) | - | c) | 46.28% | a) | - | On-going | 1
|  | 4.4 | [5 empty] | b) | Azotes | b) | - | f) | - | b) | 1630000 | b) | - | d) | - | b) | - |  | 2
[8 empty] | c) | PEO | c) | - | g) | - | c) | - | [7 empty] | 2
[8 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | Const. of DDN Hospital Carmen Zone Annex Bldg. Phase 2, |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of recipients | - | Contract | a) | 3620000 | a) | 2019-06-28 | e) | - | a) | 3620000 | a) | - | c) | - | a) | - | For implementation | 2
|  | 4.5 | [5 empty] | b) | - | b) | - | f) | - | b) | 3620000 | b) | - | d) | - | b) | - |  | 2
[8 empty] | c) | Digos Constrak Corp/ | c) | - | g) | - | c) | - | [7 empty] | 2
[8 empty] | d) | - | d) | - | [11 empty] | 2
| 5. Stimulus Projects for Various Barangays a. 20% Development Fund CY 2019 |  |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | Admin | a) | 41500000 | [12 empty] | See projects listed below | 2
[8 empty] | b) | Medalla | [13 empty] | AC
[8 empty] | c) | PEO | [13 empty] | AC
[8 empty] | d) | - | [13 empty] | AC
| CARMEN |  |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys.
| 5.1 |  | Const. of Multi-Purpose Hall, La Paz, Carmen |  |  | - | - | a) | 500000 | a) | 2019-02-20 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Fund transferred to LGU March 28, 2019 | AC
[8 empty] | b) | - | b) | 2019-08-16 | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 2
[8 empty] | d) | - | d) | - | [11 empty] | 2
| 5.2 |  | Const. of Evacuation Center Ph. 3, Sto. Niño, Carmen |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Amended in the AIP 3rd revision CY 2019/ SB No. 4 CY 2019 changing the location to Purok !-c, Sto. Nino since the previous location was implemented by DPWH | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 2
[8 empty] | d) | - | d) | - | [11 empty] | 2
| 5.3 |  | Const. of Multi-Purpose Hall, Mangalcal, Carmen |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) | 2019-02-20 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Fund transfer to LGU Carmen, 3/28/2019 with check no. 2574953 and OR no. 0118982 | 2
[8 empty] | b) | - | b) | 2019-09-16 | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 2
[8 empty] | d) | - | d) | - | [11 empty] | 2
| 5.4 |  | Rehab. of Multi-Purpose Hall, Guadalupe, Carmen |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) | 2019-02-20 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Fund transferred to LGU March 28, 2019 | 2
[8 empty] | b) | - | b) | 2019-08-15 | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 2
[8 empty] | c) | - | c) | 2019-11-13 | g) | - | c) | - | [7 empty] | 2
[8 empty] | d) | - | d) | - | [11 empty] | 2
| 5.5 |  | Const. of Multi-Purpose Hall, Mabuhay, Carmen |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) | 2019-02-20 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Fund transfer to LGU Carmen, 3/28/2019 with check no. 2574925 and OR no. 0118984 | 2
[8 empty] | b) | - | b) | 2019-08-16 | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 2
[8 empty] | d) | - | d) | - | [11 empty] | 2
| 5.6 |  | Const. Canal Lining , Mabaus, Carmen |  | Const. of Canal Lining to cater the needs of brgys. | - | - | a) | 500000 | a) | 2019-02-20 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Fund transferred to LGU March 28, 2019 | 2
[8 empty] | b) | - | b) |  | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 2
[8 empty] | c) | - | c) |  | g) | - | c) | - | [7 empty] | 2
[8 empty] | d) | - | d) | - | [11 empty] | 2
| 5.7 |  | Rehab. Of Evacuation Center, Alejal, Carmen |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) | 2019-02-20 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Fund transfer to LGU Carmen, 3/28/2019 with check no.2574949 and OR no. 0118991 | 2
[8 empty] | b) | - | b) | 2019-08-16 | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 2
[8 empty] | d) | - | d) | - | [11 empty] | 2
| 5.8 |  | Compl. Of Evacuation Center, Tuganay, Carmen |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) | 2019-02-20 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Fund transfer to LGU Carmen, 3/28/2019 with check no. 2574947 and OR no. 0118995 | 2
[8 empty] | b) | - | b) | 2019-08-16 | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 2
[8 empty] | d) | - | d) | - | [11 empty] | 2
| 5.9 |  | Const. of Multi-Purpose hall, Ising, Carmen |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) | 2019-02-20 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Fund transferred to LGU March 28, 2019 | 2
[8 empty] | b) | - | b) |  | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 2
[8 empty] | d) | - | d) | - | [11 empty] | 2
| 5.1 |  | Rehab. of Multi-Purpose hall, Cebulano, Carmen |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) | 2019-02-20 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Fund transferred to LGU March 28, 2019 | 2
[8 empty] | b) | - | b) | 2019-08-16 | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 2
[8 empty] | d) | - | d) | - | [11 empty] | 2
PANABO CITY
| 5.11 |  | Rehab. Of Multi-Purpose Hall, Kasilak, Panabo City |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Amended in AIP 3rd revison CY 2019/ SB No. 4 CY 2019 increasing the project cost to P650,000.00 | AC
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 2
[8 empty] | d) | - | d) | - | [11 empty] | 2
| 5.12 |  | Rehab. Of Multi-Purpose Hall, New Malitbog, Panabo City |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Amended in AIP 3rd revsion CY 2019 to change the project to Construction of Potable Water System because the original project will be funded by LGU, Panabo City (Brgy. resolution no. 25 series of 2019 dated Aug. 13, 2019 submitted) | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 2
2
[8 empty] | d) | - | d) | -
| 5.13 |  | Desilting of Canal, New Pandan, Panabo City |  | Const. of Drianage Canal to cater the needs of brgys. | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For re inspection to add length for desilting c/o Engr. Canillada Plan prepared can not consume the allocated amount of P500,000.00 for desilting works. | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 2
[8 empty] | d) | - | d) | - | [11 empty] | 2
| 5.14 |  | Const. Of Multi-Purpose Hall, Waterfall, Panabo City |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For allotment. Sept. 27, 2019 | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 2
[8 empty] | d) | - | d) | - | [11 empty] | 2
| 5.15 |  | Concreting of Brgy. Road @ Prk. Guyabano, Cagangohan, Panabo City |  | Road Concreting to cater the needs of brgys. | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Amended in AIP 3rd revision to change the project to Rehab of Evacuation Center because the original project has no deed of donation.(Brgy. resolution no 41 series of 2019 dated Aug. 16, 2019 submitted | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 2
2
[8 empty] | d) | - | d) | -
| 5.16 |  | Rehab. Of Evacuation Center, J.P. Laurel, Panabo City |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) | 2019-10-23 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Sched. Of bidding Dec. 27, 2019 | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 2
[8 empty] | d) | - | d) | - | [11 empty] | 2
| 5.17 |  | Const. Of Multi-Purpose Hall, Buenavista, Panabo City |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) | 2019-10-18 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Sched. Of bidding Dec. 27, 2019 | 2
[8 empty] | b) | - | b) | - | f) |  | b) | 500000 | b) | - | d) | - | b) | - |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 2
[8 empty] | d) | - | d) | - | [11 empty] | 2
| 5.18 |  | Rehab. Of Multi-Purpose Hall, San Francisco, Panabo City |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) | 2019-10-18 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Sched. Of bidding Dec. 27, 2019 | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 2
[8 empty] | c) | - | c) | - | g) |  | c) | - | [7 empty] | 2
[8 empty] | d) | - | d) | - | [11 empty] | 2
| 5.19 |  | Rehab. Of Evacuation Center, Datu Abdul Dadia, Panabo City |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) | 2019-10-18 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Sched. Of bidding Dec. 27, 2019 | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 2
[8 empty] | d) | - | d) | - | [11 empty] | 2
| 5.2 |  | Impv't./Beautification of Brgy. Grounds, Quezon, Panabo City |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Re aligned to other stimulus projects that needs additional funding | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 2
[8 empty] | d) | - | d) | - | [11 empty] | 2
| 5.21 |  | Const. of Women Livelihood Center Bldg. , Gredu, Panabo City |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) | 2019-03-28 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Fund transfer to LGU - 3/28/2019 with check no. 2574926 and OR no. 0166517 - March 28, 2019 | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 2
[8 empty] | d) | - | d) | - | [11 empty] | 2
| 5.23 |  | Const. of Canal Lining at Purok 5, Salvacion, Panabo City |  | Const. of Drainage Canal to cater the needs of brgys. | - | - | a) | 500000 | a) | 2019-10-18 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Procurement on process | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 2
[8 empty] | d) | - | d) | - | [11 empty] | 2
| 5.24 |  | Rehab. Of Health Center, New Visayas, Panabo City |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Re aligned to other stimulus projects that needs additional funding | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 2
[8 empty] | d) | - | d) | - | [11 empty] | 2
| 5.25 |  | Rehab. Of Multi-Purpose Hall, Little Panay, Panabo City |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For allotment Dec. 11, 2019 | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 2
[8 empty] | d) | - | d) | - | [11 empty] | 2
| 5.26 |  | Rehab. Of Brgy. Health Center, Dalisay, Panabo City |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For allotment Dec. 4, 2019 | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 2
[8 empty] | d) | - | d) | - | [11 empty] | 2
| 5.27 |  | Const. of Multi-Purpose Hall, Southern Davao, Panabo City |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For allotment Dec. 3, 2019 | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 2
[8 empty] | c) | - | c) | - | g) |  | c) | - | [7 empty] | 2
[8 empty] | d) | - | d) | - | [11 empty] | 2
STO. TOMAS
| 5.28 |  | Rehab. Of Evacuation Center, Casig-ang, Sto. Tomas |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | POW preparation on-going c/o Engr. Uy | AC
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 2
[8 empty] | d) | - | d) | - | [11 empty] | 2
| 5.29 |  | Const. of Brgy. Tibal-og Health Center, Tibal-og, Sto. Tomas |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | POW preparation completed amounting t oP1,550,000.00. To request for additional funds in order to complete the project to be functional | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 2
[8 empty] | d) | - | d) | - |  | Nov. 30, 2019 | [9 empty] | 2
| 5.3 |  | Compl.of Brgy. Public Market, La Libertad, Sto. Tomas |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) |  | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Fund transfer to LGU - 6/26/219 with check no. 2575131 and OR no. 0557457 Completed/ PCR for submission by LGU | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 2
[8 empty] | d) | - | d) | - | [11 empty] | 2
| 5.31 |  | Rehab. Of Evacuation Center, New Visayas, Sto. Tomas |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) |  | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Fund transfer to LGU - 6/26/219 with check no. 2575132 and OR no. 0557455 For implementation | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 2
[8 empty] | d) | - | d) | - | [11 empty] | 2
| 5.32 |  | Rehab. Of Multi-Purpose Hall, San Vicente, Sto. Tomas |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Fund transferred to LGU July 5, 2019 On -going | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 2
[8 empty] | c) | - | c) | - | g) |  | c) | - | [7 empty] | 2
[8 empty] | d) | - | d) | - |  | - | [9 empty] | 2
| 5.33 |  | Rehab. Of Multi-Purpose Hall, Salvacion, Sto. Tomas |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Amended in AIP 3rd revision CY 2019 /SB No. 4 CY 2019increasing the project cost to P1,000,000.00 | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 2
[8 empty] | d) | - | d) | - | [11 empty] | 2
| 5.34 |  | Rehab. Of Multi-Purpose Hall, Pantaron, Sto. Tomas |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) |  | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Amended in AIP 3rd revision CY 2019 / SB No. 4 CY 2019 increasing the project cost to P550,000.00 | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 2
[8 empty] | d) | - | d) | - | [11 empty] | 2
| 5.35 |  | Rehab. Of Multi-Purpose Hall, Magwawa, Sto. Tomas |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | Contract | a) | 500000 | a) | June 19 2019 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Procurement on process | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 2
[8 empty] | d) | - | d) | - | [11 empty] | 2
| 5.36 |  | Compl. Of Multi-Purpose Hall, San Jose, Sto. Tomas |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) |  | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Amended in AIP 3rd revision CY 2019 / SB No. 4 CY 2019 increasing the project cost to P600,000.00 | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 2
[8 empty] | d) | - | d) | - | [11 empty] | 2
| 5.37 |  | Const. of Evacuation Center, Bobongon, Sto. Tomas |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Re aligned to other stimulus projects that needs additional funding | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 2
[8 empty] | d) | - | d) | - | [11 empty] | 2
| 5.38 |  | Rehab. Of Brgy. Road, Lunga-og, Sto. Tomas |  | Road Rehabilitation to cater the needs of brgys. | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Amended in AIP 3rd revision CY 2019 / SB No. 4 CY 2019 increasing the project cost to P600,000.00 | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 2
[8 empty] | d) | - | d) | - | [11 empty] | 2
| 5.39 |  | Rehab. Of Multi-Purpose Hall, New Katipunan, Sto. Tomas |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | Contract | a) | 500000 | a) | 2019-06-07 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Procurement on process | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 2
[8 empty] | d) | - | d) | - | [11 empty] | 2
| 5.41 |  | Rehab. Of Multi-Purpose Hall, Talomo, Sto. Tomas |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Fund transfer to LGU - 6/26/2019 with check no. 2575130 and OR no. 0557456 For implementation | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 2
[8 empty] | d) | - | d) | - | [11 empty] | 2
| IGCS | [21 empty] | 2 | 4
| 5.42 |  | Rehab. Of Health Center, Aumbay, IGCS |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) | Feb. 28, 2019 | e) | - | a) | 500000 | a) |  | c) | 48.32% | a) | 3 | Completed Financial obligation on process | AC | 4
[8 empty] | b) | Pacquiao | b) | 7/10/2019 | f) | - | b) | 500000 | b) | - | d) |  | b) | 15 |  | 2 | 4
[8 empty] | c) | Admin | c) | 10/7/2019 | g) | - | c) | - | [7 empty] | 2 | 4
[8 empty] | d) | 90 CD | d) | - | [11 empty] | 2 | 4
| 5.43 |  | Concreting of Brgy. Road From Prk. 3 to Prk. 5, Catagman, IGCS |  | Road Concreting to cater the needs of brgys. | - | Contract | a) | 500000 | a) | 2019-01-14 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For implementation | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 2
[8 empty] | d) | - | d) | - | [11 empty] | 2
| 5.44 |  | Rehab. Of Multi-Purpose Hall, San Jose, IGCS |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | Admin | a) | 500000 | a) | 2019-03-25 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | On- going | 2
[8 empty] | b) | Pacquiao | b) | 2019-01-02 | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 2
[8 empty] | d) | - | d) | - | [11 empty] | 2
| 5.45 |  | Elctrification at Sitio Trinidad, Bandera, IGCS |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) | 2019-03-25 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Procurement on process | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 2
[8 empty] | d) | - | d) | - | [11 empty] | 2
| 5.46 |  | Rehab. Of Brgy. Health Center, Mambago-A, IGCS |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) | Feb. 28, 2019 | e) | - | a) | 500000 | a) |  | c) | 75.61% | a) | 3 | Completed Financial obligation on process | 2 | 4
[8 empty] | b) | Ganaba | b) | 07/2019 | f) | - | b) | 500000 | b) |  | d) |  | b) | 15 |  | 2 | 4
[8 empty] | c) | Admin | c) | 8/23/2019 | g) | - | c) | - | [7 empty] | 2 | 4
[8 empty] | d) | 45 CD | d) | - | [11 empty] | 2 | 4
| 5.47 |  | Rehab. Of Multi-Purpose Hall, Del Monte, IGCS |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | Admin | a) | 500000 | a) | 2019-05-29 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Pending/ activity undertaken by DPWH | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 2
[8 empty] | d) | - | d) | - | [11 empty] | 2
| 5.48 |  | Rehab. Of Multi-Purpose Hall, Aundanao, IGCS |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | Admin | a) | 500000 | a) | 2019-03-18 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | On -going | 2
[8 empty] | b) | Porras | b) | 2019-11-18 | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 2
[8 empty] | d) | - | d) | - | [11 empty] | 2
| 5.49 |  | Electrification at Upper Purok Rosal, Tagbaobo, IGCS |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Procurement on process. No Abastract | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 2
[8 empty] | d) | - | d) | - | [11 empty] | 2
| 5.5 |  | Const. Of Multi-Purpose Hall, Mambago-B, IGCS |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For implementation | 2
[8 empty] | b) | Roque | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 2
[8 empty] | d) | - | d) | - | [11 empty] | 2
| 5.51 |  | Const. Of Multi-Purpose Hall, San Antonio, IGCS |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) | 2019-06-19 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For implementation | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 2
[8 empty] | d) | - | d) | - | [11 empty] | 2
| 5.52 |  | Concreting of Brgy. Road from Prk. 1 to Prk. 2, Villarica, ICGS |  | Road Concreting to cater the needs of brgys. | - | Contract | a) | 500000 | a) | 2019-01-14 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For implementation | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 2
[8 empty] | d) | - | d) | - | [11 empty] | 2
| 5.53 |  | Rehab. Of Water System Intake Box and Pipeline, Pangubatan, IGCS |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Plan and Pow completed. Waiting of deed of donation | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 2
[8 empty] | d) | - | d) | - | [11 empty] | 2
| 5.54 |  | Const. Of Multi-Purpose Hall, Cogon (Talicud), IGCS |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Procurement on process. For rebidding Dec. 12, 2019 | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 2
[8 empty] | d) | - | d) | - | [11 empty] | 2
| 5.55 |  | Installation of Pipelines, Libertad, IGCS |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) | 2019-03-25 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For implementation | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 2
[8 empty] | d) | - | d) | - | [11 empty] | 2
| 5.56 |  | Rehab. Of Evacuation Center, Libuak, IGCS |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) | 2019-05-29 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For implementation | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 2
[8 empty] | d) | - | d) | - | [11 empty] | 2
| 5.57 |  | Const. of Water System Project, Pob. Kaputian, IGCS |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | for Allotment | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 2
[8 empty] | d) | - | d) | - | [11 empty] | 2
| 5.58 |  | Rehab. Of Potable Water System, San Isidro, Babak, IGCS |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) | 2019-06-19 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For implementation
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 2
[8 empty] | c) | - | c) | - | g) |  | c) | - | [7 empty] | 2
[8 empty] | d) | - | d) | - | [11 empty] | 2
| 5.59 |  | Rehab. Of Potable Water System, San Miguel, IGCS |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) | 2019-02-28 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For implementation | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 2
[8 empty] | d) | - | d) | - | [11 empty] | 2
| 5.6 |  | Const. of Water System Ph.II, San Remegio, IGCS |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) | 2019-05-29 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For implementation | 2
[8 empty] | b) | Porras | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 2
[8 empty] | c) | Admin | c) | - | g) | - | c) | - | [7 empty] | 2
[8 empty] | d) | - | d) | - | [11 empty] | 2
| 5.61 |  | Electrificatio at Prk. 1,3,4, 6,7 & 8, Licup, IGCS |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) | 2019-02-20 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Procurement of materials on process | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 2
[8 empty] | d) | - | d) | - | [11 empty] | 2
| 6. Rural Electrification Project (Provincewide) |  |  |  | Powerlines/posts installed & rehabilitated | - | - | a) | 5000000 | [12 empty] | See projects listed below | 2
[8 empty] | b) | Kim Pao Lu | [13 empty] | AC
[8 empty] | c) | - | [13 empty] | AC
| C. 5% CALAMITY FUND CY 2019 | [21 empty] | AC
|  | Desiltation/Excavation of rivers and creeks |  |  | creeks and canals deislted | - | - | a) | 3000000 | [12 empty] | See project listed below | FS
| 1 | [6 empty] | b) | Paraguya | [13 empty] | AC
[8 empty] | c) | PEO | [13 empty] | AC
[8 empty] | d) | - | [13 empty] | AC
|  |  | Desiltation of Mactan River Ph. II |  | creeks and canals deislted | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | On-going | 1
|  | 1.1 | [5 empty] | b) | Toquero | b) | 2019-07-29 | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 1
[8 empty] | c) | Admin | c) | 2019-09-27 | g) | - | c) | - | [7 empty] | 1
[8 empty] | d) | 60 C.D | d) | - | [11 empty] | 1
|  | Revitment of Dike and Slope Proection |  |  | Protection dikes/slope protection | - | - | a) | 3000000 | [12 empty] | See projects listed below | AC
| 2 | [6 empty] | b) | - | [13 empty] | AC
[8 empty] | c) | - | [13 empty] | AC
[8 empty] | d) | - | [13 empty] | AC
|  |  | Repair/Rehab. Of Upper Tuganay Dike |  | creeks and canals deislted | - | - | a) | 1000000 | a) | - | e) | - | a) | 1000000 | a) | - | c) | - | a) | - | On-going | 1
|  | 2.1 | [5 empty] | b) | Toquero | b) | 2019-08-19 | f) | - | b) | 1000000 | b) | - | d) |  | b) | - |  | 2
[8 empty] | c) | Admin | c) | 2019-09-29 | g) |  | c) | - | [7 empty] | 2
[8 empty] | d) | 59 C.D | d) | - | [11 empty] | 2
|  | Improvement of roads, drainage and canal |  |  | Protection dikes/slope protection | - | - | a) | 3000000 |  |  |  | - | [8 empty] | See project listed below | 2
| 3 | [6 empty] | b) | Paraguya | [13 empty] | AC
[8 empty] | c) | PEO | [13 empty] | AC
[8 empty] | d) | - | [13 empty] | AC
| a. |  | Rehab./Impv't. of New Casay-Bugtong Talisay Provincial Road (Ph.II) |  | creeks and canRoads/Draiange/canals rehab/improved | - | - | a) | 500000 | a) | 2019-03-12 | e) |  | a) | 500000 | a) | 100% | c) | 100% | a) | 12 | Completed | AC
|  |  | Rehab./Impv't. of Prk. 1 - Prk. 2 Sitio Pawas Provincial Road |  | creeks and canRoads/Draiange/canals rehab/improved | - | - | a) | 1500000 | a) | 2019-07-23 | e) | - | a) | 1500000 | a) | 17.14% | c) | 1.18% | a) | 2 | On-going | 2
|  | 3.1 | [5 empty] | b) | Sanchez | b) | 2019-08-05 | f) |  | b) | 1500000 | b) | - | d) | -15.96% | b) | 10 |  | 2
[8 empty] | c) | Admin | c) | 2019-09-28 | g) | - | c) | - | [7 empty] | 2
[8 empty] | d) | 55 | d) | - | [11 empty] | 2
|  |  | Repair/Rehab of Drainage System & Ground Gravelling at Kimamon NHS |  | creeks and canRoads/Draiange/canals rehab/improved | - | - | a) | 464833 | a) | - | e) | - | a) | 464833 | a) |  | c) |  | a) |  | On-going | 2
|  | 3.2 | [5 empty] | b) | Azotes | b) | - | f) | - | b) | 464833 | b) |  | d) |  | b) |  |  | 2
[8 empty] | c) | Admin | c) | - | g) | - | c) | - | [7 empty] | 2
[8 empty] | d) | - | d) | - | [11 empty] | 2
| D. | SUPPLEMENTAL BUDGET NO. 1 CY 2019 | [20 empty] | AC
|  |  | Repair maintenance of OPD, Pharmacy building, DDNH - CZ Compound |  | Renovation | - | - | a) | 100000 | a) | - | e) | - | a) | 100000 | a) |  | c) |  | a) |  | On-going | AC
|  | 1 | [5 empty] | b) | Estorco | b) | - | f) | - | b) | 100000 | b) |  | d) |  | b) |  |  | 2
[8 empty] | c) | Admin | c) | - | g) | - | c) | - | [7 empty] | 2
[8 empty] | d) | - | d) | - | [11 empty] | 2
| E. | SUPPLEMENTAL BUDGET NO. 3 CY 2019
|  | LOCALLY FUNDED PROGRAM/PROJECTS- 20% DEVELOPMENT FUND | [20 empty] | FS
|  | INFRASTRUCTURE DEVELOPMENT PROGRAM | [20 empty] | AC
|  | 1. 8918/ Various Local Roads & Drainage Development Project Construction in Progress- Infrastructure Assets | [20 empty] | AC
|  | ■ | Rehabilitation of Dujali-Pawas-San Vicente Provincial Road, B.E. Dujali |  | Road | Rehab./Repair | - | a) | 2000000 | a) | - | e) | - | a) | 2000000 | a) | - | c) | - | a) | - | The amount was reduced to P1,102,900.00 | AC
|  | 1.1 | [5 empty] | b) | - | b) | - | f) | - | b) | 2000000 | b) | - | d) | - | b) | - |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 2
[8 empty] | d) | - | d) | - | [11 empty] | 2
|  | ■ | Repair/Rehabil;itation of Concrete R.d. Jct. Suaon-Libuton Kapalong |  | Road | Rehab./Repair | - | a) | 1000000 | a) | - | e) | - | a) | 1000000 | a) | - | c) | - | a) | - | For implementation | 2
|  | 1.2 | [5 empty] | b) | - | b) | - | f) | - | b) | 1000000 | b) | - | d) | - | b) | - |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 1
[8 empty] | d) | - | d) | - | [11 empty] | 1
|  | 2. 8918/ VariousWater System Development Project Construction in Progress- Infrastructure Assets | [20 empty] | 1
|  | ■ | Improvement of Potable Water System at Brgy. Mambago- A, Samal District, IGACOS |  | Water System | Impv'.t/Rehab./Const. | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | (Amended in the AIP 2nd Revision to change the location from Peñaplata to Samal District) PO approved September 2, 2019 | AC
|  | 2.1 | [5 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 2
[8 empty] | d) | - | d) | - | [11 empty] | 2
|  | ■ | Rehabilitation of Potable Water System at Brgy. San Miguel, Samal District, IGACOS |  | Water System | Impv'.t/Rehab./Const. | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - |  | 2
|  | 2.2 | [5 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 2
[8 empty] | d) | - | d) | - | [11 empty] | 2
|  | ■ | Construction of Potable Water System at Brgy.Linusotan, Kaputian District, IGACOS |  | Water System | Impv'.t/Rehab./Const. | - | a) | 1300000 | a) | - | e) | - | a) | 1300000 | a) | - | c) | - | a) | - | (Additional 800,000.00 from Const. of PWS in purok 2, Pag-asa, Kapalong which was funded by OPAPP CY 2018) (amended) For allotment- October 15, 2019 | 2
|  | 2.3 | [5 empty] | b) | - | b) | - | f) | - | b) | 1300000 | b) | - | d) | - | b) | - |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 2
[8 empty] | d) | - | d) | - | [11 empty] | 2
|  | ■ | Rehabilitation of Water System in PEEDO-LPRRC, Brgy. Poblacion, New Corella |  | Water System | Impv'.t/Rehab./Const. | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For allotment- October 15, 2019 | 2
|  | 2.4 | [5 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 2
[8 empty] | c) | - | c) | - | g) |  | c) | - | [7 empty] | 2
[8 empty] | d) | - | d) | - | [11 empty] | 2
|  | DISASTER REHABILITATION & RECOVERY PROGRAM Building Back Better Project | [20 empty] | 2
|  | 1. Repairs & Maintenance- Infrastructure Assets | [20 empty] | AC
|  | ■ | Disiltation of Tagum Creek |  | Desiltation |  | - | a) | 2000000 | a) | - | e) | - | a) | 2000000 | a) | - | c) | - | a) | - | PLAN AND POW on process c/o PEO-PDPM | AC
|  | 1.1 | [5 empty] | b) | - | b) | - | f) | - | b) | 2000000 | b) | - | d) | - | b) | - |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 1
[8 empty] | d) | - | d) | - | [11 empty] | 1
|  | ■ | Disiltation of Mactan River (Ph. II) |  | Desiltation |  | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | PLAN AND POW on process c/o PEO-PDPM | 1
|  | 1.2 | [5 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 2
[8 empty] | d) | - | d) | - | [11 empty] | 2
|  | 2. Property, Plant and Equipmen Construction in Progress- Infrastructure Assets | [20 empty] | 2
|  |  | Rehabilitation of Dujali-Balisong-Magupising Provincial Road |  |  |  | - | a) | 1280000 | a) | - | e) | - | a) | 1280000 | a) | - | c) | - | a) | - |  | 1
|  | 2.1 | [5 empty] | b) | - | b) | - | f) | - | b) | 1280000 | b) | - | d) | - | b) | - |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 1
[8 empty] | d) | - | d) | - | [11 empty] | 1
| F. | SUPPLEMENTAL BUDGET NO. 4 CY 2019 | [20 empty] | 1
|  | INFRASTRUCTURE DEVELOPMENT PROGRAM | [20 empty] | FS
|  | LOCALLY FUNDED PROGRAMS/ PROJECTS GENERAL FUND PROPER | [20 empty] | AC
AC
|  | 1. PEACE AND ORDER PROGRAM/1914 Construction in Progress- Land Improvements | [20 empty] | AC
|  | ■ | Rehabilitation of San Jose- Sitio Mahayahay-Magwawa Provincial Road, Sro. Tomas |  |  |  | - | a) | 1000000 | a) | - | e) | - | a) | 1000000 | a) | - | c) | - | a) | - | POW preparation on-going c/o South District | 1
|  | 1.1 | [5 empty] | b) | - | b) | - | f) | - | b) | 1000000 | b) | - | d) | - | b) | - |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 2
[8 empty] | d) | - | d) | - | [11 empty] | 2
|  | 2. 8918/ Various Government Buildigs & Facilities Development Project Construction in Progress- Land Improvements | [20 empty] | 2
|  | ■ | Construction of Perimeter Fence of Day Care Center I Nanyo, Panabo City |  |  |  | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Sched of bidding Dec. 27, 2019 | AC
|  | 2.1 | [5 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 2
[8 empty] | d) | - | d) | - | [11 empty] | 2
|  | ■ | Construction of Multi-Purpose Building, Balagunan, Sto. Tomas |  |  |  | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For allotment Dec .3, 2019 | 2
|  | 2.2 | [5 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 2
[8 empty] | d) | - | d) | - | [11 empty] | 2
|  | INFRASTRUCTURE DEVELOPMENT PROGRAM | [20 empty] | 1
|  | LOCALLY FUNDED PROGRAMS/ PROJECTS 20% DEVELOPMENT FUND | [20 empty] | AC
AC
|  | 1. 8918/ Various Local Roads and Drainaige Development Project Construction in Progress- Infrastructure Assets | [20 empty] | 1
|  | ■ | Rehabilitation of Local Roads at Dalisay-Manay Road Section, Panabo City |  |  |  | - | a) | 246100 | a) | - | e) | - | a) | 246100 | a) | - | c) | - | a) | - |  | AC
|  | 1.1 | [5 empty] | b) | - | b) | - | f) | - | b) | 246100 | b) | - | d) | - | b) | - |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 2
[8 empty] | d) | - | d) | - | [11 empty] | 2
|  | ■ | Rehabilitation of Local Roads at Sta. Cruz-Jct. Tagpore-Buenavista Raod Section, Panabo City |  |  |  | - | a) | 431000 | a) | - | e) | - | a) | 431000 | a) | - | c) | - | a) | - |  | 2
|  | 1.2 | [5 empty] | b) | - | b) | - | f) | - | b) | 431000 | b) | - | d) | - | b) | - |  | 2
[8 empty] | c) | - | c) | - | g) |  | c) | - | [7 empty] | 2
[8 empty] | d) | - | d) | - | [11 empty] | 2
|  | ■ | Rehabilitation of Local Roads at Taba-Bucana Road Section, Taba, Carmen |  |  |  | - | a) | 220000 | a) | - | e) | - | a) | 220000 | a) | - | c) | - | a) | - |  | 2
|  | 1.3 | [5 empty] | b) | - | b) | - | f) | - | b) | 220000 | b) | - | d) | - | b) | - |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 2
[8 empty] | d) | - | d) | - | [11 empty] | 2
|  | 2. 8918/ Stimulus Projects for Various Barangays Construction in Progress- Infrastructure Assets | [20 empty] | 2
|  | ■ | Concreting of Brgy. Road Canal, Dujali, B.E. Dujali |  |  |  | contract | a) | 650000 | a) | - | e) | - | a) | 650000 | a) | - | c) | - | a) | - | Alloted Oct. 18, 2019 Procurement on process | 2
|  | 2.1 | [5 empty] | b) | - | b) | - | f) | - | b) | 650000 | b) | - | d) | - | b) | - |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 2
[8 empty] | d) | - | d) | - | [11 empty] | 2
|  | ■ | Desilting and Conretign of Drainage-Main Collector Canal, New Casay, B.E. Dujali |  |  |  | contract | a) | 650000 | a) | - | e) | - | a) | 650000 | a) | - | c) | - | a) | - | For allotment - Sept. 27, 2019 | 2
|  | 2.2 | [5 empty] | b) | - | b) | - | f) | - | b) | 650000 | b) | - | d) | - | b) | - |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 2
[8 empty] | d) | - | d) | - | [11 empty] | 2
|  | ■ | Concreting of Drainage, Tanglaw, B.E., Dujali |  |  |  | contract | a) | 1200000 | a) | - | e) | - | a) | 1200000 | a) | - | c) | - | a) | - | For allotment Sept. 19, 2019 | 2
|  | 2.3 | [5 empty] | b) | - | b) | - | f) | - | b) | 1200000 | b) | - | d) | - | b) | - |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 2
[8 empty] | d) | - | d) | - | [11 empty] | 2
|  | ■ | Construction of Potable Water System, New Malitbog, Panabo City |  |  |  | contract | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For re-inspection and plan revision in order to reflect in the plan the complete details for the project to be functional.P500,000.00 covers only drilling activity | 2
|  | 2.4 | [5 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 2
[8 empty] | d) | - | d) | - | [11 empty] | 2
|  | ■ | Construction of Water System Project, Poblacion Kaputian, Samal |  |  |  | contract | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Alloted Oct 17, 2019. Procurement on process | 2
|  | 2.5 | [5 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 2
[8 empty] | d) | - | d) | - | [11 empty] | 2
|  | ■ | Construction of Canal Linign at Prk. 5, Salvacion, Panabo City |  |  |  | contract | a) | 600000 | a) | - | e) | - | a) | 600000 | a) | - | c) | - | a) | - | Alloted Oct. 18, 2019 Procurement on process | 2
|  | 2.6 | [5 empty] | b) | - | b) | - | f) | - | b) | 600000 | b) | - | d) | - | b) | - |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 2
[8 empty] | d) | - | d) | - | [11 empty] | 2
|  | ■ | Rehabilitation of Brgy. Road at Lunga-og. Sto. Tomas |  |  |  | contract | a) | 600000 | a) | - | e) | - | a) | 600000 | a) | - | c) | - | a) | - | For allotment Sept. 19, 2019 | 2
|  | 2.7 | [5 empty] | b) | - | b) | - | f) | - | b) | 600000 | b) | - | d) | - | b) | - |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 2
[8 empty] | d) | - | d) | - | [11 empty] | 2
|  | 3. 8918/ Stimulus Projects for Various Barangays Construction in Progress- Bldgs. & Other Structures | [20 empty] | 1
|  | ■ | Construction of Evacuation Center at Purok 1-C Brgy. Sto. Niño, Carmen |  |  |  | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For allotment Dec. 3, 2019 | 1
|  | 3.1 | [5 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 2
[8 empty] | c) | - | c) | - | g) |  | c) | - | [7 empty] | 2
[8 empty] | d) | - | d) | - | [11 empty] | 2
|  | ■ | Construction of Multi-Purpose Hall, Waterfall, Panabo City |  |  |  | - | a) | 1050000 | a) | - | e) | - | a) | 1050000 | a) | - | c) | - | a) | - | For allotment | 1
|  | 3.2 | [5 empty] | b) | - | b) | - | f) | - | b) | 1050000 | b) | - | d) | - | b) | - |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 2
[8 empty] | d) | - | d) | - | [11 empty] | 2
|  | ■ | Rehabilitation of Multi-Purpose Hall, San Francisco, Panabo City |  |  |  | - | a) | 600000 | a) | - | e) | - | a) | 600000 | a) | - | c) | - | a) | - | Alloted Oct. 18, 2019 Procurement on process | 2
|  | 3.3 | [5 empty] | b) | - | b) | - | f) | - | b) | 600000 | b) | - | d) | - | b) | - |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 2
[8 empty] | d) | - | d) | - | [11 empty] | 2
|  | ■ | Rehabilitation of Evacuation Center at Datu Abdul Dadia, Panabo City |  |  |  | - | a) | 650000 | a) | - | e) | - | a) | 650000 | a) | - | c) | - | a) | - | Sched of bidding -Dec 27, 2019 | 2
|  | 3.4 | [5 empty] | b) | - | b) | - | f) | - | b) | 650000 | b) | - | d) | - | b) | - |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 2
[8 empty] | d) | - | d) | - | [11 empty] | 2
|  | ■ | Construction of Multi-Purpose Hall, Buenavista, Panabo City |  |  |  | - | a) | 1050000 | a) | - | e) | - | a) | 1050000 | a) | - | c) | - | a) | - | Sched of bidding -Dec 27, 2019 | 2
|  | 3.5 | [5 empty] | b) | - | b) | - | f) | - | b) | 1050000 | b) | - | d) | - | b) | - |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 2
[8 empty] | d) | - | d) | - | [11 empty] | 2
|  | ■ | Rehabilitation of Multi-Purpose Hall, Llittle Panay, Panabo City |  |  |  | - | a) | 550000 | a) | - | e) | - | a) | 550000 | a) | - | c) | - | a) | - | For allotment Dec. 11, 2019 | 2
|  | 3.6 | [5 empty] | b) | - | b) | - | f) | - | b) | 550000 | b) | - | d) | - | b) | - |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 2
[8 empty] | d) | - | d) | - | [11 empty] | 2
|  | ■ | Rehabilitation of Multi-Purpose Hall, Pantaron, Sto. Tomas |  |  |  | - | a) | 550000 | a) | - | e) | - | a) | 550000 | a) | - | c) | - | a) | - | Alloted Oct. 18, 2019 Procurement on process | 2
|  | 3.7 | [5 empty] | b) | - | b) | - | f) | - | b) | 550000 | b) | - | d) | - | b) | - |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 2
[8 empty] | d) | - | d) | - | [11 empty] | 2
|  | ■ | Rehabilitation of Multi-Purpose Hall, Salvacion, Sto. Tomas |  |  |  | - | a) | 1000000 | a) | - | e) | - | a) | 1000000 | a) | - | c) | - | a) | - | POW preparation on-going c/o PDPM | 2
|  | 3.8 | [5 empty] | b) | - | b) | - | f) | - | b) | 1000000 | b) | - | d) | - | b) | - |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 2
[8 empty] | d) | - | d) | - | [11 empty] | 2
|  | ■ | Completion of Multi-Purpose Hall, San Jose, Sto. Tomas |  |  |  | - | a) | 600000 | a) | - | e) | - | a) | 600000 | a) | - | c) | - | a) | - | Alloted Nov. 15, 2019 Procurement on process | 2
|  | 3.9 | [5 empty] | b) | - | b) | - | f) | - | b) | 600000 | b) | - | d) | - | b) | - |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 2
[8 empty] | d) | - | d) | - | [11 empty] | 2
|  | ■ | Rehabilitation of Multi-Purpose Hall, Kasilak, Panabo City |  |  |  | - | a) | 650000 | a) | - | e) | - | a) | 650000 | a) | - | c) | - | a) | - | Alloted Nov. 15, 2019 Procurement on process | 2
|  | 4 | [5 empty] | b) | - | b) | - | f) | - | b) | 650000 | b) | - | d) | - | b) | - |  | 2
[8 empty] | c) | - | c) | - | g) |  | c) | - | [7 empty] | 2
[8 empty] | d) | - | d) | - | [11 empty] | 2
|  | ■ | Rehabilitation of Brgy. Health Center, Dalisay, Panabo City |  |  |  | - | a) | 550000 | a) | - | e) | - | a) | 550000 | a) | - | c) | - | a) | - | For allotment Dec. 4, 2019 | 2
|  | 4.1 | [5 empty] | b) | - | b) | - | f) | - | b) | 550000 | b) | - | d) | - | b) | - |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 2
[8 empty] | d) | - | d) | - | [11 empty] | 2
|  | ■ | Rehabilitation of Evacuation Center, Kiotoy, Panabo City |  |  |  | - | a) | 650000 | a) | - | e) | - | a) | 650000 | a) | - | c) | - | a) | - | Sched of bidding Dec 27, 2019
|  | 4.2 | [5 empty] | b) | - | b) | - | f) | - | b) | 650000 | b) | - | d) | - | b) | - |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 2
[8 empty] | d) | - | d) | - | [11 empty] | 2
|  | ■ | Rehabilitation of Evacuation Center, Cagangohan, Panabo City |  |  |  | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | POW for approval Nov. 5, 2019 | 2
|  | 4.3 | [5 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 2
[8 empty] | d) | - | d) | - | [11 empty] | 2
|  | ■ | Rehabilitation of Multi-Purpose Bldg. (Brgy. Hall) Tagpopongan, IGACOS |  |  |  | - | a) | 174460.33 | a) | - | e) | - | a) | 174460.33 | a) | - | c) | - | a) | - | For allotment Nov. 5, 2019 | 2
|  | 4.4 | [5 empty] | b) | - | b) | - | f) | - | b) | 174460.33 | b) | - | d) | - | b) | - |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 2
[8 empty] | d) | - | d) | - | [11 empty] | 2
| G. | TRUST FUND | [20 empty] | 1
1. CMGP 2019
|  | ■ | Road Upgrading of Sto Nino - Kabankalan - La Paz Provincial Road, Carmen |  |  |  | - | a) | 44461624.67 | a) |  | e) | - | a) | - | a) | 4.3% | c) | 34.23% | a) | 30 | On-going
|  | 1.1 | [5 empty] | b) | Comidoy | b) | 10/7/2019 | f) | - | b) | - | b) | - | d) | 29.93% | b) | 610 |  | 2
[8 empty] | c) | GP & H CONST. | c) | 5/15/2020 | g) | - | c) | - | [7 empty] | 2
[8 empty] | d) | 222 C.D | d) | [12 empty] | 2
|  | ■ | Road Upgrading of Jct Highway - Sto Nino - La Paz - San Vicenter Provincial Road, Carmen |  |  |  | - | a) | 80481331.34 | a) |  | e) | - | a) | - | a) | 22.77% | c) | 33.12% | a) | - | On-going | 2
|  | 1.2 | [5 empty] | b) | Fernandez | b) | 10/7/2019 | f) | - | b) | - | b) | - | d) | 10.35% | b) | -
[8 empty] | c) | Tagum Builders | c) | 6/22/2020 | g) | - | c) | -
[8 empty] | d) | 259 C.D | d)
| II. | PROJECTS UNDER THE CURRENT APPROPRIATION | [20 empty] | AC |  | 893809.45
| A. | GENERAL FUND CY 2020 | [20 empty] | FS
INFRASTRUCTURE DEVELOPMENT PROGRAMS
| Road ID |  | 1. Repair/Maintenance of Provincial Roads & Bridges |  | Road Maintenance | KM | MBA | a) | 11801752 | a) | 2020-01-02 | [10 empty] | See list of Provincial Roads | FS
[6 empty] | 283.38 |  | b) | Paraguya | b) | 2020-01-02 | [11 empty] | AC
| 11DAN | [6 empty] | c) | PEO | c) | 2020-12-31 | [11 empty] | AC
[8 empty] | d) | 261 days | d) | - | [11 empty] | AC
|  |  | CEBULANO - MANGALCAL |  | Road Maintenance | 7.1 | Admin | a) | 134672.7 | a) | 2020-01-02 | e) | - | a) | 134672.7 | a) | - | c) | - | a) | - | On-going | AC
| 073 | [6 empty] | b) |  | b) |  | f) | - | b) | 134672.7 | b) | - | d) | - | b) | - |  | 1
[8 empty] | c) | PEO | c) | - | g) | - | c) | - | [7 empty] | 1
[8 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | CEBULANO - MANGALCAL |  | CBRMC | 7.1 | Contract | a) | 131004.66 | a) | - | e) | - | a) | 131004.66 | a) | - | c) | - | a) | - |  | AC
| 073 | [6 empty] | b) | - | b) | - | f) | - | b) | 131004.66 | b) | - | d) | - | b) | - |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 1
[8 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | TUBOD - BASA - MANGALCAL |  | Road Maintenance | 8.33 | Admin | a) | 143530.25 | a) | 2020-01-02 | e) | - | a) | 143530.25 | a) | - | c) | - | a) | - | On-going | AC
| 074 | [6 empty] | b) |  | b) |  | f) | - | b) | 143530.25 | b) | - | d) | - | b) | - |  | 1
[8 empty] | c) | PEO | c) | - | g) | - | c) | - | [7 empty] | 1
[8 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | TUBOD - BASA - MANGALCAL |  | CBRMC | 8.33 | Contract | a) | 106856.33 | a) | - | e) | - | a) | 106856.33 | a) | - | c) | - | a) | - |  | AC
| 074 | [6 empty] | b) |  | b) | - | f) | - | b) | 106856.33 | b) | - | d) | - | b) | - |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 1
[8 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | UPPER MANGALCAL - LOWER MANGALCAL |  | Road Maintenance | 2.68 | Admin | a) | 82374.21 | a) | 2020-01-02 | e) | - | a) | 82374.21 | a) | - | c) | - | a) | - | On-going | AC
| 078 | [6 empty] | b) |  | b) |  | f) | - | b) | 82374.21 | b) | - | d) | - | b) | - |  | 1
[8 empty] | c) | PEO | c) | - | g) | - | c) | - | [7 empty] | 1
[8 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | UPPER MANGALCAL - LOWER MANGALCAL |  | CBRMC | 2.68 | Contract | a) | 72444.97 | a) | - | e) | - | a) | 72444.97 | a) | - | c) | - | a) | - |  | AC
| 078 | [6 empty] | b) | - | b) | - | f) | - | b) | 72444.97 | b) | - | d) | - | b) | - |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 1
[8 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | CEBULANO - LOCETA |  | Road Maintenance | 9.93 | Admin | a) | 72051.43 | a) | 2020-01-02 | e) | - | a) | 72051.43 | a) | - | c) | - | a) | - | On-going | AC
| 079 | [6 empty] | b) |  | b) |  | f) | - | b) | 72051.43 | b) | - | d) | - | b) | - |  | 1
[8 empty] | c) | PEO | c) | - | g) | - | c) | - | [7 empty] | 1
[8 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | CEBULANO - LOCETA |  | CBRMC | 9.93 | Contract | a) | 47089.26 | a) | - | e) | - | a) | 47089.26 | a) | - | c) | - | a) | - |  | AC
| 079 | [6 empty] | b) | - | b) | - | f) | - | b) | 47089.26 | b) | - | d) | - | b) | - |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 1
[8 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | JCT. HIGHWAY CARMEN - MANGALCAL - TUBOD |  | Road Maintenance | 4.85 | Admin | a) | 462895.06 | a) | 2020-01-02 | e) | - | a) | 462895.06 | a) | - | c) | - | a) | - | On-going | AC
| 082 | [6 empty] | b) |  | b) |  | f) | - | b) | 462895.06 | b) | - | d) | - | b) | - |  | 1
[8 empty] | c) | PEO | c) | - | g) | - | c) | - | [7 empty] | 1
[8 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | JCT. HIGHWAY CARMEN - MANGALCAL - TUBOD |  | CBRMC | 4.85 | Contract | a) | 259594.46 | a) | - | e) | - | a) | 259594.46 | a) | - | c) | - | a) | - |  | AC
| 082 | [6 empty] | b) | - | b) | - | f) | - | b) | 259594.46 | b) | - | d) | - | b) | - |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 1
[8 empty] | d) | - | d) | - | [11 empty] | 1
` |  |  | ISING - SADPODON - TABA - DILADILA |  | Road Maintenance | 11.6 | Admin | a) | 226651.27 | a) | 2020-01-02 | e) | - | a) | 226651.27 | a) | - | c) | - | a) | - | On-going | AC
| 086 | [6 empty] | b) |  | b) |  | f) | - | b) | 226651.27 | b) | - | d) | - | b) | - |  | 1
[8 empty] | c) | PEO | c) | - | g) | - | c) | - | [7 empty] | 1
[8 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | ISING - SADPODON - TABA - DILADILA |  | CBRMC | 11.6 | Contract | a) | 135230.61 | a) | - | e) | - | a) | 135230.61 | a) | - | c) | - | a) | - |  | AC
| 086 | [6 empty] | b) | - | b) | - | f) | - | b) | 135230.61 | b) | - | d) | - | b) | - |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 1
[8 empty] | d) | - | d) | - | [11 empty] | 1
` |  |  | TUGANAY - TABA |  | Road Maintenance | 2.99 | Admin | a) | 169418.15 | a) | 2020-01-02 | e) | - | a) | 169418.15 | a) | - | c) | - | a) | - | On-going | AC
| 087 | [6 empty] | b) |  | b) |  | f) | - | b) | 169418.15 | b) | - | d) | - | b) | - |  | 1
[8 empty] | c) | PEO | c) | - | g) | - | c) | - | [7 empty] | 1
[8 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | TUGANAY - TABA |  | CBRMC | 2.99 | Contract | a) | 102630.37 | a) | - | e) | - | a) | 102630.37 | a) | - | c) | - | a) | - |  | AC
| 087 | [6 empty] | b) | - | b) | - | f) | - | b) | 102630.37 | b) | - | d) | - | b) | - |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 1
[8 empty] | d) | - | d) | - | [11 empty] | 1
` |  |  | JCT. HIGHWAY TUGANAY - TABA |  | Road Maintenance | 7.52 | Admin | a) | 222375.04 | a) | 2020-01-02 | e) | - | a) | 222375.04 | a) | - | c) | - | a) | - | On-going | AC
| 088 | [6 empty] | b) |  | b) |  | f) | - | b) | 222375.04 | b) | - | d) | - | b) | - |  | 1
[8 empty] | c) | PEO | c) | - | g) | - | c) | - | [7 empty] | 1
[8 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | JCT. HIGHWAY TUGANAY - TABA |  | CBRMC | 7.52 | Contract | a) | 57955.99 | a) | - | e) | - | a) | 57955.99 | a) | - | c) | - | a) | - |  | AC
| 088 | [6 empty] | b) | - | b) | - | f) | - | b) | 57955.99 | b) | - | d) | - | b) | - |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 1
[8 empty] | d) | - | d) | - | [11 empty] | 1
` |  |  | JCT HIGHWAY - ISING - MAGSAYSAY |  | Road Maintenance | 8.7 | Admin | a) | 478128.48 | a) | 2020-01-02 | e) | - | a) | 478128.48 | a) | - | c) | - | a) | - | On-going | AC
| 089 | [6 empty] | b) |  | b) |  | f) | - | b) | 478128.48 | b) | - | d) | - | b) | - |  | 1
[8 empty] | c) | PEO | c) | - | g) | - | c) | - | [7 empty] | 1
[8 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | JCT HIGHWAY - ISING - MAGSAYSAY |  | CBRMC | 8.7 | Contract | a) | 212505.24 | a) | - | e) | - | a) | 212505.24 | a) | - | c) | - | a) | - |  | AC
| 089 | [6 empty] | b) | - | b) | - | f) | - | b) | 212505.24 | b) | - | d) | - | b) | - |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 1
[8 empty] | d) | - | d) | - | [11 empty] | 1
` |  |  | MALIGAYA - NEW CAMILING |  | Road Maintenance | 4.11 | Admin | a) | 51790.26 | a) | 2020-01-02 | e) | - | a) | 51790.26 | a) | - | c) | - | a) | - | On-going | AC
| 090 | [6 empty] | b) |  | b) |  | f) | - | b) | 51790.26 | b) | - | d) | - | b) | - |  | 1
[8 empty] | c) | PEO | c) | - | g) | - | c) | - | [7 empty] | 1
[8 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | MALIGAYA - NEW CAMILING |  | CBRMC | 4.11 | Contract | a) | 83915.44 | a) | - | e) | - | a) | 83915.44 | a) | - | c) | - | a) | - |  | AC
| 090 | [6 empty] | b) | - | b) | - | f) | - | b) | 83915.44 | b) | - | d) | - | b) | - |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 1
[8 empty] | d) | - | d) | - | [11 empty] | 1
` |  |  | NEW CAMILING - ALEJAL - LOWER MAGSAYSAY |  | Road Maintenance | 2.73 | Admin | a) | 277852.05 | a) | 2020-01-02 | e) | - | a) | 277852.05 | a) | - | c) | - | a) | - | On-going | AC
| 091 | [6 empty] | b) |  | b) |  | f) | - | b) | 277852.05 | b) | - | d) | - | b) | - |  | 1
[8 empty] | c) | PEO | c) | - | g) | - | c) | - | [7 empty] | 1
[8 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | NEW CAMILING - ALEJAL - LOWER MAGSAYSAY |  | CBRMC | 2.73 | Contract | a) | 150927.01 | a) | - | e) | - | a) | 150927.01 | a) | - | c) | - | a) | - |  | AC
| 091 | [6 empty] | b) | - | b) | - | f) | - | b) | 150927.01 | b) | - | d) | - | b) | - |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 1
[8 empty] | d) | - | d) | - | [11 empty] | 1
` |  |  | JCT. HIGHWAY - TUGANAY - ANIBONGAN |  | Road Maintenance | 3.34 | Admin | a) | 139609.7 | a) | 2020-01-02 | e) | - | a) | 139609.7 | a) | - | c) | - | a) | - | On-going | AC
| 094 | [6 empty] | b) |  | b) |  | f) | - | b) | 139609.7 | b) | - | d) | - | b) | - |  | 1
[8 empty] | c) | PEO | c) | - | g) | - | c) | - | [7 empty] | 1
[8 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | JCT. HIGHWAY - TUGANAY - ANIBONGAN |  | CBRMC | 3.34 | Contract | a) | 93574.75 | a) | - | e) | - | a) | 93574.75 | a) | - | c) | - | a) | - |  | AC
| 094 | [6 empty] | b) | - | b) | - | f) | - | b) | 93574.75 | b) | - | d) | - | b) | - |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 1
[8 empty] | d) | - | d) | - | [11 empty] | 1
` |  |  | ANIBONGAN - GUADALUPE |  | Road Maintenance | 2.19 | Admin | a) | 85559.79 | a) | 2020-01-02 | e) | - | a) | 85559.79 | a) | - | c) | - | a) | - | On-going | AC
| 095 | [6 empty] | b) |  | b) |  | f) | - | b) | 85559.79 | b) | - | d) | - | b) | - |  | 1
[8 empty] | c) | PEO | c) | - | g) | - | c) | - | [7 empty] | 1
[8 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | ANIBONGAN - GUADALUPE |  | CBRMC | 2.19 | Contract | a) | 72444.97 | a) | - | e) | - | a) | 72444.97 | a) | - | c) | - | a) | - |  | AC
| 095 | [6 empty] | b) | - | b) | - | f) | - | b) | 72444.97 | b) | - | d) | - | b) | - |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 1
[8 empty] | d) | - | d) | - | [11 empty] | 1
` |  |  | TUGANAY - ANIBONGAN - SAN ISIDRO |  | Road Maintenance | 4.98 | Admin | a) | 344085.79 | a) | 2020-01-02 | e) | - | a) | 344085.79 | a) | - | c) | - | a) | - | On-going | AC
| 096 | [6 empty] | b) |  | b) |  | f) | - | b) | 344085.79 | b) | - | d) | - | b) | - |  | 1
[8 empty] | c) | PEO | c) | - | g) | - | c) | - | [7 empty] | 1
[8 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | TUGANAY - ANIBONGAN - SAN ISIDRO |  | CBRMC | 4.98 | Contract | a) | 115911.95 | a) | - | e) | - | a) | 115911.95 | a) | - | c) | - | a) | - |  | AC
| 096 | [6 empty] | b) | - | b) | - | f) | - | b) | 115911.95 | b) | - | d) | - | b) | - |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 1
[8 empty] | d) | - | d) | - | [11 empty] | 1
` |  |  | JCT. ANIBONGAN - PRK. 2, 7, 5 SAN ISIDRO |  | Road Maintenance | 9.17 | Admin | a) | 89575.84 | a) | 2020-01-02 | e) | - | a) | 89575.84 | a) | - | c) | - | a) | - | On-going | AC
| 097 | [6 empty] | b) |  | b) |  | f) | - | b) | 89575.84 | b) | - | d) | - | b) | - |  | 1
[8 empty] | c) | PEO | c) | - | g) | - | c) | - | [7 empty] | 1
[8 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | JCT. ANIBONGAN - PRK. 2, 7, 5 SAN ISIDRO |  | CBRMC | 9.17 | Contract | a) | 110478.58 | a) | - | e) | - | a) | 110478.58 | a) | - | c) | - | a) | - |  | AC
| 097 | [6 empty] | b) | - | b) | - | f) | - | b) | 110478.58 | b) | - | d) | - | b) | - |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 1
[8 empty] | d) | - | d) | - | [11 empty] | 1
` |  |  | ANIBONGAN - SALVACION - CABAY-ANGAN |  | Road Maintenance | 5.89 | Admin | a) | 279123.9 | a) | 2020-01-02 | e) | - | a) | 279123.9 | a) | - | c) | - | a) | - | On-going | AC
| 098 | [6 empty] | b) |  | b) |  | f) | - | b) | 279123.9 | b) | - | d) | - | b) | - |  | 1
[8 empty] | c) | PEO | c) | - | g) | - | c) | - | [7 empty] | 1
[8 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | ANIBONGAN - SALVACION - CABAY-ANGAN |  | CBRMC | 5.89 | Contract | a) | 162397.48 | a) | - | e) | - | a) | 162397.48 | a) | - | c) | - | a) | - |  | AC
| 098 | [6 empty] | b) | - | b) | - | f) | - | b) | 162397.48 | b) | - | d) | - | b) | - |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 1
[8 empty] | d) | - | d) | - | [11 empty] | 1
` |  |  | MABAUS - CABAY-ANGAN |  | Road Maintenance | 5.57 | Admin | a) | 113320.9 | a) | 2020-01-02 | e) | - | a) | 113320.9 | a) | - | c) | - | a) | - | On-going | AC
| 099 | [6 empty] | b) |  | b) |  | f) | - | b) | 113320.9 | b) | - | d) | - | b) | - |  | 1
[8 empty] | c) | PEO | c) | - | g) | - | c) | - | [7 empty] | 1
[8 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | MABAUS - CABAY-ANGAN |  | CBRMC | 5.57 | Contract | a) | 90556.21 | a) | - | e) | - | a) | 90556.21 | a) | - | c) | - | a) | - |  | AC
| 099 | [6 empty] | b) | - | b) | - | f) | - | b) | 90556.21 | b) | - | d) | - | b) | - |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 1
[8 empty] | d) | - | d) | - | [11 empty] | 1
` |  |  | JCT. HIGHWAY GUADALUPE - BDRY. TAGUM |  | Road Maintenance | 6.93 | Admin | a) | 517780.87 | a) | 2020-01-02 | e) | - | a) | 517780.87 | a) | - | c) | - | a) | - | On-going | AC
| 101 | [6 empty] | b) |  | b) |  | f) | - | b) | 517780.87 | b) | - | d) | - | b) | - |  | 1
[8 empty] | c) | PEO | c) | - | g) | - | c) | - | [7 empty] | 1
[8 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | JCT. HIGHWAY GUADALUPE - BDRY. TAGUM |  | CBRMC | 6.93 | Contract | a) | 231823.89 | a) | - | e) | - | a) | 231823.89 | a) | - | c) | - | a) | - |  | AC
| 101 | [6 empty] | b) | - | b) | - | f) | - | b) | 231823.89 | b) | - | d) | - | b) | - |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 1
[8 empty] | d) | - | d) | - | [11 empty] | 1
` |  |  | DUJALI - TANGLAW |  | Road Maintenance | 7.26 | Admin | a) | 135183.27 | a) | 2020-01-02 | e) | - | a) | 135183.27 | a) | - | c) | - | a) | - | On-going | AC
| 104 | [6 empty] | b) |  | b) |  | f) | - | b) | 135183.27 | b) | - | d) | - | b) | - |  | 1
[8 empty] | c) | PEO | c) | - | g) | - | c) | - | [7 empty] | 1
[8 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | DUJALI - TANGLAW |  | CBRMC | 7.26 | Contract | a) | 94178.48 | a) | - | e) | - | a) | 94178.48 | a) | - | c) | - | a) | - |  | AC
| 104 | [6 empty] | b) | - | b) | - | f) | - | b) | 94178.48 | b) | - | d) | - | b) | - |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 1
[8 empty] | d) | - | d) | - | [11 empty] | 1
` |  |  | POBLACION DUJALI - PRK. 8 DUJALI |  | Road Maintenance | 4.58 | Admin | a) | 329064 | a) | 2020-01-02 | e) | - | a) | 329064 | a) | - | c) | - | a) | - | On-going | AC
| 105 | [6 empty] | b) |  | b) |  | f) | - | b) | 329064 | b) | - | d) | - | b) | - |  | 1
[8 empty] | c) | PEO | c) | - | g) | - | c) | - | [7 empty] | 1
[8 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | POBLACION DUJALI - PRK. 8 DUJALI |  | CBRMC | 4.58 | Contract | a) | 193371.11 | a) | - | e) | - | a) | 193371.11 | a) | - | c) | - | a) | - |  | AC
| 105 | [6 empty] | b) | - | b) | - | f) | - | b) | 193371.11 | b) | - | d) | - | b) | - |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 1
[8 empty] | d) | - | d) | - | [11 empty] | 1
` |  |  | DUJALI - SAN ISIDRO |  | Road Maintenance | 14.48 | Admin | a) | 112652.73 | a) | 2020-01-02 | e) | - | a) | 112652.73 | a) | - | c) | - | a) | - | On-going | AC
| 107 | [6 empty] | b) |  | b) |  | f) | - | b) | 112652.73 | b) | - | d) | - | b) | - |  | 1
[8 empty] | c) | PEO | c) | - | g) | - | c) | - | [7 empty] | 1
[8 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | DUJALI - SAN ISIDRO |  | CBRMC | 14.48 | Contract | a) | 78482.06 | a) | - | e) | - | a) | 78482.06 | a) | - | c) | - | a) | - |  | AC
| 107 | [6 empty] | b) | - | b) | - | f) | - | b) | 78482.06 | b) | - | d) | - | b) | - |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 1
[8 empty] | d) | - | d) | - | [11 empty] | 1
` |  |  | NEW CASAY - BUGTONG TALISAY |  | Road Maintenance | 9.66 | Admin | a) | 74294.5 | a) | 2020-01-02 | e) | - | a) | 74294.5 | a) | - | c) | - | a) | - | On-going | AC
| 108 | [6 empty] | b) |  | b) |  | f) | - | b) | 74294.5 | b) | - | d) | - | b) | - |  | 1
[8 empty] | c) | PEO | c) | - | g) | - | c) | - | [7 empty] | 1
[8 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | NEW CASAY - BUGTONG TALISAY |  | CBRMC | 9.66 | Contract | a) | 64596.78 | a) | - | e) | - | a) | 64596.78 | a) | - | c) | - | a) | - |  | AC
| 108 | [6 empty] | b) | - | b) | - | f) | - | b) | 64596.78 | b) | - | d) | - | b) | - |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 1
[8 empty] | d) | - | d) | - | [11 empty] | 1
` |  |  | DUJALI - BALISONG - MAGUPISING |  | Road Maintenance | 0.46 | Admin | a) | 235776.07 | a) | 2020-01-02 | e) | - | a) | 235776.07 | a) | - | c) | - | a) | - | On-going | AC
| 113 | [6 empty] | b) |  | b) |  | f) | - | b) | 235776.07 | b) | - | d) | - | b) | - |  | 1
[8 empty] | c) | PEO | c) | - | g) | - | c) | - | [7 empty] | 1
[8 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | DUJALI - BALISONG - MAGUPISING |  | CBRMC | 0.46 | Contract | a) | 115911.95 | a) | - | e) | - | a) | 115911.95 | a) | - | c) | - | a) | - |  | AC
| 113 | [6 empty] | b) | - | b) | - | f) | - | b) | 115911.95 | b) | - | d) | - | b) | - |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 1
[8 empty] | d) | - | d) | - | [11 empty] | 1
` |  |  | DUJALI - PAWAS - SAN VICENTE |  | Road Maintenance | 4.92 | Admin | a) | 141544.99 | a) | 2020-01-02 | e) | - | a) | 141544.99 | a) | - | c) | - | a) | - | On-going | AC
| 117 | [6 empty] | b) |  | b) |  | f) | - | b) | 141544.99 | b) | - | d) | - | b) | - |  | 1
[8 empty] | c) | PEO | c) | - | g) | - | c) | - | [7 empty] | 1
[8 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | DUJALI - PAWAS - SAN VICENTE |  | CBRMC | 4.92 | Contract | a) | 140060.27 | a) | - | e) | - | a) | 140060.27 | a) | - | c) | - | a) | - |  | AC
| 117 | [6 empty] | b) | - | b) | - | f) | - | b) | 140060.27 | b) | - | d) | - | b) | - |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 1
[8 empty] | d) | - | d) | - | [11 empty] | 1
` |  |  | JCT. SALVACION - SAN VICENTE - CABAY-ANGAN |  | Road Maintenance | 3.19 | Admin | a) | 168583.81 | a) | 2020-01-02 | e) | - | a) | 168583.81 | a) | - | c) | - | a) | - | On-going | AC
| 118 | [6 empty] | b) |  | b) |  | f) | - | b) | 168583.81 | b) | - | d) | - | b) | - |  | 1
[8 empty] | c) | PEO | c) | - | g) | - | c) | - | [7 empty] | 1
[8 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | JCT. SALVACION - SAN VICENTE - CABAY-ANGAN |  | CBRMC | 3.19 | Contract | a) | 158775.23 | a) | - | e) | - | a) | 158775.23 | a) | - | c) | - | a) | - |  | AC
| 118 | [6 empty] | b) | - | b) | - | f) | - | b) | 158775.23 | b) | - | d) | - | b) | - |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 1
[8 empty] | d) | - | d) | - | [11 empty] | 1
` |  |  | BACALI - CASIG-ANG - LIBERTAD |  | Road Maintenance | 4.61 | Admin | a) | 167836.14 | a) | 2020-01-02 | e) | - | a) | 167836.14 | a) | - | c) | - | a) | - | On-going | AC
| 123 | [6 empty] | b) |  | b) |  | f) | - | b) | 167836.14 | b) | - | d) | - | b) | - |  | 1
[8 empty] | c) | PEO | c) | - | g) | - | c) | - | [7 empty] | 1
[8 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | BACALI - CASIG-ANG - LIBERTAD |  | CBRMC | 4.61 | Contract | a) | 131608.37 | a) | - | e) | - | a) | 131608.37 | a) | - | c) | - | a) | - |  | AC
| 123 | [6 empty] | b) | - | b) | - | f) | - | b) | 131608.37 | b) | - | d) | - | b) | - |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 1
[8 empty] | d) | - | d) | - | [11 empty] | 1
` |  |  | KINAMAYAN - MOSLOG - MAHAYAG |  | Road Maintenance | 4.17 | Admin | a) | 114628.54 | a) | 2020-01-02 | e) | - | a) | 114628.54 | a) | - | c) | - | a) | - | On-going | AC
| 124 | [6 empty] | b) |  | b) |  | f) | - | b) | 114628.54 | b) | - | d) | - | b) | - |  | 1
[8 empty] | c) | PEO | c) | - | g) | - | c) | - | [7 empty] | 1
[8 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | KINAMAYAN - MOSLOG - MAHAYAG |  | CBRMC | 4.17 | Contract | a) | 91159.92 | a) | - | e) | - | a) | 91159.92 | a) | - | c) | - | a) | - |  | AC
| 124 | [6 empty] | b) | - | b) | - | f) | - | b) | 91159.92 | b) | - | d) | - | b) | - |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 1
[8 empty] | d) | - | d) | - | [11 empty] | 1
` |  |  | KINAMAYAN - LUNGA-OG |  | Road Maintenance | 5.1 | Admin | a) | 100416.26 | a) | 2020-01-02 | e) | - | a) | 100416.26 | a) | - | c) | - | a) | - | On-going | AC
| 126 | [6 empty] | b) |  | b) |  | f) | - | b) | 100416.26 | b) | - | d) | - | b) | - |  | 1
[8 empty] | c) | PEO | c) | - | g) | - | c) | - | [7 empty] | 1
[8 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | KINAMAYAN - LUNGA-OG |  | CBRMC | 5.1 | Contract | a) | 64596.78 | a) | - | e) | - | a) | 64596.78 | a) | - | c) | - | a) | - |  | AC
| 126 | [6 empty] | b) | - | b) | - | f) | - | b) | 64596.78 | b) | - | d) | - | b) | - |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 1
[8 empty] | d) | - | d) | - | [11 empty] | 1
` |  |  | PRK. APITONG - UPPER BALISONG - DALISAY |  | Road Maintenance | 1.3 | Admin | a) | 150598.24 | a) | 2020-01-02 | e) | - | a) | 150598.24 | a) | - | c) | - | a) | - | On-going | AC
| 128 | [6 empty] | b) |  | b) |  | f) | - | b) | 150598.24 | b) | - | d) | - | b) | - |  | 1
[8 empty] | c) | PEO | c) | - | g) | - | c) | - | [7 empty] | 1
[8 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | PRK. APITONG - UPPER BALISONG - DALISAY |  | CBRMC | 1.3 | Contract | a) | 142475.11 | a) | - | e) | - | a) | 142475.11 | a) | - | c) | - | a) | - |  | AC
| 128 | [6 empty] | b) | - | b) | - | f) | - | b) | 142475.11 | b) | - | d) | - | b) | - |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 1
[8 empty] | d) | - | d) | - | [11 empty] | 1
` |  |  | LOS AMIGOS 1 - ESPERANZA - LOS AMIGOS 2 |  | Road Maintenance | 2.54 | Admin | a) | 97116.27 | a) | 2020-01-02 | e) | - | a) | 97116.27 | a) | - | c) | - | a) | - | On-going | AC
| 130 | [6 empty] | b) |  | b) |  | f) | - | b) | 97116.27 | b) | - | d) | - | b) | - |  | 1
[8 empty] | c) | PEO | c) | - | g) | - | c) | - | [7 empty] | 1
[8 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | LOS AMIGOS 1 - ESPERANZA - LOS AMIGOS 2 |  | CBRMC | 2.54 | Contract | a) | 131608.37 | a) | - | e) | - | a) | 131608.37 | a) | - | c) | - | a) | - |  | AC
| 130 | [6 empty] | b) | - | b) | - | f) | - | b) | 131608.37 | b) | - | d) | - | b) | - |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 1
[8 empty] | d) | - | d) | - | [11 empty] | 1
` |  |  | MUGAS - LANATAD |  | Road Maintenance | 3.34 | Admin | a) | 65482.21 | a) | 2020-01-02 | e) | - | a) | 65482.21 | a) | - | c) | - | a) | - | On-going | AC
| 131 | [6 empty] | b) |  | b) |  | f) | - | b) | 65482.21 | b) | - | d) | - | b) | - |  | 1
[8 empty] | c) | PEO | c) | - | g) | - | c) | - | [7 empty] | 1
[8 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | MUGAS - LANATAD |  | CBRMC | 3.34 | Contract | a) | 31996.54 | a) | - | e) | - | a) | 31996.54 | a) | - | c) | - | a) | - |  | AC
| 131 | [6 empty] | b) | - | b) | - | f) | - | b) | 31996.54 | b) | - | d) | - | b) | - |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 1
[8 empty] | d) | - | d) | - | [11 empty] | 1
` |  |  | MUGAS - LUNGA-OG |  | Road Maintenance | 11.54 | Admin | a) | 96490.97 | a) | 2020-01-02 | e) | - | a) | 96490.97 | a) | - | c) | - | a) | - | On-going | AC
| 132 | [6 empty] | b) |  | b) |  | f) | - | b) | 96490.97 | b) | - | d) | - | b) | - |  | 1
[8 empty] | c) | PEO | c) | - | g) | - | c) | - | [7 empty] | 1
[8 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | MUGAS - LUNGA-OG |  | CBRMC | 11.54 | Contract | a) | 74256.11 | a) | - | e) | - | a) | 74256.11 | a) | - | c) | - | a) | - |  | AC
| 132 | [6 empty] | b) | - | b) | - | f) | - | b) | 74256.11 | b) | - | d) | - | b) | - |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 1
[8 empty] | d) | - | d) | - | [11 empty] | 1
` |  |  | NEW KATIPUNAN - PANTARON |  | Road Maintenance | 2.5 | Admin | a) | 71748.41 | a) | 2020-01-02 | e) | - | a) | 71748.41 | a) | - | c) | - | a) | - | On-going | AC
| 134 | [6 empty] | b) |  | b) |  | f) | - | b) | 71748.41 | b) | - | d) | - | b) | - |  | 1
[8 empty] | c) | PEO | c) | - | g) | - | c) | - | [7 empty] | 1
[8 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | NEW KATIPUNAN - PANTARON |  | CBRMC | 2.5 | Contract | a) | 53126.32 | a) | - | e) | - | a) | 53126.32 | a) | - | c) | - | a) | - |  | AC
| 134 | [6 empty] | b) | - | b) | - | f) | - | b) | 53126.32 | b) | - | d) | - | b) | - |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 1
[8 empty] | d) | - | d) | - | [11 empty] | 1
` |  |  | STO. TOMAS - BDRY. MAMACAO |  | Road Maintenance | 4.32 | Admin | a) | 195671.17 | a) | 2020-01-02 | e) | - | a) | 195671.17 | a) | - | c) | - | a) | - | On-going | AC
| 135 | [6 empty] | b) |  | b) |  | f) | - | b) | 195671.17 | b) | - | d) | - | b) | - |  | 1
[8 empty] | c) | PEO | c) | - | g) | - | c) | - | [7 empty] | 1
[8 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | STO. TOMAS - BDRY. MAMACAO |  | CBRMC | 4.32 | Contract | a) | 116515.66 | a) | - | e) | - | a) | 116515.66 | a) | - | c) | - | a) | - |  | AC
| 135 | [6 empty] | b) | - | b) | - | f) | - | b) | 116515.66 | b) | - | d) | - | b) | - |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 1
[8 empty] | d) | - | d) | - | [11 empty] | 1
` |  |  | FD. RD. 3 - SAN JOSE |  | Road Maintenance | 4.32 | Admin | a) | 176994.35 | a) | 2020-01-02 | e) | - | a) | 176994.35 | a) | - | c) | - | a) | - | On-going | AC
| 136 | [6 empty] | b) |  | b) |  | f) | - | b) | 176994.35 | b) | - | d) | - | b) | - |  | 1
[8 empty] | c) | PEO | c) | - | g) | - | c) | - | [7 empty] | 1
[8 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | FD. RD. 3 - SAN JOSE |  | CBRMC | 4.32 | Contract | a) | 112893.42 | a) | - | e) | - | a) | 112893.42 | a) | - | c) | - | a) | - |  | AC
| 136 | [6 empty] | b) | - | b) | - | f) | - | b) | 112893.42 | b) | - | d) | - | b) | - |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 1
[8 empty] | d) | - | d) | - | [11 empty] | 1
` |  |  | NAFCO - BOBONGON |  | Road Maintenance | 1.32 | Admin | a) | 89179.68 | a) | 2020-01-02 | e) | - | a) | 89179.68 | a) | - | c) | - | a) | - | On-going | AC
| 139 | [6 empty] | b) |  | b) |  | f) | - | b) | 89179.68 | b) | - | d) | - | b) | - |  | 1
[8 empty] | c) | PEO | c) | - | g) | - | c) | - | [7 empty] | 1
[8 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | NAFCO - BOBONGON |  | CBRMC | 1.32 | Contract | a) | 80293.17 | a) | - | e) | - | a) | 80293.17 | a) | - | c) | - | a) | - |  | AC
| 139 | [6 empty] | b) | - | b) | - | f) | - | b) | 80293.17 | b) | - | d) | - | b) | - |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 1
[8 empty] | d) | - | d) | - | [11 empty] | 1
` |  |  | BDRY. TAGUM - CROSSING KINAMAYAN - STO. TOMAS |  | Road Maintenance | 5.13 | Admin | a) | 790874.1 | a) | 2020-01-02 | e) | - | a) | 790874.1 | a) | - | c) | - | a) | - | On-going | AC
| 146 | [6 empty] | b) |  | b) |  | f) | - | b) | 790874.1 | b) | - | d) | - | b) | - |  | 1
[8 empty] | c) | PEO | c) | - | g) | - | c) | - | [7 empty] | 1
[8 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | BDRY. TAGUM - CROSSING KINAMAYAN - STO. TOMAS |  | CBRMC | 5.13 | Contract | a) | 429840.12 | a) | - | e) | - | a) | 429840.12 | a) | - | c) | - | a) | - |  | AC
| 146 | [6 empty] | b) | - | b) | - | f) | - | b) | 429840.12 | b) | - | d) | - | b) | - |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 1
[8 empty] | d) | - | d) | - | [11 empty] | 1
` |  |  | SAN JOSE - SITIO MAHAYAHAY, MAGWAWA |  | Road Maintenance | 3.22 | Admin | a) | 22943.54 | a) | 2020-01-02 | e) | - | a) | 22943.54 | a) | - | c) | - | a) | - | On-going | AC
| 151 | [6 empty] | b) |  | b) |  | f) | - | b) | 22943.54 | b) | - | d) | - | b) | - |  | 1
[8 empty] | c) | PEO | c) | - | g) | - | c) | - | [7 empty] | 1
[8 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | SAN JOSE - SITIO MAHAYAHAY, MAGWAWA |  | CBRMC | 3.22 | Contract | a) | 30789.12 | a) | - | e) | - | a) | 30789.12 | a) | - | c) | - | a) | - |  | AC
| 151 | [6 empty] | b) | - | b) | - | f) | - | b) | 30789.12 | b) | - | d) | - | b) | - |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 1
[8 empty] | d) | - | d) | - | [11 empty] | 1
Formulas:
Date A lot. Rel. = [Date A lot. Rel., row above]

## Annual 2019_Completed Dist 2 (hidden)
PROVINCE OF DAVAO DEL NORTE
ACCOMPLISHMENT REPORT
Annual 2019
SECTOR: ECONOMIC (INFRASTRUCTURE DEV'T. PROGRAM)
OFFICE/AGENCY: PROVINCIAL ENGINEER'S OFFICE
COMPLETED PROJECTS Dist 2
| Name of Project |  |  |  |  | Type | Physical | Mode | PROJECT DATA | [5 empty] | Financial (000) |  | Physical Accomplishment |  |  |  | Employment |  | REMARKS
[6 empty] | of | Target | of | a) Project Cost |  | a) Date A lot. Rel. |  | e) # of days suspended |  | a) Program |  | a) Planned |  | c) Actual |  | Generated
[6 empty] | Project | (Descrip | Impl. | b) Project Engineer |  | b) Date Started |  | f) # of days extended |  | b) Allotment |  | b) Revised |  | d) Slippage |  | a) # of Persons
[6 empty] | (Location) | tion) |  | c) Implementor |  | c)Target Compl. Date |  | g) Date completed |  | c) Disbursement | [5 empty] | b) Man-days
[9 empty] | d) Duration |  | d) Revised Compl. Date
| I. | PROJECTS UNDER THE CONTINUING APPROPRIATION | [21 empty] | AP | 893809.45
|  | A. | TRUST FUND | [20 empty] | AC
|  |  | DILG FUND CY 2016 | [20 empty] | AC
|  |  | 1.1 | 1.1 Improvement of DILG Building, Gov't. |  | Bldg. | 400 sq.m | Contract | a) | 5000000 | a) | CY 2016 | e) | 35 days | a) | 5000000 | a) | 100.00% | c) | 100.00% | a) | 8 | Completed as per physical accomplishment. | 1
|  |  |  | Center, Mankilam, Tagum City |  |  |  |  | b) | Pasiona | b) | 06/01/18 | f) | - | b) | 5000000 | b) | - | d) | - | b) | 240 | Financial documents still on process | 1
[9 empty] | c) | PEO | c) | 12/31/18 | g) | 03/31/19 | c) | 4,786,995.44 | [7 empty] | 1
[9 empty] | d) | 249 CD | d) | 03/30/19 | [11 empty] | 1
|  |  | KALSADA CY 2016 | [20 empty] | AC
|  |  | 1.1 Upgrading of Prk. Narafil – Barangay |  |  | Road | 2.03 | Contract. | a) | 51420795.98 | a) | CY 2016 | e) | - | a) | 51420795.98 | a) | 100.00% | c) | 100.00% | a) | 12 | Completed as per physical accomplishment. | 2
|  |  | Site Magupising Provincial Road | [5 empty] | b) | Andoy | b) | 04/18/18 | f) | 178 CD | b) | 51420795.98 | b) | - | d) | - | b) | 336 | Financial documents still on process | 2
|  |  | (Part of 60.329230.72M) (Contract Cost: P 43.597322.62M) | [5 empty] | c) | DCP | c) | 12/20/18 | g) | 05/07/19 | c) | 46,279,283.18 | [7 empty] | 2
[9 empty] | d) | 247 CD | d) | 05/07/19 | [11 empty] | 2
AC
|  |  | PAMANA-DILG CY 2016 | [20 empty] | AC
|  |  |  | Construction of Civic Center, San Isidro, |  | Bldg. | - | Admin | a) | 2,000,000.00 | a) | CY 2016 | e) | 40 CD | a) | 2,000,000.00 | a) | 100.00% | c) | 100.00% | a) | 8 | Completed as per physical accomplishment. | 1
|  |  |  | Tagum City |  |  |  |  | b) | Escurzon | b) | 7/5/2018 | f) | - | b) | 2,000,000.00 | b) | - | d) | - | b) | 240 | Financial documents still on process | 1
[9 empty] | c) | MAG Carp. | c) | 12/06/18 | g) | 01/15/19 | c) | - | [7 empty] | 1
[9 empty] | d) | 155 CD | d) | 01/15/19 | [11 empty] | 1
|  | A. | OPPAP-PAMANA | [20 empty] | AC
|  |  | Construction of Processing and Bagsakan Center |  |  | Bldg. | 300 sq.m | Contract | a) | 2500000 | a) | 08/15/18 | e) | - | a) | 2500000 | a) | 100.00% | c) | 100% | a) | 6 | Completed as per physical accomplishment. | 1
|  |  | Brgy. Palma Gil, Talaingod | [5 empty] | b) | Dadula | b) | 02/02/19 | f) | 35 CD | b) | 2500000 | b) |  | d) |  | b) | 180 | Financial documents still on process | 1
[9 empty] | c) | Alpha & Omega | c) | 05/12/19 | g) | 07/19/2019 | c) | [8 empty] | 1
[9 empty] | d) | 100 CD | d) | - | [11 empty] | 1
|  | B. | 20% Development Fund CY 2015 | [20 empty] | AC
|  |  | Improvement of Potable Water System Level II, |  |  | Water |  | Admin | a) | 1,125,000.00 | a) | 08/31/17 | e) | 222 CD | a) | 1,125,000.00 | a) | 100.00% | c) | 100% | a) | 4 | Completed 7/2/2019 as per physical accomplishment. Financial Documents still on process | 2
|  |  | Toril, IGCS |  |  | System |  |  | b) | Porras | b) | 02/19/18 | f) | 83 CD | b) | 1,125,000.00 | b) | - | d) | 0% | b) | 12 |  | 2
[9 empty] | c) | PEO | c) | 06/29/18 | g) | 7/2/2019 | c) | 1,009,555.97 | [7 empty] | 2
[9 empty] | d) |  | d) | 04/30/19 | [11 empty] | 2
|  | C. | 20% Development Fund CY 2016 | [20 empty] | AC
|  |  | 1. Water System Development Projects | [20 empty] | AC
|  | (Provincewide) | [21 empty] | AC
|  |  |  | Improvement of Potable Water System Level II, |  | Water |  | Admin | a) | 525,000.00 | a) | 08/31/17 | e) | 222 CD | a) | 525,000.00 | a) | 100% | c) | 100% | a) | 4 | Completed 7/2/2019 as per physical accomplishment. Financial Documents still on process | 2
|  |  |  | Toril, IGCS |  | System |  |  | b) | Porras | b) | 02/19/18 | f) | 83 CD | b) | 525,000.00 | b) | - | d) | 0% | b) | 12 |  | 2
[9 empty] | c) | PEO | c) | 06/29/18 | g) | 7/2/2019 | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | 04/30/19 | [11 empty] | 2
|  |  | 3. Const./Rehab./Comp. of Various Gov't. Bldgs. |  |  | Bldgs./ | - | Admin | a) | 9,000,000.00 | [13 empty] | AC
|  |  | Struct., Fac. (Provincewide) |  |  | Fence |  |  | b) | Foronda/Ababon | [13 empty] | AC
[9 empty] | c) | PEO | [13 empty] | AC
|  |  |  | Const./Impv't./Renov. Of DAVNOR Pharmacy |  | Bldg. |  | Admin | a) | 500,000.00 | a) | 08/10/18 | e) | 92 | a) | 500,000.00 | a) | 100% | c) | 100% | a) | 45 | Completed 6/28/2019 as per physical accomplishment. Financial documents still on process | 2
|  |  |  | Building, DDNH-CZ Compound |  |  |  |  | b) | Estorco | b) | 01/14/19 | f) | - | b) | 500,000.00 | b) | 100% | d) | 0% | b) | 3 |  | 2
|  |  |  | (Carmen District Hospital) |  |  |  |  | c) | Admin | c) | 03/26/19 | g) | 06/28/2019 | c) | 415,227.26 | [7 empty] | 2
[11 empty] | d) | 2019-06-28 | [11 empty] | 2
|  |  | SLRF 2015 | [7 empty] | a) |  | e) | 65 days | a) |  | a) | 100% | c) | 100% | a) | 3 | Completed as per POW, Financial Documents on Process | AC
|  |  | Rehab. of Jct. Highway-Tuganay-Anibongan-BE Dujali-Kinamayan Provincial Road (Furtheranace) |  |  | Slope protection | - | - | a) | 1911175.99 | b) | 2019-02-18 | f) | 47 days | b) |  | b) |  | d) | 0% | b) | 60 |  | 2
[9 empty] | b) | Balbastro | c) | 2019-09-21 | g) | 9/21/2019 | c) | [8 empty] | 2
[9 empty] | c) | Admin | d) | [12 empty] | 2
[9 empty] | d) | - | [13 empty] | 2
|  |  | TRUST FUND 2017 | [20 empty] | AC
|  |  | Conditional Matching Grant to Provinces (CMGP) | [20 empty] | AC
|  |  |  | Road Upgrading of FDR. Rd.3 – |  | Conc. | 10.359 km | Contract. | a) | 119901954.82 | a) | CY 2017 | e) | 47 CD | a) | 119901954.82 | a) | 100.00% | c) | 100% | a) | 10 | Completed based on POW, Financial Documents on Process | 2
|  |  |  | Kimamon – Luna Provincial Road, |  |  |  |  | b) | Comidoy | a) | 12/29/17 | f) | 198 CD | b) | 119901954.82 | b) | 100% | d) | 100% | b) | 220 |  | 2
|  |  |  | Sto. Tomas |  |  |  |  | c) | GP & H CONST. | c) | 12/12/18 | g) | - | c) | 119901954.82 | [7 empty] | 2
[9 empty] | d) | 326 CD | d) | 2019-07-29 | [11 empty] | 2
|  |  |  | Road Upgrading of Anahaw-Maligaya |  | Conc. | 5.18 km | Contract. | a) | 78,228,121.56 | a) | CY 2017 | e) | - | a) | 78,228,121.56 | a) | 100.00% | c) | 100% | a) | 30 | Completed based on POW, Financial Documents on Process | 2
|  |  |  | Provincial Road, Carmen |  |  |  |  | b) | Fernandez | b) | 12/24/17 | f) | 306 CD | b) | 78,228,121.56 | b) | 100% | d) | 0% | b) | 660 |  | 2
[9 empty] | c) | MONOLITHIC CONST. | c) | 03/31/19 | g) | - | c) | 76,214,361.38 | [7 empty] | 2
[9 empty] | d) | 210 CD | d) | 2019-06-05 | [11 empty] | 2
4 |  | 8 |  | Road Upgrading of Dagohoy - Daligdigon |  | Road | 2.532 km | Contract | a) | 58048310.68 | a) | CY 2017 | e) | - | a) | 58048310.68 | a) | 100.00% | c) | 100% | a) | 16 | Completed as per Physical Accomplishment, Financial Documents on Process | 1
4 |  |  |  | Provincial Road |  |  |  |  | b) | Fabiala | b) | 01/05/18 | f) | 205 CD | b) | 58048310.68 | b) | - | d) | 0% | b) | 480 |  | 1
4 | [8 empty] | c) | PUREGOLD | c) | 11/18/18 | g) | - | c) | 29,572,637.70 | [7 empty] | 1
4 | [8 empty] | d) | 246 CD | d) | 03/31/19 | [11 empty] | 1
4 |  |  |  | Impv’t. of Maligaya-New Camiling Prov’l. |  | Conc. | 2.13 km | Contract. | a) | 50101614.08 | a) | CY 2017 | e) | 76 CD | a) | 57385680 | a) | 100.00% | c) | 100% | a) | 21 | Completed based on POW. Financial Documents on process | 2
4 |  |  |  | Road w/ Bridge Component,Carmen |  |  |  |  | b) | Mellomida | b) | 12/18/17 | f) | 209 CD | b) | 57385680 | b) | 100% | d) | 0% | b) | 147 |  | 2
4 | [8 empty] | c) | PUREGOLD CONST. | c) | 02/15/19 | g) | - | c) | 36005452 | [7 empty] | 2
4 | [8 empty] | d) | 376 CD | d) | 07/31/19 | [11 empty] | 2
|  |  | OPPAP PAMANA | [20 empty] | AC
|  |  | Tribal Hall | [20 empty] | AC
|  |  |  | Construction of Tribal Hall |  | Bldg. |  | Admin | a) | 500000 | a) | CY 2018 | e) | - | a) | 500000 | a) | 100% | c) | 100% | a) | 5 | Completed as per Physical Accomplishment. Financial Documents on process | 1
|  |  |  | Brgy. Gupitan, Kapalong |  |  |  |  | b) | Ambrocio | b) | 2/22/2019 | f) | - | b) | 500000 | b) | - | d) | 0% | b) | 150 |  | 1
[9 empty] | c) | PEO | c) | 5/22/2019 | g) | - | c) | - | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | Processing and Bagsakan Center | [20 empty] | AC
|  |  |  | Const. of Processing and Bagsakan Center, |  | Bldg. | 300 sq.m | Contract | a) | 2500000 | a) | 08/29/18 | e) | - | a) | 2500000 | a) | 100% | c) | 100% | a) | 6 | Completed as per Physical Accomplishment. Financial Documents on process | 1
|  |  |  | Brgy. Gupitan, Kapalong, Davao del Norte |  |  |  |  | b) | Ambrucio | b) | 02/12/19 | f) | - | b) | 2500000 | b) | - | d) | 0% | b) | 180 |  | 1
[9 empty] | c) | Alpha & Omega | c) | 05/12/19 | g) | - | c) | 156000 | [7 empty] | 1
[9 empty] | d) | 120 CD | d) | - | [11 empty] | 1
|  |  |  | Construction of Processing and Bagsakan Center |  | Bldg. | 300 sq.m | Contract | a) | 2500000 | a) | 08/15/18 | e) | - | a) | 2500000 | a) | 100.00% | c) | 100% | a) | 6 | Completed as per physical accomplishment. | 1
|  |  |  | Brgy. Palma Gil, Talaingod |  |  |  |  | b) | Dadula | b) | 02/02/19 | f) | 35 CD | b) | 2500000 | b) |  | d) |  | b) | 180 | Financial documents still on process | 1
[9 empty] | c) | Alpha & Omega | c) | 05/12/19 | g) | 07/19/2019 | c) | [8 empty] | 1
[9 empty] | d) | 100 CD | d) | - | [11 empty] | 1
|  | D. | 20% Development Fund CY 2017 | [20 empty] | AC
|  |  | STIMULUS PROJECTS CY 2017 | [20 empty] | AC
|  |  | TAGUM CITY | [20 empty] | AC
|  |  |  | Impv't. of Magdum Barangay Hall, |  | Bldgs. |  | Admin | a) | 500000 | a) | 11/29/17 | e) | - | a) | 500000 | a) | 100.00% | c) | 100.00% | a) | 6 | Completed as per physical accomplishment. | 1
|  |  |  | Magdum, Tagum City |  |  |  |  | b) | Pasiona | b) | 04/23/18 | f) | 10 CD | b) | 500000 | b) | - | d) | - | b) | 108 | Financial documents still on process | 1
[9 empty] | c) | PEO | c) | 06/11/18 | g) | 06/21/18 | c) | 484028 | [7 empty] | 1
[9 empty] | d) | 50 CD | d) | 06/21/18 | [11 empty] | 1
|  |  |  | Const. Stage, Canocotan, Tagum City |  | Bldgs. |  | Contract | a) | 500000 | a) | 12/28/17 | e) | - | a) | 500000 | a) | 100.00% | c) | 100.00% | a) | 7 | Completed as per physical accomplishment. | 1
[9 empty] | b) | Escurzon | b) | 06/01/18 | f) | - | b) | 500000 | b) | - | d) | - | b) | 140 | Financial documents still on process | 1
[9 empty] | c) | FT Construction | c) | 07/15/18 | g) | 08/22/18 | c) | 457128.95 | [7 empty] | 1
[9 empty] | d) | 45 CD | d) | - | [11 empty] | 1
|  |  |  | Construction of Bleachers and Firewall |  | Bldgs. |  | Contract | a) | 500000 | a) | 06/05/18 | e) | - | a) | 500000 | a) | 100.00% | c) | 100.00% | a) | 6 | Completed as per physical accomplishment. | 1
|  |  |  | for the GYM, Magugpo West, Tagum City |  |  |  |  | b) | Medalla | b) | 09/13/18 | f) | - | b) | 500000 | b) | - | d) | - | b) | 180 | Financial documents still on process | 1
[9 empty] | c) | RLHV | c) | 11/08/18 | g) | 11/08/18 | c) | 473595.97 | [7 empty] | 1
[9 empty] | d) | 60 CD | d) | - | [11 empty] | 1
|  |  |  | Const. of 1 Bay Span Covered Court, |  | Court | 96 sq.m | Contract | a) | 500000 | a) | 06/05/18 | e) | - | a) | 500000 | a) | 100.00% | c) | 100.00% | a) | 5 | Completed as per physical accomplishment. | 1
|  |  |  | Brgy. La Filipina, Tagum City |  |  |  |  | b) | Medalla | b) | 12/10/18 | f) | - | b) | 500000 | b) | - | d) | - | b) | 150 | Financial documents still on process | 1
[9 empty] | c) | FT Const. | c) | 01/29/19 | g) | 04/12/19 | c) | - | [7 empty] | 1
[9 empty] | d) | 50 CD | d) | - | [11 empty] | 1
|  |  | SAN ISIDRO | [20 empty] | AC
|  |  |  | Rehab. Of Sawata Gymnasiun, San Isidro |  | Bldgs. |  | Contract | a) | 500000 | a) | 11/29/17 | e) | - | a) | 500000 | a) | 100.00% | c) | 100.00% | a) | 6 | Completed as per physical accomplishment. | 1
[9 empty] | b) | Escurzon | b) | 01/06/18 | f) | 15 CD | b) | 500000 | b) | - | d) | - | b) | 180 | Financial documents still on process | 1
[9 empty] | c) | FT Construction | c) | 05/07/18 | g) | 07/25/18 | c) | 474,700.57 | [7 empty] | 1
[9 empty] | d) | 35 CD | d) | 07/20/18 | [11 empty] | 1
|  |  |  | Compl. Of Pipeline Level II, Brgy. San Miguel, |  | Bldgs. |  | Contract | a) | 500000 | a) | 12/28/17 | e) | - | a) | 500000 | a) | 100.00% | c) | 100.00% | a) | 5 | Completed as per physical accomplishment. | 1
|  |  |  | San Isidro |  |  |  |  | b) | Diosanta | b) | 05/25/18 | f) | 28 CD | b) | 500000 | b) | - | d) | - | b) | 100 | Financial documents still on process | 1
[9 empty] | c) | ZULAR - AZ Const. & Supply | c) | 06/07/18 | g) | 07/25/18 | c) | 479116.61 | [7 empty] | 1
[9 empty] | d) | 24 CD | d) | 07/05/18 | [11 empty] | 1
|  |  |  | Const. of Covered Court, Datu Balong, |  | Bldgs. |  | Contract | a) | 500000 | a) | 11/29/17 | e) | - | a) | 500000 | a) | 100.00% | c) | 100.00% | a) | 5 | Completed as per physical accomplishment. | 1
|  |  |  | San Isidro |  |  |  |  | b) | Escurzon | b) | 01/06/18 | f) | - | b) | 500000 | b) | - | d) | - | b) | 90 | Financial documents still on process | 1
[9 empty] | c) | FT Construction | c) | 07/10/18 | g) | 08/31/18 | c) | 472019.86 | [7 empty] | 1
[9 empty] | d) | 40 CD | d) | - | [11 empty] | 1
|  |  |  | Const. of Brgy. Stage, Linao, San Isidro |  | Bldgs. |  | Contract | a) | 500000 | a) | 11/29/17 | e) | - | a) | 500000 | a) | 100.00% | c) | 100.00% | a) | 12 | Completed as per physical accomplishment. | 1
[9 empty] | b) | Escurzon | b) | 01/06/18 | f) | 15 CD | b) | 500000 | b) | - | d) | - | b) | 216 | Financial documents still on process | 1
[9 empty] | c) | FT Construction | c) | 05/07/18 | g) | 09/03/18 | c) | 465500 | [7 empty] | 1
[9 empty] | d) | 45 CD | d) | 07/15/18 | [11 empty] | 1
|  |  |  | Const. of Potable Water System, Monte |  | Bldgs. |  | Contract | a) | 500000 | a) | 12/28/17 | e) | - | a) | 500000 | a) | 100.00% | c) | 100.00% | a) | 6 | Completed as per physical accomplishment. | 1
|  |  |  | Dujali, San Isidro |  |  |  |  | b) | Escurzon | b) | 01/06/18 | f) | 20 CD | b) | 500000 | b) | - | d) | - | b) | 180 | Financial documents still on process | 1
[9 empty] | c) | FT Construction | c) | 07/30/18 | g) | 09/07/18 | c) | 470612.51 | [7 empty] | 1
[9 empty] | d) | 60 CD | d) | 08/25/18 | [11 empty] | 1
|  |  |  | Const. of Covered Court , Libuton, San Isidro |  | Bldgs. |  | Contract | a) | 500000 | a) | 11/29/17 | e) | - | a) | 500000 | a) | 100.00% | c) | 100.00% | a) | 6 | Completed as per physical accomplishment. | 1
[9 empty] | b) | Escurzon | b) | 01/06/18 | f) | - | b) | 500000 | b) | - | d) | - | b) | 180 | Financial documents still on process | 1
[9 empty] | c) | FT Construction | c) | 07/15/18 | g) | 08/22/18 | c) | 476716.56 | [7 empty] | 1
[9 empty] | d) | 45 CD | d) | - | [11 empty] | 1
|  |  |  | Improvement of Barangay Hall Perimeter |  | Bldgs. |  | Contract | a) | 500000 | a) | 11/29/17 | e) | - | a) | 500000 | a) | 100.00% | c) | 100.00% | a) | 6 | Completed as per physical accomplishment. | 1
|  |  |  | Fence, Brgy. Dakudao, San Isidro |  |  |  |  | b) | Escurzon | b) | 06/01/18 | f) | 26 CD | b) | 500000 | b) | - | d) | - | b) | 180 | Financial documents still on process | 1
[9 empty] | c) | FT Const. | c) | 07/30/18 | g) | 09/04/18 | c) | '468,532.48 | [7 empty] | 1
[9 empty] | d) | 60 CD | d) | 08/25/18 | [11 empty] | 1
|  |  | ASUNCION | [20 empty] | AC
|  |  |  | Completion of Magatos E/S Perimeter |  | Bldgs. |  | MEO | a) | 500000 | a) | 12/28/17 | e) | - | a) | 500000 | a) | 100.00% | c) | 100.00% | a) | 19 | Completed as per physical accomplishment | 1
|  |  |  | Fence, Asuncion |  |  |  |  | b) | Inquillon | b) | 06/01/18 | f) | - | b) | 500000 | b) | - | d) | - | b) | 426 | - Fund transferred at Municipality of Asuncion | 1
[9 empty] | c) | MEO | c) | 07/30/17 | g) | 07/30/17 | c) | 500000 | [6 empty] | with ChecK No. 2445178 and OR # 9238462, | 1
[9 empty] | d) | - | d) | - | [10 empty] | dated March 16, 2018 | 1
|  |  |  | Const. of Covered Court Ph.1, Camansa, |  | Bldgs. |  | MEO | a) | 500000 | a) | 12/19/17 | e) | - | a) | 500000 | a) | 100.00% | c) | 100.00% | a) | 15 | Completed as per physical accomplishment. | 1
|  |  |  | Asuncion |  |  |  |  | b) | Inquillon | b) | 05/16/18 | f) | - | b) | 500000 | b) | - | d) | - | b) | 399 | - Fund transferred at Municipality of Asuncion | 1
[9 empty] | c) | MEO | c) | 09/15/18 | g) | 07/15/18 | c) | 500000 | [6 empty] | with ChecK No. 2445090 and OR # 8975230, | 1
[9 empty] | d) | - | d) | - | [10 empty] | dated February 5, 2018 | 1
|  |  |  | FMR 0.5km at Brgy. Site, Sonlon, |  | Bldgs. |  | MEO | a) | 500000 | a) | 12/28/17 | e) | - | a) | 500000 | a) | 100.00% | c) | 100.00% | a) | 12 | Completed as per physical accomplishment. (Fund already transferred at Municipality of Asuncion with ChecK No. 2445173 and OR # 9238463, dated March 16, 2018) | 1
|  |  |  | Asuncion |  |  |  |  | b) | Inquillon | b) | 2018-06-18 | f) | - | b) | 500000 | b) | - | d) | - | b) | 156 |  | 1
[9 empty] | c) | MEO | c) | 08/15/18 | g) | 08/10/18 | c) | 500000 | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  |  | Const. of Covered Court Ph. 1, Sta. |  | Bldgs. |  | MEO | a) | 500000 | a) | 12/28/17 | e) | - | a) | 500000 | a) | 100.00% | c) | 100.00% | a) | 13 | Completed as per physical accomplishment | 1
|  |  |  | Felomina, Asuncion |  |  |  |  | b) | Inquillon | b) | 06/18/18 | f) | - | b) | 500000 | b) | - | d) | - | b) | 426 | - Fund transferred at Municipality of Asuncion | 1
[9 empty] | c) | MEO | c) | 08/15/18 | g) | 08/05/18 | c) | 500000 | [6 empty] | with ChecK No. 2445177 and OR # 9238464, | 1
[9 empty] | d) | - | d) | - | [10 empty] | dated March 16, 2018 | 1
|  |  |  | Impv't. of Brgy. Facilities, Buclad, Asuncion |  | Bldgs. |  | MEO | a) | 500000 | a) | 12/19/17 | e) | - | a) | 500000 | a) | 100.00% | c) | 100.00% | a) | 12 | Completed as per physical accomplishment. (Fund already transferred at Municipality of Asuncion with ChecK No. 2445032 and OR # 8975234, dated February 5, 2018) | 1
[9 empty] | b) | Inquillon | b) | 04/30/18 | f) | - | b) | 500000 | b) | - | d) | - | b) | 364 |  | 1
[9 empty] | c) | MEO | c) | 07/30/18 | g) | 2018-06-30 | c) | 500000 | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  |  | Impv't. of Brgy. Hall, Cabaywa, Asuncion |  | Bldgs. |  | MEO | a) | 500000 | a) | 12/19/17 | e) | - | a) | 500000 | a) | 100.00% | c) | 100.00% | a) | 11 | Completed as per physical accomplishment. | 1
[9 empty] | b) | Inquillon | b) | 05/18/18 | f) | - | b) | 500000 | b) | - | d) | - | b) | 358 | - Fund transferred at Municipality of Asuncion | 1
[9 empty] | c) | MEO | c) | 08/16/18 | g) | 07/02/18 | c) | - | [6 empty] | with ChecK No. 2445031 and OR # 8975233, | 1
[9 empty] | d) | - | d) | - | [10 empty] | dated February 5, 2018 | 1
|  |  |  | Impv't. of Multi-Purpose Bldg., Napungas |  | Bldgs. |  | MEO | a) | 500000 | a) | 12/28/17 | e) | - | a) | 500000 | a) | 100.00% | c) | 100.00% | a) | 14 | Completed as per physical accomplishment. (Fund already transferred at Municipality of Asuncion with ChecK No. 2445147 and OR # 8975232, dated February 5, 2018) | 1
|  |  |  | Asuncion |  |  |  |  | b) | Inquillon | b) | 06/16/18 | f) | - | b) | 500000 | b) | - | d) | - | b) | 207 |  | 1
[9 empty] | c) | MEO | c) | 07/30/18 | g) | 07/30/18 | c) | 500000 | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  |  | Construction of Multi-Purpose Stage, |  | Bldgs. |  | MEO | a) | 500000 | a) | 12/19/17 | e) | - | a) | 500000 | a) | 100.00% | c) | 100.00% | a) | 18 | Completed as per physical accomplishment. (Fund already transferred at Municipality of Asuncion with ChecK No. 2445030 and OR # 8975231, dated February 5, 2018 (Compl: Aug. 16, 2018) | 1
|  |  |  | Binancian, Asuncion |  |  |  |  | b) | Inquillo | b) | 05/18/18 | f) | - | b) | 500000 | b) | - | d) | - | b) | 396 |  | 1
[9 empty] | c) | MEO | c) | 08/16/18 | g) | 08/16/18 | c) | 500000 | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  |  | Construction of Covered Court Ph. 1, |  | Bldgs. |  | MEO | a) | 500000 | a) | 02/06/18 | e) | - | a) | 500000 | a) | 100.00% | c) | 100.00% | a) | 14 | Completed as per physical accomplishment | 1
|  |  |  | Buan, Asuncion |  |  |  |  | b) | Inquillo | b) | 06/01/18 | f) | - | b) | 500000 | b) | - | d) | - | b) | 430 | - Fund transferred at Municipality of Asuncion | 1
[9 empty] | c) | MEO | c) | 08/30/18 | g) | 07/30/18 | c) | 500000 | [6 empty] | with ChecK No. 2445282 and OR # 9238466, | 1
[9 empty] | d) | - | d) | - | [10 empty] | dated March 16, 2018. | 1
|  |  |  | Construction of Nutrition Bldg. Ph. 1, |  | Bldgs. |  | MEO | a) | 500000 | a) | 12/20/17 | e) | - | a) | 500000 | a) | 100.00% | c) | 100.00% | a) | 9 | Completed as per physical accomplishment | 1
|  |  |  | Cambanogoy, Asuncion |  |  |  |  | b) | Inquillo | b) | 07/16/18 | f) | - | b) | 500000 | b) | - | d) | - | b) | 135 | - Fund transferred at Municipality of Asuncion with | 1
[9 empty] | c) | MEO | c) | 08/14/18 | g) | 11/15/18 | c) | 500000 | [6 empty] | ChecK No. 24465176 and OR # 9238465, | 1
[9 empty] | d) | - | d) | - | [10 empty] | dated March 16, 2018 | 1
|  |  |  | Rehab. Of 2 Inches Pipelines of Water System |  | Bldgs. |  | MEO | a) | 500000 | a) | 12/28/17 | e) | - | a) | 500000 | a) | 100.00% | c) | 100.00% | a) | 12 | Completed as per physical accomplishment | 1
|  |  |  | at Prk. 1, New Loon, Asuncion |  |  |  |  | b) | Inquillo | b) | 08/05/18 | f) | - | b) | 500000 | b) | - | d) | - | b) | 180 | -Fund transferred at Municipality of Asuncion with | 1
[9 empty] | c) | MEO | c) | 11/15/18 | g) | 11/15/18 | c) | 500000 | [6 empty] | ChecK No. 2445175 and OR # 9238467, | 1
[9 empty] | d) | - | d) | - | [10 empty] | dated March 16, 2018 | 1
|  |  | NEW CORELLA | [20 empty] | 1
|  |  |  | Fabrication of Bleachers, New Cortez, |  | Bldgs. |  | MEO | a) | 500000 | a) | 12/28/17 | e) | - | a) | 500000 | a) | 100.00% | c) | 100.00% | a) | - | Completed as per physical accomplishment. (Fund already transferred at Municipality of New Corella with ChecK No. 2445146 and OR # 8592069, dated March 13, 2018) | 1
|  |  |  | New Corella |  |  |  |  | b) | Inquillo & Dogoldogol | b) | 06/15/18 | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 1
[9 empty] | c) | MEO | c) | 07/31/18 | g) | 07/31/18 | c) | 500000 | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  |  | Renov./Impv't. Of Brgy. Hall, New Sambog, |  | Bldgs. |  | MEO | a) | 500000 | a) | 12/19/17 | e) | - | a) | 500000 | a) | 100.00% | c) | 100.00% | a) | - | Completed as per physical accomplishment. (Fund already transferred at Municipality of New Corella with ChecK No. 2445023 and OR # 8592070, dated March 13, 2018) | 1
|  |  |  | New Corella |  |  |  |  | b) | - | b) | 07/01/18 | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 1
[9 empty] | c) | MEO | c) | 08/15/18 | g) | 08/15/18 | c) | - | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  |  | Rehab. Of Potable Water in Prk. 2,3,3A, |  | Bldgs. |  | MEO | a) | 500000 | a) | 02/19/18 | e) | - | a) | 500000 | a) | 100.00% | c) | 100.00% | a) | - | Completed as per physical accomplishment.Fund already transferred at Municipality of New Corella with ChecK No. 2445320 and OR # 8592073, dated March 13, 2018 | 1
|  |  |  | 3B & 6, Macgum, New Corella |  |  |  |  | b) | - | b) | 08/15/18 | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 1
[9 empty] | c) | MEO | c) | - | g) | 11/19/18 | c) | 500000 | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  |  | Renov./Impv't. of Brgy. Hall, Patrocenio, |  | Bldgs. |  | MEO | a) | 500000 | a) | 12/20/17 | e) | - | a) | 500000 | a) | 100.00% | c) | 100.00% | a) | - | Completed as per physical accomplishment | 1
|  |  |  | New Corella |  |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - | - Fund transferred at Municipality of New Corella | 1
[9 empty] | c) | MEO | c) | - | g) | 11/19/18 | c) | 500000 | [6 empty] | with ChecK No. 2445022 and OR # 8592071, | 1
[9 empty] | d) |  | d) | - | [10 empty] | dated March 13, 2018 | 1
|  |  |  | Impv't. of Covered Court, New Bohol, |  | Bldgs. |  | Barangay | a) | 500000 | a) | 02/13/8 | e) | - | a) | 500000 | a) | 100.00% | c) | 100.00% | a) | - | Completed as per physical accomplishment.Fund already transferred at Municipality of New Corella with ChecK No. 2445321 and OR # 8592075, dated March 13, 2018 | 1
|  |  |  | New Corella |  |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 1
[9 empty] | c) | - | c) | - | g) | 08/15/18 | c) | 500000 | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  |  | Construction of Multi-Purpose Bldg., |  | Bldgs. |  | MEO | a) | 500000 | a) | 02/06/18 | e) | - | a) | 500000 | a) | 100.00% | c) | 100.00% | a) | - | Completed as per physical accomplishment.Fund already transferred at Municipality of New Corella ChecK No. 2445281 with and OR # 8592076, dated March 13, 2018 | 1
|  |  |  | San Jose, New Corella |  |  |  |  | b) | - | b) | 08/05/18 | f) | - | b) | 500000 | b) |  | d) | - | b) | - |  | 1
[9 empty] | c) | MEO | c) | 02/28/19 | g) | 02/28/19 | c) | 500000 | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  |  | Construction of 1 CL School Bldg., |  | Bldg. |  | Barangay | a) | 500000 | a) | 12/28/17 | e) | - | a) | 500000 | a) | 100.00% | c) | 100.00% | a) | - | Completed as per physical accomplishment.Fund already transferred at Municipality of New Corella with ChecK No. 2445183 and OR # 8592077, dated March 13, 2018 | 1
|  |  |  | Mambing, New Corella |  |  |  |  | b) | - | b) | 2018-01-06 | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 1
[9 empty] | c) | MEO | c) | 7/15/2018 | g) | 7/15/2018 | c) | - | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | SAN ISIDRO | [20 empty] | AC
|  |  |  | Rehab. Of Sawata Gymnasiun, San Isidro |  | Bldgs. |  | Contract | a) | 500000 | a) | 11/29/17 | e) | - | a) | 500000 | a) | 100.00% | c) | 100.00% | a) | - | Completed as per physical accomplishment. | 1
[9 empty] | b) | Escurzon | b) | 01/06/18 | f) | 15 CD | b) | 500000 | b) | - | d) | - | b) | - | Financial documents still on process | 1
[9 empty] | c) | FT Construction | c) | 05/07/18 | g) | 07/25/18 | c) | 474,700.57 | [7 empty] | 1
[9 empty] | d) | 35 CD | d) | 07/20/18 | [11 empty] | 1
|  |  |  | Compl. Of Pipeline Level II, Brgy. San Miguel, |  | Water |  | Contract | a) | 500000 | a) | 12/28/17 | e) | - | a) | 500000 | a) | 100.00% | c) | 100.00% | a) | 5 | Completed as per physical accomplishment. | 1
|  |  |  | San Isidro |  |  |  |  | b) | Diosanta | b) | 05/25/18 | f) | 28 CD | b) | 500000 | b) | - | d) | - | b) | 100 | Financial documents still on process | 1
[9 empty] | c) | ZULAR - AZ Const. & Supply | c) | 06/07/18 | g) | 07/25/18 | c) | 478500 | [7 empty] | 1
[9 empty] | d) | 24 CD | d) | 07/05/18 | [11 empty] | 1
|  |  |  | Const. of Covered Court, Datu Balong, |  | Bldgs. |  | Contract | a) | 500000 | a) | 11/29/17 | e) | - | a) | 500000 | a) | 100.00% | c) | 100.00% | a) | 5 | Completed as per physical accomplishment. | 1
|  |  |  | San Isidro |  |  |  |  | b) | Escurzon | b) | 01/06/18 | f) | - | b) | 500000 | b) | - | d) | - | b) | 90 | Financial documents still on process | 1
[9 empty] | c) | FT Construction | c) | 07/10/18 | g) | 08/31/18 | c) | 472019.86 | [7 empty] | 1
[9 empty] | d) | 40 CD | d) | - | [11 empty] | 1
|  |  |  | Const. of Brgy. Stage, Linao, San Isidro |  | Bldgs. |  | Contract | a) | 500000 | a) | 11/29/17 | e) | - | a) | 500000 | a) | 100.00% | c) | 100.00% | a) | 12 | Completed as per physical accomplishment. | 1
[9 empty] | b) | Escurzon | b) | 01/06/18 | f) | 15 CD | b) | 500000 | b) | - | d) | - | b) | 216 | Financial documents still on process | 1
[9 empty] | c) | FT Construction | c) | 05/07/18 | g) | 09/03/18 | c) | 495500 | [7 empty] | 1
[9 empty] | d) | 45 CD | d) | 07/15/18 | [11 empty] | 1
|  |  |  | Const. of Potable Water System, Monte |  | Water |  | Contract | a) | 500000 | a) | 12/28/17 | e) | - | a) | 500000 | a) | 100.00% | c) | 100.00% | a) | 6 | Completed as per physical accomplishment. | 1
|  |  |  | Dujali, San Isidro |  |  |  |  | b) | Escurzon | b) | 01/06/18 | f) | 20 CD | b) | 500000 | b) | - | d) | - | b) | 180 | Financial documents still on process | 1
[9 empty] | c) | FT Construction | c) | 07/30/18 | g) | 09/07/18 | c) | 472977.4 | [7 empty] | 1
[9 empty] | d) | 60 CD | d) | 08/25/18 | [11 empty] | 1
|  |  |  | Const. of Covered Court , Libuton, San Isidro |  | bldgs. |  | Contract | a) | 500000 | a) | 11/29/17 | e) | - | a) | 500000 | a) | 100.00% | c) | 100.00% | a) | 6 | Completed as per physical accomplishment. | 1
[9 empty] | b) | Escurzon | b) | 01/06/18 | f) | - | b) | 500000 | b) | - | d) | - | b) | 180 | Financial documents still on process | 1
[9 empty] | c) | FT Construction | c) | 07/15/18 | g) | 08/22/18 | c) | 476716.56 | [7 empty] | 1
[9 empty] | d) | 45 CD | d) | - | [11 empty] | 1
|  |  |  | Improvement of Barangay Hall Perimeter |  | Fence |  | Contract | a) | 500000 | a) | 11/29/17 | e) | - | a) | 500000 | a) | 100.00% | c) | 100.00% | a) | 6 | Completed as per physical accomplishment. | 1
|  |  |  | Fence, Brgy. Dakudao, San Isidro |  |  |  |  | b) | Escurzon | b) | 01/06/18 | f) | - | b) | 500000 | b) | - | d) | - | b) | 180 | Financial documents still on process | 1
[9 empty] | c) | FT Construction | c) | 07/30/18 | g) | 08/25/18 | c) | 468532.48 | [7 empty] | 1
[9 empty] | d) | 60 CD | d) | 08/25/18 | [11 empty] | 1
1
|  |  |  | Completion of Multi-Purpose Building |  | Bldg. |  | Contract | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | 100.00% | c) | 100.00% | a) | 6 | Completed as per physical accomplishment. | 1
|  |  |  | Kipalili, San isidro |  |  |  |  | b) | Obero | b) | 12/03/18 | f) | - | b) | 500000 | b) | - | d) | - | b) | 180 | Financial documents still on process | 1
[9 empty] | c) | RLHV | c) | 01/05/19 | g) | 08/22/18 | c) | 459201 | [7 empty] | 1
[9 empty] | d) | 30 CD | d) | - | [11 empty] | 1
|  |  | IGACOS | [20 empty] | AC
|  |  |  | Rehab. of Water System, Sion, IGACOS |  | Water |  | Admin | a) | 500000 | a) | 12/01/17 | e) | - | a) | 500000 | a) | 100.00% | c) | 100.00% | a) | - | Completed as per physical accomplishment. | 2
[6 empty] | System |  |  | b) | Diosanta | b) | 08/24/18 | f) | - | b) | 500000 | b) | - | d) | - | b) | - | Financial documents still on process | 2
[9 empty] | c) | PEO | c) | 09/28/18 | g) | 09/28/18 | c) | 425,192.30 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  |  | Impvt. of MP Gym, San Agustin, IGACOS |  | Bldgs. |  | Contract | a) | 500000 | a) | 12/01/17 | d) | - | a) | 500000 | a) | 100% | c) | 100% | a) | - | Completed as per physical accomplishment. | 2
[9 empty] | b) | Porras | b) | 2018-04-26 | e) | - | b) | 500000 | b) | - | d) | - | b) | - | Financial documents still on process | 2
[9 empty] | c) | SILJURE | c) | 2018-06-06 | f) | 06/01/18 | c) | 443364.85 | [7 empty] | 2
[9 empty] | d) | 42 CD | d) | - | [11 empty] | 2
|  |  |  | Conc. of Brgy. Road, Camudmud, IGACOS |  | Road |  | Contract | a) | 500000 | a) | 11/29/17 | d) | - | a) | 500000 | a) | 100% | c) | 100% | a) | 5 | Completed as per physical accomplishment. | 2
[9 empty] | b) | Pacquio | b) | 2018-04-26 | e) | 16 days | b) | 500000 | b) | - | d) | - | b) | 30 | Financial documents still on process | 2
[9 empty] | c) | SILJURE | c) | 2018-06-11 | f) | 2018-06-11 | c) | 467128.2 | [7 empty] | 2
[9 empty] | d) | 30 CD | d) | - | [11 empty] | 2
|  |  |  | Impvt of Evacuation Center, |  | Bldg. |  | Admin | a) | 500000 | a) | 12/01/17 | e) | - | a) | 500000 | a) | 100.00% | c) | 100.00% | a) | 8 | Completed as per physical accomplishment. | 2
|  |  |  | Brgy. Balet, IGACOS |  |  |  |  | b) | Porras | b) | 05/01/19 | f) | - | b) | 500000 | b) | - | d) | - | b) | 160 | Financial documents still on process | 2
[9 empty] | c) | PEO | c) | 06/12/19 | g) | 06/06/19 | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | CARMEN | [20 empty] | AC
2
|  |  |  | Compl. Of Evacuation Ctr. Bldg. Taba, Carmen |  | Bldg. |  | Barangay | a) | 500000 | a) | 12/19/17 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Completed 9/19/2018 as per physical accomplishment. Financial documents still on process | 2
[9 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 2
[9 empty] | c) | - | c) | - | g) | 9/19/2018 | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  |  | Const. of Multi-Purpose Stage @ Prk. 2, |  | Bldg. |  | Barangay | a) | 500000 | a) | 12/19/17 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Completed as per physical accomplishment. Financial documents still on process | 2
|  |  |  | Salvacion, Carmen |  |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 2
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  |  | Const. of Multi-Purpose Bldg., |  | Bldg. |  | Barangay | a) | 500000 | a) | 12/28/17 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Completed 9/19/2018 as per physical accomplishment. Financial documents still on process | 2
|  |  |  | Magsaysay, Carmen |  |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 2
[9 empty] | c) | - | c) | - | g) | 9/19/2018 | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  |  | Compl. Of Covered Court/Stage, |  | Court |  | Barangay | a) | 500000 | a) | 12/28/17 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Completed 9/19/2018 as per physical accomplishment. Financial documents still on process | 2
|  |  |  | New Camiling, Carmen |  |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 2
[9 empty] | c) | - | c) | - | g) | 9/19/2018 | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
4 |  |  |  | Construction of Evaluation Center at Prk. 1, |  | Bldg. |  | Barangay | a) | 500000 | a) | 12/28/17 | e) | - | a) | 500000 | a) | - | c) | 100% | a) | - | Completed | 2
4 |  |  |  | Asuncion, Carmen |  |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 2
4 | [8 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 2
4 | [8 empty] | d) | - | d) | - | [11 empty] | 2
AC
|  |  | PANABO CITY | [20 empty] | AC
2
|  |  |  | Brgy. Covered Court Fencing, Sta. Cruz, |  | Court |  | Barangay | a) | 500000 | a) | 12/28/17 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Completed 6/10/2019 as per physical accomplishment. Financial documents still on process | 2
|  |  |  | Panabo CIty |  |  |  |  | b) | - | b) | 5/15/2019 | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 2
[9 empty] | c) | - | c) | 6/10/2019 | g) | - | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  |  | Const. of Multi-Purpose Bldg., Katualan, |  | Bldg. |  | Barangay | a) | 500000 | a) | 12/19/17 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Completed 10/12/2018 as per physical accomplishment. Financial documents still on process | 2
|  |  |  | Panabo CIty |  |  |  |  | b) | - | b) | 9/20/2018 | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 2
[9 empty] | c) | - | c) | 10/12/2018 | g) | - | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  |  | Const. of Covered Court Bleacher, Katipunan, |  | Bleacher |  | Barangay | a) | 500000 | a) | 12/19/17 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Completed as per physical accomplishment. Financial documents still on process | 2
|  |  |  | Panabo CIty |  |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 2
[9 empty] | c) | - | c) | - | g) | 6/10/2018 | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  |  | Const. of Brgy. Gymnasium, Mabunao, |  | Gym |  | Barangay | a) | 500000 | a) | 12/28/17 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Completed as per physical accomplishment. Financial documents still on process | 2
|  |  |  | Panabo CIty |  |  |  |  | b) | - | b) | 3/11/2019 | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 2
[9 empty] | c) | - | c) | 4/10/2019 | g) | 4/10/2019 | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
2
2
|  |  |  | Completion of Footbridge at Prk. 1, Tibungol, |  | Footbridge |  | Barangay | a) | 500000 | a) | 12/28/17 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Completed as per physical accomplishment. Financial documents still on process | 2
|  |  |  | Panabo CIty |  |  |  |  | b) | - | b) | 12/13/2018 | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 2
[9 empty] | c) | - | c) | 2/11/2019 | g) | 2/11/2019 | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  |  | Const. of Multi-Purpose Bldg., Lower Panaga, |  | Bldg. |  | Barangay | a) | 500000 | a) | 12/07/17 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Completed as per physical accomplishment. Financial documents still on process | 2
|  |  |  | Panabo CIty |  |  |  |  | b) | - | b) | 10/1/2018 | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 2
[9 empty] | c) | - | c) | 11/30/2018 | g) | 11/30/2018 | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  |  | Completion of Bleachers @ Brgy. GYM, |  | Gym |  | Barangay | a) | 500000 | a) | 12/28/17 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Completed as per physical accomplishment. Financial documents still on process | 2
|  |  |  | Sindaton, Panabo City |  |  |  |  | b) | - | b) | 10/1/2018 | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 2
[9 empty] | c) | - | c) | 10/31/2018 | g) | 10/31/2018 | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  |  | Const. of Concrete Pavement, |  | Pavement |  | Barangay | a) | 500000 | a) | 12/07/17 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Completed as per physical accomplishment. Financial documents still on process | 2
|  |  |  | San Vicente, Panabo City |  |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 2
[9 empty] | c) | - | c) | - | g) | 5/15/2019 | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  |  | Const. of Stage @ Prk. 3, Tagpore, |  | Stage |  | Barangay | a) | 500000 | a) | 12/19/17 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Completed as per physical accomplishment. Financial documents still on process | 2
|  |  |  | Panabo City |  |  |  |  | b) | - | b) | 7/18/2018 | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 2
[9 empty] | c) | - | c) | 9/14/2018 | g) | 9/14/2018 | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  |  | Const. of Bleachres @ Brgy. Manay GYM, |  | Gym |  | Barangay | a) | 500000 | a) | 12/19/17 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Completed as per physical accomplishment. Financial documents still on process | 2
|  |  |  | Manay, Panabo City |  |  |  |  | b) | - | b) | 12/6/2018 | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 2
[9 empty] | c) | - | c) | 12/15/2018 | g) | 12/15/2018 | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  |  | Const. of MP Bldg. w/ Electrical installation, |  | Bldg. |  | Barangay | a) | 500000 | a) | 01/31/18 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Completed as per physical accomplishment. Financial documents still on process | 2
|  |  |  | San Roque, Panabo City |  |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 2
[9 empty] | c) | - | c) | - | g) | 06/10/2019 | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
AC
|  |  | STO TOMAS | [20 empty] | AC
|  |  |  | Const. of Violence Against Women and |  | Bldg. |  | Barangay | a) | 500000 | a) | 12/07/17 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Completed as per physical accomplishment. Financial documents still on process | 2
|  |  |  | Children Center, Tulalian |  |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 2
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | Const./Rehab./Comp. of Various Gov't. Bldgs. |  |  | Bldg. | - | Admin | a) | 9,000,000.00 | [12 empty] | Investigation/Inspection of priority projects | 2
|  |  | Struct., Fac. (Provincewide) | [5 empty] | b) | Foronda/Ababon | [13 empty] | 2
[9 empty] | c) | PEO | [13 empty] | 2
[9 empty] | d) | - | [13 empty] | 2
|  |  |  | Repair/Rehab. Of PEO Building |  | Bldg. |  | Admin | a) | 1,800,000.00 | a) | 07/31/18 | e) | - | a) | 1,800,000.00 | a) | 62.23% | c) | 100% | a) | 5 | Completed based on POW. Financial Documents on process | 1
|  |  |  | (Motorpool),Mankilam, Tagum City |  |  |  |  | b) | Chua | b) | 03/04/19 | f) | - | b) | 1,800,000.00 | b) | - | d) | 37.77% | b) | 105 |  | 1
[9 empty] | c) | PEO | c) | 08/10/19 | g) | - | c) | 1481510.07 | [7 empty] | 1
[9 empty] | d) | 160 CD | d) | - | [11 empty] | 1
|  |  |  | Construction of BSP Building Extension |  | Bldg. |  | Admin | a) | 500000 | a) | 08/21/18 | e) | 79 CD | a) | 500000 | a) | 100% | c) | 100% | a) | 6 | Completed | 1
|  |  |  | Mankilam, Tagum City |  |  |  |  | b) | Quirante | b) | 01/16/19 | f) | 15 CD | b) | 500000 | b) | - | d) | - | b) | 180 |  | 1
[9 empty] | c) | PEO | c) | 03/16/19 | g) | 06/21/19 | c) | 434,145.73 | [7 empty] | 1
[9 empty] | d) | 75 CD | d) | 03/31/19 | [11 empty] | 1
|  |  |  | Repair/Rehab. Of PEO Building |  | Bldg. | 96 sq.m | Admin | a) | 1,073,124.00 | a) | 06/11/18 | e) | - | a) | 1,073,124.00 | a) | 100.00% | c) | 100.00% | a) | 14 | Completed as per physical accomplishment. | 1
|  |  |  | (PEO Warehouse),Mankilam, |  |  |  |  | b) | Chua | b) | 12/03/18 | f) | - | b) | 1,073,124.00 | b) | - | d) | - | b) | 420 | Financial documents still on process | 1
|  |  |  | Tagum City |  |  |  |  | c) | PEO | c) | 06/15/19 | g) | 05/15/19 | c) | 1,042,097.32 | [7 empty] | 1
[9 empty] | d) | 189 CD | d) | - | [11 empty] | 1
|  |  |  | Construction of GSP Building Extension |  | Bldg. |  | Admin | a) | 500,000.00 | a) | 07/20/18 | e) | 44 cd | a) | 500,000.00 | a) | 100.00% | c) | 100.00% | a) | 8 | Completed as per physical accomplishment. | 1
|  |  |  | Mankilam, Tagum City |  |  |  |  | b) | Quirante | b) | 01/03/19 | f) | 15 CD | b) | 500,000.00 | b) | - | d) | - | b) | 240 | Financial documents still on process | 1
[9 empty] | c) | PEO | c) | 03/03/19 | g) | 05/03/19 | c) | 447,660.03 | [7 empty] | 1
[9 empty] | d) | 75 CD | d) | 03/17/19 | [11 empty] | 1
4 |  |  | 2.3 | Improvement of Garciaville Day Care |  | Bldg. |  | Admin | a) | 330,000.00 | a) | 11/06/18 | e) | - | a) | 330,000.00 | a) |  | c) | 100% | a) | 3 | Completed based on POW. Financial Documents on process | 1
4 |  | 11 |  | Center, Mankilam, Tagum City |  |  |  |  | b) | - | b) | 09/02/19 | f) | - | b) | 330,000.00 | b) | - | d) |  | b) | 90 |  | 1
4 | [8 empty] | c) | PEO | c) | 10/11/19 | g) | - | c) | - | [7 empty] | 1
4 | [8 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | Rural Electrification (Provincewide) |  |  | Elect. |  | Admin | a) | 5000000 | [12 empty] | See projects listed below | AC
[9 empty] | b) | Foronda/Misa | [13 empty] | AC
[9 empty] | c) | Admin | [13 empty] | AC
[9 empty] | d) | - | [13 empty] | AC
|  |  |  | Inst. Of distribution transformation & |  | Elect. |  | Admin | a) | 500,000.00 | a) | 06/27/18 | e) | - | a) | 500,000.00 | a) | 100.00% | c) | 100.00% | a) | - | Completed as per physical accomplishment. | 1
|  |  |  | Electrical Wirings, 10th Infantry |  |  |  |  | b) | Lu | b) | 12/17/18 | f) | 15 WD | b) | 500,000.00 | b) | - | d) | - | b) | - | Financial documents still on process | 1
|  |  |  | (Agila) Division PA, Tuburan Mawab |  |  |  |  | c) | PEO | c) | 01/15/18 | g) | 01/31/19 | c) | - | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
4 |  | F. | SDH IGCS - CONST. IN PROGRESS - BLGS. CY 2017 | [20 empty] | 2
4 |  |  | 1 | Construction Perimeter Fence Ph.II (Hospital |  | Fence |  | Admin | a) | 1,305,000.00 | a) | 11/10/17 | e) | 392 | a) | 1,305,000.00 | a) | 100% | c) | 100% | a) | 4 | Completed based on POW. Financial Documents on process | 2
4 |  |  |  | Compound) Samal District Hospital, IGCS |  |  |  |  | b) | Porras | b) | 03/12/18 | f) | 45 | b) | 1,305,000.00 | b) | - | d) | 1% | b) | 30 |  | 2
4 | [8 empty] | c) | PEO | c) | 06/19/18 | g) | - | c) | 958,597.98 | [7 empty] | 2
4 | [8 empty] | d) | - | d) | [12 empty] | 2
4 |  | C.5 | LDRRM - Trust Fund | [20 empty] | AC
4 |  | 5 | 1. Construction of Slope Protection and Concrete Pavement along Sta. Fe Mambing Road Section |  |  | Slope |  | Admin | a) | 1,853,000.00 | a) | 11/28/18 | e) |  | a) | 1,853,000.00 | a) | 100% | c) | 100% | a) | 16 | Completed based on POW. Financial Documents on process | 1
4 | [8 empty] | b) | Gone | b) | 12/03/18 | f) | 108 CD | b) | 1,853,000.00 | b) | - | d) |  | b) | 144 |  | 1
4 | [8 empty] | c) | PEO | c) | 02/28/19 | g) | 10/30/2019 | c) | 742252.72 | [7 empty] | 1
4 | [8 empty] | d) | 86 CD | d) | 06/15/2019 | [11 empty] | 1
4 |  | 1 | 3. Rehab. Of Canatan Bridge Slope Protection |  |  | Slope | 395 sq.m. | Contract | a) | 9200000 | a) | 06/20/2018 | e) | - | a) | 9200000 | a) | 100% | c) | 100% | a) | - | Completed | 1
4 |  |  | Brgy. Canatan, Asuncion | [5 empty] | b) | Aclaracion | b) | 02/11/2019 | f) | 35 CD | b) | 9200000 | b) | 100% | d) | 0% | b) | - |  | 1
4 | [8 empty] | c) | J-One Builders | c) | 04/12/2019 | g) | 05/31/2019 | c) | 7222021.59 | [7 empty] | 1
4 | [8 empty] | d) | 60 CD | d) | 05/01/2019 | [11 empty] | 1
4 |  | 5 | 5. Const. of Cabidianan Bridge Slope Protection, Brgy. Cabidianan, New Corella |  |  | Slope |  | Admin | a) | 3590000 | a) | 07/18/18 | e) | - | a) | 3590000 | a) | 100% | c) | 100% | a) | 8 | Completed based on POW. Financial Documents on process | 1
4 | [8 empty] | b) | Gone | b) | 6/17/19 | f) | - | b) | 3590000 | b) |  | d) |  | b) | 80 |  | 1
4 | [8 empty] | c) | PEO | c) | 8/20/19 | g) | - | c) | 1929823.4 | [7 empty] | 1
4 | [8 empty] | d) | 65 CD | d) | - | [11 empty] | 1
|  | D. | SEF(Special Education Fund)-SUPPLEMENTAL BUDGET # 1 CY 2017 | [20 empty] | AC
|  |  | 1. Const./Impv't./Compl. Of School Bldgs., Struc. & Fac. |  |  | Bldgs. |  | Admin | a) | 3,300,000.00 | [12 empty] | See projects listed below | AC
[9 empty] | b) | Foronda | [13 empty] | AC
[9 empty] | c) | PEO | [13 empty] | AC
[9 empty] | d) | - | [13 empty] | AC
4 |  | 8 | 1.1 | Construction of 1 unit School Building |  | Bldg. |  | Admin | a) | 1100000 | a) | 02/19/18 | e) | - | a) | 1100000 | a) | 100 | c) | 100 | a) | 6 | Completed based on POW. Financial Documents on process | 1
4 |  |  |  | Lumabag, Talaingod |  |  |  |  | b) | Dadula | b) | 03/20/19 | f) | 27 CD | b) | 1100000 | b) |  | d) |  | b) | 30 |  | 1
4 | [8 empty] | c) | PEO | c) | 05/19/19 | g) | 06/30/2019 | c) | 595230.5 | [7 empty] | 1
4 | [8 empty] | d) | 60 CD | d) | - | [11 empty] | 1
|  | E. Supplemental Budget No. 5 CY 2015 | [21 empty] | AC
|  |  | Purchased, Const & Impvt of Govt Facilities (8918) | [20 empty] | AC
|  |  | a. Const/Coml/Impvt of Various Govt. Bldgs Structures | [20 empty] | AC
|  |  | & Facilities | [20 empty] | AC
2
|  |  | Impv't. of Brgy. Hall at |  |  | Bldg. |  | Admin | a) | 500000 | a) | 03/31/17 | e) | 182 CD | a) | 500000 | a) | 100% | c) | 100% | a) | 10 | Completed 7/17/2019 as per physical accomplishment. Financial Documents still on process | 2
|  |  | Brgy. Tagpopongan, Babak Dist., IGCS | [5 empty] | b) | Andoy | b) | 09/17/18 | f) | - | b) | 500000 | b) | - | d) | 0% | b) | 55 |  | 2
[9 empty] | c) | PEO | c) | 12/25/18 | g) | 7/14/2019 | c) | 356,352.61 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | Completion of Multi-Purpose Building |  |  | Bldg. |  | Admin | a) | 500000 | a) | 03/08/16 | e) | - | a) | 500000 | a) | 100% | c) | 100% | a) | 8 | Completed 5/31/2019 as per physical accomplishment. Financial documents still on process | 2
|  |  | Brgy. San Jose, Sto. Tomas | [5 empty] | b) | Roque | b) | 02/14/17 | f) | - | b) | 500000 | b) | - | d) | - | b) | 80 |  | 2
[9 empty] | c) | PEO | c) | 04/27/17 | g) | 15/07/2019 | c) | 484,175.83 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | Completion of Covered Court 1 Bay |  |  | Court |  | Admin | a) | 500000 | a) | 03/07/16 | e) | - | a) | 500000 | a) | 100.00% | c) | 100% | a) | 8 | Completed 7/5/2019 as per physical accomplishment. Financial documents still on process | 2
|  |  | Brgy. Lunga-og, Sto. Tomas | [5 empty] | b) | Roque | b) | 02/14/17 | f) | 54 CD | b) | 500000 | b) | - | d) | - | b) | 80 |  | 2
[9 empty] | c) | PEO | c) | 06/20/17 | g) | - | c) | 473,542.40 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  | D. | LDRRM - Trust Fund 2018 | [20 empty] | AC
|  |  |  | Const. of Single Barrel 4.0m x 4.0m RCDG, Mangalcal, Carmen |  | RCDG |  | Admin | a) | 1,822,000.00 | a) | CY 2013 | e) | - | a) | 1,822,000.00 | a) | 100.00% | c) | 100.00% | a) | 12 | Completed as per physical accomplishment. | 2
|  |  | 1 | [5 empty] | b) | Foronda | b) | 11/05/18 | f) | 92 CD | b) | 1,822,000.00 | b) | - | d) | - | b) | 72 | Financial documents still on process | 2
[9 empty] | c) | PEO | c) | 2019-01-03 | g) | 04/06/19 | c) | 1,822,000.00 | [7 empty] | 2
[9 empty] | d) | 65 CD | d) | 04/06/19 | [11 empty] | 2
2
|  |  |  | Rehabilitation of Protection Dike Along Poblacion-Prk. 8, Dujali, Brgy. Tanglaw, B.E. Dujali |  | Dike |  | Admin | a) | 1,180,000.00 | a) | CY 2013 | e) | - | a) | 1,180,000.00 | a) | 100.00% | c) | 100.00% | a) | 5 | Completed as per physical accomplishment. | 2
|  |  | 2 | [5 empty] | b) | Toquero | b) | 02/15/19 | f) | - | b) | 1,180,000.00 | b) | - | d) | - | b) | 50 | Financial documents still on process | 2
[9 empty] | c) | PEO | c) | 04/02/19 | g) | - | c) | 74,338.28 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  |  | Rehab. Of New Camiling-alejal-Lower Magsaysay Provincial Road |  | RCDG |  | Admin | a) | 1,428,917.00 | a) | 08/02/18 | e) | - | a) | 1,428,917.00 | a) | 100.00% | c) | 100.00% | a) | 5 | Completed as per physical accomplishment. | 2
|  |  | 3 | [5 empty] | b) | Toquero | b) | 12/01/18 | f) | - | b) | 1,428,917.00 | b) | - | d) | - | b) | 50 | Financial documents still on process | 2
[9 empty] | c) | PEO | c) | 01/01/19 | g) | - | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
AC
|  |  | 20% Development Fund 2018 | [20 empty] | AC
[6 empty] | Road Maintenance | KM | [16 empty] | AC
| Road ID |  | Repair & Maint. Of Various Prov'l. Roads and Bridges CY 2018 |  |  |  | 525.3 | Admin | a) | 27893753 | a) | 01/01/18 | e) | - | a) | 27893753 | a) | 100.00% | c) | 100% | a) | 32 | Completed as per physical accomplishment. | AC
[8 empty] | /CBRMC | b) | Matuguinas | b) | 01/01/18 | f) | - | b) | 27893753 | b) | - | d) | - | b) | 2044 | Financial documents still on process | AC
| 11DAN | [7 empty] | c) | PEO//CBRMC | c) | 2018-12-31 | g) | 2018-12-31 | c) | 15,163,482.97 | [6 empty] | See list of Provincial Roads | AC
[9 empty] | d) | - | d) | - | [11 empty] | AC
| 11 |  | Cebulano-Mangalcal Road |  |  | Road | 4.17 | Admin | a) | 239434.4 | a) | 01/01/18 | e) | - | a) | 239434.4 | a) | 100.00% | c) | 100% | a) | 10 | Completed as per physical accomplishment. | 2
| DAN | [7 empty] | b) | Gamad/Maligro | b) | 01/08/18 | f) | - | b) | 239434.4 | b) | - | d) | - | b) | 30 | Financial documents still on process | 2
| 073 | [7 empty] | c) | PEO | c) | 2018-12-31 | g) | 2018-12-31 | c) | 236,699.57 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Cebulano-Mangalcal Road |  |  | Road | 4.17 | CBRMC | a) | 178024.03 | a) | 01/01/18 | e) | - | a) | 178024.03 | a) | 100.00% | c) | 100% | a) | 2 | Completed as per physical accomplishment. | 2
| DAN | [7 empty] | b) | Gamad/Maligro | b) | 2018-05-03 | f) | - | b) | 178024.03 | b) | - | d) | - | b) | 4 | Financial documents still on process | 2
| 073 | [7 empty] | c) | Brgy. Mangalcal Women's Homebased Workers Association | c) | 2019-02-03 | g) | 2019-02-03 | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Tubod-Basa-Mangalcal Road |  |  | Road | 3.93 | Admin | a) | 217304.13 | a) | 01/01/18 | e) | - | a) | 217304.13 | a) | 100.00% | c) | 100% | a) | 1 | Completed as per physical accomplishment. | 2
| DAN | [7 empty] | b) | Gamad/Maligro | b) | 01/08/18 | f) | - | b) | 217304.13 | b) | - | d) | - | b) | 3 | Financial documents still on process | 2
| 074 | [7 empty] | c) | PEO | c) | 2018-12-31 | g) | 2018-12-31 | c) | 212,336.25 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Basa-Tubod Road |  |  | Road | 1.56 | Admin | a) | 153509.11 | a) | 01/01/18 | e) | - | a) | 153509.11 | a) | 100.00% | c) | 100% | a) | 12 | Completed as per physical accomplishment. | 2
| DAN | [7 empty] | b) | Gamad/Maligro | b) | 01/04/18 | f) | - | b) | 153509.11 | b) | - | d) | - | b) | 36 | Financial documents still on process | 2
| 076 | [7 empty] | c) | PEO | c) | 2018-12-31 | g) | 2018-12-31 | c) | 153,509.11 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Tubod-Pilar Road |  |  | Road | 1.55 | Admin | a) | 140507.18 | a) | 01/01/18 | e) | - | a) | 140507.18 | a) | 100.00% | c) | 100% | a) | 12 | Completed as per physical accomplishment. | 2
| DAN | [7 empty] | b) | Gamad/Maligro | b) | 02/12/18 | f) | - | b) | 140507.18 | b) | - | d) | - | b) | 36 | Financial documents still on process | 2
| 077 | [7 empty] | c) | PEO | c) | 2018-12-31 | g) | 2018-12-31 | c) | 140,507.18 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Upper Mangalcal-Lower Mangalcal |  |  | Road | 2.43 | Admin | a) | 149291.32 | a) | 01/01/18 | e) | - | a) | 149291.32 | a) | 100.00% | c) | 100% | a) | 10 | Completed as per physical accomplishment. | 2
| DAN |  | Road | [5 empty] | b) | Gamad/Maligro | b) | 02/12/18 | f) | - | b) | 149291.32 | b) | - | d) | - | b) | 30 | Financial documents still on process | 2
| 078 | [7 empty] | c) | PEO | c) | 2018-12-31 | g) | 2018-12-31 | c) | 143,316.91 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Upper Mangalcal-Lower Mangalcal |  |  | Road | 2.43 | CBRMC | a) | 89828.64 | a) | 01/01/18 | e) | - | a) | 89828.64 | a) | 100.00% | c) | 100% | a) | 2 | Completed as per physical accomplishment. | 2
| DAN |  | Road | [5 empty] | b) | Gamad/Maligro | b) | 2018-05-03 | f) | - | b) | 89828.64 | b) | - | d) | - | b) | 4 | Financial documents still on process | 2
| 078 | [7 empty] | c) | Brgy. Mangalcal Women's Homebased Workers Association | c) | 2019-02-03 | g) | 2019-02-03 | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Cebulano-Loceta Road |  |  | Road | 1.87 | Admin | a) | 166206.3 | a) | 01/01/18 | e) | - | a) | 166206.3 | a) | 100.00% | c) | 100% | a) | 10 | Completed as per physical accomplishment. | 2
| DAN | [7 empty] | b) | Gamad/Maligro | b) | 01/04/18 | f) | - | b) | 166206.3 | b) | - | d) | - | b) | 30 | Financial documents still on process | 2
| 079 | [7 empty] | c) | PEO | c) | 2018-12-31 | g) | 2018-12-31 | c) | 165,088.85 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Loceta-Lower Mangalcal Road |  |  | Road | 2.07 | Admin | a) | 121918.96 | a) | 01/01/18 | e) | - | a) | 121918.96 | a) | 100.00% | c) | 100% | a) | 12 | Completed as per physical accomplishment. | 2
| DAN | [7 empty] | b) | Gamad/Maligro | b) | 01/04/18 | f) | - | b) | 121918.96 | b) | - | d) | - | b) | 36 | Financial documents still on process | 2
| 080 | [7 empty] | c) | PEO | c) | 2018-12-31 | g) | 2018-12-31 | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Lower Asuncion-Upper Asuncion Road |  |  | Road | 1.02 | Admin | a) | 90657.98 | a) | 01/01/18 | e) | - | a) | 90657.98 | a) | 100.00% | c) | 100% | a) | 12 | Completed as per physical accomplishment. | 2
| DAN | [7 empty] | b) | Gamad/Maligro | b) | 01/04/18 | f) | - | b) | 90657.98 | b) | - | d) | - | b) | 36 | Financial documents still on process | 2
| 081 | [7 empty] | c) | PEO | c) | 2018-12-31 | g) | 2018-12-31 | c) | 90,657.98 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Jct.Highway-Carmen-Mangalcal-Tubod |  |  | Road | 11.34 | Admin | a) | 888986.6 | a) | 01/01/18 | e) | - | a) | 888986.6 | a) | 100.00% | c) | 100% | a) | 8 | Completed as per physical accomplishment. | 2
| DAN |  | Road | [5 empty] | b) | Gamad/Maligro | b) | 01/04/18 | f) | - | b) | 888986.6 | b) | - | d) | - | b) | 40 | Financial documents still on process | 2
| 082 | [7 empty] | c) | PEO | c) | 2018-12-31 | g) | 2018-12-31 | c) | 698,903.80 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Jct.Highway-Sto.Niño-La Paz-San |  |  | Road | 6.08 | Admin | a) | 458781.46 | a) | 01/01/18 | e) | - | a) | 458781.46 | a) | 100.00% | c) | 100% | a) | 8 | Completed as per physical accomplishment. | 2
| DAN |  | Vicente Road | [5 empty] | b) | Gamad/Maligro | b) | 01/03/18 | f) | - | b) | 458781.46 | b) | - | d) | - | b) | 40 | Financial documents still on process | 2
| 083 | [7 empty] | c) | PEO | c) | 2018-12-31 | g) | 2018-12-31 | c) | 458,781.46 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Jct.Highway-Sto.Niño-Kabankalan- |  |  | Road | 2.13 | Admin | a) | 127936.58 | a) | 01/01/18 | e) | - | a) | 127936.58 | a) | 100.00% | c) | 100% | a) | 10 | Completed as per physical accomplishment. | 2
| DAN |  | La Paz Road | [5 empty] | b) | Gamad/Maligro | b) | 01/08/18 | f) | - | b) | 127936.58 | b) | - | d) | - | b) | 50 | Financial documents still on process | 2
| 084 | [7 empty] | c) | PEO | c) | 2018-12-31 | g) | 2018-12-31 | c) | 15,535.28 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Jct.Highway-Sto.Niño-Kabankalan- |  |  | Road | 2.13 | CBRMC | a) | 81662.4 | a) | 01/01/18 | e) | - | a) | 81662.4 | a) | 100.00% | c) | 100% | a) | 1 | Completed as per physical accomplishment. | 2
| DAN |  | La Paz Road | [5 empty] | b) | Gamad/Maligro | b) | 01/08/18 | f) | - | b) | 81662.4 | b) | - | d) | - | b) | 1 | Financial documents still on process | 2
| 084 | [7 empty] | c) | Taba Coconut Farmers Association | c) | 2018-12-31 | g) | 2018-12-31 | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Ising-Sto.Niño Road |  |  | Road | 2.07 | Admin | a) | 107208.18 | a) | 01/01/18 | e) | - | a) | 107208.18 | a) | 100.00% | c) | 100% | a) | 12 | Completed as per physical accomplishment. | 2
| DAN | [7 empty] | b) | Gamad/Maligro | b) | 01/03/18 | f) | - | b) | 107208.18 | b) | - | d) | - | b) | 36 | Financial documents still on process | 2
| 085 | [7 empty] | c) | PEO | c) | 2018-12-31 | g) | 2018-12-31 | c) | 107,151.22 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Ising-Sto.Niño Road |  |  | Road | 2.07 | CBRMC | a) | 101261.38 | a) | 01/01/18 | e) | - | a) | 101261.38 | a) | 100.00% | c) | 100% | a) | 1 | Completed as per physical accomplishment. | 2
| DAN | [7 empty] | b) | Gamad/Maligro | b) | 06/22/18 | f) | - | b) | 101261.38 | b) | - | d) | - | b) | 1 | Financial documents still on process | 2
| 085 | [7 empty] | c) | Taba Coconut Farmers Association | c) | 04/21/19 | g) | 12/31/18 | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Ising-Sadpodon-Taba-Diladila Road |  |  | Road | 5.68 | Admin | a) | 263421.11 | a) | 01/01/18 | e) | - | a) | 263421.11 | a) | 100.00% | c) | 100% | a) | 8 | Completed as per physical accomplishment. | 2
| DAN | [7 empty] | b) | Gamad/Maligro | b) | 01/03/18 | f) | - | b) | 263421.11 | b) | - | d) | - | b) | 24 | Financial documents still on process | 2
| 086 | [7 empty] | c) | PEO | c) | 2018-12-31 | g) | 2018-12-31 | c) | 261,318.46 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Ising-Sadpodon-Taba-Diladila Road |  |  | Road | 5.68 | CBRMC | a) | 175301.95 | a) | 01/01/18 | e) | - | a) | 175301.95 | a) | 100.00% | c) | 100% | a) | 2 | Completed as per physical accomplishment. | 2
| DAN | [7 empty] | b) | Gamad/Maligro | b) | 04/26/18 | f) | - | b) | 175301.95 | b) | - | d) | - | b) | 6 | Financial documents still on process | 2
| 086 | [7 empty] | c) | Taba Coconut Farmers Association | c) | 2019-01-26 | g) | 12/31/18 | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Tuganay-Taba Road |  |  | Road | 4.27 | CBRMC | a) | 140549.33 | a) | 01/01/18 | e) | - | a) | 140549.33 | a) | 100.00% | c) | 100% | a) | 2 | Completed as per physical accomplishment. | 2
| DAN | [7 empty] | b) | Gamad/Maligro | b) | 04/26/18 | f) | - | b) | 140549.33 | b) | - | d) | - | b) | 4 | Financial documents still on process | 2
| 087 | [7 empty] | c) | Taba Coconut Farmers Association | c) | 2019-01-26 | g) | 12/31/18 | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Jct. Highway-Tuganay-Taba Road |  |  | Road | 4.4 | Admin | a) | 137256.7 | a) | 01/01/18 | e) | - | a) | 137256.7 | a) | 100.00% | c) | 100% | a) | 8 | Completed as per physical accomplishment. | 2
| DAN | [7 empty] | b) | Gamad/Maligro | b) | 02/12/18 | f) | - | b) | 137256.7 | b) | - | d) | - | b) | 16 | Financial documents still on process | 2
| 088 | [7 empty] | c) | PEO | c) | 2018-12-31 | g) | 2018-12-31 | c) | 128,871.12 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Jct.Highway-Ising-Magsaysay Road |  |  | Road | 10.84 | Admin | a) | 736262 | a) | 01/01/18 | e) | - | a) | 736262 | a) | 100.00% | c) | 100% | a) | 8 | Completed as per physical accomplishment. | 2
| DAN | [7 empty] | b) | Gamad/Maligro | b) | 02/12/18 | f) | - | b) | 736262 | b) | - | d) | - | b) | 24 | Financial documents still on process | 2
| 089 | [7 empty] | c) | PEO | c) | 2018-12-31 | g) | 2018-12-31 | c) | 735,525.71 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Jct.Highway-Ising-Magsaysay Road |  |  | Road | 10.84 | CBRMC | a) | 222121.73 | a) | 01/01/18 | e) | - | a) | 222121.73 | a) | 100.00% | c) | 100% | a) | - | Completed as per physical accomplishment. | 2
| DAN | [7 empty] | b) | Gamad/Maligro | b) | 02/12/18 | f) | - | b) | 222121.73 | b) | - | d) | - | b) | - | Financial documents still on process | 2
| 089 | [7 empty] | c) | School on the Air Integrated Farmers Association | c) | 2018-12-31 | g) | 2018-12-31 | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Maligaya-New Camiling Road |  |  | Road | 2.13 | Admin | a) | 208418.14 | a) | 01/01/18 | e) | - | a) | 208418.14 | a) | 100.00% | c) | 100% | a) | 10 | Completed as per physical accomplishment. | 2
| DAN | [7 empty] | b) | Gamad/Maligro | b) | 02/12/18 | f) | - | b) | 208418.14 | b) | - | d) | - | b) | 12 | Financial documents still on process | 2
| 090 | [7 empty] | c) | PEO | c) | 2018-12-31 | g) | 2018-12-31 | c) | 194,652.04 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | New Camiling-Alejal-Lower Magsaysay |  |  | Road | 6.73 | Admin | a) | 393838.9 | a) | 01/01/18 | e) | - | a) | 393838.9 | a) | 100.00% | c) | 100% | a) | 12 | Completed as per physical accomplishment. | 2
| DAN |  | Road | [5 empty] | b) | Gamad/Maligro | b) | 02/12/18 | f) | - | b) | 393838.9 | b) | - | d) | - | b) | 48 | Financial documents still on process | 2
| 091 | [7 empty] | c) | PEO | c) | 2018-12-31 | g) | 2018-12-31 | c) | 236,036.98 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | New Camiling-Alejal-Lower Magsaysay |  |  | Road | 6.73 | CBRMC | a) | 209055.74 | a) | 01/01/18 | e) | - | a) | 209055.74 | a) | 100.00% | c) | 100% | a) | 2 | Completed as per physical accomplishment. | 2
| DAN |  | Road | [5 empty] | b) | Gamad/Maligro | b) | 05/04/18 | f) | - | b) | 209055.74 | b) | - | d) | - | b) | 2 | Financial documents still on process | 2
| 091 | [7 empty] | c) | School on the Air Integrated Farmers Association | c) | 02/04/19 | g) | 12/31/18 | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Anahaw-Maligaya Road |  |  | Road | 4.8 | Admin | a) | 328333.3 | a) | 01/01/18 | e) | - | a) | 328333.3 | a) | 100.00% | c) | 100% | a) |  | Completed as per physical accomplishment. | 2
| DAN | [7 empty] | b) | Gamad/Maligro | b) | 01/08/18 | f) | - | b) | 328333.3 | b) | - | d) | - | b) |  | Financial documents still on process | 2
| 093 | [7 empty] | c) | PEO | c) | 2018-12-31 | g) | 2018-12-31 | c) | 154,062.27 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Jct.Highway-Tuganay-Anibongan Road |  |  | Road | 3.66 | Admin | a) | 192897.9 | a) | 01/01/18 | e) | - | a) | 192897.9 | a) | 100.00% | c) | 100% | a) | 10 | Completed as per physical accomplishment. | 2
| DAN | [7 empty] | b) | Gamad/Maligro | b) | 01/04/18 | f) | - | b) | 192897.9 | b) | - | d) | - | b) | 20 | Financial documents still on process | 2
| 094 | [7 empty] | c) | PEO | c) | 2018-12-31 | g) | 2018-12-31 | c) | 176,119.23 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Jct.Highway-Tuganay-Anibongan Road |  |  | Road | 3.66 | CBRMC | a) | 97994.88 | a) | 01/01/18 | e) | - | a) | 97994.88 | a) | 100.00% | c) | 100% | a) |  | Completed as per physical accomplishment. | 2
| DAN | [7 empty] | b) | Gamad/Maligro | b) | 05/04/18 | f) | - | b) | 97994.88 | b) | - | d) | - | b) |  | Financial documents still on process | 2
| 094 | [7 empty] | c) | EZRA | c) | 02/04/19 | g) | 12/31/18 | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Anibongan-Guadalupe Road |  |  | Road | 2.48 | Admin | a) | 144312.93 | a) | 01/01/18 | e) | - | a) | 144312.93 | a) | 100.00% | c) | 100% | a) |  | Completed as per physical accomplishment. | 2
| DAN | [7 empty] | b) | Gamad/Maligro | b) | 01/04/18 | f) | - | b) | 144312.93 | b) | - | d) | - | b) |  | Financial documents still on process | 2
| 095 | [7 empty] | c) | PEO | c) | 2018-12-31 | g) | 2018-12-31 | c) | 113,396.19 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Anibongan-Guadalupe Road |  |  | Road | 2.48 | CBRMC | a) | 78395.9 | a) | 01/01/18 | e) | - | a) | 78395.9 | a) | 100.00% | c) | 100% | a) | - | Completed as per physical accomplishment. | 2
| DAN | [7 empty] | b) | Gamad/Maligro | b) | 05/04/18 | f) | - | b) | 78395.9 | b) | - | d) | - | b) | - | Financial documents still on process | 2
| 095 | [7 empty] | c) | - | c) | 02/04/19 | g) | 12/31/18 | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Tuganay-Anibongan-San Isidro Road |  |  | Road | 7.22 | Admin | a) | 219455.18 | a) | 01/01/18 | e) | - | a) | 219455.18 | a) | 100.00% | c) | 100% | a) | 12 | Completed as per physical accomplishment. | 2
| DAN | [7 empty] | b) | Gamad/Maligro | b) | 01/04/18 | f) | - | b) | 219455.18 | b) | - | d) | - | b) | 24 | Financial documents still on process | 2
| 096 | [7 empty] | c) | PEO | c) | 2018-12-31 | g) | 2018-12-31 | c) | 209,407.75 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Jct.Anibongan P2,7,5-San Isidro Road |  |  | Road | 3.14 | Admin | a) | 110524.22 | a) | 01/01/18 | e) | - | a) | 110524.22 | a) | 100.00% | c) | 100% | a) | 12 | Completed as per physical accomplishment. | 2
| DAN | [7 empty] | b) | Gamad/Maligro | b) | 01/04/18 | f) | - | b) | 110524.22 | b) | - | d) | - | b) | 24 | Financial documents still on process | 2
| 097 | [7 empty] | c) | PEO | c) | 2018-12-31 | g) | 2018-12-31 | c) | 80,736.78 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Anibongan-Salvacion-Cabay-angan |  |  | Road | 6.93 | Admin | a) | 517149.14 | a) | 01/01/18 | e) | - | a) | 517149.14 | a) | 100.00% | c) | 100% | a) | 10 | Completed as per physical accomplishment. | 2
| DAN |  | Road | [5 empty] | b) | Gamad/Maligro | b) | 02/12/18 | f) | - | b) | 517149.14 | b) | - | d) | - | b) | 20 | Financial documents still on process | 2
| 098 | [7 empty] | c) | PEO | c) | 2018-12-31 | g) | 2018-12-31 | c) | 358,470.30 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Mabaus-Cabay-angan Road |  |  | Road | 3.2 | Admin | a) | 284417.14 | a) | 01/01/18 | e) | - | a) | 284417.14 | a) | 100.00% | c) | 100% | a) |  | Completed as per physical accomplishment. | 2
| DAN | [7 empty] | b) | Gamad/Maligro | b) | 01/08/18 | f) | - | b) | 284417.14 | b) | - | d) | - | b) |  | Financial documents still on process | 2
| 099 | [7 empty] | c) | PEO | c) | 2018-12-31 | g) | 2018-12-31 | c) | 277,092.31 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Mabaus-Salvacion Road |  |  | Road | 1.38 | Admin | a) | 105132.79 | a) | 01/01/18 | e) | - | a) | 105132.79 | a) | 100.00% | c) | 100% | a) |  | Completed as per physical accomplishment. | 2
| DAN | [7 empty] | b) | Gamad/Maligro | b) | 02/12/18 | f) | - | b) | 105132.79 | b) | - | d) | - | b) |  | Financial documents still on process | 2
| 100 | [7 empty] | c) | PEO | c) | 2018-12-31 | g) | 2018-12-31 | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Jct.Highway-Guadalupe-Bdry.Tagum |  |  | Road | 7.9 | Admin | a) | 574863.11 | a) | 01/01/18 | e) | - | a) | 574863.11 | a) | 100.00% | c) | 100% | a) | 10 | Completed as per physical accomplishment. | 2
| DAN |  | Road | [5 empty] | b) | Gamad/Maligro | b) | 02/16/18 | f) | - | b) | 574863.11 | b) | - | d) | - | b) | 70 | Financial documents still on process | 2
| 101 | [7 empty] | c) | PEO | c) | 2018-12-31 | g) | 2018-12-31 | c) | 301,160.92 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Dalisay-Mabuhay Road |  |  | Road | 3.25 | Admin | a) | 319810.65 | a) | 01/01/18 | e) | - | a) | 319810.65 | a) | 100.00% | c) | 100% | a) | 8 | Completed as per physical accomplishment. | 2
| DAN | [7 empty] | b) | Gamad/Maligro | b) | 02/12/18 | f) | - | b) | 319810.65 | b) | - | d) | - | b) | 24 | Financial documents still on process | 2
| 102 | [7 empty] | c) | PEO | c) | 2018-12-31 | g) | 2018-12-31 | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Sitio Malaga-Tibulao Road |  |  | Road | 3.22 | Admin | a) | 255531.08 | a) | 01/01/18 | e) | - | a) | 255531.08 | a) | 100.00% | c) | 100% | a) |  | Completed as per physical accomplishment. | 2
| DAN | [7 empty] | b) | Gamad/Maligro | b) | 02/16/18 | f) | - | b) | 255531.08 | b) | - | d) | - | b) |  | Financial documents still on process | 2
| 103 | [7 empty] | c) | PEO | c) | 2018-12-31 | g) | 2018-12-31 | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Dujali-Tanglaw Road |  |  | Road | 3.6 | Admin | a) | 280441.08 | a) | 01/01/18 | e) | - | a) | 280441.08 | a) | 100.00% | c) | 100% | a) |  | Completed as per physical accomplishment. | 2
| DAN | [7 empty] | b) | Gamad/Maligro | b) | 01/08/18 | f) | - | b) | 280441.08 | b) | - | d) | - | b) |  | Financial documents still on process | 2
| 104 | [7 empty] | c) | PEO | c) | 2018-12-31 | g) | 2018-12-31 | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Poblacion Dujali-Prk.8, Dujali Road |  |  | Road | 8.2 | Admin | a) | 577861.87 | a) | 01/01/18 | e) | - | a) | 577861.87 | a) | 100.00% | c) | 100% | a) | 22 | Completed as per physical accomplishment. | 2
| DAN | [7 empty] | b) | Gamad/Maligro | b) | 01/04/18 | f) | - | b) | 577861.87 | b) | - | d) | - | b) | 66 | Financial documents still on process | 2
| 105 | [7 empty] | c) | PEO | c) | 2018-12-31 | g) | 2018-12-31 | c) | 350,004.70 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Poblacion Dujali-Prk.8, Dujali Road |  |  | Road | 8.2 | CBRMC | a) | 226152.24 | a) | 01/01/18 | e) | - | a) | 226152.24 | a) | 100.00% | c) | 100% | a) | - | Completed as per physical accomplishment. | 2
| DAN | [7 empty] | b) | Gamad/Maligro | b) | 01/08/18 | f) | - | b) | 226152.24 | b) | - | d) | - | b) | - | Financial documents still on process | 2
| 105 | [7 empty] | c) | Duajli Pob. Farmers Irrigators | c) | 2018-12-31 | g) | 12/31/18 | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Dujali-San Isidro Road |  |  | Road | 3 | Admin | a) | 349588.79 | a) | 01/01/18 | e) | - | a) | 349588.79 | a) | 100.00% | c) | 100% | a) | 5 | Completed as per physical accomplishment. | 2
| DAN | [7 empty] | b) | Gamad/Maligro | b) | 01/08/18 | f) | - | b) | 349588.79 | b) | - | d) | - | b) | 20 | Financial documents still on process | 2
| 107 | [7 empty] | c) | PEO | c) | 2018-12-31 | g) | 2018-12-31 | c) | 278,882.34 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Dujali-San Isidro Road |  |  | Road | 3 | CBRMC | a) | 71862.91 | a) | 01/01/18 | e) | - | a) | 71862.91 | a) | 100.00% | c) | 100% | a) | - | Completed as per physical accomplishment. | 2
| DAN | [7 empty] | b) | Gamad/Maligro | b) | 10/26/18 | f) | - | b) | 71862.91 | b) | - | d) | - | b) | - | Financial documents still on process | 2
| 107 | [7 empty] | c) |  | c) | 12/31/18 | g) | 12/31/18 | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | New Casay-Bugtong Talisay Road |  |  | Road | 2.18 | Admin | a) | 222469.81 | a) | 01/01/18 | e) | - | a) | 222469.81 | a) | 100.00% | c) | 100% | a) | 8 | Completed as per physical accomplishment. | 2
| DAN | [7 empty] | b) | Gamad/Maligro | b) | 01/08/18 | f) | - | b) | 222469.81 | b) | - | d) | - | b) | 24 | Financial documents still on process | 2
| 108 | [7 empty] | c) | PEO | c) | 2018-12-31 | g) | 2018-12-31 | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Prk.5 RJS-Prk.6 New Casay Road |  |  | Road | 2.73 | Admin | a) | 107717.9 | a) | 01/01/18 | e) | - | a) | 107717.9 | a) | 100.00% | c) | 100% | a) | 12 | Completed as per physical accomplishment. | 2
| DAN | [7 empty] | b) | Gamad/Maligro | b) | 02/12/18 | f) | - | b) | 107717.9 | b) | - | d) | - | b) | 36 | Financial documents still on process | 2
| 109 | [7 empty] | c) | PEO | c) | 2018-12-31 | g) | 2018-12-31 | c) | 106,464.30 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Prk.5 RJS-Prk.6 New Casay Road |  |  | Road | 2.73 | CBRMC | a) | 117593.86 | a) | 01/01/18 | e) | - | a) | 117593.86 | a) | 100.00% | c) | 100% | a) | 2 | Completed as per physical accomplishment. | 2
| DAN | [7 empty] | b) | Gamad/Maligro | b) | 05/07/18 | f) | - | b) | 117593.86 | b) | - | d) | - | b) | 2 | Financial documents still on process | 2
| 109 | [7 empty] | c) | MANCIIA | c) | 02/07/19 | g) | 12/31/18 | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Cabay-angan-Esperanza Road |  |  | Road | 5.37 | Admin | a) | 537948.48 | a) | 01/01/18 | e) | - | a) | 537948.48 | a) | 100.00% | c) | 100% | a) | 12 | Completed as per physical accomplishment. | 2
| DAN | [7 empty] | b) | Gamad/Maligro | b) | 01/04/18 | f) | - | b) | 537948.48 | b) | - | d) | - | b) | 36 | Financial documents still on process | 2
| 110 | [7 empty] | c) | PEO | c) | 2018-12-31 | g) | 2018-12-31 | c) | 479,947.45 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Prk.6 Cabay-angan-Esti Road |  |  | Road | 1.08 | Admin | a) | 90911.93 | a) | 01/01/18 | e) | - | a) | 90911.93 | a) | 100.00% | c) | 100% | a) | 12 | Completed as per physical accomplishment. | 2
| DAN | [7 empty] | b) | Gamad/Maligro | b) | 01/03/18 | f) | - | b) | 90911.93 | b) | - | d) | - | b) | 36 | Financial documents still on process | 2
| 111 | [7 empty] | c) | PEO | c) | 2018-12-31 | g) | 2018-12-31 | c) | 90,911.93 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Prk.5-Prk.1 Pawas, Dujali Road |  |  | Road | 2.18 | Admin | a) | 56566.39 | a) | 01/01/18 | e) | - | a) | 56566.39 | a) | 100.00% | c) | 100% | a) | 12 | Completed as per physical accomplishment. | 2
| DAN | [7 empty] | b) | Gamad/Maligro | b) | 01/03/18 | f) | - | b) | 56566.39 | b) | - | d) | - | b) | 36 | Financial documents still on process | 2
| 112 | [7 empty] | c) | PEO | c) | 2018-12-31 | g) | 2018-12-31 | c) | 54,346.01 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Prk.5-Prk.1 Pawas, Dujali Road |  |  | Road | 2.18 | CBRMC | a) | 137192.83 | a) | 01/01/18 | e) | - | a) | 137192.83 | a) | 100.00% | c) | 100% | a) | 5 | Completed as per physical accomplishment. | 2
| DAN | [7 empty] | b) | Gamad/Maligro | b) | 05/02/18 | f) | - | b) | 137192.83 | b) | - | d) | - | b) | 30 | Financial documents still on process | 2
| 112 | [7 empty] | c) | MANCIIA | c) | 02/02/19 | g) | 12/31/18 | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Dujali-Balisong-Magupising Road |  |  | Road | 5.52 | Admin | a) | 400494.66 | a) | 01/01/18 | e) | - | a) | 400494.66 | a) | 100.00% | c) | 100% | a) | 8 | Completed as per physical accomplishment. | 2
| DAN | [7 empty] | b) | Gamad/Maligro | b) | 01/03/18 | f) | - | b) | 400494.66 | b) | - | d) | - | b) | 24 | Financial documents still on process | 2
| 113 | [7 empty] | c) | PEO | c) | 2018-12-31 | g) | 2018-12-31 | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Prk.Narafil-Brgy. Site Magupising Road |  |  | Road | 2.08 | Admin | a) | 96860.19 | a) | 01/01/18 | e) | - | a) | 96860.19 | a) | 100.00% | c) | 100% | a) | 8 | Completed as per physical accomplishment. | 2
| DAN | [7 empty] | b) | Gamad/Maligro | b) | 01/03/18 | f) | - | b) | 96860.19 | b) | - | d) | - | b) | 8 | Financial documents still on process | 2
| 114 | [7 empty] | c) | PEO | c) | 12/31/18 | g) | 12/31/18 | c) | 33,963.32 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Dujali-Sitio Pawas Road |  |  | Road | 1.25 | Admin | a) | 230,810.21 | a) | 01/01/18 | e) | - | a) | 230,810.21 | a) | 100.00% | c) | 100% | a) |  | Completed as per physical accomplishment. | 2
| DAN | [7 empty] | b) | Gamad/Maligro | b) | 01/03/18 | f) | - | b) | 230,810.21 | b) | - | d) | - | b) |  | Financial documents still on process | 2
| 115 | [7 empty] | c) | PEO | c) | 12/31/18 | g) | 12/31/18 | c) | 230,657.28 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Prk.1-Prk.2, Sitio Pawas Road |  |  | Road | 1.4 | Admin | a) | 109068.92 | a) | 01/01/18 | e) | - | a) | 109068.92 | a) | 100.00% | c) | 100% | a) |  | Completed as per physical accomplishment. | 2
| DAN | [7 empty] | b) | Gamad/Maligro | b) | 02/12/18 | f) | - | b) | 109068.92 | b) | - | d) | - | b) |  | Financial documents still on process | 2
| 116 | [7 empty] | c) | PEO | c) | 12/31/18 | g) | 12/31/18 | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Dujali-Pawas-San Vicente Road |  |  | Road | 4.42 | Admin | a) | 103164.72 | a) | 01/01/18 | e) | - | a) | 103164.72 | a) | 100.00% | c) | 100% | a) | 12 | Completed as per physical accomplishment. | 2
| DAN | [7 empty] | b) | Gamad/Maligro | b) | 01/04/18 | f) | - | b) | 103164.72 | b) | - | d) | - | b) | 48 | Financial documents still on process | 2
| 117 | [7 empty] | c) | PEO | c) | 12/31/18 | g) | 12/31/18 | c) | 72,378.03 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Dujali-Pawas-San Vicente Road |  |  | Road | 4.42 | CBRMC | a) | 212322.24 | a) | 01/01/18 | e) | - | a) | 212322.24 | a) | 100.00% | c) | 100% | a) | 2 | Completed as per physical accomplishment. | 2
| DAN | [7 empty] | b) | Gamad/Maligro | b) | 05/07/18 | f) | - | b) | 212322.24 | b) | - | d) | - | b) | 24 | Financial documents still on process | 2
| 117 | [7 empty] | c) | Balisong San Vicente Irrigator's Association | c) | 02/07/19 | g) | 12/31/18 | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Jct.Salvacion-San Vicente-Cabay-angan |  |  | Road | 3.45 | Admin | a) | 205564.46 | a) | 01/01/18 | e) | - | a) | 205564.46 | a) | 100.00% | c) | 100% | a) | 12 | Completed as per physical accomplishment. | 2
| DAN |  | Road | [5 empty] | b) | Gamad/Maligro | b) | 01/03/18 | f) | - | b) | 205564.46 | b) | - | d) | - | b) | 48 | Financial documents still on process | 2
| 118 | [7 empty] | c) | PEO | c) | 12/31/18 | g) | 12/31/18 | c) | 202,565.93 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Jct.Salvacion-San Vicente-Cabay-angan |  |  | Road | 3.45 | CBRMC | a) | 133926.34 | a) | 01/01/18 | e) | - | a) | 133926.34 | a) | 100.00% | c) | 100% | a) | 2 | Completed as per physical accomplishment. | 2
| DAN |  | Road | [5 empty] | b) | Gamad/Maligro | b) | 05/07/18 | f) | - | b) | 133926.34 | b) | - | d) | - | b) | 4 | Financial documents still on process | 2
| 118 | [7 empty] | c) | Balisong San Vicente Irrigator's Association | c) | 02/07/19 | g) | 12/31/18 | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Dujali-San Miguel Road |  |  | Road | 3.95 | Admin | a) | 254671.37 | a) | 01/01/18 | e) | - | a) | 254671.37 | a) | 100.00% | c) | 100% | a) | 12 | Completed as per physical accomplishment. | 2
| DAN | [7 empty] | b) | Gamad/Maligro | b) | 02/16/18 | f) | - | b) | 254671.37 | b) | - | d) | - | b) | 60 | Financial documents still on process | 2
| 119 | [7 empty] | c) | PEO | c) | 2018-12-31 | g) | 2018-12-31 | c) | 247,867.31 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Dujali-San Miguel Road |  |  | Road | 3.95 | CBRMC | a) | 133926.34 | a) | 01/01/18 | e) | - | a) | 133926.34 | a) | 100.00% | c) | 100% | a) | - | Completed as per physical accomplishment. | 2
| DAN | [7 empty] | b) | Gamad/Maligro | b) | 01/03/18 | f) | - | b) | 133926.34 | b) | - | d) | - | b) | - | Financial documents still on process | 2
| 119 | [7 empty] | c) | Duajli Pob. Farmers Irrigator | c) | 12/31/18 | g) | 12/31/18 | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | San Miguel-Crossing Kinamayan Road |  |  | Road | 2.8 | Admin | a) | 71231.27 | a) | 01/01/18 | e) | - | a) | 71231.27 | a) | 100.00% | c) | 100% | a) |  | Completed as per physical accomplishment. | 2
| DAN | [7 empty] | b) | Gamad/Maligro | b) | 01/03/18 | f) | - | b) | 71231.27 | b) | - | d) | - | b) |  | Financial documents still on process | 2
| 120 | [7 empty] | c) | PEO | c) | 2018-12-31 | g) | 2018-12-31 | c) | 71,190.34 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | San Miguel-Libertad Road |  |  | Road | 6.2 | Admin | a) | 588705.52 | a) | 01/01/18 | e) | - | a) | 588705.52 | a) | 100.00% | c) | 100% | a) | 12 | Completed as per physical accomplishment. | 2
| DAN | [7 empty] | b) | Gamad/Maligro | b) | 01/03/18 | f) | - | b) | 588705.52 | b) | - | d) | - | b) | 36 | Financial documents still on process | 2
| 121 | [7 empty] | c) | PEO | c) | 2018-12-31 | g) | 2018-12-31 | c) | 574,308.39 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | San Miguel-Casig-ang Road |  |  | Road | 2.55 | Admin | a) | 175798.95 | a) | 01/01/18 | e) | - | a) | 175798.95 | a) | 100.00% | c) | 100% | a) | 12 | Completed as per physical accomplishment. | 2
| DAN | [7 empty] | b) | Gamad/Maligro | b) | 02/16/18 | f) | - | b) | 175798.95 | b) | - | d) | - | b) | 36 | Financial documents still on process | 2
| 122 | [7 empty] | c) | PEO | c) | 2018-12-31 | g) | 2018-12-31 | c) | 147,453.47 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | San Miguel-Casig-ang Road |  |  | Road | 2.55 | CBRMC | a) | 75129.41 | a) | 01/01/18 | e) | - | a) | 75129.41 | a) | 100.00% | c) | 100% | a) | - | Completed as per physical accomplishment. | 2
| DAN | [7 empty] | b) | Gamad/Maligro | b) | 01/03/18 | f) | - | b) | 75129.41 | b) | - | d) | - | b) | - | Financial documents still on process | 2
| 122 | [7 empty] | c) | KCIA | c) | 2018-12-31 | g) | 2018-12-31 | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Bacali-Casig-ang-Libertad Road |  |  | Road | 4.7 | Admin | a) | 446623.9 | a) | 01/01/18 | e) | - | a) | 446623.9 | a) | 100.00% | c) | 100% | a) |  | Completed as per physical accomplishment. | 2
| DAN | [7 empty] | b) | Gamad/Maligro | b) | 01/22/18 | f) | - | b) | 446623.9 | b) | - | d) | - | b) |  | Financial documents still on process | 2
| 123 | [7 empty] | c) | PEO | c) | 2018-12-31 | g) | 2018-12-31 | c) | 69,420.84 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Kinamayan-Moslog-Mahayag Road |  |  | Road | 3.23 | Admin | a) | 166223.27 | a) | 01/01/18 | e) | - | a) | 166223.27 | a) | 100.00% | c) | 100% | a) | 3 | Completed as per physical accomplishment. | 2
| DAN | [7 empty] | b) | Gamad/Maligro | b) | 02/12/18 | f) | - | b) | 166223.27 | b) | - | d) | - | b) | 12 | Financial documents still on process | 2
| 124 | [7 empty] | c) | PEO | c) | 2018-12-31 | g) | 2018-12-31 | c) | 147,526.53 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Kinamayan-Moslog-Mahayag Road |  |  | Road | 3.23 | CBRMC | a) | 120860.35 | a) | 01/01/18 | e) | - | a) | 120860.35 | a) | 100.00% | c) | 100% | a) | - | Completed as per physical accomplishment. | 2
| DAN | [7 empty] | b) | Gamad/Maligro | b) | 01/22/18 | f) | - | b) | 120860.35 | b) | - | d) | - | b) | - | Financial documents still on process | 2
| 124 | [7 empty] | c) | PAMIA | c) | 2018-12-31 | g) | 2018-12-31 | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | San Miguel-Moslog-Kinamayan Road |  |  | Road | 2.9 | Admin | a) | 202520.29 | a) | 01/01/18 | e) | - | a) | 202520.29 | a) | 100.00% | c) | 100% | a) | 10 | Completed as per physical accomplishment. | 2
| DAN | [7 empty] | b) | Gamad/Maligro | b) | 01/04/18 | f) | - | b) | 202520.29 | b) | - | d) | - | b) | 30 | Financial documents still on process | 2
| 125 | [7 empty] | c) | PEO | c) | 2018-12-31 | g) | 2018-12-31 | c) | 70,425.06 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Kinamayan-Lunga-og Road |  |  | Road | 2.59 | Admin | a) | 254864.48 | a) | 01/01/18 | e) | - | a) | 254864.48 | a) | 100.00% | c) | 100% | a) | 10 | Completed as per physical accomplishment. | 2
| DAN | [7 empty] | b) | Gamad/Maligro | b) | 01/03/18 | f) | - | b) | 254864.48 | b) | - | d) | - | b) | 30 | Financial documents still on process | 2
| 126 | [7 empty] | c) | PEO | c) | 2018-12-31 | g) | 2018-12-31 | c) | 248,573.64 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Prk.Magsaysay-Lunga-og-Dalisay Road |  |  | Road | 2.81 | Admin | a) | 152386.36 | a) | 01/01/18 | e) | - | a) | 152386.36 | a) | 100.00% | c) | 100% | a) |  | Completed as per physical accomplishment. | 2
| DAN | [7 empty] | b) | Gamad/Maligro | b) | 01/03/18 | f) | - | b) | 152386.36 | b) | - | d) | - | b) |  | Financial documents still on process | 2
| 127 | [7 empty] | c) | PEO | c) | 2018-12-31 | g) | 2018-12-31 | c) | 130,525.88 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Prk.Magsaysay-Lunga-og-Dalisay Road |  |  | Road | 2.81 | CBRMC | a) | 124126.85 | a) | 01/01/18 | e) | - | a) | 124126.85 | a) | 100.00% | c) | 100% | a) | 2 | Completed as per physical accomplishment. | 2
| DAN | [7 empty] | b) | Gamad/Maligro | b) | 05/07/18 | f) | - | b) | 124126.85 | b) | - | d) | - | b) | 2 | Financial documents still on process | 2
| 127 | [7 empty] | c) | Lunga-og Tribal Association | c) | 02/07/19 | g) | 12/31/18 | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Prk.Apitong-Upper Balisong-Dalisay |  |  | Road | 4.6 | Admin | a) | 200531.56 | a) | 01/01/18 | e) | - | a) | 200531.56 | a) | 100.00% | c) | 100% | a) | 12 | Completed as per physical accomplishment. | 2
| DAN |  | Road | [5 empty] | b) | Gamad/Maligro | b) | 01/03/18 | f) | - | b) | 200531.56 | b) | - | d) | - | b) | 36 | Financial documents still on process | 2
| 128 | [7 empty] | c) | PEO | c) | 2018-12-31 | g) | 2018-12-31 | c) | 200,041.98 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Prk.Apitong-Upper Balisong-Dalisay |  |  | Road | 4.6 | CBRMC | a) | 182923.78 | a) | 01/01/18 | e) | - | a) | 182923.78 | a) | 100.00% | c) | 100% | a) | 2 | Completed as per physical accomplishment. | 2
| DAN |  | Road | [5 empty] | b) | Gamad/Maligro | b) | 05/07/18 | f) | - | b) | 182923.78 | b) | - | d) | - | b) | 2 | Financial documents still on process | 2
| 128 | [7 empty] | c) | Lunga-og Tribal Association | c) | 02/07/19 | g) | 12/31/18 | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Sitio Paradise-Magkakaisa-Esperanza |  |  | Road | 1.75 | Admin | a) | 67345.26 | a) | 01/01/18 | e) | - | a) | 67345.26 | a) | 100.00% | c) | 100% | a) | 10 | Completed as per physical accomplishment. | 2
| DAN |  | Road | [5 empty] | b) | Gamad/Maligro | b) | 01/04/18 | f) | - | b) | 67345.26 | b) | - | d) | - | b) | 20 | Financial documents still on process | 2
| 129 | [7 empty] | c) | PEO | c) | 2018-12-31 | g) | 2018-12-31 | c) | 58,485.82 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Sitio Paradise-Magkakaisa-Esperanza |  |  | Road | 1.75 | CBRMC | a) | 88195.39 | a) | 01/01/18 | e) | - | a) | 88195.39 | a) | 100.00% | c) | 100% | a) | 2 | Completed as per physical accomplishment. | 2
| DAN |  | Road | [5 empty] | b) | Gamad/Maligro | b) | 05/09/18 | f) | - | b) | 88195.39 | b) | - | d) | - | b) | 4 | Financial documents still on process | 2
| 129 | [7 empty] | c) | Los Amigos Group of Women & Farmers Association | c) | 02/09/19 | g) | 12/31/18 | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Los Amigos 1-Esperanza-Los Amigos 2 |  |  | Road | 3.59 | Admin | a) | 129623.79 | a) | 01/01/18 | e) | - | a) | 129623.79 | a) | 100.00% | c) | 100% | a) |  | Completed as per physical accomplishment. | 2
| DAN |  | Road | [5 empty] | b) | Gamad/Maligro | b) | 01/04/18 | f) | - | b) | 129623.79 | b) | - | d) | - | b) |  | Financial documents still on process | 2
| 130 | [7 empty] | c) | PEO | c) | 2018-12-31 | g) | 2018-12-31 | c) | 113,391.65 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Los Amigos 1-Esperanza-Los Amigos 2 |  |  | Road | 3.59 | CBRMC | a) | 189456.77 | a) | 01/01/18 | e) | - | a) | 189456.77 | a) | 100.00% | c) | 100% | a) | 2 | Completed as per physical accomplishment. | 2
| DAN |  | Road | [5 empty] | b) | Gamad/Maligro | b) | 05/09/18 | f) | - | b) | 189456.77 | b) | - | d) | - | b) | 2 | Financial documents still on process | 2
| 130 | [7 empty] | c) | Los Amigos Group of Women & Farmers Association | c) | 02/09/19 | g) | 12/31/18 | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Mugas-Lanatad Road |  |  | Road | 1.53 | Admin | a) | 153098.12 | a) | 01/01/18 | e) | - | a) | 153098.12 | a) | 100.00% | c) | 100% | a) |  | Completed as per physical accomplishment. | 2
| DAN | [7 empty] | b) | Gamad/Maligro | b) | 01/22/18 | f) | - | b) | 153098.12 | b) | - | d) | - | b) |  | Financial documents still on process | 2
| 131 | [7 empty] | c) | PEO | c) | 2018-12-31 | g) | 2018-12-31 | c) | 130,993.26 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Mugas-Lunga-og Road |  |  | Road | 2.68 | Admin | a) | 128090.03 | a) | 01/01/18 | e) | - | a) | 128090.03 | a) | 100.00% | c) | 100% | a) | 12 | Completed as per physical accomplishment. | 2
| DAN | [7 empty] | b) | Gamad/Maligro | b) | 02/16/18 | f) | - | b) | 128090.03 | b) | - | d) | - | b) | 60 | Financial documents still on process | 2
| 132 | [7 empty] | c) | PEO | c) | 2018-12-31 | g) | 2018-12-31 | c) | 119,702.20 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Mugas-Lunga-og Road |  |  | Road | 2.68 | CBRMC | a) | 93095.14 | a) | 01/01/18 | e) | - | a) | 93095.14 | a) | 100.00% | c) | 100% | a) | 2 | Completed as per physical accomplishment. | 2
| DAN | [7 empty] | b) | Gamad/Maligro | b) | 05/07/18 | f) | - | b) | 93095.14 | b) | - | d) | - | b) | 2 | Financial documents still on process | 2
| 132 | [7 empty] | c) | Lunga-og Tribal Association | c) | 02/07/19 | g) | 12/31/18 | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Pantaron-Mugas Road |  |  | Road | 3.35 | Admin | a) | 198806.74 | a) | 01/01/18 | e) | - | a) | 198806.74 | a) | 100.00% | c) | 100% | a) | 12 | Completed as per physical accomplishment. | 2
| DAN | [7 empty] | b) | Gamad/Maligro | b) | 02/12/18 | f) | - | b) | 198806.74 | b) | - | d) | - | b) | 36 | Financial documents still on process | 2
| 133 | [7 empty] | c) | PEO | c) | 2018-12-31 | g) | 2018-12-31 | c) | 152,359.49 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Pantaron-Mugas Road |  |  | Road | 3.35 | CBRMC | a) | 137192.83 | a) | 01/01/18 | e) | - | a) | 137192.83 | a) | 100.00% | c) | 100% | a) | - | Completed as per physical accomplishment. | 2
| DAN | [7 empty] | b) | Gamad/Maligro | b) | 01/22/18 | f) | - | b) | 137192.83 | b) | - | d) | - | b) | - | Financial documents still on process | 2
| 133 | [7 empty] | c) | Katipunan Pantaron Irrigators Assoc. | c) | 2018-12-31 | g) | 12/31/18 | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | New Katipunan-Pantaron Road |  |  | Road | 1.96 | Admin | a) | 192870.42 | a) | 01/01/18 | e) | - | a) | 192870.42 | a) | 100.00% | c) | 100% | a) | 3 | Completed as per physical accomplishment. | 2
| DAN | [7 empty] | b) | Gamad/Maligro | b) | 01/04/18 | f) | - | b) | 192870.42 | b) | - | d) | - | b) | 12 | Financial documents still on process | 2
| 134 | [7 empty] | c) | PEO | c) | 12/31/18 | g) | 12/31/18 | c) | 51,000.00 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Sto.Tomas-Bdry.Mamacao Road |  |  | Road | 4.9 | Admin | a) | 328576.02 | a) | 01/01/18 | e) | - | a) | 328576.02 | a) | 100.00% | c) | 100% | a) | 6 | Completed as per physical accomplishment. | 2
| DAN | [7 empty] | b) | Gamad/Maligro | b) | 01/22/18 | f) | - | b) | 328576.02 | b) | - | d) | - | b) | 36 | Financial documents still on process | 2
| 135 | [7 empty] | c) | PEO | c) | 12/31/18 | g) | 12/31/18 | c) | 191,558.02 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Sto.Tomas-Bdry.Mamacao Road |  |  | Road | 4.9 | CBRMC | a) | 163324.8 | a) | 01/01/18 | e) | - | a) | 163324.8 | a) | 100.00% | c) | 100% | a) | 2 | Completed as per physical accomplishment. | 2
| DAN | [7 empty] | b) | Gamad/Maligro | b) | 04/19/18 | f) | - | b) | 163324.8 | b) | - | d) | - | b) | 6 | Financial documents still on process | 2
| 135 | [7 empty] | c) | Poblacion Tibal-og Tribal Assoc | c) | 01/19/19 | g) | 12/31/18 | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Fd.Rd.3-San Jose Road |  |  | Road | 4.55 | Admin | a) | 251487.26 | a) | 01/01/18 | e) | - | a) | 251487.26 | a) | 100.00% | c) | 100% | a) | 12 | Completed as per physical accomplishment. | 2
| DAN | [7 empty] | b) | Gamad/Maligro | b) | 02/16/18 | f) | - | b) | 251487.26 | b) | - | d) | - | b) | 36 | Financial documents still on process | 2
| 136 | [7 empty] | c) | PEO | c) | 12/31/18 | g) | 12/31/18 | c) | 193,902.25 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Fd.Rd.3-San Jose Road |  |  | Road | 4.55 | CBRMC | a) | 140459.33 | a) | 01/01/18 | e) | - | a) | 140459.33 | a) | 100.00% | c) | 100% | a) | 2 | Completed as per physical accomplishment. | 2
| DAN | [7 empty] | b) | Gamad/Maligro | b) | 05/30/18 | f) | 05/30/18 | b) | 140459.33 | b) | - | d) | - | b) | 2 | Financial documents still on process | 2
| 136 | [7 empty] | c) | Brgy. San Jose Upland Farmers Assoc of Sto. Tomas, DDN, inc | c) |  | g) | - | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Fd.Rd.2-Sto.Tomas-Magwawa Road |  |  | Road | 10.21 | Admin | a) | 438,0.37.15 | a) | 01/01/18 | e) | - | a) | 438,0.37.15 | a) | 100.00% | c) | 100% | a) | 6 | Completed as per physical accomplishment. | 2
| DAN | [7 empty] | b) | Gamad/Maligro | b) | 01/22/18 | f) | - | b) | 438,0.37.15 | b) | - | d) | - | b) | 36 | Financial documents still on process | 2
| 137 | [7 empty] | c) | PEO | c) | 2018-12-31 | g) | 2018-12-31 | c) | 148,575.00 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Menzi-Balagunan-Tulalian Road |  |  | Road | 10.63 | Admin | a) | 631810.16 | a) | 01/01/18 | e) | - | a) | 631810.16 | a) | 100.00% | c) | 100% | a) | 12 | Completed as per physical accomplishment. | 2
| DAN | [7 empty] | b) | Gamad/Maligro | b) | 01/04/18 | f) | - | b) | 631810.16 | b) | - | d) | - | b) | 120 | Financial documents still on process | 2
| 138 | [7 empty] | c) | PEO | c) | 2018-12-31 | g) | 2018-12-31 | c) | 490,290.55 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Menzi-Balagunan-Tulalian Road |  |  | Road | 10.63 | CBRMC | a) | 382180.03 | a) | 01/01/18 | e) | - | a) | 382180.03 | a) | 100.00% | c) | 100% | a) | - | Completed as per physical accomplishment. | 2
| DAN | [7 empty] | b) | Gamad/Maligro | b) | 06/18/18 | f) | - | b) | 382180.03 | b) | - | d) | - | b) | - | Financial documents still on process | 2
| 138 | [7 empty] | c) | - | c) | 03/17/18 | g) | 03/17/18 | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | NAFCO-Bobongon Road |  |  | Road | 2.66 | Admin | a) | 261752.71 | a) | 01/01/18 | e) | - | a) | 261752.71 | a) | 100.00% | c) | 100% | a) | 14 | Completed as per physical accomplishment. | 2
| DAN | [7 empty] | b) | Gamad/Maligro | b) | 01/08/18 | f) | - | b) | 261752.71 | b) | - | d) | - | b) | 140 | Financial documents still on process | 2
| 139 | [7 empty] | c) | PEO | c) | 2018-12-31 | g) | 2018-12-31 | c) | 255,107.41 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Jct.Highway-Tanglaw Road |  |  | Road | 3.98 | Admin | a) | 369464.93 | a) | 01/01/18 | e) | - | a) | 369464.93 | a) | 100.00% | c) | 100% | a) |  | Completed as per physical accomplishment. | 2
| DAN | [7 empty] | b) | Gamad/Maligro | b) | 02/16/18 | f) | - | b) | 369464.93 | b) | - | d) | - | b) |  | Financial documents still on process | 2
| 142 | [7 empty] | c) | PEO | c) | 2018-12-31 | g) | 2018-12-31 | c) | 40,667.20 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Fd.Rd.3-Kimamon-Luna Road |  |  | Road | 11.76 | Admin | a) | 1073416.56 | a) | 01/01/18 | e) | - | a) | 1073416.56 | a) | 100.00% | c) | 100% | a) |  | Completed as per physical accomplishment. | 2
| DAN | [7 empty] | b) | Gamad/Maligro | b) | 01/04/18 | f) | - | b) | 1073416.56 | b) | - | d) | - | b) |  | Financial documents still on process | 2
| 143 | [7 empty] | c) | PEO | c) | 2018-12-31 | g) | 2018-12-31 | c) | 183,025.00 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Kimamon-Lunga-og-Talomo Road |  |  | Road | 5.99 | Admin | a) | 565379.82 | a) | 01/01/18 | e) | - | a) | 565379.82 | a) | 100.00% | c) | 100% | a) | 14 | Completed as per physical accomplishment. | 2
| DAN | [7 empty] | b) | Gamad/Maligro | b) | 01/03/18 | f) | - | b) | 565379.82 | b) | - | d) | - | b) | 140 | Financial documents still on process | 2
| 144 | [7 empty] | c) | PEO | c) | 2018-12-31 | g) | 2018-12-31 | c) | 555,350.22 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Jct.Bdry.Tagum-Talomo Road |  |  | Road | 12.01 | Admin | a) | 766269.09 | a) | 01/01/18 | e) | - | a) | 766269.09 | a) | 100.00% | c) | 100% | a) | 14 | Completed as per physical accomplishment. | 2
| DAN | [7 empty] | b) | Gamad/Maligro | b) | 01/03/18 | f) | - | b) | 766269.09 | b) | - | d) | - | b) | 140 | Financial documents still on process | 2
| 145 | [7 empty] | c) | PEO | c) | 2018-12-31 | g) | 2018-12-31 | c) | 759,363.83 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Jct.Bdry.Tagum-Talomo Road |  |  | Road | 12.01 | CBRMC | a) | 306326.59 | a) | 01/01/18 | e) | - | a) | 306326.59 | a) | 100.00% | c) | 100% | a) | - | Completed as per physical accomplishment. | 2
| DAN | [7 empty] | b) | Gamad/Maligro | b) | 11/28/18/ | f) | - | b) | 306326.59 | b) | - | d) | - | b) | - | Financial documents still on process | 2
| 145 | [7 empty] | c) | - | c) | 01/31/19 | g) | 12/27/18 | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Bdry.Tagum-Crossing Kinamayan- |  |  | Road | 19.16 | Admin | a) | 1499919.84 | a) | 01/01/18 | e) | - | a) | 1499919.84 | a) | 100.00% | c) | 100% | a) | 3 | Completed as per physical accomplishment. | 2
| DAN |  | Sto.Tomas Road | [5 empty] | b) | Gamad/Maligro | b) | 01/22/18 | f) | - | b) | 1499919.84 | b) | - | d) | - | b) | 12 | Financial documents still on process | 2
| 146 | [7 empty] | c) | PEO | c) | 2018-12-31 | g) | 2018-12-31 | c) | 956,472.04 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Prk.Daisy-Prk.Narafil Road |  |  | Road | 0.75 | Admin | a) | 11982.88 | a) | 01/01/18 | e) | - | a) | 11982.88 | a) | 100.00% | c) | 100% | a) |  | Completed as per physical accomplishment. | 2
| DAN | [7 empty] | b) | Gamad/Maligro | b) | 01/03/18 | f) | - | b) | 11982.88 | b) | - | d) | - | b) |  | Financial documents still on process | 2
| 148 | [7 empty] | c) | PEO | c) | 2018-12-31 | g) | 2018-12-31 | c) | 8,711.22 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Tuganay - Anibongan - San Isidro Road |  |  | Road | 6.73 | CBRMC | a) | 52,000.00 | a) | 01/01/18 | e) | - | a) | 52,000.00 | a) | 100.00% | c) | 100% | a) | 2 | Completed as per physical accomplishment. | 2
| DAN | [7 empty] | b) | Gamad/Maligro | b) | 11/19/18 | f) | - | b) | 52,000.00 | b) | - | d) | - | b) | 2 | Financial documents still on process | 2
| 091 | [7 empty] | c) | EZRA | c) | 02/04/19 | g) | 12/11/18 | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 11 |  | Dujali - Balisong - Magupising Road |  |  | Road | 6.73 | CBRMC | a) | 29,398.46 | a) | 01/01/18 | e) | - | a) | 29,398.46 | a) | 100.00% | c) | 100% | a) | 2 | Completed as per physical accomplishment. | 2
| DAN | [7 empty] | b) | Gamad/Maligro | b) | 05/04/18 | f) | - | b) | 29,398.46 | b) | - | d) | - | b) | 2 | Financial documents still on process | 2
| 091 | [7 empty] | c) | Duajli Pob. Farmers Irrigators | c) | 02/04/19 | g) | 12/11/18 | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
AC
|  |  | Rehabilitation / Improvement Of Various Local |  |  | Road | - | Admin | a) | 5000000 | [12 empty] | See projects listed below | AC
|  |  | Roads and Drainages | [5 empty] | b) | Paraguya | [13 empty] | AC
[9 empty] | c) | Admin | [13 empty] | AC
[9 empty] | d) | - | [13 empty] | AC
|  |  |  | Rehabilitation of Brgy. Tagbay Barangay |  | Road |  | Admin | a) | 138000 | a) | 04/25/18 | e) | - | a) | 138000 | a) | 100.00% | c) | 100.00% | a) | - | Completed as per physical accomplishment. | 2
|  |  |  | Road, IGACOS |  |  |  |  | b) | Porras/Pacquiao | b) | 12/05/18 | f) | - | b) | 138000 | b) | - | d) | - | b) | - | Financial documents still on process | 2
[9 empty] | c) | PEO | c) | 12/07/18 | g) | 12/07/18 | c) | - | [7 empty] | 2
[9 empty] | d) | - | [13 empty] | 2
|  |  |  | Rehabilitation of Brgy. San Jose Barangay |  | Road |  | Admin | a) | 138000 | a) | 04/25/18 | e) | - | a) | 138000 | a) | 100.00% | c) | 100.00% | a) | - | Completed as per physical accomplishment. | 2
|  |  |  | Road, IGACOS |  |  |  |  | b) | Porras/Pacquiao | b) | 10/27/18 | f) | - | b) | 138000 | b) | - | d) | - | b) | - | Financial documents still on process | 2
[9 empty] | c) | PEO | c) | 10/31/18 | g) | 10/31/18 | c) | - | [7 empty] | 2
[9 empty] | d) | - | [13 empty] | 2
|  |  |  | Rehabilitation of Brgy. Guilon Barangay |  | Road |  | Admin | a) | 138000 | a) | 04/25/18 | e) | - | a) | 138000 | a) | 100.00% | c) | 100.00% | a) | 3 | Completed as per physical accomplishment. | 2
|  |  |  | Road, IGACOS |  |  |  |  | b) | Porras/Pacquiao | b) | 01/10/19 | f) | - | b) | 138000 | b) | - | d) | - | b) | 30 | Financial documents still on process | 2
[9 empty] | c) | PEO | c) | 01/19/19 | g) | - | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  |  | Rehabilitation of Brgy. Del Monte Barangay |  | Road |  | Admin | a) | 138000 | a) | 04/25/18 | e) | - | a) | 138000 | a) | 100.00% | c) | 100.00% | a) | - | Completed as per physical accomplishment. | 2
|  |  |  | Road, IGACOS |  |  |  |  | b) | Porras/Pacquiao | b) | 12/12/18 | f) | - | b) | 138000 | b) | - | d) | - | b) | - | Financial documents still on process | 2
[9 empty] | c) | PEO | c) | 01/08/19 | g) | - | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  |  | Rehabilitation of Brgy. Tagbitan-ag |  | Road |  | Admin | a) | 138000 | a) | 04/25/18 | e) | 61 CD | a) | 138000 | a) | 100% | c) | 100% | a) | 5 | Completed as per physical accomplishment. | 2
|  |  |  | Barangay Road, IGACOS |  |  |  |  | b) | Porras/Pacquiao | b) | 02/15/19 | f) | 30 WD | b) | 138000 | b) | - | d) | - | b) | 45 | Financial documents still on process | 2
[9 empty] | c) | PEO | c) | 02/24/19 | g) | 03/15/19 | c) | 127356.84 | [7 empty] | 2
[9 empty] | d) | - | d) | 03/15/19 | [11 empty] | 2
|  |  |  | Rehabilitation of Brgy. Peñaplata Barangay |  | Road |  | Admin | a) | 139000 | a) | 04/25/18 | e) | 66 CD | a) | 139000 | a) | 100% | c) | 100 | a) | 1 | Completed 8/31/2019 | 2
|  |  |  | Road, IGACOS |  |  |  |  | b) | Porras/Pacquiao | b) | 8/16/2019 | f) | 225 CD | b) | 139000 | b) | - | d) | - | b) | 1 |  | 2
[9 empty] | c) | PEO | c) | 8/31/2019 | g) | - | c) | 139000 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  |  | Rehabilitation of Brgy. Pob. Kaputian |  | Road |  | Admin | a) | 138000 | a) | 04/25/18 | e) | - | a) | 138000 | a) | 100% | c) | 100% | a) | 4 |  | 2
|  |  |  | Barangay Road, IGACOS |  |  |  |  | b) | Porras/Pacquiao | b) | 2019-08-08 | f) | - | b) | 138000 | b) | - | d) | - | b) | 36 | Completed Sept. 22, 2019 | 2
[9 empty] | c) | PEO | c) | 9/22/2019 | g) | 9/22/2019 | c) | - | [7 empty] | 2
[9 empty] | d) | 6/13/19 | d) | - | [11 empty] | 2
|  |  |  | Rehabilitation of Brgy. Sto. NIño Barangay |  | Road |  | Admin | a) | 130000 | a) | 04/13/18 | e) | - | a) | 130000 | a) | 100.00% | c) | 100.00% | a) | 3 | Completed as per physical accomplishment. | 2
|  |  |  | Road, IGACOS |  |  |  |  | b) | Porras/Pacquiao | b) | 03/07/19 | f) | - | b) | 130000 | b) | - | d) | - | b) | 30 | Financial documents still on process | 2
[9 empty] | c) | PEO | c) | 03/16/19 | g) | 03/15/19 | c) | 107,972.00 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  |  | Rehabilitation of Brgy.Licup Barangay |  | Road |  | Admin | a) | 139000 | a) | 04/25/18 | e) | - | a) | 139000 | a) | 100.00% | c) | 100.00% | a) | 5 | Completed as per physical accomplishment. | 2
|  |  |  | Road, IGACOS |  |  |  |  | b) | Porras/Pacquiao | b) | 03/21/19 | f) | - | b) | 139000 | b) | - | d) | - | b) | 100 | Financial documents still on process | 2
[9 empty] | c) | PEO | c) | 03/29/19 | g) | 03/29/19 | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  |  | Rehabilitation of Brgy. Aundanao Barangay |  | Road |  | Admin | a) | 138000 | a) | 04/25/18 | e) | - | a) | 138000 | a) | 100.00% | c) | 100.00% | a) | 6 | Completed as per physical accomplishment. | 2
|  |  |  | Road, IGACOS |  |  |  |  | b) | Porras/Pacquiao | b) | 04/01/19 | f) | - | b) | 138000 | b) | - | d) | - | b) | 12 | Financial documents still on process | 2
[9 empty] | c) | PEO | c) | 04/09/19 | g) | 04/12/19 | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
4 |  |  |  | Rehabilitation of Brgy. Adecor Barangay |  | Road |  | Admin | a) | 138000 | a) | 04/25/18 | e) | 66 CD | a) | 138000 | a) | 60.00% | c) | 60.00% | a) | - | Completed as per POW. Financial Documents on process | 2
4 |  |  |  | Road, IGACOS |  |  |  |  | b) | Porras/Pacquiao | b) | 10/18/18 | f) | 225 CD | b) | 138000 | b) | - | d) | - | b) | - |  | 2
4 | [8 empty] | c) | PEO | c) | 10/27/19 | g) | - | c) | 111,872.00 | [7 empty] | 2
4 | [8 empty] | d) | - | d) | 10/15/2019 | [11 empty] | 2
|  |  | Water System Development Project | [20 empty] | AC
|  |  | Construction of Water System Projects in Component LGU's | [20 empty] | AC
|  |  |  | Impv't. of Water System, Brgy. Poblacion |  | Water |  | Admin | a) | 1250000 | a) | 08/24/18 | e) | - | a) | 1250000 | a) | 100% | c) | 85.39% | a) | 8 | Completed (contract by Zular3-Az) September 15, 2019 | AC
|  |  |  | Kaputian (Level II) |  | system |  |  | b) | Porras | b) | 05/3/19 | f) | - | b) | 1250000 | b) | - | d) | -14.61 | b) | 160 |  | AC
[9 empty] | c) | Contract | c) | 08/30/19 | g) | 09/15/2019 | c) | - | [7 empty] | AC
[9 empty] | d) | - | d) | - | [11 empty] | AC
|  |  | Const./Rehab./Comp. of Various Gov't. Bldgs. |  |  | Bldgs. | - | Admin | a) | 13523124 | [12 empty] | Investigation/Inspection of priority projects | AC
|  |  | Struct., Fac. (Provincewide) | [5 empty] | b) | Foronda | [13 empty] | AC
[9 empty] | c) | Admin | [13 empty] | AC
[9 empty] | d) | - | [13 empty] | AC
|  |  |  | Completion of PVO Bldg. (PVO Penthouse), |  | Bldgs. |  | Admin | a) | 1,500,000.00 | a) | 04/02/18 | e) | - | a) | 1,500,000.00 | a) | 100.00% | c) | 100.00% | a) | - | Completed as per physical accomplishment. | 1
|  |  |  | Gov't. Center, Mankilam |  |  |  |  | b) | Pasiona | b) | 09/03/18 | f) | - | b) | 1,500,000.00 | b) | - | d) | - | b) | - | Financial documents still on process | 1
[9 empty] | c) | Admin | c) | 12/01/18 | g) | 01/15/19 | c) | 1,052,849.49 | [7 empty] | 1
[9 empty] | d) | 90 CD | d) | - | [11 empty] | 1
1
|  |  |  | Construction of Multi-Purpose Bldg. |  | Bldg | 303.75 sq.m | Admin | a) | 6748000 | a) | 12/11/18 | e) | - | a) | 6748000 | a) |  | c) | 100% | a) | 25 | Completed | 1
|  |  |  | (PENRO Building), Mankilam, Tagum City |  |  |  |  | b) | Pasiona/Juan | b) | 10/16/18 | f) | 109 | b) | 6748000 | b) | - | d) |  | b) | 750 |  | 1
|  |  |  | (Part of 8,548,000.00) |  |  |  |  | c) | PEO | c) | 9/13/2019 | g) | - | c) | 6560497.45 | [7 empty] | 1
|  |  |  | (P1,800,000.00 - SB # 3 CY 2017) |  |  |  |  | d) | 256 CD | d) | 06/30/19 | [11 empty] | 1
4 |  |  |  | Repair/Rehab. Of PEO Building (2nd District), Carmen |  | Bldg |  | Admin | a) | 2250000 | a) | 08/10/18 | e) | - | a) | 2250000 | a) | 100% | c) | 100% | a) | 18 | Completed based on POW. Financial Documents on process | 2
4 | [8 empty] | b) | Andoy | b) | 02/18/19 | f) | - | b) | 2250000 | b) | - | d) | 0% | b) | 138 |  | 2
4 | [8 empty] | c) | Admin | c) | 08/23/19 | g) | - | c) | 1577344.8 | [7 empty] | 2
4 | [8 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | STIMULUS PROJECTS | [20 empty] | AC
|  |  | TAGUM CITY | [20 empty] | AC
|  |  |  | Construction of Brgy. GYM Bleacher, |  | Bleacher |  | Contract | a) | 500000 | a) | 06/05/18 | e) | - | a) | 500000 | a) | 100.00% | c) | 100.00% | a) | - | Completed as per physical accomplishment. | 1
|  |  |  | Pandapan, Tagum City |  |  |  |  | b) | Mayang | b) | 11/16/18 | f) | - | b) | 500000 | b) | - | d) | - | b) | - | Financial documents still on process | 1
[9 empty] | c) | FT Const. | c) | 01/15/19 | g) | 01/31/19 | c) | 417608 | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  |  | Repair of Brgy. Hall, San Miguel, |  | Bldg. |  | Admin | a) | 500000 | a) | 10/26/18 | e) | 13 | a) | 500000 | a) | 100% | c) | 100% | a) | 4 | Completed as per physical accomplishment. | 1
|  |  |  | Tagum City |  |  |  |  | b) | Mayang | b) | 03/04/19 | f) | 8 days | b) | 500000 | b) | - | d) | 0% | b) | 88 | Financial documents still on process | 1
[9 empty] | c) | Admin | c) | 05/23/19 | g) | 6/14/19 | c) | 411,905.79 | [7 empty] | 1
[9 empty] | d) | 50 CD | d) | - | [11 empty] | 1
4 |  |  |  | Completion of Two Storey Multi-Purpose |  | Bldg. |  | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | 100% | c) | 100% | a) | 5 | Completed based on Physical Accomplishment. Financial Documents on process | 1
4 |  |  |  | Building, Magugpo East, Tagum City |  |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | 0% | b) | 110 |  | 1
4 | [8 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 1
4 | [8 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | IGCS | [20 empty] | AC
|  |  | 1 | 1 | Const. of Public Toilet at Guilon, IGCS | Bldg. |  | Admin | a) | 500000 | a) | 07/05/18 | e) | - | a) | 500000 | a) | 100.00% | c) | 100% | a) | - | Completed as per physical accomplishment. | 2
[9 empty] | b) | - | b) | 12/31/17 | f) | - | b) | 500000 | b) | - | d) | - | b) | - | Financial documents still on process | 2
[9 empty] | c) | - | c) | 10/19/18 | g) | 10/19/18 | c) | 403,637.34 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | 2 | 2 | Impv't. of Brgy. Hall, Cawag, IGCS | Bldg. |  | Admin | a) | 500000 | a) | 07/19/18 | e) | - | a) | 500000 | a) | 100.00% | c) | 100.00% | a) | - | Completed as per physical accomplishment. | 2
[9 empty] | b) | Porras | b) | 09/04/18 | f) | - | b) | 500000 | b) | - | d) | - | b) | - | Financial documents still on process | 2
[9 empty] | c) | Admin | c) | 12/12/18 | g) | 12/12/18 | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | 3 | 3 | Improvement of Brgy. Hall, Kinawitnon, | Bldg. |  | Admin | a) | 500000 | a) | 07/05/18 | e) | - | a) | 500000 | a) | 100.00% | c) | 100.00% | a) | - | Completed as per physical accomplishment. | 2
[5 empty] | IGCS |  |  |  | b) | Roque | b) | 10/24/18 | f) | 19 days | b) | 500000 | b) | - | d) | - | b) | - | Financial documents still on process | 2
[9 empty] | c) | PEO | c) | 11/11/19 | g) | 01/11/19 | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | 4 | 4 | Const. of New Brgy. Hall, Adecor, IGCS | Bldg. |  | Contract | a) | 500000 | a) | 10/16/18 | e) | - | a) | 500000 | a) | 100.00% | c) | 100.00% | a) | - | Completed as per physical accomplishment. | 2
[9 empty] | b) | Porras | b) | 02/21/19 | f) | - | b) | 500000 | b) | - | d) | - | b) | - | Financial documents still on process | 2
[9 empty] | c) | Ecomixed | c) | 03/03/19 | g) | 03/03/19 | c) | 475414.3 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | 5 | 5 | Impv't. of Multi-Purpose Bldg. | Bldg. |  | Admin | a) | 500000 | a) | 07/05/18 | e) | - | a) | 500000 | a) | 100.00% | c) | 100.00% | a) | 7 | Completed as per physical accomplishment. | 2
[5 empty] | (Covered Court), Tagbitan-ag, IGCS |  |  |  | b) | Porras | b) | 12/31/17 | f) | - | b) | 500000 | b) | - | d) | - | b) | 35 | Financial documents still on process | 2
[9 empty] | c) | PEO | c) | 10/19/18 | g) | 03/08/19 | c) | 494,673.25 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
4 |  | L. | 5% Calamity Fund CY 2018 | [20 empty] | AC
4 |  |  | 1. Prevention and Mitigation | [20 empty] | AC
4 |  |  | 1.1 Desiltation/Excavation of rivers and creeks |  |  | rivers |  | Admin | a) | 3000000 | [12 empty] | Investigation/Inspection of priority projects | AC
4 | [8 empty] | b) | - | [13 empty] | AC
4 | [8 empty] | c) | PEO | [13 empty] | AC
4 | [8 empty] | d) | - | [13 empty] | AC
4 | [23 empty] | 1
4 |  |  | 1.1.1. | Improvement and Desiltation of Tagum Creek (Phase I and Phase II) |  | Creek |  | Admin | a) | 2,000,000.00 | a) | 11/06/18 | e) | - | a) | 2,000,000.00 | a) | 100% | c) | 100% | a) | 5 | Completed | 1
4 | [8 empty] | b) | Mayang | b) | 03/22/19 | f) | - | b) | 2,000,000.00 | b) | - | d) | 0% | b) | 110 |  | 1
4 | [8 empty] | c) | PEO | c) | 10/31/19 | g) | - | c) | - | [7 empty] | 1
4 | [8 empty] | d) | 224 CD | d) | - | [11 empty] | 1
|  | E. | SUPPLEMENTAL BUDGET # 1 CY 2018 | [5 empty] | a) | 6,000,000.00 | [12 empty] | See list of Provincial Roads | AC
|  |  | 1 Const./Impv't./Compl. Of School Buildings, | [20 empty] | AC
|  |  | Structures & Facilities | [20 empty] | AC
|  |  |  | Completion of Carmen Central E/S Gym |  | Gym |  | Admin | a) | 1000000 | a) | 07/31/18 | e) | - | a) | 1000000 | a) | 100.00% | c) | 100.00% | a) | 10 | Completed as per physical accomplishment. | 2
[9 empty] | b) | Estorco | b) | 12/07/18 | f) | - | b) | 1000000 | b) | - | d) | - | b) | 300 | Financial documents still on process | 2
[9 empty] | c) | PEO | c) | 04/19/19 | g) | - | c) | 818,875.12 | [7 empty] | 2
[9 empty] | d) | 130 CD | d) | - | [11 empty] | 2
|  |  |  | Const. of Dujali E/S Gym |  | Gym |  | Admin | a) | 2,109,662.99 | a) | 07/05/18 | e) | - | a) | 2,109,662.99 | a) | 100.00% | c) | 100.00% | a) | 4 | Completed as per physical accomplishment. | 2
[9 empty] | b) | Azotes | b) | 12/07/18 | f) | - | b) | 2,109,662.99 | b) | - | d) | - | b) | 88 | Financial documents still on process | 2
[9 empty] | c) | PEO | c) | 04/15/19 | g) | 04/01/19 | c) | 1,712,249.72 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | 1 Const. in Progress - Infrastructure | [5 empty] | b) | Paraguya | [13 empty] | AC
|  |  | Assets (Rehabilitation of Various | [5 empty] | c) | PEO | [13 empty] | AC
|  |  | Provincial Roads) | [5 empty] | d) | - | [13 empty] | AC
|  |  | 3 | a. | New Corella - New Sambog - Silangan | Road |  | Admin | a) | 2,095,000.00 | a) | 07/19/18 | e) | 71 CD | a) | 2,095,000.00 | a) | 100.00% | c) | 100.00% | a) | 3 | Completed as per physical accomplishment. | 1
[9 empty] | b) | Salido | b) | 10/08/18 | f) | 53 CD | b) | 2,095,000.00 | b) | - | d) | - | b) | 90 | Financial documents still on process | 1
[9 empty] | c) | PEO | c) | 11/07/18 | g) | 03/19/19 | c) | - | [7 empty] | 1
[9 empty] | d) | - | d) | 03/19/19 | [11 empty] | 1
|  |  | 1 | b | Bacali - Casig-ang - Libertad | Road |  | Admin | a) | 1,081,410.00 | a) | 07/31/18 | e) | - | a) | 1,081,410.00 | a) | 100.00% | c) | 100.00% | a) | - | Completed as per physical accomplishment. | 2
[9 empty] | b) | Toquero | b) | 10/23/18 | f) | - | b) | 1,081,410.00 | b) | - | d) | - | b) | - | Financial documents still on process | 2
[9 empty] | c) | PEO | c) | 11/30/18 | g) | 11/30/18 | c) | - | [7 empty] | 2
[9 empty] | d) | Admin | d) | - | [11 empty] | 2
|  |  | 1 | c | San Miguel - Moslog - Kinamayan | Road |  | Admin | a) | 704,740.00 | a) | 08/02/18 | e) | - | a) | 704,740.00 | a) | 100.00% | c) | 100.00% | a) | - | Completed as per physical accomplishment. | 2
[9 empty] | b) | Gamad | b) | 11/05/18 | f) | - | b) | 704,740.00 | b) | - | d) | - | b) | - | Financial documents still on process | 2
[9 empty] | c) | PEO | c) | 01/12/19 | g) | 01/12/19 | c) | - | [7 empty] | 2
[9 empty] | d) |  | d) | - | [11 empty] | 2
4 |  |  | OPPAP-PAMANA | [20 empty] | AC
|  |  | 1. Tribal Hall | [20 empty] | AC
|  |  |  | Construction of Tribal Hall, B.E. Dujali |  | Bldg. |  | Admin | a) | 500000 | a) | CY 2018 | e) | - | a) | 500000 | a) | 100% | c) | 100% | a) | 4 | Completed 5/31/2019 as per physical accomplishment. Financial Documents still on process | 2
[9 empty] | b) | Azotes | b) | 03/21/19 | f) | - | b) | 500000 | b) | - | d) | 0% | b) | 104 |  | 2
[9 empty] | c) | PEO | c) | 8/06/2019 | g) | 5/31/2019 | c) | 479480 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
1
1
|  |  |  | Construction of PWS Level II in Purok JBL and Salawao, |  | PWS |  | Admin | a) | 1000000 | a) | 08/15/18 | e) | - | a) | 1000000 | a) | 100.00% | c) | 100.00% | a) | 14 | Completed as per physical accomplishment. | 1
|  |  |  | Santo Niño, Talaingod |  |  |  |  | b) | Diosanta | b) | 12/17/18 | f) | 19 days | b) | 1000000 | b) | - | d) | - | b) | 420 | Financial documents still on process | 1
[9 empty] | c) | PEO | c) | 02/24/19 | g) | 03/15/19 | c) | 560706.67 | [7 empty] | 1
[9 empty] | d) | 89 CD | d) | 03/15/19 | [11 empty] | 1
4 |  | 4 |  | Upgrading of Existing PWS Level II in Sitio Patel 2, Gupitan, Kapalong |  | PWS |  | Admin | a) | 2500000 | a) | 8/14/2019 | e) | - | a) | 2500000 | a) |  | c) | 100% | a) | - | Completed as per Physical Accomplishment. Financial Documents on process | 1
4 | [8 empty] | b) | Diosanta | b) | 3/25/2019 | f) | - | b) | 2500000 | b) |  | d) |  | b) | - |  | 1
4 | [8 empty] | c) | PEO | c) | 7/19/2019 | g) | 09/30/2019 | c) | - | [7 empty] | 1
4 | [8 empty] | d) | - | d) | - | [11 empty] | 1
4 |  | R. | LOCAL GOVERNMENT SUPPORT FUND (LGSF) CY 2018 | [20 empty] | AC
4 |  |  | 1 | Road Upgrading of San Vicente - Butay Provincial Road |  | Road |  | Contract | a) | 19949581.18 | a) | CY 2018 | e) | - | a) | 19949581.18 | a) | 100% | c) | 100% | a) | 18 | Completed as per Physical Accomplishment. Financial Documents on process | 1
4 | [8 empty] | b) | Aclaracion | b) | 11/19/18 | f) | 28 CD | b) | 19949581.18 | b) | 100% | d) | 0% | b) | 396 |  | 1
4 | [8 empty] | c) | Alpha & Omega | c) | 06/08/19 | g) | 06/26/2019 | c) | 9,685,667.31 | [7 empty] | 1
4 | [8 empty] | d) | 202 CD | d) | 07/06/19 | [11 empty] | 1
|  | F. | Supplemental Budget No. 2 CY 2018 | [20 empty] | AC
|  |  | Const/Coml/Impvt of Various Gov't Bldgs., Structures | [20 empty] | AC
|  |  | & Facilities (Const. in Progress - Bldgs and Other Structures) | [20 empty] | AC
AC
|  |  |  | Const. of Provincial Training Center, Ph.II, |  | Bldg. |  | Admin | a) | 1,250,000.00 | a) | 07/05/18 | e) | - | a) | 1,250,000.00 | a) | 100.00% | c) | 100% | a) | 10 | Completed 6/28/2019 as per physical accomplishment. Financial Documents still on process | 2
|  |  |  | Brgy. Kinawitnon, IGACOS |  |  |  |  | b) | Porras | b) | 11/05/18 | f) | 63 CD | b) | 1,250,000.00 | b) | 100.00% | d) | 0% | b) | 200 |  | 2
[9 empty] | c) | PEO | c) | 12/23/18 | g) | 06/28/2019 | c) | 860,218.02 | [7 empty] | 2
[9 empty] | d) | 177 CD | d) | 04/30/19 | [11 empty] | 2
|  |  |  | Upgrading of DAGOEMC Multi-Purpose |  | Bldg. |  | - | a) | 3,000,000.00 | a) | 09/04/18 | e) | - | a) | 3,000,000.00 | a) | 30.28% | c) | 30.28% | a) | 7 | Completed as per physical accomplishment. | 1
|  |  |  | Bldg., Mankilam |  |  |  |  | b) | Chua | b) | 03/04/19 | f) | - | b) | 3,000,000.00 | b) | - | d) | +0.36% | b) | 210 | Financial documents still on process | 1
[9 empty] | c) | PEO | c) | 07/26/19 | g) | - | c) | 1,537,217.00 | [7 empty] | 1
[9 empty] | d) | 145 CD | d) | - | [11 empty] | 1
|  |  |  | Const. of 1 Unit Triball Hall, Brgy. Carcor, |  | Bldg. | 86.40 sq.m | Admin | a) | 680,000.00 | a) | 11/22/18 | e) | - | a) | 680,000.00 | a) | 100.00% | c) | 100.00% | a) | 16 | Completed as per physical accomplishment. | 1
|  |  |  | New Corella |  |  |  |  | b) | Gone | b) | 02/01/19 | f) | 14 CD | b) | 680,000.00 | b) | - | d) | - | b) | 160 | Financial documents still on process | 1
[9 empty] | c) | PEO | c) | 04/01/19 | g) | 04/15/19 | c) | 551,946.14 | [7 empty] | 1
[9 empty] | d) | - | d) | 04/15/19 | [11 empty] | 1
|  |  |  | Const/Compl. Of Fence at bahay |  | Fence |  | - | a) | 2,500,000.00 | a) | 08/28/18 | e) | - | a) | 2,500,000.00 | a) | 100.00% | c) | 100.00% | a) | 17 | Completed as per physical accomplishment. | 1
|  |  |  | Pag-Asa for Minors, New Corella |  |  |  |  | b) | Gone | b) | 01/19/19 | f) | 20 CD | b) | 2,500,000.00 | b) | - | d) | - | b) | 323 | Financial documents still on process | 1
[9 empty] | c) | PEO | c) | 03/06/19 | g) | 05/25/19 | c) | 2,150,422.85 | [7 empty] | 1
[9 empty] | d) | 110 CD | d) | 05/25/19 | [11 empty] | 1
|  |  | 2 Infastructure Augmentation Project (Provincial Counterpart for PRDP Project) | [20 empty] | AC
AC
|  |  |  | Rehab. Of Capungagan-Bdy. San Miguel |  | Road |  | Admin | a) | 4,990,000.000 | a) | 07/20/18 | e) | - | a) | 4,990,000.000 | a) | 100.00% | c) | 100.00% | a) | 6 | Completed as per physical accomplishment. | 1
|  |  |  | FMR (Variation Order) |  |  |  |  | b) | Avila | b) | 08/23/18 | f) | 86 CD | b) | 4,990,000.000 | b) | - | d) | - | b) | 180 | Financial documents still on process | 1
[9 empty] | c) | PEO | c) | 01/13/19 | g) | 03/30/19 | c) | 4879151.58 | [7 empty] | 1
[9 empty] | d) | 134 CD | d) | 03/30/19 | [11 empty] | 1
| II. PROJECTS UNDER THE CURRENT APPROPRIATION CY 2019 | [22 empty] | AP
| A.1 GENERAL FUND CY 2019 | [6 empty] | MBA/CBRMC | a) | 18127866 | a) | 01/03/19 | e) | - | a) | 18127866 | a) | 83.63 | c) | 83.83 | a) | 46 | See list of Provincial Roads | AP
| Road ID |  | Maintenance of Various Provincial Roads and Bridges at District 1 |  |  | Road Maintenance | KM |  | b) | Paraguya | b) | 01/03/19 | f) | - | b) | 18127866 | b) | - | d) | - | b) | 920 |  | FS
[7 empty] | 288.26 |  | c) | PEO/CBRMC | c) | 12/31/19 | g) | - | c) | - | [7 empty] | AC
| 11DAN | [9 empty] | d) | - | [11 empty] | AC
[9 empty] | d) | 261 days | d) | - | [11 empty] | AC
|  |  | Jct. Highway Magatos - New Bantayan |  |  | Road Maintenance | 7.1 | MBA | a) | 287307.39 | a) | 01/03/19 | e) | - | a) | 287307.39 | a) | 100% | c) | 100% | a) | 15 | Completed | AC
| 001 | [7 empty] | b) | Crucio | b) | 01/16/19 | f) | - | b) | 287307.39 | b) | - | d) | - | b) | 480 |  | 1
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 118693.58 | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | Jct. Highway Magatos - New Bantayan |  |  | Road Maintenance | 7.1 | CBRMC | a) | 223674.22 | a) | 01/03/19 | e) | - | a) | 223674.22 | a) | 100% | c) | 100% | a) | 16 | Completed | 1
| 001 | [7 empty] | b) | Crucio | b) | 3/22/19 | f) | - | b) | 223674.22 | b) | - | d) | - | b) | 480 |  | 1
[9 empty] | c) | CALAFA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
|  |  | Magatos-Bdry Pagsabangan |  |  | Road Maintenance | 8.33 | MBA | a) | 328740.25 | a) | 01/03/19 | e) | - | a) | 328740.25 | a) | 100% | c) | 100% | a) | 15 | Completed | 1
| 002 | [7 empty] | b) | Crucio | b) | 01/03/19 | f) | - | b) | 328740.25 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 207258.49 | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | Magatos-Bdry Pagsabangan |  |  | Road Maintenance | 8.33 | CBRMC | a) | 270763.53 | a) | 01/03/19 | e) | - | a) | 270763.53 | a) | 100% | c) | 100% | a) | 16 | Completed | 1
| 002 | [7 empty] | b) | Crucio | b) | 03/22/19 | f) | - | b) | 270763.53 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | CALAFA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
|  |  | Ilog-New Bantayan |  |  | Road Maintenance | 2.68 | MBA | a) | 131131.39 | a) | 01/03/19 | e) | - | a) | 131131.39 | a) | 100% | c) | 100% | a) | 15 | Completed | 1
| 003 | [7 empty] | b) | Crucio | b) | 01/16/19 | f) | - | b) | 131131.39 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 49,316.69 | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | Ilog-New Bantayan |  |  | Road Maintenance | 2.68 | CBRMC | a) | 65925.03 | a) | 01/03/19 | e) | - | a) | 65925.03 | a) | 100% | c) | 100% | a) | 16 | Completed | 1
| 003 | [7 empty] | b) | Crucio | b) | 03/22/19 | f) | - | b) | 65925.03 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | CALAFA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
|  |  | Asuncion -Monte Carlo-Del Pilar |  |  | Road Maintenance | 9.93 | MBA | a) | 474102.88 | a) | 01/03/19 | e) | - | a) | 474102.88 | a) | 100% | c) | 100% | a) | 15 | Completed | 1
| 005 | [7 empty] | b) | Crucio | b) | 01/03/19 | f) | - | b) | 474102.88 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 240274.49 | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | Asuncion -Monte Carlo-Del Pilar |  |  | Road Maintenance | 9.93 | CBRMC | a) | 355524.28 | a) | 01/03/19 | e) | - | a) | 355524.28 | a) | 100% | c) | 100% | a) | 16 | Completed
| 005 | [7 empty] | b) | Crucio | b) | 03/22/19 | f) | - | b) | 355524.28 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | MAHAYAHAY IFA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
|  |  | Jct. Highway Canatan-Jct. Highway Magatos |  |  | Road Maintenance | 4.85 | MBA | a) | 209808.59 | a) | 01/03/19 | e) | - | a) | 209808.59 | a) | 100% | c) | 100% | a) | 15 | Completed | 1
| 006 | [7 empty] | b) | Crucio | b) | 02/18/19 | f) | - | b) | 209808.59 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 80652.8 | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | Jct. Highway Canatan-Jct. Highway Magatos |  |  | Road Maintenance | 4.85 | CBRMC | a) | 162458.12 | a) | 01/03/19 | e) | - | a) | 162458.12 | a) | 100% | c) | 100% | a) | 16 | Completed | 1
| 006 | [7 empty] | b) | Crucio | b) | 03/22/19 | f) | - | b) | 162458.12 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | CAMODA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
1
|  |  | Sta. Felomina-San Roque |  |  | Road Maintenance | 7.68 | MBA | a) | 147439.63 | a) | 01/03/19 | e) | - | a) | 147439.63 | a) | 100% | c) | 100% | a) | 15 | Completed
| 008 | [7 empty] | b) | Crucio | b) | 01/16/19 | f) | - | b) | 147439.63 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 63806.67 | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | Sta. Felomina-San Roque |  |  | Road Maintenance | 7.68 | CBRMC | a) | 261345.67 | a) | 01/03/19 | e) | - | a) | 261345.67 | a) | 100% | c) | 100% | a) | 16 | Completed | 1
| 008 | [7 empty] | b) | Crucio | b) | 03/25/19 | f) | - | b) | 261345.67 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | STAFFA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
|  |  | Saug-Sonlon-Bdy Longanapan |  |  | Road Maintenance | 11.6 | MBA | a) | 568486.36 | a) | 01/03/19 | e) | - | a) | 568486.36 | a) | 100% | c) | 100% | a) | 15 | Completed | 1
| 010 | [7 empty] | b) | Crucio | b) | 01/16/19 | f) | - | b) | 568486.36 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 262900.22 | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | Saug-Sonlon-Bdy Longanapan |  |  | Road Maintenance | 11.6 | CBRMC | a) | 185565.56 | a) | 01/03/19 | e) | - | a) | 185565.56 | a) | 100% | c) | 100% | a) | 16 | Completed | 1
| 010 | [7 empty] | b) | Crucio | b) | 03/26/19 | f) | - | b) | 185565.56 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | BINANCIAN LIVESTOCK AFA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
|  |  | Jct. New Visayas-Buan |  |  | Road Maintenance | 2.99 | MBA | a) | 79238.27 | a) | 01/03/19 | e) | - | a) | 79238.27 | a) | 100% | c) | 100% | a) | 15 | Completed | 1
| 011 | [7 empty] | b) | Crucio | b) | 02/18/19 | f) | - | b) | 79238.27 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 14682.85 | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | Jct. New Visayas-Buan |  |  | Road Maintenance | 2.99 | CBRMC | a) | 101242.01 | a) | 01/03/19 | e) | - | a) | 101242.01 | a) | 100% | c) | 100% | a) | 16 | Completed | 1
| 011 | [7 empty] | b) | Crucio | b) | 03/22/19 | f) | - | b) | 101242.01 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | BUAN IFA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
|  |  | San Vicente - Butay |  |  | Road Maintenance | 7.52 | MBA | a) | 209624.2 | a) | 01/03/19 | e) | - | a) | 209624.2 | a) | 100% | c) | 100% | a) | 15 | Completed | 1
| 013 | [7 empty] | b) | Crucio | b) | 02/18/19 | f) | - | b) | 209624.2 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 56,080.29 | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | San Vicente - Butay |  |  | Road Maintenance | 7.52 | CBRMC | a) | 227205.88 | a) | 01/03/19 | e) | - | a) | 227205.88 | a) | 100% | c) | 100% | a) | 16 | Completed | 1
| 013 | [7 empty] | b) | Crucio | b) | 03/27/19 | f) | - | b) | 227205.88 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | SVMODA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
|  |  | Jct. Highway Doña Andrea - Capungagan |  |  | Road Maintenance | 8.7 | MBA | a) | 230835.16 | a) | 01/03/19 | e) | - | a) | 230835.16 | a) | 100% | c) | 100% | a) | 15 | Completed | 1
| 014 | [7 empty] | b) | Crucio | b) | 02/18/19 | f) | - | b) | 230835.16 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 60,629.26 | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
1
|  |  | Jct. Highway Doña Andrea - Capungagan |  |  | Road Maintenance | 8.7 | CBRMC | a) | 294308.14 | a) | 01/03/19 | e) | - | a) | 294308.14 | a) | 100% | c) | 100% | a) | 16 | Completed
| 014 | [7 empty] | b) | Crucio | b) | 03/28/19 | f) | - | b) | 294308.14 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | CAPUNGAGAN MPC | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
|  |  | Semong-Palma Gil |  |  | Road Maintenance | 2.73 | MBA | a) | 147289.98 | a) | 01/03/19 | e) | - | a) | 147289.98 | a) | 100% | c) | 100% | a) | 15 | Completed | 1
| 018 | [7 empty] | b) | Crucio | b) | 02/18/19 | f) | - | b) | 147289.98 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 71745.43 | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
1
|  |  | Semong-Palma Gil |  |  | Road Maintenance | 2.73 | CBRMC | a) | 49186.05 | a) | 01/03/19 | e) | - | a) | 49186.05 | a) | 100% | c) | 100% | a) | 16 | Completed
| 018 | [7 empty] | b) | Crucio | b) | 03/22/19 | f) | - | b) | 49186.05 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | PALMA GIL FA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
|  |  | Daligdigon - Dagohoy |  |  | Road Maintenance | 3.34 | MBA | a) | 148835.45 | a) | 01/03/19 | e) | - | a) | 148835.45 | a) | 100% | c) | 100% | a) | - | Completed | 1
| 020 | [7 empty] | b) | Crucio | b) | - | f) | - | b) | 148835.45 | b) | - | d) | - | b) | - |  | 1
[9 empty] | c) | PEO | c) | - | g) | 2019-12-31 | c) | - | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | Daligdigon - Dagohoy |  |  | Road Maintenance | 3.34 | CBRMC | a) | 68279.5 | a) | 01/03/19 | e) | - | a) | 68279.5 | a) | 100% | c) | 100% | a) | 16 | Completed | 1
| 020 | [7 empty] | b) | Crucio | b) | 03/22/19 | f) | - | b) | 68279.5 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | PALMA GIL FA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
|  |  | Jct. Sampao-Bdry. Mamacao |  |  | Road Maintenance | 4.98 | MBA | a) | 154200.78 | a) | 01/03/19 | e) | - | a) | 154200.78 | a) | 100% | c) | 100% | a) | 15 | Completed | 1
| 025 | [7 empty] | b) | Crucio | b) | 02/18/19 | f) | - | b) | 154200.78 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 24,296.87 | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | Jct. Sampao-Bdry. Mamacao |  |  | Road Maintenance | 4.98 | CBRMC | a) | 169521.51 | a) | 01/03/19 | e) | - | a) | 169521.51 | a) | 100% | c) | 100% | a) | 16 | Completed | 1
| 025 | [7 empty] | b) | Crucio | b) | 03/26/19 | f) | - | b) | 169521.51 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | AMS KAPALONG | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
|  |  | Jct. Highway Luna-Mamacao-Narra |  |  | Road Maintenance | 9.17 | MBA | a) | 357957.66 | a) | 01/03/19 | e) | - | a) | 357957.66 | a) | 100% | c) | 100% | a) | 15 | Completed | 1
| 026 | [7 empty] | b) | Crucio | b) | 02/18/19 | f) | - | b) | 357957.66 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 127,996.16 | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | Jct. Highway Luna-Mamacao-Narra |  |  | Road Maintenance | 9.17 | CBRMC | a) | 313143.91 | a) | 01/03/19 | e) | - | a) | 313143.91 | a) | 100% | c) | 100% | a) | 16 | Completed | 1
| 026 | [7 empty] | b) | Crucio | b) | 03/26/19 | f) | - | b) | 313143.91 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | AMS KAPALONG | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
|  |  | Jct. Gabuyan-Katipunan-Bucana |  |  | Road Maintenance | 5.89 | MBA | a) | 294403.23 | a) | 01/03/19 | e) | - | a) | 294403.23 | a) | 100% | c) | 100% | a) | 15 | Completed | 1
| 027 | [7 empty] | b) | Crucio | b) | 02/18/19 | f) | - | b) | 294403.23 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 126,179.97 | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | Jct. Gabuyan-Katipunan-Bucana |  |  | Road Maintenance | 5.89 | CBRMC | a) | 129495.6 | a) | 01/03/19 | e) | - | a) | 129495.6 | a) | 100% | c) | 100% | a) | 16 | Completed | 1
| 027 | [7 empty] | b) | Crucio | b) | 03/26/19 | f) | - | b) | 129495.6 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | MANGULIBAS FA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
|  |  | Capungagan-Mabuhay-Pandulian |  |  | Road Maintenance | 5.57 | MBA | a) | 294917.73 | a) | 01/03/19 | e) | - | a) | 294917.73 | a) | 100% | c) | 100% | a) | 15 | Completed | 1
| 028 | [7 empty] | b) | Crucio | b) | 02/18/19 | f) | - | b) | 294917.73 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
1
|  |  | Capungagan-Mabuhay-Pandulian |  |  | Road Maintenance | 5.57 | CBRMC | a) | 105950.95 | a) | 01/03/19 | e) | - | a) | 105950.95 | a) | 100% | c) | 100% | a) | 16 | Completed
| 028 | [7 empty] | b) | Crucio | b) | 03/28/19 | f) | - | b) | 105950.95 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | CAPUNGAGAN MPC | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
|  |  | Florida - New Boholano |  |  | Road Maintenance | 2.54 | MBA | a) | 95863.17 | a) | 01/03/19 | e) | - | a) | 95863.17 | a) | 100% | c) | 100% | a) | 15 | Completed | 1
| 030 | [7 empty] | b) | Crucio | b) | 02/18/19 | f) | - | b) | 95863.17 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 31,418.99 | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | Florida - New Boholano |  |  | Road Maintenance | 2.54 | CBRMC | a) | 47425.27 | a) | 01/03/19 | e) | - | a) | 47425.27 | a) | 100% | c) | 100% | a) | 16 | Completed | 1
| 030 | [7 empty] | b) | Crucio | b) | 03/28/19 | f) | - | b) | 47425.27 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | SUPRA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
|  |  | Jct. New Boholano - New Loon |  |  | Road Maintenance | 4.77 | MBA | a) | 140549.84 | a) | 01/03/19 | e) | - | a) | 140549.84 | a) | 100% | c) | 100% | a) | 15 | Completed | 1
| 031 | [7 empty] | b) | Crucio | b) | 02/18/19 | f) | - | b) | 140549.84 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 40,056.38 | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | Jct. New Boholano - New Loon |  |  | Road Maintenance | 4.77 | CBRMC | a) | 169521.51 | a) | 01/03/19 | e) | - | a) | 169521.51 | a) | 100% | c) | 100% | a) | 16 | Completed | 1
| 031 | [7 empty] | b) | Crucio | b) | 03/28/19 | f) | - | b) | 169521.51 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | NEW LOON FA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
|  |  | Florida-Suaon-Jct. Gupitan |  |  | Road Maintenance | 15.57 | MBA | a) | 707038.05 | a) | 01/03/19 | e) | - | a) | 707038.05 | a) | 100% | c) | 100% | a) | 15 | Completed | 1
| 032 | [7 empty] | b) | Crucio | b) | 01/16/19 | f) | - | b) | 707038.05 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 226,.062.60 | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | Florida-Suaon-Jct. Gupitan |  |  | Road Maintenance | 15.57 | CBRMC | a) | 419094.85 | a) | 01/03/19 | e) | - | a) | 419094.85 | a) | 100% | c) | 100% | a) | 16 | Completed | 1
| 032 | [7 empty] | b) | Crucio | b) | 03/28/19 | f) | - | b) | 419094.85 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | SUPRA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
|  |  | Km. 15, Kipalili-New Loon |  |  | Road Maintenance | 6.93 | MBA | a) | 367659.97 | a) | 01/03/19 | e) | - | a) | 367659.97 | a) | 100% | c) | 100% | a) | 15 | Completed | 1
| 034 | [7 empty] | b) | Crucio | b) | 02/01/19 | f) | - | b) | 367659.97 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 112,175.78 | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | Km. 15, Kipalili-New Loon |  |  | Road Maintenance | 6.93 | CBRMC | a) | 237801.01 | a) | 01/03/19 | e) | - | a) | 237801.01 | a) | 100% | c) | 100% | a) | 16 | Completed | 1
| 034 | [7 empty] | b) | Crucio | b) | 03/26/19 | f) | - | b) | 237801.01 | b) | - | d) | - | b) | 480 |  | 1
[9 empty] | c) | KIPALILI FA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
|  |  | Jct. Suaon-Libuton |  |  | Road Maintenance | 7.26 | MBA | a) | 44015.68 | a) | 01/03/19 | e) | - | a) | 44015.68 | a) | 100% | c) | 100% | a) | 15 | Completed
| 035 | [7 empty] | b) | Crucio | b) | 01/16/19 | f) | - | b) | 44015.68 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 24,980.86 | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | Jct. Suaon-Libuton |  |  | Road Maintenance | 7.26 | CBRMC | a) | 91664.91 | a) | 01/03/19 | e) | - | a) | 91664.91 | a) | 100% | c) | 100% | a) | 16 | Completed | 1
| 035 | [7 empty] | b) | Crucio | b) | 03/22/19 | f) | - | b) | 91664.91 | b) | - | d) | - | b) | 480 |  | 1
[9 empty] | c) | AALLI | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
1
|  |  | Datu Balong - Pinamuno |  |  | Road Maintenance | 2.74 | MBA | a) | 95458.24 | a) | 01/03/19 | e) | - | a) | 95458.24 | a) | 100% | c) | 100% | a) | 15 | Completed
| 040 | [7 empty] | b) | Crucio | b) | 03/01/19 | f) | - | b) | 95458.24 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 12,625.00 | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | Datu Balong - Pinamuno |  |  | Road Maintenance | 2.74 | CBRMC | a) | 63570.57 | a) | 01/03/19 | e) | - | a) | 63570.57 | a) | 100% | c) | 100% | a) | 16 | Completed | 1
| 040 | [7 empty] | b) | Crucio | b) | 03/28/19 | f) | - | b) | 63570.57 | b) | - | d) | - | b) | 480 |  | 1
[9 empty] | c) | DATU BALONG FA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
|  |  | Sawata - Mamangan - Pinamuno |  |  | Road Maintenance | 14.48 | MBA | a) | 545390.17 | a) | 01/03/19 | e) | - | a) | 545390.17 | a) | 100% | c) | 100% | a) | 15 | Completed | 1
| 041 | [7 empty] | b) | Crucio | b) | 02/01/19 | f) | - | b) | 545390.17 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 196,076.60 | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | Sawata - Mamangan - Pinamuno |  |  | Road Maintenance | 14.48 | CBRMC | a) | 508564.54 | a) | 01/03/19 | e) | - | a) | 508564.54 | a) | 100% | c) | 100% | a) | 16 | Completed | 1
| 041 | [7 empty] | b) | Crucio | b) | 03/22/19 | f) | - | b) | 508564.54 | b) | - | d) | - | b) | 480 |  | 1
[9 empty] | c) | SAWATA DFA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
|  |  | Igangon - Sawata |  |  | Road Maintenance | 9.66 | MBA | a) | 497447.77 | a) | 01/03/19 | e) | - | a) | 497447.77 | a) | 100% | c) | 100% | a) | 15 | Completed | 1
| 042 | [7 empty] | b) | Crucio | b) | 02/01/19 | f) | - | b) | 497447.77 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | Igangon - Sawata |  |  | Road Maintenance | 9.66 | CBRMC | a) | 197775.1 | a) | 01/03/19 | e) | - | a) | 197775.1 | a) | 100% | c) | 100% | a) | 16 | Completed | 1
| 042 | [7 empty] | b) | Crucio | b) | 03/22/19 | f) | - | b) | 197775.1 | b) | - | d) | - | b) | 480 |  | 1
[9 empty] | c) | SAWATA DFA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
|  |  | New Corella - Sto. Niño - Macgum |  |  | Road Maintenance | 17.11 | MBA | a) | 606294.08 | a) | 01/03/19 | e) | - | a) | 606294.08 | a) | 100% | c) | 100% | a) | 15 | Completed | 1
| 044 | [7 empty] | b) | Crucio | b) | 01/03/19 | f) | - | b) | 606294.08 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 246,619.77 | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | New Corella - Sto. Niño - Macgum |  |  | Road Maintenance | 17.11 | CBRMC | a) | 308434.97 | a) | 01/03/19 | e) | - | a) | 308434.97 | a) | 100% | c) | 100% | a) | 16 | Completed | 1
| 044 | [7 empty] | b) | Crucio | b) | 03/26/19 | f) | - | b) | 308434.97 | b) | - | d) | - | b) | 480 |  | 1
[9 empty] | c) | SAN ISIDRO FA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
|  |  | Tagaytay - Buan |  |  | Road Maintenance | 4.92 | MBA | a) | 173197.37 | a) | 01/03/19 | e) | - | a) | 173197.37 | a) | 100% | c) | 100% | a) | 15 | Completed | 1
| 045 | [7 empty] | b) | Crucio | b) | 03/18/19 | f) | - | b) | 173197.37 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 26254.58 | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | Tagaytay - Buan |  |  | Road Maintenance | 4.92 | CBRMC | a) | 131850.07 | a) | 01/03/19 | e) | - | a) | 131850.07 | a) | 100% | c) | 100% | a) | 16 | Completed | 1
| 045 | [7 empty] | b) | Crucio | b) | 03/22/19 | f) | - | b) | 131850.07 | b) | - | d) | - | b) | 480 |  | 1
[9 empty] | c) | BUAN IFA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
|  |  | limbaan - Sto. Niño |  |  | Road Maintenance | 3.19 | MBA | a) | 153706.77 | a) | 01/03/19 | e) | - | a) | 153706.77 | a) | 100% | c) | 100% | a) | 15 | Completed | 1
| 049 | [7 empty] | b) | Crucio | b) | 03/01/19 | f) | - | b) | 153706.77 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 32534.49 | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | limbaan - Sto. Niño |  |  | Road Maintenance | 3.19 | CBRMC | a) | 53657.51 | a) | 01/03/19 | e) | - | a) | 53657.51 | a) | 100% | c) | 100% | a) | - | Completed | 1
| 049 | [7 empty] | b) | Crucio | b) | - | f) | - | b) | 53657.51 | b) | - | d) | - | b) | - |  | 1
[9 empty] | c) | - | c) | - | g) | 2019-12-31 | c) | - | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | Del Pilar - Jct. Silangan |  |  | Road Maintenance | 4.17 | MBA | a) | 187097.4 | a) | 01/03/19 | e) | - | a) | 187097.4 | a) | 100% | c) | 100% | a) | 15 | Completed | 1
| 051 | [7 empty] | b) | Crucio | b) | 03/18/19 | f) | - | b) | 187097.4 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 94181.74 | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | Del Pilar - Jct. Silangan |  |  | Road Maintenance | 4.17 | CBRMC | a) | 113014.34 | a) | 01/03/19 | e) | - | a) | 113014.34 | a) | 100% | c) | 100% | a) | 16 | Completed | 1
| 051 | [7 empty] | b) | Crucio | b) | 03/26/19 | f) | - | b) | 113014.34 | b) | - | d) | - | b) | 480 |  | 1
[9 empty] | c) | DURIAN DACUDAO | c) | 12/31/19 | g) | - | c) | - | [7 empty] | 1
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
|  |  | New Corella - New Sambog - Silangan |  |  | Road Maintenance | 5.1 | MBA | a) | 201994.35 | a) | 01/03/19 | e) | - | a) | 201994.35 | a) | 100% | c) | 100% | a) | 15 | Completed | 1
| 052 | [7 empty] | b) | Crucio | b) | 03/01/19 | f) | - | b) | 201994.35 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 63402.48 | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | New Corella - New Sambog - Silangan |  |  | Road Maintenance | 5.1 | CBRMC | a) | 131850.07 | a) | 01/03/19 | e) | - | a) | 131850.07 | a) | 100% | c) | 100% | a) | 16 | Completed | 1
| 052 | [7 empty] | b) | Crucio | b) | 03/26/19 | f) | - | b) | 131850.07 | b) | - | d) | - | b) | 480 |  | 1
[9 empty] | c) | DURIAN DACUDAO | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
|  |  | Sta. Fe - Del Monte |  |  | Road Maintenance | 3.34 | MBA | a) | 37923.51 | a) | 01/03/19 | e) | - | a) | 37923.51 | a) | 100% | c) | 100% | a) | 15 | Completed | 1
| 056 | [7 empty] | b) | Crucio | b) | 03/18/19 | f) | - | b) | 37923.51 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 36595.13 | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | Sta. Fe - Del Monte |  |  | Road Maintenance | 3.34 | CBRMC | a) | 70633.96 | a) | 01/03/19 | e) | - | a) | 70633.96 | a) | 100% | c) | 100% | a) | 16 | Completed | 1
| 056 | [7 empty] | b) | Crucio | b) | 03/21/19 | f) | - | b) | 70633.96 | b) | - | d) | - | b) | 480 |  | 1
[9 empty] | c) | DEL MONTE CACAO | c) | 12/31/19 | g) | 2019-12-31 | c) | 4,872.18 | [7 empty] | 1
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
|  |  | New Corella - New Bohol |  |  | Road Maintenance | 11.54 | MBA | a) | 356226.67 | a) | 01/03/19 | e) | - | a) | 356226.67 | a) | 100% | c) | 100% | a) | 15 | Completed
| 058 | [7 empty] | b) | Crucio | b) | 02/01/19 | f) | - | b) | 356226.67 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 110,982.71 | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | New Corella - New Bohol |  |  | Road Maintenance | 11.54 | CBRMC | a) | 190711.7 | a) | 01/03/19 | e) | - | a) | 190711.7 | a) | 100% | c) | 100% | a) | 16 | Completed | 1
| 058 | [7 empty] | b) | Crucio | b) | 03/22/19 | f) | - | b) | 190711.7 | b) | - | d) | - | b) | 480 |  | 1
[9 empty] | c) | SAN JOSE COCONUT | c) | 12/31/19 | g) | 2019-12-31 | c) | 5,847.18 | [7 empty] | 1
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
1
|  |  | Jct. Carcor - Prk. 9 Bagsak |  |  | Road Maintenance | 2.5 | MBA | a) | 108618.49 | a) | 01/03/19 | e) | - | a) | 108618.49 | a) | 100% | c. | 100% | a) | 15 | Completed
| 059 | [7 empty] | b) | Crucio | b) | 03/01/19 | f) | - | b) | 108618.49 | b) | - | d) |  | b) | 480 |  | 1
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 79952.88 | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
1
|  |  | Jct. Carcor - Prk. 9 Bagsak |  |  | Road Maintenance | 2.5 | CBRMC | a) | 42284.76 | a) | 01/03/19 | e) | - | a) | 42284.76 | a) | 100% | c) | 100% | a) | 16 | Completed
| 059 | [7 empty] | b) | Crucio | b) | 03/22/19 | f) | - | b) | 42284.76 | b) | - | d) | - | b) | 480 |  | 1
[9 empty] | c) | CARCOR MOTOR | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
|  |  | Carcor - Jct. Kauswagan |  |  | Road Maintenance | 4.32 | MBA | a) | 264514.71 | a) | 01/03/19 | e) | - | a) | 264514.71 | a) | 100% | c) | 100% | a) | 15 | Completed | 1
| 060 | [7 empty] | b) | Crucio | b) | 03/18/19 | f) | - | b) | 264514.71 | b) | - | d) |  | b) | 450 |  | 1
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 80733.11 | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | Carcor - Jct. Kauswagan |  |  | Road Maintenance | 4.32 | CBRMC | a) | 48398.27 | a) | 01/03/19 | e) | - | a) | 48398.27 | a) | 100% | c) | 100% | a) | 16 | Completed
| 060 | [7 empty] | b) | Crucio | b) | 03/22/19 | f) | - | b) | 48398.27 | b) | - | d) | - | b) | 480 |  | 1
[9 empty] | c) | CARCOR MOTOR | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
|  |  | Del Pilar - Prk 9 Bagsak - San Jose |  |  | Road Maintenance | 4.99 | MBA | a) | 170215.76 | a) | 01/03/19 | e) | - | a) | 170215.76 | a) | 100% | c) | 100% | a) | 15 | Completed | 1
| 061 | [7 empty] | b) | Crucio | b) | 03/01/19 | f) | - | b) | 170215.76 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 87595.63 | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | Del Pilar - Prk 9 Bagsak - San Jose |  |  | Road Maintenance | 4.99 | CBRMC | a) | 223674.22 | a) | 01/03/19 | e) | - | a) | 223674.22 | a) | 100% | c) | 100% | a) | 16 | Completed | 1
| 061 | [7 empty] | b) | Crucio | b) | 03/22/19 | f) | - | b) | 223674.22 | b) | - | d) | - | b) | 480 |  | 1
[9 empty] | c) | SAN JOSE COCONUT | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
|  |  | San Juan - New Talisay |  |  | Road Maintenance | 5.13 | MBA | a) | 306261.25 | a) | 01/03/19 | e) | - | a) | 306261.25 | a) | 100% | c) | 100% | a) | 15 | Completed | 1
| 063 | [7 empty] | b) | Crucio | b) | 02/01/19 | f) | - | b) | 306261.25 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 85123.48 | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | San Juan - New Talisay |  |  | Road Maintenance | 5.13 | CBRMC | a) | 93906.31 | a) | 01/03/19 | e) | - | a) | 93906.31 | a) | 100% | c) | 100% | a) | 16 | Completed
| 063 | [7 empty] | b) | Crucio | b) | 03/26/19 | f) | - | b) | 93906.31 | b) | - | d) | - | b) | 480 |  | 1
[9 empty] | c) | NEW TALISAY IAWA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
|  |  | San Juan - kauswagan - New Cortez |  |  | Road Maintenance | 3.22 | MBA | a) | 187879.04 | a) | 01/03/19 | e) | - | a) | 187879.04 | a) | 100% | c) | 100% | a) | 15 | Completed | 1
| 064 | [7 empty] | b) | Crucio | b) | 03/18/19 | f) | - | b) | 187879.04 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 3,025.00 | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | San Juan - kauswagan - New Cortez |  |  | Road Maintenance | 3.22 | CBRMC | a) | 63298.26 | a) | 01/03/19 | e) | - | a) | 63298.26 | a) | 100% | c) | 100% | a) | 16 | Completed
| 064 | [7 empty] | b) | Crucio | b) | 03/22/19 | f) | - | b) | 63298.26 | b) | - | d) | - | b) | 480 |  | 1
[9 empty] | c) | SAN JOSE COCONUT | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
|  |  | New Bohol - Jct. El Unido |  |  | Road Maintenance | 2.12 | MBA | a) | 54989.06 | a) | 01/03/19 | e) | - | a) | 54989.06 | a) | 100% | c) | 100% | a) | 15 | Completed
| 065 | [7 empty] | b) | Crucio | b) | 03/01/19 | f) | - | b) | 54989.06 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 21021.99 | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | New Bohol - Jct. El Unido |  |  | Road Maintenance | 2.12 | CBRMC | a) | 58861.64 | a) | 01/03/19 | e) | - | a) | 58861.64 | a) | 100% | c) | 100% | a) | 16 | Completed | 1
| 065 | [7 empty] | b) | Crucio | b) | 03/26/19 | f) | - | b) | 58861.64 | b) | - | d) | - | b) | 480 |  | 1
[9 empty] | c) | MANDISKAB TRIBAL | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
1
|  |  | New Corella - El unido - Jct. Mesaoy |  |  | Road Maintenance | 8.63 | MBA | a) | 388002.46 | a) | 01/03/19 | e) | - | a) | 388002.46 | a) | 100% | c) | 100% | a) | 15 | Completed
| 066 | [7 empty] | b) | Crucio | b) | 02/11/19 | f) | - | b) | 388002.46 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 58142.76 | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | New Corella - El unido - Jct. Mesaoy |  |  | Road Maintenance | 8.63 | CBRMC | a) | 233092.08 | a) | 01/03/19 | e) | - | a) | 233092.08 | a) | 100% | c) | 100% | a) | 16 | Completed | 1
| 066 | [7 empty] | b) | Crucio | b) | 03/26/19 | f) | - | b) | 233092.08 | b) | - | d) | - | b) | 480 |  | 1
[9 empty] | c) | MANDISKAB TRIBAL | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
|  |  | Mesaoy - Dasing |  |  | Road Maintenance | 1.39 | MBA | a) | 29749.5 | a) | 01/03/19 | e) | - | a) | 29749.5 | a) | 100% | c) | 100% | a) | 15 | Completed | 1
| 067 | [7 empty] | b) | Crucio | b) | 03/18/19 | f) | - | b) | 29749.5 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 10000 | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | Mesaoy - Dasing |  |  | Road Maintenance | 1.39 | CBRMC | a) | 54152.71 | a) | 01/03/19 | e) | - | a) | 54152.71 | a) | 100% | c) | 100% | a) | 16 | Completed | 1
| 067 | [7 empty] | b) | Crucio | b) | 03/26/19 | f) | - | b) | 54152.71 | b) | - | d) | - | b) | 480 |  | 1
[9 empty] | c) | MANDISKAB TRIBAL | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
|  |  | Jct. San Juan - Jct. Mesaoy |  |  | Road Maintenance | 1.82 | MBA | a) | 106788.95 | a) | 01/03/19 | e) | - | a) | 106788.95 | a) | 100% | c) | 100% | a) | 15 | Completed | 1
| 068 | [7 empty] | b) | Crucio | b) | 03/01/19 | f) | - | b) | 106788.95 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 17502.68 | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | Jct. San Juan - Jct. Mesaoy |  |  | Road Maintenance | 1.82 | CBRMC | a) | 35180.83 | a) | 01/03/19 | e) | - | a) | 35180.83 | a) | 100% | c) | 100% | a) | 16 | Completed | 1
| 068 | [7 empty] | b) | Crucio | b) | 03/26/19 | f) | - | b) | 35180.83 | b) | - | d) | - | b) | 480 |  | 1
[9 empty] | c) | MANDISKAB TRIBAL | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
|  |  | Mesaoy - Jct. Mahayahay |  |  | Road Maintenance | 4.6 | MBA | a) | 146984.46 | a) | 01/03/19 | e) | - | a) | 146984.46 | a) | 100% | c) | 100% | a) | 15 | Completed | 1
| 069 | [7 empty] | b) | Crucio | b) | 03/18/19 | f) | - | b) | 146984.46 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 7618.27 | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | Mesaoy - Jct. Mahayahay |  |  | Road Maintenance | 4.6 | CBRMC | a) | 160103.65 | a) | 01/03/19 | e) | - | a) | 160103.65 | a) | 100% | c) | 100% | a) | 16 | Completed
| 069 | [7 empty] | b) | Crucio | b) | 03/22/19 | f) | - | b) | 160103.65 | b) | - | d) | - | b) | 480 |  | 1
[9 empty] | c) | MAHAYAHAY IFA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
|  |  | Mesaoy - New bohol |  |  | Road Maintenance | 5.36 | MBA | a) | 165361.13 | a) | 01/03/19 | e) | - | a) | 165361.13 | a) | 100% | c) | 100% | a) | 15 | Completed
| 070 | [7 empty] | b) | Crucio | b) | 03/01/19 | f) | - | b) | 165361.13 | b) | - | d) | - | b) | 480 |  | 1
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 2543.9 | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | Mesaoy - New bohol |  |  | Road Maintenance | 5.36 | CBRMC | a) | 224851.45 | a) | 01/03/19 | e) | - | a) | 224851.45 | a) | 100% | c) | 100% | a) | 16 | Completed
| 070 | [7 empty] | b) | Crucio | b) | 03/26/19 | f) | - | b) | 224851.45 | b) | - | d) | - | b) | 480 |  | 1
[9 empty] | c) | MANDISKAB TRIBAL | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
|  |  | Bdry. Tagum - Baca - New Corella |  |  | Road Maintenance | 13.01 | MBA | a) | 217182.9 | a) | 01/03/19 | e) | - | a) | 217182.9 | a) | 100% | c) | 100% | a) | 15 | Completed | 1
| 071 | [7 empty] | b) | Crucio | b) | 03/18/19 | f) | - | b) | 217182.9 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 19550 | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | Bdry. Tagum - Baca - New Corella |  |  | Road Maintenance | 13.01 | CBRMC | a) | 214256.36 | a) | 01/03/19 | e) | - | a) | 214256.36 | a) | 100% | c) | 100% | a) | 16 | Completed | 1
| 071 | [7 empty] | b) | Crucio | b) | 03/26/19 | f) | - | b) | 214256.36 | b) | - | d) | - | b) | 480 |  | 1
[9 empty] | c) | DURIAN DACUDAO | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
|  |  | Prk. 1, Maunlom - Prk. 6 Maunlom Road |  |  | Road Maintenance | 3.56 | MBA | a) | 150912.87 | a) | 01/03/19 | e) | - | a) | 150912.87 | a) | 100% | c) | 100% | a) | 15 | Completed | 1
| 147 | [7 empty] | b) | Crucio | b) | 03/01/19 | f) | - | b) | 150912.87 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 23025 | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | Prk. 1, Maunlom - Prk. 6 Maunlom Road |  |  | Road Maintenance | 3.56 | CBRMC | a) | 63973.36 | a) | 01/03/19 | e) | - | a) | 63973.36 | a) | 100% | c) | 100% | a) | 16 | Completed | 1
| 147 | [7 empty] | b) | Crucio | b) | 03/22/19 | f) | - | b) | 63973.36 | b) | - | d) | - | b) | 480 |  | 1
[9 empty] | c) | THE BEST VEGETABLE | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
1
|  |  | New Visayas - Binancian |  |  | Road Maintenance | 7.77 | MBA | a) | 14814.34 | a) | 01/03/19 | e) | - | a) | 14814.34 | a) | 100% | c) | 100% | a) | 15 | Completed
| 149 | [7 empty] | b) | Crucio | b) | 03/18/19 | f) | - | b) | 14814.34 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 5,000.00 | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | New Visayas - Binancian |  |  | Road Maintenance | 7.77 | CBRMC | a) | 129495.6 | a) | 01/03/19 | e) | - | a) | 129495.6 | a) | 100% | c) | 100% | a) | 16 | Completed | 1
| 149 | [7 empty] | b) | Crucio | b) | 03/22/19 | f) | - | b) | 129495.6 | b) | - | d) | - | b) | 480 |  | 1
[9 empty] | c) | BUAN IFA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
|  |  | Datu Balong - Prk. Mamalian |  |  | Road Maintenance | 3.46 | MBA | a) | 117454.89 | a) | 01/03/19 | e) | - | a) | 117454.89 | a) | 100% | c) | 39.37% | a) | 15 | Completed | 1
| 150 | [7 empty] | b) | Crucio | b) | 03/18/19 | f) | - | b) | 117454.89 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 10115 | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | Datu Balong - Prk. Mamalian |  |  | Road Maintenance | 3.46 | CBRMC | a) | 59264.42 | a) | 01/03/19 | e) | - | a) | 59264.42 | a) | 100% | c) | 100% | a) | 16 | Completed | 1
| 150 | [7 empty] | b) | Crucio | b) | 03/28/19 | f) | - | b) | 59264.42 | b) | - | d) | - | b) | 480 |  | 1
[9 empty] | c) | DATU BALONG FA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
| A.2 GENERAL FUND CY 2019 |  |  |  |  | Road Maintenance | KM | MBA/CBRMC | a) | 11,618,834.00 | a) | 01/03/19 | e) | - | a) | 11,618,834.00 | a) | 66% | c) | 66% | a) | 42 | See list of Provincial Roads
| Road ID |  | 1. Maintenance Of Various Prov'l. Roads and Bridges Dist 2 |  |  |  | 288.26 |  | b) | Matuguinas | b) | 01/03/19 | f) | - | b) | 11,618,834.00 | b) | - | d) | - | b) | 924 |  | FS
[9 empty] | c) | PEO/CBRMC | c) | 12/31/19 | g) | - | c) | - | [7 empty] | AC
| 11DAN | [9 empty] | d) | - | [11 empty] | AC
[9 empty] | d) | 261 days | d) | - | [11 empty] | AC
|  |  | Cebulano - Mangalcal |  |  | Road Maintenance | 4.17 | MBA | a) | 142161.87 | a) | 01/03/19 | e) | - | a) | 142161.87 | a) | 100% | c) | 100% | a) | 9 | Completed | AC
|  | 073 | [6 empty] | b) | Clar | b) | 2019-01-15 | f) | - | b) | 142161.87 | b) | - | d) | - | b) | 18 |  | 2
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 118,609.29 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | Tubod - basa - Mangalcal |  |  | Road Maintenance | 3.93 | MBA | a) | 156875.9 | a) | 01/03/19 | e) | - | a) | 156875.9 | a) | 100% | c) | 100% | a) | 9 | Completed | 2
| 074 | [7 empty] | b) | Clar | b) | 2019-01-15 | f) | - | b) | 156875.9 | b) | - | d) | - | b) | 18 |  | 2
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 143,372.65 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | Upper Mangalcal - Lower Mangalcal |  |  | Road Maintenance | 2.43 | CBRMC | a) | 79237.14 | a) | 01/03/19 | e) | - | a) | 79237.14 | a) | 100% | c) | 100% | a) | 9 | Completed | 2
| 078 | [7 empty] | b) | Clar | b) | 2019-01-14 | f) | - | b) | 79237.14 | b) | - | d) | - | b) | 27 |  | 2
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 69,430.97 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | Jct. Highway Carmen - Mangalcal - Tubod |  |  | Road Maintenance | 11.34 | MBA | a) | 463135.67 | a) | 01/03/19 | e) | - | a) | 463135.67 | a) | 100% | c) | 100% | a) | 9 | Completed | 2
| 082 | [7 empty] | b) | Clar | b) | 01/10/19 | f) | - | b) | 463135.67 | b) | - | d) | - | b) | 45 |  | 2
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 170,106.43 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | Jct. Highway Carmen - Mangalcal - Tubod |  |  | Road Maintenance | 11.34 | CBRMC | a) | 253557.37 | a) | 01/03/19 | e) | - | a) | 253557.37 | a) | 100% | c) | 100% | a) | 10 | Completed | 2
| 082 | [7 empty] | b) | Maligro | b) | 03/25/19 | f) | - | b) | 253557.37 | b) | - | d) | - | b) | 40 |  | 2
[9 empty] | c) | TUBOD CENTRO LOWER IRRIGATORS ASSOCIATION | c) | 09/25/19 | g) | 2019-12-31 | c) | - | [7 empty] | 2
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 2
|  |  | Jct. Highway Sto. Niño - Kabanlakan - La Paz |  |  | Road Maintenance | 2.13 | MBA | a) | 76067.88 | a) | 01/03/19 | e) | - | a) | 76067.88 | a) | 100% | c) | 100% | a) | 9 | Completed | 2
| 084 | [7 empty] | b) | Clar | b) | 01/10/19 | f) | - | b) | 76067.88 | b) | - | d) | - | b) | 45 |  | 2
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 66,477.91 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | Ising - Sto Niño |  |  | Road Maintenance | 2.07 | CBRMC | a) | 82413.14 | a) | 01/03/19 | e) | - | a) | 82413.14 | a) | 100% | c) | 100% | a) | 5 | Completed | 2
| 085 | [7 empty] | b) | Clar | b) | 01/17/19 | f) | - | b) | 82413.14 | b) | - | d) | - | b) | 15 |  | 2
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 27,093.24 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | Ising - Sadpodon - Taba - Dila -Dila |  |  | Road Maintenance | 5.68 | MBA | a) | 248941.33 | a) | 01/03/19 | e) | - | a) | 248941.33 | a) | 100% | c) | 100% | a) | 9 | Completed | 2
| 086 | [7 empty] | b) | Clar | b) | 01/12/19 | f) | - | b) | 248941.33 | b) | - | d) | - | b) | 27 |  | 2
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 82,329.02 | [7 empty] | 2
[9 empty] | d) | - | d) | - |  |  |  | . | [7 empty] | 2
2
|  |  | Tuganay - taba |  |  | Road Maintenance | 4.27 | CBRMC | a) | 291377.9 | a) | 01/03/19 | e) | - | a) | 291377.9 | a) | 70% | c) | 70% | a) | 9 | Completed
| 087 | [7 empty] | b) | Clar | b) | 01/09/19 | f) | - | b) | 291377.9 | b) | - | d) | - | b) | 27 |  | 2
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 12/31/2019 | c) | 238,412.28 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | Jct. Highway Tuganay - Taba |  |  | Road Maintenance | 4.4 | MBA | a) | 32972.82 | a) | 01/03/19 | e) | - | a) | 32972.82 | a) | 65% | c) | 65% | a) | 9 | Completed | 2
| 088 | [7 empty] | b) | Clar | b) | 01/22/19 | f) | - | b) | 32972.82 | b) | - | d) | - | b) | 18 |  | 2
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 12/31/2019 | c) | 22,639.09 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | Jct. Highway Ising - Magsaysay |  |  | Road Maintenance | 10.84 | CBRMC | a) | 417818.12 | a) | 01/03/19 | e) | - | a) | 417818.12 | a) | 60% | c) | 60% | a) | 10 | Completed | 2
| 089 | [7 empty] | b) | Clar | b) | 01/22/19 | f) | - | b) | 417818.12 | b) | - | d) | - | b) | 50 |  | 2
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 12/31/2019 | c) | 313,488.39 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | New Camiling - Alejal - Lower Magsaysay |  |  | Road Maintenance | 6.73 | MBA | a) | 240878.08 | a) | 01/03/19 | e) | - | a) | 240878.08 | a) | 80% | c) | 80% | a) | 4 | Completed | 2
| 091 | [7 empty] | b) | Clar | b) | 01/22/19 | f) | - | b) | 240878.08 | b) | - | d) | - | b) | 20 |  | 2
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 12/31/2019 | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | Jct. highway Tuganay - Anibongan |  |  | Road Maintenance | 3.66 | CBRMC | a) | 150684.44 | a) | 01/03/19 | e) | - | a) | 150684.44 | a) | 100% | c) | 100% | a) | 6 | Completed | 2
| 094 | [7 empty] | b) | Clar | b) | 01/22/19 | f) | - | b) | 150684.44 | b) | - | d) | - | b) | 18 |  | 2
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 12/31/2019 | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | Anibongan - Guadalupe |  |  | Road Maintenance | 2.48 | MBA | a) | 91325.06 | a) | 01/03/19 | e) | - | a) | 91325.06 | a) | 100% | c) | 100% | a) | 9 | Completed | 2
| 095 | [7 empty] | b) | Clar | b) | 01/23/19 | f) | - | b) | 91325.06 | b) | - | d) | - | b) | 18 |  | 2
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 12/31/2019 | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | Tuganay - Anibongan - San Isidro |  |  | Road Maintenance | 7.22 | CBRMC | a) | 139979.8 | a) | 01/03/19 | e) | - | a) | 139979.8 | a) | 100% | c) | 100% | a) | 9 | Completed | 2
| 096 | [7 empty] | b) | Clar | b) | 01/24/19 | f) | - | b) | 139979.8 | b) | - | d) | - | b) | 36 |  | 2
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 12/31/2019 | c) | 1890.37 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | Jct. Anibongan - Prk. 2, 7, 5, San Isidro |  |  | Road Maintenance | 3.14 | MBA | a) | 104378.03 | a) | 01/03/19 | e) | - | a) | 104378.03 | a) | 100% | c) | 100% | a) | 10 | Completed | 2
| 097 | [7 empty] | b) | Clar | b) | 01/24/19 | f) | - | b) | 104378.03 | b) | - | d) | - | b) | 20 |  | 2
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 12/31/2019 | c) | 56,087.50 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | Anibongan - Salvacion - Cabay-angan |  |  | Road Maintenance | 6.93 | CBRMC | a) | 415461.61 | a) | 01/03/19 | e) | - | a) | 415461.61 | a) | 100% | c) | 100% | a) | 9 | Completed | 2
| 098 | [7 empty] | b) | Clar | b) | 01/25/19 | f) | - | b) | 415461.61 | b) | - | d) | - | b) | 45 |  | 2
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 12/31/2019 | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | Jct. Highway Guadalupe - Bdry. Tagum |  |  | Road Maintenance | 7.9 | MBA | a) | 456131.09 | a) | 01/03/19 | e) | - | a) | 456131.09 | a) | 100% | c) | 100% | a) | 9 | Completed | 2
| 101 | [7 empty] | b) | Clar | b) | 01/25/19 | f) | - | b) | 456131.09 | b) | - | d) | - | b) | 18 |  | 2
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 12/31/2019 | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | Jct. Highway Guadalupe - Bdry. Tagum |  |  | Road Maintenance | 7.9 | CBRMC | a) | 228201.66 | a) | 01/03/19 | e) | - | a) | 228201.66 | a) | 100% | c) | 100% | a) | 8 | Completed | 2
| 101 | [7 empty] | b) | Maligro | b) | 03/25/19 | f) | - | b) | 228201.66 | b) | - | d) | - | b) | 40 |  | 2
[9 empty] | c) | LAMPIA PAG-ASA IRRIGATORS ASSOCIATION, INC. | c) | 12/25/19 | g) | 12/31/2019 | c) | - | [7 empty] | 2
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 2
|  |  | Poblacion Dujali - Prk. 8 Dujali |  |  | Road Maintenance | 8.2 | MBA | a) | 285600.05 | a) | 01/03/19 | e) | - | a) | 285600.05 | a) | 100% | c) | 100% | a) | 10 | Completed | 2
| 105 | [7 empty] | b) | Clar | b) | 01/28/19 | f) | - | b) | 285600.05 | b) | - | d) | - | b) | 50 |  | 2
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 12/31/2019 | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | Dujali - San Isidro |  |  | Road Maintenance | 3 | CBRMC | a) | 130319.3 | a) | 01/03/19 | e) | - | a) | 130319.3 | a) | 100% | c) | 100% | a) | 8 | Completed | 2
| 107 | [7 empty] | b) | Gamad | b) | 01/28/19 | f) | - | b) | 130319.3 | b) | - | d) | - | b) | 30 |  | 2
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 12/31/2019 | c) | 45,943.12 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | Prk. 5, RJS - Prk. 6 New Casay |  |  | Road Maintenance | 2.73 | MBA | a) | 235277 | a) | 01/03/19 | e) | - | a) | 235277 | a) | 100% | c) | 100% | a) | 2 | Completed | 2
| 109 | [7 empty] | b) | Gamad | b) | 01/28/19 | f) | - | b) | 235277 | b) | - | d) | - | b) | 6 |  | 2
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 12/31/2019 | c) | 90,745.35 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | Prk. 5 - Prk. 1 Pawas Dujali |  |  | Road Maintenance | 2.18 | CBRMC | a) | 76067.68 | a) | 01/03/19 | e) | - | a) | 76067.68 | a) | 100% | c) | 100% | a) | 10 | Completed | 2
| 112 | [7 empty] | b) | Gamad | b) | 01/18/19 | f) | - | b) | 76067.68 | b) | - | d) | - | b) | 20 |  | 2
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 12/31/2019 | c) | 40,112.50 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | Dujali - Balisong - Magupising |  |  | Road Maintenance | 5.52 | MBA | a) | 260591.93 | a) | 01/03/19 | e) | - | a) | 260591.93 | a) | 100% | c) | 100% | a) | 4 | Completed | 2
| 113 | [7 empty] | b) | Gamad | b) | 01/09/19 | f) | - | b) | 260591.93 | b) | - | d) | - | b) | 8 |  | 2
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 12/31/2019 | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | Dujali - Pawas - San Vicente |  |  | Road Maintenance | 4.42 | CBRMC | a) | 139536.42 | a) | 01/03/19 | e) | - | a) | 139536.42 | a) | 100% | c) | 100% | a) | 10 | Completed | 2
| 117 | [7 empty] | b) | Gamad | b) | 01/22/19 | f) | - | b) | 139536.42 | b) | - | d) | - | b) | 18 |  | 2
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 12/31/2019 | c) | 52,133.86 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | Jct. Salvacion - San Vicente - Cabay-angan |  |  | Road Maintenance | 3.45 | MBA | a) | 247460.9 | a) | 01/03/19 | e) | - | a) | 247460.9 | a) | 100% | c) | 100% | a) | 10 | Completed | 2
| 118 | [7 empty] | b) | Gamad | b) | 01/23/19 | f) | - | b) | 247460.9 | b) | - | d) | - | b) | 18 |  | 2
[9 empty] | c) | PEO | c) | 02/31/19 | g) | 12/31/2019 | c) | 151,887.50 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | Jct. Salvacion - San Vicente - Cabay-angan |  |  | Road Maintenance | 3.45 | CBRMC | a) | 152134.44 | a) | 01/03/19 | e) | - | a) | 152134.44 | a) | 100% | c) | 100% | a) | 8 | Completed | 2
| 118 | [7 empty] | b) | Gamad | b) | 03/26/19 | f) | - | b) | 152134.44 | b) | - | d) | - | b) | 36 |  | 2
[9 empty] | c) | BALISONG SAN VICENTE IRRIGATORS ASSOCIATION | c) | 12/26/19 | g) | 12/31/2019 | c) | [8 empty] | 2
[9 empty] | d) | 3 quarters | d) | - | [10 empty] | Completed | 2
|  |  | Dujali - San Miguel |  |  | Road Maintenance | 3.95 | MBA | a) | 101202.04 | a) | 01/03/19 | e) | - | a) | 101202.04 | a) | 80% | c) | 90% | a) | 11 |  | 2
| 119 | [7 empty] | b) | Gamad | b) | 01/10/19 | f) | - | b) | 101202.04 | b) | - | d) | - | b) | 22 |  | 2
[9 empty] | c) | PEO | c) | 12/31/19 | g) | - | c) | 90,350.03 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | San Miguel - Casig-ang |  |  | Road Maintenance | 2.55 | CBRMC | a) | 79237.14 | a) | 01/03/19 | e) | - | a) | 79237.14 | a) | 100% | c) | 100% | a) | 10 | Completed | 2
| 122 | [7 empty] | b) | Gamad | b) | 01/24/19 | f) | - | b) | 79237.14 | b) | - | d) | - | b) | 10 |  | 2
[9 empty] | c) | BALISONG SAN VICENTE IRRIGATORS ASSOCIATION | c) | 12/31/19 | g) | 12/31/2019 | c) | 40,112.50 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | Prk. Magsaysay - Lunga-og - Dalisay |  |  | Road Maintenance | 2.81 | MBA | a) | 79762.14 | a) | 01/03/19 | e) | - | a) | 79762.14 | a) | 100% | c) | 100% | a) | 8 | Completed | 2
| 127 | [7 empty] | b) | Gamad | b) | 01/30/19 | f) | - | b) | 79762.14 | b) | - | d) | - | b) | 8 |  | 2
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 12/31/2019 | c) | 40,612.50 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | Prk. Apitong - Upper Balisong - Dalisay |  |  | Road Maintenance | 4.6 | CBRMC | a) | 137846.03 | a) | 01/03/19 | e) | - | a) | 137846.03 | a) | 100% | c) | 100% | a) | 8 | Completed | 2
| 128 | [7 empty] | b) | Gamad | b) | 01/31/19 | f) | - | b) | 137846.03 | b) | - | d) | - | b) | 8 |  | 2
[9 empty] | c) | BALISONG SAN VICENTE IRRIGATORS ASSOCIATION | c) | 12/31/19 | g) | 12/31/2019 | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | Sitio Paradise - Magkakaisa - Esperanza |  |  | Road Maintenance | 1.75 | MBA | a) | 66552.75 | a) | 01/03/19 | e) | - | a) | 66552.75 | a) | 100% | c) | 100% | a) | 8 | Completed | 2
| 129 | [7 empty] | b) | 79762.14 | b) | 01/22/19 | f) | - | b) | 66552.75 | b) | - | d) | - | b) | 8 |  | 2
[9 empty] | c) | Gamad | c) | 12/31/19 | g) | 12/31/2019 | c) | 22,246.26 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | Los Amigos 1 - Esperanza - Los Amigos 2 |  |  | Road Maintenance | 3.59 | CBRMC | a) | 101202.04 | a) | 01/03/19 | e) | - | a) | 101202.04 | a) | 100% | c) | 100% | a) | 10 | Completed | 2
| 130 | [7 empty] | b) | Gamad | b) | 01/24/19 | f) | - | b) | 101202.04 | b) | - | d) | - | b) | 20 |  | 2
[9 empty] | c) | BALISONG SAN VICENTE IRRIGATORS ASSOCIATION | c) | 12/31/19 | g) | 12/31/2019 | c) | 50,837.50 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | Mugas - Lunga-og |  |  | Road Maintenance | 2.68 | MBA | a) | 66552.75 | a) | 01/03/19 | e) | - | a) | 91,693.64 | a) | 100% | c) | 100% | a) | 6 | Completed | 2
| 132 | [7 empty] | b) | 79762.14 | b) | 01/17/19 | f) | - | b) | 91,693.64 | b) | - | d) | - | b) | 24 |  | 2
[9 empty] | c) | Gamad | c) | 12/31/19 | g) | 12/31/2019 | c) | 50,837.50 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | Pantaron - Mugas |  |  | Road Maintenance | 3.35 | CBRMC | a) | 101202.04 | a) | 01/03/19 | e) | - | a) | 101202.04 | a) | 100% | c) | 100% | a) | 9 | Completed | 2
| 133 | [7 empty] | b) | Gamad | b) | 01/23/19 | f) | - | b) | 101202.04 | b) | - | d) | - | b) | 18 |  | 2
[9 empty] | c) | BALISONG SAN VICENTE IRRIGATORS ASSOCIATION | c) | 12/31/19 | g) | 12/31/2019 | c) | 90,349.93 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | Sto. Tomas - Bdry. Mamacao |  |  | Road Maintenance | 4.9 | MBA | a) | 110710.44 | a) | 01/03/19 | e) | - | a) | 110710.44 | a) | 100% | c) | 100% | a) | 10 | Completed | 2
| 135 | [7 empty] | b) | 79762.14 | b) | 01/21/19 | f) | - | b) | 110710.44 | b) | - | d) | - | b) | 40 |  | 2
[9 empty] | c) | Gamad | c) | 12/31/19 | g) | 12/31/2019 | c) | 50,837.50 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | Fd. Rd. 3 - San Jose |  |  | Road Maintenance | 4.55 | CBRMC | a) | 147367.49 | a) | 01/03/19 | e) | - | a) | 147367.49 | a) | 100% | c) | 100% | a) | 10 | Completed | 2
| 136 | [7 empty] | b) | Gamad | b) | 01/25/19 | f) | - | b) | 147367.49 | b) | - | d) | - | b) | 30 |  | 2
[9 empty] | c) | BALISONG SAN VICENTE IRRIGATORS ASSOCIATION | c) | 12/31/19 | g) | 12/31/2019 | c) | 56,174.69 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | Menzi - balagunan - Tulalian |  |  | Road Maintenance | 10.63 | MBA | a) | 520167.79 | a) | 01/03/19 | e) | - | a) | 520167.79 | a) | 100% | c) | 100% | a) | 6 | Completed | 2
| 138 | [7 empty] | b) | 79762.14 | b) | 01/07/19 | f) | - | b) | 520167.79 | b) | - | d) | - | b) | 18 |  | 2
[9 empty] | c) | Gamad | c) | 12/31/19 | g) | 12/31/2019 | c) | 204,850.57 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | Jct. Bdry. Tagum - Talomo |  |  | Road Maintenance | 12.01 | CBRMC | a) | 407429.19 | a) | 01/03/19 | e) | - | a) | 407429.19 | a) | 100% | c) | 100% | a) | 10 | Completed | 2
| 145 | [7 empty] | b) | Gamad | b) | 01/11/19 | f) | - | b) | 407429.19 | b) | - | d) | - | b) | 50 |  | 2
[9 empty] | c) | BALISONG SAN VICENTE IRRIGATORS ASSOCIATION | c) | 12/31/19 | g) | 12/31/2019 | c) | 168,544.84 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | San Jose - Sitio Mahayahay, Magwawa |  |  | Road Maintenance | 0.84 | MBA | a) | 7919.35 | a) | 01/03/19 | e) | - | a) | 7919.35 | a) | 100% | c) | 100% | a) | 2 | Completed | 2
| 151 | [7 empty] | b) | 79762.14 | b) | 01/16/19 | f) | - | b) | 7919.35 | b) | - | d) | - | b) | 8 |  | 2
[9 empty] | c) | Gamad | c) | 12/31/19 | g) | 12/31/2019 | c) | 1,509.27 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| B. 20% DEVELOPMENT FUND CY 2019 | [22 empty] | FS
| Road ID |  | 1. Rehabilitation Of Various Prov'l. Roads and Bridges Dist. 1 |  |  | Road Rehabilitation | KM | MBA | a) | 41465029 | a) | 01/03/19 | e) | - | a) | 41465029 | a) | - | c) | - | a) | 46 | See list of Provincial Roads | FS
[7 empty] | 109.55 |  | b) | Paraguya | b) | 01/03/19 | f) | - | b) | 41465029 | b) | - | d) | - | b) | 920 |  | AC
| 11DAN | [7 empty] | c) | PEO | c) | 12/31/19 | g) | - | c) | - | [7 empty] | AC
[11 empty] | d) | - | [11 empty] | AC
[9 empty] | d) | 261 days | d) | - | [11 empty] | AC
[6 empty] | Road Rehabilitation |  |  | a. )P 500,000.00 |  | a.) 01/31/19 |  |  |  | a.) 500,000.00 | [8 empty] | 1
|  |  | Purok 10 Pob. Road, New Corella | [7 empty] | b.) Feb. 16, 2019 |  |  |  | b.) 500,000.00 | [7 empty] | Completed
g.) Feb. 28, 2019
[6 empty] | Road Rehabilitation |  |  | a.)1,815,000.00 |  | a.) 01/31/19 |  |  |  | a.) 1,815,000.00
|  |  | Purok 7 Pob- Jct. New Sambog | [7 empty] | b.)March 1, 2019 |  |  |  | b.) 1,815,000.00 | [7 empty] | Completed
g.) May 15, 2019
[6 empty] | Road Rehabilitation |  |  | a.) 1,389,000.00 |  | a.) 01/31/19 |  |  |  | a.) 1,389,000.00 | [7 empty] | Completed with a savings of P303,898.08 furtherance and is for implementation
|  |  | Del Pilar- El Unido Road | [5 empty] | b.) Fabian |  | b.) March 18,2019 |  |  |  | a.) 1,389,000.00
g.) May 8, 2019
SUPPLEMENTAL BUDGET NO 4 CY 2019 / CONTINUING APPROPRIATION
[9 empty] | a.) 7,742,775.95 | [5 empty] | a.) 7,742,775.95 | [7 empty] | Waiting for the delivery of materials
|  |  | Impvt. of Km. 9 Sagayen - Sawata Provincial Road Phase II | [5 empty] | b.) Kenny | [5 empty] | b.) 7,742,775.95
| Road ID |  | 1. Rehabilitation Of Various Prov'l. Roads and Bridges Dist 2 |  |  | Road Rehabilitation | KM | Admin | a) | 46740117 | a) | 01/03/19 | [10 empty] | See list of Provincial Roads
[7 empty] | 115.62 |  | b) | Matuguinas | b) | - | [11 empty] | AC
| 11DAN | [7 empty] | c) | PEO | c) | - | [11 empty] | AC
[11 empty] | d) | - | [11 empty] | AC
[9 empty] | d) | 261 days | d) | - | [11 empty] | AC
[6 empty] | Road Rehabilitation |  |  | a.) 515,000.00 |  | a.) 03/12/19 |  |  |  | a.) 515,000.00 | [8 empty] | 2
|  |  | Jct. Highway -Tubod - Bagong Silang | [5 empty] | b.) Clar |  | b.) March 18, 2019 |  |  |  | b.) 515,000.00 | [7 empty] | Completed
g.) June 15, 2019
[6 empty] | Road Rehabilitation |  |  | a.) 390,000.00 |  | a.) 03/12/19 |  |  |  | a.) 390,000.00 | [8 empty] | 2
|  |  | Cebulano- Luceta | [5 empty] | b.) Clar |  | b.) March 8, 2019 |  |  |  | b.) 390,000.00 | [7 empty] | Completed
g.) June 15, 2019
[6 empty] | Road Rehabilitation |  |  | a.) 295,000.00 |  | a.) 03/12/19 |  |  |  | a.) 295,000.00
|  |  | Lower Asuncion - Upper Asuncion | [5 empty] | b.) Clar |  | b.) March 18, 2019 |  |  |  | b.) 295,000.00 | [7 empty] | Completed
g.) June 15, 2019
[6 empty] | Road Rehabilitation |  |  | a.) 1,220,000.00 |  | a.) 03/12/19 |  |  |  | a.) 1,220,000.00
|  |  | Jct. Highway - Sto. Nino - La Paz - San Vicente | [5 empty] | b.)Obar |  | b.) March 18, 2019 |  |  |  | b.) 1,220,000.00 | [7 empty] | Completed
g.) Sept. 30, 2019
|  |  | Alejal - Alemag |  |  | Road Rehabilitation | 1.79 |  | a) | 970000 | a) | 2019-03-18 | e) | - | a) | 970000 | a) | 100% | c) | 100% | a) | 7 | Completed. Financially completed
| 092 | [7 empty] | b) | Gamad/Clar | b) | 2019-05-20 | f) | - | b) | 970000 | b) | 100 | d) | 0% | b) | 20 |  | 2
[9 empty] | c) | - | c) | 2019-09-12 | g) | Sept. 30, 2019 | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
[6 empty] | Road Rehabilitation |  |  | a.) 640,000.00 |  | a.) 03/12/19 |  |  |  | a.) 640,000.00 | [8 empty] | 2
|  |  | Mabaus - Cabay -angan | [5 empty] | b.)Clar |  | b.) Maech 18, 2019 |  |  |  | a.) 640,000.00 | [7 empty] | Completed
g.) July 30, 2019
[6 empty] | Road Rehabilitation |  |  | a.) 280,000.00 |  | a.) 03/12/19 |  |  |  | a.) 280,000.00
|  |  | Mabaus - Salvacion | [5 empty] | b.)Clar |  | b.) March 18, 2019 |  |  |  | a.) 280,000.00
[13 empty] | g.) June 30, 2019 | [9 empty] | Completed
|  |  | Dujali - New Casay |  |  |  | 3.2 | Admin | a) | 640000 | a) | 2019-05-16 | e) | - | a) | 640000 | a) | 100% | c) | 100% | a) | 10 |  | 2
| 106 | [7 empty] | b) | Gamad/Clar | b) | 2019-06-17 | f) | 40 | b) | 640000 | b) |  | d) | - | b) | 40 | Completed | 2
[9 empty] | c) | - | c) |  | g) | 10/15/2019 | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
[6 empty] | Road Rehabilitation |  |  | a.) 450,000.00 |  | a.) 03/12/19 |  |  |  | a.) 450,000.00 | [8 empty] | 2
|  |  | New Casay - Bugtong Talisay | [5 empty] | b.)Clar |  | b.) March 18, 2019 |  |  |  | a.) 450,000.00 | [7 empty] | Completed
g.)June 30, 2019
[6 empty] | Road Rehabilitation |  |  | a.)220,000.00 |  | a.) 03/12/19 |  |  |  | a.)220,000.00 |  | a.) 100 % |  | c.)100% |  |  |  |  | 2
|  |  | Purok 6 Cabay-angan - Esti | [5 empty] | b.) Gamad |  | b.) March 18, 2019 |  |  |  | a.)220,000.00 | [7 empty] | Completed
g.) June 30, 2019
[6 empty] | Road Rehabilitation |  |  | a.)250,000.00 |  | a.) March 12, 2019 | [5 empty] | a.) 100 % |  | c.)100%
|  |  | Dujali - Sitio Pawas | [5 empty] | b.) Gamad |  | b.) March 18, 2019 | [11 empty] | Completed
g.) Jun 30, 2019
[6 empty] | Road Rehabilitation |  |  | a.) 280,000.00 |  | a.) March 12, 2019 | [5 empty] | a.) 100 % |  | c.)100%
|  |  | Purok 1 to Purok 2 Sitio Pawas | [6 empty] | b.) Gamad | b.) March 18, 2019 | [11 empty] | Completed
g.) Jun 30, 2019
|  |  | San Miguel - Crossing Kinamayan |  |  | Road Rehabilitation | 2.8 | Admin | a) | 560000 | a) | 2019-06-25 | e) | - | a) | 560000 | a.) 100 % |  | c.)100% |  | a) | -
| 120 | [7 empty] | b) | Nasol | b) | Sept. 19, 2019 | f) | - | b) | 560000 | b) | - | d) | - | b) | - | Completed | 2
[9 empty] | c) | - | c) | - | g) | Nov. 30, 2019 | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | Kinamayan - Lunga-og |  |  | Road Rehabilitation | 2.59 | Admin | a) | 520000 | a) | 2019-03-18 | e) | - | a) | 520000 | a) | 100% | c) | 100% | a) | 9 | Completed | 2
| 126 | [7 empty] | b) | Gamad/Clar | b) | 5/202/019 | f) | - | b) | 520000 | b) | - | d) | - | b) | 36 |  | 2
[9 empty] | c) | - | c) |  | g) | Sept. 30, 2019 | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
[9 empty] | a.) 540,000.00 |  | a.) March 12, 2019 |  |  |  | a.) 540,000.00 |  | a.)100% |  | c.)100% |  |  |  | Completed
|  |  | Nafco - Bobongon |  |  | Road Rehabilitation |  |  | b. Gamad |  | b.) march 18, 2019 |  |  |  | b.) 540,000.00
g.) June 30, 2019
2
|  |  | Prk. Narafil - Prk. Daisy Magupising |  |  | Road Rehabilitation | 19.16 | Admin | a) | 300117 | a) | 2019-06-25 | e) | - | a) | 300117 | a) | 100% | c) | 100% | a) | - | Completed | 2
| 148 | [7 empty] | b) | Gamad/Clar | b) | Sept. 16, 2019 | f) | - | b) | 300117 | b) | - | d) | - | b) | - |  | 2
[9 empty] | c) | - | c) | - | g) | Oct. 18, 2019 | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 2. Various of Local Roads & Drainage Development Project (Provincewide) |  |  |  |  | Road Drainage rehabiliated |  | Admin | a) | 15000000 | [12 empty] | See projects listed below | 2
[9 empty] | b) | Paraguya | [13 empty] | AC
[9 empty] | c) | PEO | [13 empty] | AC
[9 empty] | d) | - | [13 empty] | AC
|  |  | Rehab. of Anibongan-Salvacion-Cabay-angan Provincial Road with Drainage |  |  | Road Drainage rehabiliated | - | - | a) | 2000000 | a) | 2019-01-14 | e) | - | a) | 2000000 | a) | 100% | c) | 100% | a) | 1 | Completed | 2
| 2.1 | [7 empty] | b) | Toquero | b) | 2019-05-22 | f) | - | b) | 2000000 | b) | - | d) | - | b) | 4 | Fiancial obligation still on process | 2
[9 empty] | c) | PEO | c) | 2019-08-04 | g) | Dec. 31, 2019 | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | Rehab./Impv't. of Sto. Tomas-Bdry. Mamacao Provincial Road |  |  | Road Drainage rehabiliated | - | Admin | a) | 1500000 | a) | 2019-01-14 | e) | - | a) | 1500000 | a) | 100% | c) | 100% | a) | - | Completed Financial obligation on process
| 2.4 | [7 empty] | b) | Toquero | b) | 2019-05-31 | f) | 60 | b) | 1500000 | b) | - | d) | - | b) | - |  | 2
[9 empty] | c) | PEO | c) | 2019-07-15 | g) | Dec. 31, 2019 | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 4. Various Government Buildings and Facilities Development Project (Provincewide) |  |  |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of recipients | - | Admin | a) | 27000000 | [12 empty] | See projects listed below | 2
[9 empty] | b) | Medalla | [13 empty] | AC
[9 empty] | c) | PEO | [13 empty] | AC
[9 empty] | d) | - | [13 empty] | AC
|  |  | Const. of GYM Bleacher at Suaybaguio Rina, Elem. School |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of recipients | - | #REF! | a) | 1000000 | a) | - | e) | - | a) | 1000000 | a) | 100% | c) | 100% | a) | - | Completed | 1
|  | 11 | [6 empty] | b) | Mayang | b) | 6/3/2019 | f) | - | b) | 1000000 | b) | 64 | d) | 0% | b) | - |  | 1
[9 empty] | c) | PEO | c) | 8/01/2019 | g) |  | c) | - | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
| 5. Stimulus Projects for Various Barangays a. 20% Development Fund CY 2019 |  |  |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | Admin | a) | 41500000 | [12 empty] | See projects listed below | 2
[9 empty] | b) | Medalla | [13 empty] | AC
[9 empty] | c) | PEO | [13 empty] | AC
[9 empty] | d) | - | [13 empty] | AC
AC
| IGCS | [22 empty] | 2
| 5.42 |  | Rehab. Of Health Center, Aumbay, IGCS |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) | Feb. 28, 2019 | e) | - | a) | 500000 | a) |  | c) | 48.32% | a) | 3 | Completed Financial obligation on process | AC
[9 empty] | b) | Pacquiao | b) | 7/10/2019 | f) | - | b) | 500000 | b) | - | d) |  | b) | 15 |  | 2
[9 empty] | c) | Admin | c) | 10/7/2019 | g) | - | c) | - | [7 empty] | 2
[9 empty] | d) | 90 CD | d) | - | [11 empty] | 2
| 5.46 |  | Rehab. Of Brgy. Health Center, Mambago-A, IGCS |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) | Feb. 28, 2019 | e) | - | a) | 500000 | a) |  | c) | 75.61% | a) | 3 | Completed Financial obligation on process | 2
[9 empty] | b) | Ganaba | b) | 07/2019 | f) | - | b) | 500000 | b) |  | d) |  | b) | 15 |  | 2
[9 empty] | c) | Admin | c) | 8/23/2019 | g) | - | c) | - | [7 empty] | 2
[9 empty] | d) | 45 CD | d) | - | [11 empty] | 2
| 6. Rural Electrification Project (Provincewide) |  |  |  |  | Powerlines/posts installed & rehabilitated | - | - | a) | 5000000 | [12 empty] | See projects listed below | 2
[9 empty] | b) | Kim Pao Lu | [13 empty] | AC
[9 empty] | c) | - | [13 empty] | AC
[9 empty] | d) | - | [13 empty] | AC
C. 5% CALAMITY FUND CY 2019
| 3 |  | Improvement of roads, drainage and canal |  |  | Protection dikes/slope protection | - | - | a) | 3000000 | [12 empty] | See projects listed below | 2
[9 empty] | b) | Paraguya | [13 empty] | AC
[9 empty] | c) | PEO | [13 empty] | AC
[9 empty] | d) | - | [13 empty] | AC
| a. |  | Rehab./Impv't. of New Casay-Bugtong Talisay Provincial Road (Ph.II) |  |  | creeks and canRoads/Draiange/canals rehab/improved | - | - | a) | 500000 | a) | 2019-03-12 | e) | - | a) | 500000 | a) | 100% | c) | 100% | a) | 12 | Completed | AC
[9 empty] | b) | Toquero | b) | 2019-05-30 | f) | - | b) | 500000 | b) | - | d) | - | b) | 120 |  | 2
[9 empty] | c) | Admin | c) | 2019-07-30 | g) |  | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | Mark | Municipality/City |  | Color
|  |  | 1 | Asuncion |  | Red
|  |  | 2 | B.E. Dujali |  | Yellow
|  | GF- GENERAL FUND | 3 | Carmen |  | Blue | [10 empty] | TF - TRUST FUND (NATIONAL FUNDED PROJECT)
|  | 20% DF - 20% DEV'T. FUND | 4 | Kapalong |  | Pink | [10 empty] | a) SLRF - Special Local Road Fund
|  | 5% CF - 5% CALAMITY FUND | 5 | New Corella |  | Gray | [10 empty] | b) KALSADA - Konkreto at Ayos na Lansangan Tungo sa Pangkalahatang Kaunlaran
|  | CO - CAPITAL OUTLAY | 6 | San Isidro |  | Orange | [10 empty] | c) PRDP - Philippine Rural Development Projects
|  | CONG. FUND - CONGRESSIONAL FUND | 7 | Sto Tomas |  | Sky Blue | [10 empty] | d) SELAP - Support to Emergency and Livelihood Assistance Project
|  |  | 8 | Talaingod |  | Violet | [10 empty] | e) PAMANA - Payapa at Masaganang Pamayanan
|  | SEF - SPECIAL EDUCATIONAL UFND | 9 | Panabo City |  | Brown | [10 empty] | f) CBRMC - Community Based Road Maintenance Contracting
|  |  | 10 | IGACOS |  | Yellow Green | [10 empty] | g) MBC - Maintenance by Contract
|  |  | 11 | Tagum City |  | Green | [10 empty] | h) PCF-Performance Challenge Fund-DILG
i) FMRDP - Farm to Market Road
j.) CMGP - Conditional Grant to Provinces
k.) OPAPP - Office of the President Adviser on the Peace Process
l.) LGSF-AM - Local Government Support Fund Assistance to Municipalities
| Prepared by: |  |  |  | Checked | [12 empty] | Recommending Approval
Noted
| GILBERT G. MAMBULAO JR |  |  |  |  | TESSIE G. ABABON | [9 empty] | JIVELLYN B. CO | [5 empty] | GLENN A. OLANDRIA
| Engineer II | [5 empty] | Engineer IV-Engineering Dist 2, Area Engineer | [9 empty] | Asst. PG-Department Head |  |  |  |  | Provincial Engineer
[5 empty] | EDWIN S. MISA |  |  |  | MARILOU A. FORONDA
[5 empty] | Engineer IV- PDPM Division Head |  |  |  | Engineer IV- QC Division Head

## Annual On going 2019_Dist 2 (hidden)
PROVINCE OF DAVAO DEL NORTE
ACCOMPLISHMENT REPORT
Annual 2019
SECTOR: ECONOMIC (INFRASTRUCTURE DEV'T. PROGRAM)
OFFICE/AGENCY: PROVINCIAL ENGINEER'S OFFICE
ON-GOING PROJECTS DISTRICT 2
Name of Project |  |  |  |  | Type | Physical | Mode | PROJECT DATA | [5 empty] | Financial (000) |  | Physical Accomplishment |  |  |  | Employment |  | REMARKS
[5 empty] | of | Target | of | a) Project Cost |  | a) | Date A lot. Rel. | e) | # of days suspended | a) Program |  | a) Planned |  | c) Actual |  | Generated
[5 empty] | Project | (Descrip | Impl. | b) Project Engineer |  | b) | Date Started | f) | # of days extended | b) Allotment |  | b) Revised |  | d) Slippage |  | a) # of Persons | # of Persons
[5 empty] | (Location) | tion) |  | c) Implementor |  | c) | Target Compl. Date | g) | Date completed | c) Disbursement | [5 empty] | b) | Man-days
[8 empty] | d) Duration |  | d) | Revised Compl. Date
I. | PROJECTS UNDER THE CONTINUING APPROPRIATION | [22 empty] | AC |  |  |  | 893809.45
| A. | Supplemental Budget # 1 CY 2015 | [19 empty] | delay due to change location & design code. For AIP amendment from Panabo City to Gov't Center, Mankilam |  | 2
|  | 1. Proposed Davao del Norte Tourism Billboard |  |  | Billboard |  | Admin | a) | 756,400.00 | a) | 05/06/15 | e) | - | a) | 756,400.00 | a) | 11.78% | c) | 11.78% | a) | - |  |  | 2
|  | Brgy. Lasang, Panabo City | [5 empty] | b) | Porras | b) | 03/30/15 | f) | - | b) | 756,400.00 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | PEO | c) | 05/10/15 | g) | - | c) | 332,087.30 | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
| B. | Supplemental Budget # 5 CY 2015 | [21 empty] | FS
|  | 1. Purchased, Const. & Imprv't. of Gov't. Facilities (8918) | [19 empty] | See projects listed below |  | AC
|  | a) Const./Compl./Imprvt. of Various Gov't. Bldgs. |  |  | Bldgs. |  | Admin | a) | 38,000,000.00 | [14 empty] | AC
|  | Structures & Facilities | [5 empty] | b) | Imboy | [14 empty] | AC
[8 empty] | c) | PEO | [14 empty] | AC
|  | 4.) Const. of Multi-Purpose Bldg. Magsaysay, Carmen |  |  | Court |  | - | a) | 500000 | a) | 03/05/16 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For cancellation since the project was already undertaken by Davao Light & no back up cash since it is part of the loan with LBP |  | 2
[8 empty] | b) | CY 2015 | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | PEO | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | 5.) Improvement of Covered Court |  |  | Court |  | - | a) | 500000 | a) | 03/05/16 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For cancellation since the project was already undertaken by Davao Light & no back up cash since it is part of the loan with LBP |  | 2
|  | Brgy. San Isidro, Carmen | [5 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | PEO | c) | - | g) | - | c) | [9 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | 6.) Construction of 1 Bay Covered Court |  |  | Court |  | - | a) | 500000 | a) | 03/08/16 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For cancellation since the project was already undertaken by Davao Light & no back up cash since it is part of the loan with LBP |  | 2
|  | Brgy. Bobongon, Sto. Tomas | [5 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | PEO | c) | - | g) | - | c) | [9 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | 7.) Construction of Multi-Purpose Building |  |  | Bldg. |  |  | a) | 500000 | a) | 03/05/16 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For cancellation since the project was already undertaken by Davao Light & no back up cash since it is part of the loan with LBP |  | 2
|  | Brgy. New Visayas, Sto. Tomas |  |  |  |  | - | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | PEO | c) | - | g) | - | c) | [9 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | 8.) Improvement of Brgy. Hall |  |  | Bldg. |  |  | a) | 500000 | a) | 03/05/16 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For cancellation since the project was already undertaken by Davao Light & no back up cash since it is part of the loan with LBP |  | 2
|  | Brgy. Tulalian, Sto. Tomas |  |  |  |  | - | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | PEO | c) | - | g) | - | c) | [9 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | 9.) Construction of Market Stall |  |  | Market |  |  | a) | 500000 | a) | 03/05/16 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For cancellation since the project was already undertaken by Davao Light & no back up cash since it is part of the loan with LBP |  | 2
|  | Brgy. La Libertad, Sto. Tomas |  |  | Stall |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[7 empty] | - | c) | PEO | c) | - | g) | - | c) | [9 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | 10.) Const. of Covered Court Bleacher w/ Roofing |  |  | Court |  |  | a) | 500000 | a) | 03/05/16 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For cancellation since the project was already undertaken by Davao Light & no back up cash since it is part of the loan with LBP |  | 2
|  | Brgy. Cabay-angan, B.E. Dujali |  |  |  |  | - | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | PEO | c) | - | g) | - | c) | [9 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
| C. | Trust Fund | [21 empty] | FS
|  | 1. PRDP | [21 empty] | AC
|  | 1.1 Rehab. of Esperanza-Pob. Sto. Tomas, |  |  | Road | 12.774 | Contract. | a) | 117,410,426.30 | a) | CY 2014 | e) | - | a) | 117,410,426.30 | a) | 100% | c) | 89.82% | a) | 20 | On-going . Request for time extension on process. Waiting for approval of variation order for billing |  | 2
|  | FMR, DDN | [5 empty] | b) | Palero | b) | 03/22/17 | f) | - | b) | 117,410,426.30 | b) | 96% | d) | -6.179% | b) | 600 |  |  | 2
[8 empty] | c) | Alzam | c) | 07/22/19 | g) | - | c) | 113,335,769.31 | [8 empty] | 2
[8 empty] | d) | 853 CD | d) | - | [12 empty] | 2
|  | 1.2 Construction of Dalisay Potable Water System |  |  | Water | - | Contract. | a) | 4664033.76 | a) | CY 2014 | e) | - | a) | 4664033.76 | a) | 100.00% | c) | 82.88% | a) | - | for resumption |  | 2
[5 empty] | System |  |  | b) | Estorco | b) | 01/29/18 | f) | 39 CD | b) | 4664033.76 | b) | 87.94% | d) | -5.06% | b) | - |  |  | 2
[8 empty] | c) | Ancor Water Resources | c) | 07/23/18 | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | 188 CD | d) | 08/31/18 | [12 empty] | 2
|  | 1.3. Construction of Kasilak Potable Water System |  |  | Water | - | Contract. | a) | 7046856.27 | a) | CY 2014 | e) | 72 CD | a) | 7046856.27 | a) | 100.00% | c) | 87.38% | a) | - | for resumption |  | 2
[5 empty] | System |  |  | b) | Estorco | b) | 01/29/18 | f) | - | b) | 7046856.27 | b) | 83.53% | d) | +3.850% | b) | - |  |  | 2
[8 empty] | c) | Ancor Water Resources | c) | 09/24/18 | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | 188 CD | d) | 12/05/18 | [12 empty] | 2
2
|  | 1.4. Improvement of Sto. Tomas Production Center with Common Facility |  |  | Building |  | Contract. | a) | 9825000 | a) | CY 2014 | e) | 72 CD | a) |  | a) |  | c) |  | a) |  | Suspended due to land issue |  | 2
[8 empty] | b) | Azotes | b) | 01/29/18 | f) | - | b) |  | b) |  | d) |  | b) |  |  |  | 2
[8 empty] | c) | Manantan | c) | 09/24/18 | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | 330 C.D | d) | 12/05/18 | [12 empty] | 2
2
|  | SLRF 2015 | [7 empty] | a) |  | e) | 65 days | a) |  | a) | 100% | c) | 100% | a) | 3 | Completed as per POW, Financial Documents on Process |  | 2
|  | Rehab. of Jct. Highway-Tuganay-Anibongan-BE Dujali-Kinamayan Provincial Road (Furtheranace) |  |  | Slope protection | - | - | a) | 1911175.99 | b) | 2019-02-18 | f) | 47 days | b) |  | b) |  | d) | 0% | b) | 60 |  |  | 2
[8 empty] | b) | Balbastro | c) | 2019-09-21 | g) | 9/21/2019 | c) | [9 empty] | 2
[8 empty] | c) | Admin | d) | [13 empty] | 2
[8 empty] | d) | - | [14 empty] | 2
| D. | 20% Development Fund CY 2016 | [21 empty] | FS
|  | 1. Water System Development Projects |  |  | Water |  | Admin | a) | 2000000 | [12 empty] | See project listed below |  | AC
|  | (Provincewide) |  |  | System |  |  | b) | - | [14 empty] | AC
[8 empty] | c) | PEO | [14 empty] | AC
|  | b. | Development of Deepwell Source and Install. Of |  | Water |  | Admin | a) | 645,000.00 | a) | 11/08/18 | e) | - | a) | 645,000.00 | a) | 82.76% | c) | 72.89% | a) | 4 | drilling works completed 7/15/2019 but insufficient water source |  | 2
|  |  | Pipelines, Licup, samal Dist. IGACOS |  | System |  |  | b) | Diosanta | b) | 03/01/19 | f) | - | b) | 645,000.00 | b) | - | d) | -9.87% | b) | 100 |  |  | 2
|  |  | (Previously Deepwell Drilling at Licup) |  |  |  |  | c) | PEO | c) | 05/10/19 | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | 2. Rural Electrification (Provincewide) |  |  | Elect. |  | Admin | a) | 5000000 | [12 empty] | See projects listed below |  | AC
[8 empty] | b) | Foronda/Ababon | [14 empty] | AC
[8 empty] | c) | Admin | [14 empty] | AC
[8 empty] | d) | - | [14 empty] | AC
|  | 2.1 | Inst. of transformer and accessories, |  | Elect. |  | Admin | a) | 150,000.00 | a) | 07/31/18 | e) | - | a) | 150,000.00 | a) | - | c) | - | a) | - | For PR - c/o Engr Kim Pao Lu |  | 2
|  |  | Brgy. Kinawitnon |  |  |  |  | b) | - | b) | - | f) | - | b) | 150,000.00 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | 2.2 | Electrification expansion to Purok 7, |  | Elect. |  | Admin | a) | 1,537,404.57 | a) | 02/04/19 | e) | - | a) | 1,537,404.57 | a) | - | c) | - | a) | - | Waiting for NTP - c/o Engr Kim Pao Lu |  | 2
|  |  | Brgy. Guilon, samal Dist. IGCS |  |  |  |  | b) | - | b) | - | f) | - | b) | 1,537,404.57 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | 2.3 | Rural Electrification at brgy. Sta. Cruz, |  | Elect. |  | Contract | a) | 2000000 | a) | - | e) | - | a) | 2000000 | a) | - | c) | - | a) | - | Delay due to action of Daneco for staking. c/o Engr. Kim |  | 2
|  |  | talikud, Samal |  |  |  |  | b) | - | b) | - | f) | - | b) | 2000000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | Admin | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | 3. Const./Rehab./Comp. of Various Gov't. Bldgs. |  |  | Bldgs./ | - | Admin | a) | 9,000,000.00 | [12 empty] | See project listed below |  | AC
|  | Struct., Fac. (Provincewide) |  |  | Fence |  |  | b) | Foronda/Ababon | [14 empty] | AC
[8 empty] | c) | PEO | [14 empty] | AC
|  | 2.1 | Construction of Provincial Training Center |  | Fence |  | Admin | a) | 940,000.00 | a) | 09/19/17 | e) | - | a) | 940,000.00 | a) | 68.00% | c) | 75.00% | a) | - | Temporarily suspended 4/23/18 due to undemolished structures of illegal settlers |  | 2
|  |  | Compound Fence, Kinawitnon, Babak |  |  |  |  | b) | Pacquiao | b) | 03/12/18 | f) | - | b) | 940,000.00 | b) | - | d) | - | b) | - |  |  | 2
|  |  | District, IGCS |  |  |  |  | c) | PEO | c) | 06/19/18 | g) | - | c) | 933,418.80 | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
| A.4 | 20% Development Fund CY 2017 | [21 empty] | FS
|  | STIMULUS PROJECTS CY 2017 | [21 empty] | FS
|  | ASUNCION | [21 empty] | FS
|  | 1 | Construction of Water Reservoir & |  | Water |  | MEO | a) | 500000 | a) | 12/28/17 | e) | - | a) | 500000 | a) | 90.00% | c) | 90.00% | a) | - | Suspended due to non availability of water source during drilling.Find another location. Fund already transferred at Municipality of Asuncion with ChecK No. 2445174 and OR # 9238468, |  | 1
| 1 |  | Purchase of P.E. Pipelines, Sagayen, |  | System |  |  | b) | - | b) | 11/15/18 | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
|  |  | Asuncion |  |  |  |  | c) | MEO | c) | - | g) | - | c) | - | [8 empty] | 1 | 1 | Asuncion | Red
[8 empty] | d) | - | d) | - | [12 empty] | 1 | 2 | B.E. Dujali | Yellow
|  | NEW CORELLA | [21 empty] | FS | 3 | Carmen | Blue
| 5 | 1 | Road Rehabilitation at Prk. 1-Prk. 5, |  | Road |  | MEO | a) | 500000 | a) | 11/29/17 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Fund already transferred at Municipality of New Corella with ChecK No. 2445213 and OR # 8592072, dated March 13, 2018. Waiting for availability of Bulldozer |  | 1 | 4 | Kapalong | Pink
|  |  | Sta. Fe, New Corella |  |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1 | 5 | New Corella | Gray
[8 empty] | c) | MEO | c) | - | g) | - | c) | - | [8 empty] | 1 | 6 | San Isidro | Orange
[8 empty] | d) | - | d) | - | [12 empty] | 1 | 7 | Sto Tomas | Sky Blue
|  | TAGUM CITY | [21 empty] | FS | 8 | Talaingod | Violet
| 11 | 1 | Construction of Multi-Purpose GYM at |  | Bldg. |  | - | a) | 500000 | a) | 11/29/17 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For AIP amendment due to change of priority.Last priority recommended was Const. of Drainage (Box Culvert) at Purok Sampaguita but funded and implemented by the City of Tagum.Waiting for new project priority |  | 1 | 9 | Panabo City | Brown
|  |  | Mangga E/S, Visayan Village, Tagum City |  |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1 | 10 | IGACOS | Yellow Green
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1 | 11 | Tagum City | Green
[8 empty] | d) | - | d) | - | [12 empty] | 1
|  | KAPALONG | [21 empty] | FS
| 4 | 1 | Impv't. of Brgy. Hall, Sua-on, Kapalong |  | Bldg. |  | - | a) | 500000 | a) | 02/13/18 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For AIP Amendment |  | 1
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| 4 | 2 | Construction of Solar Drier, Semong, |  | Solar |  | - | a) | 500,000.00 | a) | 12/28/17 | e) | - | a) | 500,000.00 | a) | - | c) | - | a) | - | For AIP Amendment |  | 1
|  |  | Kapalong |  | Drier |  |  | b) | - | b) | - | f) | - | b) | 500,000.00 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| 4 | 3 | Construction of Multi-Purpose Pavement, |  | MPP |  | - | a) | 500000 | a) | 12/28/17 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For AIP Amendment |  | 1
|  |  | Florida, Kapalong |  |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| 4 | 4 | Construction of Concrete Bleacher, |  | Bleacher |  | - | a) | 500000 | a) | 12/07/17 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For AIP Amendment |  | 1
|  |  | Tiburcia, Kapalong |  |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
| 4 | 5 | Mainline Pipes for PWS, Mabantao, |  | Water |  | - | a) | 500000 | a) | 12/07/17 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | To change priority but not yet submitted new resolution c/o Engr. Amamio. Note: Previous project was funded by LGU |  | 1
|  |  | kapalong |  | System |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| 4 | 6 | Impv't. of Covered Court, Pag-Asa, |  | Court |  | - | a) | 500000 | a) | 12/07/17 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For AIP Amendment |  | 1
|  |  | Kapalong |  |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| 4 | 7 | Covered Court Bleacher, Katipunan, |  | Bleacher |  | - | a) | 500000 | a) | 12/07/17 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For AIP Amendment |  | 1
|  |  | Kapalong |  |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| 4 | 8 | Improvement of Gabuyan Covered Court, |  | Court |  | Admin | a) | 500000 | a) | 12/07/17 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For AIP Amendment |  | 1
|  |  | Brgy. Gabuyan, Kapalong |  |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | PEO | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| A.4 | 20% Development Fund CY 2017 | [21 empty] | FS
| 4 | 9 | Ground Development and Landscape |  | Fence |  | Admin | a) | 1000000 | a) | ,11/4/2019 | e) | - | a) | 1000000 | a) | - | c) | 21.38 | a) | - | On-going |  | 1
[8 empty] | b) | - | b) | 01/31/2020 | f) | - | b) | 1000000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | PEO | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | 89 CD | d) | - | [12 empty] | 1
|  | TALAINGOD | [21 empty] | FS
| 8 | 1 | Const. of Covered Court Bleacher. |  | Elect. |  | Barangay | a) | 500000 | a) | 12/28/17 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Fund already transferred at Municipality of Talaingod with ChecK No. 2445181 and OR # 7955667, dated March 16, 2018 . Amended from Electrification @ Prk. 1A-Prk. 5A |  | 1
|  |  | Palma Gil, Talaingod |  |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) |  | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
|  | CARMEN | [19 empty] | declared as savings, forwarded to 2020 priority list of projects |  | AC
|  | 1 | Construction of Concrete Pavement |  | Pavement |  | Barangay | a) | 500000 | a) | 03/16/18 | e) | - | a) | 500000 | a) | - | c) | - | a) | - |  |  | 2
|  |  | Tibulao, Carmen |  |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | 2 | Construction of Evaluation Center at Prk. 1, |  | Bldg. |  | Barangay | a) | 500000 | a) | 12/28/17 | e) | - | a) | 500000 | a) | - | c) | 100% | a) | - | Completed |  | 2
|  |  | Asuncion, Carmen |  |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | 5 | Evacuation Center, Anibongan, Carmen |  | Bldg. |  | Barangay | a) | 500000 | a) | 03/16/18 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | declared as savings, forwarded to 2020 priority list of projects |  | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | 7 | Const. of Canal Lining @ Brgy. Site, |  | Canal |  | - | a) | 500000 | a) | 03/16/18 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | declared as savings, forwarded to 2020 priority list of projects |  | 2
|  |  | Tubod, Carmen |  | Lining |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | 9 | Rehab./Impv't. of Minda Brgy. Hall, |  | Bldg. |  | Barangay | a) | 500000 | a) | 05/10/18 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | declared as savings, forwarded to 2020 priority list of projects |  | 2
|  |  | Minda, Carmen |  |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | PANABO CITY | [21 empty] | AC
|  | 1 | Const of Market Stall/Building, Consolacion, |  | Bldg. |  | Barangay | a) | 500000 | a) | 12/28/17 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Fund transfer to LGU- 3/28/2019 with check no.2574928 and OR no. 0166514 - Issued warning for Termination of the Contract |  | 2
|  |  | Panabo CIty |  |  |  |  | b) | - | b) | 5/28/2019 | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | 2 | Rehab. Of Multi-Purpose Hall (Covered Court), |  | Footbridge |  | Barangay | a) | 500000 | a) | 12/28/17 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Fund transfer to LGU- 3/28/2019 with check no.2574927 and OR no. 0166516 - Delivery of Materials on process |  | 2
|  |  | Upper Licanan, Panabo City |  |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | 5 | Impv't. of Multi-Purpose Gym, Kauswagan, |  | GYM |  | Barangay | a) | 500000 | a) | 02/04/19 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Fund transfer to LGU- 3/28/2019 with check no.2574942 and OR no. 0166515 - procurement on process for bidding 8/5/2019 |  | 2
|  |  | Panabo CIty |  |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | 9 | Const. of MP Bldg. w/ Electrical installation, |  | Bldg. |  | Barangay | a) | 500000 | a) | 01/31/18 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Fund transfer to LGU- 3/28/2019 with check no. 2574942 and OR no 01665515 - procurement on process |  | 2
|  |  | San Roque, Panabo City |  |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | 14 | Const. of Multi-Purpose Bldg. (Back Stage/Office), San Nicolas, |  | Bldg. |  | Barangay | a) | 500000 | a) | 12/28/17 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Completed based on POW. Financial Documents on process |  | 2
|  |  | San Nicolas, Panabo City |  |  |  |  | b) | - | b) | 5/21/2019 | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | 16 | Const. of Multi-Purpose Bldg., |  | Bldg. |  | Barangay | a) | 300000 | a) | 12/19/17 | e) | - | a) | 300000 | a) | - | c) | - | a) | - | Issued warning for termination of the contract |  | 2
|  |  | Cacao, Panabo City |  |  |  |  | b) | - | b) | 12/14/2018 | f) | - | b) | 300000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | 17 | Const. of Multi-Purpose Bldg. @ A.O. Floriendo |  | Bldg. |  | Barangay | a) | 500000 | a) | 12/19/17 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Fund transfer to LGU- 3/28/2019 with check no. 2574939 and OR no. 0166518 - Materials Delivered. Construction on-going |  | 2
|  |  | National Highschool, Panabo City |  |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | STO. TOMAS | [21 empty] | AC
|  | 1 | Renov. Of Brgy. Hall, Esperanza, |  | Bldg. |  | - | a) | 500000 | a) | 12/28/17 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | declared as savings, forwarded to 2020 priority list of projects |  | 2
|  |  | Panabo City |  |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | 2 | Const. of Concrete Drainage Canal, Kimamon, |  | Drainage |  | Barangay | a) | 500000 | a) | 12/19/17 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | on-going |  | 2
|  |  | Panabo City |  |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | IGACOS | [21 empty] | AC
|  | 1 | Electrification of Prk. 4 & 6, Brgy. Toril, IGCS |  | Elect. |  |  | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | No abstract |  | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | PEO | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | 2 | Impv't. of Brgy. Street Electrification at |  | Elect. |  |  | a) | 500000 | a) | 11/28/17 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Verified at PBO 7/18/2019 that fund is not available. Proposed priority project for 2020\ |  | 2
|  |  | Brgy. Anonang, IGCS |  |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | PEO | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | 3 | Impv't of Brgy. Hall, Tagpopongan |  |  |  |  | a) | 500000 | a) | 11/28/17 | e) | 259 | a) | 500000 | a) | - | c) | 100% | a) | - | Completed based on POW. Financial Documents on process |  | 2
|  |  | IGACOS |  |  |  |  | b) | Roque | b) | 9/17/2018 | f) | 30 | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | PEO | c) | 12/30/2018 | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | 10/15/2019 | [12 empty] | 2
| F. | SDH IGCS - CONST. IN PROGRESS - BLGS. CY 2017 | [21 empty] | AC
|  | 1 | Construction Perimeter Fence Ph.II (Hospital |  | Fence |  | Admin | a) | 1,305,000.00 | a) | 11/10/17 | e) | 392 | a) | 1,305,000.00 | a) | 100% | c) | 100% | a) | 4 | Completed based on POW. Financial Documents on process |  | AC
|  |  | Compound) Samal District Hospital, IGCS |  |  |  |  | b) | Porras | b) | 03/12/18 | f) | 45 | b) | 1,305,000.00 | b) | - | d) | 1% | b) | 30 |  |  | AC
[8 empty] | c) | PEO | c) | 06/19/18 | g) | - | c) | 958,597.98 | [8 empty] | AC
[8 empty] | d) | - | d) | [13 empty] | AC
|  | 2. Const./Rehab./Comp. of Various Gov't. Bldgs. |  |  | Bldg. | - | Admin | a) | 9,000,000.00 | [12 empty] | Investigation/Inspection of priority projects |  | 2
|  | Struct., Fac. (Provincewide) | [5 empty] | b) | Foronda/Ababon | [14 empty] | AC
[8 empty] | c) | PEO | [14 empty] | AC
[8 empty] | d) | - | [14 empty] | AC
| 11 | 2.1 | Rehab. Of PEO Training Center |  | Bldg. |  | Admin | a) | 476,876.00 | a) | 02/12/19 | e) | - | a) | 476,876.00 | a) | 22.82% | c) | 22.82% | a) | 8 | On-going |  | 1
|  |  | (PDPM),Mankilam, Tagum City |  |  |  |  | b) | Chua | b) | 2019-04-11 | f) | - | b) | 476,876.00 | b) | - | d) | 0% | b) | - |  |  | 1
|  |  | (Part of P803,000.00)(20% DF CY 2018-P326,124.00) |  |  |  |  | c) | PEO | c) | 01/17/19 | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
|  | 2.2 | Repair/Rehab. Of PEO Building |  | Bldg. |  | Admin | a) | 1,800,000.00 | a) | 07/31/18 | e) | - | a) | 1,800,000.00 | a) | 62.23% | c) | 100% | a) | 5 | Completed based on POW. Financial Documents on process |  | 1
| 11 |  | (Motorpool),Mankilam, Tagum City |  |  |  |  | b) | Chua | b) | 03/04/19 | f) | - | b) | 1,800,000.00 | b) | - | d) | 37.77% | b) | 105 |  |  | 1
[8 empty] | c) | PEO | c) | 08/10/19 | g) | - | c) | 1481510.07 | [8 empty] | 1
[8 empty] | d) | 160 CD | d) | - | [12 empty] | 1
|  | 2.3 | Improvement of Garciaville Day Care |  | Bldg. |  | Admin | a) | 330,000.00 | a) | 11/06/18 | e) | - | a) | 330,000.00 | a) |  | c) | 100% | a) | 3 | Completed based on POW. Financial Documents on process |  | 1
| 11 |  | Center, Mankilam, Tagum City |  |  |  |  | b) | - | b) | 09/02/19 | f) | - | b) | 330,000.00 | b) | - | d) |  | b) | 90 |  |  | 1
[8 empty] | c) | PEO | c) | 10/11/19 | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
|  | 3. Rural Electrification (Provincewide) |  |  | Elect. |  | - | a) | 5000000 | [12 empty] | See projects listed below |  | AC
[8 empty] | b) | Foronda | [14 empty] | AC
[8 empty] | c) | - | [14 empty] | AC
[8 empty] | d) | - | [14 empty] | AC
|  | 3.1 | Electrification of Purok 1-4, Sta. Cruz, |  | Elect. |  | Admin | a) | 2,500,000.00 | a) | 02/04/19 | e) | - | a) | 2,500,000.00 | a) | 10% | c) | 12% | a) | - | On-going |  | 1
| 5 |  | New Corella |  |  |  |  | b) | - | b) | - | f) | - | b) | 2,500,000.00 | b) | - | d) | 2% | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| B.3 | Supplemental Budget # 4 CY 2017 | [21 empty] | FS
| 11 | 1 | Upgrading of DDNSTC (Basketball/Voleyball |  | Covered | 2252.69 sq.m | Contract | a) | 99992356.64 | a) | 10/16/18 | e) | - | a) | 99992356.64 | a) | 100% | c) | 72.6% | a) | 5 | On-going |  | 1
|  |  | MP Covered Court),Sports Center, Mankilam, |  | Court |  |  | b) | Escurzon | b) | 07/17/18 | f) | 20 CD | b) | 99992356.64 | b) | - | d) | -27.4% | b) | 150 |  |  | 1
|  |  | Tagum City |  |  |  |  | c) | YBC | c) | 07/11/19 | g) | - | c) | 18, 280, 402.33 | [8 empty] | 1
[8 empty] | d) | 360 CD | d) | 07/31/19 | [12 empty] | 1
| C.1 | Trust Fund 2014 | [21 empty] | FS
|  | 1. PAMANA-DILG CY 2014 | [21 empty] | AC
| 4 | 1.1 Construction of Biga Bridges, Kapalong |  |  | Road | 2-18ln.m | Contract | a) | 24959503.45 | a) | CY 2014 | e) | 304 CD | a) | 24959503.45 | a) | 100.00% | c) | 85.37% | a) | 8 | On-going |  | 1
[8 empty] | b) | Limpo | b) | 07/01/16 | f) | - | b) | 24959503.45 | b) | 99.7% | d) | -14.33% | b) | 290 |  |  | 1
[8 empty] | c) | Dvo. Rock Mixer | c) | 07/30/18 | g) | - | c) | 37,439,255.18 | [6 empty] | Issued warning letter & submit catch-up plan |  | 1
[8 empty] | d) | 880 CD | d) | 09/27/19 | [12 empty] | 1
| 4 | 1.2 Road Rehabilitation/Improvement of Prk. 3, |  |  | Road | 13.60 kms | Contract | a) | 50,500,288.95 | a) | CY 2014 | e) | - | a) | 50,500,288.95 | a) | 100.00% | c) | 100% | a) | 25 | Completed based on Physical Accomplishment. Financial Document on process |  | 1
|  | Palma Gil-Prk.2 (side 2), Sto. Niño-Mahayahay-Tugas- | [5 empty] | b) | Dadula | b) | 07/07/16 | f) | 398 CD | b) | 50,500,288.95 | b) | 100% | d) | 0% | b) | 750 |  |  | 1
|  | Nanaga Road, with 1 -unit, 40 ln.m PSCG Bridge, |  |  |  | 40 ln.m |  | c) | Puregold | c) | 03/12/18 | g) | - | c) | 41424313.06 | [8 empty] | 1
|  | Kapalong | [5 empty] | d) | 1011 CD | d) | 04/14/19 | [12 empty] | 1
| C.2 | Trust Fund 2015 | [21 empty] | FS
|  | 1. PRDP CY 2015 | [21 empty] | AC
| 4 | 1.1 Rehab. Of Capungagan-Boundary San |  |  | Road | 10.6 kms. | Contract. | a) | 108,303,841.70 | a) | CY 2015 | e) | 140 CD | a) | 108,303,841.70 | a) | 100.00% | c) | 93.23% | a) | 38 | On-going |  | 1
|  | Miguel FMR, Kapalong, Davao del Norte | [5 empty] | b) | Nasol | b) | 04/06/16 | f) | 634 | b) | 108,303,841.70 | b) | 96.05% | d) | -2.82% | b) | 1140 | Increase of Project Cost due to Variation Order with |  | 1
[8 empty] | c) | VICLAO | c) | 03/26/17 | g) | - | c) | 38,212,432.90 | [6 empty] | Extra Work. (Php 4,992,591.29) |  | 1
[8 empty] | d) | 1352 | d) | 12/18/2019 | [12 empty] | 1
| 5 | 1.2 Rehab. Of Pob.-Limbaan-Suawon-Macgum |  |  | Road | 15.01 kms./ | Contract. | a) | 205,202,114.16 | a) | CY 2015 | e) | 229 CD | a) | 205,202,114.16 | a) | 100.00% | c) | 71.41% | a) | 40 | On-going |  | 1
|  | FMR w/ Bridge, New Corella, Davao del Norte |  |  |  | 42 ln.m |  | b) | Madrigal | b) | 04/08/16 | f) | 490 CD | b) | 205,202,114.16 | b) | 82.51% | d) | -11.1% | b) | 1200 | Increase of Project Cost due to Variation Order Php 14,948,622.18 |  | 1
[8 empty] | c) | Dvo. Rock Mixer | c) | 01/18/19 | g) | - | c) | 28538091.3 | [8 empty] | 1
[8 empty] | d) | 1529CD | d) | 06/14/20 | [10 empty] | Partial suspension due to soft soil from sta. 8+000 - 10+000 |  | 1
| 1 | 1.3 Rehab. Of Sonlon - Camansa FMR |  |  | Road |  | Contract. | a) | 215125015.81 | a) | 9/18/2018 | e) |  | a) | 215125015.81 | a) | 24.63% | c) | 23% | a) | 30 | On-going |  | 1
|  | Asuncion, Davao del Norte | [5 empty] | b) | Fabiala | b) | 5/28/2019 | f) |  | b) | 215125015.81 | b) |  | d) | -1.63% | b) | 780 |  |  | 1
[8 empty] | c) | Three w/Builders, Inc? Davao Rock Mixer Enterprises (JV) | c) | 12/31/2020 | g) | - | c) | [9 empty] | 1
[8 empty] | d) | 1529CD | d) | 06/14/20 | [12 empty] | 1
|  | 2. KALSADA CY 2015 | [21 empty] | AC
| 6 | 2.1 Improvement of Km. 9 Sagayen-Sawata Provincial |  |  | Road | 3177 ln.m m | Contract | a) | 47213478.31 | a) | CY 2015 | d) | - | a) | 47213478.31 | a) | 100.00% | c) | 37.556% | a) |  | Contract Terminated |  | 1
|  | San Isidro, Davao del Norte | [5 empty] | b) | Limpo | b) | 08/26/16 | e) |  | b) | 47213478.31 | b) | 86.25% | d) | -48.69% | b) |  |  |  | 1
[8 empty] | c) | Arn Builders | c) | 04/21/18 | f) | - | c) | 24931805.19 | [8 empty] | 1
[8 empty] | d) |  | d) | [13 empty] | 1
| 6 | 2.2 Improvement of Km. 9 Sagayen-Sawata Provincial |  |  | Road | 6667.54 m | Admin | a) | 33401544.78 | a) | CY 2015 | d) | - | a) | 33401544.78 | a) | 51.85% | c) | 94.66% | a) | 30 | Original contract terminated due to very poor performance |  | 1
|  | San Isidro, Davao del Norte | [5 empty] | b) | Limpo | b) | 10/16/18 | e) |  | b) | 33401544.78 | b) | 95.76% | d) | -8.05% | b) | 900 | of the contractor.The contract cost P 47,213,478.31. |  | 1
[8 empty] | c) | PEO | c) | 09/14/19 | f) | - | c) | 19,943,597.92 | [6 empty] | On-going |  | 1
[8 empty] | d) | 334 CD | d) | [13 empty] | 1
| C.3 | Trust Fund 2016 | [21 empty] | FS
|  | 1. PRDP CY 2016 | [21 empty] | AC
| 4 | 1.1 | Cacao Production and Beans Marketing, |  | Bldg. | - | Contract. | a) | 5873626.8 | a) | CY 2016 | e) | - | a) | 5873626.8 | a) | 90.86% | c) | 84.06% | a) | 9 | On-going |  | 1
|  |  | Capungagan, Kapalong, Davao del Norte |  |  |  |  | b) | Delos Reyes | b) | 03/19/19 | f) | - | b) | 5873626.8 | b) | - | d) | -6.798% | b) | 63 | Suspension Letter on process due to |  | 1
[8 empty] | c) | MICAH CONST. & SUPPLY | c) | 11/23/19 | g) | - | c) | - | [6 empty] | modification of Detailed Design of |  | 1
[8 empty] | d) | 250 CD | d) | - | [10 empty] | mechanical Drier |  | 1
| C.4 | Trust Fund 2017 | [21 empty] | FS
|  | 1. CMGP (Conditional Matching Grant to Provinces) | [21 empty] | AC
| 6 |  | Road Upgrading km.9 sagayen-Sawata |  | Road | 10.20 km | Contract | a) | 139,761,975.14 | a) | CY 2017 | e) | - | a) | 139,761,975.14 | a) | 93.839 | c) | 93.27 | a) | 28 | On-going |  | 1
|  |  | (Sagayen-Jct. San Miguel Section) |  |  |  |  | b) | Avila | b) | 10/01/18 | f) | - | b) | 139,761,975.14 | b) | - | d) | -0.569 | b) | 11170 |  |  | 1
[8 empty] | c) | Legacy Const. Corp. | c) | 08/22/19 | g) | - | c) | 63100753.7 | [8 empty] | 1
[8 empty] | d) | 326 CD | d) | - | [12 empty] | 1
| 8 |  | Road Upgrading of Dagohoy - Daligdigon |  | Road | 2.532 km | Contract | a) | 58048310.68 | a) | CY 2017 | e) | - | a) | 58048310.68 | a) | 100.00% | c) | 100% | a) | 16 | Completed as per Physical Accomplishment, Financial Documents on Process |  | 1 | 1
|  |  | Provincial Road |  |  |  |  | b) | Fabiala | b) | 01/05/18 | f) | 205 CD | b) | 58048310.68 | b) | - | d) | 0% | b) | 480 |  |  | 1
[8 empty] | c) | PUREGOLD | c) | 11/18/18 | g) | - | c) | 29,572,637.70 | [8 empty] | 1
[8 empty] | d) | 246 CD | d) | 03/31/19 | [12 empty] | 1
|  |  | Impv’t. of Maligaya-New Camiling Prov’l. |  | Conc. | 2.13 km | Contract. | a) | 50101614.08 | a) | CY 2017 | e) | 76 CD | a) | 57385680 | a) | 100.00% | c) | 100% | a) | 21 | Completed based on POW. Financial Documents on process |  | 2
|  |  | Road w/ Bridge Component,Carmen |  |  |  |  | b) | Mellomida | b) | 12/18/17 | f) | 209 CD | b) | 57385680 | b) | 100% | d) | 0% | b) | 147 |  |  | 2
[8 empty] | c) | PUREGOLD CONST. | c) | 02/15/19 | g) | - | c) | 36005452 | [8 empty] | 2
[8 empty] | d) | 376 CD | d) | 07/31/19 | [12 empty] | 2
|  |  | Road Upgrading of FDR. Rd.3 – |  | Conc. | 10.359 km | Contract. | a) | 119901954.82 | a) | CY 2017 | e) | 47 CD | a) | 119901954.82 | a) | 100.00% | c) | 100% | a) | 10 | Completed based on POW, Financial Documents on Process |  | 2
|  |  | Kimamon – Luna Provincial Road, |  |  |  |  | b) | Comidoy | a) | 12/29/17 | f) | 198 CD | b) | 119901954.82 | b) | 100% | d) | 100% | b) | 220 |  |  | 2
|  |  | Sto. Tomas |  |  |  |  | c) | GP & H CONST. | c) | 12/12/18 | g) | - | c) | 119901954.82 | [8 empty] | 2
[8 empty] | d) | 326 CD | d) | 2019-07-29 | [12 empty] | 2
|  |  | Road Upgrading of Anahaw-Maligaya |  | Conc. | 5.18 km | Contract. | a) | 78,228,121.56 | a) | CY 2017 | e) | - | a) | 78,228,121.56 | a) | 100.00% | c) | 100% | a) | 30 | 100% as of August 31, 2019 |  | 2
|  |  | Provincial Road, Carmen |  |  |  |  | b) | Fernandez | b) | 12/24/17 | f) | 306 CD | b) | 78,228,121.56 | b) | 100% | d) | 0% | b) | 660 | Subject for liquidated damages |  | 2
[8 empty] | c) | MONOLITHIC CONST. | c) | 03/31/19 | g) | - | c) | 76,214,361.38 | [8 empty] | 2
[8 empty] | d) | 210 CD | d) | 2019-06-05 | [12 empty] | 2
|  | 2. OPPAP-PAMANA | [21 empty] | AC
1
| 11 | 2.2 | Const. of Trading Post, Storage Building |  | Bldg. |  | Contract | a) | 3,975,000.00 | a) | CY 2017 | e) | - | a) | 3,975,000.00 | a) | - | c) | - | a) | - | Rebidding |  | 1
|  |  | with (1) unit Hauling Truck, Brgy. Pandapan |  |  |  |  | b) | - | b) | - | f) | - | b) | 3,975,000.00 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
|  | 2.1 | Const. of Trading Post, Storage Building |  | Bldg. |  | Contract | a) | 3,975,000.00 | a) | CY 2017 | e) | - | a) | 3,975,000.00 | a) | - | c) | - | a) | - | c/o Engr. Rickris Fernandez |  | 2
|  |  | with (1) unit Hauling Truck, Prk. Ramihan |  |  |  |  | b) | - | b) | - | f) | - | b) | 3,975,000.00 | b) | - | d) | - | b) | - |  |  | 2
|  |  | Datu Abdul, Panabo City |  |  |  |  | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | 2.2 | Construction of Tribal Hall, Sto. Tomas |  | Bldg. |  | Admin | a) | 500000 | a) | CY 2018 | e) | - | a) | 500000 | a) | 100% | c) | 89.5% | a) | 7 | Suspended 6/28/2019, Suspended due to Delivery of Materials J.O, For time extension |  | 2
[8 empty] | b) | Roque | b) | 2019-05-22 | f) | - | b) | 500000 | b) | - | d) | 0.79% | b) | 110 |  |  | 2
[8 empty] | c) | - | c) | 2019-07-31 | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
| C.5 | LDRRM - Trust Fund | [21 empty] | FS
| 5 | 1. Construction of Slope Protection and Concrete Pavement along Sta. Fe Mambing Road Section |  |  | Slope |  | Admin | a) | 1,853,000.00 | a) | 11/28/18 | e) |  | a) | 1,853,000.00 | a) | 100% | c) | 100% | a) | 16 | Completed based on POW. Financial Documents on process |  | 1
[8 empty] | b) | Gone | b) | 12/03/18 | f) | 108 CD | b) | 1,853,000.00 | b) | - | d) |  | b) | 144 |  |  | 1
[8 empty] | c) | PEO | c) | 02/28/19 | g) | 10/30/2019 | c) | 742252.72 | [8 empty] | 1
[8 empty] | d) | 86 CD | d) | 06/15/2019 | [12 empty] | 1
| 5 | 2. Rehab. Of Saug Bridge of Slope Protection |  |  | Slope |  | Admin | a) | 4,850,000.00 | a) | 05/25/18 | e) | - | a) | 4,850,000.00 | a) | 23.60% | c) | 9.60% | a) | - | Suspended dated 01/28/19 |  | 1
[8 empty] | b) | Gone | b) | 01/03/19 | f) | - | b) | 4,850,000.00 | b) |  | d) | -14% | b) | - |  |  | 1
[8 empty] | c) | PEO | c) | 03/25/19 | g) | - | c) | 1628912.92 | [8 empty] | 1
[8 empty] | d) | 82 CD | d) | - | [12 empty] | 1
| 1 | 3. Rehab. Of Canatan Bridge Slope Protection |  |  | Slope | 395 sq.m. | Contract | a) | 9200000 | a) | 06/20/2018 | e) | - | a) | 9200000 | a) | 100% | c) | 100% | a) | - | Completed |  | 1 | 1
|  | Brgy. Canatan, Asuncion | [5 empty] | b) | Aclaracion | b) | 02/11/2019 | f) | 35 CD | b) | 9200000 | b) | 100% | d) | 0% | b) | - |  |  | 1
[8 empty] | c) | J-One Builders | c) | 04/12/2019 | g) | 05/31/2019 | c) | 7222021.59 | [8 empty] | 1
[8 empty] | d) | 60 CD | d) | 05/01/2019 | [12 empty] | 1
| 4 | 4. Re-channeling of BIGA River with Earth Dike and Slope Protection, Brgy. Gupitan, Kaplaong |  |  | Dike/Slope |  | Contract | a) | 12,100,000.00 | a) | 07/20/18 | e) | - | a) | 12,100,000.00 | a) | 8.30% | c) | 3.36% | a) | 4 | Suspended dated March 25, 2019 |  | 1
[8 empty] | b) | Limpo | b) | 02/22/19 | f) | - | b) | 12,100,000.00 | b) |  | d) | -4.94% | b) | 120 | Due to boundary conflict. |  | 1
[8 empty] | c) | Alpha & Omega | c) | 06/11/19 | g) | - | c) | - | [6 empty] | Waiting for the decision from the Bureau of Land |  | 1
[8 empty] | d) | 110 CD | d) | 9/23/2019 | [12 empty] | 1
| 5 | 5. Const. of Cabidianan Bridge Slope Protection, Brgy. Cabidianan, New Corella |  |  | Slope |  | Admin | a) | 3590000 | a) | 07/18/18 | e) | - | a) | 3590000 | a) | 100% | c) | 100% | a) | 8 | Completed based on POW. Financial Documents on process |  | 1
[8 empty] | b) | Gone | b) | 6/17/19 | f) | - | b) | 3590000 | b) |  | d) |  | b) | 80 |  |  | 1
[8 empty] | c) | PEO | c) | 8/20/19 | g) | - | c) | 1929823.4 | [8 empty] | 1
[8 empty] | d) | 65 CD | d) | - | [12 empty] | 1
| D. | SEF(Special Education Fund)-SUPPLEMENTAL BUDGET # 1 CY 2017 | [21 empty] | FS
|  | 1. Const./Impv't./Compl. Of School Bldgs., Struc. & Fac. |  |  | Bldgs. |  | Admin | a) | 3,300,000.00 | [12 empty] | See projects listed below |  | AC
[8 empty] | b) | Foronda | [14 empty] | AC
[8 empty] | c) | PEO | [14 empty] | AC
[8 empty] | d) | - | [14 empty] | AC
| 8 | 1.1 | Construction of 1 unit School Building |  | Bldg. |  | Admin | a) | 1100000 | a) | 02/19/18 | e) | - | a) | 1100000 | a) | 100 | c) | 100 | a) | 6 | Completed based on POW. Financial Documents on process |  | 1
|  |  | Lumabag, Talaingod |  |  |  |  | b) | Dadula | b) | 03/20/19 | f) | 27 CD | b) | 1100000 | b) |  | d) |  | b) | 30 |  |  | 1
[8 empty] | c) | PEO | c) | 05/19/19 | g) | 06/30/2019 | c) | 595230.5 | [8 empty] | 1
[8 empty] | d) | 60 CD | d) | - | [12 empty] | 1
F. 20% Development Fund CY 2018 | [23 empty] | FS
|  | 1. Repair & Maint. Of Various Local Roads |  |  | Road | - | Admin | a) | 5000000 | [12 empty] | See projects listed below |  | AC
|  | and Drainages | [5 empty] | b) | [15 empty] | AC
[8 empty] | c) | Admin | [14 empty] | AC
[8 empty] | d) | - | [14 empty] | AC
|  | 1.1 | Rehabilitation of Brgy. San Antonio |  | Road |  | Admin | a) | 130000 | a) | 04/13/18 | e) | - | a) | 130000 | a) | - | c) | - | a) | - | Proposed priority project for 2020 |  | 2
|  |  | Barangay Road, IGACOS |  |  |  |  | b) | Porras/Pacquiao | b) | - | f) | - | b) | 130000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | PEO | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | 1.2 | Rehabilitation of Brgy. Peñaplata Barangay |  | Road |  | Admin | a) | 139000 | a) | 04/25/18 | e) | 66 CD | a) | 139000 | a) | 100% | c) | 100 | a) | 1 | Completed 8/31/2019 |  | 2
|  |  | Road, IGACOS |  |  |  |  | b) | Porras/Pacquiao | b) | 8/16/2019 | f) | 225 CD | b) | 139000 | b) | - | d) | - | b) | 1 |  |  | 2
[8 empty] | c) | PEO | c) | 8/31/2019 | g) | - | c) | 139000 | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | 1.3 | Rehabilitation of Brgy. Adecor Barangay |  | Road |  | Admin | a) | 138000 | a) | 04/25/18 | e) | 66 CD | a) | 138000 | a) | 60.00% | c) | 60.00% | a) | - | Completed as per POW. Financial Documents on process |  | 2
|  |  | Road, IGACOS |  |  |  |  | b) | Porras/Pacquiao | b) | 10/18/18 | f) | 225 CD | b) | 138000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | PEO | c) | 10/27/19 | g) | - | c) | 111,872.00 | [8 empty] | 2
[8 empty] | d) | - | d) | 10/15/2019 | [12 empty] | 2
|  | 1.4 | Rehabilitation of Brgy. Pob. Kaputian |  | Road |  | Admin | a) | 138000 | a) | 04/25/18 | e) | - | a) | 138000 | a) | 100% | c) | 100% | a) | 4 |  |  | 2
|  |  | Barangay Road, IGACOS |  |  |  |  | b) | Porras/Pacquiao | b) | 2019-08-08 | f) | - | b) | 138000 | b) | - | d) | - | b) | 36 | Completed Sept. 22, 2019 |  | 2
[8 empty] | c) | PEO | c) | 9/22/2019 | g) | 9/22/2019 | c) | - | [8 empty] | 2
[8 empty] | d) | 6/13/19 | d) | - | [12 empty] | 2
|  | 2. Various of Water System Project (Provincewide) |  |  | Water | - | - | a) | 10000000 | [12 empty] | Investigation/Inspection of priority projects |  | AC
[5 empty] | System |  |  | b) | Foronda/Misa | [14 empty] | AC
[8 empty] | c) | PEO | [14 empty] | AC
[8 empty] | d) | - | [14 empty] | AC
|  | 2.1 | Conduct of geo-resistivity/drilling test |  | Geo- | - | - | a) | 250000 | [12 empty] | See list of projects |  | AC
|  |  | of proposed site |  | resistivity |  |  | b) | Diosanta | [14 empty] | AC
[8 empty] | c) | - | [14 empty] | AC
[8 empty] | d) | - | [14 empty] | AC
| 6 |  | 2.1.1 Const. of PWS Linao, San Isidro |  | Water | - | - | a) | 62000 | a) | - | e) | - | a) | 62000 | a) | - | c) | - | a) | - | PO approved September 2, 2019 |  | 1
[5 empty] | System |  |  | b) | - | b) | - | f) | - | b) | 62000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| 6 |  | 2.1.2 Const. of PWS Mamalian, San Isidro |  | Water | - | - | a) | 62000 | a) | - | e) | - | a) | 62000 | a) | - | c) | - | a) | - | For declaration of savings because the spring water source is not feasible for development. |  | 1
[5 empty] | System |  |  | b) | - | b) | - | f) | - | b) | 62000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| 6 |  | 2.1.3 Const. of PWS Sagayen, San Isidro |  | Water | - | - | a) | 62000 | a) | - | e) | - | a) | 62000 | a) | - | c) | - | a) | - | Waiting for the geo-resistivty equipment. |  | 1
[5 empty] | System |  |  | b) | - | b) | - | f) | - | b) | 62000 | b) | - | d) | - | b) | - | (Geo-resistivty equipment PR on process) |  | 1
[8 empty] | c) | PEO | c) | - | g) | - | c) | - | [6 empty] | Aug. 13, 2019 |  | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
|  | 2.2 | Construction of Water System Projects |  | Water | - | - | a) | 9750000 | [12 empty] | See list of projects |  | AC
|  |  | in Component LGUs |  | System |  |  | b) | Diosanta | [14 empty] | AC
[8 empty] | c) | PEO | [14 empty] | AC
[8 empty] | d) | - | [14 empty] | AC
| 11 |  | Installation of potable water System at Purok |  | Water | - | - | a) | 1125000 | a) | - | e) | - | a) | 1125000 | a) | - | c) | - | a) | - | Waiting for deed of donation. Follow-up letter was already issued |  | 1
|  |  | Nangka, Pandapan, Tagum City |  | System |  |  | b) | - | b) | - | f) | - | b) | 1125000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | PEO | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| 1 |  | Rehab./Impv't. of San Vicente |  | Water | - | - | a) | 1125000 | a) | 10/26/18 | e) | - | a) | 1125000 | a) | - | c) | - | a) | - | PO on process |  | 1
|  |  | Water System, Asuncion |  | System |  |  | b) | - | b) | - | f) | - | b) | 1125000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | PEO | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
|  |  | Impv't. of Water System, Brgy. Poblacion |  | Water |  | Admin | a) | 1250000 | a) | 08/24/18 | e) | - | a) | 1250000 | a) | 100% | c) | 85.39% | a) | 8 | Completed (contract by Zular3-Az) September 15, 2019 |  | 2
|  |  | Kaputian (Level II) |  | system |  |  | b) | Porras | b) | 05/3/19 | f) | - | b) | 1250000 | b) | - | d) | -14.61 | b) | 160 |  |  | 2
[8 empty] | c) | Contract | c) | 08/30/19 | g) | 09/15/2019 | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  |  | Water System at brgy. Malativas, |  | Water |  | Admin | a) | 1250000 | a) | - | e) | - | a) | 1250000 | a) | - | c) | - | a) | - | For preparation of POW & Plan c/o PDPM - POSSIBLE TRANSFER OF SITE SUBJECT FOR TRANSFER OF LOCATION . NO DEED OF DONATION |  | 2
|  |  | Panabo City |  | system |  |  | b) | - | b) | - | f) | - | b) | 1250000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | Admin | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  |  | Const. of Potable Water System at |  | Water |  | Admin | a) | 1250000 | a) | 11/21/18 | e) | - | a) | 1250000 | a) | - | c) | - | a) | - | for implementation |  | 2
|  |  | Brgy. Tibungol, Panabo City |  | system |  |  | b) | - | b) | - | f) | - | b) | 1250000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | Admin | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  |  | Potable Water System at Brgy. San |  | Water |  | Admin | a) | 3625000 | a) | 10/25/18 | e) | - | a) | 3625000 | a) | 49.51% | c) | 54.96% | a) | 3 | On-going |  | 2
|  |  | Remegio Kaputian (Level II WS), Samal |  | system |  |  | b) | Diosanta | b) | 7/16/2019 | f) | - | b) | 3625000 | b) | - | d) | 4.62 | b) | 20 |  |  | 2
[8 empty] | c) | Admin | c) | 12/2019 | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | 3. Counterpart to Special Projects (Provincewide) |  |  | Road | - | Contract | a) | 67415000 | [12 empty] | Investigation/Inspection of priority projects |  | AC
[8 empty] | b) | Foronda | [14 empty] | AC
[8 empty] | c) | PEO | [14 empty] | AC
[8 empty] | d) | - | [14 empty] | AC
| 1 | 3.1 | Rehab. Of Sonlon-Camansa FMR, |  | Road | - | Contract | a) | 21512501.501 | a) | 09/18/18 | e) | - | a) | 21512501.501 | a) | 9.332% | c) | 6.249% | a) | - | On-going |  | 1
|  |  | Asuncion, Davao del Norte |  |  |  |  | b) | Fabiala | b) | 5/28/2019 | f) | - | b) | 21512501.501 | b) | - | d) | -3.083% | b) | - |  |  | 1
|  |  | (PRDP Counterpart : 193,612,514.23) |  |  |  |  | c) | - | c) | 12/31/2020 | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) |  | d) | - | [12 empty] | 1
|  | 4. Const./Rehab./Comp. of Various Gov't. Bldgs. |  |  | Bldgs. | - | Admin | a) | 13523124 | [12 empty] | Investigation/Inspection of priority projects |  | AC
|  | Struct., Fac. (Provincewide) | [5 empty] | b) | Foronda | [14 empty] | AC
[8 empty] | c) | PEO | [14 empty] | AC
[8 empty] | d) | - | [14 empty] | AC
| 11 | 4.1 | Rehab. Of PEO Training Center |  | Bldg. |  | Admin | a) | 476876 | a) | 02/12/19 | e) | - | a) | 476876 | a) | - | c) | 9.17% | a) | - | On-going |  | 1
|  |  | (PDPM),Mankilam, Tagum City |  |  |  |  | b) | Chua | b) | - | f) | - | b) | 476876 | b) | - | d) | - | b) | - |  |  | 1
|  |  | (Part of P803,000.00)(20% DF CY 2017-P476,876.00) |  |  |  |  | c) | PEO | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| 1 | 4.2 | Construction of IP Tribal Council of |  | Bldg. |  | Admin | a) | 560,000.00 | a) | - | e) | - | a) | 560,000.00 | a) | - | c) | - | a) | - | POW & Plan for approval |  | 1
|  |  | Women at Brgy. Camansa, Asuncion |  |  |  |  | b) | - | b) | - | f) | - | b) | 560,000.00 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | PEO | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| 11 | 4.3 | Construction of Multi-Purpose Bldg. |  | Bldg. | 303.75 sq.m | Admin | a) | 6748000 | a) | 12/11/18 | e) | - | a) | 6748000 | a) |  | c) | 100% | a) | 25 | Completed |  | 1
|  |  | (PENRO Building), Mankilam, Tagum City |  |  |  |  | b) | Pasiona/Juan | b) | 10/16/18 | f) | 109 | b) | 6748000 | b) | - | d) |  | b) | 750 |  |  | 1
|  |  | (Part of 8,548,000.00) |  |  |  |  | c) | PEO | c) | 9/13/2019 | g) | - | c) | 6560497.45 | [8 empty] | 1
|  |  | (P1,800,000.00 - SB # 3 CY 2017) |  |  |  |  | d) | 256 CD | d) | 06/30/19 | [12 empty] | 1
| 3 | 4.4 | Repair/Rehab. Of PEO Building (2nd District), Carmen |  | Bldg. |  | Admin | a) | 2250000 | a) | 08/10/18 | e) | - | a) | 2250000 | a) | 100% | c) | 100% | a) | 18 | Completed based on POW. Financial Documents on process |  | 2
[8 empty] | b) | Andoy | b) | 02/18/19 | f) | - | b) | 2250000 | b) | - | d) | 0% | b) | 138 |  |  | 2
[8 empty] | c) | Admin | c) | 08/23/19 | g) | - | c) | 1577344.8 | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | 5. Rural Electrification (Provincewide) |  |  | Elect. |  | Admin | a) | 5000000 | [12 empty] | See projects listed below |  | AC
[8 empty] | b) | Kim Pao Lu | [14 empty] | AC
[8 empty] | c) | PEO | [14 empty] | AC
[8 empty] | d) | - | [14 empty] | AC
| 5 | 5.1 | Rural Electrification at Del Monte, |  | Elect. |  | Admin | a) | 1000000 | a) | - | e) | - | a) | 1000000 | a) | - | c) | - | a) | - | Revised POW for Approval. Change of Implementation Mode from Admin to Contract 9/6/2019 |  | 1
|  |  | New Corella |  |  |  |  | b) | - | b) | - | f) | - | b) | 1000000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| 1 | 5.2 | Const. of Distribution Line in Sitio Prk. 1,3,4, |  | Elect. |  | Admin | a) | 4000000 | a) | 11/06/18 | e) | - | a) | 4000000 | a) | - | c) | - | a) | - | For PR |  | 1
|  |  | 11 and 7, Camansa, asuncion |  |  |  |  | b) | - | b) | - | f) | - | b) | 4000000 | b) | - | d) | - | b) | - | Revised POW from Admin to Contract |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
A. 20% Development Fund CY 2018 | K. | GENERAL FUND PROPER CY 2018 | [21 empty] | FS
|  | STIMULUS PROJECTS | [21 empty] | AC
|  | ASUNCION | [21 empty] | AC
| 1 | 1 | Const. of Bleachers and Canopy, |  | Bldg. |  | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Procurement on Process |  | 1
|  |  | Canatan, Asuncion |  |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| 1 | 2 | Const. of Potable water System at Prk. 6, |  | Water |  | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Inspected – Aug. 6, 2019 For plan preparation c/o Amamio |  | 1
|  |  | New Santiago, Asuncion |  | System |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| 1 | 3 | Const. of Canopy, Camoning, Asuncion |  | Bldg. |  | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | P.O. on process |  | 1
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| 1 | 4 | Completion of Electrification at Prk. 10 |  | Elect. |  | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Proposed for future funding. Insufficient Budget to complete the project |  | 1
|  |  | & Prk. 9, Doña Andrea, Asuncion |  |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| 1 | 5 | Construction of Covered Court, |  | Court |  | - | a) | 500000 | a) | 06/05/18 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | for Fund Transfer |  | 1
|  |  | San Vicente, Asuncion |  |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| 1 | 6 | Const. Of Multi-purpose covered court Phase 2 |  | landscaping |  | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Amended from Landscaping and Beautification of Brgy. Ground to fund completion of priority project. Plan and POW for approval |  | 1
|  |  | Brgy. Ground, Pamacaun, Asuncion |  |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
|  | NEW CORELLA | [21 empty] | AC
| 5 | 1 | Const. of Concrete Bleachers, Sta. Cruz, |  | Bleacher |  | - | a) | 500000 | a) | 06/04/18 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Fund transferred to LGU - May 23, 2019 with check no. 0133011 and OR no. 9232849. On going |  | 1
|  |  | New Corella |  |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| 5 | 2 | Completion of Mini GYM at Prk. 2, |  | GYM |  | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Fund transferred to LGU - May 23, 2019 with check no. 0133010 and OR no. 9232850. On going |  | 1
|  |  | San Roque, New Corella |  |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| 5 | 3 | Completion of Covered Court, Sto. Niño, |  | Court |  | - | a) | 500000 | a) |  | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Fund transferred to LGU - May 23, 2019 with check no. 0133012 and OR no. 9232848. On going |  | 1
|  |  | New Corella |  |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| 5 | 4 | Construction of Public Market, Suawon, |  | Bldg. |  | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Fund transferred to LGU - May 23, 2019 with check no. 0133014 and OR no. 9232846. On going |  | 1
|  |  | New Corella |  |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| 5 | 5 | Construction of Concrete Line Drainage at |  | Drainage |  | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Fund transferred to LGU - May 23, 2019 with Check No. 2575058 and OR No. 0342801. On going |  | 1
|  |  | Prk. 10 to Prk. 6, Del Pilar, New Corella |  |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| 5 | 6 | Construction of Stage with Comfort Rooms |  | Bldg. |  | - | a) | 500000 | a) | 07/05/18 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Fund transferred to LGU - May 23, 2019 with check no. 0133013 and OR no. 9232847. On going |  | 1
|  |  | at Mesaoy Mini-Gym, Mesaoy, New Corella |  |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
|  | TAGUM CITY | [21 empty] | AC
| 11 | 2 | Completion of Two Storey Multi-Purpose |  | Bldg. |  | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | 100% | c) | 100% | a) | 5 | Completed based on Physical Accomplishment. Financial Documents on process |  | 1
|  |  | Building, Magugpo East, Tagum City |  |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | 0% | b) | 110 |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| 11 | 3 | Completion of GYM Bleacher w/ |  | Bleacher |  | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | for implementation |  | 1
|  |  | Electrification, Pagsabangan, Tagum City |  |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| 11 | 4 | Construction of Drainage Canal, |  | Drainage |  | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Waiting for delivery of materials |  | 1
|  |  | Libuganon, Tagum City |  |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
|  | KAPALONG | [21 empty] | AC
| 4 | 1 | Construction of Bleacher, Mamacao, |  | Bleacher |  | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Procurement of Materials on process |  | 1
|  |  | Kapalong |  |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| 4 | 2 | Improvement of Capungagan GYM Stage, |  | Stage |  | - | a) | 500000 | a) | 06/05/18 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Re-aligned to proposed project for CY 2020. |  | 1
|  |  | Capungagan, Kapalong |  |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| 4 | 3 | Construction of Concrete Perimeter Fence, |  | Fence |  | Contract | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Procurement of Materials on process |  | 1
|  |  | Luna, Kapalaong |  |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| 4 | 4 | Construction of 1 Unit 2 Classroom |  | Bldg. |  | Contract | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Needs additional funds to complete the project |  | 1
|  |  | School Bldg. at Sampao, kapalong |  |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| 4 | 5 | Completion of Brgy. Health Center, Maniki, |  | Bldg. |  | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Waiting for on-going works funded by other agency to complete. |  | 1
|  |  | Kapalong |  |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
|  | SAN ISIDRO | [21 empty] | AC
| 6 | 1 | Improvement of Water System, Sabangan, |  | Water |  | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | To change priority but not yet submitted new resolution c/o Engr. Amamio |  | 1
|  |  | San Isidro |  | System |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| 6 | 2 | Rehabilitation & Flooring of Gymnasium |  | Court |  | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | 37% | c) | 42% | a) | - | On-going |  | 1
|  |  | Basketball Court, Mamangan, San Isidro |  |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | 5% | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
|  | TALAINGOD | [21 empty] | AC
| 8 | 1 | Grouted Riprap on Embankment |  | Riprap |  | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Plan and POW on process c/o PDPM |  | 1
|  |  | Sto. Ñino, Talaingod |  |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| 8 | 2 | Barangay Hall Improvement, Dagohoy, |  | Bldg. |  | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Plan and POW on process c/o PDPM |  | 1
|  |  | Talaingod |  |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| 8 | 3 | Construction of 2 Classroom Building Datu Jose |  | Bldg. |  | - | a) | 2000000 | a) | - | e) | - | a) |  | a) | - | c) | - | a) | - |  |  | 1
|  |  | Libayao NHS Ext, |  |  |  |  | b) | - | b) | - | f) | - | b) |  | b) | - | d) | - | b) | - |  |  | 1
|  |  | Natulian, Palma Gil, Talaingod |  |  |  |  | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
|  | CARMEN | [19 empty] | Plan and POW Approval on process |  | AC
|  | 1 | Completion of Evacuation Center Building, |  | Bldg. |  | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - |  |  | 2
|  |  | San Isidro, Carmen |  |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | PANABO CITY | [19 empty] | Amended from Const. of New Brgy. Stage due to funding of Phase 1 by the LGU. Plan and POW on process c/o PDPM |  | AC
|  | 1 | Const. of New Brgy. Stage, Phase II |  | Stage |  | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - |  |  | 2
|  |  | San Pedro, Panabo City |  |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | 2 | Impv't. of Brgy. Road Covered Court, |  | Court |  | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Alloted - May 29, 2019, Additional Funding of 500,000.00,SB no. 4 cy 2019 for Allotment Nov 25, 2019 |  | 2
|  |  | Malativas, Panabo City |  |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | 3 | Rehab. Of Multi-Purpose Gym & Facililies |  | Gym |  | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Request for Allotment on process |  | 2
|  |  | Maduao, Panabo City |  |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | 4 | Const. of Multi-Purpose Bldg. |  | Bldg. |  | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Plan and POW on process c/o PDPM |  | 2
|  |  | Sto. Nino, Panabo City |  |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | 5 | Completion of Canopy at DAPCO Covered |  | Court |  | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For Plan preparation by PDPM August 5, 2019 |  | 2
|  |  | Court, Dapco, Panabo City |  |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | 6 | Perimeter Fence of Day Care Center I & II, |  | Bldg. |  | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For inspection by PDPM for PLAN and POW as of 7/19/2019 |  | 2
|  |  | Nanyo, Panabo City |  |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | STO. TOMAS | [19 empty] | For amendment in the AIP 3rd revision |  | AC
|  | 1 | Const. of Multi-Purpose Bldg./Compl. Of |  | Bldg. |  | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - |  |  | 2
|  |  | Covered Court Canopy, Balagunan, |  |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
|  |  | Sto. Tomas |  |  |  |  | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | 2 | Const. of Perimeter Fence of Kinamayan |  | Fence |  | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Inspected by PDPM for POW and POW July 31, 2019 |  | 2
|  |  | Integ,. School, Kinamayan, Sto. Tomas |  |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | B.E. DUJALI | [21 empty] | AC
|  | 1 | Concreting of Brgy. Road Canal, |  | Road |  | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For inspection by PDPM for PLAN and POW as of 7/19/2019 |  | 2
|  |  | Dujali, B.E. Dujali |  |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | 2 | Concreting of Drainage, Tanglaw, |  | Drainage |  | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For inspection by PDPM for PLAN and POW as of 7/19/2019 |  | 2
|  |  | B.E. Dujali |  |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | 3 | Const. of Bleacher w/ Canopy (Ph.II) and |  | Bleacher |  | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Check for pick-up as of July 5, 2019 with check no. 0135071 |  | 2
|  |  | Upgrading of Flooring, Cabay-angan, B.E. Dujali |  |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | 4 | Desilting and Concreting of Drainage-main |  | Bleacher |  | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For inspection by PDPM for PLAN and POW as of 7/19/2019 |  | 2
|  |  | Collector Canal, New Casay, B.E. Dujali |  |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | 5 | Const. of Brgy. Multi-Purpose Covered Court, |  | Bleacher |  | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For inspection by PDPM for PLAN and POW as of 7/19/2019 |  | 2
|  |  | Magupising, B.E. Dujali |  |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | IGCS | [21 empty] | AC
|  | 1 | Impv't. of Brgy. Water System, Pichon, IGCS |  | Water |  | Admin | a) | 500000 | a) | 05/31/18 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For Implementation |  | 2
[5 empty] | System |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | 2 | Powerline Expansion Project, Cogon, IGACOS |  | Water |  | Contract | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For Implementation. |  | 2
[5 empty] | System |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | 3 | Water System From Prk. 6 - Prk. 2 - Prk. 5A, |  | Water |  | Admin | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For Implementation |  | 2
|  |  | Tagbay, IGCS |  | System |  |  | b) | Pacquiao | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | 4 | Rehab of Multipurpose Hall, Tagdaliao |  | Bldg. |  | Admin | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | proposed realignement due to project ovelap |  | 2
|  |  | IGACOS |  |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | 5 | Electrification Project, Kanaan, IGACOS |  | Elect. |  | Admin | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For DANECO staking |  | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | 7 | Powerline Expansion Project, Tambo, IGCS |  | Elect. |  | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Procurement of Materials on process |  | 2
[8 empty] | b) | Porras | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | Admin | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | 9 | Construction of Multipurpose Pavement |  | Bldg. |  | Admin | a) | 500000 | a) |  | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Amended from Improvement of Brgy Hall due to change Brgy. Priority. Resolution No. 70 series of 2019 dated July 18, 2019. For allotment |  | 2
|  |  | Penaplata, IGCS |  |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | 10 | Completion of Kasilak Day Care Center, |  | Bldg. |  | Admin | a) | 500000 | a) | 07/05/18 | e) | - | a) | 500000 | a) | 93.04% | c) | 86.15% | a) | - | On-going |  | 2
|  |  | Sta. Cruz, IGCS |  |  |  |  | b) | Porras | b) | 5/20/2019 | f) | - | b) | 500000 | b) | - | d) | -6.89% | b) | - |  |  | 2
[8 empty] | c) | - | c) | 7/17/2019 | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | 11/30/2019 | [12 empty] | 2
|  | 11 | Const. of Concrete fence of New Brgy. Site, |  | Fence |  | - | a) | 500000 | a) |  | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For Implementation |  | 2
|  |  | San Isidro, IGCS |  |  |  |  | b) | Porras | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | [13 empty] | 2
|  | 12 | Electrification of Sitio Baongon-Diamond- |  | Elect. |  | - | a) | 500000 | a) |  | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Procurement on process |  | 2
|  |  | Mansanitas, Dadatan, IGCS |  |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | 13 | Drilling of Water System, |  | Water |  | - | a) | 500000 | a) |  | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For amendment. This project scope of work was included on a separate project titled Construction of Potable Water System at Linusotan, IGACOS. |  | 2
|  |  | Linusotan, IGCS |  | System |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
| L. | 5% Calamity Fund CY 2018 | [21 empty] | FS
|  | 1. Prevention and Mitigation | [21 empty] | AC
|  | 1.1 Desiltation/Excavation of rivers and creeks |  |  | rivers |  | Admin | a) | 3000000 | [12 empty] | Investigation/Inspection of priority projects |  | AC
[8 empty] | b) | - | [14 empty] | AC
[8 empty] | c) | PEO | [14 empty] | AC
[8 empty] | d) | - | [14 empty] | AC
| 11 | 1.1.1. | Improvement and Desiltation of Tagum Creek (Phase I and Phase II) |  | Creek |  | Admin | a) | 2,000,000.00 | a) | 11/06/18 | e) | - | a) | 2,000,000.00 | a) | 100% | c) | 100% | a) | 5 | Completed |  | 1 | 1
[8 empty] | b) | Mayang | b) | 03/22/19 | f) | - | b) | 2,000,000.00 | b) | - | d) | 0% | b) | 110 |  |  | 1
[8 empty] | c) | PEO | c) | 10/31/19 | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | 224 CD | d) | - | [12 empty] | 1
|  | 1.2 Improvement of Roads, Drainage & Canals |  |  | roads/canals |  | Admin | a) | 3000000 | [12 empty] | Investigation/Inspection of priority projects. |  | AC
[8 empty] | b) | - | [12 empty] | Declared as savings |  | AC
[8 empty] | c) | PEO | [14 empty] | AC
[8 empty] | d) | - | [14 empty] | AC
| 1 | 1.2.1 | Rehab./Impv't. of Sonlon-Longanapan Road |  | road |  | Admin | a) | 1,500,000.00 | a) | - | e) | - | a) | 1,500,000.00 | a) | 47.32% | c) | 20.57% | a) | - | On going |  | 1
[8 empty] | b) | - | b) | - | f) | - | b) | 1,500,000.00 | b) | - | d) | -26.75% | b) | - |  |  | 1
[8 empty] | c) | PEO | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
|  | 1.3 Improvement of bridges and cross drainage |  |  | bridges/drainage |  | Admin | a) | 3000000 | [12 empty] | Declared as savings |  | AC
[8 empty] | b) | - | [14 empty] | AC
[8 empty] | c) | PEO | [14 empty] | AC
[8 empty] | d) | - | [14 empty] | AC
|  | a. | Impv't. of Mabaus Cross Drainage |  | Drainage |  | Admin | a) | 3,000,000.00 | a) | - | e) | - | a) | 3,000,000.00 | a) | - | c) | - | a) | - | Preparation of POW & Plan c/o PDPM |  | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 3,000,000.00 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | 1.4 Revitment of Dike and Slope Protection |  |  | Dike |  | Admin | a) | 3000000 | [12 empty] | See project listed below |  | AC
[8 empty] | b) | - | [14 empty] | AC
[8 empty] | c) | Admin | [14 empty] | AC
[8 empty] | d) | - | [14 empty] | AC
|  | a. | Rehab. Of Dujali-Pawas-San Vicente RDCG-Abutment A&B (Embankment) - Riprapping A&B @ Both Side |  | Dike |  | Admin | a) | 3,000,000.00 | a) | 11/06/18 | e) | - | a) | 3,000,000.00 | a) | 100.00% | c) | 98.47% | a) | 10 | Suspended 9/23/2019 |  | 2
[8 empty] | b) | Sanchez | b) | 02/18/19 | f) | 145 | b) | 3,000,000.00 | b) | 88.56% | d) | -1.53% | b) | 70 |  |  | 2
[8 empty] | c) | PEO | c) | 05/08/19 | g) | - | c) | 2263892.44 | [8 empty] | 2
[8 empty] | d) | - | d) | 9/30/2019 | [12 empty] | 2
|  | 2. Rehabilitation and Recovery |  |  | roads |  | Admin | a) | 2026000 | [12 empty] | Declared as savings |  | AC
[8 empty] | b) | - | [14 empty] | AC
[8 empty] | c) | PEO | [14 empty] | AC
[8 empty] | d) | - | [14 empty] | AC
| M. | SUPPLEMENTAL BUDGET # 1 CY 2018 | [5 empty] | a) | 6,000,000.00 | [12 empty] | See list of Provincial Roads |  | FS
|  | 1 Const. in Progress - Infrastructure | [5 empty] | b) | Paraguya | [14 empty] | AC
|  | Assets (Rehabilitation of Various | [5 empty] | c) | PEO | [14 empty] | AC
|  | Provincial Roads) | [5 empty] | d) | - | [14 empty] | AC
| 5 | 1 | Mesaoy - Jct. Mahayahay |  | Road |  | Admin | a) | 1,534,000.00 | a) | 07/19/18 | e) | - | a) | 1,534,000.00 | a) | 60% | c) | 60% | a) | - | Suspended as of Dec. 27, 2018 |  | 1
[8 empty] | b) | Salido | b) | 11/16/18 | f) | - | b) | 1,534,000.00 | b) | - | d) | - | b) | - | Cancellation of PO # 2018082439 and RE-PR |  | 1
[8 empty] | c) | PEO | c) | 12/15/18 | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| 5 | 2 | Del Pilar - Jct. Silangan |  | Road |  | Admin | a) | 1,795,000.00 | a) | 07/19/18 | e) | - | a) | 1,795,000.00 | a) | 73.00% | c) | 73.00% | a) | 14 | On-going |  | 1
[8 empty] | b) | Salido | b) | 10/16/18 | f) | - | b) | 1,795,000.00 | b) | - | d) | - | b) | 30 | Suspended as of January 4, 2019 |  | 1
[8 empty] | c) | PEO | c) | 11/20/18 | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| N. | SUPPLEMENTAL BUDGET # 2 CY 2018 | [21 empty] | FS
|  | 1 Const./Compl./Impv't. of Various Gov't. | [21 empty] | AC
|  | Bldgs., Structures & Facilities (Const. in | [21 empty] | AC
|  | Progress - Bldgs. & Other Structures | [21 empty] | AC
| 4 |  | Const./Impv't. of DDN Hospital |  | Bldg. |  | - | a) | 5,000,000.00 | a) | - | e) | - | a) | 5,000,000.00 | a) | - | c) | 40% | a) | - | On-going |  | 1
|  |  | Kapalong Zone |  |  |  |  | b) | - | b) | - | f) | - | b) | 5,000,000.00 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
|  |  | Const. of DDN Hospital Carmen Zone |  | Bldg. |  | Admin | a) | 5,500,000.00 | a) | - | e) | - | a) | 5,500,000.00 | a) | - | c) | - | a) | - | PR ON PROCESS 6/11/2019 |  | 2
|  |  | Annex Bldg. |  |  |  |  | b) | Estorco | b) | - | f) | - | b) | 5,500,000.00 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | PEO | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
| 5 |  | Compl. Of Bahay Pag-Asa for Minors, |  | Bldg. |  | - | a) | 3,000,000.00 | a) | - | e) | - | a) | 3,000,000.00 | a) | - | c) | - | a) | - | Waiting for Delivery of Materials |  | 1
|  |  | New Corella |  |  |  |  | b) | - | b) | - | f) | - | b) | 3,000,000.00 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| 11 |  | Upgrading of DAGOEMC Muti-Purpose Bldg. |  | Bldg. |  | - | a) | 3,000,000.00 | a) | 09/04/2018 | e) | - | a) | 3,000,000.00 | a) | 30.28% | c) | 56.97% | a) | 7 | On-going |  | 1
|  |  | Mankilam |  |  |  |  | b) | Chua | b) | 03/04/2019 | f) | - | b) | 3,000,000.00 | b) | - | d) | - | b) | 210 |  |  | 1
[8 empty] | c) | PEO | c) | 07/26/2019 | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | 145 CD | d) | - | [12 empty] | 1
| 11 |  | Const. of Add'l. 2nd Level Multi-Purpose |  | Bldg. |  | - | a) | 7,592,588.00 | a) | - | e) | - | a) | 7,592,588.00 | a) | - | c) | - | a) | - | Preparation of POW & Plan c/o PDPM. |  | 1
|  |  | HalI, PGSO warehouse,Bldg., Mankilam |  |  |  |  | b) | - | b) | - | f) | - | b) | 7,592,588.00 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| O. | SUPPLEMENTAL BUDGET # 4 CY 2018 | [21 empty] | FS
| 11 | 1 | Construction of Multi-Purpose Bldg. (PENRO Building) |  | Bldg. | 303.75 sq.m | Admin | a) | 1800000 | a) | 06/11/18 | e) | - | a) | 1800000 | a) | 100% | c) | 100% | a) | 25 | Completed as per Physical accomplishment. Financial Documents on process |  | 1
[8 empty] | b) | Pasiona/Juan | b) | 10/16/18 | f) | 111 | b) | 1800000 | b) | - | d) | 0% | b) | 750 |  |  | 1
|  |  | (Part of P8,548,000.00)(P1,800,000.00 - |  |  |  |  | c) | PEO | c) | 09/10/19 | g) | 09/13/19 | c) | 6129861.34 | [8 empty] | 1
|  |  | SB # 4 CY 2018) |  |  |  |  | d) | 222 CD | d) | 06/30/19 | [12 empty] | 1
| P. | SUPPLEMENTAL BUDGET # 5 CY 2018 | [21 empty] | FS
|  | STIMULUS CY 2018 | [21 empty] | AC
| 1 | 1 | Const. of MP Hall, Rizal ES, Binancian, |  | Bldg. |  | - | a) | 1250000 | a) | 02/04/19 | e) | - | a) | 1250000 | a) | - | c) | 80% | a) | - | On-going |  | 1
|  |  | Asuncion |  |  |  |  | b) | - | b) | 06/18/2019 | f) | - | b) | 1250000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| 1 | 2 | Const. of MP Hall, Liguyon ES, Binancian, |  | Bldg. |  | - | a) | 1250000 | a) | 02/04/19 | e) | - | a) | 1250000 | a) | - | c) | 80% | a) | - | On-going |  | 1
|  |  | Asuncion |  |  |  |  | b) | - | b) | 06/16/2019 | f) | - | b) | 1250000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| 1 | 3 | Rehab./Impv't. of MP Bldg. (Gym), Napungas, |  | GYM |  | - | a) | 500000 | a) | 02/04/19 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Plan and POW on process |  | 1
|  |  | Asuncion |  |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| Q. | OPPAP-PAMANA | [21 empty] | FS
|  | 1. TRIBAL HALL | [21 empty] | AC
| 4 | 1.1 | Construction of Tribal Hall |  | Bldg. |  | Admin | a) | 500000 | a) | CY 2018 | e) | - | a) | 500000 | a) | 100% | c) | 100% | a) | 5 | Completed as per Physical Accomplishment. Financial Documents on process |  | 1
|  |  | Brgy. Gupitan, Kapalong |  |  |  |  | b) | Ambrocio | b) | 2/22/2019 | f) | - | b) | 500000 | b) | - | d) | 0% | b) | 150 |  |  | 1
[8 empty] | c) | PEO | c) | 5/22/2019 | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
|  | 2. PROCESSING AND BAGSAKAN CENTER | [21 empty] | AC
| 8 | 2.1 | Const. of Processing and Bagsakan Center, |  | Bldg. |  | Contract | a) | 2500000 | a) | - | e) | - | a) | 2500000 | a) | - | c) | 4% | a) | - | On going. |  | 1
|  |  | Brgy. Dagohoy, Talaingod |  |  |  |  | b) | - | b) | - | f) | - | b) | 2500000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| 4 | 2.2 | Const. of Processing and Bagsakan Center, |  | Bldg. | 300 sq.m | Contract | a) | 2500000 | a) | 08/29/18 | e) | - | a) | 2500000 | a) | 100% | c) | 100% | a) | 6 | Completed as per Physical Accomplishment. Financial Documents on process |  | 1
|  |  | Brgy. Gupitan, Kapalong, Davao del Norte |  |  |  |  | b) | Ambrucio | b) | 02/12/19 | f) | - | b) | 2500000 | b) | - | d) | 0% | b) | 180 |  |  | 1
[8 empty] | c) | Alpha & Omega | c) | 05/12/19 | g) | - | c) | 156000 | [8 empty] | 1
[8 empty] | d) | 120 CD | d) | - | [12 empty] | 1
|  | 3. SOLAR DRYER | [21 empty] | AC
| 4 | 3.1 | Post Harvest Facilities (Corn Mill, Solar Dryer, |  | Bldg. |  | Contract | a) | 1500000 | a) | - | e) | - | a) | 1500000 | a) | 10% | c) | 15% | a) | - | on-going. |  | 1
|  |  | Corn Sheller), Kapalong, Davao del Norte |  |  |  |  | b) | - | b) | - | f) | - | b) | 1500000 | b) | - | d) | 5% | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | 391970.93 | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| 8 | 3.2 | Post Harvest Facilities (Corn Mill, Solar Dryer, Corn Sheller), Sitio Butay, Palma Gil, Talaingod, Davao del Norte |  | Bldg. |  | Admin | a) |  | a) | - | e) | - | a) | 1850000 | a) |  | c) | 79.14% | a) | 11 | on-going |  | 1
[8 empty] | b) | Dadula | b) | July 16, 2019 | f) | - | b) | 1850000 | b) | - | d) |  | b) | 246 |  |  | 1
[8 empty] | c) | - | c) | Nov. 13, 2019 | g) | - | c) | [9 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
|  | 4. TRADING POST STORAGE | [21 empty] | AC
| 11 |  | Trading Post, Storage and Hauling Truck, Pandapan, Tagum City |  | Bldg. |  | Contract | a) | 4000000 | a) | - | e) | - | a) | 4000000 | a) | - | c) | - | a) | - | Re-bidding |  | 1
[8 empty] | b) | - | b) | - | f) | - | b) | 4000000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
|  |  | Trading Post, Storage and Hauling Truck, Purok Ramihan, Datu Abdul, Panabo City |  | Bldg. |  | - | a) | 4000000 | a) | CY 2018 | e) | - | a) | 4000000 | a) | 3.74% | c) | 1.91% | a) | - | On-going |  | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 4000000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  |  | Trading Post, Storage and Hauling Truck Libuak, Island Garden City of Samal (IGACOS) |  | Bldg. |  | - | a) | 4000000 | a) | CY 2018 | e) | - | a) | 4000000 | a) | - | c) | - | a) | - | For verification of beneficiary |  | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 4000000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | 5. WATER SYSTEM | [21 empty] | AC
| 4 |  | Upgrading of Existing PWS Level II in Sitio Langan, Gupitan, Kapalong |  | PWS |  | Admin | a) | 2500000 | a) |  | e) |  | a) | 2500000 | a) | 31.24% | c) | 32.67% | a) |  | On-going |  | 1
[8 empty] | b) |  | b) | 11/16/2019 | f) |  | b) | 2500000 | b) | - | d) | 1.43% | b) |  |  |  | 1
[8 empty] | c) |  | c) | 02/27/2020 | g) | - | c) | [9 empty] | 1
[8 empty] | d) |  | d) | - | [12 empty] | 1
| 4 |  | Upgrading of Existing PWS Level II in Sitio Patel 2, Gupitan, Kapalong |  | PWS |  | Admin | a) | 2500000 | a) | 8/14/2019 | e) | - | a) | 2500000 | a) |  | c) | 100% | a) | - | Completed as per Physical Accomplishment. Financial Documents on process |  | 1
[8 empty] | b) | Diosanta | b) | 3/25/2019 | f) | - | b) | 2500000 | b) |  | d) |  | b) | - |  |  | 1
[8 empty] | c) | PEO | c) | 7/19/2019 | g) | 09/30/2019 | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| 4 |  | Construction of PWS Level II in Purok 7-A and 7-B, Capungagan, Kapalong |  | PWS |  | Admin | a) | 1000000 | a) | 11/25/2019 | e) | - | a) | 1000000 | a) | - | c) | 5% | a) | - | On-going |  | 1
[8 empty] | b) | Kabinge | b) | - | f) | - | b) | 1000000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | PEO | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| 4 |  | Construction of PWS Level II in Purok 2, Pag-asa, Kapalong |  | PWS |  | Admin | a) | 1000000 | a) | 11/12/18 | e) | - | a) | 1000000 | a) | - | c) | - | a) | - | Declared savings in the AIP 2nd Revision to fund for the Construction of PWS in Brgy. Linusotan, Kaputian District, IGACOS (Project was funded by OPAPP CY 2018) |  | 1
[8 empty] | b) | - | b) | - | f) | - | b) | 1000000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| 8 |  | Construction of PWS Level II in Sitio Upper Dulyan, Palma Gil, Talaingod, DDN |  | PWS |  | Admin | a) | 1000000 | a) | - | e) | - | a) | 1000000 | a) | - | c) | 5% | a) | - | On going |  | 1
[8 empty] | b) | Kabinge | b) | - | f) |  | b) | 1000000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | PEO | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
|  | 6. CATTLE PRODUCTION | [21 empty] | AC
| 4 |  | Cattle Production- Brgy. Tiburcia, Gupitan and Semong, Kapalong |  | Bldg. |  | Admin | a) | 1500000 | a) | - | e) | - | a) | 1500000 | a) | - | c) | - | a) | - | For cancellation. A letter was sent to OPAPP last Dec 2018 requesting to allow us to reduce the number of cattle but we are still hoping that there would be a supplier will bid |  | 1
[8 empty] | b) | - | b) | - | f) | - | b) | 1500000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| 8 |  | Cattle Production, Brgy. Palma Gil, Brgy. Sto. Nino, Brgy. Dagohoy, Talaingod, Davao del Norte |  | Bldg. |  | Admin | a) | 1500000 | a) | - | e) | - | a) | 1500000 | a) | - | c) | - | a) | - | For cancellation. A letter was sent to OPAPP last Dec 2018 requesting to allow us to reduce the number of cattle but we are still hoping that there would be a supplier will bid |  | 1
[8 empty] | b) | - | b) | - | f) | - | b) | 1500000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
|  | 7. RICE MILL FOR UPLAND RICE | [21 empty] | AC
| 8 |  | Rice Mill for Upland Rice, Palma Gil, Talaingod |  | Bldg. |  | Admin | a) | 1000000 | a) | - | e) | - | a) | 1000000 | a) | 31.93% | c) | 31.93% | a) | - | No Approved P.O. |  | 1
[8 empty] | b) | - | b) | - | f) | - | b) | 1000000 | b) | - | d) | 0% | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| 4 |  | Rice Mill for Upland Rice,Gupitan, Kapalong |  | Bldg. |  | Admin | a) | 1000000 | a) | - | e) | - | a) | 1000000 | a) | 100% | c) | 100% | a) | - | Completed |  | 1
[8 empty] | b) | Ambrucio | b) | 6/17/2019 | f) | - | b) | 1000000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
|  | 8. AGRICULTURAL PRODUCTIVITY SUPPORT PROJECT | [21 empty] | AC
|  |  | Agricultural Productivity Support Project- |  | - |  | - | a) | 1500000 | a) | - | e) | - | a) | 1500000 | a) | - | c) | - | a) | - | For verification of beneficiary |  | 2
|  |  | Fishing Equipment, Tambo, IGACOS |  |  |  |  | b) | - | b) | - | f) | - | b) | 1500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
| R. | LOCAL GOVERNMENT SUPPORT FUND (LGSF) CY 2018 | [21 empty] | FS
| 1 | 1 | Road Upgrading of San Vicente - Butay Provincial Road |  | Road |  | Contract | a) | 19949581.18 | a) | CY 2018 | e) | - | a) | 19949581.18 | a) | 100% | c) | 100% | a) | 18 | Completed as per Physical Accomplishment. Financial Documents on process |  | 1
[8 empty] | b) | Aclaracion | b) | 11/19/18 | f) | 28 CD | b) | 19949581.18 | b) | 100% | d) | 0% | b) | 396 |  |  | 1
[8 empty] | c) | Alpha & Omega | c) | 06/08/19 | g) | 06/26/2019 | c) | 9,685,667.31 | [8 empty] | 1
[8 empty] | d) | 202 CD | d) | 07/06/19 | [12 empty] | 1
| S. | QUICK RESPOND FUND CY 2016 | [21 empty] | FS
| 4 | 1 | Rehab. Of Slope Protection of Libuganon River Along Kapalong - Mabantao - Florida Prov'l. Road Phase I |  | Road |  | - | a) | 900000 | a) | - | e) | - | a) | 900000 | a) | - | c) | - | a) | - | For AIP Amendment |  | 1
[8 empty] | b) | - | b) | - | f) | - | b) | 900000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
II. PROJECTS UNDER THE CURRENT APPROPRIATION CY 2019
A.1 GENERAL FUND CY 2019 | [6 empty] | MBA/CBRMC | a) | 18127866 | a) | 01/03/19 | e) | - | a) | 18127866 | a) | 83.63 | c) | 83.83 | a) | 46 | See list of Provincial Roads |  | AP
Road ID |  | Maintenance of Various Provincial Roads and Bridges at District 1 |  |  | Road Maintenance | KM |  | b) | Paraguya | b) | 01/03/19 | f) | - | b) | 18127866 | b) | - | d) | - | b) | 920 |  |  | FS
[6 empty] | 288.26 |  | c) | PEO/CBRMC | c) | 12/31/19 | g) | - | c) | - | [8 empty] | AC
11DAN | [9 empty] | d) | - | [12 empty] | AC
[8 empty] | d) | 261 days | d) | - | [12 empty] | AC
|  | Jct. Highway Magatos - New Bantayan |  |  | Road Maintenance | 7.1 | MBA | a) | 287307.39 | a) | 01/03/19 | e) | - | a) | 287307.39 | a) | 100% | c) | 100% | a) | 15 | Completed |  | AC | 4
001 | [7 empty] | b) | Crucio | b) | 01/16/19 | f) | - | b) | 287307.39 | b) | - | d) | - | b) | 480 |  |  | 1 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 118693.58 | [8 empty] | 1 | 4
[8 empty] | d) | - | d) | - | [12 empty] | 1 | 4
|  | Jct. Highway Magatos - New Bantayan |  |  | Road Maintenance | 7.1 | CBRMC | a) | 223674.22 | a) | 01/03/19 | e) | - | a) | 223674.22 | a) | 100% | c) | 100% | a) | 16 | Completed |  | 1 | 4
001 | [7 empty] | b) | Crucio | b) | 3/22/19 | f) | - | b) | 223674.22 | b) | - | d) | - | b) | 480 |  |  | 1 | 4
[8 empty] | c) | CALAFA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [8 empty] | 1 | 4
[8 empty] | d) | 3 quarters | d) | - | [12 empty] | 1 | 4
|  | Magatos-Bdry Pagsabangan |  |  | Road Maintenance | 8.33 | MBA | a) | 328740.25 | a) | 01/03/19 | e) | - | a) | 328740.25 | a) | 100% | c) | 100% | a) | 15 | Completed |  | 1 | 4
002 | [7 empty] | b) | Crucio | b) | 01/03/19 | f) | - | b) | 328740.25 | b) | - | d) | - | b) | 450 |  |  | 1 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 207258.49 | [8 empty] | 1 | 4
[8 empty] | d) | - | d) | - | [12 empty] | 1 | 4
|  | Magatos-Bdry Pagsabangan |  |  | Road Maintenance | 8.33 | CBRMC | a) | 270763.53 | a) | 01/03/19 | e) | - | a) | 270763.53 | a) | 100% | c) | 100% | a) | 16 | Completed |  | 1 | 4
002 | [7 empty] | b) | Crucio | b) | 03/22/19 | f) | - | b) | 270763.53 | b) | - | d) | - | b) | 450 |  |  | 1 | 4
[8 empty] | c) | CALAFA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [8 empty] | 1 | 4
[8 empty] | d) | 3 quarters | d) | - | [12 empty] | 1 | 4
|  | Ilog-New Bantayan |  |  | Road Maintenance | 2.68 | MBA | a) | 131131.39 | a) | 01/03/19 | e) | - | a) | 131131.39 | a) | 100% | c) | 100% | a) | 15 | Completed |  | 1 | 4
003 | [7 empty] | b) | Crucio | b) | 01/16/19 | f) | - | b) | 131131.39 | b) | - | d) | - | b) | 450 |  |  | 1 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 49,316.69 | [8 empty] | 1 | 4
[8 empty] | d) | - | d) | - | [12 empty] | 1 | 4
|  | Ilog-New Bantayan |  |  | Road Maintenance | 2.68 | CBRMC | a) | 65925.03 | a) | 01/03/19 | e) | - | a) | 65925.03 | a) | 100% | c) | 100% | a) | 16 | Completed |  | 1 | 4
003 | [7 empty] | b) | Crucio | b) | 03/22/19 | f) | - | b) | 65925.03 | b) | - | d) | - | b) | 450 |  |  | 1 | 4
[8 empty] | c) | CALAFA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [8 empty] | 1 | 4
[8 empty] | d) | 3 quarters | d) | - | [12 empty] | 1 | 4
|  | Asuncion -Monte Carlo-Del Pilar |  |  | Road Maintenance | 9.93 | MBA | a) | 474102.88 | a) | 01/03/19 | e) | - | a) | 474102.88 | a) | 100% | c) | 100% | a) | 15 | Completed |  | 1 | 4
005 | [7 empty] | b) | Crucio | b) | 01/03/19 | f) | - | b) | 474102.88 | b) | - | d) | - | b) | 450 |  |  | 1 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 240274.49 | [8 empty] | 1 | 4
[8 empty] | d) | - | d) | - | [12 empty] | 1 | 4
|  | Asuncion -Monte Carlo-Del Pilar |  |  | Road Maintenance | 9.93 | CBRMC | a) | 355524.28 | a) | 01/03/19 | e) | - | a) | 355524.28 | a) | 100% | c) | 100% | a) | 16 | Completed |  |  | 4
005 | [7 empty] | b) | Crucio | b) | 03/22/19 | f) | - | b) | 355524.28 | b) | - | d) | - | b) | 450 |  |  | 1 | 4
[8 empty] | c) | MAHAYAHAY IFA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [8 empty] | 1 | 4
[8 empty] | d) | 3 quarters | d) | - | [12 empty] | 1 | 4
|  | Jct. Highway Canatan-Jct. Highway Magatos |  |  | Road Maintenance | 4.85 | MBA | a) | 209808.59 | a) | 01/03/19 | e) | - | a) | 209808.59 | a) | 100% | c) | 100% | a) | 15 | Completed |  | 1 | 4
006 | [7 empty] | b) | Crucio | b) | 02/18/19 | f) | - | b) | 209808.59 | b) | - | d) | - | b) | 450 |  |  | 1 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 80652.8 | [8 empty] | 1 | 4
[8 empty] | d) | - | d) | - | [12 empty] | 1 | 4
|  | Jct. Highway Canatan-Jct. Highway Magatos |  |  | Road Maintenance | 4.85 | CBRMC | a) | 162458.12 | a) | 01/03/19 | e) | - | a) | 162458.12 | a) | 100% | c) | 100% | a) | 16 | Completed |  | 1 | 4
006 | [7 empty] | b) | Crucio | b) | 03/22/19 | f) | - | b) | 162458.12 | b) | - | d) | - | b) | 450 |  |  | 1 | 4
[8 empty] | c) | CAMODA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [8 empty] | 1 | 4
[8 empty] | d) | 3 quarters | d) | - | [12 empty] | 1 | 4
[24 empty] | 1 | 4
|  | Sta. Felomina-San Roque |  |  | Road Maintenance | 7.68 | MBA | a) | 147439.63 | a) | 01/03/19 | e) | - | a) | 147439.63 | a) | 100% | c) | 100% | a) | 15 | Completed |  |  | 4
008 | [7 empty] | b) | Crucio | b) | 01/16/19 | f) | - | b) | 147439.63 | b) | - | d) | - | b) | 450 |  |  | 1 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 63806.67 | [8 empty] | 1 | 4
[8 empty] | d) | - | d) | - | [12 empty] | 1 | 4
|  | Sta. Felomina-San Roque |  |  | Road Maintenance | 7.68 | CBRMC | a) | 261345.67 | a) | 01/03/19 | e) | - | a) | 261345.67 | a) | 100% | c) | 100% | a) | 16 | Completed |  | 1 | 4
008 | [7 empty] | b) | Crucio | b) | 03/25/19 | f) | - | b) | 261345.67 | b) | - | d) | - | b) | 450 |  |  | 1 | 4
[8 empty] | c) | STAFFA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [8 empty] | 1 | 4
[8 empty] | d) | 3 quarters | d) | - | [12 empty] | 1 | 4
|  | Saug-Sonlon-Bdy Longanapan |  |  | Road Maintenance | 11.6 | MBA | a) | 568486.36 | a) | 01/03/19 | e) | - | a) | 568486.36 | a) | 100% | c) | 100% | a) | 15 | Completed |  | 1 | 4
010 | [7 empty] | b) | Crucio | b) | 01/16/19 | f) | - | b) | 568486.36 | b) | - | d) | - | b) | 450 |  |  | 1 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 262900.22 | [8 empty] | 1 | 4
[8 empty] | d) | - | d) | - | [12 empty] | 1 | 4
|  | Saug-Sonlon-Bdy Longanapan |  |  | Road Maintenance | 11.6 | CBRMC | a) | 185565.56 | a) | 01/03/19 | e) | - | a) | 185565.56 | a) | 100% | c) | 100% | a) | 16 | Completed |  | 1 | 4
010 | [7 empty] | b) | Crucio | b) | 03/26/19 | f) | - | b) | 185565.56 | b) | - | d) | - | b) | 450 |  |  | 1 | 4
[8 empty] | c) | BINANCIAN LIVESTOCK AFA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [8 empty] | 1 | 4
[8 empty] | d) | 3 quarters | d) | - | [12 empty] | 1 | 4
|  | Jct. New Visayas-Buan |  |  | Road Maintenance | 2.99 | MBA | a) | 79238.27 | a) | 01/03/19 | e) | - | a) | 79238.27 | a) | 100% | c) | 100% | a) | 15 | Completed |  | 1 | 4
011 | [7 empty] | b) | Crucio | b) | 02/18/19 | f) | - | b) | 79238.27 | b) | - | d) | - | b) | 450 |  |  | 1 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 14682.85 | [8 empty] | 1 | 4
[8 empty] | d) | - | d) | - | [12 empty] | 1 | 4
|  | Jct. New Visayas-Buan |  |  | Road Maintenance | 2.99 | CBRMC | a) | 101242.01 | a) | 01/03/19 | e) | - | a) | 101242.01 | a) | 100% | c) | 100% | a) | 16 | Completed |  | 1 | 4
011 | [7 empty] | b) | Crucio | b) | 03/22/19 | f) | - | b) | 101242.01 | b) | - | d) | - | b) | 450 |  |  | 1 | 4
[8 empty] | c) | BUAN IFA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [8 empty] | 1 | 4
[8 empty] | d) | 3 quarters | d) | - | [12 empty] | 1 | 4
|  | San Vicente - Butay |  |  | Road Maintenance | 7.52 | MBA | a) | 209624.2 | a) | 01/03/19 | e) | - | a) | 209624.2 | a) | 100% | c) | 100% | a) | 15 | Completed |  | 1 | 4
013 | [7 empty] | b) | Crucio | b) | 02/18/19 | f) | - | b) | 209624.2 | b) | - | d) | - | b) | 450 |  |  | 1 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 56,080.29 | [8 empty] | 1 | 4
[8 empty] | d) | - | d) | - | [12 empty] | 1 | 4
|  | San Vicente - Butay |  |  | Road Maintenance | 7.52 | CBRMC | a) | 227205.88 | a) | 01/03/19 | e) | - | a) | 227205.88 | a) | 100% | c) | 100% | a) | 16 | Completed |  | 1 | 4
013 | [7 empty] | b) | Crucio | b) | 03/27/19 | f) | - | b) | 227205.88 | b) | - | d) | - | b) | 450 |  |  | 1 | 4
[8 empty] | c) | SVMODA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [8 empty] | 1 | 4
[8 empty] | d) | 3 quarters | d) | - | [12 empty] | 1 | 4
|  | Jct. Highway Doña Andrea - Capungagan |  |  | Road Maintenance | 8.7 | MBA | a) | 230835.16 | a) | 01/03/19 | e) | - | a) | 230835.16 | a) | 100% | c) | 100% | a) | 15 | Completed |  | 1 | 4
014 | [7 empty] | b) | Crucio | b) | 02/18/19 | f) | - | b) | 230835.16 | b) | - | d) | - | b) | 450 |  |  | 1 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 60,629.26 | [8 empty] | 1 | 4
[8 empty] | d) | - | d) | - | [12 empty] | 1 | 4
[24 empty] | 1 | 4
|  | Jct. Highway Doña Andrea - Capungagan |  |  | Road Maintenance | 8.7 | CBRMC | a) | 294308.14 | a) | 01/03/19 | e) | - | a) | 294308.14 | a) | 100% | c) | 100% | a) | 16 | Completed |  |  | 4
014 | [7 empty] | b) | Crucio | b) | 03/28/19 | f) | - | b) | 294308.14 | b) | - | d) | - | b) | 450 |  |  | 1 | 4
[8 empty] | c) | CAPUNGAGAN MPC | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [8 empty] | 1 | 4
[8 empty] | d) | 3 quarters | d) | - | [12 empty] | 1 | 4
|  | Semong-Palma Gil |  |  | Road Maintenance | 2.73 | MBA | a) | 147289.98 | a) | 01/03/19 | e) | - | a) | 147289.98 | a) | 100% | c) | 100% | a) | 15 | Completed |  | 1 | 4
018 | [7 empty] | b) | Crucio | b) | 02/18/19 | f) | - | b) | 147289.98 | b) | - | d) | - | b) | 450 |  |  | 1 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 71745.43 | [8 empty] | 1 | 4
[8 empty] | d) | - | d) | - | [12 empty] | 1 | 4
[24 empty] | 1 | 4
4
4
|  | Semong-Palma Gil |  |  | Road Maintenance | 2.73 | CBRMC | a) | 49186.05 | a) | 01/03/19 | e) | - | a) | 49186.05 | a) | 100% | c) | 100% | a) | 16 | Completed |  |  | 4
018 | [7 empty] | b) | Crucio | b) | 03/22/19 | f) | - | b) | 49186.05 | b) | - | d) | - | b) | 450 |  |  | 1 | 4
[8 empty] | c) | PALMA GIL FA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [8 empty] | 1 | 4
[8 empty] | d) | 3 quarters | d) | - | [12 empty] | 1 | 4
|  | Daligdigon - Dagohoy |  |  | Road Maintenance | 3.34 | MBA | a) | 148835.45 | a) | 01/03/19 | e) | - | a) | 148835.45 | a) | 100% | c) | 100% | a) | - | Completed |  | 1 | 4
020 | [7 empty] | b) | Crucio | b) | - | f) | - | b) | 148835.45 | b) | - | d) | - | b) | - |  |  | 1 | 4
[8 empty] | c) | PEO | c) | - | g) | 2019-12-31 | c) | - | [8 empty] | 1 | 4
[8 empty] | d) | - | d) | - | [12 empty] | 1 | 4
|  | Daligdigon - Dagohoy |  |  | Road Maintenance | 3.34 | CBRMC | a) | 68279.5 | a) | 01/03/19 | e) | - | a) | 68279.5 | a) | 100% | c) | 100% | a) | 16 | Completed |  | 1 | 4
020 | [7 empty] | b) | Crucio | b) | 03/22/19 | f) | - | b) | 68279.5 | b) | - | d) | - | b) | 450 |  |  | 1 | 4
[8 empty] | c) | PALMA GIL FA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [8 empty] | 1 | 4
[8 empty] | d) | 3 quarters | d) | - | [12 empty] | 1 | 4
|  | Jct. Sampao-Bdry. Mamacao |  |  | Road Maintenance | 4.98 | MBA | a) | 154200.78 | a) | 01/03/19 | e) | - | a) | 154200.78 | a) | 100% | c) | 100% | a) | 15 | Completed |  | 1 | 4
025 | [7 empty] | b) | Crucio | b) | 02/18/19 | f) | - | b) | 154200.78 | b) | - | d) | - | b) | 450 |  |  | 1 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 24,296.87 | [8 empty] | 1 | 4
[8 empty] | d) | - | d) | - | [12 empty] | 1 | 4
|  | Jct. Sampao-Bdry. Mamacao |  |  | Road Maintenance | 4.98 | CBRMC | a) | 169521.51 | a) | 01/03/19 | e) | - | a) | 169521.51 | a) | 100% | c) | 100% | a) | 16 | Completed |  | 1 | 4
025 | [7 empty] | b) | Crucio | b) | 03/26/19 | f) | - | b) | 169521.51 | b) | - | d) | - | b) | 450 |  |  | 1 | 4
[8 empty] | c) | AMS KAPALONG | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [8 empty] | 1 | 4
[8 empty] | d) | 3 quarters | d) | - | [12 empty] | 1 | 4
|  | Jct. Highway Luna-Mamacao-Narra |  |  | Road Maintenance | 9.17 | MBA | a) | 357957.66 | a) | 01/03/19 | e) | - | a) | 357957.66 | a) | 100% | c) | 100% | a) | 15 | Completed |  | 1 | 4
026 | [7 empty] | b) | Crucio | b) | 02/18/19 | f) | - | b) | 357957.66 | b) | - | d) | - | b) | 450 |  |  | 1 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 127,996.16 | [8 empty] | 1 | 4
[8 empty] | d) | - | d) | - | [12 empty] | 1 | 4
|  | Jct. Highway Luna-Mamacao-Narra |  |  | Road Maintenance | 9.17 | CBRMC | a) | 313143.91 | a) | 01/03/19 | e) | - | a) | 313143.91 | a) | 100% | c) | 100% | a) | 16 | Completed |  | 1 | 4
026 | [7 empty] | b) | Crucio | b) | 03/26/19 | f) | - | b) | 313143.91 | b) | - | d) | - | b) | 450 |  |  | 1 | 4
[8 empty] | c) | AMS KAPALONG | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [8 empty] | 1 | 4
[8 empty] | d) | 3 quarters | d) | - | [12 empty] | 1 | 4
|  | Jct. Gabuyan-Katipunan-Bucana |  |  | Road Maintenance | 5.89 | MBA | a) | 294403.23 | a) | 01/03/19 | e) | - | a) | 294403.23 | a) | 100% | c) | 100% | a) | 15 | Completed |  | 1 | 4
027 | [7 empty] | b) | Crucio | b) | 02/18/19 | f) | - | b) | 294403.23 | b) | - | d) | - | b) | 450 |  |  | 1 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 126,179.97 | [8 empty] | 1 | 4
[8 empty] | d) | - | d) | - | [12 empty] | 1 | 4
|  | Jct. Gabuyan-Katipunan-Bucana |  |  | Road Maintenance | 5.89 | CBRMC | a) | 129495.6 | a) | 01/03/19 | e) | - | a) | 129495.6 | a) | 100% | c) | 100% | a) | 16 | Completed |  | 1 | 4
027 | [7 empty] | b) | Crucio | b) | 03/26/19 | f) | - | b) | 129495.6 | b) | - | d) | - | b) | 450 |  |  | 1 | 4
[8 empty] | c) | MANGULIBAS FA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [8 empty] | 1 | 4
[8 empty] | d) | 3 quarters | d) | - | [12 empty] | 1 | 4
|  | Capungagan-Mabuhay-Pandulian |  |  | Road Maintenance | 5.57 | MBA | a) | 294917.73 | a) | 01/03/19 | e) | - | a) | 294917.73 | a) | 100% | c) | 100% | a) | 15 | Completed |  | 1 | 4
028 | [7 empty] | b) | Crucio | b) | 02/18/19 | f) | - | b) | 294917.73 | b) | - | d) | - | b) | 450 |  |  | 1 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [8 empty] | 1 | 4
[8 empty] | d) | - | d) | - | [12 empty] | 1 | 4
[24 empty] | 1 | 4
|  | Capungagan-Mabuhay-Pandulian |  |  | Road Maintenance | 5.57 | CBRMC | a) | 105950.95 | a) | 01/03/19 | e) | - | a) | 105950.95 | a) | 100% | c) | 100% | a) | 16 | Completed |  |  | 4
028 | [7 empty] | b) | Crucio | b) | 03/28/19 | f) | - | b) | 105950.95 | b) | - | d) | - | b) | 450 |  |  | 1 | 4
[8 empty] | c) | CAPUNGAGAN MPC | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [8 empty] | 1 | 4
[8 empty] | d) | 3 quarters | d) | - | [12 empty] | 1 | 4
|  | Florida - New Boholano |  |  | Road Maintenance | 2.54 | MBA | a) | 95863.17 | a) | 01/03/19 | e) | - | a) | 95863.17 | a) | 100% | c) | 100% | a) | 15 | Completed |  | 1 | 4
030 | [7 empty] | b) | Crucio | b) | 02/18/19 | f) | - | b) | 95863.17 | b) | - | d) | - | b) | 450 |  |  | 1 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 31,418.99 | [8 empty] | 1 | 4
[8 empty] | d) | - | d) | - | [12 empty] | 1 | 4
|  | Florida - New Boholano |  |  | Road Maintenance | 2.54 | CBRMC | a) | 47425.27 | a) | 01/03/19 | e) | - | a) | 47425.27 | a) | 100% | c) | 100% | a) | 16 | Completed |  | 1 | 4
030 | [7 empty] | b) | Crucio | b) | 03/28/19 | f) | - | b) | 47425.27 | b) | - | d) | - | b) | 450 |  |  | 1 | 4
[8 empty] | c) | SUPRA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [8 empty] | 1 | 4
[8 empty] | d) | 3 quarters | d) | - | [12 empty] | 1 | 4
|  | Jct. New Boholano - New Loon |  |  | Road Maintenance | 4.77 | MBA | a) | 140549.84 | a) | 01/03/19 | e) | - | a) | 140549.84 | a) | 100% | c) | 100% | a) | 15 | Completed |  | 1 | 4
031 | [7 empty] | b) | Crucio | b) | 02/18/19 | f) | - | b) | 140549.84 | b) | - | d) | - | b) | 450 |  |  | 1 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 40,056.38 | [8 empty] | 1 | 4
[8 empty] | d) | - | d) | - | [12 empty] | 1 | 4
4
|  | Jct. New Boholano - New Loon |  |  | Road Maintenance | 4.77 | CBRMC | a) | 169521.51 | a) | 01/03/19 | e) | - | a) | 169521.51 | a) | 100% | c) | 100% | a) | 16 | Completed |  | 1 | 4
031 | [7 empty] | b) | Crucio | b) | 03/28/19 | f) | - | b) | 169521.51 | b) | - | d) | - | b) | 450 |  |  | 1 | 4
[8 empty] | c) | NEW LOON FA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [8 empty] | 1 | 4
[8 empty] | d) | 3 quarters | d) | - | [12 empty] | 1 | 4
|  | Florida-Suaon-Jct. Gupitan |  |  | Road Maintenance | 15.57 | MBA | a) | 707038.05 | a) | 01/03/19 | e) | - | a) | 707038.05 | a) | 100% | c) | 100% | a) | 15 | Completed |  | 1 | 4
032 | [7 empty] | b) | Crucio | b) | 01/16/19 | f) | - | b) | 707038.05 | b) | - | d) | - | b) | 450 |  |  | 1 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 226,.062.60 | [8 empty] | 1 | 4
[8 empty] | d) | - | d) | - | [12 empty] | 1 | 4
|  | Florida-Suaon-Jct. Gupitan |  |  | Road Maintenance | 15.57 | CBRMC | a) | 419094.85 | a) | 01/03/19 | e) | - | a) | 419094.85 | a) | 100% | c) | 100% | a) | 16 | Completed |  | 1 | 4
032 | [7 empty] | b) | Crucio | b) | 03/28/19 | f) | - | b) | 419094.85 | b) | - | d) | - | b) | 450 |  |  | 1 | 4
[8 empty] | c) | SUPRA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [8 empty] | 1 | 4
[8 empty] | d) | 3 quarters | d) | - | [12 empty] | 1 | 4
|  | Km. 15, Kipalili-New Loon |  |  | Road Maintenance | 6.93 | MBA | a) | 367659.97 | a) | 01/03/19 | e) | - | a) | 367659.97 | a) | 100% | c) | 100% | a) | 15 | Completed |  | 1 | 4
034 | [7 empty] | b) | Crucio | b) | 02/01/19 | f) | - | b) | 367659.97 | b) | - | d) | - | b) | 450 |  |  | 1 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 112,175.78 | [8 empty] | 1 | 4
[8 empty] | d) | - | d) | - | [12 empty] | 1 | 4
|  | Km. 15, Kipalili-New Loon |  |  | Road Maintenance | 6.93 | CBRMC | a) | 237801.01 | a) | 01/03/19 | e) | - | a) | 237801.01 | a) | 100% | c) | 100% | a) | 16 | Completed |  | 1 | 4
034 | [7 empty] | b) | Crucio | b) | 03/26/19 | f) | - | b) | 237801.01 | b) | - | d) | - | b) | 480 |  |  | 1 | 4
[8 empty] | c) | KIPALILI FA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [8 empty] | 1 | 4
[8 empty] | d) | 3 quarters | d) | - | [12 empty] | 1 | 4
|  | Jct. Suaon-Libuton |  |  | Road Maintenance | 7.26 | MBA | a) | 44015.68 | a) | 01/03/19 | e) | - | a) | 44015.68 | a) | 100% | c) | 100% | a) | 15 | Completed |  |  | 4
035 | [7 empty] | b) | Crucio | b) | 01/16/19 | f) | - | b) | 44015.68 | b) | - | d) | - | b) | 450 |  |  | 1 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 24,980.86 | [8 empty] | 1 | 4
[8 empty] | d) | - | d) | - | [12 empty] | 1 | 4
|  | Jct. Suaon-Libuton |  |  | Road Maintenance | 7.26 | CBRMC | a) | 91664.91 | a) | 01/03/19 | e) | - | a) | 91664.91 | a) | 100% | c) | 100% | a) | 16 | Completed |  | 1 | 4
035 | [7 empty] | b) | Crucio | b) | 03/22/19 | f) | - | b) | 91664.91 | b) | - | d) | - | b) | 480 |  |  | 1 | 4
[8 empty] | c) | AALLI | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [8 empty] | 1 | 4
[8 empty] | d) | 3 quarters | d) | - | [12 empty] | 1 | 4
[24 empty] | 1 | 4
|  | Datu Balong - Pinamuno |  |  | Road Maintenance | 2.74 | MBA | a) | 95458.24 | a) | 01/03/19 | e) | - | a) | 95458.24 | a) | 100% | c) | 100% | a) | 15 | Completed |  |  | 4
040 | [7 empty] | b) | Crucio | b) | 03/01/19 | f) | - | b) | 95458.24 | b) | - | d) | - | b) | 450 |  |  | 1 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 12,625.00 | [8 empty] | 1 | 4
[8 empty] | d) | - | d) | - | [12 empty] | 1 | 4
|  | Datu Balong - Pinamuno |  |  | Road Maintenance | 2.74 | CBRMC | a) | 63570.57 | a) | 01/03/19 | e) | - | a) | 63570.57 | a) | 100% | c) | 100% | a) | 16 | Completed |  | 1 | 4
040 | [7 empty] | b) | Crucio | b) | 03/28/19 | f) | - | b) | 63570.57 | b) | - | d) | - | b) | 480 |  |  | 1 | 4
[8 empty] | c) | DATU BALONG FA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [8 empty] | 1 | 4
[8 empty] | d) | 3 quarters | d) | - | [12 empty] | 1 | 4
|  | Sawata - Mamangan - Pinamuno |  |  | Road Maintenance | 14.48 | MBA | a) | 545390.17 | a) | 01/03/19 | e) | - | a) | 545390.17 | a) | 100% | c) | 100% | a) | 15 | Completed |  | 1 | 4
041 | [7 empty] | b) | Crucio | b) | 02/01/19 | f) | - | b) | 545390.17 | b) | - | d) | - | b) | 450 |  |  | 1 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 196,076.60 | [8 empty] | 1 | 4
[8 empty] | d) | - | d) | - | [12 empty] | 1 | 4
|  | Sawata - Mamangan - Pinamuno |  |  | Road Maintenance | 14.48 | CBRMC | a) | 508564.54 | a) | 01/03/19 | e) | - | a) | 508564.54 | a) | 100% | c) | 100% | a) | 16 | Completed |  | 1 | 4
041 | [7 empty] | b) | Crucio | b) | 03/22/19 | f) | - | b) | 508564.54 | b) | - | d) | - | b) | 480 |  |  | 1 | 4
[8 empty] | c) | SAWATA DFA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [8 empty] | 1 | 4
[8 empty] | d) | 3 quarters | d) | - | [12 empty] | 1 | 4
|  | Igangon - Sawata |  |  | Road Maintenance | 9.66 | MBA | a) | 497447.77 | a) | 01/03/19 | e) | - | a) | 497447.77 | a) | 100% | c) | 100% | a) | 15 | Completed |  | 1 | 4
042 | [7 empty] | b) | Crucio | b) | 02/01/19 | f) | - | b) | 497447.77 | b) | - | d) | - | b) | 450 |  |  | 1 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [8 empty] | 1 | 4
[8 empty] | d) | - | d) | - | [12 empty] | 1 | 4
|  | Igangon - Sawata |  |  | Road Maintenance | 9.66 | CBRMC | a) | 197775.1 | a) | 01/03/19 | e) | - | a) | 197775.1 | a) | 100% | c) | 100% | a) | 16 | Completed |  | 1 | 4
042 | [7 empty] | b) | Crucio | b) | 03/22/19 | f) | - | b) | 197775.1 | b) | - | d) | - | b) | 480 |  |  | 1 | 4
[8 empty] | c) | SAWATA DFA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [8 empty] | 1 | 4
[8 empty] | d) | 3 quarters | d) | - | [12 empty] | 1 | 4
4
4
|  | New Corella - Sto. Niño - Macgum |  |  | Road Maintenance | 17.11 | MBA | a) | 606294.08 | a) | 01/03/19 | e) | - | a) | 606294.08 | a) | 100% | c) | 100% | a) | 15 | Completed |  | 1 | 4
044 | [7 empty] | b) | Crucio | b) | 01/03/19 | f) | - | b) | 606294.08 | b) | - | d) | - | b) | 450 |  |  | 1 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 246,619.77 | [8 empty] | 1 | 4
[8 empty] | d) | - | d) | - | [12 empty] | 1 | 4
|  | New Corella - Sto. Niño - Macgum |  |  | Road Maintenance | 17.11 | CBRMC | a) | 308434.97 | a) | 01/03/19 | e) | - | a) | 308434.97 | a) | 100% | c) | 100% | a) | 16 | Completed |  | 1 | 4
044 | [7 empty] | b) | Crucio | b) | 03/26/19 | f) | - | b) | 308434.97 | b) | - | d) | - | b) | 480 |  |  | 1 | 4
[8 empty] | c) | SAN ISIDRO FA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [8 empty] | 1 | 4
[8 empty] | d) | 3 quarters | d) | - | [12 empty] | 1 | 4
|  | Tagaytay - Buan |  |  | Road Maintenance | 4.92 | MBA | a) | 173197.37 | a) | 01/03/19 | e) | - | a) | 173197.37 | a) | 100% | c) | 100% | a) | 15 | Completed |  | 1 | 4
045 | [7 empty] | b) | Crucio | b) | 03/18/19 | f) | - | b) | 173197.37 | b) | - | d) | - | b) | 450 |  |  | 1 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 26254.58 | [8 empty] | 1 | 4
[8 empty] | d) | - | d) | - | [12 empty] | 1 | 4
|  | Tagaytay - Buan |  |  | Road Maintenance | 4.92 | CBRMC | a) | 131850.07 | a) | 01/03/19 | e) | - | a) | 131850.07 | a) | 100% | c) | 100% | a) | 16 | Completed |  | 1 | 4
045 | [7 empty] | b) | Crucio | b) | 03/22/19 | f) | - | b) | 131850.07 | b) | - | d) | - | b) | 480 |  |  | 1 | 4
[8 empty] | c) | BUAN IFA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [8 empty] | 1 | 4
[8 empty] | d) | 3 quarters | d) | - | [12 empty] | 1 | 4
|  | limbaan - Sto. Niño |  |  | Road Maintenance | 3.19 | MBA | a) | 153706.77 | a) | 01/03/19 | e) | - | a) | 153706.77 | a) | 100% | c) | 100% | a) | 15 | Completed |  | 1 | 4
049 | [7 empty] | b) | Crucio | b) | 03/01/19 | f) | - | b) | 153706.77 | b) | - | d) | - | b) | 450 |  |  | 1 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 32534.49 | [8 empty] | 1 | 4
[8 empty] | d) | - | d) | - | [12 empty] | 1 | 4
|  | limbaan - Sto. Niño |  |  | Road Maintenance | 3.19 | CBRMC | a) | 53657.51 | a) | 01/03/19 | e) | - | a) | 53657.51 | a) | 100% | c) | 100% | a) | - | Completed |  | 1 | 4
049 | [7 empty] | b) | Crucio | b) | - | f) | - | b) | 53657.51 | b) | - | d) | - | b) | - |  |  | 1 | 4
[8 empty] | c) | - | c) | - | g) | 2019-12-31 | c) | - | [8 empty] | 1 | 4
[8 empty] | d) | - | d) | - | [12 empty] | 1 | 4
|  | Del Pilar - Jct. Silangan |  |  | Road Maintenance | 4.17 | MBA | a) | 187097.4 | a) | 01/03/19 | e) | - | a) | 187097.4 | a) | 100% | c) | 100% | a) | 15 | Completed |  | 1 | 4
051 | [7 empty] | b) | Crucio | b) | 03/18/19 | f) | - | b) | 187097.4 | b) | - | d) | - | b) | 450 |  |  | 1 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 94181.74 | [8 empty] | 1 | 4
[8 empty] | d) | - | d) | - | [12 empty] | 1 | 4
|  | Del Pilar - Jct. Silangan |  |  | Road Maintenance | 4.17 | CBRMC | a) | 113014.34 | a) | 01/03/19 | e) | - | a) | 113014.34 | a) | 100% | c) | 100% | a) | 16 | Completed |  | 1 | 4
051 | [7 empty] | b) | Crucio | b) | 03/26/19 | f) | - | b) | 113014.34 | b) | - | d) | - | b) | 480 |  |  | 1 | 4
[8 empty] | c) | DURIAN DACUDAO | c) | 12/31/19 | g) | - | c) | - | [8 empty] | 1 | 4
[8 empty] | d) | 3 quarters | d) | - | [12 empty] | 1 | 4
|  | New Corella - New Sambog - Silangan |  |  | Road Maintenance | 5.1 | MBA | a) | 201994.35 | a) | 01/03/19 | e) | - | a) | 201994.35 | a) | 100% | c) | 100% | a) | 15 | Completed |  | 1 | 4
052 | [7 empty] | b) | Crucio | b) | 03/01/19 | f) | - | b) | 201994.35 | b) | - | d) | - | b) | 450 |  |  | 1 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 63402.48 | [8 empty] | 1 | 4
[8 empty] | d) | - | d) | - | [12 empty] | 1 | 4
|  | New Corella - New Sambog - Silangan |  |  | Road Maintenance | 5.1 | CBRMC | a) | 131850.07 | a) | 01/03/19 | e) | - | a) | 131850.07 | a) | 100% | c) | 100% | a) | 16 | Completed |  | 1 | 4
052 | [7 empty] | b) | Crucio | b) | 03/26/19 | f) | - | b) | 131850.07 | b) | - | d) | - | b) | 480 |  |  | 1 | 4
[8 empty] | c) | DURIAN DACUDAO | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [8 empty] | 1 | 4
[8 empty] | d) | 3 quarters | d) | - | [12 empty] | 1 | 4
|  | Sta. Fe - Del Monte |  |  | Road Maintenance | 3.34 | MBA | a) | 37923.51 | a) | 01/03/19 | e) | - | a) | 37923.51 | a) | 100% | c) | 100% | a) | 15 | Completed |  | 1 | 4
056 | [7 empty] | b) | Crucio | b) | 03/18/19 | f) | - | b) | 37923.51 | b) | - | d) | - | b) | 450 |  |  | 1 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 36595.13 | [8 empty] | 1 | 4
[8 empty] | d) | - | d) | - | [12 empty] | 1 | 4
|  | Sta. Fe - Del Monte |  |  | Road Maintenance | 3.34 | CBRMC | a) | 70633.96 | a) | 01/03/19 | e) | - | a) | 70633.96 | a) | 100% | c) | 100% | a) | 16 | Completed |  | 1 | 4
056 | [7 empty] | b) | Crucio | b) | 03/21/19 | f) | - | b) | 70633.96 | b) | - | d) | - | b) | 480 |  |  | 1 | 4
[8 empty] | c) | DEL MONTE CACAO | c) | 12/31/19 | g) | 2019-12-31 | c) | 4,872.18 | [8 empty] | 1 | 4
[8 empty] | d) | 3 quarters | d) | - | [12 empty] | 1 | 4
|  | New Corella - New Bohol |  |  | Road Maintenance | 11.54 | MBA | a) | 356226.67 | a) | 01/03/19 | e) | - | a) | 356226.67 | a) | 100% | c) | 100% | a) | 15 | Completed |  |  | 4
058 | [7 empty] | b) | Crucio | b) | 02/01/19 | f) | - | b) | 356226.67 | b) | - | d) | - | b) | 450 |  |  | 1 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 110,982.71 | [8 empty] | 1 | 4
[8 empty] | d) | - | d) | - | [12 empty] | 1 | 4
|  | New Corella - New Bohol |  |  | Road Maintenance | 11.54 | CBRMC | a) | 190711.7 | a) | 01/03/19 | e) | - | a) | 190711.7 | a) | 100% | c) | 100% | a) | 16 | Completed |  | 1 | 4
058 | [7 empty] | b) | Crucio | b) | 03/22/19 | f) | - | b) | 190711.7 | b) | - | d) | - | b) | 480 |  |  | 1 | 4
[8 empty] | c) | SAN JOSE COCONUT | c) | 12/31/19 | g) | 2019-12-31 | c) | 5,847.18 | [8 empty] | 1 | 4
[8 empty] | d) | 3 quarters | d) | - | [12 empty] | 1 | 4
[24 empty] | 1 | 4
4
|  | Jct. Carcor - Prk. 9 Bagsak |  |  | Road Maintenance | 2.5 | MBA | a) | 108618.49 | a) | 01/03/19 | e) | - | a) | 108618.49 | a) | 100% | c. | 100% | a) | 15 | Completed
059 | [7 empty] | b) | Crucio | b) | 03/01/19 | f) | - | b) | 108618.49 | b) | - | d) |  | b) | 480 |  |  | 1 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 79952.88 | [8 empty] | 1 | 4
[8 empty] | d) | - | d) | - | [12 empty] | 1 | 4
[24 empty] | 1 | 4
4
4
|  | Jct. Carcor - Prk. 9 Bagsak |  |  | Road Maintenance | 2.5 | CBRMC | a) | 42284.76 | a) | 01/03/19 | e) | - | a) | 42284.76 | a) | 100% | c) | 100% | a) | 16 | Completed |  |  | 4
059 | [7 empty] | b) | Crucio | b) | 03/22/19 | f) | - | b) | 42284.76 | b) | - | d) | - | b) | 480 |  |  | 1 | 4
[8 empty] | c) | CARCOR MOTOR | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [8 empty] | 1 | 4
[8 empty] | d) | 3 quarters | d) | - | [12 empty] | 1 | 4
|  | Carcor - Jct. Kauswagan |  |  | Road Maintenance | 4.32 | MBA | a) | 264514.71 | a) | 01/03/19 | e) | - | a) | 264514.71 | a) | 100% | c) | 100% | a) | 15 | Completed |  | 1 | 4
060 | [7 empty] | b) | Crucio | b) | 03/18/19 | f) | - | b) | 264514.71 | b) | - | d) |  | b) | 450 |  |  | 1 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 80733.11 | [8 empty] | 1 | 4
[8 empty] | d) | - | d) | - | [12 empty] | 1 | 4
|  | Carcor - Jct. Kauswagan |  |  | Road Maintenance | 4.32 | CBRMC | a) | 48398.27 | a) | 01/03/19 | e) | - | a) | 48398.27 | a) | 100% | c) | 100% | a) | 16 | Completed |  |  | 4
060 | [7 empty] | b) | Crucio | b) | 03/22/19 | f) | - | b) | 48398.27 | b) | - | d) | - | b) | 480 |  |  | 1 | 4
[8 empty] | c) | CARCOR MOTOR | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [8 empty] | 1 | 4
[8 empty] | d) | 3 quarters | d) | - | [12 empty] | 1 | 4
|  | Del Pilar - Prk 9 Bagsak - San Jose |  |  | Road Maintenance | 4.99 | MBA | a) | 170215.76 | a) | 01/03/19 | e) | - | a) | 170215.76 | a) | 100% | c) | 100% | a) | 15 | Completed |  | 1 | 4
061 | [7 empty] | b) | Crucio | b) | 03/01/19 | f) | - | b) | 170215.76 | b) | - | d) | - | b) | 450 |  |  | 1 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 87595.63 | [8 empty] | 1 | 4
[8 empty] | d) | - | d) | - | [12 empty] | 1 | 4
|  | Del Pilar - Prk 9 Bagsak - San Jose |  |  | Road Maintenance | 4.99 | CBRMC | a) | 223674.22 | a) | 01/03/19 | e) | - | a) | 223674.22 | a) | 100% | c) | 100% | a) | 16 | Completed |  | 1 | 4
061 | [7 empty] | b) | Crucio | b) | 03/22/19 | f) | - | b) | 223674.22 | b) | - | d) | - | b) | 480 |  |  | 1 | 4
[8 empty] | c) | SAN JOSE COCONUT | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [8 empty] | 1 | 4
[8 empty] | d) | 3 quarters | d) | - | [12 empty] | 1 | 4
|  | San Juan - New Talisay |  |  | Road Maintenance | 5.13 | MBA | a) | 306261.25 | a) | 01/03/19 | e) | - | a) | 306261.25 | a) | 100% | c) | 100% | a) | 15 | Completed |  | 1 | 4
063 | [7 empty] | b) | Crucio | b) | 02/01/19 | f) | - | b) | 306261.25 | b) | - | d) | - | b) | 450 |  |  | 1 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 85123.48 | [8 empty] | 1 | 4
[8 empty] | d) | - | d) | - | [12 empty] | 1 | 4
|  | San Juan - New Talisay |  |  | Road Maintenance | 5.13 | CBRMC | a) | 93906.31 | a) | 01/03/19 | e) | - | a) | 93906.31 | a) | 100% | c) | 100% | a) | 16 | Completed |  |  | 4
063 | [7 empty] | b) | Crucio | b) | 03/26/19 | f) | - | b) | 93906.31 | b) | - | d) | - | b) | 480 |  |  | 1 | 4
[8 empty] | c) | NEW TALISAY IAWA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [8 empty] | 1 | 4
[8 empty] | d) | 3 quarters | d) | - | [12 empty] | 1 | 4
|  | San Juan - kauswagan - New Cortez |  |  | Road Maintenance | 3.22 | MBA | a) | 187879.04 | a) | 01/03/19 | e) | - | a) | 187879.04 | a) | 100% | c) | 100% | a) | 15 | Completed |  | 1 | 4
064 | [7 empty] | b) | Crucio | b) | 03/18/19 | f) | - | b) | 187879.04 | b) | - | d) | - | b) | 450 |  |  | 1 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 3,025.00 | [8 empty] | 1 | 4
[8 empty] | d) | - | d) | - | [12 empty] | 1 | 4
4
4
|  | San Juan - kauswagan - New Cortez |  |  | Road Maintenance | 3.22 | CBRMC | a) | 63298.26 | a) | 01/03/19 | e) | - | a) | 63298.26 | a) | 100% | c) | 100% | a) | 16 | Completed |  |  | 4
064 | [7 empty] | b) | Crucio | b) | 03/22/19 | f) | - | b) | 63298.26 | b) | - | d) | - | b) | 480 |  |  | 1 | 4
[8 empty] | c) | SAN JOSE COCONUT | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [8 empty] | 1 | 4
[8 empty] | d) | 3 quarters | d) | - | [12 empty] | 1 | 4
|  | New Bohol - Jct. El Unido |  |  | Road Maintenance | 2.12 | MBA | a) | 54989.06 | a) | 01/03/19 | e) | - | a) | 54989.06 | a) | 100% | c) | 100% | a) | 15 | Completed |  |  | 4
065 | [7 empty] | b) | Crucio | b) | 03/01/19 | f) | - | b) | 54989.06 | b) | - | d) | - | b) | 450 |  |  | 1 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 21021.99 | [8 empty] | 1 | 4
[8 empty] | d) | - | d) | - | [12 empty] | 1 | 4
|  | New Bohol - Jct. El Unido |  |  | Road Maintenance | 2.12 | CBRMC | a) | 58861.64 | a) | 01/03/19 | e) | - | a) | 58861.64 | a) | 100% | c) | 100% | a) | 16 | Completed |  | 1 | 4
065 | [7 empty] | b) | Crucio | b) | 03/26/19 | f) | - | b) | 58861.64 | b) | - | d) | - | b) | 480 |  |  | 1 | 4
[8 empty] | c) | MANDISKAB TRIBAL | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [8 empty] | 1 | 4
[8 empty] | d) | 3 quarters | d) | - | [12 empty] | 1 | 4
[24 empty] | 1 | 4
4
|  | New Corella - El unido - Jct. Mesaoy |  |  | Road Maintenance | 8.63 | MBA | a) | 388002.46 | a) | 01/03/19 | e) | - | a) | 388002.46 | a) | 100% | c) | 100% | a) | 15 | Completed |  |  | 4
066 | [7 empty] | b) | Crucio | b) | 02/11/19 | f) | - | b) | 388002.46 | b) | - | d) | - | b) | 450 |  |  | 1 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 58142.76 | [8 empty] | 1 | 4
[8 empty] | d) | - | d) | - | [12 empty] | 1 | 4
|  | New Corella - El unido - Jct. Mesaoy |  |  | Road Maintenance | 8.63 | CBRMC | a) | 233092.08 | a) | 01/03/19 | e) | - | a) | 233092.08 | a) | 100% | c) | 100% | a) | 16 | Completed |  | 1 | 4
066 | [7 empty] | b) | Crucio | b) | 03/26/19 | f) | - | b) | 233092.08 | b) | - | d) | - | b) | 480 |  |  | 1 | 4
[8 empty] | c) | MANDISKAB TRIBAL | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [8 empty] | 1 | 4
[8 empty] | d) | 3 quarters | d) | - | [12 empty] | 1 | 4
|  | Mesaoy - Dasing |  |  | Road Maintenance | 1.39 | MBA | a) | 29749.5 | a) | 01/03/19 | e) | - | a) | 29749.5 | a) | 100% | c) | 100% | a) | 15 | Completed |  | 1 | 4
067 | [7 empty] | b) | Crucio | b) | 03/18/19 | f) | - | b) | 29749.5 | b) | - | d) | - | b) | 450 |  |  | 1 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 10000 | [8 empty] | 1 | 4
[8 empty] | d) | - | d) | - | [12 empty] | 1 | 4
|  | Mesaoy - Dasing |  |  | Road Maintenance | 1.39 | CBRMC | a) | 54152.71 | a) | 01/03/19 | e) | - | a) | 54152.71 | a) | 100% | c) | 100% | a) | 16 | Completed |  | 1 | 4
067 | [7 empty] | b) | Crucio | b) | 03/26/19 | f) | - | b) | 54152.71 | b) | - | d) | - | b) | 480 |  |  | 1 | 4
[8 empty] | c) | MANDISKAB TRIBAL | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [8 empty] | 1 | 4
[8 empty] | d) | 3 quarters | d) | - | [12 empty] | 1 | 4
|  | Jct. San Juan - Jct. Mesaoy |  |  | Road Maintenance | 1.82 | MBA | a) | 106788.95 | a) | 01/03/19 | e) | - | a) | 106788.95 | a) | 100% | c) | 100% | a) | 15 | Completed |  | 1 | 4
068 | [7 empty] | b) | Crucio | b) | 03/01/19 | f) | - | b) | 106788.95 | b) | - | d) | - | b) | 450 |  |  | 1 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 17502.68 | [8 empty] | 1 | 4
[8 empty] | d) | - | d) | - | [12 empty] | 1 | 4
|  | Jct. San Juan - Jct. Mesaoy |  |  | Road Maintenance | 1.82 | CBRMC | a) | 35180.83 | a) | 01/03/19 | e) | - | a) | 35180.83 | a) | 100% | c) | 100% | a) | 16 | Completed |  | 1 | 4
068 | [7 empty] | b) | Crucio | b) | 03/26/19 | f) | - | b) | 35180.83 | b) | - | d) | - | b) | 480 |  |  | 1 | 4
[8 empty] | c) | MANDISKAB TRIBAL | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [8 empty] | 1 | 4
[8 empty] | d) | 3 quarters | d) | - | [12 empty] | 1 | 4
|  | Mesaoy - Jct. Mahayahay |  |  | Road Maintenance | 4.6 | MBA | a) | 146984.46 | a) | 01/03/19 | e) | - | a) | 146984.46 | a) | 100% | c) | 100% | a) | 15 | Completed |  | 1 | 4
069 | [7 empty] | b) | Crucio | b) | 03/18/19 | f) | - | b) | 146984.46 | b) | - | d) | - | b) | 450 |  |  | 1 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 7618.27 | [8 empty] | 1 | 4
[8 empty] | d) | - | d) | - | [12 empty] | 1 | 4
|  | Mesaoy - Jct. Mahayahay |  |  | Road Maintenance | 4.6 | CBRMC | a) | 160103.65 | a) | 01/03/19 | e) | - | a) | 160103.65 | a) | 100% | c) | 100% | a) | 16 | Completed |  |  | 4
069 | [7 empty] | b) | Crucio | b) | 03/22/19 | f) | - | b) | 160103.65 | b) | - | d) | - | b) | 480 |  |  | 1 | 4
[8 empty] | c) | MAHAYAHAY IFA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [8 empty] | 1 | 4
[8 empty] | d) | 3 quarters | d) | - | [12 empty] | 1 | 4
4
4
|  | Mesaoy - New bohol |  |  | Road Maintenance | 5.36 | MBA | a) | 165361.13 | a) | 01/03/19 | e) | - | a) | 165361.13 | a) | 100% | c) | 100% | a) | 15 | Completed |  |  | 4
070 | [7 empty] | b) | Crucio | b) | 03/01/19 | f) | - | b) | 165361.13 | b) | - | d) | - | b) | 480 |  |  | 1 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 2543.9 | [8 empty] | 1 | 4
[8 empty] | d) | - | d) | - | [12 empty] | 1 | 4
|  | Mesaoy - New bohol |  |  | Road Maintenance | 5.36 | CBRMC | a) | 224851.45 | a) | 01/03/19 | e) | - | a) | 224851.45 | a) | 100% | c) | 100% | a) | 16 | Completed |  |  | 4
070 | [7 empty] | b) | Crucio | b) | 03/26/19 | f) | - | b) | 224851.45 | b) | - | d) | - | b) | 480 |  |  | 1 | 4
[8 empty] | c) | MANDISKAB TRIBAL | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [8 empty] | 1 | 4
[8 empty] | d) | 3 quarters | d) | - | [12 empty] | 1 | 4
|  | Bdry. Tagum - Baca - New Corella |  |  | Road Maintenance | 13.01 | MBA | a) | 217182.9 | a) | 01/03/19 | e) | - | a) | 217182.9 | a) | 100% | c) | 100% | a) | 15 | Completed |  | 1 | 4
071 | [7 empty] | b) | Crucio | b) | 03/18/19 | f) | - | b) | 217182.9 | b) | - | d) | - | b) | 450 |  |  | 1 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 19550 | [8 empty] | 1 | 4
[8 empty] | d) | - | d) | - | [12 empty] | 1 | 4
|  | Bdry. Tagum - Baca - New Corella |  |  | Road Maintenance | 13.01 | CBRMC | a) | 214256.36 | a) | 01/03/19 | e) | - | a) | 214256.36 | a) | 100% | c) | 100% | a) | 16 | Completed |  | 1 | 4
071 | [7 empty] | b) | Crucio | b) | 03/26/19 | f) | - | b) | 214256.36 | b) | - | d) | - | b) | 480 |  |  | 1 | 4
[8 empty] | c) | DURIAN DACUDAO | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [8 empty] | 1 | 4
[8 empty] | d) | 3 quarters | d) | - | [12 empty] | 1 | 4
|  | Prk. 1, Maunlom - Prk. 6 Maunlom Road |  |  | Road Maintenance | 3.56 | MBA | a) | 150912.87 | a) | 01/03/19 | e) | - | a) | 150912.87 | a) | 100% | c) | 100% | a) | 15 | Completed |  | 1 | 4
147 | [7 empty] | b) | Crucio | b) | 03/01/19 | f) | - | b) | 150912.87 | b) | - | d) | - | b) | 450 |  |  | 1 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 23025 | [8 empty] | 1 | 4
[8 empty] | d) | - | d) | - | [12 empty] | 1 | 4
|  | Prk. 1, Maunlom - Prk. 6 Maunlom Road |  |  | Road Maintenance | 3.56 | CBRMC | a) | 63973.36 | a) | 01/03/19 | e) | - | a) | 63973.36 | a) | 100% | c) | 100% | a) | 16 | Completed |  | 1 | 4
147 | [7 empty] | b) | Crucio | b) | 03/22/19 | f) | - | b) | 63973.36 | b) | - | d) | - | b) | 480 |  |  | 1 | 4
[8 empty] | c) | THE BEST VEGETABLE | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [8 empty] | 1 | 4
[8 empty] | d) | 3 quarters | d) | - | [12 empty] | 1 | 4
[24 empty] | 1 | 4
|  | New Visayas - Binancian |  |  | Road Maintenance | 7.77 | MBA | a) | 14814.34 | a) | 01/03/19 | e) | - | a) | 14814.34 | a) | 100% | c) | 100% | a) | 15 | Completed |  |  | 44
149 | [7 empty] | b) | Crucio | b) | 03/18/19 | f) | - | b) | 14814.34 | b) | - | d) | - | b) | 450 |  |  | 1 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 5,000.00 | [8 empty] | 1 | 4
[8 empty] | d) | - | d) | - | [12 empty] | 1 | 4
|  | New Visayas - Binancian |  |  | Road Maintenance | 7.77 | CBRMC | a) | 129495.6 | a) | 01/03/19 | e) | - | a) | 129495.6 | a) | 100% | c) | 100% | a) | 16 | Completed |  | 1 | 4
149 | [7 empty] | b) | Crucio | b) | 03/22/19 | f) | - | b) | 129495.6 | b) | - | d) | - | b) | 480 |  |  | 1 | 4
[8 empty] | c) | BUAN IFA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [8 empty] | 1 | 4
[8 empty] | d) | 3 quarters | d) | - | [12 empty] | 1 | 4
|  | Datu Balong - Prk. Mamalian |  |  | Road Maintenance | 3.46 | MBA | a) | 117454.89 | a) | 01/03/19 | e) | - | a) | 117454.89 | a) | 100% | c) | 39.37% | a) | 15 | Completed |  | 1 | 4
150 | [7 empty] | b) | Crucio | b) | 03/18/19 | f) | - | b) | 117454.89 | b) | - | d) | - | b) | 450 |  |  | 1 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 10115 | [8 empty] | 1 | 4
[8 empty] | d) | - | d) | - | [12 empty] | 1 | 4
|  | Datu Balong - Prk. Mamalian |  |  | Road Maintenance | 3.46 | CBRMC | a) | 59264.42 | a) | 01/03/19 | e) | - | a) | 59264.42 | a) | 100% | c) | 100% | a) | 16 | Completed |  | 1 | 4
150 | [7 empty] | b) | Crucio | b) | 03/28/19 | f) | - | b) | 59264.42 | b) | - | d) | - | b) | 480 |  |  | 1 | 4
[8 empty] | c) | DATU BALONG FA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [8 empty] | 1 | 4
[8 empty] | d) | 3 quarters | d) | - | [12 empty] | 1 | 4
4
4
4
4
4
4
4
4
4
4
4
A.2 GENERAL FUND CY 2019 |  |  |  |  | Road Maintenance | KM | MBA/CBRMC | a) | 11,618,834.00 | a) | 01/03/19 | e) | - | a) | 11,618,834.00 | a) | 66% | c) | 66% | a) | 42 | See list of Provincial Roads
Road ID |  | 1. Maintenance Of Various Prov'l. Roads and Bridges Dist 2 |  |  |  | 288.26 |  | b) | Matuguinas | b) | 01/03/19 | f) | - | b) | 11,618,834.00 | b) | - | d) | - | b) | 924 |  |  | FS
[8 empty] | c) | PEO/CBRMC | c) | 12/31/19 | g) | - | c) | - | [8 empty] | AC
11DAN | [9 empty] | d) | - | [12 empty] | AC
[8 empty] | d) | 261 days | d) | - | [12 empty] | AC
|  | Cebulano - Mangalcal |  |  | Road Maintenance | 4.17 | MBA | a) | 142161.87 | a) | 01/03/19 | e) | - | a) | 142161.87 | a) | 100% | c) | 100% | a) | 9 | Completed |  | AC | 4
| 073 | [6 empty] | b) | Clar | b) | 2019-01-15 | f) | - | b) | 142161.87 | b) | - | d) | - | b) | 18 |  |  | 2 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 118,609.29 | [8 empty] | 2 | 4
[8 empty] | d) | - | d) | - | [12 empty] | 2 | 4
|  | Tubod - basa - Mangalcal |  |  | Road Maintenance | 3.93 | MBA | a) | 156875.9 | a) | 01/03/19 | e) | - | a) | 156875.9 | a) | 100% | c) | 100% | a) | 9 | Completed |  | 2 | 4
074 | [7 empty] | b) | Clar | b) | 2019-01-15 | f) | - | b) | 156875.9 | b) | - | d) | - | b) | 18 |  |  | 2 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 143,372.65 | [8 empty] | 2 | 4
[8 empty] | d) | - | d) | - | [12 empty] | 2 | 4
|  | Upper Mangalcal - Lower Mangalcal |  |  | Road Maintenance | 2.43 | 0 | a) | 79237.14 | a) | 01/03/19 | e) | - | a) | 79237.14 | a) | 100% | c) | 100% | a) | 9 | Completed |  | 2 | 4
078 | [7 empty] | b) | Clar | b) | 2019-01-14 | f) | - | b) | 79237.14 | b) | - | d) | - | b) | 27 |  |  | 2 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 69,430.97 | [8 empty] | 2 | 4
[8 empty] | d) | - | d) | - | [12 empty] | 2 | 4
|  | Jct. Highway Carmen - Mangalcal - Tubod |  |  | Road Maintenance | 11.34 | MBA | a) | 463135.67 | a) | 01/03/19 | e) | - | a) | 463135.67 | a) | 100% | c) | 100% | a) | 9 | Completed |  | 2 | 4
082 | [7 empty] | b) | Clar | b) | 01/10/19 | f) | - | b) | 463135.67 | b) | - | d) | - | b) | 45 |  |  | 2 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 170,106.43 | [8 empty] | 2 | 4
[8 empty] | d) | - | d) | - | [12 empty] | 2 | 4
|  | Jct. Highway Carmen - Mangalcal - Tubod |  |  | Road Maintenance | 11.34 | 0 | a) | 253557.37 | a) | 01/03/19 | e) | - | a) | 253557.37 | a) | 100% | c) | 100% | a) | 10 | Completed |  | 2 | 4
082 | [7 empty] | b) | Maligro | b) | 03/25/19 | f) | - | b) | 253557.37 | b) | - | d) | - | b) | 40 |  |  | 2 | 4
[8 empty] | c) | TUBOD CENTRO LOWER IRRIGATORS ASSOCIATION | c) | 09/25/19 | g) | 2019-12-31 | c) | - | [8 empty] | 2 | 4
[8 empty] | d) | 3 quarters | d) | - | [12 empty] | 2 | 4
|  | Jct. Highway Sto. Niño - Kabanlakan - La Paz |  |  | Road Maintenance | 2.13 | MBA | a) | 76067.88 | a) | 01/03/19 | e) | - | a) | 76067.88 | a) | 100% | c) | 100% | a) | 9 | Completed |  | 2 | 4
084 | [7 empty] | b) | Clar | b) | 01/10/19 | f) | - | b) | 76067.88 | b) | - | d) | - | b) | 45 |  |  | 2 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 66,477.91 | [8 empty] | 2 | 4
[8 empty] | d) | - | d) | - | [12 empty] | 2 | 4
|  | Ising - Sto Niño |  |  | Road Maintenance | 2.07 | 0 | a) | 82413.14 | a) | 01/03/19 | e) | - | a) | 82413.14 | a) | 100% | c) | 100% | a) | 5 | Completed |  | 2 | 4
085 | [7 empty] | b) | Clar | b) | 01/17/19 | f) | - | b) | 82413.14 | b) | - | d) | - | b) | 15 |  |  | 2 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 27,093.24 | [8 empty] | 2 | 4
[8 empty] | d) | - | d) | - | [12 empty] | 2 | 4
|  | Ising - Sadpodon - Taba - Dila -Dila |  |  | Road Maintenance | 5.68 | MBA | a) | 248941.33 | a) | 01/03/19 | e) | - | a) | 248941.33 | a) | 100% | c) | 100% | a) | 9 | Completed |  | 2 | 4
086 | [7 empty] | b) | Clar | b) | 01/12/19 | f) | - | b) | 248941.33 | b) | - | d) | - | b) | 27 |  |  | 2 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 82,329.02 | [8 empty] | 2 | 4
[8 empty] | d) | - | d) | - |  |  |  | . | [8 empty] | 2 | 4
[24 empty] | 2 | 4
|  | Tuganay - taba |  |  | Road Maintenance | 4.27 | 0 | a) | 291377.9 | a) | 01/03/19 | e) | - | a) | 291377.9 | a) | 70% | c) | 70% | a) | 9 | Completed |  |  | 4
087 | [7 empty] | b) | Clar | b) | 01/09/19 | f) | - | b) | 291377.9 | b) | - | d) | - | b) | 27 |  |  | 2 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 12/31/2019 | c) | 238,412.28 | [8 empty] | 2 | 4
[8 empty] | d) | - | d) | - | [12 empty] | 2 | 4
|  | Jct. Highway Tuganay - Taba |  |  | Road Maintenance | 4.4 | MBA | a) | 32972.82 | a) | 01/03/19 | e) | - | a) | 32972.82 | a) | 65% | c) | 65% | a) | 9 | Completed |  | 2 | 4
088 | [7 empty] | b) | Clar | b) | 01/22/19 | f) | - | b) | 32972.82 | b) | - | d) | - | b) | 18 |  |  | 2 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 12/31/2019 | c) | 22,639.09 | [8 empty] | 2 | 4
[8 empty] | d) | - | d) | - | [12 empty] | 2 | 4
|  | Jct. Highway Ising - Magsaysay |  |  | Road Maintenance | 10.84 | 0 | a) | 417818.12 | a) | 01/03/19 | e) | - | a) | 417818.12 | a) | 60% | c) | 60% | a) | 10 | Completed |  | 2 | 4
089 | [7 empty] | b) | Clar | b) | 01/22/19 | f) | - | b) | 417818.12 | b) | - | d) | - | b) | 50 |  |  | 2 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 12/31/2019 | c) | 313,488.39 | [8 empty] | 2 | 4
[8 empty] | d) | - | d) | - | [12 empty] | 2 | 4
4
4
4
|  | New Camiling - Alejal - Lower Magsaysay |  |  | Road Maintenance | 6.73 | MBA | a) | 240878.08 | a) | 01/03/19 | e) | - | a) | 240878.08 | a) | 80% | c) | 80% | a) | 4 | Completed |  | 2 | 4
091 | [7 empty] | b) | Clar | b) | 01/22/19 | f) | - | b) | 240878.08 | b) | - | d) | - | b) | 20 |  |  | 2 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 12/31/2019 | c) | - | [8 empty] | 2 | 4
[8 empty] | d) | - | d) | - | [12 empty] | 2 | 4
|  | Jct. highway Tuganay - Anibongan |  |  | Road Maintenance | 3.66 | 0 | a) | 150684.44 | a) | 01/03/19 | e) | - | a) | 150684.44 | a) | 100% | c) | 100% | a) | 6 | Completed |  | 2 | 4
094 | [7 empty] | b) | Clar | b) | 01/22/19 | f) | - | b) | 150684.44 | b) | - | d) | - | b) | 18 |  |  | 2 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 12/31/2019 | c) | - | [8 empty] | 2 | 4
[8 empty] | d) | - | d) | - | [12 empty] | 2 | 4
|  | Anibongan - Guadalupe |  |  | Road Maintenance | 2.48 | MBA | a) | 91325.06 | a) | 01/03/19 | e) | - | a) | 91325.06 | a) | 100% | c) | 100% | a) | 9 | Completed |  | 2 | 4
095 | [7 empty] | b) | Clar | b) | 01/23/19 | f) | - | b) | 91325.06 | b) | - | d) | - | b) | 18 |  |  | 2 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 12/31/2019 | c) | - | [8 empty] | 2 | 4
[8 empty] | d) | - | d) | - | [12 empty] | 2 | 4
|  | Tuganay - Anibongan - San Isidro |  |  | Road Maintenance | 7.22 | 0 | a) | 139979.8 | a) | 01/03/19 | e) | - | a) | 139979.8 | a) | 100% | c) | 100% | a) | 9 | Completed |  | 2 | 4
096 | [7 empty] | b) | Clar | b) | 01/24/19 | f) | - | b) | 139979.8 | b) | - | d) | - | b) | 36 |  |  | 2 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 12/31/2019 | c) | 1890.37 | [8 empty] | 2 | 4
[8 empty] | d) | - | d) | - | [12 empty] | 2 | 4
|  | Jct. Anibongan - Prk. 2, 7, 5, San Isidro |  |  | Road Maintenance | 3.14 | MBA | a) | 104378.03 | a) | 01/03/19 | e) | - | a) | 104378.03 | a) | 100% | c) | 100% | a) | 10 | Completed |  | 2 | 4
097 | [7 empty] | b) | Clar | b) | 01/24/19 | f) | - | b) | 104378.03 | b) | - | d) | - | b) | 20 |  |  | 2 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 12/31/2019 | c) | 56,087.50 | [8 empty] | 2 | 4
[8 empty] | d) | - | d) | - | [12 empty] | 2 | 4
|  | Anibongan - Salvacion - Cabay-angan |  |  | Road Maintenance | 6.93 | 0 | a) | 415461.61 | a) | 01/03/19 | e) | - | a) | 415461.61 | a) | 100% | c) | 100% | a) | 9 | Completed |  | 2 | 4
098 | [7 empty] | b) | Clar | b) | 01/25/19 | f) | - | b) | 415461.61 | b) | - | d) | - | b) | 45 |  |  | 2 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 12/31/2019 | c) | - | [8 empty] | 2 | 4
[8 empty] | d) | - | d) | - | [12 empty] | 2 | 4
|  | Jct. Highway Guadalupe - Bdry. Tagum |  |  | Road Maintenance | 7.9 | MBA | a) | 456131.09 | a) | 01/03/19 | e) | - | a) | 456131.09 | a) | 100% | c) | 100% | a) | 9 | Completed |  | 2 | 4
101 | [7 empty] | b) | Clar | b) | 01/25/19 | f) | - | b) | 456131.09 | b) | - | d) | - | b) | 18 |  |  | 2 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 12/31/2019 | c) | - | [8 empty] | 2 | 4
[8 empty] | d) | - | d) | - | [12 empty] | 2 | 4
|  | Jct. Highway Guadalupe - Bdry. Tagum |  |  | Road Maintenance | 7.9 | 0 | a) | 228201.66 | a) | 01/03/19 | e) | - | a) | 228201.66 | a) | 100% | c) | 100% | a) | 8 | Completed |  | 2 | 4
101 | [7 empty] | b) | Maligro | b) | 03/25/19 | f) | - | b) | 228201.66 | b) | - | d) | - | b) | 40 |  |  | 2 | 4
[8 empty] | c) | LAMPIA PAG-ASA IRRIGATORS ASSOCIATION, INC. | c) | 12/25/19 | g) | 12/31/2019 | c) | - | [8 empty] | 2 | 4
[8 empty] | d) | 3 quarters | d) | - | [12 empty] | 2 | 4
|  | Poblacion Dujali - Prk. 8 Dujali |  |  | Road Maintenance | 8.2 | MBA | a) | 285600.05 | a) | 01/03/19 | e) | - | a) | 285600.05 | a) | 100% | c) | 100% | a) | 10 | Completed |  | 2 | 4
105 | [7 empty] | b) | Clar | b) | 01/28/19 | f) | - | b) | 285600.05 | b) | - | d) | - | b) | 50 |  |  | 2 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 12/31/2019 | c) | - | [8 empty] | 2 | 4
[8 empty] | d) | - | d) | - | [12 empty] | 2 | 4
|  | Dujali - San Isidro |  |  | Road Maintenance | 3 | 0 | a) | 130319.3 | a) | 01/03/19 | e) | - | a) | 130319.3 | a) | 100% | c) | 100% | a) | 8 | Completed |  | 2 | 4
107 | [7 empty] | b) | Gamad | b) | 01/28/19 | f) | - | b) | 130319.3 | b) | - | d) | - | b) | 30 |  |  | 2 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 12/31/2019 | c) | 45,943.12 | [8 empty] | 2 | 4
[8 empty] | d) | - | d) | - | [12 empty] | 2 | 4
|  | Prk. 5, RJS - Prk. 6 New Casay |  |  | Road Maintenance | 2.73 | MBA | a) | 235277 | a) | 01/03/19 | e) | - | a) | 235277 | a) | 100% | c) | 100% | a) | 2 | Completed |  | 2 | 4
109 | [7 empty] | b) | Gamad | b) | 01/28/19 | f) | - | b) | 235277 | b) | - | d) | - | b) | 6 |  |  | 2 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 12/31/2019 | c) | 90,745.35 | [8 empty] | 2 | 4
[8 empty] | d) | - | d) | - | [12 empty] | 2 | 4
|  | Prk. 5 - Prk. 1 Pawas Dujali |  |  | Road Maintenance | 2.18 | 0 | a) | 76067.68 | a) | 01/03/19 | e) | - | a) | 76067.68 | a) | 100% | c) | 100% | a) | 10 | Completed |  | 2 | 4
112 | [7 empty] | b) | Gamad | b) | 01/18/19 | f) | - | b) | 76067.68 | b) | - | d) | - | b) | 20 |  |  | 2 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 12/31/2019 | c) | 40,112.50 | [8 empty] | 2 | 4
[8 empty] | d) | - | d) | - | [12 empty] | 2 | 4
|  | Dujali - Balisong - Magupising |  |  | Road Maintenance | 5.52 | MBA | a) | 260591.93 | a) | 01/03/19 | e) | - | a) | 260591.93 | a) | 100% | c) | 100% | a) | 4 | Completed |  | 2 | 4
113 | [7 empty] | b) | Gamad | b) | 01/09/19 | f) | - | b) | 260591.93 | b) | - | d) | - | b) | 8 |  |  | 2 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 12/31/2019 | c) | - | [8 empty] | 2 | 4
[8 empty] | d) | - | d) | - | [12 empty] | 2 | 4
4
4
4
|  | Dujali - Pawas - San Vicente |  |  | Road Maintenance | 4.42 | 0 | a) | 139536.42 | a) | 01/03/19 | e) | - | a) | 139536.42 | a) | 100% | c) | 100% | a) | 10 | Completed |  | 2 | 4
117 | [7 empty] | b) | Gamad | b) | 01/22/19 | f) | - | b) | 139536.42 | b) | - | d) | - | b) | 18 |  |  | 2 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 12/31/2019 | c) | 52,133.86 | [8 empty] | 2 | 4
[8 empty] | d) | - | d) | - | [12 empty] | 2 | 4
|  | Jct. Salvacion - San Vicente - Cabay-angan |  |  | Road Maintenance | 3.45 | MBA | a) | 247460.9 | a) | 01/03/19 | e) | - | a) | 247460.9 | a) | 100% | c) | 100% | a) | 10 | Completed |  | 2 | 4
118 | [7 empty] | b) | Gamad | b) | 01/23/19 | f) | - | b) | 247460.9 | b) | - | d) | - | b) | 18 |  |  | 2 | 4
[8 empty] | c) | PEO | c) | 02/31/19 | g) | 12/31/2019 | c) | 151,887.50 | [8 empty] | 2 | 4
[8 empty] | d) | - | d) | - | [12 empty] | 2 | 4
|  | Jct. Salvacion - San Vicente - Cabay-angan |  |  | Road Maintenance | 3.45 | 0 | a) | 152134.44 | a) | 01/03/19 | e) | - | a) | 152134.44 | a) | 100% | c) | 100% | a) | 8 | Completed |  | 2 | 4
118 | [7 empty] | b) | Gamad | b) | 03/26/19 | f) | - | b) | 152134.44 | b) | - | d) | - | b) | 36 |  |  | 2 | 4
[8 empty] | c) | BALISONG SAN VICENTE IRRIGATORS ASSOCIATION | c) | 12/26/19 | g) | 12/31/2019 | c) | [9 empty] | 2 | 4
[8 empty] | d) | 3 quarters | d) | - | [10 empty] | Completed |  | 2 | 4
|  | Dujali - San Miguel |  |  | Road Maintenance | 3.95 | MBA | a) | 101202.04 | a) | 01/03/19 | e) | - | a) | 101202.04 | a) | 80% | c) | 90% | a) | 11 |  |  | 2 | 4
119 | [7 empty] | b) | Gamad | b) | 01/10/19 | f) | - | b) | 101202.04 | b) | - | d) | - | b) | 22 |  |  | 2 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | - | c) | 90,350.03 | [8 empty] | 2 | 4
[8 empty] | d) | - | d) | - | [12 empty] | 2 | 4
|  | San Miguel - Casig-ang |  |  | Road Maintenance | 2.55 | 0 | a) | 79237.14 | a) | 01/03/19 | e) | - | a) | 79237.14 | a) | 100% | c) | 100% | a) | 10 | Completed |  | 2 | 4
122 | [7 empty] | b) | Gamad | b) | 01/24/19 | f) | - | b) | 79237.14 | b) | - | d) | - | b) | 10 |  |  | 2 | 4
[8 empty] | c) | BALISONG SAN VICENTE IRRIGATORS ASSOCIATION | c) | 12/31/19 | g) | 12/31/2019 | c) | 40,112.50 | [8 empty] | 2 | 4
[8 empty] | d) | - | d) | - | [12 empty] | 2 | 4
|  | Prk. Magsaysay - Lunga-og - Dalisay |  |  | Road Maintenance | 2.81 | MBA | a) | 79762.14 | a) | 01/03/19 | e) | - | a) | 79762.14 | a) | 100% | c) | 100% | a) | 8 | Completed |  | 2 | 4
127 | [7 empty] | b) | Gamad | b) | 01/30/19 | f) | - | b) | 79762.14 | b) | - | d) | - | b) | 8 |  |  | 2 | 4
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 12/31/2019 | c) | 40,612.50 | [8 empty] | 2 | 4
[8 empty] | d) | - | d) | - | [12 empty] | 2 | 4
|  | Prk. Apitong - Upper Balisong - Dalisay |  |  | Road Maintenance | 4.6 | 0 | a) | 137846.03 | a) | 01/03/19 | e) | - | a) | 137846.03 | a) | 100% | c) | 100% | a) | 8 | Completed |  | 2 | 4
128 | [7 empty] | b) | Gamad | b) | 01/31/19 | f) | - | b) | 137846.03 | b) | - | d) | - | b) | 8 |  |  | 2 | 4
[8 empty] | c) | BALISONG SAN VICENTE IRRIGATORS ASSOCIATION | c) | 12/31/19 | g) | 12/31/2019 | c) | - | [8 empty] | 2 | 4
[8 empty] | d) | - | d) | - | [12 empty] | 2 | 4
|  | Sitio Paradise - Magkakaisa - Esperanza |  |  | Road Maintenance | 1.75 | MBA | a) | 66552.75 | a) | 01/03/19 | e) | - | a) | 66552.75 | a) | 100% | c) | 100% | a) | 8 | Completed |  | 2 | 4
129 | [7 empty] | b) | 79762.14 | b) | 01/22/19 | f) | - | b) | 66552.75 | b) | - | d) | - | b) | 8 |  |  | 2 | 4
[8 empty] | c) | Gamad | c) | 12/31/19 | g) | 12/31/2019 | c) | 22,246.26 | [8 empty] | 2 | 4
[8 empty] | d) | - | d) | - | [12 empty] | 2 | 4
|  | Los Amigos 1 - Esperanza - Los Amigos 2 |  |  | Road Maintenance | 3.59 | 0 | a) | 101202.04 | a) | 01/03/19 | e) | - | a) | 101202.04 | a) | 100% | c) | 100% | a) | 10 | Completed |  | 2 | 4
130 | [7 empty] | b) | Gamad | b) | 01/24/19 | f) | - | b) | 101202.04 | b) | - | d) | - | b) | 20 |  |  | 2 | 4
[8 empty] | c) | BALISONG SAN VICENTE IRRIGATORS ASSOCIATION | c) | 12/31/19 | g) | 12/31/2019 | c) | 50,837.50 | [8 empty] | 2 | 4
[8 empty] | d) | - | d) | - | [12 empty] | 2 | 4
|  | Mugas - Lunga-og |  |  | Road Maintenance | 2.68 | MBA | a) | 66552.75 | a) | 01/03/19 | e) | - | a) | 91,693.64 | a) | 100% | c) | 100% | a) | 6 | Completed |  | 2 | 4
132 | [7 empty] | b) | 79762.14 | b) | 01/17/19 | f) | - | b) | 91,693.64 | b) | - | d) | - | b) | 24 |  |  | 2 | 4
[8 empty] | c) | Gamad | c) | 12/31/19 | g) | 12/31/2019 | c) | 50,837.50 | [8 empty] | 2 | 4
[8 empty] | d) | - | d) | - | [12 empty] | 2 | 4
|  | Pantaron - Mugas |  |  | Road Maintenance | 3.35 | 0 | a) | 101202.04 | a) | 01/03/19 | e) | - | a) | 101202.04 | a) | 100% | c) | 100% | a) | 9 | Completed |  | 2 | 4
133 | [7 empty] | b) | Gamad | b) | 01/23/19 | f) | - | b) | 101202.04 | b) | - | d) | - | b) | 18 |  |  | 2 | 4
[8 empty] | c) | BALISONG SAN VICENTE IRRIGATORS ASSOCIATION | c) | 12/31/19 | g) | 12/31/2019 | c) | 90,349.93 | [8 empty] | 2 | 4
[8 empty] | d) | - | d) | - | [12 empty] | 2 | 4
|  | Sto. Tomas - Bdry. Mamacao |  |  | Road Maintenance | 4.9 | MBA | a) | 110710.44 | a) | 01/03/19 | e) | - | a) | 110710.44 | a) | 100% | c) | 100% | a) | 10 | Completed |  | 2 | 4
135 | [7 empty] | b) | 79762.14 | b) | 01/21/19 | f) | - | b) | 110710.44 | b) | - | d) | - | b) | 40 |  |  | 2 | 4
[8 empty] | c) | Gamad | c) | 12/31/19 | g) | 12/31/2019 | c) | 50,837.50 | [8 empty] | 2 | 4
[8 empty] | d) | - | d) | - | [12 empty] | 2 | 4
|  | Fd. Rd. 3 - San Jose |  |  | Road Maintenance | 4.55 | 0 | a) | 147367.49 | a) | 01/03/19 | e) | - | a) | 147367.49 | a) | 100% | c) | 100% | a) | 10 | Completed |  | 2 | 4
136 | [7 empty] | b) | Gamad | b) | 01/25/19 | f) | - | b) | 147367.49 | b) | - | d) | - | b) | 30 |  |  | 2 | 4
[8 empty] | c) | BALISONG SAN VICENTE IRRIGATORS ASSOCIATION | c) | 12/31/19 | g) | 12/31/2019 | c) | 56,174.69 | [8 empty] | 2 | 4
[8 empty] | d) | - | d) | - | [12 empty] | 2 | 4
4
4
|  | Menzi - balagunan - Tulalian |  |  | Road Maintenance | 10.63 | MBA | a) | 520167.79 | a) | 01/03/19 | e) | - | a) | 520167.79 | a) | 100% | c) | 100% | a) | 6 | Completed |  | 2 | 4
138 | [7 empty] | b) | 79762.14 | b) | 01/07/19 | f) | - | b) | 520167.79 | b) | - | d) | - | b) | 18 |  |  | 2 | 4
[8 empty] | c) | Gamad | c) | 12/31/19 | g) | 12/31/2019 | c) | 204,850.57 | [8 empty] | 2 | 4
[8 empty] | d) | - | d) | - | [12 empty] | 2 | 4
|  | Jct. Bdry. Tagum - Talomo |  |  | Road Maintenance | 12.01 | 0 | a) | 407429.19 | a) | 01/03/19 | e) | - | a) | 407429.19 | a) | 100% | c) | 100% | a) | 10 | Completed |  | 2 | 4
145 | [7 empty] | b) | Gamad | b) | 01/11/19 | f) | - | b) | 407429.19 | b) | - | d) | - | b) | 50 |  |  | 2 | 4
[8 empty] | c) | BALISONG SAN VICENTE IRRIGATORS ASSOCIATION | c) | 12/31/19 | g) | 12/31/2019 | c) | 168,544.84 | [8 empty] | 2 | 4
[8 empty] | d) | - | d) | - | [12 empty] | 2 | 4
|  | San Jose - Sitio Mahayahay, Magwawa |  |  | Road Maintenance | 0.84 | MBA | a) | 7919.35 | a) | 01/03/19 | e) | - | a) | 7919.35 | a) | 100% | c) | 100% | a) | 2 | Completed |  | 2 | 4
151 | [7 empty] | b) | 79762.14 | b) | 01/16/19 | f) | - | b) | 7919.35 | b) | - | d) | - | b) | 8 |  |  | 2 | 4
[8 empty] | c) | Gamad | c) | 12/31/19 | g) | 12/31/2019 | c) | 1,509.27 | [8 empty] | 2 | 4
[8 empty] | d) | - | d) | - | [12 empty] | 2 | 4
B. 20% DEVELOPMENT FUND CY 2019 | [23 empty] | FS
[5 empty] | Type | Physical | Mode | PROJECT DATA | [6 empty] | Financial (000) | Physical Accompl;ishment |  |  |  | Employment
|  | Name of Project |  |  | of | Target | of | a.)Project Cost |  | a.)Date A lot. Rel. |  | e.)# of days |  |  | a.) Program | a.) Planned |  | c.) Actual |  | Generated # |  |  | REMRRKS
[5 empty] | Project | (Discrip tion) | Impl. | b.)Project Engineer |  | b.)Date Started |  |  | suspended |  | b.)Allotment | b.) Revised |  | d.) Slippage |  | a.) Persons
[7 empty] | MBA / | c.)Implementor |  | c.)Target Compl. |  | f.) # of days extended |  |  | c.)Disbursement |  |  |  |  | b.) Man-days
[7 empty] | CBRMC |  |  |  | Date | g.)Date Completed
Road ID |  | 1. Rehabilitation Of Various Prov'l. Roads and Bridges Dist. 1 |  |  | Road Rehabilitation | KM | MBA | a) | 41465029 | a) | 01/03/19 | e) | - | a) | 41465029 | a) | - | c) | - | a) | 46 | See list of Provincial Roads |  | FS
[6 empty] | 109.55 |  | b) | Paraguya | b) | 01/03/19 | f) | - | b) | 41465029 | b) | - | d) | - | b) | 920 |  |  | AC
11DAN | [7 empty] | c) | PEO | c) | 12/31/19 | g) | - | c) | - | [8 empty] | AC
[10 empty] | d) | - | [12 empty] | AC
[8 empty] | d) | 261 days | d) | - | [12 empty] | AC
|  | Jct. Highway Canatan - Doña Andrea |  |  | Road Rehabilitation | 4.34 | Admin | a) | 2,000,000.00 | a) | 2019-12-06 | e) | - | a) | 2,000,000.00 | a) | - | c) | - | a) | - | For implementation |  | AC
007 | [7 empty] | b) | MJ / Kinanahan | b) | - | f) | - | b) | 2,000,000.00 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
|  | Pamacaun - Lasang Banate |  |  | Road Rehabilitation | 4.34 | Admin | a) | 2000000 | a) | 2019-06-27 | e) | - | a) | 2000000 | a) | - | c) | - | a) | - | For implementation |  | 1
015 | [7 empty] | b) | Gone | b) | - | f) | - | b) | 2000000 | b) | - | d) | - | b) | - | Waiting for the delivery of geo-grid |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [6 empty] | materials. An approved request letter |  | 1
[8 empty] | d) | - | d) | - | [10 empty] | dated Dec. 3, 2019 for the extension of 50 days from Provincial Administrator Engr. Rabanoz is on file |  | 1
|  | Kapalong - Mabantao - Florida |  |  | Road Rehabilitation | 7.86 | Admin | a) | 1231000 | a) | 2019-01-31 | e) | - | a) | 1231000 | a) | 70.98% | c) | 70.98% | a) | - | Waiting for the availability of the long arm backhoe |  | 1
016 | [7 empty] | b) | Aparece | b) | - | f) | - | b) | 1231000 | b) | - | d) | 0% | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
|  | Jct. Highway Gabuyan - Semong - Dagohoy |  |  | Road Rehabilitation | 6.97 | Admin | a) | 2492000 | a) | 01/03/19 | e) | - | a) | 2492000 | a) | - | c) | - | a) | - | Re-aligned to Impvt of km.9 Sagayen - Sawata Provincial Road Phase II ( AIP 3rd revision CY 2019 / SB no.4, 2019) |  | 1
017 | [7 empty] | b) |  | b) | - | f) | - | b) | 2492000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
|  | Sto. Niño - Palma Gil - Sitio Opao |  |  | Road Rehabilitation | 11.6 | Admin | a) | 1901000 | a) | 2019-06-19 | e) | - | a) | 1901000 | a) | - | c) | - | a) | - | NTP not yet serve to Tagum Builders because they have not yet complied with the construction safety requirement |  | 1
019 | [7 empty] | b) | Lumapat | b) | - | f) | - | b) | 1901000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
|  | Daligdigon - Lumabag |  |  | Road Rehabilitation | 11.6 | Admin | a) | 680000 | a) | 01/03/19 | e) | - | a) | 680000 | a) | - | c) | - | a) | - | Re-aligned to Impvt of km.9 Sagayen - Sawata Provincial Road Phase II ( AIP 3rd revision CY 2019 / SB no.4, 2019) |  | 1
022 | [7 empty] | b) |  | b) | - | f) | - | b) | 680000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
|  | Sto. Niño - Daligdigon - Paiton |  |  | Road Rehabilitation | 11.6 | Admin | a) | 3000000 | a) | 2019-10-03 | e) | - | a) | 3000000 | a) | - | c) | - | a) | - | Temporary suspended, materials for re-PR |  | 1
023 | [7 empty] | b) | Crucio | b) | - | f) | - | b) | 3000000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
|  | Jct. Paiton - Mibolo |  |  | Road Rehabilitation | 23.9 | Admin | a) | 6000000 | a) | 2019-03-25 | e) | - | a) | 6000000 | a) | 21.05% | c) | 21.05% | a) | - | 22% as of Nov. 30, 2019 Temporary suspended because the materials for the box culvert was re-PR |  | 1
024 | [7 empty] | b) | Lumapat | b) | Aug.1, 2019 | f) | - | b) | 6000000 | b) | - | d) | 0% | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
|  | Monte Dujali - Gupitan |  |  | Road Rehabilitation | 4.58 | Admin | a) | 1200000 | a) | 2019-12-06 | e) | - | a) | 1200000 | a) | - | c) | - | a) | - |  |  | 1
037 | [7 empty] | b) | MJ/Kinanahan | b) | - | f) | - | b) | 1200000 | b) | - | d) | - | b) | - | For implementation |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
|  | Jct. Sawata - Bdry. Binasbas |  |  | Road Rehabilitation | 0.46 | Admin | a) | 500000 | a) | 2019-06-19 | e) | - | a) | 500000 | a) | - | c) | - | a) | - |  |  | 1
043 | [7 empty] | b) | MJ/Kinanahan | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - | For implementation |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
|  | New Corella - Saug |  |  | Road Rehabilitation | 12.52 | Admin | a) | 6500000 | a) | 2019-03-12 | e) | - | a) | 6500000 | a) | 29.54% | c) | 29.54% | a) | 19 | Temporary suspended because the equipmenta were pulled out to fast track the implementation of Km. 9 Sagayen- Sawata Provincial Road (CMGP) |  | 1
048 | [7 empty] | b) | MJ/Kinanahan | b) | 03/26/19 | f) | - | b) | 6500000 | b) | - | d) | - | b) | 570 |  |  | 1
[8 empty] | c) | PEO | c) | 12/31/19 | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
|  | Jct. Monte Carlo - Upper Cabaywa - Canatan |  |  | Road Rehabilitation | 4.61 | Admin | a) | 8838000 | a) | 2019-01-31 | e) | - | a) | 8838000 | a) | 89.5% | c) | 89.5% | a) | 19 | On -going 90% accomplished. The target date of completion was Dec. 31, 2019, for process time extension request |  | 1
050 | [7 empty] | b) | Garcia | b) | 03/26/19 | f) | - | b) | 8838000 | b) | - | d) | 0% | b) | 570 |  |  | 1
[8 empty] | c) | PEO | c) | 12/31/19 | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
[5 empty] | Road Rehabilitation |  |  | a. )P 500,000.00 |  | a.) 01/31/19 |  |  |  | a.) 500,000.00 | [9 empty] | 1 | 4
|  | Purok 10 Pob. Road, New Corella | [7 empty] | b.) Feb. 16, 2019 |  |  |  | b.) 500,000.00 | [7 empty] | Completed |  | 1 | 4
[12 empty] | g.) Feb. 28, 2019 | [11 empty] | 1 | 4
[24 empty] | 1 | 4
[5 empty] | Road Rehabilitation |  |  | a.)1,815,000.00 |  | a.) 01/31/19 |  |  |  | a.) 1,815,000.00 | [9 empty] | 1 | 4
|  | Purok 7 Pob- Jct. New Sambog | [7 empty] | b.)March 1, 2019 |  |  |  | b.) 1,815,000.00 | [7 empty] | Completed |  | 1 | 4
[12 empty] | g.) May 15, 2019 | [11 empty] | 1 | 4
[24 empty] | 1 | 4
[5 empty] | Road Rehabilitation |  |  | a.) 1,389,000.00 |  | a.) 01/31/19 |  |  |  | a.) 1,389,000.00 | [7 empty] | Completed with a savings of P303,898.08 furtherance and is for implementation |  | 1 | 4
|  | Del Pilar- El Unido Road | [5 empty] | b.) Fabian |  | b.) March 18,2019 |  |  |  | a.) 1,389,000.00 | [9 empty] | 1 | 4
[12 empty] | g.) May 8, 2019 | [11 empty] | 1 | 4
[24 empty] | 1 | 4
|  | Bdry. Tagum - Baca - New Corella |  |  | Road Rehabilitation | 13.01 | Admin | a) | 1419029 | a) | 01/03/19 | e) | - | a) | 1419029 | a) | - | c) | - | a) | - | Re-aligned to Impvt of km.9 Sagayen Sawata Provincial Road Phase II (SB. No. 4 CY 2019) |  | 1
071 | [7 empty] | b) | Crucio | b) | - | f) | - | b) | 1419029 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
1
1
|  | SUPPLEMENTAL BUDGET NO 4 CY 2019 / CONTINUING APPROPRIATION | [21 empty] | AC
AC
[8 empty] | a.) 7,742,775.95 | [5 empty] | a.) 7,742,775.95 | [7 empty] | Waiting for the delivery of materials |  | 1
|  | Impvt. of Km. 9 Sagayen - Sawata Provincial Road Phase II | [5 empty] | b.) Kenny | [5 empty] | b.) 7,742,775.95 | [9 empty] | 1
1
1
Road ID |  | 1. Rehabilitation Of Various Prov'l. Roads and Bridges Dist 2 |  |  | Road Rehabilitation | KM | Admin | a) | 46740117 | a) | 01/03/19 | [10 empty] | See list of Provincial Roads
[6 empty] | 115.62 |  | b) | Matuguinas | b) | - | [12 empty] | AC
11DAN | [7 empty] | c) | PEO | c) | - | [12 empty] | AC
[10 empty] | d) | - | [12 empty] | AC
[8 empty] | d) | 261 days | d) | - | [12 empty] | AC
|  | Jct. Highway Sto. Niño - Cebulano |  |  | Road Rehabilitation | 2.09 | Admin | a) | 1045000 | a) | 2019-03-18 | e) | - | a) | 1045000 | a) | 20% | c) | 20% | a) | 11 | On-going |  | AC
072 | [7 empty] | b) | Obar | b) | 2019-05-21 | f) | - | b) | 1045000 | b) | - | d) | - | b) | 55 |  |  | 2
[8 empty] | c) | PEO | c) | 2020-02-02 | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
[5 empty] | Road Rehabilitation |  |  | a.) 515,000.00 |  | a.) 03/12/19 |  |  |  | a.) 515,000.00 | [9 empty] | 2
|  | Jct. Highway -Tubod - Bagong Silang | [5 empty] | b.) Clar |  | b.) March 18, 2019 |  |  |  | b.) 515,000.00 | [7 empty] | Completed |  | 2
[12 empty] | g.) June 15, 2019 | [11 empty] | 2
2
|  | Basa - Tubod |  |  | Road Rehabilitation | 1.56 | Admin | a) | 1000000 | a) | 2019-06-19 | e) | - | a) | 1000000 | a) | - | c) | - | a) | - |  |  | 2
076 | [7 empty] | b) | Piad | b) | Nov. 11, 2019 | f) | - | b) | 1000000 | b) | - | d) | - | b) | - | On-going |  | 2
[8 empty] | c) | - | c) | 2020-03-09 | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | Tubod - Pilar |  |  | Road Rehabilitation | 1.55 | Admin | a) | 16000000 | a) | 06/19/19 & 12/9/19 | e) | - | a) | 16000000 | a) | - | c) | - | a) | - | On-going |  | 2
077 | [7 empty] | b) | Gamad/Clar | b) | Dec. 18, 2019 | f) | - | b) | 16000000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | Nov. 5, 2020 | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
[5 empty] | Road Rehabilitation |  |  | a.) 390,000.00 |  | a.) 03/12/19 |  |  |  | a.) 390,000.00 | [9 empty] | 2 | 4
|  | Cebulano- Luceta | [5 empty] | b.) Clar |  | b.) March 8, 2019 |  |  |  | b.) 390,000.00 | [7 empty] | Completed |  | 2 | 4
[12 empty] | g.) June 15, 2019 | [11 empty] | 2 | 4
[24 empty] | 2 | 4
[5 empty] | Road Rehabilitation |  |  | a.) 295,000.00 |  | a.) 03/12/19 |  |  |  | a.) 295,000.00 | [9 empty] | 2 | 4
|  | Lower Asuncion - Upper Asuncion | [5 empty] | b.) Clar |  | b.) March 18, 2019 |  |  |  | b.) 295,000.00 | [7 empty] | Completed |  | 2 | 4
[12 empty] | g.) June 15, 2019 | [11 empty] | 2 | 4
[24 empty] | 2 | 4
[5 empty] | Road Rehabilitation |  |  | a.) 1,220,000.00 |  | a.) 03/12/19 |  |  |  | a.) 1,220,000.00 | [9 empty] | 2
|  | Jct. Highway - Sto. Nino - La Paz - San Vicente | [5 empty] | b.)Obar |  | b.) March 18, 2019 |  |  |  | b.) 1,220,000.00 | [7 empty] | Completed |  | 2
[12 empty] | g.) Sept. 30, 2019 | [11 empty] | 2
2
|  | Alejal - Alemag |  |  | Road Rehabilitation | 1.79 |  | a) | 970000 | a) | 2019-03-18 | e) | - | a) | 970000 | a) | 100% | c) | 100% | a) | 7 | Completed. Financially completed |  | 2
092 | [7 empty] | b) | Gamad/Clar | b) | 2019-05-20 | f) | - | b) | 970000 | b) | 100 | d) | 0% | b) | 20 |  |  | 2
[8 empty] | c) | - | c) | 2019-09-12 | g) | Sept. 30, 2019 | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
[5 empty] | Road Rehabilitation |  |  | a.) 640,000.00 |  | a.) 03/12/19 |  |  |  | a.) 640,000.00 | [9 empty] | 2
|  | Mabaus - Cabay -angan | [5 empty] | b.)Clar |  | b.) Maech 18, 2019 |  |  |  | a.) 640,000.00 | [7 empty] | Completed |  | 2
[12 empty] | g.) July 30, 2019 | [11 empty] | 2
2
[5 empty] | Road Rehabilitation |  |  | a.) 280,000.00 |  | a.) 03/12/19 |  |  |  | a.) 280,000.00 | [9 empty] | 2
|  | Mabaus - Salvacion | [5 empty] | b.)Clar |  | b.) March 18, 2019 |  |  |  | a.) 280,000.00 | [9 empty] | 2
[12 empty] | g.) June 30, 2019 | [9 empty] | Completed |  | 2
2
|  | Dalisay - Mabuhay |  |  | Road Rehabilitation | 3.25 | Admin | a) | 1000000 | a) | 2019-05-16 | e) | - | a) | 1000000 | a) | 80% | c) | 80% | a) | 10 |  |  | 2
102 | [7 empty] | b) | Gamad/Clar | b) | 2019-06-17 | f) |  | b) | 1000000 | b) |  | d) | 0% | b) | 20 | On-going |  | 2
[8 empty] | c) | - | c) | 2/29,2019 | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | Sitio Malaga - Tibulao |  |  | Road Rehabilitation | 3.22 | Admin | a) | 1000000 | a) | 2019-06-25 | e) | - | a) | 1000000 | a) | - | c) | - | a) | - |  |  | 2
103 | [7 empty] | b) | Gamad/Clar | b) | Nov. 11, 2019 | f) | - | b) | 1000000 | b) | - | d) | - | b) | - | On-going |  | 2
[8 empty] | c) | - | c) | Feb. 9, 2020 | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | Dujali - Tanglaw |  |  | Road Rehabilitation | 3.6 | Admin | a) | 2075000 | a) | 2019-10-03 | e) | - | a) | 2075000 | a) | - | c) | - | a) | - |  |  | 2
104 | [7 empty] | b) | Balbastro | b) | Dec. 28, 2019 | f) | - | b) | 2075000 | b) | - | d) | - | b) | - | On-going |  | 2
[8 empty] | c) | - | c) | Apr. 16, 2020 | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | Dujali - New Casay |  |  |  | 3.2 | Admin | a) | 640000 | a) | 2019-05-16 | e) | - | a) | 640000 | a) | 100% | c) | 100% | a) | 10 |  |  | 2 | 4
106 | [7 empty] | b) | Gamad/Clar | b) | 2019-06-17 | f) | 40 | b) | 640000 | b) |  | d) | - | b) | 40 | Completed |  | 2 | 4
[8 empty] | c) | - | c) |  | g) | 10/15/2019 | c) | - | [8 empty] | 2 | 4
[8 empty] | d) | - | d) | - | [12 empty] | 2 | 4
[5 empty] | Road Rehabilitation |  |  | a.) 450,000.00 |  | a.) 03/12/19 |  |  |  | a.) 450,000.00 | [9 empty] | 2
|  | New Casay - Bugtong Talisay | [5 empty] | b.)Clar |  | b.) March 18, 2019 |  |  |  | a.) 450,000.00 | [7 empty] | Completed |  | 2
[12 empty] | g.)June 30, 2019 | [11 empty] | 2
2
|  | Cabay-angan - Esperanza |  |  | Road Rehabilitation | 5.37 | Admin | a) | 1300000 | a) | 2019-05-16 | e) | - | a) | 1300000 | a) | 80% | c) | 80% | a) | 9 |  |  | 2
110 | [7 empty] | b) | Gamad/Clar | b) | 2019-06-17 | f) | - | b) | 1300000 | b) | - | d) | - | b) | 36 | On- going |  | 2
[8 empty] | c) | PEO | c) | Feb. 29, 2020 | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | [13 empty] | 2
[5 empty] | Road Rehabilitation |  |  | a.)220,000.00 |  | a.) 03/12/19 |  |  |  | a.)220,000.00 |  | a.) 100 % |  | c.)100% | [5 empty] | 2
|  | Purok 6 Cabay-angan - Esti | [5 empty] | b.) Gamad |  | b.) March 18, 2019 |  |  |  | a.)220,000.00 | [7 empty] | Completed |  | 2
[12 empty] | g.) June 30, 2019 | [11 empty] | 2
2
[5 empty] | Road Rehabilitation |  |  | a.)250,000.00 |  | a.) March 12, 2019 | [5 empty] | a.) 100 % |  | c.)100% | [5 empty] | 2
|  | Dujali - Sitio Pawas | [5 empty] | b.) Gamad |  | b.) March 18, 2019 | [11 empty] | Completed |  | 2
[12 empty] | g.) Jun 30, 2019 | [11 empty] | 2
2
[5 empty] | Road Rehabilitation |  |  | a.) 280,000.00 |  | a.) March 12, 2019 | [5 empty] | a.) 100 % |  | c.)100% | [5 empty] | 2
|  | Purok 1 to Purok 2 Sitio Pawas | [6 empty] | b.) Gamad | b.) March 18, 2019 | [11 empty] | Completed |  | 2
[12 empty] | g.) Jun 30, 2019 | [11 empty] | 2
2
|  | San Miguel - Crossing Kinamayan |  |  | Road Rehabilitation | 2.8 | Admin | a) | 560000 | a) | 2019-06-25 | e) | - | a) | 560000 | a.) 100 % |  | c.)100% |  | a) | - |  |  | 2 | 4
120 | [7 empty] | b) | Nasol | b) | Sept. 19, 2019 | f) | - | b) | 560000 | b) | - | d) | - | b) | - | Completed |  | 2 | 4
[8 empty] | c) | - | c) | - | g) | Nov. 30, 2019 | c) | - | [8 empty] | 2 | 4
[8 empty] | d) | - | d) | - | [12 empty] | 2 | 4
|  | San Miguel -Libertad Provincial Road |  |  | Road Rehabilitation | 6.2 | Admin | a) | 1240000 | a) | 2019-05-29 | e) | - | a) | 1240000 | a) | 59.41% | c) | 59.41% | a) | 9 |  |  | 2
121 | [7 empty] | b) | Gamad | b) | 2019-06-17 | f) |  | b) | 1240000 | b) | - | d) | - | b) | 36 | On-going |  | 2
[8 empty] | c) | - | c) | Feb. 29, 2020 | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | Bacali - Casig-ang - Libertad |  |  | Road Rehabilitation | 4.7 | Admin | a) | 940000 | a) | 2019-06-07 | e) | - | a) | 940000 | a) | 80% | c) | 80% | a) | 9 | On-going |  | 2
123 | [7 empty] | b) | Gamad | b) | 2019-06-27 | f) | 35 | b) | 940000 | b) | - | d) | - | b) | 36 |  |  | 2
[8 empty] | c) | Admin | c) | Feb. 29, 2020 | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | Kinamayan - Moslog - Mahayag |  |  | Road Rehabilitation | 3.23 | Admin | a) | 1000000 | a) | 2019-05-20 | e) | - | a) | 1000000 | a) | 80% | c) | 80% | a) | 10 | On going |  | 2
124 | [7 empty] | b) | Gamad | b) | 2019-06-27 | f) | 29 | b) | 1000000 | b) | - | d) | - | b) | 20 |  |  | 2
[8 empty] | c) | PEO | c) | Feb. 29, 2020 | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | San Miguel - Moslog - Kinamayan |  |  | Road Rehabilitation | 2.9 | Admin | a) | 1000000 | a) | 2019-05-20 | e) | - | a) | 1000000 | a) | 80% | c) | 80% | a) | 6 | On-going |  | 2
125 | [7 empty] | b) | Gamad | b) | 2019-06-27 | f) | 29 | b) | 1000000 | b) | - | d) | - | b) | 24 |  |  | 2
[8 empty] | c) | - | c) | Feb. 29, 2020 | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | Kinamayan - Lunga-og |  |  | Road Rehabilitation | 2.59 | Admin | a) | 520000 | a) | 2019-03-18 | e) | - | a) | 520000 | a) | 100% | c) | 100% | a) | 9 | Completed |  | 2
126 | [7 empty] | b) | Gamad/Clar | b) | 5/202/019 | f) | - | b) | 520000 | b) | - | d) | - | b) | 36 |  |  | 2
[8 empty] | c) | - | c) |  | g) | Sept. 30, 2019 | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | Mugas - Lanatad |  |  | Road Rehabilitation | 1.53 | Admin | a) | 500000 | a) |  | e) | - | a) | 500000 | a) | - | c) | - | a) | - | On-going |  | 2
131 | [7 empty] | b) | Balbastro | b) | 8/5/2019 | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | Feb. 20, 2020 | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | New Katipunan - Pantaron |  |  | Road Rehabilitation | 1.96 | Admin | a) | 395000 | a) | 2019-03-12 | e) | - | a) | 395000 | a) | - | c) | - | a) | - |  |  | 2
134 | [7 empty] | b) | Gamad/Clar | b) | Dec. 27, 2019 | f) | - | b) | 395000 | b) | - | d) | - | b) | - | On-going |  | 2
[8 empty] | c) | - | c) | Feb. 25, 2020 | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | Fd. Rd. 2 - Sto. Tomas - Magwawa |  |  | Road Rehabilitation | 10.21 | Admin | a) | 3575000 | a) | June `19, 2019 | e) | - | a) | 3575000 | a) | 40% | c) | 40% | a) | - |  |  | 2
137 | [7 empty] | b) | Gamad/Clar | b) | Aug. 27, 2019 | f) | - | b) | 3575000 | b) | - | d) | - | b) | - | On-going |  | 2
[8 empty] | c) | - | c) | 2020-01-24 | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
[8 empty] | a.) 540,000.00 |  | a.) March 12, 2019 |  |  |  | a.) 540,000.00 |  | a.)100% |  | c.)100% |  |  |  | Completed |  | 2
|  | Nafco - Bobongon |  |  | Road Rehabilitation |  |  | b. Gamad |  | b.) march 18, 2019 |  |  |  | b.) 540,000.00 | [9 empty] | 2
[12 empty] | g.) June 30, 2019 | [11 empty] | 2
2
2
|  | Jct. Highway - Tanglaw |  |  | Road Rehabilitation | 3.98 | Admin | a) | 1100000 | a) | 2019-05-16 | e) | - | a) | 1100000 | a) | 85% | c) | 85% | a) | 10 | On going |  | 2
142 | [7 empty] | b) | Gamad/Clar | b) | 2019-06-17 | f) | 29 | b) | 1100000 | b) | - | d) | - | b) | 20 |  |  | 2
[8 empty] | c) | PEO | c) | Feb. 29, 2020 | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | Kimamon - Lunga-og - Talomo |  |  | Road Rehabilitation | 5.99 | Admin | a) | 1800000 | a) | 5/202019 | e) | - | a) | 1800000 | a) | 73.31% | c) | 73.31% | a) | 9 | on -going |  | 2
144 | [7 empty] | b) | Gamad | b) | 2019-06-17 | f) | - | b) | 1800000 | b) | - | d) | - | b) | 6 |  |  | 2
[8 empty] | c) | PEO | c) | Feb. 27, 2020 | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | Bdry. Tagum - Crossing Kinamayan Sto. Tomas |  |  | Road Rehabilitation | 0.75 | Admin | a) | 3700000 | a) | Dec. 6, 2019 | e) | - | a) | 3700000 | a) | - | c) | - | a) | - | On-going |  | 2
146 | [7 empty] | b) | Gamad/Clar | b) | Dec. 27, 2019 | f) | - | b) | 3700000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | 2020-04-25 | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | Prk. Narafil - Prk. Daisy Magupising |  |  | Road Rehabilitation | 19.16 | Admin | a) | 300117 | a) | 2019-06-25 | e) | - | a) | 300117 | a) | 100% | c) | 100% | a) | - | Completed |  | 2 | 4
148 | [7 empty] | b) | Gamad/Clar | b) | Sept. 16, 2019 | f) | - | b) | 300117 | b) | - | d) | - | b) | - |  |  | 2 | 4
[8 empty] | c) | - | c) | - | g) | Oct. 18, 2019 | c) | - | [8 empty] | 2 | 4
[8 empty] | d) | - | d) | - | [12 empty] | 2 | 4
2. Various of Local Roads & Drainage Development Project (Provincewide) |  |  |  |  | Road Drainage rehabiliated |  | Admin | a) | 15000000 | [12 empty] | See projects listed below |  | 2
[8 empty] | b) | Paraguya | [14 empty] | AC
[8 empty] | c) | PEO | [14 empty] | AC
[8 empty] | d) | - | [14 empty] | AC
At District 1
|  | Rehab./Impv't. of San Juan-New Talisay Provincial Road with Drainage |  |  | Road Drainage rehabiliated | - | Admin | a) | 1000000 | a) | Feb. 10, 2019 | e) | - | a) | 1000000 | a) | - | c) | 60$ | a) | - | On-going. |  | AC
2.1 | [7 empty] | b) | MJ | b) | - | f) | - | b) | 1000000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | PEO | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| 6 | Repair/Rehab. Of Concrete Road Jct. Suaon-Libuton, Kapalong |  |  | Road Drainage rehabiliated | - | Admin | a) | 1000000 | a) | 2019-07-03 | e) | - | a) | 1000000 | a) | - | c) | - | a) | - | For implementation Waiting for the availability of the backhoe |  | 1
2.2 | [7 empty] | b) | Aparece | b) | - | f) | - | b) | 1000000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| 1 | Impv't. of Cross Drainage along Saug-Sonlon-Bdry. Longanapan |  |  | Road Drainage rehabiliated | - | Admin | a) | 3000000 | a) | Feb. 10, 2019 | e) | - | a) | 3000000 | a) | - | c) | 58% | a) | - | Suspended from Nov. 18, 2019 to Jan 5, 2020.Resume jan. 6, 2020 |  | 1
2.3 | [7 empty] | b) | Bataller | b.) Aug. 1, 2019 | Aug. 1, 2019 | f) | - | b) | 3000000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| 8 | Rehab./Impv't. of Sto. Niño-Palma Gil-Sitio Opao Provincial Road with Drainage |  |  | Road Drainage rehabiliated | - | Admin | a) | 3000000 | a) | 2019-05-29 | e) | - | a) | 3000000 | a) | - | c) | - | a) | - | NTP not yet serve to Tagum Builders because they have not yet complied with the construction safety requirement |  | 1
2.4 | [7 empty] | b) | Lumapat | b) | - | f) | - | b) | 3000000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
|  | Rehab. of Anibongan-Salvacion-Cabay-angan Provincial Road with Drainage |  |  | Road Drainage rehabiliated | - | - | a) | 2000000 | a) | 2019-01-14 | e) | - | a) | 2000000 | a) | 100% | c) | 100% | a) | 1 | Completed |  | 1 | 4
2.1 | [7 empty] | b) | Toquero | b) | 2019-05-22 | f) | - | b) | 2000000 | b) | - | d) | - | b) | 4 | Fiancial obligation still on process |  | 2 | 4
[8 empty] | c) | PEO | c) | 2019-08-04 | g) | Dec. 31, 2019 | c) | - | [8 empty] | 2 | 4
[8 empty] | d) | - | d) | - | [12 empty] | 2 | 4
|  | Rehab. Of Dujali-Pawas-San Vicente Provincial Road |  |  | Road Drainage rehabiliated | - | - | a) | 1102900 | a) | Aug. 5, 2019 | e) | - | a) | 1102900 | a) | - | c) | - | a) | - | Project title was amended in the 2nd AIP revision deleting drainage. The project amount was reduced from P2,000,000.00 to P1,102,900.00 to fund new projects that was inlcuded in the AIP 3rd revision CY 2019 /SB No. 4 CY 2019 On. going |  | 2
2.2 | [7 empty] | b) | Toquero | b) | - | f) | - | b) | 1102900 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | PEO | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | Rehab./Impv't. of Jct. highway Ising-Magsaysay Provincial Road with Drainage |  |  | Road Drainage rehabiliated | - | - | a) | 1500000 | a) | Jan. 16, 2019 | e) | - | a) | 1500000 | a) | - | c) | - | a) | - | Revised POW for approval - Jan. 7, 2020 Revision was made due to scarcity of boulders changing from stone masonry to concrete masonry |  | 2
2.3 | [7 empty] | b) | Toquero | b) | - | f) | - | b) | 1500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | PEO | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | Rehab./Impv't. of Sto. Tomas-Bdry. Mamacao Provincial Road |  |  | Road Drainage rehabiliated | - | - | a) | 1500000 | a) | 2019-01-14 | e) | - | a) | 1500000 | a) | 100% | c) | 100% | a) | - | Completed Financial obligation on process |  |  | 4
2.4 | [7 empty] | b) | Toquero | b) | 2019-05-31 | f) | 60 | b) | 1500000 | b) | - | d) | - | b) | - |  |  | 2 | 4
[8 empty] | c) | PEO | c) | 2019-07-15 | g) | Dec. 31, 2019 | c) | - | [8 empty] | 2 | 4
[8 empty] | d) | - | d) | - | [12 empty] | 2 | 4
| SUPPLEMENTAL BUDGET NO. 4 CY 2019 | [22 empty] | AC
AC
[10 empty] | a.) Nov. 27, 2019 | [13 empty] | 2
| 2.5 | Rehab of Local Roads at Dalisay - Manay Road Section, | [19 empty] | Completed |  | 2
|  | Panabo City | [19 empty] | Financial obligation on process |  | 2
2
| 2.6 | Rehab. of Local Roads at Sta. Cruz- jct. Tagpore- Buenavista | [7 empty] | a.) Nov. 27, 2019 | [11 empty] | Completed |  | 2
|  | Road Section, panabo City | [19 empty] | Financial obligation on process |  | 2
2
| 2.7 | Rehab. of Local Roads at Taba - Bucana Road Section | [7 empty] | a.) | Nov. 27, 2019 | [10 empty] | Financial obligation on process |  | 2
2
2
3. Various Water System Development Project (Provincewide) |  |  |  |  | Water System projects | - | Admin | a) | 9750000 | [12 empty] | See projects listed below |  | 2
[8 empty] | b) | Medalla/Imboy | [14 empty] | AC
[8 empty] | c) | PEO | [14 empty] | AC
[8 empty] | d) | - | [14 empty] | AC
3.1 |  | Construction of Water System Projects | [21 empty] | AC
AC
| 6 | Construction of PWS, Bgry. Linao, San Isidro |  |  | Water System Projects | - | Admin | a) | 500000 | a) | 06/19/19 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For implementation |  | AC
3.1.1 | [7 empty] | b) | Aclaracion | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| 6 | Construction of PWS, Brgy. Datu Balong, San Isidro |  |  | Water System Projects | - | Admin | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For declaration of savings because the spring water source is not feasible for development |  | 1
3.1.2 | [7 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| 6 | Construction of PWS, Brgy. Sagayen, San Isidro |  |  | Water System Projects | - | Admin | a) | 500000 | a) | 2019-09-10 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Procurement on process |  | 1
3.1.3 | [7 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| 4 | Construction of PWS, Brgy. Purok 7-A and B, Brgy. Capungagan, kapalong |  |  | Water System Projects | - | Admin | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | The project was funded by OPAPP CY 2018. Fund re-aligned to new project Rehab. of Water System in PEEDO- LPRRC, Pob. New Corella (AIP 2nd revision CY 2019 |  | 1
3.1.4 | [7 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| 4 | Construction of PWS Purok 2, Brgy. Pag-Asa, kapalong |  |  | Water System Projects | - | Admin | a) | 800000 | a) | - | e) | - | a) | 800000 | a) | - | c) | - | a) | - | The project was funded by OPAPP CY 2018. Fund re-aligned and added to Construction of PWS in Brgy. Linosutan, kaputian Dist, IGACOS (AIP 2nd revision CY 2019) |  | 1
3.1.5 | [7 empty] | b) | - | b) | - | f) | - | b) | 800000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| 11 | Installation of Shallow Tube Wells & Const. of Machinery Shed |  |  | Water System Projects | - | Admin | a) | 1600000 | a) | - | e) | - | a) | 1600000 | a) | - | c) | - | a) | - | POW for review |  | 1
3.1.6 | [7 empty] | b) | - | b) | - | f) | - | b) | 1600000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
|  | Impv't. of Potable Water System, Consolacion, Panabo City |  |  | Water System Projects | - | - | a) | 500000 | a) | 2019-06-28 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Sched of bidding Dec 27, 2019 |  | 1
3.1.7 | [7 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | Impv't. of Potable Water System, Tagbitan-ag, Samal Dist. |  |  | Water System Projects | - | - | a) | 500000 | a) | 2019-06-19 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For implementation |  | 2
3.1.8 | [7 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | Impv't. of Potable Water System, San Antonio, babak, IGCS |  |  | Water System Projects | - | - | a) | 500000 | a) | 2019-06-25 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For implementation |  | 2
3.1.9 | [7 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | Impv't. of Potable Water System, Mambago-A, IGCS |  |  | Water System Projects | - | - | a) | 500000 | a) | Sept. 10, 2019 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | (Amended in the AIP 2nd Revision to change the location from Peñaplata to Samal District) For implementation |  | 2
3.1.10 | [7 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | Construction of PWS, Brgy. Buenavista, Panabo City |  |  | Water System Projects | - | - | a) | 500000 | a) | June 19 ,2019 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For implementation |  | 2
3.1.11 | [7 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | Construction of PWS, Brgy. Brgy. Kiotoy, Panabo City |  |  | Water System Projects | - | Contract | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Waiting for geo-resistivity equipment since the activity is drilling works |  | 2
3.1.12 | [7 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | Construction of PWS, Brgy. Linusotan, Talikud, District, IGCS |  |  | Water System Projects | - | - | a) | 500,000 + 800,000.00 | a) | Oct. 23, 2019 | e) | - | a) | 500,000 + 800,000.00 | a) | - | c) | - | a) | - | (Additional 800,000.00 from Const. of PWS in purok 2, Pag-asa, Kapalong which was funded by OPAPP CY 2018) (amended Sched of bidding Dec 27, 2019 |  | 2
3.1.13 | [7 empty] | b) | - | b) | - | f) | - | b) | 500,000 + 800,000.00 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | Rehab. of PWS, Brgy. San Miguel, Babak, IGCS |  |  | Water System Projects | - |  | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For amendment indicating phase 2 since the project title is the same with stimulus project and same amount. |  | 2
3.1.14 | [7 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | Construction of PWS, Brgy. Cacao, Panabo City |  |  | Water System Projects | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For cancellation. Purchase of Geo-resistivity equipment but procurement still on process |  | 2
3.1.15 | [7 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | Rehabilitation of Potable Water System, Brgy. Pangubatan, kaputian Dist. IGCS |  |  | Water System Projects | - |  | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For allotment June 24, 2019 |  | 2
3.1.16 | [7 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | Conduct of Geo-resistivity/drilling Test of Proposed Site |  |  | Geo-resistivity/drilling test conducted | - | - | a) | 250000 | [12 empty] | See projects listed below |  | 2
3.1 | [7 empty] | b) | - | [14 empty] | AC
[8 empty] | c) | - | [14 empty] | AC
[8 empty] | d) | - | [14 empty] | AC
|  | Construction of PWS, Brgy. Kiotoy, Panabo City |  |  | Geo-resistivity/drilling test conducted | - | - | a) | 62500 | a) | - | e) | - | a) | 62500 | a) | - | c) | - | a) | - | For cancellation due to the purchase of geo-resistivity equipment |  | AC
a. | [7 empty] | b) | - | b) | - | f) | - | b) | 62500 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | Construction of PWS, Brgy. Linosutan, Talikud, IGCS |  |  | Geo-resistivity/drilling test conducted | - | - | a) | 62500 | a) | - | e) | - | a) | 62500 | a) | - | c) | - | a) | - |  |  | 2
b. | [7 empty] | b) | - | b) | - | f) | - | b) | 62500 | b) | - | d) | - | b) | - | For cancellation due to the purchase of geo-resistivity equipment |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | Construction of PWS, Brgy. San Miguel, Samal, IGCS |  |  | Geo-resistivity/drilling test conducted | - | - | a) | 62500 | a) | - | e) | - | a) | 62500 | a) | - | c) | - | a) | - | For cancellation due to the purchase of geo-resistivity equipment |  | 2
c. | [7 empty] | b) | - | b) | - | f) | - | b) | 62500 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | Construction of PWS, Cacao, Panabo City |  |  | Geo-resistivity/drilling test conducted | - | - | a) | 62500 | a) | - | e) | - | a) | 62500 | a) | - | c) | - | a) | - |  |  | 2
d. | [7 empty] | b) | - | b) | - | f) | - | b) | 62500 | b) | - | d) | - | b) | - | For cancellation due to the purchase of geo-resistivity equipment |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
4. Various Government Buildings and Facilities Development Project (Provincewide) |  |  |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of recipients | - | Admin | a) | 27000000 | [12 empty] | See projects listed below |  | 2
[8 empty] | b) | Medalla | [14 empty] | AC
[8 empty] | c) | PEO | [14 empty] | AC
[8 empty] | d) | - | [14 empty] | AC
|  | Repair Bay of Disaster Quick Response Equipment @ PEO Compound, Gov't. Center, Mankilam, Tagum City |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of recipients | - | Admin | a) | 1000000 | a) | 2019-01-31 | e) | - | a) | 1000000 | a) | - | c) | 46.28% | a) | - | On-going |  | AC
| 11 | [6 empty] | b) | Azotes | b) | Oct. 16, 2019 | f) | - | b) | 1000000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
|  | Repair/Impv't. of Municipal Triball Hall, New Corella |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of recipients | - | Admin | a) | 1500000 | a) | - | e) | - | a) | 1500000 | a) | - | c) | - | a) | - | For allotment June 24, 2019 |  | 1
| 5 | [6 empty] | b) | - | b) | - | f) | - | b) | 1500000 | b) | - | d) | - | b) | - | PO on process |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
|  | Const. of GYM Bleacher at Suaybaguio Rina, Elem. School |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of recipients | - | Admin | a) | 1000000 | a) | - | e) | - | a) | 1000000 | a) | 100% | c) | 100% | a) | - | Completed |  | 1
| 11 | [6 empty] | b) | Mayang | b) | 6/3/2019 | f) | - | b) | 1000000 | b) | 64 | d) | 0% | b) | - |  |  | 1
[8 empty] | c) | PEO | c) | 8/01/2019 | g) |  | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
|  | Repair of Dacudao Health Center, Dacudao, San Isidro |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of recipients | - | Admin | a) | 1000000 | a) | - | e) | - | a) | 1000000 | a) |  | c) | 93.13% | a) | 5 | On going |  | 1
| 6 | [6 empty] | b) | Aclaracion | b) | - | f) | - | b) | 1000000 | b) | - | d) |  | b) | 110 |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
|  | Const. of Perimeter Fence at Sto. Niño NASECO Integrated School with Tugas Ext., Sto. Niño, Talaingod |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of recipients | - | Admin | a) | 1000000 | a) | - | e) | - | a) | 1000000 | a) | - | c) | - | a) | - | For implementation |  | 1
| 8 | [6 empty] | b) | - | b) | - | f) | - | b) | 1000000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
|  | Const. of Multi-Purpose Hall Center (Cultural Heritage in Ancestral Domain of Ata-Manobo) |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of recipients | - | Admin | a) | 3000000 | a) | - | e) | - | a) | 3000000 | a) | - | c) | - | a) | - | Fund re-aligned to GIDAS projects |  | 1
| 8 | [6 empty] | b) | - | b) | - | f) | - | b) | 3000000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | PEO | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
|  | Const. of IP Women's Multi-{Purpose Bldg.), Cabidiangan, Sto. Niño, Talaingod |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of recipients | - | Admin | a) | 2000000 | a) | 2019-05-15 | e) | - | a) | 2000000 | a) | - | c) | - | a) | - | For re-bidding |  | 1
| 8 | [6 empty] | b) | - | b) | - | f) | - | b) | 2000000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
|  | Extension of PAGRO Training Center & Ground Dev't., Gov't. Center, Mankilam, Tagum City |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of recipients | - | Admin | a) | 1000000 | a) | - | e) | - | a) | 1000000 | a) | - | c) | - | a) | - | For allotment- June 24,2019 Abstract on process
| 11 | [6 empty] | b) | - | b) | - | f) | - | b) | 1000000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | PEO | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
|  | Construction of Abilidad Training Center, Gov't. Center, Mankilam, Tagum City |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of recipients | - | Admin | a) | 7000000 | a) | - | e) | - | a) | 7000000 | a) | - | c) | - | a) | - | Fund re-aligned to GIDAS projects |  | 1
| 11 | [6 empty] | b) | - | b) |  | f) | - | b) | 7000000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
|  | Const. of 1 CL Bldg. @ Suawon ES, New Corella |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of recipients | - | Admin | a) | 1000000 | a) | - | e) | - | a) | 1000000 | a) | - | c) | - | a) | - | On-going |  | 1
[8 empty] | b) | - | b) | Nov. 19, 2019 | f) | - | b) | 1000000 | b) |  | d) | - | b) | - |  |  | 1
| 5 | [6 empty] | c) | PEO | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
|  | Const. of Municipal Tribal Hall, San Isidro |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of recipients | - | Admin | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For implementation |  | 1
| 6 | [6 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
|  | Const. of Quail House (PDNSC Ext. Campus), Sto. Niño, Talaingod |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of recipients | - | Admin | a) | 750000 | a) | - | e) | - | a) | 750000 | a) | - | c) | - | a) | - | On-going |  | 1
| 8 | [6 empty] | b) | - | b) | - | f) | - | b) | 750000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | PEO | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
|  | Completion of Perimeter Steel Fence @ Lunga-og E/S, Brgy. Lunga-og, Sto. Tomas |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of recipients | - | Admin | a) | 1630000 | a) | 01/17/19 | e) | - | a) | 1630000 | a) | - | c) | 46.28% | a) | - | On-going |  | 1
[8 empty] | b) | Azotes | b) | - | f) | - | b) | 1630000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | PEO | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | Const. of DDN Hospital Carmen Zone Annex Bldg. Phase 2, |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of recipients | - | Contract | a) | 3620000 | a) | 2019-06-28 | e) | - | a) | 3620000 | a) | - | c) | - | a) | - | For implementation |  | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 3620000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | Digos Constrak Corp/ | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
5. Stimulus Projects for Various Barangays a. 20% Development Fund CY 2019 |  |  |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | Admin | a) | 41500000 | [12 empty] | See projects listed below |  | 2
[8 empty] | b) | Medalla | [14 empty] | AC
[8 empty] | c) | PEO | [14 empty] | AC
[8 empty] | d) | - | [14 empty] | AC
AC
5.1 |  | Rehab. Of FMR at Prk. 1,3,4 & 7, Concepcion, Asuncion |  |  | Road Rehabilitation to cater the needs of brgys. | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Re-aligned to Const. of Children's Playground with Amenities at Pob. New Corella (AIP 3rd Revision CY 2019 / SB No. 4 CY 2019 |  | AC
| 1 | [6 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
5.2 |  | Rehab. Of Multi-Purpose Hall, New Bantayan, Asuncion |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | 35% | a) | - | Fund transferred to LGU on - going c /o Engr. Lilibeth Cuajao |  | 1
| 1 | [6 empty] | b) | - | b) | 2019-11-02 | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
1
NEW CORELLA
5.3 |  | Construction of Multi-Purpose Hall, El Salvador, New Corella |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) | 2019-05-23 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Fund transferred to LGU March 23, 2019 c/o Engr. Dugoldugol |  | AC
[8 empty] | b) | - | b) | 2019-09-16 | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
| 5 | [6 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
5.4 |  | Concreting of Drainage Canal , Pob., New Corella |  |  | Const. of Drainage Canal to cater the needs of brgys. | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Amended to Const. of 2 Storey Multi-Purpose Hall phase 3 (Brgy. Hall),Pob., New Corella (AIP 3rd revision CY 2019 / SB No. 4 CY 2019 |  | 1
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
| 5 | [6 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
5.5 |  | Rehab. Of Multi-Purpose Hall, Cabidianan, New Corella |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) | 02/20/19 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Fund transferred to LGU c/o Engr. Dugoldugol |  | 1
[8 empty] | b) |  | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
| 5 | [6 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
5.6 |  | Const. of Canal Lining, Limbaan, New Corella |  |  | Const. of Drainage Canal to cater the needs of brgys. | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Fund transferred to LGU c/o Engr. Dugoldugol Completed - Nov. 8, 2019 / PCR for submission |  | 1
[8 empty] | b) | - | b) | 2019-09-06 | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
| 5 | [6 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
1
TALAINGOD
5.7 |  | Brgy. Electrification (Centro Gupitan), Gupitan, Talaingod |  |  | Rural Electrification to cater the needs of brgys. | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Re-aligned to other stimulus projects that need additional funds to complete since the amount can not complete the project. Recommended for exact fund that can complete the project. |  | AC
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
| 8 | [6 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
TAGUM CITY
5.8 |  | Rehab. of Evacuation Center, Madaum, Tagum City |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | Admin | a) | 500000 | a) | 01/14/19 | e) | - | a) | 500000 | a) | 17.17% | c) | 17.17 | a) | - | On going |  | AC
| 11 | [6 empty] | b) | Juan, Z | b) | Nov. 18, 2019 | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | PEO | c) | Jan. 16, 2019 | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | 60 CD | d) | - | [12 empty] | 1
5.9 |  | Rehab. of Evacuation Center, Magugpo Poblacion, Tagum City |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. |  | Contract | a) | 500000 | a) |  | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Amended in the AIP 3rd revision CY 2019 /SB No. 4 CY 2019 changing the total project cost to P600,000.00 |  | 1
| 11 | [6 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
5.1 |  | Rehab. of Evacuation Center, New Balambam, Tagum City |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. |  | Contract | a) | 500000 | a) | 2019-09-10 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Procurement on process |  | 1
| 11 | [6 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
5.11 |  | Rehab. Of Multi-Purpose Hall, Cuambogan, Tagum City |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. |  | Contract | a) | 500000 | a) | 2019-09-10 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Procurement on process |  | 1
| 11 | [6 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
5.12 |  | Completion of Evacuation Center, Nueva Fuerza, Tagum City |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. |  | Contract | a) | 500000 | a) | 2019-09-10 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Procurement on process |  | 1
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
| 11 | [6 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
5.13 |  | Const. of Water System, San Agustin, Tagum City |  |  | Const. of Water System to cater the needs of brgys. | - | Contract | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Re-aligned to other stimulus projects that need additional funds since there is no deed of donation for the proposed site. |  | 1
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
| 11 | [6 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
5.14 |  | Const. of Brgy. Health Center, Magugpo South, Tagum City |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Amended in the AIP 3rd revision CY 2019 /SB No. 4 CY 2019 changing the total project cost to P1,550,000.00 |  | 1
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
| 11 | [6 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
5.15 |  | Const. of Women Livelihood Center, San Isidro, Tagum City |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) | 2019-05-29 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | On -going |  | 1
[8 empty] | b) | - | b) | Jan. 2, 2020 | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
| 11 | [6 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
5.16 |  | Completion. of Water System , Busaon, Tagum City |  |  | Const. of Water System to cater the needs of brgys. |  | Contract | a) | 500000 | a) | Sept. 10, 2019 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Procurement on process |  | 1
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
| 11 | [6 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
5.17 |  | Rehab. Of Brgy. Health Center, Apokon, Tagum City |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | admin | a) | 500000 | a) | 2019-03-25 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For implementation (The brgy. council agreed not to pursue with the project if it will not be completed and needs additional funds) |  | 1
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
| 11 | [6 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
5.18 |  | Const. of Drainage Canal, Bincungan, Tagum City |  |  | Const. of Drainage Canal to cater the needs of brgys. |  | Contract | a) | 500000 | a) | Sept. 10, 2019 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Procurement on process |  | 1
| 11 | [6 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
5.19 |  | Rehab. of Evacuation Center, Mankilam, Tagum City |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) | 2019-03-25 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For implementation |  | 1
| 11 | [6 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
|  | Rehab. of Evacuation Center, Magugpo North, Tagum City |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. |  | Contract | a) | 500000 | a) | Sept. 10, 2019 | e) | - | a) | 500000 | a) | - | c) | - | a) |  | Procurement on process |  | 1
5.2 | 11 | [6 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
1
SAN ISIDRO
|  | Rehab. Of Multi-Purpose Hall , Sto. Niño, San Isidro |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | Admin | a) | 500000 | a) | 02/20/19 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | POW was revised to increase the cost for windows and approved Dec. 6, 2019 PR on process |  | AC
5.21 | 6 | [6 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
|  | Rehab. Of Water System at Purok Cabang & Mangga , Pinamuno, San Isidro |  |  | Const. of Water System to cater the needs of brgys. |  | Contract | a) | 500000 | a) | Dec. 6, 2019 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Sched. Of bidding Dec. 27, 2019 |  | 1
5.22 | 6 | [6 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
|  | Rehab. Of Water System , Igangon, San Isidro |  |  | Const. of Water System to cater the needs of brgys. | - | - | a) | 500000 | a) | 2019-05-29 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For implementation |  | 1
5.23 | 6 | [6 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
1
CARMEN |  |  |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys.
5.1 |  | Const. of Multi-Purpose Hall, La Paz, Carmen |  |  |  | - | - | a) | 500000 | a) | 02/20/19 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Fund transferred to LGU March 28, 2019 |  | AC
[8 empty] | b) | - | b) | Aug. 16, 2019 | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
5.2 |  | Const. of Evacuation Center Ph. 3, Sto. Niño, Carmen |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Amended in the AIP 3rd revision CY 2019/ SB No. 4 CY 2019 changing the location to Purok !-c, Sto. Nino since the previous location was implemented by DPWH |  | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
5.3 |  | Const. of Multi-Purpose Hall, Mangalcal, Carmen |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) | 02/20/19 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Fund transfer to LGU Carmen, 3/28/2019 with check no. 2574953 and OR no. 0118982 |  | 2
[8 empty] | b) | - | b) | Sept. 16, 2019 | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
5.4 |  | Rehab. of Multi-Purpose Hall, Guadalupe, Carmen |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) | 02/20/19 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Fund transferred to LGU March 28, 2019 |  | 2
[8 empty] | b) | - | b) | 8/15/2019 | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | 11/13/2019 | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
5.5 |  | Const. of Multi-Purpose Hall, Mabuhay, Carmen |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) | 02/20/19 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Fund transfer to LGU Carmen, 3/28/2019 with check no. 2574925 and OR no. 0118984 |  | 2
[8 empty] | b) | - | b) | Aug. 16, 2019 | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
5.6 |  | Const. Canal Lining , Mabaus, Carmen |  |  | Const. of Canal Lining to cater the needs of brgys. | - | - | a) | 500000 | a) | 02/20/19 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Fund transferred to LGU March 28, 2019 |  | 2
[8 empty] | b) | - | b) |  | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) |  | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
5.7 |  | Rehab. Of Evacuation Center, Alejal, Carmen |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) | 02/20/19 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Fund transfer to LGU Carmen, 3/28/2019 with check no.2574949 and OR no. 0118991 |  | 2
[8 empty] | b) | - | b) | Aug. 16, 2019 | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
5.8 |  | Compl. Of Evacuation Center, Tuganay, Carmen |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) | 02/20/19 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Fund transfer to LGU Carmen, 3/28/2019 with check no. 2574947 and OR no. 0118995 |  | 2
[8 empty] | b) | - | b) | Aug. 16, 2019 | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
5.9 |  | Const. of Multi-Purpose hall, Ising, Carmen |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) | 02/20/19 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Fund transferred to LGU March 28, 2019 |  | 2
[8 empty] | b) | - | b) |  | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
5.1 |  | Rehab. of Multi-Purpose hall, Cebulano, Carmen |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) | 02/20/19 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Fund transferred to LGU March 28, 2019 |  | 2
[8 empty] | b) | - | b) | Aug. 16, 2019 | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
2
PANABO CITY
5.11 |  | Rehab. Of Multi-Purpose Hall, Kasilak, Panabo City |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Amended in AIP 3rd revison CY 2019/ SB No. 4 CY 2019 increasing the project cost to P650,000.00 |  | AC
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
5.12 |  | Rehab. Of Multi-Purpose Hall, New Malitbog, Panabo City |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Amended in AIP 3rd revsion CY 2019 to change the project to Construction of Potable Water System because the original project will be funded by LGU, Panabo City (Brgy. resolution no. 25 series of 2019 dated Aug. 13, 2019 submitted) |  | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
2
[8 empty] | d) | - | d) | -
5.13 |  | Desilting of Canal, New Pandan, Panabo City |  |  | Const. of Drianage Canal to cater the needs of brgys. | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For re inspection to add length for desilting c/o Engr. Canillada Plan prepared can not consume the allocated amount of P500,000.00 for desilting works. |  | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
5.14 |  | Const. Of Multi-Purpose Hall, Waterfall, Panabo City |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For allotment. Sept. 27, 2019 |  | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
5.15 |  | Concreting of Brgy. Road @ Prk. Guyabano, Cagangohan, Panabo City |  |  | Road Concreting to cater the needs of brgys. | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Amended in AIP 3rd revision to change the project to Rehab of Evacuation Center because the original project has no deed of donation.(Brgy. resolution no 41 series of 2019 dated Aug. 16, 2019 submitted |  | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
2
[8 empty] | d) | - | d) | -
5.16 |  | Rehab. Of Evacuation Center, J.P. Laurel, Panabo City |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) | Oct. 23, 2019 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Sched. Of bidding Dec. 27, 2019 |  | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
5.17 |  | Const. Of Multi-Purpose Hall, Buenavista, Panabo City |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) | Oct. 18, 2019 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Sched. Of bidding Dec. 27, 2019 |  | 2
[8 empty] | b) | - | b) | - | f) |  | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
5.18 |  | Rehab. Of Multi-Purpose Hall, San Francisco, Panabo City |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) | Oct. 18, 2019 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Sched. Of bidding Dec. 27, 2019 |  | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) |  | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
-
5.19 |  | Rehab. Of Evacuation Center, Datu Abdul Dadia, Panabo City |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) | Oct. 18, 2019 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Sched. Of bidding Dec. 27, 2019 |  | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
5.2 |  | Impv't./Beautification of Brgy. Grounds, Quezon, Panabo City |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Re aligned to other stimulus projects that needs additional funding |  | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
5.21 |  | Const. of Women Livelihood Center Bldg. , Gredu, Panabo City |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) | 2019-03-28 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Fund transfer to LGU - 3/28/2019 with check no. 2574926 and OR no. 0166517 - March 28, 2019 |  | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
5.23 |  | Const. of Canal Lining at Purok 5, Salvacion, Panabo City |  |  | Const. of Drainage Canal to cater the needs of brgys. | - | - | a) | 500000 | a) | Oct. 18, 2019 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Procurement on process |  | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
5.24 |  | Rehab. Of Health Center, New Visayas, Panabo City |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Re aligned to other stimulus projects that needs additional funding |  | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
5.25 |  | Rehab. Of Multi-Purpose Hall, Little Panay, Panabo City |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For allotment Dec. 11, 2019 |  | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
5.26 |  | Rehab. Of Brgy. Health Center, Dalisay, Panabo City |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For allotment Dec. 4, 2019 |  | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
5.27 |  | Const. of Multi-Purpose Hall, Southern Davao, Panabo City |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For allotment Dec. 3, 2019 |  | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) |  | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
2
-
STO. TOMAS
5.28 |  | Rehab. Of Evacuation Center, Casig-ang, Sto. Tomas |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | POW preparation on-going c/o Engr. Uy |  | AC
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
5.29 |  | Const. of Brgy. Tibal-og Health Center, Tibal-og, Sto. Tomas |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | POW preparation completed amounting t oP1,550,000.00. To request for additional funds in order to complete the project to be functional |  | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - |  | Nov. 30, 2019 | [10 empty] | 2
5.3 |  | Compl.of Brgy. Public Market, La Libertad, Sto. Tomas |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) |  | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Fund transfer to LGU - 6/26/219 with check no. 2575131 and OR no. 0557457 Completed/ PCR for submission by LGU |  | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
5.31 |  | Rehab. Of Evacuation Center, New Visayas, Sto. Tomas |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) |  | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Fund transfer to LGU - 6/26/219 with check no. 2575132 and OR no. 0557455 For implementation |  | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
5.32 |  | Rehab. Of Multi-Purpose Hall, San Vicente, Sto. Tomas |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Fund transferred to LGU July 5, 2019 On -going |  | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) |  | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - |  | - | [10 empty] | 2
5.33 |  | Rehab. Of Multi-Purpose Hall, Salvacion, Sto. Tomas |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Amended in AIP 3rd revision CY 2019 /SB No. 4 CY 2019increasing the project cost to P1,000,000.00 |  | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
5.34 |  | Rehab. Of Multi-Purpose Hall, Pantaron, Sto. Tomas |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) |  | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Amended in AIP 3rd revision CY 2019 / SB No. 4 CY 2019 increasing the project cost to P550,000.00 |  | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
5.35 |  | Rehab. Of Multi-Purpose Hall, Magwawa, Sto. Tomas |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | Contract | a) | 500000 | a) | June 19 2019 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Procurement on process |  | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
5.36 |  | Compl. Of Multi-Purpose Hall, San Jose, Sto. Tomas |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) |  | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Amended in AIP 3rd revision CY 2019 / SB No. 4 CY 2019 increasing the project cost to P600,000.00 |  | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
5.37 |  | Const. of Evacuation Center, Bobongon, Sto. Tomas |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Re aligned to other stimulus projects that needs additional funding |  | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
5.38 |  | Rehab. Of Brgy. Road, Lunga-og, Sto. Tomas |  |  | Road Rehabilitation to cater the needs of brgys. | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Amended in AIP 3rd revision CY 2019 / SB No. 4 CY 2019 increasing the project cost to P600,000.00 |  | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
5.39 |  | Rehab. Of Multi-Purpose Hall, New Katipunan, Sto. Tomas |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | Contract | a) | 500000 | a) | 2019-06-07 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Procurement on process |  | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
5.4 |  | Rehab. Of Multi-Purpose Hall, San Miguel, Sto. Tomas |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | Contract | a) | 500000 | a) | 2019-06-07 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Procurement on process |  | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
5.41 |  | Rehab. Of Multi-Purpose Hall, Talomo, Sto. Tomas |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Fund transfer to LGU - 6/26/2019 with check no. 2575130 and OR no. 0557456 For implementation |  | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
IGCS | [23 empty] | 2 | 4
5.42 |  | Rehab. Of Health Center, Aumbay, IGCS |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) | Feb. 28, 2019 | e) | - | a) | 500000 | a) |  | c) | 48.32% | a) | 3 | Completed Financial obligation on process |  | AC | 4
[8 empty] | b) | Pacquiao | b) | 7/10/2019 | f) | - | b) | 500000 | b) | - | d) |  | b) | 15 |  |  | 2 | 4
[8 empty] | c) | Admin | c) | 10/7/2019 | g) | - | c) | - | [8 empty] | 2 | 4
[8 empty] | d) | 90 CD | d) | - | [12 empty] | 2 | 4
5.43 |  | Concreting of Brgy. Road From Prk. 3 to Prk. 5, Catagman, IGCS |  |  | Road Concreting to cater the needs of brgys. | - | Contract | a) | 500000 | a) | Jan. 14, 2019 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For implementation |  | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
5.44 |  | Rehab. Of Multi-Purpose Hall, San Jose, IGCS |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | Admin | a) | 500000 | a) | 2019-03-25 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | On- going |  | 2
[8 empty] | b) | Pacquiao | b) | Jan. 2, 2019 | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
5.45 |  | Elctrification at Sitio Trinidad, Bandera, IGCS |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) | 2019-03-25 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Procurement on process |  | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
5.46 |  | Rehab. Of Brgy. Health Center, Mambago-A, IGCS |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) | Feb. 28, 2019 | e) | - | a) | 500000 | a) |  | c) | 75.61% | a) | 3 | Completed Financial obligation on process |  | 2 | 4
[8 empty] | b) | Ganaba | b) | 07/2019 | f) | - | b) | 500000 | b) |  | d) |  | b) | 15 |  |  | 2 | 4
[8 empty] | c) | Admin | c) | 8/23/2019 | g) | - | c) | - | [8 empty] | 2 | 4
[8 empty] | d) | 45 CD | d) | - | [12 empty] | 2 | 4
5.47 |  | Rehab. Of Multi-Purpose Hall, Del Monte, IGCS |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | Admin | a) | 500000 | a) | 2019-05-29 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Pending/ activity undertaken by DPWH |  | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
5.48 |  | Rehab. Of Multi-Purpose Hall, Aundanao, IGCS |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | Admin | a) | 500000 | a) | 2019-03-18 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | On -going |  | 2
[8 empty] | b) | Porras | b) | Nov. 18, 2019 | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
5.49 |  | Electrification at Upper Purok Rosal, Tagbaobo, IGCS |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Procurement on process. No Abastract |  | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
5.5 |  | Const. Of Multi-Purpose Hall, Mambago-B, IGCS |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For implementation |  | 2
[8 empty] | b) | Roque | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
5.51 |  | Const. Of Multi-Purpose Hall, San Antonio, IGCS |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) | 2019-06-19 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For implementation |  | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
5.52 |  | Concreting of Brgy. Road from Prk. 1 to Prk. 2, Villarica, ICGS |  |  | Road Concreting to cater the needs of brgys. | - | Contract | a) | 500000 | a) | Jan. 14, 2019 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For implementation |  | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
5.53 |  | Rehab. Of Water System Intake Box and Pipeline, Pangubatan, IGCS |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Plan and Pow completed. Waiting of deed of donation |  | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
5.54 |  | Const. Of Multi-Purpose Hall, Cogon (Talicud), IGCS |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Procurement on process. For rebidding Dec. 12, 2019 |  | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
5.55 |  | Installation of Pipelines, Libertad, IGCS |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) | 2019-03-25 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For implementation |  | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
5.56 |  | Rehab. Of Evacuation Center, Libuak, IGCS |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) | 2019-05-29 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For implementation |  | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
5.57 |  | Const. of Water System Project, Pob. Kaputian, IGCS |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | for Allotment |  | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
2
5.58 |  | Rehab. Of Potable Water System, San Isidro, Babak, IGCS |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) | 2019-06-19 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For implementation
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) |  | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
5.59 |  | Rehab. Of Potable Water System, San Miguel, IGCS |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) | Feb. 28, 2019 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For implementation |  | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
5.6 |  | Const. of Water System Ph.II, San Remegio, IGCS |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) | 2019-05-29 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For implementation |  | 2
[8 empty] | b) | Porras | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | Admin | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
5.61 |  | Electrificatio at Prk. 1,3,4, 6,7 & 8, Licup, IGCS |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) | 02/20/19 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Procurement of materials on process |  | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
6. Rural Electrification Project (Provincewide) |  |  |  |  | Powerlines/posts installed & rehabilitated | - | - | a) | 5000000 | [12 empty] | See projects listed below |  | 2
[8 empty] | b) | Kim Pao Lu | [14 empty] | AC
[8 empty] | c) | - | [14 empty] | AC
[8 empty] | d) | - | [14 empty] | AC
|  | Rural Electrification , Del Monte, New Corella |  |  | Powerlines/posts installed & rehabilitated | - | - | a) | 3000000 | a) | - | e) | - | a) | 3000000 | a) | - | c) | - | a) | - | For implementation |  | AC
[8 empty] | b) | P.Bueno | b) | - | f) | - | b) | 3000000 | b) | - | d) | - | b) | - |  |  | 1
6.1 | 5 | [6 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
|  | Rural Electrification at St. Bundok, San Roque, New Corella |  |  | Powerlines/posts installed & rehabilitated | - | - | a) | 1000000 | a) | - | e) | - | a) | 1000000 | a) | - | c) | - | a) | - | For allotment- Dec. 3, 2019 |  | 1
[8 empty] | b) | P.Bueno | b) | - | f) | - | b) | 1000000 | b) | - | d) | - | b) | - |  |  | 1
6.2 | 5 | [6 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
|  | Rural Electrification at Pob. Kaputian, (St. Sagrada) IGCS |  |  | Powerlines/posts installed & rehabilitated | - | - | a) | 1000000 | a) | - | e) | - | a) | 1000000 | a) | - | c) | - | a) | - | Procurement on process |  | 1
[8 empty] | b) | P.Bueno | b) | - | f) | - | b) | 1000000 | b) | - | d) | - | b) | - |  |  | 2
6.3 | 10 | [6 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
2
C. 5% CALAMITY FUND CY 2019 | [23 empty] | AC
1 |  | Desiltation/Excavation of rivers and creeks |  |  | creeks and canals deislted | - | - | a) | 3000000 | [12 empty] | See project listed below |  | FS
[8 empty] | b) | Paraguya | [14 empty] | AC
[8 empty] | c) | PEO | [14 empty] | AC
[8 empty] | d) | - | [14 empty] | AC
|  | 1.1 | Desilting of Limbaan Creek, New Corella |  | creeks and canals deislted | - | - | a) | 2000000 | a) | - | e) | - | a) | 2000000 | a) | - | c) | - | a) | - | POW preparation on going |  | AC
| 5 | [6 empty] | b) | - | b) | - | f) | - | b) | 2000000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
1
a. |  | Desiltation of Mactan River Ph. II |  |  | creeks and canals deislted | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | on-going |  | 1
[8 empty] | b) | Toquero | b) | 7/29/2019 | f) | - | b) | 500000 | b) | - | d) | - | b) | - | TIME EXTENSION PROCESS |  | 1
[8 empty] | c) | Admin | c) | 9/27/2019 | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | 60 C.D | d) | - | [12 empty] | 1
2 |  | Revitment of Dike and Slope Proection |  |  | Protection dikes/slope protection | - | - | a) | 3000000 | [12 empty] | See projects listed below |  | AC
[8 empty] | b) | - | [14 empty] | AC
[8 empty] | c) | - | [14 empty] | AC
[8 empty] | d) | - | [14 empty] | AC
|  | 2.1 | Slope Protection Along Kapalong-Mabantao, Florida |  | creeks and canals deislted | - | - | a) | 1000000 | a) | - | e) | - | a) | 1000000 | a) | - | c) | - | a) | - | For cancellation funded to DPWH. Budget Transferred to |  | AC
| 4 | [6 empty] | b) | - | b) | - | f) | - | b) | 1000000 | b) | - | d) | - | b) | - | 5% Calamity Fund- Rehab and Recovery |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
b. |  | Repair/Rehab. Of Upper Tuganay Dike |  |  | creeks and canals deislted | - | - | a) | 1000000 | a) | - | e) | - | a) | 1000000 | a) | - | c) | - | a) | - | ON-GOING |  | 1
[8 empty] | b) | Toquero | b) | 8/19/2019 | f) | - | b) | 1000000 | b) | - | d) |  | b) | - | TIME EXTENSION PROCESS |  | 2
[8 empty] | c) | Admin | c) | 9/29/2019 | g) |  | c) | - | [8 empty] | 2
[8 empty] | d) | 59 C.D | d) | - | [12 empty] | 2
3 |  | Improvement of roads, drainage and canal |  |  | Protection dikes/slope protection | - | - | a) | 3000000 |  |  |  | - | [8 empty] | See projects listed below |  | 2
[8 empty] | b) | Paraguya | [14 empty] | AC
[8 empty] | c) | PEO | [14 empty] | AC
[8 empty] | d) | - | [14 empty] | AC
a. |  | Rehab./Impv't. of New Casay-Bugtong Talisay Provincial Road (Ph.II) |  |  | creeks and canRoads/Draiange/canals rehab/improved | - | - | a) | 500000 | a) | 2019-03-12 | e) |  | a) | 500000 | a) | 100% | c) | 100% | a) | 12 | Completed |  | AC
[8 empty] | b) | Toquero | b) | 2019-05-30 | f) |  | b) | 500000 | b) | - | d) | - | b) | 120 |  |  | 2
[8 empty] | c) | Admin | c) | 2019-07-30 | g) | 7/30/2019 | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
b. |  | Rehab./Impv't. of Prk. 1 - Prk. 2 Sitio Pawas Provincial Road |  |  | creeks and canRoads/Draiange/canals rehab/improved | - | - | a) | 1500000 | a) | 7/23/2019 | e) | - | a) | 1500000 | a) | 17.14% | c) | 1.18% | a) | 2 |  |  | 2
[8 empty] | b) | Sanchez | b) | 8/05/2019 | f) |  | b) | 1500000 | b) | - | d) | -15.96% | b) | 10 | On-going |  | 2
[8 empty] | c) | Admin | c) | 9/28/2019 | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | 55 | d) | - | [12 empty] | 2
c. |  | Repair/Rehab of Drainage System & Ground Gravelling at Kimamon NHS |  |  | creeks and canRoads/Draiange/canals rehab/improved | - | - | a) | 464833 | a) | - | e) | - | a) | 464833 | a) |  | c) | [5 empty] | 2
[8 empty] | b) | Azotes | b) | - | f) | - | b) | 464833 | b) |  | d) | [5 empty] | 2
[8 empty] | c) | Admin | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
2
4 |  | Improvement of bridges and cross drainage |  |  | bridge and cross drainage rehab./improved # of sq.m riprapped, culverts replaced | - | - | a) | 3000000 | [12 empty] | See projects listed below
[8 empty] | b) | Paraguya | [14 empty] | AC
[8 empty] | c) | PEO | [14 empty] | AC
[8 empty] | d) | - | [14 empty] | AC
|  | 4.1 | Impv't. of Jct. New Boholano - New Loon Cross Drainage |  | creeks and canRoads/Draiange/canals rehab/improved | - | - | a) | 2000000 | a) | - | e) | - | a) | 2000000 | a) | - | c) | - | a) | - | POW preparation on going c/o PEO-PDPM. Insufficient budget to complete required works for the project |  | AC
| 1 | [6 empty] | b) | - | b) | - | f) | - | b) | 2000000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
|  | 4.2 | Impv't. of Jct. Saug-Sonlon-Bdry. Longanapan Cross Drainage |  | creeks and canRoads/Draiange/canals rehab/improved |  | - | a) | 1000000 | a) | - | e) | - | a) | 1000000 | a) | - | c) | - | a) | - | Waiting for the delivery of Materials |  | 1
| 1 | [6 empty] | b) | - | b) | - | f) | - | b) | 1000000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
D. | SUPPLEMENTAL BUDGET NO. 1 CY 2019 | [22 empty] | AC
| 8918/Purchase / Const. / Compl./ Imprvt. Of Various Gov'y Bldgs, Structures & Facilities - General Fund Proper | [22 empty] | FS
| ■ | Purchase of Lot for Cemetery, Cambanogoy, Asuncion |  |  | Land |  | - | a) | 1500000 | a) | - | e) | - | a) | 1500000 | a) | - | c) | - | a) | - | Documents for fund transfer to be complied by the LGUs. Letter sent dated June 18, 2019 |  | AC
| 1 | [6 empty] | b) | - | b) | - | f) | - | b) | 1500000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| ■ | Purchase of Lot for Cemetery, San Roque, New Corella |  |  | Land |  | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Documents for fund transfer to be complied by the LGUs. Letter sent dated June 18, 2019 |  | 1
| 5 | [6 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| 8918/Stimulus Projects for Various Barangays. Const. in Progress - Bldgs & Other Structure | [22 empty] | 1
| ■ | Rehab/Impvt of Gymnasium, Sagayen, Asuncion |  |  | Bldg |  | - | a) | 1500000 | a) | - | e) | - | a) | 1500000 | a) | - | c) | - | a) | - | for allotment - Sept 19, 2019 |  | AC
| 1 | [6 empty] | b) | - | b) | - | f) | - | b) | 1500000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| ■ | Installation of Bleacher for the Brgy. Gym, Concepcion, Asuncion |  |  | Bldg |  | - | a) | 1000000 | a) | - | e) | - | a) | 1000000 | a) | - | c) | 30% | a) | - | On-going |  | 1
| 1 | [6 empty] | b) | - | b) | - | f) | - | b) | 1000000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
LOCALLY FUDNDED PROGRAM/PROJECT - 20% Development Fund
| Infrastructure Development Program | [22 empty] | AC
| 8918/ Stimulus Projects for Various Barangays | [22 empty] | AC
| Property, Plant and Equipment - Land | [22 empty] | AC
| ■ | Purchase of Lot for Resettlement Site, New Sambog, New Corella |  |  | Land |  | - | a) | 1500000 | a) | - | e) | - | a) | 1500000 | a) | - | c) |  | a) | - | for fund transfer. Waiting for LGU documents. Liquidation of previous fund transfer for the water system project of LGU. |  | AC
| 5 | [6 empty] | b) | - | b) | - | f) | - | b) | 1500000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| Property, Plant and Equipment - Construction in Progress-Infrastructure Assets | [22 empty] | 1
| ■ | Installation of Street Lights at Prk 1,2,3,4, Sagayen, Asuncion |  |  | Electrification |  | - | a) | 1000000 | a) | - | e) | - | a) | 1000000 | a) | - | c) |  | a) | - | PO on process |  | AC
| 1 | [6 empty] | b) | - | b) | - | f) | - | b) | 1000000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
1
| ■ | Rehab/Imprvt. Of FMR, Prk 3,7, & 8, Concepcion, Asuncion |  |  | Road |  | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) |  | a) | - | Procurement of Materials on process
| 1 | [6 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| ■ | Rural Electrification Project, Purok 6, Concepcion, Asuncion |  |  | Electrification |  | - | a) | 1000000 | a) | - | e) | - | a) | 1000000 | a) | - | c) |  | a) | - | . Re-aligned Fund allocation to Construction of Children Playground withAmenities at Pob., New Corella |  | 1
| 1 | [6 empty] | b) | - | b) | - | f) | - | b) | 1000000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| ■ | Concreting of FMR, New Santiago, Asuncion |  |  | Road |  | - | a) | 2500000 | a) | 2019-05-21 | e) | - | a) | 2500000 | a) | - | c) | 30% | a) | - | Fund transferred to LGU |  | 1
| 1 | [6 empty] | b) | - | b) | - | f) | - | b) | 2500000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| ■ | Rural Electrification Project, Purok 5-8, Napungas, Asuncion |  |  | Electrification |  | - | a) | 1500000 | a) | - | e) | - | a) | 1500000 | a) | - | c) | - | a) | - | . Re-aligned Fund allocation to Construction of Children Playground withAmenities at Pob., New Corella |  | 1
| 1 | [6 empty] | b) | - | b) | - | f) | - | b) | 1500000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| ■ | Farm to Market Road, San Jose, New Corella |  |  | Road |  | - | a) | 2000000 | a) | - | e) | - | a) | 2000000 | a) | - | c) | - | a) | - | Plan Preparation on process c/o PDPM |  | 1
| 5 | [6 empty] | b) | - | b) | - | f) | - | b) | 2000000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| ■ | Const. of Water System, New Sambog, New Corella |  |  | Water System Projects |  | - | a) | 1000000 | a) | - | e) | - | a) | 1000000 | a) | - | c) | - | a) | - | Fund transferred to LGU
| 5 | [6 empty] | b) | - | b) | - | f) | - | b) | 1000000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| ■ | Const. of Drainage Canal from Prk. 3, 1-A, 2-A to Prk 1-B, Brgy Site (Ph. 2), Limbaan, New Corella |  |  | Flood Control - Drainage |  | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | POW preparation on going c/o PDPM |  | 1
| 5 | [6 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| ■ | Const. of FMR from Prk 1 to Sitio Magsaysay via Pundol & Prk 4, Patrocenio, New Corella |  |  | Road |  | - | a) | 2000000 | a) | - | e) | - | a) | 2000000 | a) | - | c) | - | a) | - | POW preparation on going c/o PDPM |  | 1
| 5 | [6 empty] | b) | - | b) | - | f) | - | b) | 2000000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) |  | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| ■ | Const. of Multi-Purpose Pavement, San Jose, New Corella |  |  | Bldgs |  | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | POW approved but allotment not yet requested waiting for deed of donation c/o Engr. Canillada
| 5 | [6 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| Const. in Progress - Bldgs & Other Structures | [22 empty] | 1
| ■ | Rehab/Impvt of Multi-Purpose Bldg, SCFA, Napungas, Asuncion |  |  | Bldgs |  | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Fund re-aligned to fund stimulus projects that need additional funding. ( AIP 3rd revision CY 2019) |  | AC
| 1 | [6 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
1
| ■ | Const. of Multipurpose Covered Court, Buan, Asuncion |  |  | Bldgs |  | - | a) | 2500000 | a) | 2019-06-26 | e) | - | a) | 2500000 | a) | - | c) | - | a) | - | Fund transferred to LGU
| 1 | [6 empty] | b) | - | b) | - | f) | - | b) | 2500000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| ■ | Const. of Multipurpose Covered Court, Pamacaun, Asuncion |  |  | Bldgs |  | - | a) | 2500000 | a) | 2019-05-29 | e) | - | a) | 2500000 | a) | - | c) | 30% | a) | - | Fund transferred to LGU |  | 1
| 1 | [6 empty] | b) | - | b) | - | f) | - | b) | 2500000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| ■ | Const. of 2 Storey Multipurpose Hall Ph.2 (Brgy. Hall) , Poblacion, New Corella |  |  | Bldgs |  | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Plan preparation on -going c/o PDPM |  | 1
| 5 | [6 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| ■ | Rehab. Of Multi-Purpose Hall (Evacuation Ctr.) Limbaan, New Corella |  |  | Bldgs |  | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For allotment - Nov. 5, 2019
| 5 | [6 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) |  | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| ■ | Expansion of Multi-Purpose Hall ( Brgy. Hall), Patrocenio, New Corella |  |  | Bldgs |  | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Sched of bidding Dec 27 , 2019 |  | 1
| 5 | [6 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
MOOE 2019 | [9 empty] | a) |  | e) |  | a) |  | a) |  | c) |  | a) |  | For approval of POW and Plan |  | 1
|  | Repair maintenance of OPD, Pharmacy building, DDNH - CZ Compound |  |  | Renovation | - | - | a) | 100000 | b) |  | f) |  | b) |  | b) |  | d) |  | b) |  |  |  | AC
[8 empty] | b) | Estorco | c) |  | g) |  | c) | [9 empty] | 2
[8 empty] | c) | Admin | d) | [13 empty] | 2
[8 empty] | d) | - | [14 empty] | 2
E. | SUPPLEMENTAL BUDGET NO. 3 CY 2019
| LOCALLY FUNDED PROGRAM/PROJECTS- 20% DEVELOPMENT FUND | [22 empty] | FS
| INFRASTRUCTURE DEVELOPMENT PROGRAM | [22 empty] | AC
| 8918/ Various Local Roads & Drainage Development Project Construction in Progress- Infrastructure Assets | [22 empty] | AC
| ■ | Rehabilitation of Dujali-Pawas-San Vicente Provincial Road, B.E. Dujali |  |  | Road |  | - | a) | 2000000 | a) | - | e) | - | a) | 2000000 | a) | - | c) | - | a) | - | The amount was reduced to P1,102,900.00 |  | AC
[8 empty] | b) | - | b) | - | f) | - | b) | 2000000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
| ■ | Repair/Rehabil;itation of Concrete R.d. Jct. Suaon-Libuton Kapalong |  |  | Road |  | - | a) | 1000000 | a) | - | e) | - | a) | 1000000 | a) | - | c) | - | a) | - | For implementation |  | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 1000000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| 8918/ VariousWater System Development Project Construction in Progress- Infrastructure Assets | [22 empty] | 1
| ■ | Improvement of Potable Water System at Brgy. Mambago- A, Samal District, IGACOS |  |  | Water System |  | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | (Amended in the AIP 2nd Revision to change the location from Peñaplata to Samal District) PO approved September 2, 2019 |  | AC
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
| ■ | Rehabilitation of Potable Water System at Brgy. San Miguel, Samal District, IGACOS |  |  | Water System |  | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - |  |  | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
| ■ | Construction of Potable Water System at Brgy.Linusotan, Kaputian District, IGACOS |  |  | Water System |  | - | a) | 1300000 | a) | - | e) | - | a) | 1300000 | a) | - | c) | - | a) | - | (Additional 800,000.00 from Const. of PWS in purok 2, Pag-asa, Kapalong which was funded by OPAPP CY 2018) (amended) For allotment- October 15, 2019 |  | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 1300000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
| ■ | Rehabilitation of Water System in PEEDO-LPRRC, Brgy. Poblacion, New Corella |  |  | Water System |  | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For allotment- October 15, 2019 |  | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) |  | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
| 8918/ Stimulus Projects for Various Brgys.- District 1 Construction in Progress- Infrastructure Assets | [22 empty] | 2
| ■ | Construction of Water System at Brgy. San Agustin, Tagum City |  |  | Water System |  | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Declared as savings to add to stimulus projects that need additional fund No deed of donation |  | AC
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
| DISASTER REHABILITATION & RECOVERY PROGRAM Building Back Better Project | [22 empty] | 2
| Repairs & Maintenance- Infrastructure Assets | [22 empty] | AC
| ■ | Disilation of Tagum Creek |  |  |  |  | - | a) | 2000000 | a) | - | e) | - | a) | 2000000 | a) | - | c) | - | a) | - | PLAN AND POW on process c/o PEO-PDPM |  | AC
[8 empty] | b) | - | b) | - | f) | - | b) | 2000000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| ■ | Disilation of Mactan River (Ph. II) |  |  |  |  | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | PLAN AND POW on process c/o PEO-PDPM |  | 1
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
| Property, Plant and Equipmen Construction in Progress- Infrastructure Assets | [22 empty] | 2
| ■ | Rehabilitation of Pamacaun-Lasang-Banate Provincial Road |  |  |  |  | - | a) | 1500000 | a) | - | e) | - | a) | 1500000 | a) | - | c) | - | a) | - |  |  | AC
[8 empty] | b) | - | b) | - | f) | - | b) | 1500000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| ■ | Rehabilitation of Del Pilar Jct. Silangan |  |  |  |  | - | a) | 1500000 | a) | - | e) | - | a) | 1500000 | a) | - | c) | - | a) | - |  |  | 1
[8 empty] | b) | - | b) | - | f) | - | b) | 1500000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| ■ | Installation of 72" dia RCPC x 4M at San Agustin ES |  |  |  |  | - | a) | 350000 | a) | - | e) | - | a) | 350000 | a) | - | c) | - | a) | - |  |  | 1
[8 empty] | b) | - | b) | - | f) | - | b) | 350000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| ■ | Rehabilitation of Libuganon River along Kapalong Mabantao-Florida Provincial Road |  |  |  |  | - | a) | 900000 | a) | - | e) | - | a) | 900000 | a) | - | c) | - | a) | - |  |  | 1
[8 empty] | b) | - | b) | - | f) | - | b) | 900000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| ■ | Rehabilitation of Mesaoy-Jct. Mahayahay Road |  |  |  |  | - | a) | 1000000 | a) | - | e) | - | a) | 1000000 | a) | - | c) | - | a) | - |  |  | 1
[8 empty] | b) | - | b) | - | f) | - | b) | 1000000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| ■ | Rehabilitation of Dujali-Balisong-Magupising Provincial Road |  |  |  |  | - | a) | 1280000 | a) | - | e) | - | a) | 1280000 | a) | - | c) | - | a) | - |  |  | 1
[8 empty] | b) | - | b) | - | f) | - | b) | 1280000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| ■ | Rehabilitation of Sta. Fe- Mambing Road & Slope Protection |  |  |  |  | - | a) | 1320000 | a) | - | e) | - | a) | 1320000 | a) | - | c) | - | a) | - |  |  | 1
[8 empty] | b) | - | b) | - | f) | - | b) | 1320000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) |  | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
F. | SUPPLEMENTAL BUDGET NO. 4 CY 2019 | [22 empty] | 1
| INFRASTRUCTURE DEVELOPMENT PROGRAM | [22 empty] | FS
| LOCALLY FUNDED PROGRAMS/ PROJECTS GENERAL FUND PROPER | [22 empty] | AC
AC
| PEACE AND ORDER PROGRAM/1914 Construction in Progress- Land Improvements | [22 empty] | AC
| ■ | Provincial Livestock & Poultry Multiplier Farm Road Network Construction, Sitio Salawao, Sto. Niño, Talaingod |  |  |  |  | - | a) | 5500000 | a) | - | e) | - | a) | 5500000 | a) | - | c) | - | a) | - | For allotment Nov. 22, 2019 |  | AC
[8 empty] | b) | - | b) | - | f) | - | b) | 5500000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| ■ | Proposed Road Opening of Tawinian-Tapayanon Road Section |  |  |  |  | - | a) | 10000000 | a) | - | e) | - | a) | 10000000 | a) | - | c) | - | a) | - | Alloted- Dec. 6, 2019 |  | 1
[8 empty] | b) | - | b) | - | f) | - | b) | 10000000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| ■ | Rehabilitation of San Jose- Sitio Mahayahay-Magwawa Provincial Road, Sro. Tomas |  |  |  |  | - | a) | 1000000 | a) | - | e) | - | a) | 1000000 | a) | - | c) | - | a) | - | POW preparation on-going c/o South District |  | 1
[8 empty] | b) | - | b) | - | f) | - | b) | 1000000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
| 8918/ Various Government Buildigs & Facilities Development Project Construction in Progress- Land Improvements | [22 empty] | 2
| ■ | Construction of Perimeter Fence of Day Care Center I Nanyo, Panabo City |  |  |  |  | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Sched of bidding Dec. 27, 2019 |  | AC
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
| ■ | Construction of Multi-Purpose Building, Balagunan, Sto. Tomas |  |  |  |  | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For allotment Dec .3, 2019 |  | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
| ■ | Completion of Brgy. Health Center, Maniki, Kapalong |  |  |  |  | - | a) | 627000 | a) | - | e) | - | a) | 627000 | a) | - | c) | - | a) | - | PROJECT Was funded by LGU, Kapalong |  | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 627000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| INFRASTRUCTURE DEVELOPMENT PROGRAM | [22 empty] | 1
| LOCALLY FUNDED PROGRAMS/ PROJECTS 20% DEVELOPMENT FUND | [22 empty] | AC
AC
| 8918/ Rehabilitation of Various Provincial Roads, District 1 Construction in Progress- Infrastructure Assets | [22 empty] | AC
| ■ | Improvement of Km. 9 Sagayen-Sawata Provincial Road, San Isidro, Ph. 2 |  |  |  |  | - | a) | 4591029 | a) | - | e) | - | a) | 4591029 | a) | - | c) | - | a) | - |  |  | AC
[8 empty] | b) | - | b) | - | f) | - | b) | 4591029 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| 8918/ Various Local Roads and Drainaige Development Project Construction in Progress- Infrastructure Assets | [22 empty] | 1
| ■ | Rehabilitation of Local Roads at Dalisay-Manay Road Section, Panabo City |  |  |  |  | - | a) | 246100 | a) | - | e) | - | a) | 246100 | a) | - | c) | - | a) | - |  |  | AC
[8 empty] | b) | - | b) | - | f) | - | b) | 246100 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
| ■ | Rehabilitation of Local Roads at Sta. Cruz-Jct. Tagpore-Buenavista Raod Section, Panabo City |  |  |  |  | - | a) | 431000 | a) | - | e) | - | a) | 431000 | a) | - | c) | - | a) | - |  |  | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 431000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) |  | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
-
| ■ | Rehabilitation of Local Roads at Taba-Bucana Road Section, Taba, Carmen |  |  |  |  | - | a) | 220000 | a) | - | e) | - | a) | 220000 | a) | - | c) | - | a) | - |  |  | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 220000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
| 8918/ Stimulus Projects for Various Barangays Construction in Progress- Infrastructure Assets | [22 empty] | 2
| ■ | Construction of Potable Water System at Purok 6, New Santiago, Asuncion |  |  |  |  | contract | a) | 1000000 | a) | - | e) | - | a) | 1000000 | a) | - | c) | - | a) | - | For allotment Nov. 6, 2019 |  | AC
[8 empty] | b) | - | b) | - | f) | - | b) | 1000000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
| ■ | Concreting of Brgy. Road Canal, Dujali, B.E. Dujali |  |  |  |  | contract | a) | 650000 | a) | - | e) | - | a) | 650000 | a) | - | c) | - | a) | - | Alloted Oct. 18, 2019 Procurement on process |  | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 650000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
| ■ | Desilting and Conretign of Drainage-Main Collector Canal, New Casay, B.E. Dujali |  |  |  |  | contract | a) | 650000 | a) | - | e) | - | a) | 650000 | a) | - | c) | - | a) | - | For allotment - Sept. 27, 2019 |  | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 650000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
| ■ | Concreting of Drainage, Tanglaw, B.E., Dujali |  |  |  |  | contract | a) | 1200000 | a) | - | e) | - | a) | 1200000 | a) | - | c) | - | a) | - | For allotment Sept. 19, 2019 |  | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 1200000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
| ■ | Construction of Potable Water System, New Malitbog, Panabo City |  |  |  |  | contract | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For re-inspection and plan revision in order to reflect in the plan the complete details for the project to be functional.P500,000.00 covers only drilling activity |  | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
| ■ | Construction of Water System Project, Poblacion Kaputian, Samal |  |  |  |  | contract | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Alloted Oct 17, 2019 Procurement on process |  | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
| ■ | Construction of Canal Linign at Prk. 5, Salvacion, Panabo City |  |  |  |  | contract | a) | 600000 | a) | - | e) | - | a) | 600000 | a) | - | c) | - | a) | - | Alloted Oct. 18, 2019 Procurement on process |  | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 600000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
| ■ | Rehabilitation of Brgy. Road at Lunga-og. Sto. Tomas |  |  |  |  | contract | a) | 600000 | a) | - | e) | - | a) | 600000 | a) | - | c) | - | a) | - | For allotment Sept. 19, 2019 |  | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 600000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
| ■ | Construction of Children's Playground with Amenities, Poblacion, New Corella |  |  |  | Admin | contract | a) | 2500000 | a) | - | e) | - | a) | 2500000 | a) | - | c) | - | a) | - | Allotment Dec. 3, 2019 Procurement on process |  | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 2500000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| 8918/ Stimulus Projects for Various Barangays Construction in Progress- Bldgs. & Other Structures | [22 empty] | 1
| ■ | Construction of 2 Storey Multi-Purpose Hall Ph. 3 (Brgy. Hall), oblacion, New Corella |  |  |  |  | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Plan preparation on-going c/o PDPM |  | AC
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| ■ | Construction of Evacuation Center at Purok 1-C Brgy. Sto. Niño, Carmen |  |  |  |  | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For allotment Dec. 3, 2019 |  | 1
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) |  | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
| ■ | Rehabilitation of Evacuation Center at Magugpo Pob., Tagum City |  |  |  |  | - | a) | 600000 | a) | - | e) | - | a) | 600000 | a) | - | c) | - | a) | - | Sched of bidding Dec 27, 2019 |  | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 600000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| ■ | Construction of Brgy. Health Center at Magugpo South, Tagum City |  |  |  |  | - | a) | 1550000 | a) | - | e) | - | a) | 1550000 | a) | - | c) | - | a) | - | Allotd Nov. 15, 2019 Procurement on process |  | 1
[8 empty] | b) | - | b) | - | f) | - | b) | 1550000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
1
| ■ | Rehabilitation of Mulit-Purpose Building (Evacuation Center), Limbaan, New Corella |  |  |  |  | - | a) | 600000 | a) | - | e) | - | a) | 600000 | a) | - | c) | - | a) | - | For allotment nov. 5, 2019
[8 empty] | b) | - | b) | - | f) | - | b) | 600000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| ■ | Expansion of Multi-Purpose Hall ( Brgy. Hall), Patrocenio, New Corella |  |  |  |  | - | a) | 650000 | a) | - | e) | - | a) | 650000 | a) | - | c) | - | a) | - | Alloted Oct. 18, 2019 Procurement on process |  | 1
[8 empty] | b) | - | b) | - | f) | - | b) | 650000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| ■ | Construction of Multi-Purpose Hall, Waterfall, Panabo City |  |  |  |  | - | a) | 1050000 | a) | - | e) | - | a) | 1050000 | a) | - | c) | - | a) | - | For allotment |  | 1
[8 empty] | b) | - | b) | - | f) | - | b) | 1050000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
| ■ | Rehabilitation of Multi-Purpose Hall, San Francisco, Panabo City |  |  |  |  | - | a) | 600000 | a) | - | e) | - | a) | 600000 | a) | - | c) | - | a) | - | Alloted Oct. 18, 2019 Procurement on process |  | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 600000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
| ■ | Rehabilitation of Evacuation Center at Datu Abdul Dadia, Panabo City |  |  |  |  | - | a) | 650000 | a) | - | e) | - | a) | 650000 | a) | - | c) | - | a) | - | Sched of bidding -Dec 27, 2019 |  | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 650000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
| ■ | Construction of Multi-Purpose Hall, Buenavista, Panabo City |  |  |  |  | - | a) | 1050000 | a) | - | e) | - | a) | 1050000 | a) | - | c) | - | a) | - | Sched of bidding -Dec 27, 2019 |  | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 1050000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
| ■ | Rehabilitation of Multi-Purpose Hall, Llittle Panay, Panabo City |  |  |  |  | - | a) | 550000 | a) | - | e) | - | a) | 550000 | a) | - | c) | - | a) | - | For allotment Dec. 11, 2019 |  | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 550000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
| ■ | Rehabilitation of Multi-Purpose Hall, Pantaron, Sto. Tomas |  |  |  |  | - | a) | 550000 | a) | - | e) | - | a) | 550000 | a) | - | c) | - | a) | - | Alloted Oct. 18, 2019 Procurement on process |  | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 550000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
| ■ | Rehabilitation of Multi-Purpose Hall, Salvacion, Sto. Tomas |  |  |  |  | - | a) | 1000000 | a) | - | e) | - | a) | 1000000 | a) | - | c) | - | a) | - | POW preparation on-going c/o PDPM |  | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 1000000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
| ■ | Completion of Multi-Purpose Hall, San Jose, Sto. Tomas |  |  |  |  | - | a) | 600000 | a) | - | e) | - | a) | 600000 | a) | - | c) | - | a) | - | Alloted Nov. 15, 2019 Procurement on process |  | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 600000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
| ■ | Rehabilitation of Multi-Purpose Hall, Kasilak, Panabo City |  |  |  |  | - | a) | 650000 | a) | - | e) | - | a) | 650000 | a) | - | c) | - | a) | - | Alloted Nov. 15, 2019 Procurement on process |  | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 650000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) |  | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
| ■ | Rehabilitation of Brgy. Health Center, Dalisay, Panabo City |  |  |  |  | - | a) | 550000 | a) | - | e) | - | a) | 550000 | a) | - | c) | - | a) | - | For allotment Dec. 4, 2019 |  | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 550000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
2
| ■ | Rehabilitation of Evacuation Center, Kiotoy, Panabo City |  |  |  |  | - | a) | 650000 | a) | - | e) | - | a) | 650000 | a) | - | c) | - | a) | - | Sched of bidding Dec 27, 2019
[8 empty] | b) | - | b) | - | f) | - | b) | 650000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
| ■ | Rehabilitation of Evacuation Center, Cagangohan, Panabo City |  |  |  |  | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | POW for approval Nov. 5, 2019 |  | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
| ■ | Rehabilitation of Multi-Purpose Bldg. (Brgy. Hall) Tagpopongan, IGACOS |  |  |  |  | - | a) | 174460.33 | a) | - | e) | - | a) | 174460.33 | a) | - | c) | - | a) | - | For allotment Nov. 5, 2019 |  | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 174460.33 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
| 5% CALAMITY FUND | [22 empty] | 2
| DISASTER REHABILITATION & RECOVERY PROGRAM Building Back Better Project | [22 empty] | FS
| ■ | Rehabilitation of Canal Lining and Slope Protection at San Agustin E/S, San Agustin, Tagum City |  |  |  |  | - | a) | 350000 | a) | - | e) | - | a) | 350000 | a) | - | c) | - | a) | - |  |  | AC
[8 empty] | b) | - | b) | - | f) | - | b) | 350000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| TRUST FUND 2019 | [22 empty] | 1
| PROJECTS FOR PROVINCIAL VETERINARY OFFICE | [22 empty] | FS
| ■ | Poultry House and Training Center Sto. Niño, Talaingod |  |  |  |  | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - |  |  | AC
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
|  | Establishment of Multiplier Farm Project Sto. Niño, Talaingod |  |  |  |  | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - |  |  | 1
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| INFRASTRUCTURE DEVELOPMENT PROGRAM | [22 empty] | 1
| ■ | Purchase of Geo Resistivity Instrument |  |  |  |  | - | a) | 6567412 | a) | - | e) | - | a) | 6567412 | a) | - | c) | - | a) | - | Waiting for delivery of instrument |  | AC
[8 empty] | b) | - | b) | - | f) | - | b) | 6567412 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
CMGP 2019
| ■ | Road Upgrading of Sto Nino - Kabankalan - La Paz Provincial Road, Carmen |  |  |  |  | - | a) | 44461624.67 | a) |  | e) | - | a) | - | a) | 4.3% | c) | 34.23% | a) | 30 | On-going
[8 empty] | b) | Comidoy | b) | 10/7/2019 | f) | - | b) | - | b) | - | d) | 29.93% | b) | 610 |  |  | 2
[8 empty] | c) | GP & H CONST. | c) | 5/15/2020 | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | 222 C.D | d) | [13 empty] | 2
| ■ | Road Upgrading of Jct Highway - Sto Nino - La Paz - San Vicenter Provincial Road, Carmen |  |  |  |  | - | a) | 80481331.34 | a) |  | e) | - | a) | - | a) | 22.77% | c) | 33.12% | a) | - | On-going |  | 2
[8 empty] | b) | Fernandez | b) | 10/7/2019 | f) | - | b) | - | b) | - | d) | 10.35% | b) | -
[8 empty] | c) | Tagum Builders | c) | 6/22/2020 | g) | - | c) | -
[8 empty] | d) | 259 C.D | d)
| ■ | Road Upgrading of Kapalong - Mabantao - Florida Road with Bridge Component |  |  |  |  | - | a) | 15890000 | a) |  | e) | - | a) | - | a) |  | c) |  | a) | -
[8 empty] | b) |  | b) |  | f) | - | b) | - | b) | - | d) |  | b) | -
[8 empty] | c) |  | c) |  | g) | - | c) | -
[8 empty] | d) |  | d)
|  | Mark | Municipality/City |  | Color
|  | 1 | Asuncion |  | Red
|  | 2 | B.E. Dujali |  | Yellow
| GF- GENERAL FUND | 3 | Carmen |  | Blue | [10 empty] | TF - TRUST FUND (NATIONAL FUNDED PROJECT)
| 20% DF - 20% DEV'T. FUND | 4 | Kapalong |  | Pink | [10 empty] | a) SLRF - Special Local Road Fund
| 5% CF - 5% CALAMITY FUND | 5 | New Corella |  | Gray | [10 empty] | b) KALSADA - Konkreto at Ayos na Lansangan Tungo sa Pangkalahatang Kaunlaran
| CO - CAPITAL OUTLAY | 6 | San Isidro |  | Orange | [10 empty] | c) PRDP - Philippine Rural Development Projects
| CONG. FUND - CONGRESSIONAL FUND | 7 | Sto Tomas |  | Sky Blue | [10 empty] | d) SELAP - Support to Emergency and Livelihood Assistance Project
|  | 8 | Talaingod |  | Violet | [10 empty] | e) PAMANA - Payapa at Masaganang Pamayanan
| SEF - SPECIAL EDUCATIONAL UFND | 9 | Panabo City |  | Brown | [10 empty] | f) CBRMC - Community Based Road Maintenance Contracting
|  | 10 | IGACOS |  | Yellow Green | [10 empty] | g) MBC - Maintenance by Contract
|  | 11 | Tagum City |  | Green | [10 empty] | h) PCF-Performance Challenge Fund-DILG
i) FMRDP - Farm to Market Road
j.) CMGP - Conditional Grant to Provinces
k.) OPAPP - Office of the President Adviser on the Peace Process
l.) LGSF-AM - Local Government Support Fund Assistance to Municipalities
Prepared by: |  |  |  | Checked | [12 empty] | Recommending Approval
Noted
GILBERT G. MAMBULAO JR |  |  |  |  | TESSIE G. ABABON | [9 empty] | JIVELLYN B. CO | [5 empty] | GLENN A. OLANDRIA
Engineer II | [5 empty] | Engineer IV-Engineering Dist 2, Area Engineer | [9 empty] | Asst. PG-Department Head |  |  |  |  | Provincial Engineer
|  |  |  | EDWIN S. MISA |  |  |  | MARILOU A. FORONDA
|  |  |  | Engineer IV- PDPM Division Head |  |  |  | Engineer IV- QC Division Head

## Completed_4th Quarter_Dist 1 (hidden)
PROVINCE OF DAVAO DEL NORTE
ACCOMPLISHMENT REPORT
4th Quarter 2019
SECTOR: ECONOMIC (INFRASTRUCTURE DEV'T. PROGRAM)
OFFICE/AGENCY: PROVINCIAL ENGINEER'S OFFICE
COMPLETED PROJECTS 1ST DISTRICT
| Name of Project |  |  |  |  | Type | Physical | Mode | PROJECT DATA | [5 empty] | Financial (000) |  | Physical Accomplishment |  |  |  | Employment |  | REMARKS
[6 empty] | of | Target | of | a) Project Cost |  | a) Date A lot. Rel. |  | e) # of days suspended |  | a) Program |  | a) Planned |  | c) Actual |  | Generated
[6 empty] | Project | (Descrip | Impl. | b) Project Engineer |  | b) Date Started |  | f) # of days extended |  | b) Allotment |  | b) Revised |  | d) Slippage |  | a) # of Persons
[6 empty] | (Location) | tion) |  | c) Implementor |  | c)Target Compl. Date |  | g) Date completed |  | c) Disbursement | [5 empty] | b) Man-days
[9 empty] | d) Duration |  | d) Revised Compl. Date
| I. | PROJECTS UNDER THE CONTINUING APPROPRIATION | [21 empty] | AC | 893809.45
|  |  | TRUST FUND 2017 | [20 empty] | AC
|  |  | Conditional Matching Grant to Provinces (CMGP) | [20 empty] | AC
|  | 8 |  | Road Upgrading of Dagohoy - Daligdigon |  | Road | 2.532 km | Contract | a) | 58048310.68 | a) | CY 2017 | e) | - | a) | 58048310.68 | a) | 100.00% | c) | 100% | a) | 16 | Completed as per Physical Accomplishment, Financial Documents on Process | 1
|  |  |  | Provincial Road |  |  |  |  | b) | Fabiala | b) | 01/05/18 | f) | 205 CD | b) | 58048310.68 | b) | - | d) | 0% | b) | 480 |  | 1
[9 empty] | c) | PUREGOLD | c) | 11/18/18 | g) | - | c) | 29,572,637.70 | [7 empty] | 1
[9 empty] | d) | 246 CD | d) | 03/31/19 | [11 empty] | 1
4 |  |  |  | Impv’t. of Maligaya-New Camiling Prov’l. |  | Conc. | 2.13 km | Contract. | a) | 50101614.08 | a) | CY 2017 | e) | 76 CD | a) | 57385680 | a) | 100.00% | c) | 100% | a) | 21 | Completed based on POW. Financial Documents on process | 2
4 |  |  |  | Road w/ Bridge Component,Carmen |  |  |  |  | b) | Mellomida | b) | 12/18/17 | f) | 209 CD | b) | 57385680 | b) | 100% | d) | 0% | b) | 147 |  | 2
4 | [8 empty] | c) | PUREGOLD CONST. | c) | 02/15/19 | g) | - | c) | 36005452 | [7 empty] | 2
4 | [8 empty] | d) | 376 CD | d) | 07/31/19 | [11 empty] | 2
|  | D. | 20% Development Fund CY 2017 | [20 empty] | AC
|  |  | STIMULUS PROJECTS CY 2017 | [20 empty] | AC
|  |  | CARMEN | [20 empty] | AC
|  |  |  | Construction of Evaluation Center at Prk. 1, |  | Bldg. |  | Barangay | a) | 500000 | a) | 12/28/17 | e) | - | a) | 500000 | a) | - | c) | 100% | a) | - | Completed | 1
|  |  |  | Asuncion, Carmen |  |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 1
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | Const./Rehab./Comp. of Various Gov't. Bldgs. |  |  | Bldg. | - | Admin | a) | 9,000,000.00 | [12 empty] | Investigation/Inspection of priority projects | AC
|  |  | Struct., Fac. (Provincewide) | [5 empty] | b) | Foronda/Ababon | [13 empty] | AC
[9 empty] | c) | PEO | [13 empty] | AC
[9 empty] | d) | - | [13 empty] | AC
|  |  | 2.3 | Improvement of Garciaville Day Care |  | Bldg. |  | Admin | a) | 330,000.00 | a) | 11/06/18 | e) | - | a) | 330,000.00 | a) |  | c) | 100% | a) | 3 | Completed based on POW. Financial Documents on process | 1
|  | 11 |  | Center, Mankilam, Tagum City |  |  |  |  | b) | - | b) | 09/02/19 | f) | - | b) | 330,000.00 | b) | - | d) |  | b) | 90 |  | 1
[9 empty] | c) | PEO | c) | 10/11/19 | g) | - | c) | - | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
4 |  | F. | SDH IGCS - CONST. IN PROGRESS - BLGS. CY 2017 | [20 empty] | 2
4 |  |  | 1 | Construction Perimeter Fence Ph.II (Hospital |  | Fence |  | Admin | a) | 1,305,000.00 | a) | 11/10/17 | e) | 392 | a) | 1,305,000.00 | a) | 100% | c) | 100% | a) | 4 | Completed based on POW. Financial Documents on process | 2
4 |  |  |  | Compound) Samal District Hospital, IGCS |  |  |  |  | b) | Porras | b) | 03/12/18 | f) | 45 | b) | 1,305,000.00 | b) | - | d) | 1% | b) | 30 |  | 2
4 | [8 empty] | c) | PEO | c) | 06/19/18 | g) | - | c) | 958,597.98 | [7 empty] | 2
4 | [8 empty] | d) | - | d) | [12 empty] | 2
|  | C.5 | LDRRM - Trust Fund | [20 empty] | AC
|  | 5 | 1. Construction of Slope Protection and Concrete Pavement along Sta. Fe Mambing Road Section |  |  | Slope |  | Admin | a) | 1,853,000.00 | a) | 11/28/18 | e) |  | a) | 1,853,000.00 | a) | 100% | c) | 100% | a) | 16 | Completed based on POW. Financial Documents on process | 1
[9 empty] | b) | Gone | b) | 12/03/18 | f) | 108 CD | b) | 1,853,000.00 | b) | - | d) |  | b) | 144 |  | 1
[9 empty] | c) | PEO | c) | 02/28/19 | g) | 10/30/2019 | c) | 742252.72 | [7 empty] | 1
[9 empty] | d) | 86 CD | d) | 06/15/2019 | [11 empty] | 1
|  | 1 | 3. Rehab. Of Canatan Bridge Slope Protection |  |  | Slope | 395 sq.m. | Contract | a) | 9200000 | a) | 06/20/2018 | e) | - | a) | 9200000 | a) | 100% | c) | 100% | a) | - | Completed | 1
|  |  | Brgy. Canatan, Asuncion | [5 empty] | b) | Aclaracion | b) | 02/11/2019 | f) | 35 CD | b) | 9200000 | b) | 100% | d) | 0% | b) | - |  | 1
[9 empty] | c) | J-One Builders | c) | 04/12/2019 | g) | 05/31/2019 | c) | 7222021.59 | [7 empty] | 1
[9 empty] | d) | 60 CD | d) | 05/01/2019 | [11 empty] | 1
|  | 5 | 5. Const. of Cabidianan Bridge Slope Protection, Brgy. Cabidianan, New Corella |  |  | Slope |  | Admin | a) | 3590000 | a) | 07/18/18 | e) | - | a) | 3590000 | a) | 100% | c) | 100% | a) | 8 | Completed based on POW. Financial Documents on process | 1
[9 empty] | b) | Gone | b) | 6/17/19 | f) | - | b) | 3590000 | b) |  | d) |  | b) | 80 |  | 1
[9 empty] | c) | PEO | c) | 8/20/19 | g) | - | c) | 1929823.4 | [7 empty] | 1
[9 empty] | d) | 65 CD | d) | - | [11 empty] | 1
|  | D. | SEF(Special Education Fund)-SUPPLEMENTAL BUDGET # 1 CY 2017 | [20 empty] | AC
|  |  | 1. Const./Impv't./Compl. Of School Bldgs., Struc. & Fac. |  |  | Bldgs. |  | Admin | a) | 3,300,000.00 | [12 empty] | See projects listed below | 1
[9 empty] | b) | Foronda | [13 empty] | 1
[9 empty] | c) | PEO | [13 empty] | 1
[9 empty] | d) | - | [13 empty] | 1
|  | 8 | 1.1 | Construction of 1 unit School Building |  | Bldg. |  | Admin | a) | 1100000 | a) | 02/19/18 | e) | - | a) | 1100000 | a) | 100 | c) | 100 | a) | 6 | Completed based on POW. Financial Documents on process | 1
|  |  |  | Lumabag, Talaingod |  |  |  |  | b) | Dadula | b) | 03/20/19 | f) | 27 CD | b) | 1100000 | b) |  | d) |  | b) | 30 |  | 1
[9 empty] | c) | PEO | c) | 05/19/19 | g) | 06/30/2019 | c) | 595230.5 | [7 empty] | 1
[9 empty] | d) | 60 CD | d) | - | [11 empty] | 1
AC
|  |  | Rehabilitation / Improvement Of Various Local |  |  | Road | - | Admin | a) | 5000000 | [12 empty] | See projects listed below | AC
|  |  | Roads and Drainages | [5 empty] | b) | Paraguya | [13 empty] | AC
[9 empty] | c) | Admin | [13 empty] | AC
[9 empty] | d) | - | [13 empty] | AC
4 |  |  |  | Rehabilitation of Brgy. Adecor Barangay |  | Road |  | Admin | a) | 138000 | a) | 04/25/18 | e) | 66 CD | a) | 138000 | a) | 60.00% | c) | 60.00% | a) | - | Completed as per POW. Financial Documents on process | 2
4 |  |  |  | Road, IGACOS |  |  |  |  | b) | Porras/Pacquiao | b) | 10/18/18 | f) | 225 CD | b) | 138000 | b) | - | d) | - | b) | - |  | 2
4 | [8 empty] | c) | PEO | c) | 10/27/19 | g) | - | c) | 111,872.00 | [7 empty] | 2
4 | [8 empty] | d) | - | d) | 10/15/2019 | [11 empty] | 2
|  |  | Const./Rehab./Comp. of Various Gov't. Bldgs. |  |  | Bldgs. | - | Admin | a) | 13523124 | [12 empty] | Investigation/Inspection of priority projects | AC
|  |  | Struct., Fac. (Provincewide) | [5 empty] | b) | Foronda | [13 empty] | AC
[9 empty] | c) | Admin | [13 empty] | AC
[9 empty] | d) | - | [13 empty] | AC
4 |  |  |  | Repair/Rehab. Of PEO Building (2nd District), Carmen |  | Bldg |  | Admin | a) | 2250000 | a) | 08/10/18 | e) | - | a) | 2250000 | a) | 100% | c) | 100% | a) | 18 | Completed based on POW. Financial Documents on process | 2
4 | [8 empty] | b) | Andoy | b) | 02/18/19 | f) | - | b) | 2250000 | b) | - | d) | 0% | b) | 138 |  | 2
4 | [8 empty] | c) | Admin | c) | 08/23/19 | g) | - | c) | 1577344.8 | [7 empty] | 2
4 | [8 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | STIMULUS PROJECTS | [20 empty] | AC
|  |  | TAGUM CITY | [20 empty] | AC
|  |  |  | Completion of Two Storey Multi-Purpose |  | Bldg. |  | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | 100% | c) | 100% | a) | 5 | Completed based on Physical Accomplishment. Financial Documents on process | 1
|  |  |  | Building, Magugpo East, Tagum City |  |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | 0% | b) | 110 |  | 1
[9 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  | L. | 5% Calamity Fund CY 2018 | [20 empty] | AC
|  |  | 1. Prevention and Mitigation | [20 empty] | AC
|  |  | 1.1 Desiltation/Excavation of rivers and creeks |  |  | rivers |  | Admin | a) | 3000000 | [12 empty] | Investigation/Inspection of priority projects | AC
[9 empty] | b) | - | [13 empty] | AC
[9 empty] | c) | PEO | [13 empty] | AC
[9 empty] | d) | - | [13 empty] | AC
1
|  |  | 1.1.1. | Improvement and Desiltation of Tagum Creek (Phase I and Phase II) |  | Creek |  | Admin | a) | 2,000,000.00 | a) | 11/06/18 | e) | - | a) | 2,000,000.00 | a) | 100% | c) | 100% | a) | 5 | Completed | 1
[9 empty] | b) | Mayang | b) | 03/22/19 | f) | - | b) | 2,000,000.00 | b) | - | d) | 0% | b) | 110 |  | 1
[9 empty] | c) | PEO | c) | 10/31/19 | g) | - | c) | - | [7 empty] | 1
[9 empty] | d) | 224 CD | d) | - | [11 empty] | 1
|  |  | OPPAP-PAMANA | [20 empty] | AC
|  | 4 |  | Upgrading of Existing PWS Level II in Sitio Patel 2, Gupitan, Kapalong |  | PWS |  | Admin | a) | 2500000 | a) | 8/14/2019 | e) | - | a) | 2500000 | a) |  | c) | 100% | a) | - | Completed as per Physical Accomplishment. Financial Documents on process | 1
[9 empty] | b) | Diosanta | b) | 3/25/2019 | f) | - | b) | 2500000 | b) |  | d) |  | b) | - |  | 1
[9 empty] | c) | PEO | c) | 7/19/2019 | g) | 09/30/2019 | c) | - | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  | R. | LOCAL GOVERNMENT SUPPORT FUND (LGSF) CY 2018 | [20 empty] | AC
|  |  | 1 | Road Upgrading of San Vicente - Butay Provincial Road |  | Road |  | Contract | a) | 19949581.18 | a) | CY 2018 | e) | - | a) | 19949581.18 | a) | 100% | c) | 100% | a) | 18 | Completed as per Physical Accomplishment. Financial Documents on process | 1
[9 empty] | b) | Aclaracion | b) | 11/19/18 | f) | 28 CD | b) | 19949581.18 | b) | 100% | d) | 0% | b) | 396 |  | 1
[9 empty] | c) | Alpha & Omega | c) | 06/08/19 | g) | 06/26/2019 | c) | 9,685,667.31 | [7 empty] | 1
[9 empty] | d) | 202 CD | d) | 07/06/19 | [11 empty] | 1
| II. PROJECTS UNDER THE CURRENT APPROPRIATION CY 2019 | [22 empty] | AP
| A.1 GENERAL FUND CY 2019 | [6 empty] | MBA/CBRMC | a) | 18127866 | a) | 01/03/19 | e) | - | a) | 18127866 | a) | 83.63 | c) | 83.83 | a) | 46 | See list of Provincial Roads | AP
| Road ID |  | Maintenance of Various Provincial Roads and Bridges at District 1 |  |  | Road Maintenance | KM |  | b) | Paraguya | b) | 01/03/19 | f) | - | b) | 18127866 | b) | - | d) | - | b) | 920 |  | FS
[7 empty] | 288.26 |  | c) | PEO/CBRMC | c) | 12/31/19 | g) | - | c) | - | [7 empty] | AC
| 11DAN | [9 empty] | d) | - | [11 empty] | AC
[9 empty] | d) | 261 days | d) | - | [11 empty] | AC
|  |  | Jct. Highway Magatos - New Bantayan |  |  | Road Maintenance | 7.1 | MBA | a) | 287307.39 | a) | 01/03/19 | e) | - | a) | 287307.39 | a) | 100% | c) | 100% | a) | 15 | Completed | AC
| 001 | [7 empty] | b) | Crucio | b) | 01/16/19 | f) | - | b) | 287307.39 | b) | - | d) | - | b) | 480 |  | 1
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 118693.58 | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | Jct. Highway Magatos - New Bantayan |  |  | Road Maintenance | 7.1 | CBRMC | a) | 223674.22 | a) | 01/03/19 | e) | - | a) | 223674.22 | a) | 100% | c) | 100% | a) | 16 | Completed | 1
| 001 | [7 empty] | b) | Crucio | b) | 3/22/19 | f) | - | b) | 223674.22 | b) | - | d) | - | b) | 480 |  | 1
[9 empty] | c) | CALAFA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
|  |  | Magatos-Bdry Pagsabangan |  |  | Road Maintenance | 8.33 | MBA | a) | 328740.25 | a) | 01/03/19 | e) | - | a) | 328740.25 | a) | 100% | c) | 100% | a) | 15 | Completed | 1
| 002 | [7 empty] | b) | Crucio | b) | 01/03/19 | f) | - | b) | 328740.25 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 207258.49 | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | Magatos-Bdry Pagsabangan |  |  | Road Maintenance | 8.33 | CBRMC | a) | 270763.53 | a) | 01/03/19 | e) | - | a) | 270763.53 | a) | 100% | c) | 100% | a) | 16 | Completed | 1
| 002 | [7 empty] | b) | Crucio | b) | 03/22/19 | f) | - | b) | 270763.53 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | CALAFA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
|  |  | Ilog-New Bantayan |  |  | Road Maintenance | 2.68 | MBA | a) | 131131.39 | a) | 01/03/19 | e) | - | a) | 131131.39 | a) | 100% | c) | 100% | a) | 15 | Completed | 1
| 003 | [7 empty] | b) | Crucio | b) | 01/16/19 | f) | - | b) | 131131.39 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 49,316.69 | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | Ilog-New Bantayan |  |  | Road Maintenance | 2.68 | CBRMC | a) | 65925.03 | a) | 01/03/19 | e) | - | a) | 65925.03 | a) | 100% | c) | 100% | a) | 16 | Completed | 1
| 003 | [7 empty] | b) | Crucio | b) | 03/22/19 | f) | - | b) | 65925.03 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | CALAFA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
|  |  | Asuncion -Monte Carlo-Del Pilar |  |  | Road Maintenance | 9.93 | MBA | a) | 474102.88 | a) | 01/03/19 | e) | - | a) | 474102.88 | a) | 100% | c) | 100% | a) | 15 | Completed | 1
| 005 | [7 empty] | b) | Crucio | b) | 01/03/19 | f) | - | b) | 474102.88 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 240274.49 | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | Asuncion -Monte Carlo-Del Pilar |  |  | Road Maintenance | 9.93 | CBRMC | a) | 355524.28 | a) | 01/03/19 | e) | - | a) | 355524.28 | a) | 100% | c) | 100% | a) | 16 | Completed
| 005 | [7 empty] | b) | Crucio | b) | 03/22/19 | f) | - | b) | 355524.28 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | MAHAYAHAY IFA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
|  |  | Jct. Highway Canatan-Jct. Highway Magatos |  |  | Road Maintenance | 4.85 | MBA | a) | 209808.59 | a) | 01/03/19 | e) | - | a) | 209808.59 | a) | 100% | c) | 100% | a) | 15 | Completed | 1
| 006 | [7 empty] | b) | Crucio | b) | 02/18/19 | f) | - | b) | 209808.59 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 80652.8 | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | Jct. Highway Canatan-Jct. Highway Magatos |  |  | Road Maintenance | 4.85 | CBRMC | a) | 162458.12 | a) | 01/03/19 | e) | - | a) | 162458.12 | a) | 100% | c) | 100% | a) | 16 | Completed | 1
| 006 | [7 empty] | b) | Crucio | b) | 03/22/19 | f) | - | b) | 162458.12 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | CAMODA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
1
|  |  | Sta. Felomina-San Roque |  |  | Road Maintenance | 7.68 | MBA | a) | 147439.63 | a) | 01/03/19 | e) | - | a) | 147439.63 | a) | 100% | c) | 100% | a) | 15 | Completed
| 008 | [7 empty] | b) | Crucio | b) | 01/16/19 | f) | - | b) | 147439.63 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 63806.67 | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | Sta. Felomina-San Roque |  |  | Road Maintenance | 7.68 | CBRMC | a) | 261345.67 | a) | 01/03/19 | e) | - | a) | 261345.67 | a) | 100% | c) | 100% | a) | 16 | Completed | 1
| 008 | [7 empty] | b) | Crucio | b) | 03/25/19 | f) | - | b) | 261345.67 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | STAFFA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
|  |  | Saug-Sonlon-Bdy Longanapan |  |  | Road Maintenance | 11.6 | MBA | a) | 568486.36 | a) | 01/03/19 | e) | - | a) | 568486.36 | a) | 100% | c) | 100% | a) | 15 | Completed | 1
| 010 | [7 empty] | b) | Crucio | b) | 01/16/19 | f) | - | b) | 568486.36 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 262900.22 | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | Saug-Sonlon-Bdy Longanapan |  |  | Road Maintenance | 11.6 | CBRMC | a) | 185565.56 | a) | 01/03/19 | e) | - | a) | 185565.56 | a) | 100% | c) | 100% | a) | 16 | Completed | 1
| 010 | [7 empty] | b) | Crucio | b) | 03/26/19 | f) | - | b) | 185565.56 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | BINANCIAN LIVESTOCK AFA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
|  |  | Jct. New Visayas-Buan |  |  | Road Maintenance | 2.99 | MBA | a) | 79238.27 | a) | 01/03/19 | e) | - | a) | 79238.27 | a) | 100% | c) | 100% | a) | 15 | Completed | 1
| 011 | [7 empty] | b) | Crucio | b) | 02/18/19 | f) | - | b) | 79238.27 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 14682.85 | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | Jct. New Visayas-Buan |  |  | Road Maintenance | 2.99 | CBRMC | a) | 101242.01 | a) | 01/03/19 | e) | - | a) | 101242.01 | a) | 100% | c) | 100% | a) | 16 | Completed | 1
| 011 | [7 empty] | b) | Crucio | b) | 03/22/19 | f) | - | b) | 101242.01 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | BUAN IFA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
|  |  | San Vicente - Butay |  |  | Road Maintenance | 7.52 | MBA | a) | 209624.2 | a) | 01/03/19 | e) | - | a) | 209624.2 | a) | 100% | c) | 100% | a) | 15 | Completed | 1
| 013 | [7 empty] | b) | Crucio | b) | 02/18/19 | f) | - | b) | 209624.2 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 56,080.29 | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | San Vicente - Butay |  |  | Road Maintenance | 7.52 | CBRMC | a) | 227205.88 | a) | 01/03/19 | e) | - | a) | 227205.88 | a) | 100% | c) | 100% | a) | 16 | Completed | 1
| 013 | [7 empty] | b) | Crucio | b) | 03/27/19 | f) | - | b) | 227205.88 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | SVMODA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
|  |  | Jct. Highway Doña Andrea - Capungagan |  |  | Road Maintenance | 8.7 | MBA | a) | 230835.16 | a) | 01/03/19 | e) | - | a) | 230835.16 | a) | 100% | c) | 100% | a) | 15 | Completed | 1
| 014 | [7 empty] | b) | Crucio | b) | 02/18/19 | f) | - | b) | 230835.16 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 60,629.26 | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
1
|  |  | Jct. Highway Doña Andrea - Capungagan |  |  | Road Maintenance | 8.7 | CBRMC | a) | 294308.14 | a) | 01/03/19 | e) | - | a) | 294308.14 | a) | 100% | c) | 100% | a) | 16 | Completed
| 014 | [7 empty] | b) | Crucio | b) | 03/28/19 | f) | - | b) | 294308.14 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | CAPUNGAGAN MPC | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
|  |  | Semong-Palma Gil |  |  | Road Maintenance | 2.73 | MBA | a) | 147289.98 | a) | 01/03/19 | e) | - | a) | 147289.98 | a) | 100% | c) | 100% | a) | 15 | Completed | 1
| 018 | [7 empty] | b) | Crucio | b) | 02/18/19 | f) | - | b) | 147289.98 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 71745.43 | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
1
|  |  | Semong-Palma Gil |  |  | Road Maintenance | 2.73 | CBRMC | a) | 49186.05 | a) | 01/03/19 | e) | - | a) | 49186.05 | a) | 100% | c) | 100% | a) | 16 | Completed
| 018 | [7 empty] | b) | Crucio | b) | 03/22/19 | f) | - | b) | 49186.05 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | PALMA GIL FA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
|  |  | Daligdigon - Dagohoy |  |  | Road Maintenance | 3.34 | MBA | a) | 148835.45 | a) | 01/03/19 | e) | - | a) | 148835.45 | a) | 100% | c) | 100% | a) | - | Completed | 1
| 020 | [7 empty] | b) | Crucio | b) | - | f) | - | b) | 148835.45 | b) | - | d) | - | b) | - |  | 1
[9 empty] | c) | PEO | c) | - | g) | 2019-12-31 | c) | - | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | Daligdigon - Dagohoy |  |  | Road Maintenance | 3.34 | CBRMC | a) | 68279.5 | a) | 01/03/19 | e) | - | a) | 68279.5 | a) | 100% | c) | 100% | a) | 16 | Completed | 1
| 020 | [7 empty] | b) | Crucio | b) | 03/22/19 | f) | - | b) | 68279.5 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | PALMA GIL FA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
|  |  | Jct. Sampao-Bdry. Mamacao |  |  | Road Maintenance | 4.98 | MBA | a) | 154200.78 | a) | 01/03/19 | e) | - | a) | 154200.78 | a) | 100% | c) | 100% | a) | 15 | Completed | 1
| 025 | [7 empty] | b) | Crucio | b) | 02/18/19 | f) | - | b) | 154200.78 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 24,296.87 | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | Jct. Sampao-Bdry. Mamacao |  |  | Road Maintenance | 4.98 | CBRMC | a) | 169521.51 | a) | 01/03/19 | e) | - | a) | 169521.51 | a) | 100% | c) | 100% | a) | 16 | Completed | 1
| 025 | [7 empty] | b) | Crucio | b) | 03/26/19 | f) | - | b) | 169521.51 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | AMS KAPALONG | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
|  |  | Jct. Highway Luna-Mamacao-Narra |  |  | Road Maintenance | 9.17 | MBA | a) | 357957.66 | a) | 01/03/19 | e) | - | a) | 357957.66 | a) | 100% | c) | 100% | a) | 15 | Completed | 1
| 026 | [7 empty] | b) | Crucio | b) | 02/18/19 | f) | - | b) | 357957.66 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 127,996.16 | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | Jct. Highway Luna-Mamacao-Narra |  |  | Road Maintenance | 9.17 | CBRMC | a) | 313143.91 | a) | 01/03/19 | e) | - | a) | 313143.91 | a) | 100% | c) | 100% | a) | 16 | Completed | 1
| 026 | [7 empty] | b) | Crucio | b) | 03/26/19 | f) | - | b) | 313143.91 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | AMS KAPALONG | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
|  |  | Jct. Gabuyan-Katipunan-Bucana |  |  | Road Maintenance | 5.89 | MBA | a) | 294403.23 | a) | 01/03/19 | e) | - | a) | 294403.23 | a) | 100% | c) | 100% | a) | 15 | Completed | 1
| 027 | [7 empty] | b) | Crucio | b) | 02/18/19 | f) | - | b) | 294403.23 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 126,179.97 | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | Jct. Gabuyan-Katipunan-Bucana |  |  | Road Maintenance | 5.89 | CBRMC | a) | 129495.6 | a) | 01/03/19 | e) | - | a) | 129495.6 | a) | 100% | c) | 100% | a) | 16 | Completed | 1
| 027 | [7 empty] | b) | Crucio | b) | 03/26/19 | f) | - | b) | 129495.6 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | MANGULIBAS FA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
|  |  | Capungagan-Mabuhay-Pandulian |  |  | Road Maintenance | 5.57 | MBA | a) | 294917.73 | a) | 01/03/19 | e) | - | a) | 294917.73 | a) | 100% | c) | 100% | a) | 15 | Completed | 1
| 028 | [7 empty] | b) | Crucio | b) | 02/18/19 | f) | - | b) | 294917.73 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
1
|  |  | Capungagan-Mabuhay-Pandulian |  |  | Road Maintenance | 5.57 | CBRMC | a) | 105950.95 | a) | 01/03/19 | e) | - | a) | 105950.95 | a) | 100% | c) | 100% | a) | 16 | Completed
| 028 | [7 empty] | b) | Crucio | b) | 03/28/19 | f) | - | b) | 105950.95 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | CAPUNGAGAN MPC | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
|  |  | Florida - New Boholano |  |  | Road Maintenance | 2.54 | MBA | a) | 95863.17 | a) | 01/03/19 | e) | - | a) | 95863.17 | a) | 100% | c) | 100% | a) | 15 | Completed | 1
| 030 | [7 empty] | b) | Crucio | b) | 02/18/19 | f) | - | b) | 95863.17 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 31,418.99 | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | Florida - New Boholano |  |  | Road Maintenance | 2.54 | CBRMC | a) | 47425.27 | a) | 01/03/19 | e) | - | a) | 47425.27 | a) | 100% | c) | 100% | a) | 16 | Completed | 1
| 030 | [7 empty] | b) | Crucio | b) | 03/28/19 | f) | - | b) | 47425.27 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | SUPRA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
|  |  | Jct. New Boholano - New Loon |  |  | Road Maintenance | 4.77 | MBA | a) | 140549.84 | a) | 01/03/19 | e) | - | a) | 140549.84 | a) | 100% | c) | 100% | a) | 15 | Completed | 1
| 031 | [7 empty] | b) | Crucio | b) | 02/18/19 | f) | - | b) | 140549.84 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 40,056.38 | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | Jct. New Boholano - New Loon |  |  | Road Maintenance | 4.77 | CBRMC | a) | 169521.51 | a) | 01/03/19 | e) | - | a) | 169521.51 | a) | 100% | c) | 100% | a) | 16 | Completed | 1
| 031 | [7 empty] | b) | Crucio | b) | 03/28/19 | f) | - | b) | 169521.51 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | NEW LOON FA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
|  |  | Florida-Suaon-Jct. Gupitan |  |  | Road Maintenance | 15.57 | MBA | a) | 707038.05 | a) | 01/03/19 | e) | - | a) | 707038.05 | a) | 100% | c) | 100% | a) | 15 | Completed | 1
| 032 | [7 empty] | b) | Crucio | b) | 01/16/19 | f) | - | b) | 707038.05 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 226,.062.60 | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | Florida-Suaon-Jct. Gupitan |  |  | Road Maintenance | 15.57 | CBRMC | a) | 419094.85 | a) | 01/03/19 | e) | - | a) | 419094.85 | a) | 100% | c) | 100% | a) | 16 | Completed | 1
| 032 | [7 empty] | b) | Crucio | b) | 03/28/19 | f) | - | b) | 419094.85 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | SUPRA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
|  |  | Km. 15, Kipalili-New Loon |  |  | Road Maintenance | 6.93 | MBA | a) | 367659.97 | a) | 01/03/19 | e) | - | a) | 367659.97 | a) | 100% | c) | 100% | a) | 15 | Completed | 1
| 034 | [7 empty] | b) | Crucio | b) | 02/01/19 | f) | - | b) | 367659.97 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 112,175.78 | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | Km. 15, Kipalili-New Loon |  |  | Road Maintenance | 6.93 | CBRMC | a) | 237801.01 | a) | 01/03/19 | e) | - | a) | 237801.01 | a) | 100% | c) | 100% | a) | 16 | Completed | 1
| 034 | [7 empty] | b) | Crucio | b) | 03/26/19 | f) | - | b) | 237801.01 | b) | - | d) | - | b) | 480 |  | 1
[9 empty] | c) | KIPALILI FA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
|  |  | Jct. Suaon-Libuton |  |  | Road Maintenance | 7.26 | MBA | a) | 44015.68 | a) | 01/03/19 | e) | - | a) | 44015.68 | a) | 100% | c) | 100% | a) | 15 | Completed
| 035 | [7 empty] | b) | Crucio | b) | 01/16/19 | f) | - | b) | 44015.68 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 24,980.86 | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | Jct. Suaon-Libuton |  |  | Road Maintenance | 7.26 | CBRMC | a) | 91664.91 | a) | 01/03/19 | e) | - | a) | 91664.91 | a) | 100% | c) | 100% | a) | 16 | Completed | 1
| 035 | [7 empty] | b) | Crucio | b) | 03/22/19 | f) | - | b) | 91664.91 | b) | - | d) | - | b) | 480 |  | 1
[9 empty] | c) | AALLI | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
1
|  |  | Datu Balong - Pinamuno |  |  | Road Maintenance | 2.74 | MBA | a) | 95458.24 | a) | 01/03/19 | e) | - | a) | 95458.24 | a) | 100% | c) | 100% | a) | 15 | Completed
| 040 | [7 empty] | b) | Crucio | b) | 03/01/19 | f) | - | b) | 95458.24 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 12,625.00 | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | Datu Balong - Pinamuno |  |  | Road Maintenance | 2.74 | CBRMC | a) | 63570.57 | a) | 01/03/19 | e) | - | a) | 63570.57 | a) | 100% | c) | 100% | a) | 16 | Completed | 1
| 040 | [7 empty] | b) | Crucio | b) | 03/28/19 | f) | - | b) | 63570.57 | b) | - | d) | - | b) | 480 |  | 1
[9 empty] | c) | DATU BALONG FA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
|  |  | Sawata - Mamangan - Pinamuno |  |  | Road Maintenance | 14.48 | MBA | a) | 545390.17 | a) | 01/03/19 | e) | - | a) | 545390.17 | a) | 100% | c) | 100% | a) | 15 | Completed | 1
| 041 | [7 empty] | b) | Crucio | b) | 02/01/19 | f) | - | b) | 545390.17 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 196,076.60 | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | Sawata - Mamangan - Pinamuno |  |  | Road Maintenance | 14.48 | CBRMC | a) | 508564.54 | a) | 01/03/19 | e) | - | a) | 508564.54 | a) | 100% | c) | 100% | a) | 16 | Completed | 1
| 041 | [7 empty] | b) | Crucio | b) | 03/22/19 | f) | - | b) | 508564.54 | b) | - | d) | - | b) | 480 |  | 1
[9 empty] | c) | SAWATA DFA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
|  |  | Igangon - Sawata |  |  | Road Maintenance | 9.66 | MBA | a) | 497447.77 | a) | 01/03/19 | e) | - | a) | 497447.77 | a) | 100% | c) | 100% | a) | 15 | Completed | 1
| 042 | [7 empty] | b) | Crucio | b) | 02/01/19 | f) | - | b) | 497447.77 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | Igangon - Sawata |  |  | Road Maintenance | 9.66 | CBRMC | a) | 197775.1 | a) | 01/03/19 | e) | - | a) | 197775.1 | a) | 100% | c) | 100% | a) | 16 | Completed | 1
| 042 | [7 empty] | b) | Crucio | b) | 03/22/19 | f) | - | b) | 197775.1 | b) | - | d) | - | b) | 480 |  | 1
[9 empty] | c) | SAWATA DFA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
|  |  | New Corella - Sto. Niño - Macgum |  |  | Road Maintenance | 17.11 | MBA | a) | 606294.08 | a) | 01/03/19 | e) | - | a) | 606294.08 | a) | 100% | c) | 100% | a) | 15 | Completed | 1
| 044 | [7 empty] | b) | Crucio | b) | 01/03/19 | f) | - | b) | 606294.08 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 246,619.77 | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | New Corella - Sto. Niño - Macgum |  |  | Road Maintenance | 17.11 | CBRMC | a) | 308434.97 | a) | 01/03/19 | e) | - | a) | 308434.97 | a) | 100% | c) | 100% | a) | 16 | Completed | 1
| 044 | [7 empty] | b) | Crucio | b) | 03/26/19 | f) | - | b) | 308434.97 | b) | - | d) | - | b) | 480 |  | 1
[9 empty] | c) | SAN ISIDRO FA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
|  |  | Tagaytay - Buan |  |  | Road Maintenance | 4.92 | MBA | a) | 173197.37 | a) | 01/03/19 | e) | - | a) | 173197.37 | a) | 100% | c) | 100% | a) | 15 | Completed | 1
| 045 | [7 empty] | b) | Crucio | b) | 03/18/19 | f) | - | b) | 173197.37 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 26254.58 | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | Tagaytay - Buan |  |  | Road Maintenance | 4.92 | CBRMC | a) | 131850.07 | a) | 01/03/19 | e) | - | a) | 131850.07 | a) | 100% | c) | 100% | a) | 16 | Completed | 1
| 045 | [7 empty] | b) | Crucio | b) | 03/22/19 | f) | - | b) | 131850.07 | b) | - | d) | - | b) | 480 |  | 1
[9 empty] | c) | BUAN IFA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
|  |  | limbaan - Sto. Niño |  |  | Road Maintenance | 3.19 | MBA | a) | 153706.77 | a) | 01/03/19 | e) | - | a) | 153706.77 | a) | 100% | c) | 100% | a) | 15 | Completed | 1
| 049 | [7 empty] | b) | Crucio | b) | 03/01/19 | f) | - | b) | 153706.77 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 32534.49 | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | limbaan - Sto. Niño |  |  | Road Maintenance | 3.19 | CBRMC | a) | 53657.51 | a) | 01/03/19 | e) | - | a) | 53657.51 | a) | 100% | c) | 100% | a) | - | Completed | 1
| 049 | [7 empty] | b) | Crucio | b) | - | f) | - | b) | 53657.51 | b) | - | d) | - | b) | - |  | 1
[9 empty] | c) | - | c) | - | g) | 2019-12-31 | c) | - | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | Del Pilar - Jct. Silangan |  |  | Road Maintenance | 4.17 | MBA | a) | 187097.4 | a) | 01/03/19 | e) | - | a) | 187097.4 | a) | 100% | c) | 100% | a) | 15 | Completed | 1
| 051 | [7 empty] | b) | Crucio | b) | 03/18/19 | f) | - | b) | 187097.4 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 94181.74 | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | Del Pilar - Jct. Silangan |  |  | Road Maintenance | 4.17 | CBRMC | a) | 113014.34 | a) | 01/03/19 | e) | - | a) | 113014.34 | a) | 100% | c) | 100% | a) | 16 | Completed | 1
| 051 | [7 empty] | b) | Crucio | b) | 03/26/19 | f) | - | b) | 113014.34 | b) | - | d) | - | b) | 480 |  | 1
[9 empty] | c) | DURIAN DACUDAO | c) | 12/31/19 | g) | - | c) | - | [7 empty] | 1
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
|  |  | New Corella - New Sambog - Silangan |  |  | Road Maintenance | 5.1 | MBA | a) | 201994.35 | a) | 01/03/19 | e) | - | a) | 201994.35 | a) | 100% | c) | 100% | a) | 15 | Completed | 1
| 052 | [7 empty] | b) | Crucio | b) | 03/01/19 | f) | - | b) | 201994.35 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 63402.48 | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | New Corella - New Sambog - Silangan |  |  | Road Maintenance | 5.1 | CBRMC | a) | 131850.07 | a) | 01/03/19 | e) | - | a) | 131850.07 | a) | 100% | c) | 100% | a) | 16 | Completed | 1
| 052 | [7 empty] | b) | Crucio | b) | 03/26/19 | f) | - | b) | 131850.07 | b) | - | d) | - | b) | 480 |  | 1
[9 empty] | c) | DURIAN DACUDAO | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
|  |  | Sta. Fe - Del Monte |  |  | Road Maintenance | 3.34 | MBA | a) | 37923.51 | a) | 01/03/19 | e) | - | a) | 37923.51 | a) | 100% | c) | 100% | a) | 15 | Completed | 1
| 056 | [7 empty] | b) | Crucio | b) | 03/18/19 | f) | - | b) | 37923.51 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 36595.13 | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | Sta. Fe - Del Monte |  |  | Road Maintenance | 3.34 | CBRMC | a) | 70633.96 | a) | 01/03/19 | e) | - | a) | 70633.96 | a) | 100% | c) | 100% | a) | 16 | Completed | 1
| 056 | [7 empty] | b) | Crucio | b) | 03/21/19 | f) | - | b) | 70633.96 | b) | - | d) | - | b) | 480 |  | 1
[9 empty] | c) | DEL MONTE CACAO | c) | 12/31/19 | g) | 2019-12-31 | c) | 4,872.18 | [7 empty] | 1
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
|  |  | New Corella - New Bohol |  |  | Road Maintenance | 11.54 | MBA | a) | 356226.67 | a) | 01/03/19 | e) | - | a) | 356226.67 | a) | 100% | c) | 100% | a) | 15 | Completed
| 058 | [7 empty] | b) | Crucio | b) | 02/01/19 | f) | - | b) | 356226.67 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 110,982.71 | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | New Corella - New Bohol |  |  | Road Maintenance | 11.54 | CBRMC | a) | 190711.7 | a) | 01/03/19 | e) | - | a) | 190711.7 | a) | 100% | c) | 100% | a) | 16 | Completed | 1
| 058 | [7 empty] | b) | Crucio | b) | 03/22/19 | f) | - | b) | 190711.7 | b) | - | d) | - | b) | 480 |  | 1
[9 empty] | c) | SAN JOSE COCONUT | c) | 12/31/19 | g) | 2019-12-31 | c) | 5,847.18 | [7 empty] | 1
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
1
|  |  | Jct. Carcor - Prk. 9 Bagsak |  |  | Road Maintenance | 2.5 | MBA | a) | 108618.49 | a) | 01/03/19 | e) | - | a) | 108618.49 | a) | 100% | c. | 100% | a) | 15 | Completed
| 059 | [7 empty] | b) | Crucio | b) | 03/01/19 | f) | - | b) | 108618.49 | b) | - | d) |  | b) | 480 |  | 1
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 79952.88 | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
1
|  |  | Jct. Carcor - Prk. 9 Bagsak |  |  | Road Maintenance | 2.5 | CBRMC | a) | 42284.76 | a) | 01/03/19 | e) | - | a) | 42284.76 | a) | 100% | c) | 100% | a) | 16 | Completed
| 059 | [7 empty] | b) | Crucio | b) | 03/22/19 | f) | - | b) | 42284.76 | b) | - | d) | - | b) | 480 |  | 1
[9 empty] | c) | CARCOR MOTOR | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
|  |  | Carcor - Jct. Kauswagan |  |  | Road Maintenance | 4.32 | MBA | a) | 264514.71 | a) | 01/03/19 | e) | - | a) | 264514.71 | a) | 100% | c) | 100% | a) | 15 | Completed | 1
| 060 | [7 empty] | b) | Crucio | b) | 03/18/19 | f) | - | b) | 264514.71 | b) | - | d) |  | b) | 450 |  | 1
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 80733.11 | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | Carcor - Jct. Kauswagan |  |  | Road Maintenance | 4.32 | CBRMC | a) | 48398.27 | a) | 01/03/19 | e) | - | a) | 48398.27 | a) | 100% | c) | 100% | a) | 16 | Completed
| 060 | [7 empty] | b) | Crucio | b) | 03/22/19 | f) | - | b) | 48398.27 | b) | - | d) | - | b) | 480 |  | 1
[9 empty] | c) | CARCOR MOTOR | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
|  |  | Del Pilar - Prk 9 Bagsak - San Jose |  |  | Road Maintenance | 4.99 | MBA | a) | 170215.76 | a) | 01/03/19 | e) | - | a) | 170215.76 | a) | 100% | c) | 100% | a) | 15 | Completed | 1
| 061 | [7 empty] | b) | Crucio | b) | 03/01/19 | f) | - | b) | 170215.76 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 87595.63 | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | Del Pilar - Prk 9 Bagsak - San Jose |  |  | Road Maintenance | 4.99 | CBRMC | a) | 223674.22 | a) | 01/03/19 | e) | - | a) | 223674.22 | a) | 100% | c) | 100% | a) | 16 | Completed | 1
| 061 | [7 empty] | b) | Crucio | b) | 03/22/19 | f) | - | b) | 223674.22 | b) | - | d) | - | b) | 480 |  | 1
[9 empty] | c) | SAN JOSE COCONUT | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
|  |  | San Juan - New Talisay |  |  | Road Maintenance | 5.13 | MBA | a) | 306261.25 | a) | 01/03/19 | e) | - | a) | 306261.25 | a) | 100% | c) | 100% | a) | 15 | Completed | 1
| 063 | [7 empty] | b) | Crucio | b) | 02/01/19 | f) | - | b) | 306261.25 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 85123.48 | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | San Juan - New Talisay |  |  | Road Maintenance | 5.13 | CBRMC | a) | 93906.31 | a) | 01/03/19 | e) | - | a) | 93906.31 | a) | 100% | c) | 100% | a) | 16 | Completed
| 063 | [7 empty] | b) | Crucio | b) | 03/26/19 | f) | - | b) | 93906.31 | b) | - | d) | - | b) | 480 |  | 1
[9 empty] | c) | NEW TALISAY IAWA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
|  |  | San Juan - kauswagan - New Cortez |  |  | Road Maintenance | 3.22 | MBA | a) | 187879.04 | a) | 01/03/19 | e) | - | a) | 187879.04 | a) | 100% | c) | 100% | a) | 15 | Completed | 1
| 064 | [7 empty] | b) | Crucio | b) | 03/18/19 | f) | - | b) | 187879.04 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 3,025.00 | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | San Juan - kauswagan - New Cortez |  |  | Road Maintenance | 3.22 | CBRMC | a) | 63298.26 | a) | 01/03/19 | e) | - | a) | 63298.26 | a) | 100% | c) | 100% | a) | 16 | Completed
| 064 | [7 empty] | b) | Crucio | b) | 03/22/19 | f) | - | b) | 63298.26 | b) | - | d) | - | b) | 480 |  | 1
[9 empty] | c) | SAN JOSE COCONUT | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
|  |  | New Bohol - Jct. El Unido |  |  | Road Maintenance | 2.12 | MBA | a) | 54989.06 | a) | 01/03/19 | e) | - | a) | 54989.06 | a) | 100% | c) | 100% | a) | 15 | Completed
| 065 | [7 empty] | b) | Crucio | b) | 03/01/19 | f) | - | b) | 54989.06 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 21021.99 | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | New Bohol - Jct. El Unido |  |  | Road Maintenance | 2.12 | CBRMC | a) | 58861.64 | a) | 01/03/19 | e) | - | a) | 58861.64 | a) | 100% | c) | 100% | a) | 16 | Completed | 1
| 065 | [7 empty] | b) | Crucio | b) | 03/26/19 | f) | - | b) | 58861.64 | b) | - | d) | - | b) | 480 |  | 1
[9 empty] | c) | MANDISKAB TRIBAL | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
1
|  |  | New Corella - El unido - Jct. Mesaoy |  |  | Road Maintenance | 8.63 | MBA | a) | 388002.46 | a) | 01/03/19 | e) | - | a) | 388002.46 | a) | 100% | c) | 100% | a) | 15 | Completed
| 066 | [7 empty] | b) | Crucio | b) | 02/11/19 | f) | - | b) | 388002.46 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 58142.76 | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | New Corella - El unido - Jct. Mesaoy |  |  | Road Maintenance | 8.63 | CBRMC | a) | 233092.08 | a) | 01/03/19 | e) | - | a) | 233092.08 | a) | 100% | c) | 100% | a) | 16 | Completed | 1
| 066 | [7 empty] | b) | Crucio | b) | 03/26/19 | f) | - | b) | 233092.08 | b) | - | d) | - | b) | 480 |  | 1
[9 empty] | c) | MANDISKAB TRIBAL | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
|  |  | Mesaoy - Dasing |  |  | Road Maintenance | 1.39 | MBA | a) | 29749.5 | a) | 01/03/19 | e) | - | a) | 29749.5 | a) | 100% | c) | 100% | a) | 15 | Completed | 1
| 067 | [7 empty] | b) | Crucio | b) | 03/18/19 | f) | - | b) | 29749.5 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 10000 | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | Mesaoy - Dasing |  |  | Road Maintenance | 1.39 | CBRMC | a) | 54152.71 | a) | 01/03/19 | e) | - | a) | 54152.71 | a) | 100% | c) | 100% | a) | 16 | Completed | 1
| 067 | [7 empty] | b) | Crucio | b) | 03/26/19 | f) | - | b) | 54152.71 | b) | - | d) | - | b) | 480 |  | 1
[9 empty] | c) | MANDISKAB TRIBAL | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
|  |  | Jct. San Juan - Jct. Mesaoy |  |  | Road Maintenance | 1.82 | MBA | a) | 106788.95 | a) | 01/03/19 | e) | - | a) | 106788.95 | a) | 100% | c) | 100% | a) | 15 | Completed | 1
| 068 | [7 empty] | b) | Crucio | b) | 03/01/19 | f) | - | b) | 106788.95 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 17502.68 | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | Jct. San Juan - Jct. Mesaoy |  |  | Road Maintenance | 1.82 | CBRMC | a) | 35180.83 | a) | 01/03/19 | e) | - | a) | 35180.83 | a) | 100% | c) | 100% | a) | 16 | Completed | 1
| 068 | [7 empty] | b) | Crucio | b) | 03/26/19 | f) | - | b) | 35180.83 | b) | - | d) | - | b) | 480 |  | 1
[9 empty] | c) | MANDISKAB TRIBAL | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
|  |  | Mesaoy - Jct. Mahayahay |  |  | Road Maintenance | 4.6 | MBA | a) | 146984.46 | a) | 01/03/19 | e) | - | a) | 146984.46 | a) | 100% | c) | 100% | a) | 15 | Completed | 1
| 069 | [7 empty] | b) | Crucio | b) | 03/18/19 | f) | - | b) | 146984.46 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 7618.27 | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | Mesaoy - Jct. Mahayahay |  |  | Road Maintenance | 4.6 | CBRMC | a) | 160103.65 | a) | 01/03/19 | e) | - | a) | 160103.65 | a) | 100% | c) | 100% | a) | 16 | Completed
| 069 | [7 empty] | b) | Crucio | b) | 03/22/19 | f) | - | b) | 160103.65 | b) | - | d) | - | b) | 480 |  | 1
[9 empty] | c) | MAHAYAHAY IFA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
|  |  | Mesaoy - New bohol |  |  | Road Maintenance | 5.36 | MBA | a) | 165361.13 | a) | 01/03/19 | e) | - | a) | 165361.13 | a) | 100% | c) | 100% | a) | 15 | Completed
| 070 | [7 empty] | b) | Crucio | b) | 03/01/19 | f) | - | b) | 165361.13 | b) | - | d) | - | b) | 480 |  | 1
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 2543.9 | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | Mesaoy - New bohol |  |  | Road Maintenance | 5.36 | CBRMC | a) | 224851.45 | a) | 01/03/19 | e) | - | a) | 224851.45 | a) | 100% | c) | 100% | a) | 16 | Completed
| 070 | [7 empty] | b) | Crucio | b) | 03/26/19 | f) | - | b) | 224851.45 | b) | - | d) | - | b) | 480 |  | 1
[9 empty] | c) | MANDISKAB TRIBAL | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
|  |  | Bdry. Tagum - Baca - New Corella |  |  | Road Maintenance | 13.01 | MBA | a) | 217182.9 | a) | 01/03/19 | e) | - | a) | 217182.9 | a) | 100% | c) | 100% | a) | 15 | Completed | 1
| 071 | [7 empty] | b) | Crucio | b) | 03/18/19 | f) | - | b) | 217182.9 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 19550 | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | Bdry. Tagum - Baca - New Corella |  |  | Road Maintenance | 13.01 | CBRMC | a) | 214256.36 | a) | 01/03/19 | e) | - | a) | 214256.36 | a) | 100% | c) | 100% | a) | 16 | Completed | 1
| 071 | [7 empty] | b) | Crucio | b) | 03/26/19 | f) | - | b) | 214256.36 | b) | - | d) | - | b) | 480 |  | 1
[9 empty] | c) | DURIAN DACUDAO | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
|  |  | Prk. 1, Maunlom - Prk. 6 Maunlom Road |  |  | Road Maintenance | 3.56 | MBA | a) | 150912.87 | a) | 01/03/19 | e) | - | a) | 150912.87 | a) | 100% | c) | 100% | a) | 15 | Completed | 1
| 147 | [7 empty] | b) | Crucio | b) | 03/01/19 | f) | - | b) | 150912.87 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 23025 | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | Prk. 1, Maunlom - Prk. 6 Maunlom Road |  |  | Road Maintenance | 3.56 | CBRMC | a) | 63973.36 | a) | 01/03/19 | e) | - | a) | 63973.36 | a) | 100% | c) | 100% | a) | 16 | Completed | 1
| 147 | [7 empty] | b) | Crucio | b) | 03/22/19 | f) | - | b) | 63973.36 | b) | - | d) | - | b) | 480 |  | 1
[9 empty] | c) | THE BEST VEGETABLE | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
1
|  |  | New Visayas - Binancian |  |  | Road Maintenance | 7.77 | MBA | a) | 14814.34 | a) | 01/03/19 | e) | - | a) | 14814.34 | a) | 100% | c) | 100% | a) | 15 | Completed
| 149 | [7 empty] | b) | Crucio | b) | 03/18/19 | f) | - | b) | 14814.34 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 5,000.00 | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | New Visayas - Binancian |  |  | Road Maintenance | 7.77 | CBRMC | a) | 129495.6 | a) | 01/03/19 | e) | - | a) | 129495.6 | a) | 100% | c) | 100% | a) | 16 | Completed | 1
| 149 | [7 empty] | b) | Crucio | b) | 03/22/19 | f) | - | b) | 129495.6 | b) | - | d) | - | b) | 480 |  | 1
[9 empty] | c) | BUAN IFA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
|  |  | Datu Balong - Prk. Mamalian |  |  | Road Maintenance | 3.46 | MBA | a) | 117454.89 | a) | 01/03/19 | e) | - | a) | 117454.89 | a) | 100% | c) | 39.37% | a) | 15 | Completed | 1
| 150 | [7 empty] | b) | Crucio | b) | 03/18/19 | f) | - | b) | 117454.89 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 10115 | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | Datu Balong - Prk. Mamalian |  |  | Road Maintenance | 3.46 | CBRMC | a) | 59264.42 | a) | 01/03/19 | e) | - | a) | 59264.42 | a) | 100% | c) | 100% | a) | 16 | Completed | 1
| 150 | [7 empty] | b) | Crucio | b) | 03/28/19 | f) | - | b) | 59264.42 | b) | - | d) | - | b) | 480 |  | 1
[9 empty] | c) | DATU BALONG FA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
| A.2 GENERAL FUND CY 2019 |  |  |  |  | Road Maintenance | KM | MBA/CBRMC | a) | 11,618,834.00 | a) | 01/03/19 | e) | - | a) | 11,618,834.00 | a) | 66% | c) | 66% | a) | 42 | See list of Provincial Roads
| Road ID |  | 1. Maintenance Of Various Prov'l. Roads and Bridges Dist 2 |  |  |  | 288.26 |  | b) | Matuguinas | b) | 01/03/19 | f) | - | b) | 11,618,834.00 | b) | - | d) | - | b) | 924 |  | FS
[9 empty] | c) | PEO/CBRMC | c) | 12/31/19 | g) | - | c) | - | [7 empty] | AC
| 11DAN | [9 empty] | d) | - | [11 empty] | AC
[9 empty] | d) | 261 days | d) | - | [11 empty] | AC
|  |  | Cebulano - Mangalcal |  |  | Road Maintenance | 4.17 | MBA | a) | 142161.87 | a) | 01/03/19 | e) | - | a) | 142161.87 | a) | 100% | c) | 100% | a) | 9 | Completed | AC
|  | 073 | [6 empty] | b) | Clar | b) | 2019-01-15 | f) | - | b) | 142161.87 | b) | - | d) | - | b) | 18 |  | 2
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 118,609.29 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | Tubod - basa - Mangalcal |  |  | Road Maintenance | 3.93 | MBA | a) | 156875.9 | a) | 01/03/19 | e) | - | a) | 156875.9 | a) | 100% | c) | 100% | a) | 9 | Completed | 2
| 074 | [7 empty] | b) | Clar | b) | 2019-01-15 | f) | - | b) | 156875.9 | b) | - | d) | - | b) | 18 |  | 2
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 143,372.65 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | Upper Mangalcal - Lower Mangalcal |  |  | Road Maintenance | 2.43 | CBRMC | a) | 79237.14 | a) | 01/03/19 | e) | - | a) | 79237.14 | a) | 100% | c) | 100% | a) | 9 | Completed | 2
| 078 | [7 empty] | b) | Clar | b) | 2019-01-14 | f) | - | b) | 79237.14 | b) | - | d) | - | b) | 27 |  | 2
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 69,430.97 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | Jct. Highway Carmen - Mangalcal - Tubod |  |  | Road Maintenance | 11.34 | MBA | a) | 463135.67 | a) | 01/03/19 | e) | - | a) | 463135.67 | a) | 100% | c) | 100% | a) | 9 | Completed | 2
| 082 | [7 empty] | b) | Clar | b) | 01/10/19 | f) | - | b) | 463135.67 | b) | - | d) | - | b) | 45 |  | 2
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 170,106.43 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | Jct. Highway Carmen - Mangalcal - Tubod |  |  | Road Maintenance | 11.34 | CBRMC | a) | 253557.37 | a) | 01/03/19 | e) | - | a) | 253557.37 | a) | 100% | c) | 100% | a) | 10 | Completed | 2
| 082 | [7 empty] | b) | Maligro | b) | 03/25/19 | f) | - | b) | 253557.37 | b) | - | d) | - | b) | 40 |  | 2
[9 empty] | c) | TUBOD CENTRO LOWER IRRIGATORS ASSOCIATION | c) | 09/25/19 | g) | 2019-12-31 | c) | - | [7 empty] | 2
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 2
|  |  | Jct. Highway Sto. Niño - Kabanlakan - La Paz |  |  | Road Maintenance | 2.13 | MBA | a) | 76067.88 | a) | 01/03/19 | e) | - | a) | 76067.88 | a) | 100% | c) | 100% | a) | 9 | Completed | 2
| 084 | [7 empty] | b) | Clar | b) | 01/10/19 | f) | - | b) | 76067.88 | b) | - | d) | - | b) | 45 |  | 2
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 66,477.91 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | Ising - Sto Niño |  |  | Road Maintenance | 2.07 | CBRMC | a) | 82413.14 | a) | 01/03/19 | e) | - | a) | 82413.14 | a) | 100% | c) | 100% | a) | 5 | Completed | 2
| 085 | [7 empty] | b) | Clar | b) | 01/17/19 | f) | - | b) | 82413.14 | b) | - | d) | - | b) | 15 |  | 2
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 27,093.24 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | Ising - Sadpodon - Taba - Dila -Dila |  |  | Road Maintenance | 5.68 | MBA | a) | 248941.33 | a) | 01/03/19 | e) | - | a) | 248941.33 | a) | 100% | c) | 100% | a) | 9 | Completed | 2
| 086 | [7 empty] | b) | Clar | b) | 01/12/19 | f) | - | b) | 248941.33 | b) | - | d) | - | b) | 27 |  | 2
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 82,329.02 | [7 empty] | 2
[9 empty] | d) | - | d) | - |  |  |  | . | [7 empty] | 2
2
|  |  | Tuganay - taba |  |  | Road Maintenance | 4.27 | CBRMC | a) | 291377.9 | a) | 01/03/19 | e) | - | a) | 291377.9 | a) | 70% | c) | 70% | a) | 9 | Completed
| 087 | [7 empty] | b) | Clar | b) | 01/09/19 | f) | - | b) | 291377.9 | b) | - | d) | - | b) | 27 |  | 2
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 12/31/2019 | c) | 238,412.28 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | Jct. Highway Tuganay - Taba |  |  | Road Maintenance | 4.4 | MBA | a) | 32972.82 | a) | 01/03/19 | e) | - | a) | 32972.82 | a) | 65% | c) | 65% | a) | 9 | Completed | 2
| 088 | [7 empty] | b) | Clar | b) | 01/22/19 | f) | - | b) | 32972.82 | b) | - | d) | - | b) | 18 |  | 2
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 12/31/2019 | c) | 22,639.09 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | Jct. Highway Ising - Magsaysay |  |  | Road Maintenance | 10.84 | CBRMC | a) | 417818.12 | a) | 01/03/19 | e) | - | a) | 417818.12 | a) | 60% | c) | 60% | a) | 10 | Completed | 2
| 089 | [7 empty] | b) | Clar | b) | 01/22/19 | f) | - | b) | 417818.12 | b) | - | d) | - | b) | 50 |  | 2
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 12/31/2019 | c) | 313,488.39 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | New Camiling - Alejal - Lower Magsaysay |  |  | Road Maintenance | 6.73 | MBA | a) | 240878.08 | a) | 01/03/19 | e) | - | a) | 240878.08 | a) | 80% | c) | 80% | a) | 4 | Completed | 2
| 091 | [7 empty] | b) | Clar | b) | 01/22/19 | f) | - | b) | 240878.08 | b) | - | d) | - | b) | 20 |  | 2
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 12/31/2019 | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | Jct. highway Tuganay - Anibongan |  |  | Road Maintenance | 3.66 | CBRMC | a) | 150684.44 | a) | 01/03/19 | e) | - | a) | 150684.44 | a) | 100% | c) | 100% | a) | 6 | Completed | 2
| 094 | [7 empty] | b) | Clar | b) | 01/22/19 | f) | - | b) | 150684.44 | b) | - | d) | - | b) | 18 |  | 2
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 12/31/2019 | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | Anibongan - Guadalupe |  |  | Road Maintenance | 2.48 | MBA | a) | 91325.06 | a) | 01/03/19 | e) | - | a) | 91325.06 | a) | 100% | c) | 100% | a) | 9 | Completed | 2
| 095 | [7 empty] | b) | Clar | b) | 01/23/19 | f) | - | b) | 91325.06 | b) | - | d) | - | b) | 18 |  | 2
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 12/31/2019 | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | Tuganay - Anibongan - San Isidro |  |  | Road Maintenance | 7.22 | CBRMC | a) | 139979.8 | a) | 01/03/19 | e) | - | a) | 139979.8 | a) | 100% | c) | 100% | a) | 9 | Completed | 2
| 096 | [7 empty] | b) | Clar | b) | 01/24/19 | f) | - | b) | 139979.8 | b) | - | d) | - | b) | 36 |  | 2
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 12/31/2019 | c) | 1890.37 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | Jct. Anibongan - Prk. 2, 7, 5, San Isidro |  |  | Road Maintenance | 3.14 | MBA | a) | 104378.03 | a) | 01/03/19 | e) | - | a) | 104378.03 | a) | 100% | c) | 100% | a) | 10 | Completed | 2
| 097 | [7 empty] | b) | Clar | b) | 01/24/19 | f) | - | b) | 104378.03 | b) | - | d) | - | b) | 20 |  | 2
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 12/31/2019 | c) | 56,087.50 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | Anibongan - Salvacion - Cabay-angan |  |  | Road Maintenance | 6.93 | CBRMC | a) | 415461.61 | a) | 01/03/19 | e) | - | a) | 415461.61 | a) | 100% | c) | 100% | a) | 9 | Completed | 2
| 098 | [7 empty] | b) | Clar | b) | 01/25/19 | f) | - | b) | 415461.61 | b) | - | d) | - | b) | 45 |  | 2
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 12/31/2019 | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | Jct. Highway Guadalupe - Bdry. Tagum |  |  | Road Maintenance | 7.9 | MBA | a) | 456131.09 | a) | 01/03/19 | e) | - | a) | 456131.09 | a) | 100% | c) | 100% | a) | 9 | Completed | 2
| 101 | [7 empty] | b) | Clar | b) | 01/25/19 | f) | - | b) | 456131.09 | b) | - | d) | - | b) | 18 |  | 2
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 12/31/2019 | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | Jct. Highway Guadalupe - Bdry. Tagum |  |  | Road Maintenance | 7.9 | CBRMC | a) | 228201.66 | a) | 01/03/19 | e) | - | a) | 228201.66 | a) | 100% | c) | 100% | a) | 8 | Completed | 2
| 101 | [7 empty] | b) | Maligro | b) | 03/25/19 | f) | - | b) | 228201.66 | b) | - | d) | - | b) | 40 |  | 2
[9 empty] | c) | LAMPIA PAG-ASA IRRIGATORS ASSOCIATION, INC. | c) | 12/25/19 | g) | 12/31/2019 | c) | - | [7 empty] | 2
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 2
|  |  | Poblacion Dujali - Prk. 8 Dujali |  |  | Road Maintenance | 8.2 | MBA | a) | 285600.05 | a) | 01/03/19 | e) | - | a) | 285600.05 | a) | 100% | c) | 100% | a) | 10 | Completed | 2
| 105 | [7 empty] | b) | Clar | b) | 01/28/19 | f) | - | b) | 285600.05 | b) | - | d) | - | b) | 50 |  | 2
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 12/31/2019 | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | Dujali - San Isidro |  |  | Road Maintenance | 3 | CBRMC | a) | 130319.3 | a) | 01/03/19 | e) | - | a) | 130319.3 | a) | 100% | c) | 100% | a) | 8 | Completed | 2
| 107 | [7 empty] | b) | Gamad | b) | 01/28/19 | f) | - | b) | 130319.3 | b) | - | d) | - | b) | 30 |  | 2
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 12/31/2019 | c) | 45,943.12 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | Prk. 5, RJS - Prk. 6 New Casay |  |  | Road Maintenance | 2.73 | MBA | a) | 235277 | a) | 01/03/19 | e) | - | a) | 235277 | a) | 100% | c) | 100% | a) | 2 | Completed | 2
| 109 | [7 empty] | b) | Gamad | b) | 01/28/19 | f) | - | b) | 235277 | b) | - | d) | - | b) | 6 |  | 2
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 12/31/2019 | c) | 90,745.35 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | Prk. 5 - Prk. 1 Pawas Dujali |  |  | Road Maintenance | 2.18 | CBRMC | a) | 76067.68 | a) | 01/03/19 | e) | - | a) | 76067.68 | a) | 100% | c) | 100% | a) | 10 | Completed | 2
| 112 | [7 empty] | b) | Gamad | b) | 01/18/19 | f) | - | b) | 76067.68 | b) | - | d) | - | b) | 20 |  | 2
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 12/31/2019 | c) | 40,112.50 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | Dujali - Balisong - Magupising |  |  | Road Maintenance | 5.52 | MBA | a) | 260591.93 | a) | 01/03/19 | e) | - | a) | 260591.93 | a) | 100% | c) | 100% | a) | 4 | Completed | 2
| 113 | [7 empty] | b) | Gamad | b) | 01/09/19 | f) | - | b) | 260591.93 | b) | - | d) | - | b) | 8 |  | 2
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 12/31/2019 | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | Dujali - Pawas - San Vicente |  |  | Road Maintenance | 4.42 | CBRMC | a) | 139536.42 | a) | 01/03/19 | e) | - | a) | 139536.42 | a) | 100% | c) | 100% | a) | 10 | Completed | 2
| 117 | [7 empty] | b) | Gamad | b) | 01/22/19 | f) | - | b) | 139536.42 | b) | - | d) | - | b) | 18 |  | 2
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 12/31/2019 | c) | 52,133.86 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | Jct. Salvacion - San Vicente - Cabay-angan |  |  | Road Maintenance | 3.45 | MBA | a) | 247460.9 | a) | 01/03/19 | e) | - | a) | 247460.9 | a) | 100% | c) | 100% | a) | 10 | Completed | 2
| 118 | [7 empty] | b) | Gamad | b) | 01/23/19 | f) | - | b) | 247460.9 | b) | - | d) | - | b) | 18 |  | 2
[9 empty] | c) | PEO | c) | 02/31/19 | g) | 12/31/2019 | c) | 151,887.50 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | Jct. Salvacion - San Vicente - Cabay-angan |  |  | Road Maintenance | 3.45 | CBRMC | a) | 152134.44 | a) | 01/03/19 | e) | - | a) | 152134.44 | a) | 100% | c) | 100% | a) | 8 | Completed | 2
| 118 | [7 empty] | b) | Gamad | b) | 03/26/19 | f) | - | b) | 152134.44 | b) | - | d) | - | b) | 36 |  | 2
[9 empty] | c) | BALISONG SAN VICENTE IRRIGATORS ASSOCIATION | c) | 12/26/19 | g) | 12/31/2019 | c) | [8 empty] | 2
[9 empty] | d) | 3 quarters | d) | - | [10 empty] | Completed | 2
|  |  | Dujali - San Miguel |  |  | Road Maintenance | 3.95 | MBA | a) | 101202.04 | a) | 01/03/19 | e) | - | a) | 101202.04 | a) | 80% | c) | 90% | a) | 11 |  | 2
| 119 | [7 empty] | b) | Gamad | b) | 01/10/19 | f) | - | b) | 101202.04 | b) | - | d) | - | b) | 22 |  | 2
[9 empty] | c) | PEO | c) | 12/31/19 | g) | - | c) | 90,350.03 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | San Miguel - Casig-ang |  |  | Road Maintenance | 2.55 | CBRMC | a) | 79237.14 | a) | 01/03/19 | e) | - | a) | 79237.14 | a) | 100% | c) | 100% | a) | 10 | Completed | 2
| 122 | [7 empty] | b) | Gamad | b) | 01/24/19 | f) | - | b) | 79237.14 | b) | - | d) | - | b) | 10 |  | 2
[9 empty] | c) | BALISONG SAN VICENTE IRRIGATORS ASSOCIATION | c) | 12/31/19 | g) | 12/31/2019 | c) | 40,112.50 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | Prk. Magsaysay - Lunga-og - Dalisay |  |  | Road Maintenance | 2.81 | MBA | a) | 79762.14 | a) | 01/03/19 | e) | - | a) | 79762.14 | a) | 100% | c) | 100% | a) | 8 | Completed | 2
| 127 | [7 empty] | b) | Gamad | b) | 01/30/19 | f) | - | b) | 79762.14 | b) | - | d) | - | b) | 8 |  | 2
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 12/31/2019 | c) | 40,612.50 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | Prk. Apitong - Upper Balisong - Dalisay |  |  | Road Maintenance | 4.6 | CBRMC | a) | 137846.03 | a) | 01/03/19 | e) | - | a) | 137846.03 | a) | 100% | c) | 100% | a) | 8 | Completed | 2
| 128 | [7 empty] | b) | Gamad | b) | 01/31/19 | f) | - | b) | 137846.03 | b) | - | d) | - | b) | 8 |  | 2
[9 empty] | c) | BALISONG SAN VICENTE IRRIGATORS ASSOCIATION | c) | 12/31/19 | g) | 12/31/2019 | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | Sitio Paradise - Magkakaisa - Esperanza |  |  | Road Maintenance | 1.75 | MBA | a) | 66552.75 | a) | 01/03/19 | e) | - | a) | 66552.75 | a) | 100% | c) | 100% | a) | 8 | Completed | 2
| 129 | [7 empty] | b) | 79762.14 | b) | 01/22/19 | f) | - | b) | 66552.75 | b) | - | d) | - | b) | 8 |  | 2
[9 empty] | c) | Gamad | c) | 12/31/19 | g) | 12/31/2019 | c) | 22,246.26 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | Los Amigos 1 - Esperanza - Los Amigos 2 |  |  | Road Maintenance | 3.59 | CBRMC | a) | 101202.04 | a) | 01/03/19 | e) | - | a) | 101202.04 | a) | 100% | c) | 100% | a) | 10 | Completed | 2
| 130 | [7 empty] | b) | Gamad | b) | 01/24/19 | f) | - | b) | 101202.04 | b) | - | d) | - | b) | 20 |  | 2
[9 empty] | c) | BALISONG SAN VICENTE IRRIGATORS ASSOCIATION | c) | 12/31/19 | g) | 12/31/2019 | c) | 50,837.50 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | Mugas - Lunga-og |  |  | Road Maintenance | 2.68 | MBA | a) | 66552.75 | a) | 01/03/19 | e) | - | a) | 91,693.64 | a) | 100% | c) | 100% | a) | 6 | Completed | 2
| 132 | [7 empty] | b) | 79762.14 | b) | 01/17/19 | f) | - | b) | 91,693.64 | b) | - | d) | - | b) | 24 |  | 2
[9 empty] | c) | Gamad | c) | 12/31/19 | g) | 12/31/2019 | c) | 50,837.50 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | Pantaron - Mugas |  |  | Road Maintenance | 3.35 | CBRMC | a) | 101202.04 | a) | 01/03/19 | e) | - | a) | 101202.04 | a) | 100% | c) | 100% | a) | 9 | Completed | 2
| 133 | [7 empty] | b) | Gamad | b) | 01/23/19 | f) | - | b) | 101202.04 | b) | - | d) | - | b) | 18 |  | 2
[9 empty] | c) | BALISONG SAN VICENTE IRRIGATORS ASSOCIATION | c) | 12/31/19 | g) | 12/31/2019 | c) | 90,349.93 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | Sto. Tomas - Bdry. Mamacao |  |  | Road Maintenance | 4.9 | MBA | a) | 110710.44 | a) | 01/03/19 | e) | - | a) | 110710.44 | a) | 100% | c) | 100% | a) | 10 | Completed | 2
| 135 | [7 empty] | b) | 79762.14 | b) | 01/21/19 | f) | - | b) | 110710.44 | b) | - | d) | - | b) | 40 |  | 2
[9 empty] | c) | Gamad | c) | 12/31/19 | g) | 12/31/2019 | c) | 50,837.50 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | Fd. Rd. 3 - San Jose |  |  | Road Maintenance | 4.55 | CBRMC | a) | 147367.49 | a) | 01/03/19 | e) | - | a) | 147367.49 | a) | 100% | c) | 100% | a) | 10 | Completed | 2
| 136 | [7 empty] | b) | Gamad | b) | 01/25/19 | f) | - | b) | 147367.49 | b) | - | d) | - | b) | 30 |  | 2
[9 empty] | c) | BALISONG SAN VICENTE IRRIGATORS ASSOCIATION | c) | 12/31/19 | g) | 12/31/2019 | c) | 56,174.69 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | Menzi - balagunan - Tulalian |  |  | Road Maintenance | 10.63 | MBA | a) | 520167.79 | a) | 01/03/19 | e) | - | a) | 520167.79 | a) | 100% | c) | 100% | a) | 6 | Completed | 2
| 138 | [7 empty] | b) | 79762.14 | b) | 01/07/19 | f) | - | b) | 520167.79 | b) | - | d) | - | b) | 18 |  | 2
[9 empty] | c) | Gamad | c) | 12/31/19 | g) | 12/31/2019 | c) | 204,850.57 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | Jct. Bdry. Tagum - Talomo |  |  | Road Maintenance | 12.01 | CBRMC | a) | 407429.19 | a) | 01/03/19 | e) | - | a) | 407429.19 | a) | 100% | c) | 100% | a) | 10 | Completed | 2
| 145 | [7 empty] | b) | Gamad | b) | 01/11/19 | f) | - | b) | 407429.19 | b) | - | d) | - | b) | 50 |  | 2
[9 empty] | c) | BALISONG SAN VICENTE IRRIGATORS ASSOCIATION | c) | 12/31/19 | g) | 12/31/2019 | c) | 168,544.84 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | San Jose - Sitio Mahayahay, Magwawa |  |  | Road Maintenance | 0.84 | MBA | a) | 7919.35 | a) | 01/03/19 | e) | - | a) | 7919.35 | a) | 100% | c) | 100% | a) | 2 | Completed | 2
| 151 | [7 empty] | b) | 79762.14 | b) | 01/16/19 | f) | - | b) | 7919.35 | b) | - | d) | - | b) | 8 |  | 2
[9 empty] | c) | Gamad | c) | 12/31/19 | g) | 12/31/2019 | c) | 1,509.27 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| B. 20% DEVELOPMENT FUND CY 2019 | [22 empty] | FS
| Road ID |  | 1. Rehabilitation Of Various Prov'l. Roads and Bridges Dist. 1 |  |  | Road Rehabilitation | KM | MBA | a) | 41465029 | a) | 01/03/19 | e) | - | a) | 41465029 | a) | - | c) | - | a) | 46 | See list of Provincial Roads | FS
[7 empty] | 109.55 |  | b) | Paraguya | b) | 01/03/19 | f) | - | b) | 41465029 | b) | - | d) | - | b) | 920 |  | AC
| 11DAN | [7 empty] | c) | PEO | c) | 12/31/19 | g) | - | c) | - | [7 empty] | AC
[11 empty] | d) | - | [11 empty] | AC
[9 empty] | d) | 261 days | d) | - | [11 empty] | AC
[6 empty] | Road Rehabilitation |  |  | a. )P 500,000.00 |  | a.) 01/31/19 |  |  |  | a.) 500,000.00 | [8 empty] | 1
|  |  | Purok 10 Pob. Road, New Corella | [7 empty] | b.) Feb. 16, 2019 |  |  |  | b.) 500,000.00 | [7 empty] | Completed | 1
[13 empty] | g.) Feb. 28, 2019 | [10 empty] | 1
1
[6 empty] | Road Rehabilitation |  |  | a.)1,815,000.00 |  | a.) 01/31/19 |  |  |  | a.) 1,815,000.00 | [8 empty] | 1
|  |  | Purok 7 Pob- Jct. New Sambog | [7 empty] | b.)March 1, 2019 |  |  |  | b.) 1,815,000.00 | [7 empty] | Completed | 1
[13 empty] | g.) May 15, 2019 | [10 empty] | 1
1
[6 empty] | Road Rehabilitation |  |  | a.) 1,389,000.00 |  | a.) 01/31/19 |  |  |  | a.) 1,389,000.00 | [7 empty] | Completed with a savings of P303,898.08 furtherance and is for implementation | 1
|  |  | Del Pilar- El Unido Road | [5 empty] | b.) Fabian |  | b.) March 18,2019 |  |  |  | a.) 1,389,000.00 | [8 empty] | 1
[13 empty] | g.) May 8, 2019 | [10 empty] | 1
|  |  | SUPPLEMENTAL BUDGET NO 4 CY 2019 / CONTINUING APPROPRIATION | [20 empty] | AC
AC
[9 empty] | a.) 7,742,775.95 | [5 empty] | a.) 7,742,775.95 | [7 empty] | Waiting for the delivery of materials | 1
|  |  | Impvt. of Km. 9 Sagayen - Sawata Provincial Road Phase II | [5 empty] | b.) Kenny | [5 empty] | b.) 7,742,775.95 | [8 empty] | 1
1
1
| Road ID |  | 1. Rehabilitation Of Various Prov'l. Roads and Bridges Dist 2 |  |  | Road Rehabilitation | KM | Admin | a) | 46740117 | a) | 01/03/19 | [10 empty] | See list of Provincial Roads | AC
[7 empty] | 115.62 |  | b) | Matuguinas | b) | - | [11 empty] | AC
| 11DAN | [7 empty] | c) | PEO | c) | - | [11 empty] | AC
[11 empty] | d) | - | [11 empty] | AC
[9 empty] | d) | 261 days | d) | - | [11 empty] | AC
[6 empty] | Road Rehabilitation |  |  | a.) 515,000.00 |  | a.) 03/12/19 |  |  |  | a.) 515,000.00 | [8 empty] | 2
|  |  | Jct. Highway -Tubod - Bagong Silang | [5 empty] | b.) Clar |  | b.) March 18, 2019 |  |  |  | b.) 515,000.00 | [7 empty] | Completed | 2
[13 empty] | g.) June 15, 2019 | [10 empty] | 2
2
[6 empty] | Road Rehabilitation |  |  | a.) 390,000.00 |  | a.) 03/12/19 |  |  |  | a.) 390,000.00 | [8 empty] | 2
|  |  | Cebulano- Luceta | [5 empty] | b.) Clar |  | b.) March 8, 2019 |  |  |  | b.) 390,000.00 | [7 empty] | Completed | 2
[13 empty] | g.) June 15, 2019 | [10 empty] | 2
2
[6 empty] | Road Rehabilitation |  |  | a.) 295,000.00 |  | a.) 03/12/19 |  |  |  | a.) 295,000.00 | [8 empty] | 2
|  |  | Lower Asuncion - Upper Asuncion | [5 empty] | b.) Clar |  | b.) March 18, 2019 |  |  |  | b.) 295,000.00 | [7 empty] | Completed | 2
[13 empty] | g.) June 15, 2019 | [10 empty] | 2
2
[6 empty] | Road Rehabilitation |  |  | a.) 1,220,000.00 |  | a.) 03/12/19 |  |  |  | a.) 1,220,000.00 | [8 empty] | 2
|  |  | Jct. Highway - Sto. Nino - La Paz - San Vicente | [5 empty] | b.)Obar |  | b.) March 18, 2019 |  |  |  | b.) 1,220,000.00 | [7 empty] | Completed | 2
[13 empty] | g.) Sept. 30, 2019 | [10 empty] | 2
2
|  |  | Alejal - Alemag |  |  | Road Rehabilitation | 1.79 |  | a) | 970000 | a) | 2019-03-18 | e) | - | a) | 970000 | a) | 100% | c) | 100% | a) | 7 | Completed. Financially completed | 2
| 092 | [7 empty] | b) | Gamad/Clar | b) | 2019-05-20 | f) | - | b) | 970000 | b) | 100 | d) | 0% | b) | 20 |  | 2
[9 empty] | c) | - | c) | 2019-09-12 | g) | Sept. 30, 2019 | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
[6 empty] | Road Rehabilitation |  |  | a.) 640,000.00 |  | a.) 03/12/19 |  |  |  | a.) 640,000.00 | [8 empty] | 2
|  |  | Mabaus - Cabay -angan | [5 empty] | b.)Clar |  | b.) Maech 18, 2019 |  |  |  | a.) 640,000.00 | [7 empty] | Completed | 2
[13 empty] | g.) July 30, 2019 | [10 empty] | 2
2
[6 empty] | Road Rehabilitation |  |  | a.) 280,000.00 |  | a.) 03/12/19 |  |  |  | a.) 280,000.00 | [8 empty] | 2
|  |  | Mabaus - Salvacion | [5 empty] | b.)Clar |  | b.) March 18, 2019 |  |  |  | a.) 280,000.00 | [8 empty] | 2
[13 empty] | g.) June 30, 2019 | [9 empty] | Completed | 2
2
|  |  | Dujali - New Casay |  |  |  | 3.2 | Admin | a) | 640000 | a) | 2019-05-16 | e) | - | a) | 640000 | a) | 100% | c) | 100% | a) | 10 |  | 2
| 106 | [7 empty] | b) | Gamad/Clar | b) | 2019-06-17 | f) | 40 | b) | 640000 | b) |  | d) | - | b) | 40 | Completed | 2
[9 empty] | c) | - | c) |  | g) | 10/15/2019 | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
[6 empty] | Road Rehabilitation |  |  | a.) 450,000.00 |  | a.) 03/12/19 |  |  |  | a.) 450,000.00 | [8 empty] | 2
|  |  | New Casay - Bugtong Talisay | [5 empty] | b.)Clar |  | b.) March 18, 2019 |  |  |  | a.) 450,000.00 | [7 empty] | Completed | 2
[13 empty] | g.)June 30, 2019 | [10 empty] | 2
2
[6 empty] | Road Rehabilitation |  |  | a.)220,000.00 |  | a.) 03/12/19 |  |  |  | a.)220,000.00 |  | a.) 100 % |  | c.)100% |  |  |  |  | 2
|  |  | Purok 6 Cabay-angan - Esti | [5 empty] | b.) Gamad |  | b.) March 18, 2019 |  |  |  | a.)220,000.00 | [7 empty] | Completed | 2
[13 empty] | g.) June 30, 2019 | [10 empty] | 2
2
[6 empty] | Road Rehabilitation |  |  | a.)250,000.00 |  | a.) March 12, 2019 | [5 empty] | a.) 100 % |  | c.)100% |  |  |  |  | 2
|  |  | Dujali - Sitio Pawas | [5 empty] | b.) Gamad |  | b.) March 18, 2019 | [11 empty] | Completed | 2
[13 empty] | g.) Jun 30, 2019 | [10 empty] | 2
2
[6 empty] | Road Rehabilitation |  |  | a.) 280,000.00 |  | a.) March 12, 2019 | [5 empty] | a.) 100 % |  | c.)100% |  |  |  |  | 2
|  |  | Purok 1 to Purok 2 Sitio Pawas | [6 empty] | b.) Gamad | b.) March 18, 2019 | [11 empty] | Completed | 2
[13 empty] | g.) Jun 30, 2019 | [10 empty] | 2
2
|  |  | San Miguel - Crossing Kinamayan |  |  | Road Rehabilitation | 2.8 | Admin | a) | 560000 | a) | 2019-06-25 | e) | - | a) | 560000 | a.) 100 % |  | c.)100% |  | a) | - |  | 2
| 120 | [7 empty] | b) | Nasol | b) | Sept. 19, 2019 | f) | - | b) | 560000 | b) | - | d) | - | b) | - | Completed | 2
[9 empty] | c) | - | c) | - | g) | Nov. 30, 2019 | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | Kinamayan - Lunga-og |  |  | Road Rehabilitation | 2.59 | Admin | a) | 520000 | a) | 2019-03-18 | e) | - | a) | 520000 | a) | 100% | c) | 100% | a) | 9 | Completed | 2
| 126 | [7 empty] | b) | Gamad/Clar | b) | 5/202/019 | f) | - | b) | 520000 | b) | - | d) | - | b) | 36 |  | 2
[9 empty] | c) | - | c) |  | g) | Sept. 30, 2019 | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
[9 empty] | a.) 540,000.00 |  | a.) March 12, 2019 |  |  |  | a.) 540,000.00 |  | a.)100% |  | c.)100% |  |  |  | Completed | 2
|  |  | Nafco - Bobongon |  |  | Road Rehabilitation |  |  | b. Gamad |  | b.) march 18, 2019 |  |  |  | b.) 540,000.00 | [8 empty] | 2
[13 empty] | g.) June 30, 2019 | [10 empty] | 2
2
2
|  |  | Prk. Narafil - Prk. Daisy Magupising |  |  | Road Rehabilitation | 19.16 | Admin | a) | 300117 | a) | 2019-06-25 | e) | - | a) | 300117 | a) | 100% | c) | 100% | a) | - | Completed | 2
| 148 | [7 empty] | b) | Gamad/Clar | b) | Sept. 16, 2019 | f) | - | b) | 300117 | b) | - | d) | - | b) | - |  | 2
[9 empty] | c) | - | c) | - | g) | Oct. 18, 2019 | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 2. Various of Local Roads & Drainage Development Project (Provincewide) |  |  |  |  | Road Drainage rehabiliated |  | Admin | a) | 15000000 | [12 empty] | See projects listed below | 2
[9 empty] | b) | Paraguya | [13 empty] | AC
[9 empty] | c) | PEO | [13 empty] | AC
[9 empty] | d) | - | [13 empty] | AC
|  |  | Rehab. of Anibongan-Salvacion-Cabay-angan Provincial Road with Drainage |  |  | Road Drainage rehabiliated | - | - | a) | 2000000 | a) | 2019-01-14 | e) | - | a) | 2000000 | a) | 100% | c) | 100% | a) | 1 | Completed | 2
| 2.1 | [7 empty] | b) | Toquero | b) | 2019-05-22 | f) | - | b) | 2000000 | b) | - | d) | - | b) | 4 | Fiancial obligation still on process | 2
[9 empty] | c) | PEO | c) | 2019-08-04 | g) | Dec. 31, 2019 | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | Rehab./Impv't. of Sto. Tomas-Bdry. Mamacao Provincial Road |  |  | Road Drainage rehabiliated | - | Admin | a) | 1500000 | a) | 2019-01-14 | e) | - | a) | 1500000 | a) | 100% | c) | 100% | a) | - | Completed Financial obligation on process
| 2.4 | [7 empty] | b) | Toquero | b) | 2019-05-31 | f) | 60 | b) | 1500000 | b) | - | d) | - | b) | - |  | 2
[9 empty] | c) | PEO | c) | 2019-07-15 | g) | Dec. 31, 2019 | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 4. Various Government Buildings and Facilities Development Project (Provincewide) |  |  |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of recipients | - | Admin | a) | 27000000 | [12 empty] | See projects listed below | 2
[9 empty] | b) | Medalla | [13 empty] | AC
[9 empty] | c) | PEO | [13 empty] | AC
[9 empty] | d) | - | [13 empty] | AC
|  |  | Const. of GYM Bleacher at Suaybaguio Rina, Elem. School |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of recipients | - | #REF! | a) | 1000000 | a) | - | e) | - | a) | 1000000 | a) | 100% | c) | 100% | a) | - | Completed | 1
|  | 11 | [6 empty] | b) | Mayang | b) | 6/3/2019 | f) | - | b) | 1000000 | b) | 64 | d) | 0% | b) | - |  | 1
[9 empty] | c) | PEO | c) | 8/01/2019 | g) |  | c) | - | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
| 5. Stimulus Projects for Various Barangays a. 20% Development Fund CY 2019 |  |  |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | Admin | a) | 41500000 | [12 empty] | See projects listed below | 2
[9 empty] | b) | Medalla | [13 empty] | AC
[9 empty] | c) | PEO | [13 empty] | AC
[9 empty] | d) | - | [13 empty] | AC
AC
| IGCS | [22 empty] | 2
| 5.42 |  | Rehab. Of Health Center, Aumbay, IGCS |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) | Feb. 28, 2019 | e) | - | a) | 500000 | a) |  | c) | 48.32% | a) | 3 | Completed Financial obligation on process | AC
[9 empty] | b) | Pacquiao | b) | 7/10/2019 | f) | - | b) | 500000 | b) | - | d) |  | b) | 15 |  | 2
[9 empty] | c) | Admin | c) | 10/7/2019 | g) | - | c) | - | [7 empty] | 2
[9 empty] | d) | 90 CD | d) | - | [11 empty] | 2
| 5.46 |  | Rehab. Of Brgy. Health Center, Mambago-A, IGCS |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) | Feb. 28, 2019 | e) | - | a) | 500000 | a) |  | c) | 75.61% | a) | 3 | Completed Financial obligation on process | 2
[9 empty] | b) | Ganaba | b) | 07/2019 | f) | - | b) | 500000 | b) |  | d) |  | b) | 15 |  | 2
[9 empty] | c) | Admin | c) | 8/23/2019 | g) | - | c) | - | [7 empty] | 2
[9 empty] | d) | 45 CD | d) | - | [11 empty] | 2
| 6. Rural Electrification Project (Provincewide) |  |  |  |  | Powerlines/posts installed & rehabilitated | - | - | a) | 5000000 | [12 empty] | See projects listed below | 2
[9 empty] | b) | Kim Pao Lu | [13 empty] | AC
[9 empty] | c) | - | [13 empty] | AC
[9 empty] | d) | - | [13 empty] | AC
C. 5% CALAMITY FUND CY 2019
| 3 |  | Improvement of roads, drainage and canal |  |  | Protection dikes/slope protection | - | - | a) | 3000000 | [12 empty] | See projects listed below | 2
[9 empty] | b) | Paraguya | [13 empty] | AC
[9 empty] | c) | PEO | [13 empty] | AC
[9 empty] | d) | - | [13 empty] | AC
| a. |  | Rehab./Impv't. of New Casay-Bugtong Talisay Provincial Road (Ph.II) |  |  | creeks and canRoads/Draiange/canals rehab/improved | - | - | a) | 500000 | a) | 2019-03-12 | e) | - | a) | 500000 | a) | 100% | c) | 100% | a) | 12 | Completed | AC
[9 empty] | b) | Toquero | b) | 2019-05-30 | f) | - | b) | 500000 | b) | - | d) | - | b) | 120 |  | 2
[9 empty] | c) | Admin | c) | 2019-07-30 | g) |  | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | Mark | Municipality/City |  | Color
|  |  | 1 | Asuncion |  | Red
|  |  | 2 | B.E. Dujali |  | Yellow
|  | GF- GENERAL FUND | 3 | Carmen |  | Blue | [10 empty] | TF - TRUST FUND (NATIONAL FUNDED PROJECT)
|  | 20% DF - 20% DEV'T. FUND | 4 | Kapalong |  | Pink | [10 empty] | a) SLRF - Special Local Road Fund
|  | 5% CF - 5% CALAMITY FUND | 5 | New Corella |  | Gray | [10 empty] | b) KALSADA - Konkreto at Ayos na Lansangan Tungo sa Pangkalahatang Kaunlaran
|  | CO - CAPITAL OUTLAY | 6 | San Isidro |  | Orange | [10 empty] | c) PRDP - Philippine Rural Development Projects
|  | CONG. FUND - CONGRESSIONAL FUND | 7 | Sto Tomas |  | Sky Blue | [10 empty] | d) SELAP - Support to Emergency and Livelihood Assistance Project
|  |  | 8 | Talaingod |  | Violet | [10 empty] | e) PAMANA - Payapa at Masaganang Pamayanan
|  | SEF - SPECIAL EDUCATIONAL UFND | 9 | Panabo City |  | Brown | [10 empty] | f) CBRMC - Community Based Road Maintenance Contracting
|  |  | 10 | IGACOS |  | Yellow Green | [10 empty] | g) MBC - Maintenance by Contract
|  |  | 11 | Tagum City |  | Green | [10 empty] | h) PCF-Performance Challenge Fund-DILG
i) FMRDP - Farm to Market Road
j.) CMGP - Conditional Grant to Provinces
k.) OPAPP - Office of the President Adviser on the Peace Process
l.) LGSF-AM - Local Government Support Fund Assistance to Municipalities
| Prepared by: |  |  |  | Checked | [12 empty] | Recommending Approval
Noted
| GILBERT G. MAMBULAO JR |  |  |  | ELISA A. BARCENA | TESSIE G. ABABON | [9 empty] | JIVELLYN B. CO | [5 empty] | GLENN A. OLANDRIA
| Engineer II |  |  |  | Engineer IV- Engineering Dist 1, Area Engineer |  | Engineer IV-Engineering Dist 2, Area Engineer | [9 empty] | Asst. PG-Department Head |  |  |  |  | Provincial Engineer
[5 empty] | EDWIN S. MISA |  |  |  | MARILOU A. FORONDA
[5 empty] | Engineer IV- PDPM Division Head |  |  |  | Engineer IV- QC Division Head

## Completed_4th Quarter Dist 2 (hidden)
PROVINCE OF DAVAO DEL NORTE
ACCOMPLISHMENT REPORT
4th Quarter 2019
SECTOR: ECONOMIC (INFRASTRUCTURE DEV'T. PROGRAM)
OFFICE/AGENCY: PROVINCIAL ENGINEER'S OFFICE
COMPLETED PROJECTS DIST 2
| Name of Project |  |  |  |  | Type | Physical | Mode | PROJECT DATA | [5 empty] | Financial (000) |  | Physical Accomplishment |  |  |  | Employment |  | REMARKS
[6 empty] | of | Target | of | a) Project Cost |  | a) Date A lot. Rel. |  | e) # of days suspended |  | a) Program |  | a) Planned |  | c) Actual |  | Generated
[6 empty] | Project | (Descrip | Impl. | b) Project Engineer |  | b) Date Started |  | f) # of days extended |  | b) Allotment |  | b) Revised |  | d) Slippage |  | a) # of Persons
[6 empty] | (Location) | tion) |  | c) Implementor |  | c)Target Compl. Date |  | g) Date completed |  | c) Disbursement | [5 empty] | b) Man-days
[9 empty] | d) Duration |  | d) Revised Compl. Date
| I. | PROJECTS UNDER THE CONTINUING APPROPRIATION | [21 empty] | AC | 893809.45
|  |  | TRUST FUND 2017 | [20 empty] | AC
|  |  | Conditional Matching Grant to Provinces (CMGP) | [20 empty] | AC
4 |  | 8 |  | Road Upgrading of Dagohoy - Daligdigon |  | Road | 2.532 km | Contract | a) | 58048310.68 | a) | CY 2017 | e) | - | a) | 58048310.68 | a) | 100.00% | c) | 100% | a) | 16 | Completed as per Physical Accomplishment, Financial Documents on Process | 1
4 |  |  |  | Provincial Road |  |  |  |  | b) | Fabiala | b) | 01/05/18 | f) | 205 CD | b) | 58048310.68 | b) | - | d) | 0% | b) | 480 |  | 1
4 | [8 empty] | c) | PUREGOLD | c) | 11/18/18 | g) | - | c) | 29,572,637.70 | [7 empty] | 1
4 | [8 empty] | d) | 246 CD | d) | 03/31/19 | [11 empty] | 1
|  |  |  | Impv’t. of Maligaya-New Camiling Prov’l. |  | Conc. | 2.13 km | Contract. | a) | 50101614.08 | a) | CY 2017 | e) | 76 CD | a) | 57385680 | a) | 100.00% | c) | 100% | a) | 21 | Completed based on POW. Financial Documents on process | 2
|  |  |  | Road w/ Bridge Component,Carmen |  |  |  |  | b) | Mellomida | b) | 12/18/17 | f) | 209 CD | b) | 57385680 | b) | 100% | d) | 0% | b) | 147 |  | 2
[9 empty] | c) | PUREGOLD CONST. | c) | 02/15/19 | g) | - | c) | 36005452 | [7 empty] | 2
[9 empty] | d) | 376 CD | d) | 07/31/19 | [11 empty] | 2
|  | D. | 20% Development Fund CY 2017 | [20 empty] | AC
|  |  | STIMULUS PROJECTS CY 2017 | [20 empty] | AC
|  |  | CARMEN | [20 empty] | AC
4 |  |  |  | Construction of Evaluation Center at Prk. 1, |  | Bldg. |  | Barangay | a) | 500000 | a) | 12/28/17 | e) | - | a) | 500000 | a) | - | c) | 100% | a) | - | Completed | 1
4 |  |  |  | Asuncion, Carmen |  |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 1
4 | [8 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 1
4 | [8 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | Const./Rehab./Comp. of Various Gov't. Bldgs. |  |  | Bldg. | - | Admin | a) | 9,000,000.00 | [12 empty] | Investigation/Inspection of priority projects | AC
|  |  | Struct., Fac. (Provincewide) | [5 empty] | b) | Foronda/Ababon | [13 empty] | AC
[9 empty] | c) | PEO | [13 empty] | AC
[9 empty] | d) | - | [13 empty] | AC
4 |  |  | 2.3 | Improvement of Garciaville Day Care |  | Bldg. |  | Admin | a) | 330,000.00 | a) | 11/06/18 | e) | - | a) | 330,000.00 | a) |  | c) | 100% | a) | 3 | Completed based on POW. Financial Documents on process | 1
4 |  | 11 |  | Center, Mankilam, Tagum City |  |  |  |  | b) | - | b) | 09/02/19 | f) | - | b) | 330,000.00 | b) | - | d) |  | b) | 90 |  | 1
4 | [8 empty] | c) | PEO | c) | 10/11/19 | g) | - | c) | - | [7 empty] | 1
4 | [8 empty] | d) | - | d) | - | [11 empty] | 1
|  | F. | SDH IGCS - CONST. IN PROGRESS - BLGS. CY 2017 | [20 empty] | 2
|  |  | 1 | Construction Perimeter Fence Ph.II (Hospital |  | Fence |  | Admin | a) | 1,305,000.00 | a) | 11/10/17 | e) | 392 | a) | 1,305,000.00 | a) | 100% | c) | 100% | a) | 4 | Completed based on POW. Financial Documents on process | 2
|  |  |  | Compound) Samal District Hospital, IGCS |  |  |  |  | b) | Porras | b) | 03/12/18 | f) | 45 | b) | 1,305,000.00 | b) | - | d) | 1% | b) | 30 |  | 2
[9 empty] | c) | PEO | c) | 06/19/18 | g) | - | c) | 958,597.98 | [7 empty] | 2
[9 empty] | d) | - | d) | [12 empty] | 2
|  | C.5 | LDRRM - Trust Fund | [20 empty] | AC
4 |  | 5 | 1. Construction of Slope Protection and Concrete Pavement along Sta. Fe Mambing Road Section |  |  | Slope |  | Admin | a) | 1,853,000.00 | a) | 11/28/18 | e) |  | a) | 1,853,000.00 | a) | 100% | c) | 100% | a) | 16 | Completed based on POW. Financial Documents on process | 1
4 | [8 empty] | b) | Gone | b) | 12/03/18 | f) | 108 CD | b) | 1,853,000.00 | b) | - | d) |  | b) | 144 |  | 1
4 | [8 empty] | c) | PEO | c) | 02/28/19 | g) | 10/30/2019 | c) | 742252.72 | [7 empty] | 1
4 | [8 empty] | d) | 86 CD | d) | 06/15/2019 | [11 empty] | 1
4 |  | 1 | 3. Rehab. Of Canatan Bridge Slope Protection |  |  | Slope | 395 sq.m. | Contract | a) | 9200000 | a) | 06/20/2018 | e) | - | a) | 9200000 | a) | 100% | c) | 100% | a) | - | Completed | 1
4 |  |  | Brgy. Canatan, Asuncion | [5 empty] | b) | Aclaracion | b) | 02/11/2019 | f) | 35 CD | b) | 9200000 | b) | 100% | d) | 0% | b) | - |  | 1
4 | [8 empty] | c) | J-One Builders | c) | 04/12/2019 | g) | 05/31/2019 | c) | 7222021.59 | [7 empty] | 1
4 | [8 empty] | d) | 60 CD | d) | 05/01/2019 | [11 empty] | 1
4 |  | 5 | 5. Const. of Cabidianan Bridge Slope Protection, Brgy. Cabidianan, New Corella |  |  | Slope |  | Admin | a) | 3590000 | a) | 07/18/18 | e) | - | a) | 3590000 | a) | 100% | c) | 100% | a) | 8 | Completed based on POW. Financial Documents on process | 1
4 | [8 empty] | b) | Gone | b) | 6/17/19 | f) | - | b) | 3590000 | b) |  | d) |  | b) | 80 |  | 1
4 | [8 empty] | c) | PEO | c) | 8/20/19 | g) | - | c) | 1929823.4 | [7 empty] | 1
4 | [8 empty] | d) | 65 CD | d) | - | [11 empty] | 1
|  | D. | SEF(Special Education Fund)-SUPPLEMENTAL BUDGET # 1 CY 2017 | [20 empty] | AC
|  |  | 1. Const./Impv't./Compl. Of School Bldgs., Struc. & Fac. |  |  | Bldgs. |  | Admin | a) | 3,300,000.00 | [12 empty] | See projects listed below | 1
[9 empty] | b) | Foronda | [13 empty] | 1
[9 empty] | c) | PEO | [13 empty] | 1
[9 empty] | d) | - | [13 empty] | 1
4 |  | 8 | 1.1 | Construction of 1 unit School Building |  | Bldg. |  | Admin | a) | 1100000 | a) | 02/19/18 | e) | - | a) | 1100000 | a) | 100 | c) | 100 | a) | 6 | Completed based on POW. Financial Documents on process | 1
4 |  |  |  | Lumabag, Talaingod |  |  |  |  | b) | Dadula | b) | 03/20/19 | f) | 27 CD | b) | 1100000 | b) |  | d) |  | b) | 30 |  | 1
4 | [8 empty] | c) | PEO | c) | 05/19/19 | g) | 06/30/2019 | c) | 595230.5 | [7 empty] | 1
4 | [8 empty] | d) | 60 CD | d) | - | [11 empty] | 1
AC
|  |  | Rehabilitation / Improvement Of Various Local |  |  | Road | - | Admin | a) | 5000000 | [12 empty] | See projects listed below | AC
|  |  | Roads and Drainages | [5 empty] | b) | Paraguya | [13 empty] | AC
[9 empty] | c) | Admin | [13 empty] | AC
[9 empty] | d) | - | [13 empty] | AC
|  |  |  | Rehabilitation of Brgy. Adecor Barangay |  | Road |  | Admin | a) | 138000 | a) | 04/25/18 | e) | 66 CD | a) | 138000 | a) | 60.00% | c) | 60.00% | a) | - | Completed as per POW. Financial Documents on process | 2
|  |  |  | Road, IGACOS |  |  |  |  | b) | Porras/Pacquiao | b) | 10/18/18 | f) | 225 CD | b) | 138000 | b) | - | d) | - | b) | - |  | 2
[9 empty] | c) | PEO | c) | 10/27/19 | g) | - | c) | 111,872.00 | [7 empty] | 2
[9 empty] | d) | - | d) | 10/15/2019 | [11 empty] | 2
|  |  | Const./Rehab./Comp. of Various Gov't. Bldgs. |  |  | Bldgs. | - | Admin | a) | 13523124 | [12 empty] | Investigation/Inspection of priority projects | AC
|  |  | Struct., Fac. (Provincewide) | [5 empty] | b) | Foronda | [13 empty] | AC
[9 empty] | c) | Admin | [13 empty] | AC
[9 empty] | d) | - | [13 empty] | AC
|  |  |  | Repair/Rehab. Of PEO Building (2nd District), Carmen |  | Bldg |  | Admin | a) | 2250000 | a) | 08/10/18 | e) | - | a) | 2250000 | a) | 100% | c) | 100% | a) | 18 | Completed based on POW. Financial Documents on process | 2
[9 empty] | b) | Andoy | b) | 02/18/19 | f) | - | b) | 2250000 | b) | - | d) | 0% | b) | 138 |  | 2
[9 empty] | c) | Admin | c) | 08/23/19 | g) | - | c) | 1577344.8 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | STIMULUS PROJECTS | [20 empty] | AC
|  |  | TAGUM CITY | [20 empty] | AC
4 |  |  |  | Completion of Two Storey Multi-Purpose |  | Bldg. |  | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | 100% | c) | 100% | a) | 5 | Completed based on Physical Accomplishment. Financial Documents on process | 1
4 |  |  |  | Building, Magugpo East, Tagum City |  |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | 0% | b) | 110 |  | 1
4 | [8 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 1
4 | [8 empty] | d) | - | d) | - | [11 empty] | 1
|  | L. | 5% Calamity Fund CY 2018 | [20 empty] | AC
|  |  | 1. Prevention and Mitigation | [20 empty] | AC
|  |  | 1.1 Desiltation/Excavation of rivers and creeks |  |  | rivers |  | Admin | a) | 3000000 | [12 empty] | Investigation/Inspection of priority projects | AC
[9 empty] | b) | - | [13 empty] | AC
[9 empty] | c) | PEO | [13 empty] | AC
[9 empty] | d) | - | [13 empty] | AC
4 | [23 empty] | 1
4 |  |  | 1.1.1. | Improvement and Desiltation of Tagum Creek (Phase I and Phase II) |  | Creek |  | Admin | a) | 2,000,000.00 | a) | 11/06/18 | e) | - | a) | 2,000,000.00 | a) | 100% | c) | 100% | a) | 5 | Completed | 1
4 | [8 empty] | b) | Mayang | b) | 03/22/19 | f) | - | b) | 2,000,000.00 | b) | - | d) | 0% | b) | 110 |  | 1
4 | [8 empty] | c) | PEO | c) | 10/31/19 | g) | - | c) | - | [7 empty] | 1
4 | [8 empty] | d) | 224 CD | d) | - | [11 empty] | 1
4 |  |  | OPPAP-PAMANA | [20 empty] | AC
4 |  | 4 |  | Upgrading of Existing PWS Level II in Sitio Patel 2, Gupitan, Kapalong |  | PWS |  | Admin | a) | 2500000 | a) | 8/14/2019 | e) | - | a) | 2500000 | a) |  | c) | 100% | a) | - | Completed as per Physical Accomplishment. Financial Documents on process | 1
4 | [8 empty] | b) | Diosanta | b) | 3/25/2019 | f) | - | b) | 2500000 | b) |  | d) |  | b) | - |  | 1
4 | [8 empty] | c) | PEO | c) | 7/19/2019 | g) | 09/30/2019 | c) | - | [7 empty] | 1
4 | [8 empty] | d) | - | d) | - | [11 empty] | 1
4 |  | R. | LOCAL GOVERNMENT SUPPORT FUND (LGSF) CY 2018 | [20 empty] | AC
4 |  |  | 1 | Road Upgrading of San Vicente - Butay Provincial Road |  | Road |  | Contract | a) | 19949581.18 | a) | CY 2018 | e) | - | a) | 19949581.18 | a) | 100% | c) | 100% | a) | 18 | Completed as per Physical Accomplishment. Financial Documents on process | 1
4 | [8 empty] | b) | Aclaracion | b) | 11/19/18 | f) | 28 CD | b) | 19949581.18 | b) | 100% | d) | 0% | b) | 396 |  | 1
4 | [8 empty] | c) | Alpha & Omega | c) | 06/08/19 | g) | 06/26/2019 | c) | 9,685,667.31 | [7 empty] | 1
4 | [8 empty] | d) | 202 CD | d) | 07/06/19 | [11 empty] | 1
| II. PROJECTS UNDER THE CURRENT APPROPRIATION CY 2019 | [22 empty] | AP
| A.1 GENERAL FUND CY 2019 | [6 empty] | MBA/CBRMC | a) | 18127866 | a) | 01/03/19 | e) | - | a) | 18127866 | a) | 83.63 | c) | 83.83 | a) | 46 | See list of Provincial Roads | AP
| Road ID |  | Maintenance of Various Provincial Roads and Bridges at District 1 |  |  | Road Maintenance | KM |  | b) | Paraguya | b) | 01/03/19 | f) | - | b) | 18127866 | b) | - | d) | - | b) | 920 |  | FS
[7 empty] | 288.26 |  | c) | PEO/CBRMC | c) | 12/31/19 | g) | - | c) | - | [7 empty] | AC
| 11DAN | [9 empty] | d) | - | [11 empty] | AC
[9 empty] | d) | 261 days | d) | - | [11 empty] | AC
|  |  | Jct. Highway Magatos - New Bantayan |  |  | Road Maintenance | 7.1 | MBA | a) | 287307.39 | a) | 01/03/19 | e) | - | a) | 287307.39 | a) | 100% | c) | 100% | a) | 15 | Completed | AC
| 001 | [7 empty] | b) | Crucio | b) | 01/16/19 | f) | - | b) | 287307.39 | b) | - | d) | - | b) | 480 |  | 1
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 118693.58 | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | Jct. Highway Magatos - New Bantayan |  |  | Road Maintenance | 7.1 | CBRMC | a) | 223674.22 | a) | 01/03/19 | e) | - | a) | 223674.22 | a) | 100% | c) | 100% | a) | 16 | Completed | 1
| 001 | [7 empty] | b) | Crucio | b) | 3/22/19 | f) | - | b) | 223674.22 | b) | - | d) | - | b) | 480 |  | 1
[9 empty] | c) | CALAFA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
|  |  | Magatos-Bdry Pagsabangan |  |  | Road Maintenance | 8.33 | MBA | a) | 328740.25 | a) | 01/03/19 | e) | - | a) | 328740.25 | a) | 100% | c) | 100% | a) | 15 | Completed | 1
| 002 | [7 empty] | b) | Crucio | b) | 01/03/19 | f) | - | b) | 328740.25 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 207258.49 | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | Magatos-Bdry Pagsabangan |  |  | Road Maintenance | 8.33 | CBRMC | a) | 270763.53 | a) | 01/03/19 | e) | - | a) | 270763.53 | a) | 100% | c) | 100% | a) | 16 | Completed | 1
| 002 | [7 empty] | b) | Crucio | b) | 03/22/19 | f) | - | b) | 270763.53 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | CALAFA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
|  |  | Ilog-New Bantayan |  |  | Road Maintenance | 2.68 | MBA | a) | 131131.39 | a) | 01/03/19 | e) | - | a) | 131131.39 | a) | 100% | c) | 100% | a) | 15 | Completed | 1
| 003 | [7 empty] | b) | Crucio | b) | 01/16/19 | f) | - | b) | 131131.39 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 49,316.69 | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | Ilog-New Bantayan |  |  | Road Maintenance | 2.68 | CBRMC | a) | 65925.03 | a) | 01/03/19 | e) | - | a) | 65925.03 | a) | 100% | c) | 100% | a) | 16 | Completed | 1
| 003 | [7 empty] | b) | Crucio | b) | 03/22/19 | f) | - | b) | 65925.03 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | CALAFA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
|  |  | Asuncion -Monte Carlo-Del Pilar |  |  | Road Maintenance | 9.93 | MBA | a) | 474102.88 | a) | 01/03/19 | e) | - | a) | 474102.88 | a) | 100% | c) | 100% | a) | 15 | Completed | 1
| 005 | [7 empty] | b) | Crucio | b) | 01/03/19 | f) | - | b) | 474102.88 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 240274.49 | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | Asuncion -Monte Carlo-Del Pilar |  |  | Road Maintenance | 9.93 | CBRMC | a) | 355524.28 | a) | 01/03/19 | e) | - | a) | 355524.28 | a) | 100% | c) | 100% | a) | 16 | Completed
| 005 | [7 empty] | b) | Crucio | b) | 03/22/19 | f) | - | b) | 355524.28 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | MAHAYAHAY IFA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
|  |  | Jct. Highway Canatan-Jct. Highway Magatos |  |  | Road Maintenance | 4.85 | MBA | a) | 209808.59 | a) | 01/03/19 | e) | - | a) | 209808.59 | a) | 100% | c) | 100% | a) | 15 | Completed | 1
| 006 | [7 empty] | b) | Crucio | b) | 02/18/19 | f) | - | b) | 209808.59 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 80652.8 | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | Jct. Highway Canatan-Jct. Highway Magatos |  |  | Road Maintenance | 4.85 | CBRMC | a) | 162458.12 | a) | 01/03/19 | e) | - | a) | 162458.12 | a) | 100% | c) | 100% | a) | 16 | Completed | 1
| 006 | [7 empty] | b) | Crucio | b) | 03/22/19 | f) | - | b) | 162458.12 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | CAMODA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
1
|  |  | Sta. Felomina-San Roque |  |  | Road Maintenance | 7.68 | MBA | a) | 147439.63 | a) | 01/03/19 | e) | - | a) | 147439.63 | a) | 100% | c) | 100% | a) | 15 | Completed
| 008 | [7 empty] | b) | Crucio | b) | 01/16/19 | f) | - | b) | 147439.63 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 63806.67 | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | Sta. Felomina-San Roque |  |  | Road Maintenance | 7.68 | CBRMC | a) | 261345.67 | a) | 01/03/19 | e) | - | a) | 261345.67 | a) | 100% | c) | 100% | a) | 16 | Completed | 1
| 008 | [7 empty] | b) | Crucio | b) | 03/25/19 | f) | - | b) | 261345.67 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | STAFFA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
|  |  | Saug-Sonlon-Bdy Longanapan |  |  | Road Maintenance | 11.6 | MBA | a) | 568486.36 | a) | 01/03/19 | e) | - | a) | 568486.36 | a) | 100% | c) | 100% | a) | 15 | Completed | 1
| 010 | [7 empty] | b) | Crucio | b) | 01/16/19 | f) | - | b) | 568486.36 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 262900.22 | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | Saug-Sonlon-Bdy Longanapan |  |  | Road Maintenance | 11.6 | CBRMC | a) | 185565.56 | a) | 01/03/19 | e) | - | a) | 185565.56 | a) | 100% | c) | 100% | a) | 16 | Completed | 1
| 010 | [7 empty] | b) | Crucio | b) | 03/26/19 | f) | - | b) | 185565.56 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | BINANCIAN LIVESTOCK AFA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
|  |  | Jct. New Visayas-Buan |  |  | Road Maintenance | 2.99 | MBA | a) | 79238.27 | a) | 01/03/19 | e) | - | a) | 79238.27 | a) | 100% | c) | 100% | a) | 15 | Completed | 1
| 011 | [7 empty] | b) | Crucio | b) | 02/18/19 | f) | - | b) | 79238.27 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 14682.85 | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | Jct. New Visayas-Buan |  |  | Road Maintenance | 2.99 | CBRMC | a) | 101242.01 | a) | 01/03/19 | e) | - | a) | 101242.01 | a) | 100% | c) | 100% | a) | 16 | Completed | 1
| 011 | [7 empty] | b) | Crucio | b) | 03/22/19 | f) | - | b) | 101242.01 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | BUAN IFA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
|  |  | San Vicente - Butay |  |  | Road Maintenance | 7.52 | MBA | a) | 209624.2 | a) | 01/03/19 | e) | - | a) | 209624.2 | a) | 100% | c) | 100% | a) | 15 | Completed | 1
| 013 | [7 empty] | b) | Crucio | b) | 02/18/19 | f) | - | b) | 209624.2 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 56,080.29 | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | San Vicente - Butay |  |  | Road Maintenance | 7.52 | CBRMC | a) | 227205.88 | a) | 01/03/19 | e) | - | a) | 227205.88 | a) | 100% | c) | 100% | a) | 16 | Completed | 1
| 013 | [7 empty] | b) | Crucio | b) | 03/27/19 | f) | - | b) | 227205.88 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | SVMODA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
|  |  | Jct. Highway Doña Andrea - Capungagan |  |  | Road Maintenance | 8.7 | MBA | a) | 230835.16 | a) | 01/03/19 | e) | - | a) | 230835.16 | a) | 100% | c) | 100% | a) | 15 | Completed | 1
| 014 | [7 empty] | b) | Crucio | b) | 02/18/19 | f) | - | b) | 230835.16 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 60,629.26 | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
1
|  |  | Jct. Highway Doña Andrea - Capungagan |  |  | Road Maintenance | 8.7 | CBRMC | a) | 294308.14 | a) | 01/03/19 | e) | - | a) | 294308.14 | a) | 100% | c) | 100% | a) | 16 | Completed
| 014 | [7 empty] | b) | Crucio | b) | 03/28/19 | f) | - | b) | 294308.14 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | CAPUNGAGAN MPC | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
|  |  | Semong-Palma Gil |  |  | Road Maintenance | 2.73 | MBA | a) | 147289.98 | a) | 01/03/19 | e) | - | a) | 147289.98 | a) | 100% | c) | 100% | a) | 15 | Completed | 1
| 018 | [7 empty] | b) | Crucio | b) | 02/18/19 | f) | - | b) | 147289.98 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 71745.43 | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
1
|  |  | Semong-Palma Gil |  |  | Road Maintenance | 2.73 | CBRMC | a) | 49186.05 | a) | 01/03/19 | e) | - | a) | 49186.05 | a) | 100% | c) | 100% | a) | 16 | Completed
| 018 | [7 empty] | b) | Crucio | b) | 03/22/19 | f) | - | b) | 49186.05 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | PALMA GIL FA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
|  |  | Daligdigon - Dagohoy |  |  | Road Maintenance | 3.34 | MBA | a) | 148835.45 | a) | 01/03/19 | e) | - | a) | 148835.45 | a) | 100% | c) | 100% | a) | - | Completed | 1
| 020 | [7 empty] | b) | Crucio | b) | - | f) | - | b) | 148835.45 | b) | - | d) | - | b) | - |  | 1
[9 empty] | c) | PEO | c) | - | g) | 2019-12-31 | c) | - | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | Daligdigon - Dagohoy |  |  | Road Maintenance | 3.34 | CBRMC | a) | 68279.5 | a) | 01/03/19 | e) | - | a) | 68279.5 | a) | 100% | c) | 100% | a) | 16 | Completed | 1
| 020 | [7 empty] | b) | Crucio | b) | 03/22/19 | f) | - | b) | 68279.5 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | PALMA GIL FA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
|  |  | Jct. Sampao-Bdry. Mamacao |  |  | Road Maintenance | 4.98 | MBA | a) | 154200.78 | a) | 01/03/19 | e) | - | a) | 154200.78 | a) | 100% | c) | 100% | a) | 15 | Completed | 1
| 025 | [7 empty] | b) | Crucio | b) | 02/18/19 | f) | - | b) | 154200.78 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 24,296.87 | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | Jct. Sampao-Bdry. Mamacao |  |  | Road Maintenance | 4.98 | CBRMC | a) | 169521.51 | a) | 01/03/19 | e) | - | a) | 169521.51 | a) | 100% | c) | 100% | a) | 16 | Completed | 1
| 025 | [7 empty] | b) | Crucio | b) | 03/26/19 | f) | - | b) | 169521.51 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | AMS KAPALONG | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
|  |  | Jct. Highway Luna-Mamacao-Narra |  |  | Road Maintenance | 9.17 | MBA | a) | 357957.66 | a) | 01/03/19 | e) | - | a) | 357957.66 | a) | 100% | c) | 100% | a) | 15 | Completed | 1
| 026 | [7 empty] | b) | Crucio | b) | 02/18/19 | f) | - | b) | 357957.66 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 127,996.16 | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | Jct. Highway Luna-Mamacao-Narra |  |  | Road Maintenance | 9.17 | CBRMC | a) | 313143.91 | a) | 01/03/19 | e) | - | a) | 313143.91 | a) | 100% | c) | 100% | a) | 16 | Completed | 1
| 026 | [7 empty] | b) | Crucio | b) | 03/26/19 | f) | - | b) | 313143.91 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | AMS KAPALONG | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
|  |  | Jct. Gabuyan-Katipunan-Bucana |  |  | Road Maintenance | 5.89 | MBA | a) | 294403.23 | a) | 01/03/19 | e) | - | a) | 294403.23 | a) | 100% | c) | 100% | a) | 15 | Completed | 1
| 027 | [7 empty] | b) | Crucio | b) | 02/18/19 | f) | - | b) | 294403.23 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 126,179.97 | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | Jct. Gabuyan-Katipunan-Bucana |  |  | Road Maintenance | 5.89 | CBRMC | a) | 129495.6 | a) | 01/03/19 | e) | - | a) | 129495.6 | a) | 100% | c) | 100% | a) | 16 | Completed | 1
| 027 | [7 empty] | b) | Crucio | b) | 03/26/19 | f) | - | b) | 129495.6 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | MANGULIBAS FA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
|  |  | Capungagan-Mabuhay-Pandulian |  |  | Road Maintenance | 5.57 | MBA | a) | 294917.73 | a) | 01/03/19 | e) | - | a) | 294917.73 | a) | 100% | c) | 100% | a) | 15 | Completed | 1
| 028 | [7 empty] | b) | Crucio | b) | 02/18/19 | f) | - | b) | 294917.73 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
1
|  |  | Capungagan-Mabuhay-Pandulian |  |  | Road Maintenance | 5.57 | CBRMC | a) | 105950.95 | a) | 01/03/19 | e) | - | a) | 105950.95 | a) | 100% | c) | 100% | a) | 16 | Completed
| 028 | [7 empty] | b) | Crucio | b) | 03/28/19 | f) | - | b) | 105950.95 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | CAPUNGAGAN MPC | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
|  |  | Florida - New Boholano |  |  | Road Maintenance | 2.54 | MBA | a) | 95863.17 | a) | 01/03/19 | e) | - | a) | 95863.17 | a) | 100% | c) | 100% | a) | 15 | Completed | 1
| 030 | [7 empty] | b) | Crucio | b) | 02/18/19 | f) | - | b) | 95863.17 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 31,418.99 | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | Florida - New Boholano |  |  | Road Maintenance | 2.54 | CBRMC | a) | 47425.27 | a) | 01/03/19 | e) | - | a) | 47425.27 | a) | 100% | c) | 100% | a) | 16 | Completed | 1
| 030 | [7 empty] | b) | Crucio | b) | 03/28/19 | f) | - | b) | 47425.27 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | SUPRA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
|  |  | Jct. New Boholano - New Loon |  |  | Road Maintenance | 4.77 | MBA | a) | 140549.84 | a) | 01/03/19 | e) | - | a) | 140549.84 | a) | 100% | c) | 100% | a) | 15 | Completed | 1
| 031 | [7 empty] | b) | Crucio | b) | 02/18/19 | f) | - | b) | 140549.84 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 40,056.38 | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | Jct. New Boholano - New Loon |  |  | Road Maintenance | 4.77 | CBRMC | a) | 169521.51 | a) | 01/03/19 | e) | - | a) | 169521.51 | a) | 100% | c) | 100% | a) | 16 | Completed | 1
| 031 | [7 empty] | b) | Crucio | b) | 03/28/19 | f) | - | b) | 169521.51 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | NEW LOON FA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
|  |  | Florida-Suaon-Jct. Gupitan |  |  | Road Maintenance | 15.57 | MBA | a) | 707038.05 | a) | 01/03/19 | e) | - | a) | 707038.05 | a) | 100% | c) | 100% | a) | 15 | Completed | 1
| 032 | [7 empty] | b) | Crucio | b) | 01/16/19 | f) | - | b) | 707038.05 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 226,.062.60 | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | Florida-Suaon-Jct. Gupitan |  |  | Road Maintenance | 15.57 | CBRMC | a) | 419094.85 | a) | 01/03/19 | e) | - | a) | 419094.85 | a) | 100% | c) | 100% | a) | 16 | Completed | 1
| 032 | [7 empty] | b) | Crucio | b) | 03/28/19 | f) | - | b) | 419094.85 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | SUPRA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
|  |  | Km. 15, Kipalili-New Loon |  |  | Road Maintenance | 6.93 | MBA | a) | 367659.97 | a) | 01/03/19 | e) | - | a) | 367659.97 | a) | 100% | c) | 100% | a) | 15 | Completed | 1
| 034 | [7 empty] | b) | Crucio | b) | 02/01/19 | f) | - | b) | 367659.97 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 112,175.78 | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | Km. 15, Kipalili-New Loon |  |  | Road Maintenance | 6.93 | CBRMC | a) | 237801.01 | a) | 01/03/19 | e) | - | a) | 237801.01 | a) | 100% | c) | 100% | a) | 16 | Completed | 1
| 034 | [7 empty] | b) | Crucio | b) | 03/26/19 | f) | - | b) | 237801.01 | b) | - | d) | - | b) | 480 |  | 1
[9 empty] | c) | KIPALILI FA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
|  |  | Jct. Suaon-Libuton |  |  | Road Maintenance | 7.26 | MBA | a) | 44015.68 | a) | 01/03/19 | e) | - | a) | 44015.68 | a) | 100% | c) | 100% | a) | 15 | Completed
| 035 | [7 empty] | b) | Crucio | b) | 01/16/19 | f) | - | b) | 44015.68 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 24,980.86 | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | Jct. Suaon-Libuton |  |  | Road Maintenance | 7.26 | CBRMC | a) | 91664.91 | a) | 01/03/19 | e) | - | a) | 91664.91 | a) | 100% | c) | 100% | a) | 16 | Completed | 1
| 035 | [7 empty] | b) | Crucio | b) | 03/22/19 | f) | - | b) | 91664.91 | b) | - | d) | - | b) | 480 |  | 1
[9 empty] | c) | AALLI | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
1
|  |  | Datu Balong - Pinamuno |  |  | Road Maintenance | 2.74 | MBA | a) | 95458.24 | a) | 01/03/19 | e) | - | a) | 95458.24 | a) | 100% | c) | 100% | a) | 15 | Completed
| 040 | [7 empty] | b) | Crucio | b) | 03/01/19 | f) | - | b) | 95458.24 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 12,625.00 | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | Datu Balong - Pinamuno |  |  | Road Maintenance | 2.74 | CBRMC | a) | 63570.57 | a) | 01/03/19 | e) | - | a) | 63570.57 | a) | 100% | c) | 100% | a) | 16 | Completed | 1
| 040 | [7 empty] | b) | Crucio | b) | 03/28/19 | f) | - | b) | 63570.57 | b) | - | d) | - | b) | 480 |  | 1
[9 empty] | c) | DATU BALONG FA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
|  |  | Sawata - Mamangan - Pinamuno |  |  | Road Maintenance | 14.48 | MBA | a) | 545390.17 | a) | 01/03/19 | e) | - | a) | 545390.17 | a) | 100% | c) | 100% | a) | 15 | Completed | 1
| 041 | [7 empty] | b) | Crucio | b) | 02/01/19 | f) | - | b) | 545390.17 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 196,076.60 | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | Sawata - Mamangan - Pinamuno |  |  | Road Maintenance | 14.48 | CBRMC | a) | 508564.54 | a) | 01/03/19 | e) | - | a) | 508564.54 | a) | 100% | c) | 100% | a) | 16 | Completed | 1
| 041 | [7 empty] | b) | Crucio | b) | 03/22/19 | f) | - | b) | 508564.54 | b) | - | d) | - | b) | 480 |  | 1
[9 empty] | c) | SAWATA DFA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
|  |  | Igangon - Sawata |  |  | Road Maintenance | 9.66 | MBA | a) | 497447.77 | a) | 01/03/19 | e) | - | a) | 497447.77 | a) | 100% | c) | 100% | a) | 15 | Completed | 1
| 042 | [7 empty] | b) | Crucio | b) | 02/01/19 | f) | - | b) | 497447.77 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | Igangon - Sawata |  |  | Road Maintenance | 9.66 | CBRMC | a) | 197775.1 | a) | 01/03/19 | e) | - | a) | 197775.1 | a) | 100% | c) | 100% | a) | 16 | Completed | 1
| 042 | [7 empty] | b) | Crucio | b) | 03/22/19 | f) | - | b) | 197775.1 | b) | - | d) | - | b) | 480 |  | 1
[9 empty] | c) | SAWATA DFA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
|  |  | New Corella - Sto. Niño - Macgum |  |  | Road Maintenance | 17.11 | MBA | a) | 606294.08 | a) | 01/03/19 | e) | - | a) | 606294.08 | a) | 100% | c) | 100% | a) | 15 | Completed | 1
| 044 | [7 empty] | b) | Crucio | b) | 01/03/19 | f) | - | b) | 606294.08 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 246,619.77 | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | New Corella - Sto. Niño - Macgum |  |  | Road Maintenance | 17.11 | CBRMC | a) | 308434.97 | a) | 01/03/19 | e) | - | a) | 308434.97 | a) | 100% | c) | 100% | a) | 16 | Completed | 1
| 044 | [7 empty] | b) | Crucio | b) | 03/26/19 | f) | - | b) | 308434.97 | b) | - | d) | - | b) | 480 |  | 1
[9 empty] | c) | SAN ISIDRO FA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
|  |  | Tagaytay - Buan |  |  | Road Maintenance | 4.92 | MBA | a) | 173197.37 | a) | 01/03/19 | e) | - | a) | 173197.37 | a) | 100% | c) | 100% | a) | 15 | Completed | 1
| 045 | [7 empty] | b) | Crucio | b) | 03/18/19 | f) | - | b) | 173197.37 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 26254.58 | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | Tagaytay - Buan |  |  | Road Maintenance | 4.92 | CBRMC | a) | 131850.07 | a) | 01/03/19 | e) | - | a) | 131850.07 | a) | 100% | c) | 100% | a) | 16 | Completed | 1
| 045 | [7 empty] | b) | Crucio | b) | 03/22/19 | f) | - | b) | 131850.07 | b) | - | d) | - | b) | 480 |  | 1
[9 empty] | c) | BUAN IFA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
|  |  | limbaan - Sto. Niño |  |  | Road Maintenance | 3.19 | MBA | a) | 153706.77 | a) | 01/03/19 | e) | - | a) | 153706.77 | a) | 100% | c) | 100% | a) | 15 | Completed | 1
| 049 | [7 empty] | b) | Crucio | b) | 03/01/19 | f) | - | b) | 153706.77 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 32534.49 | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | limbaan - Sto. Niño |  |  | Road Maintenance | 3.19 | CBRMC | a) | 53657.51 | a) | 01/03/19 | e) | - | a) | 53657.51 | a) | 100% | c) | 100% | a) | - | Completed | 1
| 049 | [7 empty] | b) | Crucio | b) | - | f) | - | b) | 53657.51 | b) | - | d) | - | b) | - |  | 1
[9 empty] | c) | - | c) | - | g) | 2019-12-31 | c) | - | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | Del Pilar - Jct. Silangan |  |  | Road Maintenance | 4.17 | MBA | a) | 187097.4 | a) | 01/03/19 | e) | - | a) | 187097.4 | a) | 100% | c) | 100% | a) | 15 | Completed | 1
| 051 | [7 empty] | b) | Crucio | b) | 03/18/19 | f) | - | b) | 187097.4 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 94181.74 | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | Del Pilar - Jct. Silangan |  |  | Road Maintenance | 4.17 | CBRMC | a) | 113014.34 | a) | 01/03/19 | e) | - | a) | 113014.34 | a) | 100% | c) | 100% | a) | 16 | Completed | 1
| 051 | [7 empty] | b) | Crucio | b) | 03/26/19 | f) | - | b) | 113014.34 | b) | - | d) | - | b) | 480 |  | 1
[9 empty] | c) | DURIAN DACUDAO | c) | 12/31/19 | g) | - | c) | - | [7 empty] | 1
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
|  |  | New Corella - New Sambog - Silangan |  |  | Road Maintenance | 5.1 | MBA | a) | 201994.35 | a) | 01/03/19 | e) | - | a) | 201994.35 | a) | 100% | c) | 100% | a) | 15 | Completed | 1
| 052 | [7 empty] | b) | Crucio | b) | 03/01/19 | f) | - | b) | 201994.35 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 63402.48 | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | New Corella - New Sambog - Silangan |  |  | Road Maintenance | 5.1 | CBRMC | a) | 131850.07 | a) | 01/03/19 | e) | - | a) | 131850.07 | a) | 100% | c) | 100% | a) | 16 | Completed | 1
| 052 | [7 empty] | b) | Crucio | b) | 03/26/19 | f) | - | b) | 131850.07 | b) | - | d) | - | b) | 480 |  | 1
[9 empty] | c) | DURIAN DACUDAO | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
|  |  | Sta. Fe - Del Monte |  |  | Road Maintenance | 3.34 | MBA | a) | 37923.51 | a) | 01/03/19 | e) | - | a) | 37923.51 | a) | 100% | c) | 100% | a) | 15 | Completed | 1
| 056 | [7 empty] | b) | Crucio | b) | 03/18/19 | f) | - | b) | 37923.51 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 36595.13 | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | Sta. Fe - Del Monte |  |  | Road Maintenance | 3.34 | CBRMC | a) | 70633.96 | a) | 01/03/19 | e) | - | a) | 70633.96 | a) | 100% | c) | 100% | a) | 16 | Completed | 1
| 056 | [7 empty] | b) | Crucio | b) | 03/21/19 | f) | - | b) | 70633.96 | b) | - | d) | - | b) | 480 |  | 1
[9 empty] | c) | DEL MONTE CACAO | c) | 12/31/19 | g) | 2019-12-31 | c) | 4,872.18 | [7 empty] | 1
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
|  |  | New Corella - New Bohol |  |  | Road Maintenance | 11.54 | MBA | a) | 356226.67 | a) | 01/03/19 | e) | - | a) | 356226.67 | a) | 100% | c) | 100% | a) | 15 | Completed
| 058 | [7 empty] | b) | Crucio | b) | 02/01/19 | f) | - | b) | 356226.67 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 110,982.71 | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | New Corella - New Bohol |  |  | Road Maintenance | 11.54 | CBRMC | a) | 190711.7 | a) | 01/03/19 | e) | - | a) | 190711.7 | a) | 100% | c) | 100% | a) | 16 | Completed | 1
| 058 | [7 empty] | b) | Crucio | b) | 03/22/19 | f) | - | b) | 190711.7 | b) | - | d) | - | b) | 480 |  | 1
[9 empty] | c) | SAN JOSE COCONUT | c) | 12/31/19 | g) | 2019-12-31 | c) | 5,847.18 | [7 empty] | 1
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
1
|  |  | Jct. Carcor - Prk. 9 Bagsak |  |  | Road Maintenance | 2.5 | MBA | a) | 108618.49 | a) | 01/03/19 | e) | - | a) | 108618.49 | a) | 100% | c. | 100% | a) | 15 | Completed
| 059 | [7 empty] | b) | Crucio | b) | 03/01/19 | f) | - | b) | 108618.49 | b) | - | d) |  | b) | 480 |  | 1
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 79952.88 | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
1
|  |  | Jct. Carcor - Prk. 9 Bagsak |  |  | Road Maintenance | 2.5 | CBRMC | a) | 42284.76 | a) | 01/03/19 | e) | - | a) | 42284.76 | a) | 100% | c) | 100% | a) | 16 | Completed
| 059 | [7 empty] | b) | Crucio | b) | 03/22/19 | f) | - | b) | 42284.76 | b) | - | d) | - | b) | 480 |  | 1
[9 empty] | c) | CARCOR MOTOR | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
|  |  | Carcor - Jct. Kauswagan |  |  | Road Maintenance | 4.32 | MBA | a) | 264514.71 | a) | 01/03/19 | e) | - | a) | 264514.71 | a) | 100% | c) | 100% | a) | 15 | Completed | 1
| 060 | [7 empty] | b) | Crucio | b) | 03/18/19 | f) | - | b) | 264514.71 | b) | - | d) |  | b) | 450 |  | 1
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 80733.11 | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | Carcor - Jct. Kauswagan |  |  | Road Maintenance | 4.32 | CBRMC | a) | 48398.27 | a) | 01/03/19 | e) | - | a) | 48398.27 | a) | 100% | c) | 100% | a) | 16 | Completed
| 060 | [7 empty] | b) | Crucio | b) | 03/22/19 | f) | - | b) | 48398.27 | b) | - | d) | - | b) | 480 |  | 1
[9 empty] | c) | CARCOR MOTOR | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
|  |  | Del Pilar - Prk 9 Bagsak - San Jose |  |  | Road Maintenance | 4.99 | MBA | a) | 170215.76 | a) | 01/03/19 | e) | - | a) | 170215.76 | a) | 100% | c) | 100% | a) | 15 | Completed | 1
| 061 | [7 empty] | b) | Crucio | b) | 03/01/19 | f) | - | b) | 170215.76 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 87595.63 | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | Del Pilar - Prk 9 Bagsak - San Jose |  |  | Road Maintenance | 4.99 | CBRMC | a) | 223674.22 | a) | 01/03/19 | e) | - | a) | 223674.22 | a) | 100% | c) | 100% | a) | 16 | Completed | 1
| 061 | [7 empty] | b) | Crucio | b) | 03/22/19 | f) | - | b) | 223674.22 | b) | - | d) | - | b) | 480 |  | 1
[9 empty] | c) | SAN JOSE COCONUT | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
|  |  | San Juan - New Talisay |  |  | Road Maintenance | 5.13 | MBA | a) | 306261.25 | a) | 01/03/19 | e) | - | a) | 306261.25 | a) | 100% | c) | 100% | a) | 15 | Completed | 1
| 063 | [7 empty] | b) | Crucio | b) | 02/01/19 | f) | - | b) | 306261.25 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 85123.48 | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | San Juan - New Talisay |  |  | Road Maintenance | 5.13 | CBRMC | a) | 93906.31 | a) | 01/03/19 | e) | - | a) | 93906.31 | a) | 100% | c) | 100% | a) | 16 | Completed
| 063 | [7 empty] | b) | Crucio | b) | 03/26/19 | f) | - | b) | 93906.31 | b) | - | d) | - | b) | 480 |  | 1
[9 empty] | c) | NEW TALISAY IAWA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
|  |  | San Juan - kauswagan - New Cortez |  |  | Road Maintenance | 3.22 | MBA | a) | 187879.04 | a) | 01/03/19 | e) | - | a) | 187879.04 | a) | 100% | c) | 100% | a) | 15 | Completed | 1
| 064 | [7 empty] | b) | Crucio | b) | 03/18/19 | f) | - | b) | 187879.04 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 3,025.00 | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | San Juan - kauswagan - New Cortez |  |  | Road Maintenance | 3.22 | CBRMC | a) | 63298.26 | a) | 01/03/19 | e) | - | a) | 63298.26 | a) | 100% | c) | 100% | a) | 16 | Completed
| 064 | [7 empty] | b) | Crucio | b) | 03/22/19 | f) | - | b) | 63298.26 | b) | - | d) | - | b) | 480 |  | 1
[9 empty] | c) | SAN JOSE COCONUT | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
|  |  | New Bohol - Jct. El Unido |  |  | Road Maintenance | 2.12 | MBA | a) | 54989.06 | a) | 01/03/19 | e) | - | a) | 54989.06 | a) | 100% | c) | 100% | a) | 15 | Completed
| 065 | [7 empty] | b) | Crucio | b) | 03/01/19 | f) | - | b) | 54989.06 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 21021.99 | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | New Bohol - Jct. El Unido |  |  | Road Maintenance | 2.12 | CBRMC | a) | 58861.64 | a) | 01/03/19 | e) | - | a) | 58861.64 | a) | 100% | c) | 100% | a) | 16 | Completed | 1
| 065 | [7 empty] | b) | Crucio | b) | 03/26/19 | f) | - | b) | 58861.64 | b) | - | d) | - | b) | 480 |  | 1
[9 empty] | c) | MANDISKAB TRIBAL | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
1
|  |  | New Corella - El unido - Jct. Mesaoy |  |  | Road Maintenance | 8.63 | MBA | a) | 388002.46 | a) | 01/03/19 | e) | - | a) | 388002.46 | a) | 100% | c) | 100% | a) | 15 | Completed
| 066 | [7 empty] | b) | Crucio | b) | 02/11/19 | f) | - | b) | 388002.46 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 58142.76 | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | New Corella - El unido - Jct. Mesaoy |  |  | Road Maintenance | 8.63 | CBRMC | a) | 233092.08 | a) | 01/03/19 | e) | - | a) | 233092.08 | a) | 100% | c) | 100% | a) | 16 | Completed | 1
| 066 | [7 empty] | b) | Crucio | b) | 03/26/19 | f) | - | b) | 233092.08 | b) | - | d) | - | b) | 480 |  | 1
[9 empty] | c) | MANDISKAB TRIBAL | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
|  |  | Mesaoy - Dasing |  |  | Road Maintenance | 1.39 | MBA | a) | 29749.5 | a) | 01/03/19 | e) | - | a) | 29749.5 | a) | 100% | c) | 100% | a) | 15 | Completed | 1
| 067 | [7 empty] | b) | Crucio | b) | 03/18/19 | f) | - | b) | 29749.5 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 10000 | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | Mesaoy - Dasing |  |  | Road Maintenance | 1.39 | CBRMC | a) | 54152.71 | a) | 01/03/19 | e) | - | a) | 54152.71 | a) | 100% | c) | 100% | a) | 16 | Completed | 1
| 067 | [7 empty] | b) | Crucio | b) | 03/26/19 | f) | - | b) | 54152.71 | b) | - | d) | - | b) | 480 |  | 1
[9 empty] | c) | MANDISKAB TRIBAL | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
|  |  | Jct. San Juan - Jct. Mesaoy |  |  | Road Maintenance | 1.82 | MBA | a) | 106788.95 | a) | 01/03/19 | e) | - | a) | 106788.95 | a) | 100% | c) | 100% | a) | 15 | Completed | 1
| 068 | [7 empty] | b) | Crucio | b) | 03/01/19 | f) | - | b) | 106788.95 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 17502.68 | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | Jct. San Juan - Jct. Mesaoy |  |  | Road Maintenance | 1.82 | CBRMC | a) | 35180.83 | a) | 01/03/19 | e) | - | a) | 35180.83 | a) | 100% | c) | 100% | a) | 16 | Completed | 1
| 068 | [7 empty] | b) | Crucio | b) | 03/26/19 | f) | - | b) | 35180.83 | b) | - | d) | - | b) | 480 |  | 1
[9 empty] | c) | MANDISKAB TRIBAL | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
|  |  | Mesaoy - Jct. Mahayahay |  |  | Road Maintenance | 4.6 | MBA | a) | 146984.46 | a) | 01/03/19 | e) | - | a) | 146984.46 | a) | 100% | c) | 100% | a) | 15 | Completed | 1
| 069 | [7 empty] | b) | Crucio | b) | 03/18/19 | f) | - | b) | 146984.46 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 7618.27 | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | Mesaoy - Jct. Mahayahay |  |  | Road Maintenance | 4.6 | CBRMC | a) | 160103.65 | a) | 01/03/19 | e) | - | a) | 160103.65 | a) | 100% | c) | 100% | a) | 16 | Completed
| 069 | [7 empty] | b) | Crucio | b) | 03/22/19 | f) | - | b) | 160103.65 | b) | - | d) | - | b) | 480 |  | 1
[9 empty] | c) | MAHAYAHAY IFA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
|  |  | Mesaoy - New bohol |  |  | Road Maintenance | 5.36 | MBA | a) | 165361.13 | a) | 01/03/19 | e) | - | a) | 165361.13 | a) | 100% | c) | 100% | a) | 15 | Completed
| 070 | [7 empty] | b) | Crucio | b) | 03/01/19 | f) | - | b) | 165361.13 | b) | - | d) | - | b) | 480 |  | 1
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 2543.9 | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | Mesaoy - New bohol |  |  | Road Maintenance | 5.36 | CBRMC | a) | 224851.45 | a) | 01/03/19 | e) | - | a) | 224851.45 | a) | 100% | c) | 100% | a) | 16 | Completed
| 070 | [7 empty] | b) | Crucio | b) | 03/26/19 | f) | - | b) | 224851.45 | b) | - | d) | - | b) | 480 |  | 1
[9 empty] | c) | MANDISKAB TRIBAL | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
|  |  | Bdry. Tagum - Baca - New Corella |  |  | Road Maintenance | 13.01 | MBA | a) | 217182.9 | a) | 01/03/19 | e) | - | a) | 217182.9 | a) | 100% | c) | 100% | a) | 15 | Completed | 1
| 071 | [7 empty] | b) | Crucio | b) | 03/18/19 | f) | - | b) | 217182.9 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 19550 | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | Bdry. Tagum - Baca - New Corella |  |  | Road Maintenance | 13.01 | CBRMC | a) | 214256.36 | a) | 01/03/19 | e) | - | a) | 214256.36 | a) | 100% | c) | 100% | a) | 16 | Completed | 1
| 071 | [7 empty] | b) | Crucio | b) | 03/26/19 | f) | - | b) | 214256.36 | b) | - | d) | - | b) | 480 |  | 1
[9 empty] | c) | DURIAN DACUDAO | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
|  |  | Prk. 1, Maunlom - Prk. 6 Maunlom Road |  |  | Road Maintenance | 3.56 | MBA | a) | 150912.87 | a) | 01/03/19 | e) | - | a) | 150912.87 | a) | 100% | c) | 100% | a) | 15 | Completed | 1
| 147 | [7 empty] | b) | Crucio | b) | 03/01/19 | f) | - | b) | 150912.87 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 23025 | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | Prk. 1, Maunlom - Prk. 6 Maunlom Road |  |  | Road Maintenance | 3.56 | CBRMC | a) | 63973.36 | a) | 01/03/19 | e) | - | a) | 63973.36 | a) | 100% | c) | 100% | a) | 16 | Completed | 1
| 147 | [7 empty] | b) | Crucio | b) | 03/22/19 | f) | - | b) | 63973.36 | b) | - | d) | - | b) | 480 |  | 1
[9 empty] | c) | THE BEST VEGETABLE | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
1
|  |  | New Visayas - Binancian |  |  | Road Maintenance | 7.77 | MBA | a) | 14814.34 | a) | 01/03/19 | e) | - | a) | 14814.34 | a) | 100% | c) | 100% | a) | 15 | Completed
| 149 | [7 empty] | b) | Crucio | b) | 03/18/19 | f) | - | b) | 14814.34 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 5,000.00 | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | New Visayas - Binancian |  |  | Road Maintenance | 7.77 | CBRMC | a) | 129495.6 | a) | 01/03/19 | e) | - | a) | 129495.6 | a) | 100% | c) | 100% | a) | 16 | Completed | 1
| 149 | [7 empty] | b) | Crucio | b) | 03/22/19 | f) | - | b) | 129495.6 | b) | - | d) | - | b) | 480 |  | 1
[9 empty] | c) | BUAN IFA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
|  |  | Datu Balong - Prk. Mamalian |  |  | Road Maintenance | 3.46 | MBA | a) | 117454.89 | a) | 01/03/19 | e) | - | a) | 117454.89 | a) | 100% | c) | 39.37% | a) | 15 | Completed | 1
| 150 | [7 empty] | b) | Crucio | b) | 03/18/19 | f) | - | b) | 117454.89 | b) | - | d) | - | b) | 450 |  | 1
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 10115 | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | Datu Balong - Prk. Mamalian |  |  | Road Maintenance | 3.46 | CBRMC | a) | 59264.42 | a) | 01/03/19 | e) | - | a) | 59264.42 | a) | 100% | c) | 100% | a) | 16 | Completed | 1
| 150 | [7 empty] | b) | Crucio | b) | 03/28/19 | f) | - | b) | 59264.42 | b) | - | d) | - | b) | 480 |  | 1
[9 empty] | c) | DATU BALONG FA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [7 empty] | 1
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 1
| A.2 GENERAL FUND CY 2019 |  |  |  |  | Road Maintenance | KM | MBA/CBRMC | a) | 11,618,834.00 | a) | 01/03/19 | e) | - | a) | 11,618,834.00 | a) | 66% | c) | 66% | a) | 42 | See list of Provincial Roads
| Road ID |  | 1. Maintenance Of Various Prov'l. Roads and Bridges Dist 2 |  |  |  | 288.26 |  | b) | Matuguinas | b) | 01/03/19 | f) | - | b) | 11,618,834.00 | b) | - | d) | - | b) | 924 |  | FS
[9 empty] | c) | PEO/CBRMC | c) | 12/31/19 | g) | - | c) | - | [7 empty] | AC
| 11DAN | [9 empty] | d) | - | [11 empty] | AC
[9 empty] | d) | 261 days | d) | - | [11 empty] | AC
|  |  | Cebulano - Mangalcal |  |  | Road Maintenance | 4.17 | MBA | a) | 142161.87 | a) | 01/03/19 | e) | - | a) | 142161.87 | a) | 100% | c) | 100% | a) | 9 | Completed | AC
|  | 073 | [6 empty] | b) | Clar | b) | 2019-01-15 | f) | - | b) | 142161.87 | b) | - | d) | - | b) | 18 |  | 2
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 118,609.29 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | Tubod - basa - Mangalcal |  |  | Road Maintenance | 3.93 | MBA | a) | 156875.9 | a) | 01/03/19 | e) | - | a) | 156875.9 | a) | 100% | c) | 100% | a) | 9 | Completed | 2
| 074 | [7 empty] | b) | Clar | b) | 2019-01-15 | f) | - | b) | 156875.9 | b) | - | d) | - | b) | 18 |  | 2
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 143,372.65 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | Upper Mangalcal - Lower Mangalcal |  |  | Road Maintenance | 2.43 | CBRMC | a) | 79237.14 | a) | 01/03/19 | e) | - | a) | 79237.14 | a) | 100% | c) | 100% | a) | 9 | Completed | 2
| 078 | [7 empty] | b) | Clar | b) | 2019-01-14 | f) | - | b) | 79237.14 | b) | - | d) | - | b) | 27 |  | 2
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 69,430.97 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | Jct. Highway Carmen - Mangalcal - Tubod |  |  | Road Maintenance | 11.34 | MBA | a) | 463135.67 | a) | 01/03/19 | e) | - | a) | 463135.67 | a) | 100% | c) | 100% | a) | 9 | Completed | 2
| 082 | [7 empty] | b) | Clar | b) | 01/10/19 | f) | - | b) | 463135.67 | b) | - | d) | - | b) | 45 |  | 2
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 170,106.43 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | Jct. Highway Carmen - Mangalcal - Tubod |  |  | Road Maintenance | 11.34 | CBRMC | a) | 253557.37 | a) | 01/03/19 | e) | - | a) | 253557.37 | a) | 100% | c) | 100% | a) | 10 | Completed | 2
| 082 | [7 empty] | b) | Maligro | b) | 03/25/19 | f) | - | b) | 253557.37 | b) | - | d) | - | b) | 40 |  | 2
[9 empty] | c) | TUBOD CENTRO LOWER IRRIGATORS ASSOCIATION | c) | 09/25/19 | g) | 2019-12-31 | c) | - | [7 empty] | 2
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 2
|  |  | Jct. Highway Sto. Niño - Kabanlakan - La Paz |  |  | Road Maintenance | 2.13 | MBA | a) | 76067.88 | a) | 01/03/19 | e) | - | a) | 76067.88 | a) | 100% | c) | 100% | a) | 9 | Completed | 2
| 084 | [7 empty] | b) | Clar | b) | 01/10/19 | f) | - | b) | 76067.88 | b) | - | d) | - | b) | 45 |  | 2
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 66,477.91 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | Ising - Sto Niño |  |  | Road Maintenance | 2.07 | CBRMC | a) | 82413.14 | a) | 01/03/19 | e) | - | a) | 82413.14 | a) | 100% | c) | 100% | a) | 5 | Completed | 2
| 085 | [7 empty] | b) | Clar | b) | 01/17/19 | f) | - | b) | 82413.14 | b) | - | d) | - | b) | 15 |  | 2
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 27,093.24 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | Ising - Sadpodon - Taba - Dila -Dila |  |  | Road Maintenance | 5.68 | MBA | a) | 248941.33 | a) | 01/03/19 | e) | - | a) | 248941.33 | a) | 100% | c) | 100% | a) | 9 | Completed | 2
| 086 | [7 empty] | b) | Clar | b) | 01/12/19 | f) | - | b) | 248941.33 | b) | - | d) | - | b) | 27 |  | 2
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 82,329.02 | [7 empty] | 2
[9 empty] | d) | - | d) | - |  |  |  | . | [7 empty] | 2
2
|  |  | Tuganay - taba |  |  | Road Maintenance | 4.27 | CBRMC | a) | 291377.9 | a) | 01/03/19 | e) | - | a) | 291377.9 | a) | 70% | c) | 70% | a) | 9 | Completed
| 087 | [7 empty] | b) | Clar | b) | 01/09/19 | f) | - | b) | 291377.9 | b) | - | d) | - | b) | 27 |  | 2
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 12/31/2019 | c) | 238,412.28 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | Jct. Highway Tuganay - Taba |  |  | Road Maintenance | 4.4 | MBA | a) | 32972.82 | a) | 01/03/19 | e) | - | a) | 32972.82 | a) | 65% | c) | 65% | a) | 9 | Completed | 2
| 088 | [7 empty] | b) | Clar | b) | 01/22/19 | f) | - | b) | 32972.82 | b) | - | d) | - | b) | 18 |  | 2
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 12/31/2019 | c) | 22,639.09 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | Jct. Highway Ising - Magsaysay |  |  | Road Maintenance | 10.84 | CBRMC | a) | 417818.12 | a) | 01/03/19 | e) | - | a) | 417818.12 | a) | 60% | c) | 60% | a) | 10 | Completed | 2
| 089 | [7 empty] | b) | Clar | b) | 01/22/19 | f) | - | b) | 417818.12 | b) | - | d) | - | b) | 50 |  | 2
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 12/31/2019 | c) | 313,488.39 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | New Camiling - Alejal - Lower Magsaysay |  |  | Road Maintenance | 6.73 | MBA | a) | 240878.08 | a) | 01/03/19 | e) | - | a) | 240878.08 | a) | 80% | c) | 80% | a) | 4 | Completed | 2
| 091 | [7 empty] | b) | Clar | b) | 01/22/19 | f) | - | b) | 240878.08 | b) | - | d) | - | b) | 20 |  | 2
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 12/31/2019 | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | Jct. highway Tuganay - Anibongan |  |  | Road Maintenance | 3.66 | CBRMC | a) | 150684.44 | a) | 01/03/19 | e) | - | a) | 150684.44 | a) | 100% | c) | 100% | a) | 6 | Completed | 2
| 094 | [7 empty] | b) | Clar | b) | 01/22/19 | f) | - | b) | 150684.44 | b) | - | d) | - | b) | 18 |  | 2
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 12/31/2019 | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | Anibongan - Guadalupe |  |  | Road Maintenance | 2.48 | MBA | a) | 91325.06 | a) | 01/03/19 | e) | - | a) | 91325.06 | a) | 100% | c) | 100% | a) | 9 | Completed | 2
| 095 | [7 empty] | b) | Clar | b) | 01/23/19 | f) | - | b) | 91325.06 | b) | - | d) | - | b) | 18 |  | 2
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 12/31/2019 | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | Tuganay - Anibongan - San Isidro |  |  | Road Maintenance | 7.22 | CBRMC | a) | 139979.8 | a) | 01/03/19 | e) | - | a) | 139979.8 | a) | 100% | c) | 100% | a) | 9 | Completed | 2
| 096 | [7 empty] | b) | Clar | b) | 01/24/19 | f) | - | b) | 139979.8 | b) | - | d) | - | b) | 36 |  | 2
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 12/31/2019 | c) | 1890.37 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | Jct. Anibongan - Prk. 2, 7, 5, San Isidro |  |  | Road Maintenance | 3.14 | MBA | a) | 104378.03 | a) | 01/03/19 | e) | - | a) | 104378.03 | a) | 100% | c) | 100% | a) | 10 | Completed | 2
| 097 | [7 empty] | b) | Clar | b) | 01/24/19 | f) | - | b) | 104378.03 | b) | - | d) | - | b) | 20 |  | 2
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 12/31/2019 | c) | 56,087.50 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | Anibongan - Salvacion - Cabay-angan |  |  | Road Maintenance | 6.93 | CBRMC | a) | 415461.61 | a) | 01/03/19 | e) | - | a) | 415461.61 | a) | 100% | c) | 100% | a) | 9 | Completed | 2
| 098 | [7 empty] | b) | Clar | b) | 01/25/19 | f) | - | b) | 415461.61 | b) | - | d) | - | b) | 45 |  | 2
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 12/31/2019 | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | Jct. Highway Guadalupe - Bdry. Tagum |  |  | Road Maintenance | 7.9 | MBA | a) | 456131.09 | a) | 01/03/19 | e) | - | a) | 456131.09 | a) | 100% | c) | 100% | a) | 9 | Completed | 2
| 101 | [7 empty] | b) | Clar | b) | 01/25/19 | f) | - | b) | 456131.09 | b) | - | d) | - | b) | 18 |  | 2
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 12/31/2019 | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | Jct. Highway Guadalupe - Bdry. Tagum |  |  | Road Maintenance | 7.9 | CBRMC | a) | 228201.66 | a) | 01/03/19 | e) | - | a) | 228201.66 | a) | 100% | c) | 100% | a) | 8 | Completed | 2
| 101 | [7 empty] | b) | Maligro | b) | 03/25/19 | f) | - | b) | 228201.66 | b) | - | d) | - | b) | 40 |  | 2
[9 empty] | c) | LAMPIA PAG-ASA IRRIGATORS ASSOCIATION, INC. | c) | 12/25/19 | g) | 12/31/2019 | c) | - | [7 empty] | 2
[9 empty] | d) | 3 quarters | d) | - | [11 empty] | 2
|  |  | Poblacion Dujali - Prk. 8 Dujali |  |  | Road Maintenance | 8.2 | MBA | a) | 285600.05 | a) | 01/03/19 | e) | - | a) | 285600.05 | a) | 100% | c) | 100% | a) | 10 | Completed | 2
| 105 | [7 empty] | b) | Clar | b) | 01/28/19 | f) | - | b) | 285600.05 | b) | - | d) | - | b) | 50 |  | 2
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 12/31/2019 | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | Dujali - San Isidro |  |  | Road Maintenance | 3 | CBRMC | a) | 130319.3 | a) | 01/03/19 | e) | - | a) | 130319.3 | a) | 100% | c) | 100% | a) | 8 | Completed | 2
| 107 | [7 empty] | b) | Gamad | b) | 01/28/19 | f) | - | b) | 130319.3 | b) | - | d) | - | b) | 30 |  | 2
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 12/31/2019 | c) | 45,943.12 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | Prk. 5, RJS - Prk. 6 New Casay |  |  | Road Maintenance | 2.73 | MBA | a) | 235277 | a) | 01/03/19 | e) | - | a) | 235277 | a) | 100% | c) | 100% | a) | 2 | Completed | 2
| 109 | [7 empty] | b) | Gamad | b) | 01/28/19 | f) | - | b) | 235277 | b) | - | d) | - | b) | 6 |  | 2
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 12/31/2019 | c) | 90,745.35 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | Prk. 5 - Prk. 1 Pawas Dujali |  |  | Road Maintenance | 2.18 | CBRMC | a) | 76067.68 | a) | 01/03/19 | e) | - | a) | 76067.68 | a) | 100% | c) | 100% | a) | 10 | Completed | 2
| 112 | [7 empty] | b) | Gamad | b) | 01/18/19 | f) | - | b) | 76067.68 | b) | - | d) | - | b) | 20 |  | 2
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 12/31/2019 | c) | 40,112.50 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | Dujali - Balisong - Magupising |  |  | Road Maintenance | 5.52 | MBA | a) | 260591.93 | a) | 01/03/19 | e) | - | a) | 260591.93 | a) | 100% | c) | 100% | a) | 4 | Completed | 2
| 113 | [7 empty] | b) | Gamad | b) | 01/09/19 | f) | - | b) | 260591.93 | b) | - | d) | - | b) | 8 |  | 2
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 12/31/2019 | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | Dujali - Pawas - San Vicente |  |  | Road Maintenance | 4.42 | CBRMC | a) | 139536.42 | a) | 01/03/19 | e) | - | a) | 139536.42 | a) | 100% | c) | 100% | a) | 10 | Completed | 2
| 117 | [7 empty] | b) | Gamad | b) | 01/22/19 | f) | - | b) | 139536.42 | b) | - | d) | - | b) | 18 |  | 2
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 12/31/2019 | c) | 52,133.86 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | Jct. Salvacion - San Vicente - Cabay-angan |  |  | Road Maintenance | 3.45 | MBA | a) | 247460.9 | a) | 01/03/19 | e) | - | a) | 247460.9 | a) | 100% | c) | 100% | a) | 10 | Completed | 2
| 118 | [7 empty] | b) | Gamad | b) | 01/23/19 | f) | - | b) | 247460.9 | b) | - | d) | - | b) | 18 |  | 2
[9 empty] | c) | PEO | c) | 02/31/19 | g) | 12/31/2019 | c) | 151,887.50 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | Jct. Salvacion - San Vicente - Cabay-angan |  |  | Road Maintenance | 3.45 | CBRMC | a) | 152134.44 | a) | 01/03/19 | e) | - | a) | 152134.44 | a) | 100% | c) | 100% | a) | 8 | Completed | 2
| 118 | [7 empty] | b) | Gamad | b) | 03/26/19 | f) | - | b) | 152134.44 | b) | - | d) | - | b) | 36 |  | 2
[9 empty] | c) | BALISONG SAN VICENTE IRRIGATORS ASSOCIATION | c) | 12/26/19 | g) | 12/31/2019 | c) | [8 empty] | 2
[9 empty] | d) | 3 quarters | d) | - | [10 empty] | Completed | 2
|  |  | Dujali - San Miguel |  |  | Road Maintenance | 3.95 | MBA | a) | 101202.04 | a) | 01/03/19 | e) | - | a) | 101202.04 | a) | 80% | c) | 90% | a) | 11 |  | 2
| 119 | [7 empty] | b) | Gamad | b) | 01/10/19 | f) | - | b) | 101202.04 | b) | - | d) | - | b) | 22 |  | 2
[9 empty] | c) | PEO | c) | 12/31/19 | g) | - | c) | 90,350.03 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | San Miguel - Casig-ang |  |  | Road Maintenance | 2.55 | CBRMC | a) | 79237.14 | a) | 01/03/19 | e) | - | a) | 79237.14 | a) | 100% | c) | 100% | a) | 10 | Completed | 2
| 122 | [7 empty] | b) | Gamad | b) | 01/24/19 | f) | - | b) | 79237.14 | b) | - | d) | - | b) | 10 |  | 2
[9 empty] | c) | BALISONG SAN VICENTE IRRIGATORS ASSOCIATION | c) | 12/31/19 | g) | 12/31/2019 | c) | 40,112.50 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | Prk. Magsaysay - Lunga-og - Dalisay |  |  | Road Maintenance | 2.81 | MBA | a) | 79762.14 | a) | 01/03/19 | e) | - | a) | 79762.14 | a) | 100% | c) | 100% | a) | 8 | Completed | 2
| 127 | [7 empty] | b) | Gamad | b) | 01/30/19 | f) | - | b) | 79762.14 | b) | - | d) | - | b) | 8 |  | 2
[9 empty] | c) | PEO | c) | 12/31/19 | g) | 12/31/2019 | c) | 40,612.50 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | Prk. Apitong - Upper Balisong - Dalisay |  |  | Road Maintenance | 4.6 | CBRMC | a) | 137846.03 | a) | 01/03/19 | e) | - | a) | 137846.03 | a) | 100% | c) | 100% | a) | 8 | Completed | 2
| 128 | [7 empty] | b) | Gamad | b) | 01/31/19 | f) | - | b) | 137846.03 | b) | - | d) | - | b) | 8 |  | 2
[9 empty] | c) | BALISONG SAN VICENTE IRRIGATORS ASSOCIATION | c) | 12/31/19 | g) | 12/31/2019 | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | Sitio Paradise - Magkakaisa - Esperanza |  |  | Road Maintenance | 1.75 | MBA | a) | 66552.75 | a) | 01/03/19 | e) | - | a) | 66552.75 | a) | 100% | c) | 100% | a) | 8 | Completed | 2
| 129 | [7 empty] | b) | 79762.14 | b) | 01/22/19 | f) | - | b) | 66552.75 | b) | - | d) | - | b) | 8 |  | 2
[9 empty] | c) | Gamad | c) | 12/31/19 | g) | 12/31/2019 | c) | 22,246.26 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | Los Amigos 1 - Esperanza - Los Amigos 2 |  |  | Road Maintenance | 3.59 | CBRMC | a) | 101202.04 | a) | 01/03/19 | e) | - | a) | 101202.04 | a) | 100% | c) | 100% | a) | 10 | Completed | 2
| 130 | [7 empty] | b) | Gamad | b) | 01/24/19 | f) | - | b) | 101202.04 | b) | - | d) | - | b) | 20 |  | 2
[9 empty] | c) | BALISONG SAN VICENTE IRRIGATORS ASSOCIATION | c) | 12/31/19 | g) | 12/31/2019 | c) | 50,837.50 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | Mugas - Lunga-og |  |  | Road Maintenance | 2.68 | MBA | a) | 66552.75 | a) | 01/03/19 | e) | - | a) | 91,693.64 | a) | 100% | c) | 100% | a) | 6 | Completed | 2
| 132 | [7 empty] | b) | 79762.14 | b) | 01/17/19 | f) | - | b) | 91,693.64 | b) | - | d) | - | b) | 24 |  | 2
[9 empty] | c) | Gamad | c) | 12/31/19 | g) | 12/31/2019 | c) | 50,837.50 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | Pantaron - Mugas |  |  | Road Maintenance | 3.35 | CBRMC | a) | 101202.04 | a) | 01/03/19 | e) | - | a) | 101202.04 | a) | 100% | c) | 100% | a) | 9 | Completed | 2
| 133 | [7 empty] | b) | Gamad | b) | 01/23/19 | f) | - | b) | 101202.04 | b) | - | d) | - | b) | 18 |  | 2
[9 empty] | c) | BALISONG SAN VICENTE IRRIGATORS ASSOCIATION | c) | 12/31/19 | g) | 12/31/2019 | c) | 90,349.93 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | Sto. Tomas - Bdry. Mamacao |  |  | Road Maintenance | 4.9 | MBA | a) | 110710.44 | a) | 01/03/19 | e) | - | a) | 110710.44 | a) | 100% | c) | 100% | a) | 10 | Completed | 2
| 135 | [7 empty] | b) | 79762.14 | b) | 01/21/19 | f) | - | b) | 110710.44 | b) | - | d) | - | b) | 40 |  | 2
[9 empty] | c) | Gamad | c) | 12/31/19 | g) | 12/31/2019 | c) | 50,837.50 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | Fd. Rd. 3 - San Jose |  |  | Road Maintenance | 4.55 | CBRMC | a) | 147367.49 | a) | 01/03/19 | e) | - | a) | 147367.49 | a) | 100% | c) | 100% | a) | 10 | Completed | 2
| 136 | [7 empty] | b) | Gamad | b) | 01/25/19 | f) | - | b) | 147367.49 | b) | - | d) | - | b) | 30 |  | 2
[9 empty] | c) | BALISONG SAN VICENTE IRRIGATORS ASSOCIATION | c) | 12/31/19 | g) | 12/31/2019 | c) | 56,174.69 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | Menzi - balagunan - Tulalian |  |  | Road Maintenance | 10.63 | MBA | a) | 520167.79 | a) | 01/03/19 | e) | - | a) | 520167.79 | a) | 100% | c) | 100% | a) | 6 | Completed | 2
| 138 | [7 empty] | b) | 79762.14 | b) | 01/07/19 | f) | - | b) | 520167.79 | b) | - | d) | - | b) | 18 |  | 2
[9 empty] | c) | Gamad | c) | 12/31/19 | g) | 12/31/2019 | c) | 204,850.57 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | Jct. Bdry. Tagum - Talomo |  |  | Road Maintenance | 12.01 | CBRMC | a) | 407429.19 | a) | 01/03/19 | e) | - | a) | 407429.19 | a) | 100% | c) | 100% | a) | 10 | Completed | 2
| 145 | [7 empty] | b) | Gamad | b) | 01/11/19 | f) | - | b) | 407429.19 | b) | - | d) | - | b) | 50 |  | 2
[9 empty] | c) | BALISONG SAN VICENTE IRRIGATORS ASSOCIATION | c) | 12/31/19 | g) | 12/31/2019 | c) | 168,544.84 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | San Jose - Sitio Mahayahay, Magwawa |  |  | Road Maintenance | 0.84 | MBA | a) | 7919.35 | a) | 01/03/19 | e) | - | a) | 7919.35 | a) | 100% | c) | 100% | a) | 2 | Completed | 2
| 151 | [7 empty] | b) | 79762.14 | b) | 01/16/19 | f) | - | b) | 7919.35 | b) | - | d) | - | b) | 8 |  | 2
[9 empty] | c) | Gamad | c) | 12/31/19 | g) | 12/31/2019 | c) | 1,509.27 | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| B. 20% DEVELOPMENT FUND CY 2019 | [22 empty] | FS
| Road ID |  | 1. Rehabilitation Of Various Prov'l. Roads and Bridges Dist. 1 |  |  | Road Rehabilitation | KM | MBA | a) | 41465029 | a) | 01/03/19 | e) | - | a) | 41465029 | a) | - | c) | - | a) | 46 | See list of Provincial Roads | FS
[7 empty] | 109.55 |  | b) | Paraguya | b) | 01/03/19 | f) | - | b) | 41465029 | b) | - | d) | - | b) | 920 |  | AC
| 11DAN | [7 empty] | c) | PEO | c) | 12/31/19 | g) | - | c) | - | [7 empty] | AC
[11 empty] | d) | - | [11 empty] | AC
[9 empty] | d) | 261 days | d) | - | [11 empty] | AC
[6 empty] | Road Rehabilitation |  |  | a. )P 500,000.00 |  | a.) 01/31/19 |  |  |  | a.) 500,000.00 | [8 empty] | 1
|  |  | Purok 10 Pob. Road, New Corella | [7 empty] | b.) Feb. 16, 2019 |  |  |  | b.) 500,000.00 | [7 empty] | Completed | 1
[13 empty] | g.) Feb. 28, 2019 | [10 empty] | 1
1
[6 empty] | Road Rehabilitation |  |  | a.)1,815,000.00 |  | a.) 01/31/19 |  |  |  | a.) 1,815,000.00 | [8 empty] | 1
|  |  | Purok 7 Pob- Jct. New Sambog | [7 empty] | b.)March 1, 2019 |  |  |  | b.) 1,815,000.00 | [7 empty] | Completed | 1
[13 empty] | g.) May 15, 2019 | [10 empty] | 1
1
[6 empty] | Road Rehabilitation |  |  | a.) 1,389,000.00 |  | a.) 01/31/19 |  |  |  | a.) 1,389,000.00 | [7 empty] | Completed with a savings of P303,898.08 furtherance and is for implementation | 1
|  |  | Del Pilar- El Unido Road | [5 empty] | b.) Fabian |  | b.) March 18,2019 |  |  |  | a.) 1,389,000.00 | [8 empty] | 1
[13 empty] | g.) May 8, 2019 | [10 empty] | 1
|  |  | SUPPLEMENTAL BUDGET NO 4 CY 2019 / CONTINUING APPROPRIATION | [20 empty] | AC
AC
[9 empty] | a.) 7,742,775.95 | [5 empty] | a.) 7,742,775.95 | [7 empty] | Waiting for the delivery of materials | 1
|  |  | Impvt. of Km. 9 Sagayen - Sawata Provincial Road Phase II | [5 empty] | b.) Kenny | [5 empty] | b.) 7,742,775.95 | [8 empty] | 1
1
1
| Road ID |  | 1. Rehabilitation Of Various Prov'l. Roads and Bridges Dist 2 |  |  | Road Rehabilitation | KM | Admin | a) | 46740117 | a) | 01/03/19 | [10 empty] | See list of Provincial Roads | AC
[7 empty] | 115.62 |  | b) | Matuguinas | b) | - | [11 empty] | AC
| 11DAN | [7 empty] | c) | PEO | c) | - | [11 empty] | AC
[11 empty] | d) | - | [11 empty] | AC
[9 empty] | d) | 261 days | d) | - | [11 empty] | AC
[6 empty] | Road Rehabilitation |  |  | a.) 515,000.00 |  | a.) 03/12/19 |  |  |  | a.) 515,000.00 | [8 empty] | 2
|  |  | Jct. Highway -Tubod - Bagong Silang | [5 empty] | b.) Clar |  | b.) March 18, 2019 |  |  |  | b.) 515,000.00 | [7 empty] | Completed | 2
[13 empty] | g.) June 15, 2019 | [10 empty] | 2
2
[6 empty] | Road Rehabilitation |  |  | a.) 390,000.00 |  | a.) 03/12/19 |  |  |  | a.) 390,000.00 | [8 empty] | 2
|  |  | Cebulano- Luceta | [5 empty] | b.) Clar |  | b.) March 8, 2019 |  |  |  | b.) 390,000.00 | [7 empty] | Completed | 2
[13 empty] | g.) June 15, 2019 | [10 empty] | 2
2
[6 empty] | Road Rehabilitation |  |  | a.) 295,000.00 |  | a.) 03/12/19 |  |  |  | a.) 295,000.00 | [8 empty] | 2
|  |  | Lower Asuncion - Upper Asuncion | [5 empty] | b.) Clar |  | b.) March 18, 2019 |  |  |  | b.) 295,000.00 | [7 empty] | Completed | 2
[13 empty] | g.) June 15, 2019 | [10 empty] | 2
2
[6 empty] | Road Rehabilitation |  |  | a.) 1,220,000.00 |  | a.) 03/12/19 |  |  |  | a.) 1,220,000.00 | [8 empty] | 2
|  |  | Jct. Highway - Sto. Nino - La Paz - San Vicente | [5 empty] | b.)Obar |  | b.) March 18, 2019 |  |  |  | b.) 1,220,000.00 | [7 empty] | Completed | 2
[13 empty] | g.) Sept. 30, 2019 | [10 empty] | 2
2
|  |  | Alejal - Alemag |  |  | Road Rehabilitation | 1.79 |  | a) | 970000 | a) | 2019-03-18 | e) | - | a) | 970000 | a) | 100% | c) | 100% | a) | 7 | Completed. Financially completed | 2
| 092 | [7 empty] | b) | Gamad/Clar | b) | 2019-05-20 | f) | - | b) | 970000 | b) | 100 | d) | 0% | b) | 20 |  | 2
[9 empty] | c) | - | c) | 2019-09-12 | g) | Sept. 30, 2019 | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
[6 empty] | Road Rehabilitation |  |  | a.) 640,000.00 |  | a.) 03/12/19 |  |  |  | a.) 640,000.00 | [8 empty] | 2
|  |  | Mabaus - Cabay -angan | [5 empty] | b.)Clar |  | b.) Maech 18, 2019 |  |  |  | a.) 640,000.00 | [7 empty] | Completed | 2
[13 empty] | g.) July 30, 2019 | [10 empty] | 2
2
[6 empty] | Road Rehabilitation |  |  | a.) 280,000.00 |  | a.) 03/12/19 |  |  |  | a.) 280,000.00 | [8 empty] | 2
|  |  | Mabaus - Salvacion | [5 empty] | b.)Clar |  | b.) March 18, 2019 |  |  |  | a.) 280,000.00 | [8 empty] | 2
[13 empty] | g.) June 30, 2019 | [9 empty] | Completed | 2
2
|  |  | Dujali - New Casay |  |  |  | 3.2 | Admin | a) | 640000 | a) | 2019-05-16 | e) | - | a) | 640000 | a) | 100% | c) | 100% | a) | 10 |  | 2
| 106 | [7 empty] | b) | Gamad/Clar | b) | 2019-06-17 | f) | 40 | b) | 640000 | b) |  | d) | - | b) | 40 | Completed | 2
[9 empty] | c) | - | c) |  | g) | 10/15/2019 | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
[6 empty] | Road Rehabilitation |  |  | a.) 450,000.00 |  | a.) 03/12/19 |  |  |  | a.) 450,000.00 | [8 empty] | 2
|  |  | New Casay - Bugtong Talisay | [5 empty] | b.)Clar |  | b.) March 18, 2019 |  |  |  | a.) 450,000.00 | [7 empty] | Completed | 2
[13 empty] | g.)June 30, 2019 | [10 empty] | 2
2
[6 empty] | Road Rehabilitation |  |  | a.)220,000.00 |  | a.) 03/12/19 |  |  |  | a.)220,000.00 |  | a.) 100 % |  | c.)100% |  |  |  |  | 2
|  |  | Purok 6 Cabay-angan - Esti | [5 empty] | b.) Gamad |  | b.) March 18, 2019 |  |  |  | a.)220,000.00 | [7 empty] | Completed | 2
[13 empty] | g.) June 30, 2019 | [10 empty] | 2
2
[6 empty] | Road Rehabilitation |  |  | a.)250,000.00 |  | a.) March 12, 2019 | [5 empty] | a.) 100 % |  | c.)100% |  |  |  |  | 2
|  |  | Dujali - Sitio Pawas | [5 empty] | b.) Gamad |  | b.) March 18, 2019 | [11 empty] | Completed | 2
[13 empty] | g.) Jun 30, 2019 | [10 empty] | 2
2
[6 empty] | Road Rehabilitation |  |  | a.) 280,000.00 |  | a.) March 12, 2019 | [5 empty] | a.) 100 % |  | c.)100% |  |  |  |  | 2
|  |  | Purok 1 to Purok 2 Sitio Pawas | [6 empty] | b.) Gamad | b.) March 18, 2019 | [11 empty] | Completed | 2
[13 empty] | g.) Jun 30, 2019 | [10 empty] | 2
2
|  |  | San Miguel - Crossing Kinamayan |  |  | Road Rehabilitation | 2.8 | Admin | a) | 560000 | a) | 2019-06-25 | e) | - | a) | 560000 | a.) 100 % |  | c.)100% |  | a) | - |  | 2
| 120 | [7 empty] | b) | Nasol | b) | Sept. 19, 2019 | f) | - | b) | 560000 | b) | - | d) | - | b) | - | Completed | 2
[9 empty] | c) | - | c) | - | g) | Nov. 30, 2019 | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | Kinamayan - Lunga-og |  |  | Road Rehabilitation | 2.59 | Admin | a) | 520000 | a) | 2019-03-18 | e) | - | a) | 520000 | a) | 100% | c) | 100% | a) | 9 | Completed | 2
| 126 | [7 empty] | b) | Gamad/Clar | b) | 5/202/019 | f) | - | b) | 520000 | b) | - | d) | - | b) | 36 |  | 2
[9 empty] | c) | - | c) |  | g) | Sept. 30, 2019 | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
[9 empty] | a.) 540,000.00 |  | a.) March 12, 2019 |  |  |  | a.) 540,000.00 |  | a.)100% |  | c.)100% |  |  |  | Completed | 2
|  |  | Nafco - Bobongon |  |  | Road Rehabilitation |  |  | b. Gamad |  | b.) march 18, 2019 |  |  |  | b.) 540,000.00 | [8 empty] | 2
[13 empty] | g.) June 30, 2019 | [10 empty] | 2
2
2
|  |  | Prk. Narafil - Prk. Daisy Magupising |  |  | Road Rehabilitation | 19.16 | Admin | a) | 300117 | a) | 2019-06-25 | e) | - | a) | 300117 | a) | 100% | c) | 100% | a) | - | Completed | 2
| 148 | [7 empty] | b) | Gamad/Clar | b) | Sept. 16, 2019 | f) | - | b) | 300117 | b) | - | d) | - | b) | - |  | 2
[9 empty] | c) | - | c) | - | g) | Oct. 18, 2019 | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 2. Various of Local Roads & Drainage Development Project (Provincewide) |  |  |  |  | Road Drainage rehabiliated |  | Admin | a) | 15000000 | [12 empty] | See projects listed below | 2
[9 empty] | b) | Paraguya | [13 empty] | AC
[9 empty] | c) | PEO | [13 empty] | AC
[9 empty] | d) | - | [13 empty] | AC
|  |  | Rehab. of Anibongan-Salvacion-Cabay-angan Provincial Road with Drainage |  |  | Road Drainage rehabiliated | - | - | a) | 2000000 | a) | 2019-01-14 | e) | - | a) | 2000000 | a) | 100% | c) | 100% | a) | 1 | Completed | 2
| 2.1 | [7 empty] | b) | Toquero | b) | 2019-05-22 | f) | - | b) | 2000000 | b) | - | d) | - | b) | 4 | Fiancial obligation still on process | 2
[9 empty] | c) | PEO | c) | 2019-08-04 | g) | Dec. 31, 2019 | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | Rehab./Impv't. of Sto. Tomas-Bdry. Mamacao Provincial Road |  |  | Road Drainage rehabiliated | - | Admin | a) | 1500000 | a) | 2019-01-14 | e) | - | a) | 1500000 | a) | 100% | c) | 100% | a) | - | Completed Financial obligation on process
| 2.4 | [7 empty] | b) | Toquero | b) | 2019-05-31 | f) | 60 | b) | 1500000 | b) | - | d) | - | b) | - |  | 2
[9 empty] | c) | PEO | c) | 2019-07-15 | g) | Dec. 31, 2019 | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
| 4. Various Government Buildings and Facilities Development Project (Provincewide) |  |  |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of recipients | - | Admin | a) | 27000000 | [12 empty] | See projects listed below | 2
[9 empty] | b) | Medalla | [13 empty] | AC
[9 empty] | c) | PEO | [13 empty] | AC
[9 empty] | d) | - | [13 empty] | AC
|  |  | Const. of GYM Bleacher at Suaybaguio Rina, Elem. School |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of recipients | - | #REF! | a) | 1000000 | a) | - | e) | - | a) | 1000000 | a) | 100% | c) | 100% | a) | - | Completed | 1
|  | 11 | [6 empty] | b) | Mayang | b) | 6/3/2019 | f) | - | b) | 1000000 | b) | 64 | d) | 0% | b) | - |  | 1
[9 empty] | c) | PEO | c) | 8/01/2019 | g) |  | c) | - | [7 empty] | 1
[9 empty] | d) | - | d) | - | [11 empty] | 1
| 5. Stimulus Projects for Various Barangays a. 20% Development Fund CY 2019 |  |  |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | Admin | a) | 41500000 | [12 empty] | See projects listed below | 2
[9 empty] | b) | Medalla | [13 empty] | AC
[9 empty] | c) | PEO | [13 empty] | AC
[9 empty] | d) | - | [13 empty] | AC
AC
| IGCS | [22 empty] | 2
| 5.42 |  | Rehab. Of Health Center, Aumbay, IGCS |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) | Feb. 28, 2019 | e) | - | a) | 500000 | a) |  | c) | 48.32% | a) | 3 | Completed Financial obligation on process | AC
[9 empty] | b) | Pacquiao | b) | 7/10/2019 | f) | - | b) | 500000 | b) | - | d) |  | b) | 15 |  | 2
[9 empty] | c) | Admin | c) | 10/7/2019 | g) | - | c) | - | [7 empty] | 2
[9 empty] | d) | 90 CD | d) | - | [11 empty] | 2
| 5.46 |  | Rehab. Of Brgy. Health Center, Mambago-A, IGCS |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) | Feb. 28, 2019 | e) | - | a) | 500000 | a) |  | c) | 75.61% | a) | 3 | Completed Financial obligation on process | 2
[9 empty] | b) | Ganaba | b) | 07/2019 | f) | - | b) | 500000 | b) |  | d) |  | b) | 15 |  | 2
[9 empty] | c) | Admin | c) | 8/23/2019 | g) | - | c) | - | [7 empty] | 2
[9 empty] | d) | 45 CD | d) | - | [11 empty] | 2
| 6. Rural Electrification Project (Provincewide) |  |  |  |  | Powerlines/posts installed & rehabilitated | - | - | a) | 5000000 | [12 empty] | See projects listed below | 2
[9 empty] | b) | Kim Pao Lu | [13 empty] | AC
[9 empty] | c) | - | [13 empty] | AC
[9 empty] | d) | - | [13 empty] | AC
C. 5% CALAMITY FUND CY 2019
| 3 |  | Improvement of roads, drainage and canal |  |  | Protection dikes/slope protection | - | - | a) | 3000000 | [12 empty] | See projects listed below | 2
[9 empty] | b) | Paraguya | [13 empty] | AC
[9 empty] | c) | PEO | [13 empty] | AC
[9 empty] | d) | - | [13 empty] | AC
| a. |  | Rehab./Impv't. of New Casay-Bugtong Talisay Provincial Road (Ph.II) |  |  | creeks and canRoads/Draiange/canals rehab/improved | - | - | a) | 500000 | a) | 2019-03-12 | e) | - | a) | 500000 | a) | 100% | c) | 100% | a) | 12 | Completed | AC
[9 empty] | b) | Toquero | b) | 2019-05-30 | f) | - | b) | 500000 | b) | - | d) | - | b) | 120 |  | 2
[9 empty] | c) | Admin | c) | 2019-07-30 | g) |  | c) | - | [7 empty] | 2
[9 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | Mark | Municipality/City |  | Color
|  |  | 1 | Asuncion |  | Red
|  |  | 2 | B.E. Dujali |  | Yellow
|  | GF- GENERAL FUND | 3 | Carmen |  | Blue | [10 empty] | TF - TRUST FUND (NATIONAL FUNDED PROJECT)
|  | 20% DF - 20% DEV'T. FUND | 4 | Kapalong |  | Pink | [10 empty] | a) SLRF - Special Local Road Fund
|  | 5% CF - 5% CALAMITY FUND | 5 | New Corella |  | Gray | [10 empty] | b) KALSADA - Konkreto at Ayos na Lansangan Tungo sa Pangkalahatang Kaunlaran
|  | CO - CAPITAL OUTLAY | 6 | San Isidro |  | Orange | [10 empty] | c) PRDP - Philippine Rural Development Projects
|  | CONG. FUND - CONGRESSIONAL FUND | 7 | Sto Tomas |  | Sky Blue | [10 empty] | d) SELAP - Support to Emergency and Livelihood Assistance Project
|  |  | 8 | Talaingod |  | Violet | [10 empty] | e) PAMANA - Payapa at Masaganang Pamayanan
|  | SEF - SPECIAL EDUCATIONAL UFND | 9 | Panabo City |  | Brown | [10 empty] | f) CBRMC - Community Based Road Maintenance Contracting
|  |  | 10 | IGACOS |  | Yellow Green | [10 empty] | g) MBC - Maintenance by Contract
|  |  | 11 | Tagum City |  | Green | [10 empty] | h) PCF-Performance Challenge Fund-DILG
i) FMRDP - Farm to Market Road
j.) CMGP - Conditional Grant to Provinces
k.) OPAPP - Office of the President Adviser on the Peace Process
l.) LGSF-AM - Local Government Support Fund Assistance to Municipalities
| Prepared by: |  |  |  | Checked | [12 empty] | Recommending Approval
Noted
| GILBERT G. MAMBULAO JR |  |  |  | ELISA A. BARCENA | TESSIE G. ABABON | [9 empty] | JIVELLYN B. CO | [5 empty] | GLENN A. OLANDRIA
| Engineer II |  |  |  | Engineer IV- Engineering Dist 1, Area Engineer |  | Engineer IV-Engineering Dist 2, Area Engineer | [9 empty] | Asst. PG-Department Head |  |  |  |  | Provincial Engineer
[5 empty] | EDWIN S. MISA |  |  |  | MARILOU A. FORONDA
[5 empty] | Engineer IV- PDPM Division Head |  |  |  | Engineer IV- QC Division Head

## 2019 Projects (hidden)
PROVINCE OF DAVAO DEL NORTE
ANNUAL ACCOMPLISHMENT REPORT
CY 2019
SECTOR: ECONOMIC (INFRASTRUCTURE DEV'T. PROGRAM)
OFFICE/AGENCY: PROVINCIAL ENGINEER'S OFFICE
[5 empty] | Type | Physical | Mode | PROJECT DATA | [6 empty] | Financial (000) | Physical Accompl;ishment |  |  |  | Employment
|  | Name of Project |  |  | of | Target | of | a.)Project Cost |  | a.)Date A lot. Rel. |  | e.)# of days |  |  | a.) Program | a.) Planned |  | c.) Actual |  | Generated # |  |  | REMRRKS
[5 empty] | Project | (Discrip tion) | Impl. | b.)Project Engineer |  | b.)Date Started |  |  | suspended |  | b.)Allotment | b.) Revised |  | d.) Slippage |  | a.) Persons
[7 empty] | MBA / | c.)Implementor |  | c.)Target Compl. |  | f.) # of days extended |  |  | c.)Disbursement |  |  |  |  | b.) Man-days
[7 empty] | CBRMC |  |  |  | Date | g.)Date Completed
II. PROJECTS UNDER THE CURRENT APPROPRIATION CY 2019
A.1 GENERAL FUND CY 2019 | [6 empty] | MBA/CBRMC | a) | 18127866 | a) | 01/03/19 | e) | - | a) | 18127866 | a) | 83.63 | c) | 83.83 | a) | 46 | See list of Provincial Roads |  | AP
Road ID |  | Maintenance of Various Provincial Roads and Bridges at District 1 |  |  | Road Maintenance | KM |  | b) | Paraguya | b) | 01/03/19 | f) | - | b) | 18127866 | b) | - | d) | - | b) | 920 |  |  | FS
[6 empty] | 288.26 |  | c) | PEO/CBRMC | c) | 12/31/19 | g) | - | c) | - | [8 empty] | AC
11DAN | [9 empty] | d) | - | [12 empty] | AC
[8 empty] | d) | 261 days | d) | - | [12 empty] | AC
|  | Jct. Highway Magatos - New Bantayan |  |  | Road Maintenance | 7.1 | MBA | a) | 287307.39 | a) | 01/03/19 | e) | - | a) | 287307.39 | a) | 100% | c) | 100% | a) | 15 | Completed |  | AC
001 | [7 empty] | b) | Crucio | b) | 01/16/19 | f) | - | b) | 287307.39 | b) | - | d) | - | b) | 480 |  |  | 1
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 118693.58 | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
|  | Jct. Highway Magatos - New Bantayan |  |  | Road Maintenance | 7.1 | CBRMC | a) | 223674.22 | a) | 01/03/19 | e) | - | a) | 223674.22 | a) | 100% | c) | 100% | a) | 16 | Completed |  | 1
001 | [7 empty] | b) | Crucio | b) | 3/22/19 | f) | - | b) | 223674.22 | b) | - | d) | - | b) | 480 |  |  | 1
[8 empty] | c) | CALAFA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [8 empty] | 1
[8 empty] | d) | 3 quarters | d) | - | [12 empty] | 1
|  | Magatos-Bdry Pagsabangan |  |  | Road Maintenance | 8.33 | MBA | a) | 328740.25 | a) | 01/03/19 | e) | - | a) | 328740.25 | a) | 100% | c) | 100% | a) | 15 | Completed |  | 1
002 | [7 empty] | b) | Crucio | b) | 01/03/19 | f) | - | b) | 328740.25 | b) | - | d) | - | b) | 450 |  |  | 1
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 207258.49 | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
|  | Magatos-Bdry Pagsabangan |  |  | Road Maintenance | 8.33 | CBRMC | a) | 270763.53 | a) | 01/03/19 | e) | - | a) | 270763.53 | a) | 100% | c) | 100% | a) | 16 | Completed |  | 1
002 | [7 empty] | b) | Crucio | b) | 03/22/19 | f) | - | b) | 270763.53 | b) | - | d) | - | b) | 450 |  |  | 1
[8 empty] | c) | CALAFA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [8 empty] | 1
[8 empty] | d) | 3 quarters | d) | - | [12 empty] | 1
|  | Ilog-New Bantayan |  |  | Road Maintenance | 2.68 | MBA | a) | 131131.39 | a) | 01/03/19 | e) | - | a) | 131131.39 | a) | 100% | c) | 100% | a) | 15 | Completed |  | 1
003 | [7 empty] | b) | Crucio | b) | 01/16/19 | f) | - | b) | 131131.39 | b) | - | d) | - | b) | 450 |  |  | 1
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 49,316.69 | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
|  | Ilog-New Bantayan |  |  | Road Maintenance | 2.68 | CBRMC | a) | 65925.03 | a) | 01/03/19 | e) | - | a) | 65925.03 | a) | 100% | c) | 100% | a) | 16 | Completed |  | 1
003 | [7 empty] | b) | Crucio | b) | 03/22/19 | f) | - | b) | 65925.03 | b) | - | d) | - | b) | 450 |  |  | 1
[8 empty] | c) | CALAFA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [8 empty] | 1
[8 empty] | d) | 3 quarters | d) | - | [12 empty] | 1
|  | Asuncion -Monte Carlo-Del Pilar |  |  | Road Maintenance | 9.93 | MBA | a) | 474102.88 | a) | 01/03/19 | e) | - | a) | 474102.88 | a) | 100% | c) | 100% | a) | 15 | Completed |  | 1
005 | [7 empty] | b) | Crucio | b) | 01/03/19 | f) | - | b) | 474102.88 | b) | - | d) | - | b) | 450 |  |  | 1
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 240274.49 | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
|  | Asuncion -Monte Carlo-Del Pilar |  |  | Road Maintenance | 9.93 | CBRMC | a) | 355524.28 | a) | 01/03/19 | e) | - | a) | 355524.28 | a) | 100% | c) | 100% | a) | 16 | Completed
005 | [7 empty] | b) | Crucio | b) | 03/22/19 | f) | - | b) | 355524.28 | b) | - | d) | - | b) | 450 |  |  | 1
[8 empty] | c) | MAHAYAHAY IFA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [8 empty] | 1
[8 empty] | d) | 3 quarters | d) | - | [12 empty] | 1
|  | Jct. Highway Canatan-Jct. Highway Magatos |  |  | Road Maintenance | 4.85 | MBA | a) | 209808.59 | a) | 01/03/19 | e) | - | a) | 209808.59 | a) | 100% | c) | 100% | a) | 15 | Completed |  | 1
006 | [7 empty] | b) | Crucio | b) | 02/18/19 | f) | - | b) | 209808.59 | b) | - | d) | - | b) | 450 |  |  | 1
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 80652.8 | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
|  | Jct. Highway Canatan-Jct. Highway Magatos |  |  | Road Maintenance | 4.85 | CBRMC | a) | 162458.12 | a) | 01/03/19 | e) | - | a) | 162458.12 | a) | 100% | c) | 100% | a) | 16 | Completed |  | 1
006 | [7 empty] | b) | Crucio | b) | 03/22/19 | f) | - | b) | 162458.12 | b) | - | d) | - | b) | 450 |  |  | 1
[8 empty] | c) | CAMODA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [8 empty] | 1
[8 empty] | d) | 3 quarters | d) | - | [12 empty] | 1
1
|  | Sta. Felomina-San Roque |  |  | Road Maintenance | 7.68 | MBA | a) | 147439.63 | a) | 01/03/19 | e) | - | a) | 147439.63 | a) | 100% | c) | 100% | a) | 15 | Completed
008 | [7 empty] | b) | Crucio | b) | 01/16/19 | f) | - | b) | 147439.63 | b) | - | d) | - | b) | 450 |  |  | 1
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 63806.67 | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
|  | Sta. Felomina-San Roque |  |  | Road Maintenance | 7.68 | CBRMC | a) | 261345.67 | a) | 01/03/19 | e) | - | a) | 261345.67 | a) | 100% | c) | 100% | a) | 16 | Completed |  | 1
008 | [7 empty] | b) | Crucio | b) | 03/25/19 | f) | - | b) | 261345.67 | b) | - | d) | - | b) | 450 |  |  | 1
[8 empty] | c) | STAFFA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [8 empty] | 1
[8 empty] | d) | 3 quarters | d) | - | [12 empty] | 1
|  | Saug-Sonlon-Bdy Longanapan |  |  | Road Maintenance | 11.6 | MBA | a) | 568486.36 | a) | 01/03/19 | e) | - | a) | 568486.36 | a) | 100% | c) | 100% | a) | 15 | Completed |  | 1
010 | [7 empty] | b) | Crucio | b) | 01/16/19 | f) | - | b) | 568486.36 | b) | - | d) | - | b) | 450 |  |  | 1
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 262900.22 | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
|  | Saug-Sonlon-Bdy Longanapan |  |  | Road Maintenance | 11.6 | CBRMC | a) | 185565.56 | a) | 01/03/19 | e) | - | a) | 185565.56 | a) | 100% | c) | 100% | a) | 16 | Completed |  | 1
010 | [7 empty] | b) | Crucio | b) | 03/26/19 | f) | - | b) | 185565.56 | b) | - | d) | - | b) | 450 |  |  | 1
[8 empty] | c) | BINANCIAN LIVESTOCK AFA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [8 empty] | 1
[8 empty] | d) | 3 quarters | d) | - | [12 empty] | 1
|  | Jct. New Visayas-Buan |  |  | Road Maintenance | 2.99 | MBA | a) | 79238.27 | a) | 01/03/19 | e) | - | a) | 79238.27 | a) | 100% | c) | 100% | a) | 15 | Completed |  | 1
011 | [7 empty] | b) | Crucio | b) | 02/18/19 | f) | - | b) | 79238.27 | b) | - | d) | - | b) | 450 |  |  | 1
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 14682.85 | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
|  | Jct. New Visayas-Buan |  |  | Road Maintenance | 2.99 | CBRMC | a) | 101242.01 | a) | 01/03/19 | e) | - | a) | 101242.01 | a) | 100% | c) | 100% | a) | 16 | Completed |  | 1
011 | [7 empty] | b) | Crucio | b) | 03/22/19 | f) | - | b) | 101242.01 | b) | - | d) | - | b) | 450 |  |  | 1
[8 empty] | c) | BUAN IFA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [8 empty] | 1
[8 empty] | d) | 3 quarters | d) | - | [12 empty] | 1
|  | San Vicente - Butay |  |  | Road Maintenance | 7.52 | MBA | a) | 209624.2 | a) | 01/03/19 | e) | - | a) | 209624.2 | a) | 100% | c) | 100% | a) | 15 | Completed |  | 1
013 | [7 empty] | b) | Crucio | b) | 02/18/19 | f) | - | b) | 209624.2 | b) | - | d) | - | b) | 450 |  |  | 1
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 56,080.29 | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
|  | San Vicente - Butay |  |  | Road Maintenance | 7.52 | CBRMC | a) | 227205.88 | a) | 01/03/19 | e) | - | a) | 227205.88 | a) | 100% | c) | 100% | a) | 16 | Completed |  | 1
013 | [7 empty] | b) | Crucio | b) | 03/27/19 | f) | - | b) | 227205.88 | b) | - | d) | - | b) | 450 |  |  | 1
[8 empty] | c) | SVMODA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [8 empty] | 1
[8 empty] | d) | 3 quarters | d) | - | [12 empty] | 1
|  | Jct. Highway Doña Andrea - Capungagan |  |  | Road Maintenance | 8.7 | MBA | a) | 230835.16 | a) | 01/03/19 | e) | - | a) | 230835.16 | a) | 100% | c) | 100% | a) | 15 | Completed |  | 1
014 | [7 empty] | b) | Crucio | b) | 02/18/19 | f) | - | b) | 230835.16 | b) | - | d) | - | b) | 450 |  |  | 1
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 60,629.26 | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
1
|  | Jct. Highway Doña Andrea - Capungagan |  |  | Road Maintenance | 8.7 | CBRMC | a) | 294308.14 | a) | 01/03/19 | e) | - | a) | 294308.14 | a) | 100% | c) | 100% | a) | 16 | Completed
014 | [7 empty] | b) | Crucio | b) | 03/28/19 | f) | - | b) | 294308.14 | b) | - | d) | - | b) | 450 |  |  | 1
[8 empty] | c) | CAPUNGAGAN MPC | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [8 empty] | 1
[8 empty] | d) | 3 quarters | d) | - | [12 empty] | 1
|  | Semong-Palma Gil |  |  | Road Maintenance | 2.73 | MBA | a) | 147289.98 | a) | 01/03/19 | e) | - | a) | 147289.98 | a) | 100% | c) | 100% | a) | 15 | Completed |  | 1
018 | [7 empty] | b) | Crucio | b) | 02/18/19 | f) | - | b) | 147289.98 | b) | - | d) | - | b) | 450 |  |  | 1
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 71745.43 | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
1
|  | Semong-Palma Gil |  |  | Road Maintenance | 2.73 | CBRMC | a) | 49186.05 | a) | 01/03/19 | e) | - | a) | 49186.05 | a) | 100% | c) | 100% | a) | 16 | Completed
018 | [7 empty] | b) | Crucio | b) | 03/22/19 | f) | - | b) | 49186.05 | b) | - | d) | - | b) | 450 |  |  | 1
[8 empty] | c) | PALMA GIL FA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [8 empty] | 1
[8 empty] | d) | 3 quarters | d) | - | [12 empty] | 1
|  | Daligdigon - Dagohoy |  |  | Road Maintenance | 3.34 | MBA | a) | 148835.45 | a) | 01/03/19 | e) | - | a) | 148835.45 | a) | 100% | c) | 100% | a) | - | Completed |  | 1
020 | [7 empty] | b) | Crucio | b) | - | f) | - | b) | 148835.45 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | PEO | c) | - | g) | 2019-12-31 | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
|  | Daligdigon - Dagohoy |  |  | Road Maintenance | 3.34 | CBRMC | a) | 68279.5 | a) | 01/03/19 | e) | - | a) | 68279.5 | a) | 100% | c) | 100% | a) | 16 | Completed |  | 1
020 | [7 empty] | b) | Crucio | b) | 03/22/19 | f) | - | b) | 68279.5 | b) | - | d) | - | b) | 450 |  |  | 1
[8 empty] | c) | PALMA GIL FA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [8 empty] | 1
[8 empty] | d) | 3 quarters | d) | - | [12 empty] | 1
|  | Jct. Sampao-Bdry. Mamacao |  |  | Road Maintenance | 4.98 | MBA | a) | 154200.78 | a) | 01/03/19 | e) | - | a) | 154200.78 | a) | 100% | c) | 100% | a) | 15 | Completed |  | 1
025 | [7 empty] | b) | Crucio | b) | 02/18/19 | f) | - | b) | 154200.78 | b) | - | d) | - | b) | 450 |  |  | 1
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 24,296.87 | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
|  | Jct. Sampao-Bdry. Mamacao |  |  | Road Maintenance | 4.98 | CBRMC | a) | 169521.51 | a) | 01/03/19 | e) | - | a) | 169521.51 | a) | 100% | c) | 100% | a) | 16 | Completed |  | 1
025 | [7 empty] | b) | Crucio | b) | 03/26/19 | f) | - | b) | 169521.51 | b) | - | d) | - | b) | 450 |  |  | 1
[8 empty] | c) | AMS KAPALONG | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [8 empty] | 1
[8 empty] | d) | 3 quarters | d) | - | [12 empty] | 1
|  | Jct. Highway Luna-Mamacao-Narra |  |  | Road Maintenance | 9.17 | MBA | a) | 357957.66 | a) | 01/03/19 | e) | - | a) | 357957.66 | a) | 100% | c) | 100% | a) | 15 | Completed |  | 1
026 | [7 empty] | b) | Crucio | b) | 02/18/19 | f) | - | b) | 357957.66 | b) | - | d) | - | b) | 450 |  |  | 1
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 127,996.16 | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
|  | Jct. Highway Luna-Mamacao-Narra |  |  | Road Maintenance | 9.17 | CBRMC | a) | 313143.91 | a) | 01/03/19 | e) | - | a) | 313143.91 | a) | 100% | c) | 100% | a) | 16 | Completed |  | 1
026 | [7 empty] | b) | Crucio | b) | 03/26/19 | f) | - | b) | 313143.91 | b) | - | d) | - | b) | 450 |  |  | 1
[8 empty] | c) | AMS KAPALONG | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [8 empty] | 1
[8 empty] | d) | 3 quarters | d) | - | [12 empty] | 1
|  | Jct. Gabuyan-Katipunan-Bucana |  |  | Road Maintenance | 5.89 | MBA | a) | 294403.23 | a) | 01/03/19 | e) | - | a) | 294403.23 | a) | 100% | c) | 100% | a) | 15 | Completed |  | 1
027 | [7 empty] | b) | Crucio | b) | 02/18/19 | f) | - | b) | 294403.23 | b) | - | d) | - | b) | 450 |  |  | 1
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 126,179.97 | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
|  | Jct. Gabuyan-Katipunan-Bucana |  |  | Road Maintenance | 5.89 | CBRMC | a) | 129495.6 | a) | 01/03/19 | e) | - | a) | 129495.6 | a) | 100% | c) | 100% | a) | 16 | Completed |  | 1
027 | [7 empty] | b) | Crucio | b) | 03/26/19 | f) | - | b) | 129495.6 | b) | - | d) | - | b) | 450 |  |  | 1
[8 empty] | c) | MANGULIBAS FA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [8 empty] | 1
[8 empty] | d) | 3 quarters | d) | - | [12 empty] | 1
|  | Capungagan-Mabuhay-Pandulian |  |  | Road Maintenance | 5.57 | MBA | a) | 294917.73 | a) | 01/03/19 | e) | - | a) | 294917.73 | a) | 100% | c) | 100% | a) | 15 | Completed |  | 1
028 | [7 empty] | b) | Crucio | b) | 02/18/19 | f) | - | b) | 294917.73 | b) | - | d) | - | b) | 450 |  |  | 1
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
1
|  | Capungagan-Mabuhay-Pandulian |  |  | Road Maintenance | 5.57 | CBRMC | a) | 105950.95 | a) | 01/03/19 | e) | - | a) | 105950.95 | a) | 100% | c) | 100% | a) | 16 | Completed
028 | [7 empty] | b) | Crucio | b) | 03/28/19 | f) | - | b) | 105950.95 | b) | - | d) | - | b) | 450 |  |  | 1
[8 empty] | c) | CAPUNGAGAN MPC | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [8 empty] | 1
[8 empty] | d) | 3 quarters | d) | - | [12 empty] | 1
|  | Florida - New Boholano |  |  | Road Maintenance | 2.54 | MBA | a) | 95863.17 | a) | 01/03/19 | e) | - | a) | 95863.17 | a) | 100% | c) | 100% | a) | 15 | Completed |  | 1
030 | [7 empty] | b) | Crucio | b) | 02/18/19 | f) | - | b) | 95863.17 | b) | - | d) | - | b) | 450 |  |  | 1
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 31,418.99 | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
|  | Florida - New Boholano |  |  | Road Maintenance | 2.54 | CBRMC | a) | 47425.27 | a) | 01/03/19 | e) | - | a) | 47425.27 | a) | 100% | c) | 100% | a) | 16 | Completed |  | 1
030 | [7 empty] | b) | Crucio | b) | 03/28/19 | f) | - | b) | 47425.27 | b) | - | d) | - | b) | 450 |  |  | 1
[8 empty] | c) | SUPRA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [8 empty] | 1
[8 empty] | d) | 3 quarters | d) | - | [12 empty] | 1
|  | Jct. New Boholano - New Loon |  |  | Road Maintenance | 4.77 | MBA | a) | 140549.84 | a) | 01/03/19 | e) | - | a) | 140549.84 | a) | 100% | c) | 100% | a) | 15 | Completed |  | 1
031 | [7 empty] | b) | Crucio | b) | 02/18/19 | f) | - | b) | 140549.84 | b) | - | d) | - | b) | 450 |  |  | 1
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 40,056.38 | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
|  | Jct. New Boholano - New Loon |  |  | Road Maintenance | 4.77 | CBRMC | a) | 169521.51 | a) | 01/03/19 | e) | - | a) | 169521.51 | a) | 100% | c) | 100% | a) | 16 | Completed |  | 1
031 | [7 empty] | b) | Crucio | b) | 03/28/19 | f) | - | b) | 169521.51 | b) | - | d) | - | b) | 450 |  |  | 1
[8 empty] | c) | NEW LOON FA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [8 empty] | 1
[8 empty] | d) | 3 quarters | d) | - | [12 empty] | 1
|  | Florida-Suaon-Jct. Gupitan |  |  | Road Maintenance | 15.57 | MBA | a) | 707038.05 | a) | 01/03/19 | e) | - | a) | 707038.05 | a) | 100% | c) | 100% | a) | 15 | Completed |  | 1
032 | [7 empty] | b) | Crucio | b) | 01/16/19 | f) | - | b) | 707038.05 | b) | - | d) | - | b) | 450 |  |  | 1
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 226,.062.60 | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
|  | Florida-Suaon-Jct. Gupitan |  |  | Road Maintenance | 15.57 | CBRMC | a) | 419094.85 | a) | 01/03/19 | e) | - | a) | 419094.85 | a) | 100% | c) | 100% | a) | 16 | Completed |  | 1
032 | [7 empty] | b) | Crucio | b) | 03/28/19 | f) | - | b) | 419094.85 | b) | - | d) | - | b) | 450 |  |  | 1
[8 empty] | c) | SUPRA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [8 empty] | 1
[8 empty] | d) | 3 quarters | d) | - | [12 empty] | 1
|  | Km. 15, Kipalili-New Loon |  |  | Road Maintenance | 6.93 | MBA | a) | 367659.97 | a) | 01/03/19 | e) | - | a) | 367659.97 | a) | 100% | c) | 100% | a) | 15 | Completed |  | 1
034 | [7 empty] | b) | Crucio | b) | 02/01/19 | f) | - | b) | 367659.97 | b) | - | d) | - | b) | 450 |  |  | 1
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 112,175.78 | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
|  | Km. 15, Kipalili-New Loon |  |  | Road Maintenance | 6.93 | CBRMC | a) | 237801.01 | a) | 01/03/19 | e) | - | a) | 237801.01 | a) | 100% | c) | 100% | a) | 16 | Completed |  | 1
034 | [7 empty] | b) | Crucio | b) | 03/26/19 | f) | - | b) | 237801.01 | b) | - | d) | - | b) | 480 |  |  | 1
[8 empty] | c) | KIPALILI FA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [8 empty] | 1
[8 empty] | d) | 3 quarters | d) | - | [12 empty] | 1
|  | Jct. Suaon-Libuton |  |  | Road Maintenance | 7.26 | MBA | a) | 44015.68 | a) | 01/03/19 | e) | - | a) | 44015.68 | a) | 100% | c) | 100% | a) | 15 | Completed
035 | [7 empty] | b) | Crucio | b) | 01/16/19 | f) | - | b) | 44015.68 | b) | - | d) | - | b) | 450 |  |  | 1
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 24,980.86 | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
|  | Jct. Suaon-Libuton |  |  | Road Maintenance | 7.26 | CBRMC | a) | 91664.91 | a) | 01/03/19 | e) | - | a) | 91664.91 | a) | 100% | c) | 100% | a) | 16 | Completed |  | 1
035 | [7 empty] | b) | Crucio | b) | 03/22/19 | f) | - | b) | 91664.91 | b) | - | d) | - | b) | 480 |  |  | 1
[8 empty] | c) | AALLI | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [8 empty] | 1
[8 empty] | d) | 3 quarters | d) | - | [12 empty] | 1
1
|  | Datu Balong - Pinamuno |  |  | Road Maintenance | 2.74 | MBA | a) | 95458.24 | a) | 01/03/19 | e) | - | a) | 95458.24 | a) | 100% | c) | 100% | a) | 15 | Completed
040 | [7 empty] | b) | Crucio | b) | 03/01/19 | f) | - | b) | 95458.24 | b) | - | d) | - | b) | 450 |  |  | 1
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 12,625.00 | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
|  | Datu Balong - Pinamuno |  |  | Road Maintenance | 2.74 | CBRMC | a) | 63570.57 | a) | 01/03/19 | e) | - | a) | 63570.57 | a) | 100% | c) | 100% | a) | 16 | Completed |  | 1
040 | [7 empty] | b) | Crucio | b) | 03/28/19 | f) | - | b) | 63570.57 | b) | - | d) | - | b) | 480 |  |  | 1
[8 empty] | c) | DATU BALONG FA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [8 empty] | 1
[8 empty] | d) | 3 quarters | d) | - | [12 empty] | 1
|  | Sawata - Mamangan - Pinamuno |  |  | Road Maintenance | 14.48 | MBA | a) | 545390.17 | a) | 01/03/19 | e) | - | a) | 545390.17 | a) | 100% | c) | 100% | a) | 15 | Completed |  | 1
041 | [7 empty] | b) | Crucio | b) | 02/01/19 | f) | - | b) | 545390.17 | b) | - | d) | - | b) | 450 |  |  | 1
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 196,076.60 | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
|  | Sawata - Mamangan - Pinamuno |  |  | Road Maintenance | 14.48 | CBRMC | a) | 508564.54 | a) | 01/03/19 | e) | - | a) | 508564.54 | a) | 100% | c) | 100% | a) | 16 | Completed |  | 1
041 | [7 empty] | b) | Crucio | b) | 03/22/19 | f) | - | b) | 508564.54 | b) | - | d) | - | b) | 480 |  |  | 1
[8 empty] | c) | SAWATA DFA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [8 empty] | 1
[8 empty] | d) | 3 quarters | d) | - | [12 empty] | 1
|  | Igangon - Sawata |  |  | Road Maintenance | 9.66 | MBA | a) | 497447.77 | a) | 01/03/19 | e) | - | a) | 497447.77 | a) | 100% | c) | 100% | a) | 15 | Completed |  | 1
042 | [7 empty] | b) | Crucio | b) | 02/01/19 | f) | - | b) | 497447.77 | b) | - | d) | - | b) | 450 |  |  | 1
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
|  | Igangon - Sawata |  |  | Road Maintenance | 9.66 | CBRMC | a) | 197775.1 | a) | 01/03/19 | e) | - | a) | 197775.1 | a) | 100% | c) | 100% | a) | 16 | Completed |  | 1
042 | [7 empty] | b) | Crucio | b) | 03/22/19 | f) | - | b) | 197775.1 | b) | - | d) | - | b) | 480 |  |  | 1
[8 empty] | c) | SAWATA DFA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [8 empty] | 1
[8 empty] | d) | 3 quarters | d) | - | [12 empty] | 1
|  | New Corella - Sto. Niño - Macgum |  |  | Road Maintenance | 17.11 | MBA | a) | 606294.08 | a) | 01/03/19 | e) | - | a) | 606294.08 | a) | 100% | c) | 100% | a) | 15 | Completed |  | 1
044 | [7 empty] | b) | Crucio | b) | 01/03/19 | f) | - | b) | 606294.08 | b) | - | d) | - | b) | 450 |  |  | 1
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 246,619.77 | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
|  | New Corella - Sto. Niño - Macgum |  |  | Road Maintenance | 17.11 | CBRMC | a) | 308434.97 | a) | 01/03/19 | e) | - | a) | 308434.97 | a) | 100% | c) | 100% | a) | 16 | Completed |  | 1
044 | [7 empty] | b) | Crucio | b) | 03/26/19 | f) | - | b) | 308434.97 | b) | - | d) | - | b) | 480 |  |  | 1
[8 empty] | c) | SAN ISIDRO FA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [8 empty] | 1
[8 empty] | d) | 3 quarters | d) | - | [12 empty] | 1
|  | Tagaytay - Buan |  |  | Road Maintenance | 4.92 | MBA | a) | 173197.37 | a) | 01/03/19 | e) | - | a) | 173197.37 | a) | 100% | c) | 100% | a) | 15 | Completed |  | 1
045 | [7 empty] | b) | Crucio | b) | 03/18/19 | f) | - | b) | 173197.37 | b) | - | d) | - | b) | 450 |  |  | 1
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 26254.58 | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
|  | Tagaytay - Buan |  |  | Road Maintenance | 4.92 | CBRMC | a) | 131850.07 | a) | 01/03/19 | e) | - | a) | 131850.07 | a) | 100% | c) | 100% | a) | 16 | Completed |  | 1
045 | [7 empty] | b) | Crucio | b) | 03/22/19 | f) | - | b) | 131850.07 | b) | - | d) | - | b) | 480 |  |  | 1
[8 empty] | c) | BUAN IFA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [8 empty] | 1
[8 empty] | d) | 3 quarters | d) | - | [12 empty] | 1
|  | limbaan - Sto. Niño |  |  | Road Maintenance | 3.19 | MBA | a) | 153706.77 | a) | 01/03/19 | e) | - | a) | 153706.77 | a) | 100% | c) | 100% | a) | 15 | Completed |  | 1
049 | [7 empty] | b) | Crucio | b) | 03/01/19 | f) | - | b) | 153706.77 | b) | - | d) | - | b) | 450 |  |  | 1
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 32534.49 | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
|  | limbaan - Sto. Niño |  |  | Road Maintenance | 3.19 | CBRMC | a) | 53657.51 | a) | 01/03/19 | e) | - | a) | 53657.51 | a) | 100% | c) | 100% | a) | - | Completed |  | 1
049 | [7 empty] | b) | Crucio | b) | - | f) | - | b) | 53657.51 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | 2019-12-31 | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
|  | Del Pilar - Jct. Silangan |  |  | Road Maintenance | 4.17 | MBA | a) | 187097.4 | a) | 01/03/19 | e) | - | a) | 187097.4 | a) | 100% | c) | 100% | a) | 15 | Completed |  | 1
051 | [7 empty] | b) | Crucio | b) | 03/18/19 | f) | - | b) | 187097.4 | b) | - | d) | - | b) | 450 |  |  | 1
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 94181.74 | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
|  | Del Pilar - Jct. Silangan |  |  | Road Maintenance | 4.17 | CBRMC | a) | 113014.34 | a) | 01/03/19 | e) | - | a) | 113014.34 | a) | 100% | c) | 100% | a) | 16 | Completed |  | 1
051 | [7 empty] | b) | Crucio | b) | 03/26/19 | f) | - | b) | 113014.34 | b) | - | d) | - | b) | 480 |  |  | 1
[8 empty] | c) | DURIAN DACUDAO | c) | 12/31/19 | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | 3 quarters | d) | - | [12 empty] | 1
|  | New Corella - New Sambog - Silangan |  |  | Road Maintenance | 5.1 | MBA | a) | 201994.35 | a) | 01/03/19 | e) | - | a) | 201994.35 | a) | 100% | c) | 100% | a) | 15 | Completed |  | 1
052 | [7 empty] | b) | Crucio | b) | 03/01/19 | f) | - | b) | 201994.35 | b) | - | d) | - | b) | 450 |  |  | 1
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 63402.48 | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
|  | New Corella - New Sambog - Silangan |  |  | Road Maintenance | 5.1 | CBRMC | a) | 131850.07 | a) | 01/03/19 | e) | - | a) | 131850.07 | a) | 100% | c) | 100% | a) | 16 | Completed |  | 1
052 | [7 empty] | b) | Crucio | b) | 03/26/19 | f) | - | b) | 131850.07 | b) | - | d) | - | b) | 480 |  |  | 1
[8 empty] | c) | DURIAN DACUDAO | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [8 empty] | 1
[8 empty] | d) | 3 quarters | d) | - | [12 empty] | 1
|  | Sta. Fe - Del Monte |  |  | Road Maintenance | 3.34 | MBA | a) | 37923.51 | a) | 01/03/19 | e) | - | a) | 37923.51 | a) | 100% | c) | 100% | a) | 15 | Completed |  | 1
056 | [7 empty] | b) | Crucio | b) | 03/18/19 | f) | - | b) | 37923.51 | b) | - | d) | - | b) | 450 |  |  | 1
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 36595.13 | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
|  | Sta. Fe - Del Monte |  |  | Road Maintenance | 3.34 | CBRMC | a) | 70633.96 | a) | 01/03/19 | e) | - | a) | 70633.96 | a) | 100% | c) | 100% | a) | 16 | Completed |  | 1
056 | [7 empty] | b) | Crucio | b) | 03/21/19 | f) | - | b) | 70633.96 | b) | - | d) | - | b) | 480 |  |  | 1
[8 empty] | c) | DEL MONTE CACAO | c) | 12/31/19 | g) | 2019-12-31 | c) | 4,872.18 | [8 empty] | 1
[8 empty] | d) | 3 quarters | d) | - | [12 empty] | 1
|  | New Corella - New Bohol |  |  | Road Maintenance | 11.54 | MBA | a) | 356226.67 | a) | 01/03/19 | e) | - | a) | 356226.67 | a) | 100% | c) | 100% | a) | 15 | Completed
058 | [7 empty] | b) | Crucio | b) | 02/01/19 | f) | - | b) | 356226.67 | b) | - | d) | - | b) | 450 |  |  | 1
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 110,982.71 | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
|  | New Corella - New Bohol |  |  | Road Maintenance | 11.54 | CBRMC | a) | 190711.7 | a) | 01/03/19 | e) | - | a) | 190711.7 | a) | 100% | c) | 100% | a) | 16 | Completed |  | 1
058 | [7 empty] | b) | Crucio | b) | 03/22/19 | f) | - | b) | 190711.7 | b) | - | d) | - | b) | 480 |  |  | 1
[8 empty] | c) | SAN JOSE COCONUT | c) | 12/31/19 | g) | 2019-12-31 | c) | 5,847.18 | [8 empty] | 1
[8 empty] | d) | 3 quarters | d) | - | [12 empty] | 1
1
|  | Jct. Carcor - Prk. 9 Bagsak |  |  | Road Maintenance | 2.5 | MBA | a) | 108618.49 | a) | 01/03/19 | e) | - | a) | 108618.49 | a) | 100% | c. | 100% | a) | 15 | Completed
059 | [7 empty] | b) | Crucio | b) | 03/01/19 | f) | - | b) | 108618.49 | b) | - | d) |  | b) | 480 |  |  | 1
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 79952.88 | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
1
|  | Jct. Carcor - Prk. 9 Bagsak |  |  | Road Maintenance | 2.5 | CBRMC | a) | 42284.76 | a) | 01/03/19 | e) | - | a) | 42284.76 | a) | 100% | c) | 100% | a) | 16 | Completed
059 | [7 empty] | b) | Crucio | b) | 03/22/19 | f) | - | b) | 42284.76 | b) | - | d) | - | b) | 480 |  |  | 1
[8 empty] | c) | CARCOR MOTOR | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [8 empty] | 1
[8 empty] | d) | 3 quarters | d) | - | [12 empty] | 1
|  | Carcor - Jct. Kauswagan |  |  | Road Maintenance | 4.32 | MBA | a) | 264514.71 | a) | 01/03/19 | e) | - | a) | 264514.71 | a) | 100% | c) | 100% | a) | 15 | Completed |  | 1
060 | [7 empty] | b) | Crucio | b) | 03/18/19 | f) | - | b) | 264514.71 | b) | - | d) |  | b) | 450 |  |  | 1
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 80733.11 | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
|  | Carcor - Jct. Kauswagan |  |  | Road Maintenance | 4.32 | CBRMC | a) | 48398.27 | a) | 01/03/19 | e) | - | a) | 48398.27 | a) | 100% | c) | 100% | a) | 16 | Completed
060 | [7 empty] | b) | Crucio | b) | 03/22/19 | f) | - | b) | 48398.27 | b) | - | d) | - | b) | 480 |  |  | 1
[8 empty] | c) | CARCOR MOTOR | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [8 empty] | 1
[8 empty] | d) | 3 quarters | d) | - | [12 empty] | 1
|  | Del Pilar - Prk 9 Bagsak - San Jose |  |  | Road Maintenance | 4.99 | MBA | a) | 170215.76 | a) | 01/03/19 | e) | - | a) | 170215.76 | a) | 100% | c) | 100% | a) | 15 | Completed |  | 1
061 | [7 empty] | b) | Crucio | b) | 03/01/19 | f) | - | b) | 170215.76 | b) | - | d) | - | b) | 450 |  |  | 1
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 87595.63 | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
|  | Del Pilar - Prk 9 Bagsak - San Jose |  |  | Road Maintenance | 4.99 | CBRMC | a) | 223674.22 | a) | 01/03/19 | e) | - | a) | 223674.22 | a) | 100% | c) | 100% | a) | 16 | Completed |  | 1
061 | [7 empty] | b) | Crucio | b) | 03/22/19 | f) | - | b) | 223674.22 | b) | - | d) | - | b) | 480 |  |  | 1
[8 empty] | c) | SAN JOSE COCONUT | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [8 empty] | 1
[8 empty] | d) | 3 quarters | d) | - | [12 empty] | 1
|  | San Juan - New Talisay |  |  | Road Maintenance | 5.13 | MBA | a) | 306261.25 | a) | 01/03/19 | e) | - | a) | 306261.25 | a) | 100% | c) | 100% | a) | 15 | Completed |  | 1
063 | [7 empty] | b) | Crucio | b) | 02/01/19 | f) | - | b) | 306261.25 | b) | - | d) | - | b) | 450 |  |  | 1
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 85123.48 | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
|  | San Juan - New Talisay |  |  | Road Maintenance | 5.13 | CBRMC | a) | 93906.31 | a) | 01/03/19 | e) | - | a) | 93906.31 | a) | 100% | c) | 100% | a) | 16 | Completed
063 | [7 empty] | b) | Crucio | b) | 03/26/19 | f) | - | b) | 93906.31 | b) | - | d) | - | b) | 480 |  |  | 1
[8 empty] | c) | NEW TALISAY IAWA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [8 empty] | 1
[8 empty] | d) | 3 quarters | d) | - | [12 empty] | 1
|  | San Juan - kauswagan - New Cortez |  |  | Road Maintenance | 3.22 | MBA | a) | 187879.04 | a) | 01/03/19 | e) | - | a) | 187879.04 | a) | 100% | c) | 100% | a) | 15 | Completed |  | 1
064 | [7 empty] | b) | Crucio | b) | 03/18/19 | f) | - | b) | 187879.04 | b) | - | d) | - | b) | 450 |  |  | 1
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 3,025.00 | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
|  | San Juan - kauswagan - New Cortez |  |  | Road Maintenance | 3.22 | CBRMC | a) | 63298.26 | a) | 01/03/19 | e) | - | a) | 63298.26 | a) | 100% | c) | 100% | a) | 16 | Completed
064 | [7 empty] | b) | Crucio | b) | 03/22/19 | f) | - | b) | 63298.26 | b) | - | d) | - | b) | 480 |  |  | 1
[8 empty] | c) | SAN JOSE COCONUT | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [8 empty] | 1
[8 empty] | d) | 3 quarters | d) | - | [12 empty] | 1
|  | New Bohol - Jct. El Unido |  |  | Road Maintenance | 2.12 | MBA | a) | 54989.06 | a) | 01/03/19 | e) | - | a) | 54989.06 | a) | 100% | c) | 100% | a) | 15 | Completed
065 | [7 empty] | b) | Crucio | b) | 03/01/19 | f) | - | b) | 54989.06 | b) | - | d) | - | b) | 450 |  |  | 1
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 21021.99 | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
|  | New Bohol - Jct. El Unido |  |  | Road Maintenance | 2.12 | CBRMC | a) | 58861.64 | a) | 01/03/19 | e) | - | a) | 58861.64 | a) | 100% | c) | 100% | a) | 16 | Completed |  | 1
065 | [7 empty] | b) | Crucio | b) | 03/26/19 | f) | - | b) | 58861.64 | b) | - | d) | - | b) | 480 |  |  | 1
[8 empty] | c) | MANDISKAB TRIBAL | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [8 empty] | 1
[8 empty] | d) | 3 quarters | d) | - | [12 empty] | 1
1
|  | New Corella - El unido - Jct. Mesaoy |  |  | Road Maintenance | 8.63 | MBA | a) | 388002.46 | a) | 01/03/19 | e) | - | a) | 388002.46 | a) | 100% | c) | 100% | a) | 15 | Completed
066 | [7 empty] | b) | Crucio | b) | 02/11/19 | f) | - | b) | 388002.46 | b) | - | d) | - | b) | 450 |  |  | 1
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 58142.76 | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
|  | New Corella - El unido - Jct. Mesaoy |  |  | Road Maintenance | 8.63 | CBRMC | a) | 233092.08 | a) | 01/03/19 | e) | - | a) | 233092.08 | a) | 100% | c) | 100% | a) | 16 | Completed |  | 1
066 | [7 empty] | b) | Crucio | b) | 03/26/19 | f) | - | b) | 233092.08 | b) | - | d) | - | b) | 480 |  |  | 1
[8 empty] | c) | MANDISKAB TRIBAL | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [8 empty] | 1
[8 empty] | d) | 3 quarters | d) | - | [12 empty] | 1
|  | Mesaoy - Dasing |  |  | Road Maintenance | 1.39 | MBA | a) | 29749.5 | a) | 01/03/19 | e) | - | a) | 29749.5 | a) | 100% | c) | 100% | a) | 15 | Completed |  | 1
067 | [7 empty] | b) | Crucio | b) | 03/18/19 | f) | - | b) | 29749.5 | b) | - | d) | - | b) | 450 |  |  | 1
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 10000 | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
|  | Mesaoy - Dasing |  |  | Road Maintenance | 1.39 | CBRMC | a) | 54152.71 | a) | 01/03/19 | e) | - | a) | 54152.71 | a) | 100% | c) | 100% | a) | 16 | Completed |  | 1
067 | [7 empty] | b) | Crucio | b) | 03/26/19 | f) | - | b) | 54152.71 | b) | - | d) | - | b) | 480 |  |  | 1
[8 empty] | c) | MANDISKAB TRIBAL | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [8 empty] | 1
[8 empty] | d) | 3 quarters | d) | - | [12 empty] | 1
|  | Jct. San Juan - Jct. Mesaoy |  |  | Road Maintenance | 1.82 | MBA | a) | 106788.95 | a) | 01/03/19 | e) | - | a) | 106788.95 | a) | 100% | c) | 100% | a) | 15 | Completed |  | 1
068 | [7 empty] | b) | Crucio | b) | 03/01/19 | f) | - | b) | 106788.95 | b) | - | d) | - | b) | 450 |  |  | 1
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 17502.68 | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
|  | Jct. San Juan - Jct. Mesaoy |  |  | Road Maintenance | 1.82 | CBRMC | a) | 35180.83 | a) | 01/03/19 | e) | - | a) | 35180.83 | a) | 100% | c) | 100% | a) | 16 | Completed |  | 1
068 | [7 empty] | b) | Crucio | b) | 03/26/19 | f) | - | b) | 35180.83 | b) | - | d) | - | b) | 480 |  |  | 1
[8 empty] | c) | MANDISKAB TRIBAL | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [8 empty] | 1
[8 empty] | d) | 3 quarters | d) | - | [12 empty] | 1
|  | Mesaoy - Jct. Mahayahay |  |  | Road Maintenance | 4.6 | MBA | a) | 146984.46 | a) | 01/03/19 | e) | - | a) | 146984.46 | a) | 100% | c) | 100% | a) | 15 | Completed |  | 1
069 | [7 empty] | b) | Crucio | b) | 03/18/19 | f) | - | b) | 146984.46 | b) | - | d) | - | b) | 450 |  |  | 1
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 7618.27 | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
|  | Mesaoy - Jct. Mahayahay |  |  | Road Maintenance | 4.6 | CBRMC | a) | 160103.65 | a) | 01/03/19 | e) | - | a) | 160103.65 | a) | 100% | c) | 100% | a) | 16 | Completed
069 | [7 empty] | b) | Crucio | b) | 03/22/19 | f) | - | b) | 160103.65 | b) | - | d) | - | b) | 480 |  |  | 1
[8 empty] | c) | MAHAYAHAY IFA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [8 empty] | 1
[8 empty] | d) | 3 quarters | d) | - | [12 empty] | 1
|  | Mesaoy - New bohol |  |  | Road Maintenance | 5.36 | MBA | a) | 165361.13 | a) | 01/03/19 | e) | - | a) | 165361.13 | a) | 100% | c) | 100% | a) | 15 | Completed
070 | [7 empty] | b) | Crucio | b) | 03/01/19 | f) | - | b) | 165361.13 | b) | - | d) | - | b) | 480 |  |  | 1
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 2543.9 | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
|  | Mesaoy - New bohol |  |  | Road Maintenance | 5.36 | CBRMC | a) | 224851.45 | a) | 01/03/19 | e) | - | a) | 224851.45 | a) | 100% | c) | 100% | a) | 16 | Completed
070 | [7 empty] | b) | Crucio | b) | 03/26/19 | f) | - | b) | 224851.45 | b) | - | d) | - | b) | 480 |  |  | 1
[8 empty] | c) | MANDISKAB TRIBAL | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [8 empty] | 1
[8 empty] | d) | 3 quarters | d) | - | [12 empty] | 1
|  | Bdry. Tagum - Baca - New Corella |  |  | Road Maintenance | 13.01 | MBA | a) | 217182.9 | a) | 01/03/19 | e) | - | a) | 217182.9 | a) | 100% | c) | 100% | a) | 15 | Completed |  | 1
071 | [7 empty] | b) | Crucio | b) | 03/18/19 | f) | - | b) | 217182.9 | b) | - | d) | - | b) | 450 |  |  | 1
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 19550 | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
|  | Bdry. Tagum - Baca - New Corella |  |  | Road Maintenance | 13.01 | CBRMC | a) | 214256.36 | a) | 01/03/19 | e) | - | a) | 214256.36 | a) | 100% | c) | 100% | a) | 16 | Completed |  | 1
071 | [7 empty] | b) | Crucio | b) | 03/26/19 | f) | - | b) | 214256.36 | b) | - | d) | - | b) | 480 |  |  | 1
[8 empty] | c) | DURIAN DACUDAO | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [8 empty] | 1
[8 empty] | d) | 3 quarters | d) | - | [12 empty] | 1
|  | Prk. 1, Maunlom - Prk. 6 Maunlom Road |  |  | Road Maintenance | 3.56 | MBA | a) | 150912.87 | a) | 01/03/19 | e) | - | a) | 150912.87 | a) | 100% | c) | 100% | a) | 15 | Completed |  | 1
147 | [7 empty] | b) | Crucio | b) | 03/01/19 | f) | - | b) | 150912.87 | b) | - | d) | - | b) | 450 |  |  | 1
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 23025 | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
|  | Prk. 1, Maunlom - Prk. 6 Maunlom Road |  |  | Road Maintenance | 3.56 | CBRMC | a) | 63973.36 | a) | 01/03/19 | e) | - | a) | 63973.36 | a) | 100% | c) | 100% | a) | 16 | Completed |  | 1
147 | [7 empty] | b) | Crucio | b) | 03/22/19 | f) | - | b) | 63973.36 | b) | - | d) | - | b) | 480 |  |  | 1
[8 empty] | c) | THE BEST VEGETABLE | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [8 empty] | 1
[8 empty] | d) | 3 quarters | d) | - | [12 empty] | 1
1
|  | New Visayas - Binancian |  |  | Road Maintenance | 7.77 | MBA | a) | 14814.34 | a) | 01/03/19 | e) | - | a) | 14814.34 | a) | 100% | c) | 100% | a) | 15 | Completed
149 | [7 empty] | b) | Crucio | b) | 03/18/19 | f) | - | b) | 14814.34 | b) | - | d) | - | b) | 450 |  |  | 1
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 5,000.00 | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
|  | New Visayas - Binancian |  |  | Road Maintenance | 7.77 | CBRMC | a) | 129495.6 | a) | 01/03/19 | e) | - | a) | 129495.6 | a) | 100% | c) | 100% | a) | 16 | Completed |  | 1
149 | [7 empty] | b) | Crucio | b) | 03/22/19 | f) | - | b) | 129495.6 | b) | - | d) | - | b) | 480 |  |  | 1
[8 empty] | c) | BUAN IFA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [8 empty] | 1
[8 empty] | d) | 3 quarters | d) | - | [12 empty] | 1
|  | Datu Balong - Prk. Mamalian |  |  | Road Maintenance | 3.46 | MBA | a) | 117454.89 | a) | 01/03/19 | e) | - | a) | 117454.89 | a) | 100% | c) | 39.37% | a) | 15 | Completed |  | 1
150 | [7 empty] | b) | Crucio | b) | 03/18/19 | f) | - | b) | 117454.89 | b) | - | d) | - | b) | 450 |  |  | 1
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 10115 | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
|  | Datu Balong - Prk. Mamalian |  |  | Road Maintenance | 3.46 | CBRMC | a) | 59264.42 | a) | 01/03/19 | e) | - | a) | 59264.42 | a) | 100% | c) | 100% | a) | 16 | Completed |  | 1
150 | [7 empty] | b) | Crucio | b) | 03/28/19 | f) | - | b) | 59264.42 | b) | - | d) | - | b) | 480 |  |  | 1
[8 empty] | c) | DATU BALONG FA | c) | 12/31/19 | g) | 2019-12-31 | c) | - | [8 empty] | 1
[8 empty] | d) | 3 quarters | d) | - | [12 empty] | 1
A.2 GENERAL FUND CY 2019 |  |  |  |  | Road Maintenance | KM | MBA/CBRMC | a) | 11,618,834.00 | a) | 01/03/19 | e) | - | a) | 11,618,834.00 | a) | 66% | c) | 66% | a) | 42 | See list of Provincial Roads
Road ID |  | 1. Maintenance Of Various Prov'l. Roads and Bridges Dist 2 |  |  |  | 288.26 |  | b) | Matuguinas | b) | 01/03/19 | f) | - | b) | 11,618,834.00 | b) | - | d) | - | b) | 924 |  |  | FS
[8 empty] | c) | PEO/CBRMC | c) | 12/31/19 | g) | - | c) | - | [8 empty] | AC
11DAN | [9 empty] | d) | - | [12 empty] | AC
[8 empty] | d) | 261 days | d) | - | [12 empty] | AC
|  | Cebulano - Mangalcal |  |  | Road Maintenance | 4.17 | MBA | a) | 142161.87 | a) | 01/03/19 | e) | - | a) | 142161.87 | a) | 100% | c) | 100% | a) | 9 | Completed |  | AC
| 073 | [6 empty] | b) | Clar | b) | 2019-01-15 | f) | - | b) | 142161.87 | b) | - | d) | - | b) | 18 |  |  | 2
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 118,609.29 | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | Tubod - basa - Mangalcal |  |  | Road Maintenance | 3.93 | MBA | a) | 156875.9 | a) | 01/03/19 | e) | - | a) | 156875.9 | a) | 100% | c) | 100% | a) | 9 | Completed |  | 2
074 | [7 empty] | b) | Clar | b) | 2019-01-15 | f) | - | b) | 156875.9 | b) | - | d) | - | b) | 18 |  |  | 2
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 143,372.65 | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | Upper Mangalcal - Lower Mangalcal |  |  | Road Maintenance | 2.43 | 0 | a) | 79237.14 | a) | 01/03/19 | e) | - | a) | 79237.14 | a) | 100% | c) | 100% | a) | 9 | Completed |  | 2
078 | [7 empty] | b) | Clar | b) | 2019-01-14 | f) | - | b) | 79237.14 | b) | - | d) | - | b) | 27 |  |  | 2
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 69,430.97 | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | Jct. Highway Carmen - Mangalcal - Tubod |  |  | Road Maintenance | 11.34 | MBA | a) | 463135.67 | a) | 01/03/19 | e) | - | a) | 463135.67 | a) | 100% | c) | 100% | a) | 9 | Completed |  | 2
082 | [7 empty] | b) | Clar | b) | 01/10/19 | f) | - | b) | 463135.67 | b) | - | d) | - | b) | 45 |  |  | 2
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 170,106.43 | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | Jct. Highway Carmen - Mangalcal - Tubod |  |  | Road Maintenance | 11.34 | 0 | a) | 253557.37 | a) | 01/03/19 | e) | - | a) | 253557.37 | a) | 100% | c) | 100% | a) | 10 | Completed |  | 2
082 | [7 empty] | b) | Maligro | b) | 03/25/19 | f) | - | b) | 253557.37 | b) | - | d) | - | b) | 40 |  |  | 2
[8 empty] | c) | TUBOD CENTRO LOWER IRRIGATORS ASSOCIATION | c) | 09/25/19 | g) | 2019-12-31 | c) | - | [8 empty] | 2
[8 empty] | d) | 3 quarters | d) | - | [12 empty] | 2
|  | Jct. Highway Sto. Niño - Kabanlakan - La Paz |  |  | Road Maintenance | 2.13 | MBA | a) | 76067.88 | a) | 01/03/19 | e) | - | a) | 76067.88 | a) | 100% | c) | 100% | a) | 9 | Completed |  | 2
084 | [7 empty] | b) | Clar | b) | 01/10/19 | f) | - | b) | 76067.88 | b) | - | d) | - | b) | 45 |  |  | 2
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 66,477.91 | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | Ising - Sto Niño |  |  | Road Maintenance | 2.07 | 0 | a) | 82413.14 | a) | 01/03/19 | e) | - | a) | 82413.14 | a) | 100% | c) | 100% | a) | 5 | Completed |  | 2
085 | [7 empty] | b) | Clar | b) | 01/17/19 | f) | - | b) | 82413.14 | b) | - | d) | - | b) | 15 |  |  | 2
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 27,093.24 | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | Ising - Sadpodon - Taba - Dila -Dila |  |  | Road Maintenance | 5.68 | MBA | a) | 248941.33 | a) | 01/03/19 | e) | - | a) | 248941.33 | a) | 100% | c) | 100% | a) | 9 | Completed |  | 2
086 | [7 empty] | b) | Clar | b) | 01/12/19 | f) | - | b) | 248941.33 | b) | - | d) | - | b) | 27 |  |  | 2
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 2019-12-31 | c) | 82,329.02 | [8 empty] | 2
[8 empty] | d) | - | d) | - |  |  |  | . | [8 empty] | 2
2
|  | Tuganay - taba |  |  | Road Maintenance | 4.27 | 0 | a) | 291377.9 | a) | 01/03/19 | e) | - | a) | 291377.9 | a) | 70% | c) | 70% | a) | 9 | Completed
087 | [7 empty] | b) | Clar | b) | 01/09/19 | f) | - | b) | 291377.9 | b) | - | d) | - | b) | 27 |  |  | 2
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 12/31/2019 | c) | 238,412.28 | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | Jct. Highway Tuganay - Taba |  |  | Road Maintenance | 4.4 | MBA | a) | 32972.82 | a) | 01/03/19 | e) | - | a) | 32972.82 | a) | 65% | c) | 65% | a) | 9 | Completed |  | 2
088 | [7 empty] | b) | Clar | b) | 01/22/19 | f) | - | b) | 32972.82 | b) | - | d) | - | b) | 18 |  |  | 2
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 12/31/2019 | c) | 22,639.09 | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | Jct. Highway Ising - Magsaysay |  |  | Road Maintenance | 10.84 | 0 | a) | 417818.12 | a) | 01/03/19 | e) | - | a) | 417818.12 | a) | 60% | c) | 60% | a) | 10 | Completed |  | 2
089 | [7 empty] | b) | Clar | b) | 01/22/19 | f) | - | b) | 417818.12 | b) | - | d) | - | b) | 50 |  |  | 2
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 12/31/2019 | c) | 313,488.39 | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | New Camiling - Alejal - Lower Magsaysay |  |  | Road Maintenance | 6.73 | MBA | a) | 240878.08 | a) | 01/03/19 | e) | - | a) | 240878.08 | a) | 80% | c) | 80% | a) | 4 | Completed |  | 2
091 | [7 empty] | b) | Clar | b) | 01/22/19 | f) | - | b) | 240878.08 | b) | - | d) | - | b) | 20 |  |  | 2
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 12/31/2019 | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | Jct. highway Tuganay - Anibongan |  |  | Road Maintenance | 3.66 | 0 | a) | 150684.44 | a) | 01/03/19 | e) | - | a) | 150684.44 | a) | 100% | c) | 100% | a) | 6 | Completed |  | 2
094 | [7 empty] | b) | Clar | b) | 01/22/19 | f) | - | b) | 150684.44 | b) | - | d) | - | b) | 18 |  |  | 2
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 12/31/2019 | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | Anibongan - Guadalupe |  |  | Road Maintenance | 2.48 | MBA | a) | 91325.06 | a) | 01/03/19 | e) | - | a) | 91325.06 | a) | 100% | c) | 100% | a) | 9 | Completed |  | 2
095 | [7 empty] | b) | Clar | b) | 01/23/19 | f) | - | b) | 91325.06 | b) | - | d) | - | b) | 18 |  |  | 2
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 12/31/2019 | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | Tuganay - Anibongan - San Isidro |  |  | Road Maintenance | 7.22 | 0 | a) | 139979.8 | a) | 01/03/19 | e) | - | a) | 139979.8 | a) | 100% | c) | 100% | a) | 9 | Completed |  | 2
096 | [7 empty] | b) | Clar | b) | 01/24/19 | f) | - | b) | 139979.8 | b) | - | d) | - | b) | 36 |  |  | 2
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 12/31/2019 | c) | 1890.37 | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | Jct. Anibongan - Prk. 2, 7, 5, San Isidro |  |  | Road Maintenance | 3.14 | MBA | a) | 104378.03 | a) | 01/03/19 | e) | - | a) | 104378.03 | a) | 100% | c) | 100% | a) | 10 | Completed |  | 2
097 | [7 empty] | b) | Clar | b) | 01/24/19 | f) | - | b) | 104378.03 | b) | - | d) | - | b) | 20 |  |  | 2
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 12/31/2019 | c) | 56,087.50 | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | Anibongan - Salvacion - Cabay-angan |  |  | Road Maintenance | 6.93 | 0 | a) | 415461.61 | a) | 01/03/19 | e) | - | a) | 415461.61 | a) | 100% | c) | 100% | a) | 9 | Completed |  | 2
098 | [7 empty] | b) | Clar | b) | 01/25/19 | f) | - | b) | 415461.61 | b) | - | d) | - | b) | 45 |  |  | 2
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 12/31/2019 | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | Jct. Highway Guadalupe - Bdry. Tagum |  |  | Road Maintenance | 7.9 | MBA | a) | 456131.09 | a) | 01/03/19 | e) | - | a) | 456131.09 | a) | 100% | c) | 100% | a) | 9 | Completed |  | 2
101 | [7 empty] | b) | Clar | b) | 01/25/19 | f) | - | b) | 456131.09 | b) | - | d) | - | b) | 18 |  |  | 2
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 12/31/2019 | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | Jct. Highway Guadalupe - Bdry. Tagum |  |  | Road Maintenance | 7.9 | 0 | a) | 228201.66 | a) | 01/03/19 | e) | - | a) | 228201.66 | a) | 100% | c) | 100% | a) | 8 | Completed |  | 2
101 | [7 empty] | b) | Maligro | b) | 03/25/19 | f) | - | b) | 228201.66 | b) | - | d) | - | b) | 40 |  |  | 2
[8 empty] | c) | LAMPIA PAG-ASA IRRIGATORS ASSOCIATION, INC. | c) | 12/25/19 | g) | 12/31/2019 | c) | - | [8 empty] | 2
[8 empty] | d) | 3 quarters | d) | - | [12 empty] | 2
|  | Poblacion Dujali - Prk. 8 Dujali |  |  | Road Maintenance | 8.2 | MBA | a) | 285600.05 | a) | 01/03/19 | e) | - | a) | 285600.05 | a) | 100% | c) | 100% | a) | 10 | Completed |  | 2
105 | [7 empty] | b) | Clar | b) | 01/28/19 | f) | - | b) | 285600.05 | b) | - | d) | - | b) | 50 |  |  | 2
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 12/31/2019 | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | Dujali - San Isidro |  |  | Road Maintenance | 3 | 0 | a) | 130319.3 | a) | 01/03/19 | e) | - | a) | 130319.3 | a) | 100% | c) | 100% | a) | 8 | Completed |  | 2
107 | [7 empty] | b) | Gamad | b) | 01/28/19 | f) | - | b) | 130319.3 | b) | - | d) | - | b) | 30 |  |  | 2
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 12/31/2019 | c) | 45,943.12 | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | Prk. 5, RJS - Prk. 6 New Casay |  |  | Road Maintenance | 2.73 | MBA | a) | 235277 | a) | 01/03/19 | e) | - | a) | 235277 | a) | 100% | c) | 100% | a) | 2 | Completed |  | 2
109 | [7 empty] | b) | Gamad | b) | 01/28/19 | f) | - | b) | 235277 | b) | - | d) | - | b) | 6 |  |  | 2
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 12/31/2019 | c) | 90,745.35 | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | Prk. 5 - Prk. 1 Pawas Dujali |  |  | Road Maintenance | 2.18 | 0 | a) | 76067.68 | a) | 01/03/19 | e) | - | a) | 76067.68 | a) | 100% | c) | 100% | a) | 10 | Completed |  | 2
112 | [7 empty] | b) | Gamad | b) | 01/18/19 | f) | - | b) | 76067.68 | b) | - | d) | - | b) | 20 |  |  | 2
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 12/31/2019 | c) | 40,112.50 | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | Dujali - Balisong - Magupising |  |  | Road Maintenance | 5.52 | MBA | a) | 260591.93 | a) | 01/03/19 | e) | - | a) | 260591.93 | a) | 100% | c) | 100% | a) | 4 | Completed |  | 2
113 | [7 empty] | b) | Gamad | b) | 01/09/19 | f) | - | b) | 260591.93 | b) | - | d) | - | b) | 8 |  |  | 2
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 12/31/2019 | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | Dujali - Pawas - San Vicente |  |  | Road Maintenance | 4.42 | 0 | a) | 139536.42 | a) | 01/03/19 | e) | - | a) | 139536.42 | a) | 100% | c) | 100% | a) | 10 | Completed |  | 2
117 | [7 empty] | b) | Gamad | b) | 01/22/19 | f) | - | b) | 139536.42 | b) | - | d) | - | b) | 18 |  |  | 2
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 12/31/2019 | c) | 52,133.86 | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | Jct. Salvacion - San Vicente - Cabay-angan |  |  | Road Maintenance | 3.45 | MBA | a) | 247460.9 | a) | 01/03/19 | e) | - | a) | 247460.9 | a) | 100% | c) | 100% | a) | 10 | Completed |  | 2
118 | [7 empty] | b) | Gamad | b) | 01/23/19 | f) | - | b) | 247460.9 | b) | - | d) | - | b) | 18 |  |  | 2
[8 empty] | c) | PEO | c) | 02/31/19 | g) | 12/31/2019 | c) | 151,887.50 | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | Jct. Salvacion - San Vicente - Cabay-angan |  |  | Road Maintenance | 3.45 | 0 | a) | 152134.44 | a) | 01/03/19 | e) | - | a) | 152134.44 | a) | 100% | c) | 100% | a) | 8 | Completed |  | 2
118 | [7 empty] | b) | Gamad | b) | 03/26/19 | f) | - | b) | 152134.44 | b) | - | d) | - | b) | 36 |  |  | 2
[8 empty] | c) | BALISONG SAN VICENTE IRRIGATORS ASSOCIATION | c) | 12/26/19 | g) | 12/31/2019 | c) | [9 empty] | 2
[8 empty] | d) | 3 quarters | d) | - | [10 empty] | Completed |  | 2
|  | Dujali - San Miguel |  |  | Road Maintenance | 3.95 | MBA | a) | 101202.04 | a) | 01/03/19 | e) | - | a) | 101202.04 | a) | 80% | c) | 90% | a) | 11 |  |  | 2
119 | [7 empty] | b) | Gamad | b) | 01/10/19 | f) | - | b) | 101202.04 | b) | - | d) | - | b) | 22 |  |  | 2
[8 empty] | c) | PEO | c) | 12/31/19 | g) | - | c) | 90,350.03 | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | San Miguel - Casig-ang |  |  | Road Maintenance | 2.55 | 0 | a) | 79237.14 | a) | 01/03/19 | e) | - | a) | 79237.14 | a) | 100% | c) | 100% | a) | 10 | Completed |  | 2
122 | [7 empty] | b) | Gamad | b) | 01/24/19 | f) | - | b) | 79237.14 | b) | - | d) | - | b) | 10 |  |  | 2
[8 empty] | c) | BALISONG SAN VICENTE IRRIGATORS ASSOCIATION | c) | 12/31/19 | g) | 12/31/2019 | c) | 40,112.50 | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | Prk. Magsaysay - Lunga-og - Dalisay |  |  | Road Maintenance | 2.81 | MBA | a) | 79762.14 | a) | 01/03/19 | e) | - | a) | 79762.14 | a) | 100% | c) | 100% | a) | 8 | Completed |  | 2
127 | [7 empty] | b) | Gamad | b) | 01/30/19 | f) | - | b) | 79762.14 | b) | - | d) | - | b) | 8 |  |  | 2
[8 empty] | c) | PEO | c) | 12/31/19 | g) | 12/31/2019 | c) | 40,612.50 | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | Prk. Apitong - Upper Balisong - Dalisay |  |  | Road Maintenance | 4.6 | 0 | a) | 137846.03 | a) | 01/03/19 | e) | - | a) | 137846.03 | a) | 100% | c) | 100% | a) | 8 | Completed |  | 2
128 | [7 empty] | b) | Gamad | b) | 01/31/19 | f) | - | b) | 137846.03 | b) | - | d) | - | b) | 8 |  |  | 2
[8 empty] | c) | BALISONG SAN VICENTE IRRIGATORS ASSOCIATION | c) | 12/31/19 | g) | 12/31/2019 | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | Sitio Paradise - Magkakaisa - Esperanza |  |  | Road Maintenance | 1.75 | MBA | a) | 66552.75 | a) | 01/03/19 | e) | - | a) | 66552.75 | a) | 100% | c) | 100% | a) | 8 | Completed |  | 2
129 | [7 empty] | b) | 79762.14 | b) | 01/22/19 | f) | - | b) | 66552.75 | b) | - | d) | - | b) | 8 |  |  | 2
[8 empty] | c) | Gamad | c) | 12/31/19 | g) | 12/31/2019 | c) | 22,246.26 | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | Los Amigos 1 - Esperanza - Los Amigos 2 |  |  | Road Maintenance | 3.59 | 0 | a) | 101202.04 | a) | 01/03/19 | e) | - | a) | 101202.04 | a) | 100% | c) | 100% | a) | 10 | Completed |  | 2
130 | [7 empty] | b) | Gamad | b) | 01/24/19 | f) | - | b) | 101202.04 | b) | - | d) | - | b) | 20 |  |  | 2
[8 empty] | c) | BALISONG SAN VICENTE IRRIGATORS ASSOCIATION | c) | 12/31/19 | g) | 12/31/2019 | c) | 50,837.50 | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | Mugas - Lunga-og |  |  | Road Maintenance | 2.68 | MBA | a) | 66552.75 | a) | 01/03/19 | e) | - | a) | 91,693.64 | a) | 100% | c) | 100% | a) | 6 | Completed |  | 2
132 | [7 empty] | b) | 79762.14 | b) | 01/17/19 | f) | - | b) | 91,693.64 | b) | - | d) | - | b) | 24 |  |  | 2
[8 empty] | c) | Gamad | c) | 12/31/19 | g) | 12/31/2019 | c) | 50,837.50 | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | Pantaron - Mugas |  |  | Road Maintenance | 3.35 | 0 | a) | 101202.04 | a) | 01/03/19 | e) | - | a) | 101202.04 | a) | 100% | c) | 100% | a) | 9 | Completed |  | 2
133 | [7 empty] | b) | Gamad | b) | 01/23/19 | f) | - | b) | 101202.04 | b) | - | d) | - | b) | 18 |  |  | 2
[8 empty] | c) | BALISONG SAN VICENTE IRRIGATORS ASSOCIATION | c) | 12/31/19 | g) | 12/31/2019 | c) | 90,349.93 | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | Sto. Tomas - Bdry. Mamacao |  |  | Road Maintenance | 4.9 | MBA | a) | 110710.44 | a) | 01/03/19 | e) | - | a) | 110710.44 | a) | 100% | c) | 100% | a) | 10 | Completed |  | 2
135 | [7 empty] | b) | 79762.14 | b) | 01/21/19 | f) | - | b) | 110710.44 | b) | - | d) | - | b) | 40 |  |  | 2
[8 empty] | c) | Gamad | c) | 12/31/19 | g) | 12/31/2019 | c) | 50,837.50 | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | Fd. Rd. 3 - San Jose |  |  | Road Maintenance | 4.55 | 0 | a) | 147367.49 | a) | 01/03/19 | e) | - | a) | 147367.49 | a) | 100% | c) | 100% | a) | 10 | Completed |  | 2
136 | [7 empty] | b) | Gamad | b) | 01/25/19 | f) | - | b) | 147367.49 | b) | - | d) | - | b) | 30 |  |  | 2
[8 empty] | c) | BALISONG SAN VICENTE IRRIGATORS ASSOCIATION | c) | 12/31/19 | g) | 12/31/2019 | c) | 56,174.69 | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | Menzi - balagunan - Tulalian |  |  | Road Maintenance | 10.63 | MBA | a) | 520167.79 | a) | 01/03/19 | e) | - | a) | 520167.79 | a) | 100% | c) | 100% | a) | 6 | Completed |  | 2
138 | [7 empty] | b) | 79762.14 | b) | 01/07/19 | f) | - | b) | 520167.79 | b) | - | d) | - | b) | 18 |  |  | 2
[8 empty] | c) | Gamad | c) | 12/31/19 | g) | 12/31/2019 | c) | 204,850.57 | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | Jct. Bdry. Tagum - Talomo |  |  | Road Maintenance | 12.01 | 0 | a) | 407429.19 | a) | 01/03/19 | e) | - | a) | 407429.19 | a) | 100% | c) | 100% | a) | 10 | Completed |  | 2
145 | [7 empty] | b) | Gamad | b) | 01/11/19 | f) | - | b) | 407429.19 | b) | - | d) | - | b) | 50 |  |  | 2
[8 empty] | c) | BALISONG SAN VICENTE IRRIGATORS ASSOCIATION | c) | 12/31/19 | g) | 12/31/2019 | c) | 168,544.84 | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | San Jose - Sitio Mahayahay, Magwawa |  |  | Road Maintenance | 0.84 | MBA | a) | 7919.35 | a) | 01/03/19 | e) | - | a) | 7919.35 | a) | 100% | c) | 100% | a) | 2 | Completed |  | 2
151 | [7 empty] | b) | 79762.14 | b) | 01/16/19 | f) | - | b) | 7919.35 | b) | - | d) | - | b) | 8 |  |  | 2
[8 empty] | c) | Gamad | c) | 12/31/19 | g) | 12/31/2019 | c) | 1,509.27 | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
B. 20% DEVELOPMENT FUND CY 2019 | [23 empty] | FS
[5 empty] | Type | Physical | Mode | PROJECT DATA | [6 empty] | Financial (000) | Physical Accompl;ishment |  |  |  | Employment
|  | Name of Project |  |  | of | Target | of | a.)Project Cost |  | a.)Date A lot. Rel. |  | e.)# of days |  |  | a.) Program | a.) Planned |  | c.) Actual |  | Generated # |  |  | REMRRKS
[5 empty] | Project | (Discrip tion) | Impl. | b.)Project Engineer |  | b.)Date Started |  |  | suspended |  | b.)Allotment | b.) Revised |  | d.) Slippage |  | a.) Persons
[7 empty] | MBA / | c.)Implementor |  | c.)Target Compl. |  | f.) # of days extended |  |  | c.)Disbursement |  |  |  |  | b.) Man-days
[7 empty] | CBRMC |  |  |  | Date | g.)Date Completed
Road ID |  | 1. Rehabilitation Of Various Prov'l. Roads and Bridges Dist. 1 |  |  | Road Rehabilitation | KM | MBA | a) | 41465029 | a) | 01/03/19 | e) | - | a) | 41465029 | a) | - | c) | - | a) | 46 | See list of Provincial Roads |  | FS
[6 empty] | 109.55 |  | b) | Paraguya | b) | 01/03/19 | f) | - | b) | 41465029 | b) | - | d) | - | b) | 920 |  |  | AC
11DAN | [7 empty] | c) | PEO | c) | 12/31/19 | g) | - | c) | - | [8 empty] | AC
[10 empty] | d) | - | [12 empty] | AC
[8 empty] | d) | 261 days | d) | - | [12 empty] | AC
|  | Jct. Highway Canatan - Doña Andrea |  |  | Road Rehabilitation | 4.34 | Admin | a) | 2,000,000.00 | a) | 2019-12-06 | e) | - | a) | 2,000,000.00 | a) | - | c) | - | a) | - | For implementation |  | AC
007 | [7 empty] | b) | MJ / Kinanahan | b) | - | f) | - | b) | 2,000,000.00 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
|  | Pamacaun - Lasang Banate |  |  | Road Rehabilitation | 4.34 | Admin | a) | 2000000 | a) | 2019-06-27 | e) | - | a) | 2000000 | a) | - | c) | - | a) | - | For implementation |  | 1
015 | [7 empty] | b) | Gone | b) | - | f) | - | b) | 2000000 | b) | - | d) | - | b) | - | Waiting for the delivery of geo-grid |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [6 empty] | materials. An approved request letter |  | 1
[8 empty] | d) | - | d) | - | [10 empty] | dated Dec. 3, 2019 for the extension of 50 days from Provincial Administrator Engr. Rabanoz is on file |  | 1
|  | Kapalong - Mabantao - Florida |  |  | Road Rehabilitation | 7.86 | Admin | a) | 1231000 | a) | 2019-01-31 | e) | - | a) | 1231000 | a) | 70.98% | c) | 70.98% | a) | - | Waiting for the availability of the long arm backhoe |  | 1
016 | [7 empty] | b) | Aparece | b) | - | f) | - | b) | 1231000 | b) | - | d) | 0% | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
|  | Jct. Highway Gabuyan - Semong - Dagohoy |  |  | Road Rehabilitation | 6.97 | Admin | a) | 2492000 | a) | 01/03/19 | e) | - | a) | 2492000 | a) | - | c) | - | a) | - | Re-aligned to Impvt of km.9 Sagayen - Sawata Provincial Road Phase II ( AIP 3rd revision CY 2019 / SB no.4, 2019) |  | 1
017 | [7 empty] | b) |  | b) | - | f) | - | b) | 2492000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
|  | Sto. Niño - Palma Gil - Sitio Opao |  |  | Road Rehabilitation | 11.6 | Admin | a) | 1901000 | a) | 2019-06-19 | e) | - | a) | 1901000 | a) | - | c) | - | a) | - | NTP not yet serve to Tagum Builders because they have not yet complied with the construction safety requirement |  | 1
019 | [7 empty] | b) | Lumapat | b) | - | f) | - | b) | 1901000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
|  | Daligdigon - Lumabag |  |  | Road Rehabilitation | 11.6 | Admin | a) | 680000 | a) | 01/03/19 | e) | - | a) | 680000 | a) | - | c) | - | a) | - | Re-aligned to Impvt of km.9 Sagayen - Sawata Provincial Road Phase II ( AIP 3rd revision CY 2019 / SB no.4, 2019) |  | 1
022 | [7 empty] | b) |  | b) | - | f) | - | b) | 680000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
|  | Sto. Niño - Daligdigon - Paiton |  |  | Road Rehabilitation | 11.6 | Admin | a) | 3000000 | a) | 2019-10-03 | e) | - | a) | 3000000 | a) | - | c) | - | a) | - | Temporary suspended, materials for re-PR |  | 1
023 | [7 empty] | b) | Crucio | b) | - | f) | - | b) | 3000000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
|  | Jct. Paiton - Mibolo |  |  | Road Rehabilitation | 23.9 | Admin | a) | 6000000 | a) | 2019-03-25 | e) | - | a) | 6000000 | a) | 21.05% | c) | 21.05% | a) | - | 22% as of Nov. 30, 2019 Temporary suspended because the materials for the box culvert was re-PR |  | 1
024 | [7 empty] | b) | Lumapat | b) | Aug.1, 2019 | f) | - | b) | 6000000 | b) | - | d) | 0% | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
|  | Monte Dujali - Gupitan |  |  | Road Rehabilitation | 4.58 | Admin | a) | 1200000 | a) | 2019-12-06 | e) | - | a) | 1200000 | a) | - | c) | - | a) | - |  |  | 1
037 | [7 empty] | b) | MJ/Kinanahan | b) | - | f) | - | b) | 1200000 | b) | - | d) | - | b) | - | For implementation |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
|  | Jct. Sawata - Bdry. Binasbas |  |  | Road Rehabilitation | 0.46 | Admin | a) | 500000 | a) | 2019-06-19 | e) | - | a) | 500000 | a) | - | c) | - | a) | - |  |  | 1
043 | [7 empty] | b) | MJ/Kinanahan | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - | For implementation |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
|  | New Corella - Saug |  |  | Road Rehabilitation | 12.52 | Admin | a) | 6500000 | a) | 2019-03-12 | e) | - | a) | 6500000 | a) | 29.54% | c) | 29.54% | a) | 19 | Temporary suspended because the equipmenta were pulled out to fast track the implementation of Km. 9 Sagayen- Sawata Provincial Road (CMGP) |  | 1
048 | [7 empty] | b) | MJ/Kinanahan | b) | 03/26/19 | f) | - | b) | 6500000 | b) | - | d) | - | b) | 570 |  |  | 1
[8 empty] | c) | PEO | c) | 12/31/19 | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
|  | Jct. Monte Carlo - Upper Cabaywa - Canatan |  |  | Road Rehabilitation | 4.61 | Admin | a) | 8838000 | a) | 2019-01-31 | e) | - | a) | 8838000 | a) | 89.5% | c) | 89.5% | a) | 19 | On -going 90% accomplished. The target date of completion was Dec. 31, 2019, for process time extension request |  | 1
050 | [7 empty] | b) | Garcia | b) | 03/26/19 | f) | - | b) | 8838000 | b) | - | d) | 0% | b) | 570 |  |  | 1
[8 empty] | c) | PEO | c) | 12/31/19 | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
[5 empty] | Road Rehabilitation |  |  | a. )P 500,000.00 |  | a.) 01/31/19 |  |  |  | a.) 500,000.00 | [9 empty] | 1
|  | Purok 10 Pob. Road, New Corella | [7 empty] | b.) Feb. 16, 2019 |  |  |  | b.) 500,000.00 | [7 empty] | Completed
g.) Feb. 28, 2019
[5 empty] | Road Rehabilitation |  |  | a.)1,815,000.00 |  | a.) 01/31/19 |  |  |  | a.) 1,815,000.00
|  | Purok 7 Pob- Jct. New Sambog | [7 empty] | b.)March 1, 2019 |  |  |  | b.) 1,815,000.00 | [7 empty] | Completed
g.) May 15, 2019
[5 empty] | Road Rehabilitation |  |  | a.) 1,389,000.00 |  | a.) 01/31/19 |  |  |  | a.) 1,389,000.00 | [7 empty] | Completed with a savings of P303,898.08 furtherance and is for implementation
|  | Del Pilar- El Unido Road | [5 empty] | b.) Fabian |  | b.) March 18,2019 |  |  |  | a.) 1,389,000.00
g.) May 8, 2019
|  | Bdry. Tagum - Baca - New Corella |  |  | Road Rehabilitation | 13.01 | Admin | a) | 1419029 | a) | 01/03/19 | e) | - | a) | 1419029 | a) | - | c) | - | a) | - | Re-aligned to Impvt of km.9 Sagayen Sawata Provincial Road Phase II (SB. No. 4 CY 2019)
071 | [7 empty] | b) | Crucio | b) | - | f) | - | b) | 1419029 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
1
SUPPLEMENTAL BUDGET NO 4 CY 2019 / CONTINUING APPROPRIATION
[8 empty] | a.) 7,742,775.95 | [5 empty] | a.) 7,742,775.95 | [7 empty] | Waiting for the delivery of materials
|  | Impvt. of Km. 9 Sagayen - Sawata Provincial Road Phase II | [5 empty] | b.) Kenny | [5 empty] | b.) 7,742,775.95
Road ID |  | 1. Rehabilitation Of Various Prov'l. Roads and Bridges Dist 2 |  |  | Road Rehabilitation | KM | Admin | a) | 46740117 | a) | 01/03/19 | [10 empty] | See list of Provincial Roads
[6 empty] | 115.62 |  | b) | Matuguinas | b) | - | [12 empty] | AC
11DAN | [7 empty] | c) | PEO | c) | - | [12 empty] | AC
[10 empty] | d) | - | [12 empty] | AC
[8 empty] | d) | 261 days | d) | - | [12 empty] | AC
|  | Jct. Highway Sto. Niño - Cebulano |  |  | Road Rehabilitation | 2.09 | Admin | a) | 1045000 | a) | 2019-03-18 | e) | - | a) | 1045000 | a) | 20% | c) | 20% | a) | 11 | On-going |  | AC
072 | [7 empty] | b) | Obar | b) | 2019-05-21 | f) | - | b) | 1045000 | b) | - | d) | - | b) | 55 |  |  | 2
[8 empty] | c) | PEO | c) | 2020-02-02 | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
[5 empty] | Road Rehabilitation |  |  | a.) 515,000.00 |  | a.) 03/12/19 |  |  |  | a.) 515,000.00 | [9 empty] | 2
|  | Jct. Highway -Tubod - Bagong Silang | [5 empty] | b.) Clar |  | b.) March 18, 2019 |  |  |  | b.) 515,000.00 | [7 empty] | Completed
g.) June 15, 2019
|  | Basa - Tubod |  |  | Road Rehabilitation | 1.56 | Admin | a) | 1000000 | a) | 2019-06-19 | e) | - | a) | 1000000 | a) | - | c) | - | a) | -
076 | [7 empty] | b) | Piad | b) | Nov. 11, 2019 | f) | - | b) | 1000000 | b) | - | d) | - | b) | - | On-going |  | 2
[8 empty] | c) | - | c) | 2020-03-09 | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | Tubod - Pilar |  |  | Road Rehabilitation | 1.55 | Admin | a) | 16000000 | a) | 06/19/19 & 12/9/19 | e) | - | a) | 16000000 | a) | - | c) | - | a) | - | On-going |  | 2
077 | [7 empty] | b) | Gamad/Clar | b) | Dec. 18, 2019 | f) | - | b) | 16000000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | Nov. 5, 2020 | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
[5 empty] | Road Rehabilitation |  |  | a.) 390,000.00 |  | a.) 03/12/19 |  |  |  | a.) 390,000.00 | [9 empty] | 2
|  | Cebulano- Luceta | [5 empty] | b.) Clar |  | b.) March 8, 2019 |  |  |  | b.) 390,000.00 | [7 empty] | Completed
g.) June 15, 2019
[5 empty] | Road Rehabilitation |  |  | a.) 295,000.00 |  | a.) 03/12/19 |  |  |  | a.) 295,000.00
|  | Lower Asuncion - Upper Asuncion | [5 empty] | b.) Clar |  | b.) March 18, 2019 |  |  |  | b.) 295,000.00 | [7 empty] | Completed
g.) June 15, 2019
[5 empty] | Road Rehabilitation |  |  | a.) 1,220,000.00 |  | a.) 03/12/19 |  |  |  | a.) 1,220,000.00
|  | Jct. Highway - Sto. Nino - La Paz - San Vicente | [5 empty] | b.)Obar |  | b.) March 18, 2019 |  |  |  | b.) 1,220,000.00 | [7 empty] | Completed
g.) Sept. 30, 2019
|  | Alejal - Alemag |  |  | Road Rehabilitation | 1.79 |  | a) | 970000 | a) | 2019-03-18 | e) | - | a) | 970000 | a) | 100% | c) | 100% | a) | 7 | Completed. Financially completed
092 | [7 empty] | b) | Gamad/Clar | b) | 2019-05-20 | f) | - | b) | 970000 | b) | 100 | d) | 0% | b) | 20 |  |  | 2
[8 empty] | c) | - | c) | 2019-09-12 | g) | Sept. 30, 2019 | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
[5 empty] | Road Rehabilitation |  |  | a.) 640,000.00 |  | a.) 03/12/19 |  |  |  | a.) 640,000.00 | [9 empty] | 2
|  | Mabaus - Cabay -angan | [5 empty] | b.)Clar |  | b.) Maech 18, 2019 |  |  |  | a.) 640,000.00 | [7 empty] | Completed
g.) July 30, 2019
[5 empty] | Road Rehabilitation |  |  | a.) 280,000.00 |  | a.) 03/12/19 |  |  |  | a.) 280,000.00
|  | Mabaus - Salvacion | [5 empty] | b.)Clar |  | b.) March 18, 2019 |  |  |  | a.) 280,000.00
[12 empty] | g.) June 30, 2019 | [9 empty] | Completed
|  | Dalisay - Mabuhay |  |  | Road Rehabilitation | 3.25 | Admin | a) | 1000000 | a) | 2019-05-16 | e) | - | a) | 1000000 | a) | 80% | c) | 80% | a) | 10
102 | [7 empty] | b) | Gamad/Clar | b) | 2019-06-17 | f) |  | b) | 1000000 | b) |  | d) | 0% | b) | 20 | On-going |  | 2
[8 empty] | c) | - | c) | 2/29,2019 | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | Sitio Malaga - Tibulao |  |  | Road Rehabilitation | 3.22 | Admin | a) | 1000000 | a) | 2019-06-25 | e) | - | a) | 1000000 | a) | - | c) | - | a) | - |  |  | 2
103 | [7 empty] | b) | Gamad/Clar | b) | Nov. 11, 2019 | f) | - | b) | 1000000 | b) | - | d) | - | b) | - | On-going |  | 2
[8 empty] | c) | - | c) | Feb. 9, 2020 | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | Dujali - Tanglaw |  |  | Road Rehabilitation | 3.6 | Admin | a) | 2075000 | a) | 2019-10-03 | e) | - | a) | 2075000 | a) | - | c) | - | a) | - |  |  | 2
104 | [7 empty] | b) | Balbastro | b) | Dec. 28, 2019 | f) | - | b) | 2075000 | b) | - | d) | - | b) | - | On-going |  | 2
[8 empty] | c) | - | c) | Apr. 16, 2020 | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | Dujali - New Casay |  |  |  | 3.2 | Admin | a) | 640000 | a) | 2019-05-16 | e) | - | a) | 640000 | a) | 100% | c) | 100% | a) | 10 |  |  | 2
106 | [7 empty] | b) | Gamad/Clar | b) | 2019-06-17 | f) | 40 | b) | 640000 | b) |  | d) | - | b) | 40 | Completed |  | 2
[8 empty] | c) | - | c) |  | g) | 10/15/2019 | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
[5 empty] | Road Rehabilitation |  |  | a.) 450,000.00 |  | a.) 03/12/19 |  |  |  | a.) 450,000.00 | [9 empty] | 2
|  | New Casay - Bugtong Talisay | [5 empty] | b.)Clar |  | b.) March 18, 2019 |  |  |  | a.) 450,000.00 | [7 empty] | Completed
g.)June 30, 2019
|  | Cabay-angan - Esperanza |  |  | Road Rehabilitation | 5.37 | Admin | a) | 1300000 | a) | 2019-05-16 | e) | - | a) | 1300000 | a) | 80% | c) | 80% | a) | 9
110 | [7 empty] | b) | Gamad/Clar | b) | 2019-06-17 | f) | - | b) | 1300000 | b) | - | d) | - | b) | 36 | On- going |  | 2
[8 empty] | c) | PEO | c) | Feb. 29, 2020 | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | [13 empty] | 2
[5 empty] | Road Rehabilitation |  |  | a.)220,000.00 |  | a.) 03/12/19 |  |  |  | a.)220,000.00 |  | a.) 100 % |  | c.)100% | [5 empty] | 2
|  | Purok 6 Cabay-angan - Esti | [5 empty] | b.) Gamad |  | b.) March 18, 2019 |  |  |  | a.)220,000.00 | [7 empty] | Completed
g.) June 30, 2019
[5 empty] | Road Rehabilitation |  |  | a.)250,000.00 |  | a.) March 12, 2019 | [5 empty] | a.) 100 % |  | c.)100%
|  | Dujali - Sitio Pawas | [5 empty] | b.) Gamad |  | b.) March 18, 2019 | [11 empty] | Completed
g.) Jun 30, 2019
[5 empty] | Road Rehabilitation |  |  | a.) 280,000.00 |  | a.) March 12, 2019 | [5 empty] | a.) 100 % |  | c.)100%
|  | Purok 1 to Purok 2 Sitio Pawas | [6 empty] | b.) Gamad | b.) March 18, 2019 | [11 empty] | Completed
g.) Jun 30, 2019
|  | San Miguel - Crossing Kinamayan |  |  | Road Rehabilitation | 2.8 | Admin | a) | 560000 | a) | 2019-06-25 | e) | - | a) | 560000 | a.) 100 % |  | c.)100% |  | a) | -
120 | [7 empty] | b) | Nasol | b) | Sept. 19, 2019 | f) | - | b) | 560000 | b) | - | d) | - | b) | - | Completed |  | 2
[8 empty] | c) | - | c) | - | g) | Nov. 30, 2019 | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | San Miguel -Libertad Provincial Road |  |  | Road Rehabilitation | 6.2 | Admin | a) | 1240000 | a) | 2019-05-29 | e) | - | a) | 1240000 | a) | 59.41% | c) | 59.41% | a) | 9 |  |  | 2
121 | [7 empty] | b) | Gamad | b) | 2019-06-17 | f) |  | b) | 1240000 | b) | - | d) | - | b) | 36 | On-going |  | 2
[8 empty] | c) | - | c) | Feb. 29, 2020 | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | Bacali - Casig-ang - Libertad |  |  | Road Rehabilitation | 4.7 | Admin | a) | 940000 | a) | 2019-06-07 | e) | - | a) | 940000 | a) | 80% | c) | 80% | a) | 9 | On-going |  | 2
123 | [7 empty] | b) | Gamad | b) | 2019-06-27 | f) | 35 | b) | 940000 | b) | - | d) | - | b) | 36 |  |  | 2
[8 empty] | c) | Admin | c) | Feb. 29, 2020 | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | Kinamayan - Moslog - Mahayag |  |  | Road Rehabilitation | 3.23 | Admin | a) | 1000000 | a) | 2019-05-20 | e) | - | a) | 1000000 | a) | 80% | c) | 80% | a) | 10 | On going |  | 2
124 | [7 empty] | b) | Gamad | b) | 2019-06-27 | f) | 29 | b) | 1000000 | b) | - | d) | - | b) | 20 |  |  | 2
[8 empty] | c) | PEO | c) | Feb. 29, 2020 | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | San Miguel - Moslog - Kinamayan |  |  | Road Rehabilitation | 2.9 | Admin | a) | 1000000 | a) | 2019-05-20 | e) | - | a) | 1000000 | a) | 80% | c) | 80% | a) | 6 | On-going |  | 2
125 | [7 empty] | b) | Gamad | b) | 2019-06-27 | f) | 29 | b) | 1000000 | b) | - | d) | - | b) | 24 |  |  | 2
[8 empty] | c) | - | c) | Feb. 29, 2020 | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | Kinamayan - Lunga-og |  |  | Road Rehabilitation | 2.59 | Admin | a) | 520000 | a) | 2019-03-18 | e) | - | a) | 520000 | a) | 100% | c) | 100% | a) | 9 | Completed |  | 2
126 | [7 empty] | b) | Gamad/Clar | b) | 5/202/019 | f) | - | b) | 520000 | b) | - | d) | - | b) | 36 |  |  | 2
[8 empty] | c) | - | c) |  | g) | Sept. 30, 2019 | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | Mugas - Lanatad |  |  | Road Rehabilitation | 1.53 | Admin | a) | 500000 | a) |  | e) | - | a) | 500000 | a) | - | c) | - | a) | - | On-going |  | 2
131 | [7 empty] | b) | Balbastro | b) | 8/5/2019 | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | Feb. 20, 2020 | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | New Katipunan - Pantaron |  |  | Road Rehabilitation | 1.96 | Admin | a) | 395000 | a) | 2019-03-12 | e) | - | a) | 395000 | a) | - | c) | - | a) | - |  |  | 2
134 | [7 empty] | b) | Gamad/Clar | b) | Dec. 27, 2019 | f) | - | b) | 395000 | b) | - | d) | - | b) | - | On-going |  | 2
[8 empty] | c) | - | c) | Feb. 25, 2020 | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | Fd. Rd. 2 - Sto. Tomas - Magwawa |  |  | Road Rehabilitation | 10.21 | Admin | a) | 3575000 | a) | June `19, 2019 | e) | - | a) | 3575000 | a) | 40% | c) | 40% | a) | - |  |  | 2
137 | [7 empty] | b) | Gamad/Clar | b) | Aug. 27, 2019 | f) | - | b) | 3575000 | b) | - | d) | - | b) | - | On-going |  | 2
[8 empty] | c) | - | c) | 2020-01-24 | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
[8 empty] | a.) 540,000.00 |  | a.) March 12, 2019 |  |  |  | a.) 540,000.00 |  | a.)100% |  | c.)100% |  |  |  | Completed
|  | Nafco - Bobongon |  |  | Road Rehabilitation |  |  | b. Gamad |  | b.) march 18, 2019 |  |  |  | b.) 540,000.00
g.) June 30, 2019
2
|  | Jct. Highway - Tanglaw |  |  | Road Rehabilitation | 3.98 | Admin | a) | 1100000 | a) | 2019-05-16 | e) | - | a) | 1100000 | a) | 85% | c) | 85% | a) | 10 | On going
142 | [7 empty] | b) | Gamad/Clar | b) | 2019-06-17 | f) | 29 | b) | 1100000 | b) | - | d) | - | b) | 20 |  |  | 2
[8 empty] | c) | PEO | c) | Feb. 29, 2020 | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | Kimamon - Lunga-og - Talomo |  |  | Road Rehabilitation | 5.99 | Admin | a) | 1800000 | a) | 5/202019 | e) | - | a) | 1800000 | a) | 73.31% | c) | 73.31% | a) | 9 | on -going |  | 2
144 | [7 empty] | b) | Gamad | b) | 2019-06-17 | f) | - | b) | 1800000 | b) | - | d) | - | b) | 6 |  |  | 2
[8 empty] | c) | PEO | c) | Feb. 27, 2020 | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | Bdry. Tagum - Crossing Kinamayan Sto. Tomas |  |  | Road Rehabilitation | 0.75 | Admin | a) | 3700000 | a) | Dec. 6, 2019 | e) | - | a) | 3700000 | a) | - | c) | - | a) | - | On-going |  | 2
146 | [7 empty] | b) | Gamad/Clar | b) | Dec. 27, 2019 | f) | - | b) | 3700000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | 2020-04-25 | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | Prk. Narafil - Prk. Daisy Magupising |  |  | Road Rehabilitation | 19.16 | Admin | a) | 300117 | a) | 2019-06-25 | e) | - | a) | 300117 | a) | 100% | c) | 100% | a) | - | Completed |  | 2
148 | [7 empty] | b) | Gamad/Clar | b) | Sept. 16, 2019 | f) | - | b) | 300117 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | Oct. 18, 2019 | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
2. Various of Local Roads & Drainage Development Project (Provincewide) |  |  |  |  | Road Drainage rehabiliated |  | Admin | a) | 15000000 | [12 empty] | See projects listed below |  | 2
[8 empty] | b) | Paraguya | [14 empty] | AC
[8 empty] | c) | PEO | [14 empty] | AC
[8 empty] | d) | - | [14 empty] | AC
At District 1
|  | Rehab./Impv't. of San Juan-New Talisay Provincial Road with Drainage |  |  | Road Drainage rehabiliated | - | Admin | a) | 1000000 | a) | Feb. 10, 2019 | e) | - | a) | 1000000 | a) | - | c) | 60$ | a) | - | On-going. |  | AC
2.1 | [7 empty] | b) | MJ | b) | - | f) | - | b) | 1000000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | PEO | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| 6 | Repair/Rehab. Of Concrete Road Jct. Suaon-Libuton, Kapalong |  |  | Road Drainage rehabiliated | - | Admin | a) | 1000000 | a) | 2019-07-03 | e) | - | a) | 1000000 | a) | - | c) | - | a) | - | For implementation Waiting for the availability of the backhoe |  | 1
2.2 | [7 empty] | b) | Aparece | b) | - | f) | - | b) | 1000000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| 1 | Impv't. of Cross Drainage along Saug-Sonlon-Bdry. Longanapan |  |  | Road Drainage rehabiliated | - | Admin | a) | 3000000 | a) | Feb. 10, 2019 | e) | - | a) | 3000000 | a) | - | c) | 58% | a) | - | Suspended from Nov. 18, 2019 to Jan 5, 2020.Resume jan. 6, 2020 |  | 1
2.3 | [7 empty] | b) | Bataller | b.) Aug. 1, 2019 | Aug. 1, 2019 | f) | - | b) | 3000000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| 8 | Rehab./Impv't. of Sto. Niño-Palma Gil-Sitio Opao Provincial Road with Drainage |  |  | Road Drainage rehabiliated | - | Admin | a) | 3000000 | a) | 2019-05-29 | e) | - | a) | 3000000 | a) | - | c) | - | a) | - | NTP not yet serve to Tagum Builders because they have not yet complied with the construction safety requirement |  | 1
2.4 | [7 empty] | b) | Lumapat | b) | - | f) | - | b) | 3000000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
|  | Rehab. of Anibongan-Salvacion-Cabay-angan Provincial Road with Drainage |  |  | Road Drainage rehabiliated | - | - | a) | 2000000 | a) | 2019-01-14 | e) | - | a) | 2000000 | a) | 100% | c) | 100% | a) | 1 | Completed |  | 1
2.1 | [7 empty] | b) | Toquero | b) | 2019-05-22 | f) | - | b) | 2000000 | b) | - | d) | - | b) | 4 | Fiancial obligation still on process |  | 2
[8 empty] | c) | PEO | c) | 2019-08-04 | g) | Dec. 31, 2019 | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | Rehab. Of Dujali-Pawas-San Vicente Provincial Road |  |  | Road Drainage rehabiliated | - | - | a) | 1102900 | a) | Aug. 5, 2019 | e) | - | a) | 1102900 | a) | - | c) | - | a) | - | Project title was amended in the 2nd AIP revision deleting drainage. The project amount was reduced from P2,000,000.00 to P1,102,900.00 to fund new projects that was inlcuded in the AIP 3rd revision CY 2019 /SB No. 4 CY 2019 On. going |  | 2
2.2 | [7 empty] | b) | Toquero | b) | - | f) | - | b) | 1102900 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | PEO | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | Rehab./Impv't. of Jct. highway Ising-Magsaysay Provincial Road with Drainage |  |  | Road Drainage rehabiliated | - | - | a) | 1500000 | a) | Jan. 16, 2019 | e) | - | a) | 1500000 | a) | - | c) | - | a) | - | Revised POW for approval - Jan. 7, 2020 Revision was made due to scarcity of boulders changing from stone masonry to concrete masonry |  | 2
2.3 | [7 empty] | b) | Toquero | b) | - | f) | - | b) | 1500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | PEO | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | Rehab./Impv't. of Sto. Tomas-Bdry. Mamacao Provincial Road |  |  | Road Drainage rehabiliated | - | - | a) | 1500000 | a) | 2019-01-14 | e) | - | a) | 1500000 | a) | 100% | c) | 100% | a) | - | Completed Financial obligation on process
2.4 | [7 empty] | b) | Toquero | b) | 2019-05-31 | f) | 60 | b) | 1500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | PEO | c) | 2019-07-15 | g) | Dec. 31, 2019 | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
SUPPLEMENTAL BUDGET NO. 4 CY 2019
a.) Nov. 27, 2019
| 2.5 | Rehab of Local Roads at Dalisay - Manay Road Section, | [19 empty] | Completed
|  | Panabo City | [19 empty] | Financial obligation on process
| 2.6 | Rehab. of Local Roads at Sta. Cruz- jct. Tagpore- Buenavista | [7 empty] | a.) Nov. 27, 2019 | [11 empty] | Completed
|  | Road Section, panabo City | [19 empty] | Financial obligation on process
| 2.7 | Rehab. of Local Roads at Taba - Bucana Road Section | [7 empty] | a.) | Nov. 27, 2019 | [10 empty] | Financial obligation on process
3. Various Water System Development Project (Provincewide) |  |  |  |  | Water System projects | - | Admin | a) | 9750000 | [12 empty] | See projects listed below |  | 2
[8 empty] | b) | Medalla/Imboy | [14 empty] | AC
[8 empty] | c) | PEO | [14 empty] | AC
[8 empty] | d) | - | [14 empty] | AC
3.1 |  | Construction of Water System Projects | [21 empty] | AC
AC
| 6 | Construction of PWS, Bgry. Linao, San Isidro |  |  | Water System Projects | - | Admin | a) | 500000 | a) | 06/19/19 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For implementation |  | AC
3.1.1 | [7 empty] | b) | Aclaracion | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| 6 | Construction of PWS, Brgy. Datu Balong, San Isidro |  |  | Water System Projects | - | Admin | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For declaration of savings because the spring water source is not feasible for development |  | 1
3.1.2 | [7 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| 6 | Construction of PWS, Brgy. Sagayen, San Isidro |  |  | Water System Projects | - | Admin | a) | 500000 | a) | 2019-09-10 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Procurement on process |  | 1
3.1.3 | [7 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| 4 | Construction of PWS, Brgy. Purok 7-A and B, Brgy. Capungagan, kapalong |  |  | Water System Projects | - | Admin | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | The project was funded by OPAPP CY 2018. Fund re-aligned to new project Rehab. of Water System in PEEDO- LPRRC, Pob. New Corella (AIP 2nd revision CY 2019 |  | 1
3.1.4 | [7 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| 4 | Construction of PWS Purok 2, Brgy. Pag-Asa, kapalong |  |  | Water System Projects | - | Admin | a) | 800000 | a) | - | e) | - | a) | 800000 | a) | - | c) | - | a) | - | The project was funded by OPAPP CY 2018. Fund re-aligned and added to Construction of PWS in Brgy. Linosutan, kaputian Dist, IGACOS (AIP 2nd revision CY 2019) |  | 1
3.1.5 | [7 empty] | b) | - | b) | - | f) | - | b) | 800000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
| 11 | Installation of Shallow Tube Wells & Const. of Machinery Shed |  |  | Water System Projects | - | Admin | a) | 1600000 | a) | - | e) | - | a) | 1600000 | a) | - | c) | - | a) | - | POW for review |  | 1
3.1.6 | [7 empty] | b) | - | b) | - | f) | - | b) | 1600000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
|  | Impv't. of Potable Water System, Consolacion, Panabo City |  |  | Water System Projects | - | - | a) | 500000 | a) | 2019-06-28 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Sched of bidding Dec 27, 2019 |  | 1
3.1.7 | [7 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | Impv't. of Potable Water System, Tagbitan-ag, Samal Dist. |  |  | Water System Projects | - | - | a) | 500000 | a) | 2019-06-19 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For implementation |  | 2
3.1.8 | [7 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | Impv't. of Potable Water System, San Antonio, babak, IGCS |  |  | Water System Projects | - | - | a) | 500000 | a) | 2019-06-25 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For implementation |  | 2
3.1.9 | [7 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | Impv't. of Potable Water System, Mambago-A, IGCS |  |  | Water System Projects | - | - | a) | 500000 | a) | Sept. 10, 2019 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | (Amended in the AIP 2nd Revision to change the location from Peñaplata to Samal District) For implementation |  | 2
3.1.10 | [7 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | Construction of PWS, Brgy. Buenavista, Panabo City |  |  | Water System Projects | - | - | a) | 500000 | a) | June 19 ,2019 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For implementation |  | 2
3.1.11 | [7 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | Construction of PWS, Brgy. Brgy. Kiotoy, Panabo City |  |  | Water System Projects | - | Contract | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Waiting for geo-resistivity equipment since the activity is drilling works |  | 2
3.1.12 | [7 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | Construction of PWS, Brgy. Linusotan, Talikud, District, IGCS |  |  | Water System Projects | - | - | a) | 500,000 + 800,000.00 | a) | Oct. 23, 2019 | e) | - | a) | 500,000 + 800,000.00 | a) | - | c) | - | a) | - | (Additional 800,000.00 from Const. of PWS in purok 2, Pag-asa, Kapalong which was funded by OPAPP CY 2018) (amended Sched of bidding Dec 27, 2019 |  | 2
3.1.13 | [7 empty] | b) | - | b) | - | f) | - | b) | 500,000 + 800,000.00 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | Rehab. of PWS, Brgy. San Miguel, Babak, IGCS |  |  | Water System Projects | - |  | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For amendment indicating phase 2 since the project title is the same with stimulus project and same amount. |  | 2
3.1.14 | [7 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | Construction of PWS, Brgy. Cacao, Panabo City |  |  | Water System Projects | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For cancellation. Purchase of Geo-resistivity equipment but procurement still on process |  | 2
3.1.15 | [7 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | Rehabilitation of Potable Water System, Brgy. Pangubatan, kaputian Dist. IGCS |  |  | Water System Projects | - |  | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For allotment June 24, 2019 |  | 2
3.1.16 | [7 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | Conduct of Geo-resistivity/drilling Test of Proposed Site |  |  | Geo-resistivity/drilling test conducted | - | - | a) | 250000 | [12 empty] | See projects listed below |  | 2
3.1 | [7 empty] | b) | - | [14 empty] | AC
[8 empty] | c) | - | [14 empty] | AC
[8 empty] | d) | - | [14 empty] | AC
|  | Construction of PWS, Brgy. Kiotoy, Panabo City |  |  | Geo-resistivity/drilling test conducted | - | - | a) | 62500 | a) | - | e) | - | a) | 62500 | a) | - | c) | - | a) | - | For cancellation due to the purchase of geo-resistivity equipment |  | AC
a. | [7 empty] | b) | - | b) | - | f) | - | b) | 62500 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | Construction of PWS, Brgy. Linosutan, Talikud, IGCS |  |  | Geo-resistivity/drilling test conducted | - | - | a) | 62500 | a) | - | e) | - | a) | 62500 | a) | - | c) | - | a) | - |  |  | 2
b. | [7 empty] | b) | - | b) | - | f) | - | b) | 62500 | b) | - | d) | - | b) | - | For cancellation due to the purchase of geo-resistivity equipment |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | Construction of PWS, Brgy. San Miguel, Samal, IGCS |  |  | Geo-resistivity/drilling test conducted | - | - | a) | 62500 | a) | - | e) | - | a) | 62500 | a) | - | c) | - | a) | - | For cancellation due to the purchase of geo-resistivity equipment |  | 2
c. | [7 empty] | b) | - | b) | - | f) | - | b) | 62500 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | Construction of PWS, Cacao, Panabo City |  |  | Geo-resistivity/drilling test conducted | - | - | a) | 62500 | a) | - | e) | - | a) | 62500 | a) | - | c) | - | a) | -
d. | [7 empty] | b) | - | b) | - | f) | - | b) | 62500 | b) | - | d) | - | b) | - | For cancellation due to the purchase of geo-resistivity equipment |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
4. Various Government Buildings and Facilities Development Project (Provincewide) |  |  |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of recipients | - | Admin | a) | 27000000 | [12 empty] | See projects listed below |  | 2
[8 empty] | b) | Medalla | [14 empty] | AC
[8 empty] | c) | PEO | [14 empty] | AC
[8 empty] | d) | - | [14 empty] | AC
|  | Repair Bay of Disaster Quick Response Equipment @ PEO Compound, Gov't. Center, Mankilam, Tagum City |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of recipients | - | Admin | a) | 1000000 | a) | 2019-01-31 | e) | - | a) | 1000000 | a) | - | c) | 46.28% | a) | - | On-going |  | AC
| 11 | [6 empty] | b) | Azotes | b) | Oct. 16, 2019 | f) | - | b) | 1000000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
|  | Repair/Impv't. of Municipal Triball Hall, New Corella |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of recipients | - | Admin | a) | 1500000 | a) | - | e) | - | a) | 1500000 | a) | - | c) | - | a) | - | For allotment June 24, 2019 |  | 1
| 5 | [6 empty] | b) | - | b) | - | f) | - | b) | 1500000 | b) | - | d) | - | b) | - | PO on process |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
|  | Const. of GYM Bleacher at Suaybaguio Rina, Elem. School |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of recipients | - | Admin | a) | 1000000 | a) | - | e) | - | a) | 1000000 | a) | 100% | c) | 100% | a) | - | Completed |  | 1
| 11 | [6 empty] | b) | Mayang | b) | 6/3/2019 | f) | - | b) | 1000000 | b) | 64 | d) | 0% | b) | - |  |  | 1
[8 empty] | c) | PEO | c) | 8/01/2019 | g) |  | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
|  | Repair of Dacudao Health Center, Dacudao, San Isidro |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of recipients | - | Admin | a) | 1000000 | a) | - | e) | - | a) | 1000000 | a) |  | c) | 93.13% | a) | 5 | On going |  | 1
| 6 | [6 empty] | b) | Aclaracion | b) | - | f) | - | b) | 1000000 | b) | - | d) |  | b) | 110 |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
|  | Const. of Perimeter Fence at Sto. Niño NASECO Integrated School with Tugas Ext., Sto. Niño, Talaingod |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of recipients | - | Admin | a) | 1000000 | a) | - | e) | - | a) | 1000000 | a) | - | c) | - | a) | - | For implementation |  | 1
| 8 | [6 empty] | b) | - | b) | - | f) | - | b) | 1000000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
|  | Const. of Multi-Purpose Hall Center (Cultural Heritage in Ancestral Domain of Ata-Manobo) |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of recipients | - | Admin | a) | 3000000 | a) | - | e) | - | a) | 3000000 | a) | - | c) | - | a) | - | Fund re-aligned to GIDAS projects |  | 1
| 8 | [6 empty] | b) | - | b) | - | f) | - | b) | 3000000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | PEO | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
|  | Const. of IP Women's Multi-{Purpose Bldg.), Cabidiangan, Sto. Niño, Talaingod |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of recipients | - | Admin | a) | 2000000 | a) | 2019-05-15 | e) | - | a) | 2000000 | a) | - | c) | - | a) | - | For re-bidding |  | 1
| 8 | [6 empty] | b) | - | b) | - | f) | - | b) | 2000000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
1
|  | Extension of PAGRO Training Center & Ground Dev't., Gov't. Center, Mankilam, Tagum City |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of recipients | - | Admin | a) | 1000000 | a) | - | e) | - | a) | 1000000 | a) | - | c) | - | a) | - | For allotment- June 24,2019 Abstract on process
| 11 | [6 empty] | b) | - | b) | - | f) | - | b) | 1000000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | PEO | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
|  | Construction of Abilidad Training Center, Gov't. Center, Mankilam, Tagum City |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of recipients | - | Admin | a) | 7000000 | a) | - | e) | - | a) | 7000000 | a) | - | c) | - | a) | - | Fund re-aligned to GIDAS projects |  | 1
| 11 | [6 empty] | b) | - | b) |  | f) | - | b) | 7000000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
|  | Const. of 1 CL Bldg. @ Suawon ES, New Corella |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of recipients | - | Admin | a) | 1000000 | a) | - | e) | - | a) | 1000000 | a) | - | c) | - | a) | - | On-going |  | 1
[8 empty] | b) | - | b) | Nov. 19, 2019 | f) | - | b) | 1000000 | b) |  | d) | - | b) | - |  |  | 1
| 5 | [6 empty] | c) | PEO | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
|  | Const. of Municipal Tribal Hall, San Isidro |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of recipients | - | Admin | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For implementation |  | 1
| 6 | [6 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
|  | Const. of Quail House (PDNSC Ext. Campus), Sto. Niño, Talaingod |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of recipients | - | Admin | a) | 750000 | a) | - | e) | - | a) | 750000 | a) | - | c) | - | a) | - | On-going |  | 1
| 8 | [6 empty] | b) | - | b) | - | f) | - | b) | 750000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | PEO | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
|  | Completion of Perimeter Steel Fence @ Lunga-og E/S, Brgy. Lunga-og, Sto. Tomas |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of recipients | - | Admin | a) | 1630000 | a) | 01/17/19 | e) | - | a) | 1630000 | a) | - | c) | 46.28% | a) | - | On-going |  | 1
[8 empty] | b) | Azotes | b) | - | f) | - | b) | 1630000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | PEO | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
|  | Const. of DDN Hospital Carmen Zone Annex Bldg. Phase 2, |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of recipients | - | Contract | a) | 3620000 | a) | 2019-06-28 | e) | - | a) | 3620000 | a) | - | c) | - | a) | - | For implementation |  | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 3620000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | Digos Constrak Corp/ | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
5. Stimulus Projects for Various Barangays a. 20% Development Fund CY 2019 |  |  |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | Admin | a) | 41500000 | [12 empty] | See projects listed below |  | 2
[8 empty] | b) | Medalla | [14 empty] | AC
[8 empty] | c) | PEO | [14 empty] | AC
[8 empty] | d) | - | [14 empty] | AC
AC
5.1 |  | Rehab. Of FMR at Prk. 1,3,4 & 7, Concepcion, Asuncion |  |  | Road Rehabilitation to cater the needs of brgys. | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Re-aligned to Const. of Children's Playground with Amenities at Pob. New Corella (AIP 3rd Revision CY 2019 / SB No. 4 CY 2019 |  | AC
| 1 | [6 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
5.2 |  | Rehab. Of Multi-Purpose Hall, New Bantayan, Asuncion |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | 35% | a) | - | Fund transferred to LGU on - going c /o Engr. Lilibeth Cuajao |  | 1
| 1 | [6 empty] | b) | - | b) | 2019-11-02 | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
1
NEW CORELLA
5.3 |  | Construction of Multi-Purpose Hall, El Salvador, New Corella |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) | 2019-05-23 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Fund transferred to LGU March 23, 2019 c/o Engr. Dugoldugol |  | AC
[8 empty] | b) | - | b) | 2019-09-16 | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
| 5 | [6 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
5.4 |  | Concreting of Drainage Canal , Pob., New Corella |  |  | Const. of Drainage Canal to cater the needs of brgys. | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Amended to Const. of 2 Storey Multi-Purpose Hall phase 3 (Brgy. Hall),Pob., New Corella (AIP 3rd revision CY 2019 / SB No. 4 CY 2019 |  | 1
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
| 5 | [6 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
5.5 |  | Rehab. Of Multi-Purpose Hall, Cabidianan, New Corella |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) | 02/20/19 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Fund transferred to LGU c/o Engr. Dugoldugol |  | 1
[8 empty] | b) |  | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
| 5 | [6 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
5.6 |  | Const. of Canal Lining, Limbaan, New Corella |  |  | Const. of Drainage Canal to cater the needs of brgys. | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Fund transferred to LGU c/o Engr. Dugoldugol Completed - Nov. 8, 2019 / PCR for submission |  | 1
[8 empty] | b) | - | b) | 2019-09-06 | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
| 5 | [6 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
1
TALAINGOD
5.7 |  | Brgy. Electrification (Centro Gupitan), Gupitan, Talaingod |  |  | Rural Electrification to cater the needs of brgys. | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Re-aligned to other stimulus projects that need additional funds to complete since the amount can not complete the project. Recommended for exact fund that can complete the project. |  | AC
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
| 8 | [6 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
1
TAGUM CITY
5.8 |  | Rehab. of Evacuation Center, Madaum, Tagum City |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | Admin | a) | 500000 | a) | 01/14/19 | e) | - | a) | 500000 | a) | 17.17% | c) | 17.17 | a) | - | On going |  | AC
| 11 | [6 empty] | b) | Juan, Z | b) | Nov. 18, 2019 | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | PEO | c) | Jan. 16, 2019 | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | 60 CD | d) | - | [12 empty] | 1
5.9 |  | Rehab. of Evacuation Center, Magugpo Poblacion, Tagum City |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. |  | Contract | a) | 500000 | a) |  | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Amended in the AIP 3rd revision CY 2019 /SB No. 4 CY 2019 changing the total project cost to P600,000.00 |  | 1
| 11 | [6 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
5.1 |  | Rehab. of Evacuation Center, New Balambam, Tagum City |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. |  | Contract | a) | 500000 | a) | 2019-09-10 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Procurement on process |  | 1
| 11 | [6 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
5.11 |  | Rehab. Of Multi-Purpose Hall, Cuambogan, Tagum City |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. |  | Contract | a) | 500000 | a) | 2019-09-10 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Procurement on process |  | 1
| 11 | [6 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
5.12 |  | Completion of Evacuation Center, Nueva Fuerza, Tagum City |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. |  | Contract | a) | 500000 | a) | 2019-09-10 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Procurement on process |  | 1
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
| 11 | [6 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
5.13 |  | Const. of Water System, San Agustin, Tagum City |  |  | Const. of Water System to cater the needs of brgys. | - | Contract | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Re-aligned to other stimulus projects that need additional funds since there is no deed of donation for the proposed site. |  | 1
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
| 11 | [6 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
5.14 |  | Const. of Brgy. Health Center, Magugpo South, Tagum City |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Amended in the AIP 3rd revision CY 2019 /SB No. 4 CY 2019 changing the total project cost to P1,550,000.00 |  | 1
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
| 11 | [6 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
5.15 |  | Const. of Women Livelihood Center, San Isidro, Tagum City |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) | 2019-05-29 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | On -going |  | 1
[8 empty] | b) | - | b) | Jan. 2, 2020 | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
| 11 | [6 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
5.16 |  | Completion. of Water System , Busaon, Tagum City |  |  | Const. of Water System to cater the needs of brgys. |  | Contract | a) | 500000 | a) | Sept. 10, 2019 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Procurement on process |  | 1
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
| 11 | [6 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
5.17 |  | Rehab. Of Brgy. Health Center, Apokon, Tagum City |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | admin | a) | 500000 | a) | 2019-03-25 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For implementation (The brgy. council agreed not to pursue with the project if it will not be completed and needs additional funds) |  | 1
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
| 11 | [6 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
5.18 |  | Const. of Drainage Canal, Bincungan, Tagum City |  |  | Const. of Drainage Canal to cater the needs of brgys. |  | Contract | a) | 500000 | a) | Sept. 10, 2019 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Procurement on process |  | 1
| 11 | [6 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
5.19 |  | Rehab. of Evacuation Center, Mankilam, Tagum City |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) | 2019-03-25 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For implementation |  | 1
| 11 | [6 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
|  | Rehab. of Evacuation Center, Magugpo North, Tagum City |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. |  | Contract | a) | 500000 | a) | Sept. 10, 2019 | e) | - | a) | 500000 | a) | - | c) | - | a) |  | Procurement on process |  | 1
5.2 | 11 | [6 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
1
SAN ISIDRO
|  | Rehab. Of Multi-Purpose Hall , Sto. Niño, San Isidro |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | Admin | a) | 500000 | a) | 02/20/19 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | POW was revised to increase the cost for windows and approved Dec. 6, 2019 PR on process |  | AC
5.21 | 6 | [6 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
|  | Rehab. Of Water System at Purok Cabang & Mangga , Pinamuno, San Isidro |  |  | Const. of Water System to cater the needs of brgys. |  | Contract | a) | 500000 | a) | Dec. 6, 2019 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Sched. Of bidding Dec. 27, 2019 |  | 1
5.22 | 6 | [6 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
|  | Rehab. Of Water System , Igangon, San Isidro |  |  | Const. of Water System to cater the needs of brgys. | - | - | a) | 500000 | a) | 2019-05-29 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For implementation |  | 1
5.23 | 6 | [6 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - | [12 empty] | 1
1
CARMEN |  |  |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys.
5.1 |  | Const. of Multi-Purpose Hall, La Paz, Carmen |  |  |  | - | - | a) | 500000 | a) | 02/20/19 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Fund transferred to LGU March 28, 2019 |  | AC
[8 empty] | b) | - | b) | Aug. 16, 2019 | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
5.2 |  | Const. of Evacuation Center Ph. 3, Sto. Niño, Carmen |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Amended in the AIP 3rd revision CY 2019/ SB No. 4 CY 2019 changing the location to Purok !-c, Sto. Nino since the previous location was implemented by DPWH |  | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
5.3 |  | Const. of Multi-Purpose Hall, Mangalcal, Carmen |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) | 02/20/19 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Fund transfer to LGU Carmen, 3/28/2019 with check no. 2574953 and OR no. 0118982 |  | 2
[8 empty] | b) | - | b) | Sept. 16, 2019 | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
5.4 |  | Rehab. of Multi-Purpose Hall, Guadalupe, Carmen |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) | 02/20/19 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Fund transferred to LGU March 28, 2019 |  | 2
[8 empty] | b) | - | b) | 8/15/2019 | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | 11/13/2019 | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
5.5 |  | Const. of Multi-Purpose Hall, Mabuhay, Carmen |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) | 02/20/19 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Fund transfer to LGU Carmen, 3/28/2019 with check no. 2574925 and OR no. 0118984 |  | 2
[8 empty] | b) | - | b) | Aug. 16, 2019 | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
5.6 |  | Const. Canal Lining , Mabaus, Carmen |  |  | Const. of Canal Lining to cater the needs of brgys. | - | - | a) | 500000 | a) | 02/20/19 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Fund transferred to LGU March 28, 2019 |  | 2
[8 empty] | b) | - | b) |  | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) |  | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
5.7 |  | Rehab. Of Evacuation Center, Alejal, Carmen |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) | 02/20/19 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Fund transfer to LGU Carmen, 3/28/2019 with check no.2574949 and OR no. 0118991 |  | 2
[8 empty] | b) | - | b) | Aug. 16, 2019 | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
5.8 |  | Compl. Of Evacuation Center, Tuganay, Carmen |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) | 02/20/19 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Fund transfer to LGU Carmen, 3/28/2019 with check no. 2574947 and OR no. 0118995 |  | 2
[8 empty] | b) | - | b) | Aug. 16, 2019 | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
5.9 |  | Const. of Multi-Purpose hall, Ising, Carmen |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) | 02/20/19 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Fund transferred to LGU March 28, 2019 |  | 2
[8 empty] | b) | - | b) |  | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
5.1 |  | Rehab. of Multi-Purpose hall, Cebulano, Carmen |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) | 02/20/19 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Fund transferred to LGU March 28, 2019 |  | 2
[8 empty] | b) | - | b) | Aug. 16, 2019 | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
2
PANABO CITY
5.11 |  | Rehab. Of Multi-Purpose Hall, Kasilak, Panabo City |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Amended in AIP 3rd revison CY 2019/ SB No. 4 CY 2019 increasing the project cost to P650,000.00 |  | AC
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
5.12 |  | Rehab. Of Multi-Purpose Hall, New Malitbog, Panabo City |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Amended in AIP 3rd revsion CY 2019 to change the project to Construction of Potable Water System because the original project will be funded by LGU, Panabo City (Brgy. resolution no. 25 series of 2019 dated Aug. 13, 2019 submitted) |  | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
2
[8 empty] | d) | - | d) | -
5.13 |  | Desilting of Canal, New Pandan, Panabo City |  |  | Const. of Drianage Canal to cater the needs of brgys. | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For re inspection to add length for desilting c/o Engr. Canillada Plan prepared can not consume the allocated amount of P500,000.00 for desilting works. |  | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
5.14 |  | Const. Of Multi-Purpose Hall, Waterfall, Panabo City |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For allotment. Sept. 27, 2019 |  | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
5.15 |  | Concreting of Brgy. Road @ Prk. Guyabano, Cagangohan, Panabo City |  |  | Road Concreting to cater the needs of brgys. | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Amended in AIP 3rd revision to change the project to Rehab of Evacuation Center because the original project has no deed of donation.(Brgy. resolution no 41 series of 2019 dated Aug. 16, 2019 submitted |  | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
2
[8 empty] | d) | - | d) | -
5.16 |  | Rehab. Of Evacuation Center, J.P. Laurel, Panabo City |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) | Oct. 23, 2019 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Sched. Of bidding Dec. 27, 2019 |  | 2
[8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - | [12 empty] | 2
5.17 |  | Const. Of Multi-Purpose Hall, Buenavista, Panabo City |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) | Oct. 18, 2019 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Sched. Of bidding Dec. 27, 2019 |  | 2
[8 empty] | b) | - | b) | - | f) |  | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) |  | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - |  | - | [10 empty] | 2
5.18 |  | Rehab. Of Multi-Purpose Hall, San Francisco, Panabo City |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) | Oct. 18, 2019 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Sched. Of bidding Dec. 27, 2019 |  | 2
[8 empty] | b) | - | b) | - | f) |  | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - |  | - | [10 empty] | 2
5.19 |  | Rehab. Of Evacuation Center, Datu Abdul Dadia, Panabo City |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) | Oct. 18, 2019 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Sched. Of bidding Dec. 27, 2019 |  | 2
[8 empty] | b) | - | b) | - | f) |  | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - |  | - | [10 empty] | 2
5.2 |  | Impv't./Beautification of Brgy. Grounds, Quezon, Panabo City |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Re aligned to other stimulus projects that needs additional funding |  | 2
[8 empty] | b) | - | b) | - | f) |  | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - |  | - | [10 empty] | 2
5.21 |  | Const. of Women Livelihood Center Bldg. , Gredu, Panabo City |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) | 2019-03-28 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Fund transfer to LGU - 3/28/2019 with check no. 2574926 and OR no. 0166517 - March 28, 2019 |  | 2
[8 empty] | b) | - | b) | - | f) |  | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - |  | - | [10 empty] | 2
5.23 |  | Const. of Canal Lining at Purok 5, Salvacion, Panabo City |  |  | Const. of Drainage Canal to cater the needs of brgys. | - | - | a) | 500000 | a) | Oct. 18, 2019 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Procurement on process |  | 2
[8 empty] | b) | - | b) | - | f) |  | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - |  | - | [10 empty] | 2
5.24 |  | Rehab. Of Health Center, New Visayas, Panabo City |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Re aligned to other stimulus projects that needs additional funding |  | 2
[8 empty] | b) | - | b) | - | f) |  | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - |  | - | [10 empty] | 2
5.25 |  | Rehab. Of Multi-Purpose Hall, Little Panay, Panabo City |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For allotment Dec. 11, 2019 |  | 2
[8 empty] | b) | - | b) | - | f) |  | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - |  | - | [10 empty] | 2
5.26 |  | Rehab. Of Brgy. Health Center, Dalisay, Panabo City |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For allotment Dec. 4, 2019 |  | 2
[8 empty] | b) | - | b) | - | f) |  | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - |  | - | [10 empty] | 2
5.27 |  | Const. of Multi-Purpose Hall, Southern Davao, Panabo City |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For allotment Dec. 3, 2019 |  | 2
[8 empty] | b) | - | b) | - | f) |  | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - |  | - | [10 empty] | 2
2
STO. TOMAS | [12 empty] | -
5.28 |  | Rehab. Of Evacuation Center, Casig-ang, Sto. Tomas |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) | - | e) |  | a) | 500000 | a) | - | c) | - | a) | - | POW preparation on-going c/o Engr. Uy |  | AC
[8 empty] | b) | - | b) | - | f) |  | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - |  | - | [10 empty] | 2
5.29 |  | Const. of Brgy. Tibal-og Health Center, Tibal-og, Sto. Tomas |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | POW preparation completed amounting t oP1,550,000.00. To request for additional funds in order to complete the project to be functional |  | 2
[8 empty] | b) | - | b) | - | f) |  | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - |  | - | [10 empty] | 2
5.3 |  | Compl.of Brgy. Public Market, La Libertad, Sto. Tomas |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) |  | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Fund transfer to LGU - 6/26/219 with check no. 2575131 and OR no. 0557457 Completed/ PCR for submission by LGU |  | 2
[8 empty] | b) | - | b) | - | f) | Nov. 30, 2019 | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - |  | - | [10 empty] | 2
5.31 |  | Rehab. Of Evacuation Center, New Visayas, Sto. Tomas |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) |  | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Fund transfer to LGU - 6/26/219 with check no. 2575132 and OR no. 0557455 For implementation |  | 2
[8 empty] | b) | - | b) | - | f) |  | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - |  | - | [10 empty] | 2
5.32 |  | Rehab. Of Multi-Purpose Hall, San Vicente, Sto. Tomas |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Fund transferred to LGU July 5, 2019 On -going |  | 2
[8 empty] | b) | - | b) | - | f) |  | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - |  | - | [10 empty] | 2
5.33 |  | Rehab. Of Multi-Purpose Hall, Salvacion, Sto. Tomas |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Amended in AIP 3rd revision CY 2019 /SB No. 4 CY 2019increasing the project cost to P1,000,000.00 |  | 2
[8 empty] | b) | - | b) | - | f) |  | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - |  | - | [10 empty] | 2
5.34 |  | Rehab. Of Multi-Purpose Hall, Pantaron, Sto. Tomas |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) |  | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Amended in AIP 3rd revision CY 2019 / SB No. 4 CY 2019 increasing the project cost to P550,000.00 |  | 2
[8 empty] | b) | - | b) | - | f) |  | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - |  | - | [10 empty] | 2
5.35 |  | Rehab. Of Multi-Purpose Hall, Magwawa, Sto. Tomas |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | Contract | a) | 500000 | a) | June 19 2019 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Procurement on process |  | 2
[8 empty] | b) | - | b) | - | f) |  | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - |  | - | [10 empty] | 2
5.36 |  | Compl. Of Multi-Purpose Hall, San Jose, Sto. Tomas |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) |  | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Amended in AIP 3rd revision CY 2019 / SB No. 4 CY 2019 increasing the project cost to P600,000.00 |  | 2
[8 empty] | b) | - | b) | - | f) |  | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - |  | - | [10 empty] | 2
5.37 |  | Const. of Evacuation Center, Bobongon, Sto. Tomas |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Re aligned to other stimulus projects that needs additional funding |  | 2
[8 empty] | b) | - | b) | - | f) |  | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - |  | - | [10 empty] | 2
5.38 |  | Rehab. Of Brgy. Road, Lunga-og, Sto. Tomas |  |  | Road Rehabilitation to cater the needs of brgys. | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Amended in AIP 3rd revision CY 2019 / SB No. 4 CY 2019 increasing the project cost to P600,000.00 |  | 2
[8 empty] | b) | - | b) | - | f) |  | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - |  | - | [10 empty] | 2
5.39 |  | Rehab. Of Multi-Purpose Hall, New Katipunan, Sto. Tomas |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | Contract | a) | 500000 | a) | 2019-06-07 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Procurement on process |  | 2
[8 empty] | b) | - | b) | - | f) |  | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - |  | - | [10 empty] | 2
5.4 |  | Rehab. Of Multi-Purpose Hall, San Miguel, Sto. Tomas |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | Contract | a) | 500000 | a) | 2019-06-07 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Procurement on process |  | 2
[8 empty] | b) | - | b) | - | f) |  | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - |  | - | [10 empty] | 2
5.41 |  | Rehab. Of Multi-Purpose Hall, Talomo, Sto. Tomas |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Fund transfer to LGU - 6/26/2019 with check no. 2575130 and OR no. 0557456 For implementation |  | 2
[8 empty] | b) | - | b) | - | f) |  | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - |  | - | [10 empty] | 2
IGCS | [12 empty] | - | [10 empty] | 2
5.42 |  | Rehab. Of Health Center, Aumbay, IGCS |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) | Feb. 28, 2019 | e) |  | a) | 500000 | a) |  | c) | 48.32% | a) | 3 | Completed Financial obligation on process |  | AC
[8 empty] | b) | Pacquiao | b) | 7/10/2019 | f) |  | b) | 500000 | b) | - | d) |  | b) | 15 |  |  | 2
[8 empty] | c) | Admin | c) | 10/7/2019 | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | 90 CD | d) | - |  | - | [10 empty] | 2
5.43 |  | Concreting of Brgy. Road From Prk. 3 to Prk. 5, Catagman, IGCS |  |  | Road Concreting to cater the needs of brgys. | - | Contract | a) | 500000 | a) | Jan. 14, 2019 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For implementation |  | 2
[8 empty] | b) | - | b) | - | f) |  | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - |  | - | [10 empty] | 2
5.44 |  | Rehab. Of Multi-Purpose Hall, San Jose, IGCS |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | Admin | a) | 500000 | a) | 2019-03-25 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | On- going |  | 2
[8 empty] | b) | Pacquiao | b) | Jan. 2, 2019 | f) |  | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - |  | - | [10 empty] | 2
5.45 |  | Elctrification at Sitio Trinidad, Bandera, IGCS |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) | 2019-03-25 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Procurement on process |  | 2
[8 empty] | b) | - | b) | - | f) |  | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - |  | - | [10 empty] | 2
5.46 |  | Rehab. Of Brgy. Health Center, Mambago-A, IGCS |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) | Feb. 28, 2019 | e) | - | a) | 500000 | a) |  | c) | 75.61% | a) | 3 | Completed Financial obligation on process |  | 2
[8 empty] | b) | Ganaba | b) | 07/2019 | f) |  | b) | 500000 | b) |  | d) |  | b) | 15 |  |  | 2
[8 empty] | c) | Admin | c) | 8/23/2019 | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | 45 CD | d) | - |  | - | [10 empty] | 2
5.47 |  | Rehab. Of Multi-Purpose Hall, Del Monte, IGCS |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | Admin | a) | 500000 | a) | 2019-05-29 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Pending/ activity undertaken by DPWH |  | 2
[8 empty] | b) | - | b) | - | f) |  | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - |  | - | [10 empty] | 2
5.48 |  | Rehab. Of Multi-Purpose Hall, Aundanao, IGCS |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | Admin | a) | 500000 | a) | 2019-03-18 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | On -going |  | 2
[8 empty] | b) | Porras | b) | Nov. 18, 2019 | f) |  | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - |  | - | [10 empty] | 2
5.49 |  | Electrification at Upper Purok Rosal, Tagbaobo, IGCS |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Procurement on process. No Abastract |  | 2
[8 empty] | b) | - | b) | - | f) |  | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - |  | - | [10 empty] | 2
5.5 |  | Const. Of Multi-Purpose Hall, Mambago-B, IGCS |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For implementation |  | 2
[8 empty] | b) | Roque | b) | - | f) |  | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - |  | - | [10 empty] | 2
5.51 |  | Const. Of Multi-Purpose Hall, San Antonio, IGCS |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) | 2019-06-19 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For implementation |  | 2
[8 empty] | b) | - | b) | - | f) |  | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - |  | - | [10 empty] | 2
5.52 |  | Concreting of Brgy. Road from Prk. 1 to Prk. 2, Villarica, ICGS |  |  | Road Concreting to cater the needs of brgys. | - | Contract | a) | 500000 | a) | Jan. 14, 2019 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For implementation |  | 2
[8 empty] | b) | - | b) | - | f) |  | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - |  | - | [10 empty] | 2
5.53 |  | Rehab. Of Water System Intake Box and Pipeline, Pangubatan, IGCS |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Plan and Pow completed. Waiting of deed of donation |  | 2
[8 empty] | b) | - | b) | - | f) |  | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - |  | - | [10 empty] | 2
5.54 |  | Const. Of Multi-Purpose Hall, Cogon (Talicud), IGCS |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Procurement on process. For rebidding Dec. 12, 2019 |  | 2
[8 empty] | b) | - | b) | - | f) |  | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - |  | - | [10 empty] | 2
5.55 |  | Installation of Pipelines, Libertad, IGCS |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) | 2019-03-25 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For implementation |  | 2
[8 empty] | b) | - | b) | - | f) |  | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - |  | - | [10 empty] | 2
5.56 |  | Rehab. Of Evacuation Center, Libuak, IGCS |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) | 2019-05-29 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For implementation |  | 2
[8 empty] | b) | - | b) | - | f) |  | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - |  | - | [10 empty] | 2
5.57 |  | Const. of Water System Project, Pob. Kaputian, IGCS |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | for Allotment |  | 2
[8 empty] | b) | - | b) | - | f) |  | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - |  | - | [10 empty] | 2
[13 empty] | - | [10 empty] | 2
5.58 |  | Rehab. Of Potable Water System, San Isidro, Babak, IGCS |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) | 2019-06-19 | e) |  | a) | 500000 | a) | - | c) | - | a) | - | For implementation
[8 empty] | b) | - | b) | - | f) |  | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - |  | - | [10 empty] | 2
5.59 |  | Rehab. Of Potable Water System, San Miguel, IGCS |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) | Feb. 28, 2019 | e) |  | a) | 500000 | a) | - | c) | - | a) | - | For implementation |  | 2
[8 empty] | b) | - | b) | - | f) |  | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - |  | - | [10 empty] | 2
5.6 |  | Const. of Water System Ph.II, San Remegio, IGCS |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) | 2019-05-29 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For implementation |  | 2
[8 empty] | b) | Porras | b) | - | f) |  | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | Admin | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - |  | - | [10 empty] | 2
5.61 |  | Electrificatio at Prk. 1,3,4, 6,7 & 8, Licup, IGCS |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) | 02/20/19 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Procurement of materials on process |  | 2
[8 empty] | b) | - | b) | - | f) |  | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - |  | - | [10 empty] | 2
6. Rural Electrification Project (Provincewide) |  |  |  |  | Powerlines/posts installed & rehabilitated | - | - | a) | 5000000 |  |  |  | - | [8 empty] | See projects listed below |  | 2
[8 empty] | b) | Kim Pao Lu | [14 empty] | AC
[8 empty] | c) | - | [14 empty] | AC
[8 empty] | d) | - | [14 empty] | AC
|  | Rural Electrification , Del Monte, New Corella |  |  | Powerlines/posts installed & rehabilitated | - | - | a) | 3000000 | a) | - | e) |  | a) | 3000000 | a) | - | c) | - | a) | - | For implementation |  | AC
[8 empty] | b) | P.Bueno | b) | - | f) |  | b) | 3000000 | b) | - | d) | - | b) | - |  |  | 1
6.1 | 5 | [6 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - |  | - | [10 empty] | 1
|  | Rural Electrification at St. Bundok, San Roque, New Corella |  |  | Powerlines/posts installed & rehabilitated | - | - | a) | 1000000 | a) | - | e) | - | a) | 1000000 | a) | - | c) | - | a) | - | For allotment- Dec. 3, 2019 |  | 1
[8 empty] | b) | P.Bueno | b) | - | f) |  | b) | 1000000 | b) | - | d) | - | b) | - |  |  | 1
6.2 | 5 | [6 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - |  | - | [10 empty] | 1
|  | Rural Electrification at Pob. Kaputian, (St. Sagrada) IGCS |  |  | Powerlines/posts installed & rehabilitated | - | - | a) | 1000000 | a) | - | e) | - | a) | 1000000 | a) | - | c) | - | a) | - | Procurement on process |  | 1
[8 empty] | b) | P.Bueno | b) | - | f) |  | b) | 1000000 | b) | - | d) | - | b) | - |  |  | 2
6.3 | 10 | [6 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - |  | - | [10 empty] | 2
[13 empty] | - | [10 empty] | 2
C. 5% CALAMITY FUND CY 2019
1 |  | Desiltation/Excavation of rivers and creeks |  |  | creeks and canals deislted | - | - | a) | 3000000 | [12 empty] | See project listed below |  | FS
[8 empty] | b) | Paraguya | [14 empty] | AC
[8 empty] | c) | PEO | [14 empty] | AC
[8 empty] | d) | - | [14 empty] | AC
|  | 1.1 | Desilting of Limbaan Creek, New Corella |  | creeks and canals deislted | - | - | a) | 2000000 | a) | - | e) |  | a) | 2000000 | a) | - | c) | - | a) | - | POW preparation on going |  | AC
| 5 | [6 empty] | b) | - | b) | - | f) |  | b) | 2000000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - |  | - | [10 empty] | 1
[13 empty] | - | [10 empty] | 1
a. |  | Desiltation of Mactan River Ph. II |  |  | creeks and canals deislted | - | - | a) | 500000 | a) | - | e) |  | a) | 500000 | a) | - | c) | - | a) | - | on-going
[8 empty] | b) | Toquero | b) | 7/29/2019 | f) |  | b) | 500000 | b) | - | d) | - | b) | - | TIME EXTENSION PROCESS
[8 empty] | c) | Admin | c) | 9/27/2019 | g) | - | c) | -
[8 empty] | d) | 60 C.D | d) | - |  | -
2 |  | Revitment of Dike and Slope Proection |  |  | Protection dikes/slope protection | - | - | a) | 3000000 |  |  |  | - | [8 empty] | See projects listed below
[8 empty] | b) | - | [14 empty] | AC
[8 empty] | c) | - | [14 empty] | AC
[8 empty] | d) | - | [14 empty] | AC
|  | 2.1 | Slope Protection Along Kapalong-Mabantao, Florida |  | creeks and canals deislted | - | - | a) | 1000000 | a) | - | e) |  | a) | 1000000 | a) | - | c) | - | a) | - | For cancellation funded to DPWH. Budget Transferred to |  | AC
| 4 | [6 empty] | b) | - | b) | - | f) |  | b) | 1000000 | b) | - | d) | - | b) | - | 5% Calamity Fund- Rehab and Recovery |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - |  | - | [10 empty] | 1
b. |  | Repair/Rehab. Of Upper Tuganay Dike |  |  | creeks and canals deislted | - | - | a) | 1000000 | a) | - | e) | - | a) | 1000000 | a) | - | c) | - | a) | - | ON-GOING |  | 1
[8 empty] | b) | Toquero | b) | 8/19/2019 | f) |  | b) | 1000000 | b) | - | d) |  | b) | - | TIME EXTENSION PROCESS |  | 2
[8 empty] | c) | Admin | c) | 9/29/2019 | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | 59 C.D | d) | - |  | - | [10 empty] | 2
3 |  | Improvement of roads, drainage and canal |  |  | Protection dikes/slope protection | - | - | a) | 3000000 |  |  |  | - | [8 empty] | See projects listed below |  | 2
[8 empty] | b) | Paraguya | [14 empty] | AC
[8 empty] | c) | PEO | [14 empty] | AC
[8 empty] | d) | - | [14 empty] | AC
a. |  | Rehab./Impv't. of New Casay-Bugtong Talisay Provincial Road (Ph.II) |  |  | creeks and canRoads/Draiange/canals rehab/improved | - | - | a) | 500000 | a) | 2019-03-12 | e) |  | a) | 500000 | a) | 100% | c) | 100% | a) | 12 | Completed |  | AC
[8 empty] | b) | Toquero | b) | 2019-05-30 | f) |  | b) | 500000 | b) | - | d) | - | b) | 120 |  |  | 2
[8 empty] | c) | Admin | c) | 2019-07-30 | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - |  | - | [10 empty] | 2
b. |  | Rehab./Impv't. of Prk. 1 - Prk. 2 Sitio Pawas Provincial Road |  |  | creeks and canRoads/Draiange/canals rehab/improved | - | - | a) | 1500000 | a) | 7/23/2019 | e) | 7/30/2019 | a) | 1500000 | a) | 17.14% | c) | 1.18% | a) | 2 |  |  | 2
[8 empty] | b) | Sanchez | b) | 8/05/2019 | f) |  | b) | 1500000 | b) | - | d) | -15.96% | b) | 10 | On-going |  | 2
[8 empty] | c) | Admin | c) | 9/28/2019 | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | 55 | d) | - | [12 empty] | 2
c. |  | Repair/Rehab of Drainage System & Ground Gravelling at Kimamon NHS |  |  | creeks and canRoads/Draiange/canals rehab/improved | - | - | a) | 464833 | a) | - | e) | - | a) | 464833 | a) |  | c) | [5 empty] | 2
[8 empty] | b) | Azotes | b) | - | f) |  | b) | 464833 | b) |  | d) | [5 empty] | 2
[8 empty] | c) | Admin | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - |  | - | [10 empty] | 2
[13 empty] | - | [10 empty] | 2
4 |  | Improvement of bridges and cross drainage |  |  | bridge and cross drainage rehab./improved # of sq.m riprapped, culverts replaced | - | - | a) | 3000000 | [12 empty] | See projects listed below
[8 empty] | b) | Paraguya | [14 empty] | AC
[8 empty] | c) | PEO | [14 empty] | AC
[8 empty] | d) | - | [14 empty] | AC
|  | 4.1 | Impv't. of Jct. New Boholano - New Loon Cross Drainage |  | creeks and canRoads/Draiange/canals rehab/improved | - | - | a) | 2000000 | a) | - | e) |  | a) | 2000000 | a) | - | c) | - | a) | - | POW preparation on going c/o PEO-PDPM. Insufficient budget to complete required works for the project |  | AC
| 1 | [6 empty] | b) | - | b) | - | f) |  | b) | 2000000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - |  | - | [10 empty] | 1
|  | 4.2 | Impv't. of Jct. Saug-Sonlon-Bdry. Longanapan Cross Drainage |  | creeks and canRoads/Draiange/canals rehab/improved |  | - | a) | 1000000 | a) | - | e) | - | a) | 1000000 | a) | - | c) | - | a) | - | Waiting for the delivery of Materials |  | 1
| 1 | [6 empty] | b) | - | b) | - | f) |  | b) | 1000000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - |  | - | [10 empty] | 1
[13 empty] | - | [10 empty] | 1
D. | SUPPLEMENTAL BUDGET NO. 1 CY 2019
| 8918/Purchase / Const. / Compl./ Imprvt. Of Various Gov'y Bldgs, Structures & Facilities - General Fund Proper | [22 empty] | FS
| ■ | Purchase of Lot for Cemetery, Cambanogoy, Asuncion |  |  | Land |  | - | a) | 1500000 | a) | - | e) |  | a) | 1500000 | a) | - | c) | - | a) | - | Documents for fund transfer to be complied by the LGUs. Letter sent dated June 18, 2019 |  | AC
| 1 | [6 empty] | b) | - | b) | - | f) |  | b) | 1500000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - |  | - | [10 empty] | 1
| ■ | Purchase of Lot for Cemetery, San Roque, New Corella |  |  | Land |  | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Documents for fund transfer to be complied by the LGUs. Letter sent dated June 18, 2019 |  | 1
| 5 | [6 empty] | b) | - | b) | - | f) |  | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - |  | - | [10 empty] | 1
| 8918/Stimulus Projects for Various Barangays. Const. in Progress - Bldgs & Other Structure | [11 empty] | - | [10 empty] | 1
| ■ | Rehab/Impvt of Gymnasium, Sagayen, Asuncion |  |  | Bldg |  | - | a) | 1500000 | a) | - | e) |  | a) | 1500000 | a) | - | c) | - | a) | - | for allotment - Sept 19, 2019 |  | AC
| 1 | [6 empty] | b) | - | b) | - | f) |  | b) | 1500000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - |  | - | [10 empty] | 1
| ■ | Installation of Bleacher for the Brgy. Gym, Concepcion, Asuncion |  |  | Bldg |  | - | a) | 1000000 | a) | - | e) | - | a) | 1000000 | a) | - | c) | 30% | a) | - | On-going |  | 1
| 1 | [6 empty] | b) | - | b) | - | f) |  | b) | 1000000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - |  | - | [10 empty] | 1
[13 empty] | - | [10 empty] | 1
LOCALLY FUDNDED PROGRAM/PROJECT - 20% Development Fund
| Infrastructure Development Program | [22 empty] | AC
| 8918/ Stimulus Projects for Various Barangays | [22 empty] | AC
| Property, Plant and Equipment - Land | [22 empty] | AC
| ■ | Purchase of Lot for Resettlement Site, New Sambog, New Corella |  |  | Land |  | - | a) | 1500000 | a) | - | e) |  | a) | 1500000 | a) | - | c) |  | a) | - | for fund transfer. Waiting for LGU documents. Liquidation of previous fund transfer for the water system project of LGU. |  | AC
| 5 | [6 empty] | b) | - | b) | - | f) |  | b) | 1500000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - |  | - | [10 empty] | 1
| Property, Plant and Equipment - Construction in Progress-Infrastructure Assets | [11 empty] | - | [10 empty] | 1
| ■ | Installation of Street Lights at Prk 1,2,3,4, Sagayen, Asuncion |  |  | Electrification |  | - | a) | 1000000 | a) | - | e) |  | a) | 1000000 | a) | - | c) |  | a) | - | PO on process |  | AC
| 1 | [6 empty] | b) | - | b) | - | f) |  | b) | 1000000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - |  | - | [10 empty] | 1
[13 empty] | - | [10 empty] | 1
| ■ | Rehab/Imprvt. Of FMR, Prk 3,7, & 8, Concepcion, Asuncion |  |  | Road |  | - | a) | 500000 | a) | - | e) |  | a) | 500000 | a) | - | c) |  | a) | - | Procurement of Materials on process
| 1 | [6 empty] | b) | - | b) | - | f) |  | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - |  | - | [10 empty] | 1
| ■ | Rural Electrification Project, Purok 6, Concepcion, Asuncion |  |  | Electrification |  | - | a) | 1000000 | a) | - | e) | - | a) | 1000000 | a) | - | c) |  | a) | - | . Re-aligned Fund allocation to Construction of Children Playground withAmenities at Pob., New Corella |  | 1
| 1 | [6 empty] | b) | - | b) | - | f) |  | b) | 1000000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - |  | - | [10 empty] | 1
| ■ | Concreting of FMR, New Santiago, Asuncion |  |  | Road |  | - | a) | 2500000 | a) | 2019-05-21 | e) | - | a) | 2500000 | a) | - | c) | 30% | a) | - | Fund transferred to LGU |  | 1
| 1 | [6 empty] | b) | - | b) | - | f) |  | b) | 2500000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - |  | - | [10 empty] | 1
| ■ | Rural Electrification Project, Purok 5-8, Napungas, Asuncion |  |  | Electrification |  | - | a) | 1500000 | a) | - | e) | - | a) | 1500000 | a) | - | c) | - | a) | - | . Re-aligned Fund allocation to Construction of Children Playground withAmenities at Pob., New Corella |  | 1
| 1 | [6 empty] | b) | - | b) | - | f) |  | b) | 1500000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - |  | - | [10 empty] | 1
| ■ | Farm to Market Road, San Jose, New Corella |  |  | Road |  | - | a) | 2000000 | a) | - | e) | - | a) | 2000000 | a) | - | c) | - | a) | - | Plan Preparation on process c/o PDPM |  | 1
| 5 | [6 empty] | b) | - | b) | - | f) |  | b) | 2000000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - |  | - | [10 empty] | 1
[13 empty] | - | [10 empty] | 1
| ■ | Const. of Water System, New Sambog, New Corella |  |  | Water System Projects |  | - | a) | 1000000 | a) | - | e) |  | a) | 1000000 | a) | - | c) | - | a) | - | Fund transferred to LGU
| 5 | [6 empty] | b) | - | b) | - | f) |  | b) | 1000000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - |  | - | [10 empty] | 1
| ■ | Const. of Drainage Canal from Prk. 3, 1-A, 2-A to Prk 1-B, Brgy Site (Ph. 2), Limbaan, New Corella |  |  | Flood Control - Drainage |  | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | POW preparation on going c/o PDPM |  | 1
| 5 | [6 empty] | b) | - | b) | - | f) |  | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - |  | - | [10 empty] | 1
| ■ | Const. of FMR from Prk 1 to Sitio Magsaysay via Pundol & Prk 4, Patrocenio, New Corella |  |  | Road |  | - | a) | 2000000 | a) | - | e) | - | a) | 2000000 | a) | - | c) | - | a) | - | POW preparation on going c/o PDPM |  | 1
| 5 | [6 empty] | b) | - | b) | - | f) |  | b) | 2000000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - |  | - | [10 empty] | 1
| ■ | Const. of Multi-Purpose Pavement, San Jose, New Corella |  |  | Bldgs |  | - | a) | 500000 | a) | - | e) |  | a) | 500000 | a) | - | c) | - | a) | - | POW approved but allotment not yet requested waiting for deed of donation c/o Engr. Canillada
| 5 | [6 empty] | b) | - | b) | - | f) |  | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - |  | - | [10 empty] | 1
| Const. in Progress - Bldgs & Other Structures | [11 empty] | - | [10 empty] | 1
| ■ | Rehab/Impvt of Multi-Purpose Bldg, SCFA, Napungas, Asuncion |  |  | Bldgs |  | - | a) | 500000 | a) | - | e) |  | a) | 500000 | a) | - | c) | - | a) | - | Fund re-aligned to fund stimulus projects that need additional funding. ( AIP 3rd revision CY 2019) |  | AC
| 1 | [6 empty] | b) | - | b) | - | f) |  | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - |  | - | [10 empty] | 1
[13 empty] | - | [10 empty] | 1
| ■ | Const. of Multipurpose Covered Court, Buan, Asuncion |  |  | Bldgs |  | - | a) | 2500000 | a) | 2019-06-26 | e) |  | a) | 2500000 | a) | - | c) | - | a) | - | Fund transferred to LGU
| 1 | [6 empty] | b) | - | b) | - | f) |  | b) | 2500000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - |  | - | [10 empty] | 1
| ■ | Const. of Multipurpose Covered Court, Pamacaun, Asuncion |  |  | Bldgs |  | - | a) | 2500000 | a) | 2019-05-29 | e) | - | a) | 2500000 | a) | - | c) | 30% | a) | - | Fund transferred to LGU |  | 1
| 1 | [6 empty] | b) | - | b) | - | f) |  | b) | 2500000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - |  | - | [10 empty] | 1
| ■ | Const. of 2 Storey Multipurpose Hall Ph.2 (Brgy. Hall) , Poblacion, New Corella |  |  | Bldgs |  | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Plan preparation on -going c/o PDPM |  | 1
| 5 | [6 empty] | b) | - | b) | - | f) |  | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - |  | - | [10 empty] | 1
[13 empty] | - | [10 empty] | 1
| ■ | Rehab. Of Multi-Purpose Hall (Evacuation Ctr.) Limbaan, New Corella |  |  | Bldgs |  | - | a) | 500000 | a) | - | e) |  | a) | 500000 | a) | - | c) | - | a) | - | For allotment - Nov. 5, 2019
| 5 | [6 empty] | b) | - | b) | - | f) |  | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - |  | - | [10 empty] | 1
| ■ | Expansion of Multi-Purpose Hall ( Brgy. Hall), Patrocenio, New Corella |  |  | Bldgs |  | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Sched of bidding Dec 27 , 2019 |  | 1
| 5 | [6 empty] | b) | - | b) | - | f) |  | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - |  | - | [10 empty] | 1
MOOE 2019 | [9 empty] | a) |  | e) | - | a) |  | a) |  | c) |  | a) |  | For approval of POW and Plan |  | 1
|  | Repair maintenance of OPD, Pharmacy building, DDNH - CZ Compound |  |  | Renovation | - | - | a) | 100000 | b) |  | f) |  | b) |  | b) |  | d) |  | b) |  |  |  | AC
[8 empty] | b) | Estorco | c) |  | g) |  | c) | [9 empty] | 2
[8 empty] | c) | Admin | d) | [13 empty] | 2
[8 empty] | d) | - | [14 empty] | 2
2
E. | SUPPLEMENTAL BUDGET NO. 3 CY 2019
| LOCALLY FUNDED PROGRAM/PROJECTS- 20% DEVELOPMENT FUND | [22 empty] | FS
| INFRASTRUCTURE DEVELOPMENT PROGRAM | [22 empty] | AC
| 8918/ Various Local Roads & Drainage Development Project Construction in Progress- Infrastructure Assets | [22 empty] | AC
| ■ | Rehabilitation of Dujali-Pawas-San Vicente Provincial Road, B.E. Dujali |  |  | Road |  | - | a) | 2000000 | a) | - | e) |  | a) | 2000000 | a) | - | c) | - | a) | - | The amount was reduced to P1,102,900.00 |  | AC
[8 empty] | b) | - | b) | - | f) |  | b) | 2000000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - |  | - | [10 empty] | 2
| ■ | Repair/Rehabil;itation of Concrete R.d. Jct. Suaon-Libuton Kapalong |  |  | Road |  | - | a) | 1000000 | a) | - | e) | - | a) | 1000000 | a) | - | c) | - | a) | - | For implementation |  | 2
[8 empty] | b) | - | b) | - | f) |  | b) | 1000000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - |  | - | [10 empty] | 1
| 8918/ VariousWater System Development Project Construction in Progress- Infrastructure Assets | [11 empty] | - | [10 empty] | 1
| ■ | Improvement of Potable Water System at Brgy. Mambago- A, Samal District, IGACOS |  |  | Water System |  | - | a) | 500000 | a) | - | e) |  | a) | 500000 | a) | - | c) | - | a) | - | (Amended in the AIP 2nd Revision to change the location from Peñaplata to Samal District) PO approved September 2, 2019 |  | AC
[8 empty] | b) | - | b) | - | f) |  | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - |  | - | [10 empty] | 2
| ■ | Rehabilitation of Potable Water System at Brgy. San Miguel, Samal District, IGACOS |  |  | Water System |  | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - |  |  | 2
[8 empty] | b) | - | b) | - | f) |  | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - |  | - | [10 empty] | 2
| ■ | Construction of Potable Water System at Brgy.Linusotan, Kaputian District, IGACOS |  |  | Water System |  | - | a) | 1300000 | a) | - | e) | - | a) | 1300000 | a) | - | c) | - | a) | - | (Additional 800,000.00 from Const. of PWS in purok 2, Pag-asa, Kapalong which was funded by OPAPP CY 2018) (amended) For allotment- October 15, 2019 |  | 2
[8 empty] | b) | - | b) | - | f) |  | b) | 1300000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - |  | - | [10 empty] | 2
| ■ | Rehabilitation of Water System in PEEDO-LPRRC, Brgy. Poblacion, New Corella |  |  | Water System |  | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For allotment- October 15, 2019 |  | 2
[8 empty] | b) | - | b) | - | f) |  | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - |  | - | [10 empty] | 2
| 8918/ Stimulus Projects for Various Brgys.- District 1 Construction in Progress- Infrastructure Assets | [11 empty] | - | [10 empty] | 2
| ■ | Construction of Water System at Brgy. San Agustin, Tagum City |  |  | Water System |  | - | a) | 500000 | a) | - | e) |  | a) | 500000 | a) | - | c) | - | a) | - | Declared as savings to add to stimulus projects that need additional fund No deed of donation |  | AC
[8 empty] | b) | - | b) | - | f) |  | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - |  | - | [10 empty] | 2
| DISASTER REHABILITATION & RECOVERY PROGRAM Building Back Better Project | [11 empty] | - | [10 empty] | 2
| Repairs & Maintenance- Infrastructure Assets | [22 empty] | AC
| ■ | Disilation of Tagum Creek |  |  |  |  | - | a) | 2000000 | a) | - | e) |  | a) | 2000000 | a) | - | c) | - | a) | - | PLAN AND POW on process c/o PEO-PDPM |  | AC
[8 empty] | b) | - | b) | - | f) |  | b) | 2000000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - |  | - | [10 empty] | 1
| ■ | Disilation of Mactan River (Ph. II) |  |  |  |  | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | PLAN AND POW on process c/o PEO-PDPM |  | 1
[8 empty] | b) | - | b) | - | f) |  | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - |  | - | [10 empty] | 2
| Property, Plant and Equipmen Construction in Progress- Infrastructure Assets | [11 empty] | - | [10 empty] | 2
| ■ | Rehabilitation of Pamacaun-Lasang-Banate Provincial Road |  |  |  |  | - | a) | 1500000 | a) | - | e) |  | a) | 1500000 | a) | - | c) | - | a) | - |  |  | AC
[8 empty] | b) | - | b) | - | f) |  | b) | 1500000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - |  | - | [10 empty] | 1
| ■ | Rehabilitation of Del Pilar Jct. Silangan |  |  |  |  | - | a) | 1500000 | a) | - | e) | - | a) | 1500000 | a) | - | c) | - | a) | - |  |  | 1
[8 empty] | b) | - | b) | - | f) |  | b) | 1500000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - |  | - | [10 empty] | 1
| ■ | Installation of 72" dia RCPC x 4M at San Agustin ES |  |  |  |  | - | a) | 350000 | a) | - | e) | - | a) | 350000 | a) | - | c) | - | a) | - |  |  | 1
[8 empty] | b) | - | b) | - | f) |  | b) | 350000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - |  | - | [10 empty] | 1
| ■ | Rehabilitation of Libuganon River along Kapalong Mabantao-Florida Provincial Road |  |  |  |  | - | a) | 900000 | a) | - | e) | - | a) | 900000 | a) | - | c) | - | a) | - |  |  | 1
[8 empty] | b) | - | b) | - | f) |  | b) | 900000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - |  | - | [10 empty] | 1
| ■ | Rehabilitation of Mesaoy-Jct. Mahayahay Road |  |  |  |  | - | a) | 1000000 | a) | - | e) | - | a) | 1000000 | a) | - | c) | - | a) | - |  |  | 1
[8 empty] | b) | - | b) | - | f) |  | b) | 1000000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - |  | - | [10 empty] | 1
| ■ | Rehabilitation of Dujali-Balisong-Magupising Provincial Road |  |  |  |  | - | a) | 1280000 | a) | - | e) | - | a) | 1280000 | a) | - | c) | - | a) | - |  |  | 1
[8 empty] | b) | - | b) | - | f) |  | b) | 1280000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - |  | - | [10 empty] | 1
| ■ | Rehabilitation of Sta. Fe- Mambing Road & Slope Protection |  |  |  |  | - | a) | 1320000 | a) | - | e) | - | a) | 1320000 | a) | - | c) | - | a) | - |  |  | 1
[8 empty] | b) | - | b) | - | f) |  | b) | 1320000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - |  | - | [10 empty] | 1
F. | SUPPLEMENTAL BUDGET NO. 4 CY 2019 | [11 empty] | - | [10 empty] | 1
| INFRASTRUCTURE DEVELOPMENT PROGRAM | [22 empty] | FS
| LOCALLY FUNDED PROGRAMS/ PROJECTS GENERAL FUND PROPER | [22 empty] | AC
AC
| PEACE AND ORDER PROGRAM/1914 Construction in Progress- Land Improvements | [22 empty] | AC
| ■ | Provincial Livestock & Poultry Multiplier Farm Road Network Construction, Sitio Salawao, Sto. Niño, Talaingod |  |  |  |  | - | a) | 5500000 | a) | - | e) |  | a) | 5500000 | a) | - | c) | - | a) | - | For allotment Nov. 22, 2019 |  | AC
[8 empty] | b) | - | b) | - | f) |  | b) | 5500000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - |  | - | [10 empty] | 1
| ■ | Proposed Road Opening of Tawinian-Tapayanon Road Section |  |  |  |  | - | a) | 10000000 | a) | - | e) | - | a) | 10000000 | a) | - | c) | - | a) | - | Alloted- Dec. 6, 2019 |  | 1
[8 empty] | b) | - | b) | - | f) |  | b) | 10000000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - |  | - | [10 empty] | 1
| ■ | Rehabilitation of San Jose- Sitio Mahayahay-Magwawa Provincial Road, Sro. Tomas |  |  |  |  | - | a) | 1000000 | a) | - | e) | - | a) | 1000000 | a) | - | c) | - | a) | - | POW preparation on-going c/o South District |  | 1
[8 empty] | b) | - | b) | - | f) |  | b) | 1000000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - |  | - | [10 empty] | 2
| 8918/ Various Government Buildigs & Facilities Development Project Construction in Progress- Land Improvements | [11 empty] | - | [10 empty] | 2
| ■ | Construction of Perimeter Fence of Day Care Center I Nanyo, Panabo City |  |  |  |  | - | a) | 500000 | a) | - | e) |  | a) | 500000 | a) | - | c) | - | a) | - | Sched of bidding Dec. 27, 2019 |  | AC
[8 empty] | b) | - | b) | - | f) |  | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - |  | - | [10 empty] | 2
| ■ | Construction of Multi-Purpose Building, Balagunan, Sto. Tomas |  |  |  |  | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For allotment Dec .3, 2019 |  | 2
[8 empty] | b) | - | b) | - | f) |  | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - |  | - | [10 empty] | 2
| ■ | Completion of Brgy. Health Center, Maniki, Kapalong |  |  |  |  | - | a) | 627000 | a) | - | e) | - | a) | 627000 | a) | - | c) | - | a) | - | PROJECT Was funded by LGU, Kapalong |  | 2
[8 empty] | b) | - | b) | - | f) |  | b) | 627000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - |  | - | [10 empty] | 1
| INFRASTRUCTURE DEVELOPMENT PROGRAM | [11 empty] | - | [10 empty] | 1
| LOCALLY FUNDED PROGRAMS/ PROJECTS 20% DEVELOPMENT FUND | [22 empty] | AC
AC
| 8918/ Rehabilitation of Various Provincial Roads, District 1 Construction in Progress- Infrastructure Assets | [22 empty] | AC
| ■ | Improvement of Km. 9 Sagayen-Sawata Provincial Road, San Isidro, Ph. 2 |  |  |  |  | - | a) | 4591029 | a) | - | e) |  | a) | 4591029 | a) | - | c) | - | a) | - |  |  | AC
[8 empty] | b) | - | b) | - | f) |  | b) | 4591029 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - |  | - | [10 empty] | 1
| 8918/ Various Local Roads and Drainaige Development Project Construction in Progress- Infrastructure Assets | [11 empty] | - | [10 empty] | 1
| ■ | Rehabilitation of Local Roads at Dalisay-Manay Road Section, Panabo City |  |  |  |  | - | a) | 246100 | a) | - | e) |  | a) | 246100 | a) | - | c) | - | a) | - |  |  | AC
[8 empty] | b) | - | b) | - | f) |  | b) | 246100 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - |  | - | [10 empty] | 2
| ■ | Rehabilitation of Local Roads at Sta. Cruz-Jct. Tagpore-Buenavista Raod Section, Panabo City |  |  |  |  | - | a) | 431000 | a) | - | e) | - | a) | 431000 | a) | - | c) | - | a) | - |  |  | 2
[8 empty] | b) | - | b) | - | f) |  | b) | 431000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - |  | - | [10 empty] | 2
| ■ | Rehabilitation of Local Roads at Taba-Bucana Road Section, Taba, Carmen |  |  |  |  | - | a) | 220000 | a) | - | e) | - | a) | 220000 | a) | - | c) | - | a) | - |  |  | 2
[8 empty] | b) | - | b) | - | f) |  | b) | 220000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - |  | - | [10 empty] | 2
| 8918/ Stimulus Projects for Various Barangays Construction in Progress- Infrastructure Assets | [11 empty] | - | [10 empty] | 2
| ■ | Construction of Potable Water System at Purok 6, New Santiago, Asuncion |  |  |  |  | contract | a) | 1000000 | a) | - | e) |  | a) | 1000000 | a) | - | c) | - | a) | - | For allotment Nov. 6, 2019 |  | AC
[8 empty] | b) | - | b) | - | f) |  | b) | 1000000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - |  | - | [10 empty] | 2
| ■ | Concreting of Brgy. Road Canal, Dujali, B.E. Dujali |  |  |  |  | contract | a) | 650000 | a) | - | e) | - | a) | 650000 | a) | - | c) | - | a) | - | Alloted Oct. 18, 2019 Procurement on process |  | 2
[8 empty] | b) | - | b) | - | f) |  | b) | 650000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - |  | - | [10 empty] | 2
| ■ | Desilting and Conretign of Drainage-Main Collector Canal, New Casay, B.E. Dujali |  |  |  |  | contract | a) | 650000 | a) | - | e) | - | a) | 650000 | a) | - | c) | - | a) | - | For allotment - Sept. 27, 2019 |  | 2
[8 empty] | b) | - | b) | - | f) |  | b) | 650000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - |  | - | [10 empty] | 2
| ■ | Concreting of Drainage, Tanglaw, B.E., Dujali |  |  |  |  | contract | a) | 1200000 | a) | - | e) | - | a) | 1200000 | a) | - | c) | - | a) | - | For allotment Sept. 19, 2019 |  | 2
[8 empty] | b) | - | b) | - | f) |  | b) | 1200000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - |  | - | [10 empty] | 2
| ■ | Construction of Potable Water System, New Malitbog, Panabo City |  |  |  |  | contract | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For re-inspection and plan revision in order to reflect in the plan the complete details for the project to be functional.P500,000.00 covers only drilling activity |  | 2
[8 empty] | b) | - | b) | - | f) |  | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - |  | - | [10 empty] | 2
| ■ | Construction of Water System Project, Poblacion Kaputian, Samal |  |  |  |  | contract | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Alloted Oct 17, 2019 Procurement on process |  | 2
[8 empty] | b) | - | b) | - | f) |  | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - |  | - | [10 empty] | 2
| ■ | Construction of Canal Linign at Prk. 5, Salvacion, Panabo City |  |  |  |  | contract | a) | 600000 | a) | - | e) | - | a) | 600000 | a) | - | c) | - | a) | - | Alloted Oct. 18, 2019 Procurement on process |  | 2
[8 empty] | b) | - | b) | - | f) |  | b) | 600000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - |  | - | [10 empty] | 2
| ■ | Rehabilitation of Brgy. Road at Lunga-og. Sto. Tomas |  |  |  |  | contract | a) | 600000 | a) | - | e) | - | a) | 600000 | a) | - | c) | - | a) | - | For allotment Sept. 19, 2019 |  | 2
[8 empty] | b) | - | b) | - | f) |  | b) | 600000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - |  | - | [10 empty] | 2
| ■ | Construction of Children's Playground with Amenities, Poblacion, New Corella |  |  |  | Admin | contract | a) | 2500000 | a) | - | e) | - | a) | 2500000 | a) | - | c) | - | a) | - | Allotment Dec. 3, 2019 Procurement on process |  | 2
[8 empty] | b) | - | b) | - | f) |  | b) | 2500000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - |  | - | [10 empty] | 1
| 8918/ Stimulus Projects for Various Barangays Construction in Progress- Bldgs. & Other Structures | [11 empty] | - | [10 empty] | 1
| ■ | Construction of 2 Storey Multi-Purpose Hall Ph. 3 (Brgy. Hall), oblacion, New Corella |  |  |  |  | - | a) | 500000 | a) | - | e) |  | a) | 500000 | a) | - | c) | - | a) | - | Plan preparation on-going c/o PDPM |  | AC
[8 empty] | b) | - | b) | - | f) |  | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - |  | - | [10 empty] | 1
| ■ | Construction of Evacuation Center at Purok 1-C Brgy. Sto. Niño, Carmen |  |  |  |  | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For allotment Dec. 3, 2019 |  | 1
[8 empty] | b) | - | b) | - | f) |  | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - |  | - | [10 empty] | 2
| ■ | Rehabilitation of Evacuation Center at Magugpo Pob., Tagum City |  |  |  |  | - | a) | 600000 | a) | - | e) | - | a) | 600000 | a) | - | c) | - | a) | - | Sched of bidding Dec 27, 2019 |  | 2
[8 empty] | b) | - | b) | - | f) |  | b) | 600000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - |  | - | [10 empty] | 1
| ■ | Construction of Brgy. Health Center at Magugpo South, Tagum City |  |  |  |  | - | a) | 1550000 | a) | - | e) | - | a) | 1550000 | a) | - | c) | - | a) | - | Allotd Nov. 15, 2019 Procurement on process |  | 1
[8 empty] | b) | - | b) | - | f) |  | b) | 1550000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - |  | - | [10 empty] | 1
[13 empty] | - | [10 empty] | 1
| ■ | Rehabilitation of Mulit-Purpose Building (Evacuation Center), Limbaan, New Corella |  |  |  |  | - | a) | 600000 | a) | - | e) |  | a) | 600000 | a) | - | c) | - | a) | - | For allotment nov. 5, 2019
[8 empty] | b) | - | b) | - | f) |  | b) | 600000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - |  | - | [10 empty] | 1
| ■ | Expansion of Multi-Purpose Hall ( Brgy. Hall), Patrocenio, New Corella |  |  |  |  | - | a) | 650000 | a) | - | e) | - | a) | 650000 | a) | - | c) | - | a) | - | Alloted Oct. 18, 2019 Procurement on process |  | 1
[8 empty] | b) | - | b) | - | f) |  | b) | 650000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - |  | - | [10 empty] | 1
| ■ | Construction of Multi-Purpose Hall, Waterfall, Panabo City |  |  |  |  | - | a) | 1050000 | a) | - | e) | - | a) | 1050000 | a) | - | c) | - | a) | - | For allotment |  | 1
[8 empty] | b) | - | b) | - | f) |  | b) | 1050000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - |  | - | [10 empty] | 2
| ■ | Rehabilitation of Multi-Purpose Hall, San Francisco, Panabo City |  |  |  |  | - | a) | 600000 | a) | - | e) | - | a) | 600000 | a) | - | c) | - | a) | - | Alloted Oct. 18, 2019 Procurement on process |  | 2
[8 empty] | b) | - | b) | - | f) |  | b) | 600000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - |  | - | [10 empty] | 2
| ■ | Rehabilitation of Evacuation Center at Datu Abdul Dadia, Panabo City |  |  |  |  | - | a) | 650000 | a) | - | e) | - | a) | 650000 | a) | - | c) | - | a) | - | Sched of bidding -Dec 27, 2019 |  | 2
[8 empty] | b) | - | b) | - | f) |  | b) | 650000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - |  | - | [10 empty] | 2
| ■ | Construction of Multi-Purpose Hall, Buenavista, Panabo City |  |  |  |  | - | a) | 1050000 | a) | - | e) | - | a) | 1050000 | a) | - | c) | - | a) | - | Sched of bidding -Dec 27, 2019 |  | 2
[8 empty] | b) | - | b) | - | f) |  | b) | 1050000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - |  | - | [10 empty] | 2
| ■ | Rehabilitation of Multi-Purpose Hall, Llittle Panay, Panabo City |  |  |  |  | - | a) | 550000 | a) | - | e) | - | a) | 550000 | a) | - | c) | - | a) | - | For allotment Dec. 11, 2019 |  | 2
[8 empty] | b) | - | b) | - | f) |  | b) | 550000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - |  | - | [10 empty] | 2
| ■ | Rehabilitation of Multi-Purpose Hall, Pantaron, Sto. Tomas |  |  |  |  | - | a) | 550000 | a) | - | e) | - | a) | 550000 | a) | - | c) | - | a) | - | Alloted Oct. 18, 2019 Procurement on process |  | 2
[8 empty] | b) | - | b) | - | f) |  | b) | 550000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - |  | - | [10 empty] | 2
| ■ | Rehabilitation of Multi-Purpose Hall, Salvacion, Sto. Tomas |  |  |  |  | - | a) | 1000000 | a) | - | e) | - | a) | 1000000 | a) | - | c) | - | a) | - | POW preparation on-going c/o PDPM |  | 2
[8 empty] | b) | - | b) | - | f) |  | b) | 1000000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - |  | - | [10 empty] | 2
| ■ | Completion of Multi-Purpose Hall, San Jose, Sto. Tomas |  |  |  |  | - | a) | 600000 | a) | - | e) | - | a) | 600000 | a) | - | c) | - | a) | - | Alloted Nov. 15, 2019 Procurement on process |  | 2
[8 empty] | b) | - | b) | - | f) |  | b) | 600000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - |  | - | [10 empty] | 2
| ■ | Rehabilitation of Multi-Purpose Hall, Kasilak, Panabo City |  |  |  |  | - | a) | 650000 | a) | - | e) | - | a) | 650000 | a) | - | c) | - | a) | - | Alloted Nov. 15, 2019 Procurement on process |  | 2
[8 empty] | b) | - | b) | - | f) |  | b) | 650000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - |  | - | [10 empty] | 2
| ■ | Rehabilitation of Brgy. Health Center, Dalisay, Panabo City |  |  |  |  | - | a) | 550000 | a) | - | e) | - | a) | 550000 | a) | - | c) | - | a) | - | For allotment Dec. 4, 2019 |  | 2
[8 empty] | b) | - | b) | - | f) |  | b) | 550000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - |  | - | [10 empty] | 2
[13 empty] | - | [10 empty] | 2
| ■ | Rehabilitation of Evacuation Center, Kiotoy, Panabo City |  |  |  |  | - | a) | 650000 | a) | - | e) |  | a) | 650000 | a) | - | c) | - | a) | - | Sched of bidding Dec 27, 2019
[8 empty] | b) | - | b) | - | f) |  | b) | 650000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - |  | - | [10 empty] | 2
| ■ | Rehabilitation of Evacuation Center, Cagangohan, Panabo City |  |  |  |  | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | POW for approval Nov. 5, 2019 |  | 2
[8 empty] | b) | - | b) | - | f) |  | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - |  | - | [10 empty] | 2
| ■ | Rehabilitation of Multi-Purpose Bldg. (Brgy. Hall) Tagpopongan, IGACOS |  |  |  |  | - | a) | 174460.33 | a) | - | e) | - | a) | 174460.33 | a) | - | c) | - | a) | - | For allotment Nov. 5, 2019 |  | 2
[8 empty] | b) | - | b) | - | f) |  | b) | 174460.33 | b) | - | d) | - | b) | - |  |  | 2
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | - | d) | - |  | - | [10 empty] | 2
| 5% CALAMITY FUND | [11 empty] | - | [10 empty] | 2
| DISASTER REHABILITATION & RECOVERY PROGRAM Building Back Better Project | [22 empty] | FS
| ■ | Rehabilitation of Canal Lining and Slope Protection at San Agustin E/S, San Agustin, Tagum City |  |  |  |  | - | a) | 350000 | a) | - | e) |  | a) | 350000 | a) | - | c) | - | a) | - |  |  | AC
[8 empty] | b) | - | b) | - | f) |  | b) | 350000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - |  | - | [10 empty] | 1
| TRUST FUND 2019 | [11 empty] | - | [10 empty] | 1
| PROJECTS FOR PROVINCIAL VETERINARY OFFICE | [22 empty] | FS
| ■ | Poultry House and Training Center Sto. Niño, Talaingod |  |  |  |  | - | a) | 500000 | a) | - | e) |  | a) | 500000 | a) | - | c) | - | a) | - |  |  | AC
[8 empty] | b) | - | b) | - | f) |  | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - |  | - | [10 empty] | 1
|  | Establishment of Multiplier Farm Project Sto. Niño, Talaingod |  |  |  |  | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - |  |  | 1
[8 empty] | b) | - | b) | - | f) |  | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - |  | - | [10 empty] | 1
| INFRASTRUCTURE DEVELOPMENT PROGRAM | [11 empty] | - | [10 empty] | 1
| ■ | Purchase of Geo Resistivity Instrument |  |  |  |  | - | a) | 6567412 | a) | - | e) |  | a) | 6567412 | a) | - | c) | - | a) | - | Waiting for delivery of instrument |  | AC
[8 empty] | b) | - | b) | - | f) |  | b) | 6567412 | b) | - | d) | - | b) | - |  |  | 1
[8 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[8 empty] | d) | - | d) | - |  | - | [10 empty] | 1
[13 empty] | - | [10 empty] | 1
CMGP 2019
| ■ | Road Upgrading of Sto Nino - Kabankalan - La Paz Provincial Road, Carmen |  |  |  |  | - | a) | 44461624.67 | a) |  | e) |  | a) | - | a) | 4.3% | c) | 34.23% | a) | 30 | On-going
[8 empty] | b) | Comidoy | b) | 10/7/2019 | f) |  | b) | - | b) | - | d) | 29.93% | b) | 610 |  |  | 2
[8 empty] | c) | GP & H CONST. | c) | 5/15/2020 | g) | - | c) | - | [8 empty] | 2
[8 empty] | d) | 222 C.D | d) |  |  | - | [10 empty] | 2
| ■ | Road Upgrading of Jct Highway - Sto Nino - La Paz - San Vicenter Provincial Road, Carmen |  |  |  |  | - | a) | 80481331.34 | a) |  | e) | - | a) | - | a) | 22.77% | c) | 33.12% | a) | - | On-going |  | 2
[8 empty] | b) | Fernandez | b) | 10/7/2019 | f) |  | b) | - | b) | - | d) | 10.35% | b) | -
[8 empty] | c) | Tagum Builders | c) | 6/22/2020 | g) | - | c) | -
[8 empty] | d) | 259 C.D | d) |  |  | -
| ■ | Road Upgrading of Kapalong - Mabantao - Florida Road with Bridge Component |  |  |  |  | - | a) | 15890000 | a) |  | e) | - | a) | - | a) |  | c) |  | a) | -
[8 empty] | b) |  | b) |  | f) |  | b) | - | b) | - | d) |  | b) | -
[8 empty] | c) |  | c) |  | g) | - | c) | -
[8 empty] | d) |  | d) |  |  | -
-
|  | Mark | Municipality/City |  | Color
|  | 1 | Asuncion |  | Red
|  | 2 | B.E. Dujali |  | Yellow
| GF- GENERAL FUND | 3 | Carmen |  | Blue | [10 empty] | TF - TRUST FUND (NATIONAL FUNDED PROJECT)
| 20% DF - 20% DEV'T. FUND | 4 | Kapalong |  | Pink | [10 empty] | a) SLRF - Special Local Road Fund
| 5% CF - 5% CALAMITY FUND | 5 | New Corella |  | Gray | [10 empty] | b) KALSADA - Konkreto at Ayos na Lansangan Tungo sa Pangkalahatang Kaunlaran
| CO - CAPITAL OUTLAY | 6 | San Isidro |  | Orange | [10 empty] | c) PRDP - Philippine Rural Development Projects
| CONG. FUND - CONGRESSIONAL FUND | 7 | Sto Tomas |  | Sky Blue | [10 empty] | d) SELAP - Support to Emergency and Livelihood Assistance Project
|  | 8 | Talaingod |  | Violet | [10 empty] | e) PAMANA - Payapa at Masaganang Pamayanan
| SEF - SPECIAL EDUCATIONAL UFND | 9 | Panabo City |  | Brown | [10 empty] | f) CBRMC - Community Based Road Maintenance Contracting
|  | 10 | IGACOS |  | Yellow Green | [10 empty] | g) MBC - Maintenance by Contract
|  | 11 | Tagum City |  | Green | [10 empty] | h) PCF-Performance Challenge Fund-DILG
i) FMRDP - Farm to Market Road
j.) CMGP - Conditional Grant to Provinces
k.) OPAPP - Office of the President Adviser on the Peace Process
l.) LGSF-AM - Local Government Support Fund Assistance to Municipalities
Prepared by: |  |  |  | Checked | [12 empty] | Recommending Approval
Noted
GILBERT G. MAMBULAO JR |  |  |  | ELISA A. BARCENA | TESSIE G. ABABON | [9 empty] | JIVELLYN B. CO | [5 empty] | GLENN A. OLANDRIA
Engineer II |  |  |  | Engineer IV- Engineering Dist 1, Area Engineer |  | Engr. IV- Area Engr. 2nd Dist | [9 empty] | Asst. PG-Department Head |  |  |  |  | Provincial Engineer

## On Going (hidden)
PROVINCE OF DAVAO DEL NORTE
ACCOMPLISHMENT REPORT
FOR THE MONTH OF JANUARY 2018
SECTOR: ECONOMIC (INFRASTRUCTURE DEV'T. PROGRAM)
OFFICE/AGENCY: PROVINCIAL ENGINEER'S OFFICE
AREA: 1ST ENGINEERING DISTRICT - ON-GOING PROJECTS
Name of Project |  |  |  | Type | Physical | Mode | PROJECT DATA | [5 empty] | Financial (000) |  | Physical Accomplishment |  |  |  | Employment |  | REMARKS
|  |  |  | of | Target | of | a) Project Cost |  | a) Date A lot. Rel. |  | e) # of days suspended |  | a) Program |  | a) Planned |  | c) Actual |  | Generated
|  |  |  | Project | (Descrip | Impl. | b) Project Engineer |  | b) Date Started |  | f) # of days extended |  | b) Allotment |  | b) Revised |  | d) Slippage |  | a) # of Persons
|  |  |  | (Location) | tion) |  | c) Implementor |  | c)Target Compl. Date |  | g) Date completed |  | c) Disbursement | [5 empty] | b) Man-days
[7 empty] | d) Duration |  | d) Revised Compl. Date
I. | PROJECTS UNDER THE CONTINUING APPROPRIATION | [21 empty] | 893809.45
| A. | Supplemental Budget # 4 CY 2017
|  | 1 | Upgrading of DDNSTC (Basketball/Voleyball | Covered |  | Contract | a) | 99992356.64 | a) | CY 2018 | e) | - | a) | 99992356.64 | a) | 28.39% | c) | 18.9% | a) | 23 | On-going
|  |  | MP Covered Court),Sports Center, Mankilam, | Court |  |  | b) | Escurzon | b) | 07/17/18 | f) | - | b) | 99992356.64 | b) | - | d) | -9.49% | b) | 345
|  |  | Tagum City |  |  |  | c) | YBC | c) | 07/11/19 | g) | - | c) | -
[7 empty] | d) | 360 CD | d) | -
| B. | Trust Fund
1. PAMANA-DILG CY 2014
|  | 1.1 Construction of Biga Bridges, Kapalong |  | Road | - | Contract | a) | 24959503.45 | a) | CY 2014 | e) | - | a) | 24959503.45 | a) | 100.00% | c) | 30.095% | a) | 8 | On-going
[7 empty] | b) | Limpo | b) | 07/01/16 | f) | - | b) | 24959503.45 | b) | 44.99% | d) | -14.89% | b) | 1184 | Resume last June 1, 2018
[7 empty] | c) | Dvo. Rock Mixer | c) | 07/30/18 | g) | - | c) | 37,439,255.18
[7 empty] | d) | 760 CD | d) | 09/27/19
|  | 1.2 Road Rehabilitation/Improvement of Prk. 3, |  | Road | - | Contract | a) | 50,500,288.95 | a) | CY 2014 | e) | - | a) | 50,500,288.95 | a) | 100.00% | c) | 84.68% | a) | 22 | On-going
|  | Palma Gil-Prk.2 (side 2), Sto. Niño-Mahayahay-Tugas- |  |  |  |  | b) | Dadula | b) | 07/07/16 | f) | 398 CD | b) | 50,500,288.95 | b) | 97.20% | d) | -12.52% | b) | 806
|  | Nanaga Road, with 1 -unit, 40 ln.m PSCG Bridge, |  |  |  |  | c) | Puregold | c) | 03/12/18 | g) | - | c) | 7,575,009.962
|  | Kapalong |  |  |  |  | d) | 613 CD | d) | 04/14/19
2. PRDP CY 2015
|  | 2.1 Rehab. Of Capungagan-Boundary San |  | Road | 10.6 kms. | Contract. | a) | 108,303,841.70 | a) | CY 2015 | e) | 140 CD | a) | 108,303,841.70 | a) | 100.00% | c) | 54.576% | a) | 38 | On-going
|  | Miguel FMR, Kapalong, Davao del Norte |  |  |  |  | b) | Nasol | b) | 04/06/16 | f) | 547 CD | b) | 108,303,841.70 | b) | 69.94% | d) | -15.36% | b) | 836 | Increase of Project Cost due to Variation Order with
[7 empty] | c) | VICLAO | c) | 03/26/17 | g) | - | c) | 37663058.91 | [6 empty] | Extra Work. (Php 4,992,591.29)
[7 empty] | d) | 718 CD | d) | 08/28/19 | [10 empty] | Contractor catch-up plan within 3 months
|  | 2.2 Rehab. Of Pob.-Limbaan-Suawon-Macgum |  | Road | 15.01 kms./ | Contract. | a) | 205,202,114.16 | a) | CY 2015 | e) | 229 CD | a) | 205,202,114.16 | a) | 99.968% | c) | 43.379% | a) | 40 | On-going
|  | FMR w/ Bridge, New Corella, Davao del Norte |  |  | 42 ln.m |  | b) | Madrigal | b) | 04/08/16 | f) | 464 CD | b) | 205,202,114.16 | b) | 50.49% | d) | -7.111% | b) | 880 | Increase of Project Cost due to Variation Order Php 14,948,622.18
[7 empty] | c) | Dvo. Rock Mixer | c) | 01/18/19 | g) | - | c) | 28538091.3
[7 empty] | d) | 1,455 CD | d) | 03/28/20 | [10 empty] | Partial suspension due to soft soil from sta. 8+000 - 10+000
3. KALSADA CY 2015
|  | 3.1 Improvement of Km. 9 Sagayen-Sawata Provincial |  | Road | 6667.54 m | Admin | a) | 33401544.78 | a) | CY 2015 | d) | - | a) | 33401544.78 | a) | 5.062% | c) | 2.482% | a) |  | Original contract terminated due to very poor performance
|  | San Isidro, Davao del Norte |  |  |  |  | b) | Limpo | b) | 10/16/18 | e) |  | b) | 33401544.78 | b) |  | d) | -2.58% | b) |  | of the contractor.The contract cost P 47,213,478.31.
[7 empty] | c) | PEO | c) | 09/14/19 | f) | - | c) | [7 empty] | On-going
[7 empty] | d) |  | d)
| C. | Trust Fund
1. DILG FUND CY 2016
|  | 1.1 | Improvement of DILG Building, Gov't. | Bldg. | - | Contract | a) | 5000000 | a) | CY 2016 | e) | - | a) | 5000000 | a) | 75.00% | c) | 62.183% | a) | 8 | On-going
|  |  | Center, Mankilam, Tagum City |  |  |  | b) | Pasiona | b) | 06/01/18 | f) | - | b) | 5000000 | b) | - | d) | -12.82% | b) | 176 | Suspended as of December 21, 2018
[7 empty] | c) | PEO | c) | 12/31/18 | g) | - | c) | 3,119,203.14
[7 empty] | d) | 214 CD | d) | -
| D. | 20% Development Fund CY 2017
|  | 1. Const./Rehab./Comp. of Various Gov't. Bldgs. |  | Bldg. | - | Admin | a) | 9,000,000.00 | [12 empty] | Investigation/Inspection of priority projects
|  | Struct., Fac. (Provincewide) |  |  |  |  | b) | Foronda/Ababon
[7 empty] | c) | PEO
[7 empty] | d) | -
|  | 1.1 | Rehab. Of PEO Training Center | Bldg. |  | Admin | a) | 476,876.00 | a) | - | e) | - | a) | 476,876.00 | a) | - | c) | - | a) | - | For implementation
|  |  | (PDPM),Mankilam, Tagum City |  |  |  | b) | - | b) | - | f) | - | b) | 476,876.00 | b) | - | d) | - | b) | -
|  |  | (Part of P803,000.00)(20% DF CY 2018-P326,124.00) |  |  |  | c) | Admin | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
|  | 1.2 | Repair/Rehab. Of PEO Building | Bldg. |  | Admin | a) | 1,800,000.00 | a) | 07/31/18 | e) | - | a) | 1,800,000.00 | a) | - | c) | - | a) | - | For implementation
|  |  | (Motorpool),Mankilam, Tagum City |  |  |  | b) | - | b) | - | f) | - | b) | 1,800,000.00 | b) | - | d) | - | b) | -
[7 empty] | c) | Admin | c) | - | g) | - | c) | 952,282.00
[7 empty] | d) | - | d) | -
|  | 1.3 | Repair/Rehab. Of PEO Building | Bldg. |  | Admin | a) | 1,073,124.00 | a) | 06/11/18 | e) | - | a) | 1,073,124.00 | a) | - | c) | - | a) | - | For implementation
|  |  | (PEO Warehouse),Mankilam, |  |  |  | b) | - | b) | - | f) | - | b) | 1,073,124.00 | b) | - | d) | - | b) | -
|  |  | Tagum City |  |  |  | c) | Admin | c) | - | g) | - | c) | 529,793.00
[7 empty] | d) | - | d) | -
|  | 1.4 | Improvement of Garciaville Day Care | Bldg. |  | Admin | a) | 330,000.00 | a) | 11/06/18 | e) | - | a) | 330,000.00 | a) | - | c) | - | a) | - | For implementation
|  |  | Center, Mankilam, Tagum City |  |  |  | b) | - | b) | - | f) | - | b) | 330,000.00 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
|  | 1.5 | Construction of GSP Building Extension | Bldg. |  | Admin | a) | 500,000.00 | a) | 07/20/18 | e) | - | a) | 500,000.00 | a) | 16.58% | c) | 16.58% | a) | 8 | On-going
|  |  | Mankilam, Tagum City |  |  |  | b) | Quirante | b) | 01/03/19 | f) | - | b) | 500,000.00 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | 03/03/19 | g) | - | c) | 287,680.00
[7 empty] | d) | - | d) | -
|  | 1.6 | Construction of BSP Building Extension | Bldg. |  | Admin | a) | 500,000.00 | a) | - | e) | - | a) | 500,000.00 | a) | - | c) | - | a) | - | Target Date started: January 3, 2019
|  |  | Mankilam, Tagum City |  |  |  | b) | - | b) | - | f) | - | b) | 500,000.00 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | 293,312.00
[7 empty] | d) | - | d) | -
|  | 2. Rural Electrification (Provincewide) |  | Elect. |  | Admin | a) | 5000000 | [12 empty] | See projects listed below
[7 empty] | b) | Foronda/Misa
[7 empty] | c) | Admin
[7 empty] | d) | -
|  | 2.1 | Electrification of Purok 1-4, Sta. Cruz, | Elect. |  | Admin | a) | 2,500,000.00 | a) | 02/04/19 | e) | - | a) | 2,500,000.00 | a) | - | c) | - | a) | - | POW for approval
|  |  | New Corella |  |  |  | b) | - | b) | - | f) | - | b) | 2,500,000.00 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
| F. | SEF(Special Education Fund)-SUPPLEMENTAL BUDGET # 1 CY 2017
|  | 1. Const./Impv't./Compl. Of School Bldgs., Struc. & Fac. |  | Bldgs. |  | Admin | a) | 3,300,000.00 | [12 empty] | See projects listed below
[7 empty] | b) | Foronda
[7 empty] | c) | PEO
[7 empty] | d) | -
|  | 1.1 | Construction of 1 unit School Building | Bldg. |  | Admin | a) | 1100000 | a) | 02/19/18 | e) | - | a) | 1100000 | a) | - | c) | - | a) | - | For implementation
|  |  | Lumabag, Talaingod |  |  |  | b) | - | b) | - | f) | - | b) | 1100000 | b) | - | d) | - | b) | -
[7 empty] | c) | PEO | c) | - | g) | - | c) | 595230.5
[7 empty] | d) | - | d) | -
| G. | STIMULUS PROJECTS CY 2017
ASUNCION
|  | 1 | Construction of Water Reservoir & | Water |  | MEO | a) | 500000 | a) | 12/28/17 | e) | - | a) | 500000 | a) | 90.00% | c) | 90.00% | a) | - | On-going
|  |  | Purchase of P.E. Pipelines, Sagayen, | System |  |  | b) | - | b) | 11/15/18 | f) | - | b) | 500000 | b) | - | d) | - | b) | - | Fund already transferred at Municipality of Asuncion
|  |  | Asuncion |  |  |  | c) | MEO | c) | - | g) | - | c) | - | [6 empty] | with ChecK No. 2445174 and OR # 9238468,
[7 empty] | d) | - | d) | - | [10 empty] | dated March 16, 2018
NEW CORELLA
|  | 1 | Road Rehabilitation at Prk. 1-Prk. 5, | Road |  | MEO | a) | 500000 | a) | 11/29/17 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Fund already transferred at Municipality of New Corella with ChecK No. 2445213 and OR # 8592072, dated March 13, 2018
|  |  | Sta. Fe, New Corella |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | -
[7 empty] | c) | MEO | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
|  | 2 | Construction of Footbridge w/ Railings, | Footbridge |  | Barangay | a) | 500000 | a) | 01/24/18 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Fund already transferred at Municipality of New Corella with ChecK No. 2445200 and OR # 8592078, dated March 13, 2018
|  |  | Carcor, New Corella |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
|  | 3 | Construction of Concrete of Fence Lataban Elem. | Fence |  | Barangay | a) | 500000 | a) | 12/28/17 | e) | - | a) | 500000 | a) | 90% | c) | 90% | a) | - | On-going
|  |  | School, Del Monte, New Corella |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - | - Fund transferred at Municipality of New Corella
[7 empty] | c) | - | c) | - | g) | - | c) | - | [6 empty] | with ChecK No. 2445182 and OR # 8592074,
[7 empty] | d) | - | d) | - | [10 empty] | dated March 13, 2018
|  | 4 | Construction of 1 CL School Bldg., | Bldg. |  | Barangay | a) | 500000 | a) | 12/28/17 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Fund already transferred at Municipality of New Corella with ChecK No. 2445183 and OR # 8592077, dated March 13, 2018
|  |  | Mambing, New Corella |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
TAGUM CITY
|  | 1 | Construction of Multi-Purpose GYM at | Bldg. |  | - | a) | 500000 | a) | 11/29/17 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Hold in abeyance
|  |  | Mangga E/S, Visayan Village, Tagum City |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
|  | 2 | Const. of 1 Bay Span Covered Court, | Court |  | Contract | a) | 500000 | a) | 06/05/18 | e) | - | a) | 500000 | a) | 100.00% | c) | 0% | a) | -
|  |  | Brgy. La Filipina, Tagum City |  |  |  | b) | Obero | b) | 12/10/18 | f) | - | b) | 500000 | b) | - | d) | - | b) | -
[7 empty] | c) | FT Const. | c) | 01/29/19 | g) | - | c) | -
[7 empty] | d) | - | d) | -
KAPALONG
|  | 1 | Impv't. of Brgy. Hall, Sua-on, Kapalong | Bldg. |  | - | a) | 500000 | a) | 02/13/18 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Hold in abeyance
[7 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[6 empty] | p | d) | - | d) | -
|  | 2 | Construction of Solar Drier, Semong, | Solar |  | - | a) | 500,000.00 | a) | 12/28/17 | e) | - | a) | 500,000.00 | a) | - | c) | - | a) | - | Hold in abeyance
|  |  | Kapalong | Drier |  |  | b) | - | b) | - | f) | - | b) | 500,000.00 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
|  | 3 | Construction of Multi-Purpose Pavement, | MPP |  | - | a) | 500000 | a) | 12/28/17 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Hold in abeyance
|  |  | Florida, Kapalong |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
|  | 4 | Construction of Concrete Bleacher, | Bleacher |  | - | a) | 500000 | a) | 12/07/17 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Hold in abeyance
|  |  | Tiburcia, Kapalong |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
|  | 5 | Mainline Pipes for PWS, Mabantao, | Water |  | - | a) | 500000 | a) | 12/07/17 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Hold in abeyance
|  |  | kapalong | System |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
|  | 6 | Impv't. of Covered Court, Pag-Asa, | Court |  | - | a) | 500000 | a) | 12/07/17 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Hold in abeyance
|  |  | Kapalong |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
|  | 7 | Covered Court Bleacher, Katipunan, | Bleacher |  | - | a) | 500000 | a) | 12/07/17 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Hold in abeyance
|  |  | Kapalong |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
|  | 8 | Improvement of Gabuyan Covered Court, | Court |  | Admin | a) | 500000 | a) | 12/07/17 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Impelemenation by Administartion
|  |  | Brgy. Gabuyan, Kapalong |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | -
[7 empty] | c) | PEO | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
TALAINGOD
|  | 1 | Electrification @ Prk. 1A-Prk. 5A, Palma Gil, | Elect. |  | Barangay | a) | 500000 | a) | 12/28/17 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Fund already transferred at Municipality of Talaingod with ChecK No. 2445181 and OR # 7955667, dated March 16, 2018
|  |  | Talaingod |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | -
[7 empty] | c) |  | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
| H. | Trust Fund
1. CMGP (Conditional Matching Grant to Provinces)
|  | 1.1 | Road Upgrading km.9 sagayen-Sawata | Road | 10.20 km | Contract | a) | 139,761,975.14 | a) | CY 2017 | e) | - | a) | 139,761,975.14 | a) | 5.569% | c) | 16.341% | a) | - | On-going
|  |  | (Sagayen-Jct. San Miguel Section) |  |  |  | b) | Avila | b) | 10/01/18 | f) | - | b) | 139,761,975.14 | b) | - | d) | +10.77% | b) | -
[7 empty] | c) | Legacy Const. Corp. | c) | 08/22/19 | g) | - | c) | -
[7 empty] | d) | 326 CD | d) | -
|  | 1.2 | Road Upgrading of Dagohoy - Daligdigon | Road | 2.532 km | Admin | a) | 58048310.68 | a) | CY 2017 | e) | - | a) | 58048310.68 | a) | 63.122% | c) | 49.257% | a) | - | On-going
|  |  | Provincial Road |  |  |  | b) | Fabiala | b) | 01/05/18 | f) | 160 CD | b) | 58048310.68 | b) | - | d) | -13.87% | b) | -
[7 empty] | c) | PUREGOLD | c) | 11/18/18 | g) | - | c) | 8707246.6
[7 empty] | d) | 246 CD | d) | -
| I. | 2. OPPAP-PAMANA
|  | 2.1 | Const. of Trading Post, Storage Building | Bldg. |  | Contract | a) | 3,975,000.00 | a) | CY 2017 | e) | - | a) | 3,975,000.00 | a) | - | c) | - | a) | - | Validaion of TWG on process
|  |  | with (1) unit Hauling Truck, Brgy. Pandapan |  |  |  | b) | - | b) | - | f) | - | b) | 3,975,000.00 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
| J. | LDRRM - Trust Fund
|  | 1. Construction of Slope Protection and Concrete Pavement along Sta. Fe Mambing Road Section |  | Slope |  |  | a) | 1,853,000.00 | a) | 11/28/18 | e) | - | a) | 1,853,000.00 | a) | 14.76% | c) | 7.50% | a) | - | On-going
[7 empty] | b) | Gone | b) | 12/03/18 | f) | - | b) | 1,853,000.00 | b) | - | d) | -7.26% | b) | -
[7 empty] | c) | - | c) | 02/28/19 | g) | - | c) | 616,617.50
[7 empty] | d) | - | d) | -
|  | 2. Rehab. Of Saug Bridge of Slope Protection |  | Slope |  |  | a) | 4,850,000.00 | a) | 11/28/18 | e) | - | a) | 4,850,000.00 | a) | 23.60% | c) | 9.60% |  |  | On-going
[7 empty] | b) | Gone | b) | 01/03/19 | f) | - | b) | 4,850,000.00 | b) |  | d) | -14%
[7 empty] | c) | - | c) | 03/25/19 | g) | - | c) | 747,581.00
[7 empty] | d) | - | d) | -
|  | 3. Rehab. Of Canatan Bridge Slope Protection |  | Slope |  |  | a) | 9,200,000.00 | a) | - | e) | - | a) | 9,200,000.00 | a) |  | c) |  |  |  | For implementation
|  | Brgy. Canatan, Asuncion |  |  |  |  | b) | - | b) | - | f) | - | b) | - | b) |  | d)
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
|  | 4. Re-channeling of BIGA River with Earth Dike and Slope Protection, Brgy. Gupitan,, Kaplaong |  | Dike/Slope |  |  | a) | 12,100,000.00 | a) | - | e) | - | a) | 12,100,000.00 | a) |  | c) |  |  |  | Target Date Starget: 01/07/19
[7 empty] | b) | - | b) | - | f) | - | b) | - | b) |  | d)
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
|  | 5. Const. of Cabidianan Bridge Slope Protection, Brgy. Cabidianan, New Corella |  | Slope |  |  | a) | 3590000 | a) | - | e) | - | a) | 3590000 | a) |  | c) |  |  |  | For implementation
[7 empty] | b) | - | b) | - | f) | - | b) | - | b) |  | d)
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
K. 20% Development Fund CY 2018
|  | 1. Various of Water System Project (Provincewide) |  | Water | - | Admin | a) | 10000000 | [12 empty] | Investigation/Inspection of priority projects
|  |  |  | System |  |  | b) | Foronda/Misa
[7 empty] | c) | Admin
[7 empty] | d) | -
|  | 1.1 | Conduct of geo-resistivity/drilling test | Geo- |  | Admin | a) | 250000 | [12 empty] | See list of projects
|  |  | of proposed site | resistivity |  |  | b) | Diosanta
[7 empty] | c) | Admin
[7 empty] | d) | -
|  |  | a. Const. of PWS Linao, San Isidro | Water |  | Admin | a) | 62000 | a) | - | e) | - | a) | 62000 | a) | - | c) | - | a) | - | Waiting for the geo-resistivty equipment.
|  |  |  | System |  |  | b) | - | b) | - | f) | - | b) | 62000 | b) | - | d) | - | b) | - | (Geo-resistivity equipment PR on process)
[7 empty] | c) | Admin | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
|  |  | b. Const. of PWS Mamalian, San Isidro | Water |  | Admin | a) | 62000 | a) | - | e) | - | a) | 62000 | a) | - | c) | - | a) | - | Waiting for the geo-resistivty equipment.
|  |  |  | System |  |  | b) | - | b) | - | f) | - | b) | 62000 | b) | - | d) | - | b) | - | (Geo-resistivty equipment PR on process)
[7 empty] | c) | Admin | c) | - | g) | - | c) | - | [7 empty] | Impv't. of K. 9 Sagayen-Sawata Prov'l. Rd. P 1,442,028.81
[7 empty] | d) | - | d) | -
|  |  | c. Const. of PWS Sagayen, San Isidro | Water |  | Admin | a) | 62000 | a) | - | e) | - | a) | 62000 | a) | - | c) | - | a) | - | Waiting for the geo-resistivty equipment.
|  |  |  | System |  |  | b) | - | b) | - | f) | - | b) | 62000 | b) | - | d) | - | b) | - | (Geo-resistivty equipment PR on process)
[7 empty] | c) | Admin | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
|  | 1.2 | Construction of Water System Projects | Geo- |  | Admin | a) | 9750000 | [12 empty] | See list of projects
|  |  | in Component LGUs | resistivity |  |  | b) | Diosanta
[7 empty] | c) | Admin
[7 empty] | d) | -
|  |  | a. Installation of water System at Purok | Water |  | Admin | a) |  | a) | - | e) | - | a) |  | a) | - | c) | - | a) | - | For ammendment due to change of location.Waiting for deed of donation.
|  |  | Nangka, Pandapan, Tagum City | System |  |  | b) | - | b) | - | f) | - | b) |  | b) | - | d) | - | b) | -
[7 empty] | c) | Admin | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
|  |  | b. Rehab./Impv't. of San Vicente | Water |  | Admin | a) | 1125000 | a) | 10/26/18 | e) | - | a) | 1125000 | a) | - | c) | - | a) | - | PR on process
|  |  | Water System, Asuncion | System |  |  | b) | - | b) | - | f) | - | b) | 1125000 | b) | - | d) | - | b) | -
[7 empty] | c) | Admin | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
|  | 2. Counterpart to Special Projects (Provincewide) |  | Road | - | Contract | a) | 67415000 | [12 empty] | Investigation/Inspection of priority projects
[7 empty] | b) | Foronda
[7 empty] | c) | Admin
[7 empty] | d) | -
|  | 2.1 | Rehab. Of Sonlon-Camansa FMR, | Road | - | Contract | a) | 20,104,388.55 | a) | 09/18/18 | e) | - | a) | 20,104,388.55 | a) | - | c) | - | a) | - | NOL 1 approved dated June 29, 2018
|  |  | Asuncion, Davao del Norte |  |  |  | b) | - | b) | - | f) | - | b) | 20,104,388.55 | b) | - | d) | - | b) | - | Pre-procurement dated July 26, 2018
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) |  | d) | -
|  | 3. Const./Rehab./Comp. of Various Gov't. Bldgs. |  | Bldgs. | - | Admin | a) | 13523124 | [12 empty] | Investigation/Inspection of priority projects
|  | Struct., Fac. (Provincewide) |  |  |  |  | b) | Foronda
[7 empty] | c) | Admin
[7 empty] | d) | -
|  | 3.1 | Rehab. Of PEO Training Center | Bldg. |  | Admin | a) | 326124 | a) | 02/12/19 | e) | - | a) | 326124 | a) | - | c) | - | a) | - | PR on process (18062709)
|  |  | (PDPM),Mankilam, Tagum City |  |  |  | b) | - | b) | - | f) | - | b) |  | b) | - | d) | - | b) | - | PO on process ( 2018082440, 2018082449, 2018082437,
|  |  | (Part of P803,000.00)(20% DF CY 2017-P476,876.00) |  |  |  | c) | Admin | c) | - | g) | - | c) | - | [6 empty] | 2018082455)
[7 empty] | d) | - | d) | -
|  | 3.2 | Construction of IP Tribal Council of | Bldg. |  | Admin | a) | 560,000.00 | a) | - | e) | - | a) | 560,000.00 | a) | - | c) | - | a) | - | POW & Plan for approval
|  |  | Women at Brgy. Camansa, Asuncion |  |  |  | b) | - | b) | - | f) | - | b) | 560,000.00 | b) | - | d) | - | b) | -
[7 empty] | c) | Admin | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
|  | 3.3 | Construction of Multi-Purpose Bldg. | Bldg. |  | Admin | a) | 6748000 | a) | 12/11/18 | e) | - | a) | 6748000 | a) | 16.17% | c) | 20.17% | a) | - | On-going
|  |  | (PENRO Building), Mankilam, Tagum City |  |  |  | b) | Pasiona | b) | 10/16/18 | f) | - | b) | 6748000 | b) | - | d) | +4.00% | b) | -
|  |  | (Part of 8,548,000.00) |  |  |  | c) | Admin | c) | 05/25/19 | g) | - | c) | 4466245.41
|  |  | (P1,800,000.00 - SB#3 CY 2017) |  |  |  | d) | PEO | d) | -
|  | 4. Rural Electrification (Provincewide) |  | Elect. |  | Admin | a) | 5000000 | [12 empty] | See projects listed below
[7 empty] | b) | Foronda/Misa
[7 empty] | c) | Admin
[7 empty] | d) | -
|  | 4.1 | Rural Electrification at Del Monte, | Elect. |  | Admin | a) | 1000000 | a) | - | e) | - | a) | 1000000 | a) | - | c) | - | a) | - | POW for approval
|  |  | New Corella |  |  |  | b) | - | b) | - | f) | - | b) | 1000000 | b) | - | d) | - | b) | -
[7 empty] | c) | Admin | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
|  | 4.2 | Const. of Distribution Line in Sitio Prk. 1,3,4, | Elect. |  | Admin | a) | 4000000 | a) | 11/06/18 | e) | - | a) | 4000000 | a) | - | c) | - | a) | - | POW for approval
|  |  | 11 and 7, Camansa, asuncion |  |  |  | b) | - | b) | - | f) | - | b) | 4000000 | b) | - | d) | - | b) | -
[7 empty] | c) | Admin | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
A. 20% Development Fund CY 2018 | L. | GENERAL FUND PROPER CY 2018
STIMULUS PROJECTS
ASUNCION
|  | 1 | Const. of Bleachers and Canopy, | Bldg. |  | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Hold in abeyance
|  |  | Canantan, Asuncion |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
|  | 2 | Const. of Potable water System at Prk. 6, | Water |  | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Hold in abeyance
|  |  | New Santiago, Asuncion | System |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
|  | 3 | Const. of Canopy, Camoning, Asuncion | Bldg. |  | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Hold in abeyance
[7 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
|  | 4 | Completion of Electrification at Prk. 10 | Elect. |  | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Hold in abeyance
|  |  | & Prk. 9, Doña Andrea, Asuncion |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
|  | 5 | Construction of Covered Court, | Court |  | - | a) | 500000 | a) | 06/05/18 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Hold in abeyance
|  |  | San Vicente, Asuncion |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
|  | 6 | Landscaping and Beautification of | landscaping |  | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Hold in abeyance
|  |  | Brgy. Ground, Pamacaun, Asuncion |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
NEW CORELLA
|  | 1 | Const. of Concrete Bleachers, Sta. Cruz, | Bleacher |  | - | a) | 500000 | a) | 06/04/18 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Hold in abeyance
|  |  | New Corella |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
|  | 2 | Completion of Mini GYM at Prk. 2, | GYM |  | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Hold in abeyance
|  |  | San Roque, New Corella |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
|  | 3 | Completion of Covered Court, Sto. Niño, | Court |  | - | a) | 500000 | a) |  | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Hold in abeyance
|  |  | New Corella |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
|  | 4 | Construction of Public Market, Suawon, | Bldg. |  | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Hold in abeyance
|  |  | New Corella |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
|  | 5 | Construction of Concrete Line Drainage at | Drainage |  | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Hold in abeyance
|  |  | Prk. 10 to Prk. 6, Del Pilar, New Corella |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
|  | 6 | Construction of Stage with Comfort Rooms | Bldg. |  | - | a) | 500000 | a) | 07/05/18 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Hold in abeyance
|  |  | at Mesaoy Mini-Gym, Mesaoy, New Corella |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
TAGUM CITY
|  | 1 | Repair of Brgy. Hall, San Miguel, | Bldg. |  | Admin | a) | 500000 | a) | 10/26/18 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For implementation
|  |  | Tagum City |  |  |  | b) | Juan | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
|  | 2 | Completion of Two Storey Multi-Purpose | Bldg. |  | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Hold in abeyance
|  |  | Building, Magugpo East, Tagum City |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
|  | 3 | Completion of GYM Bleacher w/ | Bleacher |  | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Hold in abeyance
|  |  | Electrification, Pagsabangan, Tagum City |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
|  | 4 | Construction of Drainage Canal, | Drainage |  | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Hold in abeyance
|  |  | Libuganon, Tagum City |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
KAPALONG
|  | 1 | Construction of Bleacher, Mamacao, | Bleacher |  | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Hold in abeyance
|  |  | Kapalong |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
|  | 2 | Improvement of Capungagan GYM Stage, | Stage |  | - | a) | 500000 | a) | 06/05/18 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Hold in abeyance
|  |  | Capungagan, Kapalong |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
|  | 3 | Construction of Concrete Perimeter Fence, | Fence |  | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Hold in abeyance
|  |  | Luna, Kapalaong |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
|  | 4 | Construction of 1 Unit 2 Classroom | Bldg. |  | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Hold in abeyance
|  |  | School Bldg. at Sampao, kapalong |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
|  | 5 | Completion of Brgy. Health Center, Maniki, | Bldg. |  | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Hold in abeyance
|  |  | Kapalong |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
SAN ISIDRO
|  | 1 | Improvement of Water System, Sabangan, | Water |  | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Hold in abeyance
|  |  | San Isidro | System |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
|  | 2 | Rehabilitation & Flooring of Gymnasium | Court |  | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Hold in abeyance
|  |  | Basketball Court, Mamangan, San Isidro |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
TALAINGOD
|  | 1 | Grouted Riprap on Embankment | Riprap |  | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Hold in abeyance
|  |  | Sto. Ñino, Talaingod |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
|  | 2 | Barangay Hall Improvement, Dagohoy, | Bldg. |  | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Hold in abeyance
|  |  | Talaingod |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
| M. | 5% Calamity Fund CY 2018
1. Prevention and Mitigation
|  | 1.1 Desiltation/Excavation of rivers and creeks |  | rivers |  | Admin | a) | 3000000 | [12 empty] | Investigation/Inspection of priority projects
[7 empty] | b) | -
[7 empty] | c) | PEO
[7 empty] | d) | -
|  | a. | Impv't. and Desiltation of Tagum Creek Ph.I | Creek |  | Admin | a) | 500,000.00 | a) | 11/06/18 | e) | - | a) | 500,000.00 | a) | - | c) | - | a) | - | For implementation
[7 empty] | b) | - | b) | - | f) | - | b) |  | b) | - | d) | - | b) | -
[7 empty] | c) | PEO | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
|  | b. | Impv't. and Desiltation of Tagum Creek Ph.II | Creek |  | Admin | a) | 1,500,000.00 | a) | - | e) | - | a) | 1,500,000.00 | a) | - | c) | - | a) | - | POW & Plan for approval
[7 empty] | b) | - | b) | - | f) | - | b) |  | b) | - | d) | - | b) | -
[7 empty] | c) | PEO | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
|  | 1.2 Improvement of Roads, Drainage & Canals |  | roads/canals |  | Admin | a) | 3000000 | [12 empty] | Investigation/Inspection of priority projects
[7 empty] | b) | -
[7 empty] | c) | PEO
[7 empty] | d) | -
|  | a. | Rehab./Impv't. of Sonlon-Longanapan Road | road |  | Admin | a) | 1,500,000.00 | a) | - | e) | - | a) | 1,500,000.00 | a) | - | c) | - | a) | - | For preparation of POW & Plan
[7 empty] | b) | - | b) | - | f) | - | b) | 1,500,000.00 | b) | - | d) | - | b) | -
[7 empty] | c) | PEO | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
|  | 1.3 Improvement of bridges and cross drainage |  | bridges/drainage |  | Admin | a) | 3000000 | [12 empty] | Investigation/Inspection of priority projects
[7 empty] | b) | -
[7 empty] | c) | PEO
[7 empty] | d) | -
|  | 2. Rehabilitation and Recovery |  | roads |  | Admin | a) | 2026000 | [12 empty] | Investigation/Inspection of priority projects
[7 empty] | b) | -
[7 empty] | c) | PEO
[7 empty] | d) | -
| N. | SUPPLEMENTAL BUDGET # 1 CY 2018 |  |  |  |  | a) | 6,000,000.00 | [12 empty] | See list of Provincial Roads
|  | 1 Const. in Progress - Infrastructure |  |  |  |  | b) | Paraguya
|  | Assets (Rehabilitation of Various |  |  |  |  | c) | PEO
|  | Provincial Roads) |  |  |  |  | d) | -
|  | 1 | Mesaoy - Jct. Mahayahay | Road |  | Admin | a) | 1,534,000.00 | a) | 07/19/18 | e) | - | a) | 1,534,000.00 | a) | 60% | c) | 60% | a) | - | Suspended as of Dec. 27, 2018
[7 empty] | b) | - | b) | 11/16/18 | f) | - | b) | 1,534,000.00 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | 12/15/18 | g) | - | c) | -
[7 empty] | d) | - | d) | -
|  | 2 | Del Pilar - Jct. Silangan | Road |  | Admin | a) | 1,795,000.00 | a) | 07/19/18 | e) | - | a) | 1,795,000.00 | a) | 73.00% | c) | 73.00% | a) | 14 | On-going
[7 empty] | b) | Salido | b) | 10/16/18 | f) | - | b) | 1,795,000.00 | b) | - | d) | - | b) | 30 | Suspended as of January 4, 2019
[7 empty] | c) | PEO | c) | 11/20/19 | g) | - | c) | -
[7 empty] | d) | - | d) | -
|  | 3 | New Corella - New Sambog - Silangan | Road |  | Admin | a) | 2,095,000.00 | a) | 07/19/18 | e) | - | a) | 2,095,000.00 | a) | 80.00% | c) | 80.00% | a) | - | On-going
[7 empty] | b) | Salido | b) | 10/08/18 | f) | - | b) | 2,095,000.00 | b) | - | d) | - | b) | - | Suspended as of January 4, 2019
[7 empty] | c) | PEO | c) | 11/07/19 | g) | - | c) | -
[7 empty] | d) | - | d) | -
| O. | SUPPLEMENTAL BUDGET # 2 CY 2018
1 Const./Compl./Impv't. of Various Gov't.
Bldgs., Structures & Facilities (Const. in
Progress - Bldgs. & Other Structures
|  | 1 | Const./Impv't. of DDN Hospital | Bldg. |  | - | a) | 5,000,000.00 | a) | - | e) | - | a) | 5,000,000.00 | a) | - | c) | - | a) | - | Preparation of POW & Plan c/o PDPM
|  |  | Kapalong Zone |  |  |  | b) | - | b) | - | f) | - | b) | 5,000,000.00 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
|  | 2 | Compl. Of Bahay Pag-Asa for Minors, | Bldg. |  | - | a) | 3,000,000.00 | a) | - | e) | - | a) | 3,000,000.00 | a) | - | c) | - | a) | - | Preparation of POW & Plan c/o PDPM
|  |  | New Corella |  |  |  | b) | - | b) | - | f) | - | b) | 3,000,000.00 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
|  | 3 | Const/Compl. Of Fence at bahay pag-Asa | Fence |  | - | a) | 2,500,000.00 | a) | 12/18/18 | e) | - | a) | 2,500,000.00 | a) | 21.50% | c) | 14.23% | a) | 15 | On-going | x
|  |  | for Minors |  |  |  | b) | Gone | b) | 01/19/19 | f) | - | b) | 2,500,000.00 | b) | - | d) | -7.27% | b) | 120
[7 empty] | c) | Admin | c) | 03/06/19 | g) | - | c) | -
[7 empty] | d) | - | d) | -
|  | 4 | Upgrading of DAGOEMC Multi-Purpose | Bldg. |  | - | a) | 3,000,000.00 | a) | 09/04/18 | e) | - | a) | 3,000,000.00 | a) | - | c) | - | a) | - | Preparation of POW & Plan c/o PDPM
|  |  | Bldg., Mankilam |  |  |  | b) | - | b) | - | f) | - | b) | 3,000,000.00 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
|  | 5 | Const. of Add'l. 2nd Level Multi-Purpose | Bldg. |  | - | a) | 7,592,588.00 | a) | - | e) | - | a) | 7,592,588.00 | a) | - | c) | - | a) | - | Preparation of POW & Plan c/o PDPM
|  |  | HalI, PGSO warehouse,Bldg., Mankilam |  |  |  | b) | - | b) | - | f) | - | b) | 7,592,588.00 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
|  | 6 | Const. of 1 Unit Triball Hall, Brgy. Carcor, | Bldg. |  | - | a) | 680,000.00 | a) | - | e) | - | a) | 680,000.00 | a) | - | c) | - | a) | - | Preparation of POW & Plan c/o PDPM
|  |  | New Corella |  |  |  | b) | - | b) | - | f) | - | b) | 680,000.00 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
2 Infastructure Augmentation Project (Provincial Counterpart for PRDP Project)
|  | 1 | Rehab. Of Capungagan-Bdy. San Miguel FMR (Variation Order) | Road |  | Admin | a) | 4,990,000.000 | a) | 07/20/18 | e) | - | a) | 4,990,000.000 | a) | 91.57% | c) | 84.84% | a) | 10 | On-going
[7 empty] | b) | Avila | b) | 08/23/18 | f) | 40 CD | b) | 4,990,000.000 | b) | - | d) | -6.73% | b) | 90
[7 empty] | c) | PEO | c) | 01/13/19 | g) | - | c) | 3,575,631.72
[7 empty] | d) | 134 CD | d) | -
| P. | SUPPLEMENTAL BUDGET # 4 CY 2018
|  | 1 | Construction of Multi-Purpose Bldg. (PENRO Building) | Bldg. |  | Admin | a) | 7,000,000.00 | a) | 06/11/18 | e) | - | a) | 7,000,000.00 | a) | 19.85% | c) | 19.85% | a) | - | On-going
[7 empty] | b) | Pasiona | b) | 10/16/18 | f) | - | b) | 7,000,000.00 | b) | - | d) | - | b) | -
|  |  | (Part of P8,548,000.00)(P1,800,000.00 - |  |  |  | c) | Admin | c) | 05/25/19 | g) | - | c) | -
|  |  | SB # 4 CY 2018) |  |  |  | d) | - | d) | -
| Q. | OPPAP-PAMANA
1. TRIBAL HALLS
|  | 1.1 | Construction of Tribal Hall, Brgy. Gupitan, | Bldg. |  | Admin | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For NTP
|  |  | Kapalong |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
2. PROCESSING AND BAGSAKAN CENTER
|  | 2.1 | Const. of Processing and Bagsakan Center, | Bldg. |  | Contract | a) | 2500000 | a) | - | e) | - | a) | 2500000 | a) | - | c) | - | a) | - | Notice of award on process
|  |  | Brgy. Palma Gil, Talaingod |  |  |  | b) | - | b) | - | f) | - | b) | 2500000 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) |  | d) | -
|  | 2.2 | Const. of Processing and Bagsakan Center, | Bldg. |  | Contract | a) | 2500000 | a) | - | e) | - | a) | 2500000 | a) | - | c) | - | a) | - | Procurement on process
|  |  | Brgy. Sto. Nino, Talaingod |  |  |  | b) | - | b) | - | f) | - | b) | 2500000 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
|  | 2.3 | Const. of Processing and Bagsakan Center, | Bldg. |  | Contract | a) | 2500000 | a) | - | e) | - | a) | 2500000 | a) | - | c) | - | a) | - | Notice of award on process
|  |  | Brgy. Dagohoy, Talaingod |  |  |  | b) | - | b) | - | f) | - | b) | 2500000 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
|  | 2.4 | Const. of Processing and Bagsakan Center, | Bldg. |  | Contract | a) | 2500000 | a) | - | e) | - | a) | 2500000 | a) | - | c) | - | a) | - | Procurement on process
|  |  | Brgy. Gupitan, Kapalong, Davao del Norte |  |  |  | b) | - | b) | - | f) | - | b) | 2500000 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
3. SOLAR DRYER
|  | 3.1 | Post Harvest Facilities (Corn Mill, Solar Dryer, | Bldg. |  | Contract | a) | 1500000 | a) | - | e) | - | a) | 1500000 | a) | - | c) | - | a) | - | For PR
|  |  | Corn Sheller), Kapalong, Davao del Norte |  |  |  | b) | - | b) | - | f) | - | b) | 1500000 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
|  | 3.2 | Post Harvest Facilities (Corn Mill, Solar Dryer, Corn Sheller), Talaingod, Davao del Norte | Bldg. |  | Contract | a) | 500,000.00 | a) | - | e) | - | a) | 500,000.00 | a) | - | c) | - | a) | - | Procurement on process
[7 empty] | b) | - | b) | - | f) | - | b) | 500,000.00 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
4. TRADING POST STORAGE
|  | 4.1 | Trading Post, Storage and Hauling Truck, Pandapan, Tagum City | Bldg. |  | Contract | a) | 4000000 | a) | - | e) | - | a) | 4000000 | a) | - | c) | - | a) | - | Validation for TWG on-going
[7 empty] | b) | - | b) | - | f) | - | b) | 4000000 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
5. WATER SYSTEM
|  | 5.1 | Construction of PWS Level II in Sitio Upper Dulyan, Palma Gil, Talaingod, DDN | PWS |  | Admin | a) | 1000000 | a) | - | e) | - | a) | 1000000 | a) | - | c) | - | a) | - | PO on process
[7 empty] | b) | - | b) | - | f) |  | b) | 1000000 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
|  | 5.2 | Construction of PWS Level II in Purok 1, Dagohoy, Talaingod, | PWS |  | Admin | a) | 1000000 | a) | - | e) | - | a) | 1000000 | a) | - | c) | - | a) | - | PO on process
[7 empty] | b) | - | b) | - | f) | - | b) | 1000000 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
|  | 5.3 | Construction of PWS Level II in Purok JBL and Salawao, Santo Niño, Talaingod | PWS |  | Admin | a) | 1000000 | a) | - | e) | - | a) | 1000000 | a) | - | c) | - | a) | - | PO on process
[7 empty] | b) | - | b) | - | f) | - | b) | 1000000 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
|  | 5.4 | Construction of PWS Level II in Sitio Sambayon, Suaon, Kapalong | PWS |  | Admin | a) | 1000000 | a) | - | e) | - | a) | 1000000 | a) | 9.10% | c) | 9.80% | a) | - | On-going
[7 empty] | b) | Diosanta | b) | 11/16/18 | f) | - | b) | 1000000 | b) | - | d) | +0.70% | b) | -
[7 empty] | c) | PEO | c) | 01/24/18 | g) | - | c) | -
[7 empty] | d) | 70 CD | d) | -
|  | 5.5 | Upgrading of Existing PWS Level II in Sitio Langan, Gupitan, Kapalong | PWS |  | Admin | a) | 2500000 | a) | - | e) | - | a) | 2500000 | a) | - | c) | - | a) | - | PO on process
[7 empty] | b) | - | b) | - | f) | - | b) | 2500000 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
|  | 5.6 | Upgrading of Existing PWS Level II in Sitio Patel 2, Gupitan, Kapalong | PWS |  | Admin | a) | 2500000 | a) | - | e) | - | a) | 2500000 | a) | - | c) | - | a) | - | PO on process
[7 empty] | b) | - | b) | - | f) | - | b) | 2500000 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
|  | 5.7 | Construction of PWS Level II in Purok 7-A and 7-B, Capungagan, Kapalong | PWS |  | Admin | a) | 1000000 | a) | 11/12/18 | e) | - | a) | 1000000 | a) | - | c) | - | a) | - | PO on process
[7 empty] | b) | - | b) | - | f) | - | b) | 1000000 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
|  | 5.8 | Construction of PWS Level II in Purok 2, Pag-asa, Kapalong | PWS |  | Admin | a) | 1000000 | a) | 11/12/18 | e) | - | a) | 1000000 | a) | - | c) | - | a) | - | PO on process
[7 empty] | b) | - | b) | - | f) | - | b) | 1000000 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
|  | 5.9 | Rice Mill for Upland Rice, Kapalong, Davao del Norte | Bldg. |  | Admin | a) | 1000000 | a) | - | e) | - | a) | 1000000 | a) | - | c) | - | a) | - | Procurement on process
[7 empty] | b) | - | b) | - | f) | - | b) | 1000000 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
|  | 5.1 | Rice Mill for Upland Rice, Talaingod, Davao del Norte | Bldg. |  | Admin | a) | 1000000 | a) | - | e) | - | a) | 1000000 | a) | - | c) | - | a) | - | Procurement on process
[7 empty] | b) | - | b) | - | f) | - | b) | 1000000 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
6. CATTLE PRODUCTION
|  | 6.1 | Cattle Production- Brgy. Tiburcia, Gupitan and Semong, Kapalong | Bldg. |  | Admin | a) | 1500000 | a) | - | e) | - | a) | 1500000 | a) | - | c) | - | a) | - | Procurement on process
[7 empty] | b) | - | b) | - | f) | - | b) | 1500000 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
|  | 6.2 | Cattle Production, Brgy. Palma Gil, Brgy. Sto. Nino, Brgy. Dagohoy, Talaingod, Davao del Norte | Bldg. |  | Admin | a) | 1500000 | a) | - | e) | - | a) | 1500000 | a) | - | c) | - | a) | - | Procurement on process
[7 empty] | b) | - | b) | - | f) | - | b) | 1500000 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
| R. | LOCAL GOVERNMENT SUPPORT FUND (LGSF) CY 2018
|  | 1 | Road Upgrading of San Vicente - Butay Provincial Road | Road |  | Contract | a) | 19949581.18 | a) | CY 2018 | e) | - | a) | 19949581.18 | a) | 18.34% | c) | 15.77% | a) | 10 | On-going
[7 empty] | b) | Aclaracion | b) | 11/19/18 | f) | - | b) | 19949581.18 | b) | - | d) | - | b) | -
[7 empty] | c) | Alpha & Omega | c) | 06/08/19 | g) | - | c) | -
[7 empty] | d) | 202 CD | d) | -
II. PROJECTS UNDER THE CURRENT APPROPRIATION
A. Maintenance and Othe Operating Expenses(MOOE) CY 2019 |  |  |  | Road Maintenance | KM | MBA/CBRMC | a) | 18127866 | a) | 01/03/19 | e) | - | a) | 18127866 | a) | 1.99% | c) | 1.99% | a) | 46 | See list of Provincial Roads
Road ID |  | 1. Maintenance Of Various Prov'l. Roads and Bridges |  |  | 288.26 |  | b) | Paraguya | b) | 01/03/19 | f) | - | b) | 18127866 | b) | - | d) | - | b) | 920
[7 empty] | c) | PEO/CBRMC | c) | 12/31/19 | g) | - | c) | -
11DAN | [8 empty] | d) | -
[7 empty] | d) | 261 days | d) | -
|  | Jct. Highway Magatos - New Bantayan |  | Road Maintenance | 7.1 | MBA | a) | 287307.39 | a) | 01/03/19 | e) | - | a) | 287307.39 | a) | 12.31% | c) | 12.31% | a) | -
001 | [6 empty] | b) | Crucio | b) | - | f) | - | b) | 287307.39 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
|  | Jct. Highway Magatos - New Bantayan |  | Road Maintenance | 7.1 | CBRMC | a) | 223674.22 | a) | 01/03/19 | e) | - | a) | 223674.22 | a) | - | c) | - | a) | -
001 | [6 empty] | b) | Crucio | b) | - | f) | - | b) | 223674.22 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
|  | Magatos-Bdry Pagsabangan |  | Road Maintenance | 8.33 | MBA | a) | 328740.25 | a) | 01/03/19 | e) | - | a) | 328740.25 | a) | 11.95% | c) | 11.95% | a) | -
002 | [6 empty] | b) | Crucio | b) | - | f) | - | b) | 328740.25 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
|  | Magatos-Bdry Pagsabangan |  | Road Maintenance | 8.33 | CBRMC | a) | 270763.53 | a) | 01/03/19 | e) | - | a) | 270763.53 | a) | - | c) | - | a) | -
002 | [6 empty] | b) | Crucio | b) | - | f) | - | b) | 270763.53 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
|  | Ilog-New Bantayan |  | Road Maintenance | 2.68 | MBA | a) | 131131.39 | a) | 01/03/19 | e) | - | a) | 131131.39 | a) | 14.86% | c) | 16.86% | a) | -
003 | [6 empty] | b) | Crucio | b) | - | f) | - | b) | 131131.39 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
|  | Ilog-New Bantayan |  | Road Maintenance | 2.68 | CBRMC | a) | 65925.03 | a) | 01/03/19 | e) | - | a) | 65925.03 | a) | - | c) | - | a) | -
003 | [6 empty] | b) | Crucio | b) | - | f) | - | b) | 65925.03 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
|  | Asuncion -Monte Carlo-Del Pilar |  | Road Maintenance | 9.93 | MBA | a) | 474102.88 | a) | 01/03/19 | e) | - | a) | 474102.88 | a) | 10.31% | c) | 10.31% | a) | -
005 | [6 empty] | b) | Crucio | b) | - | f) | - | b) | 474102.88 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
|  | Asuncion -Monte Carlo-Del Pilar |  | Road Maintenance | 9.93 | CBRMC | a) | 355524.28 | a) | 01/03/19 | e) | - | a) | 355524.28 | a) | - | c) | - | a) | -
005 | [6 empty] | b) | Crucio | b) | - | f) | - | b) | 355524.28 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
|  | Jct. Highway Canatan-Jct. Highway Magatos |  | Road Maintenance | 4.85 | MBA | a) | 209808.59 | a) | 01/03/19 | e) | - | a) | 209808.59 | a) | - | c) | - | a) | -
006 | [6 empty] | b) | Crucio | b) | - | f) | - | b) | 209808.59 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
|  | Jct. Highway Canatan-Jct. Highway Magatos |  | Road Maintenance | 4.85 | CBRMC | a) | 162458.12 | a) | 01/03/19 | e) | - | a) | 162458.12 | a) | - | c) | - | a) | -
006 | [6 empty] | b) | Crucio | b) | - | f) | - | b) | 162458.12 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
|  | Sta. Felomina-San Roque |  | Road Maintenance | 7.68 | MBA | a) | 147439.63 | a) | 01/03/19 | e) | - | a) | 147439.63 | a) | 11.10% | c) | 11.10% | a) | -
008 | [6 empty] | b) | Crucio | b) | - | f) | - | b) | 147439.63 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
|  | Sta. Felomina-San Roque |  | Road Maintenance | 7.68 | CBRMC | a) | 261345.67 | a) | 01/03/19 | e) | - | a) | 261345.67 | a) | - | c) | - | a) | -
008 | [6 empty] | b) | Crucio | b) | - | f) | - | b) | 261345.67 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
|  | Saug-Sonlon-Bdy Longanapan |  | Road Maintenance | 11.6 | MBA | a) | 568486.36 | a) | 01/03/19 | e) | - | a) | 568486.36 | a) | 12.28% | c) | 12.28% | a) | -
010 | [6 empty] | b) | Crucio | b) | - | f) | - | b) | 568486.36 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
|  | Saug-Sonlon-Bdy Longanapan |  | Road Maintenance | 11.6 | CBRMC | a) | 185565.56 | a) | 01/03/19 | e) | - | a) | 185565.56 | a) | - | c) | - | a) | -
010 | [6 empty] | b) | Crucio | b) | - | f) | - | b) | 185565.56 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
|  | Jct. New Visayas-Buan |  | Road Maintenance | 2.99 | MBA | a) | 79238.27 | a) | 01/03/19 | e) | - | a) | 79238.27 | a) | - | c) | - | a) | -
011 | [6 empty] | b) | Crucio | b) | - | f) | - | b) | 79238.27 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
|  | Jct. New Visayas-Buan |  | Road Maintenance | 2.99 | CBRMC | a) | 101242.01 | a) | 01/03/19 | e) | - | a) | 101242.01 | a) | - | c) | - | a) | -
011 | [6 empty] | b) | Crucio | b) | - | f) | - | b) | 101242.01 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
|  | San Vicente - Butay |  | Road Maintenance | 7.52 | MBA | a) | 209624.2 | a) | 01/03/19 | e) | - | a) | 209624.2 | a) | - | c) | - | a) | -
013 | [6 empty] | b) | Crucio | b) | - | f) | - | b) | 209624.2 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
|  | San Vicente - Butay |  | Road Maintenance | 7.52 | CBRMC | a) | 227205.88 | a) | 01/03/19 | e) | - | a) | 227205.88 | a) | - | c) | - | a) | -
013 | [6 empty] | b) | Crucio | b) | - | f) | - | b) | 227205.88 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
|  | Jct. Highway Doña Andrea - Capungagan |  | Road Maintenance | 8.7 | MBA | a) | 230835.16 | a) | 01/03/19 | e) | - | a) | 230835.16 | a) | - | c) | - | a) | -
014 | [6 empty] | b) | Crucio | b) | - | f) | - | b) | 230835.16 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
|  | Jct. Highway Doña Andrea - Capungagan |  | Road Maintenance | 8.7 | CBRMC | a) | 294308.14 | a) | 01/03/19 | e) | - | a) | 294308.14 | a) | - | c) | - | a) | -
014 | [6 empty] | b) | Crucio | b) | - | f) | - | b) | 294308.14 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
|  | Semong-Palma Gil |  | Road Maintenance | 2.73 | MBA | a) | 147289.98 | a) | 01/03/19 | e) | - | a) | 147289.98 | a) | - | c) | - | a) | -
018 | [6 empty] | b) | Crucio | b) | - | f) | - | b) | 147289.98 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
|  | Semong-Palma Gil |  | Road Maintenance | 2.73 | CBRMC | a) | 49186.05 | a) | 01/03/19 | e) | - | a) | 49186.05 | a) | - | c) | - | a) | -
018 | [6 empty] | b) | Crucio | b) | - | f) | - | b) | 49186.05 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
|  | Daligdigon - Lumabag |  | Road Maintenance | 3.34 | MBA | a) | 148835.45 | a) | 01/03/19 | e) | - | a) | 148835.45 | a) | - | c) | - | a) | -
020 | [6 empty] | b) | Crucio | b) | - | f) | - | b) | 148835.45 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
|  | Daligdigon - Lumabag |  | Road Maintenance | 3.34 | CBRMC | a) | 68279.5 | a) | 01/03/19 | e) | - | a) | 68279.5 | a) | - | c) | - | a) | -
020 | [6 empty] | b) | Crucio | b) | - | f) | - | b) | 68279.5 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
|  | Jct. Sampao-Bdry. Mamacao |  | Road Maintenance | 4.98 | MBA | a) | 154200.78 | a) | 01/03/19 | e) | - | a) | 154200.78 | a) | - | c) | - | a) | -
025 | [6 empty] | b) | Crucio | b) | - | f) | - | b) | 154200.78 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
|  | Jct. Sampao-Bdry. Mamacao |  | Road Maintenance | 4.98 | CBRMC | a) | 169521.51 | a) | 01/03/19 | e) | - | a) | 169521.51 | a) | - | c) | - | a) | -
025 | [6 empty] | b) | Crucio | b) | - | f) | - | b) | 169521.51 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
|  | Jct. Highway Luna-Mamacao-Narra |  | Road Maintenance | 9.17 | MBA | a) | 357957.66 | a) | 01/03/19 | e) | - | a) | 357957.66 | a) | - | c) | - | a) | -
026 | [6 empty] | b) | Crucio | b) | - | f) | - | b) | 357957.66 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
|  | Jct. Highway Luna-Mamacao-Narra |  | Road Maintenance | 9.17 | CBRMC | a) | 313143.91 | a) | 01/03/19 | e) | - | a) | 313143.91 | a) | - | c) | - | a) | -
026 | [6 empty] | b) | Crucio | b) | - | f) | - | b) | 313143.91 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
|  | Jct. Gabuyan-Katipunan-Bucana |  | Road Maintenance | 5.89 | MBA | a) | 294403.23 | a) | 01/03/19 | e) | - | a) | 294403.23 | a) | - | c) | - | a) | -
027 | [6 empty] | b) | Crucio | b) | - | f) | - | b) | 294403.23 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
|  | Jct. Gabuyan-Katipunan-Bucana |  | Road Maintenance | 5.89 | CBRMC | a) | 129495.6 | a) | 01/03/19 | e) | - | a) | 129495.6 | a) | - | c) | - | a) | -
027 | [6 empty] | b) | Crucio | b) | - | f) | - | b) | 129495.6 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
|  | Capungagan-Mabuhay-Pandulian |  | Road Maintenance | 5.57 | MBA | a) | 294917.73 | a) | 01/03/19 | e) | - | a) | 294917.73 | a) | - | c) | - | a) | -
028 | [6 empty] | b) | Crucio | b) | - | f) | - | b) | 294917.73 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
|  | Capungagan-Mabuhay-Pandulian |  | Road Maintenance | 5.57 | CBRMC | a) | 105950.95 | a) | 01/03/19 | e) | - | a) | 105950.95 | a) | - | c) | - | a) | -
028 | [6 empty] | b) | Crucio | b) | - | f) | - | b) | 105950.95 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
|  | Florida - New Boholano |  | Road Maintenance | 2.54 | MBA | a) | 95863.17 | a) | 01/03/19 | e) | - | a) | 95863.17 | a) | - | c) | - | a) | -
030 | [6 empty] | b) | Crucio | b) | - | f) | - | b) | 95863.17 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
|  | Florida - New Boholano |  | Road Maintenance | 2.54 | CBRMC | a) | 47425.27 | a) | 01/03/19 | e) | - | a) | 47425.27 | a) | - | c) | - | a) | -
030 | [6 empty] | b) | Crucio | b) | - | f) | - | b) | 47425.27 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
|  | Jct. New Boholano - New Loon |  | Road Maintenance | 4.77 | MBA | a) | 140549.84 | a) | 01/03/19 | e) | - | a) | 140549.84 | a) | - | c) | - | a) | -
031 | [6 empty] | b) | Crucio | b) | - | f) | - | b) | 140549.84 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
|  | Jct. New Boholano - New Loon |  | Road Maintenance | 4.77 | CBRMC | a) | 169521.51 | a) | 01/03/19 | e) | - | a) | 169521.51 | a) | - | c) | - | a) | -
031 | [6 empty] | b) | Crucio | b) | - | f) | - | b) | 169521.51 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
|  | Florida-Suaon-Jct. Gupitan |  | Road Maintenance | 15.57 | MBA | a) | 707038.05 | a) | 01/03/19 | e) | - | a) | 707038.05 | a) | 13.66% | c) | 13.66% | a) | -
032 | [6 empty] | b) | Crucio | b) | - | f) | - | b) | 707038.05 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
|  | Florida-Suaon-Jct. Gupitan |  | Road Maintenance | 15.57 | CBRMC | a) | 419094.85 | a) | 01/03/19 | e) | - | a) | 419094.85 | a) | - | c) | - | a) | -
032 | [6 empty] | b) | Crucio | b) | - | f) | - | b) | 419094.85 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
|  | Km. 15, Kipalili-New Loon |  | Road Maintenance | 6.93 | MBA | a) | 367659.97 | a) | 01/03/19 | e) | - | a) | 367659.97 | a) | - | c) | - | a) | -
034 | [6 empty] | b) | Crucio | b) | - | f) | - | b) | 367659.97 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
|  | Km. 15, Kipalili-New Loon |  | Road Maintenance | 6.93 | CBRMC | a) | 237801.01 | a) | 01/03/19 | e) | - | a) | 237801.01 | a) | - | c) | - | a) | -
034 | [6 empty] | b) | Crucio | b) | - | f) | - | b) | 237801.01 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
|  | Jct. Suaon-Libuton |  | Road Maintenance | 7.26 | MBA | a) | 44015.68 | a) | 01/03/19 | e) | - | a) | 44015.68 | a) | 6.16% | c) | 6.16% | a) | -
035 | [6 empty] | b) | Crucio | b) | - | f) | - | b) | 44015.68 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
|  | Jct. Suaon-Libuton |  | Road Maintenance | 7.26 | CBRMC | a) | 91664.91 | a) | 01/03/19 | e) | - | a) | 91664.91 | a) | - | c) | - | a) | -
035 | [6 empty] | b) | Crucio | b) | - | f) | - | b) | 91664.91 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
|  | Datu Balong - Pinamuno |  | Road Maintenance | 2.74 | MBA | a) | 95458.24 | a) | 01/03/19 | e) | - | a) | 95458.24 | a) | - | c) | - | a) | -
040 | [6 empty] | b) | Crucio | b) | - | f) | - | b) | 95458.24 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
|  | Datu Balong - Pinamuno |  | Road Maintenance | 2.74 | CBRMC | a) | 63570.57 | a) | 01/03/19 | e) | - | a) | 63570.57 | a) | - | c) | - | a) | -
040 | [6 empty] | b) | Crucio | b) | - | f) | - | b) | 63570.57 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
|  | Sawata - Mamangan - Pinamuno |  | Road Maintenance | 14.48 | MBA | a) | 545390.17 | a) | 01/03/19 | e) | - | a) | 545390.17 | a) | - | c) | - | a) | -
041 | [6 empty] | b) | Crucio | b) | - | f) | - | b) | 545390.17 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
|  | Sawata - Mamangan - Pinamuno |  | Road Maintenance | 14.48 | CBRMC | a) | 508564.54 | a) | 01/03/19 | e) | - | a) | 508564.54 | a) | - | c) | - | a) | -
041 | [6 empty] | b) | Crucio | b) | - | f) | - | b) | 508564.54 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
|  | Igangon - Sawata |  | Road Maintenance | 9.66 | MBA | a) | 497447.77 | a) | 01/03/19 | e) | - | a) | 497447.77 | a) | - | c) | - | a) | -
042 | [6 empty] | b) | Crucio | b) | - | f) | - | b) | 497447.77 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
|  | Igangon - Sawata |  | Road Maintenance | 9.66 | CBRMC | a) | 197775.1 | a) | 01/03/19 | e) | - | a) | 197775.1 | a) | - | c) | - | a) | -
042 | [6 empty] | b) | Crucio | b) | - | f) | - | b) | 197775.1 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
|  | New Corella - Sto. Niño - Macgum |  | Road Maintenance | 17.11 | MBA | a) | 606294.08 | a) | 01/03/19 | e) | - | a) | 606294.08 | a) | 17.20% | c) | 17.20% | a) | -
044 | [6 empty] | b) | Crucio | b) | - | f) | - | b) | 606294.08 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
|  | New Corella - Sto. Niño - Macgum |  | Road Maintenance | 17.11 | CBRMC | a) | 308434.97 | a) | 01/03/19 | e) | - | a) | 308434.97 | a) | - | c) | - | a) | -
044 | [6 empty] | b) | Crucio | b) | - | f) | - | b) | 308434.97 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
|  | Tagaytay - Buan |  | Road Maintenance | 4.92 | MBA | a) | 173197.37 | a) | 01/03/19 | e) | - | a) | 173197.37 | a) | - | c) | - | a) | -
045 | [6 empty] | b) | Crucio | b) | - | f) | - | b) | 173197.37 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
|  | Tagaytay - Buan |  | Road Maintenance | 4.92 | CBRMC | a) | 131850.07 | a) | 01/03/19 | e) | - | a) | 131850.07 | a) | - | c) | - | a) | -
045 | [6 empty] | b) | Crucio | b) | - | f) | - | b) | 131850.07 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
|  | limbaan - Sto. Niño |  | Road Maintenance | 3.19 | MBA | a) | 153706.77 | a) | 01/03/19 | e) | - | a) | 153706.77 | a) | - | c) | - | a) | -
049 | [6 empty] | b) | Crucio | b) | - | f) | - | b) | 153706.77 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
|  | limbaan - Sto. Niño |  | Road Maintenance | 3.19 | CBRMC | a) | 53657.51 | a) | 01/03/19 | e) | - | a) | 53657.51 | a) | - | c) | - | a) | -
049 | [6 empty] | b) | Crucio | b) | - | f) | - | b) | 53657.51 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
|  | Del Pilar - Jct. Silangan |  | Road Maintenance | 4.17 | MBA | a) | 187097.4 | a) | 01/03/19 | e) | - | a) | 187097.4 | a) | - | c) | - | a) | -
051 | [6 empty] | b) | Crucio | b) | - | f) | - | b) | 187097.4 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
|  | Del Pilar - Jct. Silangan |  | Road Maintenance | 4.17 | CBRMC | a) | 113014.34 | a) | 01/03/19 | e) | - | a) | 113014.34 | a) | - | c) | - | a) | -
051 | [6 empty] | b) | Crucio | b) | - | f) | - | b) | 113014.34 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
|  | New Corella - New Sambog - Silangan |  | Road Maintenance | 5.1 | MBA | a) | 201994.35 | a) | 01/03/19 | e) | - | a) | 201994.35 | a) | - | c) | - | a) | -
052 | [6 empty] | b) | Crucio | b) | - | f) | - | b) | 201994.35 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
|  | New Corella - New Sambog - Silangan |  | Road Maintenance | 5.1 | CBRMC | a) | 131850.07 | a) | 01/03/19 | e) | - | a) | 131850.07 | a) | - | c) | - | a) | -
052 | [6 empty] | b) | Crucio | b) | - | f) | - | b) | 131850.07 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
|  | Sta. Fe - Del Monte |  | Road Maintenance | 3.34 | MBA | a) | 37923.51 | a) | 01/03/19 | e) | - | a) | 37923.51 | a) | - | c) | - | a) | -
056 | [6 empty] | b) | Crucio | b) | - | f) | - | b) | 37923.51 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
|  | Sta. Fe - Del Monte |  | Road Maintenance | 3.34 | CBRMC | a) | 70633.96 | a) | 01/03/19 | e) | - | a) | 70633.96 | a) | - | c) | - | a) | -
056 | [6 empty] | b) | Crucio | b) | - | f) | - | b) | 70633.96 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
|  | New Corella - New Bohol |  | Road Maintenance | 11.54 | MBA | a) | 356226.67 | a) | 01/03/19 | e) | - | a) | 356226.67 | a) | - | c) | - | a) | -
058 | [6 empty] | b) | Crucio | b) | - | f) | - | b) | 356226.67 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
|  | New Corella - New Bohol |  | Road Maintenance | 11.54 | CBRMC | a) | 190711.7 | a) | 01/03/19 | e) | - | a) | 190711.7 | a) | - | c) | - | a) | -
058 | [6 empty] | b) | Crucio | b) | - | f) | - | b) | 190711.7 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
|  | Jct. Carcor - Prk. 9 Bagsak |  | Road Maintenance | 2.5 | MBA | a) | 108618.49 | a) | 01/03/19 | e) | - | a) | 108618.49 | a) | - | c) | - | a) | -
059 | [6 empty] | b) | Crucio | b) | - | f) | - | b) | 108618.49 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
|  | Jct. Carcor - Prk. 9 Bagsak |  | Road Maintenance | 2.5 | CBRMC | a) | 42284.76 | a) | 01/03/19 | e) | - | a) | 42284.76 | a) | - | c) | - | a) | -
059 | [6 empty] | b) | Crucio | b) | - | f) | - | b) | 42284.76 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
|  | Carcor - Jct. Kauswagan |  | Road Maintenance | 4.32 | MBA | a) | 264514.71 | a) | 01/03/19 | e) | - | a) | 264514.71 | a) | - | c) | - | a) | -
060 | [6 empty] | b) | Crucio | b) | - | f) | - | b) | 264514.71 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
|  | Carcor - Jct. Kauswagan |  | Road Maintenance | 4.32 | CBRMC | a) | 48398.27 | a) | 01/03/19 | e) | - | a) | 48398.27 | a) | - | c) | - | a) | -
060 | [6 empty] | b) | Crucio | b) | - | f) | - | b) | 48398.27 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
|  | Del Pilar - Prk 9 Bagsak - San Jose |  | Road Maintenance | 4.99 | MBA | a) | 170215.76 | a) | 01/03/19 | e) | - | a) | 170215.76 | a) | - | c) | - | a) | -
061 | [6 empty] | b) | Crucio | b) | - | f) | - | b) | 170215.76 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
|  | Del Pilar - Prk 9 Bagsak - San Jose |  | Road Maintenance | 4.99 | CBRMC | a) | 223674.22 | a) | 01/03/19 | e) | - | a) | 223674.22 | a) | - | c) | - | a) | -
061 | [6 empty] | b) | Crucio | b) | - | f) | - | b) | 223674.22 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
|  | San Juan - New Talisay |  | Road Maintenance | 5.13 | MBA | a) | 306261.25 | a) | 01/03/19 | e) | - | a) | 306261.25 | a) | - | c) | - | a) | -
063 | [6 empty] | b) | Crucio | b) | - | f) | - | b) | 306261.25 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
|  | San Juan - New Talisay |  | Road Maintenance | 5.13 | CBRMC | a) | 93906.31 | a) | 01/03/19 | e) | - | a) | 93906.31 | a) | - | c) | - | a) | -
063 | [6 empty] | b) | Crucio | b) | - | f) | - | b) | 93906.31 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
|  | San Juan - kauswagan - New Cortez |  | Road Maintenance | 3.22 | MBA | a) | 187879.04 | a) | 01/03/19 | e) | - | a) | 187879.04 | a) | - | c) | - | a) | -
064 | [6 empty] | b) | Crucio | b) | - | f) | - | b) | 187879.04 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
|  | San Juan - kauswagan - New Cortez |  | Road Maintenance | 3.22 | CBRMC | a) | 63298.26 | a) | 01/03/19 | e) | - | a) | 63298.26 | a) | - | c) | - | a) | -
064 | [6 empty] | b) | Crucio | b) | - | f) | - | b) | 63298.26 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
|  | New Bohol - Jct. El Unido |  | Road Maintenance | 2.12 | MBA | a) | 54989.06 | a) | 01/03/19 | e) | - | a) | 54989.06 | a) | - | c) | - | a) | -
065 | [6 empty] | b) | Crucio | b) | - | f) | - | b) | 54989.06 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
|  | New Bohol - Jct. El Unido |  | Road Maintenance | 2.12 | CBRMC | a) | 58861.64 | a) | 01/03/19 | e) | - | a) | 58861.64 | a) | - | c) | - | a) | -
065 | [6 empty] | b) | Crucio | b) | - | f) | - | b) | 58861.64 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
|  | New Corella - El unido - Jct. Mesaoy |  | Road Maintenance | 8.63 | MBA | a) | 388002.46 | a) | 01/03/19 | e) | - | a) | 388002.46 | a) | - | c) | - | a) | -
066 | [6 empty] | b) | Crucio | b) | - | f) | - | b) | 388002.46 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
|  | New Corella - El unido - Jct. Mesaoy |  | Road Maintenance | 8.63 | CBRMC | a) | 233092.08 | a) | 01/03/19 | e) | - | a) | 233092.08 | a) | - | c) | - | a) | -
066 | [6 empty] | b) | Crucio | b) | - | f) | - | b) | 233092.08 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
|  | Mesaoy - Dasing |  | Road Maintenance | 1.39 | MBA | a) | 29749.5 | a) | 01/03/19 | e) | - | a) | 29749.5 | a) | - | c) | - | a) | -
067 | [6 empty] | b) | Crucio | b) | - | f) | - | b) | 29749.5 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
|  | Mesaoy - Dasing |  | Road Maintenance | 1.39 | CBRMC | a) | 54152.71 | a) | 01/03/19 | e) | - | a) | 54152.71 | a) | - | c) | - | a) | -
067 | [6 empty] | b) | Crucio | b) | - | f) | - | b) | 54152.71 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
|  | Jct. San Juan - Jct. Mesaoy |  | Road Maintenance | 1.82 | MBA | a) | 106788.95 | a) | 01/03/19 | e) | - | a) | 106788.95 | a) | - | c) | - | a) | -
068 | [6 empty] | b) | Crucio | b) | - | f) | - | b) | 106788.95 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
|  | Jct. San Juan - Jct. Mesaoy |  | Road Maintenance | 1.82 | CBRMC | a) | 35180.83 | a) | 01/03/19 | e) | - | a) | 35180.83 | a) | - | c) | - | a) | -
068 | [6 empty] | b) | Crucio | b) | - | f) | - | b) | 35180.83 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
|  | Mesaoy - Jct. Mahayahay |  | Road Maintenance | 4.6 | MBA | a) | 146984.46 | a) | 01/03/19 | e) | - | a) | 146984.46 | a) | - | c) | - | a) | -
069 | [6 empty] | b) | Crucio | b) | - | f) | - | b) | 146984.46 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
|  | Mesaoy - Jct. Mahayahay |  | Road Maintenance | 4.6 | CBRMC | a) | 160103.65 | a) | 01/03/19 | e) | - | a) | 160103.65 | a) | - | c) | - | a) | -
069 | [6 empty] | b) | Crucio | b) | - | f) | - | b) | 160103.65 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
|  | Mesaoy - New bohol |  | Road Maintenance | 5.36 | MBA | a) | 165361.13 | a) | 01/03/19 | e) | - | a) | 165361.13 | a) | - | c) | - | a) | -
070 | [6 empty] | b) | Crucio | b) | - | f) | - | b) | 165361.13 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
|  | Mesaoy - New bohol |  | Road Maintenance | 5.36 | CBRMC | a) | 224851.45 | a) | 01/03/19 | e) | - | a) | 224851.45 | a) | - | c) | - | a) | -
070 | [6 empty] | b) | Crucio | b) | - | f) | - | b) | 224851.45 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
|  | Bdry. Tagum - Baca - New Corella |  | Road Maintenance | 13.01 | MBA | a) | 217182.9 | a) | 01/03/19 | e) | - | a) | 217182.9 | a) | - | c) | - | a) | -
071 | [6 empty] | b) | Crucio | b) | - | f) | - | b) | 217182.9 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
|  | Bdry. Tagum - Baca - New Corella |  | Road Maintenance | 13.01 | CBRMC | a) | 214256.36 | a) | 01/03/19 | e) | - | a) | 214256.36 | a) | - | c) | - | a) | -
071 | [6 empty] | b) | Crucio | b) | - | f) | - | b) | 214256.36 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
|  | Prk. 1, Maunlom - Prk. 6 Maunlom Road |  | Road Maintenance | 3.56 | MBA | a) | 150912.87 | a) | 01/03/19 | e) | - | a) | 150912.87 | a) | - | c) | - | a) | -
147 | [6 empty] | b) | Crucio | b) | - | f) | - | b) | 150912.87 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
|  | Prk. 1, Maunlom - Prk. 6 Maunlom Road |  | Road Maintenance | 3.56 | CBRMC | a) | 63973.36 | a) | 01/03/19 | e) | - | a) | 63973.36 | a) | - | c) | - | a) | -
147 | [6 empty] | b) | Crucio | b) | - | f) | - | b) | 63973.36 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
|  | New Visayas - Binancian |  | Road Maintenance | 7.77 | MBA | a) | 14814.34 | a) | 01/03/19 | e) | - | a) | 14814.34 | a) | - | c) | - | a) | -
149 | [6 empty] | b) | Crucio | b) | - | f) | - | b) | 14814.34 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
|  | New Visayas - Binancian |  | Road Maintenance | 7.77 | CBRMC | a) | 129495.6 | a) | 01/03/19 | e) | - | a) | 129495.6 | a) | - | c) | - | a) | -
149 | [6 empty] | b) | Crucio | b) | - | f) | - | b) | 129495.6 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
|  | Datu Balong - Prk. Mamalian |  | Road Maintenance | 3.46 | MBA | a) | 117454.89 | a) | 01/03/19 | e) | - | a) | 117454.89 | a) | - | c) | - | a) | -
150 | [6 empty] | b) | Crucio | b) | - | f) | - | b) | 117454.89 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
|  | Datu Balong - Prk. Mamalian |  | Road Maintenance | 3.46 | CBRMC | a) | 59264.42 | a) | 01/03/19 | e) | - | a) | 59264.42 | a) | - | c) | - | a) | -
150 | [6 empty] | b) | Crucio | b) | - | f) | - | b) | 59264.42 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
Road ID |  | 2. Rehabilitation Of Various Prov'l. Roads and Bridges |  | Road Maintenance | KM | MBA | a) | 41465029 | a) | 01/03/19 | e) | - | a) | 41465029 | a) | - | c) | - | a) | 46 | See list of Provincial Roads
[5 empty] | 109.55 |  | b) | Paraguya | b) | 01/03/19 | f) | - | b) | 41465029 | b) | - | d) | - | b) | 920
11DAN | [6 empty] | c) | PEO | c) | 12/31/19 | g) | - | c) | -
[9 empty] | d) | -
[7 empty] | d) | 261 days | d) | -
|  | Jct. Highway Canatan - Doña Andrea |  | Road Rehab | 4.34 | MBA | a) |  | a) | 01/03/19 | e) | - | a) | 0 | a) | - | c) | - | a) | -
007 | [6 empty] | b) | Crucio | b) | - | f) | - | b) | 0 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
|  | Pamacaun - Lasang Banate |  | Road Rehab | 4.34 | MBA | a) |  | a) | 01/03/19 | e) | - | a) | 0 | a) | - | c) | - | a) | -
015 | [6 empty] | b) | Crucio | b) | - | f) | - | b) | 0 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
|  | Kapalong - Mabantao - Florida |  | Road Rehab | 7.86 | MBA | a) |  | a) | 01/03/19 | e) | - | a) | 0 | a) | - | c) | - | a) | -
016 | [6 empty] | b) | Crucio | b) | - | f) | - | b) | 0 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
|  | Jct. Highway Gabuyan - Semong - Dagohoy |  | Road Rehab | 6.97 | MBA | a) |  | a) | 01/03/19 | e) | - | a) | 0 | a) | - | c) | - | a) | -
017 | [6 empty] | b) | Crucio | b) | - | f) | - | b) | 0 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
|  | Sto. Niño - Palma Gil - Sitio Opao |  | Road Rehab | 11.6 | MBA | a) |  | a) | 01/03/19 | e) | - | a) | 0 | a) | - | c) | - | a) | -
019 | [6 empty] | b) | Crucio | b) | - | f) | - | b) | 0 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
|  | Daligdigon - Lumabag |  | Road Rehab | 11.6 | MBA | a) |  | a) | 01/03/19 | e) | - | a) | 0 | a) | - | c) | - | a) | -
022 | [6 empty] | b) | Crucio | b) | - | f) | - | b) | 0 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
|  | Sto. Niño - Daligdigon - Paiton |  | Road Rehab | 11.6 | MBA | a) |  | a) | 01/03/19 | e) | - | a) | 0 | a) | - | c) | - | a) | -
023 | [6 empty] | b) | Crucio | b) | - | f) | - | b) | 0 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
|  | Jct. Paiton - Mibolo |  | Road Rehab | 23.9 | MBA | a) |  | a) | 01/03/19 | e) | - | a) | 0 | a) | - | c) | - | a) | -
024 | [6 empty] | b) | Crucio | b) | - | f) | - | b) | 0 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
|  | Monte Dujali - Gupitan |  | Road Rehab | 4.58 | MBA | a) |  | a) | 01/03/19 | e) | - | a) | 0 | a) | - | c) | - | a) | -
037 | [6 empty] | b) | Crucio | b) | - | f) | - | b) | 0 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
|  | Jct. Patel - Langan |  | Road Rehab | 1.62 | MBA | a) |  | a) | 01/03/19 | e) | - | a) | 0 | a) | - | c) | - | a) | -
038 | [6 empty] | b) | Crucio | b) | - | f) | - | b) | 0 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
|  | Jct. Sawata - Bdry. Binasbas |  | Road Rehab | 0.46 | MBA | a) |  | a) | 01/03/19 | e) | - | a) | 0 | a) | - | c) | - | a) | -
043 | [6 empty] | b) | Crucio | b) | - | f) | - | b) | 0 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
|  | New Corella - Saug |  | Road Rehab | 12.52 | MBA | a) |  | a) | 01/03/19 | e) | - | a) | 0 | a) | - | c) | - | a) | -
048 | [6 empty] | b) | Crucio | b) | - | f) | - | b) | 0 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
|  | Jct. Monte Carlo - Upper Cabaywa - Canatan |  | Road Rehab | 4.61 | MBA | a) |  | a) | 01/03/19 | e) | - | a) | 0 | a) | - | c) | - | a) | -
050 | [6 empty] | b) | Crucio | b) | - | f) | - | b) | 0 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
|  | Pob. New Corella - Prk. 10 Pob. |  | Road Rehab | 1.3 | MBA | a) |  | a) | 01/03/19 | e) | - | a) | 0 | a) | - | c) | - | a) | -
053 | [6 empty] | b) | Crucio | b) | - | f) | - | b) | 0 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
|  | Prk. 7 Pob. - JCt. New Sambog |  | Road Rehab | 2.54 | MBA | a) |  | a) | 01/03/19 | e) | - | a) | 0 | a) | - | c) | - | a) | -
054 | [6 empty] | b) | Crucio | b) | - | f) | - | b) | 0 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
|  | Del Pilar - El Unido |  | Road Rehab | 1.32 | MBA | a) |  | a) | 01/03/19 | e) | - | a) | 0 | a) | - | c) | - | a) | -
062 | [6 empty] | b) | Crucio | b) | - | f) | - | b) | 0 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
|  | Bdry. Tagum - Baca - New Corella |  | Road Rehab | 13.01 | MBA | a) |  | a) | 01/03/19 | e) | - | a) | 0 | a) | - | c) | - | a) | -
071 | [6 empty] | b) | Crucio | b) | - | f) | - | b) | 0 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
| GF- GENERAL FUND | [13 empty] | TF - TRUST FUND (NATIONAL FUNDED PROJECT)
| 20% DF - 20% DEV'T. FUND | [13 empty] | a) SLRF - Special Local Road Fund
| 5% CF - 5% CALAMITY FUND | [13 empty] | b) KALSADA - Konkreto at Ayos na Lansangan Tungo sa Pangkalahatang Kaunlaran
| CO - CAPITAL OUTLAY | [13 empty] | c) PRDP - Philippine Rural Development Projects
| CONG. FUND - CONGRESSIONAL FUND | [13 empty] | d) SELAP - Support to Emergency and Livelihood Assistance Project
| NCF - NATIONAL CALAMITY FUND | [13 empty] | e) PAMANA - Payapa at Masaganang Pamayanan
| SEF - SPECIAL EDUCATIONAL UFND | [13 empty] | f) CBRMC - Community Based Road Maintenance Contracting
g) MBC - Maintenance by Contract
h) PCF-Performance Challenge Fund-DILG
j) FMRDP - Farm to Market Road
j.) CMGP - Conditional Grant to Provinces
| Prepared by: |  |  | Checked by: |  |  |  |  | Reviewed by: |  |  |  |  | Noted by: | [5 empty] | Recommending Approval:
| RETCHIE A. DE LOS REYES |  |  | MARILOU A. FORONDA |  |  |  |  | EDWIN S. MISA |  |  |  |  | JIVELLYN B. CO | [5 empty] | RAUL G. MABANGLO
| Engineer II |  |  | Engineer IV-Area Engineer |  |  |  |  | Engineer IV-PDP/SIM |  |  |  |  | Asst. PG-Department Head | [5 empty] | PG-Department Head
|  |  |  | 1st Engineering District |  |  |  |  | Planning Division Programming
Survey Investigation and Monitoring

## Sheet3 (hidden)
GF- GENERAL FUND |  |  |  | TF - TRUST FUND (NATIONAL FUNDED PROJECT)
20% DF - 20% DEV'T. FUND |  |  |  | a) SLRF - Special Local Road Fund
5% CF - 5% CALAMITY FUND |  |  |  | b) KALSADA - Konkreto at Ayos na Lansangan Tungo sa Pangkalahatang Kaunlaran
CO - CAPITAL OUTLAY |  |  |  | c) PRDP - Philippine Rural Development Projects
NCF - NATIONAL CALAMITY FUND |  |  |  | d) SELAP - Support to Emergency and Livelihood Assistance Project
SEF - SPECIAL EDUCATIONAL UFND |  |  |  | e) PAMANA - Payapa at Masaganang Pamayanan
f) CBRMC - Community Based Road Maintenance Contracting
g) MBC - Maintenance by Contract
h) PCF-Performance Challenge Fund-DILG
i) FMRDP - Farm to Market Road
j.) CMGP - Conditional Grant to Provinces
k.) OPAP - Office of the President Adviser on the Peace Process
l.) LGSF - LOCAL GOVERNMENT SUPPORT FUND
Prepared by: | Checked by: | Reviewed by: | Noted by: |  | Recommending Approval:
RETCHIE A. DE LOS REYES | MARILOU A. FORONDA | EDWIN S. MISA | JIVELLYN B. CO |  | RAUL G. MABANGLO
Engineer II | Engineer IV-Area Engineer | Engineer IV-PDP/SIM | Asst. PG-Department Head |  | PG-Department Head
| 1st Engineering District | Planning Division Programming
Survey Investigation and Monitoring

## Sheet6 (hidden)
PRDP PROJECTS
PROJECT NAME | AMOUNT
1. Rehab. of Little Panay-Katipunan-Kasilak FMR, Panabo City | 61938000
2. Rehab. Of Datu-Balong Prk. Mamalian San Isidro, Davao del Norte | 39024715.05
108303841.7
3. Rehab. Of Sto. Niño-Igangon FMR, San Isidro | 74173694.5 | 38212432.9882
4. Rehab. Of Capungagan-Boundary San Miguel FMR, Kapalong | 108303841.7
5. Rehab. Of Pob.-Limbaan-Suawon-Macgum FMR w/ Bridge, New Corella | 205202114.16 | 1156422096.35
6. Rehab. Of Sonlon Camansa FMR | 215125015.81 | 1176371677.53
TOTAL | 641829381.22
CMGP PROJECTS
PROJECT NAME | AMOUNT
1. Impvt. Of Km. 9 Sagayen-Sawata Provincial Road | 43596834.96
2. Upgrading of Prk. Narafil - Brgy. Site Magupising Provincial Road | 51423291.79
3. Road Upgrading of Km 9 Sagayen-Sawata Provincial Road (Sagayen-Jct. San Miguel Section) | 139761975.14
4. Road Upgrading of Anahaw-Maligaya Provincial Road | 78228121.56
5. Road Upgrading of Maligaya-New Camiling Provincial Road with Bridge Component | 50101614.08
6. Road Updgrading of FDR. Rd. 3 - Kimamon - Luna Provincial Road | 119901954.82
7. Road Upgrading of Dagohoy - Daligdigon Provincial Road | 58048310.68
8. Road Upgrading of Dujali-Balisong-Magupising Provincial Road | 17127447.06
TOTAL | 514592715.13
PAMANA PROJECTS
1156422096.35
PROJECT NAME | AMOUNT
1.Const. of Processing and Bagsakan Center, Brgy. Palma Gil, Talaingod | 2500000
2. Const. of Processing and Bagsakan Center, Brgy. Sto. Nino, Talaingod | 2500000
3. Const. of Processing and Bagsakan Center, Brgy. Gupitan, Kapalong, | 2500000
4. Construction of PWS Level II in Purok 1, Dagohoy, Talaingod, | 1000000
5. Provision of Solar Energy Dagohoy, Palma Gil & Sto. Niño | 13000000
TOTAL | 19000000
LGSF PROJECT
PROJECT NAME | AMOUNT
1.Road Upgrading of San Vicente - Butay Provincial Road | 19949581.18

## On Going (Final) (2) (hidden)
PROVINCE OF DAVAO DEL NORTE
ACCOMPLISHMENT REPORT
FOR THE MONTH OF JUNE 2019
SECTOR: ECONOMIC (INFRASTRUCTURE DEV'T. PROGRAM)
OFFICE/AGENCY: PROVINCIAL ENGINEER'S OFFICE
AREA: 1ST ENGINEERING DISTRICT - ON-GOING PROJECTS
Name of Project |  |  |  | Type | Physical | Mode | PROJECT DATA | [5 empty] | Financial (000) |  | Physical Accomplishment |  |  |  | Employment |  | REMARKS
|  |  |  | of | Target | of | a) Project Cost |  | a) Date A lot. Rel. |  | e) # of days suspended |  | a) Program |  | a) Planned |  | c) Actual |  | Generated
|  |  |  | Project | (Descrip | Impl. | b) Project Engineer |  | b) Date Started |  | f) # of days extended |  | b) Allotment |  | b) Revised |  | d) Slippage |  | a) # of Persons
|  |  |  | (Location) | tion) |  | c) Implementor |  | c)Target Compl. Date |  | g) Date completed |  | c) Disbursement | [5 empty] | b) Man-days
[7 empty] | d) Duration |  | d) Revised Compl. Date
I. | PROJECTS UNDER THE CONTINUING APPROPRIATION | [22 empty] | 893809.45
| A. | Supplemental Budget # 4 CY 2017
|  | 1 | Upgrading of DDNSTC (Basketball/Voleyball | Covered | 2252.69 sq.m | Contract | a) | 99992356.64 | a) | 10/16/18 | e) | - | a) | 99992356.64 | a) | 89.35% | c) | 20.8% | a) | 5 | On-going
|  |  | MP Covered Court),Sports Center, Mankilam, | Court |  |  | b) | Escurzon | b) | 07/17/18 | f) | 20 CD | b) | 99992356.64 | b) | - | d) | -68.55% | b) | 150
|  |  | Tagum City |  |  |  | c) | YBC | c) | 07/11/19 | g) | - | c) | 18, 280, 402.33
[7 empty] | d) | 360 CD | d) | 07/31/19
| B. | Trust Fund
1. PAMANA-DILG CY 2014
|  | 1.1 Construction of Biga Bridges, Kapalong |  | Road | 2-18ln.m | Contract | a) | 24959503.45 | a) | CY 2014 | e) | 304 CD | a) | 24959503.45 | a) | 100.00% | c) | 60.63% | a) | 8 | On-going
[7 empty] | b) | Limpo | b) | 07/01/16 | f) | - | b) | 24959503.45 | b) | 75.22% | d) | -14.59% | b) | 290 | Resume last June 1, 2018
[7 empty] | c) | Dvo. Rock Mixer | c) | 07/30/18 | g) | - | c) | 37,439,255.18 | [6 empty] | Issued warning letter & submit catch-up plan
[7 empty] | d) | 880 CD | d) | 09/27/19
|  | 1.2 Road Rehabilitation/Improvement of Prk. 3, |  | Road | 13.60 kms | Contract | a) | 50,500,288.95 | a) | CY 2014 | e) | - | a) | 50,500,288.95 | a) | 100.00% | c) | 94.1% | a) | 25 | On-going
|  | Palma Gil-Prk.2 (side 2), Sto. Niño-Mahayahay-Tugas- |  |  |  |  | b) | Dadula | b) | 07/07/16 | f) | 398 CD | b) | 50,500,288.95 | b) | 100% | d) | -5.9% | b) | 750
|  | Nanaga Road, with 1 -unit, 40 ln.m PSCG Bridge, |  |  | 40 ln.m |  | c) | Puregold | c) | 03/12/18 | g) | - | c) | 41424313.06
|  | Kapalong |  |  |  |  | d) | 1011 CD | d) | 04/14/19
2. PRDP CY 2015
|  | 2.1 Rehab. Of Capungagan-Boundary San |  | Road | 10.6 kms. | Contract. | a) | 108,303,841.70 | a) | CY 2015 | e) | 140 CD | a) | 108,303,841.70 | a) | 100.00% | c) | 74.28% | a) | 38 | On-going
|  | Miguel FMR, Kapalong, Davao del Norte |  |  |  |  | b) | Nasol | b) | 04/06/16 | f) | 575 CD | b) | 108,303,841.70 | b) | 84.5% | d) | -10.22% | b) | 1140 | Increase of Project Cost due to Variation Order with
[7 empty] | c) | VICLAO | c) | 03/26/17 | g) | - | c) | 38,212,432.90 | [6 empty] | Extra Work. (Php 4,992,591.29)
[7 empty] | d) | 1293 CD | d) | 08/28/19 | [10 empty] | Contractor catch-up plan within 3 months
|  | 2.2 Rehab. Of Pob.-Limbaan-Suawon-Macgum |  | Road | 15.01 kms./ | Contract. | a) | 205,202,114.16 | a) | CY 2015 | e) | 229 CD | a) | 205,202,114.16 | a) | 100.00% | c) | 61.22% | a) | 40 | On-going
|  | FMR w/ Bridge, New Corella, Davao del Norte |  |  | 42 ln.m |  | b) | Madrigal | b) | 04/08/16 | f) | 490 CD | b) | 205,202,114.16 | b) | 65.61% | d) | -4.393% | b) | 1200 | Increase of Project Cost due to Variation Order Php 14,948,622.18
[7 empty] | c) | Dvo. Rock Mixer | c) | 01/18/19 | g) | - | c) | 28538091.3
[7 empty] | d) | 1529CD | d) | 06/14/20 | [10 empty] | Partial suspension due to soft soil from sta. 8+000 - 10+000
3. KALSADA CY 2015
|  | 3.1 Improvement of Km. 9 Sagayen-Sawata Provincial |  | Road | 3177 ln.m m | Contract | a) | 47213478.31 | a) | CY 2015 | d) | - | a) | 47213478.31 | a) | 100.00% | c) | 37.556% | a) |  | Contract Terminated
|  | San Isidro, Davao del Norte |  |  |  |  | b) | Limpo | b) | 08/26/16 | e) |  | b) | 47213478.31 | b) | 86.25% | d) | -48.69% | b)
[7 empty] | c) | Arn Builders | c) | 04/21/18 | f) | - | c) | 24931805.19
[7 empty] | d) |  | d)
|  | 3.2 Improvement of Km. 9 Sagayen-Sawata Provincial |  | Road | 6667.54 m | Admin | a) | 33401544.78 | a) | CY 2015 | d) | - | a) | 33401544.78 | a) | 33.98% | c) | 27.7% | a) | 30 | Original contract terminated due to very poor performance
|  | San Isidro, Davao del Norte |  |  |  |  | b) | Limpo | b) | 10/16/18 | e) |  | b) | 33401544.78 | b) |  | d) | -6.28% | b) | 900 | of the contractor.The contract cost P 47,213,478.31.
[7 empty] | c) | PEO | c) | 09/14/19 | f) | - | c) | 19,943,597.92 | [6 empty] | On-going
[7 empty] | d) | 334 CD | d)
| C. | Trust Fund
1. PRDP CY 2016
|  | 1.1 | Cacao Production and Beans Marketing, | Road | - | Contract. | a) | 5873626.8 | a) | CY 2016 | e) | - | a) | 5873626.8 | a) | 21.86% | c) | 14.23% | a) | 5 | On-going
|  |  | Capungagan, Kapalong, Davao del Norte |  |  |  | b) | Escurzon | b) | 03/19/19 | f) | - | b) | 5873626.8 | b) | - | d) | -7.637% | b) | 140
[7 empty] | c) | MICAH CONST. & SUPPLY | c) | 11/23/19 | g) | - | c) | -
[7 empty] | d) | 250 CD | d) | -
| D. | 20% Development Fund CY 2017
|  | 1. Const./Rehab./Comp. of Various Gov't. Bldgs. |  | Bldg. | - | Admin | a) | 9,000,000.00 | [12 empty] | Investigation/Inspection of priority projects
|  | Struct., Fac. (Provincewide) |  |  |  |  | b) | Foronda/Ababon
[7 empty] | c) | PEO
[7 empty] | d) | -
|  | 1.1 | Rehab. Of PEO Training Center | Bldg. |  | Admin | a) | 476,876.00 | a) | 02/12/19 | e) | - | a) | 476,876.00 | a) | - | c) | - | a) | - | For implementation
|  |  | (PDPM),Mankilam, Tagum City |  |  |  | b) | Chua | b) | - | f) | - | b) | 476,876.00 | b) | - | d) | - | b) | -
|  |  | (Part of P803,000.00)(20% DF CY 2018-P326,124.00) |  |  |  | c) | PEO | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
|  | 1.2 | Repair/Rehab. Of PEO Building | Bldg. |  | Admin | a) | 1,800,000.00 | a) | 07/31/18 | e) | - | a) | 1,800,000.00 | a) | 62.23% | c) | 62.23% | a) | 5 | On-going
|  |  | (Motorpool),Mankilam, Tagum City |  |  |  | b) | Chua | b) | 03/04/19 | f) | - | b) | 1,800,000.00 | b) | - | d) | - | b) | 105
[7 empty] | c) | PEO | c) | 08/10/19 | g) | - | c) | 1624451.85
[7 empty] | d) | 160 CD | d) | -
|  | 1.3 | Improvement of Garciaville Day Care | Bldg. |  | Admin | a) | 330,000.00 | a) | 11/06/18 | e) | - | a) | 330,000.00 | a) | - | c) | - | a) | - | For implementation
|  |  | Center, Mankilam, Tagum City |  |  |  | b) | - | b) | - | f) | - | b) | 330,000.00 | b) | - | d) | - | b) | -
[7 empty] | c) | PEO | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
|  | 1.4 | Construction of BSP Building Extension | Bldg. |  | Admin | a) | 500000 | a) | 08/21/18 | e) | 79 CD | a) | 500000 | a) | 100% | c) | 100% | a) | 6 | Completed
|  |  | Mankilam, Tagum City |  |  |  | b) | Quirante | b) | 01/16/19 | f) | 15 CD | b) | 500000 | b) | - | d) | - | b) | 180
[7 empty] | c) | PEO | c) | 03/16/19 | g) | 06/21/19 | c) | 434,145.73
[7 empty] | d) | 75 CD | d) | 03/31/19
|  | 2. Rural Electrification (Provincewide) |  | Elect. |  | - | a) | 5000000 | [12 empty] | See projects listed below
[7 empty] | b) | Foronda
[7 empty] | c) | -
[7 empty] | d) | -
|  | 2.1 | Electrification of Purok 1-4, Sta. Cruz, | Elect. |  | Admin | a) | 2,500,000.00 | a) | 02/04/19 | e) | - | a) | 2,500,000.00 | a) | - | c) | - | a) | - | For PR
|  |  | New Corella |  |  |  | b) | - | b) | - | f) | - | b) | 2,500,000.00 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
| E. | SEF(Special Education Fund)-SUPPLEMENTAL BUDGET # 1 CY 2017
|  | 1. Const./Impv't./Compl. Of School Bldgs., Struc. & Fac. |  | Bldgs. |  | Admin | a) | 3,300,000.00 | [12 empty] | See projects listed below
[7 empty] | b) | Foronda
[7 empty] | c) | PEO
[7 empty] | d) | -
|  | 1.1 | Construction of 1 unit School Building | Bldg. |  | Admin | a) | 1100000 | a) | 02/19/18 | e) | - | a) | 1100000 | a) | 100 | c) | 74.37 | a) | 10 | On-going
|  |  | Lumabag, Talaingod |  |  |  | b) | Dadula | b) | 03/20/19 | f) | 27 CD | b) | 1100000 | b) | 83.63 | d) | -9.26 | b) | 30
[7 empty] | c) | PEO | c) | 05/19/19 | g) | 06/30/2019 | c) | 918405.29
[7 empty] | d) | 60 CD | d) | -
| F. | STIMULUS PROJECTS CY 2017
ASUNCION
|  | 1 | Construction of Water Reservoir & | Water |  | MEO | a) | 500000 | a) | 12/28/17 | e) | - | a) | 500000 | a) | 90.00% | c) | 90.00% | a) | - | Suspended due to non availability of water source during drilling.Find another location.
|  |  | Purchase of P.E. Pipelines, Sagayen, | System |  |  | b) | - | b) | 11/15/18 | f) | - | b) | 500000 | b) | - | d) | - | b) | - | Fund already transferred at Municipality of Asuncion
|  |  | Asuncion |  |  |  | c) | MEO | c) | - | g) | - | c) | - | [6 empty] | with ChecK No. 2445174 and OR # 9238468,
[7 empty] | d) | - | d) | - | [10 empty] | dated March 16, 2018
NEW CORELLA
|  | 1 | Road Rehabilitation at Prk. 1-Prk. 5, | Road |  | MEO | a) | 500000 | a) | 11/29/17 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Waiting for bulldozer of the Province Fund already transferred at Municipality of New Corella with ChecK No. 2445213 and OR # 8592072, dated March 13, 2018
|  |  | Sta. Fe, New Corella |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | -
[7 empty] | c) | MEO | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
TAGUM CITY
|  | 1 | Construction of Multi-Purpose GYM at | Bldg. |  | - | a) | 500000 | a) | 11/29/17 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For ammendment.Change of project priority to Const. of Drainage (Box Culvert) at Purok Sampaguita.Waiting for Planand POW to be prepared by City Engineers Office.
|  |  | Mangga E/S, Visayan Village, Tagum City |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
KAPALONG
|  | 1 | Impv't. of Brgy. Hall, Sua-on, Kapalong | Bldg. |  | - | a) | 500000 | a) | 02/13/18 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Declared as savings to fund priority projects
[7 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
|  | 2 | Construction of Solar Drier, Semong, | Solar |  | - | a) | 500,000.00 | a) | 12/28/17 | e) | - | a) | 500,000.00 | a) | - | c) | - | a) | - | Declared as savings to fund priority projects
|  |  | Kapalong | Drier |  |  | b) | - | b) | - | f) | - | b) | 500,000.00 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
|  | 3 | Construction of Multi-Purpose Pavement, | MPP |  | - | a) | 500000 | a) | 12/28/17 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Declared as savings to fund priority projects
|  |  | Florida, Kapalong |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
|  | 4 | Construction of Concrete Bleacher, | Bleacher |  | - | a) | 500000 | a) | 12/07/17 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Declared as savings to fund priority projects
|  |  | Tiburcia, Kapalong |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
|  | 5 | Mainline Pipes for PWS, Mabantao, | Water |  | - | a) | 500000 | a) | 12/07/17 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | for AIP Amendment Plan & POW for approval - Feb. 15, 2019 - (Project already funded by LGU)
|  |  | kapalong | System |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
|  | 6 | Impv't. of Covered Court, Pag-Asa, | Court |  | - | a) | 500000 | a) | 12/07/17 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Declared as savings to fund priority projects
|  |  | Kapalong |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
|  | 7 | Covered Court Bleacher, Katipunan, | Bleacher |  | - | a) | 500000 | a) | 12/07/17 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Declared as savings to fund priority projects
|  |  | Kapalong |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
|  | 8 | Improvement of Gabuyan Covered Court, | Court |  | Admin | a) | 500000 | a) | 12/07/17 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Declared as savings to fund priority projects
|  |  | Brgy. Gabuyan, Kapalong |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | -
[7 empty] | c) | PEO | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
TALAINGOD
|  | 1 | Electrification @ Prk. 1A-Prk. 5A, Palma Gil, | Elect. |  | Barangay | a) | 500000 | a) | 12/28/17 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Fund already transferred at Municipality of Talaingod with ChecK No. 2445181 and OR # 7955667, dated March 16, 2018 . Amended AIP to Const. of Covered Court Bleacher.
|  |  | Talaingod |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | -
[7 empty] | c) |  | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
| G. | Trust Fund
1. CMGP (Conditional Matching Grant to Provinces)
|  | 1.1 | Road Upgrading km.9 sagayen-Sawata | Road | 10.20 km | Contract | a) | 139,761,975.14 | a) | CY 2017 | e) | - | a) | 139,761,975.14 | a) | 66.93 | c) | 67.326 | a) | 28 | On-going
|  |  | (Sagayen-Jct. San Miguel Section) |  |  |  | b) | Avila | b) | 10/01/18 | f) | - | b) | 139,761,975.14 | b) | - | d) | +6.29% | b) | 11170
[7 empty] | c) | Legacy Const. Corp. | c) | 08/22/19 | g) | - | c) | 63100753.7
[7 empty] | d) | 326 CD | d) | -
|  | 1.2 | Road Upgrading of Dagohoy - Daligdigon | Road | 2.532 km | Admin | a) | 58048310.68 | a) | CY 2017 | e) | - | a) | 58048310.68 | a) | 100.00% | c) | 83.5% | a) | 16 | On-going
|  |  | Provincial Road |  |  |  | b) | Fabiala | b) | 01/05/18 | f) | 205 CD | b) | 58048310.68 | b) | - | d) | -16.5% | b) | 480 | Contractor will submit commitment & action plan.
[7 empty] | c) | PUREGOLD | c) | 11/18/18 | g) | - | c) | 29,572,637.70
[7 empty] | d) | 246 CD | d) | 03/31/19
| H. | 2. OPPAP-PAMANA
|  | 2.1 | Const. of Trading Post, Storage Building | Bldg. |  | Contract | a) | 3,975,000.00 | a) | CY 2017 | e) | - | a) | 3,975,000.00 | a) | - | c) | - | a) | - | Rebidding
|  |  | with (1) unit Hauling Truck, Brgy. Pandapan |  |  |  | b) | - | b) | - | f) | - | b) | 3,975,000.00 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
| I. | LDRRM - Trust Fund
|  | 1. Construction of Slope Protection and Concrete Pavement along Sta. Fe Mambing Road Section |  | Slope |  | Admin | a) | 1,853,000.00 | a) | 11/28/18 | e) | 108 CD | a) | 1,853,000.00 | a) | 85.82% | c) | 70.6% | a) | 8 | On-going
[7 empty] | b) | Gone | b) | 12/03/18 | f) | 48 | b) | 1,853,000.00 | b) | - | d) | -15.22% | b) | 240 | Notice of resumption dated April 22, 2019
[7 empty] | c) | PEO | c) | 02/28/19 | g) | - | c) | 1207867.38
[7 empty] | d) | 86 CD | d) | 7/25/19
|  | 2. Rehab. Of Saug Bridge of Slope Protection |  | Slope |  | Admin | a) | 4,850,000.00 | a) | 05/25/18 | e) | - | a) | 4,850,000.00 | a) | 23.60% | c) | 9.60% | a) | - | Suspended dated 01/28/19
[7 empty] | b) | Gone | b) | 01/03/19 | f) | - | b) | 4,850,000.00 | b) |  | d) | -14% | b) | -
[7 empty] | c) | PEO | c) | 03/25/19 | g) | - | c) | 1628912.92
[7 empty] | d) | 82 CD | d) | -
|  | 3. Rehab. Of Canatan Bridge Slope Protection |  | Slope | 395 sq.m | Contract | a) | 9,200,000.00 | a) | 06/20/18 | e) | - | a) | 9,200,000.00 | a) | 100.00% | c) | 100% | a) | 14 | Completed as per physical accomplishment.
|  | Brgy. Canatan, Asuncion |  |  |  |  | b) | Aclaracion | b) | 02/11/19 | f) | 49 CD | b) | 9,200,000.00 | b) | 100% | d) | 0% | b) | 308
[7 empty] | c) | J-One Builders | c) | 04/12/19 | g) | 5/31/2019 | c) | 8998781.4
[7 empty] | d) | 60 CD | d) | 05/01/19
|  | 4. Re-channeling of BIGA River with Earth Dike and Slope Protection, Brgy. Gupitan, Kaplaong |  | Dike/Slope |  | Contract | a) | 12,100,000.00 | a) | 07/20/18 | e) | - | a) | 12,100,000.00 | a) | 8.30% | c) | 3.36% | a) | 4 | Suspended dated March 25, 2019
[7 empty] | b) | Limpo | b) | 02/22/19 | f) | - | b) | 12,100,000.00 | b) |  | d) | -4.94% | b) | 120 | Due to boundary conflict that will be reffered to Bureau of Land.
[7 empty] | c) | Alpha & Omega | c) | 06/11/19 | g) | - | c) | -
[7 empty] | d) | 110 CD | d) | -
|  | 5. Const. of Cabidianan Bridge Slope Protection, Brgy. Cabidianan, New Corella |  | Slope |  | Admin | a) | 3590000 | a) | 07/18/18 | e) | - | a) | 3590000 | a) | 5.89% | c) | 6.15% | a) | 8 | On-going
[7 empty] | b) | Gone | b) | 6/17/19 | f) | - | b) | 3590000 | b) |  | d) | 0.26% | b) | 80
[7 empty] | c) | PEO | c) | 8/20/19 | g) | - | c) | 1929823.4
[7 empty] | d) | 65 CD | d) | -
J. 20% Development Fund CY 2018
|  | 1. Various of Water System Project (Provincewide) |  | Water | - | - | a) | 10000000 | [12 empty] | Investigation/Inspection of priority projects
|  |  |  | System |  |  | b) | Foronda/Misa
[7 empty] | c) | PEO
[7 empty] | d) | -
|  | 1.1 | Conduct of geo-resistivity/drilling test | Geo- | - | - | a) | 250000 | [12 empty] | See list of projects
|  |  | of proposed site | resistivity |  |  | b) | Diosanta
[7 empty] | c) | -
[7 empty] | d) | -
|  |  | a. Const. of PWS Linao, San Isidro | Water | - | - | a) | 62000 | a) | - | e) | - | a) | 62000 | a) | - | c) | - | a) | - | Waiting for the geo-resistivty equipment.
|  |  |  | System |  |  | b) | - | b) | - | f) | - | b) | 62000 | b) | - | d) | - | b) | - | (Geo-resistivity equipment PR on process)
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
|  |  | b. Const. of PWS Mamalian, San Isidro | Water | - | - | a) | 62000 | a) | - | e) | - | a) | 62000 | a) | - | c) | - | a) | - | Waiting for the geo-resistivty equipment.
|  |  |  | System |  |  | b) | - | b) | - | f) | - | b) | 62000 | b) | - | d) | - | b) | - | (Geo-resistivty equipment PR on process)
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
|  |  | c. Const. of PWS Sagayen, San Isidro | Water | - | - | a) | 62000 | a) | - | e) | - | a) | 62000 | a) | - | c) | - | a) | - | Waiting for the geo-resistivty equipment.
|  |  |  | System |  |  | b) | - | b) | - | f) | - | b) | 62000 | b) | - | d) | - | b) | - | (Geo-resistivty equipment PR on process)
[7 empty] | c) | PEO | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
|  | 1.2 | Construction of Water System Projects | Water | - | - | a) | 9750000 | [12 empty] | See list of projects
|  |  | in Component LGUs | System |  |  | b) | Diosanta
[7 empty] | c) | PEO
[7 empty] | d) | -
|  |  | a. Installation of water System at Purok | Water | - | - | a) | 1125000 | a) | - | e) | - | a) | 1125000 | a) | - | c) | - | a) | - | For ammendment due to change of location.Waiting for deed of donation.
|  |  | Nangka, Pandapan, Tagum City | System |  |  | b) | - | b) | - | f) | - | b) | 1125000 | b) | - | d) | - | b) | -
[7 empty] | c) | PEO | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
|  |  | b. Rehab./Impv't. of San Vicente | Water | - | - | a) | 1125000 | a) | 10/26/18 | e) | - | a) | 1125000 | a) | - | c) | - | a) | - | Abstract on process
|  |  | Water System, Asuncion | System |  |  | b) | - | b) | - | f) | - | b) | 1125000 | b) | - | d) | - | b) | -
[7 empty] | c) | PEO | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
|  | 2. Counterpart to Special Projects (Provincewide) |  | Road | - | Contract | a) | 67415000 | [12 empty] | Investigation/Inspection of priority projects
[7 empty] | b) | Foronda
[7 empty] | c) | PEO
[7 empty] | d) | -
|  | 2.1 | Rehab. Of Sonlon-Camansa FMR, | Road | - | Contract | a) | 20,104,388.55 | a) | 09/18/18 | e) | - | a) | 20,104,388.55 | a) | - | c) | - | a) | - | NOL 1 approved dated June 29, 2018
|  |  | Asuncion, Davao del Norte |  |  |  | b) | - | b) | - | f) | - | b) | 20,104,388.55 | b) | - | d) | - | b) | - | Pre-procurement dated July 26, 2018
[7 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | Impv't. of K. 9 Sagayen-Sawata Prov'l. Rd. P 1,442,028.81
[7 empty] | d) |  | d) | -
|  | 3. Const./Rehab./Comp. of Various Gov't. Bldgs. |  | Bldgs. | - | Admin | a) | 13523124 | [12 empty] | Investigation/Inspection of priority projects
|  | Struct., Fac. (Provincewide) |  |  |  |  | b) | Foronda
[7 empty] | c) | PEO
[7 empty] | d) | -
|  | 3.1 | Rehab. Of PEO Training Center | Bldg. |  | Admin | a) | 326124 | a) | 02/12/19 | e) | - | a) | 326124 | a) | - | c) | - | a) | - | PO for accepatance of suppliers
|  |  | (PDPM),Mankilam, Tagum City |  |  |  | b) | - | b) | - | f) | - | b) |  | b) | - | d) | - | b) | -
|  |  | (Part of P803,000.00)(20% DF CY 2017-P476,876.00) |  |  |  | c) | PEO | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
|  | 3.2 | Construction of IP Tribal Council of | Bldg. |  | Admin | a) | 560,000.00 | a) | - | e) | - | a) | 560,000.00 | a) | - | c) | - | a) | - | POW & Plan for approval
|  |  | Women at Brgy. Camansa, Asuncion |  |  |  | b) | - | b) | - | f) | - | b) | 560,000.00 | b) | - | d) | - | b) | -
[7 empty] | c) | PEO | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
|  | 3.3 | Construction of Multi-Purpose Bldg. | Bldg. | 303.75 sq.m | Admin | a) | 6748000 | a) | 12/11/18 | e) | - | a) | 6748000 | a) | 71.15% | c) | 61.53% | a) | 25 | On-going
|  |  | (PENRO Building), Mankilam, Tagum City |  |  |  | b) | Pasiona/Juan | b) | 10/16/18 | f) | 34 CD | b) | 6748000 | b) | - | d) | -9.618% | b) | 750
|  |  | (Part of 8,548,000.00) |  |  |  | c) | PEO | c) | 05/25/19 | g) | - | c) | 6560497.45
|  |  | (P1,800,000.00 - SB # 3 CY 2017) |  |  |  | d) | 256 CD | d) | 06/30/19
|  | 4. Rural Electrification (Provincewide) |  | Elect. |  | Admin | a) | 5000000 | [12 empty] | See projects listed below
[7 empty] | b) | Kim Pao Lu
[7 empty] | c) | PEO
[7 empty] | d) | -
|  | 4.1 | Rural Electrification at Del Monte, | Elect. |  | Admin | a) | 1000000 | a) | - | e) | - | a) | 1000000 | a) | - | c) | - | a) | - | For PR
|  |  | New Corella |  |  |  | b) | - | b) | - | f) | - | b) | 1000000 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
|  | 4.2 | Const. of Distribution Line in Sitio Prk. 1,3,4, | Elect. |  | Admin | a) | 4000000 | a) | 11/06/18 | e) | - | a) | 4000000 | a) | - | c) | - | a) | - | For PR
|  |  | 11 and 7, Camansa, asuncion |  |  |  | b) | - | b) | - | f) | - | b) | 4000000 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
A. 20% Development Fund CY 2018 | K. | GENERAL FUND PROPER CY 2018
STIMULUS PROJECTS
ASUNCION
|  | 1 | Const. of Bleachers and Canopy, | Bldg. |  | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Fund transferred to LGU - July 5, 2019 with check no. 0134969 and OR no. 0504050
|  |  | Canantan, Asuncion |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
|  | 2 | Const. of Potable water System at Prk. 6, | Water |  | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Alloted- April 15, 2019 Fund transfer was processed but can not be transfer (Note: One funding only for fund transfer)
|  |  | New Santiago, Asuncion | System |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
|  | 3 | Const. of Canopy, Camoning, Asuncion | Bldg. |  | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Fund transferred to LGU - June 20, 2019 with check no. 0134424 and OR no. 0504038
[7 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
|  | 4 | Completion of Electrification at Prk. 10 | Elect. |  | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Alloted - June 18, 2019 Fund transfer on process but not completed last June 28, 2019
|  |  | & Prk. 9, Doña Andrea, Asuncion |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
|  | 5 | Construction of Covered Court, | Court |  | - | a) | 500000 | a) | 06/05/18 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Verified at PBO - June 18, 2019, Alloted last year.To PBO OBR - June 19, 2019, process for fund transfer but not completed last June 28, 2019
|  |  | San Vicente, Asuncion |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
|  | 6 | Landscaping and Beautification of | landscaping |  | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | for AIP amendment and change to new priority Comst. Of Multi-purpose covered court Phase 2
|  |  | Brgy. Ground, Pamacaun, Asuncion |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
NEW CORELLA
|  | 1 | Const. of Concrete Bleachers, Sta. Cruz, | Bleacher |  | - | a) | 500000 | a) | 06/04/18 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Fund transferred to LGU - May 23, 2019 with check no. 0133011 and OR no. 9232849
|  |  | New Corella |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
|  | 2 | Completion of Mini GYM at Prk. 2, | GYM |  | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Fund transferred to LGU - May 23, 2019 with check no. 0133010 and OR no. 9232850
|  |  | San Roque, New Corella |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
|  | 3 | Completion of Covered Court, Sto. Niño, | Court |  | - | a) | 500000 | a) |  | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Fund transferred to LGU - May 23, 2019 with check no. 0133012 and OR no. 9232848
|  |  | New Corella |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
|  | 4 | Construction of Public Market, Suawon, | Bldg. |  | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Fund transferred to LGU - May 23, 2019 with check no. 0133014 and OR no. 9232846
|  |  | New Corella |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
|  | 5 | Construction of Concrete Line Drainage at | Drainage |  | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Fund transferred to LGU - May 23, 2019 with Check No. 2575058 and OR No. 0342801
|  |  | Prk. 10 to Prk. 6, Del Pilar, New Corella |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
|  | 6 | Construction of Stage with Comfort Rooms | Bldg. |  | - | a) | 500000 | a) | 07/05/18 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Fund transferred to LGU - May 23, 2019 with check no. 0133013 and OR no. 9232847
|  |  | at Mesaoy Mini-Gym, Mesaoy, New Corella |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
TAGUM CITY
|  | 1 | Repair of Brgy. Hall, San Miguel, | Bldg. |  | Admin | a) | 500000 | a) | 10/26/18 | e) | 13 | a) | 500000 | a) | 100% | c) | 100% | a) | 4 | Completed
|  |  | Tagum City |  |  |  | b) | Mayang | b) | 03/04/19 | f) | 8 days | b) | 500000 | b) | - | d) | 0% | b) | 88
[7 empty] | c) | Admin | c) | 05/23/19 | g) | 6/14/19 | c) | 411,905.79
[7 empty] | d) | 50 CD | d) | -
|  | 2 | Completion of Two Storey Multi-Purpose | Bldg. |  | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | PR on process
|  |  | Building, Magugpo East, Tagum City |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
|  | 3 | Completion of GYM Bleacher w/ | Bleacher |  | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | PR on process
|  |  | Electrification, Pagsabangan, Tagum City |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
|  | 4 | Construction of Drainage Canal, | Drainage |  | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | PR on process
|  |  | Libuganon, Tagum City |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
KAPALONG
|  | 1 | Construction of Bleacher, Mamacao, | Bleacher |  | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | PR on process
|  |  | Kapalong |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
|  | 2 | Improvement of Capungagan GYM Stage, | Stage |  | - | a) | 500000 | a) | 06/05/18 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Declared savings
|  |  | Capungagan, Kapalong |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
|  | 3 | Construction of Concrete Perimeter Fence, | Fence |  | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | PLAN and POW For Gov.'s approval - June 26, 2019
|  |  | Luna, Kapalaong |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
|  | 4 | Construction of 1 Unit 2 Classroom | Bldg. |  | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | POW for review by Engr. Misa - July 4, 2019
|  |  | School Bldg. at Sampao, kapalong |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
|  | 5 | Completion of Brgy. Health Center, Maniki, | Bldg. |  | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Waiting for the approval of plan by the brgy. Capt. - May 7, 2019
|  |  | Kapalong |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
SAN ISIDRO
|  | 1 | Improvement of Water System, Sabangan, | Water |  | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Change priority not yet submitted new resolution
|  |  | San Isidro | System |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
|  | 2 | Rehabilitation & Flooring of Gymnasium | Court |  | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Alloted June 19, 2019/Procurement of materials on process
|  |  | Basketball Court, Mamangan, San Isidro |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
TALAINGOD
|  | 1 | Grouted Riprap on Embankment | Riprap |  | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Alloted - March 12, 2019 Fund transfer was processed but have mistakes in the POW preparation by MEO as check by PACCO
|  |  | Sto. Ñino, Talaingod |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
|  | 2 | Barangay Hall Improvement, Dagohoy, | Bldg. |  | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Not submitted plan & POW c/o MEO
|  |  | Talaingod |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
| L. | 5% Calamity Fund CY 2018
1. Prevention and Mitigation
|  | 1.1 Desiltation/Excavation of rivers and creeks |  | rivers |  | Admin | a) | 3000000 | [12 empty] | Investigation/Inspection of priority projects
[7 empty] | b) | -
[7 empty] | c) | PEO
[7 empty] | d) | -
|  | a. | Improvement and Desiltation of Tagum Creek (Phase I and Phase II) | Creek |  | Admin | a) | 2,000,000.00 | a) | 11/06/18 | e) | - | a) | 2,000,000.00 | a) | 17.28% | c) | 13.26% | a) | 5 | On-going.Change fund source to 5% Calamity Fund 2019-Rehab and Recovery. For AIP amendment, change project title to Desiltation of Tagum Creek
[7 empty] | b) | Mayang | b) | 03/22/19 | f) | - | b) | 2,000,000.00 | b) | - | d) | -4.02% | b) | 110
[7 empty] | c) | PEO | c) | 10/31/19 | g) | - | c) | -
[7 empty] | d) | 224 CD | d) | -
|  | 1.2 Improvement of Roads, Drainage & Canals |  | roads/canals |  | Admin | a) | 3000000 | [12 empty] | Investigation/Inspection of priority projects.
[7 empty] | b) | - | [12 empty] | Declared as savings
[7 empty] | c) | PEO
[7 empty] | d) | -
|  | a. | Rehab./Impv't. of Sonlon-Longanapan Road | road |  | Admin | a) | 1,500,000.00 | a) | - | e) | - | a) | 1,500,000.00 | a) | - | c) | - | a) | - | for implementation
[7 empty] | b) | - | b) | - | f) | - | b) | 1,500,000.00 | b) | - | d) | - | b) | -
[7 empty] | c) | PEO | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
|  | 1.3 Improvement of bridges and cross drainage |  | bridges/drainage |  | Admin | a) | 3000000 | [12 empty] | Declared as savings
[7 empty] | b) | -
[7 empty] | c) | PEO
[7 empty] | d) | -
|  | 2. Rehabilitation and Recovery |  | roads |  | Admin | a) | 2026000 | [12 empty] | Declared as savings
[7 empty] | b) | -
[7 empty] | c) | PEO
[7 empty] | d) | -
| M. | SUPPLEMENTAL BUDGET # 1 CY 2018 |  |  |  |  | a) | 6,000,000.00 | [12 empty] | See list of Provincial Roads
|  | 1 Const. in Progress - Infrastructure |  |  |  |  | b) | Paraguya
|  | Assets (Rehabilitation of Various |  |  |  |  | c) | PEO
|  | Provincial Roads) |  |  |  |  | d) | -
|  | 1 | Mesaoy - Jct. Mahayahay | Road |  | Admin | a) | 1,534,000.00 | a) | 07/19/18 | e) | - | a) | 1,534,000.00 | a) | 60% | c) | 60% | a) | - | Suspended as of Dec. 27, 2018
[7 empty] | b) | Salido | b) | 11/16/18 | f) | - | b) | 1,534,000.00 | b) | - | d) | - | b) | - | Cancellation of PO # 2018082439 and RE-PR
[7 empty] | c) | PEO | c) | 12/15/18 | g) | - | c) | -
[7 empty] | d) | - | d) | -
|  | 2 | Del Pilar - Jct. Silangan | Road |  | Admin | a) | 1,795,000.00 | a) | 07/19/18 | e) | - | a) | 1,795,000.00 | a) | 73.00% | c) | 73.00% | a) | 14 | On-going
[7 empty] | b) | Salido | b) | 10/16/18 | f) | - | b) | 1,795,000.00 | b) | - | d) | - | b) | 30 | Suspended as of January 4, 2019
[7 empty] | c) | PEO | c) | 11/20/18 | g) | - | c) | -
[7 empty] | d) | - | d) | -
| N. | SUPPLEMENTAL BUDGET # 2 CY 2018
1 Const./Compl./Impv't. of Various Gov't.
Bldgs., Structures & Facilities (Const. in
Progress - Bldgs. & Other Structures
|  | 1 | Const./Impv't. of DDN Hospital | Bldg. |  | - | a) | 5,000,000.00 | a) | - | e) | - | a) | 5,000,000.00 | a) | - | c) | - | a) | - | PR on process
|  |  | Kapalong Zone |  |  |  | b) | - | b) | - | f) | - | b) | 5,000,000.00 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
|  | 2 | Compl. Of Bahay Pag-Asa for Minors, | Bldg. |  | - | a) | 3,000,000.00 | a) | - | e) | - | a) | 3,000,000.00 | a) | - | c) | - | a) | - | PR on process
|  |  | New Corella |  |  |  | b) | - | b) | - | f) | - | b) | 3,000,000.00 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
|  | 3 | Upgrading of DAGOEMC Multi-Purpose | Bldg. |  | - | a) | 3,000,000.00 | a) | 09/04/18 | e) | - | a) | 3,000,000.00 | a) | 30.28% | c) | 30.28% | a) | 7 | Completed
|  |  | Bldg., Mankilam |  |  |  | b) | Chua | b) | 03/04/19 | f) | - | b) | 3,000,000.00 | b) | - | d) | +0.36% | b) | 210
[7 empty] | c) | PEO | c) | 07/26/19 | g) | - | c) | 1,537,217.00
[7 empty] | d) | 145 CD | d) | -
|  | 4 | Const. of Add'l. 2nd Level Multi-Purpose | Bldg. |  | - | a) | 7,592,588.00 | a) | - | e) | - | a) | 7,592,588.00 | a) | - | c) | - | a) | - | Preparation of POW & Plan c/o PDPM. Plan Completed, POW on-going
|  |  | HalI, PGSO warehouse,Bldg., Mankilam |  |  |  | b) | - | b) | - | f) | - | b) | 7,592,588.00 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
| O. | SUPPLEMENTAL BUDGET # 4 CY 2018
|  | 1 | Construction of Multi-Purpose Bldg. (PENRO Building) | Bldg. | 303.75 sq.m | Admin | a) | 1800000 | a) | 06/11/18 | e) | - | a) | 1800000 | a) | 61.53% | c) | 61.53% | a) | 25 | On-going
[7 empty] | b) | Pasiona/Juan | b) | 10/16/18 | f) | 34 CD | b) | 1800000 | b) | - | d) | 0% | b) | 750
|  |  | (Part of P8,548,000.00)(P1,800,000.00 - |  |  |  | c) | PEO | c) | 05/25/19 | g) | - | c) | 6129861.34
|  |  | SB # 4 CY 2018) |  |  |  | d) | 222 CD | d) | 06/30/19
| P. | SUPPLEMENTAL BUDGET # 5 CY 2018
STIMULUS CY 2018
|  | 1 | Const. of MP Hall, Rizal ES, Binancian, | Bldg. |  | - | a) | 1250000 | a) | 02/04/19 | e) | - | a) | 1250000 | a) | - | c) | - | a) | - | Fund transferred to LGUs - March 28, 2019 with Check No. 2574930 and OR No. 00296267
|  |  | Asuncion |  |  |  | b) | - | b) | - | f) | - | b) | 1250000 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
|  | 2 | Const. of MP Hall, Liguyon ES, Binancian, | Bldg. |  | - | a) | 1250000 | a) | 02/04/19 | e) | - | a) | 1250000 | a) | - | c) | - | a) | - | Fund transferred to LGUs - March 28, 2019 with Check No. 2574929 and OR No. 0296266
|  |  | Asuncion |  |  |  | b) | - | b) | - | f) | - | b) | 1250000 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
|  | 3 | Rehab./Impv't. of MP Bldg. (Gym), Napungas, | GYM |  | - | a) | 500000 | a) | 02/04/19 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Alloted Feb. 10, 2019 - Fund transfer was processed but not completed, no liquidation submitted from previous fund transferred as per PACCO
|  |  | Asuncion |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | x
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
| Q. | OPPAP-PAMANA
1. TRIBAL HALLS
|  | 1.1 | Construction of Tribal Hall, Brgy. Gupitan, | Bldg. |  | Admin | a) | 500000 | a) | 08/15/18 | e) | - | a) | 500000 | a) | 100% | c) | 100% | a) | 5 | Completed
|  |  | Kapalong |  |  |  | b) | Ambrucio | b) | 02/22/19 | f) | 20 CD | b) | 500000 | b) | - | d) | 0% | b) | 150
[7 empty] | c) | PEO | c) | 05/02/19 | g) | 05/22/19 | c) | 379,423.83
[7 empty] | d) | 20 CD | d) | 05/22/19
2. PROCESSING AND BAGSAKAN CENTER
|  | 2.1 | Const. of Processing and Bagsakan Center, | Bldg. | 300 sq.m | Contract | a) | 2500000 | a) | 08/15/18 | e) | - | a) | 2500000 | a) | 100.00% | c) | 80% | a) | 6 | On-going
|  |  | Brgy. Palma Gil, Talaingod |  |  |  | b) | Dadula | b) | 02/02/19 | f) | 35 CD | b) | 2500000 | b) | 89.91% | d) | -9.91% | b) | 180
[7 empty] | c) | Alpha & Omega | c) | 05/12/19 | g) | 6/16/19 | c) | 138339.66
[7 empty] | d) | 100 CD | d) | -
|  | 2.2 | Const. of Processing and Bagsakan Center, | Bldg. | 300 sq.m | Contract | a) | 2500000 | a) | 08/15/18 | e) | - | a) | 2500000 | a) | 100% | c) | 100% | a) | 4 | Completed
|  |  | Brgy. Sto. Nino, Talaingod |  |  |  | b) | Dadula | b) | 12/28/18 | f) | - | b) | 2500000 | b) | - | d) | 0% | b) | 120
[7 empty] | c) | RLHV | c) | 05/22/19 | g) | - | c) | 1,309,118.57
[7 empty] | d) | 145 CD | d) | -
|  | 2.3 | Const. of Processing and Bagsakan Center, | Bldg. |  | Contract | a) | 2500000 | a) | - | e) | - | a) | 2500000 | a) | - | c) | - | a) | - | Change of location
|  |  | Brgy. Dagohoy, Talaingod |  |  |  | b) | - | b) | - | f) | - | b) | 2500000 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
|  | 2.4 | Const. of Processing and Bagsakan Center, | Bldg. | 300 sq.m | Contract | a) | 2500000 | a) | 08/29/18 | e) | - | a) | 2500000 | a) | 100% | c) | 85% | a) | 6 | On-going
|  |  | Brgy. Gupitan, Kapalong, Davao del Norte |  |  |  | b) | Ambrucio | b) | 02/12/19 | f) | - | b) | 2500000 | b) | - | d) | -15% | b) | 180
[7 empty] | c) | Alpha & Omega | c) | 05/12/19 | g) | - | c) | 156000
[7 empty] | d) | 120 CD | d) | -
3. SOLAR DRYER
|  | 3.1 | Post Harvest Facilities (Corn Mill, Solar Dryer, | Bldg. |  | Contract | a) | 1500000 | a) | - | e) | - | a) | 1500000 | a) | - | c) | - | a) | - | For implementation, Corn Sheller is already delivered in the area and used by the beneficiaries
|  |  | Corn Sheller), Kapalong, Davao del Norte |  |  |  | b) | - | b) | - | f) | - | b) | 1500000 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | 391970.93
[7 empty] | d) | - | d) | -
|  | 3.2 | Post Harvest Facilities (Corn Mill, Solar Dryer, Corn Sheller), Talaingod, Davao del Norte | Bldg. |  | Contract | a) | 500,000.00 | a) | - | e) | - | a) | 500,000.00 | a) | - | c) | - | a) | - | For implementation. For Land Preparation (Mountaneous Area)
[7 empty] | b) | - | b) | - | f) | - | b) | 500,000.00 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | 201520.22
[7 empty] | d) | - | d) | -
4. TRADING POST STORAGE
|  | 4.1 | Trading Post, Storage and Hauling Truck, Pandapan, Tagum City | Bldg. |  | Contract | a) | 4000000 | a) | - | e) | - | a) | 4000000 | a) | - | c) | - | a) | - | Re-bidding
[7 empty] | b) | - | b) | - | f) | - | b) | 4000000 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
5. WATER SYSTEM
|  | 5.1 | Upgrading of Existing PWS Level II in Sitio Langan, Gupitan, Kapalong | PWS |  | Admin | a) | 2500000 | a) | 08/14/19 | e) | - | a) | 2500000 | a) | 47.19% | c) | 48.00% | a) | 7 | On-going. Waiting for the completion of on-going construction of Bridge and Road Widening(DPWH) -Pipes already at site
[7 empty] | b) | Diosanta | b) | 03/25/19 | f) | - | b) | 2500000 | b) | - | d) | +0.81% | b) | 210
[7 empty] | c) | PEO | c) | 09/19/19 | g) | - | c) | 639,621.25
[7 empty] | d) | 162 CD | d) | -
|  | 5.2 | Upgrading of Existing PWS Level II in Sitio Patel 2, Gupitan, Kapalong | PWS |  | Admin | a) | 2500000 | a) | - | e) | - | a) | 2500000 | a) | - | c) | 48% | a) | -
[7 empty] | b) | - | b) | - | f) | - | b) | 2500000 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
|  | 5.3 | Construction of PWS Level II in Purok 7-A and 7-B, Capungagan, Kapalong | PWS |  | Admin | a) | 1000000 | a) | 11/12/18 | e) | - | a) | 1000000 | a) | - | c) | - | a) | - | Notice on Award on process
[7 empty] | b) | - | b) | - | f) | - | b) | 1000000 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
|  | 5.4 | Construction of PWS Level II in Purok 2, Pag-asa, Kapalong | PWS |  | Admin | a) | 1000000 | a) | 11/12/18 | e) | - | a) | 1000000 | a) | - | c) | - | a) | - | Notice on Award on process
[7 empty] | b) | - | b) | - | f) | - | b) | 1000000 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
|  | 5.5 | Construction of PWS Level II in Sitio Upper Dulyan, Palma Gil, Talaingod, DDN | PWS |  | Admin | a) | 1000000 | a) | - | e) | - | a) | 1000000 | a) | - | c) | - | a) | - | For POW revision. To include Manual Handling of Construction Materials to POW
[7 empty] | b) | - | b) | - | f) |  | b) | 1000000 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
6. CATTLE PRODUCTION
|  | 6.1 | Cattle Production- Brgy. Tiburcia, Gupitan and Semong, Kapalong | Bldg. |  | Admin | a) | 1500000 | a) | - | e) | - | a) | 1500000 | a) | - | c) | - | a) | - | For cancellation. A letter was sent to OPAPP last Dec 2018 requesting to allow us to reduce the number of cattle but we are still hoping that there would be a supplier will bid
[7 empty] | b) | - | b) | - | f) | - | b) | 1500000 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
|  | 6.2 | Cattle Production, Brgy. Palma Gil, Brgy. Sto. Nino, Brgy. Dagohoy, Talaingod, Davao del Norte | Bldg. |  | Admin | a) | 1500000 | a) | - | e) | - | a) | 1500000 | a) | - | c) | - | a) | - | For cancellation. A letter was sent to OPAPP last Dec 2018 requesting to allow us to reduce the number of cattle but we are still hoping that there would be a supplier will bid
[7 empty] | b) | - | b) | - | f) | - | b) | 1500000 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
7. RICE MILL FOR UPLAND RICE
|  | 7.1 | Rice Mill for Upland Rice, Palma Gil, Talaingod | Bldg. |  | Admin | a) | 1000000 | a) | - | e) | - | a) | 1000000 | a) | - | c) | - | a) | - | for implementation
[7 empty] | b) | - | b) | - | f) | - | b) | 1000000 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
|  | 7.2 | Rice Mill for Upland Rice, Palma Gil, Talaingod | Bldg. |  | Admin | a) | 1000000 | a) | - | e) | - | a) | 1000000 | a) | - | c) | - | a) | - | for implementation
[7 empty] | b) | - | b) | - | f) | - | b) | 1000000 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
| R. | LOCAL GOVERNMENT SUPPORT FUND (LGSF) CY 2018
|  | 1 | Road Upgrading of San Vicente - Butay Provincial Road | Road |  | Contract | a) | 19949581.18 | a) | CY 2018 | e) | - | a) | 19949581.18 | a) | 96.55% | c) | 76.22% | a) | 18 | On-going
[7 empty] | b) | Aclaracion | b) | 11/19/18 | f) | 28 CD | b) | 19949581.18 | b) | 75.33% | d) | +0.89% | b) | 396
[7 empty] | c) | Alpha & Omega | c) | 06/08/19 | g) | - | c) | 9,685,667.31
[7 empty] | d) | 202 CD | d) | 07/06/19
| S. | QUICK RESPOND FUND CY 2016
|  | 1 | Rehab. Of Slope Protection of Libuganon River Along Kapalong - Mabantao - Florida Prov'l. Road Phase I | Road |  | - | a) | 900000 | a) | - | e) | - | a) | 900000 | a) | - | c) | - | a) | - | For AIP Amendment
[7 empty] | b) | - | b) | - | f) | - | b) | 900000 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
II. PROJECTS UNDER THE CURRENT APPROPRIATION CY 2019
A. GENERAL FUND CY 2019 | [5 empty] | MBA/CBRMC | a) | 18127866 | a) | 01/03/19 | e) | - | a) | 18127866 | a) | 35.90% | c) | 35.90% | a) | 46 | See list of Provincial Roads
Road ID |  | 1. Maintenance Of Various Prov'l. Roads and Bridges |  | Road Maintenance | KM |  | b) | Paraguya | b) | 01/03/19 | f) | - | b) | 18127866 | b) | - | d) | - | b) | 920
[5 empty] | 288.26 |  | c) | PEO/CBRMC | c) | 12/31/19 | g) | - | c) | -
11DAN | [8 empty] | d) | -
[7 empty] | d) | 261 days | d) | -
|  | Jct. Highway Magatos - New Bantayan |  | Road Maintenance | 7.1 | MBA | a) | 287307.39 | a) | 01/03/19 | e) | - | a) | 287307.39 | a) | 43.86% | c) | 43.86% | a) | 15 | On-going
001 | [6 empty] | b) | Crucio | b) | 01/16/19 | f) | - | b) | 287307.39 | b) | - | d) | - | b) | 480
[7 empty] | c) | PEO | c) | 12/31/19 | g) | - | c) | 114,969.26
[7 empty] | d) | - | d) | -
|  | Jct. Highway Magatos - New Bantayan |  | Road Maintenance | 7.1 | CBRMC | a) | 223674.22 | a) | 01/03/19 | e) | - | a) | 223674.22 | a) | 25.00% | c) | 25.00% | a) | 16 | On-going
001 | [6 empty] | b) | Crucio | b) | 3/22/19 | f) | - | b) | 223674.22 | b) | - | d) | - | b) | 480
[7 empty] | c) | CALAFA | c) | 12/31/19 | g) | - | c) | -
[7 empty] | d) | 3 quarters | d) | -
|  | Magatos-Bdry Pagsabangan |  | Road Maintenance | 8.33 | MBA | a) | 328740.25 | a) | 01/03/19 | e) | - | a) | 328740.25 | a) | 43.29% | c) | 43.29% | a) | 15 | On-going
002 | [6 empty] | b) | Crucio | b) | 01/03/19 | f) | - | b) | 328740.25 | b) | - | d) | - | b) | 450
[7 empty] | c) | PEO | c) | 12/31/19 | g) | - | c) | 140,817.08
[7 empty] | d) | - | d) | -
|  | Magatos-Bdry Pagsabangan |  | Road Maintenance | 8.33 | CBRMC | a) | 270763.53 | a) | 01/03/19 | e) | - | a) | 270763.53 | a) | 25.00% | c) | 25.00% | a) | 16 | On-going
002 | [6 empty] | b) | Crucio | b) | 03/22/19 | f) | - | b) | 270763.53 | b) | - | d) | - | b) | 450
[7 empty] | c) | CALAFA | c) | 12/31/19 | g) | - | c) | -
[7 empty] | d) | 3 quarters | d) | -
|  | Ilog-New Bantayan |  | Road Maintenance | 2.68 | MBA | a) | 131131.39 | a) | 01/03/19 | e) | - | a) | 131131.39 | a) | 42.62 | c) | 42.62% | a) | 15 | On-going
003 | [6 empty] | b) | Crucio | b) | 01/16/19 | f) | - | b) | 131131.39 | b) | - | d) | - | b) | 450
[7 empty] | c) | PEO | c) | 12/31/19 | g) | - | c) | 49,316.69
[7 empty] | d) | - | d) | -
|  | Ilog-New Bantayan |  | Road Maintenance | 2.68 | CBRMC | a) | 65925.03 | a) | 01/03/19 | e) | - | a) | 65925.03 | a) | 25.00% | c) | 25.00% | a) | 16 | On-going
003 | [6 empty] | b) | Crucio | b) | 03/22/19 | f) | - | b) | 65925.03 | b) | - | d) | - | b) | 450
[7 empty] | c) | CALAFA | c) | 12/31/19 | g) | - | c) | -
[7 empty] | d) | 3 quarters | d) | -
|  | Asuncion -Monte Carlo-Del Pilar |  | Road Maintenance | 9.93 | MBA | a) | 474102.88 | a) | 01/03/19 | e) | - | a) | 474102.88 | a) | 53.01 | c) | 53.01 | a) | 15 | On-going
005 | [6 empty] | b) | Crucio | b) | 01/03/19 | f) | - | b) | 474102.88 | b) | - | d) | - | b) | 450
[7 empty] | c) | PEO | c) | 12/31/19 | g) | - | c) | 257274.49
[7 empty] | d) | - | d) | -
|  | Asuncion -Monte Carlo-Del Pilar |  | Road Maintenance | 9.93 | CBRMC | a) | 355524.28 | a) | 01/03/19 | e) | - | a) | 355524.28 | a) | 25.00% | c) | 25.00% | a) | 16 | On-going
005 | [6 empty] | b) | Crucio | b) | 03/22/19 | f) | - | b) | 355524.28 | b) | - | d) | - | b) | 450
[7 empty] | c) | MAHAYAHAY IFA | c) | 12/31/19 | g) | - | c) | -
[7 empty] | d) | 3 quarters | d) | -
|  | Jct. Highway Canatan-Jct. Highway Magatos |  | Road Maintenance | 4.85 | MBA | a) | 209808.59 | a) | 01/03/19 | e) | - | a) | 209808.59 | a) | 46.34% | c) | 46.34% | a) | 15 | On-going
006 | [6 empty] | b) | Crucio | b) | 02/18/19 | f) | - | b) | 209808.59 | b) | - | d) | - | b) | 450
[7 empty] | c) | PEO | c) | 12/31/19 | g) | - | c) | 80652.8
[7 empty] | d) | - | d) | -
|  | Jct. Highway Canatan-Jct. Highway Magatos |  | Road Maintenance | 4.85 | CBRMC | a) | 162458.12 | a) | 01/03/19 | e) | - | a) | 162458.12 | a) | 25.00% | c) | 25.00% | a) | 16 | On-going
006 | [6 empty] | b) | Crucio | b) | 03/22/19 | f) | - | b) | 162458.12 | b) | - | d) | - | b) | 450
[7 empty] | c) | CAMODA | c) | 12/31/19 | g) | - | c) | -
[7 empty] | d) | 3 quarters | d) | -
|  | Sta. Felomina-San Roque |  | Road Maintenance | 7.68 | MBA | a) | 147439.63 | a) | 01/03/19 | e) | - | a) | 147439.63 | a) | 44.56% | c) | 44.56% | a) | 15 | On-going
008 | [6 empty] | b) | Crucio | b) | 01/16/19 | f) | - | b) | 147439.63 | b) | - | d) | - | b) | 450
[7 empty] | c) | PEO | c) | 12/31/19 | g) | - | c) | 63806.67
[7 empty] | d) | - | d) | -
|  | Sta. Felomina-San Roque |  | Road Maintenance | 7.68 | CBRMC | a) | 261345.67 | a) | 01/03/19 | e) | - | a) | 261345.67 | a) | 25.00% | c) | 25.00% | a) | 16 | On-going
008 | [6 empty] | b) | Crucio | b) | 03/25/19 | f) | - | b) | 261345.67 | b) | - | d) | - | b) | 450
[7 empty] | c) | STAFFA | c) | 12/31/19 | g) | - | c) | -
[7 empty] | d) | 3 quarters | d) | -
|  | Saug-Sonlon-Bdy Longanapan |  | Road Maintenance | 11.6 | MBA | a) | 568486.36 | a) | 01/03/19 | e) | - | a) | 568486.36 | a) | 50.76% | c) | 50.76% | a) | 15 | On-going
010 | [6 empty] | b) | Crucio | b) | 01/16/19 | f) | - | b) | 568486.36 | b) | - | d) | - | b) | 450
[7 empty] | c) | PEO | c) | 12/31/19 | g) | - | c) | 262900.22
[7 empty] | d) | - | d) | -
|  | Saug-Sonlon-Bdy Longanapan |  | Road Maintenance | 11.6 | CBRMC | a) | 185565.56 | a) | 01/03/19 | e) | - | a) | 185565.56 | a) | 25.00% | c) | 25.00% | a) | 16 | On-going
010 | [6 empty] | b) | Crucio | b) | 03/26/19 | f) | - | b) | 185565.56 | b) | - | d) | - | b) | 450
[7 empty] | c) | BINANCIAN LIVESTOCK AFA | c) | 12/31/19 | g) | - | c) | -
[7 empty] | d) | 3 quarters | d) | -
|  | Jct. New Visayas-Buan |  | Road Maintenance | 2.99 | MBA | a) | 79238.27 | a) | 01/03/19 | e) | - | a) | 79238.27 | a) | 43.58% | c) | 43.58% | a) | 15 | On-going
011 | [6 empty] | b) | Crucio | b) | 02/18/19 | f) | - | b) | 79238.27 | b) | - | d) | - | b) | 450
[7 empty] | c) | PEO | c) | 12/31/19 | g) | - | c) | 14682.85
[7 empty] | d) | - | d) | -
|  | Jct. New Visayas-Buan |  | Road Maintenance | 2.99 | CBRMC | a) | 101242.01 | a) | 01/03/19 | e) | - | a) | 101242.01 | a) | 25.00% | c) | 25.00% | a) | 16 | On-going
011 | [6 empty] | b) | Crucio | b) | 03/22/19 | f) | - | b) | 101242.01 | b) | - | d) | - | b) | 450
[7 empty] | c) | BUAN IFA | c) | 12/31/19 | g) | - | c) | -
[7 empty] | d) | 3 quarters | d) | -
|  | San Vicente - Butay |  | Road Maintenance | 7.52 | MBA | a) | 209624.2 | a) | 01/03/19 | e) | - | a) | 209624.2 | a) | 30.99% | c) | 30.99% | a) | 15 | On-going
013 | [6 empty] | b) | Crucio | b) | 02/18/19 | f) | - | b) | 209624.2 | b) | - | d) | - | b) | 450
[7 empty] | c) | PEO | c) | 12/31/19 | g) | - | c) | 56,080.29
[7 empty] | d) | - | d) | -
|  | San Vicente - Butay |  | Road Maintenance | 7.52 | CBRMC | a) | 227205.88 | a) | 01/03/19 | e) | - | a) | 227205.88 | a) | 25.00% | c) | 25.00% | a) | 16 | On-going
013 | [6 empty] | b) | Crucio | b) | 03/27/19 | f) | - | b) | 227205.88 | b) | - | d) | - | b) | 450
[7 empty] | c) | SVMODA | c) | 12/31/19 | g) | - | c) | -
[7 empty] | d) | 3 quarters | d) | -
|  | Jct. Highway Doña Andrea - Capungagan |  | Road Maintenance | 8.7 | MBA | a) | 230835.16 | a) | 01/03/19 | e) | - | a) | 230835.16 | a) | 30.25% | c) | 30.25% | a) | 15 | On-going
014 | [6 empty] | b) | Crucio | b) | 02/18/19 | f) | - | b) | 230835.16 | b) | - | d) | - | b) | 450
[7 empty] | c) | PEO | c) | 12/31/19 | g) | - | c) | 60,629.26
[7 empty] | d) | - | d) | -
|  | Jct. Highway Doña Andrea - Capungagan |  | Road Maintenance | 8.7 | CBRMC | a) | 294308.14 | a) | 01/03/19 | e) | - | a) | 294308.14 | a) | 25.00% | c) | 25.00% | a) | 16 | On-going
014 | [6 empty] | b) | Crucio | b) | 03/28/19 | f) | - | b) | 294308.14 | b) | - | d) | - | b) | 450
[7 empty] | c) | CAPUNGAGAN MPC | c) | 12/31/19 | g) | - | c) | -
[7 empty] | d) | 3 quarters | d) | -
|  | Semong-Palma Gil |  | Road Maintenance | 2.73 | MBA | a) | 147289.98 | a) | 01/03/19 | e) | - | a) | 147289.98 | a) | 36.38% | c) | 36.38% | a) | 15 | On-going
018 | [6 empty] | b) | Crucio | b) | 02/18/19 | f) | - | b) | 147289.98 | b) | - | d) | - | b) | 450
[7 empty] | c) | PEO | c) | 12/31/19 | g) | - | c) | 71745.43
[7 empty] | d) | - | d) | -
|  | Semong-Palma Gil |  | Road Maintenance | 2.73 | CBRMC | a) | 49186.05 | a) | 01/03/19 | e) | - | a) | 49186.05 | a) | 25.00% | c) | 25.00% | a) | 16 | On-going
018 | [6 empty] | b) | Crucio | b) | 03/22/19 | f) | - | b) | 49186.05 | b) | - | d) | - | b) | 450
[7 empty] | c) | PALMA GIL FA | c) | 12/31/19 | g) | - | c) | -
[7 empty] | d) | 3 quarters | d) | -
|  | Daligdigon - Dagohoy |  | Road Maintenance | 3.34 | MBA | a) | 148835.45 | a) | 01/03/19 | e) | - | a) | 148835.45 | a) | - | c) | - | a) | - | Schedule for 1st Quarter
020 | [6 empty] | b) | Crucio | b) | - | f) | - | b) | 148835.45 | b) | - | d) | - | b) | -
[7 empty] | c) | PEO | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
|  | Daligdigon - Dagohoy |  | Road Maintenance | 3.34 | CBRMC | a) | 68279.5 | a) | 01/03/19 | e) | - | a) | 68279.5 | a) | 25.00% | c) | 25.00% | a) | 16 | On-going
020 | [6 empty] | b) | Crucio | b) | 03/22/19 | f) | - | b) | 68279.5 | b) | - | d) | - | b) | 450
[7 empty] | c) | PALMA GIL FA | c) | 12/31/19 | g) | - | c) | -
[7 empty] | d) | 3 quarters | d) | -
|  | Jct. Sampao-Bdry. Mamacao |  | Road Maintenance | 4.98 | MBA | a) | 154200.78 | a) | 01/03/19 | e) | - | a) | 154200.78 | a) | 33.42% | c) | 33.42% | a) | 15 | On-going
025 | [6 empty] | b) | Crucio | b) | 02/18/19 | f) | - | b) | 154200.78 | b) | - | d) | - | b) | 450
[7 empty] | c) | PEO | c) | 12/31/19 | g) | - | c) | 24,296.87
[7 empty] | d) | - | d) | -
|  | Jct. Sampao-Bdry. Mamacao |  | Road Maintenance | 4.98 | CBRMC | a) | 169521.51 | a) | 01/03/19 | e) | - | a) | 169521.51 | a) | 25.00% | c) | 25.00% | a) | 16 | On-going
025 | [6 empty] | b) | Crucio | b) | 03/26/19 | f) | - | b) | 169521.51 | b) | - | d) | - | b) | 450
[7 empty] | c) | AMS KAPALONG | c) | 12/31/19 | g) | - | c) | -
[7 empty] | d) | 3 quarters | d) | -
|  | Jct. Highway Luna-Mamacao-Narra |  | Road Maintenance | 9.17 | MBA | a) | 357957.66 | a) | 01/03/19 | e) | - | a) | 357957.66 | a) | 35.77% | c) | 35.77% | a) | 15 | On-going
026 | [6 empty] | b) | Crucio | b) | 02/18/19 | f) | - | b) | 357957.66 | b) | - | d) | - | b) | 450
[7 empty] | c) | PEO | c) | 12/31/19 | g) | - | c) | 127,996.16
[7 empty] | d) | - | d) | -
|  | Jct. Highway Luna-Mamacao-Narra |  | Road Maintenance | 9.17 | CBRMC | a) | 313143.91 | a) | 01/03/19 | e) | - | a) | 313143.91 | a) | 25.00% | c) | 25.00% | a) | 16 | On-going
026 | [6 empty] | b) | Crucio | b) | 03/26/19 | f) | - | b) | 313143.91 | b) | - | d) | - | b) | 450
[7 empty] | c) | AMS KAPALONG | c) | 12/31/19 | g) | - | c) | -
[7 empty] | d) | 3 quarters | d) | -
|  | Jct. Gabuyan-Katipunan-Bucana |  | Road Maintenance | 5.89 | MBA | a) | 294403.23 | a) | 01/03/19 | e) | - | a) | 294403.23 | a) | 34.15% | c) | 34.15% | a) | 15 | On-going
027 | [6 empty] | b) | Crucio | b) | 02/18/19 | f) | - | b) | 294403.23 | b) | - | d) | - | b) | 450
[7 empty] | c) | PEO | c) | 12/31/19 | g) | - | c) | 126,179.97
[7 empty] | d) | - | d) | -
|  | Jct. Gabuyan-Katipunan-Bucana |  | Road Maintenance | 5.89 | CBRMC | a) | 129495.6 | a) | 01/03/19 | e) | - | a) | 129495.6 | a) | 25.00% | c) | 25.00% | a) | 16 | On-going
027 | [6 empty] | b) | Crucio | b) | 03/26/19 | f) | - | b) | 129495.6 | b) | - | d) | - | b) | 450
[7 empty] | c) | MANGULIBAS FA | c) | 12/31/19 | g) | - | c) | -
[7 empty] | d) | 3 quarters | d) | -
|  | Capungagan-Mabuhay-Pandulian |  | Road Maintenance | 5.57 | MBA | a) | 294917.73 | a) | 01/03/19 | e) | - | a) | 294917.73 | a) | 10.55% | c) | 10.55% | a) | 15 | On-going
028 | [6 empty] | b) | Crucio | b) | 02/18/19 | f) | - | b) | 294917.73 | b) | - | d) | - | b) | 450
[7 empty] | c) | PEO | c) | 12/31/19 | g) | - | c) | -
[7 empty] | d) | - | d) | -
|  | Capungagan-Mabuhay-Pandulian |  | Road Maintenance | 5.57 | CBRMC | a) | 105950.95 | a) | 01/03/19 | e) | - | a) | 105950.95 | a) | 25.00% | c) | 25.00% | a) | 16 | On-going
028 | [6 empty] | b) | Crucio | b) | 03/28/19 | f) | - | b) | 105950.95 | b) | - | d) | - | b) | 450
[7 empty] | c) | CAPUNGAGAN MPC | c) | 12/31/19 | g) | - | c) | -
[7 empty] | d) | 3 quarters | d) | -
|  | Florida - New Boholano |  | Road Maintenance | 2.54 | MBA | a) | 95863.17 | a) | 01/03/19 | e) | - | a) | 95863.17 | a) | 39.30% | c) | 39.30% | a) | 15 | On-going
030 | [6 empty] | b) | Crucio | b) | 02/18/19 | f) | - | b) | 95863.17 | b) | - | d) | - | b) | 450
[7 empty] | c) | PEO | c) | 12/31/19 | g) | - | c) | 31,418.99
[7 empty] | d) | - | d) | -
|  | Florida - New Boholano |  | Road Maintenance | 2.54 | CBRMC | a) | 47425.27 | a) | 01/03/19 | e) | - | a) | 47425.27 | a) | 25.00% | c) | 25.00% | a) | 16 | On-going
030 | [6 empty] | b) | Crucio | b) | 03/28/19 | f) | - | b) | 47425.27 | b) | - | d) | - | b) | 450
[7 empty] | c) | SUPRA | c) | 12/31/19 | g) | - | c) | -
[7 empty] | d) | 3 quarters | d) | -
|  | Jct. New Boholano - New Loon |  | Road Maintenance | 4.77 | MBA | a) | 140549.84 | a) | 01/03/19 | e) | - | a) | 140549.84 | a) | 34.35% | c) | 34.35% | a) | 15 | On-going
031 | [6 empty] | b) | Crucio | b) | 02/18/19 | f) | - | b) | 140549.84 | b) | - | d) | - | b) | 450
[7 empty] | c) | PEO | c) | 12/31/19 | g) | - | c) | 40,056.38
[7 empty] | d) | - | d) | -
|  | Jct. New Boholano - New Loon |  | Road Maintenance | 4.77 | CBRMC | a) | 169521.51 | a) | 01/03/19 | e) | - | a) | 169521.51 | a) | 25.00% | c) | 25.00% | a) | 16 | On-going
031 | [6 empty] | b) | Crucio | b) | 03/28/19 | f) | - | b) | 169521.51 | b) | - | d) | - | b) | 450
[7 empty] | c) | NEW LOON FA | c) | 12/31/19 | g) | - | c) | -
[7 empty] | d) | 3 quarters | d) | -
|  | Florida-Suaon-Jct. Gupitan |  | Road Maintenance | 15.57 | MBA | a) | 707038.05 | a) | 01/03/19 | e) | - | a) | 707038.05 | a) | 46.24% | c) | 46.24% | a) | 15 | On-going
032 | [6 empty] | b) | Crucio | b) | 01/16/19 | f) | - | b) | 707038.05 | b) | - | d) | - | b) | 450
[7 empty] | c) | PEO | c) | 12/31/19 | g) | - | c) | 226,.062.60
[7 empty] | d) | - | d) | -
|  | Florida-Suaon-Jct. Gupitan |  | Road Maintenance | 15.57 | CBRMC | a) | 419094.85 | a) | 01/03/19 | e) | - | a) | 419094.85 | a) | 25.00% | c) | 25.00% | a) | 16 | On-going
032 | [6 empty] | b) | Crucio | b) | 03/28/19 | f) | - | b) | 419094.85 | b) | - | d) | - | b) | 450
[7 empty] | c) | SUPRA | c) | 12/31/19 | g) | - | c) | -
[7 empty] | d) | 3 quarters | d) | -
|  | Km. 15, Kipalili-New Loon |  | Road Maintenance | 6.93 | MBA | a) | 367659.97 | a) | 01/03/19 | e) | - | a) | 367659.97 | a) | 32.97% | c) | 32.97% | a) | 15 | On-going
034 | [6 empty] | b) | Crucio | b) | 02/01/19 | f) | - | b) | 367659.97 | b) | - | d) | - | b) | 450
[7 empty] | c) | PEO | c) | 12/31/19 | g) | - | c) | 112,175.78
[7 empty] | d) | - | d) | -
|  | Km. 15, Kipalili-New Loon |  | Road Maintenance | 6.93 | CBRMC | a) | 237801.01 | a) | 01/03/19 | e) | - | a) | 237801.01 | a) | 25.00% | c) | 25.00% | a) | 16 | On-going
034 | [6 empty] | b) | Crucio | b) | 03/26/19 | f) | - | b) | 237801.01 | b) | - | d) | - | b) | 480
[7 empty] | c) | KIPALILI FA | c) | 12/31/19 | g) | - | c) | -
[7 empty] | d) | 3 quarters | d) | -
|  | Jct. Suaon-Libuton |  | Road Maintenance | 7.26 | MBA | a) | 44015.68 | a) | 01/03/19 | e) | - | a) | 44015.68 | a) | 16.82% | c) | 16.82% | a) | 15 | On-going
035 | [6 empty] | b) | Crucio | b) | 01/16/19 | f) | - | b) | 44015.68 | b) | - | d) | - | b) | 450
[7 empty] | c) | PEO | c) | 12/31/19 | g) | - | c) | 24,980.86
[7 empty] | d) | - | d) | -
|  | Jct. Suaon-Libuton |  | Road Maintenance | 7.26 | CBRMC | a) | 91664.91 | a) | 01/03/19 | e) | - | a) | 91664.91 | a) | 25.00% | c) | 25.00% | a) | 16 | On-going
035 | [6 empty] | b) | Crucio | b) | 03/22/19 | f) | - | b) | 91664.91 | b) | - | d) | - | b) | 480
[7 empty] | c) | AALLI | c) | 12/31/19 | g) | - | c) | -
[7 empty] | d) | 3 quarters | d) | -
|  | Datu Balong - Pinamuno |  | Road Maintenance | 2.74 | MBA | a) | 95458.24 | a) | 01/03/19 | e) | - | a) | 95458.24 | a) | 37.38% | c) | 37.38% | a) | 15 | On-going
040 | [6 empty] | b) | Crucio | b) | 03/01/19 | f) | - | b) | 95458.24 | b) | - | d) | - | b) | 450
[7 empty] | c) | PEO | c) | 12/31/19 | g) | - | c) | 12,625.00
[7 empty] | d) | - | d) | -
|  | Datu Balong - Pinamuno |  | Road Maintenance | 2.74 | CBRMC | a) | 63570.57 | a) | 01/03/19 | e) | - | a) | 63570.57 | a) | 25.00% | c) | 25.00% | a) | 16 | On-going
040 | [6 empty] | b) | Crucio | b) | 03/28/19 | f) | - | b) | 63570.57 | b) | - | d) | - | b) | 480
[7 empty] | c) | DATU BALONG FA | c) | 12/31/19 | g) | - | c) | -
[7 empty] | d) | 3 quarters | d) | -
|  | Sawata - Mamangan - Pinamuno |  | Road Maintenance | 14.48 | MBA | a) | 545390.17 | a) | 01/03/19 | e) | - | a) | 545390.17 | a) | 35.31% | c) | 35.31% | a) | 15 | On-going
041 | [6 empty] | b) | Crucio | b) | 02/01/19 | f) | - | b) | 545390.17 | b) | - | d) | - | b) | 450
[7 empty] | c) | PEO | c) | 12/31/19 | g) | - | c) | 196,076.60
[7 empty] | d) | - | d) | -
|  | Sawata - Mamangan - Pinamuno |  | Road Maintenance | 14.48 | CBRMC | a) | 508564.54 | a) | 01/03/19 | e) | - | a) | 508564.54 | a) | 25.00% | c) | 25.00% | a) | 16 | On-going
041 | [6 empty] | b) | Crucio | b) | 03/22/19 | f) | - | b) | 508564.54 | b) | - | d) | - | b) | 480
[7 empty] | c) | SAWATA DFA | c) | 12/31/19 | g) | - | c) | -
[7 empty] | d) | 3 quarters | d) | -
|  | Igangon - Sawata |  | Road Maintenance | 9.66 | MBA | a) | 497447.77 | a) | 01/03/19 | e) | - | a) | 497447.77 | a) | 15.25% | c) | 15.25% | a) | 15 | On-going
042 | [6 empty] | b) | Crucio | b) | 02/01/19 | f) | - | b) | 497447.77 | b) | - | d) | - | b) | 450
[7 empty] | c) | PEO | c) | 12/31/19 | g) | - | c) | -
[7 empty] | d) | - | d) | -
|  | Igangon - Sawata |  | Road Maintenance | 9.66 | CBRMC | a) | 197775.1 | a) | 01/03/19 | e) | - | a) | 197775.1 | a) | 25.00% | c) | 25.00% | a) | 16 | On-going
042 | [6 empty] | b) | Crucio | b) | 03/22/19 | f) | - | b) | 197775.1 | b) | - | d) | - | b) | 480
[7 empty] | c) | SAWATA DFA | c) | 12/31/19 | g) | - | c) | -
[7 empty] | d) | 3 quarters | d) | -
|  | New Corella - Sto. Niño - Macgum |  | Road Maintenance | 17.11 | MBA | a) | 606294.08 | a) | 01/03/19 | e) | - | a) | 606294.08 | a) | 49.55% | c) | 49.55% | a) | 15 | On-going
044 | [6 empty] | b) | Crucio | b) | 01/03/19 | f) | - | b) | 606294.08 | b) | - | d) | - | b) | 450
[7 empty] | c) | PEO | c) | 12/31/19 | g) | - | c) | 246,619.77
[7 empty] | d) | - | d) | -
|  | New Corella - Sto. Niño - Macgum |  | Road Maintenance | 17.11 | CBRMC | a) | 308434.97 | a) | 01/03/19 | e) | - | a) | 308434.97 | a) | 25.00% | c) | 25.00% | a) | 16 | On-going
044 | [6 empty] | b) | Crucio | b) | 03/26/19 | f) | - | b) | 308434.97 | b) | - | d) | - | b) | 480
[7 empty] | c) | SAN ISIDRO FA | c) | 12/31/19 | g) | - | c) | -
[7 empty] | d) | 3 quarters | d) | -
|  | Tagaytay - Buan |  | Road Maintenance | 4.92 | MBA | a) | 173197.37 | a) | 01/03/19 | e) | - | a) | 173197.37 | a) | 36.67% | c) | 36.67% | a) | 15 | On-going
045 | [6 empty] | b) | Crucio | b) | 03/18/19 | f) | - | b) | 173197.37 | b) | - | d) | - | b) | 450
[7 empty] | c) | PEO | c) | 12/31/19 | g) | - | c) | 26254.58
[7 empty] | d) | - | d) | -
|  | Tagaytay - Buan |  | Road Maintenance | 4.92 | CBRMC | a) | 131850.07 | a) | 01/03/19 | e) | - | a) | 131850.07 | a) | 25.00% | c) | 25.00% | a) | 16 | On-going
045 | [6 empty] | b) | Crucio | b) | 03/22/19 | f) | - | b) | 131850.07 | b) | - | d) | - | b) | 480
[7 empty] | c) | BUAN IFA | c) | 12/31/19 | g) | - | c) | -
[7 empty] | d) | 3 quarters | d) | -
|  | limbaan - Sto. Niño |  | Road Maintenance | 3.19 | MBA | a) | 153706.77 | a) | 01/03/19 | e) | - | a) | 153706.77 | a) | 36.51% | c) | 36.51% | a) | 15 | On-going
049 | [6 empty] | b) | Crucio | b) | 03/01/19 | f) | - | b) | 153706.77 | b) | - | d) | - | b) | 450
[7 empty] | c) | PEO | c) | 12/31/19 | g) | - | c) | 32534.49
[7 empty] | d) | - | d) | -
|  | limbaan - Sto. Niño |  | Road Maintenance | 3.19 | CBRMC | a) | 53657.51 | a) | 01/03/19 | e) | - | a) | 53657.51 | a) | - | c) | - | a) | - | Procurement on process
049 | [6 empty] | b) | Crucio | b) | - | f) | - | b) | 53657.51 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
|  | Del Pilar - Jct. Silangan |  | Road Maintenance | 4.17 | MBA | a) | 187097.4 | a) | 01/03/19 | e) | - | a) | 187097.4 | a) | 36.61% | c) | 36.61% | a) | 15 | On-going
051 | [6 empty] | b) | Crucio | b) | 03/18/19 | f) | - | b) | 187097.4 | b) | - | d) | - | b) | 450
[7 empty] | c) | PEO | c) | 12/31/19 | g) | - | c) | 94181.74
[7 empty] | d) | - | d) | -
|  | Del Pilar - Jct. Silangan |  | Road Maintenance | 4.17 | CBRMC | a) | 113014.34 | a) | 01/03/19 | e) | - | a) | 113014.34 | a) | 25.00% | c) | 25.00% | a) | 16 | On-going
051 | [6 empty] | b) | Crucio | b) | 03/26/19 | f) | - | b) | 113014.34 | b) | - | d) | - | b) | 480
[7 empty] | c) | DURIAN DACUDAO | c) | 12/31/19 | g) | - | c) | -
[7 empty] | d) | 3 quarters | d) | -
|  | New Corella - New Sambog - Silangan |  | Road Maintenance | 5.1 | MBA | a) | 201994.35 | a) | 01/03/19 | e) | - | a) | 201994.35 | a) | 34.32% | c) | 34.32% | a) | 15 | On-going
052 | [6 empty] | b) | Crucio | b) | 03/01/19 | f) | - | b) | 201994.35 | b) | - | d) | - | b) | 450
[7 empty] | c) | PEO | c) | 12/31/19 | g) | - | c) | 63402.48
[7 empty] | d) | - | d) | -
|  | New Corella - New Sambog - Silangan |  | Road Maintenance | 5.1 | CBRMC | a) | 131850.07 | a) | 01/03/19 | e) | - | a) | 131850.07 | a) | 25.00% | c) | 25.00% | a) | 16 | On-going
052 | [6 empty] | b) | Crucio | b) | 03/26/19 | f) | - | b) | 131850.07 | b) | - | d) | - | b) | 480
[7 empty] | c) | DURIAN DACUDAO | c) | 12/31/19 | g) | - | c) | -
[7 empty] | d) | 3 quarters | d) | -
|  | Sta. Fe - Del Monte |  | Road Maintenance | 3.34 | MBA | a) | 37923.51 | a) | 01/03/19 | e) | - | a) | 37923.51 | a) | 26.21% | c) | 26.21% | a) | 15 | On-going
056 | [6 empty] | b) | Crucio | b) | 03/18/19 | f) | - | b) | 37923.51 | b) | - | d) | - | b) | 450
[7 empty] | c) | PEO | c) | 12/31/19 | g) | - | c) | 36595.13
[7 empty] | d) | - | d) | -
|  | Sta. Fe - Del Monte |  | Road Maintenance | 3.34 | CBRMC | a) | 70633.96 | a) | 01/03/19 | e) | - | a) | 70633.96 | a) | 25.00% | c) | 25.00% | a) | 16 | On-going
056 | [6 empty] | b) | Crucio | b) | 03/21/19 | f) | - | b) | 70633.96 | b) | - | d) | - | b) | 480
[7 empty] | c) | DEL MONTE CACAO | c) | 12/31/19 | g) | - | c) | 4,872.18
[7 empty] | d) | 3 quarters | d) | -
|  | New Corella - New Bohol |  | Road Maintenance | 11.54 | MBA | a) | 356226.67 | a) | 01/03/19 | e) | - | a) | 356226.67 | a) | 37.65% | c) | 37.65% | a) | 15 | On-going
058 | [6 empty] | b) | Crucio | b) | 02/01/19 | f) | - | b) | 356226.67 | b) | - | d) | - | b) | 450
[7 empty] | c) | PEO | c) | 12/31/19 | g) | - | c) | 110,982.71
[7 empty] | d) | - | d) | -
|  | New Corella - New Bohol |  | Road Maintenance | 11.54 | CBRMC | a) | 190711.7 | a) | 01/03/19 | e) | - | a) | 190711.7 | a) | 25.00% | c) | 25.00% | a) | 16 | On-going
058 | [6 empty] | b) | Crucio | b) | 03/22/19 | f) | - | b) | 190711.7 | b) | - | d) | - | b) | 480
[7 empty] | c) | SAN JOSE COCONUT | c) | 12/31/19 | g) | - | c) | 5,847.18
[7 empty] | d) | 3 quarters | d) | -
|  | Jct. Carcor - Prk. 9 Bagsak |  | Road Maintenance | 2.5 | MBA | a) | 108618.49 | a) | 01/03/19 | e) | - | a) | 108618.49 | a) | 21% | c) | 21% | a) | 15 | On-going
059 | [6 empty] | b) | Crucio | b) | 03/01/19 | f) | - | b) | 108618.49 | b) | - | d) | - | b) | 480
[7 empty] | c) | PEO | c) | 12/31/19 | g) | - | c) | 79952.88
[7 empty] | d) | - | d) | -
|  | Jct. Carcor - Prk. 9 Bagsak |  | Road Maintenance | 2.5 | CBRMC | a) | 42284.76 | a) | 01/03/19 | e) | - | a) | 42284.76 | a) | 25.00% | c) | 25.00% | a) | 16 | On-going
059 | [6 empty] | b) | Crucio | b) | 03/22/19 | f) | - | b) | 42284.76 | b) | - | d) | - | b) | 480
[7 empty] | c) | CARCOR MOTOR | c) | 12/31/19 | g) | - | c) | -
[7 empty] | d) | 3 quarters | d) | -
|  | Carcor - Jct. Kauswagan |  | Road Maintenance | 4.32 | MBA | a) | 264514.71 | a) | 01/03/19 | e) | - | a) | 264514.71 | a) | 41.32% | c) | 41.32% | a) | 15 | On-going
060 | [6 empty] | b) | Crucio | b) | 03/18/19 | f) | - | b) | 264514.71 | b) | - | d) | - | b) | 450
[7 empty] | c) | PEO | c) | 12/31/19 | g) | - | c) | 80733.11
[7 empty] | d) | - | d) | -
|  | Carcor - Jct. Kauswagan |  | Road Maintenance | 4.32 | CBRMC | a) | 48398.27 | a) | 01/03/19 | e) | - | a) | 48398.27 | a) | 25.00% | c) | 25.00% | a) | 16 | On-going
060 | [6 empty] | b) | Crucio | b) | 03/22/19 | f) | - | b) | 48398.27 | b) | - | d) | - | b) | 480
[7 empty] | c) | CARCOR MOTOR | c) | 12/31/19 | g) | - | c) | -
[7 empty] | d) | 3 quarters | d) | -
|  | Del Pilar - Prk 9 Bagsak - San Jose |  | Road Maintenance | 4.99 | MBA | a) | 170215.76 | a) | 01/03/19 | e) | - | a) | 170215.76 | a) | 29.35% | c) | 29.35% | a) | 15 | On-going
061 | [6 empty] | b) | Crucio | b) | 03/01/19 | f) | - | b) | 170215.76 | b) | - | d) | - | b) | 450
[7 empty] | c) | PEO | c) | 12/31/19 | g) | - | c) | 87595.63
[7 empty] | d) | - | d) | -
|  | Del Pilar - Prk 9 Bagsak - San Jose |  | Road Maintenance | 4.99 | CBRMC | a) | 223674.22 | a) | 01/03/19 | e) | - | a) | 223674.22 | a) | 25.00% | c) | 25.00% | a) | 16 | On-going
061 | [6 empty] | b) | Crucio | b) | 03/22/19 | f) | - | b) | 223674.22 | b) | - | d) | - | b) | 480
[7 empty] | c) | SAN JOSE COCONUT | c) | 12/31/19 | g) | - | c) | -
[7 empty] | d) | 3 quarters | d) | -
|  | San Juan - New Talisay |  | Road Maintenance | 5.13 | MBA | a) | 306261.25 | a) | 01/03/19 | e) | - | a) | 306261.25 | a) | 36.97% | c) | 36.97% | a) | 15 | On-going
063 | [6 empty] | b) | Crucio | b) | 02/01/19 | f) | - | b) | 306261.25 | b) | - | d) | - | b) | 450
[7 empty] | c) | PEO | c) | 12/31/19 | g) | - | c) | 85123.48
[7 empty] | d) | - | d) | -
|  | San Juan - New Talisay |  | Road Maintenance | 5.13 | CBRMC | a) | 93906.31 | a) | 01/03/19 | e) | - | a) | 93906.31 | a) | 25.00% | c) | 25.00% | a) | 16 | On-going
063 | [6 empty] | b) | Crucio | b) | 03/26/19 | f) | - | b) | 93906.31 | b) | - | d) | - | b) | 480
[7 empty] | c) | NEW TALISAY IAWA | c) | 12/31/19 | g) | - | c) | -
[7 empty] | d) | 3 quarters | d) | -
|  | San Juan - kauswagan - New Cortez |  | Road Maintenance | 3.22 | MBA | a) | 187879.04 | a) | 01/03/19 | e) | - | a) | 187879.04 | a) | 6.68% | c) | 6.68% | a) | 15 | On-going
064 | [6 empty] | b) | Crucio | b) | 03/18/19 | f) | - | b) | 187879.04 | b) | - | d) | - | b) | 450
[7 empty] | c) | PEO | c) | 12/31/19 | g) | - | c) | 3,025.00
[7 empty] | d) | - | d) | -
|  | San Juan - kauswagan - New Cortez |  | Road Maintenance | 3.22 | CBRMC | a) | 63298.26 | a) | 01/03/19 | e) | - | a) | 63298.26 | a) | 25.00% | c) | 25.00% | a) | 16 | On-going
064 | [6 empty] | b) | Crucio | b) | 03/22/19 | f) | - | b) | 63298.26 | b) | - | d) | - | b) | 480
[7 empty] | c) | SAN JOSE COCONUT | c) | 12/31/19 | g) | - | c) | -
[7 empty] | d) | 3 quarters | d) | -
|  | New Bohol - Jct. El Unido |  | Road Maintenance | 2.12 | MBA | a) | 54989.06 | a) | 01/03/19 | e) | - | a) | 54989.06 | a) | 23.17% | c) | 23.17% | a) | 15 | On-going
065 | [6 empty] | b) | Crucio | b) | 03/01/19 | f) | - | b) | 54989.06 | b) | - | d) | - | b) | 450
[7 empty] | c) | PEO | c) | 12/31/19 | g) | - | c) | 21021.99
[7 empty] | d) | - | d) | -
|  | New Bohol - Jct. El Unido |  | Road Maintenance | 2.12 | CBRMC | a) | 58861.64 | a) | 01/03/19 | e) | - | a) | 58861.64 | a) | 25.00% | c) | 25.00% | a) | 16 | On-going
065 | [6 empty] | b) | Crucio | b) | 03/26/19 | f) | - | b) | 58861.64 | b) | - | d) | - | b) | 480
[7 empty] | c) | MANDISKAB TRIBAL | c) | 12/31/19 | g) | - | c) | -
[7 empty] | d) | 3 quarters | d) | -
|  | New Corella - El unido - Jct. Mesaoy |  | Road Maintenance | 8.63 | MBA | a) | 388002.46 | a) | 01/03/19 | e) | - | a) | 388002.46 | a) | 35.45% | c) | 35.45% | a) | 15 | On-going
066 | [6 empty] | b) | Crucio | b) | 02/11/19 | f) | - | b) | 388002.46 | b) | - | d) | - | b) | 450
[7 empty] | c) | PEO | c) | 12/31/19 | g) | - | c) | 175542.68
[7 empty] | d) | - | d) | -
|  | New Corella - El unido - Jct. Mesaoy |  | Road Maintenance | 8.63 | CBRMC | a) | 233092.08 | a) | 01/03/19 | e) | - | a) | 233092.08 | a) | 25.00% | c) | 25.00% | a) | 16 | On-going
066 | [6 empty] | b) | Crucio | b) | 03/26/19 | f) | - | b) | 233092.08 | b) | - | d) | - | b) | 480
[7 empty] | c) | MANDISKAB TRIBAL | c) | 12/31/19 | g) | - | c) | -
[7 empty] | d) | 3 quarters | d) | -
|  | Mesaoy - Dasing |  | Road Maintenance | 1.39 | MBA | a) | 29749.5 | a) | 01/03/19 | e) | - | a) | 29749.5 | a) | 27.43% | c) | 27.43% | a) | 15 | On-going
067 | [6 empty] | b) | Crucio | b) | 03/18/19 | f) | - | b) | 29749.5 | b) | - | d) | - | b) | 450
[7 empty] | c) | PEO | c) | 12/31/19 | g) | - | c) | 20414.68
[7 empty] | d) | - | d) | -
|  | Mesaoy - Dasing |  | Road Maintenance | 1.39 | CBRMC | a) | 54152.71 | a) | 01/03/19 | e) | - | a) | 54152.71 | a) | 25.00% | c) | 25.00% | a) | 16 | On-going
067 | [6 empty] | b) | Crucio | b) | 03/26/19 | f) | - | b) | 54152.71 | b) | - | d) | - | b) | 480
[7 empty] | c) | MANDISKAB TRIBAL | c) | 12/31/19 | g) | - | c) | -
[7 empty] | d) | 3 quarters | d) | -
|  | Jct. San Juan - Jct. Mesaoy |  | Road Maintenance | 1.82 | MBA | a) | 106788.95 | a) | 01/03/19 | e) | - | a) | 106788.95 | a) | 42.14% | c) | 42.14% | a) | 15 | On-going
068 | [6 empty] | b) | Crucio | b) | 03/01/19 | f) | - | b) | 106788.95 | b) | - | d) | - | b) | 450
[7 empty] | c) | PEO | c) | 12/31/19 | g) | - | c) | 17502.68
[7 empty] | d) | - | d) | -
|  | Jct. San Juan - Jct. Mesaoy |  | Road Maintenance | 1.82 | CBRMC | a) | 35180.83 | a) | 01/03/19 | e) | - | a) | 35180.83 | a) | 25.00% | c) | 25.00% | a) | 16 | On-going
068 | [6 empty] | b) | Crucio | b) | 03/26/19 | f) | - | b) | 35180.83 | b) | - | d) | - | b) | 480
[7 empty] | c) | MANDISKAB TRIBAL | c) | 12/31/19 | g) | - | c) | -
[7 empty] | d) | 3 quarters | d) | -
|  | Mesaoy - Jct. Mahayahay |  | Road Maintenance | 4.6 | MBA | a) | 146984.46 | a) | 01/03/19 | e) | - | a) | 146984.46 | a) | 32.81% | c) | 32.81% | a) | 15 | On-going
069 | [6 empty] | b) | Crucio | b) | 03/18/19 | f) | - | b) | 146984.46 | b) | - | d) | - | b) | 450
[7 empty] | c) | PEO | c) | 12/31/19 | g) | - | c) | 7618.27
[7 empty] | d) | - | d) | -
|  | Mesaoy - Jct. Mahayahay |  | Road Maintenance | 4.6 | CBRMC | a) | 160103.65 | a) | 01/03/19 | e) | - | a) | 160103.65 | a) | 25.00% | c) | 25.00% | a) | 16 | On-going
069 | [6 empty] | b) | Crucio | b) | 03/22/19 | f) | - | b) | 160103.65 | b) | - | d) | - | b) | 480
[7 empty] | c) | MAHAYAHAY IFA | c) | 12/31/19 | g) | - | c) | -
[7 empty] | d) | 3 quarters | d) | -
|  | Mesaoy - New bohol |  | Road Maintenance | 5.36 | MBA | a) | 165361.13 | a) | 01/03/19 | e) | - | a) | 165361.13 | a) | 13.36% | c) | 13.36% | a) | 15 | On-going
070 | [6 empty] | b) | Crucio | b) | 03/01/19 | f) | - | b) | 165361.13 | b) | - | d) | - | b) | 480
[7 empty] | c) | PEO | c) | 12/31/19 | g) | - | c) | 58046.49
[7 empty] | d) | - | d) | -
|  | Mesaoy - New bohol |  | Road Maintenance | 5.36 | CBRMC | a) | 224851.45 | a) | 01/03/19 | e) | - | a) | 224851.45 | a) | 25.00% | c) | 25.00% | a) | 16 | On-going
070 | [6 empty] | b) | Crucio | b) | 03/26/19 | f) | - | b) | 224851.45 | b) | - | d) | - | b) | 480
[7 empty] | c) | MANDISKAB TRIBAL | c) | 12/31/19 | g) | - | c) | -
[7 empty] | d) | 3 quarters | d) | -
|  | Bdry. Tagum - Baca - New Corella |  | Road Maintenance | 13.01 | MBA | a) | 217182.9 | a) | 01/03/19 | e) | - | a) | 217182.9 | a) | 39.13% | c) | 39.13% | a) | 15 | On-going
071 | [6 empty] | b) | Crucio | b) | 03/18/19 | f) | - | b) | 217182.9 | b) | - | d) | - | b) | 450
[7 empty] | c) | PEO | c) | 12/31/19 | g) | - | c) | 66584.07
[7 empty] | d) | - | d) | -
|  | Bdry. Tagum - Baca - New Corella |  | Road Maintenance | 13.01 | CBRMC | a) | 214256.36 | a) | 01/03/19 | e) | - | a) | 214256.36 | a) | 25.00% | c) | 25.00% | a) | 16 | On-going
071 | [6 empty] | b) | Crucio | b) | 03/26/19 | f) | - | b) | 214256.36 | b) | - | d) | - | b) | 480
[7 empty] | c) | DURIAN DACUDAO | c) | 12/31/19 | g) | - | c) | -
[7 empty] | d) | 3 quarters | d) | -
|  | Prk. 1, Maunlom - Prk. 6 Maunlom Road |  | Road Maintenance | 3.56 | MBA | a) | 150912.87 | a) | 01/03/19 | e) | - | a) | 150912.87 | a) | 41.49% | c) | 41.49% | a) | 15 | On-going
147 | [6 empty] | b) | Crucio | b) | 03/01/19 | f) | - | b) | 150912.87 | b) | - | d) | - | b) | 450
[7 empty] | c) | PEO | c) | 12/31/19 | g) | - | c) | 23025
[7 empty] | d) | - | d) | -
|  | Prk. 1, Maunlom - Prk. 6 Maunlom Road |  | Road Maintenance | 3.56 | CBRMC | a) | 63973.36 | a) | 01/03/19 | e) | - | a) | 63973.36 | a) | 25.00% | c) | 25.00% | a) | 16 | On-going
147 | [6 empty] | b) | Crucio | b) | 03/22/19 | f) | - | b) | 63973.36 | b) | - | d) | - | b) | 480
[7 empty] | c) | THE BEST VEGETABLE | c) | 12/31/19 | g) | - | c) | -
[7 empty] | d) | 3 quarters | d) | -
|  | New Visayas - Binancian |  | Road Maintenance | 7.77 | MBA | a) | 14814.34 | a) | 01/03/19 | e) | - | a) | 14814.34 | a) | 9.77% | c) | 9.77% | a) | 15 | On-going
149 | [6 empty] | b) | Crucio | b) | 03/18/19 | f) | - | b) | 14814.34 | b) | - | d) | - | b) | 450
[7 empty] | c) | PEO | c) | 12/31/19 | g) | - | c) | 5,000.00
[7 empty] | d) | - | d) | -
|  | New Visayas - Binancian |  | Road Maintenance | 7.77 | CBRMC | a) | 129495.6 | a) | 01/03/19 | e) | - | a) | 129495.6 | a) | 25.00% | c) | 25.00% | a) | 16 | On-going
149 | [6 empty] | b) | Crucio | b) | 03/22/19 | f) | - | b) | 129495.6 | b) | - | d) | - | b) | 480
[7 empty] | c) | BUAN IFA | c) | 12/31/19 | g) | - | c) | -
[7 empty] | d) | 3 quarters | d) | -
|  | Datu Balong - Prk. Mamalian |  | Road Maintenance | 3.46 | MBA | a) | 117454.89 | a) | 01/03/19 | e) | - | a) | 117454.89 | a) | 39.97% | c) | 39.37% | a) | 15 | On-going
150 | [6 empty] | b) | Crucio | b) | 03/18/19 | f) | - | b) | 117454.89 | b) | - | d) | - | b) | 450
[7 empty] | c) | PEO | c) | 12/31/19 | g) | - | c) | 4140.62
[7 empty] | d) | - | d) | -
|  | Datu Balong - Prk. Mamalian |  | Road Maintenance | 3.46 | CBRMC | a) | 59264.42 | a) | 01/03/19 | e) | - | a) | 59264.42 | a) | 25.00% | c) | 25.00% | a) | 16 | On-going
150 | [6 empty] | b) | Crucio | b) | 03/28/19 | f) | - | b) | 59264.42 | b) | - | d) | - | b) | 480
[7 empty] | c) | DATU BALONG FA | c) | 12/31/19 | g) | - | c) | -
[7 empty] | d) | 3 quarters | d) | -
B. 20% DEVELOPMENT FUND CY 2019
Road ID |  | 1. Rehabilitation Of Various Prov'l. Roads and Bridges |  | Road Rehabilitation | KM | MBA | a) | 41465029 | a) | 01/03/19 | e) | - | a) | 41465029 | a) | - | c) | - | a) | 46 | See list of Provincial Roads
[5 empty] | 109.55 |  | b) | Paraguya | b) | 01/03/19 | f) | - | b) | 41465029 | b) | - | d) | - | b) | 920
11DAN | [6 empty] | c) | PEO | c) | 12/31/19 | g) | - | c) | -
[9 empty] | d) | -
[7 empty] | d) | 261 days | d) | -
|  | Jct. Highway Canatan - Doña Andrea |  | Road Rehabilitation | 4.34 | MBA | a) | 2,000,000.00 | a) | 01/03/19 | e) | - | a) | 2,000,000.00 | a) | - | c) | - | a) | - | POW for approval
007 | [6 empty] | b) | Crucio | b) | - | f) | - | b) | 2,000,000.00 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
|  | Pamacaun - Lasang Banate |  | Road Rehabilitation | 4.34 | MBA | a) | 2000000 | a) | 01/03/19 | e) | - | a) | 2000000 | a) | - | c) | - | a) | - | Pow Approved. For allotment
015 | [6 empty] | b) | Crucio | b) | - | f) | - | b) | 2000000 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
|  | Kapalong - Mabantao - Florida |  | Road Rehabilitation | 7.86 | MBA | a) | 1231000 | a) | 01/03/19 | e) | - | a) | 1231000 | a) | - | c) | - | a) | - | PR on process
016 | [6 empty] | b) | Crucio | b) | - | f) | - | b) | 1231000 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
|  | Jct. Highway Gabuyan - Semong - Dagohoy |  | Road Rehabilitation | 6.97 | MBA | a) | 2492000 | a) | 01/03/19 | e) | - | a) | 2492000 | a) | - | c) | - | a) | - | POW for approval
017 | [6 empty] | b) | Crucio | b) | - | f) | - | b) | 2492000 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
|  | Sto. Niño - Palma Gil - Sitio Opao |  | Road Rehabilitation | 11.6 | MBA | a) | 1901000 | a) | 01/03/19 | e) | - | a) | 1901000 | a) | - | c) | - | a) | - | POW for approval
019 | [6 empty] | b) | Crucio | b) | - | f) | - | b) | 1901000 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
|  | Daligdigon - Lumabag |  | Road Rehabilitation | 11.6 | MBA | a) | 680000 | a) | 01/03/19 | e) | - | a) | 680000 | a) | - | c) | - | a) | - | POW for approval
022 | [6 empty] | b) | Crucio | b) | - | f) | - | b) | 680000 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
|  | Sto. Niño - Daligdigon - Paiton |  | Road Rehabilitation | 11.6 | MBA | a) | 3000000 | a) | 01/03/19 | e) | - | a) | 3000000 | a) | - | c) | - | a) | - | POW for approval
023 | [6 empty] | b) | Crucio | b) | - | f) | - | b) | 3000000 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
|  | Jct. Paiton - Mibolo |  | Road Rehabilitation | 23.9 | MBA | a) | 6000000 | a) | 01/03/19 | e) | - | a) | 6000000 | a) | - | c) | - | a) | - | Allotment on process
024 | [6 empty] | b) | Crucio | b) | - | f) | - | b) | 6000000 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
|  | Monte Dujali - Gupitan |  | Road Rehabilitation | 4.58 | MBA | a) | 1200000 | a) | 01/03/19 | e) | - | a) | 1200000 | a) | - | c) | - | a) | - | POW for approval
037 | [6 empty] | b) | Crucio | b) | - | f) | - | b) | 1200000 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
|  | Jct. Sawata - Bdry. Binasbas |  | Road Rehabilitation | 0.46 | MBA | a) | 500000 | a) | 01/03/19 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | PR on process
043 | [6 empty] | b) | Crucio | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
|  | New Corella - Saug |  | Road Rehabilitation | 12.52 | MBA | a) | 6500000 | a) | 01/03/19 | e) | - | a) | 6500000 | a) | 0.12% | c) | 0.12% | a) | 19 | On-going
048 | [6 empty] | b) | Aizon | b) | 03/26/19 | f) | - | b) | 6500000 | b) | - | d) | - | b) | 570
[7 empty] | c) | PEO | c) | 12/31/19 | g) | - | c) | -
[7 empty] | d) | - | d) | -
|  | Jct. Monte Carlo - Upper Cabaywa - Canatan |  | Road Rehabilitation | 4.61 | MBA | a) | 8838000 | a) | 01/03/19 | e) | - | a) | 8838000 | a) | 5.72% | c) | 6.00% | a) | 19 | On-going
050 | [6 empty] | b) | Fabian | b) | 03/26/19 | f) | - | b) | 8838000 | b) | - | d) | +0.28% | b) | 570
[7 empty] | c) | PEO | c) | 12/31/19 | g) | - | c) | -
[7 empty] | d) | - | d) | -
|  | Del Pilar - El Unido |  | Road Rehabilitation | 1.32 | MBA | a) | 1389000 | a) | 01/03/19 | e) | - | a) | 1389000 | a) | 75.45% | c) | 97.55% | a) | 19 | On-going
062 | [6 empty] | b) | Fabian | b) | 03/18/19 | f) | - | b) | 1389000 | b) | - | d) | +22.10% | b) | 570
[7 empty] | c) | PEO | c) | 04/21/19 | g) | - | c) | 15,596.39
[7 empty] | d) | - | d) | -
|  | Bdry. Tagum - Baca - New Corella |  | Road Rehabilitation | 13.01 | MBA | a) | 1419029 | a) | 01/03/19 | e) | - | a) | 1419029 | a) | - | c) | - | a) | - | POW for approval
071 | [6 empty] | b) | Crucio | b) | - | f) | - | b) | 1419029 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
2. Various of Local Roads & Drainage Development Project (Provincewide) |  |  |  | Road Drainage rehabiliated |  | Admin | a) | 15000000 | [12 empty] | See projects listed below
[7 empty] | b) | Paraguya
[7 empty] | c) | PEO
[7 empty] | d) | -
|  | Rehab./Impv't. of San Juan-New Talisay Provincial Road with Drainage |  | Road Drainage rehabiliated | - | Admin | a) | 1000000 | a) | - | e) | - | a) | 1000000 | a) | - | c) | - | a) | - | PR on process
2.1 | [6 empty] | b) | - | b) | - | f) | - | b) | 1000000 | b) | - | d) | - | b) | -
[7 empty] | c) | PEO | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
|  | Repair/Rehab. Of Concrete Road Jct. Suaon-Libuton with Drainage |  | Road Drainage rehabiliated | - | Admin | a) | 1000000 | a) | - | e) | - | a) | 1000000 | a) | - | c) | - | a) | - | POW completed.For AIP amendment to correct project title (w/out drainage)
2.2 | [6 empty] | b) | - | b) | - | f) | - | b) | 1000000 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
|  | Impv't. of Cross Drainage along Saug-Sonlon-Bdry. Longanapan |  | Road Drainage rehabiliated | - | Admin | a) | 3000000 | a) | - | e) | - | a) | 3000000 | a) | - | c) | - | a) | - | PR on process
2.3 | [6 empty] | b) | - | b) | - | f) | - | b) | 3000000 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
|  | Rehab./Impv't. of Sto. Niño-Palma Gil-Sitio Opao Provincial Road with Drainage |  | Road Drainage rehabiliated | - | Admin | a) | 3000000 | a) | - | e) | - | a) | 3000000 | a) | - | c) | - | a) | - | For revision of plan
2.4 | [6 empty] | b) | - | b) | - | f) | - | b) | 3000000 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
3. Various Water System Development Project (Provincewide) |  |  |  | Water System projects | - | Admin | a) | 9750000 | [12 empty] | See projects listed below
[7 empty] | b) | Medalla
[7 empty] | c) | PEO
[7 empty] | d) | -
|  | Construction of PWS, Bgry. Linao, San Isidro |  | Water System Projects | - | Admin | a) | 500000 | a) | 06/19/19 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | PR on process
3.1 | [6 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
|  | Construction of PWS, Brgy. Datu Balong, San Isidro |  | Water System Projects | - | Admin | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For cancellation. No feasible water source at proposed location
3.2 | [6 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
|  | Construction of PWS, Brgy. Sagayen, San Isidro |  | Water System Projects | - | Admin | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Plan completed. On-going POW preparation
3.3 | [6 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
|  | Construction of PWS, Brgy. Purok 7-A and B, Brgy. Capungagan, kapalong |  | Water System Projects | - | Admin | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | To be declared as savings (Funded by OPAPP CY 2018)
3.5 | [6 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
|  | Construction of PWS Purok 2, Brgy. Pag-Asa, kapalong |  | Water System Projects | - | Admin | a) | 800000 | a) | - | e) | - | a) | 800000 | a) | - | c) | - | a) | - | To be declared as savings (Funded by OPAPP CY 2018)
3.6 | [6 empty] | b) | - | b) | - | f) | - | b) | 800000 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
|  | Procurement of materials for the installation of Shallow Tube Wells for Irrigation & Const. of Machinery Shed for storage of open surface pump for PAGRO |  | Water System Projects | - | Admin | a) | 1600000 | a) | - | e) | - | a) | 1600000 | a) | - | c) | - | a) | - | Plan preparation on -going
3.7 | [6 empty] | b) | - | b) | - | f) | - | b) | 1600000 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
4. Various Government Buildings and Facilities Development Project (Provincewide) |  |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of recipients | - | Admin | a) | 27000000 | [12 empty] | See projects listed below
[7 empty] | b) | Medalla
[7 empty] | c) | PEO
[7 empty] | d) | -
4.1 |  | Repair Bay of Disaster Quick Response Equipment @ PEO Compound, Gov't. Center, Mankilam, Tagum City |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of recipients | - | Admin | a) | 1000000 | a) | - | e) | - | a) | 1000000 | a) | - | c) | - | a) | - | PR on process
[7 empty] | b) | - | b) | - | f) | - | b) | 1000000 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
4.2 |  | Repair/Impv't. of Municipal Triball Hall, New Corella |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of recipients | - | Admin | a) | 1500000 | a) | - | e) | - | a) | 1500000 | a) | - | c) | - | a) | - | POW for checking
[7 empty] | b) | - | b) | - | f) | - | b) | 1500000 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
4.3 |  | Const. of GYM Bleacher at Suaybaguio Rina, Elem. School |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of recipients | - | Admin | a) | 1000000 | a) | - | e) | - | a) | 1000000 | a) | - | c) | - | a) | - | PR on process
[7 empty] | b) | - | b) | - | f) | - | b) | 1000000 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
4.4 |  | Repair of Dacudao Health Center, Dacudao, San Isidro |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of recipients | - | Admin | a) | 1000000 | a) | - | e) | - | a) | 1000000 | a) | - | c) | - | a) | - | For POW Preparation
[7 empty] | b) | - | b) | - | f) | - | b) | 1000000 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
4.5 |  | Const. of Perimeter Fence at Sto. Niño NASECO Integrated School with Tugas Ext., Sto. Niño, Talaingod |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of recipients | - | Admin | a) | 1000000 | a) | - | e) | - | a) | 1000000 | a) | - | c) | - | a) | - | Preparation of plan on -going
[7 empty] | b) | - | b) | - | f) | - | b) | 1000000 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
4.6 |  | Const. of Multi-Purpose Hall Center (Cultural Heritage in Ancestral Domain of Ata-Manobo) |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of recipients | - | Admin | a) | 3000000 | a) | - | e) | - | a) | 3000000 | a) | - | c) | - | a) | - | Structural design for checking
[7 empty] | b) | - | b) | - | f) | - | b) | 3000000 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
4.7 |  | Const. of IP Women's Multi-{Purpose Bldg.), Cabidiangan, Sto. Niño, Talaingod |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of recipients | - | Admin | a) | 2000000 | a) | - | e) | - | a) | 2000000 | a) | - | c) | - | a) | - | POW preparation on -going
[7 empty] | b) | - | b) | - | f) | - | b) | 2000000 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
4.8 |  | Extension of PAGRO Training Center & Ground Dev't., Gov't. Center, Mankilam, Tagum City |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of recipients | - | Admin | a) | 1000000 | a) | - | e) | - | a) | 1000000 | a) | - | c) | - | a) | - | POW preparation on -going
[7 empty] | b) | - | b) | - | f) | - | b) | 1000000 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
4.9 |  | Construction of Abilidad Training Center, Gov't. Center, Mankilam, Tagum City |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of recipients | - | Admin | a) | 7000000 | a) | - | e) | - | a) | 7000000 | a) | - | c) | - | a) | - | POW preparation on-going
[7 empty] | b) | - | b) | - | f) | - | b) | 7000000 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
4.1 |  | Const. of 1 CL Bldg. @ Suawon ES, New Corella |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of recipients | - | Admin | a) | 1000000 | a) | - | e) | - | a) | 1000000 | a) | - | c) | - | a) | - | For revision of plan
[7 empty] | b) | - | b) | - | f) | - | b) | 1000000 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
4.11 |  | Const. of Municipal Tribal Hall, San Isidro |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of recipients | - | Admin | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | PR on process
[7 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
4.12 |  | Const. of Quail House (PDNSC Ext. Campus), Sto. Niño, Talaingod |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of recipients | - | Admin | a) | 750000 | a) | - | e) | - | a) | 750000 | a) | - | c) | - | a) | - | Allotment on process
[7 empty] | b) | - | b) | - | f) | - | b) | 750000 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
5. Stimulus Projects for Various Barangays |  |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | Admin | a) | 41500000 | [12 empty] | See projects listed below
[7 empty] | b) | Medalla
[7 empty] | c) | PEO
[7 empty] | d) | -
ASUNCION
5.1 |  | Rehab. Of FMR at Prk. 1,3,4 & 7, Concepcion, Asuncion |  | Road Rehabilitation to cater the needs of brgys. | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Waiting for Plan from MEO
[7 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
5.2 |  | Rehab. Of Multi-Purpose Hall, New Bantayan, Asuncion |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Transfer of Fund
[7 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
NEW CORELLA
5.3 |  | Construction of Multi-Purpose Hall, El Salvador, New Corella |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Transfer of Fund
[7 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
5.4 |  | Concreting of Drainage Canal, Poblacion, New Corella |  | Const. of Drainage Canal to cater the needs of brgys. | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For AIP amendment to Const. of 2 Storey Multi-Purpose Hall Phase 3 (Brgy. Hall)
[7 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
5.5 |  | Rehab. Of Multi-Purpose Hall, Cabidianan, New Corella |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) | 02/20/19 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Transfer of Fund
[7 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
5.6 |  | Const. of Canal Lining, Limbaan, New Corella |  | Const. of Drainage Canal to cater the needs of brgys. | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Transfer of Fund
[7 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
TALAINGOD
5.7 |  | Brgy. Electrification (Centro Gupitan), Gupitan, Talaingod |  | Rural Electrification to cater the needs of brgys. | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For DANECO Staking
[7 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
TAGUM CITY
5.8 |  | Rehab. of Evacuation Center, Madaum, Tagum City |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) | 01/14/19 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | PO on process
[7 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
5.9 |  | Rehab. of Evacuation Center, Magugpo Poblacion, Tagum City |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | POW preparation on-going
[7 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
5.1 |  | Rehab. of Evacuation Center, New Balambam, Tagum City |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | POW preparation on-going
[7 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
5.11 |  | Rehab. Of Multi-Purpose Hall, Cuambogan, Tagum City |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | POW preparation on-going
[7 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
5.12 |  | Completion of Evacuation Center, Nueva Fuerza, Tagum City |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | PLAN & POW completed. Pending -waiting for brgy. Resolution.
[7 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
5.13 |  | Const. of Water System @ Prk. Dancing Lady, San Agustin, Tagum City |  | Const. of Water System to cater the needs of brgys. | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | No site at Prk. Dancing. Project will be transferred at Purok 1 (For AIP Amendment)
[7 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
5.14 |  | Const. of Brgy. Health Center, Magugpo South, Tagum City |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For POW preparation
[7 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
5.15 |  | Const. of Women Livelihood Center, San Isidro, Tagum City |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Plan for revision
[7 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
5.16 |  | Const. of Water System , Busaon, Tagum City |  | Const. of Water System to cater the needs of brgys. | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | POW for checking
[7 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
5.17 |  | Rehab. Of Brgy. Health Center, Apokon, Tagum City |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | POW preparation on -going
[7 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
5.18 |  | Const. of Drainage Canal, Bincungan, Tagum City |  | Const. of Drainage Canal to cater the needs of brgys. | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | PLAN & POW completed. Pending -waiting for brgy. Resolution.
[7 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
5.19 |  | Rehab. of Evacuation Center, Mankilam, Tagum City |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | PLAN & POW completed. Pending -waiting for brgy. Resolution.
[7 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
5.2 |  | Rehab. of Evacuation Center, Magugpo North, Tagum City |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | PLAN & POW completed. Pending -waiting for brgy. Resolution.
[7 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
SAN ISIDRO
5.21 |  | Rehab. Of Multi-Purpose Hall , Sto. Niño, San Isidro |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | Admin | a) | 500000 | a) | 02/20/19 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | PR on process
[7 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
5.22 |  | Rehab. Of Water System at Purok Cabang & Mangga , Pinamuno, San Isidro |  | Const. of Water System to cater the needs of brgys. | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Plan preparation on-going
[7 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
5.23 |  | Rehab. Of Water System , Igangon, San Isidro |  | Const. of Water System to cater the needs of brgys. | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | POW preparation on-going
[7 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
5. Rural Electrification Project (Provincewide) |  |  |  | Powerlines/posts installed & rehabilitated | - | - | a) | 5000000 | [12 empty] | See projects listed below
[7 empty] | b) | Kim Pao Lu
[7 empty] | c) | -
[7 empty] | d) | -
5.1 |  | Rural Electrification , Del Monte, New Corella |  | Powerlines/posts installed & rehabilitated | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For DANECO staking
[7 empty] | b) | Kim Pao Lu | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
5.2 |  | Rural Electrification at St. Bundok, San Roque, New Corella |  | Powerlines/posts installed & rehabilitated | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For DANECO staking
[7 empty] | b) | Kim Pao Lu | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
C. 5% CALAMITY FUND CY 2019
1 |  | Desiltation/Excavation of rivers and creeks |  | creeks and canals deislted | - | - | a) | 3000000 | [12 empty] | See project listed below
[7 empty] | b) | Paraguya
[7 empty] | c) | PEO
[7 empty] | d) | -
|  | a. | Desilting of Limbaan Creek, New Corella | creeks and canals deislted | - | - | a) | 2000000 | a) | - | e) | - | a) | 2000000 | a) | - | c) | - | a) | - | POW preparation on going
[7 empty] | b) | - | b) | - | f) | - | b) | 2000000 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
2 |  | Revitment of Dike and Slope Proection |  | Protection dikes/slope protection | - | - | a) | 3000000 | [12 empty] | See projects listed below
[7 empty] | b) | -
[7 empty] | c) | -
[7 empty] | d) | -
|  | a. | Slope Protection Along Kapalong-Mabantao, Florida | creeks and canals deislted | - | - | a) | 1000000 | a) | - | e) | - | a) | 1000000 | a) | - | c) | - | a) | - | For cancellation funded to DPWH. Budget Transferred to
[7 empty] | b) | - | b) | - | f) | - | b) | 1000000 | b) | - | d) | - | b) | - | 5% Calamity Fund- Rehab and Recovery
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
3 |  | Improvement of roads, drainage and canal |  | Protection dikes/slope protection | - | - | a) | 3000000 | [12 empty] | See projects listed below
[7 empty] | b) | Paraguya
[7 empty] | c) | PEO
[7 empty] | d) | -
|  | a. | Rehab/Impvt of New Casay - Bugtong Talisay Provincial Road | creeks and canRoads/Draiange/canals rehab/improved | - | - | a) | 1000000 | a) | - | e) | - | a) | 1000000 | a) | - | c) | - | a) | - | PO on process
[7 empty] | b) | - | b) | - | f) | - | b) | 1000000 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
4 |  | Improvement of bridges and cross drainage |  | bridge and cross drainage rehab./improved # of sq.m riprapped, culverts replaced | - | - | a) | 3000000 | [12 empty] | See projects listed below
[7 empty] | b) | Paraguya
[7 empty] | c) | PEO
[7 empty] | d) | -
|  | a. | Impv't. of Jct. New Boholano - New Loon Cross Drainage | creeks and canRoads/Draiange/canals rehab/improved | - | - | a) | 2000000 | a) | - | e) | - | a) | 2000000 | a) | - | c) | - | a) | - | POW preparation on going c/o PEO-PDPM. Insufficient budget to complete required works for the project
[7 empty] | b) | - | b) | - | f) | - | b) | 2000000 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
|  | b. | Impv't. of Jct. Saug-Sonlon-Bdry. Longanapan Cross Drainage | creeks and canRoads/Draiange/canals rehab/improved |  | - | a) | 1000000 | a) | - | e) | - | a) | 1000000 | a) | - | c) | - | a) | - | PR on process
[7 empty] | b) | - | b) | - | f) | - | b) | 1000000 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
| GF- GENERAL FUND | [13 empty] | TF - TRUST FUND (NATIONAL FUNDED PROJECT)
| 20% DF - 20% DEV'T. FUND | [13 empty] | a) SLRF - Special Local Road Fund
| 5% CF - 5% CALAMITY FUND | [13 empty] | b) KALSADA - Konkreto at Ayos na Lansangan Tungo sa Pangkalahatang Kaunlaran
| CO - CAPITAL OUTLAY | [13 empty] | c) PRDP - Philippine Rural Development Projects
| CONG. FUND - CONGRESSIONAL FUND | [13 empty] | d) SELAP - Support to Emergency and Livelihood Assistance Project
| NCF - NATIONAL CALAMITY FUND | [13 empty] | e) PAMANA - Payapa at Masaganang Pamayanan
| SEF - SPECIAL EDUCATIONAL UFND | [13 empty] | f) CBRMC - Community Based Road Maintenance Contracting
g) MBC - Maintenance by Contract
h) PCF-Performance Challenge Fund-DILG
i) FMRDP - Farm to Market Road
j.) CMGP - Conditional Grant to Provinces
k.) OPAPP - Office of the President Adviser on the Peace Process
l.) LGSF-AM - Local Government Support Fund Assistance to Municipalities
| Prepared by: |  |  | Checked by: |  |  |  |  | Reviewed by: |  |  |  |  | Noted by: | [5 empty] | Recommending Approval:
| Signed |  |  | Signed |  |  |  |  | Signed |  |  |  |  | Signed | [5 empty] | Signed
| RETCHIE A. DE LOS REYES |  |  | MARILOU A. FORONDA |  |  |  |  | EDWIN S. MISA |  |  |  |  | JIVELLYN B. CO | [5 empty] | RAUL G. MABANGLO
| Engineer II |  |  | Engineer IV-Area Engineer |  |  |  |  | Engineer IV-PDP/SIM |  |  |  |  | Asst. PG-Department Head | [5 empty] | PG-Department Head
|  |  |  | 1st Engineering District |  |  |  |  | Planning Division Programming
Survey Investigation and Monitoring

## On-Going pinakaFinal (hidden)
PROVINCE OF DAVAO DEL NORTE
ACCOMPLISHMENT REPORT
FOR THE MONTH OF JANUARY 2018
SECTOR: ECONOMIC (INFRASTRUCTURE DEV'T. PROGRAM)
OFFICE/AGENCY: PROVINCIAL ENGINEER'S OFFICE
AREA: 1ST ENGINEERING DISTRICT - ON-GOING PROJECTS
Name of Project |  |  |  | Type | Physical | Mode | PROJECT DATA | [7 empty] | Financial (000) |  | Physical Accomplishment |  |  |  | Employment |  | REMARKS
|  |  |  | of | Target | of | a) Source of Fund |  |  |  | a) Date A lot. Rel. |  | d) # of days suspended |  | a) Program |  | a) Planned |  | c) Actual |  | Generated
|  |  |  | Project | (Descrip | Impl. | b) Year Approp. |  | d) Project Cost |  | b) Date Started |  | e) # of days extended |  | b) Allotment |  | b) Revised |  | d) Slippage |  | a) # of Persons
|  |  |  | (Location) | tion) |  | c) Implementor |  | e) Project Engineer |  | c)Target Compl. Date |  | f) Date completed |  | c) Disbursement | [5 empty] | b) Man-days
I. | PROJECTS UNDER THE CONTINUING APPROPRIATION | [24 empty] | 893809.45
| A. | Supplemental Budget # 1 CY 2012
1. Purchase, Const. & Impv't. of
|  | Gov't. Facilities (8918) | [20 empty] | Investigation/inspecton of priority projects
|  | 1.1 Repair & Maintenance of Various |  | Road |  | Admin | a) | SB # 1 | d) | 1,000,000.00 | [12 empty] | See project listed below
|  | Local Roads & Drainage |  |  |  |  | b) | CY 2012 | e) | Paraguya/Matuguinas
|  | (Provincewide) |  |  |  |  | c) | PEO
|  | 1.1 | Installation of 48"ø at Purok 2 Crossing | Road |  | Admin | a) | SB # 1 | d) | 106,190.55 | a) | 111/11/16 | d) | - | a) | 106,190.55 | a) | - | c) | - | a) | - | For implementation
|  |  | Highway, Canatan |  |  |  | b) | CY 2012 | e) | - | b) | - | e) | - | b) | 106,190.55 | b) | - | d) | - | b) | -
[7 empty] | c) | PEO |  |  | c) | - | f) | - | c) | -
| B. | SEF (Special Educational Fund)
|  | 1. Const./Comp. of Various Sch.Bldgs./Struct./ |  | Bldgs. |  | Admin | a) | SEF | d) | 57,440.00 | [12 empty] | Investigation/inspecton of priority projects
|  | Fac. |  |  |  |  | b) | Cont. App. | e) | Foronda/Ababon | [12 empty] | ( Priority list c/o deped)
[7 empty] | c) | PEO
|  | 2. Const./Comp. of Various Sch.Bldgs./Struct./ |  | Bldgs. |  | Admin | a) | SEF | d) | 129,631.55 | [12 empty] | Investigation/inspecton of priority projects
|  | Fac. |  |  |  |  | b) | Cont, App. | e) | Foronda/Ababon | [12 empty] | ( Priority list c/o deped)
[7 empty] | c) | PEO
|  | 3. Const./Comp. of Various Sch.Bldgs./Struct./ |  | Bldgs. |  | Admin | a) | SB#1 | d) | 2867900 | [12 empty] | See projects listed below
|  | Fac. |  |  |  |  | b) | CY 2012 | e) | Foronda/Ababon
[7 empty] | c) | PEO
|  | 3.1 | Prop. 3 Rooms Makeshift Bldg., Sitio | Bldgs. |  | Admin | a) | SEF | d) | 770,000.00 | a) | - | d) | - | a) | 770,000.00 | a) | - | c) | - | a) | - | For implementation
|  |  | kapatagan, brgy. Gupitan, Kapalong |  |  |  | b) | CY 2012 | e) | - | b) | - | e) | - | b) | 770,000.00 | b) | - | d) | - | b) | -
[7 empty] | c) | PEO |  |  | c) | - | f) | - | c) | 328,513.39
|  | 3.2 | Const. of 1 Unit Makeshift Bldg. at | Bldgs. |  | Admin | a) | SEF | d) | 700,000.00 | a) | 10/28/17 | d) | - | a) | 700,000.00 | a) | 45.94% | c) | 47.98% | a) | - | On-going
|  |  | Tibucag E/S - Km. 31 Primary Sch. Extn., |  |  |  | b) | CY 2012 | e) | Pasiona | b) | 11/16/17 | e) | - | b) | 700,000.00 | b) | - | d) | - | b) | -
|  |  | Brgy. Palma Gil, Talaingod |  |  |  | c) | PEO |  |  | c) | 02/15/18 | f) | - | c) | 330,064.00
| C. | 5% Calamity Fund CY 2013 | [20 empty] | Investigation/inspecton of priority projects
|  | 1. Prevention and Mitigation |  | Road |  | Admin | a) | 5% CF | d) | 5,932,420.00 | [12 empty] | See project listed below
|  | 1.1 Impv't. Roads and Drainages |  |  |  |  | b) | CY 2013 | e) | Paraguya/Matuguinas | [12 empty] | balance as of January 2018 P 400,000.00
[7 empty] | c) | PEO
|  | a.) | Impv't. of Suaon-Gupitan | Road |  | Admin | a) | 5% CF | d) | 2,900,000.00 | a) | 09/19/17 | d) | - | a) | 2,900,000.00 | a) | 8.32% | c) | 8.32% | a) | - | On-going
[7 empty] | b) | CY 2013 | e) | Gone | b) | 10/16/17 | e) | - | b) | 2,900,000.00 | b) | - | d) | - | b) | -
[7 empty] | c) | PEO |  |  | c) | 03/13/18 | f) |  | c) | 1,289,025.00
2. Rehabilitation and Recovery
|  | 2.1 Rehab./Impv't. of Infra Projects |  | Road |  | Admin | a) | 20% DF | d) | 4,000,000.00 | [12 empty] | Investigation/inspecton of priority projects | SB # 3 CY 2017
[7 empty] | b) | CY 2013 | e) | - | [12 empty] | See project listed below
[7 empty] | c) | PEO | [14 empty] | balance as of January 2018 P 4,000,000.00
| D. | 20% Development Fund CY 2014
|  | 1. Rural Electrification Project |  | Elect. |  | Admin | a) | 20% DF | d) | 1,000,000.00 | [12 empty] | Investigation/inspecton of priority projects
|  | (Provincewide) |  |  |  |  | b) | CY 2014 | e) | Lu | [12 empty] | See project listed below | 1739698.48
[7 empty] | c) | PEO | [14 empty] | balance as of January 2018 P 103,706.09
| E. | 5% Calamity Fund CY 2014
1. Prevention and Mitigation
|  | 1.1 Impv't. of Roads and Drainages |  |  |  |  | a) | 5% CF | d) | 7,090,168.00 | [12 empty] | See project listed below
[7 empty] | b) | CY 2014 | e) | Paraguya/Matuguinas | [12 empty] | balance as of January 2018 P 494,802.00
[7 empty] | c) | PEO
|  | 1.2 Impv't. of Bridges and Cross drainages |  | Cross |  | Admin | a) | 5% CF | d) | 3,000,000.00 | [12 empty] | See project listed below
|  |  |  | Drainage |  |  | b) | CY 2014 | e) | Paraguya/Matuguinas
[7 empty] | c) | PEO
|  | a.) | Impv't. of One Lane-48"ø RCPC Along | Cross |  | Admin | a) | 5% CF | d) | 217,000.00 | a) | - | d) | - | a) | 217,000.00 | a) | - | c) | - | a) | - | For implementation
|  |  | New Corella-Sto. Niño-Macgum-Prov'l. Road | Drainage |  |  | b) | CY 2014 | e) | Paraguya | b) | - | e) | - | b) | 217,000.00 | b) | - | d) | - | b) | -
[7 empty] | c) | PEO |  |  | c) | - | f) |  | c) | 41,901.00
|  | 2. Rehabilitation & Recovery |  |  |  | Admin | a) | 5% CF | d) | 5000000 | a) | - | d) | - | a) | 5000000 | a) | - | c) | - | a) | - | See project listed below | SB # 3 CY 2017
[7 empty] | b) | CY 2014 | e) | Paraguya/Matuguinas | b) | - | e) | - | b) | 5000000 | b) | - | d) | - | b) | - | balance as of January 2018 P 5,000,000.00
[7 empty] | c) | PEO |  |  | c) | - | f) |  | c) | -
| F. | 20% Development Fund CY 2015
|  | 1. Rural Electrification |  | Elect. |  | Admin | a) | 20% DF | d) | 1,000,000.00 | [12 empty] | See projects listed below
|  | (Provincewide) |  |  |  |  | b) | CY 2015 | e) | Lu | [12 empty] | balance as of January 2018 P 825,000.00
[7 empty] | c) | PEO | [15 empty] | Tuburan - 362,614.83
|  | 2. Counterpart to Special Projecs |  | Roads |  | Admin | a) | 20% DF | d) | 5,000,000.00 | [12 empty] | Investigation/inspection of piority projects
[7 empty] | b) | CY 2015 | e) | Foronda/Ababon
[7 empty] | c) | PEO
| G. | 5% Calamity Fund CY 2015 | [21 empty] | 6.53
1. Prevention and Mitigation
|  | 1.1 Revitment of Dike and Slope Protection |  | rivers |  | Admin | a) | 20% DF | d) | 3,325,000.00 | [12 empty] | See project listed below
[7 empty] | b) | CY 2016 | e) | Paraguya/Matuguinas | [12 empty] | balance as of January 2018 P 2,223,687.49
[7 empty] | c) | PEO
|  | a.) | Inst. Of Suaon-Gupitan, Slope Protection | rivers |  | Admin | a) | 20% DF | d) | 2,041,000.00 | a) | - | d) | - | a) | 2,041,000.00 | a) | - | c) | - | a) | - | Waiting for availability of backhoe
|  |  | (Part of 3.325M) |  |  |  | b) | CY 2015 | e) | - | b) | - | e) | - | b) | 2,041,000.00 | b) | - | d) |  | b) | -
[7 empty] | c) | PEO |  |  | c) | - | f) |  | c) | ,281,190.00
2. Rehabilitation and Recovery
|  | 2.1. Rehab. Of infrastructures projects affected |  |  |  | Admin | a) | 5% CF | d) | 5,000,000.00 | [12 empty] | Investigation/inspecton of priority projects
|  | by recent calamity |  |  |  |  | b) | CY 2015 | e) | Paraguya/Matuguinas
[7 empty] | c) | PEO
| H. | Supplemental Budget # 5 CY 2015
1. Purchased, Const. & Imprv't. of Gov't. Facilities (8918)
|  | a) Const./Imprvt. Drainage/Canal Linings |  | Drainage/ |  | Admin | a) | SB # 5 | d) | 2,500,000.00 | [12 empty] | See project listed below
|  |  |  | Canal Lining |  |  | b) | CY 2015 | e) | Foronda
[7 empty] | c) | PEO
|  | a.1 | Improvement of Public Cemetery | Cemetery |  | Contract | a) | SB # 5 | d) | 500,000.00 | a) | 03/05/16 | d) | - | a) | 500,000.00 | a) | - | c) | - | a) | - | For implementation
|  |  | Brgy. Linao, San Isidro |  |  |  | b) | CY 2015 | e) | - | b) | - | e) | - | b) | 500,000.00 | b) | - | d) | - | b) | -
[7 empty] | c) | JB Lazan |  |  | c) | - | f) | - | c) | -
|  | b) Const./Compl./Imprvt. of Various Gov't. Bldgs. |  | Bldgs. |  | Admin | a) | SB # 5 | d) | 31.5M | [12 empty] | See project listed below
|  | Structures & Facilities |  |  |  |  | b) | CY 2015 | e) | Foronda
[7 empty] | c) | PEO
|  | b.1 | Improvement of Day Care Center @ Sitio Luan | Bldgs. |  | Contract | a) | SB # 5 | d) | 500,000.00 | a) | 02/29/16 | d) | - | a) | 500,000.00 | a) | - | c) | - | a) | - | For implementation
|  |  | Brgy. Mabantao, Kapalong |  |  |  | b) | CY 2015 | e) | - | b) | - | e) | - | b) | 500,000.00 | b) | - | d) | - | b) | -
[7 empty] | c) | JB Lazan |  |  | c) | - | f) | - | c) | 441,771.40 | [8 empty] | 4
|  | b.2 | Improvement of Day Care Center @ Sitio Luan | Bldgs. |  | Contract | a) | SB # 5 | d) | 500,000.00 | a) | 02/29/16 | d) | - | a) | 500,000.00 | a) | - | c) | - | a) | - | For implementation
|  |  | Brgy. Mabantao, Kapalong |  |  |  | b) | CY 2015 | e) | - | b) | - | e) | - | b) | 500,000.00 | b) | - | d) | - | b) | -
[7 empty] | c) | JB Lazan |  |  | c) | - | f) | - | c) | 441,771.40
|  | b.3 | Improvement of Public Cemetery | Cemetery |  | Contract | a) | SB # 5 | d) | 500,000.00 | a) | 03/05/16 | d) | - | a) | 500,000.00 | a) | - | c) | - | a) | - | For implementation
|  |  | Brgy. Linao, San Isidro |  |  |  | b) | CY 2015 | e) | - | b) | - | e) | - | b) | 500,000.00 | b) | - | d) | - | b) | -
[7 empty] | c) | JB Lazan |  |  | c) | - | f) | - | c) | -
|  | 2. Purchased, Const. & Imprv't. of Gov't. Facilities (3918) |  |  |  |  | a) | SB # 5 | d) | 130,000,000.00 | [12 empty] | See projects listed below
[7 empty] | b) | CY 2015 | e) | Foronda
[7 empty] | c) | PEO
|  | 1 | Upgrading of of DNSTC (Commercial Building) | Bldg. |  | Contract | a) | SB # 5 | d) | 29,999,981.00 | a) | CY 2015 | d) | - | a) | 29,999,981.00 | a) | 100.00% | c) | 98.449% | a) | - | On-going
|  |  | Sports Complex Center, Mankilam |  |  |  | b) | CY 2015 | e) | Escurzon | b) | 10/28/16 | e) | - | b) | 29,999,981.00 | b) | - | d) | -1.551% | b) | -
[7 empty] | c) | PEO |  |  | c) | 01/31/17 | f) |  | c) | 4,499,997.15
| I. | Trust Fund
1. PAMANA-DILG
|  | 1.1 Construction of Biga Bridges, Kapalong |  | Road | - | Contract | a) | TF | d) | 24959503.45 | a) | CY 2014 | d) | - | a) | 24959503.45 | a) | 16.21% | c) | 8.91% | a) | - | Suspended
[7 empty] | b) | CY 2015 | e) | Limpo | b) | 07/01/16 | e) | - | b) | 24959503.45 | b) | - | d) | -7.3% | b) | - |  | 30
[7 empty] | c) | - |  |  | c) | 10/21/18 | f) | - | c) | 37,439,255.18 | [7 empty] | .
|  | 1.2 Road Rehabilitation/Improvement of Prk. 3, |  | Road | - | Contract | a) | TF | d) | 50,500,288.95 | a) | CY 2014 | d) | - | a) | 50,500,288.95 | a) | 90.96% | c) | 70.55% | a) | - | On-going
|  | Palma Gil-Prk.2 (side 2), Sto. Niño-Mahayahay-Tugas- |  |  |  |  | b) | CY 2015 | e) | Dadula | b) | 07/07/16 | e) | - | b) | 50,500,288.95 | b) | 79.74% | d) | -9.19% | b) | -
|  | Nanaga Road, with 1 -unit, 40 ln.m PSCG Bridge, |  |  |  |  | c) | - |  |  | c) | 03/12/18 | f) | - | c) | 7,575,009.962
Kapalong
2. PRDP
|  | 2.1 Rehab. New Visayas-Binancian |  | Roads | 7.84 kms. | Contract. | a) | TF | d) | 86,500,370.47 | a) | CY 2014 | d) | 226 CD | a) | 86,500,370.47 | a) | 100.00% | c) | 69.54% | a) | 36 | On-going
|  | Asuncion. Davao del Norte |  |  |  |  | b) | CY 2014 | e) | Medalla | b) | 10/18/15 | e) | 93 CD | b) | 86,500,370.47 | b) | 77.49% | d) | -7.95% | b) | 900 | Approved variation order P 7,668,482.11
|  | (Provincial Counterpart: 1.205830M) |  |  |  |  | c) | Dvo. Rock Mixer |  |  | c) | 04/10/18 | f) | - | c) | 11,824,783.15
|  | 2.3 Rehab. Of Sto. Niño-Igangon FMR |  | #REF! | 8.93 kms. | Contract. | a) | TF | d) | 74,173,694.50 | a) | CY 2015 | d) | - | a) | 74,173,694.50 | a) | 82.681% | c) | 70.112% | a) | - | On-going
|  | San Isidro, Davao del Norte |  |  |  |  | b) | CY 2015 | e) | Fabiala | b) | 03/21/16 | e) | 146 CD | b) | 74,173,694.50 | b) | - | d) | -12.57% | b) | -
[7 empty] | c) | Monolitic Const./R.R Seismundo |  |  | c) | 03/03/18 | f) | - | c) | 12,272,507.70
|  | 2.4 Rehab. Of Capungagan-Boundary San |  | #REF! | 10.6 kms. | Contract. | a) | TF | d) | 103,311,208.43 | a) | CY 2015 | d) | 187 CD | a) | 103,311,208.43 | a) | 88.03% | c) | 13.563% | a) | 15 | On-going
|  | Miguel FMR, Kapalong, Davao del Norte |  |  |  |  | b) | CY 2015 | e) | Nasol | b) | 04/06/16 | e) | 28 CD | b) | 103,311,208.43 | b) | 36.083% | d) | -22.52% | b) | 155 | Deductive entry Item 311 due to not following
[7 empty] | c) | VICLAO |  |  | c) | 11/16/18 | f) | - | c) | - | [6 empty] | the specifications.
|  | 2.5 Rehab. Of Pob.-Limbaan-Suawon-Macgum |  | #REF! | 8.93 kms./ | Contract. | a) | TF | d) | 190,253,491.98 | a) | CY 2015 | d) | - | a) | 190,253,491.98 | a) | 92.14% | c) | 20.73% | a) | - | On-going
|  | FMR w/ Bridge, New Corella, Davao del Norte |  |  | 42 ln.m |  | b) | CY 2015 | e) | Madrigal | b) | 04/08/16 | e) | 133 CD | b) | 190,253,491.98 | b) | 43.963% | d) | -23.23% | b) | - | No pouring activity due to no stocks of cement
[7 empty] | c) | - |  |  | c) | 06/01/19 | f) | - | c) | 28538091.3
3. KALSADA
|  | 3.1 Improvement of Km. 9 Sagayen-Sawata Provincial |  | Roads | 9.09497km. | Contract. | a) | TF | d) | 60,329,230.72 | a) | CY 2015 | d) | - | a) | 60,329,230.72 | a) | 84.50% | c) | 34.73% | a) | 31 | On-going
|  | San Isidro, Davao del Norte |  |  |  |  | b) | CY 2015 | e) | Limpo | b) | 08/26/16 | e) | - | b) | 60,329,230.72 | b) | 58.77% | d) | -24.04% | b) | 837
|  | (Part of 60.329230.72M) (Contract Cost: P 43.597322.62M) |  |  |  |  | c) | ARN Builders. Inc. |  |  | c) | 04/21/18 | f) | - | c) | 6,539,598.39
(SB # 1 CY 2016 P 12.270446M)
| J. | 20% Development Fund CY 2016
1. Repair & Maint. Of Various Prov'l. Roads and Bridges
|  | Maintenance by Contract: Package 3 |  |  |  | Contract
063 |  | San Juan - New Talisay |  | Road Maintenance | 5.13 |  | a) | 20% DF | d) | 1657125.76 | a) | 04/04/16 | d) | - | a) | 1657125.76 | a) | 83.97% | c) | 83.97% | a) | 3 | On-going
004 |  | Asuncion-New Alegria-Bdry. Cuambogan |  |  | 6.66 |  | b) | CY 2016 | e) | Paraguya | b) | 07/07/16 | e) | - | b) | 1657125.76 | b) |  | d) |  | b) | 45
005 |  | Asuncion -Monte Carlo-Del Pilar |  |  | 7.93 |  | c) | SBB Const. & Supply |  |  | c) | 07/06/17 | f) | - | c) | -
050 |  | Jct. Monte Calo-Upper Cabaywa-Canatan |  |  | 4.61
|  | 2. Various of Water System Project (Provincewide) |  | Water | - | Admin | a) | 20% DF | d) | 2,000,000.00 | [12 empty] | Investigation/Inspection of priority projects
|  |  |  | System |  |  | b) | CY 2016 | e) | Foronda/Ababon
[7 empty] | c) | PEO
|  | 3. Counterpart to Special Projects (Provincewide) |  | Road | - | Admin | a) | 20% DF | d) | 55,000,000.00 | [12 empty] | Investigation/Inspection of priority projects
[7 empty] | b) | CY 2016 | e) | Foronda
[7 empty] | c) | PEO
|  | 4. Const./Rehab./Comp. of Various Gov't. Bldgs. |  | Bldgs. | - | Admin | a) | 20% DF | d) | 13,516,919.00 | [12 empty] | See projects listed below
|  | Struct., Fac. (Provincewide) |  |  |  |  | b) | CY 2016 | e) | Foronda
[7 empty] | c) | PEO
|  | 4.1 | Upgrading of DNSTC (DAVNOR Pavilion | Bldgs. | - | Admin | a) | 20% DF | d) | 1,500,000.00 | a) | 01/27/16 | d) | - | a) | 1,500,000.00 | a) | 61.10% | c) | 61.10% | a) | - | Suspended dated: 12/01/16
|  |  | Ph.II, Sports Center, Mankilam |  |  |  | b) | CY 2016 | e) | Pasiona/Escurzon | b) | 09/01/16 | e) | - | b) | 1,500,000.00 | b) | - | d) | - | b) | -
[7 empty] | c) | PEO |  |  | c) | 12/30/16 | f) | - | c) | 1,417,394.73
|  | 4.2 | Const. of Recreation Facilities Area Camp. | Bldgs. | - | Admin | a) | 20% DF | d) | 52,088.00 | a) | - | d) | - | a) | 52,088.00 | a) | - | c) | - | a) | - | For implementation
|  |  | Gen. Manuel T. Yan Sr. Tuburan, Mawab |  |  |  | b) | CY 2016 | e) | - | b) | - | e) | - | b) | 52,088.00 | b) | - | d) | - | b) | -
[7 empty] | c) | PEO |  |  | c) | - | f) | - | c) | -
|  | 5. Rural Electrification (Provincewide) |  | Electrification |  | Admin | a) | 20% DF | d) | 2,000,000.00 | [12 empty] | Investigation/Inspection of priority projects
[7 empty] | b) | CY 2016 | e) | Lu | [12 empty] | balance as of January 2018 P 1,674,000.00
[7 empty] | c) | PEO
| K. | Annual Budget CY 2016 - Operation of Bahay Pag-Asa (Const. in
in Progress-Agency Assets)
|  | 1 | Expansion of Residential Facilities for Minors | Bldg. |  | Admin | a) | 20% DF | d) | 1,500,000.00 | a) | 09/14/15 | d) | - | a) | 1,500,000.00 | a) | 65.84% | c) | 65.84% | a) | 10 | Suspended dated Oct. 2, 2017
|  |  | (Ph.I), New Corella |  |  |  | b) | CY 2016 | e) | Gone | b) | 01/23/17 | e) | 26 WD | b) | 1,500,000.00 | b) | - | d) | - | b) | 70
[7 empty] | c) | PEO |  |  | c) | 10/09/17 | f) | - | c) | 926,197.55
| L. | 5% Calamity Fund CY 2016
1. Prevention and Mitigation
|  | 1.1 | Revitment of Dike and Slope Protection | rivers |  | Admin | a) | 5% CF | d) | 3,325,000.00 | [12 empty] | See project listed below
[7 empty] | b) | CY 2016 | e) | Paraguya/Matuguinas
[7 empty] | c) | PEO
|  | a | Prop. Slope Protection of Libuganon River |  |  | Admin | a) | 5% CF | d) | 3,325,000.00 | a) | 03/06/17 | d) | - | a) | 3,325,000.00 | a) | - | c) | - | a) | - | PO on process
|  |  | Along Kapalong-Mabantao-Florida |  |  |  | b) | CY 2016 | e) | - | b) | - | e) | - | b) | 3,325,000.00 | b) | - | d) | - | b) | -
|  |  | Provincial Road Ph.I (Capungagan- |  |  |  | c) | PEO |  |  | c) | - | f) | - | c) | 944,090.00
Mabantao Portion)
|  | 1.2 | Improvement of Bridges and Cross Drainage | Roads |  | Admin | a) | 20% DF | d) | 2,900,000.00 | [12 empty] | Investigation/Inspection of priority projects
[7 empty] | b) | CY 2016 | e) | Paraguya/Matuguinas
[7 empty] | c) | PEO
|  | a | Rehab./Impv't. of Tungol Bridge Approach ''A" |  |  | Admin | a) | 5% CF | d) | 2,900,000.00 | a) | 12/20/16 | d) | - | a) | 2,900,000.00 | a) | 91.14% | c) | 91.14% | a) | - | Suspended dated 12/08/17
|  |  | Along Kapalong-Mabantao-Florida Road |  |  |  | b) | CY 2016 | e) | Gone | b) | 09/18/17 | e) | - | b) | 2,900,000.00 | b) | - | d) | - | b) | -
[7 empty] | c) | PEO |  |  | c) | 01/04/18 | f) | - | c) | 1,300,630.32
| M. | Supplemental Budget # 2 CY 2016 - PSWDO
|  | 1 | Ground Development at Women Dev't. Center | Ground |  | Admin | a) | SB # 1 | d) | 2,000,000.00 | a) | 09/16/17 | d) | - | a) | 2,000,000.00 | a) | - | c) | - | a) | - | PO on process
|  |  | New Corella, DDN |  |  |  | b) | CY 2016 | e) | - | b) | - | e) | - | b) | 2,000,000.00 | b) | - | d) | - | b) | -
[7 empty] | c) | PEO |  |  | c) | - | f) | - | c) | -
| N. | Trust Fund
1. PCF-Performance Challenge Fund-DILG
|  | 1.1 | Upgrading of DNSTC (DAVNOR Pavilion | Bldgs. | - | Admin | a) | PCF | d) | 7,000,000.00 | a) | CY 2016 | d) | 117 WD | a) | 7,000,000.00 | a) | 92.25% | c) | 92.25% | a) | - | Suspended date June 16, 2017 due to change of
|  |  | Ph.I, Sports Center, Mankilam |  |  |  | b) | CY 2016 | e) | Pasiona/Escurzon | b) | 03/16/16 | e) | - | b) | 7,000,000.00 | b) | - | d) | - | b) | - | signage designs & waiting for the Re-PR of 1 unit
[7 empty] | c) | PEO |  |  | c) | 06/30/17 | f) | - | c) | 4,986,523.32 | [6 empty] | Job Order for Inst. Of signage.
2. PRDP
|  | 2.1 | Rehab. Of Sonlon-Camansa FMR, | Bldgs. | - | Admin | a) | PRDP | d) | 143,483,158.94 | a) | - | d) | - | a) | 143,483,158.94 | a) | - | c) | - | a) | - | POW & Plans already forwarded to
|  |  | Asuncion, Davao del Norte |  |  |  | b) | CY 2016 | e) | - | b) | - | e) | - | b) | 143,483,158.94 | b) | - | d) | - | b) | - | PRDP Region for checking
[7 empty] | c) | PEO |  |  | c) | - | f) | - | c) | -
3. PAMANA-DILG
|  | 3.1 | Construction of Civic Center, Madaum, Tagum City | Bldgs. | - | Admin | a) | PAMANA | d) | 3,000,000.00 | a) | CY 2016 | d) | - | a) | 3,000,000.00 | a) | - | c) | - | a) | - | Waiting for the approval of Contract Agreement
[7 empty] | b) | CY 2016 | e) | - | b) | - | e) | - | b) | 3,000,000.00 | b) | - | d) | - | b) | -
[7 empty] | c) | PEO |  |  | c) | - | f) | - | c)
|  | 3.2 | Construction of Civic Center, San Isidro, Tagum City | Bldgs. | - | Admin | a) | PAMANA | d) | 2,000,000.00 | a) | CY 2016 | d) | - | a) | 2,000,000.00 | a) | - | c) | - | a) | - | Re-bidding
[7 empty] | b) | CY 2016 | e) | - | b) | - | e) | - | b) | 2,000,000.00 | b) | - | d) | - | b) | -
[7 empty] | c) | PEO |  |  | c) | - | f) | - | c)
| O. | 20% Development Fund CY 2017 |  | Road Maintenance | KM |  | a) | 20% DF
Road ID |  | 1. Repair & Maint. Of Various Prov'l. Roads and Bridges |  |  | 525.3 |  | b) | CY 2017 | d) | 34,562,000.01
[7 empty] | c) | Contract/CBRMC | e) | Paraguya | [12 empty] | See list of Provincial Roads
11DAN | [12 empty] | f) | - | c) | -
|  | Sta. Felomina-San Roque |  | Road Maintenance | 7.68 | CBRMC | a) | 20% DF | d) | 87052.12 | a) | 01/06/17 | d) | - | a) | 87052.12 | a) | 33.33% | c) | 33.33% | a) |  | On-going
008 | [6 empty] | b) | CY 2017 | e) | Garcia | b) | 08/23/17 | e) | - | b) | 87052.12 | b) |  | d) |  | b)
[7 empty] | c) | STA. FELOMINA FARMERS |  |  | c) | 05/22/18 | f) | - | c) | 411,094.16
|  | Semong-Palma Gil |  | Road Maintenance | 2.73 | MBC | a) | 20% DF | d) | 225186.11 | a) | 01/06/17 | d) | - | a) | 225186.11 | a) |  | c) |  | a) |  | Schedule for Maintenance
018 | [6 empty] | b) | CY 2017 | e) |  | b) |  | e) | - | b) | 225186.11 | b) |  | d) |  | b)
[7 empty] | c) | MAG CORP. |  |  | c) |  | f) | - | c)
|  | Angelo - Dagohoy |  | Road Maintenance | 2.19 | MBC | a) | 20% DF | d) | 177811.01 | a) | 01/06/17 | d) | - | a) | 177811.01 | a) |  | c) |  | a) |  | Schedule for Maintenance
021 | [6 empty] | b) | CY 2017 | e) | - | b) |  | e) | - | b) | 177811.01 | b) |  | d) |  | b)
[7 empty] | c) | MAG CORP. |  |  | c) |  | f) | - | c)
|  | Jct. New Boholano - New Loon (Revised) |  | Road Maintenance | 4.77 | CBRMC | a) | 20% DF | d) | 82806.67 | a) | 01/04/17 | d) | - | a) | 82806.67 | a) | 50.00% | c) | 50.00% | a) |  | On-going
031 | [6 empty] | b) | CY 2017 | e) | Garcia | b) | 08/29/17 | e) | - | b) | 82806.67 | b) |  | d) |  | b)
[7 empty] | c) | NEW LOON FARMERS ASSOCIATION |  |  | c) | 05/28/18 | f) | - | c) | 3,000.00
|  | Florida-Suaon-Jct. Gupitan (Revised) |  | Road Maintenance | 15.57 | CBRMC | a) | 20% DF | d) | 282388.58 | a) | 01/04/17 | d) | - | a) | 282388.58 | a) | 32.53% | c) | 32.53% | a) |  | On-going
032 | [6 empty] | b) | CY 2017 | e) | Garcia | b) | 08/16/17 | e) | - | b) | 282388.58 | b) |  | d) |  | b)
[7 empty] | c) | SUOAN UPLAND REFORESTRATION FARMERS |  |  | c) | 05/15/18 | f) | - | c)
|  | Sta. Fe-Mambing (Revised) |  | Road Maintenance | 10.96 | CBRMC | a) | 20% DF | d) | 180473.9 | a) | 01/04/17 | d) | - | a) | 180473.9 | a) | 23.71% | c) | 23.71% | a) |  | On-going
046 | [6 empty] | b) | CY 2017 | e) | Garcia | b) | 08/22/17 | e) | - | b) | 180473.9 | b) |  | d) |  | b)
[7 empty] | c) | BUCARAN FARMERS |  |  | c) | 08/21/18 | f) | - | c)
|  | Limbaan-Sta. Fe-El Salvador (Revised) |  | Road Maintenance | 18.82 | CBRMC | a) | 20% DF | d) | 322729.8 | a) | 01/04/17 | d) | - | a) | 322729.8 | a) | 33.33% | c) | 33.33% | a) |  | On-going
047 | [6 empty] | b) | CY 2017 | e) | Garcia | b) | 08/22/17 | e) | - | b) | 322729.8 | b) |  | d) |  | b)
[7 empty] | c) | BUCARAN FARMERS |  |  | c) | 05/21/18 | f) | - | c)
|  | New Corella Saug |  | Road Maintenance | 12.52 | CBRMC | a) | 20% DF | d) | 224800 | a) | 01/04/17 | d) | - | a) | 224800 | a) | 48.60% | c) | 48.60% | a) |  | On-going
048 | [6 empty] | b) | CY 2017 | e) | Garcia | b) | 09/30/17 | e) | - | b) | 224800 | b) |  | d) |  | b)
[7 empty] | c) | SUAON RUBBER BANANA FARMERS ASSOC. |  |  | c) | 03/29/18 | f) | - | c)
|  | Del Pilar - Jct. Silangan (Revised) |  | Road Maintenance | 4.17 | CBRMC | a) | 20% DF | d) | 91298.56 | a) |  | d) | - | a) | 91298.56 | a) |  | c) |  | a) |  | For implementation
051 | [6 empty] | b) | CY 2017 | e) | Garcia | b) |  | e) | - | b) | 91298.56 | b) |  | d) |  | b)
[7 empty] | c) | SAN ISIDRO FARMERS |  |  | c) |  | f) | - | c)
|  | Carcor - Patrocenio - Jct. Bayabas (Revised) |  | Road Maintenance | 14.68 | CBRMC | a) | 20% DF | d) | 259033.12 | a) | 01/04/17 | d) | - | a) | 259033.12 | a) | 5.00% | c) | 5.00% | a) |  | On-going
057 | [6 empty] | b) | CY 2017 | e) | Garcia | b) | 08/15/17 | e) | - | b) | 259033.12 | b) |  | d) |  | b)
[7 empty] | c) | MOTOR OPERATORS DRIVERS ASSOC. |  |  | c) | 05/14/18 | f) | - | c)
|  | Carcor - Jct. Kauswagan (Revised) |  | Road Maintenance | 4.32 | MBC | a) | 20% DF | d) | 373118.29 | a) | 01/04/17 | d) | - | a) | 373118.29 | a) | 20.21% | c) | 20.21% | a) |  | On-going
060 | [6 empty] | b) | CY 2017 | e) | Paraguya | b) | 08/31/17 | e) | - | b) | 373118.29 | b) |  | d) |  | b)
[7 empty] | c) | MAG CORP. |  |  | c) | 05/31/18 | f) | - | c)
|  | Del Pilar - Prk. 9 Bagsak - San Jose |  | Road Maintenance | 4.99 | MBC | a) | 20% DF | d) | 441410 | a) | 01/04/17 | d) | - | a) | 441410 | a) | 19.53% | c) | 19.53% | a) |  | On-going
061 | [6 empty] | b) | CY 2017 | e) | Paraguya | b) | 08/31/17 | e) | - | b) | 441410 | b) |  | d) |  | b)
[7 empty] | c) | MAG CORP. |  |  | c) | 05/31/18 | f) | - | c)
|  | Del Pilar - El Unido |  | Road Maintenance | 1.32 | MBC | a) | 20% DF | d) | 81857.8 | a) | 01/04/17 | d) | - | a) | 81857.8 | a) | 23.58% | c) | 23.58% | a) |  | On-going
062 | [6 empty] | b) | CY 2017 | e) | Paraguya | b) | 08/31/17 | e) | - | b) | 81857.8 | b) |  | d) |  | b)
[7 empty] | c) | MAG CORP. |  |  | c) | 05/31/18 | f) | - | c)
|  | New Bohol - Jct. El Unido |  | Road Maintenance | 2.12 | MBC | a) | 20% DF | d) | 190033.85 | a) | 01/04/17 | d) | - | a) | 190033.85 | a) | 16.62% | c) | 16.62% | a) |  | On-going
065 | [6 empty] | b) | CY 2017 | e) | Paraguya | b) | 08/31/17 | e) | - | b) | 190033.85 | b) |  | d) |  | b)
[7 empty] | c) | MAG CORP. |  |  | c) | 05/31/18 | f) | - | c)
|  | New Corella - El Unido - Jct. Mesaoy |  | Road Maintenance | 8.63 | MBC | a) | 20% DF | d) | 756773.87 | a) | 01/04/17 | d) | - | a) | 756773.87 | a) | 16.83% | c) | 16.83% | a) |  | On-going
066 | [6 empty] | b) | CY 2017 | e) | Paraguya | b) | 08/31/17 | e) | - | b) | 756773.87 | b) |  | d) |  | b)
[7 empty] | c) | MAG CORP. |  |  | c) | 05/31/18 | f) | - | c)
|  | Jct. San Juan - Jct. Mesaoy (Revised) |  | Road Maintenance | 1.82 | MBC | a) | 20% DF | d) | 184134.16 | a) | 01/04/17 | d) | - | a) | 184134.16 | a) | 19.16% | c) | 19.16% | a) |  | On-going
068 | [6 empty] | b) | CY 2017 | e) | Paraguya | b) | 08/31/17 | e) | - | b) | 184134.16 | b) |  | d) |  | b)
[7 empty] | c) | MAG CORP. |  |  | c) | 05/31/18 | f) | - | c)
|  | Mesaoy - New Bohol (Revised) |  | Road Maintenance | 5.36 | CBRMC | a) | 20% DF | d) | 110407.56 | a) |  | d) | - | a) | 110407.56 | a) | - | c) | - | a) |  | Re-bid for schedule
070 | [6 empty] | b) | CY 2017 | e) | Garcia | b) |  | e) | - | b) | 110407.56 | b) |  | d) |  | b)
[7 empty] | c) | - |  |  | c) |  | f) | - | c) | -
|  | Bdry. Tagum - Baca - New Corella (Revised) |  | Road Maintenance | 13.01 | CBRMC | a) | 20% DF | d) | 138009.46 | a) | 01/04/17 | d) | - | a) | 138009.46 | a) | 23.19% | c) | 23.19% | a) |  | On-going
071 | [6 empty] | b) | CY 2017 | e) | Garcia | b) | 06/15/17 | e) | - | b) | 138009.46 | b) |  | d) |  | b)
[7 empty] | c) | DURAIN DACUDAO ASSOC. |  |  | c) | 12/31/17 | f) | - | c)
II. PROJECTS UNDER THE CURRENT APPROPRIATION | [5 empty] | Admin
A. 20% Development Fund CY 2018 |  |  |  | Road Maintenance | KM | Contract | a) | 20% DF
Road ID |  | 1. Repair & Maint. Of Various Prov'l. Roads and Bridges |  |  | 525.3 | CBRMC | b) | CY 2018 | d) | 36268943 | a) | 01/03/18 | d) | - | a) | 36268943 | a) | 5.06% | c) | 8.33% | a) | 46 | On-going
[6 empty] | Contract with CBRMC | c) | PEO/Contract/CBRMC | e) | Paraguya | b) | 01/03/18 | e) | - | b) | 36268943 | b) | - | d) | +3.27% | b) | 920 | See list of Provincial Roads
11DAN | [10 empty] | c) | 12/31/18 |  |  | c) | -
|  | Jct. Highway Magatos - New Bantayan |  | Road Maintenance | 7.1 | ADMIN | a) | 20% DF | d) | 189489.99 | a) | - | d) | - | a) | 189489.99 | a) | - | c) | - | a) | - | Scheduled for Maintenance Works 2nd Quarter
001 | [6 empty] | b) | CY 2017 | e) | Ibañez | b) | - | e) | - | b) | 189489.99 | b) | - | d) | - | b) | -
[7 empty] | c) | Admin |  |  | c) | - | f) | - | c)
|  | Jct. Highway Magatos - New Bantayan |  | Road Maintenance | 7.1 | MBC | a) | 20% DF | d) | 453436.38 | a) | - | d) | - | a) | 453436.38 | a) | - | c) | - | a) | - | Scheduled for Maintenance Works 2nd Quarter
001 | [6 empty] | b) | CY 2017 | e) | - | b) | - | e) | - | b) | 453436.38 | b) | - | d) | - | b) | -
[7 empty] | c) | Admin |  |  | c) | - | f) | - | c)
|  | Magatos-Bdry Pagsabangan |  | Road Maintenance | 8.33 | ADMIN | a) | 20% DF | d) | 129005.52 | a) | - | d) | - | a) | 129005.52 | a) | - | c) | - | a) | - | Scheduled for Maintenance Works 2nd Quarter
002 | [6 empty] | b) | CY 2017 | e) | Ibañez | b) | - | e) | - | b) | 129005.52 | b) | - | d) | - | b) | -
[7 empty] | c) | Admin |  |  | c) | - | f) | - | c)
|  | Magatos-Bdry Pagsabangan |  | Road Maintenance | 8.33 | MBC | a) | 20% DF | d) | 470820.54 | a) | - | d) | - | a) | 470820.54 | a) | - | c) | - | a) | - | Scheduled for Maintenance Works 2nd Quarter
002 | [6 empty] | b) | CY 2017 | e) | - | b) | - | e) | - | b) | 470820.54 | b) | - | d) | - | b) | -
[7 empty] | c) | Admin |  |  | c) | - | f) | - | c)
|  | Ilog-New Bantayan |  | Road Maintenance | 2.68 | ADMIN | a) | 20% DF | d) | 52119.03 | a) | - | d) | - | a) | 52119.03 | a) | - | c) | - | a) | - | Scheduled for Maintenance Works 2nd Quarter
003 | [6 empty] | b) | CY 2017 | e) | Fabian | b) | - | e) | - | b) | 52119.03 | b) | - | d) | - | b) | -
[7 empty] | c) | Admin |  |  | c) | - | f) | - | c)
|  | Ilog-New Bantayan |  | Road Maintenance | 2.68 | MBC | a) | 20% DF | d) | 203901.02 | a) | - | d) | - | a) | 203901.02 | a) | - | c) | - | a) | - | Scheduled for Maintenance Works 3rd Quarter
003 | [6 empty] | b) | CY 2017 | e) | - | b) | - | e) | - | b) | 203901.02 | b) | - | d) | - | b) | -
[7 empty] | c) | Admin |  |  | c) | - | f) | - | c)
|  | Asuncion-New Alegria-Bdry. Cuambogan |  | Road Maintenance | 6.66 | ADMIN | a) | 20% DF | d) | 104499.26 | a) | - | d) | - | a) | 104499.26 | a) | - | c) | - | a) | - | Scheduled for Maintenance Works 3rd Quarter
004 | [6 empty] | b) | CY 2017 | e) | Ibañez | b) | - | e) | - | b) | 104499.26 | b) | - | d) | - | b) | -
[7 empty] | c) | Admin |  |  | c) | - | f) | - | c)
|  | Asuncion-New Alegria-Bdry. Cuambogan |  | Road Maintenance | 6.66 | MBC | a) | 20% DF | d) | 448441.74 | a) | - | d) | - | a) | 448441.74 | a) | - | c) | - | a) | - | Scheduled for Maintenance Works 3rd Quarter
004 | [6 empty] | b) | CY 2017 | e) | - | b) | - | e) | - | b) | 448441.74 | b) | - | d) | - | b) | -
[7 empty] | c) | Admin |  |  | c) | - | f) | - | c)
|  |  |  | Road Maintenance | 7.93 | ADMIN | a) | 20% DF | d) | 157936.8 | a) | - | d) | - | a) | 157936.8 | a) | - | c) | - | a) | - | Scheduled for Maintenance Works 3rd Quarter
005 |  | Asuncion -Monte Carlo-Del Pilar |  |  |  |  | b) | CY 2017 | e) | Ibañez | b) | - | e) | - | b) | 157936.8 | b) | - | d) | - | b) | -
[7 empty] | c) | Admin |  |  | c) | - | f) | - | c)
|  |  |  | Road Maintenance | 7.93 | MBC | a) | 20% DF | d) | 654493.98 | a) | - | d) | - | a) | 654493.98 | a) | - | c) | - | a) | - | Scheduled for Maintenance Works 3rd Quarter
005 |  | Asuncion -Monte Carlo-Del Pilar |  |  |  |  | b) | CY 2017 | e) | - | b) | - | e) | - | b) | 654493.98 | b) | - | d) | - | b) | -
[7 empty] | c) | Admin |  |  | c) | - | f) | - | c)
|  |  |  | Road Maintenance | 4.85 | ADMIN | a) | 20% DF | d) | 77898.77 | a) | - | d) | - | a) | 77898.77 | a) | - | c) | - | a) | - | Scheduled for Maintenance Works 3rd Quarter
006 |  | Jct. Highway Canatan-Jct. Highway Magatos |  |  |  |  | b) | CY 2017 | e) | Ibañez | b) | - | e) | - | b) | 77898.77 | b) | - | d) | - | b) | -
[7 empty] | c) | Admin |  |  | c) | - | f) | - | c)
|  |  |  | Road Maintenance | 4.85 | MBC | a) | 20% DF | d) | 329310.73 | a) | - | d) | - | a) | 329310.73 | a) | - | c) | - | a) | - | Scheduled for Maintenance Works 2nd Quarter |  |  | 893809.45
006 |  | Jct. Highway Canatan-Jct. Highway Magatos |  |  |  |  | b) | CY 2017 | e) | - | b) | - | e) | - | b) | 329310.73 | b) | - | d) | - | b) | -
[7 empty] | c) | Admin |  |  | c) | - | f) | - | c)
|  |  |  | Road Maintenance | 4.34 | Admin | a) | 20% DF | d) | 209448.3 | a) | - | d) | - | a) | 209448.3 | a) | - | c) | - | a) | - | Scheduled for Maintenance Works 3rd Quarter
007 |  | Jct. Highway Cantan-Doñatan |  |  |  |  | b) | CY 2017 | e) | - | b) | - | e) | - | b) | 209448.3 | b) | - | d) | - | b) | -
[7 empty] | c) | Admin |  |  | c) | - | f) | - | c)
|  |  |  | Road Maintenance | 7.68 | Admin | a) | 20% DF | d) | 384439.11 | a) | - | d) | - | a) | 384439.11 | a) | - | c) | - | a) | - | Scheduled for Maintenance Works 1st Quarter
008 |  | Sta. Felomina-San Roque |  |  |  |  | b) | CY 2017 | e) | Ibañez | b) | - | e) | - | b) | 384439.11 | b) | - | d) | - | b) | -
[7 empty] | c) | Admin |  |  | c) | - | f) | - | c) | 164405.38
|  |  |  | Road Maintenance | 7.68 | CBRMC | a) | 20% DF | d) | 87052.12 | a) | - | d) | - | a) | 87052.12 | a) | - | c) | - | a) | - | Scheduled for Maintenance Works 1st Quarter
008 |  | Sta. Felomina-San Roque |  |  |  |  | b) | CY 2017 | e) | - | b) | - | e) | - | b) | 87052.12 | b) | - | d) | - | b) | -
[7 empty] | c) | Admin |  |  | c) | - | f) | - | c)
|  |  |  | Road Maintenance | 14.04 | Admin | a) | 20% DF | d) | 578652.71 | a) | - | d) | - | a) | 578652.71 | a) | - | c) | - | a) | - | Scheduled for Maintenance Works 1st Quarter
009 |  | Jct. Sagayen-Sonlon |  |  |  |  | b) | CY 2017 | e) | Ibañez | b) | - | e) | - | b) | 578652.71 | b) | - | d) | - | b) | -
[7 empty] | c) | Admin |  |  | c) | - | f) | - | c) | 115,781.00
|  |  |  | Road Maintenance | 11.6 | Admin | a) | 20% DF | d) | 429687.34 | a) | - | d) | - | a) | 429687.34 | a) | - | c) | - | a) | - | Scheduled for Maintenance Works 3rd Quarter
010 |  | Saug-Sonlon-Bdy Longanapan |  |  |  |  | b) | CY 2017 | e) | Ibañez | b) | - | e) | - | b) | 429687.34 | b) | - | d) | - | b) | -
[7 empty] | c) | Admin |  |  | c) | - | f) | - | c)
|  |  |  | Road Maintenance | 2.99 | Admin | a) | 20% DF | d) | 109110.75 | a) | - | d) | - | a) | 109110.75 | a) | - | c) | - | a) | - | Scheduled for Maintenance Works 3rd Quarter
011 |  | Jct. New Visayas-Buan |  |  |  |  | b) | CY 2017 | e) | Ibañez | b) | - | e) | - | b) | 109110.75 | b) | - | d) | - | b) | -
[7 empty] | c) | Admin |  |  | c) | - | f) | - | c)
|  |  |  | Road Maintenance | 7.07 | Admin | a) | 20% DF | d) | 266471.86 | a) | - | d) | - | a) | 266471.86 | a) | - | c) | - | a) | - | Scheduled for Maintenance Works 1st Quarter
012 |  | Sonlon-New Visayas-Camansa |  |  |  |  | b) | CY 2017 | e) | Ibañez | b) | - | e) | - | b) | 266471.86 | b) | - | d) | - | b) | -
[7 empty] | c) | Admin |  |  | c) | - | f) | - | c) | 53,698.37
|  | Pamacaun-Lasang-Banate |  | Road Maintenance | 4.11 | Admin | a) | 20% DF | d) | 178406.28 | a) | - | d) | - | a) | 178406.28 | a) | - | c) | - | a) | - | Scheduled for Maintenance Works 3rd Quarter
015 | [6 empty] | b) | CY 2017 | e) | Fabian | b) | - | e) | - | b) | 178406.28 | b) | - | d) | - | b) | -
[7 empty] | c) | Admin |  |  | c) | - | f) | - | c)
|  | Kapalong-Mabantao-Florida |  | Road Maintenance | 12.13 | Admin | a) | 20% DF | d) | 366296.37 | a) | - | d) | - | a) | 366296.37 | a) | - | c) | - | a) | - | Scheduled for Maintenance Works 1st Quarter
016 | [6 empty] | b) | CY 2017 | e) | Fabian | b) | - | e) | - | b) | 366296.37 | b) | - | d) | - | b) | -
[7 empty] | c) | Admin |  |  | c) | - | f) | - | c) | 25472.86
|  | Semong-Palma Gil |  | Road Maintenance | 2.73 | Admin | a) | 20% DF | d) | 67441.21 | a) | - | d) | - | a) | 67441.21 | a) | - | c) | - | a) | - | Scheduled for Maintenance Works 1st Quarter
018 | [6 empty] | b) | CY 2017 | e) | Fabian | b) | - | e) | - | b) | 67441.21 | b) | - | d) | - | b) | -
[7 empty] | c) | Admin |  |  | c) | - | f) | - | c)
|  | Semong-Palma Gil |  | Road Maintenance | 2.73 | MBC | a) | 20% DF | d) | 225186.11 | a) | - | d) | - | a) | 225186.11 | a) | - | c) | - | a) | - | Scheduled for Maintenance Works 1st Quarter
018 | [6 empty] | b) | CY 2017 | e) |  | b) | - | e) | - | b) | 225186.11 | b) | - | d) | - | b) | -
[7 empty] | c) | Admin |  |  | c) | - | f) | - | c)
|  | Sto. Niño - Palma Gil - Sitio Opao |  | Road Maintenance | 5.99 | Admin | a) | 20% DF | d) | 228791.62 | a) | - | d) | - | a) | 228791.62 | a) | - | c) | - | a) | - | Scheduled for Maintenance Works 4th Quarter
019 | [6 empty] | b) | CY 2017 | e) | Fabian | b) | - | e) | - | b) | 228791.62 | b) | - | d) | - | b) | -
[7 empty] | c) | Admin |  |  | c) | - | f) | - | c)
|  | Angelo - Dagohoy |  | Road Maintenance | 2.19 | Admin | a) | 20% DF | d) | 57272.67 | a) | - | d) | - | a) | 57272.67 | a) | - | c) | - | a) | - | Scheduled for Maintenance Works 1st Quarter
021 | [6 empty] | b) | CY 2017 | e) | Fabian | b) | - | e) | - | b) | 57272.67 | b) | - | d) | - | b) | -
[7 empty] | c) | Admin |  |  | c) | - | f) | - | c)
|  | Angelo - Dagohoy |  | Road Maintenance | 2.19 | MBC | a) | 20% DF | d) | 177811.01 | a) | - | d) | - | a) | 177811.01 | a) | - | c) | - | a) | - | Scheduled for Maintenance Works 1st Quarter
021 | [6 empty] | b) | CY 2017 | e) | - | b) | - | e) | - | b) | 177811.01 | b) | - | d) | - | b) | -
[7 empty] | c) | Admin |  |  | c) | - | f) | - | c)
|  | Daligdigon - Lumabag |  | Road Maintenance | 2.82 | Admin | a) | 20% DF | d) | 98096.66 | a) | - | d) | - | a) | 98096.66 | a) | - | c) | - | a) | - | Scheduled for Maintenance Works 4th Quarter
022 | [6 empty] | b) | CY 2017 | e) | Fabian | b) | - | e) | - | b) | 98096.66 | b) | - | d) | - | b) | -
[7 empty] | c) | Admin |  |  | c) | - | f) | - | c)
|  | Sto. Niño - Daligdigon - Paiton |  | Road Maintenance | 11.6 | Admin | a) | 20% DF | d) | 238708.84 | a) | - | d) | - | a) | 238708.84 | a) | - | c) | - | a) | - | Scheduled for Maintenance Works 1st Quarter
023 | [6 empty] | b) | CY 2017 | e) | Fabian | b) | - | e) | - | b) | 238708.84 | b) | - | d) | - | b) | -
[7 empty] | c) | Admin |  |  | c) | - | f) | - | c) | 16000
|  | Sto. Niño - Daligdigon - Paiton |  | Road Maintenance | 11.6 | MBC | a) | 20% DF | d) | 607476.38 | a) | - | d) | - | a) | 607476.38 | a) | - | c) | - | a) | - | Scheduled for Maintenance Works 1st Quarter
023 | [6 empty] | b) | CY 2017 | e) | - | b) | - | e) | - | b) | 607476.38 | b) | - | d) | - | b) | -
[7 empty] | c) | Admin |  |  | c) | - | f) | - | c)
|  | Jct. Paiton-Mibolo |  | Road Maintenance | 23.9 | Admin | a) | 20% DF | d) | 993683.52 | a) | - | d) | - | a) | 993683.52 | a) | - | c) | - | a) | - | Scheduled for Maintenance Works 1st Quarter
024 | [6 empty] | b) | CY 2017 | e) | Fabian | b) | - | e) | - | b) | 993683.52 | b) | - | d) | - | b) | -
[7 empty] | c) | Admin |  |  | c) | - | f) | - | c)
|  | Jct. Sampao-Bdry. Mamacao |  | Road Maintenance | 4.98 | Admin | a) | 20% DF | d) | 170722.35 | a) | - | d) | - | a) | 170722.35 | a) | - | c) | - | a) | - | Scheduled for Maintenance Works 4th Quarter
025 | [6 empty] | b) | CY 2017 | e) | Fabian | b) | - | e) | - | b) | 170722.35 | b) | - | d) | - | b) | -
[7 empty] | c) | Admin |  |  | c) | - | f) | - | c)
|  | Jct. Highway Luna-Mamacao-Narra |  | Road Maintenance | 9.17 | Admin | a) | 20% DF | d) | 375404.79 | a) | - | d) | - | a) | 375404.79 | a) | - | c) | - | a) | - | Scheduled for Maintenance Works 1st Quarter
026 | [6 empty] | b) | CY 2017 | e) | Fabian | b) | - | e) | - | b) | 375404.79 | b) | - | d) | - | b) | -
[7 empty] | c) | Admin |  |  | c) | - | f) | - | c) | 93086.16
|  | Jct. Gabuyan-Katipunan-Bucana |  | Road Maintenance | 5.89 | Admin | a) | 20% DF | d) | 154557.87 | a) | - | d) | - | a) | 154557.87 | a) | - | c) | - | a) | - | Scheduled for Maintenance Works 2nd Quarter
027 | [6 empty] | b) | CY 2017 | e) | Fabian | b) | - | e) | - | b) | 154557.87 | b) | - | d) | - | b) | -
[7 empty] | c) | Admin |  |  | c) | - | f) | - | c)
|  | Jct. Gabuyan-Katipunan-Bucana |  | Road Maintenance | 5.89 | MBC | a) | 20% DF | d) | 364396.38 | a) | - | d) | - | a) | 364396.38 | a) | - | c) | - | a) | - | Scheduled for Maintenance Works 2nd Quarter
027 | [6 empty] | b) | CY 2017 | e) | - | b) | - | e) | - | b) | 364396.38 | b) | - | d) | - | b) | -
[7 empty] | c) | Admin |  |  | c) | - | f) | - | c)
|  | Capungagan-Mabuhay-Pandulian |  | Road Maintenance | 5.57 | Admin | a) | 20% DF | d) | 134200.24 | a) | - | d) | - | a) | 134200.24 | a) | - | c) | - | a) | - | Scheduled for Maintenance Works 2nd Quarter
028 | [6 empty] | b) | CY 2017 | e) | Fabian | b) | - | e) | - | b) | 134200.24 | b) | - | d) | - | b) | -
[7 empty] | c) | Admin |  |  | c) | - | f) | - | c)
|  | Capungagan-Mabuhay-Pandulian |  | Road Maintenance | 5.57 | Admin | a) | 20% DF | d) | 347042.52 | a) | - | d) | - | a) | 347042.52 | a) | - | c) | - | a) | - | Scheduled for Maintenance Works 2nd Quarter
028 | [6 empty] | b) | CY 2017 | e) | - | b) | - | e) | - | b) | 347042.52 | b) | - | d) | - | b) | -
[7 empty] | c) | Admin |  |  | c) | - | f) | - | c)
|  | Florida - New Boholano |  | Road Maintenance | 2.54 | Admin | a) | 20% DF | d) | 105439.39 | a) | - | d) | - | a) | 105439.39 | a) | - | c) | - | a) | - | Scheduled for Maintenance Works 4th Quarter
030 | [6 empty] | b) | CY 2017 | e) | Fabian | b) | - | e) | - | b) | 105439.39 | b) | - | d) | - | b) | -
[7 empty] | c) | Admin |  |  | c) | - | f) | - | c)
|  | Jct. New Boholano - New Loon |  | Road Maintenance | 4.77 | Admin | a) | 20% DF | d) | 164183.27 | a) | - | d) | - | a) | 164183.27 | a) | - | c) | - | a) | - | Scheduled for Maintenance Works 1st Quarter
031 | [6 empty] | b) | CY 2017 | e) | Fabian | b) | - | e) | - | b) | 164183.27 | b) | - | d) | - | b) | -
[7 empty] | c) | Admin |  |  | c) | - | f) | - | c)
|  | Jct. New Boholano - New Loon |  | Road Maintenance | 4.77 | CBRMC | a) | 20% DF | d) | 82806.67 | a) | - | d) | - | a) | 82806.67 | a) | - | c) | - | a) | - | Scheduled for Maintenance Works 1st Quarter
031 | [6 empty] | b) | CY 2017 | e) | - | b) | - | e) | - | b) | 82806.67 | b) | - | d) | - | b) | -
[7 empty] | c) | Admin |  |  | c) | - | f) | - | c)
|  | Florida-Suaon-Jct. Gupitan |  | Road Maintenance | 15.57 | Admin | a) | 20% DF | d) | 605588.85 | a) | - | d) | - | a) | 605588.85 | a) | - | c) | - | a) | - | Scheduled for Maintenance Works 1st Quarter
032 | [6 empty] | b) | CY 2017 | e) | Fabian | b) | - | e) | - | b) | 605588.85 | b) | - | d) | - | b) | -
[7 empty] | c) | Admin |  |  | c) | - | f) | - | c) | 86928.88
|  | Florida-Suaon-Jct. Gupitan |  | Road Maintenance | 15.57 | CBRMC | a) | 20% DF | d) | 282388.58 | a) | - | d) | - | a) | 282388.58 | a) | - | c) | - | a) | - | Scheduled for Maintenance Works 1st Quarter
032 | [6 empty] | b) | CY 2017 | e) | - | b) | - | e) | - | b) | 282388.58 | b) | - | d) | - | b) | -
[7 empty] | c) | Admin |  |  | c) | - | f) | - | c)
|  | Km. 15, Kipalili-New Loon |  | Road Maintenance | 6.93 | Admin | a) | 20% DF | d) | 462549.87 | a) | - | d) | - | a) | 462549.87 | a) | - | c) | - | a) | - | Scheduled for Maintenance Works 2nd Quarter
034 | [6 empty] | b) | CY 2017 | e) | Fabian | b) | - | e) | - | b) | 462549.87 | b) | - | d) | - | b) | -
[7 empty] | c) | Admin |  |  | c) | - | f) | - | c)
|  | Km. 15, Kipalili-New Loon |  | Road Maintenance | 6.93 | CBRMC | a) | 20% DF | d) | 186843.57 | a) | - | d) | - | a) | 186843.57 | a) | - | c) | - | a) | - | Scheduled for Maintenance Works 2nd Quarter
034 | [6 empty] | b) | CY 2017 | e) |  | b) | - | e) | - | b) | 186843.57 | b) | - | d) | - | b) | -
[7 empty] | c) | Admin |  |  | c) | - | f) | - | c)
|  | Jct. Suaon-Libuton |  | Road Maintenance | 7.26 | Admin | a) | 20% DF | d) | 305446.16 | a) | - | d) | - | a) | 305446.16 | a) | - | c) | - | a) | - | Scheduled for Maintenance Works 2nd Quarter
035 | [6 empty] | b) | CY 2017 | e) |  | b) | - | e) | - | b) | 305446.16 | b) | - | d) | - | b) | -
[7 empty] | c) | Admin |  |  | c) | - | f) | - | c)
|  | Jct. Dacudao - Mabuhay |  | Road Maintenance | 4.43 | Admin | a) | 20% DF | d) | 211104.09 | a) | - | d) | - | a) | 211104.09 | a) | - | c) | - | a) | - | Scheduled for Maintenance Works 2nd Quarter
036 | [6 empty] | b) | CY 2017 | e) | Fabian | b) | - | e) | - | b) | 211104.09 | b) | - | d) | - | b) | -
[7 empty] | c) | Admin |  |  | c) | - | f) | - | c)
|  | Monte Dujali-Gupitan |  | Road Maintenance | 4.58 | Admin | a) | 20% DF | d) | 178293.62 | a) | - | d) | - | a) | 178293.62 | a) | - | c) | - | a) | - | Scheduled for Maintenance Works 2nd Quarter
037 | [6 empty] | b) | CY 2017 | e) | Fabian | b) | - | e) | - | b) | 178293.62 | b) | - | d) | - | b) | -
[7 empty] | c) | Admin |  |  | c) | - | f) | - | c)
|  | Jct. Patel-Langan |  | Road Maintenance | 1.62 | Admin | a) | 20% DF | d) | 349586.48 | a) | - | d) | - | a) | 349586.48 | a) | - | c) | - | a) | - | Scheduled for Maintenance Works 1st Quarter
038 | [6 empty] | b) | CY 2017 | e) | Fabian | b) | - | e) | - | b) | 349586.48 | b) | - | d) | - | b) | -
[7 empty] | c) | Admin |  |  | c) | - | f) | - | c)
|  | Datu Balong - Pinamuno |  | Road Maintenance | 2.74 | Admin | a) | 20% DF | d) | 120237.49 | a) | - | d) | - | a) | 120237.49 | a) | - | c) | - | a) | - | Scheduled for Maintenance Works 1st Quarter
040 | [6 empty] | b) | CY 2017 | e) | Fabian | b) | - | e) | - | b) | 120237.49 | b) | - | d) | - | b) | -
[7 empty] | c) | Admin |  |  | c) | - | f) | - | c)
|  | Sawata - Mamangan - Pinamuno |  | Road Maintenance | 14.48 | Admin | a) | 20% DF | d) | 858804.35 | a) | - | d) | - | a) | 858804.35 | a) | - | c) | - | a) | - | Scheduled for Maintenance Works 1st Quarter
041 | [6 empty] | b) | CY 2017 | e) | Fabian | b) | - | e) | - | b) | 858804.35 | b) | - | d) | - | b) | -
[7 empty] | c) | Admin |  |  | c) | - | f) | - | c) | 249180.26
|  | Jct. Sawata - Bdry. Binasbas |  | Road Maintenance | 0.46 | Admin | a) | 20% DF | d) | 36369.17 | a) | - | d) | - | a) | 36369.17 | a) | - | c) | - | a) | - | Scheduled for Maintenance Works 1st Quarter
043 | [6 empty] | b) | CY 2017 | e) | Fabian | b) | - | e) | - | b) | 36369.17 | b) | - | d) | - | b) | -
[7 empty] | c) | Admin |  |  | c) | - | f) | - | c)
|  | New Corella-Sto. Niño -Macgum |  | Road Maintenance | 17.11 | Admin | a) | 20% DF | d) | 443898.36 | a) | - | d) | - | a) | 443898.36 | a) | - | c) | - | a) | - | Scheduled for Maintenance Works 1st Quarter
044 | [6 empty] | b) | CY 2017 | e) | Ibañez | b) | - | e) | - | b) | 443898.36 | b) | - | d) | - | b) | -
[7 empty] | c) | Admin |  |  | c) | - | f) | - | c) | 106854.21
|  | Tagaytay-Buan |  | Road Maintenance | 4.92 | Admin | a) | 20% DF | d) | 178293.62 | a) | - | d) | - | a) | 178293.62 | a) | - | c) | - | a) | - | Scheduled for Maintenance Works 2nd Quarter
045 | [6 empty] | b) | CY 2017 | e) | Ibañez | b) | - | e) | - | b) | 178293.62 | b) | - | d) | - | b) | -
[7 empty] | c) | Admin |  |  | c) | - | f) | - | c)
|  | Sta. Fe-Mambing |  | Road Maintenance | 10.96 | Admin | a) | 20% DF | d) | 293551.84 | a) | - | d) | - | a) | 293551.84 | a) | - | c) | - | a) | - | Scheduled for Maintenance Works 1st Quarter
046 | [6 empty] | b) | CY 2017 | e) | Ibañez | b) | - | e) | - | b) | 293551.84 | b) | - | d) | - | b) | -
[7 empty] | c) | Admin |  |  | c) | - | f) | - | c) | 116458.03
|  | Sta. Fe-Mambing |  | Road Maintenance | 10.96 | CBRMC | a) | 20% DF | d) | 180473.9 | a) | - | d) | - | a) | 180473.9 | a) | - | c) | - | a) | - | Scheduled for Maintenance Works 1st Quarter
046 | [6 empty] | b) | CY 2017 | e) | - | b) | - | e) | - | b) | 180473.9 | b) | - | d) | - | b) | -
[7 empty] | c) | Admin |  |  | c) | - | f) | - | c)
|  | Limbaan-Sta. Fe-El Salvador |  | Road Maintenance | 18.82 | Admin | a) | 20% DF | d) | 766333.39 | a) | - | d) | - | a) | 766333.39 | a) | - | c) | - | a) | - | Scheduled for Maintenance Works 1st Quarter
047 | [6 empty] | b) | CY 2017 | e) | Ibañez | b) | - | e) | - | b) | 766333.39 | b) | - | d) | - | b) | -
[7 empty] | c) | Admin |  |  | c) | - | f) | - | c) | 195769.06
|  | Limbaan-Sta. Fe-El Salvador |  | Road Maintenance | 18.82 | CBRMC | a) | 20% DF | d) | 322729.8 | a) | - | d) | - | a) | 322729.8 | a) | - | c) | - | a) | - | Scheduled for Maintenance Works 1st Quarter
047 | [6 empty] | b) | CY 2017 | e) | Ibañez | b) | - | e) | - | b) | 322729.8 | b) | - | d) | - | b) | -
[7 empty] | c) | Admin |  |  | c) | - | f) | - | c)
|  | New Corella-Saug |  | Road Maintenance | 12.52 | Admin | a) | 20% DF | d) | 913072.13 | a) |  | d) | - | a) | 913072.13 | a) | - | c) | - | a) | - | Scheduled for Maintenance Works 1st Quarter
048 | [6 empty] | b) | CY 2017 | e) | Ibañez | b) |  | e) | - | b) | 913072.13 | b) | - | d) | - | b) | -
[7 empty] | c) | Admin |  |  | c) |  | f) | - | c) | 459260.95
|  | Limbaan-Sto. Niño |  | Road Maintenance | 3.19 | Admin | a) | 20% DF | d) | 131023.02 | a) | - | d) | - | a) | 131023.02 | a) | - | c) | - | a) | - | Scheduled for Maintenance Works 1st Quarter
049 | [6 empty] | b) | CY 2017 | e) | Ibañez | b) | - | e) | - | b) | 131023.02 | b) | - | d) | - | b) | -
[7 empty] | c) | Admin |  |  | c) | - | f) | - | c)
|  | Jct. Monte Calo-Upper Cabaywa-Canatan |  | Road Maintenance | 4.61 | Admin | a) | 20% DF | d) | 154276.07 | a) | - | d) | - | a) | 154276.07 | a) | - | c) | - | a) | - | Scheduled for Maintenance Works 3rd Quarter
050 | [6 empty] | b) | CY 2017 | e) | Ibañez | b) | - | e) | - | b) | 154276.07 | b) | - | d) | - | b) | -
[7 empty] | c) | Admin |  |  | c) | - | f) | - | c)
|  | Jct. Monte Calo-Upper Cabaywa-Canatan |  | Road Maintenance | 4.61 | MBC | a) | 20% DF | d) | 305199.98 | a) | - | d) | - | a) | 305199.98 | a) | - | c) | - | a) | - | Scheduled for Maintenance Works 3rd Quarter
050 | [6 empty] | b) | CY 2017 | e) | - | b) | - | e) | - | b) | 305199.98 | b) | - | d) | - | b) | -
[7 empty] | c) | Admin |  |  | c) | - | f) | - | c)
|  | Del Pilar - Jct. Silangan |  | Road Maintenance | 4.17 | Admin | a) | 20% DF | d) | 424967.69 | a) | - | d) | - | a) | 424967.69 | a) | - | c) | - | a) | - | Scheduled for Maintenance Works 1st Quarter
051 | [6 empty] | b) | CY 2017 | e) |  | b) | - | e) | - | b) | 424967.69 | b) | - | d) | - | b) | -
[7 empty] | c) | Admin |  |  | c) | - | f) | - | c) | 62862.72
|  | Del Pilar - Jct. Silangan |  | Road Maintenance | 4.17 | CBRMC | a) | 20% DF | d) | 91298.56 | a) | - | d) | - | a) | 91298.56 | a) | - | c) | - | a) | - | Scheduled for Maintenance Works 1st Quarter
051 | [6 empty] | b) | CY 2017 | e) |  | b) | - | e) | - | b) | 91298.56 | b) | - | d) | - | b) | -
[7 empty] | c) | Admin |  |  | c) | - | f) | - | c)
|  | New Corella - New Sambog - Silangan |  | Road Maintenance | 5.1 | Admin | a) | 20% DF | d) | 203877.25 | a) | 021/03/18 | d) | - | a) | 203877.25 | a) | 7.76% | c) | 7.76% | a) | - | On-going
052 | [6 empty] | b) | CY 2017 | e) |  | b) | 01/16/18 | e) | - | b) | 203877.25 | b) | - | d) | - | b) | -
[7 empty] | c) | Admin |  |  | c) | 12/31/18 | f) | - | c) | 61000
|  | Pob. New Corella - Prk. 10 Pob. |  | Road Maintenance | 1.3 | Admin | a) | 20% DF | d) | 65511.51 | a) | - | d) | - | a) | 65511.51 | a) | - | c) | - | a) | - | Scheduled for Maintenance Works 1st Quarter
053 | [6 empty] | b) | CY 2017 | e) | Ibañez | b) | - | e) | - | b) | 65511.51 | b) | - | d) | - | b) | -
[7 empty] | c) | Admin |  |  | c) | - | f) | - | c)
|  | Prk. 7 Pob. - Jct. New Sambog |  | Road Maintenance | 2.54 | Admin | a) | 20% DF | d) | 134465.84 | a) | - | d) | - | a) | 134465.84 | a) | - | c) | - | a) | - | Scheduled for Maintenance Works 1st Quarter
054 | [6 empty] | b) | CY 2017 | e) | Ibañez | b) | - | e) | - | b) | 134465.84 | b) | - | d) | - | b) | -
[7 empty] | c) | Admin |  |  | c) | - | f) | - | c)
|  | New Corella - Guadalupe - Del Monte |  | Road Maintenance | 14.05 | Contract/CBRMC | a) | 20% DF | d) | 1636803.07 | a) | - | d) | - | a) | 1636803.07 | a) | - | c) | - | a) | - | Scheduled for Maintenance Works 1st Quarter
055 | [6 empty] | b) | CY 2017 | e) | Ibañez | b) | - | e) | - | b) | 1636803.07 | b) | - | d) | - | b) | -
[7 empty] | c) | Admin |  |  | c) | - | f) | - | c) | 26755.63
|  | Sta. Fe - Del Monte |  | Road Maintenance | 3.34 | Admin | a) | 20% DF | d) | 138137.2 | a) | - | d) | - | a) | 138137.2 | a) | - | c) | - | a) | - | Scheduled for Maintenance Works 4th Quarter
056 | [6 empty] | b) | CY 2017 | e) | Ibañez | b) | - | e) | - | b) | 138137.2 | b) | - | d) | - | b) | -
[7 empty] | c) | Admin |  |  | c) | - | f) | - | c)
|  | Carcor - Patrocenio - Jct. Bayabas |  | Road Maintenance | 14.68 | Admin | a) | 20% DF | d) | 1410899.45 | a) | - | d) | - | a) | 1410899.45 | a) | - | c) | - | a) | - | Scheduled for Maintenance Works 1st Quarter
057 | [6 empty] | b) | CY 2017 | e) | Ibañez | b) | - | e) | - | b) | 1410899.45 | b) | - | d) | - | b) | -
[7 empty] | c) | Admin |  |  | c) | - | f) | - | c) | 204013.44
|  | Carcor - Patrocenio - Jct. Bayabas |  | Road Maintenance | 14.68 | CBRMC | a) | 20% DF | d) | 138009.46 | a) | - | d) | - | a) | 138009.46 | a) | - | c) | - | a) | - | Scheduled for Maintenance Works 1st Quarter
057 | [6 empty] | b) | CY 2017 | e) | Ibañez | b) | - | e) | - | b) | 138009.46 | b) | - | d) | - | b) | -
[7 empty] | c) | Admin |  |  | c) | - | f) | - | c)
|  | New Corella - New Bohol |  | Road Maintenance | 11.54 | Admin | a) | 20% DF | d) | 476178.5 | a) | - | d) | - | a) | 476178.5 | a) | - | c) | - | a) | - | Scheduled for Maintenance Works 4th Quarter
058 | [6 empty] | b) | CY 2017 | e) | Ibañez | b) | - | e) | - | b) | 476178.5 | b) | - | d) | - | b) | -
[7 empty] | c) | Admin |  |  | c) | - | f) | - | c)
|  | Jct. Carcor - Prk. 9 Bagsak |  | Road Maintenance | 2.5 | Admin | a) | 20% DF | d) | 112894.77 | a) | - | d) | - | a) | 112894.77 | a) | - | c) | - | a) | - | Scheduled for Maintenance Works 4th Quarter
059 | [6 empty] | b) | CY 2017 | e) | Ibañez | b) | - | e) | - | b) | 112894.77 | b) | - | d) | - | b) | -
[7 empty] | c) | Admin |  |  | c) | - | f) | - | c)
|  | Carcor - Jct. Kauswagan |  | Road Maintenance | 4.32 | Admin | a) | 20% DF | d) | 101965.77 | a) | - | d) | - | a) | 101965.77 | a) | - | c) | - | a) | - | Scheduled for Maintenance Works 1st Quarter
060 | [6 empty] | b) | CY 2017 | e) | Ibañez | b) | - | e) | - | b) | 101965.77 | b) | - | d) | - | b) | -
[7 empty] | c) | Admin |  |  | c) | - | f) | - | c)
|  | Del Pilar - Prk. 9 Bagsak - San Jose |  | Road Maintenance | 4.99 | Admin | a) | 20% DF | d) | 116486 | a) | - | d) | - | a) | 116486 | a) | - | c) | - | a) | - | Scheduled for Maintenance Works 1st Quarter
061 | [6 empty] | b) | CY 2017 | e) | Ibañez | b) | - | e) | - | b) | 116486 | b) | - | d) | - | b) | -
[7 empty] | c) | Admin |  |  | c) | - | f) | - | c)
|  | Del Pilar - Prk. 9 Bagsak - San Jose |  | Road Maintenance | 4.99 | MBC | a) | 20% DF | d) | 467583.73 | a) | - | d) | - | a) | 467583.73 | a) | - | c) | - | a) | - | Scheduled for Maintenance Works 1st Quarter
061 | [6 empty] | b) | CY 2017 | e) | - | b) | - | e) | - | b) | 467583.73 | b) | - | d) | - | b) | -
[7 empty] | c) | Admin |  |  | c) | - | f) | - | c)
|  | Del Pilar - El Unido |  | Road Maintenance | 1.32 | Admin | a) | 20% DF | d) | 74816.84 | a) | - | d) | - | a) | 74816.84 | a) | - | c) | - | a) | - | Scheduled for Maintenance Works 1st Quarter
062 | [6 empty] | b) | CY 2017 | e) | Ibañez | b) | - | e) | - | b) | 74816.84 | b) | - | d) | - | b) | -
[7 empty] | c) | Admin |  |  | c) | - | f) | - | c)
|  | Del Pilar - El Unido |  | Road Maintenance | 1.32 | MBC | a) | 20% DF | d) | 202586.04 | a) | - | d) | - | a) | 202586.04 | a) | - | c) | - | a) | - | Scheduled for Maintenance Works 1st Quarter
062 | [6 empty] | b) | CY 2017 | e) | - | b) | - | e) | - | b) | 202586.04 | b) | - | d) | - | b) | -
[7 empty] | c) | Admin |  |  | c) | - | f) | - | c)
|  | San Juan - New Talisay |  | Road Maintenance | 5.13 | Admin | a) | 20% DF | d) | 113189.45 | a) | - | d) | - | a) | 113189.45 | a) | - | c) | - | a) | - | Scheduled for Maintenance Works 3rd Quarter
063 | [6 empty] | b) | CY 2017 | e) | Ibañez | b) | - | e) | - | b) | 113189.45 | b) | - | d) | - | b) | -
[7 empty] | c) | Admin |  |  | c) | - | f) | - | c)
|  | San Juan - New Talisay |  | Road Maintenance | 5.13 | MBC | a) | 20% DF | d) | 480113.2 | a) | - | d) | - | a) | 480113.2 | a) | - | c) | - | a) | - | Scheduled for Maintenance Works 4th Quarter
063 | [6 empty] | b) | CY 2017 | e) | - | b) | - | e) | - | b) | 480113.2 | b) | - | d) | - | b) | -
[7 empty] | c) | Admin |  |  | c) | - | f) | - | c)
|  | San Juan - Kauswagan - New Cortez |  | Road Maintenance | 3.22 | Admin | a) | 20% DF | d) | 99136.64 | a) | - | d) | - | a) | 99136.64 | a) | - | c) | - | a) | - | Scheduled for Maintenance Works 1st Quarter
064 | [6 empty] | b) | CY 2017 | e) | Ibañez | b) | - | e) | - | b) | 99136.64 | b) | - | d) | - | b) | -
[7 empty] | c) | Admin |  |  | c) | - | f) | - | c)
|  | New Bohol - Jct. El Unido |  | Road Maintenance | 2.12 | Admin | a) | 20% DF | d) | 52809.06 | a) | - | d) | - | a) | 52809.06 | a) | - | c) | - | a) | - | Scheduled for Maintenance Works 1st Quarter
065 | [6 empty] | b) | CY 2017 | e) | Ibañez | b) | - | e) | - | b) | 52809.06 | b) | - | d) | - | b) | -
[7 empty] | c) | Admin |  |  | c) | - | f) | - | c)
|  | New Bohol - Jct. El Unido |  | Road Maintenance | 2.12 | MBC | a) | 20% DF | d) | 274055.8 | a) | - | d) | - | a) | 274055.8 | a) | - | c) | - | a) | - | Scheduled for Maintenance Works 1st Quarter
065 | [6 empty] | b) | CY 2017 | e) | Ibañez | b) | - | e) | - | b) | 274055.8 | b) | - | d) | - | b) | -
[7 empty] | c) | Admin |  |  | c) | - | f) | - | c)
|  | New Corella - El Unido - Jct. Mesaoy |  | Road Maintenance | 8.63 | Admin | a) | 20% DF | d) | 193220.93 | a) | - | d) | - | a) | 193220.93 | a) | - | c) | - | a) | - | Scheduled for Maintenance Works 1st Quarter
066 | [6 empty] | b) | CY 2017 | e) | Ibañez | b) | - | e) | - | b) | 193220.93 | b) | - | d) | - | b) | -
[7 empty] | c) | Admin |  |  | c) | - | f) | - | c) | 54000
|  | New Corella - El Unido - Jct. Mesaoy |  | Road Maintenance | 8.63 | MBC | a) | 20% DF | d) | 852165.1 | a) | - | d) | - | a) | 852165.1 | a) | - | c) | - | a) | - | Scheduled for Maintenance Works 1st Quarter
066 | [6 empty] | b) | CY 2017 | e) | - | b) | - | e) | - | b) | 852165.1 | b) | - | d) | - | b) | -
[7 empty] | c) | Admin |  |  | c) | - | f) | - | c)
|  | Mesaoy - Dasing |  | Road Maintenance | 1.39 | Admin | a) | 20% DF | d) | 87423.79 | a) | - | d) | - | a) | 87423.79 | a) | - | c) | - | a) | - | Scheduled for Maintenance Works 1st Quarter
067 | [6 empty] | b) | CY 2017 | e) | Ibañez | b) | - | e) | - | b) | 87423.79 | b) | - | d) | - | b) | -
[7 empty] | c) | Admin |  |  | c) | - | f) | - | c)
|  | Jct. San Juan - Jct. Mesaoy |  | Road Maintenance | 1.82 | Admin | a) | 20% DF | d) | 56581.99 | a) | - | d) | - | a) | 56581.99 | a) | - | c) | - | a) | - | Scheduled for Maintenance Works 1st Quarter
068 | [6 empty] | b) | CY 2017 | e) | Ibañez | b) | - | e) | - | b) | 56581.99 | b) | - | d) | - | b) | -
[7 empty] | c) | Admin |  |  | c) | - | f) | - | c)
|  | Jct. San Juan - Jct. Mesaoy |  | Road Maintenance | 1.82 | MBC | a) | 20% DF | d) | 428731.55 | a) | - | d) | - | a) | 428731.55 | a) | - | c) | - | a) | - | Scheduled for Maintenance Works 1st Quarter
068 | [6 empty] | b) | CY 2017 | e) | - | b) | - | e) | - | b) | 428731.55 | b) | - | d) | - | b) | -
[7 empty] | c) | Admin |  |  | c) | - | f) | - | c)
|  | Mesaoy - Jct. Mahayahay |  | Road Maintenance | 4.6 | Admin | a) | 20% DF | d) | 298640.54 | a) | - | d) | - | a) | 298640.54 | a) | - | c) | - | a) | - | Scheduled for Maintenance Works 1st Quarter
069 | [6 empty] | b) | CY 2017 | e) | Ibañez | b) | - | e) | - | b) | 298640.54 | b) | - | d) | - | b) | -
[7 empty] | c) | Admin |  |  | c) | - | f) | - | c) | 14106.15
|  | Mesaoy - New Bohol |  | Road Maintenance | 5.36 | Admin | a) | 20% DF | d) | 346368.67 | a) | - | d) | - | a) | 346368.67 | a) | - | c) | - | a) | - | Scheduled for Maintenance Works 1st Quarter
070 | [6 empty] | b) | CY 2017 | e) | Ibañez | b) | - | e) | - | b) | 346368.67 | b) | - | d) | - | b) | -
[7 empty] | c) | Admin |  |  | c) | - | f) | - | c) | 16000
|  | Bdry. Tagum - Baca - New Corella |  | Road Maintenance | 13.01 | Admin | a) | 20% DF | d) | 277079.01 | a) | - | d) | - | a) | 277079.01 | a) | - | c) | - | a) | - | Scheduled for Maintenance Works 1st Quarter
071 | [6 empty] | b) | CY 2017 | e) | Ibañez | b) | - | e) | - | b) | 277079.01 | b) | - | d) | - | b) | -
[7 empty] | c) | Admin |  |  | c) | - | f) | - | c)
|  | Bdry. Tagum - Baca - New Corella |  | Road Maintenance | 13.01 | CBRMC | a) | 20% DF | d) | 138009.46 | a) | - | d) | - | a) | 138009.46 | a) | - | c) | - | a) | - | Scheduled for Maintenance Works 1st Quarter
071 | [6 empty] | b) | CY 2017 | e) | Ibañez | b) | - | e) | - | b) | 138009.46 | b) | - | d) | - | b) | -
[7 empty] | c) | Admin |  |  | c) | - | f) | - | c)
|  | Prk. Maunlom-Prk. 6 Maunlom |  | Road Maintenance | 3.56 | Admin | a) | 20% DF | d) | 142984.25 | a) | - | d) | - | a) | 142984.25 | a) | - | c) | - | a) | - | Scheduled for Maintenance Works 1st Quarter
147 | [6 empty] | b) | CY 2017 | e) | Ibañez | b) | - | e) | - | b) | 142984.25 | b) | - | d) | - | b) | -
[7 empty] | c) | Admin |  |  | c) | - | f) | - | c)
|  | 2. Repair & Maint. Of Various Local Roads |  | Road | - | Admin | a) | 20% DF | d) | 5000000 | [12 empty] | See projects listed below
|  | and Drainages |  |  |  |  | b) | CY 2018 | e) | Paraguya
[7 empty] | c) | Admin
|  | 3. Various of Water System Project (Provincewide) |  | Water | - | Admin | a) | 20% DF | d) | 10000000 | [12 empty] | For identification
|  |  |  | System |  |  | b) | CY 2018 | e) | Foronda/Misa
[7 empty] | c) | Admin
|  | 4. Counterpart to Special Projects (Provincewide) |  | Road | - | Admin | a) | 20% DF | d) | 67415000 | [12 empty] | For identification
[7 empty] | b) | CY 2018 | e) | Foronda
[7 empty] | c) | Admin
|  | 5. Const./Rehab./Comp. of Various Gov't. Bldgs. |  | Bldgs. | - | Admin | a) | 20% DF | d) | 13523124 | [12 empty] | See projects listed below
|  | Struct., Fac. (Provincewide) |  |  |  |  | b) | CY 2018 | e) | Foronda
[7 empty] | c) | Admin
|  | 6. Rural Electrification (Provincewide) |  | Electrification |  | Admin | a) | 20% DF | d) | 5000000 | [12 empty] | For identification
[7 empty] | b) | CY 2018 | e) | Foronda/Misa
[7 empty] | c) | Admin
| B. | 5% Calamity Fund CY 2018
1. Prevention and Mitigation
|  | 1.1 Desiltation/Excavation of rivers and creeks |  | rivers |  | Admin | a) | 20% DF | d) | 3000000 | [12 empty] | For identification
[7 empty] | b) | CY 2018 | e) | -
[7 empty] | c) | Admin
|  | 1.2 Revitment of Dike and Slope Protection |  | Dike |  | Admin | a) | 20% DF | d) | 3000000 | [12 empty] | For identification
[7 empty] | b) | CY 2018 | e) | -
[7 empty] | c) | Admin
|  | 1.2 Improvement of roads and canal |  | roads/canals |  | Admin | a) | 20% DF | d) | 3000000 | [12 empty] | For identification
[7 empty] | b) | CY 2018 | e) | -
[7 empty] | c) | Admin
|  | 1.4 Improvement of bridges and cross drainage |  | bridges/drainage |  | Admin | a) | 20% DF | d) | 3000000 | [12 empty] | For identification
[7 empty] | b) | CY 2018 | e) | -
[7 empty] | c) | Admin
|  | 2. Rehabilitation and Recovery |  | roads
[6 empty] | Admin | a) | 20% DF | d) | 2026000 | [12 empty] | For identification
[7 empty] | b) | CY 2018 | e) | -
[7 empty] | c) | Admin

## Sheet1 (hidden)
GF- GENERAL FUND |  |  | TF - TRUST FUND (NATIONAL FUNDED PROJECT)
20% DF - 20% DEV'T. FUND |  |  | a) SLRF - Special Local Road Fund
5% CF - 5% CALAMITY FUND |  |  | b) KALSADA - Konkreto at Ayos na Lansangan Tungo sa Pangkalahatang Kaunlaran
CO - CAPITAL OUTLAY |  |  | c) PRDP - Philippine Rural Development Projects
CONG. FUND - CONGRESSIONAL FUND |  |  | d) SELAP - Support to Emergency and Livelihood Assistance Project
NCF - NATIONAL CALAMITY FUND |  |  | e) PAMANA - Payapa at Masaganang Pamayanan
SEF - SPECIAL EDUCATIONAL UFND |  |  | f) CBRMC - Community Based Road Maintenance Contracting
g) MBC - Maintenance by Contract
h) PCF-Performance Challenge Fund-DILG
j) FMRDP - Farm to Market Road
j.) CMGP - Conditional Grant to Provinces
Prepared by: | Checked by: | Reviewed by: | Noted by: | Recommending Approval:
RETCHIE A. DE LOS REYES | MARILOU A. FORONDA | EDWIN S. MISA | JIVELLYN B. CO | RAUL G. MABANGLO
Engineer I | Engineer IV-Area Engineer | Engineer IV-PDP/SIM | Asst. PG-Department Head | PG-Department Head
| 1st Engineering District | Planning Division Programming
Survey Investigation and Monitoring

## Sheet2 (hidden)
PROJECT NAME: | CONTRACTOR: | STATUS:
SB#5 CY 2015
1.) Upgrading of of DNSTC (Commercial Building) | YBC | For Implementation
Sporst Complex Center, Mankilam
1. PAMANA-DILG
1.1 Road Opening Kamansa-Sitio Bankawan- | DAVAO ROCK | 51.75%
Binancian to FMR, Asuncion
1.2 Road Opening of Brgy. Cabidianan-Mambing, | DAVAO ROCK | 91.210%
New Corella, DDN
1.3 Construction of Biga Bridges, Kapalong | DAVAO ROCK | 5.08%
1.4 Road Rehabilitation/Improvement of Prk. 3, | PUREGOLD | 22.36%
Palma Gil-Prk.2 (side 2), Sto. Niño-Mahayahay-Tugas-
Nanaga Road, with 1 -unit, 40 ln.m PSCG Bridge,
Kapalong
2.1 Road Rehabilitation San Jose-Sitio | HEXAMINDZ | 48.94%
Mahayahay, Brgy. Magwawa, Sto. Tomas
2.2 Construction of Women's Peace Center/ | HEXAMINDZ | 90.00%
Multi-Purpose Building, Datu Abdul, Panabo
City
2. PAMANA-DA
2.1 Conc./Impv't. of Linayapan-Malapanit | AYU | 90.00%
Dangulog FMR Ph.2
(Provincial Counterpart: 1.5M)
1.) Concreting of Datu Abdul Dadia FMR | MASULOT | 100%
(Revised) Panabo City, DDN
3. PRDP
3.1 Rehab. New Visayas-Binancian | DAVAO ROCK | 56.09%
Asuncion. Davao del Norte
(Provincial Counterpart: 1.205830M)
3.2 Rehab. Of Datu-Balong Prk. Mamalian | RELY CONST. | 28.79%
San Isidro, Davao del Norte
(Provincial Counterpart: 1.514040M)
3.3 Rehab. Of Sto. Niño-Igangon FMR | RELY CONST. | 4.658%
San Isidro, Davao del Norte
3.4 Rehab. Of Capungagan-Boundary San | Monolitic Const. | 0.916%
Miguel FMR, Kapalong, Davao del Norte | Products JV
w/ R.R. Reismundo
3.5 Rehab. Of Pob.-Limbaan-Suawon-Macgum | DAVAO ROCK | 1.956%
FMR w/ Bridge, New Corella, Davao del Norte
1. Rehab. of Little Panay-Katipunan-Kasilak | RELY CONST. | 86.728%
FMR, Panabo City, DDN
4. KALSADA
4.1 Improvement of Km. 9 Sagayen-Sawata Provincial | ARN BUILDERS | 1.00%
San Isidro, Davao del Norte
(Part of 60.329230.72M) (Contract Cost: P 43.597322.62M)
(SB # 1 CY 2016 P 12.270446M)
FMRDP
1. Conc. Of Magupising-Cabay-angan | HEXAMINDZ | 14.00%
Dujali FMR, B.E. Dujali
(Provincial Counterpart: 2.0M)

## Sheet4 (hidden)
ON-GOING PROJECTS WITHIN 1ST AND 2ND ENGINEERING DISTRICT
# | PROJECT NAME | SOURCE OF FUND | PROJECT COST | Percentage | IMPLEMENTOR:
1 | Rehab./Impv't. of Jct. Paiton-Mibolo Prov'l. Road | 5% CF CY 2014 | 5200000 | 94.22% | By administration
2 | Completion of PDRRMD Training Center, Gov't. Center, Mankilam, Tagum City | 5% CF CY 2014 | 3000000 | 73.78% | By administration
3 | Desiltation of Ilog River Ph.III, (Brgy. New Santiago to Brgy. New Loon) | 5% CF CY 2016 | 885000 | 93.84% | By administration
4 | Expansion of PVO Building (Left Weng), Mankilam, Tagum City | 20% DF CY 2016 | 2000000 | 29.34% | By administration
5 | Expansion of Residential Facilities for Minors, (Ph.I), New Corella | 20% DF CY 2016 | 1500000 | 8.10% | By administration
6 | Const. Of 1 CL Bldg. at Pamacaun ES, Asuncion, Davao del Norte | SEF CY 2016 | 960000 | 32.09% | By administration
7 | Construction of School Fence, Brgy. Del Pilar, New Corella | SEF CY 2016 | 716000 | 28.12% | By administration
8 | Compl. Of Perimeter Fence w/ Gate Between Carmen NHS/ES, Carmen | SEF CY 2016 | 184000 | 11.35% | By administration
9 | Const. of Hospital Waste Vault, SDH, Peñaplata, IGCS | MOOE CY 2016 | 150000 | 87.43% | By administration
10 | Repair & Maint. Building & Other Structure (Adoration Chapel) | SB # 1 CY 2016 | 467000 | 31.41% | By administration
11 | Expansion of Civil Service Commission Field Office, Bldg. (Ph.2), Gov't. Center, Mankilam, Tagum City | Civil Service | 2000000 | 43.16% | By administration
12 | Road Opening Kamansa-Sitio Bankawan-Binancian to FMR, Asuncion | PAMANA-DILG CY 2014 | 20000000 | 73.37% | By Contract (Dvo. Rock)
13 | Road Opening of Brgy. Mambing-Cabidianan, New Corella, DDN | PAMANA-DILG CY 2014 | 10000000 | 95.76% | By Contract (Dvo. Rock)
14 | Road Rehabilitation/Improvement of Prk. 3, Palma Gil-Prk.2 (side 2), | PAMANA-DILG CY 2014 | 50500288.95 | 31.11% | By Contract (Pure Gold)
Sto. Niño-Mahayahay-Tugas- Nanaga Road, with 1 -unit, 40 ln.m PSCG Bridge,Kapalong
15 | Road Rehabilitation San Jose-Sitio Mahayahay, Brgy. Magwawa, Sto. Tomas | PAMANA-DILG CY 2014 | 15000000 | 62.31% | By Contract (Hexamindz)
16 | Rehab. New Visayas-Binancian, Asuncion. Davao del Norte | PRDP CY 2014 | 78855000 | 56.09% | By Contract (Dvo. Rock)
17 | Rehab. Of Datu-Balong Prk. Mamalian, San Isidro, Davao del Norte | PRDP CY 2014 | 37125400 | 45.36% | By Contract (Rely Const.)
18 | Rehab. Of Sto. Niño-Igangon FMR, San Isidro, Davao del Norte | PRDP CY 2015 | 81816698.08 | 11.304% | By Contract (Monolitics & Const.
Products JV w/ R.R. Seismundo)
19 | Rehab. Of Pob.-Limbaan-Suawon-Macgum FMR w/ Bridge, New Corella, Davao del Norte | PRDP CY 2015 | 190253491.98 | 4.310% | By Contract (Dvo. Rock & WEE ENG)
20 | Rehab. Of Capungagan-Boundary San Miguel FMR, Kapalong, Davao del Norte | PRDP CY 2015 | 102311209.68 | 02.67% | By Contract (VIC LAO.)
21 | Rehab. of Little Panay-Katipunan-Kasilak FMR, Panabo City, DDN | PRDP CY 2015 | 56934000 | 88.89% | By Contract (Rely Const.)
22 | Improvement of Km. 9 Sagayen-Sawata Provincial, San Isidro, Davao del Norte | KALSADA CY 2015 | 60329230.72 | 4.668% | By Contract (ARN Builders)
23 | Conc. Of Magupising-Cabay-angan Dujali FMR, B.E. Dujali | FMRDP CY 2013 | 21400000 | 5% | By Contract (Hexamindz)
24 | Rehab. Of Anibongan-Kinamayan FMR, Carmen, DDN | SLRF CY 2015 | 17,209,86.00 | 20.18% | By Administration
STIMULUS PROJECTS:
25 | Completion of Covered Court and Stage, Brgy. Canatan, Asuncion | SB # 5 CY 2015 | 500000 | 90.05% | By administration
26 | Compl.of Covered Court (Bleacher), Brgy. Magugpo Poblacion, Tagum City | SB # 5 CY 2015 | 500000 | 21.37% | By administration
27 | Improvement of Public Cemetery, Brgy. Del Monte, new Corella | SB # 5 CY 2015 | 500000 | 94.05% | By administration
28 | Renov./Impvt.of Barangay Hall Brgy. Magupising, B.E. Dujali | SB # 5 CY 2015 | 500000 | 95.00% | By administration
29 | Completion of Covered Court, Brgy. New Camiling, Carmen | SB # 5 CY 2015 | 500000 | 65.00% | By administration
30 | Renovation/Impvt.of Barangay Hall, Brgy. Sto. Nino, Carmen | SB # 5 CY 2015 | 500000 | 60.00% | By administration
31 | Impv't. of Multi-Purpose Building, Brgy. La Paz, Carmen | SB # 5 CY 2015 | 500000 | 50.00% | By administration
32 | Construction of Market Stall, Brgy. Consolacion, Panabo City | SB # 5 CY 2015 | 500000 | 65.00% | By administration
# | PROJECT NAME | SOURCE OF FUND | PROJECT COST | Percentage | IMPLEMENTED:
33 | Fencing of Barangay Facility, Brgy. Waterfall, Panabo City | SB # 5 CY 2015 | 500000 | 97.00% | By administration
34 | Rehab.of Barangay Hall, Brgy. Cagangohan, Panabo City | SB # 5 CY 2015 | 500000 | 45.00% | By administration
35 | Const.of Senior Citizen Building, Brgy. San Miguel, Sto. Tomas | SB # 5 CY 2015 | 500000 | 60.00% | By administration
36 | Completion of Covered Court (Canopy), Brgy. Alejal, Carmen | SB # 5 CY 2015 | 500000 | 90.00% | By administration
37 | Const. of Drainage System Canal Lining, Brgy. New Pandan, Panabo City | SB # 5 CY 2015 | 500000 | 35.00% | By administration
38 | Covered Court Collapsible, Brgy. Kauswagan, Panabo City | SB # 5 CY 2015 | 500000 | 40.00% | By administration
39 | Potable Water System, Brgy. Tibulao, Carmen | SB # 5 CY 2015 | 500000 | 90.00% | By administration
40 | Compl. of Water System (Level III) at Prk. 5 Brgy. Manay, Panabo City | SB # 5 CY 2015 | 500000 | 25.00% | By administration
41 | Imprvt. of Water System, Brgy. Sindaton, Panabo City | SB # 5 CY 2015 | 500000 | 25.00% | By administration
42 | Impvt. of Water System, Brgy. New Malitbog, Panabo City | SB # 5 CY 2015 | 500000 | 98.00% | By administration
43 | Potable Water System, Brgy. San Roque, Panabo City | SB # 5 CY 2015 | 500000 | 40% | By administration
MAINTENANCE BY CONTRACT:
Maintenance by Contract: Package 1
44 | Km. 9, Sagayen-Sawata | 20% DF CY 2016 | 1110279.84 | 30.00% | By Contract (MAG CORP.)
Km. 15, Kipalili-New Loon
Maintenance by Contract: Package 2
45 | San Vicente-Butay | 20% DF CY 2016 | 2087387.43 | 31.00% | By Contract (PUREGOLD CORP.)
Jct. Highway Magatos - New Bantayan
Magatos-Bdry Pagsabangan
Ilog-New Bantayan
Jct. Highway Canatan-Jct. Highway Magatos
Maintenance by Contract: Package 4
46 | Kapalong-Mabantao-Florida | 20% DF CY 2016 | 1428433.93 | 35% | By Contract (SBB Const. & Supply)
Jct. Highway-Doña Andrea-Capungagan
Capungagan-Mabuhay-Pandulian
Maintenance by Contract: Package 5
47 | Jct. Highway Gabuyan-Semong-Dagohoy | 20% DF CY 2016 | 1231547.94 | 30% | By Contract (SBB Const. & Supply)
Jct. Gabuyan-Katipunan-Bucana
Daligdigon - Dagohoy
# | PROJECT NAME | SOURCE OF FUND | PROJECT COST | Percentage | IMPLEMENTED:
CBRMC (COMMUNITY BASED ROAD MAINTENANCE CONTRACTING)
48 | Sawata-Libuton-Monte Dujali-Patel | 20% DF CY 2016 | 1117826.2 | 68.64% | By Contract (ASSOCIATION OF ALTERNATIVE
LIVELIHOOD OF LIBUTON, INC.)
49 | Cebulano-Mangalcal Prov'l. Road, Carmen, DDN | 20% DF CY 2016 | 204071.52 | 4.8% | By Contract (MANGALCAL WOMEN'S
HOMEBASED WORKER'S ASSOCIATION)
49 | Tuganay-Taba Prov'l. Road, Carmen, DDN | 20% DF CY 2016 | 191,399.73 | 44.19% | By Contract (TABA COCONUT FARMER'S)
49 | Jct. Highway-Tuganay-Taba Prov'l. Road | 20% DF CY 2016 | 154170.77 | 43.28% | By Contract (EZRA CHRISTIAN
MINISTRY FOR PEACE)
50 | Jct.Highway-Guadalupe-Bdry.Tagum | 20% DF CY 2016 | 241141.18 | 43.14% | By Contract (LAMPIA PAG-ASA
IRRIGATOR'S ASSOCIATION)
51 | Prk.5-Prk.1 Pawas, Dujali Prov'l. Road | 20% DF CY 2016 | 148282.64 | 44.04% | By Contract (MANCIIA)
52 | Prk.Narafil-Brgy. Site Magupising | 20% DF CY 2016 | 94567.08 | 44.93% | By Contract (ESTE-MAGUPISING
IRRIGATORS ASSOCIATION)
53 | Dujali-Pawas-San Vicente Prov'l. Road | 20% DF CY 2016 | 243949.6 | 44.76% | By Contract (MANCIIA)
54 | Jct.Salvacion-San Vicente-Cabay-angan | 20% DF CY 2016 | 160213.45 | 22.19% | By Contract (BALISONG SAN
VICENTE IRRIGATORS ASSOCIATION)
55 | Prk.Magsaysay-Lunga-og-Dalisay | 20% DF CY 2016 | 171933.07 | 42.40% | By Contract (Lunga-og Tribal Assoc.)
56 | Prk.Apitong-Upper Balisong-Dalisay | 20% DF CY 2016 | 264522.58 | 42.39% | By Contract (Lunga-og Tribal Assoc.)
57 | Sitio Paradise-Magkakaisa-Esperanza | 20% DF CY 2016 | 96128.07 | 43.14% | By Contract (Esperanza Lumad Assoc.)
58 | Los Amigos 1-Esperanza-Los Amigos 2 | 20% DF CY 2016 | 208618.27 | 43.62% | By Contract (Esperanza Lumad Assoc.)
59 | Fd.Rd.3-San Jose Prov'l. Road | 20% DF CY 2016 | 164410.98 | 22..42% | By Contract (SAN JOSE UPLAND
FARMER'S ASSOCIATION)
60 | Menzi-Balagunan-Tulalian Prov'l. Road | 20% DF CY 2016 | 409055.47 | 42.22% | By Contract (BRWSA, Inc.)

## Sheet5
GF- GENERAL FUND |  |  | TF - TRUST FUND (NATIONAL FUNDED PROJECT)
20% DF - 20% DEVELOPMENT FUND |  |  | a) SLRF - Special Local Road Fund
5% CF - 5% CALAMITY FUND |  |  | b) KALSADA - Konkreto at Ayos na Lansangan Tungo sa Pangkalahatang Kaunlaran
CO - CAPITAL OUTLAY |  |  | c) PRDP - Philippine Rural Development Projects
SEF - SPECIAL EDUCATIONAL UFND |  |  | d) SELAP - Support to Emergency and Livelihood Assistance Project
e) PAMANA - Payapa at Masaganang Pamayanan
f) CBRMC - Community Based Road Maintenance Contracting
g) MBC - Maintenance by Contract
h) PCF-Performance Challenge Fund-DILG
i) FMRDP - Farm to Market Road
j.) CMGP - Conditional Grant to Provinces
k.) OPAPP - Office of the President Adviser on the Peace Process
l.) LGSF-AM - Local Government Support Fund Assistance to Municipalities
Prepared by: | Checked by: |  |  | Noted by: | Recommending Approval:
RETCHIE A. DE LOS REYES, CE | ELISA A. BARCENA, CE | TESSIE A. ABABON, CE |  | JIVELLYN B. CO, CE | GLENN A. OLANDRIA, CE
Engineer II | Engineer IV- Engineering Dist 1 | Engineer IV- Engineering Dist 2 |  | Asst. Provincial Engineer | Provincial Engineer
| Area Engineer | Area Engineer
| EDWIN S. MISA, CE |  |  | MARILOU A. FORONDA, CE
| Engineer IV- PDPM Division Head |  |  | Engineer IV- QC Division Head