## SAMPLE-2 (4) (hidden)
[12 empty] | 532.04 |  |  |  | 399939250.3384 |  |  |  | 798233458.6875 |  |  |  | 224
[8 empty] | SECTOR: | ECONOMIC (INFRASTRUCTURE DEV'T. PROGRAM)
[8 empty] | OFFICE/AGENCY: | PROVINCIAL ENGINEER'S OFFICE
[8 empty] | AREA: | 2ND ENGINEERING DISTRICT - COMPLETED, ON-GOING AND FOR IMPLEMENTATION PROJECTS
#VALUE!
#VALUE!
MUNICIPALITY | BARANGAY | AREA | COMPLETED/ ON-GOING/ FOR IMPLEMENTATION/ SUSPENDED | DATE STARTED | DATE COMPLETED | APPRO- PRIATION | NOMEN- CLATURE | NAME OF PROJECT |  | SOURCE OF FUND | TYPE OF PROJECT | PHYSICAL TARGET (DESCRIPTION) |  | MODE OF IMPLEMENTATION | PROJECT DATA |  |  |  | FINANCIAL |  | PHYSICAL ACCOMPLISHMENT |  | EMPLOYMENT GENERATED |  | REMARKS
San Isidro | Sagayen | 1st Eng'g. Dist. | Completed | 2018-10-01 | 2020-04-02 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CMGP | Road upgrading Km. 9 Sagayen-Sawata (Sagayen-Jct. San Miguel Section) |  | CMGP CY 2017 | Road Concreting | 10.2 | km | Contract | Project Cost: | 139761975.14 | Target Completion Date: | 2019-08-22 23:46 | Program: | 139761975.14 | Planned: | 100% | No. of Persons: | 28 | Completed as per physical accomplishment. Financial documents still on process.
San Isidro | Sagayen | 1st Eng'g. Dist. | Completed | 2018-10-01 | 2020-04-02 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CMGP | [7 empty] | Project Engineer: | Avila | Revised Completion Date: | 2019-08-22 23:46 | Allotment: | 139761975.14 | Revised: |  | No. of Man-days: | 11170
San Isidro | Sagayen | 1st Eng'g. Dist. | Completed | 2018-10-01 | 2020-04-02 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CMGP | [7 empty] | Implementor: | Legacy Const. Corp. | No. of days suspended: | 209 | Disbursement: | 63100753.7 | Actual: | 100%
San Isidro | Sagayen | 1st Eng'g. Dist. | Completed | 2018-10-01 | 2020-04-02 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CMGP | [7 empty] | Duration: | 326 | No. of days extended: |  |  |  | Slippage: | 0%
San Isidro | Sagayen | 1st Eng'g. Dist. | Completed | 2018-10-01 | 2020-04-02 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CMGP | [7 empty] | Date Allotment Released: | CY 2017 | Date completed: | 2020-04-02
San Isidro | Sagayen | 1st Eng'g. Dist. | Completed | 2018-10-01 | 2020-04-02 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CMGP | [7 empty] | Date Started: | 2018-10-01
San Isidro | Sto. Niño | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-05-27 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | Rehab. Of Multi-Purpose Hall , Sto. Niño, San Isidro |  | 20% DF CY 2019 (STIMULUS) | Building | 182 | sq.m | Admin | Project Cost: | 500000 | Target Completion Date: | 2020-02-19 23:46 | Program: | 500000 | Planned: | 100% | No. of Persons: | 6 | Completed as per physical accomplishment. Financial documents still on process
San Isidro | Sto. Niño | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-05-27 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Project Engineer: | Aclaracion | Revised Completion Date: | 2020-02-19 23:46 | Allotment: | 500000 | Revised: |  | No. of Man-days: | 132
San Isidro | Sto. Niño | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-05-27 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Implementor: | PEO | No. of days suspended: | 28 | Disbursement: | 500000 | Actual: | 100%
San Isidro | Sto. Niño | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-05-27 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Duration: | 45 | No. of days extended: |  |  |  | Slippage: | 0%
San Isidro | Sto. Niño | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-05-27 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Allotment Released: | 2019-02-20 | Date completed: | 2020-05-27
San Isidro | Sto. Niño | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-05-27 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Started: | 2020-01-06
Tagum City | San Isidro | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-06-05 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | Const. of Women Livelihood Center, San Isidro, Tagum City |  | 20% DF CY 2019 (STIMULUS) | Building | 36.5 | sq.m | Admin | Project Cost: | 500000 | Target Completion Date: | 2020-03-21 23:46 | Program: | 500000 | Planned: | 100% | No. of Persons: | 10 | Completed as per physical accomplishment. Financial documents still on process
Tagum City | San Isidro | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-06-05 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Project Engineer: | Juan | Revised Completion Date: | 2020-06-05 23:46 | Allotment: | 500000 | Revised: | 100% | No. of Man-days: | 150
Tagum City | San Isidro | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-06-05 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Implementor: | PEO | No. of days suspended: | 28 | Disbursement: |  | Actual: | 100%
Tagum City | San Isidro | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-06-05 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Duration: | 80 | No. of days extended: | 48 |  |  | Slippage: | 0%
Tagum City | San Isidro | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-06-05 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Allotment Released: | 2019-05-29 | Date completed: | 2020-06-05
Tagum City | San Isidro | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-06-05 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Started: | 2020-01-02
New Corella | Saug | 1st Eng'g. Dist. | Completed | 2019-03-26 | 2020-06-30 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES | New Corella - Saug |  | 20% DF CY 2019 | Road Rehabilitation | 12.52 | km | Contract | Project Cost: | 6500000 | Target Completion Date: | 2019-03-26 | Program: | 6500000 | Planned: | 100% | No. of Persons: | 19 | Completed as per physical accomplishment. Financial documents still on process
New Corella | Saug | 1st Eng'g. Dist. | Completed | 2019-03-26 | 2020-06-30 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES | [7 empty] | Project Engineer: | Pilotos | Revised Completion Date: | 2019-06-10 | Allotment: | 6500000 | Revised: |  | No. of Man-days: | 570
New Corella | Saug | 1st Eng'g. Dist. | Completed | 2019-03-26 | 2020-06-30 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES | [7 empty] | Implementor: | PEO | No. of days suspended: | 28 | Disbursement: | 6500000 | Actual: | 100%
New Corella | Saug | 1st Eng'g. Dist. | Completed | 2019-03-26 | 2020-06-30 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES | [7 empty] | Duration: |  | No. of days extended: | 48 |  |  | Slippage: | 0%
New Corella | Saug | 1st Eng'g. Dist. | Completed | 2019-03-26 | 2020-06-30 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES | [7 empty] | Date Allotment Released: |  | Date completed: | 2020-06-30
New Corella | Saug | 1st Eng'g. Dist. | Completed | 2019-03-26 | 2020-06-30 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES | [7 empty] | Date Started: | 2019-03-26
Asuncion | Cabaywa | 1st Eng'g. Dist. | Completed | 2019-03-26 | 2020-06-30 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES | Jct. Monte Carlo - Upper Cabaywa - Canatan |  | 20% DF CY 2019 | Road Rehabilitation | 4.61 | km | Contract | Project Cost: | 8838000 | Target Completion Date: | 2019-03-26 | Program: | 8838000 | Planned: | 100% | No. of Persons: | 19 | Completed as per physical accomplishment. Financial documents still on process
Asuncion | Cabaywa | 1st Eng'g. Dist. | Completed | 2019-03-26 | 2020-06-30 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES | [7 empty] | Project Engineer: | Garcia | Revised Completion Date: | 2019-03-26 | Allotment: | 8838000 | Revised: |  | No. of Man-days: | 570
Asuncion | Cabaywa | 1st Eng'g. Dist. | Completed | 2019-03-26 | 2020-06-30 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES | [7 empty] | Implementor: | PEO | No. of days suspended: | 28 | Disbursement: | 8838000 | Actual: | 100%
Asuncion | Cabaywa | 1st Eng'g. Dist. | Completed | 2019-03-26 | 2020-06-30 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Asuncion | Cabaywa | 1st Eng'g. Dist. | Completed | 2019-03-26 | 2020-06-30 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES | [7 empty] | Date Allotment Released: | 2019-01-31 | Date completed: | 2020-06-30
Asuncion | Cabaywa | 1st Eng'g. Dist. | Completed | 2019-03-26 | 2020-06-30 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES | [7 empty] | Date Started: | 2019-03-26
Kapalong | Mamacao | 1st Eng'g. Dist. | On-going | 2020-02-05 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | Construction of Bleacher, Mamacao, Kapalong |  | GF CY 2018 (STIMULUS) | Bleacher |  | sq.m | Admin | Project Cost: | 500000 | Target Completion Date: | 2020-04-19 23:46 | Program: | 500000 | Planned: | 100% | No. of Persons: | 8 | Completed as per physical accomplishment. Financial documents still on process.
Kapalong | Mamacao | 1st Eng'g. Dist. | On-going | 2020-02-05 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Project Engineer: | Ambrosio | Revised Completion Date: | 2020-06-15 23:46 | Allotment: | 500000 | Revised: |  | No. of Man-days: | 120
Kapalong | Mamacao | 1st Eng'g. Dist. | On-going | 2020-02-05 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: |  | Actual: | 100%
Kapalong | Mamacao | 1st Eng'g. Dist. | On-going | 2020-02-05 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Duration: | 75 | No. of days extended: | 30 |  |  | Slippage:
Kapalong | Mamacao | 1st Eng'g. Dist. | On-going | 2020-02-05 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Date Allotment Released: |  | Date completed:
Kapalong | Mamacao | 1st Eng'g. Dist. | On-going | 2020-02-05 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Date Started: | 2020-02-05
Kapalong | Capungagan | 1st Eng'g. Dist. | On-going | 2016-04-06 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PRDP | Rehab. Of Capungagan-Boundary San Miguel FMR, Kapalong, Davao del Norte |  | PRDP CY 2015 | Road Concreting | 10.6 | km | Contract | Project Cost: | 108303841.7 | Target Completion Date: | 2020-02-14 23:46 | Program: | 108303841.7 | Planned: | 100% | No. of Persons: | 38 | Suspended effective April 5, 2020 due to issued Executive Order No. 31, series of 2020 the province of Davao del Norte in response to the State of Public Health Emergency and State of National Calamity (COVID19 Pandemic).
Kapalong | Capungagan | 1st Eng'g. Dist. | On-going | 2016-04-06 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PRDP | [7 empty] | Project Engineer: | Nasol | Revised Completion Date: | 2023-05-24 23:46 | Allotment: | 108303841.7 | Revised: | 97.28% | No. of Man-days: | 1140
Kapalong | Capungagan | 1st Eng'g. Dist. | On-going | 2016-04-06 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PRDP | [7 empty] | Implementor: | VICLAO | No. of days suspended: | 140 | Disbursement: | 60050673.93 | Actual: | 93.8%
Kapalong | Capungagan | 1st Eng'g. Dist. | On-going | 2016-04-06 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PRDP | [7 empty] | Duration: | 1410 | No. of days extended: | 1055 |  |  | Slippage: | -3.48%
Kapalong | Capungagan | 1st Eng'g. Dist. | On-going | 2016-04-06 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PRDP | [7 empty] | Date Allotment Released: | CY 2015 | Date completed:
Kapalong | Capungagan | 1st Eng'g. Dist. | On-going | 2016-04-06 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PRDP | [7 empty] | Date Started: | 2016-04-06
New Corella | Limbaan | 1st Eng'g. Dist. | On-going | 2019-04-08 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PRDP | Rehab. Of Pob.-Limbaan-Suawon-Macgum FMR w/ Bridge (42 ln.m), New Corella, Davao del Norte |  | PRDP CY 2015 | Road Concreting | 15.01 | km | Contract | Project Cost: | 205202114.16 | Target Completion Date: | 2019-01-18 | Program: | 205202114.16 | Planned: | 100% | No. of Persons: | 40 | On-going (Increase of Project Cost due to Variation Order Php 14,948,622.18, Partial suspension due to soft soil from sta. 8+000 - 10+000); (Suspended last April 5, 2020 due to COVID; Resumption Order dated June 1, 2020)
New Corella | Limbaan | 1st Eng'g. Dist. | On-going | 2019-04-08 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PRDP | [7 empty] | Project Engineer: | Madrigal | Revised Completion Date: | 2021-01-06 | Allotment: | 205202114.16 | Revised: | 83.77% | No. of Man-days: | 1200
New Corella | Limbaan | 1st Eng'g. Dist. | On-going | 2019-04-08 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PRDP | [7 empty] | Implementor: | Dvo. Rock Mixer | No. of days suspended: | 229 | Disbursement: | 141497191.47 | Actual: | 77.49%
New Corella | Limbaan | 1st Eng'g. Dist. | On-going | 2019-04-08 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PRDP | [7 empty] | Duration: | 1529 | No. of days extended: | 490 |  |  | Slippage: | -6.282%
New Corella | Limbaan | 1st Eng'g. Dist. | On-going | 2019-04-08 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PRDP | [7 empty] | Date Allotment Released: | CY 2015 | Date completed:
New Corella | Limbaan | 1st Eng'g. Dist. | On-going | 2019-04-08 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PRDP | [7 empty] | Date Started: | 2016-04-08
Asuncion | Sonlon-Camansa | 1st Eng'g. Dist. | On-going | 2019-03-28 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PRDP | Rehab. Of Sonlon - Camansa FMR Asuncion, Davao del Norte |  | PRDP CY 2015 | Road Concreting | 10.23 | km | Contract | Project Cost: | 215125015.81 | Target Completion Date: | 2020-06-15 | Program: | 215125015.81 | Planned: | 39.51% | No. of Persons: | 30 | On-going (Suspended last April 5, 2020 due to COVID; Resumption Order dated June 1, 2020)
Asuncion | Sonlon-Camansa | 1st Eng'g. Dist. | On-going | 2019-03-28 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PRDP | [7 empty] | Project Engineer: | Fabiala | Revised Completion Date: | 2020-06-15 | Allotment: | 215125015.81 | Revised: |  | No. of Man-days: | 780
Asuncion | Sonlon-Camansa | 1st Eng'g. Dist. | On-going | 2019-03-28 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PRDP | [7 empty] | Implementor: | Three w/Builders, Inc/Davao Rock Mixer Enterprises (JV) | No. of days suspended: |  | Disbursement: | 40523099.23 | Actual: | 31.6%
Asuncion | Sonlon-Camansa | 1st Eng'g. Dist. | On-going | 2019-03-28 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PRDP | [7 empty] | Duration: | 384 | No. of days extended: |  |  |  | Slippage: | -7.91%
Asuncion | Sonlon-Camansa | 1st Eng'g. Dist. | On-going | 2019-03-28 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PRDP | [7 empty] | Date Allotment Released: | 2018-09-18 | Date completed:
Asuncion | Sonlon-Camansa | 1st Eng'g. Dist. | On-going | 2019-03-28 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PRDP | [7 empty] | Date Started: | 2019-05-28
Kapalong | Capungagan | 1st Eng'g. Dist. | On-going | 2019-03-19 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PRDP | Cacao Production and Beans Marketing, Capungagan, Kapalong, Davao del Norte |  | PRDP CY 2016 | Building | 3610 | sq.m | Contract | Project Cost: | 5873626.8 | Target Completion Date: | 2019-11-24 | Program: | 5873626.8 | Planned: | 100% | No. of Persons: |  | Suspended due to modification of Detailed Design of mechanical Drier dated November 23, 2019; Waiting for the resumption order from DA.
Kapalong | Capungagan | 1st Eng'g. Dist. | On-going | 2019-03-19 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PRDP | [7 empty] | Project Engineer: | Delos Reyes | Revised Completion Date: | 2019-11-24 | Allotment: | 5873626.8 | Revised: |  | No. of Man-days:
Kapalong | Capungagan | 1st Eng'g. Dist. | On-going | 2019-03-19 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PRDP | [7 empty] | Implementor: | MICAH CONST. & SUPPLY | No. of days suspended: |  | Disbursement: | 4698901.44 | Actual: | 91.09%
Kapalong | Capungagan | 1st Eng'g. Dist. | On-going | 2019-03-19 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PRDP | [7 empty] | Duration: | 250 | No. of days extended: |  |  |  | Slippage: | -8.905%
Kapalong | Capungagan | 1st Eng'g. Dist. | On-going | 2019-03-19 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PRDP | [7 empty] | Date Allotment Released: | CY 2016 | Date completed:
Kapalong | Capungagan | 1st Eng'g. Dist. | On-going | 2019-03-19 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PRDP | [7 empty] | Date Started: | 2019-03-19
New Corella | Poblacion | 1st Eng'g. Dist. | On-going | 2019-01-17 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PRDP | Improvement of New Corella Nursery with Organic Input Production & Common Facility, Davao del Norte |  | PRDP CY 2016 | Building | 1901 | sq.m | Contract | Project Cost: | 9889628.45 | Target Completion Date: | 2019-11-23 | Program: | 9889628.45 | Planned: | 80.36% | No. of Persons: | 10 | On-going (Suspended last April 5, 2020 due to COVID; Resumption Order dated June 1, 2020)
New Corella | Poblacion | 1st Eng'g. Dist. | On-going | 2019-01-17 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PRDP | [7 empty] | Project Engineer: | Delos Reyes/Cabañero | Revised Completion Date: | 2020-08-09 | Allotment: | 9889628.45 | Revised: | 49.99% | No. of Man-days: | 250
New Corella | Poblacion | 1st Eng'g. Dist. | On-going | 2019-01-17 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PRDP | [7 empty] | Implementor: | SOUTH IRONROCK CORPORATION | No. of days suspended: | 260 | Disbursement: |  | Actual: | 46.3%
New Corella | Poblacion | 1st Eng'g. Dist. | On-going | 2019-01-17 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PRDP | [7 empty] | Duration: | 310 | No. of days extended: |  |  |  | Slippage: | -3.684%
New Corella | Poblacion | 1st Eng'g. Dist. | On-going | 2019-01-17 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PRDP | [7 empty] | Date Allotment Released: | CY 2016 | Date completed:
New Corella | Poblacion | 1st Eng'g. Dist. | On-going | 2019-01-17 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PRDP | [7 empty] | Date Started: | 2019-01-17
Tagum City | Pandapan | 1st Eng'g. Dist. | On-going |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPPAP-PAMANA | Const. of Trading Post, Storage Building with (1) unit Hauling Truck, Brgy. Pandapan |  | OPPAP-PAMANA CY 2017 | Building |  | sq.m | Contract | Project Cost: | 3975000 | Target Completion Date: | 0 | Program: | 3975000 | Planned: |  | No. of Persons: |  | Abstract 1220194004 (Tagum Builders);PO # 2019102828 - Truck
Tagum City | Pandapan | 1st Eng'g. Dist. | On-going |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPPAP-PAMANA | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 3975000 | Revised: |  | No. of Man-days:
Tagum City | Pandapan | 1st Eng'g. Dist. | On-going |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPPAP-PAMANA | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Tagum City | Pandapan | 1st Eng'g. Dist. | On-going |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPPAP-PAMANA | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Tagum City | Pandapan | 1st Eng'g. Dist. | On-going |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPPAP-PAMANA | [7 empty] | Date Allotment Released: | CY 2017 | Date completed:
Tagum City | Pandapan | 1st Eng'g. Dist. | On-going |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPPAP-PAMANA | [7 empty] | Date Started:
Kapalong |  | 1st Eng'g. Dist. | On-going | 2016-06-01 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPPAP-PAMANA | Construction of Biga Bridges, Kapalong (Original Contract Cost: P 24,959,503.45; Variation Order: P 4,067,412.00) |  | OPPAP-PAMANA CY 2014 | Road |  | km | Contract | Project Cost: | 29026915.45 | Target Completion Date: | 2018-07-30 23:59 | Program: | 29026915.45 | Planned: | 100% | No. of Persons: | 8 | Suspended due to RROW
Kapalong |  | 1st Eng'g. Dist. | On-going | 2016-06-01 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPPAP-PAMANA | [7 empty] | Project Engineer: | Limpo | Revised Completion Date: | 2020-03-25 23:59 | Allotment: | 29026915.45 | Revised: | 99.7% | No. of Man-days: | 290
Kapalong |  | 1st Eng'g. Dist. | On-going | 2016-06-01 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPPAP-PAMANA | [7 empty] | Implementor: | Davao Rock Mixer | No. of days suspended: | 604 | Disbursement: | 18489834.55 | Actual: | 85.37%
Kapalong |  | 1st Eng'g. Dist. | On-going | 2016-06-01 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPPAP-PAMANA | [7 empty] | Duration: | 760 | No. of days extended: |  |  |  | Slippage: | -14.33%
Kapalong |  | 1st Eng'g. Dist. | On-going | 2016-06-01 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPPAP-PAMANA | [7 empty] | Date Allotment Released: | CY 2014 | Date completed:
Kapalong |  | 1st Eng'g. Dist. | On-going | 2016-06-01 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPPAP-PAMANA | [7 empty] | Date Started: | 2016-07-01
Asuncion | Canatan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | QRF | Repair of Damaged Drainage/Creeks of Canatan, Asuncion |  | QRF CY 2015 & 2016 | Drainage/Creeks |  | km |  | Project Cost: | 137754.69 | Target Completion Date: | 0 | Program: | 137754.69 | Planned: |  | No. of Persons: |  | PO#2020061983 - FL2 LUMBER & CONST. SUPPLY; PO #2020062164 - jkle enterprises
Asuncion | Canatan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | QRF | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 137754.69 | Revised: |  | No. of Man-days:
Asuncion | Canatan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | QRF | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Asuncion | Canatan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | QRF | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Asuncion | Canatan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | QRF | [7 empty] | Date Allotment Released: |  | Date completed:
Asuncion | Canatan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | QRF | [7 empty] | Date Started:
Asuncion | Sagayen | 1st Eng'g. Dist. | On-going | 2018-11-15 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | QRF | Construction of Water Reservoir & Purchase of P.E. Pipelines, Sagayen, Asuncion |  | 20% DF CY 2017 (STIMULUS) | Water System |  |  | MLGU | Project Cost: | 500000 | Target Completion Date: | 2018-11-15 | Program: | 500000 | Planned: | 90% | No. of Persons: |  | Suspended due to non availability of water source during drilling.Find another location. Fund already transferred at Municipality of Asuncion with ChecK No. 2445174 and OR # 9238468,
Asuncion | Sagayen | 1st Eng'g. Dist. | On-going | 2018-11-15 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | QRF | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Asuncion | Sagayen | 1st Eng'g. Dist. | On-going | 2018-11-15 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | QRF | [7 empty] | Implementor: | MEO | No. of days suspended: |  | Disbursement: |  | Actual: | 90%
Asuncion | Sagayen | 1st Eng'g. Dist. | On-going | 2018-11-15 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | QRF | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Asuncion | Sagayen | 1st Eng'g. Dist. | On-going | 2018-11-15 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | QRF | [7 empty] | Date Allotment Released: | 2017-12-28 | Date completed:
Asuncion | Sagayen | 1st Eng'g. Dist. | On-going | 2018-11-15 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | QRF | [7 empty] | Date Started: | 2018-11-15
New Corella | Sta. Fe | 1st Eng'g. Dist. | On-going |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2017 | Road Rehabilitation at Prk. 1-Prk. 5, Sta. Fe, New Corella |  | 20% DF CY 2017 (STIMULUS) | Court |  |  | MLGU | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Fund already transferred at Municipality of Talaingod with ChecK No. 2445181 and OR # 7955667, dated March 16, 2018 . Amended from Electrification @ Prk. 1A-Prk. 5A)
New Corella | Sta. Fe | 1st Eng'g. Dist. | On-going |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2017 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 500000 | Revised: |  | No. of Man-days:
New Corella | Sta. Fe | 1st Eng'g. Dist. | On-going |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2017 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
New Corella | Sta. Fe | 1st Eng'g. Dist. | On-going |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2017 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | Sta. Fe | 1st Eng'g. Dist. | On-going |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2017 | [7 empty] | Date Allotment Released: | 2017-12-28 | Date completed:
New Corella | Sta. Fe | 1st Eng'g. Dist. | On-going |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2017 | [7 empty] | Date Started:
Talaingod | Palma Gil | 1st Eng'g. Dist. | On-going |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2017 | Const. of Covered Court Bleacher, Palma Gil, Talaingod |  | 20% DF CY 2017 | Court |  |  | MLGU | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | On-going (Fund already transferred at Municipality of Talaingod with ChecK No. 2445181 and OR # 7955667, dated March 16, 2018 . Amended from Electrification @ Prk. 1A-Prk. 5A
Talaingod | Palma Gil | 1st Eng'g. Dist. | On-going |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2017 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 500000 | Revised: |  | No. of Man-days:
Talaingod | Palma Gil | 1st Eng'g. Dist. | On-going |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2017 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Talaingod | Palma Gil | 1st Eng'g. Dist. | On-going |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2017 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Talaingod | Palma Gil | 1st Eng'g. Dist. | On-going |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2017 | [7 empty] | Date Allotment Released: | 2017-12-28 | Date completed:
Talaingod | Palma Gil | 1st Eng'g. Dist. | On-going |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2017 | [7 empty] | Date Started:
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2019-11-04 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./REHAB./COMP. OF VARIOUS GOV'T. BLDGS. STRUCT., FAC (Provincewide) LS - P9,000,000.00 | Rehab. Of PEO Training Center, (PDPM),Mankilam, Tagum City, (Part of P803,000.00)(20% DF CY 2018-P326,124.00) |  | 20% DF CY 2017 | Building | 85 | sq.m | Admin | Project Cost: | 476876 | Target Completion Date: | 2020-01-17 | Program: | 476876 | Planned: | 99% | No. of Persons: | 3 | Suspended (additional PR for Elect. Mat.) dated March 9, 2020
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2019-11-04 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./REHAB./COMP. OF VARIOUS GOV'T. BLDGS. STRUCT., FAC (Provincewide) LS - P9,000,000.00 | [7 empty] | Project Engineer: | Chua | Revised Completion Date: | 2020-03-15 | Allotment: | 476876 | Revised: |  | No. of Man-days: | 57
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2019-11-04 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./REHAB./COMP. OF VARIOUS GOV'T. BLDGS. STRUCT., FAC (Provincewide) LS - P9,000,000.00 | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: | 407521.7 | Actual: | 99%
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2019-11-04 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./REHAB./COMP. OF VARIOUS GOV'T. BLDGS. STRUCT., FAC (Provincewide) LS - P9,000,000.00 | [7 empty] | Duration: | 74 | No. of days extended: | 58 |  |  | Slippage: | 0%
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2019-11-04 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./REHAB./COMP. OF VARIOUS GOV'T. BLDGS. STRUCT., FAC (Provincewide) LS - P9,000,000.00 | [7 empty] | Date Allotment Released: | 2019-02-12 | Date completed:
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2019-11-04 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./REHAB./COMP. OF VARIOUS GOV'T. BLDGS. STRUCT., FAC (Provincewide) LS - P9,000,000.00 | [7 empty] | Date Started: | 2019-11-04
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2018-07-17 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./REHAB./COMP. OF VARIOUS GOV'T. BLDGS. STRUCT., FAC (Provincewide) LS - P9,000,000.00 | Upgrading of DDNSTC (Basketball/Voleyball MP Covered Court),Sports Center, Mankilam, Tagum City |  | SB # 4 CY 2017 | Covered Court | 2252.69 | sq.m | Contract | Project Cost: | 99992356.64 | Target Completion Date: | 2019-07-11 | Program: | 99992356.64 | Planned: | 100% | No. of Persons: | 10 | On-going (Suspended last April 5, 2020 due to COVID; Resumption Order dated May 4, 2020)
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2018-07-17 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./REHAB./COMP. OF VARIOUS GOV'T. BLDGS. STRUCT., FAC (Provincewide) LS - P9,000,000.00 | [7 empty] | Project Engineer: | Daral | Revised Completion Date: |  | Allotment: | 99992356.64 | Revised: |  | No. of Man-days: | 310
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2018-07-17 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./REHAB./COMP. OF VARIOUS GOV'T. BLDGS. STRUCT., FAC (Provincewide) LS - P9,000,000.00 | [7 empty] | Implementor: | YBC | No. of days suspended: |  | Disbursement: | 18280402.33 | Actual: | 73.04%
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2018-07-17 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./REHAB./COMP. OF VARIOUS GOV'T. BLDGS. STRUCT., FAC (Provincewide) LS - P9,000,000.00 | [7 empty] | Duration: | 360 | No. of days extended: | 20 |  |  | Slippage: | -26.96%
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2018-07-17 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./REHAB./COMP. OF VARIOUS GOV'T. BLDGS. STRUCT., FAC (Provincewide) LS - P9,000,000.00 | [7 empty] | Date Allotment Released: | 2018-10-16 | Date completed:
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2018-07-17 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./REHAB./COMP. OF VARIOUS GOV'T. BLDGS. STRUCT., FAC (Provincewide) LS - P9,000,000.00 | [7 empty] | Date Started: | 2018-07-17
Asuncion | Saug | 1st Eng'g. Dist. | On-going | 2019-01-03 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | QRF | Rehab. Of Saug Bridge of Slope Protection |  | QRF CY 2017 | Slope Protection | 356.4 | ln.m | Admin | Project Cost: | 4850000 | Target Completion Date: | 2019-05-02 23:46 | Program: | 4850000 | Planned: | 74.56% | No. of Persons: | 13 | On-going (Suspended dated January 28, 2019; Resumption February 3, 2020; Resumption Order dated May 4, 2020; Suspended last April 5, 2020 due to COVID; resumption order dated May 4, 2020)
Asuncion | Saug | 1st Eng'g. Dist. | On-going | 2019-01-03 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | QRF | [7 empty] | Project Engineer: | Gone | Revised Completion Date: | 2020-08-19 23:46 | Allotment: | 4850000 | Revised: |  | No. of Man-days: | 195
Asuncion | Saug | 1st Eng'g. Dist. | On-going | 2019-01-03 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | QRF | [7 empty] | Implementor: | PEO | No. of days suspended: | 400 | Disbursement: | 1628912.92 | Actual: | 71.13%
Asuncion | Saug | 1st Eng'g. Dist. | On-going | 2019-01-03 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | QRF | [7 empty] | Duration: | 120 | No. of days extended: | 75 |  |  | Slippage: | -3.43%
Asuncion | Saug | 1st Eng'g. Dist. | On-going | 2019-01-03 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | QRF | [7 empty] | Date Allotment Released: | 2018-05-25 | Date completed:
Asuncion | Saug | 1st Eng'g. Dist. | On-going | 2019-01-03 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | QRF | [7 empty] | Date Started: | 2019-01-03
Kapalong | Gupitan | 1st Eng'g. Dist. | On-going | 2019-02-22 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | QRF | Re-channeling of BIGA River with Earth Dike and Slope Protection, Brgy. Gupitan, Kaplaong |  | QRF CY 2017 | Slope Protection | 0.9 | ln.m | Contract | Project Cost: | 12100000 | Target Completion Date: | 2019-06-11 23:46 | Program: | 12100000 | Planned: | 8.3% | No. of Persons: | 4 | On-going (Suspended last April 5, 2020 due to COVID; resumption order dated May 4, 2020)
Kapalong | Gupitan | 1st Eng'g. Dist. | On-going | 2019-02-22 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | QRF | [7 empty] | Project Engineer: | Limpo | Revised Completion Date: | 2019-06-11 23:46 | Allotment: | 12100000 | Revised: |  | No. of Man-days: | 120
Kapalong | Gupitan | 1st Eng'g. Dist. | On-going | 2019-02-22 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | QRF | [7 empty] | Implementor: | Alpha & Omega | No. of days suspended: |  | Disbursement: |  | Actual: | 3.36%
Kapalong | Gupitan | 1st Eng'g. Dist. | On-going | 2019-02-22 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | QRF | [7 empty] | Duration: | 110 | No. of days extended: |  |  |  | Slippage: | -4.94%
Kapalong | Gupitan | 1st Eng'g. Dist. | On-going | 2019-02-22 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | QRF | [7 empty] | Date Allotment Released: | 2018-07-20 | Date completed:
Kapalong | Gupitan | 1st Eng'g. Dist. | On-going | 2019-02-22 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | QRF | [7 empty] | Date Started: | 2019-02-22
San Isidro | Linao | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | WATER SYSTEM LS - P 10,000,000.00 | Const. of PWS Linao, San Isidro |  | 20% DF CY 2018 | geo-resistivty/drillig |  |  | Admin | Project Cost: | 62000 | Target Completion Date: |  | Program: | 62000 | Planned: |  | No. of Persons: |  | For implementation
San Isidro | Linao | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | WATER SYSTEM LS - P 10,000,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 62000 | Revised: |  | No. of Man-days:
San Isidro | Linao | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | WATER SYSTEM LS - P 10,000,000.00 | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual:
San Isidro | Linao | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | WATER SYSTEM LS - P 10,000,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
San Isidro | Linao | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | WATER SYSTEM LS - P 10,000,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
San Isidro | Linao | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | WATER SYSTEM LS - P 10,000,000.00 | [7 empty] | Date Started:
San Isidro | Mamalian | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | WATER SYSTEM LS - P 10,000,000.00 | Const. of PWS Mamalian, San Isidro |  | 20% DF CY 2018 | geo-resistivty/drillig |  |  | Admin | Project Cost: | 62000 | Target Completion Date: |  | Program: | 62000 | Planned: |  | No. of Persons: |  | For declaration of savings because the spring water source is not feasible for development.
San Isidro | Mamalian | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | WATER SYSTEM LS - P 10,000,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 62000 | Revised: |  | No. of Man-days:
San Isidro | Mamalian | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | WATER SYSTEM LS - P 10,000,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
San Isidro | Mamalian | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | WATER SYSTEM LS - P 10,000,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
San Isidro | Mamalian | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | WATER SYSTEM LS - P 10,000,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
San Isidro | Mamalian | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | WATER SYSTEM LS - P 10,000,000.00 | [7 empty] | Date Started:
San Isidro | Sagayen | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | WATER SYSTEM LS - P 10,000,000.00 | Const. of PWS Sagayen, San Isidro |  | 20% DF CY 2018 | geo-resistivty/drillig |  |  | Admin | Project Cost: | 62000 | Target Completion Date: |  | Program: | 62000 | Planned: |  | No. of Persons: |  | For implementation
San Isidro | Sagayen | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | WATER SYSTEM LS - P 10,000,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 62000 | Revised: |  | No. of Man-days:
San Isidro | Sagayen | 1st Eng'g. Dist. | For Implementation |  | 0 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | WATER SYSTEM LS - P 10,000,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
San Isidro | Sagayen | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | WATER SYSTEM LS - P 10,000,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
San Isidro | Sagayen | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | WATER SYSTEM LS - P 10,000,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
San Isidro | Sagayen | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | WATER SYSTEM LS - P 10,000,000.00 | [7 empty] | Date Started:
Tagum City | Pandapan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | WATER SYSTEM LS - P 10,000,000.00 | Installation of potable water System at Purok Nangka, Pandapan, Tagum City |  | 20% DF CY 2018 | Water System |  |  | Admin | Project Cost: | 1125000 | Target Completion Date: |  | Program: | 1125000 | Planned: |  | No. of Persons: |  | Waiting for deed of donation. Follow-up letter was already issued
Tagum City | Pandapan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | WATER SYSTEM LS - P 10,000,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 1125000 | Revised: |  | No. of Man-days:
Tagum City | Pandapan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | WATER SYSTEM LS - P 10,000,000.00 | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual:
Tagum City | Pandapan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | WATER SYSTEM LS - P 10,000,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Tagum City | Pandapan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | WATER SYSTEM LS - P 10,000,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Tagum City | Pandapan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | WATER SYSTEM LS - P 10,000,000.00 | [7 empty] | Date Started:
Asuncion | San Vicente | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | WATER SYSTEM LS - P 10,000,000.00 | Rehab./Impv't. of San Vicente Water System, Asuncion |  | 20% DF CY 2018 | Water System |  |  | Admin | Project Cost: | 1125000 | Target Completion Date: |  | Program: | 1125000 | Planned: |  | No. of Persons: |  | Abstract # 0220190484 still draft
Asuncion | San Vicente | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | WATER SYSTEM LS - P 10,000,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 1125000 | Revised: |  | No. of Man-days:
Asuncion | San Vicente | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | WATER SYSTEM LS - P 10,000,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Asuncion | San Vicente | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | WATER SYSTEM LS - P 10,000,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Asuncion | San Vicente | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | WATER SYSTEM LS - P 10,000,000.00 | [7 empty] | Date Allotment Released: | 2018-10-26 | Date completed:
Asuncion | San Vicente | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | WATER SYSTEM LS - P 10,000,000.00 | [7 empty] | Date Started:
Asuncion | Sonlon-Camansa | 1st Eng'g. Dist. | On-going | 2019-05-28 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PRDP | Rehab. Of Sonlon-Camansa FMR, Asuncion, Davao del Norte (PRDP Counterpart : 193,612,514.23) |  | 20% DF CY 2018 | Road Concreting | 10.23 | km | Contract | Project Cost: | 21512501.5 | Target Completion Date: | 2020-06-14 23:46 | Program: | 21512501.5 | Planned: | 39.51% | No. of Persons: | 30 | On-going
Asuncion | Sonlon-Camansa | 1st Eng'g. Dist. | On-going | 2019-05-28 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PRDP | [7 empty] | Project Engineer: | Fabiala | Revised Completion Date: | 2020-06-14 23:46 | Allotment: | 21512501.5 | Revised: |  | No. of Man-days: | 690
Asuncion | Sonlon-Camansa | 1st Eng'g. Dist. | On-going | 2019-05-28 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PRDP | [7 empty] | Implementor: | Three w/Builders, Inc/Davao Rock Mixer Enterprises (JV) | No. of days suspended: |  | Disbursement: | 4502566.58 | Actual: | 31.6%
Asuncion | Sonlon-Camansa | 1st Eng'g. Dist. | On-going | 2019-05-28 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PRDP | [7 empty] | Duration: | 384 | No. of days extended: |  |  |  | Slippage: | -7.91%
Asuncion | Sonlon-Camansa | 1st Eng'g. Dist. | On-going | 2019-05-28 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PRDP | [7 empty] | Date Allotment Released: | 2018-09-18 | Date completed:
Asuncion | Sonlon-Camansa | 1st Eng'g. Dist. | On-going | 2019-05-28 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PRDP | [7 empty] | Date Started: | 2019-05-28
San Isidro | Sagayen-Sawata | 1st Eng'g. Dist. | On-going | 2019-09-09 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | KALSADA | Impvt. of Km. 9 Sagayen - Sawata Provincial Road Phase II |  | 20% DF CY 2018 | Road Concreting | 1.303 | km | Admin | Project Cost: | 7742775.95 | Target Completion Date: | 2020-03-27 | Program: | 7742775.95 | Planned: | 45% | No. of Persons: | 6 | Suspended dated March 6, 2020 due to delay delivery of materials
San Isidro | Sagayen-Sawata | 1st Eng'g. Dist. | On-going | 2019-09-09 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | KALSADA | [7 empty] | Project Engineer: | Kenny | Revised Completion Date: |  | Allotment: | 7742775.95 | Revised: |  | No. of Man-days: | 138
San Isidro | Sagayen-Sawata | 1st Eng'g. Dist. | On-going | 2019-09-09 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | KALSADA | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: | 2603417.9455 | Actual: | 35.05%
San Isidro | Sagayen-Sawata | 1st Eng'g. Dist. | On-going | 2019-09-09 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | KALSADA | [7 empty] | Duration: | 200 | No. of days extended: |  |  |  | Slippage: | -9.95%
San Isidro | Sagayen-Sawata | 1st Eng'g. Dist. | On-going | 2019-09-09 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | KALSADA | [7 empty] | Date Allotment Released: | 2019-01-31 | Date completed:
San Isidro | Sagayen-Sawata | 1st Eng'g. Dist. | On-going | 2019-09-09 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | KALSADA | [7 empty] | Date Started: | 2019-09-09
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2019-11-04 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./REHAB./COMP. OF VARIOUS GOV'T. BLDGS. STRUCT., FAC (Provincewide) LS - LS - P13,523,124.00 | Rehab. Of PEO Training Center, (PDPM),Mankilam, Tagum City (Part of P803,000.00)(20% DF CY 2017-P476,876.00) |  | 20% DF CY 2018 | Building | 85 | sq.m | Admin | Project Cost: | 326124 | Target Completion Date: | 2020-01-17 | Program: | 326124 | Planned: |  | No. of Persons: |  | suspended due to additional materials for electrical works
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2019-11-04 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./REHAB./COMP. OF VARIOUS GOV'T. BLDGS. STRUCT., FAC (Provincewide) LS - P13,523,124.00 | [7 empty] | Project Engineer: | Chua | Revised Completion Date: | 2020-03-14 | Allotment: | 326124 | Revised: |  | No. of Man-days:
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2019-11-04 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./REHAB./COMP. OF VARIOUS GOV'T. BLDGS. STRUCT., FAC (Provincewide) LS - P13,523,124.00 | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual:
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2019-11-04 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./REHAB./COMP. OF VARIOUS GOV'T. BLDGS. STRUCT., FAC (Provincewide) LS - P13,523,124.00 | [7 empty] | Duration: | 74 | No. of days extended: | 57 |  |  | Slippage: | 0%
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2019-11-04 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./REHAB./COMP. OF VARIOUS GOV'T. BLDGS. STRUCT., FAC (Provincewide) LS - P13,523,124.00 | [7 empty] | Date Allotment Released: | 2019-02-12 | Date completed:
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2019-11-04 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./REHAB./COMP. OF VARIOUS GOV'T. BLDGS. STRUCT., FAC (Provincewide) LS - P13,523,124.00 | [7 empty] | Date Started: | 2019-11-04
Asuncion | Camansa | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./REHAB./COMP. OF VARIOUS GOV'T. BLDGS. STRUCT., FAC (Provincewide) LS - LS - P13,523,124.00 | Construction of IP Tribal Council of Women at Brgy. Camansa, Asuncion |  | 20% DF CY 2018 | Building |  | sq.m | Admin | Project Cost: | 560000 | Target Completion Date: |  | Program: | 560000 | Planned: |  | No. of Persons: |  | Purchase Request # 20032714
Asuncion | Camansa | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./REHAB./COMP. OF VARIOUS GOV'T. BLDGS. STRUCT., FAC (Provincewide) LS - P13,523,124.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 560000 | Revised: |  | No. of Man-days:
Asuncion | Camansa | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./REHAB./COMP. OF VARIOUS GOV'T. BLDGS. STRUCT., FAC (Provincewide) LS - P13,523,124.00 | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual:
Asuncion | Camansa | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./REHAB./COMP. OF VARIOUS GOV'T. BLDGS. STRUCT., FAC (Provincewide) LS - P13,523,124.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Asuncion | Camansa | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./REHAB./COMP. OF VARIOUS GOV'T. BLDGS. STRUCT., FAC (Provincewide) LS - P13,523,124.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Asuncion | Camansa | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./REHAB./COMP. OF VARIOUS GOV'T. BLDGS. STRUCT., FAC (Provincewide) LS - P13,523,124.00 | [7 empty] | Date Started:
New Corella | Del Monte | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | RURAL ELECTRIFICATION (Provincewide) LS - P5,000,000.00 | Rural Electrification at Del Monte, New Corella |  | 20% DF CY 2018 | Electrification |  |  | Contract | Project Cost: | 1000000 | Target Completion Date: |  | Program: | 1000000 | Planned: |  | No. of Persons: |  | Post Qualification on process
New Corella | Del Monte | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | RURAL ELECTRIFICATION (Provincewide) LS - P5,000,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 1000000 | Revised: |  | No. of Man-days:
New Corella | Del Monte | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | RURAL ELECTRIFICATION (Provincewide) LS - P5,000,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
New Corella | Del Monte | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | RURAL ELECTRIFICATION (Provincewide) LS - P5,000,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | Del Monte | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | RURAL ELECTRIFICATION (Provincewide) LS - P5,000,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
New Corella | Del Monte | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | RURAL ELECTRIFICATION (Provincewide) LS - P5,000,000.00 | [7 empty] | Date Started:
Asuncion | Camansa | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | RURAL ELECTRIFICATION (Provincewide) LS - P5,000,000.00 | Const. of Distribution Line in Sitio Prk. 1,3,4, 11 and 7, Camansa, Asuncion |  | 20% DF CY 2018 | Electrification |  |  | Contract | Project Cost: | 4000000 | Target Completion Date: |  | Program: | 4000000 | Planned: |  | No. of Persons: |  | Purchase Request # 19093670 (On process )
Asuncion | Camansa | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | RURAL ELECTRIFICATION (Provincewide) LS - P5,000,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 4000000 | Revised: |  | No. of Man-days:
Asuncion | Camansa | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | RURAL ELECTRIFICATION (Provincewide) LS - P5,000,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Asuncion | Camansa | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | RURAL ELECTRIFICATION (Provincewide) LS - P5,000,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Asuncion | Camansa | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | RURAL ELECTRIFICATION (Provincewide) LS - P5,000,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Asuncion | Camansa | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | RURAL ELECTRIFICATION (Provincewide) LS - P5,000,000.00 | [7 empty] | Date Started:
Talaingod | Palma Gil | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./REHAB./COMP. OF VARIOUS GOV'T. BLDGS. STRUCT., FAC (Provincewide) | Const. of Standard Quarantine Shed for Car Bath Natulian, Brgy. Palma Gil, Talaingod |  | 20% DF CY 2018 | Car Bath |  |  | Contract | Project Cost: | 200000 | Target Completion Date: |  | Program: | 200000 | Planned: |  | No. of Persons: |  | Awarded to DIGOS CONSTRAK
Talaingod | Palma Gil | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./REHAB./COMP. OF VARIOUS GOV'T. BLDGS. STRUCT., FAC (Provincewide) | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 200000 | Revised: |  | No. of Man-days:
Talaingod | Palma Gil | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./REHAB./COMP. OF VARIOUS GOV'T. BLDGS. STRUCT., FAC (Provincewide) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Talaingod | Palma Gil | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./REHAB./COMP. OF VARIOUS GOV'T. BLDGS. STRUCT., FAC (Provincewide) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Talaingod | Palma Gil | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./REHAB./COMP. OF VARIOUS GOV'T. BLDGS. STRUCT., FAC (Provincewide) | [7 empty] | Date Allotment Released: |  | Date completed:
Talaingod | Palma Gil | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./REHAB./COMP. OF VARIOUS GOV'T. BLDGS. STRUCT., FAC (Provincewide) | [7 empty] | Date Started:
Tagum City | Balamban | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./REHAB./COMP. OF VARIOUS GOV'T. BLDGS. STRUCT., FAC (Provincewide) | Construction of Veterinary Quarantine Station, New balamban, Tagum City |  | 20% DF CY 2018 | Car Bath |  |  | Contract | Project Cost: | 200000 | Target Completion Date: |  | Program: | 200000 | Planned: |  | No. of Persons: |  | Awarded to ALLBRYCAR
Tagum City | Balamban | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./REHAB./COMP. OF VARIOUS GOV'T. BLDGS. STRUCT., FAC (Provincewide) | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 200000 | Revised: |  | No. of Man-days:
Tagum City | Balamban | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./REHAB./COMP. OF VARIOUS GOV'T. BLDGS. STRUCT., FAC (Provincewide) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Tagum City | Balamban | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./REHAB./COMP. OF VARIOUS GOV'T. BLDGS. STRUCT., FAC (Provincewide) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Tagum City | Balamban | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./REHAB./COMP. OF VARIOUS GOV'T. BLDGS. STRUCT., FAC (Provincewide) | [7 empty] | Date Allotment Released: |  | Date completed:
Tagum City | Balamban | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./REHAB./COMP. OF VARIOUS GOV'T. BLDGS. STRUCT., FAC (Provincewide) | [7 empty] | Date Started:
Asuncion | New Santiago | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | Const. of Potable water System at Prk. 6, New Santiago, Asuncion |  | GF CY 2018 (STIMULUS) | Water System |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Amended in AIP 3rd revision CY 2019 increasing the amount to complete the project For plan preparation c/o Amamio
Asuncion | New Santiago | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 500000 | Revised: |  | No. of Man-days:
Asuncion | New Santiago | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Asuncion | New Santiago | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Asuncion | New Santiago | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Date Allotment Released: |  | Date completed:
Asuncion | New Santiago | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Date Started:
Tagum City | Pagsabangan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | Completion of GYM Bleacher w/ Electrification, Pagsabangan, Tagum City |  | GF CY 2018 (STIMULUS) | Bleacher |  |  | MLGU | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | For implementation but the project was implemented by the brgy. Waiting for resolution to change priority Alloted March 12, 2019
Tagum City | Pagsabangan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 500000 | Revised: |  | No. of Man-days:
Tagum City | Pagsabangan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Tagum City | Pagsabangan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Tagum City | Pagsabangan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Date Allotment Released: |  | Date completed:
Tagum City | Pagsabangan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Date Started:
Tagum City | Libuganon | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | Construction of Drainage Canal, Libuganon, Tagum City |  | GF CY 2018 (STIMULUS) | Drainage |  |  | Admin | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | For implementation
Tagum City | Libuganon | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 500000 | Revised: |  | No. of Man-days:
Tagum City | Libuganon | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual:
Tagum City | Libuganon | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Tagum City | Libuganon | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Date Allotment Released: |  | Date completed:
Tagum City | Libuganon | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Date Started:
Kapalong | Luna | 1st Eng'g. Dist. | On-going | 2020-06-01 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | Construction of Concrete Perimeter Fence, Luna, Kapalaong |  | GF CY 2018 (STIMULUS) | Fence |  | sq.m | Admin | Project Cost: | 500000 | Target Completion Date: | 2020-07-21 | Program: | 500000 | Planned: | 92% | No. of Persons: | 8 | On-going
Kapalong | Luna | 1st Eng'g. Dist. | On-going | 2020-06-01 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Project Engineer: | Ambrosio | Revised Completion Date: | 2020-07-21 | Allotment: | 500000 | Revised: |  | No. of Man-days: | 120
Kapalong | Luna | 1st Eng'g. Dist. | On-going | 2020-06-01 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: | 93%
Kapalong | Luna | 1st Eng'g. Dist. | On-going | 2020-06-01 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Duration: | 50 | No. of days extended: |  |  |  | Slippage: | 1%
Kapalong | Luna | 1st Eng'g. Dist. | On-going | 2020-06-01 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Date Allotment Released: |  | Date completed:
Kapalong | Luna | 1st Eng'g. Dist. | On-going | 2020-06-01 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Date Started: | 2020-06-01
Kapalong | Maniki | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | Completion of Brgy. Health Center, Maniki, Kapalong |  | GF CY 2018 (STIMULUS) | Building |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | For amendment.To submit a new resolution for another priority project which is the Const. of Multi-Purpose Pavement but the propose site is not is donated because the previous project Completion of Brgy. Health Center was funded by the LGU of Kapalong
Kapalong | Maniki | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 500000 | Revised: |  | No. of Man-days:
Kapalong | Maniki | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Kapalong | Maniki | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Kapalong | Maniki | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Date Allotment Released: |  | Date completed:
Kapalong | Maniki | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Date Started:
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | Grouted Riprap on Embankment Sto. Ñino, Talaingod |  | GF CY 2018 (STIMULUS) | Riprap |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Plan and POW on process c/o PDPM
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 500000 | Revised: |  | No. of Man-days:
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Date Allotment Released: |  | Date completed:
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Date Started:
Talaingod | Dagohoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | Barangay Hall Improvement, Dagohoy, Talaingod |  | GF CY 2018 (STIMULUS) | Building |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | For amendment to Construction of Retaining Wall as per recommendation by Engr. Misa during site re-evaluation. Plan & POW completed.Resolution from the Brgy. Council to support the amendment c/o Engr. Canillada
Talaingod | Dagohoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 500000 | Revised: |  | No. of Man-days:
Talaingod | Dagohoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Talaingod | Dagohoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Talaingod | Dagohoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Date Allotment Released: |  | Date completed:
Talaingod | Dagohoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Date Started:
Talaingod | Palma Gil | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | Construction of 2 Classroom Building Datu Jose Libayao NHS Ext, Natulian, Palma Gil, Talaingod |  | GF CY 2018 (STIMULUS) | Building |  |  |  | Project Cost: | 1930933.28 | Target Completion Date: |  | Program: | 1930933.28 | Planned: |  | No. of Persons: |  | PO # 2020031342 - ALPEBEL BUILDERS & SUPPLY CORP.
Talaingod | Palma Gil | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 1930933.28 | Revised: |  | No. of Man-days:
Talaingod | Palma Gil | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Talaingod | Palma Gil | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Talaingod | Palma Gil | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Date Allotment Released: |  | Date completed:
Talaingod | Palma Gil | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Date Started:
New Corella | Mesaoy | 1st Eng'g. Dist. | On-going | 2018-11-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REHABILITATION OF VARIOUS PROVINCIAL ROADS | Mesaoy - Jct. Mahayahay |  | SB # 1 CY 2018 | Road Rehabilitation |  | km | Admin | Project Cost: | 1534000 | Target Completion Date: | 2018-12-15 23:46 | Program: | 1534000 | Planned: | 100% | No. of Persons: | 6 | Completed as per physical accomplishment. Financial documents still on process.
New Corella | Mesaoy | 1st Eng'g. Dist. | On-going | 2018-11-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REHABILITATION OF VARIOUS PROVINCIAL ROADS | [7 empty] | Project Engineer: | Pilotos | Revised Completion Date: |  | Allotment: | 1534000 | Revised: |  | No. of Man-days: | 150
New Corella | Mesaoy | 1st Eng'g. Dist. | On-going | 2018-11-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REHABILITATION OF VARIOUS PROVINCIAL ROADS | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: | 100%
New Corella | Mesaoy | 1st Eng'g. Dist. | On-going | 2018-11-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REHABILITATION OF VARIOUS PROVINCIAL ROADS | [7 empty] | Duration: | 30 | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | Mesaoy | 1st Eng'g. Dist. | On-going | 2018-11-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REHABILITATION OF VARIOUS PROVINCIAL ROADS | [7 empty] | Date Allotment Released: | 2018-07-19 | Date completed: | 2020-02-29
New Corella | Mesaoy | 1st Eng'g. Dist. | On-going | 2018-11-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REHABILITATION OF VARIOUS PROVINCIAL ROADS | [7 empty] | Date Started: | 2018-11-16
Kapalong | Maniki | 1st Eng'g. Dist. | On-going | 2019-11-02 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./COMPL./IMPV'T. OF VARIOUS GOV'T. BLDGS., STRUCTURES & FACILITIES (Const. in Progress - Bldgs. & Other Structures | Const./Impv't. of DDN Hospital Kapalong Zone |  | SB # 2 CY 2018 | Building |  | sq.m | Contract | Project Cost: | 5000000 | Target Completion Date: | 2020-06-09 | Program: | 5000000 | Planned: | 100% | No. of Persons: | 6 | Completed as per physical accomplishment. Financial documents still on process.
Kapalong | Maniki | 1st Eng'g. Dist. | On-going | 2019-11-02 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./COMPL./IMPV'T. OF VARIOUS GOV'T. BLDGS., STRUCTURES & FACILITIES (Const. in Progress - Bldgs. & Other Structures | [7 empty] | Project Engineer: | Ambrosio | Revised Completion Date: | 2020-07-07 | Allotment: | 5000000 | Revised: |  | No. of Man-days: | 150
Kapalong | Maniki | 1st Eng'g. Dist. | On-going | 2019-11-02 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./COMPL./IMPV'T. OF VARIOUS GOV'T. BLDGS., STRUCTURES & FACILITIES (Const. in Progress - Bldgs. & Other Structures | [7 empty] | Implementor: | MAG CORP. | No. of days suspended: | 28 | Disbursement: | 4781000 | Actual: | 100%
Kapalong | Maniki | 1st Eng'g. Dist. | On-going | 2019-11-02 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./COMPL./IMPV'T. OF VARIOUS GOV'T. BLDGS., STRUCTURES & FACILITIES (Const. in Progress - Bldgs. & Other Structures | [7 empty] | Duration: | 220 | No. of days extended: |  |  |  | Slippage: | 0%
Kapalong | Maniki | 1st Eng'g. Dist. | On-going | 2019-11-02 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./COMPL./IMPV'T. OF VARIOUS GOV'T. BLDGS., STRUCTURES & FACILITIES (Const. in Progress - Bldgs. & Other Structures | [7 empty] | Date Allotment Released: | 2018-09-04 | Date completed: | 2020-07-07
Kapalong | Maniki | 1st Eng'g. Dist. | On-going | 2019-11-02 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./COMPL./IMPV'T. OF VARIOUS GOV'T. BLDGS., STRUCTURES & FACILITIES (Const. in Progress - Bldgs. & Other Structures | [7 empty] | Date Started: | 2019-11-02
New Corella | Poblacion | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./COMPL./IMPV'T. OF VARIOUS GOV'T. BLDGS., STRUCTURES & FACILITIES (Const. in Progress - Bldgs. & Other Structures | Compl. Of Bahay Pag-Asa for Minors, New Corella |  | SB # 2 CY 2018 | Building |  |  | Admin | Project Cost: | 3450000 | Target Completion Date: |  | Program: | 3450000 | Planned: |  | No. of Persons: |  | For implementation
New Corella | Poblacion | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./COMPL./IMPV'T. OF VARIOUS GOV'T. BLDGS., STRUCTURES & FACILITIES (Const. in Progress - Bldgs. & Other Structures | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 3450000 | Revised: |  | No. of Man-days:
New Corella | Poblacion | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./COMPL./IMPV'T. OF VARIOUS GOV'T. BLDGS., STRUCTURES & FACILITIES (Const. in Progress - Bldgs. & Other Structures | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
New Corella | Poblacion | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./COMPL./IMPV'T. OF VARIOUS GOV'T. BLDGS., STRUCTURES & FACILITIES (Const. in Progress - Bldgs. & Other Structures | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | Poblacion | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./COMPL./IMPV'T. OF VARIOUS GOV'T. BLDGS., STRUCTURES & FACILITIES (Const. in Progress - Bldgs. & Other Structures | [7 empty] | Date Allotment Released: |  | Date completed:
New Corella | Poblacion | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./COMPL./IMPV'T. OF VARIOUS GOV'T. BLDGS., STRUCTURES & FACILITIES (Const. in Progress - Bldgs. & Other Structures | [7 empty] | Date Started:
Tagum City | Mankilam | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./COMPL./IMPV'T. OF VARIOUS GOV'T. BLDGS., STRUCTURES & FACILITIES (Const. in Progress - Bldgs. & Other Structures | Const. of Add'l. 2nd Level Multi-Purpose HalI, PGSO warehouse,Bldg., Mankilam |  | SB # 2 CY 2018 | Building |  |  | Contract | Project Cost: | 7483756.22 | Target Completion Date: |  | Program: | 7483756.22 | Planned: |  | No. of Persons: |  | PO #2020020808 - FZI CONSTRUCTION AND PARTS SUPPLY
Tagum City | Mankilam | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./COMPL./IMPV'T. OF VARIOUS GOV'T. BLDGS., STRUCTURES & FACILITIES (Const. in Progress - Bldgs. & Other Structures | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 7483756.22 | Revised: |  | No. of Man-days:
Tagum City | Mankilam | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./COMPL./IMPV'T. OF VARIOUS GOV'T. BLDGS., STRUCTURES & FACILITIES (Const. in Progress - Bldgs. & Other Structures | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Tagum City | Mankilam | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./COMPL./IMPV'T. OF VARIOUS GOV'T. BLDGS., STRUCTURES & FACILITIES (Const. in Progress - Bldgs. & Other Structures | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Tagum City | Mankilam | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./COMPL./IMPV'T. OF VARIOUS GOV'T. BLDGS., STRUCTURES & FACILITIES (Const. in Progress - Bldgs. & Other Structures | [7 empty] | Date Allotment Released: |  | Date completed:
Tagum City | Mankilam | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./COMPL./IMPV'T. OF VARIOUS GOV'T. BLDGS., STRUCTURES & FACILITIES (Const. in Progress - Bldgs. & Other Structures | [7 empty] | Date Started:
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2020-04-30 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./COMPL./IMPV'T. OF VARIOUS GOV'T. BLDGS., STRUCTURES & FACILITIES (Const. in Progress - Bldgs. & Other Structures | Construction of SP/Legislative Building, Gov't. Center, Mankilam, Tagum City |  | SB # 3 CY 2018 | Building |  | sq.m | Contract | Project Cost: | 147262698.81 | Target Completion Date: | 2021-04-04 | Program: | 147262698.81 | Planned: | 4.205% | No. of Persons: | 20 | On-going (Suspended effective April 5, 2020 due to COVID; resumption order dated May 4, 2020)
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2020-04-30 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./COMPL./IMPV'T. OF VARIOUS GOV'T. BLDGS., STRUCTURES & FACILITIES (Const. in Progress - Bldgs. & Other Structures | [7 empty] | Project Engineer: | Japay/Albaracin | Revised Completion Date: | 2021-05-01 | Allotment: | 147262698.81 | Revised: |  | No. of Man-days: | 370
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2020-04-30 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./COMPL./IMPV'T. OF VARIOUS GOV'T. BLDGS., STRUCTURES & FACILITIES (Const. in Progress - Bldgs. & Other Structures | [7 empty] | Implementor: | Tagum Builders | No. of days suspended: | 27 | Disbursement: |  | Actual: | 4.347%
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2020-04-30 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./COMPL./IMPV'T. OF VARIOUS GOV'T. BLDGS., STRUCTURES & FACILITIES (Const. in Progress - Bldgs. & Other Structures | [7 empty] | Duration: | 370 | No. of days extended: |  |  |  | Slippage: | 0.1415%
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2020-04-30 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./COMPL./IMPV'T. OF VARIOUS GOV'T. BLDGS., STRUCTURES & FACILITIES (Const. in Progress - Bldgs. & Other Structures | [7 empty] | Date Allotment Released: |  | Date completed:
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2020-04-30 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./COMPL./IMPV'T. OF VARIOUS GOV'T. BLDGS., STRUCTURES & FACILITIES (Const. in Progress - Bldgs. & Other Structures | [7 empty] | Date Started: | 2020-03-30
Asuncion | Napungas | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | Rehab./Impv't. of MP Bldg. (Gym), Napungas, Asuncion |  | SB # 5 CY 2018 (STIMULUS) | GYM |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Abstract # 0620202137
Asuncion | Napungas | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Asuncion | Napungas | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Asuncion | Napungas | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Asuncion | Napungas | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Date Allotment Released: | 2019-02-04 | Date completed:
Asuncion | Napungas | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Date Started:
New Corella | Poblacion | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | Concreting of Drainage Canal from Prk. 3, 1-A, 2-A to Prk. 1-B, Brgy. Site, Phase @, New Corella |  | SB # 5 CY 2018 (STIMULUS) | Drainage |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Abstract draft
New Corella | Poblacion | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 500000 | Revised: |  | No. of Man-days:
New Corella | Poblacion | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
New Corella | Poblacion | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | Poblacion | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Date Allotment Released: |  | Date completed:
New Corella | Poblacion | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Date Started:
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2019-11-26 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./COMPL./IMPV'T. OF VARIOUS GOV'T. BLDGS., STRUCTURES & FACILITIES (Const. in Progress - Bldgs. & Other Structures | Division School Improvement (Davao del Norte DEPED Training Center), Tagum City |  | SEF (ANNUAL BUDGET CY 2018) | Building |  | sq.m | Admin | Project Cost: | 1250000 | Target Completion Date: | 2020-05-04 | Program: | 1250000 | Planned: | 100% | No. of Persons: | 18 | On-going (Suspended last April 5, 2020 due to COVID; resumption order dated May 4, 2020)
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2019-11-26 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./COMPL./IMPV'T. OF VARIOUS GOV'T. BLDGS., STRUCTURES & FACILITIES (Const. in Progress - Bldgs. & Other Structures | [7 empty] | Project Engineer: | Japay/Quirante | Revised Completion Date: | 2020-07-15 | Allotment: | 1250000 | Revised: | 83.63% | No. of Man-days: | 270
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2019-11-26 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./COMPL./IMPV'T. OF VARIOUS GOV'T. BLDGS., STRUCTURES & FACILITIES (Const. in Progress - Bldgs. & Other Structures | [7 empty] | Implementor: | Admin | No. of days suspended: | 27 | Disbursement: | 850625 | Actual: | 78.02%
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2019-11-26 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./COMPL./IMPV'T. OF VARIOUS GOV'T. BLDGS., STRUCTURES & FACILITIES (Const. in Progress - Bldgs. & Other Structures | [7 empty] | Duration: | 160 | No. of days extended: | 45 |  |  | Slippage: | -5.61%
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2019-11-26 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./COMPL./IMPV'T. OF VARIOUS GOV'T. BLDGS., STRUCTURES & FACILITIES (Const. in Progress - Bldgs. & Other Structures | [7 empty] | Date Allotment Released: | 2019-02-04 | Date completed:
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2019-11-26 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./COMPL./IMPV'T. OF VARIOUS GOV'T. BLDGS., STRUCTURES & FACILITIES (Const. in Progress - Bldgs. & Other Structures | [7 empty] | Date Started: | 2019-11-26
Talaingod | Dagohoy | 1st Eng'g. Dist. | On-going | 2019-11-17 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPAPP | Const. of Processing and Bagsakan Center, Brgy. Dagohoy, Talaingod |  | OPAPP-PAMANA CY 2018 | Building |  | sq.m | Contract | Project Cost: | 2500000 | Target Completion Date: | 2020-04-10 | Program: | 2500000 | Planned: | 55.61% | No. of Persons: | 8 | On-going; Resumption Order dated May 4, 2020
Talaingod | Dagohoy | 1st Eng'g. Dist. | On-going | 2019-11-17 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPAPP | [7 empty] | Project Engineer: | Dadula | Revised Completion Date: |  | Allotment: | 2500000 | Revised: |  | No. of Man-days: | 200
Talaingod | Dagohoy | 1st Eng'g. Dist. | On-going | 2019-11-17 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPAPP | [7 empty] | Implementor: | RLHV | No. of days suspended: |  | Disbursement: | 375000 | Actual: | 68.72%
Talaingod | Dagohoy | 1st Eng'g. Dist. | On-going | 2019-11-17 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPAPP | [7 empty] | Duration: | 145 | No. of days extended: |  |  |  | Slippage: | 13.11%
Talaingod | Dagohoy | 1st Eng'g. Dist. | On-going | 2019-11-17 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPAPP | [7 empty] | Date Allotment Released: | 2019-11-25 | Date completed:
Talaingod | Dagohoy | 1st Eng'g. Dist. | On-going | 2019-11-17 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPAPP | [7 empty] | Date Started: | 2019-11-17
Kapalong | Maniki | 1st Eng'g. Dist. | On-going | 2019-11-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPAPP | Post Harvest Facilities (Corn Mill, Solar Dryer, Corn Sheller), Kapalong, Davao del Norte |  | OPAPP-PAMANA CY 2018 | Building |  | sq.m | Admin | Project Cost: | 1500000 | Target Completion Date: | 2020-02-27 | Program: | 1500000 | Planned: | 100% | No. of Persons: | 7 | Completed as per physical accomplishment. Financial documents still on process.
Kapalong | Maniki | 1st Eng'g. Dist. | On-going | 2019-11-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPAPP | [7 empty] | Project Engineer: | Ambrosio | Revised Completion Date: | 2020-06-15 | Allotment: | 1500000 | Revised: |  | No. of Man-days: | 175
Kapalong | Maniki | 1st Eng'g. Dist. | On-going | 2019-11-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPAPP | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 1114654.45 | Actual: | 100%
Kapalong | Maniki | 1st Eng'g. Dist. | On-going | 2019-11-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPAPP | [7 empty] | Duration: | 101 | No. of days extended: | 82 |  |  | Slippage: | 0%
Kapalong | Maniki | 1st Eng'g. Dist. | On-going | 2019-11-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPAPP | [7 empty] | Date Allotment Released: | 2019-11-18 | Date completed: | 2020-06-15
Kapalong | Maniki | 1st Eng'g. Dist. | On-going | 2019-11-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPAPP | [7 empty] | Date Started: | 2019-11-18
Kapalong | Capungagan | 1st Eng'g. Dist. | On-going | 2019-11-25 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPAPP | Construction of PWS Level II in Purok 7-A and 7-B, Capungagan, Kapalong |  | OPAPP-PAMANA CY 2018 | Potable Water System |  |  | Admin | Project Cost: | 1760000 | Target Completion Date: | 2020-02-03 | Program: | 1760000 | Planned: | 100% | No. of Persons: | 25 | On-going (Suspended last April 5, 2020 due to COVID; resumption order dated May 4, 2020)
Kapalong | Capungagan | 1st Eng'g. Dist. | On-going | 2019-11-25 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPAPP | [7 empty] | Project Engineer: | Kabinge | Revised Completion Date: | 2020-04-15 | Allotment: | 1760000 | Revised: | 100% | No. of Man-days: | 375
Kapalong | Capungagan | 1st Eng'g. Dist. | On-going | 2019-11-25 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPAPP | [7 empty] | Implementor: | PEO | No. of days suspended: | 28 | Disbursement: | 1235344 | Actual: | 76.64%
Kapalong | Capungagan | 1st Eng'g. Dist. | On-going | 2019-11-25 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPAPP | [7 empty] | Duration: | 70 | No. of days extended: | 44 |  |  | Slippage: | -23.36%
Kapalong | Capungagan | 1st Eng'g. Dist. | On-going | 2019-11-25 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPAPP | [7 empty] | Date Allotment Released: | 2019-11-25 | Date completed:
Kapalong | Capungagan | 1st Eng'g. Dist. | On-going | 2019-11-25 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPAPP | [7 empty] | Date Started: | 2019-11-25
Kapalong | Pag-Asa | 1st Eng'g. Dist. | On-going | 2019-12-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPAPP | Construction of PWS Level II in Purok 2, Pag-Asa, kapalong |  | OPAPP-PAMANA CY 2018 | Potable Water System |  |  | Admin | Project Cost: | 2310000 | Target Completion Date: | 2020-04-09 | Program: | 2310000 | Planned: | 78% | No. of Persons: | 9 | On-going (Suspended last April 5, 2020 due to COVID; resumption order dated May 4, 2020)
Kapalong | Pag-Asa | 1st Eng'g. Dist. | On-going | 2019-12-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPAPP | [7 empty] | Project Engineer: | Dadula | Revised Completion Date: | 2020-06-21 | Allotment: | 2310000 | Revised: |  | No. of Man-days: | 138
Kapalong | Pag-Asa | 1st Eng'g. Dist. | On-going | 2019-12-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPAPP | [7 empty] | Implementor: | PEO | No. of days suspended: | 28 | Disbursement: | 1133886.6 | Actual: | 49.09%
Kapalong | Pag-Asa | 1st Eng'g. Dist. | On-going | 2019-12-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPAPP | [7 empty] | Duration: | 115 | No. of days extended: | 45 |  |  | Slippage: | -28.91%
Kapalong | Pag-Asa | 1st Eng'g. Dist. | On-going | 2019-12-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPAPP | [7 empty] | Date Allotment Released: | 2019-11-25 | Date completed:
Kapalong | Pag-Asa | 1st Eng'g. Dist. | On-going | 2019-12-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPAPP | [7 empty] | Date Started: | 2019-12-16
Kapalong | Semong | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPAPP | Cattle Production- Brgy. Tiburcia, Gupitan and Semong, Kapalong |  | OPAPP-PAMANA CY 2018 | Building |  | sq.m |  | Project Cost: | 1500000 | Target Completion Date: |  | Program: | 1500000 | Planned: |  | No. of Persons: |  | For cancellation. A letter was sent to OPAPP last Dec 2018 requesting to allow us to reduce the number of cattle but we are still hoping that there would be a supplier will bid
Kapalong | Semong | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPAPP | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 1500000 | Revised: |  | No. of Man-days:
Kapalong | Semong | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPAPP | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Kapalong | Semong | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPAPP | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Kapalong | Semong | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPAPP | [7 empty] | Date Allotment Released: |  | Date completed:
Kapalong | Semong | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPAPP | [7 empty] | Date Started:
Talaingod | Dagohoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPAPP | Cattle Production, Brgy. Palma Gil, Brgy. Sto. Nino, Brgy. Dagohoy, Talaingod, Davao del Norte |  | OPAPP-PAMANA CY 2018 | Building |  | sq.m |  | Project Cost: | 1500000 | Target Completion Date: |  | Program: | 1500000 | Planned: |  | No. of Persons: |  | For cancellation. A letter was sent to OPAPP last Dec 2018 requesting to allow us to reduce the number of cattle but we are still hoping that there would be a supplier will bid
Talaingod | Dagohoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPAPP | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 1500000 | Revised: |  | No. of Man-days:
Talaingod | Dagohoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPAPP | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Talaingod | Dagohoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPAPP | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Talaingod | Dagohoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPAPP | [7 empty] | Date Allotment Released: |  | Date completed:
Talaingod | Dagohoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPAPP | [7 empty] | Date Started:
Talaingod | Palma Gil | 1st Eng'g. Dist. | On-going | 2020-06-01 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPAPP | Rice Mill for Upland Rice, Palma Gil, Talaingod |  | OPAPP-PAMANA CY 2018 | Rice Mill |  |  | Admin | Project Cost: | 1000000 | Target Completion Date: | 2020-07-30 23:46 | Program: | 1000000 | Planned: | 8.07% | No. of Persons: | 6 | On-going
Talaingod | Palma Gil | 1st Eng'g. Dist. | On-going | 2020-06-01 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPAPP | [7 empty] | Project Engineer: | Torrecampo | Revised Completion Date: | 2020-07-30 23:46 | Allotment: | 1000000 | Revised: |  | No. of Man-days: | 90
Talaingod | Palma Gil | 1st Eng'g. Dist. | On-going | 2020-06-01 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPAPP | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: | 8.07%
Talaingod | Palma Gil | 1st Eng'g. Dist. | On-going | 2020-06-01 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPAPP | [7 empty] | Duration: | 60 | No. of days extended: |  |  |  | Slippage: | 0%
Talaingod | Palma Gil | 1st Eng'g. Dist. | On-going | 2020-06-01 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPAPP | [7 empty] | Date Allotment Released: |  | Date completed:
Talaingod | Palma Gil | 1st Eng'g. Dist. | On-going | 2020-06-01 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPAPP | [7 empty] | Date Started: | 2020-06-01
Kapalong | Mabantao-Florida | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | QRF | Rehab. Of Slope Protection of Libuganon River Along Kapalong - Mabantao - Florida Prov'l. Road Phase I |  | QRF CY 2016 | Slope Protection |  |  |  | Project Cost: | 900000 | Target Completion Date: |  | Program: | 900000 | Planned: |  | No. of Persons: |  | For AIP Amendment
Kapalong | Mabantao-Florida | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | QRF | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 900000 | Revised: |  | No. of Man-days:
Kapalong | Mabantao-Florida | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | QRF | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Kapalong | Mabantao-Florida | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | QRF | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Kapalong | Mabantao-Florida | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | QRF | [7 empty] | Date Allotment Released: |  | Date completed:
Kapalong | Mabantao-Florida | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | QRF | [7 empty] | Date Started:
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2019-11-04 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Ground Dev't. | Ground Development and landscape @ PDRRMD, Gov't. Center, Mankilam, Tagum City |  | LDRRMF 2018 | Ground Dev't. |  | sq.m | Admin | Project Cost: | 1000000 | Target Completion Date: | 2020-02-29 23:46 | Program: | 1000000 | Planned: | 75.24% | No. of Persons: | 8 | Suspended (Waiting for the complete delivery of materials) dated March 2, 2020
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2019-11-04 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Ground Dev't. | [7 empty] | Project Engineer: | Juan | Revised Completion Date: | 2020-02-29 23:46 | Allotment: | 1000000 | Revised: |  | No. of Man-days: | 152
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2019-11-04 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Ground Dev't. | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: | 752400 | Actual: | 75.24%
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2019-11-04 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Ground Dev't. | [7 empty] | Duration: | 118 | No. of days extended: |  |  |  | Slippage: | 0%
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2019-11-04 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Ground Dev't. | [7 empty] | Date Allotment Released: | 2019-03-19 | Date completed:
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2019-11-04 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Ground Dev't. | [7 empty] | Date Started: | 2019-11-04
Asuncion | Canatan-Doña Andrea | 1st Eng'g. Dist. | On-going | 2020-06-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL RAODS & BRIDGES LS - P41,465,029.00 | ROAD ID 007 - Jct. Highway Canatan - Doña Andrea |  | 20% DF CY 2019 | Road Rehabilitation | 4.34 | km | Admin | Project Cost: | 2000000 | Target Completion Date: | 2020-08-11 23:46 | Program: | 2000000 | Planned: | 31.77% | No. of Persons: |  | On-going
Asuncion | Canatan-Doña Andrea | 1st Eng'g. Dist. | On-going | 2020-06-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL RAODS & BRIDGES | [7 empty] | Project Engineer: | Pilotos | Revised Completion Date: | 2020-08-11 23:46 | Allotment: | 2000000 | Revised: |  | No. of Man-days:
Asuncion | Canatan-Doña Andrea | 1st Eng'g. Dist. | On-going | 2020-06-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL RAODS & BRIDGES LS - P41,465,029.00 | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: | 31.77%
Asuncion | Canatan-Doña Andrea | 1st Eng'g. Dist. | On-going | 2020-06-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL RAODS & BRIDGES LS - P41,465,029.00 | [7 empty] | Duration: | 57 | No. of days extended: |  |  |  | Slippage: | 0%
Asuncion | Canatan-Doña Andrea | 1st Eng'g. Dist. | On-going | 2020-06-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL RAODS & BRIDGES LS - P41,465,029.00 | [7 empty] | Date Allotment Released: | 2019-06-12 | Date completed:
Asuncion | Canatan-Doña Andrea | 1st Eng'g. Dist. | On-going | 2020-06-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL RAODS & BRIDGES LS - P41,465,029.00 | [7 empty] | Date Started: | 2020-06-16
Asuncion | Pamacaun | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL RAODS & BRIDGES LS - P41,465,029.00 | ROAD ID 015 - Pamacaun - Lasang Banate |  | 20% DF CY 2019 | Road Rehabilitation | 4.34 |  | Admin | Project Cost: | 2000000 | Target Completion Date: |  | Program: | 2000000 | Planned: |  | No. of Persons: |  | For implementation (Waiting for the delivery of geo-grid materials. An approved request letter dated Dec. 3, 2019 for the extension of 50 days from Provincial Administrator Engr. Rabanoz is on file
Asuncion | Pamacaun | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL RAODS & BRIDGES | [7 empty] | Project Engineer: | Gone | Revised Completion Date: | 0 | Allotment: | 2000000 | Revised: |  | No. of Man-days:
Asuncion | Pamacaun | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL RAODS & BRIDGES LS - P41,465,029.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Asuncion | Pamacaun | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL RAODS & BRIDGES LS - P41,465,029.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Asuncion | Pamacaun | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL RAODS & BRIDGES LS - P41,465,029.00 | [7 empty] | Date Allotment Released: | 2019-06-27 | Date completed:
Asuncion | Pamacaun | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL RAODS & BRIDGES LS - P41,465,029.00 | [7 empty] | Date Started:
Talaingod | Sto.Niño-Palma Gil | 1st Eng'g. Dist. | On-going | 2020-03-06 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL RAODS & BRIDGES LS - P41,465,029.00 | ROAD ID 019 - Sto. Niño - Palma Gil - Sitio Opao |  | 20% DF CY 2019 | Road Rehabilitation | 11.6 | km | Contract | Project Cost: | 1901000 | Target Completion Date: | 2020-04-18 23:46 | Program: | 1901000 | Planned: | 44.89% | No. of Persons: |  | On-going (Suspended dated March 14, 2020; Resumption Order dated May 25, 2020)
Talaingod | Sto.Niño-Palma Gil | 1st Eng'g. Dist. | On-going | 2020-03-06 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL RAODS & BRIDGES | [7 empty] | Project Engineer: | Lumapat | Revised Completion Date: | 2020-06-29 23:46 | Allotment: | 1901000 | Revised: |  | No. of Man-days:
Talaingod | Sto.Niño-Palma Gil | 1st Eng'g. Dist. | On-going | 2020-03-06 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL RAODS & BRIDGES LS - P41,465,029.00 | [7 empty] | Implementor: | Tagum Constrak | No. of days suspended: | 72 | Disbursement: |  | Actual: | 44.89%
Talaingod | Sto.Niño-Palma Gil | 1st Eng'g. Dist. | On-going | 2020-03-06 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL RAODS & BRIDGES LS - P41,465,029.00 | [7 empty] | Duration: | 44 | No. of days extended: |  |  |  | Slippage: | 0%
Talaingod | Sto.Niño-Palma Gil | 1st Eng'g. Dist. | On-going | 2020-03-06 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL RAODS & BRIDGES LS - P41,465,029.00 | [7 empty] | Date Allotment Released: | 2019-06-19 | Date completed:
Talaingod | Sto.Niño-Palma Gil | 1st Eng'g. Dist. | On-going | 2020-03-06 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL RAODS & BRIDGES LS - P41,465,029.00 | [7 empty] | Date Started: | 2020-03-06
Talaingod | Sto. Niño-Daligdigon-Paiton | 1st Eng'g. Dist. | On-going | 2020-01-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL RAODS & BRIDGES LS - P41,465,029.00 | ROAD ID 023 - Sto. Niño - Daligdigon - Paiton |  | 20% DF CY 2019 | Road Rehabilitation | 11.6 | km | Contract | Project Cost: | 3000000 | Target Completion Date: | 2020-05-14 23:46 | Program: | 3000000 | Planned: | 2.19% | No. of Persons: |  | On-going; Resumption Order dated May 4, 2020
Talaingod | Sto. Niño-Daligdigon-Paiton | 1st Eng'g. Dist. | On-going | 2020-01-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL RAODS & BRIDGES | [7 empty] | Project Engineer: | Lumapat | Revised Completion Date: |  | Allotment: | 3000000 | Revised: |  | No. of Man-days:
Talaingod | Sto. Niño-Daligdigon-Paiton | 1st Eng'g. Dist. | On-going | 2020-01-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL RAODS & BRIDGES LS - P41,465,029.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: | 119400 | Actual: | 3.98%
Talaingod | Sto. Niño-Daligdigon-Paiton | 1st Eng'g. Dist. | On-going | 2020-01-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL RAODS & BRIDGES LS - P41,465,029.00 | [7 empty] | Duration: | 120 | No. of days extended: |  |  |  | Slippage: | 1.79%
Talaingod | Sto. Niño-Daligdigon-Paiton | 1st Eng'g. Dist. | On-going | 2020-01-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL RAODS & BRIDGES LS - P41,465,029.00 | [7 empty] | Date Allotment Released: | 2019-10-03 | Date completed:
Talaingod | Sto. Niño-Daligdigon-Paiton | 1st Eng'g. Dist. | On-going | 2020-01-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL RAODS & BRIDGES LS - P41,465,029.00 | [7 empty] | Date Started: | 2020-01-16
Talaingod | Jct. Paiton-Mibolo | 1st Eng'g. Dist. | On-going | 2019-08-01 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL RAODS & BRIDGES LS - P41,465,029.00 | ROAD ID 024 - Jct. Paiton - Mibolo |  | 20% DF CY 2019 | Road Rehabilitation | 23.9 | km | Contract | Project Cost: | 6000000 | Target Completion Date: | 2020-03-15 23:46 | Program: | 6000000 | Planned: | 21.05% | No. of Persons: |  | Temporary suspended because the materials for the box culvert procurement on process wth PO # 2019061674
Talaingod | Jct. Paiton-Mibolo | 1st Eng'g. Dist. | On-going | 2019-08-01 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL RAODS & BRIDGES | [7 empty] | Project Engineer: | Lumapat | Revised Completion Date: |  | Allotment: | 6000000 | Revised: |  | No. of Man-days:
Talaingod | Jct. Paiton-Mibolo | 1st Eng'g. Dist. | On-going | 2019-08-01 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL RAODS & BRIDGES LS - P41,465,029.00 | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: | 1263000 | Actual: | 21.05%
Talaingod | Jct. Paiton-Mibolo | 1st Eng'g. Dist. | On-going | 2019-08-01 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL RAODS & BRIDGES LS - P41,465,029.00 | [7 empty] | Duration: | 228 | No. of days extended: |  |  |  | Slippage: | 0%
Talaingod | Jct. Paiton-Mibolo | 1st Eng'g. Dist. | On-going | 2019-08-01 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL RAODS & BRIDGES LS - P41,465,029.00 | [7 empty] | Date Allotment Released: | 2019-03-25 | Date completed:
Talaingod | Jct. Paiton-Mibolo | 1st Eng'g. Dist. | On-going | 2019-08-01 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL RAODS & BRIDGES LS - P41,465,029.00 | [7 empty] | Date Started: | 2019-08-01
Talaingod | Monte Dujali-Gupitan | 1st Eng'g. Dist. | On-going | 2020-01-31 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL RAODS & BRIDGES LS - P41,465,029.00 | ROAD ID 037 - Monte Dujali - Gupitan |  | 20% DF CY 2019 | Road Rehabilitation | 4.58 | km | Admin | Project Cost: | 1200000 | Target Completion Date: | 2020-03-31 23:46 | Program: | 1200000 | Planned: | 100% | No. of Persons: | 10 | Completed as per physical accomplishment. Financial documents still on process.
Talaingod | Monte Dujali-Gupitan | 1st Eng'g. Dist. | On-going | 2020-01-31 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL RAODS & BRIDGES | [7 empty] | Project Engineer: | Bacaron | Revised Completion Date: | 2020-06-30 23:46 | Allotment: | 1200000 | Revised: |  | No. of Man-days: | 240
Talaingod | Monte Dujali-Gupitan | 1st Eng'g. Dist. | On-going | 2020-01-31 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL RAODS & BRIDGES LS - P41,465,029.00 | [7 empty] | Implementor: | PEO | No. of days suspended: | 30 | Disbursement: | 485400 | Actual: | 100%
Talaingod | Monte Dujali-Gupitan | 1st Eng'g. Dist. | On-going | 2020-01-31 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL RAODS & BRIDGES LS - P41,465,029.00 | [7 empty] | Duration: | 61 | No. of days extended: | 61 |  |  | Slippage: | 0%
Talaingod | Monte Dujali-Gupitan | 1st Eng'g. Dist. | On-going | 2020-01-31 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL RAODS & BRIDGES LS - P41,465,029.00 | [7 empty] | Date Allotment Released: | 2019-12-06 | Date completed:
Talaingod | Monte Dujali-Gupitan | 1st Eng'g. Dist. | On-going | 2020-01-31 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL RAODS & BRIDGES LS - P41,465,029.00 | [7 empty] | Date Started: | 2020-01-31
New Corella | San Juan-New Talisay | 1st Eng'g. Dist. | On-going | 2019-11-04 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS OF LOCAL ROADS & DRAINAGE DEVELOPMENT PROJECT(Provincewide) LS - 15,000,000.00 | Rehab./Impv't. of San Juan-New Talisay Provincial Road with Drainage |  | 20% DF CY 2019 | Road Drainage rehabiliated |  | km | Admin | Project Cost: | 1000000 | Target Completion Date: | 2019-12-18 | Program: | 1000000 | Planned: | 57.41% | No. of Persons: |  | Suspended dated December 18, 2019 due to revision of POW
New Corella | San Juan-New Talisay | 1st Eng'g. Dist. | On-going | 2019-11-04 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS OF LOCAL ROADS & DRAINAGE DEVELOPMENT PROJECT(Provincewide) LS - 15,000,000.00 | [7 empty] | Project Engineer: | Pilotos | Revised Completion Date: | 2019-12-18 | Allotment: | 1000000 | Revised: |  | No. of Man-days:
New Corella | San Juan-New Talisay | 1st Eng'g. Dist. | On-going | 2019-11-04 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS OF LOCAL ROADS & DRAINAGE DEVELOPMENT PROJECT(Provincewide) LS - 15,000,000.00 | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: | 74.11%
New Corella | San Juan-New Talisay | 1st Eng'g. Dist. | On-going | 2019-11-04 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS OF LOCAL ROADS & DRAINAGE DEVELOPMENT PROJECT(Provincewide) LS - 15,000,000.00 | [7 empty] | Duration: | 44 | No. of days extended: |  |  |  | Slippage: | 16.7%
New Corella | San Juan-New Talisay | 1st Eng'g. Dist. | On-going | 2019-11-04 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS OF LOCAL ROADS & DRAINAGE DEVELOPMENT PROJECT(Provincewide) LS - 15,000,000.00 | [7 empty] | Date Allotment Released: | 2019-01-31 | Date completed:
New Corella | San Juan-New Talisay | 1st Eng'g. Dist. | On-going | 2019-11-04 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS OF LOCAL ROADS & DRAINAGE DEVELOPMENT PROJECT(Provincewide) LS - 15,000,000.00 | [7 empty] | Date Started: | 2019-11-04
Kapalong | Suaon-Libuton | 1st Eng'g. Dist. | On-going | 2019-11-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS OF LOCAL ROADS & DRAINAGE DEVELOPMENT PROJECT(Provincewide) LS - 15,000,000.00 | Repair/Rehab. Of Concrete Road Jct. Suaon-Libuton, Kapalong |  | 20% DF CY 2019 | Road Drainage rehabiliated |  | km | Admin | Project Cost: | 1000000 | Target Completion Date: | 2020-02-15 23:46 | Program: | 1000000 | Planned: | 14.73% | No. of Persons: |  | Suspended dated March 30, 2020 due to availability of equipment
Kapalong | Suaon-Libuton | 1st Eng'g. Dist. | On-going | 2019-11-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS OF LOCAL ROADS & DRAINAGE DEVELOPMENT PROJECT(Provincewide) LS - 15,000,000.00 | [7 empty] | Project Engineer: | Bacaron | Revised Completion Date: |  | Allotment: | 1000000 | Revised: |  | No. of Man-days:
Kapalong | Suaon-Libuton | 1st Eng'g. Dist. | On-going | 2019-11-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS OF LOCAL ROADS & DRAINAGE DEVELOPMENT PROJECT(Provincewide) LS - 15,000,000.00 | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: | 14.2%
Kapalong | Suaon-Libuton | 1st Eng'g. Dist. | On-going | 2019-11-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS OF LOCAL ROADS & DRAINAGE DEVELOPMENT PROJECT(Provincewide) LS - 15,000,000.00 | [7 empty] | Duration: | 90 | No. of days extended: |  |  |  | Slippage: | -0.53%
Kapalong | Suaon-Libuton | 1st Eng'g. Dist. | On-going | 2019-11-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS OF LOCAL ROADS & DRAINAGE DEVELOPMENT PROJECT(Provincewide) LS - 15,000,000.00 | [7 empty] | Date Allotment Released: | 2019-03-12 | Date completed:
Kapalong | Suaon-Libuton | 1st Eng'g. Dist. | On-going | 2019-11-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS OF LOCAL ROADS & DRAINAGE DEVELOPMENT PROJECT(Provincewide) LS - 15,000,000.00 | [7 empty] | Date Started: | 2019-11-18
Asuncion | Saug-Sonlon Longanapan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS OF LOCAL ROADS & DRAINAGE DEVELOPMENT PROJECT(Provincewide) LS - 15,000,000.00 | Impv't. of Cross Drainage along Saug-Sonlon-Bdry. Longanapan |  | 20% DF CY 2019 | Road Drainage rehabiliated |  | ln.m | Admin | Project Cost: | 3000000 | Target Completion Date: |  | Program: | 3000000 | Planned: |  | No. of Persons: |  | For implementation
Asuncion | Saug-Sonlon Longanapan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS OF LOCAL ROADS & DRAINAGE DEVELOPMENT PROJECT(Provincewide) LS - 15,000,000.00 | [7 empty] | Project Engineer: | Pilotos | Revised Completion Date: | 0 | Allotment: | 3000000 | Revised: |  | No. of Man-days:
Asuncion | Saug-Sonlon Longanapan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS OF LOCAL ROADS & DRAINAGE DEVELOPMENT PROJECT(Provincewide) LS - 15,000,000.00 | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual:
Asuncion | Saug-Sonlon Longanapan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS OF LOCAL ROADS & DRAINAGE DEVELOPMENT PROJECT(Provincewide) LS - 15,000,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Asuncion | Saug-Sonlon Longanapan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS OF LOCAL ROADS & DRAINAGE DEVELOPMENT PROJECT(Provincewide) LS - 15,000,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Asuncion | Saug-Sonlon Longanapan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS OF LOCAL ROADS & DRAINAGE DEVELOPMENT PROJECT(Provincewide) LS - 15,000,000.00 | [7 empty] | Date Started:
Talaingod | Sto. Niño-Palma Gil | 1st Eng'g. Dist. | On-going | 2020-02-27 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS OF LOCAL ROADS & DRAINAGE DEVELOPMENT PROJECT(Provincewide) LS - 15,000,000.00 | Rehab./Impv't. of Sto. Niño-Palma Gil-Sitio Opao Provincial Road with Drainage |  | 20% DF CY 2019 | Road Drainage rehabiliated |  | km | Contract | Project Cost: | 3000000 | Target Completion Date: | 2020-05-07 | Program: | 3000000 | Planned: | 44.89% | No. of Persons: |  | On-going (Suspended dated March 14, 2020; Resumption Order dated May 25, 2020)
Talaingod | Sto. Niño-Palma Gil | 1st Eng'g. Dist. | On-going | 2020-02-27 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS OF LOCAL ROADS & DRAINAGE DEVELOPMENT PROJECT(Provincewide) LS - 15,000,000.00 | [7 empty] | Project Engineer: | Lumapat | Revised Completion Date: | 2020-07-17 | Allotment: | 3000000 | Revised: |  | No. of Man-days:
Talaingod | Sto. Niño-Palma Gil | 1st Eng'g. Dist. | On-going | 2020-02-27 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS OF LOCAL ROADS & DRAINAGE DEVELOPMENT PROJECT(Provincewide) LS - 15,000,000.00 | [7 empty] | Implementor: | Tagum Constrak | No. of days suspended: | 71 | Disbursement: |  | Actual: | 44.89%
Talaingod | Sto. Niño-Palma Gil | 1st Eng'g. Dist. | On-going | 2020-02-27 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS OF LOCAL ROADS & DRAINAGE DEVELOPMENT PROJECT(Provincewide) LS - 15,000,000.00 | [7 empty] | Duration: | 70 | No. of days extended: |  |  |  | Slippage: | 0%
Talaingod | Sto. Niño-Palma Gil | 1st Eng'g. Dist. | On-going | 2020-02-27 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS OF LOCAL ROADS & DRAINAGE DEVELOPMENT PROJECT(Provincewide) LS - 15,000,000.00 | [7 empty] | Date Allotment Released: | 2019-05-25 | Date completed:
Talaingod | Sto. Niño-Palma Gil | 1st Eng'g. Dist. | On-going | 2020-02-27 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS OF LOCAL ROADS & DRAINAGE DEVELOPMENT PROJECT(Provincewide) LS - 15,000,000.00 | [7 empty] | Date Started: | 2020-02-27
San Isidro | Linao | 1st Eng'g. Dist. | On-going | 2020-02-24 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS WATER SYSTEM DEVELOPMENT LS - P 9,750,000.00 | Construction of PWS, Bgry. Linao, San Isidro |  | 20% DF CY 2019 | Water System |  | ln.m | Admin | Project Cost: | 500000 | Target Completion Date: | 2020-04-23 23:46 | Program: | 500000 | Planned: | 99% | No. of Persons: | 8 | On-going (Suspended last April 5, 2020 due to COVID; resumption order dated May 4, 2020)
San Isidro | Linao | 1st Eng'g. Dist. | On-going | 2020-02-24 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS WATER SYSTEM DEVELOPMENT LS - P 9,750,000.00 | [7 empty] | Project Engineer: | Aclaracion | Revised Completion Date: | 2020-07-05 23:46 | Allotment: | 500000 | Revised: |  | No. of Man-days: | 120
San Isidro | Linao | 1st Eng'g. Dist. | On-going | 2020-02-24 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS WATER SYSTEM DEVELOPMENT LS - P 9,750,000.00 | [7 empty] | Implementor: | PEO | No. of days suspended: | 73 | Disbursement: | 216100 | Actual: | 99%
San Isidro | Linao | 1st Eng'g. Dist. | On-going | 2020-02-24 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS WATER SYSTEM DEVELOPMENT LS - P 9,750,000.00 | [7 empty] | Duration: | 60 | No. of days extended: |  |  |  | Slippage: | 0%
San Isidro | Linao | 1st Eng'g. Dist. | On-going | 2020-02-24 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS WATER SYSTEM DEVELOPMENT LS - P 9,750,000.00 | [7 empty] | Date Allotment Released: | 2019-06-19 | Date completed:
San Isidro | Linao | 1st Eng'g. Dist. | On-going | 2020-02-24 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS WATER SYSTEM DEVELOPMENT LS - P 9,750,000.00 | [7 empty] | Date Started: | 2020-02-24
San Isidro | Datu Balong | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS WATER SYSTEM DEVELOPMENT LS - P 9,750,000.00 | Construction of PWS, Brgy. Datu Balong, San Isidro |  | 20% DF CY 2019 | Water System |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | For declaration of savings because the spring water source is not feasible for development
San Isidro | Datu Balong | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS WATER SYSTEM DEVELOPMENT LS - P 9,750,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 500000 | Revised: |  | No. of Man-days:
San Isidro | Datu Balong | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS WATER SYSTEM DEVELOPMENT LS - P 9,750,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
San Isidro | Datu Balong | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS WATER SYSTEM DEVELOPMENT LS - P 9,750,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
San Isidro | Datu Balong | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS WATER SYSTEM DEVELOPMENT LS - P 9,750,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
San Isidro | Datu Balong | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS WATER SYSTEM DEVELOPMENT LS - P 9,750,000.00 | [7 empty] | Date Started:
San Isidro | Sagayen | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS WATER SYSTEM DEVELOPMENT LS - P 9,750,000.00 | Construction of PWS, Brgy. Sagayen, San Isidro |  | 20% DF CY 2019 | Water System |  |  | Contract | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | PO # 2020031340 - JJR Construction
San Isidro | Sagayen | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS WATER SYSTEM DEVELOPMENT LS - P 9,750,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 500000 | Revised: |  | No. of Man-days:
San Isidro | Sagayen | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS WATER SYSTEM DEVELOPMENT LS - P 9,750,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
San Isidro | Sagayen | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS WATER SYSTEM DEVELOPMENT LS - P 9,750,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
San Isidro | Sagayen | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS WATER SYSTEM DEVELOPMENT LS - P 9,750,000.00 | [7 empty] | Date Allotment Released: | 2019-09-10 | Date completed:
San Isidro | Sagayen | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS WATER SYSTEM DEVELOPMENT LS - P 9,750,000.00 | [7 empty] | Date Started:
Tagum City | Mankilam | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS WATER SYSTEM DEVELOPMENT LS - P 9,750,000.00 | Installation of Shallow Tube Wells & Const. of Machinery Shed |  | 20% DF CY 2019 | Water System |  |  | Admin | Project Cost: | 1600000 | Target Completion Date: |  | Program: | 1600000 | Planned: |  | No. of Persons: |  | Opening of BID for Negotiated 6/18,2020 to alpebel
Tagum City | Mankilam | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS WATER SYSTEM DEVELOPMENT LS - P 9,750,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 1600000 | Revised: |  | No. of Man-days:
Tagum City | Mankilam | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS WATER SYSTEM DEVELOPMENT LS - P 9,750,000.00 | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual:
Tagum City | Mankilam | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS WATER SYSTEM DEVELOPMENT LS - P 9,750,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Tagum City | Mankilam | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS WATER SYSTEM DEVELOPMENT LS - P 9,750,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Tagum City | Mankilam | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS WATER SYSTEM DEVELOPMENT LS - P 9,750,000.00 | [7 empty] | Date Started:
New Corella | Poblacion | 1st Eng'g. Dist. | On-going | 2020-03-02 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | Repair/Impv't. of Municipal Triball Hall, New Corella |  | 20% DF CY 2019 | Building |  | sq.m | Admin | Project Cost: | 1500000 | Target Completion Date: | 2020-06-12 23:46 | Program: | 1500000 | Planned: | 66.4% | No. of Persons: | 12 | On-going (Suspended last April 5, 2020 due to COVID; resumption order dated May 4, 2020)
New Corella | Poblacion | 1st Eng'g. Dist. | On-going | 2020-03-02 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | [7 empty] | Project Engineer: | Cahayag | Revised Completion Date: | 2020-07-10 23:46 | Allotment: | 1500000 | Revised: |  | No. of Man-days: | 180
New Corella | Poblacion | 1st Eng'g. Dist. | On-going | 2020-03-02 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | [7 empty] | Implementor: | PEO | No. of days suspended: | 28 | Disbursement: |  | Actual: | 47.31%
New Corella | Poblacion | 1st Eng'g. Dist. | On-going | 2020-03-02 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | [7 empty] | Duration: | 103 | No. of days extended: |  |  |  | Slippage: | -19.09%
New Corella | Poblacion | 1st Eng'g. Dist. | On-going | 2020-03-02 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
New Corella | Poblacion | 1st Eng'g. Dist. | On-going | 2020-03-02 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | [7 empty] | Date Started: | 2020-03-02
San Isidro | Sabangan | 1st Eng'g. Dist. | On-going | 2019-12-02 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | Const. of Municipal Tribal Hall, San Isidro |  | 20% DF CY 2019 | Building | 42 | sq.m | Admin | Project Cost: | 500000 | Target Completion Date: | 2020-02-19 23:46 | Program: | 500000 | Planned: | 81.44% | No. of Persons: | 8 | Completed as per physical accomplishment. Financial documents still on process.
San Isidro | Sabangan | 1st Eng'g. Dist. | On-going | 2019-12-02 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | [7 empty] | Project Engineer: | Aclaracion | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days: | 176
San Isidro | Sabangan | 1st Eng'g. Dist. | On-going | 2019-12-02 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | [7 empty] | Implementor: | PEO | No. of days suspended: | 28 | Disbursement: |  | Actual: | 81.44%
San Isidro | Sabangan | 1st Eng'g. Dist. | On-going | 2019-12-02 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | [7 empty] | Duration: | 80 | No. of days extended: |  |  |  | Slippage: | 0%
San Isidro | Sabangan | 1st Eng'g. Dist. | On-going | 2019-12-02 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | [7 empty] | Date Allotment Released: | 2019-01-15 | Date completed: | 2020-06-15
San Isidro | Sabangan | 1st Eng'g. Dist. | On-going | 2019-12-02 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | [7 empty] | Date Started: | 2019-12-02
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2019-12-02 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | Repair Bay of Disaster Quick Response Equipment @ PEO Compound, Gov't. Center, Mankilam, Tagum City |  | 20% DF CY 2019 | Building | 66 | sq.m | Admin | Project Cost: | 1000000 | Target Completion Date: | 2020-04-19 23:46 | Program: | 1000000 | Planned: | 74.7% | No. of Persons: | 5 | On-going (Suspended last April 5, 2020 due to COVID; resumption order dated May 4, 2020)
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2019-12-02 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | [7 empty] | Project Engineer: | Chua/Mucas | Revised Completion Date: | 2020-05-17 23:46 | Allotment: | 1000000 | Revised: |  | No. of Man-days: | 95
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2019-12-02 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | [7 empty] | Implementor: | PEO | No. of days suspended: | 28 | Disbursement: |  | Actual: | 74.7%
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2019-12-02 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | [7 empty] | Duration: | 140 | No. of days extended: |  |  |  | Slippage: | 0%
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2019-12-02 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | [7 empty] | Date Allotment Released: | 2019-01-31 | Date completed:
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2019-12-02 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | [7 empty] | Date Started: | 2019-12-02
Talaingod | Gupitan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | Const. of Multi-Purpose Hall Center (Cultural Heritage in Ancestral Domain of Ata-Manobo) |  | 20% DF CY 2019 | Building |  |  | Admin | Project Cost: | 3000000 | Target Completion Date: |  | Program: | 3000000 | Planned: |  | No. of Persons: |  | Fund re-aligned to GIDAS projects
Talaingod | Gupitan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 3000000 | Revised: |  | No. of Man-days:
Talaingod | Gupitan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Talaingod | Gupitan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Talaingod | Gupitan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Talaingod | Gupitan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | [7 empty] | Date Started:
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | Const. of IP Women's Multi-{Purpose Bldg.), Cabidiangan, Sto. Niño, Talaingod |  | 20% DF CY 2019 | Building |  |  | Admin | Project Cost: | 2000000 | Target Completion Date: |  | Program: | 2000000 | Planned: |  | No. of Persons: |  | Final abstract #0320200897 (Alpebel Builders)
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 2000000 | Revised: |  | No. of Man-days:
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual:
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | [7 empty] | Date Allotment Released: | 2019-05-15 | Date completed:
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | [7 empty] | Date Started:
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2020-02-03 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | Extension of PAGRO Training Center & Ground Dev't., Gov't. Center, Mankilam, Tagum City |  | 20% DF CY 2019 | Building |  | sq.m | Admin | Project Cost: | 1000000 | Target Completion Date: | 2020-04-23 | Program: | 1000000 | Planned: | 30.5% | No. of Persons: | 5 | On-going (Suspended last April 5, 2020 due to COVID; resumption order dated May 4, 2020)
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2020-02-03 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | [7 empty] | Project Engineer: | Chua/Mugas | Revised Completion Date: | 2020-05-21 | Allotment: | 1000000 | Revised: |  | No. of Man-days: | 57
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2020-02-03 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | [7 empty] | Implementor: | PEO | No. of days suspended: | 28 | Disbursement: |  | Actual: | 30.5%
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2020-02-03 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | [7 empty] | Duration: | 80 | No. of days extended: |  |  |  | Slippage: | 0%
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2020-02-03 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | [7 empty] | Date Allotment Released: | 2019-07-26 | Date completed:
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2020-02-03 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | [7 empty] | Date Started: | 2020-02-03
Tagum City | Mankilam | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | Construction of Abilidad Training Center, Gov't. Center, Mankilam, Tagum City |  | 20% DF CY 2019 | Building |  |  |  | Project Cost: | 7000000 | Target Completion Date: |  | Program: | 7000000 | Planned: |  | No. of Persons: |  | Fund re-aligned to GIDAS projects
Tagum City | Mankilam | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 7000000 | Revised: |  | No. of Man-days:
Tagum City | Mankilam | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual:
Tagum City | Mankilam | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Tagum City | Mankilam | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Tagum City | Mankilam | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | [7 empty] | Date Started:
New Corella | Suawon | 1st Eng'g. Dist. | On-going | 2019-12-09 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | Const. of 1 CL Bldg. @ Suawon ES, New Corella |  | 20% DF CY 2019 | Building | 82.65 | sq.m | Admin | Project Cost: | 1000000 | Target Completion Date: | 2020-04-21 23:46 | Program: | 1000000 | Planned: | 60.44% | No. of Persons: | 7 | On-going (Suspended last April 5, 2020 due to COVID; resumption order dated May 4, 2020)
New Corella | Suawon | 1st Eng'g. Dist. | On-going | 2019-12-09 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | [7 empty] | Project Engineer: | Miraflor | Revised Completion Date: | 2020-05-19 23:46 | Allotment: | 1000000 | Revised: |  | No. of Man-days: | 147
New Corella | Suawon | 1st Eng'g. Dist. | On-going | 2019-12-09 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | [7 empty] | Implementor: | PEO | No. of days suspended: | 28 | Disbursement: |  | Actual: | 60.44%
New Corella | Suawon | 1st Eng'g. Dist. | On-going | 2019-12-09 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | [7 empty] | Duration: | 135 | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | Suawon | 1st Eng'g. Dist. | On-going | 2019-12-09 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | [7 empty] | Date Allotment Released: | 2020-06-07 | Date completed:
New Corella | Suawon | 1st Eng'g. Dist. | On-going | 2019-12-09 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | [7 empty] | Date Started: | 2019-12-09
Talaingod | STo. Niño | 1st Eng'g. Dist. | On-going | 2020-03-02 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | Const. of Perimeter Fence at Sto. Niño Naseco Integrated School w/ Tugas Extension, Sto. Niño, Talaingod |  | 20% DF CY 2019 | Building |  | sq.m | Admin | Project Cost: | 2000000 | Target Completion Date: | 2020-06-09 23:46 | Program: | 2000000 | Planned: | 87.65% | No. of Persons: | 13 | On-going (Suspended last April 5, 2020 due to COVID; resumption order dated May 4, 2020)
Talaingod | STo. Niño | 1st Eng'g. Dist. | On-going | 2020-03-02 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | [7 empty] | Project Engineer: | Torrecampo | Revised Completion Date: | 2020-07-07 23:46 | Allotment: | 2000000 | Revised: |  | No. of Man-days: | 195
Talaingod | STo. Niño | 1st Eng'g. Dist. | On-going | 2020-03-02 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | [7 empty] | Implementor: | PEO | No. of days suspended: | 28 | Disbursement: |  | Actual: | 40.65%
Talaingod | STo. Niño | 1st Eng'g. Dist. | On-going | 2020-03-02 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | [7 empty] | Duration: | 100 | No. of days extended: |  |  |  | Slippage: | -47%
Talaingod | STo. Niño | 1st Eng'g. Dist. | On-going | 2020-03-02 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | [7 empty] | Date Allotment Released: | 2019-06-19 | Date completed:
Talaingod | STo. Niño | 1st Eng'g. Dist. | On-going | 2020-03-02 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | [7 empty] | Date Started: | 2020-03-02
Asuncion | New Bantayan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | Rehab. Of Multi-Purpose Hall, New Bantayan, Asuncion |  | 20% DF CY 2019 (STIMULUS) | Building |  |  | Admin | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | (Fund transferred to LGU.c /o Engr. Lilibeth Cuajao)
Asuncion | New Bantayan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 500000 | Revised: |  | No. of Man-days:
Asuncion | New Bantayan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Asuncion | New Bantayan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Asuncion | New Bantayan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Allotment Released: |  | Date completed:
Asuncion | New Bantayan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Started:
New Corella | El Salvador | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | Construction of Multi-Purpose Hall, El Salvador, New Corella |  | 20% DF CY 2019 (STIMULUS) | Building |  |  | MLGU | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Fund transferred to LGU March 23, 2019 c/o Engr. Dugoldugol
New Corella | El Salvador | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 500000 | Revised: |  | No. of Man-days:
New Corella | El Salvador | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
New Corella | El Salvador | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | El Salvador | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Allotment Released: |  | Date completed:
New Corella | El Salvador | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Started:
New Corella | Poblacion | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | Concreting of Drainage Canal , Pob., New Corella |  | 20% DF CY 2019 (STIMULUS) | Drainage |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Amended to Const. of 2 Storey Multi-Purpose Hall phase 3 (Brgy. Hall),Pob., New Corella (AIP 3rd revision CY 2019 / SB No. 4 CY 2019
New Corella | Poblacion | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 500000 | Revised: |  | No. of Man-days:
New Corella | Poblacion | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
New Corella | Poblacion | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | Poblacion | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Allotment Released: |  | Date completed:
New Corella | Poblacion | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Started:
New Corella | Cabidianan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | Rehab. Of Multi-Purpose Hall, Cabidianan, New Corella |  | 20% DF CY 2019 (STIMULUS) | Building |  |  | MLGU | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Fund transferred to LGU c/o Engr. Dugoldugol
New Corella | Cabidianan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 500000 | Revised: |  | No. of Man-days:
New Corella | Cabidianan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
New Corella | Cabidianan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | Cabidianan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Allotment Released: | 2019-02-20 | Date completed:
New Corella | Cabidianan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Started:
Talaingod | Gupitan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | Brgy. Electrification (Centro Gupitan), Gupitan, Talaingod |  | 20% DF CY 2019 (STIMULUS) | Electrification |  |  | MLGU | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Re-aligned to other stimulus projects that need additional funds to complete since the amount can not complete the project. Recommended for exact fund that can complete the project.
Talaingod | Gupitan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 500000 | Revised: |  | No. of Man-days:
Talaingod | Gupitan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Talaingod | Gupitan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Talaingod | Gupitan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Allotment Released: |  | Date completed:
Talaingod | Gupitan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Started:
Tagum City | Magugpo Poblacion | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | Rehab. of Evacuation Center, Magugpo Poblacion, Tagum City |  | 20% DF CY 2019 (STIMULUS) | Building |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Amended in the AIP 3rd revision CY 2019 /SB No. 4 CY 2019 changing the total project cost to P600,000.00
Tagum City | Magugpo Poblacion | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 500000 | Revised: |  | No. of Man-days:
Tagum City | Magugpo Poblacion | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Tagum City | Magugpo Poblacion | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Tagum City | Magugpo Poblacion | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Allotment Released: |  | Date completed:
Tagum City | Magugpo Poblacion | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Started:
Tagum City | San Agustin | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | Const. of Water System, San Agustin, Tagum City |  | 20% DF CY 2019 (STIMULUS) | Water System |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Re-aligned to other stimulus projects that need additional funds since there is no deed of donation for the proposed site.
Tagum City | San Agustin | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 500000 | Revised: |  | No. of Man-days:
Tagum City | San Agustin | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Tagum City | San Agustin | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Tagum City | San Agustin | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Allotment Released: |  | Date completed:
Tagum City | San Agustin | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Started:
Tagum City | Magugpo South | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | Const. of Brgy. Health Center, Magugpo South, Tagum City |  | 20% DF CY 2019 (STIMULUS) | Building |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Amended in the AIP 3rd revision CY 2019 /SB No. 4 CY 2019 changing the total project cost to P1,550,000.00
Tagum City | Magugpo South | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 500000 | Revised: |  | No. of Man-days:
Tagum City | Magugpo South | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Tagum City | Magugpo South | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Tagum City | Magugpo South | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Allotment Released: |  | Date completed:
Tagum City | Magugpo South | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Started:
Tagum City | Apokon | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | Rehab. Of Brgy. Health Center, Apokon, Tagum City |  | 20% DF CY 2019 (STIMULUS) | Building |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | For implementation (The brgy. council agreed not to pursue with the project if it will not be completed and needs additional funds)
Tagum City | Apokon | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 500000 | Revised: |  | No. of Man-days:
Tagum City | Apokon | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Tagum City | Apokon | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Tagum City | Apokon | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Allotment Released: | 2019-03-25 | Date completed:
Tagum City | Apokon | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Started:
Tagum City | Mankilam | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | Rehab. of Evacuation Center, Mankilam, Tagum City |  | 20% DF CY 2019 (STIMULUS) | Building |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | For implementation
Tagum City | Mankilam | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 500000 | Revised: |  | No. of Man-days:
Tagum City | Mankilam | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Tagum City | Mankilam | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Tagum City | Mankilam | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Allotment Released: | 2019-03-25 | Date completed:
Tagum City | Mankilam | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Started:
Tagum City | New Balamban | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | Rehab. of Evacuation Center, New Balambam, Tagum City |  | 20% DF CY 2019 (STIMULUS) | Building |  |  | Contract | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Final abstract #0320200899 (JJR Construction & Supply)
Tagum City | New Balamban | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 500000 | Revised: |  | No. of Man-days:
Tagum City | New Balamban | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Tagum City | New Balamban | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Tagum City | New Balamban | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Allotment Released: | 2019-09-10 | Date completed:
Tagum City | New Balamban | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Started:
Tagum City | Cuambogan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | Rehab. Of Multi-Purpose Hall, Cuambogan, Tagum City |  | 20% DF CY 2019 (STIMULUS) | Building |  |  | Contract | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | PO #2020031340 - JJR Construction
Tagum City | Cuambogan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 500000 | Revised: |  | No. of Man-days:
Tagum City | Cuambogan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Tagum City | Cuambogan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Tagum City | Cuambogan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Allotment Released: | 2019-09-10 | Date completed:
Tagum City | Cuambogan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Started:
Tagum City | Nueva Fuerza | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | Completion of Evacuation Center, Nueva Fuerza, Tagum City |  | 20% DF CY 2019 (STIMULUS) | Building |  |  | Contract | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | PO #2020031340 - JJR Construction
Tagum City | Nueva Fuerza | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 500000 | Revised: |  | No. of Man-days:
Tagum City | Nueva Fuerza | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Tagum City | Nueva Fuerza | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Tagum City | Nueva Fuerza | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Allotment Released: | 2019-09-10 | Date completed:
Tagum City | Nueva Fuerza | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Started:
Tagum City | Busaon | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | Completion. of Water System , Busaon, Tagum City |  | 20% DF CY 2019 (STIMULUS) | Water System |  |  | Contract | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | For implementation
Tagum City | Busaon | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 500000 | Revised: |  | No. of Man-days:
Tagum City | Busaon | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Tagum City | Busaon | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Tagum City | Busaon | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Allotment Released: | 2019-09-10 | Date completed:
Tagum City | Busaon | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Started:
Tagum City | Bincungan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | Const. of Drainage Canal, Bincungan, Tagum City |  | 20% DF CY 2019 (STIMULUS) | Drainage |  |  | Contract | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | PO #2020031340 - JJR Construction
Tagum City | Bincungan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 500000 | Revised: |  | No. of Man-days:
Tagum City | Bincungan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Tagum City | Bincungan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Tagum City | Bincungan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Allotment Released: | 2019-09-10 | Date completed:
Tagum City | Bincungan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Started:
Tagum City | Magugpo North | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | Rehab. of Evacuation Center, Magugpo North, Tagum City |  | 20% DF CY 2019 (STIMULUS) | Building |  |  | Contract | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | PO #2020031340 - JJR Construction
Tagum City | Magugpo North | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 500000 | Revised: |  | No. of Man-days:
Tagum City | Magugpo North | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Tagum City | Magugpo North | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Tagum City | Magugpo North | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Allotment Released: | 2019-09-10 | Date completed:
Tagum City | Magugpo North | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Started:
San Isidro | Pinamuno | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | Rehab. Of Water System at Purok Cabang & Mangga , Pinamuno, San Isidro |  | 20% DF CY 2019 (STIMULUS) | Water System |  |  | Contract | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | PO# 2020010025 (RLHV)
San Isidro | Pinamuno | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 500000 | Revised: |  | No. of Man-days:
San Isidro | Pinamuno | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
San Isidro | Pinamuno | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
San Isidro | Pinamuno | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Allotment Released: | 2019-12-06 | Date completed:
San Isidro | Pinamuno | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Started:
San Isidro | Igangon | 1st Eng'g. Dist. | On-going | 2020-05-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | Rehab. Of Water System , Igangon, San Isidro |  | 20% DF CY 2019 (STIMULUS) | Water System |  | ln.m | Admin | Project Cost: | 500000 | Target Completion Date: | 2020-07-17 | Program: | 500000 | Planned: | 12.26% | No. of Persons: | 25 | On-going
San Isidro | Igangon | 1st Eng'g. Dist. | On-going | 2020-05-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Project Engineer: | Kabinge | Revised Completion Date: | 2020-07-17 | Allotment: | 500000 | Revised: | 93.09% | No. of Man-days: | 375
San Isidro | Igangon | 1st Eng'g. Dist. | On-going | 2020-05-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: | 46.42%
San Isidro | Igangon | 1st Eng'g. Dist. | On-going | 2020-05-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Duration: | 60 | No. of days extended: |  |  |  | Slippage: | 93.09%
San Isidro | Igangon | 1st Eng'g. Dist. | On-going | 2020-05-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Allotment Released: | 2019-05-29 | Date completed:
San Isidro | Igangon | 1st Eng'g. Dist. | On-going | 2020-05-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Started: | 2020-05-18
New Corella | Del Monte | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | Rural Electrification , Del Monte, New Corella |  | 20% DF CY 2019 (STIMULUS) | Electrification |  |  |  | Project Cost: | 3000000 | Target Completion Date: |  | Program: | 3000000 | Planned: |  | No. of Persons: |  | For implementation
New Corella | Del Monte | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Project Engineer: | P.Bueno | Revised Completion Date: | 0 | Allotment: | 3000000 | Revised: |  | No. of Man-days:
New Corella | Del Monte | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
New Corella | Del Monte | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | Del Monte | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Allotment Released: |  | Date completed:
New Corella | Del Monte | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Started:
New Corella | San Roque | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | Rural Electrification at St. Bundok, San Roque, New Corella |  | 20% DF CY 2019 (STIMULUS) | Electrification |  |  |  | Project Cost: | 1000000 | Target Completion Date: |  | Program: | 1000000 | Planned: |  | No. of Persons: |  | Abstract # 0320201453
New Corella | San Roque | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Project Engineer: | P.Bueno | Revised Completion Date: | 0 | Allotment: | 1000000 | Revised: |  | No. of Man-days:
New Corella | San Roque | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
New Corella | San Roque | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | San Roque | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Allotment Released: |  | Date completed:
New Corella | San Roque | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Started:
Tagum City | Mankilam | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Anti - Crime & Government Itegration Project | Construction of Bahay Silangan for Reformation of Drug Personalities within The Military Camp/barracks, Brgy. Mankilam, Tagum City |  | 20% DF CY 2019 | Building |  |  |  | Project Cost: | 5000000 | Target Completion Date: |  | Program: | 5000000 | Planned: |  | No. of Persons: |  | Abstract #0620202232 - Post Qualification on process (ZULAR-A)
Tagum City | Mankilam | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Anti - Crime & Government Itegration Project | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 5000000 | Revised: |  | No. of Man-days:
Tagum City | Mankilam | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Anti - Crime & Government Itegration Project | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Tagum City | Mankilam | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Anti - Crime & Government Itegration Project | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Tagum City | Mankilam | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Anti - Crime & Government Itegration Project | [7 empty] | Date Allotment Released: |  | Date completed:
Tagum City | Mankilam | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Anti - Crime & Government Itegration Project | [7 empty] | Date Started:
New Corella | Poblacion | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (Special Protection & Intervention Program ) | Const. of Multi-Purpose Covered Court/Evacuation Center Ph. I, Duterte St., Poblacion, New Corella |  | 20% DF CY 2019 | Building |  |  |  | Project Cost: | 2000000 | Target Completion Date: |  | Program: | 2000000 | Planned: |  | No. of Persons: |  | Abstract #0720202481 - Post Qualification on pprocess (Royal Summit Infinity)
New Corella | Poblacion | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (Special Protection & Intervention Program ) | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 2000000 | Revised: |  | No. of Man-days:
New Corella | Poblacion | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (Special Protection & Intervention Program ) | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual:
New Corella | Poblacion | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (Special Protection & Intervention Program ) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | Poblacion | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (Special Protection & Intervention Program ) | [7 empty] | Date Allotment Released: |  | Date completed:
New Corella | Poblacion | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (Special Protection & Intervention Program ) | [7 empty] | Date Started:
New Corella | Poblacion | 1st Eng'g. Dist. | On-going | 2019-12-02 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Residential Care Facilities | Construction of Multi-Purpose Covered Court/Evacuation, Bahay Pag-Asa, New Corella, Ph.II (TF - P500,000.00) |  | 20% DF CY 2019 & TRUST FUND | Building |  | sq.m | Admin | Project Cost: | 2500000 | Target Completion Date: | 2020-04-15 | Program: | 2500000 | Planned: | 79.89% | No. of Persons: | 12 | On-going (Suspended last April 5, 2020 due to COVID; resumption order dated May 4, 2020)
New Corella | Poblacion | 1st Eng'g. Dist. | On-going | 2019-12-02 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Residential Care Facilities | [7 empty] | Project Engineer: | Mayang | Revised Completion Date: | 2020-08-30 | Allotment: | 2500000 | Revised: |  | No. of Man-days: | 180
New Corella | Poblacion | 1st Eng'g. Dist. | On-going | 2019-12-02 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Residential Care Facilities | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: |  | Actual: | 79.89%
New Corella | Poblacion | 1st Eng'g. Dist. | On-going | 2019-12-02 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Residential Care Facilities | [7 empty] | Duration: | 135 | No. of days extended: | 110 |  |  | Slippage: | 0%
New Corella | Poblacion | 1st Eng'g. Dist. | On-going | 2019-12-02 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Residential Care Facilities | [7 empty] | Date Allotment Released: | 2019-06-19 | Date completed:
New Corella | Poblacion | 1st Eng'g. Dist. | On-going | 2019-12-02 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Residential Care Facilities | [7 empty] | Date Started: | 2019-12-02
Provincewide | Provincewide | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Residential Care Facilities | Const. in Progress - Bldgs. And Other Structures |  | 20% DF CY 2019 | Building |  |  |  | Project Cost: | 2500000 | Target Completion Date: |  | Program: | 2500000 | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
Provincewide | Provincewide | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Residential Care Facilities | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 2500000 | Revised: |  | No. of Man-days:
Provincewide | Provincewide | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Residential Care Facilities | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual:
Provincewide | Provincewide | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Residential Care Facilities | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Provincewide | Provincewide | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Residential Care Facilities | [7 empty] | Date Allotment Released: |  | Date completed:
Provincewide | Provincewide | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Residential Care Facilities | [7 empty] | Date Started:
New Corella | Limbaan | 1st Eng'g. Dist. | On-going | 2019-03-20 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DISASTER PREVENTION AND MITIGATION - Flood Control and Slope Protection LS - P3,000,000.00 | Desilting of Limbaan Creek, New Corella |  | 5% CALAMITY FUND CY 2019 | creeks and canals deislted |  | ln.m | Admin | Project Cost: | 2000000 | Target Completion Date: | 2019-12-02 | Program: | 2000000 | Planned: |  | No. of Persons: |  | Suspended
New Corella | Limbaan | 1st Eng'g. Dist. | On-going | 2019-03-20 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DISASTER PREVENTION AND MITIGATION - Flood Control and Slope Protection LS - P3,000,000.00 | [7 empty] | Project Engineer: | Pilotos | Revised Completion Date: | 2019-12-02 | Allotment: | 2000000 | Revised: |  | No. of Man-days:
New Corella | Limbaan | 1st Eng'g. Dist. | On-going | 2019-03-20 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DISASTER PREVENTION AND MITIGATION - Flood Control and Slope Protection LS - P3,000,000.00 | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual:
New Corella | Limbaan | 1st Eng'g. Dist. | On-going | 2019-03-20 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DISASTER PREVENTION AND MITIGATION - Flood Control and Slope Protection LS - P3,000,000.00 | [7 empty] | Duration: | 257 | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | Limbaan | 1st Eng'g. Dist. | On-going | 2019-03-20 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DISASTER PREVENTION AND MITIGATION - Flood Control and Slope Protection LS - P3,000,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
New Corella | Limbaan | 1st Eng'g. Dist. | On-going | 2019-03-20 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DISASTER PREVENTION AND MITIGATION - Flood Control and Slope Protection LS - P3,000,000.00 | [7 empty] | Date Started: | 2019-03-20
kapalong | Mabantao-Florida | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Revitment of Dike and Slope Protection LS - P3,000,000.00 | Slope Protection Along Kapalong-Mabantao, Florida |  | 5% CALAMITY FUND CY 2019 | creeks and canals deislted |  |  |  | Project Cost: | 1000000 | Target Completion Date: |  | Program: | 1000000 | Planned: |  | No. of Persons: |  | For cancellation funded to DPWH. Budget Transferred to 5% Calamity Fund- Rehab and Recovery
kapalong | Mabantao-Florida | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Revitment of Dike and Slope Protection LS - P3,000,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 1000000 | Revised: |  | No. of Man-days:
kapalong | Mabantao-Florida | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Revitment of Dike and Slope Protection LS - P3,000,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
kapalong | Mabantao-Florida | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Revitment of Dike and Slope Protection LS - P3,000,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
kapalong | Mabantao-Florida | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Revitment of Dike and Slope Protection LS - P3,000,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
kapalong | Mabantao-Florida | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Revitment of Dike and Slope Protection LS - P3,000,000.00 | [7 empty] | Date Started:
Asuncion | New Boholano-New Loon | 1st Eng'g. Dist. | On-going | 2019-11-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Improvement of bridges and cross drainage LS - P3,000,000.00 | Impv't. of Jct. New Boholano - New Loon Cross Drainage |  | 5% CALAMITY FUND CY 2019 | Drainage |  | km | Admin | Project Cost: | 2000000 | Target Completion Date: | 2020-02-16 | Program: | 2000000 | Planned: | 42.27% | No. of Persons: |  | Suspended due to availability of equipment
Asuncion | New Boholano-New Loon | 1st Eng'g. Dist. | On-going | 2019-11-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Improvement of bridges and cross drainage LS - P3,000,000.00 | [7 empty] | Project Engineer: | Pilotos | Revised Completion Date: | 2020-02-16 | Allotment: | 2000000 | Revised: |  | No. of Man-days:
Asuncion | New Boholano-New Loon | 1st Eng'g. Dist. | On-going | 2019-11-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Improvement of bridges and cross drainage LS - P3,000,000.00 | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: | 31.7%
Asuncion | New Boholano-New Loon | 1st Eng'g. Dist. | On-going | 2019-11-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Improvement of bridges and cross drainage LS - P3,000,000.00 | [7 empty] | Duration: | 90 | No. of days extended: |  |  |  | Slippage: | -10.57%
Asuncion | New Boholano-New Loon | 1st Eng'g. Dist. | On-going | 2019-11-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Improvement of bridges and cross drainage LS - P3,000,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Asuncion | New Boholano-New Loon | 1st Eng'g. Dist. | On-going | 2019-11-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Improvement of bridges and cross drainage LS - P3,000,000.00 | [7 empty] | Date Started: | 2019-11-18
Asuncion | Saug Sonlon-Longanapan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Improvement of bridges and cross drainage LS - P3,000,000.00 | Impv't. of Jct. Saug-Sonlon-Bdry. Longanapan Cross Drainage |  | 5% CALAMITY FUND CY 2019 | Road |  |  |  | Project Cost: | 1000000 | Target Completion Date: |  | Program: | 1000000 | Planned: |  | No. of Persons: |  | For implementation
Asuncion | Saug Sonlon-Longanapan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Improvement of bridges and cross drainage LS - P3,000,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 1000000 | Revised: |  | No. of Man-days:
Asuncion | Saug Sonlon-Longanapan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Improvement of bridges and cross drainage LS - P3,000,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Asuncion | Saug Sonlon-Longanapan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Improvement of bridges and cross drainage LS - P3,000,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Asuncion | Saug Sonlon-Longanapan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Improvement of bridges and cross drainage LS - P3,000,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Asuncion | Saug Sonlon-Longanapan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Improvement of bridges and cross drainage LS - P3,000,000.00 | [7 empty] | Date Started:
Tagum City | San Miguel | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DISASTER REHABILITATION & RECOVERY PROGRAM - Building Back Better Project | Disiltation of Tagum Creek |  | 5% CALAMITY FUND CY 2019 | Creek |  |  | Admin | Project Cost: | 2000000 | Target Completion Date: |  | Program: | 2000000 | Planned: |  | No. of Persons: |  | Waiting for the delivery of materials
Tagum City | San Miguel | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DISASTER REHABILITATION & RECOVERY PROGRAM - Building Back Better Project | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 2000000 | Revised: |  | No. of Man-days:
Tagum City | San Miguel | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DISASTER REHABILITATION & RECOVERY PROGRAM - Building Back Better Project | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual:
Tagum City | San Miguel | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DISASTER REHABILITATION & RECOVERY PROGRAM - Building Back Better Project | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Tagum City | San Miguel | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DISASTER REHABILITATION & RECOVERY PROGRAM - Building Back Better Project | [7 empty] | Date Allotment Released: |  | Date completed:
Tagum City | San Miguel | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DISASTER REHABILITATION & RECOVERY PROGRAM - Building Back Better Project | [7 empty] | Date Started:
Asuncion | Pamacaun-Lasang-banate | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DISASTER REHABILITATION & RECOVERY PROGRAM - Building Back Better Project | Rehabilitation of Pamacaun-Lasang-Banate Provincial Road |  | 5% CALAMITY FUND CY 2019 | Road |  |  | Admin | Project Cost: | 1500000 | Target Completion Date: |  | Program: | 1500000 | Planned: |  | No. of Persons: |  | For implementation
Asuncion | Pamacaun-Lasang-banate | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DISASTER REHABILITATION & RECOVERY PROGRAM - Building Back Better Project | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 1500000 | Revised: |  | No. of Man-days:
Asuncion | Pamacaun-Lasang-banate | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DISASTER REHABILITATION & RECOVERY PROGRAM - Building Back Better Project | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Asuncion | Pamacaun-Lasang-banate | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DISASTER REHABILITATION & RECOVERY PROGRAM - Building Back Better Project | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Asuncion | Pamacaun-Lasang-banate | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DISASTER REHABILITATION & RECOVERY PROGRAM - Building Back Better Project | [7 empty] | Date Allotment Released: |  | Date completed:
Asuncion | Pamacaun-Lasang-banate | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DISASTER REHABILITATION & RECOVERY PROGRAM - Building Back Better Project | [7 empty] | Date Started:
New Corella | Del Pilar | 1st Eng'g. Dist. | On-going | 2020-02-17 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DISASTER REHABILITATION & RECOVERY PROGRAM - Building Back Better Project | Rehabilitation of Del Pilar Jct. Silangan |  | 5% CALAMITY FUND CY 2019 | Road |  | km | Admin | Project Cost: | 1500000 | Target Completion Date: | 2020-03-27 23:46 | Program: | 1500000 | Planned: | 81.11% | No. of Persons: | 4 | Suspended dated June 1, 2020 due to rainy days
New Corella | Del Pilar | 1st Eng'g. Dist. | On-going | 2020-02-17 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DISASTER REHABILITATION & RECOVERY PROGRAM - Building Back Better Project | [7 empty] | Project Engineer: | Gone | Revised Completion Date: | 2020-06-15 23:46 | Allotment: | 1500000 | Revised: |  | No. of Man-days: | 40
New Corella | Del Pilar | 1st Eng'g. Dist. | On-going | 2020-02-17 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DISASTER REHABILITATION & RECOVERY PROGRAM - Building Back Better Project | [7 empty] | Implementor: | PEO | No. of days suspended: | 29 | Disbursement: |  | Actual: | 81.11%
New Corella | Del Pilar | 1st Eng'g. Dist. | On-going | 2020-02-17 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DISASTER REHABILITATION & RECOVERY PROGRAM - Building Back Better Project | [7 empty] | Duration: | 40 | No. of days extended: | 51 |  |  | Slippage: | 0%
New Corella | Del Pilar | 1st Eng'g. Dist. | On-going | 2020-02-17 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DISASTER REHABILITATION & RECOVERY PROGRAM - Building Back Better Project | [7 empty] | Date Allotment Released: | 2019-07-26 | Date completed:
New Corella | Del Pilar | 1st Eng'g. Dist. | On-going | 2020-02-17 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DISASTER REHABILITATION & RECOVERY PROGRAM - Building Back Better Project | [7 empty] | Date Started: | 2020-02-17
kapalong | Mabantao-Florida | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DISASTER REHABILITATION & RECOVERY PROGRAM - Building Back Better Project | Rehabilitation of Libuganon River along Kapalong Mabantao-Florida Provincial Road |  | 5% CALAMITY FUND CY 2019 | Road |  |  | Admin | Project Cost: | 900000 |  |  | Program: | 900000 | Planned: |  | No. of Persons: |  | For implementation
kapalong | Mabantao-Florida | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DISASTER REHABILITATION & RECOVERY PROGRAM - Building Back Better Project | [7 empty] | Project Engineer: |  |  |  | Allotment: | 900000 | Revised: |  | No. of Man-days:
kapalong | Mabantao-Florida | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DISASTER REHABILITATION & RECOVERY PROGRAM - Building Back Better Project | [7 empty] | Implementor: |  |  |  | Disbursement: |  | Actual:
kapalong | Mabantao-Florida | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DISASTER REHABILITATION & RECOVERY PROGRAM - Building Back Better Project | [7 empty] | Duration: | [5 empty] | Slippage: | 0%
kapalong | Mabantao-Florida | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DISASTER REHABILITATION & RECOVERY PROGRAM - Building Back Better Project | [7 empty] | Date Allotment Released:
kapalong | Mabantao-Florida | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DISASTER REHABILITATION & RECOVERY PROGRAM - Building Back Better Project | [7 empty] | Date Started:
New Corella | Mesaoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DISASTER REHABILITATION & RECOVERY PROGRAM - Building Back Better Project | Rehabilitation of Mesaoy-Jct. Mahayahay Road |  | 5% CALAMITY FUND CY 2019 | Road |  |  | Admin | Project Cost: | 1000000 | Target Completion Date: |  | Program: | 1000000 | Planned: |  | No. of Persons: |  | For implementation
New Corella | Mesaoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DISASTER REHABILITATION & RECOVERY PROGRAM - Building Back Better Project | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 1000000 | Revised: |  | No. of Man-days:
New Corella | Mesaoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DISASTER REHABILITATION & RECOVERY PROGRAM - Building Back Better Project | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
New Corella | Mesaoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DISASTER REHABILITATION & RECOVERY PROGRAM - Building Back Better Project | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | Mesaoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DISASTER REHABILITATION & RECOVERY PROGRAM - Building Back Better Project | [7 empty] | Date Allotment Released: |  | Date completed:
New Corella | Mesaoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DISASTER REHABILITATION & RECOVERY PROGRAM - Building Back Better Project | [7 empty] | Date Started:
New Corella | Sta. Fe - Mambing | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DISASTER REHABILITATION & RECOVERY PROGRAM - Building Back Better Project | Rehabilitation of Sta. Fe- Mambing Road & Slope Protection |  | 5% CALAMITY FUND CY 2019 | Road |  |  | Admin | Project Cost: | 1320000 | Target Completion Date: |  | Program: | 1320000 | Planned: |  | No. of Persons: |  | For implementation
New Corella | Sta. Fe - Mambing | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DISASTER REHABILITATION & RECOVERY PROGRAM - Building Back Better Project | [7 empty] | Project Engineer: | Pilotos | Revised Completion Date: | 0 | Allotment: | 1320000 | Revised: |  | No. of Man-days:
New Corella | Sta. Fe - Mambing | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DISASTER REHABILITATION & RECOVERY PROGRAM - Building Back Better Project | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual:
New Corella | Sta. Fe - Mambing | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DISASTER REHABILITATION & RECOVERY PROGRAM - Building Back Better Project | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | Sta. Fe - Mambing | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DISASTER REHABILITATION & RECOVERY PROGRAM - Building Back Better Project | [7 empty] | Date Allotment Released: |  | Date completed:
New Corella | Sta. Fe - Mambing | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DISASTER REHABILITATION & RECOVERY PROGRAM - Building Back Better Project | [7 empty] | Date Started:
Asuncion | San Agustin | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DISASTER REHABILITATION & RECOVERY PROGRAM - Building Back Better Project | Rehabilitation of Canal Lining and Slope Protection at San Agustin E/S, San Agustin, Tagum City |  | 5% CALAMITY FUND CY 2019 | Drainage |  |  | Admin | Project Cost: | 350000 | Target Completion Date: |  | Program: | 350000 | Planned: |  | No. of Persons: |  | For implementation
Asuncion | San Agustin | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DISASTER REHABILITATION & RECOVERY PROGRAM - Building Back Better Project | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 350000 | Revised: |  | No. of Man-days:
Asuncion | San Agustin | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DISASTER REHABILITATION & RECOVERY PROGRAM - Building Back Better Project | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Asuncion | San Agustin | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DISASTER REHABILITATION & RECOVERY PROGRAM - Building Back Better Project | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Asuncion | San Agustin | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DISASTER REHABILITATION & RECOVERY PROGRAM - Building Back Better Project | [7 empty] | Date Allotment Released: |  | Date completed:
Asuncion | San Agustin | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DISASTER REHABILITATION & RECOVERY PROGRAM - Building Back Better Project | [7 empty] | Date Started:
Asuncion | Doña Andrea | 1st Eng'g. Dist. | On-going | 2020-02-17 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DILG | Construction of Halfway House, Brgy. Doña Andrea, Asuncion |  | DILG | Building |  | sq.m | Admin | Project Cost: | 5000000 | Target Completion Date: | 2020-08-14 23:59 | Program: | 5000000 | Planned: | 43.45% | No. of Persons: | 6 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 6, 2020)
Asuncion | Doña Andrea | 1st Eng'g. Dist. | On-going | 2020-02-17 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DILG | [7 empty] | Project Engineer: | Dadula | Revised Completion Date: | 2020-09-12 23:59 | Allotment: | 5000000 | Revised: |  | No. of Man-days: | 138
Asuncion | Doña Andrea | 1st Eng'g. Dist. | On-going | 2020-02-17 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DILG | [7 empty] | Implementor: | PEO | No. of days suspended: | 29 | Disbursement: |  | Actual: | 43.45%
Asuncion | Doña Andrea | 1st Eng'g. Dist. | On-going | 2020-02-17 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DILG | [7 empty] | Duration: | 180 | No. of days extended: |  |  |  | Slippage: | -0.004%
Asuncion | Doña Andrea | 1st Eng'g. Dist. | On-going | 2020-02-17 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DILG | [7 empty] | Date Allotment Released: | CY 2019 | Date completed:
Asuncion | Doña Andrea | 1st Eng'g. Dist. | On-going | 2020-02-17 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DILG | [7 empty] | Date Started: | 2020-02-17
Asuncion | Cambanogoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Lot Purchase | Purchase of Lot for Cemetery, Cambanogoy, Asuncion |  | SUPPLEMENTAL BUDGET NO. 1 CY 2019 (STIMULUS) | Land |  |  |  | Project Cost: | 1500000 | Target Completion Date: |  | Program: | 1500000 | Planned: |  | No. of Persons: |  | Documents for fund transfer to be complied by the LGUs. Letter sent dated June 18, 2019
Asuncion | Cambanogoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Lot Purchase | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 1500000 | Revised: |  | No. of Man-days:
Asuncion | Cambanogoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Lot Purchase | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Asuncion | Cambanogoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Lot Purchase | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Asuncion | Cambanogoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Lot Purchase | [7 empty] | Date Allotment Released: |  | Date completed:
Asuncion | Cambanogoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Lot Purchase | [7 empty] | Date Started:
New Corella | San Roque | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Lot Purchase | Purchase of Lot for Cemetery, San Roque, New Corella |  | SUPPLEMENTAL BUDGET NO. 1 CY 2019 (STIMULUS) | Land |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Documents for fund transfer to be complied by the LGUs. Letter sent dated June 18, 2019
New Corella | San Roque | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Lot Purchase | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 500000 | Revised: |  | No. of Man-days:
New Corella | San Roque | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Lot Purchase | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
New Corella | San Roque | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Lot Purchase | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | San Roque | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Lot Purchase | [7 empty] | Date Allotment Released: |  | Date completed:
New Corella | San Roque | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Lot Purchase | [7 empty] | Date Started:
Asuncion | Sagayen | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | Rehab/Impvt of Gymnasium, Sagayen, Asuncion |  | SUPPLEMENTAL BUDGET NO. 1 CY 2019 (STIMULUS) | Building |  |  |  | Project Cost: | 1500000 | Target Completion Date: |  | Program: | 1500000 | Planned: |  | No. of Persons: |  | Final Abstract # 0320200900 (Alpebel Builders & Supply Corp.)
Asuncion | Sagayen | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 1500000 | Revised: |  | No. of Man-days:
Asuncion | Sagayen | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Asuncion | Sagayen | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Asuncion | Sagayen | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Allotment Released: |  | Date completed:
Asuncion | Sagayen | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Started:
New Corella | New Sambog | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | Purchase of Lot for Resettlement Site, New Sambog, New Corella |  | SUPPLEMENTAL BUDGET NO. 1 CY 2019 (STIMULUS) | Land |  |  |  | Project Cost: | 1500000 | Target Completion Date: |  | Program: | 1500000 | Planned: |  | No. of Persons: |  | for fund transfer. Waiting for LGU documents. Liquidation of previous fund transfer for the water system project of LGU.
New Corella | New Sambog | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 1500000 | Revised: |  | No. of Man-days:
New Corella | New Sambog | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
New Corella | New Sambog | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | New Sambog | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Allotment Released: |  | Date completed:
New Corella | New Sambog | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Started:
Asuncion | Sagayen | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | Installation of Street Lights at Prk 1,2,3,4, Sagayen, Asuncion |  | SUPPLEMENTAL BUDGET NO. 1 CY 2019 (STIMULUS) | Electrification |  |  |  | Project Cost: | 1000000 | Target Completion Date: |  | Program: | 1000000 | Planned: |  | No. of Persons: |  | Purchase Order # 2019113377 (Tagum Builders)
Asuncion | Sagayen | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 1000000 | Revised: |  | No. of Man-days:
Asuncion | Sagayen | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Asuncion | Sagayen | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Asuncion | Sagayen | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Allotment Released: |  | Date completed:
Asuncion | Sagayen | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Started:
Asuncion | Concepcion | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | Rehab/Imprvt. Of FMR, Prk 3,7, & 8, Concepcion, Asuncion |  | SUPPLEMENTAL BUDGET NO. 1 CY 2019 (STIMULUS) | Road |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Waiting for equipment availability as of Feb. 5, 2020 report submitted by Engr. Cuajao
Asuncion | Concepcion | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 500000 | Revised: |  | No. of Man-days:
Asuncion | Concepcion | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Asuncion | Concepcion | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Asuncion | Concepcion | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Allotment Released: |  | Date completed:
Asuncion | Concepcion | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Started:
New Corella | San Jose | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | Farm to Market Road, San Jose, New Corella |  | SUPPLEMENTAL BUDGET NO. 1 CY 2019 (STIMULUS) | Road |  |  |  | Project Cost: | 2000000 | Target Completion Date: |  | Program: | 2000000 | Planned: |  | No. of Persons: |  | For cancellation
New Corella | San Jose | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 2000000 | Revised: |  | No. of Man-days:
New Corella | San Jose | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
New Corella | San Jose | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | San Jose | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Allotment Released: |  | Date completed:
New Corella | San Jose | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Started:
New Corella | New Sambog | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | Const. of Water System, New Sambog, New Corella |  | SUPPLEMENTAL BUDGET NO. 1 CY 2019 (STIMULUS) | Water System |  |  | MLGU | Project Cost: | 1000000 | Target Completion Date: |  | Program: | 1000000 | Planned: |  | No. of Persons: |  | Fund transferred to LGU
New Corella | New Sambog | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 1000000 | Revised: |  | No. of Man-days:
New Corella | New Sambog | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
New Corella | New Sambog | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | New Sambog | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Allotment Released: |  | Date completed:
New Corella | New Sambog | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Started:
New Corella | Limbaan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | Const. of Drainage Canal from Prk. 3, 1-A, 2-A to Prk 1-B, Brgy Site (Ph. 2), Limbaan, New Corella |  | SUPPLEMENTAL BUDGET NO. 1 CY 2019 (STIMULUS) | Flood Control - Drainage |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | POW preparation on going c/o PDPM
New Corella | Limbaan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 500000 | Revised: |  | No. of Man-days:
New Corella | Limbaan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
New Corella | Limbaan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | Limbaan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Allotment Released: |  | Date completed:
New Corella | Limbaan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Started:
New Corella | Patrocenio | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | Const. of FMR from Prk 1 to Sitio Magsaysay via Pundol & Prk 4, Patrocenio, New Corella |  | SUPPLEMENTAL BUDGET NO. 1 CY 2019 (STIMULUS) | Road |  |  |  | Project Cost: | 2000000 | Target Completion Date: |  | Program: | 2000000 | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
New Corella | Patrocenio | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 2000000 | Revised: |  | No. of Man-days:
New Corella | Patrocenio | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
New Corella | Patrocenio | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | Patrocenio | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Allotment Released: |  | Date completed:
New Corella | Patrocenio | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Started:
New Corella | San Jose | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | Const. of Multi-Purpose Pavement, San Jose, New Corella |  | SUPPLEMENTAL BUDGET NO. 1 CY 2019 (STIMULUS) | Building |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | POW approved but allotment not yet requested waiting for deed of donation c/o Engr. Canillada
New Corella | San Jose | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 500000 | Revised: |  | No. of Man-days:
New Corella | San Jose | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
New Corella | San Jose | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | San Jose | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Allotment Released: |  | Date completed:
New Corella | San Jose | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Started:
Asuncion | Buan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | Const. of Multipurpose Covered Court, Buan, Asuncion |  | SUPPLEMENTAL BUDGET NO. 1 CY 2019 (STIMULUS) | Covered Court |  |  | MLGU | Project Cost: | 2500000 | Target Completion Date: |  | Program: | 2500000 | Planned: |  | No. of Persons: |  | Fund transferred to LGU
Asuncion | Buan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 2500000 | Revised: |  | No. of Man-days:
Asuncion | Buan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Asuncion | Buan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Asuncion | Buan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Allotment Released: | 2019-06-26 | Date completed:
Asuncion | Buan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Started:
Asuncion | Pamacaun | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | Const. of Multipurpose Covered Court, Pamacaun, Asuncion |  | SUPPLEMENTAL BUDGET NO. 1 CY 2019 (STIMULUS) | Covered Court |  |  | MLGU | Project Cost: | 2500000 | Target Completion Date: |  | Program: | 2500000 | Planned: |  | No. of Persons: |  | Fund transferred to LGU
Asuncion | Pamacaun | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 2500000 | Revised: |  | No. of Man-days:
Asuncion | Pamacaun | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Asuncion | Pamacaun | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Asuncion | Pamacaun | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Allotment Released: | 2019-05-29 | Date completed:
Asuncion | Pamacaun | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Started:
New Corella | Poblacion | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | Const. of 2 Storey Multi purpose Hall Ph.2 (Brgy. Hall) , Poblacion, New Corella |  | SUPPLEMENTAL BUDGET NO. 1 CY 2019 (STIMULUS) | Building |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
New Corella | Poblacion | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 500000 | Revised: |  | No. of Man-days:
New Corella | Poblacion | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
New Corella | Poblacion | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | Poblacion | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Allotment Released: |  | Date completed:
New Corella | Poblacion | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Started:
New Corella | Patrocenio | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | Expansion of Multi-Purpose Hall ( Brgy. Hall), Patrocenio, New Corella |  | SUPPLEMENTAL BUDGET NO. 1 CY 2019 (STIMULUS) | Building |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Purchase Order # 2020020796 (JJR Construction)
New Corella | Patrocenio | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 500000 | Revised: |  | No. of Man-days:
New Corella | Patrocenio | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
New Corella | Patrocenio | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | Patrocenio | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Allotment Released: |  | Date completed:
New Corella | Patrocenio | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Started:
New Corella | Poblacion | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | Rehabilitation of Water System in PEEDO-LPRRC, Brgy. Poblacion, New Corella |  | SUPPLEMENTAL BUDGET NO. 1 CY 2019 (STIMULUS) | Water System |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Purchase Order # 2020010009 (ANCOR Water Resources)
New Corella | Poblacion | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 500000 | Revised: |  | No. of Man-days:
New Corella | Poblacion | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
New Corella | Poblacion | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | Poblacion | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Allotment Released: |  | Date completed:
New Corella | Poblacion | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Started:
Talaingod | Salawao-Sto. Niño | 1st Eng'g. Dist. | On-going | 2020-06-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | Provincial Livestock & Poultry Multiplier Farm Road Network Construction, Sitio Salawao, Sto. Niño, Talaingod |  | SUPPLEMENTAL BUDGET NO. 1 CY 2019 (STIMULUS) | Conc. Pavement |  | sq.m | Admin | Project Cost: | 5500000 | Target Completion Date: | 2020-07-13 23:46 | Program: | 5500000 | Planned: | 26.35% | No. of Persons: | 15 | On-going (For time extension)
Talaingod | Salawao-Sto. Niño | 1st Eng'g. Dist. | On-going | 2020-06-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Project Engineer: | Pasiona/Juan | Revised Completion Date: | 2020-08-10 23:46 | Allotment: | 5500000 | Revised: |  | No. of Man-days: | 225
Talaingod | Salawao-Sto. Niño | 1st Eng'g. Dist. | On-going | 2020-06-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Implementor: | PEO | No. of days suspended: | 28 | Disbursement: | 1449250 | Actual: | 26.35%
Talaingod | Salawao-Sto. Niño | 1st Eng'g. Dist. | On-going | 2020-06-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Duration: | 120 | No. of days extended: |  |  |  | Slippage: | 0%
Talaingod | Salawao-Sto. Niño | 1st Eng'g. Dist. | On-going | 2020-06-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Allotment Released: | CY 2019 | Date completed:
Talaingod | Salawao-Sto. Niño | 1st Eng'g. Dist. | On-going | 2020-06-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Started: | 2020-03-16
Talaingod | Tapayanon | 1st Eng'g. Dist. | On-going | 2019-11-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | Proposed Road Opening of Tawinian-Tapayanon Road Section |  | SUPPLEMENTAL BUDGET NO. 4 CY 2019 (STIMULUS) | Road |  | km | Admin | Project Cost: | 10000000 | Target Completion Date: | 2020-09-18 23:46 | Program: | 10000000 | Planned: | 27.08% | No. of Persons: | 5 | On-going (Suspended last April 5, 2020 due to COVID; resumption order dated May 4, 2020); Equipment Rental 1 unit Backhoe (Bidding July 16, 2020)
Talaingod | Tapayanon | 1st Eng'g. Dist. | On-going | 2019-11-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Project Engineer: | Garcia | Revised Completion Date: | 2020-10-16 23:46 | Allotment: | 10000000 | Revised: |  | No. of Man-days: | 319
Talaingod | Tapayanon | 1st Eng'g. Dist. | On-going | 2019-11-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Implementor: | PEO | No. of days suspended: | 28 | Disbursement: |  | Actual: | 27.08%
Talaingod | Tapayanon | 1st Eng'g. Dist. | On-going | 2019-11-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Duration: | 306 | No. of days extended: |  |  |  | Slippage: | 0%
Talaingod | Tapayanon | 1st Eng'g. Dist. | On-going | 2019-11-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Allotment Released: | 2019-11-15 | Date completed:
Talaingod | Tapayanon | 1st Eng'g. Dist. | On-going | 2019-11-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Started: | 2019-11-18
kapalong | Maniki | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | Completion of Brgy. Health Center, Maniki, Kapalong |  | SUPPLEMENTAL BUDGET NO. 4 CY 2019 (STIMULUS) | Building |  |  |  | Project Cost: | 627000 | Target Completion Date: |  | Program: | 627000 | Planned: |  | No. of Persons: |  | PROJECT Was funded by LGU, Kapalong
kapalong | Maniki | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 627000 | Revised: |  | No. of Man-days:
kapalong | Maniki | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
kapalong | Maniki | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
kapalong | Maniki | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Allotment Released: |  | Date completed:
kapalong | Maniki | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Started:
Asuncion | New Santiago | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | Construction of Potable Water System at Purok 6, New Santiago, Asuncion |  | SUPPLEMENTAL BUDGET NO. 4 CY 2019 (STIMULUS) | Water System |  |  | contract | Project Cost: | 1000000 | Target Completion Date: |  | Program: | 1000000 | Planned: |  | No. of Persons: |  | Change of POW to Contract
Asuncion | New Santiago | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 1000000 | Revised: |  | No. of Man-days:
Asuncion | New Santiago | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Asuncion | New Santiago | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Asuncion | New Santiago | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Allotment Released: |  | Date completed:
Asuncion | New Santiago | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Started:
New Corella | Poblacion | 1st Eng'g. Dist. | On-going | 2019-11-25 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | Construction of Children's Playground with Amenities, Poblacion, New Corella |  | SUPPLEMENTAL BUDGET NO. 4 CY 2019 (STIMULUS) | Building |  | sq.m | Admin | Project Cost: | 2500000 | Target Completion Date: | 2020-03-03 23:59 | Program: | 2500000 | Planned: | 46.63% | No. of Persons: | 10 | On-going (Suspended effective April 5, 2020 due to COVID; resumption order dated May 4, 2020)
New Corella | Poblacion | 1st Eng'g. Dist. | On-going | 2019-11-25 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Project Engineer: | Mayang | Revised Completion Date: | 2020-04-30 23:59 | Allotment: | 2500000 | Revised: |  | No. of Man-days: | 150
New Corella | Poblacion | 1st Eng'g. Dist. | On-going | 2019-11-25 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Implementor: | PEO | No. of days suspended: | 28 | Disbursement: | 1029250 | Actual: | 46.63%
New Corella | Poblacion | 1st Eng'g. Dist. | On-going | 2019-11-25 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Duration: | 100 | No. of days extended: | 30 |  |  | Slippage: | 0%
New Corella | Poblacion | 1st Eng'g. Dist. | On-going | 2019-11-25 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Allotment Released: | 2019-12-06 | Date completed:
New Corella | Poblacion | 1st Eng'g. Dist. | On-going | 2019-11-25 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Started: | 2019-11-25
Tagum City | Magugpo Poblacion | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | Rehabilitation of Evacuation Center at Magugpo Pob., Tagum City |  | SUPPLEMENTAL BUDGET NO. 4 CY 2019 (STIMULUS) | Building |  |  |  | Project Cost: | 600000 | Target Completion Date: |  | Program: | 600000 | Planned: |  | No. of Persons: |  | Purchase Order # 2020020796 (JJR Construction)
Tagum City | Magugpo Poblacion | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 600000 | Revised: |  | No. of Man-days:
Tagum City | Magugpo Poblacion | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Tagum City | Magugpo Poblacion | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Tagum City | Magugpo Poblacion | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Allotment Released: |  | Date completed:
Tagum City | Magugpo Poblacion | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Started:
Tagum City | Magugpo SOuth | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | Construction of Brgy. Health Center at Magugpo South, Tagum City |  | SUPPLEMENTAL BUDGET NO. 4 CY 2019 (STIMULUS) | Building |  |  |  | Project Cost: | 1550000 | Target Completion Date: |  | Program: | 1550000 | Planned: |  | No. of Persons: |  | Purchase Order # 20022150 (On-process)
Tagum City | Magugpo SOuth | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 1550000 | Revised: |  | No. of Man-days:
Tagum City | Magugpo SOuth | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Tagum City | Magugpo SOuth | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Tagum City | Magugpo SOuth | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Allotment Released: |  | Date completed:
Tagum City | Magugpo SOuth | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Started:
New Corella | Limbaan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | Rehab. Of Multi-Purpose Building (Evacuation Center), Limbaan, New Corella |  | SUPPLEMENTAL BUDGET NO. 4 CY 2019 (STIMULUS) | Building |  |  |  | Project Cost: | 600000 | Target Completion Date: |  | Program: | 600000 | Planned: |  | No. of Persons: |  | From SB # 1 to SB # 4 CY 2019 (Transfer to Contract) Procurement on process
New Corella | Limbaan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 600000 | Revised: |  | No. of Man-days:
New Corella | Limbaan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
New Corella | Limbaan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | Limbaan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Allotment Released: |  | Date completed:
New Corella | Limbaan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Started:
San Isidro | Sagayen-Sawata | 1st Eng'g. Dist. | On-going | 2019-09-09 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | Improvement of Km. 9 Sagayen-Sawata Provincial Road, San Isidro, Ph. II |  | SUPPLEMENTAL BUDGET NO. 4 CY 2019 (STIMULUS) | Road |  | ln.m | Admin | Project Cost: | 4591029 | Target Completion Date: | 2020-03-27 | Program: | 4591029 | Planned: | 45% | No. of Persons: | 6 | On-going (Suspended last April 5, 2020 due to COVID; resumption order dated May 4, 2020)
San Isidro | Sagayen-Sawata | 1st Eng'g. Dist. | On-going | 2019-09-09 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Project Engineer: | Limpo | Revised Completion Date: |  | Allotment: | 4591029 | Revised: |  | No. of Man-days: | 138
San Isidro | Sagayen-Sawata | 1st Eng'g. Dist. | On-going | 2019-09-09 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: | 1609155.6645 | Actual: | 35.05%
San Isidro | Sagayen-Sawata | 1st Eng'g. Dist. | On-going | 2019-09-09 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Duration: | 200 | No. of days extended: |  |  |  | Slippage: | -9.95%
San Isidro | Sagayen-Sawata | 1st Eng'g. Dist. | On-going | 2019-09-09 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Allotment Released: | 2019-12-12 | Date completed:
San Isidro | Sagayen-Sawata | 1st Eng'g. Dist. | On-going | 2019-09-09 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Started: | 2019-09-09
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Department of Agriculture | Poultry House and Training Center Sto. Niño, Talaingod |  | PROJECTS FOR PROVINCIAL VETERINARY | Building |  |  | Contract | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Final Abstract # 012020012 (Alpebel Builders & Supply Corp.)
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Department of Agriculture | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 500000 | Revised: |  | No. of Man-days:
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Department of Agriculture | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Department of Agriculture | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Department of Agriculture | [7 empty] | Date Allotment Released: |  | Date completed:
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Department of Agriculture | [7 empty] | Date Started:
Talaingod | Salawao-Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Department of Agriculture | Establishment of Livestock and Poultry Mutiplier Farm, Sitio Salawao, Sto. Niño, Talaingod |  | Department of Agriculture - Regional Field Office XI | Building |  |  |  | Project Cost: | 600000 | Target Completion Date: |  | Program: | 600000 | Planned: |  | No. of Persons: |  | Final Abstract # 012020012 (Alpebel Builders & Supply Corp.)
Talaingod | Salawao-Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Department of Agriculture | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 600000 | Revised: |  | No. of Man-days:
Talaingod | Salawao-Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Department of Agriculture | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Talaingod | Salawao-Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Department of Agriculture | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Talaingod | Salawao-Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Department of Agriculture | [7 empty] | Date Allotment Released: |  | Date completed:
Talaingod | Salawao-Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Department of Agriculture | [7 empty] | Date Started:
kapalong | Mabantao-Florida | 1st Eng'g. Dist. | On-going | 2019-10-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CMGP | Road Upgrading of Kapalong - Mabantao - Florida Road with Bridge Component |  | CMGP CY 2019 | Concreting |  | ln.m | Contract | Project Cost: | 15435008 | Target Completion Date: | 2020-03-10 23:59 | Program: | 15435008 | Planned: | 100% | No. of Persons: | 19 | On-going (Suspended last April 5, 2020 due to COVID; resumption order dated May 4, 2020)
kapalong | Mabantao-Florida | 1st Eng'g. Dist. | On-going | 2019-10-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CMGP | [7 empty] | Project Engineer: | Japay/Quirante | Revised Completion Date: | 2020-04-29 23:59 | Allotment: | 15435008 | Revised: | 81.81% | No. of Man-days: | 551
kapalong | Mabantao-Florida | 1st Eng'g. Dist. | On-going | 2019-10-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CMGP | [7 empty] | Implementor: | LEGACY | No. of days suspended: | 30 | Disbursement: | 6174003.2 | Actual: | 78.93%
kapalong | Mabantao-Florida | 1st Eng'g. Dist. | On-going | 2019-10-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CMGP | [7 empty] | Duration: | 147 | No. of days extended: | 20 |  |  | Slippage: | -2.882%
kapalong | Mabantao-Florida | 1st Eng'g. Dist. | On-going | 2019-10-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CMGP | [7 empty] | Date Allotment Released: | CY 2019 | Date completed:
kapalong | Mabantao-Florida | 1st Eng'g. Dist. | On-going | 2019-10-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CMGP | [7 empty] | Date Started: | 2019-10-16
New Corella | Del Pilar | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | LGSF | Rehabilitation of Dasing to Monte Carlo FMR, Del Pilar, New Corella |  | LGSF CY 2019 | Concreting |  |  | Contract | Project Cost: | 40000000 | Target Completion Date: |  | Program: | 40000000 | Planned: |  | No. of Persons: |  | For implementation (Awarded to Rely Construction and Supply)
New Corella | Del Pilar | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | LGSF | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 40000000 | Revised: |  | No. of Man-days:
New Corella | Del Pilar | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | LGSF | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
New Corella | Del Pilar | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | LGSF | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | Del Pilar | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | LGSF | [7 empty] | Date Allotment Released: |  | Date completed:
New Corella | Del Pilar | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | LGSF | [7 empty] | Date Started:
Tagum City | Magugpo South | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | LGSF | Concreting of Visayan Village - Purok exodus - Purok Rafael, Brgy. Magugpo South, Tagum City |  | LGSF CY 2019 | Concreting |  |  | Contract | Project Cost: | 40000000 | Target Completion Date: |  | Program: | 40000000 | Planned: |  | No. of Persons: |  | For implementation (Awarded to Legacy Construction Corporation)
Tagum City | Magugpo South | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | LGSF | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 40000000 | Revised: |  | No. of Man-days:
Tagum City | Magugpo South | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | LGSF | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Tagum City | Magugpo South | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | LGSF | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Tagum City | Magugpo South | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | LGSF | [7 empty] | Date Allotment Released: |  | Date completed:
Tagum City | Magugpo South | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | LGSF | [7 empty] | Date Started:
Asuncion | Magatos-Bantayan | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 001 - Jct. Highway Magatos - New Bantayan |  | GENERAL FUND CY 2020 | Maintenance | 7.1 | km | MBA | Project Cost: | 564839.9739 | Target Completion Date: | 2020-12-31 23:59 | Program: | 564839.9739 | Planned: | 27.45% | No. of Persons: | 17 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020)
Asuncion | Magatos-Bantayan | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 564839.9739 | Revised: |  | No. of Man-days: | 374
Asuncion | Magatos-Bantayan | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 57334.17 | Actual: | 27.45%
Asuncion | Magatos-Bantayan | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0%
Asuncion | Magatos-Bantayan | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
Asuncion | Magatos-Bantayan | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started: | 2020-01-02
Asuncion | Magatos-Bantayan | 1st Eng'g. Dist. | On-going |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 001 - Jct. Highway Magatos - New Bantayan |  | GENERAL FUND CY 2020 | Maintenance | 7.1 | km | CBRMC | Project Cost: | 230737.1976 | Target Completion Date: |  | Program: | 230737.1976 | Planned: |  | No. of Persons: |  | Purchase Request # 19125305 (On process)
Asuncion | Magatos-Bantayan | 1st Eng'g. Dist. | On-going |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 230737.1976 | Revised: |  | No. of Man-days:
Asuncion | Magatos-Bantayan | 1st Eng'g. Dist. | On-going |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Asuncion | Magatos-Bantayan | 1st Eng'g. Dist. | On-going |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Asuncion | Magatos-Bantayan | 1st Eng'g. Dist. | On-going |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: |  | Date completed:
Asuncion | Magatos-Bantayan | 1st Eng'g. Dist. | On-going |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started:
Asuncion | Magatos-Pagsabangan | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 002 - Magatos - Bdry. Pagsabangan |  | GENERAL FUND CY 2020 | Maintenance | 8.33 | km | MBA | Project Cost: | 653221.626 | Target Completion Date: | 2020-12-31 23:59 | Program: | 653221.626 | Planned: | 25.07% | No. of Persons: | 17 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020)
Asuncion | Magatos-Pagsabangan | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 653221.626 | Revised: |  | No. of Man-days: | 374
Asuncion | Magatos-Pagsabangan | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 71713.44 | Actual: | 25.07%
Asuncion | Magatos-Pagsabangan | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0%
Asuncion | Magatos-Pagsabangan | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
Asuncion | Magatos-Pagsabangan | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started: | 2020-01-02
Asuncion | Magatos-Pagsabangan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 002 - Magatos - Bdry. Pagsabangan |  | GENERAL FUND CY 2020 | Maintenance | 8.33 | km | CBRMC | Project Cost: | 280180.88 | Target Completion Date: |  | Program: | 280180.88 | Planned: |  | No. of Persons: |  | Purchase Request # 19125306 (On process)
Asuncion | Magatos-Pagsabangan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 280180.88 | Revised: |  | No. of Man-days:
Asuncion | Magatos-Pagsabangan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Asuncion | Magatos-Pagsabangan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Asuncion | Magatos-Pagsabangan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: |  | Date completed:
Asuncion | Magatos-Pagsabangan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started:
Asuncion | New Bantayan | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 003 - Ilog - New Bantayan |  | GENERAL FUND CY 2020 | Maintenance | 2.68 | km | MBA | Project Cost: | 236174.847 | Target Completion Date: | 2020-12-31 23:59 | Program: | 236174.847 | Planned: | 15.36% | No. of Persons: | 17 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020)
Asuncion | New Bantayan | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 236174.847 | Revised: |  | No. of Man-days: | 374
Asuncion | New Bantayan | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 22629.74 | Actual: | 15.36%
Asuncion | New Bantayan | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0%
Asuncion | New Bantayan | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
Asuncion | New Bantayan | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started: | 2020-01-02
Asuncion | New Bantayan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 003 - Ilog - New Bantayan |  | GENERAL FUND CY 2020 | Maintenance | 2.68 | km | CBRMC | Project Cost: | 70633.836 | Target Completion Date: |  | Program: | 70633.836 | Planned: |  | No. of Persons: |  | Purchase Request # 19125307 (On process)
Asuncion | New Bantayan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 70633.836 | Revised: |  | No. of Man-days:
Asuncion | New Bantayan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Asuncion | New Bantayan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Asuncion | New Bantayan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: |  | Date completed:
Asuncion | New Bantayan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started:
Asuncion | Monte Carlo-Del Pilar | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 005 - Asuncion - Monte Carlo - Del Pilar |  | GENERAL FUND CY 2020 | Maintenance | 9.93 | km | MBA | Project Cost: | 716344.9167 | Target Completion Date: | 2020-12-31 23:59 | Program: | 716344.9167 | Planned: | 29.09% | No. of Persons: | 17 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020)
Asuncion | Monte Carlo-Del Pilar | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 716344.9167 | Revised: |  | No. of Man-days: | 374
Asuncion | Monte Carlo-Del Pilar | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 33056.21 | Actual: | 29.09%
Asuncion | Monte Carlo-Del Pilar | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0%
Asuncion | Monte Carlo-Del Pilar | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
Asuncion | Monte Carlo-Del Pilar | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started: | 2020-01-02
Asuncion | Monte Carlo-Del Pilar | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 005 - Asuncion - Monte Carlo - Del Pilar |  | GENERAL FUND CY 2020 | Maintenance | 9.93 | km | CBRMC | Project Cost: | 360232.5636 | Target Completion Date: |  | Program: | 360232.5636 | Planned: |  | No. of Persons: |  | Purchase Request # 19125308 (On process)
Asuncion | Monte Carlo-Del Pilar | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 360232.5636 | Revised: |  | No. of Man-days:
Asuncion | Monte Carlo-Del Pilar | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Asuncion | Monte Carlo-Del Pilar | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Asuncion | Monte Carlo-Del Pilar | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: |  | Date completed:
Asuncion | Monte Carlo-Del Pilar | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started:
Asuncion | Canatan-Magatos | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 006 - Jct. Highway Canatan - Magatos |  | GENERAL FUND CY 2020 | Maintenance | 4.85 | km | MBA | Project Cost: | 391296.517 | Target Completion Date: | 2020-12-31 23:59 | Program: | 391296.517 | Planned: | 24.95% | No. of Persons: | 17 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020)
Asuncion | Canatan-Magatos | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 391296.517 | Revised: |  | No. of Man-days: | 374
Asuncion | Canatan-Magatos | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 33056.21 | Actual: | 24.95%
Asuncion | Canatan-Magatos | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0%
Asuncion | Canatan-Magatos | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
Asuncion | Canatan-Magatos | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started: | 2020-01-02
Asuncion | Canatan-Magatos | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 006 - Jct. Highway Canatan - Magatos |  | GENERAL FUND CY 2020 | Maintenance | 4.85 | km | CBRMC | Project Cost: | 164812.284 | Target Completion Date: |  | Program: | 164812.284 | Planned: |  | No. of Persons: |  | Purchase Request # 19125309 (On process)
Asuncion | Canatan-Magatos | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 164812.284 | Revised: |  | No. of Man-days:
Asuncion | Canatan-Magatos | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Asuncion | Canatan-Magatos | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Asuncion | Canatan-Magatos | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: |  | Date completed:
Asuncion | Canatan-Magatos | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started:
Asuncion | Saug-Sonlon-Longanapan | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 010 - Saug - Sonlon - Bdry. Longanapan |  | GENERAL FUND CY 2020 | Maintenance | 11.6 | km | MBA | Project Cost: | 1102041.4797 | Target Completion Date: | 2020-12-31 23:59 | Program: | 1102041.4797 | Planned: | 21.92% | No. of Persons: | 17 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020)
Asuncion | Saug-Sonlon-Longanapan | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 1102041.4797 | Revised: |  | No. of Man-days: | 374
Asuncion | Saug-Sonlon-Longanapan | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 83166.18 | Actual: | 21.92%
Asuncion | Saug-Sonlon-Longanapan | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0%
Asuncion | Saug-Sonlon-Longanapan | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
Asuncion | Saug-Sonlon-Longanapan | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started: | 2020-01-02
Asuncion | Saug-Sonlon-Longanapan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 010 - Saug - Sonlon - Bdry. Longanapan |  | GENERAL FUND CY 2020 | Maintenance | 11.6 | km | CBRMC | Project Cost: | 197774.7408 | Target Completion Date: |  | Program: | 197774.7408 | Planned: |  | No. of Persons: |  | Purchase Request # 19125310 (On process)
Asuncion | Saug-Sonlon-Longanapan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 197774.7408 | Revised: |  | No. of Man-days:
Asuncion | Saug-Sonlon-Longanapan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Asuncion | Saug-Sonlon-Longanapan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Asuncion | Saug-Sonlon-Longanapan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: |  | Date completed:
Asuncion | Saug-Sonlon-Longanapan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started:
Asuncion | New Visayas-Buan | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 011 - Jct. New Visayas - Buan |  | GENERAL FUND CY 2020 | Maintenance | 2.99 | km | MBA | Project Cost: | 134598.4525 | Target Completion Date: | 2020-12-31 23:59 | Program: | 134598.4525 | Planned: | 7.72% | No. of Persons: | 17 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020)
Asuncion | New Visayas-Buan | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 134598.4525 | Revised: |  | No. of Man-days: | 374
Asuncion | New Visayas-Buan | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 10391.0005 | Actual: | 7.72%
Asuncion | New Visayas-Buan | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0%
Asuncion | New Visayas-Buan | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
Asuncion | New Visayas-Buan | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started: | 2020-01-02
Asuncion | New Visayas-Buan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 011 - Jct. New Visayas - Buan |  | GENERAL FUND CY 2020 | Maintenance | 2.99 | km | CBRMC | Project Cost: | 124786.4436 | Target Completion Date: |  | Program: | 124786.4436 | Planned: |  | No. of Persons: |  | Purchase Request # 19125311 (On process)
Asuncion | New Visayas-Buan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 124786.4436 | Revised: |  | No. of Man-days:
Asuncion | New Visayas-Buan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Asuncion | New Visayas-Buan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Asuncion | New Visayas-Buan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: |  | Date completed:
Asuncion | New Visayas-Buan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started:
Asuncion | San Vicente-Butay | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 013 - San Vicente - Butay |  | GENERAL FUND CY 2020 | Maintenance | 7.52 | km | MBA | Project Cost: | 579541.5407 | Target Completion Date: | 2020-12-31 23:59 | Program: | 579541.5407 | Planned: | 30.2% | No. of Persons: | 17 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020)
Asuncion | San Vicente-Butay | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 579541.5407 | Revised: |  | No. of Man-days: | 374
Asuncion | San Vicente-Butay | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 123616.2106 | Actual: | 30.2%
Asuncion | San Vicente-Butay | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0%
Asuncion | San Vicente-Butay | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
Asuncion | San Vicente-Butay | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started: | 2020-01-02
Asuncion | San Vicente-Butay | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 013 - San Vicente - Butay |  | GENERAL FUND CY 2020 | Maintenance | 7.52 | km | CBRMC | Project Cost: | 235446.12 | Target Completion Date: |  | Program: | 235446.12 | Planned: |  | No. of Persons: |  | Purchase Request # 19125312 (On process)
Asuncion | San Vicente-Butay | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 235446.12 | Revised: |  | No. of Man-days:
Asuncion | San Vicente-Butay | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Asuncion | San Vicente-Butay | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Asuncion | San Vicente-Butay | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: |  | Date completed:
Asuncion | San Vicente-Butay | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started:
kapalong | Doña Andrea-Capungagan | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 014 - Jct. Highway Doña Andrea - Capungagan |  | GENERAL FUND CY 2020 | Maintenance | 8.7 | km | MBA | Project Cost: | 675845.5865 | Target Completion Date: | 2020-12-31 23:59 | Program: | 675845.5865 | Planned: | 14.87% | No. of Persons: | 17 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020)
kapalong | Doña Andrea-Capungagan | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 675845.5865 | Revised: |  | No. of Man-days: | 374
kapalong | Doña Andrea-Capungagan | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 75289.1983 | Actual: | 14.87%
kapalong | Doña Andrea-Capungagan | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0%
kapalong | Doña Andrea-Capungagan | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
kapalong | Doña Andrea-Capungagan | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started: | 2020-01-02
kapalong | Doña Andrea-Capungagan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 014 - Jct. Highway Doña Andrea - Capungagan |  | GENERAL FUND CY 2020 | Maintenance | 8.7 | km | CBRMC | Project Cost: | 299016.5724 | Target Completion Date: |  | Program: | 299016.5724 | Planned: |  | No. of Persons: |  | Purchase Request # 19125313 (On process)
kapalong | Doña Andrea-Capungagan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 299016.5724 | Revised: |  | No. of Man-days:
kapalong | Doña Andrea-Capungagan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
kapalong | Doña Andrea-Capungagan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
kapalong | Doña Andrea-Capungagan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: |  | Date completed:
kapalong | Doña Andrea-Capungagan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started:
kapalong | Pamacaun-Lasang-banate | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 015 - Pamacaun - Lasang - Banate |  | GENERAL FUND CY 2020 | Maintenance | 4.11 | km | MBA | Project Cost: | 180747.1933 | Target Completion Date: | 2020-12-31 23:59 | Program: | 180747.1933 | Planned: | 8.6% | No. of Persons: | 17 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020)
kapalong | Pamacaun-Lasang-banate | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 180747.1933 | Revised: |  | No. of Man-days: | 374
kapalong | Pamacaun-Lasang-banate | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 15544.2586 | Actual: | 8.6%
kapalong | Pamacaun-Lasang-banate | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0%
kapalong | Pamacaun-Lasang-banate | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
kapalong | Pamacaun-Lasang-banate | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started: | 2020-01-02
kapalong | Pamacaun-Lasang-banate | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 015 - Pamacaun - Lasang - Banate |  | GENERAL FUND CY 2020 | Maintenance | 4.11 | km | CBRMC | Project Cost: | 129495.366 | Target Completion Date: |  | Program: | 129495.366 | Planned: |  | No. of Persons: |  | Purchase Request # 19125314 (On process)
kapalong | Pamacaun-Lasang-banate | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 129495.366 | Revised: |  | No. of Man-days:
kapalong | Pamacaun-Lasang-banate | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
kapalong | Pamacaun-Lasang-banate | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
kapalong | Pamacaun-Lasang-banate | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: |  | Date completed:
kapalong | Pamacaun-Lasang-banate | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started:
kapalong | Semong-Palma Gil | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 018 - Semong - Palma Gil |  | GENERAL FUND CY 2020 | Maintenance | 2.73 | km | MBA | Project Cost: | 276301.31 | Target Completion Date: | 2020-12-31 23:59 | Program: | 276301.31 | Planned: | 50.35% | No. of Persons: | 14 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020)
kapalong | Semong-Palma Gil | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 276301.31 | Revised: |  | No. of Man-days: | 210
kapalong | Semong-Palma Gil | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 139117.7096 | Actual: | 50.35%
kapalong | Semong-Palma Gil | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0%
kapalong | Semong-Palma Gil | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
kapalong | Semong-Palma Gil | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started: | 2020-01-02
kapalong | Semong-Palma Gil | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 018 - Semong - Palma Gil |  | GENERAL FUND CY 2020 | Maintenance | 2.73 | km | CBRMC | Project Cost: | 77697.2196 | Target Completion Date: |  | Program: | 77697.2196 | Planned: |  | No. of Persons: |  | Purchase Request # 19125315 (On process)
kapalong | Semong-Palma Gil | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 77697.2196 | Revised: |  | No. of Man-days:
kapalong | Semong-Palma Gil | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
kapalong | Semong-Palma Gil | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
kapalong | Semong-Palma Gil | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: |  | Date completed:
kapalong | Semong-Palma Gil | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started:
Talaingod | Daligdigon-Dagohoy | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 020 - Daligdigon-Dagohoy |  | GENERAL FUND CY 2020 | Maintenance | 3.34 | km | MBA | Project Cost: | 161826.4 | Target Completion Date: | 2020-12-31 23:59 | Program: | 161826.4 | Planned: | 51.55% | No. of Persons: | 14 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020)
Talaingod | Daligdigon-Dagohoy | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 161826.4 | Revised: |  | No. of Man-days: | 210
Talaingod | Daligdigon-Dagohoy | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 83421.5092 | Actual: | 51.55%
Talaingod | Daligdigon-Dagohoy | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0%
Talaingod | Daligdigon-Dagohoy | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
Talaingod | Daligdigon-Dagohoy | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started: | 2020-01-02
Talaingod | Daligdigon-Dagohoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 020 - Daligdigon-Dagohoy |  | GENERAL FUND CY 2020 | Maintenance | 3.34 | km | CBRMC | Project Cost: | 77697.2196 | Target Completion Date: |  | Program: | 77697.2196 | Planned: |  | No. of Persons: |  | Purchase Request # 19125315 (On process)
Talaingod | Daligdigon-Dagohoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 77697.2196 | Revised: |  | No. of Man-days:
Talaingod | Daligdigon-Dagohoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Talaingod | Daligdigon-Dagohoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Talaingod | Daligdigon-Dagohoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: |  | Date completed:
Talaingod | Daligdigon-Dagohoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started:
Talaingod | Angelo-Dahgohoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 021 - Angelo - Dagohoy |  | GENERAL FUND CY 2020 | Maintenance | 2.19 | km | MBA | Project Cost: | 67286.09 | Target Completion Date: | 2020-12-31 23:59 | Program: | 67286.09 | Planned: | 21.85% | No. of Persons: | 14 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020)
Talaingod | Angelo-Dahgohoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 67286.09 | Revised: |  | No. of Man-days: | 210
Talaingod | Angelo-Dahgohoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 14702.0107 | Actual: | 21.85%
Talaingod | Angelo-Dahgohoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0%
Talaingod | Angelo-Dahgohoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
Talaingod | Angelo-Dahgohoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started: | 2020-01-02
Talaingod | Angelo-Dahgohoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 021 - Angelo - Dagohoy |  | GENERAL FUND CY 2020 | Maintenance | 2.19 | km | CBRMC | Project Cost: | 40025.8404 | Target Completion Date: |  | Program: | 40025.8404 | Planned: |  | No. of Persons: |  | Purchase Request # 19125317 (On process)
Talaingod | Angelo-Dahgohoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 40025.8404 | Revised: |  | No. of Man-days:
Talaingod | Angelo-Dahgohoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Talaingod | Angelo-Dahgohoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Talaingod | Angelo-Dahgohoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: |  | Date completed:
Talaingod | Angelo-Dahgohoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started:
kapalong | Sampao-Mamacao | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 025 - Jct. Sampao - Bdry. Mamacao |  | GENERAL FUND CY 2020 | Maintenance | 4.98 | km | MBA | Project Cost: | 325083.1184 | Target Completion Date: | 2020-12-31 23:59 | Program: | 325083.1184 | Planned: | 14.71% | No. of Persons: | 17 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020)
kapalong | Sampao-Mamacao | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 325083.1184 | Revised: |  | No. of Man-days: | 374
kapalong | Sampao-Mamacao | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 47819.7267 | Actual: | 14.71%
kapalong | Sampao-Mamacao | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0%
kapalong | Sampao-Mamacao | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
kapalong | Sampao-Mamacao | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started: | 2020-01-02
kapalong | Sampao-Mamacao | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 025 - Jct. Sampao - Bdry. Mamacao |  | GENERAL FUND CY 2020 | Maintenance | 4.98 | km | CBRMC | Project Cost: | 178939.0512 | Target Completion Date: |  | Program: | 178939.0512 | Planned: |  | No. of Persons: |  | Purchase Request # 19125318 (On process)
kapalong | Sampao-Mamacao | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 178939.0512 | Revised: |  | No. of Man-days:
kapalong | Sampao-Mamacao | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
kapalong | Sampao-Mamacao | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
kapalong | Sampao-Mamacao | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: |  | Date completed:
kapalong | Sampao-Mamacao | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started:
kapalong | Luna-Mamacao | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 026 - Jct. Highway - Luna - Mamacao - Narra |  | GENERAL FUND CY 2020 | Maintenance | 9.17 | km | MBA | Project Cost: | 361826.1515 | Target Completion Date: | 2020-12-31 23:59 | Program: | 361826.1515 | Planned: | 20.12% | No. of Persons: | 17 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020)
kapalong | Luna-Mamacao | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 361826.1515 | Revised: |  | No. of Man-days: | 374
kapalong | Luna-Mamacao | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 22433.2214 | Actual: | 20.12%
kapalong | Luna-Mamacao | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0%
kapalong | Luna-Mamacao | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
kapalong | Luna-Mamacao | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started: | 2020-01-02
kapalong | Luna-Mamacao | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 026 - Jct. Highway - Luna - Mamacao - Narra |  | GENERAL FUND CY 2020 | Maintenance | 9.17 | km | CBRMC | Project Cost: | 393195.0204 | Target Completion Date: |  | Program: | 393195.0204 | Planned: |  | No. of Persons: |  | Purchase Request # 19125337 (On process)
kapalong | Luna-Mamacao | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 393195.0204 | Revised: |  | No. of Man-days:
kapalong | Luna-Mamacao | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
kapalong | Luna-Mamacao | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
kapalong | Luna-Mamacao | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: |  | Date completed:
kapalong | Luna-Mamacao | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started:
kapalong | Gabuyan-Katipunan | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 027 - Jct. Gabuyan - Katipunan - Bucana |  | GENERAL FUND CY 2020 | Maintenance | 5.89 | km | MBA | Project Cost: | 485762.7577 | Target Completion Date: | 2020-12-31 23:59 | Program: | 485762.7577 | Planned: | 7.86% | No. of Persons: | 17 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020)
kapalong | Gabuyan-Katipunan | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 485762.7577 | Revised: |  | No. of Man-days: | 374
kapalong | Gabuyan-Katipunan | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 38180.9528 | Actual: | 7.86%
kapalong | Gabuyan-Katipunan | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0%
kapalong | Gabuyan-Katipunan | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
kapalong | Gabuyan-Katipunan | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started: | 2020-01-02
kapalong | Gabuyan-Katipunan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 027 - Jct. Gabuyan - Katipunan - Bucana |  | GENERAL FUND CY 2020 | Maintenance | 5.89 | km | CBRMC | Project Cost: | 174230.1288 | Target Completion Date: |  | Program: | 174230.1288 | Planned: |  | No. of Persons: |  | Purchase Request # 19125338 (On process)
kapalong | Gabuyan-Katipunan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 174230.1288 | Revised: |  | No. of Man-days:
kapalong | Gabuyan-Katipunan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
kapalong | Gabuyan-Katipunan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
kapalong | Gabuyan-Katipunan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: |  | Date completed:
kapalong | Gabuyan-Katipunan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started:
kapalong | Capungagan-Mabuhay | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 028 - Capungagan - Mabuhay - Pandulian |  | GENERAL FUND CY 2020 | Maintenance | 5.57 | km | MBA | Project Cost: | 468741.4542 | Target Completion Date: | 2020-12-31 23:59 | Program: | 468741.4542 | Planned: | 5.14% | No. of Persons: | 17 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020)
kapalong | Capungagan-Mabuhay | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 468741.4542 | Revised: |  | No. of Man-days: | 374
kapalong | Capungagan-Mabuhay | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 24093.3107 | Actual: | 5.14%
kapalong | Capungagan-Mabuhay | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0%
kapalong | Capungagan-Mabuhay | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
kapalong | Capungagan-Mabuhay | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started: | 2020-01-02
kapalong | Capungagan-Mabuhay | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 028 - Capungagan - Mabuhay - Pandulian |  | GENERAL FUND CY 2020 | Maintenance | 5.57 | km | CBRMC | Project Cost: | 155394.4392 | Target Completion Date: |  | Program: | 155394.4392 | Planned: |  | No. of Persons: |  | Purchase Request # 19125339 (On process)
kapalong | Capungagan-Mabuhay | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 155394.4392 | Revised: |  | No. of Man-days:
kapalong | Capungagan-Mabuhay | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
kapalong | Capungagan-Mabuhay | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
kapalong | Capungagan-Mabuhay | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: |  | Date completed:
kapalong | Capungagan-Mabuhay | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started:
San Isidro | Kipalili-New Loon | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 034 - Km. 15, Kipalili - New Loon |  | GENERAL FUND CY 2020 | Maintenance | 6.93 | km | MBA | Project Cost: | 490709.8742 | Target Completion Date: | 2020-12-31 23:59 | Program: | 490709.8742 | Planned: | 18.2% | No. of Persons: | 17 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020)
San Isidro | Kipalili-New Loon | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 490709.8742 | Revised: |  | No. of Man-days: | 374
San Isidro | Kipalili-New Loon | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 66393.046 | Actual: | 18.2%
San Isidro | Kipalili-New Loon | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0%
San Isidro | Kipalili-New Loon | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
San Isidro | Kipalili-New Loon | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started: | 2020-01-02
San Isidro | Kipalili-New Loon | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 034 - Km. 15, Kipalili - New Loon |  | GENERAL FUND CY 2020 | Maintenance | 6.93 | km | CBRMC | Project Cost: | 296662.1112 | Target Completion Date: |  | Program: | 296662.1112 | Planned: |  | No. of Persons: |  | Purchase Request # 19125340 (On process)
San Isidro | Kipalili-New Loon | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 296662.1112 | Revised: |  | No. of Man-days:
San Isidro | Kipalili-New Loon | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
San Isidro | Kipalili-New Loon | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
San Isidro | Kipalili-New Loon | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: |  | Date completed:
San Isidro | Kipalili-New Loon | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started:
San Isidro | Suaon-Libuton | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 035 - Jct. Suaon - Libuton |  | GENERAL FUND CY 2020 | Maintenance | 7.26 | km | MBA | Project Cost: | 60919.7962 | Target Completion Date: | 2020-12-31 23:59 | Program: | 60919.7962 | Planned: | 7.12% | No. of Persons: | 17 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020)
San Isidro | Suaon-Libuton | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 60919.7962 | Revised: |  | No. of Man-days: | 374
San Isidro | Suaon-Libuton | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: |  | Actual: | 7.12%
San Isidro | Suaon-Libuton | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0%
San Isidro | Suaon-Libuton | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
San Isidro | Suaon-Libuton | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started: | 2020-01-02
San Isidro | Suaon-Libuton | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 035 - Jct. Suaon - Libuton |  | GENERAL FUND CY 2020 | Maintenance | 7.26 | km | CBRMC | Project Cost: | 96532.9092 | Target Completion Date: |  | Program: | 96532.9092 | Planned: |  | No. of Persons: |  | Purchase Request # 19125341 (On process)
San Isidro | Suaon-Libuton | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 96532.9092 | Revised: |  | No. of Man-days:
San Isidro | Suaon-Libuton | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
San Isidro | Suaon-Libuton | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
San Isidro | Suaon-Libuton | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: |  | Date completed:
San Isidro | Suaon-Libuton | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started:
San Isidro | Monte Dujali-Gupitan | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 037 - Monte Dujali - Gupitan |  | GENERAL FUND CY 2020 | Maintenance | 4.58 | km | MBA | Project Cost: | 224727.1648 | Target Completion Date: | 2020-12-31 23:59 | Program: | 224727.1648 | Planned: | 11.08% | No. of Persons: | 17 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020)
San Isidro | Monte Dujali-Gupitan | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 224727.1648 | Revised: |  | No. of Man-days: | 374
San Isidro | Monte Dujali-Gupitan | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 24899.7699 | Actual: | 11.08%
San Isidro | Monte Dujali-Gupitan | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0%
San Isidro | Monte Dujali-Gupitan | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
San Isidro | Monte Dujali-Gupitan | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started: | 2020-01-02
San Isidro | Monte Dujali-Gupitan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 037 - Monte Dujali - Gupitan |  | GENERAL FUND CY 2020 | Maintenance | 4.58 | km | CBRMC | Project Cost: | 134204.2884 | Target Completion Date: |  | Program: | 134204.2884 | Planned: |  | No. of Persons: |  | Purchase Request # 19125342 (On process)
San Isidro | Monte Dujali-Gupitan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 134204.2884 | Revised: |  | No. of Man-days:
San Isidro | Monte Dujali-Gupitan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
San Isidro | Monte Dujali-Gupitan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
San Isidro | Monte Dujali-Gupitan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: |  | Date completed:
San Isidro | Monte Dujali-Gupitan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started:
San Isidro | Sawata-Mamangan-Pinamuno | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 041 - Sawata - Mamangan - Pinamuno |  | GENERAL FUND CY 2020 | Maintenance | 14.48 | km | MBA | Project Cost: | 1636481.63 | Target Completion Date: | 2021-02-01 23:59 | Program: | 1636481.63 | Planned: | 37.11% | No. of Persons: | 14 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020)
San Isidro | Sawata-Mamangan-Pinamuno | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-02-28 23:59 | Allotment: | 1636481.63 | Revised: |  | No. of Man-days: | 210
San Isidro | Sawata-Mamangan-Pinamuno | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 607298.3329 | Actual: | 37.11%
San Isidro | Sawata-Mamangan-Pinamuno | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0%
San Isidro | Sawata-Mamangan-Pinamuno | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
San Isidro | Sawata-Mamangan-Pinamuno | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started: | 2020-02-03
San Isidro | Sawata-Mamangan-Pinamuno | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 041 - Sawata - Mamangan - Pinamuno |  | GENERAL FUND CY 2020 | Maintenance | 14.48 | km | CBRMC | Project Cost: | 522690.3864 | Target Completion Date: |  | Program: | 522690.3864 | Planned: |  | No. of Persons: |  | Purchase Request # 19125343 (On process)
San Isidro | Sawata-Mamangan-Pinamuno | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 522690.3864 | Revised: |  | No. of Man-days:
San Isidro | Sawata-Mamangan-Pinamuno | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
San Isidro | Sawata-Mamangan-Pinamuno | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
San Isidro | Sawata-Mamangan-Pinamuno | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: |  | Date completed:
San Isidro | Sawata-Mamangan-Pinamuno | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started:
San Isidro | Igangon-Sawata | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 042 - Igangon - Sawata |  | GENERAL FUND CY 2020 | Maintenance | 9.66 | km | MBA | Project Cost: | 111771.1255 | Target Completion Date: | 2020-12-31 23:59 | Program: | 111771.1255 | Planned: | 8.74% | No. of Persons: | 17 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020)
San Isidro | Igangon-Sawata | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 111771.1255 | Revised: |  | No. of Man-days: | 374
San Isidro | Igangon-Sawata | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 9768.7964 | Actual: | 8.74%
San Isidro | Igangon-Sawata | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0%
San Isidro | Igangon-Sawata | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
San Isidro | Igangon-Sawata | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started: | 2020-01-02
San Isidro | Igangon-Sawata | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 042 - Igangon - Sawata |  | GENERAL FUND CY 2020 | Maintenance | 9.66 | km | CBRMC | Project Cost: | 202483.6632 | Target Completion Date: |  | Program: | 202483.6632 | Planned: |  | No. of Persons: |  | Purchase Request # 19125344 (On process)
San Isidro | Igangon-Sawata | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 202483.6632 | Revised: |  | No. of Man-days:
San Isidro | Igangon-Sawata | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
San Isidro | Igangon-Sawata | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
San Isidro | Igangon-Sawata | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: |  | Date completed:
San Isidro | Igangon-Sawata | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started:
San Isidro | Sawata | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 043 - Jct. Sawata - Bdry. Binasbas |  | GENERAL FUND CY 2020 | Maintenance | 0.46 | km | MBA | Project Cost: | 27720.5682 | Target Completion Date: | 2020-12-31 23:59 | Program: | 27720.5682 | Planned: | 10.3% | No. of Persons: | 17 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020)
San Isidro | Sawata | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 27720.5682 | Revised: |  | No. of Man-days: | 374
San Isidro | Sawata | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 2855.2185 | Actual: | 10.3%
San Isidro | Sawata | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0%
San Isidro | Sawata | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
San Isidro | Sawata | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started: | 2020-01-02
San Isidro | Sawata | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 043 - Jct. Sawata - Bdry. Binasbas |  | GENERAL FUND CY 2020 | Maintenance | 0.46 | km | CBRMC | Project Cost: | 18835.6896 | Target Completion Date: |  | Program: | 18835.6896 | Planned: |  | No. of Persons: |  | Purchase Request # 19125345 (On process)
San Isidro | Sawata | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 18835.6896 | Revised: |  | No. of Man-days:
San Isidro | Sawata | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
San Isidro | Sawata | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
San Isidro | Sawata | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: |  | Date completed:
San Isidro | Sawata | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started:
Asuncion | Buan | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 045 - Tagaytay - Buan |  | GENERAL FUND CY 2020 | Maintenance | 4.92 | km | MBA | Project Cost: | 378553.2244 | Target Completion Date: | 2020-12-31 23:59 | Program: | 378553.2244 | Planned: | 27.97% | No. of Persons: | 17 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020)
Asuncion | Buan | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 378553.2244 | Revised: |  | No. of Man-days: | 374
Asuncion | Buan | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 105881.3369 | Actual: | 27.97%
Asuncion | Buan | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0%
Asuncion | Buan | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
Asuncion | Buan | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started: | 2020-01-02
Asuncion | Buan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 045 - Tagaytay - Buan |  | GENERAL FUND CY 2020 | Maintenance | 4.92 | km | CBRMC | Project Cost: | 174230.1288 | Target Completion Date: |  | Program: | 174230.1288 | Planned: |  | No. of Persons: |  | Purchase Request # 19125346 (On process)
Asuncion | Buan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 174230.1288 | Revised: |  | No. of Man-days:
Asuncion | Buan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Asuncion | Buan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Asuncion | Buan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: |  | Date completed:
Asuncion | Buan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started:
New Corella | Limbann-Sto. Niño | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 049 - Limbaan - Sto. Niño |  | GENERAL FUND CY 2020 | Maintenance | 3.19 | km | MBA | Project Cost: | 322857.58 | Target Completion Date: | 2021-02-01 23:59 | Program: | 322857.58 | Planned: | 30.02% | No. of Persons: | 14 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020)
New Corella | Limbann-Sto. Niño | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-02-28 23:59 | Allotment: | 322857.58 | Revised: |  | No. of Man-days: | 210
New Corella | Limbann-Sto. Niño | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 96921.8455 | Actual: | 30.02%
New Corella | Limbann-Sto. Niño | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | Limbann-Sto. Niño | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
New Corella | Limbann-Sto. Niño | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started: | 2020-02-03
New Corella | Limbann-Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 049 - Limbaan - Sto. Niño |  | GENERAL FUND CY 2020 | Maintenance | 3.19 | km | CBRMC | Project Cost: | 127140.9048 | Target Completion Date: |  | Program: | 127140.9048 | Planned: |  | No. of Persons: |  | Purchase Request # 20010072 (On process)
New Corella | Limbann-Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 127140.9048 | Revised: |  | No. of Man-days:
New Corella | Limbann-Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
New Corella | Limbann-Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | Limbann-Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: |  | Date completed:
New Corella | Limbann-Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started:
New Corella | Monte Carlo | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 050 - Jct. Monte Carlo - Upper Cabaywa - Canatan |  | GENERAL FUND CY 2020 | Maintenance | 4.61 | km | MBA | Project Cost: | 285065.7818 | Target Completion Date: | 2020-12-31 23:59 | Program: | 285065.7818 | Planned: | 47.46% | No. of Persons: | 17 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020)
New Corella | Monte Carlo | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 285065.7818 | Revised: |  | No. of Man-days: | 374
New Corella | Monte Carlo | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 135292.2201 | Actual: | 47.46%
New Corella | Monte Carlo | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | Monte Carlo | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
New Corella | Monte Carlo | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started: | 2020-01-02
New Corella | Monte Carlo | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 050 - Jct. Monte Carlo - Upper Cabaywa - Canatan |  | GENERAL FUND CY 2020 | Maintenance | 4.61 | km | CBRMC | Project Cost: | 197774.7408 | Target Completion Date: |  | Program: | 197774.7408 | Planned: |  | No. of Persons: |  | Purchase Request # 20010074 (On process)
New Corella | Monte Carlo | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 197774.7408 | Revised: |  | No. of Man-days:
New Corella | Monte Carlo | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
New Corella | Monte Carlo | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | Monte Carlo | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: |  | Date completed:
New Corella | Monte Carlo | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started:
New Corella | Del Pilar | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 051 - Del Pilar - Jct. Silangan |  | GENERAL FUND CY 2020 | Maintenance | 4.17 | km | MBA | Project Cost: | 337766.1689 | Target Completion Date: | 2020-12-31 23:59 | Program: | 337766.1689 | Planned: | 5.54% | No. of Persons: |  | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020)
New Corella | Del Pilar | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 337766.1689 | Revised: |  | No. of Man-days:
New Corella | Del Pilar | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 18712.2458 | Actual: | 5.54%
New Corella | Del Pilar | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | Del Pilar | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
New Corella | Del Pilar | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started: | 2020-01-02
New Corella | Del Pilar | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 051 - Del Pilar - Jct. Silangan |  | GENERAL FUND CY 2020 | Maintenance | 4.17 | km | CBRMC | Project Cost: | 129495.366 | Target Completion Date: |  | Program: | 129495.366 | Planned: |  | No. of Persons: |  | Purchase Request # 20010093 (On process)
New Corella | Del Pilar | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 129495.366 | Revised: |  | No. of Man-days:
New Corella | Del Pilar | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
New Corella | Del Pilar | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | Del Pilar | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: |  | Date completed:
New Corella | Del Pilar | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started:
New Corella | New Sambog | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 052 - New Corella - New Sambog - Silangan |  | GENERAL FUND CY 2020 | Maintenance | 5.1 | km | MBA | Project Cost: | 371450.8414 | Target Completion Date: | 2020-12-31 23:59 | Program: | 371450.8414 | Planned: | 8.7% | No. of Persons: | 17 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020)
New Corella | New Sambog | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 371450.8414 | Revised: |  | No. of Man-days: | 374
New Corella | New Sambog | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 32316.2232 | Actual: | 8.7%
New Corella | New Sambog | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | New Sambog | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
New Corella | New Sambog | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started: | 2020-01-02
New Corella | New Sambog | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 052 - New Corella - New Sambog - Silangan |  | GENERAL FUND CY 2020 | Maintenance | 5.1 | km | CBRMC | Project Cost: | 148331.0556 | Target Completion Date: |  | Program: | 148331.0556 | Planned: |  | No. of Persons: |  | Purchase Request # 20010095 (On process)
New Corella | New Sambog | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 148331.0556 | Revised: |  | No. of Man-days:
New Corella | New Sambog | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
New Corella | New Sambog | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | New Sambog | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: |  | Date completed:
New Corella | New Sambog | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started:
New Corella | Poblacion | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 053 - Pob. New Corella - Prk. 10 Pob. |  | GENERAL FUND CY 2020 | Maintenance | 1.3 | km | MBA | Project Cost: | 28149.3653 | Target Completion Date: | 2020-12-31 23:59 | Program: | 28149.3653 | Planned: | 13.38% | No. of Persons: | 17 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020)
New Corella | Poblacion | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 28149.3653 | Revised: |  | No. of Man-days: | 374
New Corella | Poblacion | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 3766.3851 | Actual: | 13.38%
New Corella | Poblacion | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | Poblacion | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
New Corella | Poblacion | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started: | 2020-01-02
New Corella | Poblacion | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 053 - Pob. New Corella - Prk. 10 Pob. |  | GENERAL FUND CY 2020 | Maintenance | 1.3 | km | CBRMC | Project Cost: | 21190.1508 | Target Completion Date: |  | Program: | 21190.1508 | Planned: |  | No. of Persons: |  | Purchase Request # 20010155 (On process)
New Corella | Poblacion | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 21190.1508 | Revised: |  | No. of Man-days:
New Corella | Poblacion | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
New Corella | Poblacion | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | Poblacion | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: |  | Date completed:
New Corella | Poblacion | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started:
New Corella | New Sambog | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 054 - Prk. 7 Pob. - Jct. New Sambog |  | GENERAL FUND CY 2020 | Maintenance | 2.54 | km | MBA | Project Cost: | 171600.7916 | Target Completion Date: | 2020-12-31 23:59 | Program: | 171600.7916 | Planned: | 6.92% | No. of Persons: | 17 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020)
New Corella | New Sambog | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 171600.7916 | Revised: |  | No. of Man-days: | 374
New Corella | New Sambog | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 11874.7748 | Actual: | 6.92%
New Corella | New Sambog | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | New Sambog | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
New Corella | New Sambog | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started: | 2020-01-02
New Corella | New Sambog | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 054 - Prk. 7 Pob. - Jct. New Sambog |  | GENERAL FUND CY 2020 | Maintenance | 2.54 | km | CBRMC | Project Cost: | 113014.1376 | Target Completion Date: |  | Program: | 113014.1376 | Planned: |  | No. of Persons: |  | Purchase Request # 20010158 (On process)
New Corella | New Sambog | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 113014.1376 | Revised: |  | No. of Man-days:
New Corella | New Sambog | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
New Corella | New Sambog | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | New Sambog | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: |  | Date completed:
New Corella | New Sambog | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started:
New Corella | Sta. Fe-Del Monte | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 056 - Sta. Fe - Del Monte |  | GENERAL FUND CY 2020 | Maintenance | 3.34 | km | MBA | Project Cost: | 93676.7241 | Target Completion Date: | 2020-12-31 23:59 | Program: | 93676.7241 | Planned: | 11.64% | No. of Persons: | 17 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020)
New Corella | Sta. Fe-Del Monte | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 93676.7241 | Revised: |  | No. of Man-days: | 374
New Corella | Sta. Fe-Del Monte | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 10903.9707 | Actual: | 11.64%
New Corella | Sta. Fe-Del Monte | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | Sta. Fe-Del Monte | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
New Corella | Sta. Fe-Del Monte | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started: | 2020-01-02
New Corella | Sta. Fe-Del Monte | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 056 - Sta. Fe - Del Monte |  | GENERAL FUND CY 2020 | Maintenance | 3.34 | km | CBRMC | Project Cost: | 75342.7584 | Target Completion Date: |  | Program: | 75342.7584 | Planned: |  | No. of Persons: |  | Purchase Request # 20010160 (On process)
New Corella | Sta. Fe-Del Monte | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 75342.7584 | Revised: |  | No. of Man-days:
New Corella | Sta. Fe-Del Monte | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
New Corella | Sta. Fe-Del Monte | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | Sta. Fe-Del Monte | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: |  | Date completed:
New Corella | Sta. Fe-Del Monte | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started:
New Corella | New Bohol | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 058 - New Corella - New Bohol |  | GENERAL FUND CY 2020 | Maintenance | 11.54 | km | MBA | Project Cost: | 300034.9027 | Target Completion Date: | 2020-12-31 23:59 | Program: | 300034.9027 | Planned: | 17.21% | No. of Persons: | 17 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020)
New Corella | New Bohol | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 300034.9027 | Revised: |  | No. of Man-days: | 374
New Corella | New Bohol | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 51636.0068 | Actual: | 17.21%
New Corella | New Bohol | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | New Bohol | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
New Corella | New Bohol | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started: | 2020-01-02
New Corella | New Bohol | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 058 - New Corella - New Bohol |  | GENERAL FUND CY 2020 | Maintenance | 11.54 | km | CBRMC | Project Cost: | 221319.3528 | Target Completion Date: |  | Program: | 221319.3528 | Planned: |  | No. of Persons: |  | Purchase Request # 20010221 (On process)
New Corella | New Bohol | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 221319.3528 | Revised: |  | No. of Man-days:
New Corella | New Bohol | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
New Corella | New Bohol | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | New Bohol | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: |  | Date completed:
New Corella | New Bohol | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started:
New Corella | Carcor | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 059 - Jct. Carcor - Prk. 9 Bagsak |  | GENERAL FUND CY 2020 | Maintenance | 2.5 | km | MBA | Project Cost: | 161961.791 | Target Completion Date: | 2020-12-31 23:59 | Program: | 161961.791 | Planned: | 15.82% | No. of Persons: | 17 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020)
New Corella | Carcor | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 161961.791 | Revised: |  | No. of Man-days: | 374
New Corella | Carcor | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 25622.3553 | Actual: | 15.82%
New Corella | Carcor | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | Carcor | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
New Corella | Carcor | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started: | 2020-01-02
New Corella | Carcor | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 059 - Jct. Carcor - Prk. 9 Bagsak |  | GENERAL FUND CY 2020 | Maintenance | 2.5 | km | CBRMC | Project Cost: | 72988.2972 | Target Completion Date: |  | Program: | 72988.2972 | Planned: |  | No. of Persons: |  | Purchase Request # 20010223 (On process)
New Corella | Carcor | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 72988.2972 | Revised: |  | No. of Man-days:
New Corella | Carcor | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
New Corella | Carcor | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | Carcor | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: |  | Date completed:
New Corella | Carcor | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started:
New Corella | Carcor | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 060 - Carcor - Jct. Kauswagan |  | GENERAL FUND CY 2020 | Maintenance | 4.32 | km | MBA | Project Cost: | 304751.9237 | Target Completion Date: | 2020-12-31 23:59 | Program: | 304751.9237 | Planned: | 31.32% | No. of Persons: | 17 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020)
New Corella | Carcor | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 304751.9237 | Revised: |  | No. of Man-days: | 374
New Corella | Carcor | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 95448.3025 | Actual: | 31.32%
New Corella | Carcor | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | Carcor | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
New Corella | Carcor | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started: | 2020-01-02
New Corella | Carcor | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 060 - Carcor - Jct. Kauswagan |  | GENERAL FUND CY 2020 | Maintenance | 4.32 | km | CBRMC | Project Cost: | 101241.8316 | Target Completion Date: |  | Program: | 101241.8316 | Planned: |  | No. of Persons: |  | Purchase Request # 20010262 (On process)
New Corella | Carcor | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 101241.8316 | Revised: |  | No. of Man-days:
New Corella | Carcor | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
New Corella | Carcor | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | Carcor | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: |  | Date completed:
New Corella | Carcor | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started:
New Corella | Del Pilar | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 061 - Del Pilar - Prk. 9 Bagsak - San Jose |  | GENERAL FUND CY 2020 | Maintenance |  | km | MBA | Project Cost: | 505304.26 | Target Completion Date: | 2021-01-14 23:59 | Program: | 505304.26 | Planned: | 49.18% | No. of Persons: | 14 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020)
New Corella | Del Pilar | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-02-10 23:59 | Allotment: | 505304.26 | Revised: |  | No. of Man-days: | 210
New Corella | Del Pilar | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 248508.6351 | Actual: | 49.18%
New Corella | Del Pilar | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | Del Pilar | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
New Corella | Del Pilar | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started: | 2020-01-16
New Corella | Del Pilar | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 061 - Del Pilar - Prk. 9 Bagsak - San Jose |  | GENERAL FUND CY 2020 | Maintenance |  | km | CBRMC | Project Cost: | 251927.3484 | Target Completion Date: |  | Program: | 251927.3484 | Planned: |  | No. of Persons: |  | Purchase Request # 20010264 (On process)
New Corella | Del Pilar | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 251927.3484 | Revised: |  | No. of Man-days:
New Corella | Del Pilar | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
New Corella | Del Pilar | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | Del Pilar | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: |  | Date completed:
New Corella | Del Pilar | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started:
New Corella | Del Pilar | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 062 - Del Pilar - El Unido |  | GENERAL FUND CY 2020 | Maintenance | 1.32 | km | MBA | Project Cost: | 84027.808 | Target Completion Date: | 2020-12-31 23:59 | Program: | 84027.808 | Planned: | 10.78% | No. of Persons: | 17 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020)
New Corella | Del Pilar | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 84027.808 | Revised: |  | No. of Man-days: | 374
New Corella | Del Pilar | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 9058.1977 | Actual: | 10.78%
New Corella | Del Pilar | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | Del Pilar | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
New Corella | Del Pilar | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started: | 2020-01-02
New Corella | Del Pilar | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 062 - Del Pilar - El Unido |  | GENERAL FUND CY 2020 | Maintenance | 1.32 | km | CBRMC | Project Cost: | 40025.8404 | Target Completion Date: |  | Program: | 40025.8404 | Planned: |  | No. of Persons: |  | Purchase Request # 20010265 (On process)
New Corella | Del Pilar | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 40025.8404 | Revised: |  | No. of Man-days:
New Corella | Del Pilar | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
New Corella | Del Pilar | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | Del Pilar | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: |  | Date completed:
New Corella | Del Pilar | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started:
New Corella | Del Pilar | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 063 - San Juan - New Talisay |  | GENERAL FUND CY 2020 | Maintenance | 5.13 | km | MBA | Project Cost: | 442982.6933 | Target Completion Date: | 2020-12-31 23:59 | Program: | 442982.6933 | Planned: | 13.42% | No. of Persons: | 17 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020)
New Corella | Del Pilar | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 442982.6933 | Revised: |  | No. of Man-days: | 374
New Corella | Del Pilar | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 59448.2774 | Actual: | 13.42%
New Corella | Del Pilar | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | Del Pilar | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
New Corella | Del Pilar | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started: | 2020-01-02
New Corella | Del Pilar | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 063 - San Juan - New Talisay |  | GENERAL FUND CY 2020 | Maintenance | 5.13 | km | CBRMC | Project Cost: | 131849.8272 | Target Completion Date: |  | Program: | 131849.8272 | Planned: |  | No. of Persons: |  | Purchase Request # 20010267 (On process)
New Corella | Del Pilar | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 131849.8272 | Revised: |  | No. of Man-days:
New Corella | Del Pilar | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
New Corella | Del Pilar | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | Del Pilar | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: |  | Date completed:
New Corella | Del Pilar | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started:
New Corella | Del Pilar | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 064 - San Juan - Kauswagan - New Cortez |  | GENERAL FUND CY 2020 | Maintenance | 3.22 | km | MBA | Project Cost: | 128969.53 | Target Completion Date: | 2021-01-14 23:59 | Program: | 128969.53 | Planned: | 41.14% | No. of Persons: | 14 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020)
New Corella | Del Pilar | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-02-10 23:59 | Allotment: | 128969.53 | Revised: |  | No. of Man-days: | 210
New Corella | Del Pilar | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 53058.0646 | Actual: | 41.14%
New Corella | Del Pilar | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage:
New Corella | Del Pilar | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
New Corella | Del Pilar | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started: | 2020-01-16
New Corella | Del Pilar | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 064 - San Juan - Kauswagan - New Cortez |  | GENERAL FUND CY 2020 | Maintenance | 3.22 | km | CBRMC | Project Cost: | 68279.3748 | Target Completion Date: |  | Program: | 68279.3748 | Planned: |  | No. of Persons: |  | Procurement on process
New Corella | Del Pilar | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 68279.3748 | Revised: |  | No. of Man-days:
New Corella | Del Pilar | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
New Corella | Del Pilar | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | Del Pilar | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: |  | Date completed:
New Corella | Del Pilar | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started:
New Corella | New Bohol | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 065 - New Bohol - Jct. El Unido |  | GENERAL FUND CY 2020 | Maintenance | 2.12 | km | MBA | Project Cost: | 177260.81 | Target Completion Date: | 2021-01-14 23:59 | Program: | 177260.81 | Planned: |  | No. of Persons: | 14 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020)
New Corella | New Bohol | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-02-10 23:59 | Allotment: | 177260.81 | Revised: |  | No. of Man-days: | 210
New Corella | New Bohol | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 50005.2745 | Actual: | 28.21%
New Corella | New Bohol | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | #VALUE!
New Corella | New Bohol | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
New Corella | New Bohol | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started: | 2020-01-16
New Corella | New Bohol | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 065 - New Bohol - Jct. El Unido |  | GENERAL FUND CY 2020 | Maintenance | 2.12 | km | CBRMC | Project Cost: | 65924.9136 | Target Completion Date: |  | Program: | 65924.9136 | Planned: |  | No. of Persons: |  | Purchase Request # 20010275 (On process)
New Corella | New Bohol | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 65924.9136 | Revised: |  | No. of Man-days:
New Corella | New Bohol | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
New Corella | New Bohol | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | New Bohol | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: |  | Date completed:
New Corella | New Bohol | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started:
New Corella | Mesaoy | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 066 - New Corella - El Unido - Jct. Mesaoy |  | GENERAL FUND CY 2020 | Maintenance | 8.63 | km | MBA | Project Cost: | 792432.45 | Target Completion Date: | 2021-01-14 23:59 | Program: | 792432.45 | Planned: | 53.98% | No. of Persons: | 14 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020)
New Corella | Mesaoy | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-02-10 23:59 | Allotment: | 792432.45 | Revised: |  | No. of Man-days: | 210
New Corella | Mesaoy | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 427755.0365 | Actual: | 53.98%
New Corella | Mesaoy | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | Mesaoy | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
New Corella | Mesaoy | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started: | 2020-01-16
New Corella | Mesaoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 066 - New Corella - El Unido - Jct. Mesaoy |  | GENERAL FUND CY 2020 | Maintenance | 8.63 | km | CBRMC | Project Cost: | 249572.8872 | Target Completion Date: |  | Program: | 249572.8872 | Planned: |  | No. of Persons: |  | Purchase Request # 20010291 (On process)
New Corella | Mesaoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 249572.8872 | Revised: |  | No. of Man-days:
New Corella | Mesaoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
New Corella | Mesaoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | Mesaoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: |  | Date completed:
New Corella | Mesaoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started:
New Corella | Mesaoy | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 067 - Mesaoy - Dasing |  | GENERAL FUND CY 2020 | Maintenance | 1.39 | km | MBA | Project Cost: | 130632.25 | Target Completion Date: | 2021-01-14 23:59 | Program: | 130632.25 | Planned: | 48.79% | No. of Persons: | 14 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020)
New Corella | Mesaoy | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-02-10 23:59 | Allotment: | 130632.25 | Revised: |  | No. of Man-days: | 210
New Corella | Mesaoy | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 63735.4748 | Actual: | 48.79%
New Corella | Mesaoy | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | Mesaoy | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
New Corella | Mesaoy | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started: | 2020-01-16
New Corella | Mesaoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 067 - Mesaoy - Dasing |  | GENERAL FUND CY 2020 | Maintenance | 1.39 | km | CBRMC | Project Cost: | 54152.6076 | Target Completion Date: |  | Program: | 54152.6076 | Planned: |  | No. of Persons: |  | Purchase Request # 20010294 (On process)
New Corella | Mesaoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 54152.6076 | Revised: |  | No. of Man-days:
New Corella | Mesaoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
New Corella | Mesaoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | Mesaoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: |  | Date completed:
New Corella | Mesaoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started:
New Corella | Del Pilar | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 068 - Jct. San Juan - Jct. Mesaoy |  | GENERAL FUND CY 2020 | Maintenance | 1.82 | km | MBA | Project Cost: | 135657.3072 | Target Completion Date: | 2020-12-31 23:59 | Program: | 135657.3072 | Planned: | 7.32% | No. of Persons: | 17 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020)
New Corella | Del Pilar | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 135657.3072 | Revised: |  | No. of Man-days: | 374
New Corella | Del Pilar | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 9930.1149 | Actual: | 7.32%
New Corella | Del Pilar | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | Del Pilar | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
New Corella | Del Pilar | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started: | 2020-01-02
New Corella | Del Pilar | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 068 - Jct. San Juan - Jct. Mesaoy |  | GENERAL FUND CY 2020 | Maintenance | 1.82 | km | CBRMC | Project Cost: | 68279.3748 | Target Completion Date: |  | Program: | 68279.3748 | Planned: |  | No. of Persons: |  | Purchase Request # 20010294 (On process)
New Corella | Del Pilar | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 68279.3748 | Revised: |  | No. of Man-days:
New Corella | Del Pilar | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
New Corella | Del Pilar | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | Del Pilar | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: |  | Date completed:
New Corella | Del Pilar | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started:
New Corella | Mesaoy-New Bohol | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 070 - Mesaoy - New Bohol |  | GENERAL FUND CY 2020 | Maintenance | 5.36 | km | MBA | Project Cost: | 665667.84 | Target Completion Date: | 2021-01-14 23:59 | Program: | 665667.84 | Planned: | 41.99% | No. of Persons: | 14 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020)
New Corella | Mesaoy-New Bohol | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-02-10 23:59 | Allotment: | 665667.84 | Revised: |  | No. of Man-days: | 210
New Corella | Mesaoy-New Bohol | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 279513.926 | Actual: | 41.99%
New Corella | Mesaoy-New Bohol | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | Mesaoy-New Bohol | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
New Corella | Mesaoy-New Bohol | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started: | 2020-01-16
New Corella | Mesaoy-New Bohol | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 070 - Mesaoy - New Bohol |  | GENERAL FUND CY 2020 | Maintenance | 5.36 | km | CBRMC | Project Cost: | 261345.1932 | Target Completion Date: |  | Program: | 261345.1932 | Planned: |  | No. of Persons: |  | Purchase Request # 20010298 (On process)
New Corella | Mesaoy-New Bohol | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 261345.1932 | Revised: |  | No. of Man-days:
New Corella | Mesaoy-New Bohol | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
New Corella | Mesaoy-New Bohol | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | Mesaoy-New Bohol | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: |  | Date completed:
New Corella | Mesaoy-New Bohol | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started:
Asuncion | Napungas | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 147 - Prk. 1, Maunlom-Prk. 6 Maunlom Road |  | GENERAL FUND CY 2020 | Maintenance | 3.56 | km | MBA | Project Cost: | 115812.32 | Target Completion Date: | 2021-02-15 23:59 | Program: | 115812.32 | Planned: | 38.9% | No. of Persons: | 14 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020)
Asuncion | Napungas | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-03-14 23:59 | Allotment: | 115812.32 | Revised: |  | No. of Man-days: | 210
Asuncion | Napungas | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 45050.9925 | Actual: | 38.9%
Asuncion | Napungas | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0%
Asuncion | Napungas | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
Asuncion | Napungas | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started: | 2020-02-17
Asuncion | Napungas | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 147 - Prk. 1, Maunlom-Prk. 6 Maunlom Road |  | GENERAL FUND CY 2020 | Maintenance | 3.56 | km | CBRMC | Project Cost: | 65924.9136 | Target Completion Date: |  | Program: | 65924.9136 | Planned: |  | No. of Persons: |  | Purchase Request # 20010302 (On process)
Asuncion | Napungas | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 65924.9136 | Revised: |  | No. of Man-days:
Asuncion | Napungas | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Asuncion | Napungas | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Asuncion | Napungas | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: |  | Date completed:
Asuncion | Napungas | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started:
Asuncion | Binancian | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 149 - New Visayas - Binancian |  | GENERAL FUND CY 2020 | Maintenance | 7.77 | km | MBA | Project Cost: | 62394.7204 | Target Completion Date: | 2020-12-31 23:59 | Program: | 62394.7204 | Planned: | 3.47% | No. of Persons: | 17 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020)
Asuncion | Binancian | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 62394.7204 | Revised: |  | No. of Man-days: | 374
Asuncion | Binancian | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 2165.0968 | Actual: | 3.47%
Asuncion | Binancian | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0%
Asuncion | Binancian | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
Asuncion | Binancian | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started: | 2020-01-02
Asuncion | Binancian | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 149 - New Visayas - Binancian |  | GENERAL FUND CY 2020 | Maintenance | 7.77 | km | CBRMC | Project Cost: | 134204.2884 | Target Completion Date: |  | Program: | 134204.2884 | Planned: |  | No. of Persons: |  | Purchase Request # 20010305 (On process)
Asuncion | Binancian | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 134204.2884 | Revised: |  | No. of Man-days:
Asuncion | Binancian | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Asuncion | Binancian | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Asuncion | Binancian | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: |  | Date completed:
Asuncion | Binancian | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started:
San Isidro | Datu Balong-Mamalian | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 150 - Datu Balong - Prk. Mamalian |  | GENERAL FUND CY 2020 | Maintenance | 3.46 | km | MBA | Project Cost: | 45089.8864 | Target Completion Date: | 2020-12-31 23:59 | Program: | 45089.8864 | Planned: | 6.37% | No. of Persons: | 17 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020)
San Isidro | Datu Balong-Mamalian | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 45089.8864 | Revised: |  | No. of Man-days: | 374
San Isidro | Datu Balong-Mamalian | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 2872.2258 | Actual: | 6.37%
San Isidro | Datu Balong-Mamalian | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0%
San Isidro | Datu Balong-Mamalian | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | 2 | 2020-01-02 | Date completed:
San Isidro | Datu Balong-Mamalian | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started: | 2020-01-02
San Isidro | Datu Balong-Mamalian | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 150 - Datu Balong - Prk. Mamalian |  | GENERAL FUND CY 2020 | Maintenance | 3.46 | km | CBRMC | Project Cost: | 61215.9912 | Target Completion Date: |  | Program: | 61215.9912 | Planned: |  | No. of Persons: |  | Purchase Request # 20010306 (On process)
San Isidro | Datu Balong-Mamalian | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 61215.9912 | Revised: |  | No. of Man-days:
San Isidro | Datu Balong-Mamalian | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
San Isidro | Datu Balong-Mamalian | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
San Isidro | Datu Balong-Mamalian | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: |  | Date completed:
San Isidro | Datu Balong-Mamalian | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started:
Tagum City | Cuambogan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | RURAL ELECTRIFICATION PROJECT LS - P 5,000,000.00 | Rural Electrification at RAMADA Compound Purok Sto. Niño, Brgy. Cuambogan, Tagum City |  | 20% Development Fund CY 2020 | Electrification |  | km |  | Project Cost: | 1000000 | Target Completion Date: |  | Program: | 1000000 | Planned: |  | No. of Persons: |  | PO on process - Tagum Constrak
Tagum City | Cuambogan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | RURAL ELECTRIFICATION PROJECT LS - P 5,000,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 1000000 | Revised: |  | No. of Man-days:
Tagum City | Cuambogan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | RURAL ELECTRIFICATION PROJECT LS - P 5,000,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Tagum City | Cuambogan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | RURAL ELECTRIFICATION PROJECT LS - P 5,000,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Tagum City | Cuambogan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | RURAL ELECTRIFICATION PROJECT LS - P 5,000,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Tagum City | Cuambogan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | RURAL ELECTRIFICATION PROJECT LS - P 5,000,000.00 | [7 empty] | Date Started:
Asuncion | Camansa | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | RURAL ELECTRIFICATION PROJECT LS - P 5,000,000.00 | Rural Electrification at Lower Camansa, Prk.5 to 6 Lower, Brgy. Camansa, Asuncion |  | 20% Development Fund CY 2020 | Electrification |  | km |  | Project Cost: | 3000000 | Target Completion Date: |  | Program: | 3000000 | Planned: |  | No. of Persons: |  | PO on process - Tagum Constrak
Asuncion | Camansa | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | RURAL ELECTRIFICATION PROJECT LS - P 5,000,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 3000000 | Revised: |  | No. of Man-days:
Asuncion | Camansa | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | RURAL ELECTRIFICATION PROJECT LS - P 5,000,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Asuncion | Camansa | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | RURAL ELECTRIFICATION PROJECT LS - P 5,000,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Asuncion | Camansa | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | RURAL ELECTRIFICATION PROJECT LS - P 5,000,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Asuncion | Camansa | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | RURAL ELECTRIFICATION PROJECT LS - P 5,000,000.00 | [7 empty] | Date Started:
Asuncion | Doña Andrea | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | RURAL ELECTRIFICATION PROJECT LS - P 5,000,000.00 | Completion of Electrification at at Purok 10 and Purok 9, Phase 2, Brgy. Doña Andrea, Asuncion |  | 20% Development Fund CY 2020 | Electrification |  | km |  | Project Cost: | 1000000 | Target Completion Date: |  | Program: | 1000000 | Planned: |  | No. of Persons: |  | For preparation of POW and Plans
Asuncion | Doña Andrea | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | RURAL ELECTRIFICATION PROJECT LS - P 5,000,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 1000000 | Revised: |  | No. of Man-days:
Asuncion | Doña Andrea | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | RURAL ELECTRIFICATION PROJECT LS - P 5,000,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Asuncion | Doña Andrea | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | RURAL ELECTRIFICATION PROJECT LS - P 5,000,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Asuncion | Doña Andrea | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | RURAL ELECTRIFICATION PROJECT LS - P 5,000,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Asuncion | Doña Andrea | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | RURAL ELECTRIFICATION PROJECT LS - P 5,000,000.00 | [7 empty] | Date Started:
Asuncion | Sta. Felomina | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | ROAD ID 008 - Sta. Felomina - San Roque |  | 20% Development Fund CY 2020 | Road Rehabilitaion | 7.68 | km | Admin | Project Cost: | 2304000 | Target Completion Date: |  | Program: | 2304000 | Planned: |  | No. of Persons: |  | Post qualification on process
Asuncion | Sta. Felomina | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 2304000 | Revised: |  | No. of Man-days:
Asuncion | Sta. Felomina | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual:
Asuncion | Sta. Felomina | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Asuncion | Sta. Felomina | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Asuncion | Sta. Felomina | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Date Started:
Talaingod | Sto. Niño-Palma Gil | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | ROAD ID 019 - Sto. Niño - Palma Gil - Sitio Opao |  | 20% Development Fund CY 2020 | Road Rehabilitaion | 5.99 | km | Admin | Project Cost: | 1797000 | Target Completion Date: |  | Program: | 1797000 | Planned: |  | No. of Persons: |  | POW on process
Talaingod | Sto. Niño-Palma Gil | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 1797000 | Revised: |  | No. of Man-days:
Talaingod | Sto. Niño-Palma Gil | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual:
Talaingod | Sto. Niño-Palma Gil | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Talaingod | Sto. Niño-Palma Gil | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Talaingod | Sto. Niño-Palma Gil | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Date Started:
Talaingod | Daligdigon-Paiton | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | ROAD ID 023 - Sto. Niño - Daligdigon - Paiton |  | 20% Development Fund CY 2020 | Road Rehabilitaion | 11.6 | km | Admin | Project Cost: | 3480000 | Target Completion Date: |  | Program: | 3480000 | Planned: |  | No. of Persons: |  | POW on process
Talaingod | Daligdigon-Paiton | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 3480000 | Revised: |  | No. of Man-days:
Talaingod | Daligdigon-Paiton | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual:
Talaingod | Daligdigon-Paiton | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Talaingod | Daligdigon-Paiton | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Talaingod | Daligdigon-Paiton | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Date Started:
Talaingod | Paiton | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | ROAD ID 024 - Jct. Paiton - Mibolo |  | 20% Development Fund CY 2020 | Road Rehabilitaion | 23.9 | km | Admin | Project Cost: | 7170000 | Target Completion Date: |  | Program: | 7170000 | Planned: |  | No. of Persons: |  | POW on process
Talaingod | Paiton | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 7170000 | Revised: |  | No. of Man-days:
Talaingod | Paiton | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual:
Talaingod | Paiton | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Talaingod | Paiton | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Talaingod | Paiton | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Date Started:
Kapalong | Florida | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | ROAD ID 024 - Florida - Suaon - Jct. Gupitan |  | 20% Development Fund CY 2020 | Road Rehabilitaion | 15.57 | km | Admin | Project Cost: | 4671000 | Target Completion Date: |  | Program: | 4671000 | Planned: |  | No. of Persons: |  | PO on process - Royal Summit
Kapalong | Florida | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 4671000 | Revised: |  | No. of Man-days:
Kapalong | Florida | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual:
Kapalong | Florida | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Kapalong | Florida | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Kapalong | Florida | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Date Started:
San Isidro | Datu Balong | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | ROAD ID 040 - Datu Balong - Pinamuno |  | 20% Development Fund CY 2020 | Road Rehabilitaion | 2.74 | km | Admin | Project Cost: | 822000 | Target Completion Date: |  | Program: | 822000 | Planned: |  | No. of Persons: |  | POW on process
San Isidro | Datu Balong | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 822000 | Revised: |  | No. of Man-days:
San Isidro | Datu Balong | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual:
San Isidro | Datu Balong | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
San Isidro | Datu Balong | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
San Isidro | Datu Balong | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Date Started:
New Corella | Macgum | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | ROAD ID 048 - New Corella - Saug |  | 20% Development Fund CY 2020 | Road Rehabilitaion | 12.52 | km | Admin | Project Cost: | 20571000 | Target Completion Date: |  | Program: | 20571000 | Planned: |  | No. of Persons: |  | POW on process
New Corella | Macgum | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 20571000 | Revised: |  | No. of Man-days:
New Corella | Macgum | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual:
New Corella | Macgum | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | Macgum | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
New Corella | Macgum | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Date Started:
Asuncion | Canatan-Doña andrea | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | ROAD ID 074 - Jct. Highway Canatan - Doña Andrea |  | 20% Development Fund CY 2020 | Road Rehabilitaion | 4.34 | km | Admin | Project Cost: | 1302000 | Target Completion Date: |  | Program: | 1302000 | Planned: |  | No. of Persons: |  | POW on process
Asuncion | Canatan-Doña andrea | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 1302000 | Revised: |  | No. of Man-days:
Asuncion | Canatan-Doña andrea | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Asuncion | Canatan-Doña andrea | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Asuncion | Canatan-Doña andrea | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Asuncion | Canatan-Doña andrea | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Date Started:
Kapalong | Florida | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | ROAD ID 030 - Florida - New Boholano |  | 20% Development Fund CY 2020 | Road Rehabilitaion | 2.54 | km | Admin | Project Cost: | 762000 | Target Completion Date: |  | Program: | 762000 | Planned: |  | No. of Persons: |  | POW on process
Kapalong | Florida | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 762000 | Revised: |  | No. of Man-days:
Kapalong | Florida | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual:
Kapalong | Florida | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Kapalong | Florida | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Kapalong | Florida | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Date Started:
Asuncion | New Loon | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | ROAD ID 031 - Jct. New Boholano - New Loon |  | 20% Development Fund CY 2020 | Road Rehabilitaion | 4.77 | km | Admin | Project Cost: | 1431000 | Target Completion Date: |  | Program: | 1431000 | Planned: |  | No. of Persons: |  | POW on process
Asuncion | New Loon | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 1431000 | Revised: |  | No. of Man-days:
Asuncion | New Loon | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Asuncion | New Loon | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Asuncion | New Loon | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Asuncion | New Loon | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Date Started:
New Corella | Mesaoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | ROAD ID 069 - Mesaoy - Jct. Mahayahay |  | 20% Development Fund CY 2020 | Road Rehabilitaion | 4.6 | km | Admin | Project Cost: | 1380000 | Target Completion Date: |  | Program: | 1380000 | Planned: |  | No. of Persons: |  | POW on process
New Corella | Mesaoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 1380000 | Revised: |  | No. of Man-days:
New Corella | Mesaoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual:
New Corella | Mesaoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | Mesaoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
New Corella | Mesaoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Date Started:
Asuncion | Cabaywa | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | ROAD ID 071 - Lower Asuncion - Upper Asuncion |  | 20% Development Fund CY 2020 | Road Rehabilitaion |  | km | Admin | Project Cost: | 1302000 | Target Completion Date: |  | Program: | 1302000 | Planned: |  | No. of Persons: |  | Plan On-going
Asuncion | Cabaywa | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 1302000 | Revised: |  | No. of Man-days:
Asuncion | Cabaywa | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Asuncion | Cabaywa | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Asuncion | Cabaywa | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Asuncion | Cabaywa | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Date Started:
Tagum City | AAT | 1st Eng'g. Dist. | On-going | 2020-05-18 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS LOCAL ROADS & DRAINAGE DEV'T. PROJECT - LS P15,590,910.00 | Rehab. Of Various Local Roads @ Tagum City |  | 20% Development Fund CY 2020 | Rehabilitaion |  | km | Admin | Project Cost: | 2518182 | Target Completion Date: | 2020-10-20 | Program: | 2518182 | Planned: | 18.41% | No. of Persons: | 10 | On-going
Tagum City | AAT | 1st Eng'g. Dist. | On-going | 2020-05-18 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS LOCAL ROADS & DRAINAGE DEV'T. PROJECT - LS P15,590,910.00 | [7 empty] | Project Engineer: | Bataller | Revised Completion Date: |  | Allotment: | 2518182 | Revised: |  | No. of Man-days: | 150
Tagum City | AAT | 1st Eng'g. Dist. | On-going | 2020-05-18 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS LOCAL ROADS & DRAINAGE DEV'T. PROJECT - LS P15,590,910.00 | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: | 18.41%
Tagum City | AAT | 1st Eng'g. Dist. | On-going | 2020-05-18 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS LOCAL ROADS & DRAINAGE DEV'T. PROJECT - LS P15,590,910.00 | [7 empty] | Duration: | 155 | No. of days extended: |  |  |  | Slippage: | 0%
Tagum City | AAT | 1st Eng'g. Dist. | On-going | 2020-05-18 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS LOCAL ROADS & DRAINAGE DEV'T. PROJECT - LS P15,590,910.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Tagum City | AAT | 1st Eng'g. Dist. | On-going | 2020-05-18 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS LOCAL ROADS & DRAINAGE DEV'T. PROJECT - LS P15,590,910.00 | [7 empty] | Date Started: | 2020-05-18
Asuncion | AAA | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS LOCAL ROADS & DRAINAGE DEV'T. PROJECT - LS P15,590,910.00 | Rehab. Of Various Local Roads @ Asuncion |  | 20% Development Fund CY 2020 | Rehabilitaion |  | km | Admin | Project Cost: | 2518182 | Target Completion Date: |  | Program: | 2518182 | Planned: |  | No. of Persons: |  | POW on process
Asuncion | AAA | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS LOCAL ROADS & DRAINAGE DEV'T. PROJECT - LS P15,590,910.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 2518182 | Revised: |  | No. of Man-days:
Asuncion | AAA | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS LOCAL ROADS & DRAINAGE DEV'T. PROJECT - LS P15,590,910.00 | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual:
Asuncion | AAA | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS LOCAL ROADS & DRAINAGE DEV'T. PROJECT - LS P15,590,910.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Asuncion | AAA | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS LOCAL ROADS & DRAINAGE DEV'T. PROJECT - LS P15,590,910.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Asuncion | AAA | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS LOCAL ROADS & DRAINAGE DEV'T. PROJECT - LS P15,590,910.00 | [7 empty] | Date Started:
Kapalong | AAK | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS LOCAL ROADS & DRAINAGE DEV'T. PROJECT - LS P15,590,910.00 | Rehab. Of Various Local Roads @ Kapalong |  | 20% Development Fund CY 2020 | Rehabilitaion |  | km | Admin | Project Cost: | 2518182 | Target Completion Date: |  | Program: | 2518182 | Planned: |  | No. of Persons: |  | For Implementation
Kapalong | AAK | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS LOCAL ROADS & DRAINAGE DEV'T. PROJECT - LS P15,590,910.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 2518182 | Revised: |  | No. of Man-days:
Kapalong | AAK | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS LOCAL ROADS & DRAINAGE DEV'T. PROJECT - LS P15,590,910.00 | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual:
Kapalong | AAK | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS LOCAL ROADS & DRAINAGE DEV'T. PROJECT - LS P15,590,910.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Kapalong | AAK | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS LOCAL ROADS & DRAINAGE DEV'T. PROJECT - LS P15,590,910.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Kapalong | AAK | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS LOCAL ROADS & DRAINAGE DEV'T. PROJECT - LS P15,590,910.00 | [7 empty] | Date Started:
New Corella | AAN | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS LOCAL ROADS & DRAINAGE DEV'T. PROJECT - LS P15,590,910.00 | Rehab. Of Various Local Roads @ New Corella |  | 20% Development Fund CY 2020 | Rehabilitaion |  | km | Admin | Project Cost: | 2518182 | Target Completion Date: |  | Program: | 2518182 | Planned: |  | No. of Persons: |  | POW on process
New Corella | AAN | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS LOCAL ROADS & DRAINAGE DEV'T. PROJECT - LS P15,590,910.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 2518182 | Revised: |  | No. of Man-days:
New Corella | AAN | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS LOCAL ROADS & DRAINAGE DEV'T. PROJECT - LS P15,590,910.00 | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual:
New Corella | AAN | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS LOCAL ROADS & DRAINAGE DEV'T. PROJECT - LS P15,590,910.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | AAN | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS LOCAL ROADS & DRAINAGE DEV'T. PROJECT - LS P15,590,910.00 | [7 empty] | Date Allotment Released: |  | Date completed:
New Corella | AAN | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS LOCAL ROADS & DRAINAGE DEV'T. PROJECT - LS P15,590,910.00 | [7 empty] | Date Started:
San Isidro | AAS | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS LOCAL ROADS & DRAINAGE DEV'T. PROJECT - LS P15,590,910.00 | Rehab. Of Various Local Roads @ San Isidro |  | 20% Development Fund CY 2020 | Rehabilitaion |  | km | Admin | Project Cost: | 2518182 | Target Completion Date: |  | Program: | 2518182 | Planned: |  | No. of Persons: |  | POW on process
San Isidro | AAS | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS LOCAL ROADS & DRAINAGE DEV'T. PROJECT - LS P15,590,910.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 2518182 | Revised: |  | No. of Man-days:
San Isidro | AAS | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS LOCAL ROADS & DRAINAGE DEV'T. PROJECT - LS P15,590,910.00 | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual:
San Isidro | AAS | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS LOCAL ROADS & DRAINAGE DEV'T. PROJECT - LS P15,590,910.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
San Isidro | AAS | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS LOCAL ROADS & DRAINAGE DEV'T. PROJECT - LS P15,590,910.00 | [7 empty] | Date Allotment Released: |  | Date completed:
San Isidro | AAS | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS LOCAL ROADS & DRAINAGE DEV'T. PROJECT - LS P15,590,910.00 | [7 empty] | Date Started:
Talaingod | AAT | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS LOCAL ROADS & DRAINAGE DEV'T. PROJECT - LS P15,590,910.00 | Rehab. Of Various Local Roads @ Talaingod |  | 20% Development Fund CY 2020 | Rehabilitaion |  | km | Admin | Project Cost: | 2518182 | Target Completion Date: |  | Program: | 2518182 | Planned: |  | No. of Persons: |  | For Implementation
Talaingod | AAT | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS LOCAL ROADS & DRAINAGE DEV'T. PROJECT - LS P15,590,910.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 2518182 | Revised: |  | No. of Man-days:
Talaingod | AAT | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS LOCAL ROADS & DRAINAGE DEV'T. PROJECT - LS P15,590,910.00 | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual:
Talaingod | AAT | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS LOCAL ROADS & DRAINAGE DEV'T. PROJECT - LS P15,590,910.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Talaingod | AAT | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS LOCAL ROADS & DRAINAGE DEV'T. PROJECT - LS P15,590,910.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Talaingod | AAT | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS LOCAL ROADS & DRAINAGE DEV'T. PROJECT - LS P15,590,910.00 | [7 empty] | Date Started:
Tagum City | Mankilam | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | Construction of DAVNOR Tech-Vocational Center, Government Center, Mankilam, Tagum City |  | 20% Development Fund CY 2020 | Building |  | sq.m | Admin | Project Cost: | 8000000 | Target Completion Date: |  | Program: | 8000000 | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
Tagum City | Mankilam | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 8000000 | Revised: |  | No. of Man-days:
Tagum City | Mankilam | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual:
Tagum City | Mankilam | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Tagum City | Mankilam | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Tagum City | Mankilam | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Date Started:
Tagum City | Mankilam | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | Improvement of PSWDO Bodega Government Cente, Mankilam, Tagum City |  | 20% Development Fund CY 2020 | Building |  | sq.m | Admin | Project Cost: | 1000000 | Target Completion Date: |  | Program: | 1000000 | Planned: |  | No. of Persons: |  | POW and Plans on-going
Tagum City | Mankilam | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 1000000 | Revised: |  | No. of Man-days:
Tagum City | Mankilam | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual:
Tagum City | Mankilam | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Tagum City | Mankilam | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Tagum City | Mankilam | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Date Started:
San Isidro | Mamangan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | Renovation/Improvement of MAFAMCO Consumer's Bldg., Brgy. Mamangan, San Isidro |  | 20% Development Fund CY 2020 | Building |  | sq.m | Contract | Project Cost: | 800000 | Target Completion Date: |  | Program: | 800000 | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
San Isidro | Mamangan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 800000 | Revised: |  | No. of Man-days:
San Isidro | Mamangan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
San Isidro | Mamangan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
San Isidro | Mamangan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
San Isidro | Mamangan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Date Started:
Asuncion | Camansa | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | Construction of IP Council of Women Training Center, Camansa Kamadi District, Asuncion |  | 20% Development Fund CY 2020 | Building |  | sq.m | Admin | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
Asuncion | Camansa | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Asuncion | Camansa | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual:
Asuncion | Camansa | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Asuncion | Camansa | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Asuncion | Camansa | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Date Started:
New Corella | Cabidianan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | Construction of One(1) unit School Building at Cabidianan E/S, New Corella |  | 20% Development Fund CY 2020 | Building |  | sq.m | Contract | Project Cost: | 1300000 | Target Completion Date: |  | Program: | 1300000 | Planned: |  | No. of Persons:
New Corella | Cabidianan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 1300000 | Revised: |  | No. of Man-days:
New Corella | Cabidianan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
New Corella | Cabidianan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | Cabidianan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
New Corella | Cabidianan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Date Started:
Kapalong | Florida | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | Construction of one(1) unit School Building at Kamansi Integrated School, Florida, kapalong |  | 20% Development Fund CY 2020 | Building |  | sq.m | Contract | Project Cost: | 1300000 | Target Completion Date: |  | Program: | 1300000 | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
Kapalong | Florida | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 1300000 | Revised: |  | No. of Man-days:
Kapalong | Florida | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Kapalong | Florida | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Kapalong | Florida | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Kapalong | Florida | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Date Started:
Asuncion | Magatos | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | Construction of one(1) unit School Building at Magatos E/S, Magatos, Asuncion |  | 20% Development Fund CY 2020 | Building |  | sq.m | Contract | Project Cost: | 1300000 | Target Completion Date: |  | Program: | 1300000 | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
Asuncion | Magatos | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 1300000 | Revised: |  | No. of Man-days:
Asuncion | Magatos | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Asuncion | Magatos | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Asuncion | Magatos | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Asuncion | Magatos | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Date Started:
Talaingod | Sta. Cruz | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | Construction of one(1) unit School Building at Sta. Cruz E/S, New Corella |  | 20% Development Fund CY 2020 | Building |  | sq.m |  | Project Cost: | 1300000 | Target Completion Date: |  | Program: | 1300000 | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
Talaingod | Sta. Cruz | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 1300000 | Revised: |  | No. of Man-days:
Talaingod | Sta. Cruz | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Talaingod | Sta. Cruz | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Talaingod | Sta. Cruz | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Talaingod | Sta. Cruz | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Date Started:
Talaingod | Dagohoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | Construction Women Development Center, Dagohoy, Talaingod |  | 20% Development Fund CY 2020 | Building |  | sq.m |  | Project Cost: | 1000000 | Target Completion Date: |  | Program: | 1000000 | Planned: |  | No. of Persons: |  | Post qualification on process
Talaingod | Dagohoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 1000000 | Revised: |  | No. of Man-days:
Talaingod | Dagohoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Talaingod | Dagohoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Talaingod | Dagohoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Talaingod | Dagohoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Date Started:
Asuncion | Cambanogoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | Construction of Municipal Triball Hall, Asuncion |  | 20% Development Fund CY 2020 | Building |  | sq.m | Contract | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
Asuncion | Cambanogoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Asuncion | Cambanogoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Asuncion | Cambanogoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Asuncion | Cambanogoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Asuncion | Cambanogoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Date Started:
Kapalong | Maniki | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | Construction of Municipal Triball Hall, Kapalong |  | 20% Development Fund CY 2020 | Building |  | sq.m | Contract | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
Kapalong | Maniki | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Kapalong | Maniki | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Kapalong | Maniki | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Kapalong | Maniki | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Kapalong | Maniki | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Date Started:
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | Construction of Municipal Triball Hall, Talaingod |  | 20% Development Fund CY 2020 | Building |  | sq.m | Contract | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Date Started:
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | DISASTER PREVENTION AND MITIGATION PROGRAM - FLOOD CONTROL AND SLOPE PROTECTION PROJECT (Revetment of Dike and Slope Protection) | Rehab./Impv't. of Sto. Niño-Daligdigon-Paiton |  | 5% CALAMITY FUND CY 2020 | Road |  | km |  | Project Cost: | 1000000 | Target Completion Date: |  | Program: | 1000000 | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | DISASTER PREVENTION AND MITIGATION PROGRAM - FLOOD CONTROL AND SLOPE PROTECTION PROJECT (Revetment of Dike and Slope Protection) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 1000000 | Revised: |  | No. of Man-days:
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | DISASTER PREVENTION AND MITIGATION PROGRAM - FLOOD CONTROL AND SLOPE PROTECTION PROJECT (Revetment of Dike and Slope Protection) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | DISASTER PREVENTION AND MITIGATION PROGRAM - FLOOD CONTROL AND SLOPE PROTECTION PROJECT (Revetment of Dike and Slope Protection) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | DISASTER PREVENTION AND MITIGATION PROGRAM - FLOOD CONTROL AND SLOPE PROTECTION PROJECT (Revetment of Dike and Slope Protection) | [7 empty] | Date Allotment Released: |  | Date completed:
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | DISASTER PREVENTION AND MITIGATION PROGRAM - FLOOD CONTROL AND SLOPE PROTECTION PROJECT (Revetment of Dike and Slope Protection) | [7 empty] | Date Started:
Asuncion | Sonlon | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | DISASTER PREVENTION AND MITIGATION PROGRAM - FLOOD CONTROL AND SLOPE PROTECTION PROJECT (Improvement of Bridges and Cross Drainage) | Improvement of Saug-Sonlon-Bdry. Longanapan |  | 5% CALAMITY FUND CY 2020 | Road |  | km |  | Project Cost: | 1000000 | Target Completion Date: |  | Program: | 1000000 | Planned: |  | No. of Persons: |  | For preparation of POW and Plans
Asuncion | Sonlon | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | DISASTER PREVENTION AND MITIGATION PROGRAM - FLOOD CONTROL AND SLOPE PROTECTION PROJECT (Improvement of Bridges and Cross Drainage) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 1000000 | Revised: |  | No. of Man-days:
Asuncion | Sonlon | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | DISASTER PREVENTION AND MITIGATION PROGRAM - FLOOD CONTROL AND SLOPE PROTECTION PROJECT (Improvement of Bridges and Cross Drainage) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Asuncion | Sonlon | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | DISASTER PREVENTION AND MITIGATION PROGRAM - FLOOD CONTROL AND SLOPE PROTECTION PROJECT (Improvement of Bridges and Cross Drainage) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Asuncion | Sonlon | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | DISASTER PREVENTION AND MITIGATION PROGRAM - FLOOD CONTROL AND SLOPE PROTECTION PROJECT (Improvement of Bridges and Cross Drainage) | [7 empty] | Date Allotment Released: |  | Date completed:
Asuncion | Sonlon | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | DISASTER PREVENTION AND MITIGATION PROGRAM - FLOOD CONTROL AND SLOPE PROTECTION PROJECT (Improvement of Bridges and Cross Drainage) | [7 empty] | Date Started:
Kapalong | Gupitan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | Const. of 1 Classroom @ Mankay Integrated School, Gupitan, kapalong |  | SEF CY 2020 | Building |  | sq.m |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Opening of Shopping on June 25, 2020
Kapalong | Gupitan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Kapalong | Gupitan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Kapalong | Gupitan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Kapalong | Gupitan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Kapalong | Gupitan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Date Started:
Kapalong | Gupitan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | Const. of 1 Classroom @ Luno-luno E/S, Gupitan, kapalong |  | SEF CY 2020 | Building |  | sq.m |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Opening of Shopping on June 25, 2020
Kapalong | Gupitan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Kapalong | Gupitan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Kapalong | Gupitan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Kapalong | Gupitan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Kapalong | Gupitan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Date Started:
Kapalong | Gupitan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | Const. of 1 Classroom @ Kamunuan E/S, Gupitan, kapalong |  | SEF CY 2020 | Building |  | sq.m |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Opening of Shopping on June 25, 2020
Kapalong | Gupitan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Kapalong | Gupitan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Kapalong | Gupitan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Kapalong | Gupitan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Kapalong | Gupitan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Date Started:
Kapalong | Gupitan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | Const. of 1 Classroom @ Tawinian E/S, Gupitan, kapalong |  | SEF CY 2020 | Building |  | sq.m |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Opening of Shopping on June 25, 2020
Kapalong | Gupitan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Kapalong | Gupitan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Kapalong | Gupitan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Kapalong | Gupitan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Kapalong | Gupitan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Date Started:
Kapalong | Gupitan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | Const. of 1 Classroom @ Aninipot E/S, Gupitan, kapalong |  | SEF CY 2020 | Building |  | sq.m |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Opening of Shopping on June 25, 2020
Kapalong | Gupitan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Kapalong | Gupitan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Kapalong | Gupitan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Kapalong | Gupitan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Kapalong | Gupitan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Date Started:
Kapalong | Gupitan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | Const. of 1 Classroom @ Moling E/S, Gupitan, kapalong |  | SEF CY 2020 | Building |  | sq.m |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Opening of Shopping on June 25, 2020
Kapalong | Gupitan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Kapalong | Gupitan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Kapalong | Gupitan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Kapalong | Gupitan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Kapalong | Gupitan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Date Started:
Talaingod | Dagohoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | Const. of 1 Classroom @ Lomondong E/S, Dagohoy, Talaingod |  | SEF CY 2020 | Building |  | sq.m |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Opening of Shopping on June 25, 2020
Talaingod | Dagohoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Talaingod | Dagohoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Talaingod | Dagohoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Talaingod | Dagohoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Talaingod | Dagohoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Date Started:
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | Const. of 1 Classroom @ Malapanit E/S, Sto. Niño, Talaingod |  | SEF CY 2020 | Building |  | sq.m |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Opening of Shopping on June 25, 2020
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Date Started:
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | Const. of 1 Classroom @ Laputlakan E/S, Sto. Niño, Talaingod |  | SEF CY 2020 | Building |  | sq.m |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Opening of Shopping on June 25, 2020
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Date Started:
New Corella | Limbaan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | Const. of Day Care Center, Limbaan, New Corella |  | 20% DF CY 2020 | Building |  | sq.m |  | Project Cost: | 1000000 | Target Completion Date: |  | Program: | 1000000 | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
New Corella | Limbaan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 1000000 | Revised: |  | No. of Man-days:
New Corella | Limbaan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
New Corella | Limbaan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | Limbaan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
New Corella | Limbaan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Date Started:
Kapalong | Gabuyan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | Const. of Day Care Center, Gabuyan, kapalong |  | 20% DF CY 2020 | Building |  | sq.m |  | Project Cost: | 1000000 | Target Completion Date: |  | Program: | 1000000 | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
Kapalong | Gabuyan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 1000000 | Revised: |  | No. of Man-days:
Kapalong | Gabuyan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Kapalong | Gabuyan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Kapalong | Gabuyan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Kapalong | Gabuyan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Date Started:
Asuncion | Canatan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | Compl./Rep. Day Care Center,Canatan, Asuncion |  | 20% DF CY 2020 | Building |  | sq.m |  | Project Cost: | 300000 | Target Completion Date: |  | Program: | 300000 | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
Asuncion | Canatan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 300000 | Revised: |  | No. of Man-days:
Asuncion | Canatan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Asuncion | Canatan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Asuncion | Canatan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Asuncion | Canatan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Date Started:
Asuncion | Cambanogoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | Compl./Rep. Day Care Center,Cambanogoy, Asuncion |  | 20% DF CY 2020 | Building |  | sq.m |  | Project Cost: | 300000 | Target Completion Date: |  | Program: | 300000 | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
Asuncion | Cambanogoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 300000 | Revised: |  | No. of Man-days:
Asuncion | Cambanogoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Asuncion | Cambanogoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Asuncion | Cambanogoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Asuncion | Cambanogoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Date Started:
Kapalong | Gabuyan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | Compl./Rep. Day Care Center,Gabuyan, kapalong |  | 20% DF CY 2020 | Building |  | sq.m |  | Project Cost: | 600000 | Target Completion Date: |  | Program: | 600000 | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
Kapalong | Gabuyan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 600000 | Revised: |  | No. of Man-days:
Kapalong | Gabuyan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Kapalong | Gabuyan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Kapalong | Gabuyan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Kapalong | Gabuyan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Date Started:
New Corella | New Sambog | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | Compl./Rep. Day Care Center,New Sambog, New Corella |  | 20% DF CY 2020 | Building |  | sq.m |  | Project Cost: | 300000 | Target Completion Date: |  | Program: | 300000 | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
New Corella | New Sambog | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 300000 | Revised: |  | No. of Man-days:
New Corella | New Sambog | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
New Corella | New Sambog | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | New Sambog | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
New Corella | New Sambog | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Date Started:
New Corella | Cabidianan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | Compl./Rep. Day Care Center, Cabidianan, New Corella |  | 20% DF CY 2020 | Building |  | sq.m |  | Project Cost: | 300000 | Target Completion Date: |  | Program: | 300000 | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
New Corella | Cabidianan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 300000 | Revised: |  | No. of Man-days:
New Corella | Cabidianan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
New Corella | Cabidianan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | Cabidianan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
New Corella | Cabidianan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Date Started:
San Isidro | Igangon | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | Compl./Rep. Day Care Center, Igangon, San Isidro |  | 20% DF CY 2020 | Building |  | sq.m |  | Project Cost: | 300000 | Target Completion Date: |  | Program: | 300000 | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
San Isidro | Igangon | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 300000 | Revised: |  | No. of Man-days:
San Isidro | Igangon | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
San Isidro | Igangon | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
San Isidro | Igangon | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
San Isidro | Igangon | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Date Started:
Tagum City | Madaum | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | Compl./Rep. Day Care Center, Madaum, Tagum City |  | 20% DF CY 2020 | Building |  | sq.m |  | Project Cost: | 300000 | Target Completion Date: |  | Program: | 300000 | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
Tagum City | Madaum | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 300000 | Revised: |  | No. of Man-days:
Tagum City | Madaum | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Tagum City | Madaum | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Tagum City | Madaum | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Tagum City | Madaum | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Date Started:
Tagum City | Apokon | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | Compl./Rep. Day Care Center, Apokon, Tagum City |  | 20% DF CY 2020 | Building |  | sq.m |  | Project Cost: | 300000 | Target Completion Date: |  | Program: | 300000 | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
Tagum City | Apokon | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 300000 | Revised: |  | No. of Man-days:
Tagum City | Apokon | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Tagum City | Apokon | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Tagum City | Apokon | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Tagum City | Apokon | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Date Started:
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | Compl./Rep. Day Care Center, Sto. Niño, Talaingod |  | 20% DF CY 2020 | Building |  | sq.m |  | Project Cost: | 300000 | Target Completion Date: |  | Program: | 300000 | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 300000 | Revised: |  | No. of Man-days:
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Date Started:
New Corella | Poblacion | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | HEALTH CARE SERVICES PROGRAM (PEEDO) | Improvement/Rehab. Of Luntiang Paraiso, New Corella |  | 20% DF CY 2020 | Building |  | km |  | Project Cost: | 3000000 | Target Completion Date: |  | Program: | 3000000 | Planned: |  | No. of Persons: |  | For Purchase Request
New Corella | Poblacion | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | HEALTH CARE SERVICES PROGRAM (PEEDO) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 3000000 | Revised: |  | No. of Man-days:
New Corella | Poblacion | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | HEALTH CARE SERVICES PROGRAM (PEEDO) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
New Corella | Poblacion | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | HEALTH CARE SERVICES PROGRAM (PEEDO) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | Poblacion | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | HEALTH CARE SERVICES PROGRAM (PEEDO) | [7 empty] | Date Allotment Released: |  | Date completed:
New Corella | Poblacion | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | HEALTH CARE SERVICES PROGRAM (PEEDO) | [7 empty] | Date Started:
Tagum City | Mankilam | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | PSYDO YOUTH DEV'T. PROGRAM - TEEN TAMBAYAN PROJECT | Renovation of Teen Tambayan |  | 20% DF CY 2020 | Building |  | sq.m |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Date of procurement June 30, 2020
Tagum City | Mankilam | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | PSYDO YOUTH DEV'T. PROGRAM - TEEN TAMBAYAN PROJECT | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Tagum City | Mankilam | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | PSYDO YOUTH DEV'T. PROGRAM - TEEN TAMBAYAN PROJECT | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Tagum City | Mankilam | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | PSYDO YOUTH DEV'T. PROGRAM - TEEN TAMBAYAN PROJECT | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Tagum City | Mankilam | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | PSYDO YOUTH DEV'T. PROGRAM - TEEN TAMBAYAN PROJECT | [7 empty] | Date Allotment Released: |  | Date completed:
Tagum City | Mankilam | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | PSYDO YOUTH DEV'T. PROGRAM - TEEN TAMBAYAN PROJECT | [7 empty] | Date Started:
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2020-06-01 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SPECIAL TRUST FUND (PDRRMC) | Installation of 20 units Isolation Room, Sports Academy Dormitory, DNSTC |  | TF | Isolation | 20 | sq.m | Admin | Project Cost: | 170000 | Target Completion Date: |  | Program: | 170000 | Planned: | 95% | No. of Persons: |  | On-going
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2020-06-01 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SPECIAL TRUST FUND (PDRRMC) | [7 empty] | Project Engineer: | Chua | Revised Completion Date: |  | Allotment: | 170000 | Revised: |  | No. of Man-days:
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2020-06-01 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SPECIAL TRUST FUND (PDRRMC) | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: | 95%
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2020-06-01 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SPECIAL TRUST FUND (PDRRMC) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2020-06-01 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SPECIAL TRUST FUND (PDRRMC) | [7 empty] | Date Allotment Released: | 2020-06-01 | Date completed:
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2020-06-01 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SPECIAL TRUST FUND (PDRRMC) | [7 empty] | Date Started: | 2020-06-01
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2020-06-01 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SPECIAL TRUST FUND (PDRRMC) | Installation of 100 units isolation room (2.0 x 3.0m), DAVNOR GYM |  | TF | Isolation | 100 | sq.m | Admin | Project Cost: | 750000 | Target Completion Date: |  | Program: | 750000 | Planned: | 95% | No. of Persons: |  | On-going
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2020-06-01 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SPECIAL TRUST FUND (PDRRMC) | [7 empty] | Project Engineer: | Chua | Revised Completion Date: |  | Allotment: | 750000 | Revised: |  | No. of Man-days:
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2020-06-01 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SPECIAL TRUST FUND (PDRRMC) | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: | 95%
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2020-06-01 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SPECIAL TRUST FUND (PDRRMC) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2020-06-01 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SPECIAL TRUST FUND (PDRRMC) | [7 empty] | Date Allotment Released: | 2020-06-01 | Date completed:
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2020-06-01 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SPECIAL TRUST FUND (PDRRMC) | [7 empty] | Date Started: | 2020-06-01
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2020-06-01 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SPECIAL TRUST FUND (PDRRMC) | Installation of 40 units Isolation Room, Sports Academy Dormitory, DNSTC |  | TF | Isolation | 40 | sq.m | Admin | Project Cost: | 320000 | Target Completion Date: |  | Program: | 320000 | Planned: | 95% | No. of Persons: |  | On-going
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2020-06-01 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SPECIAL TRUST FUND (PDRRMC) | [7 empty] | Project Engineer: | Chua | Revised Completion Date: |  | Allotment: | 320000 | Revised: |  | No. of Man-days:
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2020-06-01 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SPECIAL TRUST FUND (PDRRMC) | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: | 95%
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2020-06-01 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SPECIAL TRUST FUND (PDRRMC) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2020-06-01 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SPECIAL TRUST FUND (PDRRMC) | [7 empty] | Date Allotment Released: | 2020-05-28 | Date completed:
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2020-06-01 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SPECIAL TRUST FUND (PDRRMC) | [7 empty] | Date Started: | 2020-06-01
Talaingod | Palma Gil | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | PEACE AND ORDER PROGRAM | Proposed Road Opening of Nasilaban - Pongpong Road Section, Talaingod |  | SB # 1 CY 2020 | Road |  | km |  | Project Cost: | 5500000 | Target Completion Date: |  | Program: | 5500000 | Planned: |  | No. of Persons: |  | PO #2020062105 - M3C CONSTRUCTION & SUPPLY; PO #2020061966 - FL2 LUMBER & CONSTRUCTION SUPPLY; PO #2020062217 - Alpebel Builders and Supply Corporation, PO #DIOCESAN PRINTING PRESS
Talaingod | Palma Gil | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | PEACE AND ORDER PROGRAM | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 5500000 | Revised: |  | No. of Man-days:
Talaingod | Palma Gil | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | PEACE AND ORDER PROGRAM | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Talaingod | Palma Gil | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | PEACE AND ORDER PROGRAM | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Talaingod | Palma Gil | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | PEACE AND ORDER PROGRAM | [7 empty] | Date Allotment Released: |  | Date completed:
Talaingod | Palma Gil | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | PEACE AND ORDER PROGRAM | [7 empty] | Date Started:
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOV'T. BLDG. & FAC. DEV'T. PROJECT | Establishment of Multiplier Farm Phase 2, Brgy. Sto. Niño, Talaingod |  | SB # 1 CY 2020 | Building |  | sq.m |  | Project Cost: | 380000 | Target Completion Date: |  | Program: | 380000 | Planned: |  | No. of Persons: |  | For bidding on June 30, 2020; Re-bid July 28, 2020.
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOV'T. BLDG. & FAC. DEV'T. PROJECT | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 380000 | Revised: |  | No. of Man-days:
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOV'T. BLDG. & FAC. DEV'T. PROJECT | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOV'T. BLDG. & FAC. DEV'T. PROJECT | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOV'T. BLDG. & FAC. DEV'T. PROJECT | [7 empty] | Date Allotment Released: |  | Date completed:
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOV'T. BLDG. & FAC. DEV'T. PROJECT | [7 empty] | Date Started:
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOV'T. BLDG. & FAC. DEV'T. PROJECT | Establishment of Multiplier Farm (Poultry House), Phase 2, Brgy. Sto. Niño, Talaingod |  | SB # 1 CY 2020 | Building |  | sq.m |  | Project Cost: | 110000 | Target Completion Date: |  | Program: | 110000 | Planned: |  | No. of Persons: |  | For bidding on June 30, 2020; Re-bid July 28, 2020.
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOV'T. BLDG. & FAC. DEV'T. PROJECT | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 110000 | Revised: |  | No. of Man-days:
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOV'T. BLDG. & FAC. DEV'T. PROJECT | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOV'T. BLDG. & FAC. DEV'T. PROJECT | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOV'T. BLDG. & FAC. DEV'T. PROJECT | [7 empty] | Date Allotment Released: |  | Date completed:
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOV'T. BLDG. & FAC. DEV'T. PROJECT | [7 empty] | Date Started:
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOV'T. BLDG. & FAC. DEV'T. PROJECT | Poultry House and Training Center Phase 2, Talaingod |  | SB # 1 CY 2020 | Building |  | sq.m |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | For bidding on June 30, 2020; Re-bid July 28, 2020.
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOV'T. BLDG. & FAC. DEV'T. PROJECT | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOV'T. BLDG. & FAC. DEV'T. PROJECT | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOV'T. BLDG. & FAC. DEV'T. PROJECT | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOV'T. BLDG. & FAC. DEV'T. PROJECT | [7 empty] | Date Allotment Released: |  | Date completed:
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOV'T. BLDG. & FAC. DEV'T. PROJECT | [7 empty] | Date Started:
Kapalong | Maniki | 1st Eng'g. Dist. | On-going | 2020-05-11 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | BAYANIHAN GRANT TO PROVINCES | Improvement of Hospital facilities (Isolation/ICU), Kapalong Dist. Hospital |  | SB # 2 CY 2020 | Isolation |  | sq.m | Admin | Project Cost: | 6000000 | Target Completion Date: | 2021-01-10 23:59 | Program: | 6000000 | Planned: | 11.27% | No. of Persons: | 30 | On-going
Kapalong | Maniki | 1st Eng'g. Dist. | On-going | 2020-05-11 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | BAYANIHAN GRANT TO PROVINCES | [7 empty] | Project Engineer: | Pasiona/Aclaracion | Revised Completion Date: |  | Allotment: | 6000000 | Revised: |  | No. of Man-days: | 930
Kapalong | Maniki | 1st Eng'g. Dist. | On-going | 2020-05-11 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | BAYANIHAN GRANT TO PROVINCES | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: | 51.69%
Kapalong | Maniki | 1st Eng'g. Dist. | On-going | 2020-05-11 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | BAYANIHAN GRANT TO PROVINCES | [7 empty] | Duration: | 245 | No. of days extended: |  |  |  | Slippage: | 40.42%
Kapalong | Maniki | 1st Eng'g. Dist. | On-going | 2020-05-11 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | BAYANIHAN GRANT TO PROVINCES | [7 empty] | Date Allotment Released: | 2020-05-07 | Date completed:
Kapalong | Maniki | 1st Eng'g. Dist. | On-going | 2020-05-11 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | BAYANIHAN GRANT TO PROVINCES | [7 empty] | Date Started: | 2020-05-11
Kapalong | Gabuyan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | CMGP | Road Improvement of Jct. Highway Gabuyan – Semong – Dagohoy Provincial Road |  | CMGP | Road |  | km |  | Project Cost: | 63458000 | Target Completion Date: |  | Program: | 63458000 | Planned: |  | No. of Persons: |  | For posting
Kapalong | Gabuyan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | CMGP | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 63458000 | Revised: |  | No. of Man-days:
Kapalong | Gabuyan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | CMGP | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Kapalong | Gabuyan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | CMGP | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Kapalong | Gabuyan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | CMGP | [7 empty] | Date Allotment Released: |  | Date completed:
Kapalong | Gabuyan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | CMGP | [7 empty] | Date Started:
Talaingod | Palma Gil | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | NHA | Const. of 100 Housing Units at Balai Lupowanan at Sitio Nasilaban, Palma Gil, Talaingod |  | Natinal Housing Project CY 2020 | Building | 100 | units | Admin | Project Cost: | 20000000 | Target Completion Date: |  | Program: | 20000000 | Planned: |  | No. of Persons: |  | For bidding on July 3, 2020
Talaingod | Palma Gil | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | NHA | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 20000000 | Revised: |  | No. of Man-days:
Talaingod | Palma Gil | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | NHA | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Talaingod | Palma Gil | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | NHA | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Talaingod | Palma Gil | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | NHA | [7 empty] | Date Allotment Released: |  | Date completed:
Talaingod | Palma Gil | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | NHA | [7 empty] | Date Started:
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | NHA | Const. of 100 Housing Units at Balai Pig Immimanan at Sitio Mesulong, Sto. Niño, Talaingod |  | Natinal Housing Project CY 2020 | Building | 100 | units | Admin | Project Cost: | 20000000 | Target Completion Date: |  | Program: | 20000000 | Planned: |  | No. of Persons: |  | For bidding on July 3, 2020
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | NHA | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 20000000 | Revised: |  | No. of Man-days:
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | NHA | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | NHA | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | NHA | [7 empty] | Date Allotment Released: |  | Date completed:
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | NHA | [7 empty] | Date Started:
Panabo City | San Roque | 2nd Eng'g. Dist. | Completed |  | 2020-06-30 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) LS - P9,000,000.00 | Const. of MP Bldg. w/ Electrical installation, San Roque, Panabo City |  | 20% DF CY 2017 (STIMULUS) | Building |  | ln.m | MLGU | Project Cost: | 500000 | Target Completion Date: | 6/10/2019 | Program: | 500000 | Planned: | 100% | No. of Persons: |  | Completed as per physical accomplishment. Financial documents still on process.
Panabo City | San Roque | 2nd Eng'g. Dist. | Completed |  | 2020-06-30 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) LS - P9,000,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Panabo City | San Roque | 2nd Eng'g. Dist. | Completed |  | 2020-06-30 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) LS - P9,000,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: | 100%
Panabo City | San Roque | 2nd Eng'g. Dist. | Completed |  | 2020-06-30 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) LS - P9,000,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Panabo City | San Roque | 2nd Eng'g. Dist. | Completed |  | 2020-06-30 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) LS - P9,000,000.00 | [7 empty] | Date Allotment Released: | 2018-01-31 | Date completed: | 2019-06-10
Panabo City | San Roque | 2nd Eng'g. Dist. | Completed |  | 2020-06-30 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) LS - P9,000,000.00 | [7 empty] | Date Started:
B.E. Dujali | Magupising | 2nd Eng'g. Dist. | Completed | 2019-12-02 | 2020-05-29 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | Rehab.of Dujali - Balisong - Magupising Provincial Road |  | 20% DF CY 2019 | Road Rehabilitation | 19.16 | km | MBA | Project Cost: | 1280000 | Target Completion Date: | 2020-01-15 23:59 | Program: | 1280000 | Planned: | 100% | No. of Persons: | 12 | Completed as per physical accomplishment. Financial documents still on process.
B.E. Dujali | Magupising | 2nd Eng'g. Dist. | Completed | 2019-12-02 | 2020-05-29 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Project Engineer: | Mellomida | Revised Completion Date: | 2020-05-31 23:59 | Allotment: | 1280000 | Revised: |  | No. of Man-days: | 900
B.E. Dujali | Magupising | 2nd Eng'g. Dist. | Completed | 2019-12-02 | 2020-05-29 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Implementor: | PEO | No. of days suspended: | 137 | Disbursement: | 14331.6 | Actual: | 100%
B.E. Dujali | Magupising | 2nd Eng'g. Dist. | Completed | 2019-12-02 | 2020-05-29 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Duration: | 45 | No. of days extended: |  |  |  | Slippage: | 0%
B.E. Dujali | Magupising | 2nd Eng'g. Dist. | Completed | 2019-12-02 | 2020-05-29 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Date Allotment Released: |  | Date completed: | 2020-05-29
B.E. Dujali | Magupising | 2nd Eng'g. Dist. | Completed | 2019-12-02 | 2020-05-29 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Date Started: | 2019-12-02
Sto. Tomas | Tibal-og | 2nd Eng'g. Dist. | Completed | 2019-02-22 | 2020-06-30 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPPAP-PAMANA | Construction of Tribal Hall, Sto. Tomas |  | OPPAP-PAMANA CY 2017 | Building |  | sq.m | Admin | Project Cost: | 500000 | Target Completion Date: | 2019-07-31 | Program: | 500000 | Planned: | 100% | No. of Persons: | 7 | Resume last June 22, 2020; Completed as per physical accomplishment. Financial documents still on process.
Sto. Tomas | Tibal-og | 2nd Eng'g. Dist. | Completed | 2019-02-22 | 2020-06-30 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPPAP-PAMANA | [7 empty] | Project Engineer: | Roque | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days: | 110
Sto. Tomas | Tibal-og | 2nd Eng'g. Dist. | Completed | 2019-02-22 | 2020-06-30 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPPAP-PAMANA | [7 empty] | Implementor: | Admin | No. of days suspended: |  | Disbursement: |  | Actual: | 100%
Sto. Tomas | Tibal-og | 2nd Eng'g. Dist. | Completed | 2019-02-22 | 2020-06-30 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPPAP-PAMANA | [7 empty] | Duration: | 70 | No. of days extended: |  |  |  | Slippage: | 0%
Sto. Tomas | Tibal-og | 2nd Eng'g. Dist. | Completed | 2019-02-22 | 2020-06-30 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPPAP-PAMANA | [7 empty] | Date Allotment Released: | CY 2018 | Date completed: | 2020-06-30
Sto. Tomas | Tibal-og | 2nd Eng'g. Dist. | Completed | 2019-02-22 | 2020-06-30 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPPAP-PAMANA | [7 empty] | Date Started: | 2019-05-22
Panabo City | Lasang | 2nd Eng'g. Dist. | On-going | 2015-05-30 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOV'T. BLDG. & FAC. DEV'T. PROJECT | Proposed Davao del Norte Tourism Billboard, Brgy. Lasang, Panabo City |  | SB # 1 CY 2015 | Billboard |  | sq.m | Admin | Project Cost: | 756400 | Target Completion Date: | 2015-05-10 23:59 | Program: | 756400 | Planned: | 11.78% | No. of Persons: |  | delay due to change location & design code. For AIP amendment from Panabo City to Gov't Center, Mankilam
Panabo City | Lasang | 2nd Eng'g. Dist. | On-going | 2015-05-30 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOV'T. BLDG. & FAC. DEV'T. PROJECT | [7 empty] | Project Engineer: | Porras | Revised Completion Date: |  | Allotment: | 756400 | Revised: |  | No. of Man-days:
Panabo City | Lasang | 2nd Eng'g. Dist. | On-going | 2015-05-30 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOV'T. BLDG. & FAC. DEV'T. PROJECT | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: | 332087.3 | Actual: | 11.78%
Panabo City | Lasang | 2nd Eng'g. Dist. | On-going | 2015-05-30 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOV'T. BLDG. & FAC. DEV'T. PROJECT | [7 empty] | Duration: | 42 | No. of days extended: |  |  |  | Slippage: | 0%
Panabo City | Lasang | 2nd Eng'g. Dist. | On-going | 2015-05-30 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOV'T. BLDG. & FAC. DEV'T. PROJECT | [7 empty] | Date Allotment Released: | 2015-05-06 | Date completed:
Panabo City | Lasang | 2nd Eng'g. Dist. | On-going | 2015-05-30 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOV'T. BLDG. & FAC. DEV'T. PROJECT | [7 empty] | Date Started: | 2015-03-30
Sto. Tomas | Esperanza | 2nd Eng'g. Dist. | On-going | 2017-03-22 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PRDP | Rehab. of Esperanza-Pob. Sto. Tomas, FMR, DDN |  | PRDP CY 2014 | Road Concreting | 12.774 | km | Contract | Project Cost: | 117410426.3 | Target Completion Date: | 2019-07-22 23:59 | Program: | 117410426.3 | Planned: | 100% | No. of Persons: | 20 | On-going (Waiting for approve Variation order for billing)
Sto. Tomas | Esperanza | 2nd Eng'g. Dist. | On-going | 2017-03-22 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PRDP | [7 empty] | Project Engineer: | Palero | Revised Completion Date: | 2020-07-31 23:59 | Allotment: | 117410426.3 | Revised: | 95.53% | No. of Man-days: | 600
Sto. Tomas | Esperanza | 2nd Eng'g. Dist. | On-going | 2017-03-22 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PRDP | [7 empty] | Implementor: | ALZAM | No. of days suspended: |  | Disbursement: |  | Actual: | 87.82%
Sto. Tomas | Esperanza | 2nd Eng'g. Dist. | On-going | 2017-03-22 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PRDP | [7 empty] | Duration: | 853 | No. of days extended: | 375 |  |  | Slippage: | -7.705%
Sto. Tomas | Esperanza | 2nd Eng'g. Dist. | On-going | 2017-03-22 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PRDP | [7 empty] | Date Allotment Released: | CY 2014 | Date completed:
Sto. Tomas | Esperanza | 2nd Eng'g. Dist. | On-going | 2017-03-22 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PRDP | [7 empty] | Date Started: | 2017-03-22
Sto. Tomas | Poblacion | 2nd Eng'g. Dist. | For Implementation | 2018-01-29 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PRDP | Improvement of Sto. Tomas Production Center with Common Facility, Sto. Tomas |  | PRDP CY 2016 | Building | 1901 | sq.m | Contract | Project Cost: | 9825000 | Target Completion Date: | 2018-12-24 23:59 | Program: | 9825000 | Planned: |  | No. of Persons: |  | Suspended due to land unsettlement. Revised POW and DED On-going
Sto. Tomas | Poblacion | 2nd Eng'g. Dist. | For Implementation | 2018-01-29 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PRDP | [7 empty] | Project Engineer: | Azotes | Revised Completion Date: |  | Allotment: | 9825000 | Revised: |  | No. of Man-days:
Sto. Tomas | Poblacion | 2nd Eng'g. Dist. | For Implementation | 2018-01-29 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PRDP | [7 empty] | Implementor: | Manantan | No. of days suspended: |  | Disbursement: |  | Actual:
Sto. Tomas | Poblacion | 2nd Eng'g. Dist. | For Implementation | 2018-01-29 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PRDP | [7 empty] | Duration: | 330 | No. of days extended: |  |  |  | Slippage: | 0%
Sto. Tomas | Poblacion | 2nd Eng'g. Dist. | For Implementation | 2018-01-29 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PRDP | [7 empty] | Date Allotment Released: | CY 2014 | Date completed:
Sto. Tomas | Poblacion | 2nd Eng'g. Dist. | For Implementation | 2018-01-29 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PRDP | [7 empty] | Date Started: | 2018-01-29
IGCS | Kinawitnon | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | RURAL ELECTRIFICATION PROJECT | Inst. of transformer and accessories, Brgy. Kinawitnon |  | 20% DF CY 2016 | Electrification |  |  | Admin | Project Cost: | 150000 | Target Completion Date: |  | Program: | 150000 | Planned: |  | No. of Persons: |  | Purchase Order # 2019103228 - Transformer; Purchase Order # 2019102931 - Billboard; Purchase Order # 2019103227 - Lumber
IGCS | Kinawitnon | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | RURAL ELECTRIFICATION PROJECT | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 150000 | Revised: |  | No. of Man-days:
IGCS | Kinawitnon | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | RURAL ELECTRIFICATION PROJECT | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
IGCS | Kinawitnon | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | RURAL ELECTRIFICATION PROJECT | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
IGCS | Kinawitnon | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | RURAL ELECTRIFICATION PROJECT | [7 empty] | Date Allotment Released: | 2018-07-31 | Date completed:
IGCS | Kinawitnon | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | RURAL ELECTRIFICATION PROJECT | [7 empty] | Date Started:
Samal | Sta. Cruz | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | RURAL ELECTRIFICATION PROJECT | Rural Electrification at brgy. Sta. Cruz, talikud, Samal |  | 20% DF CY 2016 | Electrification |  |  | Contract | Project Cost: | 2000000 | Target Completion Date: |  | Program: | 2000000 | Planned: |  | No. of Persons: |  | Delay due to slow action of Daneco for staking. c/o Engr. Kim
Samal | Sta. Cruz | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | RURAL ELECTRIFICATION PROJECT | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 2000000 | Revised: |  | No. of Man-days:
Samal | Sta. Cruz | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | RURAL ELECTRIFICATION PROJECT | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Samal | Sta. Cruz | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | RURAL ELECTRIFICATION PROJECT | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Samal | Sta. Cruz | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | RURAL ELECTRIFICATION PROJECT | [7 empty] | Date Allotment Released: |  | Date completed:
Samal | Sta. Cruz | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | RURAL ELECTRIFICATION PROJECT | [7 empty] | Date Started:
BABAK | Kinawitnon | 2nd Eng'g. Dist. | On-going | 2018-03-12 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) LS - P9,000,000.00 | Construction of Provincial Training Center , Compound Fence, Kinawitnon, Babak District, IGCS |  | 20% DF CY 2016 | Fence |  | sq.m | Admin | Project Cost: | 940000 | Target Completion Date: | 2018-06-19 23:59 | Program: | 940000 | Planned: | 68% | No. of Persons: |  | Temporarily suspended 4/23/18 due to undemolished structures of illegal settlers
BABAK | Kinawitnon | 2nd Eng'g. Dist. | On-going | 2018-03-12 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) LS - P9,000,000.00 | [7 empty] | Project Engineer: | Pacquiao | Revised Completion Date: |  | Allotment: | 940000 | Revised: |  | No. of Man-days:
BABAK | Kinawitnon | 2nd Eng'g. Dist. | On-going | 2018-03-12 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) LS - P9,000,000.00 | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: | 933418.8 | Actual: | 75%
BABAK | Kinawitnon | 2nd Eng'g. Dist. | On-going | 2018-03-12 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) LS - P9,000,000.00 | [7 empty] | Duration: | 100 | No. of days extended: |  |  |  | Slippage: | 7%
BABAK | Kinawitnon | 2nd Eng'g. Dist. | On-going | 2018-03-12 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) LS - P9,000,000.00 | [7 empty] | Date Allotment Released: | 2017-09-19 | Date completed:
BABAK | Kinawitnon | 2nd Eng'g. Dist. | On-going | 2018-03-12 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) LS - P9,000,000.00 | [7 empty] | Date Started: | 2018-03-12
Panabo City | Consolacion | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) LS - P9,000,000.00 | Const of Market Stall/Building, Consolacion, Panabo City |  | 20% DF CY 2017 (STIMULUS) | Building |  |  | MLGU | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Issued warning for Termination of the Contract
Panabo City | Consolacion | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) LS - P9,000,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Panabo City | Consolacion | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) LS - P9,000,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Panabo City | Consolacion | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) LS - P9,000,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Panabo City | Consolacion | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) LS - P9,000,000.00 | [7 empty] | Date Allotment Released: | 2017-12-28 | Date completed:
Panabo City | Consolacion | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) LS - P9,000,000.00 | [7 empty] | Date Started:
Panabo City | Upper Licanan | 2nd Eng'g. Dist. | On-going | 2017-12-28 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) LS - P9,000,000.00 | Rehab. Of Multi-Purpose Hall (Covered Court), Upper Licanan, Panabo City |  | 20% DF CY 2017 (STIMULUS) | Building |  |  | MLGU | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Fund transfer to LGU- 3/28/2019 with check no.2574927 and OR no. 0166516 - Delivery of Materials on process
Panabo City | Upper Licanan | 2nd Eng'g. Dist. | On-going | 2017-12-28 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) LS - P9,000,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Panabo City | Upper Licanan | 2nd Eng'g. Dist. | On-going | 2017-12-28 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) LS - P9,000,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Panabo City | Upper Licanan | 2nd Eng'g. Dist. | On-going | 2017-12-28 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) LS - P9,000,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Panabo City | Upper Licanan | 2nd Eng'g. Dist. | On-going | 2017-12-28 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) LS - P9,000,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Panabo City | Upper Licanan | 2nd Eng'g. Dist. | On-going | 2017-12-28 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) LS - P9,000,000.00 | [7 empty] | Date Started: | 2017-12-28
Panabo City | Kauswagan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) LS - P9,000,000.00 | Impv't. of Multi-Purpose Gym, Kauswagan, Panabo City |  | 20% DF CY 2017 (STIMULUS) | GYM |  |  | MLGU | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Fund transfer to LGU- 3/28/2019 with check no.2574942 and OR no. 0166515 - procurement on process for bidding 8/5/2019
Panabo City | Kauswagan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) LS - P9,000,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Panabo City | Kauswagan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) LS - P9,000,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Panabo City | Kauswagan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) LS - P9,000,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Panabo City | Kauswagan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) LS - P9,000,000.00 | [7 empty] | Date Allotment Released: | 2019-02-04 | Date completed:
Panabo City | Kauswagan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) LS - P9,000,000.00 | [7 empty] | Date Started:
Panabo City | Cacao | 2nd Eng'g. Dist. | On-going | 2018-12-14 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) LS - P9,000,000.00 | Const. of Multi-Purpose Bldg.,Cacao, Panabo City |  | 20% DF CY 2017 (STIMULUS) | Building |  | sq.m | MLGU | Project Cost: | 300000 | Target Completion Date: |  | Program: | 300000 | Planned: |  | No. of Persons: |  | Issued warning for termination of the contract
Panabo City | Cacao | 2nd Eng'g. Dist. | On-going | 2018-12-14 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) LS - P9,000,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 300000 | Revised: |  | No. of Man-days:
Panabo City | Cacao | 2nd Eng'g. Dist. | On-going | 2018-12-14 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) LS - P9,000,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Panabo City | Cacao | 2nd Eng'g. Dist. | On-going | 2018-12-14 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) LS - P9,000,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Panabo City | Cacao | 2nd Eng'g. Dist. | On-going | 2018-12-14 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) LS - P9,000,000.00 | [7 empty] | Date Allotment Released: | 2017-12-19 | Date completed:
Panabo City | Cacao | 2nd Eng'g. Dist. | On-going | 2018-12-14 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) LS - P9,000,000.00 | [7 empty] | Date Started: | 2018-12-14
Panabo City | A.O. Floreindo | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) LS - P9,000,000.00 | Const. of Multi-Purpose Bldg. @ A.O. Floriendo National Highschool, Panabo City |  | 20% DF CY 2017 (STIMULUS) | Building |  |  | MLGU | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Fund transfer to LGU- 3/28/2019 with check no. 2574939 and OR no. 0166518 - Materials Delivered. Construction on-going
Panabo City | A.O. Floreindo | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) LS - P9,000,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Panabo City | A.O. Floreindo | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) LS - P9,000,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Panabo City | A.O. Floreindo | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) LS - P9,000,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Panabo City | A.O. Floreindo | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) LS - P9,000,000.00 | [7 empty] | Date Allotment Released: | 2017-12-19 | Date completed:
Panabo City | A.O. Floreindo | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) LS - P9,000,000.00 | [7 empty] | Date Started:
Panabo City | Kimamon | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Drainage | Const. of Concrete Drainage Canal, Kimamon, Panabo City |  | 20% DF CY 2017 (STIMULUS) | Drainage |  |  | MLGU | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | For Implementation
Panabo City | Kimamon | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Drainage | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Panabo City | Kimamon | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Drainage | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Panabo City | Kimamon | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Drainage | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Panabo City | Kimamon | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Drainage | [7 empty] | Date Allotment Released: | 2017-12-19 | Date completed:
Panabo City | Kimamon | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Drainage | [7 empty] | Date Started:
IGCS | Anonang | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | RURAL ELECTRIFICATION PROJECT | Impv't. of Brgy. Street Electrification at Brgy. Anonang, IGCS |  | 20% DF CY 2017 (STIMULUS) | Electrification |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Verified at PBO 7/18/2019 that fund is not available. Proposed priority project for 2020.
IGCS | Anonang | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | RURAL ELECTRIFICATION PROJECT | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
IGCS | Anonang | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | RURAL ELECTRIFICATION PROJECT | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual:
IGCS | Anonang | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | RURAL ELECTRIFICATION PROJECT | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
IGCS | Anonang | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | RURAL ELECTRIFICATION PROJECT | [7 empty] | Date Allotment Released: | 2017-11-28 | Date completed:
IGCS | Anonang | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | RURAL ELECTRIFICATION PROJECT | [7 empty] | Date Started:
Panabo City | Datu Abdul | 2nd Eng'g. Dist. | On-going | 2019-11-21 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPPAP-PAMANA | Const. of Trading Post, Storage Building with (1) unit Hauling Truck, Prk. Ramihan Datu Abdul, Panabo City |  | OPPAP-PAMANA CY 2017 | Building |  | sq.m | Contract | Project Cost: | 3975000 | Target Completion Date: | 2020-04-05 23:59 | Program: | 3975000 | Planned: | 100% | No. of Persons: | 10 | On-going
Panabo City | Datu Abdul | 2nd Eng'g. Dist. | On-going | 2019-11-21 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPPAP-PAMANA | [7 empty] | Project Engineer: | Azotes | Revised Completion Date: | 2020-05-16 23:59 | Allotment: | 3975000 | Revised: | 40.36% | No. of Man-days: | 260
Panabo City | Datu Abdul | 2nd Eng'g. Dist. | On-going | 2019-11-21 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPPAP-PAMANA | [7 empty] | Implementor: | Ultra Core | No. of days suspended: | 41 | Disbursement: |  | Actual: | 40.36%
Panabo City | Datu Abdul | 2nd Eng'g. Dist. | On-going | 2019-11-21 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPPAP-PAMANA | [7 empty] | Duration: | 137 | No. of days extended: |  |  |  | Slippage: | 0%
Panabo City | Datu Abdul | 2nd Eng'g. Dist. | On-going | 2019-11-21 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPPAP-PAMANA | [7 empty] | Date Allotment Released: | CY 2017 | Date completed:
Panabo City | Datu Abdul | 2nd Eng'g. Dist. | On-going | 2019-11-21 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPPAP-PAMANA | [7 empty] | Date Started: | 2019-11-21
Samal | Kinawitnon | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPPAP-PAMANA | Trading Post, Storage and Hauling Truck Libuak, Island Garden City of Samal (IGACOS) |  | OPPAP-PAMANA CY 2017 | Building |  |  |  | Project Cost: | 4000000 | Target Completion Date: |  | Program: | 4000000 | Planned: |  | No. of Persons: |  | For bidding
Samal | Kinawitnon | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPPAP-PAMANA | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 4000000 | Revised: |  | No. of Man-days:
Samal | Kinawitnon | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPPAP-PAMANA | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Samal | Kinawitnon | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPPAP-PAMANA | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Samal | Kinawitnon | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPPAP-PAMANA | [7 empty] | Date Allotment Released: | CY 2018 | Date completed:
Samal | Kinawitnon | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPPAP-PAMANA | [7 empty] | Date Started:
IGCS | Tambo | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPPAP-PAMANA | Agricultural Productivity Support Project-Fishing Equipment, Tambo, IGACOS |  | OPPAP-PAMANA CY 2017 |  |  |  |  | Project Cost: | 1500000 | Target Completion Date: |  | Program: | 1500000 | Planned: |  | No. of Persons: |  | For bidding
IGCS | Tambo | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPPAP-PAMANA | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 1500000 | Revised: |  | No. of Man-days:
IGCS | Tambo | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPPAP-PAMANA | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
IGCS | Tambo | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPPAP-PAMANA | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
IGCS | Tambo | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPPAP-PAMANA | [7 empty] | Date Allotment Released: |  | Date completed:
IGCS | Tambo | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPPAP-PAMANA | [7 empty] | Date Started:
Carmen | Asuncion | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Construction of Water System Projects in Component LGUs LS - 9,750,000.00 | Rehab./Impv't. of San Vicente Water System, Asuncion |  | 20% DF CY 2018 | Water System |  |  | Admin | Project Cost: | 1125000 | Target Completion Date: |  | Program: | 1125000 | Planned: |  | No. of Persons: |  | Abstract # 0220190484
Carmen | Asuncion | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Construction of Water System Projects in Component LGUs LS - 9,750,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 1125000 | Revised: |  | No. of Man-days:
Carmen | Asuncion | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Construction of Water System Projects in Component LGUs LS - 9,750,000.00 | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual:
Carmen | Asuncion | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Construction of Water System Projects in Component LGUs LS - 9,750,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Carmen | Asuncion | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Construction of Water System Projects in Component LGUs LS - 9,750,000.00 | [7 empty] | Date Allotment Released: | 2018-10-26 | Date completed:
Carmen | Asuncion | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Construction of Water System Projects in Component LGUs LS - 9,750,000.00 | [7 empty] | Date Started:
Panabo City | Malativas | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Construction of Water System Projects in Component LGUs LS - 9,750,000.00 | Water System at brgy. Malativas, Panabo City |  | 20% DF CY 2018 | Water System |  |  | Admin | Project Cost: | 1250000 | Target Completion Date: |  | Program: | 1250000 | Planned: |  | No. of Persons: |  | For preparation of POW & Plan c/o PDPM - POSSIBLE TRANSFER OF SITE SUBJECT FOR TRANSFER OF LOCATION . NO DEED OF DONATION
Panabo City | Malativas | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Construction of Water System Projects in Component LGUs LS - 9,750,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 1250000 | Revised: |  | No. of Man-days:
Panabo City | Malativas | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Construction of Water System Projects in Component LGUs LS - 9,750,000.00 | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual:
Panabo City | Malativas | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Construction of Water System Projects in Component LGUs LS - 9,750,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Panabo City | Malativas | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Construction of Water System Projects in Component LGUs LS - 9,750,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Panabo City | Malativas | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Construction of Water System Projects in Component LGUs LS - 9,750,000.00 | [7 empty] | Date Started:
Panabo City | Tibungol | 2nd Eng'g. Dist. | On-going | 2020-01-20 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Construction of Water System Projects in Component LGUs LS - 9,750,000.00 | Const. of Potable Water System at Brgy. Tibungol, Panabo City |  | 20% DF CY 2018 | Water System |  | ln.m | Admin | Project Cost: | 1250000 | Target Completion Date: | 2020-04-15 23:59 | Program: | 1250000 | Planned: | 2.13% | No. of Persons: | 3 | Suspended dated February 19, 2020 undelivered hardware materials (Supplier refused to deliver. Letter already submitted to BAC.)
Panabo City | Tibungol | 2nd Eng'g. Dist. | On-going | 2020-01-20 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Construction of Water System Projects in Component LGUs LS - 9,750,000.00 | [7 empty] | Project Engineer: | Andoy | Revised Completion Date: |  | Allotment: | 1250000 | Revised: |  | No. of Man-days: | 15
Panabo City | Tibungol | 2nd Eng'g. Dist. | On-going | 2020-01-20 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Construction of Water System Projects in Component LGUs LS - 9,750,000.00 | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: | 0.76%
Panabo City | Tibungol | 2nd Eng'g. Dist. | On-going | 2020-01-20 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Construction of Water System Projects in Component LGUs LS - 9,750,000.00 | [7 empty] | Duration: | 87 | No. of days extended: |  |  |  | Slippage: | -1.37%
Panabo City | Tibungol | 2nd Eng'g. Dist. | On-going | 2020-01-20 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Construction of Water System Projects in Component LGUs LS - 9,750,000.00 | [7 empty] | Date Allotment Released: | 2018-11-21 | Date completed:
Panabo City | Tibungol | 2nd Eng'g. Dist. | On-going | 2020-01-20 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Construction of Water System Projects in Component LGUs LS - 9,750,000.00 | [7 empty] | Date Started: | 2020-01-20
Samal, Kaputian | San Remegio | 2nd Eng'g. Dist. | On-going | 2019-07-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Construction of Water System Projects in Component LGUs LS - 9,750,000.00 | Potable Water System at Brgy. San Remegio Kaputian (Level II WS), Samal |  | 20% DF CY 2018 | Water System |  |  | Admin | Project Cost: | 3625000 | Target Completion Date: | 2020-02-01 | Program: | 3625000 | Planned: | 100% | No. of Persons: | 4 | On-going/ Resumption 5/4/2020
Samal, Kaputian | San Remegio | 2nd Eng'g. Dist. | On-going | 2019-07-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Construction of Water System Projects in Component LGUs LS - 9,750,000.00 | [7 empty] | Project Engineer: | Kabigue | Revised Completion Date: | 2020-04-30 | Allotment: | 3625000 | Revised: | 72.04% | No. of Man-days: | 88
Samal, Kaputian | San Remegio | 2nd Eng'g. Dist. | On-going | 2019-07-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Construction of Water System Projects in Component LGUs LS - 9,750,000.00 | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: | 2702800 | Actual: | 74.56%
Samal, Kaputian | San Remegio | 2nd Eng'g. Dist. | On-going | 2019-07-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Construction of Water System Projects in Component LGUs LS - 9,750,000.00 | [7 empty] | Duration: | 200 | No. of days extended: | 89 |  |  | Slippage: | 2.52%
Samal, Kaputian | San Remegio | 2nd Eng'g. Dist. | On-going | 2019-07-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Construction of Water System Projects in Component LGUs LS - 9,750,000.00 | [7 empty] | Date Allotment Released: | 2018-10-25 | Date completed:
Samal, Kaputian | San Remegio | 2nd Eng'g. Dist. | On-going | 2019-07-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Construction of Water System Projects in Component LGUs LS - 9,750,000.00 | [7 empty] | Date Started: | 2019-07-16
Carmen | San Isidro | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | Completion of Evacuation Center Building, San Isidro, Carmen |  | GENERAL FUND PROPER CY 2018 (STIMULUS) | Building |  | sq.m | Contract | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | On-going
Carmen | San Isidro | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | [7 empty] | Project Engineer: | Estorco | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Carmen | San Isidro | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | [7 empty] | Implementor: | RLHV | No. of days suspended: |  | Disbursement: |  | Actual:
Carmen | San Isidro | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | [7 empty] | Duration: | 60 | No. of days extended: |  |  |  | Slippage: | 0%
Carmen | San Isidro | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | [7 empty] | Date Allotment Released: |  | Date completed:
Carmen | San Isidro | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | [7 empty] | Date Started:
Panabo City | Nanyo | 2nd Eng'g. Dist. | On-going | 2020-04-07 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | Const. of Perimeter Fence of Day Care Center 1, Nanyo, Panabo City |  | GENERAL FUND PROPER CY 2018 (STIMULUS) | Building |  | sq.m | Contract | Project Cost: | 500000 | Target Completion Date: | 2020-06-06 | Program: | 500000 | Planned: | 5% | No. of Persons: |  | (RLHV Design & Build) Winning Bidder
Panabo City | Nanyo | 2nd Eng'g. Dist. | On-going | 2020-04-07 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | [7 empty] | Project Engineer: | Estorco | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Panabo City | Nanyo | 2nd Eng'g. Dist. | On-going | 2020-04-07 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | [7 empty] | Implementor: | RLHV | No. of days suspended: |  | Disbursement: |  | Actual: | 5%
Panabo City | Nanyo | 2nd Eng'g. Dist. | On-going | 2020-04-07 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | [7 empty] | Duration: | 60 | No. of days extended: |  |  |  | Slippage: | 0%
Panabo City | Nanyo | 2nd Eng'g. Dist. | On-going | 2020-04-07 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | [7 empty] | Date Allotment Released: |  | Date completed:
Panabo City | Nanyo | 2nd Eng'g. Dist. | On-going | 2020-04-07 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | [7 empty] | Date Started: | 2020-04-07
Panabo City | Malativas | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | Impv't. of Brgy. Road Covered Court, Malativas, Panabo City |  | GENERAL FUND PROPER CY 2018 (STIMULUS) | Court |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Procurement on process
Panabo City | Malativas | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Panabo City | Malativas | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Panabo City | Malativas | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Panabo City | Malativas | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | [7 empty] | Date Allotment Released: |  | Date completed:
Panabo City | Malativas | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | [7 empty] | Date Started:
Panabo City | Maduao | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | Rehab. Of Multi-Purpose Gym & Facililies Maduao, Panabo City |  | GENERAL FUND PROPER CY 2018 (STIMULUS) | Gym |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Post qualification on process
Panabo City | Maduao | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Panabo City | Maduao | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Panabo City | Maduao | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Panabo City | Maduao | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | [7 empty] | Date Allotment Released: |  | Date completed:
Panabo City | Maduao | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | [7 empty] | Date Started:
Panabo City | Sto. Niño | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | Const. of Multi-Purpose Bldg. Sto. Nino, Panabo City |  | GENERAL FUND PROPER CY 2018 (STIMULUS) | Court |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | PR # 20032818
Panabo City | Sto. Niño | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Panabo City | Sto. Niño | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Panabo City | Sto. Niño | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Panabo City | Sto. Niño | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | [7 empty] | Date Allotment Released: |  | Date completed:
Panabo City | Sto. Niño | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | [7 empty] | Date Started:
Panabo City | Dapco | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | Completion of Canopy at DAPCO Covered Court, Dapco, Panabo City |  | GENERAL FUND PROPER CY 2018 (STIMULUS) | Court |  |  | Contract | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | (RLHV Design & Build) Winning Bidder
Panabo City | Dapco | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | [7 empty] | Project Engineer: | RLHV | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Panabo City | Dapco | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Panabo City | Dapco | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Panabo City | Dapco | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | [7 empty] | Date Allotment Released: |  | Date completed:
Panabo City | Dapco | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | [7 empty] | Date Started:
Panabo City | Nanyo | 2nd Eng'g. Dist. | On-going | 2020-04-07 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | Perimeter Fence of Day Care Center I & II, Nanyo, Panabo City/ Construction of Perimeter Fence) |  | GENERAL FUND PROPER CY 2018 (STIMULUS) | Building |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | For implementation (RLHV Design & Build) Winning Bidder
Panabo City | Nanyo | 2nd Eng'g. Dist. | On-going | 2020-04-07 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Panabo City | Nanyo | 2nd Eng'g. Dist. | On-going | 2020-04-07 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Panabo City | Nanyo | 2nd Eng'g. Dist. | On-going | 2020-04-07 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Panabo City | Nanyo | 2nd Eng'g. Dist. | On-going | 2020-04-07 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | [7 empty] | Date Allotment Released: |  | Date completed:
Panabo City | Nanyo | 2nd Eng'g. Dist. | On-going | 2020-04-07 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | [7 empty] | Date Started:
IGCS | Pichon | 2nd Eng'g. Dist. | On-going | 2020-01-13 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | Impv't. of Brgy. Water System, Pichon, IGCS (Construction of Elevated Tank) |  | GENERAL FUND PROPER CY 2018 (STIMULUS) | Water System |  |  | Admin | Project Cost: | 500000 | Target Completion Date: | 2020-03-13 | Program: | 500000 | Planned: | 100% | No. of Persons: | 5 | On-going
IGCS | Pichon | 2nd Eng'g. Dist. | On-going | 2020-01-13 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | [7 empty] | Project Engineer: | Andoy | Revised Completion Date: | 2020-07-31 | Allotment: | 500000 | Revised: | 86% | No. of Man-days: | 110
IGCS | Pichon | 2nd Eng'g. Dist. | On-going | 2020-01-13 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | [7 empty] | Implementor: | PEO | No. of days suspended: | 140 | Disbursement: | 423575.63 | Actual: | 83.5%
IGCS | Pichon | 2nd Eng'g. Dist. | On-going | 2020-01-13 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | [7 empty] | Duration: | 60 | No. of days extended: |  |  |  | Slippage: | -2.5%
IGCS | Pichon | 2nd Eng'g. Dist. | On-going | 2020-01-13 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | [7 empty] | Date Allotment Released: | 2018-05-31 | Date completed:
IGCS | Pichon | 2nd Eng'g. Dist. | On-going | 2020-01-13 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | [7 empty] | Date Started: | 2020-01-13
IGCS | Cogon | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | Powerline Expansion Project, Cogon, IGACOS |  | GENERAL FUND PROPER CY 2018 (STIMULUS) | Water System |  |  | Contract | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Waiting for NTP (3E Electrical)
IGCS | Cogon | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
IGCS | Cogon | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
IGCS | Cogon | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
IGCS | Cogon | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | [7 empty] | Date Allotment Released: |  | Date completed:
IGCS | Cogon | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | [7 empty] | Date Started:
IGCS | Tagbay | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | Water System From Prk. 6 - Prk. 2 - Prk. 5A, Tagbay, IGCS |  | GENERAL FUND PROPER CY 2018 (STIMULUS) | Water System |  |  | Admin | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | For Implementation
IGCS | Tagbay | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
IGCS | Tagbay | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
IGCS | Tagbay | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
IGCS | Tagbay | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | [7 empty] | Date Allotment Released: |  | Date completed:
IGCS | Tagbay | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | [7 empty] | Date Started:
IGCS | Tambo | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | RURAL ELECTRIFICATION PROJECT | Powerline Expansion Project, Tambo, IGCS |  | GENERAL FUND PROPER CY 2018 (STIMULUS) | Electrification |  |  | Contract | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Purchase Request # 19083312
IGCS | Tambo | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | RURAL ELECTRIFICATION PROJECT | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
IGCS | Tambo | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | RURAL ELECTRIFICATION PROJECT | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
IGCS | Tambo | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | RURAL ELECTRIFICATION PROJECT | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
IGCS | Tambo | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | RURAL ELECTRIFICATION PROJECT | [7 empty] | Date Allotment Released: |  | Date completed:
IGCS | Tambo | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | RURAL ELECTRIFICATION PROJECT | [7 empty] | Date Started:
IGCS | Peñaplata | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | Improvement of Barangay Hall, Penaplata, IGCS |  | GENERAL FUND PROPER CY 2018 (STIMULUS) | Building |  |  | Admin | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | By Contract and change to admin due to unforeseen activities because it’s a repair (For revision of POW)
IGCS | Peñaplata | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
IGCS | Peñaplata | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
IGCS | Peñaplata | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
IGCS | Peñaplata | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | [7 empty] | Date Allotment Released: |  | Date completed:
IGCS | Peñaplata | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | [7 empty] | Date Started:
IGCS | Dadatan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | RURAL ELECTRIFICATION PROJECT | Electrification of Sitio Baongon-Diamond-Mansanitas, Dadatan, IGCS |  | GENERAL FUND PROPER CY 2018 (STIMULUS) | Electrification |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Purchase Order # 20200100002 (3E Electrical Sales & Services)
IGCS | Dadatan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | RURAL ELECTRIFICATION PROJECT | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
IGCS | Dadatan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | RURAL ELECTRIFICATION PROJECT | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
IGCS | Dadatan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | RURAL ELECTRIFICATION PROJECT | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
IGCS | Dadatan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | RURAL ELECTRIFICATION PROJECT | [7 empty] | Date Allotment Released: |  | Date completed:
IGCS | Dadatan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | RURAL ELECTRIFICATION PROJECT | [7 empty] | Date Started:
IGCS | Linusotan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Construction of Water System Projects in Component LGUs | Drilling of Water System, Linusotan, IGCS |  | GENERAL FUND PROPER CY 2018 (STIMULUS) | Water System |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
IGCS | Linusotan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Construction of Water System Projects in Component LGUs | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
IGCS | Linusotan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Construction of Water System Projects in Component LGUs | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
IGCS | Linusotan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Construction of Water System Projects in Component LGUs | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
IGCS | Linusotan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Construction of Water System Projects in Component LGUs | [7 empty] | Date Allotment Released: |  | Date completed:
IGCS | Linusotan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Construction of Water System Projects in Component LGUs | [7 empty] | Date Started:
Carmen | Ising | 2nd Eng'g. Dist. | On-going | 2020-03-19 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | Const. of DDN Hospital Carmen Zone Annex Bldg. |  | SB # 1 CY 2018 | Building |  | sq.m | Contract | Project Cost: | 5500000 | Target Completion Date: | 2020-07-17 | Program: | 5500000 | Planned: | 95.2% | No. of Persons: | 10 | On-going
Carmen | Ising | 2nd Eng'g. Dist. | On-going | 2020-03-19 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | [7 empty] | Project Engineer: | Azotes | Revised Completion Date: | 2020-09-12 | Allotment: | 5500000 | Revised: | 40.5% | No. of Man-days: | 260
Carmen | Ising | 2nd Eng'g. Dist. | On-going | 2020-03-19 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | [7 empty] | Implementor: | Digos Constrak Corp/ | No. of days suspended: | 57 | Disbursement: | 1650000 | Actual: | 68.25%
Carmen | Ising | 2nd Eng'g. Dist. | On-going | 2020-03-19 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | [7 empty] | Duration: | 120 | No. of days extended: |  |  |  | Slippage: | 27.75%
Carmen | Ising | 2nd Eng'g. Dist. | On-going | 2020-03-19 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | [7 empty] | Date Allotment Released: |  | Date completed:
Carmen | Ising | 2nd Eng'g. Dist. | On-going | 2020-03-19 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | [7 empty] | Date Started: | 2020-03-19
Carmen | Cebulano | 2nd Eng'g. Dist. | Completed | 2019-05-21 | 2020-05-31 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | Road ID11 Jct. Highway Sto. Niño - Cebulano |  | 20% DF CY 2019 | Road Rehabilitation | 2.09 | km | Admin | Project Cost: | 1045000 | Target Completion Date: | 2019-10-04 | Program: | 1045000 | Planned: | 100% | No. of Persons: | 6 | Completed as per physical accomplishment. Financial documents still on process.
Carmen | Cebulano | 2nd Eng'g. Dist. | Completed | 2019-05-21 | 2020-05-31 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | [7 empty] | Project Engineer: | Obar/ Nasol | Revised Completion Date: | 2020-06-15 | Allotment: | 1045000 | Revised: |  | No. of Man-days: | 132
Carmen | Cebulano | 2nd Eng'g. Dist. | Completed | 2019-05-21 | 2020-05-31 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | [7 empty] | Implementor: | PEO | No. of days suspended: | 194 | Disbursement: | 1045000 | Actual: | 100%
Carmen | Cebulano | 2nd Eng'g. Dist. | Completed | 2019-05-21 | 2020-05-31 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | [7 empty] | Duration: | 136 | No. of days extended: | 61 |  |  | Slippage: | 0%
Carmen | Cebulano | 2nd Eng'g. Dist. | Completed | 2019-05-21 | 2020-05-31 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | [7 empty] | Date Allotment Released: | 2019-01-03 | Date completed: | 2020-05-31
Carmen | Cebulano | 2nd Eng'g. Dist. | Completed | 2019-05-21 | 2020-05-31 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | [7 empty] | Date Started: | 2019-05-21
Carmen | Tubod | 2nd Eng'g. Dist. | Completed | 2019-11-11 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | ROAD ID 076 - Basa - Tubod |  | 20% DF CY 2019 | Road Rehabilitation | 1.56 | km | Admin | Project Cost: | 1000000 | Target Completion Date: | 2020-03-19 23:59 | Program: | 1000000 | Planned: | 100% | No. of Persons: | 3 | Completed as per physical accomplishment. Financial documents still on process.
Carmen | Tubod | 2nd Eng'g. Dist. | Completed | 2019-11-11 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | [7 empty] | Project Engineer: | PIAD | Revised Completion Date: | 2020-06-30 23:59 | Allotment: | 1000000 | Revised: | 100% | No. of Man-days: | 30
Carmen | Tubod | 2nd Eng'g. Dist. | Completed | 2019-11-11 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | [7 empty] | Implementor: | PEO | No. of days suspended: | 103 | Disbursement: |  | Actual: | 100%
Carmen | Tubod | 2nd Eng'g. Dist. | Completed | 2019-11-11 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | [7 empty] | Duration: | 130 | No. of days extended: |  |  |  | Slippage: | 0%
Carmen | Tubod | 2nd Eng'g. Dist. | Completed | 2019-11-11 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | [7 empty] | Date Allotment Released: | 2019-01-03 | Date completed: | 2020-06-30 23:59
Carmen | Tubod | 2nd Eng'g. Dist. | Completed | 2019-11-11 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | [7 empty] | Date Started: | 2019-11-11
Carmen | Tubod | 2nd Eng'g. Dist. | On-going | 2019-12-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | ROAD ID 077 - Tubod - Pilar |  | 20% DF CY 2019 | Road Rehabilitation | 1.55 | km | Admin | Project Cost: | 16000000 | Target Completion Date: | 2020-11-05 | Program: | 16000000 | Planned: | 62.5% | No. of Persons: | 20 | On-going
Carmen | Tubod | 2nd Eng'g. Dist. | On-going | 2019-12-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | [7 empty] | Project Engineer: | Agang | Revised Completion Date: |  | Allotment: | 16000000 | Revised: |  | No. of Man-days: | 600
Carmen | Tubod | 2nd Eng'g. Dist. | On-going | 2019-12-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: | 4046971.2 | Actual: | 58.23%
Carmen | Tubod | 2nd Eng'g. Dist. | On-going | 2019-12-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | [7 empty] | Duration: | 323 | No. of days extended: |  |  |  | Slippage: | -4.27%
Carmen | Tubod | 2nd Eng'g. Dist. | On-going | 2019-12-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | [7 empty] | Date Allotment Released: | 2019-11-26 | Date completed:
Carmen | Tubod | 2nd Eng'g. Dist. | On-going | 2019-12-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | [7 empty] | Date Started: | 2019-12-18
Carmen | Tibulao | 2nd Eng'g. Dist. | On-going | 2019-11-11 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | ROAD ID 103 - Sitio Malaga - Tibulao |  | 20% DF CY 2019 | Road Rehabilitation | 3.22 | km | Admin | Project Cost: | 1000000 | Target Completion Date: | 2020-02-09 | Program: | 1000000 | Planned: | 78.5% | No. of Persons: | 5 | On-going
Carmen | Tibulao | 2nd Eng'g. Dist. | On-going | 2019-11-11 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | [7 empty] | Project Engineer: | Obar | Revised Completion Date: | 2020-06-30 | Allotment: | 1000000 | Revised: |  | No. of Man-days: | 110
Carmen | Tibulao | 2nd Eng'g. Dist. | On-going | 2019-11-11 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | [7 empty] | Implementor: | PEO | No. of days suspended: | 142 | Disbursement: |  | Actual: | 54.8%
Carmen | Tibulao | 2nd Eng'g. Dist. | On-going | 2019-11-11 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | [7 empty] | Duration: | 90 | No. of days extended: |  |  |  | Slippage: | -23.7%
Carmen | Tibulao | 2nd Eng'g. Dist. | On-going | 2019-11-11 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | [7 empty] | Date Allotment Released: | 2019-01-03 | Date completed:
Carmen | Tibulao | 2nd Eng'g. Dist. | On-going | 2019-11-11 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | [7 empty] | Date Started: | 2019-11-11
B.E. Dujali | Tanglaw | 2nd Eng'g. Dist. | On-going | 2019-12-28 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | ROAD ID 104 - Dujali - Tanglaw |  | 20% DF CY 2019 | Road Rehabilitation | 3.6 | km | Admin | Project Cost: | 2075000 | Target Completion Date: | 2020-04-16 | Program: | 2075000 | Planned: | 60% | No. of Persons: | 11 | On-going
B.E. Dujali | Tanglaw | 2nd Eng'g. Dist. | On-going | 2019-12-28 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | [7 empty] | Project Engineer: | Balbastro | Revised Completion Date: | 2020-08-30 | Allotment: | 2075000 | Revised: |  | No. of Man-days: | 77
B.E. Dujali | Tanglaw | 2nd Eng'g. Dist. | On-going | 2019-12-28 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | [7 empty] | Implementor: | PEO | No. of days suspended: | 28 | Disbursement: |  | Actual: | 65%
B.E. Dujali | Tanglaw | 2nd Eng'g. Dist. | On-going | 2019-12-28 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | [7 empty] | Duration: | 110 | No. of days extended: | 108 |  |  | Slippage: | 5%
B.E. Dujali | Tanglaw | 2nd Eng'g. Dist. | On-going | 2019-12-28 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | [7 empty] | Date Allotment Released: | 2019-01-03 | Date completed:
B.E. Dujali | Tanglaw | 2nd Eng'g. Dist. | On-going | 2019-12-28 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | [7 empty] | Date Started: | 2019-12-28
Sto. Tomas | Libertad | 2nd Eng'g. Dist. | On-going | 2019-06-17 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | ROAD ID 121 - San Miguel - Libertad |  | 20% DF CY 2019 | Road Rehabilitation | 6.2 | km | Admin | Project Cost: | 1240000 | Target Completion Date: | 2019-10-31 | Program: | 1240000 | Planned: | 59.41% | No. of Persons: | 9 | On-going
Sto. Tomas | Libertad | 2nd Eng'g. Dist. | On-going | 2019-06-17 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | [7 empty] | Project Engineer: | Gamad | Revised Completion Date: | 2020-02-29 | Allotment: | 1240000 | Revised: |  | No. of Man-days: | 36
Sto. Tomas | Libertad | 2nd Eng'g. Dist. | On-going | 2019-06-17 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | [7 empty] | Implementor: | PEO | No. of days suspended: | 86 | Disbursement: |  | Actual: | 59.41%
Sto. Tomas | Libertad | 2nd Eng'g. Dist. | On-going | 2019-06-17 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | [7 empty] | Duration: | 136 | No. of days extended: | 35 |  |  | Slippage: | 0%
Sto. Tomas | Libertad | 2nd Eng'g. Dist. | On-going | 2019-06-17 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | [7 empty] | Date Allotment Released: | 2019-01-03 | Date completed:
Sto. Tomas | Libertad | 2nd Eng'g. Dist. | On-going | 2019-06-17 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | [7 empty] | Date Started: | 2019-06-17
Sto. Tomas | Casig-ang | 2nd Eng'g. Dist. | On-going | 2019-06-27 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | ROAD ID 123 - Bacali - Casig-ang - Libertad |  | 20% DF CY 2019 | Road Rehabilitation | 4.7 | km | Admin | Project Cost: | 940000 | Target Completion Date: | 2019-09-15 | Program: | 940000 | Planned: | 62.1% | No. of Persons: | 9 | On-going
Sto. Tomas | Casig-ang | 2nd Eng'g. Dist. | On-going | 2019-06-27 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | [7 empty] | Project Engineer: | Gamad | Revised Completion Date: | 2020-02-29 | Allotment: | 940000 | Revised: |  | No. of Man-days: | 36
Sto. Tomas | Casig-ang | 2nd Eng'g. Dist. | On-going | 2019-06-27 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | [7 empty] | Implementor: | PEO | No. of days suspended: | 132 | Disbursement: |  | Actual: | 62%
Sto. Tomas | Casig-ang | 2nd Eng'g. Dist. | On-going | 2019-06-27 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | [7 empty] | Duration: | 80 | No. of days extended: | 35 |  |  | Slippage: | -0.1%
Sto. Tomas | Casig-ang | 2nd Eng'g. Dist. | On-going | 2019-06-27 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | [7 empty] | Date Allotment Released: | 2019-06-07 | Date completed:
Sto. Tomas | Casig-ang | 2nd Eng'g. Dist. | On-going | 2019-06-27 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | [7 empty] | Date Started: | 2019-06-27
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | On-going | 2019-06-17 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | ROAD ID 125 - San Miguel - Moslog - Kinamayan |  | 20% DF CY 2019 | Road Rehabilitation | 2.9 | km | Admin | Project Cost: | 1000000 | Target Completion Date: | 2019-09-16 | Program: | 1000000 | Planned: | 100% | No. of Persons: | 6 | On-going
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | On-going | 2019-06-17 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | [7 empty] | Project Engineer: | Gamad | Revised Completion Date: | 2020-02-29 | Allotment: | 1000000 | Revised: | 73.59% | No. of Man-days: | 30
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | On-going | 2019-06-17 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | [7 empty] | Implementor: | PEO | No. of days suspended: | 137 | Disbursement: |  | Actual: | 80%
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | On-going | 2019-06-17 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | [7 empty] | Duration: | 91 | No. of days extended: | 29 |  |  | Slippage: | 6.41%
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | On-going | 2019-06-17 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | [7 empty] | Date Allotment Released: | 2019-05-20 | Date completed:
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | On-going | 2019-06-17 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | [7 empty] | Date Started: | 2019-06-17
Sto. Tomas | Katipunana | 2nd Eng'g. Dist. | On-going | 2019-12-27 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | ROAD ID 134 - New Katipunan - Pantaron |  | 20% DF CY 2019 | Road Rehabilitation | 1.96 | km | Admin | Project Cost: | 395000 | Target Completion Date: | 2020-02-25 | Program: | 395000 | Planned: | 60% | No. of Persons: | 4 | On-going
Sto. Tomas | Katipunana | 2nd Eng'g. Dist. | On-going | 2019-12-27 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | [7 empty] | Project Engineer: | Gamad/Clar | Revised Completion Date: |  | Allotment: | 395000 | Revised: |  | No. of Man-days: | 24
Sto. Tomas | Katipunana | 2nd Eng'g. Dist. | On-going | 2019-12-27 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: | 60%
Sto. Tomas | Katipunana | 2nd Eng'g. Dist. | On-going | 2019-12-27 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | [7 empty] | Duration: | 60 | No. of days extended: |  |  |  | Slippage: | 0%
Sto. Tomas | Katipunana | 2nd Eng'g. Dist. | On-going | 2019-12-27 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | [7 empty] | Date Allotment Released: | 2019-01-03 | Date completed:
Sto. Tomas | Katipunana | 2nd Eng'g. Dist. | On-going | 2019-12-27 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | [7 empty] | Date Started: | 2019-12-27
B.E. Dujali | Tanglaw | 2nd Eng'g. Dist. | On-going | 2019-06-17 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | ROAD ID 142 - Jct. Highway - Tanglaw |  | 20% DF CY 2019 | Road Rehabilitation | 3.98 | km | Admin | Project Cost: | 1100000 | Target Completion Date: | 2019-09-16 | Program: | 1100000 | Planned: | 100% | No. of Persons: | 10 | On-going
B.E. Dujali | Tanglaw | 2nd Eng'g. Dist. | On-going | 2019-06-17 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | [7 empty] | Project Engineer: | Gamad/Clar | Revised Completion Date: | 2020-02-29 | Allotment: | 1100000 | Revised: | 73.59% | No. of Man-days: | 50
B.E. Dujali | Tanglaw | 2nd Eng'g. Dist. | On-going | 2019-06-17 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | [7 empty] | Implementor: | PEO | No. of days suspended: | 137 | Disbursement: |  | Actual: | 85%
B.E. Dujali | Tanglaw | 2nd Eng'g. Dist. | On-going | 2019-06-17 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | [7 empty] | Duration: | 91 | No. of days extended: | 29 |  |  | Slippage: | 11.41%
B.E. Dujali | Tanglaw | 2nd Eng'g. Dist. | On-going | 2019-06-17 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | [7 empty] | Date Allotment Released: | 2019-05-16 | Date completed:
B.E. Dujali | Tanglaw | 2nd Eng'g. Dist. | On-going | 2019-06-17 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | [7 empty] | Date Started: | 2019-06-17
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | On-going | 2019-12-27 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | ROAD ID 146 - Bdry. Tagum - Crossing Kinamayan Sto. Tomas |  | 20% DF CY 2019 | Road Rehabilitation | 0.75 | km | Admin | Project Cost: | 3700000 | Target Completion Date: | 2020-04-25 | Program: | 3700000 | Planned: | 100% | No. of Persons: | 15 | On-going
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | On-going | 2019-12-27 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | [7 empty] | Project Engineer: | Gamad/Clar | Revised Completion Date: | 2020-08-23 | Allotment: | 3700000 | Revised: | 15.43% | No. of Man-days: | 225
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | On-going | 2019-12-27 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | [7 empty] | Implementor: |  | No. of days suspended: | 20 | Disbursement: |  | Actual: | 16.37%
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | On-going | 2019-12-27 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | [7 empty] | Duration: | 120 | No. of days extended: | 100 |  |  | Slippage: | 0.94%
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | On-going | 2019-12-27 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | [7 empty] | Date Allotment Released: | 2019-01-03 | Date completed:
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | On-going | 2019-12-27 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | [7 empty] | Date Started: | 2019-12-27
Sto. Tomas | San Jose | 2nd Eng'g. Dist. | On-going | 2020-05-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | Fr. Rd. 3 - San Jose |  | 20% DF CY 2019 | Road Rehabilitation | 4.55 | km | Admin | Project Cost: | 800000 | Target Completion Date: | 2020-08-06 | Program: | 800000 | Planned: | 2.14% | No. of Persons: | 3 | On-going
Sto. Tomas | San Jose | 2nd Eng'g. Dist. | On-going | 2020-05-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Project Engineer: | Obar | Revised Completion Date: |  | Allotment: | 800000 | Revised: |  | No. of Man-days: | 30
Sto. Tomas | San Jose | 2nd Eng'g. Dist. | On-going | 2020-05-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: | 2.14%
Sto. Tomas | San Jose | 2nd Eng'g. Dist. | On-going | 2020-05-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Duration: | 80 | No. of days extended: |  |  |  | Slippage: | 0%
Sto. Tomas | San Jose | 2nd Eng'g. Dist. | On-going | 2020-05-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Date Allotment Released: | 2019-01-03 | Date completed:
Sto. Tomas | San Jose | 2nd Eng'g. Dist. | On-going | 2020-05-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Date Started: | 2020-05-18
Carmen | Asuncion | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | Lower Asuncion - Upper Asuncion |  | 20% DF CY 2019 | Road Rehabilitation | 1.02 | km | Admin | Project Cost: |  | Target Completion Date: |  | Program: | 0 | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
Carmen | Asuncion | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 0 | Revised: |  | No. of Man-days:
Carmen | Asuncion | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Carmen | Asuncion | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Carmen | Asuncion | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Date Allotment Released: |  | Date completed:
Carmen | Asuncion | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Date Started:
Carmen | Mangalcal | 2nd Eng'g. Dist. | On-going | 2020-06-15 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | Jct. Highway - Carmen - Mangalcal - Tubod |  | 20% DF CY 2019 | Road Rehabilitation | 11.34 | km | Admin | Project Cost: | 1323000 | Target Completion Date: | 2020-07-15 | Program: | 1323000 | Planned: | 100% | No. of Persons: | 3 | On-going
Carmen | Mangalcal | 2nd Eng'g. Dist. | On-going | 2020-06-15 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Project Engineer: | Obar | Revised Completion Date: |  | Allotment: | 1323000 | Revised: |  | No. of Man-days: | 30
Carmen | Mangalcal | 2nd Eng'g. Dist. | On-going | 2020-06-15 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: | 1.21%
Carmen | Mangalcal | 2nd Eng'g. Dist. | On-going | 2020-06-15 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Duration: | 30 | No. of days extended: |  |  |  | Slippage: | -98.79%
Carmen | Mangalcal | 2nd Eng'g. Dist. | On-going | 2020-06-15 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Date Allotment Released: | 2019-01-03 | Date completed:
Carmen | Mangalcal | 2nd Eng'g. Dist. | On-going | 2020-06-15 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Date Started: | 2020-06-15
B.E. Dujali | Tuganay-Taba | 2nd Eng'g. Dist. | On-going | 2020-05-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | Tuganay - Taba |  | 20% DF CY 2019 | Road Rehabilitation | 4.27 | km | Admin | Project Cost: | 507500 | Target Completion Date: | 2020-06-17 | Program: | 507500 | Planned: | 100% | No. of Persons: | 3 | On-going
B.E. Dujali | Tuganay-Taba | 2nd Eng'g. Dist. | On-going | 2020-05-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Project Engineer: | Obar | Revised Completion Date: |  | Allotment: | 507500 | Revised: |  | No. of Man-days: | 30
B.E. Dujali | Tuganay-Taba | 2nd Eng'g. Dist. | On-going | 2020-05-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: | 3.37%
B.E. Dujali | Tuganay-Taba | 2nd Eng'g. Dist. | On-going | 2020-05-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Duration: | 30 | No. of days extended: |  |  |  | Slippage: | -96.63%
B.E. Dujali | Tuganay-Taba | 2nd Eng'g. Dist. | On-going | 2020-05-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Date Allotment Released: | 2019-01-03 | Date completed:
B.E. Dujali | Tuganay-Taba | 2nd Eng'g. Dist. | On-going | 2020-05-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Date Started: | 2020-05-18
B.E. Dujali | Ising | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | Jct. Highway - Ising - Magsaysay |  | 20% DF CY 2019 | Road Rehabilitation | 10.84 | km | Admin | Project Cost: | 6000000 | Target Completion Date: |  | Program: | 6000000 | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
B.E. Dujali | Ising | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 6000000 | Revised: |  | No. of Man-days:
B.E. Dujali | Ising | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
B.E. Dujali | Ising | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
B.E. Dujali | Ising | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Date Allotment Released: |  | Date completed:
B.E. Dujali | Ising | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Date Started:
B.E. Dujali | Guadalupe | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | Jct. Highway - Guadalupe - Bdry. Tagum |  | 20% DF CY 2019 | Road Rehabilitation | 7.9 | km | Admin | Project Cost: | 910000 | Target Completion Date: | 2020-08-06 | Program: | 910000 | Planned: | 2.04% | No. of Persons: | 3 | On-going
B.E. Dujali | Guadalupe | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Project Engineer: | Obar | Revised Completion Date: |  | Allotment: | 910000 | Revised: |  | No. of Man-days: | 30
B.E. Dujali | Guadalupe | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: | 2.04%
B.E. Dujali | Guadalupe | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Duration: | 80 | No. of days extended: |  |  |  | Slippage: | 0%
B.E. Dujali | Guadalupe | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Date Allotment Released: | 2019-01-03 | Date completed:
B.E. Dujali | Guadalupe | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Date Started: | 2020-05-18
Carmen | Tibulao | 2nd Eng'g. Dist. | On-going | 2020-05-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | Sitio Malaga - Tibulao |  | 20% DF CY 2019 | Road Rehabilitation | 3.22 | km | Admin | Project Cost: | 300000 | Target Completion Date: | 2020-08-06 | Program: | 300000 | Planned: | 3.37% | No. of Persons: | 3 | On-going
Carmen | Tibulao | 2nd Eng'g. Dist. | On-going | 2020-05-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Project Engineer: | Obar | Revised Completion Date: |  | Allotment: | 300000 | Revised: |  | No. of Man-days: | 30
Carmen | Tibulao | 2nd Eng'g. Dist. | On-going | 2020-05-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: | 3.37%
Carmen | Tibulao | 2nd Eng'g. Dist. | On-going | 2020-05-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Duration: | 80 | No. of days extended: |  |  |  | Slippage:
Carmen | Tibulao | 2nd Eng'g. Dist. | On-going | 2020-05-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Date Allotment Released: | 2019-01-03 | Date completed:
Carmen | Tibulao | 2nd Eng'g. Dist. | On-going | 2020-05-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Date Started: | 2020-05-18
Carmen | New Casay | 2nd Eng'g. Dist. | On-going | 2020-05-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | Prk. 5 RJS - Prk 6 New Casay |  | 20% DF CY 2019 | Road Rehabilitation | 2.73 | km | Admin | Project Cost: | 350000 | Target Completion Date: | 2020-06-17 | Program: | 350000 | Planned: | 3.37% | No. of Persons: | 3 | On-going
Carmen | New Casay | 2nd Eng'g. Dist. | On-going | 2020-05-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Project Engineer: | Obar | Revised Completion Date: |  | Allotment: | 350000 | Revised: |  | No. of Man-days: | 30
Carmen | New Casay | 2nd Eng'g. Dist. | On-going | 2020-05-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: | 3.37%
Carmen | New Casay | 2nd Eng'g. Dist. | On-going | 2020-05-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Duration: | 30 | No. of days extended: |  |  |  | Slippage: | 0%
Carmen | New Casay | 2nd Eng'g. Dist. | On-going | 2020-05-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Date Allotment Released: | 2019-01-03 | Date completed:
Carmen | New Casay | 2nd Eng'g. Dist. | On-going | 2020-05-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Date Started: | 2020-05-18
B.E. Dujali | San Vicente | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | Dujali - Pawas - San Vicente |  | 20% DF CY 2019 | Road Rehabilitation | 4.42 | km | Admin | Project Cost: | 525000 | Target Completion Date: | 2020-07-02 | Program: | 525000 | Planned: | 2.41% | No. of Persons: | 3 | On-going
B.E. Dujali | San Vicente | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Project Engineer: | Obar | Revised Completion Date: |  | Allotment: | 525000 | Revised: |  | No. of Man-days: | 30
B.E. Dujali | San Vicente | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: | 2.41%
B.E. Dujali | San Vicente | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Duration: | 45 | No. of days extended: |  |  |  | Slippage: | 0%
B.E. Dujali | San Vicente | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Date Allotment Released: | 2019-01-03 | Date completed:
B.E. Dujali | San Vicente | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Date Started: | 2020-05-18
Sto. Tomas | Esperanza | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | Los Amigos 1 - Esperanza - Los Amigos 2 |  | 20% DF CY 2019 | Road Rehabilitation | 3.59 | km | Admin | Project Cost: | 19200000 | Target Completion Date: |  | Program: | 19200000 | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
Sto. Tomas | Esperanza | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 19200000 | Revised: |  | No. of Man-days:
Sto. Tomas | Esperanza | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Sto. Tomas | Esperanza | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Sto. Tomas | Esperanza | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Date Allotment Released: |  | Date completed:
Sto. Tomas | Esperanza | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Date Started:
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | On-going | 2020-05-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | San Miguel - Crossing Kinamayan |  | 20% DF CY 2019 | Road Rehabilitation | 2.8 | km | Admin | Project Cost: | 350000 | Target Completion Date: | 2020-07-17 | Program: | 350000 | Planned: | 22.58% | No. of Persons: | 6 | On-going
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | On-going | 2020-05-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Project Engineer: | Piad/ Obar | Revised Completion Date: |  | Allotment: | 350000 | Revised: |  | No. of Man-days: | 84
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | On-going | 2020-05-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: | 22.58%
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | On-going | 2020-05-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Duration: | 60 | No. of days extended: |  |  |  | Slippage: | 0%
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | On-going | 2020-05-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Date Allotment Released: | 2019-01-03 | Date completed:
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | On-going | 2020-05-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Date Started: | 2020-05-18
Sto. Tomas | Magwawa | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | Fd Rd 2 - Sto. Tomas - Magwawa |  | 20% DF CY 2019 | Road Rehabilitation | 10.21 | km | Admin | Project Cost: |  | Target Completion Date: |  | Program: | 0 | Planned: |  | No. of Persons: |  | Plan and POW Approved
Sto. Tomas | Magwawa | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 0 | Revised: |  | No. of Man-days:
Sto. Tomas | Magwawa | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Sto. Tomas | Magwawa | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Sto. Tomas | Magwawa | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Date Allotment Released: |  | Date completed:
Sto. Tomas | Magwawa | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Date Started:
Sto. Tomas | Tulalian | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | Menzi - Balagunan - Tulalian |  | 20% DF CY 2019 | Road Rehabilitation | 10.63 | km | Admin | Project Cost: | 3720500 | Target Completion Date: |  | Program: | 3720500 | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
Sto. Tomas | Tulalian | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 3720500 | Revised: |  | No. of Man-days:
Sto. Tomas | Tulalian | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Sto. Tomas | Tulalian | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Sto. Tomas | Tulalian | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Date Allotment Released: |  | Date completed:
Sto. Tomas | Tulalian | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Date Started:
Sto. Tomas | Talomo | 2nd Eng'g. Dist. | On-going | 2020-05-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | Jct. Bdry. Tagum - Talomo |  | 20% DF CY 2019 | Road Rehabilitation | 12.01 | km | Admin | Project Cost: | 1400000 | Target Completion Date: | 2020-09-15 | Program: | 1400000 | Planned: | 3% | No. of Persons: | 3 | On-going
Sto. Tomas | Talomo | 2nd Eng'g. Dist. | On-going | 2020-05-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Project Engineer: | Obar | Revised Completion Date: |  | Allotment: | 1400000 | Revised: |  | No. of Man-days: | 30
Sto. Tomas | Talomo | 2nd Eng'g. Dist. | On-going | 2020-05-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: | 3.37%
Sto. Tomas | Talomo | 2nd Eng'g. Dist. | On-going | 2020-05-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Duration: | 120 | No. of days extended: |  |  |  | Slippage: | 0.37%
Sto. Tomas | Talomo | 2nd Eng'g. Dist. | On-going | 2020-05-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Date Allotment Released: | 2019-01-23 | Date completed:
Sto. Tomas | Talomo | 2nd Eng'g. Dist. | On-going | 2020-05-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Date Started: | 2020-05-18
Carmen | Anibongan | 2nd Eng'g. Dist. | Completed | 2019-05-22 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | Rehab. of Anibongan-Salvacion-Cabay-angan Provincial Road with Drainage |  | 20% DF CY 2019 | Road Drainage rehabiliated |  | km | Admin | Project Cost: | 2000000 | Target Completion Date: | 2019-08-04 23:59 | Program: | 2000000 | Planned: | 100% | No. of Persons: | 1 | Completed as per physical accomplishment. Financial documents still on process.
Carmen | Anibongan | 2nd Eng'g. Dist. | Completed | 2019-05-22 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Project Engineer: | Toquero | Revised Completion Date: | 2019-12-31 23:59 | Allotment: | 2000000 | Revised: |  | No. of Man-days: | 4
Carmen | Anibongan | 2nd Eng'g. Dist. | Completed | 2019-05-22 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: | 100%
Carmen | Anibongan | 2nd Eng'g. Dist. | Completed | 2019-05-22 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Duration: | 75 | No. of days extended: | 149 |  |  | Slippage: | 0%
Carmen | Anibongan | 2nd Eng'g. Dist. | Completed | 2019-05-22 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Date Allotment Released: | 2019-01-14 | Date completed: | 2020-01-31
Carmen | Anibongan | 2nd Eng'g. Dist. | Completed | 2019-05-22 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Date Started: | 2019-05-22
B.E. Dujali | Dujali | 2nd Eng'g. Dist. | On-going | 2019-11-04 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various of Local Roads & Drainage Development Project (Provincewide) LS - 15,000,000.00 | Rehab. Of Dujali-Pawas-San Vicente Provincial Road |  | 20% DF CY 2019 | Road Drainage rehabiliated |  | km | Admin | Project Cost: | 2000000 | Target Completion Date: |  | Program: | 2000000 | Planned: | 80% | No. of Persons: |  | On-going
B.E. Dujali | Dujali | 2nd Eng'g. Dist. | On-going | 2019-11-04 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various of Local Roads & Drainage Development Project (Provincewide) LS - 15,000,000.00 | [7 empty] | Project Engineer: | Toquero | Revised Completion Date: |  | Allotment: | 2000000 | Revised: |  | No. of Man-days:
B.E. Dujali | Dujali | 2nd Eng'g. Dist. | On-going | 2019-11-04 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various of Local Roads & Drainage Development Project (Provincewide) LS - 15,000,000.00 | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: | 80%
B.E. Dujali | Dujali | 2nd Eng'g. Dist. | On-going | 2019-11-04 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various of Local Roads & Drainage Development Project (Provincewide) LS - 15,000,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
B.E. Dujali | Dujali | 2nd Eng'g. Dist. | On-going | 2019-11-04 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various of Local Roads & Drainage Development Project (Provincewide) LS - 15,000,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
B.E. Dujali | Dujali | 2nd Eng'g. Dist. | On-going | 2019-11-04 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various of Local Roads & Drainage Development Project (Provincewide) LS - 15,000,000.00 | [7 empty] | Date Started: | 2019-11-04
B.E. Dujali | Ising | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various of Local Roads & Drainage Development Project (Provincewide) LS - 15,000,000.00 | Rehab./Impv't. of Jct. highway Ising-Magsaysay Provincial Road with Drainage |  | 20% DF CY 2019 | Road Drainage rehabiliated |  | km | Admin | Project Cost: | 1500000 | Target Completion Date: |  | Program: | 1500000 | Planned: |  | No. of Persons: |  | Revised POW for approval - Jan. 7, 2020 Revision was made due to scarcity of boulders changing from stone masonry to concrete masonry
B.E. Dujali | Ising | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various of Local Roads & Drainage Development Project (Provincewide) LS - 15,000,000.00 | [7 empty] | Project Engineer: | Toquero | Revised Completion Date: |  | Allotment: | 1500000 | Revised: |  | No. of Man-days:
B.E. Dujali | Ising | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various of Local Roads & Drainage Development Project (Provincewide) LS - 15,000,000.00 | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual:
B.E. Dujali | Ising | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various of Local Roads & Drainage Development Project (Provincewide) LS - 15,000,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
B.E. Dujali | Ising | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various of Local Roads & Drainage Development Project (Provincewide) LS - 15,000,000.00 | [7 empty] | Date Allotment Released: | 2019-01-16 | Date completed:
B.E. Dujali | Ising | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various of Local Roads & Drainage Development Project (Provincewide) LS - 15,000,000.00 | [7 empty] | Date Started:
Panabo City | Consolacion | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | Impv't. of Potable Water System, Consolacion, Panabo City |  | 20% DF CY 2019 | Water System |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
Panabo City | Consolacion | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Panabo City | Consolacion | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Panabo City | Consolacion | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Panabo City | Consolacion | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | [7 empty] | Date Allotment Released: | 2019-06-28 | Date completed:
Panabo City | Consolacion | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | [7 empty] | Date Started:
Samal | Tagbitan-ag | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | Impv't. of Potable Water System, Tagbitan-ag, Samal Dist. |  | 20% DF CY 2019 | Water System |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | For implementation
Samal | Tagbitan-ag | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Samal | Tagbitan-ag | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Samal | Tagbitan-ag | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Samal | Tagbitan-ag | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | [7 empty] | Date Allotment Released: | 2019-06-19 | Date completed:
Samal | Tagbitan-ag | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | [7 empty] | Date Started:
Babak | San Antonio | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | Impv't. of Potable Water System, San Antonio, babak, IGCS |  | 20% DF CY 2019 | Water System |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
Babak | San Antonio | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Babak | San Antonio | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Babak | San Antonio | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Babak | San Antonio | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | [7 empty] | Date Allotment Released: | 2019-06-25 | Date completed:
Babak | San Antonio | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | [7 empty] | Date Started:
IGCS | Mambago | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | Impv't. of Potable Water System, Mambago-A, IGCS |  | 20% DF CY 2019 | Water System |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | For Implementation
IGCS | Mambago | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
IGCS | Mambago | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
IGCS | Mambago | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
IGCS | Mambago | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | [7 empty] | Date Allotment Released: | 2019-09-10 | Date completed:
IGCS | Mambago | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | [7 empty] | Date Started:
Panabo City | Buenavista | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | Construction of PWS, Brgy. Buenavista, Panabo City |  | 20% DF CY 2019 | Water System |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | For implementation
Panabo City | Buenavista | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Panabo City | Buenavista | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Panabo City | Buenavista | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Panabo City | Buenavista | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | [7 empty] | Date Allotment Released: | June 19 ,2019 | Date completed:
Panabo City | Buenavista | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | [7 empty] | Date Started:
Panabo City | Kiotoy | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | Construction of PWS, Brgy. Brgy. Kiotoy, Panabo City |  | 20% DF CY 2019 | Water System |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
Panabo City | Kiotoy | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Panabo City | Kiotoy | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Panabo City | Kiotoy | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Panabo City | Kiotoy | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Panabo City | Kiotoy | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | [7 empty] | Date Started:
IGCS | Linusotan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | Construction of PWS, Brgy. Linusotan, Talikud, District, IGCS |  | 20% DF CY 2019 | Water System |  |  |  | Project Cost: | 1300000 | Target Completion Date: |  | Program: | 1300000 | Planned: |  | No. of Persons: |  | Procurement on process
IGCS | Linusotan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 1300000 | Revised: |  | No. of Man-days:
IGCS | Linusotan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
IGCS | Linusotan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
IGCS | Linusotan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | [7 empty] | Date Allotment Released: | 2019-10-23 | Date completed:
IGCS | Linusotan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | [7 empty] | Date Started:
Babak, IGCS | San Miguel | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | Rehab. of PWS, Brgy. San Miguel, Babak, IGCS |  | 20% DF CY 2019 | Water System |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
Babak, IGCS | San Miguel | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Babak, IGCS | San Miguel | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Babak, IGCS | San Miguel | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Babak, IGCS | San Miguel | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Babak, IGCS | San Miguel | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | [7 empty] | Date Started:
Panabo City | Cacao | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | Construction of PWS, Brgy. Cacao, Panabo City |  | 20% DF CY 2019 | Water System |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | For cancellation. Purchase of Geo-resistivity equipment but procurement still on process
Panabo City | Cacao | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Panabo City | Cacao | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Panabo City | Cacao | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Panabo City | Cacao | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Panabo City | Cacao | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | [7 empty] | Date Started:
Kaputian, IGCS | Pangubatan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | Rehabilitation of Potable Water System, Brgy. Pangubatan, kaputian Dist. IGCS |  | 20% DF CY 2019 | Water System |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | For implementation
Kaputian, IGCS | Pangubatan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Kaputian, IGCS | Pangubatan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Kaputian, IGCS | Pangubatan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Kaputian, IGCS | Pangubatan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Kaputian, IGCS | Pangubatan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | [7 empty] | Date Started:
Carmen | Ising | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Government Buildings and Facilities Development Project (Provincewide) LS - P 27,000,000.00 | Const. of DDN Hospital Carmen Zone Annex Bldg. Phase 2, |  | 20% DF CY 2019 | Building |  | sq.m | Contract | Project Cost: | 3620000 | Target Completion Date: |  | Program: | 3620000 | Planned: |  | No. of Persons: |  | For implementation (Winning Bidder - Digos Constrak Corp.)
Carmen | Ising | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Government Buildings and Facilities Development Project (Provincewide) LS - P 27,000,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 3620000 | Revised: |  | No. of Man-days:
Carmen | Ising | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Government Buildings and Facilities Development Project (Provincewide) LS - P 27,000,000.00 | [7 empty] | Implementor: | Digos Constrak Corp/ | No. of days suspended: |  | Disbursement: |  | Actual:
Carmen | Ising | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Government Buildings and Facilities Development Project (Provincewide) LS - P 27,000,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Carmen | Ising | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Government Buildings and Facilities Development Project (Provincewide) LS - P 27,000,000.00 | [7 empty] | Date Allotment Released: | 2019-06-28 | Date completed:
Carmen | Ising | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | [7 empty] | Date Started:
Carmen | La Paz | 2nd Eng'g. Dist. | On-going | 2019-08-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | Const. of Multi-Purpose Hall, La Paz, Carmen |  | 20% DF CY 2019 (STIMULUS | Building |  | sq.m | MLGU | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Fund transferred to LGU March 28, 2019
Carmen | La Paz | 2nd Eng'g. Dist. | On-going | 2019-08-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Carmen | La Paz | 2nd Eng'g. Dist. | On-going | 2019-08-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Carmen | La Paz | 2nd Eng'g. Dist. | On-going | 2019-08-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Carmen | La Paz | 2nd Eng'g. Dist. | On-going | 2019-08-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Allotment Released: | 2019-02-20 | Date completed:
Carmen | La Paz | 2nd Eng'g. Dist. | On-going | 2019-08-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Started: | 2019-08-16
Carmen | Sto. Niño | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | Const. of Evacuation Center Ph. 3, Sto. Niño, Carmen |  | 20% DF CY 2019 (STIMULUS | Building |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Amended in the AIP 3rd revision CY 2019/ SB No. 4 CY 2019 changing the location to Purok !-c, Sto. Nino since the previous location was implemented by DPWH
Carmen | Sto. Niño | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Carmen | Sto. Niño | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Carmen | Sto. Niño | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Carmen | Sto. Niño | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Carmen | Sto. Niño | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Started:
Carmen | Mangalcal | 2nd Eng'g. Dist. | On-going | 2019-09-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | Const. of Multi-Purpose Hall, Mangalcal, Carmen |  | 20% DF CY 2019 (STIMULUS | Building |  | sq.m | MLGU | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Fund transfer to LGU Carmen, 3/28/2019 with check no. 2574953 and OR no. 0118982
Carmen | Mangalcal | 2nd Eng'g. Dist. | On-going | 2019-09-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Carmen | Mangalcal | 2nd Eng'g. Dist. | On-going | 2019-09-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Carmen | Mangalcal | 2nd Eng'g. Dist. | On-going | 2019-09-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Carmen | Mangalcal | 2nd Eng'g. Dist. | On-going | 2019-09-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Allotment Released: | 2019-02-20 | Date completed:
Carmen | Mangalcal | 2nd Eng'g. Dist. | On-going | 2019-09-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Started: | 2019-09-16
Carmen | Guadalupe | 2nd Eng'g. Dist. | On-going | 2019-08-15 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | Rehab. of Multi-Purpose Hall, Guadalupe, Carmen |  | 20% DF CY 2019 (STIMULUS | Building |  |  | MLGU | Project Cost: | 500000 | Target Completion Date: | 2019-11-13 23:59 | Program: | 500000 | Planned: |  | No. of Persons: |  | Fund transferred to LGU March 28, 2019
Carmen | Guadalupe | 2nd Eng'g. Dist. | On-going | 2019-08-15 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Carmen | Guadalupe | 2nd Eng'g. Dist. | On-going | 2019-08-15 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Carmen | Guadalupe | 2nd Eng'g. Dist. | On-going | 2019-08-15 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Duration: | 91 | No. of days extended: |  |  |  | Slippage: | 0%
Carmen | Guadalupe | 2nd Eng'g. Dist. | On-going | 2019-08-15 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Allotment Released: | 2019-02-20 | Date completed:
Carmen | Guadalupe | 2nd Eng'g. Dist. | On-going | 2019-08-15 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Started: | 2019-08-15
Carmen | Mabuhay | 2nd Eng'g. Dist. | On-going | 2019-08-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | Const. of Multi-Purpose Hall, Mabuhay, Carmen |  | 20% DF CY 2019 (STIMULUS | Building |  | sq.m | MLGU | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Fund transfer to LGU Carmen, 3/28/2019 with check no. 2574925 and OR no. 0118984
Carmen | Mabuhay | 2nd Eng'g. Dist. | On-going | 2019-08-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Carmen | Mabuhay | 2nd Eng'g. Dist. | On-going | 2019-08-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Carmen | Mabuhay | 2nd Eng'g. Dist. | On-going | 2019-08-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Carmen | Mabuhay | 2nd Eng'g. Dist. | On-going | 2019-08-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Allotment Released: | 2019-02-20 | Date completed:
Carmen | Mabuhay | 2nd Eng'g. Dist. | On-going | 2019-08-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Started: | 2019-08-16
Carmen | Mabaus | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | Const. Canal Lining , Mabaus, Carmen |  | 20% DF CY 2019 (STIMULUS | Canal lining |  |  | MLGU | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Fund transferred to LGU March 28, 2019
Carmen | Mabaus | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Carmen | Mabaus | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Carmen | Mabaus | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Carmen | Mabaus | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Allotment Released: | 2019-02-20 | Date completed:
Carmen | Mabaus | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Started:
Carmen | Alejal | 2nd Eng'g. Dist. | On-going | 2019-08-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | Rehab. Of Evacuation Center, Alejal, Carmen |  | 20% DF CY 2019 (STIMULUS | Building |  | sq.m | MLGU | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Fund transfer to LGU Carmen, 3/28/2019 with check no.2574949 and OR no. 0118991
Carmen | Alejal | 2nd Eng'g. Dist. | On-going | 2019-08-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Carmen | Alejal | 2nd Eng'g. Dist. | On-going | 2019-08-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Carmen | Alejal | 2nd Eng'g. Dist. | On-going | 2019-08-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Carmen | Alejal | 2nd Eng'g. Dist. | On-going | 2019-08-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Allotment Released: | 2019-02-20 | Date completed:
Carmen | Alejal | 2nd Eng'g. Dist. | On-going | 2019-08-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Started: | 2019-08-16
Carmen | Tuganay | 2nd Eng'g. Dist. | On-going | 2019-08-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | Compl. Of Evacuation Center, Tuganay, Carmen |  | 20% DF CY 2019 (STIMULUS | Building |  | sq.m | MLGU | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Fund transfer to LGU Carmen, 3/28/2019 with check no. 2574947 and OR no. 0118995
Carmen | Tuganay | 2nd Eng'g. Dist. | On-going | 2019-08-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Carmen | Tuganay | 2nd Eng'g. Dist. | On-going | 2019-08-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Carmen | Tuganay | 2nd Eng'g. Dist. | On-going | 2019-08-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Carmen | Tuganay | 2nd Eng'g. Dist. | On-going | 2019-08-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Allotment Released: | 2019-02-20 | Date completed:
Carmen | Tuganay | 2nd Eng'g. Dist. | On-going | 2019-08-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Started: | 2019-08-16
Carmen | Ising | 2nd Eng'g. Dist. | On-going | 2019-08-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | Const. of Multi-Purpose hall, Ising, Carmen |  | 20% DF CY 2019 (STIMULUS | Building |  |  | MLGU | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Fund transferred to LGU March 28, 2019
Carmen | Ising | 2nd Eng'g. Dist. | On-going | 2019-08-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Carmen | Ising | 2nd Eng'g. Dist. | On-going | 2019-08-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Carmen | Ising | 2nd Eng'g. Dist. | On-going | 2019-08-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Carmen | Ising | 2nd Eng'g. Dist. | On-going | 2019-08-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Allotment Released: | 2019-02-20 | Date completed:
Carmen | Ising | 2nd Eng'g. Dist. | On-going | 2019-08-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Started:
Carmen | Cebulano | 2nd Eng'g. Dist. | On-going | 2019-08-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | Rehab. of Multi-Purpose hall, Cebulano, Carmen |  | 20% DF CY 2019 (STIMULUS | Building |  | sq.m | MLGU | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Fund transferred to LGU March 28, 2019
Carmen | Cebulano | 2nd Eng'g. Dist. | On-going | 2019-08-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Carmen | Cebulano | 2nd Eng'g. Dist. | On-going | 2019-08-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Carmen | Cebulano | 2nd Eng'g. Dist. | On-going | 2019-08-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Carmen | Cebulano | 2nd Eng'g. Dist. | On-going | 2019-08-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Allotment Released: | 2019-02-20 | Date completed:
Carmen | Cebulano | 2nd Eng'g. Dist. | On-going | 2019-08-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Started: | 2019-08-16
Panabo City | Kasilak | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | Rehab. Of Multi-Purpose Hall, Kasilak, Panabo City |  | 20% DF CY 2019 (STIMULUS | Building |  |  | Contract | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | PO #2020041509 - JJR CONSTRUCTION AND SUPPLY
Panabo City | Kasilak | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Panabo City | Kasilak | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Panabo City | Kasilak | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Panabo City | Kasilak | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Panabo City | Kasilak | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Started:
Panabo City | New Malitbog | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | Rehab. Of Multi-Purpose Hall, New Malitbog, Panabo City |  | 20% DF CY 2019 (STIMULUS | Building |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Amended in AIP 3rd revsion CY 2019 to change the project to Construction of Potable Water System because the original project will be funded by LGU, Panabo City (Brgy. resolution no. 25 series of 2019 dated Aug. 13, 2019 submitted)
Panabo City | New Malitbog | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Panabo City | New Malitbog | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Panabo City | New Malitbog | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Panabo City | New Malitbog | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Panabo City | New Malitbog | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Started:
Panabo City | New Pandan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | Desilting of Canal, New Pandan, Panabo City |  | 20% DF CY 2019 (STIMULUS | Desiltation |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
Panabo City | New Pandan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Panabo City | New Pandan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Panabo City | New Pandan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Panabo City | New Pandan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Panabo City | New Pandan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Started:
Panabo City | Waterfall | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | Const. Of Multi-Purpose Hall, Waterfall, Panabo City |  | 20% DF CY 2019 (STIMULUS | Building |  |  | Contract | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Abstract #0520201797
Panabo City | Waterfall | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Panabo City | Waterfall | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Panabo City | Waterfall | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Panabo City | Waterfall | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Panabo City | Waterfall | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Started:
Panabo City | Cagangohan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | Concreting of Brgy. Road @ Prk. Guyabano, Cagangohan, Panabo City |  | 20% DF CY 2019 (STIMULUS | Concreting |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Amended in AIP 3rd revision to change the project to Rehab of Evacuation Center because the original project has no deed of donation.(Brgy. resolution no 41 series of 2019 dated Aug. 16, 2019 submitted
Panabo City | Cagangohan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Panabo City | Cagangohan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Panabo City | Cagangohan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Panabo City | Cagangohan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Panabo City | Cagangohan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Started:
Panabo City | J.P Laurel | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | Rehab. Of Evacuation Center, J.P. Laurel, Panabo City |  | 20% DF CY 2019 (STIMULUS | Building |  |  | Contract | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Purchase Order # 2020031248- DIGOS CONSTRAK
Panabo City | J.P Laurel | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Panabo City | J.P Laurel | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Panabo City | J.P Laurel | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Panabo City | J.P Laurel | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Allotment Released: | 2019-10-23 | Date completed:
Panabo City | J.P Laurel | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Started:
Panabo City | Buenavista | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | Const. Of Multi-Purpose Hall, Buenavista, Panabo City |  | 20% DF CY 2019 (STIMULUS | Building |  |  | Contract | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Purchase Order # 2020031248- DIGOS CONSTRAK
Panabo City | Buenavista | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Panabo City | Buenavista | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Panabo City | Buenavista | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Panabo City | Buenavista | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Allotment Released: | 2019-10-18 | Date completed:
Panabo City | Buenavista | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Started:
Panabo City | San Francisco | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | Rehab. Of Multi-Purpose Hall, San Francisco, Panabo City |  | 20% DF CY 2019 (STIMULUS | Building |  |  | Contract | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Purchase Order # 2020031248- DIGOS CONSTRAK
Panabo City | San Francisco | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Panabo City | San Francisco | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Panabo City | San Francisco | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Panabo City | San Francisco | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Allotment Released: | 2019-10-18 | Date completed:
Panabo City | San Francisco | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Started:
Panabo City | Datu Abdul | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | Rehab. Of Evacuation Center, Datu Abdul Dadia, Panabo City |  | 20% DF CY 2019 (STIMULUS | Building |  |  | Contract | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Purchase Order # 2020031248- DIGOS CONSTRAK
Panabo City | Datu Abdul | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Panabo City | Datu Abdul | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Panabo City | Datu Abdul | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Panabo City | Datu Abdul | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Allotment Released: | 2019-10-18 | Date completed:
Panabo City | Datu Abdul | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Started:
Panabo City | Quezon | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | Impv't./Beautification of Brgy. Grounds, Quezon, Panabo City |  | 20% DF CY 2019 (STIMULUS | Ground dev't. |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Re aligned to other stimulus projects that needs additional funding
Panabo City | Quezon | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Panabo City | Quezon | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Panabo City | Quezon | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Panabo City | Quezon | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Panabo City | Quezon | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Started:
Panabo City | Gredu | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | Const. of Women Livelihood Center Bldg. , Gredu, Panabo City |  | 20% DF CY 2019 (STIMULUS | Building |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Fund transfer to LGU - 3/28/2019 with check no. 2574926 and OR no. 0166517 - March 28, 2019
Panabo City | Gredu | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Panabo City | Gredu | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Panabo City | Gredu | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Panabo City | Gredu | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Allotment Released: | 2019-03-28 | Date completed:
Panabo City | Gredu | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Started:
Panabo City | Salvacion | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | Const. of Canal Lining at Purok 5, Salvacion, Panabo City |  | 20% DF CY 2019 (STIMULUS | Building |  |  | Contract | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | PO #2020041516- DANIMERH CONSTRUCTION & SUPPLY
Panabo City | Salvacion | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Panabo City | Salvacion | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Panabo City | Salvacion | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Panabo City | Salvacion | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Allotment Released: | 2019-10-18 | Date completed:
Panabo City | Salvacion | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Started:
Panabo City | New Visayas | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | Rehab. Of Health Center, New Visayas, Panabo City |  | 20% DF CY 2019 (STIMULUS | Building |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Re aligned to other stimulus projects that needs additional funding
Panabo City | New Visayas | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Panabo City | New Visayas | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Panabo City | New Visayas | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Panabo City | New Visayas | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Panabo City | New Visayas | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Started:
Panabo City | Little Panay | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | Rehab. Of Multi-Purpose Hall, Little Panay, Panabo City |  | 20% DF CY 2019 (STIMULUS | Building |  |  | Contract | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Abstract #0520201796
Panabo City | Little Panay | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Panabo City | Little Panay | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Panabo City | Little Panay | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Panabo City | Little Panay | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Panabo City | Little Panay | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Started:
Panabo City | Dalisay | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | Rehab. Of Brgy. Health Center, Dalisay, Panabo City |  | 20% DF CY 2019 (STIMULUS | Building |  |  | Contract | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Abstract #0520201798
Panabo City | Dalisay | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Panabo City | Dalisay | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Panabo City | Dalisay | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Panabo City | Dalisay | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Panabo City | Dalisay | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Started:
Panabo City | Southern Davao | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | Const. of Multi-Purpose Hall, Southern Davao, Panabo City |  | 20% DF CY 2019 (STIMULUS | Building |  |  | Contract | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Abstract #0520201798
Panabo City | Southern Davao | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Panabo City | Southern Davao | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Panabo City | Southern Davao | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Panabo City | Southern Davao | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Panabo City | Southern Davao | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Started:
Sto. Tomas | Casig-ang | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | Rehab. Of Evacuation Center, Casig-ang, Sto. Tomas |  | 20% DF CY 2019 (STIMULUS | Building |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | PR #20063670
Sto. Tomas | Casig-ang | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Sto. Tomas | Casig-ang | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Sto. Tomas | Casig-ang | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Sto. Tomas | Casig-ang | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Sto. Tomas | Casig-ang | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Started:
Sto. Tomas | Tibal-og | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | Const. of Brgy. Tibal-og Health Center, Tibal-og, Sto. Tomas |  | 20% DF CY 2019 (STIMULUS | Building |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | POW preparation completed amounting t oP1,550,000.00. To request for additional funds in order to complete the project to be functional
Sto. Tomas | Tibal-og | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Sto. Tomas | Tibal-og | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Sto. Tomas | Tibal-og | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Sto. Tomas | Tibal-og | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Sto. Tomas | Tibal-og | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Started:
Sto. Tomas | La Libertad | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | Compl.of Brgy. Public Market, La Libertad, Sto. Tomas |  | 20% DF CY 2019 (STIMULUS | Building |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Fund transfer to LGU - 6/26/219 with check no. 2575131 and OR no. 0557457 Completed/ PCR for submission by LGU
Sto. Tomas | La Libertad | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Sto. Tomas | La Libertad | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Sto. Tomas | La Libertad | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Sto. Tomas | La Libertad | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Sto. Tomas | La Libertad | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Started:
Sto. Tomas | New Visayas | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | Rehab. Of Evacuation Center, New Visayas, Sto. Tomas |  | 20% DF CY 2019 (STIMULUS | Building |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Fund transfer to LGU - 6/26/219 with check no. 2575132 and OR no. 0557455 For implementation
Sto. Tomas | New Visayas | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Sto. Tomas | New Visayas | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Sto. Tomas | New Visayas | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Sto. Tomas | New Visayas | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Sto. Tomas | New Visayas | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Started:
Sto. Tomas | San Vicente | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | Rehab. Of Multi-Purpose Hall, San Vicente, Sto. Tomas |  | 20% DF CY 2019 (STIMULUS | Building |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Fund transferred to LGU July 5, 2019
Sto. Tomas | San Vicente | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Project Engineer: | 0 | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Sto. Tomas | San Vicente | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Sto. Tomas | San Vicente | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Sto. Tomas | San Vicente | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Sto. Tomas | San Vicente | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Started:
Sto. Tomas | Salvacion | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | Rehab. Of Multi-Purpose Hall, Salvacion, Sto. Tomas |  | 20% DF CY 2019 (STIMULUS | Building |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
Sto. Tomas | Salvacion | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Sto. Tomas | Salvacion | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Sto. Tomas | Salvacion | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Sto. Tomas | Salvacion | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Sto. Tomas | Salvacion | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Started:
Sto. Tomas | Pantaron | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | Rehab. Of Multi-Purpose Hall, Pantaron, Sto. Tomas |  | 20% DF CY 2019 (STIMULUS | Building |  |  |  | Project Cost: |  | Target Completion Date: |  | Program: | 0 | Planned: |  | No. of Persons: |  | Amended in AIP 3rd revision CY 2019 / SB No. 4 CY 2019 increasing the project cost to P550,000.00
Sto. Tomas | Pantaron | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 0 | Revised: |  | No. of Man-days:
Sto. Tomas | Pantaron | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Sto. Tomas | Pantaron | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Sto. Tomas | Pantaron | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Sto. Tomas | Pantaron | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Started:
Sto. Tomas | Magwawa | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | Rehab. Of Multi-Purpose Hall, Magwawa, Sto. Tomas |  | 20% DF CY 2019 (STIMULUS | Building |  |  | Contract | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | For implementation - Awarded to JJR CONSTRUCTION AND SUPPLY
Sto. Tomas | Magwawa | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Sto. Tomas | Magwawa | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Sto. Tomas | Magwawa | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Sto. Tomas | Magwawa | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Allotment Released: | June 19 2019 | Date completed:
Sto. Tomas | Magwawa | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Started:
Sto. Tomas | San Jose | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | Compl. Of Multi-Purpose Hall, San Jose, Sto. Tomas |  | 20% DF CY 2019 (STIMULUS | Building |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Amended in AIP 3rd revision CY 2019 / SB No. 4 CY 2019 increasing the project cost to P600,000.00
Sto. Tomas | San Jose | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Sto. Tomas | San Jose | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Sto. Tomas | San Jose | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Sto. Tomas | San Jose | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Sto. Tomas | San Jose | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Started:
Sto. Tomas | Bobongon | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | Const. of Evacuation Center, Bobongon, Sto. Tomas |  | 20% DF CY 2019 (STIMULUS | Building |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Re aligned to other stimulus projects that needs additional funding
Sto. Tomas | Bobongon | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Sto. Tomas | Bobongon | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Sto. Tomas | Bobongon | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Sto. Tomas | Bobongon | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Sto. Tomas | Bobongon | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Started:
Sto. Tomas | Lunga-og | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | Rehab. Of Brgy. Road, Lunga-og, Sto. Tomas |  | 20% DF CY 2019 (STIMULUS | Building |  |  |  | Project Cost: |  | Target Completion Date: |  | Program: | 0 | Planned: |  | No. of Persons: |  | Amended in AIP 3rd revision CY 2019 / SB No. 4 CY 2019 increasing the project cost to P600,000.00
Sto. Tomas | Lunga-og | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 0 | Revised: |  | No. of Man-days:
Sto. Tomas | Lunga-og | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Sto. Tomas | Lunga-og | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Sto. Tomas | Lunga-og | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Sto. Tomas | Lunga-og | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Started:
Sto. Tomas | New Katipunan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | Rehab. Of Multi-Purpose Hall, New Katipunan, Sto. Tomas |  | 20% DF CY 2019 (STIMULUS | Building |  |  | Contract | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Abstract #0520201798 - Digos Constrak
Sto. Tomas | New Katipunan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Sto. Tomas | New Katipunan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Sto. Tomas | New Katipunan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Sto. Tomas | New Katipunan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Allotment Released: | 2019-06-07 | Date completed:
Sto. Tomas | New Katipunan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Started:
Sto. Tomas | San Miguel | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | Rehab. Of Multi-Purpose Hall, San Miguel, Sto. Tomas |  | 20% DF CY 2019 (STIMULUS | Building |  |  | Contract | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | PO #2020041509 - JJR CONSTRUCTION AND SUPPLY
Sto. Tomas | San Miguel | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Sto. Tomas | San Miguel | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Sto. Tomas | San Miguel | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Sto. Tomas | San Miguel | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Allotment Released: | 2019-06-07 | Date completed:
Sto. Tomas | San Miguel | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Started:
Sto. Tomas | Talomo | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | Rehab. Of Multi-Purpose Hall, Talomo, Sto. Tomas |  | 20% DF CY 2019 (STIMULUS | Building |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Fund transfer to LGU - 6/26/2019 with check no. 2575130 and OR no. 0557456 For implementation
Sto. Tomas | Talomo | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Sto. Tomas | Talomo | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Sto. Tomas | Talomo | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Sto. Tomas | Talomo | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Sto. Tomas | Talomo | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Started:
IGCS | Catagman | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | Concreting of Brgy. Road From Prk. 3 to Prk. 5, Catagman, IGCS |  | 20% DF CY 2019 (STIMULUS | Concreting |  |  | Contract | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | For implementation
IGCS | Catagman | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
IGCS | Catagman | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
IGCS | Catagman | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
IGCS | Catagman | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Allotment Released: | 2019-01-14 | Date completed:
IGCS | Catagman | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Started:
IGCS | Bandera | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | Electrification at Sitio Trinidad, Bandera, IGCS |  | 20% DF CY 2019 (STIMULUS | Electrification |  |  | Contract | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | PO #2020072352 - (3E Electrical Sales & Services)
IGCS | Bandera | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
IGCS | Bandera | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
IGCS | Bandera | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
IGCS | Bandera | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Allotment Released: | 2019-03-25 | Date completed:
IGCS | Bandera | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Started:
IGCS | Del Monte | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | Rehab. Of Multi-Purpose Hall, Del Monte, IGCS |  | 20% DF CY 2019 (STIMULUS | Building |  |  | Admin | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Pending/ activity undertaken by DPWH
IGCS | Del Monte | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
IGCS | Del Monte | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
IGCS | Del Monte | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
IGCS | Del Monte | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Allotment Released: | 2019-05-29 | Date completed:
IGCS | Del Monte | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Started:
IGCS | Tagbaobo | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | Electrification at Upper Purok Rosal, Tagbaobo, IGCS |  | 20% DF CY 2019 (STIMULUS | Electrification |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Purchase Order # 2020010002 (3E Electrical Sales & Services)
IGCS | Tagbaobo | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
IGCS | Tagbaobo | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
IGCS | Tagbaobo | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
IGCS | Tagbaobo | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
IGCS | Tagbaobo | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Started:
IGCS | Mambago-B | 2nd Eng'g. Dist. | On-going | 2019-10-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | Const. Of Multi-Purpose Hall, Mambago-B, IGCS |  | 20% DF CY 2019 (STIMULUS | Building |  | sq.m | Admin | Project Cost: | 500000 | Target Completion Date: | 2019-12-27 | Program: | 500000 | Planned: | 100% | No. of Persons: | 5 | On-going
IGCS | Mambago-B | 2nd Eng'g. Dist. | On-going | 2019-10-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Project Engineer: | Roque | Revised Completion Date: | 2020-03-29 | Allotment: | 500000 | Revised: | 99.48% | No. of Man-days: | 22
IGCS | Mambago-B | 2nd Eng'g. Dist. | On-going | 2019-10-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Implementor: | PEO | No. of days suspended: | 29 | Disbursement: |  | Actual: | 97.59%
IGCS | Mambago-B | 2nd Eng'g. Dist. | On-going | 2019-10-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Duration: | 70 | No. of days extended: | 64 |  |  | Slippage: | -1.89%
IGCS | Mambago-B | 2nd Eng'g. Dist. | On-going | 2019-10-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
IGCS | Mambago-B | 2nd Eng'g. Dist. | On-going | 2019-10-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Started: | 2019-10-18
IGCS | San Antonio | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | Const. Of Multi-Purpose Hall, San Antonio, IGCS |  | 20% DF CY 2019 (STIMULUS | Building |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | For implementation
IGCS | San Antonio | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
IGCS | San Antonio | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
IGCS | San Antonio | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
IGCS | San Antonio | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Allotment Released: | 2019-06-19 | Date completed:
IGCS | San Antonio | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Started:
IGCS | Pangubatan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | Rehab. Of Water System Intake Box and Pipeline, Pangubatan, IGCS |  | 20% DF CY 2019 (STIMULUS | Water System |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Plan and Pow completed. Waiting of deed of donation
IGCS | Pangubatan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
IGCS | Pangubatan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
IGCS | Pangubatan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
IGCS | Pangubatan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
IGCS | Pangubatan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Started:
IGCS | Cogon | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | Const. Of Multi-Purpose Hall, Cogon (Talicud), IGCS |  | 20% DF CY 2019 (STIMULUS | Building |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | For implementation
IGCS | Cogon | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
IGCS | Cogon | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
IGCS | Cogon | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
IGCS | Cogon | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
IGCS | Cogon | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Started:
IGCS | Libertad | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | Installation of Pipelines, Libertad, IGCS |  | 20% DF CY 2019 (STIMULUS | Pipelines |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | For implementation
IGCS | Libertad | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
IGCS | Libertad | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
IGCS | Libertad | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
IGCS | Libertad | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Allotment Released: | 2019-03-25 | Date completed:
IGCS | Libertad | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Started:
IGCS | Libuak | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | Rehab. Of Evacuation Center, Libuak, IGCS |  | 20% DF CY 2019 (STIMULUS | Building |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | For implementation
IGCS | Libuak | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
IGCS | Libuak | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
IGCS | Libuak | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
IGCS | Libuak | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Allotment Released: | 2019-05-29 | Date completed:
IGCS | Libuak | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Started:
IGCS | Kaputian | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | Const. of Water System Project, Pob. Kaputian, IGCS |  | 20% DF CY 2019 (STIMULUS | Water System |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | For implementation
IGCS | Kaputian | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
IGCS | Kaputian | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
IGCS | Kaputian | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
IGCS | Kaputian | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
IGCS | Kaputian | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Started:
Babak, IGCS | San Isidro | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | Rehab. Of Potable Water System, San Isidro, Babak, IGCS |  | 20% DF CY 2019 (STIMULUS | Water System |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | For implementation
Babak, IGCS | San Isidro | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Babak, IGCS | San Isidro | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Babak, IGCS | San Isidro | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Babak, IGCS | San Isidro | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Allotment Released: | 2019-06-19 | Date completed:
Babak, IGCS | San Isidro | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Started:
IGCS | San Miguel | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | Rehab. Of Potable Water System, San Miguel, IGCS |  | 20% DF CY 2019 (STIMULUS | Water System |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | For implementation
IGCS | San Miguel | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
IGCS | San Miguel | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
IGCS | San Miguel | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
IGCS | San Miguel | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Allotment Released: | 2019-02-28 | Date completed:
IGCS | San Miguel | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Started:
IGCS | San Remegio | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | Const. of Water System Ph.II, San Remegio, IGCS |  | 20% DF CY 2019 (STIMULUS | Water System |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | For implementation
IGCS | San Remegio | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
IGCS | San Remegio | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
IGCS | San Remegio | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
IGCS | San Remegio | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Allotment Released: | 2019-05-29 | Date completed:
IGCS | San Remegio | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Started:
IGCS | Licup | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | Electrificatio at Prk. 1,3,4, 6,7 & 8, Licup, IGCS |  | 20% DF CY 2019 (STIMULUS | Electrification |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | For implementation
IGCS | Licup | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
IGCS | Licup | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
IGCS | Licup | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
IGCS | Licup | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Allotment Released: | 2019-02-20 | Date completed:
IGCS | Licup | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Started:
IGCS | Kaputian | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Rural Electrification Project (Provincewide) | Rural Electrification at Sitio Sagrada, Pob. Kaputian, IGCS |  | 20% DF CY 2019 | Electrification |  |  |  | Project Cost: | 1000000 | Target Completion Date: |  | Program: | 1000000 | Planned: |  | No. of Persons: |  | Purchase Request # 19031251
IGCS | Kaputian | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Rural Electrification Project (Provincewide) | [7 empty] | Project Engineer: | Buena | Revised Completion Date: |  | Allotment: | 1000000 | Revised: |  | No. of Man-days:
IGCS | Kaputian | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Rural Electrification Project (Provincewide) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
IGCS | Kaputian | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Rural Electrification Project (Provincewide) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
IGCS | Kaputian | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Rural Electrification Project (Provincewide) | [7 empty] | Date Allotment Released: |  | Date completed:
IGCS | Kaputian | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Rural Electrification Project (Provincewide) | [7 empty] | Date Started:
Carmen | Tuganay | 2nd Eng'g. Dist. | On-going | 2009-08-19 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Revitment of Dike and Slope Proection | Repair/Rehab. Of Upper Tuganay Dike |  | 5% CALAMITY FUND CY 2019 | Dike |  | ln.m | Admin | Project Cost: | 1000000 | Target Completion Date: | 2019-09-29 | Program: | 1000000 | Planned: | 90% | No. of Persons: | 9 | On-going
Carmen | Tuganay | 2nd Eng'g. Dist. | On-going | 2009-08-19 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Revitment of Dike and Slope Proection | [7 empty] | Project Engineer: | Toquero | Revised Completion Date: |  | Allotment: | 1000000 | Revised: |  | No. of Man-days: | 80
Carmen | Tuganay | 2nd Eng'g. Dist. | On-going | 2009-08-19 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Revitment of Dike and Slope Proection | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: | 90%
Carmen | Tuganay | 2nd Eng'g. Dist. | On-going | 2009-08-19 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Revitment of Dike and Slope Proection | [7 empty] | Duration: | 41 | No. of days extended: |  |  |  | Slippage: | 0%
Carmen | Tuganay | 2nd Eng'g. Dist. | On-going | 2009-08-19 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Revitment of Dike and Slope Proection | [7 empty] | Date Allotment Released: | 2019-08-15 | Date completed:
Carmen | Tuganay | 2nd Eng'g. Dist. | On-going | 2009-08-19 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Revitment of Dike and Slope Proection | [7 empty] | Date Started: | 2019-08-19
Carmen | Ising | 2nd Eng'g. Dist. | On-going | 2019-11-15 | 2020-06-30 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPLAN CANAL | Repair of Damaged Drainage/ Creek along Abucay Creek |  | 5% CALAMITY FUND | Creek |  | ln.m | Admin | Project Cost: | 1320000 | Target Completion Date: | 2019-12-05 | Program: | 1320000 | Planned: | 100% | No. of Persons: |  | Completed as per physical accomplishment. Financial documents still on process.
Carmen | Ising | 2nd Eng'g. Dist. | On-going | 2019-11-15 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPLAN CANAL | [7 empty] | Project Engineer: | Ganaba | Revised Completion Date: | 2020-06-04 | Allotment: | 1320000 | Revised: |  | No. of Man-days:
Carmen | Ising | 2nd Eng'g. Dist. | On-going | 2019-11-15 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPLAN CANAL | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: | 100%
Carmen | Ising | 2nd Eng'g. Dist. | On-going | 2019-11-15 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPLAN CANAL | [7 empty] | Duration: | 65 | No. of days extended: | 182 |  |  | Slippage: | 0%
Carmen | Ising | 2nd Eng'g. Dist. | On-going | 2019-11-15 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPLAN CANAL | [7 empty] | Date Allotment Released: |  | Date completed: | 2020-06-30
Carmen | Ising | 2nd Eng'g. Dist. | On-going | 2019-11-15 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPLAN CANAL | [7 empty] | Date Started: | 2019-10-01
Carmen | Ising | 2nd Eng'g. Dist. | On-going | 2019-11-15 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPLAN CANAL | Repair of Damaged Drainage Creek along Panabo River |  | 5% CALAMITY FUND | Creek |  | ln.m | Admin | Project Cost: | 665000 | Target Completion Date: | 2020-01-27 | Program: | 665000 | Planned: | 100% | No. of Persons: | 3 | On-going
Carmen | Ising | 2nd Eng'g. Dist. | On-going | 2019-11-15 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPLAN CANAL | [7 empty] | Project Engineer: | Alconera | Revised Completion Date: |  | Allotment: | 665000 | Revised: |  | No. of Man-days: | 66
Carmen | Ising | 2nd Eng'g. Dist. | On-going | 2019-11-15 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPLAN CANAL | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: | 15.3%
Carmen | Ising | 2nd Eng'g. Dist. | On-going | 2019-11-15 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPLAN CANAL | [7 empty] | Duration: | 73 | No. of days extended: |  |  |  | Slippage: | -84.7%
Carmen | Ising | 2nd Eng'g. Dist. | On-going | 2019-11-15 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPLAN CANAL | [7 empty] | Date Allotment Released: |  | Date completed:
Carmen | Ising | 2nd Eng'g. Dist. | On-going | 2019-11-15 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPLAN CANAL | [7 empty] | Date Started: | 2019-11-15
Carmen | Ising | 2nd Eng'g. Dist. | On-going | 2019-11-15 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPLAN CANAL | Repair of Damaged Drainage/Creek along Tuganay-Ising River |  | 5% CALAMITY FUND | Creek |  | ln.m | Admin | Project Cost: | 1540500 | Target Completion Date: | 2020-05-15 | Program: | 1540500 | Planned: | 25.6% | No. of Persons: | 3 | On-going
Carmen | Ising | 2nd Eng'g. Dist. | On-going | 2019-11-15 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPLAN CANAL | [7 empty] | Project Engineer: | Ganaba | Revised Completion Date: |  | Allotment: | 1540500 | Revised: |  | No. of Man-days: | 66
Carmen | Ising | 2nd Eng'g. Dist. | On-going | 2019-11-15 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPLAN CANAL | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: | 23.6%
Carmen | Ising | 2nd Eng'g. Dist. | On-going | 2019-11-15 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPLAN CANAL | [7 empty] | Duration: | 182 | No. of days extended: |  |  |  | Slippage: | -2%
Carmen | Ising | 2nd Eng'g. Dist. | On-going | 2019-11-15 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPLAN CANAL | [7 empty] | Date Allotment Released: |  | Date completed:
Carmen | Ising | 2nd Eng'g. Dist. | On-going | 2019-11-15 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPLAN CANAL | [7 empty] | Date Started: | 2019-11-15
Panabo City | Lasang | 2nd Eng'g. Dist. | Completed | 2019-08-01 | 2020-05-28 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPLAN CANAL | Repair of Damaged Drainage/ Creeks along San Miguel NIA Road |  | 5% CALAMITY FUND | Creek |  | ln.m | Admin | Project Cost: | 470000 | Target Completion Date: | 2019-09-16 | Program: | 470000 | Planned: | 100% | No. of Persons: | 3 | Completed as per physical accomplishment. Financial documents still on process.
Panabo City | Lasang | 2nd Eng'g. Dist. | Completed | 2019-08-01 | 2020-05-28 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPLAN CANAL | [7 empty] | Project Engineer: | Nasol | Revised Completion Date: | 2020-05-28 | Allotment: | 470000 | Revised: |  | No. of Man-days: | 66
Panabo City | Lasang | 2nd Eng'g. Dist. | Completed | 2019-08-01 | 2020-05-28 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPLAN CANAL | [7 empty] | Implementor: | PEO | No. of days suspended: | 255 | Disbursement: |  | Actual: | 100%
Panabo City | Lasang | 2nd Eng'g. Dist. | Completed | 2019-08-01 | 2020-05-28 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPLAN CANAL | [7 empty] | Duration: | 46 | No. of days extended: |  |  |  | Slippage: | 0%
Panabo City | Lasang | 2nd Eng'g. Dist. | Completed | 2019-08-01 | 2020-05-28 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPLAN CANAL | [7 empty] | Date Allotment Released: |  | Date completed: | 2020-05-28
Panabo City | Lasang | 2nd Eng'g. Dist. | Completed | 2019-08-01 | 2020-05-28 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPLAN CANAL | [7 empty] | Date Started: | 2019-08-01
Carmen | Ising | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPLAN CANAL | Repair of Damaged Drainage/ Creeks along Sadpodon Creek |  | 5% CALAMITY FUND | Creek |  |  | Admin | Project Cost: | 470000 | Target Completion Date: |  | Program: | 470000 | Planned: |  | No. of Persons: |  | For implementation
Carmen | Ising | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPLAN CANAL | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 470000 | Revised: |  | No. of Man-days:
Carmen | Ising | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPLAN CANAL | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual:
Carmen | Ising | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPLAN CANAL | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Carmen | Ising | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPLAN CANAL | [7 empty] | Date Allotment Released: |  | Date completed:
Carmen | Ising | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPLAN CANAL | [7 empty] | Date Started:
B.E. Dujali | Pawas | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Local Roads & Drainage Development Project Construction in Progress- Infrastructure Assets | Rehabilitation of Dujali-Pawas-San Vicente Provincial Road, B.E. Dujali |  | SB # 3 CY 2019 | Road |  |  |  | Project Cost: | 2000000 | Target Completion Date: |  | Program: | 2000000 | Planned: |  | No. of Persons: |  | The amount was reduced to P1,102,900.00
B.E. Dujali | Pawas | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Local Roads & Drainage Development Project Construction in Progress- Infrastructure Assets | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 2000000 | Revised: |  | No. of Man-days:
B.E. Dujali | Pawas | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Local Roads & Drainage Development Project Construction in Progress- Infrastructure Assets | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
B.E. Dujali | Pawas | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Local Roads & Drainage Development Project Construction in Progress- Infrastructure Assets | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
B.E. Dujali | Pawas | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Local Roads & Drainage Development Project Construction in Progress- Infrastructure Assets | [7 empty] | Date Allotment Released: |  | Date completed:
B.E. Dujali | Pawas | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Local Roads & Drainage Development Project Construction in Progress- Infrastructure Assets | [7 empty] | Date Started:
Samal | Mambago-A | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VariousWater System Development Project Construction in Progress- Infrastructure Assets | Improvement of Potable Water System at Brgy. Mambago- A, Samal District, IGACOS |  | SB # 3 CY 2019 | Water System |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | (Amended in the AIP 2nd Revision to change the location from Peñaplata to Samal District) PO approved September 2, 2019
Samal | Mambago-A | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VariousWater System Development Project Construction in Progress- Infrastructure Assets | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Samal | Mambago-A | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VariousWater System Development Project Construction in Progress- Infrastructure Assets | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Samal | Mambago-A | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VariousWater System Development Project Construction in Progress- Infrastructure Assets | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Samal | Mambago-A | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VariousWater System Development Project Construction in Progress- Infrastructure Assets | [7 empty] | Date Allotment Released: |  | Date completed:
Samal | Mambago-A | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VariousWater System Development Project Construction in Progress- Infrastructure Assets | [7 empty] | Date Started:
Samal | San Miguel | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VariousWater System Development Project Construction in Progress- Infrastructure Assets | Rehabilitation of Potable Water System at Brgy. San Miguel, Samal District, IGACOS |  | SB # 3 CY 2019 | Water System |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | For implementation
Samal | San Miguel | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VariousWater System Development Project Construction in Progress- Infrastructure Assets | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Samal | San Miguel | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VariousWater System Development Project Construction in Progress- Infrastructure Assets | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Samal | San Miguel | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VariousWater System Development Project Construction in Progress- Infrastructure Assets | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Samal | San Miguel | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VariousWater System Development Project Construction in Progress- Infrastructure Assets | [7 empty] | Date Allotment Released: |  | Date completed:
Samal | San Miguel | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VariousWater System Development Project Construction in Progress- Infrastructure Assets | [7 empty] | Date Started:
Kaputian, IGCS | Linusotan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VariousWater System Development Project Construction in Progress- Infrastructure Assets | Construction of Potable Water System at Brgy.Linusotan, Kaputian District, IGACOS |  | SB # 3 CY 2019 | Water System |  |  |  | Project Cost: | 1300000 | Target Completion Date: |  | Program: | 1300000 | Planned: |  | No. of Persons: |  | (Additional 800,000.00 from Const. of PWS in purok 2, Pag-asa, Kapalong which was funded by OPAPP CY 2018) (amended) For allotment- October 15, 2019
Kaputian, IGCS | Linusotan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VariousWater System Development Project Construction in Progress- Infrastructure Assets | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 1300000 | Revised: |  | No. of Man-days:
Kaputian, IGCS | Linusotan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VariousWater System Development Project Construction in Progress- Infrastructure Assets | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Kaputian, IGCS | Linusotan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VariousWater System Development Project Construction in Progress- Infrastructure Assets | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Kaputian, IGCS | Linusotan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VariousWater System Development Project Construction in Progress- Infrastructure Assets | [7 empty] | Date Allotment Released: |  | Date completed:
Kaputian, IGCS | Linusotan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VariousWater System Development Project Construction in Progress- Infrastructure Assets | [7 empty] | Date Started:
Carmen | Ising | 2nd Eng'g. Dist. | Completed | 2019-07-29 | 2019-11-11 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DISASTER REHABILITATION & RECOVERY PROGRAM Building Back Better Project | Disiltation of Mactan River (Ph. II) |  | 5% Calamity Fund CY 2019 | Desiltation |  | ln.m |  | Project Cost: | 500000 | Target Completion Date: | 2019-09-27 | Program: | 500000 | Planned: | 100% | No. of Persons: |  | Completed as per physical accomplishment. Financial documents still on process.
Carmen | Ising | 2nd Eng'g. Dist. | Completed | 2019-07-29 | 2019-11-11 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DISASTER REHABILITATION & RECOVERY PROGRAM Building Back Better Project | [7 empty] | Project Engineer: | Toquero | Revised Completion Date: | 2019-11-11 | Allotment: | 500000 | Revised: |  | No. of Man-days:
Carmen | Ising | 2nd Eng'g. Dist. | Completed | 2019-07-29 | 2019-11-11 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DISASTER REHABILITATION & RECOVERY PROGRAM Building Back Better Project | [7 empty] | Implementor: | PEO | No. of days suspended: | 45 | Disbursement: |  | Actual: | 100%
Carmen | Ising | 2nd Eng'g. Dist. | Completed | 2019-07-29 | 2019-11-11 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DISASTER REHABILITATION & RECOVERY PROGRAM Building Back Better Project | [7 empty] | Duration: | 60 | No. of days extended: |  |  |  | Slippage: | 0%
Carmen | Ising | 2nd Eng'g. Dist. | Completed | 2019-07-29 | 2019-11-11 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DISASTER REHABILITATION & RECOVERY PROGRAM Building Back Better Project | [7 empty] | Date Allotment Released: | 2019-05-28 | Date completed: | 2019-11-11
Carmen | Ising | 2nd Eng'g. Dist. | Completed | 2019-07-29 | 2019-11-11 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DISASTER REHABILITATION & RECOVERY PROGRAM Building Back Better Project | [7 empty] | Date Started: | 2019-07-29
B.E. Dujali | Magupising | 2nd Eng'g. Dist. | Completed | 2019-12-02 | 2020-06-15 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DISASTER REHABILITATION & RECOVERY PROGRAM Building Back Better Project | Rehabilitation of Dujali-Balisong-Magupising Provincial Road |  | 5% Calamity Fund CY 2019 | Rehabilitation |  | km | Admin | Project Cost: | 1280000 | Target Completion Date: | 2020-02-03 | Program: | 1280000 | Planned: | 100% | No. of Persons: |  | Completed as per physical accomplishment. Financial documents still on process.
B.E. Dujali | Magupising | 2nd Eng'g. Dist. | Completed | 2019-12-02 | 2020-06-15 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DISASTER REHABILITATION & RECOVERY PROGRAM Building Back Better Project | [7 empty] | Project Engineer: | Mellomida | Revised Completion Date: | 2020-06-15 | Allotment: | 1280000 | Revised: | 100% | No. of Man-days:
B.E. Dujali | Magupising | 2nd Eng'g. Dist. | Completed | 2019-12-02 | 2020-06-15 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DISASTER REHABILITATION & RECOVERY PROGRAM Building Back Better Project | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: |  | Actual: | 100%
B.E. Dujali | Magupising | 2nd Eng'g. Dist. | Completed | 2019-12-02 | 2020-06-15 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DISASTER REHABILITATION & RECOVERY PROGRAM Building Back Better Project | [7 empty] | Duration: | 63 | No. of days extended: | 106 |  |  | Slippage: | 0%
B.E. Dujali | Magupising | 2nd Eng'g. Dist. | Completed | 2019-12-02 | 2020-06-15 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DISASTER REHABILITATION & RECOVERY PROGRAM Building Back Better Project | [7 empty] | Date Allotment Released: |  | Date completed: | 2020-06-15
B.E. Dujali | Magupising | 2nd Eng'g. Dist. | Completed | 2019-12-02 | 2020-06-15 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DISASTER REHABILITATION & RECOVERY PROGRAM Building Back Better Project | [7 empty] | Date Started: | 2019-12-02
Sto. Tomas | Magwawa | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PEACE AND ORDER PROGRAM/1914 Construction in Progress- Land Improvements | Rehabilitation of San Jose- Sitio Mahayahay-Magwawa Provincial Road, Sto. Tomas |  | SB # 4 CY 2019 | Road |  |  |  | Project Cost: | 1000000 | Target Completion Date: |  | Program: | 1000000 | Planned: |  | No. of Persons: |  | POW preparation on-going c/o South District
Sto. Tomas | Magwawa | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PEACE AND ORDER PROGRAM/1914 Construction in Progress- Land Improvements | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 1000000 | Revised: |  | No. of Man-days:
Sto. Tomas | Magwawa | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PEACE AND ORDER PROGRAM/1914 Construction in Progress- Land Improvements | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Sto. Tomas | Magwawa | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PEACE AND ORDER PROGRAM/1914 Construction in Progress- Land Improvements | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Sto. Tomas | Magwawa | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PEACE AND ORDER PROGRAM/1914 Construction in Progress- Land Improvements | [7 empty] | Date Allotment Released: |  | Date completed:
Sto. Tomas | Magwawa | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PEACE AND ORDER PROGRAM/1914 Construction in Progress- Land Improvements | [7 empty] | Date Started:
Panabo City | Dalisay | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Local Roads and Drainage Development Project Construction in Progress- Infrastructure Assets | Rehabilitation of Local Roads at Dalisay-Manay Road Section, Panabo City |  | SB # 4 CY 2019 | Road |  |  | Admin | Project Cost: | 246100 | Target Completion Date: |  | Program: | 246100 | Planned: |  | No. of Persons: |  | For implementation
Panabo City | Dalisay | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Local Roads and Drainage Development Project Construction in Progress- Infrastructure Assets | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 246100 | Revised: |  | No. of Man-days:
Panabo City | Dalisay | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Local Roads and Drainage Development Project Construction in Progress- Infrastructure Assets | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Panabo City | Dalisay | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Local Roads and Drainage Development Project Construction in Progress- Infrastructure Assets | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Panabo City | Dalisay | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Local Roads and Drainage Development Project Construction in Progress- Infrastructure Assets | [7 empty] | Date Allotment Released: |  | Date completed:
Panabo City | Dalisay | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Local Roads and Drainage Development Project Construction in Progress- Infrastructure Assets | [7 empty] | Date Started:
Panabo City | Buenavista | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Local Roads and Drainage Development Project Construction in Progress- Infrastructure Assets | Rehabilitation of Local Roads at Sta. Cruz-Jct. Tagpore-Buenavista Raod Section, Panabo City |  | SB # 4 CY 2019 | Road |  |  | Admin | Project Cost: | 431000 | Target Completion Date: |  | Program: | 431000 | Planned: |  | No. of Persons: |  | For implementation
Panabo City | Buenavista | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Local Roads and Drainage Development Project Construction in Progress- Infrastructure Assets | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 431000 | Revised: |  | No. of Man-days:
Panabo City | Buenavista | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Local Roads and Drainage Development Project Construction in Progress- Infrastructure Assets | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Panabo City | Buenavista | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Local Roads and Drainage Development Project Construction in Progress- Infrastructure Assets | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Panabo City | Buenavista | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Local Roads and Drainage Development Project Construction in Progress- Infrastructure Assets | [7 empty] | Date Allotment Released: |  | Date completed:
Panabo City | Buenavista | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Local Roads and Drainage Development Project Construction in Progress- Infrastructure Assets | [7 empty] | Date Started:
Carmen | Taba | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Local Roads and Drainage Development Project Construction in Progress- Infrastructure Assets | Rehabilitation of Local Roads at Taba-Bucana Road Section, Taba, Carmen |  | SB # 4 CY 2019 | Road |  |  | Admin | Project Cost: | 220000 | Target Completion Date: |  | Program: | 220000 | Planned: |  | No. of Persons: |  | For implementation
Carmen | Taba | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Local Roads and Drainage Development Project Construction in Progress- Infrastructure Assets | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 220000 | Revised: |  | No. of Man-days:
Carmen | Taba | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Local Roads and Drainage Development Project Construction in Progress- Infrastructure Assets | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Carmen | Taba | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Local Roads and Drainage Development Project Construction in Progress- Infrastructure Assets | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Carmen | Taba | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Local Roads and Drainage Development Project Construction in Progress- Infrastructure Assets | [7 empty] | Date Allotment Released: |  | Date completed:
Carmen | Taba | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Local Roads and Drainage Development Project Construction in Progress- Infrastructure Assets | [7 empty] | Date Started:
B.E. Dujali | Dujali | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | Concreting of Brgy. Road Canal, Dujali, B.E. Dujali |  | SB # 4 CY 2019 (STIMULUS | Concreting |  |  | Contract | Project Cost: | 650000 | Target Completion Date: |  | Program: | 650000 | Planned: |  | No. of Persons: |  | For implementation
B.E. Dujali | Dujali | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 650000 | Revised: |  | No. of Man-days:
B.E. Dujali | Dujali | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
B.E. Dujali | Dujali | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
B.E. Dujali | Dujali | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Date Allotment Released: |  | Date completed:
B.E. Dujali | Dujali | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Date Started:
B.E. Dujali | New Casay | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | Desilting and Conretign of Drainage-Main Collector Canal, New Casay, B.E. Dujali |  | SB # 4 CY 2019 (STIMULUS | Desiltation |  |  | Contract | Project Cost: | 650000 | Target Completion Date: |  | Program: | 650000 | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
B.E. Dujali | New Casay | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 650000 | Revised: |  | No. of Man-days:
B.E. Dujali | New Casay | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
B.E. Dujali | New Casay | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
B.E. Dujali | New Casay | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Date Allotment Released: |  | Date completed:
B.E. Dujali | New Casay | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Date Started:
B.E. Dujali | Tanglaw | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | Concreting of Drainage, Tanglaw, B.E., Dujali |  | SB # 4 CY 2019 (STIMULUS | Desiltation |  |  | Contract | Project Cost: | 1200000 | Target Completion Date: |  | Program: | 1200000 | Planned: |  | No. of Persons: |  | For implementation
B.E. Dujali | Tanglaw | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 1200000 | Revised: |  | No. of Man-days:
B.E. Dujali | Tanglaw | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
B.E. Dujali | Tanglaw | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
B.E. Dujali | Tanglaw | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Date Allotment Released: |  | Date completed:
B.E. Dujali | Tanglaw | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Date Started:
Panabo City | New Malitbog | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | Construction of Potable Water System, New Malitbog, Panabo City |  | SB # 4 CY 2019 (STIMULUS | Water System |  |  | Contract | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
Panabo City | New Malitbog | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Panabo City | New Malitbog | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Panabo City | New Malitbog | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Panabo City | New Malitbog | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Date Allotment Released: |  | Date completed:
Panabo City | New Malitbog | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Date Started:
Kaputian, IGCS | Poblacion | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | Construction of Water System Project, Poblacion Kaputian, Samal |  | SB # 4 CY 2019 (STIMULUS | Water System |  |  | Contract | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | For implementation
Kaputian, IGCS | Poblacion | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Kaputian, IGCS | Poblacion | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Kaputian, IGCS | Poblacion | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Kaputian, IGCS | Poblacion | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Date Allotment Released: |  | Date completed:
Kaputian, IGCS | Poblacion | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Date Started:
Panabo City | salvacion | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | Construction of Canal Lining at Prk. 5, Salvacion, Panabo City |  | SB # 4 CY 2019 (STIMULUS | Canal lining |  |  | Contract | Project Cost: | 600000 | Target Completion Date: |  | Program: | 600000 | Planned: |  | No. of Persons: |  | For implementation
Panabo City | salvacion | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 600000 | Revised: |  | No. of Man-days:
Panabo City | salvacion | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Panabo City | salvacion | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Panabo City | salvacion | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Date Allotment Released: |  | Date completed:
Panabo City | salvacion | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Date Started:
Sto. Tomas | Lunga-og | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | Rehabilitation of Brgy. Road at Lunga-og. Sto. Tomas |  | SB # 4 CY 2019 (STIMULUS | Road |  |  | Contract | Project Cost: | 600000 | Target Completion Date: |  | Program: | 600000 | Planned: |  | No. of Persons: |  | For implementation
Sto. Tomas | Lunga-og | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 600000 | Revised: |  | No. of Man-days:
Sto. Tomas | Lunga-og | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Sto. Tomas | Lunga-og | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Sto. Tomas | Lunga-og | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Date Allotment Released: |  | Date completed:
Sto. Tomas | Lunga-og | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Date Started:
Carmen | Sto. Niño | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | Construction of Evacuation Center at Purok 1-C Brgy. Sto. Niño, Carmen |  | SB # 4 CY 2019 (STIMULUS | Building |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | For implementation
Carmen | Sto. Niño | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Carmen | Sto. Niño | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Carmen | Sto. Niño | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Carmen | Sto. Niño | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Date Allotment Released: |  | Date completed:
Carmen | Sto. Niño | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Date Started:
Panabo City | Waterfall | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | Construction of Multi-Purpose Hall, Waterfall, Panabo City |  | SB # 4 CY 2019 (STIMULUS | Building |  |  |  | Project Cost: | 1050000 | Target Completion Date: |  | Program: | 1050000 | Planned: |  | No. of Persons: |  | For implementation
Panabo City | Waterfall | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 1050000 | Revised: |  | No. of Man-days:
Panabo City | Waterfall | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Panabo City | Waterfall | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Panabo City | Waterfall | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Date Allotment Released: |  | Date completed:
Panabo City | Waterfall | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Date Started:
Panabo City | San Francisco | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | Rehabilitation of Multi-Purpose Hall, San Francisco, Panabo City |  | SB # 4 CY 2019 (STIMULUS | Building |  |  |  | Project Cost: | 600000 | Target Completion Date: |  | Program: | 600000 | Planned: |  | No. of Persons: |  | For implementation
Panabo City | San Francisco | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 600000 | Revised: |  | No. of Man-days:
Panabo City | San Francisco | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Panabo City | San Francisco | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Panabo City | San Francisco | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Date Allotment Released: |  | Date completed:
Panabo City | San Francisco | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Date Started:
Panabo City | Datu Abdul | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | Rehabilitation of Evacuation Center at Datu Abdul Dadia, Panabo City |  | SB # 4 CY 2019 (STIMULUS | Building |  |  |  | Project Cost: | 650000 | Target Completion Date: |  | Program: | 650000 | Planned: |  | No. of Persons: |  | For implementation
Panabo City | Datu Abdul | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 650000 | Revised: |  | No. of Man-days:
Panabo City | Datu Abdul | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Panabo City | Datu Abdul | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Panabo City | Datu Abdul | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Date Allotment Released: |  | Date completed:
Panabo City | Datu Abdul | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Date Started:
Panabo City | Buenavista | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | Construction of Multi-Purpose Hall, Buenavista, Panabo City |  | SB # 4 CY 2019 (STIMULUS | Building |  |  |  | Project Cost: | 1050000 | Target Completion Date: |  | Program: | 1050000 | Planned: |  | No. of Persons: |  | For implementation
Panabo City | Buenavista | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 1050000 | Revised: |  | No. of Man-days:
Panabo City | Buenavista | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Panabo City | Buenavista | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Panabo City | Buenavista | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Date Allotment Released: |  | Date completed:
Panabo City | Buenavista | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Date Started:
Panabo City | Little Panay | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | Rehabilitation of Multi-Purpose Hall, Llittle Panay, Panabo City |  | SB # 4 CY 2019 (STIMULUS | Building |  |  |  | Project Cost: | 550000 | Target Completion Date: |  | Program: | 550000 | Planned: |  | No. of Persons: |  | For implementation
Panabo City | Little Panay | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 550000 | Revised: |  | No. of Man-days:
Panabo City | Little Panay | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Panabo City | Little Panay | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Panabo City | Little Panay | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Date Allotment Released: |  | Date completed:
Panabo City | Little Panay | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Date Started:
Sto. Tomas | Pantaron | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | Rehabilitation of Multi-Purpose Hall, Pantaron, Sto. Tomas |  | SB # 4 CY 2019 (STIMULUS | Building |  |  |  | Project Cost: | 550000 | Target Completion Date: |  | Program: | 550000 | Planned: |  | No. of Persons: |  | For implementation
Sto. Tomas | Pantaron | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 550000 | Revised: |  | No. of Man-days:
Sto. Tomas | Pantaron | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Sto. Tomas | Pantaron | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Sto. Tomas | Pantaron | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Date Allotment Released: |  | Date completed:
Sto. Tomas | Pantaron | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Date Started:
Sto. Tomas | salvacion | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | Rehabilitation of Multi-Purpose Hall, Salvacion, Sto. Tomas |  | SB # 4 CY 2019 (STIMULUS | Building |  |  |  | Project Cost: | 1000000 | Target Completion Date: |  | Program: | 1000000 | Planned: |  | No. of Persons: |  | PR #20032281
Sto. Tomas | salvacion | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 1000000 | Revised: |  | No. of Man-days:
Sto. Tomas | salvacion | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Sto. Tomas | salvacion | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Sto. Tomas | salvacion | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Date Allotment Released: |  | Date completed:
Sto. Tomas | salvacion | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Date Started:
Sto. Tomas | San Jose | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | Completion of Multi-Purpose Hall, San Jose, Sto. Tomas |  | SB # 4 CY 2019 (STIMULUS | Building |  |  |  | Project Cost: | 600000 | Target Completion Date: |  | Program: | 600000 | Planned: |  | No. of Persons: |  | For implementation
Sto. Tomas | San Jose | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 600000 | Revised: |  | No. of Man-days:
Sto. Tomas | San Jose | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Sto. Tomas | San Jose | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Sto. Tomas | San Jose | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Date Allotment Released: |  | Date completed:
Sto. Tomas | San Jose | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Date Started:
Panabo City | Kasilak | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | Rehabilitation of Multi-Purpose Hall, Kasilak, Panabo City |  | SB # 4 CY 2019 (STIMULUS | Building |  |  |  | Project Cost: | 650000 | Target Completion Date: |  | Program: | 650000 | Planned: |  | No. of Persons: |  | For implementation
Panabo City | Kasilak | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 650000 | Revised: |  | No. of Man-days:
Panabo City | Kasilak | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Panabo City | Kasilak | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Panabo City | Kasilak | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Date Allotment Released: |  | Date completed:
Panabo City | Kasilak | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Date Started:
Panabo City | Dalisay | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | Rehabilitation of Brgy. Health Center, Dalisay, Panabo City |  | SB # 4 CY 2019 (STIMULUS | Building |  |  |  | Project Cost: | 550000 | Target Completion Date: |  | Program: | 550000 | Planned: |  | No. of Persons: |  | For implementation
Panabo City | Dalisay | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 550000 | Revised: |  | No. of Man-days:
Panabo City | Dalisay | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Panabo City | Dalisay | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Panabo City | Dalisay | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Date Allotment Released: |  | Date completed:
Panabo City | Dalisay | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Date Started:
Panabo City | Kiotoy | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | Rehabilitation of Evacuation Center, Kiotoy, Panabo City |  | SB # 4 CY 2019 (STIMULUS | Building |  |  |  | Project Cost: | 650000 | Target Completion Date: |  | Program: | 650000 | Planned: |  | No. of Persons: |  | For implementation
Panabo City | Kiotoy | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 650000 | Revised: |  | No. of Man-days:
Panabo City | Kiotoy | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Panabo City | Kiotoy | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Panabo City | Kiotoy | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Date Allotment Released: |  | Date completed:
Panabo City | Kiotoy | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Date Started:
Panabo City | Cagangohan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | Rehabilitation of Evacuation Center, Cagangohan, Panabo City |  | SB # 4 CY 2019 (STIMULUS | Building |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Abstract #0520201798 - Digos constrak
Panabo City | Cagangohan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Panabo City | Cagangohan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Panabo City | Cagangohan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Panabo City | Cagangohan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Date Allotment Released: |  | Date completed:
Panabo City | Cagangohan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Date Started:
IGCS | Tagpopongan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | Rehabilitation of Multi-Purpose Bldg. (Brgy. Hall) Tagpopongan, IGACOS |  | SB # 4 CY 2019 (STIMULUS | Building |  |  |  | Project Cost: | 174460.33 | Target Completion Date: |  | Program: | 174460.33 | Planned: |  | No. of Persons: |  | Procurement on process
IGCS | Tagpopongan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 174460.33 | Revised: |  | No. of Man-days:
IGCS | Tagpopongan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
IGCS | Tagpopongan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
IGCS | Tagpopongan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Date Allotment Released: |  | Date completed:
IGCS | Tagpopongan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Date Started:
Sto. Tomas | Balagunan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | Construction of Multi-Purpose Building, Balagunan, Sto. Tomas |  | SB # 4 CY 2019 (STIMULUS | Building |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | For implementation
Sto. Tomas | Balagunan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Sto. Tomas | Balagunan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Sto. Tomas | Balagunan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Sto. Tomas | Balagunan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Date Allotment Released: |  | Date completed:
Sto. Tomas | Balagunan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Date Started:
Carmen | La Paz | 2nd Eng'g. Dist. | On-going |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CMGP | Road Upgrading of Sto Nino - Kabankalan - La Paz Provincial Road, Carmen |  | CMGP CY 2019 | Road |  | km | Contract | Project Cost: | 44461624.67 | Target Completion Date: | 2020-05-15 23:59 | Program: | 44461624.67 | Planned: | 76.36% | No. of Persons: | 42 | On-going
Carmen | La Paz | 2nd Eng'g. Dist. | On-going |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CMGP | [7 empty] | Project Engineer: | Comidoy | Revised Completion Date: | 2020-07-20 23:59 | Allotment: | 44461624.67 | Revised: |  | No. of Man-days: | 610
Carmen | La Paz | 2nd Eng'g. Dist. | On-going |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CMGP | [7 empty] | Implementor: | GP & H CONST. | No. of days suspended: | 66 | Disbursement: | 6684253.05 | Actual: | 95.75%
Carmen | La Paz | 2nd Eng'g. Dist. | On-going |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CMGP | [7 empty] | Duration: | 222 | No. of days extended: |  |  |  | Slippage: | 19.39%
Carmen | La Paz | 2nd Eng'g. Dist. | On-going |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CMGP | [7 empty] | Date Allotment Released: | CY 2019 | Date completed:
Carmen | La Paz | 2nd Eng'g. Dist. | On-going |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CMGP | [7 empty] | Date Started: | 2019-10-07
Carmen | La Paz | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CMGP | Road Upgrading of Jct Highway - Sto Nino - La Paz - San Vicenter Provincial Road, Carmen |  | CMGP CY 2019 | Road |  | km | Contract | Project Cost: | 80481331.34 | Target Completion Date: | 2020-06-22 | Program: | 80481331.34 | Planned: | 94.91% | No. of Persons: | 40 | On-going
Carmen | La Paz | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CMGP | [7 empty] | Project Engineer: | Fernandez | Revised Completion Date: | 2020-08-04 | Allotment: | 80481331.34 | Revised: |  | No. of Man-days: | 660
Carmen | La Paz | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CMGP | [7 empty] | Implementor: | Tagum Builders | No. of days suspended: | 43 | Disbursement: | 45481609.97 | Actual: | 94.79%
Carmen | La Paz | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CMGP | [7 empty] | Duration: | 259 | No. of days extended: |  |  |  | Slippage: | -0.12%
Carmen | La Paz | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CMGP | [7 empty] | Date Allotment Released: | CY 2019 | Date completed:
Carmen | La Paz | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CMGP | [7 empty] | Date Started: | 2019-10-07
Carmen | Mangalcal | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | 0 | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 073 - Cebulano - Mangalcal |  | GENERAL FUND CY 2020 | Maintenance | 4.17 | km | MBA | Project Cost: | 134672.7 | Target Completion Date: | 2020-12-31 23:59 | Program: | 134672.7 | Planned: | 50% | No. of Persons: | 64 | On-going
Carmen | Mangalcal | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Gamad/Clar | Revised Completion Date: |  | Allotment: | 134672.7 | Revised: |  | No. of Man-days: | 1280
Carmen | Mangalcal | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: | 51%
Carmen | Mangalcal | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 1%
Carmen | Mangalcal | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
Carmen | Mangalcal | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started: | 2020-01-02
Carmen | Mangalcal | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 073 - Cebulano - Mangalcal |  | GENERAL FUND CY 2020 | Maintenance | 4.17 | km | CBRMC | Project Cost: | 131004.66 | Target Completion Date: | 2020-11-11 | Program: | 131004.66 | Planned: | 5% | No. of Persons: |  | On-going
Carmen | Mangalcal | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Maligro | Revised Completion Date: |  | Allotment: | 131004.66 | Revised: |  | No. of Man-days:
Carmen | Mangalcal | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: | Brgy. Mangalcal Women's Household | No. of days suspended: |  | Disbursement: |  | Actual: | 5%
Carmen | Mangalcal | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: | 180 | No. of days extended: |  |  |  | Slippage: | 0%
Carmen | Mangalcal | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
Carmen | Mangalcal | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started: | 2020-05-15
Carmen | Tubod | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 074 - Tubod - basa - Mangalcal |  | GENERAL FUND CY 2020 | Maintenance | 3.93 | km | MBA | Project Cost: | 143530.25 | Target Completion Date: | 2020-12-31 23:59 | Program: | 143530.25 | Planned: | 50% | No. of Persons: | 3 | On-going
Carmen | Tubod | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Gamad/Clar | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 143530.25 | Revised: |  | No. of Man-days: | 66
Carmen | Tubod | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: |  | Actual: | 52%
Carmen | Tubod | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 2%
Carmen | Tubod | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
Carmen | Tubod | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started: | 2020-01-02
Carmen | Tubod | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 074 - Tubod - basa - Mangalcal |  | GENERAL FUND CY 2020 | Maintenance | 3.93 | km | CBRMC | Project Cost: | 106856.33 | Target Completion Date: | 2020-11-25 23:59 | Program: | 106856.33 | Planned: | 5% | No. of Persons: | 2 | On-going
Carmen | Tubod | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Maligro | Revised Completion Date: |  | Allotment: | 106856.33 | Revised: |  | No. of Man-days: | 2
Carmen | Tubod | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: | Tubod Centro Lower Irrigator's Association | No. of days suspended: |  | Disbursement: |  | Actual: | 5%
Carmen | Tubod | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: | 185 | No. of days extended: |  |  |  | Slippage: | 0%
Carmen | Tubod | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
Carmen | Tubod | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started: | 2020-05-25
Carmen | Tubod | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 078 - Upper Mangalcal - Lower Mangalcal |  | GENERAL FUND CY 2020 | Maintenance | 2.43 | km | MBA | Project Cost: | 82374.21 | Target Completion Date: | 2020-12-31 23:59 | Program: | 82374.21 | Planned: | 50% | No. of Persons: | 3 | On-going
Carmen | Tubod | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Gamad/Clar | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 82374.21 | Revised: |  | No. of Man-days: | 66
Carmen | Tubod | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: |  | Actual: | 55%
Carmen | Tubod | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 5%
Carmen | Tubod | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
Carmen | Tubod | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started: | 2020-01-02
Carmen | Mangalcal | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 078 - Upper Mangalcal - Lower Mangalcal |  | GENERAL FUND CY 2020 | Maintenance | 2.43 | km | CBRMC | Project Cost: | 72444.97 | Target Completion Date: | 2020-11-15 23:59 | Program: | 72444.97 | Planned: | 5% | No. of Persons: | 2 | On-going
Carmen | Mangalcal | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Maligro | Revised Completion Date: |  | Allotment: | 72444.97 | Revised: |  | No. of Man-days: | 2
Carmen | Mangalcal | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: | Brgy. Mangalcal Women's Homebased Association | No. of days suspended: |  | Disbursement: |  | Actual: | 5%
Carmen | Mangalcal | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: | 185 | No. of days extended: |  |  |  | Slippage: | 0%
Carmen | Mangalcal | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
Carmen | Mangalcal | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started: | 2020-05-15
Carmen | Cebulano | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 079 - Cebulano - Loceta |  | GENERAL FUND CY 2020 | Maintenance |  | km | MBA | Project Cost: | 72051.43 | Target Completion Date: | 2020-12-31 23:59 | Program: | 72051.43 | Planned: | 30% | No. of Persons: | 3 | On-going
Carmen | Cebulano | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Gamad/Clar | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 72051.43 | Revised: |  | No. of Man-days: | 66
Carmen | Cebulano | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: |  | Actual: | 54%
Carmen | Cebulano | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 24%
Carmen | Cebulano | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
Carmen | Cebulano | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started: | 2020-01-02
Carmen | Cebulano | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 079 - Cebulano - Loceta |  | GENERAL FUND CY 2020 | Maintenance |  | km | CBRMC | Project Cost: | 47089.26 | Target Completion Date: | 2020-11-15 23:59 | Program: | 47089.26 | Planned: | 5% | No. of Persons: | 2 | On-going
Carmen | Cebulano | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Maligro | Revised Completion Date: |  | Allotment: | 47089.26 | Revised: |  | No. of Man-days: | 2
Carmen | Cebulano | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: | Brgy. Mangalcal Women's Homebased Association | No. of days suspended: |  | Disbursement: |  | Actual: | 5%
Carmen | Cebulano | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: | 185 | No. of days extended: |  |  |  | Slippage: | 0%
Carmen | Cebulano | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
Carmen | Cebulano | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started: | 2020-05-15
Carmen | Tubod | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 082 - Jct. Highway Carmen - Mangalcal - Tubod |  | GENERAL FUND CY 2020 | Maintenance | 11.34 | km | MBA | Project Cost: | 462895.06 | Target Completion Date: | 2020-12-31 23:59 | Program: | 462895.06 | Planned: | 50% | No. of Persons: | 4 | On-going
Carmen | Tubod | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Gamad/Clar | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 462895.06 | Revised: |  | No. of Man-days: | 88
Carmen | Tubod | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: |  | Actual: | 50%
Carmen | Tubod | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0%
Carmen | Tubod | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
Carmen | Tubod | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started: | 2020-01-02
Carmen | Tubod | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 082 - Jct. Highway Carmen - Mangalcal - Tubod |  | GENERAL FUND CY 2020 | Maintenance | 11.34 | km | CBRMC | Project Cost: | 259594.46 | Target Completion Date: |  | Program: | 259594.46 | Planned: |  | No. of Persons: |  | PO #2020031403 - Awarded to TUBOD CENTRO LOWER IRRIGATORS ASS'T (TUCLIA)
Carmen | Tubod | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Maligro | Revised Completion Date: |  | Allotment: | 259594.46 | Revised: |  | No. of Man-days:
Carmen | Tubod | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Carmen | Tubod | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Carmen | Tubod | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: |  | Date completed:
Carmen | Tubod | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started:
Carmen | Taba | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 086 - Ising - Sadpodon - Taba - Dila -Dila |  | GENERAL FUND CY 2020 | Maintenance | 5.68 | km | MBA | Project Cost: | 226651.27 | Target Completion Date: | 2020-12-31 23:59 | Program: | 226651.27 | Planned: | 50% | No. of Persons: | 3 | On-going
Carmen | Taba | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Gamad/Clar | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 226651.27 | Revised: |  | No. of Man-days: | 66
Carmen | Taba | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: |  | Actual: | 50%
Carmen | Taba | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0%
Carmen | Taba | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
Carmen | Taba | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started: | 2020-01-02
Carmen | Taba | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 086 - Ising - Sadpodon - Taba - Dila -Dila |  | GENERAL FUND CY 2020 | Maintenance | 5.68 | km | CBRMC | Project Cost: | 135230.61 | Target Completion Date: |  | Program: | 135230.61 | Planned: | 50% | No. of Persons: |  | PO #2020031408 - Awarded to TABA COCONUT FARMERS ORGANIZATION
Carmen | Taba | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Maligro | Revised Completion Date: |  | Allotment: | 135230.61 | Revised: |  | No. of Man-days:
Carmen | Taba | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: | 55%
Carmen | Taba | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 5%
Carmen | Taba | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: |  | Date completed:
Carmen | Taba | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started:
Carmen | Tuganay | 2nd Eng'g. Dist. | For Implementation | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 087 - Tuganay - taba |  | GENERAL FUND CY 2020 | Maintenance | 4.27 | km | MBA | Project Cost: | 169418.15 | Target Completion Date: | 2020-12-31 23:59 | Program: | 169418.15 | Planned: | 52% | No. of Persons: | 3 | On-going
Carmen | Tuganay | 2nd Eng'g. Dist. | For Implementation | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Gamad/Clar | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 169418.15 | Revised: |  | No. of Man-days: | 66
Carmen | Tuganay | 2nd Eng'g. Dist. | For Implementation | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: |  | Actual: | 52%
Carmen | Tuganay | 2nd Eng'g. Dist. | For Implementation | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0%
Carmen | Tuganay | 2nd Eng'g. Dist. | For Implementation | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
Carmen | Tuganay | 2nd Eng'g. Dist. | For Implementation | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started: | 2020-01-02
Carmen | Tuganay | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 087 - Tuganay - taba |  | GENERAL FUND CY 2020 | Maintenance | 4.27 | km | CBRMC | Project Cost: | 102630.37 | Target Completion Date: |  | Program: | 102630.37 | Planned: |  | No. of Persons: |  | PO #2020031406 - TABA COCONUT FARMERS ORGANIZATION
Carmen | Tuganay | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Maligro | Revised Completion Date: |  | Allotment: | 102630.37 | Revised: |  | No. of Man-days:
Carmen | Tuganay | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Carmen | Tuganay | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Carmen | Tuganay | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: |  | Date completed:
Carmen | Tuganay | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started:
Carmen | Tuganay | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 088 - Jct. Highway Tuganay - Taba |  | GENERAL FUND CY 2020 | Maintenance | 4.4 | km | MBA | Project Cost: | 222375.04 | Target Completion Date: | 2020-12-31 23:59 | Program: | 222375.04 | Planned: | 50% | No. of Persons: | 3 | On-going
Carmen | Tuganay | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Gamad/Clar | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 222375.04 | Revised: |  | No. of Man-days: | 66
Carmen | Tuganay | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: |  | Actual: | 51%
Carmen | Tuganay | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 1%
Carmen | Tuganay | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
Carmen | Tuganay | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started: | 2020-01-02
Carmen | Tuganay | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 088 - Jct. Highway Tuganay - Taba |  | GENERAL FUND CY 2020 | Maintenance | 4.4 | km | CBRMC | Project Cost: | 57955.99 | Target Completion Date: | 2020-11-13 23:59 | Program: | 57955.99 | Planned: | 5% | No. of Persons: | 2 | On-going
Carmen | Tuganay | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Maligro | Revised Completion Date: |  | Allotment: | 57955.99 | Revised: |  | No. of Man-days: | 2
Carmen | Tuganay | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: | Ezra Christian Minsitry For Peace, Inc. | No. of days suspended: |  | Disbursement: |  | Actual: | 5%
Carmen | Tuganay | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: | 185 | No. of days extended: |  |  |  | Slippage: | 0%
Carmen | Tuganay | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
Carmen | Tuganay | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started: | 2020-05-13
Carmen | Ising | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 089 - Jct. Highway Ising - Magsaysay |  | GENERAL FUND CY 2020 | Maintenance | 10.84 | km | MBA | Project Cost: | 478128.48 | Target Completion Date: | 2020-12-31 23:59 | Program: | 478128.48 | Planned: | 50% | No. of Persons: | 3 | On-going
Carmen | Ising | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Gamad/Clar | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 478128.48 | Revised: |  | No. of Man-days: | 66
Carmen | Ising | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: |  | Actual: | 50%
Carmen | Ising | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0%
Carmen | Ising | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
Carmen | Ising | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started: | 2020-01-02
Carmen | Ising | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 089 - Jct. Highway Ising - Magsaysay |  | GENERAL FUND CY 2020 | Maintenance | 10.84 | km | CBRMC | Project Cost: | 212505.24 | Target Completion Date: | 2020-11-14 23:59 | Program: | 212505.24 | Planned: | 5% | No. of Persons: | 2 | On-going
Carmen | Ising | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Maligro | Revised Completion Date: |  | Allotment: | 212505.24 | Revised: |  | No. of Man-days: | 42
Carmen | Ising | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: | School in the Air Integrated Farmer's Associiation | No. of days suspended: |  | Disbursement: |  | Actual: | 5%
Carmen | Ising | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: | 185 | No. of days extended: |  |  |  | Slippage: | 0%
Carmen | Ising | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
Carmen | Ising | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started: | 2020-05-14
C armen | New Camiling | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 090 - Maligaya - New Camiling |  | GENERAL FUND CY 2020 | Maintenance |  | km | MBA | Project Cost: | 51790.26 | Target Completion Date: | 2020-12-31 23:59 | Program: | 51790.26 | Planned: | 50% | No. of Persons: | 3 | On-going
C armen | New Camiling | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Gamad/Clar | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 51790.26 | Revised: |  | No. of Man-days: | 66
C armen | New Camiling | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: |  | Actual: | 51%
C armen | New Camiling | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 1%
C armen | New Camiling | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
C armen | New Camiling | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started: | 2020-01-02
C armen | New Camiling | 2nd Eng'g. Dist. | On-going | 2020-05-14 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 090 - Maligaya - New Camiling |  | GENERAL FUND CY 2020 | Maintenance |  | km | CBRMC | Project Cost: | 83915.44 | Target Completion Date: | 2020-11-14 23:59 | Program: | 83915.44 | Planned: | 5% | No. of Persons: | 2 | On-going
C armen | New Camiling | 2nd Eng'g. Dist. | On-going | 2020-05-14 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Maligro | Revised Completion Date: |  | Allotment: | 83915.44 | Revised: |  | No. of Man-days: | 2
C armen | New Camiling | 2nd Eng'g. Dist. | On-going | 2020-05-14 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: | School in the Air Integrated Farmer's Associiation | No. of days suspended: |  | Disbursement: |  | Actual: | 5%
C armen | New Camiling | 2nd Eng'g. Dist. | On-going | 2020-05-14 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: | 185 | No. of days extended: |  |  |  | Slippage: | 0%
C armen | New Camiling | 2nd Eng'g. Dist. | On-going | 2020-05-14 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
C armen | New Camiling | 2nd Eng'g. Dist. | On-going | 2020-05-14 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started: | 2020-05-14
C armen | New Camiling | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 091 - New Camiling - Alejal - Lower Magsaysay |  | GENERAL FUND CY 2020 | Maintenance | 6.73 | km | MBA | Project Cost: | 277852.05 | Target Completion Date: | 2020-12-31 23:59 | Program: | 277852.05 | Planned: | 50% | No. of Persons: | 3 | On-going
C armen | New Camiling | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Gamad/Clar | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 277852.05 | Revised: |  | No. of Man-days: | 66
C armen | New Camiling | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: |  | Actual: | 50%
C armen | New Camiling | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0%
C armen | New Camiling | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
C armen | New Camiling | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started: | 2020-01-02
C armen | New Camiling | 2nd Eng'g. Dist. | On-going | 2020-05-14 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 091 - New Camiling - Alejal - Lower Magsaysay |  | GENERAL FUND CY 2020 | Maintenance | 6.73 | km | CBRMC | Project Cost: | 150927.01 | Target Completion Date: | 2020-11-14 23:59 | Program: | 150927.01 | Planned: | 5% | No. of Persons: |  | On-going
C armen | New Camiling | 2nd Eng'g. Dist. | On-going | 2020-05-14 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Maligro | Revised Completion Date: |  | Allotment: | 150927.01 | Revised: |  | No. of Man-days:
C armen | New Camiling | 2nd Eng'g. Dist. | On-going | 2020-05-14 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: | School in the Air Integrated Farmer's Association | No. of days suspended: |  | Disbursement: |  | Actual: | 5%
C armen | New Camiling | 2nd Eng'g. Dist. | On-going | 2020-05-14 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: | 185 | No. of days extended: |  |  |  | Slippage: | 0%
C armen | New Camiling | 2nd Eng'g. Dist. | On-going | 2020-05-14 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
C armen | New Camiling | 2nd Eng'g. Dist. | On-going | 2020-05-14 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started: | 2020-05-14
Carmen | Tuganay | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 094 - Jct. highway Tuganay - Anibongan |  | GENERAL FUND CY 2020 | Maintenance | 3.66 | km | MBA | Project Cost: | 139609.7 | Target Completion Date: | 2020-12-31 23:59 | Program: | 139609.7 | Planned: | 50% | No. of Persons: | 4 | On-going
Carmen | Tuganay | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Gamad/Clar | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 139609.7 | Revised: |  | No. of Man-days: | 88
Carmen | Tuganay | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: |  | Actual: | 55%
Carmen | Tuganay | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 5%
Carmen | Tuganay | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
Carmen | Tuganay | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started: | 2020-01-02
Carmen | Tuganay | 2nd Eng'g. Dist. | On-going | 2020-05-13 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 094 - Jct. highway Tuganay - Anibongan |  | GENERAL FUND CY 2020 | Maintenance | 3.66 | km | CBRMC | Project Cost: | 93574.75 | Target Completion Date: | 2020-11-13 23:59 | Program: | 93574.75 | Planned: | 5% | No. of Persons: |  | Purchase Order # 2020030977 (Ezra Christian Minsitry For Peace, Inc.)
Carmen | Tuganay | 2nd Eng'g. Dist. | On-going | 2020-05-13 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Maligro | Revised Completion Date: |  | Allotment: | 93574.75 | Revised: |  | No. of Man-days:
Carmen | Tuganay | 2nd Eng'g. Dist. | On-going | 2020-05-13 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: | Ezra Christian Minsitry For Peace, Inc. | No. of days suspended: |  | Disbursement: |  | Actual: | 5%
Carmen | Tuganay | 2nd Eng'g. Dist. | On-going | 2020-05-13 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: | 185 | No. of days extended: |  |  |  | Slippage: | 0%
Carmen | Tuganay | 2nd Eng'g. Dist. | On-going | 2020-05-13 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
Carmen | Tuganay | 2nd Eng'g. Dist. | On-going | 2020-05-13 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started: | 2020-05-13
Carmen | Anibongan | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 095 - Anibongan - Guadalupe |  | GENERAL FUND CY 2020 | Maintenance | 2.48 | km | MBA | Project Cost: | 85559.79 | Target Completion Date: | 2020-12-31 23:59 | Program: | 85559.79 | Planned: | 50% | No. of Persons: | 4 | On-going / Time extension on process due to suspension of activity
Carmen | Anibongan | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Gamad/Clar | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 85559.79 | Revised: |  | No. of Man-days: | 78
Carmen | Anibongan | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: |  | Actual: | 55%
Carmen | Anibongan | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 5%
Carmen | Anibongan | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
Carmen | Anibongan | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started: | 2020-01-02
Carmen | Anibongan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 095 - Anibongan - Guadalupe |  | GENERAL FUND CY 2020 | Maintenance | 2.48 | km | CBRMC | Project Cost: | 72444.97 | Target Completion Date: |  | Program: | 72444.97 | Planned: |  | No. of Persons: |  | PO #2020031404 - PRK 4. ANIBONGAN CARMENT IRRIGATORS ASSN.
Carmen | Anibongan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Maligro | Revised Completion Date: |  | Allotment: | 72444.97 | Revised: |  | No. of Man-days:
Carmen | Anibongan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Carmen | Anibongan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Carmen | Anibongan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: |  | Date completed:
Carmen | Anibongan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started:
Carmen | Tuganay | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 096 - Tuganay - Anibongan - San Isidro |  | GENERAL FUND CY 2020 | Maintenance | 7.22 | km | MBA | Project Cost: | 344085.79 | Target Completion Date: | 2020-12-31 23:59 | Program: | 344085.79 | Planned: | 50% | No. of Persons: | 3 | On-going
Carmen | Tuganay | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Gamad/Clar | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 344085.79 | Revised: |  | No. of Man-days: | 66
Carmen | Tuganay | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: |  | Actual: | 50%
Carmen | Tuganay | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0%
Carmen | Tuganay | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
Carmen | Tuganay | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started: | 2020-01-02
Carmen | Tuganay | 2nd Eng'g. Dist. | On-going | 2020-05-13 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 096 - Tuganay - Anibongan - San Isidro |  | GENERAL FUND CY 2020 | Maintenance | 7.22 | km | CBRMC | Project Cost: | 115911.95 | Target Completion Date: | 2020-11-13 23:59 | Program: | 115911.95 | Planned: | 5% | No. of Persons: |  | On-going
Carmen | Tuganay | 2nd Eng'g. Dist. | On-going | 2020-05-13 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Maligro | Revised Completion Date: |  | Allotment: | 115911.95 | Revised: |  | No. of Man-days:
Carmen | Tuganay | 2nd Eng'g. Dist. | On-going | 2020-05-13 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: | Ezra Christian Minsitry For Peace, Inc. | No. of days suspended: |  | Disbursement: |  | Actual: | 5%
Carmen | Tuganay | 2nd Eng'g. Dist. | On-going | 2020-05-13 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: | 185 | No. of days extended: |  |  |  | Slippage: | 0%
Carmen | Tuganay | 2nd Eng'g. Dist. | On-going | 2020-05-13 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: |  | Date completed:
Carmen | Tuganay | 2nd Eng'g. Dist. | On-going | 2020-05-13 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started: | 2020-05-13
Carmen | Anibongan | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 097 - Jct. Anibongan - Prk. 2, 7, 5, San Isidro |  | GENERAL FUND CY 2020 | Maintenance | 3.14 | km | MBA | Project Cost: | 89575.84 | Target Completion Date: | 2020-12-31 23:59 | Program: | 89575.84 | Planned: | 50% | No. of Persons: | 4 | On-going
Carmen | Anibongan | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Gamad/Clar | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 89575.84 | Revised: |  | No. of Man-days: | 88
Carmen | Anibongan | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: |  | Actual: | 53%
Carmen | Anibongan | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 3%
Carmen | Anibongan | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
Carmen | Anibongan | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started: | 2020-01-02
Carmen | Anibongan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 097 - Jct. Anibongan - Prk. 2, 7, 5, San Isidro |  | GENERAL FUND CY 2020 | Maintenance | 3.14 | km | CBRMC | Project Cost: | 110478.58 | Target Completion Date: |  | Program: | 110478.58 | Planned: |  | No. of Persons: |  | PO #2020031378 - SAN ISIDRO FARMERS IRRIGATORS ASSN.
Carmen | Anibongan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Maligro | Revised Completion Date: |  | Allotment: | 110478.58 | Revised: |  | No. of Man-days:
Carmen | Anibongan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Carmen | Anibongan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Carmen | Anibongan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: |  | Date completed:
Carmen | Anibongan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started:
Carmen | Anibongan | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 098 - Anibongan - Salvacion - Cabay-angan |  | GENERAL FUND CY 2020 | Maintenance | 6.93 | km | MBA | Project Cost: | 279123.9 | Target Completion Date: | 2020-12-31 23:59 | Program: | 279123.9 | Planned: | 50% | No. of Persons: | 4 | On-going
Carmen | Anibongan | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Gamad/Clar | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 279123.9 | Revised: |  | No. of Man-days: | 88
Carmen | Anibongan | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: |  | Actual: | 51%
Carmen | Anibongan | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 1%
Carmen | Anibongan | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
Carmen | Anibongan | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started: | 2020-01-02
Carmen | Anibongan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 098 - Anibongan - Salvacion - Cabay-angan |  | GENERAL FUND CY 2020 | Maintenance | 6.93 | km | CBRMC | Project Cost: | 162397.48 | Target Completion Date: |  | Program: | 162397.48 | Planned: |  | No. of Persons: |  | PO #2020031379 - PRK4. ANIBONGAN CARMEN IRRIGATORS ASS.
Carmen | Anibongan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Maligro | Revised Completion Date: |  | Allotment: | 162397.48 | Revised: |  | No. of Man-days:
Carmen | Anibongan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Carmen | Anibongan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Carmen | Anibongan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: |  | Date completed:
Carmen | Anibongan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started:
Carmen | Mabaus | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 099 - Mabaus - Cabay - angan |  | GENERAL FUND CY 2020 | Maintenance |  | km | MBA | Project Cost: | 113320.9 | Target Completion Date: | 2020-12-31 23:59 | Program: | 113320.9 | Planned: | 50% | No. of Persons: | 3 | On-going
Carmen | Mabaus | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Gamad/Clar | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 113320.9 | Revised: |  | No. of Man-days: | 66
Carmen | Mabaus | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: |  | Actual: | 54%
Carmen | Mabaus | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 4%
Carmen | Mabaus | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
Carmen | Mabaus | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started: | 2020-01-02
Carmen | Mabaus | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 099 - Mabaus - Cabay - angan |  | GENERAL FUND CY 2020 | Maintenance |  | km | CBRMC | Project Cost: | 90556.21 | Target Completion Date: |  | Program: | 90556.21 | Planned: |  | No. of Persons: |  | PO #2020031410 - LAMPIA PAG ASA IRRIGATORS ASS., INC.
Carmen | Mabaus | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Maligro | Revised Completion Date: |  | Allotment: | 90556.21 | Revised: |  | No. of Man-days:
Carmen | Mabaus | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Carmen | Mabaus | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Carmen | Mabaus | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: |  | Date completed:
Carmen | Mabaus | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started:
Carmen | Guadalupe | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 101 - Jct. Highway Guadalupe - Bdry. Tagum |  | GENERAL FUND CY 2020 | Maintenance | 7.9 | km | MBA | Project Cost: | 517780.87 | Target Completion Date: | 2020-12-31 23:59 | Program: | 517780.87 | Planned: | 50% | No. of Persons: | 3 | On-going
Carmen | Guadalupe | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Gamad/Clar | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 517780.87 | Revised: |  | No. of Man-days: | 66
Carmen | Guadalupe | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: |  | Actual: | 55%
Carmen | Guadalupe | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 5%
Carmen | Guadalupe | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
Carmen | Guadalupe | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started: | 2020-01-02
Carmen | Guadalupe | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 101 - Jct. Highway Guadalupe - Bdry. Tagum |  | GENERAL FUND CY 2020 | Maintenance | 7.9 | km | CBRMC | Project Cost: | 231823.89 | Target Completion Date: |  | Program: | 231823.89 | Planned: |  | No. of Persons: |  | PO #2020031376 - LAMPIA PAG ASA IRRIGATORS ASS., INC.
Carmen | Guadalupe | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Maligro | Revised Completion Date: |  | Allotment: | 231823.89 | Revised: |  | No. of Man-days:
Carmen | Guadalupe | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Carmen | Guadalupe | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Carmen | Guadalupe | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: |  | Date completed:
Carmen | Guadalupe | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started:
B.E. Dujali | Tanglaw | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 104 - Dujali - Tanglaw |  | GENERAL FUND CY 2020 | Maintenance |  | km | MBA | Project Cost: | 135183.27 | Target Completion Date: | 2020-12-31 23:59 | Program: | 135183.27 | Planned: | 50% | No. of Persons: | 3 | On-going
B.E. Dujali | Tanglaw | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Gamad/Clar | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 135183.27 | Revised: |  | No. of Man-days: | 66
B.E. Dujali | Tanglaw | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: |  | Actual: | 52%
B.E. Dujali | Tanglaw | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 2%
B.E. Dujali | Tanglaw | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
B.E. Dujali | Tanglaw | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started: | 2020-01-02
B.E. Dujali | Tanglaw | 2nd Eng'g. Dist. | On-going | 2020-06-08 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 104 - Dujali - Tanglaw |  | GENERAL FUND CY 2020 | Maintenance |  | km | CBRMC | Project Cost: | 94178.48 | Target Completion Date: | 2020-12-12 | Program: | 94178.48 | Planned: | 5% | No. of Persons: | 2 | On-going
B.E. Dujali | Tanglaw | 2nd Eng'g. Dist. | On-going | 2020-06-08 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Maligro | Revised Completion Date: | 2021-01-08 | Allotment: | 94178.48 | Revised: |  | No. of Man-days: | 2
B.E. Dujali | Tanglaw | 2nd Eng'g. Dist. | On-going | 2020-06-08 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: | Dujali Poblacion Farmer's Irrigator's Association, Inc. | No. of days suspended: | 27 | Disbursement: |  | Actual: | 5%
B.E. Dujali | Tanglaw | 2nd Eng'g. Dist. | On-going | 2020-06-08 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: | 187 | No. of days extended: |  |  |  | Slippage: | 0%
B.E. Dujali | Tanglaw | 2nd Eng'g. Dist. | On-going | 2020-06-08 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
B.E. Dujali | Tanglaw | 2nd Eng'g. Dist. | On-going | 2020-06-08 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started: | 2020-06-08
B.E. Dujali | Dujali | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 105 - Poblacion Dujali - Prk. 8 Dujali |  | GENERAL FUND CY 2020 | Maintenance | 8.2 | km | MBA | Project Cost: | 329064 | Target Completion Date: | 2020-12-31 23:59 | Program: | 329064 | Planned: | 50% | No. of Persons: | 3 | On-going
B.E. Dujali | Dujali | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Gamad/Clar | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 329064 | Revised: |  | No. of Man-days: | 66
B.E. Dujali | Dujali | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: |  | Actual: | 56%
B.E. Dujali | Dujali | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 6%
B.E. Dujali | Dujali | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
B.E. Dujali | Dujali | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started: | 2020-01-02
B.E. Dujali | Dujali | 2nd Eng'g. Dist. | On-going | 2020-06-08 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 105 - Poblacion Dujali - Prk. 8 Dujali |  | GENERAL FUND CY 2020 | Maintenance | 8.2 | km | CBRMC | Project Cost: | 193371.11 | Target Completion Date: | 2020-12-12 | Program: | 193371.11 | Planned: | 5% | No. of Persons: | 2 | On-going
B.E. Dujali | Dujali | 2nd Eng'g. Dist. | On-going | 2020-06-08 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Maligro | Revised Completion Date: | 2021-01-08 | Allotment: | 193371.11 | Revised: |  | No. of Man-days: | 2
B.E. Dujali | Dujali | 2nd Eng'g. Dist. | On-going | 2020-06-08 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: | Dujali Poblacion Farmer's Irrigator's Association, Inc. | No. of days suspended: | 27 | Disbursement: |  | Actual: | 5%
B.E. Dujali | Dujali | 2nd Eng'g. Dist. | On-going | 2020-06-08 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: | 187 | No. of days extended: |  |  |  | Slippage: | 0%
B.E. Dujali | Dujali | 2nd Eng'g. Dist. | On-going | 2020-06-08 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
B.E. Dujali | Dujali | 2nd Eng'g. Dist. | On-going | 2020-06-08 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started: | 2020-06-08
B.E. Dujali | Dujali | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 107 - Dujali - San Isidro |  | GENERAL FUND CY 2020 | Maintenance | 3 | km | MBA | Project Cost: | 112652.73 | Target Completion Date: | 2020-12-31 23:59 | Program: | 112652.73 | Planned: | 50% | No. of Persons: | 3 | On-going
B.E. Dujali | Dujali | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Gamad/Clar | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 112652.73 | Revised: |  | No. of Man-days: | 66
B.E. Dujali | Dujali | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: |  | Actual: | 57%
B.E. Dujali | Dujali | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 7%
B.E. Dujali | Dujali | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
B.E. Dujali | Dujali | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started: | 2020-01-02
B.E. Dujali | Dujali | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 107 - Dujali - San Isidro |  | GENERAL FUND CY 2020 | Maintenance | 3 | km | CBRMC | Project Cost: | 78482.06 | Target Completion Date: |  | Program: | 78482.06 | Planned: |  | No. of Persons: |  | PO #2020031411 - SAN ISIDRO FARMERS IRRIGATORS ASSN., INC.
B.E. Dujali | Dujali | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Maligro | Revised Completion Date: |  | Allotment: | 78482.06 | Revised: |  | No. of Man-days:
B.E. Dujali | Dujali | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
B.E. Dujali | Dujali | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
B.E. Dujali | Dujali | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: |  | Date completed:
B.E. Dujali | Dujali | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started:
B.E. Dujali | New Casay | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 108 - New Casay - Bugtong Talisay |  | GENERAL FUND CY 2020 | Maintenance |  | km | MBA | Project Cost: | 74294.5 | Target Completion Date: | 2020-12-31 23:59 | Program: | 74294.5 | Planned: | 50% | No. of Persons: | 4 | On-going
B.E. Dujali | New Casay | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Gamad/Clar | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 74294.5 | Revised: |  | No. of Man-days: | 88
B.E. Dujali | New Casay | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: |  | Actual: | 50%
B.E. Dujali | New Casay | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0%
B.E. Dujali | New Casay | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
B.E. Dujali | New Casay | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started: | 2020-01-02
B.E. Dujali | New Casay | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 108 - New Casay - Bugtong Talisay |  | GENERAL FUND CY 2020 | Maintenance |  | km | CBRMC | Project Cost: | 64596.78 | Target Completion Date: |  | Program: | 64596.78 | Planned: |  | No. of Persons: |  | For re-bid
B.E. Dujali | New Casay | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Maligro | Revised Completion Date: |  | Allotment: | 64596.78 | Revised: |  | No. of Man-days:
B.E. Dujali | New Casay | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
B.E. Dujali | New Casay | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
B.E. Dujali | New Casay | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: |  | Date completed:
B.E. Dujali | New Casay | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started:
B.E. Dujali | Magupising | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 113 - Dujali - Balisong - Magupising |  | GENERAL FUND CY 2020 | Maintenance | 5.52 | km | MBA | Project Cost: | 235776.07 | Target Completion Date: | 2020-12-31 23:59 | Program: | 235776.07 | Planned: | 50% | No. of Persons: | 3 | On-going
B.E. Dujali | Magupising | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Gamad/Clar | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 235776.07 | Revised: |  | No. of Man-days: | 22
B.E. Dujali | Magupising | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: |  | Actual: | 55%
B.E. Dujali | Magupising | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 5%
B.E. Dujali | Magupising | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
B.E. Dujali | Magupising | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started: | 2020-01-02
B.E. Dujali | Magupising | 2nd Eng'g. Dist. | On-going | 2020-06-08 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 113 - Dujali - Balisong - Magupising |  | GENERAL FUND CY 2020 | Maintenance | 5.52 | km | CBRMC | Project Cost: | 115911.95 | Target Completion Date: | 2020-12-12 | Program: | 115911.95 | Planned: | 5% | No. of Persons: |  | On-going
B.E. Dujali | Magupising | 2nd Eng'g. Dist. | On-going | 2020-06-08 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Maligro | Revised Completion Date: | 2021-01-08 | Allotment: | 115911.95 | Revised: |  | No. of Man-days:
B.E. Dujali | Magupising | 2nd Eng'g. Dist. | On-going | 2020-06-08 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: | Dujali Poblacion Farmer's Irrigator's Association, Inc. | No. of days suspended: | 27 | Disbursement: |  | Actual: | 5%
B.E. Dujali | Magupising | 2nd Eng'g. Dist. | On-going | 2020-06-08 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: | 187 | No. of days extended: |  |  |  | Slippage: | 0%
B.E. Dujali | Magupising | 2nd Eng'g. Dist. | On-going | 2020-06-08 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
B.E. Dujali | Magupising | 2nd Eng'g. Dist. | On-going | 2020-06-08 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started: | 2020-06-08
B.E. Dujali | Dujali | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 117 - Dujali - Pawas - San Vicente |  | GENERAL FUND CY 2020 | Maintenance | 4.42 | km | MBA | Project Cost: | 141544.99 | Target Completion Date: | 2020-12-31 23:59 | Program: | 141544.99 | Planned: | 50% | No. of Persons: | 3 | On-going
B.E. Dujali | Dujali | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Gamad/Clar | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 141544.99 | Revised: |  | No. of Man-days: | 22
B.E. Dujali | Dujali | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: |  | Actual: | 50%
B.E. Dujali | Dujali | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0%
B.E. Dujali | Dujali | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
B.E. Dujali | Dujali | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started: | 2020-01-02
B.E. Dujali | Dujali | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 117 - Dujali - Pawas - San Vicente |  | GENERAL FUND CY 2020 | Maintenance | 4.42 | km | CBRMC | Project Cost: | 140060.27 | Target Completion Date: |  | Program: | 140060.27 | Planned: |  | No. of Persons: |  | Abstract #320201344 -For post qualification
B.E. Dujali | Dujali | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Maligro | Revised Completion Date: |  | Allotment: | 140060.27 | Revised: |  | No. of Man-days:
B.E. Dujali | Dujali | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
B.E. Dujali | Dujali | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
B.E. Dujali | Dujali | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: |  | Date completed:
B.E. Dujali | Dujali | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started:
Sto. Tomas | Salvacion | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 118- Jct. Salvacion - San Vicente - Cabay-angan |  | GENERAL FUND CY 2020 | Maintenance | 3.45 | km | MBA | Project Cost: | 168583.81 | Target Completion Date: | 2020-12-31 23:59 | Program: | 168583.81 | Planned: | 50% | No. of Persons: | 3 | On-going
Sto. Tomas | Salvacion | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Gamad/Clar | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 168583.81 | Revised: |  | No. of Man-days: | 60
Sto. Tomas | Salvacion | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: |  | Actual: | 55%
Sto. Tomas | Salvacion | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 5%
Sto. Tomas | Salvacion | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
Sto. Tomas | Salvacion | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started: | 2020-01-02
Sto. Tomas | Salvacion | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 118- Jct. Salvacion - San Vicente - Cabay-angan |  | GENERAL FUND CY 2020 | Maintenance | 3.45 | km | CBRMC | Project Cost: | 158775.23 | Target Completion Date: |  | Program: | 158775.23 | Planned: |  | No. of Persons: |  | Abstract #320201396 - For post qualification
Sto. Tomas | Salvacion | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Maligro | Revised Completion Date: |  | Allotment: | 158775.23 | Revised: |  | No. of Man-days:
Sto. Tomas | Salvacion | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Sto. Tomas | Salvacion | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Sto. Tomas | Salvacion | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: |  | Date completed:
Sto. Tomas | Salvacion | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started:
Sto. Tomas | Casig-ang | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 123- Bacali - Casig-ang - Libertad |  | GENERAL FUND CY 2020 | Maintenance |  | km | MBA | Project Cost: | 167836.14 | Target Completion Date: | 2020-12-31 23:59 | Program: | 167836.14 | Planned: | 50% | No. of Persons: | 3 | On-going
Sto. Tomas | Casig-ang | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Gamad/Clar | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 167836.14 | Revised: |  | No. of Man-days: | 60
Sto. Tomas | Casig-ang | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: |  | Actual: | 58%
Sto. Tomas | Casig-ang | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 8%
Sto. Tomas | Casig-ang | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
Sto. Tomas | Casig-ang | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started: | 2020-01-02
Sto. Tomas | Casig-ang | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 123- Bacali - Casig-ang - Libertad |  | GENERAL FUND CY 2020 | Maintenance |  | km | CBRMC | Project Cost: | 131608.37 | Target Completion Date: |  | Program: | 131608.37 | Planned: |  | No. of Persons: |  | Abstract #320201449 - For post qualification
Sto. Tomas | Casig-ang | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Maligro | Revised Completion Date: |  | Allotment: | 131608.37 | Revised: |  | No. of Man-days:
Sto. Tomas | Casig-ang | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Sto. Tomas | Casig-ang | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Sto. Tomas | Casig-ang | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: |  | Date completed:
Sto. Tomas | Casig-ang | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started:
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 124 - Kinamayan - Moslog - Mahayag |  | GENERAL FUND CY 2020 | Maintenance |  | km | MBA | Project Cost: | 114628.54 | Target Completion Date: | 2020-12-31 23:59 | Program: | 114628.54 | Planned: | 50% | No. of Persons: | 3 | On-going
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Gamad/Clar | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 114628.54 | Revised: |  | No. of Man-days: | 66
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: |  | Actual: | 50%
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0%
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started: | 2020-01-02
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 124 - Kinamayan - Moslog - Mahayag |  | GENERAL FUND CY 2020 | Maintenance |  | km | CBRMC | Project Cost: | 91159.92 | Target Completion Date: |  | Program: | 91159.92 | Planned: |  | No. of Persons: |  | For re-bid
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Maligro | Revised Completion Date: |  | Allotment: | 91159.92 | Revised: |  | No. of Man-days:
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: |  | Date completed:
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started:
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 126 - Kinamayan - Lunga-og |  | GENERAL FUND CY 2020 | Maintenance |  | km | MBA | Project Cost: | 100416.26 | Target Completion Date: | 2020-12-31 23:59 | Program: | 100416.26 | Planned: | 50% | No. of Persons: |  | On-going
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Gamad/Clar | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 100416.26 | Revised: |  | No. of Man-days:
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: |  | Actual: | 52%
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 2%
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started: | 2020-01-02
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | On-going | 2020-06-15 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 126 - Kinamayan - Lunga-og |  | GENERAL FUND CY 2020 | Maintenance |  | km | CBRMC | Project Cost: | 64596.78 | Target Completion Date: | 2020-12-15 23:59 | Program: | 64596.78 | Planned: | 5% | No. of Persons: | 1 | On-going
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | On-going | 2020-06-15 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Maligro | Revised Completion Date: |  | Allotment: | 64596.78 | Revised: |  | No. of Man-days: | 2
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | On-going | 2020-06-15 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: | Lunga-og Tribal Association | No. of days suspended: |  | Disbursement: |  | Actual: | 5%
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | On-going | 2020-06-15 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: | 184 | No. of days extended: |  |  |  | Slippage: | 0%
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | On-going | 2020-06-15 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | On-going | 2020-06-15 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started: | 2020-06-15
Sto. Tomas | La Libertad | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 128 - Prk. Apitong - Upper Balisong - Dalisay |  | GENERAL FUND CY 2020 | Maintenance | 4.6 | km | MBA | Project Cost: | 150598.24 | Target Completion Date: | 2020-12-31 23:59 | Program: | 150598.24 | Planned: | 10% | No. of Persons: | 3 | On-going
Sto. Tomas | La Libertad | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Gamad/Clar | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 150598.24 | Revised: |  | No. of Man-days: | 60
Sto. Tomas | La Libertad | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: |  | Actual: | 9%
Sto. Tomas | La Libertad | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | -1%
Sto. Tomas | La Libertad | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
Sto. Tomas | La Libertad | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started: | 2020-01-02
Sto. Tomas | La Libertad | 2nd Eng'g. Dist. | On-going | 2020-06-15 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 128 - Prk. Apitong - Upper Balisong - Dalisay |  | GENERAL FUND CY 2020 | Maintenance | 4.6 | km | CBRMC | Project Cost: | 142475.11 | Target Completion Date: | 2020-12-15 23:59 | Program: | 142475.11 | Planned: | 5% | No. of Persons: |  | On-going
Sto. Tomas | La Libertad | 2nd Eng'g. Dist. | On-going | 2020-06-15 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Maligro | Revised Completion Date: |  | Allotment: | 142475.11 | Revised: |  | No. of Man-days:
Sto. Tomas | La Libertad | 2nd Eng'g. Dist. | On-going | 2020-06-15 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: | Lunga-og Tribal Association | No. of days suspended: |  | Disbursement: |  | Actual: | 5%
Sto. Tomas | La Libertad | 2nd Eng'g. Dist. | On-going | 2020-06-15 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: | 184 | No. of days extended: |  |  |  | Slippage: | 0%
Sto. Tomas | La Libertad | 2nd Eng'g. Dist. | On-going | 2020-06-15 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
Sto. Tomas | La Libertad | 2nd Eng'g. Dist. | On-going | 2020-06-15 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started: | 2020-06-15
Sto. Tomas | Esperanza | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 130 - Los Amigos 1 - Esperanza - Los Amigos 2 |  | GENERAL FUND CY 2020 | Maintenance | 3.59 | km | MBA | Project Cost: | 97116.27 | Target Completion Date: | 2020-12-31 23:59 | Program: | 97116.27 | Planned: | 50% | No. of Persons: | 4 | On-going
Sto. Tomas | Esperanza | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Gamad/Clar | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 97116.27 | Revised: |  | No. of Man-days: | 88
Sto. Tomas | Esperanza | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: |  | Actual: | 55%
Sto. Tomas | Esperanza | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 5%
Sto. Tomas | Esperanza | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
Sto. Tomas | Esperanza | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started: | 2020-01-02
Sto. Tomas | Esperanza | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 130 - Los Amigos 1 - Esperanza - Los Amigos 2 |  | GENERAL FUND CY 2020 | Maintenance | 3.59 | km | CBRMC | Project Cost: | 131608.37 | Target Completion Date: |  | Program: | 131608.37 | Planned: |  | No. of Persons: |  | PO #2020031351 - LOS AMIGOS GROUP OF WOMEN & FARMERS ASSN.
Sto. Tomas | Esperanza | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Maligro | Revised Completion Date: |  | Allotment: | 131608.37 | Revised: |  | No. of Man-days:
Sto. Tomas | Esperanza | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Sto. Tomas | Esperanza | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Sto. Tomas | Esperanza | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: |  | Date completed:
Sto. Tomas | Esperanza | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started:
Sto. Tomas | Lunga-og | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 131 - Mugas - Lanatad |  | GENERAL FUND CY 2020 | Maintenance |  | km | MBA | Project Cost: | 65482.21 | Target Completion Date: | 2020-12-31 23:59 | Program: | 65482.21 | Planned: | 50% | No. of Persons: | 3 | On-going
Sto. Tomas | Lunga-og | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Gamad/Clar | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 65482.21 | Revised: |  | No. of Man-days: | 12
Sto. Tomas | Lunga-og | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: |  | Actual: | 50%
Sto. Tomas | Lunga-og | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0%
Sto. Tomas | Lunga-og | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
Sto. Tomas | Lunga-og | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started: | 2020-01-02
Sto. Tomas | Lunga-og | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 131 - Mugas - Lanatad |  | GENERAL FUND CY 2020 | Maintenance |  | km | CBRMC | Project Cost: | 31996.54 | Target Completion Date: |  | Program: | 31996.54 | Planned: |  | No. of Persons: |  | Purchase Order # 2020030961 (Katipunan Pantaron Irrigator's Association)
Sto. Tomas | Lunga-og | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Maligro | Revised Completion Date: |  | Allotment: | 31996.54 | Revised: |  | No. of Man-days:
Sto. Tomas | Lunga-og | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Sto. Tomas | Lunga-og | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Sto. Tomas | Lunga-og | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: |  | Date completed:
Sto. Tomas | Lunga-og | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started:
Sto. Tomas | Lunga-og | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 132 - Mugas - Lunga-og |  | GENERAL FUND CY 2020 | Maintenance | 2.68 | km | MBA | Project Cost: | 96490.97 | Target Completion Date: | 2020-12-31 23:59 | Program: | 96490.97 | Planned: | 50% | No. of Persons: | 3 | On-going
Sto. Tomas | Lunga-og | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Gamad/Clar | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 96490.97 | Revised: |  | No. of Man-days: | 20
Sto. Tomas | Lunga-og | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: |  | Actual: | 50%
Sto. Tomas | Lunga-og | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0%
Sto. Tomas | Lunga-og | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
Sto. Tomas | Lunga-og | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started: | 2020-01-02
Sto. Tomas | Lunga-og | 2nd Eng'g. Dist. | On-going | 2020-06-15 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 132 - Mugas - Lunga-og |  | GENERAL FUND CY 2020 | Maintenance | 2.68 | km | CBRMC | Project Cost: | 74256.11 | Target Completion Date: | 2020-12-15 23:59 | Program: | 74256.11 | Planned: |  | No. of Persons: | 5 | On-going
Sto. Tomas | Lunga-og | 2nd Eng'g. Dist. | On-going | 2020-06-15 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Maligro | Revised Completion Date: | 2021-01-11 23:59 | Allotment: | 74256.11 | Revised: |  | No. of Man-days: | 5
Sto. Tomas | Lunga-og | 2nd Eng'g. Dist. | On-going | 2020-06-15 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: | Lunga-og Tribal Association | No. of days suspended: | 27 | Disbursement: |  | Actual:
Sto. Tomas | Lunga-og | 2nd Eng'g. Dist. | On-going | 2020-06-15 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: | 184 | No. of days extended: |  |  |  | Slippage: | 0%
Sto. Tomas | Lunga-og | 2nd Eng'g. Dist. | On-going | 2020-06-15 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
Sto. Tomas | Lunga-og | 2nd Eng'g. Dist. | On-going | 2020-06-15 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started: | 2020-06-15
Sto. Tomas | New Katipunan | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 134 - New Katipunan - Pantaron |  | GENERAL FUND CY 2020 | Maintenance |  | km | MBA | Project Cost: | 71748.41 | Target Completion Date: | 2020-12-31 23:59 | Program: | 71748.41 | Planned: | 50% | No. of Persons: | 2 | On-going
Sto. Tomas | New Katipunan | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Gamad/Clar | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 71748.41 | Revised: |  | No. of Man-days: | 20
Sto. Tomas | New Katipunan | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: |  | Actual: | 51%
Sto. Tomas | New Katipunan | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 1%
Sto. Tomas | New Katipunan | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
Sto. Tomas | New Katipunan | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started: | 2020-01-02
Sto. Tomas | New Katipunan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 134 - New Katipunan - Pantaron |  | GENERAL FUND CY 2020 | Maintenance |  | km | CBRMC | Project Cost: | 53126.32 | Target Completion Date: |  | Program: | 53126.32 | Planned: |  | No. of Persons: |  | Purchase Order # 2020030964 (Katipunan Pantaron Irrigator's Association)
Sto. Tomas | New Katipunan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Maligro | Revised Completion Date: |  | Allotment: | 53126.32 | Revised: |  | No. of Man-days:
Sto. Tomas | New Katipunan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Sto. Tomas | New Katipunan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Sto. Tomas | New Katipunan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: |  | Date completed:
Sto. Tomas | New Katipunan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started:
Sto. Tomas | New Katipunan | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 135 - Sto. Tomas - Bdry. Mamacao |  | GENERAL FUND CY 2020 | Maintenance | 4.9 | km | MBA | Project Cost: | 195671.17 | Target Completion Date: | 2020-12-31 23:59 | Program: | 195671.17 | Planned: | 50% | No. of Persons: | 3 | On-going
Sto. Tomas | New Katipunan | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Gamad/Clar | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 195671.17 | Revised: |  | No. of Man-days: | 33
Sto. Tomas | New Katipunan | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: |  | Actual: | 52%
Sto. Tomas | New Katipunan | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 2%
Sto. Tomas | New Katipunan | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
Sto. Tomas | New Katipunan | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started: | 2020-01-02
Sto. Tomas | New Katipunan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 135 - Sto. Tomas - Bdry. Mamacao |  | GENERAL FUND CY 2020 | Maintenance | 4.9 | km | CBRMC | Project Cost: | 116515.66 | Target Completion Date: |  | Program: | 116515.66 | Planned: |  | No. of Persons: |  | PO #2020031353 - KATIPUNAN PANTARON IRRIGATORS ASSN.
Sto. Tomas | New Katipunan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Maligro | Revised Completion Date: |  | Allotment: | 116515.66 | Revised: |  | No. of Man-days:
Sto. Tomas | New Katipunan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Sto. Tomas | New Katipunan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Sto. Tomas | New Katipunan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: |  | Date completed:
Sto. Tomas | New Katipunan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started:
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 136 - Fd. Rd. 3 - San Jose |  | GENERAL FUND CY 2020 | Maintenance | 4.55 | km | MBA | Project Cost: | 176994.35 | Target Completion Date: | 2020-12-31 23:59 | Program: | 176994.35 | Planned: | 50% | No. of Persons: | 2 | On-going
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Gamad/Clar | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 176994.35 | Revised: |  | No. of Man-days: | 10
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: |  | Actual: | 55%
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 5%
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started: | 2020-01-02
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 136 - Fd. Rd. 3 - San Jose |  | GENERAL FUND CY 2020 | Maintenance | 4.55 | km | CBRMC | Project Cost: | 112893.42 | Target Completion Date: |  | Program: | 112893.42 | Planned: |  | No. of Persons: |  | Purchase Order # 2020030974 (Brgy. San Jose Upland Farmer's Assocaition)
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Maligro | Revised Completion Date: |  | Allotment: | 112893.42 | Revised: |  | No. of Man-days:
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: |  | Date completed:
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started:
Sto. Tomas | Bobongon | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 139 - Nafco - Bobongon |  | GENERAL FUND CY 2020 | Maintenance |  | km | MBA | Project Cost: | 89179.68 | Target Completion Date: | 2020-12-31 23:59 | Program: | 89179.68 | Planned: | 50% | No. of Persons: | 3 | On-going
Sto. Tomas | Bobongon | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Gamad/Clar | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 89179.68 | Revised: |  | No. of Man-days: | 56
Sto. Tomas | Bobongon | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: |  | Actual: | 55%
Sto. Tomas | Bobongon | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 5%
Sto. Tomas | Bobongon | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
Sto. Tomas | Bobongon | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started: | 2020-01-02
Sto. Tomas | Bobongon | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 139 - Nafco - Bobongon |  | GENERAL FUND CY 2020 | Maintenance |  | km | CBRMC | Project Cost: | 80293.17 | Target Completion Date: |  | Program: | 80293.17 | Planned: |  | No. of Persons: |  | Purchase Order # 2020030968 (Bobongon Rural Waterworks & Sanitation Association, Inc.)
Sto. Tomas | Bobongon | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Maligro | Revised Completion Date: |  | Allotment: | 80293.17 | Revised: |  | No. of Man-days:
Sto. Tomas | Bobongon | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Sto. Tomas | Bobongon | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Sto. Tomas | Bobongon | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: |  | Date completed:
Sto. Tomas | Bobongon | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started:
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 146 - Bdry. Tagum - Crossing Kinamayan Sto. Tomas |  | GENERAL FUND CY 2020 | Maintenance |  | km | MBA | Project Cost: | 790874.1 | Target Completion Date: | 2020-12-31 23:59 | Program: | 790874.1 | Planned: | 50% | No. of Persons: | 3 | On-going
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Gamad/Clar | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 790874.1 | Revised: |  | No. of Man-days: | 66
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: |  | Actual: | 50%
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0%
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started: | 2020-01-02
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 146 - Bdry. Tagum - Crossing Kinamayan Sto. Tomas |  | GENERAL FUND CY 2020 | Maintenance |  | km | CBRMC | Project Cost: | 429840.12 | Target Completion Date: |  | Program: | 429840.12 | Planned: |  | No. of Persons: |  | PO #2020031407 - LOS AMIGOS GROUP OF WOMEN & FARMERS ASSN.
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Maligro | Revised Completion Date: |  | Allotment: | 429840.12 | Revised: |  | No. of Man-days:
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: |  | Date completed:
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started:
Sto. Tomas | Magwawa | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 151 - San Jose - Sitio Mahayahay, Magwawa |  | GENERAL FUND CY 2020 | Maintenance | 0.84 | km | MBA | Project Cost: | 22943.54 | Target Completion Date: | 2020-12-31 23:59 | Program: | 22943.54 | Planned: | 50% | No. of Persons: | 3 | On-going
Sto. Tomas | Magwawa | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Gamad/Clar | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 22943.54 | Revised: |  | No. of Man-days: | 60
Sto. Tomas | Magwawa | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: |  | Actual: | 50%
Sto. Tomas | Magwawa | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0%
Sto. Tomas | Magwawa | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
Sto. Tomas | Magwawa | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started: | 2020-01-02
Sto. Tomas | Magwawa | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 151 - San Jose - Sitio Mahayahay, Magwawa |  | GENERAL FUND CY 2020 | Maintenance | 0.84 | km | CBRMC | Project Cost: | 30789.12 | Target Completion Date: |  | Program: | 30789.12 | Planned: |  | No. of Persons: |  | Purchase Order # 2020030972 (Brgy. San Jose Upland Farmer's Assocaition)
Sto. Tomas | Magwawa | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Maligro | Revised Completion Date: |  | Allotment: | 30789.12 | Revised: |  | No. of Man-days:
Sto. Tomas | Magwawa | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Sto. Tomas | Magwawa | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Sto. Tomas | Magwawa | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: |  | Date completed:
Sto. Tomas | Magwawa | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started:
Babak, IGCS | Cogon | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rural Electrification Project | Completion of Single Phase Line at Purok 6 and Purok 7, Brgy. Cogon, Babak Distirct, IGACOS |  | 20% DF CY 2020 | Electrificaton |  | km |  | Project Cost: | 1000000 | Target Completion Date: |  | Program: | 1000000 | Planned: |  | No. of Persons: |  | PR #20063965
Babak, IGCS | Cogon | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rural Electrification Project | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 1000000 | Revised: |  | No. of Man-days:
Babak, IGCS | Cogon | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rural Electrification Project | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Babak, IGCS | Cogon | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rural Electrification Project | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Babak, IGCS | Cogon | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rural Electrification Project | [7 empty] | Date Allotment Released: |  | Date completed:
Babak, IGCS | Cogon | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rural Electrification Project | [7 empty] | Date Started:
IGCS | Sta. Cruz | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rural Electrification Project | Completion of Single Phase Line at Purok Perlas, Brgy. Sta. Cruz, Talicud (Day Care Center), IGACOS |  | 20% DF CY 2020 | Electrificaton |  | km |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | POW preparation on-going c/o Engr. Kim Pao Lu
IGCS | Sta. Cruz | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rural Electrification Project | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
IGCS | Sta. Cruz | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rural Electrification Project | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
IGCS | Sta. Cruz | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rural Electrification Project | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
IGCS | Sta. Cruz | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rural Electrification Project | [7 empty] | Date Allotment Released: |  | Date completed:
IGCS | Sta. Cruz | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rural Electrification Project | [7 empty] | Date Started:
Sto. Tomas | San Jose | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | ROAD ID 008 - Fr. Rd. 3 - San Jose |  | 20% DF CY 2020 | Rehabilitation |  | km |  | Project Cost: | 8000000 | Target Completion Date: |  | Program: | 8000000 | Planned: |  | No. of Persons: |  | Plan On-going
Sto. Tomas | San Jose | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 8000000 | Revised: |  | No. of Man-days:
Sto. Tomas | San Jose | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Sto. Tomas | San Jose | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Sto. Tomas | San Jose | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Date Allotment Released: |  | Date completed:
Sto. Tomas | San Jose | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Date Started:
Carmen | Asuncion | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | ROAD ID 007 - Lower Asuncion - Upper Asuncion |  | 20% DF CY 2020 | Rehabilitation |  | km |  | Project Cost: | 1302000 | Target Completion Date: |  | Program: | 1302000 | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No
Carmen | Asuncion | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 1302000 | Revised: |  | No. of Man-days:
Carmen | Asuncion | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Carmen | Asuncion | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Carmen | Asuncion | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Date Allotment Released: |  | Date completed:
Carmen | Asuncion | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Date Started:
Carmen | Mangalcal | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | ROAD ID 030 - Jct. Highway - Carmen - Mangalcal - Tubod |  | 20% DF CY 2020 | Rehabilitation |  | km |  | Project Cost: | 1323000 | Target Completion Date: |  | Program: | 1323000 | Planned: |  | No. of Persons: |  | Plan On-going
Carmen | Mangalcal | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 1323000 | Revised: |  | No. of Man-days:
Carmen | Mangalcal | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Carmen | Mangalcal | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Carmen | Mangalcal | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Date Allotment Released: |  | Date completed:
Carmen | Mangalcal | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Date Started:
Carmen | Tuganay | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | ROAD ID 031 - Tuganay - Taba |  | 20% DF CY 2020 | Rehabilitation |  | km |  | Project Cost: | 1431000 | Target Completion Date: |  | Program: | 1431000 | Planned: |  | No. of Persons: |  | Plan On-going
Carmen | Tuganay | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 1431000 | Revised: |  | No. of Man-days:
Carmen | Tuganay | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Carmen | Tuganay | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Carmen | Tuganay | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Date Allotment Released: |  | Date completed:
Carmen | Tuganay | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Date Started:
Carmen | Ising | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | ROAD ID 069 - Jct. Highway - Ising - Magsaysay |  | 20% DF CY 2020 | Rehabilitation |  | km |  | Project Cost: | 6000000 | Target Completion Date: |  | Program: | 6000000 | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No
Carmen | Ising | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 6000000 | Revised: |  | No. of Man-days:
Carmen | Ising | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Carmen | Ising | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Carmen | Ising | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Date Allotment Released: |  | Date completed:
Carmen | Ising | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Date Started:
Carmen | Guadalupe | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | Jct. Highway - Guadalupe - Bdry. Tagum |  | 20% DF CY 2020 | Rehabilitation |  | km |  | Project Cost: | 910000 | Target Completion Date: |  | Program: | 910000 | Planned: |  | No. of Persons: |  | Plan On-going
Carmen | Guadalupe | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 910000 | Revised: |  | No. of Man-days:
Carmen | Guadalupe | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Carmen | Guadalupe | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Carmen | Guadalupe | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Date Allotment Released: |  | Date completed:
Carmen | Guadalupe | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Date Started:
Carmen | Tibulao | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | Sitio Malaga - Tibulao |  | 20% DF CY 2020 | Rehabilitation |  | km |  | Project Cost: | 350000 | Target Completion Date: |  | Program: | 350000 | Planned: |  | No. of Persons: |  | Plan On-going
Carmen | Tibulao | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 350000 | Revised: |  | No. of Man-days:
Carmen | Tibulao | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Carmen | Tibulao | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Carmen | Tibulao | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Date Allotment Released: |  | Date completed:
Carmen | Tibulao | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Date Started:
Carmen | New Casay | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | Prk. 5 RJS - Prk. 6 New Casay |  | 20% DF CY 2020 | Rehabilitation |  | km |  | Project Cost: | 350000 | Target Completion Date: |  | Program: | 350000 | Planned: |  | No. of Persons: |  | Plan On-going
Carmen | New Casay | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 350000 | Revised: |  | No. of Man-days:
Carmen | New Casay | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Carmen | New Casay | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Carmen | New Casay | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Date Allotment Released: |  | Date completed:
Carmen | New Casay | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Date Started:
B.E. Dujali | Pawas | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | Dujali - Pawas - San Vicente |  | 20% DF CY 2020 | Rehabilitation |  | km |  | Project Cost: | 350000 | Target Completion Date: |  | Program: | 350000 | Planned: |  | No. of Persons: |  | Plan On-going
B.E. Dujali | Pawas | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 350000 | Revised: |  | No. of Man-days:
B.E. Dujali | Pawas | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
B.E. Dujali | Pawas | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
B.E. Dujali | Pawas | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Date Allotment Released: |  | Date completed:
B.E. Dujali | Pawas | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Date Started:
Sto. Tomas | Esperanza | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | Los Amigos 1 - Esperanza - Los Amigos 2 |  | 20% DF CY 2020 | Rehabilitation |  | km |  | Project Cost: | 350000 | Target Completion Date: |  | Program: | 350000 | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No
Sto. Tomas | Esperanza | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 350000 | Revised: |  | No. of Man-days:
Sto. Tomas | Esperanza | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Sto. Tomas | Esperanza | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Sto. Tomas | Esperanza | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Date Allotment Released: |  | Date completed:
Sto. Tomas | Esperanza | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Date Started:
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | San Miguel - Crossing Kinamayan |  | 20% DF CY 2020 | Rehabilitation |  | km |  | Project Cost: | 19200000 | Target Completion Date: |  | Program: | 19200000 | Planned: |  | No. of Persons: |  | Plan On-going
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 19200000 | Revised: |  | No. of Man-days:
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Date Allotment Released: |  | Date completed:
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Date Started:
Sto. Tomas | Magwawa | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | Fd. Rd. 2 - Sto. Tomas - Magwawa |  | 20% DF CY 2020 | Rehabilitation |  | km |  | Project Cost: | 350000 | Target Completion Date: |  | Program: | 350000 | Planned: |  | No. of Persons: |  | Plan On-going
Sto. Tomas | Magwawa | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 350000 | Revised: |  | No. of Man-days:
Sto. Tomas | Magwawa | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Sto. Tomas | Magwawa | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Sto. Tomas | Magwawa | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Date Allotment Released: |  | Date completed:
Sto. Tomas | Magwawa | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Date Started:
Sto. Tomas | Balagunan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | Menzi - Balagunan - Tulalian |  | 20% DF CY 2020 | Rehabilitation |  | km |  | Project Cost: | 3720500 | Target Completion Date: |  | Program: | 3720500 | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No
Sto. Tomas | Balagunan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 3720500 | Revised: |  | No. of Man-days:
Sto. Tomas | Balagunan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Sto. Tomas | Balagunan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Sto. Tomas | Balagunan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Date Allotment Released: |  | Date completed:
Sto. Tomas | Balagunan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Date Started:
B.E. Dujali | Magupising | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | Jct,. Bdry. Tagum- Talomo |  | 20% DF CY 2020 | Rehabilitation |  | km |  | Project Cost: | 3720500 | Target Completion Date: |  | Program: | 3720500 | Planned: |  | No. of Persons: |  | POW for approval with the Governor
B.E. Dujali | Magupising | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 3720500 | Revised: |  | No. of Man-days:
B.E. Dujali | Magupising | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
B.E. Dujali | Magupising | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
B.E. Dujali | Magupising | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Date Allotment Released: |  | Date completed:
B.E. Dujali | Magupising | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Date Started:
IGCS | AI | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Various Local Roads & Drainage Dev't. Project | Rehab. Of Various Local Roads @ Island Garden City of Samal |  | 20% DF CY 2020 | Rehabilitation |  | km |  | Project Cost: | 2518182 | Target Completion Date: |  | Program: | 2518182 | Planned: |  | No. of Persons: |  | Plan On-going
IGCS | AI | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Various Local Roads & Drainage Dev't. Project | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 2518182 | Revised: |  | No. of Man-days:
IGCS | AI | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Various Local Roads & Drainage Dev't. Project | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
IGCS | AI | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Various Local Roads & Drainage Dev't. Project | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
IGCS | AI | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Various Local Roads & Drainage Dev't. Project | [7 empty] | Date Allotment Released: |  | Date completed:
IGCS | AI | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Various Local Roads & Drainage Dev't. Project | [7 empty] | Date Started:
Panabo City | APC | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Various Local Roads & Drainage Dev't. Project | Rehab. Of Various Local Roads @ Panabo City |  | 20% DF CY 2020 | Rehabilitation |  | km |  | Project Cost: | 2518182 | Target Completion Date: |  | Program: | 2518182 | Planned: |  | No. of Persons: |  | Abstract # 0420201633 - Billboard; Abstract 0520201661 - hardware
Panabo City | APC | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Various Local Roads & Drainage Dev't. Project | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 2518182 | Revised: |  | No. of Man-days:
Panabo City | APC | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Various Local Roads & Drainage Dev't. Project | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Panabo City | APC | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Various Local Roads & Drainage Dev't. Project | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Panabo City | APC | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Various Local Roads & Drainage Dev't. Project | [7 empty] | Date Allotment Released: |  | Date completed:
Panabo City | APC | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Various Local Roads & Drainage Dev't. Project | [7 empty] | Date Started:
B.E. Dujali | ABD | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Various Local Roads & Drainage Dev't. Project | Rehab. Of Various Local Roads @ B.E Dujali |  | 20% DF CY 2020 | Rehabilitation |  | km |  | Project Cost: | 2518182 | Target Completion Date: |  | Program: | 2518182 | Planned: |  | No. of Persons: |  | Purchase Request # 20053256 - Hardware; PR # 20053255 - Billboard
B.E. Dujali | ABD | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Various Local Roads & Drainage Dev't. Project | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 2518182 | Revised: |  | No. of Man-days:
B.E. Dujali | ABD | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Various Local Roads & Drainage Dev't. Project | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
B.E. Dujali | ABD | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Various Local Roads & Drainage Dev't. Project | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
B.E. Dujali | ABD | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Various Local Roads & Drainage Dev't. Project | [7 empty] | Date Allotment Released: |  | Date completed:
B.E. Dujali | ABD | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Various Local Roads & Drainage Dev't. Project | [7 empty] | Date Started:
Carmen | AC | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Various Local Roads & Drainage Dev't. Project | Rehab. Of Various Local Roads @ Carmen |  | 20% DF CY 2020 | Rehabilitation |  | km |  | Project Cost: | 2518182 | Target Completion Date: |  | Program: | 2518182 | Planned: |  | No. of Persons: |  | Abstract # 0420201633 - Billboard; Abstract 0520201661 - hardware
Carmen | AC | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Various Local Roads & Drainage Dev't. Project | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 2518182 | Revised: |  | No. of Man-days:
Carmen | AC | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Various Local Roads & Drainage Dev't. Project | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Carmen | AC | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Various Local Roads & Drainage Dev't. Project | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Carmen | AC | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Various Local Roads & Drainage Dev't. Project | [7 empty] | Date Allotment Released: |  | Date completed:
Carmen | AC | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Various Local Roads & Drainage Dev't. Project | [7 empty] | Date Started:
Sto. Tomas | AST | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Various Local Roads & Drainage Dev't. Project | Rehab. Of Various Local Roads @ Sto. Tomas |  | 20% DF CY 2020 | Rehabilitation |  | km |  | Project Cost: | 2518182 | Target Completion Date: |  | Program: | 2518182 | Planned: |  | No. of Persons: |  | Plan On-going
Sto. Tomas | AST | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Various Local Roads & Drainage Dev't. Project | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 2518182 | Revised: |  | No. of Man-days:
Sto. Tomas | AST | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Various Local Roads & Drainage Dev't. Project | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Sto. Tomas | AST | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Various Local Roads & Drainage Dev't. Project | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Sto. Tomas | AST | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Various Local Roads & Drainage Dev't. Project | [7 empty] | Date Allotment Released: |  | Date completed:
Sto. Tomas | AST | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Various Local Roads & Drainage Dev't. Project | [7 empty] | Date Started:
Babak, IGCS | AB | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Various Government Buildings and Facilities Development Project | Construction of Commercial Building at Kinawitnon, IGACOS, Babak |  | 20% DF CY 2020 | Building |  | sq.m |  | Project Cost: | 2000000 | Target Completion Date: |  | Program: | 2000000 | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
Babak, IGCS | AB | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Various Government Buildings and Facilities Development Project | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 2000000 | Revised: |  | No. of Man-days:
Babak, IGCS | AB | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Various Government Buildings and Facilities Development Project | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Babak, IGCS | AB | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Various Government Buildings and Facilities Development Project | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Babak, IGCS | AB | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Various Government Buildings and Facilities Development Project | [7 empty] | Date Allotment Released: |  | Date completed:
Babak, IGCS | AB | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Various Government Buildings and Facilities Development Project | [7 empty] | Date Started:
Carmen | Ising | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Various Government Buildings and Facilities Development Project | Improvement of Provincial Engineer's Office 2nd District Office Phase 2, Carmen |  | 20% DF CY 2020 | Building |  | sq.m |  | Project Cost: | 1590000 | Target Completion Date: |  | Program: | 1590000 | Planned: |  | No. of Persons: |  | Plan and DED On-going
Carmen | Ising | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Various Government Buildings and Facilities Development Project | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 1590000 | Revised: |  | No. of Man-days:
Carmen | Ising | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Various Government Buildings and Facilities Development Project | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Carmen | Ising | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Various Government Buildings and Facilities Development Project | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Carmen | Ising | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Various Government Buildings and Facilities Development Project | [7 empty] | Date Allotment Released: |  | Date completed:
Carmen | Ising | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Various Government Buildings and Facilities Development Project | [7 empty] | Date Started:
B.E. Dujali | Ising | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Various Government Buildings and Facilities Development Project | Construction of DDN hospital Carmen Zone Annex Building Phase 3, Carmen |  | GENERAL FUND CY 2020 | Building |  | sq.m |  | Project Cost: | 800000 | Target Completion Date: |  | Program: | 800000 | Planned: |  | No. of Persons: |  | Abstract #0420201476
B.E. Dujali | Ising | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Various Government Buildings and Facilities Development Project | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 800000 | Revised: |  | No. of Man-days:
B.E. Dujali | Ising | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Various Government Buildings and Facilities Development Project | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
B.E. Dujali | Ising | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Various Government Buildings and Facilities Development Project | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
B.E. Dujali | Ising | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Various Government Buildings and Facilities Development Project | [7 empty] | Date Allotment Released: |  | Date completed:
B.E. Dujali | Ising | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Various Government Buildings and Facilities Development Project | [7 empty] | Date Started:
B.E. Dujali | Dujali | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Various Government Buildings and Facilities Development Project | Construction of Municipal Triball Hall, B.E. Dujali |  | GENERAL FUND CY 2020 | Building |  | sq.m |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
B.E. Dujali | Dujali | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Various Government Buildings and Facilities Development Project | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
B.E. Dujali | Dujali | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Various Government Buildings and Facilities Development Project | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
B.E. Dujali | Dujali | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Various Government Buildings and Facilities Development Project | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
B.E. Dujali | Dujali | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Various Government Buildings and Facilities Development Project | [7 empty] | Date Allotment Released: |  | Date completed:
B.E. Dujali | Dujali | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Various Government Buildings and Facilities Development Project | [7 empty] | Date Started:
Sto. Tomas | Tibal-og | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Various Government Buildings and Facilities Development Project | Construction of Municipal Triball Hall, Sto. Tomas |  | GENERAL FUND CY 2020 | Building |  | sq.m | Admin | Project Cost: | 500000 | Target Completion Date: | 2019-07-31 | Program: | 500000 | Planned: | 100% | No. of Persons: | 7 | Suspended June 28, 2019. Waiting for the delivery of JO Materials
Sto. Tomas | Tibal-og | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Various Government Buildings and Facilities Development Project | [7 empty] | Project Engineer: | Roque | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days: | 110
Sto. Tomas | Tibal-og | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Various Government Buildings and Facilities Development Project | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: | 85%
Sto. Tomas | Tibal-og | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Various Government Buildings and Facilities Development Project | [7 empty] | Duration: | 70 | No. of days extended: |  |  |  | Slippage: | -15%
Sto. Tomas | Tibal-og | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Various Government Buildings and Facilities Development Project | [7 empty] | Date Allotment Released: | CY 2018 | Date completed:
Sto. Tomas | Tibal-og | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Various Government Buildings and Facilities Development Project | [7 empty] | Date Started: | 2019-05-22
Sto. Tomas | Tulalian | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Various Government Buildings and Facilities Development Project | Construction of Fence at Tulalian National High School, Tulalian, Sto. Tomas |  | GENERAL FUND CY 2020 | Fence |  | sq.m |  | Project Cost: | 1500000 | Target Completion Date: |  | Program: | 1500000 | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
Sto. Tomas | Tulalian | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Various Government Buildings and Facilities Development Project | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 1500000 | Revised: |  | No. of Man-days:
Sto. Tomas | Tulalian | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Various Government Buildings and Facilities Development Project | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Sto. Tomas | Tulalian | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Various Government Buildings and Facilities Development Project | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Sto. Tomas | Tulalian | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Various Government Buildings and Facilities Development Project | [7 empty] | Date Allotment Released: |  | Date completed:
Sto. Tomas | Tulalian | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Various Government Buildings and Facilities Development Project | [7 empty] | Date Started:
Carmen | Tibulao | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Various Government Buildings and Facilities Development Project | Construction of Two(2) Classroom at Tibulao Elem. School, Tibulao, Carmen |  | GENERAL FUND CY 2020 | Building |  | sq.m |  | Project Cost: | 2900000 | Target Completion Date: |  | Program: | 2900000 | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
Carmen | Tibulao | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Various Government Buildings and Facilities Development Project | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 2900000 | Revised: |  | No. of Man-days:
Carmen | Tibulao | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Various Government Buildings and Facilities Development Project | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Carmen | Tibulao | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Various Government Buildings and Facilities Development Project | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Carmen | Tibulao | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Various Government Buildings and Facilities Development Project | [7 empty] | Date Allotment Released: |  | Date completed:
Carmen | Tibulao | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Various Government Buildings and Facilities Development Project | [7 empty] | Date Started:
Carmen |  | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Desiltation/Excavation of Rivers & Creeks | Improvement and Desiltation of Camoning Creek |  | 5% Calamity Fund CY 2020 | Desiltation |  | ln.m |  | Project Cost: | 2500000 | Target Completion Date: |  | Program: | 2500000 | Planned: |  | No. of Persons: |  | Abstract # 0520201658
Carmen |  | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Desiltation/Excavation of Rivers & Creeks | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 2500000 | Revised: |  | No. of Man-days:
Carmen |  | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Desiltation/Excavation of Rivers & Creeks | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Carmen |  | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Desiltation/Excavation of Rivers & Creeks | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Carmen |  | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Desiltation/Excavation of Rivers & Creeks | [7 empty] | Date Allotment Released: |  | Date completed:
Carmen |  | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Desiltation/Excavation of Rivers & Creeks | [7 empty] | Date Started:
Carmen | Ising | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Desiltation/Excavation of Rivers & Creeks | Improvement and Desiltation of Ising Creek |  | 5% Calamity Fund CY 2020 | Desiltation |  | ln.m |  | Project Cost: | 2000000 | Target Completion Date: |  | Program: | 2000000 | Planned: |  | No. of Persons: |  | Abstract # 0420201637; 0520201662
Carmen | Ising | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Desiltation/Excavation of Rivers & Creeks | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 2000000 | Revised: |  | No. of Man-days:
Carmen | Ising | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Desiltation/Excavation of Rivers & Creeks | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Carmen | Ising | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Desiltation/Excavation of Rivers & Creeks | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Carmen | Ising | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Desiltation/Excavation of Rivers & Creeks | [7 empty] | Date Allotment Released: |  | Date completed:
Carmen | Ising | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Desiltation/Excavation of Rivers & Creeks | [7 empty] | Date Started:
Carmen | Anibongan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Desiltation/Excavation of Rivers & Creeks | Desiltation of Buhang Creek, Anibongan, Carmen |  | 5% Calamity Fund CY 2020 | Desiltation |  | ln.m |  | Project Cost: | 2130206 | Target Completion Date: |  | Program: | 2130206 | Planned: |  | No. of Persons: |  | Abstract # 0520201657; 0420201626
Carmen | Anibongan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Desiltation/Excavation of Rivers & Creeks | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 2130206 | Revised: |  | No. of Man-days:
Carmen | Anibongan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Desiltation/Excavation of Rivers & Creeks | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Carmen | Anibongan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Desiltation/Excavation of Rivers & Creeks | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Carmen | Anibongan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Desiltation/Excavation of Rivers & Creeks | [7 empty] | Date Allotment Released: |  | Date completed:
Carmen | Anibongan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Desiltation/Excavation of Rivers & Creeks | [7 empty] | Date Started:
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Revetment of Dike and Slope Protection | Rehab./Impv't. of San Miguel - Moslog - Kinamayan, Sto. Tomas |  | 5% Calamity Fund CY 2020 | Rehabilitation |  | ln.m |  | Project Cost: | 1000000 | Target Completion Date: |  | Program: | 1000000 | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Revetment of Dike and Slope Protection | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 1000000 | Revised: |  | No. of Man-days:
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Revetment of Dike and Slope Protection | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Revetment of Dike and Slope Protection | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Revetment of Dike and Slope Protection | [7 empty] | Date Allotment Released: |  | Date completed:
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Revetment of Dike and Slope Protection | [7 empty] | Date Started:
Carmen | Mangalcal | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Improvement of Roads, Drainage and Canal | Improvement of Mangalcal to Diamond Creek Farm to Market Road Opening |  | 5% Calamity Fund CY 2020 | Improvement |  | ln.m |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
Carmen | Mangalcal | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Improvement of Roads, Drainage and Canal | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Carmen | Mangalcal | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Improvement of Roads, Drainage and Canal | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Carmen | Mangalcal | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Improvement of Roads, Drainage and Canal | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Carmen | Mangalcal | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Improvement of Roads, Drainage and Canal | [7 empty] | Date Allotment Released: |  | Date completed:
Carmen | Mangalcal | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Improvement of Roads, Drainage and Canal | [7 empty] | Date Started:
Carmen | Mabaus | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Improvement of Roads, Drainage and Canal | Improvement of Mabaus - Salvacion Provincial Road Continuing Road Opening |  | 5% Calamity Fund CY 2020 | Improvement |  | ln.m |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Plan On-going
Carmen | Mabaus | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Improvement of Roads, Drainage and Canal | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Carmen | Mabaus | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Improvement of Roads, Drainage and Canal | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Carmen | Mabaus | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Improvement of Roads, Drainage and Canal | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Carmen | Mabaus | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Improvement of Roads, Drainage and Canal | [7 empty] | Date Allotment Released: |  | Date completed:
Carmen | Mabaus | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Improvement of Roads, Drainage and Canal | [7 empty] | Date Started:
Carmen | Mangalcal | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Improvement of Bridges and Cross Drainage | Single Barrel Box Culvert at Mangalcal-Diamond Creek, Brgy. Mangalcal, Carmen |  | 5% Calamity Fund CY 2020 | Box Culvert |  | ln.m |  | Project Cost: | 2000000 | Target Completion Date: |  | Program: | 2000000 | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
Carmen | Mangalcal | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Improvement of Bridges and Cross Drainage | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 2000000 | Revised: |  | No. of Man-days:
Carmen | Mangalcal | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Improvement of Bridges and Cross Drainage | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Carmen | Mangalcal | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Improvement of Bridges and Cross Drainage | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Carmen | Mangalcal | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Improvement of Bridges and Cross Drainage | [7 empty] | Date Allotment Released: |  | Date completed:
Carmen | Mangalcal | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Improvement of Bridges and Cross Drainage | [7 empty] | Date Started:
Sto. Tomas | Magwawa | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. | Const. of 1 Classroom @ Mangga ES, Magwawa, Sto. Tomas |  | SEF-AB CY 2020 | Building |  | sq.m |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | For preparation of POW and Plans
Sto. Tomas | Magwawa | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Sto. Tomas | Magwawa | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Sto. Tomas | Magwawa | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Sto. Tomas | Magwawa | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. | [7 empty] | Date Allotment Released: |  | Date completed:
Sto. Tomas | Magwawa | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. | [7 empty] | Date Started:
Panabo City | J.P. Laurel | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | Const. of Day Care Center, JP Laurel, Panabo City |  | AB CY 2020 | Building |  | sq.m |  | Project Cost: | 1000000 | Target Completion Date: |  | Program: | 1000000 | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
Panabo City | J.P. Laurel | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 1000000 | Revised: |  | No. of Man-days:
Panabo City | J.P. Laurel | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Panabo City | J.P. Laurel | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Panabo City | J.P. Laurel | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | [7 empty] | Date Allotment Released: |  | Date completed:
Panabo City | J.P. Laurel | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | [7 empty] | Date Started:
B.E. Dujali | Dujali | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | Const. of Day Care Center, Dujali, B.E. Dujali |  | AB CY 2020 | Building |  | sq.m |  | Project Cost: | 1000000 | Target Completion Date: |  | Program: | 1000000 | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
B.E. Dujali | Dujali | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 1000000 | Revised: |  | No. of Man-days:
B.E. Dujali | Dujali | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
B.E. Dujali | Dujali | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
B.E. Dujali | Dujali | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | [7 empty] | Date Allotment Released: |  | Date completed:
B.E. Dujali | Dujali | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | [7 empty] | Date Started:
Sto. Tomas | Tibal-og | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | Const. of Day Care Center, Tibal-og, Sto Tomas |  | AB CY 2020 | Building |  | sq.m |  | Project Cost: | 1000000 | Target Completion Date: |  | Program: | 1000000 | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
Sto. Tomas | Tibal-og | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 1000000 | Revised: |  | No. of Man-days:
Sto. Tomas | Tibal-og | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Sto. Tomas | Tibal-og | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Sto. Tomas | Tibal-og | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | [7 empty] | Date Allotment Released: |  | Date completed:
Sto. Tomas | Tibal-og | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | [7 empty] | Date Started:
B.E. Dujali | Cabay-angan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | Compl./Rep. Day Care Center, Cabay-angan, B.E. Dujali |  | AB CY 2020 | Building |  | sq.m |  | Project Cost: | 300000 | Target Completion Date: |  | Program: | 300000 | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
B.E. Dujali | Cabay-angan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 300000 | Revised: |  | No. of Man-days:
B.E. Dujali | Cabay-angan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
B.E. Dujali | Cabay-angan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
B.E. Dujali | Cabay-angan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | [7 empty] | Date Allotment Released: |  | Date completed:
B.E. Dujali | Cabay-angan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | [7 empty] | Date Started:
B.E. Dujali | Tanglaw | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | Compl./Rep. Day Care Center, Tanglaw, B.E. Dujali |  | AB CY 2020 | Building |  | sq.m |  | Project Cost: | 300000 | Target Completion Date: |  | Program: | 300000 | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
B.E. Dujali | Tanglaw | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 300000 | Revised: |  | No. of Man-days:
B.E. Dujali | Tanglaw | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
B.E. Dujali | Tanglaw | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
B.E. Dujali | Tanglaw | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | [7 empty] | Date Allotment Released: |  | Date completed:
B.E. Dujali | Tanglaw | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | [7 empty] | Date Started:
Carmen | Salvacion | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | Compl./Rep. Day Care Center, Salvacion, Carmen |  | AB CY 2020 | Building |  | sq.m |  | Project Cost: | 300000 | Target Completion Date: |  | Program: | 300000 | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
Carmen | Salvacion | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 300000 | Revised: |  | No. of Man-days:
Carmen | Salvacion | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Carmen | Salvacion | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Carmen | Salvacion | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | [7 empty] | Date Allotment Released: |  | Date completed:
Carmen | Salvacion | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | [7 empty] | Date Started:
IGCS | San Agustin | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | Compl./Rep. Day Care Center, San Agustin, IGCS |  | AB CY 2020 | Building |  | sq.m |  | Project Cost: | 300000 | Target Completion Date: |  | Program: | 300000 | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
IGCS | San Agustin | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 300000 | Revised: |  | No. of Man-days:
IGCS | San Agustin | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
IGCS | San Agustin | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
IGCS | San Agustin | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | [7 empty] | Date Allotment Released: |  | Date completed:
IGCS | San Agustin | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | [7 empty] | Date Started:
IGCS | Toril | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | Compl./Rep. Day Care Center, Toril, IGCS |  | AB CY 2020 | Building |  | sq.m |  | Project Cost: | 300000 | Target Completion Date: |  | Program: | 300000 | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
IGCS | Toril | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 300000 | Revised: |  | No. of Man-days:
IGCS | Toril | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
IGCS | Toril | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
IGCS | Toril | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | [7 empty] | Date Allotment Released: |  | Date completed:
IGCS | Toril | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | [7 empty] | Date Started:
Sto. Tomas | Tibal-og | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | Compl./Rep. Day Care Center, Tibal-og, Sto. Tomas |  | AB CY 2020 | Building |  | sq.m |  | Project Cost: | 600000 | Target Completion Date: |  | Program: | 600000 | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
Sto. Tomas | Tibal-og | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 600000 | Revised: |  | No. of Man-days:
Sto. Tomas | Tibal-og | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Sto. Tomas | Tibal-og | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Sto. Tomas | Tibal-og | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | [7 empty] | Date Allotment Released: |  | Date completed:
Sto. Tomas | Tibal-og | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | [7 empty] | Date Started:
Sto. Tomas | Talomo | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | Compl./Rep. Day Care Center, Talomo, Sto. Tomas |  | AB CY 2020 | Building |  | sq.m |  | Project Cost: | 300000 | Target Completion Date: |  | Program: | 300000 | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
Sto. Tomas | Talomo | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 300000 | Revised: |  | No. of Man-days:
Sto. Tomas | Talomo | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Sto. Tomas | Talomo | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Sto. Tomas | Talomo | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | [7 empty] | Date Allotment Released: |  | Date completed:
Sto. Tomas | Talomo | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | [7 empty] | Date Started:
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | Compl./Rep. Day Care Center, Kinamayan, Sto. Tomas |  | AB CY 2020 | Building |  | sq.m |  | Project Cost: | 300000 | Target Completion Date: |  | Program: | 300000 | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 300000 | Revised: |  | No. of Man-days:
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | [7 empty] | Date Allotment Released: |  | Date completed:
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | [7 empty] | Date Started:
Sto. Tomas | La Libertad | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | Compl./Rep. Day Care Center, La Libertad, Sto. Tomas |  | AB CY 2020 | Building |  | sq.m |  | Project Cost: | 300000 | Target Completion Date: |  | Program: | 300000 | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
Sto. Tomas | La Libertad | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 300000 | Revised: |  | No. of Man-days:
Sto. Tomas | La Libertad | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Sto. Tomas | La Libertad | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Sto. Tomas | La Libertad | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | [7 empty] | Date Allotment Released: |  | Date completed:
Sto. Tomas | La Libertad | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | [7 empty] | Date Started:
Carmen | Ising | 2nd Eng'g. Dist. | On-going | 2020-05-11 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | BAYANIHAN | Impv't of Hospital Facilities (Isolation/ICU Room) Carmen District Hospital |  | TF CY 2020 | Building |  | sq.m | Admin | Project Cost: | 3000000 | Target Completion Date: | 2020-08-09 | Program: | 3000000 | Planned: | 30.21% | No. of Persons: | 8 | On-going
Carmen | Ising | 2nd Eng'g. Dist. | On-going | 2020-05-11 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | BAYANIHAN | [7 empty] | Project Engineer: | Estorco | Revised Completion Date: |  | Allotment: | 3000000 | Revised: |  | No. of Man-days: | 240
Carmen | Ising | 2nd Eng'g. Dist. | On-going | 2020-05-11 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | BAYANIHAN | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: | 22.72%
Carmen | Ising | 2nd Eng'g. Dist. | On-going | 2020-05-11 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | BAYANIHAN | [7 empty] | Duration: | 90 | No. of days extended: |  |  |  | Slippage: | -7.49%
Carmen | Ising | 2nd Eng'g. Dist. | On-going | 2020-05-11 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | BAYANIHAN | [7 empty] | Date Allotment Released: |  | Date completed:
Carmen | Ising | 2nd Eng'g. Dist. | On-going | 2020-05-11 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | BAYANIHAN | [7 empty] | Date Started: | 2020-05-11
Samal | Peñaplata | 2nd Eng'g. Dist. | On-going | 2020-05-11 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | BAYANIHAN | Impv't of Hospital Facilities (Isolation/ICU Room) Samal District Hospital |  | TF CY 2020 | Building |  | sq.m | Admin | Project Cost: | 1000000 | Target Completion Date: | 2020-08-09 | Program: | 1000000 | Planned: | 30.12% | No. of Persons: | 6 | On-going
Samal | Peñaplata | 2nd Eng'g. Dist. | On-going | 2020-05-11 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | BAYANIHAN | [7 empty] | Project Engineer: | Porras/Obar | Revised Completion Date: |  | Allotment: | 1000000 | Revised: |  | No. of Man-days: | 60
Samal | Peñaplata | 2nd Eng'g. Dist. | On-going | 2020-05-11 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | BAYANIHAN | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: | 50.17%
Samal | Peñaplata | 2nd Eng'g. Dist. | On-going | 2020-05-11 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | BAYANIHAN | [7 empty] | Duration: | 90 | No. of days extended: |  |  |  | Slippage: | 20.05%
Samal | Peñaplata | 2nd Eng'g. Dist. | On-going | 2020-05-11 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | BAYANIHAN | [7 empty] | Date Allotment Released: |  | Date completed:
Samal | Peñaplata | 2nd Eng'g. Dist. | On-going | 2020-05-11 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | BAYANIHAN | [7 empty] | Date Started: | 2020-05-11
Carmen | Ising | 2nd Eng'g. Dist. | On-going | 2020-05-11 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | BAYANIHAN | Rehab of DavNor Pharmacy into Isolation Room Phase I |  | TF CY 2020 | Building |  | sq.m | Admin | Project Cost: | 1480000 | Target Completion Date: | 2020-07-20 | Program: | 1480000 | Planned: | 63.38% | No. of Persons: | 10 | On-going
Carmen | Ising | 2nd Eng'g. Dist. | On-going | 2020-05-11 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | BAYANIHAN | [7 empty] | Project Engineer: | Andoy | Revised Completion Date: |  | Allotment: | 1480000 | Revised: |  | No. of Man-days: | 260
Carmen | Ising | 2nd Eng'g. Dist. | On-going | 2020-05-11 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | BAYANIHAN | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: | 1137930.67 | Actual: | 88.68%
Carmen | Ising | 2nd Eng'g. Dist. | On-going | 2020-05-11 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | BAYANIHAN | [7 empty] | Duration: | 83 | No. of days extended: |  |  |  | Slippage: | 25.3%
Carmen | Ising | 2nd Eng'g. Dist. | On-going | 2020-05-11 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | BAYANIHAN | [7 empty] | Date Allotment Released: |  | Date completed:
Carmen | Ising | 2nd Eng'g. Dist. | On-going | 2020-05-11 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | BAYANIHAN | [7 empty] | Date Started: | 2020-04-28
Carmen | Ising | 2nd Eng'g. Dist. | On-going | 2020-05-11 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | BAYANIHAN | Rehab of DavNor Pharmacy into Isolation Room Phase II |  | TF CY 2020 | Building |  | sq.m | Admin | Project Cost: | 1000000 | Target Completion Date: | 2020-07-24 | Program: | 1000000 | Planned: | 36.42% | No. of Persons: | 6 | On-going
Carmen | Ising | 2nd Eng'g. Dist. | On-going | 2020-05-11 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | BAYANIHAN | [7 empty] | Project Engineer: | Andoy | Revised Completion Date: |  | Allotment: | 1000000 | Revised: |  | No. of Man-days: | 132
Carmen | Ising | 2nd Eng'g. Dist. | On-going | 2020-05-11 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | BAYANIHAN | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: | 664107.16 | Actual: | 32.01%
Carmen | Ising | 2nd Eng'g. Dist. | On-going | 2020-05-11 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | BAYANIHAN | [7 empty] | Duration: | 74 | No. of days extended: |  |  |  | Slippage: | -4.41%
Carmen | Ising | 2nd Eng'g. Dist. | On-going | 2020-05-11 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | BAYANIHAN | [7 empty] | Date Allotment Released: |  | Date completed:
Carmen | Ising | 2nd Eng'g. Dist. | On-going | 2020-05-11 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | BAYANIHAN | [7 empty] | Date Started: | 2020-05-11

## C (hidden)
[12 empty] | 245.83 |  |  |  | 156993135.14 |  |  |  | 392138703.98 |  |  |  | 12802
[8 empty] | SECTOR: | ECONOMIC (INFRASTRUCTURE DEV'T. PROGRAM)
[8 empty] | OFFICE/AGENCY: | PROVINCIAL ENGINEER'S OFFICE
[8 empty] | AREA: | 2ND ENGINEERING DISTRICT - COMPLETED, ON-GOING AND FOR IMPLEMENTATION PROJECTS
I. PROJECTS UNDER THE CONTINUING APPROPRIATION
CMGP
MUNICIPALITY | BARANGAY | AREA | COMPLETED/ ON-GOING/ FOR IMPLEMENTATION/ SUSPENDED | DATE STARTED | DATE COMPLETED | APPRO- PRIATION | NOMEN- CLATURE | NAME OF PROJECT |  | SOURCE OF FUND | TYPE OF PROJECT | PHYSICAL TARGET (DESCRIPTION) |  | MODE OF IMPLEMENTATION | PROJECT DATA |  |  |  | FINANCIAL |  | PHYSICAL ACCOMPLISHMENT |  | EMPLOYMENT GENERATED |  | REMARKS
San Isidro | Sagayen | 1st Eng'g. Dist. | Completed | 2018-10-01 | 2020-04-02 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CMGP | Road upgrading Km. 9 Sagayen-Sawata (Sagayen-Jct. San Miguel Section) |  | CMGP CY 2017 | Road Concreting | 10.2 | km | Contract | Project Cost: | 139761975.14 | Target Completion Date: | 2019-08-22 23:46 | Program: | 139761975.14 | Planned: | 100% | No. of Persons: | 28 | Completed as per physical accomplishment. Financial documents still on process.
San Isidro | Sagayen | 1st Eng'g. Dist. | Completed | 2018-10-01 | 2020-04-02 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CMGP | [7 empty] | Project Engineer: | Avila | Revised Completion Date: | 2019-08-22 23:46 | Allotment: | 139761975.14 | Revised: |  | No. of Man-days: | 11170
San Isidro | Sagayen | 1st Eng'g. Dist. | Completed | 2018-10-01 | 2020-04-02 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CMGP | [7 empty] | Implementor: | Legacy Const. Corp. | No. of days suspended: | 209 | Disbursement: | 63100753.7 | Actual: | 100%
San Isidro | Sagayen | 1st Eng'g. Dist. | Completed | 2018-10-01 | 2020-04-02 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CMGP | [7 empty] | Duration: | 326 | No. of days extended: |  |  |  | Slippage: | 0%
San Isidro | Sagayen | 1st Eng'g. Dist. | Completed | 2018-10-01 | 2020-04-02 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CMGP | [7 empty] | Date Allotment Released: | CY 2017 | Date completed: | 2020-04-02
San Isidro | Sagayen | 1st Eng'g. Dist. | Completed | 2018-10-01 | 2020-04-02 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CMGP | [7 empty] | Date Started: | 2018-10-01
San Isidro | Sto. Niño | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-05-27 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | Rehab. Of Multi-Purpose Hall , Sto. Niño, San Isidro |  | 20% DF CY 2019 (STIMULUS) | Building | 182 | sq.m | Admin | Project Cost: | 500000 | Target Completion Date: | 2020-02-19 23:46 | Program: | 500000 | Planned: | 100% | No. of Persons: | 6 | Completed as per physical accomplishment. Financial documents still on process
San Isidro | Sto. Niño | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-05-27 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Project Engineer: | Aclaracion | Revised Completion Date: | 2020-02-19 23:46 | Allotment: | 500000 | Revised: |  | No. of Man-days: | 132
San Isidro | Sto. Niño | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-05-27 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Implementor: | PEO | No. of days suspended: | 28 | Disbursement: | 500000 | Actual: | 100%
San Isidro | Sto. Niño | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-05-27 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Duration: | 45 | No. of days extended: |  |  |  | Slippage: | 0%
San Isidro | Sto. Niño | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-05-27 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Allotment Released: | 2019-02-20 | Date completed: | 2020-05-27
San Isidro | Sto. Niño | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-05-27 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Started: | 2020-01-06
Tagum City | San Isidro | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-06-05 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | Const. of Women Livelihood Center, San Isidro, Tagum City |  | 20% DF CY 2019 (STIMULUS) | Building | 36.5 | sq.m | Admin | Project Cost: | 500000 | Target Completion Date: | 2020-03-21 23:46 | Program: | 500000 | Planned: | 100% | No. of Persons: | 10 | Completed as per physical accomplishment. Financial documents still on process
Tagum City | San Isidro | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-06-05 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Project Engineer: | Juan | Revised Completion Date: | 2020-06-05 23:46 | Allotment: | 500000 | Revised: | 100% | No. of Man-days: | 150
Tagum City | San Isidro | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-06-05 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Implementor: | PEO | No. of days suspended: | 28 | Disbursement: |  | Actual: | 100%
Tagum City | San Isidro | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-06-05 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Duration: | 80 | No. of days extended: | 48 |  |  | Slippage: | 0%
Tagum City | San Isidro | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-06-05 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Allotment Released: | 2019-05-29 | Date completed: | 2020-06-05
Tagum City | San Isidro | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-06-05 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Started: | 2020-01-02
New Corella | Saug | 1st Eng'g. Dist. | Completed | 2019-03-26 | 2020-06-30 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES | New Corella - Saug |  | 20% DF CY 2019 | Road Rehabilitation | 12.52 | km | Contract | Project Cost: | 6500000 | Target Completion Date: | 2019-03-26 | Program: | 6500000 | Planned: | 100% | No. of Persons: | 19 | Completed as per physical accomplishment. Financial documents still on process
New Corella | Saug | 1st Eng'g. Dist. | Completed | 2019-03-26 | 2020-06-30 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES | [7 empty] | Project Engineer: | Pilotos | Revised Completion Date: | 2019-06-10 | Allotment: | 6500000 | Revised: |  | No. of Man-days: | 570
New Corella | Saug | 1st Eng'g. Dist. | Completed | 2019-03-26 | 2020-06-30 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES | [7 empty] | Implementor: | PEO | No. of days suspended: | 28 | Disbursement: | 6500000 | Actual: | 100%
New Corella | Saug | 1st Eng'g. Dist. | Completed | 2019-03-26 | 2020-06-30 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES | [7 empty] | Duration: |  | No. of days extended: | 48 |  |  | Slippage: | 0%
New Corella | Saug | 1st Eng'g. Dist. | Completed | 2019-03-26 | 2020-06-30 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES | [7 empty] | Date Allotment Released: |  | Date completed: | 2020-06-30
New Corella | Saug | 1st Eng'g. Dist. | Completed | 2019-03-26 | 2020-06-30 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES | [7 empty] | Date Started: | 2019-03-26
Asuncion | Cabaywa | 1st Eng'g. Dist. | Completed | 2019-03-26 | 2020-06-30 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES | Jct. Monte Carlo - Upper Cabaywa - Canatan |  | 20% DF CY 2019 | Road Rehabilitation | 4.61 | km | Contract | Project Cost: | 8838000 | Target Completion Date: | 2019-03-26 | Program: | 8838000 | Planned: | 100% | No. of Persons: | 19 | Completed as per physical accomplishment. Financial documents still on process
Asuncion | Cabaywa | 1st Eng'g. Dist. | Completed | 2019-03-26 | 2020-06-30 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES | [7 empty] | Project Engineer: | Garcia | Revised Completion Date: | 2019-03-26 | Allotment: | 8838000 | Revised: |  | No. of Man-days: | 570
Asuncion | Cabaywa | 1st Eng'g. Dist. | Completed | 2019-03-26 | 2020-06-30 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES | [7 empty] | Implementor: | PEO | No. of days suspended: | 28 | Disbursement: | 8838000 | Actual: | 100%
Asuncion | Cabaywa | 1st Eng'g. Dist. | Completed | 2019-03-26 | 2020-06-30 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Asuncion | Cabaywa | 1st Eng'g. Dist. | Completed | 2019-03-26 | 2020-06-30 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES | [7 empty] | Date Allotment Released: | 2019-01-31 | Date completed: | 2020-06-30
Asuncion | Cabaywa | 1st Eng'g. Dist. | Completed | 2019-03-26 | 2020-06-30 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES | [7 empty] | Date Started: | 2019-03-26
Kapalong | Mamacao | 1st Eng'g. Dist. | Completed | 2020-02-05 | 2020-06-15 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | Construction of Bleacher, Mamacao, Kapalong |  | GF CY 2018 (STIMULUS) | Bleacher |  | sq.m | Admin | Project Cost: | 500000 | Target Completion Date: | 2020-04-19 23:46 | Program: | 500000 | Planned: | 100% | No. of Persons: | 8 | Completed as per physical accomplishment. Financial documents still on process.
Kapalong | Mamacao | 1st Eng'g. Dist. | Completed | 2020-02-05 | 2020-06-15 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Project Engineer: | Ambrosio | Revised Completion Date: | 2020-06-15 23:46 | Allotment: | 500000 | Revised: |  | No. of Man-days: | 120
Kapalong | Mamacao | 1st Eng'g. Dist. | Completed | 2020-02-05 | 2020-06-15 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: |  | Actual: | 100%
Kapalong | Mamacao | 1st Eng'g. Dist. | Completed | 2020-02-05 | 2020-06-15 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Duration: | 75 | No. of days extended: | 30 |  |  | Slippage:
Kapalong | Mamacao | 1st Eng'g. Dist. | Completed | 2020-02-05 | 2020-06-15 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Date Allotment Released: |  | Date completed: | 2020-03-15 23:46
Kapalong | Mamacao | 1st Eng'g. Dist. | Completed | 2020-02-05 | 2020-06-15 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Date Started: | 2020-02-05
Kapalong | Capungagan | 1st Eng'g. Dist. | On-going | 2016-04-06 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PRDP | Rehab. Of Capungagan-Boundary San Miguel FMR, Kapalong, Davao del Norte |  | PRDP CY 2015 | Road Concreting | 10.6 | km | Contract | Project Cost: | 108303841.7 | Target Completion Date: | 2020-02-14 23:46 | Program: | 108303841.7 | Planned: | 100% | No. of Persons: | 38 | Suspended effective April 5, 2020 due to issued Executive Order No. 31, series of 2020 the province of Davao del Norte in response to the State of Public Health Emergency and State of National Calamity (COVID19 Pandemic).
Kapalong | Capungagan | 1st Eng'g. Dist. | On-going | 2016-04-06 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PRDP | [7 empty] | Project Engineer: | Nasol | Revised Completion Date: | 2023-05-24 23:46 | Allotment: | 108303841.7 | Revised: | 97.28% | No. of Man-days: | 1140
Kapalong | Capungagan | 1st Eng'g. Dist. | On-going | 2016-04-06 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PRDP | [7 empty] | Implementor: | VICLAO | No. of days suspended: | 140 | Disbursement: | 60050673.93 | Actual: | 93.8%
Kapalong | Capungagan | 1st Eng'g. Dist. | On-going | 2016-04-06 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PRDP | [7 empty] | Duration: | 1410 | No. of days extended: | 1055 |  |  | Slippage: | -3.48%
Kapalong | Capungagan | 1st Eng'g. Dist. | On-going | 2016-04-06 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PRDP | [7 empty] | Date Allotment Released: | CY 2015 | Date completed:
Kapalong | Capungagan | 1st Eng'g. Dist. | On-going | 2016-04-06 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PRDP | [7 empty] | Date Started: | 2016-04-06
New Corella | Limbaan | 1st Eng'g. Dist. | On-going | 2019-04-08 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PRDP | Rehab. Of Pob.-Limbaan-Suawon-Macgum FMR w/ Bridge (42 ln.m), New Corella, Davao del Norte |  | PRDP CY 2015 | Road Concreting | 15.01 | km | Contract | Project Cost: | 205202114.16 | Target Completion Date: | 2019-01-18 | Program: | 205202114.16 | Planned: | 100% | No. of Persons: | 40 | On-going (Increase of Project Cost due to Variation Order Php 14,948,622.18, Partial suspension due to soft soil from sta. 8+000 - 10+000); (Suspended last April 5, 2020 due to COVID; Resumption Order dated June 1, 2020)
New Corella | Limbaan | 1st Eng'g. Dist. | On-going | 2019-04-08 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PRDP | [7 empty] | Project Engineer: | Madrigal | Revised Completion Date: | 2021-01-06 | Allotment: | 205202114.16 | Revised: | 83.77% | No. of Man-days: | 1200
New Corella | Limbaan | 1st Eng'g. Dist. | On-going | 2019-04-08 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PRDP | [7 empty] | Implementor: | Dvo. Rock Mixer | No. of days suspended: | 229 | Disbursement: | 141497191.47 | Actual: | 77.49%
New Corella | Limbaan | 1st Eng'g. Dist. | On-going | 2019-04-08 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PRDP | [7 empty] | Duration: | 1529 | No. of days extended: | 490 |  |  | Slippage: | -6.282%
New Corella | Limbaan | 1st Eng'g. Dist. | On-going | 2019-04-08 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PRDP | [7 empty] | Date Allotment Released: | CY 2015 | Date completed:
New Corella | Limbaan | 1st Eng'g. Dist. | On-going | 2019-04-08 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PRDP | [7 empty] | Date Started: | 2016-04-08
Asuncion | Sonlon-Camansa | 1st Eng'g. Dist. | On-going | 2019-03-28 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PRDP | Rehab. Of Sonlon - Camansa FMR Asuncion, Davao del Norte |  | PRDP CY 2015 | Road Concreting | 10.23 | km | Contract | Project Cost: | 215125015.81 | Target Completion Date: | 2020-06-15 | Program: | 215125015.81 | Planned: | 39.51% | No. of Persons: | 30 | On-going (Suspended last April 5, 2020 due to COVID; Resumption Order dated June 1, 2020)
Asuncion | Sonlon-Camansa | 1st Eng'g. Dist. | On-going | 2019-03-28 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PRDP | [7 empty] | Project Engineer: | Fabiala | Revised Completion Date: | 2020-06-15 | Allotment: | 215125015.81 | Revised: |  | No. of Man-days: | 780
Asuncion | Sonlon-Camansa | 1st Eng'g. Dist. | On-going | 2019-03-28 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PRDP | [7 empty] | Implementor: | Three w/Builders, Inc/Davao Rock Mixer Enterprises (JV) | No. of days suspended: |  | Disbursement: | 40523099.23 | Actual: | 31.6%
Asuncion | Sonlon-Camansa | 1st Eng'g. Dist. | On-going | 2019-03-28 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PRDP | [7 empty] | Duration: | 384 | No. of days extended: |  |  |  | Slippage: | -7.91%
Asuncion | Sonlon-Camansa | 1st Eng'g. Dist. | On-going | 2019-03-28 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PRDP | [7 empty] | Date Allotment Released: | 2018-09-18 | Date completed:
Asuncion | Sonlon-Camansa | 1st Eng'g. Dist. | On-going | 2019-03-28 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PRDP | [7 empty] | Date Started: | 2019-05-28
Kapalong | Capungagan | 1st Eng'g. Dist. | On-going | 2019-03-19 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PRDP | Cacao Production and Beans Marketing, Capungagan, Kapalong, Davao del Norte |  | PRDP CY 2016 | Building | 3610 | sq.m | Contract | Project Cost: | 5873626.8 | Target Completion Date: | 2019-11-24 | Program: | 5873626.8 | Planned: | 100% | No. of Persons: |  | Suspended due to modification of Detailed Design of mechanical Drier dated November 23, 2019; Waiting for the resumption order from DA.
Kapalong | Capungagan | 1st Eng'g. Dist. | On-going | 2019-03-19 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PRDP | [7 empty] | Project Engineer: | Delos Reyes | Revised Completion Date: | 2019-11-24 | Allotment: | 5873626.8 | Revised: |  | No. of Man-days:
Kapalong | Capungagan | 1st Eng'g. Dist. | On-going | 2019-03-19 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PRDP | [7 empty] | Implementor: | MICAH CONST. & SUPPLY | No. of days suspended: |  | Disbursement: | 4698901.44 | Actual: | 91.09%
Kapalong | Capungagan | 1st Eng'g. Dist. | On-going | 2019-03-19 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PRDP | [7 empty] | Duration: | 250 | No. of days extended: |  |  |  | Slippage: | -8.905%
Kapalong | Capungagan | 1st Eng'g. Dist. | On-going | 2019-03-19 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PRDP | [7 empty] | Date Allotment Released: | CY 2016 | Date completed:
Kapalong | Capungagan | 1st Eng'g. Dist. | On-going | 2019-03-19 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PRDP | [7 empty] | Date Started: | 2019-03-19
New Corella | Poblacion | 1st Eng'g. Dist. | On-going | 2019-01-17 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PRDP | Improvement of New Corella Nursery with Organic Input Production & Common Facility, Davao del Norte |  | PRDP CY 2016 | Building | 1901 | sq.m | Contract | Project Cost: | 9889628.45 | Target Completion Date: | 2019-11-23 | Program: | 9889628.45 | Planned: | 80.36% | No. of Persons: | 10 | On-going (Suspended last April 5, 2020 due to COVID; Resumption Order dated June 1, 2020)
New Corella | Poblacion | 1st Eng'g. Dist. | On-going | 2019-01-17 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PRDP | [7 empty] | Project Engineer: | Delos Reyes/Cabañero | Revised Completion Date: | 2020-08-09 | Allotment: | 9889628.45 | Revised: | 49.99% | No. of Man-days: | 250
New Corella | Poblacion | 1st Eng'g. Dist. | On-going | 2019-01-17 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PRDP | [7 empty] | Implementor: | SOUTH IRONROCK CORPORATION | No. of days suspended: | 260 | Disbursement: |  | Actual: | 46.3%
New Corella | Poblacion | 1st Eng'g. Dist. | On-going | 2019-01-17 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PRDP | [7 empty] | Duration: | 310 | No. of days extended: |  |  |  | Slippage: | -3.684%
New Corella | Poblacion | 1st Eng'g. Dist. | On-going | 2019-01-17 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PRDP | [7 empty] | Date Allotment Released: | CY 2016 | Date completed:
New Corella | Poblacion | 1st Eng'g. Dist. | On-going | 2019-01-17 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PRDP | [7 empty] | Date Started: | 2019-01-17
Tagum City | Pandapan | 1st Eng'g. Dist. | On-going |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPPAP-PAMANA | Const. of Trading Post, Storage Building with (1) unit Hauling Truck, Brgy. Pandapan |  | OPPAP-PAMANA CY 2017 | Building |  | sq.m | Contract | Project Cost: | 3975000 | Target Completion Date: | 0 | Program: | 3975000 | Planned: |  | No. of Persons: |  | Abstract 1220194004 (Tagum Builders);PO # 2019102828 - Truck
Tagum City | Pandapan | 1st Eng'g. Dist. | On-going |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPPAP-PAMANA | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 3975000 | Revised: |  | No. of Man-days:
Tagum City | Pandapan | 1st Eng'g. Dist. | On-going |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPPAP-PAMANA | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Tagum City | Pandapan | 1st Eng'g. Dist. | On-going |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPPAP-PAMANA | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Tagum City | Pandapan | 1st Eng'g. Dist. | On-going |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPPAP-PAMANA | [7 empty] | Date Allotment Released: | CY 2017 | Date completed:
Tagum City | Pandapan | 1st Eng'g. Dist. | On-going |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPPAP-PAMANA | [7 empty] | Date Started:
Kapalong |  | 1st Eng'g. Dist. | On-going | 2016-06-01 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPPAP-PAMANA | Construction of Biga Bridges, Kapalong (Original Contract Cost: P 24,959,503.45; Variation Order: P 4,067,412.00) |  | OPPAP-PAMANA CY 2014 | Road |  | km | Contract | Project Cost: | 29026915.45 | Target Completion Date: | 2018-07-30 23:59 | Program: | 29026915.45 | Planned: | 100% | No. of Persons: | 8 | Suspended due to RROW
Kapalong |  | 1st Eng'g. Dist. | On-going | 2016-06-01 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPPAP-PAMANA | [7 empty] | Project Engineer: | Limpo | Revised Completion Date: | 2020-03-25 23:59 | Allotment: | 29026915.45 | Revised: | 99.7% | No. of Man-days: | 290
Kapalong |  | 1st Eng'g. Dist. | On-going | 2016-06-01 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPPAP-PAMANA | [7 empty] | Implementor: | Davao Rock Mixer | No. of days suspended: | 604 | Disbursement: | 18489834.55 | Actual: | 85.37%
Kapalong |  | 1st Eng'g. Dist. | On-going | 2016-06-01 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPPAP-PAMANA | [7 empty] | Duration: | 760 | No. of days extended: |  |  |  | Slippage: | -14.33%
Kapalong |  | 1st Eng'g. Dist. | On-going | 2016-06-01 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPPAP-PAMANA | [7 empty] | Date Allotment Released: | CY 2014 | Date completed:
Kapalong |  | 1st Eng'g. Dist. | On-going | 2016-06-01 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPPAP-PAMANA | [7 empty] | Date Started: | 2016-07-01
Asuncion | Canatan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | QRF | Repair of Damaged Drainage/Creeks of Canatan, Asuncion |  | QRF CY 2015 & 2016 | Drainage/Creeks |  | km |  | Project Cost: | 137754.69 | Target Completion Date: | 0 | Program: | 137754.69 | Planned: |  | No. of Persons: |  | PO#2020061983 - FL2 LUMBER & CONST. SUPPLY; PO #2020062164 - jkle enterprises
Asuncion | Canatan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | QRF | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 137754.69 | Revised: |  | No. of Man-days:
Asuncion | Canatan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | QRF | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Asuncion | Canatan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | QRF | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Asuncion | Canatan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | QRF | [7 empty] | Date Allotment Released: |  | Date completed:
Asuncion | Canatan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | QRF | [7 empty] | Date Started:
Asuncion | Sagayen | 1st Eng'g. Dist. | On-going | 2018-11-15 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | QRF | Construction of Water Reservoir & Purchase of P.E. Pipelines, Sagayen, Asuncion |  | 20% DF CY 2017 (STIMULUS) | Water System |  |  | MLGU | Project Cost: | 500000 | Target Completion Date: | 2018-11-15 | Program: | 500000 | Planned: | 90% | No. of Persons: |  | Suspended due to non availability of water source during drilling.Find another location. Fund already transferred at Municipality of Asuncion with ChecK No. 2445174 and OR # 9238468,
Asuncion | Sagayen | 1st Eng'g. Dist. | On-going | 2018-11-15 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | QRF | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Asuncion | Sagayen | 1st Eng'g. Dist. | On-going | 2018-11-15 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | QRF | [7 empty] | Implementor: | MEO | No. of days suspended: |  | Disbursement: |  | Actual: | 90%
Asuncion | Sagayen | 1st Eng'g. Dist. | On-going | 2018-11-15 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | QRF | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Asuncion | Sagayen | 1st Eng'g. Dist. | On-going | 2018-11-15 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | QRF | [7 empty] | Date Allotment Released: | 2017-12-28 | Date completed:
Asuncion | Sagayen | 1st Eng'g. Dist. | On-going | 2018-11-15 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | QRF | [7 empty] | Date Started: | 2018-11-15
New Corella | Sta. Fe | 1st Eng'g. Dist. | On-going |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2017 | Road Rehabilitation at Prk. 1-Prk. 5, Sta. Fe, New Corella |  | 20% DF CY 2017 (STIMULUS) | Court |  |  | MLGU | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Fund already transferred at Municipality of Talaingod with ChecK No. 2445181 and OR # 7955667, dated March 16, 2018 . Amended from Electrification @ Prk. 1A-Prk. 5A)
New Corella | Sta. Fe | 1st Eng'g. Dist. | On-going |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2017 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 500000 | Revised: |  | No. of Man-days:
New Corella | Sta. Fe | 1st Eng'g. Dist. | On-going |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2017 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
New Corella | Sta. Fe | 1st Eng'g. Dist. | On-going |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2017 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | Sta. Fe | 1st Eng'g. Dist. | On-going |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2017 | [7 empty] | Date Allotment Released: | 2017-12-28 | Date completed:
New Corella | Sta. Fe | 1st Eng'g. Dist. | On-going |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2017 | [7 empty] | Date Started:
Talaingod | Palma Gil | 1st Eng'g. Dist. | On-going |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2017 | Const. of Covered Court Bleacher, Palma Gil, Talaingod |  | 20% DF CY 2017 | Court |  |  | MLGU | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | On-going (Fund already transferred at Municipality of Talaingod with ChecK No. 2445181 and OR # 7955667, dated March 16, 2018 . Amended from Electrification @ Prk. 1A-Prk. 5A
Talaingod | Palma Gil | 1st Eng'g. Dist. | On-going |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2017 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 500000 | Revised: |  | No. of Man-days:
Talaingod | Palma Gil | 1st Eng'g. Dist. | On-going |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2017 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Talaingod | Palma Gil | 1st Eng'g. Dist. | On-going |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2017 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Talaingod | Palma Gil | 1st Eng'g. Dist. | On-going |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2017 | [7 empty] | Date Allotment Released: | 2017-12-28 | Date completed:
Talaingod | Palma Gil | 1st Eng'g. Dist. | On-going |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2017 | [7 empty] | Date Started:
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2019-11-04 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./REHAB./COMP. OF VARIOUS GOV'T. BLDGS. STRUCT., FAC (Provincewide) LS - P9,000,000.00 | Rehab. Of PEO Training Center, (PDPM),Mankilam, Tagum City, (Part of P803,000.00)(20% DF CY 2018-P326,124.00) |  | 20% DF CY 2017 | Building | 85 | sq.m | Admin | Project Cost: | 476876 | Target Completion Date: | 2020-01-17 | Program: | 476876 | Planned: | 99% | No. of Persons: | 3 | Suspended (additional PR for Elect. Mat.) dated March 9, 2020
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2019-11-04 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./REHAB./COMP. OF VARIOUS GOV'T. BLDGS. STRUCT., FAC (Provincewide) LS - P9,000,000.00 | [7 empty] | Project Engineer: | Chua | Revised Completion Date: | 2020-03-15 | Allotment: | 476876 | Revised: |  | No. of Man-days: | 57
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2019-11-04 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./REHAB./COMP. OF VARIOUS GOV'T. BLDGS. STRUCT., FAC (Provincewide) LS - P9,000,000.00 | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: | 407521.7 | Actual: | 99%
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2019-11-04 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./REHAB./COMP. OF VARIOUS GOV'T. BLDGS. STRUCT., FAC (Provincewide) LS - P9,000,000.00 | [7 empty] | Duration: | 74 | No. of days extended: | 58 |  |  | Slippage: | 0%
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2019-11-04 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./REHAB./COMP. OF VARIOUS GOV'T. BLDGS. STRUCT., FAC (Provincewide) LS - P9,000,000.00 | [7 empty] | Date Allotment Released: | 2019-02-12 | Date completed:
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2019-11-04 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./REHAB./COMP. OF VARIOUS GOV'T. BLDGS. STRUCT., FAC (Provincewide) LS - P9,000,000.00 | [7 empty] | Date Started: | 2019-11-04
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2018-07-17 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./REHAB./COMP. OF VARIOUS GOV'T. BLDGS. STRUCT., FAC (Provincewide) LS - P9,000,000.00 | Upgrading of DDNSTC (Basketball/Voleyball MP Covered Court),Sports Center, Mankilam, Tagum City |  | SB # 4 CY 2017 | Covered Court | 2252.69 | sq.m | Contract | Project Cost: | 99992356.64 | Target Completion Date: | 2019-07-11 | Program: | 99992356.64 | Planned: | 100% | No. of Persons: | 10 | On-going (Suspended last April 5, 2020 due to COVID; Resumption Order dated May 4, 2020)
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2018-07-17 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./REHAB./COMP. OF VARIOUS GOV'T. BLDGS. STRUCT., FAC (Provincewide) LS - P9,000,000.00 | [7 empty] | Project Engineer: | Daral | Revised Completion Date: |  | Allotment: | 99992356.64 | Revised: |  | No. of Man-days: | 310
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2018-07-17 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./REHAB./COMP. OF VARIOUS GOV'T. BLDGS. STRUCT., FAC (Provincewide) LS - P9,000,000.00 | [7 empty] | Implementor: | YBC | No. of days suspended: |  | Disbursement: | 18280402.33 | Actual: | 73.04%
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2018-07-17 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./REHAB./COMP. OF VARIOUS GOV'T. BLDGS. STRUCT., FAC (Provincewide) LS - P9,000,000.00 | [7 empty] | Duration: | 360 | No. of days extended: | 20 |  |  | Slippage: | -26.96%
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2018-07-17 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./REHAB./COMP. OF VARIOUS GOV'T. BLDGS. STRUCT., FAC (Provincewide) LS - P9,000,000.00 | [7 empty] | Date Allotment Released: | 2018-10-16 | Date completed:
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2018-07-17 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./REHAB./COMP. OF VARIOUS GOV'T. BLDGS. STRUCT., FAC (Provincewide) LS - P9,000,000.00 | [7 empty] | Date Started: | 2018-07-17
Asuncion | Saug | 1st Eng'g. Dist. | On-going | 2019-01-03 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | QRF | Rehab. Of Saug Bridge of Slope Protection |  | QRF CY 2017 | Slope Protection | 356.4 | ln.m | Admin | Project Cost: | 4850000 | Target Completion Date: | 2019-05-02 23:46 | Program: | 4850000 | Planned: | 74.56% | No. of Persons: | 13 | On-going (Suspended dated January 28, 2019; Resumption February 3, 2020; Resumption Order dated May 4, 2020; Suspended last April 5, 2020 due to COVID; resumption order dated May 4, 2020)
Asuncion | Saug | 1st Eng'g. Dist. | On-going | 2019-01-03 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | QRF | [7 empty] | Project Engineer: | Gone | Revised Completion Date: | 2020-08-19 23:46 | Allotment: | 4850000 | Revised: |  | No. of Man-days: | 195
Asuncion | Saug | 1st Eng'g. Dist. | On-going | 2019-01-03 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | QRF | [7 empty] | Implementor: | PEO | No. of days suspended: | 400 | Disbursement: | 1628912.92 | Actual: | 71.13%
Asuncion | Saug | 1st Eng'g. Dist. | On-going | 2019-01-03 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | QRF | [7 empty] | Duration: | 120 | No. of days extended: | 75 |  |  | Slippage: | -3.43%
Asuncion | Saug | 1st Eng'g. Dist. | On-going | 2019-01-03 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | QRF | [7 empty] | Date Allotment Released: | 2018-05-25 | Date completed:
Asuncion | Saug | 1st Eng'g. Dist. | On-going | 2019-01-03 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | QRF | [7 empty] | Date Started: | 2019-01-03
Kapalong | Gupitan | 1st Eng'g. Dist. | On-going | 2019-02-22 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | QRF | Re-channeling of BIGA River with Earth Dike and Slope Protection, Brgy. Gupitan, Kaplaong |  | QRF CY 2017 | Slope Protection | 0.9 | ln.m | Contract | Project Cost: | 12100000 | Target Completion Date: | 2019-06-11 23:46 | Program: | 12100000 | Planned: | 8.3% | No. of Persons: | 4 | On-going (Suspended last April 5, 2020 due to COVID; resumption order dated May 4, 2020)
Kapalong | Gupitan | 1st Eng'g. Dist. | On-going | 2019-02-22 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | QRF | [7 empty] | Project Engineer: | Limpo | Revised Completion Date: | 2019-06-11 23:46 | Allotment: | 12100000 | Revised: |  | No. of Man-days: | 120
Kapalong | Gupitan | 1st Eng'g. Dist. | On-going | 2019-02-22 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | QRF | [7 empty] | Implementor: | Alpha & Omega | No. of days suspended: |  | Disbursement: |  | Actual: | 3.36%
Kapalong | Gupitan | 1st Eng'g. Dist. | On-going | 2019-02-22 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | QRF | [7 empty] | Duration: | 110 | No. of days extended: |  |  |  | Slippage: | -4.94%
Kapalong | Gupitan | 1st Eng'g. Dist. | On-going | 2019-02-22 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | QRF | [7 empty] | Date Allotment Released: | 2018-07-20 | Date completed:
Kapalong | Gupitan | 1st Eng'g. Dist. | On-going | 2019-02-22 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | QRF | [7 empty] | Date Started: | 2019-02-22
San Isidro | Linao | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | WATER SYSTEM LS - P 10,000,000.00 | Const. of PWS Linao, San Isidro |  | 20% DF CY 2018 | geo-resistivty/drillig |  |  | Admin | Project Cost: | 62000 | Target Completion Date: |  | Program: | 62000 | Planned: |  | No. of Persons: |  | For implementation
San Isidro | Linao | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | WATER SYSTEM LS - P 10,000,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 62000 | Revised: |  | No. of Man-days:
San Isidro | Linao | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | WATER SYSTEM LS - P 10,000,000.00 | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual:
San Isidro | Linao | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | WATER SYSTEM LS - P 10,000,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
San Isidro | Linao | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | WATER SYSTEM LS - P 10,000,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
San Isidro | Linao | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | WATER SYSTEM LS - P 10,000,000.00 | [7 empty] | Date Started:
San Isidro | Mamalian | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | WATER SYSTEM LS - P 10,000,000.00 | Const. of PWS Mamalian, San Isidro |  | 20% DF CY 2018 | geo-resistivty/drillig |  |  | Admin | Project Cost: | 62000 | Target Completion Date: |  | Program: | 62000 | Planned: |  | No. of Persons: |  | For declaration of savings because the spring water source is not feasible for development.
San Isidro | Mamalian | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | WATER SYSTEM LS - P 10,000,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 62000 | Revised: |  | No. of Man-days:
San Isidro | Mamalian | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | WATER SYSTEM LS - P 10,000,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
San Isidro | Mamalian | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | WATER SYSTEM LS - P 10,000,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
San Isidro | Mamalian | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | WATER SYSTEM LS - P 10,000,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
San Isidro | Mamalian | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | WATER SYSTEM LS - P 10,000,000.00 | [7 empty] | Date Started:
San Isidro | Sagayen | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | WATER SYSTEM LS - P 10,000,000.00 | Const. of PWS Sagayen, San Isidro |  | 20% DF CY 2018 | geo-resistivty/drillig |  |  | Admin | Project Cost: | 62000 | Target Completion Date: |  | Program: | 62000 | Planned: |  | No. of Persons: |  | For implementation
San Isidro | Sagayen | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | WATER SYSTEM LS - P 10,000,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 62000 | Revised: |  | No. of Man-days:
San Isidro | Sagayen | 1st Eng'g. Dist. | For Implementation |  | 0 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | WATER SYSTEM LS - P 10,000,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
San Isidro | Sagayen | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | WATER SYSTEM LS - P 10,000,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
San Isidro | Sagayen | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | WATER SYSTEM LS - P 10,000,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
San Isidro | Sagayen | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | WATER SYSTEM LS - P 10,000,000.00 | [7 empty] | Date Started:
Tagum City | Pandapan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | WATER SYSTEM LS - P 10,000,000.00 | Installation of potable water System at Purok Nangka, Pandapan, Tagum City |  | 20% DF CY 2018 | Water System |  |  | Admin | Project Cost: | 1125000 | Target Completion Date: |  | Program: | 1125000 | Planned: |  | No. of Persons: |  | Waiting for deed of donation. Follow-up letter was already issued
Tagum City | Pandapan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | WATER SYSTEM LS - P 10,000,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 1125000 | Revised: |  | No. of Man-days:
Tagum City | Pandapan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | WATER SYSTEM LS - P 10,000,000.00 | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual:
Tagum City | Pandapan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | WATER SYSTEM LS - P 10,000,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Tagum City | Pandapan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | WATER SYSTEM LS - P 10,000,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Tagum City | Pandapan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | WATER SYSTEM LS - P 10,000,000.00 | [7 empty] | Date Started:
Asuncion | San Vicente | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | WATER SYSTEM LS - P 10,000,000.00 | Rehab./Impv't. of San Vicente Water System, Asuncion |  | 20% DF CY 2018 | Water System |  |  | Admin | Project Cost: | 1125000 | Target Completion Date: |  | Program: | 1125000 | Planned: |  | No. of Persons: |  | Abstract # 0220190484 still draft
Asuncion | San Vicente | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | WATER SYSTEM LS - P 10,000,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 1125000 | Revised: |  | No. of Man-days:
Asuncion | San Vicente | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | WATER SYSTEM LS - P 10,000,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Asuncion | San Vicente | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | WATER SYSTEM LS - P 10,000,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Asuncion | San Vicente | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | WATER SYSTEM LS - P 10,000,000.00 | [7 empty] | Date Allotment Released: | 2018-10-26 | Date completed:
Asuncion | San Vicente | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | WATER SYSTEM LS - P 10,000,000.00 | [7 empty] | Date Started:
Asuncion | Sonlon-Camansa | 1st Eng'g. Dist. | On-going | 2019-05-28 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PRDP | Rehab. Of Sonlon-Camansa FMR, Asuncion, Davao del Norte (PRDP Counterpart : 193,612,514.23) |  | 20% DF CY 2018 | Road Concreting | 10.23 | km | Contract | Project Cost: | 21512501.5 | Target Completion Date: | 2020-06-14 23:46 | Program: | 21512501.5 | Planned: | 39.51% | No. of Persons: | 30 | On-going
Asuncion | Sonlon-Camansa | 1st Eng'g. Dist. | On-going | 2019-05-28 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PRDP | [7 empty] | Project Engineer: | Fabiala | Revised Completion Date: | 2020-06-14 23:46 | Allotment: | 21512501.5 | Revised: |  | No. of Man-days: | 690
Asuncion | Sonlon-Camansa | 1st Eng'g. Dist. | On-going | 2019-05-28 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PRDP | [7 empty] | Implementor: | Three w/Builders, Inc/Davao Rock Mixer Enterprises (JV) | No. of days suspended: |  | Disbursement: | 4502566.58 | Actual: | 31.6%
Asuncion | Sonlon-Camansa | 1st Eng'g. Dist. | On-going | 2019-05-28 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PRDP | [7 empty] | Duration: | 384 | No. of days extended: |  |  |  | Slippage: | -7.91%
Asuncion | Sonlon-Camansa | 1st Eng'g. Dist. | On-going | 2019-05-28 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PRDP | [7 empty] | Date Allotment Released: | 2018-09-18 | Date completed:
Asuncion | Sonlon-Camansa | 1st Eng'g. Dist. | On-going | 2019-05-28 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PRDP | [7 empty] | Date Started: | 2019-05-28
San Isidro | Sagayen-Sawata | 1st Eng'g. Dist. | On-going | 2019-09-09 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | KALSADA | Impvt. of Km. 9 Sagayen - Sawata Provincial Road Phase II |  | 20% DF CY 2018 | Road Concreting | 1.303 | km | Admin | Project Cost: | 7742775.95 | Target Completion Date: | 2020-03-27 | Program: | 7742775.95 | Planned: | 45% | No. of Persons: | 6 | Suspended dated March 6, 2020 due to delay delivery of materials
San Isidro | Sagayen-Sawata | 1st Eng'g. Dist. | On-going | 2019-09-09 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | KALSADA | [7 empty] | Project Engineer: | Kenny | Revised Completion Date: |  | Allotment: | 7742775.95 | Revised: |  | No. of Man-days: | 138
San Isidro | Sagayen-Sawata | 1st Eng'g. Dist. | On-going | 2019-09-09 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | KALSADA | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: | 2603417.9455 | Actual: | 35.05%
San Isidro | Sagayen-Sawata | 1st Eng'g. Dist. | On-going | 2019-09-09 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | KALSADA | [7 empty] | Duration: | 200 | No. of days extended: |  |  |  | Slippage: | -9.95%
San Isidro | Sagayen-Sawata | 1st Eng'g. Dist. | On-going | 2019-09-09 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | KALSADA | [7 empty] | Date Allotment Released: | 2019-01-31 | Date completed:
San Isidro | Sagayen-Sawata | 1st Eng'g. Dist. | On-going | 2019-09-09 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | KALSADA | [7 empty] | Date Started: | 2019-09-09
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2019-11-04 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./REHAB./COMP. OF VARIOUS GOV'T. BLDGS. STRUCT., FAC (Provincewide) LS - LS - P13,523,124.00 | Rehab. Of PEO Training Center, (PDPM),Mankilam, Tagum City (Part of P803,000.00)(20% DF CY 2017-P476,876.00) |  | 20% DF CY 2018 | Building | 85 | sq.m | Admin | Project Cost: | 326124 | Target Completion Date: | 2020-01-17 | Program: | 326124 | Planned: |  | No. of Persons: |  | suspended due to additional materials for electrical works
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2019-11-04 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./REHAB./COMP. OF VARIOUS GOV'T. BLDGS. STRUCT., FAC (Provincewide) LS - P13,523,124.00 | [7 empty] | Project Engineer: | Chua | Revised Completion Date: | 2020-03-14 | Allotment: | 326124 | Revised: |  | No. of Man-days:
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2019-11-04 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./REHAB./COMP. OF VARIOUS GOV'T. BLDGS. STRUCT., FAC (Provincewide) LS - P13,523,124.00 | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual:
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2019-11-04 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./REHAB./COMP. OF VARIOUS GOV'T. BLDGS. STRUCT., FAC (Provincewide) LS - P13,523,124.00 | [7 empty] | Duration: | 74 | No. of days extended: | 57 |  |  | Slippage: | 0%
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2019-11-04 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./REHAB./COMP. OF VARIOUS GOV'T. BLDGS. STRUCT., FAC (Provincewide) LS - P13,523,124.00 | [7 empty] | Date Allotment Released: | 2019-02-12 | Date completed:
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2019-11-04 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./REHAB./COMP. OF VARIOUS GOV'T. BLDGS. STRUCT., FAC (Provincewide) LS - P13,523,124.00 | [7 empty] | Date Started: | 2019-11-04
Asuncion | Camansa | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./REHAB./COMP. OF VARIOUS GOV'T. BLDGS. STRUCT., FAC (Provincewide) LS - LS - P13,523,124.00 | Construction of IP Tribal Council of Women at Brgy. Camansa, Asuncion |  | 20% DF CY 2018 | Building |  | sq.m | Admin | Project Cost: | 560000 | Target Completion Date: |  | Program: | 560000 | Planned: |  | No. of Persons: |  | Purchase Request # 20032714
Asuncion | Camansa | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./REHAB./COMP. OF VARIOUS GOV'T. BLDGS. STRUCT., FAC (Provincewide) LS - P13,523,124.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 560000 | Revised: |  | No. of Man-days:
Asuncion | Camansa | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./REHAB./COMP. OF VARIOUS GOV'T. BLDGS. STRUCT., FAC (Provincewide) LS - P13,523,124.00 | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual:
Asuncion | Camansa | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./REHAB./COMP. OF VARIOUS GOV'T. BLDGS. STRUCT., FAC (Provincewide) LS - P13,523,124.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Asuncion | Camansa | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./REHAB./COMP. OF VARIOUS GOV'T. BLDGS. STRUCT., FAC (Provincewide) LS - P13,523,124.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Asuncion | Camansa | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./REHAB./COMP. OF VARIOUS GOV'T. BLDGS. STRUCT., FAC (Provincewide) LS - P13,523,124.00 | [7 empty] | Date Started:
New Corella | Del Monte | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | RURAL ELECTRIFICATION (Provincewide) LS - P5,000,000.00 | Rural Electrification at Del Monte, New Corella |  | 20% DF CY 2018 | Electrification |  |  | Contract | Project Cost: | 1000000 | Target Completion Date: |  | Program: | 1000000 | Planned: |  | No. of Persons: |  | Post Qualification on process
New Corella | Del Monte | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | RURAL ELECTRIFICATION (Provincewide) LS - P5,000,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 1000000 | Revised: |  | No. of Man-days:
New Corella | Del Monte | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | RURAL ELECTRIFICATION (Provincewide) LS - P5,000,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
New Corella | Del Monte | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | RURAL ELECTRIFICATION (Provincewide) LS - P5,000,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | Del Monte | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | RURAL ELECTRIFICATION (Provincewide) LS - P5,000,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
New Corella | Del Monte | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | RURAL ELECTRIFICATION (Provincewide) LS - P5,000,000.00 | [7 empty] | Date Started:
Asuncion | Camansa | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | RURAL ELECTRIFICATION (Provincewide) LS - P5,000,000.00 | Const. of Distribution Line in Sitio Prk. 1,3,4, 11 and 7, Camansa, Asuncion |  | 20% DF CY 2018 | Electrification |  |  | Contract | Project Cost: | 4000000 | Target Completion Date: |  | Program: | 4000000 | Planned: |  | No. of Persons: |  | Purchase Request # 19093670 (On process )
Asuncion | Camansa | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | RURAL ELECTRIFICATION (Provincewide) LS - P5,000,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 4000000 | Revised: |  | No. of Man-days:
Asuncion | Camansa | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | RURAL ELECTRIFICATION (Provincewide) LS - P5,000,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Asuncion | Camansa | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | RURAL ELECTRIFICATION (Provincewide) LS - P5,000,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Asuncion | Camansa | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | RURAL ELECTRIFICATION (Provincewide) LS - P5,000,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Asuncion | Camansa | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | RURAL ELECTRIFICATION (Provincewide) LS - P5,000,000.00 | [7 empty] | Date Started:
Talaingod | Palma Gil | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./REHAB./COMP. OF VARIOUS GOV'T. BLDGS. STRUCT., FAC (Provincewide) | Const. of Standard Quarantine Shed for Car Bath Natulian, Brgy. Palma Gil, Talaingod |  | 20% DF CY 2018 | Car Bath |  |  | Contract | Project Cost: | 200000 | Target Completion Date: |  | Program: | 200000 | Planned: |  | No. of Persons: |  | Awarded to DIGOS CONSTRAK
Talaingod | Palma Gil | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./REHAB./COMP. OF VARIOUS GOV'T. BLDGS. STRUCT., FAC (Provincewide) | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 200000 | Revised: |  | No. of Man-days:
Talaingod | Palma Gil | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./REHAB./COMP. OF VARIOUS GOV'T. BLDGS. STRUCT., FAC (Provincewide) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Talaingod | Palma Gil | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./REHAB./COMP. OF VARIOUS GOV'T. BLDGS. STRUCT., FAC (Provincewide) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Talaingod | Palma Gil | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./REHAB./COMP. OF VARIOUS GOV'T. BLDGS. STRUCT., FAC (Provincewide) | [7 empty] | Date Allotment Released: |  | Date completed:
Talaingod | Palma Gil | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./REHAB./COMP. OF VARIOUS GOV'T. BLDGS. STRUCT., FAC (Provincewide) | [7 empty] | Date Started:
Tagum City | Balamban | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./REHAB./COMP. OF VARIOUS GOV'T. BLDGS. STRUCT., FAC (Provincewide) | Construction of Veterinary Quarantine Station, New balamban, Tagum City |  | 20% DF CY 2018 | Car Bath |  |  | Contract | Project Cost: | 200000 | Target Completion Date: |  | Program: | 200000 | Planned: |  | No. of Persons: |  | Awarded to ALLBRYCAR
Tagum City | Balamban | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./REHAB./COMP. OF VARIOUS GOV'T. BLDGS. STRUCT., FAC (Provincewide) | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 200000 | Revised: |  | No. of Man-days:
Tagum City | Balamban | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./REHAB./COMP. OF VARIOUS GOV'T. BLDGS. STRUCT., FAC (Provincewide) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Tagum City | Balamban | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./REHAB./COMP. OF VARIOUS GOV'T. BLDGS. STRUCT., FAC (Provincewide) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Tagum City | Balamban | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./REHAB./COMP. OF VARIOUS GOV'T. BLDGS. STRUCT., FAC (Provincewide) | [7 empty] | Date Allotment Released: |  | Date completed:
Tagum City | Balamban | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./REHAB./COMP. OF VARIOUS GOV'T. BLDGS. STRUCT., FAC (Provincewide) | [7 empty] | Date Started:
Asuncion | New Santiago | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | Const. of Potable water System at Prk. 6, New Santiago, Asuncion |  | GF CY 2018 (STIMULUS) | Water System |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Amended in AIP 3rd revision CY 2019 increasing the amount to complete the project For plan preparation c/o Amamio
Asuncion | New Santiago | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 500000 | Revised: |  | No. of Man-days:
Asuncion | New Santiago | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Asuncion | New Santiago | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Asuncion | New Santiago | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Date Allotment Released: |  | Date completed:
Asuncion | New Santiago | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Date Started:
Tagum City | Pagsabangan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | Completion of GYM Bleacher w/ Electrification, Pagsabangan, Tagum City |  | GF CY 2018 (STIMULUS) | Bleacher |  |  | MLGU | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | For implementation but the project was implemented by the brgy. Waiting for resolution to change priority Alloted March 12, 2019
Tagum City | Pagsabangan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 500000 | Revised: |  | No. of Man-days:
Tagum City | Pagsabangan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Tagum City | Pagsabangan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Tagum City | Pagsabangan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Date Allotment Released: |  | Date completed:
Tagum City | Pagsabangan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Date Started:
Tagum City | Libuganon | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | Construction of Drainage Canal, Libuganon, Tagum City |  | GF CY 2018 (STIMULUS) | Drainage |  |  | Admin | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | For implementation
Tagum City | Libuganon | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 500000 | Revised: |  | No. of Man-days:
Tagum City | Libuganon | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual:
Tagum City | Libuganon | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Tagum City | Libuganon | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Date Allotment Released: |  | Date completed:
Tagum City | Libuganon | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Date Started:
Kapalong | Luna | 1st Eng'g. Dist. | On-going | 2020-06-01 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | Construction of Concrete Perimeter Fence, Luna, Kapalaong |  | GF CY 2018 (STIMULUS) | Fence |  | sq.m | Admin | Project Cost: | 500000 | Target Completion Date: | 2020-07-21 | Program: | 500000 | Planned: | 92% | No. of Persons: | 8 | On-going
Kapalong | Luna | 1st Eng'g. Dist. | On-going | 2020-06-01 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Project Engineer: | Ambrosio | Revised Completion Date: | 2020-07-21 | Allotment: | 500000 | Revised: |  | No. of Man-days: | 120
Kapalong | Luna | 1st Eng'g. Dist. | On-going | 2020-06-01 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: | 93%
Kapalong | Luna | 1st Eng'g. Dist. | On-going | 2020-06-01 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Duration: | 50 | No. of days extended: |  |  |  | Slippage: | 1%
Kapalong | Luna | 1st Eng'g. Dist. | On-going | 2020-06-01 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Date Allotment Released: |  | Date completed:
Kapalong | Luna | 1st Eng'g. Dist. | On-going | 2020-06-01 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Date Started: | 2020-06-01
Kapalong | Maniki | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | Completion of Brgy. Health Center, Maniki, Kapalong |  | GF CY 2018 (STIMULUS) | Building |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | For amendment.To submit a new resolution for another priority project which is the Const. of Multi-Purpose Pavement but the propose site is not is donated because the previous project Completion of Brgy. Health Center was funded by the LGU of Kapalong
Kapalong | Maniki | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 500000 | Revised: |  | No. of Man-days:
Kapalong | Maniki | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Kapalong | Maniki | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Kapalong | Maniki | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Date Allotment Released: |  | Date completed:
Kapalong | Maniki | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Date Started:
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | Grouted Riprap on Embankment Sto. Ñino, Talaingod |  | GF CY 2018 (STIMULUS) | Riprap |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Plan and POW on process c/o PDPM
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 500000 | Revised: |  | No. of Man-days:
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Date Allotment Released: |  | Date completed:
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Date Started:
Talaingod | Dagohoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | Barangay Hall Improvement, Dagohoy, Talaingod |  | GF CY 2018 (STIMULUS) | Building |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | For amendment to Construction of Retaining Wall as per recommendation by Engr. Misa during site re-evaluation. Plan & POW completed.Resolution from the Brgy. Council to support the amendment c/o Engr. Canillada
Talaingod | Dagohoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 500000 | Revised: |  | No. of Man-days:
Talaingod | Dagohoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Talaingod | Dagohoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Talaingod | Dagohoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Date Allotment Released: |  | Date completed:
Talaingod | Dagohoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Date Started:
Talaingod | Palma Gil | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | Construction of 2 Classroom Building Datu Jose Libayao NHS Ext, Natulian, Palma Gil, Talaingod |  | GF CY 2018 (STIMULUS) | Building |  |  |  | Project Cost: | 1930933.28 | Target Completion Date: |  | Program: | 1930933.28 | Planned: |  | No. of Persons: |  | PO # 2020031342 - ALPEBEL BUILDERS & SUPPLY CORP.
Talaingod | Palma Gil | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 1930933.28 | Revised: |  | No. of Man-days:
Talaingod | Palma Gil | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Talaingod | Palma Gil | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Talaingod | Palma Gil | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Date Allotment Released: |  | Date completed:
Talaingod | Palma Gil | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Date Started:
New Corella | Mesaoy | 1st Eng'g. Dist. | On-going | 2018-11-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REHABILITATION OF VARIOUS PROVINCIAL ROADS | Mesaoy - Jct. Mahayahay |  | SB # 1 CY 2018 | Road Rehabilitation |  | km | Admin | Project Cost: | 1534000 | Target Completion Date: | 2018-12-15 23:46 | Program: | 1534000 | Planned: | 100% | No. of Persons: | 6 | Completed as per physical accomplishment. Financial documents still on process.
New Corella | Mesaoy | 1st Eng'g. Dist. | On-going | 2018-11-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REHABILITATION OF VARIOUS PROVINCIAL ROADS | [7 empty] | Project Engineer: | Pilotos | Revised Completion Date: |  | Allotment: | 1534000 | Revised: |  | No. of Man-days: | 150
New Corella | Mesaoy | 1st Eng'g. Dist. | On-going | 2018-11-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REHABILITATION OF VARIOUS PROVINCIAL ROADS | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: | 100%
New Corella | Mesaoy | 1st Eng'g. Dist. | On-going | 2018-11-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REHABILITATION OF VARIOUS PROVINCIAL ROADS | [7 empty] | Duration: | 30 | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | Mesaoy | 1st Eng'g. Dist. | On-going | 2018-11-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REHABILITATION OF VARIOUS PROVINCIAL ROADS | [7 empty] | Date Allotment Released: | 2018-07-19 | Date completed: | 2020-02-29
New Corella | Mesaoy | 1st Eng'g. Dist. | On-going | 2018-11-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REHABILITATION OF VARIOUS PROVINCIAL ROADS | [7 empty] | Date Started: | 2018-11-16
Kapalong | Maniki | 1st Eng'g. Dist. | On-going | 2019-11-02 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./COMPL./IMPV'T. OF VARIOUS GOV'T. BLDGS., STRUCTURES & FACILITIES (Const. in Progress - Bldgs. & Other Structures | Const./Impv't. of DDN Hospital Kapalong Zone |  | SB # 2 CY 2018 | Building |  | sq.m | Contract | Project Cost: | 5000000 | Target Completion Date: | 2020-06-09 | Program: | 5000000 | Planned: | 100% | No. of Persons: | 6 | Completed as per physical accomplishment. Financial documents still on process.
Kapalong | Maniki | 1st Eng'g. Dist. | On-going | 2019-11-02 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./COMPL./IMPV'T. OF VARIOUS GOV'T. BLDGS., STRUCTURES & FACILITIES (Const. in Progress - Bldgs. & Other Structures | [7 empty] | Project Engineer: | Ambrosio | Revised Completion Date: | 2020-07-07 | Allotment: | 5000000 | Revised: |  | No. of Man-days: | 150
Kapalong | Maniki | 1st Eng'g. Dist. | On-going | 2019-11-02 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./COMPL./IMPV'T. OF VARIOUS GOV'T. BLDGS., STRUCTURES & FACILITIES (Const. in Progress - Bldgs. & Other Structures | [7 empty] | Implementor: | MAG CORP. | No. of days suspended: | 28 | Disbursement: | 4781000 | Actual: | 100%
Kapalong | Maniki | 1st Eng'g. Dist. | On-going | 2019-11-02 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./COMPL./IMPV'T. OF VARIOUS GOV'T. BLDGS., STRUCTURES & FACILITIES (Const. in Progress - Bldgs. & Other Structures | [7 empty] | Duration: | 220 | No. of days extended: |  |  |  | Slippage: | 0%
Kapalong | Maniki | 1st Eng'g. Dist. | On-going | 2019-11-02 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./COMPL./IMPV'T. OF VARIOUS GOV'T. BLDGS., STRUCTURES & FACILITIES (Const. in Progress - Bldgs. & Other Structures | [7 empty] | Date Allotment Released: | 2018-09-04 | Date completed: | 2020-07-07
Kapalong | Maniki | 1st Eng'g. Dist. | On-going | 2019-11-02 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./COMPL./IMPV'T. OF VARIOUS GOV'T. BLDGS., STRUCTURES & FACILITIES (Const. in Progress - Bldgs. & Other Structures | [7 empty] | Date Started: | 2019-11-02
New Corella | Poblacion | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./COMPL./IMPV'T. OF VARIOUS GOV'T. BLDGS., STRUCTURES & FACILITIES (Const. in Progress - Bldgs. & Other Structures | Compl. Of Bahay Pag-Asa for Minors, New Corella |  | SB # 2 CY 2018 | Building |  |  | Admin | Project Cost: | 3450000 | Target Completion Date: |  | Program: | 3450000 | Planned: |  | No. of Persons: |  | For implementation
New Corella | Poblacion | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./COMPL./IMPV'T. OF VARIOUS GOV'T. BLDGS., STRUCTURES & FACILITIES (Const. in Progress - Bldgs. & Other Structures | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 3450000 | Revised: |  | No. of Man-days:
New Corella | Poblacion | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./COMPL./IMPV'T. OF VARIOUS GOV'T. BLDGS., STRUCTURES & FACILITIES (Const. in Progress - Bldgs. & Other Structures | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
New Corella | Poblacion | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./COMPL./IMPV'T. OF VARIOUS GOV'T. BLDGS., STRUCTURES & FACILITIES (Const. in Progress - Bldgs. & Other Structures | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | Poblacion | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./COMPL./IMPV'T. OF VARIOUS GOV'T. BLDGS., STRUCTURES & FACILITIES (Const. in Progress - Bldgs. & Other Structures | [7 empty] | Date Allotment Released: |  | Date completed:
New Corella | Poblacion | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./COMPL./IMPV'T. OF VARIOUS GOV'T. BLDGS., STRUCTURES & FACILITIES (Const. in Progress - Bldgs. & Other Structures | [7 empty] | Date Started:
Tagum City | Mankilam | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./COMPL./IMPV'T. OF VARIOUS GOV'T. BLDGS., STRUCTURES & FACILITIES (Const. in Progress - Bldgs. & Other Structures | Const. of Add'l. 2nd Level Multi-Purpose HalI, PGSO warehouse,Bldg., Mankilam |  | SB # 2 CY 2018 | Building |  |  | Contract | Project Cost: | 7483756.22 | Target Completion Date: |  | Program: | 7483756.22 | Planned: |  | No. of Persons: |  | PO #2020020808 - FZI CONSTRUCTION AND PARTS SUPPLY
Tagum City | Mankilam | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./COMPL./IMPV'T. OF VARIOUS GOV'T. BLDGS., STRUCTURES & FACILITIES (Const. in Progress - Bldgs. & Other Structures | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 7483756.22 | Revised: |  | No. of Man-days:
Tagum City | Mankilam | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./COMPL./IMPV'T. OF VARIOUS GOV'T. BLDGS., STRUCTURES & FACILITIES (Const. in Progress - Bldgs. & Other Structures | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Tagum City | Mankilam | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./COMPL./IMPV'T. OF VARIOUS GOV'T. BLDGS., STRUCTURES & FACILITIES (Const. in Progress - Bldgs. & Other Structures | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Tagum City | Mankilam | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./COMPL./IMPV'T. OF VARIOUS GOV'T. BLDGS., STRUCTURES & FACILITIES (Const. in Progress - Bldgs. & Other Structures | [7 empty] | Date Allotment Released: |  | Date completed:
Tagum City | Mankilam | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./COMPL./IMPV'T. OF VARIOUS GOV'T. BLDGS., STRUCTURES & FACILITIES (Const. in Progress - Bldgs. & Other Structures | [7 empty] | Date Started:
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2020-04-30 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./COMPL./IMPV'T. OF VARIOUS GOV'T. BLDGS., STRUCTURES & FACILITIES (Const. in Progress - Bldgs. & Other Structures | Construction of SP/Legislative Building, Gov't. Center, Mankilam, Tagum City |  | SB # 3 CY 2018 | Building |  | sq.m | Contract | Project Cost: | 147262698.81 | Target Completion Date: | 2021-04-04 | Program: | 147262698.81 | Planned: | 4.205% | No. of Persons: | 20 | On-going (Suspended effective April 5, 2020 due to COVID; resumption order dated May 4, 2020)
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2020-04-30 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./COMPL./IMPV'T. OF VARIOUS GOV'T. BLDGS., STRUCTURES & FACILITIES (Const. in Progress - Bldgs. & Other Structures | [7 empty] | Project Engineer: | Japay/Albaracin | Revised Completion Date: | 2021-05-01 | Allotment: | 147262698.81 | Revised: |  | No. of Man-days: | 370
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2020-04-30 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./COMPL./IMPV'T. OF VARIOUS GOV'T. BLDGS., STRUCTURES & FACILITIES (Const. in Progress - Bldgs. & Other Structures | [7 empty] | Implementor: | Tagum Builders | No. of days suspended: | 27 | Disbursement: |  | Actual: | 4.347%
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2020-04-30 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./COMPL./IMPV'T. OF VARIOUS GOV'T. BLDGS., STRUCTURES & FACILITIES (Const. in Progress - Bldgs. & Other Structures | [7 empty] | Duration: | 370 | No. of days extended: |  |  |  | Slippage: | 0.1415%
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2020-04-30 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./COMPL./IMPV'T. OF VARIOUS GOV'T. BLDGS., STRUCTURES & FACILITIES (Const. in Progress - Bldgs. & Other Structures | [7 empty] | Date Allotment Released: |  | Date completed:
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2020-04-30 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./COMPL./IMPV'T. OF VARIOUS GOV'T. BLDGS., STRUCTURES & FACILITIES (Const. in Progress - Bldgs. & Other Structures | [7 empty] | Date Started: | 2020-03-30
Asuncion | Napungas | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | Rehab./Impv't. of MP Bldg. (Gym), Napungas, Asuncion |  | SB # 5 CY 2018 (STIMULUS) | GYM |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Abstract # 0620202137
Asuncion | Napungas | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Asuncion | Napungas | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Asuncion | Napungas | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Asuncion | Napungas | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Date Allotment Released: | 2019-02-04 | Date completed:
Asuncion | Napungas | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Date Started:
New Corella | Poblacion | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | Concreting of Drainage Canal from Prk. 3, 1-A, 2-A to Prk. 1-B, Brgy. Site, Phase @, New Corella |  | SB # 5 CY 2018 (STIMULUS) | Drainage |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Abstract draft
New Corella | Poblacion | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 500000 | Revised: |  | No. of Man-days:
New Corella | Poblacion | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
New Corella | Poblacion | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | Poblacion | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Date Allotment Released: |  | Date completed:
New Corella | Poblacion | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Date Started:
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2019-11-26 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./COMPL./IMPV'T. OF VARIOUS GOV'T. BLDGS., STRUCTURES & FACILITIES (Const. in Progress - Bldgs. & Other Structures | Division School Improvement (Davao del Norte DEPED Training Center), Tagum City |  | SEF (ANNUAL BUDGET CY 2018) | Building |  | sq.m | Admin | Project Cost: | 1250000 | Target Completion Date: | 2020-05-04 | Program: | 1250000 | Planned: | 100% | No. of Persons: | 18 | On-going (Suspended last April 5, 2020 due to COVID; resumption order dated May 4, 2020)
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2019-11-26 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./COMPL./IMPV'T. OF VARIOUS GOV'T. BLDGS., STRUCTURES & FACILITIES (Const. in Progress - Bldgs. & Other Structures | [7 empty] | Project Engineer: | Japay/Quirante | Revised Completion Date: | 2020-07-15 | Allotment: | 1250000 | Revised: | 83.63% | No. of Man-days: | 270
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2019-11-26 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./COMPL./IMPV'T. OF VARIOUS GOV'T. BLDGS., STRUCTURES & FACILITIES (Const. in Progress - Bldgs. & Other Structures | [7 empty] | Implementor: | Admin | No. of days suspended: | 27 | Disbursement: | 850625 | Actual: | 78.02%
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2019-11-26 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./COMPL./IMPV'T. OF VARIOUS GOV'T. BLDGS., STRUCTURES & FACILITIES (Const. in Progress - Bldgs. & Other Structures | [7 empty] | Duration: | 160 | No. of days extended: | 45 |  |  | Slippage: | -5.61%
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2019-11-26 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./COMPL./IMPV'T. OF VARIOUS GOV'T. BLDGS., STRUCTURES & FACILITIES (Const. in Progress - Bldgs. & Other Structures | [7 empty] | Date Allotment Released: | 2019-02-04 | Date completed:
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2019-11-26 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./COMPL./IMPV'T. OF VARIOUS GOV'T. BLDGS., STRUCTURES & FACILITIES (Const. in Progress - Bldgs. & Other Structures | [7 empty] | Date Started: | 2019-11-26
Talaingod | Dagohoy | 1st Eng'g. Dist. | On-going | 2019-11-17 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPAPP | Const. of Processing and Bagsakan Center, Brgy. Dagohoy, Talaingod |  | OPAPP-PAMANA CY 2018 | Building |  | sq.m | Contract | Project Cost: | 2500000 | Target Completion Date: | 2020-04-10 | Program: | 2500000 | Planned: | 55.61% | No. of Persons: | 8 | On-going; Resumption Order dated May 4, 2020
Talaingod | Dagohoy | 1st Eng'g. Dist. | On-going | 2019-11-17 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPAPP | [7 empty] | Project Engineer: | Dadula | Revised Completion Date: |  | Allotment: | 2500000 | Revised: |  | No. of Man-days: | 200
Talaingod | Dagohoy | 1st Eng'g. Dist. | On-going | 2019-11-17 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPAPP | [7 empty] | Implementor: | RLHV | No. of days suspended: |  | Disbursement: | 375000 | Actual: | 68.72%
Talaingod | Dagohoy | 1st Eng'g. Dist. | On-going | 2019-11-17 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPAPP | [7 empty] | Duration: | 145 | No. of days extended: |  |  |  | Slippage: | 13.11%
Talaingod | Dagohoy | 1st Eng'g. Dist. | On-going | 2019-11-17 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPAPP | [7 empty] | Date Allotment Released: | 2019-11-25 | Date completed:
Talaingod | Dagohoy | 1st Eng'g. Dist. | On-going | 2019-11-17 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPAPP | [7 empty] | Date Started: | 2019-11-17
Kapalong | Maniki | 1st Eng'g. Dist. | On-going | 2019-11-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPAPP | Post Harvest Facilities (Corn Mill, Solar Dryer, Corn Sheller), Kapalong, Davao del Norte |  | OPAPP-PAMANA CY 2018 | Building |  | sq.m | Admin | Project Cost: | 1500000 | Target Completion Date: | 2020-02-27 | Program: | 1500000 | Planned: | 100% | No. of Persons: | 7 | Completed as per physical accomplishment. Financial documents still on process.
Kapalong | Maniki | 1st Eng'g. Dist. | On-going | 2019-11-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPAPP | [7 empty] | Project Engineer: | Ambrosio | Revised Completion Date: | 2020-06-15 | Allotment: | 1500000 | Revised: |  | No. of Man-days: | 175
Kapalong | Maniki | 1st Eng'g. Dist. | On-going | 2019-11-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPAPP | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 1114654.45 | Actual: | 100%
Kapalong | Maniki | 1st Eng'g. Dist. | On-going | 2019-11-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPAPP | [7 empty] | Duration: | 101 | No. of days extended: | 82 |  |  | Slippage: | 0%
Kapalong | Maniki | 1st Eng'g. Dist. | On-going | 2019-11-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPAPP | [7 empty] | Date Allotment Released: | 2019-11-18 | Date completed: | 2020-06-15
Kapalong | Maniki | 1st Eng'g. Dist. | On-going | 2019-11-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPAPP | [7 empty] | Date Started: | 2019-11-18
Kapalong | Capungagan | 1st Eng'g. Dist. | On-going | 2019-11-25 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPAPP | Construction of PWS Level II in Purok 7-A and 7-B, Capungagan, Kapalong |  | OPAPP-PAMANA CY 2018 | Potable Water System |  |  | Admin | Project Cost: | 1760000 | Target Completion Date: | 2020-02-03 | Program: | 1760000 | Planned: | 100% | No. of Persons: | 25 | On-going (Suspended last April 5, 2020 due to COVID; resumption order dated May 4, 2020)
Kapalong | Capungagan | 1st Eng'g. Dist. | On-going | 2019-11-25 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPAPP | [7 empty] | Project Engineer: | Kabinge | Revised Completion Date: | 2020-04-15 | Allotment: | 1760000 | Revised: | 100% | No. of Man-days: | 375
Kapalong | Capungagan | 1st Eng'g. Dist. | On-going | 2019-11-25 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPAPP | [7 empty] | Implementor: | PEO | No. of days suspended: | 28 | Disbursement: | 1235344 | Actual: | 76.64%
Kapalong | Capungagan | 1st Eng'g. Dist. | On-going | 2019-11-25 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPAPP | [7 empty] | Duration: | 70 | No. of days extended: | 44 |  |  | Slippage: | -23.36%
Kapalong | Capungagan | 1st Eng'g. Dist. | On-going | 2019-11-25 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPAPP | [7 empty] | Date Allotment Released: | 2019-11-25 | Date completed:
Kapalong | Capungagan | 1st Eng'g. Dist. | On-going | 2019-11-25 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPAPP | [7 empty] | Date Started: | 2019-11-25
Kapalong | Pag-Asa | 1st Eng'g. Dist. | On-going | 2019-12-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPAPP | Construction of PWS Level II in Purok 2, Pag-Asa, kapalong |  | OPAPP-PAMANA CY 2018 | Potable Water System |  |  | Admin | Project Cost: | 2310000 | Target Completion Date: | 2020-04-09 | Program: | 2310000 | Planned: | 78% | No. of Persons: | 9 | On-going (Suspended last April 5, 2020 due to COVID; resumption order dated May 4, 2020)
Kapalong | Pag-Asa | 1st Eng'g. Dist. | On-going | 2019-12-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPAPP | [7 empty] | Project Engineer: | Dadula | Revised Completion Date: | 2020-06-21 | Allotment: | 2310000 | Revised: |  | No. of Man-days: | 138
Kapalong | Pag-Asa | 1st Eng'g. Dist. | On-going | 2019-12-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPAPP | [7 empty] | Implementor: | PEO | No. of days suspended: | 28 | Disbursement: | 1133886.6 | Actual: | 49.09%
Kapalong | Pag-Asa | 1st Eng'g. Dist. | On-going | 2019-12-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPAPP | [7 empty] | Duration: | 115 | No. of days extended: | 45 |  |  | Slippage: | -28.91%
Kapalong | Pag-Asa | 1st Eng'g. Dist. | On-going | 2019-12-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPAPP | [7 empty] | Date Allotment Released: | 2019-11-25 | Date completed:
Kapalong | Pag-Asa | 1st Eng'g. Dist. | On-going | 2019-12-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPAPP | [7 empty] | Date Started: | 2019-12-16
Kapalong | Semong | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPAPP | Cattle Production- Brgy. Tiburcia, Gupitan and Semong, Kapalong |  | OPAPP-PAMANA CY 2018 | Building |  | sq.m |  | Project Cost: | 1500000 | Target Completion Date: |  | Program: | 1500000 | Planned: |  | No. of Persons: |  | For cancellation. A letter was sent to OPAPP last Dec 2018 requesting to allow us to reduce the number of cattle but we are still hoping that there would be a supplier will bid
Kapalong | Semong | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPAPP | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 1500000 | Revised: |  | No. of Man-days:
Kapalong | Semong | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPAPP | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Kapalong | Semong | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPAPP | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Kapalong | Semong | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPAPP | [7 empty] | Date Allotment Released: |  | Date completed:
Kapalong | Semong | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPAPP | [7 empty] | Date Started:
Talaingod | Dagohoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPAPP | Cattle Production, Brgy. Palma Gil, Brgy. Sto. Nino, Brgy. Dagohoy, Talaingod, Davao del Norte |  | OPAPP-PAMANA CY 2018 | Building |  | sq.m |  | Project Cost: | 1500000 | Target Completion Date: |  | Program: | 1500000 | Planned: |  | No. of Persons: |  | For cancellation. A letter was sent to OPAPP last Dec 2018 requesting to allow us to reduce the number of cattle but we are still hoping that there would be a supplier will bid
Talaingod | Dagohoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPAPP | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 1500000 | Revised: |  | No. of Man-days:
Talaingod | Dagohoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPAPP | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Talaingod | Dagohoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPAPP | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Talaingod | Dagohoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPAPP | [7 empty] | Date Allotment Released: |  | Date completed:
Talaingod | Dagohoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPAPP | [7 empty] | Date Started:
Talaingod | Palma Gil | 1st Eng'g. Dist. | On-going | 2020-06-01 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPAPP | Rice Mill for Upland Rice, Palma Gil, Talaingod |  | OPAPP-PAMANA CY 2018 | Rice Mill |  |  | Admin | Project Cost: | 1000000 | Target Completion Date: | 2020-07-30 23:46 | Program: | 1000000 | Planned: | 8.07% | No. of Persons: | 6 | On-going
Talaingod | Palma Gil | 1st Eng'g. Dist. | On-going | 2020-06-01 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPAPP | [7 empty] | Project Engineer: | Torrecampo | Revised Completion Date: | 2020-07-30 23:46 | Allotment: | 1000000 | Revised: |  | No. of Man-days: | 90
Talaingod | Palma Gil | 1st Eng'g. Dist. | On-going | 2020-06-01 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPAPP | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: | 8.07%
Talaingod | Palma Gil | 1st Eng'g. Dist. | On-going | 2020-06-01 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPAPP | [7 empty] | Duration: | 60 | No. of days extended: |  |  |  | Slippage: | 0%
Talaingod | Palma Gil | 1st Eng'g. Dist. | On-going | 2020-06-01 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPAPP | [7 empty] | Date Allotment Released: |  | Date completed:
Talaingod | Palma Gil | 1st Eng'g. Dist. | On-going | 2020-06-01 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPAPP | [7 empty] | Date Started: | 2020-06-01
Kapalong | Mabantao-Florida | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | QRF | Rehab. Of Slope Protection of Libuganon River Along Kapalong - Mabantao - Florida Prov'l. Road Phase I |  | QRF CY 2016 | Slope Protection |  |  |  | Project Cost: | 900000 | Target Completion Date: |  | Program: | 900000 | Planned: |  | No. of Persons: |  | For AIP Amendment
Kapalong | Mabantao-Florida | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | QRF | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 900000 | Revised: |  | No. of Man-days:
Kapalong | Mabantao-Florida | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | QRF | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Kapalong | Mabantao-Florida | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | QRF | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Kapalong | Mabantao-Florida | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | QRF | [7 empty] | Date Allotment Released: |  | Date completed:
Kapalong | Mabantao-Florida | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | QRF | [7 empty] | Date Started:
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2019-11-04 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Ground Dev't. | Ground Development and landscape @ PDRRMD, Gov't. Center, Mankilam, Tagum City |  | LDRRMF 2018 | Ground Dev't. |  | sq.m | Admin | Project Cost: | 1000000 | Target Completion Date: | 2020-02-29 23:46 | Program: | 1000000 | Planned: | 75.24% | No. of Persons: | 8 | Suspended (Waiting for the complete delivery of materials) dated March 2, 2020
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2019-11-04 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Ground Dev't. | [7 empty] | Project Engineer: | Juan | Revised Completion Date: | 2020-02-29 23:46 | Allotment: | 1000000 | Revised: |  | No. of Man-days: | 152
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2019-11-04 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Ground Dev't. | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: | 752400 | Actual: | 75.24%
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2019-11-04 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Ground Dev't. | [7 empty] | Duration: | 118 | No. of days extended: |  |  |  | Slippage: | 0%
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2019-11-04 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Ground Dev't. | [7 empty] | Date Allotment Released: | 2019-03-19 | Date completed:
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2019-11-04 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Ground Dev't. | [7 empty] | Date Started: | 2019-11-04
Asuncion | Canatan-Doña Andrea | 1st Eng'g. Dist. | On-going | 2020-06-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL RAODS & BRIDGES LS - P41,465,029.00 | ROAD ID 007 - Jct. Highway Canatan - Doña Andrea |  | 20% DF CY 2019 | Road Rehabilitation | 4.34 | km | Admin | Project Cost: | 2000000 | Target Completion Date: | 2020-08-11 23:46 | Program: | 2000000 | Planned: | 31.77% | No. of Persons: |  | On-going
Asuncion | Canatan-Doña Andrea | 1st Eng'g. Dist. | On-going | 2020-06-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL RAODS & BRIDGES | [7 empty] | Project Engineer: | Pilotos | Revised Completion Date: | 2020-08-11 23:46 | Allotment: | 2000000 | Revised: |  | No. of Man-days:
Asuncion | Canatan-Doña Andrea | 1st Eng'g. Dist. | On-going | 2020-06-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL RAODS & BRIDGES LS - P41,465,029.00 | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: | 31.77%
Asuncion | Canatan-Doña Andrea | 1st Eng'g. Dist. | On-going | 2020-06-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL RAODS & BRIDGES LS - P41,465,029.00 | [7 empty] | Duration: | 57 | No. of days extended: |  |  |  | Slippage: | 0%
Asuncion | Canatan-Doña Andrea | 1st Eng'g. Dist. | On-going | 2020-06-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL RAODS & BRIDGES LS - P41,465,029.00 | [7 empty] | Date Allotment Released: | 2019-06-12 | Date completed:
Asuncion | Canatan-Doña Andrea | 1st Eng'g. Dist. | On-going | 2020-06-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL RAODS & BRIDGES LS - P41,465,029.00 | [7 empty] | Date Started: | 2020-06-16
Asuncion | Pamacaun | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL RAODS & BRIDGES LS - P41,465,029.00 | ROAD ID 015 - Pamacaun - Lasang Banate |  | 20% DF CY 2019 | Road Rehabilitation | 4.34 |  | Admin | Project Cost: | 2000000 | Target Completion Date: |  | Program: | 2000000 | Planned: |  | No. of Persons: |  | For implementation (Waiting for the delivery of geo-grid materials. An approved request letter dated Dec. 3, 2019 for the extension of 50 days from Provincial Administrator Engr. Rabanoz is on file
Asuncion | Pamacaun | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL RAODS & BRIDGES | [7 empty] | Project Engineer: | Gone | Revised Completion Date: | 0 | Allotment: | 2000000 | Revised: |  | No. of Man-days:
Asuncion | Pamacaun | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL RAODS & BRIDGES LS - P41,465,029.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Asuncion | Pamacaun | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL RAODS & BRIDGES LS - P41,465,029.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Asuncion | Pamacaun | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL RAODS & BRIDGES LS - P41,465,029.00 | [7 empty] | Date Allotment Released: | 2019-06-27 | Date completed:
Asuncion | Pamacaun | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL RAODS & BRIDGES LS - P41,465,029.00 | [7 empty] | Date Started:
Talaingod | Sto.Niño-Palma Gil | 1st Eng'g. Dist. | On-going | 2020-03-06 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL RAODS & BRIDGES LS - P41,465,029.00 | ROAD ID 019 - Sto. Niño - Palma Gil - Sitio Opao |  | 20% DF CY 2019 | Road Rehabilitation | 11.6 | km | Contract | Project Cost: | 1901000 | Target Completion Date: | 2020-04-18 23:46 | Program: | 1901000 | Planned: | 44.89% | No. of Persons: |  | On-going (Suspended dated March 14, 2020; Resumption Order dated May 25, 2020)
Talaingod | Sto.Niño-Palma Gil | 1st Eng'g. Dist. | On-going | 2020-03-06 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL RAODS & BRIDGES | [7 empty] | Project Engineer: | Lumapat | Revised Completion Date: | 2020-06-29 23:46 | Allotment: | 1901000 | Revised: |  | No. of Man-days:
Talaingod | Sto.Niño-Palma Gil | 1st Eng'g. Dist. | On-going | 2020-03-06 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL RAODS & BRIDGES LS - P41,465,029.00 | [7 empty] | Implementor: | Tagum Constrak | No. of days suspended: | 72 | Disbursement: |  | Actual: | 44.89%
Talaingod | Sto.Niño-Palma Gil | 1st Eng'g. Dist. | On-going | 2020-03-06 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL RAODS & BRIDGES LS - P41,465,029.00 | [7 empty] | Duration: | 44 | No. of days extended: |  |  |  | Slippage: | 0%
Talaingod | Sto.Niño-Palma Gil | 1st Eng'g. Dist. | On-going | 2020-03-06 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL RAODS & BRIDGES LS - P41,465,029.00 | [7 empty] | Date Allotment Released: | 2019-06-19 | Date completed:
Talaingod | Sto.Niño-Palma Gil | 1st Eng'g. Dist. | On-going | 2020-03-06 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL RAODS & BRIDGES LS - P41,465,029.00 | [7 empty] | Date Started: | 2020-03-06
Talaingod | Sto. Niño-Daligdigon-Paiton | 1st Eng'g. Dist. | On-going | 2020-01-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL RAODS & BRIDGES LS - P41,465,029.00 | ROAD ID 023 - Sto. Niño - Daligdigon - Paiton |  | 20% DF CY 2019 | Road Rehabilitation | 11.6 | km | Contract | Project Cost: | 3000000 | Target Completion Date: | 2020-05-14 23:46 | Program: | 3000000 | Planned: | 2.19% | No. of Persons: |  | On-going; Resumption Order dated May 4, 2020
Talaingod | Sto. Niño-Daligdigon-Paiton | 1st Eng'g. Dist. | On-going | 2020-01-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL RAODS & BRIDGES | [7 empty] | Project Engineer: | Lumapat | Revised Completion Date: |  | Allotment: | 3000000 | Revised: |  | No. of Man-days:
Talaingod | Sto. Niño-Daligdigon-Paiton | 1st Eng'g. Dist. | On-going | 2020-01-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL RAODS & BRIDGES LS - P41,465,029.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: | 119400 | Actual: | 3.98%
Talaingod | Sto. Niño-Daligdigon-Paiton | 1st Eng'g. Dist. | On-going | 2020-01-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL RAODS & BRIDGES LS - P41,465,029.00 | [7 empty] | Duration: | 120 | No. of days extended: |  |  |  | Slippage: | 1.79%
Talaingod | Sto. Niño-Daligdigon-Paiton | 1st Eng'g. Dist. | On-going | 2020-01-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL RAODS & BRIDGES LS - P41,465,029.00 | [7 empty] | Date Allotment Released: | 2019-10-03 | Date completed:
Talaingod | Sto. Niño-Daligdigon-Paiton | 1st Eng'g. Dist. | On-going | 2020-01-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL RAODS & BRIDGES LS - P41,465,029.00 | [7 empty] | Date Started: | 2020-01-16
Talaingod | Jct. Paiton-Mibolo | 1st Eng'g. Dist. | On-going | 2019-08-01 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL RAODS & BRIDGES LS - P41,465,029.00 | ROAD ID 024 - Jct. Paiton - Mibolo |  | 20% DF CY 2019 | Road Rehabilitation | 23.9 | km | Contract | Project Cost: | 6000000 | Target Completion Date: | 2020-03-15 23:46 | Program: | 6000000 | Planned: | 21.05% | No. of Persons: |  | Temporary suspended because the materials for the box culvert procurement on process wth PO # 2019061674
Talaingod | Jct. Paiton-Mibolo | 1st Eng'g. Dist. | On-going | 2019-08-01 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL RAODS & BRIDGES | [7 empty] | Project Engineer: | Lumapat | Revised Completion Date: |  | Allotment: | 6000000 | Revised: |  | No. of Man-days:
Talaingod | Jct. Paiton-Mibolo | 1st Eng'g. Dist. | On-going | 2019-08-01 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL RAODS & BRIDGES LS - P41,465,029.00 | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: | 1263000 | Actual: | 21.05%
Talaingod | Jct. Paiton-Mibolo | 1st Eng'g. Dist. | On-going | 2019-08-01 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL RAODS & BRIDGES LS - P41,465,029.00 | [7 empty] | Duration: | 228 | No. of days extended: |  |  |  | Slippage: | 0%
Talaingod | Jct. Paiton-Mibolo | 1st Eng'g. Dist. | On-going | 2019-08-01 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL RAODS & BRIDGES LS - P41,465,029.00 | [7 empty] | Date Allotment Released: | 2019-03-25 | Date completed:
Talaingod | Jct. Paiton-Mibolo | 1st Eng'g. Dist. | On-going | 2019-08-01 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL RAODS & BRIDGES LS - P41,465,029.00 | [7 empty] | Date Started: | 2019-08-01
Talaingod | Monte Dujali-Gupitan | 1st Eng'g. Dist. | On-going | 2020-01-31 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL RAODS & BRIDGES LS - P41,465,029.00 | ROAD ID 037 - Monte Dujali - Gupitan |  | 20% DF CY 2019 | Road Rehabilitation | 4.58 | km | Admin | Project Cost: | 1200000 | Target Completion Date: | 2020-03-31 23:46 | Program: | 1200000 | Planned: | 100% | No. of Persons: | 10 | Completed as per physical accomplishment. Financial documents still on process.
Talaingod | Monte Dujali-Gupitan | 1st Eng'g. Dist. | On-going | 2020-01-31 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL RAODS & BRIDGES | [7 empty] | Project Engineer: | Bacaron | Revised Completion Date: | 2020-06-30 23:46 | Allotment: | 1200000 | Revised: |  | No. of Man-days: | 240
Talaingod | Monte Dujali-Gupitan | 1st Eng'g. Dist. | On-going | 2020-01-31 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL RAODS & BRIDGES LS - P41,465,029.00 | [7 empty] | Implementor: | PEO | No. of days suspended: | 30 | Disbursement: | 485400 | Actual: | 100%
Talaingod | Monte Dujali-Gupitan | 1st Eng'g. Dist. | On-going | 2020-01-31 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL RAODS & BRIDGES LS - P41,465,029.00 | [7 empty] | Duration: | 61 | No. of days extended: | 61 |  |  | Slippage: | 0%
Talaingod | Monte Dujali-Gupitan | 1st Eng'g. Dist. | On-going | 2020-01-31 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL RAODS & BRIDGES LS - P41,465,029.00 | [7 empty] | Date Allotment Released: | 2019-12-06 | Date completed:
Talaingod | Monte Dujali-Gupitan | 1st Eng'g. Dist. | On-going | 2020-01-31 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL RAODS & BRIDGES LS - P41,465,029.00 | [7 empty] | Date Started: | 2020-01-31
New Corella | San Juan-New Talisay | 1st Eng'g. Dist. | On-going | 2019-11-04 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS OF LOCAL ROADS & DRAINAGE DEVELOPMENT PROJECT(Provincewide) LS - 15,000,000.00 | Rehab./Impv't. of San Juan-New Talisay Provincial Road with Drainage |  | 20% DF CY 2019 | Road Drainage rehabiliated |  | km | Admin | Project Cost: | 1000000 | Target Completion Date: | 2019-12-18 | Program: | 1000000 | Planned: | 57.41% | No. of Persons: |  | Suspended dated December 18, 2019 due to revision of POW
New Corella | San Juan-New Talisay | 1st Eng'g. Dist. | On-going | 2019-11-04 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS OF LOCAL ROADS & DRAINAGE DEVELOPMENT PROJECT(Provincewide) LS - 15,000,000.00 | [7 empty] | Project Engineer: | Pilotos | Revised Completion Date: | 2019-12-18 | Allotment: | 1000000 | Revised: |  | No. of Man-days:
New Corella | San Juan-New Talisay | 1st Eng'g. Dist. | On-going | 2019-11-04 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS OF LOCAL ROADS & DRAINAGE DEVELOPMENT PROJECT(Provincewide) LS - 15,000,000.00 | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: | 74.11%
New Corella | San Juan-New Talisay | 1st Eng'g. Dist. | On-going | 2019-11-04 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS OF LOCAL ROADS & DRAINAGE DEVELOPMENT PROJECT(Provincewide) LS - 15,000,000.00 | [7 empty] | Duration: | 44 | No. of days extended: |  |  |  | Slippage: | 16.7%
New Corella | San Juan-New Talisay | 1st Eng'g. Dist. | On-going | 2019-11-04 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS OF LOCAL ROADS & DRAINAGE DEVELOPMENT PROJECT(Provincewide) LS - 15,000,000.00 | [7 empty] | Date Allotment Released: | 2019-01-31 | Date completed:
New Corella | San Juan-New Talisay | 1st Eng'g. Dist. | On-going | 2019-11-04 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS OF LOCAL ROADS & DRAINAGE DEVELOPMENT PROJECT(Provincewide) LS - 15,000,000.00 | [7 empty] | Date Started: | 2019-11-04
Kapalong | Suaon-Libuton | 1st Eng'g. Dist. | On-going | 2019-11-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS OF LOCAL ROADS & DRAINAGE DEVELOPMENT PROJECT(Provincewide) LS - 15,000,000.00 | Repair/Rehab. Of Concrete Road Jct. Suaon-Libuton, Kapalong |  | 20% DF CY 2019 | Road Drainage rehabiliated |  | km | Admin | Project Cost: | 1000000 | Target Completion Date: | 2020-02-15 23:46 | Program: | 1000000 | Planned: | 14.73% | No. of Persons: |  | Suspended dated March 30, 2020 due to availability of equipment
Kapalong | Suaon-Libuton | 1st Eng'g. Dist. | On-going | 2019-11-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS OF LOCAL ROADS & DRAINAGE DEVELOPMENT PROJECT(Provincewide) LS - 15,000,000.00 | [7 empty] | Project Engineer: | Bacaron | Revised Completion Date: |  | Allotment: | 1000000 | Revised: |  | No. of Man-days:
Kapalong | Suaon-Libuton | 1st Eng'g. Dist. | On-going | 2019-11-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS OF LOCAL ROADS & DRAINAGE DEVELOPMENT PROJECT(Provincewide) LS - 15,000,000.00 | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: | 14.2%
Kapalong | Suaon-Libuton | 1st Eng'g. Dist. | On-going | 2019-11-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS OF LOCAL ROADS & DRAINAGE DEVELOPMENT PROJECT(Provincewide) LS - 15,000,000.00 | [7 empty] | Duration: | 90 | No. of days extended: |  |  |  | Slippage: | -0.53%
Kapalong | Suaon-Libuton | 1st Eng'g. Dist. | On-going | 2019-11-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS OF LOCAL ROADS & DRAINAGE DEVELOPMENT PROJECT(Provincewide) LS - 15,000,000.00 | [7 empty] | Date Allotment Released: | 2019-03-12 | Date completed:
Kapalong | Suaon-Libuton | 1st Eng'g. Dist. | On-going | 2019-11-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS OF LOCAL ROADS & DRAINAGE DEVELOPMENT PROJECT(Provincewide) LS - 15,000,000.00 | [7 empty] | Date Started: | 2019-11-18
Asuncion | Saug-Sonlon Longanapan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS OF LOCAL ROADS & DRAINAGE DEVELOPMENT PROJECT(Provincewide) LS - 15,000,000.00 | Impv't. of Cross Drainage along Saug-Sonlon-Bdry. Longanapan |  | 20% DF CY 2019 | Road Drainage rehabiliated |  | ln.m | Admin | Project Cost: | 3000000 | Target Completion Date: |  | Program: | 3000000 | Planned: |  | No. of Persons: |  | For implementation
Asuncion | Saug-Sonlon Longanapan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS OF LOCAL ROADS & DRAINAGE DEVELOPMENT PROJECT(Provincewide) LS - 15,000,000.00 | [7 empty] | Project Engineer: | Pilotos | Revised Completion Date: | 0 | Allotment: | 3000000 | Revised: |  | No. of Man-days:
Asuncion | Saug-Sonlon Longanapan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS OF LOCAL ROADS & DRAINAGE DEVELOPMENT PROJECT(Provincewide) LS - 15,000,000.00 | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual:
Asuncion | Saug-Sonlon Longanapan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS OF LOCAL ROADS & DRAINAGE DEVELOPMENT PROJECT(Provincewide) LS - 15,000,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Asuncion | Saug-Sonlon Longanapan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS OF LOCAL ROADS & DRAINAGE DEVELOPMENT PROJECT(Provincewide) LS - 15,000,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Asuncion | Saug-Sonlon Longanapan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS OF LOCAL ROADS & DRAINAGE DEVELOPMENT PROJECT(Provincewide) LS - 15,000,000.00 | [7 empty] | Date Started:
Talaingod | Sto. Niño-Palma Gil | 1st Eng'g. Dist. | On-going | 2020-02-27 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS OF LOCAL ROADS & DRAINAGE DEVELOPMENT PROJECT(Provincewide) LS - 15,000,000.00 | Rehab./Impv't. of Sto. Niño-Palma Gil-Sitio Opao Provincial Road with Drainage |  | 20% DF CY 2019 | Road Drainage rehabiliated |  | km | Contract | Project Cost: | 3000000 | Target Completion Date: | 2020-05-07 | Program: | 3000000 | Planned: | 44.89% | No. of Persons: |  | On-going (Suspended dated March 14, 2020; Resumption Order dated May 25, 2020)
Talaingod | Sto. Niño-Palma Gil | 1st Eng'g. Dist. | On-going | 2020-02-27 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS OF LOCAL ROADS & DRAINAGE DEVELOPMENT PROJECT(Provincewide) LS - 15,000,000.00 | [7 empty] | Project Engineer: | Lumapat | Revised Completion Date: | 2020-07-17 | Allotment: | 3000000 | Revised: |  | No. of Man-days:
Talaingod | Sto. Niño-Palma Gil | 1st Eng'g. Dist. | On-going | 2020-02-27 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS OF LOCAL ROADS & DRAINAGE DEVELOPMENT PROJECT(Provincewide) LS - 15,000,000.00 | [7 empty] | Implementor: | Tagum Constrak | No. of days suspended: | 71 | Disbursement: |  | Actual: | 44.89%
Talaingod | Sto. Niño-Palma Gil | 1st Eng'g. Dist. | On-going | 2020-02-27 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS OF LOCAL ROADS & DRAINAGE DEVELOPMENT PROJECT(Provincewide) LS - 15,000,000.00 | [7 empty] | Duration: | 70 | No. of days extended: |  |  |  | Slippage: | 0%
Talaingod | Sto. Niño-Palma Gil | 1st Eng'g. Dist. | On-going | 2020-02-27 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS OF LOCAL ROADS & DRAINAGE DEVELOPMENT PROJECT(Provincewide) LS - 15,000,000.00 | [7 empty] | Date Allotment Released: | 2019-05-25 | Date completed:
Talaingod | Sto. Niño-Palma Gil | 1st Eng'g. Dist. | On-going | 2020-02-27 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS OF LOCAL ROADS & DRAINAGE DEVELOPMENT PROJECT(Provincewide) LS - 15,000,000.00 | [7 empty] | Date Started: | 2020-02-27
San Isidro | Linao | 1st Eng'g. Dist. | On-going | 2020-02-24 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS WATER SYSTEM DEVELOPMENT LS - P 9,750,000.00 | Construction of PWS, Bgry. Linao, San Isidro |  | 20% DF CY 2019 | Water System |  | ln.m | Admin | Project Cost: | 500000 | Target Completion Date: | 2020-04-23 23:46 | Program: | 500000 | Planned: | 99% | No. of Persons: | 8 | On-going (Suspended last April 5, 2020 due to COVID; resumption order dated May 4, 2020)
San Isidro | Linao | 1st Eng'g. Dist. | On-going | 2020-02-24 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS WATER SYSTEM DEVELOPMENT LS - P 9,750,000.00 | [7 empty] | Project Engineer: | Aclaracion | Revised Completion Date: | 2020-07-05 23:46 | Allotment: | 500000 | Revised: |  | No. of Man-days: | 120
San Isidro | Linao | 1st Eng'g. Dist. | On-going | 2020-02-24 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS WATER SYSTEM DEVELOPMENT LS - P 9,750,000.00 | [7 empty] | Implementor: | PEO | No. of days suspended: | 73 | Disbursement: | 216100 | Actual: | 99%
San Isidro | Linao | 1st Eng'g. Dist. | On-going | 2020-02-24 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS WATER SYSTEM DEVELOPMENT LS - P 9,750,000.00 | [7 empty] | Duration: | 60 | No. of days extended: |  |  |  | Slippage: | 0%
San Isidro | Linao | 1st Eng'g. Dist. | On-going | 2020-02-24 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS WATER SYSTEM DEVELOPMENT LS - P 9,750,000.00 | [7 empty] | Date Allotment Released: | 2019-06-19 | Date completed:
San Isidro | Linao | 1st Eng'g. Dist. | On-going | 2020-02-24 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS WATER SYSTEM DEVELOPMENT LS - P 9,750,000.00 | [7 empty] | Date Started: | 2020-02-24
San Isidro | Datu Balong | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS WATER SYSTEM DEVELOPMENT LS - P 9,750,000.00 | Construction of PWS, Brgy. Datu Balong, San Isidro |  | 20% DF CY 2019 | Water System |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | For declaration of savings because the spring water source is not feasible for development
San Isidro | Datu Balong | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS WATER SYSTEM DEVELOPMENT LS - P 9,750,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 500000 | Revised: |  | No. of Man-days:
San Isidro | Datu Balong | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS WATER SYSTEM DEVELOPMENT LS - P 9,750,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
San Isidro | Datu Balong | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS WATER SYSTEM DEVELOPMENT LS - P 9,750,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
San Isidro | Datu Balong | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS WATER SYSTEM DEVELOPMENT LS - P 9,750,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
San Isidro | Datu Balong | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS WATER SYSTEM DEVELOPMENT LS - P 9,750,000.00 | [7 empty] | Date Started:
San Isidro | Sagayen | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS WATER SYSTEM DEVELOPMENT LS - P 9,750,000.00 | Construction of PWS, Brgy. Sagayen, San Isidro |  | 20% DF CY 2019 | Water System |  |  | Contract | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | PO # 2020031340 - JJR Construction
San Isidro | Sagayen | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS WATER SYSTEM DEVELOPMENT LS - P 9,750,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 500000 | Revised: |  | No. of Man-days:
San Isidro | Sagayen | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS WATER SYSTEM DEVELOPMENT LS - P 9,750,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
San Isidro | Sagayen | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS WATER SYSTEM DEVELOPMENT LS - P 9,750,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
San Isidro | Sagayen | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS WATER SYSTEM DEVELOPMENT LS - P 9,750,000.00 | [7 empty] | Date Allotment Released: | 2019-09-10 | Date completed:
San Isidro | Sagayen | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS WATER SYSTEM DEVELOPMENT LS - P 9,750,000.00 | [7 empty] | Date Started:
Tagum City | Mankilam | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS WATER SYSTEM DEVELOPMENT LS - P 9,750,000.00 | Installation of Shallow Tube Wells & Const. of Machinery Shed |  | 20% DF CY 2019 | Water System |  |  | Admin | Project Cost: | 1600000 | Target Completion Date: |  | Program: | 1600000 | Planned: |  | No. of Persons: |  | Opening of BID for Negotiated 6/18,2020 to alpebel
Tagum City | Mankilam | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS WATER SYSTEM DEVELOPMENT LS - P 9,750,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 1600000 | Revised: |  | No. of Man-days:
Tagum City | Mankilam | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS WATER SYSTEM DEVELOPMENT LS - P 9,750,000.00 | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual:
Tagum City | Mankilam | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS WATER SYSTEM DEVELOPMENT LS - P 9,750,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Tagum City | Mankilam | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS WATER SYSTEM DEVELOPMENT LS - P 9,750,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Tagum City | Mankilam | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS WATER SYSTEM DEVELOPMENT LS - P 9,750,000.00 | [7 empty] | Date Started:
New Corella | Poblacion | 1st Eng'g. Dist. | On-going | 2020-03-02 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | Repair/Impv't. of Municipal Triball Hall, New Corella |  | 20% DF CY 2019 | Building |  | sq.m | Admin | Project Cost: | 1500000 | Target Completion Date: | 2020-06-12 23:46 | Program: | 1500000 | Planned: | 66.4% | No. of Persons: | 12 | On-going (Suspended last April 5, 2020 due to COVID; resumption order dated May 4, 2020)
New Corella | Poblacion | 1st Eng'g. Dist. | On-going | 2020-03-02 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | [7 empty] | Project Engineer: | Cahayag | Revised Completion Date: | 2020-07-10 23:46 | Allotment: | 1500000 | Revised: |  | No. of Man-days: | 180
New Corella | Poblacion | 1st Eng'g. Dist. | On-going | 2020-03-02 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | [7 empty] | Implementor: | PEO | No. of days suspended: | 28 | Disbursement: |  | Actual: | 47.31%
New Corella | Poblacion | 1st Eng'g. Dist. | On-going | 2020-03-02 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | [7 empty] | Duration: | 103 | No. of days extended: |  |  |  | Slippage: | -19.09%
New Corella | Poblacion | 1st Eng'g. Dist. | On-going | 2020-03-02 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
New Corella | Poblacion | 1st Eng'g. Dist. | On-going | 2020-03-02 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | [7 empty] | Date Started: | 2020-03-02
San Isidro | Sabangan | 1st Eng'g. Dist. | On-going | 2019-12-02 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | Const. of Municipal Tribal Hall, San Isidro |  | 20% DF CY 2019 | Building | 42 | sq.m | Admin | Project Cost: | 500000 | Target Completion Date: | 2020-02-19 23:46 | Program: | 500000 | Planned: | 81.44% | No. of Persons: | 8 | Completed as per physical accomplishment. Financial documents still on process.
San Isidro | Sabangan | 1st Eng'g. Dist. | On-going | 2019-12-02 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | [7 empty] | Project Engineer: | Aclaracion | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days: | 176
San Isidro | Sabangan | 1st Eng'g. Dist. | On-going | 2019-12-02 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | [7 empty] | Implementor: | PEO | No. of days suspended: | 28 | Disbursement: |  | Actual: | 81.44%
San Isidro | Sabangan | 1st Eng'g. Dist. | On-going | 2019-12-02 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | [7 empty] | Duration: | 80 | No. of days extended: |  |  |  | Slippage: | 0%
San Isidro | Sabangan | 1st Eng'g. Dist. | On-going | 2019-12-02 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | [7 empty] | Date Allotment Released: | 2019-01-15 | Date completed: | 2020-06-15
San Isidro | Sabangan | 1st Eng'g. Dist. | On-going | 2019-12-02 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | [7 empty] | Date Started: | 2019-12-02
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2019-12-02 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | Repair Bay of Disaster Quick Response Equipment @ PEO Compound, Gov't. Center, Mankilam, Tagum City |  | 20% DF CY 2019 | Building | 66 | sq.m | Admin | Project Cost: | 1000000 | Target Completion Date: | 2020-04-19 23:46 | Program: | 1000000 | Planned: | 74.7% | No. of Persons: | 5 | On-going (Suspended last April 5, 2020 due to COVID; resumption order dated May 4, 2020)
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2019-12-02 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | [7 empty] | Project Engineer: | Chua/Mucas | Revised Completion Date: | 2020-05-17 23:46 | Allotment: | 1000000 | Revised: |  | No. of Man-days: | 95
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2019-12-02 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | [7 empty] | Implementor: | PEO | No. of days suspended: | 28 | Disbursement: |  | Actual: | 74.7%
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2019-12-02 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | [7 empty] | Duration: | 140 | No. of days extended: |  |  |  | Slippage: | 0%
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2019-12-02 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | [7 empty] | Date Allotment Released: | 2019-01-31 | Date completed:
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2019-12-02 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | [7 empty] | Date Started: | 2019-12-02
Talaingod | Gupitan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | Const. of Multi-Purpose Hall Center (Cultural Heritage in Ancestral Domain of Ata-Manobo) |  | 20% DF CY 2019 | Building |  |  | Admin | Project Cost: | 3000000 | Target Completion Date: |  | Program: | 3000000 | Planned: |  | No. of Persons: |  | Fund re-aligned to GIDAS projects
Talaingod | Gupitan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 3000000 | Revised: |  | No. of Man-days:
Talaingod | Gupitan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Talaingod | Gupitan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Talaingod | Gupitan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Talaingod | Gupitan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | [7 empty] | Date Started:
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | Const. of IP Women's Multi-{Purpose Bldg.), Cabidiangan, Sto. Niño, Talaingod |  | 20% DF CY 2019 | Building |  |  | Admin | Project Cost: | 2000000 | Target Completion Date: |  | Program: | 2000000 | Planned: |  | No. of Persons: |  | Final abstract #0320200897 (Alpebel Builders)
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 2000000 | Revised: |  | No. of Man-days:
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual:
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | [7 empty] | Date Allotment Released: | 2019-05-15 | Date completed:
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | [7 empty] | Date Started:
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2020-02-03 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | Extension of PAGRO Training Center & Ground Dev't., Gov't. Center, Mankilam, Tagum City |  | 20% DF CY 2019 | Building |  | sq.m | Admin | Project Cost: | 1000000 | Target Completion Date: | 2020-04-23 | Program: | 1000000 | Planned: | 30.5% | No. of Persons: | 5 | On-going (Suspended last April 5, 2020 due to COVID; resumption order dated May 4, 2020)
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2020-02-03 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | [7 empty] | Project Engineer: | Chua/Mugas | Revised Completion Date: | 2020-05-21 | Allotment: | 1000000 | Revised: |  | No. of Man-days: | 57
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2020-02-03 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | [7 empty] | Implementor: | PEO | No. of days suspended: | 28 | Disbursement: |  | Actual: | 30.5%
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2020-02-03 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | [7 empty] | Duration: | 80 | No. of days extended: |  |  |  | Slippage: | 0%
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2020-02-03 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | [7 empty] | Date Allotment Released: | 2019-07-26 | Date completed:
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2020-02-03 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | [7 empty] | Date Started: | 2020-02-03
Tagum City | Mankilam | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | Construction of Abilidad Training Center, Gov't. Center, Mankilam, Tagum City |  | 20% DF CY 2019 | Building |  |  |  | Project Cost: | 7000000 | Target Completion Date: |  | Program: | 7000000 | Planned: |  | No. of Persons: |  | Fund re-aligned to GIDAS projects
Tagum City | Mankilam | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 7000000 | Revised: |  | No. of Man-days:
Tagum City | Mankilam | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual:
Tagum City | Mankilam | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Tagum City | Mankilam | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Tagum City | Mankilam | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | [7 empty] | Date Started:
New Corella | Suawon | 1st Eng'g. Dist. | On-going | 2019-12-09 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | Const. of 1 CL Bldg. @ Suawon ES, New Corella |  | 20% DF CY 2019 | Building | 82.65 | sq.m | Admin | Project Cost: | 1000000 | Target Completion Date: | 2020-04-21 23:46 | Program: | 1000000 | Planned: | 60.44% | No. of Persons: | 7 | On-going (Suspended last April 5, 2020 due to COVID; resumption order dated May 4, 2020)
New Corella | Suawon | 1st Eng'g. Dist. | On-going | 2019-12-09 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | [7 empty] | Project Engineer: | Miraflor | Revised Completion Date: | 2020-05-19 23:46 | Allotment: | 1000000 | Revised: |  | No. of Man-days: | 147
New Corella | Suawon | 1st Eng'g. Dist. | On-going | 2019-12-09 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | [7 empty] | Implementor: | PEO | No. of days suspended: | 28 | Disbursement: |  | Actual: | 60.44%
New Corella | Suawon | 1st Eng'g. Dist. | On-going | 2019-12-09 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | [7 empty] | Duration: | 135 | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | Suawon | 1st Eng'g. Dist. | On-going | 2019-12-09 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | [7 empty] | Date Allotment Released: | 2020-06-07 | Date completed:
New Corella | Suawon | 1st Eng'g. Dist. | On-going | 2019-12-09 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | [7 empty] | Date Started: | 2019-12-09
Talaingod | STo. Niño | 1st Eng'g. Dist. | On-going | 2020-03-02 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | Const. of Perimeter Fence at Sto. Niño Naseco Integrated School w/ Tugas Extension, Sto. Niño, Talaingod |  | 20% DF CY 2019 | Building |  | sq.m | Admin | Project Cost: | 2000000 | Target Completion Date: | 2020-06-09 23:46 | Program: | 2000000 | Planned: | 87.65% | No. of Persons: | 13 | On-going (Suspended last April 5, 2020 due to COVID; resumption order dated May 4, 2020)
Talaingod | STo. Niño | 1st Eng'g. Dist. | On-going | 2020-03-02 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | [7 empty] | Project Engineer: | Torrecampo | Revised Completion Date: | 2020-07-07 23:46 | Allotment: | 2000000 | Revised: |  | No. of Man-days: | 195
Talaingod | STo. Niño | 1st Eng'g. Dist. | On-going | 2020-03-02 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | [7 empty] | Implementor: | PEO | No. of days suspended: | 28 | Disbursement: |  | Actual: | 40.65%
Talaingod | STo. Niño | 1st Eng'g. Dist. | On-going | 2020-03-02 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | [7 empty] | Duration: | 100 | No. of days extended: |  |  |  | Slippage: | -47%
Talaingod | STo. Niño | 1st Eng'g. Dist. | On-going | 2020-03-02 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | [7 empty] | Date Allotment Released: | 2019-06-19 | Date completed:
Talaingod | STo. Niño | 1st Eng'g. Dist. | On-going | 2020-03-02 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | [7 empty] | Date Started: | 2020-03-02
Asuncion | New Bantayan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | Rehab. Of Multi-Purpose Hall, New Bantayan, Asuncion |  | 20% DF CY 2019 (STIMULUS) | Building |  |  | Admin | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | (Fund transferred to LGU.c /o Engr. Lilibeth Cuajao)
Asuncion | New Bantayan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 500000 | Revised: |  | No. of Man-days:
Asuncion | New Bantayan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Asuncion | New Bantayan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Asuncion | New Bantayan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Allotment Released: |  | Date completed:
Asuncion | New Bantayan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Started:
New Corella | El Salvador | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | Construction of Multi-Purpose Hall, El Salvador, New Corella |  | 20% DF CY 2019 (STIMULUS) | Building |  |  | MLGU | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Fund transferred to LGU March 23, 2019 c/o Engr. Dugoldugol
New Corella | El Salvador | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 500000 | Revised: |  | No. of Man-days:
New Corella | El Salvador | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
New Corella | El Salvador | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | El Salvador | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Allotment Released: |  | Date completed:
New Corella | El Salvador | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Started:
New Corella | Poblacion | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | Concreting of Drainage Canal , Pob., New Corella |  | 20% DF CY 2019 (STIMULUS) | Drainage |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Amended to Const. of 2 Storey Multi-Purpose Hall phase 3 (Brgy. Hall),Pob., New Corella (AIP 3rd revision CY 2019 / SB No. 4 CY 2019
New Corella | Poblacion | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 500000 | Revised: |  | No. of Man-days:
New Corella | Poblacion | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
New Corella | Poblacion | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | Poblacion | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Allotment Released: |  | Date completed:
New Corella | Poblacion | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Started:
New Corella | Cabidianan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | Rehab. Of Multi-Purpose Hall, Cabidianan, New Corella |  | 20% DF CY 2019 (STIMULUS) | Building |  |  | MLGU | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Fund transferred to LGU c/o Engr. Dugoldugol
New Corella | Cabidianan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 500000 | Revised: |  | No. of Man-days:
New Corella | Cabidianan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
New Corella | Cabidianan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | Cabidianan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Allotment Released: | 2019-02-20 | Date completed:
New Corella | Cabidianan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Started:
Talaingod | Gupitan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | Brgy. Electrification (Centro Gupitan), Gupitan, Talaingod |  | 20% DF CY 2019 (STIMULUS) | Electrification |  |  | MLGU | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Re-aligned to other stimulus projects that need additional funds to complete since the amount can not complete the project. Recommended for exact fund that can complete the project.
Talaingod | Gupitan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 500000 | Revised: |  | No. of Man-days:
Talaingod | Gupitan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Talaingod | Gupitan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Talaingod | Gupitan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Allotment Released: |  | Date completed:
Talaingod | Gupitan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Started:
Tagum City | Magugpo Poblacion | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | Rehab. of Evacuation Center, Magugpo Poblacion, Tagum City |  | 20% DF CY 2019 (STIMULUS) | Building |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Amended in the AIP 3rd revision CY 2019 /SB No. 4 CY 2019 changing the total project cost to P600,000.00
Tagum City | Magugpo Poblacion | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 500000 | Revised: |  | No. of Man-days:
Tagum City | Magugpo Poblacion | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Tagum City | Magugpo Poblacion | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Tagum City | Magugpo Poblacion | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Allotment Released: |  | Date completed:
Tagum City | Magugpo Poblacion | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Started:
Tagum City | San Agustin | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | Const. of Water System, San Agustin, Tagum City |  | 20% DF CY 2019 (STIMULUS) | Water System |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Re-aligned to other stimulus projects that need additional funds since there is no deed of donation for the proposed site.
Tagum City | San Agustin | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 500000 | Revised: |  | No. of Man-days:
Tagum City | San Agustin | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Tagum City | San Agustin | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Tagum City | San Agustin | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Allotment Released: |  | Date completed:
Tagum City | San Agustin | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Started:
Tagum City | Magugpo South | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | Const. of Brgy. Health Center, Magugpo South, Tagum City |  | 20% DF CY 2019 (STIMULUS) | Building |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Amended in the AIP 3rd revision CY 2019 /SB No. 4 CY 2019 changing the total project cost to P1,550,000.00
Tagum City | Magugpo South | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 500000 | Revised: |  | No. of Man-days:
Tagum City | Magugpo South | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Tagum City | Magugpo South | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Tagum City | Magugpo South | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Allotment Released: |  | Date completed:
Tagum City | Magugpo South | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Started:
Tagum City | Apokon | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | Rehab. Of Brgy. Health Center, Apokon, Tagum City |  | 20% DF CY 2019 (STIMULUS) | Building |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | For implementation (The brgy. council agreed not to pursue with the project if it will not be completed and needs additional funds)
Tagum City | Apokon | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 500000 | Revised: |  | No. of Man-days:
Tagum City | Apokon | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Tagum City | Apokon | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Tagum City | Apokon | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Allotment Released: | 2019-03-25 | Date completed:
Tagum City | Apokon | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Started:
Tagum City | Mankilam | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | Rehab. of Evacuation Center, Mankilam, Tagum City |  | 20% DF CY 2019 (STIMULUS) | Building |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | For implementation
Tagum City | Mankilam | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 500000 | Revised: |  | No. of Man-days:
Tagum City | Mankilam | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Tagum City | Mankilam | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Tagum City | Mankilam | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Allotment Released: | 2019-03-25 | Date completed:
Tagum City | Mankilam | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Started:
Tagum City | New Balamban | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | Rehab. of Evacuation Center, New Balambam, Tagum City |  | 20% DF CY 2019 (STIMULUS) | Building |  |  | Contract | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Final abstract #0320200899 (JJR Construction & Supply)
Tagum City | New Balamban | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 500000 | Revised: |  | No. of Man-days:
Tagum City | New Balamban | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Tagum City | New Balamban | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Tagum City | New Balamban | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Allotment Released: | 2019-09-10 | Date completed:
Tagum City | New Balamban | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Started:
Tagum City | Cuambogan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | Rehab. Of Multi-Purpose Hall, Cuambogan, Tagum City |  | 20% DF CY 2019 (STIMULUS) | Building |  |  | Contract | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | PO #2020031340 - JJR Construction
Tagum City | Cuambogan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 500000 | Revised: |  | No. of Man-days:
Tagum City | Cuambogan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Tagum City | Cuambogan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Tagum City | Cuambogan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Allotment Released: | 2019-09-10 | Date completed:
Tagum City | Cuambogan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Started:
Tagum City | Nueva Fuerza | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | Completion of Evacuation Center, Nueva Fuerza, Tagum City |  | 20% DF CY 2019 (STIMULUS) | Building |  |  | Contract | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | PO #2020031340 - JJR Construction
Tagum City | Nueva Fuerza | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 500000 | Revised: |  | No. of Man-days:
Tagum City | Nueva Fuerza | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Tagum City | Nueva Fuerza | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Tagum City | Nueva Fuerza | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Allotment Released: | 2019-09-10 | Date completed:
Tagum City | Nueva Fuerza | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Started:
Tagum City | Busaon | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | Completion. of Water System , Busaon, Tagum City |  | 20% DF CY 2019 (STIMULUS) | Water System |  |  | Contract | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | For implementation
Tagum City | Busaon | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 500000 | Revised: |  | No. of Man-days:
Tagum City | Busaon | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Tagum City | Busaon | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Tagum City | Busaon | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Allotment Released: | 2019-09-10 | Date completed:
Tagum City | Busaon | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Started:
Tagum City | Bincungan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | Const. of Drainage Canal, Bincungan, Tagum City |  | 20% DF CY 2019 (STIMULUS) | Drainage |  |  | Contract | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | PO #2020031340 - JJR Construction
Tagum City | Bincungan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 500000 | Revised: |  | No. of Man-days:
Tagum City | Bincungan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Tagum City | Bincungan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Tagum City | Bincungan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Allotment Released: | 2019-09-10 | Date completed:
Tagum City | Bincungan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Started:
Tagum City | Magugpo North | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | Rehab. of Evacuation Center, Magugpo North, Tagum City |  | 20% DF CY 2019 (STIMULUS) | Building |  |  | Contract | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | PO #2020031340 - JJR Construction
Tagum City | Magugpo North | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 500000 | Revised: |  | No. of Man-days:
Tagum City | Magugpo North | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Tagum City | Magugpo North | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Tagum City | Magugpo North | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Allotment Released: | 2019-09-10 | Date completed:
Tagum City | Magugpo North | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Started:
San Isidro | Pinamuno | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | Rehab. Of Water System at Purok Cabang & Mangga , Pinamuno, San Isidro |  | 20% DF CY 2019 (STIMULUS) | Water System |  |  | Contract | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | PO# 2020010025 (RLHV)
San Isidro | Pinamuno | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 500000 | Revised: |  | No. of Man-days:
San Isidro | Pinamuno | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
San Isidro | Pinamuno | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
San Isidro | Pinamuno | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Allotment Released: | 2019-12-06 | Date completed:
San Isidro | Pinamuno | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Started:
San Isidro | Igangon | 1st Eng'g. Dist. | On-going | 2020-05-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | Rehab. Of Water System , Igangon, San Isidro |  | 20% DF CY 2019 (STIMULUS) | Water System |  | ln.m | Admin | Project Cost: | 500000 | Target Completion Date: | 2020-07-17 | Program: | 500000 | Planned: | 12.26% | No. of Persons: | 25 | On-going
San Isidro | Igangon | 1st Eng'g. Dist. | On-going | 2020-05-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Project Engineer: | Kabinge | Revised Completion Date: | 2020-07-17 | Allotment: | 500000 | Revised: | 93.09% | No. of Man-days: | 375
San Isidro | Igangon | 1st Eng'g. Dist. | On-going | 2020-05-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: | 46.42%
San Isidro | Igangon | 1st Eng'g. Dist. | On-going | 2020-05-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Duration: | 60 | No. of days extended: |  |  |  | Slippage: | 93.09%
San Isidro | Igangon | 1st Eng'g. Dist. | On-going | 2020-05-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Allotment Released: | 2019-05-29 | Date completed:
San Isidro | Igangon | 1st Eng'g. Dist. | On-going | 2020-05-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Started: | 2020-05-18
New Corella | Del Monte | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | Rural Electrification , Del Monte, New Corella |  | 20% DF CY 2019 (STIMULUS) | Electrification |  |  |  | Project Cost: | 3000000 | Target Completion Date: |  | Program: | 3000000 | Planned: |  | No. of Persons: |  | For implementation
New Corella | Del Monte | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Project Engineer: | P.Bueno | Revised Completion Date: | 0 | Allotment: | 3000000 | Revised: |  | No. of Man-days:
New Corella | Del Monte | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
New Corella | Del Monte | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | Del Monte | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Allotment Released: |  | Date completed:
New Corella | Del Monte | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Started:
New Corella | San Roque | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | Rural Electrification at St. Bundok, San Roque, New Corella |  | 20% DF CY 2019 (STIMULUS) | Electrification |  |  |  | Project Cost: | 1000000 | Target Completion Date: |  | Program: | 1000000 | Planned: |  | No. of Persons: |  | Abstract # 0320201453
New Corella | San Roque | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Project Engineer: | P.Bueno | Revised Completion Date: | 0 | Allotment: | 1000000 | Revised: |  | No. of Man-days:
New Corella | San Roque | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
New Corella | San Roque | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | San Roque | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Allotment Released: |  | Date completed:
New Corella | San Roque | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Started:
Tagum City | Mankilam | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Anti - Crime & Government Itegration Project | Construction of Bahay Silangan for Reformation of Drug Personalities within The Military Camp/barracks, Brgy. Mankilam, Tagum City |  | 20% DF CY 2019 | Building |  |  |  | Project Cost: | 5000000 | Target Completion Date: |  | Program: | 5000000 | Planned: |  | No. of Persons: |  | Abstract #0620202232 - Post Qualification on process (ZULAR-A)
Tagum City | Mankilam | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Anti - Crime & Government Itegration Project | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 5000000 | Revised: |  | No. of Man-days:
Tagum City | Mankilam | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Anti - Crime & Government Itegration Project | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Tagum City | Mankilam | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Anti - Crime & Government Itegration Project | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Tagum City | Mankilam | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Anti - Crime & Government Itegration Project | [7 empty] | Date Allotment Released: |  | Date completed:
Tagum City | Mankilam | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Anti - Crime & Government Itegration Project | [7 empty] | Date Started:
New Corella | Poblacion | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (Special Protection & Intervention Program ) | Const. of Multi-Purpose Covered Court/Evacuation Center Ph. I, Duterte St., Poblacion, New Corella |  | 20% DF CY 2019 | Building |  |  |  | Project Cost: | 2000000 | Target Completion Date: |  | Program: | 2000000 | Planned: |  | No. of Persons: |  | Abstract #0720202481 - Post Qualification on pprocess (Royal Summit Infinity)
New Corella | Poblacion | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (Special Protection & Intervention Program ) | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 2000000 | Revised: |  | No. of Man-days:
New Corella | Poblacion | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (Special Protection & Intervention Program ) | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual:
New Corella | Poblacion | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (Special Protection & Intervention Program ) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | Poblacion | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (Special Protection & Intervention Program ) | [7 empty] | Date Allotment Released: |  | Date completed:
New Corella | Poblacion | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (Special Protection & Intervention Program ) | [7 empty] | Date Started:
New Corella | Poblacion | 1st Eng'g. Dist. | On-going | 2019-12-02 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Residential Care Facilities | Construction of Multi-Purpose Covered Court/Evacuation, Bahay Pag-Asa, New Corella, Ph.II (TF - P500,000.00) |  | 20% DF CY 2019 & TRUST FUND | Building |  | sq.m | Admin | Project Cost: | 2500000 | Target Completion Date: | 2020-04-15 | Program: | 2500000 | Planned: | 79.89% | No. of Persons: | 12 | On-going (Suspended last April 5, 2020 due to COVID; resumption order dated May 4, 2020)
New Corella | Poblacion | 1st Eng'g. Dist. | On-going | 2019-12-02 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Residential Care Facilities | [7 empty] | Project Engineer: | Mayang | Revised Completion Date: | 2020-08-30 | Allotment: | 2500000 | Revised: |  | No. of Man-days: | 180
New Corella | Poblacion | 1st Eng'g. Dist. | On-going | 2019-12-02 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Residential Care Facilities | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: |  | Actual: | 79.89%
New Corella | Poblacion | 1st Eng'g. Dist. | On-going | 2019-12-02 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Residential Care Facilities | [7 empty] | Duration: | 135 | No. of days extended: | 110 |  |  | Slippage: | 0%
New Corella | Poblacion | 1st Eng'g. Dist. | On-going | 2019-12-02 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Residential Care Facilities | [7 empty] | Date Allotment Released: | 2019-06-19 | Date completed:
New Corella | Poblacion | 1st Eng'g. Dist. | On-going | 2019-12-02 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Residential Care Facilities | [7 empty] | Date Started: | 2019-12-02
Provincewide | Provincewide | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Residential Care Facilities | Const. in Progress - Bldgs. And Other Structures |  | 20% DF CY 2019 | Building |  |  |  | Project Cost: | 2500000 | Target Completion Date: |  | Program: | 2500000 | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
Provincewide | Provincewide | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Residential Care Facilities | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 2500000 | Revised: |  | No. of Man-days:
Provincewide | Provincewide | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Residential Care Facilities | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual:
Provincewide | Provincewide | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Residential Care Facilities | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Provincewide | Provincewide | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Residential Care Facilities | [7 empty] | Date Allotment Released: |  | Date completed:
Provincewide | Provincewide | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Residential Care Facilities | [7 empty] | Date Started:
New Corella | Limbaan | 1st Eng'g. Dist. | On-going | 2019-03-20 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DISASTER PREVENTION AND MITIGATION - Flood Control and Slope Protection LS - P3,000,000.00 | Desilting of Limbaan Creek, New Corella |  | 5% CALAMITY FUND CY 2019 | creeks and canals deislted |  | ln.m | Admin | Project Cost: | 2000000 | Target Completion Date: | 2019-12-02 | Program: | 2000000 | Planned: |  | No. of Persons: |  | Suspended
New Corella | Limbaan | 1st Eng'g. Dist. | On-going | 2019-03-20 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DISASTER PREVENTION AND MITIGATION - Flood Control and Slope Protection LS - P3,000,000.00 | [7 empty] | Project Engineer: | Pilotos | Revised Completion Date: | 2019-12-02 | Allotment: | 2000000 | Revised: |  | No. of Man-days:
New Corella | Limbaan | 1st Eng'g. Dist. | On-going | 2019-03-20 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DISASTER PREVENTION AND MITIGATION - Flood Control and Slope Protection LS - P3,000,000.00 | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual:
New Corella | Limbaan | 1st Eng'g. Dist. | On-going | 2019-03-20 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DISASTER PREVENTION AND MITIGATION - Flood Control and Slope Protection LS - P3,000,000.00 | [7 empty] | Duration: | 257 | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | Limbaan | 1st Eng'g. Dist. | On-going | 2019-03-20 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DISASTER PREVENTION AND MITIGATION - Flood Control and Slope Protection LS - P3,000,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
New Corella | Limbaan | 1st Eng'g. Dist. | On-going | 2019-03-20 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DISASTER PREVENTION AND MITIGATION - Flood Control and Slope Protection LS - P3,000,000.00 | [7 empty] | Date Started: | 2019-03-20
kapalong | Mabantao-Florida | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Revitment of Dike and Slope Protection LS - P3,000,000.00 | Slope Protection Along Kapalong-Mabantao, Florida |  | 5% CALAMITY FUND CY 2019 | creeks and canals deislted |  |  |  | Project Cost: | 1000000 | Target Completion Date: |  | Program: | 1000000 | Planned: |  | No. of Persons: |  | For cancellation funded to DPWH. Budget Transferred to 5% Calamity Fund- Rehab and Recovery
kapalong | Mabantao-Florida | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Revitment of Dike and Slope Protection LS - P3,000,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 1000000 | Revised: |  | No. of Man-days:
kapalong | Mabantao-Florida | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Revitment of Dike and Slope Protection LS - P3,000,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
kapalong | Mabantao-Florida | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Revitment of Dike and Slope Protection LS - P3,000,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
kapalong | Mabantao-Florida | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Revitment of Dike and Slope Protection LS - P3,000,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
kapalong | Mabantao-Florida | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Revitment of Dike and Slope Protection LS - P3,000,000.00 | [7 empty] | Date Started:
Asuncion | New Boholano-New Loon | 1st Eng'g. Dist. | On-going | 2019-11-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Improvement of bridges and cross drainage LS - P3,000,000.00 | Impv't. of Jct. New Boholano - New Loon Cross Drainage |  | 5% CALAMITY FUND CY 2019 | Drainage |  | km | Admin | Project Cost: | 2000000 | Target Completion Date: | 2020-02-16 | Program: | 2000000 | Planned: | 42.27% | No. of Persons: |  | Suspended due to availability of equipment
Asuncion | New Boholano-New Loon | 1st Eng'g. Dist. | On-going | 2019-11-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Improvement of bridges and cross drainage LS - P3,000,000.00 | [7 empty] | Project Engineer: | Pilotos | Revised Completion Date: | 2020-02-16 | Allotment: | 2000000 | Revised: |  | No. of Man-days:
Asuncion | New Boholano-New Loon | 1st Eng'g. Dist. | On-going | 2019-11-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Improvement of bridges and cross drainage LS - P3,000,000.00 | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: | 31.7%
Asuncion | New Boholano-New Loon | 1st Eng'g. Dist. | On-going | 2019-11-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Improvement of bridges and cross drainage LS - P3,000,000.00 | [7 empty] | Duration: | 90 | No. of days extended: |  |  |  | Slippage: | -10.57%
Asuncion | New Boholano-New Loon | 1st Eng'g. Dist. | On-going | 2019-11-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Improvement of bridges and cross drainage LS - P3,000,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Asuncion | New Boholano-New Loon | 1st Eng'g. Dist. | On-going | 2019-11-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Improvement of bridges and cross drainage LS - P3,000,000.00 | [7 empty] | Date Started: | 2019-11-18
Asuncion | Saug Sonlon-Longanapan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Improvement of bridges and cross drainage LS - P3,000,000.00 | Impv't. of Jct. Saug-Sonlon-Bdry. Longanapan Cross Drainage |  | 5% CALAMITY FUND CY 2019 | Road |  |  |  | Project Cost: | 1000000 | Target Completion Date: |  | Program: | 1000000 | Planned: |  | No. of Persons: |  | For implementation
Asuncion | Saug Sonlon-Longanapan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Improvement of bridges and cross drainage LS - P3,000,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 1000000 | Revised: |  | No. of Man-days:
Asuncion | Saug Sonlon-Longanapan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Improvement of bridges and cross drainage LS - P3,000,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Asuncion | Saug Sonlon-Longanapan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Improvement of bridges and cross drainage LS - P3,000,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Asuncion | Saug Sonlon-Longanapan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Improvement of bridges and cross drainage LS - P3,000,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Asuncion | Saug Sonlon-Longanapan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Improvement of bridges and cross drainage LS - P3,000,000.00 | [7 empty] | Date Started:
Tagum City | San Miguel | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DISASTER REHABILITATION & RECOVERY PROGRAM - Building Back Better Project | Disiltation of Tagum Creek |  | 5% CALAMITY FUND CY 2019 | Creek |  |  | Admin | Project Cost: | 2000000 | Target Completion Date: |  | Program: | 2000000 | Planned: |  | No. of Persons: |  | Waiting for the delivery of materials
Tagum City | San Miguel | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DISASTER REHABILITATION & RECOVERY PROGRAM - Building Back Better Project | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 2000000 | Revised: |  | No. of Man-days:
Tagum City | San Miguel | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DISASTER REHABILITATION & RECOVERY PROGRAM - Building Back Better Project | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual:
Tagum City | San Miguel | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DISASTER REHABILITATION & RECOVERY PROGRAM - Building Back Better Project | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Tagum City | San Miguel | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DISASTER REHABILITATION & RECOVERY PROGRAM - Building Back Better Project | [7 empty] | Date Allotment Released: |  | Date completed:
Tagum City | San Miguel | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DISASTER REHABILITATION & RECOVERY PROGRAM - Building Back Better Project | [7 empty] | Date Started:
Asuncion | Pamacaun-Lasang-banate | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DISASTER REHABILITATION & RECOVERY PROGRAM - Building Back Better Project | Rehabilitation of Pamacaun-Lasang-Banate Provincial Road |  | 5% CALAMITY FUND CY 2019 | Road |  |  | Admin | Project Cost: | 1500000 | Target Completion Date: |  | Program: | 1500000 | Planned: |  | No. of Persons: |  | For implementation
Asuncion | Pamacaun-Lasang-banate | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DISASTER REHABILITATION & RECOVERY PROGRAM - Building Back Better Project | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 1500000 | Revised: |  | No. of Man-days:
Asuncion | Pamacaun-Lasang-banate | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DISASTER REHABILITATION & RECOVERY PROGRAM - Building Back Better Project | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Asuncion | Pamacaun-Lasang-banate | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DISASTER REHABILITATION & RECOVERY PROGRAM - Building Back Better Project | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Asuncion | Pamacaun-Lasang-banate | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DISASTER REHABILITATION & RECOVERY PROGRAM - Building Back Better Project | [7 empty] | Date Allotment Released: |  | Date completed:
Asuncion | Pamacaun-Lasang-banate | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DISASTER REHABILITATION & RECOVERY PROGRAM - Building Back Better Project | [7 empty] | Date Started:
New Corella | Del Pilar | 1st Eng'g. Dist. | On-going | 2020-02-17 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DISASTER REHABILITATION & RECOVERY PROGRAM - Building Back Better Project | Rehabilitation of Del Pilar Jct. Silangan |  | 5% CALAMITY FUND CY 2019 | Road |  | km | Admin | Project Cost: | 1500000 | Target Completion Date: | 2020-03-27 23:46 | Program: | 1500000 | Planned: | 81.11% | No. of Persons: | 4 | Suspended dated June 1, 2020 due to rainy days
New Corella | Del Pilar | 1st Eng'g. Dist. | On-going | 2020-02-17 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DISASTER REHABILITATION & RECOVERY PROGRAM - Building Back Better Project | [7 empty] | Project Engineer: | Gone | Revised Completion Date: | 2020-06-15 23:46 | Allotment: | 1500000 | Revised: |  | No. of Man-days: | 40
New Corella | Del Pilar | 1st Eng'g. Dist. | On-going | 2020-02-17 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DISASTER REHABILITATION & RECOVERY PROGRAM - Building Back Better Project | [7 empty] | Implementor: | PEO | No. of days suspended: | 29 | Disbursement: |  | Actual: | 81.11%
New Corella | Del Pilar | 1st Eng'g. Dist. | On-going | 2020-02-17 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DISASTER REHABILITATION & RECOVERY PROGRAM - Building Back Better Project | [7 empty] | Duration: | 40 | No. of days extended: | 51 |  |  | Slippage: | 0%
New Corella | Del Pilar | 1st Eng'g. Dist. | On-going | 2020-02-17 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DISASTER REHABILITATION & RECOVERY PROGRAM - Building Back Better Project | [7 empty] | Date Allotment Released: | 2019-07-26 | Date completed:
New Corella | Del Pilar | 1st Eng'g. Dist. | On-going | 2020-02-17 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DISASTER REHABILITATION & RECOVERY PROGRAM - Building Back Better Project | [7 empty] | Date Started: | 2020-02-17
kapalong | Mabantao-Florida | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DISASTER REHABILITATION & RECOVERY PROGRAM - Building Back Better Project | Rehabilitation of Libuganon River along Kapalong Mabantao-Florida Provincial Road |  | 5% CALAMITY FUND CY 2019 | Road |  |  | Admin | Project Cost: | 900000 |  |  | Program: | 900000 | Planned: |  | No. of Persons: |  | For implementation
kapalong | Mabantao-Florida | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DISASTER REHABILITATION & RECOVERY PROGRAM - Building Back Better Project | [7 empty] | Project Engineer: |  |  |  | Allotment: | 900000 | Revised: |  | No. of Man-days:
kapalong | Mabantao-Florida | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DISASTER REHABILITATION & RECOVERY PROGRAM - Building Back Better Project | [7 empty] | Implementor: |  |  |  | Disbursement: |  | Actual:
kapalong | Mabantao-Florida | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DISASTER REHABILITATION & RECOVERY PROGRAM - Building Back Better Project | [7 empty] | Duration: | [5 empty] | Slippage: | 0%
kapalong | Mabantao-Florida | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DISASTER REHABILITATION & RECOVERY PROGRAM - Building Back Better Project | [7 empty] | Date Allotment Released:
kapalong | Mabantao-Florida | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DISASTER REHABILITATION & RECOVERY PROGRAM - Building Back Better Project | [7 empty] | Date Started:
New Corella | Mesaoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DISASTER REHABILITATION & RECOVERY PROGRAM - Building Back Better Project | Rehabilitation of Mesaoy-Jct. Mahayahay Road |  | 5% CALAMITY FUND CY 2019 | Road |  |  | Admin | Project Cost: | 1000000 | Target Completion Date: |  | Program: | 1000000 | Planned: |  | No. of Persons: |  | For implementation
New Corella | Mesaoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DISASTER REHABILITATION & RECOVERY PROGRAM - Building Back Better Project | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 1000000 | Revised: |  | No. of Man-days:
New Corella | Mesaoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DISASTER REHABILITATION & RECOVERY PROGRAM - Building Back Better Project | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
New Corella | Mesaoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DISASTER REHABILITATION & RECOVERY PROGRAM - Building Back Better Project | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | Mesaoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DISASTER REHABILITATION & RECOVERY PROGRAM - Building Back Better Project | [7 empty] | Date Allotment Released: |  | Date completed:
New Corella | Mesaoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DISASTER REHABILITATION & RECOVERY PROGRAM - Building Back Better Project | [7 empty] | Date Started:
New Corella | Sta. Fe - Mambing | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DISASTER REHABILITATION & RECOVERY PROGRAM - Building Back Better Project | Rehabilitation of Sta. Fe- Mambing Road & Slope Protection |  | 5% CALAMITY FUND CY 2019 | Road |  |  | Admin | Project Cost: | 1320000 | Target Completion Date: |  | Program: | 1320000 | Planned: |  | No. of Persons: |  | For implementation
New Corella | Sta. Fe - Mambing | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DISASTER REHABILITATION & RECOVERY PROGRAM - Building Back Better Project | [7 empty] | Project Engineer: | Pilotos | Revised Completion Date: | 0 | Allotment: | 1320000 | Revised: |  | No. of Man-days:
New Corella | Sta. Fe - Mambing | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DISASTER REHABILITATION & RECOVERY PROGRAM - Building Back Better Project | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual:
New Corella | Sta. Fe - Mambing | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DISASTER REHABILITATION & RECOVERY PROGRAM - Building Back Better Project | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | Sta. Fe - Mambing | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DISASTER REHABILITATION & RECOVERY PROGRAM - Building Back Better Project | [7 empty] | Date Allotment Released: |  | Date completed:
New Corella | Sta. Fe - Mambing | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DISASTER REHABILITATION & RECOVERY PROGRAM - Building Back Better Project | [7 empty] | Date Started:
Asuncion | San Agustin | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DISASTER REHABILITATION & RECOVERY PROGRAM - Building Back Better Project | Rehabilitation of Canal Lining and Slope Protection at San Agustin E/S, San Agustin, Tagum City |  | 5% CALAMITY FUND CY 2019 | Drainage |  |  | Admin | Project Cost: | 350000 | Target Completion Date: |  | Program: | 350000 | Planned: |  | No. of Persons: |  | For implementation
Asuncion | San Agustin | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DISASTER REHABILITATION & RECOVERY PROGRAM - Building Back Better Project | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 350000 | Revised: |  | No. of Man-days:
Asuncion | San Agustin | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DISASTER REHABILITATION & RECOVERY PROGRAM - Building Back Better Project | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Asuncion | San Agustin | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DISASTER REHABILITATION & RECOVERY PROGRAM - Building Back Better Project | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Asuncion | San Agustin | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DISASTER REHABILITATION & RECOVERY PROGRAM - Building Back Better Project | [7 empty] | Date Allotment Released: |  | Date completed:
Asuncion | San Agustin | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DISASTER REHABILITATION & RECOVERY PROGRAM - Building Back Better Project | [7 empty] | Date Started:
Asuncion | Doña Andrea | 1st Eng'g. Dist. | On-going | 2020-02-17 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DILG | Construction of Halfway House, Brgy. Doña Andrea, Asuncion |  | DILG | Building |  | sq.m | Admin | Project Cost: | 5000000 | Target Completion Date: | 2020-08-14 23:59 | Program: | 5000000 | Planned: | 43.45% | No. of Persons: | 6 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 6, 2020)
Asuncion | Doña Andrea | 1st Eng'g. Dist. | On-going | 2020-02-17 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DILG | [7 empty] | Project Engineer: | Dadula | Revised Completion Date: | 2020-09-12 23:59 | Allotment: | 5000000 | Revised: |  | No. of Man-days: | 138
Asuncion | Doña Andrea | 1st Eng'g. Dist. | On-going | 2020-02-17 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DILG | [7 empty] | Implementor: | PEO | No. of days suspended: | 29 | Disbursement: |  | Actual: | 43.45%
Asuncion | Doña Andrea | 1st Eng'g. Dist. | On-going | 2020-02-17 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DILG | [7 empty] | Duration: | 180 | No. of days extended: |  |  |  | Slippage: | -0.004%
Asuncion | Doña Andrea | 1st Eng'g. Dist. | On-going | 2020-02-17 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DILG | [7 empty] | Date Allotment Released: | CY 2019 | Date completed:
Asuncion | Doña Andrea | 1st Eng'g. Dist. | On-going | 2020-02-17 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DILG | [7 empty] | Date Started: | 2020-02-17
Asuncion | Cambanogoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Lot Purchase | Purchase of Lot for Cemetery, Cambanogoy, Asuncion |  | SUPPLEMENTAL BUDGET NO. 1 CY 2019 (STIMULUS) | Land |  |  |  | Project Cost: | 1500000 | Target Completion Date: |  | Program: | 1500000 | Planned: |  | No. of Persons: |  | Documents for fund transfer to be complied by the LGUs. Letter sent dated June 18, 2019
Asuncion | Cambanogoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Lot Purchase | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 1500000 | Revised: |  | No. of Man-days:
Asuncion | Cambanogoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Lot Purchase | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Asuncion | Cambanogoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Lot Purchase | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Asuncion | Cambanogoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Lot Purchase | [7 empty] | Date Allotment Released: |  | Date completed:
Asuncion | Cambanogoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Lot Purchase | [7 empty] | Date Started:
New Corella | San Roque | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Lot Purchase | Purchase of Lot for Cemetery, San Roque, New Corella |  | SUPPLEMENTAL BUDGET NO. 1 CY 2019 (STIMULUS) | Land |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Documents for fund transfer to be complied by the LGUs. Letter sent dated June 18, 2019
New Corella | San Roque | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Lot Purchase | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 500000 | Revised: |  | No. of Man-days:
New Corella | San Roque | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Lot Purchase | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
New Corella | San Roque | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Lot Purchase | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | San Roque | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Lot Purchase | [7 empty] | Date Allotment Released: |  | Date completed:
New Corella | San Roque | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Lot Purchase | [7 empty] | Date Started:
Asuncion | Sagayen | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | Rehab/Impvt of Gymnasium, Sagayen, Asuncion |  | SUPPLEMENTAL BUDGET NO. 1 CY 2019 (STIMULUS) | Building |  |  |  | Project Cost: | 1500000 | Target Completion Date: |  | Program: | 1500000 | Planned: |  | No. of Persons: |  | Final Abstract # 0320200900 (Alpebel Builders & Supply Corp.)
Asuncion | Sagayen | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 1500000 | Revised: |  | No. of Man-days:
Asuncion | Sagayen | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Asuncion | Sagayen | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Asuncion | Sagayen | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Allotment Released: |  | Date completed:
Asuncion | Sagayen | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Started:
New Corella | New Sambog | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | Purchase of Lot for Resettlement Site, New Sambog, New Corella |  | SUPPLEMENTAL BUDGET NO. 1 CY 2019 (STIMULUS) | Land |  |  |  | Project Cost: | 1500000 | Target Completion Date: |  | Program: | 1500000 | Planned: |  | No. of Persons: |  | for fund transfer. Waiting for LGU documents. Liquidation of previous fund transfer for the water system project of LGU.
New Corella | New Sambog | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 1500000 | Revised: |  | No. of Man-days:
New Corella | New Sambog | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
New Corella | New Sambog | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | New Sambog | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Allotment Released: |  | Date completed:
New Corella | New Sambog | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Started:
Asuncion | Sagayen | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | Installation of Street Lights at Prk 1,2,3,4, Sagayen, Asuncion |  | SUPPLEMENTAL BUDGET NO. 1 CY 2019 (STIMULUS) | Electrification |  |  |  | Project Cost: | 1000000 | Target Completion Date: |  | Program: | 1000000 | Planned: |  | No. of Persons: |  | Purchase Order # 2019113377 (Tagum Builders)
Asuncion | Sagayen | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 1000000 | Revised: |  | No. of Man-days:
Asuncion | Sagayen | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Asuncion | Sagayen | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Asuncion | Sagayen | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Allotment Released: |  | Date completed:
Asuncion | Sagayen | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Started:
Asuncion | Concepcion | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | Rehab/Imprvt. Of FMR, Prk 3,7, & 8, Concepcion, Asuncion |  | SUPPLEMENTAL BUDGET NO. 1 CY 2019 (STIMULUS) | Road |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Waiting for equipment availability as of Feb. 5, 2020 report submitted by Engr. Cuajao
Asuncion | Concepcion | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 500000 | Revised: |  | No. of Man-days:
Asuncion | Concepcion | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Asuncion | Concepcion | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Asuncion | Concepcion | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Allotment Released: |  | Date completed:
Asuncion | Concepcion | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Started:
New Corella | San Jose | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | Farm to Market Road, San Jose, New Corella |  | SUPPLEMENTAL BUDGET NO. 1 CY 2019 (STIMULUS) | Road |  |  |  | Project Cost: | 2000000 | Target Completion Date: |  | Program: | 2000000 | Planned: |  | No. of Persons: |  | For cancellation
New Corella | San Jose | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 2000000 | Revised: |  | No. of Man-days:
New Corella | San Jose | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
New Corella | San Jose | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | San Jose | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Allotment Released: |  | Date completed:
New Corella | San Jose | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Started:
New Corella | New Sambog | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | Const. of Water System, New Sambog, New Corella |  | SUPPLEMENTAL BUDGET NO. 1 CY 2019 (STIMULUS) | Water System |  |  | MLGU | Project Cost: | 1000000 | Target Completion Date: |  | Program: | 1000000 | Planned: |  | No. of Persons: |  | Fund transferred to LGU
New Corella | New Sambog | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 1000000 | Revised: |  | No. of Man-days:
New Corella | New Sambog | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
New Corella | New Sambog | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | New Sambog | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Allotment Released: |  | Date completed:
New Corella | New Sambog | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Started:
New Corella | Limbaan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | Const. of Drainage Canal from Prk. 3, 1-A, 2-A to Prk 1-B, Brgy Site (Ph. 2), Limbaan, New Corella |  | SUPPLEMENTAL BUDGET NO. 1 CY 2019 (STIMULUS) | Flood Control - Drainage |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | POW preparation on going c/o PDPM
New Corella | Limbaan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 500000 | Revised: |  | No. of Man-days:
New Corella | Limbaan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
New Corella | Limbaan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | Limbaan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Allotment Released: |  | Date completed:
New Corella | Limbaan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Started:
New Corella | Patrocenio | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | Const. of FMR from Prk 1 to Sitio Magsaysay via Pundol & Prk 4, Patrocenio, New Corella |  | SUPPLEMENTAL BUDGET NO. 1 CY 2019 (STIMULUS) | Road |  |  |  | Project Cost: | 2000000 | Target Completion Date: |  | Program: | 2000000 | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
New Corella | Patrocenio | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 2000000 | Revised: |  | No. of Man-days:
New Corella | Patrocenio | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
New Corella | Patrocenio | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | Patrocenio | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Allotment Released: |  | Date completed:
New Corella | Patrocenio | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Started:
New Corella | San Jose | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | Const. of Multi-Purpose Pavement, San Jose, New Corella |  | SUPPLEMENTAL BUDGET NO. 1 CY 2019 (STIMULUS) | Building |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | POW approved but allotment not yet requested waiting for deed of donation c/o Engr. Canillada
New Corella | San Jose | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 500000 | Revised: |  | No. of Man-days:
New Corella | San Jose | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
New Corella | San Jose | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | San Jose | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Allotment Released: |  | Date completed:
New Corella | San Jose | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Started:
Asuncion | Buan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | Const. of Multipurpose Covered Court, Buan, Asuncion |  | SUPPLEMENTAL BUDGET NO. 1 CY 2019 (STIMULUS) | Covered Court |  |  | MLGU | Project Cost: | 2500000 | Target Completion Date: |  | Program: | 2500000 | Planned: |  | No. of Persons: |  | Fund transferred to LGU
Asuncion | Buan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 2500000 | Revised: |  | No. of Man-days:
Asuncion | Buan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Asuncion | Buan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Asuncion | Buan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Allotment Released: | 2019-06-26 | Date completed:
Asuncion | Buan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Started:
Asuncion | Pamacaun | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | Const. of Multipurpose Covered Court, Pamacaun, Asuncion |  | SUPPLEMENTAL BUDGET NO. 1 CY 2019 (STIMULUS) | Covered Court |  |  | MLGU | Project Cost: | 2500000 | Target Completion Date: |  | Program: | 2500000 | Planned: |  | No. of Persons: |  | Fund transferred to LGU
Asuncion | Pamacaun | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 2500000 | Revised: |  | No. of Man-days:
Asuncion | Pamacaun | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Asuncion | Pamacaun | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Asuncion | Pamacaun | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Allotment Released: | 2019-05-29 | Date completed:
Asuncion | Pamacaun | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Started:
New Corella | Poblacion | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | Const. of 2 Storey Multi purpose Hall Ph.2 (Brgy. Hall) , Poblacion, New Corella |  | SUPPLEMENTAL BUDGET NO. 1 CY 2019 (STIMULUS) | Building |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
New Corella | Poblacion | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 500000 | Revised: |  | No. of Man-days:
New Corella | Poblacion | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
New Corella | Poblacion | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | Poblacion | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Allotment Released: |  | Date completed:
New Corella | Poblacion | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Started:
New Corella | Patrocenio | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | Expansion of Multi-Purpose Hall ( Brgy. Hall), Patrocenio, New Corella |  | SUPPLEMENTAL BUDGET NO. 1 CY 2019 (STIMULUS) | Building |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Purchase Order # 2020020796 (JJR Construction)
New Corella | Patrocenio | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 500000 | Revised: |  | No. of Man-days:
New Corella | Patrocenio | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
New Corella | Patrocenio | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | Patrocenio | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Allotment Released: |  | Date completed:
New Corella | Patrocenio | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Started:
New Corella | Poblacion | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | Rehabilitation of Water System in PEEDO-LPRRC, Brgy. Poblacion, New Corella |  | SUPPLEMENTAL BUDGET NO. 1 CY 2019 (STIMULUS) | Water System |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Purchase Order # 2020010009 (ANCOR Water Resources)
New Corella | Poblacion | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 500000 | Revised: |  | No. of Man-days:
New Corella | Poblacion | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
New Corella | Poblacion | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | Poblacion | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Allotment Released: |  | Date completed:
New Corella | Poblacion | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Started:
Talaingod | Salawao-Sto. Niño | 1st Eng'g. Dist. | On-going | 2020-06-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | Provincial Livestock & Poultry Multiplier Farm Road Network Construction, Sitio Salawao, Sto. Niño, Talaingod |  | SUPPLEMENTAL BUDGET NO. 1 CY 2019 (STIMULUS) | Conc. Pavement |  | sq.m | Admin | Project Cost: | 5500000 | Target Completion Date: | 2020-07-13 23:46 | Program: | 5500000 | Planned: | 26.35% | No. of Persons: | 15 | On-going (For time extension)
Talaingod | Salawao-Sto. Niño | 1st Eng'g. Dist. | On-going | 2020-06-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Project Engineer: | Pasiona/Juan | Revised Completion Date: | 2020-08-10 23:46 | Allotment: | 5500000 | Revised: |  | No. of Man-days: | 225
Talaingod | Salawao-Sto. Niño | 1st Eng'g. Dist. | On-going | 2020-06-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Implementor: | PEO | No. of days suspended: | 28 | Disbursement: | 1449250 | Actual: | 26.35%
Talaingod | Salawao-Sto. Niño | 1st Eng'g. Dist. | On-going | 2020-06-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Duration: | 120 | No. of days extended: |  |  |  | Slippage: | 0%
Talaingod | Salawao-Sto. Niño | 1st Eng'g. Dist. | On-going | 2020-06-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Allotment Released: | CY 2019 | Date completed:
Talaingod | Salawao-Sto. Niño | 1st Eng'g. Dist. | On-going | 2020-06-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Started: | 2020-03-16
Talaingod | Tapayanon | 1st Eng'g. Dist. | On-going | 2019-11-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | Proposed Road Opening of Tawinian-Tapayanon Road Section |  | SUPPLEMENTAL BUDGET NO. 4 CY 2019 (STIMULUS) | Road |  | km | Admin | Project Cost: | 10000000 | Target Completion Date: | 2020-09-18 23:46 | Program: | 10000000 | Planned: | 27.08% | No. of Persons: | 5 | On-going (Suspended last April 5, 2020 due to COVID; resumption order dated May 4, 2020); Equipment Rental 1 unit Backhoe (Bidding July 16, 2020)
Talaingod | Tapayanon | 1st Eng'g. Dist. | On-going | 2019-11-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Project Engineer: | Garcia | Revised Completion Date: | 2020-10-16 23:46 | Allotment: | 10000000 | Revised: |  | No. of Man-days: | 319
Talaingod | Tapayanon | 1st Eng'g. Dist. | On-going | 2019-11-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Implementor: | PEO | No. of days suspended: | 28 | Disbursement: |  | Actual: | 27.08%
Talaingod | Tapayanon | 1st Eng'g. Dist. | On-going | 2019-11-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Duration: | 306 | No. of days extended: |  |  |  | Slippage: | 0%
Talaingod | Tapayanon | 1st Eng'g. Dist. | On-going | 2019-11-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Allotment Released: | 2019-11-15 | Date completed:
Talaingod | Tapayanon | 1st Eng'g. Dist. | On-going | 2019-11-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Started: | 2019-11-18
kapalong | Maniki | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | Completion of Brgy. Health Center, Maniki, Kapalong |  | SUPPLEMENTAL BUDGET NO. 4 CY 2019 (STIMULUS) | Building |  |  |  | Project Cost: | 627000 | Target Completion Date: |  | Program: | 627000 | Planned: |  | No. of Persons: |  | PROJECT Was funded by LGU, Kapalong
kapalong | Maniki | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 627000 | Revised: |  | No. of Man-days:
kapalong | Maniki | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
kapalong | Maniki | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
kapalong | Maniki | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Allotment Released: |  | Date completed:
kapalong | Maniki | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Started:
Asuncion | New Santiago | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | Construction of Potable Water System at Purok 6, New Santiago, Asuncion |  | SUPPLEMENTAL BUDGET NO. 4 CY 2019 (STIMULUS) | Water System |  |  | contract | Project Cost: | 1000000 | Target Completion Date: |  | Program: | 1000000 | Planned: |  | No. of Persons: |  | Change of POW to Contract
Asuncion | New Santiago | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 1000000 | Revised: |  | No. of Man-days:
Asuncion | New Santiago | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Asuncion | New Santiago | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Asuncion | New Santiago | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Allotment Released: |  | Date completed:
Asuncion | New Santiago | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Started:
New Corella | Poblacion | 1st Eng'g. Dist. | On-going | 2019-11-25 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | Construction of Children's Playground with Amenities, Poblacion, New Corella |  | SUPPLEMENTAL BUDGET NO. 4 CY 2019 (STIMULUS) | Building |  | sq.m | Admin | Project Cost: | 2500000 | Target Completion Date: | 2020-03-03 23:59 | Program: | 2500000 | Planned: | 46.63% | No. of Persons: | 10 | On-going (Suspended effective April 5, 2020 due to COVID; resumption order dated May 4, 2020)
New Corella | Poblacion | 1st Eng'g. Dist. | On-going | 2019-11-25 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Project Engineer: | Mayang | Revised Completion Date: | 2020-04-30 23:59 | Allotment: | 2500000 | Revised: |  | No. of Man-days: | 150
New Corella | Poblacion | 1st Eng'g. Dist. | On-going | 2019-11-25 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Implementor: | PEO | No. of days suspended: | 28 | Disbursement: | 1029250 | Actual: | 46.63%
New Corella | Poblacion | 1st Eng'g. Dist. | On-going | 2019-11-25 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Duration: | 100 | No. of days extended: | 30 |  |  | Slippage: | 0%
New Corella | Poblacion | 1st Eng'g. Dist. | On-going | 2019-11-25 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Allotment Released: | 2019-12-06 | Date completed:
New Corella | Poblacion | 1st Eng'g. Dist. | On-going | 2019-11-25 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Started: | 2019-11-25
Tagum City | Magugpo Poblacion | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | Rehabilitation of Evacuation Center at Magugpo Pob., Tagum City |  | SUPPLEMENTAL BUDGET NO. 4 CY 2019 (STIMULUS) | Building |  |  |  | Project Cost: | 600000 | Target Completion Date: |  | Program: | 600000 | Planned: |  | No. of Persons: |  | Purchase Order # 2020020796 (JJR Construction)
Tagum City | Magugpo Poblacion | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 600000 | Revised: |  | No. of Man-days:
Tagum City | Magugpo Poblacion | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Tagum City | Magugpo Poblacion | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Tagum City | Magugpo Poblacion | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Allotment Released: |  | Date completed:
Tagum City | Magugpo Poblacion | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Started:
Tagum City | Magugpo SOuth | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | Construction of Brgy. Health Center at Magugpo South, Tagum City |  | SUPPLEMENTAL BUDGET NO. 4 CY 2019 (STIMULUS) | Building |  |  |  | Project Cost: | 1550000 | Target Completion Date: |  | Program: | 1550000 | Planned: |  | No. of Persons: |  | Purchase Order # 20022150 (On-process)
Tagum City | Magugpo SOuth | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 1550000 | Revised: |  | No. of Man-days:
Tagum City | Magugpo SOuth | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Tagum City | Magugpo SOuth | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Tagum City | Magugpo SOuth | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Allotment Released: |  | Date completed:
Tagum City | Magugpo SOuth | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Started:
New Corella | Limbaan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | Rehab. Of Multi-Purpose Building (Evacuation Center), Limbaan, New Corella |  | SUPPLEMENTAL BUDGET NO. 4 CY 2019 (STIMULUS) | Building |  |  |  | Project Cost: | 600000 | Target Completion Date: |  | Program: | 600000 | Planned: |  | No. of Persons: |  | From SB # 1 to SB # 4 CY 2019 (Transfer to Contract) Procurement on process
New Corella | Limbaan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 600000 | Revised: |  | No. of Man-days:
New Corella | Limbaan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
New Corella | Limbaan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | Limbaan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Allotment Released: |  | Date completed:
New Corella | Limbaan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Started:
San Isidro | Sagayen-Sawata | 1st Eng'g. Dist. | On-going | 2019-09-09 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | Improvement of Km. 9 Sagayen-Sawata Provincial Road, San Isidro, Ph. II |  | SUPPLEMENTAL BUDGET NO. 4 CY 2019 (STIMULUS) | Road |  | ln.m | Admin | Project Cost: | 4591029 | Target Completion Date: | 2020-03-27 | Program: | 4591029 | Planned: | 45% | No. of Persons: | 6 | On-going (Suspended last April 5, 2020 due to COVID; resumption order dated May 4, 2020)
San Isidro | Sagayen-Sawata | 1st Eng'g. Dist. | On-going | 2019-09-09 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Project Engineer: | Limpo | Revised Completion Date: |  | Allotment: | 4591029 | Revised: |  | No. of Man-days: | 138
San Isidro | Sagayen-Sawata | 1st Eng'g. Dist. | On-going | 2019-09-09 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: | 1609155.6645 | Actual: | 35.05%
San Isidro | Sagayen-Sawata | 1st Eng'g. Dist. | On-going | 2019-09-09 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Duration: | 200 | No. of days extended: |  |  |  | Slippage: | -9.95%
San Isidro | Sagayen-Sawata | 1st Eng'g. Dist. | On-going | 2019-09-09 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Allotment Released: | 2019-12-12 | Date completed:
San Isidro | Sagayen-Sawata | 1st Eng'g. Dist. | On-going | 2019-09-09 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Started: | 2019-09-09
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Department of Agriculture | Poultry House and Training Center Sto. Niño, Talaingod |  | PROJECTS FOR PROVINCIAL VETERINARY | Building |  |  | Contract | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Final Abstract # 012020012 (Alpebel Builders & Supply Corp.)
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Department of Agriculture | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 500000 | Revised: |  | No. of Man-days:
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Department of Agriculture | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Department of Agriculture | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Department of Agriculture | [7 empty] | Date Allotment Released: |  | Date completed:
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Department of Agriculture | [7 empty] | Date Started:
Talaingod | Salawao-Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Department of Agriculture | Establishment of Livestock and Poultry Mutiplier Farm, Sitio Salawao, Sto. Niño, Talaingod |  | Department of Agriculture - Regional Field Office XI | Building |  |  |  | Project Cost: | 600000 | Target Completion Date: |  | Program: | 600000 | Planned: |  | No. of Persons: |  | Final Abstract # 012020012 (Alpebel Builders & Supply Corp.)
Talaingod | Salawao-Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Department of Agriculture | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 600000 | Revised: |  | No. of Man-days:
Talaingod | Salawao-Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Department of Agriculture | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Talaingod | Salawao-Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Department of Agriculture | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Talaingod | Salawao-Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Department of Agriculture | [7 empty] | Date Allotment Released: |  | Date completed:
Talaingod | Salawao-Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Department of Agriculture | [7 empty] | Date Started:
kapalong | Mabantao-Florida | 1st Eng'g. Dist. | On-going | 2019-10-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CMGP | Road Upgrading of Kapalong - Mabantao - Florida Road with Bridge Component |  | CMGP CY 2019 | Concreting |  | ln.m | Contract | Project Cost: | 15435008 | Target Completion Date: | 2020-03-10 23:59 | Program: | 15435008 | Planned: | 100% | No. of Persons: | 19 | On-going (Suspended last April 5, 2020 due to COVID; resumption order dated May 4, 2020)
kapalong | Mabantao-Florida | 1st Eng'g. Dist. | On-going | 2019-10-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CMGP | [7 empty] | Project Engineer: | Japay/Quirante | Revised Completion Date: | 2020-04-29 23:59 | Allotment: | 15435008 | Revised: | 81.81% | No. of Man-days: | 551
kapalong | Mabantao-Florida | 1st Eng'g. Dist. | On-going | 2019-10-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CMGP | [7 empty] | Implementor: | LEGACY | No. of days suspended: | 30 | Disbursement: | 6174003.2 | Actual: | 78.93%
kapalong | Mabantao-Florida | 1st Eng'g. Dist. | On-going | 2019-10-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CMGP | [7 empty] | Duration: | 147 | No. of days extended: | 20 |  |  | Slippage: | -2.882%
kapalong | Mabantao-Florida | 1st Eng'g. Dist. | On-going | 2019-10-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CMGP | [7 empty] | Date Allotment Released: | CY 2019 | Date completed:
kapalong | Mabantao-Florida | 1st Eng'g. Dist. | On-going | 2019-10-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CMGP | [7 empty] | Date Started: | 2019-10-16
New Corella | Del Pilar | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | LGSF | Rehabilitation of Dasing to Monte Carlo FMR, Del Pilar, New Corella |  | LGSF CY 2019 | Concreting |  |  | Contract | Project Cost: | 40000000 | Target Completion Date: |  | Program: | 40000000 | Planned: |  | No. of Persons: |  | For implementation (Awarded to Rely Construction and Supply)
New Corella | Del Pilar | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | LGSF | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 40000000 | Revised: |  | No. of Man-days:
New Corella | Del Pilar | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | LGSF | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
New Corella | Del Pilar | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | LGSF | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | Del Pilar | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | LGSF | [7 empty] | Date Allotment Released: |  | Date completed:
New Corella | Del Pilar | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | LGSF | [7 empty] | Date Started:
Tagum City | Magugpo South | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | LGSF | Concreting of Visayan Village - Purok exodus - Purok Rafael, Brgy. Magugpo South, Tagum City |  | LGSF CY 2019 | Concreting |  |  | Contract | Project Cost: | 40000000 | Target Completion Date: |  | Program: | 40000000 | Planned: |  | No. of Persons: |  | For implementation (Awarded to Legacy Construction Corporation)
Tagum City | Magugpo South | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | LGSF | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 40000000 | Revised: |  | No. of Man-days:
Tagum City | Magugpo South | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | LGSF | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Tagum City | Magugpo South | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | LGSF | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Tagum City | Magugpo South | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | LGSF | [7 empty] | Date Allotment Released: |  | Date completed:
Tagum City | Magugpo South | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | LGSF | [7 empty] | Date Started:
Asuncion | Magatos-Bantayan | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 001 - Jct. Highway Magatos - New Bantayan |  | GENERAL FUND CY 2020 | Maintenance | 7.1 | km | MBA | Project Cost: | 564839.9739 | Target Completion Date: | 2020-12-31 23:59 | Program: | 564839.9739 | Planned: | 27.45% | No. of Persons: | 17 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020)
Asuncion | Magatos-Bantayan | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 564839.9739 | Revised: |  | No. of Man-days: | 374
Asuncion | Magatos-Bantayan | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 57334.17 | Actual: | 27.45%
Asuncion | Magatos-Bantayan | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0%
Asuncion | Magatos-Bantayan | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
Asuncion | Magatos-Bantayan | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started: | 2020-01-02
Asuncion | Magatos-Bantayan | 1st Eng'g. Dist. | On-going |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 001 - Jct. Highway Magatos - New Bantayan |  | GENERAL FUND CY 2020 | Maintenance | 7.1 | km | CBRMC | Project Cost: | 230737.1976 | Target Completion Date: |  | Program: | 230737.1976 | Planned: |  | No. of Persons: |  | Purchase Request # 19125305 (On process)
Asuncion | Magatos-Bantayan | 1st Eng'g. Dist. | On-going |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 230737.1976 | Revised: |  | No. of Man-days:
Asuncion | Magatos-Bantayan | 1st Eng'g. Dist. | On-going |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Asuncion | Magatos-Bantayan | 1st Eng'g. Dist. | On-going |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Asuncion | Magatos-Bantayan | 1st Eng'g. Dist. | On-going |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: |  | Date completed:
Asuncion | Magatos-Bantayan | 1st Eng'g. Dist. | On-going |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started:
Asuncion | Magatos-Pagsabangan | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 002 - Magatos - Bdry. Pagsabangan |  | GENERAL FUND CY 2020 | Maintenance | 8.33 | km | MBA | Project Cost: | 653221.626 | Target Completion Date: | 2020-12-31 23:59 | Program: | 653221.626 | Planned: | 25.07% | No. of Persons: | 17 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020)
Asuncion | Magatos-Pagsabangan | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 653221.626 | Revised: |  | No. of Man-days: | 374
Asuncion | Magatos-Pagsabangan | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 71713.44 | Actual: | 25.07%
Asuncion | Magatos-Pagsabangan | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0%
Asuncion | Magatos-Pagsabangan | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
Asuncion | Magatos-Pagsabangan | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started: | 2020-01-02
Asuncion | Magatos-Pagsabangan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 002 - Magatos - Bdry. Pagsabangan |  | GENERAL FUND CY 2020 | Maintenance | 8.33 | km | CBRMC | Project Cost: | 280180.88 | Target Completion Date: |  | Program: | 280180.88 | Planned: |  | No. of Persons: |  | Purchase Request # 19125306 (On process)
Asuncion | Magatos-Pagsabangan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 280180.88 | Revised: |  | No. of Man-days:
Asuncion | Magatos-Pagsabangan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Asuncion | Magatos-Pagsabangan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Asuncion | Magatos-Pagsabangan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: |  | Date completed:
Asuncion | Magatos-Pagsabangan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started:
Asuncion | New Bantayan | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 003 - Ilog - New Bantayan |  | GENERAL FUND CY 2020 | Maintenance | 2.68 | km | MBA | Project Cost: | 236174.847 | Target Completion Date: | 2020-12-31 23:59 | Program: | 236174.847 | Planned: | 15.36% | No. of Persons: | 17 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020)
Asuncion | New Bantayan | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 236174.847 | Revised: |  | No. of Man-days: | 374
Asuncion | New Bantayan | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 22629.74 | Actual: | 15.36%
Asuncion | New Bantayan | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0%
Asuncion | New Bantayan | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
Asuncion | New Bantayan | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started: | 2020-01-02
Asuncion | New Bantayan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 003 - Ilog - New Bantayan |  | GENERAL FUND CY 2020 | Maintenance | 2.68 | km | CBRMC | Project Cost: | 70633.836 | Target Completion Date: |  | Program: | 70633.836 | Planned: |  | No. of Persons: |  | Purchase Request # 19125307 (On process)
Asuncion | New Bantayan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 70633.836 | Revised: |  | No. of Man-days:
Asuncion | New Bantayan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Asuncion | New Bantayan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Asuncion | New Bantayan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: |  | Date completed:
Asuncion | New Bantayan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started:
Asuncion | Monte Carlo-Del Pilar | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 005 - Asuncion - Monte Carlo - Del Pilar |  | GENERAL FUND CY 2020 | Maintenance | 9.93 | km | MBA | Project Cost: | 716344.9167 | Target Completion Date: | 2020-12-31 23:59 | Program: | 716344.9167 | Planned: | 29.09% | No. of Persons: | 17 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020)
Asuncion | Monte Carlo-Del Pilar | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 716344.9167 | Revised: |  | No. of Man-days: | 374
Asuncion | Monte Carlo-Del Pilar | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 33056.21 | Actual: | 29.09%
Asuncion | Monte Carlo-Del Pilar | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0%
Asuncion | Monte Carlo-Del Pilar | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
Asuncion | Monte Carlo-Del Pilar | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started: | 2020-01-02
Asuncion | Monte Carlo-Del Pilar | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 005 - Asuncion - Monte Carlo - Del Pilar |  | GENERAL FUND CY 2020 | Maintenance | 9.93 | km | CBRMC | Project Cost: | 360232.5636 | Target Completion Date: |  | Program: | 360232.5636 | Planned: |  | No. of Persons: |  | Purchase Request # 19125308 (On process)
Asuncion | Monte Carlo-Del Pilar | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 360232.5636 | Revised: |  | No. of Man-days:
Asuncion | Monte Carlo-Del Pilar | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Asuncion | Monte Carlo-Del Pilar | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Asuncion | Monte Carlo-Del Pilar | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: |  | Date completed:
Asuncion | Monte Carlo-Del Pilar | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started:
Asuncion | Canatan-Magatos | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 006 - Jct. Highway Canatan - Magatos |  | GENERAL FUND CY 2020 | Maintenance | 4.85 | km | MBA | Project Cost: | 391296.517 | Target Completion Date: | 2020-12-31 23:59 | Program: | 391296.517 | Planned: | 24.95% | No. of Persons: | 17 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020)
Asuncion | Canatan-Magatos | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 391296.517 | Revised: |  | No. of Man-days: | 374
Asuncion | Canatan-Magatos | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 33056.21 | Actual: | 24.95%
Asuncion | Canatan-Magatos | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0%
Asuncion | Canatan-Magatos | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
Asuncion | Canatan-Magatos | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started: | 2020-01-02
Asuncion | Canatan-Magatos | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 006 - Jct. Highway Canatan - Magatos |  | GENERAL FUND CY 2020 | Maintenance | 4.85 | km | CBRMC | Project Cost: | 164812.284 | Target Completion Date: |  | Program: | 164812.284 | Planned: |  | No. of Persons: |  | Purchase Request # 19125309 (On process)
Asuncion | Canatan-Magatos | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 164812.284 | Revised: |  | No. of Man-days:
Asuncion | Canatan-Magatos | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Asuncion | Canatan-Magatos | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Asuncion | Canatan-Magatos | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: |  | Date completed:
Asuncion | Canatan-Magatos | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started:
Asuncion | Saug-Sonlon-Longanapan | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 010 - Saug - Sonlon - Bdry. Longanapan |  | GENERAL FUND CY 2020 | Maintenance | 11.6 | km | MBA | Project Cost: | 1102041.4797 | Target Completion Date: | 2020-12-31 23:59 | Program: | 1102041.4797 | Planned: | 21.92% | No. of Persons: | 17 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020)
Asuncion | Saug-Sonlon-Longanapan | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 1102041.4797 | Revised: |  | No. of Man-days: | 374
Asuncion | Saug-Sonlon-Longanapan | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 83166.18 | Actual: | 21.92%
Asuncion | Saug-Sonlon-Longanapan | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0%
Asuncion | Saug-Sonlon-Longanapan | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
Asuncion | Saug-Sonlon-Longanapan | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started: | 2020-01-02
Asuncion | Saug-Sonlon-Longanapan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 010 - Saug - Sonlon - Bdry. Longanapan |  | GENERAL FUND CY 2020 | Maintenance | 11.6 | km | CBRMC | Project Cost: | 197774.7408 | Target Completion Date: |  | Program: | 197774.7408 | Planned: |  | No. of Persons: |  | Purchase Request # 19125310 (On process)
Asuncion | Saug-Sonlon-Longanapan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 197774.7408 | Revised: |  | No. of Man-days:
Asuncion | Saug-Sonlon-Longanapan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Asuncion | Saug-Sonlon-Longanapan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Asuncion | Saug-Sonlon-Longanapan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: |  | Date completed:
Asuncion | Saug-Sonlon-Longanapan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started:
Asuncion | New Visayas-Buan | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 011 - Jct. New Visayas - Buan |  | GENERAL FUND CY 2020 | Maintenance | 2.99 | km | MBA | Project Cost: | 134598.4525 | Target Completion Date: | 2020-12-31 23:59 | Program: | 134598.4525 | Planned: | 7.72% | No. of Persons: | 17 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020)
Asuncion | New Visayas-Buan | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 134598.4525 | Revised: |  | No. of Man-days: | 374
Asuncion | New Visayas-Buan | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 10391.0005 | Actual: | 7.72%
Asuncion | New Visayas-Buan | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0%
Asuncion | New Visayas-Buan | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
Asuncion | New Visayas-Buan | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started: | 2020-01-02
Asuncion | New Visayas-Buan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 011 - Jct. New Visayas - Buan |  | GENERAL FUND CY 2020 | Maintenance | 2.99 | km | CBRMC | Project Cost: | 124786.4436 | Target Completion Date: |  | Program: | 124786.4436 | Planned: |  | No. of Persons: |  | Purchase Request # 19125311 (On process)
Asuncion | New Visayas-Buan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 124786.4436 | Revised: |  | No. of Man-days:
Asuncion | New Visayas-Buan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Asuncion | New Visayas-Buan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Asuncion | New Visayas-Buan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: |  | Date completed:
Asuncion | New Visayas-Buan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started:
Asuncion | San Vicente-Butay | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 013 - San Vicente - Butay |  | GENERAL FUND CY 2020 | Maintenance | 7.52 | km | MBA | Project Cost: | 579541.5407 | Target Completion Date: | 2020-12-31 23:59 | Program: | 579541.5407 | Planned: | 30.2% | No. of Persons: | 17 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020)
Asuncion | San Vicente-Butay | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 579541.5407 | Revised: |  | No. of Man-days: | 374
Asuncion | San Vicente-Butay | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 123616.2106 | Actual: | 30.2%
Asuncion | San Vicente-Butay | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0%
Asuncion | San Vicente-Butay | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
Asuncion | San Vicente-Butay | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started: | 2020-01-02
Asuncion | San Vicente-Butay | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 013 - San Vicente - Butay |  | GENERAL FUND CY 2020 | Maintenance | 7.52 | km | CBRMC | Project Cost: | 235446.12 | Target Completion Date: |  | Program: | 235446.12 | Planned: |  | No. of Persons: |  | Purchase Request # 19125312 (On process)
Asuncion | San Vicente-Butay | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 235446.12 | Revised: |  | No. of Man-days:
Asuncion | San Vicente-Butay | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Asuncion | San Vicente-Butay | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Asuncion | San Vicente-Butay | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: |  | Date completed:
Asuncion | San Vicente-Butay | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started:
kapalong | Doña Andrea-Capungagan | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 014 - Jct. Highway Doña Andrea - Capungagan |  | GENERAL FUND CY 2020 | Maintenance | 8.7 | km | MBA | Project Cost: | 675845.5865 | Target Completion Date: | 2020-12-31 23:59 | Program: | 675845.5865 | Planned: | 14.87% | No. of Persons: | 17 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020)
kapalong | Doña Andrea-Capungagan | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 675845.5865 | Revised: |  | No. of Man-days: | 374
kapalong | Doña Andrea-Capungagan | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 75289.1983 | Actual: | 14.87%
kapalong | Doña Andrea-Capungagan | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0%
kapalong | Doña Andrea-Capungagan | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
kapalong | Doña Andrea-Capungagan | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started: | 2020-01-02
kapalong | Doña Andrea-Capungagan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 014 - Jct. Highway Doña Andrea - Capungagan |  | GENERAL FUND CY 2020 | Maintenance | 8.7 | km | CBRMC | Project Cost: | 299016.5724 | Target Completion Date: |  | Program: | 299016.5724 | Planned: |  | No. of Persons: |  | Purchase Request # 19125313 (On process)
kapalong | Doña Andrea-Capungagan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 299016.5724 | Revised: |  | No. of Man-days:
kapalong | Doña Andrea-Capungagan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
kapalong | Doña Andrea-Capungagan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
kapalong | Doña Andrea-Capungagan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: |  | Date completed:
kapalong | Doña Andrea-Capungagan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started:
kapalong | Pamacaun-Lasang-banate | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 015 - Pamacaun - Lasang - Banate |  | GENERAL FUND CY 2020 | Maintenance | 4.11 | km | MBA | Project Cost: | 180747.1933 | Target Completion Date: | 2020-12-31 23:59 | Program: | 180747.1933 | Planned: | 8.6% | No. of Persons: | 17 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020)
kapalong | Pamacaun-Lasang-banate | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 180747.1933 | Revised: |  | No. of Man-days: | 374
kapalong | Pamacaun-Lasang-banate | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 15544.2586 | Actual: | 8.6%
kapalong | Pamacaun-Lasang-banate | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0%
kapalong | Pamacaun-Lasang-banate | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
kapalong | Pamacaun-Lasang-banate | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started: | 2020-01-02
kapalong | Pamacaun-Lasang-banate | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 015 - Pamacaun - Lasang - Banate |  | GENERAL FUND CY 2020 | Maintenance | 4.11 | km | CBRMC | Project Cost: | 129495.366 | Target Completion Date: |  | Program: | 129495.366 | Planned: |  | No. of Persons: |  | Purchase Request # 19125314 (On process)
kapalong | Pamacaun-Lasang-banate | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 129495.366 | Revised: |  | No. of Man-days:
kapalong | Pamacaun-Lasang-banate | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
kapalong | Pamacaun-Lasang-banate | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
kapalong | Pamacaun-Lasang-banate | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: |  | Date completed:
kapalong | Pamacaun-Lasang-banate | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started:
kapalong | Semong-Palma Gil | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 018 - Semong - Palma Gil |  | GENERAL FUND CY 2020 | Maintenance | 2.73 | km | MBA | Project Cost: | 276301.31 | Target Completion Date: | 2020-12-31 23:59 | Program: | 276301.31 | Planned: | 50.35% | No. of Persons: | 14 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020)
kapalong | Semong-Palma Gil | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 276301.31 | Revised: |  | No. of Man-days: | 210
kapalong | Semong-Palma Gil | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 139117.7096 | Actual: | 50.35%
kapalong | Semong-Palma Gil | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0%
kapalong | Semong-Palma Gil | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
kapalong | Semong-Palma Gil | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started: | 2020-01-02
kapalong | Semong-Palma Gil | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 018 - Semong - Palma Gil |  | GENERAL FUND CY 2020 | Maintenance | 2.73 | km | CBRMC | Project Cost: | 77697.2196 | Target Completion Date: |  | Program: | 77697.2196 | Planned: |  | No. of Persons: |  | Purchase Request # 19125315 (On process)
kapalong | Semong-Palma Gil | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 77697.2196 | Revised: |  | No. of Man-days:
kapalong | Semong-Palma Gil | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
kapalong | Semong-Palma Gil | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
kapalong | Semong-Palma Gil | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: |  | Date completed:
kapalong | Semong-Palma Gil | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started:
Talaingod | Daligdigon-Dagohoy | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 020 - Daligdigon-Dagohoy |  | GENERAL FUND CY 2020 | Maintenance | 3.34 | km | MBA | Project Cost: | 161826.4 | Target Completion Date: | 2020-12-31 23:59 | Program: | 161826.4 | Planned: | 51.55% | No. of Persons: | 14 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020)
Talaingod | Daligdigon-Dagohoy | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 161826.4 | Revised: |  | No. of Man-days: | 210
Talaingod | Daligdigon-Dagohoy | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 83421.5092 | Actual: | 51.55%
Talaingod | Daligdigon-Dagohoy | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0%
Talaingod | Daligdigon-Dagohoy | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
Talaingod | Daligdigon-Dagohoy | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started: | 2020-01-02
Talaingod | Daligdigon-Dagohoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 020 - Daligdigon-Dagohoy |  | GENERAL FUND CY 2020 | Maintenance | 3.34 | km | CBRMC | Project Cost: | 77697.2196 | Target Completion Date: |  | Program: | 77697.2196 | Planned: |  | No. of Persons: |  | Purchase Request # 19125315 (On process)
Talaingod | Daligdigon-Dagohoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 77697.2196 | Revised: |  | No. of Man-days:
Talaingod | Daligdigon-Dagohoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Talaingod | Daligdigon-Dagohoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Talaingod | Daligdigon-Dagohoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: |  | Date completed:
Talaingod | Daligdigon-Dagohoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started:
Talaingod | Angelo-Dahgohoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 021 - Angelo - Dagohoy |  | GENERAL FUND CY 2020 | Maintenance | 2.19 | km | MBA | Project Cost: | 67286.09 | Target Completion Date: | 2020-12-31 23:59 | Program: | 67286.09 | Planned: | 21.85% | No. of Persons: | 14 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020)
Talaingod | Angelo-Dahgohoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 67286.09 | Revised: |  | No. of Man-days: | 210
Talaingod | Angelo-Dahgohoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 14702.0107 | Actual: | 21.85%
Talaingod | Angelo-Dahgohoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0%
Talaingod | Angelo-Dahgohoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
Talaingod | Angelo-Dahgohoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started: | 2020-01-02
Talaingod | Angelo-Dahgohoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 021 - Angelo - Dagohoy |  | GENERAL FUND CY 2020 | Maintenance | 2.19 | km | CBRMC | Project Cost: | 40025.8404 | Target Completion Date: |  | Program: | 40025.8404 | Planned: |  | No. of Persons: |  | Purchase Request # 19125317 (On process)
Talaingod | Angelo-Dahgohoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 40025.8404 | Revised: |  | No. of Man-days:
Talaingod | Angelo-Dahgohoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Talaingod | Angelo-Dahgohoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Talaingod | Angelo-Dahgohoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: |  | Date completed:
Talaingod | Angelo-Dahgohoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started:
kapalong | Sampao-Mamacao | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 025 - Jct. Sampao - Bdry. Mamacao |  | GENERAL FUND CY 2020 | Maintenance | 4.98 | km | MBA | Project Cost: | 325083.1184 | Target Completion Date: | 2020-12-31 23:59 | Program: | 325083.1184 | Planned: | 14.71% | No. of Persons: | 17 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020)
kapalong | Sampao-Mamacao | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 325083.1184 | Revised: |  | No. of Man-days: | 374
kapalong | Sampao-Mamacao | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 47819.7267 | Actual: | 14.71%
kapalong | Sampao-Mamacao | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0%
kapalong | Sampao-Mamacao | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
kapalong | Sampao-Mamacao | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started: | 2020-01-02
kapalong | Sampao-Mamacao | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 025 - Jct. Sampao - Bdry. Mamacao |  | GENERAL FUND CY 2020 | Maintenance | 4.98 | km | CBRMC | Project Cost: | 178939.0512 | Target Completion Date: |  | Program: | 178939.0512 | Planned: |  | No. of Persons: |  | Purchase Request # 19125318 (On process)
kapalong | Sampao-Mamacao | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 178939.0512 | Revised: |  | No. of Man-days:
kapalong | Sampao-Mamacao | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
kapalong | Sampao-Mamacao | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
kapalong | Sampao-Mamacao | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: |  | Date completed:
kapalong | Sampao-Mamacao | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started:
kapalong | Luna-Mamacao | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 026 - Jct. Highway - Luna - Mamacao - Narra |  | GENERAL FUND CY 2020 | Maintenance | 9.17 | km | MBA | Project Cost: | 361826.1515 | Target Completion Date: | 2020-12-31 23:59 | Program: | 361826.1515 | Planned: | 20.12% | No. of Persons: | 17 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020)
kapalong | Luna-Mamacao | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 361826.1515 | Revised: |  | No. of Man-days: | 374
kapalong | Luna-Mamacao | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 22433.2214 | Actual: | 20.12%
kapalong | Luna-Mamacao | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0%
kapalong | Luna-Mamacao | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
kapalong | Luna-Mamacao | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started: | 2020-01-02
kapalong | Luna-Mamacao | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 026 - Jct. Highway - Luna - Mamacao - Narra |  | GENERAL FUND CY 2020 | Maintenance | 9.17 | km | CBRMC | Project Cost: | 393195.0204 | Target Completion Date: |  | Program: | 393195.0204 | Planned: |  | No. of Persons: |  | Purchase Request # 19125337 (On process)
kapalong | Luna-Mamacao | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 393195.0204 | Revised: |  | No. of Man-days:
kapalong | Luna-Mamacao | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
kapalong | Luna-Mamacao | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
kapalong | Luna-Mamacao | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: |  | Date completed:
kapalong | Luna-Mamacao | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started:
kapalong | Gabuyan-Katipunan | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 027 - Jct. Gabuyan - Katipunan - Bucana |  | GENERAL FUND CY 2020 | Maintenance | 5.89 | km | MBA | Project Cost: | 485762.7577 | Target Completion Date: | 2020-12-31 23:59 | Program: | 485762.7577 | Planned: | 7.86% | No. of Persons: | 17 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020)
kapalong | Gabuyan-Katipunan | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 485762.7577 | Revised: |  | No. of Man-days: | 374
kapalong | Gabuyan-Katipunan | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 38180.9528 | Actual: | 7.86%
kapalong | Gabuyan-Katipunan | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0%
kapalong | Gabuyan-Katipunan | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
kapalong | Gabuyan-Katipunan | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started: | 2020-01-02
kapalong | Gabuyan-Katipunan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 027 - Jct. Gabuyan - Katipunan - Bucana |  | GENERAL FUND CY 2020 | Maintenance | 5.89 | km | CBRMC | Project Cost: | 174230.1288 | Target Completion Date: |  | Program: | 174230.1288 | Planned: |  | No. of Persons: |  | Purchase Request # 19125338 (On process)
kapalong | Gabuyan-Katipunan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 174230.1288 | Revised: |  | No. of Man-days:
kapalong | Gabuyan-Katipunan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
kapalong | Gabuyan-Katipunan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
kapalong | Gabuyan-Katipunan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: |  | Date completed:
kapalong | Gabuyan-Katipunan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started:
kapalong | Capungagan-Mabuhay | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 028 - Capungagan - Mabuhay - Pandulian |  | GENERAL FUND CY 2020 | Maintenance | 5.57 | km | MBA | Project Cost: | 468741.4542 | Target Completion Date: | 2020-12-31 23:59 | Program: | 468741.4542 | Planned: | 5.14% | No. of Persons: | 17 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020)
kapalong | Capungagan-Mabuhay | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 468741.4542 | Revised: |  | No. of Man-days: | 374
kapalong | Capungagan-Mabuhay | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 24093.3107 | Actual: | 5.14%
kapalong | Capungagan-Mabuhay | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0%
kapalong | Capungagan-Mabuhay | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
kapalong | Capungagan-Mabuhay | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started: | 2020-01-02
kapalong | Capungagan-Mabuhay | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 028 - Capungagan - Mabuhay - Pandulian |  | GENERAL FUND CY 2020 | Maintenance | 5.57 | km | CBRMC | Project Cost: | 155394.4392 | Target Completion Date: |  | Program: | 155394.4392 | Planned: |  | No. of Persons: |  | Purchase Request # 19125339 (On process)
kapalong | Capungagan-Mabuhay | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 155394.4392 | Revised: |  | No. of Man-days:
kapalong | Capungagan-Mabuhay | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
kapalong | Capungagan-Mabuhay | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
kapalong | Capungagan-Mabuhay | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: |  | Date completed:
kapalong | Capungagan-Mabuhay | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started:
San Isidro | Kipalili-New Loon | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 034 - Km. 15, Kipalili - New Loon |  | GENERAL FUND CY 2020 | Maintenance | 6.93 | km | MBA | Project Cost: | 490709.8742 | Target Completion Date: | 2020-12-31 23:59 | Program: | 490709.8742 | Planned: | 18.2% | No. of Persons: | 17 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020)
San Isidro | Kipalili-New Loon | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 490709.8742 | Revised: |  | No. of Man-days: | 374
San Isidro | Kipalili-New Loon | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 66393.046 | Actual: | 18.2%
San Isidro | Kipalili-New Loon | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0%
San Isidro | Kipalili-New Loon | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
San Isidro | Kipalili-New Loon | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started: | 2020-01-02
San Isidro | Kipalili-New Loon | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 034 - Km. 15, Kipalili - New Loon |  | GENERAL FUND CY 2020 | Maintenance | 6.93 | km | CBRMC | Project Cost: | 296662.1112 | Target Completion Date: |  | Program: | 296662.1112 | Planned: |  | No. of Persons: |  | Purchase Request # 19125340 (On process)
San Isidro | Kipalili-New Loon | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 296662.1112 | Revised: |  | No. of Man-days:
San Isidro | Kipalili-New Loon | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
San Isidro | Kipalili-New Loon | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
San Isidro | Kipalili-New Loon | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: |  | Date completed:
San Isidro | Kipalili-New Loon | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started:
San Isidro | Suaon-Libuton | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 035 - Jct. Suaon - Libuton |  | GENERAL FUND CY 2020 | Maintenance | 7.26 | km | MBA | Project Cost: | 60919.7962 | Target Completion Date: | 2020-12-31 23:59 | Program: | 60919.7962 | Planned: | 7.12% | No. of Persons: | 17 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020)
San Isidro | Suaon-Libuton | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 60919.7962 | Revised: |  | No. of Man-days: | 374
San Isidro | Suaon-Libuton | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: |  | Actual: | 7.12%
San Isidro | Suaon-Libuton | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0%
San Isidro | Suaon-Libuton | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
San Isidro | Suaon-Libuton | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started: | 2020-01-02
San Isidro | Suaon-Libuton | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 035 - Jct. Suaon - Libuton |  | GENERAL FUND CY 2020 | Maintenance | 7.26 | km | CBRMC | Project Cost: | 96532.9092 | Target Completion Date: |  | Program: | 96532.9092 | Planned: |  | No. of Persons: |  | Purchase Request # 19125341 (On process)
San Isidro | Suaon-Libuton | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 96532.9092 | Revised: |  | No. of Man-days:
San Isidro | Suaon-Libuton | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
San Isidro | Suaon-Libuton | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
San Isidro | Suaon-Libuton | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: |  | Date completed:
San Isidro | Suaon-Libuton | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started:
San Isidro | Monte Dujali-Gupitan | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 037 - Monte Dujali - Gupitan |  | GENERAL FUND CY 2020 | Maintenance | 4.58 | km | MBA | Project Cost: | 224727.1648 | Target Completion Date: | 2020-12-31 23:59 | Program: | 224727.1648 | Planned: | 11.08% | No. of Persons: | 17 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020)
San Isidro | Monte Dujali-Gupitan | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 224727.1648 | Revised: |  | No. of Man-days: | 374
San Isidro | Monte Dujali-Gupitan | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 24899.7699 | Actual: | 11.08%
San Isidro | Monte Dujali-Gupitan | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0%
San Isidro | Monte Dujali-Gupitan | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
San Isidro | Monte Dujali-Gupitan | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started: | 2020-01-02
San Isidro | Monte Dujali-Gupitan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 037 - Monte Dujali - Gupitan |  | GENERAL FUND CY 2020 | Maintenance | 4.58 | km | CBRMC | Project Cost: | 134204.2884 | Target Completion Date: |  | Program: | 134204.2884 | Planned: |  | No. of Persons: |  | Purchase Request # 19125342 (On process)
San Isidro | Monte Dujali-Gupitan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 134204.2884 | Revised: |  | No. of Man-days:
San Isidro | Monte Dujali-Gupitan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
San Isidro | Monte Dujali-Gupitan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
San Isidro | Monte Dujali-Gupitan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: |  | Date completed:
San Isidro | Monte Dujali-Gupitan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started:
San Isidro | Sawata-Mamangan-Pinamuno | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 041 - Sawata - Mamangan - Pinamuno |  | GENERAL FUND CY 2020 | Maintenance | 14.48 | km | MBA | Project Cost: | 1636481.63 | Target Completion Date: | 2021-02-01 23:59 | Program: | 1636481.63 | Planned: | 37.11% | No. of Persons: | 14 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020)
San Isidro | Sawata-Mamangan-Pinamuno | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-02-28 23:59 | Allotment: | 1636481.63 | Revised: |  | No. of Man-days: | 210
San Isidro | Sawata-Mamangan-Pinamuno | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 607298.3329 | Actual: | 37.11%
San Isidro | Sawata-Mamangan-Pinamuno | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0%
San Isidro | Sawata-Mamangan-Pinamuno | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
San Isidro | Sawata-Mamangan-Pinamuno | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started: | 2020-02-03
San Isidro | Sawata-Mamangan-Pinamuno | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 041 - Sawata - Mamangan - Pinamuno |  | GENERAL FUND CY 2020 | Maintenance | 14.48 | km | CBRMC | Project Cost: | 522690.3864 | Target Completion Date: |  | Program: | 522690.3864 | Planned: |  | No. of Persons: |  | Purchase Request # 19125343 (On process)
San Isidro | Sawata-Mamangan-Pinamuno | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 522690.3864 | Revised: |  | No. of Man-days:
San Isidro | Sawata-Mamangan-Pinamuno | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
San Isidro | Sawata-Mamangan-Pinamuno | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
San Isidro | Sawata-Mamangan-Pinamuno | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: |  | Date completed:
San Isidro | Sawata-Mamangan-Pinamuno | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started:
San Isidro | Igangon-Sawata | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 042 - Igangon - Sawata |  | GENERAL FUND CY 2020 | Maintenance | 9.66 | km | MBA | Project Cost: | 111771.1255 | Target Completion Date: | 2020-12-31 23:59 | Program: | 111771.1255 | Planned: | 8.74% | No. of Persons: | 17 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020)
San Isidro | Igangon-Sawata | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 111771.1255 | Revised: |  | No. of Man-days: | 374
San Isidro | Igangon-Sawata | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 9768.7964 | Actual: | 8.74%
San Isidro | Igangon-Sawata | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0%
San Isidro | Igangon-Sawata | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
San Isidro | Igangon-Sawata | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started: | 2020-01-02
San Isidro | Igangon-Sawata | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 042 - Igangon - Sawata |  | GENERAL FUND CY 2020 | Maintenance | 9.66 | km | CBRMC | Project Cost: | 202483.6632 | Target Completion Date: |  | Program: | 202483.6632 | Planned: |  | No. of Persons: |  | Purchase Request # 19125344 (On process)
San Isidro | Igangon-Sawata | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 202483.6632 | Revised: |  | No. of Man-days:
San Isidro | Igangon-Sawata | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
San Isidro | Igangon-Sawata | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
San Isidro | Igangon-Sawata | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: |  | Date completed:
San Isidro | Igangon-Sawata | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started:
San Isidro | Sawata | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 043 - Jct. Sawata - Bdry. Binasbas |  | GENERAL FUND CY 2020 | Maintenance | 0.46 | km | MBA | Project Cost: | 27720.5682 | Target Completion Date: | 2020-12-31 23:59 | Program: | 27720.5682 | Planned: | 10.3% | No. of Persons: | 17 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020)
San Isidro | Sawata | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 27720.5682 | Revised: |  | No. of Man-days: | 374
San Isidro | Sawata | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 2855.2185 | Actual: | 10.3%
San Isidro | Sawata | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0%
San Isidro | Sawata | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
San Isidro | Sawata | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started: | 2020-01-02
San Isidro | Sawata | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 043 - Jct. Sawata - Bdry. Binasbas |  | GENERAL FUND CY 2020 | Maintenance | 0.46 | km | CBRMC | Project Cost: | 18835.6896 | Target Completion Date: |  | Program: | 18835.6896 | Planned: |  | No. of Persons: |  | Purchase Request # 19125345 (On process)
San Isidro | Sawata | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 18835.6896 | Revised: |  | No. of Man-days:
San Isidro | Sawata | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
San Isidro | Sawata | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
San Isidro | Sawata | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: |  | Date completed:
San Isidro | Sawata | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started:
Asuncion | Buan | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 045 - Tagaytay - Buan |  | GENERAL FUND CY 2020 | Maintenance | 4.92 | km | MBA | Project Cost: | 378553.2244 | Target Completion Date: | 2020-12-31 23:59 | Program: | 378553.2244 | Planned: | 27.97% | No. of Persons: | 17 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020)
Asuncion | Buan | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 378553.2244 | Revised: |  | No. of Man-days: | 374
Asuncion | Buan | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 105881.3369 | Actual: | 27.97%
Asuncion | Buan | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0%
Asuncion | Buan | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
Asuncion | Buan | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started: | 2020-01-02
Asuncion | Buan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 045 - Tagaytay - Buan |  | GENERAL FUND CY 2020 | Maintenance | 4.92 | km | CBRMC | Project Cost: | 174230.1288 | Target Completion Date: |  | Program: | 174230.1288 | Planned: |  | No. of Persons: |  | Purchase Request # 19125346 (On process)
Asuncion | Buan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 174230.1288 | Revised: |  | No. of Man-days:
Asuncion | Buan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Asuncion | Buan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Asuncion | Buan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: |  | Date completed:
Asuncion | Buan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started:
New Corella | Limbann-Sto. Niño | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 049 - Limbaan - Sto. Niño |  | GENERAL FUND CY 2020 | Maintenance | 3.19 | km | MBA | Project Cost: | 322857.58 | Target Completion Date: | 2021-02-01 23:59 | Program: | 322857.58 | Planned: | 30.02% | No. of Persons: | 14 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020)
New Corella | Limbann-Sto. Niño | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-02-28 23:59 | Allotment: | 322857.58 | Revised: |  | No. of Man-days: | 210
New Corella | Limbann-Sto. Niño | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 96921.8455 | Actual: | 30.02%
New Corella | Limbann-Sto. Niño | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | Limbann-Sto. Niño | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
New Corella | Limbann-Sto. Niño | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started: | 2020-02-03
New Corella | Limbann-Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 049 - Limbaan - Sto. Niño |  | GENERAL FUND CY 2020 | Maintenance | 3.19 | km | CBRMC | Project Cost: | 127140.9048 | Target Completion Date: |  | Program: | 127140.9048 | Planned: |  | No. of Persons: |  | Purchase Request # 20010072 (On process)
New Corella | Limbann-Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 127140.9048 | Revised: |  | No. of Man-days:
New Corella | Limbann-Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
New Corella | Limbann-Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | Limbann-Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: |  | Date completed:
New Corella | Limbann-Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started:
New Corella | Monte Carlo | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 050 - Jct. Monte Carlo - Upper Cabaywa - Canatan |  | GENERAL FUND CY 2020 | Maintenance | 4.61 | km | MBA | Project Cost: | 285065.7818 | Target Completion Date: | 2020-12-31 23:59 | Program: | 285065.7818 | Planned: | 47.46% | No. of Persons: | 17 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020)
New Corella | Monte Carlo | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 285065.7818 | Revised: |  | No. of Man-days: | 374
New Corella | Monte Carlo | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 135292.2201 | Actual: | 47.46%
New Corella | Monte Carlo | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | Monte Carlo | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
New Corella | Monte Carlo | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started: | 2020-01-02
New Corella | Monte Carlo | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 050 - Jct. Monte Carlo - Upper Cabaywa - Canatan |  | GENERAL FUND CY 2020 | Maintenance | 4.61 | km | CBRMC | Project Cost: | 197774.7408 | Target Completion Date: |  | Program: | 197774.7408 | Planned: |  | No. of Persons: |  | Purchase Request # 20010074 (On process)
New Corella | Monte Carlo | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 197774.7408 | Revised: |  | No. of Man-days:
New Corella | Monte Carlo | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
New Corella | Monte Carlo | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | Monte Carlo | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: |  | Date completed:
New Corella | Monte Carlo | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started:
New Corella | Del Pilar | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 051 - Del Pilar - Jct. Silangan |  | GENERAL FUND CY 2020 | Maintenance | 4.17 | km | MBA | Project Cost: | 337766.1689 | Target Completion Date: | 2020-12-31 23:59 | Program: | 337766.1689 | Planned: | 5.54% | No. of Persons: |  | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020)
New Corella | Del Pilar | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 337766.1689 | Revised: |  | No. of Man-days:
New Corella | Del Pilar | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 18712.2458 | Actual: | 5.54%
New Corella | Del Pilar | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | Del Pilar | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
New Corella | Del Pilar | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started: | 2020-01-02
New Corella | Del Pilar | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 051 - Del Pilar - Jct. Silangan |  | GENERAL FUND CY 2020 | Maintenance | 4.17 | km | CBRMC | Project Cost: | 129495.366 | Target Completion Date: |  | Program: | 129495.366 | Planned: |  | No. of Persons: |  | Purchase Request # 20010093 (On process)
New Corella | Del Pilar | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 129495.366 | Revised: |  | No. of Man-days:
New Corella | Del Pilar | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
New Corella | Del Pilar | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | Del Pilar | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: |  | Date completed:
New Corella | Del Pilar | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started:
New Corella | New Sambog | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 052 - New Corella - New Sambog - Silangan |  | GENERAL FUND CY 2020 | Maintenance | 5.1 | km | MBA | Project Cost: | 371450.8414 | Target Completion Date: | 2020-12-31 23:59 | Program: | 371450.8414 | Planned: | 8.7% | No. of Persons: | 17 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020)
New Corella | New Sambog | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 371450.8414 | Revised: |  | No. of Man-days: | 374
New Corella | New Sambog | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 32316.2232 | Actual: | 8.7%
New Corella | New Sambog | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | New Sambog | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
New Corella | New Sambog | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started: | 2020-01-02
New Corella | New Sambog | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 052 - New Corella - New Sambog - Silangan |  | GENERAL FUND CY 2020 | Maintenance | 5.1 | km | CBRMC | Project Cost: | 148331.0556 | Target Completion Date: |  | Program: | 148331.0556 | Planned: |  | No. of Persons: |  | Purchase Request # 20010095 (On process)
New Corella | New Sambog | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 148331.0556 | Revised: |  | No. of Man-days:
New Corella | New Sambog | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
New Corella | New Sambog | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | New Sambog | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: |  | Date completed:
New Corella | New Sambog | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started:
New Corella | Poblacion | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 053 - Pob. New Corella - Prk. 10 Pob. |  | GENERAL FUND CY 2020 | Maintenance | 1.3 | km | MBA | Project Cost: | 28149.3653 | Target Completion Date: | 2020-12-31 23:59 | Program: | 28149.3653 | Planned: | 13.38% | No. of Persons: | 17 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020)
New Corella | Poblacion | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 28149.3653 | Revised: |  | No. of Man-days: | 374
New Corella | Poblacion | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 3766.3851 | Actual: | 13.38%
New Corella | Poblacion | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | Poblacion | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
New Corella | Poblacion | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started: | 2020-01-02
New Corella | Poblacion | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 053 - Pob. New Corella - Prk. 10 Pob. |  | GENERAL FUND CY 2020 | Maintenance | 1.3 | km | CBRMC | Project Cost: | 21190.1508 | Target Completion Date: |  | Program: | 21190.1508 | Planned: |  | No. of Persons: |  | Purchase Request # 20010155 (On process)
New Corella | Poblacion | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 21190.1508 | Revised: |  | No. of Man-days:
New Corella | Poblacion | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
New Corella | Poblacion | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | Poblacion | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: |  | Date completed:
New Corella | Poblacion | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started:
New Corella | New Sambog | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 054 - Prk. 7 Pob. - Jct. New Sambog |  | GENERAL FUND CY 2020 | Maintenance | 2.54 | km | MBA | Project Cost: | 171600.7916 | Target Completion Date: | 2020-12-31 23:59 | Program: | 171600.7916 | Planned: | 6.92% | No. of Persons: | 17 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020)
New Corella | New Sambog | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 171600.7916 | Revised: |  | No. of Man-days: | 374
New Corella | New Sambog | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 11874.7748 | Actual: | 6.92%
New Corella | New Sambog | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | New Sambog | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
New Corella | New Sambog | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started: | 2020-01-02
New Corella | New Sambog | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 054 - Prk. 7 Pob. - Jct. New Sambog |  | GENERAL FUND CY 2020 | Maintenance | 2.54 | km | CBRMC | Project Cost: | 113014.1376 | Target Completion Date: |  | Program: | 113014.1376 | Planned: |  | No. of Persons: |  | Purchase Request # 20010158 (On process)
New Corella | New Sambog | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 113014.1376 | Revised: |  | No. of Man-days:
New Corella | New Sambog | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
New Corella | New Sambog | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | New Sambog | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: |  | Date completed:
New Corella | New Sambog | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started:
New Corella | Sta. Fe-Del Monte | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 056 - Sta. Fe - Del Monte |  | GENERAL FUND CY 2020 | Maintenance | 3.34 | km | MBA | Project Cost: | 93676.7241 | Target Completion Date: | 2020-12-31 23:59 | Program: | 93676.7241 | Planned: | 11.64% | No. of Persons: | 17 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020)
New Corella | Sta. Fe-Del Monte | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 93676.7241 | Revised: |  | No. of Man-days: | 374
New Corella | Sta. Fe-Del Monte | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 10903.9707 | Actual: | 11.64%
New Corella | Sta. Fe-Del Monte | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | Sta. Fe-Del Monte | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
New Corella | Sta. Fe-Del Monte | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started: | 2020-01-02
New Corella | Sta. Fe-Del Monte | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 056 - Sta. Fe - Del Monte |  | GENERAL FUND CY 2020 | Maintenance | 3.34 | km | CBRMC | Project Cost: | 75342.7584 | Target Completion Date: |  | Program: | 75342.7584 | Planned: |  | No. of Persons: |  | Purchase Request # 20010160 (On process)
New Corella | Sta. Fe-Del Monte | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 75342.7584 | Revised: |  | No. of Man-days:
New Corella | Sta. Fe-Del Monte | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
New Corella | Sta. Fe-Del Monte | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | Sta. Fe-Del Monte | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: |  | Date completed:
New Corella | Sta. Fe-Del Monte | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started:
New Corella | New Bohol | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 058 - New Corella - New Bohol |  | GENERAL FUND CY 2020 | Maintenance | 11.54 | km | MBA | Project Cost: | 300034.9027 | Target Completion Date: | 2020-12-31 23:59 | Program: | 300034.9027 | Planned: | 17.21% | No. of Persons: | 17 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020)
New Corella | New Bohol | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 300034.9027 | Revised: |  | No. of Man-days: | 374
New Corella | New Bohol | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 51636.0068 | Actual: | 17.21%
New Corella | New Bohol | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | New Bohol | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
New Corella | New Bohol | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started: | 2020-01-02
New Corella | New Bohol | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 058 - New Corella - New Bohol |  | GENERAL FUND CY 2020 | Maintenance | 11.54 | km | CBRMC | Project Cost: | 221319.3528 | Target Completion Date: |  | Program: | 221319.3528 | Planned: |  | No. of Persons: |  | Purchase Request # 20010221 (On process)
New Corella | New Bohol | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 221319.3528 | Revised: |  | No. of Man-days:
New Corella | New Bohol | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
New Corella | New Bohol | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | New Bohol | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: |  | Date completed:
New Corella | New Bohol | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started:
New Corella | Carcor | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 059 - Jct. Carcor - Prk. 9 Bagsak |  | GENERAL FUND CY 2020 | Maintenance | 2.5 | km | MBA | Project Cost: | 161961.791 | Target Completion Date: | 2020-12-31 23:59 | Program: | 161961.791 | Planned: | 15.82% | No. of Persons: | 17 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020)
New Corella | Carcor | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 161961.791 | Revised: |  | No. of Man-days: | 374
New Corella | Carcor | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 25622.3553 | Actual: | 15.82%
New Corella | Carcor | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | Carcor | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
New Corella | Carcor | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started: | 2020-01-02
New Corella | Carcor | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 059 - Jct. Carcor - Prk. 9 Bagsak |  | GENERAL FUND CY 2020 | Maintenance | 2.5 | km | CBRMC | Project Cost: | 72988.2972 | Target Completion Date: |  | Program: | 72988.2972 | Planned: |  | No. of Persons: |  | Purchase Request # 20010223 (On process)
New Corella | Carcor | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 72988.2972 | Revised: |  | No. of Man-days:
New Corella | Carcor | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
New Corella | Carcor | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | Carcor | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: |  | Date completed:
New Corella | Carcor | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started:
New Corella | Carcor | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 060 - Carcor - Jct. Kauswagan |  | GENERAL FUND CY 2020 | Maintenance | 4.32 | km | MBA | Project Cost: | 304751.9237 | Target Completion Date: | 2020-12-31 23:59 | Program: | 304751.9237 | Planned: | 31.32% | No. of Persons: | 17 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020)
New Corella | Carcor | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 304751.9237 | Revised: |  | No. of Man-days: | 374
New Corella | Carcor | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 95448.3025 | Actual: | 31.32%
New Corella | Carcor | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | Carcor | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
New Corella | Carcor | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started: | 2020-01-02
New Corella | Carcor | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 060 - Carcor - Jct. Kauswagan |  | GENERAL FUND CY 2020 | Maintenance | 4.32 | km | CBRMC | Project Cost: | 101241.8316 | Target Completion Date: |  | Program: | 101241.8316 | Planned: |  | No. of Persons: |  | Purchase Request # 20010262 (On process)
New Corella | Carcor | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 101241.8316 | Revised: |  | No. of Man-days:
New Corella | Carcor | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
New Corella | Carcor | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | Carcor | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: |  | Date completed:
New Corella | Carcor | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started:
New Corella | Del Pilar | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 061 - Del Pilar - Prk. 9 Bagsak - San Jose |  | GENERAL FUND CY 2020 | Maintenance |  | km | MBA | Project Cost: | 505304.26 | Target Completion Date: | 2021-01-14 23:59 | Program: | 505304.26 | Planned: | 49.18% | No. of Persons: | 14 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020)
New Corella | Del Pilar | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-02-10 23:59 | Allotment: | 505304.26 | Revised: |  | No. of Man-days: | 210
New Corella | Del Pilar | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 248508.6351 | Actual: | 49.18%
New Corella | Del Pilar | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | Del Pilar | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
New Corella | Del Pilar | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started: | 2020-01-16
New Corella | Del Pilar | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 061 - Del Pilar - Prk. 9 Bagsak - San Jose |  | GENERAL FUND CY 2020 | Maintenance |  | km | CBRMC | Project Cost: | 251927.3484 | Target Completion Date: |  | Program: | 251927.3484 | Planned: |  | No. of Persons: |  | Purchase Request # 20010264 (On process)
New Corella | Del Pilar | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 251927.3484 | Revised: |  | No. of Man-days:
New Corella | Del Pilar | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
New Corella | Del Pilar | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | Del Pilar | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: |  | Date completed:
New Corella | Del Pilar | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started:
New Corella | Del Pilar | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 062 - Del Pilar - El Unido |  | GENERAL FUND CY 2020 | Maintenance | 1.32 | km | MBA | Project Cost: | 84027.808 | Target Completion Date: | 2020-12-31 23:59 | Program: | 84027.808 | Planned: | 10.78% | No. of Persons: | 17 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020)
New Corella | Del Pilar | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 84027.808 | Revised: |  | No. of Man-days: | 374
New Corella | Del Pilar | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 9058.1977 | Actual: | 10.78%
New Corella | Del Pilar | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | Del Pilar | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
New Corella | Del Pilar | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started: | 2020-01-02
New Corella | Del Pilar | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 062 - Del Pilar - El Unido |  | GENERAL FUND CY 2020 | Maintenance | 1.32 | km | CBRMC | Project Cost: | 40025.8404 | Target Completion Date: |  | Program: | 40025.8404 | Planned: |  | No. of Persons: |  | Purchase Request # 20010265 (On process)
New Corella | Del Pilar | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 40025.8404 | Revised: |  | No. of Man-days:
New Corella | Del Pilar | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
New Corella | Del Pilar | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | Del Pilar | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: |  | Date completed:
New Corella | Del Pilar | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started:
New Corella | Del Pilar | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 063 - San Juan - New Talisay |  | GENERAL FUND CY 2020 | Maintenance | 5.13 | km | MBA | Project Cost: | 442982.6933 | Target Completion Date: | 2020-12-31 23:59 | Program: | 442982.6933 | Planned: | 13.42% | No. of Persons: | 17 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020)
New Corella | Del Pilar | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 442982.6933 | Revised: |  | No. of Man-days: | 374
New Corella | Del Pilar | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 59448.2774 | Actual: | 13.42%
New Corella | Del Pilar | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | Del Pilar | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
New Corella | Del Pilar | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started: | 2020-01-02
New Corella | Del Pilar | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 063 - San Juan - New Talisay |  | GENERAL FUND CY 2020 | Maintenance | 5.13 | km | CBRMC | Project Cost: | 131849.8272 | Target Completion Date: |  | Program: | 131849.8272 | Planned: |  | No. of Persons: |  | Purchase Request # 20010267 (On process)
New Corella | Del Pilar | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 131849.8272 | Revised: |  | No. of Man-days:
New Corella | Del Pilar | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
New Corella | Del Pilar | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | Del Pilar | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: |  | Date completed:
New Corella | Del Pilar | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started:
New Corella | Del Pilar | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 064 - San Juan - Kauswagan - New Cortez |  | GENERAL FUND CY 2020 | Maintenance | 3.22 | km | MBA | Project Cost: | 128969.53 | Target Completion Date: | 2021-01-14 23:59 | Program: | 128969.53 | Planned: | 41.14% | No. of Persons: | 14 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020)
New Corella | Del Pilar | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-02-10 23:59 | Allotment: | 128969.53 | Revised: |  | No. of Man-days: | 210
New Corella | Del Pilar | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 53058.0646 | Actual: | 41.14%
New Corella | Del Pilar | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage:
New Corella | Del Pilar | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
New Corella | Del Pilar | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started: | 2020-01-16
New Corella | Del Pilar | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 064 - San Juan - Kauswagan - New Cortez |  | GENERAL FUND CY 2020 | Maintenance | 3.22 | km | CBRMC | Project Cost: | 68279.3748 | Target Completion Date: |  | Program: | 68279.3748 | Planned: |  | No. of Persons: |  | Procurement on process
New Corella | Del Pilar | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 68279.3748 | Revised: |  | No. of Man-days:
New Corella | Del Pilar | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
New Corella | Del Pilar | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | Del Pilar | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: |  | Date completed:
New Corella | Del Pilar | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started:
New Corella | New Bohol | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 065 - New Bohol - Jct. El Unido |  | GENERAL FUND CY 2020 | Maintenance | 2.12 | km | MBA | Project Cost: | 177260.81 | Target Completion Date: | 2021-01-14 23:59 | Program: | 177260.81 | Planned: |  | No. of Persons: | 14 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020)
New Corella | New Bohol | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-02-10 23:59 | Allotment: | 177260.81 | Revised: |  | No. of Man-days: | 210
New Corella | New Bohol | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 50005.2745 | Actual: | 28.21%
New Corella | New Bohol | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | #VALUE!
New Corella | New Bohol | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
New Corella | New Bohol | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started: | 2020-01-16
New Corella | New Bohol | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 065 - New Bohol - Jct. El Unido |  | GENERAL FUND CY 2020 | Maintenance | 2.12 | km | CBRMC | Project Cost: | 65924.9136 | Target Completion Date: |  | Program: | 65924.9136 | Planned: |  | No. of Persons: |  | Purchase Request # 20010275 (On process)
New Corella | New Bohol | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 65924.9136 | Revised: |  | No. of Man-days:
New Corella | New Bohol | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
New Corella | New Bohol | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | New Bohol | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: |  | Date completed:
New Corella | New Bohol | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started:
New Corella | Mesaoy | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 066 - New Corella - El Unido - Jct. Mesaoy |  | GENERAL FUND CY 2020 | Maintenance | 8.63 | km | MBA | Project Cost: | 792432.45 | Target Completion Date: | 2021-01-14 23:59 | Program: | 792432.45 | Planned: | 53.98% | No. of Persons: | 14 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020)
New Corella | Mesaoy | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-02-10 23:59 | Allotment: | 792432.45 | Revised: |  | No. of Man-days: | 210
New Corella | Mesaoy | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 427755.0365 | Actual: | 53.98%
New Corella | Mesaoy | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | Mesaoy | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
New Corella | Mesaoy | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started: | 2020-01-16
New Corella | Mesaoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 066 - New Corella - El Unido - Jct. Mesaoy |  | GENERAL FUND CY 2020 | Maintenance | 8.63 | km | CBRMC | Project Cost: | 249572.8872 | Target Completion Date: |  | Program: | 249572.8872 | Planned: |  | No. of Persons: |  | Purchase Request # 20010291 (On process)
New Corella | Mesaoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 249572.8872 | Revised: |  | No. of Man-days:
New Corella | Mesaoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
New Corella | Mesaoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | Mesaoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: |  | Date completed:
New Corella | Mesaoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started:
New Corella | Mesaoy | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 067 - Mesaoy - Dasing |  | GENERAL FUND CY 2020 | Maintenance | 1.39 | km | MBA | Project Cost: | 130632.25 | Target Completion Date: | 2021-01-14 23:59 | Program: | 130632.25 | Planned: | 48.79% | No. of Persons: | 14 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020)
New Corella | Mesaoy | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-02-10 23:59 | Allotment: | 130632.25 | Revised: |  | No. of Man-days: | 210
New Corella | Mesaoy | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 63735.4748 | Actual: | 48.79%
New Corella | Mesaoy | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | Mesaoy | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
New Corella | Mesaoy | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started: | 2020-01-16
New Corella | Mesaoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 067 - Mesaoy - Dasing |  | GENERAL FUND CY 2020 | Maintenance | 1.39 | km | CBRMC | Project Cost: | 54152.6076 | Target Completion Date: |  | Program: | 54152.6076 | Planned: |  | No. of Persons: |  | Purchase Request # 20010294 (On process)
New Corella | Mesaoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 54152.6076 | Revised: |  | No. of Man-days:
New Corella | Mesaoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
New Corella | Mesaoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | Mesaoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: |  | Date completed:
New Corella | Mesaoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started:
New Corella | Del Pilar | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 068 - Jct. San Juan - Jct. Mesaoy |  | GENERAL FUND CY 2020 | Maintenance | 1.82 | km | MBA | Project Cost: | 135657.3072 | Target Completion Date: | 2020-12-31 23:59 | Program: | 135657.3072 | Planned: | 7.32% | No. of Persons: | 17 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020)
New Corella | Del Pilar | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 135657.3072 | Revised: |  | No. of Man-days: | 374
New Corella | Del Pilar | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 9930.1149 | Actual: | 7.32%
New Corella | Del Pilar | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | Del Pilar | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
New Corella | Del Pilar | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started: | 2020-01-02
New Corella | Del Pilar | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 068 - Jct. San Juan - Jct. Mesaoy |  | GENERAL FUND CY 2020 | Maintenance | 1.82 | km | CBRMC | Project Cost: | 68279.3748 | Target Completion Date: |  | Program: | 68279.3748 | Planned: |  | No. of Persons: |  | Purchase Request # 20010294 (On process)
New Corella | Del Pilar | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 68279.3748 | Revised: |  | No. of Man-days:
New Corella | Del Pilar | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
New Corella | Del Pilar | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | Del Pilar | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: |  | Date completed:
New Corella | Del Pilar | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started:
New Corella | Mesaoy-New Bohol | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 070 - Mesaoy - New Bohol |  | GENERAL FUND CY 2020 | Maintenance | 5.36 | km | MBA | Project Cost: | 665667.84 | Target Completion Date: | 2021-01-14 23:59 | Program: | 665667.84 | Planned: | 41.99% | No. of Persons: | 14 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020)
New Corella | Mesaoy-New Bohol | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-02-10 23:59 | Allotment: | 665667.84 | Revised: |  | No. of Man-days: | 210
New Corella | Mesaoy-New Bohol | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 279513.926 | Actual: | 41.99%
New Corella | Mesaoy-New Bohol | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | Mesaoy-New Bohol | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
New Corella | Mesaoy-New Bohol | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started: | 2020-01-16
New Corella | Mesaoy-New Bohol | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 070 - Mesaoy - New Bohol |  | GENERAL FUND CY 2020 | Maintenance | 5.36 | km | CBRMC | Project Cost: | 261345.1932 | Target Completion Date: |  | Program: | 261345.1932 | Planned: |  | No. of Persons: |  | Purchase Request # 20010298 (On process)
New Corella | Mesaoy-New Bohol | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 261345.1932 | Revised: |  | No. of Man-days:
New Corella | Mesaoy-New Bohol | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
New Corella | Mesaoy-New Bohol | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | Mesaoy-New Bohol | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: |  | Date completed:
New Corella | Mesaoy-New Bohol | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started:
Asuncion | Napungas | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 147 - Prk. 1, Maunlom-Prk. 6 Maunlom Road |  | GENERAL FUND CY 2020 | Maintenance | 3.56 | km | MBA | Project Cost: | 115812.32 | Target Completion Date: | 2021-02-15 23:59 | Program: | 115812.32 | Planned: | 38.9% | No. of Persons: | 14 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020)
Asuncion | Napungas | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-03-14 23:59 | Allotment: | 115812.32 | Revised: |  | No. of Man-days: | 210
Asuncion | Napungas | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 45050.9925 | Actual: | 38.9%
Asuncion | Napungas | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0%
Asuncion | Napungas | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
Asuncion | Napungas | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started: | 2020-02-17
Asuncion | Napungas | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 147 - Prk. 1, Maunlom-Prk. 6 Maunlom Road |  | GENERAL FUND CY 2020 | Maintenance | 3.56 | km | CBRMC | Project Cost: | 65924.9136 | Target Completion Date: |  | Program: | 65924.9136 | Planned: |  | No. of Persons: |  | Purchase Request # 20010302 (On process)
Asuncion | Napungas | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 65924.9136 | Revised: |  | No. of Man-days:
Asuncion | Napungas | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Asuncion | Napungas | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Asuncion | Napungas | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: |  | Date completed:
Asuncion | Napungas | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started:
Asuncion | Binancian | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 149 - New Visayas - Binancian |  | GENERAL FUND CY 2020 | Maintenance | 7.77 | km | MBA | Project Cost: | 62394.7204 | Target Completion Date: | 2020-12-31 23:59 | Program: | 62394.7204 | Planned: | 3.47% | No. of Persons: | 17 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020)
Asuncion | Binancian | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 62394.7204 | Revised: |  | No. of Man-days: | 374
Asuncion | Binancian | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 2165.0968 | Actual: | 3.47%
Asuncion | Binancian | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0%
Asuncion | Binancian | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
Asuncion | Binancian | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started: | 2020-01-02
Asuncion | Binancian | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 149 - New Visayas - Binancian |  | GENERAL FUND CY 2020 | Maintenance | 7.77 | km | CBRMC | Project Cost: | 134204.2884 | Target Completion Date: |  | Program: | 134204.2884 | Planned: |  | No. of Persons: |  | Purchase Request # 20010305 (On process)
Asuncion | Binancian | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 134204.2884 | Revised: |  | No. of Man-days:
Asuncion | Binancian | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Asuncion | Binancian | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Asuncion | Binancian | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: |  | Date completed:
Asuncion | Binancian | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started:
San Isidro | Datu Balong-Mamalian | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 150 - Datu Balong - Prk. Mamalian |  | GENERAL FUND CY 2020 | Maintenance | 3.46 | km | MBA | Project Cost: | 45089.8864 | Target Completion Date: | 2020-12-31 23:59 | Program: | 45089.8864 | Planned: | 6.37% | No. of Persons: | 17 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020)
San Isidro | Datu Balong-Mamalian | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 45089.8864 | Revised: |  | No. of Man-days: | 374
San Isidro | Datu Balong-Mamalian | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 2872.2258 | Actual: | 6.37%
San Isidro | Datu Balong-Mamalian | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0%
San Isidro | Datu Balong-Mamalian | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | 2 | 2020-01-02 | Date completed:
San Isidro | Datu Balong-Mamalian | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started: | 2020-01-02
San Isidro | Datu Balong-Mamalian | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 150 - Datu Balong - Prk. Mamalian |  | GENERAL FUND CY 2020 | Maintenance | 3.46 | km | CBRMC | Project Cost: | 61215.9912 | Target Completion Date: |  | Program: | 61215.9912 | Planned: |  | No. of Persons: |  | Purchase Request # 20010306 (On process)
San Isidro | Datu Balong-Mamalian | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 61215.9912 | Revised: |  | No. of Man-days:
San Isidro | Datu Balong-Mamalian | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
San Isidro | Datu Balong-Mamalian | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
San Isidro | Datu Balong-Mamalian | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: |  | Date completed:
San Isidro | Datu Balong-Mamalian | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started:
Tagum City | Cuambogan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | RURAL ELECTRIFICATION PROJECT LS - P 5,000,000.00 | Rural Electrification at RAMADA Compound Purok Sto. Niño, Brgy. Cuambogan, Tagum City |  | 20% Development Fund CY 2020 | Electrification |  | km |  | Project Cost: | 1000000 | Target Completion Date: |  | Program: | 1000000 | Planned: |  | No. of Persons: |  | PO on process - Tagum Constrak
Tagum City | Cuambogan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | RURAL ELECTRIFICATION PROJECT LS - P 5,000,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 1000000 | Revised: |  | No. of Man-days:
Tagum City | Cuambogan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | RURAL ELECTRIFICATION PROJECT LS - P 5,000,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Tagum City | Cuambogan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | RURAL ELECTRIFICATION PROJECT LS - P 5,000,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Tagum City | Cuambogan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | RURAL ELECTRIFICATION PROJECT LS - P 5,000,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Tagum City | Cuambogan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | RURAL ELECTRIFICATION PROJECT LS - P 5,000,000.00 | [7 empty] | Date Started:
Asuncion | Camansa | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | RURAL ELECTRIFICATION PROJECT LS - P 5,000,000.00 | Rural Electrification at Lower Camansa, Prk.5 to 6 Lower, Brgy. Camansa, Asuncion |  | 20% Development Fund CY 2020 | Electrification |  | km |  | Project Cost: | 3000000 | Target Completion Date: |  | Program: | 3000000 | Planned: |  | No. of Persons: |  | PO on process - Tagum Constrak
Asuncion | Camansa | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | RURAL ELECTRIFICATION PROJECT LS - P 5,000,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 3000000 | Revised: |  | No. of Man-days:
Asuncion | Camansa | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | RURAL ELECTRIFICATION PROJECT LS - P 5,000,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Asuncion | Camansa | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | RURAL ELECTRIFICATION PROJECT LS - P 5,000,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Asuncion | Camansa | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | RURAL ELECTRIFICATION PROJECT LS - P 5,000,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Asuncion | Camansa | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | RURAL ELECTRIFICATION PROJECT LS - P 5,000,000.00 | [7 empty] | Date Started:
Asuncion | Doña Andrea | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | RURAL ELECTRIFICATION PROJECT LS - P 5,000,000.00 | Completion of Electrification at at Purok 10 and Purok 9, Phase 2, Brgy. Doña Andrea, Asuncion |  | 20% Development Fund CY 2020 | Electrification |  | km |  | Project Cost: | 1000000 | Target Completion Date: |  | Program: | 1000000 | Planned: |  | No. of Persons: |  | For preparation of POW and Plans
Asuncion | Doña Andrea | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | RURAL ELECTRIFICATION PROJECT LS - P 5,000,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 1000000 | Revised: |  | No. of Man-days:
Asuncion | Doña Andrea | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | RURAL ELECTRIFICATION PROJECT LS - P 5,000,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Asuncion | Doña Andrea | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | RURAL ELECTRIFICATION PROJECT LS - P 5,000,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Asuncion | Doña Andrea | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | RURAL ELECTRIFICATION PROJECT LS - P 5,000,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Asuncion | Doña Andrea | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | RURAL ELECTRIFICATION PROJECT LS - P 5,000,000.00 | [7 empty] | Date Started:
Asuncion | Sta. Felomina | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | ROAD ID 008 - Sta. Felomina - San Roque |  | 20% Development Fund CY 2020 | Road Rehabilitaion | 7.68 | km | Admin | Project Cost: | 2304000 | Target Completion Date: |  | Program: | 2304000 | Planned: |  | No. of Persons: |  | Post qualification on process
Asuncion | Sta. Felomina | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 2304000 | Revised: |  | No. of Man-days:
Asuncion | Sta. Felomina | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual:
Asuncion | Sta. Felomina | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Asuncion | Sta. Felomina | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Asuncion | Sta. Felomina | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Date Started:
Talaingod | Sto. Niño-Palma Gil | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | ROAD ID 019 - Sto. Niño - Palma Gil - Sitio Opao |  | 20% Development Fund CY 2020 | Road Rehabilitaion | 5.99 | km | Admin | Project Cost: | 1797000 | Target Completion Date: |  | Program: | 1797000 | Planned: |  | No. of Persons: |  | POW on process
Talaingod | Sto. Niño-Palma Gil | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 1797000 | Revised: |  | No. of Man-days:
Talaingod | Sto. Niño-Palma Gil | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual:
Talaingod | Sto. Niño-Palma Gil | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Talaingod | Sto. Niño-Palma Gil | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Talaingod | Sto. Niño-Palma Gil | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Date Started:
Talaingod | Daligdigon-Paiton | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | ROAD ID 023 - Sto. Niño - Daligdigon - Paiton |  | 20% Development Fund CY 2020 | Road Rehabilitaion | 11.6 | km | Admin | Project Cost: | 3480000 | Target Completion Date: |  | Program: | 3480000 | Planned: |  | No. of Persons: |  | POW on process
Talaingod | Daligdigon-Paiton | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 3480000 | Revised: |  | No. of Man-days:
Talaingod | Daligdigon-Paiton | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual:
Talaingod | Daligdigon-Paiton | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Talaingod | Daligdigon-Paiton | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Talaingod | Daligdigon-Paiton | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Date Started:
Talaingod | Paiton | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | ROAD ID 024 - Jct. Paiton - Mibolo |  | 20% Development Fund CY 2020 | Road Rehabilitaion | 23.9 | km | Admin | Project Cost: | 7170000 | Target Completion Date: |  | Program: | 7170000 | Planned: |  | No. of Persons: |  | POW on process
Talaingod | Paiton | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 7170000 | Revised: |  | No. of Man-days:
Talaingod | Paiton | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual:
Talaingod | Paiton | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Talaingod | Paiton | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Talaingod | Paiton | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Date Started:
Kapalong | Florida | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | ROAD ID 024 - Florida - Suaon - Jct. Gupitan |  | 20% Development Fund CY 2020 | Road Rehabilitaion | 15.57 | km | Admin | Project Cost: | 4671000 | Target Completion Date: |  | Program: | 4671000 | Planned: |  | No. of Persons: |  | PO on process - Royal Summit
Kapalong | Florida | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 4671000 | Revised: |  | No. of Man-days:
Kapalong | Florida | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual:
Kapalong | Florida | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Kapalong | Florida | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Kapalong | Florida | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Date Started:
San Isidro | Datu Balong | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | ROAD ID 040 - Datu Balong - Pinamuno |  | 20% Development Fund CY 2020 | Road Rehabilitaion | 2.74 | km | Admin | Project Cost: | 822000 | Target Completion Date: |  | Program: | 822000 | Planned: |  | No. of Persons: |  | POW on process
San Isidro | Datu Balong | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 822000 | Revised: |  | No. of Man-days:
San Isidro | Datu Balong | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual:
San Isidro | Datu Balong | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
San Isidro | Datu Balong | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
San Isidro | Datu Balong | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Date Started:
New Corella | Macgum | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | ROAD ID 048 - New Corella - Saug |  | 20% Development Fund CY 2020 | Road Rehabilitaion | 12.52 | km | Admin | Project Cost: | 20571000 | Target Completion Date: |  | Program: | 20571000 | Planned: |  | No. of Persons: |  | POW on process
New Corella | Macgum | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 20571000 | Revised: |  | No. of Man-days:
New Corella | Macgum | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual:
New Corella | Macgum | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | Macgum | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
New Corella | Macgum | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Date Started:
Asuncion | Canatan-Doña andrea | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | ROAD ID 074 - Jct. Highway Canatan - Doña Andrea |  | 20% Development Fund CY 2020 | Road Rehabilitaion | 4.34 | km | Admin | Project Cost: | 1302000 | Target Completion Date: |  | Program: | 1302000 | Planned: |  | No. of Persons: |  | POW on process
Asuncion | Canatan-Doña andrea | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 1302000 | Revised: |  | No. of Man-days:
Asuncion | Canatan-Doña andrea | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Asuncion | Canatan-Doña andrea | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Asuncion | Canatan-Doña andrea | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Asuncion | Canatan-Doña andrea | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Date Started:
Kapalong | Florida | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | ROAD ID 030 - Florida - New Boholano |  | 20% Development Fund CY 2020 | Road Rehabilitaion | 2.54 | km | Admin | Project Cost: | 762000 | Target Completion Date: |  | Program: | 762000 | Planned: |  | No. of Persons: |  | POW on process
Kapalong | Florida | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 762000 | Revised: |  | No. of Man-days:
Kapalong | Florida | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual:
Kapalong | Florida | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Kapalong | Florida | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Kapalong | Florida | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Date Started:
Asuncion | New Loon | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | ROAD ID 031 - Jct. New Boholano - New Loon |  | 20% Development Fund CY 2020 | Road Rehabilitaion | 4.77 | km | Admin | Project Cost: | 1431000 | Target Completion Date: |  | Program: | 1431000 | Planned: |  | No. of Persons: |  | POW on process
Asuncion | New Loon | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 1431000 | Revised: |  | No. of Man-days:
Asuncion | New Loon | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Asuncion | New Loon | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Asuncion | New Loon | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Asuncion | New Loon | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Date Started:
New Corella | Mesaoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | ROAD ID 069 - Mesaoy - Jct. Mahayahay |  | 20% Development Fund CY 2020 | Road Rehabilitaion | 4.6 | km | Admin | Project Cost: | 1380000 | Target Completion Date: |  | Program: | 1380000 | Planned: |  | No. of Persons: |  | POW on process
New Corella | Mesaoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 1380000 | Revised: |  | No. of Man-days:
New Corella | Mesaoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual:
New Corella | Mesaoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | Mesaoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
New Corella | Mesaoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Date Started:
Asuncion | Cabaywa | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | ROAD ID 071 - Lower Asuncion - Upper Asuncion |  | 20% Development Fund CY 2020 | Road Rehabilitaion |  | km | Admin | Project Cost: | 1302000 | Target Completion Date: |  | Program: | 1302000 | Planned: |  | No. of Persons: |  | Plan On-going
Asuncion | Cabaywa | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 1302000 | Revised: |  | No. of Man-days:
Asuncion | Cabaywa | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Asuncion | Cabaywa | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Asuncion | Cabaywa | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Asuncion | Cabaywa | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Date Started:
Tagum City | AAT | 1st Eng'g. Dist. | On-going | 2020-05-18 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS LOCAL ROADS & DRAINAGE DEV'T. PROJECT - LS P15,590,910.00 | Rehab. Of Various Local Roads @ Tagum City |  | 20% Development Fund CY 2020 | Rehabilitaion |  | km | Admin | Project Cost: | 2518182 | Target Completion Date: | 2020-10-20 | Program: | 2518182 | Planned: | 18.41% | No. of Persons: | 10 | On-going
Tagum City | AAT | 1st Eng'g. Dist. | On-going | 2020-05-18 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS LOCAL ROADS & DRAINAGE DEV'T. PROJECT - LS P15,590,910.00 | [7 empty] | Project Engineer: | Bataller | Revised Completion Date: |  | Allotment: | 2518182 | Revised: |  | No. of Man-days: | 150
Tagum City | AAT | 1st Eng'g. Dist. | On-going | 2020-05-18 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS LOCAL ROADS & DRAINAGE DEV'T. PROJECT - LS P15,590,910.00 | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: | 18.41%
Tagum City | AAT | 1st Eng'g. Dist. | On-going | 2020-05-18 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS LOCAL ROADS & DRAINAGE DEV'T. PROJECT - LS P15,590,910.00 | [7 empty] | Duration: | 155 | No. of days extended: |  |  |  | Slippage: | 0%
Tagum City | AAT | 1st Eng'g. Dist. | On-going | 2020-05-18 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS LOCAL ROADS & DRAINAGE DEV'T. PROJECT - LS P15,590,910.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Tagum City | AAT | 1st Eng'g. Dist. | On-going | 2020-05-18 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS LOCAL ROADS & DRAINAGE DEV'T. PROJECT - LS P15,590,910.00 | [7 empty] | Date Started: | 2020-05-18
Asuncion | AAA | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS LOCAL ROADS & DRAINAGE DEV'T. PROJECT - LS P15,590,910.00 | Rehab. Of Various Local Roads @ Asuncion |  | 20% Development Fund CY 2020 | Rehabilitaion |  | km | Admin | Project Cost: | 2518182 | Target Completion Date: |  | Program: | 2518182 | Planned: |  | No. of Persons: |  | POW on process
Asuncion | AAA | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS LOCAL ROADS & DRAINAGE DEV'T. PROJECT - LS P15,590,910.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 2518182 | Revised: |  | No. of Man-days:
Asuncion | AAA | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS LOCAL ROADS & DRAINAGE DEV'T. PROJECT - LS P15,590,910.00 | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual:
Asuncion | AAA | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS LOCAL ROADS & DRAINAGE DEV'T. PROJECT - LS P15,590,910.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Asuncion | AAA | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS LOCAL ROADS & DRAINAGE DEV'T. PROJECT - LS P15,590,910.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Asuncion | AAA | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS LOCAL ROADS & DRAINAGE DEV'T. PROJECT - LS P15,590,910.00 | [7 empty] | Date Started:
Kapalong | AAK | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS LOCAL ROADS & DRAINAGE DEV'T. PROJECT - LS P15,590,910.00 | Rehab. Of Various Local Roads @ Kapalong |  | 20% Development Fund CY 2020 | Rehabilitaion |  | km | Admin | Project Cost: | 2518182 | Target Completion Date: |  | Program: | 2518182 | Planned: |  | No. of Persons: |  | For Implementation
Kapalong | AAK | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS LOCAL ROADS & DRAINAGE DEV'T. PROJECT - LS P15,590,910.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 2518182 | Revised: |  | No. of Man-days:
Kapalong | AAK | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS LOCAL ROADS & DRAINAGE DEV'T. PROJECT - LS P15,590,910.00 | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual:
Kapalong | AAK | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS LOCAL ROADS & DRAINAGE DEV'T. PROJECT - LS P15,590,910.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Kapalong | AAK | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS LOCAL ROADS & DRAINAGE DEV'T. PROJECT - LS P15,590,910.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Kapalong | AAK | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS LOCAL ROADS & DRAINAGE DEV'T. PROJECT - LS P15,590,910.00 | [7 empty] | Date Started:
New Corella | AAN | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS LOCAL ROADS & DRAINAGE DEV'T. PROJECT - LS P15,590,910.00 | Rehab. Of Various Local Roads @ New Corella |  | 20% Development Fund CY 2020 | Rehabilitaion |  | km | Admin | Project Cost: | 2518182 | Target Completion Date: |  | Program: | 2518182 | Planned: |  | No. of Persons: |  | POW on process
New Corella | AAN | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS LOCAL ROADS & DRAINAGE DEV'T. PROJECT - LS P15,590,910.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 2518182 | Revised: |  | No. of Man-days:
New Corella | AAN | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS LOCAL ROADS & DRAINAGE DEV'T. PROJECT - LS P15,590,910.00 | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual:
New Corella | AAN | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS LOCAL ROADS & DRAINAGE DEV'T. PROJECT - LS P15,590,910.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | AAN | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS LOCAL ROADS & DRAINAGE DEV'T. PROJECT - LS P15,590,910.00 | [7 empty] | Date Allotment Released: |  | Date completed:
New Corella | AAN | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS LOCAL ROADS & DRAINAGE DEV'T. PROJECT - LS P15,590,910.00 | [7 empty] | Date Started:
San Isidro | AAS | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS LOCAL ROADS & DRAINAGE DEV'T. PROJECT - LS P15,590,910.00 | Rehab. Of Various Local Roads @ San Isidro |  | 20% Development Fund CY 2020 | Rehabilitaion |  | km | Admin | Project Cost: | 2518182 | Target Completion Date: |  | Program: | 2518182 | Planned: |  | No. of Persons: |  | POW on process
San Isidro | AAS | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS LOCAL ROADS & DRAINAGE DEV'T. PROJECT - LS P15,590,910.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 2518182 | Revised: |  | No. of Man-days:
San Isidro | AAS | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS LOCAL ROADS & DRAINAGE DEV'T. PROJECT - LS P15,590,910.00 | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual:
San Isidro | AAS | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS LOCAL ROADS & DRAINAGE DEV'T. PROJECT - LS P15,590,910.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
San Isidro | AAS | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS LOCAL ROADS & DRAINAGE DEV'T. PROJECT - LS P15,590,910.00 | [7 empty] | Date Allotment Released: |  | Date completed:
San Isidro | AAS | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS LOCAL ROADS & DRAINAGE DEV'T. PROJECT - LS P15,590,910.00 | [7 empty] | Date Started:
Talaingod | AAT | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS LOCAL ROADS & DRAINAGE DEV'T. PROJECT - LS P15,590,910.00 | Rehab. Of Various Local Roads @ Talaingod |  | 20% Development Fund CY 2020 | Rehabilitaion |  | km | Admin | Project Cost: | 2518182 | Target Completion Date: |  | Program: | 2518182 | Planned: |  | No. of Persons: |  | For Implementation
Talaingod | AAT | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS LOCAL ROADS & DRAINAGE DEV'T. PROJECT - LS P15,590,910.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 2518182 | Revised: |  | No. of Man-days:
Talaingod | AAT | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS LOCAL ROADS & DRAINAGE DEV'T. PROJECT - LS P15,590,910.00 | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual:
Talaingod | AAT | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS LOCAL ROADS & DRAINAGE DEV'T. PROJECT - LS P15,590,910.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Talaingod | AAT | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS LOCAL ROADS & DRAINAGE DEV'T. PROJECT - LS P15,590,910.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Talaingod | AAT | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS LOCAL ROADS & DRAINAGE DEV'T. PROJECT - LS P15,590,910.00 | [7 empty] | Date Started:
Tagum City | Mankilam | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | Construction of DAVNOR Tech-Vocational Center, Government Center, Mankilam, Tagum City |  | 20% Development Fund CY 2020 | Building |  | sq.m | Admin | Project Cost: | 8000000 | Target Completion Date: |  | Program: | 8000000 | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
Tagum City | Mankilam | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 8000000 | Revised: |  | No. of Man-days:
Tagum City | Mankilam | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual:
Tagum City | Mankilam | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Tagum City | Mankilam | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Tagum City | Mankilam | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Date Started:
Tagum City | Mankilam | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | Improvement of PSWDO Bodega Government Cente, Mankilam, Tagum City |  | 20% Development Fund CY 2020 | Building |  | sq.m | Admin | Project Cost: | 1000000 | Target Completion Date: |  | Program: | 1000000 | Planned: |  | No. of Persons: |  | POW and Plans on-going
Tagum City | Mankilam | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 1000000 | Revised: |  | No. of Man-days:
Tagum City | Mankilam | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual:
Tagum City | Mankilam | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Tagum City | Mankilam | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Tagum City | Mankilam | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Date Started:
San Isidro | Mamangan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | Renovation/Improvement of MAFAMCO Consumer's Bldg., Brgy. Mamangan, San Isidro |  | 20% Development Fund CY 2020 | Building |  | sq.m | Contract | Project Cost: | 800000 | Target Completion Date: |  | Program: | 800000 | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
San Isidro | Mamangan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 800000 | Revised: |  | No. of Man-days:
San Isidro | Mamangan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
San Isidro | Mamangan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
San Isidro | Mamangan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
San Isidro | Mamangan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Date Started:
Asuncion | Camansa | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | Construction of IP Council of Women Training Center, Camansa Kamadi District, Asuncion |  | 20% Development Fund CY 2020 | Building |  | sq.m | Admin | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
Asuncion | Camansa | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Asuncion | Camansa | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual:
Asuncion | Camansa | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Asuncion | Camansa | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Asuncion | Camansa | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Date Started:
New Corella | Cabidianan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | Construction of One(1) unit School Building at Cabidianan E/S, New Corella |  | 20% Development Fund CY 2020 | Building |  | sq.m | Contract | Project Cost: | 1300000 | Target Completion Date: |  | Program: | 1300000 | Planned: |  | No. of Persons:
New Corella | Cabidianan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 1300000 | Revised: |  | No. of Man-days:
New Corella | Cabidianan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
New Corella | Cabidianan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | Cabidianan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
New Corella | Cabidianan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Date Started:
Kapalong | Florida | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | Construction of one(1) unit School Building at Kamansi Integrated School, Florida, kapalong |  | 20% Development Fund CY 2020 | Building |  | sq.m | Contract | Project Cost: | 1300000 | Target Completion Date: |  | Program: | 1300000 | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
Kapalong | Florida | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 1300000 | Revised: |  | No. of Man-days:
Kapalong | Florida | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Kapalong | Florida | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Kapalong | Florida | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Kapalong | Florida | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Date Started:
Asuncion | Magatos | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | Construction of one(1) unit School Building at Magatos E/S, Magatos, Asuncion |  | 20% Development Fund CY 2020 | Building |  | sq.m | Contract | Project Cost: | 1300000 | Target Completion Date: |  | Program: | 1300000 | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
Asuncion | Magatos | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 1300000 | Revised: |  | No. of Man-days:
Asuncion | Magatos | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Asuncion | Magatos | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Asuncion | Magatos | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Asuncion | Magatos | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Date Started:
Talaingod | Sta. Cruz | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | Construction of one(1) unit School Building at Sta. Cruz E/S, New Corella |  | 20% Development Fund CY 2020 | Building |  | sq.m |  | Project Cost: | 1300000 | Target Completion Date: |  | Program: | 1300000 | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
Talaingod | Sta. Cruz | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 1300000 | Revised: |  | No. of Man-days:
Talaingod | Sta. Cruz | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Talaingod | Sta. Cruz | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Talaingod | Sta. Cruz | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Talaingod | Sta. Cruz | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Date Started:
Talaingod | Dagohoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | Construction Women Development Center, Dagohoy, Talaingod |  | 20% Development Fund CY 2020 | Building |  | sq.m |  | Project Cost: | 1000000 | Target Completion Date: |  | Program: | 1000000 | Planned: |  | No. of Persons: |  | Post qualification on process
Talaingod | Dagohoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 1000000 | Revised: |  | No. of Man-days:
Talaingod | Dagohoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Talaingod | Dagohoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Talaingod | Dagohoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Talaingod | Dagohoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Date Started:
Asuncion | Cambanogoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | Construction of Municipal Triball Hall, Asuncion |  | 20% Development Fund CY 2020 | Building |  | sq.m | Contract | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
Asuncion | Cambanogoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Asuncion | Cambanogoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Asuncion | Cambanogoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Asuncion | Cambanogoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Asuncion | Cambanogoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Date Started:
Kapalong | Maniki | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | Construction of Municipal Triball Hall, Kapalong |  | 20% Development Fund CY 2020 | Building |  | sq.m | Contract | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
Kapalong | Maniki | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Kapalong | Maniki | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Kapalong | Maniki | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Kapalong | Maniki | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Kapalong | Maniki | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Date Started:
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | Construction of Municipal Triball Hall, Talaingod |  | 20% Development Fund CY 2020 | Building |  | sq.m | Contract | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Date Started:
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | DISASTER PREVENTION AND MITIGATION PROGRAM - FLOOD CONTROL AND SLOPE PROTECTION PROJECT (Revetment of Dike and Slope Protection) | Rehab./Impv't. of Sto. Niño-Daligdigon-Paiton |  | 5% CALAMITY FUND CY 2020 | Road |  | km |  | Project Cost: | 1000000 | Target Completion Date: |  | Program: | 1000000 | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | DISASTER PREVENTION AND MITIGATION PROGRAM - FLOOD CONTROL AND SLOPE PROTECTION PROJECT (Revetment of Dike and Slope Protection) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 1000000 | Revised: |  | No. of Man-days:
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | DISASTER PREVENTION AND MITIGATION PROGRAM - FLOOD CONTROL AND SLOPE PROTECTION PROJECT (Revetment of Dike and Slope Protection) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | DISASTER PREVENTION AND MITIGATION PROGRAM - FLOOD CONTROL AND SLOPE PROTECTION PROJECT (Revetment of Dike and Slope Protection) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | DISASTER PREVENTION AND MITIGATION PROGRAM - FLOOD CONTROL AND SLOPE PROTECTION PROJECT (Revetment of Dike and Slope Protection) | [7 empty] | Date Allotment Released: |  | Date completed:
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | DISASTER PREVENTION AND MITIGATION PROGRAM - FLOOD CONTROL AND SLOPE PROTECTION PROJECT (Revetment of Dike and Slope Protection) | [7 empty] | Date Started:
Asuncion | Sonlon | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | DISASTER PREVENTION AND MITIGATION PROGRAM - FLOOD CONTROL AND SLOPE PROTECTION PROJECT (Improvement of Bridges and Cross Drainage) | Improvement of Saug-Sonlon-Bdry. Longanapan |  | 5% CALAMITY FUND CY 2020 | Road |  | km |  | Project Cost: | 1000000 | Target Completion Date: |  | Program: | 1000000 | Planned: |  | No. of Persons: |  | For preparation of POW and Plans
Asuncion | Sonlon | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | DISASTER PREVENTION AND MITIGATION PROGRAM - FLOOD CONTROL AND SLOPE PROTECTION PROJECT (Improvement of Bridges and Cross Drainage) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 1000000 | Revised: |  | No. of Man-days:
Asuncion | Sonlon | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | DISASTER PREVENTION AND MITIGATION PROGRAM - FLOOD CONTROL AND SLOPE PROTECTION PROJECT (Improvement of Bridges and Cross Drainage) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Asuncion | Sonlon | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | DISASTER PREVENTION AND MITIGATION PROGRAM - FLOOD CONTROL AND SLOPE PROTECTION PROJECT (Improvement of Bridges and Cross Drainage) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Asuncion | Sonlon | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | DISASTER PREVENTION AND MITIGATION PROGRAM - FLOOD CONTROL AND SLOPE PROTECTION PROJECT (Improvement of Bridges and Cross Drainage) | [7 empty] | Date Allotment Released: |  | Date completed:
Asuncion | Sonlon | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | DISASTER PREVENTION AND MITIGATION PROGRAM - FLOOD CONTROL AND SLOPE PROTECTION PROJECT (Improvement of Bridges and Cross Drainage) | [7 empty] | Date Started:
Kapalong | Gupitan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | Const. of 1 Classroom @ Mankay Integrated School, Gupitan, kapalong |  | SEF CY 2020 | Building |  | sq.m |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Opening of Shopping on June 25, 2020
Kapalong | Gupitan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Kapalong | Gupitan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Kapalong | Gupitan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Kapalong | Gupitan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Kapalong | Gupitan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Date Started:
Kapalong | Gupitan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | Const. of 1 Classroom @ Luno-luno E/S, Gupitan, kapalong |  | SEF CY 2020 | Building |  | sq.m |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Opening of Shopping on June 25, 2020
Kapalong | Gupitan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Kapalong | Gupitan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Kapalong | Gupitan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Kapalong | Gupitan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Kapalong | Gupitan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Date Started:
Kapalong | Gupitan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | Const. of 1 Classroom @ Kamunuan E/S, Gupitan, kapalong |  | SEF CY 2020 | Building |  | sq.m |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Opening of Shopping on June 25, 2020
Kapalong | Gupitan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Kapalong | Gupitan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Kapalong | Gupitan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Kapalong | Gupitan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Kapalong | Gupitan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Date Started:
Kapalong | Gupitan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | Const. of 1 Classroom @ Tawinian E/S, Gupitan, kapalong |  | SEF CY 2020 | Building |  | sq.m |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Opening of Shopping on June 25, 2020
Kapalong | Gupitan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Kapalong | Gupitan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Kapalong | Gupitan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Kapalong | Gupitan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Kapalong | Gupitan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Date Started:
Kapalong | Gupitan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | Const. of 1 Classroom @ Aninipot E/S, Gupitan, kapalong |  | SEF CY 2020 | Building |  | sq.m |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Opening of Shopping on June 25, 2020
Kapalong | Gupitan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Kapalong | Gupitan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Kapalong | Gupitan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Kapalong | Gupitan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Kapalong | Gupitan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Date Started:
Kapalong | Gupitan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | Const. of 1 Classroom @ Moling E/S, Gupitan, kapalong |  | SEF CY 2020 | Building |  | sq.m |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Opening of Shopping on June 25, 2020
Kapalong | Gupitan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Kapalong | Gupitan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Kapalong | Gupitan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Kapalong | Gupitan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Kapalong | Gupitan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Date Started:
Talaingod | Dagohoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | Const. of 1 Classroom @ Lomondong E/S, Dagohoy, Talaingod |  | SEF CY 2020 | Building |  | sq.m |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Opening of Shopping on June 25, 2020
Talaingod | Dagohoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Talaingod | Dagohoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Talaingod | Dagohoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Talaingod | Dagohoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Talaingod | Dagohoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Date Started:
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | Const. of 1 Classroom @ Malapanit E/S, Sto. Niño, Talaingod |  | SEF CY 2020 | Building |  | sq.m |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Opening of Shopping on June 25, 2020
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Date Started:
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | Const. of 1 Classroom @ Laputlakan E/S, Sto. Niño, Talaingod |  | SEF CY 2020 | Building |  | sq.m |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Opening of Shopping on June 25, 2020
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Date Started:
New Corella | Limbaan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | Const. of Day Care Center, Limbaan, New Corella |  | 20% DF CY 2020 | Building |  | sq.m |  | Project Cost: | 1000000 | Target Completion Date: |  | Program: | 1000000 | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
New Corella | Limbaan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 1000000 | Revised: |  | No. of Man-days:
New Corella | Limbaan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
New Corella | Limbaan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | Limbaan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
New Corella | Limbaan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Date Started:
Kapalong | Gabuyan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | Const. of Day Care Center, Gabuyan, kapalong |  | 20% DF CY 2020 | Building |  | sq.m |  | Project Cost: | 1000000 | Target Completion Date: |  | Program: | 1000000 | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
Kapalong | Gabuyan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 1000000 | Revised: |  | No. of Man-days:
Kapalong | Gabuyan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Kapalong | Gabuyan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Kapalong | Gabuyan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Kapalong | Gabuyan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Date Started:
Asuncion | Canatan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | Compl./Rep. Day Care Center,Canatan, Asuncion |  | 20% DF CY 2020 | Building |  | sq.m |  | Project Cost: | 300000 | Target Completion Date: |  | Program: | 300000 | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
Asuncion | Canatan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 300000 | Revised: |  | No. of Man-days:
Asuncion | Canatan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Asuncion | Canatan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Asuncion | Canatan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Asuncion | Canatan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Date Started:
Asuncion | Cambanogoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | Compl./Rep. Day Care Center,Cambanogoy, Asuncion |  | 20% DF CY 2020 | Building |  | sq.m |  | Project Cost: | 300000 | Target Completion Date: |  | Program: | 300000 | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
Asuncion | Cambanogoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 300000 | Revised: |  | No. of Man-days:
Asuncion | Cambanogoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Asuncion | Cambanogoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Asuncion | Cambanogoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Asuncion | Cambanogoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Date Started:
Kapalong | Gabuyan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | Compl./Rep. Day Care Center,Gabuyan, kapalong |  | 20% DF CY 2020 | Building |  | sq.m |  | Project Cost: | 600000 | Target Completion Date: |  | Program: | 600000 | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
Kapalong | Gabuyan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 600000 | Revised: |  | No. of Man-days:
Kapalong | Gabuyan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Kapalong | Gabuyan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Kapalong | Gabuyan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Kapalong | Gabuyan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Date Started:
New Corella | New Sambog | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | Compl./Rep. Day Care Center,New Sambog, New Corella |  | 20% DF CY 2020 | Building |  | sq.m |  | Project Cost: | 300000 | Target Completion Date: |  | Program: | 300000 | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
New Corella | New Sambog | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 300000 | Revised: |  | No. of Man-days:
New Corella | New Sambog | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
New Corella | New Sambog | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | New Sambog | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
New Corella | New Sambog | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Date Started:
New Corella | Cabidianan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | Compl./Rep. Day Care Center, Cabidianan, New Corella |  | 20% DF CY 2020 | Building |  | sq.m |  | Project Cost: | 300000 | Target Completion Date: |  | Program: | 300000 | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
New Corella | Cabidianan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 300000 | Revised: |  | No. of Man-days:
New Corella | Cabidianan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
New Corella | Cabidianan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | Cabidianan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
New Corella | Cabidianan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Date Started:
San Isidro | Igangon | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | Compl./Rep. Day Care Center, Igangon, San Isidro |  | 20% DF CY 2020 | Building |  | sq.m |  | Project Cost: | 300000 | Target Completion Date: |  | Program: | 300000 | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
San Isidro | Igangon | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 300000 | Revised: |  | No. of Man-days:
San Isidro | Igangon | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
San Isidro | Igangon | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
San Isidro | Igangon | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
San Isidro | Igangon | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Date Started:
Tagum City | Madaum | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | Compl./Rep. Day Care Center, Madaum, Tagum City |  | 20% DF CY 2020 | Building |  | sq.m |  | Project Cost: | 300000 | Target Completion Date: |  | Program: | 300000 | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
Tagum City | Madaum | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 300000 | Revised: |  | No. of Man-days:
Tagum City | Madaum | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Tagum City | Madaum | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Tagum City | Madaum | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Tagum City | Madaum | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Date Started:
Tagum City | Apokon | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | Compl./Rep. Day Care Center, Apokon, Tagum City |  | 20% DF CY 2020 | Building |  | sq.m |  | Project Cost: | 300000 | Target Completion Date: |  | Program: | 300000 | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
Tagum City | Apokon | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 300000 | Revised: |  | No. of Man-days:
Tagum City | Apokon | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Tagum City | Apokon | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Tagum City | Apokon | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Tagum City | Apokon | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Date Started:
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | Compl./Rep. Day Care Center, Sto. Niño, Talaingod |  | 20% DF CY 2020 | Building |  | sq.m |  | Project Cost: | 300000 | Target Completion Date: |  | Program: | 300000 | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 300000 | Revised: |  | No. of Man-days:
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Date Started:
New Corella | Poblacion | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | HEALTH CARE SERVICES PROGRAM (PEEDO) | Improvement/Rehab. Of Luntiang Paraiso, New Corella |  | 20% DF CY 2020 | Building |  | km |  | Project Cost: | 3000000 | Target Completion Date: |  | Program: | 3000000 | Planned: |  | No. of Persons: |  | For Purchase Request
New Corella | Poblacion | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | HEALTH CARE SERVICES PROGRAM (PEEDO) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 3000000 | Revised: |  | No. of Man-days:
New Corella | Poblacion | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | HEALTH CARE SERVICES PROGRAM (PEEDO) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
New Corella | Poblacion | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | HEALTH CARE SERVICES PROGRAM (PEEDO) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | Poblacion | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | HEALTH CARE SERVICES PROGRAM (PEEDO) | [7 empty] | Date Allotment Released: |  | Date completed:
New Corella | Poblacion | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | HEALTH CARE SERVICES PROGRAM (PEEDO) | [7 empty] | Date Started:
Tagum City | Mankilam | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | PSYDO YOUTH DEV'T. PROGRAM - TEEN TAMBAYAN PROJECT | Renovation of Teen Tambayan |  | 20% DF CY 2020 | Building |  | sq.m |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Date of procurement June 30, 2020
Tagum City | Mankilam | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | PSYDO YOUTH DEV'T. PROGRAM - TEEN TAMBAYAN PROJECT | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Tagum City | Mankilam | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | PSYDO YOUTH DEV'T. PROGRAM - TEEN TAMBAYAN PROJECT | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Tagum City | Mankilam | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | PSYDO YOUTH DEV'T. PROGRAM - TEEN TAMBAYAN PROJECT | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Tagum City | Mankilam | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | PSYDO YOUTH DEV'T. PROGRAM - TEEN TAMBAYAN PROJECT | [7 empty] | Date Allotment Released: |  | Date completed:
Tagum City | Mankilam | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | PSYDO YOUTH DEV'T. PROGRAM - TEEN TAMBAYAN PROJECT | [7 empty] | Date Started:
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2020-06-01 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SPECIAL TRUST FUND (PDRRMC) | Installation of 20 units Isolation Room, Sports Academy Dormitory, DNSTC |  | TF | Isolation | 20 | sq.m | Admin | Project Cost: | 170000 | Target Completion Date: |  | Program: | 170000 | Planned: | 95% | No. of Persons: |  | On-going
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2020-06-01 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SPECIAL TRUST FUND (PDRRMC) | [7 empty] | Project Engineer: | Chua | Revised Completion Date: |  | Allotment: | 170000 | Revised: |  | No. of Man-days:
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2020-06-01 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SPECIAL TRUST FUND (PDRRMC) | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: | 95%
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2020-06-01 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SPECIAL TRUST FUND (PDRRMC) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2020-06-01 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SPECIAL TRUST FUND (PDRRMC) | [7 empty] | Date Allotment Released: | 2020-06-01 | Date completed:
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2020-06-01 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SPECIAL TRUST FUND (PDRRMC) | [7 empty] | Date Started: | 2020-06-01
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2020-06-01 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SPECIAL TRUST FUND (PDRRMC) | Installation of 100 units isolation room (2.0 x 3.0m), DAVNOR GYM |  | TF | Isolation | 100 | sq.m | Admin | Project Cost: | 750000 | Target Completion Date: |  | Program: | 750000 | Planned: | 95% | No. of Persons: |  | On-going
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2020-06-01 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SPECIAL TRUST FUND (PDRRMC) | [7 empty] | Project Engineer: | Chua | Revised Completion Date: |  | Allotment: | 750000 | Revised: |  | No. of Man-days:
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2020-06-01 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SPECIAL TRUST FUND (PDRRMC) | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: | 95%
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2020-06-01 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SPECIAL TRUST FUND (PDRRMC) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2020-06-01 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SPECIAL TRUST FUND (PDRRMC) | [7 empty] | Date Allotment Released: | 2020-06-01 | Date completed:
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2020-06-01 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SPECIAL TRUST FUND (PDRRMC) | [7 empty] | Date Started: | 2020-06-01
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2020-06-01 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SPECIAL TRUST FUND (PDRRMC) | Installation of 40 units Isolation Room, Sports Academy Dormitory, DNSTC |  | TF | Isolation | 40 | sq.m | Admin | Project Cost: | 320000 | Target Completion Date: |  | Program: | 320000 | Planned: | 95% | No. of Persons: |  | On-going
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2020-06-01 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SPECIAL TRUST FUND (PDRRMC) | [7 empty] | Project Engineer: | Chua | Revised Completion Date: |  | Allotment: | 320000 | Revised: |  | No. of Man-days:
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2020-06-01 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SPECIAL TRUST FUND (PDRRMC) | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: | 95%
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2020-06-01 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SPECIAL TRUST FUND (PDRRMC) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2020-06-01 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SPECIAL TRUST FUND (PDRRMC) | [7 empty] | Date Allotment Released: | 2020-05-28 | Date completed:
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2020-06-01 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SPECIAL TRUST FUND (PDRRMC) | [7 empty] | Date Started: | 2020-06-01
Talaingod | Palma Gil | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | PEACE AND ORDER PROGRAM | Proposed Road Opening of Nasilaban - Pongpong Road Section, Talaingod |  | SB # 1 CY 2020 | Road |  | km |  | Project Cost: | 5500000 | Target Completion Date: |  | Program: | 5500000 | Planned: |  | No. of Persons: |  | PO #2020062105 - M3C CONSTRUCTION & SUPPLY; PO #2020061966 - FL2 LUMBER & CONSTRUCTION SUPPLY; PO #2020062217 - Alpebel Builders and Supply Corporation, PO #DIOCESAN PRINTING PRESS
Talaingod | Palma Gil | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | PEACE AND ORDER PROGRAM | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 5500000 | Revised: |  | No. of Man-days:
Talaingod | Palma Gil | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | PEACE AND ORDER PROGRAM | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Talaingod | Palma Gil | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | PEACE AND ORDER PROGRAM | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Talaingod | Palma Gil | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | PEACE AND ORDER PROGRAM | [7 empty] | Date Allotment Released: |  | Date completed:
Talaingod | Palma Gil | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | PEACE AND ORDER PROGRAM | [7 empty] | Date Started:
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOV'T. BLDG. & FAC. DEV'T. PROJECT | Establishment of Multiplier Farm Phase 2, Brgy. Sto. Niño, Talaingod |  | SB # 1 CY 2020 | Building |  | sq.m |  | Project Cost: | 380000 | Target Completion Date: |  | Program: | 380000 | Planned: |  | No. of Persons: |  | For bidding on June 30, 2020; Re-bid July 28, 2020.
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOV'T. BLDG. & FAC. DEV'T. PROJECT | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 380000 | Revised: |  | No. of Man-days:
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOV'T. BLDG. & FAC. DEV'T. PROJECT | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOV'T. BLDG. & FAC. DEV'T. PROJECT | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOV'T. BLDG. & FAC. DEV'T. PROJECT | [7 empty] | Date Allotment Released: |  | Date completed:
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOV'T. BLDG. & FAC. DEV'T. PROJECT | [7 empty] | Date Started:
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOV'T. BLDG. & FAC. DEV'T. PROJECT | Establishment of Multiplier Farm (Poultry House), Phase 2, Brgy. Sto. Niño, Talaingod |  | SB # 1 CY 2020 | Building |  | sq.m |  | Project Cost: | 110000 | Target Completion Date: |  | Program: | 110000 | Planned: |  | No. of Persons: |  | For bidding on June 30, 2020; Re-bid July 28, 2020.
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOV'T. BLDG. & FAC. DEV'T. PROJECT | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 110000 | Revised: |  | No. of Man-days:
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOV'T. BLDG. & FAC. DEV'T. PROJECT | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOV'T. BLDG. & FAC. DEV'T. PROJECT | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOV'T. BLDG. & FAC. DEV'T. PROJECT | [7 empty] | Date Allotment Released: |  | Date completed:
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOV'T. BLDG. & FAC. DEV'T. PROJECT | [7 empty] | Date Started:
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOV'T. BLDG. & FAC. DEV'T. PROJECT | Poultry House and Training Center Phase 2, Talaingod |  | SB # 1 CY 2020 | Building |  | sq.m |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | For bidding on June 30, 2020; Re-bid July 28, 2020.
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOV'T. BLDG. & FAC. DEV'T. PROJECT | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOV'T. BLDG. & FAC. DEV'T. PROJECT | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOV'T. BLDG. & FAC. DEV'T. PROJECT | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOV'T. BLDG. & FAC. DEV'T. PROJECT | [7 empty] | Date Allotment Released: |  | Date completed:
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOV'T. BLDG. & FAC. DEV'T. PROJECT | [7 empty] | Date Started:
Kapalong | Maniki | 1st Eng'g. Dist. | On-going | 2020-05-11 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | BAYANIHAN GRANT TO PROVINCES | Improvement of Hospital facilities (Isolation/ICU), Kapalong Dist. Hospital |  | SB # 2 CY 2020 | Isolation |  | sq.m | Admin | Project Cost: | 6000000 | Target Completion Date: | 2021-01-10 23:59 | Program: | 6000000 | Planned: | 11.27% | No. of Persons: | 30 | On-going
Kapalong | Maniki | 1st Eng'g. Dist. | On-going | 2020-05-11 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | BAYANIHAN GRANT TO PROVINCES | [7 empty] | Project Engineer: | Pasiona/Aclaracion | Revised Completion Date: |  | Allotment: | 6000000 | Revised: |  | No. of Man-days: | 930
Kapalong | Maniki | 1st Eng'g. Dist. | On-going | 2020-05-11 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | BAYANIHAN GRANT TO PROVINCES | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: | 51.69%
Kapalong | Maniki | 1st Eng'g. Dist. | On-going | 2020-05-11 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | BAYANIHAN GRANT TO PROVINCES | [7 empty] | Duration: | 245 | No. of days extended: |  |  |  | Slippage: | 40.42%
Kapalong | Maniki | 1st Eng'g. Dist. | On-going | 2020-05-11 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | BAYANIHAN GRANT TO PROVINCES | [7 empty] | Date Allotment Released: | 2020-05-07 | Date completed:
Kapalong | Maniki | 1st Eng'g. Dist. | On-going | 2020-05-11 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | BAYANIHAN GRANT TO PROVINCES | [7 empty] | Date Started: | 2020-05-11
Kapalong | Gabuyan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | CMGP | Road Improvement of Jct. Highway Gabuyan – Semong – Dagohoy Provincial Road |  | CMGP | Road |  | km |  | Project Cost: | 63458000 | Target Completion Date: |  | Program: | 63458000 | Planned: |  | No. of Persons: |  | For posting
Kapalong | Gabuyan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | CMGP | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 63458000 | Revised: |  | No. of Man-days:
Kapalong | Gabuyan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | CMGP | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Kapalong | Gabuyan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | CMGP | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Kapalong | Gabuyan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | CMGP | [7 empty] | Date Allotment Released: |  | Date completed:
Kapalong | Gabuyan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | CMGP | [7 empty] | Date Started:
Talaingod | Palma Gil | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | NHA | Const. of 100 Housing Units at Balai Lupowanan at Sitio Nasilaban, Palma Gil, Talaingod |  | Natinal Housing Project CY 2020 | Building | 100 | units | Admin | Project Cost: | 20000000 | Target Completion Date: |  | Program: | 20000000 | Planned: |  | No. of Persons: |  | For bidding on July 3, 2020
Talaingod | Palma Gil | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | NHA | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 20000000 | Revised: |  | No. of Man-days:
Talaingod | Palma Gil | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | NHA | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Talaingod | Palma Gil | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | NHA | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Talaingod | Palma Gil | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | NHA | [7 empty] | Date Allotment Released: |  | Date completed:
Talaingod | Palma Gil | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | NHA | [7 empty] | Date Started:
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | NHA | Const. of 100 Housing Units at Balai Pig Immimanan at Sitio Mesulong, Sto. Niño, Talaingod |  | Natinal Housing Project CY 2020 | Building | 100 | units | Admin | Project Cost: | 20000000 | Target Completion Date: |  | Program: | 20000000 | Planned: |  | No. of Persons: |  | For bidding on July 3, 2020
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | NHA | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 20000000 | Revised: |  | No. of Man-days:
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | NHA | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | NHA | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | NHA | [7 empty] | Date Allotment Released: |  | Date completed:
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | NHA | [7 empty] | Date Started:
Panabo City | San Roque | 2nd Eng'g. Dist. | Completed |  | 2020-06-30 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) LS - P9,000,000.00 | Const. of MP Bldg. w/ Electrical installation, San Roque, Panabo City |  | 20% DF CY 2017 (STIMULUS) | Building |  | ln.m | MLGU | Project Cost: | 500000 | Target Completion Date: | 6/10/2019 | Program: | 500000 | Planned: | 100% | No. of Persons: |  | Completed as per physical accomplishment. Financial documents still on process.
Panabo City | San Roque | 2nd Eng'g. Dist. | Completed |  | 2020-06-30 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) LS - P9,000,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Panabo City | San Roque | 2nd Eng'g. Dist. | Completed |  | 2020-06-30 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) LS - P9,000,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: | 100%
Panabo City | San Roque | 2nd Eng'g. Dist. | Completed |  | 2020-06-30 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) LS - P9,000,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Panabo City | San Roque | 2nd Eng'g. Dist. | Completed |  | 2020-06-30 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) LS - P9,000,000.00 | [7 empty] | Date Allotment Released: | 2018-01-31 | Date completed: | 2019-06-10
Panabo City | San Roque | 2nd Eng'g. Dist. | Completed |  | 2020-06-30 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) LS - P9,000,000.00 | [7 empty] | Date Started:
B.E. Dujali | Magupising | 2nd Eng'g. Dist. | Completed | 2019-12-02 | 2020-05-29 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | Rehab.of Dujali - Balisong - Magupising Provincial Road |  | 20% DF CY 2019 | Road Rehabilitation | 19.16 | km | MBA | Project Cost: | 1280000 | Target Completion Date: | 2020-01-15 23:59 | Program: | 1280000 | Planned: | 100% | No. of Persons: | 12 | Completed as per physical accomplishment. Financial documents still on process.
B.E. Dujali | Magupising | 2nd Eng'g. Dist. | Completed | 2019-12-02 | 2020-05-29 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Project Engineer: | Mellomida | Revised Completion Date: | 2020-05-31 23:59 | Allotment: | 1280000 | Revised: |  | No. of Man-days: | 900
B.E. Dujali | Magupising | 2nd Eng'g. Dist. | Completed | 2019-12-02 | 2020-05-29 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Implementor: | PEO | No. of days suspended: | 137 | Disbursement: | 14331.6 | Actual: | 100%
B.E. Dujali | Magupising | 2nd Eng'g. Dist. | Completed | 2019-12-02 | 2020-05-29 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Duration: | 45 | No. of days extended: |  |  |  | Slippage: | 0%
B.E. Dujali | Magupising | 2nd Eng'g. Dist. | Completed | 2019-12-02 | 2020-05-29 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Date Allotment Released: |  | Date completed: | 2020-05-29
B.E. Dujali | Magupising | 2nd Eng'g. Dist. | Completed | 2019-12-02 | 2020-05-29 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Date Started: | 2019-12-02
Sto. Tomas | Tibal-og | 2nd Eng'g. Dist. | Completed | 2019-02-22 | 2020-06-30 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPPAP-PAMANA | Construction of Tribal Hall, Sto. Tomas |  | OPPAP-PAMANA CY 2017 | Building |  | sq.m | Admin | Project Cost: | 500000 | Target Completion Date: | 2019-07-31 | Program: | 500000 | Planned: | 100% | No. of Persons: | 7 | Resume last June 22, 2020; Completed as per physical accomplishment. Financial documents still on process.
Sto. Tomas | Tibal-og | 2nd Eng'g. Dist. | Completed | 2019-02-22 | 2020-06-30 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPPAP-PAMANA | [7 empty] | Project Engineer: | Roque | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days: | 110
Sto. Tomas | Tibal-og | 2nd Eng'g. Dist. | Completed | 2019-02-22 | 2020-06-30 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPPAP-PAMANA | [7 empty] | Implementor: | Admin | No. of days suspended: |  | Disbursement: |  | Actual: | 100%
Sto. Tomas | Tibal-og | 2nd Eng'g. Dist. | Completed | 2019-02-22 | 2020-06-30 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPPAP-PAMANA | [7 empty] | Duration: | 70 | No. of days extended: |  |  |  | Slippage: | 0%
Sto. Tomas | Tibal-og | 2nd Eng'g. Dist. | Completed | 2019-02-22 | 2020-06-30 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPPAP-PAMANA | [7 empty] | Date Allotment Released: | CY 2018 | Date completed: | 2020-06-30
Sto. Tomas | Tibal-og | 2nd Eng'g. Dist. | Completed | 2019-02-22 | 2020-06-30 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPPAP-PAMANA | [7 empty] | Date Started: | 2019-05-22
Panabo City | Lasang | 2nd Eng'g. Dist. | On-going | 2015-05-30 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOV'T. BLDG. & FAC. DEV'T. PROJECT | Proposed Davao del Norte Tourism Billboard, Brgy. Lasang, Panabo City |  | SB # 1 CY 2015 | Billboard |  | sq.m | Admin | Project Cost: | 756400 | Target Completion Date: | 2015-05-10 23:59 | Program: | 756400 | Planned: | 11.78% | No. of Persons: |  | delay due to change location & design code. For AIP amendment from Panabo City to Gov't Center, Mankilam
Panabo City | Lasang | 2nd Eng'g. Dist. | On-going | 2015-05-30 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOV'T. BLDG. & FAC. DEV'T. PROJECT | [7 empty] | Project Engineer: | Porras | Revised Completion Date: |  | Allotment: | 756400 | Revised: |  | No. of Man-days:
Panabo City | Lasang | 2nd Eng'g. Dist. | On-going | 2015-05-30 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOV'T. BLDG. & FAC. DEV'T. PROJECT | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: | 332087.3 | Actual: | 11.78%
Panabo City | Lasang | 2nd Eng'g. Dist. | On-going | 2015-05-30 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOV'T. BLDG. & FAC. DEV'T. PROJECT | [7 empty] | Duration: | 42 | No. of days extended: |  |  |  | Slippage: | 0%
Panabo City | Lasang | 2nd Eng'g. Dist. | On-going | 2015-05-30 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOV'T. BLDG. & FAC. DEV'T. PROJECT | [7 empty] | Date Allotment Released: | 2015-05-06 | Date completed:
Panabo City | Lasang | 2nd Eng'g. Dist. | On-going | 2015-05-30 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOV'T. BLDG. & FAC. DEV'T. PROJECT | [7 empty] | Date Started: | 2015-03-30
Sto. Tomas | Esperanza | 2nd Eng'g. Dist. | On-going | 2017-03-22 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PRDP | Rehab. of Esperanza-Pob. Sto. Tomas, FMR, DDN |  | PRDP CY 2014 | Road Concreting | 12.774 | km | Contract | Project Cost: | 117410426.3 | Target Completion Date: | 2019-07-22 23:59 | Program: | 117410426.3 | Planned: | 100% | No. of Persons: | 20 | On-going (Waiting for approve Variation order for billing)
Sto. Tomas | Esperanza | 2nd Eng'g. Dist. | On-going | 2017-03-22 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PRDP | [7 empty] | Project Engineer: | Palero | Revised Completion Date: | 2020-07-31 23:59 | Allotment: | 117410426.3 | Revised: | 95.53% | No. of Man-days: | 600
Sto. Tomas | Esperanza | 2nd Eng'g. Dist. | On-going | 2017-03-22 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PRDP | [7 empty] | Implementor: | ALZAM | No. of days suspended: |  | Disbursement: |  | Actual: | 87.82%
Sto. Tomas | Esperanza | 2nd Eng'g. Dist. | On-going | 2017-03-22 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PRDP | [7 empty] | Duration: | 853 | No. of days extended: | 375 |  |  | Slippage: | -7.705%
Sto. Tomas | Esperanza | 2nd Eng'g. Dist. | On-going | 2017-03-22 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PRDP | [7 empty] | Date Allotment Released: | CY 2014 | Date completed:
Sto. Tomas | Esperanza | 2nd Eng'g. Dist. | On-going | 2017-03-22 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PRDP | [7 empty] | Date Started: | 2017-03-22
Sto. Tomas | Poblacion | 2nd Eng'g. Dist. | For Implementation | 2018-01-29 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PRDP | Improvement of Sto. Tomas Production Center with Common Facility, Sto. Tomas |  | PRDP CY 2016 | Building | 1901 | sq.m | Contract | Project Cost: | 9825000 | Target Completion Date: | 2018-12-24 23:59 | Program: | 9825000 | Planned: |  | No. of Persons: |  | Suspended due to land unsettlement. Revised POW and DED On-going
Sto. Tomas | Poblacion | 2nd Eng'g. Dist. | For Implementation | 2018-01-29 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PRDP | [7 empty] | Project Engineer: | Azotes | Revised Completion Date: |  | Allotment: | 9825000 | Revised: |  | No. of Man-days:
Sto. Tomas | Poblacion | 2nd Eng'g. Dist. | For Implementation | 2018-01-29 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PRDP | [7 empty] | Implementor: | Manantan | No. of days suspended: |  | Disbursement: |  | Actual:
Sto. Tomas | Poblacion | 2nd Eng'g. Dist. | For Implementation | 2018-01-29 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PRDP | [7 empty] | Duration: | 330 | No. of days extended: |  |  |  | Slippage: | 0%
Sto. Tomas | Poblacion | 2nd Eng'g. Dist. | For Implementation | 2018-01-29 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PRDP | [7 empty] | Date Allotment Released: | CY 2014 | Date completed:
Sto. Tomas | Poblacion | 2nd Eng'g. Dist. | For Implementation | 2018-01-29 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PRDP | [7 empty] | Date Started: | 2018-01-29
IGCS | Kinawitnon | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PRDP | Inst. of transformer and accessories, Brgy. Kinawitnon |  | PRDP CY 2016 | Electrification |  |  | Admin | Project Cost: | 150000 | Target Completion Date: |  | Program: | 150000 | Planned: |  | No. of Persons: |  | Purchase Order # 2019103228 - Transformer; Purchase Order # 2019102931 - Billboard; Purchase Order # 2019103227 - Lumber
IGCS | Kinawitnon | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PRDP | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 150000 | Revised: |  | No. of Man-days:
IGCS | Kinawitnon | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PRDP | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
IGCS | Kinawitnon | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PRDP | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
IGCS | Kinawitnon | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PRDP | [7 empty] | Date Allotment Released: | 2018-07-31 | Date completed:
IGCS | Kinawitnon | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PRDP | [7 empty] | Date Started:
Samal | Sta. Cruz | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | RURAL ELECTRIFICATION PROJECT | Rural Electrification at brgy. Sta. Cruz, talikud, Samal |  | 20% DF CY 2016 | Electrification |  |  | Contract | Project Cost: | 2000000 | Target Completion Date: |  | Program: | 2000000 | Planned: |  | No. of Persons: |  | Delay due to slow action of Daneco for staking. c/o Engr. Kim
Samal | Sta. Cruz | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | RURAL ELECTRIFICATION PROJECT | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 2000000 | Revised: |  | No. of Man-days:
Samal | Sta. Cruz | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | RURAL ELECTRIFICATION PROJECT | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Samal | Sta. Cruz | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | RURAL ELECTRIFICATION PROJECT | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Samal | Sta. Cruz | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | RURAL ELECTRIFICATION PROJECT | [7 empty] | Date Allotment Released: |  | Date completed:
Samal | Sta. Cruz | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | RURAL ELECTRIFICATION PROJECT | [7 empty] | Date Started:
BABAK | Kinawitnon | 2nd Eng'g. Dist. | On-going | 2018-03-12 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) LS - P9,000,000.00 | Construction of Provincial Training Center , Compound Fence, Kinawitnon, Babak District, IGCS |  | 20% DF CY 2016 | Fence |  | sq.m | Admin | Project Cost: | 940000 | Target Completion Date: | 2018-06-19 23:59 | Program: | 940000 | Planned: | 68% | No. of Persons: |  | Temporarily suspended 4/23/18 due to undemolished structures of illegal settlers
BABAK | Kinawitnon | 2nd Eng'g. Dist. | On-going | 2018-03-12 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) LS - P9,000,000.00 | [7 empty] | Project Engineer: | Pacquiao | Revised Completion Date: |  | Allotment: | 940000 | Revised: |  | No. of Man-days:
BABAK | Kinawitnon | 2nd Eng'g. Dist. | On-going | 2018-03-12 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) LS - P9,000,000.00 | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: | 933418.8 | Actual: | 75%
BABAK | Kinawitnon | 2nd Eng'g. Dist. | On-going | 2018-03-12 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) LS - P9,000,000.00 | [7 empty] | Duration: | 100 | No. of days extended: |  |  |  | Slippage: | 7%
BABAK | Kinawitnon | 2nd Eng'g. Dist. | On-going | 2018-03-12 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) LS - P9,000,000.00 | [7 empty] | Date Allotment Released: | 2017-09-19 | Date completed:
BABAK | Kinawitnon | 2nd Eng'g. Dist. | On-going | 2018-03-12 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) LS - P9,000,000.00 | [7 empty] | Date Started: | 2018-03-12
Panabo City | Consolacion | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) LS - P9,000,000.00 | Const of Market Stall/Building, Consolacion, Panabo City |  | 20% DF CY 2017 (STIMULUS) | Building |  |  | MLGU | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Issued warning for Termination of the Contract
Panabo City | Consolacion | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) LS - P9,000,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Panabo City | Consolacion | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) LS - P9,000,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Panabo City | Consolacion | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) LS - P9,000,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Panabo City | Consolacion | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) LS - P9,000,000.00 | [7 empty] | Date Allotment Released: | 2017-12-28 | Date completed:
Panabo City | Consolacion | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) LS - P9,000,000.00 | [7 empty] | Date Started:
Panabo City | Upper Licanan | 2nd Eng'g. Dist. | On-going | 2017-12-28 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) LS - P9,000,000.00 | Rehab. Of Multi-Purpose Hall (Covered Court), Upper Licanan, Panabo City |  | 20% DF CY 2017 (STIMULUS) | Building |  |  | MLGU | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Fund transfer to LGU- 3/28/2019 with check no.2574927 and OR no. 0166516 - Delivery of Materials on process
Panabo City | Upper Licanan | 2nd Eng'g. Dist. | On-going | 2017-12-28 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) LS - P9,000,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Panabo City | Upper Licanan | 2nd Eng'g. Dist. | On-going | 2017-12-28 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) LS - P9,000,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Panabo City | Upper Licanan | 2nd Eng'g. Dist. | On-going | 2017-12-28 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) LS - P9,000,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Panabo City | Upper Licanan | 2nd Eng'g. Dist. | On-going | 2017-12-28 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) LS - P9,000,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Panabo City | Upper Licanan | 2nd Eng'g. Dist. | On-going | 2017-12-28 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) LS - P9,000,000.00 | [7 empty] | Date Started: | 2017-12-28
Panabo City | Kauswagan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) LS - P9,000,000.00 | Impv't. of Multi-Purpose Gym, Kauswagan, Panabo City |  | 20% DF CY 2017 (STIMULUS) | GYM |  |  | MLGU | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Fund transfer to LGU- 3/28/2019 with check no.2574942 and OR no. 0166515 - procurement on process for bidding 8/5/2019
Panabo City | Kauswagan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) LS - P9,000,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Panabo City | Kauswagan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) LS - P9,000,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Panabo City | Kauswagan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) LS - P9,000,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Panabo City | Kauswagan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) LS - P9,000,000.00 | [7 empty] | Date Allotment Released: | 2019-02-04 | Date completed:
Panabo City | Kauswagan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) LS - P9,000,000.00 | [7 empty] | Date Started:
Panabo City | Cacao | 2nd Eng'g. Dist. | On-going | 2018-12-14 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) LS - P9,000,000.00 | Const. of Multi-Purpose Bldg.,Cacao, Panabo City |  | 20% DF CY 2017 (STIMULUS) | Building |  | sq.m | MLGU | Project Cost: | 300000 | Target Completion Date: |  | Program: | 300000 | Planned: |  | No. of Persons: |  | Issued warning for termination of the contract
Panabo City | Cacao | 2nd Eng'g. Dist. | On-going | 2018-12-14 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) LS - P9,000,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 300000 | Revised: |  | No. of Man-days:
Panabo City | Cacao | 2nd Eng'g. Dist. | On-going | 2018-12-14 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) LS - P9,000,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Panabo City | Cacao | 2nd Eng'g. Dist. | On-going | 2018-12-14 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) LS - P9,000,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Panabo City | Cacao | 2nd Eng'g. Dist. | On-going | 2018-12-14 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) LS - P9,000,000.00 | [7 empty] | Date Allotment Released: | 2017-12-19 | Date completed:
Panabo City | Cacao | 2nd Eng'g. Dist. | On-going | 2018-12-14 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) LS - P9,000,000.00 | [7 empty] | Date Started: | 2018-12-14
Panabo City | A.O. Floreindo | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) LS - P9,000,000.00 | Const. of Multi-Purpose Bldg. @ A.O. Floriendo National Highschool, Panabo City |  | 20% DF CY 2017 (STIMULUS) | Building |  |  | MLGU | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Fund transfer to LGU- 3/28/2019 with check no. 2574939 and OR no. 0166518 - Materials Delivered. Construction on-going
Panabo City | A.O. Floreindo | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) LS - P9,000,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Panabo City | A.O. Floreindo | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) LS - P9,000,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Panabo City | A.O. Floreindo | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) LS - P9,000,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Panabo City | A.O. Floreindo | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) LS - P9,000,000.00 | [7 empty] | Date Allotment Released: | 2017-12-19 | Date completed:
Panabo City | A.O. Floreindo | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) LS - P9,000,000.00 | [7 empty] | Date Started:
Panabo City | Kimamon | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Drainage | Const. of Concrete Drainage Canal, Kimamon, Panabo City |  | 20% DF CY 2017 (STIMULUS) | Drainage |  |  | MLGU | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | For Implementation
Panabo City | Kimamon | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Drainage | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Panabo City | Kimamon | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Drainage | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Panabo City | Kimamon | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Drainage | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Panabo City | Kimamon | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Drainage | [7 empty] | Date Allotment Released: | 2017-12-19 | Date completed:
Panabo City | Kimamon | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Drainage | [7 empty] | Date Started:
IGCS | Anonang | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | RURAL ELECTRIFICATION PROJECT | Impv't. of Brgy. Street Electrification at Brgy. Anonang, IGCS |  | 20% DF CY 2017 (STIMULUS) | Electrification |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Verified at PBO 7/18/2019 that fund is not available. Proposed priority project for 2020.
IGCS | Anonang | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | RURAL ELECTRIFICATION PROJECT | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
IGCS | Anonang | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | RURAL ELECTRIFICATION PROJECT | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual:
IGCS | Anonang | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | RURAL ELECTRIFICATION PROJECT | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
IGCS | Anonang | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | RURAL ELECTRIFICATION PROJECT | [7 empty] | Date Allotment Released: | 2017-11-28 | Date completed:
IGCS | Anonang | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | RURAL ELECTRIFICATION PROJECT | [7 empty] | Date Started:
Panabo City | Datu Abdul | 2nd Eng'g. Dist. | On-going | 2019-11-21 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPPAP-PAMANA | Const. of Trading Post, Storage Building with (1) unit Hauling Truck, Prk. Ramihan Datu Abdul, Panabo City |  | OPPAP-PAMANA CY 2017 | Building |  | sq.m | Contract | Project Cost: | 3975000 | Target Completion Date: | 2020-04-05 23:59 | Program: | 3975000 | Planned: | 100% | No. of Persons: | 10 | On-going
Panabo City | Datu Abdul | 2nd Eng'g. Dist. | On-going | 2019-11-21 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPPAP-PAMANA | [7 empty] | Project Engineer: | Azotes | Revised Completion Date: | 2020-05-16 23:59 | Allotment: | 3975000 | Revised: | 40.36% | No. of Man-days: | 260
Panabo City | Datu Abdul | 2nd Eng'g. Dist. | On-going | 2019-11-21 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPPAP-PAMANA | [7 empty] | Implementor: | Ultra Core | No. of days suspended: | 41 | Disbursement: |  | Actual: | 40.36%
Panabo City | Datu Abdul | 2nd Eng'g. Dist. | On-going | 2019-11-21 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPPAP-PAMANA | [7 empty] | Duration: | 137 | No. of days extended: |  |  |  | Slippage: | 0%
Panabo City | Datu Abdul | 2nd Eng'g. Dist. | On-going | 2019-11-21 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPPAP-PAMANA | [7 empty] | Date Allotment Released: | CY 2017 | Date completed:
Panabo City | Datu Abdul | 2nd Eng'g. Dist. | On-going | 2019-11-21 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPPAP-PAMANA | [7 empty] | Date Started: | 2019-11-21
Samal | Kinawitnon | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPPAP-PAMANA | Trading Post, Storage and Hauling Truck Libuak, Island Garden City of Samal (IGACOS) |  | OPPAP-PAMANA CY 2017 | Building |  |  |  | Project Cost: | 4000000 | Target Completion Date: |  | Program: | 4000000 | Planned: |  | No. of Persons: |  | For bidding
Samal | Kinawitnon | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPPAP-PAMANA | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 4000000 | Revised: |  | No. of Man-days:
Samal | Kinawitnon | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPPAP-PAMANA | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Samal | Kinawitnon | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPPAP-PAMANA | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Samal | Kinawitnon | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPPAP-PAMANA | [7 empty] | Date Allotment Released: | CY 2018 | Date completed:
Samal | Kinawitnon | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPPAP-PAMANA | [7 empty] | Date Started:
IGCS | Tambo | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPPAP-PAMANA | Agricultural Productivity Support Project-Fishing Equipment, Tambo, IGACOS |  | OPPAP-PAMANA CY 2017 |  |  |  |  | Project Cost: | 1500000 | Target Completion Date: |  | Program: | 1500000 | Planned: |  | No. of Persons: |  | For bidding
IGCS | Tambo | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPPAP-PAMANA | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 1500000 | Revised: |  | No. of Man-days:
IGCS | Tambo | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPPAP-PAMANA | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
IGCS | Tambo | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPPAP-PAMANA | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
IGCS | Tambo | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPPAP-PAMANA | [7 empty] | Date Allotment Released: |  | Date completed:
IGCS | Tambo | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPPAP-PAMANA | [7 empty] | Date Started:
Carmen | Asuncion | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Construction of Water System Projects in Component LGUs LS - 9,750,000.00 | Rehab./Impv't. of San Vicente Water System, Asuncion |  | 20% DF CY 2018 | Water System |  |  | Admin | Project Cost: | 1125000 | Target Completion Date: |  | Program: | 1125000 | Planned: |  | No. of Persons: |  | Abstract # 0220190484
Carmen | Asuncion | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Construction of Water System Projects in Component LGUs LS - 9,750,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 1125000 | Revised: |  | No. of Man-days:
Carmen | Asuncion | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Construction of Water System Projects in Component LGUs LS - 9,750,000.00 | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual:
Carmen | Asuncion | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Construction of Water System Projects in Component LGUs LS - 9,750,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Carmen | Asuncion | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Construction of Water System Projects in Component LGUs LS - 9,750,000.00 | [7 empty] | Date Allotment Released: | 2018-10-26 | Date completed:
Carmen | Asuncion | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Construction of Water System Projects in Component LGUs LS - 9,750,000.00 | [7 empty] | Date Started:
Panabo City | Malativas | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Construction of Water System Projects in Component LGUs LS - 9,750,000.00 | Water System at brgy. Malativas, Panabo City |  | 20% DF CY 2018 | Water System |  |  | Admin | Project Cost: | 1250000 | Target Completion Date: |  | Program: | 1250000 | Planned: |  | No. of Persons: |  | For preparation of POW & Plan c/o PDPM - POSSIBLE TRANSFER OF SITE SUBJECT FOR TRANSFER OF LOCATION . NO DEED OF DONATION
Panabo City | Malativas | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Construction of Water System Projects in Component LGUs LS - 9,750,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 1250000 | Revised: |  | No. of Man-days:
Panabo City | Malativas | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Construction of Water System Projects in Component LGUs LS - 9,750,000.00 | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual:
Panabo City | Malativas | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Construction of Water System Projects in Component LGUs LS - 9,750,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Panabo City | Malativas | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Construction of Water System Projects in Component LGUs LS - 9,750,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Panabo City | Malativas | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Construction of Water System Projects in Component LGUs LS - 9,750,000.00 | [7 empty] | Date Started:
Panabo City | Tibungol | 2nd Eng'g. Dist. | On-going | 2020-01-20 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Construction of Water System Projects in Component LGUs LS - 9,750,000.00 | Const. of Potable Water System at Brgy. Tibungol, Panabo City |  | 20% DF CY 2018 | Water System |  | ln.m | Admin | Project Cost: | 1250000 | Target Completion Date: | 2020-04-15 23:59 | Program: | 1250000 | Planned: | 2.13% | No. of Persons: | 3 | Suspended dated February 19, 2020 undelivered hardware materials (Supplier refused to deliver. Letter already submitted to BAC.)
Panabo City | Tibungol | 2nd Eng'g. Dist. | On-going | 2020-01-20 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Construction of Water System Projects in Component LGUs LS - 9,750,000.00 | [7 empty] | Project Engineer: | Andoy | Revised Completion Date: |  | Allotment: | 1250000 | Revised: |  | No. of Man-days: | 15
Panabo City | Tibungol | 2nd Eng'g. Dist. | On-going | 2020-01-20 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Construction of Water System Projects in Component LGUs LS - 9,750,000.00 | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: | 0.76%
Panabo City | Tibungol | 2nd Eng'g. Dist. | On-going | 2020-01-20 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Construction of Water System Projects in Component LGUs LS - 9,750,000.00 | [7 empty] | Duration: | 87 | No. of days extended: |  |  |  | Slippage: | -1.37%
Panabo City | Tibungol | 2nd Eng'g. Dist. | On-going | 2020-01-20 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Construction of Water System Projects in Component LGUs LS - 9,750,000.00 | [7 empty] | Date Allotment Released: | 2018-11-21 | Date completed:
Panabo City | Tibungol | 2nd Eng'g. Dist. | On-going | 2020-01-20 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Construction of Water System Projects in Component LGUs LS - 9,750,000.00 | [7 empty] | Date Started: | 2020-01-20
Samal, Kaputian | San Remegio | 2nd Eng'g. Dist. | On-going | 2019-07-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Construction of Water System Projects in Component LGUs LS - 9,750,000.00 | Potable Water System at Brgy. San Remegio Kaputian (Level II WS), Samal |  | 20% DF CY 2018 | Water System |  |  | Admin | Project Cost: | 3625000 | Target Completion Date: | 2020-02-01 | Program: | 3625000 | Planned: | 100% | No. of Persons: | 4 | On-going/ Resumption 5/4/2020
Samal, Kaputian | San Remegio | 2nd Eng'g. Dist. | On-going | 2019-07-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Construction of Water System Projects in Component LGUs LS - 9,750,000.00 | [7 empty] | Project Engineer: | Kabigue | Revised Completion Date: | 2020-04-30 | Allotment: | 3625000 | Revised: | 72.04% | No. of Man-days: | 88
Samal, Kaputian | San Remegio | 2nd Eng'g. Dist. | On-going | 2019-07-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Construction of Water System Projects in Component LGUs LS - 9,750,000.00 | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: | 2702800 | Actual: | 74.56%
Samal, Kaputian | San Remegio | 2nd Eng'g. Dist. | On-going | 2019-07-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Construction of Water System Projects in Component LGUs LS - 9,750,000.00 | [7 empty] | Duration: | 200 | No. of days extended: | 89 |  |  | Slippage: | 2.52%
Samal, Kaputian | San Remegio | 2nd Eng'g. Dist. | On-going | 2019-07-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Construction of Water System Projects in Component LGUs LS - 9,750,000.00 | [7 empty] | Date Allotment Released: | 2018-10-25 | Date completed:
Samal, Kaputian | San Remegio | 2nd Eng'g. Dist. | On-going | 2019-07-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Construction of Water System Projects in Component LGUs LS - 9,750,000.00 | [7 empty] | Date Started: | 2019-07-16
Carmen | San Isidro | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | Completion of Evacuation Center Building, San Isidro, Carmen |  | GENERAL FUND PROPER CY 2018 (STIMULUS) | Building |  | sq.m | Contract | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | On-going
Carmen | San Isidro | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | [7 empty] | Project Engineer: | Estorco | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Carmen | San Isidro | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | [7 empty] | Implementor: | RLHV | No. of days suspended: |  | Disbursement: |  | Actual:
Carmen | San Isidro | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | [7 empty] | Duration: | 60 | No. of days extended: |  |  |  | Slippage: | 0%
Carmen | San Isidro | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | [7 empty] | Date Allotment Released: |  | Date completed:
Carmen | San Isidro | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | [7 empty] | Date Started:
Panabo City | Nanyo | 2nd Eng'g. Dist. | On-going | 2020-04-07 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | Const. of Perimeter Fence of Day Care Center 1, Nanyo, Panabo City |  | GENERAL FUND PROPER CY 2018 (STIMULUS) | Building |  | sq.m | Contract | Project Cost: | 500000 | Target Completion Date: | 2020-06-06 | Program: | 500000 | Planned: | 5% | No. of Persons: |  | (RLHV Design & Build) Winning Bidder
Panabo City | Nanyo | 2nd Eng'g. Dist. | On-going | 2020-04-07 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | [7 empty] | Project Engineer: | Estorco | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Panabo City | Nanyo | 2nd Eng'g. Dist. | On-going | 2020-04-07 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | [7 empty] | Implementor: | RLHV | No. of days suspended: |  | Disbursement: |  | Actual: | 5%
Panabo City | Nanyo | 2nd Eng'g. Dist. | On-going | 2020-04-07 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | [7 empty] | Duration: | 60 | No. of days extended: |  |  |  | Slippage: | 0%
Panabo City | Nanyo | 2nd Eng'g. Dist. | On-going | 2020-04-07 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | [7 empty] | Date Allotment Released: |  | Date completed:
Panabo City | Nanyo | 2nd Eng'g. Dist. | On-going | 2020-04-07 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | [7 empty] | Date Started: | 2020-04-07
Panabo City | Malativas | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | Impv't. of Brgy. Road Covered Court, Malativas, Panabo City |  | GENERAL FUND PROPER CY 2018 (STIMULUS) | Court |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Procurement on process
Panabo City | Malativas | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Panabo City | Malativas | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Panabo City | Malativas | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Panabo City | Malativas | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | [7 empty] | Date Allotment Released: |  | Date completed:
Panabo City | Malativas | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | [7 empty] | Date Started:
Panabo City | Maduao | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | Rehab. Of Multi-Purpose Gym & Facililies Maduao, Panabo City |  | GENERAL FUND PROPER CY 2018 (STIMULUS) | Gym |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Post qualification on process
Panabo City | Maduao | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Panabo City | Maduao | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Panabo City | Maduao | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Panabo City | Maduao | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | [7 empty] | Date Allotment Released: |  | Date completed:
Panabo City | Maduao | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | [7 empty] | Date Started:
Panabo City | Sto. Niño | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | Const. of Multi-Purpose Bldg. Sto. Nino, Panabo City |  | GENERAL FUND PROPER CY 2018 (STIMULUS) | Court |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | PR # 20032818
Panabo City | Sto. Niño | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Panabo City | Sto. Niño | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Panabo City | Sto. Niño | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Panabo City | Sto. Niño | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | [7 empty] | Date Allotment Released: |  | Date completed:
Panabo City | Sto. Niño | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | [7 empty] | Date Started:
Panabo City | Dapco | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | Completion of Canopy at DAPCO Covered Court, Dapco, Panabo City |  | GENERAL FUND PROPER CY 2018 (STIMULUS) | Court |  |  | Contract | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | (RLHV Design & Build) Winning Bidder
Panabo City | Dapco | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | [7 empty] | Project Engineer: | RLHV | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Panabo City | Dapco | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Panabo City | Dapco | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Panabo City | Dapco | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | [7 empty] | Date Allotment Released: |  | Date completed:
Panabo City | Dapco | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | [7 empty] | Date Started:
Panabo City | Nanyo | 2nd Eng'g. Dist. | On-going | 2020-04-07 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | Perimeter Fence of Day Care Center I & II, Nanyo, Panabo City/ Construction of Perimeter Fence) |  | GENERAL FUND PROPER CY 2018 (STIMULUS) | Building |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | For implementation (RLHV Design & Build) Winning Bidder
Panabo City | Nanyo | 2nd Eng'g. Dist. | On-going | 2020-04-07 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Panabo City | Nanyo | 2nd Eng'g. Dist. | On-going | 2020-04-07 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Panabo City | Nanyo | 2nd Eng'g. Dist. | On-going | 2020-04-07 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Panabo City | Nanyo | 2nd Eng'g. Dist. | On-going | 2020-04-07 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | [7 empty] | Date Allotment Released: |  | Date completed:
Panabo City | Nanyo | 2nd Eng'g. Dist. | On-going | 2020-04-07 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | [7 empty] | Date Started:
IGCS | Pichon | 2nd Eng'g. Dist. | On-going | 2020-01-13 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | Impv't. of Brgy. Water System, Pichon, IGCS (Construction of Elevated Tank) |  | GENERAL FUND PROPER CY 2018 (STIMULUS) | Water System |  |  | Admin | Project Cost: | 500000 | Target Completion Date: | 2020-03-13 | Program: | 500000 | Planned: | 100% | No. of Persons: | 5 | On-going
IGCS | Pichon | 2nd Eng'g. Dist. | On-going | 2020-01-13 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | [7 empty] | Project Engineer: | Andoy | Revised Completion Date: | 2020-07-31 | Allotment: | 500000 | Revised: | 86% | No. of Man-days: | 110
IGCS | Pichon | 2nd Eng'g. Dist. | On-going | 2020-01-13 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | [7 empty] | Implementor: | PEO | No. of days suspended: | 140 | Disbursement: | 423575.63 | Actual: | 83.5%
IGCS | Pichon | 2nd Eng'g. Dist. | On-going | 2020-01-13 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | [7 empty] | Duration: | 60 | No. of days extended: |  |  |  | Slippage: | -2.5%
IGCS | Pichon | 2nd Eng'g. Dist. | On-going | 2020-01-13 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | [7 empty] | Date Allotment Released: | 2018-05-31 | Date completed:
IGCS | Pichon | 2nd Eng'g. Dist. | On-going | 2020-01-13 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | [7 empty] | Date Started: | 2020-01-13
IGCS | Cogon | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | Powerline Expansion Project, Cogon, IGACOS |  | GENERAL FUND PROPER CY 2018 (STIMULUS) | Water System |  |  | Contract | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Waiting for NTP (3E Electrical)
IGCS | Cogon | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
IGCS | Cogon | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
IGCS | Cogon | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
IGCS | Cogon | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | [7 empty] | Date Allotment Released: |  | Date completed:
IGCS | Cogon | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | [7 empty] | Date Started:
IGCS | Tagbay | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | Water System From Prk. 6 - Prk. 2 - Prk. 5A, Tagbay, IGCS |  | GENERAL FUND PROPER CY 2018 (STIMULUS) | Water System |  |  | Admin | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | For Implementation
IGCS | Tagbay | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
IGCS | Tagbay | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
IGCS | Tagbay | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
IGCS | Tagbay | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | [7 empty] | Date Allotment Released: |  | Date completed:
IGCS | Tagbay | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | [7 empty] | Date Started:
IGCS | Tambo | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | RURAL ELECTRIFICATION PROJECT | Powerline Expansion Project, Tambo, IGCS |  | GENERAL FUND PROPER CY 2018 (STIMULUS) | Electrification |  |  | Contract | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Purchase Request # 19083312
IGCS | Tambo | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | RURAL ELECTRIFICATION PROJECT | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
IGCS | Tambo | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | RURAL ELECTRIFICATION PROJECT | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
IGCS | Tambo | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | RURAL ELECTRIFICATION PROJECT | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
IGCS | Tambo | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | RURAL ELECTRIFICATION PROJECT | [7 empty] | Date Allotment Released: |  | Date completed:
IGCS | Tambo | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | RURAL ELECTRIFICATION PROJECT | [7 empty] | Date Started:
IGCS | Peñaplata | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | Improvement of Barangay Hall, Penaplata, IGCS |  | GENERAL FUND PROPER CY 2018 (STIMULUS) | Building |  |  | Admin | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | By Contract and change to admin due to unforeseen activities because it’s a repair (For revision of POW)
IGCS | Peñaplata | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
IGCS | Peñaplata | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
IGCS | Peñaplata | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
IGCS | Peñaplata | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | [7 empty] | Date Allotment Released: |  | Date completed:
IGCS | Peñaplata | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | [7 empty] | Date Started:
IGCS | Dadatan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | RURAL ELECTRIFICATION PROJECT | Electrification of Sitio Baongon-Diamond-Mansanitas, Dadatan, IGCS |  | GENERAL FUND PROPER CY 2018 (STIMULUS) | Electrification |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Purchase Order # 20200100002 (3E Electrical Sales & Services)
IGCS | Dadatan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | RURAL ELECTRIFICATION PROJECT | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
IGCS | Dadatan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | RURAL ELECTRIFICATION PROJECT | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
IGCS | Dadatan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | RURAL ELECTRIFICATION PROJECT | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
IGCS | Dadatan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | RURAL ELECTRIFICATION PROJECT | [7 empty] | Date Allotment Released: |  | Date completed:
IGCS | Dadatan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | RURAL ELECTRIFICATION PROJECT | [7 empty] | Date Started:
IGCS | Linusotan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Construction of Water System Projects in Component LGUs | Drilling of Water System, Linusotan, IGCS |  | GENERAL FUND PROPER CY 2018 (STIMULUS) | Water System |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
IGCS | Linusotan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Construction of Water System Projects in Component LGUs | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
IGCS | Linusotan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Construction of Water System Projects in Component LGUs | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
IGCS | Linusotan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Construction of Water System Projects in Component LGUs | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
IGCS | Linusotan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Construction of Water System Projects in Component LGUs | [7 empty] | Date Allotment Released: |  | Date completed:
IGCS | Linusotan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Construction of Water System Projects in Component LGUs | [7 empty] | Date Started:
Carmen | Ising | 2nd Eng'g. Dist. | On-going | 2020-03-19 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | Const. of DDN Hospital Carmen Zone Annex Bldg. |  | SB # 1 CY 2018 | Building |  | sq.m | Contract | Project Cost: | 5500000 | Target Completion Date: | 2020-07-17 | Program: | 5500000 | Planned: | 95.2% | No. of Persons: | 10 | On-going
Carmen | Ising | 2nd Eng'g. Dist. | On-going | 2020-03-19 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | [7 empty] | Project Engineer: | Azotes | Revised Completion Date: | 2020-09-12 | Allotment: | 5500000 | Revised: | 40.5% | No. of Man-days: | 260
Carmen | Ising | 2nd Eng'g. Dist. | On-going | 2020-03-19 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | [7 empty] | Implementor: | Digos Constrak Corp/ | No. of days suspended: | 57 | Disbursement: | 1650000 | Actual: | 68.25%
Carmen | Ising | 2nd Eng'g. Dist. | On-going | 2020-03-19 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | [7 empty] | Duration: | 120 | No. of days extended: |  |  |  | Slippage: | 27.75%
Carmen | Ising | 2nd Eng'g. Dist. | On-going | 2020-03-19 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | [7 empty] | Date Allotment Released: |  | Date completed:
Carmen | Ising | 2nd Eng'g. Dist. | On-going | 2020-03-19 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | [7 empty] | Date Started: | 2020-03-19
Carmen | Cebulano | 2nd Eng'g. Dist. | Completed | 2019-05-21 | 2020-05-31 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | Road ID11 Jct. Highway Sto. Niño - Cebulano |  | 20% DF CY 2019 | Road Rehabilitation | 2.09 | km | Admin | Project Cost: | 1045000 | Target Completion Date: | 2019-10-04 | Program: | 1045000 | Planned: | 100% | No. of Persons: | 6 | Completed as per physical accomplishment. Financial documents still on process.
Carmen | Cebulano | 2nd Eng'g. Dist. | Completed | 2019-05-21 | 2020-05-31 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | [7 empty] | Project Engineer: | Obar/ Nasol | Revised Completion Date: | 2020-06-15 | Allotment: | 1045000 | Revised: |  | No. of Man-days: | 132
Carmen | Cebulano | 2nd Eng'g. Dist. | Completed | 2019-05-21 | 2020-05-31 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | [7 empty] | Implementor: | PEO | No. of days suspended: | 194 | Disbursement: | 1045000 | Actual: | 100%
Carmen | Cebulano | 2nd Eng'g. Dist. | Completed | 2019-05-21 | 2020-05-31 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | [7 empty] | Duration: | 136 | No. of days extended: | 61 |  |  | Slippage: | 0%
Carmen | Cebulano | 2nd Eng'g. Dist. | Completed | 2019-05-21 | 2020-05-31 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | [7 empty] | Date Allotment Released: | 2019-01-03 | Date completed: | 2020-05-31
Carmen | Cebulano | 2nd Eng'g. Dist. | Completed | 2019-05-21 | 2020-05-31 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | [7 empty] | Date Started: | 2019-05-21
Carmen | Tubod | 2nd Eng'g. Dist. | Completed | 2019-11-11 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | ROAD ID 076 - Basa - Tubod |  | 20% DF CY 2019 | Road Rehabilitation | 1.56 | km | Admin | Project Cost: | 1000000 | Target Completion Date: | 2020-03-19 23:59 | Program: | 1000000 | Planned: | 100% | No. of Persons: | 3 | Completed as per physical accomplishment. Financial documents still on process.
Carmen | Tubod | 2nd Eng'g. Dist. | Completed | 2019-11-11 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | [7 empty] | Project Engineer: | PIAD | Revised Completion Date: | 2020-06-30 23:59 | Allotment: | 1000000 | Revised: | 100% | No. of Man-days: | 30
Carmen | Tubod | 2nd Eng'g. Dist. | Completed | 2019-11-11 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | [7 empty] | Implementor: | PEO | No. of days suspended: | 103 | Disbursement: |  | Actual: | 100%
Carmen | Tubod | 2nd Eng'g. Dist. | Completed | 2019-11-11 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | [7 empty] | Duration: | 130 | No. of days extended: |  |  |  | Slippage: | 0%
Carmen | Tubod | 2nd Eng'g. Dist. | Completed | 2019-11-11 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | [7 empty] | Date Allotment Released: | 2019-01-03 | Date completed: | 2020-06-30 23:59
Carmen | Tubod | 2nd Eng'g. Dist. | Completed | 2019-11-11 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | [7 empty] | Date Started: | 2019-11-11
Carmen | Tubod | 2nd Eng'g. Dist. | On-going | 2019-12-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | ROAD ID 077 - Tubod - Pilar |  | 20% DF CY 2019 | Road Rehabilitation | 1.55 | km | Admin | Project Cost: | 16000000 | Target Completion Date: | 2020-11-05 | Program: | 16000000 | Planned: | 62.5% | No. of Persons: | 20 | On-going
Carmen | Tubod | 2nd Eng'g. Dist. | On-going | 2019-12-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | [7 empty] | Project Engineer: | Agang | Revised Completion Date: |  | Allotment: | 16000000 | Revised: |  | No. of Man-days: | 600
Carmen | Tubod | 2nd Eng'g. Dist. | On-going | 2019-12-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: | 4046971.2 | Actual: | 58.23%
Carmen | Tubod | 2nd Eng'g. Dist. | On-going | 2019-12-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | [7 empty] | Duration: | 323 | No. of days extended: |  |  |  | Slippage: | -4.27%
Carmen | Tubod | 2nd Eng'g. Dist. | On-going | 2019-12-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | [7 empty] | Date Allotment Released: | 2019-11-26 | Date completed:
Carmen | Tubod | 2nd Eng'g. Dist. | On-going | 2019-12-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | [7 empty] | Date Started: | 2019-12-18
Carmen | Tibulao | 2nd Eng'g. Dist. | On-going | 2019-11-11 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | ROAD ID 103 - Sitio Malaga - Tibulao |  | 20% DF CY 2019 | Road Rehabilitation | 3.22 | km | Admin | Project Cost: | 1000000 | Target Completion Date: | 2020-02-09 | Program: | 1000000 | Planned: | 78.5% | No. of Persons: | 5 | On-going
Carmen | Tibulao | 2nd Eng'g. Dist. | On-going | 2019-11-11 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | [7 empty] | Project Engineer: | Obar | Revised Completion Date: | 2020-06-30 | Allotment: | 1000000 | Revised: |  | No. of Man-days: | 110
Carmen | Tibulao | 2nd Eng'g. Dist. | On-going | 2019-11-11 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | [7 empty] | Implementor: | PEO | No. of days suspended: | 142 | Disbursement: |  | Actual: | 54.8%
Carmen | Tibulao | 2nd Eng'g. Dist. | On-going | 2019-11-11 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | [7 empty] | Duration: | 90 | No. of days extended: |  |  |  | Slippage: | -23.7%
Carmen | Tibulao | 2nd Eng'g. Dist. | On-going | 2019-11-11 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | [7 empty] | Date Allotment Released: | 2019-01-03 | Date completed:
Carmen | Tibulao | 2nd Eng'g. Dist. | On-going | 2019-11-11 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | [7 empty] | Date Started: | 2019-11-11
B.E. Dujali | Tanglaw | 2nd Eng'g. Dist. | On-going | 2019-12-28 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | ROAD ID 104 - Dujali - Tanglaw |  | 20% DF CY 2019 | Road Rehabilitation | 3.6 | km | Admin | Project Cost: | 2075000 | Target Completion Date: | 2020-04-16 | Program: | 2075000 | Planned: | 60% | No. of Persons: | 11 | On-going
B.E. Dujali | Tanglaw | 2nd Eng'g. Dist. | On-going | 2019-12-28 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | [7 empty] | Project Engineer: | Balbastro | Revised Completion Date: | 2020-08-30 | Allotment: | 2075000 | Revised: |  | No. of Man-days: | 77
B.E. Dujali | Tanglaw | 2nd Eng'g. Dist. | On-going | 2019-12-28 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | [7 empty] | Implementor: | PEO | No. of days suspended: | 28 | Disbursement: |  | Actual: | 65%
B.E. Dujali | Tanglaw | 2nd Eng'g. Dist. | On-going | 2019-12-28 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | [7 empty] | Duration: | 110 | No. of days extended: | 108 |  |  | Slippage: | 5%
B.E. Dujali | Tanglaw | 2nd Eng'g. Dist. | On-going | 2019-12-28 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | [7 empty] | Date Allotment Released: | 2019-01-03 | Date completed:
B.E. Dujali | Tanglaw | 2nd Eng'g. Dist. | On-going | 2019-12-28 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | [7 empty] | Date Started: | 2019-12-28
Sto. Tomas | Libertad | 2nd Eng'g. Dist. | On-going | 2019-06-17 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | ROAD ID 121 - San Miguel - Libertad |  | 20% DF CY 2019 | Road Rehabilitation | 6.2 | km | Admin | Project Cost: | 1240000 | Target Completion Date: | 2019-10-31 | Program: | 1240000 | Planned: | 59.41% | No. of Persons: | 9 | On-going
Sto. Tomas | Libertad | 2nd Eng'g. Dist. | On-going | 2019-06-17 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | [7 empty] | Project Engineer: | Gamad | Revised Completion Date: | 2020-02-29 | Allotment: | 1240000 | Revised: |  | No. of Man-days: | 36
Sto. Tomas | Libertad | 2nd Eng'g. Dist. | On-going | 2019-06-17 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | [7 empty] | Implementor: | PEO | No. of days suspended: | 86 | Disbursement: |  | Actual: | 59.41%
Sto. Tomas | Libertad | 2nd Eng'g. Dist. | On-going | 2019-06-17 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | [7 empty] | Duration: | 136 | No. of days extended: | 35 |  |  | Slippage: | 0%
Sto. Tomas | Libertad | 2nd Eng'g. Dist. | On-going | 2019-06-17 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | [7 empty] | Date Allotment Released: | 2019-01-03 | Date completed:
Sto. Tomas | Libertad | 2nd Eng'g. Dist. | On-going | 2019-06-17 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | [7 empty] | Date Started: | 2019-06-17
Sto. Tomas | Casig-ang | 2nd Eng'g. Dist. | On-going | 2019-06-27 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | ROAD ID 123 - Bacali - Casig-ang - Libertad |  | 20% DF CY 2019 | Road Rehabilitation | 4.7 | km | Admin | Project Cost: | 940000 | Target Completion Date: | 2019-09-15 | Program: | 940000 | Planned: | 62.1% | No. of Persons: | 9 | On-going
Sto. Tomas | Casig-ang | 2nd Eng'g. Dist. | On-going | 2019-06-27 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | [7 empty] | Project Engineer: | Gamad | Revised Completion Date: | 2020-02-29 | Allotment: | 940000 | Revised: |  | No. of Man-days: | 36
Sto. Tomas | Casig-ang | 2nd Eng'g. Dist. | On-going | 2019-06-27 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | [7 empty] | Implementor: | PEO | No. of days suspended: | 132 | Disbursement: |  | Actual: | 62%
Sto. Tomas | Casig-ang | 2nd Eng'g. Dist. | On-going | 2019-06-27 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | [7 empty] | Duration: | 80 | No. of days extended: | 35 |  |  | Slippage: | -0.1%
Sto. Tomas | Casig-ang | 2nd Eng'g. Dist. | On-going | 2019-06-27 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | [7 empty] | Date Allotment Released: | 2019-06-07 | Date completed:
Sto. Tomas | Casig-ang | 2nd Eng'g. Dist. | On-going | 2019-06-27 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | [7 empty] | Date Started: | 2019-06-27
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | On-going | 2019-06-17 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | ROAD ID 125 - San Miguel - Moslog - Kinamayan |  | 20% DF CY 2019 | Road Rehabilitation | 2.9 | km | Admin | Project Cost: | 1000000 | Target Completion Date: | 2019-09-16 | Program: | 1000000 | Planned: | 100% | No. of Persons: | 6 | On-going
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | On-going | 2019-06-17 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | [7 empty] | Project Engineer: | Gamad | Revised Completion Date: | 2020-02-29 | Allotment: | 1000000 | Revised: | 73.59% | No. of Man-days: | 30
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | On-going | 2019-06-17 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | [7 empty] | Implementor: | PEO | No. of days suspended: | 137 | Disbursement: |  | Actual: | 80%
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | On-going | 2019-06-17 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | [7 empty] | Duration: | 91 | No. of days extended: | 29 |  |  | Slippage: | 6.41%
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | On-going | 2019-06-17 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | [7 empty] | Date Allotment Released: | 2019-05-20 | Date completed:
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | On-going | 2019-06-17 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | [7 empty] | Date Started: | 2019-06-17
Sto. Tomas | Katipunana | 2nd Eng'g. Dist. | On-going | 2019-12-27 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | ROAD ID 134 - New Katipunan - Pantaron |  | 20% DF CY 2019 | Road Rehabilitation | 1.96 | km | Admin | Project Cost: | 395000 | Target Completion Date: | 2020-02-25 | Program: | 395000 | Planned: | 60% | No. of Persons: | 4 | On-going
Sto. Tomas | Katipunana | 2nd Eng'g. Dist. | On-going | 2019-12-27 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | [7 empty] | Project Engineer: | Gamad/Clar | Revised Completion Date: |  | Allotment: | 395000 | Revised: |  | No. of Man-days: | 24
Sto. Tomas | Katipunana | 2nd Eng'g. Dist. | On-going | 2019-12-27 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: | 60%
Sto. Tomas | Katipunana | 2nd Eng'g. Dist. | On-going | 2019-12-27 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | [7 empty] | Duration: | 60 | No. of days extended: |  |  |  | Slippage: | 0%
Sto. Tomas | Katipunana | 2nd Eng'g. Dist. | On-going | 2019-12-27 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | [7 empty] | Date Allotment Released: | 2019-01-03 | Date completed:
Sto. Tomas | Katipunana | 2nd Eng'g. Dist. | On-going | 2019-12-27 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | [7 empty] | Date Started: | 2019-12-27
B.E. Dujali | Tanglaw | 2nd Eng'g. Dist. | On-going | 2019-06-17 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | ROAD ID 142 - Jct. Highway - Tanglaw |  | 20% DF CY 2019 | Road Rehabilitation | 3.98 | km | Admin | Project Cost: | 1100000 | Target Completion Date: | 2019-09-16 | Program: | 1100000 | Planned: | 100% | No. of Persons: | 10 | On-going
B.E. Dujali | Tanglaw | 2nd Eng'g. Dist. | On-going | 2019-06-17 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | [7 empty] | Project Engineer: | Gamad/Clar | Revised Completion Date: | 2020-02-29 | Allotment: | 1100000 | Revised: | 73.59% | No. of Man-days: | 50
B.E. Dujali | Tanglaw | 2nd Eng'g. Dist. | On-going | 2019-06-17 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | [7 empty] | Implementor: | PEO | No. of days suspended: | 137 | Disbursement: |  | Actual: | 85%
B.E. Dujali | Tanglaw | 2nd Eng'g. Dist. | On-going | 2019-06-17 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | [7 empty] | Duration: | 91 | No. of days extended: | 29 |  |  | Slippage: | 11.41%
B.E. Dujali | Tanglaw | 2nd Eng'g. Dist. | On-going | 2019-06-17 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | [7 empty] | Date Allotment Released: | 2019-05-16 | Date completed:
B.E. Dujali | Tanglaw | 2nd Eng'g. Dist. | On-going | 2019-06-17 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | [7 empty] | Date Started: | 2019-06-17
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | On-going | 2019-12-27 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | ROAD ID 146 - Bdry. Tagum - Crossing Kinamayan Sto. Tomas |  | 20% DF CY 2019 | Road Rehabilitation | 0.75 | km | Admin | Project Cost: | 3700000 | Target Completion Date: | 2020-04-25 | Program: | 3700000 | Planned: | 100% | No. of Persons: | 15 | On-going
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | On-going | 2019-12-27 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | [7 empty] | Project Engineer: | Gamad/Clar | Revised Completion Date: | 2020-08-23 | Allotment: | 3700000 | Revised: | 15.43% | No. of Man-days: | 225
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | On-going | 2019-12-27 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | [7 empty] | Implementor: |  | No. of days suspended: | 20 | Disbursement: |  | Actual: | 16.37%
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | On-going | 2019-12-27 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | [7 empty] | Duration: | 120 | No. of days extended: | 100 |  |  | Slippage: | 0.94%
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | On-going | 2019-12-27 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | [7 empty] | Date Allotment Released: | 2019-01-03 | Date completed:
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | On-going | 2019-12-27 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | [7 empty] | Date Started: | 2019-12-27
Sto. Tomas | San Jose | 2nd Eng'g. Dist. | On-going | 2020-05-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | Fr. Rd. 3 - San Jose |  | 20% DF CY 2019 | Road Rehabilitation | 4.55 | km | Admin | Project Cost: | 800000 | Target Completion Date: | 2020-08-06 | Program: | 800000 | Planned: | 2.14% | No. of Persons: | 3 | On-going
Sto. Tomas | San Jose | 2nd Eng'g. Dist. | On-going | 2020-05-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Project Engineer: | Obar | Revised Completion Date: |  | Allotment: | 800000 | Revised: |  | No. of Man-days: | 30
Sto. Tomas | San Jose | 2nd Eng'g. Dist. | On-going | 2020-05-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: | 2.14%
Sto. Tomas | San Jose | 2nd Eng'g. Dist. | On-going | 2020-05-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Duration: | 80 | No. of days extended: |  |  |  | Slippage: | 0%
Sto. Tomas | San Jose | 2nd Eng'g. Dist. | On-going | 2020-05-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Date Allotment Released: | 2019-01-03 | Date completed:
Sto. Tomas | San Jose | 2nd Eng'g. Dist. | On-going | 2020-05-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Date Started: | 2020-05-18
Carmen | Asuncion | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | Lower Asuncion - Upper Asuncion |  | 20% DF CY 2019 | Road Rehabilitation | 1.02 | km | Admin | Project Cost: |  | Target Completion Date: |  | Program: | 0 | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
Carmen | Asuncion | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 0 | Revised: |  | No. of Man-days:
Carmen | Asuncion | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Carmen | Asuncion | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Carmen | Asuncion | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Date Allotment Released: |  | Date completed:
Carmen | Asuncion | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Date Started:
Carmen | Mangalcal | 2nd Eng'g. Dist. | On-going | 2020-06-15 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | Jct. Highway - Carmen - Mangalcal - Tubod |  | 20% DF CY 2019 | Road Rehabilitation | 11.34 | km | Admin | Project Cost: | 1323000 | Target Completion Date: | 2020-07-15 | Program: | 1323000 | Planned: | 100% | No. of Persons: | 3 | On-going
Carmen | Mangalcal | 2nd Eng'g. Dist. | On-going | 2020-06-15 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Project Engineer: | Obar | Revised Completion Date: |  | Allotment: | 1323000 | Revised: |  | No. of Man-days: | 30
Carmen | Mangalcal | 2nd Eng'g. Dist. | On-going | 2020-06-15 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: | 1.21%
Carmen | Mangalcal | 2nd Eng'g. Dist. | On-going | 2020-06-15 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Duration: | 30 | No. of days extended: |  |  |  | Slippage: | -98.79%
Carmen | Mangalcal | 2nd Eng'g. Dist. | On-going | 2020-06-15 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Date Allotment Released: | 2019-01-03 | Date completed:
Carmen | Mangalcal | 2nd Eng'g. Dist. | On-going | 2020-06-15 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Date Started: | 2020-06-15
B.E. Dujali | Tuganay-Taba | 2nd Eng'g. Dist. | On-going | 2020-05-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | Tuganay - Taba |  | 20% DF CY 2019 | Road Rehabilitation | 4.27 | km | Admin | Project Cost: | 507500 | Target Completion Date: | 2020-06-17 | Program: | 507500 | Planned: | 100% | No. of Persons: | 3 | On-going
B.E. Dujali | Tuganay-Taba | 2nd Eng'g. Dist. | On-going | 2020-05-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Project Engineer: | Obar | Revised Completion Date: |  | Allotment: | 507500 | Revised: |  | No. of Man-days: | 30
B.E. Dujali | Tuganay-Taba | 2nd Eng'g. Dist. | On-going | 2020-05-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: | 3.37%
B.E. Dujali | Tuganay-Taba | 2nd Eng'g. Dist. | On-going | 2020-05-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Duration: | 30 | No. of days extended: |  |  |  | Slippage: | -96.63%
B.E. Dujali | Tuganay-Taba | 2nd Eng'g. Dist. | On-going | 2020-05-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Date Allotment Released: | 2019-01-03 | Date completed:
B.E. Dujali | Tuganay-Taba | 2nd Eng'g. Dist. | On-going | 2020-05-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Date Started: | 2020-05-18
B.E. Dujali | Ising | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | Jct. Highway - Ising - Magsaysay |  | 20% DF CY 2019 | Road Rehabilitation | 10.84 | km | Admin | Project Cost: | 6000000 | Target Completion Date: |  | Program: | 6000000 | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
B.E. Dujali | Ising | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 6000000 | Revised: |  | No. of Man-days:
B.E. Dujali | Ising | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
B.E. Dujali | Ising | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
B.E. Dujali | Ising | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Date Allotment Released: |  | Date completed:
B.E. Dujali | Ising | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Date Started:
B.E. Dujali | Guadalupe | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | Jct. Highway - Guadalupe - Bdry. Tagum |  | 20% DF CY 2019 | Road Rehabilitation | 7.9 | km | Admin | Project Cost: | 910000 | Target Completion Date: | 2020-08-06 | Program: | 910000 | Planned: | 2.04% | No. of Persons: | 3 | On-going
B.E. Dujali | Guadalupe | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Project Engineer: | Obar | Revised Completion Date: |  | Allotment: | 910000 | Revised: |  | No. of Man-days: | 30
B.E. Dujali | Guadalupe | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: | 2.04%
B.E. Dujali | Guadalupe | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Duration: | 80 | No. of days extended: |  |  |  | Slippage: | 0%
B.E. Dujali | Guadalupe | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Date Allotment Released: | 2019-01-03 | Date completed:
B.E. Dujali | Guadalupe | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Date Started: | 2020-05-18
Carmen | Tibulao | 2nd Eng'g. Dist. | On-going | 2020-05-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | Sitio Malaga - Tibulao |  | 20% DF CY 2019 | Road Rehabilitation | 3.22 | km | Admin | Project Cost: | 300000 | Target Completion Date: | 2020-08-06 | Program: | 300000 | Planned: | 3.37% | No. of Persons: | 3 | On-going
Carmen | Tibulao | 2nd Eng'g. Dist. | On-going | 2020-05-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Project Engineer: | Obar | Revised Completion Date: |  | Allotment: | 300000 | Revised: |  | No. of Man-days: | 30
Carmen | Tibulao | 2nd Eng'g. Dist. | On-going | 2020-05-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: | 3.37%
Carmen | Tibulao | 2nd Eng'g. Dist. | On-going | 2020-05-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Duration: | 80 | No. of days extended: |  |  |  | Slippage:
Carmen | Tibulao | 2nd Eng'g. Dist. | On-going | 2020-05-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Date Allotment Released: | 2019-01-03 | Date completed:
Carmen | Tibulao | 2nd Eng'g. Dist. | On-going | 2020-05-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Date Started: | 2020-05-18
Carmen | New Casay | 2nd Eng'g. Dist. | On-going | 2020-05-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | Prk. 5 RJS - Prk 6 New Casay |  | 20% DF CY 2019 | Road Rehabilitation | 2.73 | km | Admin | Project Cost: | 350000 | Target Completion Date: | 2020-06-17 | Program: | 350000 | Planned: | 3.37% | No. of Persons: | 3 | On-going
Carmen | New Casay | 2nd Eng'g. Dist. | On-going | 2020-05-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Project Engineer: | Obar | Revised Completion Date: |  | Allotment: | 350000 | Revised: |  | No. of Man-days: | 30
Carmen | New Casay | 2nd Eng'g. Dist. | On-going | 2020-05-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: | 3.37%
Carmen | New Casay | 2nd Eng'g. Dist. | On-going | 2020-05-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Duration: | 30 | No. of days extended: |  |  |  | Slippage: | 0%
Carmen | New Casay | 2nd Eng'g. Dist. | On-going | 2020-05-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Date Allotment Released: | 2019-01-03 | Date completed:
Carmen | New Casay | 2nd Eng'g. Dist. | On-going | 2020-05-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Date Started: | 2020-05-18
B.E. Dujali | San Vicente | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | Dujali - Pawas - San Vicente |  | 20% DF CY 2019 | Road Rehabilitation | 4.42 | km | Admin | Project Cost: | 525000 | Target Completion Date: | 2020-07-02 | Program: | 525000 | Planned: | 2.41% | No. of Persons: | 3 | On-going
B.E. Dujali | San Vicente | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Project Engineer: | Obar | Revised Completion Date: |  | Allotment: | 525000 | Revised: |  | No. of Man-days: | 30
B.E. Dujali | San Vicente | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: | 2.41%
B.E. Dujali | San Vicente | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Duration: | 45 | No. of days extended: |  |  |  | Slippage: | 0%
B.E. Dujali | San Vicente | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Date Allotment Released: | 2019-01-03 | Date completed:
B.E. Dujali | San Vicente | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Date Started: | 2020-05-18
Sto. Tomas | Esperanza | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | Los Amigos 1 - Esperanza - Los Amigos 2 |  | 20% DF CY 2019 | Road Rehabilitation | 3.59 | km | Admin | Project Cost: | 19200000 | Target Completion Date: |  | Program: | 19200000 | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
Sto. Tomas | Esperanza | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 19200000 | Revised: |  | No. of Man-days:
Sto. Tomas | Esperanza | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Sto. Tomas | Esperanza | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Sto. Tomas | Esperanza | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Date Allotment Released: |  | Date completed:
Sto. Tomas | Esperanza | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Date Started:
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | On-going | 2020-05-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | San Miguel - Crossing Kinamayan |  | 20% DF CY 2019 | Road Rehabilitation | 2.8 | km | Admin | Project Cost: | 350000 | Target Completion Date: | 2020-07-17 | Program: | 350000 | Planned: | 22.58% | No. of Persons: | 6 | On-going
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | On-going | 2020-05-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Project Engineer: | Piad/ Obar | Revised Completion Date: |  | Allotment: | 350000 | Revised: |  | No. of Man-days: | 84
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | On-going | 2020-05-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: | 22.58%
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | On-going | 2020-05-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Duration: | 60 | No. of days extended: |  |  |  | Slippage: | 0%
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | On-going | 2020-05-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Date Allotment Released: | 2019-01-03 | Date completed:
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | On-going | 2020-05-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Date Started: | 2020-05-18
Sto. Tomas | Magwawa | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | Fd Rd 2 - Sto. Tomas - Magwawa |  | 20% DF CY 2019 | Road Rehabilitation | 10.21 | km | Admin | Project Cost: |  | Target Completion Date: |  | Program: | 0 | Planned: |  | No. of Persons: |  | Plan and POW Approved
Sto. Tomas | Magwawa | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 0 | Revised: |  | No. of Man-days:
Sto. Tomas | Magwawa | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Sto. Tomas | Magwawa | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Sto. Tomas | Magwawa | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Date Allotment Released: |  | Date completed:
Sto. Tomas | Magwawa | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Date Started:
Sto. Tomas | Tulalian | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | Menzi - Balagunan - Tulalian |  | 20% DF CY 2019 | Road Rehabilitation | 10.63 | km | Admin | Project Cost: | 3720500 | Target Completion Date: |  | Program: | 3720500 | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
Sto. Tomas | Tulalian | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 3720500 | Revised: |  | No. of Man-days:
Sto. Tomas | Tulalian | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Sto. Tomas | Tulalian | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Sto. Tomas | Tulalian | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Date Allotment Released: |  | Date completed:
Sto. Tomas | Tulalian | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Date Started:
Sto. Tomas | Talomo | 2nd Eng'g. Dist. | On-going | 2020-05-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | Jct. Bdry. Tagum - Talomo |  | 20% DF CY 2019 | Road Rehabilitation | 12.01 | km | Admin | Project Cost: | 1400000 | Target Completion Date: | 2020-09-15 | Program: | 1400000 | Planned: | 3% | No. of Persons: | 3 | On-going
Sto. Tomas | Talomo | 2nd Eng'g. Dist. | On-going | 2020-05-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Project Engineer: | Obar | Revised Completion Date: |  | Allotment: | 1400000 | Revised: |  | No. of Man-days: | 30
Sto. Tomas | Talomo | 2nd Eng'g. Dist. | On-going | 2020-05-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: | 3.37%
Sto. Tomas | Talomo | 2nd Eng'g. Dist. | On-going | 2020-05-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Duration: | 120 | No. of days extended: |  |  |  | Slippage: | 0.37%
Sto. Tomas | Talomo | 2nd Eng'g. Dist. | On-going | 2020-05-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Date Allotment Released: | 2019-01-23 | Date completed:
Sto. Tomas | Talomo | 2nd Eng'g. Dist. | On-going | 2020-05-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Date Started: | 2020-05-18
Carmen | Anibongan | 2nd Eng'g. Dist. | Completed | 2019-05-22 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | Rehab. of Anibongan-Salvacion-Cabay-angan Provincial Road with Drainage |  | 20% DF CY 2019 | Road Drainage rehabiliated |  | km | Admin | Project Cost: | 2000000 | Target Completion Date: | 2019-08-04 23:59 | Program: | 2000000 | Planned: | 100% | No. of Persons: | 1 | Completed as per physical accomplishment. Financial documents still on process.
Carmen | Anibongan | 2nd Eng'g. Dist. | Completed | 2019-05-22 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Project Engineer: | Toquero | Revised Completion Date: | 2019-12-31 23:59 | Allotment: | 2000000 | Revised: |  | No. of Man-days: | 4
Carmen | Anibongan | 2nd Eng'g. Dist. | Completed | 2019-05-22 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: | 100%
Carmen | Anibongan | 2nd Eng'g. Dist. | Completed | 2019-05-22 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Duration: | 75 | No. of days extended: | 149 |  |  | Slippage: | 0%
Carmen | Anibongan | 2nd Eng'g. Dist. | Completed | 2019-05-22 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Date Allotment Released: | 2019-01-14 | Date completed: | 2020-01-31
Carmen | Anibongan | 2nd Eng'g. Dist. | Completed | 2019-05-22 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Date Started: | 2019-05-22
B.E. Dujali | Dujali | 2nd Eng'g. Dist. | On-going | 2019-11-04 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various of Local Roads & Drainage Development Project (Provincewide) LS - 15,000,000.00 | Rehab. Of Dujali-Pawas-San Vicente Provincial Road |  | 20% DF CY 2019 | Road Drainage rehabiliated |  | km | Admin | Project Cost: | 2000000 | Target Completion Date: |  | Program: | 2000000 | Planned: | 80% | No. of Persons: |  | On-going
B.E. Dujali | Dujali | 2nd Eng'g. Dist. | On-going | 2019-11-04 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various of Local Roads & Drainage Development Project (Provincewide) LS - 15,000,000.00 | [7 empty] | Project Engineer: | Toquero | Revised Completion Date: |  | Allotment: | 2000000 | Revised: |  | No. of Man-days:
B.E. Dujali | Dujali | 2nd Eng'g. Dist. | On-going | 2019-11-04 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various of Local Roads & Drainage Development Project (Provincewide) LS - 15,000,000.00 | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: | 80%
B.E. Dujali | Dujali | 2nd Eng'g. Dist. | On-going | 2019-11-04 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various of Local Roads & Drainage Development Project (Provincewide) LS - 15,000,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
B.E. Dujali | Dujali | 2nd Eng'g. Dist. | On-going | 2019-11-04 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various of Local Roads & Drainage Development Project (Provincewide) LS - 15,000,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
B.E. Dujali | Dujali | 2nd Eng'g. Dist. | On-going | 2019-11-04 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various of Local Roads & Drainage Development Project (Provincewide) LS - 15,000,000.00 | [7 empty] | Date Started: | 2019-11-04
B.E. Dujali | Ising | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various of Local Roads & Drainage Development Project (Provincewide) LS - 15,000,000.00 | Rehab./Impv't. of Jct. highway Ising-Magsaysay Provincial Road with Drainage |  | 20% DF CY 2019 | Road Drainage rehabiliated |  | km | Admin | Project Cost: | 1500000 | Target Completion Date: |  | Program: | 1500000 | Planned: |  | No. of Persons: |  | Revised POW for approval - Jan. 7, 2020 Revision was made due to scarcity of boulders changing from stone masonry to concrete masonry
B.E. Dujali | Ising | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various of Local Roads & Drainage Development Project (Provincewide) LS - 15,000,000.00 | [7 empty] | Project Engineer: | Toquero | Revised Completion Date: |  | Allotment: | 1500000 | Revised: |  | No. of Man-days:
B.E. Dujali | Ising | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various of Local Roads & Drainage Development Project (Provincewide) LS - 15,000,000.00 | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual:
B.E. Dujali | Ising | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various of Local Roads & Drainage Development Project (Provincewide) LS - 15,000,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
B.E. Dujali | Ising | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various of Local Roads & Drainage Development Project (Provincewide) LS - 15,000,000.00 | [7 empty] | Date Allotment Released: | 2019-01-16 | Date completed:
B.E. Dujali | Ising | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various of Local Roads & Drainage Development Project (Provincewide) LS - 15,000,000.00 | [7 empty] | Date Started:
Panabo City | Consolacion | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | Impv't. of Potable Water System, Consolacion, Panabo City |  | 20% DF CY 2019 | Water System |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
Panabo City | Consolacion | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Panabo City | Consolacion | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Panabo City | Consolacion | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Panabo City | Consolacion | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | [7 empty] | Date Allotment Released: | 2019-06-28 | Date completed:
Panabo City | Consolacion | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | [7 empty] | Date Started:
Samal | Tagbitan-ag | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | Impv't. of Potable Water System, Tagbitan-ag, Samal Dist. |  | 20% DF CY 2019 | Water System |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | For implementation
Samal | Tagbitan-ag | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Samal | Tagbitan-ag | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Samal | Tagbitan-ag | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Samal | Tagbitan-ag | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | [7 empty] | Date Allotment Released: | 2019-06-19 | Date completed:
Samal | Tagbitan-ag | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | [7 empty] | Date Started:
Babak | San Antonio | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | Impv't. of Potable Water System, San Antonio, babak, IGCS |  | 20% DF CY 2019 | Water System |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
Babak | San Antonio | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Babak | San Antonio | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Babak | San Antonio | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Babak | San Antonio | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | [7 empty] | Date Allotment Released: | 2019-06-25 | Date completed:
Babak | San Antonio | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | [7 empty] | Date Started:
IGCS | Mambago | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | Impv't. of Potable Water System, Mambago-A, IGCS |  | 20% DF CY 2019 | Water System |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | For Implementation
IGCS | Mambago | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
IGCS | Mambago | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
IGCS | Mambago | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
IGCS | Mambago | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | [7 empty] | Date Allotment Released: | 2019-09-10 | Date completed:
IGCS | Mambago | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | [7 empty] | Date Started:
Panabo City | Buenavista | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | Construction of PWS, Brgy. Buenavista, Panabo City |  | 20% DF CY 2019 | Water System |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | For implementation
Panabo City | Buenavista | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Panabo City | Buenavista | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Panabo City | Buenavista | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Panabo City | Buenavista | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | [7 empty] | Date Allotment Released: | June 19 ,2019 | Date completed:
Panabo City | Buenavista | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | [7 empty] | Date Started:
Panabo City | Kiotoy | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | Construction of PWS, Brgy. Brgy. Kiotoy, Panabo City |  | 20% DF CY 2019 | Water System |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
Panabo City | Kiotoy | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Panabo City | Kiotoy | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Panabo City | Kiotoy | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Panabo City | Kiotoy | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Panabo City | Kiotoy | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | [7 empty] | Date Started:
IGCS | Linusotan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | Construction of PWS, Brgy. Linusotan, Talikud, District, IGCS |  | 20% DF CY 2019 | Water System |  |  |  | Project Cost: | 1300000 | Target Completion Date: |  | Program: | 1300000 | Planned: |  | No. of Persons: |  | Procurement on process
IGCS | Linusotan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 1300000 | Revised: |  | No. of Man-days:
IGCS | Linusotan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
IGCS | Linusotan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
IGCS | Linusotan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | [7 empty] | Date Allotment Released: | 2019-10-23 | Date completed:
IGCS | Linusotan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | [7 empty] | Date Started:
Babak, IGCS | San Miguel | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | Rehab. of PWS, Brgy. San Miguel, Babak, IGCS |  | 20% DF CY 2019 | Water System |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
Babak, IGCS | San Miguel | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Babak, IGCS | San Miguel | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Babak, IGCS | San Miguel | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Babak, IGCS | San Miguel | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Babak, IGCS | San Miguel | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | [7 empty] | Date Started:
Panabo City | Cacao | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | Construction of PWS, Brgy. Cacao, Panabo City |  | 20% DF CY 2019 | Water System |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | For cancellation. Purchase of Geo-resistivity equipment but procurement still on process
Panabo City | Cacao | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Panabo City | Cacao | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Panabo City | Cacao | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Panabo City | Cacao | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Panabo City | Cacao | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | [7 empty] | Date Started:
Kaputian, IGCS | Pangubatan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | Rehabilitation of Potable Water System, Brgy. Pangubatan, kaputian Dist. IGCS |  | 20% DF CY 2019 | Water System |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | For implementation
Kaputian, IGCS | Pangubatan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Kaputian, IGCS | Pangubatan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Kaputian, IGCS | Pangubatan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Kaputian, IGCS | Pangubatan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Kaputian, IGCS | Pangubatan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | [7 empty] | Date Started:
Carmen | Ising | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Government Buildings and Facilities Development Project (Provincewide) LS - P 27,000,000.00 | Const. of DDN Hospital Carmen Zone Annex Bldg. Phase 2, |  | 20% DF CY 2019 | Building |  | sq.m | Contract | Project Cost: | 3620000 | Target Completion Date: |  | Program: | 3620000 | Planned: |  | No. of Persons: |  | For implementation (Winning Bidder - Digos Constrak Corp.)
Carmen | Ising | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Government Buildings and Facilities Development Project (Provincewide) LS - P 27,000,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 3620000 | Revised: |  | No. of Man-days:
Carmen | Ising | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Government Buildings and Facilities Development Project (Provincewide) LS - P 27,000,000.00 | [7 empty] | Implementor: | Digos Constrak Corp/ | No. of days suspended: |  | Disbursement: |  | Actual:
Carmen | Ising | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Government Buildings and Facilities Development Project (Provincewide) LS - P 27,000,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Carmen | Ising | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Government Buildings and Facilities Development Project (Provincewide) LS - P 27,000,000.00 | [7 empty] | Date Allotment Released: | 2019-06-28 | Date completed:
Carmen | Ising | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | [7 empty] | Date Started:
Carmen | La Paz | 2nd Eng'g. Dist. | On-going | 2019-08-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | Const. of Multi-Purpose Hall, La Paz, Carmen |  | 20% DF CY 2019 (STIMULUS | Building |  | sq.m | MLGU | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Fund transferred to LGU March 28, 2019
Carmen | La Paz | 2nd Eng'g. Dist. | On-going | 2019-08-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Carmen | La Paz | 2nd Eng'g. Dist. | On-going | 2019-08-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Carmen | La Paz | 2nd Eng'g. Dist. | On-going | 2019-08-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Carmen | La Paz | 2nd Eng'g. Dist. | On-going | 2019-08-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Allotment Released: | 2019-02-20 | Date completed:
Carmen | La Paz | 2nd Eng'g. Dist. | On-going | 2019-08-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Started: | 2019-08-16
Carmen | Sto. Niño | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | Const. of Evacuation Center Ph. 3, Sto. Niño, Carmen |  | 20% DF CY 2019 (STIMULUS | Building |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Amended in the AIP 3rd revision CY 2019/ SB No. 4 CY 2019 changing the location to Purok !-c, Sto. Nino since the previous location was implemented by DPWH
Carmen | Sto. Niño | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Carmen | Sto. Niño | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Carmen | Sto. Niño | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Carmen | Sto. Niño | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Carmen | Sto. Niño | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Started:
Carmen | Mangalcal | 2nd Eng'g. Dist. | On-going | 2019-09-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | Const. of Multi-Purpose Hall, Mangalcal, Carmen |  | 20% DF CY 2019 (STIMULUS | Building |  | sq.m | MLGU | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Fund transfer to LGU Carmen, 3/28/2019 with check no. 2574953 and OR no. 0118982
Carmen | Mangalcal | 2nd Eng'g. Dist. | On-going | 2019-09-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Carmen | Mangalcal | 2nd Eng'g. Dist. | On-going | 2019-09-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Carmen | Mangalcal | 2nd Eng'g. Dist. | On-going | 2019-09-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Carmen | Mangalcal | 2nd Eng'g. Dist. | On-going | 2019-09-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Allotment Released: | 2019-02-20 | Date completed:
Carmen | Mangalcal | 2nd Eng'g. Dist. | On-going | 2019-09-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Started: | 2019-09-16
Carmen | Guadalupe | 2nd Eng'g. Dist. | On-going | 2019-08-15 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | Rehab. of Multi-Purpose Hall, Guadalupe, Carmen |  | 20% DF CY 2019 (STIMULUS | Building |  |  | MLGU | Project Cost: | 500000 | Target Completion Date: | 2019-11-13 23:59 | Program: | 500000 | Planned: |  | No. of Persons: |  | Fund transferred to LGU March 28, 2019
Carmen | Guadalupe | 2nd Eng'g. Dist. | On-going | 2019-08-15 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Carmen | Guadalupe | 2nd Eng'g. Dist. | On-going | 2019-08-15 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Carmen | Guadalupe | 2nd Eng'g. Dist. | On-going | 2019-08-15 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Duration: | 91 | No. of days extended: |  |  |  | Slippage: | 0%
Carmen | Guadalupe | 2nd Eng'g. Dist. | On-going | 2019-08-15 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Allotment Released: | 2019-02-20 | Date completed:
Carmen | Guadalupe | 2nd Eng'g. Dist. | On-going | 2019-08-15 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Started: | 2019-08-15
Carmen | Mabuhay | 2nd Eng'g. Dist. | On-going | 2019-08-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | Const. of Multi-Purpose Hall, Mabuhay, Carmen |  | 20% DF CY 2019 (STIMULUS | Building |  | sq.m | MLGU | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Fund transfer to LGU Carmen, 3/28/2019 with check no. 2574925 and OR no. 0118984
Carmen | Mabuhay | 2nd Eng'g. Dist. | On-going | 2019-08-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Carmen | Mabuhay | 2nd Eng'g. Dist. | On-going | 2019-08-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Carmen | Mabuhay | 2nd Eng'g. Dist. | On-going | 2019-08-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Carmen | Mabuhay | 2nd Eng'g. Dist. | On-going | 2019-08-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Allotment Released: | 2019-02-20 | Date completed:
Carmen | Mabuhay | 2nd Eng'g. Dist. | On-going | 2019-08-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Started: | 2019-08-16
Carmen | Mabaus | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | Const. Canal Lining , Mabaus, Carmen |  | 20% DF CY 2019 (STIMULUS | Canal lining |  |  | MLGU | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Fund transferred to LGU March 28, 2019
Carmen | Mabaus | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Carmen | Mabaus | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Carmen | Mabaus | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Carmen | Mabaus | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Allotment Released: | 2019-02-20 | Date completed:
Carmen | Mabaus | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Started:
Carmen | Alejal | 2nd Eng'g. Dist. | On-going | 2019-08-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | Rehab. Of Evacuation Center, Alejal, Carmen |  | 20% DF CY 2019 (STIMULUS | Building |  | sq.m | MLGU | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Fund transfer to LGU Carmen, 3/28/2019 with check no.2574949 and OR no. 0118991
Carmen | Alejal | 2nd Eng'g. Dist. | On-going | 2019-08-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Carmen | Alejal | 2nd Eng'g. Dist. | On-going | 2019-08-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Carmen | Alejal | 2nd Eng'g. Dist. | On-going | 2019-08-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Carmen | Alejal | 2nd Eng'g. Dist. | On-going | 2019-08-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Allotment Released: | 2019-02-20 | Date completed:
Carmen | Alejal | 2nd Eng'g. Dist. | On-going | 2019-08-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Started: | 2019-08-16
Carmen | Tuganay | 2nd Eng'g. Dist. | On-going | 2019-08-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | Compl. Of Evacuation Center, Tuganay, Carmen |  | 20% DF CY 2019 (STIMULUS | Building |  | sq.m | MLGU | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Fund transfer to LGU Carmen, 3/28/2019 with check no. 2574947 and OR no. 0118995
Carmen | Tuganay | 2nd Eng'g. Dist. | On-going | 2019-08-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Carmen | Tuganay | 2nd Eng'g. Dist. | On-going | 2019-08-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Carmen | Tuganay | 2nd Eng'g. Dist. | On-going | 2019-08-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Carmen | Tuganay | 2nd Eng'g. Dist. | On-going | 2019-08-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Allotment Released: | 2019-02-20 | Date completed:
Carmen | Tuganay | 2nd Eng'g. Dist. | On-going | 2019-08-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Started: | 2019-08-16
Carmen | Ising | 2nd Eng'g. Dist. | On-going | 2019-08-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | Const. of Multi-Purpose hall, Ising, Carmen |  | 20% DF CY 2019 (STIMULUS | Building |  |  | MLGU | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Fund transferred to LGU March 28, 2019
Carmen | Ising | 2nd Eng'g. Dist. | On-going | 2019-08-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Carmen | Ising | 2nd Eng'g. Dist. | On-going | 2019-08-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Carmen | Ising | 2nd Eng'g. Dist. | On-going | 2019-08-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Carmen | Ising | 2nd Eng'g. Dist. | On-going | 2019-08-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Allotment Released: | 2019-02-20 | Date completed:
Carmen | Ising | 2nd Eng'g. Dist. | On-going | 2019-08-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Started:
Carmen | Cebulano | 2nd Eng'g. Dist. | On-going | 2019-08-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | Rehab. of Multi-Purpose hall, Cebulano, Carmen |  | 20% DF CY 2019 (STIMULUS | Building |  | sq.m | MLGU | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Fund transferred to LGU March 28, 2019
Carmen | Cebulano | 2nd Eng'g. Dist. | On-going | 2019-08-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Carmen | Cebulano | 2nd Eng'g. Dist. | On-going | 2019-08-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Carmen | Cebulano | 2nd Eng'g. Dist. | On-going | 2019-08-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Carmen | Cebulano | 2nd Eng'g. Dist. | On-going | 2019-08-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Allotment Released: | 2019-02-20 | Date completed:
Carmen | Cebulano | 2nd Eng'g. Dist. | On-going | 2019-08-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Started: | 2019-08-16
Panabo City | Kasilak | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | Rehab. Of Multi-Purpose Hall, Kasilak, Panabo City |  | 20% DF CY 2019 (STIMULUS | Building |  |  | Contract | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | PO #2020041509 - JJR CONSTRUCTION AND SUPPLY
Panabo City | Kasilak | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Panabo City | Kasilak | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Panabo City | Kasilak | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Panabo City | Kasilak | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Panabo City | Kasilak | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Started:
Panabo City | New Malitbog | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | Rehab. Of Multi-Purpose Hall, New Malitbog, Panabo City |  | 20% DF CY 2019 (STIMULUS | Building |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Amended in AIP 3rd revsion CY 2019 to change the project to Construction of Potable Water System because the original project will be funded by LGU, Panabo City (Brgy. resolution no. 25 series of 2019 dated Aug. 13, 2019 submitted)
Panabo City | New Malitbog | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Panabo City | New Malitbog | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Panabo City | New Malitbog | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Panabo City | New Malitbog | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Panabo City | New Malitbog | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Started:
Panabo City | New Pandan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | Desilting of Canal, New Pandan, Panabo City |  | 20% DF CY 2019 (STIMULUS | Desiltation |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
Panabo City | New Pandan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Panabo City | New Pandan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Panabo City | New Pandan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Panabo City | New Pandan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Panabo City | New Pandan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Started:
Panabo City | Waterfall | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | Const. Of Multi-Purpose Hall, Waterfall, Panabo City |  | 20% DF CY 2019 (STIMULUS | Building |  |  | Contract | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Abstract #0520201797
Panabo City | Waterfall | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Panabo City | Waterfall | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Panabo City | Waterfall | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Panabo City | Waterfall | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Panabo City | Waterfall | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Started:
Panabo City | Cagangohan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | Concreting of Brgy. Road @ Prk. Guyabano, Cagangohan, Panabo City |  | 20% DF CY 2019 (STIMULUS | Concreting |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Amended in AIP 3rd revision to change the project to Rehab of Evacuation Center because the original project has no deed of donation.(Brgy. resolution no 41 series of 2019 dated Aug. 16, 2019 submitted
Panabo City | Cagangohan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Panabo City | Cagangohan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Panabo City | Cagangohan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Panabo City | Cagangohan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Panabo City | Cagangohan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Started:
Panabo City | J.P Laurel | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | Rehab. Of Evacuation Center, J.P. Laurel, Panabo City |  | 20% DF CY 2019 (STIMULUS | Building |  |  | Contract | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Purchase Order # 2020031248- DIGOS CONSTRAK
Panabo City | J.P Laurel | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Panabo City | J.P Laurel | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Panabo City | J.P Laurel | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Panabo City | J.P Laurel | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Allotment Released: | 2019-10-23 | Date completed:
Panabo City | J.P Laurel | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Started:
Panabo City | Buenavista | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | Const. Of Multi-Purpose Hall, Buenavista, Panabo City |  | 20% DF CY 2019 (STIMULUS | Building |  |  | Contract | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Purchase Order # 2020031248- DIGOS CONSTRAK
Panabo City | Buenavista | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Panabo City | Buenavista | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Panabo City | Buenavista | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Panabo City | Buenavista | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Allotment Released: | 2019-10-18 | Date completed:
Panabo City | Buenavista | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Started:
Panabo City | San Francisco | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | Rehab. Of Multi-Purpose Hall, San Francisco, Panabo City |  | 20% DF CY 2019 (STIMULUS | Building |  |  | Contract | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Purchase Order # 2020031248- DIGOS CONSTRAK
Panabo City | San Francisco | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Panabo City | San Francisco | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Panabo City | San Francisco | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Panabo City | San Francisco | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Allotment Released: | 2019-10-18 | Date completed:
Panabo City | San Francisco | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Started:
Panabo City | Datu Abdul | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | Rehab. Of Evacuation Center, Datu Abdul Dadia, Panabo City |  | 20% DF CY 2019 (STIMULUS | Building |  |  | Contract | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Purchase Order # 2020031248- DIGOS CONSTRAK
Panabo City | Datu Abdul | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Panabo City | Datu Abdul | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Panabo City | Datu Abdul | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Panabo City | Datu Abdul | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Allotment Released: | 2019-10-18 | Date completed:
Panabo City | Datu Abdul | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Started:
Panabo City | Quezon | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | Impv't./Beautification of Brgy. Grounds, Quezon, Panabo City |  | 20% DF CY 2019 (STIMULUS | Ground dev't. |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Re aligned to other stimulus projects that needs additional funding
Panabo City | Quezon | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Panabo City | Quezon | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Panabo City | Quezon | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Panabo City | Quezon | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Panabo City | Quezon | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Started:
Panabo City | Gredu | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | Const. of Women Livelihood Center Bldg. , Gredu, Panabo City |  | 20% DF CY 2019 (STIMULUS | Building |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Fund transfer to LGU - 3/28/2019 with check no. 2574926 and OR no. 0166517 - March 28, 2019
Panabo City | Gredu | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Panabo City | Gredu | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Panabo City | Gredu | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Panabo City | Gredu | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Allotment Released: | 2019-03-28 | Date completed:
Panabo City | Gredu | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Started:
Panabo City | Salvacion | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | Const. of Canal Lining at Purok 5, Salvacion, Panabo City |  | 20% DF CY 2019 (STIMULUS | Building |  |  | Contract | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | PO #2020041516- DANIMERH CONSTRUCTION & SUPPLY
Panabo City | Salvacion | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Panabo City | Salvacion | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Panabo City | Salvacion | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Panabo City | Salvacion | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Allotment Released: | 2019-10-18 | Date completed:
Panabo City | Salvacion | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Started:
Panabo City | New Visayas | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | Rehab. Of Health Center, New Visayas, Panabo City |  | 20% DF CY 2019 (STIMULUS | Building |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Re aligned to other stimulus projects that needs additional funding
Panabo City | New Visayas | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Panabo City | New Visayas | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Panabo City | New Visayas | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Panabo City | New Visayas | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Panabo City | New Visayas | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Started:
Panabo City | Little Panay | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | Rehab. Of Multi-Purpose Hall, Little Panay, Panabo City |  | 20% DF CY 2019 (STIMULUS | Building |  |  | Contract | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Abstract #0520201796
Panabo City | Little Panay | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Panabo City | Little Panay | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Panabo City | Little Panay | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Panabo City | Little Panay | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Panabo City | Little Panay | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Started:
Panabo City | Dalisay | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | Rehab. Of Brgy. Health Center, Dalisay, Panabo City |  | 20% DF CY 2019 (STIMULUS | Building |  |  | Contract | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Abstract #0520201798
Panabo City | Dalisay | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Panabo City | Dalisay | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Panabo City | Dalisay | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Panabo City | Dalisay | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Panabo City | Dalisay | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Started:
Panabo City | Southern Davao | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | Const. of Multi-Purpose Hall, Southern Davao, Panabo City |  | 20% DF CY 2019 (STIMULUS | Building |  |  | Contract | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Abstract #0520201798
Panabo City | Southern Davao | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Panabo City | Southern Davao | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Panabo City | Southern Davao | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Panabo City | Southern Davao | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Panabo City | Southern Davao | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Started:
Sto. Tomas | Casig-ang | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | Rehab. Of Evacuation Center, Casig-ang, Sto. Tomas |  | 20% DF CY 2019 (STIMULUS | Building |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | PR #20063670
Sto. Tomas | Casig-ang | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Sto. Tomas | Casig-ang | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Sto. Tomas | Casig-ang | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Sto. Tomas | Casig-ang | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Sto. Tomas | Casig-ang | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Started:
Sto. Tomas | Tibal-og | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | Const. of Brgy. Tibal-og Health Center, Tibal-og, Sto. Tomas |  | 20% DF CY 2019 (STIMULUS | Building |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | POW preparation completed amounting t oP1,550,000.00. To request for additional funds in order to complete the project to be functional
Sto. Tomas | Tibal-og | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Sto. Tomas | Tibal-og | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Sto. Tomas | Tibal-og | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Sto. Tomas | Tibal-og | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Sto. Tomas | Tibal-og | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Started:
Sto. Tomas | La Libertad | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | Compl.of Brgy. Public Market, La Libertad, Sto. Tomas |  | 20% DF CY 2019 (STIMULUS | Building |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Fund transfer to LGU - 6/26/219 with check no. 2575131 and OR no. 0557457 Completed/ PCR for submission by LGU
Sto. Tomas | La Libertad | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Sto. Tomas | La Libertad | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Sto. Tomas | La Libertad | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Sto. Tomas | La Libertad | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Sto. Tomas | La Libertad | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Started:
Sto. Tomas | New Visayas | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | Rehab. Of Evacuation Center, New Visayas, Sto. Tomas |  | 20% DF CY 2019 (STIMULUS | Building |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Fund transfer to LGU - 6/26/219 with check no. 2575132 and OR no. 0557455 For implementation
Sto. Tomas | New Visayas | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Sto. Tomas | New Visayas | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Sto. Tomas | New Visayas | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Sto. Tomas | New Visayas | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Sto. Tomas | New Visayas | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Started:
Sto. Tomas | San Vicente | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | Rehab. Of Multi-Purpose Hall, San Vicente, Sto. Tomas |  | 20% DF CY 2019 (STIMULUS | Building |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Fund transferred to LGU July 5, 2019
Sto. Tomas | San Vicente | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Project Engineer: | 0 | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Sto. Tomas | San Vicente | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Sto. Tomas | San Vicente | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Sto. Tomas | San Vicente | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Sto. Tomas | San Vicente | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Started:
Sto. Tomas | Salvacion | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | Rehab. Of Multi-Purpose Hall, Salvacion, Sto. Tomas |  | 20% DF CY 2019 (STIMULUS | Building |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
Sto. Tomas | Salvacion | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Sto. Tomas | Salvacion | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Sto. Tomas | Salvacion | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Sto. Tomas | Salvacion | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Sto. Tomas | Salvacion | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Started:
Sto. Tomas | Pantaron | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | Rehab. Of Multi-Purpose Hall, Pantaron, Sto. Tomas |  | 20% DF CY 2019 (STIMULUS | Building |  |  |  | Project Cost: |  | Target Completion Date: |  | Program: | 0 | Planned: |  | No. of Persons: |  | Amended in AIP 3rd revision CY 2019 / SB No. 4 CY 2019 increasing the project cost to P550,000.00
Sto. Tomas | Pantaron | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 0 | Revised: |  | No. of Man-days:
Sto. Tomas | Pantaron | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Sto. Tomas | Pantaron | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Sto. Tomas | Pantaron | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Sto. Tomas | Pantaron | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Started:
Sto. Tomas | Magwawa | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | Rehab. Of Multi-Purpose Hall, Magwawa, Sto. Tomas |  | 20% DF CY 2019 (STIMULUS | Building |  |  | Contract | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | For implementation - Awarded to JJR CONSTRUCTION AND SUPPLY
Sto. Tomas | Magwawa | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Sto. Tomas | Magwawa | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Sto. Tomas | Magwawa | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Sto. Tomas | Magwawa | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Allotment Released: | June 19 2019 | Date completed:
Sto. Tomas | Magwawa | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Started:
Sto. Tomas | San Jose | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | Compl. Of Multi-Purpose Hall, San Jose, Sto. Tomas |  | 20% DF CY 2019 (STIMULUS | Building |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Amended in AIP 3rd revision CY 2019 / SB No. 4 CY 2019 increasing the project cost to P600,000.00
Sto. Tomas | San Jose | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Sto. Tomas | San Jose | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Sto. Tomas | San Jose | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Sto. Tomas | San Jose | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Sto. Tomas | San Jose | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Started:
Sto. Tomas | Bobongon | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | Const. of Evacuation Center, Bobongon, Sto. Tomas |  | 20% DF CY 2019 (STIMULUS | Building |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Re aligned to other stimulus projects that needs additional funding
Sto. Tomas | Bobongon | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Sto. Tomas | Bobongon | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Sto. Tomas | Bobongon | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Sto. Tomas | Bobongon | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Sto. Tomas | Bobongon | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Started:
Sto. Tomas | Lunga-og | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | Rehab. Of Brgy. Road, Lunga-og, Sto. Tomas |  | 20% DF CY 2019 (STIMULUS | Building |  |  |  | Project Cost: |  | Target Completion Date: |  | Program: | 0 | Planned: |  | No. of Persons: |  | Amended in AIP 3rd revision CY 2019 / SB No. 4 CY 2019 increasing the project cost to P600,000.00
Sto. Tomas | Lunga-og | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 0 | Revised: |  | No. of Man-days:
Sto. Tomas | Lunga-og | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Sto. Tomas | Lunga-og | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Sto. Tomas | Lunga-og | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Sto. Tomas | Lunga-og | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Started:
Sto. Tomas | New Katipunan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | Rehab. Of Multi-Purpose Hall, New Katipunan, Sto. Tomas |  | 20% DF CY 2019 (STIMULUS | Building |  |  | Contract | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Abstract #0520201798 - Digos Constrak
Sto. Tomas | New Katipunan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Sto. Tomas | New Katipunan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Sto. Tomas | New Katipunan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Sto. Tomas | New Katipunan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Allotment Released: | 2019-06-07 | Date completed:
Sto. Tomas | New Katipunan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Started:
Sto. Tomas | San Miguel | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | Rehab. Of Multi-Purpose Hall, San Miguel, Sto. Tomas |  | 20% DF CY 2019 (STIMULUS | Building |  |  | Contract | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | PO #2020041509 - JJR CONSTRUCTION AND SUPPLY
Sto. Tomas | San Miguel | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Sto. Tomas | San Miguel | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Sto. Tomas | San Miguel | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Sto. Tomas | San Miguel | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Allotment Released: | 2019-06-07 | Date completed:
Sto. Tomas | San Miguel | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Started:
Sto. Tomas | Talomo | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | Rehab. Of Multi-Purpose Hall, Talomo, Sto. Tomas |  | 20% DF CY 2019 (STIMULUS | Building |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Fund transfer to LGU - 6/26/2019 with check no. 2575130 and OR no. 0557456 For implementation
Sto. Tomas | Talomo | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Sto. Tomas | Talomo | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Sto. Tomas | Talomo | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Sto. Tomas | Talomo | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Sto. Tomas | Talomo | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Started:
IGCS | Catagman | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | Concreting of Brgy. Road From Prk. 3 to Prk. 5, Catagman, IGCS |  | 20% DF CY 2019 (STIMULUS | Concreting |  |  | Contract | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | For implementation
IGCS | Catagman | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
IGCS | Catagman | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
IGCS | Catagman | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
IGCS | Catagman | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Allotment Released: | 2019-01-14 | Date completed:
IGCS | Catagman | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Started:
IGCS | Bandera | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | Electrification at Sitio Trinidad, Bandera, IGCS |  | 20% DF CY 2019 (STIMULUS | Electrification |  |  | Contract | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | PO #2020072352 - (3E Electrical Sales & Services)
IGCS | Bandera | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
IGCS | Bandera | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
IGCS | Bandera | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
IGCS | Bandera | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Allotment Released: | 2019-03-25 | Date completed:
IGCS | Bandera | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Started:
IGCS | Del Monte | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | Rehab. Of Multi-Purpose Hall, Del Monte, IGCS |  | 20% DF CY 2019 (STIMULUS | Building |  |  | Admin | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Pending/ activity undertaken by DPWH
IGCS | Del Monte | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
IGCS | Del Monte | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
IGCS | Del Monte | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
IGCS | Del Monte | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Allotment Released: | 2019-05-29 | Date completed:
IGCS | Del Monte | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Started:
IGCS | Tagbaobo | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | Electrification at Upper Purok Rosal, Tagbaobo, IGCS |  | 20% DF CY 2019 (STIMULUS | Electrification |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Purchase Order # 2020010002 (3E Electrical Sales & Services)
IGCS | Tagbaobo | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
IGCS | Tagbaobo | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
IGCS | Tagbaobo | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
IGCS | Tagbaobo | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
IGCS | Tagbaobo | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Started:
IGCS | Mambago-B | 2nd Eng'g. Dist. | On-going | 2019-10-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | Const. Of Multi-Purpose Hall, Mambago-B, IGCS |  | 20% DF CY 2019 (STIMULUS | Building |  | sq.m | Admin | Project Cost: | 500000 | Target Completion Date: | 2019-12-27 | Program: | 500000 | Planned: | 100% | No. of Persons: | 5 | On-going
IGCS | Mambago-B | 2nd Eng'g. Dist. | On-going | 2019-10-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Project Engineer: | Roque | Revised Completion Date: | 2020-03-29 | Allotment: | 500000 | Revised: | 99.48% | No. of Man-days: | 22
IGCS | Mambago-B | 2nd Eng'g. Dist. | On-going | 2019-10-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Implementor: | PEO | No. of days suspended: | 29 | Disbursement: |  | Actual: | 97.59%
IGCS | Mambago-B | 2nd Eng'g. Dist. | On-going | 2019-10-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Duration: | 70 | No. of days extended: | 64 |  |  | Slippage: | -1.89%
IGCS | Mambago-B | 2nd Eng'g. Dist. | On-going | 2019-10-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
IGCS | Mambago-B | 2nd Eng'g. Dist. | On-going | 2019-10-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Started: | 2019-10-18
IGCS | San Antonio | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | Const. Of Multi-Purpose Hall, San Antonio, IGCS |  | 20% DF CY 2019 (STIMULUS | Building |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | For implementation
IGCS | San Antonio | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
IGCS | San Antonio | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
IGCS | San Antonio | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
IGCS | San Antonio | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Allotment Released: | 2019-06-19 | Date completed:
IGCS | San Antonio | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Started:
IGCS | Pangubatan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | Rehab. Of Water System Intake Box and Pipeline, Pangubatan, IGCS |  | 20% DF CY 2019 (STIMULUS | Water System |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Plan and Pow completed. Waiting of deed of donation
IGCS | Pangubatan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
IGCS | Pangubatan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
IGCS | Pangubatan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
IGCS | Pangubatan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
IGCS | Pangubatan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Started:
IGCS | Cogon | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | Const. Of Multi-Purpose Hall, Cogon (Talicud), IGCS |  | 20% DF CY 2019 (STIMULUS | Building |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | For implementation
IGCS | Cogon | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
IGCS | Cogon | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
IGCS | Cogon | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
IGCS | Cogon | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
IGCS | Cogon | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Started:
IGCS | Libertad | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | Installation of Pipelines, Libertad, IGCS |  | 20% DF CY 2019 (STIMULUS | Pipelines |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | For implementation
IGCS | Libertad | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
IGCS | Libertad | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
IGCS | Libertad | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
IGCS | Libertad | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Allotment Released: | 2019-03-25 | Date completed:
IGCS | Libertad | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Started:
IGCS | Libuak | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | Rehab. Of Evacuation Center, Libuak, IGCS |  | 20% DF CY 2019 (STIMULUS | Building |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | For implementation
IGCS | Libuak | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
IGCS | Libuak | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
IGCS | Libuak | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
IGCS | Libuak | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Allotment Released: | 2019-05-29 | Date completed:
IGCS | Libuak | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Started:
IGCS | Kaputian | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | Const. of Water System Project, Pob. Kaputian, IGCS |  | 20% DF CY 2019 (STIMULUS | Water System |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | For implementation
IGCS | Kaputian | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
IGCS | Kaputian | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
IGCS | Kaputian | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
IGCS | Kaputian | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
IGCS | Kaputian | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Started:
Babak, IGCS | San Isidro | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | Rehab. Of Potable Water System, San Isidro, Babak, IGCS |  | 20% DF CY 2019 (STIMULUS | Water System |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | For implementation
Babak, IGCS | San Isidro | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Babak, IGCS | San Isidro | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Babak, IGCS | San Isidro | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Babak, IGCS | San Isidro | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Allotment Released: | 2019-06-19 | Date completed:
Babak, IGCS | San Isidro | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Started:
IGCS | San Miguel | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | Rehab. Of Potable Water System, San Miguel, IGCS |  | 20% DF CY 2019 (STIMULUS | Water System |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | For implementation
IGCS | San Miguel | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
IGCS | San Miguel | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
IGCS | San Miguel | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
IGCS | San Miguel | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Allotment Released: | 2019-02-28 | Date completed:
IGCS | San Miguel | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Started:
IGCS | San Remegio | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | Const. of Water System Ph.II, San Remegio, IGCS |  | 20% DF CY 2019 (STIMULUS | Water System |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | For implementation
IGCS | San Remegio | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
IGCS | San Remegio | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
IGCS | San Remegio | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
IGCS | San Remegio | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Allotment Released: | 2019-05-29 | Date completed:
IGCS | San Remegio | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Started:
IGCS | Licup | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | Electrificatio at Prk. 1,3,4, 6,7 & 8, Licup, IGCS |  | 20% DF CY 2019 (STIMULUS | Electrification |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | For implementation
IGCS | Licup | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
IGCS | Licup | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
IGCS | Licup | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
IGCS | Licup | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Allotment Released: | 2019-02-20 | Date completed:
IGCS | Licup | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Started:
IGCS | Kaputian | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Rural Electrification Project (Provincewide) | Rural Electrification at Sitio Sagrada, Pob. Kaputian, IGCS |  | 20% DF CY 2019 | Electrification |  |  |  | Project Cost: | 1000000 | Target Completion Date: |  | Program: | 1000000 | Planned: |  | No. of Persons: |  | Purchase Request # 19031251
IGCS | Kaputian | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Rural Electrification Project (Provincewide) | [7 empty] | Project Engineer: | Buena | Revised Completion Date: |  | Allotment: | 1000000 | Revised: |  | No. of Man-days:
IGCS | Kaputian | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Rural Electrification Project (Provincewide) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
IGCS | Kaputian | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Rural Electrification Project (Provincewide) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
IGCS | Kaputian | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Rural Electrification Project (Provincewide) | [7 empty] | Date Allotment Released: |  | Date completed:
IGCS | Kaputian | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Rural Electrification Project (Provincewide) | [7 empty] | Date Started:
Carmen | Tuganay | 2nd Eng'g. Dist. | On-going | 2009-08-19 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Revitment of Dike and Slope Proection | Repair/Rehab. Of Upper Tuganay Dike |  | 5% CALAMITY FUND CY 2019 | Dike |  | ln.m | Admin | Project Cost: | 1000000 | Target Completion Date: | 2019-09-29 | Program: | 1000000 | Planned: | 90% | No. of Persons: | 9 | On-going
Carmen | Tuganay | 2nd Eng'g. Dist. | On-going | 2009-08-19 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Revitment of Dike and Slope Proection | [7 empty] | Project Engineer: | Toquero | Revised Completion Date: |  | Allotment: | 1000000 | Revised: |  | No. of Man-days: | 80
Carmen | Tuganay | 2nd Eng'g. Dist. | On-going | 2009-08-19 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Revitment of Dike and Slope Proection | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: | 90%
Carmen | Tuganay | 2nd Eng'g. Dist. | On-going | 2009-08-19 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Revitment of Dike and Slope Proection | [7 empty] | Duration: | 41 | No. of days extended: |  |  |  | Slippage: | 0%
Carmen | Tuganay | 2nd Eng'g. Dist. | On-going | 2009-08-19 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Revitment of Dike and Slope Proection | [7 empty] | Date Allotment Released: | 2019-08-15 | Date completed:
Carmen | Tuganay | 2nd Eng'g. Dist. | On-going | 2009-08-19 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Revitment of Dike and Slope Proection | [7 empty] | Date Started: | 2019-08-19
Carmen | Ising | 2nd Eng'g. Dist. | On-going | 2019-11-15 | 2020-06-30 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPLAN CANAL | Repair of Damaged Drainage/ Creek along Abucay Creek |  | 5% CALAMITY FUND | Creek |  | ln.m | Admin | Project Cost: | 1320000 | Target Completion Date: | 2019-12-05 | Program: | 1320000 | Planned: | 100% | No. of Persons: |  | Completed as per physical accomplishment. Financial documents still on process.
Carmen | Ising | 2nd Eng'g. Dist. | On-going | 2019-11-15 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPLAN CANAL | [7 empty] | Project Engineer: | Ganaba | Revised Completion Date: | 2020-06-04 | Allotment: | 1320000 | Revised: |  | No. of Man-days:
Carmen | Ising | 2nd Eng'g. Dist. | On-going | 2019-11-15 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPLAN CANAL | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: | 100%
Carmen | Ising | 2nd Eng'g. Dist. | On-going | 2019-11-15 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPLAN CANAL | [7 empty] | Duration: | 65 | No. of days extended: | 182 |  |  | Slippage: | 0%
Carmen | Ising | 2nd Eng'g. Dist. | On-going | 2019-11-15 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPLAN CANAL | [7 empty] | Date Allotment Released: |  | Date completed: | 2020-06-30
Carmen | Ising | 2nd Eng'g. Dist. | On-going | 2019-11-15 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPLAN CANAL | [7 empty] | Date Started: | 2019-10-01
Carmen | Ising | 2nd Eng'g. Dist. | On-going | 2019-11-15 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPLAN CANAL | Repair of Damaged Drainage Creek along Panabo River |  | 5% CALAMITY FUND | Creek |  | ln.m | Admin | Project Cost: | 665000 | Target Completion Date: | 2020-01-27 | Program: | 665000 | Planned: | 100% | No. of Persons: | 3 | On-going
Carmen | Ising | 2nd Eng'g. Dist. | On-going | 2019-11-15 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPLAN CANAL | [7 empty] | Project Engineer: | Alconera | Revised Completion Date: |  | Allotment: | 665000 | Revised: |  | No. of Man-days: | 66
Carmen | Ising | 2nd Eng'g. Dist. | On-going | 2019-11-15 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPLAN CANAL | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: | 15.3%
Carmen | Ising | 2nd Eng'g. Dist. | On-going | 2019-11-15 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPLAN CANAL | [7 empty] | Duration: | 73 | No. of days extended: |  |  |  | Slippage: | -84.7%
Carmen | Ising | 2nd Eng'g. Dist. | On-going | 2019-11-15 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPLAN CANAL | [7 empty] | Date Allotment Released: |  | Date completed:
Carmen | Ising | 2nd Eng'g. Dist. | On-going | 2019-11-15 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPLAN CANAL | [7 empty] | Date Started: | 2019-11-15
Carmen | Ising | 2nd Eng'g. Dist. | On-going | 2019-11-15 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPLAN CANAL | Repair of Damaged Drainage/Creek along Tuganay-Ising River |  | 5% CALAMITY FUND | Creek |  | ln.m | Admin | Project Cost: | 1540500 | Target Completion Date: | 2020-05-15 | Program: | 1540500 | Planned: | 25.6% | No. of Persons: | 3 | On-going
Carmen | Ising | 2nd Eng'g. Dist. | On-going | 2019-11-15 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPLAN CANAL | [7 empty] | Project Engineer: | Ganaba | Revised Completion Date: |  | Allotment: | 1540500 | Revised: |  | No. of Man-days: | 66
Carmen | Ising | 2nd Eng'g. Dist. | On-going | 2019-11-15 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPLAN CANAL | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: | 23.6%
Carmen | Ising | 2nd Eng'g. Dist. | On-going | 2019-11-15 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPLAN CANAL | [7 empty] | Duration: | 182 | No. of days extended: |  |  |  | Slippage: | -2%
Carmen | Ising | 2nd Eng'g. Dist. | On-going | 2019-11-15 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPLAN CANAL | [7 empty] | Date Allotment Released: |  | Date completed:
Carmen | Ising | 2nd Eng'g. Dist. | On-going | 2019-11-15 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPLAN CANAL | [7 empty] | Date Started: | 2019-11-15
Panabo City | Lasang | 2nd Eng'g. Dist. | Completed | 2019-08-01 | 2020-05-28 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPLAN CANAL | Repair of Damaged Drainage/ Creeks along San Miguel NIA Road |  | 5% CALAMITY FUND | Creek |  | ln.m | Admin | Project Cost: | 470000 | Target Completion Date: | 2019-09-16 | Program: | 470000 | Planned: | 100% | No. of Persons: | 3 | Completed as per physical accomplishment. Financial documents still on process.
Panabo City | Lasang | 2nd Eng'g. Dist. | Completed | 2019-08-01 | 2020-05-28 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPLAN CANAL | [7 empty] | Project Engineer: | Nasol | Revised Completion Date: | 2020-05-28 | Allotment: | 470000 | Revised: |  | No. of Man-days: | 66
Panabo City | Lasang | 2nd Eng'g. Dist. | Completed | 2019-08-01 | 2020-05-28 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPLAN CANAL | [7 empty] | Implementor: | PEO | No. of days suspended: | 255 | Disbursement: |  | Actual: | 100%
Panabo City | Lasang | 2nd Eng'g. Dist. | Completed | 2019-08-01 | 2020-05-28 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPLAN CANAL | [7 empty] | Duration: | 46 | No. of days extended: |  |  |  | Slippage: | 0%
Panabo City | Lasang | 2nd Eng'g. Dist. | Completed | 2019-08-01 | 2020-05-28 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPLAN CANAL | [7 empty] | Date Allotment Released: |  | Date completed: | 2020-05-28
Panabo City | Lasang | 2nd Eng'g. Dist. | Completed | 2019-08-01 | 2020-05-28 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPLAN CANAL | [7 empty] | Date Started: | 2019-08-01
Carmen | Ising | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPLAN CANAL | Repair of Damaged Drainage/ Creeks along Sadpodon Creek |  | 5% CALAMITY FUND | Creek |  |  | Admin | Project Cost: | 470000 | Target Completion Date: |  | Program: | 470000 | Planned: |  | No. of Persons: |  | For implementation
Carmen | Ising | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPLAN CANAL | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 470000 | Revised: |  | No. of Man-days:
Carmen | Ising | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPLAN CANAL | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual:
Carmen | Ising | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPLAN CANAL | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Carmen | Ising | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPLAN CANAL | [7 empty] | Date Allotment Released: |  | Date completed:
Carmen | Ising | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPLAN CANAL | [7 empty] | Date Started:
B.E. Dujali | Pawas | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Local Roads & Drainage Development Project Construction in Progress- Infrastructure Assets | Rehabilitation of Dujali-Pawas-San Vicente Provincial Road, B.E. Dujali |  | SB # 3 CY 2019 | Road |  |  |  | Project Cost: | 2000000 | Target Completion Date: |  | Program: | 2000000 | Planned: |  | No. of Persons: |  | The amount was reduced to P1,102,900.00
B.E. Dujali | Pawas | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Local Roads & Drainage Development Project Construction in Progress- Infrastructure Assets | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 2000000 | Revised: |  | No. of Man-days:
B.E. Dujali | Pawas | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Local Roads & Drainage Development Project Construction in Progress- Infrastructure Assets | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
B.E. Dujali | Pawas | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Local Roads & Drainage Development Project Construction in Progress- Infrastructure Assets | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
B.E. Dujali | Pawas | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Local Roads & Drainage Development Project Construction in Progress- Infrastructure Assets | [7 empty] | Date Allotment Released: |  | Date completed:
B.E. Dujali | Pawas | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Local Roads & Drainage Development Project Construction in Progress- Infrastructure Assets | [7 empty] | Date Started:
Samal | Mambago-A | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VariousWater System Development Project Construction in Progress- Infrastructure Assets | Improvement of Potable Water System at Brgy. Mambago- A, Samal District, IGACOS |  | SB # 3 CY 2019 | Water System |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | (Amended in the AIP 2nd Revision to change the location from Peñaplata to Samal District) PO approved September 2, 2019
Samal | Mambago-A | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VariousWater System Development Project Construction in Progress- Infrastructure Assets | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Samal | Mambago-A | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VariousWater System Development Project Construction in Progress- Infrastructure Assets | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Samal | Mambago-A | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VariousWater System Development Project Construction in Progress- Infrastructure Assets | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Samal | Mambago-A | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VariousWater System Development Project Construction in Progress- Infrastructure Assets | [7 empty] | Date Allotment Released: |  | Date completed:
Samal | Mambago-A | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VariousWater System Development Project Construction in Progress- Infrastructure Assets | [7 empty] | Date Started:
Samal | San Miguel | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VariousWater System Development Project Construction in Progress- Infrastructure Assets | Rehabilitation of Potable Water System at Brgy. San Miguel, Samal District, IGACOS |  | SB # 3 CY 2019 | Water System |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | For implementation
Samal | San Miguel | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VariousWater System Development Project Construction in Progress- Infrastructure Assets | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Samal | San Miguel | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VariousWater System Development Project Construction in Progress- Infrastructure Assets | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Samal | San Miguel | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VariousWater System Development Project Construction in Progress- Infrastructure Assets | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Samal | San Miguel | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VariousWater System Development Project Construction in Progress- Infrastructure Assets | [7 empty] | Date Allotment Released: |  | Date completed:
Samal | San Miguel | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VariousWater System Development Project Construction in Progress- Infrastructure Assets | [7 empty] | Date Started:
Kaputian, IGCS | Linusotan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VariousWater System Development Project Construction in Progress- Infrastructure Assets | Construction of Potable Water System at Brgy.Linusotan, Kaputian District, IGACOS |  | SB # 3 CY 2019 | Water System |  |  |  | Project Cost: | 1300000 | Target Completion Date: |  | Program: | 1300000 | Planned: |  | No. of Persons: |  | (Additional 800,000.00 from Const. of PWS in purok 2, Pag-asa, Kapalong which was funded by OPAPP CY 2018) (amended) For allotment- October 15, 2019
Kaputian, IGCS | Linusotan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VariousWater System Development Project Construction in Progress- Infrastructure Assets | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 1300000 | Revised: |  | No. of Man-days:
Kaputian, IGCS | Linusotan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VariousWater System Development Project Construction in Progress- Infrastructure Assets | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Kaputian, IGCS | Linusotan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VariousWater System Development Project Construction in Progress- Infrastructure Assets | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Kaputian, IGCS | Linusotan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VariousWater System Development Project Construction in Progress- Infrastructure Assets | [7 empty] | Date Allotment Released: |  | Date completed:
Kaputian, IGCS | Linusotan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VariousWater System Development Project Construction in Progress- Infrastructure Assets | [7 empty] | Date Started:
Carmen | Ising | 2nd Eng'g. Dist. | Completed | 2019-07-29 | 2019-11-11 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DISASTER REHABILITATION & RECOVERY PROGRAM Building Back Better Project | Disiltation of Mactan River (Ph. II) |  | 5% Calamity Fund CY 2019 | Desiltation |  | ln.m |  | Project Cost: | 500000 | Target Completion Date: | 2019-09-27 | Program: | 500000 | Planned: | 100% | No. of Persons: |  | Completed as per physical accomplishment. Financial documents still on process.
Carmen | Ising | 2nd Eng'g. Dist. | Completed | 2019-07-29 | 2019-11-11 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DISASTER REHABILITATION & RECOVERY PROGRAM Building Back Better Project | [7 empty] | Project Engineer: | Toquero | Revised Completion Date: | 2019-11-11 | Allotment: | 500000 | Revised: |  | No. of Man-days:
Carmen | Ising | 2nd Eng'g. Dist. | Completed | 2019-07-29 | 2019-11-11 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DISASTER REHABILITATION & RECOVERY PROGRAM Building Back Better Project | [7 empty] | Implementor: | PEO | No. of days suspended: | 45 | Disbursement: |  | Actual: | 100%
Carmen | Ising | 2nd Eng'g. Dist. | Completed | 2019-07-29 | 2019-11-11 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DISASTER REHABILITATION & RECOVERY PROGRAM Building Back Better Project | [7 empty] | Duration: | 60 | No. of days extended: |  |  |  | Slippage: | 0%
Carmen | Ising | 2nd Eng'g. Dist. | Completed | 2019-07-29 | 2019-11-11 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DISASTER REHABILITATION & RECOVERY PROGRAM Building Back Better Project | [7 empty] | Date Allotment Released: | 2019-05-28 | Date completed: | 2019-11-11
Carmen | Ising | 2nd Eng'g. Dist. | Completed | 2019-07-29 | 2019-11-11 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DISASTER REHABILITATION & RECOVERY PROGRAM Building Back Better Project | [7 empty] | Date Started: | 2019-07-29
B.E. Dujali | Magupising | 2nd Eng'g. Dist. | Completed | 2019-12-02 | 2020-06-15 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DISASTER REHABILITATION & RECOVERY PROGRAM Building Back Better Project | Rehabilitation of Dujali-Balisong-Magupising Provincial Road |  | 5% Calamity Fund CY 2019 | Rehabilitation |  | km | Admin | Project Cost: | 1280000 | Target Completion Date: | 2020-02-03 | Program: | 1280000 | Planned: | 100% | No. of Persons: |  | Completed as per physical accomplishment. Financial documents still on process.
B.E. Dujali | Magupising | 2nd Eng'g. Dist. | Completed | 2019-12-02 | 2020-06-15 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DISASTER REHABILITATION & RECOVERY PROGRAM Building Back Better Project | [7 empty] | Project Engineer: | Mellomida | Revised Completion Date: | 2020-06-15 | Allotment: | 1280000 | Revised: | 100% | No. of Man-days:
B.E. Dujali | Magupising | 2nd Eng'g. Dist. | Completed | 2019-12-02 | 2020-06-15 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DISASTER REHABILITATION & RECOVERY PROGRAM Building Back Better Project | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: |  | Actual: | 100%
B.E. Dujali | Magupising | 2nd Eng'g. Dist. | Completed | 2019-12-02 | 2020-06-15 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DISASTER REHABILITATION & RECOVERY PROGRAM Building Back Better Project | [7 empty] | Duration: | 63 | No. of days extended: | 106 |  |  | Slippage: | 0%
B.E. Dujali | Magupising | 2nd Eng'g. Dist. | Completed | 2019-12-02 | 2020-06-15 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DISASTER REHABILITATION & RECOVERY PROGRAM Building Back Better Project | [7 empty] | Date Allotment Released: |  | Date completed: | 2020-06-15
B.E. Dujali | Magupising | 2nd Eng'g. Dist. | Completed | 2019-12-02 | 2020-06-15 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DISASTER REHABILITATION & RECOVERY PROGRAM Building Back Better Project | [7 empty] | Date Started: | 2019-12-02
Sto. Tomas | Magwawa | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PEACE AND ORDER PROGRAM/1914 Construction in Progress- Land Improvements | Rehabilitation of San Jose- Sitio Mahayahay-Magwawa Provincial Road, Sto. Tomas |  | SB # 4 CY 2019 | Road |  |  |  | Project Cost: | 1000000 | Target Completion Date: |  | Program: | 1000000 | Planned: |  | No. of Persons: |  | POW preparation on-going c/o South District
Sto. Tomas | Magwawa | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PEACE AND ORDER PROGRAM/1914 Construction in Progress- Land Improvements | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 1000000 | Revised: |  | No. of Man-days:
Sto. Tomas | Magwawa | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PEACE AND ORDER PROGRAM/1914 Construction in Progress- Land Improvements | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Sto. Tomas | Magwawa | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PEACE AND ORDER PROGRAM/1914 Construction in Progress- Land Improvements | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Sto. Tomas | Magwawa | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PEACE AND ORDER PROGRAM/1914 Construction in Progress- Land Improvements | [7 empty] | Date Allotment Released: |  | Date completed:
Sto. Tomas | Magwawa | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PEACE AND ORDER PROGRAM/1914 Construction in Progress- Land Improvements | [7 empty] | Date Started:
Panabo City | Dalisay | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Local Roads and Drainage Development Project Construction in Progress- Infrastructure Assets | Rehabilitation of Local Roads at Dalisay-Manay Road Section, Panabo City |  | SB # 4 CY 2019 | Road |  |  | Admin | Project Cost: | 246100 | Target Completion Date: |  | Program: | 246100 | Planned: |  | No. of Persons: |  | For implementation
Panabo City | Dalisay | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Local Roads and Drainage Development Project Construction in Progress- Infrastructure Assets | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 246100 | Revised: |  | No. of Man-days:
Panabo City | Dalisay | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Local Roads and Drainage Development Project Construction in Progress- Infrastructure Assets | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Panabo City | Dalisay | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Local Roads and Drainage Development Project Construction in Progress- Infrastructure Assets | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Panabo City | Dalisay | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Local Roads and Drainage Development Project Construction in Progress- Infrastructure Assets | [7 empty] | Date Allotment Released: |  | Date completed:
Panabo City | Dalisay | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Local Roads and Drainage Development Project Construction in Progress- Infrastructure Assets | [7 empty] | Date Started:
Panabo City | Buenavista | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Local Roads and Drainage Development Project Construction in Progress- Infrastructure Assets | Rehabilitation of Local Roads at Sta. Cruz-Jct. Tagpore-Buenavista Raod Section, Panabo City |  | SB # 4 CY 2019 | Road |  |  | Admin | Project Cost: | 431000 | Target Completion Date: |  | Program: | 431000 | Planned: |  | No. of Persons: |  | For implementation
Panabo City | Buenavista | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Local Roads and Drainage Development Project Construction in Progress- Infrastructure Assets | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 431000 | Revised: |  | No. of Man-days:
Panabo City | Buenavista | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Local Roads and Drainage Development Project Construction in Progress- Infrastructure Assets | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Panabo City | Buenavista | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Local Roads and Drainage Development Project Construction in Progress- Infrastructure Assets | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Panabo City | Buenavista | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Local Roads and Drainage Development Project Construction in Progress- Infrastructure Assets | [7 empty] | Date Allotment Released: |  | Date completed:
Panabo City | Buenavista | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Local Roads and Drainage Development Project Construction in Progress- Infrastructure Assets | [7 empty] | Date Started:
Carmen | Taba | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Local Roads and Drainage Development Project Construction in Progress- Infrastructure Assets | Rehabilitation of Local Roads at Taba-Bucana Road Section, Taba, Carmen |  | SB # 4 CY 2019 | Road |  |  | Admin | Project Cost: | 220000 | Target Completion Date: |  | Program: | 220000 | Planned: |  | No. of Persons: |  | For implementation
Carmen | Taba | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Local Roads and Drainage Development Project Construction in Progress- Infrastructure Assets | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 220000 | Revised: |  | No. of Man-days:
Carmen | Taba | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Local Roads and Drainage Development Project Construction in Progress- Infrastructure Assets | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Carmen | Taba | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Local Roads and Drainage Development Project Construction in Progress- Infrastructure Assets | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Carmen | Taba | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Local Roads and Drainage Development Project Construction in Progress- Infrastructure Assets | [7 empty] | Date Allotment Released: |  | Date completed:
Carmen | Taba | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Local Roads and Drainage Development Project Construction in Progress- Infrastructure Assets | [7 empty] | Date Started:
B.E. Dujali | Dujali | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | Concreting of Brgy. Road Canal, Dujali, B.E. Dujali |  | SB # 4 CY 2019 (STIMULUS | Concreting |  |  | Contract | Project Cost: | 650000 | Target Completion Date: |  | Program: | 650000 | Planned: |  | No. of Persons: |  | For implementation
B.E. Dujali | Dujali | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 650000 | Revised: |  | No. of Man-days:
B.E. Dujali | Dujali | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
B.E. Dujali | Dujali | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
B.E. Dujali | Dujali | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Date Allotment Released: |  | Date completed:
B.E. Dujali | Dujali | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Date Started:
B.E. Dujali | New Casay | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | Desilting and Conretign of Drainage-Main Collector Canal, New Casay, B.E. Dujali |  | SB # 4 CY 2019 (STIMULUS | Desiltation |  |  | Contract | Project Cost: | 650000 | Target Completion Date: |  | Program: | 650000 | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
B.E. Dujali | New Casay | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 650000 | Revised: |  | No. of Man-days:
B.E. Dujali | New Casay | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
B.E. Dujali | New Casay | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
B.E. Dujali | New Casay | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Date Allotment Released: |  | Date completed:
B.E. Dujali | New Casay | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Date Started:
B.E. Dujali | Tanglaw | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | Concreting of Drainage, Tanglaw, B.E., Dujali |  | SB # 4 CY 2019 (STIMULUS | Desiltation |  |  | Contract | Project Cost: | 1200000 | Target Completion Date: |  | Program: | 1200000 | Planned: |  | No. of Persons: |  | For implementation
B.E. Dujali | Tanglaw | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 1200000 | Revised: |  | No. of Man-days:
B.E. Dujali | Tanglaw | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
B.E. Dujali | Tanglaw | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
B.E. Dujali | Tanglaw | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Date Allotment Released: |  | Date completed:
B.E. Dujali | Tanglaw | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Date Started:
Panabo City | New Malitbog | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | Construction of Potable Water System, New Malitbog, Panabo City |  | SB # 4 CY 2019 (STIMULUS | Water System |  |  | Contract | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
Panabo City | New Malitbog | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Panabo City | New Malitbog | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Panabo City | New Malitbog | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Panabo City | New Malitbog | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Date Allotment Released: |  | Date completed:
Panabo City | New Malitbog | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Date Started:
Kaputian, IGCS | Poblacion | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | Construction of Water System Project, Poblacion Kaputian, Samal |  | SB # 4 CY 2019 (STIMULUS | Water System |  |  | Contract | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | For implementation
Kaputian, IGCS | Poblacion | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Kaputian, IGCS | Poblacion | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Kaputian, IGCS | Poblacion | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Kaputian, IGCS | Poblacion | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Date Allotment Released: |  | Date completed:
Kaputian, IGCS | Poblacion | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Date Started:
Panabo City | salvacion | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | Construction of Canal Lining at Prk. 5, Salvacion, Panabo City |  | SB # 4 CY 2019 (STIMULUS | Canal lining |  |  | Contract | Project Cost: | 600000 | Target Completion Date: |  | Program: | 600000 | Planned: |  | No. of Persons: |  | For implementation
Panabo City | salvacion | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 600000 | Revised: |  | No. of Man-days:
Panabo City | salvacion | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Panabo City | salvacion | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Panabo City | salvacion | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Date Allotment Released: |  | Date completed:
Panabo City | salvacion | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Date Started:
Sto. Tomas | Lunga-og | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | Rehabilitation of Brgy. Road at Lunga-og. Sto. Tomas |  | SB # 4 CY 2019 (STIMULUS | Road |  |  | Contract | Project Cost: | 600000 | Target Completion Date: |  | Program: | 600000 | Planned: |  | No. of Persons: |  | For implementation
Sto. Tomas | Lunga-og | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 600000 | Revised: |  | No. of Man-days:
Sto. Tomas | Lunga-og | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Sto. Tomas | Lunga-og | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Sto. Tomas | Lunga-og | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Date Allotment Released: |  | Date completed:
Sto. Tomas | Lunga-og | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Date Started:
Carmen | Sto. Niño | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | Construction of Evacuation Center at Purok 1-C Brgy. Sto. Niño, Carmen |  | SB # 4 CY 2019 (STIMULUS | Building |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | For implementation
Carmen | Sto. Niño | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Carmen | Sto. Niño | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Carmen | Sto. Niño | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Carmen | Sto. Niño | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Date Allotment Released: |  | Date completed:
Carmen | Sto. Niño | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Date Started:
Panabo City | Waterfall | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | Construction of Multi-Purpose Hall, Waterfall, Panabo City |  | SB # 4 CY 2019 (STIMULUS | Building |  |  |  | Project Cost: | 1050000 | Target Completion Date: |  | Program: | 1050000 | Planned: |  | No. of Persons: |  | For implementation
Panabo City | Waterfall | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 1050000 | Revised: |  | No. of Man-days:
Panabo City | Waterfall | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Panabo City | Waterfall | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Panabo City | Waterfall | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Date Allotment Released: |  | Date completed:
Panabo City | Waterfall | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Date Started:
Panabo City | San Francisco | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | Rehabilitation of Multi-Purpose Hall, San Francisco, Panabo City |  | SB # 4 CY 2019 (STIMULUS | Building |  |  |  | Project Cost: | 600000 | Target Completion Date: |  | Program: | 600000 | Planned: |  | No. of Persons: |  | For implementation
Panabo City | San Francisco | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 600000 | Revised: |  | No. of Man-days:
Panabo City | San Francisco | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Panabo City | San Francisco | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Panabo City | San Francisco | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Date Allotment Released: |  | Date completed:
Panabo City | San Francisco | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Date Started:
Panabo City | Datu Abdul | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | Rehabilitation of Evacuation Center at Datu Abdul Dadia, Panabo City |  | SB # 4 CY 2019 (STIMULUS | Building |  |  |  | Project Cost: | 650000 | Target Completion Date: |  | Program: | 650000 | Planned: |  | No. of Persons: |  | For implementation
Panabo City | Datu Abdul | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 650000 | Revised: |  | No. of Man-days:
Panabo City | Datu Abdul | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Panabo City | Datu Abdul | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Panabo City | Datu Abdul | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Date Allotment Released: |  | Date completed:
Panabo City | Datu Abdul | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Date Started:
Panabo City | Buenavista | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | Construction of Multi-Purpose Hall, Buenavista, Panabo City |  | SB # 4 CY 2019 (STIMULUS | Building |  |  |  | Project Cost: | 1050000 | Target Completion Date: |  | Program: | 1050000 | Planned: |  | No. of Persons: |  | For implementation
Panabo City | Buenavista | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 1050000 | Revised: |  | No. of Man-days:
Panabo City | Buenavista | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Panabo City | Buenavista | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Panabo City | Buenavista | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Date Allotment Released: |  | Date completed:
Panabo City | Buenavista | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Date Started:
Panabo City | Little Panay | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | Rehabilitation of Multi-Purpose Hall, Llittle Panay, Panabo City |  | SB # 4 CY 2019 (STIMULUS | Building |  |  |  | Project Cost: | 550000 | Target Completion Date: |  | Program: | 550000 | Planned: |  | No. of Persons: |  | For implementation
Panabo City | Little Panay | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 550000 | Revised: |  | No. of Man-days:
Panabo City | Little Panay | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Panabo City | Little Panay | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Panabo City | Little Panay | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Date Allotment Released: |  | Date completed:
Panabo City | Little Panay | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Date Started:
Sto. Tomas | Pantaron | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | Rehabilitation of Multi-Purpose Hall, Pantaron, Sto. Tomas |  | SB # 4 CY 2019 (STIMULUS | Building |  |  |  | Project Cost: | 550000 | Target Completion Date: |  | Program: | 550000 | Planned: |  | No. of Persons: |  | For implementation
Sto. Tomas | Pantaron | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 550000 | Revised: |  | No. of Man-days:
Sto. Tomas | Pantaron | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Sto. Tomas | Pantaron | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Sto. Tomas | Pantaron | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Date Allotment Released: |  | Date completed:
Sto. Tomas | Pantaron | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Date Started:
Sto. Tomas | salvacion | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | Rehabilitation of Multi-Purpose Hall, Salvacion, Sto. Tomas |  | SB # 4 CY 2019 (STIMULUS | Building |  |  |  | Project Cost: | 1000000 | Target Completion Date: |  | Program: | 1000000 | Planned: |  | No. of Persons: |  | PR #20032281
Sto. Tomas | salvacion | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 1000000 | Revised: |  | No. of Man-days:
Sto. Tomas | salvacion | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Sto. Tomas | salvacion | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Sto. Tomas | salvacion | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Date Allotment Released: |  | Date completed:
Sto. Tomas | salvacion | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Date Started:
Sto. Tomas | San Jose | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | Completion of Multi-Purpose Hall, San Jose, Sto. Tomas |  | SB # 4 CY 2019 (STIMULUS | Building |  |  |  | Project Cost: | 600000 | Target Completion Date: |  | Program: | 600000 | Planned: |  | No. of Persons: |  | For implementation
Sto. Tomas | San Jose | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 600000 | Revised: |  | No. of Man-days:
Sto. Tomas | San Jose | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Sto. Tomas | San Jose | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Sto. Tomas | San Jose | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Date Allotment Released: |  | Date completed:
Sto. Tomas | San Jose | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Date Started:
Panabo City | Kasilak | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | Rehabilitation of Multi-Purpose Hall, Kasilak, Panabo City |  | SB # 4 CY 2019 (STIMULUS | Building |  |  |  | Project Cost: | 650000 | Target Completion Date: |  | Program: | 650000 | Planned: |  | No. of Persons: |  | For implementation
Panabo City | Kasilak | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 650000 | Revised: |  | No. of Man-days:
Panabo City | Kasilak | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Panabo City | Kasilak | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Panabo City | Kasilak | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Date Allotment Released: |  | Date completed:
Panabo City | Kasilak | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Date Started:
Panabo City | Dalisay | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | Rehabilitation of Brgy. Health Center, Dalisay, Panabo City |  | SB # 4 CY 2019 (STIMULUS | Building |  |  |  | Project Cost: | 550000 | Target Completion Date: |  | Program: | 550000 | Planned: |  | No. of Persons: |  | For implementation
Panabo City | Dalisay | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 550000 | Revised: |  | No. of Man-days:
Panabo City | Dalisay | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Panabo City | Dalisay | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Panabo City | Dalisay | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Date Allotment Released: |  | Date completed:
Panabo City | Dalisay | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Date Started:
Panabo City | Kiotoy | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | Rehabilitation of Evacuation Center, Kiotoy, Panabo City |  | SB # 4 CY 2019 (STIMULUS | Building |  |  |  | Project Cost: | 650000 | Target Completion Date: |  | Program: | 650000 | Planned: |  | No. of Persons: |  | For implementation
Panabo City | Kiotoy | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 650000 | Revised: |  | No. of Man-days:
Panabo City | Kiotoy | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Panabo City | Kiotoy | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Panabo City | Kiotoy | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Date Allotment Released: |  | Date completed:
Panabo City | Kiotoy | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Date Started:
Panabo City | Cagangohan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | Rehabilitation of Evacuation Center, Cagangohan, Panabo City |  | SB # 4 CY 2019 (STIMULUS | Building |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Abstract #0520201798 - Digos constrak
Panabo City | Cagangohan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Panabo City | Cagangohan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Panabo City | Cagangohan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Panabo City | Cagangohan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Date Allotment Released: |  | Date completed:
Panabo City | Cagangohan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Date Started:
IGCS | Tagpopongan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | Rehabilitation of Multi-Purpose Bldg. (Brgy. Hall) Tagpopongan, IGACOS |  | SB # 4 CY 2019 (STIMULUS | Building |  |  |  | Project Cost: | 174460.33 | Target Completion Date: |  | Program: | 174460.33 | Planned: |  | No. of Persons: |  | Procurement on process
IGCS | Tagpopongan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 174460.33 | Revised: |  | No. of Man-days:
IGCS | Tagpopongan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
IGCS | Tagpopongan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
IGCS | Tagpopongan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Date Allotment Released: |  | Date completed:
IGCS | Tagpopongan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Date Started:
Sto. Tomas | Balagunan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | Construction of Multi-Purpose Building, Balagunan, Sto. Tomas |  | SB # 4 CY 2019 (STIMULUS | Building |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | For implementation
Sto. Tomas | Balagunan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Sto. Tomas | Balagunan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Sto. Tomas | Balagunan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Sto. Tomas | Balagunan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Date Allotment Released: |  | Date completed:
Sto. Tomas | Balagunan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Date Started:
Carmen | La Paz | 2nd Eng'g. Dist. | On-going |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CMGP | Road Upgrading of Sto Nino - Kabankalan - La Paz Provincial Road, Carmen |  | CMGP CY 2019 | Road |  | km | Contract | Project Cost: | 44461624.67 | Target Completion Date: | 2020-05-15 23:59 | Program: | 44461624.67 | Planned: | 76.36% | No. of Persons: | 42 | On-going
Carmen | La Paz | 2nd Eng'g. Dist. | On-going |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CMGP | [7 empty] | Project Engineer: | Comidoy | Revised Completion Date: | 2020-07-20 23:59 | Allotment: | 44461624.67 | Revised: |  | No. of Man-days: | 610
Carmen | La Paz | 2nd Eng'g. Dist. | On-going |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CMGP | [7 empty] | Implementor: | GP & H CONST. | No. of days suspended: | 66 | Disbursement: | 6684253.05 | Actual: | 95.75%
Carmen | La Paz | 2nd Eng'g. Dist. | On-going |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CMGP | [7 empty] | Duration: | 222 | No. of days extended: |  |  |  | Slippage: | 19.39%
Carmen | La Paz | 2nd Eng'g. Dist. | On-going |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CMGP | [7 empty] | Date Allotment Released: | CY 2019 | Date completed:
Carmen | La Paz | 2nd Eng'g. Dist. | On-going |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CMGP | [7 empty] | Date Started: | 2019-10-07
Carmen | La Paz | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CMGP | Road Upgrading of Jct Highway - Sto Nino - La Paz - San Vicenter Provincial Road, Carmen |  | CMGP CY 2019 | Road |  | km | Contract | Project Cost: | 80481331.34 | Target Completion Date: | 2020-06-22 | Program: | 80481331.34 | Planned: | 94.91% | No. of Persons: | 40 | On-going | 94.91
Carmen | La Paz | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CMGP | [7 empty] | Project Engineer: | Fernandez | Revised Completion Date: | 2020-08-04 | Allotment: | 80481331.34 | Revised: |  | No. of Man-days: | 660
Carmen | La Paz | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CMGP | [7 empty] | Implementor: | Tagum Builders | No. of days suspended: | 43 | Disbursement: | 45481609.97 | Actual: | 94.79%
Carmen | La Paz | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CMGP | [7 empty] | Duration: | 259 | No. of days extended: |  |  |  | Slippage: | -0.12%
Carmen | La Paz | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CMGP | [7 empty] | Date Allotment Released: | CY 2019 | Date completed:
Carmen | La Paz | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CMGP | [7 empty] | Date Started: | 2019-10-07
Carmen | Mangalcal | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | 0 | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 073 - Cebulano - Mangalcal |  | GENERAL FUND CY 2020 | Maintenance | 4.17 | km | MBA | Project Cost: | 134672.7 | Target Completion Date: | 2020-12-31 23:59 | Program: | 134672.7 | Planned: | 50% | No. of Persons: | 64 | On-going
Carmen | Mangalcal | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Gamad/Clar | Revised Completion Date: |  | Allotment: | 134672.7 | Revised: |  | No. of Man-days: | 1280
Carmen | Mangalcal | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: | 51%
Carmen | Mangalcal | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 1%
Carmen | Mangalcal | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
Carmen | Mangalcal | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started: | 2020-01-02
Carmen | Mangalcal | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 073 - Cebulano - Mangalcal |  | GENERAL FUND CY 2020 | Maintenance | 4.17 | km | CBRMC | Project Cost: | 131004.66 | Target Completion Date: | 2020-11-11 | Program: | 131004.66 | Planned: | 5% | No. of Persons: |  | On-going
Carmen | Mangalcal | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Maligro | Revised Completion Date: |  | Allotment: | 131004.66 | Revised: |  | No. of Man-days:
Carmen | Mangalcal | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: | Brgy. Mangalcal Women's Household | No. of days suspended: |  | Disbursement: |  | Actual: | 5%
Carmen | Mangalcal | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: | 180 | No. of days extended: |  |  |  | Slippage: | 0%
Carmen | Mangalcal | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
Carmen | Mangalcal | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started: | 2020-05-15
Carmen | Tubod | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 074 - Tubod - basa - Mangalcal |  | GENERAL FUND CY 2020 | Maintenance | 3.93 | km | MBA | Project Cost: | 143530.25 | Target Completion Date: | 2020-12-31 23:59 | Program: | 143530.25 | Planned: | 50% | No. of Persons: | 3 | On-going
Carmen | Tubod | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Gamad/Clar | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 143530.25 | Revised: |  | No. of Man-days: | 66
Carmen | Tubod | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: |  | Actual: | 52%
Carmen | Tubod | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 2%
Carmen | Tubod | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
Carmen | Tubod | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started: | 2020-01-02
Carmen | Tubod | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 074 - Tubod - basa - Mangalcal |  | GENERAL FUND CY 2020 | Maintenance | 3.93 | km | CBRMC | Project Cost: | 106856.33 | Target Completion Date: | 2020-11-25 23:59 | Program: | 106856.33 | Planned: | 5% | No. of Persons: | 2 | On-going
Carmen | Tubod | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Maligro | Revised Completion Date: |  | Allotment: | 106856.33 | Revised: |  | No. of Man-days: | 2
Carmen | Tubod | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: | Tubod Centro Lower Irrigator's Association | No. of days suspended: |  | Disbursement: |  | Actual: | 5%
Carmen | Tubod | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: | 185 | No. of days extended: |  |  |  | Slippage: | 0%
Carmen | Tubod | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
Carmen | Tubod | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started: | 2020-05-25
Carmen | Tubod | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 078 - Upper Mangalcal - Lower Mangalcal |  | GENERAL FUND CY 2020 | Maintenance | 2.43 | km | MBA | Project Cost: | 82374.21 | Target Completion Date: | 2020-12-31 23:59 | Program: | 82374.21 | Planned: | 50% | No. of Persons: | 3 | On-going
Carmen | Tubod | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Gamad/Clar | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 82374.21 | Revised: |  | No. of Man-days: | 66
Carmen | Tubod | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: |  | Actual: | 55%
Carmen | Tubod | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 5%
Carmen | Tubod | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
Carmen | Tubod | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started: | 2020-01-02
Carmen | Mangalcal | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 078 - Upper Mangalcal - Lower Mangalcal |  | GENERAL FUND CY 2020 | Maintenance | 2.43 | km | CBRMC | Project Cost: | 72444.97 | Target Completion Date: | 2020-11-15 23:59 | Program: | 72444.97 | Planned: | 5% | No. of Persons: | 2 | On-going
Carmen | Mangalcal | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Maligro | Revised Completion Date: |  | Allotment: | 72444.97 | Revised: |  | No. of Man-days: | 2
Carmen | Mangalcal | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: | Brgy. Mangalcal Women's Homebased Association | No. of days suspended: |  | Disbursement: |  | Actual: | 5%
Carmen | Mangalcal | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: | 185 | No. of days extended: |  |  |  | Slippage: | 0%
Carmen | Mangalcal | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
Carmen | Mangalcal | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started: | 2020-05-15
Carmen | Cebulano | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 079 - Cebulano - Loceta |  | GENERAL FUND CY 2020 | Maintenance |  | km | MBA | Project Cost: | 72051.43 | Target Completion Date: | 2020-12-31 23:59 | Program: | 72051.43 | Planned: | 30% | No. of Persons: | 3 | On-going
Carmen | Cebulano | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Gamad/Clar | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 72051.43 | Revised: |  | No. of Man-days: | 66
Carmen | Cebulano | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: |  | Actual: | 54%
Carmen | Cebulano | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 24%
Carmen | Cebulano | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
Carmen | Cebulano | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started: | 2020-01-02
Carmen | Cebulano | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 079 - Cebulano - Loceta |  | GENERAL FUND CY 2020 | Maintenance |  | km | CBRMC | Project Cost: | 47089.26 | Target Completion Date: | 2020-11-15 23:59 | Program: | 47089.26 | Planned: | 5% | No. of Persons: | 2 | On-going
Carmen | Cebulano | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Maligro | Revised Completion Date: |  | Allotment: | 47089.26 | Revised: |  | No. of Man-days: | 2
Carmen | Cebulano | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: | Brgy. Mangalcal Women's Homebased Association | No. of days suspended: |  | Disbursement: |  | Actual: | 5%
Carmen | Cebulano | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: | 185 | No. of days extended: |  |  |  | Slippage: | 0%
Carmen | Cebulano | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
Carmen | Cebulano | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started: | 2020-05-15
Carmen | Tubod | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 082 - Jct. Highway Carmen - Mangalcal - Tubod |  | GENERAL FUND CY 2020 | Maintenance | 11.34 | km | MBA | Project Cost: | 462895.06 | Target Completion Date: | 2020-12-31 23:59 | Program: | 462895.06 | Planned: | 50% | No. of Persons: | 4 | On-going
Carmen | Tubod | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Gamad/Clar | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 462895.06 | Revised: |  | No. of Man-days: | 88
Carmen | Tubod | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: |  | Actual: | 50%
Carmen | Tubod | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0%
Carmen | Tubod | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
Carmen | Tubod | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started: | 2020-01-02
Carmen | Tubod | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 082 - Jct. Highway Carmen - Mangalcal - Tubod |  | GENERAL FUND CY 2020 | Maintenance | 11.34 | km | CBRMC | Project Cost: | 259594.46 | Target Completion Date: |  | Program: | 259594.46 | Planned: |  | No. of Persons: |  | PO #2020031403 - Awarded to TUBOD CENTRO LOWER IRRIGATORS ASS'T (TUCLIA)
Carmen | Tubod | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Maligro | Revised Completion Date: |  | Allotment: | 259594.46 | Revised: |  | No. of Man-days:
Carmen | Tubod | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Carmen | Tubod | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Carmen | Tubod | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: |  | Date completed:
Carmen | Tubod | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started:
Carmen | Taba | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 086 - Ising - Sadpodon - Taba - Dila -Dila |  | GENERAL FUND CY 2020 | Maintenance | 5.68 | km | MBA | Project Cost: | 226651.27 | Target Completion Date: | 2020-12-31 23:59 | Program: | 226651.27 | Planned: | 50% | No. of Persons: | 3 | On-going
Carmen | Taba | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Gamad/Clar | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 226651.27 | Revised: |  | No. of Man-days: | 66
Carmen | Taba | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: |  | Actual: | 50%
Carmen | Taba | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0%
Carmen | Taba | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
Carmen | Taba | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started: | 2020-01-02
Carmen | Taba | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 086 - Ising - Sadpodon - Taba - Dila -Dila |  | GENERAL FUND CY 2020 | Maintenance | 5.68 | km | CBRMC | Project Cost: | 135230.61 | Target Completion Date: |  | Program: | 135230.61 | Planned: | 50% | No. of Persons: |  | PO #2020031408 - Awarded to TABA COCONUT FARMERS ORGANIZATION
Carmen | Taba | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Maligro | Revised Completion Date: |  | Allotment: | 135230.61 | Revised: |  | No. of Man-days:
Carmen | Taba | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: | 55%
Carmen | Taba | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 5%
Carmen | Taba | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: |  | Date completed:
Carmen | Taba | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started:
Carmen | Tuganay | 2nd Eng'g. Dist. | For Implementation | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 087 - Tuganay - taba |  | GENERAL FUND CY 2020 | Maintenance | 4.27 | km | MBA | Project Cost: | 169418.15 | Target Completion Date: | 2020-12-31 23:59 | Program: | 169418.15 | Planned: | 52% | No. of Persons: | 3 | On-going
Carmen | Tuganay | 2nd Eng'g. Dist. | For Implementation | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Gamad/Clar | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 169418.15 | Revised: |  | No. of Man-days: | 66
Carmen | Tuganay | 2nd Eng'g. Dist. | For Implementation | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: |  | Actual: | 52%
Carmen | Tuganay | 2nd Eng'g. Dist. | For Implementation | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0%
Carmen | Tuganay | 2nd Eng'g. Dist. | For Implementation | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
Carmen | Tuganay | 2nd Eng'g. Dist. | For Implementation | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started: | 2020-01-02
Carmen | Tuganay | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 087 - Tuganay - taba |  | GENERAL FUND CY 2020 | Maintenance | 4.27 | km | CBRMC | Project Cost: | 102630.37 | Target Completion Date: |  | Program: | 102630.37 | Planned: |  | No. of Persons: |  | PO #2020031406 - TABA COCONUT FARMERS ORGANIZATION
Carmen | Tuganay | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Maligro | Revised Completion Date: |  | Allotment: | 102630.37 | Revised: |  | No. of Man-days:
Carmen | Tuganay | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Carmen | Tuganay | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Carmen | Tuganay | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: |  | Date completed:
Carmen | Tuganay | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started:
Carmen | Tuganay | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 088 - Jct. Highway Tuganay - Taba |  | GENERAL FUND CY 2020 | Maintenance | 4.4 | km | MBA | Project Cost: | 222375.04 | Target Completion Date: | 2020-12-31 23:59 | Program: | 222375.04 | Planned: | 50% | No. of Persons: | 3 | On-going
Carmen | Tuganay | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Gamad/Clar | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 222375.04 | Revised: |  | No. of Man-days: | 66
Carmen | Tuganay | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: |  | Actual: | 51%
Carmen | Tuganay | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 1%
Carmen | Tuganay | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
Carmen | Tuganay | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started: | 2020-01-02
Carmen | Tuganay | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 088 - Jct. Highway Tuganay - Taba |  | GENERAL FUND CY 2020 | Maintenance | 4.4 | km | CBRMC | Project Cost: | 57955.99 | Target Completion Date: | 2020-11-13 23:59 | Program: | 57955.99 | Planned: | 5% | No. of Persons: | 2 | On-going
Carmen | Tuganay | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Maligro | Revised Completion Date: |  | Allotment: | 57955.99 | Revised: |  | No. of Man-days: | 2
Carmen | Tuganay | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: | Ezra Christian Minsitry For Peace, Inc. | No. of days suspended: |  | Disbursement: |  | Actual: | 5%
Carmen | Tuganay | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: | 185 | No. of days extended: |  |  |  | Slippage: | 0%
Carmen | Tuganay | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
Carmen | Tuganay | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started: | 2020-05-13
Carmen | Ising | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 089 - Jct. Highway Ising - Magsaysay |  | GENERAL FUND CY 2020 | Maintenance | 10.84 | km | MBA | Project Cost: | 478128.48 | Target Completion Date: | 2020-12-31 23:59 | Program: | 478128.48 | Planned: | 50% | No. of Persons: | 3 | On-going
Carmen | Ising | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Gamad/Clar | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 478128.48 | Revised: |  | No. of Man-days: | 66
Carmen | Ising | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: |  | Actual: | 50%
Carmen | Ising | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0%
Carmen | Ising | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
Carmen | Ising | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started: | 2020-01-02
Carmen | Ising | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 089 - Jct. Highway Ising - Magsaysay |  | GENERAL FUND CY 2020 | Maintenance | 10.84 | km | CBRMC | Project Cost: | 212505.24 | Target Completion Date: | 2020-11-14 23:59 | Program: | 212505.24 | Planned: | 5% | No. of Persons: | 2 | On-going
Carmen | Ising | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Maligro | Revised Completion Date: |  | Allotment: | 212505.24 | Revised: |  | No. of Man-days: | 42
Carmen | Ising | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: | School in the Air Integrated Farmer's Associiation | No. of days suspended: |  | Disbursement: |  | Actual: | 5%
Carmen | Ising | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: | 185 | No. of days extended: |  |  |  | Slippage: | 0%
Carmen | Ising | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
Carmen | Ising | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started: | 2020-05-14
C armen | New Camiling | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 090 - Maligaya - New Camiling |  | GENERAL FUND CY 2020 | Maintenance |  | km | MBA | Project Cost: | 51790.26 | Target Completion Date: | 2020-12-31 23:59 | Program: | 51790.26 | Planned: | 50% | No. of Persons: | 3 | On-going
C armen | New Camiling | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Gamad/Clar | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 51790.26 | Revised: |  | No. of Man-days: | 66
C armen | New Camiling | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: |  | Actual: | 51%
C armen | New Camiling | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 1%
C armen | New Camiling | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
C armen | New Camiling | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started: | 2020-01-02
C armen | New Camiling | 2nd Eng'g. Dist. | On-going | 2020-05-14 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 090 - Maligaya - New Camiling |  | GENERAL FUND CY 2020 | Maintenance |  | km | CBRMC | Project Cost: | 83915.44 | Target Completion Date: | 2020-11-14 23:59 | Program: | 83915.44 | Planned: | 5% | No. of Persons: | 2 | On-going
C armen | New Camiling | 2nd Eng'g. Dist. | On-going | 2020-05-14 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Maligro | Revised Completion Date: |  | Allotment: | 83915.44 | Revised: |  | No. of Man-days: | 2
C armen | New Camiling | 2nd Eng'g. Dist. | On-going | 2020-05-14 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: | School in the Air Integrated Farmer's Associiation | No. of days suspended: |  | Disbursement: |  | Actual: | 5%
C armen | New Camiling | 2nd Eng'g. Dist. | On-going | 2020-05-14 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: | 185 | No. of days extended: |  |  |  | Slippage: | 0%
C armen | New Camiling | 2nd Eng'g. Dist. | On-going | 2020-05-14 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
C armen | New Camiling | 2nd Eng'g. Dist. | On-going | 2020-05-14 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started: | 2020-05-14
C armen | New Camiling | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 091 - New Camiling - Alejal - Lower Magsaysay |  | GENERAL FUND CY 2020 | Maintenance | 6.73 | km | MBA | Project Cost: | 277852.05 | Target Completion Date: | 2020-12-31 23:59 | Program: | 277852.05 | Planned: | 50% | No. of Persons: | 3 | On-going
C armen | New Camiling | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Gamad/Clar | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 277852.05 | Revised: |  | No. of Man-days: | 66
C armen | New Camiling | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: |  | Actual: | 50%
C armen | New Camiling | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0%
C armen | New Camiling | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
C armen | New Camiling | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started: | 2020-01-02
C armen | New Camiling | 2nd Eng'g. Dist. | On-going | 2020-05-14 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 091 - New Camiling - Alejal - Lower Magsaysay |  | GENERAL FUND CY 2020 | Maintenance | 6.73 | km | CBRMC | Project Cost: | 150927.01 | Target Completion Date: | 2020-11-14 23:59 | Program: | 150927.01 | Planned: | 5% | No. of Persons: |  | On-going
C armen | New Camiling | 2nd Eng'g. Dist. | On-going | 2020-05-14 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Maligro | Revised Completion Date: |  | Allotment: | 150927.01 | Revised: |  | No. of Man-days:
C armen | New Camiling | 2nd Eng'g. Dist. | On-going | 2020-05-14 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: | School in the Air Integrated Farmer's Association | No. of days suspended: |  | Disbursement: |  | Actual: | 5%
C armen | New Camiling | 2nd Eng'g. Dist. | On-going | 2020-05-14 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: | 185 | No. of days extended: |  |  |  | Slippage: | 0%
C armen | New Camiling | 2nd Eng'g. Dist. | On-going | 2020-05-14 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
C armen | New Camiling | 2nd Eng'g. Dist. | On-going | 2020-05-14 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started: | 2020-05-14
Carmen | Tuganay | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 094 - Jct. highway Tuganay - Anibongan |  | GENERAL FUND CY 2020 | Maintenance | 3.66 | km | MBA | Project Cost: | 139609.7 | Target Completion Date: | 2020-12-31 23:59 | Program: | 139609.7 | Planned: | 50% | No. of Persons: | 4 | On-going
Carmen | Tuganay | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Gamad/Clar | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 139609.7 | Revised: |  | No. of Man-days: | 88
Carmen | Tuganay | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: |  | Actual: | 55%
Carmen | Tuganay | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 5%
Carmen | Tuganay | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
Carmen | Tuganay | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started: | 2020-01-02
Carmen | Tuganay | 2nd Eng'g. Dist. | On-going | 2020-05-13 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 094 - Jct. highway Tuganay - Anibongan |  | GENERAL FUND CY 2020 | Maintenance | 3.66 | km | CBRMC | Project Cost: | 93574.75 | Target Completion Date: | 2020-11-13 23:59 | Program: | 93574.75 | Planned: | 5% | No. of Persons: |  | Purchase Order # 2020030977 (Ezra Christian Minsitry For Peace, Inc.)
Carmen | Tuganay | 2nd Eng'g. Dist. | On-going | 2020-05-13 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Maligro | Revised Completion Date: |  | Allotment: | 93574.75 | Revised: |  | No. of Man-days:
Carmen | Tuganay | 2nd Eng'g. Dist. | On-going | 2020-05-13 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: | Ezra Christian Minsitry For Peace, Inc. | No. of days suspended: |  | Disbursement: |  | Actual: | 5%
Carmen | Tuganay | 2nd Eng'g. Dist. | On-going | 2020-05-13 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: | 185 | No. of days extended: |  |  |  | Slippage: | 0%
Carmen | Tuganay | 2nd Eng'g. Dist. | On-going | 2020-05-13 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
Carmen | Tuganay | 2nd Eng'g. Dist. | On-going | 2020-05-13 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started: | 2020-05-13
Carmen | Anibongan | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 095 - Anibongan - Guadalupe |  | GENERAL FUND CY 2020 | Maintenance | 2.48 | km | MBA | Project Cost: | 85559.79 | Target Completion Date: | 2020-12-31 23:59 | Program: | 85559.79 | Planned: | 50% | No. of Persons: | 4 | On-going / Time extension on process due to suspension of activity
Carmen | Anibongan | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Gamad/Clar | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 85559.79 | Revised: |  | No. of Man-days: | 78
Carmen | Anibongan | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: |  | Actual: | 55%
Carmen | Anibongan | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 5%
Carmen | Anibongan | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
Carmen | Anibongan | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started: | 2020-01-02
Carmen | Anibongan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 095 - Anibongan - Guadalupe |  | GENERAL FUND CY 2020 | Maintenance | 2.48 | km | CBRMC | Project Cost: | 72444.97 | Target Completion Date: |  | Program: | 72444.97 | Planned: |  | No. of Persons: |  | PO #2020031404 - PRK 4. ANIBONGAN CARMENT IRRIGATORS ASSN.
Carmen | Anibongan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Maligro | Revised Completion Date: |  | Allotment: | 72444.97 | Revised: |  | No. of Man-days:
Carmen | Anibongan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Carmen | Anibongan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Carmen | Anibongan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: |  | Date completed:
Carmen | Anibongan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started:
Carmen | Tuganay | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 096 - Tuganay - Anibongan - San Isidro |  | GENERAL FUND CY 2020 | Maintenance | 7.22 | km | MBA | Project Cost: | 344085.79 | Target Completion Date: | 2020-12-31 23:59 | Program: | 344085.79 | Planned: | 50% | No. of Persons: | 3 | On-going
Carmen | Tuganay | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Gamad/Clar | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 344085.79 | Revised: |  | No. of Man-days: | 66
Carmen | Tuganay | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: |  | Actual: | 50%
Carmen | Tuganay | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0%
Carmen | Tuganay | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
Carmen | Tuganay | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started: | 2020-01-02
Carmen | Tuganay | 2nd Eng'g. Dist. | On-going | 2020-05-13 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 096 - Tuganay - Anibongan - San Isidro |  | GENERAL FUND CY 2020 | Maintenance | 7.22 | km | CBRMC | Project Cost: | 115911.95 | Target Completion Date: | 2020-11-13 23:59 | Program: | 115911.95 | Planned: | 5% | No. of Persons: |  | On-going
Carmen | Tuganay | 2nd Eng'g. Dist. | On-going | 2020-05-13 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Maligro | Revised Completion Date: |  | Allotment: | 115911.95 | Revised: |  | No. of Man-days:
Carmen | Tuganay | 2nd Eng'g. Dist. | On-going | 2020-05-13 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: | Ezra Christian Minsitry For Peace, Inc. | No. of days suspended: |  | Disbursement: |  | Actual: | 5%
Carmen | Tuganay | 2nd Eng'g. Dist. | On-going | 2020-05-13 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: | 185 | No. of days extended: |  |  |  | Slippage: | 0%
Carmen | Tuganay | 2nd Eng'g. Dist. | On-going | 2020-05-13 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: |  | Date completed:
Carmen | Tuganay | 2nd Eng'g. Dist. | On-going | 2020-05-13 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started: | 2020-05-13
Carmen | Anibongan | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 097 - Jct. Anibongan - Prk. 2, 7, 5, San Isidro |  | GENERAL FUND CY 2020 | Maintenance | 3.14 | km | MBA | Project Cost: | 89575.84 | Target Completion Date: | 2020-12-31 23:59 | Program: | 89575.84 | Planned: | 50% | No. of Persons: | 4 | On-going
Carmen | Anibongan | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Gamad/Clar | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 89575.84 | Revised: |  | No. of Man-days: | 88
Carmen | Anibongan | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: |  | Actual: | 53%
Carmen | Anibongan | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 3%
Carmen | Anibongan | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
Carmen | Anibongan | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started: | 2020-01-02
Carmen | Anibongan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 097 - Jct. Anibongan - Prk. 2, 7, 5, San Isidro |  | GENERAL FUND CY 2020 | Maintenance | 3.14 | km | CBRMC | Project Cost: | 110478.58 | Target Completion Date: |  | Program: | 110478.58 | Planned: |  | No. of Persons: |  | PO #2020031378 - SAN ISIDRO FARMERS IRRIGATORS ASSN.
Carmen | Anibongan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Maligro | Revised Completion Date: |  | Allotment: | 110478.58 | Revised: |  | No. of Man-days:
Carmen | Anibongan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Carmen | Anibongan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Carmen | Anibongan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: |  | Date completed:
Carmen | Anibongan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started:
Carmen | Anibongan | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 098 - Anibongan - Salvacion - Cabay-angan |  | GENERAL FUND CY 2020 | Maintenance | 6.93 | km | MBA | Project Cost: | 279123.9 | Target Completion Date: | 2020-12-31 23:59 | Program: | 279123.9 | Planned: | 50% | No. of Persons: | 4 | On-going
Carmen | Anibongan | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Gamad/Clar | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 279123.9 | Revised: |  | No. of Man-days: | 88
Carmen | Anibongan | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: |  | Actual: | 51%
Carmen | Anibongan | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 1%
Carmen | Anibongan | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
Carmen | Anibongan | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started: | 2020-01-02
Carmen | Anibongan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 098 - Anibongan - Salvacion - Cabay-angan |  | GENERAL FUND CY 2020 | Maintenance | 6.93 | km | CBRMC | Project Cost: | 162397.48 | Target Completion Date: |  | Program: | 162397.48 | Planned: |  | No. of Persons: |  | PO #2020031379 - PRK4. ANIBONGAN CARMEN IRRIGATORS ASS.
Carmen | Anibongan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Maligro | Revised Completion Date: |  | Allotment: | 162397.48 | Revised: |  | No. of Man-days:
Carmen | Anibongan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Carmen | Anibongan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Carmen | Anibongan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: |  | Date completed:
Carmen | Anibongan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started:
Carmen | Mabaus | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 099 - Mabaus - Cabay - angan |  | GENERAL FUND CY 2020 | Maintenance |  | km | MBA | Project Cost: | 113320.9 | Target Completion Date: | 2020-12-31 23:59 | Program: | 113320.9 | Planned: | 50% | No. of Persons: | 3 | On-going
Carmen | Mabaus | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Gamad/Clar | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 113320.9 | Revised: |  | No. of Man-days: | 66
Carmen | Mabaus | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: |  | Actual: | 54%
Carmen | Mabaus | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 4%
Carmen | Mabaus | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
Carmen | Mabaus | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started: | 2020-01-02
Carmen | Mabaus | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 099 - Mabaus - Cabay - angan |  | GENERAL FUND CY 2020 | Maintenance |  | km | CBRMC | Project Cost: | 90556.21 | Target Completion Date: |  | Program: | 90556.21 | Planned: |  | No. of Persons: |  | PO #2020031410 - LAMPIA PAG ASA IRRIGATORS ASS., INC.
Carmen | Mabaus | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Maligro | Revised Completion Date: |  | Allotment: | 90556.21 | Revised: |  | No. of Man-days:
Carmen | Mabaus | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Carmen | Mabaus | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Carmen | Mabaus | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: |  | Date completed:
Carmen | Mabaus | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started:
Carmen | Guadalupe | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 101 - Jct. Highway Guadalupe - Bdry. Tagum |  | GENERAL FUND CY 2020 | Maintenance | 7.9 | km | MBA | Project Cost: | 517780.87 | Target Completion Date: | 2020-12-31 23:59 | Program: | 517780.87 | Planned: | 50% | No. of Persons: | 3 | On-going
Carmen | Guadalupe | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Gamad/Clar | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 517780.87 | Revised: |  | No. of Man-days: | 66
Carmen | Guadalupe | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: |  | Actual: | 55%
Carmen | Guadalupe | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 5%
Carmen | Guadalupe | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
Carmen | Guadalupe | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started: | 2020-01-02
Carmen | Guadalupe | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 101 - Jct. Highway Guadalupe - Bdry. Tagum |  | GENERAL FUND CY 2020 | Maintenance | 7.9 | km | CBRMC | Project Cost: | 231823.89 | Target Completion Date: |  | Program: | 231823.89 | Planned: |  | No. of Persons: |  | PO #2020031376 - LAMPIA PAG ASA IRRIGATORS ASS., INC.
Carmen | Guadalupe | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Maligro | Revised Completion Date: |  | Allotment: | 231823.89 | Revised: |  | No. of Man-days:
Carmen | Guadalupe | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Carmen | Guadalupe | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Carmen | Guadalupe | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: |  | Date completed:
Carmen | Guadalupe | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started:
B.E. Dujali | Tanglaw | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 104 - Dujali - Tanglaw |  | GENERAL FUND CY 2020 | Maintenance |  | km | MBA | Project Cost: | 135183.27 | Target Completion Date: | 2020-12-31 23:59 | Program: | 135183.27 | Planned: | 50% | No. of Persons: | 3 | On-going
B.E. Dujali | Tanglaw | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Gamad/Clar | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 135183.27 | Revised: |  | No. of Man-days: | 66
B.E. Dujali | Tanglaw | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: |  | Actual: | 52%
B.E. Dujali | Tanglaw | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 2%
B.E. Dujali | Tanglaw | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
B.E. Dujali | Tanglaw | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started: | 2020-01-02
B.E. Dujali | Tanglaw | 2nd Eng'g. Dist. | On-going | 2020-06-08 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 104 - Dujali - Tanglaw |  | GENERAL FUND CY 2020 | Maintenance |  | km | CBRMC | Project Cost: | 94178.48 | Target Completion Date: | 2020-12-12 | Program: | 94178.48 | Planned: | 5% | No. of Persons: | 2 | On-going
B.E. Dujali | Tanglaw | 2nd Eng'g. Dist. | On-going | 2020-06-08 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Maligro | Revised Completion Date: | 2021-01-08 | Allotment: | 94178.48 | Revised: |  | No. of Man-days: | 2
B.E. Dujali | Tanglaw | 2nd Eng'g. Dist. | On-going | 2020-06-08 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: | Dujali Poblacion Farmer's Irrigator's Association, Inc. | No. of days suspended: | 27 | Disbursement: |  | Actual: | 5%
B.E. Dujali | Tanglaw | 2nd Eng'g. Dist. | On-going | 2020-06-08 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: | 187 | No. of days extended: |  |  |  | Slippage: | 0%
B.E. Dujali | Tanglaw | 2nd Eng'g. Dist. | On-going | 2020-06-08 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
B.E. Dujali | Tanglaw | 2nd Eng'g. Dist. | On-going | 2020-06-08 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started: | 2020-06-08
B.E. Dujali | Dujali | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 105 - Poblacion Dujali - Prk. 8 Dujali |  | GENERAL FUND CY 2020 | Maintenance | 8.2 | km | MBA | Project Cost: | 329064 | Target Completion Date: | 2020-12-31 23:59 | Program: | 329064 | Planned: | 50% | No. of Persons: | 3 | On-going
B.E. Dujali | Dujali | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Gamad/Clar | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 329064 | Revised: |  | No. of Man-days: | 66
B.E. Dujali | Dujali | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: |  | Actual: | 56%
B.E. Dujali | Dujali | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 6%
B.E. Dujali | Dujali | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
B.E. Dujali | Dujali | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started: | 2020-01-02
B.E. Dujali | Dujali | 2nd Eng'g. Dist. | On-going | 2020-06-08 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 105 - Poblacion Dujali - Prk. 8 Dujali |  | GENERAL FUND CY 2020 | Maintenance | 8.2 | km | CBRMC | Project Cost: | 193371.11 | Target Completion Date: | 2020-12-12 | Program: | 193371.11 | Planned: | 5% | No. of Persons: | 2 | On-going
B.E. Dujali | Dujali | 2nd Eng'g. Dist. | On-going | 2020-06-08 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Maligro | Revised Completion Date: | 2021-01-08 | Allotment: | 193371.11 | Revised: |  | No. of Man-days: | 2
B.E. Dujali | Dujali | 2nd Eng'g. Dist. | On-going | 2020-06-08 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: | Dujali Poblacion Farmer's Irrigator's Association, Inc. | No. of days suspended: | 27 | Disbursement: |  | Actual: | 5%
B.E. Dujali | Dujali | 2nd Eng'g. Dist. | On-going | 2020-06-08 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: | 187 | No. of days extended: |  |  |  | Slippage: | 0%
B.E. Dujali | Dujali | 2nd Eng'g. Dist. | On-going | 2020-06-08 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
B.E. Dujali | Dujali | 2nd Eng'g. Dist. | On-going | 2020-06-08 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started: | 2020-06-08
B.E. Dujali | Dujali | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 107 - Dujali - San Isidro |  | GENERAL FUND CY 2020 | Maintenance | 3 | km | MBA | Project Cost: | 112652.73 | Target Completion Date: | 2020-12-31 23:59 | Program: | 112652.73 | Planned: | 50% | No. of Persons: | 3 | On-going
B.E. Dujali | Dujali | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Gamad/Clar | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 112652.73 | Revised: |  | No. of Man-days: | 66
B.E. Dujali | Dujali | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: |  | Actual: | 57%
B.E. Dujali | Dujali | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 7%
B.E. Dujali | Dujali | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
B.E. Dujali | Dujali | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started: | 2020-01-02
B.E. Dujali | Dujali | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 107 - Dujali - San Isidro |  | GENERAL FUND CY 2020 | Maintenance | 3 | km | CBRMC | Project Cost: | 78482.06 | Target Completion Date: |  | Program: | 78482.06 | Planned: |  | No. of Persons: |  | PO #2020031411 - SAN ISIDRO FARMERS IRRIGATORS ASSN., INC.
B.E. Dujali | Dujali | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Maligro | Revised Completion Date: |  | Allotment: | 78482.06 | Revised: |  | No. of Man-days:
B.E. Dujali | Dujali | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
B.E. Dujali | Dujali | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
B.E. Dujali | Dujali | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: |  | Date completed:
B.E. Dujali | Dujali | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started:
B.E. Dujali | New Casay | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 108 - New Casay - Bugtong Talisay |  | GENERAL FUND CY 2020 | Maintenance |  | km | MBA | Project Cost: | 74294.5 | Target Completion Date: | 2020-12-31 23:59 | Program: | 74294.5 | Planned: | 50% | No. of Persons: | 4 | On-going
B.E. Dujali | New Casay | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Gamad/Clar | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 74294.5 | Revised: |  | No. of Man-days: | 88
B.E. Dujali | New Casay | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: |  | Actual: | 50%
B.E. Dujali | New Casay | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0%
B.E. Dujali | New Casay | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
B.E. Dujali | New Casay | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started: | 2020-01-02
B.E. Dujali | New Casay | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 108 - New Casay - Bugtong Talisay |  | GENERAL FUND CY 2020 | Maintenance |  | km | CBRMC | Project Cost: | 64596.78 | Target Completion Date: |  | Program: | 64596.78 | Planned: |  | No. of Persons: |  | For re-bid
B.E. Dujali | New Casay | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Maligro | Revised Completion Date: |  | Allotment: | 64596.78 | Revised: |  | No. of Man-days:
B.E. Dujali | New Casay | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
B.E. Dujali | New Casay | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
B.E. Dujali | New Casay | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: |  | Date completed:
B.E. Dujali | New Casay | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started:
B.E. Dujali | Magupising | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 113 - Dujali - Balisong - Magupising |  | GENERAL FUND CY 2020 | Maintenance | 5.52 | km | MBA | Project Cost: | 235776.07 | Target Completion Date: | 2020-12-31 23:59 | Program: | 235776.07 | Planned: | 50% | No. of Persons: | 3 | On-going
B.E. Dujali | Magupising | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Gamad/Clar | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 235776.07 | Revised: |  | No. of Man-days: | 22
B.E. Dujali | Magupising | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: |  | Actual: | 55%
B.E. Dujali | Magupising | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 5%
B.E. Dujali | Magupising | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
B.E. Dujali | Magupising | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started: | 2020-01-02
B.E. Dujali | Magupising | 2nd Eng'g. Dist. | On-going | 2020-06-08 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 113 - Dujali - Balisong - Magupising |  | GENERAL FUND CY 2020 | Maintenance | 5.52 | km | CBRMC | Project Cost: | 115911.95 | Target Completion Date: | 2020-12-12 | Program: | 115911.95 | Planned: | 5% | No. of Persons: |  | On-going
B.E. Dujali | Magupising | 2nd Eng'g. Dist. | On-going | 2020-06-08 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Maligro | Revised Completion Date: | 2021-01-08 | Allotment: | 115911.95 | Revised: |  | No. of Man-days:
B.E. Dujali | Magupising | 2nd Eng'g. Dist. | On-going | 2020-06-08 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: | Dujali Poblacion Farmer's Irrigator's Association, Inc. | No. of days suspended: | 27 | Disbursement: |  | Actual: | 5%
B.E. Dujali | Magupising | 2nd Eng'g. Dist. | On-going | 2020-06-08 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: | 187 | No. of days extended: |  |  |  | Slippage: | 0%
B.E. Dujali | Magupising | 2nd Eng'g. Dist. | On-going | 2020-06-08 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
B.E. Dujali | Magupising | 2nd Eng'g. Dist. | On-going | 2020-06-08 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started: | 2020-06-08
B.E. Dujali | Dujali | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 117 - Dujali - Pawas - San Vicente |  | GENERAL FUND CY 2020 | Maintenance | 4.42 | km | MBA | Project Cost: | 141544.99 | Target Completion Date: | 2020-12-31 23:59 | Program: | 141544.99 | Planned: | 50% | No. of Persons: | 3 | On-going
B.E. Dujali | Dujali | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Gamad/Clar | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 141544.99 | Revised: |  | No. of Man-days: | 22
B.E. Dujali | Dujali | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: |  | Actual: | 50%
B.E. Dujali | Dujali | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0%
B.E. Dujali | Dujali | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
B.E. Dujali | Dujali | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started: | 2020-01-02
B.E. Dujali | Dujali | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 117 - Dujali - Pawas - San Vicente |  | GENERAL FUND CY 2020 | Maintenance | 4.42 | km | CBRMC | Project Cost: | 140060.27 | Target Completion Date: |  | Program: | 140060.27 | Planned: |  | No. of Persons: |  | Abstract #320201344 -For post qualification
B.E. Dujali | Dujali | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Maligro | Revised Completion Date: |  | Allotment: | 140060.27 | Revised: |  | No. of Man-days:
B.E. Dujali | Dujali | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
B.E. Dujali | Dujali | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
B.E. Dujali | Dujali | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: |  | Date completed:
B.E. Dujali | Dujali | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started:
Sto. Tomas | Salvacion | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 118- Jct. Salvacion - San Vicente - Cabay-angan |  | GENERAL FUND CY 2020 | Maintenance | 3.45 | km | MBA | Project Cost: | 168583.81 | Target Completion Date: | 2020-12-31 23:59 | Program: | 168583.81 | Planned: | 50% | No. of Persons: | 3 | On-going
Sto. Tomas | Salvacion | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Gamad/Clar | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 168583.81 | Revised: |  | No. of Man-days: | 60
Sto. Tomas | Salvacion | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: |  | Actual: | 55%
Sto. Tomas | Salvacion | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 5%
Sto. Tomas | Salvacion | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
Sto. Tomas | Salvacion | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started: | 2020-01-02
Sto. Tomas | Salvacion | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 118- Jct. Salvacion - San Vicente - Cabay-angan |  | GENERAL FUND CY 2020 | Maintenance | 3.45 | km | CBRMC | Project Cost: | 158775.23 | Target Completion Date: |  | Program: | 158775.23 | Planned: |  | No. of Persons: |  | Abstract #320201396 - For post qualification
Sto. Tomas | Salvacion | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Maligro | Revised Completion Date: |  | Allotment: | 158775.23 | Revised: |  | No. of Man-days:
Sto. Tomas | Salvacion | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Sto. Tomas | Salvacion | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Sto. Tomas | Salvacion | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: |  | Date completed:
Sto. Tomas | Salvacion | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started:
Sto. Tomas | Casig-ang | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 123- Bacali - Casig-ang - Libertad |  | GENERAL FUND CY 2020 | Maintenance |  | km | MBA | Project Cost: | 167836.14 | Target Completion Date: | 2020-12-31 23:59 | Program: | 167836.14 | Planned: | 50% | No. of Persons: | 3 | On-going
Sto. Tomas | Casig-ang | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Gamad/Clar | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 167836.14 | Revised: |  | No. of Man-days: | 60
Sto. Tomas | Casig-ang | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: |  | Actual: | 58%
Sto. Tomas | Casig-ang | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 8%
Sto. Tomas | Casig-ang | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
Sto. Tomas | Casig-ang | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started: | 2020-01-02
Sto. Tomas | Casig-ang | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 123- Bacali - Casig-ang - Libertad |  | GENERAL FUND CY 2020 | Maintenance |  | km | CBRMC | Project Cost: | 131608.37 | Target Completion Date: |  | Program: | 131608.37 | Planned: |  | No. of Persons: |  | Abstract #320201449 - For post qualification
Sto. Tomas | Casig-ang | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Maligro | Revised Completion Date: |  | Allotment: | 131608.37 | Revised: |  | No. of Man-days:
Sto. Tomas | Casig-ang | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Sto. Tomas | Casig-ang | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Sto. Tomas | Casig-ang | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: |  | Date completed:
Sto. Tomas | Casig-ang | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started:
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 124 - Kinamayan - Moslog - Mahayag |  | GENERAL FUND CY 2020 | Maintenance |  | km | MBA | Project Cost: | 114628.54 | Target Completion Date: | 2020-12-31 23:59 | Program: | 114628.54 | Planned: | 50% | No. of Persons: | 3 | On-going
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Gamad/Clar | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 114628.54 | Revised: |  | No. of Man-days: | 66
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: |  | Actual: | 50%
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0%
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started: | 2020-01-02
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 124 - Kinamayan - Moslog - Mahayag |  | GENERAL FUND CY 2020 | Maintenance |  | km | CBRMC | Project Cost: | 91159.92 | Target Completion Date: |  | Program: | 91159.92 | Planned: |  | No. of Persons: |  | For re-bid
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Maligro | Revised Completion Date: |  | Allotment: | 91159.92 | Revised: |  | No. of Man-days:
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: |  | Date completed:
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started:
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 126 - Kinamayan - Lunga-og |  | GENERAL FUND CY 2020 | Maintenance |  | km | MBA | Project Cost: | 100416.26 | Target Completion Date: | 2020-12-31 23:59 | Program: | 100416.26 | Planned: | 50% | No. of Persons: |  | On-going
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Gamad/Clar | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 100416.26 | Revised: |  | No. of Man-days:
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: |  | Actual: | 52%
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 2%
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started: | 2020-01-02
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | On-going | 2020-06-15 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 126 - Kinamayan - Lunga-og |  | GENERAL FUND CY 2020 | Maintenance |  | km | CBRMC | Project Cost: | 64596.78 | Target Completion Date: | 2020-12-15 23:59 | Program: | 64596.78 | Planned: | 5% | No. of Persons: | 1 | On-going
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | On-going | 2020-06-15 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Maligro | Revised Completion Date: |  | Allotment: | 64596.78 | Revised: |  | No. of Man-days: | 2
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | On-going | 2020-06-15 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: | Lunga-og Tribal Association | No. of days suspended: |  | Disbursement: |  | Actual: | 5%
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | On-going | 2020-06-15 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: | 184 | No. of days extended: |  |  |  | Slippage: | 0%
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | On-going | 2020-06-15 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | On-going | 2020-06-15 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started: | 2020-06-15
Sto. Tomas | La Libertad | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 128 - Prk. Apitong - Upper Balisong - Dalisay |  | GENERAL FUND CY 2020 | Maintenance | 4.6 | km | MBA | Project Cost: | 150598.24 | Target Completion Date: | 2020-12-31 23:59 | Program: | 150598.24 | Planned: | 10% | No. of Persons: | 3 | On-going
Sto. Tomas | La Libertad | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Gamad/Clar | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 150598.24 | Revised: |  | No. of Man-days: | 60
Sto. Tomas | La Libertad | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: |  | Actual: | 9%
Sto. Tomas | La Libertad | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | -1%
Sto. Tomas | La Libertad | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
Sto. Tomas | La Libertad | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started: | 2020-01-02
Sto. Tomas | La Libertad | 2nd Eng'g. Dist. | On-going | 2020-06-15 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 128 - Prk. Apitong - Upper Balisong - Dalisay |  | GENERAL FUND CY 2020 | Maintenance | 4.6 | km | CBRMC | Project Cost: | 142475.11 | Target Completion Date: | 2020-12-15 23:59 | Program: | 142475.11 | Planned: | 5% | No. of Persons: |  | On-going
Sto. Tomas | La Libertad | 2nd Eng'g. Dist. | On-going | 2020-06-15 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Maligro | Revised Completion Date: |  | Allotment: | 142475.11 | Revised: |  | No. of Man-days:
Sto. Tomas | La Libertad | 2nd Eng'g. Dist. | On-going | 2020-06-15 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: | Lunga-og Tribal Association | No. of days suspended: |  | Disbursement: |  | Actual: | 5%
Sto. Tomas | La Libertad | 2nd Eng'g. Dist. | On-going | 2020-06-15 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: | 184 | No. of days extended: |  |  |  | Slippage: | 0%
Sto. Tomas | La Libertad | 2nd Eng'g. Dist. | On-going | 2020-06-15 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
Sto. Tomas | La Libertad | 2nd Eng'g. Dist. | On-going | 2020-06-15 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started: | 2020-06-15
Sto. Tomas | Esperanza | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 130 - Los Amigos 1 - Esperanza - Los Amigos 2 |  | GENERAL FUND CY 2020 | Maintenance | 3.59 | km | MBA | Project Cost: | 97116.27 | Target Completion Date: | 2020-12-31 23:59 | Program: | 97116.27 | Planned: | 50% | No. of Persons: | 4 | On-going
Sto. Tomas | Esperanza | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Gamad/Clar | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 97116.27 | Revised: |  | No. of Man-days: | 88
Sto. Tomas | Esperanza | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: |  | Actual: | 55%
Sto. Tomas | Esperanza | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 5%
Sto. Tomas | Esperanza | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
Sto. Tomas | Esperanza | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started: | 2020-01-02
Sto. Tomas | Esperanza | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 130 - Los Amigos 1 - Esperanza - Los Amigos 2 |  | GENERAL FUND CY 2020 | Maintenance | 3.59 | km | CBRMC | Project Cost: | 131608.37 | Target Completion Date: |  | Program: | 131608.37 | Planned: |  | No. of Persons: |  | PO #2020031351 - LOS AMIGOS GROUP OF WOMEN & FARMERS ASSN.
Sto. Tomas | Esperanza | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Maligro | Revised Completion Date: |  | Allotment: | 131608.37 | Revised: |  | No. of Man-days:
Sto. Tomas | Esperanza | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Sto. Tomas | Esperanza | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Sto. Tomas | Esperanza | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: |  | Date completed:
Sto. Tomas | Esperanza | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started:
Sto. Tomas | Lunga-og | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 131 - Mugas - Lanatad |  | GENERAL FUND CY 2020 | Maintenance |  | km | MBA | Project Cost: | 65482.21 | Target Completion Date: | 2020-12-31 23:59 | Program: | 65482.21 | Planned: | 50% | No. of Persons: | 3 | On-going
Sto. Tomas | Lunga-og | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Gamad/Clar | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 65482.21 | Revised: |  | No. of Man-days: | 12
Sto. Tomas | Lunga-og | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: |  | Actual: | 50%
Sto. Tomas | Lunga-og | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0%
Sto. Tomas | Lunga-og | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
Sto. Tomas | Lunga-og | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started: | 2020-01-02
Sto. Tomas | Lunga-og | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 131 - Mugas - Lanatad |  | GENERAL FUND CY 2020 | Maintenance |  | km | CBRMC | Project Cost: | 31996.54 | Target Completion Date: |  | Program: | 31996.54 | Planned: |  | No. of Persons: |  | Purchase Order # 2020030961 (Katipunan Pantaron Irrigator's Association)
Sto. Tomas | Lunga-og | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Maligro | Revised Completion Date: |  | Allotment: | 31996.54 | Revised: |  | No. of Man-days:
Sto. Tomas | Lunga-og | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Sto. Tomas | Lunga-og | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Sto. Tomas | Lunga-og | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: |  | Date completed:
Sto. Tomas | Lunga-og | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started:
Sto. Tomas | Lunga-og | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 132 - Mugas - Lunga-og |  | GENERAL FUND CY 2020 | Maintenance | 2.68 | km | MBA | Project Cost: | 96490.97 | Target Completion Date: | 2020-12-31 23:59 | Program: | 96490.97 | Planned: | 50% | No. of Persons: | 3 | On-going
Sto. Tomas | Lunga-og | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Gamad/Clar | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 96490.97 | Revised: |  | No. of Man-days: | 20
Sto. Tomas | Lunga-og | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: |  | Actual: | 50%
Sto. Tomas | Lunga-og | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0%
Sto. Tomas | Lunga-og | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
Sto. Tomas | Lunga-og | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started: | 2020-01-02
Sto. Tomas | Lunga-og | 2nd Eng'g. Dist. | On-going | 2020-06-15 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 132 - Mugas - Lunga-og |  | GENERAL FUND CY 2020 | Maintenance | 2.68 | km | CBRMC | Project Cost: | 74256.11 | Target Completion Date: | 2020-12-15 23:59 | Program: | 74256.11 | Planned: |  | No. of Persons: | 5 | On-going
Sto. Tomas | Lunga-og | 2nd Eng'g. Dist. | On-going | 2020-06-15 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Maligro | Revised Completion Date: | 2021-01-11 23:59 | Allotment: | 74256.11 | Revised: |  | No. of Man-days: | 5
Sto. Tomas | Lunga-og | 2nd Eng'g. Dist. | On-going | 2020-06-15 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: | Lunga-og Tribal Association | No. of days suspended: | 27 | Disbursement: |  | Actual:
Sto. Tomas | Lunga-og | 2nd Eng'g. Dist. | On-going | 2020-06-15 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: | 184 | No. of days extended: |  |  |  | Slippage: | 0%
Sto. Tomas | Lunga-og | 2nd Eng'g. Dist. | On-going | 2020-06-15 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
Sto. Tomas | Lunga-og | 2nd Eng'g. Dist. | On-going | 2020-06-15 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started: | 2020-06-15
Sto. Tomas | New Katipunan | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 134 - New Katipunan - Pantaron |  | GENERAL FUND CY 2020 | Maintenance |  | km | MBA | Project Cost: | 71748.41 | Target Completion Date: | 2020-12-31 23:59 | Program: | 71748.41 | Planned: | 50% | No. of Persons: | 2 | On-going
Sto. Tomas | New Katipunan | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Gamad/Clar | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 71748.41 | Revised: |  | No. of Man-days: | 20
Sto. Tomas | New Katipunan | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: |  | Actual: | 51%
Sto. Tomas | New Katipunan | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 1%
Sto. Tomas | New Katipunan | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
Sto. Tomas | New Katipunan | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started: | 2020-01-02
Sto. Tomas | New Katipunan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 134 - New Katipunan - Pantaron |  | GENERAL FUND CY 2020 | Maintenance |  | km | CBRMC | Project Cost: | 53126.32 | Target Completion Date: |  | Program: | 53126.32 | Planned: |  | No. of Persons: |  | Purchase Order # 2020030964 (Katipunan Pantaron Irrigator's Association)
Sto. Tomas | New Katipunan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Maligro | Revised Completion Date: |  | Allotment: | 53126.32 | Revised: |  | No. of Man-days:
Sto. Tomas | New Katipunan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Sto. Tomas | New Katipunan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Sto. Tomas | New Katipunan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: |  | Date completed:
Sto. Tomas | New Katipunan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started:
Sto. Tomas | New Katipunan | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 135 - Sto. Tomas - Bdry. Mamacao |  | GENERAL FUND CY 2020 | Maintenance | 4.9 | km | MBA | Project Cost: | 195671.17 | Target Completion Date: | 2020-12-31 23:59 | Program: | 195671.17 | Planned: | 50% | No. of Persons: | 3 | On-going
Sto. Tomas | New Katipunan | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Gamad/Clar | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 195671.17 | Revised: |  | No. of Man-days: | 33
Sto. Tomas | New Katipunan | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: |  | Actual: | 52%
Sto. Tomas | New Katipunan | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 2%
Sto. Tomas | New Katipunan | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
Sto. Tomas | New Katipunan | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started: | 2020-01-02
Sto. Tomas | New Katipunan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 135 - Sto. Tomas - Bdry. Mamacao |  | GENERAL FUND CY 2020 | Maintenance | 4.9 | km | CBRMC | Project Cost: | 116515.66 | Target Completion Date: |  | Program: | 116515.66 | Planned: |  | No. of Persons: |  | PO #2020031353 - KATIPUNAN PANTARON IRRIGATORS ASSN.
Sto. Tomas | New Katipunan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Maligro | Revised Completion Date: |  | Allotment: | 116515.66 | Revised: |  | No. of Man-days:
Sto. Tomas | New Katipunan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Sto. Tomas | New Katipunan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Sto. Tomas | New Katipunan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: |  | Date completed:
Sto. Tomas | New Katipunan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started:
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 136 - Fd. Rd. 3 - San Jose |  | GENERAL FUND CY 2020 | Maintenance | 4.55 | km | MBA | Project Cost: | 176994.35 | Target Completion Date: | 2020-12-31 23:59 | Program: | 176994.35 | Planned: | 50% | No. of Persons: | 2 | On-going
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Gamad/Clar | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 176994.35 | Revised: |  | No. of Man-days: | 10
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: |  | Actual: | 55%
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 5%
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started: | 2020-01-02
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 136 - Fd. Rd. 3 - San Jose |  | GENERAL FUND CY 2020 | Maintenance | 4.55 | km | CBRMC | Project Cost: | 112893.42 | Target Completion Date: |  | Program: | 112893.42 | Planned: |  | No. of Persons: |  | Purchase Order # 2020030974 (Brgy. San Jose Upland Farmer's Assocaition)
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Maligro | Revised Completion Date: |  | Allotment: | 112893.42 | Revised: |  | No. of Man-days:
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: |  | Date completed:
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started:
Sto. Tomas | Bobongon | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 139 - Nafco - Bobongon |  | GENERAL FUND CY 2020 | Maintenance |  | km | MBA | Project Cost: | 89179.68 | Target Completion Date: | 2020-12-31 23:59 | Program: | 89179.68 | Planned: | 50% | No. of Persons: | 3 | On-going
Sto. Tomas | Bobongon | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Gamad/Clar | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 89179.68 | Revised: |  | No. of Man-days: | 56
Sto. Tomas | Bobongon | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: |  | Actual: | 55%
Sto. Tomas | Bobongon | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 5%
Sto. Tomas | Bobongon | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
Sto. Tomas | Bobongon | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started: | 2020-01-02
Sto. Tomas | Bobongon | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 139 - Nafco - Bobongon |  | GENERAL FUND CY 2020 | Maintenance |  | km | CBRMC | Project Cost: | 80293.17 | Target Completion Date: |  | Program: | 80293.17 | Planned: |  | No. of Persons: |  | Purchase Order # 2020030968 (Bobongon Rural Waterworks & Sanitation Association, Inc.)
Sto. Tomas | Bobongon | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Maligro | Revised Completion Date: |  | Allotment: | 80293.17 | Revised: |  | No. of Man-days:
Sto. Tomas | Bobongon | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Sto. Tomas | Bobongon | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Sto. Tomas | Bobongon | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: |  | Date completed:
Sto. Tomas | Bobongon | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started:
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 146 - Bdry. Tagum - Crossing Kinamayan Sto. Tomas |  | GENERAL FUND CY 2020 | Maintenance |  | km | MBA | Project Cost: | 790874.1 | Target Completion Date: | 2020-12-31 23:59 | Program: | 790874.1 | Planned: | 50% | No. of Persons: | 3 | On-going
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Gamad/Clar | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 790874.1 | Revised: |  | No. of Man-days: | 66
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: |  | Actual: | 50%
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0%
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started: | 2020-01-02
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 146 - Bdry. Tagum - Crossing Kinamayan Sto. Tomas |  | GENERAL FUND CY 2020 | Maintenance |  | km | CBRMC | Project Cost: | 429840.12 | Target Completion Date: |  | Program: | 429840.12 | Planned: |  | No. of Persons: |  | PO #2020031407 - LOS AMIGOS GROUP OF WOMEN & FARMERS ASSN.
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Maligro | Revised Completion Date: |  | Allotment: | 429840.12 | Revised: |  | No. of Man-days:
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: |  | Date completed:
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started:
Sto. Tomas | Magwawa | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 151 - San Jose - Sitio Mahayahay, Magwawa |  | GENERAL FUND CY 2020 | Maintenance | 0.84 | km | MBA | Project Cost: | 22943.54 | Target Completion Date: | 2020-12-31 23:59 | Program: | 22943.54 | Planned: | 50% | No. of Persons: | 3 | On-going
Sto. Tomas | Magwawa | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Gamad/Clar | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 22943.54 | Revised: |  | No. of Man-days: | 60
Sto. Tomas | Magwawa | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: |  | Actual: | 50%
Sto. Tomas | Magwawa | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0%
Sto. Tomas | Magwawa | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
Sto. Tomas | Magwawa | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started: | 2020-01-02
Sto. Tomas | Magwawa | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 151 - San Jose - Sitio Mahayahay, Magwawa |  | GENERAL FUND CY 2020 | Maintenance | 0.84 | km | CBRMC | Project Cost: | 30789.12 | Target Completion Date: |  | Program: | 30789.12 | Planned: |  | No. of Persons: |  | Purchase Order # 2020030972 (Brgy. San Jose Upland Farmer's Assocaition)
Sto. Tomas | Magwawa | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Maligro | Revised Completion Date: |  | Allotment: | 30789.12 | Revised: |  | No. of Man-days:
Sto. Tomas | Magwawa | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Sto. Tomas | Magwawa | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Sto. Tomas | Magwawa | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: |  | Date completed:
Sto. Tomas | Magwawa | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started:
Babak, IGCS | Cogon | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rural Electrification Project | Completion of Single Phase Line at Purok 6 and Purok 7, Brgy. Cogon, Babak Distirct, IGACOS |  | 20% DF CY 2020 | Electrificaton |  | km |  | Project Cost: | 1000000 | Target Completion Date: |  | Program: | 1000000 | Planned: |  | No. of Persons: |  | PR #20063965
Babak, IGCS | Cogon | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rural Electrification Project | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 1000000 | Revised: |  | No. of Man-days:
Babak, IGCS | Cogon | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rural Electrification Project | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Babak, IGCS | Cogon | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rural Electrification Project | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Babak, IGCS | Cogon | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rural Electrification Project | [7 empty] | Date Allotment Released: |  | Date completed:
Babak, IGCS | Cogon | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rural Electrification Project | [7 empty] | Date Started:
IGCS | Sta. Cruz | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rural Electrification Project | Completion of Single Phase Line at Purok Perlas, Brgy. Sta. Cruz, Talicud (Day Care Center), IGACOS |  | 20% DF CY 2020 | Electrificaton |  | km |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | POW preparation on-going c/o Engr. Kim Pao Lu
IGCS | Sta. Cruz | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rural Electrification Project | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
IGCS | Sta. Cruz | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rural Electrification Project | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
IGCS | Sta. Cruz | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rural Electrification Project | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
IGCS | Sta. Cruz | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rural Electrification Project | [7 empty] | Date Allotment Released: |  | Date completed:
IGCS | Sta. Cruz | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rural Electrification Project | [7 empty] | Date Started:
Sto. Tomas | San Jose | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | ROAD ID 008 - Fr. Rd. 3 - San Jose |  | 20% DF CY 2020 | Rehabilitation |  | km |  | Project Cost: | 8000000 | Target Completion Date: |  | Program: | 8000000 | Planned: |  | No. of Persons: |  | Plan On-going
Sto. Tomas | San Jose | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 8000000 | Revised: |  | No. of Man-days:
Sto. Tomas | San Jose | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Sto. Tomas | San Jose | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Sto. Tomas | San Jose | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Date Allotment Released: |  | Date completed:
Sto. Tomas | San Jose | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Date Started:
Carmen | Asuncion | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | ROAD ID 007 - Lower Asuncion - Upper Asuncion |  | 20% DF CY 2020 | Rehabilitation |  | km |  | Project Cost: | 1302000 | Target Completion Date: |  | Program: | 1302000 | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No
Carmen | Asuncion | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 1302000 | Revised: |  | No. of Man-days:
Carmen | Asuncion | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Carmen | Asuncion | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Carmen | Asuncion | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Date Allotment Released: |  | Date completed:
Carmen | Asuncion | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Date Started:
Carmen | Mangalcal | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | ROAD ID 030 - Jct. Highway - Carmen - Mangalcal - Tubod |  | 20% DF CY 2020 | Rehabilitation |  | km |  | Project Cost: | 1323000 | Target Completion Date: |  | Program: | 1323000 | Planned: |  | No. of Persons: |  | Plan On-going
Carmen | Mangalcal | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 1323000 | Revised: |  | No. of Man-days:
Carmen | Mangalcal | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Carmen | Mangalcal | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Carmen | Mangalcal | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Date Allotment Released: |  | Date completed:
Carmen | Mangalcal | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Date Started:
Carmen | Tuganay | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | ROAD ID 031 - Tuganay - Taba |  | 20% DF CY 2020 | Rehabilitation |  | km |  | Project Cost: | 1431000 | Target Completion Date: |  | Program: | 1431000 | Planned: |  | No. of Persons: |  | Plan On-going
Carmen | Tuganay | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 1431000 | Revised: |  | No. of Man-days:
Carmen | Tuganay | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Carmen | Tuganay | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Carmen | Tuganay | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Date Allotment Released: |  | Date completed:
Carmen | Tuganay | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Date Started:
Carmen | Ising | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | ROAD ID 069 - Jct. Highway - Ising - Magsaysay |  | 20% DF CY 2020 | Rehabilitation |  | km |  | Project Cost: | 6000000 | Target Completion Date: |  | Program: | 6000000 | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No
Carmen | Ising | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 6000000 | Revised: |  | No. of Man-days:
Carmen | Ising | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Carmen | Ising | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Carmen | Ising | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Date Allotment Released: |  | Date completed:
Carmen | Ising | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Date Started:
Carmen | Guadalupe | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | Jct. Highway - Guadalupe - Bdry. Tagum |  | 20% DF CY 2020 | Rehabilitation |  | km |  | Project Cost: | 910000 | Target Completion Date: |  | Program: | 910000 | Planned: |  | No. of Persons: |  | Plan On-going
Carmen | Guadalupe | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 910000 | Revised: |  | No. of Man-days:
Carmen | Guadalupe | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Carmen | Guadalupe | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Carmen | Guadalupe | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Date Allotment Released: |  | Date completed:
Carmen | Guadalupe | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Date Started:
Carmen | Tibulao | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | Sitio Malaga - Tibulao |  | 20% DF CY 2020 | Rehabilitation |  | km |  | Project Cost: | 350000 | Target Completion Date: |  | Program: | 350000 | Planned: |  | No. of Persons: |  | Plan On-going
Carmen | Tibulao | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 350000 | Revised: |  | No. of Man-days:
Carmen | Tibulao | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Carmen | Tibulao | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Carmen | Tibulao | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Date Allotment Released: |  | Date completed:
Carmen | Tibulao | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Date Started:
Carmen | New Casay | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | Prk. 5 RJS - Prk. 6 New Casay |  | 20% DF CY 2020 | Rehabilitation |  | km |  | Project Cost: | 350000 | Target Completion Date: |  | Program: | 350000 | Planned: |  | No. of Persons: |  | Plan On-going
Carmen | New Casay | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 350000 | Revised: |  | No. of Man-days:
Carmen | New Casay | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Carmen | New Casay | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Carmen | New Casay | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Date Allotment Released: |  | Date completed:
Carmen | New Casay | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Date Started:
B.E. Dujali | Pawas | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | Dujali - Pawas - San Vicente |  | 20% DF CY 2020 | Rehabilitation |  | km |  | Project Cost: | 350000 | Target Completion Date: |  | Program: | 350000 | Planned: |  | No. of Persons: |  | Plan On-going
B.E. Dujali | Pawas | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 350000 | Revised: |  | No. of Man-days:
B.E. Dujali | Pawas | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
B.E. Dujali | Pawas | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
B.E. Dujali | Pawas | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Date Allotment Released: |  | Date completed:
B.E. Dujali | Pawas | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Date Started:
Sto. Tomas | Esperanza | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | Los Amigos 1 - Esperanza - Los Amigos 2 |  | 20% DF CY 2020 | Rehabilitation |  | km |  | Project Cost: | 350000 | Target Completion Date: |  | Program: | 350000 | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No
Sto. Tomas | Esperanza | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 350000 | Revised: |  | No. of Man-days:
Sto. Tomas | Esperanza | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Sto. Tomas | Esperanza | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Sto. Tomas | Esperanza | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Date Allotment Released: |  | Date completed:
Sto. Tomas | Esperanza | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Date Started:
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | San Miguel - Crossing Kinamayan |  | 20% DF CY 2020 | Rehabilitation |  | km |  | Project Cost: | 19200000 | Target Completion Date: |  | Program: | 19200000 | Planned: |  | No. of Persons: |  | Plan On-going
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 19200000 | Revised: |  | No. of Man-days:
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Date Allotment Released: |  | Date completed:
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Date Started:
Sto. Tomas | Magwawa | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | Fd. Rd. 2 - Sto. Tomas - Magwawa |  | 20% DF CY 2020 | Rehabilitation |  | km |  | Project Cost: | 350000 | Target Completion Date: |  | Program: | 350000 | Planned: |  | No. of Persons: |  | Plan On-going
Sto. Tomas | Magwawa | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 350000 | Revised: |  | No. of Man-days:
Sto. Tomas | Magwawa | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Sto. Tomas | Magwawa | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Sto. Tomas | Magwawa | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Date Allotment Released: |  | Date completed:
Sto. Tomas | Magwawa | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Date Started:
Sto. Tomas | Balagunan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | Menzi - Balagunan - Tulalian |  | 20% DF CY 2020 | Rehabilitation |  | km |  | Project Cost: | 3720500 | Target Completion Date: |  | Program: | 3720500 | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No
Sto. Tomas | Balagunan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 3720500 | Revised: |  | No. of Man-days:
Sto. Tomas | Balagunan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Sto. Tomas | Balagunan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Sto. Tomas | Balagunan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Date Allotment Released: |  | Date completed:
Sto. Tomas | Balagunan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Date Started:
B.E. Dujali | Magupising | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | Jct,. Bdry. Tagum- Talomo |  | 20% DF CY 2020 | Rehabilitation |  | km |  | Project Cost: | 3720500 | Target Completion Date: |  | Program: | 3720500 | Planned: |  | No. of Persons: |  | POW for approval with the Governor
B.E. Dujali | Magupising | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 3720500 | Revised: |  | No. of Man-days:
B.E. Dujali | Magupising | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
B.E. Dujali | Magupising | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
B.E. Dujali | Magupising | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Date Allotment Released: |  | Date completed:
B.E. Dujali | Magupising | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Date Started:
IGCS | AI | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Various Local Roads & Drainage Dev't. Project | Rehab. Of Various Local Roads @ Island Garden City of Samal |  | 20% DF CY 2020 | Rehabilitation |  | km |  | Project Cost: | 2518182 | Target Completion Date: |  | Program: | 2518182 | Planned: |  | No. of Persons: |  | Plan On-going
IGCS | AI | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Various Local Roads & Drainage Dev't. Project | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 2518182 | Revised: |  | No. of Man-days:
IGCS | AI | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Various Local Roads & Drainage Dev't. Project | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
IGCS | AI | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Various Local Roads & Drainage Dev't. Project | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
IGCS | AI | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Various Local Roads & Drainage Dev't. Project | [7 empty] | Date Allotment Released: |  | Date completed:
IGCS | AI | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Various Local Roads & Drainage Dev't. Project | [7 empty] | Date Started:
Panabo City | APC | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Various Local Roads & Drainage Dev't. Project | Rehab. Of Various Local Roads @ Panabo City |  | 20% DF CY 2020 | Rehabilitation |  | km |  | Project Cost: | 2518182 | Target Completion Date: |  | Program: | 2518182 | Planned: |  | No. of Persons: |  | Abstract # 0420201633 - Billboard; Abstract 0520201661 - hardware
Panabo City | APC | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Various Local Roads & Drainage Dev't. Project | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 2518182 | Revised: |  | No. of Man-days:
Panabo City | APC | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Various Local Roads & Drainage Dev't. Project | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Panabo City | APC | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Various Local Roads & Drainage Dev't. Project | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Panabo City | APC | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Various Local Roads & Drainage Dev't. Project | [7 empty] | Date Allotment Released: |  | Date completed:
Panabo City | APC | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Various Local Roads & Drainage Dev't. Project | [7 empty] | Date Started:
B.E. Dujali | ABD | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Various Local Roads & Drainage Dev't. Project | Rehab. Of Various Local Roads @ B.E Dujali |  | 20% DF CY 2020 | Rehabilitation |  | km |  | Project Cost: | 2518182 | Target Completion Date: |  | Program: | 2518182 | Planned: |  | No. of Persons: |  | Purchase Request # 20053256 - Hardware; PR # 20053255 - Billboard
B.E. Dujali | ABD | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Various Local Roads & Drainage Dev't. Project | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 2518182 | Revised: |  | No. of Man-days:
B.E. Dujali | ABD | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Various Local Roads & Drainage Dev't. Project | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
B.E. Dujali | ABD | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Various Local Roads & Drainage Dev't. Project | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
B.E. Dujali | ABD | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Various Local Roads & Drainage Dev't. Project | [7 empty] | Date Allotment Released: |  | Date completed:
B.E. Dujali | ABD | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Various Local Roads & Drainage Dev't. Project | [7 empty] | Date Started:
Carmen | AC | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Various Local Roads & Drainage Dev't. Project | Rehab. Of Various Local Roads @ Carmen |  | 20% DF CY 2020 | Rehabilitation |  | km |  | Project Cost: | 2518182 | Target Completion Date: |  | Program: | 2518182 | Planned: |  | No. of Persons: |  | Abstract # 0420201633 - Billboard; Abstract 0520201661 - hardware
Carmen | AC | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Various Local Roads & Drainage Dev't. Project | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 2518182 | Revised: |  | No. of Man-days:
Carmen | AC | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Various Local Roads & Drainage Dev't. Project | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Carmen | AC | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Various Local Roads & Drainage Dev't. Project | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Carmen | AC | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Various Local Roads & Drainage Dev't. Project | [7 empty] | Date Allotment Released: |  | Date completed:
Carmen | AC | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Various Local Roads & Drainage Dev't. Project | [7 empty] | Date Started:
Sto. Tomas | AST | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Various Local Roads & Drainage Dev't. Project | Rehab. Of Various Local Roads @ Sto. Tomas |  | 20% DF CY 2020 | Rehabilitation |  | km |  | Project Cost: | 2518182 | Target Completion Date: |  | Program: | 2518182 | Planned: |  | No. of Persons: |  | Plan On-going
Sto. Tomas | AST | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Various Local Roads & Drainage Dev't. Project | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 2518182 | Revised: |  | No. of Man-days:
Sto. Tomas | AST | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Various Local Roads & Drainage Dev't. Project | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Sto. Tomas | AST | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Various Local Roads & Drainage Dev't. Project | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Sto. Tomas | AST | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Various Local Roads & Drainage Dev't. Project | [7 empty] | Date Allotment Released: |  | Date completed:
Sto. Tomas | AST | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Various Local Roads & Drainage Dev't. Project | [7 empty] | Date Started:
Babak, IGCS | AB | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Various Government Buildings and Facilities Development Project | Construction of Commercial Building at Kinawitnon, IGACOS, Babak |  | 20% DF CY 2020 | Building |  | sq.m |  | Project Cost: | 2000000 | Target Completion Date: |  | Program: | 2000000 | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
Babak, IGCS | AB | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Various Government Buildings and Facilities Development Project | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 2000000 | Revised: |  | No. of Man-days:
Babak, IGCS | AB | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Various Government Buildings and Facilities Development Project | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Babak, IGCS | AB | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Various Government Buildings and Facilities Development Project | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Babak, IGCS | AB | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Various Government Buildings and Facilities Development Project | [7 empty] | Date Allotment Released: |  | Date completed:
Babak, IGCS | AB | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Various Government Buildings and Facilities Development Project | [7 empty] | Date Started:
Carmen | Ising | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Various Government Buildings and Facilities Development Project | Improvement of Provincial Engineer's Office 2nd District Office Phase 2, Carmen |  | 20% DF CY 2020 | Building |  | sq.m |  | Project Cost: | 1590000 | Target Completion Date: |  | Program: | 1590000 | Planned: |  | No. of Persons: |  | Plan and DED On-going
Carmen | Ising | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Various Government Buildings and Facilities Development Project | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 1590000 | Revised: |  | No. of Man-days:
Carmen | Ising | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Various Government Buildings and Facilities Development Project | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Carmen | Ising | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Various Government Buildings and Facilities Development Project | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Carmen | Ising | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Various Government Buildings and Facilities Development Project | [7 empty] | Date Allotment Released: |  | Date completed:
Carmen | Ising | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Various Government Buildings and Facilities Development Project | [7 empty] | Date Started:
B.E. Dujali | Ising | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Various Government Buildings and Facilities Development Project | Construction of DDN hospital Carmen Zone Annex Building Phase 3, Carmen |  | GENERAL FUND CY 2020 | Building |  | sq.m |  | Project Cost: | 800000 | Target Completion Date: |  | Program: | 800000 | Planned: |  | No. of Persons: |  | Abstract #0420201476
B.E. Dujali | Ising | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Various Government Buildings and Facilities Development Project | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 800000 | Revised: |  | No. of Man-days:
B.E. Dujali | Ising | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Various Government Buildings and Facilities Development Project | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
B.E. Dujali | Ising | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Various Government Buildings and Facilities Development Project | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
B.E. Dujali | Ising | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Various Government Buildings and Facilities Development Project | [7 empty] | Date Allotment Released: |  | Date completed:
B.E. Dujali | Ising | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Various Government Buildings and Facilities Development Project | [7 empty] | Date Started:
B.E. Dujali | Dujali | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Various Government Buildings and Facilities Development Project | Construction of Municipal Triball Hall, B.E. Dujali |  | GENERAL FUND CY 2020 | Building |  | sq.m |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
B.E. Dujali | Dujali | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Various Government Buildings and Facilities Development Project | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
B.E. Dujali | Dujali | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Various Government Buildings and Facilities Development Project | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
B.E. Dujali | Dujali | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Various Government Buildings and Facilities Development Project | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
B.E. Dujali | Dujali | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Various Government Buildings and Facilities Development Project | [7 empty] | Date Allotment Released: |  | Date completed:
B.E. Dujali | Dujali | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Various Government Buildings and Facilities Development Project | [7 empty] | Date Started:
Sto. Tomas | Tibal-og | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Various Government Buildings and Facilities Development Project | Construction of Municipal Triball Hall, Sto. Tomas |  | GENERAL FUND CY 2020 | Building |  | sq.m | Admin | Project Cost: | 500000 | Target Completion Date: | 2019-07-31 | Program: | 500000 | Planned: | 100% | No. of Persons: | 7 | Suspended June 28, 2019. Waiting for the delivery of JO Materials
Sto. Tomas | Tibal-og | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Various Government Buildings and Facilities Development Project | [7 empty] | Project Engineer: | Roque | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days: | 110
Sto. Tomas | Tibal-og | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Various Government Buildings and Facilities Development Project | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: | 85%
Sto. Tomas | Tibal-og | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Various Government Buildings and Facilities Development Project | [7 empty] | Duration: | 70 | No. of days extended: |  |  |  | Slippage: | -15%
Sto. Tomas | Tibal-og | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Various Government Buildings and Facilities Development Project | [7 empty] | Date Allotment Released: | CY 2018 | Date completed:
Sto. Tomas | Tibal-og | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Various Government Buildings and Facilities Development Project | [7 empty] | Date Started: | 2019-05-22
Sto. Tomas | Tulalian | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Various Government Buildings and Facilities Development Project | Construction of Fence at Tulalian National High School, Tulalian, Sto. Tomas |  | GENERAL FUND CY 2020 | Fence |  | sq.m |  | Project Cost: | 1500000 | Target Completion Date: |  | Program: | 1500000 | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
Sto. Tomas | Tulalian | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Various Government Buildings and Facilities Development Project | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 1500000 | Revised: |  | No. of Man-days:
Sto. Tomas | Tulalian | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Various Government Buildings and Facilities Development Project | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Sto. Tomas | Tulalian | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Various Government Buildings and Facilities Development Project | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Sto. Tomas | Tulalian | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Various Government Buildings and Facilities Development Project | [7 empty] | Date Allotment Released: |  | Date completed:
Sto. Tomas | Tulalian | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Various Government Buildings and Facilities Development Project | [7 empty] | Date Started:
Carmen | Tibulao | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Various Government Buildings and Facilities Development Project | Construction of Two(2) Classroom at Tibulao Elem. School, Tibulao, Carmen |  | GENERAL FUND CY 2020 | Building |  | sq.m |  | Project Cost: | 2900000 | Target Completion Date: |  | Program: | 2900000 | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
Carmen | Tibulao | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Various Government Buildings and Facilities Development Project | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 2900000 | Revised: |  | No. of Man-days:
Carmen | Tibulao | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Various Government Buildings and Facilities Development Project | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Carmen | Tibulao | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Various Government Buildings and Facilities Development Project | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Carmen | Tibulao | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Various Government Buildings and Facilities Development Project | [7 empty] | Date Allotment Released: |  | Date completed:
Carmen | Tibulao | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Various Government Buildings and Facilities Development Project | [7 empty] | Date Started:
Carmen |  | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Desiltation/Excavation of Rivers & Creeks | Improvement and Desiltation of Camoning Creek |  | 5% Calamity Fund CY 2020 | Desiltation |  | ln.m |  | Project Cost: | 2500000 | Target Completion Date: |  | Program: | 2500000 | Planned: |  | No. of Persons: |  | Abstract # 0520201658
Carmen |  | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Desiltation/Excavation of Rivers & Creeks | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 2500000 | Revised: |  | No. of Man-days:
Carmen |  | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Desiltation/Excavation of Rivers & Creeks | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Carmen |  | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Desiltation/Excavation of Rivers & Creeks | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Carmen |  | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Desiltation/Excavation of Rivers & Creeks | [7 empty] | Date Allotment Released: |  | Date completed:
Carmen |  | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Desiltation/Excavation of Rivers & Creeks | [7 empty] | Date Started:
Carmen | Ising | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Desiltation/Excavation of Rivers & Creeks | Improvement and Desiltation of Ising Creek |  | 5% Calamity Fund CY 2020 | Desiltation |  | ln.m |  | Project Cost: | 2000000 | Target Completion Date: |  | Program: | 2000000 | Planned: |  | No. of Persons: |  | Abstract # 0420201637; 0520201662
Carmen | Ising | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Desiltation/Excavation of Rivers & Creeks | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 2000000 | Revised: |  | No. of Man-days:
Carmen | Ising | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Desiltation/Excavation of Rivers & Creeks | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Carmen | Ising | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Desiltation/Excavation of Rivers & Creeks | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Carmen | Ising | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Desiltation/Excavation of Rivers & Creeks | [7 empty] | Date Allotment Released: |  | Date completed:
Carmen | Ising | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Desiltation/Excavation of Rivers & Creeks | [7 empty] | Date Started:
Carmen | Anibongan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Desiltation/Excavation of Rivers & Creeks | Desiltation of Buhang Creek, Anibongan, Carmen |  | 5% Calamity Fund CY 2020 | Desiltation |  | ln.m |  | Project Cost: | 2130206 | Target Completion Date: |  | Program: | 2130206 | Planned: |  | No. of Persons: |  | Abstract # 0520201657; 0420201626
Carmen | Anibongan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Desiltation/Excavation of Rivers & Creeks | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 2130206 | Revised: |  | No. of Man-days:
Carmen | Anibongan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Desiltation/Excavation of Rivers & Creeks | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Carmen | Anibongan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Desiltation/Excavation of Rivers & Creeks | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Carmen | Anibongan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Desiltation/Excavation of Rivers & Creeks | [7 empty] | Date Allotment Released: |  | Date completed:
Carmen | Anibongan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Desiltation/Excavation of Rivers & Creeks | [7 empty] | Date Started:
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Revetment of Dike and Slope Protection | Rehab./Impv't. of San Miguel - Moslog - Kinamayan, Sto. Tomas |  | 5% Calamity Fund CY 2020 | Rehabilitation |  | ln.m |  | Project Cost: | 1000000 | Target Completion Date: |  | Program: | 1000000 | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Revetment of Dike and Slope Protection | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 1000000 | Revised: |  | No. of Man-days:
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Revetment of Dike and Slope Protection | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Revetment of Dike and Slope Protection | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Revetment of Dike and Slope Protection | [7 empty] | Date Allotment Released: |  | Date completed:
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Revetment of Dike and Slope Protection | [7 empty] | Date Started:
Carmen | Mangalcal | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Improvement of Roads, Drainage and Canal | Improvement of Mangalcal to Diamond Creek Farm to Market Road Opening |  | 5% Calamity Fund CY 2020 | Improvement |  | ln.m |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
Carmen | Mangalcal | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Improvement of Roads, Drainage and Canal | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Carmen | Mangalcal | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Improvement of Roads, Drainage and Canal | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Carmen | Mangalcal | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Improvement of Roads, Drainage and Canal | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Carmen | Mangalcal | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Improvement of Roads, Drainage and Canal | [7 empty] | Date Allotment Released: |  | Date completed:
Carmen | Mangalcal | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Improvement of Roads, Drainage and Canal | [7 empty] | Date Started:
Carmen | Mabaus | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Improvement of Roads, Drainage and Canal | Improvement of Mabaus - Salvacion Provincial Road Continuing Road Opening |  | 5% Calamity Fund CY 2020 | Improvement |  | ln.m |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Plan On-going
Carmen | Mabaus | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Improvement of Roads, Drainage and Canal | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Carmen | Mabaus | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Improvement of Roads, Drainage and Canal | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Carmen | Mabaus | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Improvement of Roads, Drainage and Canal | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Carmen | Mabaus | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Improvement of Roads, Drainage and Canal | [7 empty] | Date Allotment Released: |  | Date completed:
Carmen | Mabaus | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Improvement of Roads, Drainage and Canal | [7 empty] | Date Started:
Carmen | Mangalcal | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Improvement of Bridges and Cross Drainage | Single Barrel Box Culvert at Mangalcal-Diamond Creek, Brgy. Mangalcal, Carmen |  | 5% Calamity Fund CY 2020 | Box Culvert |  | ln.m |  | Project Cost: | 2000000 | Target Completion Date: |  | Program: | 2000000 | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
Carmen | Mangalcal | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Improvement of Bridges and Cross Drainage | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 2000000 | Revised: |  | No. of Man-days:
Carmen | Mangalcal | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Improvement of Bridges and Cross Drainage | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Carmen | Mangalcal | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Improvement of Bridges and Cross Drainage | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Carmen | Mangalcal | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Improvement of Bridges and Cross Drainage | [7 empty] | Date Allotment Released: |  | Date completed:
Carmen | Mangalcal | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Improvement of Bridges and Cross Drainage | [7 empty] | Date Started:
Sto. Tomas | Magwawa | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. | Const. of 1 Classroom @ Mangga ES, Magwawa, Sto. Tomas |  | SEF-AB CY 2020 | Building |  | sq.m |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | For preparation of POW and Plans
Sto. Tomas | Magwawa | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Sto. Tomas | Magwawa | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Sto. Tomas | Magwawa | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Sto. Tomas | Magwawa | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. | [7 empty] | Date Allotment Released: |  | Date completed:
Sto. Tomas | Magwawa | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. | [7 empty] | Date Started:
Panabo City | J.P. Laurel | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | Const. of Day Care Center, JP Laurel, Panabo City |  | AB CY 2020 | Building |  | sq.m |  | Project Cost: | 1000000 | Target Completion Date: |  | Program: | 1000000 | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
Panabo City | J.P. Laurel | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 1000000 | Revised: |  | No. of Man-days:
Panabo City | J.P. Laurel | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Panabo City | J.P. Laurel | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Panabo City | J.P. Laurel | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | [7 empty] | Date Allotment Released: |  | Date completed:
Panabo City | J.P. Laurel | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | [7 empty] | Date Started:
B.E. Dujali | Dujali | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | Const. of Day Care Center, Dujali, B.E. Dujali |  | AB CY 2020 | Building |  | sq.m |  | Project Cost: | 1000000 | Target Completion Date: |  | Program: | 1000000 | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
B.E. Dujali | Dujali | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 1000000 | Revised: |  | No. of Man-days:
B.E. Dujali | Dujali | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
B.E. Dujali | Dujali | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
B.E. Dujali | Dujali | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | [7 empty] | Date Allotment Released: |  | Date completed:
B.E. Dujali | Dujali | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | [7 empty] | Date Started:
Sto. Tomas | Tibal-og | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | Const. of Day Care Center, Tibal-og, Sto Tomas |  | AB CY 2020 | Building |  | sq.m |  | Project Cost: | 1000000 | Target Completion Date: |  | Program: | 1000000 | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
Sto. Tomas | Tibal-og | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 1000000 | Revised: |  | No. of Man-days:
Sto. Tomas | Tibal-og | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Sto. Tomas | Tibal-og | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Sto. Tomas | Tibal-og | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | [7 empty] | Date Allotment Released: |  | Date completed:
Sto. Tomas | Tibal-og | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | [7 empty] | Date Started:
B.E. Dujali | Cabay-angan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | Compl./Rep. Day Care Center, Cabay-angan, B.E. Dujali |  | AB CY 2020 | Building |  | sq.m |  | Project Cost: | 300000 | Target Completion Date: |  | Program: | 300000 | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
B.E. Dujali | Cabay-angan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 300000 | Revised: |  | No. of Man-days:
B.E. Dujali | Cabay-angan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
B.E. Dujali | Cabay-angan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
B.E. Dujali | Cabay-angan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | [7 empty] | Date Allotment Released: |  | Date completed:
B.E. Dujali | Cabay-angan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | [7 empty] | Date Started:
B.E. Dujali | Tanglaw | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | Compl./Rep. Day Care Center, Tanglaw, B.E. Dujali |  | AB CY 2020 | Building |  | sq.m |  | Project Cost: | 300000 | Target Completion Date: |  | Program: | 300000 | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
B.E. Dujali | Tanglaw | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 300000 | Revised: |  | No. of Man-days:
B.E. Dujali | Tanglaw | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
B.E. Dujali | Tanglaw | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
B.E. Dujali | Tanglaw | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | [7 empty] | Date Allotment Released: |  | Date completed:
B.E. Dujali | Tanglaw | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | [7 empty] | Date Started:
Carmen | Salvacion | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | Compl./Rep. Day Care Center, Salvacion, Carmen |  | AB CY 2020 | Building |  | sq.m |  | Project Cost: | 300000 | Target Completion Date: |  | Program: | 300000 | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
Carmen | Salvacion | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 300000 | Revised: |  | No. of Man-days:
Carmen | Salvacion | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Carmen | Salvacion | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Carmen | Salvacion | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | [7 empty] | Date Allotment Released: |  | Date completed:
Carmen | Salvacion | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | [7 empty] | Date Started:
IGCS | San Agustin | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | Compl./Rep. Day Care Center, San Agustin, IGCS |  | AB CY 2020 | Building |  | sq.m |  | Project Cost: | 300000 | Target Completion Date: |  | Program: | 300000 | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
IGCS | San Agustin | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 300000 | Revised: |  | No. of Man-days:
IGCS | San Agustin | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
IGCS | San Agustin | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
IGCS | San Agustin | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | [7 empty] | Date Allotment Released: |  | Date completed:
IGCS | San Agustin | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | [7 empty] | Date Started:
IGCS | Toril | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | Compl./Rep. Day Care Center, Toril, IGCS |  | AB CY 2020 | Building |  | sq.m |  | Project Cost: | 300000 | Target Completion Date: |  | Program: | 300000 | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
IGCS | Toril | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 300000 | Revised: |  | No. of Man-days:
IGCS | Toril | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
IGCS | Toril | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
IGCS | Toril | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | [7 empty] | Date Allotment Released: |  | Date completed:
IGCS | Toril | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | [7 empty] | Date Started:
Sto. Tomas | Tibal-og | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | Compl./Rep. Day Care Center, Tibal-og, Sto. Tomas |  | AB CY 2020 | Building |  | sq.m |  | Project Cost: | 600000 | Target Completion Date: |  | Program: | 600000 | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
Sto. Tomas | Tibal-og | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 600000 | Revised: |  | No. of Man-days:
Sto. Tomas | Tibal-og | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Sto. Tomas | Tibal-og | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Sto. Tomas | Tibal-og | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | [7 empty] | Date Allotment Released: |  | Date completed:
Sto. Tomas | Tibal-og | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | [7 empty] | Date Started:
Sto. Tomas | Talomo | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | Compl./Rep. Day Care Center, Talomo, Sto. Tomas |  | AB CY 2020 | Building |  | sq.m |  | Project Cost: | 300000 | Target Completion Date: |  | Program: | 300000 | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
Sto. Tomas | Talomo | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 300000 | Revised: |  | No. of Man-days:
Sto. Tomas | Talomo | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Sto. Tomas | Talomo | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Sto. Tomas | Talomo | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | [7 empty] | Date Allotment Released: |  | Date completed:
Sto. Tomas | Talomo | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | [7 empty] | Date Started:
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | Compl./Rep. Day Care Center, Kinamayan, Sto. Tomas |  | AB CY 2020 | Building |  | sq.m |  | Project Cost: | 300000 | Target Completion Date: |  | Program: | 300000 | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 300000 | Revised: |  | No. of Man-days:
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | [7 empty] | Date Allotment Released: |  | Date completed:
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | [7 empty] | Date Started:
Sto. Tomas | La Libertad | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | Compl./Rep. Day Care Center, La Libertad, Sto. Tomas |  | AB CY 2020 | Building |  | sq.m |  | Project Cost: | 300000 | Target Completion Date: |  | Program: | 300000 | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
Sto. Tomas | La Libertad | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 300000 | Revised: |  | No. of Man-days:
Sto. Tomas | La Libertad | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Sto. Tomas | La Libertad | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Sto. Tomas | La Libertad | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | [7 empty] | Date Allotment Released: |  | Date completed:
Sto. Tomas | La Libertad | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | [7 empty] | Date Started:
Carmen | Ising | 2nd Eng'g. Dist. | On-going | 2020-05-11 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | BAYANIHAN | Impv't of Hospital Facilities (Isolation/ICU Room) Carmen District Hospital |  | TF CY 2020 | Building |  | sq.m | Admin | Project Cost: | 3000000 | Target Completion Date: | 2020-08-09 | Program: | 3000000 | Planned: | 30.21% | No. of Persons: | 8 | On-going
Carmen | Ising | 2nd Eng'g. Dist. | On-going | 2020-05-11 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | BAYANIHAN | [7 empty] | Project Engineer: | Estorco | Revised Completion Date: |  | Allotment: | 3000000 | Revised: |  | No. of Man-days: | 240
Carmen | Ising | 2nd Eng'g. Dist. | On-going | 2020-05-11 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | BAYANIHAN | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: | 22.72%
Carmen | Ising | 2nd Eng'g. Dist. | On-going | 2020-05-11 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | BAYANIHAN | [7 empty] | Duration: | 90 | No. of days extended: |  |  |  | Slippage: | -7.49%
Carmen | Ising | 2nd Eng'g. Dist. | On-going | 2020-05-11 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | BAYANIHAN | [7 empty] | Date Allotment Released: |  | Date completed:
Carmen | Ising | 2nd Eng'g. Dist. | On-going | 2020-05-11 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | BAYANIHAN | [7 empty] | Date Started: | 2020-05-11
Samal | Peñaplata | 2nd Eng'g. Dist. | On-going | 2020-05-11 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | BAYANIHAN | Impv't of Hospital Facilities (Isolation/ICU Room) Samal District Hospital |  | TF CY 2020 | Building |  | sq.m | Admin | Project Cost: | 1000000 | Target Completion Date: | 2020-08-09 | Program: | 1000000 | Planned: | 30.12% | No. of Persons: | 6 | On-going
Samal | Peñaplata | 2nd Eng'g. Dist. | On-going | 2020-05-11 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | BAYANIHAN | [7 empty] | Project Engineer: | Porras/Obar | Revised Completion Date: |  | Allotment: | 1000000 | Revised: |  | No. of Man-days: | 60
Samal | Peñaplata | 2nd Eng'g. Dist. | On-going | 2020-05-11 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | BAYANIHAN | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: | 50.17%
Samal | Peñaplata | 2nd Eng'g. Dist. | On-going | 2020-05-11 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | BAYANIHAN | [7 empty] | Duration: | 90 | No. of days extended: |  |  |  | Slippage: | 20.05%
Samal | Peñaplata | 2nd Eng'g. Dist. | On-going | 2020-05-11 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | BAYANIHAN | [7 empty] | Date Allotment Released: |  | Date completed:
Samal | Peñaplata | 2nd Eng'g. Dist. | On-going | 2020-05-11 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | BAYANIHAN | [7 empty] | Date Started: | 2020-05-11
Carmen | Ising | 2nd Eng'g. Dist. | On-going | 2020-05-11 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | BAYANIHAN | Rehab of DavNor Pharmacy into Isolation Room Phase I |  | TF CY 2020 | Building |  | sq.m | Admin | Project Cost: | 1480000 | Target Completion Date: | 2020-07-20 | Program: | 1480000 | Planned: | 63.38% | No. of Persons: | 10 | On-going
Carmen | Ising | 2nd Eng'g. Dist. | On-going | 2020-05-11 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | BAYANIHAN | [7 empty] | Project Engineer: | Andoy | Revised Completion Date: |  | Allotment: | 1480000 | Revised: |  | No. of Man-days: | 260
Carmen | Ising | 2nd Eng'g. Dist. | On-going | 2020-05-11 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | BAYANIHAN | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: | 1137930.67 | Actual: | 88.68%
Carmen | Ising | 2nd Eng'g. Dist. | On-going | 2020-05-11 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | BAYANIHAN | [7 empty] | Duration: | 83 | No. of days extended: |  |  |  | Slippage: | 25.3%
Carmen | Ising | 2nd Eng'g. Dist. | On-going | 2020-05-11 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | BAYANIHAN | [7 empty] | Date Allotment Released: |  | Date completed:
Carmen | Ising | 2nd Eng'g. Dist. | On-going | 2020-05-11 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | BAYANIHAN | [7 empty] | Date Started: | 2020-04-28
Carmen | Ising | 2nd Eng'g. Dist. | On-going | 2020-05-11 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | BAYANIHAN | Rehab of DavNor Pharmacy into Isolation Room Phase II |  | TF CY 2020 | Building |  | sq.m | Admin | Project Cost: | 1000000 | Target Completion Date: | 2020-07-24 | Program: | 1000000 | Planned: | 36.42% | No. of Persons: | 6 | On-going
Carmen | Ising | 2nd Eng'g. Dist. | On-going | 2020-05-11 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | BAYANIHAN | [7 empty] | Project Engineer: | Andoy | Revised Completion Date: |  | Allotment: | 1000000 | Revised: |  | No. of Man-days: | 132
Carmen | Ising | 2nd Eng'g. Dist. | On-going | 2020-05-11 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | BAYANIHAN | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: | 664107.16 | Actual: | 32.01%
Carmen | Ising | 2nd Eng'g. Dist. | On-going | 2020-05-11 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | BAYANIHAN | [7 empty] | Duration: | 74 | No. of days extended: |  |  |  | Slippage: | -4.41%
Carmen | Ising | 2nd Eng'g. Dist. | On-going | 2020-05-11 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | BAYANIHAN | [7 empty] | Date Allotment Released: |  | Date completed:
Carmen | Ising | 2nd Eng'g. Dist. | On-going | 2020-05-11 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | BAYANIHAN | [7 empty] | Date Started: | 2020-05-11

## SAMPLE-2 (BAYAHANIHAN) (hidden)
[12 empty] | 0 |  |  |  | 12744337 |  |  |  | 26762037.83 |  |  |  | 1810
[8 empty] | SECTOR: | ECONOMIC (INFRASTRUCTURE DEV'T. PROGRAM)
[8 empty] | OFFICE/AGENCY: | PROVINCIAL ENGINEER'S OFFICE
[8 empty] | AREA: | 1ST & 2ND ENGINEERING DISTRICT - COMPLETED, ON-GOING AND FOR IMPLEMENTATION PROJECTS
#VALUE!
SPECIAL TRUST FUND
MUNICIPALITY | BARANGAY | AREA | COMPLETED/ ON-GOING/ FOR IMPLEMENTATION/ SUSPENDED | DATE STARTED | DATE COMPLETED | APPRO- PRIATION | NOMEN- CLATURE | NAME OF PROJECT |  | SOURCE OF FUND | TYPE OF PROJECT | PHYSICAL TARGET (DESCRIPTION) |  | MODE OF IMPLEMENTATION | PROJECT DATA |  |  |  | FINANCIAL |  | PHYSICAL ACCOMPLISHMENT |  | EMPLOYMENT GENERATED |  | REMARKS
San Isidro | Sagayen | 1st Eng'g. Dist. | Completed | 2018-10-01 | 2020-04-02 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CMGP | Road upgrading Km. 9 Sagayen-Sawata (Sagayen-Jct. San Miguel Section) |  | CMGP CY 2017 | Road Concreting | 10.2 | km | Contract | Project Cost: | 139761975.14 | Target Completion Date: | 2019-08-22 23:46 | Program: | 139761975.14 | Planned: | 100% | No. of Persons: | 28 | Completed as per physical accomplishment. Financial documents still on process.
San Isidro | Sagayen | 1st Eng'g. Dist. | Completed | 2018-10-01 | 2020-04-02 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CMGP | [7 empty] | Project Engineer: | Avila | Revised Completion Date: | 2019-08-22 23:46 | Allotment: | 139761975.14 | Revised: |  | No. of Man-days: | 11170
San Isidro | Sagayen | 1st Eng'g. Dist. | Completed | 2018-10-01 | 2020-04-02 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CMGP | [7 empty] | Implementor: | Legacy Const. Corp. | No. of days suspended: | 209 | Disbursement: | 63100753.7 | Actual: | 100%
San Isidro | Sagayen | 1st Eng'g. Dist. | Completed | 2018-10-01 | 2020-04-02 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CMGP | [7 empty] | Duration: | 326 | No. of days extended: |  |  |  | Slippage: | 0%
San Isidro | Sagayen | 1st Eng'g. Dist. | Completed | 2018-10-01 | 2020-04-02 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CMGP | [7 empty] | Date Allotment Released: | CY 2017 | Date completed: | 2020-04-02
San Isidro | Sagayen | 1st Eng'g. Dist. | Completed | 2018-10-01 | 2020-04-02 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CMGP | [7 empty] | Date Started: | 2018-10-01
San Isidro | Sto. Niño | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-05-27 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | Rehab. Of Multi-Purpose Hall , Sto. Niño, San Isidro |  | 20% DF CY 2019 (STIMULUS) | Building | 182 | sq.m | Admin | Project Cost: | 500000 | Target Completion Date: | 2020-02-19 23:46 | Program: | 500000 | Planned: | 100% | No. of Persons: | 6 | Completed as per physical accomplishment. Financial documents still on process
San Isidro | Sto. Niño | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-05-27 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Project Engineer: | Aclaracion | Revised Completion Date: | 2020-02-19 23:46 | Allotment: | 500000 | Revised: |  | No. of Man-days: | 132
San Isidro | Sto. Niño | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-05-27 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Implementor: | PEO | No. of days suspended: | 28 | Disbursement: | 500000 | Actual: | 100%
San Isidro | Sto. Niño | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-05-27 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Duration: | 45 | No. of days extended: |  |  |  | Slippage: | 0%
San Isidro | Sto. Niño | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-05-27 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Allotment Released: | 2019-02-20 | Date completed: | 2020-05-27
San Isidro | Sto. Niño | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-05-27 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Started: | 2020-01-06
Tagum City | San Isidro | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-06-05 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | Const. of Women Livelihood Center, San Isidro, Tagum City |  | 20% DF CY 2019 (STIMULUS) | Building | 36.5 | sq.m | Admin | Project Cost: | 500000 | Target Completion Date: | 2020-03-21 23:46 | Program: | 500000 | Planned: | 100% | No. of Persons: | 10 | Completed as per physical accomplishment. Financial documents still on process
Tagum City | San Isidro | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-06-05 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Project Engineer: | Juan | Revised Completion Date: | 2020-06-05 23:46 | Allotment: | 500000 | Revised: | 100% | No. of Man-days: | 150
Tagum City | San Isidro | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-06-05 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Implementor: | PEO | No. of days suspended: | 28 | Disbursement: |  | Actual: | 100%
Tagum City | San Isidro | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-06-05 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Duration: | 80 | No. of days extended: | 48 |  |  | Slippage: | 0%
Tagum City | San Isidro | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-06-05 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Allotment Released: | 2019-05-29 | Date completed: | 2020-06-05
Tagum City | San Isidro | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-06-05 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Started: | 2020-01-02
New Corella | Saug | 1st Eng'g. Dist. | Completed | 2019-03-26 | 2020-06-30 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES | New Corella - Saug |  | 20% DF CY 2019 | Road Rehabilitation | 12.52 | km | Contract | Project Cost: | 6500000 | Target Completion Date: | 2019-03-26 | Program: | 6500000 | Planned: | 100% | No. of Persons: | 19 | Completed as per physical accomplishment. Financial documents still on process
New Corella | Saug | 1st Eng'g. Dist. | Completed | 2019-03-26 | 2020-06-30 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES | [7 empty] | Project Engineer: | Pilotos | Revised Completion Date: | 2019-06-10 | Allotment: | 6500000 | Revised: |  | No. of Man-days: | 570
New Corella | Saug | 1st Eng'g. Dist. | Completed | 2019-03-26 | 2020-06-30 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES | [7 empty] | Implementor: | PEO | No. of days suspended: | 28 | Disbursement: | 6500000 | Actual: | 100%
New Corella | Saug | 1st Eng'g. Dist. | Completed | 2019-03-26 | 2020-06-30 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES | [7 empty] | Duration: |  | No. of days extended: | 48 |  |  | Slippage: | 0%
New Corella | Saug | 1st Eng'g. Dist. | Completed | 2019-03-26 | 2020-06-30 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES | [7 empty] | Date Allotment Released: |  | Date completed: | 2020-06-30
New Corella | Saug | 1st Eng'g. Dist. | Completed | 2019-03-26 | 2020-06-30 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES | [7 empty] | Date Started: | 2019-03-26
Asuncion | Cabaywa | 1st Eng'g. Dist. | Completed | 2019-03-26 | 2020-06-30 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES | Jct. Monte Carlo - Upper Cabaywa - Canatan |  | 20% DF CY 2019 | Road Rehabilitation | 4.61 | km | Contract | Project Cost: | 8838000 | Target Completion Date: | 2019-03-26 | Program: | 8838000 | Planned: | 100% | No. of Persons: | 19 | Completed as per physical accomplishment. Financial documents still on process
Asuncion | Cabaywa | 1st Eng'g. Dist. | Completed | 2019-03-26 | 2020-06-30 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES | [7 empty] | Project Engineer: | Garcia | Revised Completion Date: | 2019-03-26 | Allotment: | 8838000 | Revised: |  | No. of Man-days: | 570
Asuncion | Cabaywa | 1st Eng'g. Dist. | Completed | 2019-03-26 | 2020-06-30 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES | [7 empty] | Implementor: | PEO | No. of days suspended: | 28 | Disbursement: | 8838000 | Actual: | 100%
Asuncion | Cabaywa | 1st Eng'g. Dist. | Completed | 2019-03-26 | 2020-06-30 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Asuncion | Cabaywa | 1st Eng'g. Dist. | Completed | 2019-03-26 | 2020-06-30 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES | [7 empty] | Date Allotment Released: | 2019-01-31 | Date completed: | 2020-06-30
Asuncion | Cabaywa | 1st Eng'g. Dist. | Completed | 2019-03-26 | 2020-06-30 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES | [7 empty] | Date Started: | 2019-03-26
Kapalong | Mamacao | 1st Eng'g. Dist. | On-going | 2020-02-05 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | Construction of Bleacher, Mamacao, Kapalong |  | GF CY 2018 (STIMULUS) | Bleacher |  | sq.m | Admin | Project Cost: | 500000 | Target Completion Date: | 2020-04-19 23:46 | Program: | 500000 | Planned: | 100% | No. of Persons: | 8 | Completed as per physical accomplishment. Financial documents still on process.
Kapalong | Mamacao | 1st Eng'g. Dist. | On-going | 2020-02-05 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Project Engineer: | Ambrosio | Revised Completion Date: | 2020-06-15 23:46 | Allotment: | 500000 | Revised: |  | No. of Man-days: | 120
Kapalong | Mamacao | 1st Eng'g. Dist. | On-going | 2020-02-05 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: |  | Actual: | 100%
Kapalong | Mamacao | 1st Eng'g. Dist. | On-going | 2020-02-05 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Duration: | 75 | No. of days extended: | 30 |  |  | Slippage:
Kapalong | Mamacao | 1st Eng'g. Dist. | On-going | 2020-02-05 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Date Allotment Released: |  | Date completed:
Kapalong | Mamacao | 1st Eng'g. Dist. | On-going | 2020-02-05 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Date Started: | 2020-02-05
Kapalong | Capungagan | 1st Eng'g. Dist. | On-going | 2016-04-06 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PRDP | Rehab. Of Capungagan-Boundary San Miguel FMR, Kapalong, Davao del Norte |  | PRDP CY 2015 | Road Concreting | 10.6 | km | Contract | Project Cost: | 108303841.7 | Target Completion Date: | 2020-02-14 23:46 | Program: | 108303841.7 | Planned: | 100% | No. of Persons: | 38 | Suspended effective April 5, 2020 due to issued Executive Order No. 31, series of 2020 the province of Davao del Norte in response to the State of Public Health Emergency and State of National Calamity (COVID19 Pandemic).
Kapalong | Capungagan | 1st Eng'g. Dist. | On-going | 2016-04-06 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PRDP | [7 empty] | Project Engineer: | Nasol | Revised Completion Date: | 2023-05-24 23:46 | Allotment: | 108303841.7 | Revised: | 97.28% | No. of Man-days: | 1140
Kapalong | Capungagan | 1st Eng'g. Dist. | On-going | 2016-04-06 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PRDP | [7 empty] | Implementor: | VICLAO | No. of days suspended: | 140 | Disbursement: | 60050673.93 | Actual: | 93.8%
Kapalong | Capungagan | 1st Eng'g. Dist. | On-going | 2016-04-06 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PRDP | [7 empty] | Duration: | 1410 | No. of days extended: | 1055 |  |  | Slippage: | -3.48%
Kapalong | Capungagan | 1st Eng'g. Dist. | On-going | 2016-04-06 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PRDP | [7 empty] | Date Allotment Released: | CY 2015 | Date completed:
Kapalong | Capungagan | 1st Eng'g. Dist. | On-going | 2016-04-06 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PRDP | [7 empty] | Date Started: | 2016-04-06
New Corella | Limbaan | 1st Eng'g. Dist. | On-going | 2019-04-08 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PRDP | Rehab. Of Pob.-Limbaan-Suawon-Macgum FMR w/ Bridge (42 ln.m), New Corella, Davao del Norte |  | PRDP CY 2015 | Road Concreting | 15.01 | km | Contract | Project Cost: | 205202114.16 | Target Completion Date: | 2019-01-18 | Program: | 205202114.16 | Planned: | 100% | No. of Persons: | 40 | On-going (Increase of Project Cost due to Variation Order Php 14,948,622.18, Partial suspension due to soft soil from sta. 8+000 - 10+000); (Suspended last April 5, 2020 due to COVID; Resumption Order dated June 1, 2020)
New Corella | Limbaan | 1st Eng'g. Dist. | On-going | 2019-04-08 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PRDP | [7 empty] | Project Engineer: | Madrigal | Revised Completion Date: | 2021-01-06 | Allotment: | 205202114.16 | Revised: | 83.77% | No. of Man-days: | 1200
New Corella | Limbaan | 1st Eng'g. Dist. | On-going | 2019-04-08 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PRDP | [7 empty] | Implementor: | Dvo. Rock Mixer | No. of days suspended: | 229 | Disbursement: | 141497191.47 | Actual: | 77.49%
New Corella | Limbaan | 1st Eng'g. Dist. | On-going | 2019-04-08 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PRDP | [7 empty] | Duration: | 1529 | No. of days extended: | 490 |  |  | Slippage: | -6.282%
New Corella | Limbaan | 1st Eng'g. Dist. | On-going | 2019-04-08 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PRDP | [7 empty] | Date Allotment Released: | CY 2015 | Date completed:
New Corella | Limbaan | 1st Eng'g. Dist. | On-going | 2019-04-08 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PRDP | [7 empty] | Date Started: | 2016-04-08
Asuncion | Sonlon-Camansa | 1st Eng'g. Dist. | On-going | 2019-03-28 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PRDP | Rehab. Of Sonlon - Camansa FMR Asuncion, Davao del Norte |  | PRDP CY 2015 | Road Concreting | 10.23 | km | Contract | Project Cost: | 215125015.81 | Target Completion Date: | 2020-06-15 | Program: | 215125015.81 | Planned: | 39.51% | No. of Persons: | 30 | On-going (Suspended last April 5, 2020 due to COVID; Resumption Order dated June 1, 2020)
Asuncion | Sonlon-Camansa | 1st Eng'g. Dist. | On-going | 2019-03-28 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PRDP | [7 empty] | Project Engineer: | Fabiala | Revised Completion Date: | 2020-06-15 | Allotment: | 215125015.81 | Revised: |  | No. of Man-days: | 780
Asuncion | Sonlon-Camansa | 1st Eng'g. Dist. | On-going | 2019-03-28 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PRDP | [7 empty] | Implementor: | Three w/Builders, Inc/Davao Rock Mixer Enterprises (JV) | No. of days suspended: |  | Disbursement: | 40523099.23 | Actual: | 31.6%
Asuncion | Sonlon-Camansa | 1st Eng'g. Dist. | On-going | 2019-03-28 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PRDP | [7 empty] | Duration: | 384 | No. of days extended: |  |  |  | Slippage: | -7.91%
Asuncion | Sonlon-Camansa | 1st Eng'g. Dist. | On-going | 2019-03-28 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PRDP | [7 empty] | Date Allotment Released: | 2018-09-18 | Date completed:
Asuncion | Sonlon-Camansa | 1st Eng'g. Dist. | On-going | 2019-03-28 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PRDP | [7 empty] | Date Started: | 2019-05-28
Kapalong | Capungagan | 1st Eng'g. Dist. | On-going | 2019-03-19 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PRDP | Cacao Production and Beans Marketing, Capungagan, Kapalong, Davao del Norte |  | PRDP CY 2016 | Building | 3610 | sq.m | Contract | Project Cost: | 5873626.8 | Target Completion Date: | 2019-11-24 | Program: | 5873626.8 | Planned: | 100% | No. of Persons: |  | Suspended due to modification of Detailed Design of mechanical Drier dated November 23, 2019; Waiting for the resumption order from DA.
Kapalong | Capungagan | 1st Eng'g. Dist. | On-going | 2019-03-19 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PRDP | [7 empty] | Project Engineer: | Delos Reyes | Revised Completion Date: | 2019-11-24 | Allotment: | 5873626.8 | Revised: |  | No. of Man-days:
Kapalong | Capungagan | 1st Eng'g. Dist. | On-going | 2019-03-19 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PRDP | [7 empty] | Implementor: | MICAH CONST. & SUPPLY | No. of days suspended: |  | Disbursement: | 4698901.44 | Actual: | 91.09%
Kapalong | Capungagan | 1st Eng'g. Dist. | On-going | 2019-03-19 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PRDP | [7 empty] | Duration: | 250 | No. of days extended: |  |  |  | Slippage: | -8.905%
Kapalong | Capungagan | 1st Eng'g. Dist. | On-going | 2019-03-19 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PRDP | [7 empty] | Date Allotment Released: | CY 2016 | Date completed:
Kapalong | Capungagan | 1st Eng'g. Dist. | On-going | 2019-03-19 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PRDP | [7 empty] | Date Started: | 2019-03-19
New Corella | Poblacion | 1st Eng'g. Dist. | On-going | 2019-01-17 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PRDP | Improvement of New Corella Nursery with Organic Input Production & Common Facility, Davao del Norte |  | PRDP CY 2016 | Building | 1901 | sq.m | Contract | Project Cost: | 9889628.45 | Target Completion Date: | 2019-11-23 | Program: | 9889628.45 | Planned: | 80.36% | No. of Persons: | 10 | On-going (Suspended last April 5, 2020 due to COVID; Resumption Order dated June 1, 2020)
New Corella | Poblacion | 1st Eng'g. Dist. | On-going | 2019-01-17 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PRDP | [7 empty] | Project Engineer: | Delos Reyes/Cabañero | Revised Completion Date: | 2020-08-09 | Allotment: | 9889628.45 | Revised: | 49.99% | No. of Man-days: | 250
New Corella | Poblacion | 1st Eng'g. Dist. | On-going | 2019-01-17 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PRDP | [7 empty] | Implementor: | SOUTH IRONROCK CORPORATION | No. of days suspended: | 260 | Disbursement: |  | Actual: | 46.3%
New Corella | Poblacion | 1st Eng'g. Dist. | On-going | 2019-01-17 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PRDP | [7 empty] | Duration: | 310 | No. of days extended: |  |  |  | Slippage: | -3.684%
New Corella | Poblacion | 1st Eng'g. Dist. | On-going | 2019-01-17 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PRDP | [7 empty] | Date Allotment Released: | CY 2016 | Date completed:
New Corella | Poblacion | 1st Eng'g. Dist. | On-going | 2019-01-17 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PRDP | [7 empty] | Date Started: | 2019-01-17
Tagum City | Pandapan | 1st Eng'g. Dist. | On-going |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPPAP-PAMANA | Const. of Trading Post, Storage Building with (1) unit Hauling Truck, Brgy. Pandapan |  | OPPAP-PAMANA CY 2017 | Building |  | sq.m | Contract | Project Cost: | 3975000 | Target Completion Date: | 0 | Program: | 3975000 | Planned: |  | No. of Persons: |  | Abstract 1220194004 (Tagum Builders);PO # 2019102828 - Truck
Tagum City | Pandapan | 1st Eng'g. Dist. | On-going |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPPAP-PAMANA | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 3975000 | Revised: |  | No. of Man-days:
Tagum City | Pandapan | 1st Eng'g. Dist. | On-going |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPPAP-PAMANA | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Tagum City | Pandapan | 1st Eng'g. Dist. | On-going |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPPAP-PAMANA | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Tagum City | Pandapan | 1st Eng'g. Dist. | On-going |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPPAP-PAMANA | [7 empty] | Date Allotment Released: | CY 2017 | Date completed:
Tagum City | Pandapan | 1st Eng'g. Dist. | On-going |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPPAP-PAMANA | [7 empty] | Date Started:
Kapalong |  | 1st Eng'g. Dist. | On-going | 2016-06-01 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPPAP-PAMANA | Construction of Biga Bridges, Kapalong (Original Contract Cost: P 24,959,503.45; Variation Order: P 4,067,412.00) |  | OPPAP-PAMANA CY 2014 | Road |  | km | Contract | Project Cost: | 29026915.45 | Target Completion Date: | 2018-07-30 23:59 | Program: | 29026915.45 | Planned: | 100% | No. of Persons: | 8 | Suspended due to RROW
Kapalong |  | 1st Eng'g. Dist. | On-going | 2016-06-01 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPPAP-PAMANA | [7 empty] | Project Engineer: | Limpo | Revised Completion Date: | 2020-03-25 23:59 | Allotment: | 29026915.45 | Revised: | 99.7% | No. of Man-days: | 290
Kapalong |  | 1st Eng'g. Dist. | On-going | 2016-06-01 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPPAP-PAMANA | [7 empty] | Implementor: | Davao Rock Mixer | No. of days suspended: | 604 | Disbursement: | 18489834.55 | Actual: | 85.37%
Kapalong |  | 1st Eng'g. Dist. | On-going | 2016-06-01 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPPAP-PAMANA | [7 empty] | Duration: | 760 | No. of days extended: |  |  |  | Slippage: | -14.33%
Kapalong |  | 1st Eng'g. Dist. | On-going | 2016-06-01 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPPAP-PAMANA | [7 empty] | Date Allotment Released: | CY 2014 | Date completed:
Kapalong |  | 1st Eng'g. Dist. | On-going | 2016-06-01 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPPAP-PAMANA | [7 empty] | Date Started: | 2016-07-01
Asuncion | Canatan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | QRF | Repair of Damaged Drainage/Creeks of Canatan, Asuncion |  | QRF CY 2015 & 2016 | Drainage/Creeks |  | km |  | Project Cost: | 137754.69 | Target Completion Date: | 0 | Program: | 137754.69 | Planned: |  | No. of Persons: |  | PO#2020061983 - FL2 LUMBER & CONST. SUPPLY; PO #2020062164 - jkle enterprises
Asuncion | Canatan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | QRF | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 137754.69 | Revised: |  | No. of Man-days:
Asuncion | Canatan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | QRF | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Asuncion | Canatan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | QRF | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Asuncion | Canatan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | QRF | [7 empty] | Date Allotment Released: |  | Date completed:
Asuncion | Canatan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | QRF | [7 empty] | Date Started:
Asuncion | Sagayen | 1st Eng'g. Dist. | On-going | 2018-11-15 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | QRF | Construction of Water Reservoir & Purchase of P.E. Pipelines, Sagayen, Asuncion |  | 20% DF CY 2017 (STIMULUS) | Water System |  |  | MLGU | Project Cost: | 500000 | Target Completion Date: | 2018-11-15 | Program: | 500000 | Planned: | 90% | No. of Persons: |  | Suspended due to non availability of water source during drilling.Find another location. Fund already transferred at Municipality of Asuncion with ChecK No. 2445174 and OR # 9238468,
Asuncion | Sagayen | 1st Eng'g. Dist. | On-going | 2018-11-15 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | QRF | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Asuncion | Sagayen | 1st Eng'g. Dist. | On-going | 2018-11-15 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | QRF | [7 empty] | Implementor: | MEO | No. of days suspended: |  | Disbursement: |  | Actual: | 90%
Asuncion | Sagayen | 1st Eng'g. Dist. | On-going | 2018-11-15 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | QRF | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Asuncion | Sagayen | 1st Eng'g. Dist. | On-going | 2018-11-15 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | QRF | [7 empty] | Date Allotment Released: | 2017-12-28 | Date completed:
Asuncion | Sagayen | 1st Eng'g. Dist. | On-going | 2018-11-15 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | QRF | [7 empty] | Date Started: | 2018-11-15
New Corella | Sta. Fe | 1st Eng'g. Dist. | On-going |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2017 | Road Rehabilitation at Prk. 1-Prk. 5, Sta. Fe, New Corella |  | 20% DF CY 2017 (STIMULUS) | Court |  |  | MLGU | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Fund already transferred at Municipality of Talaingod with ChecK No. 2445181 and OR # 7955667, dated March 16, 2018 . Amended from Electrification @ Prk. 1A-Prk. 5A)
New Corella | Sta. Fe | 1st Eng'g. Dist. | On-going |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2017 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 500000 | Revised: |  | No. of Man-days:
New Corella | Sta. Fe | 1st Eng'g. Dist. | On-going |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2017 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
New Corella | Sta. Fe | 1st Eng'g. Dist. | On-going |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2017 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | Sta. Fe | 1st Eng'g. Dist. | On-going |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2017 | [7 empty] | Date Allotment Released: | 2017-12-28 | Date completed:
New Corella | Sta. Fe | 1st Eng'g. Dist. | On-going |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2017 | [7 empty] | Date Started:
Talaingod | Palma Gil | 1st Eng'g. Dist. | On-going |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2017 | Const. of Covered Court Bleacher, Palma Gil, Talaingod |  | 20% DF CY 2017 | Court |  |  | MLGU | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | On-going (Fund already transferred at Municipality of Talaingod with ChecK No. 2445181 and OR # 7955667, dated March 16, 2018 . Amended from Electrification @ Prk. 1A-Prk. 5A
Talaingod | Palma Gil | 1st Eng'g. Dist. | On-going |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2017 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 500000 | Revised: |  | No. of Man-days:
Talaingod | Palma Gil | 1st Eng'g. Dist. | On-going |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2017 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Talaingod | Palma Gil | 1st Eng'g. Dist. | On-going |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2017 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Talaingod | Palma Gil | 1st Eng'g. Dist. | On-going |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2017 | [7 empty] | Date Allotment Released: | 2017-12-28 | Date completed:
Talaingod | Palma Gil | 1st Eng'g. Dist. | On-going |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2017 | [7 empty] | Date Started:
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2019-11-04 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./REHAB./COMP. OF VARIOUS GOV'T. BLDGS. STRUCT., FAC (Provincewide) LS - P9,000,000.00 | Rehab. Of PEO Training Center, (PDPM),Mankilam, Tagum City, (Part of P803,000.00)(20% DF CY 2018-P326,124.00) |  | 20% DF CY 2017 | Building | 85 | sq.m | Admin | Project Cost: | 476876 | Target Completion Date: | 2020-01-17 | Program: | 476876 | Planned: | 99% | No. of Persons: | 3 | Suspended (additional PR for Elect. Mat.) dated March 9, 2020
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2019-11-04 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./REHAB./COMP. OF VARIOUS GOV'T. BLDGS. STRUCT., FAC (Provincewide) LS - P9,000,000.00 | [7 empty] | Project Engineer: | Chua | Revised Completion Date: | 2020-03-15 | Allotment: | 476876 | Revised: |  | No. of Man-days: | 57
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2019-11-04 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./REHAB./COMP. OF VARIOUS GOV'T. BLDGS. STRUCT., FAC (Provincewide) LS - P9,000,000.00 | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: | 407521.7 | Actual: | 99%
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2019-11-04 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./REHAB./COMP. OF VARIOUS GOV'T. BLDGS. STRUCT., FAC (Provincewide) LS - P9,000,000.00 | [7 empty] | Duration: | 74 | No. of days extended: | 58 |  |  | Slippage: | 0%
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2019-11-04 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./REHAB./COMP. OF VARIOUS GOV'T. BLDGS. STRUCT., FAC (Provincewide) LS - P9,000,000.00 | [7 empty] | Date Allotment Released: | 2019-02-12 | Date completed:
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2019-11-04 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./REHAB./COMP. OF VARIOUS GOV'T. BLDGS. STRUCT., FAC (Provincewide) LS - P9,000,000.00 | [7 empty] | Date Started: | 2019-11-04
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2018-07-17 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./REHAB./COMP. OF VARIOUS GOV'T. BLDGS. STRUCT., FAC (Provincewide) LS - P9,000,000.00 | Upgrading of DDNSTC (Basketball/Voleyball MP Covered Court),Sports Center, Mankilam, Tagum City |  | SB # 4 CY 2017 | Covered Court | 2252.69 | sq.m | Contract | Project Cost: | 99992356.64 | Target Completion Date: | 2019-07-11 | Program: | 99992356.64 | Planned: | 100% | No. of Persons: | 10 | On-going (Suspended last April 5, 2020 due to COVID; Resumption Order dated May 4, 2020)
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2018-07-17 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./REHAB./COMP. OF VARIOUS GOV'T. BLDGS. STRUCT., FAC (Provincewide) LS - P9,000,000.00 | [7 empty] | Project Engineer: | Daral | Revised Completion Date: |  | Allotment: | 99992356.64 | Revised: |  | No. of Man-days: | 310
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2018-07-17 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./REHAB./COMP. OF VARIOUS GOV'T. BLDGS. STRUCT., FAC (Provincewide) LS - P9,000,000.00 | [7 empty] | Implementor: | YBC | No. of days suspended: |  | Disbursement: | 18280402.33 | Actual: | 73.04%
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2018-07-17 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./REHAB./COMP. OF VARIOUS GOV'T. BLDGS. STRUCT., FAC (Provincewide) LS - P9,000,000.00 | [7 empty] | Duration: | 360 | No. of days extended: | 20 |  |  | Slippage: | -26.96%
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2018-07-17 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./REHAB./COMP. OF VARIOUS GOV'T. BLDGS. STRUCT., FAC (Provincewide) LS - P9,000,000.00 | [7 empty] | Date Allotment Released: | 2018-10-16 | Date completed:
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2018-07-17 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./REHAB./COMP. OF VARIOUS GOV'T. BLDGS. STRUCT., FAC (Provincewide) LS - P9,000,000.00 | [7 empty] | Date Started: | 2018-07-17
Asuncion | Saug | 1st Eng'g. Dist. | On-going | 2019-01-03 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | QRF | Rehab. Of Saug Bridge of Slope Protection |  | QRF CY 2017 | Slope Protection | 356.4 | ln.m | Admin | Project Cost: | 4850000 | Target Completion Date: | 2019-05-02 23:46 | Program: | 4850000 | Planned: | 84.06% | No. of Persons: | 13 | On-going (Suspended dated January 28, 2019; Resumption February 3, 2020; Resumption Order dated May 4, 2020; Suspended last April 5, 2020 due to COVID; resumption order dated May 4, 2020)
Asuncion | Saug | 1st Eng'g. Dist. | On-going | 2019-01-03 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | QRF | [7 empty] | Project Engineer: | Gone | Revised Completion Date: | 2020-08-19 23:46 | Allotment: | 4850000 | Revised: |  | No. of Man-days: | 195
Asuncion | Saug | 1st Eng'g. Dist. | On-going | 2019-01-03 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | QRF | [7 empty] | Implementor: | PEO | No. of days suspended: | 400 | Disbursement: | 1628912.92 | Actual: | 77.63%
Asuncion | Saug | 1st Eng'g. Dist. | On-going | 2019-01-03 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | QRF | [7 empty] | Duration: | 120 | No. of days extended: | 75 |  |  | Slippage: | -6.43%
Asuncion | Saug | 1st Eng'g. Dist. | On-going | 2019-01-03 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | QRF | [7 empty] | Date Allotment Released: | 2018-05-25 | Date completed:
Asuncion | Saug | 1st Eng'g. Dist. | On-going | 2019-01-03 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | QRF | [7 empty] | Date Started: | 2019-01-03
Kapalong | Gupitan | 1st Eng'g. Dist. | On-going | 2019-02-22 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | QRF | Re-channeling of BIGA River with Earth Dike and Slope Protection, Brgy. Gupitan, Kaplaong |  | QRF CY 2017 | Slope Protection | 0.9 | ln.m | Contract | Project Cost: | 12100000 | Target Completion Date: | 2019-06-11 23:46 | Program: | 12100000 | Planned: | 8.3% | No. of Persons: | 4 | On-going (Suspended last April 5, 2020 due to COVID; resumption order dated May 4, 2020)
Kapalong | Gupitan | 1st Eng'g. Dist. | On-going | 2019-02-22 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | QRF | [7 empty] | Project Engineer: | Limpo | Revised Completion Date: | 2019-06-11 23:46 | Allotment: | 12100000 | Revised: |  | No. of Man-days: | 120
Kapalong | Gupitan | 1st Eng'g. Dist. | On-going | 2019-02-22 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | QRF | [7 empty] | Implementor: | Alpha & Omega | No. of days suspended: |  | Disbursement: |  | Actual: | 3.36%
Kapalong | Gupitan | 1st Eng'g. Dist. | On-going | 2019-02-22 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | QRF | [7 empty] | Duration: | 110 | No. of days extended: |  |  |  | Slippage: | -4.94%
Kapalong | Gupitan | 1st Eng'g. Dist. | On-going | 2019-02-22 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | QRF | [7 empty] | Date Allotment Released: | 2018-07-20 | Date completed:
Kapalong | Gupitan | 1st Eng'g. Dist. | On-going | 2019-02-22 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | QRF | [7 empty] | Date Started: | 2019-02-22
San Isidro | Linao | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | WATER SYSTEM LS - P 10,000,000.00 | Const. of PWS Linao, San Isidro |  | 20% DF CY 2018 | geo-resistivty/drillig |  |  | Admin | Project Cost: | 62000 | Target Completion Date: |  | Program: | 62000 | Planned: |  | No. of Persons: |  | For implementation
San Isidro | Linao | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | WATER SYSTEM LS - P 10,000,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 62000 | Revised: |  | No. of Man-days:
San Isidro | Linao | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | WATER SYSTEM LS - P 10,000,000.00 | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual:
San Isidro | Linao | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | WATER SYSTEM LS - P 10,000,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
San Isidro | Linao | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | WATER SYSTEM LS - P 10,000,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
San Isidro | Linao | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | WATER SYSTEM LS - P 10,000,000.00 | [7 empty] | Date Started:
San Isidro | Mamalian | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | WATER SYSTEM LS - P 10,000,000.00 | Const. of PWS Mamalian, San Isidro |  | 20% DF CY 2018 | geo-resistivty/drillig |  |  | Admin | Project Cost: | 62000 | Target Completion Date: |  | Program: | 62000 | Planned: |  | No. of Persons: |  | For declaration of savings because the spring water source is not feasible for development.
San Isidro | Mamalian | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | WATER SYSTEM LS - P 10,000,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 62000 | Revised: |  | No. of Man-days:
San Isidro | Mamalian | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | WATER SYSTEM LS - P 10,000,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
San Isidro | Mamalian | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | WATER SYSTEM LS - P 10,000,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
San Isidro | Mamalian | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | WATER SYSTEM LS - P 10,000,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
San Isidro | Mamalian | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | WATER SYSTEM LS - P 10,000,000.00 | [7 empty] | Date Started:
San Isidro | Sagayen | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | WATER SYSTEM LS - P 10,000,000.00 | Const. of PWS Sagayen, San Isidro |  | 20% DF CY 2018 | geo-resistivty/drillig |  |  | Admin | Project Cost: | 62000 | Target Completion Date: |  | Program: | 62000 | Planned: |  | No. of Persons: |  | For implementation
San Isidro | Sagayen | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | WATER SYSTEM LS - P 10,000,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 62000 | Revised: |  | No. of Man-days:
San Isidro | Sagayen | 1st Eng'g. Dist. | For Implementation |  | 0 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | WATER SYSTEM LS - P 10,000,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
San Isidro | Sagayen | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | WATER SYSTEM LS - P 10,000,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
San Isidro | Sagayen | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | WATER SYSTEM LS - P 10,000,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
San Isidro | Sagayen | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | WATER SYSTEM LS - P 10,000,000.00 | [7 empty] | Date Started:
Tagum City | Pandapan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | WATER SYSTEM LS - P 10,000,000.00 | Installation of potable water System at Purok Nangka, Pandapan, Tagum City |  | 20% DF CY 2018 | Water System |  |  | Admin | Project Cost: | 1125000 | Target Completion Date: |  | Program: | 1125000 | Planned: |  | No. of Persons: |  | Waiting for deed of donation. Follow-up letter was already issued
Tagum City | Pandapan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | WATER SYSTEM LS - P 10,000,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 1125000 | Revised: |  | No. of Man-days:
Tagum City | Pandapan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | WATER SYSTEM LS - P 10,000,000.00 | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual:
Tagum City | Pandapan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | WATER SYSTEM LS - P 10,000,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Tagum City | Pandapan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | WATER SYSTEM LS - P 10,000,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Tagum City | Pandapan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | WATER SYSTEM LS - P 10,000,000.00 | [7 empty] | Date Started:
Asuncion | San Vicente | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | WATER SYSTEM LS - P 10,000,000.00 | Rehab./Impv't. of San Vicente Water System, Asuncion |  | 20% DF CY 2018 | Water System |  |  | Admin | Project Cost: | 1125000 | Target Completion Date: |  | Program: | 1125000 | Planned: |  | No. of Persons: |  | Abstract # 0220190484 still draft
Asuncion | San Vicente | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | WATER SYSTEM LS - P 10,000,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 1125000 | Revised: |  | No. of Man-days:
Asuncion | San Vicente | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | WATER SYSTEM LS - P 10,000,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Asuncion | San Vicente | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | WATER SYSTEM LS - P 10,000,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Asuncion | San Vicente | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | WATER SYSTEM LS - P 10,000,000.00 | [7 empty] | Date Allotment Released: | 2018-10-26 | Date completed:
Asuncion | San Vicente | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | WATER SYSTEM LS - P 10,000,000.00 | [7 empty] | Date Started:
Asuncion | Sonlon-Camansa | 1st Eng'g. Dist. | On-going | 2019-05-28 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PRDP | Rehab. Of Sonlon-Camansa FMR, Asuncion, Davao del Norte (PRDP Counterpart : 193,612,514.23) |  | 20% DF CY 2018 | Road Concreting | 10.23 | km | Contract | Project Cost: | 21512501.5 | Target Completion Date: | 2020-06-14 23:46 | Program: | 21512501.5 | Planned: | 39.51% | No. of Persons: | 30 | On-going
Asuncion | Sonlon-Camansa | 1st Eng'g. Dist. | On-going | 2019-05-28 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PRDP | [7 empty] | Project Engineer: | Fabiala | Revised Completion Date: | 2020-06-14 23:46 | Allotment: | 21512501.5 | Revised: |  | No. of Man-days: | 690
Asuncion | Sonlon-Camansa | 1st Eng'g. Dist. | On-going | 2019-05-28 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PRDP | [7 empty] | Implementor: | Three w/Builders, Inc/Davao Rock Mixer Enterprises (JV) | No. of days suspended: |  | Disbursement: | 4502566.58 | Actual: | 31.6%
Asuncion | Sonlon-Camansa | 1st Eng'g. Dist. | On-going | 2019-05-28 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PRDP | [7 empty] | Duration: | 384 | No. of days extended: |  |  |  | Slippage: | -7.91%
Asuncion | Sonlon-Camansa | 1st Eng'g. Dist. | On-going | 2019-05-28 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PRDP | [7 empty] | Date Allotment Released: | 2018-09-18 | Date completed:
Asuncion | Sonlon-Camansa | 1st Eng'g. Dist. | On-going | 2019-05-28 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PRDP | [7 empty] | Date Started: | 2019-05-28
San Isidro | Sagayen-Sawata | 1st Eng'g. Dist. | On-going | 2019-09-09 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | KALSADA | Impvt. of Km. 9 Sagayen - Sawata Provincial Road Phase II |  | 20% DF CY 2018 | Road Concreting | 1.303 | km | Admin | Project Cost: | 7742775.95 | Target Completion Date: | 2020-03-27 | Program: | 7742775.95 | Planned: | 45% | No. of Persons: | 6 | Suspended dated March 6, 2020 due to delay delivery of materials
San Isidro | Sagayen-Sawata | 1st Eng'g. Dist. | On-going | 2019-09-09 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | KALSADA | [7 empty] | Project Engineer: | Kenny | Revised Completion Date: |  | Allotment: | 7742775.95 | Revised: |  | No. of Man-days: | 138
San Isidro | Sagayen-Sawata | 1st Eng'g. Dist. | On-going | 2019-09-09 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | KALSADA | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: | 2603417.9455 | Actual: | 35.05%
San Isidro | Sagayen-Sawata | 1st Eng'g. Dist. | On-going | 2019-09-09 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | KALSADA | [7 empty] | Duration: | 200 | No. of days extended: |  |  |  | Slippage: | -9.95%
San Isidro | Sagayen-Sawata | 1st Eng'g. Dist. | On-going | 2019-09-09 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | KALSADA | [7 empty] | Date Allotment Released: | 2019-01-31 | Date completed:
San Isidro | Sagayen-Sawata | 1st Eng'g. Dist. | On-going | 2019-09-09 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | KALSADA | [7 empty] | Date Started: | 2019-09-09
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2019-11-04 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./REHAB./COMP. OF VARIOUS GOV'T. BLDGS. STRUCT., FAC (Provincewide) LS - LS - P13,523,124.00 | Rehab. Of PEO Training Center, (PDPM),Mankilam, Tagum City (Part of P803,000.00)(20% DF CY 2017-P476,876.00) |  | 20% DF CY 2018 | Building | 85 | sq.m | Admin | Project Cost: | 326124 | Target Completion Date: | 2020-01-17 | Program: | 326124 | Planned: |  | No. of Persons: |  | suspended due to additional materials for electrical works
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2019-11-04 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./REHAB./COMP. OF VARIOUS GOV'T. BLDGS. STRUCT., FAC (Provincewide) LS - P13,523,124.00 | [7 empty] | Project Engineer: | Chua | Revised Completion Date: | 2020-03-14 | Allotment: | 326124 | Revised: |  | No. of Man-days:
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2019-11-04 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./REHAB./COMP. OF VARIOUS GOV'T. BLDGS. STRUCT., FAC (Provincewide) LS - P13,523,124.00 | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual:
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2019-11-04 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./REHAB./COMP. OF VARIOUS GOV'T. BLDGS. STRUCT., FAC (Provincewide) LS - P13,523,124.00 | [7 empty] | Duration: | 74 | No. of days extended: | 57 |  |  | Slippage: | 0%
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2019-11-04 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./REHAB./COMP. OF VARIOUS GOV'T. BLDGS. STRUCT., FAC (Provincewide) LS - P13,523,124.00 | [7 empty] | Date Allotment Released: | 2019-02-12 | Date completed:
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2019-11-04 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./REHAB./COMP. OF VARIOUS GOV'T. BLDGS. STRUCT., FAC (Provincewide) LS - P13,523,124.00 | [7 empty] | Date Started: | 2019-11-04
Asuncion | Camansa | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./REHAB./COMP. OF VARIOUS GOV'T. BLDGS. STRUCT., FAC (Provincewide) LS - LS - P13,523,124.00 | Construction of IP Tribal Council of Women at Brgy. Camansa, Asuncion |  | 20% DF CY 2018 | Building |  | sq.m | Admin | Project Cost: | 560000 | Target Completion Date: |  | Program: | 560000 | Planned: |  | No. of Persons: |  | Purchase Request # 20032714
Asuncion | Camansa | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./REHAB./COMP. OF VARIOUS GOV'T. BLDGS. STRUCT., FAC (Provincewide) LS - P13,523,124.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 560000 | Revised: |  | No. of Man-days:
Asuncion | Camansa | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./REHAB./COMP. OF VARIOUS GOV'T. BLDGS. STRUCT., FAC (Provincewide) LS - P13,523,124.00 | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual:
Asuncion | Camansa | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./REHAB./COMP. OF VARIOUS GOV'T. BLDGS. STRUCT., FAC (Provincewide) LS - P13,523,124.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Asuncion | Camansa | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./REHAB./COMP. OF VARIOUS GOV'T. BLDGS. STRUCT., FAC (Provincewide) LS - P13,523,124.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Asuncion | Camansa | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./REHAB./COMP. OF VARIOUS GOV'T. BLDGS. STRUCT., FAC (Provincewide) LS - P13,523,124.00 | [7 empty] | Date Started:
New Corella | Del Monte | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | RURAL ELECTRIFICATION (Provincewide) LS - P5,000,000.00 | Rural Electrification at Del Monte, New Corella |  | 20% DF CY 2018 | Electrification |  |  | Contract | Project Cost: | 1000000 | Target Completion Date: |  | Program: | 1000000 | Planned: |  | No. of Persons: |  | Post Qualification on process
New Corella | Del Monte | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | RURAL ELECTRIFICATION (Provincewide) LS - P5,000,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 1000000 | Revised: |  | No. of Man-days:
New Corella | Del Monte | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | RURAL ELECTRIFICATION (Provincewide) LS - P5,000,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
New Corella | Del Monte | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | RURAL ELECTRIFICATION (Provincewide) LS - P5,000,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | Del Monte | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | RURAL ELECTRIFICATION (Provincewide) LS - P5,000,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
New Corella | Del Monte | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | RURAL ELECTRIFICATION (Provincewide) LS - P5,000,000.00 | [7 empty] | Date Started:
Asuncion | Camansa | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | RURAL ELECTRIFICATION (Provincewide) LS - P5,000,000.00 | Const. of Distribution Line in Sitio Prk. 1,3,4, 11 and 7, Camansa, Asuncion |  | 20% DF CY 2018 | Electrification |  |  | Contract | Project Cost: | 4000000 | Target Completion Date: |  | Program: | 4000000 | Planned: |  | No. of Persons: |  | Purchase Request # 19093670 (On process )
Asuncion | Camansa | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | RURAL ELECTRIFICATION (Provincewide) LS - P5,000,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 4000000 | Revised: |  | No. of Man-days:
Asuncion | Camansa | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | RURAL ELECTRIFICATION (Provincewide) LS - P5,000,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Asuncion | Camansa | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | RURAL ELECTRIFICATION (Provincewide) LS - P5,000,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Asuncion | Camansa | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | RURAL ELECTRIFICATION (Provincewide) LS - P5,000,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Asuncion | Camansa | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | RURAL ELECTRIFICATION (Provincewide) LS - P5,000,000.00 | [7 empty] | Date Started:
Talaingod | Palma Gil | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./REHAB./COMP. OF VARIOUS GOV'T. BLDGS. STRUCT., FAC (Provincewide) | Const. of Standard Quarantine Shed for Car Bath Natulian, Brgy. Palma Gil, Talaingod |  | 20% DF CY 2018 | Car Bath |  |  | Contract | Project Cost: | 200000 | Target Completion Date: |  | Program: | 200000 | Planned: |  | No. of Persons: |  | Awarded to DIGOS CONSTRAK
Talaingod | Palma Gil | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./REHAB./COMP. OF VARIOUS GOV'T. BLDGS. STRUCT., FAC (Provincewide) | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 200000 | Revised: |  | No. of Man-days:
Talaingod | Palma Gil | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./REHAB./COMP. OF VARIOUS GOV'T. BLDGS. STRUCT., FAC (Provincewide) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Talaingod | Palma Gil | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./REHAB./COMP. OF VARIOUS GOV'T. BLDGS. STRUCT., FAC (Provincewide) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Talaingod | Palma Gil | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./REHAB./COMP. OF VARIOUS GOV'T. BLDGS. STRUCT., FAC (Provincewide) | [7 empty] | Date Allotment Released: |  | Date completed:
Talaingod | Palma Gil | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./REHAB./COMP. OF VARIOUS GOV'T. BLDGS. STRUCT., FAC (Provincewide) | [7 empty] | Date Started:
Tagum City | Balamban | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./REHAB./COMP. OF VARIOUS GOV'T. BLDGS. STRUCT., FAC (Provincewide) | Construction of Veterinary Quarantine Station, New balamban, Tagum City |  | 20% DF CY 2018 | Car Bath |  |  | Contract | Project Cost: | 200000 | Target Completion Date: |  | Program: | 200000 | Planned: |  | No. of Persons: |  | Awarded to ALLBRYCAR
Tagum City | Balamban | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./REHAB./COMP. OF VARIOUS GOV'T. BLDGS. STRUCT., FAC (Provincewide) | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 200000 | Revised: |  | No. of Man-days:
Tagum City | Balamban | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./REHAB./COMP. OF VARIOUS GOV'T. BLDGS. STRUCT., FAC (Provincewide) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Tagum City | Balamban | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./REHAB./COMP. OF VARIOUS GOV'T. BLDGS. STRUCT., FAC (Provincewide) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Tagum City | Balamban | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./REHAB./COMP. OF VARIOUS GOV'T. BLDGS. STRUCT., FAC (Provincewide) | [7 empty] | Date Allotment Released: |  | Date completed:
Tagum City | Balamban | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./REHAB./COMP. OF VARIOUS GOV'T. BLDGS. STRUCT., FAC (Provincewide) | [7 empty] | Date Started:
Asuncion | New Santiago | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | Const. of Potable water System at Prk. 6, New Santiago, Asuncion |  | GF CY 2018 (STIMULUS) | Water System |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Amended in AIP 3rd revision CY 2019 increasing the amount to complete the project For plan preparation c/o Amamio
Asuncion | New Santiago | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 500000 | Revised: |  | No. of Man-days:
Asuncion | New Santiago | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Asuncion | New Santiago | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Asuncion | New Santiago | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Date Allotment Released: |  | Date completed:
Asuncion | New Santiago | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Date Started:
Tagum City | Pagsabangan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | Completion of GYM Bleacher w/ Electrification, Pagsabangan, Tagum City |  | GF CY 2018 (STIMULUS) | Bleacher |  |  | MLGU | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | For implementation but the project was implemented by the brgy. Waiting for resolution to change priority Alloted March 12, 2019
Tagum City | Pagsabangan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 500000 | Revised: |  | No. of Man-days:
Tagum City | Pagsabangan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Tagum City | Pagsabangan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Tagum City | Pagsabangan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Date Allotment Released: |  | Date completed:
Tagum City | Pagsabangan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Date Started:
Tagum City | Libuganon | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | Construction of Drainage Canal, Libuganon, Tagum City |  | GF CY 2018 (STIMULUS) | Drainage |  |  | Admin | Project Cost: | 500000 | Target Completion Date: | 2020-08-18 23:59 | Program: | 500000 | Planned: | 53.04% | No. of Persons: | 14 | On-going
Tagum City | Libuganon | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Project Engineer: | Quirante | Revised Completion Date: | 2020-08-18 23:59 | Allotment: | 500000 | Revised: |  | No. of Man-days: | 434
Tagum City | Libuganon | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: | 53.04%
Tagum City | Libuganon | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Duration: | 64 | No. of days extended: |  |  |  | Slippage: | 0%
Tagum City | Libuganon | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Date Allotment Released: |  | Date completed:
Tagum City | Libuganon | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Date Started: | 2020-06-16
Kapalong | Luna | 1st Eng'g. Dist. | On-going | 2020-06-01 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | Construction of Concrete Perimeter Fence, Luna, Kapalaong |  | GF CY 2018 (STIMULUS) | Fence |  | sq.m | Admin | Project Cost: | 500000 | Target Completion Date: | 2020-07-21 | Program: | 500000 | Planned: | 92% | No. of Persons: | 8 | On-going
Kapalong | Luna | 1st Eng'g. Dist. | On-going | 2020-06-01 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Project Engineer: | Ambrosio | Revised Completion Date: | 2020-07-21 | Allotment: | 500000 | Revised: |  | No. of Man-days: | 120
Kapalong | Luna | 1st Eng'g. Dist. | On-going | 2020-06-01 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: | 93%
Kapalong | Luna | 1st Eng'g. Dist. | On-going | 2020-06-01 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Duration: | 50 | No. of days extended: |  |  |  | Slippage: | 1%
Kapalong | Luna | 1st Eng'g. Dist. | On-going | 2020-06-01 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Date Allotment Released: |  | Date completed:
Kapalong | Luna | 1st Eng'g. Dist. | On-going | 2020-06-01 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Date Started: | 2020-06-01
Kapalong | Maniki | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | Completion of Brgy. Health Center, Maniki, Kapalong |  | GF CY 2018 (STIMULUS) | Building |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | For amendment.To submit a new resolution for another priority project which is the Const. of Multi-Purpose Pavement but the propose site is not is donated because the previous project Completion of Brgy. Health Center was funded by the LGU of Kapalong
Kapalong | Maniki | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 500000 | Revised: |  | No. of Man-days:
Kapalong | Maniki | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Kapalong | Maniki | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Kapalong | Maniki | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Date Allotment Released: |  | Date completed:
Kapalong | Maniki | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Date Started:
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | Grouted Riprap on Embankment Sto. Ñino, Talaingod |  | GF CY 2018 (STIMULUS) | Riprap |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Plan and POW on process c/o PDPM
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 500000 | Revised: |  | No. of Man-days:
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Date Allotment Released: |  | Date completed:
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Date Started:
Talaingod | Dagohoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | Barangay Hall Improvement, Dagohoy, Talaingod |  | GF CY 2018 (STIMULUS) | Building |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | For amendment to Construction of Retaining Wall as per recommendation by Engr. Misa during site re-evaluation. Plan & POW completed.Resolution from the Brgy. Council to support the amendment c/o Engr. Canillada
Talaingod | Dagohoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 500000 | Revised: |  | No. of Man-days:
Talaingod | Dagohoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Talaingod | Dagohoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Talaingod | Dagohoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Date Allotment Released: |  | Date completed:
Talaingod | Dagohoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Date Started:
Talaingod | Palma Gil | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | Construction of 2 Classroom Building Datu Jose Libayao NHS Ext, Natulian, Palma Gil, Talaingod |  | GF CY 2018 (STIMULUS) | Building |  |  |  | Project Cost: | 1930933.28 | Target Completion Date: |  | Program: | 1930933.28 | Planned: |  | No. of Persons: |  | PO # 2020031342 - ALPEBEL BUILDERS & SUPPLY CORP.
Talaingod | Palma Gil | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 1930933.28 | Revised: |  | No. of Man-days:
Talaingod | Palma Gil | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Talaingod | Palma Gil | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Talaingod | Palma Gil | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Date Allotment Released: |  | Date completed:
Talaingod | Palma Gil | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Date Started:
New Corella | Mesaoy | 1st Eng'g. Dist. | On-going | 2018-11-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REHABILITATION OF VARIOUS PROVINCIAL ROADS | Mesaoy - Jct. Mahayahay |  | SB # 1 CY 2018 | Road Rehabilitation |  | km | Admin | Project Cost: | 1534000 | Target Completion Date: | 2018-12-15 23:46 | Program: | 1534000 | Planned: | 100% | No. of Persons: | 6 | Completed as per physical accomplishment. Financial documents still on process.
New Corella | Mesaoy | 1st Eng'g. Dist. | On-going | 2018-11-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REHABILITATION OF VARIOUS PROVINCIAL ROADS | [7 empty] | Project Engineer: | Pilotos | Revised Completion Date: |  | Allotment: | 1534000 | Revised: |  | No. of Man-days: | 150
New Corella | Mesaoy | 1st Eng'g. Dist. | On-going | 2018-11-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REHABILITATION OF VARIOUS PROVINCIAL ROADS | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: | 100%
New Corella | Mesaoy | 1st Eng'g. Dist. | On-going | 2018-11-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REHABILITATION OF VARIOUS PROVINCIAL ROADS | [7 empty] | Duration: | 30 | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | Mesaoy | 1st Eng'g. Dist. | On-going | 2018-11-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REHABILITATION OF VARIOUS PROVINCIAL ROADS | [7 empty] | Date Allotment Released: | 2018-07-19 | Date completed: | 2020-02-29
New Corella | Mesaoy | 1st Eng'g. Dist. | On-going | 2018-11-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REHABILITATION OF VARIOUS PROVINCIAL ROADS | [7 empty] | Date Started: | 2018-11-16
Kapalong | Maniki | 1st Eng'g. Dist. | On-going | 2019-11-02 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./COMPL./IMPV'T. OF VARIOUS GOV'T. BLDGS., STRUCTURES & FACILITIES (Const. in Progress - Bldgs. & Other Structures | Const./Impv't. of DDN Hospital Kapalong Zone |  | SB # 2 CY 2018 | Building |  | sq.m | Contract | Project Cost: | 5000000 | Target Completion Date: | 2020-06-09 | Program: | 5000000 | Planned: | 100% | No. of Persons: | 7 | Completed as per physical accomplishment. Financial documents still on process.
Kapalong | Maniki | 1st Eng'g. Dist. | On-going | 2019-11-02 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./COMPL./IMPV'T. OF VARIOUS GOV'T. BLDGS., STRUCTURES & FACILITIES (Const. in Progress - Bldgs. & Other Structures | [7 empty] | Project Engineer: | Ambrosio | Revised Completion Date: | 2020-07-07 | Allotment: | 5000000 | Revised: |  | No. of Man-days: | 217
Kapalong | Maniki | 1st Eng'g. Dist. | On-going | 2019-11-02 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./COMPL./IMPV'T. OF VARIOUS GOV'T. BLDGS., STRUCTURES & FACILITIES (Const. in Progress - Bldgs. & Other Structures | [7 empty] | Implementor: | MAG CORP. | No. of days suspended: | 28 | Disbursement: | 4781000 | Actual: | 100%
Kapalong | Maniki | 1st Eng'g. Dist. | On-going | 2019-11-02 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./COMPL./IMPV'T. OF VARIOUS GOV'T. BLDGS., STRUCTURES & FACILITIES (Const. in Progress - Bldgs. & Other Structures | [7 empty] | Duration: | 220 | No. of days extended: |  |  |  | Slippage: | 0%
Kapalong | Maniki | 1st Eng'g. Dist. | On-going | 2019-11-02 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./COMPL./IMPV'T. OF VARIOUS GOV'T. BLDGS., STRUCTURES & FACILITIES (Const. in Progress - Bldgs. & Other Structures | [7 empty] | Date Allotment Released: | 2018-09-04 | Date completed: | 2020-07-07
Kapalong | Maniki | 1st Eng'g. Dist. | On-going | 2019-11-02 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./COMPL./IMPV'T. OF VARIOUS GOV'T. BLDGS., STRUCTURES & FACILITIES (Const. in Progress - Bldgs. & Other Structures | [7 empty] | Date Started: | 2019-11-02
New Corella | Poblacion | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./COMPL./IMPV'T. OF VARIOUS GOV'T. BLDGS., STRUCTURES & FACILITIES (Const. in Progress - Bldgs. & Other Structures | Compl. Of Bahay Pag-Asa for Minors, New Corella |  | SB # 2 CY 2018 | Building |  |  | Admin | Project Cost: | 3450000 | Target Completion Date: | 2020-11-07 23:46 | Program: | 3450000 | Planned: | 15.75% | No. of Persons: | 8 | On-going
New Corella | Poblacion | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./COMPL./IMPV'T. OF VARIOUS GOV'T. BLDGS., STRUCTURES & FACILITIES (Const. in Progress - Bldgs. & Other Structures | [7 empty] | Project Engineer: | Cahayag | Revised Completion Date: |  | Allotment: | 3450000 | Revised: |  | No. of Man-days: | 248
New Corella | Poblacion | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./COMPL./IMPV'T. OF VARIOUS GOV'T. BLDGS., STRUCTURES & FACILITIES (Const. in Progress - Bldgs. & Other Structures | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: | 5.04%
New Corella | Poblacion | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./COMPL./IMPV'T. OF VARIOUS GOV'T. BLDGS., STRUCTURES & FACILITIES (Const. in Progress - Bldgs. & Other Structures | [7 empty] | Duration: | 144 | No. of days extended: |  |  |  | Slippage: | -10.71%
New Corella | Poblacion | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./COMPL./IMPV'T. OF VARIOUS GOV'T. BLDGS., STRUCTURES & FACILITIES (Const. in Progress - Bldgs. & Other Structures | [7 empty] | Date Allotment Released: |  | Date completed:
New Corella | Poblacion | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./COMPL./IMPV'T. OF VARIOUS GOV'T. BLDGS., STRUCTURES & FACILITIES (Const. in Progress - Bldgs. & Other Structures | [7 empty] | Date Started: | 2020-06-17
Tagum City | Mankilam | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./COMPL./IMPV'T. OF VARIOUS GOV'T. BLDGS., STRUCTURES & FACILITIES (Const. in Progress - Bldgs. & Other Structures | Const. of Add'l. 2nd Level Multi-Purpose HalI, PGSO warehouse,Bldg., Mankilam |  | SB # 2 CY 2018 | Building |  |  | Contract | Project Cost: | 7483756.22 | Target Completion Date: |  | Program: | 7483756.22 | Planned: |  | No. of Persons: |  | PO #2020020808 - FZI CONSTRUCTION AND PARTS SUPPLY
Tagum City | Mankilam | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./COMPL./IMPV'T. OF VARIOUS GOV'T. BLDGS., STRUCTURES & FACILITIES (Const. in Progress - Bldgs. & Other Structures | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 7483756.22 | Revised: |  | No. of Man-days:
Tagum City | Mankilam | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./COMPL./IMPV'T. OF VARIOUS GOV'T. BLDGS., STRUCTURES & FACILITIES (Const. in Progress - Bldgs. & Other Structures | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Tagum City | Mankilam | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./COMPL./IMPV'T. OF VARIOUS GOV'T. BLDGS., STRUCTURES & FACILITIES (Const. in Progress - Bldgs. & Other Structures | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Tagum City | Mankilam | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./COMPL./IMPV'T. OF VARIOUS GOV'T. BLDGS., STRUCTURES & FACILITIES (Const. in Progress - Bldgs. & Other Structures | [7 empty] | Date Allotment Released: |  | Date completed:
Tagum City | Mankilam | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./COMPL./IMPV'T. OF VARIOUS GOV'T. BLDGS., STRUCTURES & FACILITIES (Const. in Progress - Bldgs. & Other Structures | [7 empty] | Date Started:
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2020-04-30 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./COMPL./IMPV'T. OF VARIOUS GOV'T. BLDGS., STRUCTURES & FACILITIES (Const. in Progress - Bldgs. & Other Structures | Construction of SP/Legislative Building, Gov't. Center, Mankilam, Tagum City |  | SB # 3 CY 2018 | Building |  | sq.m | Contract | Project Cost: | 147262698.81 | Target Completion Date: | 2021-04-04 | Program: | 147262698.81 | Planned: | 4.205% | No. of Persons: | 20 | On-going (Suspended effective April 5, 2020 due to COVID; resumption order dated May 4, 2020)
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2020-04-30 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./COMPL./IMPV'T. OF VARIOUS GOV'T. BLDGS., STRUCTURES & FACILITIES (Const. in Progress - Bldgs. & Other Structures | [7 empty] | Project Engineer: | Japay/Albaracin | Revised Completion Date: | 2021-05-01 | Allotment: | 147262698.81 | Revised: |  | No. of Man-days: | 370
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2020-04-30 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./COMPL./IMPV'T. OF VARIOUS GOV'T. BLDGS., STRUCTURES & FACILITIES (Const. in Progress - Bldgs. & Other Structures | [7 empty] | Implementor: | Tagum Builders | No. of days suspended: | 27 | Disbursement: |  | Actual: | 4.347%
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2020-04-30 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./COMPL./IMPV'T. OF VARIOUS GOV'T. BLDGS., STRUCTURES & FACILITIES (Const. in Progress - Bldgs. & Other Structures | [7 empty] | Duration: | 370 | No. of days extended: |  |  |  | Slippage: | 0.1415%
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2020-04-30 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./COMPL./IMPV'T. OF VARIOUS GOV'T. BLDGS., STRUCTURES & FACILITIES (Const. in Progress - Bldgs. & Other Structures | [7 empty] | Date Allotment Released: |  | Date completed:
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2020-04-30 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./COMPL./IMPV'T. OF VARIOUS GOV'T. BLDGS., STRUCTURES & FACILITIES (Const. in Progress - Bldgs. & Other Structures | [7 empty] | Date Started: | 2020-03-30
Asuncion | Napungas | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | Rehab./Impv't. of MP Bldg. (Gym), Napungas, Asuncion |  | SB # 5 CY 2018 (STIMULUS) | GYM |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Abstract # 0620202137
Asuncion | Napungas | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Asuncion | Napungas | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Asuncion | Napungas | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Asuncion | Napungas | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Date Allotment Released: | 2019-02-04 | Date completed:
Asuncion | Napungas | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Date Started:
New Corella | Poblacion | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | Concreting of Drainage Canal from Prk. 3, 1-A, 2-A to Prk. 1-B, Brgy. Site, Phase @, New Corella |  | SB # 5 CY 2018 (STIMULUS) | Drainage |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Abstract draft
New Corella | Poblacion | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 500000 | Revised: |  | No. of Man-days:
New Corella | Poblacion | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
New Corella | Poblacion | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | Poblacion | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Date Allotment Released: |  | Date completed:
New Corella | Poblacion | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Date Started:
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2019-11-26 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./COMPL./IMPV'T. OF VARIOUS GOV'T. BLDGS., STRUCTURES & FACILITIES (Const. in Progress - Bldgs. & Other Structures | Division School Improvement (Davao del Norte DEPED Training Center), Tagum City |  | SEF (ANNUAL BUDGET CY 2018) | Building |  | sq.m | Admin | Project Cost: | 1250000 | Target Completion Date: | 2020-05-04 | Program: | 1250000 | Planned: | 100% | No. of Persons: | 18 | On-going (Suspended last April 5, 2020 due to COVID; resumption order dated May 4, 2020)
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2019-11-26 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./COMPL./IMPV'T. OF VARIOUS GOV'T. BLDGS., STRUCTURES & FACILITIES (Const. in Progress - Bldgs. & Other Structures | [7 empty] | Project Engineer: | Japay/Quirante | Revised Completion Date: | 2020-07-15 | Allotment: | 1250000 | Revised: | 83.63% | No. of Man-days: | 270
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2019-11-26 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./COMPL./IMPV'T. OF VARIOUS GOV'T. BLDGS., STRUCTURES & FACILITIES (Const. in Progress - Bldgs. & Other Structures | [7 empty] | Implementor: | Admin | No. of days suspended: | 27 | Disbursement: | 850625 | Actual: | 78.02%
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2019-11-26 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./COMPL./IMPV'T. OF VARIOUS GOV'T. BLDGS., STRUCTURES & FACILITIES (Const. in Progress - Bldgs. & Other Structures | [7 empty] | Duration: | 160 | No. of days extended: | 45 |  |  | Slippage: | -5.61%
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2019-11-26 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./COMPL./IMPV'T. OF VARIOUS GOV'T. BLDGS., STRUCTURES & FACILITIES (Const. in Progress - Bldgs. & Other Structures | [7 empty] | Date Allotment Released: | 2019-02-04 | Date completed:
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2019-11-26 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./COMPL./IMPV'T. OF VARIOUS GOV'T. BLDGS., STRUCTURES & FACILITIES (Const. in Progress - Bldgs. & Other Structures | [7 empty] | Date Started: | 2019-11-26
Talaingod | Dagohoy | 1st Eng'g. Dist. | On-going | 2019-11-17 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPAPP | Const. of Processing and Bagsakan Center, Brgy. Dagohoy, Talaingod |  | OPAPP-PAMANA CY 2018 | Building |  | sq.m | Contract | Project Cost: | 2500000 | Target Completion Date: | 2020-04-10 | Program: | 2500000 | Planned: | 55.61% | No. of Persons: | 8 | On-going; Resumption Order dated May 4, 2020
Talaingod | Dagohoy | 1st Eng'g. Dist. | On-going | 2019-11-17 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPAPP | [7 empty] | Project Engineer: | Dadula | Revised Completion Date: |  | Allotment: | 2500000 | Revised: |  | No. of Man-days: | 200
Talaingod | Dagohoy | 1st Eng'g. Dist. | On-going | 2019-11-17 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPAPP | [7 empty] | Implementor: | RLHV | No. of days suspended: |  | Disbursement: | 375000 | Actual: | 68.72%
Talaingod | Dagohoy | 1st Eng'g. Dist. | On-going | 2019-11-17 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPAPP | [7 empty] | Duration: | 145 | No. of days extended: |  |  |  | Slippage: | 13.11%
Talaingod | Dagohoy | 1st Eng'g. Dist. | On-going | 2019-11-17 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPAPP | [7 empty] | Date Allotment Released: | 2019-11-25 | Date completed:
Talaingod | Dagohoy | 1st Eng'g. Dist. | On-going | 2019-11-17 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPAPP | [7 empty] | Date Started: | 2019-11-17
Kapalong | Maniki | 1st Eng'g. Dist. | On-going | 2019-11-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPAPP | Post Harvest Facilities (Corn Mill, Solar Dryer, Corn Sheller), Kapalong, Davao del Norte |  | OPAPP-PAMANA CY 2018 | Building |  | sq.m | Admin | Project Cost: | 1500000 | Target Completion Date: | 2020-02-27 | Program: | 1500000 | Planned: | 100% | No. of Persons: | 7 | Completed as per physical accomplishment. Financial documents still on process.
Kapalong | Maniki | 1st Eng'g. Dist. | On-going | 2019-11-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPAPP | [7 empty] | Project Engineer: | Ambrosio | Revised Completion Date: | 2020-06-15 | Allotment: | 1500000 | Revised: |  | No. of Man-days: | 175
Kapalong | Maniki | 1st Eng'g. Dist. | On-going | 2019-11-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPAPP | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 1114654.45 | Actual: | 100%
Kapalong | Maniki | 1st Eng'g. Dist. | On-going | 2019-11-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPAPP | [7 empty] | Duration: | 101 | No. of days extended: | 82 |  |  | Slippage: | 0%
Kapalong | Maniki | 1st Eng'g. Dist. | On-going | 2019-11-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPAPP | [7 empty] | Date Allotment Released: | 2019-11-18 | Date completed: | 2020-06-15
Kapalong | Maniki | 1st Eng'g. Dist. | On-going | 2019-11-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPAPP | [7 empty] | Date Started: | 2019-11-18
Kapalong | Capungagan | 1st Eng'g. Dist. | On-going | 2019-11-25 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPAPP | Construction of PWS Level II in Purok 7-A and 7-B, Capungagan, Kapalong |  | OPAPP-PAMANA CY 2018 | Potable Water System |  |  | Admin | Project Cost: | 1760000 | Target Completion Date: | 2020-02-03 | Program: | 1760000 | Planned: | 100% | No. of Persons: | 25 | On-going (Suspended last April 5, 2020 due to COVID; resumption order dated May 4, 2020)
Kapalong | Capungagan | 1st Eng'g. Dist. | On-going | 2019-11-25 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPAPP | [7 empty] | Project Engineer: | Kabinge | Revised Completion Date: | 2020-04-15 | Allotment: | 1760000 | Revised: | 100% | No. of Man-days: | 375
Kapalong | Capungagan | 1st Eng'g. Dist. | On-going | 2019-11-25 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPAPP | [7 empty] | Implementor: | PEO | No. of days suspended: | 28 | Disbursement: | 1235344 | Actual: | 76.64%
Kapalong | Capungagan | 1st Eng'g. Dist. | On-going | 2019-11-25 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPAPP | [7 empty] | Duration: | 70 | No. of days extended: | 44 |  |  | Slippage: | -23.36%
Kapalong | Capungagan | 1st Eng'g. Dist. | On-going | 2019-11-25 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPAPP | [7 empty] | Date Allotment Released: | 2019-11-25 | Date completed:
Kapalong | Capungagan | 1st Eng'g. Dist. | On-going | 2019-11-25 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPAPP | [7 empty] | Date Started: | 2019-11-25
Kapalong | Pag-Asa | 1st Eng'g. Dist. | On-going | 2019-12-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPAPP | Construction of PWS Level II in Purok 2, Pag-Asa, kapalong |  | OPAPP-PAMANA CY 2018 | Potable Water System |  |  | Admin | Project Cost: | 2310000 | Target Completion Date: | 2020-04-09 | Program: | 2310000 | Planned: | 78% | No. of Persons: | 23 | On-going (Suspended last April 5, 2020 due to COVID; resumption order dated May 4, 2020)
Kapalong | Pag-Asa | 1st Eng'g. Dist. | On-going | 2019-12-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPAPP | [7 empty] | Project Engineer: | Dadula | Revised Completion Date: | 2020-07-31 | Allotment: | 2310000 | Revised: | 71.1% | No. of Man-days: | 713
Kapalong | Pag-Asa | 1st Eng'g. Dist. | On-going | 2019-12-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPAPP | [7 empty] | Implementor: | PEO | No. of days suspended: | 28 | Disbursement: | 1642410 | Actual: | 71.1%
Kapalong | Pag-Asa | 1st Eng'g. Dist. | On-going | 2019-12-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPAPP | [7 empty] | Duration: | 115 | No. of days extended: | 85 |  |  | Slippage: | 0%
Kapalong | Pag-Asa | 1st Eng'g. Dist. | On-going | 2019-12-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPAPP | [7 empty] | Date Allotment Released: | 2019-11-25 | Date completed:
Kapalong | Pag-Asa | 1st Eng'g. Dist. | On-going | 2019-12-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPAPP | [7 empty] | Date Started: | 2019-12-16
Kapalong | Semong | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPAPP | Cattle Production- Brgy. Tiburcia, Gupitan and Semong, Kapalong |  | OPAPP-PAMANA CY 2018 | Building |  | sq.m |  | Project Cost: | 1500000 | Target Completion Date: |  | Program: | 1500000 | Planned: |  | No. of Persons: |  | For cancellation. A letter was sent to OPAPP last Dec 2018 requesting to allow us to reduce the number of cattle but we are still hoping that there would be a supplier will bid
Kapalong | Semong | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPAPP | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 1500000 | Revised: |  | No. of Man-days:
Kapalong | Semong | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPAPP | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Kapalong | Semong | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPAPP | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Kapalong | Semong | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPAPP | [7 empty] | Date Allotment Released: |  | Date completed:
Kapalong | Semong | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPAPP | [7 empty] | Date Started:
Talaingod | Dagohoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPAPP | Cattle Production, Brgy. Palma Gil, Brgy. Sto. Nino, Brgy. Dagohoy, Talaingod, Davao del Norte |  | OPAPP-PAMANA CY 2018 | Building |  | sq.m |  | Project Cost: | 1500000 | Target Completion Date: |  | Program: | 1500000 | Planned: |  | No. of Persons: |  | For cancellation. A letter was sent to OPAPP last Dec 2018 requesting to allow us to reduce the number of cattle but we are still hoping that there would be a supplier will bid
Talaingod | Dagohoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPAPP | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 1500000 | Revised: |  | No. of Man-days:
Talaingod | Dagohoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPAPP | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Talaingod | Dagohoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPAPP | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Talaingod | Dagohoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPAPP | [7 empty] | Date Allotment Released: |  | Date completed:
Talaingod | Dagohoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPAPP | [7 empty] | Date Started:
Talaingod | Palma Gil | 1st Eng'g. Dist. | On-going | 2020-06-01 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPAPP | Rice Mill for Upland Rice, Palma Gil, Talaingod |  | OPAPP-PAMANA CY 2018 | Rice Mill |  |  | Admin | Project Cost: | 1000000 | Target Completion Date: | 2020-07-30 23:46 | Program: | 1000000 | Planned: | 35.69% | No. of Persons: | 6 | On-going
Talaingod | Palma Gil | 1st Eng'g. Dist. | On-going | 2020-06-01 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPAPP | [7 empty] | Project Engineer: | Torrecampo | Revised Completion Date: | 2020-07-30 23:46 | Allotment: | 1000000 | Revised: |  | No. of Man-days: | 90
Talaingod | Palma Gil | 1st Eng'g. Dist. | On-going | 2020-06-01 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPAPP | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: | 356900 | Actual: | 35.69%
Talaingod | Palma Gil | 1st Eng'g. Dist. | On-going | 2020-06-01 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPAPP | [7 empty] | Duration: | 60 | No. of days extended: |  |  |  | Slippage: | 0%
Talaingod | Palma Gil | 1st Eng'g. Dist. | On-going | 2020-06-01 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPAPP | [7 empty] | Date Allotment Released: |  | Date completed:
Talaingod | Palma Gil | 1st Eng'g. Dist. | On-going | 2020-06-01 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPAPP | [7 empty] | Date Started: | 2020-06-01
Kapalong | Mabantao-Florida | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | QRF | Rehab. Of Slope Protection of Libuganon River Along Kapalong - Mabantao - Florida Prov'l. Road Phase I |  | QRF CY 2016 | Slope Protection |  |  |  | Project Cost: | 900000 | Target Completion Date: |  | Program: | 900000 | Planned: |  | No. of Persons: |  | For AIP Amendment
Kapalong | Mabantao-Florida | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | QRF | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 900000 | Revised: |  | No. of Man-days:
Kapalong | Mabantao-Florida | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | QRF | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Kapalong | Mabantao-Florida | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | QRF | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Kapalong | Mabantao-Florida | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | QRF | [7 empty] | Date Allotment Released: |  | Date completed:
Kapalong | Mabantao-Florida | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | QRF | [7 empty] | Date Started:
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2019-11-04 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Ground Dev't. | Ground Development and landscape @ PDRRMD, Gov't. Center, Mankilam, Tagum City |  | LDRRMF 2018 | Ground Dev't. |  | sq.m | Admin | Project Cost: | 1000000 | Target Completion Date: | 2020-02-29 23:46 | Program: | 1000000 | Planned: | 75.24% | No. of Persons: | 8 | Suspended (Waiting for the complete delivery of materials) dated March 2, 2020
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2019-11-04 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Ground Dev't. | [7 empty] | Project Engineer: | Juan | Revised Completion Date: | 2020-02-29 23:46 | Allotment: | 1000000 | Revised: |  | No. of Man-days: | 152
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2019-11-04 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Ground Dev't. | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: | 752400 | Actual: | 75.24%
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2019-11-04 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Ground Dev't. | [7 empty] | Duration: | 118 | No. of days extended: |  |  |  | Slippage: | 0%
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2019-11-04 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Ground Dev't. | [7 empty] | Date Allotment Released: | 2019-03-19 | Date completed:
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2019-11-04 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Ground Dev't. | [7 empty] | Date Started: | 2019-11-04
Asuncion | Canatan-Doña Andrea | 1st Eng'g. Dist. | On-going | 2020-06-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL RAODS & BRIDGES LS - P41,465,029.00 | ROAD ID 007 - Jct. Highway Canatan - Doña Andrea |  | 20% DF CY 2019 | Road Rehabilitation | 4.34 | km | Admin | Project Cost: | 2000000 | Target Completion Date: | 2020-08-11 23:46 | Program: | 2000000 | Planned: | 31.77% | No. of Persons: |  | On-going
Asuncion | Canatan-Doña Andrea | 1st Eng'g. Dist. | On-going | 2020-06-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL RAODS & BRIDGES | [7 empty] | Project Engineer: | Pilotos | Revised Completion Date: | 2020-08-11 23:46 | Allotment: | 2000000 | Revised: |  | No. of Man-days:
Asuncion | Canatan-Doña Andrea | 1st Eng'g. Dist. | On-going | 2020-06-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL RAODS & BRIDGES LS - P41,465,029.00 | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: | 635400 | Actual: | 31.77%
Asuncion | Canatan-Doña Andrea | 1st Eng'g. Dist. | On-going | 2020-06-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL RAODS & BRIDGES LS - P41,465,029.00 | [7 empty] | Duration: | 57 | No. of days extended: |  |  |  | Slippage: | 0%
Asuncion | Canatan-Doña Andrea | 1st Eng'g. Dist. | On-going | 2020-06-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL RAODS & BRIDGES LS - P41,465,029.00 | [7 empty] | Date Allotment Released: | 2019-06-12 | Date completed:
Asuncion | Canatan-Doña Andrea | 1st Eng'g. Dist. | On-going | 2020-06-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL RAODS & BRIDGES LS - P41,465,029.00 | [7 empty] | Date Started: | 2020-06-16
Asuncion | Pamacaun | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL RAODS & BRIDGES LS - P41,465,029.00 | ROAD ID 015 - Pamacaun - Lasang Banate |  | 20% DF CY 2019 | Road Rehabilitation | 4.34 |  | Admin | Project Cost: | 2000000 | Target Completion Date: |  | Program: | 2000000 | Planned: |  | No. of Persons: |  | For implementation (Waiting for the delivery of geo-grid materials. An approved request letter dated Dec. 3, 2019 for the extension of 50 days from Provincial Administrator Engr. Rabanoz is on file
Asuncion | Pamacaun | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL RAODS & BRIDGES | [7 empty] | Project Engineer: | Gone | Revised Completion Date: | 0 | Allotment: | 2000000 | Revised: |  | No. of Man-days:
Asuncion | Pamacaun | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL RAODS & BRIDGES LS - P41,465,029.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Asuncion | Pamacaun | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL RAODS & BRIDGES LS - P41,465,029.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Asuncion | Pamacaun | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL RAODS & BRIDGES LS - P41,465,029.00 | [7 empty] | Date Allotment Released: | 2019-06-27 | Date completed:
Asuncion | Pamacaun | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL RAODS & BRIDGES LS - P41,465,029.00 | [7 empty] | Date Started:
Talaingod | Sto.Niño-Palma Gil | 1st Eng'g. Dist. | On-going | 2020-03-06 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL RAODS & BRIDGES LS - P41,465,029.00 | ROAD ID 019 - Sto. Niño - Palma Gil - Sitio Opao |  | 20% DF CY 2019 | Road Rehabilitation | 11.6 | km | Contract | Project Cost: | 1901000 | Target Completion Date: | 2020-04-18 23:46 | Program: | 1901000 | Planned: | 44.89% | No. of Persons: |  | On-going (Suspended dated March 14, 2020; Resumption Order dated May 25, 2020)
Talaingod | Sto.Niño-Palma Gil | 1st Eng'g. Dist. | On-going | 2020-03-06 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL RAODS & BRIDGES | [7 empty] | Project Engineer: | Lumapat | Revised Completion Date: | 2020-06-29 23:46 | Allotment: | 1901000 | Revised: |  | No. of Man-days:
Talaingod | Sto.Niño-Palma Gil | 1st Eng'g. Dist. | On-going | 2020-03-06 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL RAODS & BRIDGES LS - P41,465,029.00 | [7 empty] | Implementor: | Tagum Constrak | No. of days suspended: | 72 | Disbursement: | 853358.9 | Actual: | 44.89%
Talaingod | Sto.Niño-Palma Gil | 1st Eng'g. Dist. | On-going | 2020-03-06 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL RAODS & BRIDGES LS - P41,465,029.00 | [7 empty] | Duration: | 44 | No. of days extended: |  |  |  | Slippage: | 0%
Talaingod | Sto.Niño-Palma Gil | 1st Eng'g. Dist. | On-going | 2020-03-06 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL RAODS & BRIDGES LS - P41,465,029.00 | [7 empty] | Date Allotment Released: | 2019-06-19 | Date completed:
Talaingod | Sto.Niño-Palma Gil | 1st Eng'g. Dist. | On-going | 2020-03-06 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL RAODS & BRIDGES LS - P41,465,029.00 | [7 empty] | Date Started: | 2020-03-06
Talaingod | Sto. Niño-Daligdigon-Paiton | 1st Eng'g. Dist. | On-going | 2020-01-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL RAODS & BRIDGES LS - P41,465,029.00 | ROAD ID 023 - Sto. Niño - Daligdigon - Paiton |  | 20% DF CY 2019 | Road Rehabilitation | 11.6 | km | Contract | Project Cost: | 3000000 | Target Completion Date: | 2020-05-14 23:46 | Program: | 3000000 | Planned: | 19.35% | No. of Persons: | 7 | On-going; Resumption Order dated May 4, 2020
Talaingod | Sto. Niño-Daligdigon-Paiton | 1st Eng'g. Dist. | On-going | 2020-01-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL RAODS & BRIDGES | [7 empty] | Project Engineer: | Lumapat | Revised Completion Date: | 2020-06-11 23:46 | Allotment: | 3000000 | Revised: |  | No. of Man-days: | 217
Talaingod | Sto. Niño-Daligdigon-Paiton | 1st Eng'g. Dist. | On-going | 2020-01-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL RAODS & BRIDGES LS - P41,465,029.00 | [7 empty] | Implementor: |  | No. of days suspended: | 28 | Disbursement: | 580500 | Actual: | 19.35%
Talaingod | Sto. Niño-Daligdigon-Paiton | 1st Eng'g. Dist. | On-going | 2020-01-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL RAODS & BRIDGES LS - P41,465,029.00 | [7 empty] | Duration: | 120 | No. of days extended: |  |  |  | Slippage: | 0%
Talaingod | Sto. Niño-Daligdigon-Paiton | 1st Eng'g. Dist. | On-going | 2020-01-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL RAODS & BRIDGES LS - P41,465,029.00 | [7 empty] | Date Allotment Released: | 2019-10-03 | Date completed:
Talaingod | Sto. Niño-Daligdigon-Paiton | 1st Eng'g. Dist. | On-going | 2020-01-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL RAODS & BRIDGES LS - P41,465,029.00 | [7 empty] | Date Started: | 2020-01-16
Talaingod | Jct. Paiton-Mibolo | 1st Eng'g. Dist. | On-going | 2019-08-01 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL RAODS & BRIDGES LS - P41,465,029.00 | ROAD ID 024 - Jct. Paiton - Mibolo |  | 20% DF CY 2019 | Road Rehabilitation | 23.9 | km | Contract | Project Cost: | 6000000 | Target Completion Date: | 2020-03-15 23:46 | Program: | 6000000 | Planned: | 21.05% | No. of Persons: |  | Temporary suspended because the materials for the box culvert procurement on process wth PO # 2019061674
Talaingod | Jct. Paiton-Mibolo | 1st Eng'g. Dist. | On-going | 2019-08-01 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL RAODS & BRIDGES | [7 empty] | Project Engineer: | Lumapat | Revised Completion Date: |  | Allotment: | 6000000 | Revised: |  | No. of Man-days:
Talaingod | Jct. Paiton-Mibolo | 1st Eng'g. Dist. | On-going | 2019-08-01 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL RAODS & BRIDGES LS - P41,465,029.00 | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: | 1263000 | Actual: | 21.05%
Talaingod | Jct. Paiton-Mibolo | 1st Eng'g. Dist. | On-going | 2019-08-01 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL RAODS & BRIDGES LS - P41,465,029.00 | [7 empty] | Duration: | 228 | No. of days extended: |  |  |  | Slippage: | 0%
Talaingod | Jct. Paiton-Mibolo | 1st Eng'g. Dist. | On-going | 2019-08-01 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL RAODS & BRIDGES LS - P41,465,029.00 | [7 empty] | Date Allotment Released: | 2019-03-25 | Date completed:
Talaingod | Jct. Paiton-Mibolo | 1st Eng'g. Dist. | On-going | 2019-08-01 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL RAODS & BRIDGES LS - P41,465,029.00 | [7 empty] | Date Started: | 2019-08-01
Talaingod | Monte Dujali-Gupitan | 1st Eng'g. Dist. | On-going | 2020-01-31 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL RAODS & BRIDGES LS - P41,465,029.00 | ROAD ID 037 - Monte Dujali - Gupitan |  | 20% DF CY 2019 | Road Rehabilitation | 4.58 | km | Admin | Project Cost: | 1200000 | Target Completion Date: | 2020-03-31 23:46 | Program: | 1200000 | Planned: | 100% | No. of Persons: | 10 | Completed as per physical accomplishment. Financial documents still on process.
Talaingod | Monte Dujali-Gupitan | 1st Eng'g. Dist. | On-going | 2020-01-31 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL RAODS & BRIDGES | [7 empty] | Project Engineer: | Bacaron | Revised Completion Date: | 2020-06-30 23:46 | Allotment: | 1200000 | Revised: |  | No. of Man-days: | 240
Talaingod | Monte Dujali-Gupitan | 1st Eng'g. Dist. | On-going | 2020-01-31 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL RAODS & BRIDGES LS - P41,465,029.00 | [7 empty] | Implementor: | PEO | No. of days suspended: | 30 | Disbursement: | 1200000 | Actual: | 100%
Talaingod | Monte Dujali-Gupitan | 1st Eng'g. Dist. | On-going | 2020-01-31 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL RAODS & BRIDGES LS - P41,465,029.00 | [7 empty] | Duration: | 61 | No. of days extended: | 61 |  |  | Slippage: | 0%
Talaingod | Monte Dujali-Gupitan | 1st Eng'g. Dist. | On-going | 2020-01-31 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL RAODS & BRIDGES LS - P41,465,029.00 | [7 empty] | Date Allotment Released: | 2019-12-06 | Date completed:
Talaingod | Monte Dujali-Gupitan | 1st Eng'g. Dist. | On-going | 2020-01-31 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL RAODS & BRIDGES LS - P41,465,029.00 | [7 empty] | Date Started: | 2020-01-31
New Corella | San Juan-New Talisay | 1st Eng'g. Dist. | On-going | 2019-11-04 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS OF LOCAL ROADS & DRAINAGE DEVELOPMENT PROJECT(Provincewide) LS - 15,000,000.00 | Rehab./Impv't. of San Juan-New Talisay Provincial Road with Drainage |  | 20% DF CY 2019 | Road Drainage rehabiliated |  | km | Admin | Project Cost: | 1000000 | Target Completion Date: | 2019-12-18 | Program: | 1000000 | Planned: | 57.41% | No. of Persons: |  | Suspended dated December 18, 2019 due to revision of POW
New Corella | San Juan-New Talisay | 1st Eng'g. Dist. | On-going | 2019-11-04 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS OF LOCAL ROADS & DRAINAGE DEVELOPMENT PROJECT(Provincewide) LS - 15,000,000.00 | [7 empty] | Project Engineer: | Pilotos | Revised Completion Date: | 2019-12-18 | Allotment: | 1000000 | Revised: |  | No. of Man-days:
New Corella | San Juan-New Talisay | 1st Eng'g. Dist. | On-going | 2019-11-04 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS OF LOCAL ROADS & DRAINAGE DEVELOPMENT PROJECT(Provincewide) LS - 15,000,000.00 | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: | 741100 | Actual: | 74.11%
New Corella | San Juan-New Talisay | 1st Eng'g. Dist. | On-going | 2019-11-04 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS OF LOCAL ROADS & DRAINAGE DEVELOPMENT PROJECT(Provincewide) LS - 15,000,000.00 | [7 empty] | Duration: | 44 | No. of days extended: |  |  |  | Slippage: | 16.7%
New Corella | San Juan-New Talisay | 1st Eng'g. Dist. | On-going | 2019-11-04 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS OF LOCAL ROADS & DRAINAGE DEVELOPMENT PROJECT(Provincewide) LS - 15,000,000.00 | [7 empty] | Date Allotment Released: | 2019-01-31 | Date completed:
New Corella | San Juan-New Talisay | 1st Eng'g. Dist. | On-going | 2019-11-04 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS OF LOCAL ROADS & DRAINAGE DEVELOPMENT PROJECT(Provincewide) LS - 15,000,000.00 | [7 empty] | Date Started: | 2019-11-04
Kapalong | Suaon-Libuton | 1st Eng'g. Dist. | On-going | 2019-11-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS OF LOCAL ROADS & DRAINAGE DEVELOPMENT PROJECT(Provincewide) LS - 15,000,000.00 | Repair/Rehab. Of Concrete Road Jct. Suaon-Libuton, Kapalong |  | 20% DF CY 2019 | Road Drainage rehabiliated |  | km | Admin | Project Cost: | 1000000 | Target Completion Date: | 2020-02-15 23:46 | Program: | 1000000 | Planned: | 14.73% | No. of Persons: |  | Suspended dated March 30, 2020 due to availability of equipment
Kapalong | Suaon-Libuton | 1st Eng'g. Dist. | On-going | 2019-11-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS OF LOCAL ROADS & DRAINAGE DEVELOPMENT PROJECT(Provincewide) LS - 15,000,000.00 | [7 empty] | Project Engineer: | Bacaron | Revised Completion Date: |  | Allotment: | 1000000 | Revised: |  | No. of Man-days:
Kapalong | Suaon-Libuton | 1st Eng'g. Dist. | On-going | 2019-11-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS OF LOCAL ROADS & DRAINAGE DEVELOPMENT PROJECT(Provincewide) LS - 15,000,000.00 | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: | 142000 | Actual: | 14.2%
Kapalong | Suaon-Libuton | 1st Eng'g. Dist. | On-going | 2019-11-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS OF LOCAL ROADS & DRAINAGE DEVELOPMENT PROJECT(Provincewide) LS - 15,000,000.00 | [7 empty] | Duration: | 90 | No. of days extended: |  |  |  | Slippage: | -0.53%
Kapalong | Suaon-Libuton | 1st Eng'g. Dist. | On-going | 2019-11-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS OF LOCAL ROADS & DRAINAGE DEVELOPMENT PROJECT(Provincewide) LS - 15,000,000.00 | [7 empty] | Date Allotment Released: | 2019-03-12 | Date completed:
Kapalong | Suaon-Libuton | 1st Eng'g. Dist. | On-going | 2019-11-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS OF LOCAL ROADS & DRAINAGE DEVELOPMENT PROJECT(Provincewide) LS - 15,000,000.00 | [7 empty] | Date Started: | 2019-11-18
Asuncion | Saug-Sonlon Longanapan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS OF LOCAL ROADS & DRAINAGE DEVELOPMENT PROJECT(Provincewide) LS - 15,000,000.00 | Impv't. of Cross Drainage along Saug-Sonlon-Bdry. Longanapan |  | 20% DF CY 2019 | Road Drainage rehabiliated |  | ln.m | Admin | Project Cost: | 3000000 | Target Completion Date: |  | Program: | 3000000 | Planned: |  | No. of Persons: |  | For implementation
Asuncion | Saug-Sonlon Longanapan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS OF LOCAL ROADS & DRAINAGE DEVELOPMENT PROJECT(Provincewide) LS - 15,000,000.00 | [7 empty] | Project Engineer: | Pilotos | Revised Completion Date: | 0 | Allotment: | 3000000 | Revised: |  | No. of Man-days:
Asuncion | Saug-Sonlon Longanapan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS OF LOCAL ROADS & DRAINAGE DEVELOPMENT PROJECT(Provincewide) LS - 15,000,000.00 | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual:
Asuncion | Saug-Sonlon Longanapan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS OF LOCAL ROADS & DRAINAGE DEVELOPMENT PROJECT(Provincewide) LS - 15,000,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Asuncion | Saug-Sonlon Longanapan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS OF LOCAL ROADS & DRAINAGE DEVELOPMENT PROJECT(Provincewide) LS - 15,000,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Asuncion | Saug-Sonlon Longanapan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS OF LOCAL ROADS & DRAINAGE DEVELOPMENT PROJECT(Provincewide) LS - 15,000,000.00 | [7 empty] | Date Started:
Talaingod | Sto. Niño-Palma Gil | 1st Eng'g. Dist. | On-going | 2020-02-27 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS OF LOCAL ROADS & DRAINAGE DEVELOPMENT PROJECT(Provincewide) LS - 15,000,000.00 | Rehab./Impv't. of Sto. Niño-Palma Gil-Sitio Opao Provincial Road with Drainage |  | 20% DF CY 2019 | Road Drainage rehabiliated |  | km | Contract | Project Cost: | 3000000 | Target Completion Date: | 2020-05-07 | Program: | 3000000 | Planned: | 44.89% | No. of Persons: |  | On-going (Suspended dated March 14, 2020; Resumption Order dated May 25, 2020)
Talaingod | Sto. Niño-Palma Gil | 1st Eng'g. Dist. | On-going | 2020-02-27 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS OF LOCAL ROADS & DRAINAGE DEVELOPMENT PROJECT(Provincewide) LS - 15,000,000.00 | [7 empty] | Project Engineer: | Lumapat | Revised Completion Date: | 2020-07-17 | Allotment: | 3000000 | Revised: |  | No. of Man-days:
Talaingod | Sto. Niño-Palma Gil | 1st Eng'g. Dist. | On-going | 2020-02-27 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS OF LOCAL ROADS & DRAINAGE DEVELOPMENT PROJECT(Provincewide) LS - 15,000,000.00 | [7 empty] | Implementor: | Tagum Constrak | No. of days suspended: | 71 | Disbursement: | 1346700 | Actual: | 44.89%
Talaingod | Sto. Niño-Palma Gil | 1st Eng'g. Dist. | On-going | 2020-02-27 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS OF LOCAL ROADS & DRAINAGE DEVELOPMENT PROJECT(Provincewide) LS - 15,000,000.00 | [7 empty] | Duration: | 70 | No. of days extended: |  |  |  | Slippage: | 0%
Talaingod | Sto. Niño-Palma Gil | 1st Eng'g. Dist. | On-going | 2020-02-27 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS OF LOCAL ROADS & DRAINAGE DEVELOPMENT PROJECT(Provincewide) LS - 15,000,000.00 | [7 empty] | Date Allotment Released: | 2019-05-25 | Date completed:
Talaingod | Sto. Niño-Palma Gil | 1st Eng'g. Dist. | On-going | 2020-02-27 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS OF LOCAL ROADS & DRAINAGE DEVELOPMENT PROJECT(Provincewide) LS - 15,000,000.00 | [7 empty] | Date Started: | 2020-02-27
San Isidro | Linao | 1st Eng'g. Dist. | On-going | 2020-02-24 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS WATER SYSTEM DEVELOPMENT LS - P 9,750,000.00 | Construction of PWS, Bgry. Linao, San Isidro |  | 20% DF CY 2019 | Water System |  | ln.m | Admin | Project Cost: | 500000 | Target Completion Date: | 2020-04-23 23:46 | Program: | 500000 | Planned: | 99% | No. of Persons: | 8 | On-going (Suspended last April 5, 2020 due to COVID; resumption order dated May 4, 2020)
San Isidro | Linao | 1st Eng'g. Dist. | On-going | 2020-02-24 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS WATER SYSTEM DEVELOPMENT LS - P 9,750,000.00 | [7 empty] | Project Engineer: | Aclaracion | Revised Completion Date: | 2020-07-05 23:46 | Allotment: | 500000 | Revised: |  | No. of Man-days: | 120
San Isidro | Linao | 1st Eng'g. Dist. | On-going | 2020-02-24 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS WATER SYSTEM DEVELOPMENT LS - P 9,750,000.00 | [7 empty] | Implementor: | PEO | No. of days suspended: | 73 | Disbursement: | 216100 | Actual: | 99%
San Isidro | Linao | 1st Eng'g. Dist. | On-going | 2020-02-24 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS WATER SYSTEM DEVELOPMENT LS - P 9,750,000.00 | [7 empty] | Duration: | 60 | No. of days extended: |  |  |  | Slippage: | 0%
San Isidro | Linao | 1st Eng'g. Dist. | On-going | 2020-02-24 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS WATER SYSTEM DEVELOPMENT LS - P 9,750,000.00 | [7 empty] | Date Allotment Released: | 2019-06-19 | Date completed:
San Isidro | Linao | 1st Eng'g. Dist. | On-going | 2020-02-24 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS WATER SYSTEM DEVELOPMENT LS - P 9,750,000.00 | [7 empty] | Date Started: | 2020-02-24
San Isidro | Datu Balong | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS WATER SYSTEM DEVELOPMENT LS - P 9,750,000.00 | Construction of PWS, Brgy. Datu Balong, San Isidro |  | 20% DF CY 2019 | Water System |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | For declaration of savings because the spring water source is not feasible for development
San Isidro | Datu Balong | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS WATER SYSTEM DEVELOPMENT LS - P 9,750,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 500000 | Revised: |  | No. of Man-days:
San Isidro | Datu Balong | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS WATER SYSTEM DEVELOPMENT LS - P 9,750,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
San Isidro | Datu Balong | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS WATER SYSTEM DEVELOPMENT LS - P 9,750,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
San Isidro | Datu Balong | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS WATER SYSTEM DEVELOPMENT LS - P 9,750,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
San Isidro | Datu Balong | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS WATER SYSTEM DEVELOPMENT LS - P 9,750,000.00 | [7 empty] | Date Started:
San Isidro | Sagayen | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS WATER SYSTEM DEVELOPMENT LS - P 9,750,000.00 | Construction of PWS, Brgy. Sagayen, San Isidro |  | 20% DF CY 2019 | Water System |  |  | Contract | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | PO # 2020031340 - JJR Construction
San Isidro | Sagayen | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS WATER SYSTEM DEVELOPMENT LS - P 9,750,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 500000 | Revised: |  | No. of Man-days:
San Isidro | Sagayen | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS WATER SYSTEM DEVELOPMENT LS - P 9,750,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
San Isidro | Sagayen | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS WATER SYSTEM DEVELOPMENT LS - P 9,750,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
San Isidro | Sagayen | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS WATER SYSTEM DEVELOPMENT LS - P 9,750,000.00 | [7 empty] | Date Allotment Released: | 2019-09-10 | Date completed:
San Isidro | Sagayen | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS WATER SYSTEM DEVELOPMENT LS - P 9,750,000.00 | [7 empty] | Date Started:
Tagum City | Mankilam | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS WATER SYSTEM DEVELOPMENT LS - P 9,750,000.00 | Installation of Shallow Tube Wells & Const. of Machinery Shed |  | 20% DF CY 2019 | Water System |  |  | Admin | Project Cost: | 1600000 | Target Completion Date: |  | Program: | 1600000 | Planned: |  | No. of Persons: |  | Opening of BID for Negotiated 6/18,2020 to alpebel
Tagum City | Mankilam | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS WATER SYSTEM DEVELOPMENT LS - P 9,750,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 1600000 | Revised: |  | No. of Man-days:
Tagum City | Mankilam | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS WATER SYSTEM DEVELOPMENT LS - P 9,750,000.00 | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual:
Tagum City | Mankilam | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS WATER SYSTEM DEVELOPMENT LS - P 9,750,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Tagum City | Mankilam | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS WATER SYSTEM DEVELOPMENT LS - P 9,750,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Tagum City | Mankilam | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS WATER SYSTEM DEVELOPMENT LS - P 9,750,000.00 | [7 empty] | Date Started:
New Corella | Poblacion | 1st Eng'g. Dist. | On-going | 2020-03-02 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | Repair/Impv't. of Municipal Triball Hall, New Corella |  | 20% DF CY 2019 | Building |  | sq.m | Admin | Project Cost: | 1500000 | Target Completion Date: | 2020-06-12 23:46 | Program: | 1500000 | Planned: | 82.55% | No. of Persons: | 15 | On-going (Suspended last April 5, 2020 due to COVID; resumption order dated May 4, 2020)
New Corella | Poblacion | 1st Eng'g. Dist. | On-going | 2020-03-02 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | [7 empty] | Project Engineer: | Cahayag | Revised Completion Date: | 2020-07-10 23:46 | Allotment: | 1500000 | Revised: |  | No. of Man-days: | 225
New Corella | Poblacion | 1st Eng'g. Dist. | On-going | 2020-03-02 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | [7 empty] | Implementor: | PEO | No. of days suspended: | 28 | Disbursement: |  | Actual: | 77.72%
New Corella | Poblacion | 1st Eng'g. Dist. | On-going | 2020-03-02 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | [7 empty] | Duration: | 103 | No. of days extended: |  |  |  | Slippage: | -4.83%
New Corella | Poblacion | 1st Eng'g. Dist. | On-going | 2020-03-02 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
New Corella | Poblacion | 1st Eng'g. Dist. | On-going | 2020-03-02 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | [7 empty] | Date Started: | 2020-03-02
San Isidro | Sabangan | 1st Eng'g. Dist. | On-going | 2019-12-02 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | Const. of Municipal Tribal Hall, San Isidro |  | 20% DF CY 2019 | Building | 42 | sq.m | Admin | Project Cost: | 500000 | Target Completion Date: | 2020-02-19 23:46 | Program: | 500000 | Planned: | 81.44% | No. of Persons: | 8 | Completed as per physical accomplishment. Financial documents still on process.
San Isidro | Sabangan | 1st Eng'g. Dist. | On-going | 2019-12-02 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | [7 empty] | Project Engineer: | Aclaracion | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days: | 176
San Isidro | Sabangan | 1st Eng'g. Dist. | On-going | 2019-12-02 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | [7 empty] | Implementor: | PEO | No. of days suspended: | 28 | Disbursement: |  | Actual: | 81.44%
San Isidro | Sabangan | 1st Eng'g. Dist. | On-going | 2019-12-02 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | [7 empty] | Duration: | 80 | No. of days extended: |  |  |  | Slippage: | 0%
San Isidro | Sabangan | 1st Eng'g. Dist. | On-going | 2019-12-02 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | [7 empty] | Date Allotment Released: | 2019-01-15 | Date completed: | 2020-06-15
San Isidro | Sabangan | 1st Eng'g. Dist. | On-going | 2019-12-02 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | [7 empty] | Date Started: | 2019-12-02
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2019-12-02 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | Repair Bay of Disaster Quick Response Equipment @ PEO Compound, Gov't. Center, Mankilam, Tagum City |  | 20% DF CY 2019 | Building | 66 | sq.m | Admin | Project Cost: | 1000000 | Target Completion Date: | 2020-04-19 23:46 | Program: | 1000000 | Planned: | 74.7% | No. of Persons: | 5 | On-going (Suspended last April 5, 2020 due to COVID; resumption order dated May 4, 2020)
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2019-12-02 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | [7 empty] | Project Engineer: | Chua/Mucas | Revised Completion Date: | 2020-05-17 23:46 | Allotment: | 1000000 | Revised: |  | No. of Man-days: | 95
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2019-12-02 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | [7 empty] | Implementor: | PEO | No. of days suspended: | 28 | Disbursement: |  | Actual: | 74.7%
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2019-12-02 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | [7 empty] | Duration: | 140 | No. of days extended: |  |  |  | Slippage: | 0%
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2019-12-02 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | [7 empty] | Date Allotment Released: | 2019-01-31 | Date completed:
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2019-12-02 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | [7 empty] | Date Started: | 2019-12-02
Talaingod | Gupitan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | Const. of Multi-Purpose Hall Center (Cultural Heritage in Ancestral Domain of Ata-Manobo) |  | 20% DF CY 2019 | Building |  |  | Admin | Project Cost: | 3000000 | Target Completion Date: |  | Program: | 3000000 | Planned: |  | No. of Persons: |  | Fund re-aligned to GIDAS projects
Talaingod | Gupitan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 3000000 | Revised: |  | No. of Man-days:
Talaingod | Gupitan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Talaingod | Gupitan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Talaingod | Gupitan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Talaingod | Gupitan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | [7 empty] | Date Started:
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | Const. of IP Women's Multi-{Purpose Bldg.), Cabidiangan, Sto. Niño, Talaingod |  | 20% DF CY 2019 | Building |  |  | Admin | Project Cost: | 2000000 | Target Completion Date: |  | Program: | 2000000 | Planned: |  | No. of Persons: |  | Final abstract #0320200897 (Alpebel Builders)
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 2000000 | Revised: |  | No. of Man-days:
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual:
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | [7 empty] | Date Allotment Released: | 2019-05-15 | Date completed:
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | [7 empty] | Date Started:
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2020-02-03 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | Extension of PAGRO Training Center & Ground Dev't., Gov't. Center, Mankilam, Tagum City |  | 20% DF CY 2019 | Building |  | sq.m | Admin | Project Cost: | 1000000 | Target Completion Date: | 2020-04-23 | Program: | 1000000 | Planned: | 30.5% | No. of Persons: | 5 | On-going (Suspended last April 5, 2020 due to COVID; resumption order dated May 4, 2020)
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2020-02-03 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | [7 empty] | Project Engineer: | Chua/Mugas | Revised Completion Date: | 2020-05-21 | Allotment: | 1000000 | Revised: |  | No. of Man-days: | 57
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2020-02-03 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | [7 empty] | Implementor: | PEO | No. of days suspended: | 28 | Disbursement: |  | Actual: | 30.5%
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2020-02-03 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | [7 empty] | Duration: | 80 | No. of days extended: |  |  |  | Slippage: | 0%
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2020-02-03 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | [7 empty] | Date Allotment Released: | 2019-07-26 | Date completed:
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2020-02-03 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | [7 empty] | Date Started: | 2020-02-03
Tagum City | Mankilam | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | Construction of Abilidad Training Center, Gov't. Center, Mankilam, Tagum City |  | 20% DF CY 2019 | Building |  |  |  | Project Cost: | 7000000 | Target Completion Date: |  | Program: | 7000000 | Planned: |  | No. of Persons: |  | Fund re-aligned to GIDAS projects
Tagum City | Mankilam | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 7000000 | Revised: |  | No. of Man-days:
Tagum City | Mankilam | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual:
Tagum City | Mankilam | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Tagum City | Mankilam | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Tagum City | Mankilam | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | [7 empty] | Date Started:
New Corella | Suawon | 1st Eng'g. Dist. | On-going | 2019-12-09 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | Const. of 1 CL Bldg. @ Suawon ES, New Corella |  | 20% DF CY 2019 | Building | 82.65 | sq.m | Admin | Project Cost: | 1000000 | Target Completion Date: | 2020-04-21 23:46 | Program: | 1000000 | Planned: | 60.44% | No. of Persons: | 7 | On-going (Suspended last April 5, 2020 due to COVID; resumption order dated May 4, 2020)
New Corella | Suawon | 1st Eng'g. Dist. | On-going | 2019-12-09 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | [7 empty] | Project Engineer: | Miraflor | Revised Completion Date: | 2020-05-19 23:46 | Allotment: | 1000000 | Revised: |  | No. of Man-days: | 147
New Corella | Suawon | 1st Eng'g. Dist. | On-going | 2019-12-09 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | [7 empty] | Implementor: | PEO | No. of days suspended: | 28 | Disbursement: |  | Actual: | 60.44%
New Corella | Suawon | 1st Eng'g. Dist. | On-going | 2019-12-09 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | [7 empty] | Duration: | 135 | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | Suawon | 1st Eng'g. Dist. | On-going | 2019-12-09 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | [7 empty] | Date Allotment Released: | 2020-06-07 | Date completed:
New Corella | Suawon | 1st Eng'g. Dist. | On-going | 2019-12-09 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | [7 empty] | Date Started: | 2019-12-09
Talaingod | STo. Niño | 1st Eng'g. Dist. | On-going | 2020-03-02 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | Const. of Perimeter Fence at Sto. Niño Naseco Integrated School w/ Tugas Extension, Sto. Niño, Talaingod |  | 20% DF CY 2019 | Building |  | sq.m | Admin | Project Cost: | 2000000 | Target Completion Date: | 2020-06-09 23:46 | Program: | 2000000 | Planned: | 100% | No. of Persons: | 13 | On-going (Suspended last April 5, 2020 due to COVID; resumption order dated May 4, 2020)
Talaingod | STo. Niño | 1st Eng'g. Dist. | On-going | 2020-03-02 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | [7 empty] | Project Engineer: | Torrecampo | Revised Completion Date: | 2020-07-07 23:46 | Allotment: | 2000000 | Revised: | 55.86% | No. of Man-days: | 195
Talaingod | STo. Niño | 1st Eng'g. Dist. | On-going | 2020-03-02 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | [7 empty] | Implementor: | PEO | No. of days suspended: | 28 | Disbursement: | 1117200 | Actual: | 55.86%
Talaingod | STo. Niño | 1st Eng'g. Dist. | On-going | 2020-03-02 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | [7 empty] | Duration: | 100 | No. of days extended: |  |  |  | Slippage: | 0%
Talaingod | STo. Niño | 1st Eng'g. Dist. | On-going | 2020-03-02 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | [7 empty] | Date Allotment Released: | 2019-06-19 | Date completed:
Talaingod | STo. Niño | 1st Eng'g. Dist. | On-going | 2020-03-02 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | [7 empty] | Date Started: | 2020-03-02
Asuncion | New Bantayan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | Rehab. Of Multi-Purpose Hall, New Bantayan, Asuncion |  | 20% DF CY 2019 (STIMULUS) | Building |  |  | Admin | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | (Fund transferred to LGU.c /o Engr. Lilibeth Cuajao)
Asuncion | New Bantayan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 500000 | Revised: |  | No. of Man-days:
Asuncion | New Bantayan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Asuncion | New Bantayan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Asuncion | New Bantayan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Allotment Released: |  | Date completed:
Asuncion | New Bantayan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Started:
New Corella | El Salvador | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | Construction of Multi-Purpose Hall, El Salvador, New Corella |  | 20% DF CY 2019 (STIMULUS) | Building |  |  | MLGU | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Fund transferred to LGU March 23, 2019 c/o Engr. Dugoldugol
New Corella | El Salvador | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 500000 | Revised: |  | No. of Man-days:
New Corella | El Salvador | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
New Corella | El Salvador | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | El Salvador | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Allotment Released: |  | Date completed:
New Corella | El Salvador | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Started:
New Corella | Poblacion | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | Concreting of Drainage Canal , Pob., New Corella |  | 20% DF CY 2019 (STIMULUS) | Drainage |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Amended to Const. of 2 Storey Multi-Purpose Hall phase 3 (Brgy. Hall),Pob., New Corella (AIP 3rd revision CY 2019 / SB No. 4 CY 2019
New Corella | Poblacion | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 500000 | Revised: |  | No. of Man-days:
New Corella | Poblacion | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
New Corella | Poblacion | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | Poblacion | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Allotment Released: |  | Date completed:
New Corella | Poblacion | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Started:
New Corella | Cabidianan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | Rehab. Of Multi-Purpose Hall, Cabidianan, New Corella |  | 20% DF CY 2019 (STIMULUS) | Building |  |  | MLGU | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Fund transferred to LGU c/o Engr. Dugoldugol
New Corella | Cabidianan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 500000 | Revised: |  | No. of Man-days:
New Corella | Cabidianan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
New Corella | Cabidianan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | Cabidianan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Allotment Released: | 2019-02-20 | Date completed:
New Corella | Cabidianan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Started:
Talaingod | Gupitan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | Brgy. Electrification (Centro Gupitan), Gupitan, Talaingod |  | 20% DF CY 2019 (STIMULUS) | Electrification |  |  | MLGU | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Re-aligned to other stimulus projects that need additional funds to complete since the amount can not complete the project. Recommended for exact fund that can complete the project.
Talaingod | Gupitan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 500000 | Revised: |  | No. of Man-days:
Talaingod | Gupitan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Talaingod | Gupitan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Talaingod | Gupitan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Allotment Released: |  | Date completed:
Talaingod | Gupitan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Started:
Tagum City | Magugpo Poblacion | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | Rehab. of Evacuation Center, Magugpo Poblacion, Tagum City |  | 20% DF CY 2019 (STIMULUS) | Building |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Amended in the AIP 3rd revision CY 2019 /SB No. 4 CY 2019 changing the total project cost to P600,000.00
Tagum City | Magugpo Poblacion | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 500000 | Revised: |  | No. of Man-days:
Tagum City | Magugpo Poblacion | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Tagum City | Magugpo Poblacion | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Tagum City | Magugpo Poblacion | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Allotment Released: |  | Date completed:
Tagum City | Magugpo Poblacion | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Started:
Tagum City | San Agustin | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | Const. of Water System, San Agustin, Tagum City |  | 20% DF CY 2019 (STIMULUS) | Water System |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Re-aligned to other stimulus projects that need additional funds since there is no deed of donation for the proposed site.
Tagum City | San Agustin | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 500000 | Revised: |  | No. of Man-days:
Tagum City | San Agustin | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Tagum City | San Agustin | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Tagum City | San Agustin | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Allotment Released: |  | Date completed:
Tagum City | San Agustin | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Started:
Tagum City | Magugpo South | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | Const. of Brgy. Health Center, Magugpo South, Tagum City |  | 20% DF CY 2019 (STIMULUS) | Building |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Amended in the AIP 3rd revision CY 2019 /SB No. 4 CY 2019 changing the total project cost to P1,550,000.00
Tagum City | Magugpo South | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 500000 | Revised: |  | No. of Man-days:
Tagum City | Magugpo South | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Tagum City | Magugpo South | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Tagum City | Magugpo South | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Allotment Released: |  | Date completed:
Tagum City | Magugpo South | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Started:
Tagum City | Apokon | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | Rehab. Of Brgy. Health Center, Apokon, Tagum City |  | 20% DF CY 2019 (STIMULUS) | Building |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | For implementation (The brgy. council agreed not to pursue with the project if it will not be completed and needs additional funds)
Tagum City | Apokon | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 500000 | Revised: |  | No. of Man-days:
Tagum City | Apokon | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Tagum City | Apokon | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Tagum City | Apokon | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Allotment Released: | 2019-03-25 | Date completed:
Tagum City | Apokon | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Started:
Tagum City | Mankilam | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | Rehab. of Evacuation Center, Mankilam, Tagum City |  | 20% DF CY 2019 (STIMULUS) | Building |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | For implementation
Tagum City | Mankilam | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 500000 | Revised: |  | No. of Man-days:
Tagum City | Mankilam | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Tagum City | Mankilam | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Tagum City | Mankilam | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Allotment Released: | 2019-03-25 | Date completed:
Tagum City | Mankilam | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Started:
Tagum City | New Balamban | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | Rehab. of Evacuation Center, New Balambam, Tagum City |  | 20% DF CY 2019 (STIMULUS) | Building |  |  | Contract | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Final abstract #0320200899 (JJR Construction & Supply)
Tagum City | New Balamban | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 500000 | Revised: |  | No. of Man-days:
Tagum City | New Balamban | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Tagum City | New Balamban | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Tagum City | New Balamban | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Allotment Released: | 2019-09-10 | Date completed:
Tagum City | New Balamban | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Started:
Tagum City | Cuambogan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | Rehab. Of Multi-Purpose Hall, Cuambogan, Tagum City |  | 20% DF CY 2019 (STIMULUS) | Building |  |  | Contract | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | PO #2020031340 - JJR Construction
Tagum City | Cuambogan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 500000 | Revised: |  | No. of Man-days:
Tagum City | Cuambogan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Tagum City | Cuambogan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Tagum City | Cuambogan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Allotment Released: | 2019-09-10 | Date completed:
Tagum City | Cuambogan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Started:
Tagum City | Nueva Fuerza | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | Completion of Evacuation Center, Nueva Fuerza, Tagum City |  | 20% DF CY 2019 (STIMULUS) | Building |  |  | Contract | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | PO #2020031340 - JJR Construction
Tagum City | Nueva Fuerza | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 500000 | Revised: |  | No. of Man-days:
Tagum City | Nueva Fuerza | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Tagum City | Nueva Fuerza | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Tagum City | Nueva Fuerza | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Allotment Released: | 2019-09-10 | Date completed:
Tagum City | Nueva Fuerza | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Started:
Tagum City | Busaon | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | Completion. of Water System , Busaon, Tagum City |  | 20% DF CY 2019 (STIMULUS) | Water System |  |  | Contract | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | For implementation
Tagum City | Busaon | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 500000 | Revised: |  | No. of Man-days:
Tagum City | Busaon | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Tagum City | Busaon | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Tagum City | Busaon | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Allotment Released: | 2019-09-10 | Date completed:
Tagum City | Busaon | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Started:
Tagum City | Bincungan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | Const. of Drainage Canal, Bincungan, Tagum City |  | 20% DF CY 2019 (STIMULUS) | Drainage |  |  | Contract | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | PO #2020031340 - JJR Construction
Tagum City | Bincungan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 500000 | Revised: |  | No. of Man-days:
Tagum City | Bincungan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Tagum City | Bincungan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Tagum City | Bincungan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Allotment Released: | 2019-09-10 | Date completed:
Tagum City | Bincungan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Started:
Tagum City | Magugpo North | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | Rehab. of Evacuation Center, Magugpo North, Tagum City |  | 20% DF CY 2019 (STIMULUS) | Building |  |  | Contract | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | PO #2020031340 - JJR Construction
Tagum City | Magugpo North | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 500000 | Revised: |  | No. of Man-days:
Tagum City | Magugpo North | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Tagum City | Magugpo North | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Tagum City | Magugpo North | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Allotment Released: | 2019-09-10 | Date completed:
Tagum City | Magugpo North | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Started:
San Isidro | Pinamuno | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | Rehab. Of Water System at Purok Cabang & Mangga , Pinamuno, San Isidro |  | 20% DF CY 2019 (STIMULUS) | Water System |  |  | Contract | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | PO# 2020010025 (RLHV)
San Isidro | Pinamuno | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 500000 | Revised: |  | No. of Man-days:
San Isidro | Pinamuno | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
San Isidro | Pinamuno | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
San Isidro | Pinamuno | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Allotment Released: | 2019-12-06 | Date completed:
San Isidro | Pinamuno | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Started:
San Isidro | Igangon | 1st Eng'g. Dist. | On-going | 2020-05-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | Rehab. Of Water System , Igangon, San Isidro |  | 20% DF CY 2019 (STIMULUS) | Water System |  | ln.m | Admin | Project Cost: | 500000 | Target Completion Date: | 2020-07-17 | Program: | 500000 | Planned: | 12.26% | No. of Persons: | 25 | On-going
San Isidro | Igangon | 1st Eng'g. Dist. | On-going | 2020-05-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Project Engineer: | Kabinge | Revised Completion Date: | 2020-07-17 | Allotment: | 500000 | Revised: | 93.09% | No. of Man-days: | 375
San Isidro | Igangon | 1st Eng'g. Dist. | On-going | 2020-05-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: | 46.42%
San Isidro | Igangon | 1st Eng'g. Dist. | On-going | 2020-05-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Duration: | 60 | No. of days extended: |  |  |  | Slippage: | 93.09%
San Isidro | Igangon | 1st Eng'g. Dist. | On-going | 2020-05-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Allotment Released: | 2019-05-29 | Date completed:
San Isidro | Igangon | 1st Eng'g. Dist. | On-going | 2020-05-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Started: | 2020-05-18
New Corella | Del Monte | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | Rural Electrification , Del Monte, New Corella |  | 20% DF CY 2019 (STIMULUS) | Electrification |  |  |  | Project Cost: | 3000000 | Target Completion Date: |  | Program: | 3000000 | Planned: |  | No. of Persons: |  | For implementation
New Corella | Del Monte | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Project Engineer: | P.Bueno | Revised Completion Date: | 0 | Allotment: | 3000000 | Revised: |  | No. of Man-days:
New Corella | Del Monte | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
New Corella | Del Monte | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | Del Monte | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Allotment Released: |  | Date completed:
New Corella | Del Monte | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Started:
New Corella | San Roque | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | Rural Electrification at St. Bundok, San Roque, New Corella |  | 20% DF CY 2019 (STIMULUS) | Electrification |  |  |  | Project Cost: | 1000000 | Target Completion Date: |  | Program: | 1000000 | Planned: |  | No. of Persons: |  | Abstract # 0320201453
New Corella | San Roque | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Project Engineer: | P.Bueno | Revised Completion Date: | 0 | Allotment: | 1000000 | Revised: |  | No. of Man-days:
New Corella | San Roque | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
New Corella | San Roque | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | San Roque | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Allotment Released: |  | Date completed:
New Corella | San Roque | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Started:
Tagum City | Mankilam | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Anti - Crime & Government Itegration Project | Construction of Bahay Silangan for Reformation of Drug Personalities within The Military Camp/barracks, Brgy. Mankilam, Tagum City |  | 20% DF CY 2019 | Building |  |  |  | Project Cost: | 5000000 | Target Completion Date: |  | Program: | 5000000 | Planned: |  | No. of Persons: |  | Abstract #0620202232 - Post Qualification on process (ZULAR-A)
Tagum City | Mankilam | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Anti - Crime & Government Itegration Project | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 5000000 | Revised: |  | No. of Man-days:
Tagum City | Mankilam | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Anti - Crime & Government Itegration Project | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Tagum City | Mankilam | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Anti - Crime & Government Itegration Project | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Tagum City | Mankilam | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Anti - Crime & Government Itegration Project | [7 empty] | Date Allotment Released: |  | Date completed:
Tagum City | Mankilam | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Anti - Crime & Government Itegration Project | [7 empty] | Date Started:
New Corella | Poblacion | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (Special Protection & Intervention Program ) | Const. of Multi-Purpose Covered Court/Evacuation Center Ph. I, Duterte St., Poblacion, New Corella |  | 20% DF CY 2019 | Building |  |  |  | Project Cost: | 2000000 | Target Completion Date: |  | Program: | 2000000 | Planned: |  | No. of Persons: |  | Abstract #0720202481 - Post Qualification on pprocess (Royal Summit Infinity)
New Corella | Poblacion | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (Special Protection & Intervention Program ) | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 2000000 | Revised: |  | No. of Man-days:
New Corella | Poblacion | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (Special Protection & Intervention Program ) | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual:
New Corella | Poblacion | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (Special Protection & Intervention Program ) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | Poblacion | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (Special Protection & Intervention Program ) | [7 empty] | Date Allotment Released: |  | Date completed:
New Corella | Poblacion | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (Special Protection & Intervention Program ) | [7 empty] | Date Started:
New Corella | Poblacion | 1st Eng'g. Dist. | On-going | 2019-12-02 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Residential Care Facilities | Construction of Multi-Purpose Covered Court/Evacuation, Bahay Pag-Asa, New Corella, Ph.II (TF - P500,000.00) |  | 20% DF CY 2019 & TRUST FUND | Building |  | sq.m | Admin | Project Cost: | 2500000 | Target Completion Date: | 2020-04-15 | Program: | 2500000 | Planned: | 79.89% | No. of Persons: | 12 | On-going (Suspended last April 5, 2020 due to COVID; resumption order dated May 4, 2020)
New Corella | Poblacion | 1st Eng'g. Dist. | On-going | 2019-12-02 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Residential Care Facilities | [7 empty] | Project Engineer: | Mayang | Revised Completion Date: | 2020-08-30 | Allotment: | 2500000 | Revised: |  | No. of Man-days: | 180
New Corella | Poblacion | 1st Eng'g. Dist. | On-going | 2019-12-02 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Residential Care Facilities | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: |  | Actual: | 79.89%
New Corella | Poblacion | 1st Eng'g. Dist. | On-going | 2019-12-02 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Residential Care Facilities | [7 empty] | Duration: | 135 | No. of days extended: | 110 |  |  | Slippage: | 0%
New Corella | Poblacion | 1st Eng'g. Dist. | On-going | 2019-12-02 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Residential Care Facilities | [7 empty] | Date Allotment Released: | 2019-06-19 | Date completed:
New Corella | Poblacion | 1st Eng'g. Dist. | On-going | 2019-12-02 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Residential Care Facilities | [7 empty] | Date Started: | 2019-12-02
Provincewide | Provincewide | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Residential Care Facilities | Const. in Progress - Bldgs. And Other Structures |  | 20% DF CY 2019 | Building |  |  |  | Project Cost: | 2500000 | Target Completion Date: |  | Program: | 2500000 | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
Provincewide | Provincewide | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Residential Care Facilities | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 2500000 | Revised: |  | No. of Man-days:
Provincewide | Provincewide | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Residential Care Facilities | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual:
Provincewide | Provincewide | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Residential Care Facilities | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Provincewide | Provincewide | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Residential Care Facilities | [7 empty] | Date Allotment Released: |  | Date completed:
Provincewide | Provincewide | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Residential Care Facilities | [7 empty] | Date Started:
New Corella | Limbaan | 1st Eng'g. Dist. | On-going | 2019-03-20 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DISASTER PREVENTION AND MITIGATION - Flood Control and Slope Protection LS - P3,000,000.00 | Desilting of Limbaan Creek, New Corella |  | 5% CALAMITY FUND CY 2019 | creeks and canals deislted |  | ln.m | Admin | Project Cost: | 2000000 | Target Completion Date: | 2019-12-02 | Program: | 2000000 | Planned: |  | No. of Persons: |  | Suspended
New Corella | Limbaan | 1st Eng'g. Dist. | On-going | 2019-03-20 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DISASTER PREVENTION AND MITIGATION - Flood Control and Slope Protection LS - P3,000,000.00 | [7 empty] | Project Engineer: | Pilotos | Revised Completion Date: | 2019-12-02 | Allotment: | 2000000 | Revised: |  | No. of Man-days:
New Corella | Limbaan | 1st Eng'g. Dist. | On-going | 2019-03-20 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DISASTER PREVENTION AND MITIGATION - Flood Control and Slope Protection LS - P3,000,000.00 | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual:
New Corella | Limbaan | 1st Eng'g. Dist. | On-going | 2019-03-20 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DISASTER PREVENTION AND MITIGATION - Flood Control and Slope Protection LS - P3,000,000.00 | [7 empty] | Duration: | 257 | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | Limbaan | 1st Eng'g. Dist. | On-going | 2019-03-20 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DISASTER PREVENTION AND MITIGATION - Flood Control and Slope Protection LS - P3,000,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
New Corella | Limbaan | 1st Eng'g. Dist. | On-going | 2019-03-20 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DISASTER PREVENTION AND MITIGATION - Flood Control and Slope Protection LS - P3,000,000.00 | [7 empty] | Date Started: | 2019-03-20
kapalong | Mabantao-Florida | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Revitment of Dike and Slope Protection LS - P3,000,000.00 | Slope Protection Along Kapalong-Mabantao, Florida |  | 5% CALAMITY FUND CY 2019 | creeks and canals deislted |  |  |  | Project Cost: | 1000000 | Target Completion Date: |  | Program: | 1000000 | Planned: |  | No. of Persons: |  | For cancellation funded to DPWH. Budget Transferred to 5% Calamity Fund- Rehab and Recovery
kapalong | Mabantao-Florida | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Revitment of Dike and Slope Protection LS - P3,000,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 1000000 | Revised: |  | No. of Man-days:
kapalong | Mabantao-Florida | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Revitment of Dike and Slope Protection LS - P3,000,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
kapalong | Mabantao-Florida | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Revitment of Dike and Slope Protection LS - P3,000,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
kapalong | Mabantao-Florida | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Revitment of Dike and Slope Protection LS - P3,000,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
kapalong | Mabantao-Florida | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Revitment of Dike and Slope Protection LS - P3,000,000.00 | [7 empty] | Date Started:
Asuncion | New Boholano-New Loon | 1st Eng'g. Dist. | On-going | 2019-11-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Improvement of bridges and cross drainage LS - P3,000,000.00 | Impv't. of Jct. New Boholano - New Loon Cross Drainage |  | 5% CALAMITY FUND CY 2019 | Drainage |  | km | Admin | Project Cost: | 2000000 | Target Completion Date: | 2020-02-16 | Program: | 2000000 | Planned: | 42.27% | No. of Persons: |  | Suspended due to availability of equipment
Asuncion | New Boholano-New Loon | 1st Eng'g. Dist. | On-going | 2019-11-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Improvement of bridges and cross drainage LS - P3,000,000.00 | [7 empty] | Project Engineer: | Pilotos | Revised Completion Date: | 2020-02-16 | Allotment: | 2000000 | Revised: |  | No. of Man-days:
Asuncion | New Boholano-New Loon | 1st Eng'g. Dist. | On-going | 2019-11-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Improvement of bridges and cross drainage LS - P3,000,000.00 | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: | 31.7%
Asuncion | New Boholano-New Loon | 1st Eng'g. Dist. | On-going | 2019-11-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Improvement of bridges and cross drainage LS - P3,000,000.00 | [7 empty] | Duration: | 90 | No. of days extended: |  |  |  | Slippage: | -10.57%
Asuncion | New Boholano-New Loon | 1st Eng'g. Dist. | On-going | 2019-11-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Improvement of bridges and cross drainage LS - P3,000,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Asuncion | New Boholano-New Loon | 1st Eng'g. Dist. | On-going | 2019-11-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Improvement of bridges and cross drainage LS - P3,000,000.00 | [7 empty] | Date Started: | 2019-11-18
Asuncion | Saug Sonlon-Longanapan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Improvement of bridges and cross drainage LS - P3,000,000.00 | Impv't. of Jct. Saug-Sonlon-Bdry. Longanapan Cross Drainage |  | 5% CALAMITY FUND CY 2019 | Road |  |  |  | Project Cost: | 1000000 | Target Completion Date: |  | Program: | 1000000 | Planned: |  | No. of Persons: |  | For implementation
Asuncion | Saug Sonlon-Longanapan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Improvement of bridges and cross drainage LS - P3,000,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 1000000 | Revised: |  | No. of Man-days:
Asuncion | Saug Sonlon-Longanapan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Improvement of bridges and cross drainage LS - P3,000,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Asuncion | Saug Sonlon-Longanapan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Improvement of bridges and cross drainage LS - P3,000,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Asuncion | Saug Sonlon-Longanapan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Improvement of bridges and cross drainage LS - P3,000,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Asuncion | Saug Sonlon-Longanapan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Improvement of bridges and cross drainage LS - P3,000,000.00 | [7 empty] | Date Started:
Tagum City | San Miguel | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DISASTER REHABILITATION & RECOVERY PROGRAM - Building Back Better Project | Disiltation of Tagum Creek |  | 5% CALAMITY FUND CY 2019 | Creek |  |  | Admin | Project Cost: | 2000000 | Target Completion Date: |  | Program: | 2000000 | Planned: |  | No. of Persons: |  | Waiting for the delivery of materials
Tagum City | San Miguel | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DISASTER REHABILITATION & RECOVERY PROGRAM - Building Back Better Project | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 2000000 | Revised: |  | No. of Man-days:
Tagum City | San Miguel | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DISASTER REHABILITATION & RECOVERY PROGRAM - Building Back Better Project | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual:
Tagum City | San Miguel | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DISASTER REHABILITATION & RECOVERY PROGRAM - Building Back Better Project | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Tagum City | San Miguel | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DISASTER REHABILITATION & RECOVERY PROGRAM - Building Back Better Project | [7 empty] | Date Allotment Released: |  | Date completed:
Tagum City | San Miguel | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DISASTER REHABILITATION & RECOVERY PROGRAM - Building Back Better Project | [7 empty] | Date Started:
Asuncion | Pamacaun-Lasang-banate | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DISASTER REHABILITATION & RECOVERY PROGRAM - Building Back Better Project | Rehabilitation of Pamacaun-Lasang-Banate Provincial Road |  | 5% CALAMITY FUND CY 2019 | Road |  |  | Admin | Project Cost: | 1500000 | Target Completion Date: |  | Program: | 1500000 | Planned: |  | No. of Persons: |  | For implementation
Asuncion | Pamacaun-Lasang-banate | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DISASTER REHABILITATION & RECOVERY PROGRAM - Building Back Better Project | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 1500000 | Revised: |  | No. of Man-days:
Asuncion | Pamacaun-Lasang-banate | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DISASTER REHABILITATION & RECOVERY PROGRAM - Building Back Better Project | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Asuncion | Pamacaun-Lasang-banate | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DISASTER REHABILITATION & RECOVERY PROGRAM - Building Back Better Project | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Asuncion | Pamacaun-Lasang-banate | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DISASTER REHABILITATION & RECOVERY PROGRAM - Building Back Better Project | [7 empty] | Date Allotment Released: |  | Date completed:
Asuncion | Pamacaun-Lasang-banate | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DISASTER REHABILITATION & RECOVERY PROGRAM - Building Back Better Project | [7 empty] | Date Started:
New Corella | Del Pilar | 1st Eng'g. Dist. | On-going | 2020-02-17 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DISASTER REHABILITATION & RECOVERY PROGRAM - Building Back Better Project | Rehabilitation of Del Pilar Jct. Silangan |  | 5% CALAMITY FUND CY 2019 | Road |  | km | Admin | Project Cost: | 1500000 | Target Completion Date: | 2020-03-27 23:46 | Program: | 1500000 | Planned: | 81.11% | No. of Persons: | 4 | Suspended dated June 1, 2020 due to rainy days
New Corella | Del Pilar | 1st Eng'g. Dist. | On-going | 2020-02-17 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DISASTER REHABILITATION & RECOVERY PROGRAM - Building Back Better Project | [7 empty] | Project Engineer: | Gone | Revised Completion Date: | 2020-06-15 23:46 | Allotment: | 1500000 | Revised: |  | No. of Man-days: | 40
New Corella | Del Pilar | 1st Eng'g. Dist. | On-going | 2020-02-17 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DISASTER REHABILITATION & RECOVERY PROGRAM - Building Back Better Project | [7 empty] | Implementor: | PEO | No. of days suspended: | 29 | Disbursement: |  | Actual: | 81.11%
New Corella | Del Pilar | 1st Eng'g. Dist. | On-going | 2020-02-17 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DISASTER REHABILITATION & RECOVERY PROGRAM - Building Back Better Project | [7 empty] | Duration: | 40 | No. of days extended: | 51 |  |  | Slippage: | 0%
New Corella | Del Pilar | 1st Eng'g. Dist. | On-going | 2020-02-17 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DISASTER REHABILITATION & RECOVERY PROGRAM - Building Back Better Project | [7 empty] | Date Allotment Released: | 2019-07-26 | Date completed:
New Corella | Del Pilar | 1st Eng'g. Dist. | On-going | 2020-02-17 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DISASTER REHABILITATION & RECOVERY PROGRAM - Building Back Better Project | [7 empty] | Date Started: | 2020-02-17
kapalong | Mabantao-Florida | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DISASTER REHABILITATION & RECOVERY PROGRAM - Building Back Better Project | Rehabilitation of Libuganon River along Kapalong Mabantao-Florida Provincial Road |  | 5% CALAMITY FUND CY 2019 | Road |  |  | Admin | Project Cost: | 900000 |  |  | Program: | 900000 | Planned: |  | No. of Persons: |  | For implementation
kapalong | Mabantao-Florida | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DISASTER REHABILITATION & RECOVERY PROGRAM - Building Back Better Project | [7 empty] | Project Engineer: |  |  |  | Allotment: | 900000 | Revised: |  | No. of Man-days:
kapalong | Mabantao-Florida | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DISASTER REHABILITATION & RECOVERY PROGRAM - Building Back Better Project | [7 empty] | Implementor: |  |  |  | Disbursement: |  | Actual:
kapalong | Mabantao-Florida | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DISASTER REHABILITATION & RECOVERY PROGRAM - Building Back Better Project | [7 empty] | Duration: | [5 empty] | Slippage: | 0%
kapalong | Mabantao-Florida | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DISASTER REHABILITATION & RECOVERY PROGRAM - Building Back Better Project | [7 empty] | Date Allotment Released:
kapalong | Mabantao-Florida | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DISASTER REHABILITATION & RECOVERY PROGRAM - Building Back Better Project | [7 empty] | Date Started:
New Corella | Mesaoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DISASTER REHABILITATION & RECOVERY PROGRAM - Building Back Better Project | Rehabilitation of Mesaoy-Jct. Mahayahay Road |  | 5% CALAMITY FUND CY 2019 | Road |  |  | Admin | Project Cost: | 1000000 | Target Completion Date: |  | Program: | 1000000 | Planned: |  | No. of Persons: |  | For implementation
New Corella | Mesaoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DISASTER REHABILITATION & RECOVERY PROGRAM - Building Back Better Project | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 1000000 | Revised: |  | No. of Man-days:
New Corella | Mesaoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DISASTER REHABILITATION & RECOVERY PROGRAM - Building Back Better Project | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
New Corella | Mesaoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DISASTER REHABILITATION & RECOVERY PROGRAM - Building Back Better Project | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | Mesaoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DISASTER REHABILITATION & RECOVERY PROGRAM - Building Back Better Project | [7 empty] | Date Allotment Released: |  | Date completed:
New Corella | Mesaoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DISASTER REHABILITATION & RECOVERY PROGRAM - Building Back Better Project | [7 empty] | Date Started:
New Corella | Sta. Fe - Mambing | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DISASTER REHABILITATION & RECOVERY PROGRAM - Building Back Better Project | Rehabilitation of Sta. Fe- Mambing Road & Slope Protection |  | 5% CALAMITY FUND CY 2019 | Road |  |  | Admin | Project Cost: | 1320000 | Target Completion Date: |  | Program: | 1320000 | Planned: |  | No. of Persons: |  | For implementation
New Corella | Sta. Fe - Mambing | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DISASTER REHABILITATION & RECOVERY PROGRAM - Building Back Better Project | [7 empty] | Project Engineer: | Pilotos | Revised Completion Date: | 0 | Allotment: | 1320000 | Revised: |  | No. of Man-days:
New Corella | Sta. Fe - Mambing | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DISASTER REHABILITATION & RECOVERY PROGRAM - Building Back Better Project | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual:
New Corella | Sta. Fe - Mambing | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DISASTER REHABILITATION & RECOVERY PROGRAM - Building Back Better Project | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | Sta. Fe - Mambing | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DISASTER REHABILITATION & RECOVERY PROGRAM - Building Back Better Project | [7 empty] | Date Allotment Released: |  | Date completed:
New Corella | Sta. Fe - Mambing | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DISASTER REHABILITATION & RECOVERY PROGRAM - Building Back Better Project | [7 empty] | Date Started:
Asuncion | San Agustin | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DISASTER REHABILITATION & RECOVERY PROGRAM - Building Back Better Project | Rehabilitation of Canal Lining and Slope Protection at San Agustin E/S, San Agustin, Tagum City |  | 5% CALAMITY FUND CY 2019 | Drainage |  |  | Admin | Project Cost: | 350000 | Target Completion Date: |  | Program: | 350000 | Planned: |  | No. of Persons: |  | For implementation
Asuncion | San Agustin | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DISASTER REHABILITATION & RECOVERY PROGRAM - Building Back Better Project | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 350000 | Revised: |  | No. of Man-days:
Asuncion | San Agustin | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DISASTER REHABILITATION & RECOVERY PROGRAM - Building Back Better Project | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Asuncion | San Agustin | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DISASTER REHABILITATION & RECOVERY PROGRAM - Building Back Better Project | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Asuncion | San Agustin | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DISASTER REHABILITATION & RECOVERY PROGRAM - Building Back Better Project | [7 empty] | Date Allotment Released: |  | Date completed:
Asuncion | San Agustin | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DISASTER REHABILITATION & RECOVERY PROGRAM - Building Back Better Project | [7 empty] | Date Started:
Asuncion | Doña Andrea | 1st Eng'g. Dist. | On-going | 2020-02-17 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DILG | Construction of Halfway House, Brgy. Doña Andrea, Asuncion |  | DILG | Building |  | sq.m | Admin | Project Cost: | 5000000 | Target Completion Date: | 2020-08-14 23:59 | Program: | 5000000 | Planned: | 54.84% | No. of Persons: | 38 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 6, 2020)
Asuncion | Doña Andrea | 1st Eng'g. Dist. | On-going | 2020-02-17 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DILG | [7 empty] | Project Engineer: | Dadula | Revised Completion Date: | 2020-09-12 23:59 | Allotment: | 5000000 | Revised: |  | No. of Man-days: | 1178
Asuncion | Doña Andrea | 1st Eng'g. Dist. | On-going | 2020-02-17 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DILG | [7 empty] | Implementor: | PEO | No. of days suspended: | 29 | Disbursement: |  | Actual: | 54.84%
Asuncion | Doña Andrea | 1st Eng'g. Dist. | On-going | 2020-02-17 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DILG | [7 empty] | Duration: | 180 | No. of days extended: |  |  |  | Slippage: | 0%
Asuncion | Doña Andrea | 1st Eng'g. Dist. | On-going | 2020-02-17 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DILG | [7 empty] | Date Allotment Released: | CY 2019 | Date completed:
Asuncion | Doña Andrea | 1st Eng'g. Dist. | On-going | 2020-02-17 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DILG | [7 empty] | Date Started: | 2020-02-17
Asuncion | Cambanogoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Lot Purchase | Purchase of Lot for Cemetery, Cambanogoy, Asuncion |  | SUPPLEMENTAL BUDGET NO. 1 CY 2019 (STIMULUS) | Land |  |  |  | Project Cost: | 1500000 | Target Completion Date: |  | Program: | 1500000 | Planned: |  | No. of Persons: |  | Documents for fund transfer to be complied by the LGUs. Letter sent dated June 18, 2019
Asuncion | Cambanogoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Lot Purchase | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 1500000 | Revised: |  | No. of Man-days:
Asuncion | Cambanogoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Lot Purchase | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Asuncion | Cambanogoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Lot Purchase | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Asuncion | Cambanogoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Lot Purchase | [7 empty] | Date Allotment Released: |  | Date completed:
Asuncion | Cambanogoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Lot Purchase | [7 empty] | Date Started:
New Corella | San Roque | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Lot Purchase | Purchase of Lot for Cemetery, San Roque, New Corella |  | SUPPLEMENTAL BUDGET NO. 1 CY 2019 (STIMULUS) | Land |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Documents for fund transfer to be complied by the LGUs. Letter sent dated June 18, 2019
New Corella | San Roque | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Lot Purchase | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 500000 | Revised: |  | No. of Man-days:
New Corella | San Roque | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Lot Purchase | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
New Corella | San Roque | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Lot Purchase | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | San Roque | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Lot Purchase | [7 empty] | Date Allotment Released: |  | Date completed:
New Corella | San Roque | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Lot Purchase | [7 empty] | Date Started:
Asuncion | Sagayen | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | Rehab/Impvt of Gymnasium, Sagayen, Asuncion |  | SUPPLEMENTAL BUDGET NO. 1 CY 2019 (STIMULUS) | Building |  |  |  | Project Cost: | 1500000 | Target Completion Date: |  | Program: | 1500000 | Planned: |  | No. of Persons: |  | Final Abstract # 0320200900 (Alpebel Builders & Supply Corp.)
Asuncion | Sagayen | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 1500000 | Revised: |  | No. of Man-days:
Asuncion | Sagayen | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Asuncion | Sagayen | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Asuncion | Sagayen | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Allotment Released: |  | Date completed:
Asuncion | Sagayen | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Started:
New Corella | New Sambog | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | Purchase of Lot for Resettlement Site, New Sambog, New Corella |  | SUPPLEMENTAL BUDGET NO. 1 CY 2019 (STIMULUS) | Land |  |  |  | Project Cost: | 1500000 | Target Completion Date: |  | Program: | 1500000 | Planned: |  | No. of Persons: |  | for fund transfer. Waiting for LGU documents. Liquidation of previous fund transfer for the water system project of LGU.
New Corella | New Sambog | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 1500000 | Revised: |  | No. of Man-days:
New Corella | New Sambog | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
New Corella | New Sambog | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | New Sambog | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Allotment Released: |  | Date completed:
New Corella | New Sambog | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Started:
Asuncion | Sagayen | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | Installation of Street Lights at Prk 1,2,3,4, Sagayen, Asuncion |  | SUPPLEMENTAL BUDGET NO. 1 CY 2019 (STIMULUS) | Electrification |  |  |  | Project Cost: | 1000000 | Target Completion Date: |  | Program: | 1000000 | Planned: |  | No. of Persons: |  | Purchase Order # 2019113377 (Tagum Builders)
Asuncion | Sagayen | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 1000000 | Revised: |  | No. of Man-days:
Asuncion | Sagayen | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Asuncion | Sagayen | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Asuncion | Sagayen | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Allotment Released: |  | Date completed:
Asuncion | Sagayen | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Started:
Asuncion | Concepcion | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | Rehab/Imprvt. Of FMR, Prk 3,7, & 8, Concepcion, Asuncion |  | SUPPLEMENTAL BUDGET NO. 1 CY 2019 (STIMULUS) | Road |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Waiting for equipment availability as of Feb. 5, 2020 report submitted by Engr. Cuajao
Asuncion | Concepcion | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 500000 | Revised: |  | No. of Man-days:
Asuncion | Concepcion | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Asuncion | Concepcion | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Asuncion | Concepcion | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Allotment Released: |  | Date completed:
Asuncion | Concepcion | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Started:
New Corella | San Jose | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | Farm to Market Road, San Jose, New Corella |  | SUPPLEMENTAL BUDGET NO. 1 CY 2019 (STIMULUS) | Road |  |  |  | Project Cost: | 2000000 | Target Completion Date: |  | Program: | 2000000 | Planned: |  | No. of Persons: |  | For cancellation
New Corella | San Jose | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 2000000 | Revised: |  | No. of Man-days:
New Corella | San Jose | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
New Corella | San Jose | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | San Jose | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Allotment Released: |  | Date completed:
New Corella | San Jose | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Started:
New Corella | New Sambog | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | Const. of Water System, New Sambog, New Corella |  | SUPPLEMENTAL BUDGET NO. 1 CY 2019 (STIMULUS) | Water System |  |  | MLGU | Project Cost: | 1000000 | Target Completion Date: |  | Program: | 1000000 | Planned: |  | No. of Persons: |  | Fund transferred to LGU
New Corella | New Sambog | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 1000000 | Revised: |  | No. of Man-days:
New Corella | New Sambog | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
New Corella | New Sambog | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | New Sambog | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Allotment Released: |  | Date completed:
New Corella | New Sambog | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Started:
New Corella | Limbaan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | Const. of Drainage Canal from Prk. 3, 1-A, 2-A to Prk 1-B, Brgy Site (Ph. 2), Limbaan, New Corella |  | SUPPLEMENTAL BUDGET NO. 1 CY 2019 (STIMULUS) | Flood Control - Drainage |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | POW preparation on going c/o PDPM
New Corella | Limbaan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 500000 | Revised: |  | No. of Man-days:
New Corella | Limbaan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
New Corella | Limbaan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | Limbaan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Allotment Released: |  | Date completed:
New Corella | Limbaan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Started:
New Corella | Patrocenio | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | Const. of FMR from Prk 1 to Sitio Magsaysay via Pundol & Prk 4, Patrocenio, New Corella |  | SUPPLEMENTAL BUDGET NO. 1 CY 2019 (STIMULUS) | Road |  |  |  | Project Cost: | 2000000 | Target Completion Date: |  | Program: | 2000000 | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
New Corella | Patrocenio | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 2000000 | Revised: |  | No. of Man-days:
New Corella | Patrocenio | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
New Corella | Patrocenio | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | Patrocenio | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Allotment Released: |  | Date completed:
New Corella | Patrocenio | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Started:
New Corella | San Jose | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | Const. of Multi-Purpose Pavement, San Jose, New Corella |  | SUPPLEMENTAL BUDGET NO. 1 CY 2019 (STIMULUS) | Building |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | POW approved but allotment not yet requested waiting for deed of donation c/o Engr. Canillada
New Corella | San Jose | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 500000 | Revised: |  | No. of Man-days:
New Corella | San Jose | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
New Corella | San Jose | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | San Jose | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Allotment Released: |  | Date completed:
New Corella | San Jose | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Started:
Asuncion | Buan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | Const. of Multipurpose Covered Court, Buan, Asuncion |  | SUPPLEMENTAL BUDGET NO. 1 CY 2019 (STIMULUS) | Covered Court |  |  | MLGU | Project Cost: | 2500000 | Target Completion Date: |  | Program: | 2500000 | Planned: |  | No. of Persons: |  | Fund transferred to LGU
Asuncion | Buan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 2500000 | Revised: |  | No. of Man-days:
Asuncion | Buan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Asuncion | Buan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Asuncion | Buan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Allotment Released: | 2019-06-26 | Date completed:
Asuncion | Buan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Started:
Asuncion | Pamacaun | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | Const. of Multipurpose Covered Court, Pamacaun, Asuncion |  | SUPPLEMENTAL BUDGET NO. 1 CY 2019 (STIMULUS) | Covered Court |  |  | MLGU | Project Cost: | 2500000 | Target Completion Date: |  | Program: | 2500000 | Planned: |  | No. of Persons: |  | Fund transferred to LGU
Asuncion | Pamacaun | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 2500000 | Revised: |  | No. of Man-days:
Asuncion | Pamacaun | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Asuncion | Pamacaun | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Asuncion | Pamacaun | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Allotment Released: | 2019-05-29 | Date completed:
Asuncion | Pamacaun | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Started:
New Corella | Poblacion | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | Const. of 2 Storey Multi purpose Hall Ph.2 (Brgy. Hall) , Poblacion, New Corella |  | SUPPLEMENTAL BUDGET NO. 1 CY 2019 (STIMULUS) | Building |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
New Corella | Poblacion | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 500000 | Revised: |  | No. of Man-days:
New Corella | Poblacion | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
New Corella | Poblacion | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | Poblacion | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Allotment Released: |  | Date completed:
New Corella | Poblacion | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Started:
New Corella | Patrocenio | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | Expansion of Multi-Purpose Hall ( Brgy. Hall), Patrocenio, New Corella |  | SUPPLEMENTAL BUDGET NO. 1 CY 2019 (STIMULUS) | Building |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Purchase Order # 2020020796 (JJR Construction)
New Corella | Patrocenio | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 500000 | Revised: |  | No. of Man-days:
New Corella | Patrocenio | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
New Corella | Patrocenio | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | Patrocenio | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Allotment Released: |  | Date completed:
New Corella | Patrocenio | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Started:
New Corella | Poblacion | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | Rehabilitation of Water System in PEEDO-LPRRC, Brgy. Poblacion, New Corella |  | SUPPLEMENTAL BUDGET NO. 1 CY 2019 (STIMULUS) | Water System |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Purchase Order # 2020010009 (ANCOR Water Resources)
New Corella | Poblacion | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 500000 | Revised: |  | No. of Man-days:
New Corella | Poblacion | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
New Corella | Poblacion | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | Poblacion | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Allotment Released: |  | Date completed:
New Corella | Poblacion | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Started:
Talaingod | Salawao-Sto. Niño | 1st Eng'g. Dist. | On-going | 2020-06-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | Provincial Livestock & Poultry Multiplier Farm Road Network Construction, Sitio Salawao, Sto. Niño, Talaingod |  | SUPPLEMENTAL BUDGET NO. 1 CY 2019 (STIMULUS) | Conc. Pavement |  | sq.m | Admin | Project Cost: | 5500000 | Target Completion Date: | 2020-07-13 23:46 | Program: | 5500000 | Planned: | 30.06% | No. of Persons: | 15 | On-going (For time extension)
Talaingod | Salawao-Sto. Niño | 1st Eng'g. Dist. | On-going | 2020-06-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Project Engineer: | Pasiona/Juan | Revised Completion Date: | 2020-08-10 23:46 | Allotment: | 5500000 | Revised: |  | No. of Man-days: | 225
Talaingod | Salawao-Sto. Niño | 1st Eng'g. Dist. | On-going | 2020-06-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Implementor: | PEO | No. of days suspended: | 28 | Disbursement: | 1653300 | Actual: | 30.06%
Talaingod | Salawao-Sto. Niño | 1st Eng'g. Dist. | On-going | 2020-06-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Duration: | 120 | No. of days extended: |  |  |  | Slippage: | 0%
Talaingod | Salawao-Sto. Niño | 1st Eng'g. Dist. | On-going | 2020-06-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Allotment Released: | CY 2019 | Date completed:
Talaingod | Salawao-Sto. Niño | 1st Eng'g. Dist. | On-going | 2020-06-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Started: | 2020-03-16
Talaingod | Tapayanon | 1st Eng'g. Dist. | On-going | 2019-11-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | Proposed Road Opening of Tawinian-Tapayanon Road Section |  | SUPPLEMENTAL BUDGET NO. 4 CY 2019 (STIMULUS) | Road |  | km | Admin | Project Cost: | 10000000 | Target Completion Date: | 2020-09-18 23:46 | Program: | 10000000 | Planned: | 27.08% | No. of Persons: | 5 | On-going (Suspended last April 5, 2020 due to COVID; resumption order dated May 4, 2020); Equipment Rental 1 unit Backhoe (Bidding July 16, 2020)
Talaingod | Tapayanon | 1st Eng'g. Dist. | On-going | 2019-11-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Project Engineer: | Garcia | Revised Completion Date: | 2020-10-16 23:46 | Allotment: | 10000000 | Revised: |  | No. of Man-days: | 319
Talaingod | Tapayanon | 1st Eng'g. Dist. | On-going | 2019-11-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Implementor: | PEO | No. of days suspended: | 28 | Disbursement: |  | Actual: | 27.08%
Talaingod | Tapayanon | 1st Eng'g. Dist. | On-going | 2019-11-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Duration: | 306 | No. of days extended: |  |  |  | Slippage: | 0%
Talaingod | Tapayanon | 1st Eng'g. Dist. | On-going | 2019-11-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Allotment Released: | 2019-11-15 | Date completed:
Talaingod | Tapayanon | 1st Eng'g. Dist. | On-going | 2019-11-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Started: | 2019-11-18
kapalong | Maniki | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | Completion of Brgy. Health Center, Maniki, Kapalong |  | SUPPLEMENTAL BUDGET NO. 4 CY 2019 (STIMULUS) | Building |  |  |  | Project Cost: | 627000 | Target Completion Date: |  | Program: | 627000 | Planned: |  | No. of Persons: |  | PROJECT Was funded by LGU, Kapalong
kapalong | Maniki | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 627000 | Revised: |  | No. of Man-days:
kapalong | Maniki | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
kapalong | Maniki | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
kapalong | Maniki | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Allotment Released: |  | Date completed:
kapalong | Maniki | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Started:
Asuncion | New Santiago | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | Construction of Potable Water System at Purok 6, New Santiago, Asuncion |  | SUPPLEMENTAL BUDGET NO. 4 CY 2019 (STIMULUS) | Water System |  |  | contract | Project Cost: | 1000000 | Target Completion Date: |  | Program: | 1000000 | Planned: |  | No. of Persons: |  | Change of POW to Contract
Asuncion | New Santiago | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 1000000 | Revised: |  | No. of Man-days:
Asuncion | New Santiago | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Asuncion | New Santiago | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Asuncion | New Santiago | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Allotment Released: |  | Date completed:
Asuncion | New Santiago | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Started:
New Corella | Poblacion | 1st Eng'g. Dist. | On-going | 2019-11-25 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | Construction of Children's Playground with Amenities, Poblacion, New Corella |  | SUPPLEMENTAL BUDGET NO. 4 CY 2019 (STIMULUS) | Building |  | sq.m | Admin | Project Cost: | 2500000 | Target Completion Date: | 2020-03-03 23:59 | Program: | 2500000 | Planned: | 46.63% | No. of Persons: | 10 | On-going (Suspended effective April 5, 2020 due to COVID; resumption order dated May 4, 2020)
New Corella | Poblacion | 1st Eng'g. Dist. | On-going | 2019-11-25 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Project Engineer: | Mayang | Revised Completion Date: | 2020-04-30 23:59 | Allotment: | 2500000 | Revised: |  | No. of Man-days: | 150
New Corella | Poblacion | 1st Eng'g. Dist. | On-going | 2019-11-25 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Implementor: | PEO | No. of days suspended: | 28 | Disbursement: | 1029250 | Actual: | 46.63%
New Corella | Poblacion | 1st Eng'g. Dist. | On-going | 2019-11-25 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Duration: | 100 | No. of days extended: | 30 |  |  | Slippage: | 0%
New Corella | Poblacion | 1st Eng'g. Dist. | On-going | 2019-11-25 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Allotment Released: | 2019-12-06 | Date completed:
New Corella | Poblacion | 1st Eng'g. Dist. | On-going | 2019-11-25 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Started: | 2019-11-25
Tagum City | Magugpo Poblacion | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | Rehabilitation of Evacuation Center at Magugpo Pob., Tagum City |  | SUPPLEMENTAL BUDGET NO. 4 CY 2019 (STIMULUS) | Building |  |  |  | Project Cost: | 600000 | Target Completion Date: |  | Program: | 600000 | Planned: |  | No. of Persons: |  | Purchase Order # 2020020796 (JJR Construction)
Tagum City | Magugpo Poblacion | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 600000 | Revised: |  | No. of Man-days:
Tagum City | Magugpo Poblacion | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Tagum City | Magugpo Poblacion | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Tagum City | Magugpo Poblacion | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Allotment Released: |  | Date completed:
Tagum City | Magugpo Poblacion | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Started:
Tagum City | Magugpo SOuth | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | Construction of Brgy. Health Center at Magugpo South, Tagum City |  | SUPPLEMENTAL BUDGET NO. 4 CY 2019 (STIMULUS) | Building |  |  |  | Project Cost: | 1550000 | Target Completion Date: |  | Program: | 1550000 | Planned: |  | No. of Persons: |  | Purchase Order # 20022150 (On-process)
Tagum City | Magugpo SOuth | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 1550000 | Revised: |  | No. of Man-days:
Tagum City | Magugpo SOuth | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Tagum City | Magugpo SOuth | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Tagum City | Magugpo SOuth | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Allotment Released: |  | Date completed:
Tagum City | Magugpo SOuth | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Started:
New Corella | Limbaan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | Rehab. Of Multi-Purpose Building (Evacuation Center), Limbaan, New Corella |  | SUPPLEMENTAL BUDGET NO. 4 CY 2019 (STIMULUS) | Building |  |  |  | Project Cost: | 600000 | Target Completion Date: |  | Program: | 600000 | Planned: |  | No. of Persons: |  | From SB # 1 to SB # 4 CY 2019 (Transfer to Contract) Procurement on process
New Corella | Limbaan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 600000 | Revised: |  | No. of Man-days:
New Corella | Limbaan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
New Corella | Limbaan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | Limbaan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Allotment Released: |  | Date completed:
New Corella | Limbaan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Started:
San Isidro | Sagayen-Sawata | 1st Eng'g. Dist. | On-going | 2019-09-09 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | Improvement of Km. 9 Sagayen-Sawata Provincial Road, San Isidro, Ph. II |  | SUPPLEMENTAL BUDGET NO. 4 CY 2019 (STIMULUS) | Road |  | ln.m | Admin | Project Cost: | 4591029 | Target Completion Date: | 2020-03-27 | Program: | 4591029 | Planned: | 45% | No. of Persons: | 6 | On-going (Suspended last April 5, 2020 due to COVID; resumption order dated May 4, 2020)
San Isidro | Sagayen-Sawata | 1st Eng'g. Dist. | On-going | 2019-09-09 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Project Engineer: | Limpo | Revised Completion Date: |  | Allotment: | 4591029 | Revised: |  | No. of Man-days: | 138
San Isidro | Sagayen-Sawata | 1st Eng'g. Dist. | On-going | 2019-09-09 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: | 1609155.6645 | Actual: | 35.05%
San Isidro | Sagayen-Sawata | 1st Eng'g. Dist. | On-going | 2019-09-09 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Duration: | 200 | No. of days extended: |  |  |  | Slippage: | -9.95%
San Isidro | Sagayen-Sawata | 1st Eng'g. Dist. | On-going | 2019-09-09 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Allotment Released: | 2019-12-12 | Date completed:
San Isidro | Sagayen-Sawata | 1st Eng'g. Dist. | On-going | 2019-09-09 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Started: | 2019-09-09
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Department of Agriculture | Poultry House and Training Center Sto. Niño, Talaingod |  | PROJECTS FOR PROVINCIAL VETERINARY | Building |  |  | Contract | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Final Abstract # 012020012 (Alpebel Builders & Supply Corp.)
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Department of Agriculture | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 500000 | Revised: |  | No. of Man-days:
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Department of Agriculture | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Department of Agriculture | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Department of Agriculture | [7 empty] | Date Allotment Released: |  | Date completed:
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Department of Agriculture | [7 empty] | Date Started:
Talaingod | Salawao-Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Department of Agriculture | Establishment of Livestock and Poultry Mutiplier Farm, Sitio Salawao, Sto. Niño, Talaingod |  | Department of Agriculture - Regional Field Office XI | Building |  |  |  | Project Cost: | 600000 | Target Completion Date: |  | Program: | 600000 | Planned: |  | No. of Persons: |  | Final Abstract # 012020012 (Alpebel Builders & Supply Corp.)
Talaingod | Salawao-Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Department of Agriculture | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 600000 | Revised: |  | No. of Man-days:
Talaingod | Salawao-Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Department of Agriculture | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Talaingod | Salawao-Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Department of Agriculture | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Talaingod | Salawao-Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Department of Agriculture | [7 empty] | Date Allotment Released: |  | Date completed:
Talaingod | Salawao-Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Department of Agriculture | [7 empty] | Date Started:
kapalong | Mabantao-Florida | 1st Eng'g. Dist. | On-going | 2019-10-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CMGP | Road Upgrading of Kapalong - Mabantao - Florida Road with Bridge Component |  | CMGP CY 2019 | Concreting |  | ln.m | Contract | Project Cost: | 15435008 | Target Completion Date: | 2020-03-10 23:59 | Program: | 15435008 | Planned: | 100% | No. of Persons: | 19 | On-going (Suspended last April 5, 2020 due to COVID; resumption order dated May 4, 2020)
kapalong | Mabantao-Florida | 1st Eng'g. Dist. | On-going | 2019-10-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CMGP | [7 empty] | Project Engineer: | Japay/Quirante | Revised Completion Date: | 2020-04-29 23:59 | Allotment: | 15435008 | Revised: | 81.81% | No. of Man-days: | 551
kapalong | Mabantao-Florida | 1st Eng'g. Dist. | On-going | 2019-10-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CMGP | [7 empty] | Implementor: | LEGACY | No. of days suspended: | 30 | Disbursement: | 6174003.2 | Actual: | 78.93%
kapalong | Mabantao-Florida | 1st Eng'g. Dist. | On-going | 2019-10-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CMGP | [7 empty] | Duration: | 147 | No. of days extended: | 20 |  |  | Slippage: | -2.882%
kapalong | Mabantao-Florida | 1st Eng'g. Dist. | On-going | 2019-10-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CMGP | [7 empty] | Date Allotment Released: | CY 2019 | Date completed:
kapalong | Mabantao-Florida | 1st Eng'g. Dist. | On-going | 2019-10-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CMGP | [7 empty] | Date Started: | 2019-10-16
New Corella | Del Pilar | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | LGSF | Rehabilitation of Dasing to Monte Carlo FMR, Del Pilar, New Corella |  | LGSF CY 2019 | Concreting |  |  | Contract | Project Cost: | 40000000 | Target Completion Date: |  | Program: | 40000000 | Planned: |  | No. of Persons: |  | For implementation (Awarded to Rely Construction and Supply)
New Corella | Del Pilar | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | LGSF | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 40000000 | Revised: |  | No. of Man-days:
New Corella | Del Pilar | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | LGSF | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
New Corella | Del Pilar | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | LGSF | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | Del Pilar | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | LGSF | [7 empty] | Date Allotment Released: |  | Date completed:
New Corella | Del Pilar | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | LGSF | [7 empty] | Date Started:
Tagum City | Magugpo South | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | LGSF | Concreting of Visayan Village - Purok exodus - Purok Rafael, Brgy. Magugpo South, Tagum City |  | LGSF CY 2019 | Concreting |  |  | Contract | Project Cost: | 40000000 | Target Completion Date: |  | Program: | 40000000 | Planned: |  | No. of Persons: |  | For implementation (Awarded to Legacy Construction Corporation)
Tagum City | Magugpo South | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | LGSF | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 40000000 | Revised: |  | No. of Man-days:
Tagum City | Magugpo South | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | LGSF | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Tagum City | Magugpo South | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | LGSF | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Tagum City | Magugpo South | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | LGSF | [7 empty] | Date Allotment Released: |  | Date completed:
Tagum City | Magugpo South | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | LGSF | [7 empty] | Date Started:
Asuncion | Magatos-Bantayan | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 001 - Jct. Highway Magatos - New Bantayan |  | GENERAL FUND CY 2020 | Maintenance | 7.1 | km | MBA | Project Cost: | 564839.9739 | Target Completion Date: | 2020-12-31 23:59 | Program: | 564839.9739 | Planned: | 31.14% | No. of Persons: | 17 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020)
Asuncion | Magatos-Bantayan | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 564839.9739 | Revised: |  | No. of Man-days: | 374
Asuncion | Magatos-Bantayan | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 57334.17 | Actual: | 31.14%
Asuncion | Magatos-Bantayan | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0%
Asuncion | Magatos-Bantayan | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
Asuncion | Magatos-Bantayan | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started: | 2020-01-02
Asuncion | Magatos-Bantayan | 1st Eng'g. Dist. | On-going |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 001 - Jct. Highway Magatos - New Bantayan |  | GENERAL FUND CY 2020 | Maintenance | 7.1 | km | CBRMC | Project Cost: | 230737.1976 | Target Completion Date: |  | Program: | 230737.1976 | Planned: |  | No. of Persons: |  | Purchase Request # 19125305 (On process)
Asuncion | Magatos-Bantayan | 1st Eng'g. Dist. | On-going |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 230737.1976 | Revised: |  | No. of Man-days:
Asuncion | Magatos-Bantayan | 1st Eng'g. Dist. | On-going |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Asuncion | Magatos-Bantayan | 1st Eng'g. Dist. | On-going |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Asuncion | Magatos-Bantayan | 1st Eng'g. Dist. | On-going |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: |  | Date completed:
Asuncion | Magatos-Bantayan | 1st Eng'g. Dist. | On-going |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started:
Asuncion | Magatos-Pagsabangan | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 002 - Magatos - Bdry. Pagsabangan |  | GENERAL FUND CY 2020 | Maintenance | 8.33 | km | MBA | Project Cost: | 653221.626 | Target Completion Date: | 2020-12-31 23:59 | Program: | 653221.626 | Planned: | 28.54% | No. of Persons: | 17 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020)
Asuncion | Magatos-Pagsabangan | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 653221.626 | Revised: |  | No. of Man-days: | 374
Asuncion | Magatos-Pagsabangan | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 71713.44 | Actual: | 28.54%
Asuncion | Magatos-Pagsabangan | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0%
Asuncion | Magatos-Pagsabangan | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
Asuncion | Magatos-Pagsabangan | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started: | 2020-01-02
Asuncion | Magatos-Pagsabangan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 002 - Magatos - Bdry. Pagsabangan |  | GENERAL FUND CY 2020 | Maintenance | 8.33 | km | CBRMC | Project Cost: | 280180.88 | Target Completion Date: |  | Program: | 280180.88 | Planned: |  | No. of Persons: |  | Purchase Request # 19125306 (On process)
Asuncion | Magatos-Pagsabangan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 280180.88 | Revised: |  | No. of Man-days:
Asuncion | Magatos-Pagsabangan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Asuncion | Magatos-Pagsabangan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Asuncion | Magatos-Pagsabangan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: |  | Date completed:
Asuncion | Magatos-Pagsabangan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started:
Asuncion | New Bantayan | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 003 - Ilog - New Bantayan |  | GENERAL FUND CY 2020 | Maintenance | 2.68 | km | MBA | Project Cost: | 236174.847 | Target Completion Date: | 2020-12-31 23:59 | Program: | 236174.847 | Planned: | 15.36% | No. of Persons: | 17 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020)
Asuncion | New Bantayan | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 236174.847 | Revised: |  | No. of Man-days: | 374
Asuncion | New Bantayan | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 22629.74 | Actual: | 15.36%
Asuncion | New Bantayan | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0%
Asuncion | New Bantayan | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
Asuncion | New Bantayan | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started: | 2020-01-02
Asuncion | New Bantayan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 003 - Ilog - New Bantayan |  | GENERAL FUND CY 2020 | Maintenance | 2.68 | km | CBRMC | Project Cost: | 70633.836 | Target Completion Date: |  | Program: | 70633.836 | Planned: |  | No. of Persons: |  | Purchase Request # 19125307 (On process)
Asuncion | New Bantayan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 70633.836 | Revised: |  | No. of Man-days:
Asuncion | New Bantayan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Asuncion | New Bantayan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Asuncion | New Bantayan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: |  | Date completed:
Asuncion | New Bantayan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started:
Asuncion | Monte Carlo-Del Pilar | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 005 - Asuncion - Monte Carlo - Del Pilar |  | GENERAL FUND CY 2020 | Maintenance | 9.93 | km | MBA | Project Cost: | 716344.9167 | Target Completion Date: | 2020-12-31 23:59 | Program: | 716344.9167 | Planned: | 29.09% | No. of Persons: | 17 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020)
Asuncion | Monte Carlo-Del Pilar | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 716344.9167 | Revised: |  | No. of Man-days: | 374
Asuncion | Monte Carlo-Del Pilar | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 33056.21 | Actual: | 29.09%
Asuncion | Monte Carlo-Del Pilar | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0%
Asuncion | Monte Carlo-Del Pilar | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
Asuncion | Monte Carlo-Del Pilar | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started: | 2020-01-02
Asuncion | Monte Carlo-Del Pilar | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 005 - Asuncion - Monte Carlo - Del Pilar |  | GENERAL FUND CY 2020 | Maintenance | 9.93 | km | CBRMC | Project Cost: | 360232.5636 | Target Completion Date: |  | Program: | 360232.5636 | Planned: |  | No. of Persons: |  | Purchase Request # 19125308 (On process)
Asuncion | Monte Carlo-Del Pilar | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 360232.5636 | Revised: |  | No. of Man-days:
Asuncion | Monte Carlo-Del Pilar | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Asuncion | Monte Carlo-Del Pilar | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Asuncion | Monte Carlo-Del Pilar | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: |  | Date completed:
Asuncion | Monte Carlo-Del Pilar | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started:
Asuncion | Canatan-Magatos | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 006 - Jct. Highway Canatan - Magatos |  | GENERAL FUND CY 2020 | Maintenance | 4.85 | km | MBA | Project Cost: | 391296.517 | Target Completion Date: | 2020-12-31 23:59 | Program: | 391296.517 | Planned: | 24.95% | No. of Persons: | 17 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020)
Asuncion | Canatan-Magatos | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 391296.517 | Revised: |  | No. of Man-days: | 374
Asuncion | Canatan-Magatos | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 33056.21 | Actual: | 24.95%
Asuncion | Canatan-Magatos | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0%
Asuncion | Canatan-Magatos | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
Asuncion | Canatan-Magatos | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started: | 2020-01-02
Asuncion | Canatan-Magatos | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 006 - Jct. Highway Canatan - Magatos |  | GENERAL FUND CY 2020 | Maintenance | 4.85 | km | CBRMC | Project Cost: | 164812.284 | Target Completion Date: |  | Program: | 164812.284 | Planned: |  | No. of Persons: |  | Purchase Request # 19125309 (On process)
Asuncion | Canatan-Magatos | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 164812.284 | Revised: |  | No. of Man-days:
Asuncion | Canatan-Magatos | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Asuncion | Canatan-Magatos | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Asuncion | Canatan-Magatos | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: |  | Date completed:
Asuncion | Canatan-Magatos | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started:
Asuncion | Saug-Sonlon-Longanapan | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 010 - Saug - Sonlon - Bdry. Longanapan |  | GENERAL FUND CY 2020 | Maintenance | 11.6 | km | MBA | Project Cost: | 1102041.4797 | Target Completion Date: | 2020-12-31 23:59 | Program: | 1102041.4797 | Planned: | 21.92% | No. of Persons: | 17 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020)
Asuncion | Saug-Sonlon-Longanapan | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 1102041.4797 | Revised: |  | No. of Man-days: | 374
Asuncion | Saug-Sonlon-Longanapan | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 83166.18 | Actual: | 21.92%
Asuncion | Saug-Sonlon-Longanapan | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0%
Asuncion | Saug-Sonlon-Longanapan | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
Asuncion | Saug-Sonlon-Longanapan | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started: | 2020-01-02
Asuncion | Saug-Sonlon-Longanapan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 010 - Saug - Sonlon - Bdry. Longanapan |  | GENERAL FUND CY 2020 | Maintenance | 11.6 | km | CBRMC | Project Cost: | 197774.7408 | Target Completion Date: |  | Program: | 197774.7408 | Planned: |  | No. of Persons: |  | Purchase Request # 19125310 (On process)
Asuncion | Saug-Sonlon-Longanapan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 197774.7408 | Revised: |  | No. of Man-days:
Asuncion | Saug-Sonlon-Longanapan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Asuncion | Saug-Sonlon-Longanapan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Asuncion | Saug-Sonlon-Longanapan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: |  | Date completed:
Asuncion | Saug-Sonlon-Longanapan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started:
Asuncion | New Visayas-Buan | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 011 - Jct. New Visayas - Buan |  | GENERAL FUND CY 2020 | Maintenance | 2.99 | km | MBA | Project Cost: | 134598.4525 | Target Completion Date: | 2020-12-31 23:59 | Program: | 134598.4525 | Planned: | 7.72% | No. of Persons: | 17 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020)
Asuncion | New Visayas-Buan | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 134598.4525 | Revised: |  | No. of Man-days: | 374
Asuncion | New Visayas-Buan | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 10391.0005 | Actual: | 7.72%
Asuncion | New Visayas-Buan | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0%
Asuncion | New Visayas-Buan | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
Asuncion | New Visayas-Buan | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started: | 2020-01-02
Asuncion | New Visayas-Buan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 011 - Jct. New Visayas - Buan |  | GENERAL FUND CY 2020 | Maintenance | 2.99 | km | CBRMC | Project Cost: | 124786.4436 | Target Completion Date: |  | Program: | 124786.4436 | Planned: |  | No. of Persons: |  | Purchase Request # 19125311 (On process)
Asuncion | New Visayas-Buan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 124786.4436 | Revised: |  | No. of Man-days:
Asuncion | New Visayas-Buan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Asuncion | New Visayas-Buan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Asuncion | New Visayas-Buan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: |  | Date completed:
Asuncion | New Visayas-Buan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started:
Asuncion | San Vicente-Butay | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 013 - San Vicente - Butay |  | GENERAL FUND CY 2020 | Maintenance | 7.52 | km | MBA | Project Cost: | 579541.5407 | Target Completion Date: | 2020-12-31 23:59 | Program: | 579541.5407 | Planned: | 30.2% | No. of Persons: | 17 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020)
Asuncion | San Vicente-Butay | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 579541.5407 | Revised: |  | No. of Man-days: | 374
Asuncion | San Vicente-Butay | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 123616.2106 | Actual: | 30.2%
Asuncion | San Vicente-Butay | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0%
Asuncion | San Vicente-Butay | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
Asuncion | San Vicente-Butay | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started: | 2020-01-02
Asuncion | San Vicente-Butay | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 013 - San Vicente - Butay |  | GENERAL FUND CY 2020 | Maintenance | 7.52 | km | CBRMC | Project Cost: | 235446.12 | Target Completion Date: |  | Program: | 235446.12 | Planned: |  | No. of Persons: |  | Purchase Request # 19125312 (On process)
Asuncion | San Vicente-Butay | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 235446.12 | Revised: |  | No. of Man-days:
Asuncion | San Vicente-Butay | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Asuncion | San Vicente-Butay | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Asuncion | San Vicente-Butay | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: |  | Date completed:
Asuncion | San Vicente-Butay | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started:
kapalong | Doña Andrea-Capungagan | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 014 - Jct. Highway Doña Andrea - Capungagan |  | GENERAL FUND CY 2020 | Maintenance | 8.7 | km | MBA | Project Cost: | 675845.5865 | Target Completion Date: | 2020-12-31 23:59 | Program: | 675845.5865 | Planned: | 14.87% | No. of Persons: | 17 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020)
kapalong | Doña Andrea-Capungagan | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 675845.5865 | Revised: |  | No. of Man-days: | 374
kapalong | Doña Andrea-Capungagan | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 75289.1983 | Actual: | 14.87%
kapalong | Doña Andrea-Capungagan | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0%
kapalong | Doña Andrea-Capungagan | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
kapalong | Doña Andrea-Capungagan | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started: | 2020-01-02
kapalong | Doña Andrea-Capungagan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 014 - Jct. Highway Doña Andrea - Capungagan |  | GENERAL FUND CY 2020 | Maintenance | 8.7 | km | CBRMC | Project Cost: | 299016.5724 | Target Completion Date: |  | Program: | 299016.5724 | Planned: |  | No. of Persons: |  | Purchase Request # 19125313 (On process)
kapalong | Doña Andrea-Capungagan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 299016.5724 | Revised: |  | No. of Man-days:
kapalong | Doña Andrea-Capungagan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
kapalong | Doña Andrea-Capungagan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
kapalong | Doña Andrea-Capungagan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: |  | Date completed:
kapalong | Doña Andrea-Capungagan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started:
kapalong | Pamacaun-Lasang-banate | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 015 - Pamacaun - Lasang - Banate |  | GENERAL FUND CY 2020 | Maintenance | 4.11 | km | MBA | Project Cost: | 180747.1933 | Target Completion Date: | 2020-12-31 23:59 | Program: | 180747.1933 | Planned: | 8.6% | No. of Persons: | 17 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020)
kapalong | Pamacaun-Lasang-banate | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 180747.1933 | Revised: |  | No. of Man-days: | 374
kapalong | Pamacaun-Lasang-banate | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 15544.2586 | Actual: | 8.6%
kapalong | Pamacaun-Lasang-banate | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0%
kapalong | Pamacaun-Lasang-banate | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
kapalong | Pamacaun-Lasang-banate | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started: | 2020-01-02
kapalong | Pamacaun-Lasang-banate | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 015 - Pamacaun - Lasang - Banate |  | GENERAL FUND CY 2020 | Maintenance | 4.11 | km | CBRMC | Project Cost: | 129495.366 | Target Completion Date: |  | Program: | 129495.366 | Planned: |  | No. of Persons: |  | Purchase Request # 19125314 (On process)
kapalong | Pamacaun-Lasang-banate | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 129495.366 | Revised: |  | No. of Man-days:
kapalong | Pamacaun-Lasang-banate | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
kapalong | Pamacaun-Lasang-banate | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
kapalong | Pamacaun-Lasang-banate | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: |  | Date completed:
kapalong | Pamacaun-Lasang-banate | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started:
kapalong | Semong-Palma Gil | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 018 - Semong - Palma Gil |  | GENERAL FUND CY 2020 | Maintenance | 2.73 | km | MBA | Project Cost: | 276301.31 | Target Completion Date: | 2020-12-31 23:59 | Program: | 276301.31 | Planned: | 50.35% | No. of Persons: | 14 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020)
kapalong | Semong-Palma Gil | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 276301.31 | Revised: |  | No. of Man-days: | 210
kapalong | Semong-Palma Gil | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 139117.7096 | Actual: | 50.35%
kapalong | Semong-Palma Gil | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0%
kapalong | Semong-Palma Gil | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
kapalong | Semong-Palma Gil | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started: | 2020-01-02
kapalong | Semong-Palma Gil | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 018 - Semong - Palma Gil |  | GENERAL FUND CY 2020 | Maintenance | 2.73 | km | CBRMC | Project Cost: | 77697.2196 | Target Completion Date: |  | Program: | 77697.2196 | Planned: |  | No. of Persons: |  | Purchase Request # 19125315 (On process)
kapalong | Semong-Palma Gil | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 77697.2196 | Revised: |  | No. of Man-days:
kapalong | Semong-Palma Gil | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
kapalong | Semong-Palma Gil | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
kapalong | Semong-Palma Gil | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: |  | Date completed:
kapalong | Semong-Palma Gil | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started:
Talaingod | Daligdigon-Dagohoy | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 020 - Daligdigon-Dagohoy |  | GENERAL FUND CY 2020 | Maintenance | 3.34 | km | MBA | Project Cost: | 161826.4 | Target Completion Date: | 2020-12-31 23:59 | Program: | 161826.4 | Planned: | 51.55% | No. of Persons: | 14 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020)
Talaingod | Daligdigon-Dagohoy | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 161826.4 | Revised: |  | No. of Man-days: | 210
Talaingod | Daligdigon-Dagohoy | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 83421.5092 | Actual: | 51.55%
Talaingod | Daligdigon-Dagohoy | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0%
Talaingod | Daligdigon-Dagohoy | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
Talaingod | Daligdigon-Dagohoy | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started: | 2020-01-02
Talaingod | Daligdigon-Dagohoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 020 - Daligdigon-Dagohoy |  | GENERAL FUND CY 2020 | Maintenance | 3.34 | km | CBRMC | Project Cost: | 77697.2196 | Target Completion Date: |  | Program: | 77697.2196 | Planned: |  | No. of Persons: |  | Purchase Request # 19125315 (On process)
Talaingod | Daligdigon-Dagohoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 77697.2196 | Revised: |  | No. of Man-days:
Talaingod | Daligdigon-Dagohoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Talaingod | Daligdigon-Dagohoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Talaingod | Daligdigon-Dagohoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: |  | Date completed:
Talaingod | Daligdigon-Dagohoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started:
Talaingod | Angelo-Dahgohoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 021 - Angelo - Dagohoy |  | GENERAL FUND CY 2020 | Maintenance | 2.19 | km | MBA | Project Cost: | 67286.09 | Target Completion Date: | 2020-12-31 23:59 | Program: | 67286.09 | Planned: | 21.85% | No. of Persons: | 14 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020)
Talaingod | Angelo-Dahgohoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 67286.09 | Revised: |  | No. of Man-days: | 210
Talaingod | Angelo-Dahgohoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 14702.0107 | Actual: | 21.85%
Talaingod | Angelo-Dahgohoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0%
Talaingod | Angelo-Dahgohoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
Talaingod | Angelo-Dahgohoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started: | 2020-01-02
Talaingod | Angelo-Dahgohoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 021 - Angelo - Dagohoy |  | GENERAL FUND CY 2020 | Maintenance | 2.19 | km | CBRMC | Project Cost: | 40025.8404 | Target Completion Date: |  | Program: | 40025.8404 | Planned: |  | No. of Persons: |  | Purchase Request # 19125317 (On process)
Talaingod | Angelo-Dahgohoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 40025.8404 | Revised: |  | No. of Man-days:
Talaingod | Angelo-Dahgohoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Talaingod | Angelo-Dahgohoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Talaingod | Angelo-Dahgohoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: |  | Date completed:
Talaingod | Angelo-Dahgohoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started:
kapalong | Sampao-Mamacao | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 025 - Jct. Sampao - Bdry. Mamacao |  | GENERAL FUND CY 2020 | Maintenance | 4.98 | km | MBA | Project Cost: | 325083.1184 | Target Completion Date: | 2020-12-31 23:59 | Program: | 325083.1184 | Planned: | 14.71% | No. of Persons: | 17 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020)
kapalong | Sampao-Mamacao | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 325083.1184 | Revised: |  | No. of Man-days: | 374
kapalong | Sampao-Mamacao | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 47819.7267 | Actual: | 14.71%
kapalong | Sampao-Mamacao | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0%
kapalong | Sampao-Mamacao | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
kapalong | Sampao-Mamacao | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started: | 2020-01-02
kapalong | Sampao-Mamacao | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 025 - Jct. Sampao - Bdry. Mamacao |  | GENERAL FUND CY 2020 | Maintenance | 4.98 | km | CBRMC | Project Cost: | 178939.0512 | Target Completion Date: |  | Program: | 178939.0512 | Planned: |  | No. of Persons: |  | Purchase Request # 19125318 (On process)
kapalong | Sampao-Mamacao | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 178939.0512 | Revised: |  | No. of Man-days:
kapalong | Sampao-Mamacao | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
kapalong | Sampao-Mamacao | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
kapalong | Sampao-Mamacao | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: |  | Date completed:
kapalong | Sampao-Mamacao | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started:
kapalong | Luna-Mamacao | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 026 - Jct. Highway - Luna - Mamacao - Narra |  | GENERAL FUND CY 2020 | Maintenance | 9.17 | km | MBA | Project Cost: | 361826.1515 | Target Completion Date: | 2020-12-31 23:59 | Program: | 361826.1515 | Planned: | 20.12% | No. of Persons: | 17 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020)
kapalong | Luna-Mamacao | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 361826.1515 | Revised: |  | No. of Man-days: | 374
kapalong | Luna-Mamacao | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 22433.2214 | Actual: | 20.12%
kapalong | Luna-Mamacao | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0%
kapalong | Luna-Mamacao | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
kapalong | Luna-Mamacao | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started: | 2020-01-02
kapalong | Luna-Mamacao | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 026 - Jct. Highway - Luna - Mamacao - Narra |  | GENERAL FUND CY 2020 | Maintenance | 9.17 | km | CBRMC | Project Cost: | 393195.0204 | Target Completion Date: |  | Program: | 393195.0204 | Planned: |  | No. of Persons: |  | Purchase Request # 19125337 (On process)
kapalong | Luna-Mamacao | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 393195.0204 | Revised: |  | No. of Man-days:
kapalong | Luna-Mamacao | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
kapalong | Luna-Mamacao | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
kapalong | Luna-Mamacao | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: |  | Date completed:
kapalong | Luna-Mamacao | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started:
kapalong | Gabuyan-Katipunan | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 027 - Jct. Gabuyan - Katipunan - Bucana |  | GENERAL FUND CY 2020 | Maintenance | 5.89 | km | MBA | Project Cost: | 485762.7577 | Target Completion Date: | 2020-12-31 23:59 | Program: | 485762.7577 | Planned: | 7.86% | No. of Persons: | 17 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020)
kapalong | Gabuyan-Katipunan | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 485762.7577 | Revised: |  | No. of Man-days: | 374
kapalong | Gabuyan-Katipunan | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 38180.9528 | Actual: | 7.86%
kapalong | Gabuyan-Katipunan | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0%
kapalong | Gabuyan-Katipunan | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
kapalong | Gabuyan-Katipunan | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started: | 2020-01-02
kapalong | Gabuyan-Katipunan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 027 - Jct. Gabuyan - Katipunan - Bucana |  | GENERAL FUND CY 2020 | Maintenance | 5.89 | km | CBRMC | Project Cost: | 174230.1288 | Target Completion Date: |  | Program: | 174230.1288 | Planned: |  | No. of Persons: |  | Purchase Request # 19125338 (On process)
kapalong | Gabuyan-Katipunan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 174230.1288 | Revised: |  | No. of Man-days:
kapalong | Gabuyan-Katipunan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
kapalong | Gabuyan-Katipunan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
kapalong | Gabuyan-Katipunan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: |  | Date completed:
kapalong | Gabuyan-Katipunan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started:
kapalong | Capungagan-Mabuhay | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 028 - Capungagan - Mabuhay - Pandulian |  | GENERAL FUND CY 2020 | Maintenance | 5.57 | km | MBA | Project Cost: | 468741.4542 | Target Completion Date: | 2020-12-31 23:59 | Program: | 468741.4542 | Planned: | 5.14% | No. of Persons: | 17 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020)
kapalong | Capungagan-Mabuhay | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 468741.4542 | Revised: |  | No. of Man-days: | 374
kapalong | Capungagan-Mabuhay | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 24093.3107 | Actual: | 5.14%
kapalong | Capungagan-Mabuhay | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0%
kapalong | Capungagan-Mabuhay | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
kapalong | Capungagan-Mabuhay | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started: | 2020-01-02
kapalong | Capungagan-Mabuhay | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 028 - Capungagan - Mabuhay - Pandulian |  | GENERAL FUND CY 2020 | Maintenance | 5.57 | km | CBRMC | Project Cost: | 155394.4392 | Target Completion Date: |  | Program: | 155394.4392 | Planned: |  | No. of Persons: |  | Purchase Request # 19125339 (On process)
kapalong | Capungagan-Mabuhay | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 155394.4392 | Revised: |  | No. of Man-days:
kapalong | Capungagan-Mabuhay | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
kapalong | Capungagan-Mabuhay | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
kapalong | Capungagan-Mabuhay | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: |  | Date completed:
kapalong | Capungagan-Mabuhay | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started:
San Isidro | Kipalili-New Loon | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 034 - Km. 15, Kipalili - New Loon |  | GENERAL FUND CY 2020 | Maintenance | 6.93 | km | MBA | Project Cost: | 490709.8742 | Target Completion Date: | 2020-12-31 23:59 | Program: | 490709.8742 | Planned: | 18.2% | No. of Persons: | 17 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020)
San Isidro | Kipalili-New Loon | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 490709.8742 | Revised: |  | No. of Man-days: | 374
San Isidro | Kipalili-New Loon | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 66393.046 | Actual: | 18.2%
San Isidro | Kipalili-New Loon | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0%
San Isidro | Kipalili-New Loon | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
San Isidro | Kipalili-New Loon | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started: | 2020-01-02
San Isidro | Kipalili-New Loon | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 034 - Km. 15, Kipalili - New Loon |  | GENERAL FUND CY 2020 | Maintenance | 6.93 | km | CBRMC | Project Cost: | 296662.1112 | Target Completion Date: |  | Program: | 296662.1112 | Planned: |  | No. of Persons: |  | Purchase Request # 19125340 (On process)
San Isidro | Kipalili-New Loon | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 296662.1112 | Revised: |  | No. of Man-days:
San Isidro | Kipalili-New Loon | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
San Isidro | Kipalili-New Loon | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
San Isidro | Kipalili-New Loon | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: |  | Date completed:
San Isidro | Kipalili-New Loon | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started:
San Isidro | Suaon-Libuton | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 035 - Jct. Suaon - Libuton |  | GENERAL FUND CY 2020 | Maintenance | 7.26 | km | MBA | Project Cost: | 60919.7962 | Target Completion Date: | 2020-12-31 23:59 | Program: | 60919.7962 | Planned: | 7.12% | No. of Persons: | 17 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020)
San Isidro | Suaon-Libuton | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 60919.7962 | Revised: |  | No. of Man-days: | 374
San Isidro | Suaon-Libuton | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: |  | Actual: | 7.12%
San Isidro | Suaon-Libuton | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0%
San Isidro | Suaon-Libuton | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
San Isidro | Suaon-Libuton | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started: | 2020-01-02
San Isidro | Suaon-Libuton | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 035 - Jct. Suaon - Libuton |  | GENERAL FUND CY 2020 | Maintenance | 7.26 | km | CBRMC | Project Cost: | 96532.9092 | Target Completion Date: |  | Program: | 96532.9092 | Planned: |  | No. of Persons: |  | Purchase Request # 19125341 (On process)
San Isidro | Suaon-Libuton | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 96532.9092 | Revised: |  | No. of Man-days:
San Isidro | Suaon-Libuton | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
San Isidro | Suaon-Libuton | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
San Isidro | Suaon-Libuton | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: |  | Date completed:
San Isidro | Suaon-Libuton | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started:
San Isidro | Monte Dujali-Gupitan | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 037 - Monte Dujali - Gupitan |  | GENERAL FUND CY 2020 | Maintenance | 4.58 | km | MBA | Project Cost: | 224727.1648 | Target Completion Date: | 2020-12-31 23:59 | Program: | 224727.1648 | Planned: | 11.08% | No. of Persons: | 17 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020)
San Isidro | Monte Dujali-Gupitan | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 224727.1648 | Revised: |  | No. of Man-days: | 374
San Isidro | Monte Dujali-Gupitan | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 24899.7699 | Actual: | 11.08%
San Isidro | Monte Dujali-Gupitan | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0%
San Isidro | Monte Dujali-Gupitan | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
San Isidro | Monte Dujali-Gupitan | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started: | 2020-01-02
San Isidro | Monte Dujali-Gupitan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 037 - Monte Dujali - Gupitan |  | GENERAL FUND CY 2020 | Maintenance | 4.58 | km | CBRMC | Project Cost: | 134204.2884 | Target Completion Date: |  | Program: | 134204.2884 | Planned: |  | No. of Persons: |  | Purchase Request # 19125342 (On process)
San Isidro | Monte Dujali-Gupitan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 134204.2884 | Revised: |  | No. of Man-days:
San Isidro | Monte Dujali-Gupitan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
San Isidro | Monte Dujali-Gupitan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
San Isidro | Monte Dujali-Gupitan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: |  | Date completed:
San Isidro | Monte Dujali-Gupitan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started:
San Isidro | Sawata-Mamangan-Pinamuno | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 041 - Sawata - Mamangan - Pinamuno |  | GENERAL FUND CY 2020 | Maintenance | 14.48 | km | MBA | Project Cost: | 1636481.63 | Target Completion Date: | 2021-02-01 23:59 | Program: | 1636481.63 | Planned: | 37.11% | No. of Persons: | 14 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020)
San Isidro | Sawata-Mamangan-Pinamuno | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-02-28 23:59 | Allotment: | 1636481.63 | Revised: |  | No. of Man-days: | 210
San Isidro | Sawata-Mamangan-Pinamuno | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 607298.3329 | Actual: | 37.11%
San Isidro | Sawata-Mamangan-Pinamuno | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0%
San Isidro | Sawata-Mamangan-Pinamuno | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
San Isidro | Sawata-Mamangan-Pinamuno | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started: | 2020-02-03
San Isidro | Sawata-Mamangan-Pinamuno | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 041 - Sawata - Mamangan - Pinamuno |  | GENERAL FUND CY 2020 | Maintenance | 14.48 | km | CBRMC | Project Cost: | 522690.3864 | Target Completion Date: |  | Program: | 522690.3864 | Planned: |  | No. of Persons: |  | Purchase Request # 19125343 (On process)
San Isidro | Sawata-Mamangan-Pinamuno | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 522690.3864 | Revised: |  | No. of Man-days:
San Isidro | Sawata-Mamangan-Pinamuno | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
San Isidro | Sawata-Mamangan-Pinamuno | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
San Isidro | Sawata-Mamangan-Pinamuno | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: |  | Date completed:
San Isidro | Sawata-Mamangan-Pinamuno | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started:
San Isidro | Igangon-Sawata | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 042 - Igangon - Sawata |  | GENERAL FUND CY 2020 | Maintenance | 9.66 | km | MBA | Project Cost: | 111771.1255 | Target Completion Date: | 2020-12-31 23:59 | Program: | 111771.1255 | Planned: | 8.74% | No. of Persons: | 17 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020)
San Isidro | Igangon-Sawata | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 111771.1255 | Revised: |  | No. of Man-days: | 374
San Isidro | Igangon-Sawata | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 9768.7964 | Actual: | 8.74%
San Isidro | Igangon-Sawata | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0%
San Isidro | Igangon-Sawata | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
San Isidro | Igangon-Sawata | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started: | 2020-01-02
San Isidro | Igangon-Sawata | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 042 - Igangon - Sawata |  | GENERAL FUND CY 2020 | Maintenance | 9.66 | km | CBRMC | Project Cost: | 202483.6632 | Target Completion Date: |  | Program: | 202483.6632 | Planned: |  | No. of Persons: |  | Purchase Request # 19125344 (On process)
San Isidro | Igangon-Sawata | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 202483.6632 | Revised: |  | No. of Man-days:
San Isidro | Igangon-Sawata | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
San Isidro | Igangon-Sawata | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
San Isidro | Igangon-Sawata | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: |  | Date completed:
San Isidro | Igangon-Sawata | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started:
San Isidro | Sawata | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 043 - Jct. Sawata - Bdry. Binasbas |  | GENERAL FUND CY 2020 | Maintenance | 0.46 | km | MBA | Project Cost: | 27720.5682 | Target Completion Date: | 2020-12-31 23:59 | Program: | 27720.5682 | Planned: | 10.3% | No. of Persons: | 17 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020)
San Isidro | Sawata | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 27720.5682 | Revised: |  | No. of Man-days: | 374
San Isidro | Sawata | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 2855.2185 | Actual: | 10.3%
San Isidro | Sawata | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0%
San Isidro | Sawata | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
San Isidro | Sawata | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started: | 2020-01-02
San Isidro | Sawata | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 043 - Jct. Sawata - Bdry. Binasbas |  | GENERAL FUND CY 2020 | Maintenance | 0.46 | km | CBRMC | Project Cost: | 18835.6896 | Target Completion Date: |  | Program: | 18835.6896 | Planned: |  | No. of Persons: |  | Purchase Request # 19125345 (On process)
San Isidro | Sawata | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 18835.6896 | Revised: |  | No. of Man-days:
San Isidro | Sawata | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
San Isidro | Sawata | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
San Isidro | Sawata | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: |  | Date completed:
San Isidro | Sawata | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started:
Asuncion | Buan | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 045 - Tagaytay - Buan |  | GENERAL FUND CY 2020 | Maintenance | 4.92 | km | MBA | Project Cost: | 378553.2244 | Target Completion Date: | 2020-12-31 23:59 | Program: | 378553.2244 | Planned: | 27.97% | No. of Persons: | 17 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020)
Asuncion | Buan | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 378553.2244 | Revised: |  | No. of Man-days: | 374
Asuncion | Buan | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 105881.3369 | Actual: | 27.97%
Asuncion | Buan | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0%
Asuncion | Buan | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
Asuncion | Buan | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started: | 2020-01-02
Asuncion | Buan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 045 - Tagaytay - Buan |  | GENERAL FUND CY 2020 | Maintenance | 4.92 | km | CBRMC | Project Cost: | 174230.1288 | Target Completion Date: |  | Program: | 174230.1288 | Planned: |  | No. of Persons: |  | Purchase Request # 19125346 (On process)
Asuncion | Buan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 174230.1288 | Revised: |  | No. of Man-days:
Asuncion | Buan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Asuncion | Buan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Asuncion | Buan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: |  | Date completed:
Asuncion | Buan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started:
New Corella | Limbann-Sto. Niño | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 049 - Limbaan - Sto. Niño |  | GENERAL FUND CY 2020 | Maintenance | 3.19 | km | MBA | Project Cost: | 322857.58 | Target Completion Date: | 2021-02-01 23:59 | Program: | 322857.58 | Planned: | 30.02% | No. of Persons: | 14 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020)
New Corella | Limbann-Sto. Niño | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-02-28 23:59 | Allotment: | 322857.58 | Revised: |  | No. of Man-days: | 210
New Corella | Limbann-Sto. Niño | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 96921.8455 | Actual: | 30.02%
New Corella | Limbann-Sto. Niño | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | Limbann-Sto. Niño | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
New Corella | Limbann-Sto. Niño | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started: | 2020-02-03
New Corella | Limbann-Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 049 - Limbaan - Sto. Niño |  | GENERAL FUND CY 2020 | Maintenance | 3.19 | km | CBRMC | Project Cost: | 127140.9048 | Target Completion Date: |  | Program: | 127140.9048 | Planned: |  | No. of Persons: |  | Purchase Request # 20010072 (On process)
New Corella | Limbann-Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 127140.9048 | Revised: |  | No. of Man-days:
New Corella | Limbann-Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
New Corella | Limbann-Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | Limbann-Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: |  | Date completed:
New Corella | Limbann-Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started:
New Corella | Monte Carlo | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 050 - Jct. Monte Carlo - Upper Cabaywa - Canatan |  | GENERAL FUND CY 2020 | Maintenance | 4.61 | km | MBA | Project Cost: | 285065.7818 | Target Completion Date: | 2020-12-31 23:59 | Program: | 285065.7818 | Planned: | 47.46% | No. of Persons: | 17 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020)
New Corella | Monte Carlo | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 285065.7818 | Revised: |  | No. of Man-days: | 374
New Corella | Monte Carlo | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 135292.2201 | Actual: | 47.46%
New Corella | Monte Carlo | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | Monte Carlo | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
New Corella | Monte Carlo | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started: | 2020-01-02
New Corella | Monte Carlo | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 050 - Jct. Monte Carlo - Upper Cabaywa - Canatan |  | GENERAL FUND CY 2020 | Maintenance | 4.61 | km | CBRMC | Project Cost: | 197774.7408 | Target Completion Date: |  | Program: | 197774.7408 | Planned: |  | No. of Persons: |  | Purchase Request # 20010074 (On process)
New Corella | Monte Carlo | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 197774.7408 | Revised: |  | No. of Man-days:
New Corella | Monte Carlo | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
New Corella | Monte Carlo | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | Monte Carlo | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: |  | Date completed:
New Corella | Monte Carlo | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started:
New Corella | Del Pilar | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 051 - Del Pilar - Jct. Silangan |  | GENERAL FUND CY 2020 | Maintenance | 4.17 | km | MBA | Project Cost: | 337766.1689 | Target Completion Date: | 2020-12-31 23:59 | Program: | 337766.1689 | Planned: | 5.54% | No. of Persons: |  | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020)
New Corella | Del Pilar | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 337766.1689 | Revised: |  | No. of Man-days:
New Corella | Del Pilar | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 18712.2458 | Actual: | 5.54%
New Corella | Del Pilar | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | Del Pilar | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
New Corella | Del Pilar | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started: | 2020-01-02
New Corella | Del Pilar | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 051 - Del Pilar - Jct. Silangan |  | GENERAL FUND CY 2020 | Maintenance | 4.17 | km | CBRMC | Project Cost: | 129495.366 | Target Completion Date: |  | Program: | 129495.366 | Planned: |  | No. of Persons: |  | Purchase Request # 20010093 (On process)
New Corella | Del Pilar | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 129495.366 | Revised: |  | No. of Man-days:
New Corella | Del Pilar | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
New Corella | Del Pilar | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | Del Pilar | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: |  | Date completed:
New Corella | Del Pilar | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started:
New Corella | New Sambog | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 052 - New Corella - New Sambog - Silangan |  | GENERAL FUND CY 2020 | Maintenance | 5.1 | km | MBA | Project Cost: | 371450.8414 | Target Completion Date: | 2020-12-31 23:59 | Program: | 371450.8414 | Planned: | 8.7% | No. of Persons: | 17 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020)
New Corella | New Sambog | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 371450.8414 | Revised: |  | No. of Man-days: | 374
New Corella | New Sambog | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 32316.2232 | Actual: | 8.7%
New Corella | New Sambog | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | New Sambog | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
New Corella | New Sambog | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started: | 2020-01-02
New Corella | New Sambog | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 052 - New Corella - New Sambog - Silangan |  | GENERAL FUND CY 2020 | Maintenance | 5.1 | km | CBRMC | Project Cost: | 148331.0556 | Target Completion Date: |  | Program: | 148331.0556 | Planned: |  | No. of Persons: |  | Purchase Request # 20010095 (On process)
New Corella | New Sambog | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 148331.0556 | Revised: |  | No. of Man-days:
New Corella | New Sambog | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
New Corella | New Sambog | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | New Sambog | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: |  | Date completed:
New Corella | New Sambog | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started:
New Corella | Poblacion | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 053 - Pob. New Corella - Prk. 10 Pob. |  | GENERAL FUND CY 2020 | Maintenance | 1.3 | km | MBA | Project Cost: | 28149.3653 | Target Completion Date: | 2020-12-31 23:59 | Program: | 28149.3653 | Planned: | 13.38% | No. of Persons: | 17 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020)
New Corella | Poblacion | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 28149.3653 | Revised: |  | No. of Man-days: | 374
New Corella | Poblacion | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 3766.3851 | Actual: | 13.38%
New Corella | Poblacion | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | Poblacion | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
New Corella | Poblacion | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started: | 2020-01-02
New Corella | Poblacion | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 053 - Pob. New Corella - Prk. 10 Pob. |  | GENERAL FUND CY 2020 | Maintenance | 1.3 | km | CBRMC | Project Cost: | 21190.1508 | Target Completion Date: |  | Program: | 21190.1508 | Planned: |  | No. of Persons: |  | Purchase Request # 20010155 (On process)
New Corella | Poblacion | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 21190.1508 | Revised: |  | No. of Man-days:
New Corella | Poblacion | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
New Corella | Poblacion | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | Poblacion | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: |  | Date completed:
New Corella | Poblacion | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started:
New Corella | New Sambog | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 054 - Prk. 7 Pob. - Jct. New Sambog |  | GENERAL FUND CY 2020 | Maintenance | 2.54 | km | MBA | Project Cost: | 171600.7916 | Target Completion Date: | 2020-12-31 23:59 | Program: | 171600.7916 | Planned: | 6.92% | No. of Persons: | 17 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020)
New Corella | New Sambog | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 171600.7916 | Revised: |  | No. of Man-days: | 374
New Corella | New Sambog | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 11874.7748 | Actual: | 6.92%
New Corella | New Sambog | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | New Sambog | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
New Corella | New Sambog | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started: | 2020-01-02
New Corella | New Sambog | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 054 - Prk. 7 Pob. - Jct. New Sambog |  | GENERAL FUND CY 2020 | Maintenance | 2.54 | km | CBRMC | Project Cost: | 113014.1376 | Target Completion Date: |  | Program: | 113014.1376 | Planned: |  | No. of Persons: |  | Purchase Request # 20010158 (On process)
New Corella | New Sambog | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 113014.1376 | Revised: |  | No. of Man-days:
New Corella | New Sambog | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
New Corella | New Sambog | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | New Sambog | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: |  | Date completed:
New Corella | New Sambog | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started:
New Corella | Sta. Fe-Del Monte | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 056 - Sta. Fe - Del Monte |  | GENERAL FUND CY 2020 | Maintenance | 3.34 | km | MBA | Project Cost: | 93676.7241 | Target Completion Date: | 2020-12-31 23:59 | Program: | 93676.7241 | Planned: | 11.64% | No. of Persons: | 17 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020)
New Corella | Sta. Fe-Del Monte | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 93676.7241 | Revised: |  | No. of Man-days: | 374
New Corella | Sta. Fe-Del Monte | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 10903.9707 | Actual: | 11.64%
New Corella | Sta. Fe-Del Monte | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | Sta. Fe-Del Monte | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
New Corella | Sta. Fe-Del Monte | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started: | 2020-01-02
New Corella | Sta. Fe-Del Monte | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 056 - Sta. Fe - Del Monte |  | GENERAL FUND CY 2020 | Maintenance | 3.34 | km | CBRMC | Project Cost: | 75342.7584 | Target Completion Date: |  | Program: | 75342.7584 | Planned: |  | No. of Persons: |  | Purchase Request # 20010160 (On process)
New Corella | Sta. Fe-Del Monte | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 75342.7584 | Revised: |  | No. of Man-days:
New Corella | Sta. Fe-Del Monte | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
New Corella | Sta. Fe-Del Monte | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | Sta. Fe-Del Monte | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: |  | Date completed:
New Corella | Sta. Fe-Del Monte | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started:
New Corella | New Bohol | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 058 - New Corella - New Bohol |  | GENERAL FUND CY 2020 | Maintenance | 11.54 | km | MBA | Project Cost: | 300034.9027 | Target Completion Date: | 2020-12-31 23:59 | Program: | 300034.9027 | Planned: | 17.21% | No. of Persons: | 17 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020)
New Corella | New Bohol | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 300034.9027 | Revised: |  | No. of Man-days: | 374
New Corella | New Bohol | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 51636.0068 | Actual: | 17.21%
New Corella | New Bohol | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | New Bohol | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
New Corella | New Bohol | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started: | 2020-01-02
New Corella | New Bohol | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 058 - New Corella - New Bohol |  | GENERAL FUND CY 2020 | Maintenance | 11.54 | km | CBRMC | Project Cost: | 221319.3528 | Target Completion Date: |  | Program: | 221319.3528 | Planned: |  | No. of Persons: |  | Purchase Request # 20010221 (On process)
New Corella | New Bohol | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 221319.3528 | Revised: |  | No. of Man-days:
New Corella | New Bohol | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
New Corella | New Bohol | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | New Bohol | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: |  | Date completed:
New Corella | New Bohol | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started:
New Corella | Carcor | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 059 - Jct. Carcor - Prk. 9 Bagsak |  | GENERAL FUND CY 2020 | Maintenance | 2.5 | km | MBA | Project Cost: | 161961.791 | Target Completion Date: | 2020-12-31 23:59 | Program: | 161961.791 | Planned: | 15.82% | No. of Persons: | 17 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020)
New Corella | Carcor | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 161961.791 | Revised: |  | No. of Man-days: | 374
New Corella | Carcor | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 25622.3553 | Actual: | 15.82%
New Corella | Carcor | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | Carcor | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
New Corella | Carcor | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started: | 2020-01-02
New Corella | Carcor | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 059 - Jct. Carcor - Prk. 9 Bagsak |  | GENERAL FUND CY 2020 | Maintenance | 2.5 | km | CBRMC | Project Cost: | 72988.2972 | Target Completion Date: |  | Program: | 72988.2972 | Planned: |  | No. of Persons: |  | Purchase Request # 20010223 (On process)
New Corella | Carcor | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 72988.2972 | Revised: |  | No. of Man-days:
New Corella | Carcor | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
New Corella | Carcor | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | Carcor | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: |  | Date completed:
New Corella | Carcor | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started:
New Corella | Carcor | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 060 - Carcor - Jct. Kauswagan |  | GENERAL FUND CY 2020 | Maintenance | 4.32 | km | MBA | Project Cost: | 304751.9237 | Target Completion Date: | 2020-12-31 23:59 | Program: | 304751.9237 | Planned: | 31.32% | No. of Persons: | 17 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020)
New Corella | Carcor | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 304751.9237 | Revised: |  | No. of Man-days: | 374
New Corella | Carcor | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 95448.3025 | Actual: | 31.32%
New Corella | Carcor | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | Carcor | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
New Corella | Carcor | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started: | 2020-01-02
New Corella | Carcor | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 060 - Carcor - Jct. Kauswagan |  | GENERAL FUND CY 2020 | Maintenance | 4.32 | km | CBRMC | Project Cost: | 101241.8316 | Target Completion Date: |  | Program: | 101241.8316 | Planned: |  | No. of Persons: |  | Purchase Request # 20010262 (On process)
New Corella | Carcor | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 101241.8316 | Revised: |  | No. of Man-days:
New Corella | Carcor | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
New Corella | Carcor | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | Carcor | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: |  | Date completed:
New Corella | Carcor | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started:
New Corella | Del Pilar | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 061 - Del Pilar - Prk. 9 Bagsak - San Jose |  | GENERAL FUND CY 2020 | Maintenance |  | km | MBA | Project Cost: | 505304.26 | Target Completion Date: | 2021-01-14 23:59 | Program: | 505304.26 | Planned: | 49.18% | No. of Persons: | 14 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020)
New Corella | Del Pilar | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-02-10 23:59 | Allotment: | 505304.26 | Revised: |  | No. of Man-days: | 210
New Corella | Del Pilar | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 248508.6351 | Actual: | 49.18%
New Corella | Del Pilar | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | Del Pilar | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
New Corella | Del Pilar | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started: | 2020-01-16
New Corella | Del Pilar | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 061 - Del Pilar - Prk. 9 Bagsak - San Jose |  | GENERAL FUND CY 2020 | Maintenance |  | km | CBRMC | Project Cost: | 251927.3484 | Target Completion Date: |  | Program: | 251927.3484 | Planned: |  | No. of Persons: |  | Purchase Request # 20010264 (On process)
New Corella | Del Pilar | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 251927.3484 | Revised: |  | No. of Man-days:
New Corella | Del Pilar | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
New Corella | Del Pilar | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | Del Pilar | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: |  | Date completed:
New Corella | Del Pilar | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started:
New Corella | Del Pilar | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 062 - Del Pilar - El Unido |  | GENERAL FUND CY 2020 | Maintenance | 1.32 | km | MBA | Project Cost: | 84027.808 | Target Completion Date: | 2020-12-31 23:59 | Program: | 84027.808 | Planned: | 10.78% | No. of Persons: | 17 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020)
New Corella | Del Pilar | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 84027.808 | Revised: |  | No. of Man-days: | 374
New Corella | Del Pilar | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 9058.1977 | Actual: | 10.78%
New Corella | Del Pilar | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | Del Pilar | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
New Corella | Del Pilar | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started: | 2020-01-02
New Corella | Del Pilar | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 062 - Del Pilar - El Unido |  | GENERAL FUND CY 2020 | Maintenance | 1.32 | km | CBRMC | Project Cost: | 40025.8404 | Target Completion Date: |  | Program: | 40025.8404 | Planned: |  | No. of Persons: |  | Purchase Request # 20010265 (On process)
New Corella | Del Pilar | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 40025.8404 | Revised: |  | No. of Man-days:
New Corella | Del Pilar | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
New Corella | Del Pilar | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | Del Pilar | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: |  | Date completed:
New Corella | Del Pilar | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started:
New Corella | Del Pilar | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 063 - San Juan - New Talisay |  | GENERAL FUND CY 2020 | Maintenance | 5.13 | km | MBA | Project Cost: | 442982.6933 | Target Completion Date: | 2020-12-31 23:59 | Program: | 442982.6933 | Planned: | 13.42% | No. of Persons: | 17 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020)
New Corella | Del Pilar | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 442982.6933 | Revised: |  | No. of Man-days: | 374
New Corella | Del Pilar | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 59448.2774 | Actual: | 13.42%
New Corella | Del Pilar | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | Del Pilar | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
New Corella | Del Pilar | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started: | 2020-01-02
New Corella | Del Pilar | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 063 - San Juan - New Talisay |  | GENERAL FUND CY 2020 | Maintenance | 5.13 | km | CBRMC | Project Cost: | 131849.8272 | Target Completion Date: |  | Program: | 131849.8272 | Planned: |  | No. of Persons: |  | Purchase Request # 20010267 (On process)
New Corella | Del Pilar | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 131849.8272 | Revised: |  | No. of Man-days:
New Corella | Del Pilar | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
New Corella | Del Pilar | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | Del Pilar | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: |  | Date completed:
New Corella | Del Pilar | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started:
New Corella | Del Pilar | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 064 - San Juan - Kauswagan - New Cortez |  | GENERAL FUND CY 2020 | Maintenance | 3.22 | km | MBA | Project Cost: | 128969.53 | Target Completion Date: | 2021-01-14 23:59 | Program: | 128969.53 | Planned: | 41.14% | No. of Persons: | 14 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020)
New Corella | Del Pilar | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-02-10 23:59 | Allotment: | 128969.53 | Revised: |  | No. of Man-days: | 210
New Corella | Del Pilar | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 53058.0646 | Actual: | 41.14%
New Corella | Del Pilar | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage:
New Corella | Del Pilar | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
New Corella | Del Pilar | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started: | 2020-01-16
New Corella | Del Pilar | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 064 - San Juan - Kauswagan - New Cortez |  | GENERAL FUND CY 2020 | Maintenance | 3.22 | km | CBRMC | Project Cost: | 68279.3748 | Target Completion Date: |  | Program: | 68279.3748 | Planned: |  | No. of Persons: |  | Procurement on process
New Corella | Del Pilar | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 68279.3748 | Revised: |  | No. of Man-days:
New Corella | Del Pilar | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
New Corella | Del Pilar | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | Del Pilar | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: |  | Date completed:
New Corella | Del Pilar | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started:
New Corella | New Bohol | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 065 - New Bohol - Jct. El Unido |  | GENERAL FUND CY 2020 | Maintenance | 2.12 | km | MBA | Project Cost: | 177260.81 | Target Completion Date: | 2021-01-14 23:59 | Program: | 177260.81 | Planned: |  | No. of Persons: | 14 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020)
New Corella | New Bohol | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-02-10 23:59 | Allotment: | 177260.81 | Revised: |  | No. of Man-days: | 210
New Corella | New Bohol | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 50005.2745 | Actual: | 28.21%
New Corella | New Bohol | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | #VALUE!
New Corella | New Bohol | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
New Corella | New Bohol | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started: | 2020-01-16
New Corella | New Bohol | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 065 - New Bohol - Jct. El Unido |  | GENERAL FUND CY 2020 | Maintenance | 2.12 | km | CBRMC | Project Cost: | 65924.9136 | Target Completion Date: |  | Program: | 65924.9136 | Planned: |  | No. of Persons: |  | Purchase Request # 20010275 (On process)
New Corella | New Bohol | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 65924.9136 | Revised: |  | No. of Man-days:
New Corella | New Bohol | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
New Corella | New Bohol | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | New Bohol | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: |  | Date completed:
New Corella | New Bohol | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started:
New Corella | Mesaoy | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 066 - New Corella - El Unido - Jct. Mesaoy |  | GENERAL FUND CY 2020 | Maintenance | 8.63 | km | MBA | Project Cost: | 792432.45 | Target Completion Date: | 2021-01-14 23:59 | Program: | 792432.45 | Planned: | 53.98% | No. of Persons: | 14 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020)
New Corella | Mesaoy | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-02-10 23:59 | Allotment: | 792432.45 | Revised: |  | No. of Man-days: | 210
New Corella | Mesaoy | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 427755.0365 | Actual: | 53.98%
New Corella | Mesaoy | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | Mesaoy | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
New Corella | Mesaoy | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started: | 2020-01-16
New Corella | Mesaoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 066 - New Corella - El Unido - Jct. Mesaoy |  | GENERAL FUND CY 2020 | Maintenance | 8.63 | km | CBRMC | Project Cost: | 249572.8872 | Target Completion Date: |  | Program: | 249572.8872 | Planned: |  | No. of Persons: |  | Purchase Request # 20010291 (On process)
New Corella | Mesaoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 249572.8872 | Revised: |  | No. of Man-days:
New Corella | Mesaoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
New Corella | Mesaoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | Mesaoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: |  | Date completed:
New Corella | Mesaoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started:
New Corella | Mesaoy | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 067 - Mesaoy - Dasing |  | GENERAL FUND CY 2020 | Maintenance | 1.39 | km | MBA | Project Cost: | 130632.25 | Target Completion Date: | 2021-01-14 23:59 | Program: | 130632.25 | Planned: | 48.79% | No. of Persons: | 14 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020)
New Corella | Mesaoy | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-02-10 23:59 | Allotment: | 130632.25 | Revised: |  | No. of Man-days: | 210
New Corella | Mesaoy | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 63735.4748 | Actual: | 48.79%
New Corella | Mesaoy | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | Mesaoy | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
New Corella | Mesaoy | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started: | 2020-01-16
New Corella | Mesaoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 067 - Mesaoy - Dasing |  | GENERAL FUND CY 2020 | Maintenance | 1.39 | km | CBRMC | Project Cost: | 54152.6076 | Target Completion Date: |  | Program: | 54152.6076 | Planned: |  | No. of Persons: |  | Purchase Request # 20010294 (On process)
New Corella | Mesaoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 54152.6076 | Revised: |  | No. of Man-days:
New Corella | Mesaoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
New Corella | Mesaoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | Mesaoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: |  | Date completed:
New Corella | Mesaoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started:
New Corella | Del Pilar | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 068 - Jct. San Juan - Jct. Mesaoy |  | GENERAL FUND CY 2020 | Maintenance | 1.82 | km | MBA | Project Cost: | 135657.3072 | Target Completion Date: | 2020-12-31 23:59 | Program: | 135657.3072 | Planned: | 7.32% | No. of Persons: | 17 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020)
New Corella | Del Pilar | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 135657.3072 | Revised: |  | No. of Man-days: | 374
New Corella | Del Pilar | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 9930.1149 | Actual: | 7.32%
New Corella | Del Pilar | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | Del Pilar | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
New Corella | Del Pilar | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started: | 2020-01-02
New Corella | Del Pilar | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 068 - Jct. San Juan - Jct. Mesaoy |  | GENERAL FUND CY 2020 | Maintenance | 1.82 | km | CBRMC | Project Cost: | 68279.3748 | Target Completion Date: |  | Program: | 68279.3748 | Planned: |  | No. of Persons: |  | Purchase Request # 20010294 (On process)
New Corella | Del Pilar | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 68279.3748 | Revised: |  | No. of Man-days:
New Corella | Del Pilar | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
New Corella | Del Pilar | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | Del Pilar | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: |  | Date completed:
New Corella | Del Pilar | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started:
New Corella | Mesaoy-New Bohol | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 070 - Mesaoy - New Bohol |  | GENERAL FUND CY 2020 | Maintenance | 5.36 | km | MBA | Project Cost: | 665667.84 | Target Completion Date: | 2021-01-14 23:59 | Program: | 665667.84 | Planned: | 41.99% | No. of Persons: | 14 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020)
New Corella | Mesaoy-New Bohol | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-02-10 23:59 | Allotment: | 665667.84 | Revised: |  | No. of Man-days: | 210
New Corella | Mesaoy-New Bohol | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 279513.926 | Actual: | 41.99%
New Corella | Mesaoy-New Bohol | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | Mesaoy-New Bohol | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
New Corella | Mesaoy-New Bohol | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started: | 2020-01-16
New Corella | Mesaoy-New Bohol | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 070 - Mesaoy - New Bohol |  | GENERAL FUND CY 2020 | Maintenance | 5.36 | km | CBRMC | Project Cost: | 261345.1932 | Target Completion Date: |  | Program: | 261345.1932 | Planned: |  | No. of Persons: |  | Purchase Request # 20010298 (On process)
New Corella | Mesaoy-New Bohol | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 261345.1932 | Revised: |  | No. of Man-days:
New Corella | Mesaoy-New Bohol | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
New Corella | Mesaoy-New Bohol | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | Mesaoy-New Bohol | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: |  | Date completed:
New Corella | Mesaoy-New Bohol | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started:
Asuncion | Napungas | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 147 - Prk. 1, Maunlom-Prk. 6 Maunlom Road |  | GENERAL FUND CY 2020 | Maintenance | 3.56 | km | MBA | Project Cost: | 115812.32 | Target Completion Date: | 2021-02-15 23:59 | Program: | 115812.32 | Planned: | 38.9% | No. of Persons: | 14 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020)
Asuncion | Napungas | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-03-14 23:59 | Allotment: | 115812.32 | Revised: |  | No. of Man-days: | 210
Asuncion | Napungas | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 45050.9925 | Actual: | 38.9%
Asuncion | Napungas | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0%
Asuncion | Napungas | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
Asuncion | Napungas | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started: | 2020-02-17
Asuncion | Napungas | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 147 - Prk. 1, Maunlom-Prk. 6 Maunlom Road |  | GENERAL FUND CY 2020 | Maintenance | 3.56 | km | CBRMC | Project Cost: | 65924.9136 | Target Completion Date: |  | Program: | 65924.9136 | Planned: |  | No. of Persons: |  | Purchase Request # 20010302 (On process)
Asuncion | Napungas | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 65924.9136 | Revised: |  | No. of Man-days:
Asuncion | Napungas | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Asuncion | Napungas | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Asuncion | Napungas | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: |  | Date completed:
Asuncion | Napungas | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started:
Asuncion | Binancian | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 149 - New Visayas - Binancian |  | GENERAL FUND CY 2020 | Maintenance | 7.77 | km | MBA | Project Cost: | 62394.7204 | Target Completion Date: | 2020-12-31 23:59 | Program: | 62394.7204 | Planned: | 3.47% | No. of Persons: | 17 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020)
Asuncion | Binancian | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 62394.7204 | Revised: |  | No. of Man-days: | 374
Asuncion | Binancian | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 2165.0968 | Actual: | 3.47%
Asuncion | Binancian | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0%
Asuncion | Binancian | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
Asuncion | Binancian | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started: | 2020-01-02
Asuncion | Binancian | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 149 - New Visayas - Binancian |  | GENERAL FUND CY 2020 | Maintenance | 7.77 | km | CBRMC | Project Cost: | 134204.2884 | Target Completion Date: |  | Program: | 134204.2884 | Planned: |  | No. of Persons: |  | Purchase Request # 20010305 (On process)
Asuncion | Binancian | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 134204.2884 | Revised: |  | No. of Man-days:
Asuncion | Binancian | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Asuncion | Binancian | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Asuncion | Binancian | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: |  | Date completed:
Asuncion | Binancian | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started:
San Isidro | Datu Balong-Mamalian | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 150 - Datu Balong - Prk. Mamalian |  | GENERAL FUND CY 2020 | Maintenance | 3.46 | km | MBA | Project Cost: | 45089.8864 | Target Completion Date: | 2020-12-31 23:59 | Program: | 45089.8864 | Planned: | 6.37% | No. of Persons: | 17 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020)
San Isidro | Datu Balong-Mamalian | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 45089.8864 | Revised: |  | No. of Man-days: | 374
San Isidro | Datu Balong-Mamalian | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 2872.2258 | Actual: | 6.37%
San Isidro | Datu Balong-Mamalian | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0%
San Isidro | Datu Balong-Mamalian | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | 2 | 2020-01-02 | Date completed:
San Isidro | Datu Balong-Mamalian | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started: | 2020-01-02
San Isidro | Datu Balong-Mamalian | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 150 - Datu Balong - Prk. Mamalian |  | GENERAL FUND CY 2020 | Maintenance | 3.46 | km | CBRMC | Project Cost: | 61215.9912 | Target Completion Date: |  | Program: | 61215.9912 | Planned: |  | No. of Persons: |  | Purchase Request # 20010306 (On process)
San Isidro | Datu Balong-Mamalian | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 61215.9912 | Revised: |  | No. of Man-days:
San Isidro | Datu Balong-Mamalian | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
San Isidro | Datu Balong-Mamalian | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
San Isidro | Datu Balong-Mamalian | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: |  | Date completed:
San Isidro | Datu Balong-Mamalian | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started:
Tagum City | Cuambogan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | RURAL ELECTRIFICATION PROJECT LS - P 5,000,000.00 | Rural Electrification at RAMADA Compound Purok Sto. Niño, Brgy. Cuambogan, Tagum City |  | 20% Development Fund CY 2020 | Electrification |  | km |  | Project Cost: | 1000000 | Target Completion Date: |  | Program: | 1000000 | Planned: |  | No. of Persons: |  | PO on process - Tagum Constrak
Tagum City | Cuambogan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | RURAL ELECTRIFICATION PROJECT LS - P 5,000,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 1000000 | Revised: |  | No. of Man-days:
Tagum City | Cuambogan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | RURAL ELECTRIFICATION PROJECT LS - P 5,000,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Tagum City | Cuambogan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | RURAL ELECTRIFICATION PROJECT LS - P 5,000,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Tagum City | Cuambogan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | RURAL ELECTRIFICATION PROJECT LS - P 5,000,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Tagum City | Cuambogan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | RURAL ELECTRIFICATION PROJECT LS - P 5,000,000.00 | [7 empty] | Date Started:
Asuncion | Camansa | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | RURAL ELECTRIFICATION PROJECT LS - P 5,000,000.00 | Rural Electrification at Lower Camansa, Prk.5 to 6 Lower, Brgy. Camansa, Asuncion |  | 20% Development Fund CY 2020 | Electrification |  | km |  | Project Cost: | 3000000 | Target Completion Date: |  | Program: | 3000000 | Planned: |  | No. of Persons: |  | PO on process - Tagum Constrak
Asuncion | Camansa | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | RURAL ELECTRIFICATION PROJECT LS - P 5,000,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 3000000 | Revised: |  | No. of Man-days:
Asuncion | Camansa | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | RURAL ELECTRIFICATION PROJECT LS - P 5,000,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Asuncion | Camansa | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | RURAL ELECTRIFICATION PROJECT LS - P 5,000,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Asuncion | Camansa | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | RURAL ELECTRIFICATION PROJECT LS - P 5,000,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Asuncion | Camansa | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | RURAL ELECTRIFICATION PROJECT LS - P 5,000,000.00 | [7 empty] | Date Started:
Asuncion | Doña Andrea | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | RURAL ELECTRIFICATION PROJECT LS - P 5,000,000.00 | Completion of Electrification at at Purok 10 and Purok 9, Phase 2, Brgy. Doña Andrea, Asuncion |  | 20% Development Fund CY 2020 | Electrification |  | km |  | Project Cost: | 1000000 | Target Completion Date: |  | Program: | 1000000 | Planned: |  | No. of Persons: |  | For preparation of POW and Plans
Asuncion | Doña Andrea | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | RURAL ELECTRIFICATION PROJECT LS - P 5,000,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 1000000 | Revised: |  | No. of Man-days:
Asuncion | Doña Andrea | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | RURAL ELECTRIFICATION PROJECT LS - P 5,000,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Asuncion | Doña Andrea | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | RURAL ELECTRIFICATION PROJECT LS - P 5,000,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Asuncion | Doña Andrea | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | RURAL ELECTRIFICATION PROJECT LS - P 5,000,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Asuncion | Doña Andrea | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | RURAL ELECTRIFICATION PROJECT LS - P 5,000,000.00 | [7 empty] | Date Started:
Asuncion | Sta. Felomina | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | ROAD ID 008 - Sta. Felomina - San Roque |  | 20% Development Fund CY 2020 | Road Rehabilitaion | 7.68 | km | Admin | Project Cost: | 2304000 | Target Completion Date: |  | Program: | 2304000 | Planned: |  | No. of Persons: |  | Post qualification on process
Asuncion | Sta. Felomina | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 2304000 | Revised: |  | No. of Man-days:
Asuncion | Sta. Felomina | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual:
Asuncion | Sta. Felomina | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Asuncion | Sta. Felomina | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Asuncion | Sta. Felomina | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Date Started:
Talaingod | Sto. Niño-Palma Gil | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | ROAD ID 019 - Sto. Niño - Palma Gil - Sitio Opao |  | 20% Development Fund CY 2020 | Road Rehabilitaion | 5.99 | km | Admin | Project Cost: | 1797000 | Target Completion Date: |  | Program: | 1797000 | Planned: |  | No. of Persons: |  | POW on process
Talaingod | Sto. Niño-Palma Gil | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 1797000 | Revised: |  | No. of Man-days:
Talaingod | Sto. Niño-Palma Gil | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual:
Talaingod | Sto. Niño-Palma Gil | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Talaingod | Sto. Niño-Palma Gil | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Talaingod | Sto. Niño-Palma Gil | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Date Started:
Talaingod | Daligdigon-Paiton | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | ROAD ID 023 - Sto. Niño - Daligdigon - Paiton |  | 20% Development Fund CY 2020 | Road Rehabilitaion | 11.6 | km | Admin | Project Cost: | 3480000 | Target Completion Date: |  | Program: | 3480000 | Planned: |  | No. of Persons: |  | POW on process
Talaingod | Daligdigon-Paiton | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 3480000 | Revised: |  | No. of Man-days:
Talaingod | Daligdigon-Paiton | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual:
Talaingod | Daligdigon-Paiton | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Talaingod | Daligdigon-Paiton | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Talaingod | Daligdigon-Paiton | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Date Started:
Talaingod | Paiton | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | ROAD ID 024 - Jct. Paiton - Mibolo |  | 20% Development Fund CY 2020 | Road Rehabilitaion | 23.9 | km | Admin | Project Cost: | 7170000 | Target Completion Date: |  | Program: | 7170000 | Planned: |  | No. of Persons: |  | POW on process
Talaingod | Paiton | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 7170000 | Revised: |  | No. of Man-days:
Talaingod | Paiton | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual:
Talaingod | Paiton | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Talaingod | Paiton | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Talaingod | Paiton | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Date Started:
Kapalong | Florida | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | ROAD ID 024 - Florida - Suaon - Jct. Gupitan |  | 20% Development Fund CY 2020 | Road Rehabilitaion | 15.57 | km | Admin | Project Cost: | 4671000 | Target Completion Date: |  | Program: | 4671000 | Planned: |  | No. of Persons: |  | PO on process - Royal Summit
Kapalong | Florida | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 4671000 | Revised: |  | No. of Man-days:
Kapalong | Florida | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual:
Kapalong | Florida | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Kapalong | Florida | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Kapalong | Florida | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Date Started:
San Isidro | Datu Balong | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | ROAD ID 040 - Datu Balong - Pinamuno |  | 20% Development Fund CY 2020 | Road Rehabilitaion | 2.74 | km | Admin | Project Cost: | 822000 | Target Completion Date: |  | Program: | 822000 | Planned: |  | No. of Persons: |  | POW on process
San Isidro | Datu Balong | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 822000 | Revised: |  | No. of Man-days:
San Isidro | Datu Balong | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual:
San Isidro | Datu Balong | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
San Isidro | Datu Balong | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
San Isidro | Datu Balong | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Date Started:
New Corella | Macgum | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | ROAD ID 048 - New Corella - Saug |  | 20% Development Fund CY 2020 | Road Rehabilitaion | 12.52 | km | Admin | Project Cost: | 20571000 | Target Completion Date: |  | Program: | 20571000 | Planned: |  | No. of Persons: |  | POW on process
New Corella | Macgum | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 20571000 | Revised: |  | No. of Man-days:
New Corella | Macgum | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual:
New Corella | Macgum | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | Macgum | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
New Corella | Macgum | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Date Started:
Asuncion | Canatan-Doña andrea | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | ROAD ID 074 - Jct. Highway Canatan - Doña Andrea |  | 20% Development Fund CY 2020 | Road Rehabilitaion | 4.34 | km | Admin | Project Cost: | 1302000 | Target Completion Date: |  | Program: | 1302000 | Planned: |  | No. of Persons: |  | POW on process
Asuncion | Canatan-Doña andrea | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 1302000 | Revised: |  | No. of Man-days:
Asuncion | Canatan-Doña andrea | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Asuncion | Canatan-Doña andrea | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Asuncion | Canatan-Doña andrea | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Asuncion | Canatan-Doña andrea | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Date Started:
Kapalong | Florida | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | ROAD ID 030 - Florida - New Boholano |  | 20% Development Fund CY 2020 | Road Rehabilitaion | 2.54 | km | Admin | Project Cost: | 762000 | Target Completion Date: |  | Program: | 762000 | Planned: |  | No. of Persons: |  | POW on process
Kapalong | Florida | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 762000 | Revised: |  | No. of Man-days:
Kapalong | Florida | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual:
Kapalong | Florida | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Kapalong | Florida | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Kapalong | Florida | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Date Started:
Asuncion | New Loon | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | ROAD ID 031 - Jct. New Boholano - New Loon |  | 20% Development Fund CY 2020 | Road Rehabilitaion | 4.77 | km | Admin | Project Cost: | 1431000 | Target Completion Date: |  | Program: | 1431000 | Planned: |  | No. of Persons: |  | POW on process
Asuncion | New Loon | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 1431000 | Revised: |  | No. of Man-days:
Asuncion | New Loon | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Asuncion | New Loon | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Asuncion | New Loon | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Asuncion | New Loon | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Date Started:
New Corella | Mesaoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | ROAD ID 069 - Mesaoy - Jct. Mahayahay |  | 20% Development Fund CY 2020 | Road Rehabilitaion | 4.6 | km | Admin | Project Cost: | 1380000 | Target Completion Date: |  | Program: | 1380000 | Planned: |  | No. of Persons: |  | POW on process
New Corella | Mesaoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 1380000 | Revised: |  | No. of Man-days:
New Corella | Mesaoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual:
New Corella | Mesaoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | Mesaoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
New Corella | Mesaoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Date Started:
Asuncion | Cabaywa | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | ROAD ID 071 - Lower Asuncion - Upper Asuncion |  | 20% Development Fund CY 2020 | Road Rehabilitaion |  | km | Admin | Project Cost: | 1302000 | Target Completion Date: |  | Program: | 1302000 | Planned: |  | No. of Persons: |  | Plan On-going
Asuncion | Cabaywa | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 1302000 | Revised: |  | No. of Man-days:
Asuncion | Cabaywa | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Asuncion | Cabaywa | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Asuncion | Cabaywa | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Asuncion | Cabaywa | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Date Started:
Tagum City | AAT | 1st Eng'g. Dist. | On-going | 2020-05-18 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS LOCAL ROADS & DRAINAGE DEV'T. PROJECT - LS P15,590,910.00 | Rehab. Of Various Local Roads @ Tagum City |  | 20% Development Fund CY 2020 | Rehabilitaion |  | km | Admin | Project Cost: | 2518182 | Target Completion Date: | 2020-10-20 | Program: | 2518182 | Planned: | 18.41% | No. of Persons: | 10 | On-going
Tagum City | AAT | 1st Eng'g. Dist. | On-going | 2020-05-18 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS LOCAL ROADS & DRAINAGE DEV'T. PROJECT - LS P15,590,910.00 | [7 empty] | Project Engineer: | Bataller | Revised Completion Date: |  | Allotment: | 2518182 | Revised: |  | No. of Man-days: | 150
Tagum City | AAT | 1st Eng'g. Dist. | On-going | 2020-05-18 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS LOCAL ROADS & DRAINAGE DEV'T. PROJECT - LS P15,590,910.00 | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: | 18.41%
Tagum City | AAT | 1st Eng'g. Dist. | On-going | 2020-05-18 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS LOCAL ROADS & DRAINAGE DEV'T. PROJECT - LS P15,590,910.00 | [7 empty] | Duration: | 155 | No. of days extended: |  |  |  | Slippage: | 0%
Tagum City | AAT | 1st Eng'g. Dist. | On-going | 2020-05-18 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS LOCAL ROADS & DRAINAGE DEV'T. PROJECT - LS P15,590,910.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Tagum City | AAT | 1st Eng'g. Dist. | On-going | 2020-05-18 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS LOCAL ROADS & DRAINAGE DEV'T. PROJECT - LS P15,590,910.00 | [7 empty] | Date Started: | 2020-05-18
Asuncion | AAA | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS LOCAL ROADS & DRAINAGE DEV'T. PROJECT - LS P15,590,910.00 | Rehab. Of Various Local Roads @ Asuncion |  | 20% Development Fund CY 2020 | Rehabilitaion |  | km | Admin | Project Cost: | 2518182 | Target Completion Date: | 2020-10-20 | Program: | 2518182 | Planned: | 37.83% | No. of Persons: | 10 | On-going
Asuncion | AAA | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS LOCAL ROADS & DRAINAGE DEV'T. PROJECT - LS P15,590,910.00 | [7 empty] | Project Engineer: | Bataller | Revised Completion Date: |  | Allotment: | 2518182 | Revised: |  | No. of Man-days: | 310
Asuncion | AAA | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS LOCAL ROADS & DRAINAGE DEV'T. PROJECT - LS P15,590,910.00 | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: | 37.82%
Asuncion | AAA | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS LOCAL ROADS & DRAINAGE DEV'T. PROJECT - LS P15,590,910.00 | [7 empty] | Duration: | 155 | No. of days extended: |  |  |  | Slippage: | -0.01%
Asuncion | AAA | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS LOCAL ROADS & DRAINAGE DEV'T. PROJECT - LS P15,590,910.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Asuncion | AAA | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS LOCAL ROADS & DRAINAGE DEV'T. PROJECT - LS P15,590,910.00 | [7 empty] | Date Started: | 2020-05-18
Kapalong | AAK | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS LOCAL ROADS & DRAINAGE DEV'T. PROJECT - LS P15,590,910.00 | Rehab. Of Various Local Roads @ Kapalong |  | 20% Development Fund CY 2020 | Rehabilitaion |  | km | Admin | Project Cost: | 2518182 | Target Completion Date: |  | Program: | 2518182 | Planned: |  | No. of Persons: |  | For Implementation
Kapalong | AAK | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS LOCAL ROADS & DRAINAGE DEV'T. PROJECT - LS P15,590,910.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 2518182 | Revised: |  | No. of Man-days:
Kapalong | AAK | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS LOCAL ROADS & DRAINAGE DEV'T. PROJECT - LS P15,590,910.00 | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual:
Kapalong | AAK | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS LOCAL ROADS & DRAINAGE DEV'T. PROJECT - LS P15,590,910.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Kapalong | AAK | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS LOCAL ROADS & DRAINAGE DEV'T. PROJECT - LS P15,590,910.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Kapalong | AAK | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS LOCAL ROADS & DRAINAGE DEV'T. PROJECT - LS P15,590,910.00 | [7 empty] | Date Started:
New Corella | AAN | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS LOCAL ROADS & DRAINAGE DEV'T. PROJECT - LS P15,590,910.00 | Rehab. Of Various Local Roads @ New Corella |  | 20% Development Fund CY 2020 | Rehabilitaion |  | km | Admin | Project Cost: | 2518182 | Target Completion Date: |  | Program: | 2518182 | Planned: |  | No. of Persons: |  | POW on process
New Corella | AAN | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS LOCAL ROADS & DRAINAGE DEV'T. PROJECT - LS P15,590,910.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 2518182 | Revised: |  | No. of Man-days:
New Corella | AAN | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS LOCAL ROADS & DRAINAGE DEV'T. PROJECT - LS P15,590,910.00 | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual:
New Corella | AAN | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS LOCAL ROADS & DRAINAGE DEV'T. PROJECT - LS P15,590,910.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | AAN | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS LOCAL ROADS & DRAINAGE DEV'T. PROJECT - LS P15,590,910.00 | [7 empty] | Date Allotment Released: |  | Date completed:
New Corella | AAN | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS LOCAL ROADS & DRAINAGE DEV'T. PROJECT - LS P15,590,910.00 | [7 empty] | Date Started:
San Isidro | AAS | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS LOCAL ROADS & DRAINAGE DEV'T. PROJECT - LS P15,590,910.00 | Rehab. Of Various Local Roads @ San Isidro |  | 20% Development Fund CY 2020 | Rehabilitaion |  | km | Admin | Project Cost: | 2518182 | Target Completion Date: |  | Program: | 2518182 | Planned: |  | No. of Persons: |  | POW on process
San Isidro | AAS | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS LOCAL ROADS & DRAINAGE DEV'T. PROJECT - LS P15,590,910.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 2518182 | Revised: |  | No. of Man-days:
San Isidro | AAS | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS LOCAL ROADS & DRAINAGE DEV'T. PROJECT - LS P15,590,910.00 | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual:
San Isidro | AAS | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS LOCAL ROADS & DRAINAGE DEV'T. PROJECT - LS P15,590,910.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
San Isidro | AAS | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS LOCAL ROADS & DRAINAGE DEV'T. PROJECT - LS P15,590,910.00 | [7 empty] | Date Allotment Released: |  | Date completed:
San Isidro | AAS | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS LOCAL ROADS & DRAINAGE DEV'T. PROJECT - LS P15,590,910.00 | [7 empty] | Date Started:
Talaingod | AAT | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS LOCAL ROADS & DRAINAGE DEV'T. PROJECT - LS P15,590,910.00 | Rehab. Of Various Local Roads @ Talaingod |  | 20% Development Fund CY 2020 | Rehabilitaion |  | km | Admin | Project Cost: | 2518182 | Target Completion Date: |  | Program: | 2518182 | Planned: |  | No. of Persons: |  | For Implementation
Talaingod | AAT | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS LOCAL ROADS & DRAINAGE DEV'T. PROJECT - LS P15,590,910.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 2518182 | Revised: |  | No. of Man-days:
Talaingod | AAT | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS LOCAL ROADS & DRAINAGE DEV'T. PROJECT - LS P15,590,910.00 | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual:
Talaingod | AAT | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS LOCAL ROADS & DRAINAGE DEV'T. PROJECT - LS P15,590,910.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Talaingod | AAT | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS LOCAL ROADS & DRAINAGE DEV'T. PROJECT - LS P15,590,910.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Talaingod | AAT | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS LOCAL ROADS & DRAINAGE DEV'T. PROJECT - LS P15,590,910.00 | [7 empty] | Date Started:
Tagum City | Mankilam | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | Construction of DAVNOR Tech-Vocational Center, Government Center, Mankilam, Tagum City |  | 20% Development Fund CY 2020 | Building |  | sq.m | Admin | Project Cost: | 8000000 | Target Completion Date: |  | Program: | 8000000 | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
Tagum City | Mankilam | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 8000000 | Revised: |  | No. of Man-days:
Tagum City | Mankilam | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual:
Tagum City | Mankilam | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Tagum City | Mankilam | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Tagum City | Mankilam | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Date Started:
Tagum City | Mankilam | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | Improvement of PSWDO Bodega Government Cente, Mankilam, Tagum City |  | 20% Development Fund CY 2020 | Building |  | sq.m | Admin | Project Cost: | 1000000 | Target Completion Date: |  | Program: | 1000000 | Planned: |  | No. of Persons: |  | POW and Plans on-going
Tagum City | Mankilam | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 1000000 | Revised: |  | No. of Man-days:
Tagum City | Mankilam | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual:
Tagum City | Mankilam | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Tagum City | Mankilam | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Tagum City | Mankilam | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Date Started:
San Isidro | Mamangan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | Renovation/Improvement of MAFAMCO Consumer's Bldg., Brgy. Mamangan, San Isidro |  | 20% Development Fund CY 2020 | Building |  | sq.m | Contract | Project Cost: | 800000 | Target Completion Date: |  | Program: | 800000 | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
San Isidro | Mamangan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 800000 | Revised: |  | No. of Man-days:
San Isidro | Mamangan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
San Isidro | Mamangan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
San Isidro | Mamangan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
San Isidro | Mamangan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Date Started:
Asuncion | Camansa | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | Construction of IP Council of Women Training Center, Camansa Kamadi District, Asuncion |  | 20% Development Fund CY 2020 | Building |  | sq.m | Admin | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
Asuncion | Camansa | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Asuncion | Camansa | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual:
Asuncion | Camansa | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Asuncion | Camansa | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Asuncion | Camansa | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Date Started:
New Corella | Cabidianan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | Construction of One(1) unit School Building at Cabidianan E/S, New Corella |  | 20% Development Fund CY 2020 | Building |  | sq.m | Contract | Project Cost: | 1300000 | Target Completion Date: |  | Program: | 1300000 | Planned: |  | No. of Persons:
New Corella | Cabidianan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 1300000 | Revised: |  | No. of Man-days:
New Corella | Cabidianan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
New Corella | Cabidianan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | Cabidianan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
New Corella | Cabidianan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Date Started:
Kapalong | Florida | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | Construction of one(1) unit School Building at Kamansi Integrated School, Florida, kapalong |  | 20% Development Fund CY 2020 | Building |  | sq.m | Contract | Project Cost: | 1300000 | Target Completion Date: |  | Program: | 1300000 | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
Kapalong | Florida | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 1300000 | Revised: |  | No. of Man-days:
Kapalong | Florida | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Kapalong | Florida | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Kapalong | Florida | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Kapalong | Florida | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Date Started:
Asuncion | Magatos | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | Construction of one(1) unit School Building at Magatos E/S, Magatos, Asuncion |  | 20% Development Fund CY 2020 | Building |  | sq.m | Contract | Project Cost: | 1300000 | Target Completion Date: |  | Program: | 1300000 | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
Asuncion | Magatos | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 1300000 | Revised: |  | No. of Man-days:
Asuncion | Magatos | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Asuncion | Magatos | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Asuncion | Magatos | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Asuncion | Magatos | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Date Started:
Talaingod | Sta. Cruz | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | Construction of one(1) unit School Building at Sta. Cruz E/S, New Corella |  | 20% Development Fund CY 2020 | Building |  | sq.m |  | Project Cost: | 1300000 | Target Completion Date: |  | Program: | 1300000 | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
Talaingod | Sta. Cruz | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 1300000 | Revised: |  | No. of Man-days:
Talaingod | Sta. Cruz | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Talaingod | Sta. Cruz | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Talaingod | Sta. Cruz | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Talaingod | Sta. Cruz | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Date Started:
Talaingod | Dagohoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | Construction Women Development Center, Dagohoy, Talaingod |  | 20% Development Fund CY 2020 | Building |  | sq.m |  | Project Cost: | 1000000 | Target Completion Date: |  | Program: | 1000000 | Planned: |  | No. of Persons: |  | Post qualification on process
Talaingod | Dagohoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 1000000 | Revised: |  | No. of Man-days:
Talaingod | Dagohoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Talaingod | Dagohoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Talaingod | Dagohoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Talaingod | Dagohoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Date Started:
Asuncion | Cambanogoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | Construction of Municipal Triball Hall, Asuncion |  | 20% Development Fund CY 2020 | Building |  | sq.m | Contract | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
Asuncion | Cambanogoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Asuncion | Cambanogoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Asuncion | Cambanogoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Asuncion | Cambanogoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Asuncion | Cambanogoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Date Started:
Kapalong | Maniki | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | Construction of Municipal Triball Hall, Kapalong |  | 20% Development Fund CY 2020 | Building |  | sq.m | Contract | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
Kapalong | Maniki | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Kapalong | Maniki | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Kapalong | Maniki | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Kapalong | Maniki | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Kapalong | Maniki | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Date Started:
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | Construction of Municipal Triball Hall, Talaingod |  | 20% Development Fund CY 2020 | Building |  | sq.m | Contract | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Date Started:
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | DISASTER PREVENTION AND MITIGATION PROGRAM - FLOOD CONTROL AND SLOPE PROTECTION PROJECT (Revetment of Dike and Slope Protection) | Rehab./Impv't. of Sto. Niño-Daligdigon-Paiton |  | 5% CALAMITY FUND CY 2020 | Road |  | km |  | Project Cost: | 1000000 | Target Completion Date: |  | Program: | 1000000 | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | DISASTER PREVENTION AND MITIGATION PROGRAM - FLOOD CONTROL AND SLOPE PROTECTION PROJECT (Revetment of Dike and Slope Protection) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 1000000 | Revised: |  | No. of Man-days:
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | DISASTER PREVENTION AND MITIGATION PROGRAM - FLOOD CONTROL AND SLOPE PROTECTION PROJECT (Revetment of Dike and Slope Protection) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | DISASTER PREVENTION AND MITIGATION PROGRAM - FLOOD CONTROL AND SLOPE PROTECTION PROJECT (Revetment of Dike and Slope Protection) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | DISASTER PREVENTION AND MITIGATION PROGRAM - FLOOD CONTROL AND SLOPE PROTECTION PROJECT (Revetment of Dike and Slope Protection) | [7 empty] | Date Allotment Released: |  | Date completed:
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | DISASTER PREVENTION AND MITIGATION PROGRAM - FLOOD CONTROL AND SLOPE PROTECTION PROJECT (Revetment of Dike and Slope Protection) | [7 empty] | Date Started:
Asuncion | Sonlon | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | DISASTER PREVENTION AND MITIGATION PROGRAM - FLOOD CONTROL AND SLOPE PROTECTION PROJECT (Improvement of Bridges and Cross Drainage) | Improvement of Saug-Sonlon-Bdry. Longanapan |  | 5% CALAMITY FUND CY 2020 | Road |  | km |  | Project Cost: | 1000000 | Target Completion Date: |  | Program: | 1000000 | Planned: |  | No. of Persons: |  | For preparation of POW and Plans
Asuncion | Sonlon | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | DISASTER PREVENTION AND MITIGATION PROGRAM - FLOOD CONTROL AND SLOPE PROTECTION PROJECT (Improvement of Bridges and Cross Drainage) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 1000000 | Revised: |  | No. of Man-days:
Asuncion | Sonlon | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | DISASTER PREVENTION AND MITIGATION PROGRAM - FLOOD CONTROL AND SLOPE PROTECTION PROJECT (Improvement of Bridges and Cross Drainage) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Asuncion | Sonlon | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | DISASTER PREVENTION AND MITIGATION PROGRAM - FLOOD CONTROL AND SLOPE PROTECTION PROJECT (Improvement of Bridges and Cross Drainage) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Asuncion | Sonlon | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | DISASTER PREVENTION AND MITIGATION PROGRAM - FLOOD CONTROL AND SLOPE PROTECTION PROJECT (Improvement of Bridges and Cross Drainage) | [7 empty] | Date Allotment Released: |  | Date completed:
Asuncion | Sonlon | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | DISASTER PREVENTION AND MITIGATION PROGRAM - FLOOD CONTROL AND SLOPE PROTECTION PROJECT (Improvement of Bridges and Cross Drainage) | [7 empty] | Date Started:
Kapalong | Gupitan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | Const. of 1 Classroom @ Mankay Integrated School, Gupitan, kapalong |  | SEF CY 2020 | Building |  | sq.m |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Opening of Shopping on June 25, 2020
Kapalong | Gupitan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Kapalong | Gupitan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Kapalong | Gupitan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Kapalong | Gupitan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Kapalong | Gupitan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Date Started:
Kapalong | Gupitan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | Const. of 1 Classroom @ Luno-luno E/S, Gupitan, kapalong |  | SEF CY 2020 | Building |  | sq.m |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Opening of Shopping on June 25, 2020
Kapalong | Gupitan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Kapalong | Gupitan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Kapalong | Gupitan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Kapalong | Gupitan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Kapalong | Gupitan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Date Started:
Kapalong | Gupitan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | Const. of 1 Classroom @ Kamunuan E/S, Gupitan, kapalong |  | SEF CY 2020 | Building |  | sq.m |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Opening of Shopping on June 25, 2020
Kapalong | Gupitan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Kapalong | Gupitan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Kapalong | Gupitan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Kapalong | Gupitan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Kapalong | Gupitan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Date Started:
Kapalong | Gupitan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | Const. of 1 Classroom @ Tawinian E/S, Gupitan, kapalong |  | SEF CY 2020 | Building |  | sq.m |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Opening of Shopping on June 25, 2020
Kapalong | Gupitan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Kapalong | Gupitan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Kapalong | Gupitan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Kapalong | Gupitan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Kapalong | Gupitan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Date Started:
Kapalong | Gupitan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | Const. of 1 Classroom @ Aninipot E/S, Gupitan, kapalong |  | SEF CY 2020 | Building |  | sq.m |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Opening of Shopping on June 25, 2020
Kapalong | Gupitan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Kapalong | Gupitan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Kapalong | Gupitan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Kapalong | Gupitan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Kapalong | Gupitan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Date Started:
Kapalong | Gupitan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | Const. of 1 Classroom @ Moling E/S, Gupitan, kapalong |  | SEF CY 2020 | Building |  | sq.m |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Opening of Shopping on June 25, 2020
Kapalong | Gupitan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Kapalong | Gupitan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Kapalong | Gupitan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Kapalong | Gupitan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Kapalong | Gupitan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Date Started:
Talaingod | Dagohoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | Const. of 1 Classroom @ Lomondong E/S, Dagohoy, Talaingod |  | SEF CY 2020 | Building |  | sq.m |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Opening of Shopping on June 25, 2020
Talaingod | Dagohoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Talaingod | Dagohoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Talaingod | Dagohoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Talaingod | Dagohoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Talaingod | Dagohoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Date Started:
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | Const. of 1 Classroom @ Malapanit E/S, Sto. Niño, Talaingod |  | SEF CY 2020 | Building |  | sq.m |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Opening of Shopping on June 25, 2020
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Date Started:
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | Const. of 1 Classroom @ Laputlakan E/S, Sto. Niño, Talaingod |  | SEF CY 2020 | Building |  | sq.m |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Opening of Shopping on June 25, 2020
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Date Started:
New Corella | Limbaan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | Const. of Day Care Center, Limbaan, New Corella |  | 20% DF CY 2020 | Building |  | sq.m |  | Project Cost: | 1000000 | Target Completion Date: |  | Program: | 1000000 | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
New Corella | Limbaan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 1000000 | Revised: |  | No. of Man-days:
New Corella | Limbaan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
New Corella | Limbaan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | Limbaan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
New Corella | Limbaan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Date Started:
Kapalong | Gabuyan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | Const. of Day Care Center, Gabuyan, kapalong |  | 20% DF CY 2020 | Building |  | sq.m |  | Project Cost: | 1000000 | Target Completion Date: |  | Program: | 1000000 | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
Kapalong | Gabuyan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 1000000 | Revised: |  | No. of Man-days:
Kapalong | Gabuyan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Kapalong | Gabuyan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Kapalong | Gabuyan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Kapalong | Gabuyan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Date Started:
Asuncion | Canatan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | Compl./Rep. Day Care Center,Canatan, Asuncion |  | 20% DF CY 2020 | Building |  | sq.m |  | Project Cost: | 300000 | Target Completion Date: |  | Program: | 300000 | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
Asuncion | Canatan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 300000 | Revised: |  | No. of Man-days:
Asuncion | Canatan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Asuncion | Canatan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Asuncion | Canatan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Asuncion | Canatan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Date Started:
Asuncion | Cambanogoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | Compl./Rep. Day Care Center,Cambanogoy, Asuncion |  | 20% DF CY 2020 | Building |  | sq.m |  | Project Cost: | 300000 | Target Completion Date: |  | Program: | 300000 | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
Asuncion | Cambanogoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 300000 | Revised: |  | No. of Man-days:
Asuncion | Cambanogoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Asuncion | Cambanogoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Asuncion | Cambanogoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Asuncion | Cambanogoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Date Started:
Kapalong | Gabuyan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | Compl./Rep. Day Care Center,Gabuyan, kapalong |  | 20% DF CY 2020 | Building |  | sq.m |  | Project Cost: | 600000 | Target Completion Date: |  | Program: | 600000 | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
Kapalong | Gabuyan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 600000 | Revised: |  | No. of Man-days:
Kapalong | Gabuyan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Kapalong | Gabuyan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Kapalong | Gabuyan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Kapalong | Gabuyan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Date Started:
New Corella | New Sambog | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | Compl./Rep. Day Care Center,New Sambog, New Corella |  | 20% DF CY 2020 | Building |  | sq.m |  | Project Cost: | 300000 | Target Completion Date: |  | Program: | 300000 | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
New Corella | New Sambog | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 300000 | Revised: |  | No. of Man-days:
New Corella | New Sambog | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
New Corella | New Sambog | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | New Sambog | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
New Corella | New Sambog | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Date Started:
New Corella | Cabidianan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | Compl./Rep. Day Care Center, Cabidianan, New Corella |  | 20% DF CY 2020 | Building |  | sq.m |  | Project Cost: | 300000 | Target Completion Date: |  | Program: | 300000 | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
New Corella | Cabidianan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 300000 | Revised: |  | No. of Man-days:
New Corella | Cabidianan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
New Corella | Cabidianan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | Cabidianan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
New Corella | Cabidianan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Date Started:
San Isidro | Igangon | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | Compl./Rep. Day Care Center, Igangon, San Isidro |  | 20% DF CY 2020 | Building |  | sq.m |  | Project Cost: | 300000 | Target Completion Date: |  | Program: | 300000 | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
San Isidro | Igangon | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 300000 | Revised: |  | No. of Man-days:
San Isidro | Igangon | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
San Isidro | Igangon | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
San Isidro | Igangon | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
San Isidro | Igangon | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Date Started:
Tagum City | Madaum | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | Compl./Rep. Day Care Center, Madaum, Tagum City |  | 20% DF CY 2020 | Building |  | sq.m |  | Project Cost: | 300000 | Target Completion Date: |  | Program: | 300000 | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
Tagum City | Madaum | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 300000 | Revised: |  | No. of Man-days:
Tagum City | Madaum | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Tagum City | Madaum | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Tagum City | Madaum | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Tagum City | Madaum | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Date Started:
Tagum City | Apokon | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | Compl./Rep. Day Care Center, Apokon, Tagum City |  | 20% DF CY 2020 | Building |  | sq.m |  | Project Cost: | 300000 | Target Completion Date: |  | Program: | 300000 | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
Tagum City | Apokon | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 300000 | Revised: |  | No. of Man-days:
Tagum City | Apokon | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Tagum City | Apokon | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Tagum City | Apokon | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Tagum City | Apokon | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Date Started:
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | Compl./Rep. Day Care Center, Sto. Niño, Talaingod |  | 20% DF CY 2020 | Building |  | sq.m |  | Project Cost: | 300000 | Target Completion Date: |  | Program: | 300000 | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 300000 | Revised: |  | No. of Man-days:
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Date Started:
New Corella | Poblacion | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | HEALTH CARE SERVICES PROGRAM (PEEDO) | Improvement/Rehab. Of Luntiang Paraiso, New Corella |  | 20% DF CY 2020 | Building |  | km |  | Project Cost: | 3000000 | Target Completion Date: |  | Program: | 3000000 | Planned: |  | No. of Persons: |  | For Purchase Request
New Corella | Poblacion | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | HEALTH CARE SERVICES PROGRAM (PEEDO) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 3000000 | Revised: |  | No. of Man-days:
New Corella | Poblacion | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | HEALTH CARE SERVICES PROGRAM (PEEDO) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
New Corella | Poblacion | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | HEALTH CARE SERVICES PROGRAM (PEEDO) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | Poblacion | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | HEALTH CARE SERVICES PROGRAM (PEEDO) | [7 empty] | Date Allotment Released: |  | Date completed:
New Corella | Poblacion | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | HEALTH CARE SERVICES PROGRAM (PEEDO) | [7 empty] | Date Started:
Tagum City | Mankilam | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | PSYDO YOUTH DEV'T. PROGRAM - TEEN TAMBAYAN PROJECT | Renovation of Teen Tambayan |  | 20% DF CY 2020 | Building |  | sq.m |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Date of procurement June 30, 2020
Tagum City | Mankilam | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | PSYDO YOUTH DEV'T. PROGRAM - TEEN TAMBAYAN PROJECT | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Tagum City | Mankilam | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | PSYDO YOUTH DEV'T. PROGRAM - TEEN TAMBAYAN PROJECT | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Tagum City | Mankilam | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | PSYDO YOUTH DEV'T. PROGRAM - TEEN TAMBAYAN PROJECT | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Tagum City | Mankilam | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | PSYDO YOUTH DEV'T. PROGRAM - TEEN TAMBAYAN PROJECT | [7 empty] | Date Allotment Released: |  | Date completed:
Tagum City | Mankilam | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | PSYDO YOUTH DEV'T. PROGRAM - TEEN TAMBAYAN PROJECT | [7 empty] | Date Started:
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2020-06-01 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SPECIAL TRUST FUND (PDRRMC) | Installation of 20 units Isolation Room, Sports Academy Dormitory, DNSTC |  | SPECIAL TRUST FUND | Isolation | 20 | sq.m | Admin | Project Cost: | 170000 | Target Completion Date: | 2020-07-15 23:46 | Program: | 170000 | Planned: | 100% | No. of Persons: |  | Completed as per physical accomplishment. Financial documents still on process.
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2020-06-01 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SPECIAL TRUST FUND (PDRRMC) | [7 empty] | Project Engineer: | Chua | Revised Completion Date: | 2020-07-15 23:46 | Allotment: | 170000 | Revised: |  | No. of Man-days:
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2020-06-01 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SPECIAL TRUST FUND (PDRRMC) | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: | 100%
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2020-06-01 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SPECIAL TRUST FUND (PDRRMC) | [7 empty] | Duration: | 45 | No. of days extended: |  |  |  | Slippage: | 0%
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2020-06-01 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SPECIAL TRUST FUND (PDRRMC) | [7 empty] | Date Allotment Released: | 2020-06-01 | Date completed: | 2020-07-15 23:46
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2020-06-01 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SPECIAL TRUST FUND (PDRRMC) | [7 empty] | Date Started: | 2020-06-01
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2020-06-01 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SPECIAL TRUST FUND (PDRRMC) | Installation of 100 units isolation room (2.0 x 3.0m), DAVNOR GYM |  | SPECIAL TRUST FUND | Isolation | 100 | sq.m | Admin | Project Cost: | 750000 | Target Completion Date: | 2020-07-15 23:46 | Program: | 750000 | Planned: | 100% | No. of Persons: |  | Completed as per physical accomplishment. Financial documents still on process.
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2020-06-01 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SPECIAL TRUST FUND (PDRRMC) | [7 empty] | Project Engineer: | Chua | Revised Completion Date: | 2020-07-15 23:46 | Allotment: | 750000 | Revised: |  | No. of Man-days:
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2020-06-01 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SPECIAL TRUST FUND (PDRRMC) | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: | 100%
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2020-06-01 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SPECIAL TRUST FUND (PDRRMC) | [7 empty] | Duration: | 45 | No. of days extended: |  |  |  | Slippage: | 0%
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2020-06-01 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SPECIAL TRUST FUND (PDRRMC) | [7 empty] | Date Allotment Released: | 2020-06-01 | Date completed: | 2020-07-15 23:46
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2020-06-01 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SPECIAL TRUST FUND (PDRRMC) | [7 empty] | Date Started: | 2020-06-01
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2020-06-01 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SPECIAL TRUST FUND (PDRRMC) | Installation of 40 units Isolation Room, Sports Academy Dormitory, DNSTC |  | SPECIAL TRUST FUND | Isolation | 40 | sq.m | Admin | Project Cost: | 320000 | Target Completion Date: | 2020-07-15 23:46 | Program: | 320000 | Planned: | 100% | No. of Persons: |  | Completed as per physical accomplishment. Financial documents still on process.
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2020-06-01 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SPECIAL TRUST FUND (PDRRMC) | [7 empty] | Project Engineer: | Chua | Revised Completion Date: | 2020-07-15 23:46 | Allotment: | 320000 | Revised: |  | No. of Man-days:
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2020-06-01 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SPECIAL TRUST FUND (PDRRMC) | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: | 100%
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2020-06-01 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SPECIAL TRUST FUND (PDRRMC) | [7 empty] | Duration: | 45 | No. of days extended: |  |  |  | Slippage: | 0%
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2020-06-01 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SPECIAL TRUST FUND (PDRRMC) | [7 empty] | Date Allotment Released: | 2020-05-28 | Date completed: | 2020-07-15
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2020-06-01 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SPECIAL TRUST FUND (PDRRMC) | [7 empty] | Date Started: | 2020-06-01
Talaingod | Palma Gil | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | PEACE AND ORDER PROGRAM | Proposed Road Opening of Nasilaban - Pongpong Road Section, Talaingod |  | SB # 1 CY 2020 | Road |  | km |  | Project Cost: | 5500000 | Target Completion Date: |  | Program: | 5500000 | Planned: |  | No. of Persons: |  | PO #2020062105 - M3C CONSTRUCTION & SUPPLY; PO #2020061966 - FL2 LUMBER & CONSTRUCTION SUPPLY; PO #2020062217 - Alpebel Builders and Supply Corporation, PO #DIOCESAN PRINTING PRESS
Talaingod | Palma Gil | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | PEACE AND ORDER PROGRAM | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 5500000 | Revised: |  | No. of Man-days:
Talaingod | Palma Gil | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | PEACE AND ORDER PROGRAM | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Talaingod | Palma Gil | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | PEACE AND ORDER PROGRAM | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Talaingod | Palma Gil | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | PEACE AND ORDER PROGRAM | [7 empty] | Date Allotment Released: |  | Date completed:
Talaingod | Palma Gil | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | PEACE AND ORDER PROGRAM | [7 empty] | Date Started:
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOV'T. BLDG. & FAC. DEV'T. PROJECT | Establishment of Multiplier Farm Phase 2, Brgy. Sto. Niño, Talaingod |  | SB # 1 CY 2020 | Building |  | sq.m |  | Project Cost: | 380000 | Target Completion Date: |  | Program: | 380000 | Planned: |  | No. of Persons: |  | For bidding on June 30, 2020; Re-bid July 28, 2020.
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOV'T. BLDG. & FAC. DEV'T. PROJECT | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 380000 | Revised: |  | No. of Man-days:
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOV'T. BLDG. & FAC. DEV'T. PROJECT | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOV'T. BLDG. & FAC. DEV'T. PROJECT | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOV'T. BLDG. & FAC. DEV'T. PROJECT | [7 empty] | Date Allotment Released: |  | Date completed:
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOV'T. BLDG. & FAC. DEV'T. PROJECT | [7 empty] | Date Started:
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOV'T. BLDG. & FAC. DEV'T. PROJECT | Establishment of Multiplier Farm (Poultry House), Phase 2, Brgy. Sto. Niño, Talaingod |  | SB # 1 CY 2020 | Building |  | sq.m |  | Project Cost: | 110000 | Target Completion Date: |  | Program: | 110000 | Planned: |  | No. of Persons: |  | For bidding on June 30, 2020; Re-bid July 28, 2020.
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOV'T. BLDG. & FAC. DEV'T. PROJECT | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 110000 | Revised: |  | No. of Man-days:
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOV'T. BLDG. & FAC. DEV'T. PROJECT | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOV'T. BLDG. & FAC. DEV'T. PROJECT | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOV'T. BLDG. & FAC. DEV'T. PROJECT | [7 empty] | Date Allotment Released: |  | Date completed:
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOV'T. BLDG. & FAC. DEV'T. PROJECT | [7 empty] | Date Started:
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOV'T. BLDG. & FAC. DEV'T. PROJECT | Poultry House and Training Center Phase 2, Talaingod |  | SB # 1 CY 2020 | Building |  | sq.m |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | For bidding on June 30, 2020; Re-bid July 28, 2020.
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOV'T. BLDG. & FAC. DEV'T. PROJECT | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOV'T. BLDG. & FAC. DEV'T. PROJECT | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOV'T. BLDG. & FAC. DEV'T. PROJECT | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOV'T. BLDG. & FAC. DEV'T. PROJECT | [7 empty] | Date Allotment Released: |  | Date completed:
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOV'T. BLDG. & FAC. DEV'T. PROJECT | [7 empty] | Date Started:
Kapalong | Maniki | 1st Eng'g. Dist. | On-going | 2020-05-11 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | BAYANIHAN GRANT TO PROVINCES | Improvement of Hospital facilities (Isolation/ICU), Kapalong Dist. Hospital |  | SB # 2 CY 2020 (BAYANIHAN GRANT) | Isolation |  | sq.m | Admin | Project Cost: | 6000000 | Target Completion Date: | 2021-01-10 23:59 | Program: | 6000000 | Planned: | 60.08% | No. of Persons: | 34 | On-going
Kapalong | Maniki | 1st Eng'g. Dist. | On-going | 2020-05-11 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | BAYANIHAN GRANT TO PROVINCES | [7 empty] | Project Engineer: | Pasiona/Aclaracion | Revised Completion Date: |  | Allotment: | 6000000 | Revised: |  | No. of Man-days: | 1054
Kapalong | Maniki | 1st Eng'g. Dist. | On-going | 2020-05-11 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | BAYANIHAN GRANT TO PROVINCES | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: | 60.08%
Kapalong | Maniki | 1st Eng'g. Dist. | On-going | 2020-05-11 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | BAYANIHAN GRANT TO PROVINCES | [7 empty] | Duration: | 245 | No. of days extended: |  |  |  | Slippage: | 0%
Kapalong | Maniki | 1st Eng'g. Dist. | On-going | 2020-05-11 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | BAYANIHAN GRANT TO PROVINCES | [7 empty] | Date Allotment Released: | 2020-05-07 | Date completed:
Kapalong | Maniki | 1st Eng'g. Dist. | On-going | 2020-05-11 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | BAYANIHAN GRANT TO PROVINCES | [7 empty] | Date Started: | 2020-05-11
Kapalong | Gabuyan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | CMGP | Road Improvement of Jct. Highway Gabuyan – Semong – Dagohoy Provincial Road |  | CMGP | Road |  | km |  | Project Cost: | 63458000 | Target Completion Date: |  | Program: | 63458000 | Planned: |  | No. of Persons: |  | For posting
Kapalong | Gabuyan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | CMGP | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 63458000 | Revised: |  | No. of Man-days:
Kapalong | Gabuyan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | CMGP | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Kapalong | Gabuyan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | CMGP | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Kapalong | Gabuyan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | CMGP | [7 empty] | Date Allotment Released: |  | Date completed:
Kapalong | Gabuyan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | CMGP | [7 empty] | Date Started:
Talaingod | Palma Gil | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | NHA | Const. of 100 Housing Units at Balai Lupowanan at Sitio Nasilaban, Palma Gil, Talaingod |  | Natinal Housing Project CY 2020 | Building | 100 | units | Admin | Project Cost: | 20000000 | Target Completion Date: |  | Program: | 20000000 | Planned: |  | No. of Persons: |  | For bidding on July 3, 2020
Talaingod | Palma Gil | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | NHA | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 20000000 | Revised: |  | No. of Man-days:
Talaingod | Palma Gil | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | NHA | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Talaingod | Palma Gil | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | NHA | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Talaingod | Palma Gil | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | NHA | [7 empty] | Date Allotment Released: |  | Date completed:
Talaingod | Palma Gil | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | NHA | [7 empty] | Date Started:
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | NHA | Const. of 100 Housing Units at Balai Pig Immimanan at Sitio Mesulong, Sto. Niño, Talaingod |  | Natinal Housing Project CY 2020 | Building | 100 | units | Admin | Project Cost: | 20000000 | Target Completion Date: |  | Program: | 20000000 | Planned: |  | No. of Persons: |  | For bidding on July 3, 2020
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | NHA | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 20000000 | Revised: |  | No. of Man-days:
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | NHA | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | NHA | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | NHA | [7 empty] | Date Allotment Released: |  | Date completed:
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | NHA | [7 empty] | Date Started:
Panabo City | San Roque | 2nd Eng'g. Dist. | Completed |  | 2020-06-30 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) LS - P9,000,000.00 | Const. of MP Bldg. w/ Electrical installation, San Roque, Panabo City |  | 20% DF CY 2017 (STIMULUS) | Building |  | ln.m | MLGU | Project Cost: | 500000 | Target Completion Date: | 6/10/2019 | Program: | 500000 | Planned: | 100% | No. of Persons: |  | Completed as per physical accomplishment. Financial documents still on process.
Panabo City | San Roque | 2nd Eng'g. Dist. | Completed |  | 2020-06-30 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) LS - P9,000,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Panabo City | San Roque | 2nd Eng'g. Dist. | Completed |  | 2020-06-30 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) LS - P9,000,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: | 100%
Panabo City | San Roque | 2nd Eng'g. Dist. | Completed |  | 2020-06-30 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) LS - P9,000,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Panabo City | San Roque | 2nd Eng'g. Dist. | Completed |  | 2020-06-30 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) LS - P9,000,000.00 | [7 empty] | Date Allotment Released: | 2018-01-31 | Date completed: | 2019-06-10
Panabo City | San Roque | 2nd Eng'g. Dist. | Completed |  | 2020-06-30 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) LS - P9,000,000.00 | [7 empty] | Date Started:
B.E. Dujali | Magupising | 2nd Eng'g. Dist. | Completed | 2019-12-02 | 2020-05-29 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | Rehab.of Dujali - Balisong - Magupising Provincial Road |  | 20% DF CY 2019 | Road Rehabilitation | 19.16 | km | MBA | Project Cost: | 1280000 | Target Completion Date: | 2020-01-15 23:59 | Program: | 1280000 | Planned: | 100% | No. of Persons: | 12 | Completed as per physical accomplishment. Financial documents still on process.
B.E. Dujali | Magupising | 2nd Eng'g. Dist. | Completed | 2019-12-02 | 2020-05-29 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Project Engineer: | Mellomida | Revised Completion Date: | 2020-05-31 23:59 | Allotment: | 1280000 | Revised: |  | No. of Man-days: | 900
B.E. Dujali | Magupising | 2nd Eng'g. Dist. | Completed | 2019-12-02 | 2020-05-29 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Implementor: | PEO | No. of days suspended: | 137 | Disbursement: | 14331.6 | Actual: | 100%
B.E. Dujali | Magupising | 2nd Eng'g. Dist. | Completed | 2019-12-02 | 2020-05-29 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Duration: | 45 | No. of days extended: |  |  |  | Slippage: | 0%
B.E. Dujali | Magupising | 2nd Eng'g. Dist. | Completed | 2019-12-02 | 2020-05-29 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Date Allotment Released: |  | Date completed: | 2020-05-29
B.E. Dujali | Magupising | 2nd Eng'g. Dist. | Completed | 2019-12-02 | 2020-05-29 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Date Started: | 2019-12-02
Sto. Tomas | Tibal-og | 2nd Eng'g. Dist. | Completed | 2019-02-22 | 2020-06-30 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPPAP-PAMANA | Construction of Tribal Hall, Sto. Tomas |  | OPPAP-PAMANA CY 2017 | Building |  | sq.m | Admin | Project Cost: | 500000 | Target Completion Date: | 2019-07-31 | Program: | 500000 | Planned: | 100% | No. of Persons: | 7 | Resume last June 22, 2020; Completed as per physical accomplishment. Financial documents still on process.
Sto. Tomas | Tibal-og | 2nd Eng'g. Dist. | Completed | 2019-02-22 | 2020-06-30 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPPAP-PAMANA | [7 empty] | Project Engineer: | Roque | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days: | 110
Sto. Tomas | Tibal-og | 2nd Eng'g. Dist. | Completed | 2019-02-22 | 2020-06-30 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPPAP-PAMANA | [7 empty] | Implementor: | Admin | No. of days suspended: |  | Disbursement: |  | Actual: | 100%
Sto. Tomas | Tibal-og | 2nd Eng'g. Dist. | Completed | 2019-02-22 | 2020-06-30 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPPAP-PAMANA | [7 empty] | Duration: | 70 | No. of days extended: |  |  |  | Slippage: | 0%
Sto. Tomas | Tibal-og | 2nd Eng'g. Dist. | Completed | 2019-02-22 | 2020-06-30 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPPAP-PAMANA | [7 empty] | Date Allotment Released: | CY 2018 | Date completed: | 2020-06-30
Sto. Tomas | Tibal-og | 2nd Eng'g. Dist. | Completed | 2019-02-22 | 2020-06-30 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPPAP-PAMANA | [7 empty] | Date Started: | 2019-05-22
Panabo City | Lasang | 2nd Eng'g. Dist. | On-going | 2015-05-30 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOV'T. BLDG. & FAC. DEV'T. PROJECT | Proposed Davao del Norte Tourism Billboard, Brgy. Lasang, Panabo City |  | SB # 1 CY 2015 | Billboard |  | sq.m | Admin | Project Cost: | 756400 | Target Completion Date: | 2015-05-10 23:59 | Program: | 756400 | Planned: | 11.78% | No. of Persons: |  | delay due to change location & design code. For AIP amendment from Panabo City to Gov't Center, Mankilam
Panabo City | Lasang | 2nd Eng'g. Dist. | On-going | 2015-05-30 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOV'T. BLDG. & FAC. DEV'T. PROJECT | [7 empty] | Project Engineer: | Porras | Revised Completion Date: |  | Allotment: | 756400 | Revised: |  | No. of Man-days:
Panabo City | Lasang | 2nd Eng'g. Dist. | On-going | 2015-05-30 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOV'T. BLDG. & FAC. DEV'T. PROJECT | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: | 332087.3 | Actual: | 11.78%
Panabo City | Lasang | 2nd Eng'g. Dist. | On-going | 2015-05-30 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOV'T. BLDG. & FAC. DEV'T. PROJECT | [7 empty] | Duration: | 42 | No. of days extended: |  |  |  | Slippage: | 0%
Panabo City | Lasang | 2nd Eng'g. Dist. | On-going | 2015-05-30 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOV'T. BLDG. & FAC. DEV'T. PROJECT | [7 empty] | Date Allotment Released: | 2015-05-06 | Date completed:
Panabo City | Lasang | 2nd Eng'g. Dist. | On-going | 2015-05-30 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOV'T. BLDG. & FAC. DEV'T. PROJECT | [7 empty] | Date Started: | 2015-03-30
Sto. Tomas | Esperanza | 2nd Eng'g. Dist. | On-going | 2017-03-22 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PRDP | Rehab. of Esperanza-Pob. Sto. Tomas, FMR, DDN |  | PRDP CY 2014 | Road Concreting | 12.774 | km | Contract | Project Cost: | 117410426.3 | Target Completion Date: | 2019-07-22 23:59 | Program: | 117410426.3 | Planned: | 100% | No. of Persons: | 20 | On-going (Waiting for approve Variation order for billing)
Sto. Tomas | Esperanza | 2nd Eng'g. Dist. | On-going | 2017-03-22 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PRDP | [7 empty] | Project Engineer: | Palero | Revised Completion Date: | 2020-07-31 23:59 | Allotment: | 117410426.3 | Revised: | 95.53% | No. of Man-days: | 600
Sto. Tomas | Esperanza | 2nd Eng'g. Dist. | On-going | 2017-03-22 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PRDP | [7 empty] | Implementor: | ALZAM | No. of days suspended: |  | Disbursement: |  | Actual: | 87.82%
Sto. Tomas | Esperanza | 2nd Eng'g. Dist. | On-going | 2017-03-22 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PRDP | [7 empty] | Duration: | 853 | No. of days extended: | 375 |  |  | Slippage: | -7.705%
Sto. Tomas | Esperanza | 2nd Eng'g. Dist. | On-going | 2017-03-22 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PRDP | [7 empty] | Date Allotment Released: | CY 2014 | Date completed:
Sto. Tomas | Esperanza | 2nd Eng'g. Dist. | On-going | 2017-03-22 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PRDP | [7 empty] | Date Started: | 2017-03-22
Sto. Tomas | Poblacion | 2nd Eng'g. Dist. | For Implementation | 2018-01-29 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PRDP | Improvement of Sto. Tomas Production Center with Common Facility, Sto. Tomas |  | PRDP CY 2016 | Building | 1901 | sq.m | Contract | Project Cost: | 9825000 | Target Completion Date: | 2018-12-24 23:59 | Program: | 9825000 | Planned: |  | No. of Persons: |  | Suspended due to land unsettlement. Revised POW and DED On-going
Sto. Tomas | Poblacion | 2nd Eng'g. Dist. | For Implementation | 2018-01-29 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PRDP | [7 empty] | Project Engineer: | Azotes | Revised Completion Date: |  | Allotment: | 9825000 | Revised: |  | No. of Man-days:
Sto. Tomas | Poblacion | 2nd Eng'g. Dist. | For Implementation | 2018-01-29 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PRDP | [7 empty] | Implementor: | Manantan | No. of days suspended: |  | Disbursement: |  | Actual:
Sto. Tomas | Poblacion | 2nd Eng'g. Dist. | For Implementation | 2018-01-29 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PRDP | [7 empty] | Duration: | 330 | No. of days extended: |  |  |  | Slippage: | 0%
Sto. Tomas | Poblacion | 2nd Eng'g. Dist. | For Implementation | 2018-01-29 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PRDP | [7 empty] | Date Allotment Released: | CY 2014 | Date completed:
Sto. Tomas | Poblacion | 2nd Eng'g. Dist. | For Implementation | 2018-01-29 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PRDP | [7 empty] | Date Started: | 2018-01-29
IGCS | Kinawitnon | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PRDP | Inst. of transformer and accessories, Brgy. Kinawitnon |  | PRDP CY 2016 | Electrification |  |  | Admin | Project Cost: | 150000 | Target Completion Date: |  | Program: | 150000 | Planned: |  | No. of Persons: |  | Purchase Order # 2019103228 - Transformer; Purchase Order # 2019102931 - Billboard; Purchase Order # 2019103227 - Lumber
IGCS | Kinawitnon | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PRDP | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 150000 | Revised: |  | No. of Man-days:
IGCS | Kinawitnon | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PRDP | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
IGCS | Kinawitnon | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PRDP | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
IGCS | Kinawitnon | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PRDP | [7 empty] | Date Allotment Released: | 2018-07-31 | Date completed:
IGCS | Kinawitnon | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PRDP | [7 empty] | Date Started:
Samal | Sta. Cruz | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | RURAL ELECTRIFICATION PROJECT | Rural Electrification at brgy. Sta. Cruz, talikud, Samal |  | 20% DF CY 2016 | Electrification |  |  | Contract | Project Cost: | 2000000 | Target Completion Date: |  | Program: | 2000000 | Planned: |  | No. of Persons: |  | Delay due to slow action of Daneco for staking. c/o Engr. Kim
Samal | Sta. Cruz | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | RURAL ELECTRIFICATION PROJECT | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 2000000 | Revised: |  | No. of Man-days:
Samal | Sta. Cruz | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | RURAL ELECTRIFICATION PROJECT | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Samal | Sta. Cruz | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | RURAL ELECTRIFICATION PROJECT | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Samal | Sta. Cruz | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | RURAL ELECTRIFICATION PROJECT | [7 empty] | Date Allotment Released: |  | Date completed:
Samal | Sta. Cruz | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | RURAL ELECTRIFICATION PROJECT | [7 empty] | Date Started:
BABAK | Kinawitnon | 2nd Eng'g. Dist. | On-going | 2018-03-12 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) LS - P9,000,000.00 | Construction of Provincial Training Center , Compound Fence, Kinawitnon, Babak District, IGCS |  | 20% DF CY 2016 | Fence |  | sq.m | Admin | Project Cost: | 940000 | Target Completion Date: | 2018-06-19 23:59 | Program: | 940000 | Planned: | 68% | No. of Persons: |  | Temporarily suspended 4/23/18 due to undemolished structures of illegal settlers
BABAK | Kinawitnon | 2nd Eng'g. Dist. | On-going | 2018-03-12 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) LS - P9,000,000.00 | [7 empty] | Project Engineer: | Pacquiao | Revised Completion Date: |  | Allotment: | 940000 | Revised: |  | No. of Man-days:
BABAK | Kinawitnon | 2nd Eng'g. Dist. | On-going | 2018-03-12 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) LS - P9,000,000.00 | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: | 933418.8 | Actual: | 75%
BABAK | Kinawitnon | 2nd Eng'g. Dist. | On-going | 2018-03-12 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) LS - P9,000,000.00 | [7 empty] | Duration: | 100 | No. of days extended: |  |  |  | Slippage: | 7%
BABAK | Kinawitnon | 2nd Eng'g. Dist. | On-going | 2018-03-12 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) LS - P9,000,000.00 | [7 empty] | Date Allotment Released: | 2017-09-19 | Date completed:
BABAK | Kinawitnon | 2nd Eng'g. Dist. | On-going | 2018-03-12 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) LS - P9,000,000.00 | [7 empty] | Date Started: | 2018-03-12
Panabo City | Consolacion | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) LS - P9,000,000.00 | Const of Market Stall/Building, Consolacion, Panabo City |  | 20% DF CY 2017 (STIMULUS) | Building |  |  | MLGU | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Issued warning for Termination of the Contract
Panabo City | Consolacion | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) LS - P9,000,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Panabo City | Consolacion | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) LS - P9,000,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Panabo City | Consolacion | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) LS - P9,000,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Panabo City | Consolacion | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) LS - P9,000,000.00 | [7 empty] | Date Allotment Released: | 2017-12-28 | Date completed:
Panabo City | Consolacion | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) LS - P9,000,000.00 | [7 empty] | Date Started:
Panabo City | Upper Licanan | 2nd Eng'g. Dist. | On-going | 2017-12-28 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) LS - P9,000,000.00 | Rehab. Of Multi-Purpose Hall (Covered Court), Upper Licanan, Panabo City |  | 20% DF CY 2017 (STIMULUS) | Building |  |  | MLGU | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Fund transfer to LGU- 3/28/2019 with check no.2574927 and OR no. 0166516 - Delivery of Materials on process
Panabo City | Upper Licanan | 2nd Eng'g. Dist. | On-going | 2017-12-28 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) LS - P9,000,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Panabo City | Upper Licanan | 2nd Eng'g. Dist. | On-going | 2017-12-28 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) LS - P9,000,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Panabo City | Upper Licanan | 2nd Eng'g. Dist. | On-going | 2017-12-28 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) LS - P9,000,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Panabo City | Upper Licanan | 2nd Eng'g. Dist. | On-going | 2017-12-28 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) LS - P9,000,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Panabo City | Upper Licanan | 2nd Eng'g. Dist. | On-going | 2017-12-28 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) LS - P9,000,000.00 | [7 empty] | Date Started: | 2017-12-28
Panabo City | Kauswagan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) LS - P9,000,000.00 | Impv't. of Multi-Purpose Gym, Kauswagan, Panabo City |  | 20% DF CY 2017 (STIMULUS) | GYM |  |  | MLGU | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Fund transfer to LGU- 3/28/2019 with check no.2574942 and OR no. 0166515 - procurement on process for bidding 8/5/2019
Panabo City | Kauswagan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) LS - P9,000,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Panabo City | Kauswagan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) LS - P9,000,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Panabo City | Kauswagan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) LS - P9,000,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Panabo City | Kauswagan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) LS - P9,000,000.00 | [7 empty] | Date Allotment Released: | 2019-02-04 | Date completed:
Panabo City | Kauswagan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) LS - P9,000,000.00 | [7 empty] | Date Started:
Panabo City | Cacao | 2nd Eng'g. Dist. | On-going | 2018-12-14 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) LS - P9,000,000.00 | Const. of Multi-Purpose Bldg.,Cacao, Panabo City |  | 20% DF CY 2017 (STIMULUS) | Building |  | sq.m | MLGU | Project Cost: | 300000 | Target Completion Date: |  | Program: | 300000 | Planned: |  | No. of Persons: |  | Issued warning for termination of the contract
Panabo City | Cacao | 2nd Eng'g. Dist. | On-going | 2018-12-14 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) LS - P9,000,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 300000 | Revised: |  | No. of Man-days:
Panabo City | Cacao | 2nd Eng'g. Dist. | On-going | 2018-12-14 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) LS - P9,000,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Panabo City | Cacao | 2nd Eng'g. Dist. | On-going | 2018-12-14 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) LS - P9,000,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Panabo City | Cacao | 2nd Eng'g. Dist. | On-going | 2018-12-14 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) LS - P9,000,000.00 | [7 empty] | Date Allotment Released: | 2017-12-19 | Date completed:
Panabo City | Cacao | 2nd Eng'g. Dist. | On-going | 2018-12-14 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) LS - P9,000,000.00 | [7 empty] | Date Started: | 2018-12-14
Panabo City | A.O. Floreindo | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) LS - P9,000,000.00 | Const. of Multi-Purpose Bldg. @ A.O. Floriendo National Highschool, Panabo City |  | 20% DF CY 2017 (STIMULUS) | Building |  |  | MLGU | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Fund transfer to LGU- 3/28/2019 with check no. 2574939 and OR no. 0166518 - Materials Delivered. Construction on-going
Panabo City | A.O. Floreindo | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) LS - P9,000,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Panabo City | A.O. Floreindo | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) LS - P9,000,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Panabo City | A.O. Floreindo | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) LS - P9,000,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Panabo City | A.O. Floreindo | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) LS - P9,000,000.00 | [7 empty] | Date Allotment Released: | 2017-12-19 | Date completed:
Panabo City | A.O. Floreindo | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) LS - P9,000,000.00 | [7 empty] | Date Started:
Panabo City | Kimamon | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Drainage | Const. of Concrete Drainage Canal, Kimamon, Panabo City |  | 20% DF CY 2017 (STIMULUS) | Drainage |  |  | MLGU | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | For Implementation
Panabo City | Kimamon | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Drainage | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Panabo City | Kimamon | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Drainage | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Panabo City | Kimamon | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Drainage | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Panabo City | Kimamon | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Drainage | [7 empty] | Date Allotment Released: | 2017-12-19 | Date completed:
Panabo City | Kimamon | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Drainage | [7 empty] | Date Started:
IGCS | Anonang | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | RURAL ELECTRIFICATION PROJECT | Impv't. of Brgy. Street Electrification at Brgy. Anonang, IGCS |  | 20% DF CY 2017 (STIMULUS) | Electrification |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Verified at PBO 7/18/2019 that fund is not available. Proposed priority project for 2020.
IGCS | Anonang | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | RURAL ELECTRIFICATION PROJECT | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
IGCS | Anonang | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | RURAL ELECTRIFICATION PROJECT | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual:
IGCS | Anonang | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | RURAL ELECTRIFICATION PROJECT | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
IGCS | Anonang | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | RURAL ELECTRIFICATION PROJECT | [7 empty] | Date Allotment Released: | 2017-11-28 | Date completed:
IGCS | Anonang | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | RURAL ELECTRIFICATION PROJECT | [7 empty] | Date Started:
Panabo City | Datu Abdul | 2nd Eng'g. Dist. | On-going | 2019-11-21 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPPAP-PAMANA | Const. of Trading Post, Storage Building with (1) unit Hauling Truck, Prk. Ramihan Datu Abdul, Panabo City |  | OPPAP-PAMANA CY 2017 | Building |  | sq.m | Contract | Project Cost: | 3975000 | Target Completion Date: | 2020-04-05 23:59 | Program: | 3975000 | Planned: | 100% | No. of Persons: | 10 | On-going
Panabo City | Datu Abdul | 2nd Eng'g. Dist. | On-going | 2019-11-21 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPPAP-PAMANA | [7 empty] | Project Engineer: | Azotes | Revised Completion Date: | 2020-05-16 23:59 | Allotment: | 3975000 | Revised: | 40.36% | No. of Man-days: | 260
Panabo City | Datu Abdul | 2nd Eng'g. Dist. | On-going | 2019-11-21 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPPAP-PAMANA | [7 empty] | Implementor: | Ultra Core | No. of days suspended: | 41 | Disbursement: |  | Actual: | 40.36%
Panabo City | Datu Abdul | 2nd Eng'g. Dist. | On-going | 2019-11-21 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPPAP-PAMANA | [7 empty] | Duration: | 137 | No. of days extended: |  |  |  | Slippage: | 0%
Panabo City | Datu Abdul | 2nd Eng'g. Dist. | On-going | 2019-11-21 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPPAP-PAMANA | [7 empty] | Date Allotment Released: | CY 2017 | Date completed:
Panabo City | Datu Abdul | 2nd Eng'g. Dist. | On-going | 2019-11-21 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPPAP-PAMANA | [7 empty] | Date Started: | 2019-11-21
Samal | Kinawitnon | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPPAP-PAMANA | Trading Post, Storage and Hauling Truck Libuak, Island Garden City of Samal (IGACOS) |  | OPPAP-PAMANA CY 2017 | Building |  |  |  | Project Cost: | 4000000 | Target Completion Date: |  | Program: | 4000000 | Planned: |  | No. of Persons: |  | For bidding
Samal | Kinawitnon | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPPAP-PAMANA | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 4000000 | Revised: |  | No. of Man-days:
Samal | Kinawitnon | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPPAP-PAMANA | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Samal | Kinawitnon | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPPAP-PAMANA | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Samal | Kinawitnon | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPPAP-PAMANA | [7 empty] | Date Allotment Released: | CY 2018 | Date completed:
Samal | Kinawitnon | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPPAP-PAMANA | [7 empty] | Date Started:
IGCS | Tambo | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPPAP-PAMANA | Agricultural Productivity Support Project-Fishing Equipment, Tambo, IGACOS |  | OPPAP-PAMANA CY 2017 |  |  |  |  | Project Cost: | 1500000 | Target Completion Date: |  | Program: | 1500000 | Planned: |  | No. of Persons: |  | For bidding
IGCS | Tambo | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPPAP-PAMANA | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 1500000 | Revised: |  | No. of Man-days:
IGCS | Tambo | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPPAP-PAMANA | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
IGCS | Tambo | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPPAP-PAMANA | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
IGCS | Tambo | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPPAP-PAMANA | [7 empty] | Date Allotment Released: |  | Date completed:
IGCS | Tambo | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPPAP-PAMANA | [7 empty] | Date Started:
Carmen | Asuncion | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Construction of Water System Projects in Component LGUs LS - 9,750,000.00 | Rehab./Impv't. of San Vicente Water System, Asuncion |  | 20% DF CY 2018 | Water System |  |  | Admin | Project Cost: | 1125000 | Target Completion Date: |  | Program: | 1125000 | Planned: |  | No. of Persons: |  | Abstract # 0220190484
Carmen | Asuncion | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Construction of Water System Projects in Component LGUs LS - 9,750,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 1125000 | Revised: |  | No. of Man-days:
Carmen | Asuncion | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Construction of Water System Projects in Component LGUs LS - 9,750,000.00 | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual:
Carmen | Asuncion | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Construction of Water System Projects in Component LGUs LS - 9,750,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Carmen | Asuncion | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Construction of Water System Projects in Component LGUs LS - 9,750,000.00 | [7 empty] | Date Allotment Released: | 2018-10-26 | Date completed:
Carmen | Asuncion | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Construction of Water System Projects in Component LGUs LS - 9,750,000.00 | [7 empty] | Date Started:
Panabo City | Malativas | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Construction of Water System Projects in Component LGUs LS - 9,750,000.00 | Water System at brgy. Malativas, Panabo City |  | 20% DF CY 2018 | Water System |  |  | Admin | Project Cost: | 1250000 | Target Completion Date: |  | Program: | 1250000 | Planned: |  | No. of Persons: |  | For preparation of POW & Plan c/o PDPM - POSSIBLE TRANSFER OF SITE SUBJECT FOR TRANSFER OF LOCATION . NO DEED OF DONATION
Panabo City | Malativas | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Construction of Water System Projects in Component LGUs LS - 9,750,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 1250000 | Revised: |  | No. of Man-days:
Panabo City | Malativas | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Construction of Water System Projects in Component LGUs LS - 9,750,000.00 | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual:
Panabo City | Malativas | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Construction of Water System Projects in Component LGUs LS - 9,750,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Panabo City | Malativas | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Construction of Water System Projects in Component LGUs LS - 9,750,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Panabo City | Malativas | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Construction of Water System Projects in Component LGUs LS - 9,750,000.00 | [7 empty] | Date Started:
Panabo City | Tibungol | 2nd Eng'g. Dist. | On-going | 2020-01-20 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Construction of Water System Projects in Component LGUs LS - 9,750,000.00 | Const. of Potable Water System at Brgy. Tibungol, Panabo City |  | 20% DF CY 2018 | Water System |  | ln.m | Admin | Project Cost: | 1250000 | Target Completion Date: | 2020-04-15 23:59 | Program: | 1250000 | Planned: | 2.13% | No. of Persons: | 3 | Suspended dated February 19, 2020 undelivered hardware materials (Supplier refused to deliver. Letter already submitted to BAC.)
Panabo City | Tibungol | 2nd Eng'g. Dist. | On-going | 2020-01-20 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Construction of Water System Projects in Component LGUs LS - 9,750,000.00 | [7 empty] | Project Engineer: | Andoy | Revised Completion Date: |  | Allotment: | 1250000 | Revised: |  | No. of Man-days: | 15
Panabo City | Tibungol | 2nd Eng'g. Dist. | On-going | 2020-01-20 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Construction of Water System Projects in Component LGUs LS - 9,750,000.00 | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: | 0.76%
Panabo City | Tibungol | 2nd Eng'g. Dist. | On-going | 2020-01-20 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Construction of Water System Projects in Component LGUs LS - 9,750,000.00 | [7 empty] | Duration: | 87 | No. of days extended: |  |  |  | Slippage: | -1.37%
Panabo City | Tibungol | 2nd Eng'g. Dist. | On-going | 2020-01-20 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Construction of Water System Projects in Component LGUs LS - 9,750,000.00 | [7 empty] | Date Allotment Released: | 2018-11-21 | Date completed:
Panabo City | Tibungol | 2nd Eng'g. Dist. | On-going | 2020-01-20 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Construction of Water System Projects in Component LGUs LS - 9,750,000.00 | [7 empty] | Date Started: | 2020-01-20
Samal, Kaputian | San Remegio | 2nd Eng'g. Dist. | On-going | 2019-07-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Construction of Water System Projects in Component LGUs LS - 9,750,000.00 | Potable Water System at Brgy. San Remegio Kaputian (Level II WS), Samal |  | 20% DF CY 2018 | Water System |  |  | Admin | Project Cost: | 3625000 | Target Completion Date: | 2020-02-01 | Program: | 3625000 | Planned: | 100% | No. of Persons: | 4 | On-going/ Resumption 5/4/2020
Samal, Kaputian | San Remegio | 2nd Eng'g. Dist. | On-going | 2019-07-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Construction of Water System Projects in Component LGUs LS - 9,750,000.00 | [7 empty] | Project Engineer: | Kabigue | Revised Completion Date: | 2020-04-30 | Allotment: | 3625000 | Revised: | 72.04% | No. of Man-days: | 88
Samal, Kaputian | San Remegio | 2nd Eng'g. Dist. | On-going | 2019-07-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Construction of Water System Projects in Component LGUs LS - 9,750,000.00 | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: | 2702800 | Actual: | 74.56%
Samal, Kaputian | San Remegio | 2nd Eng'g. Dist. | On-going | 2019-07-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Construction of Water System Projects in Component LGUs LS - 9,750,000.00 | [7 empty] | Duration: | 200 | No. of days extended: | 89 |  |  | Slippage: | 2.52%
Samal, Kaputian | San Remegio | 2nd Eng'g. Dist. | On-going | 2019-07-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Construction of Water System Projects in Component LGUs LS - 9,750,000.00 | [7 empty] | Date Allotment Released: | 2018-10-25 | Date completed:
Samal, Kaputian | San Remegio | 2nd Eng'g. Dist. | On-going | 2019-07-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Construction of Water System Projects in Component LGUs LS - 9,750,000.00 | [7 empty] | Date Started: | 2019-07-16
Carmen | San Isidro | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | Completion of Evacuation Center Building, San Isidro, Carmen |  | GENERAL FUND PROPER CY 2018 (STIMULUS) | Building |  | sq.m | Contract | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | On-going
Carmen | San Isidro | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | [7 empty] | Project Engineer: | Estorco | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Carmen | San Isidro | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | [7 empty] | Implementor: | RLHV | No. of days suspended: |  | Disbursement: |  | Actual:
Carmen | San Isidro | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | [7 empty] | Duration: | 60 | No. of days extended: |  |  |  | Slippage: | 0%
Carmen | San Isidro | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | [7 empty] | Date Allotment Released: |  | Date completed:
Carmen | San Isidro | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | [7 empty] | Date Started:
Panabo City | Nanyo | 2nd Eng'g. Dist. | On-going | 2020-04-07 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | Const. of Perimeter Fence of Day Care Center 1, Nanyo, Panabo City |  | GENERAL FUND PROPER CY 2018 (STIMULUS) | Building |  | sq.m | Contract | Project Cost: | 500000 | Target Completion Date: | 2020-06-06 | Program: | 500000 | Planned: | 5% | No. of Persons: |  | (RLHV Design & Build) Winning Bidder
Panabo City | Nanyo | 2nd Eng'g. Dist. | On-going | 2020-04-07 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | [7 empty] | Project Engineer: | Estorco | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Panabo City | Nanyo | 2nd Eng'g. Dist. | On-going | 2020-04-07 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | [7 empty] | Implementor: | RLHV | No. of days suspended: |  | Disbursement: |  | Actual: | 5%
Panabo City | Nanyo | 2nd Eng'g. Dist. | On-going | 2020-04-07 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | [7 empty] | Duration: | 60 | No. of days extended: |  |  |  | Slippage: | 0%
Panabo City | Nanyo | 2nd Eng'g. Dist. | On-going | 2020-04-07 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | [7 empty] | Date Allotment Released: |  | Date completed:
Panabo City | Nanyo | 2nd Eng'g. Dist. | On-going | 2020-04-07 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | [7 empty] | Date Started: | 2020-04-07
Panabo City | Malativas | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | Impv't. of Brgy. Road Covered Court, Malativas, Panabo City |  | GENERAL FUND PROPER CY 2018 (STIMULUS) | Court |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Procurement on process
Panabo City | Malativas | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Panabo City | Malativas | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Panabo City | Malativas | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Panabo City | Malativas | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | [7 empty] | Date Allotment Released: |  | Date completed:
Panabo City | Malativas | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | [7 empty] | Date Started:
Panabo City | Maduao | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | Rehab. Of Multi-Purpose Gym & Facililies Maduao, Panabo City |  | GENERAL FUND PROPER CY 2018 (STIMULUS) | Gym |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Post qualification on process
Panabo City | Maduao | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Panabo City | Maduao | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Panabo City | Maduao | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Panabo City | Maduao | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | [7 empty] | Date Allotment Released: |  | Date completed:
Panabo City | Maduao | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | [7 empty] | Date Started:
Panabo City | Sto. Niño | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | Const. of Multi-Purpose Bldg. Sto. Nino, Panabo City |  | GENERAL FUND PROPER CY 2018 (STIMULUS) | Court |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | PR # 20032818
Panabo City | Sto. Niño | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Panabo City | Sto. Niño | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Panabo City | Sto. Niño | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Panabo City | Sto. Niño | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | [7 empty] | Date Allotment Released: |  | Date completed:
Panabo City | Sto. Niño | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | [7 empty] | Date Started:
Panabo City | Dapco | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | Completion of Canopy at DAPCO Covered Court, Dapco, Panabo City |  | GENERAL FUND PROPER CY 2018 (STIMULUS) | Court |  |  | Contract | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | (RLHV Design & Build) Winning Bidder
Panabo City | Dapco | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | [7 empty] | Project Engineer: | RLHV | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Panabo City | Dapco | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Panabo City | Dapco | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Panabo City | Dapco | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | [7 empty] | Date Allotment Released: |  | Date completed:
Panabo City | Dapco | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | [7 empty] | Date Started:
Panabo City | Nanyo | 2nd Eng'g. Dist. | On-going | 2020-04-07 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | Perimeter Fence of Day Care Center I & II, Nanyo, Panabo City/ Construction of Perimeter Fence) |  | GENERAL FUND PROPER CY 2018 (STIMULUS) | Building |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | For implementation (RLHV Design & Build) Winning Bidder
Panabo City | Nanyo | 2nd Eng'g. Dist. | On-going | 2020-04-07 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Panabo City | Nanyo | 2nd Eng'g. Dist. | On-going | 2020-04-07 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Panabo City | Nanyo | 2nd Eng'g. Dist. | On-going | 2020-04-07 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Panabo City | Nanyo | 2nd Eng'g. Dist. | On-going | 2020-04-07 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | [7 empty] | Date Allotment Released: |  | Date completed:
Panabo City | Nanyo | 2nd Eng'g. Dist. | On-going | 2020-04-07 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | [7 empty] | Date Started:
IGCS | Pichon | 2nd Eng'g. Dist. | On-going | 2020-01-13 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | Impv't. of Brgy. Water System, Pichon, IGCS (Construction of Elevated Tank) |  | GENERAL FUND PROPER CY 2018 (STIMULUS) | Water System |  |  | Admin | Project Cost: | 500000 | Target Completion Date: | 2020-03-13 | Program: | 500000 | Planned: | 100% | No. of Persons: | 5 | On-going
IGCS | Pichon | 2nd Eng'g. Dist. | On-going | 2020-01-13 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | [7 empty] | Project Engineer: | Andoy | Revised Completion Date: | 2020-07-31 | Allotment: | 500000 | Revised: | 86% | No. of Man-days: | 110
IGCS | Pichon | 2nd Eng'g. Dist. | On-going | 2020-01-13 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | [7 empty] | Implementor: | PEO | No. of days suspended: | 140 | Disbursement: | 423575.63 | Actual: | 83.5%
IGCS | Pichon | 2nd Eng'g. Dist. | On-going | 2020-01-13 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | [7 empty] | Duration: | 60 | No. of days extended: |  |  |  | Slippage: | -2.5%
IGCS | Pichon | 2nd Eng'g. Dist. | On-going | 2020-01-13 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | [7 empty] | Date Allotment Released: | 2018-05-31 | Date completed:
IGCS | Pichon | 2nd Eng'g. Dist. | On-going | 2020-01-13 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | [7 empty] | Date Started: | 2020-01-13
IGCS | Cogon | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | Powerline Expansion Project, Cogon, IGACOS |  | GENERAL FUND PROPER CY 2018 (STIMULUS) | Water System |  |  | Contract | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Waiting for NTP (3E Electrical)
IGCS | Cogon | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
IGCS | Cogon | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
IGCS | Cogon | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
IGCS | Cogon | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | [7 empty] | Date Allotment Released: |  | Date completed:
IGCS | Cogon | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | [7 empty] | Date Started:
IGCS | Tagbay | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | Water System From Prk. 6 - Prk. 2 - Prk. 5A, Tagbay, IGCS |  | GENERAL FUND PROPER CY 2018 (STIMULUS) | Water System |  |  | Admin | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | For Implementation
IGCS | Tagbay | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
IGCS | Tagbay | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
IGCS | Tagbay | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
IGCS | Tagbay | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | [7 empty] | Date Allotment Released: |  | Date completed:
IGCS | Tagbay | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | [7 empty] | Date Started:
IGCS | Tambo | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | RURAL ELECTRIFICATION PROJECT | Powerline Expansion Project, Tambo, IGCS |  | GENERAL FUND PROPER CY 2018 (STIMULUS) | Electrification |  |  | Contract | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Purchase Request # 19083312
IGCS | Tambo | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | RURAL ELECTRIFICATION PROJECT | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
IGCS | Tambo | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | RURAL ELECTRIFICATION PROJECT | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
IGCS | Tambo | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | RURAL ELECTRIFICATION PROJECT | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
IGCS | Tambo | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | RURAL ELECTRIFICATION PROJECT | [7 empty] | Date Allotment Released: |  | Date completed:
IGCS | Tambo | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | RURAL ELECTRIFICATION PROJECT | [7 empty] | Date Started:
IGCS | Peñaplata | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | Improvement of Barangay Hall, Penaplata, IGCS |  | GENERAL FUND PROPER CY 2018 (STIMULUS) | Building |  |  | Admin | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | By Contract and change to admin due to unforeseen activities because it’s a repair (For revision of POW)
IGCS | Peñaplata | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
IGCS | Peñaplata | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
IGCS | Peñaplata | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
IGCS | Peñaplata | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | [7 empty] | Date Allotment Released: |  | Date completed:
IGCS | Peñaplata | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | [7 empty] | Date Started:
IGCS | Dadatan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | RURAL ELECTRIFICATION PROJECT | Electrification of Sitio Baongon-Diamond-Mansanitas, Dadatan, IGCS |  | GENERAL FUND PROPER CY 2018 (STIMULUS) | Electrification |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Purchase Order # 20200100002 (3E Electrical Sales & Services)
IGCS | Dadatan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | RURAL ELECTRIFICATION PROJECT | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
IGCS | Dadatan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | RURAL ELECTRIFICATION PROJECT | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
IGCS | Dadatan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | RURAL ELECTRIFICATION PROJECT | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
IGCS | Dadatan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | RURAL ELECTRIFICATION PROJECT | [7 empty] | Date Allotment Released: |  | Date completed:
IGCS | Dadatan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | RURAL ELECTRIFICATION PROJECT | [7 empty] | Date Started:
IGCS | Linusotan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Construction of Water System Projects in Component LGUs | Drilling of Water System, Linusotan, IGCS |  | GENERAL FUND PROPER CY 2018 (STIMULUS) | Water System |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
IGCS | Linusotan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Construction of Water System Projects in Component LGUs | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
IGCS | Linusotan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Construction of Water System Projects in Component LGUs | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
IGCS | Linusotan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Construction of Water System Projects in Component LGUs | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
IGCS | Linusotan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Construction of Water System Projects in Component LGUs | [7 empty] | Date Allotment Released: |  | Date completed:
IGCS | Linusotan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Construction of Water System Projects in Component LGUs | [7 empty] | Date Started:
Carmen | Ising | 2nd Eng'g. Dist. | On-going | 2020-03-19 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | Const. of DDN Hospital Carmen Zone Annex Bldg. |  | SB # 1 CY 2018 | Building |  | sq.m | Contract | Project Cost: | 5500000 | Target Completion Date: | 2020-07-17 | Program: | 5500000 | Planned: | 95.2% | No. of Persons: | 10 | On-going
Carmen | Ising | 2nd Eng'g. Dist. | On-going | 2020-03-19 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | [7 empty] | Project Engineer: | Azotes | Revised Completion Date: | 2020-09-12 | Allotment: | 5500000 | Revised: | 40.5% | No. of Man-days: | 260
Carmen | Ising | 2nd Eng'g. Dist. | On-going | 2020-03-19 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | [7 empty] | Implementor: | Digos Constrak Corp/ | No. of days suspended: | 57 | Disbursement: | 1650000 | Actual: | 68.25%
Carmen | Ising | 2nd Eng'g. Dist. | On-going | 2020-03-19 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | [7 empty] | Duration: | 120 | No. of days extended: |  |  |  | Slippage: | 27.75%
Carmen | Ising | 2nd Eng'g. Dist. | On-going | 2020-03-19 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | [7 empty] | Date Allotment Released: |  | Date completed:
Carmen | Ising | 2nd Eng'g. Dist. | On-going | 2020-03-19 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | [7 empty] | Date Started: | 2020-03-19
Carmen | Cebulano | 2nd Eng'g. Dist. | Completed | 2019-05-21 | 2020-05-31 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | Road ID11 Jct. Highway Sto. Niño - Cebulano |  | 20% DF CY 2019 | Road Rehabilitation | 2.09 | km | Admin | Project Cost: | 1045000 | Target Completion Date: | 2019-10-04 | Program: | 1045000 | Planned: | 100% | No. of Persons: | 6 | Completed as per physical accomplishment. Financial documents still on process.
Carmen | Cebulano | 2nd Eng'g. Dist. | Completed | 2019-05-21 | 2020-05-31 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | [7 empty] | Project Engineer: | Obar/ Nasol | Revised Completion Date: | 2020-06-15 | Allotment: | 1045000 | Revised: |  | No. of Man-days: | 132
Carmen | Cebulano | 2nd Eng'g. Dist. | Completed | 2019-05-21 | 2020-05-31 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | [7 empty] | Implementor: | PEO | No. of days suspended: | 194 | Disbursement: | 1045000 | Actual: | 100%
Carmen | Cebulano | 2nd Eng'g. Dist. | Completed | 2019-05-21 | 2020-05-31 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | [7 empty] | Duration: | 136 | No. of days extended: | 61 |  |  | Slippage: | 0%
Carmen | Cebulano | 2nd Eng'g. Dist. | Completed | 2019-05-21 | 2020-05-31 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | [7 empty] | Date Allotment Released: | 2019-01-03 | Date completed: | 2020-05-31
Carmen | Cebulano | 2nd Eng'g. Dist. | Completed | 2019-05-21 | 2020-05-31 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | [7 empty] | Date Started: | 2019-05-21
Carmen | Tubod | 2nd Eng'g. Dist. | Completed | 2019-11-11 | 2020-06-30 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | ROAD ID 076 - Basa - Tubod |  | 20% DF CY 2019 | Road Rehabilitation | 1.56 | km | Admin | Project Cost: | 1000000 | Target Completion Date: | 2020-03-19 23:59 | Program: | 1000000 | Planned: | 100% | No. of Persons: | 3 | Completed as per physical accomplishment. Financial documents still on process.
Carmen | Tubod | 2nd Eng'g. Dist. | Completed | 2019-11-11 | 2020-06-30 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | [7 empty] | Project Engineer: | PIAD | Revised Completion Date: | 2020-06-30 23:59 | Allotment: | 1000000 | Revised: | 100% | No. of Man-days: | 30
Carmen | Tubod | 2nd Eng'g. Dist. | Completed | 2019-11-11 | 2020-06-30 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | [7 empty] | Implementor: | PEO | No. of days suspended: | 103 | Disbursement: |  | Actual: | 100%
Carmen | Tubod | 2nd Eng'g. Dist. | Completed | 2019-11-11 | 2020-06-30 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | [7 empty] | Duration: | 130 | No. of days extended: |  |  |  | Slippage: | 0%
Carmen | Tubod | 2nd Eng'g. Dist. | Completed | 2019-11-11 | 2020-06-30 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | [7 empty] | Date Allotment Released: | 2019-01-03 | Date completed: | 2020-06-30 23:59
Carmen | Tubod | 2nd Eng'g. Dist. | Completed | 2019-11-11 | 2020-06-30 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | [7 empty] | Date Started: | 2019-11-11
Carmen | Tubod | 2nd Eng'g. Dist. | On-going | 2019-12-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | ROAD ID 077 - Tubod - Pilar |  | 20% DF CY 2019 | Road Rehabilitation | 1.55 | km | Admin | Project Cost: | 16000000 | Target Completion Date: | 2020-11-05 | Program: | 16000000 | Planned: | 62.5% | No. of Persons: | 20 | On-going
Carmen | Tubod | 2nd Eng'g. Dist. | On-going | 2019-12-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | [7 empty] | Project Engineer: | Agang | Revised Completion Date: |  | Allotment: | 16000000 | Revised: |  | No. of Man-days: | 600
Carmen | Tubod | 2nd Eng'g. Dist. | On-going | 2019-12-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: | 4046971.2 | Actual: | 58.23%
Carmen | Tubod | 2nd Eng'g. Dist. | On-going | 2019-12-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | [7 empty] | Duration: | 323 | No. of days extended: |  |  |  | Slippage: | -4.27%
Carmen | Tubod | 2nd Eng'g. Dist. | On-going | 2019-12-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | [7 empty] | Date Allotment Released: | 2019-11-26 | Date completed:
Carmen | Tubod | 2nd Eng'g. Dist. | On-going | 2019-12-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | [7 empty] | Date Started: | 2019-12-18
Carmen | Tibulao | 2nd Eng'g. Dist. | On-going | 2019-11-11 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | ROAD ID 103 - Sitio Malaga - Tibulao |  | 20% DF CY 2019 | Road Rehabilitation | 3.22 | km | Admin | Project Cost: | 1000000 | Target Completion Date: | 2020-02-09 | Program: | 1000000 | Planned: | 78.5% | No. of Persons: | 5 | On-going
Carmen | Tibulao | 2nd Eng'g. Dist. | On-going | 2019-11-11 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | [7 empty] | Project Engineer: | Obar | Revised Completion Date: | 2020-06-30 | Allotment: | 1000000 | Revised: |  | No. of Man-days: | 110
Carmen | Tibulao | 2nd Eng'g. Dist. | On-going | 2019-11-11 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | [7 empty] | Implementor: | PEO | No. of days suspended: | 142 | Disbursement: |  | Actual: | 54.8%
Carmen | Tibulao | 2nd Eng'g. Dist. | On-going | 2019-11-11 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | [7 empty] | Duration: | 90 | No. of days extended: |  |  |  | Slippage: | -23.7%
Carmen | Tibulao | 2nd Eng'g. Dist. | On-going | 2019-11-11 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | [7 empty] | Date Allotment Released: | 2019-01-03 | Date completed:
Carmen | Tibulao | 2nd Eng'g. Dist. | On-going | 2019-11-11 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | [7 empty] | Date Started: | 2019-11-11
B.E. Dujali | Tanglaw | 2nd Eng'g. Dist. | On-going | 2019-12-28 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | ROAD ID 104 - Dujali - Tanglaw |  | 20% DF CY 2019 | Road Rehabilitation | 3.6 | km | Admin | Project Cost: | 2075000 | Target Completion Date: | 2020-04-16 | Program: | 2075000 | Planned: | 60% | No. of Persons: | 11 | On-going
B.E. Dujali | Tanglaw | 2nd Eng'g. Dist. | On-going | 2019-12-28 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | [7 empty] | Project Engineer: | Balbastro | Revised Completion Date: | 2020-08-30 | Allotment: | 2075000 | Revised: |  | No. of Man-days: | 77
B.E. Dujali | Tanglaw | 2nd Eng'g. Dist. | On-going | 2019-12-28 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | [7 empty] | Implementor: | PEO | No. of days suspended: | 28 | Disbursement: |  | Actual: | 65%
B.E. Dujali | Tanglaw | 2nd Eng'g. Dist. | On-going | 2019-12-28 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | [7 empty] | Duration: | 110 | No. of days extended: | 108 |  |  | Slippage: | 5%
B.E. Dujali | Tanglaw | 2nd Eng'g. Dist. | On-going | 2019-12-28 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | [7 empty] | Date Allotment Released: | 2019-01-03 | Date completed:
B.E. Dujali | Tanglaw | 2nd Eng'g. Dist. | On-going | 2019-12-28 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | [7 empty] | Date Started: | 2019-12-28
Sto. Tomas | Libertad | 2nd Eng'g. Dist. | On-going | 2019-06-17 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | ROAD ID 121 - San Miguel - Libertad |  | 20% DF CY 2019 | Road Rehabilitation | 6.2 | km | Admin | Project Cost: | 1240000 | Target Completion Date: | 2019-10-31 | Program: | 1240000 | Planned: | 59.41% | No. of Persons: | 9 | On-going
Sto. Tomas | Libertad | 2nd Eng'g. Dist. | On-going | 2019-06-17 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | [7 empty] | Project Engineer: | Gamad | Revised Completion Date: | 2020-02-29 | Allotment: | 1240000 | Revised: |  | No. of Man-days: | 36
Sto. Tomas | Libertad | 2nd Eng'g. Dist. | On-going | 2019-06-17 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | [7 empty] | Implementor: | PEO | No. of days suspended: | 86 | Disbursement: |  | Actual: | 59.41%
Sto. Tomas | Libertad | 2nd Eng'g. Dist. | On-going | 2019-06-17 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | [7 empty] | Duration: | 136 | No. of days extended: | 35 |  |  | Slippage: | 0%
Sto. Tomas | Libertad | 2nd Eng'g. Dist. | On-going | 2019-06-17 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | [7 empty] | Date Allotment Released: | 2019-01-03 | Date completed:
Sto. Tomas | Libertad | 2nd Eng'g. Dist. | On-going | 2019-06-17 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | [7 empty] | Date Started: | 2019-06-17
Sto. Tomas | Casig-ang | 2nd Eng'g. Dist. | On-going | 2019-06-27 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | ROAD ID 123 - Bacali - Casig-ang - Libertad |  | 20% DF CY 2019 | Road Rehabilitation | 4.7 | km | Admin | Project Cost: | 940000 | Target Completion Date: | 2019-09-15 | Program: | 940000 | Planned: | 62.1% | No. of Persons: | 9 | On-going
Sto. Tomas | Casig-ang | 2nd Eng'g. Dist. | On-going | 2019-06-27 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | [7 empty] | Project Engineer: | Gamad | Revised Completion Date: | 2020-02-29 | Allotment: | 940000 | Revised: |  | No. of Man-days: | 36
Sto. Tomas | Casig-ang | 2nd Eng'g. Dist. | On-going | 2019-06-27 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | [7 empty] | Implementor: | PEO | No. of days suspended: | 132 | Disbursement: |  | Actual: | 62%
Sto. Tomas | Casig-ang | 2nd Eng'g. Dist. | On-going | 2019-06-27 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | [7 empty] | Duration: | 80 | No. of days extended: | 35 |  |  | Slippage: | -0.1%
Sto. Tomas | Casig-ang | 2nd Eng'g. Dist. | On-going | 2019-06-27 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | [7 empty] | Date Allotment Released: | 2019-06-07 | Date completed:
Sto. Tomas | Casig-ang | 2nd Eng'g. Dist. | On-going | 2019-06-27 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | [7 empty] | Date Started: | 2019-06-27
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | On-going | 2019-06-17 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | ROAD ID 125 - San Miguel - Moslog - Kinamayan |  | 20% DF CY 2019 | Road Rehabilitation | 2.9 | km | Admin | Project Cost: | 1000000 | Target Completion Date: | 2019-09-16 | Program: | 1000000 | Planned: | 100% | No. of Persons: | 6 | On-going
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | On-going | 2019-06-17 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | [7 empty] | Project Engineer: | Gamad | Revised Completion Date: | 2020-02-29 | Allotment: | 1000000 | Revised: | 73.59% | No. of Man-days: | 30
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | On-going | 2019-06-17 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | [7 empty] | Implementor: | PEO | No. of days suspended: | 137 | Disbursement: |  | Actual: | 80%
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | On-going | 2019-06-17 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | [7 empty] | Duration: | 91 | No. of days extended: | 29 |  |  | Slippage: | 6.41%
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | On-going | 2019-06-17 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | [7 empty] | Date Allotment Released: | 2019-05-20 | Date completed:
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | On-going | 2019-06-17 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | [7 empty] | Date Started: | 2019-06-17
Sto. Tomas | Katipunana | 2nd Eng'g. Dist. | On-going | 2019-12-27 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | ROAD ID 134 - New Katipunan - Pantaron |  | 20% DF CY 2019 | Road Rehabilitation | 1.96 | km | Admin | Project Cost: | 395000 | Target Completion Date: | 2020-02-25 | Program: | 395000 | Planned: | 60% | No. of Persons: | 4 | On-going
Sto. Tomas | Katipunana | 2nd Eng'g. Dist. | On-going | 2019-12-27 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | [7 empty] | Project Engineer: | Gamad/Clar | Revised Completion Date: |  | Allotment: | 395000 | Revised: |  | No. of Man-days: | 24
Sto. Tomas | Katipunana | 2nd Eng'g. Dist. | On-going | 2019-12-27 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: | 60%
Sto. Tomas | Katipunana | 2nd Eng'g. Dist. | On-going | 2019-12-27 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | [7 empty] | Duration: | 60 | No. of days extended: |  |  |  | Slippage: | 0%
Sto. Tomas | Katipunana | 2nd Eng'g. Dist. | On-going | 2019-12-27 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | [7 empty] | Date Allotment Released: | 2019-01-03 | Date completed:
Sto. Tomas | Katipunana | 2nd Eng'g. Dist. | On-going | 2019-12-27 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | [7 empty] | Date Started: | 2019-12-27
B.E. Dujali | Tanglaw | 2nd Eng'g. Dist. | On-going | 2019-06-17 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | ROAD ID 142 - Jct. Highway - Tanglaw |  | 20% DF CY 2019 | Road Rehabilitation | 3.98 | km | Admin | Project Cost: | 1100000 | Target Completion Date: | 2019-09-16 | Program: | 1100000 | Planned: | 100% | No. of Persons: | 10 | On-going
B.E. Dujali | Tanglaw | 2nd Eng'g. Dist. | On-going | 2019-06-17 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | [7 empty] | Project Engineer: | Gamad/Clar | Revised Completion Date: | 2020-02-29 | Allotment: | 1100000 | Revised: | 73.59% | No. of Man-days: | 50
B.E. Dujali | Tanglaw | 2nd Eng'g. Dist. | On-going | 2019-06-17 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | [7 empty] | Implementor: | PEO | No. of days suspended: | 137 | Disbursement: |  | Actual: | 85%
B.E. Dujali | Tanglaw | 2nd Eng'g. Dist. | On-going | 2019-06-17 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | [7 empty] | Duration: | 91 | No. of days extended: | 29 |  |  | Slippage: | 11.41%
B.E. Dujali | Tanglaw | 2nd Eng'g. Dist. | On-going | 2019-06-17 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | [7 empty] | Date Allotment Released: | 2019-05-16 | Date completed:
B.E. Dujali | Tanglaw | 2nd Eng'g. Dist. | On-going | 2019-06-17 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | [7 empty] | Date Started: | 2019-06-17
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | On-going | 2019-12-27 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | ROAD ID 146 - Bdry. Tagum - Crossing Kinamayan Sto. Tomas |  | 20% DF CY 2019 | Road Rehabilitation | 0.75 | km | Admin | Project Cost: | 3700000 | Target Completion Date: | 2020-04-25 | Program: | 3700000 | Planned: | 100% | No. of Persons: | 15 | On-going
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | On-going | 2019-12-27 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | [7 empty] | Project Engineer: | Gamad/Clar | Revised Completion Date: | 2020-08-23 | Allotment: | 3700000 | Revised: | 15.43% | No. of Man-days: | 225
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | On-going | 2019-12-27 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | [7 empty] | Implementor: |  | No. of days suspended: | 20 | Disbursement: |  | Actual: | 16.37%
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | On-going | 2019-12-27 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | [7 empty] | Duration: | 120 | No. of days extended: | 100 |  |  | Slippage: | 0.94%
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | On-going | 2019-12-27 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | [7 empty] | Date Allotment Released: | 2019-01-03 | Date completed:
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | On-going | 2019-12-27 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | [7 empty] | Date Started: | 2019-12-27
Sto. Tomas | San Jose | 2nd Eng'g. Dist. | On-going | 2020-05-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | Fr. Rd. 3 - San Jose |  | 20% DF CY 2019 | Road Rehabilitation | 4.55 | km | Admin | Project Cost: | 800000 | Target Completion Date: | 2020-08-06 | Program: | 800000 | Planned: | 2.14% | No. of Persons: | 3 | On-going
Sto. Tomas | San Jose | 2nd Eng'g. Dist. | On-going | 2020-05-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Project Engineer: | Obar | Revised Completion Date: |  | Allotment: | 800000 | Revised: |  | No. of Man-days: | 30
Sto. Tomas | San Jose | 2nd Eng'g. Dist. | On-going | 2020-05-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: | 2.14%
Sto. Tomas | San Jose | 2nd Eng'g. Dist. | On-going | 2020-05-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Duration: | 80 | No. of days extended: |  |  |  | Slippage: | 0%
Sto. Tomas | San Jose | 2nd Eng'g. Dist. | On-going | 2020-05-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Date Allotment Released: | 2019-01-03 | Date completed:
Sto. Tomas | San Jose | 2nd Eng'g. Dist. | On-going | 2020-05-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Date Started: | 2020-05-18
Carmen | Asuncion | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | Lower Asuncion - Upper Asuncion |  | 20% DF CY 2019 | Road Rehabilitation | 1.02 | km | Admin | Project Cost: |  | Target Completion Date: |  | Program: | 0 | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
Carmen | Asuncion | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 0 | Revised: |  | No. of Man-days:
Carmen | Asuncion | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Carmen | Asuncion | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Carmen | Asuncion | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Date Allotment Released: |  | Date completed:
Carmen | Asuncion | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Date Started:
Carmen | Mangalcal | 2nd Eng'g. Dist. | On-going | 2020-06-15 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | Jct. Highway - Carmen - Mangalcal - Tubod |  | 20% DF CY 2019 | Road Rehabilitation | 11.34 | km | Admin | Project Cost: | 1323000 | Target Completion Date: | 2020-07-15 | Program: | 1323000 | Planned: | 100% | No. of Persons: | 3 | On-going
Carmen | Mangalcal | 2nd Eng'g. Dist. | On-going | 2020-06-15 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Project Engineer: | Obar | Revised Completion Date: |  | Allotment: | 1323000 | Revised: |  | No. of Man-days: | 30
Carmen | Mangalcal | 2nd Eng'g. Dist. | On-going | 2020-06-15 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: | 1.21%
Carmen | Mangalcal | 2nd Eng'g. Dist. | On-going | 2020-06-15 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Duration: | 30 | No. of days extended: |  |  |  | Slippage: | -98.79%
Carmen | Mangalcal | 2nd Eng'g. Dist. | On-going | 2020-06-15 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Date Allotment Released: | 2019-01-03 | Date completed:
Carmen | Mangalcal | 2nd Eng'g. Dist. | On-going | 2020-06-15 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Date Started: | 2020-06-15
B.E. Dujali | Tuganay-Taba | 2nd Eng'g. Dist. | On-going | 2020-05-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | Tuganay - Taba |  | 20% DF CY 2019 | Road Rehabilitation | 4.27 | km | Admin | Project Cost: | 507500 | Target Completion Date: | 2020-06-17 | Program: | 507500 | Planned: | 100% | No. of Persons: | 3 | On-going
B.E. Dujali | Tuganay-Taba | 2nd Eng'g. Dist. | On-going | 2020-05-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Project Engineer: | Obar | Revised Completion Date: |  | Allotment: | 507500 | Revised: |  | No. of Man-days: | 30
B.E. Dujali | Tuganay-Taba | 2nd Eng'g. Dist. | On-going | 2020-05-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: | 3.37%
B.E. Dujali | Tuganay-Taba | 2nd Eng'g. Dist. | On-going | 2020-05-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Duration: | 30 | No. of days extended: |  |  |  | Slippage: | -96.63%
B.E. Dujali | Tuganay-Taba | 2nd Eng'g. Dist. | On-going | 2020-05-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Date Allotment Released: | 2019-01-03 | Date completed:
B.E. Dujali | Tuganay-Taba | 2nd Eng'g. Dist. | On-going | 2020-05-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Date Started: | 2020-05-18
B.E. Dujali | Ising | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | Jct. Highway - Ising - Magsaysay |  | 20% DF CY 2019 | Road Rehabilitation | 10.84 | km | Admin | Project Cost: | 6000000 | Target Completion Date: |  | Program: | 6000000 | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
B.E. Dujali | Ising | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 6000000 | Revised: |  | No. of Man-days:
B.E. Dujali | Ising | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
B.E. Dujali | Ising | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
B.E. Dujali | Ising | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Date Allotment Released: |  | Date completed:
B.E. Dujali | Ising | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Date Started:
B.E. Dujali | Guadalupe | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | Jct. Highway - Guadalupe - Bdry. Tagum |  | 20% DF CY 2019 | Road Rehabilitation | 7.9 | km | Admin | Project Cost: | 910000 | Target Completion Date: | 2020-08-06 | Program: | 910000 | Planned: | 2.04% | No. of Persons: | 3 | On-going
B.E. Dujali | Guadalupe | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Project Engineer: | Obar | Revised Completion Date: |  | Allotment: | 910000 | Revised: |  | No. of Man-days: | 30
B.E. Dujali | Guadalupe | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: | 2.04%
B.E. Dujali | Guadalupe | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Duration: | 80 | No. of days extended: |  |  |  | Slippage: | 0%
B.E. Dujali | Guadalupe | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Date Allotment Released: | 2019-01-03 | Date completed:
B.E. Dujali | Guadalupe | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Date Started: | 2020-05-18
Carmen | Tibulao | 2nd Eng'g. Dist. | On-going | 2020-05-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | Sitio Malaga - Tibulao |  | 20% DF CY 2019 | Road Rehabilitation | 3.22 | km | Admin | Project Cost: | 300000 | Target Completion Date: | 2020-08-06 | Program: | 300000 | Planned: | 3.37% | No. of Persons: | 3 | On-going
Carmen | Tibulao | 2nd Eng'g. Dist. | On-going | 2020-05-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Project Engineer: | Obar | Revised Completion Date: |  | Allotment: | 300000 | Revised: |  | No. of Man-days: | 30
Carmen | Tibulao | 2nd Eng'g. Dist. | On-going | 2020-05-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: | 3.37%
Carmen | Tibulao | 2nd Eng'g. Dist. | On-going | 2020-05-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Duration: | 80 | No. of days extended: |  |  |  | Slippage:
Carmen | Tibulao | 2nd Eng'g. Dist. | On-going | 2020-05-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Date Allotment Released: | 2019-01-03 | Date completed:
Carmen | Tibulao | 2nd Eng'g. Dist. | On-going | 2020-05-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Date Started: | 2020-05-18
Carmen | New Casay | 2nd Eng'g. Dist. | On-going | 2020-05-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | Prk. 5 RJS - Prk 6 New Casay |  | 20% DF CY 2019 | Road Rehabilitation | 2.73 | km | Admin | Project Cost: | 350000 | Target Completion Date: | 2020-06-17 | Program: | 350000 | Planned: | 3.37% | No. of Persons: | 3 | On-going
Carmen | New Casay | 2nd Eng'g. Dist. | On-going | 2020-05-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Project Engineer: | Obar | Revised Completion Date: |  | Allotment: | 350000 | Revised: |  | No. of Man-days: | 30
Carmen | New Casay | 2nd Eng'g. Dist. | On-going | 2020-05-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: | 3.37%
Carmen | New Casay | 2nd Eng'g. Dist. | On-going | 2020-05-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Duration: | 30 | No. of days extended: |  |  |  | Slippage: | 0%
Carmen | New Casay | 2nd Eng'g. Dist. | On-going | 2020-05-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Date Allotment Released: | 2019-01-03 | Date completed:
Carmen | New Casay | 2nd Eng'g. Dist. | On-going | 2020-05-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Date Started: | 2020-05-18
B.E. Dujali | San Vicente | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | Dujali - Pawas - San Vicente |  | 20% DF CY 2019 | Road Rehabilitation | 4.42 | km | Admin | Project Cost: | 525000 | Target Completion Date: | 2020-07-02 | Program: | 525000 | Planned: | 2.41% | No. of Persons: | 3 | On-going
B.E. Dujali | San Vicente | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Project Engineer: | Obar | Revised Completion Date: |  | Allotment: | 525000 | Revised: |  | No. of Man-days: | 30
B.E. Dujali | San Vicente | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: | 2.41%
B.E. Dujali | San Vicente | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Duration: | 45 | No. of days extended: |  |  |  | Slippage: | 0%
B.E. Dujali | San Vicente | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Date Allotment Released: | 2019-01-03 | Date completed:
B.E. Dujali | San Vicente | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Date Started: | 2020-05-18
Sto. Tomas | Esperanza | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | Los Amigos 1 - Esperanza - Los Amigos 2 |  | 20% DF CY 2019 | Road Rehabilitation | 3.59 | km | Admin | Project Cost: | 19200000 | Target Completion Date: |  | Program: | 19200000 | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
Sto. Tomas | Esperanza | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 19200000 | Revised: |  | No. of Man-days:
Sto. Tomas | Esperanza | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Sto. Tomas | Esperanza | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Sto. Tomas | Esperanza | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Date Allotment Released: |  | Date completed:
Sto. Tomas | Esperanza | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Date Started:
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | On-going | 2020-05-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | San Miguel - Crossing Kinamayan |  | 20% DF CY 2019 | Road Rehabilitation | 2.8 | km | Admin | Project Cost: | 350000 | Target Completion Date: | 2020-07-17 | Program: | 350000 | Planned: | 22.58% | No. of Persons: | 6 | On-going
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | On-going | 2020-05-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Project Engineer: | Piad/ Obar | Revised Completion Date: |  | Allotment: | 350000 | Revised: |  | No. of Man-days: | 84
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | On-going | 2020-05-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: | 22.58%
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | On-going | 2020-05-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Duration: | 60 | No. of days extended: |  |  |  | Slippage: | 0%
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | On-going | 2020-05-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Date Allotment Released: | 2019-01-03 | Date completed:
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | On-going | 2020-05-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Date Started: | 2020-05-18
Sto. Tomas | Magwawa | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | Fd Rd 2 - Sto. Tomas - Magwawa |  | 20% DF CY 2019 | Road Rehabilitation | 10.21 | km | Admin | Project Cost: |  | Target Completion Date: |  | Program: | 0 | Planned: |  | No. of Persons: |  | Plan and POW Approved
Sto. Tomas | Magwawa | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 0 | Revised: |  | No. of Man-days:
Sto. Tomas | Magwawa | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Sto. Tomas | Magwawa | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Sto. Tomas | Magwawa | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Date Allotment Released: |  | Date completed:
Sto. Tomas | Magwawa | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Date Started:
Sto. Tomas | Tulalian | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | Menzi - Balagunan - Tulalian |  | 20% DF CY 2019 | Road Rehabilitation | 10.63 | km | Admin | Project Cost: | 3720500 | Target Completion Date: |  | Program: | 3720500 | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
Sto. Tomas | Tulalian | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 3720500 | Revised: |  | No. of Man-days:
Sto. Tomas | Tulalian | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Sto. Tomas | Tulalian | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Sto. Tomas | Tulalian | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Date Allotment Released: |  | Date completed:
Sto. Tomas | Tulalian | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Date Started:
Sto. Tomas | Talomo | 2nd Eng'g. Dist. | On-going | 2020-05-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | Jct. Bdry. Tagum - Talomo |  | 20% DF CY 2019 | Road Rehabilitation | 12.01 | km | Admin | Project Cost: | 1400000 | Target Completion Date: | 2020-09-15 | Program: | 1400000 | Planned: | 3% | No. of Persons: | 3 | On-going
Sto. Tomas | Talomo | 2nd Eng'g. Dist. | On-going | 2020-05-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Project Engineer: | Obar | Revised Completion Date: |  | Allotment: | 1400000 | Revised: |  | No. of Man-days: | 30
Sto. Tomas | Talomo | 2nd Eng'g. Dist. | On-going | 2020-05-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: | 3.37%
Sto. Tomas | Talomo | 2nd Eng'g. Dist. | On-going | 2020-05-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Duration: | 120 | No. of days extended: |  |  |  | Slippage: | 0.37%
Sto. Tomas | Talomo | 2nd Eng'g. Dist. | On-going | 2020-05-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Date Allotment Released: | 2019-01-23 | Date completed:
Sto. Tomas | Talomo | 2nd Eng'g. Dist. | On-going | 2020-05-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Date Started: | 2020-05-18
Carmen | Anibongan | 2nd Eng'g. Dist. | Completed | 2019-05-22 | 2020-01-31 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | Rehab. of Anibongan-Salvacion-Cabay-angan Provincial Road with Drainage |  | 20% DF CY 2019 | Road Drainage rehabiliated |  | km | Admin | Project Cost: | 2000000 | Target Completion Date: | 2019-08-04 23:59 | Program: | 2000000 | Planned: | 100% | No. of Persons: | 1 | Completed as per physical accomplishment. Financial documents still on process.
Carmen | Anibongan | 2nd Eng'g. Dist. | Completed | 2019-05-22 | 2020-01-31 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Project Engineer: | Toquero | Revised Completion Date: | 2019-12-31 23:59 | Allotment: | 2000000 | Revised: |  | No. of Man-days: | 4
Carmen | Anibongan | 2nd Eng'g. Dist. | Completed | 2019-05-22 | 2020-01-31 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: | 100%
Carmen | Anibongan | 2nd Eng'g. Dist. | Completed | 2019-05-22 | 2020-01-31 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Duration: | 75 | No. of days extended: | 149 |  |  | Slippage: | 0%
Carmen | Anibongan | 2nd Eng'g. Dist. | Completed | 2019-05-22 | 2020-01-31 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Date Allotment Released: | 2019-01-14 | Date completed: | 2020-01-31
Carmen | Anibongan | 2nd Eng'g. Dist. | Completed | 2019-05-22 | 2020-01-31 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Date Started: | 2019-05-22
B.E. Dujali | Dujali | 2nd Eng'g. Dist. | On-going | 2019-11-04 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various of Local Roads & Drainage Development Project (Provincewide) LS - 15,000,000.00 | Rehab. Of Dujali-Pawas-San Vicente Provincial Road |  | 20% DF CY 2019 | Road Drainage rehabiliated |  | km | Admin | Project Cost: | 2000000 | Target Completion Date: |  | Program: | 2000000 | Planned: | 80% | No. of Persons: |  | On-going
B.E. Dujali | Dujali | 2nd Eng'g. Dist. | On-going | 2019-11-04 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various of Local Roads & Drainage Development Project (Provincewide) LS - 15,000,000.00 | [7 empty] | Project Engineer: | Toquero | Revised Completion Date: |  | Allotment: | 2000000 | Revised: |  | No. of Man-days:
B.E. Dujali | Dujali | 2nd Eng'g. Dist. | On-going | 2019-11-04 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various of Local Roads & Drainage Development Project (Provincewide) LS - 15,000,000.00 | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: | 80%
B.E. Dujali | Dujali | 2nd Eng'g. Dist. | On-going | 2019-11-04 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various of Local Roads & Drainage Development Project (Provincewide) LS - 15,000,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
B.E. Dujali | Dujali | 2nd Eng'g. Dist. | On-going | 2019-11-04 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various of Local Roads & Drainage Development Project (Provincewide) LS - 15,000,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
B.E. Dujali | Dujali | 2nd Eng'g. Dist. | On-going | 2019-11-04 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various of Local Roads & Drainage Development Project (Provincewide) LS - 15,000,000.00 | [7 empty] | Date Started: | 2019-11-04
B.E. Dujali | Ising | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various of Local Roads & Drainage Development Project (Provincewide) LS - 15,000,000.00 | Rehab./Impv't. of Jct. highway Ising-Magsaysay Provincial Road with Drainage |  | 20% DF CY 2019 | Road Drainage rehabiliated |  | km | Admin | Project Cost: | 1500000 | Target Completion Date: |  | Program: | 1500000 | Planned: |  | No. of Persons: |  | Revised POW for approval - Jan. 7, 2020 Revision was made due to scarcity of boulders changing from stone masonry to concrete masonry
B.E. Dujali | Ising | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various of Local Roads & Drainage Development Project (Provincewide) LS - 15,000,000.00 | [7 empty] | Project Engineer: | Toquero | Revised Completion Date: |  | Allotment: | 1500000 | Revised: |  | No. of Man-days:
B.E. Dujali | Ising | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various of Local Roads & Drainage Development Project (Provincewide) LS - 15,000,000.00 | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual:
B.E. Dujali | Ising | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various of Local Roads & Drainage Development Project (Provincewide) LS - 15,000,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
B.E. Dujali | Ising | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various of Local Roads & Drainage Development Project (Provincewide) LS - 15,000,000.00 | [7 empty] | Date Allotment Released: | 2019-01-16 | Date completed:
B.E. Dujali | Ising | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various of Local Roads & Drainage Development Project (Provincewide) LS - 15,000,000.00 | [7 empty] | Date Started:
Panabo City | Consolacion | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | Impv't. of Potable Water System, Consolacion, Panabo City |  | 20% DF CY 2019 | Water System |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
Panabo City | Consolacion | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Panabo City | Consolacion | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Panabo City | Consolacion | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Panabo City | Consolacion | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | [7 empty] | Date Allotment Released: | 2019-06-28 | Date completed:
Panabo City | Consolacion | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | [7 empty] | Date Started:
Samal | Tagbitan-ag | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | Impv't. of Potable Water System, Tagbitan-ag, Samal Dist. |  | 20% DF CY 2019 | Water System |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | For implementation
Samal | Tagbitan-ag | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Samal | Tagbitan-ag | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Samal | Tagbitan-ag | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Samal | Tagbitan-ag | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | [7 empty] | Date Allotment Released: | 2019-06-19 | Date completed:
Samal | Tagbitan-ag | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | [7 empty] | Date Started:
Babak | San Antonio | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | Impv't. of Potable Water System, San Antonio, babak, IGCS |  | 20% DF CY 2019 | Water System |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
Babak | San Antonio | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Babak | San Antonio | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Babak | San Antonio | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Babak | San Antonio | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | [7 empty] | Date Allotment Released: | 2019-06-25 | Date completed:
Babak | San Antonio | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | [7 empty] | Date Started:
IGCS | Mambago | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | Impv't. of Potable Water System, Mambago-A, IGCS |  | 20% DF CY 2019 | Water System |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | For Implementation
IGCS | Mambago | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
IGCS | Mambago | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
IGCS | Mambago | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
IGCS | Mambago | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | [7 empty] | Date Allotment Released: | 2019-09-10 | Date completed:
IGCS | Mambago | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | [7 empty] | Date Started:
Panabo City | Buenavista | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | Construction of PWS, Brgy. Buenavista, Panabo City |  | 20% DF CY 2019 | Water System |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | For implementation
Panabo City | Buenavista | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Panabo City | Buenavista | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Panabo City | Buenavista | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Panabo City | Buenavista | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | [7 empty] | Date Allotment Released: | June 19 ,2019 | Date completed:
Panabo City | Buenavista | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | [7 empty] | Date Started:
Panabo City | Kiotoy | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | Construction of PWS, Brgy. Brgy. Kiotoy, Panabo City |  | 20% DF CY 2019 | Water System |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
Panabo City | Kiotoy | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Panabo City | Kiotoy | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Panabo City | Kiotoy | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Panabo City | Kiotoy | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Panabo City | Kiotoy | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | [7 empty] | Date Started:
IGCS | Linusotan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | Construction of PWS, Brgy. Linusotan, Talikud, District, IGCS |  | 20% DF CY 2019 | Water System |  |  |  | Project Cost: | 1300000 | Target Completion Date: |  | Program: | 1300000 | Planned: |  | No. of Persons: |  | Procurement on process
IGCS | Linusotan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 1300000 | Revised: |  | No. of Man-days:
IGCS | Linusotan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
IGCS | Linusotan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
IGCS | Linusotan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | [7 empty] | Date Allotment Released: | 2019-10-23 | Date completed:
IGCS | Linusotan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | [7 empty] | Date Started:
Babak, IGCS | San Miguel | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | Rehab. of PWS, Brgy. San Miguel, Babak, IGCS |  | 20% DF CY 2019 | Water System |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
Babak, IGCS | San Miguel | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Babak, IGCS | San Miguel | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Babak, IGCS | San Miguel | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Babak, IGCS | San Miguel | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Babak, IGCS | San Miguel | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | [7 empty] | Date Started:
Panabo City | Cacao | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | Construction of PWS, Brgy. Cacao, Panabo City |  | 20% DF CY 2019 | Water System |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | For cancellation. Purchase of Geo-resistivity equipment but procurement still on process
Panabo City | Cacao | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Panabo City | Cacao | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Panabo City | Cacao | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Panabo City | Cacao | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Panabo City | Cacao | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | [7 empty] | Date Started:
Kaputian, IGCS | Pangubatan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | Rehabilitation of Potable Water System, Brgy. Pangubatan, kaputian Dist. IGCS |  | 20% DF CY 2019 | Water System |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | For implementation
Kaputian, IGCS | Pangubatan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Kaputian, IGCS | Pangubatan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Kaputian, IGCS | Pangubatan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Kaputian, IGCS | Pangubatan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Kaputian, IGCS | Pangubatan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | [7 empty] | Date Started:
Carmen | Ising | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Government Buildings and Facilities Development Project (Provincewide) LS - P 27,000,000.00 | Const. of DDN Hospital Carmen Zone Annex Bldg. Phase 2, |  | 20% DF CY 2019 | Building |  | sq.m | Contract | Project Cost: | 3620000 | Target Completion Date: |  | Program: | 3620000 | Planned: |  | No. of Persons: |  | For implementation (Winning Bidder - Digos Constrak Corp.)
Carmen | Ising | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Government Buildings and Facilities Development Project (Provincewide) LS - P 27,000,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 3620000 | Revised: |  | No. of Man-days:
Carmen | Ising | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Government Buildings and Facilities Development Project (Provincewide) LS - P 27,000,000.00 | [7 empty] | Implementor: | Digos Constrak Corp/ | No. of days suspended: |  | Disbursement: |  | Actual:
Carmen | Ising | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Government Buildings and Facilities Development Project (Provincewide) LS - P 27,000,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Carmen | Ising | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Government Buildings and Facilities Development Project (Provincewide) LS - P 27,000,000.00 | [7 empty] | Date Allotment Released: | 2019-06-28 | Date completed:
Carmen | Ising | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | [7 empty] | Date Started:
Carmen | La Paz | 2nd Eng'g. Dist. | On-going | 2019-08-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | Const. of Multi-Purpose Hall, La Paz, Carmen |  | 20% DF CY 2019 (STIMULUS | Building |  | sq.m | MLGU | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Fund transferred to LGU March 28, 2019
Carmen | La Paz | 2nd Eng'g. Dist. | On-going | 2019-08-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Carmen | La Paz | 2nd Eng'g. Dist. | On-going | 2019-08-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Carmen | La Paz | 2nd Eng'g. Dist. | On-going | 2019-08-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Carmen | La Paz | 2nd Eng'g. Dist. | On-going | 2019-08-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Allotment Released: | 2019-02-20 | Date completed:
Carmen | La Paz | 2nd Eng'g. Dist. | On-going | 2019-08-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Started: | 2019-08-16
Carmen | Sto. Niño | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | Const. of Evacuation Center Ph. 3, Sto. Niño, Carmen |  | 20% DF CY 2019 (STIMULUS | Building |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Amended in the AIP 3rd revision CY 2019/ SB No. 4 CY 2019 changing the location to Purok !-c, Sto. Nino since the previous location was implemented by DPWH
Carmen | Sto. Niño | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Carmen | Sto. Niño | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Carmen | Sto. Niño | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Carmen | Sto. Niño | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Carmen | Sto. Niño | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Started:
Carmen | Mangalcal | 2nd Eng'g. Dist. | On-going | 2019-09-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | Const. of Multi-Purpose Hall, Mangalcal, Carmen |  | 20% DF CY 2019 (STIMULUS | Building |  | sq.m | MLGU | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Fund transfer to LGU Carmen, 3/28/2019 with check no. 2574953 and OR no. 0118982
Carmen | Mangalcal | 2nd Eng'g. Dist. | On-going | 2019-09-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Carmen | Mangalcal | 2nd Eng'g. Dist. | On-going | 2019-09-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Carmen | Mangalcal | 2nd Eng'g. Dist. | On-going | 2019-09-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Carmen | Mangalcal | 2nd Eng'g. Dist. | On-going | 2019-09-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Allotment Released: | 2019-02-20 | Date completed:
Carmen | Mangalcal | 2nd Eng'g. Dist. | On-going | 2019-09-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Started: | 2019-09-16
Carmen | Guadalupe | 2nd Eng'g. Dist. | On-going | 2019-08-15 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | Rehab. of Multi-Purpose Hall, Guadalupe, Carmen |  | 20% DF CY 2019 (STIMULUS | Building |  |  | MLGU | Project Cost: | 500000 | Target Completion Date: | 2019-11-13 23:59 | Program: | 500000 | Planned: |  | No. of Persons: |  | Fund transferred to LGU March 28, 2019
Carmen | Guadalupe | 2nd Eng'g. Dist. | On-going | 2019-08-15 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Carmen | Guadalupe | 2nd Eng'g. Dist. | On-going | 2019-08-15 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Carmen | Guadalupe | 2nd Eng'g. Dist. | On-going | 2019-08-15 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Duration: | 91 | No. of days extended: |  |  |  | Slippage: | 0%
Carmen | Guadalupe | 2nd Eng'g. Dist. | On-going | 2019-08-15 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Allotment Released: | 2019-02-20 | Date completed:
Carmen | Guadalupe | 2nd Eng'g. Dist. | On-going | 2019-08-15 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Started: | 2019-08-15
Carmen | Mabuhay | 2nd Eng'g. Dist. | On-going | 2019-08-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | Const. of Multi-Purpose Hall, Mabuhay, Carmen |  | 20% DF CY 2019 (STIMULUS | Building |  | sq.m | MLGU | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Fund transfer to LGU Carmen, 3/28/2019 with check no. 2574925 and OR no. 0118984
Carmen | Mabuhay | 2nd Eng'g. Dist. | On-going | 2019-08-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Carmen | Mabuhay | 2nd Eng'g. Dist. | On-going | 2019-08-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Carmen | Mabuhay | 2nd Eng'g. Dist. | On-going | 2019-08-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Carmen | Mabuhay | 2nd Eng'g. Dist. | On-going | 2019-08-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Allotment Released: | 2019-02-20 | Date completed:
Carmen | Mabuhay | 2nd Eng'g. Dist. | On-going | 2019-08-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Started: | 2019-08-16
Carmen | Mabaus | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | Const. Canal Lining , Mabaus, Carmen |  | 20% DF CY 2019 (STIMULUS | Canal lining |  |  | MLGU | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Fund transferred to LGU March 28, 2019
Carmen | Mabaus | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Carmen | Mabaus | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Carmen | Mabaus | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Carmen | Mabaus | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Allotment Released: | 2019-02-20 | Date completed:
Carmen | Mabaus | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Started:
Carmen | Alejal | 2nd Eng'g. Dist. | On-going | 2019-08-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | Rehab. Of Evacuation Center, Alejal, Carmen |  | 20% DF CY 2019 (STIMULUS | Building |  | sq.m | MLGU | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Fund transfer to LGU Carmen, 3/28/2019 with check no.2574949 and OR no. 0118991
Carmen | Alejal | 2nd Eng'g. Dist. | On-going | 2019-08-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Carmen | Alejal | 2nd Eng'g. Dist. | On-going | 2019-08-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Carmen | Alejal | 2nd Eng'g. Dist. | On-going | 2019-08-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Carmen | Alejal | 2nd Eng'g. Dist. | On-going | 2019-08-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Allotment Released: | 2019-02-20 | Date completed:
Carmen | Alejal | 2nd Eng'g. Dist. | On-going | 2019-08-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Started: | 2019-08-16
Carmen | Tuganay | 2nd Eng'g. Dist. | On-going | 2019-08-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | Compl. Of Evacuation Center, Tuganay, Carmen |  | 20% DF CY 2019 (STIMULUS | Building |  | sq.m | MLGU | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Fund transfer to LGU Carmen, 3/28/2019 with check no. 2574947 and OR no. 0118995
Carmen | Tuganay | 2nd Eng'g. Dist. | On-going | 2019-08-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Carmen | Tuganay | 2nd Eng'g. Dist. | On-going | 2019-08-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Carmen | Tuganay | 2nd Eng'g. Dist. | On-going | 2019-08-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Carmen | Tuganay | 2nd Eng'g. Dist. | On-going | 2019-08-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Allotment Released: | 2019-02-20 | Date completed:
Carmen | Tuganay | 2nd Eng'g. Dist. | On-going | 2019-08-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Started: | 2019-08-16
Carmen | Ising | 2nd Eng'g. Dist. | On-going | 2019-08-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | Const. of Multi-Purpose hall, Ising, Carmen |  | 20% DF CY 2019 (STIMULUS | Building |  |  | MLGU | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Fund transferred to LGU March 28, 2019
Carmen | Ising | 2nd Eng'g. Dist. | On-going | 2019-08-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Carmen | Ising | 2nd Eng'g. Dist. | On-going | 2019-08-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Carmen | Ising | 2nd Eng'g. Dist. | On-going | 2019-08-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Carmen | Ising | 2nd Eng'g. Dist. | On-going | 2019-08-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Allotment Released: | 2019-02-20 | Date completed:
Carmen | Ising | 2nd Eng'g. Dist. | On-going | 2019-08-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Started:
Carmen | Cebulano | 2nd Eng'g. Dist. | On-going | 2019-08-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | Rehab. of Multi-Purpose hall, Cebulano, Carmen |  | 20% DF CY 2019 (STIMULUS | Building |  | sq.m | MLGU | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Fund transferred to LGU March 28, 2019
Carmen | Cebulano | 2nd Eng'g. Dist. | On-going | 2019-08-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Carmen | Cebulano | 2nd Eng'g. Dist. | On-going | 2019-08-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Carmen | Cebulano | 2nd Eng'g. Dist. | On-going | 2019-08-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Carmen | Cebulano | 2nd Eng'g. Dist. | On-going | 2019-08-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Allotment Released: | 2019-02-20 | Date completed:
Carmen | Cebulano | 2nd Eng'g. Dist. | On-going | 2019-08-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Started: | 2019-08-16
Panabo City | Kasilak | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | Rehab. Of Multi-Purpose Hall, Kasilak, Panabo City |  | 20% DF CY 2019 (STIMULUS | Building |  |  | Contract | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | PO #2020041509 - JJR CONSTRUCTION AND SUPPLY
Panabo City | Kasilak | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Panabo City | Kasilak | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Panabo City | Kasilak | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Panabo City | Kasilak | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Panabo City | Kasilak | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Started:
Panabo City | New Malitbog | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | Rehab. Of Multi-Purpose Hall, New Malitbog, Panabo City |  | 20% DF CY 2019 (STIMULUS | Building |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Amended in AIP 3rd revsion CY 2019 to change the project to Construction of Potable Water System because the original project will be funded by LGU, Panabo City (Brgy. resolution no. 25 series of 2019 dated Aug. 13, 2019 submitted)
Panabo City | New Malitbog | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Panabo City | New Malitbog | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Panabo City | New Malitbog | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Panabo City | New Malitbog | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Panabo City | New Malitbog | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Started:
Panabo City | New Pandan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | Desilting of Canal, New Pandan, Panabo City |  | 20% DF CY 2019 (STIMULUS | Desiltation |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
Panabo City | New Pandan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Panabo City | New Pandan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Panabo City | New Pandan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Panabo City | New Pandan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Panabo City | New Pandan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Started:
Panabo City | Waterfall | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | Const. Of Multi-Purpose Hall, Waterfall, Panabo City |  | 20% DF CY 2019 (STIMULUS | Building |  |  | Contract | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Abstract #0520201797
Panabo City | Waterfall | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Panabo City | Waterfall | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Panabo City | Waterfall | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Panabo City | Waterfall | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Panabo City | Waterfall | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Started:
Panabo City | Cagangohan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | Concreting of Brgy. Road @ Prk. Guyabano, Cagangohan, Panabo City |  | 20% DF CY 2019 (STIMULUS | Concreting |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Amended in AIP 3rd revision to change the project to Rehab of Evacuation Center because the original project has no deed of donation.(Brgy. resolution no 41 series of 2019 dated Aug. 16, 2019 submitted
Panabo City | Cagangohan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Panabo City | Cagangohan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Panabo City | Cagangohan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Panabo City | Cagangohan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Panabo City | Cagangohan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Started:
Panabo City | J.P Laurel | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | Rehab. Of Evacuation Center, J.P. Laurel, Panabo City |  | 20% DF CY 2019 (STIMULUS | Building |  |  | Contract | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Purchase Order # 2020031248- DIGOS CONSTRAK
Panabo City | J.P Laurel | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Panabo City | J.P Laurel | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Panabo City | J.P Laurel | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Panabo City | J.P Laurel | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Allotment Released: | 2019-10-23 | Date completed:
Panabo City | J.P Laurel | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Started:
Panabo City | Buenavista | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | Const. Of Multi-Purpose Hall, Buenavista, Panabo City |  | 20% DF CY 2019 (STIMULUS | Building |  |  | Contract | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Purchase Order # 2020031248- DIGOS CONSTRAK
Panabo City | Buenavista | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Panabo City | Buenavista | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Panabo City | Buenavista | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Panabo City | Buenavista | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Allotment Released: | 2019-10-18 | Date completed:
Panabo City | Buenavista | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Started:
Panabo City | San Francisco | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | Rehab. Of Multi-Purpose Hall, San Francisco, Panabo City |  | 20% DF CY 2019 (STIMULUS | Building |  |  | Contract | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Purchase Order # 2020031248- DIGOS CONSTRAK
Panabo City | San Francisco | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Panabo City | San Francisco | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Panabo City | San Francisco | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Panabo City | San Francisco | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Allotment Released: | 2019-10-18 | Date completed:
Panabo City | San Francisco | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Started:
Panabo City | Datu Abdul | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | Rehab. Of Evacuation Center, Datu Abdul Dadia, Panabo City |  | 20% DF CY 2019 (STIMULUS | Building |  |  | Contract | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Purchase Order # 2020031248- DIGOS CONSTRAK
Panabo City | Datu Abdul | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Panabo City | Datu Abdul | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Panabo City | Datu Abdul | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Panabo City | Datu Abdul | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Allotment Released: | 2019-10-18 | Date completed:
Panabo City | Datu Abdul | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Started:
Panabo City | Quezon | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | Impv't./Beautification of Brgy. Grounds, Quezon, Panabo City |  | 20% DF CY 2019 (STIMULUS | Ground dev't. |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Re aligned to other stimulus projects that needs additional funding
Panabo City | Quezon | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Panabo City | Quezon | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Panabo City | Quezon | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Panabo City | Quezon | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Panabo City | Quezon | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Started:
Panabo City | Gredu | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | Const. of Women Livelihood Center Bldg. , Gredu, Panabo City |  | 20% DF CY 2019 (STIMULUS | Building |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Fund transfer to LGU - 3/28/2019 with check no. 2574926 and OR no. 0166517 - March 28, 2019
Panabo City | Gredu | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Panabo City | Gredu | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Panabo City | Gredu | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Panabo City | Gredu | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Allotment Released: | 2019-03-28 | Date completed:
Panabo City | Gredu | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Started:
Panabo City | Salvacion | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | Const. of Canal Lining at Purok 5, Salvacion, Panabo City |  | 20% DF CY 2019 (STIMULUS | Building |  |  | Contract | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | PO #2020041516- DANIMERH CONSTRUCTION & SUPPLY
Panabo City | Salvacion | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Panabo City | Salvacion | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Panabo City | Salvacion | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Panabo City | Salvacion | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Allotment Released: | 2019-10-18 | Date completed:
Panabo City | Salvacion | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Started:
Panabo City | New Visayas | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | Rehab. Of Health Center, New Visayas, Panabo City |  | 20% DF CY 2019 (STIMULUS | Building |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Re aligned to other stimulus projects that needs additional funding
Panabo City | New Visayas | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Panabo City | New Visayas | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Panabo City | New Visayas | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Panabo City | New Visayas | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Panabo City | New Visayas | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Started:
Panabo City | Little Panay | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | Rehab. Of Multi-Purpose Hall, Little Panay, Panabo City |  | 20% DF CY 2019 (STIMULUS | Building |  |  | Contract | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Abstract #0520201796
Panabo City | Little Panay | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Panabo City | Little Panay | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Panabo City | Little Panay | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Panabo City | Little Panay | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Panabo City | Little Panay | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Started:
Panabo City | Dalisay | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | Rehab. Of Brgy. Health Center, Dalisay, Panabo City |  | 20% DF CY 2019 (STIMULUS | Building |  |  | Contract | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Abstract #0520201798
Panabo City | Dalisay | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Panabo City | Dalisay | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Panabo City | Dalisay | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Panabo City | Dalisay | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Panabo City | Dalisay | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Started:
Panabo City | Southern Davao | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | Const. of Multi-Purpose Hall, Southern Davao, Panabo City |  | 20% DF CY 2019 (STIMULUS | Building |  |  | Contract | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Abstract #0520201798
Panabo City | Southern Davao | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Panabo City | Southern Davao | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Panabo City | Southern Davao | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Panabo City | Southern Davao | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Panabo City | Southern Davao | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Started:
Sto. Tomas | Casig-ang | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | Rehab. Of Evacuation Center, Casig-ang, Sto. Tomas |  | 20% DF CY 2019 (STIMULUS | Building |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | PR #20063670
Sto. Tomas | Casig-ang | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Sto. Tomas | Casig-ang | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Sto. Tomas | Casig-ang | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Sto. Tomas | Casig-ang | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Sto. Tomas | Casig-ang | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Started:
Sto. Tomas | Tibal-og | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | Const. of Brgy. Tibal-og Health Center, Tibal-og, Sto. Tomas |  | 20% DF CY 2019 (STIMULUS | Building |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | POW preparation completed amounting t oP1,550,000.00. To request for additional funds in order to complete the project to be functional
Sto. Tomas | Tibal-og | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Sto. Tomas | Tibal-og | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Sto. Tomas | Tibal-og | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Sto. Tomas | Tibal-og | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Sto. Tomas | Tibal-og | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Started:
Sto. Tomas | La Libertad | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | Compl.of Brgy. Public Market, La Libertad, Sto. Tomas |  | 20% DF CY 2019 (STIMULUS | Building |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Fund transfer to LGU - 6/26/219 with check no. 2575131 and OR no. 0557457 Completed/ PCR for submission by LGU
Sto. Tomas | La Libertad | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Sto. Tomas | La Libertad | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Sto. Tomas | La Libertad | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Sto. Tomas | La Libertad | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Sto. Tomas | La Libertad | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Started:
Sto. Tomas | New Visayas | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | Rehab. Of Evacuation Center, New Visayas, Sto. Tomas |  | 20% DF CY 2019 (STIMULUS | Building |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Fund transfer to LGU - 6/26/219 with check no. 2575132 and OR no. 0557455 For implementation
Sto. Tomas | New Visayas | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Sto. Tomas | New Visayas | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Sto. Tomas | New Visayas | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Sto. Tomas | New Visayas | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Sto. Tomas | New Visayas | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Started:
Sto. Tomas | San Vicente | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | Rehab. Of Multi-Purpose Hall, San Vicente, Sto. Tomas |  | 20% DF CY 2019 (STIMULUS | Building |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Fund transferred to LGU July 5, 2019
Sto. Tomas | San Vicente | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Project Engineer: | 0 | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Sto. Tomas | San Vicente | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Sto. Tomas | San Vicente | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Sto. Tomas | San Vicente | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Sto. Tomas | San Vicente | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Started:
Sto. Tomas | Salvacion | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | Rehab. Of Multi-Purpose Hall, Salvacion, Sto. Tomas |  | 20% DF CY 2019 (STIMULUS | Building |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
Sto. Tomas | Salvacion | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Sto. Tomas | Salvacion | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Sto. Tomas | Salvacion | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Sto. Tomas | Salvacion | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Sto. Tomas | Salvacion | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Started:
Sto. Tomas | Pantaron | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | Rehab. Of Multi-Purpose Hall, Pantaron, Sto. Tomas |  | 20% DF CY 2019 (STIMULUS | Building |  |  |  | Project Cost: |  | Target Completion Date: |  | Program: | 0 | Planned: |  | No. of Persons: |  | Amended in AIP 3rd revision CY 2019 / SB No. 4 CY 2019 increasing the project cost to P550,000.00
Sto. Tomas | Pantaron | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 0 | Revised: |  | No. of Man-days:
Sto. Tomas | Pantaron | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Sto. Tomas | Pantaron | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Sto. Tomas | Pantaron | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Sto. Tomas | Pantaron | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Started:
Sto. Tomas | Magwawa | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | Rehab. Of Multi-Purpose Hall, Magwawa, Sto. Tomas |  | 20% DF CY 2019 (STIMULUS | Building |  |  | Contract | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | For implementation - Awarded to JJR CONSTRUCTION AND SUPPLY
Sto. Tomas | Magwawa | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Sto. Tomas | Magwawa | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Sto. Tomas | Magwawa | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Sto. Tomas | Magwawa | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Allotment Released: | June 19 2019 | Date completed:
Sto. Tomas | Magwawa | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Started:
Sto. Tomas | San Jose | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | Compl. Of Multi-Purpose Hall, San Jose, Sto. Tomas |  | 20% DF CY 2019 (STIMULUS | Building |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Amended in AIP 3rd revision CY 2019 / SB No. 4 CY 2019 increasing the project cost to P600,000.00
Sto. Tomas | San Jose | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Sto. Tomas | San Jose | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Sto. Tomas | San Jose | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Sto. Tomas | San Jose | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Sto. Tomas | San Jose | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Started:
Sto. Tomas | Bobongon | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | Const. of Evacuation Center, Bobongon, Sto. Tomas |  | 20% DF CY 2019 (STIMULUS | Building |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Re aligned to other stimulus projects that needs additional funding
Sto. Tomas | Bobongon | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Sto. Tomas | Bobongon | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Sto. Tomas | Bobongon | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Sto. Tomas | Bobongon | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Sto. Tomas | Bobongon | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Started:
Sto. Tomas | Lunga-og | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | Rehab. Of Brgy. Road, Lunga-og, Sto. Tomas |  | 20% DF CY 2019 (STIMULUS | Building |  |  |  | Project Cost: |  | Target Completion Date: |  | Program: | 0 | Planned: |  | No. of Persons: |  | Amended in AIP 3rd revision CY 2019 / SB No. 4 CY 2019 increasing the project cost to P600,000.00
Sto. Tomas | Lunga-og | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 0 | Revised: |  | No. of Man-days:
Sto. Tomas | Lunga-og | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Sto. Tomas | Lunga-og | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Sto. Tomas | Lunga-og | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Sto. Tomas | Lunga-og | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Started:
Sto. Tomas | New Katipunan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | Rehab. Of Multi-Purpose Hall, New Katipunan, Sto. Tomas |  | 20% DF CY 2019 (STIMULUS | Building |  |  | Contract | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Abstract #0520201798 - Digos Constrak
Sto. Tomas | New Katipunan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Sto. Tomas | New Katipunan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Sto. Tomas | New Katipunan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Sto. Tomas | New Katipunan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Allotment Released: | 2019-06-07 | Date completed:
Sto. Tomas | New Katipunan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Started:
Sto. Tomas | San Miguel | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | Rehab. Of Multi-Purpose Hall, San Miguel, Sto. Tomas |  | 20% DF CY 2019 (STIMULUS | Building |  |  | Contract | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | PO #2020041509 - JJR CONSTRUCTION AND SUPPLY
Sto. Tomas | San Miguel | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Sto. Tomas | San Miguel | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Sto. Tomas | San Miguel | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Sto. Tomas | San Miguel | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Allotment Released: | 2019-06-07 | Date completed:
Sto. Tomas | San Miguel | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Started:
Sto. Tomas | Talomo | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | Rehab. Of Multi-Purpose Hall, Talomo, Sto. Tomas |  | 20% DF CY 2019 (STIMULUS | Building |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Fund transfer to LGU - 6/26/2019 with check no. 2575130 and OR no. 0557456 For implementation
Sto. Tomas | Talomo | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Sto. Tomas | Talomo | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Sto. Tomas | Talomo | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Sto. Tomas | Talomo | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Sto. Tomas | Talomo | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Started:
IGCS | Catagman | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | Concreting of Brgy. Road From Prk. 3 to Prk. 5, Catagman, IGCS |  | 20% DF CY 2019 (STIMULUS | Concreting |  |  | Contract | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | For implementation
IGCS | Catagman | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
IGCS | Catagman | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
IGCS | Catagman | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
IGCS | Catagman | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Allotment Released: | 2019-01-14 | Date completed:
IGCS | Catagman | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Started:
IGCS | Bandera | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | Electrification at Sitio Trinidad, Bandera, IGCS |  | 20% DF CY 2019 (STIMULUS | Electrification |  |  | Contract | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | PO #2020072352 - (3E Electrical Sales & Services)
IGCS | Bandera | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
IGCS | Bandera | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
IGCS | Bandera | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
IGCS | Bandera | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Allotment Released: | 2019-03-25 | Date completed:
IGCS | Bandera | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Started:
IGCS | Del Monte | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | Rehab. Of Multi-Purpose Hall, Del Monte, IGCS |  | 20% DF CY 2019 (STIMULUS | Building |  |  | Admin | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Pending/ activity undertaken by DPWH
IGCS | Del Monte | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
IGCS | Del Monte | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
IGCS | Del Monte | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
IGCS | Del Monte | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Allotment Released: | 2019-05-29 | Date completed:
IGCS | Del Monte | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Started:
IGCS | Tagbaobo | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | Electrification at Upper Purok Rosal, Tagbaobo, IGCS |  | 20% DF CY 2019 (STIMULUS | Electrification |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Purchase Order # 2020010002 (3E Electrical Sales & Services)
IGCS | Tagbaobo | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
IGCS | Tagbaobo | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
IGCS | Tagbaobo | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
IGCS | Tagbaobo | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
IGCS | Tagbaobo | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Started:
IGCS | Mambago-B | 2nd Eng'g. Dist. | On-going | 2019-10-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | Const. Of Multi-Purpose Hall, Mambago-B, IGCS |  | 20% DF CY 2019 (STIMULUS | Building |  | sq.m | Admin | Project Cost: | 500000 | Target Completion Date: | 2019-12-27 | Program: | 500000 | Planned: | 100% | No. of Persons: | 5 | On-going
IGCS | Mambago-B | 2nd Eng'g. Dist. | On-going | 2019-10-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Project Engineer: | Roque | Revised Completion Date: | 2020-03-29 | Allotment: | 500000 | Revised: | 99.48% | No. of Man-days: | 22
IGCS | Mambago-B | 2nd Eng'g. Dist. | On-going | 2019-10-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Implementor: | PEO | No. of days suspended: | 29 | Disbursement: |  | Actual: | 97.59%
IGCS | Mambago-B | 2nd Eng'g. Dist. | On-going | 2019-10-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Duration: | 70 | No. of days extended: | 64 |  |  | Slippage: | -1.89%
IGCS | Mambago-B | 2nd Eng'g. Dist. | On-going | 2019-10-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
IGCS | Mambago-B | 2nd Eng'g. Dist. | On-going | 2019-10-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Started: | 2019-10-18
IGCS | San Antonio | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | Const. Of Multi-Purpose Hall, San Antonio, IGCS |  | 20% DF CY 2019 (STIMULUS | Building |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | For implementation
IGCS | San Antonio | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
IGCS | San Antonio | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
IGCS | San Antonio | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
IGCS | San Antonio | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Allotment Released: | 2019-06-19 | Date completed:
IGCS | San Antonio | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Started:
IGCS | Pangubatan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | Rehab. Of Water System Intake Box and Pipeline, Pangubatan, IGCS |  | 20% DF CY 2019 (STIMULUS | Water System |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Plan and Pow completed. Waiting of deed of donation
IGCS | Pangubatan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
IGCS | Pangubatan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
IGCS | Pangubatan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
IGCS | Pangubatan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
IGCS | Pangubatan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Started:
IGCS | Cogon | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | Const. Of Multi-Purpose Hall, Cogon (Talicud), IGCS |  | 20% DF CY 2019 (STIMULUS | Building |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | For implementation
IGCS | Cogon | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
IGCS | Cogon | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
IGCS | Cogon | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
IGCS | Cogon | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
IGCS | Cogon | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Started:
IGCS | Libertad | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | Installation of Pipelines, Libertad, IGCS |  | 20% DF CY 2019 (STIMULUS | Pipelines |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | For implementation
IGCS | Libertad | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
IGCS | Libertad | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
IGCS | Libertad | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
IGCS | Libertad | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Allotment Released: | 2019-03-25 | Date completed:
IGCS | Libertad | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Started:
IGCS | Libuak | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | Rehab. Of Evacuation Center, Libuak, IGCS |  | 20% DF CY 2019 (STIMULUS | Building |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | For implementation
IGCS | Libuak | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
IGCS | Libuak | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
IGCS | Libuak | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
IGCS | Libuak | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Allotment Released: | 2019-05-29 | Date completed:
IGCS | Libuak | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Started:
IGCS | Kaputian | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | Const. of Water System Project, Pob. Kaputian, IGCS |  | 20% DF CY 2019 (STIMULUS | Water System |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | For implementation
IGCS | Kaputian | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
IGCS | Kaputian | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
IGCS | Kaputian | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
IGCS | Kaputian | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
IGCS | Kaputian | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Started:
Babak, IGCS | San Isidro | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | Rehab. Of Potable Water System, San Isidro, Babak, IGCS |  | 20% DF CY 2019 (STIMULUS | Water System |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | For implementation
Babak, IGCS | San Isidro | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Babak, IGCS | San Isidro | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Babak, IGCS | San Isidro | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Babak, IGCS | San Isidro | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Allotment Released: | 2019-06-19 | Date completed:
Babak, IGCS | San Isidro | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Started:
IGCS | San Miguel | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | Rehab. Of Potable Water System, San Miguel, IGCS |  | 20% DF CY 2019 (STIMULUS | Water System |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | For implementation
IGCS | San Miguel | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
IGCS | San Miguel | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
IGCS | San Miguel | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
IGCS | San Miguel | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Allotment Released: | 2019-02-28 | Date completed:
IGCS | San Miguel | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Started:
IGCS | San Remegio | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | Const. of Water System Ph.II, San Remegio, IGCS |  | 20% DF CY 2019 (STIMULUS | Water System |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | For implementation
IGCS | San Remegio | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
IGCS | San Remegio | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
IGCS | San Remegio | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
IGCS | San Remegio | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Allotment Released: | 2019-05-29 | Date completed:
IGCS | San Remegio | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Started:
IGCS | Licup | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | Electrificatio at Prk. 1,3,4, 6,7 & 8, Licup, IGCS |  | 20% DF CY 2019 (STIMULUS | Electrification |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | For implementation
IGCS | Licup | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
IGCS | Licup | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
IGCS | Licup | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
IGCS | Licup | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Allotment Released: | 2019-02-20 | Date completed:
IGCS | Licup | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Started:
IGCS | Kaputian | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Rural Electrification Project (Provincewide) | Rural Electrification at Sitio Sagrada, Pob. Kaputian, IGCS |  | 20% DF CY 2019 | Electrification |  |  |  | Project Cost: | 1000000 | Target Completion Date: |  | Program: | 1000000 | Planned: |  | No. of Persons: |  | Purchase Request # 19031251
IGCS | Kaputian | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Rural Electrification Project (Provincewide) | [7 empty] | Project Engineer: | Buena | Revised Completion Date: |  | Allotment: | 1000000 | Revised: |  | No. of Man-days:
IGCS | Kaputian | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Rural Electrification Project (Provincewide) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
IGCS | Kaputian | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Rural Electrification Project (Provincewide) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
IGCS | Kaputian | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Rural Electrification Project (Provincewide) | [7 empty] | Date Allotment Released: |  | Date completed:
IGCS | Kaputian | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Rural Electrification Project (Provincewide) | [7 empty] | Date Started:
Carmen | Tuganay | 2nd Eng'g. Dist. | On-going | 2009-08-19 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Revitment of Dike and Slope Proection | Repair/Rehab. Of Upper Tuganay Dike |  | 5% CALAMITY FUND CY 2019 | Dike |  | ln.m | Admin | Project Cost: | 1000000 | Target Completion Date: | 2019-09-29 | Program: | 1000000 | Planned: | 90% | No. of Persons: | 9 | On-going
Carmen | Tuganay | 2nd Eng'g. Dist. | On-going | 2009-08-19 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Revitment of Dike and Slope Proection | [7 empty] | Project Engineer: | Toquero | Revised Completion Date: |  | Allotment: | 1000000 | Revised: |  | No. of Man-days: | 80
Carmen | Tuganay | 2nd Eng'g. Dist. | On-going | 2009-08-19 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Revitment of Dike and Slope Proection | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: | 90%
Carmen | Tuganay | 2nd Eng'g. Dist. | On-going | 2009-08-19 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Revitment of Dike and Slope Proection | [7 empty] | Duration: | 41 | No. of days extended: |  |  |  | Slippage: | 0%
Carmen | Tuganay | 2nd Eng'g. Dist. | On-going | 2009-08-19 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Revitment of Dike and Slope Proection | [7 empty] | Date Allotment Released: | 2019-08-15 | Date completed:
Carmen | Tuganay | 2nd Eng'g. Dist. | On-going | 2009-08-19 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Revitment of Dike and Slope Proection | [7 empty] | Date Started: | 2019-08-19
Carmen | Ising | 2nd Eng'g. Dist. | Completed | 2019-11-15 | 2020-06-30 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPLAN CANAL | Repair of Damaged Drainage/ Creek along Abucay Creek |  | 5% CALAMITY FUND | Creek |  | ln.m | Admin | Project Cost: | 1320000 | Target Completion Date: | 2019-12-05 | Program: | 1320000 | Planned: | 100% | No. of Persons: |  | Completed as per physical accomplishment. Financial documents still on process.
Carmen | Ising | 2nd Eng'g. Dist. | Completed | 2019-11-15 | 2020-06-30 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPLAN CANAL | [7 empty] | Project Engineer: | Ganaba | Revised Completion Date: | 2020-06-04 | Allotment: | 1320000 | Revised: |  | No. of Man-days:
Carmen | Ising | 2nd Eng'g. Dist. | Completed | 2019-11-15 | 2020-06-30 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPLAN CANAL | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: | 100%
Carmen | Ising | 2nd Eng'g. Dist. | Completed | 2019-11-15 | 2020-06-30 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPLAN CANAL | [7 empty] | Duration: | 65 | No. of days extended: | 182 |  |  | Slippage: | 0%
Carmen | Ising | 2nd Eng'g. Dist. | Completed | 2019-11-15 | 2020-06-30 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPLAN CANAL | [7 empty] | Date Allotment Released: |  | Date completed: | 2020-06-30
Carmen | Ising | 2nd Eng'g. Dist. | Completed | 2019-11-15 | 2020-06-30 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPLAN CANAL | [7 empty] | Date Started: | 2019-10-01
Carmen | Ising | 2nd Eng'g. Dist. | On-going | 2019-11-15 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPLAN CANAL | Repair of Damaged Drainage Creek along Panabo River |  | 5% CALAMITY FUND | Creek |  | ln.m | Admin | Project Cost: | 665000 | Target Completion Date: | 2020-01-27 | Program: | 665000 | Planned: | 100% | No. of Persons: | 3 | On-going
Carmen | Ising | 2nd Eng'g. Dist. | On-going | 2019-11-15 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPLAN CANAL | [7 empty] | Project Engineer: | Alconera | Revised Completion Date: |  | Allotment: | 665000 | Revised: |  | No. of Man-days: | 66
Carmen | Ising | 2nd Eng'g. Dist. | On-going | 2019-11-15 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPLAN CANAL | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: | 15.3%
Carmen | Ising | 2nd Eng'g. Dist. | On-going | 2019-11-15 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPLAN CANAL | [7 empty] | Duration: | 73 | No. of days extended: |  |  |  | Slippage: | -84.7%
Carmen | Ising | 2nd Eng'g. Dist. | On-going | 2019-11-15 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPLAN CANAL | [7 empty] | Date Allotment Released: |  | Date completed:
Carmen | Ising | 2nd Eng'g. Dist. | On-going | 2019-11-15 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPLAN CANAL | [7 empty] | Date Started: | 2019-11-15
Carmen | Ising | 2nd Eng'g. Dist. | On-going | 2019-11-15 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPLAN CANAL | Repair of Damaged Drainage/Creek along Tuganay-Ising River |  | 5% CALAMITY FUND | Creek |  | ln.m | Admin | Project Cost: | 1540500 | Target Completion Date: | 2020-05-15 | Program: | 1540500 | Planned: | 25.6% | No. of Persons: | 3 | On-going
Carmen | Ising | 2nd Eng'g. Dist. | On-going | 2019-11-15 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPLAN CANAL | [7 empty] | Project Engineer: | Ganaba | Revised Completion Date: |  | Allotment: | 1540500 | Revised: |  | No. of Man-days: | 66
Carmen | Ising | 2nd Eng'g. Dist. | On-going | 2019-11-15 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPLAN CANAL | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: | 23.6%
Carmen | Ising | 2nd Eng'g. Dist. | On-going | 2019-11-15 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPLAN CANAL | [7 empty] | Duration: | 182 | No. of days extended: |  |  |  | Slippage: | -2%
Carmen | Ising | 2nd Eng'g. Dist. | On-going | 2019-11-15 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPLAN CANAL | [7 empty] | Date Allotment Released: |  | Date completed:
Carmen | Ising | 2nd Eng'g. Dist. | On-going | 2019-11-15 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPLAN CANAL | [7 empty] | Date Started: | 2019-11-15
Panabo City | Lasang | 2nd Eng'g. Dist. | Completed | 2019-08-01 | 2020-05-28 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPLAN CANAL | Repair of Damaged Drainage/ Creeks along San Miguel NIA Road |  | 5% CALAMITY FUND | Creek |  | ln.m | Admin | Project Cost: | 470000 | Target Completion Date: | 2019-09-16 | Program: | 470000 | Planned: | 100% | No. of Persons: | 3 | Completed as per physical accomplishment. Financial documents still on process.
Panabo City | Lasang | 2nd Eng'g. Dist. | Completed | 2019-08-01 | 2020-05-28 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPLAN CANAL | [7 empty] | Project Engineer: | Nasol | Revised Completion Date: | 2020-05-28 | Allotment: | 470000 | Revised: |  | No. of Man-days: | 66
Panabo City | Lasang | 2nd Eng'g. Dist. | Completed | 2019-08-01 | 2020-05-28 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPLAN CANAL | [7 empty] | Implementor: | PEO | No. of days suspended: | 255 | Disbursement: |  | Actual: | 100%
Panabo City | Lasang | 2nd Eng'g. Dist. | Completed | 2019-08-01 | 2020-05-28 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPLAN CANAL | [7 empty] | Duration: | 46 | No. of days extended: |  |  |  | Slippage: | 0%
Panabo City | Lasang | 2nd Eng'g. Dist. | Completed | 2019-08-01 | 2020-05-28 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPLAN CANAL | [7 empty] | Date Allotment Released: |  | Date completed: | 2020-05-28
Panabo City | Lasang | 2nd Eng'g. Dist. | Completed | 2019-08-01 | 2020-05-28 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPLAN CANAL | [7 empty] | Date Started: | 2019-08-01
Carmen | Ising | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPLAN CANAL | Repair of Damaged Drainage/ Creeks along Sadpodon Creek |  | 5% CALAMITY FUND | Creek |  |  | Admin | Project Cost: | 470000 | Target Completion Date: |  | Program: | 470000 | Planned: |  | No. of Persons: |  | For implementation
Carmen | Ising | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPLAN CANAL | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 470000 | Revised: |  | No. of Man-days:
Carmen | Ising | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPLAN CANAL | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual:
Carmen | Ising | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPLAN CANAL | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Carmen | Ising | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPLAN CANAL | [7 empty] | Date Allotment Released: |  | Date completed:
Carmen | Ising | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPLAN CANAL | [7 empty] | Date Started:
B.E. Dujali | Pawas | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Local Roads & Drainage Development Project Construction in Progress- Infrastructure Assets | Rehabilitation of Dujali-Pawas-San Vicente Provincial Road, B.E. Dujali |  | SB # 3 CY 2019 | Road |  |  |  | Project Cost: | 2000000 | Target Completion Date: |  | Program: | 2000000 | Planned: |  | No. of Persons: |  | The amount was reduced to P1,102,900.00
B.E. Dujali | Pawas | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Local Roads & Drainage Development Project Construction in Progress- Infrastructure Assets | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 2000000 | Revised: |  | No. of Man-days:
B.E. Dujali | Pawas | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Local Roads & Drainage Development Project Construction in Progress- Infrastructure Assets | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
B.E. Dujali | Pawas | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Local Roads & Drainage Development Project Construction in Progress- Infrastructure Assets | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
B.E. Dujali | Pawas | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Local Roads & Drainage Development Project Construction in Progress- Infrastructure Assets | [7 empty] | Date Allotment Released: |  | Date completed:
B.E. Dujali | Pawas | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Local Roads & Drainage Development Project Construction in Progress- Infrastructure Assets | [7 empty] | Date Started:
Samal | Mambago-A | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VariousWater System Development Project Construction in Progress- Infrastructure Assets | Improvement of Potable Water System at Brgy. Mambago- A, Samal District, IGACOS |  | SB # 3 CY 2019 | Water System |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | (Amended in the AIP 2nd Revision to change the location from Peñaplata to Samal District) PO approved September 2, 2019
Samal | Mambago-A | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VariousWater System Development Project Construction in Progress- Infrastructure Assets | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Samal | Mambago-A | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VariousWater System Development Project Construction in Progress- Infrastructure Assets | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Samal | Mambago-A | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VariousWater System Development Project Construction in Progress- Infrastructure Assets | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Samal | Mambago-A | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VariousWater System Development Project Construction in Progress- Infrastructure Assets | [7 empty] | Date Allotment Released: |  | Date completed:
Samal | Mambago-A | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VariousWater System Development Project Construction in Progress- Infrastructure Assets | [7 empty] | Date Started:
Samal | San Miguel | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VariousWater System Development Project Construction in Progress- Infrastructure Assets | Rehabilitation of Potable Water System at Brgy. San Miguel, Samal District, IGACOS |  | SB # 3 CY 2019 | Water System |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | For implementation
Samal | San Miguel | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VariousWater System Development Project Construction in Progress- Infrastructure Assets | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Samal | San Miguel | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VariousWater System Development Project Construction in Progress- Infrastructure Assets | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Samal | San Miguel | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VariousWater System Development Project Construction in Progress- Infrastructure Assets | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Samal | San Miguel | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VariousWater System Development Project Construction in Progress- Infrastructure Assets | [7 empty] | Date Allotment Released: |  | Date completed:
Samal | San Miguel | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VariousWater System Development Project Construction in Progress- Infrastructure Assets | [7 empty] | Date Started:
Kaputian, IGCS | Linusotan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VariousWater System Development Project Construction in Progress- Infrastructure Assets | Construction of Potable Water System at Brgy.Linusotan, Kaputian District, IGACOS |  | SB # 3 CY 2019 | Water System |  |  |  | Project Cost: | 1300000 | Target Completion Date: |  | Program: | 1300000 | Planned: |  | No. of Persons: |  | (Additional 800,000.00 from Const. of PWS in purok 2, Pag-asa, Kapalong which was funded by OPAPP CY 2018) (amended) For allotment- October 15, 2019
Kaputian, IGCS | Linusotan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VariousWater System Development Project Construction in Progress- Infrastructure Assets | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 1300000 | Revised: |  | No. of Man-days:
Kaputian, IGCS | Linusotan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VariousWater System Development Project Construction in Progress- Infrastructure Assets | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Kaputian, IGCS | Linusotan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VariousWater System Development Project Construction in Progress- Infrastructure Assets | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Kaputian, IGCS | Linusotan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VariousWater System Development Project Construction in Progress- Infrastructure Assets | [7 empty] | Date Allotment Released: |  | Date completed:
Kaputian, IGCS | Linusotan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VariousWater System Development Project Construction in Progress- Infrastructure Assets | [7 empty] | Date Started:
Carmen | Ising | 2nd Eng'g. Dist. | Completed | 2019-07-29 | 2019-11-11 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DISASTER REHABILITATION & RECOVERY PROGRAM Building Back Better Project | Disiltation of Mactan River (Ph. II) |  | 5% Calamity Fund CY 2019 | Desiltation |  | ln.m |  | Project Cost: | 500000 | Target Completion Date: | 2019-09-27 | Program: | 500000 | Planned: | 100% | No. of Persons: |  | Completed as per physical accomplishment. Financial documents still on process.
Carmen | Ising | 2nd Eng'g. Dist. | Completed | 2019-07-29 | 2019-11-11 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DISASTER REHABILITATION & RECOVERY PROGRAM Building Back Better Project | [7 empty] | Project Engineer: | Toquero | Revised Completion Date: | 2019-11-11 | Allotment: | 500000 | Revised: |  | No. of Man-days:
Carmen | Ising | 2nd Eng'g. Dist. | Completed | 2019-07-29 | 2019-11-11 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DISASTER REHABILITATION & RECOVERY PROGRAM Building Back Better Project | [7 empty] | Implementor: | PEO | No. of days suspended: | 45 | Disbursement: |  | Actual: | 100%
Carmen | Ising | 2nd Eng'g. Dist. | Completed | 2019-07-29 | 2019-11-11 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DISASTER REHABILITATION & RECOVERY PROGRAM Building Back Better Project | [7 empty] | Duration: | 60 | No. of days extended: |  |  |  | Slippage: | 0%
Carmen | Ising | 2nd Eng'g. Dist. | Completed | 2019-07-29 | 2019-11-11 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DISASTER REHABILITATION & RECOVERY PROGRAM Building Back Better Project | [7 empty] | Date Allotment Released: | 2019-05-28 | Date completed: | 2019-11-11
Carmen | Ising | 2nd Eng'g. Dist. | Completed | 2019-07-29 | 2019-11-11 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DISASTER REHABILITATION & RECOVERY PROGRAM Building Back Better Project | [7 empty] | Date Started: | 2019-07-29
B.E. Dujali | Magupising | 2nd Eng'g. Dist. | Completed | 2019-12-02 | 2020-06-15 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DISASTER REHABILITATION & RECOVERY PROGRAM Building Back Better Project | Rehabilitation of Dujali-Balisong-Magupising Provincial Road |  | 5% Calamity Fund CY 2019 | Rehabilitation |  | km | Admin | Project Cost: | 1280000 | Target Completion Date: | 2020-02-03 | Program: | 1280000 | Planned: | 100% | No. of Persons: |  | Completed as per physical accomplishment. Financial documents still on process.
B.E. Dujali | Magupising | 2nd Eng'g. Dist. | Completed | 2019-12-02 | 2020-06-15 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DISASTER REHABILITATION & RECOVERY PROGRAM Building Back Better Project | [7 empty] | Project Engineer: | Mellomida | Revised Completion Date: | 2020-06-15 | Allotment: | 1280000 | Revised: | 100% | No. of Man-days:
B.E. Dujali | Magupising | 2nd Eng'g. Dist. | Completed | 2019-12-02 | 2020-06-15 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DISASTER REHABILITATION & RECOVERY PROGRAM Building Back Better Project | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: |  | Actual: | 100%
B.E. Dujali | Magupising | 2nd Eng'g. Dist. | Completed | 2019-12-02 | 2020-06-15 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DISASTER REHABILITATION & RECOVERY PROGRAM Building Back Better Project | [7 empty] | Duration: | 63 | No. of days extended: | 106 |  |  | Slippage: | 0%
B.E. Dujali | Magupising | 2nd Eng'g. Dist. | Completed | 2019-12-02 | 2020-06-15 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DISASTER REHABILITATION & RECOVERY PROGRAM Building Back Better Project | [7 empty] | Date Allotment Released: |  | Date completed: | 2020-06-15
B.E. Dujali | Magupising | 2nd Eng'g. Dist. | Completed | 2019-12-02 | 2020-06-15 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DISASTER REHABILITATION & RECOVERY PROGRAM Building Back Better Project | [7 empty] | Date Started: | 2019-12-02
Sto. Tomas | Magwawa | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PEACE AND ORDER PROGRAM/1914 Construction in Progress- Land Improvements | Rehabilitation of San Jose- Sitio Mahayahay-Magwawa Provincial Road, Sto. Tomas |  | SB # 4 CY 2019 | Road |  |  |  | Project Cost: | 1000000 | Target Completion Date: |  | Program: | 1000000 | Planned: |  | No. of Persons: |  | POW preparation on-going c/o South District
Sto. Tomas | Magwawa | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PEACE AND ORDER PROGRAM/1914 Construction in Progress- Land Improvements | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 1000000 | Revised: |  | No. of Man-days:
Sto. Tomas | Magwawa | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PEACE AND ORDER PROGRAM/1914 Construction in Progress- Land Improvements | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Sto. Tomas | Magwawa | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PEACE AND ORDER PROGRAM/1914 Construction in Progress- Land Improvements | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Sto. Tomas | Magwawa | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PEACE AND ORDER PROGRAM/1914 Construction in Progress- Land Improvements | [7 empty] | Date Allotment Released: |  | Date completed:
Sto. Tomas | Magwawa | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PEACE AND ORDER PROGRAM/1914 Construction in Progress- Land Improvements | [7 empty] | Date Started:
Panabo City | Dalisay | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Local Roads and Drainage Development Project Construction in Progress- Infrastructure Assets | Rehabilitation of Local Roads at Dalisay-Manay Road Section, Panabo City |  | SB # 4 CY 2019 | Road |  |  | Admin | Project Cost: | 246100 | Target Completion Date: |  | Program: | 246100 | Planned: |  | No. of Persons: |  | For implementation
Panabo City | Dalisay | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Local Roads and Drainage Development Project Construction in Progress- Infrastructure Assets | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 246100 | Revised: |  | No. of Man-days:
Panabo City | Dalisay | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Local Roads and Drainage Development Project Construction in Progress- Infrastructure Assets | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Panabo City | Dalisay | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Local Roads and Drainage Development Project Construction in Progress- Infrastructure Assets | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Panabo City | Dalisay | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Local Roads and Drainage Development Project Construction in Progress- Infrastructure Assets | [7 empty] | Date Allotment Released: |  | Date completed:
Panabo City | Dalisay | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Local Roads and Drainage Development Project Construction in Progress- Infrastructure Assets | [7 empty] | Date Started:
Panabo City | Buenavista | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Local Roads and Drainage Development Project Construction in Progress- Infrastructure Assets | Rehabilitation of Local Roads at Sta. Cruz-Jct. Tagpore-Buenavista Raod Section, Panabo City |  | SB # 4 CY 2019 | Road |  |  | Admin | Project Cost: | 431000 | Target Completion Date: |  | Program: | 431000 | Planned: |  | No. of Persons: |  | For implementation
Panabo City | Buenavista | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Local Roads and Drainage Development Project Construction in Progress- Infrastructure Assets | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 431000 | Revised: |  | No. of Man-days:
Panabo City | Buenavista | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Local Roads and Drainage Development Project Construction in Progress- Infrastructure Assets | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Panabo City | Buenavista | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Local Roads and Drainage Development Project Construction in Progress- Infrastructure Assets | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Panabo City | Buenavista | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Local Roads and Drainage Development Project Construction in Progress- Infrastructure Assets | [7 empty] | Date Allotment Released: |  | Date completed:
Panabo City | Buenavista | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Local Roads and Drainage Development Project Construction in Progress- Infrastructure Assets | [7 empty] | Date Started:
Carmen | Taba | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Local Roads and Drainage Development Project Construction in Progress- Infrastructure Assets | Rehabilitation of Local Roads at Taba-Bucana Road Section, Taba, Carmen |  | SB # 4 CY 2019 | Road |  |  | Admin | Project Cost: | 220000 | Target Completion Date: |  | Program: | 220000 | Planned: |  | No. of Persons: |  | For implementation
Carmen | Taba | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Local Roads and Drainage Development Project Construction in Progress- Infrastructure Assets | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 220000 | Revised: |  | No. of Man-days:
Carmen | Taba | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Local Roads and Drainage Development Project Construction in Progress- Infrastructure Assets | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Carmen | Taba | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Local Roads and Drainage Development Project Construction in Progress- Infrastructure Assets | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Carmen | Taba | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Local Roads and Drainage Development Project Construction in Progress- Infrastructure Assets | [7 empty] | Date Allotment Released: |  | Date completed:
Carmen | Taba | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Local Roads and Drainage Development Project Construction in Progress- Infrastructure Assets | [7 empty] | Date Started:
B.E. Dujali | Dujali | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | Concreting of Brgy. Road Canal, Dujali, B.E. Dujali |  | SB # 4 CY 2019 (STIMULUS | Concreting |  |  | Contract | Project Cost: | 650000 | Target Completion Date: |  | Program: | 650000 | Planned: |  | No. of Persons: |  | For implementation
B.E. Dujali | Dujali | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 650000 | Revised: |  | No. of Man-days:
B.E. Dujali | Dujali | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
B.E. Dujali | Dujali | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
B.E. Dujali | Dujali | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Date Allotment Released: |  | Date completed:
B.E. Dujali | Dujali | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Date Started:
B.E. Dujali | New Casay | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | Desilting and Conretign of Drainage-Main Collector Canal, New Casay, B.E. Dujali |  | SB # 4 CY 2019 (STIMULUS | Desiltation |  |  | Contract | Project Cost: | 650000 | Target Completion Date: |  | Program: | 650000 | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
B.E. Dujali | New Casay | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 650000 | Revised: |  | No. of Man-days:
B.E. Dujali | New Casay | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
B.E. Dujali | New Casay | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
B.E. Dujali | New Casay | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Date Allotment Released: |  | Date completed:
B.E. Dujali | New Casay | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Date Started:
B.E. Dujali | Tanglaw | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | Concreting of Drainage, Tanglaw, B.E., Dujali |  | SB # 4 CY 2019 (STIMULUS | Desiltation |  |  | Contract | Project Cost: | 1200000 | Target Completion Date: |  | Program: | 1200000 | Planned: |  | No. of Persons: |  | For implementation
B.E. Dujali | Tanglaw | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 1200000 | Revised: |  | No. of Man-days:
B.E. Dujali | Tanglaw | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
B.E. Dujali | Tanglaw | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
B.E. Dujali | Tanglaw | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Date Allotment Released: |  | Date completed:
B.E. Dujali | Tanglaw | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Date Started:
Panabo City | New Malitbog | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | Construction of Potable Water System, New Malitbog, Panabo City |  | SB # 4 CY 2019 (STIMULUS | Water System |  |  | Contract | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
Panabo City | New Malitbog | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Panabo City | New Malitbog | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Panabo City | New Malitbog | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Panabo City | New Malitbog | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Date Allotment Released: |  | Date completed:
Panabo City | New Malitbog | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Date Started:
Kaputian, IGCS | Poblacion | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | Construction of Water System Project, Poblacion Kaputian, Samal |  | SB # 4 CY 2019 (STIMULUS | Water System |  |  | Contract | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | For implementation
Kaputian, IGCS | Poblacion | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Kaputian, IGCS | Poblacion | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Kaputian, IGCS | Poblacion | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Kaputian, IGCS | Poblacion | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Date Allotment Released: |  | Date completed:
Kaputian, IGCS | Poblacion | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Date Started:
Panabo City | salvacion | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | Construction of Canal Lining at Prk. 5, Salvacion, Panabo City |  | SB # 4 CY 2019 (STIMULUS | Canal lining |  |  | Contract | Project Cost: | 600000 | Target Completion Date: |  | Program: | 600000 | Planned: |  | No. of Persons: |  | For implementation
Panabo City | salvacion | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 600000 | Revised: |  | No. of Man-days:
Panabo City | salvacion | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Panabo City | salvacion | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Panabo City | salvacion | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Date Allotment Released: |  | Date completed:
Panabo City | salvacion | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Date Started:
Sto. Tomas | Lunga-og | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | Rehabilitation of Brgy. Road at Lunga-og. Sto. Tomas |  | SB # 4 CY 2019 (STIMULUS | Road |  |  | Contract | Project Cost: | 600000 | Target Completion Date: |  | Program: | 600000 | Planned: |  | No. of Persons: |  | For implementation
Sto. Tomas | Lunga-og | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 600000 | Revised: |  | No. of Man-days:
Sto. Tomas | Lunga-og | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Sto. Tomas | Lunga-og | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Sto. Tomas | Lunga-og | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Date Allotment Released: |  | Date completed:
Sto. Tomas | Lunga-og | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Date Started:
Carmen | Sto. Niño | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | Construction of Evacuation Center at Purok 1-C Brgy. Sto. Niño, Carmen |  | SB # 4 CY 2019 (STIMULUS | Building |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | For implementation
Carmen | Sto. Niño | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Carmen | Sto. Niño | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Carmen | Sto. Niño | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Carmen | Sto. Niño | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Date Allotment Released: |  | Date completed:
Carmen | Sto. Niño | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Date Started:
Panabo City | Waterfall | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | Construction of Multi-Purpose Hall, Waterfall, Panabo City |  | SB # 4 CY 2019 (STIMULUS | Building |  |  |  | Project Cost: | 1050000 | Target Completion Date: |  | Program: | 1050000 | Planned: |  | No. of Persons: |  | For implementation
Panabo City | Waterfall | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 1050000 | Revised: |  | No. of Man-days:
Panabo City | Waterfall | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Panabo City | Waterfall | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Panabo City | Waterfall | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Date Allotment Released: |  | Date completed:
Panabo City | Waterfall | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Date Started:
Panabo City | San Francisco | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | Rehabilitation of Multi-Purpose Hall, San Francisco, Panabo City |  | SB # 4 CY 2019 (STIMULUS | Building |  |  |  | Project Cost: | 600000 | Target Completion Date: |  | Program: | 600000 | Planned: |  | No. of Persons: |  | For implementation
Panabo City | San Francisco | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 600000 | Revised: |  | No. of Man-days:
Panabo City | San Francisco | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Panabo City | San Francisco | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Panabo City | San Francisco | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Date Allotment Released: |  | Date completed:
Panabo City | San Francisco | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Date Started:
Panabo City | Datu Abdul | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | Rehabilitation of Evacuation Center at Datu Abdul Dadia, Panabo City |  | SB # 4 CY 2019 (STIMULUS | Building |  |  |  | Project Cost: | 650000 | Target Completion Date: |  | Program: | 650000 | Planned: |  | No. of Persons: |  | For implementation
Panabo City | Datu Abdul | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 650000 | Revised: |  | No. of Man-days:
Panabo City | Datu Abdul | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Panabo City | Datu Abdul | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Panabo City | Datu Abdul | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Date Allotment Released: |  | Date completed:
Panabo City | Datu Abdul | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Date Started:
Panabo City | Buenavista | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | Construction of Multi-Purpose Hall, Buenavista, Panabo City |  | SB # 4 CY 2019 (STIMULUS | Building |  |  |  | Project Cost: | 1050000 | Target Completion Date: |  | Program: | 1050000 | Planned: |  | No. of Persons: |  | For implementation
Panabo City | Buenavista | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 1050000 | Revised: |  | No. of Man-days:
Panabo City | Buenavista | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Panabo City | Buenavista | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Panabo City | Buenavista | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Date Allotment Released: |  | Date completed:
Panabo City | Buenavista | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Date Started:
Panabo City | Little Panay | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | Rehabilitation of Multi-Purpose Hall, Llittle Panay, Panabo City |  | SB # 4 CY 2019 (STIMULUS | Building |  |  |  | Project Cost: | 550000 | Target Completion Date: |  | Program: | 550000 | Planned: |  | No. of Persons: |  | For implementation
Panabo City | Little Panay | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 550000 | Revised: |  | No. of Man-days:
Panabo City | Little Panay | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Panabo City | Little Panay | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Panabo City | Little Panay | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Date Allotment Released: |  | Date completed:
Panabo City | Little Panay | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Date Started:
Sto. Tomas | Pantaron | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | Rehabilitation of Multi-Purpose Hall, Pantaron, Sto. Tomas |  | SB # 4 CY 2019 (STIMULUS | Building |  |  |  | Project Cost: | 550000 | Target Completion Date: |  | Program: | 550000 | Planned: |  | No. of Persons: |  | For implementation
Sto. Tomas | Pantaron | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 550000 | Revised: |  | No. of Man-days:
Sto. Tomas | Pantaron | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Sto. Tomas | Pantaron | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Sto. Tomas | Pantaron | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Date Allotment Released: |  | Date completed:
Sto. Tomas | Pantaron | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Date Started:
Sto. Tomas | salvacion | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | Rehabilitation of Multi-Purpose Hall, Salvacion, Sto. Tomas |  | SB # 4 CY 2019 (STIMULUS | Building |  |  |  | Project Cost: | 1000000 | Target Completion Date: |  | Program: | 1000000 | Planned: |  | No. of Persons: |  | PR #20032281
Sto. Tomas | salvacion | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 1000000 | Revised: |  | No. of Man-days:
Sto. Tomas | salvacion | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Sto. Tomas | salvacion | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Sto. Tomas | salvacion | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Date Allotment Released: |  | Date completed:
Sto. Tomas | salvacion | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Date Started:
Sto. Tomas | San Jose | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | Completion of Multi-Purpose Hall, San Jose, Sto. Tomas |  | SB # 4 CY 2019 (STIMULUS | Building |  |  |  | Project Cost: | 600000 | Target Completion Date: |  | Program: | 600000 | Planned: |  | No. of Persons: |  | For implementation
Sto. Tomas | San Jose | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 600000 | Revised: |  | No. of Man-days:
Sto. Tomas | San Jose | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Sto. Tomas | San Jose | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Sto. Tomas | San Jose | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Date Allotment Released: |  | Date completed:
Sto. Tomas | San Jose | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Date Started:
Panabo City | Kasilak | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | Rehabilitation of Multi-Purpose Hall, Kasilak, Panabo City |  | SB # 4 CY 2019 (STIMULUS | Building |  |  |  | Project Cost: | 650000 | Target Completion Date: |  | Program: | 650000 | Planned: |  | No. of Persons: |  | For implementation
Panabo City | Kasilak | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 650000 | Revised: |  | No. of Man-days:
Panabo City | Kasilak | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Panabo City | Kasilak | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Panabo City | Kasilak | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Date Allotment Released: |  | Date completed:
Panabo City | Kasilak | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Date Started:
Panabo City | Dalisay | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | Rehabilitation of Brgy. Health Center, Dalisay, Panabo City |  | SB # 4 CY 2019 (STIMULUS | Building |  |  |  | Project Cost: | 550000 | Target Completion Date: |  | Program: | 550000 | Planned: |  | No. of Persons: |  | For implementation
Panabo City | Dalisay | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 550000 | Revised: |  | No. of Man-days:
Panabo City | Dalisay | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Panabo City | Dalisay | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Panabo City | Dalisay | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Date Allotment Released: |  | Date completed:
Panabo City | Dalisay | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Date Started:
Panabo City | Kiotoy | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | Rehabilitation of Evacuation Center, Kiotoy, Panabo City |  | SB # 4 CY 2019 (STIMULUS | Building |  |  |  | Project Cost: | 650000 | Target Completion Date: |  | Program: | 650000 | Planned: |  | No. of Persons: |  | For implementation
Panabo City | Kiotoy | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 650000 | Revised: |  | No. of Man-days:
Panabo City | Kiotoy | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Panabo City | Kiotoy | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Panabo City | Kiotoy | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Date Allotment Released: |  | Date completed:
Panabo City | Kiotoy | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Date Started:
Panabo City | Cagangohan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | Rehabilitation of Evacuation Center, Cagangohan, Panabo City |  | SB # 4 CY 2019 (STIMULUS | Building |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Abstract #0520201798 - Digos constrak
Panabo City | Cagangohan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Panabo City | Cagangohan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Panabo City | Cagangohan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Panabo City | Cagangohan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Date Allotment Released: |  | Date completed:
Panabo City | Cagangohan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Date Started:
IGCS | Tagpopongan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | Rehabilitation of Multi-Purpose Bldg. (Brgy. Hall) Tagpopongan, IGACOS |  | SB # 4 CY 2019 (STIMULUS | Building |  |  |  | Project Cost: | 174460.33 | Target Completion Date: |  | Program: | 174460.33 | Planned: |  | No. of Persons: |  | Procurement on process
IGCS | Tagpopongan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 174460.33 | Revised: |  | No. of Man-days:
IGCS | Tagpopongan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
IGCS | Tagpopongan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
IGCS | Tagpopongan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Date Allotment Released: |  | Date completed:
IGCS | Tagpopongan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Date Started:
Sto. Tomas | Balagunan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | Construction of Multi-Purpose Building, Balagunan, Sto. Tomas |  | SB # 4 CY 2019 (STIMULUS | Building |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | For implementation
Sto. Tomas | Balagunan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Sto. Tomas | Balagunan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Sto. Tomas | Balagunan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Sto. Tomas | Balagunan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Date Allotment Released: |  | Date completed:
Sto. Tomas | Balagunan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Date Started:
Carmen | La Paz | 2nd Eng'g. Dist. | On-going |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CMGP | Road Upgrading of Sto Nino - Kabankalan - La Paz Provincial Road, Carmen |  | CMGP CY 2019 | Road |  | km | Contract | Project Cost: | 44461624.67 | Target Completion Date: | 2020-05-15 23:59 | Program: | 44461624.67 | Planned: | 76.36% | No. of Persons: | 42 | On-going
Carmen | La Paz | 2nd Eng'g. Dist. | On-going |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CMGP | [7 empty] | Project Engineer: | Comidoy | Revised Completion Date: | 2020-07-20 23:59 | Allotment: | 44461624.67 | Revised: |  | No. of Man-days: | 610
Carmen | La Paz | 2nd Eng'g. Dist. | On-going |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CMGP | [7 empty] | Implementor: | GP & H CONST. | No. of days suspended: | 66 | Disbursement: | 6684253.05 | Actual: | 95.75%
Carmen | La Paz | 2nd Eng'g. Dist. | On-going |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CMGP | [7 empty] | Duration: | 222 | No. of days extended: |  |  |  | Slippage: | 19.39%
Carmen | La Paz | 2nd Eng'g. Dist. | On-going |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CMGP | [7 empty] | Date Allotment Released: | CY 2019 | Date completed:
Carmen | La Paz | 2nd Eng'g. Dist. | On-going |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CMGP | [7 empty] | Date Started: | 2019-10-07
Carmen | La Paz | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CMGP | Road Upgrading of Jct Highway - Sto Nino - La Paz - San Vicenter Provincial Road, Carmen |  | CMGP CY 2019 | Road |  | km | Contract | Project Cost: | 80481331.34 | Target Completion Date: | 2020-06-22 | Program: | 80481331.34 | Planned: | 94.91% | No. of Persons: | 40 | On-going | 94.91
Carmen | La Paz | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CMGP | [7 empty] | Project Engineer: | Fernandez | Revised Completion Date: | 2020-08-04 | Allotment: | 80481331.34 | Revised: |  | No. of Man-days: | 660
Carmen | La Paz | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CMGP | [7 empty] | Implementor: | Tagum Builders | No. of days suspended: | 43 | Disbursement: | 45481609.97 | Actual: | 94.79%
Carmen | La Paz | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CMGP | [7 empty] | Duration: | 259 | No. of days extended: |  |  |  | Slippage: | -0.12%
Carmen | La Paz | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CMGP | [7 empty] | Date Allotment Released: | CY 2019 | Date completed:
Carmen | La Paz | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CMGP | [7 empty] | Date Started: | 2019-10-07
Carmen | Mangalcal | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | 0 | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 073 - Cebulano - Mangalcal |  | GENERAL FUND CY 2020 | Maintenance | 4.17 | km | MBA | Project Cost: | 134672.7 | Target Completion Date: | 2020-12-31 23:59 | Program: | 134672.7 | Planned: | 50% | No. of Persons: | 64 | On-going
Carmen | Mangalcal | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Gamad/Clar | Revised Completion Date: |  | Allotment: | 134672.7 | Revised: |  | No. of Man-days: | 1280
Carmen | Mangalcal | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: | 51%
Carmen | Mangalcal | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 1%
Carmen | Mangalcal | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
Carmen | Mangalcal | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started: | 2020-01-02
Carmen | Mangalcal | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 073 - Cebulano - Mangalcal |  | GENERAL FUND CY 2020 | Maintenance | 4.17 | km | CBRMC | Project Cost: | 131004.66 | Target Completion Date: | 2020-11-11 | Program: | 131004.66 | Planned: | 5% | No. of Persons: |  | On-going
Carmen | Mangalcal | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Maligro | Revised Completion Date: |  | Allotment: | 131004.66 | Revised: |  | No. of Man-days:
Carmen | Mangalcal | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: | Brgy. Mangalcal Women's Household | No. of days suspended: |  | Disbursement: |  | Actual: | 5%
Carmen | Mangalcal | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: | 180 | No. of days extended: |  |  |  | Slippage: | 0%
Carmen | Mangalcal | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
Carmen | Mangalcal | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started: | 2020-05-15
Carmen | Tubod | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 074 - Tubod - basa - Mangalcal |  | GENERAL FUND CY 2020 | Maintenance | 3.93 | km | MBA | Project Cost: | 143530.25 | Target Completion Date: | 2020-12-31 23:59 | Program: | 143530.25 | Planned: | 50% | No. of Persons: | 3 | On-going
Carmen | Tubod | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Gamad/Clar | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 143530.25 | Revised: |  | No. of Man-days: | 66
Carmen | Tubod | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: |  | Actual: | 52%
Carmen | Tubod | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 2%
Carmen | Tubod | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
Carmen | Tubod | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started: | 2020-01-02
Carmen | Tubod | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 074 - Tubod - basa - Mangalcal |  | GENERAL FUND CY 2020 | Maintenance | 3.93 | km | CBRMC | Project Cost: | 106856.33 | Target Completion Date: | 2020-11-25 23:59 | Program: | 106856.33 | Planned: | 5% | No. of Persons: | 2 | On-going
Carmen | Tubod | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Maligro | Revised Completion Date: |  | Allotment: | 106856.33 | Revised: |  | No. of Man-days: | 2
Carmen | Tubod | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: | Tubod Centro Lower Irrigator's Association | No. of days suspended: |  | Disbursement: |  | Actual: | 5%
Carmen | Tubod | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: | 185 | No. of days extended: |  |  |  | Slippage: | 0%
Carmen | Tubod | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
Carmen | Tubod | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started: | 2020-05-25
Carmen | Tubod | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 078 - Upper Mangalcal - Lower Mangalcal |  | GENERAL FUND CY 2020 | Maintenance | 2.43 | km | MBA | Project Cost: | 82374.21 | Target Completion Date: | 2020-12-31 23:59 | Program: | 82374.21 | Planned: | 50% | No. of Persons: | 3 | On-going
Carmen | Tubod | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Gamad/Clar | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 82374.21 | Revised: |  | No. of Man-days: | 66
Carmen | Tubod | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: |  | Actual: | 55%
Carmen | Tubod | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 5%
Carmen | Tubod | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
Carmen | Tubod | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started: | 2020-01-02
Carmen | Mangalcal | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 078 - Upper Mangalcal - Lower Mangalcal |  | GENERAL FUND CY 2020 | Maintenance | 2.43 | km | CBRMC | Project Cost: | 72444.97 | Target Completion Date: | 2020-11-15 23:59 | Program: | 72444.97 | Planned: | 5% | No. of Persons: | 2 | On-going
Carmen | Mangalcal | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Maligro | Revised Completion Date: |  | Allotment: | 72444.97 | Revised: |  | No. of Man-days: | 2
Carmen | Mangalcal | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: | Brgy. Mangalcal Women's Homebased Association | No. of days suspended: |  | Disbursement: |  | Actual: | 5%
Carmen | Mangalcal | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: | 185 | No. of days extended: |  |  |  | Slippage: | 0%
Carmen | Mangalcal | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
Carmen | Mangalcal | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started: | 2020-05-15
Carmen | Cebulano | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 079 - Cebulano - Loceta |  | GENERAL FUND CY 2020 | Maintenance |  | km | MBA | Project Cost: | 72051.43 | Target Completion Date: | 2020-12-31 23:59 | Program: | 72051.43 | Planned: | 30% | No. of Persons: | 3 | On-going
Carmen | Cebulano | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Gamad/Clar | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 72051.43 | Revised: |  | No. of Man-days: | 66
Carmen | Cebulano | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: |  | Actual: | 54%
Carmen | Cebulano | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 24%
Carmen | Cebulano | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
Carmen | Cebulano | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started: | 2020-01-02
Carmen | Cebulano | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 079 - Cebulano - Loceta |  | GENERAL FUND CY 2020 | Maintenance |  | km | CBRMC | Project Cost: | 47089.26 | Target Completion Date: | 2020-11-15 23:59 | Program: | 47089.26 | Planned: | 5% | No. of Persons: | 2 | On-going
Carmen | Cebulano | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Maligro | Revised Completion Date: |  | Allotment: | 47089.26 | Revised: |  | No. of Man-days: | 2
Carmen | Cebulano | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: | Brgy. Mangalcal Women's Homebased Association | No. of days suspended: |  | Disbursement: |  | Actual: | 5%
Carmen | Cebulano | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: | 185 | No. of days extended: |  |  |  | Slippage: | 0%
Carmen | Cebulano | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
Carmen | Cebulano | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started: | 2020-05-15
Carmen | Tubod | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 082 - Jct. Highway Carmen - Mangalcal - Tubod |  | GENERAL FUND CY 2020 | Maintenance | 11.34 | km | MBA | Project Cost: | 462895.06 | Target Completion Date: | 2020-12-31 23:59 | Program: | 462895.06 | Planned: | 50% | No. of Persons: | 4 | On-going
Carmen | Tubod | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Gamad/Clar | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 462895.06 | Revised: |  | No. of Man-days: | 88
Carmen | Tubod | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: |  | Actual: | 50%
Carmen | Tubod | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0%
Carmen | Tubod | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
Carmen | Tubod | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started: | 2020-01-02
Carmen | Tubod | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 082 - Jct. Highway Carmen - Mangalcal - Tubod |  | GENERAL FUND CY 2020 | Maintenance | 11.34 | km | CBRMC | Project Cost: | 259594.46 | Target Completion Date: |  | Program: | 259594.46 | Planned: |  | No. of Persons: |  | PO #2020031403 - Awarded to TUBOD CENTRO LOWER IRRIGATORS ASS'T (TUCLIA)
Carmen | Tubod | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Maligro | Revised Completion Date: |  | Allotment: | 259594.46 | Revised: |  | No. of Man-days:
Carmen | Tubod | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Carmen | Tubod | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Carmen | Tubod | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: |  | Date completed:
Carmen | Tubod | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started:
Carmen | Taba | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 086 - Ising - Sadpodon - Taba - Dila -Dila |  | GENERAL FUND CY 2020 | Maintenance | 5.68 | km | MBA | Project Cost: | 226651.27 | Target Completion Date: | 2020-12-31 23:59 | Program: | 226651.27 | Planned: | 50% | No. of Persons: | 3 | On-going
Carmen | Taba | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Gamad/Clar | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 226651.27 | Revised: |  | No. of Man-days: | 66
Carmen | Taba | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: |  | Actual: | 50%
Carmen | Taba | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0%
Carmen | Taba | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
Carmen | Taba | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started: | 2020-01-02
Carmen | Taba | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 086 - Ising - Sadpodon - Taba - Dila -Dila |  | GENERAL FUND CY 2020 | Maintenance | 5.68 | km | CBRMC | Project Cost: | 135230.61 | Target Completion Date: |  | Program: | 135230.61 | Planned: | 50% | No. of Persons: |  | PO #2020031408 - Awarded to TABA COCONUT FARMERS ORGANIZATION
Carmen | Taba | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Maligro | Revised Completion Date: |  | Allotment: | 135230.61 | Revised: |  | No. of Man-days:
Carmen | Taba | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: | 55%
Carmen | Taba | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 5%
Carmen | Taba | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: |  | Date completed:
Carmen | Taba | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started:
Carmen | Tuganay | 2nd Eng'g. Dist. | For Implementation | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 087 - Tuganay - taba |  | GENERAL FUND CY 2020 | Maintenance | 4.27 | km | MBA | Project Cost: | 169418.15 | Target Completion Date: | 2020-12-31 23:59 | Program: | 169418.15 | Planned: | 52% | No. of Persons: | 3 | On-going
Carmen | Tuganay | 2nd Eng'g. Dist. | For Implementation | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Gamad/Clar | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 169418.15 | Revised: |  | No. of Man-days: | 66
Carmen | Tuganay | 2nd Eng'g. Dist. | For Implementation | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: |  | Actual: | 52%
Carmen | Tuganay | 2nd Eng'g. Dist. | For Implementation | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0%
Carmen | Tuganay | 2nd Eng'g. Dist. | For Implementation | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
Carmen | Tuganay | 2nd Eng'g. Dist. | For Implementation | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started: | 2020-01-02
Carmen | Tuganay | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 087 - Tuganay - taba |  | GENERAL FUND CY 2020 | Maintenance | 4.27 | km | CBRMC | Project Cost: | 102630.37 | Target Completion Date: |  | Program: | 102630.37 | Planned: |  | No. of Persons: |  | PO #2020031406 - TABA COCONUT FARMERS ORGANIZATION
Carmen | Tuganay | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Maligro | Revised Completion Date: |  | Allotment: | 102630.37 | Revised: |  | No. of Man-days:
Carmen | Tuganay | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Carmen | Tuganay | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Carmen | Tuganay | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: |  | Date completed:
Carmen | Tuganay | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started:
Carmen | Tuganay | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 088 - Jct. Highway Tuganay - Taba |  | GENERAL FUND CY 2020 | Maintenance | 4.4 | km | MBA | Project Cost: | 222375.04 | Target Completion Date: | 2020-12-31 23:59 | Program: | 222375.04 | Planned: | 50% | No. of Persons: | 3 | On-going
Carmen | Tuganay | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Gamad/Clar | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 222375.04 | Revised: |  | No. of Man-days: | 66
Carmen | Tuganay | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: |  | Actual: | 51%
Carmen | Tuganay | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 1%
Carmen | Tuganay | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
Carmen | Tuganay | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started: | 2020-01-02
Carmen | Tuganay | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 088 - Jct. Highway Tuganay - Taba |  | GENERAL FUND CY 2020 | Maintenance | 4.4 | km | CBRMC | Project Cost: | 57955.99 | Target Completion Date: | 2020-11-13 23:59 | Program: | 57955.99 | Planned: | 5% | No. of Persons: | 2 | On-going
Carmen | Tuganay | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Maligro | Revised Completion Date: |  | Allotment: | 57955.99 | Revised: |  | No. of Man-days: | 2
Carmen | Tuganay | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: | Ezra Christian Minsitry For Peace, Inc. | No. of days suspended: |  | Disbursement: |  | Actual: | 5%
Carmen | Tuganay | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: | 185 | No. of days extended: |  |  |  | Slippage: | 0%
Carmen | Tuganay | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
Carmen | Tuganay | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started: | 2020-05-13
Carmen | Ising | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 089 - Jct. Highway Ising - Magsaysay |  | GENERAL FUND CY 2020 | Maintenance | 10.84 | km | MBA | Project Cost: | 478128.48 | Target Completion Date: | 2020-12-31 23:59 | Program: | 478128.48 | Planned: | 50% | No. of Persons: | 3 | On-going
Carmen | Ising | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Gamad/Clar | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 478128.48 | Revised: |  | No. of Man-days: | 66
Carmen | Ising | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: |  | Actual: | 50%
Carmen | Ising | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0%
Carmen | Ising | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
Carmen | Ising | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started: | 2020-01-02
Carmen | Ising | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 089 - Jct. Highway Ising - Magsaysay |  | GENERAL FUND CY 2020 | Maintenance | 10.84 | km | CBRMC | Project Cost: | 212505.24 | Target Completion Date: | 2020-11-14 23:59 | Program: | 212505.24 | Planned: | 5% | No. of Persons: | 2 | On-going
Carmen | Ising | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Maligro | Revised Completion Date: |  | Allotment: | 212505.24 | Revised: |  | No. of Man-days: | 42
Carmen | Ising | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: | School in the Air Integrated Farmer's Associiation | No. of days suspended: |  | Disbursement: |  | Actual: | 5%
Carmen | Ising | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: | 185 | No. of days extended: |  |  |  | Slippage: | 0%
Carmen | Ising | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
Carmen | Ising | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started: | 2020-05-14
C armen | New Camiling | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 090 - Maligaya - New Camiling |  | GENERAL FUND CY 2020 | Maintenance |  | km | MBA | Project Cost: | 51790.26 | Target Completion Date: | 2020-12-31 23:59 | Program: | 51790.26 | Planned: | 50% | No. of Persons: | 3 | On-going
C armen | New Camiling | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Gamad/Clar | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 51790.26 | Revised: |  | No. of Man-days: | 66
C armen | New Camiling | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: |  | Actual: | 51%
C armen | New Camiling | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 1%
C armen | New Camiling | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
C armen | New Camiling | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started: | 2020-01-02
C armen | New Camiling | 2nd Eng'g. Dist. | On-going | 2020-05-14 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 090 - Maligaya - New Camiling |  | GENERAL FUND CY 2020 | Maintenance |  | km | CBRMC | Project Cost: | 83915.44 | Target Completion Date: | 2020-11-14 23:59 | Program: | 83915.44 | Planned: | 5% | No. of Persons: | 2 | On-going
C armen | New Camiling | 2nd Eng'g. Dist. | On-going | 2020-05-14 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Maligro | Revised Completion Date: |  | Allotment: | 83915.44 | Revised: |  | No. of Man-days: | 2
C armen | New Camiling | 2nd Eng'g. Dist. | On-going | 2020-05-14 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: | School in the Air Integrated Farmer's Associiation | No. of days suspended: |  | Disbursement: |  | Actual: | 5%
C armen | New Camiling | 2nd Eng'g. Dist. | On-going | 2020-05-14 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: | 185 | No. of days extended: |  |  |  | Slippage: | 0%
C armen | New Camiling | 2nd Eng'g. Dist. | On-going | 2020-05-14 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
C armen | New Camiling | 2nd Eng'g. Dist. | On-going | 2020-05-14 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started: | 2020-05-14
C armen | New Camiling | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 091 - New Camiling - Alejal - Lower Magsaysay |  | GENERAL FUND CY 2020 | Maintenance | 6.73 | km | MBA | Project Cost: | 277852.05 | Target Completion Date: | 2020-12-31 23:59 | Program: | 277852.05 | Planned: | 50% | No. of Persons: | 3 | On-going
C armen | New Camiling | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Gamad/Clar | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 277852.05 | Revised: |  | No. of Man-days: | 66
C armen | New Camiling | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: |  | Actual: | 50%
C armen | New Camiling | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0%
C armen | New Camiling | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
C armen | New Camiling | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started: | 2020-01-02
C armen | New Camiling | 2nd Eng'g. Dist. | On-going | 2020-05-14 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 091 - New Camiling - Alejal - Lower Magsaysay |  | GENERAL FUND CY 2020 | Maintenance | 6.73 | km | CBRMC | Project Cost: | 150927.01 | Target Completion Date: | 2020-11-14 23:59 | Program: | 150927.01 | Planned: | 5% | No. of Persons: |  | On-going
C armen | New Camiling | 2nd Eng'g. Dist. | On-going | 2020-05-14 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Maligro | Revised Completion Date: |  | Allotment: | 150927.01 | Revised: |  | No. of Man-days:
C armen | New Camiling | 2nd Eng'g. Dist. | On-going | 2020-05-14 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: | School in the Air Integrated Farmer's Association | No. of days suspended: |  | Disbursement: |  | Actual: | 5%
C armen | New Camiling | 2nd Eng'g. Dist. | On-going | 2020-05-14 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: | 185 | No. of days extended: |  |  |  | Slippage: | 0%
C armen | New Camiling | 2nd Eng'g. Dist. | On-going | 2020-05-14 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
C armen | New Camiling | 2nd Eng'g. Dist. | On-going | 2020-05-14 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started: | 2020-05-14
Carmen | Tuganay | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 094 - Jct. highway Tuganay - Anibongan |  | GENERAL FUND CY 2020 | Maintenance | 3.66 | km | MBA | Project Cost: | 139609.7 | Target Completion Date: | 2020-12-31 23:59 | Program: | 139609.7 | Planned: | 50% | No. of Persons: | 4 | On-going
Carmen | Tuganay | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Gamad/Clar | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 139609.7 | Revised: |  | No. of Man-days: | 88
Carmen | Tuganay | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: |  | Actual: | 55%
Carmen | Tuganay | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 5%
Carmen | Tuganay | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
Carmen | Tuganay | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started: | 2020-01-02
Carmen | Tuganay | 2nd Eng'g. Dist. | On-going | 2020-05-13 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 094 - Jct. highway Tuganay - Anibongan |  | GENERAL FUND CY 2020 | Maintenance | 3.66 | km | CBRMC | Project Cost: | 93574.75 | Target Completion Date: | 2020-11-13 23:59 | Program: | 93574.75 | Planned: | 5% | No. of Persons: |  | Purchase Order # 2020030977 (Ezra Christian Minsitry For Peace, Inc.)
Carmen | Tuganay | 2nd Eng'g. Dist. | On-going | 2020-05-13 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Maligro | Revised Completion Date: |  | Allotment: | 93574.75 | Revised: |  | No. of Man-days:
Carmen | Tuganay | 2nd Eng'g. Dist. | On-going | 2020-05-13 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: | Ezra Christian Minsitry For Peace, Inc. | No. of days suspended: |  | Disbursement: |  | Actual: | 5%
Carmen | Tuganay | 2nd Eng'g. Dist. | On-going | 2020-05-13 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: | 185 | No. of days extended: |  |  |  | Slippage: | 0%
Carmen | Tuganay | 2nd Eng'g. Dist. | On-going | 2020-05-13 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
Carmen | Tuganay | 2nd Eng'g. Dist. | On-going | 2020-05-13 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started: | 2020-05-13
Carmen | Anibongan | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 095 - Anibongan - Guadalupe |  | GENERAL FUND CY 2020 | Maintenance | 2.48 | km | MBA | Project Cost: | 85559.79 | Target Completion Date: | 2020-12-31 23:59 | Program: | 85559.79 | Planned: | 50% | No. of Persons: | 4 | On-going / Time extension on process due to suspension of activity
Carmen | Anibongan | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Gamad/Clar | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 85559.79 | Revised: |  | No. of Man-days: | 78
Carmen | Anibongan | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: |  | Actual: | 55%
Carmen | Anibongan | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 5%
Carmen | Anibongan | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
Carmen | Anibongan | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started: | 2020-01-02
Carmen | Anibongan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 095 - Anibongan - Guadalupe |  | GENERAL FUND CY 2020 | Maintenance | 2.48 | km | CBRMC | Project Cost: | 72444.97 | Target Completion Date: |  | Program: | 72444.97 | Planned: |  | No. of Persons: |  | PO #2020031404 - PRK 4. ANIBONGAN CARMENT IRRIGATORS ASSN.
Carmen | Anibongan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Maligro | Revised Completion Date: |  | Allotment: | 72444.97 | Revised: |  | No. of Man-days:
Carmen | Anibongan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Carmen | Anibongan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Carmen | Anibongan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: |  | Date completed:
Carmen | Anibongan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started:
Carmen | Tuganay | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 096 - Tuganay - Anibongan - San Isidro |  | GENERAL FUND CY 2020 | Maintenance | 7.22 | km | MBA | Project Cost: | 344085.79 | Target Completion Date: | 2020-12-31 23:59 | Program: | 344085.79 | Planned: | 50% | No. of Persons: | 3 | On-going
Carmen | Tuganay | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Gamad/Clar | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 344085.79 | Revised: |  | No. of Man-days: | 66
Carmen | Tuganay | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: |  | Actual: | 50%
Carmen | Tuganay | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0%
Carmen | Tuganay | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
Carmen | Tuganay | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started: | 2020-01-02
Carmen | Tuganay | 2nd Eng'g. Dist. | On-going | 2020-05-13 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 096 - Tuganay - Anibongan - San Isidro |  | GENERAL FUND CY 2020 | Maintenance | 7.22 | km | CBRMC | Project Cost: | 115911.95 | Target Completion Date: | 2020-11-13 23:59 | Program: | 115911.95 | Planned: | 5% | No. of Persons: |  | On-going
Carmen | Tuganay | 2nd Eng'g. Dist. | On-going | 2020-05-13 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Maligro | Revised Completion Date: |  | Allotment: | 115911.95 | Revised: |  | No. of Man-days:
Carmen | Tuganay | 2nd Eng'g. Dist. | On-going | 2020-05-13 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: | Ezra Christian Minsitry For Peace, Inc. | No. of days suspended: |  | Disbursement: |  | Actual: | 5%
Carmen | Tuganay | 2nd Eng'g. Dist. | On-going | 2020-05-13 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: | 185 | No. of days extended: |  |  |  | Slippage: | 0%
Carmen | Tuganay | 2nd Eng'g. Dist. | On-going | 2020-05-13 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: |  | Date completed:
Carmen | Tuganay | 2nd Eng'g. Dist. | On-going | 2020-05-13 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started: | 2020-05-13
Carmen | Anibongan | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 097 - Jct. Anibongan - Prk. 2, 7, 5, San Isidro |  | GENERAL FUND CY 2020 | Maintenance | 3.14 | km | MBA | Project Cost: | 89575.84 | Target Completion Date: | 2020-12-31 23:59 | Program: | 89575.84 | Planned: | 50% | No. of Persons: | 4 | On-going
Carmen | Anibongan | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Gamad/Clar | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 89575.84 | Revised: |  | No. of Man-days: | 88
Carmen | Anibongan | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: |  | Actual: | 53%
Carmen | Anibongan | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 3%
Carmen | Anibongan | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
Carmen | Anibongan | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started: | 2020-01-02
Carmen | Anibongan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 097 - Jct. Anibongan - Prk. 2, 7, 5, San Isidro |  | GENERAL FUND CY 2020 | Maintenance | 3.14 | km | CBRMC | Project Cost: | 110478.58 | Target Completion Date: |  | Program: | 110478.58 | Planned: |  | No. of Persons: |  | PO #2020031378 - SAN ISIDRO FARMERS IRRIGATORS ASSN.
Carmen | Anibongan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Maligro | Revised Completion Date: |  | Allotment: | 110478.58 | Revised: |  | No. of Man-days:
Carmen | Anibongan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Carmen | Anibongan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Carmen | Anibongan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: |  | Date completed:
Carmen | Anibongan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started:
Carmen | Anibongan | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 098 - Anibongan - Salvacion - Cabay-angan |  | GENERAL FUND CY 2020 | Maintenance | 6.93 | km | MBA | Project Cost: | 279123.9 | Target Completion Date: | 2020-12-31 23:59 | Program: | 279123.9 | Planned: | 50% | No. of Persons: | 4 | On-going
Carmen | Anibongan | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Gamad/Clar | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 279123.9 | Revised: |  | No. of Man-days: | 88
Carmen | Anibongan | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: |  | Actual: | 51%
Carmen | Anibongan | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 1%
Carmen | Anibongan | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
Carmen | Anibongan | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started: | 2020-01-02
Carmen | Anibongan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 098 - Anibongan - Salvacion - Cabay-angan |  | GENERAL FUND CY 2020 | Maintenance | 6.93 | km | CBRMC | Project Cost: | 162397.48 | Target Completion Date: |  | Program: | 162397.48 | Planned: |  | No. of Persons: |  | PO #2020031379 - PRK4. ANIBONGAN CARMEN IRRIGATORS ASS.
Carmen | Anibongan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Maligro | Revised Completion Date: |  | Allotment: | 162397.48 | Revised: |  | No. of Man-days:
Carmen | Anibongan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Carmen | Anibongan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Carmen | Anibongan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: |  | Date completed:
Carmen | Anibongan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started:
Carmen | Mabaus | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 099 - Mabaus - Cabay - angan |  | GENERAL FUND CY 2020 | Maintenance |  | km | MBA | Project Cost: | 113320.9 | Target Completion Date: | 2020-12-31 23:59 | Program: | 113320.9 | Planned: | 50% | No. of Persons: | 3 | On-going
Carmen | Mabaus | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Gamad/Clar | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 113320.9 | Revised: |  | No. of Man-days: | 66
Carmen | Mabaus | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: |  | Actual: | 54%
Carmen | Mabaus | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 4%
Carmen | Mabaus | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
Carmen | Mabaus | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started: | 2020-01-02
Carmen | Mabaus | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 099 - Mabaus - Cabay - angan |  | GENERAL FUND CY 2020 | Maintenance |  | km | CBRMC | Project Cost: | 90556.21 | Target Completion Date: |  | Program: | 90556.21 | Planned: |  | No. of Persons: |  | PO #2020031410 - LAMPIA PAG ASA IRRIGATORS ASS., INC.
Carmen | Mabaus | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Maligro | Revised Completion Date: |  | Allotment: | 90556.21 | Revised: |  | No. of Man-days:
Carmen | Mabaus | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Carmen | Mabaus | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Carmen | Mabaus | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: |  | Date completed:
Carmen | Mabaus | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started:
Carmen | Guadalupe | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 101 - Jct. Highway Guadalupe - Bdry. Tagum |  | GENERAL FUND CY 2020 | Maintenance | 7.9 | km | MBA | Project Cost: | 517780.87 | Target Completion Date: | 2020-12-31 23:59 | Program: | 517780.87 | Planned: | 50% | No. of Persons: | 3 | On-going
Carmen | Guadalupe | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Gamad/Clar | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 517780.87 | Revised: |  | No. of Man-days: | 66
Carmen | Guadalupe | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: |  | Actual: | 55%
Carmen | Guadalupe | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 5%
Carmen | Guadalupe | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
Carmen | Guadalupe | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started: | 2020-01-02
Carmen | Guadalupe | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 101 - Jct. Highway Guadalupe - Bdry. Tagum |  | GENERAL FUND CY 2020 | Maintenance | 7.9 | km | CBRMC | Project Cost: | 231823.89 | Target Completion Date: |  | Program: | 231823.89 | Planned: |  | No. of Persons: |  | PO #2020031376 - LAMPIA PAG ASA IRRIGATORS ASS., INC.
Carmen | Guadalupe | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Maligro | Revised Completion Date: |  | Allotment: | 231823.89 | Revised: |  | No. of Man-days:
Carmen | Guadalupe | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Carmen | Guadalupe | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Carmen | Guadalupe | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: |  | Date completed:
Carmen | Guadalupe | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started:
B.E. Dujali | Tanglaw | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 104 - Dujali - Tanglaw |  | GENERAL FUND CY 2020 | Maintenance |  | km | MBA | Project Cost: | 135183.27 | Target Completion Date: | 2020-12-31 23:59 | Program: | 135183.27 | Planned: | 50% | No. of Persons: | 3 | On-going
B.E. Dujali | Tanglaw | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Gamad/Clar | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 135183.27 | Revised: |  | No. of Man-days: | 66
B.E. Dujali | Tanglaw | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: |  | Actual: | 52%
B.E. Dujali | Tanglaw | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 2%
B.E. Dujali | Tanglaw | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
B.E. Dujali | Tanglaw | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started: | 2020-01-02
B.E. Dujali | Tanglaw | 2nd Eng'g. Dist. | On-going | 2020-06-08 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 104 - Dujali - Tanglaw |  | GENERAL FUND CY 2020 | Maintenance |  | km | CBRMC | Project Cost: | 94178.48 | Target Completion Date: | 2020-12-12 | Program: | 94178.48 | Planned: | 5% | No. of Persons: | 2 | On-going
B.E. Dujali | Tanglaw | 2nd Eng'g. Dist. | On-going | 2020-06-08 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Maligro | Revised Completion Date: | 2021-01-08 | Allotment: | 94178.48 | Revised: |  | No. of Man-days: | 2
B.E. Dujali | Tanglaw | 2nd Eng'g. Dist. | On-going | 2020-06-08 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: | Dujali Poblacion Farmer's Irrigator's Association, Inc. | No. of days suspended: | 27 | Disbursement: |  | Actual: | 5%
B.E. Dujali | Tanglaw | 2nd Eng'g. Dist. | On-going | 2020-06-08 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: | 187 | No. of days extended: |  |  |  | Slippage: | 0%
B.E. Dujali | Tanglaw | 2nd Eng'g. Dist. | On-going | 2020-06-08 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
B.E. Dujali | Tanglaw | 2nd Eng'g. Dist. | On-going | 2020-06-08 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started: | 2020-06-08
B.E. Dujali | Dujali | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 105 - Poblacion Dujali - Prk. 8 Dujali |  | GENERAL FUND CY 2020 | Maintenance | 8.2 | km | MBA | Project Cost: | 329064 | Target Completion Date: | 2020-12-31 23:59 | Program: | 329064 | Planned: | 50% | No. of Persons: | 3 | On-going
B.E. Dujali | Dujali | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Gamad/Clar | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 329064 | Revised: |  | No. of Man-days: | 66
B.E. Dujali | Dujali | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: |  | Actual: | 56%
B.E. Dujali | Dujali | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 6%
B.E. Dujali | Dujali | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
B.E. Dujali | Dujali | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started: | 2020-01-02
B.E. Dujali | Dujali | 2nd Eng'g. Dist. | On-going | 2020-06-08 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 105 - Poblacion Dujali - Prk. 8 Dujali |  | GENERAL FUND CY 2020 | Maintenance | 8.2 | km | CBRMC | Project Cost: | 193371.11 | Target Completion Date: | 2020-12-12 | Program: | 193371.11 | Planned: | 5% | No. of Persons: | 2 | On-going
B.E. Dujali | Dujali | 2nd Eng'g. Dist. | On-going | 2020-06-08 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Maligro | Revised Completion Date: | 2021-01-08 | Allotment: | 193371.11 | Revised: |  | No. of Man-days: | 2
B.E. Dujali | Dujali | 2nd Eng'g. Dist. | On-going | 2020-06-08 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: | Dujali Poblacion Farmer's Irrigator's Association, Inc. | No. of days suspended: | 27 | Disbursement: |  | Actual: | 5%
B.E. Dujali | Dujali | 2nd Eng'g. Dist. | On-going | 2020-06-08 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: | 187 | No. of days extended: |  |  |  | Slippage: | 0%
B.E. Dujali | Dujali | 2nd Eng'g. Dist. | On-going | 2020-06-08 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
B.E. Dujali | Dujali | 2nd Eng'g. Dist. | On-going | 2020-06-08 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started: | 2020-06-08
B.E. Dujali | Dujali | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 107 - Dujali - San Isidro |  | GENERAL FUND CY 2020 | Maintenance | 3 | km | MBA | Project Cost: | 112652.73 | Target Completion Date: | 2020-12-31 23:59 | Program: | 112652.73 | Planned: | 50% | No. of Persons: | 3 | On-going
B.E. Dujali | Dujali | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Gamad/Clar | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 112652.73 | Revised: |  | No. of Man-days: | 66
B.E. Dujali | Dujali | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: |  | Actual: | 57%
B.E. Dujali | Dujali | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 7%
B.E. Dujali | Dujali | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
B.E. Dujali | Dujali | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started: | 2020-01-02
B.E. Dujali | Dujali | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 107 - Dujali - San Isidro |  | GENERAL FUND CY 2020 | Maintenance | 3 | km | CBRMC | Project Cost: | 78482.06 | Target Completion Date: |  | Program: | 78482.06 | Planned: |  | No. of Persons: |  | PO #2020031411 - SAN ISIDRO FARMERS IRRIGATORS ASSN., INC.
B.E. Dujali | Dujali | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Maligro | Revised Completion Date: |  | Allotment: | 78482.06 | Revised: |  | No. of Man-days:
B.E. Dujali | Dujali | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
B.E. Dujali | Dujali | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
B.E. Dujali | Dujali | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: |  | Date completed:
B.E. Dujali | Dujali | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started:
B.E. Dujali | New Casay | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 108 - New Casay - Bugtong Talisay |  | GENERAL FUND CY 2020 | Maintenance |  | km | MBA | Project Cost: | 74294.5 | Target Completion Date: | 2020-12-31 23:59 | Program: | 74294.5 | Planned: | 50% | No. of Persons: | 4 | On-going
B.E. Dujali | New Casay | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Gamad/Clar | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 74294.5 | Revised: |  | No. of Man-days: | 88
B.E. Dujali | New Casay | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: |  | Actual: | 50%
B.E. Dujali | New Casay | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0%
B.E. Dujali | New Casay | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
B.E. Dujali | New Casay | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started: | 2020-01-02
B.E. Dujali | New Casay | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 108 - New Casay - Bugtong Talisay |  | GENERAL FUND CY 2020 | Maintenance |  | km | CBRMC | Project Cost: | 64596.78 | Target Completion Date: |  | Program: | 64596.78 | Planned: |  | No. of Persons: |  | For re-bid
B.E. Dujali | New Casay | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Maligro | Revised Completion Date: |  | Allotment: | 64596.78 | Revised: |  | No. of Man-days:
B.E. Dujali | New Casay | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
B.E. Dujali | New Casay | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
B.E. Dujali | New Casay | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: |  | Date completed:
B.E. Dujali | New Casay | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started:
B.E. Dujali | Magupising | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 113 - Dujali - Balisong - Magupising |  | GENERAL FUND CY 2020 | Maintenance | 5.52 | km | MBA | Project Cost: | 235776.07 | Target Completion Date: | 2020-12-31 23:59 | Program: | 235776.07 | Planned: | 50% | No. of Persons: | 3 | On-going
B.E. Dujali | Magupising | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Gamad/Clar | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 235776.07 | Revised: |  | No. of Man-days: | 22
B.E. Dujali | Magupising | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: |  | Actual: | 55%
B.E. Dujali | Magupising | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 5%
B.E. Dujali | Magupising | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
B.E. Dujali | Magupising | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started: | 2020-01-02
B.E. Dujali | Magupising | 2nd Eng'g. Dist. | On-going | 2020-06-08 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 113 - Dujali - Balisong - Magupising |  | GENERAL FUND CY 2020 | Maintenance | 5.52 | km | CBRMC | Project Cost: | 115911.95 | Target Completion Date: | 2020-12-12 | Program: | 115911.95 | Planned: | 5% | No. of Persons: |  | On-going
B.E. Dujali | Magupising | 2nd Eng'g. Dist. | On-going | 2020-06-08 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Maligro | Revised Completion Date: | 2021-01-08 | Allotment: | 115911.95 | Revised: |  | No. of Man-days:
B.E. Dujali | Magupising | 2nd Eng'g. Dist. | On-going | 2020-06-08 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: | Dujali Poblacion Farmer's Irrigator's Association, Inc. | No. of days suspended: | 27 | Disbursement: |  | Actual: | 5%
B.E. Dujali | Magupising | 2nd Eng'g. Dist. | On-going | 2020-06-08 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: | 187 | No. of days extended: |  |  |  | Slippage: | 0%
B.E. Dujali | Magupising | 2nd Eng'g. Dist. | On-going | 2020-06-08 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
B.E. Dujali | Magupising | 2nd Eng'g. Dist. | On-going | 2020-06-08 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started: | 2020-06-08
B.E. Dujali | Dujali | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 117 - Dujali - Pawas - San Vicente |  | GENERAL FUND CY 2020 | Maintenance | 4.42 | km | MBA | Project Cost: | 141544.99 | Target Completion Date: | 2020-12-31 23:59 | Program: | 141544.99 | Planned: | 50% | No. of Persons: | 3 | On-going
B.E. Dujali | Dujali | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Gamad/Clar | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 141544.99 | Revised: |  | No. of Man-days: | 22
B.E. Dujali | Dujali | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: |  | Actual: | 50%
B.E. Dujali | Dujali | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0%
B.E. Dujali | Dujali | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
B.E. Dujali | Dujali | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started: | 2020-01-02
B.E. Dujali | Dujali | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 117 - Dujali - Pawas - San Vicente |  | GENERAL FUND CY 2020 | Maintenance | 4.42 | km | CBRMC | Project Cost: | 140060.27 | Target Completion Date: |  | Program: | 140060.27 | Planned: |  | No. of Persons: |  | Abstract #320201344 -For post qualification
B.E. Dujali | Dujali | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Maligro | Revised Completion Date: |  | Allotment: | 140060.27 | Revised: |  | No. of Man-days:
B.E. Dujali | Dujali | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
B.E. Dujali | Dujali | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
B.E. Dujali | Dujali | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: |  | Date completed:
B.E. Dujali | Dujali | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started:
Sto. Tomas | Salvacion | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 118- Jct. Salvacion - San Vicente - Cabay-angan |  | GENERAL FUND CY 2020 | Maintenance | 3.45 | km | MBA | Project Cost: | 168583.81 | Target Completion Date: | 2020-12-31 23:59 | Program: | 168583.81 | Planned: | 50% | No. of Persons: | 3 | On-going
Sto. Tomas | Salvacion | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Gamad/Clar | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 168583.81 | Revised: |  | No. of Man-days: | 60
Sto. Tomas | Salvacion | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: |  | Actual: | 55%
Sto. Tomas | Salvacion | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 5%
Sto. Tomas | Salvacion | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
Sto. Tomas | Salvacion | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started: | 2020-01-02
Sto. Tomas | Salvacion | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 118- Jct. Salvacion - San Vicente - Cabay-angan |  | GENERAL FUND CY 2020 | Maintenance | 3.45 | km | CBRMC | Project Cost: | 158775.23 | Target Completion Date: |  | Program: | 158775.23 | Planned: |  | No. of Persons: |  | Abstract #320201396 - For post qualification
Sto. Tomas | Salvacion | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Maligro | Revised Completion Date: |  | Allotment: | 158775.23 | Revised: |  | No. of Man-days:
Sto. Tomas | Salvacion | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Sto. Tomas | Salvacion | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Sto. Tomas | Salvacion | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: |  | Date completed:
Sto. Tomas | Salvacion | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started:
Sto. Tomas | Casig-ang | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 123- Bacali - Casig-ang - Libertad |  | GENERAL FUND CY 2020 | Maintenance |  | km | MBA | Project Cost: | 167836.14 | Target Completion Date: | 2020-12-31 23:59 | Program: | 167836.14 | Planned: | 50% | No. of Persons: | 3 | On-going
Sto. Tomas | Casig-ang | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Gamad/Clar | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 167836.14 | Revised: |  | No. of Man-days: | 60
Sto. Tomas | Casig-ang | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: |  | Actual: | 58%
Sto. Tomas | Casig-ang | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 8%
Sto. Tomas | Casig-ang | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
Sto. Tomas | Casig-ang | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started: | 2020-01-02
Sto. Tomas | Casig-ang | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 123- Bacali - Casig-ang - Libertad |  | GENERAL FUND CY 2020 | Maintenance |  | km | CBRMC | Project Cost: | 131608.37 | Target Completion Date: |  | Program: | 131608.37 | Planned: |  | No. of Persons: |  | Abstract #320201449 - For post qualification
Sto. Tomas | Casig-ang | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Maligro | Revised Completion Date: |  | Allotment: | 131608.37 | Revised: |  | No. of Man-days:
Sto. Tomas | Casig-ang | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Sto. Tomas | Casig-ang | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Sto. Tomas | Casig-ang | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: |  | Date completed:
Sto. Tomas | Casig-ang | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started:
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 124 - Kinamayan - Moslog - Mahayag |  | GENERAL FUND CY 2020 | Maintenance |  | km | MBA | Project Cost: | 114628.54 | Target Completion Date: | 2020-12-31 23:59 | Program: | 114628.54 | Planned: | 50% | No. of Persons: | 3 | On-going
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Gamad/Clar | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 114628.54 | Revised: |  | No. of Man-days: | 66
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: |  | Actual: | 50%
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0%
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started: | 2020-01-02
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 124 - Kinamayan - Moslog - Mahayag |  | GENERAL FUND CY 2020 | Maintenance |  | km | CBRMC | Project Cost: | 91159.92 | Target Completion Date: |  | Program: | 91159.92 | Planned: |  | No. of Persons: |  | For re-bid
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Maligro | Revised Completion Date: |  | Allotment: | 91159.92 | Revised: |  | No. of Man-days:
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: |  | Date completed:
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started:
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 126 - Kinamayan - Lunga-og |  | GENERAL FUND CY 2020 | Maintenance |  | km | MBA | Project Cost: | 100416.26 | Target Completion Date: | 2020-12-31 23:59 | Program: | 100416.26 | Planned: | 50% | No. of Persons: |  | On-going
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Gamad/Clar | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 100416.26 | Revised: |  | No. of Man-days:
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: |  | Actual: | 52%
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 2%
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started: | 2020-01-02
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | On-going | 2020-06-15 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 126 - Kinamayan - Lunga-og |  | GENERAL FUND CY 2020 | Maintenance |  | km | CBRMC | Project Cost: | 64596.78 | Target Completion Date: | 2020-12-15 23:59 | Program: | 64596.78 | Planned: | 5% | No. of Persons: | 1 | On-going
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | On-going | 2020-06-15 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Maligro | Revised Completion Date: |  | Allotment: | 64596.78 | Revised: |  | No. of Man-days: | 2
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | On-going | 2020-06-15 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: | Lunga-og Tribal Association | No. of days suspended: |  | Disbursement: |  | Actual: | 5%
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | On-going | 2020-06-15 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: | 184 | No. of days extended: |  |  |  | Slippage: | 0%
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | On-going | 2020-06-15 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | On-going | 2020-06-15 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started: | 2020-06-15
Sto. Tomas | La Libertad | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 128 - Prk. Apitong - Upper Balisong - Dalisay |  | GENERAL FUND CY 2020 | Maintenance | 4.6 | km | MBA | Project Cost: | 150598.24 | Target Completion Date: | 2020-12-31 23:59 | Program: | 150598.24 | Planned: | 10% | No. of Persons: | 3 | On-going
Sto. Tomas | La Libertad | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Gamad/Clar | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 150598.24 | Revised: |  | No. of Man-days: | 60
Sto. Tomas | La Libertad | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: |  | Actual: | 9%
Sto. Tomas | La Libertad | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | -1%
Sto. Tomas | La Libertad | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
Sto. Tomas | La Libertad | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started: | 2020-01-02
Sto. Tomas | La Libertad | 2nd Eng'g. Dist. | On-going | 2020-06-15 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 128 - Prk. Apitong - Upper Balisong - Dalisay |  | GENERAL FUND CY 2020 | Maintenance | 4.6 | km | CBRMC | Project Cost: | 142475.11 | Target Completion Date: | 2020-12-15 23:59 | Program: | 142475.11 | Planned: | 5% | No. of Persons: |  | On-going
Sto. Tomas | La Libertad | 2nd Eng'g. Dist. | On-going | 2020-06-15 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Maligro | Revised Completion Date: |  | Allotment: | 142475.11 | Revised: |  | No. of Man-days:
Sto. Tomas | La Libertad | 2nd Eng'g. Dist. | On-going | 2020-06-15 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: | Lunga-og Tribal Association | No. of days suspended: |  | Disbursement: |  | Actual: | 5%
Sto. Tomas | La Libertad | 2nd Eng'g. Dist. | On-going | 2020-06-15 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: | 184 | No. of days extended: |  |  |  | Slippage: | 0%
Sto. Tomas | La Libertad | 2nd Eng'g. Dist. | On-going | 2020-06-15 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
Sto. Tomas | La Libertad | 2nd Eng'g. Dist. | On-going | 2020-06-15 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started: | 2020-06-15
Sto. Tomas | Esperanza | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 130 - Los Amigos 1 - Esperanza - Los Amigos 2 |  | GENERAL FUND CY 2020 | Maintenance | 3.59 | km | MBA | Project Cost: | 97116.27 | Target Completion Date: | 2020-12-31 23:59 | Program: | 97116.27 | Planned: | 50% | No. of Persons: | 4 | On-going
Sto. Tomas | Esperanza | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Gamad/Clar | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 97116.27 | Revised: |  | No. of Man-days: | 88
Sto. Tomas | Esperanza | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: |  | Actual: | 55%
Sto. Tomas | Esperanza | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 5%
Sto. Tomas | Esperanza | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
Sto. Tomas | Esperanza | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started: | 2020-01-02
Sto. Tomas | Esperanza | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 130 - Los Amigos 1 - Esperanza - Los Amigos 2 |  | GENERAL FUND CY 2020 | Maintenance | 3.59 | km | CBRMC | Project Cost: | 131608.37 | Target Completion Date: |  | Program: | 131608.37 | Planned: |  | No. of Persons: |  | PO #2020031351 - LOS AMIGOS GROUP OF WOMEN & FARMERS ASSN.
Sto. Tomas | Esperanza | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Maligro | Revised Completion Date: |  | Allotment: | 131608.37 | Revised: |  | No. of Man-days:
Sto. Tomas | Esperanza | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Sto. Tomas | Esperanza | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Sto. Tomas | Esperanza | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: |  | Date completed:
Sto. Tomas | Esperanza | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started:
Sto. Tomas | Lunga-og | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 131 - Mugas - Lanatad |  | GENERAL FUND CY 2020 | Maintenance |  | km | MBA | Project Cost: | 65482.21 | Target Completion Date: | 2020-12-31 23:59 | Program: | 65482.21 | Planned: | 50% | No. of Persons: | 3 | On-going
Sto. Tomas | Lunga-og | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Gamad/Clar | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 65482.21 | Revised: |  | No. of Man-days: | 12
Sto. Tomas | Lunga-og | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: |  | Actual: | 50%
Sto. Tomas | Lunga-og | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0%
Sto. Tomas | Lunga-og | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
Sto. Tomas | Lunga-og | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started: | 2020-01-02
Sto. Tomas | Lunga-og | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 131 - Mugas - Lanatad |  | GENERAL FUND CY 2020 | Maintenance |  | km | CBRMC | Project Cost: | 31996.54 | Target Completion Date: |  | Program: | 31996.54 | Planned: |  | No. of Persons: |  | Purchase Order # 2020030961 (Katipunan Pantaron Irrigator's Association)
Sto. Tomas | Lunga-og | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Maligro | Revised Completion Date: |  | Allotment: | 31996.54 | Revised: |  | No. of Man-days:
Sto. Tomas | Lunga-og | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Sto. Tomas | Lunga-og | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Sto. Tomas | Lunga-og | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: |  | Date completed:
Sto. Tomas | Lunga-og | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started:
Sto. Tomas | Lunga-og | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 132 - Mugas - Lunga-og |  | GENERAL FUND CY 2020 | Maintenance | 2.68 | km | MBA | Project Cost: | 96490.97 | Target Completion Date: | 2020-12-31 23:59 | Program: | 96490.97 | Planned: | 50% | No. of Persons: | 3 | On-going
Sto. Tomas | Lunga-og | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Gamad/Clar | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 96490.97 | Revised: |  | No. of Man-days: | 20
Sto. Tomas | Lunga-og | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: |  | Actual: | 50%
Sto. Tomas | Lunga-og | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0%
Sto. Tomas | Lunga-og | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
Sto. Tomas | Lunga-og | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started: | 2020-01-02
Sto. Tomas | Lunga-og | 2nd Eng'g. Dist. | On-going | 2020-06-15 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 132 - Mugas - Lunga-og |  | GENERAL FUND CY 2020 | Maintenance | 2.68 | km | CBRMC | Project Cost: | 74256.11 | Target Completion Date: | 2020-12-15 23:59 | Program: | 74256.11 | Planned: |  | No. of Persons: | 5 | On-going
Sto. Tomas | Lunga-og | 2nd Eng'g. Dist. | On-going | 2020-06-15 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Maligro | Revised Completion Date: | 2021-01-11 23:59 | Allotment: | 74256.11 | Revised: |  | No. of Man-days: | 5
Sto. Tomas | Lunga-og | 2nd Eng'g. Dist. | On-going | 2020-06-15 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: | Lunga-og Tribal Association | No. of days suspended: | 27 | Disbursement: |  | Actual:
Sto. Tomas | Lunga-og | 2nd Eng'g. Dist. | On-going | 2020-06-15 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: | 184 | No. of days extended: |  |  |  | Slippage: | 0%
Sto. Tomas | Lunga-og | 2nd Eng'g. Dist. | On-going | 2020-06-15 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
Sto. Tomas | Lunga-og | 2nd Eng'g. Dist. | On-going | 2020-06-15 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started: | 2020-06-15
Sto. Tomas | New Katipunan | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 134 - New Katipunan - Pantaron |  | GENERAL FUND CY 2020 | Maintenance |  | km | MBA | Project Cost: | 71748.41 | Target Completion Date: | 2020-12-31 23:59 | Program: | 71748.41 | Planned: | 50% | No. of Persons: | 2 | On-going
Sto. Tomas | New Katipunan | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Gamad/Clar | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 71748.41 | Revised: |  | No. of Man-days: | 20
Sto. Tomas | New Katipunan | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: |  | Actual: | 51%
Sto. Tomas | New Katipunan | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 1%
Sto. Tomas | New Katipunan | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
Sto. Tomas | New Katipunan | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started: | 2020-01-02
Sto. Tomas | New Katipunan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 134 - New Katipunan - Pantaron |  | GENERAL FUND CY 2020 | Maintenance |  | km | CBRMC | Project Cost: | 53126.32 | Target Completion Date: |  | Program: | 53126.32 | Planned: |  | No. of Persons: |  | Purchase Order # 2020030964 (Katipunan Pantaron Irrigator's Association)
Sto. Tomas | New Katipunan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Maligro | Revised Completion Date: |  | Allotment: | 53126.32 | Revised: |  | No. of Man-days:
Sto. Tomas | New Katipunan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Sto. Tomas | New Katipunan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Sto. Tomas | New Katipunan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: |  | Date completed:
Sto. Tomas | New Katipunan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started:
Sto. Tomas | New Katipunan | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 135 - Sto. Tomas - Bdry. Mamacao |  | GENERAL FUND CY 2020 | Maintenance | 4.9 | km | MBA | Project Cost: | 195671.17 | Target Completion Date: | 2020-12-31 23:59 | Program: | 195671.17 | Planned: | 50% | No. of Persons: | 3 | On-going
Sto. Tomas | New Katipunan | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Gamad/Clar | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 195671.17 | Revised: |  | No. of Man-days: | 33
Sto. Tomas | New Katipunan | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: |  | Actual: | 52%
Sto. Tomas | New Katipunan | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 2%
Sto. Tomas | New Katipunan | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
Sto. Tomas | New Katipunan | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started: | 2020-01-02
Sto. Tomas | New Katipunan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 135 - Sto. Tomas - Bdry. Mamacao |  | GENERAL FUND CY 2020 | Maintenance | 4.9 | km | CBRMC | Project Cost: | 116515.66 | Target Completion Date: |  | Program: | 116515.66 | Planned: |  | No. of Persons: |  | PO #2020031353 - KATIPUNAN PANTARON IRRIGATORS ASSN.
Sto. Tomas | New Katipunan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Maligro | Revised Completion Date: |  | Allotment: | 116515.66 | Revised: |  | No. of Man-days:
Sto. Tomas | New Katipunan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Sto. Tomas | New Katipunan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Sto. Tomas | New Katipunan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: |  | Date completed:
Sto. Tomas | New Katipunan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started:
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 136 - Fd. Rd. 3 - San Jose |  | GENERAL FUND CY 2020 | Maintenance | 4.55 | km | MBA | Project Cost: | 176994.35 | Target Completion Date: | 2020-12-31 23:59 | Program: | 176994.35 | Planned: | 50% | No. of Persons: | 2 | On-going
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Gamad/Clar | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 176994.35 | Revised: |  | No. of Man-days: | 10
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: |  | Actual: | 55%
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 5%
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started: | 2020-01-02
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 136 - Fd. Rd. 3 - San Jose |  | GENERAL FUND CY 2020 | Maintenance | 4.55 | km | CBRMC | Project Cost: | 112893.42 | Target Completion Date: |  | Program: | 112893.42 | Planned: |  | No. of Persons: |  | Purchase Order # 2020030974 (Brgy. San Jose Upland Farmer's Assocaition)
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Maligro | Revised Completion Date: |  | Allotment: | 112893.42 | Revised: |  | No. of Man-days:
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: |  | Date completed:
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started:
Sto. Tomas | Bobongon | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 139 - Nafco - Bobongon |  | GENERAL FUND CY 2020 | Maintenance |  | km | MBA | Project Cost: | 89179.68 | Target Completion Date: | 2020-12-31 23:59 | Program: | 89179.68 | Planned: | 50% | No. of Persons: | 3 | On-going
Sto. Tomas | Bobongon | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Gamad/Clar | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 89179.68 | Revised: |  | No. of Man-days: | 56
Sto. Tomas | Bobongon | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: |  | Actual: | 55%
Sto. Tomas | Bobongon | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 5%
Sto. Tomas | Bobongon | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
Sto. Tomas | Bobongon | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started: | 2020-01-02
Sto. Tomas | Bobongon | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 139 - Nafco - Bobongon |  | GENERAL FUND CY 2020 | Maintenance |  | km | CBRMC | Project Cost: | 80293.17 | Target Completion Date: |  | Program: | 80293.17 | Planned: |  | No. of Persons: |  | Purchase Order # 2020030968 (Bobongon Rural Waterworks & Sanitation Association, Inc.)
Sto. Tomas | Bobongon | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Maligro | Revised Completion Date: |  | Allotment: | 80293.17 | Revised: |  | No. of Man-days:
Sto. Tomas | Bobongon | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Sto. Tomas | Bobongon | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Sto. Tomas | Bobongon | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: |  | Date completed:
Sto. Tomas | Bobongon | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started:
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 146 - Bdry. Tagum - Crossing Kinamayan Sto. Tomas |  | GENERAL FUND CY 2020 | Maintenance |  | km | MBA | Project Cost: | 790874.1 | Target Completion Date: | 2020-12-31 23:59 | Program: | 790874.1 | Planned: | 50% | No. of Persons: | 3 | On-going
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Gamad/Clar | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 790874.1 | Revised: |  | No. of Man-days: | 66
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: |  | Actual: | 50%
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0%
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started: | 2020-01-02
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 146 - Bdry. Tagum - Crossing Kinamayan Sto. Tomas |  | GENERAL FUND CY 2020 | Maintenance |  | km | CBRMC | Project Cost: | 429840.12 | Target Completion Date: |  | Program: | 429840.12 | Planned: |  | No. of Persons: |  | PO #2020031407 - LOS AMIGOS GROUP OF WOMEN & FARMERS ASSN.
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Maligro | Revised Completion Date: |  | Allotment: | 429840.12 | Revised: |  | No. of Man-days:
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: |  | Date completed:
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started:
Sto. Tomas | Magwawa | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 151 - San Jose - Sitio Mahayahay, Magwawa |  | GENERAL FUND CY 2020 | Maintenance | 0.84 | km | MBA | Project Cost: | 22943.54 | Target Completion Date: | 2020-12-31 23:59 | Program: | 22943.54 | Planned: | 50% | No. of Persons: | 3 | On-going
Sto. Tomas | Magwawa | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Gamad/Clar | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 22943.54 | Revised: |  | No. of Man-days: | 60
Sto. Tomas | Magwawa | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: |  | Actual: | 50%
Sto. Tomas | Magwawa | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0%
Sto. Tomas | Magwawa | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
Sto. Tomas | Magwawa | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started: | 2020-01-02
Sto. Tomas | Magwawa | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 151 - San Jose - Sitio Mahayahay, Magwawa |  | GENERAL FUND CY 2020 | Maintenance | 0.84 | km | CBRMC | Project Cost: | 30789.12 | Target Completion Date: |  | Program: | 30789.12 | Planned: |  | No. of Persons: |  | Purchase Order # 2020030972 (Brgy. San Jose Upland Farmer's Assocaition)
Sto. Tomas | Magwawa | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Maligro | Revised Completion Date: |  | Allotment: | 30789.12 | Revised: |  | No. of Man-days:
Sto. Tomas | Magwawa | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Sto. Tomas | Magwawa | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Sto. Tomas | Magwawa | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: |  | Date completed:
Sto. Tomas | Magwawa | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started:
Babak, IGCS | Cogon | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rural Electrification Project | Completion of Single Phase Line at Purok 6 and Purok 7, Brgy. Cogon, Babak Distirct, IGACOS |  | 20% DF CY 2020 | Electrificaton |  | km |  | Project Cost: | 1000000 | Target Completion Date: |  | Program: | 1000000 | Planned: |  | No. of Persons: |  | PR #20063965
Babak, IGCS | Cogon | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rural Electrification Project | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 1000000 | Revised: |  | No. of Man-days:
Babak, IGCS | Cogon | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rural Electrification Project | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Babak, IGCS | Cogon | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rural Electrification Project | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Babak, IGCS | Cogon | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rural Electrification Project | [7 empty] | Date Allotment Released: |  | Date completed:
Babak, IGCS | Cogon | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rural Electrification Project | [7 empty] | Date Started:
IGCS | Sta. Cruz | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rural Electrification Project | Completion of Single Phase Line at Purok Perlas, Brgy. Sta. Cruz, Talicud (Day Care Center), IGACOS |  | 20% DF CY 2020 | Electrificaton |  | km |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | POW preparation on-going c/o Engr. Kim Pao Lu
IGCS | Sta. Cruz | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rural Electrification Project | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
IGCS | Sta. Cruz | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rural Electrification Project | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
IGCS | Sta. Cruz | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rural Electrification Project | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
IGCS | Sta. Cruz | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rural Electrification Project | [7 empty] | Date Allotment Released: |  | Date completed:
IGCS | Sta. Cruz | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rural Electrification Project | [7 empty] | Date Started:
Sto. Tomas | San Jose | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | ROAD ID 008 - Fr. Rd. 3 - San Jose |  | 20% DF CY 2020 | Rehabilitation |  | km |  | Project Cost: | 8000000 | Target Completion Date: |  | Program: | 8000000 | Planned: |  | No. of Persons: |  | Plan On-going
Sto. Tomas | San Jose | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 8000000 | Revised: |  | No. of Man-days:
Sto. Tomas | San Jose | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Sto. Tomas | San Jose | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Sto. Tomas | San Jose | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Date Allotment Released: |  | Date completed:
Sto. Tomas | San Jose | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Date Started:
Carmen | Asuncion | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | ROAD ID 007 - Lower Asuncion - Upper Asuncion |  | 20% DF CY 2020 | Rehabilitation |  | km |  | Project Cost: | 1302000 | Target Completion Date: |  | Program: | 1302000 | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No
Carmen | Asuncion | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 1302000 | Revised: |  | No. of Man-days:
Carmen | Asuncion | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Carmen | Asuncion | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Carmen | Asuncion | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Date Allotment Released: |  | Date completed:
Carmen | Asuncion | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Date Started:
Carmen | Mangalcal | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | ROAD ID 030 - Jct. Highway - Carmen - Mangalcal - Tubod |  | 20% DF CY 2020 | Rehabilitation |  | km |  | Project Cost: | 1323000 | Target Completion Date: |  | Program: | 1323000 | Planned: |  | No. of Persons: |  | Plan On-going
Carmen | Mangalcal | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 1323000 | Revised: |  | No. of Man-days:
Carmen | Mangalcal | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Carmen | Mangalcal | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Carmen | Mangalcal | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Date Allotment Released: |  | Date completed:
Carmen | Mangalcal | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Date Started:
Carmen | Tuganay | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | ROAD ID 031 - Tuganay - Taba |  | 20% DF CY 2020 | Rehabilitation |  | km |  | Project Cost: | 1431000 | Target Completion Date: |  | Program: | 1431000 | Planned: |  | No. of Persons: |  | Plan On-going
Carmen | Tuganay | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 1431000 | Revised: |  | No. of Man-days:
Carmen | Tuganay | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Carmen | Tuganay | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Carmen | Tuganay | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Date Allotment Released: |  | Date completed:
Carmen | Tuganay | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Date Started:
Carmen | Ising | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | ROAD ID 069 - Jct. Highway - Ising - Magsaysay |  | 20% DF CY 2020 | Rehabilitation |  | km |  | Project Cost: | 6000000 | Target Completion Date: |  | Program: | 6000000 | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No
Carmen | Ising | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 6000000 | Revised: |  | No. of Man-days:
Carmen | Ising | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Carmen | Ising | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Carmen | Ising | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Date Allotment Released: |  | Date completed:
Carmen | Ising | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Date Started:
Carmen | Guadalupe | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | Jct. Highway - Guadalupe - Bdry. Tagum |  | 20% DF CY 2020 | Rehabilitation |  | km |  | Project Cost: | 910000 | Target Completion Date: |  | Program: | 910000 | Planned: |  | No. of Persons: |  | Plan On-going
Carmen | Guadalupe | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 910000 | Revised: |  | No. of Man-days:
Carmen | Guadalupe | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Carmen | Guadalupe | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Carmen | Guadalupe | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Date Allotment Released: |  | Date completed:
Carmen | Guadalupe | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Date Started:
Carmen | Tibulao | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | Sitio Malaga - Tibulao |  | 20% DF CY 2020 | Rehabilitation |  | km |  | Project Cost: | 350000 | Target Completion Date: |  | Program: | 350000 | Planned: |  | No. of Persons: |  | Plan On-going
Carmen | Tibulao | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 350000 | Revised: |  | No. of Man-days:
Carmen | Tibulao | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Carmen | Tibulao | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Carmen | Tibulao | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Date Allotment Released: |  | Date completed:
Carmen | Tibulao | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Date Started:
Carmen | New Casay | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | Prk. 5 RJS - Prk. 6 New Casay |  | 20% DF CY 2020 | Rehabilitation |  | km |  | Project Cost: | 350000 | Target Completion Date: |  | Program: | 350000 | Planned: |  | No. of Persons: |  | Plan On-going
Carmen | New Casay | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 350000 | Revised: |  | No. of Man-days:
Carmen | New Casay | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Carmen | New Casay | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Carmen | New Casay | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Date Allotment Released: |  | Date completed:
Carmen | New Casay | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Date Started:
B.E. Dujali | Pawas | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | Dujali - Pawas - San Vicente |  | 20% DF CY 2020 | Rehabilitation |  | km |  | Project Cost: | 350000 | Target Completion Date: |  | Program: | 350000 | Planned: |  | No. of Persons: |  | Plan On-going
B.E. Dujali | Pawas | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 350000 | Revised: |  | No. of Man-days:
B.E. Dujali | Pawas | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
B.E. Dujali | Pawas | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
B.E. Dujali | Pawas | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Date Allotment Released: |  | Date completed:
B.E. Dujali | Pawas | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Date Started:
Sto. Tomas | Esperanza | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | Los Amigos 1 - Esperanza - Los Amigos 2 |  | 20% DF CY 2020 | Rehabilitation |  | km |  | Project Cost: | 350000 | Target Completion Date: |  | Program: | 350000 | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No
Sto. Tomas | Esperanza | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 350000 | Revised: |  | No. of Man-days:
Sto. Tomas | Esperanza | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Sto. Tomas | Esperanza | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Sto. Tomas | Esperanza | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Date Allotment Released: |  | Date completed:
Sto. Tomas | Esperanza | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Date Started:
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | San Miguel - Crossing Kinamayan |  | 20% DF CY 2020 | Rehabilitation |  | km |  | Project Cost: | 19200000 | Target Completion Date: |  | Program: | 19200000 | Planned: |  | No. of Persons: |  | Plan On-going
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 19200000 | Revised: |  | No. of Man-days:
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Date Allotment Released: |  | Date completed:
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Date Started:
Sto. Tomas | Magwawa | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | Fd. Rd. 2 - Sto. Tomas - Magwawa |  | 20% DF CY 2020 | Rehabilitation |  | km |  | Project Cost: | 350000 | Target Completion Date: |  | Program: | 350000 | Planned: |  | No. of Persons: |  | Plan On-going
Sto. Tomas | Magwawa | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 350000 | Revised: |  | No. of Man-days:
Sto. Tomas | Magwawa | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Sto. Tomas | Magwawa | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Sto. Tomas | Magwawa | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Date Allotment Released: |  | Date completed:
Sto. Tomas | Magwawa | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Date Started:
Sto. Tomas | Balagunan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | Menzi - Balagunan - Tulalian |  | 20% DF CY 2020 | Rehabilitation |  | km |  | Project Cost: | 3720500 | Target Completion Date: |  | Program: | 3720500 | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No
Sto. Tomas | Balagunan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 3720500 | Revised: |  | No. of Man-days:
Sto. Tomas | Balagunan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Sto. Tomas | Balagunan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Sto. Tomas | Balagunan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Date Allotment Released: |  | Date completed:
Sto. Tomas | Balagunan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Date Started:
B.E. Dujali | Magupising | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | Jct,. Bdry. Tagum- Talomo |  | 20% DF CY 2020 | Rehabilitation |  | km |  | Project Cost: | 3720500 | Target Completion Date: |  | Program: | 3720500 | Planned: |  | No. of Persons: |  | POW for approval with the Governor
B.E. Dujali | Magupising | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 3720500 | Revised: |  | No. of Man-days:
B.E. Dujali | Magupising | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
B.E. Dujali | Magupising | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
B.E. Dujali | Magupising | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Date Allotment Released: |  | Date completed:
B.E. Dujali | Magupising | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Date Started:
IGCS | AI | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Various Local Roads & Drainage Dev't. Project | Rehab. Of Various Local Roads @ Island Garden City of Samal |  | 20% DF CY 2020 | Rehabilitation |  | km |  | Project Cost: | 2518182 | Target Completion Date: |  | Program: | 2518182 | Planned: |  | No. of Persons: |  | Plan On-going
IGCS | AI | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Various Local Roads & Drainage Dev't. Project | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 2518182 | Revised: |  | No. of Man-days:
IGCS | AI | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Various Local Roads & Drainage Dev't. Project | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
IGCS | AI | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Various Local Roads & Drainage Dev't. Project | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
IGCS | AI | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Various Local Roads & Drainage Dev't. Project | [7 empty] | Date Allotment Released: |  | Date completed:
IGCS | AI | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Various Local Roads & Drainage Dev't. Project | [7 empty] | Date Started:
Panabo City | APC | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Various Local Roads & Drainage Dev't. Project | Rehab. Of Various Local Roads @ Panabo City |  | 20% DF CY 2020 | Rehabilitation |  | km |  | Project Cost: | 2518182 | Target Completion Date: |  | Program: | 2518182 | Planned: |  | No. of Persons: |  | Abstract # 0420201633 - Billboard; Abstract 0520201661 - hardware
Panabo City | APC | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Various Local Roads & Drainage Dev't. Project | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 2518182 | Revised: |  | No. of Man-days:
Panabo City | APC | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Various Local Roads & Drainage Dev't. Project | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Panabo City | APC | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Various Local Roads & Drainage Dev't. Project | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Panabo City | APC | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Various Local Roads & Drainage Dev't. Project | [7 empty] | Date Allotment Released: |  | Date completed:
Panabo City | APC | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Various Local Roads & Drainage Dev't. Project | [7 empty] | Date Started:
B.E. Dujali | ABD | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Various Local Roads & Drainage Dev't. Project | Rehab. Of Various Local Roads @ B.E Dujali |  | 20% DF CY 2020 | Rehabilitation |  | km |  | Project Cost: | 2518182 | Target Completion Date: |  | Program: | 2518182 | Planned: |  | No. of Persons: |  | Purchase Request # 20053256 - Hardware; PR # 20053255 - Billboard
B.E. Dujali | ABD | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Various Local Roads & Drainage Dev't. Project | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 2518182 | Revised: |  | No. of Man-days:
B.E. Dujali | ABD | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Various Local Roads & Drainage Dev't. Project | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
B.E. Dujali | ABD | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Various Local Roads & Drainage Dev't. Project | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
B.E. Dujali | ABD | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Various Local Roads & Drainage Dev't. Project | [7 empty] | Date Allotment Released: |  | Date completed:
B.E. Dujali | ABD | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Various Local Roads & Drainage Dev't. Project | [7 empty] | Date Started:
Carmen | AC | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Various Local Roads & Drainage Dev't. Project | Rehab. Of Various Local Roads @ Carmen |  | 20% DF CY 2020 | Rehabilitation |  | km |  | Project Cost: | 2518182 | Target Completion Date: |  | Program: | 2518182 | Planned: |  | No. of Persons: |  | Abstract # 0420201633 - Billboard; Abstract 0520201661 - hardware
Carmen | AC | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Various Local Roads & Drainage Dev't. Project | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 2518182 | Revised: |  | No. of Man-days:
Carmen | AC | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Various Local Roads & Drainage Dev't. Project | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Carmen | AC | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Various Local Roads & Drainage Dev't. Project | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Carmen | AC | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Various Local Roads & Drainage Dev't. Project | [7 empty] | Date Allotment Released: |  | Date completed:
Carmen | AC | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Various Local Roads & Drainage Dev't. Project | [7 empty] | Date Started:
Sto. Tomas | AST | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Various Local Roads & Drainage Dev't. Project | Rehab. Of Various Local Roads @ Sto. Tomas |  | 20% DF CY 2020 | Rehabilitation |  | km |  | Project Cost: | 2518182 | Target Completion Date: |  | Program: | 2518182 | Planned: |  | No. of Persons: |  | Plan On-going
Sto. Tomas | AST | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Various Local Roads & Drainage Dev't. Project | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 2518182 | Revised: |  | No. of Man-days:
Sto. Tomas | AST | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Various Local Roads & Drainage Dev't. Project | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Sto. Tomas | AST | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Various Local Roads & Drainage Dev't. Project | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Sto. Tomas | AST | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Various Local Roads & Drainage Dev't. Project | [7 empty] | Date Allotment Released: |  | Date completed:
Sto. Tomas | AST | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Various Local Roads & Drainage Dev't. Project | [7 empty] | Date Started:
Babak, IGCS | AB | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Various Government Buildings and Facilities Development Project | Construction of Commercial Building at Kinawitnon, IGACOS, Babak |  | 20% DF CY 2020 | Building |  | sq.m |  | Project Cost: | 2000000 | Target Completion Date: |  | Program: | 2000000 | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
Babak, IGCS | AB | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Various Government Buildings and Facilities Development Project | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 2000000 | Revised: |  | No. of Man-days:
Babak, IGCS | AB | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Various Government Buildings and Facilities Development Project | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Babak, IGCS | AB | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Various Government Buildings and Facilities Development Project | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Babak, IGCS | AB | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Various Government Buildings and Facilities Development Project | [7 empty] | Date Allotment Released: |  | Date completed:
Babak, IGCS | AB | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Various Government Buildings and Facilities Development Project | [7 empty] | Date Started:
Carmen | Ising | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Various Government Buildings and Facilities Development Project | Improvement of Provincial Engineer's Office 2nd District Office Phase 2, Carmen |  | 20% DF CY 2020 | Building |  | sq.m |  | Project Cost: | 1590000 | Target Completion Date: |  | Program: | 1590000 | Planned: |  | No. of Persons: |  | Plan and DED On-going
Carmen | Ising | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Various Government Buildings and Facilities Development Project | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 1590000 | Revised: |  | No. of Man-days:
Carmen | Ising | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Various Government Buildings and Facilities Development Project | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Carmen | Ising | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Various Government Buildings and Facilities Development Project | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Carmen | Ising | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Various Government Buildings and Facilities Development Project | [7 empty] | Date Allotment Released: |  | Date completed:
Carmen | Ising | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Various Government Buildings and Facilities Development Project | [7 empty] | Date Started:
B.E. Dujali | Ising | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Various Government Buildings and Facilities Development Project | Construction of DDN hospital Carmen Zone Annex Building Phase 3, Carmen |  | GENERAL FUND CY 2020 | Building |  | sq.m |  | Project Cost: | 800000 | Target Completion Date: |  | Program: | 800000 | Planned: |  | No. of Persons: |  | Abstract #0420201476
B.E. Dujali | Ising | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Various Government Buildings and Facilities Development Project | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 800000 | Revised: |  | No. of Man-days:
B.E. Dujali | Ising | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Various Government Buildings and Facilities Development Project | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
B.E. Dujali | Ising | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Various Government Buildings and Facilities Development Project | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
B.E. Dujali | Ising | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Various Government Buildings and Facilities Development Project | [7 empty] | Date Allotment Released: |  | Date completed:
B.E. Dujali | Ising | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Various Government Buildings and Facilities Development Project | [7 empty] | Date Started:
B.E. Dujali | Dujali | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Various Government Buildings and Facilities Development Project | Construction of Municipal Triball Hall, B.E. Dujali |  | GENERAL FUND CY 2020 | Building |  | sq.m |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
B.E. Dujali | Dujali | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Various Government Buildings and Facilities Development Project | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
B.E. Dujali | Dujali | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Various Government Buildings and Facilities Development Project | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
B.E. Dujali | Dujali | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Various Government Buildings and Facilities Development Project | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
B.E. Dujali | Dujali | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Various Government Buildings and Facilities Development Project | [7 empty] | Date Allotment Released: |  | Date completed:
B.E. Dujali | Dujali | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Various Government Buildings and Facilities Development Project | [7 empty] | Date Started:
Sto. Tomas | Tibal-og | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Various Government Buildings and Facilities Development Project | Construction of Municipal Triball Hall, Sto. Tomas |  | GENERAL FUND CY 2020 | Building |  | sq.m | Admin | Project Cost: | 500000 | Target Completion Date: | 2019-07-31 | Program: | 500000 | Planned: | 100% | No. of Persons: | 7 | Suspended June 28, 2019. Waiting for the delivery of JO Materials
Sto. Tomas | Tibal-og | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Various Government Buildings and Facilities Development Project | [7 empty] | Project Engineer: | Roque | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days: | 110
Sto. Tomas | Tibal-og | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Various Government Buildings and Facilities Development Project | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: | 85%
Sto. Tomas | Tibal-og | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Various Government Buildings and Facilities Development Project | [7 empty] | Duration: | 70 | No. of days extended: |  |  |  | Slippage: | -15%
Sto. Tomas | Tibal-og | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Various Government Buildings and Facilities Development Project | [7 empty] | Date Allotment Released: | CY 2018 | Date completed:
Sto. Tomas | Tibal-og | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Various Government Buildings and Facilities Development Project | [7 empty] | Date Started: | 2019-05-22
Sto. Tomas | Tulalian | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Various Government Buildings and Facilities Development Project | Construction of Fence at Tulalian National High School, Tulalian, Sto. Tomas |  | GENERAL FUND CY 2020 | Fence |  | sq.m |  | Project Cost: | 1500000 | Target Completion Date: |  | Program: | 1500000 | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
Sto. Tomas | Tulalian | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Various Government Buildings and Facilities Development Project | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 1500000 | Revised: |  | No. of Man-days:
Sto. Tomas | Tulalian | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Various Government Buildings and Facilities Development Project | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Sto. Tomas | Tulalian | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Various Government Buildings and Facilities Development Project | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Sto. Tomas | Tulalian | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Various Government Buildings and Facilities Development Project | [7 empty] | Date Allotment Released: |  | Date completed:
Sto. Tomas | Tulalian | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Various Government Buildings and Facilities Development Project | [7 empty] | Date Started:
Carmen | Tibulao | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Various Government Buildings and Facilities Development Project | Construction of Two(2) Classroom at Tibulao Elem. School, Tibulao, Carmen |  | GENERAL FUND CY 2020 | Building |  | sq.m |  | Project Cost: | 2900000 | Target Completion Date: |  | Program: | 2900000 | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
Carmen | Tibulao | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Various Government Buildings and Facilities Development Project | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 2900000 | Revised: |  | No. of Man-days:
Carmen | Tibulao | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Various Government Buildings and Facilities Development Project | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Carmen | Tibulao | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Various Government Buildings and Facilities Development Project | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Carmen | Tibulao | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Various Government Buildings and Facilities Development Project | [7 empty] | Date Allotment Released: |  | Date completed:
Carmen | Tibulao | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Various Government Buildings and Facilities Development Project | [7 empty] | Date Started:
Carmen |  | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Desiltation/Excavation of Rivers & Creeks | Improvement and Desiltation of Camoning Creek |  | 5% Calamity Fund CY 2020 | Desiltation |  | ln.m |  | Project Cost: | 2500000 | Target Completion Date: |  | Program: | 2500000 | Planned: |  | No. of Persons: |  | Abstract # 0520201658
Carmen |  | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Desiltation/Excavation of Rivers & Creeks | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 2500000 | Revised: |  | No. of Man-days:
Carmen |  | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Desiltation/Excavation of Rivers & Creeks | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Carmen |  | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Desiltation/Excavation of Rivers & Creeks | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Carmen |  | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Desiltation/Excavation of Rivers & Creeks | [7 empty] | Date Allotment Released: |  | Date completed:
Carmen |  | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Desiltation/Excavation of Rivers & Creeks | [7 empty] | Date Started:
Carmen | Ising | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Desiltation/Excavation of Rivers & Creeks | Improvement and Desiltation of Ising Creek |  | 5% Calamity Fund CY 2020 | Desiltation |  | ln.m |  | Project Cost: | 2000000 | Target Completion Date: |  | Program: | 2000000 | Planned: |  | No. of Persons: |  | Abstract # 0420201637; 0520201662
Carmen | Ising | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Desiltation/Excavation of Rivers & Creeks | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 2000000 | Revised: |  | No. of Man-days:
Carmen | Ising | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Desiltation/Excavation of Rivers & Creeks | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Carmen | Ising | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Desiltation/Excavation of Rivers & Creeks | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Carmen | Ising | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Desiltation/Excavation of Rivers & Creeks | [7 empty] | Date Allotment Released: |  | Date completed:
Carmen | Ising | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Desiltation/Excavation of Rivers & Creeks | [7 empty] | Date Started:
Carmen | Anibongan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Desiltation/Excavation of Rivers & Creeks | Desiltation of Buhang Creek, Anibongan, Carmen |  | 5% Calamity Fund CY 2020 | Desiltation |  | ln.m |  | Project Cost: | 2130206 | Target Completion Date: |  | Program: | 2130206 | Planned: |  | No. of Persons: |  | Abstract # 0520201657; 0420201626
Carmen | Anibongan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Desiltation/Excavation of Rivers & Creeks | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 2130206 | Revised: |  | No. of Man-days:
Carmen | Anibongan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Desiltation/Excavation of Rivers & Creeks | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Carmen | Anibongan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Desiltation/Excavation of Rivers & Creeks | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Carmen | Anibongan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Desiltation/Excavation of Rivers & Creeks | [7 empty] | Date Allotment Released: |  | Date completed:
Carmen | Anibongan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Desiltation/Excavation of Rivers & Creeks | [7 empty] | Date Started:
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Revetment of Dike and Slope Protection | Rehab./Impv't. of San Miguel - Moslog - Kinamayan, Sto. Tomas |  | 5% Calamity Fund CY 2020 | Rehabilitation |  | ln.m |  | Project Cost: | 1000000 | Target Completion Date: |  | Program: | 1000000 | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Revetment of Dike and Slope Protection | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 1000000 | Revised: |  | No. of Man-days:
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Revetment of Dike and Slope Protection | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Revetment of Dike and Slope Protection | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Revetment of Dike and Slope Protection | [7 empty] | Date Allotment Released: |  | Date completed:
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Revetment of Dike and Slope Protection | [7 empty] | Date Started:
Carmen | Mangalcal | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Improvement of Roads, Drainage and Canal | Improvement of Mangalcal to Diamond Creek Farm to Market Road Opening |  | 5% Calamity Fund CY 2020 | Improvement |  | ln.m |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
Carmen | Mangalcal | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Improvement of Roads, Drainage and Canal | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Carmen | Mangalcal | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Improvement of Roads, Drainage and Canal | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Carmen | Mangalcal | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Improvement of Roads, Drainage and Canal | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Carmen | Mangalcal | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Improvement of Roads, Drainage and Canal | [7 empty] | Date Allotment Released: |  | Date completed:
Carmen | Mangalcal | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Improvement of Roads, Drainage and Canal | [7 empty] | Date Started:
Carmen | Mabaus | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Improvement of Roads, Drainage and Canal | Improvement of Mabaus - Salvacion Provincial Road Continuing Road Opening |  | 5% Calamity Fund CY 2020 | Improvement |  | ln.m |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Plan On-going
Carmen | Mabaus | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Improvement of Roads, Drainage and Canal | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Carmen | Mabaus | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Improvement of Roads, Drainage and Canal | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Carmen | Mabaus | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Improvement of Roads, Drainage and Canal | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Carmen | Mabaus | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Improvement of Roads, Drainage and Canal | [7 empty] | Date Allotment Released: |  | Date completed:
Carmen | Mabaus | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Improvement of Roads, Drainage and Canal | [7 empty] | Date Started:
Carmen | Mangalcal | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Improvement of Bridges and Cross Drainage | Single Barrel Box Culvert at Mangalcal-Diamond Creek, Brgy. Mangalcal, Carmen |  | 5% Calamity Fund CY 2020 | Box Culvert |  | ln.m |  | Project Cost: | 2000000 | Target Completion Date: |  | Program: | 2000000 | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
Carmen | Mangalcal | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Improvement of Bridges and Cross Drainage | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 2000000 | Revised: |  | No. of Man-days:
Carmen | Mangalcal | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Improvement of Bridges and Cross Drainage | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Carmen | Mangalcal | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Improvement of Bridges and Cross Drainage | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Carmen | Mangalcal | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Improvement of Bridges and Cross Drainage | [7 empty] | Date Allotment Released: |  | Date completed:
Carmen | Mangalcal | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Improvement of Bridges and Cross Drainage | [7 empty] | Date Started:
Sto. Tomas | Magwawa | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. | Const. of 1 Classroom @ Mangga ES, Magwawa, Sto. Tomas |  | SEF-AB CY 2020 | Building |  | sq.m |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | For preparation of POW and Plans
Sto. Tomas | Magwawa | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Sto. Tomas | Magwawa | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Sto. Tomas | Magwawa | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Sto. Tomas | Magwawa | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. | [7 empty] | Date Allotment Released: |  | Date completed:
Sto. Tomas | Magwawa | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. | [7 empty] | Date Started:
Panabo City | J.P. Laurel | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | Const. of Day Care Center, JP Laurel, Panabo City |  | AB CY 2020 | Building |  | sq.m |  | Project Cost: | 1000000 | Target Completion Date: |  | Program: | 1000000 | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
Panabo City | J.P. Laurel | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 1000000 | Revised: |  | No. of Man-days:
Panabo City | J.P. Laurel | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Panabo City | J.P. Laurel | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Panabo City | J.P. Laurel | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | [7 empty] | Date Allotment Released: |  | Date completed:
Panabo City | J.P. Laurel | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | [7 empty] | Date Started:
B.E. Dujali | Dujali | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | Const. of Day Care Center, Dujali, B.E. Dujali |  | AB CY 2020 | Building |  | sq.m |  | Project Cost: | 1000000 | Target Completion Date: |  | Program: | 1000000 | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
B.E. Dujali | Dujali | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 1000000 | Revised: |  | No. of Man-days:
B.E. Dujali | Dujali | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
B.E. Dujali | Dujali | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
B.E. Dujali | Dujali | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | [7 empty] | Date Allotment Released: |  | Date completed:
B.E. Dujali | Dujali | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | [7 empty] | Date Started:
Sto. Tomas | Tibal-og | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | Const. of Day Care Center, Tibal-og, Sto Tomas |  | AB CY 2020 | Building |  | sq.m |  | Project Cost: | 1000000 | Target Completion Date: |  | Program: | 1000000 | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
Sto. Tomas | Tibal-og | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 1000000 | Revised: |  | No. of Man-days:
Sto. Tomas | Tibal-og | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Sto. Tomas | Tibal-og | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Sto. Tomas | Tibal-og | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | [7 empty] | Date Allotment Released: |  | Date completed:
Sto. Tomas | Tibal-og | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | [7 empty] | Date Started:
B.E. Dujali | Cabay-angan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | Compl./Rep. Day Care Center, Cabay-angan, B.E. Dujali |  | AB CY 2020 | Building |  | sq.m |  | Project Cost: | 300000 | Target Completion Date: |  | Program: | 300000 | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
B.E. Dujali | Cabay-angan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 300000 | Revised: |  | No. of Man-days:
B.E. Dujali | Cabay-angan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
B.E. Dujali | Cabay-angan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
B.E. Dujali | Cabay-angan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | [7 empty] | Date Allotment Released: |  | Date completed:
B.E. Dujali | Cabay-angan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | [7 empty] | Date Started:
B.E. Dujali | Tanglaw | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | Compl./Rep. Day Care Center, Tanglaw, B.E. Dujali |  | AB CY 2020 | Building |  | sq.m |  | Project Cost: | 300000 | Target Completion Date: |  | Program: | 300000 | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
B.E. Dujali | Tanglaw | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 300000 | Revised: |  | No. of Man-days:
B.E. Dujali | Tanglaw | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
B.E. Dujali | Tanglaw | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
B.E. Dujali | Tanglaw | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | [7 empty] | Date Allotment Released: |  | Date completed:
B.E. Dujali | Tanglaw | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | [7 empty] | Date Started:
Carmen | Salvacion | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | Compl./Rep. Day Care Center, Salvacion, Carmen |  | AB CY 2020 | Building |  | sq.m |  | Project Cost: | 300000 | Target Completion Date: |  | Program: | 300000 | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
Carmen | Salvacion | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 300000 | Revised: |  | No. of Man-days:
Carmen | Salvacion | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Carmen | Salvacion | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Carmen | Salvacion | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | [7 empty] | Date Allotment Released: |  | Date completed:
Carmen | Salvacion | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | [7 empty] | Date Started:
IGCS | San Agustin | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | Compl./Rep. Day Care Center, San Agustin, IGCS |  | AB CY 2020 | Building |  | sq.m |  | Project Cost: | 300000 | Target Completion Date: |  | Program: | 300000 | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
IGCS | San Agustin | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 300000 | Revised: |  | No. of Man-days:
IGCS | San Agustin | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
IGCS | San Agustin | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
IGCS | San Agustin | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | [7 empty] | Date Allotment Released: |  | Date completed:
IGCS | San Agustin | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | [7 empty] | Date Started:
IGCS | Toril | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | Compl./Rep. Day Care Center, Toril, IGCS |  | AB CY 2020 | Building |  | sq.m |  | Project Cost: | 300000 | Target Completion Date: |  | Program: | 300000 | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
IGCS | Toril | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 300000 | Revised: |  | No. of Man-days:
IGCS | Toril | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
IGCS | Toril | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
IGCS | Toril | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | [7 empty] | Date Allotment Released: |  | Date completed:
IGCS | Toril | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | [7 empty] | Date Started:
Sto. Tomas | Tibal-og | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | Compl./Rep. Day Care Center, Tibal-og, Sto. Tomas |  | AB CY 2020 | Building |  | sq.m |  | Project Cost: | 600000 | Target Completion Date: |  | Program: | 600000 | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
Sto. Tomas | Tibal-og | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 600000 | Revised: |  | No. of Man-days:
Sto. Tomas | Tibal-og | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Sto. Tomas | Tibal-og | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Sto. Tomas | Tibal-og | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | [7 empty] | Date Allotment Released: |  | Date completed:
Sto. Tomas | Tibal-og | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | [7 empty] | Date Started:
Sto. Tomas | Talomo | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | Compl./Rep. Day Care Center, Talomo, Sto. Tomas |  | AB CY 2020 | Building |  | sq.m |  | Project Cost: | 300000 | Target Completion Date: |  | Program: | 300000 | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
Sto. Tomas | Talomo | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 300000 | Revised: |  | No. of Man-days:
Sto. Tomas | Talomo | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Sto. Tomas | Talomo | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Sto. Tomas | Talomo | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | [7 empty] | Date Allotment Released: |  | Date completed:
Sto. Tomas | Talomo | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | [7 empty] | Date Started:
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | Compl./Rep. Day Care Center, Kinamayan, Sto. Tomas |  | AB CY 2020 | Building |  | sq.m |  | Project Cost: | 300000 | Target Completion Date: |  | Program: | 300000 | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 300000 | Revised: |  | No. of Man-days:
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | [7 empty] | Date Allotment Released: |  | Date completed:
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | [7 empty] | Date Started:
Sto. Tomas | La Libertad | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | Compl./Rep. Day Care Center, La Libertad, Sto. Tomas |  | AB CY 2020 | Building |  | sq.m |  | Project Cost: | 300000 | Target Completion Date: |  | Program: | 300000 | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
Sto. Tomas | La Libertad | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 300000 | Revised: |  | No. of Man-days:
Sto. Tomas | La Libertad | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Sto. Tomas | La Libertad | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Sto. Tomas | La Libertad | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | [7 empty] | Date Allotment Released: |  | Date completed:
Sto. Tomas | La Libertad | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | [7 empty] | Date Started:
Carmen | Ising | 2nd Eng'g. Dist. | On-going | 2020-05-11 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | BAYANIHAN | Impv't of Hospital Facilities (Isolation/ICU Room) Carmen District Hospital |  | SB # 2 CY 2020 (BAYANIHAN GRANT) | Building |  | sq.m | Admin | Project Cost: | 3000000 | Target Completion Date: | 2020-08-09 | Program: | 3000000 | Planned: | 90% | No. of Persons: | 8 | On-going
Carmen | Ising | 2nd Eng'g. Dist. | On-going | 2020-05-11 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | BAYANIHAN | [7 empty] | Project Engineer: | Estorco | Revised Completion Date: |  | Allotment: | 3000000 | Revised: |  | No. of Man-days: | 240
Carmen | Ising | 2nd Eng'g. Dist. | On-going | 2020-05-11 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | BAYANIHAN | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: | 90%
Carmen | Ising | 2nd Eng'g. Dist. | On-going | 2020-05-11 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | BAYANIHAN | [7 empty] | Duration: | 90 | No. of days extended: |  |  |  | Slippage: | 0%
Carmen | Ising | 2nd Eng'g. Dist. | On-going | 2020-05-11 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | BAYANIHAN | [7 empty] | Date Allotment Released: |  | Date completed:
Carmen | Ising | 2nd Eng'g. Dist. | On-going | 2020-05-11 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | BAYANIHAN | [7 empty] | Date Started: | 2020-05-11
Samal | Peñaplata | 2nd Eng'g. Dist. | On-going | 2020-05-11 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | BAYANIHAN | Impv't of Hospital Facilities (Isolation/ICU Room) Samal District Hospital |  | SB # 2 CY 2020 (BAYANIHAN GRANT) | Building |  | sq.m | Admin | Project Cost: | 1000000 | Target Completion Date: | 2020-08-09 | Program: | 1000000 | Planned: | 80.15% | No. of Persons: | 6 | On-going
Samal | Peñaplata | 2nd Eng'g. Dist. | On-going | 2020-05-11 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | BAYANIHAN | [7 empty] | Project Engineer: | Porras/Obar | Revised Completion Date: |  | Allotment: | 1000000 | Revised: |  | No. of Man-days: | 60
Samal | Peñaplata | 2nd Eng'g. Dist. | On-going | 2020-05-11 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | BAYANIHAN | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: | 80.15%
Samal | Peñaplata | 2nd Eng'g. Dist. | On-going | 2020-05-11 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | BAYANIHAN | [7 empty] | Duration: | 90 | No. of days extended: |  |  |  | Slippage: | 0%
Samal | Peñaplata | 2nd Eng'g. Dist. | On-going | 2020-05-11 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | BAYANIHAN | [7 empty] | Date Allotment Released: |  | Date completed:
Samal | Peñaplata | 2nd Eng'g. Dist. | On-going | 2020-05-11 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | BAYANIHAN | [7 empty] | Date Started: | 2020-05-11
Carmen | Ising | 2nd Eng'g. Dist. | Completed | 2020-04-28 | 2020-07-20 | I. PROJECTS UNDER THE CURRENT APPROPRIATION | BAYANIHAN | Rehab of DavNor Pharmacy into Isolation Room Phase I |  | SB # 2 CY 2020 (BAYANIHAN GRANT) | Building |  | sq.m | Admin | Project Cost: | 1480000 | Target Completion Date: | 2020-07-20 | Program: | 1480000 | Planned: | 100% | No. of Persons: | 10 | Completed as per physical accomplishment. Financial documents still on process.
Carmen | Ising | 2nd Eng'g. Dist. | Completed | 2020-04-28 | 2020-07-20 | I. PROJECTS UNDER THE CURRENT APPROPRIATION | BAYANIHAN | [7 empty] | Project Engineer: | Andoy | Revised Completion Date: |  | Allotment: | 1480000 | Revised: |  | No. of Man-days: | 260
Carmen | Ising | 2nd Eng'g. Dist. | Completed | 2020-04-28 | 2020-07-20 | I. PROJECTS UNDER THE CURRENT APPROPRIATION | BAYANIHAN | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: | 1137930.67 | Actual: | 100%
Carmen | Ising | 2nd Eng'g. Dist. | Completed | 2020-04-28 | 2020-07-20 | I. PROJECTS UNDER THE CURRENT APPROPRIATION | BAYANIHAN | [7 empty] | Duration: | 83 | No. of days extended: |  |  |  | Slippage: | 0%
Carmen | Ising | 2nd Eng'g. Dist. | Completed | 2020-04-28 | 2020-07-20 | I. PROJECTS UNDER THE CURRENT APPROPRIATION | BAYANIHAN | [7 empty] | Date Allotment Released: |  | Date completed: | 2020-07-20
Carmen | Ising | 2nd Eng'g. Dist. | Completed | 2020-04-28 | 2020-07-20 | I. PROJECTS UNDER THE CURRENT APPROPRIATION | BAYANIHAN | [7 empty] | Date Started: | 2020-04-28
Carmen | Ising | 2nd Eng'g. Dist. | On-going | 2020-05-11 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | BAYANIHAN | Rehab of DavNor Pharmacy into Isolation Room Phase II |  | SB # 2 CY 2020 (BAYANIHAN GRANT) | Building |  | sq.m | Admin | Project Cost: | 1000000 | Target Completion Date: | 2020-07-24 | Program: | 1000000 | Planned: | 97% | No. of Persons: | 6 | On-going
Carmen | Ising | 2nd Eng'g. Dist. | On-going | 2020-05-11 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | BAYANIHAN | [7 empty] | Project Engineer: | Andoy | Revised Completion Date: | 2020-08-15 | Allotment: | 1000000 | Revised: |  | No. of Man-days: | 132
Carmen | Ising | 2nd Eng'g. Dist. | On-going | 2020-05-11 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | BAYANIHAN | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: | 664107.16 | Actual: | 97%
Carmen | Ising | 2nd Eng'g. Dist. | On-going | 2020-05-11 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | BAYANIHAN | [7 empty] | Duration: | 74 | No. of days extended: | 22 |  |  | Slippage: | 0%
Carmen | Ising | 2nd Eng'g. Dist. | On-going | 2020-05-11 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | BAYANIHAN | [7 empty] | Date Allotment Released: |  | Date completed:
Carmen | Ising | 2nd Eng'g. Dist. | On-going | 2020-05-11 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | BAYANIHAN | [7 empty] | Date Started: | 2020-05-11
[8 empty] | Installation of 15 units pre-fabricated isolation room w/ complete ameniities & accessories, DDN Hospital-Carmen Zone |  | SB # 2 CY 2020 (BAYANIHAN GRANT) | Building |  | sq.m | Admin | Project Cost: | 8314856 | Target Completion Date: | 2020-04-27 | Program: | 8314856 | Planned: | 100% | No. of Persons: | 6 | Completed as per physical accomplishment.
[15 empty] | Project Engineer: | Azotes | Revised Completion Date: | 2020-04-27 | Allotment: | 8314856 | Revised: |  | No. of Man-days: | 132
[15 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: | 664107.16 | Actual: | 100%
[15 empty] | Duration: | 28 | No. of days extended: |  |  |  | Slippage: | 0%
[15 empty] | Date Allotment Released: |  | Date completed: | 2020-04-27
[15 empty] | Date Started: | 2020-03-30

## SAMPLE-2 (PRDP) (hidden)
[12 empty] | 7470.844 |  |  |  | 887192336.03 |  |  |  | 2024781770.71 |  |  |  | 4940
[8 empty] | SECTOR: | ECONOMIC (INFRASTRUCTURE DEV'T. PROGRAM)
[8 empty] | OFFICE/AGENCY: | PROVINCIAL ENGINEER'S OFFICE
[8 empty] | AREA: | 1ST ENGINEERING DISTRICT - COMPLETED, ON-GOING AND FOR IMPLEMENTATION PROJECTS
#VALUE!
PHILIPPINE RURAL DEVELOPMENT PROJECT (PRDP)
MUNICIPALITY | BARANGAY | AREA | COMPLETED/ ON-GOING/ FOR IMPLEMENTATION/ SUSPENDED | DATE STARTED | DATE COMPLETED | APPRO- PRIATION | NOMEN- CLATURE | NAME OF PROJECT |  | SOURCE OF FUND | TYPE OF PROJECT | PHYSICAL TARGET (DESCRIPTION) |  | MODE OF IMPLEMENTATION | PROJECT DATA |  |  |  | FINANCIAL |  | PHYSICAL ACCOMPLISHMENT |  | EMPLOYMENT GENERATED |  | REMARKS
San Isidro | Sagayen | 1st Eng'g. Dist. | Completed | 2018-10-01 | 2020-04-02 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CMGP | Road upgrading Km. 9 Sagayen-Sawata (Sagayen-Jct. San Miguel Section) |  | CMGP CY 2017 | Road Concreting | 10.2 | km | Contract | Project Cost: | 139761975.14 | Target Completion Date: | 2019-08-22 23:46 | Program: | 139761975.14 | Planned: | 100% | No. of Persons: | 28 | Completed as per physical accomplishment. Financial documents still on process.
San Isidro | Sagayen | 1st Eng'g. Dist. | Completed | 2018-10-01 | 2020-04-02 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CMGP | [7 empty] | Project Engineer: | Avila | Revised Completion Date: | 2019-08-22 23:46 | Allotment: | 139761975.14 | Revised: |  | No. of Man-days: | 11170
San Isidro | Sagayen | 1st Eng'g. Dist. | Completed | 2018-10-01 | 2020-04-02 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CMGP | [7 empty] | Implementor: | Legacy Const. Corp. | No. of days suspended: | 209 | Disbursement: | 63100753.7 | Actual: | 100%
San Isidro | Sagayen | 1st Eng'g. Dist. | Completed | 2018-10-01 | 2020-04-02 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CMGP | [7 empty] | Duration: | 326 | No. of days extended: |  |  |  | Slippage: | 0%
San Isidro | Sagayen | 1st Eng'g. Dist. | Completed | 2018-10-01 | 2020-04-02 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CMGP | [7 empty] | Date Allotment Released: | CY 2017 | Date completed: | 2020-04-02
San Isidro | Sagayen | 1st Eng'g. Dist. | Completed | 2018-10-01 | 2020-04-02 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CMGP | [7 empty] | Date Started: | 2018-10-01
San Isidro | Sto. Niño | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-05-27 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | Rehab. Of Multi-Purpose Hall , Sto. Niño, San Isidro |  | 20% DF CY 2019 (STIMULUS) | Building | 182 | sq.m | Admin | Project Cost: | 500000 | Target Completion Date: | 2020-02-19 23:46 | Program: | 500000 | Planned: | 100% | No. of Persons: | 6 | Completed as per physical accomplishment. Financial documents still on process
San Isidro | Sto. Niño | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-05-27 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Project Engineer: | Aclaracion | Revised Completion Date: | 2020-02-19 23:46 | Allotment: | 500000 | Revised: |  | No. of Man-days: | 132
San Isidro | Sto. Niño | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-05-27 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Implementor: | PEO | No. of days suspended: | 28 | Disbursement: | 500000 | Actual: | 100%
San Isidro | Sto. Niño | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-05-27 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Duration: | 45 | No. of days extended: |  |  |  | Slippage: | 0%
San Isidro | Sto. Niño | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-05-27 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Allotment Released: | 2019-02-20 | Date completed: | 2020-05-27
San Isidro | Sto. Niño | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-05-27 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Started: | 2020-01-06
Tagum City | San Isidro | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-06-05 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | Const. of Women Livelihood Center, San Isidro, Tagum City |  | 20% DF CY 2019 (STIMULUS) | Building | 36.5 | sq.m | Admin | Project Cost: | 500000 | Target Completion Date: | 2020-03-21 23:46 | Program: | 500000 | Planned: | 100% | No. of Persons: | 10 | Completed as per physical accomplishment. Financial documents still on process
Tagum City | San Isidro | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-06-05 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Project Engineer: | Juan | Revised Completion Date: | 2020-06-05 23:46 | Allotment: | 500000 | Revised: | 100% | No. of Man-days: | 150
Tagum City | San Isidro | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-06-05 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Implementor: | PEO | No. of days suspended: | 28 | Disbursement: |  | Actual: | 100%
Tagum City | San Isidro | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-06-05 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Duration: | 80 | No. of days extended: | 48 |  |  | Slippage: | 0%
Tagum City | San Isidro | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-06-05 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Allotment Released: | 2019-05-29 | Date completed: | 2020-06-05
Tagum City | San Isidro | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-06-05 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Started: | 2020-01-02
New Corella | Saug | 1st Eng'g. Dist. | Completed | 2019-03-26 | 2020-06-30 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES | New Corella - Saug |  | 20% DF CY 2019 | Road Rehabilitation | 12.52 | km | Contract | Project Cost: | 6500000 | Target Completion Date: | 2019-03-26 | Program: | 6500000 | Planned: | 100% | No. of Persons: | 19 | Completed as per physical accomplishment. Financial documents still on process
New Corella | Saug | 1st Eng'g. Dist. | Completed | 2019-03-26 | 2020-06-30 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES | [7 empty] | Project Engineer: | Pilotos | Revised Completion Date: | 2019-06-10 | Allotment: | 6500000 | Revised: |  | No. of Man-days: | 570
New Corella | Saug | 1st Eng'g. Dist. | Completed | 2019-03-26 | 2020-06-30 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES | [7 empty] | Implementor: | PEO | No. of days suspended: | 28 | Disbursement: | 6500000 | Actual: | 100%
New Corella | Saug | 1st Eng'g. Dist. | Completed | 2019-03-26 | 2020-06-30 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES | [7 empty] | Duration: |  | No. of days extended: | 48 |  |  | Slippage: | 0%
New Corella | Saug | 1st Eng'g. Dist. | Completed | 2019-03-26 | 2020-06-30 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES | [7 empty] | Date Allotment Released: |  | Date completed: | 2020-06-30
New Corella | Saug | 1st Eng'g. Dist. | Completed | 2019-03-26 | 2020-06-30 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES | [7 empty] | Date Started: | 2019-03-26
Asuncion | Cabaywa | 1st Eng'g. Dist. | Completed | 2019-03-26 | 2020-06-30 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES | Jct. Monte Carlo - Upper Cabaywa - Canatan |  | 20% DF CY 2019 | Road Rehabilitation | 4.61 | km | Contract | Project Cost: | 8838000 | Target Completion Date: | 2019-03-26 | Program: | 8838000 | Planned: | 100% | No. of Persons: | 19 | Completed as per physical accomplishment. Financial documents still on process
Asuncion | Cabaywa | 1st Eng'g. Dist. | Completed | 2019-03-26 | 2020-06-30 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES | [7 empty] | Project Engineer: | Garcia | Revised Completion Date: | 2019-03-26 | Allotment: | 8838000 | Revised: |  | No. of Man-days: | 570
Asuncion | Cabaywa | 1st Eng'g. Dist. | Completed | 2019-03-26 | 2020-06-30 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES | [7 empty] | Implementor: | PEO | No. of days suspended: | 28 | Disbursement: | 8838000 | Actual: | 100%
Asuncion | Cabaywa | 1st Eng'g. Dist. | Completed | 2019-03-26 | 2020-06-30 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Asuncion | Cabaywa | 1st Eng'g. Dist. | Completed | 2019-03-26 | 2020-06-30 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES | [7 empty] | Date Allotment Released: | 2019-01-31 | Date completed: | 2020-06-30
Asuncion | Cabaywa | 1st Eng'g. Dist. | Completed | 2019-03-26 | 2020-06-30 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES | [7 empty] | Date Started: | 2019-03-26
Kapalong | Mamacao | 1st Eng'g. Dist. | On-going | 2020-02-05 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | Construction of Bleacher, Mamacao, Kapalong |  | GF CY 2018 (STIMULUS) | Bleacher |  | sq.m | Admin | Project Cost: | 500000 | Target Completion Date: | 2020-04-19 23:46 | Program: | 500000 | Planned: | 100% | No. of Persons: | 8 | Completed as per physical accomplishment. Financial documents still on process.
Kapalong | Mamacao | 1st Eng'g. Dist. | On-going | 2020-02-05 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Project Engineer: | Ambrosio | Revised Completion Date: | 2020-06-15 23:46 | Allotment: | 500000 | Revised: |  | No. of Man-days: | 120
Kapalong | Mamacao | 1st Eng'g. Dist. | On-going | 2020-02-05 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: |  | Actual: | 100%
Kapalong | Mamacao | 1st Eng'g. Dist. | On-going | 2020-02-05 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Duration: | 75 | No. of days extended: | 30 |  |  | Slippage:
Kapalong | Mamacao | 1st Eng'g. Dist. | On-going | 2020-02-05 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Date Allotment Released: |  | Date completed:
Kapalong | Mamacao | 1st Eng'g. Dist. | On-going | 2020-02-05 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Date Started: | 2020-02-05
Kapalong | Capungagan | 1st Eng'g. Dist. | On-going | 2016-04-06 | 2020-07-27 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PRDP | Rehab. Of Capungagan-Boundary San Miguel FMR, Kapalong, Davao del Norte |  | PRDP CY 2015 | Road Concreting | 10.6 | km | Contract | Project Cost: | 108303841.7 | Target Completion Date: | 2020-02-14 23:46 | Program: | 108303841.7 | Planned: | 100% | No. of Persons: | 38 | Completed as physical accomplishment; for rectification
Kapalong | Capungagan | 1st Eng'g. Dist. | On-going | 2016-04-06 | 2020-07-27 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PRDP | [7 empty] | Project Engineer: | Nasol | Revised Completion Date: | 2023-05-24 23:46 | Allotment: | 108303841.7 | Revised: | 100% | No. of Man-days: | 1140
Kapalong | Capungagan | 1st Eng'g. Dist. | On-going | 2016-04-06 | 2020-07-27 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PRDP | [7 empty] | Implementor: | VICLAO | No. of days suspended: | 140 | Disbursement: | 60050673.93 | Actual: | 100%
Kapalong | Capungagan | 1st Eng'g. Dist. | On-going | 2016-04-06 | 2020-07-27 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PRDP | [7 empty] | Duration: | 1410 | No. of days extended: | 1055 |  |  | Slippage: | 100%
Kapalong | Capungagan | 1st Eng'g. Dist. | On-going | 2016-04-06 | 2020-07-27 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PRDP | [7 empty] | Date Allotment Released: | CY 2015 | Date completed: | 2020-07-27
Kapalong | Capungagan | 1st Eng'g. Dist. | On-going | 2016-04-06 | 2020-07-27 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PRDP | [7 empty] | Date Started: | 2016-04-06
New Corella | Limbaan | 1st Eng'g. Dist. | On-going | 2019-04-08 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PRDP | Rehab. Of Pob.-Limbaan-Suawon-Macgum FMR w/ Bridge (42 ln.m), New Corella, Davao del Norte |  | PRDP CY 2015 | Road Concreting | 15.01 | km | Contract | Project Cost: | 205202114.16 | Target Completion Date: | 2019-01-18 | Program: | 205202114.16 | Planned: | 100% | No. of Persons: | 40 | On-going (Increase of Project Cost due to Variation Order Php 14,948,622.18, Partial suspension due to soft soil from sta. 8+000 - 10+000); (Suspended last April 5, 2020 due to COVID; Resumption Order dated June 1, 2020)
New Corella | Limbaan | 1st Eng'g. Dist. | On-going | 2019-04-08 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PRDP | [7 empty] | Project Engineer: | Madrigal | Revised Completion Date: | 2021-01-06 | Allotment: | 205202114.16 | Revised: | 83.77% | No. of Man-days: | 1200
New Corella | Limbaan | 1st Eng'g. Dist. | On-going | 2019-04-08 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PRDP | [7 empty] | Implementor: | Dvo. Rock Mixer | No. of days suspended: | 229 | Disbursement: | 141497191.47 | Actual: | 77.49%
New Corella | Limbaan | 1st Eng'g. Dist. | On-going | 2019-04-08 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PRDP | [7 empty] | Duration: | 1529 | No. of days extended: | 490 |  |  | Slippage: | -6.282%
New Corella | Limbaan | 1st Eng'g. Dist. | On-going | 2019-04-08 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PRDP | [7 empty] | Date Allotment Released: | CY 2015 | Date completed:
New Corella | Limbaan | 1st Eng'g. Dist. | On-going | 2019-04-08 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PRDP | [7 empty] | Date Started: | 2016-04-08
Asuncion | Sonlon-Camansa | 1st Eng'g. Dist. | On-going | 2019-03-28 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PRDP | Rehab. Of Sonlon - Camansa FMR Asuncion, Davao del Norte |  | PRDP CY 2015 | Road Concreting | 10.23 | km | Contract | Project Cost: | 215125015.81 | Target Completion Date: | 2020-06-15 | Program: | 215125015.81 | Planned: | 39.51% | No. of Persons: | 30 | On-going (Suspended last April 5, 2020 due to COVID; Resumption Order dated June 1, 2020)
Asuncion | Sonlon-Camansa | 1st Eng'g. Dist. | On-going | 2019-03-28 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PRDP | [7 empty] | Project Engineer: | Fabiala | Revised Completion Date: | 2020-06-15 | Allotment: | 215125015.81 | Revised: |  | No. of Man-days: | 780
Asuncion | Sonlon-Camansa | 1st Eng'g. Dist. | On-going | 2019-03-28 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PRDP | [7 empty] | Implementor: | Three w/Builders, Inc/Davao Rock Mixer Enterprises (JV) | No. of days suspended: |  | Disbursement: | 40523099.23 | Actual: | 31.6%
Asuncion | Sonlon-Camansa | 1st Eng'g. Dist. | On-going | 2019-03-28 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PRDP | [7 empty] | Duration: | 384 | No. of days extended: |  |  |  | Slippage: | -7.91%
Asuncion | Sonlon-Camansa | 1st Eng'g. Dist. | On-going | 2019-03-28 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PRDP | [7 empty] | Date Allotment Released: | 2018-09-18 | Date completed:
Asuncion | Sonlon-Camansa | 1st Eng'g. Dist. | On-going | 2019-03-28 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PRDP | [7 empty] | Date Started: | 2019-05-28
Kapalong | Capungagan | 1st Eng'g. Dist. | On-going | 2019-03-19 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PRDP | Cacao Production and Beans Marketing, Capungagan, Kapalong, Davao del Norte |  | PRDP CY 2016 | Building | 3610 | sq.m | Contract | Project Cost: | 5873626.8 | Target Completion Date: | 2019-11-24 | Program: | 5873626.8 | Planned: | 100% | No. of Persons: |  | Completed as per physical accomplishment; For final Inspection
Kapalong | Capungagan | 1st Eng'g. Dist. | On-going | 2019-03-19 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PRDP | [7 empty] | Project Engineer: | Delos Reyes | Revised Completion Date: | 2020-07-20 | Allotment: | 5873626.8 | Revised: |  | No. of Man-days:
Kapalong | Capungagan | 1st Eng'g. Dist. | On-going | 2019-03-19 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PRDP | [7 empty] | Implementor: | MICAH CONST. & SUPPLY | No. of days suspended: | 239 | Disbursement: | 4698901.44 | Actual: | 100%
Kapalong | Capungagan | 1st Eng'g. Dist. | On-going | 2019-03-19 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PRDP | [7 empty] | Duration: | 250 | No. of days extended: |  |  |  | Slippage: | 100%
Kapalong | Capungagan | 1st Eng'g. Dist. | On-going | 2019-03-19 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PRDP | [7 empty] | Date Allotment Released: | CY 2016 | Date completed: | 2020-07-20
Kapalong | Capungagan | 1st Eng'g. Dist. | On-going | 2019-03-19 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PRDP | [7 empty] | Date Started: | 2019-03-19
New Corella | Poblacion | 1st Eng'g. Dist. | On-going | 2019-01-17 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PRDP | Improvement of New Corella Nursery with Organic Input Production & Common Facility, Davao del Norte |  | PRDP CY 2016 | Building | 1901 | sq.m | Contract | Project Cost: | 9889628.45 | Target Completion Date: | 2019-11-23 | Program: | 9889628.45 | Planned: | 80.36% | No. of Persons: | 10 | On-going (Suspended last April 5, 2020 due to COVID; Resumption Order dated June 1, 2020)
New Corella | Poblacion | 1st Eng'g. Dist. | On-going | 2019-01-17 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PRDP | [7 empty] | Project Engineer: | Delos Reyes/Cabañero | Revised Completion Date: | 2020-08-09 | Allotment: | 9889628.45 | Revised: | 49.99% | No. of Man-days: | 250
New Corella | Poblacion | 1st Eng'g. Dist. | On-going | 2019-01-17 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PRDP | [7 empty] | Implementor: | SOUTH IRONROCK CORPORATION | No. of days suspended: | 260 | Disbursement: |  | Actual: | 46.3%
New Corella | Poblacion | 1st Eng'g. Dist. | On-going | 2019-01-17 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PRDP | [7 empty] | Duration: | 310 | No. of days extended: |  |  |  | Slippage: | -3.684%
New Corella | Poblacion | 1st Eng'g. Dist. | On-going | 2019-01-17 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PRDP | [7 empty] | Date Allotment Released: | CY 2016 | Date completed:
New Corella | Poblacion | 1st Eng'g. Dist. | On-going | 2019-01-17 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PRDP | [7 empty] | Date Started: | 2019-01-17
Tagum City | Pandapan | 1st Eng'g. Dist. | On-going |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPPAP-PAMANA | Const. of Trading Post, Storage Building with (1) unit Hauling Truck, Brgy. Pandapan |  | OPPAP-PAMANA CY 2017 | Building |  | sq.m | Contract | Project Cost: | 3975000 | Target Completion Date: | 0 | Program: | 3975000 | Planned: |  | No. of Persons: |  | Abstract 1220194004 (Tagum Builders);PO # 2019102828 - Truck
Tagum City | Pandapan | 1st Eng'g. Dist. | On-going |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPPAP-PAMANA | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 3975000 | Revised: |  | No. of Man-days:
Tagum City | Pandapan | 1st Eng'g. Dist. | On-going |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPPAP-PAMANA | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Tagum City | Pandapan | 1st Eng'g. Dist. | On-going |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPPAP-PAMANA | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Tagum City | Pandapan | 1st Eng'g. Dist. | On-going |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPPAP-PAMANA | [7 empty] | Date Allotment Released: | CY 2017 | Date completed:
Tagum City | Pandapan | 1st Eng'g. Dist. | On-going |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPPAP-PAMANA | [7 empty] | Date Started:
Kapalong |  | 1st Eng'g. Dist. | On-going | 2016-06-01 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPPAP-PAMANA | Construction of Biga Bridges, Kapalong (Original Contract Cost: P 24,959,503.45; Variation Order: P 4,067,412.00) |  | OPPAP-PAMANA CY 2014 | Road |  | km | Contract | Project Cost: | 29026915.45 | Target Completion Date: | 2018-07-30 23:59 | Program: | 29026915.45 | Planned: | 100% | No. of Persons: | 8 | Suspended due to RROW
Kapalong |  | 1st Eng'g. Dist. | On-going | 2016-06-01 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPPAP-PAMANA | [7 empty] | Project Engineer: | Limpo | Revised Completion Date: | 2020-03-25 23:59 | Allotment: | 29026915.45 | Revised: | 99.7% | No. of Man-days: | 290
Kapalong |  | 1st Eng'g. Dist. | On-going | 2016-06-01 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPPAP-PAMANA | [7 empty] | Implementor: | Davao Rock Mixer | No. of days suspended: | 604 | Disbursement: | 18489834.55 | Actual: | 85.37%
Kapalong |  | 1st Eng'g. Dist. | On-going | 2016-06-01 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPPAP-PAMANA | [7 empty] | Duration: | 760 | No. of days extended: |  |  |  | Slippage: | -14.33%
Kapalong |  | 1st Eng'g. Dist. | On-going | 2016-06-01 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPPAP-PAMANA | [7 empty] | Date Allotment Released: | CY 2014 | Date completed:
Kapalong |  | 1st Eng'g. Dist. | On-going | 2016-06-01 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPPAP-PAMANA | [7 empty] | Date Started: | 2016-07-01
Asuncion | Canatan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | QRF | Repair of Damaged Drainage/Creeks of Canatan, Asuncion |  | QRF CY 2015 & 2016 | Drainage/Creeks |  | km |  | Project Cost: | 137754.69 | Target Completion Date: | 0 | Program: | 137754.69 | Planned: |  | No. of Persons: |  | PO#2020061983 - FL2 LUMBER & CONST. SUPPLY; PO #2020062164 - jkle enterprises
Asuncion | Canatan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | QRF | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 137754.69 | Revised: |  | No. of Man-days:
Asuncion | Canatan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | QRF | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Asuncion | Canatan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | QRF | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Asuncion | Canatan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | QRF | [7 empty] | Date Allotment Released: |  | Date completed:
Asuncion | Canatan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | QRF | [7 empty] | Date Started:
Asuncion | Sagayen | 1st Eng'g. Dist. | On-going | 2018-11-15 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | QRF | Construction of Water Reservoir & Purchase of P.E. Pipelines, Sagayen, Asuncion |  | 20% DF CY 2017 (STIMULUS) | Water System |  |  | MLGU | Project Cost: | 500000 | Target Completion Date: | 2018-11-15 | Program: | 500000 | Planned: | 90% | No. of Persons: |  | Suspended due to non availability of water source during drilling.Find another location. Fund already transferred at Municipality of Asuncion with ChecK No. 2445174 and OR # 9238468,
Asuncion | Sagayen | 1st Eng'g. Dist. | On-going | 2018-11-15 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | QRF | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Asuncion | Sagayen | 1st Eng'g. Dist. | On-going | 2018-11-15 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | QRF | [7 empty] | Implementor: | MEO | No. of days suspended: |  | Disbursement: |  | Actual: | 90%
Asuncion | Sagayen | 1st Eng'g. Dist. | On-going | 2018-11-15 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | QRF | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Asuncion | Sagayen | 1st Eng'g. Dist. | On-going | 2018-11-15 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | QRF | [7 empty] | Date Allotment Released: | 2017-12-28 | Date completed:
Asuncion | Sagayen | 1st Eng'g. Dist. | On-going | 2018-11-15 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | QRF | [7 empty] | Date Started: | 2018-11-15
New Corella | Sta. Fe | 1st Eng'g. Dist. | On-going |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2017 | Road Rehabilitation at Prk. 1-Prk. 5, Sta. Fe, New Corella |  | 20% DF CY 2017 (STIMULUS) | Court |  |  | MLGU | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Fund already transferred at Municipality of Talaingod with ChecK No. 2445181 and OR # 7955667, dated March 16, 2018 . Amended from Electrification @ Prk. 1A-Prk. 5A)
New Corella | Sta. Fe | 1st Eng'g. Dist. | On-going |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2017 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 500000 | Revised: |  | No. of Man-days:
New Corella | Sta. Fe | 1st Eng'g. Dist. | On-going |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2017 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
New Corella | Sta. Fe | 1st Eng'g. Dist. | On-going |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2017 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | Sta. Fe | 1st Eng'g. Dist. | On-going |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2017 | [7 empty] | Date Allotment Released: | 2017-12-28 | Date completed:
New Corella | Sta. Fe | 1st Eng'g. Dist. | On-going |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2017 | [7 empty] | Date Started:
Talaingod | Palma Gil | 1st Eng'g. Dist. | On-going |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2017 | Const. of Covered Court Bleacher, Palma Gil, Talaingod |  | 20% DF CY 2017 | Court |  |  | MLGU | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | On-going (Fund already transferred at Municipality of Talaingod with ChecK No. 2445181 and OR # 7955667, dated March 16, 2018 . Amended from Electrification @ Prk. 1A-Prk. 5A
Talaingod | Palma Gil | 1st Eng'g. Dist. | On-going |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2017 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 500000 | Revised: |  | No. of Man-days:
Talaingod | Palma Gil | 1st Eng'g. Dist. | On-going |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2017 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Talaingod | Palma Gil | 1st Eng'g. Dist. | On-going |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2017 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Talaingod | Palma Gil | 1st Eng'g. Dist. | On-going |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2017 | [7 empty] | Date Allotment Released: | 2017-12-28 | Date completed:
Talaingod | Palma Gil | 1st Eng'g. Dist. | On-going |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2017 | [7 empty] | Date Started:
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2019-11-04 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./REHAB./COMP. OF VARIOUS GOV'T. BLDGS. STRUCT., FAC (Provincewide) LS - P9,000,000.00 | Rehab. Of PEO Training Center, (PDPM),Mankilam, Tagum City, (Part of P803,000.00)(20% DF CY 2018-P326,124.00) |  | 20% DF CY 2017 | Building | 85 | sq.m | Admin | Project Cost: | 476876 | Target Completion Date: | 2020-01-17 | Program: | 476876 | Planned: | 99% | No. of Persons: | 3 | Suspended (additional PR for Elect. Mat.) dated March 9, 2020
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2019-11-04 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./REHAB./COMP. OF VARIOUS GOV'T. BLDGS. STRUCT., FAC (Provincewide) LS - P9,000,000.00 | [7 empty] | Project Engineer: | Chua | Revised Completion Date: | 2020-03-15 | Allotment: | 476876 | Revised: |  | No. of Man-days: | 57
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2019-11-04 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./REHAB./COMP. OF VARIOUS GOV'T. BLDGS. STRUCT., FAC (Provincewide) LS - P9,000,000.00 | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: | 407521.7 | Actual: | 99%
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2019-11-04 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./REHAB./COMP. OF VARIOUS GOV'T. BLDGS. STRUCT., FAC (Provincewide) LS - P9,000,000.00 | [7 empty] | Duration: | 74 | No. of days extended: | 58 |  |  | Slippage: | 0%
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2019-11-04 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./REHAB./COMP. OF VARIOUS GOV'T. BLDGS. STRUCT., FAC (Provincewide) LS - P9,000,000.00 | [7 empty] | Date Allotment Released: | 2019-02-12 | Date completed:
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2019-11-04 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./REHAB./COMP. OF VARIOUS GOV'T. BLDGS. STRUCT., FAC (Provincewide) LS - P9,000,000.00 | [7 empty] | Date Started: | 2019-11-04
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2018-07-17 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./REHAB./COMP. OF VARIOUS GOV'T. BLDGS. STRUCT., FAC (Provincewide) LS - P9,000,000.00 | Upgrading of DDNSTC (Basketball/Voleyball MP Covered Court),Sports Center, Mankilam, Tagum City |  | SB # 4 CY 2017 | Covered Court | 2252.69 | sq.m | Contract | Project Cost: | 99992356.64 | Target Completion Date: | 2019-07-11 | Program: | 99992356.64 | Planned: | 100% | No. of Persons: | 10 | On-going (Suspended last April 5, 2020 due to COVID; Resumption Order dated May 4, 2020)
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2018-07-17 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./REHAB./COMP. OF VARIOUS GOV'T. BLDGS. STRUCT., FAC (Provincewide) LS - P9,000,000.00 | [7 empty] | Project Engineer: | Daral | Revised Completion Date: |  | Allotment: | 99992356.64 | Revised: |  | No. of Man-days: | 310
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2018-07-17 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./REHAB./COMP. OF VARIOUS GOV'T. BLDGS. STRUCT., FAC (Provincewide) LS - P9,000,000.00 | [7 empty] | Implementor: | YBC | No. of days suspended: |  | Disbursement: | 18280402.33 | Actual: | 73.04%
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2018-07-17 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./REHAB./COMP. OF VARIOUS GOV'T. BLDGS. STRUCT., FAC (Provincewide) LS - P9,000,000.00 | [7 empty] | Duration: | 360 | No. of days extended: | 20 |  |  | Slippage: | -26.96%
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2018-07-17 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./REHAB./COMP. OF VARIOUS GOV'T. BLDGS. STRUCT., FAC (Provincewide) LS - P9,000,000.00 | [7 empty] | Date Allotment Released: | 2018-10-16 | Date completed:
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2018-07-17 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./REHAB./COMP. OF VARIOUS GOV'T. BLDGS. STRUCT., FAC (Provincewide) LS - P9,000,000.00 | [7 empty] | Date Started: | 2018-07-17
Asuncion | Saug | 1st Eng'g. Dist. | On-going | 2019-01-03 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | QRF | Rehab. Of Saug Bridge of Slope Protection |  | QRF CY 2017 | Slope Protection | 356.4 | ln.m | Admin | Project Cost: | 4850000 | Target Completion Date: | 2019-05-02 23:46 | Program: | 4850000 | Planned: | 84.06% | No. of Persons: | 13 | On-going (Suspended dated January 28, 2019; Resumption February 3, 2020; Resumption Order dated May 4, 2020; Suspended last April 5, 2020 due to COVID; resumption order dated May 4, 2020)
Asuncion | Saug | 1st Eng'g. Dist. | On-going | 2019-01-03 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | QRF | [7 empty] | Project Engineer: | Gone | Revised Completion Date: | 2020-08-19 23:46 | Allotment: | 4850000 | Revised: |  | No. of Man-days: | 195
Asuncion | Saug | 1st Eng'g. Dist. | On-going | 2019-01-03 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | QRF | [7 empty] | Implementor: | PEO | No. of days suspended: | 400 | Disbursement: | 1628912.92 | Actual: | 77.63%
Asuncion | Saug | 1st Eng'g. Dist. | On-going | 2019-01-03 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | QRF | [7 empty] | Duration: | 120 | No. of days extended: | 75 |  |  | Slippage: | -6.43%
Asuncion | Saug | 1st Eng'g. Dist. | On-going | 2019-01-03 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | QRF | [7 empty] | Date Allotment Released: | 2018-05-25 | Date completed:
Asuncion | Saug | 1st Eng'g. Dist. | On-going | 2019-01-03 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | QRF | [7 empty] | Date Started: | 2019-01-03
Kapalong | Gupitan | 1st Eng'g. Dist. | On-going | 2019-02-22 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | QRF | Re-channeling of BIGA River with Earth Dike and Slope Protection, Brgy. Gupitan, Kaplaong |  | QRF CY 2017 | Slope Protection | 0.9 | ln.m | Contract | Project Cost: | 12100000 | Target Completion Date: | 2019-06-11 23:46 | Program: | 12100000 | Planned: | 8.3% | No. of Persons: | 4 | On-going (Suspended last April 5, 2020 due to COVID; resumption order dated May 4, 2020)
Kapalong | Gupitan | 1st Eng'g. Dist. | On-going | 2019-02-22 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | QRF | [7 empty] | Project Engineer: | Limpo | Revised Completion Date: | 2019-06-11 23:46 | Allotment: | 12100000 | Revised: |  | No. of Man-days: | 120
Kapalong | Gupitan | 1st Eng'g. Dist. | On-going | 2019-02-22 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | QRF | [7 empty] | Implementor: | Alpha & Omega | No. of days suspended: |  | Disbursement: |  | Actual: | 3.36%
Kapalong | Gupitan | 1st Eng'g. Dist. | On-going | 2019-02-22 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | QRF | [7 empty] | Duration: | 110 | No. of days extended: |  |  |  | Slippage: | -4.94%
Kapalong | Gupitan | 1st Eng'g. Dist. | On-going | 2019-02-22 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | QRF | [7 empty] | Date Allotment Released: | 2018-07-20 | Date completed:
Kapalong | Gupitan | 1st Eng'g. Dist. | On-going | 2019-02-22 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | QRF | [7 empty] | Date Started: | 2019-02-22
San Isidro | Linao | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | WATER SYSTEM LS - P 10,000,000.00 | Const. of PWS Linao, San Isidro |  | 20% DF CY 2018 | geo-resistivty/drillig |  |  | Admin | Project Cost: | 62000 | Target Completion Date: |  | Program: | 62000 | Planned: |  | No. of Persons: |  | For implementation
San Isidro | Linao | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | WATER SYSTEM LS - P 10,000,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 62000 | Revised: |  | No. of Man-days:
San Isidro | Linao | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | WATER SYSTEM LS - P 10,000,000.00 | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual:
San Isidro | Linao | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | WATER SYSTEM LS - P 10,000,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
San Isidro | Linao | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | WATER SYSTEM LS - P 10,000,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
San Isidro | Linao | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | WATER SYSTEM LS - P 10,000,000.00 | [7 empty] | Date Started:
San Isidro | Mamalian | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | WATER SYSTEM LS - P 10,000,000.00 | Const. of PWS Mamalian, San Isidro |  | 20% DF CY 2018 | geo-resistivty/drillig |  |  | Admin | Project Cost: | 62000 | Target Completion Date: |  | Program: | 62000 | Planned: |  | No. of Persons: |  | For declaration of savings because the spring water source is not feasible for development.
San Isidro | Mamalian | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | WATER SYSTEM LS - P 10,000,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 62000 | Revised: |  | No. of Man-days:
San Isidro | Mamalian | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | WATER SYSTEM LS - P 10,000,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
San Isidro | Mamalian | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | WATER SYSTEM LS - P 10,000,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
San Isidro | Mamalian | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | WATER SYSTEM LS - P 10,000,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
San Isidro | Mamalian | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | WATER SYSTEM LS - P 10,000,000.00 | [7 empty] | Date Started:
San Isidro | Sagayen | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | WATER SYSTEM LS - P 10,000,000.00 | Const. of PWS Sagayen, San Isidro |  | 20% DF CY 2018 | geo-resistivty/drillig |  |  | Admin | Project Cost: | 62000 | Target Completion Date: |  | Program: | 62000 | Planned: |  | No. of Persons: |  | For implementation
San Isidro | Sagayen | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | WATER SYSTEM LS - P 10,000,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 62000 | Revised: |  | No. of Man-days:
San Isidro | Sagayen | 1st Eng'g. Dist. | For Implementation |  | 0 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | WATER SYSTEM LS - P 10,000,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
San Isidro | Sagayen | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | WATER SYSTEM LS - P 10,000,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
San Isidro | Sagayen | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | WATER SYSTEM LS - P 10,000,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
San Isidro | Sagayen | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | WATER SYSTEM LS - P 10,000,000.00 | [7 empty] | Date Started:
Tagum City | Pandapan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | WATER SYSTEM LS - P 10,000,000.00 | Installation of potable water System at Purok Nangka, Pandapan, Tagum City |  | 20% DF CY 2018 | Water System |  |  | Admin | Project Cost: | 1125000 | Target Completion Date: |  | Program: | 1125000 | Planned: |  | No. of Persons: |  | Waiting for deed of donation. Follow-up letter was already issued
Tagum City | Pandapan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | WATER SYSTEM LS - P 10,000,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 1125000 | Revised: |  | No. of Man-days:
Tagum City | Pandapan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | WATER SYSTEM LS - P 10,000,000.00 | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual:
Tagum City | Pandapan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | WATER SYSTEM LS - P 10,000,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Tagum City | Pandapan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | WATER SYSTEM LS - P 10,000,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Tagum City | Pandapan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | WATER SYSTEM LS - P 10,000,000.00 | [7 empty] | Date Started:
Asuncion | San Vicente | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | WATER SYSTEM LS - P 10,000,000.00 | Rehab./Impv't. of San Vicente Water System, Asuncion |  | 20% DF CY 2018 | Water System |  |  | Admin | Project Cost: | 1125000 | Target Completion Date: |  | Program: | 1125000 | Planned: |  | No. of Persons: |  | Abstract # 0220190484 still draft
Asuncion | San Vicente | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | WATER SYSTEM LS - P 10,000,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 1125000 | Revised: |  | No. of Man-days:
Asuncion | San Vicente | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | WATER SYSTEM LS - P 10,000,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Asuncion | San Vicente | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | WATER SYSTEM LS - P 10,000,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Asuncion | San Vicente | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | WATER SYSTEM LS - P 10,000,000.00 | [7 empty] | Date Allotment Released: | 2018-10-26 | Date completed:
Asuncion | San Vicente | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | WATER SYSTEM LS - P 10,000,000.00 | [7 empty] | Date Started:
Asuncion | Sonlon-Camansa | 1st Eng'g. Dist. | On-going | 2019-05-28 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PRDP | Rehab. Of Sonlon-Camansa FMR, Asuncion, Davao del Norte (PRDP Counterpart : 193,612,514.23) |  | 20% DF CY 2018 | Road Concreting | 10.23 | km | Contract | Project Cost: | 215125015.81 | Target Completion Date: | 2020-06-14 23:46 | Program: | 215125015.81 | Planned: | 39.51% | No. of Persons: | 30 | On-going
Asuncion | Sonlon-Camansa | 1st Eng'g. Dist. | On-going | 2019-05-28 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PRDP | [7 empty] | Project Engineer: | Fabiala | Revised Completion Date: | 2020-06-14 23:46 | Allotment: | 215125015.81 | Revised: |  | No. of Man-days: | 690
Asuncion | Sonlon-Camansa | 1st Eng'g. Dist. | On-going | 2019-05-28 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PRDP | [7 empty] | Implementor: | Three w/Builders, Inc/Davao Rock Mixer Enterprises (JV) | No. of days suspended: |  | Disbursement: | 4502566.58 | Actual: | 31.6%
Asuncion | Sonlon-Camansa | 1st Eng'g. Dist. | On-going | 2019-05-28 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PRDP | [7 empty] | Duration: | 384 | No. of days extended: |  |  |  | Slippage: | -7.91%
Asuncion | Sonlon-Camansa | 1st Eng'g. Dist. | On-going | 2019-05-28 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PRDP | [7 empty] | Date Allotment Released: | 2018-09-18 | Date completed:
Asuncion | Sonlon-Camansa | 1st Eng'g. Dist. | On-going | 2019-05-28 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PRDP | [7 empty] | Date Started: | 2019-05-28
San Isidro | Sagayen-Sawata | 1st Eng'g. Dist. | On-going | 2019-09-09 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | KALSADA | Impvt. of Km. 9 Sagayen - Sawata Provincial Road Phase II |  | 20% DF CY 2018 | Road Concreting | 1.303 | km | Admin | Project Cost: | 7742775.95 | Target Completion Date: | 2020-03-27 | Program: | 7742775.95 | Planned: | 45% | No. of Persons: | 6 | Suspended dated March 6, 2020 due to delay delivery of materials
San Isidro | Sagayen-Sawata | 1st Eng'g. Dist. | On-going | 2019-09-09 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | KALSADA | [7 empty] | Project Engineer: | Kenny | Revised Completion Date: |  | Allotment: | 7742775.95 | Revised: |  | No. of Man-days: | 138
San Isidro | Sagayen-Sawata | 1st Eng'g. Dist. | On-going | 2019-09-09 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | KALSADA | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: | 2603417.9455 | Actual: | 35.05%
San Isidro | Sagayen-Sawata | 1st Eng'g. Dist. | On-going | 2019-09-09 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | KALSADA | [7 empty] | Duration: | 200 | No. of days extended: |  |  |  | Slippage: | -9.95%
San Isidro | Sagayen-Sawata | 1st Eng'g. Dist. | On-going | 2019-09-09 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | KALSADA | [7 empty] | Date Allotment Released: | 2019-01-31 | Date completed:
San Isidro | Sagayen-Sawata | 1st Eng'g. Dist. | On-going | 2019-09-09 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | KALSADA | [7 empty] | Date Started: | 2019-09-09
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2019-11-04 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./REHAB./COMP. OF VARIOUS GOV'T. BLDGS. STRUCT., FAC (Provincewide) LS - LS - P13,523,124.00 | Rehab. Of PEO Training Center, (PDPM),Mankilam, Tagum City (Part of P803,000.00)(20% DF CY 2017-P476,876.00) |  | 20% DF CY 2018 | Building | 85 | sq.m | Admin | Project Cost: | 326124 | Target Completion Date: | 2020-01-17 | Program: | 326124 | Planned: |  | No. of Persons: |  | suspended due to additional materials for electrical works
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2019-11-04 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./REHAB./COMP. OF VARIOUS GOV'T. BLDGS. STRUCT., FAC (Provincewide) LS - P13,523,124.00 | [7 empty] | Project Engineer: | Chua | Revised Completion Date: | 2020-03-14 | Allotment: | 326124 | Revised: |  | No. of Man-days:
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2019-11-04 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./REHAB./COMP. OF VARIOUS GOV'T. BLDGS. STRUCT., FAC (Provincewide) LS - P13,523,124.00 | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual:
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2019-11-04 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./REHAB./COMP. OF VARIOUS GOV'T. BLDGS. STRUCT., FAC (Provincewide) LS - P13,523,124.00 | [7 empty] | Duration: | 74 | No. of days extended: | 57 |  |  | Slippage: | 0%
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2019-11-04 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./REHAB./COMP. OF VARIOUS GOV'T. BLDGS. STRUCT., FAC (Provincewide) LS - P13,523,124.00 | [7 empty] | Date Allotment Released: | 2019-02-12 | Date completed:
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2019-11-04 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./REHAB./COMP. OF VARIOUS GOV'T. BLDGS. STRUCT., FAC (Provincewide) LS - P13,523,124.00 | [7 empty] | Date Started: | 2019-11-04
Asuncion | Camansa | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./REHAB./COMP. OF VARIOUS GOV'T. BLDGS. STRUCT., FAC (Provincewide) LS - LS - P13,523,124.00 | Construction of IP Tribal Council of Women at Brgy. Camansa, Asuncion |  | 20% DF CY 2018 | Building |  | sq.m | Admin | Project Cost: | 560000 | Target Completion Date: |  | Program: | 560000 | Planned: |  | No. of Persons: |  | Purchase Request # 20032714
Asuncion | Camansa | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./REHAB./COMP. OF VARIOUS GOV'T. BLDGS. STRUCT., FAC (Provincewide) LS - P13,523,124.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 560000 | Revised: |  | No. of Man-days:
Asuncion | Camansa | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./REHAB./COMP. OF VARIOUS GOV'T. BLDGS. STRUCT., FAC (Provincewide) LS - P13,523,124.00 | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual:
Asuncion | Camansa | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./REHAB./COMP. OF VARIOUS GOV'T. BLDGS. STRUCT., FAC (Provincewide) LS - P13,523,124.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Asuncion | Camansa | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./REHAB./COMP. OF VARIOUS GOV'T. BLDGS. STRUCT., FAC (Provincewide) LS - P13,523,124.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Asuncion | Camansa | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./REHAB./COMP. OF VARIOUS GOV'T. BLDGS. STRUCT., FAC (Provincewide) LS - P13,523,124.00 | [7 empty] | Date Started:
New Corella | Del Monte | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | RURAL ELECTRIFICATION (Provincewide) LS - P5,000,000.00 | Rural Electrification at Del Monte, New Corella |  | 20% DF CY 2018 | Electrification |  |  | Contract | Project Cost: | 1000000 | Target Completion Date: |  | Program: | 1000000 | Planned: |  | No. of Persons: |  | Post Qualification on process
New Corella | Del Monte | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | RURAL ELECTRIFICATION (Provincewide) LS - P5,000,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 1000000 | Revised: |  | No. of Man-days:
New Corella | Del Monte | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | RURAL ELECTRIFICATION (Provincewide) LS - P5,000,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
New Corella | Del Monte | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | RURAL ELECTRIFICATION (Provincewide) LS - P5,000,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | Del Monte | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | RURAL ELECTRIFICATION (Provincewide) LS - P5,000,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
New Corella | Del Monte | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | RURAL ELECTRIFICATION (Provincewide) LS - P5,000,000.00 | [7 empty] | Date Started:
Asuncion | Camansa | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | RURAL ELECTRIFICATION (Provincewide) LS - P5,000,000.00 | Const. of Distribution Line in Sitio Prk. 1,3,4, 11 and 7, Camansa, Asuncion |  | 20% DF CY 2018 | Electrification |  |  | Contract | Project Cost: | 4000000 | Target Completion Date: |  | Program: | 4000000 | Planned: |  | No. of Persons: |  | Purchase Request # 19093670 (On process )
Asuncion | Camansa | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | RURAL ELECTRIFICATION (Provincewide) LS - P5,000,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 4000000 | Revised: |  | No. of Man-days:
Asuncion | Camansa | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | RURAL ELECTRIFICATION (Provincewide) LS - P5,000,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Asuncion | Camansa | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | RURAL ELECTRIFICATION (Provincewide) LS - P5,000,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Asuncion | Camansa | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | RURAL ELECTRIFICATION (Provincewide) LS - P5,000,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Asuncion | Camansa | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | RURAL ELECTRIFICATION (Provincewide) LS - P5,000,000.00 | [7 empty] | Date Started:
Talaingod | Palma Gil | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./REHAB./COMP. OF VARIOUS GOV'T. BLDGS. STRUCT., FAC (Provincewide) | Const. of Standard Quarantine Shed for Car Bath Natulian, Brgy. Palma Gil, Talaingod |  | 20% DF CY 2018 | Car Bath |  |  | Contract | Project Cost: | 200000 | Target Completion Date: |  | Program: | 200000 | Planned: |  | No. of Persons: |  | Awarded to DIGOS CONSTRAK
Talaingod | Palma Gil | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./REHAB./COMP. OF VARIOUS GOV'T. BLDGS. STRUCT., FAC (Provincewide) | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 200000 | Revised: |  | No. of Man-days:
Talaingod | Palma Gil | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./REHAB./COMP. OF VARIOUS GOV'T. BLDGS. STRUCT., FAC (Provincewide) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Talaingod | Palma Gil | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./REHAB./COMP. OF VARIOUS GOV'T. BLDGS. STRUCT., FAC (Provincewide) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Talaingod | Palma Gil | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./REHAB./COMP. OF VARIOUS GOV'T. BLDGS. STRUCT., FAC (Provincewide) | [7 empty] | Date Allotment Released: |  | Date completed:
Talaingod | Palma Gil | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./REHAB./COMP. OF VARIOUS GOV'T. BLDGS. STRUCT., FAC (Provincewide) | [7 empty] | Date Started:
Tagum City | Balamban | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./REHAB./COMP. OF VARIOUS GOV'T. BLDGS. STRUCT., FAC (Provincewide) | Construction of Veterinary Quarantine Station, New balamban, Tagum City |  | 20% DF CY 2018 | Car Bath |  |  | Contract | Project Cost: | 200000 | Target Completion Date: |  | Program: | 200000 | Planned: |  | No. of Persons: |  | Awarded to ALLBRYCAR
Tagum City | Balamban | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./REHAB./COMP. OF VARIOUS GOV'T. BLDGS. STRUCT., FAC (Provincewide) | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 200000 | Revised: |  | No. of Man-days:
Tagum City | Balamban | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./REHAB./COMP. OF VARIOUS GOV'T. BLDGS. STRUCT., FAC (Provincewide) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Tagum City | Balamban | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./REHAB./COMP. OF VARIOUS GOV'T. BLDGS. STRUCT., FAC (Provincewide) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Tagum City | Balamban | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./REHAB./COMP. OF VARIOUS GOV'T. BLDGS. STRUCT., FAC (Provincewide) | [7 empty] | Date Allotment Released: |  | Date completed:
Tagum City | Balamban | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./REHAB./COMP. OF VARIOUS GOV'T. BLDGS. STRUCT., FAC (Provincewide) | [7 empty] | Date Started:
Asuncion | New Santiago | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | Const. of Potable water System at Prk. 6, New Santiago, Asuncion |  | GF CY 2018 (STIMULUS) | Water System |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Amended in AIP 3rd revision CY 2019 increasing the amount to complete the project For plan preparation c/o Amamio
Asuncion | New Santiago | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 500000 | Revised: |  | No. of Man-days:
Asuncion | New Santiago | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Asuncion | New Santiago | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Asuncion | New Santiago | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Date Allotment Released: |  | Date completed:
Asuncion | New Santiago | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Date Started:
Tagum City | Pagsabangan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | Completion of GYM Bleacher w/ Electrification, Pagsabangan, Tagum City |  | GF CY 2018 (STIMULUS) | Bleacher |  |  | MLGU | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | For implementation but the project was implemented by the brgy. Waiting for resolution to change priority Alloted March 12, 2019
Tagum City | Pagsabangan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 500000 | Revised: |  | No. of Man-days:
Tagum City | Pagsabangan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Tagum City | Pagsabangan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Tagum City | Pagsabangan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Date Allotment Released: |  | Date completed:
Tagum City | Pagsabangan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Date Started:
Tagum City | Libuganon | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | Construction of Drainage Canal, Libuganon, Tagum City |  | GF CY 2018 (STIMULUS) | Drainage |  |  | Admin | Project Cost: | 500000 | Target Completion Date: | 2020-08-18 23:59 | Program: | 500000 | Planned: | 53.04% | No. of Persons: | 14 | On-going
Tagum City | Libuganon | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Project Engineer: | Quirante | Revised Completion Date: | 2020-08-18 23:59 | Allotment: | 500000 | Revised: |  | No. of Man-days: | 434
Tagum City | Libuganon | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: | 53.04%
Tagum City | Libuganon | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Duration: | 64 | No. of days extended: |  |  |  | Slippage: | 0%
Tagum City | Libuganon | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Date Allotment Released: |  | Date completed:
Tagum City | Libuganon | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Date Started: | 2020-06-16
Kapalong | Luna | 1st Eng'g. Dist. | On-going | 2020-06-01 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | Construction of Concrete Perimeter Fence, Luna, Kapalaong |  | GF CY 2018 (STIMULUS) | Fence |  | sq.m | Admin | Project Cost: | 500000 | Target Completion Date: | 2020-07-21 | Program: | 500000 | Planned: | 92% | No. of Persons: | 8 | On-going
Kapalong | Luna | 1st Eng'g. Dist. | On-going | 2020-06-01 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Project Engineer: | Ambrosio | Revised Completion Date: | 2020-07-21 | Allotment: | 500000 | Revised: |  | No. of Man-days: | 120
Kapalong | Luna | 1st Eng'g. Dist. | On-going | 2020-06-01 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: | 93%
Kapalong | Luna | 1st Eng'g. Dist. | On-going | 2020-06-01 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Duration: | 50 | No. of days extended: |  |  |  | Slippage: | 1%
Kapalong | Luna | 1st Eng'g. Dist. | On-going | 2020-06-01 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Date Allotment Released: |  | Date completed:
Kapalong | Luna | 1st Eng'g. Dist. | On-going | 2020-06-01 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Date Started: | 2020-06-01
Kapalong | Maniki | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | Completion of Brgy. Health Center, Maniki, Kapalong |  | GF CY 2018 (STIMULUS) | Building |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | For amendment.To submit a new resolution for another priority project which is the Const. of Multi-Purpose Pavement but the propose site is not is donated because the previous project Completion of Brgy. Health Center was funded by the LGU of Kapalong
Kapalong | Maniki | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 500000 | Revised: |  | No. of Man-days:
Kapalong | Maniki | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Kapalong | Maniki | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Kapalong | Maniki | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Date Allotment Released: |  | Date completed:
Kapalong | Maniki | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Date Started:
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | Grouted Riprap on Embankment Sto. Ñino, Talaingod |  | GF CY 2018 (STIMULUS) | Riprap |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Plan and POW on process c/o PDPM
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 500000 | Revised: |  | No. of Man-days:
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Date Allotment Released: |  | Date completed:
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Date Started:
Talaingod | Dagohoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | Barangay Hall Improvement, Dagohoy, Talaingod |  | GF CY 2018 (STIMULUS) | Building |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | For amendment to Construction of Retaining Wall as per recommendation by Engr. Misa during site re-evaluation. Plan & POW completed.Resolution from the Brgy. Council to support the amendment c/o Engr. Canillada
Talaingod | Dagohoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 500000 | Revised: |  | No. of Man-days:
Talaingod | Dagohoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Talaingod | Dagohoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Talaingod | Dagohoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Date Allotment Released: |  | Date completed:
Talaingod | Dagohoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Date Started:
Talaingod | Palma Gil | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | Construction of 2 Classroom Building Datu Jose Libayao NHS Ext, Natulian, Palma Gil, Talaingod |  | GF CY 2018 (STIMULUS) | Building |  |  |  | Project Cost: | 1930933.28 | Target Completion Date: |  | Program: | 1930933.28 | Planned: |  | No. of Persons: |  | PO # 2020031342 - ALPEBEL BUILDERS & SUPPLY CORP.
Talaingod | Palma Gil | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 1930933.28 | Revised: |  | No. of Man-days:
Talaingod | Palma Gil | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Talaingod | Palma Gil | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Talaingod | Palma Gil | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Date Allotment Released: |  | Date completed:
Talaingod | Palma Gil | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Date Started:
New Corella | Mesaoy | 1st Eng'g. Dist. | On-going | 2018-11-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REHABILITATION OF VARIOUS PROVINCIAL ROADS | Mesaoy - Jct. Mahayahay |  | SB # 1 CY 2018 | Road Rehabilitation |  | km | Admin | Project Cost: | 1534000 | Target Completion Date: | 2018-12-15 23:46 | Program: | 1534000 | Planned: | 100% | No. of Persons: | 6 | Completed as per physical accomplishment. Financial documents still on process.
New Corella | Mesaoy | 1st Eng'g. Dist. | On-going | 2018-11-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REHABILITATION OF VARIOUS PROVINCIAL ROADS | [7 empty] | Project Engineer: | Pilotos | Revised Completion Date: |  | Allotment: | 1534000 | Revised: |  | No. of Man-days: | 150
New Corella | Mesaoy | 1st Eng'g. Dist. | On-going | 2018-11-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REHABILITATION OF VARIOUS PROVINCIAL ROADS | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: | 100%
New Corella | Mesaoy | 1st Eng'g. Dist. | On-going | 2018-11-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REHABILITATION OF VARIOUS PROVINCIAL ROADS | [7 empty] | Duration: | 30 | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | Mesaoy | 1st Eng'g. Dist. | On-going | 2018-11-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REHABILITATION OF VARIOUS PROVINCIAL ROADS | [7 empty] | Date Allotment Released: | 2018-07-19 | Date completed: | 2020-02-29
New Corella | Mesaoy | 1st Eng'g. Dist. | On-going | 2018-11-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REHABILITATION OF VARIOUS PROVINCIAL ROADS | [7 empty] | Date Started: | 2018-11-16
Kapalong | Maniki | 1st Eng'g. Dist. | On-going | 2019-11-02 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./COMPL./IMPV'T. OF VARIOUS GOV'T. BLDGS., STRUCTURES & FACILITIES (Const. in Progress - Bldgs. & Other Structures | Const./Impv't. of DDN Hospital Kapalong Zone |  | SB # 2 CY 2018 | Building |  | sq.m | Contract | Project Cost: | 5000000 | Target Completion Date: | 2020-06-09 | Program: | 5000000 | Planned: | 100% | No. of Persons: | 7 | Completed as per physical accomplishment. Financial documents still on process.
Kapalong | Maniki | 1st Eng'g. Dist. | On-going | 2019-11-02 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./COMPL./IMPV'T. OF VARIOUS GOV'T. BLDGS., STRUCTURES & FACILITIES (Const. in Progress - Bldgs. & Other Structures | [7 empty] | Project Engineer: | Ambrosio | Revised Completion Date: | 2020-07-07 | Allotment: | 5000000 | Revised: |  | No. of Man-days: | 217
Kapalong | Maniki | 1st Eng'g. Dist. | On-going | 2019-11-02 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./COMPL./IMPV'T. OF VARIOUS GOV'T. BLDGS., STRUCTURES & FACILITIES (Const. in Progress - Bldgs. & Other Structures | [7 empty] | Implementor: | MAG CORP. | No. of days suspended: | 28 | Disbursement: | 4781000 | Actual: | 100%
Kapalong | Maniki | 1st Eng'g. Dist. | On-going | 2019-11-02 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./COMPL./IMPV'T. OF VARIOUS GOV'T. BLDGS., STRUCTURES & FACILITIES (Const. in Progress - Bldgs. & Other Structures | [7 empty] | Duration: | 220 | No. of days extended: |  |  |  | Slippage: | 0%
Kapalong | Maniki | 1st Eng'g. Dist. | On-going | 2019-11-02 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./COMPL./IMPV'T. OF VARIOUS GOV'T. BLDGS., STRUCTURES & FACILITIES (Const. in Progress - Bldgs. & Other Structures | [7 empty] | Date Allotment Released: | 2018-09-04 | Date completed: | 2020-07-07
Kapalong | Maniki | 1st Eng'g. Dist. | On-going | 2019-11-02 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./COMPL./IMPV'T. OF VARIOUS GOV'T. BLDGS., STRUCTURES & FACILITIES (Const. in Progress - Bldgs. & Other Structures | [7 empty] | Date Started: | 2019-11-02
New Corella | Poblacion | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./COMPL./IMPV'T. OF VARIOUS GOV'T. BLDGS., STRUCTURES & FACILITIES (Const. in Progress - Bldgs. & Other Structures | Compl. Of Bahay Pag-Asa for Minors, New Corella |  | SB # 2 CY 2018 | Building |  |  | Admin | Project Cost: | 3450000 | Target Completion Date: | 2020-11-07 23:46 | Program: | 3450000 | Planned: | 15.75% | No. of Persons: | 8 | On-going
New Corella | Poblacion | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./COMPL./IMPV'T. OF VARIOUS GOV'T. BLDGS., STRUCTURES & FACILITIES (Const. in Progress - Bldgs. & Other Structures | [7 empty] | Project Engineer: | Cahayag | Revised Completion Date: |  | Allotment: | 3450000 | Revised: |  | No. of Man-days: | 248
New Corella | Poblacion | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./COMPL./IMPV'T. OF VARIOUS GOV'T. BLDGS., STRUCTURES & FACILITIES (Const. in Progress - Bldgs. & Other Structures | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: | 5.04%
New Corella | Poblacion | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./COMPL./IMPV'T. OF VARIOUS GOV'T. BLDGS., STRUCTURES & FACILITIES (Const. in Progress - Bldgs. & Other Structures | [7 empty] | Duration: | 144 | No. of days extended: |  |  |  | Slippage: | -10.71%
New Corella | Poblacion | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./COMPL./IMPV'T. OF VARIOUS GOV'T. BLDGS., STRUCTURES & FACILITIES (Const. in Progress - Bldgs. & Other Structures | [7 empty] | Date Allotment Released: |  | Date completed:
New Corella | Poblacion | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./COMPL./IMPV'T. OF VARIOUS GOV'T. BLDGS., STRUCTURES & FACILITIES (Const. in Progress - Bldgs. & Other Structures | [7 empty] | Date Started: | 2020-06-17
Tagum City | Mankilam | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./COMPL./IMPV'T. OF VARIOUS GOV'T. BLDGS., STRUCTURES & FACILITIES (Const. in Progress - Bldgs. & Other Structures | Const. of Add'l. 2nd Level Multi-Purpose HalI, PGSO warehouse,Bldg., Mankilam |  | SB # 2 CY 2018 | Building |  |  | Contract | Project Cost: | 7483756.22 | Target Completion Date: |  | Program: | 7483756.22 | Planned: |  | No. of Persons: |  | PO #2020020808 - FZI CONSTRUCTION AND PARTS SUPPLY
Tagum City | Mankilam | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./COMPL./IMPV'T. OF VARIOUS GOV'T. BLDGS., STRUCTURES & FACILITIES (Const. in Progress - Bldgs. & Other Structures | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 7483756.22 | Revised: |  | No. of Man-days:
Tagum City | Mankilam | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./COMPL./IMPV'T. OF VARIOUS GOV'T. BLDGS., STRUCTURES & FACILITIES (Const. in Progress - Bldgs. & Other Structures | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Tagum City | Mankilam | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./COMPL./IMPV'T. OF VARIOUS GOV'T. BLDGS., STRUCTURES & FACILITIES (Const. in Progress - Bldgs. & Other Structures | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Tagum City | Mankilam | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./COMPL./IMPV'T. OF VARIOUS GOV'T. BLDGS., STRUCTURES & FACILITIES (Const. in Progress - Bldgs. & Other Structures | [7 empty] | Date Allotment Released: |  | Date completed:
Tagum City | Mankilam | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./COMPL./IMPV'T. OF VARIOUS GOV'T. BLDGS., STRUCTURES & FACILITIES (Const. in Progress - Bldgs. & Other Structures | [7 empty] | Date Started:
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2020-04-30 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./COMPL./IMPV'T. OF VARIOUS GOV'T. BLDGS., STRUCTURES & FACILITIES (Const. in Progress - Bldgs. & Other Structures | Construction of SP/Legislative Building, Gov't. Center, Mankilam, Tagum City |  | SB # 3 CY 2018 | Building |  | sq.m | Contract | Project Cost: | 147262698.81 | Target Completion Date: | 2021-04-04 | Program: | 147262698.81 | Planned: | 4.205% | No. of Persons: | 20 | On-going (Suspended effective April 5, 2020 due to COVID; resumption order dated May 4, 2020)
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2020-04-30 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./COMPL./IMPV'T. OF VARIOUS GOV'T. BLDGS., STRUCTURES & FACILITIES (Const. in Progress - Bldgs. & Other Structures | [7 empty] | Project Engineer: | Japay/Albaracin | Revised Completion Date: | 2021-05-01 | Allotment: | 147262698.81 | Revised: |  | No. of Man-days: | 370
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2020-04-30 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./COMPL./IMPV'T. OF VARIOUS GOV'T. BLDGS., STRUCTURES & FACILITIES (Const. in Progress - Bldgs. & Other Structures | [7 empty] | Implementor: | Tagum Builders | No. of days suspended: | 27 | Disbursement: |  | Actual: | 4.347%
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2020-04-30 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./COMPL./IMPV'T. OF VARIOUS GOV'T. BLDGS., STRUCTURES & FACILITIES (Const. in Progress - Bldgs. & Other Structures | [7 empty] | Duration: | 370 | No. of days extended: |  |  |  | Slippage: | 0.1415%
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2020-04-30 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./COMPL./IMPV'T. OF VARIOUS GOV'T. BLDGS., STRUCTURES & FACILITIES (Const. in Progress - Bldgs. & Other Structures | [7 empty] | Date Allotment Released: |  | Date completed:
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2020-04-30 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./COMPL./IMPV'T. OF VARIOUS GOV'T. BLDGS., STRUCTURES & FACILITIES (Const. in Progress - Bldgs. & Other Structures | [7 empty] | Date Started: | 2020-03-30
Asuncion | Napungas | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | Rehab./Impv't. of MP Bldg. (Gym), Napungas, Asuncion |  | SB # 5 CY 2018 (STIMULUS) | GYM |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Abstract # 0620202137
Asuncion | Napungas | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Asuncion | Napungas | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Asuncion | Napungas | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Asuncion | Napungas | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Date Allotment Released: | 2019-02-04 | Date completed:
Asuncion | Napungas | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Date Started:
New Corella | Poblacion | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | Concreting of Drainage Canal from Prk. 3, 1-A, 2-A to Prk. 1-B, Brgy. Site, Phase @, New Corella |  | SB # 5 CY 2018 (STIMULUS) | Drainage |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Abstract draft
New Corella | Poblacion | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 500000 | Revised: |  | No. of Man-days:
New Corella | Poblacion | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
New Corella | Poblacion | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | Poblacion | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Date Allotment Released: |  | Date completed:
New Corella | Poblacion | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Date Started:
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2019-11-26 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./COMPL./IMPV'T. OF VARIOUS GOV'T. BLDGS., STRUCTURES & FACILITIES (Const. in Progress - Bldgs. & Other Structures | Division School Improvement (Davao del Norte DEPED Training Center), Tagum City |  | SEF (ANNUAL BUDGET CY 2018) | Building |  | sq.m | Admin | Project Cost: | 1250000 | Target Completion Date: | 2020-05-04 | Program: | 1250000 | Planned: | 100% | No. of Persons: | 18 | On-going (Suspended last April 5, 2020 due to COVID; resumption order dated May 4, 2020)
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2019-11-26 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./COMPL./IMPV'T. OF VARIOUS GOV'T. BLDGS., STRUCTURES & FACILITIES (Const. in Progress - Bldgs. & Other Structures | [7 empty] | Project Engineer: | Japay/Quirante | Revised Completion Date: | 2020-07-15 | Allotment: | 1250000 | Revised: | 83.63% | No. of Man-days: | 270
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2019-11-26 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./COMPL./IMPV'T. OF VARIOUS GOV'T. BLDGS., STRUCTURES & FACILITIES (Const. in Progress - Bldgs. & Other Structures | [7 empty] | Implementor: | Admin | No. of days suspended: | 27 | Disbursement: | 850625 | Actual: | 78.02%
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2019-11-26 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./COMPL./IMPV'T. OF VARIOUS GOV'T. BLDGS., STRUCTURES & FACILITIES (Const. in Progress - Bldgs. & Other Structures | [7 empty] | Duration: | 160 | No. of days extended: | 45 |  |  | Slippage: | -5.61%
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2019-11-26 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./COMPL./IMPV'T. OF VARIOUS GOV'T. BLDGS., STRUCTURES & FACILITIES (Const. in Progress - Bldgs. & Other Structures | [7 empty] | Date Allotment Released: | 2019-02-04 | Date completed:
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2019-11-26 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./COMPL./IMPV'T. OF VARIOUS GOV'T. BLDGS., STRUCTURES & FACILITIES (Const. in Progress - Bldgs. & Other Structures | [7 empty] | Date Started: | 2019-11-26
Talaingod | Dagohoy | 1st Eng'g. Dist. | On-going | 2019-11-17 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPAPP | Const. of Processing and Bagsakan Center, Brgy. Dagohoy, Talaingod |  | OPAPP-PAMANA CY 2018 | Building |  | sq.m | Contract | Project Cost: | 2500000 | Target Completion Date: | 2020-04-10 | Program: | 2500000 | Planned: | 55.61% | No. of Persons: | 8 | On-going; Resumption Order dated May 4, 2020
Talaingod | Dagohoy | 1st Eng'g. Dist. | On-going | 2019-11-17 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPAPP | [7 empty] | Project Engineer: | Dadula | Revised Completion Date: |  | Allotment: | 2500000 | Revised: |  | No. of Man-days: | 200
Talaingod | Dagohoy | 1st Eng'g. Dist. | On-going | 2019-11-17 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPAPP | [7 empty] | Implementor: | RLHV | No. of days suspended: |  | Disbursement: | 375000 | Actual: | 68.72%
Talaingod | Dagohoy | 1st Eng'g. Dist. | On-going | 2019-11-17 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPAPP | [7 empty] | Duration: | 145 | No. of days extended: |  |  |  | Slippage: | 13.11%
Talaingod | Dagohoy | 1st Eng'g. Dist. | On-going | 2019-11-17 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPAPP | [7 empty] | Date Allotment Released: | 2019-11-25 | Date completed:
Talaingod | Dagohoy | 1st Eng'g. Dist. | On-going | 2019-11-17 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPAPP | [7 empty] | Date Started: | 2019-11-17
Kapalong | Maniki | 1st Eng'g. Dist. | On-going | 2019-11-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPAPP | Post Harvest Facilities (Corn Mill, Solar Dryer, Corn Sheller), Kapalong, Davao del Norte |  | OPAPP-PAMANA CY 2018 | Building |  | sq.m | Admin | Project Cost: | 1500000 | Target Completion Date: | 2020-02-27 | Program: | 1500000 | Planned: | 100% | No. of Persons: | 7 | Completed as per physical accomplishment. Financial documents still on process.
Kapalong | Maniki | 1st Eng'g. Dist. | On-going | 2019-11-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPAPP | [7 empty] | Project Engineer: | Ambrosio | Revised Completion Date: | 2020-06-15 | Allotment: | 1500000 | Revised: |  | No. of Man-days: | 175
Kapalong | Maniki | 1st Eng'g. Dist. | On-going | 2019-11-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPAPP | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 1114654.45 | Actual: | 100%
Kapalong | Maniki | 1st Eng'g. Dist. | On-going | 2019-11-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPAPP | [7 empty] | Duration: | 101 | No. of days extended: | 82 |  |  | Slippage: | 0%
Kapalong | Maniki | 1st Eng'g. Dist. | On-going | 2019-11-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPAPP | [7 empty] | Date Allotment Released: | 2019-11-18 | Date completed: | 2020-06-15
Kapalong | Maniki | 1st Eng'g. Dist. | On-going | 2019-11-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPAPP | [7 empty] | Date Started: | 2019-11-18
Kapalong | Capungagan | 1st Eng'g. Dist. | On-going | 2019-11-25 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPAPP | Construction of PWS Level II in Purok 7-A and 7-B, Capungagan, Kapalong |  | OPAPP-PAMANA CY 2018 | Potable Water System |  |  | Admin | Project Cost: | 1760000 | Target Completion Date: | 2020-02-03 | Program: | 1760000 | Planned: | 100% | No. of Persons: | 25 | On-going (Suspended last April 5, 2020 due to COVID; resumption order dated May 4, 2020)
Kapalong | Capungagan | 1st Eng'g. Dist. | On-going | 2019-11-25 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPAPP | [7 empty] | Project Engineer: | Kabinge | Revised Completion Date: | 2020-04-15 | Allotment: | 1760000 | Revised: | 100% | No. of Man-days: | 375
Kapalong | Capungagan | 1st Eng'g. Dist. | On-going | 2019-11-25 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPAPP | [7 empty] | Implementor: | PEO | No. of days suspended: | 28 | Disbursement: | 1235344 | Actual: | 76.64%
Kapalong | Capungagan | 1st Eng'g. Dist. | On-going | 2019-11-25 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPAPP | [7 empty] | Duration: | 70 | No. of days extended: | 44 |  |  | Slippage: | -23.36%
Kapalong | Capungagan | 1st Eng'g. Dist. | On-going | 2019-11-25 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPAPP | [7 empty] | Date Allotment Released: | 2019-11-25 | Date completed:
Kapalong | Capungagan | 1st Eng'g. Dist. | On-going | 2019-11-25 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPAPP | [7 empty] | Date Started: | 2019-11-25
Kapalong | Pag-Asa | 1st Eng'g. Dist. | On-going | 2019-12-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPAPP | Construction of PWS Level II in Purok 2, Pag-Asa, kapalong |  | OPAPP-PAMANA CY 2018 | Potable Water System |  |  | Admin | Project Cost: | 2310000 | Target Completion Date: | 2020-04-09 | Program: | 2310000 | Planned: | 78% | No. of Persons: | 23 | On-going (Suspended last April 5, 2020 due to COVID; resumption order dated May 4, 2020)
Kapalong | Pag-Asa | 1st Eng'g. Dist. | On-going | 2019-12-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPAPP | [7 empty] | Project Engineer: | Dadula | Revised Completion Date: | 2020-07-31 | Allotment: | 2310000 | Revised: | 71.1% | No. of Man-days: | 713
Kapalong | Pag-Asa | 1st Eng'g. Dist. | On-going | 2019-12-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPAPP | [7 empty] | Implementor: | PEO | No. of days suspended: | 28 | Disbursement: | 1642410 | Actual: | 71.1%
Kapalong | Pag-Asa | 1st Eng'g. Dist. | On-going | 2019-12-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPAPP | [7 empty] | Duration: | 115 | No. of days extended: | 85 |  |  | Slippage: | 0%
Kapalong | Pag-Asa | 1st Eng'g. Dist. | On-going | 2019-12-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPAPP | [7 empty] | Date Allotment Released: | 2019-11-25 | Date completed:
Kapalong | Pag-Asa | 1st Eng'g. Dist. | On-going | 2019-12-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPAPP | [7 empty] | Date Started: | 2019-12-16
Kapalong | Semong | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPAPP | Cattle Production- Brgy. Tiburcia, Gupitan and Semong, Kapalong |  | OPAPP-PAMANA CY 2018 | Building |  | sq.m |  | Project Cost: | 1500000 | Target Completion Date: |  | Program: | 1500000 | Planned: |  | No. of Persons: |  | For cancellation. A letter was sent to OPAPP last Dec 2018 requesting to allow us to reduce the number of cattle but we are still hoping that there would be a supplier will bid
Kapalong | Semong | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPAPP | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 1500000 | Revised: |  | No. of Man-days:
Kapalong | Semong | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPAPP | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Kapalong | Semong | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPAPP | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Kapalong | Semong | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPAPP | [7 empty] | Date Allotment Released: |  | Date completed:
Kapalong | Semong | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPAPP | [7 empty] | Date Started:
Talaingod | Dagohoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPAPP | Cattle Production, Brgy. Palma Gil, Brgy. Sto. Nino, Brgy. Dagohoy, Talaingod, Davao del Norte |  | OPAPP-PAMANA CY 2018 | Building |  | sq.m |  | Project Cost: | 1500000 | Target Completion Date: |  | Program: | 1500000 | Planned: |  | No. of Persons: |  | For cancellation. A letter was sent to OPAPP last Dec 2018 requesting to allow us to reduce the number of cattle but we are still hoping that there would be a supplier will bid
Talaingod | Dagohoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPAPP | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 1500000 | Revised: |  | No. of Man-days:
Talaingod | Dagohoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPAPP | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Talaingod | Dagohoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPAPP | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Talaingod | Dagohoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPAPP | [7 empty] | Date Allotment Released: |  | Date completed:
Talaingod | Dagohoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPAPP | [7 empty] | Date Started:
Talaingod | Palma Gil | 1st Eng'g. Dist. | On-going | 2020-06-01 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPAPP | Rice Mill for Upland Rice, Palma Gil, Talaingod |  | OPAPP-PAMANA CY 2018 | Rice Mill |  |  | Admin | Project Cost: | 1000000 | Target Completion Date: | 2020-07-30 23:46 | Program: | 1000000 | Planned: | 35.69% | No. of Persons: | 6 | On-going
Talaingod | Palma Gil | 1st Eng'g. Dist. | On-going | 2020-06-01 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPAPP | [7 empty] | Project Engineer: | Torrecampo | Revised Completion Date: | 2020-07-30 23:46 | Allotment: | 1000000 | Revised: |  | No. of Man-days: | 90
Talaingod | Palma Gil | 1st Eng'g. Dist. | On-going | 2020-06-01 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPAPP | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: | 356900 | Actual: | 35.69%
Talaingod | Palma Gil | 1st Eng'g. Dist. | On-going | 2020-06-01 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPAPP | [7 empty] | Duration: | 60 | No. of days extended: |  |  |  | Slippage: | 0%
Talaingod | Palma Gil | 1st Eng'g. Dist. | On-going | 2020-06-01 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPAPP | [7 empty] | Date Allotment Released: |  | Date completed:
Talaingod | Palma Gil | 1st Eng'g. Dist. | On-going | 2020-06-01 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPAPP | [7 empty] | Date Started: | 2020-06-01
Kapalong | Mabantao-Florida | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | QRF | Rehab. Of Slope Protection of Libuganon River Along Kapalong - Mabantao - Florida Prov'l. Road Phase I |  | QRF CY 2016 | Slope Protection |  |  |  | Project Cost: | 900000 | Target Completion Date: |  | Program: | 900000 | Planned: |  | No. of Persons: |  | For AIP Amendment
Kapalong | Mabantao-Florida | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | QRF | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 900000 | Revised: |  | No. of Man-days:
Kapalong | Mabantao-Florida | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | QRF | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Kapalong | Mabantao-Florida | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | QRF | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Kapalong | Mabantao-Florida | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | QRF | [7 empty] | Date Allotment Released: |  | Date completed:
Kapalong | Mabantao-Florida | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | QRF | [7 empty] | Date Started:
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2019-11-04 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Ground Dev't. | Ground Development and landscape @ PDRRMD, Gov't. Center, Mankilam, Tagum City |  | LDRRMF 2018 | Ground Dev't. |  | sq.m | Admin | Project Cost: | 1000000 | Target Completion Date: | 2020-02-29 23:46 | Program: | 1000000 | Planned: | 75.24% | No. of Persons: | 8 | Suspended (Waiting for the complete delivery of materials) dated March 2, 2020
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2019-11-04 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Ground Dev't. | [7 empty] | Project Engineer: | Juan | Revised Completion Date: | 2020-02-29 23:46 | Allotment: | 1000000 | Revised: |  | No. of Man-days: | 152
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2019-11-04 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Ground Dev't. | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: | 752400 | Actual: | 75.24%
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2019-11-04 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Ground Dev't. | [7 empty] | Duration: | 118 | No. of days extended: |  |  |  | Slippage: | 0%
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2019-11-04 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Ground Dev't. | [7 empty] | Date Allotment Released: | 2019-03-19 | Date completed:
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2019-11-04 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Ground Dev't. | [7 empty] | Date Started: | 2019-11-04
Asuncion | Canatan-Doña Andrea | 1st Eng'g. Dist. | On-going | 2020-06-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL RAODS & BRIDGES LS - P41,465,029.00 | ROAD ID 007 - Jct. Highway Canatan - Doña Andrea |  | 20% DF CY 2019 | Road Rehabilitation | 4.34 | km | Admin | Project Cost: | 2000000 | Target Completion Date: | 2020-08-11 23:46 | Program: | 2000000 | Planned: | 31.77% | No. of Persons: |  | On-going
Asuncion | Canatan-Doña Andrea | 1st Eng'g. Dist. | On-going | 2020-06-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL RAODS & BRIDGES | [7 empty] | Project Engineer: | Pilotos | Revised Completion Date: | 2020-08-11 23:46 | Allotment: | 2000000 | Revised: |  | No. of Man-days:
Asuncion | Canatan-Doña Andrea | 1st Eng'g. Dist. | On-going | 2020-06-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL RAODS & BRIDGES LS - P41,465,029.00 | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: | 635400 | Actual: | 31.77%
Asuncion | Canatan-Doña Andrea | 1st Eng'g. Dist. | On-going | 2020-06-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL RAODS & BRIDGES LS - P41,465,029.00 | [7 empty] | Duration: | 57 | No. of days extended: |  |  |  | Slippage: | 0%
Asuncion | Canatan-Doña Andrea | 1st Eng'g. Dist. | On-going | 2020-06-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL RAODS & BRIDGES LS - P41,465,029.00 | [7 empty] | Date Allotment Released: | 2019-06-12 | Date completed:
Asuncion | Canatan-Doña Andrea | 1st Eng'g. Dist. | On-going | 2020-06-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL RAODS & BRIDGES LS - P41,465,029.00 | [7 empty] | Date Started: | 2020-06-16
Asuncion | Pamacaun | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL RAODS & BRIDGES LS - P41,465,029.00 | ROAD ID 015 - Pamacaun - Lasang Banate |  | 20% DF CY 2019 | Road Rehabilitation | 4.34 |  | Admin | Project Cost: | 2000000 | Target Completion Date: |  | Program: | 2000000 | Planned: |  | No. of Persons: |  | For implementation (Waiting for the delivery of geo-grid materials. An approved request letter dated Dec. 3, 2019 for the extension of 50 days from Provincial Administrator Engr. Rabanoz is on file
Asuncion | Pamacaun | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL RAODS & BRIDGES | [7 empty] | Project Engineer: | Gone | Revised Completion Date: | 0 | Allotment: | 2000000 | Revised: |  | No. of Man-days:
Asuncion | Pamacaun | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL RAODS & BRIDGES LS - P41,465,029.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Asuncion | Pamacaun | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL RAODS & BRIDGES LS - P41,465,029.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Asuncion | Pamacaun | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL RAODS & BRIDGES LS - P41,465,029.00 | [7 empty] | Date Allotment Released: | 2019-06-27 | Date completed:
Asuncion | Pamacaun | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL RAODS & BRIDGES LS - P41,465,029.00 | [7 empty] | Date Started:
Talaingod | Sto.Niño-Palma Gil | 1st Eng'g. Dist. | On-going | 2020-03-06 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL RAODS & BRIDGES LS - P41,465,029.00 | ROAD ID 019 - Sto. Niño - Palma Gil - Sitio Opao |  | 20% DF CY 2019 | Road Rehabilitation | 11.6 | km | Contract | Project Cost: | 1901000 | Target Completion Date: | 2020-04-18 23:46 | Program: | 1901000 | Planned: | 44.89% | No. of Persons: |  | On-going (Suspended dated March 14, 2020; Resumption Order dated May 25, 2020)
Talaingod | Sto.Niño-Palma Gil | 1st Eng'g. Dist. | On-going | 2020-03-06 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL RAODS & BRIDGES | [7 empty] | Project Engineer: | Lumapat | Revised Completion Date: | 2020-06-29 23:46 | Allotment: | 1901000 | Revised: |  | No. of Man-days:
Talaingod | Sto.Niño-Palma Gil | 1st Eng'g. Dist. | On-going | 2020-03-06 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL RAODS & BRIDGES LS - P41,465,029.00 | [7 empty] | Implementor: | Tagum Constrak | No. of days suspended: | 72 | Disbursement: | 853358.9 | Actual: | 44.89%
Talaingod | Sto.Niño-Palma Gil | 1st Eng'g. Dist. | On-going | 2020-03-06 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL RAODS & BRIDGES LS - P41,465,029.00 | [7 empty] | Duration: | 44 | No. of days extended: |  |  |  | Slippage: | 0%
Talaingod | Sto.Niño-Palma Gil | 1st Eng'g. Dist. | On-going | 2020-03-06 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL RAODS & BRIDGES LS - P41,465,029.00 | [7 empty] | Date Allotment Released: | 2019-06-19 | Date completed:
Talaingod | Sto.Niño-Palma Gil | 1st Eng'g. Dist. | On-going | 2020-03-06 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL RAODS & BRIDGES LS - P41,465,029.00 | [7 empty] | Date Started: | 2020-03-06
Talaingod | Sto. Niño-Daligdigon-Paiton | 1st Eng'g. Dist. | On-going | 2020-01-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL RAODS & BRIDGES LS - P41,465,029.00 | ROAD ID 023 - Sto. Niño - Daligdigon - Paiton |  | 20% DF CY 2019 | Road Rehabilitation | 11.6 | km | Contract | Project Cost: | 3000000 | Target Completion Date: | 2020-05-14 23:46 | Program: | 3000000 | Planned: | 19.35% | No. of Persons: | 7 | On-going; Resumption Order dated May 4, 2020
Talaingod | Sto. Niño-Daligdigon-Paiton | 1st Eng'g. Dist. | On-going | 2020-01-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL RAODS & BRIDGES | [7 empty] | Project Engineer: | Lumapat | Revised Completion Date: | 2020-06-11 23:46 | Allotment: | 3000000 | Revised: |  | No. of Man-days: | 217
Talaingod | Sto. Niño-Daligdigon-Paiton | 1st Eng'g. Dist. | On-going | 2020-01-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL RAODS & BRIDGES LS - P41,465,029.00 | [7 empty] | Implementor: |  | No. of days suspended: | 28 | Disbursement: | 580500 | Actual: | 19.35%
Talaingod | Sto. Niño-Daligdigon-Paiton | 1st Eng'g. Dist. | On-going | 2020-01-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL RAODS & BRIDGES LS - P41,465,029.00 | [7 empty] | Duration: | 120 | No. of days extended: |  |  |  | Slippage: | 0%
Talaingod | Sto. Niño-Daligdigon-Paiton | 1st Eng'g. Dist. | On-going | 2020-01-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL RAODS & BRIDGES LS - P41,465,029.00 | [7 empty] | Date Allotment Released: | 2019-10-03 | Date completed:
Talaingod | Sto. Niño-Daligdigon-Paiton | 1st Eng'g. Dist. | On-going | 2020-01-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL RAODS & BRIDGES LS - P41,465,029.00 | [7 empty] | Date Started: | 2020-01-16
Talaingod | Jct. Paiton-Mibolo | 1st Eng'g. Dist. | On-going | 2019-08-01 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL RAODS & BRIDGES LS - P41,465,029.00 | ROAD ID 024 - Jct. Paiton - Mibolo |  | 20% DF CY 2019 | Road Rehabilitation | 23.9 | km | Contract | Project Cost: | 6000000 | Target Completion Date: | 2020-03-15 23:46 | Program: | 6000000 | Planned: | 21.05% | No. of Persons: |  | Temporary suspended because the materials for the box culvert procurement on process wth PO # 2019061674
Talaingod | Jct. Paiton-Mibolo | 1st Eng'g. Dist. | On-going | 2019-08-01 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL RAODS & BRIDGES | [7 empty] | Project Engineer: | Lumapat | Revised Completion Date: |  | Allotment: | 6000000 | Revised: |  | No. of Man-days:
Talaingod | Jct. Paiton-Mibolo | 1st Eng'g. Dist. | On-going | 2019-08-01 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL RAODS & BRIDGES LS - P41,465,029.00 | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: | 1263000 | Actual: | 21.05%
Talaingod | Jct. Paiton-Mibolo | 1st Eng'g. Dist. | On-going | 2019-08-01 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL RAODS & BRIDGES LS - P41,465,029.00 | [7 empty] | Duration: | 228 | No. of days extended: |  |  |  | Slippage: | 0%
Talaingod | Jct. Paiton-Mibolo | 1st Eng'g. Dist. | On-going | 2019-08-01 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL RAODS & BRIDGES LS - P41,465,029.00 | [7 empty] | Date Allotment Released: | 2019-03-25 | Date completed:
Talaingod | Jct. Paiton-Mibolo | 1st Eng'g. Dist. | On-going | 2019-08-01 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL RAODS & BRIDGES LS - P41,465,029.00 | [7 empty] | Date Started: | 2019-08-01
Talaingod | Monte Dujali-Gupitan | 1st Eng'g. Dist. | On-going | 2020-01-31 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL RAODS & BRIDGES LS - P41,465,029.00 | ROAD ID 037 - Monte Dujali - Gupitan |  | 20% DF CY 2019 | Road Rehabilitation | 4.58 | km | Admin | Project Cost: | 1200000 | Target Completion Date: | 2020-03-31 23:46 | Program: | 1200000 | Planned: | 100% | No. of Persons: | 10 | Completed as per physical accomplishment. Financial documents still on process.
Talaingod | Monte Dujali-Gupitan | 1st Eng'g. Dist. | On-going | 2020-01-31 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL RAODS & BRIDGES | [7 empty] | Project Engineer: | Bacaron | Revised Completion Date: | 2020-06-30 23:46 | Allotment: | 1200000 | Revised: |  | No. of Man-days: | 240
Talaingod | Monte Dujali-Gupitan | 1st Eng'g. Dist. | On-going | 2020-01-31 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL RAODS & BRIDGES LS - P41,465,029.00 | [7 empty] | Implementor: | PEO | No. of days suspended: | 30 | Disbursement: | 1200000 | Actual: | 100%
Talaingod | Monte Dujali-Gupitan | 1st Eng'g. Dist. | On-going | 2020-01-31 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL RAODS & BRIDGES LS - P41,465,029.00 | [7 empty] | Duration: | 61 | No. of days extended: | 61 |  |  | Slippage: | 0%
Talaingod | Monte Dujali-Gupitan | 1st Eng'g. Dist. | On-going | 2020-01-31 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL RAODS & BRIDGES LS - P41,465,029.00 | [7 empty] | Date Allotment Released: | 2019-12-06 | Date completed:
Talaingod | Monte Dujali-Gupitan | 1st Eng'g. Dist. | On-going | 2020-01-31 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL RAODS & BRIDGES LS - P41,465,029.00 | [7 empty] | Date Started: | 2020-01-31
New Corella | San Juan-New Talisay | 1st Eng'g. Dist. | On-going | 2019-11-04 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS OF LOCAL ROADS & DRAINAGE DEVELOPMENT PROJECT(Provincewide) LS - 15,000,000.00 | Rehab./Impv't. of San Juan-New Talisay Provincial Road with Drainage |  | 20% DF CY 2019 | Road Drainage rehabiliated |  | km | Admin | Project Cost: | 1000000 | Target Completion Date: | 2019-12-18 | Program: | 1000000 | Planned: | 57.41% | No. of Persons: |  | Suspended dated December 18, 2019 due to revision of POW
New Corella | San Juan-New Talisay | 1st Eng'g. Dist. | On-going | 2019-11-04 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS OF LOCAL ROADS & DRAINAGE DEVELOPMENT PROJECT(Provincewide) LS - 15,000,000.00 | [7 empty] | Project Engineer: | Pilotos | Revised Completion Date: | 2019-12-18 | Allotment: | 1000000 | Revised: |  | No. of Man-days:
New Corella | San Juan-New Talisay | 1st Eng'g. Dist. | On-going | 2019-11-04 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS OF LOCAL ROADS & DRAINAGE DEVELOPMENT PROJECT(Provincewide) LS - 15,000,000.00 | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: | 741100 | Actual: | 74.11%
New Corella | San Juan-New Talisay | 1st Eng'g. Dist. | On-going | 2019-11-04 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS OF LOCAL ROADS & DRAINAGE DEVELOPMENT PROJECT(Provincewide) LS - 15,000,000.00 | [7 empty] | Duration: | 44 | No. of days extended: |  |  |  | Slippage: | 16.7%
New Corella | San Juan-New Talisay | 1st Eng'g. Dist. | On-going | 2019-11-04 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS OF LOCAL ROADS & DRAINAGE DEVELOPMENT PROJECT(Provincewide) LS - 15,000,000.00 | [7 empty] | Date Allotment Released: | 2019-01-31 | Date completed:
New Corella | San Juan-New Talisay | 1st Eng'g. Dist. | On-going | 2019-11-04 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS OF LOCAL ROADS & DRAINAGE DEVELOPMENT PROJECT(Provincewide) LS - 15,000,000.00 | [7 empty] | Date Started: | 2019-11-04
Kapalong | Suaon-Libuton | 1st Eng'g. Dist. | On-going | 2019-11-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS OF LOCAL ROADS & DRAINAGE DEVELOPMENT PROJECT(Provincewide) LS - 15,000,000.00 | Repair/Rehab. Of Concrete Road Jct. Suaon-Libuton, Kapalong |  | 20% DF CY 2019 | Road Drainage rehabiliated |  | km | Admin | Project Cost: | 1000000 | Target Completion Date: | 2020-02-15 23:46 | Program: | 1000000 | Planned: | 14.73% | No. of Persons: |  | Suspended dated March 30, 2020 due to availability of equipment
Kapalong | Suaon-Libuton | 1st Eng'g. Dist. | On-going | 2019-11-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS OF LOCAL ROADS & DRAINAGE DEVELOPMENT PROJECT(Provincewide) LS - 15,000,000.00 | [7 empty] | Project Engineer: | Bacaron | Revised Completion Date: |  | Allotment: | 1000000 | Revised: |  | No. of Man-days:
Kapalong | Suaon-Libuton | 1st Eng'g. Dist. | On-going | 2019-11-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS OF LOCAL ROADS & DRAINAGE DEVELOPMENT PROJECT(Provincewide) LS - 15,000,000.00 | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: | 142000 | Actual: | 14.2%
Kapalong | Suaon-Libuton | 1st Eng'g. Dist. | On-going | 2019-11-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS OF LOCAL ROADS & DRAINAGE DEVELOPMENT PROJECT(Provincewide) LS - 15,000,000.00 | [7 empty] | Duration: | 90 | No. of days extended: |  |  |  | Slippage: | -0.53%
Kapalong | Suaon-Libuton | 1st Eng'g. Dist. | On-going | 2019-11-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS OF LOCAL ROADS & DRAINAGE DEVELOPMENT PROJECT(Provincewide) LS - 15,000,000.00 | [7 empty] | Date Allotment Released: | 2019-03-12 | Date completed:
Kapalong | Suaon-Libuton | 1st Eng'g. Dist. | On-going | 2019-11-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS OF LOCAL ROADS & DRAINAGE DEVELOPMENT PROJECT(Provincewide) LS - 15,000,000.00 | [7 empty] | Date Started: | 2019-11-18
Asuncion | Saug-Sonlon Longanapan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS OF LOCAL ROADS & DRAINAGE DEVELOPMENT PROJECT(Provincewide) LS - 15,000,000.00 | Impv't. of Cross Drainage along Saug-Sonlon-Bdry. Longanapan |  | 20% DF CY 2019 | Road Drainage rehabiliated |  | ln.m | Admin | Project Cost: | 3000000 | Target Completion Date: |  | Program: | 3000000 | Planned: |  | No. of Persons: |  | For implementation
Asuncion | Saug-Sonlon Longanapan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS OF LOCAL ROADS & DRAINAGE DEVELOPMENT PROJECT(Provincewide) LS - 15,000,000.00 | [7 empty] | Project Engineer: | Pilotos | Revised Completion Date: | 0 | Allotment: | 3000000 | Revised: |  | No. of Man-days:
Asuncion | Saug-Sonlon Longanapan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS OF LOCAL ROADS & DRAINAGE DEVELOPMENT PROJECT(Provincewide) LS - 15,000,000.00 | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual:
Asuncion | Saug-Sonlon Longanapan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS OF LOCAL ROADS & DRAINAGE DEVELOPMENT PROJECT(Provincewide) LS - 15,000,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Asuncion | Saug-Sonlon Longanapan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS OF LOCAL ROADS & DRAINAGE DEVELOPMENT PROJECT(Provincewide) LS - 15,000,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Asuncion | Saug-Sonlon Longanapan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS OF LOCAL ROADS & DRAINAGE DEVELOPMENT PROJECT(Provincewide) LS - 15,000,000.00 | [7 empty] | Date Started:
Talaingod | Sto. Niño-Palma Gil | 1st Eng'g. Dist. | On-going | 2020-02-27 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS OF LOCAL ROADS & DRAINAGE DEVELOPMENT PROJECT(Provincewide) LS - 15,000,000.00 | Rehab./Impv't. of Sto. Niño-Palma Gil-Sitio Opao Provincial Road with Drainage |  | 20% DF CY 2019 | Road Drainage rehabiliated |  | km | Contract | Project Cost: | 3000000 | Target Completion Date: | 2020-05-07 | Program: | 3000000 | Planned: | 44.89% | No. of Persons: |  | On-going (Suspended dated March 14, 2020; Resumption Order dated May 25, 2020)
Talaingod | Sto. Niño-Palma Gil | 1st Eng'g. Dist. | On-going | 2020-02-27 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS OF LOCAL ROADS & DRAINAGE DEVELOPMENT PROJECT(Provincewide) LS - 15,000,000.00 | [7 empty] | Project Engineer: | Lumapat | Revised Completion Date: | 2020-07-17 | Allotment: | 3000000 | Revised: |  | No. of Man-days:
Talaingod | Sto. Niño-Palma Gil | 1st Eng'g. Dist. | On-going | 2020-02-27 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS OF LOCAL ROADS & DRAINAGE DEVELOPMENT PROJECT(Provincewide) LS - 15,000,000.00 | [7 empty] | Implementor: | Tagum Constrak | No. of days suspended: | 71 | Disbursement: | 1346700 | Actual: | 44.89%
Talaingod | Sto. Niño-Palma Gil | 1st Eng'g. Dist. | On-going | 2020-02-27 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS OF LOCAL ROADS & DRAINAGE DEVELOPMENT PROJECT(Provincewide) LS - 15,000,000.00 | [7 empty] | Duration: | 70 | No. of days extended: |  |  |  | Slippage: | 0%
Talaingod | Sto. Niño-Palma Gil | 1st Eng'g. Dist. | On-going | 2020-02-27 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS OF LOCAL ROADS & DRAINAGE DEVELOPMENT PROJECT(Provincewide) LS - 15,000,000.00 | [7 empty] | Date Allotment Released: | 2019-05-25 | Date completed:
Talaingod | Sto. Niño-Palma Gil | 1st Eng'g. Dist. | On-going | 2020-02-27 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS OF LOCAL ROADS & DRAINAGE DEVELOPMENT PROJECT(Provincewide) LS - 15,000,000.00 | [7 empty] | Date Started: | 2020-02-27
San Isidro | Linao | 1st Eng'g. Dist. | On-going | 2020-02-24 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS WATER SYSTEM DEVELOPMENT LS - P 9,750,000.00 | Construction of PWS, Bgry. Linao, San Isidro |  | 20% DF CY 2019 | Water System |  | ln.m | Admin | Project Cost: | 500000 | Target Completion Date: | 2020-04-23 23:46 | Program: | 500000 | Planned: | 99% | No. of Persons: | 8 | On-going (Suspended last April 5, 2020 due to COVID; resumption order dated May 4, 2020)
San Isidro | Linao | 1st Eng'g. Dist. | On-going | 2020-02-24 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS WATER SYSTEM DEVELOPMENT LS - P 9,750,000.00 | [7 empty] | Project Engineer: | Aclaracion | Revised Completion Date: | 2020-07-05 23:46 | Allotment: | 500000 | Revised: |  | No. of Man-days: | 120
San Isidro | Linao | 1st Eng'g. Dist. | On-going | 2020-02-24 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS WATER SYSTEM DEVELOPMENT LS - P 9,750,000.00 | [7 empty] | Implementor: | PEO | No. of days suspended: | 73 | Disbursement: | 216100 | Actual: | 99%
San Isidro | Linao | 1st Eng'g. Dist. | On-going | 2020-02-24 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS WATER SYSTEM DEVELOPMENT LS - P 9,750,000.00 | [7 empty] | Duration: | 60 | No. of days extended: |  |  |  | Slippage: | 0%
San Isidro | Linao | 1st Eng'g. Dist. | On-going | 2020-02-24 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS WATER SYSTEM DEVELOPMENT LS - P 9,750,000.00 | [7 empty] | Date Allotment Released: | 2019-06-19 | Date completed:
San Isidro | Linao | 1st Eng'g. Dist. | On-going | 2020-02-24 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS WATER SYSTEM DEVELOPMENT LS - P 9,750,000.00 | [7 empty] | Date Started: | 2020-02-24
San Isidro | Datu Balong | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS WATER SYSTEM DEVELOPMENT LS - P 9,750,000.00 | Construction of PWS, Brgy. Datu Balong, San Isidro |  | 20% DF CY 2019 | Water System |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | For declaration of savings because the spring water source is not feasible for development
San Isidro | Datu Balong | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS WATER SYSTEM DEVELOPMENT LS - P 9,750,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 500000 | Revised: |  | No. of Man-days:
San Isidro | Datu Balong | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS WATER SYSTEM DEVELOPMENT LS - P 9,750,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
San Isidro | Datu Balong | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS WATER SYSTEM DEVELOPMENT LS - P 9,750,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
San Isidro | Datu Balong | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS WATER SYSTEM DEVELOPMENT LS - P 9,750,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
San Isidro | Datu Balong | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS WATER SYSTEM DEVELOPMENT LS - P 9,750,000.00 | [7 empty] | Date Started:
San Isidro | Sagayen | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS WATER SYSTEM DEVELOPMENT LS - P 9,750,000.00 | Construction of PWS, Brgy. Sagayen, San Isidro |  | 20% DF CY 2019 | Water System |  |  | Contract | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | PO # 2020031340 - JJR Construction
San Isidro | Sagayen | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS WATER SYSTEM DEVELOPMENT LS - P 9,750,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 500000 | Revised: |  | No. of Man-days:
San Isidro | Sagayen | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS WATER SYSTEM DEVELOPMENT LS - P 9,750,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
San Isidro | Sagayen | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS WATER SYSTEM DEVELOPMENT LS - P 9,750,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
San Isidro | Sagayen | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS WATER SYSTEM DEVELOPMENT LS - P 9,750,000.00 | [7 empty] | Date Allotment Released: | 2019-09-10 | Date completed:
San Isidro | Sagayen | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS WATER SYSTEM DEVELOPMENT LS - P 9,750,000.00 | [7 empty] | Date Started:
Tagum City | Mankilam | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS WATER SYSTEM DEVELOPMENT LS - P 9,750,000.00 | Installation of Shallow Tube Wells & Const. of Machinery Shed |  | 20% DF CY 2019 | Water System |  |  | Admin | Project Cost: | 1600000 | Target Completion Date: |  | Program: | 1600000 | Planned: |  | No. of Persons: |  | Opening of BID for Negotiated 6/18,2020 to alpebel
Tagum City | Mankilam | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS WATER SYSTEM DEVELOPMENT LS - P 9,750,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 1600000 | Revised: |  | No. of Man-days:
Tagum City | Mankilam | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS WATER SYSTEM DEVELOPMENT LS - P 9,750,000.00 | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual:
Tagum City | Mankilam | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS WATER SYSTEM DEVELOPMENT LS - P 9,750,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Tagum City | Mankilam | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS WATER SYSTEM DEVELOPMENT LS - P 9,750,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Tagum City | Mankilam | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS WATER SYSTEM DEVELOPMENT LS - P 9,750,000.00 | [7 empty] | Date Started:
New Corella | Poblacion | 1st Eng'g. Dist. | On-going | 2020-03-02 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | Repair/Impv't. of Municipal Triball Hall, New Corella |  | 20% DF CY 2019 | Building |  | sq.m | Admin | Project Cost: | 1500000 | Target Completion Date: | 2020-06-12 23:46 | Program: | 1500000 | Planned: | 82.55% | No. of Persons: | 15 | On-going (Suspended last April 5, 2020 due to COVID; resumption order dated May 4, 2020)
New Corella | Poblacion | 1st Eng'g. Dist. | On-going | 2020-03-02 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | [7 empty] | Project Engineer: | Cahayag | Revised Completion Date: | 2020-07-10 23:46 | Allotment: | 1500000 | Revised: |  | No. of Man-days: | 225
New Corella | Poblacion | 1st Eng'g. Dist. | On-going | 2020-03-02 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | [7 empty] | Implementor: | PEO | No. of days suspended: | 28 | Disbursement: |  | Actual: | 77.72%
New Corella | Poblacion | 1st Eng'g. Dist. | On-going | 2020-03-02 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | [7 empty] | Duration: | 103 | No. of days extended: |  |  |  | Slippage: | -4.83%
New Corella | Poblacion | 1st Eng'g. Dist. | On-going | 2020-03-02 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
New Corella | Poblacion | 1st Eng'g. Dist. | On-going | 2020-03-02 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | [7 empty] | Date Started: | 2020-03-02
San Isidro | Sabangan | 1st Eng'g. Dist. | On-going | 2019-12-02 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | Const. of Municipal Tribal Hall, San Isidro |  | 20% DF CY 2019 | Building | 42 | sq.m | Admin | Project Cost: | 500000 | Target Completion Date: | 2020-02-19 23:46 | Program: | 500000 | Planned: | 81.44% | No. of Persons: | 8 | Completed as per physical accomplishment. Financial documents still on process.
San Isidro | Sabangan | 1st Eng'g. Dist. | On-going | 2019-12-02 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | [7 empty] | Project Engineer: | Aclaracion | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days: | 176
San Isidro | Sabangan | 1st Eng'g. Dist. | On-going | 2019-12-02 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | [7 empty] | Implementor: | PEO | No. of days suspended: | 28 | Disbursement: |  | Actual: | 81.44%
San Isidro | Sabangan | 1st Eng'g. Dist. | On-going | 2019-12-02 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | [7 empty] | Duration: | 80 | No. of days extended: |  |  |  | Slippage: | 0%
San Isidro | Sabangan | 1st Eng'g. Dist. | On-going | 2019-12-02 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | [7 empty] | Date Allotment Released: | 2019-01-15 | Date completed: | 2020-06-15
San Isidro | Sabangan | 1st Eng'g. Dist. | On-going | 2019-12-02 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | [7 empty] | Date Started: | 2019-12-02
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2019-12-02 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | Repair Bay of Disaster Quick Response Equipment @ PEO Compound, Gov't. Center, Mankilam, Tagum City |  | 20% DF CY 2019 | Building | 66 | sq.m | Admin | Project Cost: | 1000000 | Target Completion Date: | 2020-04-19 23:46 | Program: | 1000000 | Planned: | 74.7% | No. of Persons: | 5 | On-going (Suspended last April 5, 2020 due to COVID; resumption order dated May 4, 2020)
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2019-12-02 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | [7 empty] | Project Engineer: | Chua/Mucas | Revised Completion Date: | 2020-05-17 23:46 | Allotment: | 1000000 | Revised: |  | No. of Man-days: | 95
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2019-12-02 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | [7 empty] | Implementor: | PEO | No. of days suspended: | 28 | Disbursement: |  | Actual: | 74.7%
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2019-12-02 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | [7 empty] | Duration: | 140 | No. of days extended: |  |  |  | Slippage: | 0%
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2019-12-02 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | [7 empty] | Date Allotment Released: | 2019-01-31 | Date completed:
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2019-12-02 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | [7 empty] | Date Started: | 2019-12-02
Talaingod | Gupitan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | Const. of Multi-Purpose Hall Center (Cultural Heritage in Ancestral Domain of Ata-Manobo) |  | 20% DF CY 2019 | Building |  |  | Admin | Project Cost: | 3000000 | Target Completion Date: |  | Program: | 3000000 | Planned: |  | No. of Persons: |  | Fund re-aligned to GIDAS projects
Talaingod | Gupitan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 3000000 | Revised: |  | No. of Man-days:
Talaingod | Gupitan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Talaingod | Gupitan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Talaingod | Gupitan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Talaingod | Gupitan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | [7 empty] | Date Started:
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | Const. of IP Women's Multi-{Purpose Bldg.), Cabidiangan, Sto. Niño, Talaingod |  | 20% DF CY 2019 | Building |  |  | Admin | Project Cost: | 2000000 | Target Completion Date: |  | Program: | 2000000 | Planned: |  | No. of Persons: |  | Final abstract #0320200897 (Alpebel Builders)
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 2000000 | Revised: |  | No. of Man-days:
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual:
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | [7 empty] | Date Allotment Released: | 2019-05-15 | Date completed:
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | [7 empty] | Date Started:
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2020-02-03 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | Extension of PAGRO Training Center & Ground Dev't., Gov't. Center, Mankilam, Tagum City |  | 20% DF CY 2019 | Building |  | sq.m | Admin | Project Cost: | 1000000 | Target Completion Date: | 2020-04-23 | Program: | 1000000 | Planned: | 30.5% | No. of Persons: | 5 | On-going (Suspended last April 5, 2020 due to COVID; resumption order dated May 4, 2020)
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2020-02-03 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | [7 empty] | Project Engineer: | Chua/Mugas | Revised Completion Date: | 2020-05-21 | Allotment: | 1000000 | Revised: |  | No. of Man-days: | 57
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2020-02-03 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | [7 empty] | Implementor: | PEO | No. of days suspended: | 28 | Disbursement: |  | Actual: | 30.5%
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2020-02-03 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | [7 empty] | Duration: | 80 | No. of days extended: |  |  |  | Slippage: | 0%
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2020-02-03 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | [7 empty] | Date Allotment Released: | 2019-07-26 | Date completed:
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2020-02-03 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | [7 empty] | Date Started: | 2020-02-03
Tagum City | Mankilam | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | Construction of Abilidad Training Center, Gov't. Center, Mankilam, Tagum City |  | 20% DF CY 2019 | Building |  |  |  | Project Cost: | 7000000 | Target Completion Date: |  | Program: | 7000000 | Planned: |  | No. of Persons: |  | Fund re-aligned to GIDAS projects
Tagum City | Mankilam | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 7000000 | Revised: |  | No. of Man-days:
Tagum City | Mankilam | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual:
Tagum City | Mankilam | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Tagum City | Mankilam | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Tagum City | Mankilam | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | [7 empty] | Date Started:
New Corella | Suawon | 1st Eng'g. Dist. | On-going | 2019-12-09 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | Const. of 1 CL Bldg. @ Suawon ES, New Corella |  | 20% DF CY 2019 | Building | 82.65 | sq.m | Admin | Project Cost: | 1000000 | Target Completion Date: | 2020-04-21 23:46 | Program: | 1000000 | Planned: | 60.44% | No. of Persons: | 7 | On-going (Suspended last April 5, 2020 due to COVID; resumption order dated May 4, 2020)
New Corella | Suawon | 1st Eng'g. Dist. | On-going | 2019-12-09 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | [7 empty] | Project Engineer: | Miraflor | Revised Completion Date: | 2020-05-19 23:46 | Allotment: | 1000000 | Revised: |  | No. of Man-days: | 147
New Corella | Suawon | 1st Eng'g. Dist. | On-going | 2019-12-09 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | [7 empty] | Implementor: | PEO | No. of days suspended: | 28 | Disbursement: |  | Actual: | 60.44%
New Corella | Suawon | 1st Eng'g. Dist. | On-going | 2019-12-09 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | [7 empty] | Duration: | 135 | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | Suawon | 1st Eng'g. Dist. | On-going | 2019-12-09 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | [7 empty] | Date Allotment Released: | 2020-06-07 | Date completed:
New Corella | Suawon | 1st Eng'g. Dist. | On-going | 2019-12-09 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | [7 empty] | Date Started: | 2019-12-09
Talaingod | STo. Niño | 1st Eng'g. Dist. | On-going | 2020-03-02 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | Const. of Perimeter Fence at Sto. Niño Naseco Integrated School w/ Tugas Extension, Sto. Niño, Talaingod |  | 20% DF CY 2019 | Building |  | sq.m | Admin | Project Cost: | 2000000 | Target Completion Date: | 2020-06-09 23:46 | Program: | 2000000 | Planned: | 100% | No. of Persons: | 13 | On-going (Suspended last April 5, 2020 due to COVID; resumption order dated May 4, 2020)
Talaingod | STo. Niño | 1st Eng'g. Dist. | On-going | 2020-03-02 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | [7 empty] | Project Engineer: | Torrecampo | Revised Completion Date: | 2020-07-07 23:46 | Allotment: | 2000000 | Revised: | 55.86% | No. of Man-days: | 195
Talaingod | STo. Niño | 1st Eng'g. Dist. | On-going | 2020-03-02 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | [7 empty] | Implementor: | PEO | No. of days suspended: | 28 | Disbursement: | 1117200 | Actual: | 55.86%
Talaingod | STo. Niño | 1st Eng'g. Dist. | On-going | 2020-03-02 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | [7 empty] | Duration: | 100 | No. of days extended: |  |  |  | Slippage: | 0%
Talaingod | STo. Niño | 1st Eng'g. Dist. | On-going | 2020-03-02 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | [7 empty] | Date Allotment Released: | 2019-06-19 | Date completed:
Talaingod | STo. Niño | 1st Eng'g. Dist. | On-going | 2020-03-02 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | [7 empty] | Date Started: | 2020-03-02
Asuncion | New Bantayan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | Rehab. Of Multi-Purpose Hall, New Bantayan, Asuncion |  | 20% DF CY 2019 (STIMULUS) | Building |  |  | Admin | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | (Fund transferred to LGU.c /o Engr. Lilibeth Cuajao)
Asuncion | New Bantayan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 500000 | Revised: |  | No. of Man-days:
Asuncion | New Bantayan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Asuncion | New Bantayan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Asuncion | New Bantayan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Allotment Released: |  | Date completed:
Asuncion | New Bantayan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Started:
New Corella | El Salvador | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | Construction of Multi-Purpose Hall, El Salvador, New Corella |  | 20% DF CY 2019 (STIMULUS) | Building |  |  | MLGU | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Fund transferred to LGU March 23, 2019 c/o Engr. Dugoldugol
New Corella | El Salvador | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 500000 | Revised: |  | No. of Man-days:
New Corella | El Salvador | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
New Corella | El Salvador | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | El Salvador | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Allotment Released: |  | Date completed:
New Corella | El Salvador | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Started:
New Corella | Poblacion | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | Concreting of Drainage Canal , Pob., New Corella |  | 20% DF CY 2019 (STIMULUS) | Drainage |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Amended to Const. of 2 Storey Multi-Purpose Hall phase 3 (Brgy. Hall),Pob., New Corella (AIP 3rd revision CY 2019 / SB No. 4 CY 2019
New Corella | Poblacion | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 500000 | Revised: |  | No. of Man-days:
New Corella | Poblacion | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
New Corella | Poblacion | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | Poblacion | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Allotment Released: |  | Date completed:
New Corella | Poblacion | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Started:
New Corella | Cabidianan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | Rehab. Of Multi-Purpose Hall, Cabidianan, New Corella |  | 20% DF CY 2019 (STIMULUS) | Building |  |  | MLGU | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Fund transferred to LGU c/o Engr. Dugoldugol
New Corella | Cabidianan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 500000 | Revised: |  | No. of Man-days:
New Corella | Cabidianan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
New Corella | Cabidianan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | Cabidianan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Allotment Released: | 2019-02-20 | Date completed:
New Corella | Cabidianan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Started:
Talaingod | Gupitan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | Brgy. Electrification (Centro Gupitan), Gupitan, Talaingod |  | 20% DF CY 2019 (STIMULUS) | Electrification |  |  | MLGU | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Re-aligned to other stimulus projects that need additional funds to complete since the amount can not complete the project. Recommended for exact fund that can complete the project.
Talaingod | Gupitan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 500000 | Revised: |  | No. of Man-days:
Talaingod | Gupitan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Talaingod | Gupitan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Talaingod | Gupitan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Allotment Released: |  | Date completed:
Talaingod | Gupitan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Started:
Tagum City | Magugpo Poblacion | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | Rehab. of Evacuation Center, Magugpo Poblacion, Tagum City |  | 20% DF CY 2019 (STIMULUS) | Building |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Amended in the AIP 3rd revision CY 2019 /SB No. 4 CY 2019 changing the total project cost to P600,000.00
Tagum City | Magugpo Poblacion | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 500000 | Revised: |  | No. of Man-days:
Tagum City | Magugpo Poblacion | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Tagum City | Magugpo Poblacion | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Tagum City | Magugpo Poblacion | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Allotment Released: |  | Date completed:
Tagum City | Magugpo Poblacion | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Started:
Tagum City | San Agustin | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | Const. of Water System, San Agustin, Tagum City |  | 20% DF CY 2019 (STIMULUS) | Water System |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Re-aligned to other stimulus projects that need additional funds since there is no deed of donation for the proposed site.
Tagum City | San Agustin | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 500000 | Revised: |  | No. of Man-days:
Tagum City | San Agustin | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Tagum City | San Agustin | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Tagum City | San Agustin | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Allotment Released: |  | Date completed:
Tagum City | San Agustin | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Started:
Tagum City | Magugpo South | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | Const. of Brgy. Health Center, Magugpo South, Tagum City |  | 20% DF CY 2019 (STIMULUS) | Building |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Amended in the AIP 3rd revision CY 2019 /SB No. 4 CY 2019 changing the total project cost to P1,550,000.00
Tagum City | Magugpo South | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 500000 | Revised: |  | No. of Man-days:
Tagum City | Magugpo South | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Tagum City | Magugpo South | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Tagum City | Magugpo South | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Allotment Released: |  | Date completed:
Tagum City | Magugpo South | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Started:
Tagum City | Apokon | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | Rehab. Of Brgy. Health Center, Apokon, Tagum City |  | 20% DF CY 2019 (STIMULUS) | Building |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | For implementation (The brgy. council agreed not to pursue with the project if it will not be completed and needs additional funds)
Tagum City | Apokon | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 500000 | Revised: |  | No. of Man-days:
Tagum City | Apokon | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Tagum City | Apokon | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Tagum City | Apokon | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Allotment Released: | 2019-03-25 | Date completed:
Tagum City | Apokon | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Started:
Tagum City | Mankilam | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | Rehab. of Evacuation Center, Mankilam, Tagum City |  | 20% DF CY 2019 (STIMULUS) | Building |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | For implementation
Tagum City | Mankilam | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 500000 | Revised: |  | No. of Man-days:
Tagum City | Mankilam | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Tagum City | Mankilam | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Tagum City | Mankilam | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Allotment Released: | 2019-03-25 | Date completed:
Tagum City | Mankilam | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Started:
Tagum City | New Balamban | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | Rehab. of Evacuation Center, New Balambam, Tagum City |  | 20% DF CY 2019 (STIMULUS) | Building |  |  | Contract | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Final abstract #0320200899 (JJR Construction & Supply)
Tagum City | New Balamban | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 500000 | Revised: |  | No. of Man-days:
Tagum City | New Balamban | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Tagum City | New Balamban | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Tagum City | New Balamban | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Allotment Released: | 2019-09-10 | Date completed:
Tagum City | New Balamban | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Started:
Tagum City | Cuambogan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | Rehab. Of Multi-Purpose Hall, Cuambogan, Tagum City |  | 20% DF CY 2019 (STIMULUS) | Building |  |  | Contract | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | PO #2020031340 - JJR Construction
Tagum City | Cuambogan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 500000 | Revised: |  | No. of Man-days:
Tagum City | Cuambogan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Tagum City | Cuambogan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Tagum City | Cuambogan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Allotment Released: | 2019-09-10 | Date completed:
Tagum City | Cuambogan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Started:
Tagum City | Nueva Fuerza | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | Completion of Evacuation Center, Nueva Fuerza, Tagum City |  | 20% DF CY 2019 (STIMULUS) | Building |  |  | Contract | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | PO #2020031340 - JJR Construction
Tagum City | Nueva Fuerza | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 500000 | Revised: |  | No. of Man-days:
Tagum City | Nueva Fuerza | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Tagum City | Nueva Fuerza | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Tagum City | Nueva Fuerza | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Allotment Released: | 2019-09-10 | Date completed:
Tagum City | Nueva Fuerza | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Started:
Tagum City | Busaon | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | Completion. of Water System , Busaon, Tagum City |  | 20% DF CY 2019 (STIMULUS) | Water System |  |  | Contract | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | For implementation
Tagum City | Busaon | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 500000 | Revised: |  | No. of Man-days:
Tagum City | Busaon | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Tagum City | Busaon | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Tagum City | Busaon | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Allotment Released: | 2019-09-10 | Date completed:
Tagum City | Busaon | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Started:
Tagum City | Bincungan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | Const. of Drainage Canal, Bincungan, Tagum City |  | 20% DF CY 2019 (STIMULUS) | Drainage |  |  | Contract | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | PO #2020031340 - JJR Construction
Tagum City | Bincungan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 500000 | Revised: |  | No. of Man-days:
Tagum City | Bincungan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Tagum City | Bincungan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Tagum City | Bincungan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Allotment Released: | 2019-09-10 | Date completed:
Tagum City | Bincungan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Started:
Tagum City | Magugpo North | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | Rehab. of Evacuation Center, Magugpo North, Tagum City |  | 20% DF CY 2019 (STIMULUS) | Building |  |  | Contract | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | PO #2020031340 - JJR Construction
Tagum City | Magugpo North | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 500000 | Revised: |  | No. of Man-days:
Tagum City | Magugpo North | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Tagum City | Magugpo North | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Tagum City | Magugpo North | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Allotment Released: | 2019-09-10 | Date completed:
Tagum City | Magugpo North | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Started:
San Isidro | Pinamuno | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | Rehab. Of Water System at Purok Cabang & Mangga , Pinamuno, San Isidro |  | 20% DF CY 2019 (STIMULUS) | Water System |  |  | Contract | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | PO# 2020010025 (RLHV)
San Isidro | Pinamuno | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 500000 | Revised: |  | No. of Man-days:
San Isidro | Pinamuno | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
San Isidro | Pinamuno | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
San Isidro | Pinamuno | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Allotment Released: | 2019-12-06 | Date completed:
San Isidro | Pinamuno | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Started:
San Isidro | Igangon | 1st Eng'g. Dist. | On-going | 2020-05-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | Rehab. Of Water System , Igangon, San Isidro |  | 20% DF CY 2019 (STIMULUS) | Water System |  | ln.m | Admin | Project Cost: | 500000 | Target Completion Date: | 2020-07-17 | Program: | 500000 | Planned: | 12.26% | No. of Persons: | 25 | On-going
San Isidro | Igangon | 1st Eng'g. Dist. | On-going | 2020-05-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Project Engineer: | Kabinge | Revised Completion Date: | 2020-07-17 | Allotment: | 500000 | Revised: | 93.09% | No. of Man-days: | 375
San Isidro | Igangon | 1st Eng'g. Dist. | On-going | 2020-05-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: | 46.42%
San Isidro | Igangon | 1st Eng'g. Dist. | On-going | 2020-05-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Duration: | 60 | No. of days extended: |  |  |  | Slippage: | 93.09%
San Isidro | Igangon | 1st Eng'g. Dist. | On-going | 2020-05-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Allotment Released: | 2019-05-29 | Date completed:
San Isidro | Igangon | 1st Eng'g. Dist. | On-going | 2020-05-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Started: | 2020-05-18
New Corella | Del Monte | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | Rural Electrification , Del Monte, New Corella |  | 20% DF CY 2019 (STIMULUS) | Electrification |  |  |  | Project Cost: | 3000000 | Target Completion Date: |  | Program: | 3000000 | Planned: |  | No. of Persons: |  | For implementation
New Corella | Del Monte | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Project Engineer: | P.Bueno | Revised Completion Date: | 0 | Allotment: | 3000000 | Revised: |  | No. of Man-days:
New Corella | Del Monte | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
New Corella | Del Monte | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | Del Monte | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Allotment Released: |  | Date completed:
New Corella | Del Monte | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Started:
New Corella | San Roque | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | Rural Electrification at St. Bundok, San Roque, New Corella |  | 20% DF CY 2019 (STIMULUS) | Electrification |  |  |  | Project Cost: | 1000000 | Target Completion Date: |  | Program: | 1000000 | Planned: |  | No. of Persons: |  | Abstract # 0320201453
New Corella | San Roque | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Project Engineer: | P.Bueno | Revised Completion Date: | 0 | Allotment: | 1000000 | Revised: |  | No. of Man-days:
New Corella | San Roque | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
New Corella | San Roque | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | San Roque | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Allotment Released: |  | Date completed:
New Corella | San Roque | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Started:
Tagum City | Mankilam | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Anti - Crime & Government Itegration Project | Construction of Bahay Silangan for Reformation of Drug Personalities within The Military Camp/barracks, Brgy. Mankilam, Tagum City |  | 20% DF CY 2019 | Building |  |  |  | Project Cost: | 5000000 | Target Completion Date: |  | Program: | 5000000 | Planned: |  | No. of Persons: |  | Abstract #0620202232 - Post Qualification on process (ZULAR-A)
Tagum City | Mankilam | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Anti - Crime & Government Itegration Project | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 5000000 | Revised: |  | No. of Man-days:
Tagum City | Mankilam | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Anti - Crime & Government Itegration Project | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Tagum City | Mankilam | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Anti - Crime & Government Itegration Project | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Tagum City | Mankilam | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Anti - Crime & Government Itegration Project | [7 empty] | Date Allotment Released: |  | Date completed:
Tagum City | Mankilam | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Anti - Crime & Government Itegration Project | [7 empty] | Date Started:
New Corella | Poblacion | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (Special Protection & Intervention Program ) | Const. of Multi-Purpose Covered Court/Evacuation Center Ph. I, Duterte St., Poblacion, New Corella |  | 20% DF CY 2019 | Building |  |  |  | Project Cost: | 2000000 | Target Completion Date: |  | Program: | 2000000 | Planned: |  | No. of Persons: |  | Abstract #0720202481 - Post Qualification on pprocess (Royal Summit Infinity)
New Corella | Poblacion | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (Special Protection & Intervention Program ) | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 2000000 | Revised: |  | No. of Man-days:
New Corella | Poblacion | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (Special Protection & Intervention Program ) | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual:
New Corella | Poblacion | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (Special Protection & Intervention Program ) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | Poblacion | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (Special Protection & Intervention Program ) | [7 empty] | Date Allotment Released: |  | Date completed:
New Corella | Poblacion | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (Special Protection & Intervention Program ) | [7 empty] | Date Started:
New Corella | Poblacion | 1st Eng'g. Dist. | On-going | 2019-12-02 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Residential Care Facilities | Construction of Multi-Purpose Covered Court/Evacuation, Bahay Pag-Asa, New Corella, Ph.II (TF - P500,000.00) |  | 20% DF CY 2019 & TRUST FUND | Building |  | sq.m | Admin | Project Cost: | 2500000 | Target Completion Date: | 2020-04-15 | Program: | 2500000 | Planned: | 79.89% | No. of Persons: | 12 | On-going (Suspended last April 5, 2020 due to COVID; resumption order dated May 4, 2020)
New Corella | Poblacion | 1st Eng'g. Dist. | On-going | 2019-12-02 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Residential Care Facilities | [7 empty] | Project Engineer: | Mayang | Revised Completion Date: | 2020-08-30 | Allotment: | 2500000 | Revised: |  | No. of Man-days: | 180
New Corella | Poblacion | 1st Eng'g. Dist. | On-going | 2019-12-02 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Residential Care Facilities | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: |  | Actual: | 79.89%
New Corella | Poblacion | 1st Eng'g. Dist. | On-going | 2019-12-02 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Residential Care Facilities | [7 empty] | Duration: | 135 | No. of days extended: | 110 |  |  | Slippage: | 0%
New Corella | Poblacion | 1st Eng'g. Dist. | On-going | 2019-12-02 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Residential Care Facilities | [7 empty] | Date Allotment Released: | 2019-06-19 | Date completed:
New Corella | Poblacion | 1st Eng'g. Dist. | On-going | 2019-12-02 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Residential Care Facilities | [7 empty] | Date Started: | 2019-12-02
Provincewide | Provincewide | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Residential Care Facilities | Const. in Progress - Bldgs. And Other Structures |  | 20% DF CY 2019 | Building |  |  |  | Project Cost: | 2500000 | Target Completion Date: |  | Program: | 2500000 | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
Provincewide | Provincewide | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Residential Care Facilities | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 2500000 | Revised: |  | No. of Man-days:
Provincewide | Provincewide | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Residential Care Facilities | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual:
Provincewide | Provincewide | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Residential Care Facilities | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Provincewide | Provincewide | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Residential Care Facilities | [7 empty] | Date Allotment Released: |  | Date completed:
Provincewide | Provincewide | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Residential Care Facilities | [7 empty] | Date Started:
New Corella | Limbaan | 1st Eng'g. Dist. | On-going | 2019-03-20 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DISASTER PREVENTION AND MITIGATION - Flood Control and Slope Protection LS - P3,000,000.00 | Desilting of Limbaan Creek, New Corella |  | 5% CALAMITY FUND CY 2019 | creeks and canals deislted |  | ln.m | Admin | Project Cost: | 2000000 | Target Completion Date: | 2019-12-02 | Program: | 2000000 | Planned: |  | No. of Persons: |  | Suspended
New Corella | Limbaan | 1st Eng'g. Dist. | On-going | 2019-03-20 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DISASTER PREVENTION AND MITIGATION - Flood Control and Slope Protection LS - P3,000,000.00 | [7 empty] | Project Engineer: | Pilotos | Revised Completion Date: | 2019-12-02 | Allotment: | 2000000 | Revised: |  | No. of Man-days:
New Corella | Limbaan | 1st Eng'g. Dist. | On-going | 2019-03-20 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DISASTER PREVENTION AND MITIGATION - Flood Control and Slope Protection LS - P3,000,000.00 | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual:
New Corella | Limbaan | 1st Eng'g. Dist. | On-going | 2019-03-20 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DISASTER PREVENTION AND MITIGATION - Flood Control and Slope Protection LS - P3,000,000.00 | [7 empty] | Duration: | 257 | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | Limbaan | 1st Eng'g. Dist. | On-going | 2019-03-20 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DISASTER PREVENTION AND MITIGATION - Flood Control and Slope Protection LS - P3,000,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
New Corella | Limbaan | 1st Eng'g. Dist. | On-going | 2019-03-20 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DISASTER PREVENTION AND MITIGATION - Flood Control and Slope Protection LS - P3,000,000.00 | [7 empty] | Date Started: | 2019-03-20
kapalong | Mabantao-Florida | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Revitment of Dike and Slope Protection LS - P3,000,000.00 | Slope Protection Along Kapalong-Mabantao, Florida |  | 5% CALAMITY FUND CY 2019 | creeks and canals deislted |  |  |  | Project Cost: | 1000000 | Target Completion Date: |  | Program: | 1000000 | Planned: |  | No. of Persons: |  | For cancellation funded to DPWH. Budget Transferred to 5% Calamity Fund- Rehab and Recovery
kapalong | Mabantao-Florida | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Revitment of Dike and Slope Protection LS - P3,000,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 1000000 | Revised: |  | No. of Man-days:
kapalong | Mabantao-Florida | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Revitment of Dike and Slope Protection LS - P3,000,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
kapalong | Mabantao-Florida | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Revitment of Dike and Slope Protection LS - P3,000,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
kapalong | Mabantao-Florida | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Revitment of Dike and Slope Protection LS - P3,000,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
kapalong | Mabantao-Florida | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Revitment of Dike and Slope Protection LS - P3,000,000.00 | [7 empty] | Date Started:
Asuncion | New Boholano-New Loon | 1st Eng'g. Dist. | On-going | 2019-11-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Improvement of bridges and cross drainage LS - P3,000,000.00 | Impv't. of Jct. New Boholano - New Loon Cross Drainage |  | 5% CALAMITY FUND CY 2019 | Drainage |  | km | Admin | Project Cost: | 2000000 | Target Completion Date: | 2020-02-16 | Program: | 2000000 | Planned: | 42.27% | No. of Persons: |  | Suspended due to availability of equipment
Asuncion | New Boholano-New Loon | 1st Eng'g. Dist. | On-going | 2019-11-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Improvement of bridges and cross drainage LS - P3,000,000.00 | [7 empty] | Project Engineer: | Pilotos | Revised Completion Date: | 2020-02-16 | Allotment: | 2000000 | Revised: |  | No. of Man-days:
Asuncion | New Boholano-New Loon | 1st Eng'g. Dist. | On-going | 2019-11-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Improvement of bridges and cross drainage LS - P3,000,000.00 | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: | 31.7%
Asuncion | New Boholano-New Loon | 1st Eng'g. Dist. | On-going | 2019-11-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Improvement of bridges and cross drainage LS - P3,000,000.00 | [7 empty] | Duration: | 90 | No. of days extended: |  |  |  | Slippage: | -10.57%
Asuncion | New Boholano-New Loon | 1st Eng'g. Dist. | On-going | 2019-11-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Improvement of bridges and cross drainage LS - P3,000,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Asuncion | New Boholano-New Loon | 1st Eng'g. Dist. | On-going | 2019-11-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Improvement of bridges and cross drainage LS - P3,000,000.00 | [7 empty] | Date Started: | 2019-11-18
Asuncion | Saug Sonlon-Longanapan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Improvement of bridges and cross drainage LS - P3,000,000.00 | Impv't. of Jct. Saug-Sonlon-Bdry. Longanapan Cross Drainage |  | 5% CALAMITY FUND CY 2019 | Road |  |  |  | Project Cost: | 1000000 | Target Completion Date: |  | Program: | 1000000 | Planned: |  | No. of Persons: |  | For implementation
Asuncion | Saug Sonlon-Longanapan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Improvement of bridges and cross drainage LS - P3,000,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 1000000 | Revised: |  | No. of Man-days:
Asuncion | Saug Sonlon-Longanapan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Improvement of bridges and cross drainage LS - P3,000,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Asuncion | Saug Sonlon-Longanapan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Improvement of bridges and cross drainage LS - P3,000,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Asuncion | Saug Sonlon-Longanapan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Improvement of bridges and cross drainage LS - P3,000,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Asuncion | Saug Sonlon-Longanapan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Improvement of bridges and cross drainage LS - P3,000,000.00 | [7 empty] | Date Started:
Tagum City | San Miguel | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DISASTER REHABILITATION & RECOVERY PROGRAM - Building Back Better Project | Disiltation of Tagum Creek |  | 5% CALAMITY FUND CY 2019 | Creek |  |  | Admin | Project Cost: | 2000000 | Target Completion Date: |  | Program: | 2000000 | Planned: |  | No. of Persons: |  | Waiting for the delivery of materials
Tagum City | San Miguel | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DISASTER REHABILITATION & RECOVERY PROGRAM - Building Back Better Project | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 2000000 | Revised: |  | No. of Man-days:
Tagum City | San Miguel | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DISASTER REHABILITATION & RECOVERY PROGRAM - Building Back Better Project | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual:
Tagum City | San Miguel | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DISASTER REHABILITATION & RECOVERY PROGRAM - Building Back Better Project | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Tagum City | San Miguel | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DISASTER REHABILITATION & RECOVERY PROGRAM - Building Back Better Project | [7 empty] | Date Allotment Released: |  | Date completed:
Tagum City | San Miguel | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DISASTER REHABILITATION & RECOVERY PROGRAM - Building Back Better Project | [7 empty] | Date Started:
Asuncion | Pamacaun-Lasang-banate | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DISASTER REHABILITATION & RECOVERY PROGRAM - Building Back Better Project | Rehabilitation of Pamacaun-Lasang-Banate Provincial Road |  | 5% CALAMITY FUND CY 2019 | Road |  |  | Admin | Project Cost: | 1500000 | Target Completion Date: |  | Program: | 1500000 | Planned: |  | No. of Persons: |  | For implementation
Asuncion | Pamacaun-Lasang-banate | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DISASTER REHABILITATION & RECOVERY PROGRAM - Building Back Better Project | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 1500000 | Revised: |  | No. of Man-days:
Asuncion | Pamacaun-Lasang-banate | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DISASTER REHABILITATION & RECOVERY PROGRAM - Building Back Better Project | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Asuncion | Pamacaun-Lasang-banate | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DISASTER REHABILITATION & RECOVERY PROGRAM - Building Back Better Project | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Asuncion | Pamacaun-Lasang-banate | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DISASTER REHABILITATION & RECOVERY PROGRAM - Building Back Better Project | [7 empty] | Date Allotment Released: |  | Date completed:
Asuncion | Pamacaun-Lasang-banate | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DISASTER REHABILITATION & RECOVERY PROGRAM - Building Back Better Project | [7 empty] | Date Started:
New Corella | Del Pilar | 1st Eng'g. Dist. | On-going | 2020-02-17 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DISASTER REHABILITATION & RECOVERY PROGRAM - Building Back Better Project | Rehabilitation of Del Pilar Jct. Silangan |  | 5% CALAMITY FUND CY 2019 | Road |  | km | Admin | Project Cost: | 1500000 | Target Completion Date: | 2020-03-27 23:46 | Program: | 1500000 | Planned: | 81.11% | No. of Persons: | 4 | Suspended dated June 1, 2020 due to rainy days
New Corella | Del Pilar | 1st Eng'g. Dist. | On-going | 2020-02-17 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DISASTER REHABILITATION & RECOVERY PROGRAM - Building Back Better Project | [7 empty] | Project Engineer: | Gone | Revised Completion Date: | 2020-06-15 23:46 | Allotment: | 1500000 | Revised: |  | No. of Man-days: | 40
New Corella | Del Pilar | 1st Eng'g. Dist. | On-going | 2020-02-17 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DISASTER REHABILITATION & RECOVERY PROGRAM - Building Back Better Project | [7 empty] | Implementor: | PEO | No. of days suspended: | 29 | Disbursement: |  | Actual: | 81.11%
New Corella | Del Pilar | 1st Eng'g. Dist. | On-going | 2020-02-17 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DISASTER REHABILITATION & RECOVERY PROGRAM - Building Back Better Project | [7 empty] | Duration: | 40 | No. of days extended: | 51 |  |  | Slippage: | 0%
New Corella | Del Pilar | 1st Eng'g. Dist. | On-going | 2020-02-17 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DISASTER REHABILITATION & RECOVERY PROGRAM - Building Back Better Project | [7 empty] | Date Allotment Released: | 2019-07-26 | Date completed:
New Corella | Del Pilar | 1st Eng'g. Dist. | On-going | 2020-02-17 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DISASTER REHABILITATION & RECOVERY PROGRAM - Building Back Better Project | [7 empty] | Date Started: | 2020-02-17
kapalong | Mabantao-Florida | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DISASTER REHABILITATION & RECOVERY PROGRAM - Building Back Better Project | Rehabilitation of Libuganon River along Kapalong Mabantao-Florida Provincial Road |  | 5% CALAMITY FUND CY 2019 | Road |  |  | Admin | Project Cost: | 900000 |  |  | Program: | 900000 | Planned: |  | No. of Persons: |  | For implementation
kapalong | Mabantao-Florida | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DISASTER REHABILITATION & RECOVERY PROGRAM - Building Back Better Project | [7 empty] | Project Engineer: |  |  |  | Allotment: | 900000 | Revised: |  | No. of Man-days:
kapalong | Mabantao-Florida | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DISASTER REHABILITATION & RECOVERY PROGRAM - Building Back Better Project | [7 empty] | Implementor: |  |  |  | Disbursement: |  | Actual:
kapalong | Mabantao-Florida | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DISASTER REHABILITATION & RECOVERY PROGRAM - Building Back Better Project | [7 empty] | Duration: | [5 empty] | Slippage: | 0%
kapalong | Mabantao-Florida | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DISASTER REHABILITATION & RECOVERY PROGRAM - Building Back Better Project | [7 empty] | Date Allotment Released:
kapalong | Mabantao-Florida | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DISASTER REHABILITATION & RECOVERY PROGRAM - Building Back Better Project | [7 empty] | Date Started:
New Corella | Mesaoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DISASTER REHABILITATION & RECOVERY PROGRAM - Building Back Better Project | Rehabilitation of Mesaoy-Jct. Mahayahay Road |  | 5% CALAMITY FUND CY 2019 | Road |  |  | Admin | Project Cost: | 1000000 | Target Completion Date: |  | Program: | 1000000 | Planned: |  | No. of Persons: |  | For implementation
New Corella | Mesaoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DISASTER REHABILITATION & RECOVERY PROGRAM - Building Back Better Project | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 1000000 | Revised: |  | No. of Man-days:
New Corella | Mesaoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DISASTER REHABILITATION & RECOVERY PROGRAM - Building Back Better Project | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
New Corella | Mesaoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DISASTER REHABILITATION & RECOVERY PROGRAM - Building Back Better Project | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | Mesaoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DISASTER REHABILITATION & RECOVERY PROGRAM - Building Back Better Project | [7 empty] | Date Allotment Released: |  | Date completed:
New Corella | Mesaoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DISASTER REHABILITATION & RECOVERY PROGRAM - Building Back Better Project | [7 empty] | Date Started:
New Corella | Sta. Fe - Mambing | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DISASTER REHABILITATION & RECOVERY PROGRAM - Building Back Better Project | Rehabilitation of Sta. Fe- Mambing Road & Slope Protection |  | 5% CALAMITY FUND CY 2019 | Road |  |  | Admin | Project Cost: | 1320000 | Target Completion Date: |  | Program: | 1320000 | Planned: |  | No. of Persons: |  | For implementation
New Corella | Sta. Fe - Mambing | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DISASTER REHABILITATION & RECOVERY PROGRAM - Building Back Better Project | [7 empty] | Project Engineer: | Pilotos | Revised Completion Date: | 0 | Allotment: | 1320000 | Revised: |  | No. of Man-days:
New Corella | Sta. Fe - Mambing | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DISASTER REHABILITATION & RECOVERY PROGRAM - Building Back Better Project | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual:
New Corella | Sta. Fe - Mambing | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DISASTER REHABILITATION & RECOVERY PROGRAM - Building Back Better Project | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | Sta. Fe - Mambing | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DISASTER REHABILITATION & RECOVERY PROGRAM - Building Back Better Project | [7 empty] | Date Allotment Released: |  | Date completed:
New Corella | Sta. Fe - Mambing | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DISASTER REHABILITATION & RECOVERY PROGRAM - Building Back Better Project | [7 empty] | Date Started:
Asuncion | San Agustin | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DISASTER REHABILITATION & RECOVERY PROGRAM - Building Back Better Project | Rehabilitation of Canal Lining and Slope Protection at San Agustin E/S, San Agustin, Tagum City |  | 5% CALAMITY FUND CY 2019 | Drainage |  |  | Admin | Project Cost: | 350000 | Target Completion Date: |  | Program: | 350000 | Planned: |  | No. of Persons: |  | For implementation
Asuncion | San Agustin | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DISASTER REHABILITATION & RECOVERY PROGRAM - Building Back Better Project | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 350000 | Revised: |  | No. of Man-days:
Asuncion | San Agustin | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DISASTER REHABILITATION & RECOVERY PROGRAM - Building Back Better Project | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Asuncion | San Agustin | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DISASTER REHABILITATION & RECOVERY PROGRAM - Building Back Better Project | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Asuncion | San Agustin | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DISASTER REHABILITATION & RECOVERY PROGRAM - Building Back Better Project | [7 empty] | Date Allotment Released: |  | Date completed:
Asuncion | San Agustin | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DISASTER REHABILITATION & RECOVERY PROGRAM - Building Back Better Project | [7 empty] | Date Started:
Asuncion | Doña Andrea | 1st Eng'g. Dist. | On-going | 2020-02-17 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DILG | Construction of Halfway House, Brgy. Doña Andrea, Asuncion |  | DILG | Building |  | sq.m | Admin | Project Cost: | 5000000 | Target Completion Date: | 2020-08-14 23:59 | Program: | 5000000 | Planned: | 54.84% | No. of Persons: | 38 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 6, 2020)
Asuncion | Doña Andrea | 1st Eng'g. Dist. | On-going | 2020-02-17 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DILG | [7 empty] | Project Engineer: | Dadula | Revised Completion Date: | 2020-09-12 23:59 | Allotment: | 5000000 | Revised: |  | No. of Man-days: | 1178
Asuncion | Doña Andrea | 1st Eng'g. Dist. | On-going | 2020-02-17 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DILG | [7 empty] | Implementor: | PEO | No. of days suspended: | 29 | Disbursement: |  | Actual: | 54.84%
Asuncion | Doña Andrea | 1st Eng'g. Dist. | On-going | 2020-02-17 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DILG | [7 empty] | Duration: | 180 | No. of days extended: |  |  |  | Slippage: | 0%
Asuncion | Doña Andrea | 1st Eng'g. Dist. | On-going | 2020-02-17 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DILG | [7 empty] | Date Allotment Released: | CY 2019 | Date completed:
Asuncion | Doña Andrea | 1st Eng'g. Dist. | On-going | 2020-02-17 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DILG | [7 empty] | Date Started: | 2020-02-17
Asuncion | Cambanogoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Lot Purchase | Purchase of Lot for Cemetery, Cambanogoy, Asuncion |  | SUPPLEMENTAL BUDGET NO. 1 CY 2019 (STIMULUS) | Land |  |  |  | Project Cost: | 1500000 | Target Completion Date: |  | Program: | 1500000 | Planned: |  | No. of Persons: |  | Documents for fund transfer to be complied by the LGUs. Letter sent dated June 18, 2019
Asuncion | Cambanogoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Lot Purchase | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 1500000 | Revised: |  | No. of Man-days:
Asuncion | Cambanogoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Lot Purchase | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Asuncion | Cambanogoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Lot Purchase | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Asuncion | Cambanogoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Lot Purchase | [7 empty] | Date Allotment Released: |  | Date completed:
Asuncion | Cambanogoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Lot Purchase | [7 empty] | Date Started:
New Corella | San Roque | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Lot Purchase | Purchase of Lot for Cemetery, San Roque, New Corella |  | SUPPLEMENTAL BUDGET NO. 1 CY 2019 (STIMULUS) | Land |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Documents for fund transfer to be complied by the LGUs. Letter sent dated June 18, 2019
New Corella | San Roque | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Lot Purchase | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 500000 | Revised: |  | No. of Man-days:
New Corella | San Roque | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Lot Purchase | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
New Corella | San Roque | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Lot Purchase | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | San Roque | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Lot Purchase | [7 empty] | Date Allotment Released: |  | Date completed:
New Corella | San Roque | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Lot Purchase | [7 empty] | Date Started:
Asuncion | Sagayen | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | Rehab/Impvt of Gymnasium, Sagayen, Asuncion |  | SUPPLEMENTAL BUDGET NO. 1 CY 2019 (STIMULUS) | Building |  |  |  | Project Cost: | 1500000 | Target Completion Date: |  | Program: | 1500000 | Planned: |  | No. of Persons: |  | Final Abstract # 0320200900 (Alpebel Builders & Supply Corp.)
Asuncion | Sagayen | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 1500000 | Revised: |  | No. of Man-days:
Asuncion | Sagayen | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Asuncion | Sagayen | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Asuncion | Sagayen | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Allotment Released: |  | Date completed:
Asuncion | Sagayen | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Started:
New Corella | New Sambog | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | Purchase of Lot for Resettlement Site, New Sambog, New Corella |  | SUPPLEMENTAL BUDGET NO. 1 CY 2019 (STIMULUS) | Land |  |  |  | Project Cost: | 1500000 | Target Completion Date: |  | Program: | 1500000 | Planned: |  | No. of Persons: |  | for fund transfer. Waiting for LGU documents. Liquidation of previous fund transfer for the water system project of LGU.
New Corella | New Sambog | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 1500000 | Revised: |  | No. of Man-days:
New Corella | New Sambog | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
New Corella | New Sambog | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | New Sambog | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Allotment Released: |  | Date completed:
New Corella | New Sambog | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Started:
Asuncion | Sagayen | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | Installation of Street Lights at Prk 1,2,3,4, Sagayen, Asuncion |  | SUPPLEMENTAL BUDGET NO. 1 CY 2019 (STIMULUS) | Electrification |  |  |  | Project Cost: | 1000000 | Target Completion Date: |  | Program: | 1000000 | Planned: |  | No. of Persons: |  | Purchase Order # 2019113377 (Tagum Builders)
Asuncion | Sagayen | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 1000000 | Revised: |  | No. of Man-days:
Asuncion | Sagayen | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Asuncion | Sagayen | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Asuncion | Sagayen | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Allotment Released: |  | Date completed:
Asuncion | Sagayen | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Started:
Asuncion | Concepcion | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | Rehab/Imprvt. Of FMR, Prk 3,7, & 8, Concepcion, Asuncion |  | SUPPLEMENTAL BUDGET NO. 1 CY 2019 (STIMULUS) | Road |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Waiting for equipment availability as of Feb. 5, 2020 report submitted by Engr. Cuajao
Asuncion | Concepcion | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 500000 | Revised: |  | No. of Man-days:
Asuncion | Concepcion | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Asuncion | Concepcion | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Asuncion | Concepcion | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Allotment Released: |  | Date completed:
Asuncion | Concepcion | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Started:
New Corella | San Jose | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | Farm to Market Road, San Jose, New Corella |  | SUPPLEMENTAL BUDGET NO. 1 CY 2019 (STIMULUS) | Road |  |  |  | Project Cost: | 2000000 | Target Completion Date: |  | Program: | 2000000 | Planned: |  | No. of Persons: |  | For cancellation
New Corella | San Jose | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 2000000 | Revised: |  | No. of Man-days:
New Corella | San Jose | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
New Corella | San Jose | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | San Jose | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Allotment Released: |  | Date completed:
New Corella | San Jose | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Started:
New Corella | New Sambog | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | Const. of Water System, New Sambog, New Corella |  | SUPPLEMENTAL BUDGET NO. 1 CY 2019 (STIMULUS) | Water System |  |  | MLGU | Project Cost: | 1000000 | Target Completion Date: |  | Program: | 1000000 | Planned: |  | No. of Persons: |  | Fund transferred to LGU
New Corella | New Sambog | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 1000000 | Revised: |  | No. of Man-days:
New Corella | New Sambog | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
New Corella | New Sambog | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | New Sambog | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Allotment Released: |  | Date completed:
New Corella | New Sambog | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Started:
New Corella | Limbaan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | Const. of Drainage Canal from Prk. 3, 1-A, 2-A to Prk 1-B, Brgy Site (Ph. 2), Limbaan, New Corella |  | SUPPLEMENTAL BUDGET NO. 1 CY 2019 (STIMULUS) | Flood Control - Drainage |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | POW preparation on going c/o PDPM
New Corella | Limbaan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 500000 | Revised: |  | No. of Man-days:
New Corella | Limbaan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
New Corella | Limbaan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | Limbaan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Allotment Released: |  | Date completed:
New Corella | Limbaan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Started:
New Corella | Patrocenio | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | Const. of FMR from Prk 1 to Sitio Magsaysay via Pundol & Prk 4, Patrocenio, New Corella |  | SUPPLEMENTAL BUDGET NO. 1 CY 2019 (STIMULUS) | Road |  |  |  | Project Cost: | 2000000 | Target Completion Date: |  | Program: | 2000000 | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
New Corella | Patrocenio | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 2000000 | Revised: |  | No. of Man-days:
New Corella | Patrocenio | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
New Corella | Patrocenio | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | Patrocenio | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Allotment Released: |  | Date completed:
New Corella | Patrocenio | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Started:
New Corella | San Jose | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | Const. of Multi-Purpose Pavement, San Jose, New Corella |  | SUPPLEMENTAL BUDGET NO. 1 CY 2019 (STIMULUS) | Building |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | POW approved but allotment not yet requested waiting for deed of donation c/o Engr. Canillada
New Corella | San Jose | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 500000 | Revised: |  | No. of Man-days:
New Corella | San Jose | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
New Corella | San Jose | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | San Jose | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Allotment Released: |  | Date completed:
New Corella | San Jose | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Started:
Asuncion | Buan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | Const. of Multipurpose Covered Court, Buan, Asuncion |  | SUPPLEMENTAL BUDGET NO. 1 CY 2019 (STIMULUS) | Covered Court |  |  | MLGU | Project Cost: | 2500000 | Target Completion Date: |  | Program: | 2500000 | Planned: |  | No. of Persons: |  | Fund transferred to LGU
Asuncion | Buan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 2500000 | Revised: |  | No. of Man-days:
Asuncion | Buan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Asuncion | Buan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Asuncion | Buan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Allotment Released: | 2019-06-26 | Date completed:
Asuncion | Buan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Started:
Asuncion | Pamacaun | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | Const. of Multipurpose Covered Court, Pamacaun, Asuncion |  | SUPPLEMENTAL BUDGET NO. 1 CY 2019 (STIMULUS) | Covered Court |  |  | MLGU | Project Cost: | 2500000 | Target Completion Date: |  | Program: | 2500000 | Planned: |  | No. of Persons: |  | Fund transferred to LGU
Asuncion | Pamacaun | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 2500000 | Revised: |  | No. of Man-days:
Asuncion | Pamacaun | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Asuncion | Pamacaun | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Asuncion | Pamacaun | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Allotment Released: | 2019-05-29 | Date completed:
Asuncion | Pamacaun | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Started:
New Corella | Poblacion | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | Const. of 2 Storey Multi purpose Hall Ph.2 (Brgy. Hall) , Poblacion, New Corella |  | SUPPLEMENTAL BUDGET NO. 1 CY 2019 (STIMULUS) | Building |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
New Corella | Poblacion | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 500000 | Revised: |  | No. of Man-days:
New Corella | Poblacion | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
New Corella | Poblacion | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | Poblacion | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Allotment Released: |  | Date completed:
New Corella | Poblacion | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Started:
New Corella | Patrocenio | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | Expansion of Multi-Purpose Hall ( Brgy. Hall), Patrocenio, New Corella |  | SUPPLEMENTAL BUDGET NO. 1 CY 2019 (STIMULUS) | Building |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Purchase Order # 2020020796 (JJR Construction)
New Corella | Patrocenio | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 500000 | Revised: |  | No. of Man-days:
New Corella | Patrocenio | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
New Corella | Patrocenio | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | Patrocenio | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Allotment Released: |  | Date completed:
New Corella | Patrocenio | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Started:
New Corella | Poblacion | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | Rehabilitation of Water System in PEEDO-LPRRC, Brgy. Poblacion, New Corella |  | SUPPLEMENTAL BUDGET NO. 1 CY 2019 (STIMULUS) | Water System |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Purchase Order # 2020010009 (ANCOR Water Resources)
New Corella | Poblacion | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 500000 | Revised: |  | No. of Man-days:
New Corella | Poblacion | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
New Corella | Poblacion | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | Poblacion | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Allotment Released: |  | Date completed:
New Corella | Poblacion | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Started:
Talaingod | Salawao-Sto. Niño | 1st Eng'g. Dist. | On-going | 2020-06-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | Provincial Livestock & Poultry Multiplier Farm Road Network Construction, Sitio Salawao, Sto. Niño, Talaingod |  | SUPPLEMENTAL BUDGET NO. 1 CY 2019 (STIMULUS) | Conc. Pavement |  | sq.m | Admin | Project Cost: | 5500000 | Target Completion Date: | 2020-07-13 23:46 | Program: | 5500000 | Planned: | 30.06% | No. of Persons: | 15 | On-going (For time extension)
Talaingod | Salawao-Sto. Niño | 1st Eng'g. Dist. | On-going | 2020-06-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Project Engineer: | Pasiona/Juan | Revised Completion Date: | 2020-08-10 23:46 | Allotment: | 5500000 | Revised: |  | No. of Man-days: | 225
Talaingod | Salawao-Sto. Niño | 1st Eng'g. Dist. | On-going | 2020-06-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Implementor: | PEO | No. of days suspended: | 28 | Disbursement: | 1653300 | Actual: | 30.06%
Talaingod | Salawao-Sto. Niño | 1st Eng'g. Dist. | On-going | 2020-06-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Duration: | 120 | No. of days extended: |  |  |  | Slippage: | 0%
Talaingod | Salawao-Sto. Niño | 1st Eng'g. Dist. | On-going | 2020-06-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Allotment Released: | CY 2019 | Date completed:
Talaingod | Salawao-Sto. Niño | 1st Eng'g. Dist. | On-going | 2020-06-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Started: | 2020-03-16
Talaingod | Tapayanon | 1st Eng'g. Dist. | On-going | 2019-11-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | Proposed Road Opening of Tawinian-Tapayanon Road Section |  | SUPPLEMENTAL BUDGET NO. 4 CY 2019 (STIMULUS) | Road |  | km | Admin | Project Cost: | 10000000 | Target Completion Date: | 2020-09-18 23:46 | Program: | 10000000 | Planned: | 27.08% | No. of Persons: | 5 | On-going (Suspended last April 5, 2020 due to COVID; resumption order dated May 4, 2020); Equipment Rental 1 unit Backhoe (Bidding July 16, 2020)
Talaingod | Tapayanon | 1st Eng'g. Dist. | On-going | 2019-11-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Project Engineer: | Garcia | Revised Completion Date: | 2020-10-16 23:46 | Allotment: | 10000000 | Revised: |  | No. of Man-days: | 319
Talaingod | Tapayanon | 1st Eng'g. Dist. | On-going | 2019-11-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Implementor: | PEO | No. of days suspended: | 28 | Disbursement: |  | Actual: | 27.08%
Talaingod | Tapayanon | 1st Eng'g. Dist. | On-going | 2019-11-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Duration: | 306 | No. of days extended: |  |  |  | Slippage: | 0%
Talaingod | Tapayanon | 1st Eng'g. Dist. | On-going | 2019-11-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Allotment Released: | 2019-11-15 | Date completed:
Talaingod | Tapayanon | 1st Eng'g. Dist. | On-going | 2019-11-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Started: | 2019-11-18
kapalong | Maniki | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | Completion of Brgy. Health Center, Maniki, Kapalong |  | SUPPLEMENTAL BUDGET NO. 4 CY 2019 (STIMULUS) | Building |  |  |  | Project Cost: | 627000 | Target Completion Date: |  | Program: | 627000 | Planned: |  | No. of Persons: |  | PROJECT Was funded by LGU, Kapalong
kapalong | Maniki | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 627000 | Revised: |  | No. of Man-days:
kapalong | Maniki | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
kapalong | Maniki | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
kapalong | Maniki | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Allotment Released: |  | Date completed:
kapalong | Maniki | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Started:
Asuncion | New Santiago | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | Construction of Potable Water System at Purok 6, New Santiago, Asuncion |  | SUPPLEMENTAL BUDGET NO. 4 CY 2019 (STIMULUS) | Water System |  |  | contract | Project Cost: | 1000000 | Target Completion Date: |  | Program: | 1000000 | Planned: |  | No. of Persons: |  | Change of POW to Contract
Asuncion | New Santiago | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 1000000 | Revised: |  | No. of Man-days:
Asuncion | New Santiago | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Asuncion | New Santiago | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Asuncion | New Santiago | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Allotment Released: |  | Date completed:
Asuncion | New Santiago | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Started:
New Corella | Poblacion | 1st Eng'g. Dist. | On-going | 2019-11-25 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | Construction of Children's Playground with Amenities, Poblacion, New Corella |  | SUPPLEMENTAL BUDGET NO. 4 CY 2019 (STIMULUS) | Building |  | sq.m | Admin | Project Cost: | 2500000 | Target Completion Date: | 2020-03-03 23:59 | Program: | 2500000 | Planned: | 46.63% | No. of Persons: | 10 | On-going (Suspended effective April 5, 2020 due to COVID; resumption order dated May 4, 2020)
New Corella | Poblacion | 1st Eng'g. Dist. | On-going | 2019-11-25 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Project Engineer: | Mayang | Revised Completion Date: | 2020-04-30 23:59 | Allotment: | 2500000 | Revised: |  | No. of Man-days: | 150
New Corella | Poblacion | 1st Eng'g. Dist. | On-going | 2019-11-25 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Implementor: | PEO | No. of days suspended: | 28 | Disbursement: | 1029250 | Actual: | 46.63%
New Corella | Poblacion | 1st Eng'g. Dist. | On-going | 2019-11-25 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Duration: | 100 | No. of days extended: | 30 |  |  | Slippage: | 0%
New Corella | Poblacion | 1st Eng'g. Dist. | On-going | 2019-11-25 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Allotment Released: | 2019-12-06 | Date completed:
New Corella | Poblacion | 1st Eng'g. Dist. | On-going | 2019-11-25 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Started: | 2019-11-25
Tagum City | Magugpo Poblacion | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | Rehabilitation of Evacuation Center at Magugpo Pob., Tagum City |  | SUPPLEMENTAL BUDGET NO. 4 CY 2019 (STIMULUS) | Building |  |  |  | Project Cost: | 600000 | Target Completion Date: |  | Program: | 600000 | Planned: |  | No. of Persons: |  | Purchase Order # 2020020796 (JJR Construction)
Tagum City | Magugpo Poblacion | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 600000 | Revised: |  | No. of Man-days:
Tagum City | Magugpo Poblacion | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Tagum City | Magugpo Poblacion | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Tagum City | Magugpo Poblacion | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Allotment Released: |  | Date completed:
Tagum City | Magugpo Poblacion | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Started:
Tagum City | Magugpo SOuth | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | Construction of Brgy. Health Center at Magugpo South, Tagum City |  | SUPPLEMENTAL BUDGET NO. 4 CY 2019 (STIMULUS) | Building |  |  |  | Project Cost: | 1550000 | Target Completion Date: |  | Program: | 1550000 | Planned: |  | No. of Persons: |  | Purchase Order # 20022150 (On-process)
Tagum City | Magugpo SOuth | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 1550000 | Revised: |  | No. of Man-days:
Tagum City | Magugpo SOuth | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Tagum City | Magugpo SOuth | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Tagum City | Magugpo SOuth | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Allotment Released: |  | Date completed:
Tagum City | Magugpo SOuth | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Started:
New Corella | Limbaan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | Rehab. Of Multi-Purpose Building (Evacuation Center), Limbaan, New Corella |  | SUPPLEMENTAL BUDGET NO. 4 CY 2019 (STIMULUS) | Building |  |  |  | Project Cost: | 600000 | Target Completion Date: |  | Program: | 600000 | Planned: |  | No. of Persons: |  | From SB # 1 to SB # 4 CY 2019 (Transfer to Contract) Procurement on process
New Corella | Limbaan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 600000 | Revised: |  | No. of Man-days:
New Corella | Limbaan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
New Corella | Limbaan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | Limbaan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Allotment Released: |  | Date completed:
New Corella | Limbaan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Started:
San Isidro | Sagayen-Sawata | 1st Eng'g. Dist. | On-going | 2019-09-09 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | Improvement of Km. 9 Sagayen-Sawata Provincial Road, San Isidro, Ph. II |  | SUPPLEMENTAL BUDGET NO. 4 CY 2019 (STIMULUS) | Road |  | ln.m | Admin | Project Cost: | 4591029 | Target Completion Date: | 2020-03-27 | Program: | 4591029 | Planned: | 45% | No. of Persons: | 6 | On-going (Suspended last April 5, 2020 due to COVID; resumption order dated May 4, 2020)
San Isidro | Sagayen-Sawata | 1st Eng'g. Dist. | On-going | 2019-09-09 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Project Engineer: | Limpo | Revised Completion Date: |  | Allotment: | 4591029 | Revised: |  | No. of Man-days: | 138
San Isidro | Sagayen-Sawata | 1st Eng'g. Dist. | On-going | 2019-09-09 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: | 1609155.6645 | Actual: | 35.05%
San Isidro | Sagayen-Sawata | 1st Eng'g. Dist. | On-going | 2019-09-09 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Duration: | 200 | No. of days extended: |  |  |  | Slippage: | -9.95%
San Isidro | Sagayen-Sawata | 1st Eng'g. Dist. | On-going | 2019-09-09 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Allotment Released: | 2019-12-12 | Date completed:
San Isidro | Sagayen-Sawata | 1st Eng'g. Dist. | On-going | 2019-09-09 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Started: | 2019-09-09
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Department of Agriculture | Poultry House and Training Center Sto. Niño, Talaingod |  | PROJECTS FOR PROVINCIAL VETERINARY | Building |  |  | Contract | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Final Abstract # 012020012 (Alpebel Builders & Supply Corp.)
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Department of Agriculture | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 500000 | Revised: |  | No. of Man-days:
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Department of Agriculture | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Department of Agriculture | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Department of Agriculture | [7 empty] | Date Allotment Released: |  | Date completed:
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Department of Agriculture | [7 empty] | Date Started:
Talaingod | Salawao-Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Department of Agriculture | Establishment of Livestock and Poultry Mutiplier Farm, Sitio Salawao, Sto. Niño, Talaingod |  | Department of Agriculture - Regional Field Office XI | Building |  |  |  | Project Cost: | 600000 | Target Completion Date: |  | Program: | 600000 | Planned: |  | No. of Persons: |  | Final Abstract # 012020012 (Alpebel Builders & Supply Corp.)
Talaingod | Salawao-Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Department of Agriculture | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 600000 | Revised: |  | No. of Man-days:
Talaingod | Salawao-Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Department of Agriculture | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Talaingod | Salawao-Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Department of Agriculture | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Talaingod | Salawao-Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Department of Agriculture | [7 empty] | Date Allotment Released: |  | Date completed:
Talaingod | Salawao-Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Department of Agriculture | [7 empty] | Date Started:
kapalong | Mabantao-Florida | 1st Eng'g. Dist. | On-going | 2019-10-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CMGP | Road Upgrading of Kapalong - Mabantao - Florida Road with Bridge Component |  | CMGP CY 2019 | Concreting |  | ln.m | Contract | Project Cost: | 15435008 | Target Completion Date: | 2020-03-10 23:59 | Program: | 15435008 | Planned: | 100% | No. of Persons: | 19 | On-going (Suspended last April 5, 2020 due to COVID; resumption order dated May 4, 2020)
kapalong | Mabantao-Florida | 1st Eng'g. Dist. | On-going | 2019-10-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CMGP | [7 empty] | Project Engineer: | Japay/Quirante | Revised Completion Date: | 2020-04-29 23:59 | Allotment: | 15435008 | Revised: | 81.81% | No. of Man-days: | 551
kapalong | Mabantao-Florida | 1st Eng'g. Dist. | On-going | 2019-10-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CMGP | [7 empty] | Implementor: | LEGACY | No. of days suspended: | 30 | Disbursement: | 6174003.2 | Actual: | 78.93%
kapalong | Mabantao-Florida | 1st Eng'g. Dist. | On-going | 2019-10-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CMGP | [7 empty] | Duration: | 147 | No. of days extended: | 20 |  |  | Slippage: | -2.882%
kapalong | Mabantao-Florida | 1st Eng'g. Dist. | On-going | 2019-10-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CMGP | [7 empty] | Date Allotment Released: | CY 2019 | Date completed:
kapalong | Mabantao-Florida | 1st Eng'g. Dist. | On-going | 2019-10-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CMGP | [7 empty] | Date Started: | 2019-10-16
New Corella | Del Pilar | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | LGSF | Rehabilitation of Dasing to Monte Carlo FMR, Del Pilar, New Corella |  | LGSF CY 2019 | Concreting |  |  | Contract | Project Cost: | 40000000 | Target Completion Date: |  | Program: | 40000000 | Planned: |  | No. of Persons: |  | For implementation (Awarded to Rely Construction and Supply)
New Corella | Del Pilar | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | LGSF | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 40000000 | Revised: |  | No. of Man-days:
New Corella | Del Pilar | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | LGSF | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
New Corella | Del Pilar | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | LGSF | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | Del Pilar | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | LGSF | [7 empty] | Date Allotment Released: |  | Date completed:
New Corella | Del Pilar | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | LGSF | [7 empty] | Date Started:
Tagum City | Magugpo South | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | LGSF | Concreting of Visayan Village - Purok exodus - Purok Rafael, Brgy. Magugpo South, Tagum City |  | LGSF CY 2019 | Concreting |  |  | Contract | Project Cost: | 40000000 | Target Completion Date: |  | Program: | 40000000 | Planned: |  | No. of Persons: |  | For implementation (Awarded to Legacy Construction Corporation)
Tagum City | Magugpo South | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | LGSF | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 40000000 | Revised: |  | No. of Man-days:
Tagum City | Magugpo South | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | LGSF | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Tagum City | Magugpo South | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | LGSF | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Tagum City | Magugpo South | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | LGSF | [7 empty] | Date Allotment Released: |  | Date completed:
Tagum City | Magugpo South | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | LGSF | [7 empty] | Date Started:
Asuncion | Magatos-Bantayan | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 001 - Jct. Highway Magatos - New Bantayan |  | GENERAL FUND CY 2020 | Maintenance | 7.1 | km | MBA | Project Cost: | 564839.9739 | Target Completion Date: | 2020-12-31 23:59 | Program: | 564839.9739 | Planned: | 31.14% | No. of Persons: | 17 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020)
Asuncion | Magatos-Bantayan | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 564839.9739 | Revised: |  | No. of Man-days: | 374
Asuncion | Magatos-Bantayan | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 57334.17 | Actual: | 31.14%
Asuncion | Magatos-Bantayan | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0%
Asuncion | Magatos-Bantayan | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
Asuncion | Magatos-Bantayan | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started: | 2020-01-02
Asuncion | Magatos-Bantayan | 1st Eng'g. Dist. | On-going |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 001 - Jct. Highway Magatos - New Bantayan |  | GENERAL FUND CY 2020 | Maintenance | 7.1 | km | CBRMC | Project Cost: | 230737.1976 | Target Completion Date: |  | Program: | 230737.1976 | Planned: |  | No. of Persons: |  | Purchase Request # 19125305 (On process)
Asuncion | Magatos-Bantayan | 1st Eng'g. Dist. | On-going |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 230737.1976 | Revised: |  | No. of Man-days:
Asuncion | Magatos-Bantayan | 1st Eng'g. Dist. | On-going |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Asuncion | Magatos-Bantayan | 1st Eng'g. Dist. | On-going |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Asuncion | Magatos-Bantayan | 1st Eng'g. Dist. | On-going |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: |  | Date completed:
Asuncion | Magatos-Bantayan | 1st Eng'g. Dist. | On-going |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started:
Asuncion | Magatos-Pagsabangan | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 002 - Magatos - Bdry. Pagsabangan |  | GENERAL FUND CY 2020 | Maintenance | 8.33 | km | MBA | Project Cost: | 653221.626 | Target Completion Date: | 2020-12-31 23:59 | Program: | 653221.626 | Planned: | 28.54% | No. of Persons: | 17 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020)
Asuncion | Magatos-Pagsabangan | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 653221.626 | Revised: |  | No. of Man-days: | 374
Asuncion | Magatos-Pagsabangan | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 71713.44 | Actual: | 28.54%
Asuncion | Magatos-Pagsabangan | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0%
Asuncion | Magatos-Pagsabangan | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
Asuncion | Magatos-Pagsabangan | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started: | 2020-01-02
Asuncion | Magatos-Pagsabangan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 002 - Magatos - Bdry. Pagsabangan |  | GENERAL FUND CY 2020 | Maintenance | 8.33 | km | CBRMC | Project Cost: | 280180.88 | Target Completion Date: |  | Program: | 280180.88 | Planned: |  | No. of Persons: |  | Purchase Request # 19125306 (On process)
Asuncion | Magatos-Pagsabangan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 280180.88 | Revised: |  | No. of Man-days:
Asuncion | Magatos-Pagsabangan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Asuncion | Magatos-Pagsabangan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Asuncion | Magatos-Pagsabangan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: |  | Date completed:
Asuncion | Magatos-Pagsabangan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started:
Asuncion | New Bantayan | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 003 - Ilog - New Bantayan |  | GENERAL FUND CY 2020 | Maintenance | 2.68 | km | MBA | Project Cost: | 236174.847 | Target Completion Date: | 2020-12-31 23:59 | Program: | 236174.847 | Planned: | 15.36% | No. of Persons: | 17 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020)
Asuncion | New Bantayan | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 236174.847 | Revised: |  | No. of Man-days: | 374
Asuncion | New Bantayan | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 22629.74 | Actual: | 15.36%
Asuncion | New Bantayan | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0%
Asuncion | New Bantayan | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
Asuncion | New Bantayan | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started: | 2020-01-02
Asuncion | New Bantayan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 003 - Ilog - New Bantayan |  | GENERAL FUND CY 2020 | Maintenance | 2.68 | km | CBRMC | Project Cost: | 70633.836 | Target Completion Date: |  | Program: | 70633.836 | Planned: |  | No. of Persons: |  | Purchase Request # 19125307 (On process)
Asuncion | New Bantayan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 70633.836 | Revised: |  | No. of Man-days:
Asuncion | New Bantayan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Asuncion | New Bantayan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Asuncion | New Bantayan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: |  | Date completed:
Asuncion | New Bantayan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started:
Asuncion | Monte Carlo-Del Pilar | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 005 - Asuncion - Monte Carlo - Del Pilar |  | GENERAL FUND CY 2020 | Maintenance | 9.93 | km | MBA | Project Cost: | 716344.9167 | Target Completion Date: | 2020-12-31 23:59 | Program: | 716344.9167 | Planned: | 29.09% | No. of Persons: | 17 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020)
Asuncion | Monte Carlo-Del Pilar | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 716344.9167 | Revised: |  | No. of Man-days: | 374
Asuncion | Monte Carlo-Del Pilar | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 33056.21 | Actual: | 29.09%
Asuncion | Monte Carlo-Del Pilar | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0%
Asuncion | Monte Carlo-Del Pilar | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
Asuncion | Monte Carlo-Del Pilar | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started: | 2020-01-02
Asuncion | Monte Carlo-Del Pilar | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 005 - Asuncion - Monte Carlo - Del Pilar |  | GENERAL FUND CY 2020 | Maintenance | 9.93 | km | CBRMC | Project Cost: | 360232.5636 | Target Completion Date: |  | Program: | 360232.5636 | Planned: |  | No. of Persons: |  | Purchase Request # 19125308 (On process)
Asuncion | Monte Carlo-Del Pilar | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 360232.5636 | Revised: |  | No. of Man-days:
Asuncion | Monte Carlo-Del Pilar | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Asuncion | Monte Carlo-Del Pilar | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Asuncion | Monte Carlo-Del Pilar | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: |  | Date completed:
Asuncion | Monte Carlo-Del Pilar | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started:
Asuncion | Canatan-Magatos | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 006 - Jct. Highway Canatan - Magatos |  | GENERAL FUND CY 2020 | Maintenance | 4.85 | km | MBA | Project Cost: | 391296.517 | Target Completion Date: | 2020-12-31 23:59 | Program: | 391296.517 | Planned: | 24.95% | No. of Persons: | 17 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020)
Asuncion | Canatan-Magatos | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 391296.517 | Revised: |  | No. of Man-days: | 374
Asuncion | Canatan-Magatos | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 33056.21 | Actual: | 24.95%
Asuncion | Canatan-Magatos | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0%
Asuncion | Canatan-Magatos | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
Asuncion | Canatan-Magatos | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started: | 2020-01-02
Asuncion | Canatan-Magatos | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 006 - Jct. Highway Canatan - Magatos |  | GENERAL FUND CY 2020 | Maintenance | 4.85 | km | CBRMC | Project Cost: | 164812.284 | Target Completion Date: |  | Program: | 164812.284 | Planned: |  | No. of Persons: |  | Purchase Request # 19125309 (On process)
Asuncion | Canatan-Magatos | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 164812.284 | Revised: |  | No. of Man-days:
Asuncion | Canatan-Magatos | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Asuncion | Canatan-Magatos | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Asuncion | Canatan-Magatos | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: |  | Date completed:
Asuncion | Canatan-Magatos | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started:
Asuncion | Saug-Sonlon-Longanapan | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 010 - Saug - Sonlon - Bdry. Longanapan |  | GENERAL FUND CY 2020 | Maintenance | 11.6 | km | MBA | Project Cost: | 1102041.4797 | Target Completion Date: | 2020-12-31 23:59 | Program: | 1102041.4797 | Planned: | 21.92% | No. of Persons: | 17 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020)
Asuncion | Saug-Sonlon-Longanapan | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 1102041.4797 | Revised: |  | No. of Man-days: | 374
Asuncion | Saug-Sonlon-Longanapan | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 83166.18 | Actual: | 21.92%
Asuncion | Saug-Sonlon-Longanapan | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0%
Asuncion | Saug-Sonlon-Longanapan | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
Asuncion | Saug-Sonlon-Longanapan | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started: | 2020-01-02
Asuncion | Saug-Sonlon-Longanapan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 010 - Saug - Sonlon - Bdry. Longanapan |  | GENERAL FUND CY 2020 | Maintenance | 11.6 | km | CBRMC | Project Cost: | 197774.7408 | Target Completion Date: |  | Program: | 197774.7408 | Planned: |  | No. of Persons: |  | Purchase Request # 19125310 (On process)
Asuncion | Saug-Sonlon-Longanapan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 197774.7408 | Revised: |  | No. of Man-days:
Asuncion | Saug-Sonlon-Longanapan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Asuncion | Saug-Sonlon-Longanapan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Asuncion | Saug-Sonlon-Longanapan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: |  | Date completed:
Asuncion | Saug-Sonlon-Longanapan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started:
Asuncion | New Visayas-Buan | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 011 - Jct. New Visayas - Buan |  | GENERAL FUND CY 2020 | Maintenance | 2.99 | km | MBA | Project Cost: | 134598.4525 | Target Completion Date: | 2020-12-31 23:59 | Program: | 134598.4525 | Planned: | 7.72% | No. of Persons: | 17 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020)
Asuncion | New Visayas-Buan | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 134598.4525 | Revised: |  | No. of Man-days: | 374
Asuncion | New Visayas-Buan | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 10391.0005 | Actual: | 7.72%
Asuncion | New Visayas-Buan | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0%
Asuncion | New Visayas-Buan | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
Asuncion | New Visayas-Buan | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started: | 2020-01-02
Asuncion | New Visayas-Buan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 011 - Jct. New Visayas - Buan |  | GENERAL FUND CY 2020 | Maintenance | 2.99 | km | CBRMC | Project Cost: | 124786.4436 | Target Completion Date: |  | Program: | 124786.4436 | Planned: |  | No. of Persons: |  | Purchase Request # 19125311 (On process)
Asuncion | New Visayas-Buan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 124786.4436 | Revised: |  | No. of Man-days:
Asuncion | New Visayas-Buan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Asuncion | New Visayas-Buan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Asuncion | New Visayas-Buan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: |  | Date completed:
Asuncion | New Visayas-Buan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started:
Asuncion | San Vicente-Butay | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 013 - San Vicente - Butay |  | GENERAL FUND CY 2020 | Maintenance | 7.52 | km | MBA | Project Cost: | 579541.5407 | Target Completion Date: | 2020-12-31 23:59 | Program: | 579541.5407 | Planned: | 30.2% | No. of Persons: | 17 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020)
Asuncion | San Vicente-Butay | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 579541.5407 | Revised: |  | No. of Man-days: | 374
Asuncion | San Vicente-Butay | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 123616.2106 | Actual: | 30.2%
Asuncion | San Vicente-Butay | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0%
Asuncion | San Vicente-Butay | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
Asuncion | San Vicente-Butay | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started: | 2020-01-02
Asuncion | San Vicente-Butay | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 013 - San Vicente - Butay |  | GENERAL FUND CY 2020 | Maintenance | 7.52 | km | CBRMC | Project Cost: | 235446.12 | Target Completion Date: |  | Program: | 235446.12 | Planned: |  | No. of Persons: |  | Purchase Request # 19125312 (On process)
Asuncion | San Vicente-Butay | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 235446.12 | Revised: |  | No. of Man-days:
Asuncion | San Vicente-Butay | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Asuncion | San Vicente-Butay | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Asuncion | San Vicente-Butay | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: |  | Date completed:
Asuncion | San Vicente-Butay | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started:
kapalong | Doña Andrea-Capungagan | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 014 - Jct. Highway Doña Andrea - Capungagan |  | GENERAL FUND CY 2020 | Maintenance | 8.7 | km | MBA | Project Cost: | 675845.5865 | Target Completion Date: | 2020-12-31 23:59 | Program: | 675845.5865 | Planned: | 14.87% | No. of Persons: | 17 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020)
kapalong | Doña Andrea-Capungagan | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 675845.5865 | Revised: |  | No. of Man-days: | 374
kapalong | Doña Andrea-Capungagan | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 75289.1983 | Actual: | 14.87%
kapalong | Doña Andrea-Capungagan | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0%
kapalong | Doña Andrea-Capungagan | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
kapalong | Doña Andrea-Capungagan | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started: | 2020-01-02
kapalong | Doña Andrea-Capungagan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 014 - Jct. Highway Doña Andrea - Capungagan |  | GENERAL FUND CY 2020 | Maintenance | 8.7 | km | CBRMC | Project Cost: | 299016.5724 | Target Completion Date: |  | Program: | 299016.5724 | Planned: |  | No. of Persons: |  | Purchase Request # 19125313 (On process)
kapalong | Doña Andrea-Capungagan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 299016.5724 | Revised: |  | No. of Man-days:
kapalong | Doña Andrea-Capungagan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
kapalong | Doña Andrea-Capungagan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
kapalong | Doña Andrea-Capungagan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: |  | Date completed:
kapalong | Doña Andrea-Capungagan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started:
kapalong | Pamacaun-Lasang-banate | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 015 - Pamacaun - Lasang - Banate |  | GENERAL FUND CY 2020 | Maintenance | 4.11 | km | MBA | Project Cost: | 180747.1933 | Target Completion Date: | 2020-12-31 23:59 | Program: | 180747.1933 | Planned: | 8.6% | No. of Persons: | 17 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020)
kapalong | Pamacaun-Lasang-banate | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 180747.1933 | Revised: |  | No. of Man-days: | 374
kapalong | Pamacaun-Lasang-banate | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 15544.2586 | Actual: | 8.6%
kapalong | Pamacaun-Lasang-banate | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0%
kapalong | Pamacaun-Lasang-banate | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
kapalong | Pamacaun-Lasang-banate | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started: | 2020-01-02
kapalong | Pamacaun-Lasang-banate | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 015 - Pamacaun - Lasang - Banate |  | GENERAL FUND CY 2020 | Maintenance | 4.11 | km | CBRMC | Project Cost: | 129495.366 | Target Completion Date: |  | Program: | 129495.366 | Planned: |  | No. of Persons: |  | Purchase Request # 19125314 (On process)
kapalong | Pamacaun-Lasang-banate | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 129495.366 | Revised: |  | No. of Man-days:
kapalong | Pamacaun-Lasang-banate | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
kapalong | Pamacaun-Lasang-banate | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
kapalong | Pamacaun-Lasang-banate | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: |  | Date completed:
kapalong | Pamacaun-Lasang-banate | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started:
kapalong | Semong-Palma Gil | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 018 - Semong - Palma Gil |  | GENERAL FUND CY 2020 | Maintenance | 2.73 | km | MBA | Project Cost: | 276301.31 | Target Completion Date: | 2020-12-31 23:59 | Program: | 276301.31 | Planned: | 50.35% | No. of Persons: | 14 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020)
kapalong | Semong-Palma Gil | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 276301.31 | Revised: |  | No. of Man-days: | 210
kapalong | Semong-Palma Gil | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 139117.7096 | Actual: | 50.35%
kapalong | Semong-Palma Gil | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0%
kapalong | Semong-Palma Gil | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
kapalong | Semong-Palma Gil | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started: | 2020-01-02
kapalong | Semong-Palma Gil | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 018 - Semong - Palma Gil |  | GENERAL FUND CY 2020 | Maintenance | 2.73 | km | CBRMC | Project Cost: | 77697.2196 | Target Completion Date: |  | Program: | 77697.2196 | Planned: |  | No. of Persons: |  | Purchase Request # 19125315 (On process)
kapalong | Semong-Palma Gil | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 77697.2196 | Revised: |  | No. of Man-days:
kapalong | Semong-Palma Gil | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
kapalong | Semong-Palma Gil | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
kapalong | Semong-Palma Gil | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: |  | Date completed:
kapalong | Semong-Palma Gil | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started:
Talaingod | Daligdigon-Dagohoy | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 020 - Daligdigon-Dagohoy |  | GENERAL FUND CY 2020 | Maintenance | 3.34 | km | MBA | Project Cost: | 161826.4 | Target Completion Date: | 2020-12-31 23:59 | Program: | 161826.4 | Planned: | 51.55% | No. of Persons: | 14 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020)
Talaingod | Daligdigon-Dagohoy | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 161826.4 | Revised: |  | No. of Man-days: | 210
Talaingod | Daligdigon-Dagohoy | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 83421.5092 | Actual: | 51.55%
Talaingod | Daligdigon-Dagohoy | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0%
Talaingod | Daligdigon-Dagohoy | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
Talaingod | Daligdigon-Dagohoy | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started: | 2020-01-02
Talaingod | Daligdigon-Dagohoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 020 - Daligdigon-Dagohoy |  | GENERAL FUND CY 2020 | Maintenance | 3.34 | km | CBRMC | Project Cost: | 77697.2196 | Target Completion Date: |  | Program: | 77697.2196 | Planned: |  | No. of Persons: |  | Purchase Request # 19125315 (On process)
Talaingod | Daligdigon-Dagohoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 77697.2196 | Revised: |  | No. of Man-days:
Talaingod | Daligdigon-Dagohoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Talaingod | Daligdigon-Dagohoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Talaingod | Daligdigon-Dagohoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: |  | Date completed:
Talaingod | Daligdigon-Dagohoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started:
Talaingod | Angelo-Dahgohoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 021 - Angelo - Dagohoy |  | GENERAL FUND CY 2020 | Maintenance | 2.19 | km | MBA | Project Cost: | 67286.09 | Target Completion Date: | 2020-12-31 23:59 | Program: | 67286.09 | Planned: | 21.85% | No. of Persons: | 14 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020)
Talaingod | Angelo-Dahgohoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 67286.09 | Revised: |  | No. of Man-days: | 210
Talaingod | Angelo-Dahgohoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 14702.0107 | Actual: | 21.85%
Talaingod | Angelo-Dahgohoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0%
Talaingod | Angelo-Dahgohoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
Talaingod | Angelo-Dahgohoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started: | 2020-01-02
Talaingod | Angelo-Dahgohoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 021 - Angelo - Dagohoy |  | GENERAL FUND CY 2020 | Maintenance | 2.19 | km | CBRMC | Project Cost: | 40025.8404 | Target Completion Date: |  | Program: | 40025.8404 | Planned: |  | No. of Persons: |  | Purchase Request # 19125317 (On process)
Talaingod | Angelo-Dahgohoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 40025.8404 | Revised: |  | No. of Man-days:
Talaingod | Angelo-Dahgohoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Talaingod | Angelo-Dahgohoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Talaingod | Angelo-Dahgohoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: |  | Date completed:
Talaingod | Angelo-Dahgohoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started:
kapalong | Sampao-Mamacao | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 025 - Jct. Sampao - Bdry. Mamacao |  | GENERAL FUND CY 2020 | Maintenance | 4.98 | km | MBA | Project Cost: | 325083.1184 | Target Completion Date: | 2020-12-31 23:59 | Program: | 325083.1184 | Planned: | 14.71% | No. of Persons: | 17 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020)
kapalong | Sampao-Mamacao | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 325083.1184 | Revised: |  | No. of Man-days: | 374
kapalong | Sampao-Mamacao | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 47819.7267 | Actual: | 14.71%
kapalong | Sampao-Mamacao | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0%
kapalong | Sampao-Mamacao | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
kapalong | Sampao-Mamacao | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started: | 2020-01-02
kapalong | Sampao-Mamacao | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 025 - Jct. Sampao - Bdry. Mamacao |  | GENERAL FUND CY 2020 | Maintenance | 4.98 | km | CBRMC | Project Cost: | 178939.0512 | Target Completion Date: |  | Program: | 178939.0512 | Planned: |  | No. of Persons: |  | Purchase Request # 19125318 (On process)
kapalong | Sampao-Mamacao | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 178939.0512 | Revised: |  | No. of Man-days:
kapalong | Sampao-Mamacao | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
kapalong | Sampao-Mamacao | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
kapalong | Sampao-Mamacao | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: |  | Date completed:
kapalong | Sampao-Mamacao | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started:
kapalong | Luna-Mamacao | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 026 - Jct. Highway - Luna - Mamacao - Narra |  | GENERAL FUND CY 2020 | Maintenance | 9.17 | km | MBA | Project Cost: | 361826.1515 | Target Completion Date: | 2020-12-31 23:59 | Program: | 361826.1515 | Planned: | 20.12% | No. of Persons: | 17 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020)
kapalong | Luna-Mamacao | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 361826.1515 | Revised: |  | No. of Man-days: | 374
kapalong | Luna-Mamacao | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 22433.2214 | Actual: | 20.12%
kapalong | Luna-Mamacao | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0%
kapalong | Luna-Mamacao | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
kapalong | Luna-Mamacao | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started: | 2020-01-02
kapalong | Luna-Mamacao | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 026 - Jct. Highway - Luna - Mamacao - Narra |  | GENERAL FUND CY 2020 | Maintenance | 9.17 | km | CBRMC | Project Cost: | 393195.0204 | Target Completion Date: |  | Program: | 393195.0204 | Planned: |  | No. of Persons: |  | Purchase Request # 19125337 (On process)
kapalong | Luna-Mamacao | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 393195.0204 | Revised: |  | No. of Man-days:
kapalong | Luna-Mamacao | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
kapalong | Luna-Mamacao | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
kapalong | Luna-Mamacao | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: |  | Date completed:
kapalong | Luna-Mamacao | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started:
kapalong | Gabuyan-Katipunan | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 027 - Jct. Gabuyan - Katipunan - Bucana |  | GENERAL FUND CY 2020 | Maintenance | 5.89 | km | MBA | Project Cost: | 485762.7577 | Target Completion Date: | 2020-12-31 23:59 | Program: | 485762.7577 | Planned: | 7.86% | No. of Persons: | 17 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020)
kapalong | Gabuyan-Katipunan | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 485762.7577 | Revised: |  | No. of Man-days: | 374
kapalong | Gabuyan-Katipunan | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 38180.9528 | Actual: | 7.86%
kapalong | Gabuyan-Katipunan | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0%
kapalong | Gabuyan-Katipunan | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
kapalong | Gabuyan-Katipunan | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started: | 2020-01-02
kapalong | Gabuyan-Katipunan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 027 - Jct. Gabuyan - Katipunan - Bucana |  | GENERAL FUND CY 2020 | Maintenance | 5.89 | km | CBRMC | Project Cost: | 174230.1288 | Target Completion Date: |  | Program: | 174230.1288 | Planned: |  | No. of Persons: |  | Purchase Request # 19125338 (On process)
kapalong | Gabuyan-Katipunan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 174230.1288 | Revised: |  | No. of Man-days:
kapalong | Gabuyan-Katipunan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
kapalong | Gabuyan-Katipunan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
kapalong | Gabuyan-Katipunan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: |  | Date completed:
kapalong | Gabuyan-Katipunan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started:
kapalong | Capungagan-Mabuhay | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 028 - Capungagan - Mabuhay - Pandulian |  | GENERAL FUND CY 2020 | Maintenance | 5.57 | km | MBA | Project Cost: | 468741.4542 | Target Completion Date: | 2020-12-31 23:59 | Program: | 468741.4542 | Planned: | 5.14% | No. of Persons: | 17 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020)
kapalong | Capungagan-Mabuhay | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 468741.4542 | Revised: |  | No. of Man-days: | 374
kapalong | Capungagan-Mabuhay | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 24093.3107 | Actual: | 5.14%
kapalong | Capungagan-Mabuhay | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0%
kapalong | Capungagan-Mabuhay | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
kapalong | Capungagan-Mabuhay | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started: | 2020-01-02
kapalong | Capungagan-Mabuhay | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 028 - Capungagan - Mabuhay - Pandulian |  | GENERAL FUND CY 2020 | Maintenance | 5.57 | km | CBRMC | Project Cost: | 155394.4392 | Target Completion Date: |  | Program: | 155394.4392 | Planned: |  | No. of Persons: |  | Purchase Request # 19125339 (On process)
kapalong | Capungagan-Mabuhay | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 155394.4392 | Revised: |  | No. of Man-days:
kapalong | Capungagan-Mabuhay | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
kapalong | Capungagan-Mabuhay | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
kapalong | Capungagan-Mabuhay | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: |  | Date completed:
kapalong | Capungagan-Mabuhay | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started:
San Isidro | Kipalili-New Loon | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 034 - Km. 15, Kipalili - New Loon |  | GENERAL FUND CY 2020 | Maintenance | 6.93 | km | MBA | Project Cost: | 490709.8742 | Target Completion Date: | 2020-12-31 23:59 | Program: | 490709.8742 | Planned: | 18.2% | No. of Persons: | 17 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020)
San Isidro | Kipalili-New Loon | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 490709.8742 | Revised: |  | No. of Man-days: | 374
San Isidro | Kipalili-New Loon | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 66393.046 | Actual: | 18.2%
San Isidro | Kipalili-New Loon | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0%
San Isidro | Kipalili-New Loon | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
San Isidro | Kipalili-New Loon | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started: | 2020-01-02
San Isidro | Kipalili-New Loon | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 034 - Km. 15, Kipalili - New Loon |  | GENERAL FUND CY 2020 | Maintenance | 6.93 | km | CBRMC | Project Cost: | 296662.1112 | Target Completion Date: |  | Program: | 296662.1112 | Planned: |  | No. of Persons: |  | Purchase Request # 19125340 (On process)
San Isidro | Kipalili-New Loon | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 296662.1112 | Revised: |  | No. of Man-days:
San Isidro | Kipalili-New Loon | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
San Isidro | Kipalili-New Loon | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
San Isidro | Kipalili-New Loon | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: |  | Date completed:
San Isidro | Kipalili-New Loon | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started:
San Isidro | Suaon-Libuton | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 035 - Jct. Suaon - Libuton |  | GENERAL FUND CY 2020 | Maintenance | 7.26 | km | MBA | Project Cost: | 60919.7962 | Target Completion Date: | 2020-12-31 23:59 | Program: | 60919.7962 | Planned: | 7.12% | No. of Persons: | 17 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020)
San Isidro | Suaon-Libuton | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 60919.7962 | Revised: |  | No. of Man-days: | 374
San Isidro | Suaon-Libuton | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: |  | Actual: | 7.12%
San Isidro | Suaon-Libuton | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0%
San Isidro | Suaon-Libuton | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
San Isidro | Suaon-Libuton | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started: | 2020-01-02
San Isidro | Suaon-Libuton | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 035 - Jct. Suaon - Libuton |  | GENERAL FUND CY 2020 | Maintenance | 7.26 | km | CBRMC | Project Cost: | 96532.9092 | Target Completion Date: |  | Program: | 96532.9092 | Planned: |  | No. of Persons: |  | Purchase Request # 19125341 (On process)
San Isidro | Suaon-Libuton | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 96532.9092 | Revised: |  | No. of Man-days:
San Isidro | Suaon-Libuton | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
San Isidro | Suaon-Libuton | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
San Isidro | Suaon-Libuton | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: |  | Date completed:
San Isidro | Suaon-Libuton | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started:
San Isidro | Monte Dujali-Gupitan | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 037 - Monte Dujali - Gupitan |  | GENERAL FUND CY 2020 | Maintenance | 4.58 | km | MBA | Project Cost: | 224727.1648 | Target Completion Date: | 2020-12-31 23:59 | Program: | 224727.1648 | Planned: | 11.08% | No. of Persons: | 17 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020)
San Isidro | Monte Dujali-Gupitan | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 224727.1648 | Revised: |  | No. of Man-days: | 374
San Isidro | Monte Dujali-Gupitan | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 24899.7699 | Actual: | 11.08%
San Isidro | Monte Dujali-Gupitan | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0%
San Isidro | Monte Dujali-Gupitan | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
San Isidro | Monte Dujali-Gupitan | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started: | 2020-01-02
San Isidro | Monte Dujali-Gupitan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 037 - Monte Dujali - Gupitan |  | GENERAL FUND CY 2020 | Maintenance | 4.58 | km | CBRMC | Project Cost: | 134204.2884 | Target Completion Date: |  | Program: | 134204.2884 | Planned: |  | No. of Persons: |  | Purchase Request # 19125342 (On process)
San Isidro | Monte Dujali-Gupitan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 134204.2884 | Revised: |  | No. of Man-days:
San Isidro | Monte Dujali-Gupitan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
San Isidro | Monte Dujali-Gupitan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
San Isidro | Monte Dujali-Gupitan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: |  | Date completed:
San Isidro | Monte Dujali-Gupitan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started:
San Isidro | Sawata-Mamangan-Pinamuno | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 041 - Sawata - Mamangan - Pinamuno |  | GENERAL FUND CY 2020 | Maintenance | 14.48 | km | MBA | Project Cost: | 1636481.63 | Target Completion Date: | 2021-02-01 23:59 | Program: | 1636481.63 | Planned: | 37.11% | No. of Persons: | 14 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020)
San Isidro | Sawata-Mamangan-Pinamuno | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-02-28 23:59 | Allotment: | 1636481.63 | Revised: |  | No. of Man-days: | 210
San Isidro | Sawata-Mamangan-Pinamuno | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 607298.3329 | Actual: | 37.11%
San Isidro | Sawata-Mamangan-Pinamuno | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0%
San Isidro | Sawata-Mamangan-Pinamuno | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
San Isidro | Sawata-Mamangan-Pinamuno | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started: | 2020-02-03
San Isidro | Sawata-Mamangan-Pinamuno | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 041 - Sawata - Mamangan - Pinamuno |  | GENERAL FUND CY 2020 | Maintenance | 14.48 | km | CBRMC | Project Cost: | 522690.3864 | Target Completion Date: |  | Program: | 522690.3864 | Planned: |  | No. of Persons: |  | Purchase Request # 19125343 (On process)
San Isidro | Sawata-Mamangan-Pinamuno | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 522690.3864 | Revised: |  | No. of Man-days:
San Isidro | Sawata-Mamangan-Pinamuno | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
San Isidro | Sawata-Mamangan-Pinamuno | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
San Isidro | Sawata-Mamangan-Pinamuno | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: |  | Date completed:
San Isidro | Sawata-Mamangan-Pinamuno | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started:
San Isidro | Igangon-Sawata | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 042 - Igangon - Sawata |  | GENERAL FUND CY 2020 | Maintenance | 9.66 | km | MBA | Project Cost: | 111771.1255 | Target Completion Date: | 2020-12-31 23:59 | Program: | 111771.1255 | Planned: | 8.74% | No. of Persons: | 17 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020)
San Isidro | Igangon-Sawata | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 111771.1255 | Revised: |  | No. of Man-days: | 374
San Isidro | Igangon-Sawata | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 9768.7964 | Actual: | 8.74%
San Isidro | Igangon-Sawata | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0%
San Isidro | Igangon-Sawata | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
San Isidro | Igangon-Sawata | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started: | 2020-01-02
San Isidro | Igangon-Sawata | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 042 - Igangon - Sawata |  | GENERAL FUND CY 2020 | Maintenance | 9.66 | km | CBRMC | Project Cost: | 202483.6632 | Target Completion Date: |  | Program: | 202483.6632 | Planned: |  | No. of Persons: |  | Purchase Request # 19125344 (On process)
San Isidro | Igangon-Sawata | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 202483.6632 | Revised: |  | No. of Man-days:
San Isidro | Igangon-Sawata | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
San Isidro | Igangon-Sawata | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
San Isidro | Igangon-Sawata | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: |  | Date completed:
San Isidro | Igangon-Sawata | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started:
San Isidro | Sawata | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 043 - Jct. Sawata - Bdry. Binasbas |  | GENERAL FUND CY 2020 | Maintenance | 0.46 | km | MBA | Project Cost: | 27720.5682 | Target Completion Date: | 2020-12-31 23:59 | Program: | 27720.5682 | Planned: | 10.3% | No. of Persons: | 17 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020)
San Isidro | Sawata | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 27720.5682 | Revised: |  | No. of Man-days: | 374
San Isidro | Sawata | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 2855.2185 | Actual: | 10.3%
San Isidro | Sawata | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0%
San Isidro | Sawata | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
San Isidro | Sawata | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started: | 2020-01-02
San Isidro | Sawata | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 043 - Jct. Sawata - Bdry. Binasbas |  | GENERAL FUND CY 2020 | Maintenance | 0.46 | km | CBRMC | Project Cost: | 18835.6896 | Target Completion Date: |  | Program: | 18835.6896 | Planned: |  | No. of Persons: |  | Purchase Request # 19125345 (On process)
San Isidro | Sawata | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 18835.6896 | Revised: |  | No. of Man-days:
San Isidro | Sawata | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
San Isidro | Sawata | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
San Isidro | Sawata | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: |  | Date completed:
San Isidro | Sawata | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started:
Asuncion | Buan | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 045 - Tagaytay - Buan |  | GENERAL FUND CY 2020 | Maintenance | 4.92 | km | MBA | Project Cost: | 378553.2244 | Target Completion Date: | 2020-12-31 23:59 | Program: | 378553.2244 | Planned: | 27.97% | No. of Persons: | 17 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020)
Asuncion | Buan | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 378553.2244 | Revised: |  | No. of Man-days: | 374
Asuncion | Buan | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 105881.3369 | Actual: | 27.97%
Asuncion | Buan | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0%
Asuncion | Buan | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
Asuncion | Buan | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started: | 2020-01-02
Asuncion | Buan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 045 - Tagaytay - Buan |  | GENERAL FUND CY 2020 | Maintenance | 4.92 | km | CBRMC | Project Cost: | 174230.1288 | Target Completion Date: |  | Program: | 174230.1288 | Planned: |  | No. of Persons: |  | Purchase Request # 19125346 (On process)
Asuncion | Buan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 174230.1288 | Revised: |  | No. of Man-days:
Asuncion | Buan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Asuncion | Buan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Asuncion | Buan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: |  | Date completed:
Asuncion | Buan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started:
New Corella | Limbann-Sto. Niño | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 049 - Limbaan - Sto. Niño |  | GENERAL FUND CY 2020 | Maintenance | 3.19 | km | MBA | Project Cost: | 322857.58 | Target Completion Date: | 2021-02-01 23:59 | Program: | 322857.58 | Planned: | 30.02% | No. of Persons: | 14 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020)
New Corella | Limbann-Sto. Niño | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-02-28 23:59 | Allotment: | 322857.58 | Revised: |  | No. of Man-days: | 210
New Corella | Limbann-Sto. Niño | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 96921.8455 | Actual: | 30.02%
New Corella | Limbann-Sto. Niño | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | Limbann-Sto. Niño | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
New Corella | Limbann-Sto. Niño | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started: | 2020-02-03
New Corella | Limbann-Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 049 - Limbaan - Sto. Niño |  | GENERAL FUND CY 2020 | Maintenance | 3.19 | km | CBRMC | Project Cost: | 127140.9048 | Target Completion Date: |  | Program: | 127140.9048 | Planned: |  | No. of Persons: |  | Purchase Request # 20010072 (On process)
New Corella | Limbann-Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 127140.9048 | Revised: |  | No. of Man-days:
New Corella | Limbann-Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
New Corella | Limbann-Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | Limbann-Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: |  | Date completed:
New Corella | Limbann-Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started:
New Corella | Monte Carlo | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 050 - Jct. Monte Carlo - Upper Cabaywa - Canatan |  | GENERAL FUND CY 2020 | Maintenance | 4.61 | km | MBA | Project Cost: | 285065.7818 | Target Completion Date: | 2020-12-31 23:59 | Program: | 285065.7818 | Planned: | 47.46% | No. of Persons: | 17 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020)
New Corella | Monte Carlo | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 285065.7818 | Revised: |  | No. of Man-days: | 374
New Corella | Monte Carlo | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 135292.2201 | Actual: | 47.46%
New Corella | Monte Carlo | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | Monte Carlo | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
New Corella | Monte Carlo | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started: | 2020-01-02
New Corella | Monte Carlo | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 050 - Jct. Monte Carlo - Upper Cabaywa - Canatan |  | GENERAL FUND CY 2020 | Maintenance | 4.61 | km | CBRMC | Project Cost: | 197774.7408 | Target Completion Date: |  | Program: | 197774.7408 | Planned: |  | No. of Persons: |  | Purchase Request # 20010074 (On process)
New Corella | Monte Carlo | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 197774.7408 | Revised: |  | No. of Man-days:
New Corella | Monte Carlo | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
New Corella | Monte Carlo | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | Monte Carlo | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: |  | Date completed:
New Corella | Monte Carlo | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started:
New Corella | Del Pilar | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 051 - Del Pilar - Jct. Silangan |  | GENERAL FUND CY 2020 | Maintenance | 4.17 | km | MBA | Project Cost: | 337766.1689 | Target Completion Date: | 2020-12-31 23:59 | Program: | 337766.1689 | Planned: | 5.54% | No. of Persons: |  | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020)
New Corella | Del Pilar | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 337766.1689 | Revised: |  | No. of Man-days:
New Corella | Del Pilar | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 18712.2458 | Actual: | 5.54%
New Corella | Del Pilar | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | Del Pilar | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
New Corella | Del Pilar | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started: | 2020-01-02
New Corella | Del Pilar | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 051 - Del Pilar - Jct. Silangan |  | GENERAL FUND CY 2020 | Maintenance | 4.17 | km | CBRMC | Project Cost: | 129495.366 | Target Completion Date: |  | Program: | 129495.366 | Planned: |  | No. of Persons: |  | Purchase Request # 20010093 (On process)
New Corella | Del Pilar | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 129495.366 | Revised: |  | No. of Man-days:
New Corella | Del Pilar | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
New Corella | Del Pilar | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | Del Pilar | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: |  | Date completed:
New Corella | Del Pilar | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started:
New Corella | New Sambog | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 052 - New Corella - New Sambog - Silangan |  | GENERAL FUND CY 2020 | Maintenance | 5.1 | km | MBA | Project Cost: | 371450.8414 | Target Completion Date: | 2020-12-31 23:59 | Program: | 371450.8414 | Planned: | 8.7% | No. of Persons: | 17 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020)
New Corella | New Sambog | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 371450.8414 | Revised: |  | No. of Man-days: | 374
New Corella | New Sambog | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 32316.2232 | Actual: | 8.7%
New Corella | New Sambog | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | New Sambog | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
New Corella | New Sambog | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started: | 2020-01-02
New Corella | New Sambog | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 052 - New Corella - New Sambog - Silangan |  | GENERAL FUND CY 2020 | Maintenance | 5.1 | km | CBRMC | Project Cost: | 148331.0556 | Target Completion Date: |  | Program: | 148331.0556 | Planned: |  | No. of Persons: |  | Purchase Request # 20010095 (On process)
New Corella | New Sambog | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 148331.0556 | Revised: |  | No. of Man-days:
New Corella | New Sambog | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
New Corella | New Sambog | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | New Sambog | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: |  | Date completed:
New Corella | New Sambog | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started:
New Corella | Poblacion | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 053 - Pob. New Corella - Prk. 10 Pob. |  | GENERAL FUND CY 2020 | Maintenance | 1.3 | km | MBA | Project Cost: | 28149.3653 | Target Completion Date: | 2020-12-31 23:59 | Program: | 28149.3653 | Planned: | 13.38% | No. of Persons: | 17 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020)
New Corella | Poblacion | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 28149.3653 | Revised: |  | No. of Man-days: | 374
New Corella | Poblacion | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 3766.3851 | Actual: | 13.38%
New Corella | Poblacion | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | Poblacion | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
New Corella | Poblacion | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started: | 2020-01-02
New Corella | Poblacion | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 053 - Pob. New Corella - Prk. 10 Pob. |  | GENERAL FUND CY 2020 | Maintenance | 1.3 | km | CBRMC | Project Cost: | 21190.1508 | Target Completion Date: |  | Program: | 21190.1508 | Planned: |  | No. of Persons: |  | Purchase Request # 20010155 (On process)
New Corella | Poblacion | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 21190.1508 | Revised: |  | No. of Man-days:
New Corella | Poblacion | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
New Corella | Poblacion | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | Poblacion | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: |  | Date completed:
New Corella | Poblacion | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started:
New Corella | New Sambog | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 054 - Prk. 7 Pob. - Jct. New Sambog |  | GENERAL FUND CY 2020 | Maintenance | 2.54 | km | MBA | Project Cost: | 171600.7916 | Target Completion Date: | 2020-12-31 23:59 | Program: | 171600.7916 | Planned: | 6.92% | No. of Persons: | 17 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020)
New Corella | New Sambog | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 171600.7916 | Revised: |  | No. of Man-days: | 374
New Corella | New Sambog | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 11874.7748 | Actual: | 6.92%
New Corella | New Sambog | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | New Sambog | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
New Corella | New Sambog | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started: | 2020-01-02
New Corella | New Sambog | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 054 - Prk. 7 Pob. - Jct. New Sambog |  | GENERAL FUND CY 2020 | Maintenance | 2.54 | km | CBRMC | Project Cost: | 113014.1376 | Target Completion Date: |  | Program: | 113014.1376 | Planned: |  | No. of Persons: |  | Purchase Request # 20010158 (On process)
New Corella | New Sambog | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 113014.1376 | Revised: |  | No. of Man-days:
New Corella | New Sambog | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
New Corella | New Sambog | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | New Sambog | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: |  | Date completed:
New Corella | New Sambog | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started:
New Corella | Sta. Fe-Del Monte | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 056 - Sta. Fe - Del Monte |  | GENERAL FUND CY 2020 | Maintenance | 3.34 | km | MBA | Project Cost: | 93676.7241 | Target Completion Date: | 2020-12-31 23:59 | Program: | 93676.7241 | Planned: | 11.64% | No. of Persons: | 17 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020)
New Corella | Sta. Fe-Del Monte | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 93676.7241 | Revised: |  | No. of Man-days: | 374
New Corella | Sta. Fe-Del Monte | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 10903.9707 | Actual: | 11.64%
New Corella | Sta. Fe-Del Monte | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | Sta. Fe-Del Monte | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
New Corella | Sta. Fe-Del Monte | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started: | 2020-01-02
New Corella | Sta. Fe-Del Monte | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 056 - Sta. Fe - Del Monte |  | GENERAL FUND CY 2020 | Maintenance | 3.34 | km | CBRMC | Project Cost: | 75342.7584 | Target Completion Date: |  | Program: | 75342.7584 | Planned: |  | No. of Persons: |  | Purchase Request # 20010160 (On process)
New Corella | Sta. Fe-Del Monte | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 75342.7584 | Revised: |  | No. of Man-days:
New Corella | Sta. Fe-Del Monte | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
New Corella | Sta. Fe-Del Monte | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | Sta. Fe-Del Monte | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: |  | Date completed:
New Corella | Sta. Fe-Del Monte | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started:
New Corella | New Bohol | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 058 - New Corella - New Bohol |  | GENERAL FUND CY 2020 | Maintenance | 11.54 | km | MBA | Project Cost: | 300034.9027 | Target Completion Date: | 2020-12-31 23:59 | Program: | 300034.9027 | Planned: | 17.21% | No. of Persons: | 17 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020)
New Corella | New Bohol | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 300034.9027 | Revised: |  | No. of Man-days: | 374
New Corella | New Bohol | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 51636.0068 | Actual: | 17.21%
New Corella | New Bohol | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | New Bohol | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
New Corella | New Bohol | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started: | 2020-01-02
New Corella | New Bohol | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 058 - New Corella - New Bohol |  | GENERAL FUND CY 2020 | Maintenance | 11.54 | km | CBRMC | Project Cost: | 221319.3528 | Target Completion Date: |  | Program: | 221319.3528 | Planned: |  | No. of Persons: |  | Purchase Request # 20010221 (On process)
New Corella | New Bohol | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 221319.3528 | Revised: |  | No. of Man-days:
New Corella | New Bohol | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
New Corella | New Bohol | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | New Bohol | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: |  | Date completed:
New Corella | New Bohol | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started:
New Corella | Carcor | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 059 - Jct. Carcor - Prk. 9 Bagsak |  | GENERAL FUND CY 2020 | Maintenance | 2.5 | km | MBA | Project Cost: | 161961.791 | Target Completion Date: | 2020-12-31 23:59 | Program: | 161961.791 | Planned: | 15.82% | No. of Persons: | 17 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020)
New Corella | Carcor | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 161961.791 | Revised: |  | No. of Man-days: | 374
New Corella | Carcor | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 25622.3553 | Actual: | 15.82%
New Corella | Carcor | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | Carcor | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
New Corella | Carcor | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started: | 2020-01-02
New Corella | Carcor | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 059 - Jct. Carcor - Prk. 9 Bagsak |  | GENERAL FUND CY 2020 | Maintenance | 2.5 | km | CBRMC | Project Cost: | 72988.2972 | Target Completion Date: |  | Program: | 72988.2972 | Planned: |  | No. of Persons: |  | Purchase Request # 20010223 (On process)
New Corella | Carcor | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 72988.2972 | Revised: |  | No. of Man-days:
New Corella | Carcor | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
New Corella | Carcor | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | Carcor | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: |  | Date completed:
New Corella | Carcor | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started:
New Corella | Carcor | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 060 - Carcor - Jct. Kauswagan |  | GENERAL FUND CY 2020 | Maintenance | 4.32 | km | MBA | Project Cost: | 304751.9237 | Target Completion Date: | 2020-12-31 23:59 | Program: | 304751.9237 | Planned: | 31.32% | No. of Persons: | 17 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020)
New Corella | Carcor | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 304751.9237 | Revised: |  | No. of Man-days: | 374
New Corella | Carcor | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 95448.3025 | Actual: | 31.32%
New Corella | Carcor | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | Carcor | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
New Corella | Carcor | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started: | 2020-01-02
New Corella | Carcor | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 060 - Carcor - Jct. Kauswagan |  | GENERAL FUND CY 2020 | Maintenance | 4.32 | km | CBRMC | Project Cost: | 101241.8316 | Target Completion Date: |  | Program: | 101241.8316 | Planned: |  | No. of Persons: |  | Purchase Request # 20010262 (On process)
New Corella | Carcor | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 101241.8316 | Revised: |  | No. of Man-days:
New Corella | Carcor | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
New Corella | Carcor | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | Carcor | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: |  | Date completed:
New Corella | Carcor | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started:
New Corella | Del Pilar | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 061 - Del Pilar - Prk. 9 Bagsak - San Jose |  | GENERAL FUND CY 2020 | Maintenance |  | km | MBA | Project Cost: | 505304.26 | Target Completion Date: | 2021-01-14 23:59 | Program: | 505304.26 | Planned: | 49.18% | No. of Persons: | 14 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020)
New Corella | Del Pilar | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-02-10 23:59 | Allotment: | 505304.26 | Revised: |  | No. of Man-days: | 210
New Corella | Del Pilar | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 248508.6351 | Actual: | 49.18%
New Corella | Del Pilar | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | Del Pilar | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
New Corella | Del Pilar | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started: | 2020-01-16
New Corella | Del Pilar | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 061 - Del Pilar - Prk. 9 Bagsak - San Jose |  | GENERAL FUND CY 2020 | Maintenance |  | km | CBRMC | Project Cost: | 251927.3484 | Target Completion Date: |  | Program: | 251927.3484 | Planned: |  | No. of Persons: |  | Purchase Request # 20010264 (On process)
New Corella | Del Pilar | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 251927.3484 | Revised: |  | No. of Man-days:
New Corella | Del Pilar | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
New Corella | Del Pilar | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | Del Pilar | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: |  | Date completed:
New Corella | Del Pilar | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started:
New Corella | Del Pilar | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 062 - Del Pilar - El Unido |  | GENERAL FUND CY 2020 | Maintenance | 1.32 | km | MBA | Project Cost: | 84027.808 | Target Completion Date: | 2020-12-31 23:59 | Program: | 84027.808 | Planned: | 10.78% | No. of Persons: | 17 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020)
New Corella | Del Pilar | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 84027.808 | Revised: |  | No. of Man-days: | 374
New Corella | Del Pilar | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 9058.1977 | Actual: | 10.78%
New Corella | Del Pilar | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | Del Pilar | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
New Corella | Del Pilar | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started: | 2020-01-02
New Corella | Del Pilar | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 062 - Del Pilar - El Unido |  | GENERAL FUND CY 2020 | Maintenance | 1.32 | km | CBRMC | Project Cost: | 40025.8404 | Target Completion Date: |  | Program: | 40025.8404 | Planned: |  | No. of Persons: |  | Purchase Request # 20010265 (On process)
New Corella | Del Pilar | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 40025.8404 | Revised: |  | No. of Man-days:
New Corella | Del Pilar | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
New Corella | Del Pilar | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | Del Pilar | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: |  | Date completed:
New Corella | Del Pilar | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started:
New Corella | Del Pilar | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 063 - San Juan - New Talisay |  | GENERAL FUND CY 2020 | Maintenance | 5.13 | km | MBA | Project Cost: | 442982.6933 | Target Completion Date: | 2020-12-31 23:59 | Program: | 442982.6933 | Planned: | 13.42% | No. of Persons: | 17 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020)
New Corella | Del Pilar | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 442982.6933 | Revised: |  | No. of Man-days: | 374
New Corella | Del Pilar | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 59448.2774 | Actual: | 13.42%
New Corella | Del Pilar | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | Del Pilar | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
New Corella | Del Pilar | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started: | 2020-01-02
New Corella | Del Pilar | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 063 - San Juan - New Talisay |  | GENERAL FUND CY 2020 | Maintenance | 5.13 | km | CBRMC | Project Cost: | 131849.8272 | Target Completion Date: |  | Program: | 131849.8272 | Planned: |  | No. of Persons: |  | Purchase Request # 20010267 (On process)
New Corella | Del Pilar | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 131849.8272 | Revised: |  | No. of Man-days:
New Corella | Del Pilar | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
New Corella | Del Pilar | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | Del Pilar | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: |  | Date completed:
New Corella | Del Pilar | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started:
New Corella | Del Pilar | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 064 - San Juan - Kauswagan - New Cortez |  | GENERAL FUND CY 2020 | Maintenance | 3.22 | km | MBA | Project Cost: | 128969.53 | Target Completion Date: | 2021-01-14 23:59 | Program: | 128969.53 | Planned: | 41.14% | No. of Persons: | 14 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020)
New Corella | Del Pilar | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-02-10 23:59 | Allotment: | 128969.53 | Revised: |  | No. of Man-days: | 210
New Corella | Del Pilar | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 53058.0646 | Actual: | 41.14%
New Corella | Del Pilar | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage:
New Corella | Del Pilar | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
New Corella | Del Pilar | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started: | 2020-01-16
New Corella | Del Pilar | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 064 - San Juan - Kauswagan - New Cortez |  | GENERAL FUND CY 2020 | Maintenance | 3.22 | km | CBRMC | Project Cost: | 68279.3748 | Target Completion Date: |  | Program: | 68279.3748 | Planned: |  | No. of Persons: |  | Procurement on process
New Corella | Del Pilar | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 68279.3748 | Revised: |  | No. of Man-days:
New Corella | Del Pilar | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
New Corella | Del Pilar | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | Del Pilar | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: |  | Date completed:
New Corella | Del Pilar | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started:
New Corella | New Bohol | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 065 - New Bohol - Jct. El Unido |  | GENERAL FUND CY 2020 | Maintenance | 2.12 | km | MBA | Project Cost: | 177260.81 | Target Completion Date: | 2021-01-14 23:59 | Program: | 177260.81 | Planned: |  | No. of Persons: | 14 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020)
New Corella | New Bohol | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-02-10 23:59 | Allotment: | 177260.81 | Revised: |  | No. of Man-days: | 210
New Corella | New Bohol | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 50005.2745 | Actual: | 28.21%
New Corella | New Bohol | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | #VALUE!
New Corella | New Bohol | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
New Corella | New Bohol | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started: | 2020-01-16
New Corella | New Bohol | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 065 - New Bohol - Jct. El Unido |  | GENERAL FUND CY 2020 | Maintenance | 2.12 | km | CBRMC | Project Cost: | 65924.9136 | Target Completion Date: |  | Program: | 65924.9136 | Planned: |  | No. of Persons: |  | Purchase Request # 20010275 (On process)
New Corella | New Bohol | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 65924.9136 | Revised: |  | No. of Man-days:
New Corella | New Bohol | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
New Corella | New Bohol | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | New Bohol | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: |  | Date completed:
New Corella | New Bohol | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started:
New Corella | Mesaoy | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 066 - New Corella - El Unido - Jct. Mesaoy |  | GENERAL FUND CY 2020 | Maintenance | 8.63 | km | MBA | Project Cost: | 792432.45 | Target Completion Date: | 2021-01-14 23:59 | Program: | 792432.45 | Planned: | 53.98% | No. of Persons: | 14 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020)
New Corella | Mesaoy | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-02-10 23:59 | Allotment: | 792432.45 | Revised: |  | No. of Man-days: | 210
New Corella | Mesaoy | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 427755.0365 | Actual: | 53.98%
New Corella | Mesaoy | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | Mesaoy | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
New Corella | Mesaoy | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started: | 2020-01-16
New Corella | Mesaoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 066 - New Corella - El Unido - Jct. Mesaoy |  | GENERAL FUND CY 2020 | Maintenance | 8.63 | km | CBRMC | Project Cost: | 249572.8872 | Target Completion Date: |  | Program: | 249572.8872 | Planned: |  | No. of Persons: |  | Purchase Request # 20010291 (On process)
New Corella | Mesaoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 249572.8872 | Revised: |  | No. of Man-days:
New Corella | Mesaoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
New Corella | Mesaoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | Mesaoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: |  | Date completed:
New Corella | Mesaoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started:
New Corella | Mesaoy | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 067 - Mesaoy - Dasing |  | GENERAL FUND CY 2020 | Maintenance | 1.39 | km | MBA | Project Cost: | 130632.25 | Target Completion Date: | 2021-01-14 23:59 | Program: | 130632.25 | Planned: | 48.79% | No. of Persons: | 14 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020)
New Corella | Mesaoy | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-02-10 23:59 | Allotment: | 130632.25 | Revised: |  | No. of Man-days: | 210
New Corella | Mesaoy | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 63735.4748 | Actual: | 48.79%
New Corella | Mesaoy | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | Mesaoy | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
New Corella | Mesaoy | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started: | 2020-01-16
New Corella | Mesaoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 067 - Mesaoy - Dasing |  | GENERAL FUND CY 2020 | Maintenance | 1.39 | km | CBRMC | Project Cost: | 54152.6076 | Target Completion Date: |  | Program: | 54152.6076 | Planned: |  | No. of Persons: |  | Purchase Request # 20010294 (On process)
New Corella | Mesaoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 54152.6076 | Revised: |  | No. of Man-days:
New Corella | Mesaoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
New Corella | Mesaoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | Mesaoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: |  | Date completed:
New Corella | Mesaoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started:
New Corella | Del Pilar | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 068 - Jct. San Juan - Jct. Mesaoy |  | GENERAL FUND CY 2020 | Maintenance | 1.82 | km | MBA | Project Cost: | 135657.3072 | Target Completion Date: | 2020-12-31 23:59 | Program: | 135657.3072 | Planned: | 7.32% | No. of Persons: | 17 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020)
New Corella | Del Pilar | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 135657.3072 | Revised: |  | No. of Man-days: | 374
New Corella | Del Pilar | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 9930.1149 | Actual: | 7.32%
New Corella | Del Pilar | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | Del Pilar | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
New Corella | Del Pilar | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started: | 2020-01-02
New Corella | Del Pilar | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 068 - Jct. San Juan - Jct. Mesaoy |  | GENERAL FUND CY 2020 | Maintenance | 1.82 | km | CBRMC | Project Cost: | 68279.3748 | Target Completion Date: |  | Program: | 68279.3748 | Planned: |  | No. of Persons: |  | Purchase Request # 20010294 (On process)
New Corella | Del Pilar | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 68279.3748 | Revised: |  | No. of Man-days:
New Corella | Del Pilar | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
New Corella | Del Pilar | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | Del Pilar | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: |  | Date completed:
New Corella | Del Pilar | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started:
New Corella | Mesaoy-New Bohol | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 070 - Mesaoy - New Bohol |  | GENERAL FUND CY 2020 | Maintenance | 5.36 | km | MBA | Project Cost: | 665667.84 | Target Completion Date: | 2021-01-14 23:59 | Program: | 665667.84 | Planned: | 41.99% | No. of Persons: | 14 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020)
New Corella | Mesaoy-New Bohol | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-02-10 23:59 | Allotment: | 665667.84 | Revised: |  | No. of Man-days: | 210
New Corella | Mesaoy-New Bohol | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 279513.926 | Actual: | 41.99%
New Corella | Mesaoy-New Bohol | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | Mesaoy-New Bohol | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
New Corella | Mesaoy-New Bohol | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started: | 2020-01-16
New Corella | Mesaoy-New Bohol | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 070 - Mesaoy - New Bohol |  | GENERAL FUND CY 2020 | Maintenance | 5.36 | km | CBRMC | Project Cost: | 261345.1932 | Target Completion Date: |  | Program: | 261345.1932 | Planned: |  | No. of Persons: |  | Purchase Request # 20010298 (On process)
New Corella | Mesaoy-New Bohol | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 261345.1932 | Revised: |  | No. of Man-days:
New Corella | Mesaoy-New Bohol | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
New Corella | Mesaoy-New Bohol | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | Mesaoy-New Bohol | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: |  | Date completed:
New Corella | Mesaoy-New Bohol | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started:
Asuncion | Napungas | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 147 - Prk. 1, Maunlom-Prk. 6 Maunlom Road |  | GENERAL FUND CY 2020 | Maintenance | 3.56 | km | MBA | Project Cost: | 115812.32 | Target Completion Date: | 2021-02-15 23:59 | Program: | 115812.32 | Planned: | 38.9% | No. of Persons: | 14 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020)
Asuncion | Napungas | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-03-14 23:59 | Allotment: | 115812.32 | Revised: |  | No. of Man-days: | 210
Asuncion | Napungas | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 45050.9925 | Actual: | 38.9%
Asuncion | Napungas | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0%
Asuncion | Napungas | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
Asuncion | Napungas | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started: | 2020-02-17
Asuncion | Napungas | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 147 - Prk. 1, Maunlom-Prk. 6 Maunlom Road |  | GENERAL FUND CY 2020 | Maintenance | 3.56 | km | CBRMC | Project Cost: | 65924.9136 | Target Completion Date: |  | Program: | 65924.9136 | Planned: |  | No. of Persons: |  | Purchase Request # 20010302 (On process)
Asuncion | Napungas | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 65924.9136 | Revised: |  | No. of Man-days:
Asuncion | Napungas | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Asuncion | Napungas | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Asuncion | Napungas | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: |  | Date completed:
Asuncion | Napungas | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started:
Asuncion | Binancian | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 149 - New Visayas - Binancian |  | GENERAL FUND CY 2020 | Maintenance | 7.77 | km | MBA | Project Cost: | 62394.7204 | Target Completion Date: | 2020-12-31 23:59 | Program: | 62394.7204 | Planned: | 3.47% | No. of Persons: | 17 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020)
Asuncion | Binancian | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 62394.7204 | Revised: |  | No. of Man-days: | 374
Asuncion | Binancian | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 2165.0968 | Actual: | 3.47%
Asuncion | Binancian | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0%
Asuncion | Binancian | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
Asuncion | Binancian | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started: | 2020-01-02
Asuncion | Binancian | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 149 - New Visayas - Binancian |  | GENERAL FUND CY 2020 | Maintenance | 7.77 | km | CBRMC | Project Cost: | 134204.2884 | Target Completion Date: |  | Program: | 134204.2884 | Planned: |  | No. of Persons: |  | Purchase Request # 20010305 (On process)
Asuncion | Binancian | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 134204.2884 | Revised: |  | No. of Man-days:
Asuncion | Binancian | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Asuncion | Binancian | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Asuncion | Binancian | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: |  | Date completed:
Asuncion | Binancian | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started:
San Isidro | Datu Balong-Mamalian | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 150 - Datu Balong - Prk. Mamalian |  | GENERAL FUND CY 2020 | Maintenance | 3.46 | km | MBA | Project Cost: | 45089.8864 | Target Completion Date: | 2020-12-31 23:59 | Program: | 45089.8864 | Planned: | 6.37% | No. of Persons: | 17 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020)
San Isidro | Datu Balong-Mamalian | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 45089.8864 | Revised: |  | No. of Man-days: | 374
San Isidro | Datu Balong-Mamalian | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 2872.2258 | Actual: | 6.37%
San Isidro | Datu Balong-Mamalian | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0%
San Isidro | Datu Balong-Mamalian | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | 2 | 2020-01-02 | Date completed:
San Isidro | Datu Balong-Mamalian | 1st Eng'g. Dist. | On-going | 2020-01-02 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started: | 2020-01-02
San Isidro | Datu Balong-Mamalian | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 150 - Datu Balong - Prk. Mamalian |  | GENERAL FUND CY 2020 | Maintenance | 3.46 | km | CBRMC | Project Cost: | 61215.9912 | Target Completion Date: |  | Program: | 61215.9912 | Planned: |  | No. of Persons: |  | Purchase Request # 20010306 (On process)
San Isidro | Datu Balong-Mamalian | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 61215.9912 | Revised: |  | No. of Man-days:
San Isidro | Datu Balong-Mamalian | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
San Isidro | Datu Balong-Mamalian | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
San Isidro | Datu Balong-Mamalian | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: |  | Date completed:
San Isidro | Datu Balong-Mamalian | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started:
Tagum City | Cuambogan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | RURAL ELECTRIFICATION PROJECT LS - P 5,000,000.00 | Rural Electrification at RAMADA Compound Purok Sto. Niño, Brgy. Cuambogan, Tagum City |  | 20% Development Fund CY 2020 | Electrification |  | km |  | Project Cost: | 1000000 | Target Completion Date: |  | Program: | 1000000 | Planned: |  | No. of Persons: |  | PO on process - Tagum Constrak
Tagum City | Cuambogan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | RURAL ELECTRIFICATION PROJECT LS - P 5,000,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 1000000 | Revised: |  | No. of Man-days:
Tagum City | Cuambogan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | RURAL ELECTRIFICATION PROJECT LS - P 5,000,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Tagum City | Cuambogan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | RURAL ELECTRIFICATION PROJECT LS - P 5,000,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Tagum City | Cuambogan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | RURAL ELECTRIFICATION PROJECT LS - P 5,000,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Tagum City | Cuambogan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | RURAL ELECTRIFICATION PROJECT LS - P 5,000,000.00 | [7 empty] | Date Started:
Asuncion | Camansa | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | RURAL ELECTRIFICATION PROJECT LS - P 5,000,000.00 | Rural Electrification at Lower Camansa, Prk.5 to 6 Lower, Brgy. Camansa, Asuncion |  | 20% Development Fund CY 2020 | Electrification |  | km |  | Project Cost: | 3000000 | Target Completion Date: |  | Program: | 3000000 | Planned: |  | No. of Persons: |  | PO on process - Tagum Constrak
Asuncion | Camansa | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | RURAL ELECTRIFICATION PROJECT LS - P 5,000,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 3000000 | Revised: |  | No. of Man-days:
Asuncion | Camansa | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | RURAL ELECTRIFICATION PROJECT LS - P 5,000,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Asuncion | Camansa | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | RURAL ELECTRIFICATION PROJECT LS - P 5,000,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Asuncion | Camansa | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | RURAL ELECTRIFICATION PROJECT LS - P 5,000,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Asuncion | Camansa | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | RURAL ELECTRIFICATION PROJECT LS - P 5,000,000.00 | [7 empty] | Date Started:
Asuncion | Doña Andrea | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | RURAL ELECTRIFICATION PROJECT LS - P 5,000,000.00 | Completion of Electrification at at Purok 10 and Purok 9, Phase 2, Brgy. Doña Andrea, Asuncion |  | 20% Development Fund CY 2020 | Electrification |  | km |  | Project Cost: | 1000000 | Target Completion Date: |  | Program: | 1000000 | Planned: |  | No. of Persons: |  | For preparation of POW and Plans
Asuncion | Doña Andrea | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | RURAL ELECTRIFICATION PROJECT LS - P 5,000,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 1000000 | Revised: |  | No. of Man-days:
Asuncion | Doña Andrea | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | RURAL ELECTRIFICATION PROJECT LS - P 5,000,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Asuncion | Doña Andrea | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | RURAL ELECTRIFICATION PROJECT LS - P 5,000,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Asuncion | Doña Andrea | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | RURAL ELECTRIFICATION PROJECT LS - P 5,000,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Asuncion | Doña Andrea | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | RURAL ELECTRIFICATION PROJECT LS - P 5,000,000.00 | [7 empty] | Date Started:
Asuncion | Sta. Felomina | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | ROAD ID 008 - Sta. Felomina - San Roque |  | 20% Development Fund CY 2020 | Road Rehabilitaion | 7.68 | km | Admin | Project Cost: | 2304000 | Target Completion Date: |  | Program: | 2304000 | Planned: |  | No. of Persons: |  | Post qualification on process
Asuncion | Sta. Felomina | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 2304000 | Revised: |  | No. of Man-days:
Asuncion | Sta. Felomina | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual:
Asuncion | Sta. Felomina | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Asuncion | Sta. Felomina | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Asuncion | Sta. Felomina | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Date Started:
Talaingod | Sto. Niño-Palma Gil | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | ROAD ID 019 - Sto. Niño - Palma Gil - Sitio Opao |  | 20% Development Fund CY 2020 | Road Rehabilitaion | 5.99 | km | Admin | Project Cost: | 1797000 | Target Completion Date: |  | Program: | 1797000 | Planned: |  | No. of Persons: |  | POW on process
Talaingod | Sto. Niño-Palma Gil | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 1797000 | Revised: |  | No. of Man-days:
Talaingod | Sto. Niño-Palma Gil | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual:
Talaingod | Sto. Niño-Palma Gil | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Talaingod | Sto. Niño-Palma Gil | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Talaingod | Sto. Niño-Palma Gil | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Date Started:
Talaingod | Daligdigon-Paiton | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | ROAD ID 023 - Sto. Niño - Daligdigon - Paiton |  | 20% Development Fund CY 2020 | Road Rehabilitaion | 11.6 | km | Admin | Project Cost: | 3480000 | Target Completion Date: |  | Program: | 3480000 | Planned: |  | No. of Persons: |  | POW on process
Talaingod | Daligdigon-Paiton | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 3480000 | Revised: |  | No. of Man-days:
Talaingod | Daligdigon-Paiton | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual:
Talaingod | Daligdigon-Paiton | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Talaingod | Daligdigon-Paiton | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Talaingod | Daligdigon-Paiton | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Date Started:
Talaingod | Paiton | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | ROAD ID 024 - Jct. Paiton - Mibolo |  | 20% Development Fund CY 2020 | Road Rehabilitaion | 23.9 | km | Admin | Project Cost: | 7170000 | Target Completion Date: |  | Program: | 7170000 | Planned: |  | No. of Persons: |  | POW on process
Talaingod | Paiton | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 7170000 | Revised: |  | No. of Man-days:
Talaingod | Paiton | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual:
Talaingod | Paiton | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Talaingod | Paiton | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Talaingod | Paiton | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Date Started:
Kapalong | Florida | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | ROAD ID 024 - Florida - Suaon - Jct. Gupitan |  | 20% Development Fund CY 2020 | Road Rehabilitaion | 15.57 | km | Admin | Project Cost: | 4671000 | Target Completion Date: |  | Program: | 4671000 | Planned: |  | No. of Persons: |  | PO on process - Royal Summit
Kapalong | Florida | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 4671000 | Revised: |  | No. of Man-days:
Kapalong | Florida | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual:
Kapalong | Florida | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Kapalong | Florida | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Kapalong | Florida | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Date Started:
San Isidro | Datu Balong | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | ROAD ID 040 - Datu Balong - Pinamuno |  | 20% Development Fund CY 2020 | Road Rehabilitaion | 2.74 | km | Admin | Project Cost: | 822000 | Target Completion Date: |  | Program: | 822000 | Planned: |  | No. of Persons: |  | POW on process
San Isidro | Datu Balong | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 822000 | Revised: |  | No. of Man-days:
San Isidro | Datu Balong | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual:
San Isidro | Datu Balong | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
San Isidro | Datu Balong | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
San Isidro | Datu Balong | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Date Started:
New Corella | Macgum | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | ROAD ID 048 - New Corella - Saug |  | 20% Development Fund CY 2020 | Road Rehabilitaion | 12.52 | km | Admin | Project Cost: | 20571000 | Target Completion Date: |  | Program: | 20571000 | Planned: |  | No. of Persons: |  | POW on process
New Corella | Macgum | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 20571000 | Revised: |  | No. of Man-days:
New Corella | Macgum | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual:
New Corella | Macgum | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | Macgum | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
New Corella | Macgum | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Date Started:
Asuncion | Canatan-Doña andrea | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | ROAD ID 074 - Jct. Highway Canatan - Doña Andrea |  | 20% Development Fund CY 2020 | Road Rehabilitaion | 4.34 | km | Admin | Project Cost: | 1302000 | Target Completion Date: |  | Program: | 1302000 | Planned: |  | No. of Persons: |  | POW on process
Asuncion | Canatan-Doña andrea | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 1302000 | Revised: |  | No. of Man-days:
Asuncion | Canatan-Doña andrea | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Asuncion | Canatan-Doña andrea | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Asuncion | Canatan-Doña andrea | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Asuncion | Canatan-Doña andrea | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Date Started:
Kapalong | Florida | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | ROAD ID 030 - Florida - New Boholano |  | 20% Development Fund CY 2020 | Road Rehabilitaion | 2.54 | km | Admin | Project Cost: | 762000 | Target Completion Date: |  | Program: | 762000 | Planned: |  | No. of Persons: |  | POW on process
Kapalong | Florida | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 762000 | Revised: |  | No. of Man-days:
Kapalong | Florida | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual:
Kapalong | Florida | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Kapalong | Florida | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Kapalong | Florida | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Date Started:
Asuncion | New Loon | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | ROAD ID 031 - Jct. New Boholano - New Loon |  | 20% Development Fund CY 2020 | Road Rehabilitaion | 4.77 | km | Admin | Project Cost: | 1431000 | Target Completion Date: |  | Program: | 1431000 | Planned: |  | No. of Persons: |  | POW on process
Asuncion | New Loon | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 1431000 | Revised: |  | No. of Man-days:
Asuncion | New Loon | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Asuncion | New Loon | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Asuncion | New Loon | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Asuncion | New Loon | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Date Started:
New Corella | Mesaoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | ROAD ID 069 - Mesaoy - Jct. Mahayahay |  | 20% Development Fund CY 2020 | Road Rehabilitaion | 4.6 | km | Admin | Project Cost: | 1380000 | Target Completion Date: |  | Program: | 1380000 | Planned: |  | No. of Persons: |  | POW on process
New Corella | Mesaoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 1380000 | Revised: |  | No. of Man-days:
New Corella | Mesaoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual:
New Corella | Mesaoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | Mesaoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
New Corella | Mesaoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Date Started:
Asuncion | Cabaywa | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | ROAD ID 071 - Lower Asuncion - Upper Asuncion |  | 20% Development Fund CY 2020 | Road Rehabilitaion |  | km | Admin | Project Cost: | 1302000 | Target Completion Date: |  | Program: | 1302000 | Planned: |  | No. of Persons: |  | Plan On-going
Asuncion | Cabaywa | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 1302000 | Revised: |  | No. of Man-days:
Asuncion | Cabaywa | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Asuncion | Cabaywa | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Asuncion | Cabaywa | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Asuncion | Cabaywa | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Date Started:
Tagum City | AAT | 1st Eng'g. Dist. | On-going | 2020-05-18 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS LOCAL ROADS & DRAINAGE DEV'T. PROJECT - LS P15,590,910.00 | Rehab. Of Various Local Roads @ Tagum City |  | 20% Development Fund CY 2020 | Rehabilitaion |  | km | Admin | Project Cost: | 2518182 | Target Completion Date: | 2020-10-20 | Program: | 2518182 | Planned: | 18.41% | No. of Persons: | 10 | On-going
Tagum City | AAT | 1st Eng'g. Dist. | On-going | 2020-05-18 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS LOCAL ROADS & DRAINAGE DEV'T. PROJECT - LS P15,590,910.00 | [7 empty] | Project Engineer: | Bataller | Revised Completion Date: |  | Allotment: | 2518182 | Revised: |  | No. of Man-days: | 150
Tagum City | AAT | 1st Eng'g. Dist. | On-going | 2020-05-18 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS LOCAL ROADS & DRAINAGE DEV'T. PROJECT - LS P15,590,910.00 | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: | 18.41%
Tagum City | AAT | 1st Eng'g. Dist. | On-going | 2020-05-18 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS LOCAL ROADS & DRAINAGE DEV'T. PROJECT - LS P15,590,910.00 | [7 empty] | Duration: | 155 | No. of days extended: |  |  |  | Slippage: | 0%
Tagum City | AAT | 1st Eng'g. Dist. | On-going | 2020-05-18 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS LOCAL ROADS & DRAINAGE DEV'T. PROJECT - LS P15,590,910.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Tagum City | AAT | 1st Eng'g. Dist. | On-going | 2020-05-18 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS LOCAL ROADS & DRAINAGE DEV'T. PROJECT - LS P15,590,910.00 | [7 empty] | Date Started: | 2020-05-18
Asuncion | AAA | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS LOCAL ROADS & DRAINAGE DEV'T. PROJECT - LS P15,590,910.00 | Rehab. Of Various Local Roads @ Asuncion |  | 20% Development Fund CY 2020 | Rehabilitaion |  | km | Admin | Project Cost: | 2518182 | Target Completion Date: | 2020-10-20 | Program: | 2518182 | Planned: | 37.83% | No. of Persons: | 10 | On-going
Asuncion | AAA | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS LOCAL ROADS & DRAINAGE DEV'T. PROJECT - LS P15,590,910.00 | [7 empty] | Project Engineer: | Bataller | Revised Completion Date: |  | Allotment: | 2518182 | Revised: |  | No. of Man-days: | 310
Asuncion | AAA | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS LOCAL ROADS & DRAINAGE DEV'T. PROJECT - LS P15,590,910.00 | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: | 37.82%
Asuncion | AAA | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS LOCAL ROADS & DRAINAGE DEV'T. PROJECT - LS P15,590,910.00 | [7 empty] | Duration: | 155 | No. of days extended: |  |  |  | Slippage: | -0.01%
Asuncion | AAA | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS LOCAL ROADS & DRAINAGE DEV'T. PROJECT - LS P15,590,910.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Asuncion | AAA | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS LOCAL ROADS & DRAINAGE DEV'T. PROJECT - LS P15,590,910.00 | [7 empty] | Date Started: | 2020-05-18
Kapalong | AAK | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS LOCAL ROADS & DRAINAGE DEV'T. PROJECT - LS P15,590,910.00 | Rehab. Of Various Local Roads @ Kapalong |  | 20% Development Fund CY 2020 | Rehabilitaion |  | km | Admin | Project Cost: | 2518182 | Target Completion Date: |  | Program: | 2518182 | Planned: |  | No. of Persons: |  | For Implementation
Kapalong | AAK | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS LOCAL ROADS & DRAINAGE DEV'T. PROJECT - LS P15,590,910.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 2518182 | Revised: |  | No. of Man-days:
Kapalong | AAK | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS LOCAL ROADS & DRAINAGE DEV'T. PROJECT - LS P15,590,910.00 | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual:
Kapalong | AAK | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS LOCAL ROADS & DRAINAGE DEV'T. PROJECT - LS P15,590,910.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Kapalong | AAK | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS LOCAL ROADS & DRAINAGE DEV'T. PROJECT - LS P15,590,910.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Kapalong | AAK | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS LOCAL ROADS & DRAINAGE DEV'T. PROJECT - LS P15,590,910.00 | [7 empty] | Date Started:
New Corella | AAN | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS LOCAL ROADS & DRAINAGE DEV'T. PROJECT - LS P15,590,910.00 | Rehab. Of Various Local Roads @ New Corella |  | 20% Development Fund CY 2020 | Rehabilitaion |  | km | Admin | Project Cost: | 2518182 | Target Completion Date: |  | Program: | 2518182 | Planned: |  | No. of Persons: |  | POW on process
New Corella | AAN | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS LOCAL ROADS & DRAINAGE DEV'T. PROJECT - LS P15,590,910.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 2518182 | Revised: |  | No. of Man-days:
New Corella | AAN | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS LOCAL ROADS & DRAINAGE DEV'T. PROJECT - LS P15,590,910.00 | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual:
New Corella | AAN | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS LOCAL ROADS & DRAINAGE DEV'T. PROJECT - LS P15,590,910.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | AAN | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS LOCAL ROADS & DRAINAGE DEV'T. PROJECT - LS P15,590,910.00 | [7 empty] | Date Allotment Released: |  | Date completed:
New Corella | AAN | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS LOCAL ROADS & DRAINAGE DEV'T. PROJECT - LS P15,590,910.00 | [7 empty] | Date Started:
San Isidro | AAS | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS LOCAL ROADS & DRAINAGE DEV'T. PROJECT - LS P15,590,910.00 | Rehab. Of Various Local Roads @ San Isidro |  | 20% Development Fund CY 2020 | Rehabilitaion |  | km | Admin | Project Cost: | 2518182 | Target Completion Date: |  | Program: | 2518182 | Planned: |  | No. of Persons: |  | POW on process
San Isidro | AAS | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS LOCAL ROADS & DRAINAGE DEV'T. PROJECT - LS P15,590,910.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 2518182 | Revised: |  | No. of Man-days:
San Isidro | AAS | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS LOCAL ROADS & DRAINAGE DEV'T. PROJECT - LS P15,590,910.00 | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual:
San Isidro | AAS | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS LOCAL ROADS & DRAINAGE DEV'T. PROJECT - LS P15,590,910.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
San Isidro | AAS | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS LOCAL ROADS & DRAINAGE DEV'T. PROJECT - LS P15,590,910.00 | [7 empty] | Date Allotment Released: |  | Date completed:
San Isidro | AAS | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS LOCAL ROADS & DRAINAGE DEV'T. PROJECT - LS P15,590,910.00 | [7 empty] | Date Started:
Talaingod | AAT | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS LOCAL ROADS & DRAINAGE DEV'T. PROJECT - LS P15,590,910.00 | Rehab. Of Various Local Roads @ Talaingod |  | 20% Development Fund CY 2020 | Rehabilitaion |  | km | Admin | Project Cost: | 2518182 | Target Completion Date: |  | Program: | 2518182 | Planned: |  | No. of Persons: |  | For Implementation
Talaingod | AAT | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS LOCAL ROADS & DRAINAGE DEV'T. PROJECT - LS P15,590,910.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 2518182 | Revised: |  | No. of Man-days:
Talaingod | AAT | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS LOCAL ROADS & DRAINAGE DEV'T. PROJECT - LS P15,590,910.00 | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual:
Talaingod | AAT | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS LOCAL ROADS & DRAINAGE DEV'T. PROJECT - LS P15,590,910.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Talaingod | AAT | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS LOCAL ROADS & DRAINAGE DEV'T. PROJECT - LS P15,590,910.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Talaingod | AAT | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS LOCAL ROADS & DRAINAGE DEV'T. PROJECT - LS P15,590,910.00 | [7 empty] | Date Started:
Tagum City | Mankilam | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | Construction of DAVNOR Tech-Vocational Center, Government Center, Mankilam, Tagum City |  | 20% Development Fund CY 2020 | Building |  | sq.m | Admin | Project Cost: | 8000000 | Target Completion Date: |  | Program: | 8000000 | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
Tagum City | Mankilam | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 8000000 | Revised: |  | No. of Man-days:
Tagum City | Mankilam | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual:
Tagum City | Mankilam | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Tagum City | Mankilam | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Tagum City | Mankilam | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Date Started:
Tagum City | Mankilam | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | Improvement of PSWDO Bodega Government Cente, Mankilam, Tagum City |  | 20% Development Fund CY 2020 | Building |  | sq.m | Admin | Project Cost: | 1000000 | Target Completion Date: |  | Program: | 1000000 | Planned: |  | No. of Persons: |  | POW and Plans on-going
Tagum City | Mankilam | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 1000000 | Revised: |  | No. of Man-days:
Tagum City | Mankilam | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual:
Tagum City | Mankilam | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Tagum City | Mankilam | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Tagum City | Mankilam | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Date Started:
San Isidro | Mamangan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | Renovation/Improvement of MAFAMCO Consumer's Bldg., Brgy. Mamangan, San Isidro |  | 20% Development Fund CY 2020 | Building |  | sq.m | Contract | Project Cost: | 800000 | Target Completion Date: |  | Program: | 800000 | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
San Isidro | Mamangan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 800000 | Revised: |  | No. of Man-days:
San Isidro | Mamangan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
San Isidro | Mamangan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
San Isidro | Mamangan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
San Isidro | Mamangan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Date Started:
Asuncion | Camansa | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | Construction of IP Council of Women Training Center, Camansa Kamadi District, Asuncion |  | 20% Development Fund CY 2020 | Building |  | sq.m | Admin | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
Asuncion | Camansa | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Asuncion | Camansa | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual:
Asuncion | Camansa | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Asuncion | Camansa | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Asuncion | Camansa | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Date Started:
New Corella | Cabidianan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | Construction of One(1) unit School Building at Cabidianan E/S, New Corella |  | 20% Development Fund CY 2020 | Building |  | sq.m | Contract | Project Cost: | 1300000 | Target Completion Date: |  | Program: | 1300000 | Planned: |  | No. of Persons:
New Corella | Cabidianan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 1300000 | Revised: |  | No. of Man-days:
New Corella | Cabidianan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
New Corella | Cabidianan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | Cabidianan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
New Corella | Cabidianan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Date Started:
Kapalong | Florida | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | Construction of one(1) unit School Building at Kamansi Integrated School, Florida, kapalong |  | 20% Development Fund CY 2020 | Building |  | sq.m | Contract | Project Cost: | 1300000 | Target Completion Date: |  | Program: | 1300000 | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
Kapalong | Florida | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 1300000 | Revised: |  | No. of Man-days:
Kapalong | Florida | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Kapalong | Florida | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Kapalong | Florida | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Kapalong | Florida | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Date Started:
Asuncion | Magatos | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | Construction of one(1) unit School Building at Magatos E/S, Magatos, Asuncion |  | 20% Development Fund CY 2020 | Building |  | sq.m | Contract | Project Cost: | 1300000 | Target Completion Date: |  | Program: | 1300000 | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
Asuncion | Magatos | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 1300000 | Revised: |  | No. of Man-days:
Asuncion | Magatos | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Asuncion | Magatos | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Asuncion | Magatos | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Asuncion | Magatos | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Date Started:
Talaingod | Sta. Cruz | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | Construction of one(1) unit School Building at Sta. Cruz E/S, New Corella |  | 20% Development Fund CY 2020 | Building |  | sq.m |  | Project Cost: | 1300000 | Target Completion Date: |  | Program: | 1300000 | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
Talaingod | Sta. Cruz | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 1300000 | Revised: |  | No. of Man-days:
Talaingod | Sta. Cruz | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Talaingod | Sta. Cruz | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Talaingod | Sta. Cruz | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Talaingod | Sta. Cruz | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Date Started:
Talaingod | Dagohoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | Construction Women Development Center, Dagohoy, Talaingod |  | 20% Development Fund CY 2020 | Building |  | sq.m |  | Project Cost: | 1000000 | Target Completion Date: |  | Program: | 1000000 | Planned: |  | No. of Persons: |  | Post qualification on process
Talaingod | Dagohoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 1000000 | Revised: |  | No. of Man-days:
Talaingod | Dagohoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Talaingod | Dagohoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Talaingod | Dagohoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Talaingod | Dagohoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Date Started:
Asuncion | Cambanogoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | Construction of Municipal Triball Hall, Asuncion |  | 20% Development Fund CY 2020 | Building |  | sq.m | Contract | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
Asuncion | Cambanogoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Asuncion | Cambanogoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Asuncion | Cambanogoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Asuncion | Cambanogoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Asuncion | Cambanogoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Date Started:
Kapalong | Maniki | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | Construction of Municipal Triball Hall, Kapalong |  | 20% Development Fund CY 2020 | Building |  | sq.m | Contract | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
Kapalong | Maniki | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Kapalong | Maniki | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Kapalong | Maniki | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Kapalong | Maniki | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Kapalong | Maniki | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Date Started:
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | Construction of Municipal Triball Hall, Talaingod |  | 20% Development Fund CY 2020 | Building |  | sq.m | Contract | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Date Started:
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | DISASTER PREVENTION AND MITIGATION PROGRAM - FLOOD CONTROL AND SLOPE PROTECTION PROJECT (Revetment of Dike and Slope Protection) | Rehab./Impv't. of Sto. Niño-Daligdigon-Paiton |  | 5% CALAMITY FUND CY 2020 | Road |  | km |  | Project Cost: | 1000000 | Target Completion Date: |  | Program: | 1000000 | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | DISASTER PREVENTION AND MITIGATION PROGRAM - FLOOD CONTROL AND SLOPE PROTECTION PROJECT (Revetment of Dike and Slope Protection) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 1000000 | Revised: |  | No. of Man-days:
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | DISASTER PREVENTION AND MITIGATION PROGRAM - FLOOD CONTROL AND SLOPE PROTECTION PROJECT (Revetment of Dike and Slope Protection) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | DISASTER PREVENTION AND MITIGATION PROGRAM - FLOOD CONTROL AND SLOPE PROTECTION PROJECT (Revetment of Dike and Slope Protection) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | DISASTER PREVENTION AND MITIGATION PROGRAM - FLOOD CONTROL AND SLOPE PROTECTION PROJECT (Revetment of Dike and Slope Protection) | [7 empty] | Date Allotment Released: |  | Date completed:
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | DISASTER PREVENTION AND MITIGATION PROGRAM - FLOOD CONTROL AND SLOPE PROTECTION PROJECT (Revetment of Dike and Slope Protection) | [7 empty] | Date Started:
Asuncion | Sonlon | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | DISASTER PREVENTION AND MITIGATION PROGRAM - FLOOD CONTROL AND SLOPE PROTECTION PROJECT (Improvement of Bridges and Cross Drainage) | Improvement of Saug-Sonlon-Bdry. Longanapan |  | 5% CALAMITY FUND CY 2020 | Road |  | km |  | Project Cost: | 1000000 | Target Completion Date: |  | Program: | 1000000 | Planned: |  | No. of Persons: |  | For preparation of POW and Plans
Asuncion | Sonlon | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | DISASTER PREVENTION AND MITIGATION PROGRAM - FLOOD CONTROL AND SLOPE PROTECTION PROJECT (Improvement of Bridges and Cross Drainage) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 1000000 | Revised: |  | No. of Man-days:
Asuncion | Sonlon | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | DISASTER PREVENTION AND MITIGATION PROGRAM - FLOOD CONTROL AND SLOPE PROTECTION PROJECT (Improvement of Bridges and Cross Drainage) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Asuncion | Sonlon | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | DISASTER PREVENTION AND MITIGATION PROGRAM - FLOOD CONTROL AND SLOPE PROTECTION PROJECT (Improvement of Bridges and Cross Drainage) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Asuncion | Sonlon | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | DISASTER PREVENTION AND MITIGATION PROGRAM - FLOOD CONTROL AND SLOPE PROTECTION PROJECT (Improvement of Bridges and Cross Drainage) | [7 empty] | Date Allotment Released: |  | Date completed:
Asuncion | Sonlon | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | DISASTER PREVENTION AND MITIGATION PROGRAM - FLOOD CONTROL AND SLOPE PROTECTION PROJECT (Improvement of Bridges and Cross Drainage) | [7 empty] | Date Started:
Kapalong | Gupitan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | Const. of 1 Classroom @ Mankay Integrated School, Gupitan, kapalong |  | SEF CY 2020 | Building |  | sq.m |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Opening of Shopping on June 25, 2020
Kapalong | Gupitan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Kapalong | Gupitan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Kapalong | Gupitan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Kapalong | Gupitan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Kapalong | Gupitan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Date Started:
Kapalong | Gupitan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | Const. of 1 Classroom @ Luno-luno E/S, Gupitan, kapalong |  | SEF CY 2020 | Building |  | sq.m |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Opening of Shopping on June 25, 2020
Kapalong | Gupitan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Kapalong | Gupitan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Kapalong | Gupitan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Kapalong | Gupitan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Kapalong | Gupitan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Date Started:
Kapalong | Gupitan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | Const. of 1 Classroom @ Kamunuan E/S, Gupitan, kapalong |  | SEF CY 2020 | Building |  | sq.m |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Opening of Shopping on June 25, 2020
Kapalong | Gupitan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Kapalong | Gupitan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Kapalong | Gupitan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Kapalong | Gupitan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Kapalong | Gupitan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Date Started:
Kapalong | Gupitan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | Const. of 1 Classroom @ Tawinian E/S, Gupitan, kapalong |  | SEF CY 2020 | Building |  | sq.m |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Opening of Shopping on June 25, 2020
Kapalong | Gupitan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Kapalong | Gupitan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Kapalong | Gupitan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Kapalong | Gupitan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Kapalong | Gupitan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Date Started:
Kapalong | Gupitan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | Const. of 1 Classroom @ Aninipot E/S, Gupitan, kapalong |  | SEF CY 2020 | Building |  | sq.m |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Opening of Shopping on June 25, 2020
Kapalong | Gupitan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Kapalong | Gupitan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Kapalong | Gupitan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Kapalong | Gupitan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Kapalong | Gupitan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Date Started:
Kapalong | Gupitan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | Const. of 1 Classroom @ Moling E/S, Gupitan, kapalong |  | SEF CY 2020 | Building |  | sq.m |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Opening of Shopping on June 25, 2020
Kapalong | Gupitan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Kapalong | Gupitan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Kapalong | Gupitan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Kapalong | Gupitan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Kapalong | Gupitan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Date Started:
Talaingod | Dagohoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | Const. of 1 Classroom @ Lomondong E/S, Dagohoy, Talaingod |  | SEF CY 2020 | Building |  | sq.m |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Opening of Shopping on June 25, 2020
Talaingod | Dagohoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Talaingod | Dagohoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Talaingod | Dagohoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Talaingod | Dagohoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Talaingod | Dagohoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Date Started:
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | Const. of 1 Classroom @ Malapanit E/S, Sto. Niño, Talaingod |  | SEF CY 2020 | Building |  | sq.m |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Opening of Shopping on June 25, 2020
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Date Started:
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | Const. of 1 Classroom @ Laputlakan E/S, Sto. Niño, Talaingod |  | SEF CY 2020 | Building |  | sq.m |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Opening of Shopping on June 25, 2020
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Date Started:
New Corella | Limbaan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | Const. of Day Care Center, Limbaan, New Corella |  | 20% DF CY 2020 | Building |  | sq.m |  | Project Cost: | 1000000 | Target Completion Date: |  | Program: | 1000000 | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
New Corella | Limbaan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 1000000 | Revised: |  | No. of Man-days:
New Corella | Limbaan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
New Corella | Limbaan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | Limbaan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
New Corella | Limbaan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Date Started:
Kapalong | Gabuyan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | Const. of Day Care Center, Gabuyan, kapalong |  | 20% DF CY 2020 | Building |  | sq.m |  | Project Cost: | 1000000 | Target Completion Date: |  | Program: | 1000000 | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
Kapalong | Gabuyan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 1000000 | Revised: |  | No. of Man-days:
Kapalong | Gabuyan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Kapalong | Gabuyan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Kapalong | Gabuyan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Kapalong | Gabuyan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Date Started:
Asuncion | Canatan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | Compl./Rep. Day Care Center,Canatan, Asuncion |  | 20% DF CY 2020 | Building |  | sq.m |  | Project Cost: | 300000 | Target Completion Date: |  | Program: | 300000 | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
Asuncion | Canatan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 300000 | Revised: |  | No. of Man-days:
Asuncion | Canatan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Asuncion | Canatan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Asuncion | Canatan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Asuncion | Canatan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Date Started:
Asuncion | Cambanogoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | Compl./Rep. Day Care Center,Cambanogoy, Asuncion |  | 20% DF CY 2020 | Building |  | sq.m |  | Project Cost: | 300000 | Target Completion Date: |  | Program: | 300000 | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
Asuncion | Cambanogoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 300000 | Revised: |  | No. of Man-days:
Asuncion | Cambanogoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Asuncion | Cambanogoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Asuncion | Cambanogoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Asuncion | Cambanogoy | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Date Started:
Kapalong | Gabuyan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | Compl./Rep. Day Care Center,Gabuyan, kapalong |  | 20% DF CY 2020 | Building |  | sq.m |  | Project Cost: | 600000 | Target Completion Date: |  | Program: | 600000 | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
Kapalong | Gabuyan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 600000 | Revised: |  | No. of Man-days:
Kapalong | Gabuyan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Kapalong | Gabuyan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Kapalong | Gabuyan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Kapalong | Gabuyan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Date Started:
New Corella | New Sambog | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | Compl./Rep. Day Care Center,New Sambog, New Corella |  | 20% DF CY 2020 | Building |  | sq.m |  | Project Cost: | 300000 | Target Completion Date: |  | Program: | 300000 | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
New Corella | New Sambog | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 300000 | Revised: |  | No. of Man-days:
New Corella | New Sambog | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
New Corella | New Sambog | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | New Sambog | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
New Corella | New Sambog | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Date Started:
New Corella | Cabidianan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | Compl./Rep. Day Care Center, Cabidianan, New Corella |  | 20% DF CY 2020 | Building |  | sq.m |  | Project Cost: | 300000 | Target Completion Date: |  | Program: | 300000 | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
New Corella | Cabidianan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 300000 | Revised: |  | No. of Man-days:
New Corella | Cabidianan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
New Corella | Cabidianan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | Cabidianan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
New Corella | Cabidianan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Date Started:
San Isidro | Igangon | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | Compl./Rep. Day Care Center, Igangon, San Isidro |  | 20% DF CY 2020 | Building |  | sq.m |  | Project Cost: | 300000 | Target Completion Date: |  | Program: | 300000 | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
San Isidro | Igangon | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 300000 | Revised: |  | No. of Man-days:
San Isidro | Igangon | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
San Isidro | Igangon | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
San Isidro | Igangon | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
San Isidro | Igangon | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Date Started:
Tagum City | Madaum | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | Compl./Rep. Day Care Center, Madaum, Tagum City |  | 20% DF CY 2020 | Building |  | sq.m |  | Project Cost: | 300000 | Target Completion Date: |  | Program: | 300000 | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
Tagum City | Madaum | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 300000 | Revised: |  | No. of Man-days:
Tagum City | Madaum | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Tagum City | Madaum | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Tagum City | Madaum | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Tagum City | Madaum | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Date Started:
Tagum City | Apokon | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | Compl./Rep. Day Care Center, Apokon, Tagum City |  | 20% DF CY 2020 | Building |  | sq.m |  | Project Cost: | 300000 | Target Completion Date: |  | Program: | 300000 | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
Tagum City | Apokon | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 300000 | Revised: |  | No. of Man-days:
Tagum City | Apokon | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Tagum City | Apokon | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Tagum City | Apokon | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Tagum City | Apokon | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Date Started:
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | Compl./Rep. Day Care Center, Sto. Niño, Talaingod |  | 20% DF CY 2020 | Building |  | sq.m |  | Project Cost: | 300000 | Target Completion Date: |  | Program: | 300000 | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 300000 | Revised: |  | No. of Man-days:
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Date Started:
New Corella | Poblacion | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | HEALTH CARE SERVICES PROGRAM (PEEDO) | Improvement/Rehab. Of Luntiang Paraiso, New Corella |  | 20% DF CY 2020 | Building |  | km |  | Project Cost: | 3000000 | Target Completion Date: |  | Program: | 3000000 | Planned: |  | No. of Persons: |  | For Purchase Request
New Corella | Poblacion | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | HEALTH CARE SERVICES PROGRAM (PEEDO) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 3000000 | Revised: |  | No. of Man-days:
New Corella | Poblacion | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | HEALTH CARE SERVICES PROGRAM (PEEDO) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
New Corella | Poblacion | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | HEALTH CARE SERVICES PROGRAM (PEEDO) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
New Corella | Poblacion | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | HEALTH CARE SERVICES PROGRAM (PEEDO) | [7 empty] | Date Allotment Released: |  | Date completed:
New Corella | Poblacion | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | HEALTH CARE SERVICES PROGRAM (PEEDO) | [7 empty] | Date Started:
Tagum City | Mankilam | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | PSYDO YOUTH DEV'T. PROGRAM - TEEN TAMBAYAN PROJECT | Renovation of Teen Tambayan |  | 20% DF CY 2020 | Building |  | sq.m |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Date of procurement June 30, 2020
Tagum City | Mankilam | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | PSYDO YOUTH DEV'T. PROGRAM - TEEN TAMBAYAN PROJECT | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Tagum City | Mankilam | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | PSYDO YOUTH DEV'T. PROGRAM - TEEN TAMBAYAN PROJECT | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Tagum City | Mankilam | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | PSYDO YOUTH DEV'T. PROGRAM - TEEN TAMBAYAN PROJECT | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Tagum City | Mankilam | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | PSYDO YOUTH DEV'T. PROGRAM - TEEN TAMBAYAN PROJECT | [7 empty] | Date Allotment Released: |  | Date completed:
Tagum City | Mankilam | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | PSYDO YOUTH DEV'T. PROGRAM - TEEN TAMBAYAN PROJECT | [7 empty] | Date Started:
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2020-06-01 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SPECIAL TRUST FUND (PDRRMC) | Installation of 20 units Isolation Room, Sports Academy Dormitory, DNSTC |  | TF | Isolation | 20 | sq.m | Admin | Project Cost: | 170000 | Target Completion Date: |  | Program: | 170000 | Planned: | 95% | No. of Persons: |  | On-going
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2020-06-01 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SPECIAL TRUST FUND (PDRRMC) | [7 empty] | Project Engineer: | Chua | Revised Completion Date: |  | Allotment: | 170000 | Revised: |  | No. of Man-days:
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2020-06-01 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SPECIAL TRUST FUND (PDRRMC) | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: | 95%
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2020-06-01 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SPECIAL TRUST FUND (PDRRMC) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2020-06-01 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SPECIAL TRUST FUND (PDRRMC) | [7 empty] | Date Allotment Released: | 2020-06-01 | Date completed:
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2020-06-01 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SPECIAL TRUST FUND (PDRRMC) | [7 empty] | Date Started: | 2020-06-01
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2020-06-01 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SPECIAL TRUST FUND (PDRRMC) | Installation of 100 units isolation room (2.0 x 3.0m), DAVNOR GYM |  | TF | Isolation | 100 | sq.m | Admin | Project Cost: | 750000 | Target Completion Date: |  | Program: | 750000 | Planned: | 95% | No. of Persons: |  | On-going
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2020-06-01 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SPECIAL TRUST FUND (PDRRMC) | [7 empty] | Project Engineer: | Chua | Revised Completion Date: |  | Allotment: | 750000 | Revised: |  | No. of Man-days:
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2020-06-01 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SPECIAL TRUST FUND (PDRRMC) | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: | 95%
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2020-06-01 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SPECIAL TRUST FUND (PDRRMC) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2020-06-01 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SPECIAL TRUST FUND (PDRRMC) | [7 empty] | Date Allotment Released: | 2020-06-01 | Date completed:
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2020-06-01 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SPECIAL TRUST FUND (PDRRMC) | [7 empty] | Date Started: | 2020-06-01
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2020-06-01 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SPECIAL TRUST FUND (PDRRMC) | Installation of 40 units Isolation Room, Sports Academy Dormitory, DNSTC |  | TF | Isolation | 40 | sq.m | Admin | Project Cost: | 320000 | Target Completion Date: |  | Program: | 320000 | Planned: | 95% | No. of Persons: |  | On-going
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2020-06-01 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SPECIAL TRUST FUND (PDRRMC) | [7 empty] | Project Engineer: | Chua | Revised Completion Date: |  | Allotment: | 320000 | Revised: |  | No. of Man-days:
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2020-06-01 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SPECIAL TRUST FUND (PDRRMC) | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: | 95%
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2020-06-01 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SPECIAL TRUST FUND (PDRRMC) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2020-06-01 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SPECIAL TRUST FUND (PDRRMC) | [7 empty] | Date Allotment Released: | 2020-05-28 | Date completed:
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2020-06-01 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | SPECIAL TRUST FUND (PDRRMC) | [7 empty] | Date Started: | 2020-06-01
Talaingod | Palma Gil | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | PEACE AND ORDER PROGRAM | Proposed Road Opening of Nasilaban - Pongpong Road Section, Talaingod |  | SB # 1 CY 2020 | Road |  | km |  | Project Cost: | 5500000 | Target Completion Date: |  | Program: | 5500000 | Planned: |  | No. of Persons: |  | PO #2020062105 - M3C CONSTRUCTION & SUPPLY; PO #2020061966 - FL2 LUMBER & CONSTRUCTION SUPPLY; PO #2020062217 - Alpebel Builders and Supply Corporation, PO #DIOCESAN PRINTING PRESS
Talaingod | Palma Gil | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | PEACE AND ORDER PROGRAM | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 5500000 | Revised: |  | No. of Man-days:
Talaingod | Palma Gil | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | PEACE AND ORDER PROGRAM | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Talaingod | Palma Gil | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | PEACE AND ORDER PROGRAM | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Talaingod | Palma Gil | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | PEACE AND ORDER PROGRAM | [7 empty] | Date Allotment Released: |  | Date completed:
Talaingod | Palma Gil | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | PEACE AND ORDER PROGRAM | [7 empty] | Date Started:
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOV'T. BLDG. & FAC. DEV'T. PROJECT | Establishment of Multiplier Farm Phase 2, Brgy. Sto. Niño, Talaingod |  | SB # 1 CY 2020 | Building |  | sq.m |  | Project Cost: | 380000 | Target Completion Date: |  | Program: | 380000 | Planned: |  | No. of Persons: |  | For bidding on June 30, 2020; Re-bid July 28, 2020.
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOV'T. BLDG. & FAC. DEV'T. PROJECT | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 380000 | Revised: |  | No. of Man-days:
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOV'T. BLDG. & FAC. DEV'T. PROJECT | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOV'T. BLDG. & FAC. DEV'T. PROJECT | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOV'T. BLDG. & FAC. DEV'T. PROJECT | [7 empty] | Date Allotment Released: |  | Date completed:
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOV'T. BLDG. & FAC. DEV'T. PROJECT | [7 empty] | Date Started:
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOV'T. BLDG. & FAC. DEV'T. PROJECT | Establishment of Multiplier Farm (Poultry House), Phase 2, Brgy. Sto. Niño, Talaingod |  | SB # 1 CY 2020 | Building |  | sq.m |  | Project Cost: | 110000 | Target Completion Date: |  | Program: | 110000 | Planned: |  | No. of Persons: |  | For bidding on June 30, 2020; Re-bid July 28, 2020.
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOV'T. BLDG. & FAC. DEV'T. PROJECT | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 110000 | Revised: |  | No. of Man-days:
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOV'T. BLDG. & FAC. DEV'T. PROJECT | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOV'T. BLDG. & FAC. DEV'T. PROJECT | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOV'T. BLDG. & FAC. DEV'T. PROJECT | [7 empty] | Date Allotment Released: |  | Date completed:
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOV'T. BLDG. & FAC. DEV'T. PROJECT | [7 empty] | Date Started:
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOV'T. BLDG. & FAC. DEV'T. PROJECT | Poultry House and Training Center Phase 2, Talaingod |  | SB # 1 CY 2020 | Building |  | sq.m |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | For bidding on June 30, 2020; Re-bid July 28, 2020.
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOV'T. BLDG. & FAC. DEV'T. PROJECT | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOV'T. BLDG. & FAC. DEV'T. PROJECT | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOV'T. BLDG. & FAC. DEV'T. PROJECT | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOV'T. BLDG. & FAC. DEV'T. PROJECT | [7 empty] | Date Allotment Released: |  | Date completed:
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | VARIOUS GOV'T. BLDG. & FAC. DEV'T. PROJECT | [7 empty] | Date Started:
Kapalong | Maniki | 1st Eng'g. Dist. | On-going | 2020-05-11 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | BAYANIHAN GRANT TO PROVINCES | Improvement of Hospital facilities (Isolation/ICU), Kapalong Dist. Hospital |  | SB # 2 CY 2020 | Isolation |  | sq.m | Admin | Project Cost: | 6000000 | Target Completion Date: | 2021-01-10 23:59 | Program: | 6000000 | Planned: | 60.08% | No. of Persons: | 34 | On-going
Kapalong | Maniki | 1st Eng'g. Dist. | On-going | 2020-05-11 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | BAYANIHAN GRANT TO PROVINCES | [7 empty] | Project Engineer: | Pasiona/Aclaracion | Revised Completion Date: |  | Allotment: | 6000000 | Revised: |  | No. of Man-days: | 1054
Kapalong | Maniki | 1st Eng'g. Dist. | On-going | 2020-05-11 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | BAYANIHAN GRANT TO PROVINCES | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: | 60.08%
Kapalong | Maniki | 1st Eng'g. Dist. | On-going | 2020-05-11 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | BAYANIHAN GRANT TO PROVINCES | [7 empty] | Duration: | 245 | No. of days extended: |  |  |  | Slippage: | 0%
Kapalong | Maniki | 1st Eng'g. Dist. | On-going | 2020-05-11 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | BAYANIHAN GRANT TO PROVINCES | [7 empty] | Date Allotment Released: | 2020-05-07 | Date completed:
Kapalong | Maniki | 1st Eng'g. Dist. | On-going | 2020-05-11 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | BAYANIHAN GRANT TO PROVINCES | [7 empty] | Date Started: | 2020-05-11
Kapalong | Gabuyan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | CMGP | Road Improvement of Jct. Highway Gabuyan – Semong – Dagohoy Provincial Road |  | CMGP | Road |  | km |  | Project Cost: | 63458000 | Target Completion Date: |  | Program: | 63458000 | Planned: |  | No. of Persons: |  | For posting
Kapalong | Gabuyan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | CMGP | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 63458000 | Revised: |  | No. of Man-days:
Kapalong | Gabuyan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | CMGP | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Kapalong | Gabuyan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | CMGP | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Kapalong | Gabuyan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | CMGP | [7 empty] | Date Allotment Released: |  | Date completed:
Kapalong | Gabuyan | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | CMGP | [7 empty] | Date Started:
Talaingod | Palma Gil | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | NHA | Const. of 100 Housing Units at Balai Lupowanan at Sitio Nasilaban, Palma Gil, Talaingod |  | Natinal Housing Project CY 2020 | Building | 100 | units | Admin | Project Cost: | 20000000 | Target Completion Date: |  | Program: | 20000000 | Planned: |  | No. of Persons: |  | For bidding on July 3, 2020
Talaingod | Palma Gil | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | NHA | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 20000000 | Revised: |  | No. of Man-days:
Talaingod | Palma Gil | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | NHA | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Talaingod | Palma Gil | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | NHA | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Talaingod | Palma Gil | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | NHA | [7 empty] | Date Allotment Released: |  | Date completed:
Talaingod | Palma Gil | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | NHA | [7 empty] | Date Started:
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | NHA | Const. of 100 Housing Units at Balai Pig Immimanan at Sitio Mesulong, Sto. Niño, Talaingod |  | Natinal Housing Project CY 2020 | Building | 100 | units | Admin | Project Cost: | 20000000 | Target Completion Date: |  | Program: | 20000000 | Planned: |  | No. of Persons: |  | For bidding on July 3, 2020
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | NHA | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 20000000 | Revised: |  | No. of Man-days:
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | NHA | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | NHA | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | NHA | [7 empty] | Date Allotment Released: |  | Date completed:
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | NHA | [7 empty] | Date Started:
Panabo City | San Roque | 2nd Eng'g. Dist. | Completed |  | 2020-06-30 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) LS - P9,000,000.00 | Const. of MP Bldg. w/ Electrical installation, San Roque, Panabo City |  | 20% DF CY 2017 (STIMULUS) | Building |  | ln.m | MLGU | Project Cost: | 500000 | Target Completion Date: | 6/10/2019 | Program: | 500000 | Planned: | 100% | No. of Persons: |  | Completed as per physical accomplishment. Financial documents still on process.
Panabo City | San Roque | 2nd Eng'g. Dist. | Completed |  | 2020-06-30 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) LS - P9,000,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Panabo City | San Roque | 2nd Eng'g. Dist. | Completed |  | 2020-06-30 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) LS - P9,000,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: | 100%
Panabo City | San Roque | 2nd Eng'g. Dist. | Completed |  | 2020-06-30 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) LS - P9,000,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Panabo City | San Roque | 2nd Eng'g. Dist. | Completed |  | 2020-06-30 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) LS - P9,000,000.00 | [7 empty] | Date Allotment Released: | 2018-01-31 | Date completed: | 2019-06-10
Panabo City | San Roque | 2nd Eng'g. Dist. | Completed |  | 2020-06-30 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) LS - P9,000,000.00 | [7 empty] | Date Started:
B.E. Dujali | Magupising | 2nd Eng'g. Dist. | Completed | 2019-12-02 | 2020-05-29 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | Rehab.of Dujali - Balisong - Magupising Provincial Road |  | 20% DF CY 2019 | Road Rehabilitation | 19.16 | km | MBA | Project Cost: | 1280000 | Target Completion Date: | 2020-01-15 23:59 | Program: | 1280000 | Planned: | 100% | No. of Persons: | 12 | Completed as per physical accomplishment. Financial documents still on process.
B.E. Dujali | Magupising | 2nd Eng'g. Dist. | Completed | 2019-12-02 | 2020-05-29 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Project Engineer: | Mellomida | Revised Completion Date: | 2020-05-31 23:59 | Allotment: | 1280000 | Revised: |  | No. of Man-days: | 900
B.E. Dujali | Magupising | 2nd Eng'g. Dist. | Completed | 2019-12-02 | 2020-05-29 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Implementor: | PEO | No. of days suspended: | 137 | Disbursement: | 14331.6 | Actual: | 100%
B.E. Dujali | Magupising | 2nd Eng'g. Dist. | Completed | 2019-12-02 | 2020-05-29 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Duration: | 45 | No. of days extended: |  |  |  | Slippage: | 0%
B.E. Dujali | Magupising | 2nd Eng'g. Dist. | Completed | 2019-12-02 | 2020-05-29 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Date Allotment Released: |  | Date completed: | 2020-05-29
B.E. Dujali | Magupising | 2nd Eng'g. Dist. | Completed | 2019-12-02 | 2020-05-29 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Date Started: | 2019-12-02
Sto. Tomas | Tibal-og | 2nd Eng'g. Dist. | Completed | 2019-02-22 | 2020-06-30 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPPAP-PAMANA | Construction of Tribal Hall, Sto. Tomas |  | OPPAP-PAMANA CY 2017 | Building |  | sq.m | Admin | Project Cost: | 500000 | Target Completion Date: | 2019-07-31 | Program: | 500000 | Planned: | 100% | No. of Persons: | 7 | Resume last June 22, 2020; Completed as per physical accomplishment. Financial documents still on process.
Sto. Tomas | Tibal-og | 2nd Eng'g. Dist. | Completed | 2019-02-22 | 2020-06-30 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPPAP-PAMANA | [7 empty] | Project Engineer: | Roque | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days: | 110
Sto. Tomas | Tibal-og | 2nd Eng'g. Dist. | Completed | 2019-02-22 | 2020-06-30 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPPAP-PAMANA | [7 empty] | Implementor: | Admin | No. of days suspended: |  | Disbursement: |  | Actual: | 100%
Sto. Tomas | Tibal-og | 2nd Eng'g. Dist. | Completed | 2019-02-22 | 2020-06-30 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPPAP-PAMANA | [7 empty] | Duration: | 70 | No. of days extended: |  |  |  | Slippage: | 0%
Sto. Tomas | Tibal-og | 2nd Eng'g. Dist. | Completed | 2019-02-22 | 2020-06-30 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPPAP-PAMANA | [7 empty] | Date Allotment Released: | CY 2018 | Date completed: | 2020-06-30
Sto. Tomas | Tibal-og | 2nd Eng'g. Dist. | Completed | 2019-02-22 | 2020-06-30 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPPAP-PAMANA | [7 empty] | Date Started: | 2019-05-22
Panabo City | Lasang | 2nd Eng'g. Dist. | On-going | 2015-05-30 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOV'T. BLDG. & FAC. DEV'T. PROJECT | Proposed Davao del Norte Tourism Billboard, Brgy. Lasang, Panabo City |  | SB # 1 CY 2015 | Billboard |  | sq.m | Admin | Project Cost: | 756400 | Target Completion Date: | 2015-05-10 23:59 | Program: | 756400 | Planned: | 11.78% | No. of Persons: |  | delay due to change location & design code. For AIP amendment from Panabo City to Gov't Center, Mankilam
Panabo City | Lasang | 2nd Eng'g. Dist. | On-going | 2015-05-30 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOV'T. BLDG. & FAC. DEV'T. PROJECT | [7 empty] | Project Engineer: | Porras | Revised Completion Date: |  | Allotment: | 756400 | Revised: |  | No. of Man-days:
Panabo City | Lasang | 2nd Eng'g. Dist. | On-going | 2015-05-30 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOV'T. BLDG. & FAC. DEV'T. PROJECT | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: | 332087.3 | Actual: | 11.78%
Panabo City | Lasang | 2nd Eng'g. Dist. | On-going | 2015-05-30 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOV'T. BLDG. & FAC. DEV'T. PROJECT | [7 empty] | Duration: | 42 | No. of days extended: |  |  |  | Slippage: | 0%
Panabo City | Lasang | 2nd Eng'g. Dist. | On-going | 2015-05-30 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOV'T. BLDG. & FAC. DEV'T. PROJECT | [7 empty] | Date Allotment Released: | 2015-05-06 | Date completed:
Panabo City | Lasang | 2nd Eng'g. Dist. | On-going | 2015-05-30 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOV'T. BLDG. & FAC. DEV'T. PROJECT | [7 empty] | Date Started: | 2015-03-30
Sto. Tomas | Esperanza | 2nd Eng'g. Dist. | On-going | 2017-03-22 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PRDP | Rehab. of Esperanza-Pob. Sto. Tomas, FMR, DDN |  | PRDP CY 2014 | Road Concreting | 12.774 | km | Contract | Project Cost: | 117410426.3 | Target Completion Date: | 2019-07-22 23:59 | Program: | 117410426.3 | Planned: | 100% | No. of Persons: | 20 | On-going
Sto. Tomas | Esperanza | 2nd Eng'g. Dist. | On-going | 2017-03-22 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PRDP | [7 empty] | Project Engineer: | Palero | Revised Completion Date: | 2020-07-31 23:59 | Allotment: | 117410426.3 | Revised: | 95.53% | No. of Man-days: | 600
Sto. Tomas | Esperanza | 2nd Eng'g. Dist. | On-going | 2017-03-22 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PRDP | [7 empty] | Implementor: | ALZAM | No. of days suspended: |  | Disbursement: |  | Actual: | 87.82%
Sto. Tomas | Esperanza | 2nd Eng'g. Dist. | On-going | 2017-03-22 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PRDP | [7 empty] | Duration: | 853 | No. of days extended: | 375 |  |  | Slippage: | -7.705%
Sto. Tomas | Esperanza | 2nd Eng'g. Dist. | On-going | 2017-03-22 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PRDP | [7 empty] | Date Allotment Released: | CY 2014 | Date completed:
Sto. Tomas | Esperanza | 2nd Eng'g. Dist. | On-going | 2017-03-22 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PRDP | [7 empty] | Date Started: | 2017-03-22
Sto. Tomas | Poblacion | 2nd Eng'g. Dist. | On-going | 2018-01-29 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PRDP | Improvement of Sto. Tomas Production Center with Common Facility, Sto. Tomas |  | PRDP CY 2016 | Building | 1901 | sq.m | Contract | Project Cost: | 9825000 | Target Completion Date: | 2019-12-24 23:59 | Program: | 9825000 | Planned: | 3.94% | No. of Persons: | 7 | On-going (Resumption dated last July 6, 2020)
Sto. Tomas | Poblacion | 2nd Eng'g. Dist. | On-going | 2018-01-29 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PRDP | [7 empty] | Project Engineer: | Azotes | Revised Completion Date: | 2021-05-31 23:59 | Allotment: | 9825000 | Revised: |  | No. of Man-days: | 105
Sto. Tomas | Poblacion | 2nd Eng'g. Dist. | On-going | 2018-01-29 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PRDP | [7 empty] | Implementor: | Manantan | No. of days suspended: | 524 | Disbursement: |  | Actual: | 1.72%
Sto. Tomas | Poblacion | 2nd Eng'g. Dist. | On-going | 2018-01-29 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PRDP | [7 empty] | Duration: | 330 | No. of days extended: |  |  |  | Slippage: | -2.22%
Sto. Tomas | Poblacion | 2nd Eng'g. Dist. | On-going | 2018-01-29 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PRDP | [7 empty] | Date Allotment Released: | CY 2014 | Date completed:
Sto. Tomas | Poblacion | 2nd Eng'g. Dist. | On-going | 2018-01-29 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PRDP | [7 empty] | Date Started: | 2019-01-29
IGCS | Kinawitnon | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | RURAL ELECTRIFICATION PROJECT | Inst. of transformer and accessories, Brgy. Kinawitnon |  | 20% DF CY 2016 | Electrification |  |  | Admin | Project Cost: | 150000 | Target Completion Date: |  | Program: | 150000 | Planned: |  | No. of Persons: |  | Purchase Order # 2019103228 - Transformer; Purchase Order # 2019102931 - Billboard; Purchase Order # 2019103227 - Lumber
IGCS | Kinawitnon | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | RURAL ELECTRIFICATION PROJECT | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 150000 | Revised: |  | No. of Man-days:
IGCS | Kinawitnon | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | RURAL ELECTRIFICATION PROJECT | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
IGCS | Kinawitnon | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | RURAL ELECTRIFICATION PROJECT | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
IGCS | Kinawitnon | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | RURAL ELECTRIFICATION PROJECT | [7 empty] | Date Allotment Released: | 2018-07-31 | Date completed:
IGCS | Kinawitnon | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | RURAL ELECTRIFICATION PROJECT | [7 empty] | Date Started:
Samal | Sta. Cruz | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | RURAL ELECTRIFICATION PROJECT | Rural Electrification at brgy. Sta. Cruz, talikud, Samal |  | 20% DF CY 2016 | Electrification |  |  | Contract | Project Cost: | 2000000 | Target Completion Date: |  | Program: | 2000000 | Planned: |  | No. of Persons: |  | Delay due to slow action of Daneco for staking. c/o Engr. Kim
Samal | Sta. Cruz | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | RURAL ELECTRIFICATION PROJECT | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 2000000 | Revised: |  | No. of Man-days:
Samal | Sta. Cruz | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | RURAL ELECTRIFICATION PROJECT | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Samal | Sta. Cruz | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | RURAL ELECTRIFICATION PROJECT | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Samal | Sta. Cruz | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | RURAL ELECTRIFICATION PROJECT | [7 empty] | Date Allotment Released: |  | Date completed:
Samal | Sta. Cruz | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | RURAL ELECTRIFICATION PROJECT | [7 empty] | Date Started:
BABAK | Kinawitnon | 2nd Eng'g. Dist. | On-going | 2018-03-12 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) LS - P9,000,000.00 | Construction of Provincial Training Center , Compound Fence, Kinawitnon, Babak District, IGCS |  | 20% DF CY 2016 | Fence |  | sq.m | Admin | Project Cost: | 940000 | Target Completion Date: | 2018-06-19 23:59 | Program: | 940000 | Planned: | 68% | No. of Persons: |  | Temporarily suspended 4/23/18 due to undemolished structures of illegal settlers
BABAK | Kinawitnon | 2nd Eng'g. Dist. | On-going | 2018-03-12 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) LS - P9,000,000.00 | [7 empty] | Project Engineer: | Pacquiao | Revised Completion Date: |  | Allotment: | 940000 | Revised: |  | No. of Man-days:
BABAK | Kinawitnon | 2nd Eng'g. Dist. | On-going | 2018-03-12 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) LS - P9,000,000.00 | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: | 933418.8 | Actual: | 75%
BABAK | Kinawitnon | 2nd Eng'g. Dist. | On-going | 2018-03-12 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) LS - P9,000,000.00 | [7 empty] | Duration: | 100 | No. of days extended: |  |  |  | Slippage: | 7%
BABAK | Kinawitnon | 2nd Eng'g. Dist. | On-going | 2018-03-12 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) LS - P9,000,000.00 | [7 empty] | Date Allotment Released: | 2017-09-19 | Date completed:
BABAK | Kinawitnon | 2nd Eng'g. Dist. | On-going | 2018-03-12 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) LS - P9,000,000.00 | [7 empty] | Date Started: | 2018-03-12
Panabo City | Consolacion | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) LS - P9,000,000.00 | Const of Market Stall/Building, Consolacion, Panabo City |  | 20% DF CY 2017 (STIMULUS) | Building |  |  | MLGU | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Issued warning for Termination of the Contract
Panabo City | Consolacion | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) LS - P9,000,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Panabo City | Consolacion | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) LS - P9,000,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Panabo City | Consolacion | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) LS - P9,000,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Panabo City | Consolacion | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) LS - P9,000,000.00 | [7 empty] | Date Allotment Released: | 2017-12-28 | Date completed:
Panabo City | Consolacion | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) LS - P9,000,000.00 | [7 empty] | Date Started:
Panabo City | Upper Licanan | 2nd Eng'g. Dist. | On-going | 2017-12-28 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) LS - P9,000,000.00 | Rehab. Of Multi-Purpose Hall (Covered Court), Upper Licanan, Panabo City |  | 20% DF CY 2017 (STIMULUS) | Building |  |  | MLGU | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Fund transfer to LGU- 3/28/2019 with check no.2574927 and OR no. 0166516 - Delivery of Materials on process
Panabo City | Upper Licanan | 2nd Eng'g. Dist. | On-going | 2017-12-28 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) LS - P9,000,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Panabo City | Upper Licanan | 2nd Eng'g. Dist. | On-going | 2017-12-28 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) LS - P9,000,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Panabo City | Upper Licanan | 2nd Eng'g. Dist. | On-going | 2017-12-28 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) LS - P9,000,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Panabo City | Upper Licanan | 2nd Eng'g. Dist. | On-going | 2017-12-28 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) LS - P9,000,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Panabo City | Upper Licanan | 2nd Eng'g. Dist. | On-going | 2017-12-28 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) LS - P9,000,000.00 | [7 empty] | Date Started: | 2017-12-28
Panabo City | Kauswagan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) LS - P9,000,000.00 | Impv't. of Multi-Purpose Gym, Kauswagan, Panabo City |  | 20% DF CY 2017 (STIMULUS) | GYM |  |  | MLGU | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Fund transfer to LGU- 3/28/2019 with check no.2574942 and OR no. 0166515 - procurement on process for bidding 8/5/2019
Panabo City | Kauswagan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) LS - P9,000,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Panabo City | Kauswagan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) LS - P9,000,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Panabo City | Kauswagan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) LS - P9,000,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Panabo City | Kauswagan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) LS - P9,000,000.00 | [7 empty] | Date Allotment Released: | 2019-02-04 | Date completed:
Panabo City | Kauswagan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) LS - P9,000,000.00 | [7 empty] | Date Started:
Panabo City | Cacao | 2nd Eng'g. Dist. | On-going | 2018-12-14 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) LS - P9,000,000.00 | Const. of Multi-Purpose Bldg.,Cacao, Panabo City |  | 20% DF CY 2017 (STIMULUS) | Building |  | sq.m | MLGU | Project Cost: | 300000 | Target Completion Date: |  | Program: | 300000 | Planned: |  | No. of Persons: |  | Issued warning for termination of the contract
Panabo City | Cacao | 2nd Eng'g. Dist. | On-going | 2018-12-14 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) LS - P9,000,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 300000 | Revised: |  | No. of Man-days:
Panabo City | Cacao | 2nd Eng'g. Dist. | On-going | 2018-12-14 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) LS - P9,000,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Panabo City | Cacao | 2nd Eng'g. Dist. | On-going | 2018-12-14 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) LS - P9,000,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Panabo City | Cacao | 2nd Eng'g. Dist. | On-going | 2018-12-14 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) LS - P9,000,000.00 | [7 empty] | Date Allotment Released: | 2017-12-19 | Date completed:
Panabo City | Cacao | 2nd Eng'g. Dist. | On-going | 2018-12-14 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) LS - P9,000,000.00 | [7 empty] | Date Started: | 2018-12-14
Panabo City | A.O. Floreindo | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) LS - P9,000,000.00 | Const. of Multi-Purpose Bldg. @ A.O. Floriendo National Highschool, Panabo City |  | 20% DF CY 2017 (STIMULUS) | Building |  |  | MLGU | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Fund transfer to LGU- 3/28/2019 with check no. 2574939 and OR no. 0166518 - Materials Delivered. Construction on-going
Panabo City | A.O. Floreindo | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) LS - P9,000,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Panabo City | A.O. Floreindo | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) LS - P9,000,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Panabo City | A.O. Floreindo | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) LS - P9,000,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Panabo City | A.O. Floreindo | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) LS - P9,000,000.00 | [7 empty] | Date Allotment Released: | 2017-12-19 | Date completed:
Panabo City | A.O. Floreindo | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) LS - P9,000,000.00 | [7 empty] | Date Started:
Panabo City | Kimamon | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Drainage | Const. of Concrete Drainage Canal, Kimamon, Panabo City |  | 20% DF CY 2017 (STIMULUS) | Drainage |  |  | MLGU | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | For Implementation
Panabo City | Kimamon | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Drainage | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Panabo City | Kimamon | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Drainage | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Panabo City | Kimamon | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Drainage | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Panabo City | Kimamon | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Drainage | [7 empty] | Date Allotment Released: | 2017-12-19 | Date completed:
Panabo City | Kimamon | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Drainage | [7 empty] | Date Started:
IGCS | Anonang | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | RURAL ELECTRIFICATION PROJECT | Impv't. of Brgy. Street Electrification at Brgy. Anonang, IGCS |  | 20% DF CY 2017 (STIMULUS) | Electrification |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Verified at PBO 7/18/2019 that fund is not available. Proposed priority project for 2020.
IGCS | Anonang | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | RURAL ELECTRIFICATION PROJECT | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
IGCS | Anonang | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | RURAL ELECTRIFICATION PROJECT | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual:
IGCS | Anonang | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | RURAL ELECTRIFICATION PROJECT | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
IGCS | Anonang | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | RURAL ELECTRIFICATION PROJECT | [7 empty] | Date Allotment Released: | 2017-11-28 | Date completed:
IGCS | Anonang | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | RURAL ELECTRIFICATION PROJECT | [7 empty] | Date Started:
Panabo City | Datu Abdul | 2nd Eng'g. Dist. | On-going | 2019-11-21 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPPAP-PAMANA | Const. of Trading Post, Storage Building with (1) unit Hauling Truck, Prk. Ramihan Datu Abdul, Panabo City |  | OPPAP-PAMANA CY 2017 | Building |  | sq.m | Contract | Project Cost: | 3975000 | Target Completion Date: | 2020-04-05 23:59 | Program: | 3975000 | Planned: | 100% | No. of Persons: | 10 | On-going
Panabo City | Datu Abdul | 2nd Eng'g. Dist. | On-going | 2019-11-21 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPPAP-PAMANA | [7 empty] | Project Engineer: | Azotes | Revised Completion Date: | 2020-05-16 23:59 | Allotment: | 3975000 | Revised: | 40.36% | No. of Man-days: | 260
Panabo City | Datu Abdul | 2nd Eng'g. Dist. | On-going | 2019-11-21 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPPAP-PAMANA | [7 empty] | Implementor: | Ultra Core | No. of days suspended: | 41 | Disbursement: |  | Actual: | 40.36%
Panabo City | Datu Abdul | 2nd Eng'g. Dist. | On-going | 2019-11-21 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPPAP-PAMANA | [7 empty] | Duration: | 137 | No. of days extended: |  |  |  | Slippage: | 0%
Panabo City | Datu Abdul | 2nd Eng'g. Dist. | On-going | 2019-11-21 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPPAP-PAMANA | [7 empty] | Date Allotment Released: | CY 2017 | Date completed:
Panabo City | Datu Abdul | 2nd Eng'g. Dist. | On-going | 2019-11-21 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPPAP-PAMANA | [7 empty] | Date Started: | 2019-11-21
Samal | Kinawitnon | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPPAP-PAMANA | Trading Post, Storage and Hauling Truck Libuak, Island Garden City of Samal (IGACOS) |  | OPPAP-PAMANA CY 2017 | Building |  |  |  | Project Cost: | 4000000 | Target Completion Date: |  | Program: | 4000000 | Planned: |  | No. of Persons: |  | For bidding
Samal | Kinawitnon | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPPAP-PAMANA | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 4000000 | Revised: |  | No. of Man-days:
Samal | Kinawitnon | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPPAP-PAMANA | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Samal | Kinawitnon | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPPAP-PAMANA | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Samal | Kinawitnon | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPPAP-PAMANA | [7 empty] | Date Allotment Released: | CY 2018 | Date completed:
Samal | Kinawitnon | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPPAP-PAMANA | [7 empty] | Date Started:
IGCS | Tambo | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPPAP-PAMANA | Agricultural Productivity Support Project-Fishing Equipment, Tambo, IGACOS |  | OPPAP-PAMANA CY 2017 |  |  |  |  | Project Cost: | 1500000 | Target Completion Date: |  | Program: | 1500000 | Planned: |  | No. of Persons: |  | For bidding
IGCS | Tambo | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPPAP-PAMANA | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 1500000 | Revised: |  | No. of Man-days:
IGCS | Tambo | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPPAP-PAMANA | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
IGCS | Tambo | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPPAP-PAMANA | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
IGCS | Tambo | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPPAP-PAMANA | [7 empty] | Date Allotment Released: |  | Date completed:
IGCS | Tambo | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPPAP-PAMANA | [7 empty] | Date Started:
Carmen | Asuncion | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Construction of Water System Projects in Component LGUs LS - 9,750,000.00 | Rehab./Impv't. of San Vicente Water System, Asuncion |  | 20% DF CY 2018 | Water System |  |  | Admin | Project Cost: | 1125000 | Target Completion Date: |  | Program: | 1125000 | Planned: |  | No. of Persons: |  | Abstract # 0220190484
Carmen | Asuncion | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Construction of Water System Projects in Component LGUs LS - 9,750,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 1125000 | Revised: |  | No. of Man-days:
Carmen | Asuncion | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Construction of Water System Projects in Component LGUs LS - 9,750,000.00 | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual:
Carmen | Asuncion | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Construction of Water System Projects in Component LGUs LS - 9,750,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Carmen | Asuncion | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Construction of Water System Projects in Component LGUs LS - 9,750,000.00 | [7 empty] | Date Allotment Released: | 2018-10-26 | Date completed:
Carmen | Asuncion | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Construction of Water System Projects in Component LGUs LS - 9,750,000.00 | [7 empty] | Date Started:
Panabo City | Malativas | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Construction of Water System Projects in Component LGUs LS - 9,750,000.00 | Water System at brgy. Malativas, Panabo City |  | 20% DF CY 2018 | Water System |  |  | Admin | Project Cost: | 1250000 | Target Completion Date: |  | Program: | 1250000 | Planned: |  | No. of Persons: |  | For preparation of POW & Plan c/o PDPM - POSSIBLE TRANSFER OF SITE SUBJECT FOR TRANSFER OF LOCATION . NO DEED OF DONATION
Panabo City | Malativas | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Construction of Water System Projects in Component LGUs LS - 9,750,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 1250000 | Revised: |  | No. of Man-days:
Panabo City | Malativas | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Construction of Water System Projects in Component LGUs LS - 9,750,000.00 | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual:
Panabo City | Malativas | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Construction of Water System Projects in Component LGUs LS - 9,750,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Panabo City | Malativas | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Construction of Water System Projects in Component LGUs LS - 9,750,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Panabo City | Malativas | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Construction of Water System Projects in Component LGUs LS - 9,750,000.00 | [7 empty] | Date Started:
Panabo City | Tibungol | 2nd Eng'g. Dist. | On-going | 2020-01-20 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Construction of Water System Projects in Component LGUs LS - 9,750,000.00 | Const. of Potable Water System at Brgy. Tibungol, Panabo City |  | 20% DF CY 2018 | Water System |  | ln.m | Admin | Project Cost: | 1250000 | Target Completion Date: | 2020-04-15 23:59 | Program: | 1250000 | Planned: | 2.13% | No. of Persons: | 3 | Suspended dated February 19, 2020 undelivered hardware materials (Supplier refused to deliver. Letter already submitted to BAC.)
Panabo City | Tibungol | 2nd Eng'g. Dist. | On-going | 2020-01-20 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Construction of Water System Projects in Component LGUs LS - 9,750,000.00 | [7 empty] | Project Engineer: | Andoy | Revised Completion Date: |  | Allotment: | 1250000 | Revised: |  | No. of Man-days: | 15
Panabo City | Tibungol | 2nd Eng'g. Dist. | On-going | 2020-01-20 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Construction of Water System Projects in Component LGUs LS - 9,750,000.00 | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: | 0.76%
Panabo City | Tibungol | 2nd Eng'g. Dist. | On-going | 2020-01-20 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Construction of Water System Projects in Component LGUs LS - 9,750,000.00 | [7 empty] | Duration: | 87 | No. of days extended: |  |  |  | Slippage: | -1.37%
Panabo City | Tibungol | 2nd Eng'g. Dist. | On-going | 2020-01-20 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Construction of Water System Projects in Component LGUs LS - 9,750,000.00 | [7 empty] | Date Allotment Released: | 2018-11-21 | Date completed:
Panabo City | Tibungol | 2nd Eng'g. Dist. | On-going | 2020-01-20 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Construction of Water System Projects in Component LGUs LS - 9,750,000.00 | [7 empty] | Date Started: | 2020-01-20
Samal, Kaputian | San Remegio | 2nd Eng'g. Dist. | On-going | 2019-07-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Construction of Water System Projects in Component LGUs LS - 9,750,000.00 | Potable Water System at Brgy. San Remegio Kaputian (Level II WS), Samal |  | 20% DF CY 2018 | Water System |  |  | Admin | Project Cost: | 3625000 | Target Completion Date: | 2020-02-01 | Program: | 3625000 | Planned: | 100% | No. of Persons: | 4 | On-going/ Resumption 5/4/2020
Samal, Kaputian | San Remegio | 2nd Eng'g. Dist. | On-going | 2019-07-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Construction of Water System Projects in Component LGUs LS - 9,750,000.00 | [7 empty] | Project Engineer: | Kabigue | Revised Completion Date: | 2020-04-30 | Allotment: | 3625000 | Revised: | 72.04% | No. of Man-days: | 88
Samal, Kaputian | San Remegio | 2nd Eng'g. Dist. | On-going | 2019-07-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Construction of Water System Projects in Component LGUs LS - 9,750,000.00 | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: | 2702800 | Actual: | 74.56%
Samal, Kaputian | San Remegio | 2nd Eng'g. Dist. | On-going | 2019-07-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Construction of Water System Projects in Component LGUs LS - 9,750,000.00 | [7 empty] | Duration: | 200 | No. of days extended: | 89 |  |  | Slippage: | 2.52%
Samal, Kaputian | San Remegio | 2nd Eng'g. Dist. | On-going | 2019-07-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Construction of Water System Projects in Component LGUs LS - 9,750,000.00 | [7 empty] | Date Allotment Released: | 2018-10-25 | Date completed:
Samal, Kaputian | San Remegio | 2nd Eng'g. Dist. | On-going | 2019-07-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Construction of Water System Projects in Component LGUs LS - 9,750,000.00 | [7 empty] | Date Started: | 2019-07-16
Carmen | San Isidro | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | Completion of Evacuation Center Building, San Isidro, Carmen |  | GENERAL FUND PROPER CY 2018 (STIMULUS) | Building |  | sq.m | Contract | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | On-going
Carmen | San Isidro | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | [7 empty] | Project Engineer: | Estorco | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Carmen | San Isidro | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | [7 empty] | Implementor: | RLHV | No. of days suspended: |  | Disbursement: |  | Actual:
Carmen | San Isidro | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | [7 empty] | Duration: | 60 | No. of days extended: |  |  |  | Slippage: | 0%
Carmen | San Isidro | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | [7 empty] | Date Allotment Released: |  | Date completed:
Carmen | San Isidro | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | [7 empty] | Date Started:
Panabo City | Nanyo | 2nd Eng'g. Dist. | On-going | 2020-04-07 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | Const. of Perimeter Fence of Day Care Center 1, Nanyo, Panabo City |  | GENERAL FUND PROPER CY 2018 (STIMULUS) | Building |  | sq.m | Contract | Project Cost: | 500000 | Target Completion Date: | 2020-06-06 | Program: | 500000 | Planned: | 5% | No. of Persons: |  | (RLHV Design & Build) Winning Bidder
Panabo City | Nanyo | 2nd Eng'g. Dist. | On-going | 2020-04-07 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | [7 empty] | Project Engineer: | Estorco | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Panabo City | Nanyo | 2nd Eng'g. Dist. | On-going | 2020-04-07 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | [7 empty] | Implementor: | RLHV | No. of days suspended: |  | Disbursement: |  | Actual: | 5%
Panabo City | Nanyo | 2nd Eng'g. Dist. | On-going | 2020-04-07 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | [7 empty] | Duration: | 60 | No. of days extended: |  |  |  | Slippage: | 0%
Panabo City | Nanyo | 2nd Eng'g. Dist. | On-going | 2020-04-07 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | [7 empty] | Date Allotment Released: |  | Date completed:
Panabo City | Nanyo | 2nd Eng'g. Dist. | On-going | 2020-04-07 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | [7 empty] | Date Started: | 2020-04-07
Panabo City | Malativas | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | Impv't. of Brgy. Road Covered Court, Malativas, Panabo City |  | GENERAL FUND PROPER CY 2018 (STIMULUS) | Court |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Procurement on process
Panabo City | Malativas | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Panabo City | Malativas | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Panabo City | Malativas | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Panabo City | Malativas | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | [7 empty] | Date Allotment Released: |  | Date completed:
Panabo City | Malativas | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | [7 empty] | Date Started:
Panabo City | Maduao | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | Rehab. Of Multi-Purpose Gym & Facililies Maduao, Panabo City |  | GENERAL FUND PROPER CY 2018 (STIMULUS) | Gym |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Post qualification on process
Panabo City | Maduao | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Panabo City | Maduao | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Panabo City | Maduao | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Panabo City | Maduao | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | [7 empty] | Date Allotment Released: |  | Date completed:
Panabo City | Maduao | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | [7 empty] | Date Started:
Panabo City | Sto. Niño | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | Const. of Multi-Purpose Bldg. Sto. Nino, Panabo City |  | GENERAL FUND PROPER CY 2018 (STIMULUS) | Court |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | PR # 20032818
Panabo City | Sto. Niño | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Panabo City | Sto. Niño | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Panabo City | Sto. Niño | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Panabo City | Sto. Niño | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | [7 empty] | Date Allotment Released: |  | Date completed:
Panabo City | Sto. Niño | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | [7 empty] | Date Started:
Panabo City | Dapco | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | Completion of Canopy at DAPCO Covered Court, Dapco, Panabo City |  | GENERAL FUND PROPER CY 2018 (STIMULUS) | Court |  |  | Contract | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | (RLHV Design & Build) Winning Bidder
Panabo City | Dapco | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | [7 empty] | Project Engineer: | RLHV | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Panabo City | Dapco | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Panabo City | Dapco | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Panabo City | Dapco | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | [7 empty] | Date Allotment Released: |  | Date completed:
Panabo City | Dapco | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | [7 empty] | Date Started:
Panabo City | Nanyo | 2nd Eng'g. Dist. | On-going | 2020-04-07 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | Perimeter Fence of Day Care Center I & II, Nanyo, Panabo City/ Construction of Perimeter Fence) |  | GENERAL FUND PROPER CY 2018 (STIMULUS) | Building |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | For implementation (RLHV Design & Build) Winning Bidder
Panabo City | Nanyo | 2nd Eng'g. Dist. | On-going | 2020-04-07 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Panabo City | Nanyo | 2nd Eng'g. Dist. | On-going | 2020-04-07 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Panabo City | Nanyo | 2nd Eng'g. Dist. | On-going | 2020-04-07 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Panabo City | Nanyo | 2nd Eng'g. Dist. | On-going | 2020-04-07 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | [7 empty] | Date Allotment Released: |  | Date completed:
Panabo City | Nanyo | 2nd Eng'g. Dist. | On-going | 2020-04-07 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | [7 empty] | Date Started:
IGCS | Pichon | 2nd Eng'g. Dist. | On-going | 2020-01-13 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | Impv't. of Brgy. Water System, Pichon, IGCS (Construction of Elevated Tank) |  | GENERAL FUND PROPER CY 2018 (STIMULUS) | Water System |  |  | Admin | Project Cost: | 500000 | Target Completion Date: | 2020-03-13 | Program: | 500000 | Planned: | 100% | No. of Persons: | 5 | On-going
IGCS | Pichon | 2nd Eng'g. Dist. | On-going | 2020-01-13 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | [7 empty] | Project Engineer: | Andoy | Revised Completion Date: | 2020-07-31 | Allotment: | 500000 | Revised: | 86% | No. of Man-days: | 110
IGCS | Pichon | 2nd Eng'g. Dist. | On-going | 2020-01-13 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | [7 empty] | Implementor: | PEO | No. of days suspended: | 140 | Disbursement: | 423575.63 | Actual: | 83.5%
IGCS | Pichon | 2nd Eng'g. Dist. | On-going | 2020-01-13 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | [7 empty] | Duration: | 60 | No. of days extended: |  |  |  | Slippage: | -2.5%
IGCS | Pichon | 2nd Eng'g. Dist. | On-going | 2020-01-13 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | [7 empty] | Date Allotment Released: | 2018-05-31 | Date completed:
IGCS | Pichon | 2nd Eng'g. Dist. | On-going | 2020-01-13 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | [7 empty] | Date Started: | 2020-01-13
IGCS | Cogon | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | Powerline Expansion Project, Cogon, IGACOS |  | GENERAL FUND PROPER CY 2018 (STIMULUS) | Water System |  |  | Contract | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Waiting for NTP (3E Electrical)
IGCS | Cogon | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
IGCS | Cogon | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
IGCS | Cogon | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
IGCS | Cogon | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | [7 empty] | Date Allotment Released: |  | Date completed:
IGCS | Cogon | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | [7 empty] | Date Started:
IGCS | Tagbay | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | Water System From Prk. 6 - Prk. 2 - Prk. 5A, Tagbay, IGCS |  | GENERAL FUND PROPER CY 2018 (STIMULUS) | Water System |  |  | Admin | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | For Implementation
IGCS | Tagbay | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
IGCS | Tagbay | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
IGCS | Tagbay | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
IGCS | Tagbay | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | [7 empty] | Date Allotment Released: |  | Date completed:
IGCS | Tagbay | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | [7 empty] | Date Started:
IGCS | Tambo | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | RURAL ELECTRIFICATION PROJECT | Powerline Expansion Project, Tambo, IGCS |  | GENERAL FUND PROPER CY 2018 (STIMULUS) | Electrification |  |  | Contract | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Purchase Request # 19083312
IGCS | Tambo | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | RURAL ELECTRIFICATION PROJECT | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
IGCS | Tambo | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | RURAL ELECTRIFICATION PROJECT | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
IGCS | Tambo | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | RURAL ELECTRIFICATION PROJECT | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
IGCS | Tambo | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | RURAL ELECTRIFICATION PROJECT | [7 empty] | Date Allotment Released: |  | Date completed:
IGCS | Tambo | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | RURAL ELECTRIFICATION PROJECT | [7 empty] | Date Started:
IGCS | Peñaplata | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | Improvement of Barangay Hall, Penaplata, IGCS |  | GENERAL FUND PROPER CY 2018 (STIMULUS) | Building |  |  | Admin | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | By Contract and change to admin due to unforeseen activities because it’s a repair (For revision of POW)
IGCS | Peñaplata | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
IGCS | Peñaplata | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
IGCS | Peñaplata | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
IGCS | Peñaplata | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | [7 empty] | Date Allotment Released: |  | Date completed:
IGCS | Peñaplata | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | [7 empty] | Date Started:
IGCS | Dadatan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | RURAL ELECTRIFICATION PROJECT | Electrification of Sitio Baongon-Diamond-Mansanitas, Dadatan, IGCS |  | GENERAL FUND PROPER CY 2018 (STIMULUS) | Electrification |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Purchase Order # 20200100002 (3E Electrical Sales & Services)
IGCS | Dadatan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | RURAL ELECTRIFICATION PROJECT | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
IGCS | Dadatan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | RURAL ELECTRIFICATION PROJECT | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
IGCS | Dadatan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | RURAL ELECTRIFICATION PROJECT | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
IGCS | Dadatan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | RURAL ELECTRIFICATION PROJECT | [7 empty] | Date Allotment Released: |  | Date completed:
IGCS | Dadatan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | RURAL ELECTRIFICATION PROJECT | [7 empty] | Date Started:
IGCS | Linusotan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Construction of Water System Projects in Component LGUs | Drilling of Water System, Linusotan, IGCS |  | GENERAL FUND PROPER CY 2018 (STIMULUS) | Water System |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
IGCS | Linusotan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Construction of Water System Projects in Component LGUs | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
IGCS | Linusotan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Construction of Water System Projects in Component LGUs | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
IGCS | Linusotan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Construction of Water System Projects in Component LGUs | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
IGCS | Linusotan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Construction of Water System Projects in Component LGUs | [7 empty] | Date Allotment Released: |  | Date completed:
IGCS | Linusotan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Construction of Water System Projects in Component LGUs | [7 empty] | Date Started:
Carmen | Ising | 2nd Eng'g. Dist. | On-going | 2020-03-19 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | Const. of DDN Hospital Carmen Zone Annex Bldg. |  | SB # 1 CY 2018 | Building |  | sq.m | Contract | Project Cost: | 5500000 | Target Completion Date: | 2020-07-17 | Program: | 5500000 | Planned: | 95.2% | No. of Persons: | 10 | On-going
Carmen | Ising | 2nd Eng'g. Dist. | On-going | 2020-03-19 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | [7 empty] | Project Engineer: | Azotes | Revised Completion Date: | 2020-09-12 | Allotment: | 5500000 | Revised: | 40.5% | No. of Man-days: | 260
Carmen | Ising | 2nd Eng'g. Dist. | On-going | 2020-03-19 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | [7 empty] | Implementor: | Digos Constrak Corp/ | No. of days suspended: | 57 | Disbursement: | 1650000 | Actual: | 68.25%
Carmen | Ising | 2nd Eng'g. Dist. | On-going | 2020-03-19 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | [7 empty] | Duration: | 120 | No. of days extended: |  |  |  | Slippage: | 27.75%
Carmen | Ising | 2nd Eng'g. Dist. | On-going | 2020-03-19 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | [7 empty] | Date Allotment Released: |  | Date completed:
Carmen | Ising | 2nd Eng'g. Dist. | On-going | 2020-03-19 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | [7 empty] | Date Started: | 2020-03-19
Carmen | Cebulano | 2nd Eng'g. Dist. | Completed | 2019-05-21 | 2020-05-31 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | Road ID11 Jct. Highway Sto. Niño - Cebulano |  | 20% DF CY 2019 | Road Rehabilitation | 2.09 | km | Admin | Project Cost: | 1045000 | Target Completion Date: | 2019-10-04 | Program: | 1045000 | Planned: | 100% | No. of Persons: | 6 | Completed as per physical accomplishment. Financial documents still on process.
Carmen | Cebulano | 2nd Eng'g. Dist. | Completed | 2019-05-21 | 2020-05-31 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | [7 empty] | Project Engineer: | Obar/ Nasol | Revised Completion Date: | 2020-06-15 | Allotment: | 1045000 | Revised: |  | No. of Man-days: | 132
Carmen | Cebulano | 2nd Eng'g. Dist. | Completed | 2019-05-21 | 2020-05-31 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | [7 empty] | Implementor: | PEO | No. of days suspended: | 194 | Disbursement: | 1045000 | Actual: | 100%
Carmen | Cebulano | 2nd Eng'g. Dist. | Completed | 2019-05-21 | 2020-05-31 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | [7 empty] | Duration: | 136 | No. of days extended: | 61 |  |  | Slippage: | 0%
Carmen | Cebulano | 2nd Eng'g. Dist. | Completed | 2019-05-21 | 2020-05-31 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | [7 empty] | Date Allotment Released: | 2019-01-03 | Date completed: | 2020-05-31
Carmen | Cebulano | 2nd Eng'g. Dist. | Completed | 2019-05-21 | 2020-05-31 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | [7 empty] | Date Started: | 2019-05-21
Carmen | Tubod | 2nd Eng'g. Dist. | Completed | 2019-11-11 | 2020-06-30 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | ROAD ID 076 - Basa - Tubod |  | 20% DF CY 2019 | Road Rehabilitation | 1.56 | km | Admin | Project Cost: | 1000000 | Target Completion Date: | 2020-03-19 23:59 | Program: | 1000000 | Planned: | 100% | No. of Persons: | 3 | Completed as per physical accomplishment. Financial documents still on process.
Carmen | Tubod | 2nd Eng'g. Dist. | Completed | 2019-11-11 | 2020-06-30 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | [7 empty] | Project Engineer: | PIAD | Revised Completion Date: | 2020-06-30 23:59 | Allotment: | 1000000 | Revised: | 100% | No. of Man-days: | 30
Carmen | Tubod | 2nd Eng'g. Dist. | Completed | 2019-11-11 | 2020-06-30 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | [7 empty] | Implementor: | PEO | No. of days suspended: | 103 | Disbursement: |  | Actual: | 100%
Carmen | Tubod | 2nd Eng'g. Dist. | Completed | 2019-11-11 | 2020-06-30 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | [7 empty] | Duration: | 130 | No. of days extended: |  |  |  | Slippage: | 0%
Carmen | Tubod | 2nd Eng'g. Dist. | Completed | 2019-11-11 | 2020-06-30 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | [7 empty] | Date Allotment Released: | 2019-01-03 | Date completed: | 2020-06-30 23:59
Carmen | Tubod | 2nd Eng'g. Dist. | Completed | 2019-11-11 | 2020-06-30 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | [7 empty] | Date Started: | 2019-11-11
Carmen | Tubod | 2nd Eng'g. Dist. | On-going | 2019-12-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | ROAD ID 077 - Tubod - Pilar |  | 20% DF CY 2019 | Road Rehabilitation | 1.55 | km | Admin | Project Cost: | 16000000 | Target Completion Date: | 2020-11-05 | Program: | 16000000 | Planned: | 62.5% | No. of Persons: | 20 | On-going
Carmen | Tubod | 2nd Eng'g. Dist. | On-going | 2019-12-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | [7 empty] | Project Engineer: | Agang | Revised Completion Date: |  | Allotment: | 16000000 | Revised: |  | No. of Man-days: | 600
Carmen | Tubod | 2nd Eng'g. Dist. | On-going | 2019-12-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: | 4046971.2 | Actual: | 58.23%
Carmen | Tubod | 2nd Eng'g. Dist. | On-going | 2019-12-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | [7 empty] | Duration: | 323 | No. of days extended: |  |  |  | Slippage: | -4.27%
Carmen | Tubod | 2nd Eng'g. Dist. | On-going | 2019-12-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | [7 empty] | Date Allotment Released: | 2019-11-26 | Date completed:
Carmen | Tubod | 2nd Eng'g. Dist. | On-going | 2019-12-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | [7 empty] | Date Started: | 2019-12-18
Carmen | Tibulao | 2nd Eng'g. Dist. | On-going | 2019-11-11 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | ROAD ID 103 - Sitio Malaga - Tibulao |  | 20% DF CY 2019 | Road Rehabilitation | 3.22 | km | Admin | Project Cost: | 1000000 | Target Completion Date: | 2020-02-09 | Program: | 1000000 | Planned: | 78.5% | No. of Persons: | 5 | On-going
Carmen | Tibulao | 2nd Eng'g. Dist. | On-going | 2019-11-11 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | [7 empty] | Project Engineer: | Obar | Revised Completion Date: | 2020-06-30 | Allotment: | 1000000 | Revised: |  | No. of Man-days: | 110
Carmen | Tibulao | 2nd Eng'g. Dist. | On-going | 2019-11-11 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | [7 empty] | Implementor: | PEO | No. of days suspended: | 142 | Disbursement: |  | Actual: | 54.8%
Carmen | Tibulao | 2nd Eng'g. Dist. | On-going | 2019-11-11 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | [7 empty] | Duration: | 90 | No. of days extended: |  |  |  | Slippage: | -23.7%
Carmen | Tibulao | 2nd Eng'g. Dist. | On-going | 2019-11-11 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | [7 empty] | Date Allotment Released: | 2019-01-03 | Date completed:
Carmen | Tibulao | 2nd Eng'g. Dist. | On-going | 2019-11-11 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | [7 empty] | Date Started: | 2019-11-11
B.E. Dujali | Tanglaw | 2nd Eng'g. Dist. | On-going | 2019-12-28 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | ROAD ID 104 - Dujali - Tanglaw |  | 20% DF CY 2019 | Road Rehabilitation | 3.6 | km | Admin | Project Cost: | 2075000 | Target Completion Date: | 2020-04-16 | Program: | 2075000 | Planned: | 60% | No. of Persons: | 11 | On-going
B.E. Dujali | Tanglaw | 2nd Eng'g. Dist. | On-going | 2019-12-28 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | [7 empty] | Project Engineer: | Balbastro | Revised Completion Date: | 2020-08-30 | Allotment: | 2075000 | Revised: |  | No. of Man-days: | 77
B.E. Dujali | Tanglaw | 2nd Eng'g. Dist. | On-going | 2019-12-28 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | [7 empty] | Implementor: | PEO | No. of days suspended: | 28 | Disbursement: |  | Actual: | 65%
B.E. Dujali | Tanglaw | 2nd Eng'g. Dist. | On-going | 2019-12-28 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | [7 empty] | Duration: | 110 | No. of days extended: | 108 |  |  | Slippage: | 5%
B.E. Dujali | Tanglaw | 2nd Eng'g. Dist. | On-going | 2019-12-28 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | [7 empty] | Date Allotment Released: | 2019-01-03 | Date completed:
B.E. Dujali | Tanglaw | 2nd Eng'g. Dist. | On-going | 2019-12-28 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | [7 empty] | Date Started: | 2019-12-28
Sto. Tomas | Libertad | 2nd Eng'g. Dist. | On-going | 2019-06-17 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | ROAD ID 121 - San Miguel - Libertad |  | 20% DF CY 2019 | Road Rehabilitation | 6.2 | km | Admin | Project Cost: | 1240000 | Target Completion Date: | 2019-10-31 | Program: | 1240000 | Planned: | 59.41% | No. of Persons: | 9 | On-going
Sto. Tomas | Libertad | 2nd Eng'g. Dist. | On-going | 2019-06-17 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | [7 empty] | Project Engineer: | Gamad | Revised Completion Date: | 2020-02-29 | Allotment: | 1240000 | Revised: |  | No. of Man-days: | 36
Sto. Tomas | Libertad | 2nd Eng'g. Dist. | On-going | 2019-06-17 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | [7 empty] | Implementor: | PEO | No. of days suspended: | 86 | Disbursement: |  | Actual: | 59.41%
Sto. Tomas | Libertad | 2nd Eng'g. Dist. | On-going | 2019-06-17 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | [7 empty] | Duration: | 136 | No. of days extended: | 35 |  |  | Slippage: | 0%
Sto. Tomas | Libertad | 2nd Eng'g. Dist. | On-going | 2019-06-17 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | [7 empty] | Date Allotment Released: | 2019-01-03 | Date completed:
Sto. Tomas | Libertad | 2nd Eng'g. Dist. | On-going | 2019-06-17 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | [7 empty] | Date Started: | 2019-06-17
Sto. Tomas | Casig-ang | 2nd Eng'g. Dist. | On-going | 2019-06-27 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | ROAD ID 123 - Bacali - Casig-ang - Libertad |  | 20% DF CY 2019 | Road Rehabilitation | 4.7 | km | Admin | Project Cost: | 940000 | Target Completion Date: | 2019-09-15 | Program: | 940000 | Planned: | 62.1% | No. of Persons: | 9 | On-going
Sto. Tomas | Casig-ang | 2nd Eng'g. Dist. | On-going | 2019-06-27 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | [7 empty] | Project Engineer: | Gamad | Revised Completion Date: | 2020-02-29 | Allotment: | 940000 | Revised: |  | No. of Man-days: | 36
Sto. Tomas | Casig-ang | 2nd Eng'g. Dist. | On-going | 2019-06-27 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | [7 empty] | Implementor: | PEO | No. of days suspended: | 132 | Disbursement: |  | Actual: | 62%
Sto. Tomas | Casig-ang | 2nd Eng'g. Dist. | On-going | 2019-06-27 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | [7 empty] | Duration: | 80 | No. of days extended: | 35 |  |  | Slippage: | -0.1%
Sto. Tomas | Casig-ang | 2nd Eng'g. Dist. | On-going | 2019-06-27 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | [7 empty] | Date Allotment Released: | 2019-06-07 | Date completed:
Sto. Tomas | Casig-ang | 2nd Eng'g. Dist. | On-going | 2019-06-27 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | [7 empty] | Date Started: | 2019-06-27
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | On-going | 2019-06-17 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | ROAD ID 125 - San Miguel - Moslog - Kinamayan |  | 20% DF CY 2019 | Road Rehabilitation | 2.9 | km | Admin | Project Cost: | 1000000 | Target Completion Date: | 2019-09-16 | Program: | 1000000 | Planned: | 100% | No. of Persons: | 6 | On-going
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | On-going | 2019-06-17 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | [7 empty] | Project Engineer: | Gamad | Revised Completion Date: | 2020-02-29 | Allotment: | 1000000 | Revised: | 73.59% | No. of Man-days: | 30
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | On-going | 2019-06-17 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | [7 empty] | Implementor: | PEO | No. of days suspended: | 137 | Disbursement: |  | Actual: | 80%
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | On-going | 2019-06-17 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | [7 empty] | Duration: | 91 | No. of days extended: | 29 |  |  | Slippage: | 6.41%
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | On-going | 2019-06-17 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | [7 empty] | Date Allotment Released: | 2019-05-20 | Date completed:
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | On-going | 2019-06-17 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | [7 empty] | Date Started: | 2019-06-17
Sto. Tomas | Katipunana | 2nd Eng'g. Dist. | On-going | 2019-12-27 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | ROAD ID 134 - New Katipunan - Pantaron |  | 20% DF CY 2019 | Road Rehabilitation | 1.96 | km | Admin | Project Cost: | 395000 | Target Completion Date: | 2020-02-25 | Program: | 395000 | Planned: | 60% | No. of Persons: | 4 | On-going
Sto. Tomas | Katipunana | 2nd Eng'g. Dist. | On-going | 2019-12-27 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | [7 empty] | Project Engineer: | Gamad/Clar | Revised Completion Date: |  | Allotment: | 395000 | Revised: |  | No. of Man-days: | 24
Sto. Tomas | Katipunana | 2nd Eng'g. Dist. | On-going | 2019-12-27 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: | 60%
Sto. Tomas | Katipunana | 2nd Eng'g. Dist. | On-going | 2019-12-27 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | [7 empty] | Duration: | 60 | No. of days extended: |  |  |  | Slippage: | 0%
Sto. Tomas | Katipunana | 2nd Eng'g. Dist. | On-going | 2019-12-27 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | [7 empty] | Date Allotment Released: | 2019-01-03 | Date completed:
Sto. Tomas | Katipunana | 2nd Eng'g. Dist. | On-going | 2019-12-27 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | [7 empty] | Date Started: | 2019-12-27
B.E. Dujali | Tanglaw | 2nd Eng'g. Dist. | On-going | 2019-06-17 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | ROAD ID 142 - Jct. Highway - Tanglaw |  | 20% DF CY 2019 | Road Rehabilitation | 3.98 | km | Admin | Project Cost: | 1100000 | Target Completion Date: | 2019-09-16 | Program: | 1100000 | Planned: | 100% | No. of Persons: | 10 | On-going
B.E. Dujali | Tanglaw | 2nd Eng'g. Dist. | On-going | 2019-06-17 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | [7 empty] | Project Engineer: | Gamad/Clar | Revised Completion Date: | 2020-02-29 | Allotment: | 1100000 | Revised: | 73.59% | No. of Man-days: | 50
B.E. Dujali | Tanglaw | 2nd Eng'g. Dist. | On-going | 2019-06-17 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | [7 empty] | Implementor: | PEO | No. of days suspended: | 137 | Disbursement: |  | Actual: | 85%
B.E. Dujali | Tanglaw | 2nd Eng'g. Dist. | On-going | 2019-06-17 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | [7 empty] | Duration: | 91 | No. of days extended: | 29 |  |  | Slippage: | 11.41%
B.E. Dujali | Tanglaw | 2nd Eng'g. Dist. | On-going | 2019-06-17 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | [7 empty] | Date Allotment Released: | 2019-05-16 | Date completed:
B.E. Dujali | Tanglaw | 2nd Eng'g. Dist. | On-going | 2019-06-17 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | [7 empty] | Date Started: | 2019-06-17
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | On-going | 2019-12-27 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | ROAD ID 146 - Bdry. Tagum - Crossing Kinamayan Sto. Tomas |  | 20% DF CY 2019 | Road Rehabilitation | 0.75 | km | Admin | Project Cost: | 3700000 | Target Completion Date: | 2020-04-25 | Program: | 3700000 | Planned: | 100% | No. of Persons: | 15 | On-going
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | On-going | 2019-12-27 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | [7 empty] | Project Engineer: | Gamad/Clar | Revised Completion Date: | 2020-08-23 | Allotment: | 3700000 | Revised: | 15.43% | No. of Man-days: | 225
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | On-going | 2019-12-27 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | [7 empty] | Implementor: |  | No. of days suspended: | 20 | Disbursement: |  | Actual: | 16.37%
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | On-going | 2019-12-27 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | [7 empty] | Duration: | 120 | No. of days extended: | 100 |  |  | Slippage: | 0.94%
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | On-going | 2019-12-27 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | [7 empty] | Date Allotment Released: | 2019-01-03 | Date completed:
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | On-going | 2019-12-27 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | [7 empty] | Date Started: | 2019-12-27
Sto. Tomas | San Jose | 2nd Eng'g. Dist. | On-going | 2020-05-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | Fr. Rd. 3 - San Jose |  | 20% DF CY 2019 | Road Rehabilitation | 4.55 | km | Admin | Project Cost: | 800000 | Target Completion Date: | 2020-08-06 | Program: | 800000 | Planned: | 2.14% | No. of Persons: | 3 | On-going
Sto. Tomas | San Jose | 2nd Eng'g. Dist. | On-going | 2020-05-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Project Engineer: | Obar | Revised Completion Date: |  | Allotment: | 800000 | Revised: |  | No. of Man-days: | 30
Sto. Tomas | San Jose | 2nd Eng'g. Dist. | On-going | 2020-05-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: | 2.14%
Sto. Tomas | San Jose | 2nd Eng'g. Dist. | On-going | 2020-05-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Duration: | 80 | No. of days extended: |  |  |  | Slippage: | 0%
Sto. Tomas | San Jose | 2nd Eng'g. Dist. | On-going | 2020-05-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Date Allotment Released: | 2019-01-03 | Date completed:
Sto. Tomas | San Jose | 2nd Eng'g. Dist. | On-going | 2020-05-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Date Started: | 2020-05-18
Carmen | Asuncion | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | Lower Asuncion - Upper Asuncion |  | 20% DF CY 2019 | Road Rehabilitation | 1.02 | km | Admin | Project Cost: |  | Target Completion Date: |  | Program: | 0 | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
Carmen | Asuncion | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 0 | Revised: |  | No. of Man-days:
Carmen | Asuncion | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Carmen | Asuncion | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Carmen | Asuncion | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Date Allotment Released: |  | Date completed:
Carmen | Asuncion | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Date Started:
Carmen | Mangalcal | 2nd Eng'g. Dist. | On-going | 2020-06-15 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | Jct. Highway - Carmen - Mangalcal - Tubod |  | 20% DF CY 2019 | Road Rehabilitation | 11.34 | km | Admin | Project Cost: | 1323000 | Target Completion Date: | 2020-07-15 | Program: | 1323000 | Planned: | 100% | No. of Persons: | 3 | On-going
Carmen | Mangalcal | 2nd Eng'g. Dist. | On-going | 2020-06-15 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Project Engineer: | Obar | Revised Completion Date: |  | Allotment: | 1323000 | Revised: |  | No. of Man-days: | 30
Carmen | Mangalcal | 2nd Eng'g. Dist. | On-going | 2020-06-15 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: | 1.21%
Carmen | Mangalcal | 2nd Eng'g. Dist. | On-going | 2020-06-15 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Duration: | 30 | No. of days extended: |  |  |  | Slippage: | -98.79%
Carmen | Mangalcal | 2nd Eng'g. Dist. | On-going | 2020-06-15 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Date Allotment Released: | 2019-01-03 | Date completed:
Carmen | Mangalcal | 2nd Eng'g. Dist. | On-going | 2020-06-15 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Date Started: | 2020-06-15
B.E. Dujali | Tuganay-Taba | 2nd Eng'g. Dist. | On-going | 2020-05-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | Tuganay - Taba |  | 20% DF CY 2019 | Road Rehabilitation | 4.27 | km | Admin | Project Cost: | 507500 | Target Completion Date: | 2020-06-17 | Program: | 507500 | Planned: | 100% | No. of Persons: | 3 | On-going
B.E. Dujali | Tuganay-Taba | 2nd Eng'g. Dist. | On-going | 2020-05-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Project Engineer: | Obar | Revised Completion Date: |  | Allotment: | 507500 | Revised: |  | No. of Man-days: | 30
B.E. Dujali | Tuganay-Taba | 2nd Eng'g. Dist. | On-going | 2020-05-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: | 3.37%
B.E. Dujali | Tuganay-Taba | 2nd Eng'g. Dist. | On-going | 2020-05-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Duration: | 30 | No. of days extended: |  |  |  | Slippage: | -96.63%
B.E. Dujali | Tuganay-Taba | 2nd Eng'g. Dist. | On-going | 2020-05-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Date Allotment Released: | 2019-01-03 | Date completed:
B.E. Dujali | Tuganay-Taba | 2nd Eng'g. Dist. | On-going | 2020-05-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Date Started: | 2020-05-18
B.E. Dujali | Ising | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | Jct. Highway - Ising - Magsaysay |  | 20% DF CY 2019 | Road Rehabilitation | 10.84 | km | Admin | Project Cost: | 6000000 | Target Completion Date: |  | Program: | 6000000 | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
B.E. Dujali | Ising | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 6000000 | Revised: |  | No. of Man-days:
B.E. Dujali | Ising | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
B.E. Dujali | Ising | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
B.E. Dujali | Ising | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Date Allotment Released: |  | Date completed:
B.E. Dujali | Ising | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Date Started:
B.E. Dujali | Guadalupe | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | Jct. Highway - Guadalupe - Bdry. Tagum |  | 20% DF CY 2019 | Road Rehabilitation | 7.9 | km | Admin | Project Cost: | 910000 | Target Completion Date: | 2020-08-06 | Program: | 910000 | Planned: | 2.04% | No. of Persons: | 3 | On-going
B.E. Dujali | Guadalupe | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Project Engineer: | Obar | Revised Completion Date: |  | Allotment: | 910000 | Revised: |  | No. of Man-days: | 30
B.E. Dujali | Guadalupe | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: | 2.04%
B.E. Dujali | Guadalupe | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Duration: | 80 | No. of days extended: |  |  |  | Slippage: | 0%
B.E. Dujali | Guadalupe | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Date Allotment Released: | 2019-01-03 | Date completed:
B.E. Dujali | Guadalupe | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Date Started: | 2020-05-18
Carmen | Tibulao | 2nd Eng'g. Dist. | On-going | 2020-05-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | Sitio Malaga - Tibulao |  | 20% DF CY 2019 | Road Rehabilitation | 3.22 | km | Admin | Project Cost: | 300000 | Target Completion Date: | 2020-08-06 | Program: | 300000 | Planned: | 3.37% | No. of Persons: | 3 | On-going
Carmen | Tibulao | 2nd Eng'g. Dist. | On-going | 2020-05-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Project Engineer: | Obar | Revised Completion Date: |  | Allotment: | 300000 | Revised: |  | No. of Man-days: | 30
Carmen | Tibulao | 2nd Eng'g. Dist. | On-going | 2020-05-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: | 3.37%
Carmen | Tibulao | 2nd Eng'g. Dist. | On-going | 2020-05-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Duration: | 80 | No. of days extended: |  |  |  | Slippage:
Carmen | Tibulao | 2nd Eng'g. Dist. | On-going | 2020-05-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Date Allotment Released: | 2019-01-03 | Date completed:
Carmen | Tibulao | 2nd Eng'g. Dist. | On-going | 2020-05-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Date Started: | 2020-05-18
Carmen | New Casay | 2nd Eng'g. Dist. | On-going | 2020-05-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | Prk. 5 RJS - Prk 6 New Casay |  | 20% DF CY 2019 | Road Rehabilitation | 2.73 | km | Admin | Project Cost: | 350000 | Target Completion Date: | 2020-06-17 | Program: | 350000 | Planned: | 3.37% | No. of Persons: | 3 | On-going
Carmen | New Casay | 2nd Eng'g. Dist. | On-going | 2020-05-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Project Engineer: | Obar | Revised Completion Date: |  | Allotment: | 350000 | Revised: |  | No. of Man-days: | 30
Carmen | New Casay | 2nd Eng'g. Dist. | On-going | 2020-05-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: | 3.37%
Carmen | New Casay | 2nd Eng'g. Dist. | On-going | 2020-05-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Duration: | 30 | No. of days extended: |  |  |  | Slippage: | 0%
Carmen | New Casay | 2nd Eng'g. Dist. | On-going | 2020-05-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Date Allotment Released: | 2019-01-03 | Date completed:
Carmen | New Casay | 2nd Eng'g. Dist. | On-going | 2020-05-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Date Started: | 2020-05-18
B.E. Dujali | San Vicente | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | Dujali - Pawas - San Vicente |  | 20% DF CY 2019 | Road Rehabilitation | 4.42 | km | Admin | Project Cost: | 525000 | Target Completion Date: | 2020-07-02 | Program: | 525000 | Planned: | 2.41% | No. of Persons: | 3 | On-going
B.E. Dujali | San Vicente | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Project Engineer: | Obar | Revised Completion Date: |  | Allotment: | 525000 | Revised: |  | No. of Man-days: | 30
B.E. Dujali | San Vicente | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: | 2.41%
B.E. Dujali | San Vicente | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Duration: | 45 | No. of days extended: |  |  |  | Slippage: | 0%
B.E. Dujali | San Vicente | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Date Allotment Released: | 2019-01-03 | Date completed:
B.E. Dujali | San Vicente | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Date Started: | 2020-05-18
Sto. Tomas | Esperanza | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | Los Amigos 1 - Esperanza - Los Amigos 2 |  | 20% DF CY 2019 | Road Rehabilitation | 3.59 | km | Admin | Project Cost: | 19200000 | Target Completion Date: |  | Program: | 19200000 | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
Sto. Tomas | Esperanza | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 19200000 | Revised: |  | No. of Man-days:
Sto. Tomas | Esperanza | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Sto. Tomas | Esperanza | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Sto. Tomas | Esperanza | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Date Allotment Released: |  | Date completed:
Sto. Tomas | Esperanza | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Date Started:
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | On-going | 2020-05-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | San Miguel - Crossing Kinamayan |  | 20% DF CY 2019 | Road Rehabilitation | 2.8 | km | Admin | Project Cost: | 350000 | Target Completion Date: | 2020-07-17 | Program: | 350000 | Planned: | 22.58% | No. of Persons: | 6 | On-going
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | On-going | 2020-05-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Project Engineer: | Piad/ Obar | Revised Completion Date: |  | Allotment: | 350000 | Revised: |  | No. of Man-days: | 84
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | On-going | 2020-05-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: | 22.58%
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | On-going | 2020-05-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Duration: | 60 | No. of days extended: |  |  |  | Slippage: | 0%
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | On-going | 2020-05-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Date Allotment Released: | 2019-01-03 | Date completed:
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | On-going | 2020-05-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Date Started: | 2020-05-18
Sto. Tomas | Magwawa | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | Fd Rd 2 - Sto. Tomas - Magwawa |  | 20% DF CY 2019 | Road Rehabilitation | 10.21 | km | Admin | Project Cost: |  | Target Completion Date: |  | Program: | 0 | Planned: |  | No. of Persons: |  | Plan and POW Approved
Sto. Tomas | Magwawa | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 0 | Revised: |  | No. of Man-days:
Sto. Tomas | Magwawa | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Sto. Tomas | Magwawa | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Sto. Tomas | Magwawa | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Date Allotment Released: |  | Date completed:
Sto. Tomas | Magwawa | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Date Started:
Sto. Tomas | Tulalian | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | Menzi - Balagunan - Tulalian |  | 20% DF CY 2019 | Road Rehabilitation | 10.63 | km | Admin | Project Cost: | 3720500 | Target Completion Date: |  | Program: | 3720500 | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
Sto. Tomas | Tulalian | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 3720500 | Revised: |  | No. of Man-days:
Sto. Tomas | Tulalian | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Sto. Tomas | Tulalian | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Sto. Tomas | Tulalian | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Date Allotment Released: |  | Date completed:
Sto. Tomas | Tulalian | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Date Started:
Sto. Tomas | Talomo | 2nd Eng'g. Dist. | On-going | 2020-05-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | Jct. Bdry. Tagum - Talomo |  | 20% DF CY 2019 | Road Rehabilitation | 12.01 | km | Admin | Project Cost: | 1400000 | Target Completion Date: | 2020-09-15 | Program: | 1400000 | Planned: | 3% | No. of Persons: | 3 | On-going
Sto. Tomas | Talomo | 2nd Eng'g. Dist. | On-going | 2020-05-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Project Engineer: | Obar | Revised Completion Date: |  | Allotment: | 1400000 | Revised: |  | No. of Man-days: | 30
Sto. Tomas | Talomo | 2nd Eng'g. Dist. | On-going | 2020-05-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: | 3.37%
Sto. Tomas | Talomo | 2nd Eng'g. Dist. | On-going | 2020-05-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Duration: | 120 | No. of days extended: |  |  |  | Slippage: | 0.37%
Sto. Tomas | Talomo | 2nd Eng'g. Dist. | On-going | 2020-05-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Date Allotment Released: | 2019-01-23 | Date completed:
Sto. Tomas | Talomo | 2nd Eng'g. Dist. | On-going | 2020-05-18 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Date Started: | 2020-05-18
Carmen | Anibongan | 2nd Eng'g. Dist. | Completed | 2019-05-22 | 2020-01-31 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | Rehab. of Anibongan-Salvacion-Cabay-angan Provincial Road with Drainage |  | 20% DF CY 2019 | Road Drainage rehabiliated |  | km | Admin | Project Cost: | 2000000 | Target Completion Date: | 2019-08-04 23:59 | Program: | 2000000 | Planned: | 100% | No. of Persons: | 1 | Completed as per physical accomplishment. Financial documents still on process.
Carmen | Anibongan | 2nd Eng'g. Dist. | Completed | 2019-05-22 | 2020-01-31 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Project Engineer: | Toquero | Revised Completion Date: | 2019-12-31 23:59 | Allotment: | 2000000 | Revised: |  | No. of Man-days: | 4
Carmen | Anibongan | 2nd Eng'g. Dist. | Completed | 2019-05-22 | 2020-01-31 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: | 100%
Carmen | Anibongan | 2nd Eng'g. Dist. | Completed | 2019-05-22 | 2020-01-31 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Duration: | 75 | No. of days extended: | 149 |  |  | Slippage: | 0%
Carmen | Anibongan | 2nd Eng'g. Dist. | Completed | 2019-05-22 | 2020-01-31 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Date Allotment Released: | 2019-01-14 | Date completed: | 2020-01-31
Carmen | Anibongan | 2nd Eng'g. Dist. | Completed | 2019-05-22 | 2020-01-31 | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Date Started: | 2019-05-22
B.E. Dujali | Dujali | 2nd Eng'g. Dist. | On-going | 2019-11-04 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various of Local Roads & Drainage Development Project (Provincewide) LS - 15,000,000.00 | Rehab. Of Dujali-Pawas-San Vicente Provincial Road |  | 20% DF CY 2019 | Road Drainage rehabiliated |  | km | Admin | Project Cost: | 2000000 | Target Completion Date: |  | Program: | 2000000 | Planned: | 80% | No. of Persons: |  | On-going
B.E. Dujali | Dujali | 2nd Eng'g. Dist. | On-going | 2019-11-04 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various of Local Roads & Drainage Development Project (Provincewide) LS - 15,000,000.00 | [7 empty] | Project Engineer: | Toquero | Revised Completion Date: |  | Allotment: | 2000000 | Revised: |  | No. of Man-days:
B.E. Dujali | Dujali | 2nd Eng'g. Dist. | On-going | 2019-11-04 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various of Local Roads & Drainage Development Project (Provincewide) LS - 15,000,000.00 | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: | 80%
B.E. Dujali | Dujali | 2nd Eng'g. Dist. | On-going | 2019-11-04 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various of Local Roads & Drainage Development Project (Provincewide) LS - 15,000,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
B.E. Dujali | Dujali | 2nd Eng'g. Dist. | On-going | 2019-11-04 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various of Local Roads & Drainage Development Project (Provincewide) LS - 15,000,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
B.E. Dujali | Dujali | 2nd Eng'g. Dist. | On-going | 2019-11-04 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various of Local Roads & Drainage Development Project (Provincewide) LS - 15,000,000.00 | [7 empty] | Date Started: | 2019-11-04
B.E. Dujali | Ising | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various of Local Roads & Drainage Development Project (Provincewide) LS - 15,000,000.00 | Rehab./Impv't. of Jct. highway Ising-Magsaysay Provincial Road with Drainage |  | 20% DF CY 2019 | Road Drainage rehabiliated |  | km | Admin | Project Cost: | 1500000 | Target Completion Date: |  | Program: | 1500000 | Planned: |  | No. of Persons: |  | Revised POW for approval - Jan. 7, 2020 Revision was made due to scarcity of boulders changing from stone masonry to concrete masonry
B.E. Dujali | Ising | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various of Local Roads & Drainage Development Project (Provincewide) LS - 15,000,000.00 | [7 empty] | Project Engineer: | Toquero | Revised Completion Date: |  | Allotment: | 1500000 | Revised: |  | No. of Man-days:
B.E. Dujali | Ising | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various of Local Roads & Drainage Development Project (Provincewide) LS - 15,000,000.00 | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual:
B.E. Dujali | Ising | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various of Local Roads & Drainage Development Project (Provincewide) LS - 15,000,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
B.E. Dujali | Ising | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various of Local Roads & Drainage Development Project (Provincewide) LS - 15,000,000.00 | [7 empty] | Date Allotment Released: | 2019-01-16 | Date completed:
B.E. Dujali | Ising | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various of Local Roads & Drainage Development Project (Provincewide) LS - 15,000,000.00 | [7 empty] | Date Started:
Panabo City | Consolacion | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | Impv't. of Potable Water System, Consolacion, Panabo City |  | 20% DF CY 2019 | Water System |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
Panabo City | Consolacion | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Panabo City | Consolacion | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Panabo City | Consolacion | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Panabo City | Consolacion | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | [7 empty] | Date Allotment Released: | 2019-06-28 | Date completed:
Panabo City | Consolacion | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | [7 empty] | Date Started:
Samal | Tagbitan-ag | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | Impv't. of Potable Water System, Tagbitan-ag, Samal Dist. |  | 20% DF CY 2019 | Water System |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | For implementation
Samal | Tagbitan-ag | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Samal | Tagbitan-ag | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Samal | Tagbitan-ag | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Samal | Tagbitan-ag | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | [7 empty] | Date Allotment Released: | 2019-06-19 | Date completed:
Samal | Tagbitan-ag | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | [7 empty] | Date Started:
Babak | San Antonio | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | Impv't. of Potable Water System, San Antonio, babak, IGCS |  | 20% DF CY 2019 | Water System |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
Babak | San Antonio | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Babak | San Antonio | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Babak | San Antonio | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Babak | San Antonio | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | [7 empty] | Date Allotment Released: | 2019-06-25 | Date completed:
Babak | San Antonio | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | [7 empty] | Date Started:
IGCS | Mambago | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | Impv't. of Potable Water System, Mambago-A, IGCS |  | 20% DF CY 2019 | Water System |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | For Implementation
IGCS | Mambago | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
IGCS | Mambago | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
IGCS | Mambago | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
IGCS | Mambago | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | [7 empty] | Date Allotment Released: | 2019-09-10 | Date completed:
IGCS | Mambago | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | [7 empty] | Date Started:
Panabo City | Buenavista | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | Construction of PWS, Brgy. Buenavista, Panabo City |  | 20% DF CY 2019 | Water System |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | For implementation
Panabo City | Buenavista | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Panabo City | Buenavista | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Panabo City | Buenavista | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Panabo City | Buenavista | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | [7 empty] | Date Allotment Released: | June 19 ,2019 | Date completed:
Panabo City | Buenavista | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | [7 empty] | Date Started:
Panabo City | Kiotoy | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | Construction of PWS, Brgy. Brgy. Kiotoy, Panabo City |  | 20% DF CY 2019 | Water System |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
Panabo City | Kiotoy | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Panabo City | Kiotoy | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Panabo City | Kiotoy | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Panabo City | Kiotoy | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Panabo City | Kiotoy | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | [7 empty] | Date Started:
IGCS | Linusotan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | Construction of PWS, Brgy. Linusotan, Talikud, District, IGCS |  | 20% DF CY 2019 | Water System |  |  |  | Project Cost: | 1300000 | Target Completion Date: |  | Program: | 1300000 | Planned: |  | No. of Persons: |  | Procurement on process
IGCS | Linusotan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 1300000 | Revised: |  | No. of Man-days:
IGCS | Linusotan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
IGCS | Linusotan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
IGCS | Linusotan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | [7 empty] | Date Allotment Released: | 2019-10-23 | Date completed:
IGCS | Linusotan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | [7 empty] | Date Started:
Babak, IGCS | San Miguel | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | Rehab. of PWS, Brgy. San Miguel, Babak, IGCS |  | 20% DF CY 2019 | Water System |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
Babak, IGCS | San Miguel | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Babak, IGCS | San Miguel | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Babak, IGCS | San Miguel | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Babak, IGCS | San Miguel | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Babak, IGCS | San Miguel | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | [7 empty] | Date Started:
Panabo City | Cacao | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | Construction of PWS, Brgy. Cacao, Panabo City |  | 20% DF CY 2019 | Water System |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | For cancellation. Purchase of Geo-resistivity equipment but procurement still on process
Panabo City | Cacao | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Panabo City | Cacao | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Panabo City | Cacao | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Panabo City | Cacao | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Panabo City | Cacao | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | [7 empty] | Date Started:
Kaputian, IGCS | Pangubatan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | Rehabilitation of Potable Water System, Brgy. Pangubatan, kaputian Dist. IGCS |  | 20% DF CY 2019 | Water System |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | For implementation
Kaputian, IGCS | Pangubatan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Kaputian, IGCS | Pangubatan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Kaputian, IGCS | Pangubatan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Kaputian, IGCS | Pangubatan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Kaputian, IGCS | Pangubatan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | [7 empty] | Date Started:
Carmen | Ising | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Government Buildings and Facilities Development Project (Provincewide) LS - P 27,000,000.00 | Const. of DDN Hospital Carmen Zone Annex Bldg. Phase 2, |  | 20% DF CY 2019 | Building |  | sq.m | Contract | Project Cost: | 3620000 | Target Completion Date: |  | Program: | 3620000 | Planned: |  | No. of Persons: |  | For implementation (Winning Bidder - Digos Constrak Corp.)
Carmen | Ising | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Government Buildings and Facilities Development Project (Provincewide) LS - P 27,000,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 3620000 | Revised: |  | No. of Man-days:
Carmen | Ising | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Government Buildings and Facilities Development Project (Provincewide) LS - P 27,000,000.00 | [7 empty] | Implementor: | Digos Constrak Corp/ | No. of days suspended: |  | Disbursement: |  | Actual:
Carmen | Ising | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Government Buildings and Facilities Development Project (Provincewide) LS - P 27,000,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Carmen | Ising | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Government Buildings and Facilities Development Project (Provincewide) LS - P 27,000,000.00 | [7 empty] | Date Allotment Released: | 2019-06-28 | Date completed:
Carmen | Ising | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | [7 empty] | Date Started:
Carmen | La Paz | 2nd Eng'g. Dist. | On-going | 2019-08-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | Const. of Multi-Purpose Hall, La Paz, Carmen |  | 20% DF CY 2019 (STIMULUS | Building |  | sq.m | MLGU | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Fund transferred to LGU March 28, 2019
Carmen | La Paz | 2nd Eng'g. Dist. | On-going | 2019-08-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Carmen | La Paz | 2nd Eng'g. Dist. | On-going | 2019-08-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Carmen | La Paz | 2nd Eng'g. Dist. | On-going | 2019-08-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Carmen | La Paz | 2nd Eng'g. Dist. | On-going | 2019-08-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Allotment Released: | 2019-02-20 | Date completed:
Carmen | La Paz | 2nd Eng'g. Dist. | On-going | 2019-08-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Started: | 2019-08-16
Carmen | Sto. Niño | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | Const. of Evacuation Center Ph. 3, Sto. Niño, Carmen |  | 20% DF CY 2019 (STIMULUS | Building |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Amended in the AIP 3rd revision CY 2019/ SB No. 4 CY 2019 changing the location to Purok !-c, Sto. Nino since the previous location was implemented by DPWH
Carmen | Sto. Niño | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Carmen | Sto. Niño | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Carmen | Sto. Niño | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Carmen | Sto. Niño | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Carmen | Sto. Niño | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Started:
Carmen | Mangalcal | 2nd Eng'g. Dist. | On-going | 2019-09-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | Const. of Multi-Purpose Hall, Mangalcal, Carmen |  | 20% DF CY 2019 (STIMULUS | Building |  | sq.m | MLGU | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Fund transfer to LGU Carmen, 3/28/2019 with check no. 2574953 and OR no. 0118982
Carmen | Mangalcal | 2nd Eng'g. Dist. | On-going | 2019-09-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Carmen | Mangalcal | 2nd Eng'g. Dist. | On-going | 2019-09-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Carmen | Mangalcal | 2nd Eng'g. Dist. | On-going | 2019-09-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Carmen | Mangalcal | 2nd Eng'g. Dist. | On-going | 2019-09-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Allotment Released: | 2019-02-20 | Date completed:
Carmen | Mangalcal | 2nd Eng'g. Dist. | On-going | 2019-09-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Started: | 2019-09-16
Carmen | Guadalupe | 2nd Eng'g. Dist. | On-going | 2019-08-15 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | Rehab. of Multi-Purpose Hall, Guadalupe, Carmen |  | 20% DF CY 2019 (STIMULUS | Building |  |  | MLGU | Project Cost: | 500000 | Target Completion Date: | 2019-11-13 23:59 | Program: | 500000 | Planned: |  | No. of Persons: |  | Fund transferred to LGU March 28, 2019
Carmen | Guadalupe | 2nd Eng'g. Dist. | On-going | 2019-08-15 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Carmen | Guadalupe | 2nd Eng'g. Dist. | On-going | 2019-08-15 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Carmen | Guadalupe | 2nd Eng'g. Dist. | On-going | 2019-08-15 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Duration: | 91 | No. of days extended: |  |  |  | Slippage: | 0%
Carmen | Guadalupe | 2nd Eng'g. Dist. | On-going | 2019-08-15 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Allotment Released: | 2019-02-20 | Date completed:
Carmen | Guadalupe | 2nd Eng'g. Dist. | On-going | 2019-08-15 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Started: | 2019-08-15
Carmen | Mabuhay | 2nd Eng'g. Dist. | On-going | 2019-08-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | Const. of Multi-Purpose Hall, Mabuhay, Carmen |  | 20% DF CY 2019 (STIMULUS | Building |  | sq.m | MLGU | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Fund transfer to LGU Carmen, 3/28/2019 with check no. 2574925 and OR no. 0118984
Carmen | Mabuhay | 2nd Eng'g. Dist. | On-going | 2019-08-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Carmen | Mabuhay | 2nd Eng'g. Dist. | On-going | 2019-08-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Carmen | Mabuhay | 2nd Eng'g. Dist. | On-going | 2019-08-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Carmen | Mabuhay | 2nd Eng'g. Dist. | On-going | 2019-08-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Allotment Released: | 2019-02-20 | Date completed:
Carmen | Mabuhay | 2nd Eng'g. Dist. | On-going | 2019-08-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Started: | 2019-08-16
Carmen | Mabaus | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | Const. Canal Lining , Mabaus, Carmen |  | 20% DF CY 2019 (STIMULUS | Canal lining |  |  | MLGU | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Fund transferred to LGU March 28, 2019
Carmen | Mabaus | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Carmen | Mabaus | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Carmen | Mabaus | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Carmen | Mabaus | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Allotment Released: | 2019-02-20 | Date completed:
Carmen | Mabaus | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Started:
Carmen | Alejal | 2nd Eng'g. Dist. | On-going | 2019-08-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | Rehab. Of Evacuation Center, Alejal, Carmen |  | 20% DF CY 2019 (STIMULUS | Building |  | sq.m | MLGU | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Fund transfer to LGU Carmen, 3/28/2019 with check no.2574949 and OR no. 0118991
Carmen | Alejal | 2nd Eng'g. Dist. | On-going | 2019-08-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Carmen | Alejal | 2nd Eng'g. Dist. | On-going | 2019-08-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Carmen | Alejal | 2nd Eng'g. Dist. | On-going | 2019-08-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Carmen | Alejal | 2nd Eng'g. Dist. | On-going | 2019-08-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Allotment Released: | 2019-02-20 | Date completed:
Carmen | Alejal | 2nd Eng'g. Dist. | On-going | 2019-08-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Started: | 2019-08-16
Carmen | Tuganay | 2nd Eng'g. Dist. | On-going | 2019-08-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | Compl. Of Evacuation Center, Tuganay, Carmen |  | 20% DF CY 2019 (STIMULUS | Building |  | sq.m | MLGU | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Fund transfer to LGU Carmen, 3/28/2019 with check no. 2574947 and OR no. 0118995
Carmen | Tuganay | 2nd Eng'g. Dist. | On-going | 2019-08-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Carmen | Tuganay | 2nd Eng'g. Dist. | On-going | 2019-08-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Carmen | Tuganay | 2nd Eng'g. Dist. | On-going | 2019-08-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Carmen | Tuganay | 2nd Eng'g. Dist. | On-going | 2019-08-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Allotment Released: | 2019-02-20 | Date completed:
Carmen | Tuganay | 2nd Eng'g. Dist. | On-going | 2019-08-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Started: | 2019-08-16
Carmen | Ising | 2nd Eng'g. Dist. | On-going | 2019-08-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | Const. of Multi-Purpose hall, Ising, Carmen |  | 20% DF CY 2019 (STIMULUS | Building |  |  | MLGU | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Fund transferred to LGU March 28, 2019
Carmen | Ising | 2nd Eng'g. Dist. | On-going | 2019-08-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Carmen | Ising | 2nd Eng'g. Dist. | On-going | 2019-08-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Carmen | Ising | 2nd Eng'g. Dist. | On-going | 2019-08-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Carmen | Ising | 2nd Eng'g. Dist. | On-going | 2019-08-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Allotment Released: | 2019-02-20 | Date completed:
Carmen | Ising | 2nd Eng'g. Dist. | On-going | 2019-08-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Started:
Carmen | Cebulano | 2nd Eng'g. Dist. | On-going | 2019-08-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | Rehab. of Multi-Purpose hall, Cebulano, Carmen |  | 20% DF CY 2019 (STIMULUS | Building |  | sq.m | MLGU | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Fund transferred to LGU March 28, 2019
Carmen | Cebulano | 2nd Eng'g. Dist. | On-going | 2019-08-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Carmen | Cebulano | 2nd Eng'g. Dist. | On-going | 2019-08-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Carmen | Cebulano | 2nd Eng'g. Dist. | On-going | 2019-08-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Carmen | Cebulano | 2nd Eng'g. Dist. | On-going | 2019-08-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Allotment Released: | 2019-02-20 | Date completed:
Carmen | Cebulano | 2nd Eng'g. Dist. | On-going | 2019-08-16 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Started: | 2019-08-16
Panabo City | Kasilak | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | Rehab. Of Multi-Purpose Hall, Kasilak, Panabo City |  | 20% DF CY 2019 (STIMULUS | Building |  |  | Contract | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | PO #2020041509 - JJR CONSTRUCTION AND SUPPLY
Panabo City | Kasilak | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Panabo City | Kasilak | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Panabo City | Kasilak | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Panabo City | Kasilak | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Panabo City | Kasilak | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Started:
Panabo City | New Malitbog | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | Rehab. Of Multi-Purpose Hall, New Malitbog, Panabo City |  | 20% DF CY 2019 (STIMULUS | Building |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Amended in AIP 3rd revsion CY 2019 to change the project to Construction of Potable Water System because the original project will be funded by LGU, Panabo City (Brgy. resolution no. 25 series of 2019 dated Aug. 13, 2019 submitted)
Panabo City | New Malitbog | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Panabo City | New Malitbog | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Panabo City | New Malitbog | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Panabo City | New Malitbog | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Panabo City | New Malitbog | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Started:
Panabo City | New Pandan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | Desilting of Canal, New Pandan, Panabo City |  | 20% DF CY 2019 (STIMULUS | Desiltation |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
Panabo City | New Pandan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Panabo City | New Pandan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Panabo City | New Pandan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Panabo City | New Pandan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Panabo City | New Pandan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Started:
Panabo City | Waterfall | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | Const. Of Multi-Purpose Hall, Waterfall, Panabo City |  | 20% DF CY 2019 (STIMULUS | Building |  |  | Contract | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Abstract #0520201797
Panabo City | Waterfall | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Panabo City | Waterfall | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Panabo City | Waterfall | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Panabo City | Waterfall | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Panabo City | Waterfall | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Started:
Panabo City | Cagangohan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | Concreting of Brgy. Road @ Prk. Guyabano, Cagangohan, Panabo City |  | 20% DF CY 2019 (STIMULUS | Concreting |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Amended in AIP 3rd revision to change the project to Rehab of Evacuation Center because the original project has no deed of donation.(Brgy. resolution no 41 series of 2019 dated Aug. 16, 2019 submitted
Panabo City | Cagangohan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Panabo City | Cagangohan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Panabo City | Cagangohan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Panabo City | Cagangohan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Panabo City | Cagangohan | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Started:
Panabo City | J.P Laurel | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | Rehab. Of Evacuation Center, J.P. Laurel, Panabo City |  | 20% DF CY 2019 (STIMULUS | Building |  |  | Contract | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Purchase Order # 2020031248- DIGOS CONSTRAK
Panabo City | J.P Laurel | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Panabo City | J.P Laurel | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Panabo City | J.P Laurel | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Panabo City | J.P Laurel | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Allotment Released: | 2019-10-23 | Date completed:
Panabo City | J.P Laurel | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Started:
Panabo City | Buenavista | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | Const. Of Multi-Purpose Hall, Buenavista, Panabo City |  | 20% DF CY 2019 (STIMULUS | Building |  |  | Contract | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Purchase Order # 2020031248- DIGOS CONSTRAK
Panabo City | Buenavista | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Panabo City | Buenavista | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Panabo City | Buenavista | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Panabo City | Buenavista | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Allotment Released: | 2019-10-18 | Date completed:
Panabo City | Buenavista | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Started:
Panabo City | San Francisco | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | Rehab. Of Multi-Purpose Hall, San Francisco, Panabo City |  | 20% DF CY 2019 (STIMULUS | Building |  |  | Contract | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Purchase Order # 2020031248- DIGOS CONSTRAK
Panabo City | San Francisco | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Panabo City | San Francisco | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Panabo City | San Francisco | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Panabo City | San Francisco | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Allotment Released: | 2019-10-18 | Date completed:
Panabo City | San Francisco | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Started:
Panabo City | Datu Abdul | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | Rehab. Of Evacuation Center, Datu Abdul Dadia, Panabo City |  | 20% DF CY 2019 (STIMULUS | Building |  |  | Contract | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Purchase Order # 2020031248- DIGOS CONSTRAK
Panabo City | Datu Abdul | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Panabo City | Datu Abdul | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Panabo City | Datu Abdul | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Panabo City | Datu Abdul | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Allotment Released: | 2019-10-18 | Date completed:
Panabo City | Datu Abdul | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Started:
Panabo City | Quezon | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | Impv't./Beautification of Brgy. Grounds, Quezon, Panabo City |  | 20% DF CY 2019 (STIMULUS | Ground dev't. |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | No. of Persons: |  | Re aligned to other stimulus projects that needs additional funding
Panabo City | Quezon | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | No. of Man-days:
Panabo City | Quezon | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Panabo City | Quezon | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0%
Panabo City | Quezon | 2nd Eng'g. Dist. | For Implementation |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Allotment Released: |  | Date completed: