[9 empty] | b) | Balbastro | c) | 2019-09-21 | g) | 9/21/2019 | c) | [9 empty] | 2
[9 empty] | c) | Admin | d) | [13 empty] | 2
[9 empty] | d) | - | [14 empty] | 2
| A. | Supplemental Budget # 1 CY 2015 | [22 empty] | FS
|  |  | 1. Proposed Davao del Norte Tourism Billboard |  |  | Billboard |  | Admin | a) | 756,400.00 | a) | 05/06/15 | e) | - | a) | 756,400.00 | a) | 11.78% | c) | 11.78% | a) | - | delay due to change location & design code. For AIP amendment from Panabo City to Gov't Center, Mankilam |  | FS
|  |  | Brgy. Lasang, Panabo City | [5 empty] | b) | Porras | b) | 03/30/15 | f) | - | b) | 756,400.00 | b) | - | d) | - | b) | - |  |  | FS
[9 empty] | c) | PEO | c) | 05/10/15 | g) | - | c) | 332,087.30 | [8 empty] | 1
[9 empty] | d) | - | d) | - | [12 empty] | 1
| B. | Trust Fund 2014 | [22 empty] | 1
|  |  | 1. PAMANA-DILG CY 2014 | [21 empty] | 2
|  |  |  | Construction of Biga Bridges, Kapalong (Original Contract Cost: P 24,959,503.45; Variation Order: P 4,067,412.00) |  | Road | 2-18ln.m | Contract | a) | 29026915.45 | a) | CY 2014 | e) | 48 CD | a) | 29026915.45 | a) | 100.00% | c) | 85.37% | a) | 8 | Suspended due to RROW dated Dec. 13, 2019 |  | 2
|  |  | 1.1 | [5 empty] | b) | Limpo | b) | 2016-07-01 | f) | - | b) | 29026915.45 | b) | 99.7% | d) | -14.33% | b) | 290 |  |  | 2
[9 empty] | c) | Dvo. Rock Mixer | c) | 2018-07-30 | g) | - | c) | 18,489,834.55 | [8 empty] | 2
[9 empty] | d) | 880 CD | d) | 2020-03-25 | [12 empty] | AC
| D. | Trust Fund 2015 | [22 empty] | AC
|  |  | 1. PRDP CY 2014 | [21 empty] | 2
|  |  |  | Rehab. of Esperanza-Pob. Sto. Tomas, FMR, DDN |  | Road | 12.77399 km | Contract. | a) | 117,410,426.30 | a) | CY 2014 | e) | - | a) | 117,410,426.30 | a) | 100% | c) | 87.82% | a) | 20 | On-going (Waiting for approve Variation order for billing) |  | AC
|  |  | 1.1 | [5 empty] | b) | Palero | b) | 2017-03-22 | f) | 252 | b) | 117,410,426.30 | b) | 95.53% | d) | -7.705% | b) | 600 |  |  | AC
[9 empty] | c) | Alzam | c) | 2019-07-22 | g) | - | c) | 113,335,769.31 | [8 empty] | AC
[9 empty] | d) | 853 CD | d) | 7/31/2020 | [12 empty] | 1
| C. | Trust Fund 2016 | [22 empty] | 1 | 1 | Asuncion | Red
|  |  | 1. PRDP CY 2016 | [21 empty] | 1 | 2 | B.E. Dujali | Yellow
|  |  |  | Improvement of Sto. Tomas Production Center with Common Facility, Sto. Tomas |  | Bldg. | 1901 sq.m | Contract. | a) | 9825000 | a) | CY 2014 | f) | - | b) |  | a) |  | c) |  | a) |  | Suspended due to land unsettlement |  | 1
|  |  | 1.3 | [5 empty] | b) | Azotes | b) | 2018-01-29 | g) | - | c) | - | b) |  | d) |  | b) |  | Revised POW and DED On-going
[9 empty] | c) | Manantan | c) | 2018-09-24 | [12 empty] | 1
[9 empty] | d) | 330 C.D | d) | 2018-12-05 | [12 empty] | FS
| D. | 20% Development Fund CY 2016 | [22 empty] | 1
|  |  | 1. Rural Electrification (Provincewide) |  |  | Elect. | km | Admin | a) | 5000000 | [12 empty] | See projects listed below |  | FS
[9 empty] | b) | Foronda/Ababon | [14 empty] | AC
[9 empty] | c) | Admin | [14 empty] | 1
[9 empty] | d) | - | [14 empty] | 1
|  |  | 1.1 | Inst. of transformer and accessories, |  | Elect. | Households | Admin | a) | 150,000.00 | a) | 2018-07-31 | e) | - | a) | 150,000.00 | a) | - | c) | - | a) | - | Purchase Order # 2019103228 - Transformer |  | 1
|  |  |  | Brgy. Kinawitnon |  |  |  |  | b) | - | b) | - | f) | - | b) | 150,000.00 | b) | - | d) | - | b) | - | Purchase Order # 2019102931 - Billboard |  | 1
[9 empty] | c) | - | c) | - | g) | - | c) | - | [6 empty] | Purchase Order # 2019103227 - Lumber |  | 1
[9 empty] | d) | - | d) | - | [12 empty] | 1
|  |  | 1.2 | Rural Electrification at brgy. Sta. Cruz, |  | Elect. | Households | Contract | a) | 2000000 | a) | - | e) | - | a) | 2000000 | a) | - | c) | - | a) | - | Delay due to slow action of Daneco for staking. c/o Engr. Kim
|  |  |  | talikud, Samal |  |  |  |  | b) | - | b) | - | f) | - | b) | 2000000 | b) | - | d) | - | b) | -
[9 empty] | c) | Admin | c) | - | g) | - | c) | -
[9 empty] | d) | - | d) | -
|  |  | 2. Const./Rehab./Comp. of Various Gov't. Bldgs. |  |  | Bldgs./ | sq.m | Admin | a) | 9,000,000.00 | [12 empty] | See project listed below
|  |  | Struct., Fac. (Provincewide) | [5 empty] | b) | Foronda/Ababon | [14 empty] | 1
[9 empty] | c) | PEO | [14 empty] | 1
|  |  | 2.1 | Construction of Provincial Training Center |  | Fence | sq.m | Admin | a) | 940,000.00 | a) | 2017-09-19 | e) | - | a) | 940,000.00 | a) | 68.00% | c) | 75.00% | a) | - | Temporarily suspended 4/23/18 due to undemolished structures of illegal settlers |  | 1
|  |  |  | Compound Fence, Kinawitnon, Babak |  |  |  |  | b) | Pacquiao | b) | 2018-03-12 | f) | - | b) | 940,000.00 | b) | - | d) | - | b) | -
|  |  |  | District, IGCS |  |  |  |  | c) | PEO | c) | 2018-06-19 | g) | - | c) | 933,418.80 | [8 empty] | FS
[9 empty] | d) | - | d) | - | [12 empty] | 1
| E. | 20% Development Fund CY 2017 | [22 empty] | 1
|  |  | STIMULUS PROJECTS | [21 empty] | 1
|  |  | PANABO CITY | [21 empty] | 1
|  |  |  | Const of Market Stall/Building, Consolacion, Panabo City |  | Bldg. | sq.m | MLGU | a) | 500000 | a) | 2017-12-28 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Suspended effective April 5, 2020 due to issued Executive Order No. 31, series of 2020 the province of Davao del Norte in response to the State of Public Health Emergency and State of National Calamity (COVID19 Pandemic). |  | 1
|  |  | 1 | [5 empty] | b) | - | b) | 2019-05-28 | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[9 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[9 empty] | d) | - | d) | - | [12 empty] | 1
|  |  |  | Rehab. Of Multi-Purpose Hall (Covered Court), Upper Licanan, Panabo City |  | Footbridge | sq.m | MLGU | a) | 500000 | a) | 2017-12-28 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Suspended effective April 5, 2020 due to issued Executive Order No. 31, series of 2020 the province of Davao del Norte in response to the State of Public Health Emergency and State of National Calamity (COVID19 Pandemic). |  | 1
|  |  | 2 | [5 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[9 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[9 empty] | d) | - | d) | - | [12 empty] | 1
|  |  |  | Impv't. of Multi-Purpose Gym, Kauswagan, Panabo City |  | GYM | sq.m | MLGU | a) | 500000 | a) | 2019-02-04 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Suspended effective April 5, 2020 due to issued Executive Order No. 31, series of 2020 the province of Davao del Norte in response to the State of Public Health Emergency and State of National Calamity (COVID19 Pandemic). |  | 1
|  |  | 3 | [5 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[9 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[9 empty] | d) | - | d) | - | [12 empty] | AC
|  |  |  | Const. of MP Bldg. w/ Electrical installation, San Roque, Panabo City |  | Bldg. | sq.m | MLGU | a) | 500000 | a) | 2018-01-31 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Suspended effective April 5, 2020 due to issued Executive Order No. 31, series of 2020 the province of Davao del Norte in response to the State of Public Health Emergency and State of National Calamity (COVID19 Pandemic). |  | AC
|  |  | 4 | [5 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | AC
[9 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[9 empty] | d) | - | d) | - | [12 empty] | 1
|  |  |  | Const. of Multi-Purpose Bldg.,Cacao, Panabo City |  | Bldg. | sq.m | MLGU | a) | 300000 | a) | 2017-12-19 | e) | - | a) | 300000 | a) | - | c) | - | a) | - | Suspended effective April 5, 2020 due to issued Executive Order No. 31, series of 2020 the province of Davao del Norte in response to the State of Public Health Emergency and State of National Calamity (COVID19 Pandemic). |  | 1
|  |  | 5 | [5 empty] | b) | - | b) | 2018-12-14 | f) | - | b) | 300000 | b) | - | d) | - | b) | - |  |  | 1
[9 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1 | 21512501.501
[9 empty] | d) | - | d) | - | [12 empty] | 2
|  |  |  | Const. of Multi-Purpose Bldg. @ A.O. Floriendo National Highschool, Panabo City |  | Bldg. | sq.m | MLGU | a) | 500000 | a) | 2017-12-19 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Suspended effective April 5, 2020 due to issued Executive Order No. 31, series of 2020 the province of Davao del Norte in response to the State of Public Health Emergency and State of National Calamity (COVID19 Pandemic). |  | 2
|  |  | 6 | [5 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[9 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[9 empty] | d) | - | d) | -
STO. TOMAS
|  |  |  | Const. of Concrete Drainage Canal, Kimamon, Panabo City |  | Drainage | ln.m | MLGU | a) | 500000 | a) | 2017-12-19 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For Implementation
|  |  | 7 | [5 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | AC
[9 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | AC
[9 empty] | d) | - | d) | - | [12 empty] | AC
|  |  | IGACOS | [21 empty] | 1
|  |  |  | Impv't. of Brgy. Street Electrification at Brgy. Anonang, IGCS |  | Elect. | Households |  | a) | 500000 | a) | 2017-11-28 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Verified at PBO 7/18/2019 that fund is not available. Proposed priority project for 2020\ |  | 1
|  |  | 8 | [5 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[9 empty] | c) | PEO | c) | - | g) | - | c) | - | [8 empty] | 1
[9 empty] | d) | - | d) | - | [12 empty] | AC
| F. | Trust Fund 2017 | [22 empty] | AC
|  |  | 1. OPPAP-PAMANA | [21 empty] | AC
|  |  | 1.1 | Const. of Trading Post, Storage Building |  | Bldg. |  | Contract | a) | 3,975,000.00 | a) | CY 2017 | e) | - | a) | 3,975,000.00 | a) | 100% | c) | 40.36% | a) | 10 | On-going/ Time extension on process due to suspension of activity due to covid 19 |  | 2
|  |  |  | with (1) unit Hauling Truck, Prk. Ramihan |  |  |  |  | b) | Azotes | b) | 2019-11-21 | f) | - | b) | 3,975,000.00 | b) | 35.53% | d) | -4.83% | b) | 260 |  |  | 2
|  |  |  | Datu Abdul, Panabo City |  |  |  |  | c) | Ultra Core | c) | 2019-04-05 | g) | - | c) | - | [8 empty] | 2
[9 empty] | d) | - | d) | 5/16/2020 | [12 empty] | 2
[6 empty] | - | - | - | a) | 4000000 | a) | CY 2018 | e) | - | a) | 4000000 | a) | - | c) | - | a) | - | For bidding |  | AC
|  |  | 1.2 | Trading Post, Storage and Hauling Truck Libuak, Island Garden City of Samal (IGACOS) |  |  |  |  | b) | - | b) | - | f) | - | b) | 4000000 | b) | - | d) | - | b) | - |  |  | AC
[9 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | AC
` | [8 empty] | d) | - | d) | - | [12 empty] | 1
|  |  | 1.3 | Construction of Tribal Hall, Sto. Tomas |  | Bldg. |  | Admin | a) | 500000 | a) | CY 2018 | e) | - | a) | 500000 | a) | 100% | c) | 89.5% | a) | 7 | Suspended June 28, 2019. Waiting for the delivery of JO Materials |  | 1
[9 empty] | b) | Roque | b) | 2019-05-22 | f) | - | b) | 500000 | b) | - | d) | -10.5% | b) | 110 |  |  | 1
[9 empty] | c) | Admin | c) | 2019-07-31 | g) | - | c) | - | [8 empty] | 1
[9 empty] | d) | 70 CD | d) | - | [12 empty] | 1
|  |  | 1.4 | Agricultural Productivity Support Project- |  | - |  | - | a) | 1500000 | a) | - | e) | - | a) | 1500000 | a) | - | c) | - | a) | - | For bidding |  | 2
|  |  |  | Fishing Equipment, Tambo, IGACOS |  |  |  |  | b) | - | b) | - | f) | - | b) | 1500000 | b) | - | d) | - | b) | - |  |  | 2
[9 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[9 empty] | d) | - | d) | - | [12 empty] | 2
| J. | 20% Development Fund CY 2018 | [22 empty] | AC
|  |  | 1. Construction of Water System Projects in Component LGUs |  |  | Water System | sq.m | Admin/Contract | a) | 9750000 | [12 empty] | See list of projects |  | 1
[9 empty] | b) | Diosanta | [14 empty] | 1
[9 empty] | c) | PEO | [14 empty] | ?
[9 empty] | d) | - | [14 empty] | 1
|  |  |  | Installation of potable water System at Purok Nangka, Pandapan, Tagum City |  | Water System | Households | Admin | a) | 1125000 | a) | - | e) | - | a) | 1125000 | a) | - | c) | - | a) | - | Waiting for deed of donation. Follow-up letter was already issued |  | 1
|  |  | 1.1 | [5 empty] | b) | - | b) | - | f) | - | b) | 1125000 | b) | - | d) | - | b) | - |  |  | 1
[9 empty] | c) | PEO | c) | - | g) | - | c) | - | [8 empty] | 1
[9 empty] | d) | - | d) | - | [12 empty] | 1
|  |  |  | Rehab./Impv't. of San Vicente Water System, Asuncion |  | Water System | Households | Admin | a) | 1125000 | a) | 2018-10-26 | e) | - | a) | 1125000 | a) | - | c) | - | a) | - | Abstract # 0220190484 still draft |  | 1
|  |  | 1.2 | [5 empty] | b) | - | b) | - | f) | - | b) | 1125000 | b) | - | d) | - | b) | - |  |  | 1
[9 empty] | c) | PEO | c) | - | g) | - | c) | - | [8 empty] | 1
[9 empty] | d) | - | d) | - | [12 empty] | 1
|  |  |  | Water System at brgy. Malativas, Panabo City |  | Water System | Households | Admin | a) | 1250000 | a) | - | e) | - | a) | 1250000 | a) | - | c) | - | a) | - | For preparation of POW & Plan c/o PDPM - POSSIBLE TRANSFER OF SITE SUBJECT FOR TRANSFER OF LOCATION . NO DEED OF DONATION |  | 1
|  |  | 1.3 | [5 empty] | b) | - | b) | - | f) | - | b) | 1250000 | b) | - | d) | - | b) | - |  |  | 1
[9 empty] | c) | Admin | c) | - | g) | - | c) | - | [8 empty] | 1
[9 empty] | d) | - | d) | -
|  |  |  | Const. of Potable Water System at Brgy. Tibungol, Panabo City |  | Water System | Households | Admin | a) | 1250000 | a) | 2018-11-21 | e) | - | a) | 1250000 | a) | 2.13% | c) | 0.76% | a) | 3 | Suspended dated February 19, 2020 undelivered hardware materials (Supplier refused to deliver. Letter already submitted to BAC.) |  | 1
|  |  | 1.4 | [5 empty] | b) | Andoy | b) | 2020-01-20 | f) | - | b) | 1250000 | b) | - | d) | -1.37% | b) | 15 |  |  | 1
[9 empty] | c) | Admin | c) | 2020-04-15 | g) | - | c) | - | [8 empty] | 1
[9 empty] | d) | 76 C.D | d) | - | [12 empty] | 1
|  |  |  | Potable Water System at Brgy. San Remegio Kaputian (Level II WS), Samal |  | Water System | Households | Admin | a) | 3625000 | a) | 2018-10-25 | e) | - | a) | 3625000 | a) | 100% | c) | 74.56% | a) | 4 | On-going/ Resumption 5/4/2020 |  | 1
|  |  | 1.5 | [5 empty] | b) | Diosanta | b) | 2019-07-16 | f) | 89 CD | b) | 3625000 | b) | 72.04% | d) | 2.52% | b) | 88 |  |  | 1
[9 empty] | c) | Admin | c) | 2020-02-01 | g) | - | c) | 2702800 | [8 empty] | AC
[9 empty] | d) | 200 C.D | d) | 2020-04-30 | [12 empty] | 1
| H. | GENERAL FUND PROPER CY 2018 | [22 empty] | 1
|  |  | STIMULUS PROJECTS | [21 empty] | 1
|  |  | CARMEN | [19 empty] | Plan and POW Approval on process |  | 1
|  |  | 1 | Completion of Evacuation Center Building, |  | Bldg. |  | Contract | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - |  |  | 1
|  |  |  | San Isidro, Carmen |  |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[9 empty] | c) | Contract | c) | - | g) | - | c) | - | [8 empty] | 1
[9 empty] | d) | - | d) | - | [12 empty] | 1
|  |  | PANABO CITY | [19 empty] | (RLHV Design & Build) Winning Bidder |  | 1
|  |  | 2 | Const. of Perimeter Fence of Day Care Center 1 |  | Bldg. |  | Contract | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - |  |  | FS
|  |  |  | Nanyo, Panabo City |  |  |  |  | b) | RLHV | b) | 4/7/2020 | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | AC
[9 empty] | c) | Contract | c) | 6/6/2020 | g) | - | c) | - | [8 empty] | 1
[9 empty] | d) | 60 | d) | - | [12 empty] | 1
|  |  |  | Impv't. of Brgy. Road Covered Court, Malativas, Panabo City |  | Court | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Alloted - May 29, 2019, Additional Funding of 500,000.00,SB no. 4 CY 2019 |  | 1
|  |  | 3 | [5 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[9 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[9 empty] | d) | - | d) | - | [12 empty] | AC
|  |  |  | Rehab. Of Multi-Purpose Gym & Facililies Maduao, Panabo City |  | Gym | sq.m | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Purchase Request # 20032056 |  | 1
|  |  | 4 | [5 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[9 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[9 empty] | d) | - | d) | - | [12 empty] | 1
|  |  |  | Const. of Multi-Purpose Bldg. Sto. Nino, Panabo City |  | Bldg. | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Plan and POW on process c/o PDPM |  | 1
|  |  | 5 | [5 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[9 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[9 empty] | d) | - | d) | - | [12 empty] | 1
|  |  |  | Completion of Canopy at DAPCO Covered Court, Dapco, Panabo City |  | Court | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | (RLHV Design & Build) Winning Bidder |  | AC
|  |  | 6 | [5 empty] | b) | RLHV | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[9 empty] | c) | Contract | c) | - | g) | - | c) | - | [8 empty] | 1
[9 empty] | d) | - | d) | - | [12 empty] | 1
|  |  |  | Perimeter Fence of Day Care Center I & II, Nanyo, Panabo City/ Construction of Perimeter Fence) |  | Bldg. | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For inspection by PDPM for PLAN and POW as of 7/19/2019/ (RLHV Design & Build) Winning Bidder |  | 1
|  |  | 7 | [5 empty] | b) | - | b) | 4/7/2020 | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[9 empty] | c) | - | c) | 6/6/2020 | g) | - | c) | - | [8 empty] | 1
[9 empty] | d) | - | d) | - | [12 empty] | 1
|  |  | IGCS | [21 empty] | 1
|  |  | 8 | Impv't. of Brgy. Water System, Pichon, IGCS |  | Water |  | Admin | a) | 500000 | a) | 2018-05-31 | e) | - | a) | 500000 | a) | 100% | c) | 83.5% | a) | 5 | Suspended effective April 5, 2020 due to issued Executive Order No. 31, series of 2020 the province of Davao del Norte in response to the State of Public Health Emergency and State of National Calamity (COVID19 Pandemic). |  | 1
|  |  |  | (Construction of Elevated Tank) |  | System |  |  | b) | Andoy | b) | 2020-01-13 | f) | - | b) | 500000 | b) | - | d) | -16.5% | b) | 110 |  |  | AC
[9 empty] | c) | Admin | c) | 2020-03-13 | g) | - | c) | 423575.63 | [8 empty] | 1
[9 empty] | d) | 80 | d) | - | [12 empty] | 1
|  |  | 9 | Powerline Expansion Project, Cogon, IGACOS |  | Water |  | Contract | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Waiting for NTP |  | 1
[6 empty] | System |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | AC
[9 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[9 empty] | d) | - | d) | - | [12 empty] | 1
|  |  | 10 | Water System From Prk. 6 - Prk. 2 - Prk. 5A, |  | Water |  | Admin | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For Implementation |  | 1
|  |  |  | Tagbay, IGCS |  | System |  |  | b) | Pacquiao | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[9 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[9 empty] | d) | - | d) | - | [12 empty] | 1
|  |  | 11 | Powerline Expansion Project, Tambo, IGCS |  | Elect. |  | Contract | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Purchase Request # 19083312 |  | 1
[9 empty] | b) | Porras | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[9 empty] | c) | Admin | c) | - | g) | - | c) | - | [8 empty] | 1
[9 empty] | d) | - | d) | - | [12 empty] | 1
|  |  | 12 | Improvement of Barangay Hall, |  | Bldg. |  | Admin | a) | 500000 | a) |  | e) | - | a) | 500000 | a) | - | c) | - | a) | - | By Contract and change to admin due to unforeseen activities because it’s a repair (For revision of POW) |  | 1
|  |  |  | Penaplata, IGCS |  |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[9 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | AC
[9 empty] | d) | - | d) | - | [12 empty] | 1
|  |  | 13 | Electrification of Sitio Baongon-Diamond- |  | Elect. |  | - | a) | 500000 | a) |  | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Purchase Order # 20200100002 (3E Electrical Sales & Services) |  | 1
|  |  |  | Mansanitas, Dadatan, IGCS |  |  |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[9 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[9 empty] | d) | - | d) | - | [12 empty] | 1
|  |  | 14 | Drilling of Water System, |  | Water |  | - | a) | 500000 | a) |  | e) | - | a) | 500000 | a) | - | c) | - | a) | - | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. |  | 1
|  |  |  | Linusotan, IGCS |  | System |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[9 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[9 empty] | d) | - | d) | - | [12 empty] | FS
| I. | SUPPLEMENTAL BUDGET # 1 CY 2018 | [22 empty] | 1
|  |  | Const./Compl./Impv't. of Various Gov't. Bldgs., Structures & Facilities (Const. in Progress - Bldgs. & Other Structures | [21 empty] | 1
|  | 1 | [22 empty] | 1
1
|  |  |  | Const. of DDN Hospital Carmen Zone Annex Bldg. |  | Bldg. | sq.m | Admin | a) | 5,500,000.00 | a) | - | e) | - | a) | 5,500,000.00 | a) | - | c) | - | a) | - | Winning Bidder - Digos Constrak Corp. |  | 1
|  |  | 1.1 | [5 empty] | b) | Azotes | b) | 3/19/2020 | f) |  | b) | 5,500,000.00 | b) | - | d) | - | b) | - |  |  | 1
[9 empty] | c) | PEO | c) | 7/17/2020 | g) | - | c) | - | [8 empty] | 1
[9 empty] | d) | - | d) | - | [12 empty] | 1
| J. | 20% DEVELOPMENT FUND CY 2019 | [22 empty] | 1
[8 empty] | Admin | a) | 46740177 | [12 empty] | See list of Provincial Roads |  | 1
| Road ID |  | 1. Maintenance of Various Provincial Roads and Bridges at District |  |  | Road Maintenance | 115.620 km |  | b) | Paraguya | [14 empty] | 1
[9 empty] | c) | PEO | [14 empty] | 1
| 11DAN | [23 empty] | 1
[9 empty] | d) | 261 days | [14 empty] | 1
|  |  | Jct. Highway Sto. Niño - Cebulano |  |  | Road Rehabilitation | 2.09 | MBA | a) | 1045000 | a) | 2019-01-03 | e) | 120 CD | a) | 1045000 | a) | 100% | c) | 100% | a) | 6 | Completed 5/31/2020 |  | 1
| 072 | [7 empty] | b) | Obar/ Nasol | b) | 2019-05-21 | f) | 61 | b) | 1045000 | b) | - | d) | - | b) | 132
[9 empty] | c) | PEO | c) | 2019-10-04 | g) | 5/31/2020 | c) | - | [8 empty] | AC
[9 empty] | d) | - | d) | 4/15/2020 | [12 empty] | 1
|  |  | Basa - Tubod |  |  | Road Rehabilitation | 1.56 | MBA | a) | 1000000 | a) | 2019-01-03 | e) | - | a) | 1000000 | a) | 100% | c) | 100% | a) | 3 | Completed 6/30/2020 |  | 1
| 076 | [7 empty] | b) | PIAD | b) | 2019-11-11 | f) | - | b) | 1000000 | b) | 100% | d) | 0% | b) | 30 |  |  | 1
[9 empty] | c) | Admin | c) | 2020-03-19 | g) | 6/30/2020 | c) | [9 empty] | 1
[9 empty] | d) | 120 | d) | 6/30/2020 | [12 empty] | 1
|  |  | Tubod - Pilar |  |  | Road Rehabilitation | 1.55 | MBA | a) | 16000000 | a) | 2019-11-26 | e) | - | a) | 16000000 | a) | 62.5% | c) | 58.23% | a) | 20 | On-going |  | 1
| 077 | [7 empty] | b) | Agang | b) | 2019-12-18 | f) | - | b) | 16000000 | b) | - | d) | -4.27% | b) | 600 |  |  | 1
[9 empty] | c) | Admin | c) | 2020-11-05 | g) | - | c) | 4046971.2 | [8 empty] | 1
[9 empty] | d) | 323 C.D | d) | - | [12 empty] | 1
|  |  | Sitio Malaga - Tibulao |  |  | Road Rehabilitation | 3.22 | MBA | a) | 1000000 | a) | 2019-01-03 | e) | - | a) | 1000000 | a) | 78.5% | c) | 54.8% | a) | 5 | On-going |  | 1
| 103 | [7 empty] | b) | Obar | b) | 2019-11-11 | f) | - | b) | 1000000 | b) | - | d) | -23.7% | b) | 110
[9 empty] | c) | Admin | c) | 2020-02-09 | g) | - | c) | [9 empty] | AC
[9 empty] | d) | 90 | d) | 6/30/2020 | [12 empty] | 1
|  |  | Dujali - Tanglaw |  |  | Road Rehabilitation | 3.6 | MBA | a) | 2075000 | a) | 2019-01-03 | e) | 28 | a) | 2075000 | a) | 60% | c) | 65% | a) | 11 | On-going |  | 1
| 104 | [7 empty] | b) | Balbastro | b) | 2019-12-28 | f) | 108 | b) | 2075000 | b) | - | d) | 5% | b) | 77 |  |  | 1
` | [8 empty] | c) | Admin | c) | 2020-04-16 | g) | - | c) | [9 empty] | 1
[9 empty] | d) | 110 | d) | 7/31/2020
|  |  | San Miguel - Libertad |  |  | Road Rehabilitation | 6.2 | MBA | a) | 1240000 | a) | 2019-01-03 | e) | - | a) | 1240000 | a) | 59.41% | c) | 59.41% | a) | 9 | On-going/ Time extension on process due to suspension of activity due to covid 19 |  | AC
| 121 | [7 empty] | b) | Gamad | b) | 2019-06-17 | f) | 30 | b) | 1240000 | b) | - | d) | - | b) | 36 |  |  | 1
[9 empty] | c) | - | c) | 2019-10-31 | g) | - | c) | [9 empty] | 1
[9 empty] | d) | - | d) | 2020-02-29 | [12 empty] | 1
|  |  | Bacali - Casig-ang - Libertad |  |  | Road Rehabilitation | 4.7 | MBA | a) | 940000 | a) | 2019-06-07 | e) | - | a) | 940000 | a) | 62.1% | c) | 62% | a) | 9 | On-going/ Time extension on process due to suspension of activity due to covid 19 |  | 1
| 123 | [7 empty] | b) | Gamad | b) | 2019-06-27 | f) | 35 | b) | 940000 | b) | - | d) | - | b) | 36 |  |  | 1
[9 empty] | c) | Admin | c) | 2019-09-15 | g) | - | c) | [9 empty] | 1
[9 empty] | d) | 80 C.D | d) | 2020-02-29 | [12 empty] | 1
|  |  | San Miguel - Moslog - Kinamayan |  |  | Road Rehabilitation | 2.9 | MBA | a) | 1000000 | a) | 2019-05-20 | e) | - | a) | 1000000 | a) | 100% | c) | 80% | a) | 6 | On-going/ Time extension on process due to suspension of activity due to covid 19 |  | 1
| 125 | [7 empty] | b) | Gamad | b) | 2019-06-17 | f) | 29 | b) | 1000000 | b) | 73.59% | d) | 6.41% | b) | 30 |  |  | 1
[9 empty] | c) | - | c) | 2019-09-16 | g) | - | c) | [9 empty] | 1
[9 empty] | d) | - | d) | 2020-02-29 | [12 empty] | 1
|  |  | Mugas - Lanatad |  |  | Road Rehabilitation | 1.53 | MBA | a) | 500000 | a) | 2019-01-03 | e) | 90 | a) | 500000 | a) | 100% | c) | 100% | a) | 4 | Completed 3/31/2020 |  | 1
| 131 | [7 empty] | b) | Balbastro | b) | 2019-08-05 | f) | - | b) | 500000 | b) | - | d) |  | b) | 104 |  |  | 1
[9 empty] | c) | Admin | c) | 2019-10-06 | g) | 3/31/2020 | c) | [9 empty] | 1
[9 empty] | d) | 60 C.D | d) | 2020-02-29 | [12 empty] | 1
|  |  | New Katipunan - Pantaron |  |  | Road Rehabilitation | 1.96 | MBA | a) | 395000 | a) | 2019-01-03 | e) | - | a) | 395000 | a) | 60% | c) | 60% | a) | 4 | On-going/ Time extension on process due to suspension of activity due to covid 19 |  | 1
| 134 | [7 empty] | b) | Gamad/Clar | b) | 2019-12-27 | f) | - | b) | 395000 | b) | - | d) | - | b) | 24 |  |  | 1
[9 empty] | c) | - | c) | 2020-02-25 | g) | - | c) | [9 empty] | 1
[9 empty] | d) | 60 | d) | - | [12 empty] | 1
|  |  | Fd. Rd. 2 - Sto. Tomas - Magwawa |  |  | Road Rehabilitation | 10.21 | MBA | a) | 3575000 | a) | 2019-01-03 | e) | - | a) | 3575000 | a) | 100% | c) | 100% | a) | 16 | Completed 3/31/2020 |  | 1
| 137 | [7 empty] | b) | Sanchez | b) | 2019-08-27 | f) | - | b) | 3575000 | b) | - | d) | 0% | b) | 112 |  |  | 1
[9 empty] | c) | Admin | c) | 2020-01-24 | g) | - | c) | [9 empty] | 1
[9 empty] | d) | 150 C.D | d) | 3/31/20020 | [12 empty] | 1
|  |  | Jct. Highway - Tanglaw |  |  | Road Rehabilitation | 3.98 | MBA | a) | 1100000 | a) | 2019-05-16 | e) | - | a) | 1100000 | a) | 100% | c) | 85% | a) | 10 | On-going/ Time extension on process due to suspension of activity due to covid 19 |  | 1
| 142 | [7 empty] | b) | Gamad/Clar | b) | 2019-06-17 | f) | 29 CD | b) | 1100000 | b) | 73.59% | d) | 11.41% | b) | 50 |  |  | 1
[9 empty] | c) | PEO | c) | 2019-09-16 | g) | - | c) | [9 empty] | 1
[9 empty] | d) | - | d) | 2020-02-29 | [12 empty] | 1
|  |  | Bdry. Tagum - Crossing Kinamayan Sto. Tomas |  |  | Road Rehabilitation | 0.75 | MBA | a) | 3700000 | a) | 2019-01-03 | e) | 20 | a) | 3700000 | a) | 100% | c) | 16.37% | a) | 15 | On-going
| 146 | [7 empty] | b) | Mellomida | b) | 2019-12-27 | f) | 100 | b) | 3700000 | b) | 15.43% | d) | 0.94% | b) | 225
[9 empty] | c) | Admin | c) | 2020-04-25 | g) | - | c) | [9 empty] | 1
[9 empty] | d) | 120 | d) | 8/14/2020 | [12 empty] | 1
|  | Road Rehabilitation of Provincial Roads | [22 empty] | 1
|  |  | 1. Rehab.of Dujali - Balisong - Magupising Provincial Road |  |  | Road Rehabilitation | 19.16 | MBA | a) | 1280000 | a) |  | e) | - | a) | 1280000 | a) | 100% | c) | 96.23% | a) | 12 | Completed 529/2020 |  | 1
[9 empty] | b) | Mellomida | b) | 2019-12-02 | f) | - | b) | 1280000 | b) | 100% | d) | -3.77% | b) | 900 |  |  | 1
[9 empty] | c) | Admin | c) | 2019-01-15 | g) | 5/29/2020 | c) | 14331.6 | [8 empty] | 1
[9 empty] | d) | 45 CD | d) | 5/31/2020 | [12 empty] | 1
|  |  | 2. Fr. Rd. 3 - San Jose |  |  | Road Rehabilitation | 4.55 | Admin | a) | 800000 | a) |  | e) | - | a) |  | a) |  | c) | 2.14% | a) | 3 | On-going |  | 1
[9 empty] | b) | Obar | b) | 5/18/2020 | f) | - | b) |  | b) |  | d) |  | b) | 30 |  |  | 1
[9 empty] | c) | Admin | c) | 2020-08-06 | g) |  | c) | [9 empty] | 1
[9 empty] | d) | 80 | d) | [13 empty] | 1
|  |  | 3. Lower Asuncion - Upper Asuncion |  |  | Road Rehabilitation | 1.02 | Admin | a) | 8000000 | a) |  | e) | - | a) |  | a) |  | c) |  | a) |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. |  | 1
[9 empty] | b) |  | b) |  | f) | - | b) |  | b) |  | d) |  | b) |  |  |  | 1
[9 empty] | c) |  | c) |  | g) |  | c) | [9 empty] | 1
[9 empty] | d) |  | d) | [13 empty] | 1
|  |  | 4. Jct. Highway - Carmen - Mangalcal - Tubod |  |  | Road Rehabilitation | 11.34 | Admin | a) | 1323000 | a) |  | e) | 1323000 | a) |  | a) | 100% | c) | 1.21% | a) | 3 | On-going |  | 1
[9 empty] | b) | Obar | b) | 6/15/2020 | f) | - | b) |  | b) |  | d) |  | b) | 30 |  |  | 1
[9 empty] | c) | Admin | c) | 2020-07-15 | g) |  | c) | [9 empty] | 1
[9 empty] | d) | 30 | d) | [13 empty] | 1
|  |  | 5. Tuganay - Taba |  |  | Road Rehabilitation | 4.27 | Admin | a) | 507500 | a) |  | e) | 507500 | a) | 507500 | a) | 100% | c) | 3.37% | a) | 3 | On-going |  | 1
[9 empty] | b) | Obar | b) | 5/18/2020 | f) | - | b) | 507500 | b) |  | d) |  | b) | 30 |  |  | AC
[9 empty] | c) | Admin | c) | 6/17/2020 | g) |  | c) | [9 empty] | 1
[9 empty] | d) | 30 | d) | [13 empty] | 1
|  |  | 6. Jct. Highway - Ising - Magsaysay |  |  | Road Rehabilitation | 10.84 | Admin | a) | 6000000 | a) |  | e) | 6000000 | a) | 6000000 | a) |  | c) |  | a) |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. |  | 1
[9 empty] | b) |  | b) |  | f) | - | b) |  | b) |  | d) |  | b) |  |  |  | 1
[9 empty] | c) |  | c) |  | g) |  | c) | [9 empty] | 1
[9 empty] | d) |  | d) | [13 empty] | 1
|  |  | 7. Jct. Highway - Guadalupe - Bdry. Tagum |  |  | Road Rehabilitation | 7.9 | Admin | a) | 910000 | a) |  | e) | - | a) | 910000 | a) |  | c) | 2.04% | a) | 3 | On-going |  | 1
[9 empty] | b) | Obar | b) | 5/18/2020 | f) | 910000 | b) | 910000 | b) |  | d) |  | b) | 30 |  |  | 1
[9 empty] | c) | Admin | c) | 2020-08-06 | g) |  | c) | [9 empty] | 1
[9 empty] | d) | 80 | d) | [13 empty] | 1
|  |  | 8. Sitio Malaga - Tibulao |  |  | Road Rehabilitation | 3.22 | Admin | a) | 350000 | a) |  | e) | 350000 | a) | 350000 | a) |  | c) | 3.37% | a) | 3 | On-going |  | 1
[9 empty] | b) | Obar | b) | 5/18/2020 | f) | - | b) | 350000 | b) |  | d) |  | b) | 30 |  |  | 2
[9 empty] | c) | Admin | c) | 2020-06-17 | g) |  | c) | [9 empty] | AC
[9 empty] | d) | 30 | d) | [13 empty] | AC
|  |  | 9. Prk. 5 RJS - Prk 6 New Casay |  |  | Road Rehabilitation | 2.73 | Admin | a) | 350000 | a) |  | e) | 350000 | a) | 350000 | a) |  | c) | 3.37% | a) | 3 | On-going |  | AC
[9 empty] | b) | Obar | b) | 5/18/2020 | f) | - | b) | 350000 | b) |  | d) |  | b) | 30 |  |  | AC
[9 empty] | c) | Admin | c) | 2020-06-17 | g) |  | c) | [9 empty] | 1
[9 empty] | d) | 30 | d) | [13 empty] | 1
|  |  | 10. Dujali - Pawas - San Vicente |  |  | Road Rehabilitation | 4.42 | Admin | a) | 525000 | a) |  | e) | 525000 | a) | 525000 | a) |  | c) | 2.41% | a) | 3 | On-going |  | 1
[9 empty] | b) | Obar | b) | 5/18/2020 | f) | - | b) | 525000 | b) |  | d) |  | b) | 30 |  |  | 1
[9 empty] | c) | Admin | c) | 2020-07-02 | g) |  | c) | [9 empty] | 1
[9 empty] | d) | 45 | d) | [13 empty] | 1
|  |  | 11. Los Amigos 1 - Esperanza - Los Amigos 2 |  |  | Road Rehabilitation | 3.59 | Admin | a) | 19200000 | a) |  | e) | 19200000 | a) | 19200000 | a) |  | c) |  | a) |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. |  | 1
[9 empty] | b) |  | b) |  | f) | - | b) | 19200000 | b) |  | d) |  | b) |  |  |  | AC
[9 empty] | c) |  | c) |  | g) |  | c) | [9 empty] | FS
[9 empty] | d) |  | d) | [13 empty] | AC
|  |  | 12. San Miguel - Crossing Kinamayan |  |  | Road Rehabilitation | 2.8 | Admin | a) | 350000 | a) |  | e) | 350000 | a) | 350000 | a) | 22.58% | c) | 22.58% | a) | 6 | On-going |  | AC
[9 empty] | b) | Piad/ Obar | b) | 5/18/2020 | f) | 350000 | b) | 350000 | b) |  | d) |  | b) | 84 |  |  | AC
[9 empty] | c) | Admin | c) | 7/17/2020 | g) |  | c) | [9 empty] | 1
[9 empty] | d) | 60 | d) | [13 empty] | 1
|  |  | 13. Fd Rd 2 - Sto. Tomas - Magwawa |  |  | Road Rehabilitation | 10.21 | Admin | a) |  | a) |  | e) | - | a) |  | a) |  | c) | 3.37% | a) | 3 | On-going |  | 1
[9 empty] | b) |  | b) |  | f) | - | b) |  | b) |  | d) |  | b) | 30 |  |  | 1
[9 empty] | c) |  | c) |  | g) |  | c)
[9 empty] | d) |  | d) | [13 empty] | AC
|  |  | 14. Menzi - Balagunan - Tulalian |  |  | Road Rehabilitation | 10.63 | Admin | a) | 3720500 | a) |  | e) | 3720500 | a) | 3720500 | a) |  | c) |  | a) |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. |  | AC
[9 empty] | b) |  | b) |  | f) | 3720500 | b) | 3720500 | b) |  | d) |  | b) |  |  |  | AC
[9 empty] | c) |  | c) |  | g) |  | c) | [9 empty] | AC
[9 empty] | d) |  | d) | [13 empty] | AC
|  |  | 15. Jct. Bdry. Tagum - Talomo |  |  | Road Rehabilitation | 12.01 | Admin | a) | 1400000 | a) |  | e) | - | a) |  | a) | 3% | c) | 3.37% | a) | 3 | On-going |  | AC
[9 empty] | b) | Obar | b) | 5/18/2020 | f) | - | b) |  | b) |  | d) |  | b) | 30 |  |  | AC
[9 empty] | c) | Admin | c) | 2020-09-15 | g) |  | c) | [9 empty] | AC
[9 empty] | d) | 120 | d) | [13 empty] | AC
|  |  | 16. Rehab. of Anibongan-Salvacion-Cabay-angan Provincial Road with Drainage |  |  | Road Drainage rehabiliated | - | - | a) | 2000000 | a) | 2019-01-14 | e) | - | a) | 2000000 | a) | 100% | c) | 100% | a) | 1 | Completed 1/31/2020 |  | AC
[9 empty] | b) | Toquero | b) | 5/22/2019 | f) | 149 | b) | 2000000 | b) | - | d) | - | b) | 4 |  |  | AC
[9 empty] | c) | PEO | c) | 2019-08-04 | g) | 1/31/2020 | c) | [9 empty] | AC
[9 empty] | d) | 75 C.D | d) | 12/31/2019
| 2. Various of Local Roads & Drainage Development Project (Provincewide) |  |  |  |  | Road Drainage rehabiliated | km. | Admin | a) | 15000000 | [12 empty] | See projects listed below |  | AC
[9 empty] | b) | Paraguya | [14 empty] | AC
[9 empty] | c) | PEO | [14 empty] | AC
[9 empty] | d) | - | [14 empty] | AC
|  |  | Rehab. Of Dujali-Pawas-San Vicente Provincial Road |  |  | Road Drainage rehabiliated | km | Admin | a) | 2000000 | a) | - | e) | - | a) | 1102900 | a) | 80% | c) | 80% | a) | - | On-going |  | AC
| 2.1 | [7 empty] | b) | Toquero | b) | 2019-11-04 | f) | - | b) | 2000000 | b) | - | d) | - | b) | - |  |  | 1
[9 empty] | c) | PEO | c) | - | g) | - | c) | - | [8 empty] | 1
[9 empty] | d) | - | d) | - | [12 empty] | 1
|  |  | Rehab./Impv't. of Jct. highway Ising-Magsaysay Provincial Road with Drainage |  |  | Road Drainage rehabiliated | km | Admin | a) | 1500000 | a) | 2019-01-14 | e) | - | a) | 1500000 | a) | - | c) | - | a) | - | For Implementation 7/1/2020 |  | 1
| 2.2 | [7 empty] | b) | Toquero | b) | - | f) | - | b) | 1500000 | b) | - | d) | - | b) | - |  |  | 1
[9 empty] | c) | PEO | c) | - | g) | - | c) | - | [8 empty] | 1
[9 empty] | d) | 61 | d) | - | [12 empty] | 1
| 3. Various Water System Development Project (Provincewide) |  |  |  |  | Water System projects | km | Admin | a) | 9750000 | [12 empty] | See projects listed below (Note: 1.3M declared savings funded to other Water System Projects-AIP 2nd revision CY 2019) |  | AC
[9 empty] | b) | Varon/Imboy | [14 empty] | FS
[9 empty] | c) | PEO | [14 empty] | AC
[9 empty] | d) | - | [14 empty] | 1
| 3.1 | Construction of Water System Projects | [22 empty] | 1
1
|  |  | Impv't. of Potable Water System, Consolacion, Panabo City |  |  | Water System Projects | Households | - | a) | 500000 | a) | 2019-06-28 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. |  | 1
| 3.1.1 | [7 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[9 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | AC
[9 empty] | d) | - | d) | - | [12 empty] | 1
|  |  | Impv't. of Potable Water System, Tagbitan-ag, Samal Dist. |  |  | Water System Projects | Households | - | a) | 500000 | a) | 2019-06-19 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For implementation |  | 1
| 3.1.2 | [7 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[9 empty] | c) | - | c) | - | g) | - | c) | -
[9 empty] | d) | - | d) | - | [12 empty] | 1
|  |  | Impv't. of Potable Water System, San Antonio, babak, IGCS |  |  | Water System Projects | - | - | a) | 500000 | a) | 2019-06-25 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. |  | 1
| 3.1.3 | [7 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[9 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[9 empty] | d) | - | d) | - | [12 empty] | 1
|  |  | Impv't. of Potable Water System, Mambago-A, IGCS |  |  | Water System Projects | Households | - | a) | 500000 | a) | 2019-09-10 | e) | - | a) | 500000 | a) | - | c) | - | a) | - |  |  | 1
| 3.1.4 | [7 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - | For Implementation |  | 1
[9 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[9 empty] | d) | - | d) | - | [12 empty] | 1
|  |  | Construction of PWS, Brgy. Buenavista, Panabo City |  |  | Water System Projects | - | - | a) | 500000 | a) | June 19 ,2019 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For implementation |  | 1
| 3.1.5 | [7 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[9 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[9 empty] | d) | - | d) | - | [12 empty] | 1
|  |  | Construction of PWS, Brgy. Brgy. Kiotoy, Panabo City |  |  | Water System Projects | Households | Contract | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. |  | 1
| 3.1.6 | [7 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[9 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[9 empty] | d) | - | d) | - | [12 empty] | 1
|  |  | Construction of PWS, Brgy. Linusotan, Talikud, District, IGCS |  |  | Water System Projects | Households | - | a) | 1300000 | a) | 2019-10-23 | e) | - | a) | 1300000 | a) | - | c) | - | a) | - | Procurement on process |  | 1
| 3.1.7 | [7 empty] | b) | - | b) | - | f) | - | b) | 1300000 | b) | - | d) | - | b) | -
[9 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[9 empty] | d) | - | d) | - | [12 empty] | 1
|  |  | Rehab. of PWS, Brgy. San Miguel, Babak, IGCS |  |  | Water System Projects | Households | Contract | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. |  | 1
| 3.1.8 | [7 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[9 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[9 empty] | d) | - | d) | - | [12 empty] | 1
|  |  | Construction of PWS, Brgy. Cacao, Panabo City |  |  | Water System Projects | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For cancellation. Purchase of Geo-resistivity equipment but procurement still on process |  | 1
| 3.1.9 | [7 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | -
[9 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[9 empty] | d) | - | d) | - | [12 empty] | 1
|  |  | Rehabilitation of Potable Water System, Brgy. Pangubatan, kaputian Dist. IGCS |  |  | Water System Projects | Households | Contract | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Purchase Order # 19093434 |  | 1
| 3.2.0 | [7 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[9 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | AC
[9 empty] | d) | - | d) | - | [12 empty] | 1
| 4. Various Government Buildings and Facilities Development Project (Provincewide) |  |  |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of recipients | - | Admin | a) | 27000000 | [12 empty] | See projects listed below |  | 1
[9 empty] | b) | Medalla | [14 empty] | 1
[9 empty] | c) | PEO
[9 empty] | d) | - | [14 empty] | 1
|  |  | Const. of DDN Hospital Carmen Zone Annex Bldg. Phase 2, |  |  | Bldg. | - | Contract | a) | 3620000 | a) | 2019-06-28 | e) | - | a) | 3620000 | a) | - | c) | - | a) | - | For implementation (Winning Bidder - Digos Constrak Corp.) |  | 1
|  | 4.1 | [6 empty] | b) | - | b) | - | f) | - | b) | 3620000 | b) | - | d) | - | b) | - |  |  | 1
[9 empty] | c) | Digos Constrak Corp/ | c) | - | g) | - | c) | - | [8 empty] | 1
[9 empty] | d) | - | d) | - | [12 empty] | 1
| 5. Stimulus Projects for Various Barangays |  |  |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of brgys. | - | Admin | a) | 41500000 | [12 empty] | See projects listed below |  | 1
[9 empty] | b) | Medalla | [14 empty] | 1
[9 empty] | c) | PEO | [14 empty] | 1
[9 empty] | d) | - | [14 empty] | 1
| CARMEN | [23 empty] | AC
|  |  | Const. of Multi-Purpose Hall, La Paz, Carmen |  |  | Bldg. | - | - | a) | 500000 | a) | 2019-02-20 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Fund transferred to LGU March 28, 2019 |  | 1
| 1 | [7 empty] | b) | - | b) | 2019-08-16 | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[9 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[9 empty] | d) | - | d) | - | [12 empty] | 1
|  |  | Const. of Evacuation Center Ph. 3, Sto. Niño, Carmen |  |  | Bldg. | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Amended in the AIP 3rd revision CY 2019/ SB No. 4 CY 2019 changing the location to Purok !-c, Sto. Nino since the previous location was implemented by DPWH |  | 1
| 2 | [7 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[9 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[9 empty] | d) | - | d) | - | [12 empty] | 1
| 3 |  | Const. of Multi-Purpose Hall, Mangalcal, Carmen |  |  | Bldg. | - | - | a) | 500000 | a) | 2019-02-20 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Fund transfer to LGU Carmen, 3/28/2019 with check no. 2574953 and OR no. 0118982 |  | AC
[9 empty] | b) | - | b) | 2019-09-16 | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[9 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[9 empty] | d) | - | d) | - | [12 empty] | 1
| 4 |  | Rehab. of Multi-Purpose Hall, Guadalupe, Carmen |  |  | Bldg. | - | - | a) | 500000 | a) | 2019-02-20 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Fund transferred to LGU March 28, 2019
[9 empty] | b) | - | b) | 2019-08-15 | f) | - | b) | 500000 | b) | - | d) | - | b) | -
[9 empty] | c) | - | c) | 2019-11-13 | g) | - | c) | -
[9 empty] | d) | - | d) | -
| 5 |  | Const. of Multi-Purpose Hall, Mabuhay, Carmen |  |  | Bldg. | - | - | a) | 500000 | a) | 2019-02-20 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Fund transfer to LGU Carmen, 3/28/2019 with check no. 2574925 and OR no. 0118984
[9 empty] | b) | - | b) | 2019-08-16 | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | AC |  |  |  | 893809.45
[9 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | FS
[9 empty] | d) | - | d) | -
| 6 |  | Const. Canal Lining , Mabaus, Carmen |  |  | Canal lining | - | - | a) | 500000 | a) | 2019-02-20 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Fund transferred to LGU March 28, 2019 |  | FS
[9 empty] | b) | - | b) |  | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | AC
[9 empty] | c) | - | c) |  | g) | - | c) | - | [8 empty] | AC
[9 empty] | d) | - | d) | - | [12 empty] | AC
| 7 |  | Rehab. Of Evacuation Center, Alejal, Carmen |  |  | Bldg. | - | - | a) | 500000 | a) | 2019-02-20 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Fund transfer to LGU Carmen, 3/28/2019 with check no.2574949 and OR no. 0118991 |  | AC
[9 empty] | b) | - | b) | 2019-08-16 | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | AC
[9 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[9 empty] | d) | - | d) | - | [12 empty] | 1
| 8 |  | Compl. Of Evacuation Center, Tuganay, Carmen |  |  | Bldg. | - | - | a) | 500000 | a) | 2019-02-20 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Fund transfer to LGU Carmen, 3/28/2019 with check no. 2574947 and OR no. 0118995 |  | 1
[9 empty] | b) | - | b) | 2019-08-16 | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | AC
[9 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[9 empty] | d) | - | d) | - | [12 empty] | 1
| 9 |  | Const. of Multi-Purpose hall, Ising, Carmen |  |  | Bldg. | - | - | a) | 500000 | a) | 2019-02-20 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Fund transferred to LGU March 28, 2019 |  | 1
[9 empty] | b) | - | b) |  | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | AC
[9 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[9 empty] | d) | - | d) | - | [12 empty] | 1
| 10 |  | Rehab. of Multi-Purpose hall, Cebulano, Carmen |  |  | Bldg. | - | - | a) | 500000 | a) | 2019-02-20 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Fund transferred to LGU March 28, 2019 |  | 1
[9 empty] | b) | - | b) | 2019-08-16 | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | AC
[9 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[9 empty] | d) | - | d) | - | [12 empty] | 1
| PANABO CITY | [23 empty] | 1
| 11 |  | Rehab. Of Multi-Purpose Hall, Kasilak, Panabo City |  |  | Bldg. | - | Contract | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Purchase Request # 19115111 |  | AC
[9 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[9 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[9 empty] | d) | - | d) | - | [12 empty] | 1
| 12 |  | Rehab. Of Multi-Purpose Hall, New Malitbog, Panabo City |  |  | Bldg. | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Amended in AIP 3rd revsion CY 2019 to change the project to Construction of Potable Water System because the original project will be funded by LGU, Panabo City (Brgy. resolution no. 25 series of 2019 dated Aug. 13, 2019 submitted) |  | AC
[9 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[9 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
1
AC
[9 empty] | d) | - | d) | - | [12 empty] | 1
| 13 |  | Desilting of Canal, New Pandan, Panabo City |  |  | Canal lining | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. |  | 1
[9 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[9 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | AC
[9 empty] | d) | - | d) | - | [12 empty] | 1
| 14 |  | Const. Of Multi-Purpose Hall, Waterfall, Panabo City |  |  | Bldg. | - | Contract | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Purchase Request # 19125303 |  | 1
[9 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[9 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | AC
[9 empty] | d) | - | d) | - | [12 empty] | 1
| 15 |  | Concreting of Brgy. Road @ Prk. Guyabano, Cagangohan, Panabo City |  |  | Road | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Amended in AIP 3rd revision to change the project to Rehab of Evacuation Center because the original project has no deed of donation.(Brgy. resolution no 41 series of 2019 dated Aug. 16, 2019 submitted |  | 1
[9 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[9 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | AC
1
[9 empty] | d) | - | d) | - | [12 empty] | 1
| 16 |  | Rehab. Of Evacuation Center, J.P. Laurel, Panabo City |  |  | Bldg. | - | Contract | a) | 500000 | a) | 2019-10-23 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Purchase Order # 2020031248 |  | 1
` | [8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | AC
[9 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[9 empty] | d) | - | d) | - | [12 empty] | 1
| 17 |  | Const. Of Multi-Purpose Hall, Buenavista, Panabo City |  |  | Bldg. | - | Contract | a) | 500000 | a) | 2019-10-18 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Purchase Order # 2020031248 |  | 1
[9 empty] | b) | - | b) | - | f) |  | b) | 500000 | b) | - | d) | - | b) | - |  |  | AC
[9 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[9 empty] | d) | - | d) | - | [12 empty] | 1
| 18 |  | Rehab. Of Multi-Purpose Hall, San Francisco, Panabo City |  |  | Bldg. | - | Contract | a) | 500000 | a) | 2019-10-18 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Purchase Order # 2020031248 |  | 1
` | [8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | AC
[9 empty] | c) | - | c) | - | g) |  | c) | - | [8 empty] | 1
[9 empty] | d) | - | d) | - | [12 empty] | 1
| 19 |  | Rehab. Of Evacuation Center, Datu Abdul Dadia, Panabo City |  |  | Bldg. | - | Contract | a) | 500000 | a) | 2019-10-18 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Purchase Order # 2020031248 |  | 1
[9 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | AC
[9 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[9 empty] | d) | - | d) | - | [12 empty] | 1
| 20 |  | Impv't./Beautification of Brgy. Grounds, Quezon, Panabo City |  |  | Ground Dev't. | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Re aligned to other stimulus projects that needs additional funding |  | 1
` | [8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | AC
[9 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[9 empty] | d) | - | d) | - | [12 empty] | 1
| 21 |  | Const. of Women Livelihood Center Bldg. , Gredu, Panabo City |  |  | Bldg. | - | - | a) | 500000 | a) | 2019-03-28 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Fund transfer to LGU - 3/28/2019 with check no. 2574926 and OR no. 0166517 - March 28, 2019 |  | 1
[9 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | AC
[9 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[9 empty] | d) | - | d) | - | [12 empty] | 1
| 22 |  | Const. of Canal Lining at Purok 5, Salvacion, Panabo City |  |  | Bldg. | - | Contract | a) | 500000 | a) | 2019-10-18 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Purchase Request # 19104835 |  | 1
` | [8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | AC
[9 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[9 empty] | d) | - | d) | - | [12 empty] | 1
| 23 |  | Rehab. Of Health Center, New Visayas, Panabo City |  |  | Bldg. | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Re aligned to other stimulus projects that needs additional funding |  | 1
[9 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | AC
[9 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[9 empty] | d) | - | d) | - | [12 empty] | 1
| 24 |  | Rehab. Of Multi-Purpose Hall, Little Panay, Panabo City |  |  | Bldg. | - | Contract | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Purchase Request # 19125320 |  | 1
` | [8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | AC
[9 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[9 empty] | d) | - | d) | - | [12 empty] | 1
| 25 |  | Rehab. Of Brgy. Health Center, Dalisay, Panabo City |  |  | Bldg. | - | Contract | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Purchase Request # 19125279 |  | 1
[9 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | AC
[9 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[9 empty] | d) | - | d) | - | [12 empty] | 1
| 26 |  | Const. of Multi-Purpose Hall, Southern Davao, Panabo City |  |  | Bldg. | - | Contract | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Purchase Request # 19125279 |  | 1
` | [8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | AC
[9 empty] | c) | - | c) | - | g) |  | c) | - | [8 empty] | 1
[9 empty] | d) | - | d) | - | [12 empty] | 1
| STO. TOMAS | [23 empty] | 1
| 27 |  | Rehab. Of Evacuation Center, Casig-ang, Sto. Tomas |  |  | Bldg. | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | POW preparation on-going c/o Engr. Uy |  | AC
[9 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[9 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[9 empty] | d) | - | d) | - | [12 empty] | 1
` | 28 |  | Const. of Brgy. Tibal-og Health Center, Tibal-og, Sto. Tomas |  |  | Bldg. | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | POW preparation completed amounting t oP1,550,000.00. To request for additional funds in order to complete the project to be functional |  | AC
[9 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[9 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[9 empty] | d) | - | d) | - | [12 empty] | 1
| 29 |  | Compl.of Brgy. Public Market, La Libertad, Sto. Tomas |  |  | Bldg. | - | - | a) | 500000 | a) |  | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Fund transfer to LGU - 6/26/219 with check no. 2575131 and OR no. 0557457 Completed/ PCR for submission by LGU |  | AC
[9 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[9 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[9 empty] | d) | - | d) | - | [12 empty] | 1
` | 30 |  | Rehab. Of Evacuation Center, New Visayas, Sto. Tomas |  |  | Bldg. | - | - | a) | 500000 | a) |  | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Fund transfer to LGU - 6/26/219 with check no. 2575132 and OR no. 0557455 For implementation |  | AC
[9 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[9 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[9 empty] | d) | - | d) | - | [12 empty] | 1
| 31 |  | Rehab. Of Multi-Purpose Hall, San Vicente, Sto. Tomas |  |  | Bldg. | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Fund transferred to LGU July 5, 2019 |  | AC
[9 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[9 empty] | c) | - | c) | - | g) |  | c) | - | [8 empty] | 1
[9 empty] | d) | - | d) | - |  | - | [10 empty] | 1
` | 32 |  | Rehab. Of Multi-Purpose Hall, Salvacion, Sto. Tomas |  |  | Bldg. | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. |  | AC
[9 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[9 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[9 empty] | d) | - | d) | - | [12 empty] | 1
| 33 |  | Rehab. Of Multi-Purpose Hall, Pantaron, Sto. Tomas |  |  | Bldg. | - | - | a) | 500000 | a) |  | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Amended in AIP 3rd revision CY 2019 / SB No. 4 CY 2019 increasing the project cost to P550,000.00 |  | AC
[9 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[9 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[9 empty] | d) | - | d) | - | [12 empty] | 1
` | 34 |  | Rehab. Of Multi-Purpose Hall, Magwawa, Sto. Tomas |  |  | Bldg. | sq.m | Contract | a) | 500000 | a) | June 19 2019 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Purchase Request # 19115111 |  | AC
[9 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[9 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[9 empty] | d) | - | d) | - | [12 empty] | 1
| 35 |  | Compl. Of Multi-Purpose Hall, San Jose, Sto. Tomas |  |  | Bldg. | - | - | a) | 500000 | a) |  | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Amended in AIP 3rd revision CY 2019 / SB No. 4 CY 2019 increasing the project cost to P600,000.00 |  | AC
[9 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[9 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[9 empty] | d) | - | d) | - | [12 empty] | 1
` | 36 |  | Const. of Evacuation Center, Bobongon, Sto. Tomas |  |  | Bldg. | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Re aligned to other stimulus projects that needs additional funding |  | AC
[9 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[9 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[9 empty] | d) | - | d) | - | [12 empty] | 1
| 37 |  | Rehab. Of Brgy. Road, Lunga-og, Sto. Tomas |  |  | Bldg. | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Amended in AIP 3rd revision CY 2019 / SB No. 4 CY 2019 increasing the project cost to P600,000.00 |  | AC
[9 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[9 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[9 empty] | d) | - | d) | - | [12 empty] | 1
` | 38 |  | Rehab. Of Multi-Purpose Hall, New Katipunan, Sto. Tomas |  |  | Bldg. | sq.m | Contract | a) | 500000 | a) | 2019-06-07 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Purchase Request # 19125279 |  | AC
[9 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[9 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[9 empty] | d) | - | d) | - | [12 empty] | 1
| 39 |  | Rehab. Of Multi-Purpose Hall, San Miguel, Sto. Tomas |  |  | Bldg. | sq.m | Contract | a) | 500000 | a) | 2019-06-07 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Purchase Request # 19115111 |  | AC
[9 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[9 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[9 empty] | d) | - | d) | - | [12 empty] | 1
` | 40 |  | Rehab. Of Multi-Purpose Hall, Talomo, Sto. Tomas |  |  | Bldg. | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Fund transfer to LGU - 6/26/2019 with check no. 2575130 and OR no. 0557456 For implementation |  | AC
[9 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[9 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[9 empty] | d) | - | d) | - | [12 empty] | 1
| IGCS | [23 empty] | AC
| 41 |  | Concreting of Brgy. Road From Prk. 3 to Prk. 5, Catagman, IGCS |  |  | Road | km | Contract | a) | 500000 | a) | 2019-01-14 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For implementation |  | 1
[9 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[9 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
` | [8 empty] | d) | - | d) | - | [12 empty] | AC
| 42 |  | Rehab. Of Multi-Purpose Hall, San Jose, IGCS |  |  | Bldg. | sq.m | Admin | a) | 500000 | a) | 2019-03-25 | e) | - | a) | 500000 | a) | 100% | c) | 100% | a) | 3 | Completed 3/22/2020 |  | 1
[9 empty] | b) | Porras | b) | 2019-01-02 | f) | - | b) | 500000 | b) | - | d) | 0% | b) | 44 |  |  | 1
[9 empty] | c) | PEO | c) | 2020-03-22 | g) | 3/22/2020 | c) | - | [8 empty] | 1
[9 empty] | d) | 80 CD | d) | - | [12 empty] | AC
| 43 |  | Electrification at Sitio Trinidad, Bandera, IGCS |  |  | Elect. | Households | Contract | a) | 500000 | a) | 2019-03-25 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Purchase Request # 19031251 |  | 1
[9 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[9 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
` | [8 empty] | d) | - | d) | - | [12 empty] | AC
| 44 |  | Rehab. Of Multi-Purpose Hall, Del Monte, IGCS |  |  | Bldg. | - | Admin | a) | 500000 | a) | 2019-05-29 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Pending/ activity undertaken by DPWH |  | 1
[9 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[9 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[9 empty] | d) | - | d) | - | [12 empty] | AC
| 45 |  | Electrification at Upper Purok Rosal, Tagbaobo, IGCS |  |  | Elect. | Households | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Purchase Order # 2020010002 (3E Electrical Sales & Services) |  | 1
[9 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[9 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
` | [8 empty] | d) | - | d) | - | [12 empty] | AC
| 46 |  | Const. Of Multi-Purpose Hall, Mambago-B, IGCS |  |  | Bldg. | sq.m | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | 100% | c) | 97.59% | a) | 5 | Suspended effective April 5, 2020 due to issued Executive Order No. 31, series of 2020 the province of Davao del Norte in response to the State of Public Health Emergency and State of National Calamity (COVID19 Pandemic). |  | 1
[9 empty] | b) | Roque | b) | 2019-10-18 | f) | 64 CD | b) | 500000 | b) | 99.48% | d) | -1.89% | b) | 22 |  |  | 1
[9 empty] | c) | PEO | c) | 2019-12-27 | g) | - | c) | - | [8 empty] | 1
[9 empty] | d) | 60 CD | d) | 2020-03-29 | [12 empty] | AC
| 47 |  | Const. Of Multi-Purpose Hall, San Antonio, IGCS |  |  | Bldg. | sq.m | - | a) | 500000 | a) | 2019-06-19 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For implementation Proposed date started 3/24/2020 |  | 1
[9 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[9 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
` | [8 empty] | d) | - | d) | - | [12 empty] | AC
| 48 |  | Rehab. Of Water System Intake Box and Pipeline, Pangubatan, IGCS |  |  | Water System | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Plan and Pow completed. Waiting of deed of donation |  | 1
[9 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[9 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[9 empty] | d) | - | d) | - | [12 empty] | AC
| 49 |  | Const. Of Multi-Purpose Hall, Cogon (Talicud), IGCS |  |  | Bldg. | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For implementation |  | 1
[9 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[9 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
` | [8 empty] | d) | - | d) | - | [12 empty] | AC
| 50 |  | Installation of Pipelines, Libertad, IGCS |  |  | Water System | Households | - | a) | 500000 | a) | 2019-03-25 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For implementation |  | 1
[9 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[9 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[9 empty] | d) | - | d) | - | [12 empty] | AC
| 51 |  | Rehab. Of Evacuation Center, Libuak, IGCS |  |  | Bldg. | - | - | a) | 500000 | a) | 2019-05-29 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For implementation |  | 1
[9 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[9 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
` | [8 empty] | d) | - | d) | - | [12 empty] | AC
| 52 |  | Const. of Water System Project, Pob. Kaputian, IGCS |  |  | Water System | Households | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For implementation |  | 1
[9 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[9 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[9 empty] | d) | - | d) | - | [12 empty] | AC
| 53 |  | Rehab. Of Potable Water System, San Isidro, Babak, IGCS |  |  | Water System | Households | - | a) | 500000 | a) | 2019-06-19 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For implementation |  | 1
[9 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[9 empty] | c) | - | c) | - | g) |  | c) | - | [8 empty] | 1
` | [8 empty] | d) | - | d) | - | [12 empty] | AC
| 54 |  | Rehab. Of Potable Water System, San Miguel, IGCS |  |  | Water System | Households | - | a) | 500000 | a) | 2019-02-28 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For implementation |  | 1
[9 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[9 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[9 empty] | d) | - | d) | - | [12 empty] | AC
| 55 |  | Const. of Water System Ph.II, San Remegio, IGCS |  |  | Water System | Households | - | a) | 500000 | a) | 2019-05-29 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For implementation |  | 1
[9 empty] | b) | Porras | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[9 empty] | c) | Admin | c) | - | g) | - | c) | - | [8 empty] | 1
` | [8 empty] | d) | - | d) | - | [12 empty] | AC
| 56 |  | Electrificatio at Prk. 1,3,4, 6,7 & 8, Licup, IGCS |  |  | Elect. | Households | - | a) | 500000 | a) | 2019-02-20 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For implementation |  | 1
[9 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[9 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[9 empty] | d) | - | d) | - | [12 empty] | AC
| 6. Rural Electrification Project (Provincewide) |  |  |  |  | Powerlines/posts installed & rehabilitated | Households | - | a) | 5000000 | [12 empty] | See projects listed below |  | 1
[9 empty] | b) | Kim Pao Lu | [14 empty] | 1
[9 empty] | c) | - | [14 empty] | 1
` | [8 empty] | d) | - | [14 empty] | AC
|  |  | Rural Electrification at Sitio Sagrada, Pob. Kaputian, IGCS |  |  | Elect. | Households | - | a) | 1000000 | a) | - | e) | - | a) | 1000000 | a) | - | c) | - | a) | - | Purchase Request # 19031251 |  | 1
|  | 6.1 | [6 empty] | b) | P.Bueno | b) | - | f) | - | b) | 1000000 | b) | - | d) | - | b) | - |  |  | 1
[9 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[9 empty] | d) | - | d) | - | [12 empty] | AC
| K. | 5% CALAMITY FUND CY 2019 | [22 empty] | 1
|  | DISASTER PREVENTION AND MITIGATION | [22 empty] | 1
|  | Flood Control and Slope Protection | [22 empty] | 1
` | 1 |  | Revitment of Dike and Slope Proection |  |  | Protection dikes/slope protection | ln.m | Admin | a) | 3000000 | [12 empty] | See project listed below |  | AC
[9 empty] | b) | - | [14 empty] | 1
[9 empty] | c) | - | [14 empty] | 1
[9 empty] | d) | - | [14 empty] | 1
` |  |  |  | Repair/Rehab. Of Upper Tuganay Dike |  | creeks and canals deislted | - | - | a) | 1000000 | a) | 2019-08-15 | e) | - | a) | 1000000 | a) | 90% | c) | 90% | a) | 9 | On-going |  | AC
|  |  | 1.1 | [5 empty] | b) | Toquero | b) | 2019-08-19 | f) | - | b) | 1000000 | b) | - | d) |  | b) | 80 |  |  | 1
[9 empty] | c) | Admin | c) | 2019-09-29 | g) |  | c) | - | [8 empty] | 1
[9 empty] | d) | 59 C.D | d) | - | [12 empty] | 1
|  |  | Improvement of roads, drainage and canal |  |  | Protection dikes/slope protection | - | - | a) | 3000000 |  |  |  | - | [8 empty] | See project listed below |  | 1
|  | 2 | [6 empty] | b) | Paraguya | [14 empty] | 1
[9 empty] | c) | PEO | [14 empty] | 1
[9 empty] | d) | - | [14 empty] | AC
|  |  |  | Rehab./Impv't. of Prk. 1 - Prk. 2 Sitio Pawas Provincial Road |  | Road | km | Admin | a) | 1500000 | a) | 2019-07-23 | e) | - | a) | 1500000 | a) | 100% | c) | 100% | a) | 2 | Completed 12/15/2019 |  | 1
|  |  | 2.1 | [5 empty] | b) | Sanchez | b) | 2019-08-05 | f) |  | b) | 1500000 | b) | - | d) | 0% | b) | 10 |  |  | 1
` | [8 empty] | c) | Admin | c) | 2019-09-28 | g) | 12/15/2020 | c) | - | [8 empty] | AC
[9 empty] | d) | 55 | d) | - | [12 empty] | 1
` | CALAMITY/ OPLAN CANAL | [21 empty] | Completed 6/30/2020 |  | AC
|  |  |  | Repair of Damaged Drainage/ Creek along Abucay Creek |  |  | - | - | a) | 1320000 | a) |  | e) |  | a) |  | a) | 100% | c) | 100% | a) |  |  |  | 1
|  |  | 1 | [5 empty] | b) | Ganaba | b) | 2019-10-01 | f) | 182 | b) |  | b) |  | d) |  | b) |  |  |  | 1
[9 empty] | c) | Admin | c) | 2019-12-02 | g) | 6/30/2020 | c) | [9 empty] | 1
[9 empty] | d) | 65 C.D | d) | 2019-12-31 | [12 empty] | AC
|  |  |  | Repair of Damaged Drainage Creek along Panabo River |  |  |  |  | a) | 665000 | a) |  | e) |  | a) |  | a) | 15.3% | c) | 15.3% | a) |  | On-going/ Waiting for P.O rental of equipment |  | 1
|  |  | 2 | [5 empty] | b) | Alconera | b) | 2019-11-15 | f) |  | b) |  | b) |  | d) |  | b) |  |  |  | 1
[9 empty] | c) | Admin | c) | 2020-01-27 | g) |  | c) | [9 empty] | 1
` | [8 empty] | d) | 73 C.D | d) | [13 empty] | AC
|  |  |  | Repair of Damaged Drainage/Creek along Tuganay-Ising River |  |  |  |  | a) | 1540500 | a) |  | e) |  | a) |  | a) | 25.6% | c) | 23.6% | a) | 3 | On-going/ Waiting for P.O rental of equipment |  | 1
|  |  | 3 | [5 empty] | b) | Ganaba | b) | 2019-11-15 | f) |  | b) |  | b) |  | d) | -2% | b) | 66 |  |  | 1
[9 empty] | c) | Admin | c) | 2020-05-15 | g) |  | c) | [9 empty] | 1
[9 empty] | d) | 182 C.D | d) | [13 empty] | AC
|  |  |  | Repair of Damaged Drainage/ Creeks along San Miguel NIA Road |  |  |  |  | a) | 470000 | a) |  | e) | 251 | a) | 470000 | a) | 100% | c) | 100% | a) | 3 | Completed 5/28/2020 |  | 1
|  |  | 4 | [5 empty] | b) | Nasol | b) | 8/1/2019 | f) |  | b) | 470000 | b) |  | d) |  | b) | 66 |  |  | 1
[9 empty] | c) | Admin | c) | 9/16/2019 | g) | 5/28/2020 | c) | [9 empty] | 1
` | [8 empty] | d) |  | d) | 5/28/2020 | [12 empty] | AC
|  |  |  | Repair of Damaged Drainage/ Creeks along Sadpodon Creek |  |  |  |  | a) | 470000 | a) |  | e) |  | a) |  | a) |  | c) |  | a) |  | For implementation/ Waiting for Excavation (Floating) |  | 1
|  |  | 5 | [5 empty] | b) |  | b) |  | f) |  | b) |  | b) |  | d) |  | b) |  |  |  | 1
[9 empty] | c) | Admin | c) |  | g) |  | c) | [9 empty] | 1
[9 empty] | d) |  | d) | [13 empty] | AC
` | L. | SUPPLEMENTAL BUDGET NO. 3 CY 2019 | [22 empty] | AC
|  | LOCALLY FUNDED PROGRAM/PROJECTS- 20% DEVELOPMENT FUND | [22 empty] | 1
|  | INFRASTRUCTURE DEVELOPMENT PROGRAM | [22 empty] | 1
|  | 1. 8918/ Various Local Roads & Drainage Development Project Construction in Progress- Infrastructure Assets | [22 empty] | 1
` |  | ■ |  | Rehabilitation of Dujali-Pawas-San Vicente Provincial Road, B.E. Dujali |  | Road | km | - | a) |  | a) | 8/5/2019 | e) | - | a) | 0 | a) | 80% | c) | 80% | a) | - | The amount was reduced to P1,102,900.00 - On-going |  | AC
|  |  | 1.1 | [5 empty] | b) | Toquero | b) | 11/4/2019 | f) | - | b) | 0 | b) | - | d) | - | b) | - |  |  | 1
[9 empty] | c) | Admin | c) | - | g) | - | c) | - | [8 empty] | 1
[9 empty] | d) | - | d) | - | [12 empty] | 1
2. 8918/ VariousWater System Development Project Construction in Progress- Infrastructure Assets
|  | ■ |  | Improvement of Potable Water System at Brgy. Mambago- A, Samal District, IGACOS |  | Water System | Households | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | (Amended in the AIP 2nd Revision to change the location from Peñaplata to Samal District) PO approved September 2, 2019 |  | 1
|  |  | 2.1 | [5 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[9 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[9 empty] | d) | - | d) | - | [12 empty] | 2
|  | ■ |  | Rehabilitation of Potable Water System at Brgy. San Miguel, Samal District, IGACOS |  | Water System | Households | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For implementation |  | 1
|  |  | 2.2 | [5 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[9 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[9 empty] | d) | - | d) | - | [12 empty] | 2
|  | ■ |  | Construction of Potable Water System at Brgy.Linusotan, Kaputian District, IGACOS |  | Water System | Households | - | a) | 1300000 | a) | - | e) | - | a) | 1300000 | a) | - | c) | - | a) | - | (Additional 800,000.00 from Const. of PWS in purok 2, Pag-asa, Kapalong which was funded by OPAPP CY 2018) (amended) For allotment- October 15, 2019 |  | 1
|  |  | 2.3 | [5 empty] | b) | - | b) | - | f) | - | b) | 1300000 | b) | - | d) | - | b) | - |  |  | 1
[9 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[9 empty] | d) | - | d) | - | [12 empty] | 2
|  | DISASTER REHABILITATION & RECOVERY PROGRAM Building Back Better Project | [22 empty] | 1
|  | 1. Repairs & Maintenance- Infrastructure Assets | [22 empty] | 1
|  | ■ |  | Disiltation of Mactan River (Ph. II) |  | Desiltation | - | - | a) | 500000 | a) | 5/8/2019 | e) | - | a) | 500000 | a) | 100% | c) | 100% | a) | - | Completed |  | 1
|  |  | 1.1 | [5 empty] | b) | Toquero | b) | 7/29/2019 | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[9 empty] | c) | PEO | c) | 9/27/2019 | g) | 11/30/2020 | c) | - | [8 empty] | 1
[9 empty] | d) | 60 | d) | 11/30/2019 | [12 empty] | 1
|  | 2. Property, Plant and Equipmen Construction in Progress- Infrastructure Assets | [22 empty] | 1
|  |  |  | Rehabilitation of Dujali-Balisong-Magupising Provincial Road |  | Road | km | Admin | a) | 1280000 | a) | - | e) | 27 | a) | 1280000 | a) | 100% | c) | 100 | a) | - | Completed 6/15/2020 |  | 2
|  |  | 2.1 | [5 empty] | b) | Mellomida | b) | 2019-12-02 | f) | 17 | b) | 1280000 | b) | 100 | d) | 0% | b) | - |  |  | 1
[9 empty] | c) | PEO | c) | 2020-02-03 | g) | 6/15/2020 | c) | - | [8 empty] | 1
[9 empty] | d) | - | d) | 6/15/2020 | [12 empty] | 1
| M. | SUPPLEMENTAL BUDGET NO. 4 CY 2019
INFRASTRUCTURE DEVELOPMENT PROGRAM
LOCALLY FUNDED PROGRAMS/ PROJECTS GENERAL FUND PROPER
|  | 1 | PEACE AND ORDER PROGRAM/1914 Construction in Progress- Land Improvements | [21 empty] | 2
|  | ■ |  | Rehabilitation of San Jose- Sitio Mahayahay-Magwawa Provincial Road, Sto. Tomas |  | Road | - | - | a) | 1000000 | a) | - | e) | - | a) | 1000000 | a) | - | c) | - | a) | - | POW preparation on-going c/o South District |  | 1
|  |  | 1.1 | [5 empty] | b) | - | b) | - | f) | - | b) | 1000000 | b) | - | d) | - | b) | - |  |  | 1
[9 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[9 empty] | d) | - | d) | - | [12 empty] | 1
|  | 2 | 8918/ Various Local Roads and Drainage Development Project Construction in Progress- Infrastructure Assets | [21 empty] | 1
|  | ■ |  | Rehabilitation of Local Roads at Dalisay-Manay Road Section, Panabo City |  | Road | - | - | a) | 246100 | a) | - | e) | - | a) | 246100 | a) | - | c) | - | a) | - | For implementation |  | 1
|  |  | 2.1 | [5 empty] | b) | - | b) | - | f) | - | b) | 246100 | b) | - | d) | - | b) | - |  |  | 2
[9 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[9 empty] | d) | - | d) | - | [12 empty] | 1
|  | ■ |  | Rehabilitation of Local Roads at Sta. Cruz-Jct. Tagpore-Buenavista Raod Section, Panabo City |  | Road | - | - | a) | 431000 | a) | - | e) | - | a) | 431000 | a) | - | c) | - | a) | - | For implementation |  | 1
|  |  | 2.2 | [5 empty] | b) | - | b) | - | f) | - | b) | 431000 | b) | - | d) | - | b) | - |  |  | 2
[9 empty] | c) | - | c) | - | g) |  | c) | - | [8 empty] | 1
[9 empty] | d) | - | d) | - | [12 empty] | 1
|  | ■ |  | Rehabilitation of Local Roads at Taba-Bucana Road Section, Taba, Carmen |  | Road | - | - | a) | 220000 | a) | - | e) | - | a) | 220000 | a) | - | c) | - | a) | - | For implementation |  | 1
|  |  | 2.3 | [5 empty] | b) | - | b) | - | f) | - | b) | 220000 | b) | - | d) | - | b) | - |  |  | 2
[9 empty] | c) | - | c) | - | g) | - | c) | -
[9 empty] | d) | - | d) | -
|  | 3 | 8918/ Stimulus Projects for Various Barangays Construction in Progress- Infrastructure Assets
|  | ■ |  | Concreting of Brgy. Road Canal, Dujali, B.E. Dujali |  | Road | - | contract | a) | 650000 | a) | - | e) | - | a) | 650000 | a) | - | c) | - | a) | - | For implementation
|  |  | 3.1 | [5 empty] | b) | - | b) | - | f) | - | b) | 650000 | b) | - | d) | - | b) | - |  |  | 1
[9 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[9 empty] | d) | - | d) | - | [12 empty] | 2
|  | ■ |  | Desilting and Conretign of Drainage-Main Collector Canal, New Casay, B.E. Dujali |  | Desiltation | - | contract | a) | 650000 | a) | - | e) | - | a) | 650000 | a) | - | c) | - | a) | - | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. |  | 1
|  |  | 3.2 | [5 empty] | b) | - | b) | - | f) | - | b) | 650000 | b) | - | d) | - | b) | - |  |  | 1
[9 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[9 empty] | d) | - | d) | - | [12 empty] | 2
|  | ■ |  | Concreting of Drainage, Tanglaw, B.E., Dujali |  | Drainage | - | contract | a) | 1200000 | a) | - | e) | - | a) | 1200000 | a) | - | c) | - | a) | - | For implementation |  | 1
|  |  | 3.3 | [5 empty] | b) | - | b) | - | f) | - | b) | 1200000 | b) | - | d) | - | b) | - |  |  | 1
[9 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[9 empty] | d) | - | d) | - | [12 empty] | 2
|  |  |  | Construction of Potable Water System, New Malitbog, Panabo City |  | Water System | Households | contract | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. |  | 1
|  |  | 3.4 | [5 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[9 empty] | c) | - | c) | - | g) | - | c) | -
[9 empty] | d) | - | d) | -
|  | ■ |  | Construction of Water System Project, Poblacion Kaputian, Samal |  | Water System | Households | contract | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For implementation
|  |  | 3.5 | [5 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | -
[9 empty] | c) | - | c) | - | g) | - | c) | -
[9 empty] | d) | - | d) | - | [12 empty] | 1
|  | ■ |  | Construction of Canal Lining at Prk. 5, Salvacion, Panabo City |  |  |  | contract | a) | 600000 | a) | - | e) | - | a) | 600000 | a) | - | c) | - | a) | - | For implementation |  | 1
|  |  | 3.6 | [5 empty] | b) | - | b) | - | f) | - | b) | 600000 | b) | - | d) | - | b) | - |  |  | 1
[9 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | FS
[9 empty] | d) | - | d) | -
|  | ■ |  | Rehabilitation of Brgy. Road at Lunga-og. Sto. Tomas |  |  |  | contract | a) | 600000 | a) | - | e) | - | a) | 600000 | a) | - | c) | - | a) | - | For implementation
|  |  | 3.7 | [5 empty] | b) | - | b) | - | f) | - | b) | 600000 | b) | - | d) | - | b) | -
[9 empty] | c) | - | c) | - | g) | - | c) | -
[9 empty] | d) | - | d) | -
|  | 4 | 8918/ Stimulus Projects for Various Barangays Construction in Progress- Bldgs. & Other Structures
|  | ■ |  | Construction of Evacuation Center at Purok 1-C Brgy. Sto. Niño, Carmen |  |  |  | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For implementation
|  |  | 4.1 | [5 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | -
[9 empty] | c) | - | c) | - | g) |  | c) | -
[9 empty] | d) | - | d) | -
|  | ■ |  | Construction of Multi-Purpose Hall, Waterfall, Panabo City |  |  |  | - | a) | 1050000 | a) | - | e) | - | a) | 1050000 | a) | - | c) | - | a) | - | For implementation
|  |  | 4.2 | [5 empty] | b) | - | b) | - | f) | - | b) | 1050000 | b) | - | d) | - | b) | -
[9 empty] | c) | - | c) | - | g) | - | c) | -
[9 empty] | d) | - | d) | -
|  |  |  | Rehabilitation of Multi-Purpose Hall, San Francisco, Panabo City |  |  |  | - | a) | 600000 | a) | - | e) | - | a) | 600000 | a) | - | c) | - | a) | - | For implementation
|  |  | 4.3 | [5 empty] | b) | - | b) | - | f) | - | b) | 600000 | b) | - | d) | - | b) | -
[9 empty] | c) | - | c) | - | g) | - | c) | -
[9 empty] | d) | - | d) | -
|  | ■ |  | Rehabilitation of Evacuation Center at Datu Abdul Dadia, Panabo City |  |  |  | - | a) | 650000 | a) | - | e) | - | a) | 650000 | a) | - | c) | - | a) | - | For implementation
|  |  | 4.4 | [5 empty] | b) | - | b) | - | f) | - | b) | 650000 | b) | - | d) | - | b) | -
[9 empty] | c) | - | c) | - | g) | - | c) | -
[9 empty] | d) | - | d) | -
|  |  |  | Construction of Multi-Purpose Hall, Buenavista, Panabo City |  |  |  | - | a) | 1050000 | a) | - | e) | - | a) | 1050000 | a) | - | c) | - | a) | - | For implementation
|  |  | 4.5 | [5 empty] | b) | - | b) | - | f) | - | b) | 1050000 | b) | - | d) | - | b) | -
[9 empty] | c) | - | c) | - | g) | - | c) | -
[9 empty] | d) | - | d) | -
|  |  |  | Rehabilitation of Multi-Purpose Hall, Llittle Panay, Panabo City |  |  |  | - | a) | 550000 | a) | - | e) | - | a) | 550000 | a) | - | c) | - | a) | - | For implementation
|  |  | 4.6 | [5 empty] | b) | - | b) | - | f) | - | b) | 550000 | b) | - | d) | - | b) | -
[9 empty] | c) | - | c) | - | g) | - | c) | -
[9 empty] | d) | - | d) | -
|  |  |  | Rehabilitation of Multi-Purpose Hall, Pantaron, Sto. Tomas |  |  |  | - | a) | 550000 | a) | - | e) | - | a) | 550000 | a) | - | c) | - | a) | - | For implementation
|  |  | 4.7 | [5 empty] | b) | - | b) | - | f) | - | b) | 550000 | b) | - | d) | - | b) | -
[9 empty] | c) | - | c) | - | g) | - | c) | -
[9 empty] | d) | - | d) | -
|  | ■ |  | Rehabilitation of Multi-Purpose Hall, Salvacion, Sto. Tomas |  |  |  | - | a) | 1000000 | a) | - | e) | - | a) | 1000000 | a) | - | c) | - | a) | - | POW preparation on-going c/o PDPM
|  |  | 4.8 | [5 empty] | b) | - | b) | - | f) | - | b) | 1000000 | b) | - | d) | - | b) | -
[9 empty] | c) | - | c) | - | g) | - | c) | -
[9 empty] | d) | - | d) | -
|  |  |  | Completion of Multi-Purpose Hall, San Jose, Sto. Tomas |  |  |  | - | a) | 600000 | a) | - | e) | - | a) | 600000 | a) | - | c) | - | a) | - | For implementation
|  |  | 4.9 | [5 empty] | b) | - | b) | - | f) | - | b) | 600000 | b) | - | d) | - | b) | -
[9 empty] | c) | - | c) | - | g) | - | c) | -
[9 empty] | d) | - | d) | -
|  |  |  | Rehabilitation of Multi-Purpose Hall, Kasilak, Panabo City |  |  |  | - | a) | 650000 | a) | - | e) | - | a) | 650000 | a) | - | c) | - | a) | - | For implementation
|  |  | 5 | [5 empty] | b) | - | b) | - | f) | - | b) | 650000 | b) | - | d) | - | b) | -
[9 empty] | c) | - | c) | - | g) |  | c) | -
[9 empty] | d) | - | d) | -
|  |  |  | Rehabilitation of Brgy. Health Center, Dalisay, Panabo City |  |  |  | - | a) | 550000 | a) | - | e) | - | a) | 550000 | a) | - | c) | - | a) | - | For implementation
|  |  | 5.1 | [5 empty] | b) | - | b) | - | f) | - | b) | 550000 | b) | - | d) | - | b) | -
[9 empty] | c) | - | c) | - | g) | - | c) | -
[9 empty] | d) | - | d) | -
|  |  |  | Rehabilitation of Evacuation Center, Kiotoy, Panabo City |  |  |  | - | a) | 650000 | a) | - | e) | - | a) | 650000 | a) | - | c) | - | a) | - | For implementation
|  |  | 5.2 | [5 empty] | b) | - | b) | - | f) | - | b) | 650000 | b) | - | d) | - | b) | -
[9 empty] | c) | - | c) | - | g) | - | c) | -
[9 empty] | d) | - | d) | -
|  |  |  | Rehabilitation of Evacuation Center, Cagangohan, Panabo City |  |  |  | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Purchase Request # 19125279
|  |  | 5.3 | [5 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | -
[9 empty] | c) | - | c) | - | g) | - | c) | -
[9 empty] | d) | - | d) | -
|  |  |  | Rehabilitation of Multi-Purpose Bldg. (Brgy. Hall) Tagpopongan, IGACOS |  |  |  | - | a) | 174460.33 | a) | - | e) | - | a) | 174460.33 | a) | - | c) | - | a) | - | Procurement on process
|  |  | 5.4 | [5 empty] | b) | - | b) | - | f) | - | b) | 174460.33 | b) | - | d) | - | b) | -
[9 empty] | c) | - | c) | - | g) | - | c) | -
[9 empty] | d) | - | d) | -
|  | 5 | INFRASTRUCTURE DEVELOPMENT PROGRAM
|  | ■ |  | Construction of Multi-Purpose Building, Balagunan, Sto. Tomas |  | Bldg. | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For implementation
|  |  | 5.1 | [5 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | -
[9 empty] | c) | - | c) | - | g) | - | c) | -
[9 empty] | d) | - | d) | -
| N. | TRUST FUND 2019
1. CMGP 2019
|  | ■ |  | Road Upgrading of Sto Nino - Kabankalan - La Paz Provincial Road, Carmen |  |  |  | - | a) | 44461624.67 | a) | CY 2019 | e) | 60 | a) | 44561687 | a) | 65.35% | c) | 93.2% | a) | 30 | On-going
|  |  | 1.1 | [5 empty] | b) | Comidoy | b) | 2019-10-07 | f) | 96 | b) | 44561687 | b) | - | d) | 27.85% | b) | 650
[9 empty] | c) | GP & H CONST. | c) | 2020-05-15 | g) |  | c) | 6,684,253.05
[9 empty] | d) | 222 C.D | d) | 8/19/2020
|  | ■ |  | Road Upgrading of Jct Highway - Sto Nino - La Paz - San Vicenter Provincial Road, Carmen |  |  |  | - | a) | 80481331.34 | a) | CY 2019 | e) | - | a) | 80481331.34 | a) | 77.27% | c) | 78.31% | a) | 40 | On-going
|  |  | 1.2 | [5 empty] | b) | Fernandez | b) | 2019-10-07 | f) | - | b) | 80481331.34 | b) | - | d) | 1.04% | b) | 660
[9 empty] | c) | Tagum Builders | c) | 2020-06-22 | g) | - | c) | 45,481,609.97
[9 empty] | d) | 259 C.D | d) | 8/4/2020
| II. | PROJECTS UNDER THE CURRENT APPROPRIATION
| A. | GENERAL FUND CY 2020
INFRASTRUCTURE DEVELOPMENT PROGRAMS
| Road ID |  | 1. Maintenance Of Various Prov'l. Roads and Bridges 2 |  |  |  | 288.26 |  | a) | 11801752 | [12 empty] | See list of Provincial Roads
[9 empty] | b) | Matuguinas
| 11DAN | [7 empty] | c) | PEO
[9 empty] | d) | 261 days
|  |  | Cebulano - Mangalcal |  |  | Road Maintenance | 4.17 | MBA | a) | 134,672.70 | a) | 2020-01-02 | e) |  | a) | 134,672.70 | a) | 50% | c) | 51% | a) | 64 | On-going
| 073 | [7 empty] | b) | Gamad/Clar | b) | 2020-01-02 | f) |  | b) | 134,672.70 | b) |  | d) |  | b) | 1280
[9 empty] | c) | Admin | c) | 2020-12-31 | g) |  | c)
[9 empty] | d) | 1 year | d)
|  |  | Cebulano - Mangalcal |  |  | Road Maintenance | 4.17 | CBRMC | a) | 131,004.66 | a) |  | e) |  | a) | 131,004.66 | a) | 5% | c) | 5% | a) | 2 | Brgy. Mangalcal Women's Household - On going
| 073 | [7 empty] | b) | Maligro | b) | 5/15/2020 | f) |  | b) | 131,004.66 | b) |  | d) |  | b) | 2
[9 empty] | c) |  | c) | 11/15/2020 | g) |  | c)
[9 empty] | d) | 6 months | d)
|  |  | Tubod - basa - Mangalcal |  |  | Road Maintenance | 3.93 | MBA | a) | 143530.25 | a) | 2020-01-02 | e) | 27 | a) | 143530.25 | a) | 50% | c) | 52% | a) | 3 | On-going
| 074 | [7 empty] | b) | Gamad/Clar | b) | 2020-01-02 | f) |  | b) | 143530.25 | b) |  | d) |  | b) | 66
[9 empty] | c) | Admin | c) | 2020-12-31 | g) |  | c)
[9 empty] | d) | 1 year | d) |  | `
|  |  | Tubod - basa - Mangalcal |  |  | Road Maintenance | 3.93 | CBRMC | a) | 106,856.33 | a) |  | e) |  | a) | 106,856.33 | a) | 5% | c) | 5% | a) | 2 | On-going (Tubod Centro Lower Irrigator's Association)
| 074 | [7 empty] | b) | Maligro | b) | 5/25/2020 | f) |  | b) | 106,856.33 | b) |  | d) |  | b) | 2
[9 empty] | c) |  | c) | 11/25/2020 | g) |  | c)
[9 empty] | d) | 6 months | d)
|  |  | Upper Mangalcal - Lower Mangalcal |  |  | Road Maintenance | 2.43 | MBA | a) | 82,374.21 | a) | 2020-01-02 | e) | 27 | a) | 82,374.21 | a) | 50% | c) | 55% | a) | 3 | On-going
| 078 | [7 empty] | b) | Gamad/Clar | b) | 2020-01-02 | f) |  | b) | 82,374.21 | b) |  | d) |  | b) | 66
[9 empty] | c) | Admin | c) | 2020-12-31 | g) |  | c)
[9 empty] | d) | 1 year | d)
|  |  | Upper Mangalcal - Lower Mangalcal |  |  | Road Maintenance | 2.43 | CBRMC | a) | 72444.97 | a) |  | e) |  | a) | 72444.97 | a) | 5% | c) | 5% | a) | 2 | On-going (Brgy. Mangalcal Women's Homebased Association)
| 078 | [7 empty] | b) | Maligro | b) | 5/15/2020 | f) |  | b) | 72444.97 | b) |  | d) |  | b) | 2
[9 empty] | c) |  | c) | 11/15/2020 | g) |  | c)
[9 empty] | d) | 6 months | d)
|  |  | Cebulano - Loceta |  |  | Road Maintenance |  | MBA | a) | 72051.43 | a) | 2020-01-02 | e) | 27 | a) | 72051.43 | a) | 30% | c) | 54% | a) | 3 | On-going
| 079 | [7 empty] | b) | Gamad/Clar | b) | 2020-01-02 | f) |  | b) | 72051.43 | b) |  | d) |  | b) | 66
[9 empty] | c) | Admin | c) | 2020-12-31 | g) |  | c)
[9 empty] | d) | 1 year | d)
|  |  | Cebulano - Loceta |  |  | Road Maintenance |  | CBRMC | a) | 47089.26 | a) |  | e) |  | a) | 47089.26 | a) | 5% | c) | 5% | a) | 2 | On-going (Brgy. Mangalcal Women's Homebased Association)
| 079 | [7 empty] | b) | Maligro | b) | 5/15/2020 | f) |  | b) | 47089.26 | b) |  | d) |  | b) | 2
[9 empty] | c) |  | c) | 11/15/2020 | g) |  | c)
[9 empty] | d) | 6 months | d)
|  |  | Jct. Highway Carmen - Mangalcal - Tubod |  |  | Road Maintenance | 11.34 | MBA | a) | 462895.06 | a) | 2020-01-02 | e) | 27 | a) | 462895.06 | a) | 50% | c) | 50% | a) | 4 | On-going
| 082 | [7 empty] | b) | Gamad/Clar | b) | 2020-01-02 | f) |  | b) | 462895.06 | b) |  | d) |  | b) | 88
[9 empty] | c) | Admin | c) | 2020-12-31 | g) |  | c)
[9 empty] | d) | 1 year | d)
|  |  | Jct. Highway Carmen - Mangalcal - Tubod |  |  | Road Maintenance | 11.34 | CBRMC | a) | 259594.46 | a) |  | e) |  | a) | 259594.46 | a) |  | c) |  | a) |  | Bidded 3/12/2020 Documents on process
| 082 | [7 empty] | b) | Maligro | b) |  | f) |  | b) | 259594.46 | b) |  | d) |  | b)
[9 empty] | c) |  | c) |  | g) |  | c)
[9 empty] | d) | 6 months | d)
|  |  | Ising - Sadpodon - Taba - Dila -Dila |  |  | Road Maintenance | 5.68 | MBA | a) | 226651.27 | a) | 2020-01-02 | e) | 27 | a) | 226651.27 | a) | 50% | c) | 55% | a) | 3 | On-going
| 086 | [7 empty] | b) | Gamad/Clar | b) | 2020-01-02 | f) |  | b) | 226651.27 | b) |  | d) |  | b) | 66
[9 empty] | c) | Admin | c) | 2020-12-31 | g) |  | c)
[9 empty] | d) | 1 year | d)
|  |  | Ising - Sadpodon - Taba - Dila -Dila |  |  | Road Maintenance | 5.68 | CBRMC | a) | 135230.61 | a) |  | e) |  | a) | 135230.61 | a) |  | c) |  | a) |  | Bidded 3/12/2020 Documents on process
| 086 | [7 empty] | b) | Maligro | b) |  | f) |  | b) | 135230.61 | b) |  | d) |  | b)
[9 empty] | c) |  | c) |  | g) |  | c)
[9 empty] | d) | 6 months | d)
|  |  | Tuganay - taba |  |  | Road Maintenance | 4.27 | MBA | a) | 169418.15 | a) | 2020-01-02 | e) | 27 | a) | 169418.15 | a) | 50% | c) | 52% | a) | 3 | On-going
| 087 | [7 empty] | b) | Gamad/Clar | b) | 2020-01-02 | f) |  | b) | 169418.15 | b) |  | d) |  | b) | 66
[9 empty] | c) | Admin | c) | 2020-12-31 | g) |  | c)
[9 empty] | d) | 1 year | d)
|  |  | Tuganay - taba |  |  | Road Maintenance | 4.27 | CBRMC | a) | 102630.37 | a) |  | e) |  | a) | 102630.37 | a) |  | c) |  | a) |  | Bidded 3/12/2020 Documents on process
| 087 | [7 empty] | b) | Maligro | b) |  | f) |  | b) | 102630.37 | b) |  | d) |  | b)
[9 empty] | c) |  | c) |  | g) |  | c)
[9 empty] | d) | 6 months | d)
|  |  | Jct. Highway Tuganay - Taba |  |  | Road Maintenance | 4.4 | MBA | a) | 222375.04 | a) | 2020-01-02 | e) | 27 | a) | 222375.04 | a) | 50% | c) | 51% | a) | 3 | On-going
| 088 | [7 empty] | b) | Gamad/Clar | b) | 2020-01-02 | f) |  | b) | 222375.04 | b) |  | d) |  | b) | 66
[9 empty] | c) | Admin | c) | 2020-12-31 | g) |  | c)
[9 empty] | d) | 1 year | d)
|  |  | Jct. Highway Tuganay - Taba |  |  | Road Maintenance | 4.4 | CBRMC | a) | 57955.99 | a) |  | e) |  | a) | 57955.99 | a) | 5% | c) | 5% | a) | 2 | On-going (Ezra Christian Minsitry For Peace, Inc.)
| 088 | [7 empty] | b) | Maligro | b) | 5/13/2020 | f) |  | b) | 57955.99 | b) |  | d) |  | b) | 2
[9 empty] | c) |  | c) | 11/13/2020 | g) |  | c)
[9 empty] | d) | 6 months | d)
|  |  | Jct. Highway Ising - Magsaysay |  |  | Road Maintenance | 10.84 | MBA | a) | 478128.48 | a) | 2020-01-02 | e) | 27 | a) | 478128.48 | a) | 50% | c) | 50% | a) | 3 | On-going
| 089 | [7 empty] | b) | Gamad/Clar | b) | 2020-01-02 | f) |  | b) | 478128.48 | b) |  | d) |  | b) | 66
[9 empty] | c) | Admin | c) | 2020-12-31 | g) |  | c)
[9 empty] | d) |  | d)
|  |  | Jct. Highway Ising - Magsaysay |  |  | Road Maintenance | 10.84 | CBRMC | a) | 212505.24 | a) |  | e) |  | a) | 212505.24 | a) | 5% | c) | 5% | a) | 2 | On-going (School in the Air Integrated Farmer's Associiation)
| 089 | [7 empty] | b) | Maligro | b) | 5/14/2020 | f) |  | b) | 212505.24 | b) |  | d) |  | b) | 42
[9 empty] | c) |  | c) | 11/14/2020 | g) |  | c)
[9 empty] | d) | 6 months | d)
|  |  | Maligaya - New Camiling |  |  | Road Maintenance |  | MBA | a) | 51790.26 | a) | 2020-01-02 | e) | 27 | a) | 51790.26 | a) | 50% | c) | 51% | a) | 3 | On-going
| 090 | [7 empty] | b) | Gamad/Clar | b) | 2020-01-02 | f) |  | b) | 51790.26 | b) |  | d) |  | b) | 66
[9 empty] | c) | Admin | c) | 2020-12-31 | g) |  | c)
[9 empty] | d) | 1 year | d)
|  |  | Maligaya - New Camiling |  |  | Road Maintenance |  | CBRMC | a) | 83915.44 | a) |  | e) |  | a) | 83915.44 | a) | 5% | c) | 5% | a) | 2 | On-going (School in the Air Integrated Farmer's Associiation)
| 090 | [7 empty] | b) | Maligro | b) | 5/14/2020 | f) |  | b) | 83915.44 | b) |  | d) |  | b) | 2
[9 empty] | c) |  | c) | 11/14/2020 | g) |  | c)
[9 empty] | d) | 9 months | d)
|  |  | New Camiling - Alejal - Lower Magsaysay |  |  | Road Maintenance | 6.73 | MBA | a) | 277852.05 | a) | 2020-01-02 | e) | 27 | a) | 277852.05 | a) | 50% | c) | 50% | a) | 3 | On-going
| 091 | [7 empty] | b) | Gamad/Clar | b) | 2020-01-02 | f) |  | b) | 277852.05 | b) |  | d) |  | b) | 66
[9 empty] | c) | Admin | c) | 2020-12-31 | g) |  | c)
[9 empty] | d) | 1 year | d)
|  |  | New Camiling - Alejal - Lower Magsaysay |  |  | Road Maintenance | 6.73 | CBRMC | a) | 150927.01 | a) |  | e) |  | a) | 150927.01 | a) |  | c) |  | a) |  | On-going (School in the Air Integrated Farmer's Associiation)
| 091 | [7 empty] | b) | Maligro | b) | 5/14/2020 | f) |  | b) | 150927.01 | b) |  | d) |  | b)
[9 empty] | c) |  | c) | 11/14/2020 | g) |  | c)
[9 empty] | d) | 6 months | d)
|  |  | Jct. highway Tuganay - Anibongan |  |  | Road Maintenance | 3.66 | MBA | a) | 139609.7 | a) | 2020-01-02 | e) | 27 | a) | 139609.7 | a) | 50% | c) | 55% | a) | 4 | On-going
| 094 | [7 empty] | b) | Gamad/Clar | b) | 2020-01-02 | f) |  | b) | 139609.7 | b) |  | d) |  | b) | 88
[9 empty] | c) | Admin | c) | 2020-12-31 | g) |  | c)
[9 empty] | d) | 1 year | d)
|  |  | Jct. highway Tuganay - Anibongan |  |  | Road Maintenance | 3.66 | CBRMC | a) | 93574.75 | a) |  | e) |  | a) | 93574.75 | a) | 5% | c) | 5% | a) | 2 | On-going (Ezra Christian Minsitry For Peace, Inc.)
| 094 | [7 empty] | b) | Maligro | b) | 5/13/2020 | f) |  | b) | 93574.75 | b) |  | d) |  | b) | 2
[9 empty] | c) |  | c) | 11/13/2020 | g) |  | c)
[9 empty] | d) | 6 months | d)
|  |  | Anibongan - Guadalupe |  |  | Road Maintenance | 2.48 | MBA | a) | 85559.79 | a) | 2020-01-02 | e) | 27 | a) | 85559.79 | a) | 50% | c) | 55% | a) | 4 | On-going
| 095 | [7 empty] | b) | Gamad/Clar | b) | 2020-01-02 | f) |  | b) | 85559.79 | b) |  | d) |  | b) | 78
[9 empty] | c) | Admin | c) | 2020-12-31 | g) |  | c)
[9 empty] | d) | 1 year | d)
|  |  | Anibongan - Guadalupe |  |  | Road Maintenance | 2.48 | CBRMC | a) | 72444.97 | a) |  | e) |  | a) | 72444.97 | a) |  | c) |  | a) |  | Bidded 3/12/2020 Documents on process
| 095 | [7 empty] | b) | Maligro | b) |  | f) |  | b) | 72444.97 | b) |  | d) |  | b)
[9 empty] | c) |  | c) |  | g) |  | c)
[9 empty] | d) | 6 months | d)
|  |  | Tuganay - Anibongan - San Isidro |  |  | Road Maintenance | 7.22 | MBA | a) | 344085.79 | a) | 2020-01-02 | e) | 27 | a) | 344085.79 | a) | 50% | c) | 50% | a) | 3 | On-going
| 096 | [7 empty] | b) | Gamad/Clar | b) | 2020-01-02 | f) |  | b) | 344085.79 | b) |  | d) |  | b) | 66
[9 empty] | c) | Admin | c) | 2020-12-31 | g) |  | c)
[9 empty] | d) | 1 year | d)
|  |  | Tuganay - Anibongan - San Isidro |  |  | Road Maintenance | 7.22 | CBRMC | a) | 115911.95 | a) |  | e) |  | a) | 115911.95 | a) | 5% | c) | 5% | a) |  | On-going(Ezra Christian Minsitry For Peace, Inc.)
| 096 | [7 empty] | b) | Maligro | b) | 5/13/2020 | f) |  | b) | 115911.95 | b) |  | d) |  | b)
[9 empty] | c) |  | c) | 11/13/2020 | g) |  | c)
[9 empty] | d) | 6 months | d)
|  |  | Jct. Anibongan - Prk. 2, 7, 5, San Isidro |  |  | Road Maintenance | 3.14 | MBA | a) | 89575.84 | a) | 2020-01-02 | e) | 27 | a) | 89575.84 | a) | 50% | c) | 53% | a) | 4 | On-going
| 097 | [7 empty] | b) | Gamad/Clar | b) | 2020-01-02 | f) |  | b) | 89575.84 | b) |  | d) |  | b) | 88
[9 empty] | c) | Admin | c) | 2020-12-31 | g) |  | c)
[9 empty] | d) | 1 year | d)
|  |  | Jct. Anibongan - Prk. 2, 7, 5, San Isidro |  |  | Road Maintenance | 3.14 | CBRMC | a) | 110478.58 | a) |  | e) |  | a) | 110478.58 | a) |  | c) |  | a) |  | Bidded 3/12/2020 Documents on process
| 097 | [7 empty] | b) | Maligro | b) |  | f) |  | b) | 110478.58 | b) |  | d) |  | b)
[9 empty] | c) |  | c) |  | g) |  | c)
[9 empty] | d) | 6 months | d)
|  |  | Anibongan - Salvacion - Cabay-angan |  |  | Road Maintenance | 6.93 | MBA | a) | 279123.9 | a) | 2020-01-02 | e) | 27 | a) | 279123.9 | a) | 50% | c) | 51% | a) | 4 | On-going
| 098 | [7 empty] | b) | Gamad/Clar | b) | 2020-01-02 | f) |  | b) | 279123.9 | b) |  | d) |  | b) | 88
[9 empty] | c) | Admin | c) | 2020-12-31 | g) |  | c)
[9 empty] | d) |  | d)
|  |  | Anibongan - Salvacion - Cabay-angan |  |  | Road Maintenance | 6.93 | CBRMC | a) | 162397.48 | a) |  | e) |  | a) | 162397.48 | a) |  | c) |  | a) |  | Bidded 3/12/2020 Documents on process
| 098 | [7 empty] | b) | Maligro | b) |  | f) |  | b) | 162397.48 | b) |  | d) |  | b)
[9 empty] | c) |  | c) |  | g) |  | c)
[9 empty] | d) | 6 months | d)
|  |  | Mabaus - Cabay - angan |  |  | Road Maintenance |  | MBA | a) | 113320.9 | a) | 2020-01-02 | e) | 27 | a) | 113320.9 | a) | 50% | c) | 54% | a) | 3 | On-going
| 099 | [7 empty] | b) | Gamad/Clar | b) | 2020-01-02 | f) |  | b) | 113320.9 | b) |  | d) |  | b) | 66
[9 empty] | c) | Admin | c) | 2020-12-31 | g) |  | c)
[9 empty] | d) |  | d)
|  |  | Mabaus - Cabay - angan |  |  | Road Maintenance |  | CBRMC | a) | 90556.21 | a) |  | e) |  | a) | 90556.21 | a) |  | c) |  | a)
| 099 | [7 empty] | b) | Maligro | b) |  | f) |  | b) | 90556.21 | b) |  | d) |  | b) |  | Bidded 3/12/2020 Documents on process
[9 empty] | c) |  | c) |  | g) |  | c)
[9 empty] | d) | 6 months | d)
|  |  | Jct. Highway Guadalupe - Bdry. Tagum |  |  | Road Maintenance | 7.9 | MBA | a) | 517780.87 | a) | 2020-01-02 | e) | 27 | a) | 517780.87 | a) | 50% | c) | 55% | a) | 3 | On-going
| 101 | [7 empty] | b) | Gamad/Clar | b) | 2020-01-02 | f) |  | b) | 517780.87 | b) |  | d) |  | b) | 66
[9 empty] | c) | Admin | c) | 2020-12-31 | g) |  | c)
[9 empty] | d) | 9 months | d)
|  |  | Jct. Highway Guadalupe - Bdry. Tagum |  |  | Road Maintenance | 7.9 | CBRMC | a) | 231823.89 | a) |  | e) |  | a) | 231823.89 | a) |  | c) |  | a)
| 101 | [7 empty] | b) | Maligro | b) |  | f) |  | b) | 231823.89 | b) |  | d) |  | b) |  | Bidded 3/12/2020 Documents on process
[9 empty] | c) |  | c) |  | g) |  | c)
[9 empty] | d) | 6 months | d)
|  |  | Dujali - Tanglaw |  |  | Road Maintenance |  | MBA | a) | 135183.27 | a) | 2020-01-02 | e) | 27 | a) | 135183.27 | a) | 50% | c) | 52% | a) | 3 | On-going
| 104 | [7 empty] | b) | Gamad/Clar | b) | 2020-01-02 | f) |  | b) | 135183.27 | b) |  | d) |  | b) | 66
[9 empty] | c) | Admin | c) | 2020-12-31 | g) |  | c)
[9 empty] | d) |  | d)
|  |  | Dujali - Tanglaw |  |  | Road Maintenance |  | CBRMC | a) | 94178.48 | a) |  | e) | 94178.48 | a) |  | a) | 5% | c) | 5% | a) | 2 | On-going (Dujali Poblacion Farmer's Irrigator's Association, Inc.)
| 104 | [7 empty] | b) | Maligro | b) | 6/8/2020 | f) | 94178.48 | b) |  | b) |  | d) |  | b) | 2
[9 empty] | c) |  | c) | 12/8/2020 | g) |  | c)
[9 empty] | d) | 6 months | d)
|  |  | Poblacion Dujali - Prk. 8 Dujali |  |  | Road Maintenance | 8.2 | MBA | a) | 329064 | a) | 2020-01-02 | e) | 27 | a) | 329064 | a) | 50% | c) | 56% | a) | 3 | On-going
| 105 | [7 empty] | b) | Gamad/Clar | b) | 2020-01-02 | f) |  | b) | 329064 | b) |  | d) |  | b) | 66
[9 empty] | c) | Admin | c) | 2020-12-31 | g) |  | c)
[9 empty] | d) |  | d)
|  |  | Poblacion Dujali - Prk. 8 Dujali |  |  | Road Maintenance | 8.2 | CBRMC | a) | 193371.11 | a) |  | e) | 193371.11 | a) |  | a) | 5% | c) | 5% | a) | 2 | On-going (Dujali Poblacion Farmer's Irrigator's Association, Inc.)
| 105 | [7 empty] | b) | Maligro | b) | 6/8/2020 | f) | 193371.11 | b) |  | b) |  | d) |  | b) | 2
[9 empty] | c) |  | c) | 12/8/2020 | g) |  | c)
[9 empty] | d) | 6 months | d)
|  |  | Dujali - San Isidro |  |  | Road Maintenance | 3 | MBA | a) | 112652.73 | a) | 2020-01-02 | e) | 27 | a) | 112652.73 | a) | 50% | c) | 57% | a) | 3 | On-going
| 107 | [7 empty] | b) | Gamad/Clar | b) | 2020-01-02 | f) |  | b) | 112652.73 | b) |  | d) | 7% | b) | 66
[9 empty] | c) | Admin | c) | 2020-12-31 | g) |  | c)
[9 empty] | d) |  | d)
|  |  | Dujali - San Isidro |  |  | Road Maintenance | 3 | CBRMC | a) | 78482.06 | a) |  | e) | 78482.06 | a) |  | a) |  | c) |  | a) |  | Bidded 3/12/2020 Documents on process
| 107 | [7 empty] | b) | Maligro | b) |  | f) | 78482.06 | b) |  | b) |  | d) |  | b)
[9 empty] | c) |  | c) |  | g) |  | c)
[9 empty] | d) | 6 months | d)
|  |  | New Casay - Bugtong Talisay |  |  | Road Maintenance |  | MBA | a) | 74294.5 | a) | 2020-01-02 | e) | 27 | a) | 74294.5 | a) | 50% | c) | 50% | a) | 4 | On-going
| 108 | [7 empty] | b) | Gamad/Clar | b) | 2020-01-02 | f) |  | b) | 74294.5 | b) |  | d) | 0% | b) | 88
[9 empty] | c) | Admin | c) | 2020-12-31 | g) |  | c)
[9 empty] | d) | 1 year | d)
|  |  | New Casay - Bugtong Talisay |  |  | Road Maintenance |  | CBRMC | a) | 64596.78 | a) |  | e) |  | a) | 64596.78 | a) |  | c) |  | a)
| 108 | [7 empty] | b) | Maligro | b) |  | f) |  | b) | 64596.78 | b) |  | d) |  | b) |  | For Re-bid
[9 empty] | c) |  | c) |  | g) |  | c)
[9 empty] | d) | 6 months | d)
|  |  | Dujali - Balisong - Magupising |  |  | Road Maintenance | 5.52 | MBA | a) | 235776.07 | a) | 2020-01-02 | e) | 27 | a) | 235776.07 | a) | 50% | c) | 55% | a) | 3 | On-going
| 113 | [7 empty] | b) | Gamad/Clar | b) | 2020-01-02 | f) |  | b) | 235776.07 | b) |  | d) | 5% | b) | 22
[9 empty] | c) | Admin | c) | 2020-12-31 | g) |  | c)
[9 empty] | d) | 1 year | d)
|  |  | Dujali - Balisong - Magupising |  |  | Road Maintenance | 5.52 | CBRMC | a) | 115911.95 | a) |  | e) | 115911.95 | a) |  | a) | 5% | c) | 5% | a) |  | On-going (Dujali Poblacion Farmer's Irrigator's Association, Inc.)
| 113 | [7 empty] | b) | Maligro | b) | 6/8/2020 | f) | 115911.95 | b) |  | b) |  | d) |  | b)
[9 empty] | c) |  | c) | 12/8/2020 | g) |  | c)
[9 empty] | d) | 9 months | d)
|  |  | Dujali - Pawas - San Vicente |  |  | Road Maintenance | 4.42 | MBA | a) | 141544.99 | a) | 2020-01-02 | e) | 27 | a) | 141544.99 | a) | 50% | c) | 50% | a) | 3 | On-going
| 117 | [7 empty] | b) | Gamad/Clar | b) | 2020-01-02 | f) |  | b) | 141544.99 | b) |  | d) | 0% | b) | 22
[9 empty] | c) | Admin | c) | 2020-12-31 | g) |  | c)
[9 empty] | d) | 1 year | d)
|  |  | Dujali - Pawas - San Vicente |  |  | Road Maintenance | 4.42 | CBRMC | a) | 140060.27 | a) |  | e) | 140060.27 | a) |  | a) |  | c) |  | a) |  | Bidded 3/12/2020 Documents on process
| 117 | [7 empty] | b) | Maligro | b) |  | f) | 140060.27 | b) |  | b) |  | d) |  | b)
[9 empty] | c) |  | c) |  | g) |  | c)
[9 empty] | d) | 6 months | d)
|  |  | Jct. Salvacion - San Vicente - Cabay-angan |  |  | Road Maintenance | 3.45 | MBA | a) | 168583.81 | a) | 2020-01-02 | e) |  | a) | 168583.81 | a) | 50% | c) | 55% | a) | 3 | On-going
| 118 | [7 empty] | b) | Gamad/Clar | b) | 2020-01-02 | f) |  | b) | 168583.81 | b) |  | d) | 5% | b) | 60
[9 empty] | c) | Admin | c) | 2020-12-31 | g) |  | c)
[9 empty] | d) | 9 months | d)
|  |  | Jct. Salvacion - San Vicente - Cabay-angan |  |  | Road Maintenance | 3.45 | CBRMC | a) | 158775.23 | a) |  | e) |  | a) | 158775.23 | a) |  | c) |  | a) |  | Bidded 3/12/2020 Documents on process
| 118 | [7 empty] | b) | Maligro | b) |  | f) |  | b) | 158775.23 | b) |  | d) |  | b)
[9 empty] | c) |  | c) |  | g) |  | c)
[9 empty] | d) | 6 months | d)
|  |  | Bacali - Casig-ang - Libertad |  |  | Road Maintenance |  | MBA | a) | 167836.14 | a) | 2020-01-02 | e) | 27 | a) | 167836.14 | a) | 50% | c) | 58% | a) | 3 | On-going
| 123 | [7 empty] | b) | Gamad/Clar | b) | 2020-01-02 | f) |  | b) | 167836.14 | b) |  | d) | 8% | b) | 60
[9 empty] | c) | Admin | c) | 2020-12-31 | g) |  | c)
[9 empty] | d) | 1 year | d)
|  |  | Bacali - Casig-ang - Libertad |  |  | Road Maintenance |  | CBRMC | a) | 131608.37 | a) |  | e) |  | a) | 131608.37 | a) |  | c) |  | a) |  | Bidded 3/12/2020 Documents on process
| 123 | [7 empty] | b) | Maligro | b) |  | f) |  | b) | 131608.37 | b) |  | d) |  | b)
[9 empty] | c) |  | c) |  | g) |  | c)
[9 empty] | d) | 6 months | d)
|  |  | Kinamayan - Moslog - Mahayag |  |  | Road Maintenance |  | MBA | a) | 114628.54 | a) | 2020-01-02 | e) | 27 | a) | 114628.54 | a) | 50% | c) | 50% | a) | 3 | On-going
| 124 | [7 empty] | b) | Gamad/Clar | b) | 2020-01-02 | f) |  | b) | 114628.54 | b) |  | d) | 0% | b) | 66
[9 empty] | c) | Admin | c) | 2020-12-31 | g) |  | c)
[9 empty] | d) | 1 year | d)
|  |  | Kinamayan - Moslog - Mahayag |  |  | Road Maintenance |  | CBRMC | a) | 91159.92 | a) |  | e) |  | a) | 91159.92 | a) |  | c) |  | a)
| 124 | [7 empty] | b) | Maligro | b) |  | f) |  | b) | 91159.92 | b) |  | d) |  | b) |  | For re-bid
[9 empty] | c) |  | c) |  | g) |  | c)
[9 empty] | d) | 6 months | d)
|  |  | Kinamayan - Lunga-og |  |  | Road Maintenance |  | MBA | a) | 100416.26 | a) | 2020-01-02 | e) | 27 | a) | 100416.26 | a) | 50% | c) | 52% | a) | 3 | On-going
| 126 | [7 empty] | b) | Gamad/Clar | b) | 2020-01-02 | f) |  | b) | 0 | b) |  | d) | 2% | b) | 66
[9 empty] | c) | Admin | c) | 2020-12-31 | g) |  | c)
[9 empty] | d) | 1 year | d)
|  |  | Kinamayan - Lunga-og |  |  | Road Maintenance |  | CBRMC | a) | 64596.78 | a) |  | e) | 64596.78 | a) |  | a) | 5% | c) | 5% | a) | 1 | On-going (Lunga-og Tribal Association)
| 126 | [7 empty] | b) | Maligro | b) | 6/15/2020 | f) | 64596.78 | b) |  | b) |  | d) |  | b) | 2
[9 empty] | c) |  | c) | 12/15/2020 | g) |  | c)
[9 empty] | d) | 6 months | d)
|  |  | Prk. Apitong - Upper Balisong - Dalisay |  |  | Road Maintenance | 4.6 | MBA | a) | 150598.24 | a) | 2020-01-02 | e) | 27 | a) | 150598.24 | a) | 10% | c) | 9% | a) | 1 | On-going
| 128 | [7 empty] | b) | Gamad/Clar | b) | 2020-01-02 | f) |  | b) | 150598.24 | b) |  | d) | -1% | b) | 2
[9 empty] | c) | Admin | c) | 2020-12-31 | g) |  | c)
[9 empty] | d) | 1 year | d)
|  |  | Prk. Apitong - Upper Balisong - Dalisay |  |  | Road Maintenance | 4.6 | CBRMC | a) | 142475.11 | a) |  | e) |  | a) | 142475.11 | a) | 5% | c) | 5% | a) |  | On-going (Lunga-og Tribal Association)
| 128 | [7 empty] | b) | Maligro | b) | 6/15/2020 | f) |  | b) | 142475.11 | b) |  | d) |  | b)
[9 empty] | c) |  | c) | 12/15/2020 | g) |  | c)
[9 empty] | d) | 6 months | d)
|  |  | Los Amigos 1 - Esperanza - Los Amigos 2 |  |  | Road Maintenance | 3.59 | MBA | a) | 97116.27 | a) | 2020-01-02 | e) | 27 | a) | 97116.27 | a) | 50% | c) | 55% | a) | 4 | On-going
| 130 | [7 empty] | b) | Gamad/Clar | b) | 2020-01-02 | f) |  | b) | 97116.27 | b) |  | d) | 5% | b) | 88
[9 empty] | c) | Admin | c) | 2020-12-31 | g) |  | c)
[9 empty] | d) | 1 year | d)
|  |  | Los Amigos 1 - Esperanza - Los Amigos 2 |  |  | Road Maintenance | 3.59 | CBRMC | a) | 131608.37 | a) |  | e) | 131608.37 | a) |  | a) |  | c) |  | a) |  | Bidded 3/12/2020 Documents on process
| 130 | [7 empty] | b) | Maligro | b) |  | f) | 131608.37 | b) |  | b) |  | d) |  | b)
[9 empty] | c) |  | c) |  | g) |  | c)
[9 empty] | d) | 6 months | d)
|  |  | Mugas - Lanatad |  |  | Road Maintenance |  | MBA | a) | 65482.21 | a) | 2020-01-02 | e) | 27 | a) | 65482.21 | a) | 50% | c) | 50% | a) | 3 | On-going
| 131 | [7 empty] | b) | Gamad/Clar | b) | 2020-01-02 | f) |  | b) | 65482.21 | b) |  | d) | 0% | b) | 12
[9 empty] | c) | Admin | c) | 2020-12-31 | g) |  | c)
[9 empty] | d) |  | d)
|  |  | Mugas - Lanatad |  |  | Road Maintenance |  | CBRMC | a) | 31996.54 | a) |  | e) | 31996.54 | a) |  | a) |  | c) |  | a) |  | Purchase Order # 2020030961 (Katipunan Pantaron Irrigator's Association)
| 131 | [7 empty] | b) | Maligro | b) |  | f) | 31996.54 | b) |  | b) |  | d) |  | b)
[9 empty] | c) |  | c) |  | g) |  | c)
[9 empty] | d) | 6 months | d)
|  |  | Mugas - Lunga-og |  |  | Road Maintenance | 2.68 | MBA | a) | 96490.97 | a) | 2020-01-02 | e) | 27 | a) | 96490.97 | a) | 50% | c) | 50% | a) | 3 | On-going
| 132 | [7 empty] | b) | Gamad/Clar | b) | 2020-01-02 | f) |  | b) | 96490.97 | b) |  | d) | 0% | b) | 20
[9 empty] | c) | Admin | c) | 2020-12-31 | g) |  | c)
[9 empty] | d) |  | d)
|  |  | Mugas - Lunga-og |  |  | Road Maintenance | 2.68 | CBRMC | a) | 74256.11 | a) |  | e) | 74256.11 | a) |  | a) | 5% | c) | 5% | a) | 2 | On-going (Lunga-og Tribal Association)
| 132 | [7 empty] | b) | Maligro | b) | 6/15/2020 | f) | 74256.11 | b) |  | b) |  | d) |  | b) | 2
[9 empty] | c) |  | c) | 12/15/2020 | g) |  | c)
[9 empty] | d) | 6 months | d)
|  |  | New Katipunan - Pantaron |  |  | Road Maintenance |  | MBA | a) | 71748.41 | a) | 2020-01-02 | e) | 27 | a) | 71748.41 | a) | 50% | c) | 51% | a) | 2 | On-going
| 134 | [7 empty] | b) | Gamad/Clar | b) | 2020-01-02 | f) |  | b) | 71748.41 | b) |  | d) | 1% | b) | 20
[9 empty] | c) | Admin | c) | 2020-12-31 | g) |  | c)
[9 empty] | d) |  | d)
|  |  | New Katipunan - Pantaron |  |  | Road Maintenance |  | CBRMC | a) | 53126.32 | a) |  | e) |  | a) | 53126.32 | a) |  | c) |  | a) |  | Purchase Order # 2020030964 (Katipunan Pantaron Irrigator's Association)
| 134 | [7 empty] | b) | Maligro | b) |  | f) |  | b) | 53126.32 | b) |  | d) |  | b)
[9 empty] | c) |  | c) |  | g) |  | c)
[9 empty] | d) | 6 months | d)
|  |  | Sto. Tomas - Bdry. Mamacao |  |  | Road Maintenance | 4.9 | MBA | a) | 195671.17 | a) | 2020-01-02 | e) | 27 | a) | 43832 | a) | 50% | c) | 52% | a) | 3 | On-going
| 135 | [7 empty] | b) | Gamad/Clar | b) | 2020-01-02 | f) |  | b) | 43832 | b) |  | d) | 2% | b) | 33
[9 empty] | c) | Admin | c) | 2020-12-31 | g) |  | c)
[9 empty] | d) |  | d)
|  |  | Sto. Tomas - Bdry. Mamacao |  |  | Road Maintenance | 4.9 | CBRMC | a) | 116515.66 | a) |  | e) |  | a) | 0 | a) |  | c) |  | a) |  | Bidded 3/12/2020 Documents on process
| 135 | [7 empty] | b) | Maligro | b) |  | f) |  | b) | 0 | b) |  | d) |  | b)
[9 empty] | c) |  | c) |  | g) |  | c)
[9 empty] | d) | 6 months | d)
|  |  | Fd. Rd. 3 - San Jose |  |  | Road Maintenance | 4.55 | MBA | a) | 176994.35 | a) | 2020-01-02 | e) | 27 | a) | 43832 | a) | 50% | c) | 55% | a) | 2 | On-going
| 136 | [7 empty] | b) | Gamad/Clar | b) | 2020-01-02 | f) |  | b) | 43832 | b) |  | d) | 5% | b) | 10
[9 empty] | c) | Admin | c) | 2020-12-31 | g) |  | c)
[9 empty] | d) |  | d)
|  |  | Fd. Rd. 3 - San Jose |  |  | Road Maintenance | 4.55 | CBRMC | a) | 112893.42 | a) |  | e) |  | a) | 112893.42 | a) |  | c) |  | a) |  | On process (Brgy. San Jose Upland Farmer's Assocaition)
| 136 | [7 empty] | b) | Maligro | b) |  | f) |  | b) | 112893.42 | b) |  | d) |  | b)
[9 empty] | c) |  | c) |  | g) |  | c)
[9 empty] | d) | 6 months | d)
|  |  | Nafco - Bobongon |  |  | Road Maintenance |  | MBA | a) | 89179.68 | a) | 2020-01-02 | e) | 27 | a) | 43832 | a) | 50% | c) | 55% | a) | 3 | On-going
| 139 | [7 empty] | b) | Gamad/Clar | b) | 2020-01-02 | f) |  | b) | 43832 | b) |  | d) | 5% | b) | 56
[9 empty] | c) | Admin | c) | 2020-12-31 | g) |  | c)
[9 empty] | d) |  | d)
|  |  | Nafco - Bobongon |  |  | Road Maintenance |  | CBRMC | a) | 80293.17 | a) |  | e) |  | a) | 0 | a) | 5% | c) | 5% | a) |  | On-going (Bobongon Rural Waterworks & Sanitation Association, Inc.)
| 139 | [7 empty] | b) | Maligro | b) |  | f) |  | b) | 0 | b) |  | d) |  | b)
[9 empty] | c) |  | c) |  | g) |  | c)
[9 empty] | d) | 6 months | d)
|  |  | Bdry. Tagum - Crossing Kinamayan Sto. Tomas |  |  | Road Maintenance |  | MBA | a) | 790874.1 | a) | 2020-01-02 | e) | 27 | a) | 43832 | a) | 50% | c) | 50% | a) | 3 | On-going
| 146 | [7 empty] | b) | Gamad/Clar | b) | 2020-01-02 | f) |  | b) | 43832 | b) |  | d) | 0% | b) | 66
[9 empty] | c) | Admin | c) | 2020-12-31 | g) |  | c)
[9 empty] | d) |  | d)
|  |  | Bdry. Tagum - Crossing Kinamayan Sto. Tomas |  |  | Road Maintenance |  | CBRMC | a) | 429840.12 | a) |  | e) | 429840.12 | a) |  | a) |  | c) |  | a) |  | Bidded 3/12/2020 Documents on process
| 146 | [7 empty] | b) | Maligro | b) |  | f) | 429840.12 | b) |  | b) |  | d) |  | b)
[9 empty] | c) |  | c) |  | g) |  | c)
[9 empty] | d) | 9 months | d)
|  |  | San Jose - Sitio Mahayahay, Magwawa |  |  | Road Maintenance | 0.84 | MBA | a) | 22943.54 | a) | 2020-01-02 | e) | 27 | a) | 43832 | a) | 50% | c) | 50% | a) | 3 | On-going | 4/7/2020
| 151 | [7 empty] | b) | Gamad/Clar | b) | 2020-01-02 | f) |  | b) | 43832 | b) |  | d) |  | b) | 60 |  | 5/4/2020
[9 empty] | c) | Admin | c) | 2020-12-31 | g) |  | c) | [8 empty] | 27
[9 empty] | d) | - | d)
|  |  | San Jose - Sitio Mahayahay, Magwawa |  |  | Road Maintenance | 0.84 | CBRMC | a) | 30789.12 | a) |  | e) | 30789.12 | a) |  | a) |  | c) |  | a) |  | Purchase Order # 2020030972 (Brgy. San Jose Upland Farmer's Assocaition)
| 151 | [7 empty] | b) | Maligro | b) |  | f) | 30789.12 | b) |  | b) |  | d) |  | b) | 10
[9 empty] | c) |  | c) |  | g) |  | c)
[9 empty] | d) | 9 months | d)
|  | B. | 20% Development Fund CY 2020
PEACE AND ORDER PROGRAM
|  | 1. Rural Electrification Project |  |  |  | Rural Electrification to cater the needs of brgys. | - | Admin/Contract | a) | 5000000 | [12 empty] | See projects listed below
[9 empty] | b) | -
[9 empty] | c) | -
[9 empty] | d) | -
|  | ■ | Completion of Single Phase Line at Purok 6 and Purok 7, Brgy. Cogon, Babak Distirct, IGACOS |  |  | Rural Electrification to cater the needs of brgys. | - | - | a) | 1000000 | a) | - | e) | - | a) | 1000000 | a) | - | c) | - | a) | - | For preparation of POW and Plans
|  | 1.1 | [6 empty] | b) | - | b) | - | f) | - | b) | 1000000 | b) | - | d) | - | b) | -
[9 empty] | c) | - | c) | - | g) | - | c) | -
[9 empty] | d) | - | d) | -
|  | ■ | Completion of Single Phase Line at Purok Perlas, Brgy. Sta. Cruz, Talicud (Day Care Center), IGACOS |  |  | Rural Electrification to cater the needs of brgys. | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For preparation of POW and Plans
|  | 1.2 | [6 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | -
[9 empty] | c) | - | c) | - | g) | - | c) | -
[9 empty] | d) | - | d) | -
| Road ID | 2. Rehabilitation of Provincial Roads & Bridges |  |  |  | Road Maintenance | KM | MBA | a) | 47357000 | a) | 2020-01-02 | e) | - | a) | 47357000 | a) | - | c) | - | a) | 46 | See list of Provincial Roads
[7 empty] | 54 |  | b) | Matuguinas | b) | 2020-01-02 | f) | - | b) | 47357000 | b) | - | d) | - | b) | 920
| 11DAN | [7 empty] | c) | PEO | c) | 2020-12-31 | g) | - | c) | -
[11 empty] | d) | -
[9 empty] | d) | 261 days | d) | -
PEACE AND ORDER PROGRAM
|  |  | Fr. Rd. 3 - San Jose |  |  | Road Rehabilitaion | KM | Admin | a) | 8000000 | a) | - | e) | - | a) | 8000000 | a) | - | c) | - | a) | - | Plan On-going
| 008 | [7 empty] | b) |  | b) | - | f) | - | b) | 8000000 | b) | - | d) | - | b) | -
[9 empty] | c) | PEO | c) | - | g) | - | c) | -
[9 empty] | d) | - | d) | -
INFRASTRUCTURE DEVELOPMENT PROGRAMS
|  |  | Lower Asuncion - Upper Asuncion |  |  | Road Rehabilitaion | KM | Admin | a) | 1302000 | a) |  | e) | - | a) | 1302000 | a) | - | c) | - | a) | - | Plan On-going
| 007 | [7 empty] | b) |  | b) |  | f) | - | b) | 1302000 | b) | - | d) | - | b) | -
[9 empty] | c) | PEO | c) | - | g) | - | c) | -
[9 empty] | d) | - | d) | -
|  |  | Jct. Highway - Carmen - Mangalcal - Tubod |  |  | Road Rehabilitaion | KM | Admin | a) | 1323000 | a) | - | e) | - | a) | 1323000 | a) | - | c) | - | a) | - | Plan On-going
| 030 | [7 empty] | b) |  | b) | - | f) | - | b) | 1323000 | b) | - | d) | - | b) | -
[9 empty] | c) | PEO | c) | - | g) | - | c) | -
[9 empty] | d) | - | d) | -
|  |  | Tuganay - Taba |  |  | Road Rehabilitaion | KM | Admin | a) | 1431000 | a) |  | e) | - | a) | 1431000 | a) | - | c) | - | a) | - | Plan On-going
| 031 | [7 empty] | b) |  | b) |  | f) | - | b) | 1431000 | b) | - | d) | - | b) | -
[9 empty] | c) | PEO | c) | - | g) | - | c) | -
[9 empty] | d) | - | d) | -
|  |  | Jct. Highway - Ising - Magsaysay |  |  | Road Rehabilitaion | KM | Admin | a) | 6000000 | a) | - | e) | - | a) | 6000000 | a) | - | c) | - | a) | - | Plan On-going
| 069 | [7 empty] | b) |  | b) | - | f) | - | b) | 6000000 | b) | - | d) | - | b) | -
[9 empty] | c) | PEO | c) | - | g) | - | c) | -
[9 empty] | d) | - | d) | -
|  |  | Jct. Highway - Guadalupe - Bdry. Tagum |  |  | Road Rehabilitaion | KM | Admin | a) | 910000 | a) | - | e) | - | a) | 910000 | a) | - | c) | - | a) | -
| 069 | [7 empty] | b) |  | b) | - | f) | - | b) | 910000 | b) | - | d) | - | b) | -
[9 empty] | c) | PEO | c) | - | g) | - | c) | -
[9 empty] | d) | - | d) | -
|  |  | Sitio Malaga - Tibulao |  |  | Road Rehabilitaion | KM | Admin | a) | 350000 | a) | - | e) | - | a) | 350000 | a) | - | c) | - | a) | - | Plan On-going
| 069 | [7 empty] | b) |  | b) | - | f) | - | b) | 350000 | b) | - | d) | - | b) | -
[9 empty] | c) | PEO | c) | - | g) | - | c) | -
[9 empty] | d) | - | d) | -
|  |  | Prk. 5 RJS - Prk. 6 New Casay |  |  | Road Rehabilitaion | KM | Admin | a) | 350000 | a) | - | e) | - | a) | 350000 | a) | - | c) | - | a) | - | Plan On-going
| 069 | [7 empty] | b) |  | b) | - | f) | - | b) | 350000 | b) | - | d) | - | b) | -
[9 empty] | c) | PEO | c) | - | g) | - | c) | -
[9 empty] | d) | - | d) | -
|  |  | Dujali - Pawas - San Vicente |  |  | Road Rehabilitaion | KM | Admin | a) | 350000 | a) | - | e) | - | a) | 350000 | a) | - | c) | - | a) | - | Plan On-going
| 069 | [7 empty] | b) |  | b) | - | f) | - | b) | 350000 | b) | - | d) | - | b) | -
[9 empty] | c) | PEO | c) | - | g) | - | c) | -
[9 empty] | d) | - | d) | -
|  |  | Los Amigos 1 - Esperanza - Los Amigos 2 |  |  | Road Rehabilitaion | KM | Admin | a) | 350000 | a) | - | e) | - | a) | 350000 | a) | - | c) | - | a) | - | Plan On-going
| 069 | [7 empty] | b) |  | b) | - | f) | - | b) | 350000 | b) | - | d) | - | b) | -
[9 empty] | c) | PEO | c) | - | g) | - | c) | -
[9 empty] | d) | - | d) | -
|  |  | San Miguel - Crossing Kinamayan |  |  | Road Rehabilitaion | KM | Admin | a) | 19200000 | a) | - | e) | - | a) | 19200000 | a) | - | c) | - | a) | - | Plan On-going
| 069 | [7 empty] | b) |  | b) | - | f) | - | b) | 19200000 | b) | - | d) | - | b) | -
[9 empty] | c) | PEO | c) | - | g) | - | c) | -
[9 empty] | d) | - | d) | -
|  |  | Fd. Rd. 2 - Sto. Tomas - Magwawa |  |  | Road Rehabilitaion | KM | Admin | a) | 350000 | a) | - | e) | - | a) | 350000 | a) | - | c) | - | a) | - | Plan On-going
| 069 | [7 empty] | b) |  | b) | - | f) | - | b) | 350000 | b) | - | d) | - | b) | -
[9 empty] | c) | PEO | c) | - | g) | - | c) | -
[9 empty] | d) | - | d) | -
|  |  | Menzi - Balagunan - Tulalian |  |  | Road Rehabilitaion | KM | Admin | a) | 3720500 | a) | - | e) | - | a) | 3720500 | a) | - | c) | - | a) | - | Plan On-going
| 069 | [7 empty] | b) |  | b) | - | f) | - | b) | 3720500 | b) | - | d) | - | b) | -
[9 empty] | c) | PEO | c) | - | g) | - | c) | -
[9 empty] | d) | - | d) | -
|  |  | Jct,. Bdry. Tagum- Talomo |  |  | Road Rehabilitaion | KM | Admin | a) | 3720500 | a) | - | e) | - | a) | 3720500 | a) | - | c) | - | a) | - | Plan On-going
| 069 | [7 empty] | b) |  | b) | - | f) | - | b) | 3720500 | b) | - | d) | - | b) | -
[9 empty] | c) | PEO | c) | - | g) | - | c) | -
[9 empty] | d) | - | d) | -
|  | 3. Various Local Roads & Drainage Dev't. Project |  |  |  | Rehabilitaion |  | - | a) | 12590910 | a) | [11 empty] | See projects listed below
[9 empty] | b) |  | b)
[9 empty] | c) | PEO | c) | -
[9 empty] | d) | - | d)
|  | ■ | Rehab. Of Various Local Roads @ Island Garden City of Samal |  |  | Rehabilitaion |  | - | a) | 2518182 | a) | - | e) | - | a) | 2518182 | a) | - | c) | - | a) | - | Plan On-going
|  | 3.1 | [6 empty] | b) | - | b) | - | f) | - | b) | 2518182 | b) | - | d) | - | b) | -
[9 empty] | c) | - | c) | - | g) | - | c) | -
[9 empty] | d) | - | d) | -
|  | ■ | Rehab. Of Various Local Roads @ Panabo City |  |  | Rehabilitaion |  | - | a) | 2518182 | a) | - | e) | - | a) | 2518182 | a) | - | c) | - | a) | - | Abstract # 0420201633 - Billboard; Abstract 0520201661 - hardware
|  | 3.2 | [6 empty] | b) | - | b) | - | f) | - | b) | 2518182 | b) | - | d) | - | b) | -
[9 empty] | c) | - | c) | - | g) | - | c) | -
[9 empty] | d) | - | d) | -
|  | ■ | Rehab. Of Various Local Roads @ B.E Dujali |  |  | Rehabilitaion |  | - | a) | 2518182 | a) | - | e) | - | a) | 2518182 | a) | - | c) | - | a) | - | Purchase Request # 20053256 - Hardware; PR # 20053255 - Billboard
|  | 3.3 | [6 empty] | b) | - | b) | - | f) | - | b) | 2518182 | b) | - | d) | - | b) | -
[9 empty] | c) | - | c) | - | g) | - | c) | -
[9 empty] | d) | - | d) | -
|  | ■ | Rehab. Of Various Local Roads @ Carmen |  |  | Rehabilitaion |  | - | a) | 2518182 | a) | - | e) | - | a) | 2518182 | a) | - | c) | - | a) | - | Abstract # 0420201633 - Billboard; Abstract 0520201661 - hardware
|  | 3.4 | [6 empty] | b) | - | b) | - | f) | - | b) | 2518182 | b) | - | d) | - | b) | -
[9 empty] | c) | - | c) | - | g) | - | c) | -
[9 empty] | d) | - | d) | -
|  | ■ | Rehab. Of Various Local Roads @ Sto. Tomas |  |  | Rehabilitaion |  | - | a) | 2518182 | a) | - | e) | - | a) | 2518182 | a) | - | c) | - | a) | - | Plan On-going
|  | 3.5 | [6 empty] | b) | - | b) | - | f) | - | b) | 2518182 | b) | - | d) | - | b) | -
[9 empty] | c) | - | c) | - | g) | - | c) | -
[9 empty] | d) | - | d) | -
|  | 4. Various Government Buildings and Facilities Development Project |  |  |  | Various Bldgs./Facilities | km. | - | a) | 9790000 | a) | [11 empty] | See projects listed below
[9 empty] | b) |  | b)
[9 empty] | c) | PEO | c) | -
[9 empty] | d) | - | d)
|  | ■ | Construction of Commercial Building at Kinawitnon, IGACOS, Babak |  |  | Various Bldgs./Facilities |  | - | a) | 2000000 | a) | - | e) | - | a) | 2000000 | a) | - | c) | - | a) | - | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
|  | 5.2 | [6 empty] | b) | - | b) | - | f) | - | b) | 2000000 | b) | - | d) | - | b) | -
[9 empty] | c) | - | c) | - | g) | - | c) | -
[9 empty] | d) | - | d) | -
|  | ■ | Improvement of Provincial Engineer's Office 2nd District Office Phase 2, Carmen |  |  | Various Bldgs./Facilities |  | - | a) | 1590000 | a) | - | e) | - | a) | 1590000 | a) | - | c) | - | a) | - | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
|  | 5.3 | [6 empty] | b) | - | b) | - | f) | - | b) | 1590000 | b) | - | d) | - | b) | -
[9 empty] | c) | - | c) | - | g) | - | c) | -
[9 empty] | d) | - | d) | -
|  | ■ | Construction of DDN hospital Carmen Zone Annex Building Phase 3, Carmen |  |  | Various Bldgs./Facilities |  | - | a) | 800000 | a) | - | e) | - | a) | 800000 | a) | - | c) | - | a) | - | Purchase Request # 20021473
|  | 5.4 | [6 empty] | b) | - | b) | - | f) | - | b) | 800000 | b) | - | d) | - | b) | -
[9 empty] | c) | - | c) | - | g) | - | c) | -
[9 empty] | d) | - | d) | -
|  | ■ | Construction of Municipal Triball Hall, B.E. Dujali |  |  | Various Bldgs./Facilities |  | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
|  | 5.6 | [6 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | -
[9 empty] | c) | - | c) | - | g) | - | c) | -
[9 empty] | d) | - | d) | -
|  | ■ | Construction of Municipal Triball Hall, Sto. Tomas |  |  | Various Bldgs./Facilities |  | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
|  | 5.7 | [6 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | -
[9 empty] | c) | - | c) | - | g) | - | c) | -
[9 empty] | d) | - | d) | -
|  | ■ | Construction of Fence at Tulalian National High School, Tulalian, Sto. Tomas |  |  | Various Bldgs./Facilities |  | - | a) | 1500000 | a) | - | e) | - | a) | 1500000 | a) | - | c) | - | a) | - | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
|  | 5.8 | [6 empty] | b) | - | b) | - | f) | - | b) | 1500000 | b) | - | d) | - | b) | -
|  | . | [6 empty] | c) | - | c) | - | g) | - | c) | -
[9 empty] | d) | - | d) | -
|  | ■ | Construction of Two(2) Classroom at Tibulao Elem. School, Tibulao, Carmen |  |  | Various Bldgs./Facilities |  | - | a) | 2900000 | a) | - | e) | - | a) | 2900000 | a) | - | c) | - | a) | - | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
|  | 5.9 | [6 empty] | b) | - | b) | - | f) | - | b) | 2900000 | b) | - | d) | - | b) | -
[9 empty] | c) | - | c) | - | g) | - | c) | -
[9 empty] | d) | - | d) | -
| C. | 5% CALAMITY FUND CY 2020
DISASTER PREVENTION AND MITIGATION PROGRAM
I. FLOOD CONTROL AND SLOPE PROTECTION PROJECT
|  | Desiltation/Excavation of Rivers & Creeks |  |  |  | Desiltation/Excavation |  | - | a) | 6630206 | [12 empty] | See projects listed below
| 1 | [7 empty] | b) | Matuguinas
[9 empty] | c) | PEO
[9 empty] | d) | -
|  |  | Improvement and Desiltation of Camoning Creek |  |  | Desiltation/Excavation |  | - | a) | 2500000 | a) | - | e) | - | a) | 2500000 | a) | - | c) | - | a) | - | Waiting for approved P.O of equipment rental
|  | 1.1 | [6 empty] | b) | - | b) | - | f) | - | b) | 2500000 | b) | - | d) | - | b) | -
[9 empty] | c) | PEO | c) | - | g) | - | c) | -
[9 empty] | d) | - | d) | -
|  |  | Improvement and Desiltation of Ising Creek |  |  | Desiltation/Excavation |  | - | a) | 2000000 | a) | 3/10/2020 | e) | - | a) | 2000000 | a) | - | c) | - | a) | - | Waiting for approved P.O of equipment rental
|  | 1.2 | [6 empty] | b) | - | b) | - | f) | - | b) | 2000000 | b) | - | d) | - | b) | -
[9 empty] | c) | PEO | c) | - | g) | - | c) | -
[9 empty] | d) | 94 | d) | -
|  |  | Desiltation of Buhang Creek, Anibongan, Carmen |  |  | Desiltation/Excavation |  | - | a) | 2130206 | a) | - | e) | - | a) | 2130206 | a) | - | c) | - | a) | - | Abstract # 0520201657; 0420201626
|  | 1.3 | [6 empty] | b) | - | b) | - | f) | - | b) | 2130206 | b) | - | d) | - | b) | -
[9 empty] | c) | - | c) | - | g) | - | c) | -
[9 empty] | d) | - | d) | -
| 2 | Revetment of Dike and Slope Protection
|  |  | Rehab./Impv't. of Sto. Niño-Daligdigon-Paiton |  |  | Rehab./Impv't. | km. | - | a) | 1000000 | a) |  | e) | - | a) | 1000000 | a) | - | c) | - | a) | - | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
|  | 2.1 | [6 empty] | b) |  | b) |  | f) | - | b) | 1000000 | b) | - | d) | - | b) | -
[9 empty] | c) | PEO | c) | - | g) | - | c) | -
[9 empty] | d) | - | d) | -
|  |  | Rehab./Impv't. of San Miguel - Moslog - Kinamayan, Sto. Tomas |  |  | Rehab./Impv't. |  | - | a) | 1000000 | a) | - | e) | - | a) | 1000000 | a) | - | c) | - | a) | - | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
|  | 2.2 | [6 empty] | b) | - | b) | - | f) | - | b) | 1000000 | b) | - | d) | - | b) | -
[9 empty] | c) | PEO | c) | - | g) | - | c) | -
[9 empty] | d) | - | d) | -
|  | Improvement of Roads, Drainage and Canal |  |  |  | Rehab./Impv't. |  | - | a) | 1000000 | [12 empty] | See projects listed below
| 3 | [7 empty] | b) | Matuguinas
[9 empty] | c) | PEO
[9 empty] | d) | -
|  |  | Improvement of Mangalcal to Diamond Creek Farm to Market Road Opening |  |  | Rehab./Impv't. |  | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
|  | 3.1 | [6 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | -
[9 empty] | c) | - | c) | - | g) | - | c) | -
[9 empty] | d) | - | d) | -
|  |  | Improvement of Mabaus - Salvacion Provincial Road Continuing Road Opening |  |  | Rehab./Impv't. |  | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For Implementation
|  | 3.2 | [6 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | -
[9 empty] | c) | - | c) | - | g) | - | c) | -
[9 empty] | d) | - | d) | -
| 4 | Improvement of Bridges and Cross Drainage
|  |  | Single Barrel Box Culvert at Mangalcal-Diamond Creek, Brgy. Mangalcal, Carmen |  |  | Rehab./Impv't. |  | - | a) | 2000000 | a) | - | e) | - | a) | 2000000 | a) | - | c) | - | a) | - | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
|  | 4.1 | [6 empty] | b) | - | b) | - | f) | - | b) | 2000000 | b) | - | d) | - | b) | -
[9 empty] | c) | - | c) | - | g) | - | c) | -
[9 empty] | d) | - | d) | -
| D. | SPECIAL EDUCATION FUND - ANNUAL BUDGET CY 2020
|  | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. | [20 empty] | See projects listed below
| 1 |  |  |  |  | Const./Impv't./Compl. |  | - | a) | 500000
[9 empty] | b) | -
[9 empty] | c) | -
[9 empty] | d) | -
|  |  | Const. of 1 Classroom @ Mangga ES, Magwawa, Sto. Tomas |  |  | Bldg. | sq.m | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Procurement on process
|  | 1.7 | [6 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | -
[9 empty] | c) | - | c) | - | g) | - | c) | -
[9 empty] | d) | - | d) | -
| E. | SOCIAL WELFARE AND DEVELOPMENT
|  | 1. CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) |  |  |  | Bldg. | sq.m | Admin/Contract | a) | 6000000 | [12 empty] | See list of projects
[9 empty] | b) | -
[9 empty] | c) | -
[9 empty] | d) | -
|  |  | Const. of Day Care Center, JP Laurel, Panabo City |  |  | Bldg. | sq.m | - | a) | 1000000 | a) | - | e) | - | a) | 1000000 | a) | - | c) | - | a) | - | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
|  | 2.2 | [6 empty] | b) | - | b) | - | f) | - | b) | 1000000 | b) | - | d) | - | b) | -
[9 empty] | c) | - | c) | - | g) | - | c) | -
[9 empty] | d) | - | d) | -
|  |  | Const. of Day Care Center, Dujali, B.E. Dujali |  |  | Bldg. | sq.m | - | a) | 1000000 | a) | - | e) | - | a) | 1000000 | a) | - | c) | - | a) | - | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
|  | 2.3 | [6 empty] | b) | - | b) | - | f) | - | b) | 1000000 | b) | - | d) | - | b) | -
[9 empty] | c) | - | c) | - | g) | - | c) | -
[9 empty] | d) | - | d) | -
|  |  | Const. of Day Care Center, Tibal-og, Sto Tomas |  |  | Bldg. | sq.m | - | a) | 1000000 | a) | - | e) | - | a) | 1000000 | a) | - | c) | - | a) | - | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
|  | 2.4 | [6 empty] | b) | - | b) | - | f) | - | b) | 1000000 | b) | - | d) | - | b) | -
[9 empty] | c) | - | c) | - | g) | - | c) | -
[9 empty] | d) | - | d) | -
|  |  | Compl./Rep. Day Care Center, Cabay-angan, B.E. Dujali |  |  | Bldg. | sq.m | - | a) | 300000 | a) | - | e) | - | a) | 300000 | a) | - | c) | - | a) | - | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
|  | 2.5 | [6 empty] | b) | - | b) | - | f) | - | b) | 300000 | b) | - | d) | - | b) | -
[9 empty] | c) | - | c) | - | g) | - | c) | -
[9 empty] | d) | - | d) | -
|  |  | Compl./Rep. Day Care Center, Tanglaw, B.E. Dujali |  |  | Bldg. | sq.m | - | a) | 300000 | a) | - | e) | - | a) | 300000 | a) | - | c) | - | a) | - | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
|  | 2.6 | [6 empty] | b) | - | b) | - | f) | - | b) | 300000 | b) | - | d) | - | b) | -
[9 empty] | c) | - | c) | - | g) | - | c) | -
[9 empty] | d) | - | d) | -
|  |  | Compl./Rep. Day Care Center, Salvacion, Carmen |  |  | Bldg. | sq.m | - | a) | 300000 | a) | - | e) | - | a) | 300000 | a) | - | c) | - | a) | - | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
|  | 2.7 | [6 empty] | b) | - | b) | - | f) | - | b) | 300000 | b) | - | d) | - | b) | -
[9 empty] | c) | - | c) | - | g) | - | c) | -
[9 empty] | d) | - | d) | -
|  |  | Compl./Rep. Day Care Center, San Agustin, IGCS |  |  | Bldg. | sq.m | - | a) | 300000 | a) | - | e) | - | a) | 300000 | a) | - | c) | - | a) | - | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
|  | 2.8 | [6 empty] | b) | - | b) | - | f) | - | b) | 300000 | b) | - | d) | - | b) | -
[9 empty] | c) | - | c) | - | g) | - | c) | -
[9 empty] | d) | - | d) | -
|  |  | Compl./Rep. Day Care Center, Toril, IGCS |  |  | Bldg. | sq.m | - | a) | 300000 | a) | - | e) | - | a) | 300000 | a) | - | c) | - | a) | - | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
|  | 2.9 | [6 empty] | b) | - | b) | - | f) | - | b) | 300000 | b) | - | d) | - | b) | -
[9 empty] | c) | - | c) | - | g) | - | c) | -
[9 empty] | d) | - | d) | -
|  |  | Compl./Rep. Day Care Center, Tibal-og, Sto. Tomas |  |  | Bldg. | sq.m | - | a) | 600000 | a) | - | e) | - | a) | 600000 | a) | - | c) | - | a) | - | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
|  | 3 | [6 empty] | b) | - | b) | - | f) | - | b) | 600000 | b) | - | d) | - | b) | -
[9 empty] | c) | - | c) | - | g) | - | c) | -
[9 empty] | d) | - | d) | -
|  |  | Compl./Rep. Day Care Center, Talomo, Sto. Tomas |  |  | Bldg. | sq.m | - | a) | 300000 | a) | - | e) | - | a) | 300000 | a) | - | c) | - | a) | - | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
|  | 3.1 | [6 empty] | b) | - | b) | - | f) | - | b) | 300000 | b) | - | d) | - | b) | -
[9 empty] | c) | - | c) | - | g) | - | c) | -
[9 empty] | d) | - | d) | -
|  |  | Compl./Rep. Day Care Center, Kinamayan, Sto. Tomas |  |  | Bldg. | sq.m | - | a) | 300000 | a) | - | e) | - | a) | 300000 | a) | - | c) | - | a) | -
|  | 3.2 | [6 empty] | b) | - | b) | - | f) | - | b) | 300000 | b) | - | d) | - | b) | -
[9 empty] | c) | - | c) | - | g) | - | c) | -
[9 empty] | d) | - | d) | -
|  |  | Compl./Rep. Day Care Center, La Libertad, Sto. Tomas |  |  | Bldg. | sq.m | - | a) | 300000 | a) | - | e) | - | a) | 300000 | a) | - | c) | - | a) | -
|  | 3.3 | [6 empty] | b) | - | b) | - | f) | - | b) | 300000 | b) | - | d) | - | b) | -
[9 empty] | c) | - | c) | - | g) | - | c) | -
[9 empty] | d) | - | d) | -
|  |  | Impv't of Hospital Facilities (Isolation/ICU Room) Carmen District Hospital |  |  | Bldg. |  |  | a) | 3000000 | a) | - | e) | - | a) | 3000000 | a) | 30.21% | c) | 22.72% | a) | 8 | On-going
[9 empty] | b) | Estorco | b) | 5/11/2020 | f) | - | b) | 3000000 | b) | - | d) | -7.49% | b) | 240
[9 empty] | c) | Admin | c) | 2020-08-09 | g) | - | c) | -
[9 empty] | d) | 90 | d) | -
|  |  | Impv't of Hospital Facilities (Isolation/ICU Room) Samal District Hospital |  |  | Bldg. |  |  | a) | 1000000 | a) |  | e) | - | a) | 1000000 | a) | 30.12% | c) | 50.17% | a) | 6 | On-going
[9 empty] | b) | Porras/Obar | b) | 5/11/2020 | f) | - | b) | 1000000 | b) | - | d) | 20.05% | b) | 60
[9 empty] | c) | Admin | c) | 8/9/2020 | g) | - | c) | -
[9 empty] | d) | 90 | d) | -
|  |  | Rehab of DavNor Pharmacy into Isolation Room Phase I |  |  | Bldg. |  |  | a) | 1480000 | a) | - | e) | - | a) | 1480000 | a) | 63.38% | c) | 88.68% | a) | 10 | On-going
[9 empty] | b) | Andoy | b) | 4/28/2020 | f) | - | b) | 1480000 | b) | - | d) | 25.3% | b) | 260
[9 empty] | c) | Admin | c) | 2020-07-20 | g) | - | c) | 1137930.67
[9 empty] | d) | 83 | d) | -
|  |  | Rehab of DavNor Pharmacy into Isolation Room Phase II |  |  | Bldg. |  |  | a) | 1000000 | a) | - | e) | - | a) | 1000000 | a) | 36.42% | c) | 32.01% | a) | 6 | On-going
[9 empty] | b) | Andoy | b) | 5/11/2020 | f) | - | b) | 1000000 | b) | - | d) | -4.41% | b) | 132
[9 empty] | c) | Admin | c) | 2020-07-24 | g) | - | c) | 664107.16
[9 empty] | d) | 74 | d) | -
[5 empty] | GF- GENERAL FUND | [11 empty] | TF - TRUST FUND (NATIONAL FUNDED PROJECT)
[5 empty] | 20% DF - 20% DEV'T. FUND | [11 empty] | a) SLRF - Special Local Road Fund
[5 empty] | 5% CF - 5% CALAMITY FUND | [11 empty] | b) KALSADA - Konkreto at Ayos na Lansangan Tungo sa Pangkalahatang Kaunlaran
[5 empty] | CO - CAPITAL OUTLAY | [11 empty] | c) PRDP - Philippine Rural Development Projects
[5 empty] | CONG. FUND - CONGRESSIONAL FUND | [11 empty] | d) SELAP - Support to Emergency and Livelihood Assistance Project
[5 empty] | SEF - SPECIAL EDUCATIONAL UFND | [11 empty] | e) PAMANA - Payapa at Masaganang Pamayanan
f) CBRMC - Community Based Road Maintenance Contracting
g) MBC - Maintenance by Contract
h) PCF-Performance Challenge Fund-DILG
i) FMRDP - Farm to Market Road
j.) CMGP - Conditional Grant to Provinces
k.) OPAPP - Office of the President Adviser on the Peace Process
l.) LGSF-AM - Local Government Support Fund Assistance to Municipalities
|  |  | Prepared by: |  |  |  | Checked | [5 empty] | Noted | [6 empty] | Recommending Approval
|  |  | RETCHIE A. DE LOS REYES |  |  |  | ELISA A. BARCENA | [5 empty] | JIVELLYN B. CO | [6 empty] | GLENN A. OLANDRIA
|  |  | Engineer II |  |  |  | Engineer IV- Engineering Dist 1, Area Engineer | [5 empty] | Asst. PG-Department Head | [6 empty] | Provincial Engineer
Formulas:
Date A lot. Rel. = +[Date A lot. Rel., row above]+200
Date A lot. Rel. = +[Date A lot. Rel., row above]+[Admin, row below]

## South (hidden)
PROVINCE OF DAVAO DEL NORTE
ACCOMPLISHMENT REPORT
FOR THE MONTH OF MAY 2020
SECTOR: ECONOMIC (INFRASTRUCTURE DEV'T. PROGRAM)
OFFICE/AGENCY: PROVINCIAL ENGINEER'S OFFICE
AREA: AREA: 2ND ENGINEERING DISTRICT - COMPLETED AND ON-GOING PROJECTS
| Name of Project |  |  |  |  | Source of Fund | Type | Physical | Mode | PROJECT DATA | [5 empty] | Financial (000) |  | Physical Accomplishment |  |  |  | Employment |  | REMARKS
[7 empty] | of | Target | of | a) Project Cost |  | a) | Date A lot. Rel. | e) | # of days suspended | a) Program |  | a) Planned |  | c) Actual |  | Generated
[7 empty] | Project | (Descrip | Impl. | b) Project Engineer |  | b) | Date Started | f) | # of days extended | b) Allotment |  | b) Revised |  | d) Slippage |  | a) # of Persons | # of Persons
[7 empty] | (Location) | tion) |  | c) Implementor |  | c) | Target Compl. Date | g) | Date completed | c) Disbursement | [5 empty] | b) | Man-days
[10 empty] | d) Duration |  | d) | Revised Compl. Date
| I. |  | I. | PROJECTS UNDER THE CONTINUING APPROPRIATION | [20 empty] | AC |  | 893809.45
COMPLETED
|  |  |  | Road Rehabilitation of Provincial Roads | [20 empty] | 1
|  |  | 1 | Rehab.of Dujali - Balisong - Magupising Provincial Road |  |  | Road Rehabilitation | 19.16 | MBA | a) | 1280000 | a) |  | e) | - | a) | 1280000 | a) | 100% | c) | 96.23% | a) | 12 | Completed 529/2020 | 1
|  |  | 1 | [6 empty] | b) | Mellomida | b) | 2019-12-02 | f) | - | b) | 1280000 | b) | 100% | d) | -3.77% | b) | 900 |  | 1
[10 empty] | c) | Admin | c) | 2019-01-15 | g) | 5/29/2020 | c) | 14331.6 | [7 empty] | 1
[10 empty] | d) | 45 CD | d) | 5/31/2020 | [11 empty] | 1
ON-GOING
|  |  | 1 | Proposed Davao del Norte Tourism Billboard, Brgy. Lasang, Panabo City |  | SB # 1 CY 2015 | Billboard |  | Admin | a) | 756,400.00 | a) | 05/06/15 | e) | - | a) | 756,400.00 | a) | 11.78% | c) | 11.78% | a) | - | delay due to change location & design code. For AIP amendment from Panabo City to Gov't Center, Mankilam | FS
|  |  | 2 | [6 empty] | b) | Porras | b) | 03/30/15 | f) | - | b) | 756,400.00 | b) | - | d) | - | b) | - |  | FS
[10 empty] | c) | PEO | c) | 05/10/15 | g) | - | c) | 332,087.30 | [7 empty] | 1
[10 empty] | d) | - | d) | - | [11 empty] | 1
|  |  |  | Rehab. of Esperanza-Pob. Sto. Tomas, FMR, DDN |  | PRDP CY 2014 | Road | 12.77399 km | Contract. | a) | 117,410,426.30 | a) | CY 2014 | e) | - | a) | 117,410,426.30 | a) | 100% | c) | 87.82% | a) | 20 | On-going (Waiting for approve Variation order for billing) | AC
|  |  | 1.1 | [6 empty] | b) | Palero | b) | 2017-03-22 | f) | 252 | b) | 117,410,426.30 | b) | 95.53% | d) | -7.705% | b) | 600 |  | AC
[10 empty] | c) | Alzam | c) | 2019-07-22 | g) | - | c) | [8 empty] | AC
[10 empty] | d) | 853 CD | d) | 7/31/2020 | [11 empty] | 1
|  |  |  | Improvement of Sto. Tomas Production Center with Common Facility, Sto. Tomas |  | PRDP CY 2016 | Bldg. | 1901 sq.m | Contract. | a) | 9825000 | a) | CY 2014 | f) | - | b) |  | a) |  | c) |  | a) |  | Suspended due to land unsettlement. Revised POW and DED On-going | 1
|  |  | 1.3 | [6 empty] | b) | Azotes | b) | 2018-01-29 | g) | - | c) | - | b) |  | d) |  | b)
[10 empty] | c) | Manantan | c) | 2018-09-24 | [11 empty] | 1
[10 empty] | d) | 330 C.D | d) | 2018-12-05 | [11 empty] | FS
|  |  | 1.1 | Inst. of transformer and accessories, Brgy. Kinawitnon |  | 20% DF CY 2016 | Elect. | Households | Admin | a) | 150,000.00 | a) | 2018-07-31 | e) | - | a) | 150,000.00 | a) | - | c) | - | a) | - | Purchase Order # 2019103228 - Transformer | 1
[10 empty] | b) | - | b) | - | f) | - | b) | 150,000.00 | b) | - | d) | - | b) | - | Purchase Order # 2019102931 - Billboard | 1
[10 empty] | c) | - | c) | - | g) | - | c) | - | [6 empty] | Purchase Order # 2019103227 - Lumber | 1
[10 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | 1.2 | Rural Electrification at brgy. Sta. Cruz, talikud, Samal |  | 20% DF CY 2016 | Elect. | Households | Contract | a) | 2000000 | a) | - | e) | - | a) | 2000000 | a) | - | c) | - | a) | - | Delay due to slow action of Daneco for staking. c/o Engr. Kim
[10 empty] | b) | - | b) | - | f) | - | b) | 2000000 | b) | - | d) | - | b) | -
[10 empty] | c) |  | c) | - | g) | - | c) | -
[10 empty] | d) | - | d) | -
|  |  | 2 | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) LS - P9,000,000.00 | [19 empty] | See project listed below
1
1
|  |  | 2.1 | Construction of Provincial Training Center |  | 20% DF CY 2016 | Fence | sq.m | Admin | a) | 940,000.00 | a) | 2017-09-19 | e) | - | a) | 940,000.00 | a) | 68.00% | c) | 75.00% | a) | - | Temporarily suspended 4/23/18 due to undemolished structures of illegal settlers | 1
|  |  |  | Compound Fence, Kinawitnon, Babak | [5 empty] | b) | Pacquiao | b) | 2018-03-12 | f) | - | b) | 940,000.00 | b) | - | d) | - | b) | -
|  |  |  | District, IGCS | [5 empty] | c) | PEO | c) | 2018-06-19 | g) | - | c) | 933,418.80 | [7 empty] | FS
[10 empty] | d) | - | d) | - | [11 empty] | 1
|  |  |  | PANABO CITY | [20 empty] | 1
|  |  |  | Const of Market Stall/Building, Consolacion, Panabo City |  | 20% DF CY 2017 (STIMULUS) | Bldg. | sq.m | MLGU | a) | 500000 | a) | 2017-12-28 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Suspended effective April 5, 2020 due to issued Executive Order No. 31, series of 2020 the province of Davao del Norte in response to the State of Public Health Emergency and State of National Calamity (COVID19 Pandemic). | 1
|  |  | 1 | [6 empty] | b) | - | b) | 2019-05-28 | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 1
[10 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 1
[10 empty] | d) | - | d) | - | [11 empty] | 1
|  |  |  | Rehab. Of Multi-Purpose Hall (Covered Court), Upper Licanan, Panabo City |  | 20% DF CY 2017 (STIMULUS) |  | sq.m | MLGU | a) | 500000 | a) | 2017-12-28 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Suspended effective April 5, 2020 due to issued Executive Order No. 31, series of 2020 the province of Davao del Norte in response to the State of Public Health Emergency and State of National Calamity (COVID19 Pandemic). | 1
|  |  | 2 | [6 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 1
[10 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 1
[10 empty] | d) | - | d) | - | [11 empty] | 1
|  |  |  | Impv't. of Multi-Purpose Gym, Kauswagan, Panabo City |  | 20% DF CY 2017 (STIMULUS) | GYM | sq.m | MLGU | a) | 500000 | a) | 2019-02-04 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Suspended effective April 5, 2020 due to issued Executive Order No. 31, series of 2020 the province of Davao del Norte in response to the State of Public Health Emergency and State of National Calamity (COVID19 Pandemic). | 1
|  |  | 3 | [6 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 1
[10 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 1
[10 empty] | d) | - | d) | - | [11 empty] | AC
|  |  |  | Const. of MP Bldg. w/ Electrical installation, San Roque, Panabo City |  | 20% DF CY 2017 (STIMULUS) | Bldg. | sq.m | MLGU | a) | 500000 | a) | 2018-01-31 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Suspended effective April 5, 2020 due to issued Executive Order No. 31, series of 2020 the province of Davao del Norte in response to the State of Public Health Emergency and State of National Calamity (COVID19 Pandemic). | AC
|  |  | 4 | [6 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | AC
[10 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 1
[10 empty] | d) | - | d) | - | [11 empty] | 1
|  |  |  | Const. of Multi-Purpose Bldg.,Cacao, Panabo City |  | 20% DF CY 2017 (STIMULUS) | Bldg. | sq.m | MLGU | a) | 300000 | a) | 2017-12-19 | e) | - | a) | 300000 | a) | - | c) | - | a) | - | Suspended effective April 5, 2020 due to issued Executive Order No. 31, series of 2020 the province of Davao del Norte in response to the State of Public Health Emergency and State of National Calamity (COVID19 Pandemic). | 1
|  |  | 5 | [6 empty] | b) | - | b) | 2018-12-14 | f) | - | b) | 300000 | b) | - | d) | - | b) | - |  | 1
[10 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 1 | 21512501.501
[10 empty] | d) | - | d) | - | [11 empty] | 2
|  |  |  | Const. of Multi-Purpose Bldg. @ A.O. Floriendo National Highschool, Panabo City |  | 20% DF CY 2017 (STIMULUS) | Bldg. | sq.m | MLGU | a) | 500000 | a) | 2017-12-19 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Suspended effective April 5, 2020 due to issued Executive Order No. 31, series of 2020 the province of Davao del Norte in response to the State of Public Health Emergency and State of National Calamity (COVID19 Pandemic). | 2
|  |  | 6 | [6 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 2
[10 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 2
[10 empty] | d) | - | d) | -
STO. TOMAS
|  |  |  | Const. of Concrete Drainage Canal, Kimamon, Panabo City |  | 20% DF CY 2017 (STIMULUS) | Drainage | ln.m | MLGU | a) | 500000 | a) | 2017-12-19 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For Implementation
|  |  | 7 | [6 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | AC
[10 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | AC
[10 empty] | d) | - | d) | - | [11 empty] | AC
|  |  |  | IGACOS | [20 empty] | 1
|  |  |  | Impv't. of Brgy. Street Electrification at Brgy. Anonang, IGCS |  | 20% DF CY 2017 (STIMULUS) | Elect. | Households |  | a) | 500000 | a) | 2017-11-28 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Verified at PBO 7/18/2019 that fund is not available. Proposed priority project for 2020\ | 1
|  |  | 8 | [6 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 1
[10 empty] | c) | PEO | c) | - | g) | - | c) | - | [7 empty] | 1
[10 empty] | d) | - | d) | - | [11 empty] | AC
|  |  | 1.1 | Const. of Trading Post, Storage Building with (1) unit Hauling Truck, Prk. Ramihan Datu Abdul, Panabo City |  | OPPAP-PAMANA CY 2017 | Bldg. |  | Contract | a) | 3,975,000.00 | a) | CY 2017 | e) | - | a) | 3,975,000.00 | a) | 100% | c) | 40.36% | a) | 10 | On-going/ Time extension on process due to suspension of activity due to covid 19 | 2
[10 empty] | b) | Azotes | b) | 2019-11-21 | f) | - | b) | 3,975,000.00 | b) | 0% | d) | -40.36% | b) | 260 |  | 2
[10 empty] | c) | Ultra Core | c) | 2019-04-05 | g) | - | c) | - | [7 empty] | 2
[10 empty] | d) | - | d) | 5/16/2020 | [11 empty] | 2
|  |  |  | Trading Post, Storage and Hauling Truck Libuak, Island Garden City of Samal (IGACOS) |  | OPPAP-PAMANA CY 2017 | - | - | - | a) | 4000000 | a) | CY 2018 | e) | - | a) | 4000000 | a) | - | c) | - | a) | - | For bidding | AC
|  |  | 1.2 | [6 empty] | b) | - | b) | - | f) | - | b) | 4000000 | b) | - | d) | - | b) | - |  | AC
[10 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | AC
` | [9 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | 1.3 | Construction of Tribal Hall, Sto. Tomas |  | OPPAP-PAMANA CY 2017 | Bldg. |  | Admin | a) | 500000 | a) | CY 2018 | e) | - | a) | 500000 | a) | 100% | c) | 89.5% | a) | 7 | Suspended June 28, 2019. Waiting for the delivery of JO Materials | 1
[10 empty] | b) | Roque | b) | 2019-05-22 | f) | - | b) | 500000 | b) | - | d) | -10.5% | b) | 110 |  | 1
[10 empty] | c) | Admin | c) | 2019-07-31 | g) | - | c) | - | [7 empty] | 1
[10 empty] | d) | 70 CD | d) | - | [11 empty] | 1
|  |  | 1.4 | Agricultural Productivity Support Project-Fishing Equipment, Tambo, IGACOS |  | OPPAP-PAMANA CY 2017 | - |  | - | a) | 1500000 | a) | - | e) | - | a) | 1500000 | a) | - | c) | - | a) | - | For bidding | 2
[10 empty] | b) | - | b) | - | f) | - | b) | 1500000 | b) | - | d) | - | b) | - |  | 2
[10 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 2
[10 empty] | d) | - | d) | - | [11 empty] | 2
|  |  | 1 | Construction of Water System Projects in Component LGUs LS - 9,750,000.00 | [19 empty] | See list of projects | 1
1
?
1
|  |  |  | Installation of potable water System at Purok Nangka, Pandapan, Tagum City |  | 20% DF CY 2018 | Water System | Households | Admin | a) | 1125000 | a) | - | e) | - | a) | 1125000 | a) | - | c) | - | a) | - | Waiting for deed of donation. Follow-up letter was already issued | 1
|  |  | 1.1 | [6 empty] | b) | - | b) | - | f) | - | b) | 1125000 | b) | - | d) | - | b) | - |  | 1
[10 empty] | c) | PEO | c) | - | g) | - | c) | - | [7 empty] | 1
[10 empty] | d) | - | d) | - | [11 empty] | 1
|  |  |  | Rehab./Impv't. of San Vicente Water System, Asuncion |  | 20% DF CY 2018 | Water System | Households | Admin | a) | 1125000 | a) | 2018-10-26 | e) | - | a) | 1125000 | a) | - | c) | - | a) | - | Abstract # 0220190484 still draft | 1
|  |  | 1.2 | [6 empty] | b) | - | b) | - | f) | - | b) | 1125000 | b) | - | d) | - | b) | - |  | 1
[10 empty] | c) | PEO | c) | - | g) | - | c) | - | [7 empty] | 1
[10 empty] | d) | - | d) | - | [11 empty] | 1
|  |  |  | Water System at brgy. Malativas, Panabo City |  | 20% DF CY 2018 | Water System | Households | Admin | a) | 1250000 | a) | - | e) | - | a) | 1250000 | a) | - | c) | - | a) | - | For preparation of POW & Plan c/o PDPM - POSSIBLE TRANSFER OF SITE SUBJECT FOR TRANSFER OF LOCATION . NO DEED OF DONATION | 1
|  |  | 1.3 | [6 empty] | b) | - | b) | - | f) | - | b) | 1250000 | b) | - | d) | - | b) | - |  | 1
[10 empty] | c) | Admin | c) | - | g) | - | c) | - | [7 empty] | 1
[10 empty] | d) | - | d) | -
|  |  |  | Const. of Potable Water System at Brgy. Tibungol, Panabo City |  | 20% DF CY 2018 | Water System | Households | Admin | a) | 1250000 | a) | 2018-11-21 | e) | - | a) | 1250000 | a) | 2.13% | c) | 0.76% | a) | 3 | Suspended dated February 19, 2020 undelivered hardware materials (Supplier refused to deliver. Letter already submitted to BAC.) | 1
|  |  | 1.4 | [6 empty] | b) | Andoy | b) | 2020-01-20 | f) | - | b) | 1250000 | b) | - | d) | -1.37% | b) | 15 |  | 1
[10 empty] | c) | Admin | c) | 2020-04-15 | g) | - | c) | - | [7 empty] | 1
[10 empty] | d) | 76 C.D | d) | - | [11 empty] | 1
|  |  |  | Potable Water System at Brgy. San Remegio Kaputian (Level II WS), Samal |  | 20% DF CY 2018 | Water System | Households | Admin | a) | 3625000 | a) | 2018-10-25 | e) | - | a) | 3625000 | a) | 100% | c) | 74.56% | a) | 4 | On-going/ Resumption 5/4/2020 | 1
|  |  | 1.5 | [6 empty] | b) | Diosanta | b) | 2019-07-16 | f) | 89 CD | b) | 3625000 | b) | 72.04% | d) | 2.52% | b) | 88 |  | 1
[10 empty] | c) | Admin | c) | 2020-02-01 | g) | - | c) | 2702800 | [7 empty] | AC
[10 empty] | d) | 200 C.D | d) | 2020-04-30 | [11 empty] | 1
|  |  |  | CARMEN | [19 empty] | Plan and POW Approval on process | 1
|  |  | 1 | Completion of Evacuation Center Building, |  | GENERAL FUND PROPER CY 2018 (STIMULUS) | Bldg. |  | Contract | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - |  | 1
|  |  |  | San Isidro, Carmen | [5 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 1
[10 empty] | c) | Contract | c) | - | g) | - | c) | - | [7 empty] | 1
[10 empty] | d) | - | d) | - | [11 empty] | 1
|  |  |  | PANABO CITY | [19 empty] | (RLHV Design & Build) Winning Bidder | 1
|  |  | 2 | Const. of Perimeter Fence of Day Care Center 1, Nanyo, Panabo City |  | GENERAL FUND PROPER CY 2018 (STIMULUS) | Bldg. |  | Contract | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - |  | FS
[10 empty] | b) | RLHV | b) | 4/7/2020 | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | AC
[10 empty] | c) | Contract | c) | 6/6/2020 | g) | - | c) | - | [7 empty] | 1
[10 empty] | d) | 60 | d) | - | [11 empty] | 1
|  |  |  | Impv't. of Brgy. Road Covered Court, Malativas, Panabo City |  | GENERAL FUND PROPER CY 2018 (STIMULUS) | Court | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Alloted - May 29, 2019, Additional Funding of 500,000.00,SB no. 4 CY 2019 | 1
|  |  | 3 | [6 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 1
[10 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 1
[10 empty] | d) | - | d) | - | [11 empty] | AC
|  |  |  | Rehab. Of Multi-Purpose Gym & Facililies Maduao, Panabo City |  | GENERAL FUND PROPER CY 2018 (STIMULUS) | Gym | sq.m | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Purchase Request # 20032056 | 1
|  |  | 4 | [6 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 1
[10 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 1
[10 empty] | d) | - | d) | - | [11 empty] | 1
|  |  |  | Const. of Multi-Purpose Bldg. Sto. Nino, Panabo City |  | GENERAL FUND PROPER CY 2018 (STIMULUS) | Bldg. | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Plan and POW on process c/o PDPM | 1
|  |  | 5 | [6 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 1
[10 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 1
[10 empty] | d) | - | d) | - | [11 empty] | 1
|  |  |  | Completion of Canopy at DAPCO Covered Court, Dapco, Panabo City |  | GENERAL FUND PROPER CY 2018 (STIMULUS) | Court | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | (RLHV Design & Build) Winning Bidder | AC
|  |  | 6 | [6 empty] | b) | RLHV | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 1
[10 empty] | c) | Contract | c) | - | g) | - | c) | - | [7 empty] | 1
[10 empty] | d) | - | d) | - | [11 empty] | 1
|  |  |  | Perimeter Fence of Day Care Center I & II, Nanyo, Panabo City/ Construction of Perimeter Fence) |  | GENERAL FUND PROPER CY 2018 (STIMULUS) | Bldg. | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For inspection by PDPM for PLAN and POW as of 7/19/2019/ (RLHV Design & Build) Winning Bidder | 1
|  |  | 7 | [6 empty] | b) | - | b) | 4/7/2020 | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 1
[10 empty] | c) | - | c) | 6/6/2020 | g) | - | c) | - | [7 empty] | 1
[10 empty] | d) | - | d) | - | [11 empty] | 1
|  |  |  | IGCS | [20 empty] | 1
|  |  | 8 | Impv't. of Brgy. Water System, Pichon, IGCS (Construction of Elevated Tank) |  | GENERAL FUND PROPER CY 2018 (STIMULUS) | Water |  | Admin | a) | 500000 | a) | 2018-05-31 | e) | - | a) | 500000 | a) | 100% | c) | 83.5% | a) | 5 | Suspended effective April 5, 2020 due to issued Executive Order No. 31, series of 2020 the province of Davao del Norte in response to the State of Public Health Emergency and State of National Calamity (COVID19 Pandemic). | 1
[7 empty] | System |  |  | b) | Andoy | b) | 2020-01-13 | f) | - | b) | 500000 | b) | - | d) | -16.5% | b) | 110 |  | AC
[10 empty] | c) | Admin | c) | 2020-03-13 | g) | - | c) | 423575.63 | [7 empty] | 1
[10 empty] | d) | 80 | d) | - | [11 empty] | 1
|  |  | 9 | Powerline Expansion Project, Cogon, IGACOS |  | GENERAL FUND PROPER CY 2018 (STIMULUS) | Water |  | Contract | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Waiting for NTP | 1
[7 empty] | System |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | AC
[10 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 1
[10 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | 10 | Water System From Prk. 6 - Prk. 2 - Prk. 5A, Tagbay, IGCS |  | GENERAL FUND PROPER CY 2018 (STIMULUS) | Water |  | Admin | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For Implementation | 1
[7 empty] | System |  |  | b) | Pacquiao | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 1
[10 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 1
[10 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | 11 | Powerline Expansion Project, Tambo, IGCS |  | GENERAL FUND PROPER CY 2018 (STIMULUS) | Elect. |  | Contract | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Purchase Request # 19083312 | 1
[10 empty] | b) | Porras | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 1
[10 empty] | c) | Admin | c) | - | g) | - | c) | - | [7 empty] | 1
[10 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | 12 | Improvement of Barangay Hall, Penaplata, IGCS |  | GENERAL FUND PROPER CY 2018 (STIMULUS) | Bldg. |  | Admin | a) | 500000 | a) |  | e) | - | a) | 500000 | a) | - | c) | - | a) | - | By Contract and change to admin due to unforeseen activities because it’s a repair (For revision of POW) | 1
[10 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 1
[10 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | AC
[10 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | 13 | Electrification of Sitio Baongon-Diamond-Mansanitas, Dadatan, IGCS |  | GENERAL FUND PROPER CY 2018 (STIMULUS) | Elect. |  | - | a) | 500000 | a) |  | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Purchase Order # 20200100002 (3E Electrical Sales & Services) | 1
[10 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 1
[10 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 1
[10 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | 14 | Drilling of Water System, Linusotan, IGCS |  | GENERAL FUND PROPER CY 2018 (STIMULUS) | Water |  | - | a) | 500000 | a) |  | e) | - | a) | 500000 | a) | - | c) | - | a) | - | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | 1
[7 empty] | System |  |  | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 1
[10 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 1
[10 empty] | d) | - | d) | - | [11 empty] | FS
|  |  |  | Const./Compl./Impv't. of Various Gov't. Bldgs., Structures & Facilities (Const. in Progress - Bldgs. & Other Structures | [19 empty] | See project listed below | 1
|  | 1 | [22 empty] | 1
1
|  |  |  | Const. of DDN Hospital Carmen Zone Annex Bldg. |  | SB # 1 CY 2018 | Bldg. | sq.m | Admin | a) | 5,500,000.00 | a) | - | e) | - | a) | 5,500,000.00 | a) | - | c) | - | a) | - | Winning Bidder - Digos Constrak Corp. | 1
|  |  | 1.1 | [6 empty] | b) | Estorco | b) | - | f) | - | b) | 5,500,000.00 | b) | - | d) | - | b) | - |  | 1
[10 empty] | c) | PEO | c) | - | g) | - | c) | - | [7 empty] | 1
[10 empty] | d) | - | d) | - | [11 empty] | 1
|  |  | Road ID11DAN | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | [19 empty] | See List of Provincial Roads | 1
1
1
1
|  |  | Road ID11DAN | Road ID11 Jct. Highway Sto. Niño - Cebulano |  | 20% DF CY 2019 | Road Rehabilitation | 2.09 | MBA | a) | 1045000 | a) | 2019-01-03 | e) | 120 CD | a) | 1045000 | a) | 80% | c) | 80% | a) | 6 | On-going/ Time extension on process due to suspension of activity due to covid 19 | 1
[10 empty] | b) | Obar/ Nasol | b) | 2019-05-21 | f) |  | b) | 1045000 | b) | - | d) | - | b) | 132
[10 empty] | c) | PEO | c) | 2019-10-04 | g) | - | c) | - | [7 empty] | AC
[10 empty] | d) | - | d) | 4/15/2020 | [11 empty] | 1
|  |  |  | ROAD ID 076 - Basa - Tubod |  | 20% DF CY 2019 | Road Rehabilitation | 1.56 | MBA | a) | 1000000 | a) | 2019-01-03 | e) | - | a) | 1000000 | a) | 100% | c) | 35.6% | a) | 3 | On-going | 1
[10 empty] | b) | PIAD | b) | 2019-11-11 | f) | - | b) | 1000000 | b) | 60.5% | d) | -24.9% | b) | 30 |  | 1
[10 empty] | c) | Admin | c) | 2020-03-19 | g) | - | c) | [8 empty] | 1
[10 empty] | d) | 120 | d) | 6/30/2020 | [11 empty] | 1
|  |  |  | ROAD ID 077 - Tubod - Pilar |  | 20% DF CY 2019 | Road Rehabilitation | 1.55 | MBA | a) | 16000000 | a) | 2019-11-26 | e) | - | a) | 16000000 | a) | 11.51% | c) | 14.52% | a) | 7 | On-going | 1
| 077 | [8 empty] | b) | Agang | b) | 2019-12-18 | f) | - | b) | 16000000 | b) | - | d) | 3.01% | b) | 210 |  | 1
[10 empty] | c) | Admin | c) | 2020-11-05 | g) | - | c) | 4046971.2 | [7 empty] | 1
[10 empty] | d) | 323 C.D | d) | - | [11 empty] | 1
|  |  |  | ROAD ID 103 - Sitio Malaga - Tibulao |  | 20% DF CY 2019 | Road Rehabilitation | 3.22 | MBA | a) | 1000000 | a) | 2019-01-03 | e) | - | a) | 1000000 | a) | 67.81% | c) | 24.5% | a) | 5 | On-going/ Time extension on process due to suspension of activity due to covid 19 | 1
[10 empty] | b) | Obar | b) | 2019-11-11 | f) | - | b) | 1000000 | b) | - | d) | -43.31% | b) | 110
[10 empty] | c) | Admin | c) | 2020-02-09 | g) | - | c) | [8 empty] | AC
[10 empty] | d) | 90 | d) | 6/30/2020 | [11 empty] | 1
|  |  |  | ROAD ID 104 - Dujali - Tanglaw |  | 20% DF CY 2019 | Road Rehabilitation | 3.6 | MBA | a) | 2075000 | a) | 2019-01-03 | e) | 28 | a) | 2075000 | a) | 50% | c) | 48% | a) | 11 | On-going | 1
| 104 | [8 empty] | b) | Balbastro | b) | 2019-12-28 | f) | 108 | b) | 2075000 | b) | - | d) | -2% | b) | 77 |  | 1
` | [9 empty] | c) | Admin | c) | 2020-04-16 | g) | - | c) | [8 empty] | 1
[10 empty] | d) | 110 | d) | 7/31/2020
|  |  |  | ROAD ID 121 - San Miguel - Libertad |  | 20% DF CY 2019 | Road Rehabilitation | 6.2 | MBA | a) | 1240000 | a) | 2019-01-03 | e) | - | a) | 1240000 | a) | 59.41% | c) | 59.41% | a) | 9 | On-going/ Time extension on process due to suspension of activity due to covid 19 | AC
| 121 | [8 empty] | b) | Gamad | b) | 2019-06-17 | f) | 30 | b) | 1240000 | b) | - | d) | - | b) | 36 |  | 1
[10 empty] | c) | - | c) | 2019-10-31 | g) | - | c) | [8 empty] | 1
[10 empty] | d) | - | d) | 2020-02-29 | [11 empty] | 1
|  |  | ROAD ID 123 | Bacali - Casig-ang - Libertad |  | 20% DF CY 2019 | Road Rehabilitation | 4.7 | MBA | a) | 940000 | a) | 2019-06-07 | e) | - | a) | 940000 | a) | 62.1% | c) | 62% | a) | 9 | On-going/ Time extension on process due to suspension of activity due to covid 19 | 1
| 123 | [8 empty] | b) | Gamad | b) | 2019-06-27 | f) | 35 | b) | 940000 | b) | - | d) | - | b) | 36 |  | 1
[10 empty] | c) | Admin | c) | 2019-09-15 | g) | - | c) | [8 empty] | 1
[10 empty] | d) | 80 C.D | d) | 2020-02-29 | [11 empty] | 1
|  |  | ROAD ID 125 | San Miguel - Moslog - Kinamayan |  | 20% DF CY 2019 | Road Rehabilitation | 2.9 | MBA | a) | 1000000 | a) | 2019-05-20 | e) | - | a) | 1000000 | a) | 100% | c) | 80% | a) | 6 | On-going/ Time extension on process due to suspension of activity due to covid 19 | 1
| 125 | [8 empty] | b) | Gamad | b) | 2019-06-17 | f) | 29 | b) | 1000000 | b) | 73.59% | d) | 6.41% | b) | 30 |  | 1
[10 empty] | c) | - | c) | 2019-09-16 | g) | - | c) | [8 empty] | 1
[10 empty] | d) | - | d) | 2020-02-29 | [11 empty] | 1
|  |  | ROAD ID 131 | Mugas - Lanatad |  | 20% DF CY 2019 | Road Rehabilitation | 1.53 | MBA | a) | 500000 | a) | 2019-01-03 | e) | 90 | a) | 500000 | a) | 100% | c) | 100% | a) | 4 | Completed 3/31/2020 | 1
| 131 | [8 empty] | b) | Balbastro | b) | 2019-08-05 | f) | - | b) | 500000 | b) | - | d) |  | b) | 104 |  | 1
[10 empty] | c) | Admin | c) | 2019-10-06 | g) | 3/31/2020 | c) | [8 empty] | 1
[10 empty] | d) | 60 C.D | d) | 2020-02-29 | [11 empty] | 1
|  |  | ROAD ID 134 | New Katipunan - Pantaron |  | 20% DF CY 2019 | Road Rehabilitation | 1.96 | MBA | a) | 395000 | a) | 2019-01-03 | e) | - | a) | 395000 | a) | 60% | c) | 60% | a) | 4 | On-going/ Time extension on process due to suspension of activity due to covid 19 | 1
| 134 | [8 empty] | b) | Gamad/Clar | b) | 2019-12-27 | f) | - | b) | 395000 | b) | - | d) | - | b) | 24 |  | 1
[10 empty] | c) | - | c) | 2020-02-25 | g) | - | c) | [8 empty] | 1
[10 empty] | d) | 60 | d) | - | [11 empty] | 1
|  |  | ROAD ID 137 | Fd. Rd. 2 - Sto. Tomas - Magwawa |  | 20% DF CY 2019 | Road Rehabilitation | 10.21 | MBA | a) | 3575000 | a) | 2019-01-03 | e) | - | a) | 3575000 | a) | 100% | c) | 100% | a) | 16 | Completed 3/31/2020 | 1
| 137 | [8 empty] | b) | Sanchez | b) | 2019-08-27 | f) | - | b) | 3575000 | b) | - | d) | 0% | b) | 112 |  | 1
[10 empty] | c) | Admin | c) | 2020-01-24 | g) | - | c) | [8 empty] | 1
[10 empty] | d) | 150 C.D | d) | 3/31/20020 | [11 empty] | 1
|  |  | ROAD ID 142 | Jct. Highway - Tanglaw |  | 20% DF CY 2019 | Road Rehabilitation | 3.98 | MBA | a) | 1100000 | a) | 2019-05-16 | e) | - | a) | 1100000 | a) | 100% | c) | 85% | a) | 10 | On-going/ Time extension on process due to suspension of activity due to covid 19 | 1
| 142 | [8 empty] | b) | Gamad/Clar | b) | 2019-06-17 | f) | 29 CD | b) | 1100000 | b) | 73.59% | d) | 11.41% | b) | 50 |  | 1
[10 empty] | c) | PEO | c) | 2019-09-16 | g) | - | c) | [8 empty] | 1
[10 empty] | d) | - | d) | 2020-02-29 | [11 empty] | 1
|  |  | ROAD ID 146 | Bdry. Tagum - Crossing Kinamayan Sto. Tomas |  | 20% DF CY 2019 | Road Rehabilitation | 0.75 | MBA | a) | 3700000 | a) | 2019-01-03 | e) | - | a) | 3700000 | a) | 40% | c) | 40% | a) | 3 | On-going/ Time extension on process due to suspension of activity due to covid 19
| 146 | [8 empty] | b) | Gamad/Clar | b) | 2019-12-27 | f) | - | b) | 3700000 | b) | - | d) | - | b) | 66
[10 empty] | c) | - | c) | 2020-04-25 | g) | - | c) | [8 empty] | 1
[10 empty] | d) | 120 | d) | - | [11 empty] | 1
|  |  |  | Road Rehabilitation of Provincial Roads | [20 empty] | 1
|  |  | 2 | Fr. Rd. 3 - San Jose |  | 20% DF CY 2019 | Road Rehabilitation | 4.55 | Admin | a) |  | a) |  | e) | - | a) |  | a) |  | c) |  | a) |  | POW on process | 1
[10 empty] | b) |  | b) |  | f) | - | b) |  | b) |  | d) |  | b) |  |  | 1
[10 empty] | c) |  | c) |  | g) |  | c) | [8 empty] | 1
[10 empty] | d) |  | d) | [12 empty] | 1
|  |  | 3 | Lower Asuncion - Upper Asuncion |  | 20% DF CY 2019 | Road Rehabilitation | 1.02 | Admin | a) | 8000000 | a) |  | e) | - | a) |  | a) |  | c) |  | a) |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | 1
[10 empty] | b) |  | b) |  | f) | - | b) |  | b) |  | d) |  | b) |  |  | 1
[10 empty] | c) |  | c) |  | g) |  | c) | [8 empty] | 1
[10 empty] | d) |  | d) | [12 empty] | 1
|  |  | 4 | Jct. Highway - Carmen - Mangalcal - Tubod |  | 20% DF CY 2019 | Road Rehabilitation | 11.34 | Admin | a) |  | a) |  | e) | - | a) |  | a) |  | c) |  | a) |  | POW on process | 1
[10 empty] | b) |  | b) |  | f) | - | b) |  | b) |  | d) |  | b) |  |  | 1
[10 empty] | c) |  | c) |  | g) |  | c) | [8 empty] | 1
[10 empty] | d) |  | d) | [12 empty] | 1
|  |  | 5 | Tuganay - Taba |  | 20% DF CY 2019 | Road Rehabilitation | 4.27 | Admin | a) |  | a) |  | e) | - | a) |  | a) |  | c) |  | a) |  | POW on process | 1
[10 empty] | b) |  | b) |  | f) | - | b) |  | b) |  | d) |  | b) |  |  | AC
[10 empty] | c) |  | c) |  | g) |  | c) | [8 empty] | 1
[10 empty] | d) |  | d) | [12 empty] | 1
|  |  | 6 | Jct. Highway - Ising - Magsaysay |  | 20% DF CY 2019 | Road Rehabilitation | 10.84 | Admin | a) | 6000000 | a) |  | e) | - | a) |  | a) |  | c) |  | a) |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | 1
[10 empty] | b) |  | b) |  | f) | - | b) |  | b) |  | d) |  | b) |  |  | 1
[10 empty] | c) |  | c) |  | g) |  | c) | [8 empty] | 1
[10 empty] | d) |  | d) | [12 empty] | 1
|  |  | 7 | Jct. Highway - Guadalupe - Bdry. Tagum |  | 20% DF CY 2019 | Road Rehabilitation | 7.9 | Admin | a) |  | a) |  | e) | - | a) |  | a) |  | c) |  | a) |  | POW on process | 1
[10 empty] | b) |  | b) |  | f) | - | b) |  | b) |  | d) |  | b) |  |  | 1
[10 empty] | c) |  | c) |  | g) |  | c) | [8 empty] | 1
[10 empty] | d) |  | d) | [12 empty] | 1
|  |  | 8 | Sitio Malaga - Tibulao |  | 20% DF CY 2019 | Road Rehabilitation | 3.22 | Admin | a) |  | a) |  | e) | - | a) |  | a) |  | c) |  | a) |  | POW on process | 1
[10 empty] | b) |  | b) |  | f) | - | b) |  | b) |  | d) |  | b) |  |  | 2
[10 empty] | c) |  | c) |  | g) |  | c) | [8 empty] | AC
[10 empty] | d) |  | d) | [12 empty] | AC
|  |  | 9 | Prk. 5 RJS - Prk 6 New Casay |  | 20% DF CY 2019 | Road Rehabilitation | 2.73 | Admin | a) |  | a) |  | e) | - | a) |  | a) |  | c) |  | a) |  | POW on process | AC
[10 empty] | b) |  | b) |  | f) | - | b) |  | b) |  | d) |  | b) |  |  | AC
[10 empty] | c) |  | c) |  | g) |  | c) | [8 empty] | 1
[10 empty] | d) |  | d) | [12 empty] | 1
|  |  | 10 | Dujali - Pawas - San Vicente |  | 20% DF CY 2019 | Road Rehabilitation | 4.42 | Admin | a) |  | a) |  | e) | - | a) |  | a) |  | c) |  | a) |  | POW on process | 1
[10 empty] | b) |  | b) |  | f) | - | b) |  | b) |  | d) |  | b) |  |  | 1
[10 empty] | c) |  | c) |  | g) |  | c) | [8 empty] | 1
[10 empty] | d) |  | d) | [12 empty] | 1
|  |  | 11 | Los Amigos 1 - Esperanza - Los Amigos 2 |  | 20% DF CY 2019 | Road Rehabilitation | 3.59 | Admin | a) | 19200000 | a) |  | e) | - | a) |  | a) |  | c) |  | a) |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | 1
[10 empty] | b) |  | b) |  | f) | - | b) |  | b) |  | d) |  | b) |  |  | AC
[10 empty] | c) |  | c) |  | g) |  | c) | [8 empty] | FS
[10 empty] | d) |  | d) | [12 empty] | AC
|  |  | 12 | San Miguel - Crossing Kinamayan |  | 20% DF CY 2019 | Road Rehabilitation | 2.8 | Admin | a) |  | a) |  | e) | - | a) |  | a) |  | c) |  | a) |  | POW on process | AC
[10 empty] | b) |  | b) |  | f) | - | b) |  | b) |  | d) |  | b) |  |  | AC
[10 empty] | c) |  | c) |  | g) |  | c) | [8 empty] | 1
[10 empty] | d) |  | d) | [12 empty] | 1
|  |  | 13 | Fd Rd 2 - Sto. Tomas - Magwawa |  | 20% DF CY 2019 | Road Rehabilitation | 10.21 | Admin | a) |  | a) |  | e) | - | a) |  | a) |  | c) |  | a) |  | POW on process | 1
[10 empty] | b) |  | b) |  | f) | - | b) |  | b) |  | d) |  | b) |  |  | 1
[10 empty] | c) |  | c) |  | g) |  | c)
[10 empty] | d) |  | d) | [12 empty] | AC
|  |  | 14 | Menzi - Balagunan - Tulalian |  | 20% DF CY 2019 | Road Rehabilitation | 10.63 | Admin | a) | 3720500 | a) |  | e) | - | a) |  | a) |  | c) |  | a) |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | AC
[10 empty] | b) |  | b) |  | f) | - | b) |  | b) |  | d) |  | b) |  |  | AC
[10 empty] | c) |  | c) |  | g) |  | c) | [8 empty] | AC
[10 empty] | d) |  | d) | [12 empty] | AC
|  |  | 15 | Jct. Bdry. Tagum - Talomo |  | 20% DF CY 2019 | Road Rehabilitation | 12.01 | Admin | a) |  | a) |  | e) | - | a) |  | a) |  | c) |  | a) |  | POW on process | AC
[10 empty] | b) |  | b) |  | f) | - | b) |  | b) |  | d) |  | b) |  |  | AC
[10 empty] | c) |  | c) |  | g) |  | c) | [8 empty] | AC
[10 empty] | d) |  | d) | [12 empty] | AC
|  |  | 16 | Rehab. of Anibongan-Salvacion-Cabay-angan Provincial Road with Drainage |  | 20% DF CY 2019 | Road Drainage rehabiliated | - | - | a) | 2000000 | a) | 2019-01-14 | e) | - | a) | 2000000 | a) | 89.8% | c) | 89.8% | a) | 1 | Suspended effective April 5, 2020 due to issued Executive Order No. 31, series of 2020 the province of Davao del Norte in response to the State of Public Health Emergency and State of National Calamity (COVID19 Pandemic). | AC
[10 empty] | b) | Toquero | b) | 5/22/2019 | f) | 149 | b) | 2000000 | b) | - | d) | - | b) | 4 |  | AC
[10 empty] | c) | PEO | c) | 2019-08-04 | g) | - | c) | [8 empty] | AC
[10 empty] | d) | 75 C.D | d) | 12/31/2019
| 2 |  |  | Various of Local Roads & Drainage Development Project (Provincewide) LS - 15,000,000.00 | [19 empty] | See projects listed below | AC
AC
AC
AC
|  |  |  | Rehab. Of Dujali-Pawas-San Vicente Provincial Road |  | 20% DF CY 2019 | Road Drainage rehabiliated | km | Admin | a) | 2000000 | a) | - | e) | - | a) | 1102900 | a) | 20% | c) | 50% | a) | - | Suspended effective April 5, 2020 due to issued Executive Order No. 31, series of 2020 the province of Davao del Norte in response to the State of Public Health Emergency and State of National Calamity (COVID19 Pandemic). | AC
| 2.1 | [8 empty] | b) | Toquero | b) | 2019-11-04 | f) | - | b) | 2000000 | b) | - | d) | - | b) | - |  | 1
[10 empty] | c) | PEO | c) | - | g) | - | c) | - | [7 empty] | 1
[10 empty] | d) | - | d) | - | [11 empty] | 1
|  |  |  | Rehab./Impv't. of Jct. highway Ising-Magsaysay Provincial Road with Drainage |  | 20% DF CY 2019 | Road Drainage rehabiliated | km | Admin | a) | 1500000 | a) | 2019-01-16 | e) | - | a) | 1500000 | a) | - | c) | - | a) | - | Revised POW for approval - Jan. 7, 2020 Revision was made due to scarcity of boulders changing from stone masonry to concrete masonry | 1
| 2.2 | [8 empty] | b) | Toquero | b) | - | f) | - | b) | 1500000 | b) | - | d) | - | b) | - |  | 1
[10 empty] | c) | PEO | c) | - | g) | - | c) | - | [7 empty] | 1
[10 empty] | d) | - | d) | - | [11 empty] | 1
| 3 |  |  | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | [19 empty] | See projects listed below (Note: 1.3M declared savings funded to other Water System Projects-AIP 2nd revision CY 2019) | AC
FS
AC
1
| 3.1 |  |  | Construction of Water System Projects | [20 empty] | 1
|  |  |  | Impv't. of Potable Water System, Consolacion, Panabo City |  | 20% DF CY 2019 | Water System Projects | Households | - | a) | 500000 | a) | 2019-06-28 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | 1
| 3.1.1 | [8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 1
[10 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | AC
[10 empty] | d) | - | d) | - | [11 empty] | 1
|  |  |  | Impv't. of Potable Water System, Tagbitan-ag, Samal Dist. |  | 20% DF CY 2019 | Water System Projects | Households | - | a) | 500000 | a) | 2019-06-19 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For implementation | 1
| 3.1.2 | [8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 1
[10 empty] | c) | - | c) | - | g) | - | c) | -
[10 empty] | d) | - | d) | - | [11 empty] | 1
|  |  |  | Impv't. of Potable Water System, San Antonio, babak, IGCS |  | 20% DF CY 2019 | Water System Projects | - | - | a) | 500000 | a) | 2019-06-25 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | 1
| 3.1.3 | [8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 1
[10 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 1
[10 empty] | d) | - | d) | - | [11 empty] | 1
|  |  |  | Impv't. of Potable Water System, Mambago-A, IGCS |  | 20% DF CY 2019 | Water System Projects | Households | - | a) | 500000 | a) | 2019-09-10 | e) | - | a) | 500000 | a) | - | c) | - | a) | - |  | 1
| 3.1.4 | [8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - | For Implementation | 1
[10 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 1
[10 empty] | d) | - | d) | - | [11 empty] | 1
|  |  |  | Construction of PWS, Brgy. Buenavista, Panabo City |  | 20% DF CY 2019 | Water System Projects | - | - | a) | 500000 | a) | June 19 ,2019 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For implementation | 1
| 3.1.5 | [8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 1
[10 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 1
[10 empty] | d) | - | d) | - | [11 empty] | 1
|  |  |  | Construction of PWS, Brgy. Brgy. Kiotoy, Panabo City |  | 20% DF CY 2019 | Water System Projects | Households | Contract | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | 1
| 3.1.6 | [8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 1
[10 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 1
[10 empty] | d) | - | d) | - | [11 empty] | 1
|  |  |  | Construction of PWS, Brgy. Linusotan, Talikud, District, IGCS |  | 20% DF CY 2019 | Water System Projects | Households | - | a) | 1300000 | a) | 2019-10-23 | e) | - | a) | 1300000 | a) | - | c) | - | a) | - | Procurement on process | 1
| 3.1.7 | [8 empty] | b) | - | b) | - | f) | - | b) | 1300000 | b) | - | d) | - | b) | -
[10 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 1
[10 empty] | d) | - | d) | - | [11 empty] | 1
|  |  |  | Rehab. of PWS, Brgy. San Miguel, Babak, IGCS |  | 20% DF CY 2019 | Water System Projects | Households | Contract | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | 1
| 3.1.8 | [8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 1
[10 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 1
[10 empty] | d) | - | d) | - | [11 empty] | 1
|  |  |  | Construction of PWS, Brgy. Cacao, Panabo City |  | 20% DF CY 2019 | Water System Projects | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For cancellation. Purchase of Geo-resistivity equipment but procurement still on process | 1
| 3.1.9 | [8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | -
[10 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 1
[10 empty] | d) | - | d) | - | [11 empty] | 1
|  |  |  | Rehabilitation of Potable Water System, Brgy. Pangubatan, kaputian Dist. IGCS |  | 20% DF CY 2019 | Water System Projects | Households | Contract | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Purchase Order # 19093434 | 1
| 3.2.0 | [8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 1
[10 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | AC
[10 empty] | d) | - | d) | - | [11 empty] | 1
|  |  |  | Various Government Buildings and Facilities Development Project (Provincewide) LS - P 27,000,000.00 |  |  | Gov't. Bldgs. & Fac. Const./upgraded to cater the needs of recipients | - | Admin | a) | 27000000 | [12 empty] | See projects listed below | 1
[10 empty] | b) | Medalla | [13 empty] | 1
[10 empty] | c) | PEO
[10 empty] | d) | - | [13 empty] | 1
|  |  |  | Const. of DDN Hospital Carmen Zone Annex Bldg. Phase 2, |  | 20% DF CY 2019 | Bldg. | - | Contract | a) | 3620000 | a) | 2019-06-28 | e) | - | a) | 3620000 | a) | - | c) | - | a) | - | For implementation (Winning Bidder - Digos Constrak Corp.) | 1
|  | 4.1 | [7 empty] | b) | - | b) | - | f) | - | b) | 3620000 | b) | - | d) | - | b) | - |  | 1
[10 empty] | c) | Digos Constrak Corp/ | c) | - | g) | - | c) | - | [7 empty] | 1
[10 empty] | d) | - | d) | - | [11 empty] | 1
| 5 |  |  | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [19 empty] | See projects listed below | 1
1
|  |  |  | CARMEN | [20 empty] | AC
|  |  |  | Const. of Multi-Purpose Hall, La Paz, Carmen |  |  | Bldg. | - | - | a) | 500000 | a) | 2019-02-20 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Fund transferred to LGU March 28, 2019 | 1
| 1 | [8 empty] | b) | - | b) | 2019-08-16 | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 1
[10 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 1
[10 empty] | d) | - | d) | - | [11 empty] | 1
|  |  |  | Const. of Evacuation Center Ph. 3, Sto. Niño, Carmen |  |  | Bldg. | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Amended in the AIP 3rd revision CY 2019/ SB No. 4 CY 2019 changing the location to Purok !-c, Sto. Nino since the previous location was implemented by DPWH | 1
| 2 | [8 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 1
[10 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 1
[10 empty] | d) | - | d) | - | [11 empty] | 1
| 3 |  | Const. of Multi-Purpose Hall, Mangalcal, Carmen |  |  |  | Bldg. | - | - | a) | 500000 | a) | 2019-02-20 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Fund transfer to LGU Carmen, 3/28/2019 with check no. 2574953 and OR no. 0118982 | AC
[10 empty] | b) | - | b) | 2019-09-16 | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 1
[10 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 1
[10 empty] | d) | - | d) | - | [11 empty] | 1
| 4 |  | Rehab. of Multi-Purpose Hall, Guadalupe, Carmen |  |  |  | Bldg. | - | - | a) | 500000 | a) | 2019-02-20 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Fund transferred to LGU March 28, 2019
[10 empty] | b) | - | b) | 2019-08-15 | f) | - | b) | 500000 | b) | - | d) | - | b) | -
[10 empty] | c) | - | c) | 2019-11-13 | g) | - | c) | -
[10 empty] | d) | - | d) | -
| 5 |  | Const. of Multi-Purpose Hall, Mabuhay, Carmen |  |  |  | Bldg. | - | - | a) | 500000 | a) | 2019-02-20 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Fund transfer to LGU Carmen, 3/28/2019 with check no. 2574925 and OR no. 0118984
[10 empty] | b) | - | b) | 2019-08-16 | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | AC |  | 893809.45
[10 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | FS
[10 empty] | d) | - | d) | -
| 6 |  | Const. Canal Lining , Mabaus, Carmen |  |  |  | Canal lining | - | - | a) | 500000 | a) | 2019-02-20 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Fund transferred to LGU March 28, 2019 | FS
[10 empty] | b) | - | b) |  | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | AC
[10 empty] | c) | - | c) |  | g) | - | c) | - | [7 empty] | AC
[10 empty] | d) | - | d) | - | [11 empty] | AC
| 7 |  | Rehab. Of Evacuation Center, Alejal, Carmen |  |  |  | Bldg. | - | - | a) | 500000 | a) | 2019-02-20 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Fund transfer to LGU Carmen, 3/28/2019 with check no.2574949 and OR no. 0118991 | AC
[10 empty] | b) | - | b) | 2019-08-16 | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | AC
[10 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 1
[10 empty] | d) | - | d) | - | [11 empty] | 1
| 8 |  | Compl. Of Evacuation Center, Tuganay, Carmen |  |  |  | Bldg. | - | - | a) | 500000 | a) | 2019-02-20 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Fund transfer to LGU Carmen, 3/28/2019 with check no. 2574947 and OR no. 0118995 | 1
[10 empty] | b) | - | b) | 2019-08-16 | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | AC
[10 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 1
[10 empty] | d) | - | d) | - | [11 empty] | 1
| 9 |  | Const. of Multi-Purpose hall, Ising, Carmen |  |  |  | Bldg. | - | - | a) | 500000 | a) | 2019-02-20 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Fund transferred to LGU March 28, 2019 | 1
[10 empty] | b) | - | b) |  | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | AC
[10 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 1
[10 empty] | d) | - | d) | - | [11 empty] | 1
| 10 |  | Rehab. of Multi-Purpose hall, Cebulano, Carmen |  |  |  | Bldg. | - | - | a) | 500000 | a) | 2019-02-20 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Fund transferred to LGU March 28, 2019 | 1
[10 empty] | b) | - | b) | 2019-08-16 | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | AC
[10 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 1
[10 empty] | d) | - | d) | - | [11 empty] | 1
| PANABO CITY | [23 empty] | 1
| 11 |  | Rehab. Of Multi-Purpose Hall, Kasilak, Panabo City |  |  |  | Bldg. | - | Contract | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Purchase Request # 19115111 | AC
[10 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 1
[10 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 1
[10 empty] | d) | - | d) | - | [11 empty] | 1
| 12 |  | Rehab. Of Multi-Purpose Hall, New Malitbog, Panabo City |  |  |  | Bldg. | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Amended in AIP 3rd revsion CY 2019 to change the project to Construction of Potable Water System because the original project will be funded by LGU, Panabo City (Brgy. resolution no. 25 series of 2019 dated Aug. 13, 2019 submitted) | AC
[10 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 1
[10 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 1
1
AC
[10 empty] | d) | - | d) | - | [11 empty] | 1
| 13 |  | Desilting of Canal, New Pandan, Panabo City |  |  |  | Canal lining | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | 1
[10 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 1
[10 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | AC
[10 empty] | d) | - | d) | - | [11 empty] | 1
| 14 |  | Const. Of Multi-Purpose Hall, Waterfall, Panabo City |  |  |  | Bldg. | - | Contract | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Purchase Request # 19125303 | 1
[10 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 1
[10 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | AC
[10 empty] | d) | - | d) | - | [11 empty] | 1
| 15 |  | Concreting of Brgy. Road @ Prk. Guyabano, Cagangohan, Panabo City |  |  |  | Road | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Amended in AIP 3rd revision to change the project to Rehab of Evacuation Center because the original project has no deed of donation.(Brgy. resolution no 41 series of 2019 dated Aug. 16, 2019 submitted | 1
[10 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 1
[10 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | AC
1
[10 empty] | d) | - | d) | - | [11 empty] | 1
| 16 |  | Rehab. Of Evacuation Center, J.P. Laurel, Panabo City |  |  |  | Bldg. | - | Contract | a) | 500000 | a) | 2019-10-23 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Purchase Order # 2020031248 | 1
` | [9 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | AC
[10 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 1
[10 empty] | d) | - | d) | - | [11 empty] | 1
| 17 |  | Const. Of Multi-Purpose Hall, Buenavista, Panabo City |  |  |  | Bldg. | - | Contract | a) | 500000 | a) | 2019-10-18 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Purchase Order # 2020031248 | 1
[10 empty] | b) | - | b) | - | f) |  | b) | 500000 | b) | - | d) | - | b) | - |  | AC
[10 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 1
[10 empty] | d) | - | d) | - | [11 empty] | 1
| 18 |  | Rehab. Of Multi-Purpose Hall, San Francisco, Panabo City |  |  |  | Bldg. | - | Contract | a) | 500000 | a) | 2019-10-18 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Purchase Order # 2020031248 | 1
` | [9 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | AC
[10 empty] | c) | - | c) | - | g) |  | c) | - | [7 empty] | 1
[10 empty] | d) | - | d) | - | [11 empty] | 1
| 19 |  | Rehab. Of Evacuation Center, Datu Abdul Dadia, Panabo City |  |  |  | Bldg. | - | Contract | a) | 500000 | a) | 2019-10-18 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Purchase Order # 2020031248 | 1
[10 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | AC
[10 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 1
[10 empty] | d) | - | d) | - | [11 empty] | 1
| 20 |  | Impv't./Beautification of Brgy. Grounds, Quezon, Panabo City |  |  |  | Ground Dev't. | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Re aligned to other stimulus projects that needs additional funding | 1
` | [9 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | AC
[10 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 1
[10 empty] | d) | - | d) | - | [11 empty] | 1
| 21 |  | Const. of Women Livelihood Center Bldg. , Gredu, Panabo City |  |  |  | Bldg. | - | - | a) | 500000 | a) | 2019-03-28 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Fund transfer to LGU - 3/28/2019 with check no. 2574926 and OR no. 0166517 - March 28, 2019 | 1
[10 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | AC
[10 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 1
[10 empty] | d) | - | d) | - | [11 empty] | 1
| 22 |  | Const. of Canal Lining at Purok 5, Salvacion, Panabo City |  |  |  | Bldg. | - | Contract | a) | 500000 | a) | 2019-10-18 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Purchase Request # 19104835 | 1
` | [9 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | AC
[10 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 1
[10 empty] | d) | - | d) | - | [11 empty] | 1
| 23 |  | Rehab. Of Health Center, New Visayas, Panabo City |  |  |  | Bldg. | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Re aligned to other stimulus projects that needs additional funding | 1
[10 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | AC
[10 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 1
[10 empty] | d) | - | d) | - | [11 empty] | 1
| 24 |  | Rehab. Of Multi-Purpose Hall, Little Panay, Panabo City |  |  |  | Bldg. | - | Contract | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Purchase Request # 19125320 | 1
` | [9 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | AC
[10 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 1
[10 empty] | d) | - | d) | - | [11 empty] | 1
| 25 |  | Rehab. Of Brgy. Health Center, Dalisay, Panabo City |  |  |  | Bldg. | - | Contract | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Purchase Request # 19125279 | 1
[10 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | AC
[10 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 1
[10 empty] | d) | - | d) | - | [11 empty] | 1
| 26 |  | Const. of Multi-Purpose Hall, Southern Davao, Panabo City |  |  |  | Bldg. | - | Contract | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Purchase Request # 19125279 | 1
` | [9 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | AC
[10 empty] | c) | - | c) | - | g) |  | c) | - | [7 empty] | 1
[10 empty] | d) | - | d) | - | [11 empty] | 1
| STO. TOMAS | [23 empty] | 1
| 27 |  | Rehab. Of Evacuation Center, Casig-ang, Sto. Tomas |  |  |  | Bldg. | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | POW preparation on-going c/o Engr. Uy | AC
[10 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 1
[10 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 1
[10 empty] | d) | - | d) | - | [11 empty] | 1
` | 28 |  | Const. of Brgy. Tibal-og Health Center, Tibal-og, Sto. Tomas |  |  |  | Bldg. | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | POW preparation completed amounting t oP1,550,000.00. To request for additional funds in order to complete the project to be functional | AC
[10 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 1
[10 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 1
[10 empty] | d) | - | d) | - | [11 empty] | 1
| 29 |  | Compl.of Brgy. Public Market, La Libertad, Sto. Tomas |  |  |  | Bldg. | - | - | a) | 500000 | a) |  | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Fund transfer to LGU - 6/26/219 with check no. 2575131 and OR no. 0557457 Completed/ PCR for submission by LGU | AC
[10 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 1
[10 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 1
[10 empty] | d) | - | d) | - | [11 empty] | 1
` | 30 |  | Rehab. Of Evacuation Center, New Visayas, Sto. Tomas |  |  |  | Bldg. | - | - | a) | 500000 | a) |  | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Fund transfer to LGU - 6/26/219 with check no. 2575132 and OR no. 0557455 For implementation | AC
[10 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 1
[10 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 1
[10 empty] | d) | - | d) | - | [11 empty] | 1
| 31 |  | Rehab. Of Multi-Purpose Hall, San Vicente, Sto. Tomas |  |  |  | Bldg. | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Fund transferred to LGU July 5, 2019 | AC
[10 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 1
[10 empty] | c) | - | c) | - | g) |  | c) | - | [7 empty] | 1
[10 empty] | d) | - | d) | - |  | - | [9 empty] | 1
` | 32 |  | Rehab. Of Multi-Purpose Hall, Salvacion, Sto. Tomas |  |  |  | Bldg. | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | AC
[10 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 1
[10 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 1
[10 empty] | d) | - | d) | - | [11 empty] | 1
| 33 |  | Rehab. Of Multi-Purpose Hall, Pantaron, Sto. Tomas |  |  |  | Bldg. | - | - | a) | 500000 | a) |  | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Amended in AIP 3rd revision CY 2019 / SB No. 4 CY 2019 increasing the project cost to P550,000.00 | AC
[10 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 1
[10 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 1
[10 empty] | d) | - | d) | - | [11 empty] | 1
` | 34 |  | Rehab. Of Multi-Purpose Hall, Magwawa, Sto. Tomas |  |  |  | Bldg. | sq.m | Contract | a) | 500000 | a) | June 19 2019 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Purchase Request # 19115111 | AC
[10 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 1
[10 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 1
[10 empty] | d) | - | d) | - | [11 empty] | 1
| 35 |  | Compl. Of Multi-Purpose Hall, San Jose, Sto. Tomas |  |  |  | Bldg. | - | - | a) | 500000 | a) |  | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Amended in AIP 3rd revision CY 2019 / SB No. 4 CY 2019 increasing the project cost to P600,000.00 | AC
[10 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 1
[10 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 1
[10 empty] | d) | - | d) | - | [11 empty] | 1
` | 36 |  | Const. of Evacuation Center, Bobongon, Sto. Tomas |  |  |  | Bldg. | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Re aligned to other stimulus projects that needs additional funding | AC
[10 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 1
[10 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 1
[10 empty] | d) | - | d) | - | [11 empty] | 1
| 37 |  | Rehab. Of Brgy. Road, Lunga-og, Sto. Tomas |  |  |  | Bldg. | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Amended in AIP 3rd revision CY 2019 / SB No. 4 CY 2019 increasing the project cost to P600,000.00 | AC
[10 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 1
[10 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 1
[10 empty] | d) | - | d) | - | [11 empty] | 1
` | 38 |  | Rehab. Of Multi-Purpose Hall, New Katipunan, Sto. Tomas |  |  |  | Bldg. | sq.m | Contract | a) | 500000 | a) | 2019-06-07 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Purchase Request # 19125279 | AC
[10 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 1
[10 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 1
[10 empty] | d) | - | d) | - | [11 empty] | 1
| 39 |  | Rehab. Of Multi-Purpose Hall, San Miguel, Sto. Tomas |  |  |  | Bldg. | sq.m | Contract | a) | 500000 | a) | 2019-06-07 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Purchase Request # 19115111 | AC
[10 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 1
[10 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 1
[10 empty] | d) | - | d) | - | [11 empty] | 1
` | 40 |  | Rehab. Of Multi-Purpose Hall, Talomo, Sto. Tomas |  |  |  | Bldg. | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Fund transfer to LGU - 6/26/2019 with check no. 2575130 and OR no. 0557456 For implementation | AC
[10 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 1
[10 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 1
[10 empty] | d) | - | d) | - | [11 empty] | 1
| IGCS | [23 empty] | AC
| 41 |  | Concreting of Brgy. Road From Prk. 3 to Prk. 5, Catagman, IGCS |  |  |  | Road | km | Contract | a) | 500000 | a) | 2019-01-14 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For implementation | 1
[10 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 1
[10 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 1
` | [9 empty] | d) | - | d) | - | [11 empty] | AC
| 42 |  | Rehab. Of Multi-Purpose Hall, San Jose, IGCS |  |  |  | Bldg. | sq.m | Admin | a) | 500000 | a) | 2019-03-25 | e) | - | a) | 500000 | a) | 100% | c) | 100% | a) | 3 | Completed 3/22/2020 | 1
[10 empty] | b) | Porras | b) | 2019-01-02 | f) | - | b) | 500000 | b) | - | d) | 0% | b) | 44 |  | 1
[10 empty] | c) | PEO | c) | 2020-03-22 | g) | 3/22/2020 | c) | - | [7 empty] | 1
[10 empty] | d) | 80 CD | d) | - | [11 empty] | AC
| 43 |  | Electrification at Sitio Trinidad, Bandera, IGCS |  |  |  | Elect. | Households | Contract | a) | 500000 | a) | 2019-03-25 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Purchase Request # 19031251 | 1
[10 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 1
[10 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 1
` | [9 empty] | d) | - | d) | - | [11 empty] | AC
| 44 |  | Rehab. Of Multi-Purpose Hall, Del Monte, IGCS |  |  |  | Bldg. | - | Admin | a) | 500000 | a) | 2019-05-29 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Pending/ activity undertaken by DPWH | 1
[10 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 1
[10 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 1
[10 empty] | d) | - | d) | - | [11 empty] | AC
| 45 |  | Electrification at Upper Purok Rosal, Tagbaobo, IGCS |  |  |  | Elect. | Households | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Purchase Order # 2020010002 (3E Electrical Sales & Services) | 1
[10 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 1
[10 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 1
` | [9 empty] | d) | - | d) | - | [11 empty] | AC
| 46 |  | Const. Of Multi-Purpose Hall, Mambago-B, IGCS |  |  |  | Bldg. | sq.m | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | 100% | c) | 97.59% | a) | 5 | Suspended effective April 5, 2020 due to issued Executive Order No. 31, series of 2020 the province of Davao del Norte in response to the State of Public Health Emergency and State of National Calamity (COVID19 Pandemic). | 1
[10 empty] | b) | Roque | b) | 2019-10-18 | f) | 64 CD | b) | 500000 | b) | 99.48% | d) | -1.89% | b) | 22 |  | 1
[10 empty] | c) | PEO | c) | 2019-12-27 | g) | - | c) | - | [7 empty] | 1
[10 empty] | d) | 60 CD | d) | 2020-03-29 | [11 empty] | AC
| 47 |  | Const. Of Multi-Purpose Hall, San Antonio, IGCS |  |  |  | Bldg. | sq.m | - | a) | 500000 | a) | 2019-06-19 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For implementation Proposed date started 3/24/2020 | 1
[10 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 1
[10 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 1
` | [9 empty] | d) | - | d) | - | [11 empty] | AC
| 48 |  | Rehab. Of Water System Intake Box and Pipeline, Pangubatan, IGCS |  |  |  | Water System | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Plan and Pow completed. Waiting of deed of donation | 1
[10 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 1
[10 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 1
[10 empty] | d) | - | d) | - | [11 empty] | AC
| 49 |  | Const. Of Multi-Purpose Hall, Cogon (Talicud), IGCS |  |  |  | Bldg. | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For implementation | 1
[10 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 1
[10 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 1
` | [9 empty] | d) | - | d) | - | [11 empty] | AC
| 50 |  | Installation of Pipelines, Libertad, IGCS |  |  |  | Water System | Households | - | a) | 500000 | a) | 2019-03-25 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For implementation | 1
[10 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 1
[10 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 1
[10 empty] | d) | - | d) | - | [11 empty] | AC
| 51 |  | Rehab. Of Evacuation Center, Libuak, IGCS |  |  |  | Bldg. | - | - | a) | 500000 | a) | 2019-05-29 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For implementation | 1
[10 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 1
[10 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 1
` | [9 empty] | d) | - | d) | - | [11 empty] | AC
| 52 |  | Const. of Water System Project, Pob. Kaputian, IGCS |  |  |  | Water System | Households | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For implementation | 1
[10 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 1
[10 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 1
[10 empty] | d) | - | d) | - | [11 empty] | AC
| 53 |  | Rehab. Of Potable Water System, San Isidro, Babak, IGCS |  |  |  | Water System | Households | - | a) | 500000 | a) | 2019-06-19 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For implementation | 1
[10 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 1
[10 empty] | c) | - | c) | - | g) |  | c) | - | [7 empty] | 1
` | [9 empty] | d) | - | d) | - | [11 empty] | AC
| 54 |  | Rehab. Of Potable Water System, San Miguel, IGCS |  |  |  | Water System | Households | - | a) | 500000 | a) | 2019-02-28 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For implementation | 1
[10 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 1
[10 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 1
[10 empty] | d) | - | d) | - | [11 empty] | AC
| 55 |  | Const. of Water System Ph.II, San Remegio, IGCS |  |  |  | Water System | Households | - | a) | 500000 | a) | 2019-05-29 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For implementation | 1
[10 empty] | b) | Porras | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 1
[10 empty] | c) | Admin | c) | - | g) | - | c) | - | [7 empty] | 1
` | [9 empty] | d) | - | d) | - | [11 empty] | AC
| 56 |  | Electrificatio at Prk. 1,3,4, 6,7 & 8, Licup, IGCS |  |  |  | Elect. | Households | - | a) | 500000 | a) | 2019-02-20 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For implementation | 1
[10 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 1
[10 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 1
[10 empty] | d) | - | d) | - | [11 empty] | AC
| 6. Rural Electrification Project (Provincewide) | [5 empty] | Powerlines/posts installed & rehabilitated | Households | - | a) | 5000000 | [12 empty] | See projects listed below | 1
[10 empty] | b) | Kim Pao Lu | [13 empty] | 1
[10 empty] | c) | - | [13 empty] | 1
` | [9 empty] | d) | - | [13 empty] | AC
|  |  | Rural Electrification at Sitio Sagrada, Pob. Kaputian, IGCS |  |  |  | Elect. | Households | - | a) | 1000000 | a) | - | e) | - | a) | 1000000 | a) | - | c) | - | a) | - | Purchase Request # 19031251 | 1
|  | 6.1 | [7 empty] | b) | P.Bueno | b) | - | f) | - | b) | 1000000 | b) | - | d) | - | b) | - |  | 1
[10 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 1
[10 empty] | d) | - | d) | - | [11 empty] | AC
| K. | 5% CALAMITY FUND CY 2019 | [22 empty] | 1
|  | DISASTER PREVENTION AND MITIGATION | [22 empty] | 1
|  | Flood Control and Slope Protection | [22 empty] | 1
` | 1 |  | Revitment of Dike and Slope Proection |  |  |  | Protection dikes/slope protection | ln.m | Admin | a) | 3000000 | [12 empty] | See project listed below | AC
[10 empty] | b) | - | [13 empty] | 1
[10 empty] | c) | - | [13 empty] | 1
[10 empty] | d) | - | [13 empty] | 1
` |  |  |  | Repair/Rehab. Of Upper Tuganay Dike |  |  | creeks and canals deislted | - | - | a) | 1000000 | a) | 2019-08-15 | e) | - | a) | 1000000 | a) | 60% | c) | 70% | a) | 9 | Suspended effective April 5, 2020 due to issued Executive Order No. 31, series of 2020 the province of Davao del Norte in response to the State of Public Health Emergency and State of National Calamity (COVID19 Pandemic). | AC
|  |  | 1.1 | [6 empty] | b) | Toquero | b) | 2019-08-19 | f) | - | b) | 1000000 | b) | - | d) |  | b) | 80 |  | 1
[10 empty] | c) | Admin | c) | 2019-09-29 | g) |  | c) | - | [7 empty] | 1
[10 empty] | d) | 59 C.D | d) | - | [11 empty] | 1
|  |  | Improvement of roads, drainage and canal |  |  |  | Protection dikes/slope protection | - | - | a) | 3000000 |  |  |  | - | [8 empty] | See project listed below | 1
|  | 2 | [7 empty] | b) | Paraguya | [13 empty] | 1
[10 empty] | c) | PEO | [13 empty] | 1
[10 empty] | d) | - | [13 empty] | AC
|  |  |  | Rehab./Impv't. of Prk. 1 - Prk. 2 Sitio Pawas Provincial Road |  |  | Road | km | Admin | a) | 1500000 | a) | 2019-07-23 | e) | - | a) | 1500000 | a) | 100% | c) | 100% | a) | 2 | Completed 12/15/2019 | 1
|  |  | 2.1 | [6 empty] | b) | Sanchez | b) | 2019-08-05 | f) |  | b) | 1500000 | b) | - | d) | 0% | b) | 10 |  | 1
` | [9 empty] | c) | Admin | c) | 2019-09-28 | g) | 12/15/2020 | c) | - | [7 empty] | AC
[10 empty] | d) | 55 | d) | - | [11 empty] | 1
` | CALAMITY/ OPLAN CANAL | [22 empty] | On-going | AC
|  |  |  | Repair of Damaged Drainage/ Creek along Abucay Creek |  |  |  | - | - | a) | 1320000 | a) |  | e) |  | a) |  | a) | 100% | c) | 85% | a) |  |  | 1
|  |  | 1 | [6 empty] | b) | Ganaba | b) | 2019-10-01 | f) |  | b) |  | b) |  | d) |  | b) |  |  | 1
[10 empty] | c) | Admin | c) | 2019-12-02 | g) |  | c) | [8 empty] | 1
[10 empty] | d) | 65 C.D | d) | 2019-12-31 | [11 empty] | AC
|  |  |  | Repair of Damaged Drainage Creek along Panabo River | [5 empty] | a) | 665000 | a) |  | e) |  | a) |  | a) | 15.3% | c) | 15.3% | a) |  | On-going | 1
|  |  | 2 | [6 empty] | b) | Alconera | b) | 2019-11-15 | f) |  | b) |  | b) |  | d) |  | b) |  |  | 1
[10 empty] | c) | Admin | c) | 2020-01-27 | g) |  | c) | [8 empty] | 1
` | [9 empty] | d) | 73 C.D | d) | [12 empty] | AC
|  |  |  | Repair of Damaged Drainage/Creek along Tuganay-Ising River | [5 empty] | a) | 1540500 | a) |  | e) |  | a) |  | a) | 25.6% | c) | 23.6% | a) | 3 | On-going | 1
|  |  | 3 | [6 empty] | b) | Ganaba | b) | 2019-11-15 | f) |  | b) |  | b) |  | d) | -2% | b) | 66 |  | 1
[10 empty] | c) | Admin | c) | 2020-05-15 | g) |  | c) | [8 empty] | 1
[10 empty] | d) | 182 C.D | d) | [12 empty] | AC
|  |  |  | Repair of Damaged Drainage/ Creeks along San Miguel NIA Road | [5 empty] | a) | 470000 | a) |  | e) |  | a) |  | a) | 80% | c) | 80% | a) | 3 | On-going | 1
|  |  | 4 | [6 empty] | b) | Nasol | b) |  | f) |  | b) |  | b) |  | d) |  | b) | 66 |  | 1
[10 empty] | c) | Admin | c) |  | g) |  | c) | [8 empty] | 1
` | [9 empty] | d) |  | d) | [12 empty] | AC
|  |  |  | Repair of Damaged Drainage/ Creeks along Sadpodon Creek | [5 empty] | a) | 470000 | a) |  | e) |  | a) |  | a) |  | c) |  | a) |  | For implementation | 1
|  |  | 5 | [6 empty] | b) |  | b) |  | f) |  | b) |  | b) |  | d) |  | b) |  |  | 1
[10 empty] | c) | Admin | c) |  | g) |  | c) | [8 empty] | 1
[10 empty] | d) |  | d) | [12 empty] | AC
` | L. | SUPPLEMENTAL BUDGET NO. 3 CY 2019 | [22 empty] | AC
|  | LOCALLY FUNDED PROGRAM/PROJECTS- 20% DEVELOPMENT FUND | [22 empty] | 1
|  | INFRASTRUCTURE DEVELOPMENT PROGRAM | [22 empty] | 1
|  | 1. 8918/ Various Local Roads & Drainage Development Project Construction in Progress- Infrastructure Assets | [22 empty] | 1
` |  | ■ |  | Rehabilitation of Dujali-Pawas-San Vicente Provincial Road, B.E. Dujali |  |  | Road | km | - | a) | 2000000 | a) | - | e) | - | a) | 2000000 | a) | - | c) | - | a) | - | The amount was reduced to P1,102,900.00 | AC
|  |  | 1.1 | [6 empty] | b) | - | b) | - | f) | - | b) | 2000000 | b) | - | d) | - | b) | - |  | 1
[10 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 1
[10 empty] | d) | - | d) | - | [11 empty] | 1
2. 8918/ VariousWater System Development Project Construction in Progress- Infrastructure Assets
|  | ■ |  | Improvement of Potable Water System at Brgy. Mambago- A, Samal District, IGACOS |  |  | Water System | Households | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | (Amended in the AIP 2nd Revision to change the location from Peñaplata to Samal District) PO approved September 2, 2019 | 1
|  |  | 2.1 | [6 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 1
[10 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 1
[10 empty] | d) | - | d) | - | [11 empty] | 2
|  | ■ |  | Rehabilitation of Potable Water System at Brgy. San Miguel, Samal District, IGACOS |  |  | Water System | Households | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For implementation | 1
|  |  | 2.2 | [6 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 1
[10 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 1
[10 empty] | d) | - | d) | - | [11 empty] | 2
|  | ■ |  | Construction of Potable Water System at Brgy.Linusotan, Kaputian District, IGACOS |  |  | Water System | Households | - | a) | 1300000 | a) | - | e) | - | a) | 1300000 | a) | - | c) | - | a) | - | (Additional 800,000.00 from Const. of PWS in purok 2, Pag-asa, Kapalong which was funded by OPAPP CY 2018) (amended) For allotment- October 15, 2019 | 1
|  |  | 2.3 | [6 empty] | b) | - | b) | - | f) | - | b) | 1300000 | b) | - | d) | - | b) | - |  | 1
[10 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 1
[10 empty] | d) | - | d) | - | [11 empty] | 2
|  | DISASTER REHABILITATION & RECOVERY PROGRAM Building Back Better Project | [22 empty] | 1
|  | 1. Repairs & Maintenance- Infrastructure Assets | [22 empty] | 1
|  | ■ |  | Disiltation of Mactan River (Ph. II) |  |  | Desiltation | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | PLAN AND POW on process c/o PEO-PDPM | 1
|  |  | 1.1 | [6 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 2
[10 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 1
[10 empty] | d) | - | d) | - | [11 empty] | 1
|  | 2. Property, Plant and Equipmen Construction in Progress- Infrastructure Assets | [22 empty] | 1
|  |  |  | Rehabilitation of Dujali-Balisong-Magupising Provincial Road |  |  | Road | km | Admin | a) | 1280000 | a) | - | e) | - | a) | 1280000 | a) | 100% | c) | 6.48% | a) | - | Suspended effective April 5, 2020 due to issued Executive Order No. 31, series of 2020 the province of Davao del Norte in response to the State of Public Health Emergency and State of National Calamity (COVID19 Pandemic). | 2
|  |  | 2.1 | [6 empty] | b) | Mellomida | b) | 2019-12-02 | f) | 20 CD | b) | 1280000 | b) | 97.61% | d) | -91.13% | b) | - |  | 1
[10 empty] | c) | PEO | c) | 2020-02-03 | g) | - | c) | - | [7 empty] | 1
[10 empty] | d) | - | d) | - | [11 empty] | 1
| M. | SUPPLEMENTAL BUDGET NO. 4 CY 2019
INFRASTRUCTURE DEVELOPMENT PROGRAM
LOCALLY FUNDED PROGRAMS/ PROJECTS GENERAL FUND PROPER
|  | 1 | PEACE AND ORDER PROGRAM/1914 Construction in Progress- Land Improvements | [21 empty] | 2
|  | ■ |  | Rehabilitation of San Jose- Sitio Mahayahay-Magwawa Provincial Road, Sto. Tomas |  |  | Road | - | - | a) | 1000000 | a) | - | e) | - | a) | 1000000 | a) | - | c) | - | a) | - | POW preparation on-going c/o South District | 1
|  |  | 1.1 | [6 empty] | b) | - | b) | - | f) | - | b) | 1000000 | b) | - | d) | - | b) | - |  | 1
[10 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 2
[10 empty] | d) | - | d) | - | [11 empty] | 1
|  | 2 | 8918/ Various Local Roads and Drainage Development Project Construction in Progress- Infrastructure Assets | [21 empty] | 1
|  | ■ |  | Rehabilitation of Local Roads at Dalisay-Manay Road Section, Panabo City |  |  | Road | - | - | a) | 246100 | a) | - | e) | - | a) | 246100 | a) | - | c) | - | a) | - | For implementation | 1
|  |  | 2.1 | [6 empty] | b) | - | b) | - | f) | - | b) | 246100 | b) | - | d) | - | b) | - |  | 2
[10 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 1
[10 empty] | d) | - | d) | - | [11 empty] | 1
|  | ■ |  | Rehabilitation of Local Roads at Sta. Cruz-Jct. Tagpore-Buenavista Raod Section, Panabo City |  |  | Road | - | - | a) | 431000 | a) | - | e) | - | a) | 431000 | a) | - | c) | - | a) | - | For implementation | 1
|  |  | 2.2 | [6 empty] | b) | - | b) | - | f) | - | b) | 431000 | b) | - | d) | - | b) | - |  | 2
[10 empty] | c) | - | c) | - | g) |  | c) | - | [7 empty] | 1
[10 empty] | d) | - | d) | - | [11 empty] | 1
|  | ■ |  | Rehabilitation of Local Roads at Taba-Bucana Road Section, Taba, Carmen |  |  | Road | - | - | a) | 220000 | a) | - | e) | - | a) | 220000 | a) | - | c) | - | a) | - | For implementation | 1
|  |  | 2.3 | [6 empty] | b) | - | b) | - | f) | - | b) | 220000 | b) | - | d) | - | b) | - |  | 2
[10 empty] | c) | - | c) | - | g) | - | c) | -
[10 empty] | d) | - | d) | -
|  | 3 | 8918/ Stimulus Projects for Various Barangays Construction in Progress- Infrastructure Assets
|  | ■ |  | Concreting of Brgy. Road Canal, Dujali, B.E. Dujali |  |  | Road | - | contract | a) | 650000 | a) | - | e) | - | a) | 650000 | a) | - | c) | - | a) | - | For implementation
|  |  | 3.1 | [6 empty] | b) | - | b) | - | f) | - | b) | 650000 | b) | - | d) | - | b) | - |  | 1
[10 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 1
[10 empty] | d) | - | d) | - | [11 empty] | 2
|  | ■ |  | Desilting and Conretign of Drainage-Main Collector Canal, New Casay, B.E. Dujali |  |  | Desiltation | - | contract | a) | 650000 | a) | - | e) | - | a) | 650000 | a) | - | c) | - | a) | - | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | 1
|  |  | 3.2 | [6 empty] | b) | - | b) | - | f) | - | b) | 650000 | b) | - | d) | - | b) | - |  | 1
[10 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 1
[10 empty] | d) | - | d) | - | [11 empty] | 2
|  | ■ |  | Concreting of Drainage, Tanglaw, B.E., Dujali |  |  | Drainage | - | contract | a) | 1200000 | a) | - | e) | - | a) | 1200000 | a) | - | c) | - | a) | - | For implementation | 1
|  |  | 3.3 | [6 empty] | b) | - | b) | - | f) | - | b) | 1200000 | b) | - | d) | - | b) | - |  | 1
[10 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | 1
[10 empty] | d) | - | d) | - | [11 empty] | 2
|  |  |  | Construction of Potable Water System, New Malitbog, Panabo City |  |  | Water System | Households | contract | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | 1
|  |  | 3.4 | [6 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  | 1
[10 empty] | c) | - | c) | - | g) | - | c) | -
[10 empty] | d) | - | d) | -
|  | ■ |  | Construction of Water System Project, Poblacion Kaputian, Samal |  |  | Water System | Households | contract | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For implementation
|  |  | 3.5 | [6 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | -
[10 empty] | c) | - | c) | - | g) | - | c) | -
[10 empty] | d) | - | d) | - | [11 empty] | 1
|  | ■ |  | Construction of Canal Lining at Prk. 5, Salvacion, Panabo City |  |  |  |  | contract | a) | 600000 | a) | - | e) | - | a) | 600000 | a) | - | c) | - | a) | - | For implementation | 1
|  |  | 3.6 | [6 empty] | b) | - | b) | - | f) | - | b) | 600000 | b) | - | d) | - | b) | - |  | 1
[10 empty] | c) | - | c) | - | g) | - | c) | - | [7 empty] | FS
[10 empty] | d) | - | d) | -
|  | ■ |  | Rehabilitation of Brgy. Road at Lunga-og. Sto. Tomas |  |  |  |  | contract | a) | 600000 | a) | - | e) | - | a) | 600000 | a) | - | c) | - | a) | - | For implementation
|  |  | 3.7 | [6 empty] | b) | - | b) | - | f) | - | b) | 600000 | b) | - | d) | - | b) | -
[10 empty] | c) | - | c) | - | g) | - | c) | -
[10 empty] | d) | - | d) | -
|  | 4 | 8918/ Stimulus Projects for Various Barangays Construction in Progress- Bldgs. & Other Structures
|  | ■ |  | Construction of Evacuation Center at Purok 1-C Brgy. Sto. Niño, Carmen |  |  |  |  | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For implementation
|  |  | 4.1 | [6 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | -
[10 empty] | c) | - | c) | - | g) |  | c) | -
[10 empty] | d) | - | d) | -
|  | ■ |  | Construction of Multi-Purpose Hall, Waterfall, Panabo City |  |  |  |  | - | a) | 1050000 | a) | - | e) | - | a) | 1050000 | a) | - | c) | - | a) | - | For implementation
|  |  | 4.2 | [6 empty] | b) | - | b) | - | f) | - | b) | 1050000 | b) | - | d) | - | b) | -
[10 empty] | c) | - | c) | - | g) | - | c) | -
[10 empty] | d) | - | d) | -
|  |  |  | Rehabilitation of Multi-Purpose Hall, San Francisco, Panabo City |  |  |  |  | - | a) | 600000 | a) | - | e) | - | a) | 600000 | a) | - | c) | - | a) | - | For implementation
|  |  | 4.3 | [6 empty] | b) | - | b) | - | f) | - | b) | 600000 | b) | - | d) | - | b) | -
[10 empty] | c) | - | c) | - | g) | - | c) | -
[10 empty] | d) | - | d) | -
|  | ■ |  | Rehabilitation of Evacuation Center at Datu Abdul Dadia, Panabo City |  |  |  |  | - | a) | 650000 | a) | - | e) | - | a) | 650000 | a) | - | c) | - | a) | - | For implementation
|  |  | 4.4 | [6 empty] | b) | - | b) | - | f) | - | b) | 650000 | b) | - | d) | - | b) | -
[10 empty] | c) | - | c) | - | g) | - | c) | -
[10 empty] | d) | - | d) | -
|  |  |  | Construction of Multi-Purpose Hall, Buenavista, Panabo City |  |  |  |  | - | a) | 1050000 | a) | - | e) | - | a) | 1050000 | a) | - | c) | - | a) | - | For implementation
|  |  | 4.5 | [6 empty] | b) | - | b) | - | f) | - | b) | 1050000 | b) | - | d) | - | b) | -
[10 empty] | c) | - | c) | - | g) | - | c) | -
[10 empty] | d) | - | d) | -
|  |  |  | Rehabilitation of Multi-Purpose Hall, Llittle Panay, Panabo City |  |  |  |  | - | a) | 550000 | a) | - | e) | - | a) | 550000 | a) | - | c) | - | a) | - | For implementation
|  |  | 4.6 | [6 empty] | b) | - | b) | - | f) | - | b) | 550000 | b) | - | d) | - | b) | -
[10 empty] | c) | - | c) | - | g) | - | c) | -
[10 empty] | d) | - | d) | -
|  |  |  | Rehabilitation of Multi-Purpose Hall, Pantaron, Sto. Tomas |  |  |  |  | - | a) | 550000 | a) | - | e) | - | a) | 550000 | a) | - | c) | - | a) | - | For implementation
|  |  | 4.7 | [6 empty] | b) | - | b) | - | f) | - | b) | 550000 | b) | - | d) | - | b) | -
[10 empty] | c) | - | c) | - | g) | - | c) | -
[10 empty] | d) | - | d) | -
|  | ■ |  | Rehabilitation of Multi-Purpose Hall, Salvacion, Sto. Tomas |  |  |  |  | - | a) | 1000000 | a) | - | e) | - | a) | 1000000 | a) | - | c) | - | a) | - | POW preparation on-going c/o PDPM
|  |  | 4.8 | [6 empty] | b) | - | b) | - | f) | - | b) | 1000000 | b) | - | d) | - | b) | -
[10 empty] | c) | - | c) | - | g) | - | c) | -
[10 empty] | d) | - | d) | -
|  |  |  | Completion of Multi-Purpose Hall, San Jose, Sto. Tomas |  |  |  |  | - | a) | 600000 | a) | - | e) | - | a) | 600000 | a) | - | c) | - | a) | - | For implementation
|  |  | 4.9 | [6 empty] | b) | - | b) | - | f) | - | b) | 600000 | b) | - | d) | - | b) | -
[10 empty] | c) | - | c) | - | g) | - | c) | -
[10 empty] | d) | - | d) | -
|  |  |  | Rehabilitation of Multi-Purpose Hall, Kasilak, Panabo City |  |  |  |  | - | a) | 650000 | a) | - | e) | - | a) | 650000 | a) | - | c) | - | a) | - | For implementation
|  |  | 5 | [6 empty] | b) | - | b) | - | f) | - | b) | 650000 | b) | - | d) | - | b) | -
[10 empty] | c) | - | c) | - | g) |  | c) | -
[10 empty] | d) | - | d) | -
|  |  |  | Rehabilitation of Brgy. Health Center, Dalisay, Panabo City |  |  |  |  | - | a) | 550000 | a) | - | e) | - | a) | 550000 | a) | - | c) | - | a) | - | For implementation
|  |  | 5.1 | [6 empty] | b) | - | b) | - | f) | - | b) | 550000 | b) | - | d) | - | b) | -
[10 empty] | c) | - | c) | - | g) | - | c) | -
[10 empty] | d) | - | d) | -
|  |  |  | Rehabilitation of Evacuation Center, Kiotoy, Panabo City |  |  |  |  | - | a) | 650000 | a) | - | e) | - | a) | 650000 | a) | - | c) | - | a) | - | For implementation
|  |  | 5.2 | [6 empty] | b) | - | b) | - | f) | - | b) | 650000 | b) | - | d) | - | b) | -
[10 empty] | c) | - | c) | - | g) | - | c) | -
[10 empty] | d) | - | d) | -
|  |  |  | Rehabilitation of Evacuation Center, Cagangohan, Panabo City |  |  |  |  | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Purchase Request # 19125279
|  |  | 5.3 | [6 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | -
[10 empty] | c) | - | c) | - | g) | - | c) | -
[10 empty] | d) | - | d) | -
|  |  |  | Rehabilitation of Multi-Purpose Bldg. (Brgy. Hall) Tagpopongan, IGACOS |  |  |  |  | - | a) | 174460.33 | a) | - | e) | - | a) | 174460.33 | a) | - | c) | - | a) | - | Procurement on process
|  |  | 5.4 | [6 empty] | b) | - | b) | - | f) | - | b) | 174460.33 | b) | - | d) | - | b) | -
[10 empty] | c) | - | c) | - | g) | - | c) | -
[10 empty] | d) | - | d) | -
|  | 5 | INFRASTRUCTURE DEVELOPMENT PROGRAM
|  | ■ |  | Construction of Multi-Purpose Building, Balagunan, Sto. Tomas |  |  | Bldg. | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For implementation
|  |  | 5.1 | [6 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | -
[10 empty] | c) | - | c) | - | g) | - | c) | -
[10 empty] | d) | - | d) | -
| N. | TRUST FUND 2019
1. CMGP 2019
|  | ■ |  | Road Upgrading of Sto Nino - Kabankalan - La Paz Provincial Road, Carmen |  |  |  |  | - | a) | 44461624.67 | a) | CY 2019 | e) | - | a) | 44561687 | a) | 32.2% | c) | 65.03% | a) | 42 | On-going
|  |  | 1.1 | [6 empty] | b) | Comidoy | b) | 2019-10-07 | f) | - | b) | 44561687 | b) | - | d) | 32.83% | b) | 610
[10 empty] | c) | GP & H CONST. | c) | 2020-05-15 | g) |  | c) | 6,684,253.05
[10 empty] | d) | 222 C.D | d) | 7/20/2020
|  | ■ |  | Road Upgrading of Jct Highway - Sto Nino - La Paz - San Vicenter Provincial Road, Carmen |  |  |  |  | - | a) | 80481331.34 | a) | CY 2019 | e) | - | a) | 80481331.34 | a) | 77.27% | c) | 78.31% | a) | 40 | On-going
|  |  | 1.2 | [6 empty] | b) | Fernandez | b) | 2019-10-07 | f) | - | b) | 80481331.34 | b) | - | d) | 1.04% | b) | 660
[10 empty] | c) | Tagum Builders | c) | 2020-06-22 | g) | - | c) | 45,481,609.97
[10 empty] | d) | 259 C.D | d) | 8/4/2020
| II. | PROJECTS UNDER THE CURRENT APPROPRIATION
| A. | GENERAL FUND CY 2020
INFRASTRUCTURE DEVELOPMENT PROGRAMS
| Road ID |  | 1. Maintenance Of Various Prov'l. Roads and Bridges 2 |  |  |  |  | 288.26 |  | a) | 11801752 | [12 empty] | See list of Provincial Roads
[10 empty] | b) | Matuguinas
| 11DAN | [8 empty] | c) | PEO
[10 empty] | d) | 261 days
|  |  | Cebulano - Mangalcal |  |  |  | Road Maintenance | 4.17 | MBA | a) | 134,672.70 | a) | 2020-01-02 | e) | 134,672.70 | a) |  | a) | 14% | c) | 20% | a) | 64 | On-going / Time extension on process due to suspension of activity
| 073 | [8 empty] | b) | Gamad/Clar | b) | 2020-01-02 | f) | 134,672.70 | b) |  | b) |  | d) |  | b) | 1280
[10 empty] | c) | Admin | c) | 2020-12-31 | g) |  | c)
[10 empty] | d) | 1 year | d)
|  |  | Cebulano - Mangalcal |  |  |  | Road Maintenance | 4.17 | CBRMC | a) | 131,004.66 | a) |  | e) | 131,004.66 | a) |  | a) |  | c) |  | a) |  | Purchase Order # 2020030966 (Brgy. Mangalcal Women's Household)
| 073 | [8 empty] | b) | Maligro | b) |  | f) | 131,004.66 | b) |  | b) |  | d) |  | b)
[10 empty] | c) |  | c) |  | g) |  | c)
[10 empty] | d) | 6 months | d)
|  |  | Tubod - basa - Mangalcal |  |  |  | Road Maintenance | 3.93 | MBA | a) | 143530.25 | a) | 2020-01-02 | e) | 143530.25 | a) |  | a) | 16% | c) | 20% | a) | 3 | On-going / Time extension on process due to suspension of activity
| 074 | [8 empty] | b) | Gamad/Clar | b) | 2020-01-02 | f) | 143530.25 | b) |  | b) |  | d) |  | b) | 66
[10 empty] | c) | Admin | c) | 2020-12-31 | g) |  | c)
[10 empty] | d) | 1 year | d) |  | `
|  |  | Tubod - basa - Mangalcal |  |  |  | Road Maintenance | 3.93 | CBRMC | a) | 106,856.33 | a) |  | e) | 106,856.33 | a) |  | a) |  | c) |  | a) |  | Purchase Order # 2020030985 (Tubod Centro Lower Irrigator's Association)
| 074 | [8 empty] | b) | Maligro | b) |  | f) | 106,856.33 | b) |  | b) |  | d) |  | b)
[10 empty] | c) |  | c) |  | g) |  | c)
[10 empty] | d) | 6 months | d)
|  |  | Upper Mangalcal - Lower Mangalcal |  |  |  | Road Maintenance | 2.43 | MBA | a) | 82,374.21 | a) | 2020-01-02 | e) | 82,374.21 | a) |  | a) | 16% | c) | 20% | a) | 3 | On-going / Time extension on process due to suspension of activity
| 078 | [8 empty] | b) | Gamad/Clar | b) | 2020-01-02 | f) | 82,374.21 | b) |  | b) |  | d) |  | b) | 66
[10 empty] | c) | Admin | c) | 2020-12-31 | g) |  | c)
[10 empty] | d) | 1 year | d)
|  |  | Upper Mangalcal - Lower Mangalcal |  |  |  | Road Maintenance | 2.43 | CBRMC | a) | 72444.97 | a) |  | e) | 72444.97 | a) |  | a) |  | c) |  | a) |  | Purchase Order # 2020030948 (Brgy. Mangalcal Women's Homebased Association)
| 078 | [8 empty] | b) | Maligro | b) |  | f) | 72444.97 | b) |  | b) |  | d) |  | b)
[10 empty] | c) |  | c) |  | g) |  | c)
[10 empty] | d) | 6 months | d)
|  |  | Cebulano - Loceta |  |  |  | Road Maintenance |  | MBA | a) | 72051.43 | a) | 2020-01-02 | e) | 72051.43 | a) |  | a) | 16% | c) | 20% | a) | 3 | On-going / Time extension on process due to suspension of activity
| 079 | [8 empty] | b) | Gamad/Clar | b) | 2020-01-02 | f) | 72051.43 | b) |  | b) |  | d) |  | b) | 66
[10 empty] | c) | Admin | c) | 2020-12-31 | g) |  | c)
[10 empty] | d) | 1 year | d)
|  |  | Cebulano - Loceta |  |  |  | Road Maintenance |  | CBRMC | a) | 47089.26 | a) |  | e) | 47089.26 | a) |  | a) |  | c) |  | a) |  | Purchase Order # 2020030965 (Brgy. Mangalcal Women's Homebased Association)
| 079 | [8 empty] | b) | Maligro | b) |  | f) | 47089.26 | b) |  | b) |  | d) |  | b)
[10 empty] | c) |  | c) |  | g) |  | c)
[10 empty] | d) | 6 months | d)
|  |  | Jct. Highway Carmen - Mangalcal - Tubod |  |  |  | Road Maintenance | 11.34 | MBA | a) | 462895.06 | a) | 2020-01-02 | e) | 462895.06 | a) |  | a) | 16% | c) | 17% | a) | 4 | On-going / Time extension on process due to suspension of activity
| 082 | [8 empty] | b) | Gamad/Clar | b) | 2020-01-02 | f) | 462895.06 | b) |  | b) |  | d) |  | b) | 88
[10 empty] | c) | Admin | c) | 2020-12-31 | g) |  | c)
[10 empty] | d) | 1 year | d)
|  |  | Jct. Highway Carmen - Mangalcal - Tubod |  |  |  | Road Maintenance | 11.34 | CBRMC | a) | 259594.46 | a) |  | e) | 259594.46 | a) |  | a) |  | c) |  | a) |  | Abstract # 0320201443
| 082 | [8 empty] | b) | Maligro | b) |  | f) | 259594.46 | b) |  | b) |  | d) |  | b)
[10 empty] | c) |  | c) |  | g) |  | c)
[10 empty] | d) | 6 months | d)
|  |  | Ising - Sadpodon - Taba - Dila -Dila |  |  |  | Road Maintenance | 5.68 | MBA | a) | 226651.27 | a) | 2020-01-02 | e) | 226651.27 | a) |  | a) | 16% | c) | 16% | a) | 3 | On-going / Time extension on process due to suspension of activity
| 086 | [8 empty] | b) | Gamad/Clar | b) | 2020-01-02 | f) | 226651.27 | b) |  | b) |  | d) |  | b) | 66
[10 empty] | c) | Admin | c) | 2020-12-31 | g) |  | c)
[10 empty] | d) | 1 year | d)
|  |  | Ising - Sadpodon - Taba - Dila -Dila |  |  |  | Road Maintenance | 5.68 | CBRMC | a) | 135230.61 | a) |  | e) | 135230.61 | a) |  | a) |  | c) |  | a) |  | Abstract # 0320201448
| 086 | [8 empty] | b) | Maligro | b) |  | f) | 135230.61 | b) |  | b) |  | d) |  | b)
[10 empty] | c) |  | c) |  | g) |  | c)
[10 empty] | d) | 6 months | d)
|  |  | Tuganay - taba |  |  |  | Road Maintenance | 4.27 | MBA | a) | 169418.15 | a) | 2020-01-02 | e) | 169418.15 | a) |  | a) | 15% | c) | 16% | a) | 3 | On-going / Time extension on process due to suspension of activity
| 087 | [8 empty] | b) | Gamad/Clar | b) | 2020-01-02 | f) | 169418.15 | b) |  | b) |  | d) |  | b) | 66
[10 empty] | c) | Admin | c) | 2020-12-31 | g) |  | c)
[10 empty] | d) | 1 year | d)
|  |  | Tuganay - taba |  |  |  | Road Maintenance | 4.27 | CBRMC | a) | 102630.37 | a) |  | e) | 102630.37 | a) |  | a) |  | c) |  | a) |  | Abstract # 0320201446
| 087 | [8 empty] | b) | Maligro | b) |  | f) | 102630.37 | b) |  | b) |  | d) |  | b)
[10 empty] | c) |  | c) |  | g) |  | c)
[10 empty] | d) | 6 months | d)
|  |  | Jct. Highway Tuganay - Taba |  |  |  | Road Maintenance | 4.4 | MBA | a) | 222375.04 | a) | 2020-01-02 | e) | 222375.04 | a) |  | a) | 16% | c) | 16% | a) | 3 | On-going / Time extension on process due to suspension of activity
| 088 | [8 empty] | b) | Gamad/Clar | b) | 2020-01-02 | f) | 222375.04 | b) |  | b) |  | d) |  | b) | 66
[10 empty] | c) | Admin | c) | 2020-12-31 | g) |  | c)
[10 empty] | d) | 1 year | d)
|  |  | Jct. Highway Tuganay - Taba |  |  |  | Road Maintenance | 4.4 | CBRMC | a) | 57955.99 | a) |  | e) | 57955.99 | a) |  | a) |  | c) |  | a) |  | Purchase Order # 2020030976 (Ezra Christian Minsitry For Peace, Inc.)
| 088 | [8 empty] | b) | Maligro | b) |  | f) | 57955.99 | b) |  | b) |  | d) |  | b)
[10 empty] | c) |  | c) |  | g) |  | c)
[10 empty] | d) | 6 months | d)
|  |  | Jct. Highway Ising - Magsaysay |  |  |  | Road Maintenance | 10.84 | MBA | a) | 478128.48 | a) | 2020-01-02 | e) | 478128.48 | a) |  | a) | 15% | c) | 16% | a) | 3 | On-going / Time extension on process due to suspension of activity
| 089 | [8 empty] | b) | Gamad/Clar | b) | 2020-01-02 | f) | 478128.48 | b) |  | b) |  | d) |  | b) | 66
[10 empty] | c) | Admin | c) | 2020-12-31 | g) |  | c)
[10 empty] | d) |  | d)
|  |  | Jct. Highway Ising - Magsaysay |  |  |  | Road Maintenance | 10.84 | CBRMC | a) | 212505.24 | a) |  | e) | 212505.24 | a) |  | a) |  | c) |  | a) |  | Purchase Order # 2020030969 (School in the Air Integrated Farmer's Associiation)
| 089 | [8 empty] | b) | Maligro | b) |  | f) | 212505.24 | b) |  | b) |  | d) |  | b)
[10 empty] | c) |  | c) |  | g) |  | c)
[10 empty] | d) | 6 months | d)
|  |  | Maligaya - New Camiling |  |  |  | Road Maintenance |  | MBA | a) | 51790.26 | a) | 2020-01-02 | e) | 51790.26 | a) |  | a) | 16% | c) | 16% | a) | 3 | On-going / Time extension on process due to suspension of activity
| 090 | [8 empty] | b) | Gamad/Clar | b) | 2020-01-02 | f) | 51790.26 | b) |  | b) |  | d) |  | b) | 66
[10 empty] | c) | Admin | c) | 2020-12-31 | g) |  | c)
[10 empty] | d) | 1 year | d)
|  |  | Maligaya - New Camiling |  |  |  | Road Maintenance |  | CBRMC | a) | 83915.44 | a) |  | e) | 83915.44 | a) |  | a) |  | c) |  | a) |  | Purchase Order # 2020030967 (School in the Air Integrated Farmer's Associiation)
| 090 | [8 empty] | b) | Maligro | b) |  | f) | 83915.44 | b) |  | b) |  | d) |  | b)
[10 empty] | c) |  | c) |  | g) |  | c)
[10 empty] | d) | 9 months | d)
|  |  | New Camiling - Alejal - Lower Magsaysay |  |  |  | Road Maintenance | 6.73 | MBA | a) | 277852.05 | a) | 2020-01-02 | e) | 277852.05 | a) |  | a) | 16% | c) | 16% | a) | 3 | On-going / Time extension on process due to suspension of activity
| 091 | [8 empty] | b) | Gamad/Clar | b) | 2020-01-02 | f) | 277852.05 | b) |  | b) |  | d) |  | b) | 66
[10 empty] | c) | Admin | c) | 2020-12-31 | g) |  | c)
[10 empty] | d) | 1 year | d)
|  |  | New Camiling - Alejal - Lower Magsaysay |  |  |  | Road Maintenance | 6.73 | CBRMC | a) | 150927.01 | a) |  | e) | 150927.01 | a) |  | a) |  | c) |  | a) |  | Purchase Order # 2020030970 (School in the Air Integrated Farmer's Associiation)
| 091 | [8 empty] | b) | Maligro | b) |  | f) | 150927.01 | b) |  | b) |  | d) |  | b)
[10 empty] | c) |  | c) |  | g) |  | c)
[10 empty] | d) | 6 months | d)
|  |  | Jct. highway Tuganay - Anibongan |  |  |  | Road Maintenance | 3.66 | MBA | a) | 139609.7 | a) | 2020-01-02 | e) | 139609.7 | a) |  | a) | 15% | c) | 16% | a) | 4 | On-going / Time extension on process due to suspension of activity
| 094 | [8 empty] | b) | Gamad/Clar | b) | 2020-01-02 | f) | 139609.7 | b) |  | b) |  | d) |  | b) | 88
[10 empty] | c) | Admin | c) | 2020-12-31 | g) |  | c)
[10 empty] | d) | 1 year | d)
|  |  | Jct. highway Tuganay - Anibongan |  |  |  | Road Maintenance | 3.66 | CBRMC | a) | 93574.75 | a) |  | e) | 93574.75 | a) |  | a) |  | c) |  | a) |  | Purchase Order # 2020030977 (Ezra Christian Minsitry For Peace, Inc.)
| 094 | [8 empty] | b) | Maligro | b) |  | f) | 93574.75 | b) |  | b) |  | d) |  | b)
[10 empty] | c) |  | c) |  | g) |  | c)
[10 empty] | d) | 6 months | d)
|  |  | Anibongan - Guadalupe |  |  |  | Road Maintenance | 2.48 | MBA | a) | 85559.79 | a) | 2020-01-02 | e) | 85559.79 | a) |  | a) | 16% | c) | 17% | a) | 4 | On-going / Time extension on process due to suspension of activity
| 095 | [8 empty] | b) | Gamad/Clar | b) | 2020-01-02 | f) | 85559.79 | b) |  | b) |  | d) |  | b) | 78
[10 empty] | c) | Admin | c) | 2020-12-31 | g) |  | c)
[10 empty] | d) | 1 year | d)
|  |  | Anibongan - Guadalupe |  |  |  | Road Maintenance | 2.48 | CBRMC | a) | 72444.97 | a) |  | e) | 72444.97 | a) |  | a) |  | c) |  | a) |  | Abstract # 0320201444
| 095 | [8 empty] | b) | Maligro | b) |  | f) | 72444.97 | b) |  | b) |  | d) |  | b)
[10 empty] | c) |  | c) |  | g) |  | c)
[10 empty] | d) | 6 months | d)
|  |  | Tuganay - Anibongan - San Isidro |  |  |  | Road Maintenance | 7.22 | MBA | a) | 344085.79 | a) | 2020-01-02 | e) | 344085.79 | a) |  | a) | 16% | c) | 17% | a) | 3 | On-going / Time extension on process due to suspension of activity
| 096 | [8 empty] | b) | Gamad/Clar | b) | 2020-01-02 | f) | 344085.79 | b) |  | b) |  | d) |  | b) | 66
[10 empty] | c) | Admin | c) | 2020-12-31 | g) |  | c)
[10 empty] | d) | 1 year | d)
|  |  | Tuganay - Anibongan - San Isidro |  |  |  | Road Maintenance | 7.22 | CBRMC | a) | 115911.95 | a) |  | e) | 115911.95 | a) |  | a) |  | c) |  | a) |  | Purchase Order # 2020030975 (Ezra Christian Minsitry For Peace, Inc.)
| 096 | [8 empty] | b) | Maligro | b) |  | f) | 115911.95 | b) |  | b) |  | d) |  | b)
[10 empty] | c) |  | c) |  | g) |  | c)
[10 empty] | d) | 6 months | d)
|  |  | Jct. Anibongan - Prk. 2, 7, 5, San Isidro |  |  |  | Road Maintenance | 3.14 | MBA | a) | 89575.84 | a) | 2020-01-02 | e) | 89575.84 | a) |  | a) | 16% | c) | 17% | a) | 4 | On-going / Time extension on process due to suspension of activity .
| 097 | [8 empty] | b) | Gamad/Clar | b) | 2020-01-02 | f) | 89575.84 | b) |  | b) |  | d) |  | b) | 88
[10 empty] | c) | Admin | c) | 2020-12-31 | g) |  | c)
[10 empty] | d) | 1 year | d)
|  |  | Jct. Anibongan - Prk. 2, 7, 5, San Isidro |  |  |  | Road Maintenance | 3.14 | CBRMC | a) | 110478.58 | a) |  | e) | 110478.58 | a) |  | a) |  | c) |  | a) |  | Abstract # 0320201404
| 097 | [8 empty] | b) | Maligro | b) |  | f) | 110478.58 | b) |  | b) |  | d) |  | b)
[10 empty] | c) |  | c) |  | g) |  | c)
[10 empty] | d) | 6 months | d)
|  |  | Anibongan - Salvacion - Cabay-angan |  |  |  | Road Maintenance | 6.93 | MBA | a) | 279123.9 | a) | 2020-01-02 | e) | 279123.9 | a) |  | a) | 16% | c) | 18% | a) | 4 | On-going / Time extension on process due to suspension of activity
| 098 | [8 empty] | b) | Gamad/Clar | b) | 2020-01-02 | f) | 279123.9 | b) |  | b) |  | d) |  | b) | 88
[10 empty] | c) | Admin | c) | 2020-12-31 | g) |  | c)
[10 empty] | d) |  | d)
|  |  | Anibongan - Salvacion - Cabay-angan |  |  |  | Road Maintenance | 6.93 | CBRMC | a) | 162397.48 | a) |  | e) | 162397.48 | a) |  | a) |  | c) |  | a) |  | Abstract # 0320201409
| 098 | [8 empty] | b) | Maligro | b) |  | f) | 162397.48 | b) |  | b) |  | d) |  | b)
[10 empty] | c) |  | c) |  | g) |  | c)
[10 empty] | d) | 6 months | d)
|  |  | Mabaus - Cabay - angan |  |  |  | Road Maintenance |  | MBA | a) | 113320.9 | a) | 2020-01-02 | e) | 113320.9 | a) |  | a) | 16% | c) | 18% | a) | 3 | On-going / Time extension on process due to suspension of activity
| 099 | [8 empty] | b) | Gamad/Clar | b) | 2020-01-02 | f) | 113320.9 | b) |  | b) |  | d) |  | b) | 66
[10 empty] | c) | Admin | c) | 2020-12-31 | g) |  | c)
[10 empty] | d) |  | d)
|  |  | Mabaus - Cabay - angan |  |  |  | Road Maintenance |  | CBRMC | a) | 90556.21 | a) |  | e) | 90556.21 | a) |  | a) |  | c) |  | a)
| 099 | [8 empty] | b) | Maligro | b) |  | f) | 90556.21 | b) |  | b) |  | d) |  | b) |  | Bidding on process
[10 empty] | c) |  | c) |  | g) |  | c)
[10 empty] | d) | 6 months | d)
|  |  | Jct. Highway Guadalupe - Bdry. Tagum |  |  |  | Road Maintenance | 7.9 | MBA | a) | 517780.87 | a) | 2020-01-02 | e) | 517780.87 | a) |  | a) | 16% | c) | 18% | a) | 3 | On-going
| 101 | [8 empty] | b) | Gamad/Clar | b) | 2020-01-02 | f) | 517780.87 | b) |  | b) |  | d) |  | b) | 66
[10 empty] | c) | Admin | c) | 2020-12-31 | g) |  | c)
[10 empty] | d) | 9 months | d)
|  |  | Jct. Highway Guadalupe - Bdry. Tagum |  |  |  | Road Maintenance | 7.9 | CBRMC | a) | 231823.89 | a) |  | e) | 231823.89 | a) |  | a) |  | c) |  | a)
| 101 | [8 empty] | b) | Maligro | b) |  | f) | 231823.89 | b) |  | b) |  | d) |  | b) |  | Bidding on process
[10 empty] | c) |  | c) |  | g) |  | c)
[10 empty] | d) | 6 months | d)
|  |  | Dujali - Tanglaw |  |  |  | Road Maintenance |  | MBA | a) | 135183.27 | a) | 2020-01-02 | e) | 135183.27 | a) |  | a) | 15% | c) | 15% | a) | 3 | On-going
| 104 | [8 empty] | b) | Gamad/Clar | b) | 2020-01-02 | f) | 135183.27 | b) |  | b) |  | d) |  | b) | 66
[10 empty] | c) | Admin | c) | 2020-12-31 | g) |  | c)
[10 empty] | d) |  | d)
|  |  | Dujali - Tanglaw |  |  |  | Road Maintenance |  | CBRMC | a) | 94178.48 | a) |  | e) | 94178.48 | a) |  | a) |  | c) |  | a) |  | Purchase Order # 2020030948 (Dujali Poblacion Farmer's Irrigator's Association, Inc.)
| 104 | [8 empty] | b) | Maligro | b) |  | f) | 94178.48 | b) |  | b) |  | d) |  | b)
[10 empty] | c) |  | c) |  | g) |  | c)
[10 empty] | d) | 6 months | d)
|  |  | Poblacion Dujali - Prk. 8 Dujali |  |  |  | Road Maintenance | 8.2 | MBA | a) | 329064 | a) | 2020-01-02 | e) | 329064 | a) |  | a) | 15% | c) | 16% | a) | 3 | On-going
| 105 | [8 empty] | b) | Gamad/Clar | b) | 2020-01-02 | f) | 329064 | b) |  | b) |  | d) |  | b) | 66
[10 empty] | c) | Admin | c) | 2020-12-31 | g) |  | c)
[10 empty] | d) |  | d)
|  |  | Poblacion Dujali - Prk. 8 Dujali |  |  |  | Road Maintenance | 8.2 | CBRMC | a) | 193371.11 | a) |  | e) | 193371.11 | a) |  | a) |  | c) |  | a) |  | Purchase Order # 2020030981 (Dujali Poblacion Farmer's Irrigator's Association, Inc.)
| 105 | [8 empty] | b) | Maligro | b) |  | f) | 193371.11 | b) |  | b) |  | d) |  | b)
[10 empty] | c) |  | c) |  | g) |  | c)
[10 empty] | d) | 6 months | d)
|  |  | Dujali - San Isidro |  |  |  | Road Maintenance | 3 | MBA | a) | 112652.73 | a) | 2020-01-02 | e) | 112652.73 | a) |  | a) | 8% | c) | 10% | a) | 3 | On-going
| 107 | [8 empty] | b) | Gamad/Clar | b) | 2020-01-02 | f) | 112652.73 | b) |  | b) |  | d) | 2% | b) | 66
[10 empty] | c) | Admin | c) | 2020-12-31 | g) |  | c)
[10 empty] | d) |  | d)
|  |  | Dujali - San Isidro |  |  |  | Road Maintenance | 3 | CBRMC | a) | 78482.06 | a) |  | e) | 78482.06 | a) |  | a) |  | c) |  | a) |  | Abstract # 0320201451
| 107 | [8 empty] | b) | Maligro | b) |  | f) | 78482.06 | b) |  | b) |  | d) |  | b)
[10 empty] | c) |  | c) |  | g) |  | c)
[10 empty] | d) | 6 months | d)
|  |  | New Casay - Bugtong Talisay |  |  |  | Road Maintenance |  | MBA | a) | 74294.5 | a) | 2020-01-02 | e) | 74294.5 | a) |  | a) | 6% | c) | 10% | a) | 4 | On-going
| 108 | [8 empty] | b) | Gamad/Clar | b) | 2020-01-02 | f) | 74294.5 | b) |  | b) |  | d) | 4% | b) | 88
[10 empty] | c) | Admin | c) | 2020-12-31 | g) |  | c)
[10 empty] | d) | 1 year | d)
|  |  | New Casay - Bugtong Talisay |  |  |  | Road Maintenance |  | CBRMC | a) | 64596.78 | a) |  | e) | 64596.78 | a) |  | a) |  | c) |  | a)
| 108 | [8 empty] | b) | Maligro | b) |  | f) | 64596.78 | b) |  | b) |  | d) |  | b) |  | Bidded 2/20/2020
[10 empty] | c) |  | c) |  | g) |  | c)
[10 empty] | d) | 6 months | d)
|  |  | Dujali - Balisong - Magupising |  |  |  | Road Maintenance | 5.52 | MBA | a) | 235776.07 | a) | 2020-01-02 | e) | 235776.07 | a) |  | a) | 8% | c) | 7% | a) | 3 | On-going / Time extension on process due to suspension of activity
| 113 | [8 empty] | b) | Gamad/Clar | b) | 2020-01-02 | f) | 235776.07 | b) |  | b) |  | d) | -1% | b) | 22
[10 empty] | c) | Admin | c) | 2020-12-31 | g) |  | c)
[10 empty] | d) | 1 year | d)
|  |  | Dujali - Balisong - Magupising |  |  |  | Road Maintenance | 5.52 | CBRMC | a) | 115911.95 | a) |  | e) | 115911.95 | a) |  | a) |  | c) |  | a) |  | Purchase Order # 2020030978 (Dujali Poblacion Farmer's Irrigator's Association, Inc.)
| 113 | [8 empty] | b) | Maligro | b) |  | f) | 115911.95 | b) |  | b) |  | d) |  | b)
[10 empty] | c) |  | c) |  | g) |  | c)
[10 empty] | d) | 9 months | d)
|  |  | Dujali - Pawas - San Vicente |  |  |  | Road Maintenance | 4.42 | MBA | a) | 141544.99 | a) | 2020-01-02 | e) | 141544.99 | a) |  | a) | 8% | c) | 7% | a) | 3 | On-going / Time extension on process due to suspension of activity
| 117 | [8 empty] | b) | Gamad/Clar | b) | 2020-01-02 | f) | 141544.99 | b) |  | b) |  | d) | -1% | b) | 22
[10 empty] | c) | Admin | c) | 2020-12-31 | g) |  | c)
[10 empty] | d) | 1 year | d)
|  |  | Dujali - Pawas - San Vicente |  |  |  | Road Maintenance | 4.42 | CBRMC | a) | 140060.27 | a) |  | e) | 140060.27 | a) |  | a) |  | c) |  | a) |  | Bidding on process
| 117 | [8 empty] | b) | Maligro | b) |  | f) | 140060.27 | b) |  | b) |  | d) |  | b)
[10 empty] | c) |  | c) |  | g) |  | c)
[10 empty] | d) | 6 months | d)
|  |  | Jct. Salvacion - San Vicente - Cabay-angan |  |  |  | Road Maintenance | 3.45 | MBA | a) | 168583.81 | a) | 2020-01-02 | e) | 168583.81 | a) |  | a) | 10% | c) | 8% | a) | 3 | On-going / Time extension on process due to suspension of activity
| 118 | [8 empty] | b) | Gamad/Clar | b) | 2020-01-02 | f) | 168583.81 | b) |  | b) |  | d) | -2% | b) | 60
[10 empty] | c) | Admin | c) | 2020-12-31 | g) |  | c)
[10 empty] | d) | 9 months | d)
|  |  | Jct. Salvacion - San Vicente - Cabay-angan |  |  |  | Road Maintenance | 3.45 | CBRMC | a) | 158775.23 | a) |  | e) | 158775.23 | a) |  | a) |  | c) |  | a) |  | Bidding on process
| 118 | [8 empty] | b) | Maligro | b) |  | f) | 158775.23 | b) |  | b) |  | d) |  | b)
[10 empty] | c) |  | c) |  | g) |  | c)
[10 empty] | d) | 6 months | d)
|  |  | Bacali - Casig-ang - Libertad |  |  |  | Road Maintenance |  | MBA | a) | 167836.14 | a) | 2020-01-02 | e) | 167836.14 | a) |  | a) | 10% | c) | 9% | a) | 3 | On-going / Time extension on process due to suspension of activity
| 123 | [8 empty] | b) | Gamad/Clar | b) | 2020-01-02 | f) | 167836.14 | b) |  | b) |  | d) | -1% | b) | 60
[10 empty] | c) | Admin | c) | 2020-12-31 | g) |  | c)
[10 empty] | d) | 1 year | d)
|  |  | Bacali - Casig-ang - Libertad |  |  |  | Road Maintenance |  | CBRMC | a) | 131608.37 | a) |  | e) | 131608.37 | a) |  | a) |  | c) |  | a) |  | Bidding on process
| 123 | [8 empty] | b) | Maligro | b) |  | f) | 131608.37 | b) |  | b) |  | d) |  | b)
[10 empty] | c) |  | c) |  | g) |  | c)
[10 empty] | d) | 6 months | d)
|  |  | Kinamayan - Moslog - Mahayag |  |  |  | Road Maintenance |  | MBA | a) | 114628.54 | a) | 2020-01-02 | e) | 114628.54 | a) |  | a) | 10% | c) | 8% | a) | 3 | On-going / Time extension on process due to suspension of activity
| 124 | [8 empty] | b) | Gamad/Clar | b) | 2020-01-02 | f) | 114628.54 | b) |  | b) |  | d) | -2% | b) | 66
[10 empty] | c) | Admin | c) | 2020-12-31 | g) |  | c)
[10 empty] | d) | 1 year | d)
|  |  | Kinamayan - Moslog - Mahayag |  |  |  | Road Maintenance |  | CBRMC | a) | 91159.92 | a) |  | e) | 91159.92 | a) |  | a) |  | c) |  | a)
| 124 | [8 empty] | b) | Maligro | b) |  | f) | 91159.92 | b) |  | b) |  | d) |  | b) |  | Bidding on process
[10 empty] | c) |  | c) |  | g) |  | c)
[10 empty] | d) | 6 months | d)
|  |  | Kinamayan - Lunga-og |  |  |  | Road Maintenance |  | MBA | a) | 100416.26 | a) | 2020-01-02 | e) | 100416.26 | a) |  | a) | 10% | c) | 8% | a) | 3 | On-going / Time extension on process due to suspension of activity
| 126 | [8 empty] | b) | Gamad/Clar | b) | 2020-01-02 | f) | 100416.26 | b) |  | b) |  | d) | -2% | b) | 66
[10 empty] | c) | Admin | c) | 2020-12-31 | g) |  | c)
[10 empty] | d) | 1 year | d)
|  |  | Kinamayan - Lunga-og |  |  |  | Road Maintenance |  | CBRMC | a) | 64596.78 | a) |  | e) | 64596.78 | a) |  | a) |  | c) |  | a) |  | Purchase Order # 2020030971 (Lunga-og Tribal Association)
| 126 | [8 empty] | b) | Maligro | b) |  | f) | 64596.78 | b) |  | b) |  | d) |  | b)
[10 empty] | c) |  | c) |  | g) |  | c)
[10 empty] | d) | 6 months | d)
|  |  | Prk. Apitong - Upper Balisong - Dalisay |  |  |  | Road Maintenance | 4.6 | MBA | a) | 150598.24 | a) | 2020-01-02 | e) | 150598.24 | a) |  | a) | 10% | c) | 9% | a) | 3 | On-going / Time extension on process due to suspension of activity
| 128 | [8 empty] | b) | Gamad/Clar | b) | 2020-01-02 | f) | 150598.24 | b) |  | b) |  | d) | -1% | b) | 60
[10 empty] | c) | Admin | c) | 2020-12-31 | g) |  | c)
[10 empty] | d) | 1 year | d)
|  |  | Prk. Apitong - Upper Balisong - Dalisay |  |  |  | Road Maintenance | 4.6 | CBRMC | a) | 142475.11 | a) |  | e) | 142475.11 | a) |  | a) |  | c) |  | a) |  | Purchase Order # 2020030946 (Lunga-og Tribal Association)
| 128 | [8 empty] | b) | Maligro | b) |  | f) | 142475.11 | b) |  | b) |  | d) |  | b)
[10 empty] | c) |  | c) |  | g) |  | c)
[10 empty] | d) | 6 months | d)
|  |  | Los Amigos 1 - Esperanza - Los Amigos 2 |  |  |  | Road Maintenance | 3.59 | MBA | a) | 97116.27 | a) | 2020-01-02 | e) | 97116.27 | a) |  | a) | 10% | c) | 12% | a) | 4 | On-going / Time extension on process due to suspension of activity
| 130 | [8 empty] | b) | Gamad/Clar | b) | 2020-01-02 | f) | 97116.27 | b) |  | b) |  | d) | 2% | b) | 88
[10 empty] | c) | Admin | c) | 2020-12-31 | g) |  | c)
[10 empty] | d) | 1 year | d)
|  |  | Los Amigos 1 - Esperanza - Los Amigos 2 |  |  |  | Road Maintenance | 3.59 | CBRMC | a) | 131608.37 | a) |  | e) | 131608.37 | a) |  | a) |  | c) |  | a) |  | Abstract # 0320201348
| 130 | [8 empty] | b) | Maligro | b) |  | f) | 131608.37 | b) |  | b) |  | d) |  | b)
[10 empty] | c) |  | c) |  | g) |  | c)
[10 empty] | d) | 6 months | d)
|  |  | Mugas - Lanatad |  |  |  | Road Maintenance |  | MBA | a) | 65482.21 | a) | 2020-01-02 | e) | 65482.21 | a) |  | a) | 2% | c) | 3% | a) | 3 | On-going / Time extension on process due to suspension of activity
| 131 | [8 empty] | b) | Gamad/Clar | b) | 2020-01-02 | f) | 65482.21 | b) |  | b) |  | d) | 1% | b) | 12
[10 empty] | c) | Admin | c) | 2020-12-31 | g) |  | c)
[10 empty] | d) |  | d)
|  |  | Mugas - Lanatad |  |  |  | Road Maintenance |  | CBRMC | a) | 31996.54 | a) |  | e) | 31996.54 | a) |  | a) |  | c) |  | a) |  | Purchase Order # 2020030961 (Katipunan Pantaron Irrigator's Association)
| 131 | [8 empty] | b) | Maligro | b) |  | f) | 31996.54 | b) |  | b) |  | d) |  | b)
[10 empty] | c) |  | c) |  | g) |  | c)
[10 empty] | d) | 6 months | d)
|  |  | Mugas - Lunga-og |  |  |  | Road Maintenance | 2.68 | MBA | a) | 96490.97 | a) | 2020-01-02 | e) | 96490.97 | a) |  | a) | 5% | c) | 3% | a) | 3 | On-going / Time extension on process due to suspension of activity
| 132 | [8 empty] | b) | Gamad/Clar | b) | 2020-01-02 | f) | 96490.97 | b) |  | b) |  | d) | -2% | b) | 20
[10 empty] | c) | Admin | c) | 2020-12-31 | g) |  | c)
[10 empty] | d) |  | d)
|  |  | Mugas - Lunga-og |  |  |  | Road Maintenance | 2.68 | CBRMC | a) | 74256.11 | a) |  | e) | 74256.11 | a) |  | a) |  | c) |  | a) |  | Purchase Order # 2020030947 (Lunga-og Tribal Association)
| 132 | [8 empty] | b) | Maligro | b) |  | f) | 74256.11 | b) |  | b) |  | d) |  | b)
[10 empty] | c) |  | c) |  | g) |  | c)
[10 empty] | d) | 6 months | d)
|  |  | New Katipunan - Pantaron |  |  |  | Road Maintenance |  | MBA | a) | 71748.41 | a) | 2020-01-02 | e) | 71748.41 | a) |  | a) | 6% | c) | 3% | a) | 2 | On-going / Time extension on process due to suspension of activity
| 134 | [8 empty] | b) | Gamad/Clar | b) | 2020-01-02 | f) | 71748.41 | b) |  | b) |  | d) | -3% | b) | 20
[10 empty] | c) | Admin | c) | 2020-12-31 | g) |  | c)
[10 empty] | d) |  | d)
|  |  | New Katipunan - Pantaron |  |  |  | Road Maintenance |  | CBRMC | a) | 53126.32 | a) |  | e) | 53126.32 | a) |  | a) |  | c) |  | a) |  | Purchase Order # 2020030964 (Katipunan Pantaron Irrigator's Association)
| 134 | [8 empty] | b) | Maligro | b) |  | f) | 53126.32 | b) |  | b) |  | d) |  | b)
[10 empty] | c) |  | c) |  | g) |  | c)
[10 empty] | d) | 6 months | d)
|  |  | Sto. Tomas - Bdry. Mamacao |  |  |  | Road Maintenance | 4.9 | MBA | a) | 195671.17 | a) | 2020-01-02 | e) | 195671.17 | a) |  | a) | 8% | c) | 6% | a) | 3 | On-going / Time extension on process due to suspension of activity
| 135 | [8 empty] | b) | Gamad/Clar | b) | 2020-01-02 | f) | 195671.17 | b) |  | b) |  | d) | -2% | b) | 33
[10 empty] | c) | Admin | c) | 2020-12-31 | g) |  | c)
[10 empty] | d) |  | d)
|  |  | Sto. Tomas - Bdry. Mamacao |  |  |  | Road Maintenance | 4.9 | CBRMC | a) | 116515.66 | a) |  | e) | 116515.66 | a) |  | a) |  | c) |  | a) |  | Abstract # 0320301351
| 135 | [8 empty] | b) | Maligro | b) |  | f) | 116515.66 | b) |  | b) |  | d) |  | b)
[10 empty] | c) |  | c) |  | g) |  | c)
[10 empty] | d) | 6 months | d)
|  |  | Fd. Rd. 3 - San Jose |  |  |  | Road Maintenance | 4.55 | MBA | a) | 176994.35 | a) | 2020-01-02 | e) | 176994.35 | a) |  | a) | 6% | c) | 2% | a) | 2 | On-going / Time extension on process due to suspension of activity
| 136 | [8 empty] | b) | Gamad/Clar | b) | 2020-01-02 | f) | 176994.35 | b) |  | b) |  | d) | -4% | b) | 10
[10 empty] | c) | Admin | c) | 2020-12-31 | g) |  | c)
[10 empty] | d) |  | d)
|  |  | Fd. Rd. 3 - San Jose |  |  |  | Road Maintenance | 4.55 | CBRMC | a) | 112893.42 | a) |  | e) | 112893.42 | a) |  | a) |  | c) |  | a) |  | Purchase Order # 2020030974 (Brgy. San Jose Upland Farmer's Assocaition)
| 136 | [8 empty] | b) | Maligro | b) |  | f) | 112893.42 | b) |  | b) |  | d) |  | b)
[10 empty] | c) |  | c) |  | g) |  | c)
[10 empty] | d) | 6 months | d)
|  |  | Nafco - Bobongon |  |  |  | Road Maintenance |  | MBA | a) | 89179.68 | a) | 2020-01-02 | e) | 89179.68 | a) |  | a) | 8% | c) | 7% | a) | 3 | On-going / Time extension on process due to suspension of activity
| 139 | [8 empty] | b) | Gamad/Clar | b) | 2020-01-02 | f) | 89179.68 | b) |  | b) |  | d) | -15% | b) | 56
[10 empty] | c) | Admin | c) | 2020-12-31 | g) |  | c)
[10 empty] | d) |  | d)
|  |  | Nafco - Bobongon |  |  |  | Road Maintenance |  | CBRMC | a) | 80293.17 | a) |  | e) | 80293.17 | a) |  | a) |  | c) |  | a) |  | Purchase Order # 2020030968 (Bobongon Rural Waterworks & Sanitation Association, Inc.)
| 139 | [8 empty] | b) | Maligro | b) |  | f) | 80293.17 | b) |  | b) |  | d) |  | b)
[10 empty] | c) |  | c) |  | g) |  | c)
[10 empty] | d) | 6 months | d)
|  |  | Bdry. Tagum - Crossing Kinamayan Sto. Tomas |  |  |  | Road Maintenance |  | MBA | a) | 790874.1 | a) | 2020-01-02 | e) | 790874.1 | a) |  | a) | 8% | c) | 10% | a) | 3 | On-going / Time extension on process due to suspension of activity
| 146 | [8 empty] | b) | Gamad/Clar | b) | 2020-01-02 | f) | 790874.1 | b) |  | b) |  | d) | 2% | b) | 66
[10 empty] | c) | Admin | c) | 2020-12-31 | g) |  | c)
[10 empty] | d) |  | d)
|  |  | Bdry. Tagum - Crossing Kinamayan Sto. Tomas |  |  |  | Road Maintenance |  | CBRMC | a) | 429840.12 | a) |  | e) | 429840.12 | a) |  | a) |  | c) |  | a) |  | Abstract 0320201447
| 146 | [8 empty] | b) | Maligro | b) |  | f) | 429840.12 | b) |  | b) |  | d) |  | b)
[10 empty] | c) |  | c) |  | g) |  | c)
[10 empty] | d) | 9 months | d)
|  |  | San Jose - Sitio Mahayahay, Magwawa |  |  |  | Road Maintenance | 0.84 | MBA | a) | 22943.54 | a) | 2020-01-02 | e) | 22943.54 | a) |  | a) | 15% | c) | 15% | a) | 3 | Suspended effective April 5, 2020 due to issued Executive Order No. 31, series of 2020 the province of Davao del Norte in response to the State of Public Health Emergency and State of National Calamity (COVID19 Pandemic).
| 151 | [8 empty] | b) | Gamad/Clar | b) | 2020-01-02 | f) | 22943.54 | b) |  | b) |  | d) |  | b) | 60
[10 empty] | c) | Admin | c) | 2020-12-31 | g) |  | c)
[10 empty] | d) | - | d)
|  |  | San Jose - Sitio Mahayahay, Magwawa |  |  |  | Road Maintenance | 0.84 | CBRMC | a) | 30789.12 | a) |  | e) | 30789.12 | a) |  | a) |  | c) |  | a) |  | Purchase Order # 2020030972 (Brgy. San Jose Upland Farmer's Assocaition)
| 151 | [8 empty] | b) | Maligro | b) |  | f) | 30789.12 | b) |  | b) |  | d) |  | b) | 10
[10 empty] | c) |  | c) |  | g) |  | c)
[10 empty] | d) | 9 months | d)
|  | B. | 20% Development Fund CY 2020
PEACE AND ORDER PROGRAM
|  | 1. Rural Electrification Project |  |  |  |  | Rural Electrification to cater the needs of brgys. | - | Admin/Contract | a) | 5000000 | [12 empty] | See projects listed below
[10 empty] | b) | -
[10 empty] | c) | -
[10 empty] | d) | -
|  | ■ | Completion of Single Phase Line at Purok 6 and Purok 7, Brgy. Cogon, Babak Distirct, IGACOS |  |  |  | Rural Electrification to cater the needs of brgys. | - | - | a) | 1000000 | a) | - | e) | - | a) | 1000000 | a) | - | c) | - | a) | - | For preparation of POW and Plans
|  | 1.1 | [7 empty] | b) | - | b) | - | f) | - | b) | 1000000 | b) | - | d) | - | b) | -
[10 empty] | c) | - | c) | - | g) | - | c) | -
[10 empty] | d) | - | d) | -
|  | ■ | Completion of Single Phase Line at Purok Perlas, Brgy. Sta. Cruz, Talicud (Day Care Center), IGACOS |  |  |  | Rural Electrification to cater the needs of brgys. | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For preparation of POW and Plans
|  | 1.2 | [7 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | -
[10 empty] | c) | - | c) | - | g) | - | c) | -
[10 empty] | d) | - | d) | -
| Road ID | 2. Rehabilitation of Provincial Roads & Bridges |  |  |  |  | Road Maintenance | KM | MBA | a) | 47357000 | a) | 2020-01-02 | e) | - | a) | 47357000 | a) | - | c) | - | a) | 46 | See list of Provincial Roads
[8 empty] | 54 |  | b) | Matuguinas | b) | 2020-01-02 | f) | - | b) | 47357000 | b) | - | d) | - | b) | 920
| 11DAN | [8 empty] | c) | PEO | c) | 2020-12-31 | g) | - | c) | -
[12 empty] | d) | -
[10 empty] | d) | 261 days | d) | -
PEACE AND ORDER PROGRAM
|  |  | Fr. Rd. 3 - San Jose |  |  |  | Road Rehabilitaion | KM | Admin | a) | 8000000 | a) | - | e) | - | a) | 8000000 | a) | - | c) | - | a) | - | Plan On-going
| 008 | [8 empty] | b) |  | b) | - | f) | - | b) | 8000000 | b) | - | d) | - | b) | -
[10 empty] | c) | PEO | c) | - | g) | - | c) | -
[10 empty] | d) | - | d) | -
INFRASTRUCTURE DEVELOPMENT PROGRAMS
|  |  | Lower Asuncion - Upper Asuncion |  |  |  | Road Rehabilitaion | KM | Admin | a) | 1302000 | a) |  | e) | - | a) | 1302000 | a) | - | c) | - | a) | - | Plan On-going
| 007 | [8 empty] | b) |  | b) |  | f) | - | b) | 1302000 | b) | - | d) | - | b) | -
[10 empty] | c) | PEO | c) | - | g) | - | c) | -
[10 empty] | d) | - | d) | -
|  |  | Jct. Highway - Carmen - Mangalcal - Tubod |  |  |  | Road Rehabilitaion | KM | Admin | a) | 1323000 | a) | - | e) | - | a) | 1323000 | a) | - | c) | - | a) | - | Plan On-going
| 030 | [8 empty] | b) |  | b) | - | f) | - | b) | 1323000 | b) | - | d) | - | b) | -
[10 empty] | c) | PEO | c) | - | g) | - | c) | -
[10 empty] | d) | - | d) | -
|  |  | Tuganay - Taba |  |  |  | Road Rehabilitaion | KM | Admin | a) | 1431000 | a) |  | e) | - | a) | 1431000 | a) | - | c) | - | a) | - | Plan On-going
| 031 | [8 empty] | b) |  | b) |  | f) | - | b) | 1431000 | b) | - | d) | - | b) | -
[10 empty] | c) | PEO | c) | - | g) | - | c) | -
[10 empty] | d) | - | d) | -
|  |  | Jct. Highway - Ising - Magsaysay |  |  |  | Road Rehabilitaion | KM | Admin | a) | 6000000 | a) | - | e) | - | a) | 6000000 | a) | - | c) | - | a) | - | Plan On-going
| 069 | [8 empty] | b) |  | b) | - | f) | - | b) | 6000000 | b) | - | d) | - | b) | -
[10 empty] | c) | PEO | c) | - | g) | - | c) | -
[10 empty] | d) | - | d) | -
|  |  | Jct. Highway - Guadalupe - Bdry. Tagum |  |  |  | Road Rehabilitaion | KM | Admin | a) | 910000 | a) | - | e) | - | a) | 910000 | a) | - | c) | - | a) | -
| 069 | [8 empty] | b) |  | b) | - | f) | - | b) | 910000 | b) | - | d) | - | b) | -
[10 empty] | c) | PEO | c) | - | g) | - | c) | -
[10 empty] | d) | - | d) | -
|  |  | Sitio Malaga - Tibulao |  |  |  | Road Rehabilitaion | KM | Admin | a) | 350000 | a) | - | e) | - | a) | 350000 | a) | - | c) | - | a) | - | Plan On-going
| 069 | [8 empty] | b) |  | b) | - | f) | - | b) | 350000 | b) | - | d) | - | b) | -
[10 empty] | c) | PEO | c) | - | g) | - | c) | -
[10 empty] | d) | - | d) | -
|  |  | Prk. 5 RJS - Prk. 6 New Casay |  |  |  | Road Rehabilitaion | KM | Admin | a) | 350000 | a) | - | e) | - | a) | 350000 | a) | - | c) | - | a) | - | Plan On-going
| 069 | [8 empty] | b) |  | b) | - | f) | - | b) | 350000 | b) | - | d) | - | b) | -
[10 empty] | c) | PEO | c) | - | g) | - | c) | -
[10 empty] | d) | - | d) | -
|  |  | Dujali - Pawas - San Vicente |  |  |  | Road Rehabilitaion | KM | Admin | a) | 350000 | a) | - | e) | - | a) | 350000 | a) | - | c) | - | a) | - | Plan On-going
| 069 | [8 empty] | b) |  | b) | - | f) | - | b) | 350000 | b) | - | d) | - | b) | -
[10 empty] | c) | PEO | c) | - | g) | - | c) | -
[10 empty] | d) | - | d) | -
|  |  | Los Amigos 1 - Esperanza - Los Amigos 2 |  |  |  | Road Rehabilitaion | KM | Admin | a) | 350000 | a) | - | e) | - | a) | 350000 | a) | - | c) | - | a) | - | Plan On-going
| 069 | [8 empty] | b) |  | b) | - | f) | - | b) | 350000 | b) | - | d) | - | b) | -
[10 empty] | c) | PEO | c) | - | g) | - | c) | -
[10 empty] | d) | - | d) | -
|  |  | San Miguel - Crossing Kinamayan |  |  |  | Road Rehabilitaion | KM | Admin | a) | 19200000 | a) | - | e) | - | a) | 19200000 | a) | - | c) | - | a) | - | Plan On-going
| 069 | [8 empty] | b) |  | b) | - | f) | - | b) | 19200000 | b) | - | d) | - | b) | -
[10 empty] | c) | PEO | c) | - | g) | - | c) | -
[10 empty] | d) | - | d) | -
|  |  | Fd. Rd. 2 - Sto. Tomas - Magwawa |  |  |  | Road Rehabilitaion | KM | Admin | a) | 350000 | a) | - | e) | - | a) | 350000 | a) | - | c) | - | a) | - | Plan On-going
| 069 | [8 empty] | b) |  | b) | - | f) | - | b) | 350000 | b) | - | d) | - | b) | -
[10 empty] | c) | PEO | c) | - | g) | - | c) | -
[10 empty] | d) | - | d) | -
|  |  | Menzi - Balagunan - Tulalian |  |  |  | Road Rehabilitaion | KM | Admin | a) | 3720500 | a) | - | e) | - | a) | 3720500 | a) | - | c) | - | a) | - | Plan On-going
| 069 | [8 empty] | b) |  | b) | - | f) | - | b) | 3720500 | b) | - | d) | - | b) | -
[10 empty] | c) | PEO | c) | - | g) | - | c) | -
[10 empty] | d) | - | d) | -
|  |  | Jct,. Bdry. Tagum- Talomo |  |  |  | Road Rehabilitaion | KM | Admin | a) | 3720500 | a) | - | e) | - | a) | 3720500 | a) | - | c) | - | a) | - | Plan On-going
| 069 | [8 empty] | b) |  | b) | - | f) | - | b) | 3720500 | b) | - | d) | - | b) | -
[10 empty] | c) | PEO | c) | - | g) | - | c) | -
[10 empty] | d) | - | d) | -
|  | 3. Various Local Roads & Drainage Dev't. Project |  |  |  |  | Rehabilitaion |  | - | a) | 12590910 | a) | [11 empty] | See projects listed below
[10 empty] | b) |  | b)
[10 empty] | c) | PEO | c) | -
[10 empty] | d) | - | d)
|  | ■ | Rehab. Of Various Local Roads @ Island Garden City of Samal |  |  |  | Rehabilitaion |  | - | a) | 2518182 | a) | - | e) | - | a) | 2518182 | a) | - | c) | - | a) | - | Plan On-going
|  | 3.1 | [7 empty] | b) | - | b) | - | f) | - | b) | 2518182 | b) | - | d) | - | b) | -
[10 empty] | c) | - | c) | - | g) | - | c) | -
[10 empty] | d) | - | d) | -
|  | ■ | Rehab. Of Various Local Roads @ Panabo City |  |  |  | Rehabilitaion |  | - | a) | 2518182 | a) | - | e) | - | a) | 2518182 | a) | - | c) | - | a) | - | Abstract # 0420201633 - Billboard; Abstract 0520201661 - hardware
|  | 3.2 | [7 empty] | b) | - | b) | - | f) | - | b) | 2518182 | b) | - | d) | - | b) | -
[10 empty] | c) | - | c) | - | g) | - | c) | -
[10 empty] | d) | - | d) | -
|  | ■ | Rehab. Of Various Local Roads @ B.E Dujali |  |  |  | Rehabilitaion |  | - | a) | 2518182 | a) | - | e) | - | a) | 2518182 | a) | - | c) | - | a) | - | Purchase Request # 20053256 - Hardware; PR # 20053255 - Billboard
|  | 3.3 | [7 empty] | b) | - | b) | - | f) | - | b) | 2518182 | b) | - | d) | - | b) | -
[10 empty] | c) | - | c) | - | g) | - | c) | -
[10 empty] | d) | - | d) | -
|  | ■ | Rehab. Of Various Local Roads @ Carmen |  |  |  | Rehabilitaion |  | - | a) | 2518182 | a) | - | e) | - | a) | 2518182 | a) | - | c) | - | a) | - | Abstract # 0420201633 - Billboard; Abstract 0520201661 - hardware
|  | 3.4 | [7 empty] | b) | - | b) | - | f) | - | b) | 2518182 | b) | - | d) | - | b) | -
[10 empty] | c) | - | c) | - | g) | - | c) | -
[10 empty] | d) | - | d) | -
|  | ■ | Rehab. Of Various Local Roads @ Sto. Tomas |  |  |  | Rehabilitaion |  | - | a) | 2518182 | a) | - | e) | - | a) | 2518182 | a) | - | c) | - | a) | - | Plan On-going
|  | 3.5 | [7 empty] | b) | - | b) | - | f) | - | b) | 2518182 | b) | - | d) | - | b) | -
[10 empty] | c) | - | c) | - | g) | - | c) | -
[10 empty] | d) | - | d) | -
|  | 4. Various Government Buildings and Facilities Development Project |  |  |  |  | Various Bldgs./Facilities | km. | - | a) | 9790000 | a) | [11 empty] | See projects listed below
[10 empty] | b) |  | b)
[10 empty] | c) | PEO | c) | -
[10 empty] | d) | - | d)
|  | ■ | Construction of Commercial Building at Kinawitnon, IGACOS, Babak |  |  |  | Various Bldgs./Facilities |  | - | a) | 2000000 | a) | - | e) | - | a) | 2000000 | a) | - | c) | - | a) | - | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
|  | 5.2 | [7 empty] | b) | - | b) | - | f) | - | b) | 2000000 | b) | - | d) | - | b) | -
[10 empty] | c) | - | c) | - | g) | - | c) | -
[10 empty] | d) | - | d) | -
|  | ■ | Improvement of Provincial Engineer's Office 2nd District Office Phase 2, Carmen |  |  |  | Various Bldgs./Facilities |  | - | a) | 1590000 | a) | - | e) | - | a) | 1590000 | a) | - | c) | - | a) | - | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
|  | 5.3 | [7 empty] | b) | - | b) | - | f) | - | b) | 1590000 | b) | - | d) | - | b) | -
[10 empty] | c) | - | c) | - | g) | - | c) | -
[10 empty] | d) | - | d) | -
|  | ■ | Construction of DDN hospital Carmen Zone Annex Building Phase 3, Carmen |  |  |  | Various Bldgs./Facilities |  | - | a) | 800000 | a) | - | e) | - | a) | 800000 | a) | - | c) | - | a) | - | Purchase Request # 20021473
|  | 5.4 | [7 empty] | b) | - | b) | - | f) | - | b) | 800000 | b) | - | d) | - | b) | -
[10 empty] | c) | - | c) | - | g) | - | c) | -
[10 empty] | d) | - | d) | -
|  | ■ | Construction of Municipal Triball Hall, B.E. Dujali |  |  |  | Various Bldgs./Facilities |  | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
|  | 5.6 | [7 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | -
[10 empty] | c) | - | c) | - | g) | - | c) | -
[10 empty] | d) | - | d) | -
|  | ■ | Construction of Municipal Triball Hall, Sto. Tomas |  |  |  | Various Bldgs./Facilities |  | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
|  | 5.7 | [7 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | -
[10 empty] | c) | - | c) | - | g) | - | c) | -
[10 empty] | d) | - | d) | -
|  | ■ | Construction of Fence at Tulalian National High School, Tulalian, Sto. Tomas |  |  |  | Various Bldgs./Facilities |  | - | a) | 1500000 | a) | - | e) | - | a) | 1500000 | a) | - | c) | - | a) | - | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
|  | 5.8 | [7 empty] | b) | - | b) | - | f) | - | b) | 1500000 | b) | - | d) | - | b) | -
|  | . | [7 empty] | c) | - | c) | - | g) | - | c) | -
[10 empty] | d) | - | d) | -
|  | ■ | Construction of Two(2) Classroom at Tibulao Elem. School, Tibulao, Carmen |  |  |  | Various Bldgs./Facilities |  | - | a) | 2900000 | a) | - | e) | - | a) | 2900000 | a) | - | c) | - | a) | - | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
|  | 5.9 | [7 empty] | b) | - | b) | - | f) | - | b) | 2900000 | b) | - | d) | - | b) | -
[10 empty] | c) | - | c) | - | g) | - | c) | -
[10 empty] | d) | - | d) | -
| C. | 5% CALAMITY FUND CY 2020
DISASTER PREVENTION AND MITIGATION PROGRAM
I. FLOOD CONTROL AND SLOPE PROTECTION PROJECT
|  | Desiltation/Excavation of Rivers & Creeks |  |  |  |  | Desiltation/Excavation |  | - | a) | 6630206 | [12 empty] | See projects listed below
| 1 | [8 empty] | b) | Matuguinas
[10 empty] | c) | PEO
[10 empty] | d) | -
|  |  | Improvement and Desiltation of Camoning Creek |  |  |  | Desiltation/Excavation |  | - | a) | 2500000 | a) | - | e) | - | a) | 2500000 | a) | - | c) | - | a) | - | Abstract # 0520201658
|  | 1.1 | [7 empty] | b) | - | b) | - | f) | - | b) | 2500000 | b) | - | d) | - | b) | -
[10 empty] | c) | PEO | c) | - | g) | - | c) | -
[10 empty] | d) | - | d) | -
|  |  | Improvement and Desiltation of Ising Creek |  |  |  | Desiltation/Excavation |  | - | a) | 2000000 | a) | - | e) | - | a) | 2000000 | a) | - | c) | - | a) | - | Abstract # 0420201637; 0520201662
|  | 1.2 | [7 empty] | b) | - | b) | - | f) | - | b) | 2000000 | b) | - | d) | - | b) | -
[10 empty] | c) | PEO | c) | - | g) | - | c) | -
[10 empty] | d) | - | d) | -
|  |  | Desiltation of Buhang Creek, Anibongan, Carmen |  |  |  | Desiltation/Excavation |  | - | a) | 2130206 | a) | - | e) | - | a) | 2130206 | a) | - | c) | - | a) | - | Abstract # 0520201657; 0420201626
|  | 1.3 | [7 empty] | b) | - | b) | - | f) | - | b) | 2130206 | b) | - | d) | - | b) | -
[10 empty] | c) | - | c) | - | g) | - | c) | -
[10 empty] | d) | - | d) | -
| 2 | Revetment of Dike and Slope Protection
|  |  | Rehab./Impv't. of Sto. Niño-Daligdigon-Paiton |  |  |  | Rehab./Impv't. | km. | - | a) | 1000000 | a) |  | e) | - | a) | 1000000 | a) | - | c) | - | a) | - | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
|  | 2.1 | [7 empty] | b) |  | b) |  | f) | - | b) | 1000000 | b) | - | d) | - | b) | -
[10 empty] | c) | PEO | c) | - | g) | - | c) | -
[10 empty] | d) | - | d) | -
|  |  | Rehab./Impv't. of San Miguel - Moslog - Kinamayan, Sto. Tomas |  |  |  | Rehab./Impv't. |  | - | a) | 1000000 | a) | - | e) | - | a) | 1000000 | a) | - | c) | - | a) | - | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
|  | 2.2 | [7 empty] | b) | - | b) | - | f) | - | b) | 1000000 | b) | - | d) | - | b) | -
[10 empty] | c) | PEO | c) | - | g) | - | c) | -
[10 empty] | d) | - | d) | -
|  | Improvement of Roads, Drainage and Canal |  |  |  |  | Rehab./Impv't. |  | - | a) | 1000000 | [12 empty] | See projects listed below
| 3 | [8 empty] | b) | Matuguinas
[10 empty] | c) | PEO
[10 empty] | d) | -
|  |  | Improvement of Mangalcal to Diamond Creek Farm to Market Road Opening |  |  |  | Rehab./Impv't. |  | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
|  | 3.1 | [7 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | -
[10 empty] | c) | - | c) | - | g) | - | c) | -
[10 empty] | d) | - | d) | -
|  |  | Improvement of Mabaus - Salvacion Provincial Road Continuing Road Opening |  |  |  | Rehab./Impv't. |  | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Plan On-going
|  | 3.2 | [7 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | -
[10 empty] | c) | - | c) | - | g) | - | c) | -
[10 empty] | d) | - | d) | -
| 4 | Improvement of Bridges and Cross Drainage
|  |  | Single Barrel Box Culvert at Mangalcal-Diamond Creek, Brgy. Mangalcal, Carmen |  |  |  | Rehab./Impv't. |  | - | a) | 2000000 | a) | - | e) | - | a) | 2000000 | a) | - | c) | - | a) | - | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
|  | 4.1 | [7 empty] | b) | - | b) | - | f) | - | b) | 2000000 | b) | - | d) | - | b) | -
[10 empty] | c) | - | c) | - | g) | - | c) | -
[10 empty] | d) | - | d) | -
| D. | SPECIAL EDUCATION FUND - ANNUAL BUDGET CY 2020
|  | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. | [21 empty] | See projects listed below
| 1 | [5 empty] | Const./Impv't./Compl. |  | - | a) | 500000
[10 empty] | b) | -
[10 empty] | c) | -
[10 empty] | d) | -
|  |  | Const. of 1 Classroom @ Mangga ES, Magwawa, Sto. Tomas |  |  |  | Bldg. | sq.m | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For preparation of POW and Plans
|  | 1.7 | [7 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | -
[10 empty] | c) | - | c) | - | g) | - | c) | -
[10 empty] | d) | - | d) | -
| E. | SOCIAL WELFARE AND DEVELOPMENT
|  | 1. CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) |  |  |  |  | Bldg. | sq.m | Admin/Contract | a) | 6000000 | [12 empty] | See list of projects
[10 empty] | b) | -
[10 empty] | c) | -
[10 empty] | d) | -
|  |  | Const. of Day Care Center, JP Laurel, Panabo City |  |  |  | Bldg. | sq.m | - | a) | 1000000 | a) | - | e) | - | a) | 1000000 | a) | - | c) | - | a) | - | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
|  | 2.2 | [7 empty] | b) | - | b) | - | f) | - | b) | 1000000 | b) | - | d) | - | b) | -
[10 empty] | c) | - | c) | - | g) | - | c) | -
[10 empty] | d) | - | d) | -
|  |  | Const. of Day Care Center, Dujali, B.E. Dujali |  |  |  | Bldg. | sq.m | - | a) | 1000000 | a) | - | e) | - | a) | 1000000 | a) | - | c) | - | a) | - | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
|  | 2.3 | [7 empty] | b) | - | b) | - | f) | - | b) | 1000000 | b) | - | d) | - | b) | -
[10 empty] | c) | - | c) | - | g) | - | c) | -
[10 empty] | d) | - | d) | -
|  |  | Const. of Day Care Center, Tibal-og, Sto Tomas |  |  |  | Bldg. | sq.m | - | a) | 1000000 | a) | - | e) | - | a) | 1000000 | a) | - | c) | - | a) | - | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
|  | 2.4 | [7 empty] | b) | - | b) | - | f) | - | b) | 1000000 | b) | - | d) | - | b) | -
[10 empty] | c) | - | c) | - | g) | - | c) | -
[10 empty] | d) | - | d) | -
|  |  | Compl./Rep. Day Care Center, Cabay-angan, B.E. Dujali |  |  |  | Bldg. | sq.m | - | a) | 300000 | a) | - | e) | - | a) | 300000 | a) | - | c) | - | a) | - | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
|  | 2.5 | [7 empty] | b) | - | b) | - | f) | - | b) | 300000 | b) | - | d) | - | b) | -
[10 empty] | c) | - | c) | - | g) | - | c) | -
[10 empty] | d) | - | d) | -
|  |  | Compl./Rep. Day Care Center, Tanglaw, B.E. Dujali |  |  |  | Bldg. | sq.m | - | a) | 300000 | a) | - | e) | - | a) | 300000 | a) | - | c) | - | a) | - | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
|  | 2.6 | [7 empty] | b) | - | b) | - | f) | - | b) | 300000 | b) | - | d) | - | b) | -
[10 empty] | c) | - | c) | - | g) | - | c) | -
[10 empty] | d) | - | d) | -
|  |  | Compl./Rep. Day Care Center, Salvacion, Carmen |  |  |  | Bldg. | sq.m | - | a) | 300000 | a) | - | e) | - | a) | 300000 | a) | - | c) | - | a) | - | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
|  | 2.7 | [7 empty] | b) | - | b) | - | f) | - | b) | 300000 | b) | - | d) | - | b) | -
[10 empty] | c) | - | c) | - | g) | - | c) | -
[10 empty] | d) | - | d) | -
|  |  | Compl./Rep. Day Care Center, San Agustin, IGCS |  |  |  | Bldg. | sq.m | - | a) | 300000 | a) | - | e) | - | a) | 300000 | a) | - | c) | - | a) | - | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
|  | 2.8 | [7 empty] | b) | - | b) | - | f) | - | b) | 300000 | b) | - | d) | - | b) | -
[10 empty] | c) | - | c) | - | g) | - | c) | -
[10 empty] | d) | - | d) | -
|  |  | Compl./Rep. Day Care Center, Toril, IGCS |  |  |  | Bldg. | sq.m | - | a) | 300000 | a) | - | e) | - | a) | 300000 | a) | - | c) | - | a) | - | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
|  | 2.9 | [7 empty] | b) | - | b) | - | f) | - | b) | 300000 | b) | - | d) | - | b) | -
[10 empty] | c) | - | c) | - | g) | - | c) | -
[10 empty] | d) | - | d) | -
|  |  | Compl./Rep. Day Care Center, Tibal-og, Sto. Tomas |  |  |  | Bldg. | sq.m | - | a) | 600000 | a) | - | e) | - | a) | 600000 | a) | - | c) | - | a) | - | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
|  | 3 | [7 empty] | b) | - | b) | - | f) | - | b) | 600000 | b) | - | d) | - | b) | -
[10 empty] | c) | - | c) | - | g) | - | c) | -
[10 empty] | d) | - | d) | -
|  |  | Compl./Rep. Day Care Center, Talomo, Sto. Tomas |  |  |  | Bldg. | sq.m | - | a) | 300000 | a) | - | e) | - | a) | 300000 | a) | - | c) | - | a) | - | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
|  | 3.1 | [7 empty] | b) | - | b) | - | f) | - | b) | 300000 | b) | - | d) | - | b) | -
[10 empty] | c) | - | c) | - | g) | - | c) | -
[10 empty] | d) | - | d) | -
|  |  | Compl./Rep. Day Care Center, Kinamayan, Sto. Tomas |  |  |  | Bldg. | sq.m | - | a) | 300000 | a) | - | e) | - | a) | 300000 | a) | - | c) | - | a) | - | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
|  | 3.2 | [7 empty] | b) | - | b) | - | f) | - | b) | 300000 | b) | - | d) | - | b) | -
[10 empty] | c) | - | c) | - | g) | - | c) | -
[10 empty] | d) | - | d) | -
|  |  | Compl./Rep. Day Care Center, La Libertad, Sto. Tomas |  |  |  | Bldg. | sq.m | - | a) | 300000 | a) | - | e) | - | a) | 300000 | a) | - | c) | - | a) | - | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
|  | 3.3 | [7 empty] | b) | - | b) | - | f) | - | b) | 300000 | b) | - | d) | - | b) | -
[10 empty] | c) | - | c) | - | g) | - | c) | -
[10 empty] | d) | - | d) | -
[5 empty] | GF- GENERAL FUND | [12 empty] | TF - TRUST FUND (NATIONAL FUNDED PROJECT)
[5 empty] | 20% DF - 20% DEV'T. FUND | [12 empty] | a) SLRF - Special Local Road Fund
[5 empty] | 5% CF - 5% CALAMITY FUND | [12 empty] | b) KALSADA - Konkreto at Ayos na Lansangan Tungo sa Pangkalahatang Kaunlaran
[5 empty] | CO - CAPITAL OUTLAY | [12 empty] | c) PRDP - Philippine Rural Development Projects
[5 empty] | CONG. FUND - CONGRESSIONAL FUND | [12 empty] | d) SELAP - Support to Emergency and Livelihood Assistance Project
[5 empty] | SEF - SPECIAL EDUCATIONAL UFND | [12 empty] | e) PAMANA - Payapa at Masaganang Pamayanan
f) CBRMC - Community Based Road Maintenance Contracting
g) MBC - Maintenance by Contract
h) PCF-Performance Challenge Fund-DILG
i) FMRDP - Farm to Market Road
j.) CMGP - Conditional Grant to Provinces
k.) OPAPP - Office of the President Adviser on the Peace Process
l.) LGSF-AM - Local Government Support Fund Assistance to Municipalities
|  |  | Prepared by: |  |  |  |  | Checked | [5 empty] | Noted | [6 empty] | Recommending Approval
|  |  | RETCHIE A. DE LOS REYES |  |  |  |  | ELISA A. BARCENA | [5 empty] | JIVELLYN B. CO | [6 empty] | GLENN A. OLANDRIA
|  |  | Engineer II |  |  |  |  | Engineer IV- Engineering Dist 1, Area Engineer | [5 empty] | Asst. PG-Department Head | [6 empty] | Provincial Engineer
Formulas:
Date A lot. Rel. = +[Date A lot. Rel., row above]+200
Date A lot. Rel. = +[Date A lot. Rel., row above]+[Alzam, row below]

## Central (hidden)
PROVINCE OF DAVAO DEL NORTE
ACCOMPLISHMENT REPORT
FOR THE MONTH OF JUNE 2020
SECTOR: ECONOMIC (INFRASTRUCTURE DEV'T. PROGRAM)
OFFICE/AGENCY: PROVINCIAL ENGINEER'S OFFICE
AREA: AREA: 1ST ENGINEERING DISTRICT - COMPLETED AND ON-GOING PROJECTS
Name of Project |  |  | Source of Fund | Type | Physical | Mode | PROJECT DATA | [5 empty] | Financial (000) |  | Physical Accomplishment |  |  |  | Employment |  | REMARKS
|  |  |  | of | Target | of | a) Project Cost |  | a) | Date A lot. Rel. | e) | # of days suspended | a) Program |  | a) Planned |  | c) Actual |  | Generated
|  |  |  | Project | (Descrip | Impl. | b) Project Engineer |  | b) | Date Started | f) | # of days extended | b) Allotment |  | b) Revised |  | d) Slippage |  | a) # of Persons | # of Persons
|  |  |  | (Location) | tion) |  | c) Implementor |  | c) | Target Compl. Date | g) | Date completed | c) Disbursement | [5 empty] | b) | Man-days
[7 empty] | d) Duration |  | d) | Revised Compl. Date
I. PROJECTS UNDER THE CONTINUING APPROPRIATION | [22 empty] | AC |  |  |  | 893809.45
ON-GOING/FOR IMPLEMENTATION | [22 empty] | 1
| Rehab. Of Capungagan-Boundary San Miguel FMR, Kapalong, Davao del Norte |  | PRDP CY 2015 | Road | 10.6 kms. | Contract. | a) | 108,303,841.70 | a) | CY 2015 | e) | 140 CD | a) | 108,303,841.70 | a) | 100.00% | c) | 93.8% | a) | 38 | Suspended effective April 5, 2020 due to issued Executive Order No. 31, series of 2020 the province of Davao del Norte in response to the State of Public Health Emergency and State of National Calamity (COVID19 Pandemic). |  | 1
1 | [6 empty] | b) | Nasol | b) | 2016-04-06 | f) | 634 | b) | 108,303,841.70 | b) | 97.28% | d) | -3.48% | b) | 1140 |  |  | 1
[7 empty] | c) | VICLAO | c) | 2017-03-26 | g) | - | c) | 60,050,673.93 | [8 empty] | 1
[7 empty] | d) | 1410 | d) | 2020-02-14 | [12 empty] | FS
| Rehab. Of Pob.-Limbaan-Suawon-Macgum FMR w/ Bridge, New Corella, Davao del Norte |  | PRDP CY 2015 | Road | 15.01 kms./42 ln.m | Contract. | a) | 205,202,114.16 | a) | CY 2015 | e) | 229 CD | a) | 205,202,114.16 | a) | 100.00% | c) | 77.49% | a) | 40 | On-going (Increase of Project Cost due to Variation Order Php 14,948,622.18, Partial suspension due to soft soil from sta. 8+000 - 10+000); (Suspended last April 5, 2020 due to COVID; Resumption Order dated June 1, 2020) |  | AC
2 | [6 empty] | b) | Madrigal | b) | 2016-04-08 | f) | 490 CD | b) | 205,202,114.16 | b) | 83.77% | d) | -6.282% | b) | 1200 |  |  | 1
[7 empty] | c) | Dvo. Rock Mixer | c) | 2019-01-18 | g) | - | c) | 141497191.47 | [8 empty] | 1 | 1 | Asuncion | Red
[7 empty] | d) | 1529 CD | d) | 2020-08-15 | [12 empty] | FS
| Rehab. Of Sonlon - Camansa FMR Asuncion, Davao del Norte |  | PRDP CY 2015 | Road | 10.23 km. | Contract. | a) | 215,125,015.81 | a) | 2018-09-18 | e) |  | a) | 215,125,015.81 | a) | 39.51% | c) | 31.6% | a) | 30 | On-going (Suspended last April 5, 2020 due to COVID; Resumption Order dated June 1, 2020) |  | 1
3 | [6 empty] | b) | Fabiala | b) | 2019-05-28 | f) |  | b) | 215,125,015.81 | b) | - | d) | -7.91% | b) | 780 |  |  | 1 | 1 | Asuncion | Red
[7 empty] | c) | Three w/Builders, Inc/Davao Rock Mixer Enterprises (JV) | c) | 2020-12-31 | g) | - | c) | 40,523,099.23 | [8 empty] | 1 | 2 | B.E. Dujali | Yellow
[7 empty] | d) | 384 CD | d) | - | [12 empty] | FS | 3 | Carmen | Blue
| Cacao Production and Beans Marketing, Capungagan, Kapalong, Davao del Norte |  | PRDP CY 2016 | Bldg. | 3610 sq.m | Contract. | a) | 5873626.8 | a) | CY 2016 | e) | - | a) | 5873626.8 | a) | 100% | c) | 91.09% | a) |  | Suspended due to modification of Detailed Design of mechanical Drier dated November 23, 2019; Waiting for the resumption order from DA. |  | 1 | 4 | Kapalong | Pink
4 | [6 empty] | b) | Delos Reyes | b) | 2019-03-19 | f) | - | b) | 5873626.8 | b) | - | d) | -8.905% | b) |  |  |  | 1 | 5 | New Corella | Gray
[7 empty] | c) | MICAH CONST. & SUPPLY | c) | 2019-11-23 | g) | - | c) | 4698901.44 | [8 empty] | 1 | 6 | San Isidro | Orange
[7 empty] | d) | 250 CD | d) | - | [12 empty] | 1 | 7 | Sto Tomas | Sky Blue
| Improvement of New Corella Nursery with Organic Input Production & Common Facility, Davao del Norte |  | PRDP CY 2016 | Bldg. | 1901.00 sq.m | Contract. | a) | 9,889,628.45 | a) | CY 2016 | e) | 222 CD | a) | 9,889,628.45 | a) | 80.36% | c) | 46.3% | a) | 10 | On-going (Suspended last April 5, 2020 due to COVID; Resumption Order dated June 1, 2020) |  | 1 | 9 | Panabo City | Brown
5 | [6 empty] | b) | Delos Reyes/Cabañero | b) | 2019-01-17 | f) | - | b) | 9,889,628.45 | b) | 49.99% | d) | -3.684% | b) | 250 |  |  | 1 | 10 | IGACOS | Yellow Green
[7 empty] | c) | SOUTH IRONROCK CORPORATION | c) | 2019-11-23 | g) | - | c) | - | [8 empty] | 1 | 11 | Tagum City | Green
[7 empty] | d) | 514 CD | d) | 2020-06-18 | [12 empty] | 1
| Repair of Damaged Drainage/Creeks of Canatan, Asuncion |  | QRF CY 2015 & 2016 | Drainage/Creeks | - | - | a) | 137754.69 | a) | - | e) | - | a) | 137754.69 | a) | - | c) | - | a) | - | Suspended due to modification of Detailed Design of mechanical Drier dated November 23, 2019 |  | 1
6 | [6 empty] | b) |  | b) | - | f) | - | b) | 137754.69 | b) | - | d) | - | b) | - |  |  | 1
[7 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[7 empty] | d) | - | d) | - | [12 empty] | 1
| Construction of Water Reservoir & Purchase of P.E. Pipelines, Sagayen, Asuncion |  |  | Water System | Households | MLGU | a) | 500000 | a) | 2017-12-28 | e) | - | a) | 500000 | a) | 90.00% | c) | 90.00% | a) | - | Suspended due to non availability of water source during drilling.Find another location. Fund already transferred at Municipality of Asuncion with ChecK No. 2445174 and OR # 9238468, |  | 1
7 | [6 empty] | b) | - | b) | 2018-11-15 | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[7 empty] | c) | MEO | c) | - | g) | - | c) | - | [8 empty] | 1
[7 empty] | d) | - | d) | - | [12 empty] | 1
| NEW CORELLA | [21 empty] | 1
| Road Rehabilitation at Prk. 1-Prk. 5, Sta. Fe, New Corella |  | 20% DF CY 2017 (STIMULUS) | Road | km. | MLGU | a) | 500000 | a) | 2017-11-29 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Fund already transferred at Municipality of New Corella with ChecK No. 2445213 and OR # 8592072, dated March 13, 2018. Waiting for availability of Bulldozer. |  | 1
8 | [6 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[7 empty] | c) | MEO | c) | - | g) | - | c) | - | [8 empty] | 1
[7 empty] | d) | - | d) | - | [12 empty] | 1
| TALAINGOD | [21 empty] | 1
| Const. of Covered Court Bleacher, Palma Gil, Talaingod |  | 20% DF CY 2017 (STIMULUS) | Court | sq.m | MLGU | a) | 500000 | a) | 2017-12-28 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | On-going (Fund already transferred at Municipality of Talaingod with ChecK No. 2445181 and OR # 7955667, dated March 16, 2018 . Amended from Electrification @ Prk. 1A-Prk. 5A) |  | 1
9 | [6 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[7 empty] | c) |  | c) | - | g) | - | c) | - | [8 empty] | 1
[7 empty] | d) | - | d) | - | [12 empty] | AC
| CONST./REHAB./COMP. OF VARIOUS GOV'T. BLDGS. STRUCT., FAC (Provincewide) LS - P9,000,000.00 | [21 empty] | 1
| Rehab. Of PEO Training Center, (PDPM),Mankilam, Tagum City, (Part of P803,000.00)(20% DF CY 2018-P326,124.00) |  | 20% DF CY 2017 | Bldgs. | sq.m | Admin | a) | 476,876.00 | a) | 2019-02-12 | e) | - | a) | 476,876.00 | a) | 99.00% | c) | 99.00% | a) | 3 | Suspended (additional PR for Elect. Mat.) dated March 9, 2020 |  | 1
10 | [6 empty] | b) | Chua | b) | 2019-11-04 | f) | - | b) | 476,876.00 | b) | - | d) | - | b) | 57 |  |  | 1
[7 empty] | c) | PEO | c) | 2020-01-17 | g) | - | c) | 407,521.70 | [8 empty] | 1
[7 empty] | d) | 50 WD | d) | 2020-03-15 | [12 empty] | 1
| Upgrading of DDNSTC (Basketball/Voleyball MP Covered Court),Sports Center, Mankilam, Tagum City |  | SB # 4 CY 2017 | Covered | 2252.69 sq.m | Contract | a) | 99992356.64 | a) | 2018-10-16 | e) | - | a) | 99992356.64 | a) | 100% | c) | 70.5% | a) | 10 | On-going (Suspended last April 5, 2020 due to COVID; Resumption Order dated May 4, 2020) |  | 1
11 | [6 empty] | b) | Daral | b) | 2018-07-17 | f) | 20 CD | b) | 99992356.64 | b) | - | d) | -29.5% | b) | 310 |  |  | AC
[7 empty] | c) | YBC | c) | 2019-07-11 | g) | - | c) | 18, 280, 402.33 | [8 empty] | AC
[7 empty] | d) | 360 CD | d) | 2020-02-02 | [12 empty] | AC
| Rehab. Of Saug Bridge of Slope Protection |  | QRF CY 2017 | Slope | 356.40 cu.m | Admin | a) | 4,850,000.00 | a) | 2018-05-25 | e) | 400 CD | a) | 4,850,000.00 | a) | 49.81% | c) | 49.81% | a) | 17 | On-going (Suspended dated January 28, 2019; Resumption February 3, 2020; Resumption Order dated May 4, 2020; Suspended effective April 5, 2020 due to COVID; resumption order dated May 4, 2020) |  | AC
12 | [6 empty] | b) | Gone | b) | 2019-01-03 | f) | - | b) | 4,850,000.00 | b) | - | d) | - | b) | 306 |  |  | AC
[7 empty] | c) | PEO | c) | 2019-03-25 | g) | - | c) | 1628912.92 | [8 empty] | 1
[7 empty] | d) | 120 CD | d) | 2020-06-05 | [12 empty] | AC
| Re-channeling of BIGA River with Earth Dike and Slope Protection, Brgy. Gupitan, Kaplaong |  | QRF CY 2017 | Slope | 0.9 km | Contract | a) | 12,100,000.00 | a) | 2018-07-20 | e) | - | a) | 12,100,000.00 | a) | 8.30% | c) | 3.36% | a) | 4 | On-going (Suspended effective April 5, 2020 due to COVID; resumption order dated May 4, 2020) |  | AC
13 | [6 empty] | b) | Limpo | b) | 2019-02-22 | f) | - | b) | 12,100,000.00 | b) |  | d) | -4.94% | b) | 120 |  |  | FS
[7 empty] | c) | Alpha & Omega | c) | 2019-06-11 | g) | - | c) | - | [8 empty] | AC
[7 empty] | d) | 110 CD | d) | [13 empty] | AC
| Const. of Trading Post, Storage Building |  | OPPAP-PAMANA CY 2017 | Bldg. | sq.m | Contract | a) | 3,975,000.00 | a) | CY 2017 | e) | - | a) | 3,975,000.00 | a) | - | c) | - | a) | - | Abstract 1220194004 (Tagum Builders) |  | 1
14 | with (1) unit Hauling Truck, Brgy. Pandapan | [5 empty] | b) | - | b) | - | f) | - | b) | 3,975,000.00 | b) | - | d) | - | b) | - | PO # 2019102828 - Truck |  | 1
[7 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[7 empty] | d) | - | [14 empty] | 1
| VARIOUS OF WATER SYSTEM (Provincewide) | [21 empty] | 1
| LS - P 10,000,000.00 | [21 empty] | 1
- Conduct of geo-resistivty/drillig test | [22 empty] | 1
of proposed site LS - P250,000.00 | [22 empty] | 1
| Const. of PWS Linao, San Isidro |  | 20% DF CY 2018 | geo-resistivty/drillig | Ft. | Admin | a) | 62000 | a) |  | e) |  | a) | 62000 | a) |  | a) |  | a) |  | For implementation |  | 1
15 | [6 empty] | b) | - | b) | - | f) | - | b) | 62000 | b) | - | d) | - | b) | - |  |  | 1
[7 empty] | c) | PEO | c) | - | g) | - | c) | - | [8 empty] | 1
[7 empty] | d) | - | d) | - | [12 empty] | ?
| Const. of PWS Mamalian, San Isidro |  | 20% DF CY 2018 | geo-resistivty/drillig | Ft. | Admin | a) | 62000 | a) | - | e) | - | a) | 62000 | a) | - | c) | - | a) | - | For declaration of savings because the spring water source is not feasible for development. |  | 1
16 | [6 empty] | b) | - | b) | - | f) | - | b) | 62000 | b) | - | d) | - | b) | - |  |  | 1
[7 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[7 empty] | d) | - | d) | - | [12 empty] | 1
| Const. of PWS Sagayen, San Isidro |  | 20% DF CY 2018 | geo-resistivty/drillig | Ft. | Admin | a) | 62000 | a) | - | e) | - | a) | 62000 | a) | - | c) | - | a) | - | For implementation |  | 1
17 | [6 empty] | b) | - | b) | - | f) | - | b) | 62000 | b) | - | d) | - | b) | - |  |  | 1
[7 empty] | c) | PEO | c) | - | g) | - | c) | - | [8 empty] | 1
[7 empty] | d) | - | d) | - | [12 empty] | 1
- Construction of Water System Projects | [22 empty] | 1
in Component LGU's LS - 9,750,000.00 | [22 empty] | 1
| Installation of potable water System at Purok Nangka, Pandapan, Tagum City |  | 20% DF CY 2018 | Water System | Households | Admin | a) | 1125000 | a) | - | e) | - | a) | 1125000 | a) | - | c) | - | a) | - | Waiting for deed of donation. Follow-up letter was already issued
18 | [6 empty] | b) | - | b) | - | f) | - | b) | 1125000 | b) | - | d) | - | b) | -
[7 empty] | c) | PEO | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
| Rehab./Impv't. of San Vicente Water System, Asuncion |  | 20% DF CY 2018 | Water System | Households | Admin | a) | 1125000 | a) | 2018-10-26 | e) | - | a) | 1125000 | a) | - | c) | - | a) | - | Abstract # 0220190484 still draft
19 | [6 empty] | b) | - | b) | - | f) | - | b) | 1125000 | b) | - | d) | - | b) | - |  |  | 1
[7 empty] | c) | PEO | c) | - | g) | - | c) | - | [8 empty] | 1
[7 empty] | d) | - | d) | - | [12 empty] | 1
| COUNTERPART TO SPECIAL PROJECTS (Provincewide) LS - P 67,415,000.00 | [21 empty] | AC
| Rehab. Of Sonlon-Camansa FMR, Asuncion, Davao del Norte (PRDP Counterpart : 193,612,514.23) |  | 20% DF CY 2018 | Road | 10.230 km | Contract | a) | 21,512,501.5 | a) | 2018-09-18 | e) |  | a) | 21,512,501.5 | a) | 39.51% | c) | 31.6% | a) | 30 | On-going |  | 1
20 | [6 empty] | b) | Fabiala | b) | 2019-05-28 | f) | - | b) | 21,512,501.5 | b) | - | d) | -7.91% | b) | 690 |  |  | 1
[7 empty] | c) | Three w/Builders, Inc/Davao Rock Mixer Enterprises (JV) | c) | 2020-12-31 | g) | - | c) | 4,502,566.58 | [8 empty] | 1
[7 empty] | d) | 384 CD | d) | - | [12 empty] | 1
| Impvt. of Km. 9 Sagayen - Sawata Provincial Road Phase II |  | 20% DF CY 2018 | Road | 1.303 km. | Admin | a.) 7,742,775.95 |  | a) | 2019-01-31 |  |  | a) | 7427725.95 | a) | 45% | c) | 35.05% | a) | 6 | Suspended dated March 6, 2020 due to delay delivery of materials
21 | [6 empty] | b.) Kenny |  | b) | 2019-09-09 |  |  | b) | 7427725.95 | b) | - | d) | - | b) | 138 |  |  | 1
[7 empty] | c) | PEO | c) | 2020-03-27 |  |  | c) | 2603417.9455 | [8 empty] | 1
[7 empty] | d) | 200 CD | d) | - | [12 empty] | 1
| CONST./REHAB./COMP. OF VARIOUS GOV'T. BLDGS. STRUCT., FAC (Provincewide) (Provincewide) LS - P13,523,124.00 | [21 empty] | 1
| Rehab. Of PEO Training Center, (PDPM),Mankilam, Tagum City (Part of P803,000.00)(20% DF CY 2017-P476,876.00) |  | 20% DF CY 2018 | Bldg. | 85 sq. m | Admin | a) | 326124 | a) | 2019-02-12 | e) | - | a) | 326124 | a) | 100% | c) | 99% | a) | 3 | suspended due to additional materials for electrical works |  | 1
22 | [6 empty] | b) | Chua | b) | 2019-11-04 | f) | 57 CD | b) | 326124 | b) | - | d) | -1% | b) | 57 |  |  | 1
[7 empty] | c) | PEO | c) | 2019-01-17 | g) | - | c) | 322862.76 | [8 empty] | 1
[7 empty] | d) | 50 WD | d) | 2020-03-15 | [12 empty] | 1
| Construction of IP Tribal Council of Women at Brgy. Camansa, Asuncion |  | 20% DF CY 2018 | Bldg. | sq. m | Admin | a) | 560,000.00 | a) | - | e) | - | a) | 560,000.00 | a) | - | c) | - | a) | - | Purchase Request # 20032714
23 | [6 empty] | b) | - | b) | - | f) | - | b) | 560,000.00 | b) | - | d) | - | b) | - |  |  | 1
[7 empty] | c) | PEO | c) | - | g) | - | c) | - | [8 empty] | 1
[7 empty] | d) | - | d) | - | [12 empty] | 1
| RURAL ELECTRIFICATION (Provincewide) | [21 empty] | 1
LS - P5,000,000.00
| Rural Electrification at Del Monte, New Corella |  | 20% DF CY 2018 | Elect. | Households | Contract | a) | 1000000 | a) | - | e) | - | a) | 1000000 | a) | - | c) | - | a) | - | For bidding |  | 1
24 | [6 empty] | b) | - | b) | - | f) | - | b) | 1000000 | b) | - | d) | - | b) | - |  |  | 1
[7 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[7 empty] | d) | - | d) | - | [12 empty] | 1
| Const. of Distribution Line in Sitio Prk. 1,3,4, 11 and 7, Camansa, Asuncion |  | 20% DF CY 2018 | Elect. | Households | Contract | a) | 4000000 | a) | - | e) | - | a) | 4000000 | a) | - | c) | - | a) | - | Purchase Request # 19093670 (On process ) |  | 1
25 | [6 empty] | b) | - | b) | - | f) | - | b) | 4000000 | b) | - | d) | - | b) | - |  |  | 1
[7 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[7 empty] | d) | - | d) | - | [12 empty] | 1
| Const. of Standard Quarantine Shed for Car Bath Natulian, Brgy. Palma Gil, Talaingod |  | 20% DF CY 2018 | Bldg. | sq.m | Contract | a) | 200000 | a) | - | e) | - | a) | 200000 | a) | - | c) | - | a) | - | For implementation |  | 1
26 | [6 empty] | b) | - | b) | - | f) | - | b) | 200000 | b) | - | d) | - | b) | - |  |  | AC
[7 empty] | c) | DIGOS CONSTRAK | c) | - | g) | - | c) | - | [8 empty] | AC
[7 empty] | d) | - | d) | - | [12 empty] | AC
| Construction of Veterinary Quarantine Station, New balamban, Tagum City |  | 20% DF CY 2018 | - | - | Contract | a) | 200000 | a) | - | e) | - | a) | 200000 | a) | - | c) | - | a) | - | For implementation |  | 1 | 1
27 | [6 empty] | b) | - | b) | - | f) | - | b) | 200000 | b) | - | d) | - | b) | - |  |  | 1
[7 empty] | c) | ALLBRYCAR | c) | - | g) | - | c) | - | [8 empty] | 1
[7 empty] | d) | - | d) | - | [12 empty] | 1
| ASUNCION | [21 empty] | 1
| Const. of Potable water System at Prk. 6, New Santiago, Asuncion |  | GF CY 2018 (STIMULUS) | Water System | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For bidding June 30, 2020 |  | 1
28 | [6 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[7 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[7 empty] | d) | - | d) | - | [12 empty] | 1 | Const. of MP Hall, Rizal ES, Binancian, Asuncion
| TAGUM CITY | [21 empty] | AC
| Completion of GYM Bleacher w/ Electrification, Pagsabangan, Tagum City |  | GF CY 2018 (STIMULUS) | Bleacher | km | MLGU | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For implementation but the project was implemented by the brgy. Waiting for resolution to change priority Alloted March 12, 2019 |  | AC
29 | [6 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[7 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | AC
[7 empty] | d) | - | d) | - | [12 empty] | 1
| Construction of Drainage Canal, Libuganon, Tagum City |  | GF CY 2018 (STIMULUS) | Drainage | ln.m | Admin | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For implementation |  | 1
30 | [6 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[7 empty] | c) | PEO | c) | - | g) | - | c) | - | [8 empty] | 1
[7 empty] | d) | - | d) | - | [12 empty] | 1
| KAPALONG | [21 empty] | 1
| Construction of Bleacher, Mamacao, Kapalong |  | GF CY 2018 (STIMULUS) | Bleacher | sq.m | Admin | a) | 500000 | a) | - | e) | 27 CD | a) | 500000 | a) | 73.71% | c) | 73.71% | a) | 7 | On-going (Suspended last April 5, 2020 due to COVID; Resumption Order dated May 4, 2020) |  | 1
31 | [6 empty] | b) | Ambrosio | b) | 2020-02-05 | f) | - | b) | 500000 | b) | - | d) | - | b) | 75 |  |  | 1
[7 empty] | c) | PEO | c) | 2020-04-19 | g) | - | c) | - | [8 empty] | FS
[7 empty] | d) | 75 CD | d) | 2020-05-17 | [12 empty] | AC
| Construction of Concrete Perimeter Fence, Luna, Kapalaong |  | GF CY 2018 (STIMULUS) | Fence | sq.m | Contract | a) | 500000 | a) | 2019-06-28 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For implementation |  | AC
32 | [6 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
| Completion of Brgy. Health Center, Maniki, Kapalong |  | GF CY 2018 (STIMULUS) | Bldg. | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For amendment.To submit a new resolution for another priority project which is the Const. of Multi-Purpose Pavement but the propose site is not is donated because the previous project Completion of Brgy. Health Center was funded by the LGU of Kapalong
33 | [6 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | FS
[7 empty] | d) | - | d) | - | [12 empty] | AC
| TALAINGOD | [21 empty] | 1
| Grouted Riprap on Embankment Sto. Ñino, Talaingod |  | GF CY 2018 (STIMULUS) | Riprap | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Plan and POW on process c/o PDPM |  | 1
34 | [6 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[7 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[7 empty] | d) | - | d) | - | [12 empty] | 1
| Barangay Hall Improvement, Dagohoy, Talaingod |  | GF CY 2018 (STIMULUS) | Bldg. | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For amendment to Construction of Retaining Wall as per recommendation by Engr. Misa during site re-evaluation. Plan & POW completed.Resolution from the Brgy. Council to support the amendment c/o Engr. Canillada |  | 1
35 | [6 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
| Construction of 2 Classroom Building Datu Jose Libayao NHS Ext, Natulian, Palma Gil, Talaingod |  | GF CY 2018 (STIMULUS) | Bldg. | - | - | a) | 2000000 | a) | - | e) | - | a) |  | a) | - | c) | - | a) | - | Post Qualification on process |  | 1
36 | [6 empty] | b) | - | b) | - | f) | - | b) |  | b) | - | d) | - | b) | - |  |  | 1
[7 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[7 empty] | d) | - | d) | - | [12 empty] | 1
| REHABILITATION OF VARIOUS PROVINCIAL ROADS | [21 empty] | 1
| Mesaoy - Jct. Mahayahay |  | SB # 1 CY 2018 | road | km | Admin | a) | 1,534,000.00 | a) | 2018-07-19 | e) | - | a) | 1,534,000.00 | a) | 60% | c) | 60% | a) | - | Suspended as of Dec. 27, 2018 (For clarification regarding the cancellation of PO # 2018082439) |  | 1
37 | [6 empty] | b) | Paraguya | b) | 2018-11-16 | f) | - | b) | 1,534,000.00 | b) | - | d) | - | b) | - |  |  | 1
[7 empty] | c) | PEO | c) | 2018-12-15 | g) | - | c) | 920400 | [8 empty] | 1
[7 empty] | d) | - | d) | - | [12 empty] | 1
| CONST./COMPL./IMPV'T. OF VARIOUS GOV'T. BLDGS., STRUCTURES & FACILITIES (Const. in Progress - Bldgs. & Other Structures | [21 empty] | 1
1
1
| Const./Impv't. of DDN Hospital Kapalong Zone |  | SB # 2 CY 2018 | Bldg. | sq.m | Contract | a) | 5,000,000.00 | a) | 2018-09-04 | e) | 25 CD | a) | 5,000,000.00 | a) | 95.62% | c) | 95.62% | a) | 6 | On-going (Suspended last April 5, 2020 due to COVID; resumption order dated May 4, 2020) |  | 1
38 | [6 empty] | b) | Ambrosio | b) | 2019-11-02 | f) | - | b) | 5,000,000.00 | b) | - | d) | - | b) | 150 |  |  | 1 | 4
[7 empty] | c) | MAG CORP. | c) | 2020-04-30 | g) | - | c) | 4781000 | [8 empty] | 1
[7 empty] | d) | 220 CD | d) | 2020-06-25 | [12 empty] | 1
| Compl. Of Bahay Pag-Asa for Minors, New Corella |  | SB # 2 CY 2018 | Bldg. | sq.m | Admin | a) | 3,450,000.00 | a) | - | e) | - | a) | 3,450,000.00 | a) | - | c) | - | a) | - | For implementation |  | 1
39 | [6 empty] | b) | - | b) | - | f) | - | b) | 3,450,000.00 | b) | - | d) | - | b) | - |  |  | 1 | 4
[7 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1 | 4
[7 empty] | d) | - | d) | - | [12 empty] | 1 | 4
| Const. of Add'l. 2nd Level Multi-Purpose HalI, PGSO warehouse,Bldg., Mankilam |  | SB # 2 CY 2018 | Bldg. | sq.m | Contract | a) | 7,592,588.00 | a) | - | e) | - | a) | 7,592,588.00 | a) | - | c) | - | a) | - | PO # 2020020808 (F2 Construction) |  | 1
40 | [6 empty] | b) | - | b) | - | f) | - | b) | 7,592,588.00 | b) | - | d) | - | b) | - |  |  | 1 | 4
[7 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1 | 4
[7 empty] | d) | - | d) | - | [12 empty] | 1 | 4
| Construction of SP/Legislative Building, Gov't. Center, Mankilam, Tagum City |  | SB # 3 CY 2018 | Bldg. | sq.m | Contract | a) | 147262698.81 | a) | - | e) | 27 CD | a) | 147262698.81 | a) | 2.21% | c) | 2.21% | a) | 20 | On-going (Suspended last April 5, 2020 due to COVID; resumption order dated May 4, 2020) |  | 1 | 4
41 | [6 empty] | b) | Japay/Albaracin | b) | 2020-04-30 | f) | - | b) | 147262698.81 | b) | - | d) | - | b) | 370 |  |  | 1 | 4
[7 empty] | c) | Tagum Builders | c) | 2021-05-02 | g) | - | c) | - | [8 empty] | 1 | 4
[7 empty] | d) | 370 CD | d) | 2021-05-29 | [12 empty] | 1 | 4
| Rehab./Impv't. of MP Bldg. (Gym), Napungas, Asuncion |  | SB # 5 CY 2018 (STIMULUS) | GYM | sq.m | - | a) | 500000 | a) | 2019-02-04 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | PR # 20010252 |  | 1 | 4
41 | [6 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1 | 4
[7 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1 | 4
[7 empty] | d) | - | d) | - | [12 empty] | 1
| Concreting of Drainage Canal from Prk. 3, 1-A, 2-A to Prk. 1-B, Brgy. Site, Phase @, New Corella |  | SB # 5 CY 2018 (STIMULUS) | - | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Bidding Documents for posting |  | 1
42 | [6 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  |  | 4
[7 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | AC
[7 empty] | d) | - | d) | - | [12 empty] | AC
| Division School Improvement (Davao del Norte DEPED Training Center), Tagum City |  | SEF (ANNUAL BUDGET CY 2018) | Bldg. | sq.m | Admin | a) | 1250000 | a) | 2019-02-04 | e) | 28 CD | a) | 1250000 | a) | 70.05% | c) | 68.05% | a) | 16 | On-going (Suspended last April 5, 2020 due to COVID; resumption order dated May 4, 2020) |  | 1
43 | [6 empty] | b) | Japay/Quirant | b) | 2019-11-26 | f) | - | b) | 1250000 | b) | - | d) | -2% | b) | 320 |  |  | 1
[7 empty] | c) | Admin | c) | 2020-05-03 | g) | - | c) | 850625 | [8 empty] | 1
[7 empty] | d) | 160 CD | d) | 2020-05-31 | [12 empty] | 1
| Const. of Processing and Bagsakan Center, Brgy. Dagohoy, Talaingod |  | OPAPP-PAMANA CY 2018 | Bldg. | sq.m | Contract | a) | 2500000 | a) | 2019-11-25 | e) | - | a) | 2500000 | a) | 55.61% | c) | 68.72% | a) | 8 | On-going; Resumption Order dated May 4, 2020 |  | 1
44 | [6 empty] | b) | Dadula | b) | 2019-11-25 | f) | - | b) | 2500000 | b) | - | d) | +13.11% | b) | 200 |  |  | 1
[7 empty] | c) | RLHV | c) | 2020-04-10 | g) | - | c) | 375000 | [8 empty] | 1
[7 empty] | d) | 145 CD | d) | - | [12 empty] | 1
| Post Harvest Facilities (Corn Mill, Solar Dryer, Corn Sheller), Kapalong, Davao del Norte |  | OPAPP-PAMANA CY 2018 | Bldg. | sq.m | Admin | a) | 1500000 | a) | 2019-11-18 | e) | 28 CD | a) | 1500000 | a) | 93.44% | c) | 93.44% | a) | 7 | On-going (Suspended last April 5, 2020 due to COVID; resumption order dated May 4, 2020) |  | 1
45 | [6 empty] | b) | Ambrosio | b) | 2019-11-18 | f) | - | b) | 1500000 | b) | - | d) | - | b) | 175 |  |  | 1
[7 empty] | c) | PEO | c) | 2020-02-26 | g) | - | c) | 1114654.45 | [8 empty] | 1
[7 empty] | d) | - | d) | 2020-06-15 | [12 empty] | 1
| Construction of PWS Level II in Purok 7-A and 7-B, Capungagan, Kapalong |  | OPAPP-PAMANA CY 2018 | PWS | Households | Admin | a) | 1760000 | a) | 2019-11-25 | e) | 28 CD | a) | 1760000 | a) | 100% | c) | 70.19% | a) | 5 | On-going (Suspended last April 5, 2020 due to COVID; resumption order dated May 4, 2020) |  | 1
46 | [6 empty] | b) | Kabinge | b) | 2019-11-25 | f) | 44 CD | b) | 1760000 | b) | 93.05% | d) | -22.86% | b) | 125 |  |  | 1
[7 empty] | c) | PEO | c) | 2020-03-20 | g) | - | c) | 1235344 | [8 empty] | 2
[7 empty] | d) | 116 CD | d) | 2020-05-07 | [12 empty] | AC
| Construction of PWS Level II in Purok 2, Pag-Asa, kapalong |  | OPAPP-PAMANA CY 2018 | PWS | Households | Admin | a) | 2310000 | a) | 2019-11-25 | e) | 28 CD | a) | 2310000 | a) | 78.00% | c) | 49.086% | a) | 9 | On-going (Suspended last April 5, 2020 due to COVID; resumption order dated May 4, 2020) |  | AC
47 | [6 empty] | b) | Dadula | b) | 2019-12-16 | f) | 45 CD | b) | 2310000 | b) | - | d) | -28.91% | b) | 138 |  |  | 1
[7 empty] | c) | PEO | c) | 2020-04-14 | g) | - | c) | 1133886.6 | [8 empty] | 1
[7 empty] | d) | 115 CD | d) | 2020-07-15 | [12 empty] | 1
| Cattle Production- Brgy. Tiburcia, Gupitan and Semong, Kapalong |  | OPAPP-PAMANA CY 2018 | Bldg. | - | - | a) | 1500000 | a) | - | e) | - | a) | 1500000 | a) | - | c) | - | a) | - | For cancellation. A letter was sent to OPAPP last Dec 2018 requesting to allow us to reduce the number of cattle but we are still hoping that there would be a supplier will bid |  | 1
48 | [6 empty] | b) | - | b) | - | f) | - | b) | 1500000 | b) | - | d) | - | b) | - |  |  | 1
[7 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[7 empty] | d) | - | d) | - | [12 empty] | 1
| Cattle Production, Brgy. Palma Gil, Brgy. Sto. Nino, Brgy. Dagohoy, Talaingod, Davao del Norte |  | OPAPP-PAMANA CY 2018 | Bldg. | - | - | a) | 1500000 | a) | - | e) | - | a) | 1500000 | a) | - | c) | - | a) | - | For cancellation. A letter was sent to OPAPP last Dec 2018 requesting to allow us to reduce the number of cattle but we are still hoping that there would be a supplier will bid
49 | [6 empty] | b) | - | b) | - | f) | - | b) | 1500000 | b) | - | d) | - | b) | - |  |  | 1
[7 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[7 empty] | d) | - | d) | - | [12 empty] | 1
| Rice Mill for Upland Rice, Palma Gil, Talaingod |  | OPAPP-PAMANA CY 2018 | Rice Mill | sq.m | Admin | a) | 1000000 | a) | - | e) | - | a) | 1000000 | a) | - | c) | - | a) | - | For implementation |  | 1
50 | [6 empty] | b) | - | b) | - | f) | - | b) | 1000000 | b) | - | d) | - | b) | - |  |  | 1
[7 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[7 empty] | d) | - | d) | - | [12 empty] | 1
| Rehab. Of Slope Protection of Libuganon River Along Kapalong - Mabantao - Florida Prov'l. Road Phase I |  | QRF CY 2016 | Road | km | - | a) | 900000 | a) | - | e) | - | a) | 900000 | a) | - | c) | - | a) | - | For AIP Amendment |  | 1
51 | [6 empty] | b) | - | b) | - | f) | - | b) | 900000 | b) | - | d) | - | b) | - |  |  | 1
[7 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[7 empty] | d) | - | d) | - | [12 empty] | 1
| GROUND DEVELOPMENT | [21 empty] | 1
| Ground Development and landscape @ PDRRMD, Gov't. Center, Mankilam, Tagum City |  | LDRRMF 2018 | Ground Dev't. | km. | Admin | a) | 1000000 | a) | 2019-03-19 | e) | - | a) | 1000000 | a) | 75.24% | c) | 75.24% | a) | 8 | Suspended (Waiting for the complete delivery of materials) dated March 2, 2020 |  | 1
52 | [6 empty] | b) | Juan | b) | 2019-11-04 | f) | - | b) | 1000000 | b) | - | d) | - | b) | 152 |  |  | 1
[7 empty] | c) | PEO | c) | 2020-02-29 | g) | - | c) | 752400 | [8 empty] | 1
[7 empty] | d) | 118 CD | d) | - | [12 empty] | 1
| REPAIR/MAINTENANCE OF PROVINCIAL RAODS & BRIDGES LS - (14.084KM) | [21 empty] | 1
| LS - P41,465,029.00 | [21 empty] | 1
| ROAD ID 007 - Jct. Highway Canatan - Doña Andrea |  | 20% DF CY 2019 | Road Rehabilitation | 4.34 | Admin | a) | 2000000 | a) | 2019-06-12 | e) | - | a) | 2000000 | a) | - | c) | - | a) | - | For implementation |  | 1
53 | [6 empty] | b) | Pilotos | b) | - | f) | - | b) | 2000000 | b) | - | d) | - | b) | - |  |  | 1
[7 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[7 empty] | d) | - | d) | - | [12 empty] | 1
| ROAD ID 015 - Pamacaun - Lasang Banate |  | 20% DF CY 2019 | Road Rehabilitation | 4.34 | Admin | a) | 2000000 | a) | 2019-06-27 | e) | - | a) | 2000000 | a) | - | c) | - | a) | - | For implementation (Waiting for the delivery of geo-grid materials. An approved request letter dated Dec. 3, 2019 for the extension of 50 days from Provincial Administrator Engr. Rabanoz is on file |  | 1
54 | [6 empty] | b) | Gone | b) | - | f) | - | b) | 2000000 | b) | - | d) | - | b) | - |  |  | 1
[7 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[7 empty] | d) | - | d) | - | [12 empty] | 1
| ROAD ID 019 - Sto. Niño - Palma Gil - Sitio Opao |  | 20% DF CY 2019 | Road Rehabilitation | 11.6 | Contract | a) | 1901000 | a) | 2019-06-19 | e) | 72 CD | a) | 1901000 | a) | 44.89% | c) | 44.89% | a) | - | On-going (Suspended dated March 14, 2020; Resumption Order dated May 25, 2020) |  | 1
55 | [6 empty] | b) | Lumapat | b) | 2020-03-06 | f) | - | b) | 1901000 | b) | - | d) | - | b) | - |  |  | 1
[7 empty] | c) | Tagum Constrak | c) | 2020-04-18 | g) | - | c) | - | [8 empty] | 1
[7 empty] | d) | 44 CD | d) | - | [12 empty] | 1
| ROAD ID 023 - Sto. Niño - Daligdigon - Paiton |  | 20% DF CY 2019 | Road Rehabilitation | 11.6 | Contract | a) | 3000000 | a) | 2019-10-03 | e) | - | a) | 3000000 | a) | 2.19% | c) | 3.98% | a) | - | On-going; Resumption Order dated May 4, 2020 |  | 1
56 | [6 empty] | b) | Lumapat | b) | 2020-01-16 | f) | - | b) | 3000000 | b) | - | d) | +1.79% | b) | - |  |  | 1
[7 empty] | c) | - | c) | 2020-05-14 | g) | - | c) | 119400 | [8 empty] | 1
[7 empty] | d) | - | d) | - | [12 empty] | 2
| ROAD ID 024 - Jct. Paiton - Mibolo |  | 20% DF CY 2019 | Road Rehabilitation | 23.9 | Contract | a) | 6000000 | a) | 2019-03-25 | e) | - | a) | 6000000 | a) | 21.05% | c) | 21.05% | a) | - | Temporary suspended because the materials for the box culvert procurement on process wth PO # 2019061674 |  | AC
57 | [6 empty] | b) | Lumapat | b) | 2019-08-01 | f) | - | b) | 6000000 | b) | - | d) | 0% | b) | - |  |  | AC
[7 empty] | c) | PEO | c) | 2020-03-15 | g) | - | c) | 1263000 | [8 empty] | AC
[7 empty] | d) | - | d) | - | [12 empty] | AC
| ROAD ID 037 - Monte Dujali - Gupitan |  | 20% DF CY 2019 | Road Rehabilitation | 4.58 | Contract | a) | 1200000 | a) | 2019-12-06 | e) | 30 CD | a) | 1200000 | a) | 40.45% | c) | 40.45% | a) | 8 | On-going (Suspended last April 5, 2020 due to COVID; resumption order dated May 4, 2020) |  | 1
58 | [6 empty] | b) | Bacaron | b) | 2020-01-31 | f) | - | b) | 1200000 | b) | - | d) | - | b) | 240 |  |  | AC
[7 empty] | c) | PEO | c) | 2020-03-31 | g) | - | c) | 485400 | [8 empty] | AC
[7 empty] | d) | 61 CD | d) | 2020-07-15 | [12 empty] | 1
| VARIOUS OF LOCAL ROADS & DRAINAGE DEVELOPMENT PROJECT(Provincewide) LS - 15,000,000.00 | [21 empty] | 1
| Rehab./Impv't. of San Juan-New Talisay Provincial Road with Drainage |  | 20% DF CY 2019 | Road Drainage rehabiliated | km. | - | a) | 1000000 | a) | 2019-01-31 | e) | - | a) | 1000000 | a) | - | c) | - | a) | - | For implementation |  | 1
59 | [6 empty] | b) | Pilotos | b) | - | f) | - | b) | 1000000 | b) | - | d) | - | b) | -
[7 empty] | c) | PEO | c) | - | g) | - | c) | - | [8 empty] | AC
[7 empty] | d) | 44 CD | d) | - | [12 empty] | AC
| Repair/Rehab. Of Concrete Road Jct. Suaon-Libuton, Kapalong |  | 20% DF CY 2019 | Road Drainage rehabiliated | km. | - | a) | 1000000 | a) | 2019-03-12 | e) |  | a) | 1000000 | a) |  | c) |  | a) | - | For implementation |  | AC
60 | [6 empty] | b) | Bacaron | b) | - | f) | - | b) | 1000000 | b) | - | d) | - | b) | - |  |  | AC
[7 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | FS
[7 empty] | d) | - | d) | - | [12 empty] | AC
| Impv't. of Cross Drainage along Saug-Sonlon-Bdry. Longanapan |  | 20% DF CY 2019 | Road Drainage rehabiliated | ln.m | - | a) | 3000000 | a) | - | e) | - | a) | 3000000 | a) | - | c) | - | a) | - | For implementation |  | 1
61 | [6 empty] | b) | Pilotos | b) | - | f) | - | b) | 3000000 | b) | - | d) | - | b) | - |  |  | 1
[7 empty] | c) | PEO | c) | - | g) | - | c) | - | [8 empty] | 1
[7 empty] | d) | 89 CD | d) | - | [12 empty] | 1
| Rehab./Impv't. of Sto. Niño-Palma Gil-Sitio Opao Provincial Road with Drainage |  | 20% DF CY 2019 | Road Drainage rehabiliated | ln.m | Contract | a) | 3000000 | a) | 2019-05-25 | e) | 71 CD | a) | 3000000 | a) | 53% | c) | 53% | a) | - | On-going (Suspended dated March 14, 2020; Resumption Order dated May 25, 2020) |  | 1
62 | [6 empty] | b) | Lumapat | b) | 2020-02-27 | f) | - | b) | 3000000 | b) | - | d) | - | b) | - |  |  | 1
[7 empty] | c) | Tagum Constrak | c) | 2020-05-14 | g) | - | c) | - | [8 empty] | 1
[7 empty] | d) | 70 CD | d) | - | [12 empty] | 1
| VARIOUS WATER SYSTEM DEVELOPMENT LS - P 9,750,000.00 | [19 empty] | (Note: 1.3M declared savings funded to other |  | 1
[21 empty] | Water System Projects-AIP 2nd revision CY 2019) |  | 1
| Construction of PWS, Bgry. Linao, San Isidro |  | 20% DF CY 2019 | Water System | Households | Admin | a) | 500000 | a) | 2019-06-19 | e) | - | a) | 500000 | a) | 43.22% | c) | 43.22% | a) | 4 | On-going (Suspended last April 5, 2020 due to COVID; resumption order dated May 4, 2020) |  | 1
63 | [6 empty] | b) | Aclaracion | b) | 2020-02-24 | f) | - | b) | 500000 | b) | - | d) | - | b) | 88 |  |  | 1
[7 empty] | c) | PEO | c) | 2020-04-23 | g) | - | c) | 216100
[7 empty] | d) | 60 CD | d) | 2020-07-05 | [12 empty] | 1
| Construction of PWS, Brgy. Datu Balong, San Isidro |  | 20% DF CY 2019 | Water System | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For declaration of savings because the spring water source is not feasible for development |  | 1
64 | [6 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[7 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[7 empty] | d) | - | d) | - | [12 empty] | 1
| Construction of PWS, Brgy. Sagayen, San Isidro |  | 20% DF CY 2019 | Water System | Households | Contract | a) | 500000 | a) | 2019-09-10 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Re-bid PR # 1908-3071 |  | 2
65 | [6 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | AC
[7 empty] | c) |  | c) | - | g) | - | c) | - | [8 empty] | AC
[7 empty] | d) | - | d) | - | [12 empty] | 1
| Installation of Shallow Tube Wells & Const. of Machinery Shed |  | 20% DF CY 2019 | Water System | - | Admin | a) | 1600000 | a) | - | e) | - | a) | 1600000 | a) | - | c) | - | a) | - | Amended from- Procurement of materials for the installation of Shallow Tube Wells for Irrigation & Const. of Machinery Shed for storage of open surface pump for PAGRO. POW revision on going due to the revision of plan to suit the amount allocated. |  | 1
66 | [6 empty] | b) | - | b) | - | f) | - | b) | 1600000 | b) | - | d) | - | b) | - |  |  | 1
[7 empty] | c) | PEO | c) | - | g) | - | c) | - | [8 empty] | 1
[7 empty] | d) | - | d) | - | [12 empty] | 1
| VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | [21 empty] | 1
| Repair/Impv't. of Municipal Triball Hall, New Corella |  | 20% DF CY 2019 | Bldg. | sq.m | Admin | a) | 1500000 | a) |  | e) | 28 CD | a) | 1500000 | a) | 34.60% | c) | 28.27% | a) | 5 | On-going (Suspended last April 5, 2020 due to COVID; resumption order dated May 4, 2020) |  | 1
67 | [6 empty] | b) | Cahayag | b) | 2020-03-02 | f) | - | b) | 1500000 | b) | - | d) | -6.33% | b) | 95 |  |  | 1
[7 empty] | c) | PEO | c) | 2020-06-12 | g) | - | c) | - | [8 empty] | 1
[7 empty] | d) | 103 CD | d) | 2020-07-10
| Const. of Municipal Tribal Hall, San Isidro |  | 20% DF CY 2019 | Bldg. | 42.00 sq.m | Admin | a) | 500000 | a) | 2019-01-15 | e) | - | a) | 500000 | a) | 81.44% | c) | 81.44% | a) | 8 | On-going (Suspended last April 5, 2020 due to COVID; resumption order dated May 4, 2020) |  | 1
68 | [6 empty] | b) | Aclaracion | b) | 2019-12-02 | f) | - | b) | 500000 | b) |  | d) | - | b) | 176 |  |  | 1
[7 empty] | c) | PEO | c) | 2020-02-19 | g) | - | c) | 407200 | [8 empty] | 1
[7 empty] | d) | 80 CD | d) | - | [12 empty] | 1
| Repair Bay of Disaster Quick Response Equipment @ PEO Compound, Gov't. Center, Mankilam, Tagum City |  | 20% DF CY 2019 | Bldg. | 66 sq.m | Admin | a) | 1000000 | a) | 2019-01-31 | e) | 28 CD | a) | 1000000 | a) | 74.70% | c) | 74.70% | a) | 5 | On-going (Suspended last April 5, 2020 due to COVID; resumption order dated May 4, 2020) |  | 1
69 | [6 empty] | b) | Chua/Mucas | b) | 2019-12-02 | f) | - | b) | 1000000 | b) | - | d) | - | b) | 95 |  |  | 1
[7 empty] | c) | PEO | c) | 2020-04-19 | g) | - | c) | 747000 | [8 empty] | 1
[7 empty] | d) | 140 CD | d) | 2020-05-17
| Const. of Multi-Purpose Hall Center (Cultural Heritage in Ancestral Domain of Ata-Manobo) |  | 20% DF CY 2019 | Bldg. | sq.m | Admin | a) | 3000000 | a) | - | e) | - | a) | 3000000 | a) | - | c) | - | a) | - | Fund re-aligned to GIDAS projects |  | FS
70 | [6 empty] | b) | - | b) | - | f) | - | b) | 3000000 | b) | - | d) | - | b) | - |  |  | AC
[7 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | AC
[7 empty] | d) | - | d) | - | [12 empty] | AC
| Const. of IP Women's Multi-{Purpose Bldg.), Cabidiangan, Sto. Niño, Talaingod |  | 20% DF CY 2019 | Bldg. | - | Admin | a) | 2000000 | a) | 2019-05-15 | e) | - | a) | 2000000 | a) | - | c) | - | a) | - | Final abstract #0320200897 (Alpebel Builders) |  | 1
71 | [6 empty] | b) | - | b) | - | f) | - | b) | 2000000 | b) | - | d) | - | b) | - |  |  | 1
[7 empty] | c) | PEO | c) | - | g) | - | c) | - | [8 empty] | 2
[7 empty] | d) | - | d) | - | [12 empty] | AC
| Extension of PAGRO Training Center & Ground Dev't., Gov't. Center, Mankilam, Tagum City |  | 20% DF CY 2019 | Bldg. | sq.m | Admin | a) | 1000000 | a) | 2019-07-26 | e) | 28 CD | a) | 1000000 | a) | 30.50% | c) | 30.50% | a) | 5 | On-going (Suspended last April 5, 2020 due to COVID; resumption order dated May 4, 2020) |  | 1
72 | [6 empty] | b) | Chua/Mugas | b) | 2020-02-03 | f) | - | b) | 1000000 | b) | - | d) | - | b) | 57 |  |  | 1
[7 empty] | c) | PEO | c) | 2020-04-23 | g) | - | c) | - | [8 empty] | 1
[7 empty] | d) | 80 CD | d) | 2020-05-21 | [12 empty] | 1
| Construction of Abilidad Training Center, Gov't. Center, Mankilam, Tagum City |  | 20% DF CY 2019 | Bldg. | - | - | a) | 7000000 | a) | - | e) | - | a) | 7000000 | a) | - | c) | - | a) | - | Fund re-aligned to GIDAS projects |  | 1
73 | [6 empty] | b) | - | b) |  | f) | - | b) | 7000000 | b) | - | d) | - | b) | - |  |  | 1
[7 empty] | c) | PEO | c) | - | g) | - | c) | - | [8 empty] | 1
[7 empty] | d) | - | d) | - | [12 empty] | 1
| Const. of 1 CL Bldg. @ Suawon ES, New Corella |  | 20% DF CY 2019 | Bldg. | 82.65 sq.m | Admin | a) | 1000000 | a) | 2020-06-07 | e) | 28 CD | a) | 1000000 | a) | 60.44% | c) | 60.44% | a) | 7 | On-going (Suspended last April 5, 2020 due to COVID; resumption order dated May 4, 2020) |  | 1
74 | [6 empty] | b) | Miraflor | b) | 2019-12-09 | f) | - | b) | 1000000 | b) |  | d) | - | b) | 147 |  |  | 1
[7 empty] | c) | PEO | c) | 2020-04-21 | g) | - | c) | 604400 | [8 empty] | 1
[7 empty] | d) | 135 CD | d) | 2020-05-19 | [12 empty] | 1
| Const. of Perimeter Fence at Sto. Niño Naseco Integrated School w/ Tugas Extension, Sto. Niño, Talaingod |  | 20% DF CY 2019 | Bldg. | sq.m | Admin | a) | 2000000 | a) | 2019-06-19 | e) | 28 CD | a) | 2000000 | a) | 87.65% | c) | 13.55% | a) | 8 | On-going (Suspended last April 5, 2020 due to COVID; resumption order dated May 4, 2020) | NOTE: STIMULUS CY 2019 | 1
75 | [6 empty] | b) | Torrecampo | b) | 2020-03-02 | f) | - | b) | 2000000 | b) |  | d) | - | b) | 76 |  | LS - PHP 41,000,000.00 | 1
[7 empty] | c) | PEO | c) | 2020-06-09 | g) | - | c) | - | [8 empty] | 1
[7 empty] | d) | 100 CD | d) | 2020-07-07 | [12 empty] | 1
| ASUNCION | [21 empty] | 1
| Rehab. Of Multi-Purpose Hall, New Bantayan, Asuncion |  | 20% DF CY 2019 (STIMULUS) | Bldg. | sq.m | Admin | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | (Fund transferred to LGU.c /o Engr. Lilibeth Cuajao) |  | 1
76 | [6 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[7 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[7 empty] | d) | - | d) | - | [12 empty] | 2
| NEW CORELLA | [21 empty] | 2
| Construction of Multi-Purpose Hall, El Salvador, New Corella |  | 20% DF CY 2019 (STIMULUS) | Bldg. | sq.m | MLGU | a) | 500000 | a) |  | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Fund transferred to LGU March 23, 2019 c/o Engr. Dugoldugol |  | 2
77 | [6 empty] | b) | - | b) |  | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[7 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[7 empty] | d) | - | d) | - | [12 empty] | 1
| Concreting of Drainage Canal , Pob., New Corella |  | 20% DF CY 2019 (STIMULUS) | Drainage | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Amended to Const. of 2 Storey Multi-Purpose Hall phase 3 (Brgy. Hall),Pob., New Corella (AIP 3rd revision CY 2019 / SB No. 4 CY 2019 |  | 1
78 | [6 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[7 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[7 empty] | d) | - | d) | - | [12 empty] | 2
| Rehab. Of Multi-Purpose Hall, Cabidianan, New Corella |  | 20% DF CY 2019 (STIMULUS) | Bldg. | sq.m | MLGU | a) | 500000 | a) | 2019-02-20 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Fund transferred to LGU c/o Engr. Dugoldugol |  | 2
79 | [6 empty] | b) |  | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[7 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[7 empty] | d) | - | d) | - | [12 empty] | AC
| Brgy. Electrification (Centro Gupitan), Gupitan, Talaingod |  | 20% DF CY 2019 (STIMULUS) | Elect. | - | MLGU | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Re-aligned to other stimulus projects that need additional funds to complete since the amount can not complete the project. Recommended for exact fund that can complete the project. |  | 2
80 | [6 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[7 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[7 empty] | d) | - | d) | - | [12 empty] | 2
| TAGUM CITY | [21 empty] | FS
| Rehab. of Evacuation Center, Magugpo Poblacion, Tagum City |  | 20% DF CY 2019 (STIMULUS) | Bldg. | - | - | a) | 500000 | a) |  | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Amended in the AIP 3rd revision CY 2019 /SB No. 4 CY 2019 changing the total project cost to P600,000.00 |  | AC
81 | [6 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | AC
[7 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | AC
[7 empty] | d) | - | d) | - | [12 empty] | AC
| Const. of Water System, San Agustin, Tagum City |  | 20% DF CY 2019 (STIMULUS) | Water System | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Re-aligned to other stimulus projects that need additional funds since there is no deed of donation for the proposed site. |  | 1
82 | [6 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[7 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[7 empty] | d) | - | d) | - | [12 empty] | 1
| Const. of Brgy. Health Center, Magugpo South, Tagum City |  | 20% DF CY 2019 (STIMULUS) | Bldg. | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Bidding Documents for posting |  | 1
83 | [6 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[7 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[7 empty] | d) | - | d) | - | [12 empty] | 2
| Const. of Women Livelihood Center, San Isidro, Tagum City |  | 20% DF CY 2019 (STIMULUS) | Bldg. | sq.m | Admin | a) | 500000 | a) | 2019-05-29 | e) | 28 CD | a) | 500000 | a) | 91.64% | c) | 91.64% | a) | 5 | On-going (Suspended last April 5, 2020 due to COVID; resumption order dated May 4, 2020) |  | AC
84 | [6 empty] | b) | Juan | b) | 2020-01-02 | f) | 27 CD | b) | 500000 | b) | - | d) | - | b) | 95 |  |  | 2
[7 empty] | c) | PEO | c) | 2020-03-21 | g) |  | c) | 458200 | [8 empty] | 2
[7 empty] | d) | 80 CD | d) | 2020-06-12 | [12 empty] | 2
| Rehab. Of Brgy. Health Center, Apokon, Tagum City |  | 20% DF CY 2019 (STIMULUS) | Bldg. | - | - | a) | 500000 | a) | 2019-03-25 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For implementation (The brgy. council agreed not to pursue with the project if it will not be completed and needs additional funds) |  | 2
85 | [6 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 2
[7 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 2
[7 empty] | d) | - | d) | - | [12 empty] | 1
| Rehab. of Evacuation Center, Mankilam, Tagum City |  | 20% DF CY 2019 (STIMULUS) | Bldg. | - | - | a) | 500000 | a) | 2019-03-25 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For implementation |  | 1
86 | [6 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[7 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[7 empty] | d) | - | d) | - | [12 empty] | 1
1
| Rehab. of Evacuation Center, New Balambam, Tagum City |  | 20% DF CY 2019 (STIMULUS) | Bldg. | sq.m | Contract | a) | 500000 | a) | 2019-09-10 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Final abstract #0320200899 (JJR Construction & Supply) |  | 1
87 | [6 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[7 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[7 empty] | d) | - | d) | - | [12 empty] | AC
| Rehab. Of Multi-Purpose Hall, Cuambogan, Tagum City |  | 20% DF CY 2019 (STIMULUS) | Bldg. | sq.m | Contract | a) | 500000 | a) | 2019-09-10 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Purchase Order # 19083071 (Post Qualification on process) |  | AC
88 | [6 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | AC
[7 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | AC
[7 empty] | d) | - | d) | - | [12 empty] | 1
| Completion of Evacuation Center, Nueva Fuerza, Tagum City |  | 20% DF CY 2019 (STIMULUS) | Bldg. | sq.m | Contract | a) | 500000 | a) | 2019-09-10 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Purchase Order # 19083071 (Post Qualification on process) |  | AC
89 | [6 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[7 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[7 empty] | d) | - | d) | - | [12 empty] | 1
| Completion. of Water System , Busaon, Tagum City |  | 20% DF CY 2019 (STIMULUS) | Water System | Households | Contract | a) | 500000 | a) | 2019-09-10 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | For implementation |  | 2
90 | [6 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[7 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[7 empty] | d) | - | d) | - | [12 empty] | AC
| Const. of Drainage Canal, Bincungan, Tagum City |  | 20% DF CY 2019 (STIMULUS) | Drainage | sq.m | Contract | a) | 500000 | a) | 2019-09-10 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Purchase Order # 19083071 (Post Qualification on process) |  | 1
91 | [6 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[7 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[7 empty] | d) | - | d) | - | [12 empty] | 1
| Rehab. of Evacuation Center, Magugpo North, Tagum City |  | 20% DF CY 2019 (STIMULUS) | Bldg. | sq.m | Contract | a) | 500000 | a) | 2019-09-10 | e) | - | a) | 500000 | a) | - | c) | - | a) |  | Purchase Order # 19083071 (Post Qualification on process)
92 | [6 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | FS
[7 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | AC
[7 empty] | d) | - | d) | - | [12 empty] | 1
| SAN ISIDRO | [21 empty] | 1
| Rehab. Of Water System at Purok Cabang & Mangga , Pinamuno, San Isidro |  | 20% DF CY 2019 (STIMULUS) | Water System | Households | Contract | a) | 500000 | a) | 2019-12-06 | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Purchase Order # 2020010025 (RLHV) |  | FS
93 | [6 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[7 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | AC
[7 empty] | d) | - | d) | - | [12 empty] | 1
| Rehab. Of Water System , Igangon, San Isidro |  | 20% DF CY 2019 (STIMULUS) | Water System | Households | Contract | a) | 500000 | a) | 2019-05-29 | e) | - | a) | 500000 | a) | 12.26% | c) | 20.13% | a) | 7 | On-going |  | 1
94 | [6 empty] | b) | Kabinge | b) | 2020-05-18 | f) | - | b) | 500000 | b) | - | d) | - | b) | 60 |  |  | 1
[7 empty] | c) | PEO | c) | 2020-06-17 | g) | - | c) | - | [8 empty] | 1
[7 empty] | d) | 60 CD | d) | - | [12 empty] | 1
| RURAL ELECTRIFICATION PROJECT (Provincewide) LS - P5,000,000.00 | [21 empty] | AC
| Rural Electrification , Del Monte, New Corella |  | 20% DF CY 2019 (STIMULUS) | Elect. | - | - | a) | 3000000 | a) | - | e) | - | a) | 3000000 | a) | - | c) | - | a) | - | For implementation |  | 1
95 | [6 empty] | b) | P.Bueno | b) | - | f) | - | b) | 3000000 | b) | - | d) | - | b) | - |  |  | 1
[7 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[7 empty] | d) | - | d) | -
| Rural Electrification at St. Bundok, San Roque, New Corella |  | 20% DF CY 2019 (STIMULUS) | Elect. | - | - | a) | 1000000 | a) | - | e) | - | a) | 1000000 | a) | - | c) | - | a) | - | Draft abstract # 0320201453 |  | AC
96 | [6 empty] | b) | P.Bueno | b) | - | f) | - | b) | 1000000 | b) | - | d) | - | b) | - |  |  | 1
[7 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[7 empty] | d) | - | d) | - | [12 empty] | 1
| Anti - Crime & Government Itegration Project |  |  | Bldg. | - | - | [14 empty] | Date of procurement June 30, 2020 |  | AC
| Construction of Bahay Silangan for Reformation of Drug Personalities within The Military Camp/barracks, Brgy. Mankilam, Tagum City |  | 20% DF CY 2019 |  |  |  | a) | 5000000 | a) | - | e) | - | a) | 5000000 | a) | - | c) | - | a) | -
97 | [6 empty] | b) | - | b) | - | f) | - | b) | 5000000 | b) | - | d) | - | b) | - |  |  | 1
[7 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[7 empty] | d) | - | d) | - | [12 empty] | 1
| SOCIAL WELFARE AND DEVELOPMENT | [21 empty] | AC
| Special Protection & Intervention Program | [21 empty] | 1
| Const. of Multi-Purpose Covered Court/Evacuation Center Ph. I, Duterte St., Poblacion, New Corella |  | 20% DF CY 2019 | Bldg. | sq.m | - | a) | 2000000 | a) | - | e) | - | a) | 2000000 | a) | - | c) | - | a) | - | For Purchase Request |  | 1
98 | [6 empty] | b) | - | b) | - | f) | - | b) | 2000000 | b) | - | d) | - | b) | - |  |  | 1
[7 empty] | c) | PEO | c) | - | g) | - | c) | - | [8 empty] | 1
[7 empty] | d) | - | d) | -
| Residential Care Facilities | [21 empty] | 1
| Construction of Multi-Purpose Covered Court/Evacuation, Bahay Pag-Asa, New Corella, Ph.II (TF - P500,000.00) |  | 20% DF CY 2019 & TRUST FUND | Bldg. | sq.m | Admin | a) | 2500000 | a) | 2019-06-19 | e) | 28 CD | a) | 2500000 | a) | 60.41% | c) | 60.41% | a) | 12 | On-going (Suspended last April 5, 2020 due to COVID; resumption order dated May 4, 2020)
99 | [6 empty] | b) | Mayang | b) | 2019-12-02 | f) | 28 CD | b) | 2500000 | b) | - | d) | - | b) | 360 |  |  | AC
[7 empty] | c) | PEO | c) | 2020-03-09 | g) | - | c) | - | [8 empty] | 1
[7 empty] | d) | 135 CD | d) | 2020-07-25 | [12 empty] | 1
| Const. in Progress - Bldgs. And Other Structures |  | 20% DF CY 2019 | Bldg. | sq.m | - | a) | 2500000 | a) | - | e) | - | a) | 2500000 | a) | - | c) | - | a) | - | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. |  | AC
100 | [6 empty] | b) | - | b) | - | f) | - | b) | 2500000 | b) | - | d) | - | b) | - |  |  | 1
[7 empty] | c) | PEO | c) | - | g) | - | c) | - | [8 empty] | 1
[7 empty] | d) | - | d) | - | [12 empty] | 1
| DISASTER PREVENTION AND MITIGATION | [21 empty] | 1
| - Flood Control and Slope Protection | [21 empty] | 1
| Desiltation/Excavation of rivers and creeks | [21 empty] | 1
| LS - P3,000,000.00 | [21 empty] | AC
| Desilting of Limbaan Creek, New Corella |  | 5% CALAMITY FUND CY 2019 | creeks and canals deislted | ln.m | Admin | a) | 2000000 | a) | - | e) | - | a) | 2000000 | a) | - | c) | - | a) | - | Purchase Order # 2019124324 - Digos Constrak; PO # 2019124231 - Diocesan |  | 1
101 | [6 empty] | b) | - | b) | - | f) | - | b) | 2000000 | b) | - | d) | - | b) | - |  |  | AC
[7 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[7 empty] | d) | - | d) | - | [12 empty] | 1
| - Revitment of Dike and Slope Protection | [21 empty] | 1
| LS - P3,000,000.00 | [21 empty] | AC
| Slope Protection Along Kapalong-Mabantao, Florida |  | 5% CALAMITY FUND CY 2019 | creeks and canals deislted | - | - | a) | 1000000 | a) | - | e) | - | a) | 1000000 | a) | - | c) | - | a) | - | For cancellation funded to DPWH. Budget Transferred to 5% Calamity Fund- Rehab and Recovery |  | 1
102 | [6 empty] | b) | - | b) | - | f) | - | b) | 1000000 | b) | - | d) | - | b) | - |  |  | AC
[7 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[7 empty] | d) | - | d) | - | [12 empty] | 1
| - Improvement of bridges and cross drainage LS - P3,000,000.00 | [21 empty] | 1
| Impv't. of Jct. New Boholano - New Loon Cross Drainage |  | 5% CALAMITY FUND CY 2019 | Drainage | - | - | a) | 2000000 | a) | - | e) | - | a) | 2000000 | a) | - | c) | - | a) | - | POW preparation on going c/o PEO-PDPM. Insufficient budget to complete required works for the project |  | 1
103 | [6 empty] | b) | - | b) | - | f) | - | b) | 2000000 | b) | - | d) | - | b) | - |  |  | 1
[7 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[7 empty] | d) | - | d) | - | [12 empty] | 1
| Impv't. of Jct. Saug-Sonlon-Bdry. Longanapan Cross Drainage |  | 5% CALAMITY FUND CY 2019 | Road | - | - | a) | 1000000 | a) | - | e) | - | a) | 1000000 | a) | - | c) | - | a) | - | For implementation |  | AC
104 | [6 empty] | b) | - | b) | - | f) | - | b) | 1000000 | b) | - | d) | - | b) | - |  |  | 1
[7 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[7 empty] | d) | - | d) | - | [12 empty] | AC
| DISASTER REHABILITATION & RECOVERY PROGRAM - Building Back Better Project | [21 empty] | 1
| Disiltation of Tagum Creek |  | 5% CALAMITY FUND CY 2019 | Creek | ln.m | Admin | a) | 2000000 | a) | - | e) | - | a) | 2000000 | a) | - | c) | - | a) | - | Waiting for the delivery of materials |  | AC
105 | [6 empty] | b) | - | b) | - | f) | - | b) | 2000000 | b) | - | d) | - | b) | - |  |  | 1
[7 empty] | c) | PEO | c) | - | g) | - | c) | - | [8 empty] | 1
[7 empty] | d) | - | d) | - | [12 empty] | AC
| Rehabilitation of Pamacaun-Lasang-Banate Provincial Road |  | 5% CALAMITY FUND CY 2019 | Road | km | Admin | a) | 1500000 | a) | - | e) | - | a) | 1500000 | a) | - | c) | - | a) | - | For implementation |  | 1
106 | [6 empty] | b) | - | b) | - | f) | - | b) | 1500000 | b) | - | d) | - | b) | - |  |  | 1
[7 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[7 empty] | d) | - | d) | - | [12 empty] | 1
| Rehabilitation of Del Pilar Jct. Silangan |  | 5% CALAMITY FUND CY 2019 | Road | km | Admin | a) | 1500000 | a) | 2019-07-26 | e) | 29 CD | a) | 1500000 | a) | 81.11% | c) | 81.11% | a) | 4 | On-going (Suspended last April 5, 2020 due to COVID; resumption order dated May 4, 2020) |  | 1
107 | [6 empty] | b) | Gone | b) | 2020-02-17 | f) | 51 CD | b) | 1500000 | b) | - | d) | - | b) | 40 |  |  | AC
[7 empty] | c) | PEO | c) | 2020-03-27 | g) | - | c) | - | [8 empty] | 1
[7 empty] | d) | 40 CD | d) | 2020-06-15 | [12 empty] | 1
| Rehab. Of Canal Lining and Slope Protection (Installation of 72" dia RCPC x 4M at San Agustin ES) |  | 5% CALAMITY FUND CY 2019 | Drainage | ln.m | Admin | a) | 350000 | a) | - | e) | - | a) | 350000 | a) | - | c) | - | a) | - | Procurement on process |  | 1
108 | [6 empty] | b) | - | b) | - | f) | - | b) | 350000 | b) | - | d) | - | b) | - |  |  | AC
[7 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[7 empty] | d) | - | d) | - | [12 empty] | 1
| Rehabilitation of Libuganon River along Kapalong Mabantao-Florida Provincial Road |  | 5% CALAMITY FUND CY 2019 | Road | km | Admin | a) | 900000 | a) | - | e) | - | a) | 900000 | a) | - | c) | - | a) | - | For implementation |  | 1
109 | [6 empty] | b) | - | b) | - | f) | - | b) | 900000 | b) | - | d) | - | b) | - |  |  | AC
[7 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[7 empty] | d) | - | d) | - | [12 empty] | 1
| Rehabilitation of Mesaoy-Jct. Mahayahay Road |  | 5% CALAMITY FUND CY 2019 | Road | km | Admin | a) | 1000000 | a) | - | e) | - | a) | 1000000 | a) | - | c) | - | a) | - | For implementation |  | 1
110 | [6 empty] | b) | - | b) | - | f) | - | b) | 1000000 | b) | - | d) | - | b) | - |  |  | AC
[7 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[7 empty] | d) | - | d) | - | [12 empty] | 1
| Rehabilitation of Sta. Fe- Mambing Road & Slope Protection |  | 5% CALAMITY FUND CY 2019 | Road | km | Admin | a) | 1320000 | a) | - | e) | - | a) | 1320000 | a) | - | c) | - | a) | - | Materials RE-PR |  | 1
111 | [6 empty] | b) | - | b) | - | f) | - | b) | 1320000 | b) | - | d) | - | b) | - |  |  | AC
[7 empty] | c) | - | c) | - | g) |  | c) | - | [8 empty] | 1
[7 empty] | d) | - | d) | - | [12 empty] | 1
| Rehabilitation of Canal Lining and Slope Protection at San Agustin E/S, San Agustin, Tagum City |  | 5% CALAMITY FUND CY 2019 | Drainage | ln.m | Admin | a) | 350000 | a) | - | e) | - | a) | 350000 | a) | - | c) | - | a) | - | Pending due to for cancellation of previous project. |  | 1
112 | [6 empty] | b) | - | b) | - | f) | - | b) | 350000 | b) | - | d) | - | b) | - |  |  | AC
[7 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[7 empty] | d) | - | d) | - | [12 empty] | 1
TRUST FUND PROPER CY 2019
| Construction of Halfway House, Brgy. Doña Andrea, Asuncion |  | DILG | Bldg. | sq.m | Admin | a) | 5000000 | a) | CY 2019 | e) | 28 CD | a) | 5000000 | a) | 20.12% | c) | 20.12% | a) | 6 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) |  | 1
112 | [6 empty] | b) | Dadula | b) | 2020-02-17 | f) | - | b) | 5000000 | b) | - | d) | - | b) | 138 |  |  | 1
[7 empty] | c) | PEO | c) | 2020-08-15 | g) | - | c) | - | [8 empty] | AC
[7 empty] | d) | 193 CD | d) | 2020-09-12 | [12 empty] | 1
| Purchase of Lot for Cemetery, Cambanogoy, Asuncion |  | SUPPLEMENTAL BUDGET NO. 1 CY 2019 | Land | - | - | a) | 1500000 | a) | - | e) | - | a) | 1500000 | a) | - | c) | - | a) | - | Documents for fund transfer to be complied by the LGUs. Letter sent dated June 18, 2019 |  | 1
113 | [6 empty] | b) | - | b) | - | f) | - | b) | 1500000 | b) | - | d) | - | b) | - |  |  | 1
[7 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | AC
[7 empty] | d) | - | d) | - | [12 empty] | 1
| Purchase of Lot for Cemetery, San Roque, New Corella |  | SUPPLEMENTAL BUDGET NO. 1 CY 2019 | Land | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Documents for fund transfer to be complied by the LGUs. Letter sent dated June 18, 2019 |  | 1
114 | [6 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[7 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | AC
[7 empty] | d) | - | d) | - | [12 empty] | 1
| Rehab/Impvt of Gymnasium, Sagayen, Asuncion |  | SUPPLEMENTAL BUDGET NO. 1 CY 2019 (STIMULUS) | Bldg | sq.m | - | a) | 1500000 | a) | - | e) | - | a) | 1500000 | a) | - | c) | - | a) | - | Final Abstract # 0320200900 (Alpebel Builders & Supply Corp.) |  | 1
115 | [6 empty] | b) | - | b) | - | f) | - | b) | 1500000 | b) | - | d) | - | b) | - |  |  | AC
[7 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[7 empty] | d) | - | d) | - | [12 empty] | 1
| Purchase of Lot for Resettlement Site, New Sambog, New Corella |  | SUPPLEMENTAL BUDGET NO. 1 CY 2019 (STIMULUS) | Land | - | - | a) | 1500000 | a) | - | e) | - | a) | 1500000 | a) | - | c) |  | a) | - | for fund transfer. Waiting for LGU documents. Liquidation of previous fund transfer for the water system project of LGU. |  | 1
116 | [6 empty] | b) | - | b) | - | f) | - | b) | 1500000 | b) | - | d) | - | b) | - |  |  | 1
[7 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | FS
[7 empty] | d) | - | d) | -
| Installation of Street Lights at Prk 1,2,3,4, Sagayen, Asuncion |  | SUPPLEMENTAL BUDGET NO. 1 CY 2019 (STIMULUS) | Elect. | Households | - | a) | 1000000 | a) | - | e) | - | a) | 1000000 | a) | - | c) |  | a) | - | Purchase Order # 2019113377 (Tagum Builders)
117 | [6 empty] | b) | - | b) | - | f) | - | b) | 1000000 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | - | [12 empty] | 2
| Rehab/Imprvt. Of FMR, Prk 3,7, & 8, Concepcion, Asuncion |  | SUPPLEMENTAL BUDGET NO. 1 CY 2019 (STIMULUS) | Road | km | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) |  | a) | - | Waiting for equipment availability as of Feb. 5, 2020 report submitted by Engr. Cuajao |  | 1
118 | [6 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[7 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[7 empty] | d) | - | d) | - | [12 empty] | 2
| Farm to Market Road, San Jose, New Corella |  | SUPPLEMENTAL BUDGET NO. 1 CY 2019 (STIMULUS) | Road | - | - | a) | 2000000 | a) | - | e) | - | a) | 2000000 | a) | - | c) | - | a) | - | Procurement on process |  | 1
119 | [6 empty] | b) | - | b) | - | f) | - | b) | 2000000 | b) | - | d) | - | b) | - |  |  | 1
[7 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[7 empty] | d) | - | d) | - | [12 empty] | 2
| Const. of Water System, New Sambog, New Corella |  | SUPPLEMENTAL BUDGET NO. 1 CY 2019 (STIMULUS) | Water System | Households | MLGU | a) | 1000000 | a) | - | e) | - | a) | 1000000 | a) | - | c) | - | a) | - | Fund transferred to LGU |  | 1
120 | [6 empty] | b) | - | b) | - | f) | - | b) | 1000000 | b) | - | d) | - | b) | - |  |  | 1
[7 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[7 empty] | d) | - | d) | - | [12 empty] | FS
| Const. of Drainage Canal from Prk. 3, 1-A, 2-A to Prk 1-B, Brgy Site (Ph. 2), Limbaan, New Corella |  | SUPPLEMENTAL BUDGET NO. 1 CY 2019 (STIMULUS) | Flood Control - Drainage | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | POW preparation on going c/o PDPM |  | AC
121 | [6 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | AC
[7 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | AC
[7 empty] | d) | - | d) | - | [12 empty] | AC
| Const. of FMR from Prk 1 to Sitio Magsaysay via Pundol & Prk 4, Patrocenio, New Corella |  | SUPPLEMENTAL BUDGET NO. 1 CY 2019 (STIMULUS) | Road | - | - | a) | 2000000 | a) | - | e) | - | a) | 2000000 | a) | - | c) | - | a) | - | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
122 | [6 empty] | b) | - | b) | - | f) | - | b) | 2000000 | b) | - | d) | - | b) | - |  |  | AC
[7 empty] | c) | - | c) | - | g) |  | c) | - | [8 empty] | 1
[7 empty] | d) | - | d) | - | [12 empty] | 1
| Const. of Multi-Purpose Pavement, San Jose, New Corella |  | SUPPLEMENTAL BUDGET NO. 1 CY 2019 (STIMULUS) | Bldgs | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | POW approved but allotment not yet requested waiting for deed of donation c/o Engr. Canillada |  | 1
123 | [6 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | AC
[7 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[7 empty] | d) | - | d) | - | [12 empty] | 1
| Const. of Multipurpose Covered Court, Buan, Asuncion |  | SUPPLEMENTAL BUDGET NO. 1 CY 2019 (STIMULUS) | Covered Court | sq.m | MLGU | a) | 2500000 | a) | 2019-06-26 | e) | - | a) | 2500000 | a) | - | c) | - | a) | - | Fund transferred to LGU |  | AC
124 | [6 empty] | b) | - | b) | - | f) | - | b) | 2500000 | b) | - | d) | - | b) | - |  |  | 1
[7 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[7 empty] | d) | - | d) | - | [12 empty] | 1
| Const. of Multipurpose Covered Court, Pamacaun, Asuncion |  | SUPPLEMENTAL BUDGET NO. 1 CY 2019 (STIMULUS) | Covered Court | sq.m | MLGU | a) | 2500000 | a) | 2019-05-29 | e) | - | a) | 2500000 | a) | - | c) |  | a) | - | Fund transferred to LGU |  | AC
126 | [6 empty] | b) | - | b) | - | f) | - | b) | 2500000 | b) | - | d) | - | b) | - |  |  | 1
[7 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[7 empty] | d) | - | d) | - | [12 empty] | 1
| Const. of 2 Storey Multi purpose Hall Ph.2 (Brgy. Hall) , Poblacion, New Corella |  | SUPPLEMENTAL BUDGET NO. 1 CY 2019 (STIMULUS) | Bldgs | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. |  | AC
126 | [6 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[7 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[7 empty] | d) | - | d) | - | [12 empty] | 1
| Rehab. Of Multi-Purpose Hall (Evacuation Ctr.) Limbaan, New Corella |  | SUPPLEMENTAL BUDGET NO. 1 CY 2019 (STIMULUS) | Bldgs | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | POW for revision. Change to Contract |  | AC
127 | [6 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[7 empty] | c) | - | c) | - | g) |  | c) | - | [8 empty] | 1
[7 empty] | d) | - | d) | - | [12 empty] | 1
| Expansion of Multi-Purpose Hall ( Brgy. Hall), Patrocenio, New Corella |  | SUPPLEMENTAL BUDGET NO. 1 CY 2019 (STIMULUS) | Bldgs | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Purchase Order # 2020020796 (JJR Construction) |  | AC
128 | [6 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[7 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[7 empty] | d) | - | d) | - | [12 empty] | 1
| Rehabilitation of Water System in PEEDO-LPRRC, Brgy. Poblacion, New Corella |  | SUPPLEMENTAL BUDGET NO. 3 CY 2019 | Water System | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Purchase Order # 2020010009 (ANCOR Water Resources) |  | 1
129 | [6 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | - |  |  | 1
[7 empty] | c) | - | c) | - | g) |  | c) | - | [8 empty] | 1
[7 empty] | d) | - | d) | - | [12 empty] | 2
| Provincial Livestock & Poultry Multiplier Farm Road Network Construction, Sitio Salawao, Sto. Niño, Talaingod |  | SUPPLEMENTAL BUDGET NO. 4 CY 2019 | Conc. Pavement | km | Admin | a) | 5500000 | a) | CY 2019 | e) | - | a) | 5500000 | a) | 11.3% | c) | 16.02% | a) | 10 | On-going |  | 2
130 | [6 empty] | b) | Pasiona/Juan | b) | 2020-06-16 | f) | - | b) | 5500000 | b) | - | d) | - | b) | 300 |  |  | 1
[7 empty] | c) | PEO | c) | 2020-07-13 | g) | - | c) | - | [8 empty] | 1
[7 empty] | d) | 120 CD | d) | - | [12 empty] | 1
| Proposed Road Opening of Tawinian-Tapayanon Road Section |  | SUPPLEMENTAL BUDGET NO. 4 CY 2019 | Road | km | Admin | a) | 10000000 | a) | 2019-11-15 | e) | 28 CD | a) | 10000000 | a) | 18.48% | c) | 18.48% | a) | 5 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) |  | 2
131 | [6 empty] | b) | Garcia | b) | 2019-11-18 | f) | - | b) | 10000000 | b) | - | d) | - | b) | 319 |  |  | 1
[7 empty] | c) | PEO | c) | 2020-09-18 | g) | - | c) | - | [8 empty] | 1
[7 empty] | d) | - | d) | 2020-10-16 | [12 empty] | 1
| Completion of Brgy. Health Center, Maniki, Kapalong |  | SUPPLEMENTAL BUDGET NO. 4 CY 2019 | Bldg. | - | - | a) | 627000 | a) | - | e) | - | a) | 627000 | a) | - | c) | - | a) | - | PROJECT Was funded by LGU, Kapalong |  | 1
132 | [6 empty] | b) | - | b) | - | f) | - | b) | 627000 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[7 empty] | d) | - | d) | - | [12 empty] | 2
| Construction of Potable Water System at Purok 6, New Santiago, Asuncion |  | SUPPLEMENTAL BUDGET NO. 4 CY 2019 | Water System | Households | contract | a) | 1000000 | a) | - | e) | - | a) | 1000000 | a) | - | c) | - | a) | - | Change of POW to Contract
133 | [6 empty] | b) | - | b) | - | f) | - | b) | 1000000 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
| Construction of Children's Playground with Amenities, Poblacion, New Corella |  | SUPPLEMENTAL BUDGET NO. 4 CY 2019 | Bldg. | sq.m | Admin | a) | 2500000 | a) | 2019-12-06 | e) | 28 CD | a) | 2500000 | a) | 37.69% | c) | 41.17% | a) | 10 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020)
134 | [6 empty] | b) | Mayang | b) | 2019-11-25 | f) | 30 CD | b) | 2500000 | b) | - | d) | - | b) | 290
[7 empty] | c) | PEO | c) | 2020-03-03 | g) | - | c) | 1029250
[7 empty] | d) | 129 CD | d) | -
CONSTRUCTION IN PROGRESS - Bldgs. & Other Structures
| Rehabilitation of Evacuation Center at Magugpo Pob., Tagum City |  | SUPPLEMENTAL BUDGET NO. 4 CY 2019 (STIMULUS) | Bldg. | sq.m | - | a) | 600000 | a) | - | e) | - | a) | 600000 | a) | - | c) | - | a) | - | Purchase Order # 2020020796 (JJR Construction)
135 | [6 empty] | b) | - | b) | - | f) | - | b) | 600000 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
| Construction of Brgy. Health Center at Magugpo South, Tagum City |  | SUPPLEMENTAL BUDGET NO. 4 CY 2019 (STIMULUS) | Bldg. | sq.m | - | a) | 1550000 | a) | - | e) | - | a) | 1550000 | a) | - | c) | - | a) | - | Bidding Documents for Posting
136 | [6 empty] | b) | - | b) | - | f) | - | b) | 1550000 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
| Const. of Multipurpose Covered Court Ph.II, Pamacaun, Asuncion |  | SUPPLEMENTAL BUDGET NO. 4 CY 2019 (STIMULUS) | Covered Court | sq.m | MLGU | a) | 474515.23 | a) | 2019-05-29 | e) | - | a) | 474515.23 | a) | - | c) |  | a) | - | Bidding Documents for Posting |  | AC
125 | [6 empty] | b) | - | b) | - | f) | - | b) | 474515.23 | b) | - | d) | - | b) | - |  |  | 1
[7 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | 1
[7 empty] | d) | - | d) | - | [12 empty] | 1
| Rehab. Of Multi-Purpose Building (Evacuation Center), Limbaan, New Corella |  | SUPPLEMENTAL BUDGET NO. 4 CY 2019 (STIMULUS) | Bldg. | sq.m | - | a) | 600000 | a) | - | e) | - | a) | 600000 | a) | - | c) | - | a) | - | Procurement on process
137 | [6 empty] | b) | - | b) | - | f) | - | b) | 600000 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | - | [8 empty] | FS
[7 empty] | d) | - | d) | -
| Improvement of Km. 9 Sagayen-Sawata Provincial Road, San Isidro, Ph. II |  | SUPPLEMENTAL BUDGET NO. 4 CY 2019 (STIMULUS) | Road | km | Admin | a) | 4591029 | a) | 2019-12-12 | e) | - | a) | 4591029 | a) | 45% | c) | 35.05% | a) | 6 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020)
138 | [6 empty] | b) | Limpo | b) | 2019-09-09 | f) | - | b) | 4591029 | b) | - | d) | - | b) | 138
[7 empty] | c) | PEO | c) | 2020-03-27 | g) | - | c) | 1609155.6645 | [8 empty] | FS
[7 empty] | d) | 200 CD | d) | -
| Poultry House and Training Center Sto. Niño, Talaingod |  | PROJECTS FOR PROVINCIAL VETERINARY | Bldg. | sq.m | Contract | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Final Abstract # 012020012
139 | [6 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
| Establishment of Livestock and Poultry Mutiplier Farm, Sitio Salawao, Sto. Niño, Talaingod |  | Department of Agriculture - Regional Field Office XI | - | - | - | a) | 600000 | a) | - | e) | - | a) | 600000 | a) | - | c) | - | a) | - | Final Abstract # 012020012
140 | [6 empty] | b) | - | b) | - | f) | - | b) | 600000 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
| Road Upgrading of Kapalong - Mabantao - Florida Road with Bridge Component |  | CMGP CY 2019 | Concreting | km. | Contract | a) | 15,435,008.00 | a) | CY 2019 | e) | 30 CD | a) | 15,435,008.00 | a) | 100% | c) | 78.93% | a) | 19 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) |  | FS
141 | [6 empty] | b) | Japay/Quirante | b) | 2019-10-16 | f) | 20 CD | b) | 15,435,008.00 | b) | 81.81% | d) |  | b) | 551 |  |  | FS
[7 empty] | c) | LEGACY | c) | 2020-03-10 | g) | - | c) | 6,174,003.20
[7 empty] | d) | 147 CD | d) | 2020-04-24
| Rehabilitation of Dasing to Monte Carlo FMR, Del Pilar, New Corella |  | LGSF CY 2019 | Concreting | km. | Contract | a) | 40000000 | a) | - | e) | - | a) | 40000000 | a) | - | c) | - | a) | - | For implementation
142 | [6 empty] | b) | - | b) | - | f) | - | b) | 40000000 | b) | - | d) | - | b) | -
[7 empty] | c) | Rely Const. | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
| Concreting of Visayan Village - Purok exodus - Purok Rafael, Brgy. Magugpo South, Tagum City |  | LGSF CY 2019 | Concreting | km. | Contract | a) | 40000000 | a) | - | e) | - | a) | 40000000 | a) | - | c) | - | a) | - | For implementation
143 | [6 empty] | b) | - | b) | - | f) | - | b) | 40000000 | b) | - | d) | - | b) | -
[7 empty] | c) | Legacy Const. Corp. | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
II. PROJECTS UNDER THE CURRENT APPROPRIATION
REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM)
| ROAD ID 001 - Jct. Highway Magatos - New Bantayan |  | GENERAL FUND CY 2020 | MBA | 7.1 | Admin | a) | 564839.9739 | a) | 2020-01-02 | e) | 27 CD | a) | 564839.9739 | a) | 19.63% | c) | 19.63% | a) | 17 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020)
1 | [6 empty] | b) | Crucio | b) | 2020-01-02 | f) | - | b) | 564839.9739 | b) | - | d) | - | b) | 374
[7 empty] | c) | PEO | c) | 2020-12-31 | g) | - | c) | 57334.17
[7 empty] | d) | 365 CD | d) | -
| ROAD ID 001 - Jct. Highway Magatos - New Bantayan |  | GENERAL FUND CY 2020 | CBRMC | 7.1 | Contract | a) | 230737.1976 | a) | - | e) | - | a) | 230737.1976 | a) | - | c) | - | a) | - | Purchase Request # 19125305 (On process)
2 | [6 empty] | b) | - | b) | - | f) | - | b) | 230737.1976 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
| ROAD ID 002 - Magatos - Bdry. Pagsabangan |  | GENERAL FUND CY 2020 | MBA | 8.33 | Admin | a) | 653221.626 | a) | 2020-01-02 | e) | 27 CD | a) | 653221.626 | a) | 17.87% | c) | 17.87% | a) | 17 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020)
3 | [6 empty] | b) | Crucio | b) | 2020-01-02 | f) | - | b) | 653221.626 | b) | - | d) | - | b) | 374
[7 empty] | c) | PEO | c) | 2020-12-31 | g) | - | c) | 71713.44
[7 empty] | d) | 365 CD | d) | -
| ROAD ID 002 - Magatos - Bdry. Pagsabangan |  | GENERAL FUND CY 2020 | CBRMC | 8.33 | Contract | a) | 280,180.88 | a) | - | e) | - | a) | 280,180.88 | a) | - | c) | - | a) | - | Purchase Request # 19125306 (On process)
4 | [6 empty] | b) | - | b) | - | f) | - | b) | 280,180.88 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
| ROAD ID 003 - Ilog - New Bantayan |  | GENERAL FUND CY 2020 | MBA | 2.68 | Admin | a) | 236174.847 | a) | 2020-01-02 | e) | 27 CD | a) | 236174.847 | a) | 11.64% | c) | 11.64% | a) | 17 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020)
5 | [6 empty] | b) | Crucio | b) | 2020-01-02 | f) | - | b) | 236174.847 | b) | - | d) | - | b) | 374
[7 empty] | c) | PEO | c) | 2020-12-31 | g) | - | c) | 22629.74
[7 empty] | d) | 365 CD | d) | -
| ROAD ID 003 - Ilog - New Bantayan |  | GENERAL FUND CY 2020 | CBRMC | 2.68 | Contract | a) | 70633.836 | a) | - | e) | - | a) | 70633.836 | a) | - | c) | - | a) | - | Purchase Request # 19125307 (On process)
6 | [6 empty] | b) | - | b) | - | f) | - | b) | 70633.836 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
| ROAD ID 005 - Asuncion - Monte Carlo - Del Pilar |  | GENERAL FUND CY 2020 | MBA | 9.93 | Admin | a) | 716344.9167 | a) | 2020-01-02 | e) | 27 CD | a) | 716344.9167 | a) | 20.71% | c) | 20.71% | a) | 17 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020)
7 | [6 empty] | b) | Crucio | b) | 2020-01-02 | f) | - | b) | 716344.9167 | b) | - | d) | - | b) | 374
[7 empty] | c) | PEO | c) | 2020-12-31 | g) | - | c) | 84301.23
[7 empty] | d) | 365 CD | d) | -
| ROAD ID 005 - Asuncion - Monte Carlo - Del Pilar |  | GENERAL FUND CY 2020 | CBRMC | 9.93 | Contract | a) | 360232.5636 | a) | - | e) | - | a) | 360232.5636 | a) | - | c) | - | a) | - | Purchase Request # 19125308 (On process)
8 | [6 empty] | b) | - | b) | - | f) | - | b) | 360232.5636 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
| ROAD ID 006 - Jct. Highway Canatan - Magatos |  | GENERAL FUND CY 2020 | MBA | 4.85 | Admin | a) | 391296.517 | a) | 2020-01-02 | e) | 27 CD | a) | 391296.517 | a) | 17.81% | c) | 17.81% | a) | 17 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020)
9 | [6 empty] | b) | Crucio | b) | 2020-01-02 | f) | - | b) | 391296.517 | b) | - | d) | - | b) | 374
[7 empty] | c) | PEO | c) | 2020-12-31 | g) | - | c) | 33056.21
[7 empty] | d) | 365 CD | d) | -
| ROAD ID 006 - Jct. Highway Canatan - Magatos |  | GENERAL FUND CY 2020 | CBRMC | 4.85 | Contract | a) | 164812.284 | a) | - | e) | - | a) | 164812.284 | a) | - | c) | - | a) | - | Purchase Request # 19125309 (On process)
10 | [6 empty] | b) | - | b) | - | f) | - | b) | 164812.284 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
| ROAD ID 010 - Saug - Sonlon - Bdry. Longanapan |  | GENERAL FUND CY 2020 | MBA | 11.6 | Admin | a) | 1102041.4797 | a) | 2020-01-02 | e) | 27 CD | a) | 1102041.4797 | a) | 15.76% | c) | 15.76% | a) | 17 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020)
11 | [6 empty] | b) | Crucio | b) | 2020-01-02 | f) | - | b) | 1102041.4797 | b) | - | d) | - | b) | 374
[7 empty] | c) | PEO | c) | 2020-12-31 | g) | - | c) | 83166.18
[7 empty] | d) | 365 CD | d) | -
| ROAD ID 010 - Saug - Sonlon - Bdry. Longanapan |  | GENERAL FUND CY 2020 | CBRMC | bahay | Contract | a) | 197774.7408 | a) | - | e) | - | a) | 197774.7408 | a) | - | c) | - | a) | - | Purchase Request # 19125310 (On process)
12 | [6 empty] | b) | - | b) | - | f) | - | b) | 197774.7408 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
| ROAD ID 011 - Jct. New Visayas - Buan |  | GENERAL FUND CY 2020 | MBA | 2.99 | Admin | a) | 134598.4525 | a) | 2020-01-02 | e) | 27 CD | a) | 134598.4525 | a) | 7.72% | c) | 7.72% | a) | 17 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020)
13 | [6 empty] | b) | Crucio | b) | 2020-01-02 | f) | - | b) | 134598.4525 | b) | - | d) | - | b) | 374
[7 empty] | c) | PEO | c) | 2020-12-31 | g) | - | c) | 10391.0005
[7 empty] | d) | 365 CD | d) | -
| ROAD ID 011 - Jct. New Visayas - Buan |  | GENERAL FUND CY 2020 | CBRMC | 2.99 | Contract | a) | 124786.4436 | a) | - | e) | - | a) | 124786.4436 | a) | - | c) | - | a) | - | Purchase Request # 19125311 (On process)
14 | [6 empty] | b) | - | b) | - | f) | - | b) | 124786.4436 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
| ROAD ID 013 - San Vicente - Butay |  | GENERAL FUND CY 2020 | MBA | 7.52 | Admin | a) | 579541.5407 | a) | 2020-01-02 | e) | 27 CD | a) | 579541.5407 | a) | 21.33% | c) | 21.33% | a) | 17 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020)
15 | [6 empty] | b) | Crucio | b) | 2020-01-02 | f) | - | b) | 579541.5407 | b) | - | d) | - | b) | 374
[7 empty] | c) | PEO | c) | 2020-12-31 | g) | - | c) | 123616.2106
[7 empty] | d) | 365 CD | d) | -
| ROAD ID 013 - San Vicente - Butay |  | GENERAL FUND CY 2020 | CBRMC | 7.52 | Contract | a) | 235446.12 | a) | - | e) | - | a) | 235446.12 | a) | - | c) | - | a) | - | Purchase Request # 19125312 (On process)
16 | [6 empty] | b) | - | b) | - | f) | - | b) | 235446.12 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
| ROAD ID 014 - Jct. Highway Doña Andrea - Capungagan |  | GENERAL FUND CY 2020 | MBA | 8.7 | Admin | a) | 675845.5865 | a) | 2020-01-02 | e) | 27 CD | a) | 675845.5865 | a) | 11.14% | c) | 11.14% | a) | 17 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020)
17 | [6 empty] | b) | Crucio | b) | 2020-01-02 | f) | - | b) | 675845.5865 | b) | - | d) | - | b) | 374
[7 empty] | c) | PEO | c) | 2020-12-31 | g) | - | c) | 75289.1983
[7 empty] | d) | 365 CD | d) | -
| ROAD ID 014 - Jct. Highway Doña Andrea - Capungagan |  | GENERAL FUND CY 2020 | CBRMC | 8.7 | Contract | a) | 299016.5724 | a) | - | e) | - | a) | 299016.5724 | a) | - | c) | - | a) | - | Purchase Request # 19125313 (On process)
18 | [6 empty] | b) | - | b) | - | f) | - | b) | 299016.5724 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
| ROAD ID 015 - Pamacaun - Lasang - Banate |  | GENERAL FUND CY 2020 | MBA | 4.11 | Admin | a) | 180747.1933 | a) | 2020-01-02 | e) | 27 CD | a) | 180747.1933 | a) | 8.6% | c) | 8.6% | a) | 17 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020)
19 | [6 empty] | b) | Crucio | b) | 2020-01-02 | f) | - | b) | 180747.1933 | b) | - | d) | - | b) | 374
[7 empty] | c) | PEO | c) | 2020-12-31 | g) | - | c) | 15544.2586
[7 empty] | d) | 365 CD | d) | -
| ROAD ID 015 - Pamacaun - Lasang - Banate |  | GENERAL FUND CY 2020 | CBRMC | 4.11 | Contract | a) | 129495.366 | a) | - | e) | - | a) | 129495.366 | a) | - | c) | - | a) | - | Purchase Request # 19125314 (On process)
20 | [6 empty] | b) | - | b) | - | f) | - | b) | 129495.366 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
| ROAD ID 018 - Semong - Palma Gil |  | GENERAL FUND CY 2020 | MBA | 2.73 | Admin | a) | 198604.0889 | a) | 2020-01-02 | e) | 27 CD | a) | 198604.0889 | a) | 18.11% | c) | 18.11% | a) | 17 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020)
21 | [6 empty] | b) | Crucio | b) | 2020-01-02 | f) | - | b) | 198604.0889 | b) | - | d) | - | b) | 374
[7 empty] | c) | PEO | c) | 2020-12-31 | g) | - | c) | 35967.2005
[7 empty] | d) | 365 CD | d) | -
| ROAD ID 018 - Semong - Palma Gil |  | GENERAL FUND CY 2020 | CBRMC | 2.73 | Contract | a) | 77697.2196 | a) | - | e) | - | a) | 77697.2196 | a) | - | c) | - | a) | - | Purchase Request # 19125315 (On process)
22 | [6 empty] | b) | - | b) | - | f) | - | b) | 77697.2196 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
| ROAD ID 020 - Daligdigon-Dagohoy |  | GENERAL FUND CY 2020 | MBA | 3.34 | Admin | a) | 84129.1818 | a) | 2020-01-02 | e) | 27 CD | a) | 84129.1818 | a) | 8.6% | c) | 8.6% | a) | 17 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020)
23 | [6 empty] | b) | Crucio | b) | 2020-01-02 | f) | - | b) | 84129.1818 | b) | - | d) | - | b) | 374
[7 empty] | c) | PEO | c) | 2020-12-31 | g) | - | c) | 7235.1096
[7 empty] | d) | 365 CD | d) | -
| ROAD ID 020 - Daligdigon-Dagohoy |  | GENERAL FUND CY 2020 | CBRMC | 3.34 | Contract | a) | 77697.2196 | a) | - | e) | - | a) | 77697.2196 | a) | - | c) | - | a) | - | Purchase Request # 19125315 (On process)
24 | [6 empty] | b) | - | b) | - | f) | - | b) | 77697.2196 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
| ROAD ID 021 - Angelo - Dagohoy |  | GENERAL FUND CY 2020 | MBA | 2.19 | Admin | a) | 27260.2474 | a) | 2020-01-02 | e) | - | a) | 27260.2474 | a) | - | c) | - | a) | - | For implementation
25 | [6 empty] | b) | Crucio | b) | - | f) | - | b) | 27260.2474 | b) | - | d) | - | b) | -
[7 empty] | c) | PEO | c) | - | g) | - | c) | -
[7 empty] | d) |  | d) | -
| ROAD ID 021 - Angelo - Dagohoy |  | GENERAL FUND CY 2020 | CBRMC | 2.19 | Contract | a) | 40025.8404 | a) | - | e) | - | a) | 40025.8404 | a) | - | c) | - | a) | - | Purchase Request # 19125317 (On process)
26 | [6 empty] | b) | - | b) | - | f) | - | b) | 40025.8404 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
| ROAD ID 025 - Jct. Sampao - Bdry. Mamacao |  | GENERAL FUND CY 2020 | MBA | 4.98 | Admin | a) | 325083.1184 | a) | 2020-01-02 | e) | 27 CD | a) | 325083.1184 | a) | 14.71% | c) | 14.71% | a) | 17 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020)
27 | [6 empty] | b) | Crucio | b) | 2020-01-02 | f) | - | b) | 325083.1184 | b) | - | d) | - | b) | 374
[7 empty] | c) | PEO | c) | 2020-12-31 | g) | - | c) | 47819.7267
[7 empty] | d) | 365 CD | d) | -
| ROAD ID 025 - Jct. Sampao - Bdry. Mamacao |  | GENERAL FUND CY 2020 | CBRMC | 4.98 | Contract | a) | 178939.0512 | a) | - | e) | - | a) | 178939.0512 | a) | - | c) | - | a) | - | Purchase Request # 19125318 (On process)
28 | [6 empty] | b) | - | b) | - | f) | - | b) | 178939.0512 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
| ROAD ID 026 - Jct. Highway - Luna - Mamacao - Narra |  | GENERAL FUND CY 2020 | MBA | 9.17 | Admin | a) | 361826.1515 | a) | 2020-01-02 | e) | 27 CD | a) | 361826.1515 | a) | 6.2% | c) | 6.2% | a) | 17 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020)
29 | [6 empty] | b) | Crucio | b) | 2020-01-02 | f) | - | b) | 361826.1515 | b) | - | d) | - | b) | 374
[7 empty] | c) | PEO | c) | 2020-12-31 | g) | - | c) | 22433.2214
[7 empty] | d) | 365 CD | d) | -
| ROAD ID 026 - Jct. Highway - Luna - Mamacao - Narra |  | GENERAL FUND CY 2020 | CBRMC | 9.17 | Contract | a) | 393195.0204 | a) | - | e) | - | a) | 393195.0204 | a) | - | c) | - | a) | - | Purchase Request # 19125337 (On process)
30 | [6 empty] | b) | - | b) | - | f) | - | b) | 393195.0204 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
| ROAD ID 027 - Jct. Gabuyan - Katipunan - Bucana |  | GENERAL FUND CY 2020 | MBA | 5.89 | Admin | a) | 485762.7577 | a) | 2020-01-02 | e) | 27 CD | a) | 485762.7577 | a) | 7.86% | c) | 7.86% | a) | 17 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020)
31 | [6 empty] | b) | Crucio | b) | 2020-01-02 | f) | - | b) | 485762.7577 | b) | - | d) | - | b) | 374
[7 empty] | c) | PEO | c) | 2020-12-31 | g) | - | c) | 38180.9528
[7 empty] | d) | 365 CD | d) | -
| ROAD ID 027 - Jct. Gabuyan - Katipunan - Bucana |  | GENERAL FUND CY 2020 | CBRMC | 5.89 | Contract | a) | 174230.1288 | a) | - | e) | - | a) | 174230.1288 | a) | - | c) | - | a) | - | Purchase Request # 19125338 (On process)
32 | [6 empty] | b) | - | b) | - | f) | - | b) | 174230.1288 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
| ROAD ID 028 - Capungagan - Mabuhay - Pandulian |  | GENERAL FUND CY 2020 | MBA | 5.57 | Admin | a) | 468741.4542 | a) | 2020-01-02 | e) | 27 CD | a) | 468741.4542 | a) | 5.14% | c) | 5.14% | a) | 17 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020)
33 | [6 empty] | b) | Crucio | b) | 2020-01-02 | f) | - | b) | 468741.4542 | b) | - | d) | - | b) | 374
[7 empty] | c) | PEO | c) | 2020-12-31 | g) | - | c) | 24093.3107
[7 empty] | d) | 365 CD | d) | -
| ROAD ID 028 - Capungagan - Mabuhay - Pandulian |  | GENERAL FUND CY 2020 | CBRMC | 5.57 | Contract | a) | 155394.4392 | a) | - | e) | - | a) | 155394.4392 | a) | - | c) | - | a) | - | Purchase Request # 19125339 (On process)
34 | [6 empty] | b) | - | b) | - | f) | - | b) | 155394.4392 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
| ROAD ID 034 - Km. 15, Kipalili - New Loon |  | GENERAL FUND CY 2020 | MBA | 6.93 | Admin | a) | 490709.8742 | a) | 2020-01-02 | e) | 27 CD | a) | 490709.8742 | a) | 13.53% | c) | 13.53% | a) | 17 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020)
35 | [6 empty] | b) | Crucio | b) | 2020-01-02 | f) | - | b) | 490709.8742 | b) | - | d) | - | b) | 374
[7 empty] | c) | PEO | c) | 2020-12-31 | g) | - | c) | 66393.046
[7 empty] | d) | 365 CD | d) | -
| ROAD ID 034 - Km. 15, Kipalili - New Loon |  | GENERAL FUND CY 2020 | CBRMC | 6.93 | Contract | a) | 296662.1112 | a) | - | e) | - | a) | 296662.1112 | a) | - | c) | - | a) | - | Purchase Request # 19125340 (On process)
36 | [6 empty] | b) | - | b) | - | f) | - | b) | 296662.1112 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
| ROAD ID 035 - Jct. Suaon - Libuton |  | GENERAL FUND CY 2020 | MBA | 7.26 | Admin | a) | 60919.7962 | a) | 2020-01-02 | e) | 27 CD | a) | 60919.7962 | a) | 7.12% | c) | 7.12% | a) | 17 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020)
37 | [6 empty] | b) | Crucio | b) | 2020-01-02 | f) | - | b) | 60919.7962 | b) | - | d) | - | b) | 374
[7 empty] | c) | PEO | c) | 2020-12-31 | g) | - | c) | 4337.4895
[7 empty] | d) | 365 CD | d) | -
| ROAD ID 035 - Jct. Suaon - Libuton |  | GENERAL FUND CY 2020 | CBRMC | 7.26 | Contract | a) | 96532.9092 | a) | - | e) | - | a) | 96532.9092 | a) | - | c) | - | a) | - | Purchase Request # 19125341 (On process)
38 | [6 empty] | b) | - | b) | - | f) | - | b) | 96532.9092 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
| ROAD ID 037 - Monte Dujali - Gupitan |  | GENERAL FUND CY 2020 | MBA | 4.58 | Admin | a) | 224727.1648 | a) | 2020-01-02 | e) | 27 CD | a) | 224727.1648 | a) | 11.08% | c) | 11.08% | a) | 17 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020)
39 | [6 empty] | b) | Crucio | b) | 2020-01-02 | f) | - | b) | 224727.1648 | b) | - | d) | - | b) | 374
[7 empty] | c) | PEO | c) | 2020-12-31 | g) | - | c) | 24899.7699
[7 empty] | d) | 365 CD | d) | -
| ROAD ID 037 - Monte Dujali - Gupitan |  | GENERAL FUND CY 2020 | CBRMC | 4.58 | Contract | a) | 134204.2884 | a) | - | e) | - | a) | 134204.2884 | a) | - | c) | - | a) | - | Purchase Request # 19125342 (On process)
40 | [6 empty] | b) | - | b) | - | f) | - | b) | 134204.2884 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
| ROAD ID 041 - Sawata - Mamangan - Pinamuno |  | GENERAL FUND CY 2020 | MBA | 14.48 | Admin | a) | 1113791.2481 | a) | 2020-01-02 | e) | 27 CD | a) | 1113791.2481 | a) | 9.12% | c) | 9.12% | a) | 17 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020)
41 | [6 empty] | b) | Crucio | b) | 2020-01-02 | f) | - | b) | 1113791.2481 | b) | - | d) | - | b) | 374
[7 empty] | c) | PEO | c) | 2020-12-31 | g) | - | c) | 101577.7618
[7 empty] | d) | 365 CD | d) | -
| ROAD ID 041 - Sawata - Mamangan - Pinamuno |  | GENERAL FUND CY 2020 | CBRMC | 14.48 | Contract | a) | 522690.3864 | a) | - | e) | - | a) | 522690.3864 | a) | - | c) | - | a) | - | Purchase Request # 19125343 (On process)
42 | [6 empty] | b) | - | b) | - | f) | - | b) | 522690.3864 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
| ROAD ID 042 - Igangon - Sawata |  | GENERAL FUND CY 2020 | MBA | 9.66 | Admin | a) | 111771.1255 | a) | 2020-01-02 | e) | 27 CD | a) | 111771.1255 | a) | 8.74% | c) | 8.74% | a) | 17 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020)
43 | [6 empty] | b) | Crucio | b) | 2020-01-02 | f) | - | b) | 111771.1255 | b) | - | d) | - | b) | 374
[7 empty] | c) | PEO | c) | 2020-12-31 | g) | - | c) | 9768.7964
[7 empty] | d) | 365 CD | d) | -
| ROAD ID 042 - Igangon - Sawata |  | GENERAL FUND CY 2020 | CBRMC | 9.66 | Contract | a) | 202483.6632 | a) | - | e) | - | a) | 202483.6632 | a) | - | c) | - | a) | - | Purchase Request # 19125344 (On process)
44 | [6 empty] | b) | - | b) | - | f) | - | b) | 202483.6632 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
| ROAD ID 043 - Jct. Sawata - Bdry. Binasbas |  | GENERAL FUND CY 2020 | MBA | 0.46 | Admin | a) | 27720.5682 | a) | 2020-01-02 | e) | 27 CD | a) | 27720.5682 | a) | 10.3% | c) | 10.3% | a) | 17 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020)
45 | [6 empty] | b) | Crucio | b) | 2020-01-02 | f) | - | b) | 27720.5682 | b) | - | d) | - | b) | 374
[7 empty] | c) | PEO | c) | 2020-12-31 | g) | - | c) | 2855.2185
[7 empty] | d) | 365 CD | d) | -
| ROAD ID 043 - Jct. Sawata - Bdry. Binasbas |  | GENERAL FUND CY 2020 | CBRMC | 0.46 | Contract | a) | 18835.6896 | a) | - | e) | - | a) | 18835.6896 | a) | - | c) | - | a) | - | Purchase Request # 19125345 (On process)
46 | [6 empty] | b) | - | b) | - | f) | - | b) | 18835.6896 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
| ROAD ID 045 - Tagaytay - Buan |  | GENERAL FUND CY 2020 | MBA | 4.92 | Admin | a) | 378553.2244 | a) | 2020-01-02 | e) | 27 CD | a) | 378553.2244 | a) | 19.85% | c) | 19.85% | a) | 17 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020)
47 | [6 empty] | b) | Crucio | b) | 2020-01-02 | f) | - | b) | 378553.2244 | b) | - | d) | - | b) | 374
[7 empty] | c) | PEO | c) | 2020-12-31 | g) | - | c) | 75142.815
[7 empty] | d) | 365 CD | d) | -
| ROAD ID 045 - Tagaytay - Buan |  | GENERAL FUND CY 2020 | CBRMC | 4.92 | Contract | a) | 174230.1288 | a) | - | e) | - | a) | 174230.1288 | a) | - | c) | - | a) | - | Purchase Request # 19125346 (On process)
48 | [6 empty] | b) | - | b) | - | f) | - | b) | 174230.1288 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
| ROAD ID 049 - Limbaan - Sto. Niño |  | GENERAL FUND CY 2020 | MBA | 3.19 | Admin | a) | 195716.6763 | a) | 2020-01-02 | e) | 27 CD | a) | 195716.6763 | a) | 9.73% | c) | 9.73% | a) | 17 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020)
49 | [6 empty] | b) | Crucio | b) | 2020-01-02 | f) | - | b) | 195716.6763 | b) | - | d) | - | b) | 374
[7 empty] | c) | PEO | c) | 2020-12-31 | g) | - | c) | 19043.2326
[7 empty] | d) | 365 CD | d) | -
| ROAD ID 049 - Limbaan - Sto. Niño |  | GENERAL FUND CY 2020 | CBRMC | 3.19 | Contract | a) | 127140.9048 | a) | - | e) | - | a) | 127140.9048 | a) | - | c) | - | a) | - | Purchase Request # 20010072 (On process)
50 | [6 empty] | b) | - | b) | - | f) | - | b) | 127140.9048 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
| ROAD ID 050 - Jct. Monte Carlo - Upper Cabaywa - Canatan |  | GENERAL FUND CY 2020 | MBA | 4.61 | Admin | a) | 285065.7818 | a) | 2020-01-02 | e) | 27 CD | a) | 285065.7818 | a) | 10.98% | c) | 10.98% | a) | 17 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020)
51 | [6 empty] | b) | Crucio | b) | 2020-01-02 | f) | - | b) | 285065.7818 | b) | - | d) | - | b) | 374
[7 empty] | c) | PEO | c) | 2020-12-31 | g) | - | c) | 31300.2228
[7 empty] | d) | 365 CD | d) | -
| ROAD ID 050 - Jct. Monte Carlo - Upper Cabaywa - Canatan |  | GENERAL FUND CY 2020 | CBRMC | 4.61 | Contract | a) | 197774.7408 | a) | - | e) | - | a) | 197774.7408 | a) | - | c) | - | a) | - | Purchase Request # 20010074 (On process)
52 | [6 empty] | b) | - | b) | - | f) | - | b) | 197774.7408 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
| ROAD ID 051 - Del Pilar - Jct. Silangan |  | GENERAL FUND CY 2020 | MBA | 4.17 | Admin | a) | 337766.1689 | a) | 2020-01-02 | e) | 27 CD | a) | 337766.1689 | a) | 5.54% | c) | 5.54% | a) | 17 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020)
53 | [6 empty] | b) | Crucio | b) | 2020-01-02 | f) | - | b) | 337766.1689 | b) | - | d) | - | b) | 374
[7 empty] | c) | PEO | c) | 2020-12-31 | g) | - | c) | 18712.2458
[7 empty] | d) | 365 CD | d) | -
| ROAD ID 051 - Del Pilar - Jct. Silangan |  | GENERAL FUND CY 2020 | CBRMC | 4.17 | Contract | a) | 129495.366 | a) | - | e) | - | a) | 129495.366 | a) | - | c) | - | a) | - | Purchase Request # 20010093 (On process)
54 | [6 empty] | b) | - | b) | - | f) | - | b) | 129495.366 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
| ROAD ID 052 - New Corella - New Sambog - Silangan |  | GENERAL FUND CY 2020 | MBA | 5.1 | Admin | a) | 371450.8414 | a) | 2020-01-02 | e) | 27 CD | a) | 371450.8414 | a) | 8.7% | c) | 8.7% | a) | 17 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020)
55 | [6 empty] | b) | Crucio | b) | 2020-01-02 | f) | - | b) | 371450.8414 | b) | - | d) | - | b) | 374
[7 empty] | c) | PEO | c) | 2020-12-31 | g) | - | c) | 32316.2232
[7 empty] | d) | 365 CD | d) | -
| ROAD ID 052 - New Corella - New Sambog - Silangan |  | GENERAL FUND CY 2020 | CBRMC | 5.1 | Contract | a) | 148331.0556 | a) | - | e) | - | a) | 148331.0556 | a) | - | c) | - | a) | - | Purchase Request # 20010095 (On process)
56 | [6 empty] | b) | - | b) | - | f) | - | b) | 148331.0556 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
| ROAD ID 053 - Pob. New Corella - Prk. 10 Pob. |  | GENERAL FUND CY 2020 | MBA | 1.3 | Admin | a) | 28149.3653 | a) | 2020-01-02 | e) | 27 CD | a) | 28149.3653 | a) | 13.38% | c) | 13.38% | a) | 17 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020)
57 | [6 empty] | b) | Crucio | b) | 2020-01-02 | f) | - | b) | 28149.3653 | b) | - | d) | - | b) | 374
[7 empty] | c) | PEO | c) | 2020-12-31 | g) | - | c) | -
[7 empty] | d) | 365 CD | d) | -
| ROAD ID 053 - Pob. New Corella - Prk. 10 Pob. |  | GENERAL FUND CY 2020 | CBRMC | 1.3 | Contract | a) | 21190.1508 | a) | - | e) | - | a) | 21190.1508 | a) | - | c) | - | a) | - | Purchase Request # 20010155 (On process)
58 | [6 empty] | b) | - | b) | - | f) | - | b) | 21190.1508 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
| ROAD ID 054 - Prk. 7 Pob. - Jct. New Sambog |  | GENERAL FUND CY 2020 | MBA | 2.54 | Admin | a) | 171600.7916 | a) | 2020-01-02 | e) | 27 CD | a) | 171600.7916 | a) | 6.92% | c) | 6.92% | a) | 17 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020)
59 | [6 empty] | b) | Crucio | b) | 2020-01-02 | f) | - | b) | 171600.7916 | b) | - | d) | - | b) | 374
[7 empty] | c) | PEO | c) | 2020-12-31 | g) | - | c) | 11874.7748
[7 empty] | d) | 365 CD | d) | -
| ROAD ID 054 - Prk. 7 Pob. - Jct. New Sambog |  | GENERAL FUND CY 2020 | CBRMC | 2.54 | Contract | a) | 113014.1376 | a) | - | e) | - | a) | 113014.1376 | a) | - | c) | - | a) | - | Purchase Request # 20010158 (On process)
60 | [6 empty] | b) | - | b) | - | f) | - | b) | 113014.1376 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
| ROAD ID 056 - Sta. Fe - Del Monte |  | GENERAL FUND CY 2020 | MBA | 3.34 | Admin | a) | 93676.7241 | a) | 2020-01-02 | e) | 27 CD | a) | 93676.7241 | a) | 11.64% | c) | 11.64% | a) | 17 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020)
61 | [6 empty] | b) | Crucio | b) | 2020-01-02 | f) | - | b) | 93676.7241 | b) | - | d) | - | b) | 374
[7 empty] | c) | PEO | c) | 2020-12-31 | g) | - | c) | 10903.9707
[7 empty] | d) | 365 CD | d) | -
| ROAD ID 056 - Sta. Fe - Del Monte |  | GENERAL FUND CY 2020 | CBRMC | 3.34 | Contract | a) | 75342.7584 | a) | - | e) | - | a) | 75342.7584 | a) | - | c) | - | a) | - | Purchase Request # 20010160 (On process)
62 | [6 empty] | b) | - | b) | - | f) | - | b) | 75342.7584 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
| ROAD ID 058 - New Corella - New Bohol |  | GENERAL FUND CY 2020 | MBA | 11.54 | Admin | a) | 300034.9027 | a) | 2020-01-02 | e) | 27 CD | a) | 300034.9027 | a) | 14.15% | c) | 14.15% | a) | 17 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020)
63 | [6 empty] | b) | Crucio | b) | 2020-01-02 | f) | - | b) | 300034.9027 | b) | - | d) | - | b) | 374
[7 empty] | c) | PEO | c) | 2020-12-31 | g) | - | c) | 42454.9387
[7 empty] | d) | 365 CD | d) | -
| ROAD ID 058 - New Corella - New Bohol |  | GENERAL FUND CY 2020 | CBRMC | 11.54 | Contract | a) | 221319.3528 | a) | - | e) | - | a) | 221319.3528 | a) | - | c) | - | a) | - | Purchase Request # 20010221 (On process)
64 | [6 empty] | b) | - | b) | - | f) | - | b) | 221319.3528 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
| ROAD ID 059 - Jct. Carcor - Prk. 9 Bagsak |  | GENERAL FUND CY 2020 | MBA | 2.5 | Admin | a) | 161961.791 | a) | 2020-01-02 | e) | 27 CD | a) | 161961.791 | a) | 11.94% | c) | 11.94% | a) | 17 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020)
65 | [6 empty] | b) | Crucio | b) | 2020-01-02 | f) | - | b) | 161961.791 | b) | - | d) | - | b) | 374
[7 empty] | c) | PEO | c) | 2020-12-31 | g) | - | c) | 19338.2378
[7 empty] | d) | 365 CD | d) | -
| ROAD ID 059 - Jct. Carcor - Prk. 9 Bagsak |  | GENERAL FUND CY 2020 | CBRMC | 2.5 | Contract | a) | 72988.2972 | a) | - | e) | - | a) | 72988.2972 | a) | - | c) | - | a) | - | Purchase Request # 20010223 (On process)
66 | [6 empty] | b) | - | b) | - | f) | - | b) | 72988.2972 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
| ROAD ID 060 - Carcor - Jct. Kauswagan |  | GENERAL FUND CY 2020 | MBA | 4.32 | Admin | a) | 304751.9237 | a) | 2020-01-02 | e) | 27 CD | a) | 304751.9237 | a) | 22.47% | c) | 22.47% | a) | 17 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020)
67 | [6 empty] | b) | Crucio | b) | 2020-01-02 | f) | - | b) | 304751.9237 | b) | - | d) | - | b) | 374
[7 empty] | c) | PEO | c) | 2020-12-31 | g) | - | c) | 68477.7573
[7 empty] | d) | 365 CD | d) | -
| ROAD ID 060 - Carcor - Jct. Kauswagan |  | GENERAL FUND CY 2020 | CBRMC | 4.32 | Contract | a) | 101241.8316 | a) | - | e) | - | a) | 101241.8316 | a) | - | c) | - | a) | - | Purchase Request # 20010262 (On process)
68 | [6 empty] | b) | - | b) | - | f) | - | b) | 101241.8316 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
| ROAD ID 061 - Del Pilar - Prk. 9 Bagsak - San Jose |  | GENERAL FUND CY 2020 | MBA | 4.32 | Admin | a) | 253106.9161 | a) | 2020-01-02 | e) | 27 CD | a) | 253106.9161 | a) | 7.88% | c) | 7.88% | a) | 17 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020)
69 | [6 empty] | b) | Crucio | b) | 2020-01-02 | f) | - | b) | 253106.9161 | b) | - | d) | - | b) | 374
[7 empty] | c) | PEO | c) | 2020-12-31 | g) | - | c) | 19944.825
[7 empty] | d) | 365 CD | d) | -
| ROAD ID 061 - Del Pilar - Prk. 9 Bagsak - San Jose |  | GENERAL FUND CY 2020 | CBRMC | 4.32 | Contract | a) | 251927.3484 | a) | - | e) | - | a) | 251927.3484 | a) | - | c) | - | a) | - | Purchase Request # 20010264 (On process)
70 | [6 empty] | b) | - | b) | - | f) | - | b) | 251927.3484 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
| ROAD ID 062 - Del Pilar - El Unido |  | GENERAL FUND CY 2020 | MBA | 1.32 | Admin | a) | 84027.808 | a) | 2020-01-02 | e) | 27 CD | a) | 84027.808 | a) | 10.78% | c) | 10.78% | a) | 17 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020)
71 | [6 empty] | b) | Crucio | b) | 2020-01-02 | f) | - | b) | 84027.808 | b) | - | d) | - | b) | 374
[7 empty] | c) | PEO | c) | 2020-12-31 | g) | - | c) | 9058.1977
[7 empty] | d) | 365 CD | d) | -
| ROAD ID 062 - Del Pilar - El Unido |  | GENERAL FUND CY 2020 | CBRMC | 1.32 | Contract | a) | 40025.8404 | a) | - | e) | - | a) | 40025.8404 | a) | - | c) | - | a) | - | Purchase Request # 20010265 (On process)
72 | [6 empty] | b) | - | b) | - | f) | - | b) | 40025.8404 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
| ROAD ID 063 - San Juan - New Talisay |  | GENERAL FUND CY 2020 | MBA | 5.13 | Admin | a) | 442982.6933 | a) | 2020-01-02 | e) | 27 CD | a) | 442982.6933 | a) | 13.42% | c) | 13.42% | a) | 17 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020)
73 | [6 empty] | b) | Crucio | b) | 2020-01-02 | f) | - | b) | 442982.6933 | b) | - | d) | - | b) | 374
[7 empty] | c) | PEO | c) | 2020-12-31 | g) | - | c) | 59448.2774
[7 empty] | d) | 365 CD | d) | -
| ROAD ID 063 - San Juan - New Talisay |  | GENERAL FUND CY 2020 | CBRMC | 5.13 | Contract | a) | 131849.8272 | a) | - | e) | - | a) | 131849.8272 | a) | - | c) | - | a) | - | Purchase Request # 20010267 (On process)
74 | [6 empty] | b) | - | b) | - | f) | - | b) | 131849.8272 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
| ROAD ID 064 - San Juan - Kauswagan - New Cortez |  | GENERAL FUND CY 2020 | MBA | 3.22 | Admin | a) | 60690.1506 | a) | 2020-01-02 | e) | 27 CD | a) | 60690.1506 | a) | 5.26% | c) | 5.26% | a) | 17 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020)
75 | [6 empty] | b) | Crucio | b) | 2020-01-02 | f) | - | b) | 60690.1506 | b) | - | d) | - | b) | 374
[7 empty] | c) | PEO | c) | 2020-12-31 | g) | - | c) | 3192.3019
[7 empty] | d) | 365 CD | d) | -
| ROAD ID 064 - San Juan - Kauswagan - New Cortez |  | GENERAL FUND CY 2020 | CBRMC | 3.22 | Contract | a) | 68279.3748 | a) | - | e) | - | a) | 68279.3748 | a) | - | c) | - | a) | - | Procurement on process
76 | [6 empty] | b) | - | b) | - | f) | - | b) | 68279.3748 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | 8108.51
[7 empty] | d) | - | d) | -
| ROAD ID 065 - New Bohol - Jct. El Unido |  | GENERAL FUND CY 2020 | MBA | 2.12 | Admin | a) | 111335.8968 | a) | 2020-01-02 | e) | 27 CD | a) | 111335.8968 | a) | 8.16% | c) | 8.16% | a) | 17 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020)
77 | [6 empty] | b) | Crucio | b) | 2020-01-02 | f) | - | b) | 111335.8968 | b) | - | d) | - | b) | 374
[7 empty] | c) | PEO | c) | 2020-12-31 | g) | - | c) | 9085.0092
[7 empty] | d) | 365 CD | d) | -
| ROAD ID 065 - New Bohol - Jct. El Unido |  | GENERAL FUND CY 2020 | CBRMC | 2.12 | Contract | a) | 65924.9136 | a) | - | e) | - | a) | 65924.9136 | a) | - | c) | - | a) | - | Purchase Request # 20010275 (On process)
78 | [6 empty] | b) | - | b) | - | f) | - | b) | 65924.9136 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
| ROAD ID 066 - New Corella - El Unido - Jct. Mesaoy |  | GENERAL FUND CY 2020 | MBA | 8.63 | Admin | a) | 542859.5597 | a) | 2020-01-02 | e) | 27 CD | a) | 542859.5597 | a) | 21.43% | c) | 21.43% | a) | 17 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020)
79 | [6 empty] | b) | Crucio | b) | 2020-01-02 | f) | - | b) | 542859.5597 | b) | - | d) | - | b) | 374
[7 empty] | c) | PEO | c) | 2020-12-31 | g) | - | c) | 116334.8036
[7 empty] | d) | 365 CD | d) | -
| ROAD ID 066 - New Corella - El Unido - Jct. Mesaoy |  | GENERAL FUND CY 2020 | CBRMC | 8.63 | Contract | a) | 249572.8872 | a) | - | e) | - | a) | 249572.8872 | a) | - | c) | - | a) | - | Purchase Request # 20010291 (On process)
80 | [6 empty] | b) | - | b) | - | f) | - | b) | 249572.8872 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
| ROAD ID 067 - Mesaoy - Dasing |  | GENERAL FUND CY 2020 | MBA | 1.39 | Admin | a) | 76479.645 | a) | 2020-01-02 | e) | 27 CD | a) | 76479.645 | a) | 7.01% | c) | 7.01% | a) | 17 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020)
81 | [6 empty] | b) | Crucio | b) | 2020-01-02 | f) | - | b) | 76479.645 | b) | - | d) | - | b) | 374
[7 empty] | c) | PEO | c) | 2020-12-31 | g) | - | c) | 5361.2231
[7 empty] | d) | 365 CD | d) | -
| ROAD ID 067 - Mesaoy - Dasing |  | GENERAL FUND CY 2020 | CBRMC | 1.39 | Contract | a) | 54152.6076 | a) | - | e) | - | a) | 54152.6076 | a) | - | c) | - | a) | - | Purchase Request # 20010294 (On process)
82 | [6 empty] | b) | - | b) | - | f) | - | b) | 54152.6076 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
| ROAD ID 068 - Jct. San Juan - Jct. Mesaoy |  | GENERAL FUND CY 2020 | MBA | 1.82 | Admin | a) | 135657.3072 | a) | 2020-01-02 | e) | 27 CD | a) | 135657.3072 | a) | 7.32% | c) | 7.32% | a) | 17 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020)
83 | [6 empty] | b) | Crucio | b) | 2020-01-02 | f) | - | b) | 135657.3072 | b) | - | d) | - | b) | 374
[7 empty] | c) | PEO | c) | 2020-12-31 | g) | - | c) | 9930.1149
[7 empty] | d) | 365 CD | d) | -
| ROAD ID 068 - Jct. San Juan - Jct. Mesaoy |  | GENERAL FUND CY 2020 | CBRMC | 1.82 | Contract | a) | 68279.3748 | a) | - | e) | - | a) | 68279.3748 | a) | - | c) | - | a) | - | Purchase Request # 20010294 (On process)
84 | [6 empty] | b) | - | b) | - | f) | - | b) | 68279.3748 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
| ROAD ID 070 - Mesaoy - New Bohol |  | GENERAL FUND CY 2020 | MBA | 5.36 | Admin | a) | 404322.6481 | a) | 2020-01-02 | e) | 27 CD | a) | 404322.6481 | a) | 8.29% | c) | 8.29% | a) | 17 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020)
85 | [6 empty] | b) | Crucio | b) | 2020-01-02 | f) | - | b) | 404322.6481 | b) | - | d) | - | b) | 374
[7 empty] | c) | PEO | c) | 2020-12-31 | g) | - | c) | 33518.3475
[7 empty] | d) | 365 CD | d) | -
| ROAD ID 070 - Mesaoy - New Bohol |  | GENERAL FUND CY 2020 | CBRMC | 5.36 | Contract | a) | 261345.1932 | a) | - | e) | - | a) | 261345.1932 | a) | - | c) | - | a) | - | Purchase Request # 20010298 (On process)
86 | [6 empty] | b) | - | b) | - | f) | - | b) | 261345.1932 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
| ROAD ID 147 - Prk. 1, Maunlom-Prk. 6 Maunlom Road |  | GENERAL FUND CY 2020 | MBA | 3.56 | Admin | a) | 49887.4041 | a) | 2020-01-02 | e) | - | a) | 49887.4041 | a) | 7.34% | c) | 7.34% | a) | 17 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020)
87 | [6 empty] | b) | Crucio | b) | 2020-01-02 | f) | - | b) | 49887.4041 | b) | - | d) | - | b) | 374
[7 empty] | c) | PEO | c) | 2020-12-31 | g) | - | c) | 3661.7355
[7 empty] | d) | 365 CD | d) | -
| ROAD ID 147 - Prk. 1, Maunlom-Prk. 6 Maunlom Road |  | GENERAL FUND CY 2020 | CBRMC | 3.56 | Contract | a) | 65924.9136 | a) | - | e) | - | a) | 65924.9136 | a) | - | c) | - | a) | - | Purchase Request # 20010302 (On process)
88 | [6 empty] | b) | - | b) | - | f) | - | b) | 65924.9136 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
| ROAD ID 149 - New Visayas - Binancian |  | GENERAL FUND CY 2020 | MBA | 7.774 | Admin | a) | 62394.7204 | a) | 2020-01-02 | e) | - | a) | 62394.7204 | a) | 3.47% | c) | 3.47% | a) | 17 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020)
89 | [6 empty] | b) | Crucio | b) | 2020-01-02 | f) | - | b) | 62394.7204 | b) | - | d) | - | b) | 374
[7 empty] | c) | PEO | c) | 2020-12-31 | g) | - | c) | 2165.0968
[7 empty] | d) | 365 CD | d) | -
| ROAD ID 149 - New Visayas - Binancian |  | GENERAL FUND CY 2020 | CBRMC | 7.774 | Contract | a) | 134204.2884 | a) | - | e) | - | a) | 134204.2884 | a) | - | c) | - | a) | - | Purchase Request # 20010305 (On process)
90 | [6 empty] | b) | - | b) | - | f) | - | b) | 134204.2884 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
| ROAD ID 150 - Datu Balong - Prk. Mamalian |  | GENERAL FUND CY 2020 | MBA | 3.46 | Admin | a) | 45089.8864 | a) | 2020-01-02 | e) | - | a) | 45089.8864 | a) | 6.37% | c) | 6.37% | a) | 17 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020)
91 | [6 empty] | b) | Crucio | b) | 2020-01-02 | f) | - | b) | 45089.8864 | b) | - | d) | - | b) | 374
[7 empty] | c) | PEO | c) | 2020-12-31 | g) | - | c) | 2872.2258
[7 empty] | d) | 365 CD | d) | -
| ROAD ID 150 - Datu Balong - Prk. Mamalian |  | GENERAL FUND CY 2020 | CBRMC | 3.46 | Contract | a) | 61215.9912 | a) | - | e) | - | a) | 61215.9912 | a) | - | c) | - | a) | - | Purchase Request # 20010306 (On process)
92 | [6 empty] | b) | - | b) | - | f) | - | b) | 61215.9912 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
PEACE AND ORDER PROGRAM
RURAL ELECTRIFICATION PROJECT LS - P 5,000,000.00
| Rural Electrification at RAMADA Compound Purok Sto. Niño, Brgy. Cuambogan, Tagum City |  | 20% Development Fund CY 2020 | Elect. | - | - | a) | 1000000 | a) | - | e) | - | a) | 1000000 | a) | - | c) | - | a) | - | Date of procurement June 30, 2020
93 | [6 empty] | b) | - | b) | - | f) | - | b) | 1000000 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
| Rural Electrification at RAMADA Compound, Brgy. Camansa, Asuncion |  | 20% Development Fund CY 2020 | Elect. | - | - | a) | 3000000 | a) | - | e) | - | a) | 3000000 | a) | - | c) | - | a) | - | Date of procurement June 30, 2020
94 | [6 empty] | b) | - | b) | - | f) | - | b) | 3000000 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
| Completion of Electrification at at Purok 10 and Purok 9, Phase 2, Brgy. Doña Andrea, Asuncion |  | 20% Development Fund CY 2020 | Elect. | - | - | a) | 1000000 | a) | - | e) | - | a) | 1000000 | a) | - | c) | - | a) | - | For preparation of POW and Plans
95 | [6 empty] | b) | - | b) | - | f) | - | b) | 1000000 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00
| ROAD ID 008 - Sta. Felomina - San Roque |  | 20% Development Fund CY 2020 | Road Rehabilitaion | 7.68 | Admin | a) | 2304000 | a) | - | e) | - | a) | 2304000 | a) | - | c) | - | a) | - | Purhase Request for checking
96 | [6 empty] | b) |  | b) | - | f) | - | b) | 2304000 | b) | - | d) | - | b) | -
[7 empty] | c) | PEO | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
| ROAD ID 019 - Sto. Niño - Palma Gil - Sitio Opao |  | 20% Development Fund CY 2020 | Road Rehabilitaion | 5.99 | Admin | a) | 1797000 | a) |  | e) | - | a) | 1797000 | a) | - | c) | - | a) | - | POW on process
97 | [6 empty] | b) |  | b) |  | f) | - | b) | 1797000 | b) | - | d) | - | b) | -
[7 empty] | c) | PEO | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
| ROAD ID 023 - Sto. Niño - Daligdigon - Paiton |  | 20% Development Fund CY 2020 | Road Rehabilitaion | 11.6 | Admin | a) | 3480000 | a) |  | e) | - | a) | 3480000 | a) | - | c) | - | a) | - | POW on process
98 | [6 empty] | b) |  | b) |  | f) | - | b) | 3480000 | b) | - | d) | - | b) | -
[7 empty] | c) | PEO | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
| ROAD ID 024 - Jct. Paiton - Mibolo |  | 20% Development Fund CY 2020 | Road Rehabilitaion | 23.9 | Admin | a) | 7170000 | a) |  | e) | - | a) | 7170000 | a) | - | c) | - | a) | - | POW on process
99 | [6 empty] | b) |  | b) |  | f) | - | b) | 7170000 | b) | - | d) | - | b) | -
[7 empty] | c) | PEO | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
| ROAD ID 024 - Florida - Suaon - Jct. Gupitan |  | 20% Development Fund CY 2020 | Road Rehabilitaion | 15.57 | Admin | a) | 4671000 | a) |  | e) | - | a) | 4671000 | a) | - | c) | - | a) | - | For bidding on July 3, 2020
100 | [6 empty] | b) |  | b) |  | f) | - | b) | 4671000 | b) | - | d) | - | b) | -
[7 empty] | c) | PEO | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
| ROAD ID 040 - Datu Balong - Pinamuno |  | 20% Development Fund CY 2020 | Road Rehabilitaion | 2.74 | Admin | a) | 822000 | a) |  | e) | - | a) | 822000 | a) | - | c) | - | a) | - | POW on process
101 | [6 empty] | b) |  | b) |  | f) | - | b) | 822000 | b) | - | d) | - | b) | -
[7 empty] | c) | PEO | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
| ROAD ID 048 - New Corella - Saug |  | 20% Development Fund CY 2020 | Road Rehabilitaion | 12.52 | Admin | a) | 20571000 | a) |  | e) | - | a) | 20571000 | a) | - | c) | - | a) | - | POW on process
102 | [6 empty] | b) |  | b) |  | f) | - | b) | 20571000 | b) | - | d) | - | b) | -
[7 empty] | c) | PEO | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
INFRASTRUCTURE DEVELOPMENT PROGRAMS
| ROAD ID 074 - Jct. Highway Canatan - Doña Andrea |  | 20% Development Fund CY 2020 | Road Rehabilitaion | 4.34 | Admin | a) | 1302000 | a) |  | e) | - | a) | 1302000 | a) | - | c) | - | a) | - | POW on process
103 | [6 empty] | b) |  | b) |  | f) | - | b) | 1302000 | b) | - | d) | - | b) | -
[7 empty] | c) | PEO | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
| ROAD ID 030 - Florida - New Boholano |  | 20% Development Fund CY 2020 | Road Rehabilitaion | 2.54 | Admin | a) | 762000 | a) |  | e) | - | a) | 762000 | a) | - | c) | - | a) | - | POW on process
104 | [6 empty] | b) |  | b) |  | f) | - | b) | 762000 | b) | - | d) | - | b) | -
[7 empty] | c) | PEO | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
| ROAD ID 031 - Jct. New Boholano - New Loon |  | 20% Development Fund CY 2020 | Road Rehabilitaion | 4.77 | Admin | a) | 1431000 | a) |  | e) | - | a) | 1431000 | a) | - | c) | - | a) | - | POW on process
105 | [6 empty] | b) |  | b) |  | f) | - | b) | 1431000 | b) | - | d) | - | b) | -
[7 empty] | c) | PEO | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
| ROAD ID 069 - Mesaoy - Jct. Mahayahay |  | 20% Development Fund CY 2020 | Road Rehabilitaion | 4.6 | Admin | a) | 1380000 | a) |  | e) | - | a) | 1380000 | a) | - | c) | - | a) | - | POW on process
106 | [6 empty] | b) |  | b) |  | f) | - | b) | 1380000 | b) | - | d) | - | b) | -
[7 empty] | c) | PEO | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
| ROAD ID 071 - Lower Asuncion - Upper Asuncion |  | 20% Development Fund CY 2020 | Road Rehabilitaion | KM | Admin | a) | 1302000 | a) |  | e) | - | a) | 1302000 | a) | - | c) | - | a) | - | Plan On-going
107 | [6 empty] | b) |  | b) |  | f) | - | b) | 1302000 | b) | - | d) | - | b) | -
[7 empty] | c) | PEO | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
VARIOUS LOCAL ROADS & DRAINAGE DEV'T. PROJECT - LS P15,590,910.00
| Rehab. Of Various Locl Roads @ Tagum City |  | 20% Development Fund CY 2020 | Rehabilitaion | km. | - | a) | 2518182 | a) |  | e) | - | a) | 2518182 | a) | - | c) | - | a) | - | POW on process
108 | [6 empty] | b) |  | b) |  | f) | - | b) | 2518182 | b) | - | d) | - | b) | -
[7 empty] | c) | PEO | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
| Rehab. Of Various Locl Roads @ Asuncion |  | 20% Development Fund CY 2020 | Rehabilitaion | km. | - | a) | 2518182 | a) |  | e) | - | a) | 2518182 | a) | - | c) | - | a) | - | POW on process
109 | [6 empty] | b) |  | b) |  | f) | - | b) | 2518182 | b) | - | d) | - | b) | -
[7 empty] | c) | PEO | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
| Rehab. Of Various Locl Roads @ Kapalong |  | 20% Development Fund CY 2020 | Rehabilitaion | km. | - | a) | 2518182 | a) |  | e) | - | a) | 2518182 | a) | - | c) | - | a) | - | Purchase Request on process
110 | [6 empty] | b) |  | b) |  | f) | - | b) | 2518182 | b) | - | d) | - | b) | -
[7 empty] | c) | PEO | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
| Rehab. Of Various Locl Roads @ New Corella |  | 20% Development Fund CY 2020 | Rehabilitaion | km. | - | a) | 2518182 | a) |  | e) | - | a) | 2518182 | a) | - | c) | - | a) | - | POW on process
111 | [6 empty] | b) |  | b) |  | f) | - | b) | 2518182 | b) | - | d) | - | b) | -
[7 empty] | c) | PEO | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
| Rehab. Of Various Locl Roads @ San Isidro |  | 20% Development Fund CY 2020 | Rehabilitaion | km. | - | a) | 2518182 | a) |  | e) | - | a) | 2518182 | a) | - | c) | - | a) | - | POW on process
112 | [6 empty] | b) |  | b) |  | f) | - | b) | 2518182 | b) | - | d) | - | b) | -
[7 empty] | c) | PEO | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
| Rehab. Of Various Local Roads @ Talaingod |  | 20% Development Fund CY 2020 | Rehabilitaion | km. | - | a) | 2518182 | a) |  | e) | - | a) | 2518182 | a) | - | c) | - | a) | - | Purchase Request on process
113 | [6 empty] | b) |  | b) |  | f) | - | b) | 2518182 | b) | - | d) | - | b) | -
[7 empty] | c) | PEO | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
| VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 |  |  |  |  | -
| Construction of DAVNOR Tech-Vocational Center, Government Center, Mankilam, Tagum City |  | 20% Development Fund CY 2020 | Various Bldgs./Facilities | sq.m | - | a) | 8000000 | a) |  | e) | - | a) | 8000000 | a) | - | c) | - | a) | - | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
114 | [6 empty] | b) |  | b) |  | f) | - | b) | 8000000 | b) | - | d) | - | b) | -
[7 empty] | c) | PEO | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
| Improvement of PSWDO Bodega Government Cente, Mankilam, Tagu City |  | 20% Development Fund CY 2020 | Various Bldgs./Facilities | sq.m | - | a) | 1000000 | a) |  | e) | - | a) | 1000000 | a) | - | c) | - | a) | - | POW and Plans on-going
115 | [6 empty] | b) |  | b) |  | f) | - | b) | 1000000 | b) | - | d) | - | b) | -
[7 empty] | c) | PEO | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
| Renovation/Improvement of MAFAMCO Consumer's Bldg., Brgy. Mamangan, San Isidro |  | 20% Development Fund CY 2020 | Various Bldgs./Facilities | sq.m | Contract | a) | 800000 | a) |  | e) | - | a) | 800000 | a) | - | c) | - | a) | - | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
116 | [6 empty] | b) |  | b) |  | f) | - | b) | 800000 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
| Construction of IP Council of Women Training Center, Camansa Kamadi District, Asuncion |  | 20% Development Fund CY 2020 | Various Bldgs./Facilities | sq.m | - | a) | 500000 | a) |  | e) | - | a) | 500000 | a) | - | c) | - | a) | - | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
117 | [6 empty] | b) |  | b) |  | f) | - | b) | 500000 | b) | - | d) | - | b) | -
[7 empty] | c) | PEO | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
| Construction of One(1) unit School Building at Cabidianan E/S, New Corella |  | 20% Development Fund CY 2020 | Various Bldgs./Facilities | sq.m | Contract | a) | 1300000 | a) |  | e) | - | a) | 1300000 | a) | - | c) | - | a) | -
118 | [6 empty] | b) |  | b) |  | f) | - | b) | 1300000 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
| Construction of one(1) unit School Building at Kamansi Integrated School, Florida, kapalong |  | 20% Development Fund CY 2020 | Various Bldgs./Facilities | sq.m | Contract | a) | 1300000 | a) |  | e) | - | a) | 1300000 | a) | - | c) | - | a) | - | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
119 | [6 empty] | b) |  | b) |  | f) | - | b) | 1300000 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
| Construction of one(1) unit School Building at Magatos E/S, Magatos, Asuncion |  | 20% Development Fund CY 2020 | Various Bldgs./Facilities | sq.m | Contract | a) | 1300000 | a) |  | e) | - | a) | 1300000 | a) | - | c) | - | a) | - | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
120 | [6 empty] | b) |  | b) |  | f) | - | b) | 1300000 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
| Construction of one(1) unit School Building at Sta. Cruz E/S, New Corella |  | 20% Development Fund CY 2020 | Various Bldgs./Facilities | sq.m | - | a) | 1300000 | a) |  | e) | - | a) | 1300000 | a) | - | c) | - | a) | - | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
121 | [6 empty] | b) |  | b) |  | f) | - | b) | 1300000 | b) | - | d) | - | b) | -
[7 empty] | c) | PEO | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
| Construction Women Development Center, Dagohoy, Talaingod |  | 20% Development Fund CY 2020 | Various Bldgs./Facilities | sq.m | - | a) | 1000000 | a) |  | e) | - | a) | 1000000 | a) | - | c) | - | a) | - | Bidding Documents for Posting
122 | [6 empty] | b) |  | b) |  | f) | - | b) | 1000000 | b) | - | d) | - | b) | -
[7 empty] | c) | PEO | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
CONTRACT PACKAGE:
| Construction of Municipal Triball Hall, Asuncion |  | 20% Development Fund CY 2020 | Various Bldgs./Facilities | sq.m | Contract | a) | 500000 | a) |  | e) | - | a) | 500000 | a) | - | c) | - | a) | - | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
123 | [6 empty] | b) |  | b) |  | f) | - | b) | 500000 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
| Construction of Municipal Triball Hall, Kapalong |  | 20% Development Fund CY 2020 | Various Bldgs./Facilities | sq.m | Contract | a) | 500000 | a) |  | e) | - | a) | 500000 | a) | - | c) | - | a) | - | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
124 | [6 empty] | b) |  | b) |  | f) | - | b) | 500000 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
| Construction of Municipal Triball Hall, Talaingod |  | 20% Development Fund CY 2020 | Various Bldgs./Facilities | sq.m | - | a) | 500000 | a) |  | e) | - | a) | 500000 | a) | - | c) | - | a) | - | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
125 | [6 empty] | b) |  | b) |  | f) | - | b) | 500000 | b) | - | d) | - | b) | -
[7 empty] | c) | PEO | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
DISASTER PREVENTION AND MITIGATION PROGRAM - FLOOD CONTROL AND SLOPE PROTECTION PROJECT
Revetment of Dike and Slope Protection
| Rehab./Impv't. of Sto. Niño-Daligdigon-Paiton |  | 5% CALAMITY FUND CY 2020 | Rehab./Impv't. | km. | - | a) | 1000000 | a) |  | e) | - | a) | 1000000 | a) | - | c) | - | a) | - | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
126 | [6 empty] | b) |  | b) |  | f) | - | b) | 1000000 | b) | - | d) | - | b) | -
[7 empty] | c) | PEO | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
Improvement of Bridges and Cross Drainage
| Improvement of Saug-Sonlon-Bdry. Longanapan |  | 5% CALAMITY FUND CY 2020 | Rehab./Impv't. | km. | - | a) | 1000000 | a) |  | e) | - | a) | 1000000 | a) | - | c) | - | a) | - | For preparation of POW and Plans
127 | [6 empty] | b) |  | b) |  | f) | - | b) | 1000000 | b) | - | d) | - | b) | -
[7 empty] | c) | PEO | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00
| Const. of 1 Classroom @ Mankay Integrated School, Gupitan, kapalong |  | SEF CY 2020 | Bldg. | sq.m | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Opening of Shopping on June 25, 2020
128 | [6 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
| Const. of 1 Classroom @ Luno-luno E/S, Gupitan, kapalong |  | SEF CY 2020 | Bldg. | sq.m | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Opening of Shopping on June 25, 2020
129 | [6 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
| Const. of 1 Classroom @ Kamunuan E/S, Gupitan, kapalong |  | SEF CY 2020 | Bldg. | sq.m | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Opening of Shopping on June 25, 2020
130 | [6 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
| Const. of 1 Classroom @ Tawinian E/S, Gupitan, kapalong |  | SEF CY 2020 | Bldg. | sq.m | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Opening of Shopping on June 25, 2020
131 | [6 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
| Const. of 1 Classroom @ Aninipot E/S, Gupitan, kapalong |  | SEF CY 2020 | Bldg. | sq.m | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Opening of Shopping on June 25, 2020
132 | [6 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
| Const. of 1 Classroom @ Moling E/S, Gupitan, kapalong |  | SEF CY 2020 | Bldg. | sq.m | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Opening of Shopping on June 25, 2020
133 | [6 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
| Const. of 1 Classroom @ Lomondong E/S, Dagohoy, Talaingod |  | SEF CY 2020 | Bldg. | sq.m | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Opening of Shopping on June 25, 2020
134 | [6 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
| Const. of 1 Classroom @ Malapanit E/S, Sto. Niño, Talaingod |  | SEF CY 2020 | Bldg. | sq.m | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Opening of Shopping on June 25, 2020
135 | [6 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
| Const. of 1 Classroom @ Laputlakan E/S, Sto. Niño, Talaingod |  | SEF CY 2020 | Bldg. | sq.m | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Opening of Shopping on June 25, 2020
136 | [6 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
SOCIAL WELFARE AND DEVELOPMENT
CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00
| Const. of Day Care Center, Limbaan, New Corella |  | 20% DF CY 2020 | Bldg. | sq.m | - | a) | 1000000 | a) | - | e) | - | a) | 1000000 | a) | - | c) | - | a) | - | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
137 | [6 empty] | b) | - | b) | - | f) | - | b) | 1000000 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
| Const. of Day Care Center, Gabuyan, kapalong |  | 20% DF CY 2020 | Bldg. | sq.m | - | a) | 1000000 | a) | - | e) | - | a) | 1000000 | a) | - | c) | - | a) | - | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
138 | [6 empty] | b) | - | b) | - | f) | - | b) | 1000000 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
| Compl./Rep. Day Care Center,Canatan, Asuncion |  | 20% DF CY 2020 | Bldg. | sq.m | - | a) | 300000 | a) | - | e) | - | a) | 300000 | a) | - | c) | - | a) | - | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
139 | [6 empty] | b) | - | b) | - | f) | - | b) | 300000 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
| Compl./Rep. Day Care Center,Cambanogoy, Asuncion |  | 20% DF CY 2020 | Bldg. | sq.m | - | a) | 300000 | a) | - | e) | - | a) | 300000 | a) | - | c) | - | a) | - | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
140 | [6 empty] | b) | - | b) | - | f) | - | b) | 300000 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
| Compl./Rep. Day Care Center,Gabuyan, kapalong |  | 20% DF CY 2020 | Bldg. | sq.m | - | a) | 600000 | a) | - | e) | - | a) | 600000 | a) | - | c) | - | a) | - | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
141 | [6 empty] | b) | - | b) | - | f) | - | b) | 600000 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
| Compl./Rep. Day Care Center,New Sambog, New Corella |  | 20% DF CY 2020 | Bldg. | sq.m | - | a) | 300000 | a) | - | e) | - | a) | 300000 | a) | - | c) | - | a) | - | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
142 | [6 empty] | b) | - | b) | - | f) | - | b) | 300000 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
| Compl./Rep. Day Care Center, Cabidianan, New Corella |  | 20% DF CY 2020 | Bldg. | sq.m | - | a) | 300000 | a) | - | e) | - | a) | 300000 | a) | - | c) | - | a) | - | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
143 | [6 empty] | b) | - | b) | - | f) | - | b) | 300000 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
| Compl./Rep. Day Care Center, Igangon, San Isidro |  | 20% DF CY 2020 | Bldg. | sq.m | - | a) | 300000 | a) | - | e) | - | a) | 300000 | a) | - | c) | - | a) | - | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
144 | [6 empty] | b) | - | b) | - | f) | - | b) | 300000 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
| Compl./Rep. Day Care Center, Madaum, Tagum City |  | 20% DF CY 2020 | Bldg. | sq.m | - | a) | 300000 | a) | - | e) | - | a) | 300000 | a) | - | c) | - | a) | - | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
145 | [6 empty] | b) | - | b) | - | f) | - | b) | 300000 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
| Compl./Rep. Day Care Center, Apokon, Tagum City |  | 20% DF CY 2020 | Bldg. | sq.m | - | a) | 300000 | a) | - | e) | - | a) | 300000 | a) | - | c) | - | a) | - | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
146 | [6 empty] | b) | - | b) | - | f) | - | b) | 300000 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
| Compl./Rep. Day Care Center, Sto. Niño, Talaingod |  | 20% DF CY 2020 | Bldg. | sq.m | - | a) | 300000 | a) | - | e) | - | c) | 300000 | a) | - | c) | - | a) | - | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
147 | [6 empty] | b) | - | b) | - | f) | - | b) | 300000 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
HEALTH CARE SERVICES PROGRAM (PEEDO)
| Improvement/Rehab. Of Luntiang Paraiso, New Corella |  | 20% DF CY 2020 | - | - | - | a) | 3000000 | a) | - | e) | - | a) | 3000000 | a) | - | c) | - | a) | - | For Purchase Request
148 | [6 empty] | b) | - | b) | - | f) | - | b) | 3000000 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
PSYDO YOUTH DEV'T. PROGRAM - TEEN TAMBAYAN PROJECT
| Renovation of Teen Tambayan |  | 20% DF CY 2020 | - | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Date of procurement June 30, 2020
149 | [6 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
SPECIAL TRUST FUND (PDRRMC)
| Installation of 20 units Isolation Room, Sports Academy Dormitory, DNSTC |  | TF | - | - | - | a) | 170000 | a) | 2020-06-01 | e) | - | a) | 170000 | a) | 95% | c) | 95% | a) | - | On-going
150 | [6 empty] | b) | - | b) | 2020-06-01 | f) | - | b) | 170000 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
| Installation of 100 units isolation room (2.0 x 3.0m), DAVNOR GYM |  | TF | Bldg. | sq.m | - | a) | 750000 | a) | 2020-06-02 | e) | - | a) | 750000 | a) | 95% | c) | 95% | a) | - | On-going
151 | [6 empty] | b) |  | b) | 2020-06-01 | f) | - | b) | 750000 | b) | - | d) | - | b) | -
[7 empty] | c) | PEO | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
| Installation of 40 units Isolation Room, Sports Academy Dormitory, DNSTC |  | TF | Bldg. | sq.m | - | a) | 320000 | a) | 2020-05-28 | e) | - | a) | 320000 | a) | 95% | c) | 95% | a) | - | On-going
152 | [6 empty] | b) |  | b) | 2020-06-01 | f) | - | b) | 320000 | b) | - | d) | - | b) | -
[7 empty] | c) | PEO | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
PEACE AND ORDER PROGRAM
| Proposed Road Opening of Nasilaban - Pongpong Road Section, Talaingod |  | SB # 1 CY 2020 | - | - | - | a) | 5500000 | a) | - | e) | - | a) | 5500000 | a) | - | c) | - | a) | - | Purchase Order on process
153 | [6 empty] | b) | - | b) | - | f) | - | b) | 5500000 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
VARIOUS GOV'T. BLDG. & FAC. DEV'T. PROJECT
| Establishment of Multiplier Farm Phase 2, Brgy. Sto. Niño, Talaingod |  | SB # 1 CY 2020 | - | - | - | a) | 380000 | a) | - | e) | - | a) | 380000 | a) | - | c) | - | a) | - | Purchase Order on process
154 | [6 empty] | b) | - | b) | - | f) | - | b) | 380000 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
| Establishment of Multiplier Farm (Poultry House), Phase 2, Brgy. Sto. Niño, Talaingod |  | SB # 1 CY 2020 |  | - | - | a) | 110000 | a) | - | e) | - | a) | 110000 | a) | - | c) | - | a) | - | Purchase Order on process
155 | [6 empty] | b) | - | b) | - | f) | - | b) | 110000 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
| Poultry House and Training Center Phase 2, Talaingod |  | SB # 1 CY 2020 | - | - | - | a) | 500000 | a) | - | e) | - | a) | 500000 | a) | - | c) | - | a) | - | Purchase Order on process
156 | [6 empty] | b) | - | b) | - | f) | - | b) | 500000 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
BAYANIHAN GRANT TO PROVINCES
| Improvement of Hospital facilities (Isolation/ICU), Kapalong Dist. Hospital |  | SB # 2 CY 2020 | Bldg. |  | - | a) | 6000000 | a) | 2020-05-07 | e) | - | a) | 6000000 | a) | 4.8% | c) | 8.1% | a) | 18 | On-going
157 | [6 empty] | b) | Pasiona/Aclaracion | b) | 2020-05-11 | f) | - | b) | 6000000 | b) | - | d) | - | b) | 540
[7 empty] | c) | Admin | c) | 2021-01-10 | g) | - | c) | -
[7 empty] | d) | 245 CD | d) | -
NATIONAL PROJECTS
| Road Improvement of Jct. Highway Gabuyan – Semong – Dagohoy Provincial Road |  | CMGP CY 2020 | Road | - | - | a) | 63458000 | a) | - | e) | - | a) | 63458000 | a) | - | c) | - | a) | - | For posting
158 | [6 empty] | b) | - | b) | - | f) | - | b) | 63458000 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
| Const. of 100 Housing Units at Balai Lupowanan at Sitio Nasilaban, Palma Gil, Talaingod |  | Natinal Housing Project CY 2020 | Bldg. | - | - | a) | 20000000 | a) | - | e) | - | a) | 20000000 | a) | - | c) | - | a) | - | For bidding on July 3, 2020
159 | [6 empty] | b) | - | b) | - | f) | - | b) | 20000000 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
| Const. of 100 Housing Units at Balai Pig Immimanan at Sitio Mesulong, Sto. Niño, Talaingod |  | Natinal Housing Project CY 2020 | Bldg. | - | - | a) | 20000000 | a) | - | e) | - | a) | 20000000 | a) | - | c) | - | a) | - | For bidding on July 3, 2020
160 | [6 empty] | b) | - | b) | - | f) | - | b) | 20000000 | b) | - | d) | - | b) | -
[7 empty] | c) | - | c) | - | g) | - | c) | -
[7 empty] | d) | - | d) | -
|  | GF- GENERAL FUND | [12 empty] | TF - TRUST FUND (NATIONAL FUNDED PROJECT)
|  | 20% DF - 20% DEV'T. FUND | [12 empty] | a) SLRF - Special Local Road Fund
|  | 5% CF - 5% CALAMITY FUND | [12 empty] | b) KALSADA - Konkreto at Ayos na Lansangan Tungo sa Pangkalahatang Kaunlaran
|  | CO - CAPITAL OUTLAY | [12 empty] | c) PRDP - Philippine Rural Development Projects
|  | CONG. FUND - CONGRESSIONAL FUND | [12 empty] | d) SELAP - Support to Emergency and Livelihood Assistance Project
|  | SEF - SPECIAL EDUCATIONAL UFND | [12 empty] | e) PAMANA - Payapa at Masaganang Pamayanan
f) CBRMC - Community Based Road Maintenance Contracting
g) MBC - Maintenance by Contract
h) PCF-Performance Challenge Fund-DILG
i) FMRDP - Farm to Market Road
j.) CMGP - Conditional Matching Grant to Provinces
k.) OPAPP - Office of the President Adviser on the Peace Process
l.) LGSF-AM - Local Government Support Fund Assistance to Municipalities
Prepared by: |  |  |  |  | Checked | [5 empty] | Noted | [6 empty] | Recommending Approval
RETCHIE A. DE LOS REYES |  |  |  |  | ELISA A. BARCENA | [5 empty] | JIVELLYN B. CO | [6 empty] | GLENN A. OLANDRIA
Engineer II |  |  |  |  | Engineer IV- Engineering Dist 1, Area Engineer | [5 empty] | Asst. PG-Department Head | [6 empty] | Provincial Engineer
Note on C1042: chy2x:

## Signatures1st (hidden)
GF- GENERAL FUND |  |  | TF - TRUST FUND (NATIONAL FUNDED PROJECT)
20% DF - 20% DEVELOPMENT FUND |  |  | a) SLRF - Special Local Road Fund
5% CF - 5% CALAMITY FUND |  |  | b) KALSADA - Konkreto at Ayos na Lansangan Tungo sa Pangkalahatang Kaunlaran
CO - CAPITAL OUTLAY |  |  | c) PRDP - Philippine Rural Development Projects
SEF - SPECIAL EDUCATIONAL UFND |  |  | d) SELAP - Support to Emergency and Livelihood Assistance Project
e) PAMANA - Payapa at Masaganang Pamayanan
f) CBRMC - Community Based Road Maintenance Contracting
g) MBC - Maintenance by Contract
h) PCF-Performance Challenge Fund-DILG
i) FMRDP - Farm to Market Road
j.) CMGP - Conditional Grant to Provinces
k.) OPAPP - Office of the President Adviser on the Peace Process
l.) LGSF-AM - Local Government Support Fund Assistance to Municipalities
Prepared by: | Checked by: | Noted by: |  | Recommending Approval:
RETCHIE A. DE LOS REYES, CE | ELISA A. BARCENA, CE | JIVELLYN B. CO, CE |  | GLENN A. OLANDRIA, CE
Engineer II | Engineer IV- Engineering Dist. 1 | Asst. Provincial Engineer |  | Provincial Engineer
Area Engineer

## Signatures2nd (hidden)
GF- GENERAL FUND |  |  | TF - TRUST FUND (NATIONAL FUNDED PROJECT)
20% DF - 20% DEVELOPMENT FUND |  |  | a) SLRF - Special Local Road Fund
5% CF - 5% CALAMITY FUND |  |  | b) KALSADA - Konkreto at Ayos na Lansangan Tungo sa Pangkalahatang Kaunlaran
CO - CAPITAL OUTLAY |  |  | c) PRDP - Philippine Rural Development Projects
SEF - SPECIAL EDUCATIONAL UFND |  |  | d) SELAP - Support to Emergency and Livelihood Assistance Project
e) PAMANA - Payapa at Masaganang Pamayanan
f) CBRMC - Community Based Road Maintenance Contracting
g) MBC - Maintenance by Contract
h) PCF-Performance Challenge Fund-DILG
i) FMRDP - Farm to Market Road
j.) CMGP - Conditional Grant to Provinces
k.) OPAPP - Office of the President Adviser on the Peace Process
l.) LGSF-AM - Local Government Support Fund Assistance to Municipalities
Prepared by: | Checked by: | Noted by: |  | Recommending Approval:
RETCHIE A. DE LOS REYES, CE | TESSIE G. ABABON | JIVELLYN B. CO, CE |  | GLENN A. OLANDRIA, CE
Engineer II | Engineer IV- Engineering Dist. 2 | Asst. Provincial Engineer |  | Provincial Engineer
Area Engineer