## July 2020 (2) (hidden)
AIP 2019
PROJECT STATUS REPORT
As of: |  |  | August 2020
LEGEND: |  | PLAN & POW APPROVED/ ALLOTED
FOR INSPECTION/TESTING
PLAN/POW FOR APPROVAL
PLAN/POW ONGOING PREPARATION
PENDING
| [TEXT] | RE-ALIGNED/DECLARED AS SAVINGS/CANCELLED
REHAB. OF VARIOUS PROVINCIAL ROADS AND BRIDGES
ITEM NO. | PROJECT TITLE | SOURCE OF FUND | AMOUNT (Php) | REMARKS | RESPONSIBLE OFFICE/PERSON
DISTRICT 1
1 | Rehab. of Jct. Highway Canatan- Dona Andrea | 20% DF CY 2019 | 2000000 | PLAN & POW APPROVED/ ALLOTED
2 | Rehab. of Pamacaun – Lasang Banate Road, Asuncion | 20% DF CY 2019 | 2000000 | PLAN & POW APPROVED/ ALLOTED
3 | Rehab. of Kapalong – Mabantao- Florida Road, Kapalong | 20% DF CY 2019 | 1231000 | PLAN & POW APPROVED/ ALLOTED
4 | Rehab. of Sto. Nino-Palma Gil – Sitio Opao Road | 20% DF CY 2019 | 1901000 | PLAN & POW APPROVED/ ALLOTED
5 | Rehab. of Sto. Nino- Daligdigon- Paiton | 20% DF CY 2019 | 3000000 | PLAN & POW APPROVED/ ALLOTED
6 | Rehab. of Jct. Paiton- Mibolo, Talaingod | 20% DF CY 2019 | 6000000 | PLAN & POW APPROVED/ ALLOTED
7 | Rehab. of Monte- Dujali - Gupitan | 20% DF CY 2019 | 1200000 | PLAN & POW APPROVED/ ALLOTED
8 | Rehab. of Jct. Sawata- Bdry. Binasbas | 20% DF CY 2019 | 500000 | PLAN & POW APPROVED/ ALLOTED
9 | Rehab. of New Corella-Saug Road, New Corella | 20% DF CY 2019 | 6500000 | PLAN & POW APPROVED/ ALLOTED
10 | Rehab. of Jct. Monte Carlo – Upper Cabaywa-Canatan Road | 20% DF CY 2019 | 8838000 | PLAN & POW APPROVED/ ALLOTED
11 | Rehab. of Purok 10 Pob. Road, New Corella | 20% DF CY 2019 | 500000 | PLAN & POW APPROVED/ ALLOTED
12 | Rehab. of Purok 7 Pob.-Jct. New Sambog | 20% DF CY 2019 | 1815000 | PLAN & POW APPROVED/ ALLOTED
13 | Rehab. of Del Pilar- El Unido Road, New Corella | 20% DF CY 2019 | 1389000 | PLAN & POW APPROVED/ ALLOTED
14 | Rehab. of Junction Highway Gabuyan – Semong - Dagohoy | 20% DF CY 2019 | 2492000 | Re-aligned to Impvt. of Km. 9 Sagayen-Sawata Provincial Road Phase II (AIP 3rd Revision CY 2019/ SB No. 4 CY 2019)
15 | Rehab. of Daligdigon – Lumabag Road | 20% DF CY 2019 | 680000 | Re-aligned to Impvt. of Km. 9 Sagayen-Sawata Provincial Road Phase II (AIP 3rd Revision CY 2019/ SB No. 4 CY 2019)
16 | Rehab. of Bdry. Tagum – Baca – New Corella | 20% DF CY 2019 | 1419029 | Re-aligned to Impvt. of Km. 9 Sagayen-Sawata Provincial Road Phase II (AIP 3rd Revision CY 2019/ SB No. 4 CY 2019)
17 | Impvt. of Km. 9 Sagayen – Sawata Provincial Road Phase II | SB No. 4 CY 2019 | 4591029 | PLAN & POW APPROVED/ ALLOTED
SUB-TOTAL |  |  | 41465029
ITEM NO. | PROJECT TITLE | SOURCE OF FUND | AMOUNT (Php) | REMARKS | RESPONSIBLE OFFICE/PERSON
DISTRICT 2
1 | Rehab./ Impvt. of Jct. Highway Sto. Nino – Cebulano Provincial Road | 20% DF CY 2019 | 1045000 | PLAN & POW APPROVED/ ALLOTED
2 | Rehab./Impvt. of Jct. Highway-Tubod-Bagong Silang Provincial Road | 20% DF CY 2019 | 515000 | PLAN & POW APPROVED/ ALLOTED
3 | Rehab/Impvt. of Basa – Tubod Provincial Road | 20% DF CY 2019 | 1000000 | PLAN & POW APPROVED/ ALLOTED
4 | Rehab./Impvt. of Tubod – Pilar Provincial Road | 20% DF CY 2019 | 395000 | PLAN & POW APPROVED/ ALLOTED
|  |  | 15605000 | PLAN & POW APPROVED/ ALLOTED
5 | Rehab./Impvt. of Cebulano – Loceta Provincial Road | 20% DF CY 2019 | 390000 | PLAN & POW APPROVED/ ALLOTED
6 | Rehab./Impvt. of Lower Asuncion – Upper Asuncion Provincial Road | 20% DF CY 2019 | 295000 | PLAN & POW APPROVED/ ALLOTED
7 | Rehab./ Imvpt. Of Jct. Highway – Sto. Nino – LaPaz - San Vicente Provincial Road | 20% DF CY 2019 | 1220000 | PLAN & POW APPROVED/ ALLOTED
8 | Rehab./Impvt. of Alejal – Alemag Provincial Road | 20% DF CY 2019 | 970000 | PLAN & POW APPROVED/ ALLOTED
9 | Rehab./ Imvpt. Of Mabaus- Cabay –angan Provincial Road | 20% DF CY 2019 | 640000 | PLAN & POW APPROVED/ ALLOTED
10 | Rehab./ Impvt. of Mabaus – Salvacion Provincial Road | 20% DF CY 2019 | 280000 | PLAN & POW APPROVED/ ALLOTED
11 | Rehab./ Imvpt. Of Dalisay – Mabuhay Provincial Road | 20% DF CY 2019 | 1000000 | PLAN & POW APPROVED/ ALLOTED
12 | Rehab./ Imvpt. Of Sitio Malaga – Tibulao Provincial Road | 20% DF CY 2019 | 1000000 | PLAN & POW APPROVED/ ALLOTED
13 | Rehab./Impvt. of Dujali – Tanglaw Provincial Road | 20% DF CY 2019 | 2075000 | PLAN & POW APPROVED/ ALLOTED
14 | Rehab./ Imvpt. Of Dujali – New Casay Provincial Road | 20% DF CY 2019 | 640000 | PLAN & POW APPROVED/ ALLOTED
15 | Rehab./Impvt. of New Casay – Bugtong Talisay Provincial Road | 20% DF CY 2019 | 450000 | PLAN & POW APPROVED/ ALLOTED
16 | Rehab./ Imvpt. Of Cabay –angan – Esperanza Provincial Road | 20% DF CY 2019 | 1300000 | PLAN & POW APPROVED/ ALLOTED
17 | Rehab./ Impvt. of Prk. 6 Cabay-angan – Esti Provincial Road | 20% DF CY 2019 | 220000 | PLAN & POW APPROVED/ ALLOTED
18 | Rehab./ Impvt. of Dujali – Sitio Pawas Provincial Road | 20% DF CY 2019 | 250000 | PLAN & POW APPROVED/ ALLOTED
19 | Rehab./ Impvt. of Purok 1 to Purok 2 Sitio Pawas Provincial Road | 20% DF CY 2019 | 280000 | PLAN & POW APPROVED/ ALLOTED
20 | Rehab./Impvt. of San Miguel – Crossing Kinamayan Provincial Road | 20% DF CY 2019 | 560000 | PLAN & POW APPROVED/ ALLOTED
21 | Rehab./ Impvt. of San Miguel – Libertad Provincial Road | 20% DF CY 2019 | 1240000 | PLAN & POW APPROVED/ ALLOTED
22 | Rehab. /impvt. of Bacali – Casig –ang – Libertad Provincial Road | 20% DF CY 2019 | 940000 | PLAN & POW APPROVED/ ALLOTED
23 | Rehab./ Impvt. of Kinamayan – Moslog – Mahayag Provincial Road | 20% DF CY 2019 | 1000000 | PLAN & POW APPROVED/ ALLOTED
24 | Rehab./ Impvt. of San Miguel – Moslog – Kinamayan Provincial Road | 20% DF CY 2019 | 1000000 | PLAN & POW APPROVED/ ALLOTED
25 | Rehab./ Impvt. of Kinamayan – Lunga – og Provincial Road | 20% DF CY 2019 | 520000 | PLAN & POW APPROVED/ ALLOTED
26 | Rehab. Impvt. of Mugas – Lanatad Provincial Road | 20% DF CY 2019 | 500000 | PLAN & POW APPROVED/ ALLOTED
27 | Rehab./ Impvt. of New Katipunan – Pantaron Provincial Road | 20% DF CY 2019 | 395000 | PLAN & POW APPROVED/ ALLOTED
28 | Rehab./ Impvt. of Fd. RD. 2 – Sto. Tomas – Magwawa Provincial Road | 20% DF CY 2019 | 3, 575,000.00 | PLAN & POW APPROVED/ ALLOTED
29 | Rehab./ Impvt. of Nafco – Bobongon Provincial Road | 20% DF CY 2019 | 540000 | PLAN & POW APPROVED/ ALLOTED
30 | Rehab./ Impvt. of Jct. Highway – Tanglaw Provincial Road | 20% DF CY 2019 | 1100000 | PLAN & POW APPROVED/ ALLOTED
31 | Rehab./ Impvt. of Kimamon – Lunga –og – Talomo Provincial Road | 20% DF CY 2019 | 1800000 | PLAN & POW APPROVED/ ALLOTED
32 | Rehab./ Impvt. of Prk. Narafil – Prk. Daisy Magupising Provincial Road | 20% DF CY 2019 | 300117 | PLAN & POW APPROVED/ ALLOTED
33 | Rehab./Impvt. of Boundary Tagum –Crossing Kinamayan - Sto. Tomas Provincial Road | 20% DF CY 2019 | 3700000 | PLAN & POW APPROVED/ ALLOTED
SUB-TOTAL |  |  | 43165117
VARIOUS LOCAL ROADS AND DRAINAGE DEVELOPMENTS
ITEM NO. | PROJECT TITLE | SOURCE OF FUND | AMOUNT (Php) | REMARKS | RESPONSIBLE OFFICE/PERSON
DISTRICT 1
1 | Rehab./Impvt. of San Juan-New Talisay Prov'l. Road with Drainage | 20% DF CY 2019 | 1000000 | PLAN & POW APPROVED/ ALLOTED
2 | Repair/Rehab. of Concrete Road Jct. Suaon-Libuton, Kapalong | 20% DF CY 2019 (SB No. 3) | 1000000 | PLAN & POW APPROVED/ ALLOTED
3 | Impvt. of Cross Drainage along Saug-Sonlon-Bdry. Longganapan | 20% DF CY 2019 | 3000000 | PLAN & POW APPROVED/ ALLOTED
4 | Rehab./Impvt. of Sto. Nino -Palma Gil- Sitio Opao Provincial Road with Drainage | 20% DF CY 2019 | 3000000 | PLAN & POW APPROVED/ ALLOTED
SUB-TOTAL |  |  | 8000000
ITEM NO. | PROJECT TITLE | SOURCE OF FUND | AMOUNT (Php) | REMARKS | RESPONSIBLE OFFICE/PERSON
DISTRICT 2
1 | Rehab. of Anibongan-Salvacion-Cabay-angan Provincial Road with Drainage | 20% DF CY 2019 | 2000000 | PLAN & POW APPROVED/ ALLOTED
2 | Rehab. of Dujali-Pawas-San Vicente Provincial Rd. | 20% DF CY 2019 (SB No. 3) | -2000000 | Project title was amended in the 2nd AIP revision. But the project amount was reduced to P1,102,900.00 from P2,000,000.00 to fund new projects that was included in the AIP 3rd revision CY 2019 last Aug. 27, 2019 (Refer to items no. 5-7)
|  |  | 1102900 | PLAN & POW APPROVED/ ALLOTED
3 | Rehab./Impvt. Of Jct. Hi-way Ising- Magsaysay Provincial Road with Drainage | 20% DF CY 2019 | 1500000 | PLAN & POW APPROVED/ ALLOTED
4 | Rehab/Impvt. of Sto. Tomas-Boundary Mamacao Prov'l. Road | 20% DF CY 2019 | 1500000 | PLAN & POW APPROVED/ ALLOTED
Funds from Rehab. of Dujali- Pawas – San Vicente Provincial Road ( AIP 3rd Revision CY 2019 /SB 4 CY 2019)
5 | Rehab. of Local Roads at Dalisay- Manay Road Section, Panabo City | SB No. 4 CY 2019 | 246100 | PLAN & POW APPROVED/ ALLOTED
6 | Rehab. of Local Roads at Sta. Cruz-Jct. Tagpore-Buenavista Road Section, Panabo City | SB No. 4 CY 2019 | 431000 | PLAN & POW APPROVED/ ALLOTED
7 | Rehab. of Local Roads at Taba- Bucana Road Section | SB No. 4 CY 2019 | 220000 | PLAN & POW APPROVED/ ALLOTED
SUB-TOTAL |  |  | 7000000
VARIOUS WATER SYSTEM DEVELOPMENT PROJECT
ITEM NO. | PROJECT TITLE | SOURCE OF FUND | AMOUNT (Php) | REMARKS | RESPONSIBLE OFFICE/PERSON
Conduct of Geo-resistivity/Drilling Test of proposed Site
1 | 1. Const. of PWS in Brgy.Kiotoy, Panabo City | 20% DF CY 2019 | 62500 | For re-alignment to Const. of One (1) unit Dugwell with Jetmatic Pump, Bahay Pag-asa, New Corella
2 | 2. Const. of PWS in Brgy. Linusutan, Talikud District, IGCS | 20% DF CY 2019 | 62500 | For cancellation due to the purchase of geo-resistivity equipment but procurement still on process
3 | 3. Const. of PWS in Brgy. San Miguel, Samal District, IGCS | 20% DF CY 2019 | 62500 | For cancellation due to the purchase of geo-resistivity equipment but procurement still on process
4 | 4. Const. of PWS in Brgy. Cacao, Panabo City | 20% DF CY 2019 | 62500 | For re –alignment to Const. of One (1) unit Dugwell with Jetmatic Pump, Women’s Center, New Corella
Construction of Water System Project in Component LGUs
5 | Impvt. of Potable Water System in Consolacion, Panabo City | 20% DF CY 2019 | 500000 | PLAN & POW APPROVED/ ALLOTED
6 | Impvt. Of Potable Water System in Tagbitan-ag,Samal, Dist. IGCS | 20% DF CY 2019 | 500000 | PLAN & POW APPROVED/ ALLOTED
7 | Impvt. of Potable Water System in San Antonio, Babak,Dist. IGCS | 20% DF CY 2019 | 500000 | PLAN & POW APPROVED/ ALLOTED
8 | Original AIP - Impvt. of Potable Water System in Mambago-A, Penaplata Dist. , IGCS | 20% DF CY 2019/ | 500000 | Amended in the AIP 2nd Revision to change the location from Penaplata to Samal Dist
| Amended AIP – Impvt. of Potable Water System at Brgy. Mambago A, Samal Dist., IGACOS | SB No. 3 CY 2019 |  | PLAN & POW APPROVED/ ALLOTED
9 | Const. of PWS in Brgy. Linao, San Isidro | 20% DF CY 2019 | 500000 | PLAN & POW APPROVED/ ALLOTED
10 | Const.of PWS in Prk. Mamalian, Datu Balong, San isidro | 20% DF CY 2019 | 500000 | For declaration of savings because the spring water source is not feasible for development
11 | Const. of PWS in Brgy. Sagayen, Asuncion | 20% DF CY 2019 | 500000 | PLAN & POW APPROVED/ ALLOTED
12 | Const. of PWS in Buenavista, Panabo City | 20% DF CY 2019 |  | PLAN & POW APPROVED/ ALLOTED
13 | Const. of PWS in Brgy. Kiotoy, Panabo City | 20% DF CY 2019 | 500000 | For geo-resistivity survey c/o Amamio | R. Amamio - PDPM
14 | Original AIP - Const. of PWS in Linusotan, Talicud Dist., IGCS | 20% DF CY 2019 | -500000 | Additional 800,000.00 from Const. of PWS in Purok 2, Pag asa, Kapalong which was funded by OPAPP CY 2018)
| Amended AIP – Construction of PWS in Brgy. Linusotan, Kaputian Dist, IGACOS | SB No. 3 CY 2019 | 1300000 | PLAN & POW APPROVED/ ALLOTED
15 | Original AIP – Rehab. of PWS in San Miguel, Babak Dist., IGACOS | 20% DF CY 2019 | 500000 | Amended in the 2nd AIP Revision to change the location from Babak to Samal Dist.
| Amended AIP – Rehab. of PWS in San Miguel, Samal Dist. IGACOS |  |  | Plan for revision | R. Amamio - PDPM
16 | Const. of PWS in Brgy. Cacao, Panabo City | 20% DF CY 2019 | 500000 | For amendment indicating phase 2 since the project title is the same with stimulus project (letter will be submitted by Mr. Amamio-focal person for water system for explanation)
17 | Const. of PWS in Purok 7-A & B, Capungagan, Kapalong | 20% DF CY 2019 | 500000 | PLAN & POW APPROVED/ ALLOTED
18 | Const. of PWS in Purok 2, Pag asa, Kapalong | 20% DF CY 2019 | 800000 | Declared as savings in the AIP 2nd Revision to fund for the Rehab. of Water System in PEEDO –LPRRC, Brgy. Poblacion, New Corella (Project was funded by OPAPP CY 2018)
19 | Rehab. of Potable Water System in Pangubatan, Kaputian Dist., IGCS | 20% DF CY 2019 | 850000 | Declared as savings in the AIP 2nd Revision to fund for the Construction of PWS in Brgy Linusotan, Kaputian Dist. IGACOS (Project was funded by OPAPP CY 2018)
20 | Original AIP – Procurement of materials for the installation of Shallow Tube wells for irrigation & const. of Machinery Shed for storage of open surface pump for PAGRO | 20% DF CY 2019 | 1600000 | Amended
| Amended AIP - Inst. of Shll Tube Wells & Const. of Mch Shed |  |  | PLAN & POW APPROVED/ ALLOTED
SUB-TOTAL |  |  | 9800000
2nd Revision
1 | Installation of Potable Water System, Pandapan, Tagum City | 20% DF CY 2018 | 1250000 | For geo-resistivity survey at Brgy. site
2 | Rehab. of Water System in PEEDO-LPRRC, Brgy. Poblacion, New Corella | SB No. 3 CY 2019 | 500000 | PLAN & POW APPROVED/ ALLOTED
SUB-TOTAL |  |  | 1750000
VARIOUS WATER SYSTEM DEVELOPMENT PROJECT
ITEM NO. | PROJECT TITLE | SOURCE OF FUND | AMOUNT (Php) | REMARKS | RESPONSIBLE OFFICE/PERSON
1 | Completion of Perimeter Steel Fence at Lungaog E/S Brgy. Lungaog, Sto. Tomas | 20% DF CY 2019 | 1630000 | PLAN & POW APPROVED/ ALLOTED
2 | Repair Bay for Disaster Quick Response Equipment at PEO Compound, Government Center Mankilam, Tagum City | 20% DF CY 2019 | 1000000 | PLAN & POW APPROVED/ ALLOTED
3 | Repair/Impvt. of Municipal Tribal Hall at New Corella | 20% DF CY 2019 | 1500000 | PLAN & POW APPROVED/ ALLOTED
4 | Const. of Gym Bleacher at Suaybaguio Rina Elem. School | 20% DF CY 2019 | 1000000 | PLAN & POW APPROVED/ ALLOTED
5 | Repair of Dacudao Health Center at Dacudao, San Isidro | 20% DF CY 2019 | 1000000 | PLAN & POW APPROVED/ ALLOTED
6 | Const. of Perimeter Fence at Sto. Nino NASECO Integrated School with Tugas Extension, Sto. Nino, Talaingod | 20% DF CY 2019 | 2000000 | PLAN & POW APPROVED/ ALLOTED
7 | Const. of Multi-Purposr Hall Center (Cultural Heritage in Ancestral Domain of Ata- Manobo | 20% DF CY 2019 | 2000000 | Fund re-aligned to GIDAS projects
8 | Const. of IP Women’s Multi-Purpose Bldg. at Cabadiangan, Sto. Nino, Talaingod | 20% DF CY 2019 | 2000000 | PLAN & POW APPROVED/ ALLOTED
9 | Extension of PAGRO Training Center & Ground Dev’t. | 20% DF CY 2019 | 1000000 | PLAN & POW APPROVED/ ALLOTED
10 | Construction of Abilidad Training Center, Government Center, Mankilam, Tagum City | 20% DF CY 2019 | 7000000 | Fund re-aligned to GIDAS projects
11 | Const. of DDN Hospital Carmen Zone Bldg., Phase 2, Carmen, Davao Del Norte | 20% DF CY 2019 | 3620000 | PLAN & POW APPROVED/ ALLOTED
12 | Const. of 1 CL Bldg. at Suawon ES, Suawon, New Corella | 20% DF CY 2019 | 1000000 | PLAN & POW APPROVED/ ALLOTED
13 | Const. of Municipal Tribal Hall, San Isidro | 20% DF CY 2019 | 500000 | PLAN & POW APPROVED/ ALLOTED
14 | Const. of Quail House ( PDNSC Extension Campus)Salawao,, Sto. Nino, Talaingod | 20% DF CY 2019 | 750000 | PLAN & POW APPROVED/ ALLOTED
SUB-TOTAL |  |  | 26000000
ELECTRIFICATION
ITEM NO. | PROJECT TITLE | SOURCE OF FUND | AMOUNT (Php) | REMARKS | RESPONSIBLE OFFICE/PERSON
1 | Rural Electrification at Del Monte, New Corella | 20% DF CY 2019 | 3000000 | PLAN & POW APPROVED/ ALLOTED
2 | Rural Electrification at Sitio Bundok San Roque, Brgy. New Cortez, New Corella | 20% DF CY 2019 | 1000000 | PLAN & POW APPROVED/ ALLOTED
3 | Rural Electrification at Brgy. Poblacion, Kaputian, IGACOS ( Sitio Sagrada) | 20% DF CY 2019 | 1000000 | PLAN & POW APPROVED/ ALLOTED
INFRASTRUCTURE DEVELOPMENT PROGRAM
ITEM NO. | PROJECT TITLE | SOURCE OF FUND | AMOUNT (Php) | REMARKS | RESPONSIBLE OFFICE/PERSON
1 | Purchase of Geo – Resisitivity Instrument |  | 6567412 | Delivered
PEACE AND ORDER PROGRAM (GIDAS Project)
ITEM NO. | PROJECT TITLE | SOURCE OF FUND | AMOUNT (Php) | REMARKS | RESPONSIBLE OFFICE/PERSON
1 | Provincial Livestock & Poultry Multiplier Farm Road Network Const., Sitio Salawao, Sto. Nino, Talaingod | SB No. 4 CY 2019 | 5500000 | PLAN & POW APPROVED/ ALLOTED
2 | Proposed Road Opening of Tawinian – Tapayanon Road Section | SB No. 4 CY 2019 | 10000000 | PLAN & POW APPROVED/ ALLOTED
3 | Rehab. of San Jose-Sitio Mahayahay – Magwawa Provincial Road, Sto. Tomas | SB No. 4 CY 2019 | 1000000 | PLAN & POW APPROVED/ ALLOTED
SUB-TOTAL |  |  | 16500000
FOR FUND TRANSFER
ITEM NO. | PROJECT TITLE | SOURCE OF FUND | AMOUNT (Php) | REMARKS | RESPONSIBLE OFFICE/PERSON
1 | Purchase of Lot Cemetery, Cambanogoy, Asuncion | SB No. 1 CY 2019 | 1500000 | Documents for the fund transfer to be complied by the LGUs. Letter sent dated June 18, 2019 | LGU - Asuncion
2 | Purchase of Lot Cemetery, San Roque, New Corella | SB No. 1 CY 2019 | 500000 | Documents for the fund transfer to be complied by the LGUs. Letter sent dated June 18, 2019 | LGU - Asuncion
SOCIAL PROTECTION & INTERVENTION PROGRAM (PSWDO)
ITEM NO. | PROJECT TITLE | SOURCE OF FUND | AMOUNT (Php) | REMARKS | RESPONSIBLE OFFICE/PERSON
1 | Const. of Multi Purpose/Evacuation Center Phase 1 Duterte St, Poblacion, New Corella | 20% DF CY 2019 | 2000000 | PLAN & POW APPROVED/ ALLOTED
TRUST FUND/ OTHER SOURCES
ITEM NO. | PROJECT TITLE | SOURCE OF FUND | AMOUNT (Php) | REMARKS | RESPONSIBLE OFFICE/PERSON
1 | Poultry House and Training Center, Sto. Nino, Talaingod | Multiplier Farm under DA –Livestock Banner Program CY 2018 | 500000 | PLAN & POW APPROVED/ ALLOTED | District 1
2 | Establishment of Multiplier Farm Project, Sto. Nino, Talalingod | DA Central Office – Establishment of Native Chicken Production Techno Demo Farm | 500000 | PLAN & POW APPROVED/ ALLOTED | District 1
3 | Road Upgrading of Jct. Highway Sto. Nino – La Paz – San Vicente Provincial Road | CMGP 2019 | 80639854 | PLAN & POW APPROVED/ ALLOTED | District 2
4 | Road Upgrading of Jct. Highway Sto. Nino – Kabankalan - La Paz Provincial Road | CMGP 2019 | 44561686.35 | PLAN & POW APPROVED/ ALLOTED | District 2
5 | Road Upgrading of Kapalong – Mabantao – Florida Provincial Road with Bridge Component | CMGP 2019 | 15435008.65 | PLAN & POW APPROVED/ ALLOTED | District 1
6 | Concreting of Visayan Village - Purok Exodus - Purok Rafael, Brgy.Magugpo South | LGSF CY 2019 | 40000000 | PLAN & POW APPROVED/ ALLOTED | District 1
7 | Rehabilitation of Dasing To Monte Carlo FMR, Del Pilar | LGSF CY 2019 | 40000000 | PLAN & POW APPROVED/ ALLOTED | District 1
8 | Road Upgrading of Farm To Market Road at. Brgy. Buenavista | LGSF CY 2019 | 40000000 | PLAN & POW APPROVED/ ALLOTED | District 2
9 | Road Upgrading of New Katipunan - Pantaron Provincial Road | LGSF CY 2019 | 30000000 | PLAN & POW APPROVED/ ALLOTED | District 2
| Prepared by: | Checked by:
| THESSA R. DELA CRUZ, CE | ARSENIO T. CANILLADA III, CE |  | JULMANDY D. LUMOSBOG, UAP
| Engineer - I | Engineer - III |  | Architect - III
| Reviewed by: | Attested by: |  | Submitted to:
| EDWIN S. MISA, CE | JIVELLYN B. CO, CE, MPA |  | GLENN A. OLANDRIA, CE
| Engineer - IV | Asst. PG-Dept. Head |  | PG-Dept. Head

## August 2020 AIP 2019 DIST I (hidden)
AIP 2019
PLANNING STATUS REPORT
|  | As of: | August 2020
LEGEND: |  | PLAN & POW APPROVED/ ALLOTED
FOR INSPECTION/TESTING
PLAN/POW FOR APPROVAL
PLAN/POW ONGOING PREPARATION
PENDING
| [TEXT] | RE-ALIGNED/DECLARED AS SAVINGS/CANCELLED
DISTRICT 1
ITEM NO. | PROJECT TITLE | SOURCE OF FUND | AMOUNT (Php) | REMARKS | RESPONSIBLE OFFICE/PERSON
1 | Rehab. of Jct. Highway Canatan- Dona Andrea | 20% DF CY 2019 | 2000000 | PLAN & POW APPROVED/ ALLOTED
2 | Rehab. of Pamacaun – Lasang Banate Road, Asuncion | 20% DF CY 2019 | 2000000 | PLAN & POW APPROVED/ ALLOTED
3 | Rehab. of Kapalong – Mabantao- Florida Road, Kapalong | 20% DF CY 2019 | 1231000 | PLAN & POW APPROVED/ ALLOTED
4 | Rehab. of Sto. Nino-Palma Gil – Sitio Opao Road | 20% DF CY 2019 | 1901000 | PLAN & POW APPROVED/ ALLOTED
5 | Rehab. of Sto. Nino- Daligdigon- Paiton | 20% DF CY 2019 | 3000000 | PLAN & POW APPROVED/ ALLOTED
6 | Rehab. of Jct. Paiton- Mibolo, Talaingod | 20% DF CY 2019 | 6000000 | PLAN & POW APPROVED/ ALLOTED
7 | Rehab. of Monte- Dujali - Gupitan | 20% DF CY 2019 | 1200000 | PLAN & POW APPROVED/ ALLOTED
8 | Rehab. of Jct. Sawata- Bdry. Binasbas | 20% DF CY 2019 | 500000 | PLAN & POW APPROVED/ ALLOTED
9 | Rehab. of New Corella-Saug Road, New Corella | 20% DF CY 2019 | 6500000 | PLAN & POW APPROVED/ ALLOTED
10 | Rehab. of Jct. Monte Carlo – Upper Cabaywa-Canatan Road | 20% DF CY 2019 | 8838000 | PLAN & POW APPROVED/ ALLOTED
11 | Rehab. of Purok 10 Pob. Road, New Corella | 20% DF CY 2019 | 500000 | PLAN & POW APPROVED/ ALLOTED
12 | Rehab. of Purok 7 Pob.-Jct. New Sambog | 20% DF CY 2019 | 1815000 | PLAN & POW APPROVED/ ALLOTED
13 | Rehab. of Del Pilar- El Unido Road, New Corella | 20% DF CY 2019 | 1389000 | PLAN & POW APPROVED/ ALLOTED
14 | Rehab. of Junction Highway Gabuyan – Semong - Dagohoy | 20% DF CY 2019 | 2492000 | Re-aligned to Impvt. of Km. 9 Sagayen-Sawata Provincial Road Phase II (AIP 3rd Revision CY 2019/ SB No. 4 CY 2019)
15 | Rehab. of Daligdigon – Lumabag Road | 20% DF CY 2019 | 680000 | Re-aligned to Impvt. of Km. 9 Sagayen-Sawata Provincial Road Phase II (AIP 3rd Revision CY 2019/ SB No. 4 CY 2019)
16 | Rehab. of Bdry. Tagum – Baca – New Corella | 20% DF CY 2019 | 1419029 | Re-aligned to Impvt. of Km. 9 Sagayen-Sawata Provincial Road Phase II (AIP 3rd Revision CY 2019/ SB No. 4 CY 2019)
17 | Impvt. of Km. 9 Sagayen – Sawata Provincial Road Phase II | SB No. 4 CY 2019 | 4591029 | PLAN & POW APPROVED/ ALLOTED
18 | Repair/Rehab. of Concrete Road Jct. Suaon-Libuton, Kapalong | 20% DF CY 2019 (SB No. 3) | 1000000 | PLAN & POW APPROVED/ ALLOTED
19 | Impvt. of Cross Drainage along Saug-Sonlon-Bdry. Longganapan | 20% DF CY 2019 | 3000000 | PLAN & POW APPROVED/ ALLOTED
20 | Rehab./Impvt. of Sto. Nino -Palma Gil- Sitio Opao Provincial Road with Drainage | 20% DF CY 2019 | 3000000 | PLAN & POW APPROVED/ ALLOTED
21 | Const. of PWS in Brgy. Linao, San Isidro | 20% DF CY 2019 | 500000 | PLAN & POW APPROVED/ ALLOTED
22 | Const.of PWS in Prk. Mamalian, Datu Balong, San isidro | 20% DF CY 2019 | 500000 | For declaration of savings because the spring water source is not feasible for development
23 | Const. of PWS in Brgy. Sagayen, Asuncion | 20% DF CY 2019 | 500000 | PLAN & POW APPROVED/ ALLOTED
24 | Const. of PWS in Purok 7-A & B, Capungagan, Kapalong | 20% DF CY 2019 | 500000 | PLAN & POW APPROVED/ ALLOTED
25 | Const. of PWS in Purok 2, Pag asa, Kapalong | 20% DF CY 2019 | 800000 | Declared as savings in the AIP 2nd Revision to fund for the Rehab. of Water System in PEEDO –LPRRC, Brgy. Poblacion, New Corella (Project was funded by OPAPP CY 2018)
26 | Amended AIP - Inst. of Shll Tube Wells & Const. of Mch Shed |  |  | PLAN & POW APPROVED/ ALLOTED |  | Original AIP – Procurement of materials for the installation of Shallow Tube wells for irrigation & const. of Machinery Shed for storage of open surface pump for PAGRO | 20% DF CY 2019 | 1600000 | Amended
27 | Installation of Potable Water System, Pandapan, Tagum City | 20% DF CY 2018 | 1250000 | Plan preparation ongoing | R. Amamio - PDPM
28 | Rehab. of Water System in PEEDO-LPRRC, Brgy. Poblacion, New Corella | SB No. 3 CY 2019 | 500000 | PLAN & POW APPROVED/ ALLOTED
29 | Repair Bay for Disaster Quick Response Equipment at PEO Compound, Government Center Mankilam, Tagum City | 20% DF CY 2019 | 1000000 | PLAN & POW APPROVED/ ALLOTED
30 | Repair/Impvt. of Municipal Tribal Hall at New Corella | 20% DF CY 2019 | 1500000 | PLAN & POW APPROVED/ ALLOTED
31 | Const. of Gym Bleacher at Suaybaguio Rina Elem. School | 20% DF CY 2019 | 1000000 | PLAN & POW APPROVED/ ALLOTED
32 | Repair of Dacudao Health Center at Dacudao, San Isidro | 20% DF CY 2019 | 1000000 | PLAN & POW APPROVED/ ALLOTED
33 | Const. of Perimeter Fence at Sto. Nino NASECO Integrated School with Tugas Extension, Sto. Nino, Talaingod | 20% DF CY 2019 | 2000000 | PLAN & POW APPROVED/ ALLOTED
34 | Const. of Multi-Purposr Hall Center (Cultural Heritage in Ancestral Domain of Ata- Manobo | 20% DF CY 2019 | 2000000 | Fund re-aligned to GIDAS projects
35 | Const. of IP Women’s Multi-Purpose Bldg. at Cabadiangan, Sto. Nino, Talaingod | 20% DF CY 2019 | 2000000 | PLAN & POW APPROVED/ ALLOTED
36 | Extension of PAGRO Training Center & Ground Dev’t. | 20% DF CY 2019 | 1000000 | PLAN & POW APPROVED/ ALLOTED
37 | Construction of Abilidad Training Center, Government Center, Mankilam, Tagum City | 20% DF CY 2019 | 7000000 | Fund re-aligned to GIDAS projects
38 | Const. of 1 CL Bldg. at Suawon ES, Suawon, New Corella | 20% DF CY 2019 | 1000000 | PLAN & POW APPROVED/ ALLOTED
39 | Const. of Municipal Tribal Hall, San Isidro | 20% DF CY 2019 | 500000 | PLAN & POW APPROVED/ ALLOTED
40 | Const. of Quail House ( PDNSC Extension Campus) Salawao, Sto. Nino, Talaingod | 20% DF CY 2019 | 750000 | PLAN & POW APPROVED/ ALLOTED
41 | Rural Electrification at Del Monte, New Corella | 20% DF CY 2019 | 3000000 | PLAN & POW APPROVED/ ALLOTED
42 | Rural Electrification at Sitio Bundok San Roque, Brgy. New Cortez, New Corella | 20% DF CY 2019 | 1000000 | PLAN & POW APPROVED/ ALLOTED
43 | Purchase of Geo – Resisitivity Instrument |  | 6567412 | Delivered
44 | Provincial Livestock & Poultry Multiplier Farm Road Network Const., Sitio Salawao, Sto. Nino, Talaingod | SB No. 4 CY 2019 | 5500000 | PLAN & POW APPROVED/ ALLOTED
45 | Proposed Road Opening of Tawinian – Tapayanon Road Section | SB No. 4 CY 2019 | 10000000 | PLAN & POW APPROVED/ ALLOTED
46 | Purchase of Lot Cemetery, Cambanogoy, Asuncion | SB No. 1 CY 2019 | 1500000 | Documents for the fund transfer to be complied by the LGUs. Letter sent dated June 18, 2019. Follow up last July 20, 2020. | MLGU - Asuncion
47 | Purchase of Lot Cemetery, San Roque, New Corella | SB No. 1 CY 2019 | 500000 | Lot already purchased by Brgy. San Roque, New Corella. For ammendment for new project of the same location. Resolution already submitted by Brgy. San Roque; Energization of Purok-3 Sitio Libas, Brgy. San Roque. POW preparation ongoing. | PDPM
48 | Const. of Multi Purpose/Evacuation Center Phase 1 Duterte St, Poblacion, New Corella | 20% DF CY 2019 | 2000000 | PLAN & POW APPROVED/ ALLOTED
49 | Poultry House and Training Center, Sto. Nino, Talaingod | Multiplier Farm under DA –Livestock Banner Program CY 2018 | 500000 | PLAN & POW APPROVED/ ALLOTED | District 1
50 | Establishment of Multiplier Farm Project, Sto. Nino, Talalingod | DA Central Office – Establishment of Native Chicken Production Techno Demo Farm | 500000 | PLAN & POW APPROVED/ ALLOTED | District 1
51 | Concreting of Visayan Village - Purok Exodus - Purok Rafael, Brgy. Magugpo South | LGSF CY 2019 | 40000000 | PLAN & POW APPROVED/ ALLOTED | District 1
52 | Rehabilitation of Dasing To Monte Carlo FMR, Del Pilar | LGSF CY 2019 | 40000000 | PLAN & POW APPROVED/ ALLOTED | District 1
| Prepared by: | Checked by:
| PRINCESS M. ALCAZAR, CE | ARSENIO T. CANILLADA III, CE |  | JULMANDY D. LUMOSBOG, UAP
| Engineer - II | Engineer - III |  | Architect - III
| Reviewed by: | Attested by: |  | Submitted to:
| EDWIN S. MISA, CE | JIVELLYN B. CO, CE, MPA |  | GLENN A. OLANDRIA, CE
| Engineer - IV | Asst. PG-Dept. Head |  | PG-Dept. Head

## August 2020 (hidden)
STIMULUS PROJECTS
PROJECT STATUS REPORT
as of August 2020
| LEGEND: |  | PROJECT COMPLETED
COMPLETED BUT COMPLETION DOCS STILL FOR SUBMISSION
PROJECT IMPLEMENTATION ONGOING
PROCUREMENT
PLAN AND POW PREPARATION ONGOING
PENDING/ FOR ACTION
|  | [TEXT] | NO BUDGET/DECLARED AS SAVINGS/CANCELLED
ITEM NO. | BARANGAY | MUNICIPALITY/ CITY | PROJECT TITLE | PLAN | POW | SOURCE OF FUND | AMOUNT (Php) | MODE OF IMPLEMENTATION | DATE STARTED | DATE COMPLETED | DATE STARTED | DATE COMPLETED | STATUS | REMARKS | RESPONSIBLE OFFICE/PERSON
1 | Magatos | Asuncion | Compl. of Magatos E/S Per Fence |  |  | 20% DF CY 2017 | 500000 | Transfer of funds | 2018-06-18 | 2018-07-30 |  |  | PROJECT COMPLETED | COMPLETED
2 | Camansa | Asuncion | Cons. of Covered Court Phase 1 |  |  | 20% DF CY 2017 | 500000 | Transfer of funds | 2018-05-16 | 2018-07-15 |  |  | PROJECT COMPLETED | COMPLETED
3 | Sonlon | Asuncion | 0.5 Km. FMR at Brgy. Site |  |  | 20% DF CY 2017 | 500000 | Transfer of funds | 2018-06-18 | Aug. 10, 2018 |  |  | PROJECT COMPLETED | COMPLETED
4 | Santa Felomina | Asuncion | Cons. of Covered Court Phase 1 |  |  | 20% DF CY 2017 | 500000 | Transfer of funds | 2018-06-18 | Aug. 5, 2018 |  |  | PROJECT COMPLETED | COMPLETED
5 | Buclad | Asuncion | Amended AIP - Impvt. of Brgy. Facilities |  |  | 20% DF CY 2017 | 500000 | Transfer of funds | 2018-04-30 | 2018-06-30 |  |  | PROJECT COMPLETED | COMPLETED |  | Original AIP - Impvt. of Brgy. Hall
6 | Cabaywa | Asuncion | Amended AIP - Improvement of Barangay Hall |  |  | 20% DF CY 2017 | 500000 | Transfer of funds | 2018-05-18 | 2018-07-02 |  |  | PROJECT COMPLETED | COMPLETED |  | Original AIP - Impvt. of Brgy. Hall/Covered Court
7 | Napungas | Asuncion | Impvt. of Multi-Purpose Bldg. |  |  | 20% DF CY 2017 | 500000 | Transfer of funds | 2018-06-16 | 2018-06-30 |  |  | PROJECT COMPLETED | COMPLETED
8 | Cambanogoy | Asuncion | Amended AIP - Const. of Nutrition Building Phase 1 |  |  | 20% DF CY 2017 | 500000 | Transfer of funds | 2018-06-16 | 2018-07-15 |  |  | PROJECT COMPLETED | COMPLETED |  | Original AIP - Cons. of Nutrition Center
9 | New Loon | Asuncion | Rehab. of 2" Pipelines of Water System at Prk. 1 |  |  | 20% DF CY 2017 | 500000 | Transfer of funds | 2018-06-10 | Aug. 8, 2018 |  |  | PROJECT COMPLETED | COMPLETED
10 | Binancian | Asuncion | Cons. Of Multi-Purpose Stage |  |  | 20% DF CY 2017 | 500000 | Transfer of funds | 2018-05-18 | Aug. 16, 2018 |  |  | PROJECT COMPLETED | COMPLETED
11 | Sagayen | Asuncion | Cons. Of Water Reservoir & Purchase of P.E. Pipelines |  |  | 20% DF CY 2017 | 500000 | Transfer of funds |  |  |  |  | PENDING/ FOR ACTION | Project not implemented due to non availability of water source during drilling. Awaiting for the official documents from Brgy. Sagayen and MLGU - Asuncion for the cancellation of the project. | Engr. Cuajao - MLGU Asuncion
12 | Buan | Asuncion | Cons. Of Covered Court Phase 1 |  |  | 20% DF CY 2017 | 500000 | Transfer of funds | 2018-06-01 | 2018-07-30 |  |  | PROJECT COMPLETED | COMPLETED
13 | Canatan | Asuncion | Const. of Bleachers and Canopy |  |  | GF CY 2018 | 500000 | Transfer of funds |  |  |  |  | COMPLETED BUT COMPLETION DOCS STILL FOR SUBMISSION | COMPLETED - PCR & other completion documents for submission PCR, SWA, Before and after Pictures | Engr. Cuajao - MLGU Asuncion
15 | Camoning | Asuncion | Const. of Canopy |  |  | GF CY 2018 | 500000 | Transfer of funds |  |  |  |  | COMPLETED BUT COMPLETION DOCS STILL FOR SUBMISSION | COMPLETED - PCR & other completion documents for submission PCR, SWA, Before and after Pictures | Engr. Cuajao - MLGU Asuncion
17 | San Vicente | Asuncion | Construction of Covered Court |  |  | GF CY 2018 | 500000 | Transfer of funds |  |  |  |  | COMPLETED BUT COMPLETION DOCS STILL FOR SUBMISSION | COMPLETED - PCR & other completion documents for submission PCR, SWA, Before and after Pictures | Engr. Cuajao - MLGU Asuncion
20 | New Bantayan | Asuncion | Rehab. of Multi-purpose Hall |  |  | 20% DF CY 2019 | 500000 | Transfer of funds |  |  |  |  | COMPLETED BUT COMPLETION DOCS STILL FOR SUBMISSION | COMPLETED - PCR & other completion documents for submission PCR, SWA, Before and after Pictures | Engr. Cuajao - MLGU Asuncion
21 | Binancian | Asuncion | Consruction. of Multi- Purpose Hall at Liguyon E/S |  |  | SB No. 5 CY 2018 | 1250000 | Transfer of funds |  |  |  |  | COMPLETED BUT COMPLETION DOCS STILL FOR SUBMISSION | COMPLETED - PCR & other completion documents for submission PCR, SWA, Before and after Pictures | Engr. Cuajao - MLGU Asuncion
22 | Binancian | Asuncion | Consruction. of Multi- Purpose Hall at Rizal E/S |  |  | SB No. 5 CY 2018 | 1250000 | Transfer of funds |  |  |  |  | COMPLETED BUT COMPLETION DOCS STILL FOR SUBMISSION | COMPLETED - PCR & other completion documents for submission PCR, SWA, Before and after Pictures | Engr. Cuajao - MLGU Asuncion
26 | Concepcion | Asuncion | Rehab./Improvement of FMR, Purok 3, 7 & 8 |  |  | SB No. 1 CY 2019 | 500000 | Transfer of funds |  |  |  |  | PENDING/ FOR ACTION | Resumption of Work on August 4, 2020 | Engr. Cuajao - MLGU Asuncion
28 | Concepcion | Asuncion | Installation of Bleacher for the Brgy. Gym |  |  | SB No. 1 CY 2019 | 1000000 | Transfer of funds |  |  |  |  | COMPLETED BUT COMPLETION DOCS STILL FOR SUBMISSION | COMPLETED - PCR & other completion documents for submission PCR, SWA, Before and after Pictures | Engr. Cuajao - MLGU Asuncion
29 | New Santiago | Asuncion | Concreting of FMR |  |  | SB No. 1 CY 2019 | 2500000 | Transfer of funds |  |  |  |  | COMPLETED BUT COMPLETION DOCS STILL FOR SUBMISSION | COMPLETED - PCR & other completion documents for submission PCR, SWA, Before and after Pictures | Engr. Cuajao - MLGU Asuncion
32 | Buan | Asuncion | Construction of Multi-Purpose Covered Court |  |  |  | 2500000 | Transfer of funds |  |  |  |  | COMPLETED BUT COMPLETION DOCS STILL FOR SUBMISSION | COMPLETED - PCR & other completion documents for submission PCR, SWA, Before and after Pictures | Engr. Cuajao - MLGU Asuncion
33 | Pamacaun | Asuncion | Construction of Multi-Purpose Covered Court |  |  |  | 2500000 | Transfer of funds |  |  |  |  | COMPLETED BUT COMPLETION DOCS STILL FOR SUBMISSION | COMPLETED - PCR & other completion documents for submission PCR, SWA, Before and after Pictures | Engr. Cuajao - MLGU Asuncion
34 | New Cortez | New Corella | Fabrication of Bleachers |  |  | 20% DF CY 2017 | 500000 | Transfer of funds | 2018-06-15 | 2018-07-31 |  |  | PROJECT COMPLETED | COMPLETED
35 | Santa Fe | New Corella | Road Rehabilitation At Prk 1 - Prk 5 |  |  | 20% DF CY 2017 | 500000 | Transfer of funds | 2020-08-25 |  |  |  | PROJECT IMPLEMENTATION ONGOING | On-going | Engr. Dogoldogol - MLGU New Corella
36 | Macgum | New Corella | Rehab. of Potable Water In Prk. 2,3,3a,3b & 6 |  |  | 20% DF CY 2017 | 500000 | Transfer of funds |  |  |  |  | PROJECT COMPLETED | COMPLETED
37 | New Sambog | New Corella | Amended AIP - Renov./Impv't. of Brgy. Hall |  |  | 20% DF CY 2017 | 500000 | Transfer of funds |  | Aug. 18, 2018 |  |  | PROJECT COMPLETED | COMPLETED |  | Original AIP - Renov. of Brgy. Hall & Compl. of Covered C. Flooring
38 | San Jose | New Corella | Cons. Of Multi-Purpose Bldg. |  |  | 20% DF CY 2017 | 500000 | Transfer of funds |  |  |  |  | PROJECT COMPLETED | COMPLETED
39 | Patrocenio | New Corella | Amended POW - Renovation/Impv't. Of Brgy. Hall |  |  | 20% DF CY 2017 | 500000 | Transfer of funds |  | Nov. 19, 2018 |  |  | PROJECT COMPLETED | COMPLETED |  | Original AIP - Renov. of Brgy. Hall
40 | Mambing | New Corella | Amended AIP - Completion of Covered Court/Gym |  |  | 20% DF CY 2017 | 500000 | Transfer of funds |  | 2018-07-15 |  |  | PROJECT COMPLETED | COMPLETED |  | Original AIP - Const. of 1 CL School Building
41 | Carcor | New Corella | Const. of Footbridge w/ Railings |  |  | 20% DF CY 2017 | 500000 | Transfer of funds |  | 2018-07-30 |  |  | PROJECT COMPLETED | COMPLETED
42 | Del Monte | New Corella | Const. of Concrete Fence of Lataban Elem. School |  |  | 20% DF CY 2017 | 500000 | Transfer of funds |  | Dec, 2018 |  |  | PROJECT COMPLETED | COMPLETED
43 | New Bohol | New Corella | Amended AIP - Improvement of Covered Court |  |  | 20% DF CY 2017 | 500000 | Transfer of funds |  | Aug. 15, 2018 |  |  | PROJECT COMPLETED | COMPLETED |  | Original AIP - Completion of Covered Court
44 | Sta. Cruz | New Corella | Const. of Concrete Bleachers |  |  | GF CY 2018 | 500000 | Transfer of funds | 2019-07-16 | Sept. 30, 2019 |  |  | PROJECT COMPLETED | COMPLETED - PCR & pictures submitted Feb. 7, 2016
45 | San Roque | New Corella | Completion of Mini Gym @ Prk.2 |  |  | GF CY 2018 | 500000 | Transfer of funds | 2019-07-26 | Sept. 30, 2019 |  |  | PROJECT COMPLETED | COMPLETED - PCR & pictures submitted Feb. 7, 2016
46 | Sto. Niño | New Corella | Completion of Covered Court |  |  | GF CY 2018 | 500000 | Transfer of funds | Sept. 16, 2019 | Dec. 15, 2019 |  |  | PROJECT COMPLETED | COMPLETED - PCR & pictures submitted Feb. 7, 2017
47 | Suawon | New Corella | Const. of Public Market |  |  | GF CY 2018 | 500000 | Transfer of funds | 2019-07-22 | Oct. 15, 2019 |  |  | PROJECT COMPLETED | COMPLETED - PCR & pictures submitted Feb. 7, 2018
48 | Del Pilar | New Corella | Const. of Concrete Line Drainage At Prk. 10 To Prk. 6 |  |  | SB No. 4 CY 2018 | 500000 | Transfer of funds | Aug. 5, 2019 | Oct. 15, 2019 |  |  | PROJECT COMPLETED | COMPLETED - PCR & pictures submitted Feb. 7, 2019
49 | Mesaoy | New Corella | Const. of Stage With Comfort Rooms At Mesaoy Mini-Gym |  |  | GF CY 2018 | 500000 | Transfer of funds | 2019-07-22 | Oct. 15, 2019 |  |  | PROJECT COMPLETED | COMPLETED - PCR & pictures submitted Feb. 7, 2020
50 | Poblacion | New Corella | Construction of 2 Storey Multi-Purpose hall (Brgy. Hall) Phase 1 |  |  | SB No. 5 CY 2018 | 2000000 | Transfer of funds | Nov. 13, 2019 |  |  |  | COMPLETED BUT COMPLETION DOCS STILL FOR SUBMISSION | COMPLETED - PCR & other completion documents for submission PCR, SWA, Before and after Pictures | Engr. Dogoldogol - MLGU New Corella
52 | El Salvador | New Corella | Const. of Multi-purpose Hall |  |  | 20% DF CY 2019 | 500000 | Transfer of funds | Sept. 16, 2019 | Dec. 15, 2019 |  |  | PROJECT COMPLETED | COMPLETED - PCR & pictures submitted Feb. 7, 2020
54 | Cabidianan | New Corella | Rehab. of Multi-purpose Hall |  |  | 20% DF CY 2019 | 500000 | Transfer of funds | Oct. 22, 2019 | Dec. 31, 2019 |  |  | PROJECT COMPLETED | COMPLETED - PCR & pictures submitted Feb. 7, 2020
55 | Limbaan | New Corella | Const. of Canal Lining |  |  | 20% DF CY 2019 | 500000 | Transfer of funds | Sept. 6, 2019 | Nov. 8, 2019 |  |  | PROJECT COMPLETED | COMPLETED - PCR & pictures submitted Feb. 7, 2020
59 | New Sambog | New Corella | Purchase of Lot for Resettlement Site |  |  | SB No. 1 CY 2019 | 1500000 | Transfer of funds |  |  |  |  | PENDING/ FOR ACTION | Fund transfer pending waiting for the liquidation of the completed project: Const. of Water System. One funding only per fund transfer.
60 | New Sambog | New Corella | Const. of Water System |  |  | SB No. 1 CY 2019 | 1000000 | Transfer of funds | Nov. 3, 2019 |  |  |  | COMPLETED BUT COMPLETION DOCS STILL FOR SUBMISSION | COMPLETED - PCR & other completion documents for submission PCR, SWA, Before and after Pictures | Engr. Dogoldogol - MLGU New Corella
80 | Palma Gil | Talaingod | Amended AIP - Const. of Covered Court Bleacher |  |  | SB No. 4 CY 2018 | 500000 | Transfer of funds |  |  |  |  | PROCUREMENT | Procurement on Process |  | Original AIP - Electrification of Prk 1a - Prk 5a | 20% DF CY 2017
120 | Asuncion | Carmen | Const of Evacuation Center at Prk. 1 |  |  | 20% DF CY 2017 | 500000 | Transfer of funds |  |  |  |  | PROJECT COMPLETED | COMPLETED
121 | Taba | Carmen | Amended AIP - Completion of Evacuation Center Building Phase 3 |  |  | 20% DF CY 2017 | 500000 | Transfer of funds |  | Sept. 19, 2018 |  |  | PROJECT COMPLETED | COMPLETED |  | Original AIP - Completion of Evacuation Center Bldg.
122 | Salvacion | Carmen | Const. of Multi-Purpose Stage @ Prk. 2 |  |  | 20% DF CY 2017 | 500000 | Transfer of funds |  |  |  |  | PROJECT COMPLETED | COMPLETED
124 | Magsaysay | Carmen | Const. of Multi-Purpose Bldg. |  |  | 20% DF CY 2017 | 500000 | Transfer of funds |  |  |  |  | PROJECT COMPLETED | COMPLETED
126 | New Camiling | Carmen | Completion of Covered Court/Stage |  |  | 20% DF CY 2017 | 500000 | Transfer of funds |  |  |  |  | PROJECT COMPLETED | COMPLETED
129 | La Paz | Carmen | Const.of Multi-purpose Hall |  |  | 20% DF CY 2019 | 500000 | Transfer of funds |  |  |  |  | PROJECT COMPLETED | COMPLETED
131 | Mangalcal | Carmen | Const. of Multi-purpose Hall |  |  | 20% DF CY 2019 | 500000 | Transfer of funds |  |  |  |  | PROJECT COMPLETED | COMPLETED
132 | Guadalupe | Carmen | Rehab. of Multi-purpose Hall |  |  | 20% DF CY 2019 | 500000 | Transfer of funds |  |  |  |  | PROJECT COMPLETED | COMPLETED
133 | Mabuhay | Carmen | Const. of Multi-purpose Hall |  |  | 20% DF CY 2019 | 500000 | Transfer of funds |  |  |  |  | PROJECT COMPLETED | COMPLETED
134 | Mabaus | Carmen | Const. of Canal Lining |  |  | 20% DF CY 2019 | 500000 | Transfer of funds |  |  |  |  | PROJECT COMPLETED | COMPLETED
135 | Alejal | Carmen | Rehab. of Evacuation Center |  |  | 20% DF CY 2019 | 500000 | Transfer of funds |  |  |  |  | PROJECT COMPLETED | COMPLETED
136 | Tuganay | Carmen | Completion of Evacuation Center |  |  | 20% DF CY 2019 | 500000 | Transfer of funds |  |  |  |  | PROJECT COMPLETED | COMPLETED
137 | Ising | Carmen | Const. of Multi-purpose Hall |  |  | 20% DF CY 2019 | 500000 | Transfer of funds |  |  |  |  | PROJECT COMPLETED | COMPLETED
138 | Cebulano | Carmen | Rehab. of Multi-purpose Hall |  |  | 20% DF CY 2019 | 500000 | Transfer of funds |  |  |  |  | PROJECT COMPLETED | COMPLETED
139 | Consolacion | Panabo City | Amended AIP - Const. Of Market Stall/Bldg. |  |  | SB No. 4 CY 2018 | 500000 | Transfer of funds | 2019-05-28 |  |  |  | COMPLETED BUT COMPLETION DOCS STILL FOR SUBMISSION | Completed physically; completion docs on process | Engr. Rabanoz - LGU Panabo | Original AIP - Additional Market Bldg.
140 | Upper Licanan | Panabo City | Amended AIP - Rehab. of Multi-Purpose Hall (Covered Court) |  |  | SB No. 4 CY 2018 | 500000 | Transfer of funds |  | Nov. 16, 2019 |  |  | PROJECT COMPLETED | COMPLETED |  | Original AIP - Const. of Footbridge
141 | Sta. Cruz | Panabo City | Brgy. Covered Court Fencing |  |  | 20% DF CY 2017 | 500000 | Transfer of funds | 2019-05-15 | 2019-06-14 |  |  | PROJECT COMPLETED | COMPLETED
142 | Katualan | Panabo City | Const. of Multi-Purpose Bldg. |  |  | 20% DF CY 2017 | 500000 | Transfer of funds | Sept. 20, 2019 | Oct. 12, 2018 |  |  | PROJECT COMPLETED | COMPLETED
143 | Kauswagan | Panabo City | Amended AIP - Impvt. Of Multi-Purpose Gym |  |  | SB No. 4 CY 2018 | 500000 | Transfer of funds |  | Feb. 3, 2020 |  |  | PROJECT COMPLETED | COMPLETED |  | Original AIP - FMR
144 | Katipunan | Panabo City | Const. of Covered Court Bleacher |  |  | 20% DF CY 2017 | 500000 | Transfer of funds | 2018-07-18 | Sept. 10, 2019 |  |  | PROJECT COMPLETED | COMPLETED
145 | Mabunao | Panabo City | Constructionof Brgy. Gymnasium |  |  | 20% DF CY 2017 | 500000 | Transfer of funds | 2019-03-11 | April 10 ,2019 |  |  | PROJECT COMPLETED | COMPLETED
146 | Tibungol | Panabo City | Completion of Footbridge at Prk. 1 |  |  | 20% DF CY 2017 | 500000 | Transfer of funds | Dec. 13, 2018 | Feb. 11, 2019 |  |  | PROJECT COMPLETED | COMPLETED
147 | San Roque | Panabo City | Amended AIP - Construction Of Multi-Purpose Building W/ Eletrical Installation |  |  | SB No. 4 CY 2018 | 500000 | Transfer of funds | 2019-05-15 | 2019-06-10 |  |  | PROJECT COMPLETED | COMPLETED |  | Original AIP - Multi-Purpose Bldg. W/ Electrical | 20% DF CY 2017
148 | Lower Panaga | Panabo City | Const. of Multi Purpose Building |  |  | 20% DF CY 2017 | 500000 | Transfer of funds | Oct. 1, 2018 | Nov. 30, 2018 |  |  | PROJECT COMPLETED | COMPLETED
149 | Sindaton | Panabo City | Completion of Bleachers @ Brgy. Gym |  |  | 20% DF CY 2017 | 500000 | Transfer of funds | Oct. 1, 2018 | Oct. 31, 2018 |  |  | PROJECT COMPLETED | COMPLETED
150 | San Vicente | Panabo City | Const. of Concrete Pavement |  |  | 20% DF CY 2017 | 500000 | Transfer of funds |  | 2019-05-15 |  |  | PROJECT COMPLETED | COMPLETED
151 | Tagpore | Panabo City | Const. of Stage @ Prk. 3 |  |  | 20% DF CY 2017 | 500000 | Transfer of funds | 2018-07-18 | Sept. 14, 2018 |  |  | PROJECT COMPLETED | COMPLETED
152 | San Nicolas | Panabo City | Amended AIP - Construction of Multi-Purpose Building (Backstage/ Office) |  |  | SB No. 4 CY 2018 | 500000 | Transfer of funds | 2019-05-21 | 2019-06-19 |  |  | PROJECT COMPLETED | COMPLETED |  | Original AIP - Const. of Multi Purpose Bldg. | 20% DF CY 2017
153 | Manay | Panabo City | Const. of Bleachers @ Brgy. Manay Gym |  |  | 20% DF CY 2017 | 500000 | Transfer of funds | Dec. 6, 2018 | Dec. 14, 2018 |  |  | PROJECT COMPLETED | COMPLETED
154 | Cacao | Panabo City | Const. of Multi Purpose Bldg. |  |  | 20% DF CY 2017 | 500000 | Transfer of funds | Dec. 14, 2018 |  |  |  | COMPLETED BUT COMPLETION DOCS STILL FOR SUBMISSION | Completed physically; completion docs on process | Engr. Rabanoz - LGU Panabo
155 | A.O. Floirendo | Panabo City | Ammended AIP - Construction of Multi-Purpose Bldg. at A. O. Floirendo Nat'l. High School |  |  | SB No. 4 CY 2018 | 500000 | Transfer of funds |  |  |  |  | PENDING/ FOR ACTION | Materials already procured. Ongoing hiring of Admin Laborers. Target date to start the project on September 14, 2020. | Engr. Rabanoz - LGU Panabo | Original AIP - Multi-Purpose Bldg. | 20% DF CY 2017
173 | Gredu | Panabo City | Const. of Women Livelihood Bldg. |  |  | 20% DF CY 2019 | 500000 | Transfer of funds |  |  |  |  | PROJECT COMPLETED | COMPLETED
180 | Kimamon | Sto. Tomas | Const. of Concrete Drainage Canal |  |  | 20% DF CY 2017 | 500000 | Transfer of funds |  |  |  |  | PROJECT IMPLEMENTATION ONGOING | On-going
181 | Tulalian | Sto. Tomas | Const. of Violence Against Women and Children Center |  |  | 20% DF CY 2017 | 500000 | Transfer of funds | Dec. 18, 2018 | 2019-03-19 |  |  | PROJECT COMPLETED | COMPLETED
186 | La Libertad | Sto. Tomas | Completion of Brgy. Public Market |  |  | 20% DF CY 2019 | 500000 | Transfer of funds | Nov. 4, 2019 | Nov. 30, 2019 |  |  | PROJECT COMPLETED | COMPLETED
187 | New Visayas | Sto. Tomas | Rehab. of Evacuation Center |  |  | 20% DF CY 2019 | 500000 | Transfer of funds |  |  |  |  | PROJECT IMPLEMENTATION ONGOING | On-going Fund transferred to LGU - June 26, 2019 with check no. 2575132 and OR no. 0557455
188 | San Vicente | Sto. Tomas | Rehab. of Multi-purpose Hall |  |  | 20% DF CY 2019 | 500000 | Transfer of funds | Nov. 18, 2019 | Nov. 30, 2019 |  |  | PROJECT COMPLETED | COMPLETED
197 | Talomo | Sto. Tomas | Rehab. of Multi-purpose Hall |  |  | 20% DF CY 2019 | 500000 | Transfer of funds |  |  |  |  | PROJECT IMPLEMENTATION ONGOING | On-going Fund transferred to LGU - June 26, 2019 with check no. 2575130 and OR no. 0557456
202 | Cabay-Angan | B.E. Dujali | Construction of Bleacher With Canopy (Phase II) and Upgrading of Flooring |  |  | GF CY 2018 | 500000 | Transfer of funds |  |  |  |  | COMPLETED BUT COMPLETION DOCS STILL FOR SUBMISSION | COMPLETED - PCR & other completion documents for submission PCR, SWA, Before and after Pictures | Engr. Colaljo - MLGU B.E. Dujali
| Prepared by: |  |  |  |  | Checked by:
|  | THESSA R. DELA CRUZ, CE |  |  |  |  | ARSENIO T. CANILLADA III, CE |  |  | JULMANDY D. LUMOSBOG, UAP |  |  |  | JULMANDY LUMOSBOG
|  | Engineer - I |  |  |  |  | Engineer - III |  |  | Architect - III |  |  |  | Engineer - III
| Reviewed by: |  |  |  |  | Attested by: |  |  |  | Submitted to: |  |  | Submitted to:
|  | EDWIN S. MISA, CE |  |  |  |  | JIVELLYN B. CO, CE, MPA |  |  | GLENN A. OLANDRIA, CE |  |  |  | GLENN A. OLANDRIA,CE
|  | Engineer - IV |  |  |  |  | Asst. PG-Dept. Head |  |  | PG-Dept. Head |  |  |  | PG-Dept. Head

## July 2020 (hidden)
STIMULUS PROJECTS
PROJECT STATUS REPORT
as of July 2020
| LEGEND: |  | PROJECT COMPLETED
COMPLETED BUT COMPLETION DOCS STILL FOR SUBMISSION
PROJECT IMPLEMENTATION ONGOING
PROCUREMENT
PLAN AND POW PREPARATION ONGOING
PENDING/ FOR ACTION
|  | [TEXT] | NO BUDGET/DECLARED AS SAVINGS/CANCELLED
ITEM NO. | BARANGAY | CITY | PROJECT TITLE | PLAN |  | POW |  | SOURCE OF FUND | AMOUNT (Php) | MODE OF IMPLEMENTATION | DATE STARTED | DATE COMPLETED | STATUS | REMARKS | RESPONSIBLE OFFICE/PERSON
1 | Magatos | Asuncion | Compl. of Magatos E/S Per Fence | ok |  | ok |  | 20% DF CY 2017 | 500000 | Transfer of funds | 2018-06-18 | 2018-07-30 | PROJECT COMPLETED | COMPLETED
2 | Camansa | Asuncion | Cons. of Covered Court Phase 1 | ok |  | ok |  | 20% DF CY 2017 | 500000 | Transfer of funds | 2018-05-16 | 2018-07-15 | PROJECT COMPLETED | COMPLETED
3 | Sonlon | Asuncion | 0.5 Km. FMR at Brgy. Site | ok |  | ok |  | 20% DF CY 2017 | 500000 | Transfer of funds | 2018-06-18 | Aug. 10, 2018 | PROJECT COMPLETED | COMPLETED
4 | Santa Felomina | Asuncion | Cons. of Covered Court Phase 1 | ok |  | ok |  | 20% DF CY 2017 | 500000 | Transfer of funds | 2018-06-18 | Aug. 5, 2018 | PROJECT COMPLETED | COMPLETED
5 | Buclad | Asuncion | Amended AIP - Impvt. of Brgy. Facilities | ok |  | ok |  | 20% DF CY 2017 | 500000 | Transfer of funds | 2018-04-30 | 2018-06-30 | PROJECT COMPLETED | COMPLETED |  | Original AIP - Impvt. of Brgy. Hall
6 | Cabaywa | Asuncion | Amended AIP - Improvement of Barangay Hall | ok |  | ok |  | 20% DF CY 2017 | 500000 | Transfer of funds | 2018-05-18 | 2018-07-02 | PROJECT COMPLETED | COMPLETED |  | Original AIP - Impvt. of Brgy. Hall/Covered Court
7 | Napungas | Asuncion | Impvt. of Multi-Purpose Bldg. | ok |  | ok |  | 20% DF CY 2017 | 500000 | Transfer of funds | 2018-06-16 | 2018-06-30 | PROJECT COMPLETED | COMPLETED
8 | Cambanogoy | Asuncion | Amended AIP - Const. of Nutrition Building Phase 1 | ok |  | ok |  | 20% DF CY 2017 | 500000 | Transfer of funds | 2018-06-16 | 2018-07-15 | PROJECT COMPLETED | COMPLETED |  | Original AIP - Cons. of Nutrition Center
9 | New Loon | Asuncion | Rehab. of 2" Pipelines of Water System at Prk. 1 | ok |  | ok |  | 20% DF CY 2017 | 500000 | Transfer of funds | 2018-06-10 | Aug. 8, 2018 | PROJECT COMPLETED | COMPLETED
10 | Binancian | Asuncion | Cons. Of Multi-Purpose Stage | ok |  | ok |  | 20% DF CY 2017 | 500000 | Transfer of funds | 2018-05-18 | Aug. 16, 2018 | PROJECT COMPLETED | COMPLETED
11 | Sagayen | Asuncion | Cons. Of Water Reservoir & Purchase of P.E. Pipelines | ok |  | ok |  | 20% DF CY 2017 | 500000 | Transfer of funds |  |  | PENDING/ FOR ACTION | Project not implemented due to non availability of water source during drilling. Awaiting for the official documents from Brgy. Sagayen and MLGU - Asuncion for the cancellation of the project. | Engr. Cuajao - MLGU Asuncion
12 | Buan | Asuncion | Cons. Of Covered Court Phase 1 | ok |  | ok |  | 20% DF CY 2017 | 500000 | Transfer of funds | 2018-06-01 | 2018-07-30 | PROJECT COMPLETED | COMPLETED
13 | Canatan | Asuncion | Const. of Bleachers and Canopy | ok |  | ok |  | GF CY 2018 | 500000 | Transfer of funds |  |  | COMPLETED BUT COMPLETION DOCS STILL FOR SUBMISSION | COMPLETED - PCR & other completion documents for submission PCR, SWA, Before and after Pictures | Engr. Cuajao - MLGU Asuncion
14 | New Santiago | Asuncion | Const. Potable Water System at Prk.6 | ok |  | ok |  | SB No. 4 CY 2019 | 1,000,000.00 500,000.00 | Contract |  |  | PROCUREMENT | For bidding: June 30, 2020
15 | Camoning | Asuncion | Const. of Canopy | ok |  | ok |  | GF CY 2018 | 500000 | Transfer of funds |  |  | COMPLETED BUT COMPLETION DOCS STILL FOR SUBMISSION | COMPLETED - PCR & other completion documents for submission PCR, SWA, Before and after Pictures | Engr. Cuajao - MLGU Asuncion
16 | Doña Andrea | Asuncion | Completion of Electrification at Prk.10 & Prk.9 | ok |  | ok |  | GF CY 2018 | 500000 | Declared as savings |  |  | NO BUDGET/DECLARED AS SAVINGS/CANCELLED | The fund for this project was declared savings and re-aligned, added to stimulus projects that need additional funds and approved in SB No. 4 CY 2019
17 | San Vicente | Asuncion | Construction of Covered Court | ok |  | ok |  | GF CY 2018 | 500000 | Transfer of funds |  |  | COMPLETED BUT COMPLETION DOCS STILL FOR SUBMISSION | COMPLETED - PCR & other completion documents for submission PCR, SWA, Before and after Pictures | Engr. Cuajao - MLGU Asuncion
18 | Pamacaun | Asuncion | Const of Multi-Purpose Covered Court Phase 2 | ok |  | ok |  | SB No. 4 CY 2019 | 500000 | Contract |  |  | PROCUREMENT | Abstract on Process as of August 17, 2020 Contractor: Royal Summit Infinity Dev't. Corp. | SMAD
19 | Concepcion | Asuncion | Rehab. of FMR at Prk. 1, 3, 4 & 7 | ok |  | ok |  |  | 500000 | Declared as savings |  |  | NO BUDGET/DECLARED AS SAVINGS/CANCELLED | Declared savings to fund new project Construction of Children's Playground with Amenities at Pob. New Corella (SB No. 4 CY 2019)
20 | New Bantayan | Asuncion | Rehab. of Multi-purpose Hall | ok |  | ok |  | 20% DF CY 2019 | 500000 | Transfer of funds |  |  | COMPLETED BUT COMPLETION DOCS STILL FOR SUBMISSION | COMPLETED - PCR & other completion documents for submission PCR, SWA, Before and after Pictures | Engr. Cuajao - MLGU Asuncion
21 | Binancian | Asuncion | Consruction. of Multi- Purpose Hall at Liguyon E/S | ok |  | ok |  | SB No. 5 CY 2018 | 1250000 | Transfer of funds |  |  | COMPLETED BUT COMPLETION DOCS STILL FOR SUBMISSION | COMPLETED - PCR & other completion documents for submission PCR, SWA, Before and after Pictures | Engr. Cuajao - MLGU Asuncion
22 | Binancian | Asuncion | Consruction. of Multi- Purpose Hall at Rizal E/S | ok |  | ok |  | SB No. 5 CY 2018 | 1250000 | Transfer of funds |  |  | COMPLETED BUT COMPLETION DOCS STILL FOR SUBMISSION | COMPLETED - PCR & other completion documents for submission PCR, SWA, Before and after Pictures | Engr. Cuajao - MLGU Asuncion
23 | Napungas | Asuncion | Rehab./Impvt. of Multi-Purpose Bldg. (Gym) | ok |  | ok |  | SB No. 5 CY 2018 | 500000 | Contract |  |  | PROCUREMENT | Abstract on Process Contractor: Two Degrees Construction and Supply | SMAD
24 | Sagayen | Asuncion | Rehab./Improvement of Gymnasium |  |  |  |  | SB No. 1 CY 2019 | 1500000 | Contract |  |  | PROJECT IMPLEMENTATION ONGOING | NTP - July 17, 2020 | F. Kabingue - District 1
25 | Sagayen | Asuncion | Installation of street lights at Purok 1, 2, 3 , 4 |  |  |  |  | SB No. 1 CY 2019 | 1000000 | Contract | Jan. 27, 2020 |  | PROJECT IMPLEMENTATION ONGOING | On-going
26 | Concepcion | Asuncion | Rehab./Improvement of FMR, Purok 3, 7 & 8 |  |  |  |  | SB No. 1 CY 2019 | 500000 | Transfer of funds |  |  | PENDING/ FOR ACTION | Resumption of Work on August 4, 2020 | Engr. Cuajao - MLGU Asuncion
27 | Concepcion | Asuncion | Rural Electrification Project, Purok 6 |  |  |  |  | SB No. 1 CY 2019 | 1000000 | Declared as savings |  |  | NO BUDGET/DECLARED AS SAVINGS/CANCELLED | P 500,000.00 - Declared savings to fund new project: Construction of Children's Playground with Amenities at Pob. New Corella (SB No. 4 CY 2019) P 500,000.00 - Re-aligned due to Covid-19
28 | Concepcion | Asuncion | Installation of Bleacher for the Brgy. Gym |  |  |  |  | SB No. 1 CY 2019 | 1000000 | Transfer of funds |  |  | COMPLETED BUT COMPLETION DOCS STILL FOR SUBMISSION | COMPLETED - PCR & other completion documents for submission PCR, SWA, Before and after Pictures | Engr. Cuajao - MLGU Asuncion
29 | New Santiago | Asuncion | Concreting of FMR |  |  |  |  | SB No. 1 CY 2019 | 2500000 | Transfer of funds |  |  | COMPLETED BUT COMPLETION DOCS STILL FOR SUBMISSION | COMPLETED - PCR & other completion documents for submission PCR, SWA, Before and after Pictures | Engr. Cuajao - MLGU Asuncion
30 | Napungas | Asuncion | Rural Electrification Project, Purok 5 - 8 |  |  |  |  | SB No. 1 CY 2019 | 1500000 | Declared as savings |  |  | NO BUDGET/DECLARED AS SAVINGS/CANCELLED | Declared savings to fund new projectConstruction of Children's Playground with Amenities at Pob . New Corella (SB No. 4 CY 2019)
31 | Napungas | Asuncion | Rehab./Impvt. of Multi-Purpose Building, SCFA |  |  |  |  | SB No. 1 CY 2019 | 500000 | Declared as savings |  |  | NO BUDGET/DECLARED AS SAVINGS/CANCELLED | The fund for this project was declared savings and re-aligned, added to stimulus projects that need additional funds and approved in (SB No. 4 CY 2019)
32 | Buan | Asuncion | Construction of Multi-Purpose Covered Court | [5 empty] | 2500000 | Transfer of funds |  |  | COMPLETED BUT COMPLETION DOCS STILL FOR SUBMISSION | COMPLETED - PCR & other completion documents for submission PCR, SWA, Before and after Pictures | Engr. Cuajao - MLGU Asuncion
33 | Pamacaun | Asuncion | Construction of Multi-Purpose Covered Court | [5 empty] | 2500000 | Transfer of funds |  |  | COMPLETED BUT COMPLETION DOCS STILL FOR SUBMISSION | COMPLETED - PCR & other completion documents for submission PCR, SWA, Before and after Pictures | Engr. Cuajao - MLGU Asuncion
34 | New Cortez | New Corella | Fabrication of Bleachers | ok |  | ok |  | 20% DF CY 2017 | 500000 | Transfer of funds | 2018-06-15 | 2018-07-31 | PROJECT COMPLETED | COMPLETED
35 | Santa Fe | New Corella | Road Rehabilitation At Prk 1 - Prk 5 | ok |  | ok |  | 20% DF CY 2017 | 500000 | Transfer of funds |  |  | PROCUREMENT | Scheduled for bidding | Engr. Dogoldogol - MLGU New Corella
36 | Macgum | New Corella | Rehab. of Potable Water In Prk. 2,3,3a,3b & 6 | ok |  | ok |  | 20% DF CY 2017 | 500000 | Transfer of funds |  |  | PROJECT COMPLETED | COMPLETED
37 | New Sambog | New Corella | Amended AIP - Renov./Impv't. of Brgy. Hall | ok |  | ok |  | 20% DF CY 2017 | 500000 | Transfer of funds |  | Aug. 18, 2018 | PROJECT COMPLETED | COMPLETED |  | Original AIP - Renov. of Brgy. Hall & Compl. of Covered C. Flooring
38 | San Jose | New Corella | Cons. Of Multi-Purpose Bldg. | ok |  | ok |  | 20% DF CY 2017 | 500000 | Transfer of funds |  |  | PROJECT COMPLETED | COMPLETED
39 | Patrocenio | New Corella | Amended POW - Renovation/Impv't. Of Brgy. Hall | ok |  | ok |  | 20% DF CY 2017 | 500000 | Transfer of funds |  | Nov. 19, 2018 | PROJECT COMPLETED | COMPLETED |  | Original AIP - Renov. of Brgy. Hall
40 | Mambing | New Corella | Amended AIP - Completion of Covered Court/Gym | ok |  | ok |  | 20% DF CY 2017 | 500000 | Transfer of funds |  | 2018-07-15 | PROJECT COMPLETED | COMPLETED |  | Original AIP - Const. of 1 CL School Building
41 | Carcor | New Corella | Const. of Footbridge w/ Railings | ok |  | ok |  | 20% DF CY 2017 | 500000 | Transfer of funds |  | 2018-07-30 | PROJECT COMPLETED | COMPLETED
42 | Del Monte | New Corella | Const. of Concrete Fence of Lataban Elem. School | ok |  | ok |  | 20% DF CY 2017 | 500000 | Transfer of funds |  | Dec, 2018 | PROJECT COMPLETED | COMPLETED
43 | New Bohol | New Corella | Amended AIP - Improvement of Covered Court | ok |  | ok |  | 20% DF CY 2017 | 500000 | Transfer of funds |  | Aug. 15, 2018 | PROJECT COMPLETED | COMPLETED |  | Original AIP - Completion of Covered Court
44 | Sta. Cruz | New Corella | Const. of Concrete Bleachers | ok |  | ok |  | GF CY 2018 | 500000 | Transfer of funds | 2019-07-16 | Sept. 30, 2019 | PROJECT COMPLETED | COMPLETED - PCR & pictures submitted Feb. 7, 2016
45 | San Roque | New Corella | Completion of Mini Gym @ Prk.2 | ok |  | ok |  | GF CY 2018 | 500000 | Transfer of funds | 2019-07-26 | Sept. 30, 2019 | PROJECT COMPLETED | COMPLETED - PCR & pictures submitted Feb. 7, 2016
46 | Sto. Niño | New Corella | Completion of Covered Court | ok |  | ok |  | GF CY 2018 | 500000 | Transfer of funds | Sept. 16, 2019 | Dec. 15, 2019 | PROJECT COMPLETED | COMPLETED - PCR & pictures submitted Feb. 7, 2017
47 | Suawon | New Corella | Const. of Public Market | ok |  | ok |  | GF CY 2018 | 500000 | Transfer of funds | 2019-07-22 | Oct. 15, 2019 | PROJECT COMPLETED | COMPLETED - PCR & pictures submitted Feb. 7, 2018
48 | Del Pilar | New Corella | Const. of Concrete Line Drainage At Prk. 10 To Prk. 6 | ok |  | ok |  | SB No. 4 CY 2018 | 500000 | Transfer of funds | Aug. 5, 2019 | Oct. 15, 2019 | PROJECT COMPLETED | COMPLETED - PCR & pictures submitted Feb. 7, 2019
49 | Mesaoy | New Corella | Const. of Stage With Comfort Rooms At Mesaoy Mini-Gym | ok |  | ok |  | GF CY 2018 | 500000 | Transfer of funds | 2019-07-22 | Oct. 15, 2019 | PROJECT COMPLETED | COMPLETED - PCR & pictures submitted Feb. 7, 2020
50 | Poblacion | New Corella | Construction of 2 Storey Multi-Purpose hall (Brgy. Hall) Phase 1 | OK |  | OK |  | SB No. 5 CY 2018 | 2000000 | Transfer of funds | Nov. 13, 2019 |  | COMPLETED BUT COMPLETION DOCS STILL FOR SUBMISSION | COMPLETED - PCR & other completion documents for submission PCR, SWA, Before and after Pictures | Engr. Dogoldogol - MLGU New Corella
51 | Limbaan | New Corella | Concreting of Drainage Canal From Prk 3, 1-A, 2-A, To Purok 1-B, Brgy. Site | OK |  | OK |  | SB No. 5 CY 2018 | 1500000 | Contract |  |  | PROCUREMENT | Abstract on Process Contractor: Royal Summit Infinity Dev't. Corp. | SMAD
52 | El Salvador | New Corella | Const. of Multi-purpose Hall | ok |  | ok |  | 20% DF CY 2019 | 500000 | Transfer of funds | Sept. 16, 2019 | Dec. 15, 2019 | PROJECT COMPLETED | COMPLETED - PCR & pictures submitted Feb. 7, 2020
53 | Poblacion | New Corella | Const. of 2 Storey Multi-Purpose Hall Phase 3 (Brgy. Hall) | ok |  | ok |  | SB No. 4 CY 2019 | 500000 | Contract |  |  | NO BUDGET/DECLARED AS SAVINGS/CANCELLED | Re-aligned due to COVID-19 |  | Previous project name - Concreting of Drainage Canal (Amended in AIP 3rd revision CY 2019) | (20% DF CY 2019)
54 | Cabidianan | New Corella | Rehab. of Multi-purpose Hall | ok |  | ok |  | 20% DF CY 2019 | 500000 | Transfer of funds | Oct. 22, 2019 | Dec. 31, 2019 | PROJECT COMPLETED | COMPLETED - PCR & pictures submitted Feb. 7, 2020
55 | Limbaan | New Corella | Const. of Canal Lining | ok |  | ok |  | 20% DF CY 2019 | 500000 | Transfer of funds | Sept. 6, 2019 | Nov. 8, 2019 | PROJECT COMPLETED | COMPLETED - PCR & pictures submitted Feb. 7, 2020
56 | Poblacion | New Corella | Construction of 2 Storey Multi-Purpose Hall Phase 2 (Brgy. Hall) |  |  |  |  | SB No. 1 CY 2019 | 500000 | Contract |  |  | NO BUDGET/DECLARED AS SAVINGS/CANCELLED | Re-aligned due to COVID-19
57 | San Jose | New Corella | Farm to Market Road |  |  |  |  | SB No. 1 CY 2019 | 2000000 | By Admin |  |  | NO BUDGET/DECLARED AS SAVINGS/CANCELLED | PROJECT CANCELLED due to unavailability of budget
58 | San Jose | New Corella | Construction of Multi-Purpose Pavement |  |  |  |  | SB No. 1 CY 2019 | 500000 | By admin |  |  | PENDING/ FOR ACTION | For checking with PBO and/or PACCO for the availability of the fund
59 | New Sambog | New Corella | Purchase of Lot for Resettlement Site |  |  |  |  | SB No. 1 CY 2019 | 1500000 | Transfer of funds |  |  | PENDING/ FOR ACTION | Fund transfer pending waiting for the liquidation of the completed project: Const. of Water System. One funding only per fund transfer. | Engr. Dogoldogol - MLGU New Corella
60 | New Sambog | New Corella | Const. of Water System |  |  |  |  | SB No. 1 CY 2019 | 1000000 | Transfer of funds | Nov. 3, 2019 |  | COMPLETED BUT COMPLETION DOCS STILL FOR SUBMISSION | COMPLETED - PCR & other completion documents for submission PCR, SWA, Before and after Pictures | Engr. Dogoldogol - MLGU New Corella
61 | Limbaan | New Corella | Concreting of Drainage Canal from Purok 3, 1-A, 2-A to Purok 1-B , Brgy Site (Phase 2) |  |  |  |  | SB No. 1 CY 2019 | 500000 | Contract |  |  | PROCUREMENT | Abstract on Process Contractor: Royal Summit Infinity Dev't. Corp. | SMAD
62 | Limbaan | New Corella | Rehab. of Multi-Purpose Building (Evacuation Center) |  |  |  |  | SB No. 4 CY 2019 SB No. 1 CY 2019 | 600,000.00 500,000.00 | Contract / 45 CD |  |  | PROCUREMENT | Procurement on Process | SMAD
63 | Patrocenio | New Corella | Expansion of Multi-Purpose Hall (Brgy. Hall) |  |  |  |  | SB No. 1 CY 2019 | 500000 | Contract |  |  | COMPLETED BUT COMPLETION DOCS STILL FOR SUBMISSION | Completed physically; completion docs on process | District 1
64 | Patrocenio | New Corella | Const. of FMR from Purok 1 to Sitio Magsaysay via Pundol and Purok 4 |  |  |  |  | SB No. 1 CY 2019 | 2000000 | By admin |  |  | NO BUDGET/DECLARED AS SAVINGS/CANCELLED | Re-aligned due to COVID-19
65 | Poblacion | New Corella | Const. of Children's Playground with Amenities |  |  |  |  | SB No. 4 CY 2019 | 2500000 | By Admin |  |  | PROJECT IMPLEMENTATION ONGOING | Ongoing | D. Mayang - District 1
66 | Sua-On | Kapalong | Impvt. of Brgy. Hall | ok |  | ok |  | 20% DF CY 2017 | 500000 | Declared as savings |  |  | NO BUDGET/DECLARED AS SAVINGS/CANCELLED | Declared as savings and re-aligned to projects in SB No. 5 CY 2018
67 | Semong | Kapalong | Const. of Solar Drier |  |  |  |  | 20% DF CY 2017 | 500000 | Declared as savings |  |  | NO BUDGET/DECLARED AS SAVINGS/CANCELLED | Declared as savings and re-aligned to projects in SB No. 5 CY 2018
68 | Florida | Kapalong | Const. of Multi-Purpose Pavement | ok |  | ok |  | 20% DF CY 2017 | 500000 | Declared as savings |  |  | NO BUDGET/DECLARED AS SAVINGS/CANCELLED | Declared as savings and re-aligned to projects in SB No. 5 CY 2018
69 | Tiburcia | Kapalong | Const. of Concrete Bleacher | ok |  | ok |  | 20% DF CY 2017 | 500000 | Declared as savings |  |  | NO BUDGET/DECLARED AS SAVINGS/CANCELLED | Declared as savings and re-aligned to projects in SB No. 5 CY 2018
70 | Mabantao | Kapalong | Mainline Pipes For PWS | ok |  | ok |  | 20% DF CY 2017 | 500000 | Declared as savings |  |  | NO BUDGET/DECLARED AS SAVINGS/CANCELLED | Declared as savings and re-aligned to projects in SB N0. 4 CY 2019
71 | Pag-Asa | Kapalong | Impvt. of Covered Court | ok |  | ok |  | 20% DF CY 2017 | 500000 | Declared as savings |  |  | NO BUDGET/DECLARED AS SAVINGS/CANCELLED | Declared as savings and re-aligned to projects in SB No. 5 CY 2018
72 | Katipunan | Kapalong | Covered Court Bleacher | ok |  | ok |  | 20% DF CY 2017 | 500000 | Declared as savings |  |  | NO BUDGET/DECLARED AS SAVINGS/CANCELLED | Declared as savings and re-aligned to projects in SB No. 5 CY 2018
73 | Gabuyan | Kapalong | Impvt. of Gabuyan Covered Court | ok |  | ok |  | 20% DF CY 2017 | 500000 | Declared as savings |  |  | NO BUDGET/DECLARED AS SAVINGS/CANCELLED | Declared as savings and re-aligned to projects in SB No. 5 CY 2018
74 | Mamacao | Kapalong | Construction of Bleacher | ok |  | ok |  | GF CY 2018 | 500000 | By admin | Feb. 5, 2020 |  | COMPLETED BUT COMPLETION DOCS STILL FOR SUBMISSION | Completed physically; completion docs on process | N. Ambrosio - District 1
75 | Capungagan | Kapalong | Impvt. of Capungagan Gym Stage | ok |  | ok |  | GF CY 2018 | 500000 | Declared as savings |  |  | NO BUDGET/DECLARED AS SAVINGS/CANCELLED | Declared as savings and re-aligned to projects in SB No. 5 CY 2018
76 | Luna | Kapalong | Const. of Concrete Perimeter Fence | NO PLAN |  | NO POW |  | GF CY 2018 | 500000 | By admin |  |  | PROJECT IMPLEMENTATION ONGOING | Ongoing | N. Ambrosio - District 1
77 | Sampao | Kapalong | Const. of 1 Unit 2 Classroom School Bldg. at Sampao Integrated School | ok |  | ok |  | GF CY 2018 | 500000 | Declared as savings |  |  | NO BUDGET/DECLARED AS SAVINGS/CANCELLED | Declared as savings and re-aligned to projects in SB No. 4 CY 2019
78 | Maniki | Kapalong | Completion of Brgy. Health Center | NO PLAN |  | NO POW |  | SB No. 4 CY 2019 GF CY 2018 | 627,000.00 500,000.00 | Contract |  |  | PENDING/ FOR ACTION | For amendment.To submit a new resolution for another priority project which is the Const. of Multi-Purpose Pavement but the propose site is not donated because the previous project Completion of Brgy. Health Center was funded by the LGU of Kapalong
79 | Gupitan | Kapalong | Brgy. Electrification (Centro Gupitan) | ok |  | ok |  | 20% DF CY 2019 | 500000 | Declared as savings |  |  | NO BUDGET/DECLARED AS SAVINGS/CANCELLED | Declared as savings and re-aligned to projects in SB No. 4 CY 2019
80 | Palma Gil | Talaingod | Amended AIP - Const. of Covered Court Bleacher | ok |  | ok |  | SB No. 4 CY 2018 | 500000 | Transfer of funds |  |  | PROCUREMENT | Procurement on Process | SMAD | Original AIP - Electrification of Prk 1a - Prk 5a | 20% DF CY 2017
81 | Sto. Niño | Talaingod | Amended - Construction of Retaining Wall | ok |  | ok |  | GF CY 2018 | 500000 | Contract |  |  | PROCUREMENT | Procurement on Process | SMAD | Previous title - Grouted Riprap on Embankment
82 | Dagohoy | Talaingod | Brgy. Hall Improvement | ok |  | ok |  | GF CY 2018 | 500000 | Contract |  |  | PROCUREMENT | Abstract on Process Contractor - Alpebel Builders & Supply Corporation | SMAD
83 | Visayan Village | Tagum City | Const. of Multi Purpose Gym at Manga E/S |  |  |  |  | 20% DF CY 2017 | 500000 | Declared as savings |  |  | NO BUDGET/DECLARED AS SAVINGS/CANCELLED | Declared as savings and re-aligned to projects in SB No. 4 CY 2019
84 | Magdum | Tagum City | Improvement Of Barangay Hall |  |  |  |  | 20% DF CY 2017 | 500000 | By admin |  | 2018-06-21 | PROJECT COMPLETED | COMPLETED
85 | Pandapan | Tagum City | Construction of Brgy. Gym Bleacher | ok |  | ok |  | GF CY 2018 | 500000 | By admin |  | Jan. 30, 2019 | PROJECT COMPLETED | COMPLETED
86 | Canocotan | Tagum City | Const. of Stage | ok |  | ok |  | GF CY 2018 | 500000 | By admin |  | Sept. 22, 2019 | PROJECT COMPLETED | COMPLETED
87 | Magugpo West | Tagum City | Const. of Bleachers And Firewall For The Gym | ok |  | ok |  | GF CY 2018 | 500000 | By admin |  |  | PROJECT COMPLETED | COMPLETED
88 | La Filipina | Tagum City | Const. of One Bay Span Covered Court | ok |  | ok |  | GF CY 2018 | 500000 | By admin |  |  | PROJECT COMPLETED | COMPLETED
89 | San Miguel | Tagum City | Repair of Brgy. Hall | ok |  | ok |  | GF CY 2018 | 500000 | By admin |  | 2019-06-14 | PROJECT COMPLETED | COMPLETED
90 | Magugpo East | Tagum City | Compl. of Two Storey Multi-Purpose Building | ok |  | ok |  | GF CY 2018 | 500000 | By admin | Aug. 18, 2019 | Oct. 4, 2019 | PROJECT COMPLETED | COMPLETED
91 | Pagsabangan | Tagum City | Ammended AIP - Construction of Satellite Market | ok |  | ok |  | GF CY 2018 | 238125 | By admin |  |  | PENDING/ FOR ACTION | Approved Supplemental Budget for checking |  | Original AIP - Completion of Gym Bleacher w/ Electrification
92 | Libuganon | Tagum City | Const. of Drainage Canal | ok |  | ok |  | GF CY 2018 | 500000 | Contract |  |  | PROJECT IMPLEMENTATION ONGOING | Ongoing | Q. Quirante - District 1
93 | Madaum | Tagum City | Rehab. of Evacuation Center | ok |  | ok |  | 20% DF CY 2019 | 500000 | By admin | Nov. 16, 2019 | Jan. 16, 2020 | PROJECT COMPLETED | COMPLETED
94 | Magugpo Poblacion | Tagum City | Rehab. of Evacuation Center | ok |  | ok |  | SB No. 4 CY 2019 (20% DF CY 2019) | 600,000.00 (500,000.00) | Contract |  |  | COMPLETED BUT COMPLETION DOCS STILL FOR SUBMISSION | Completed physically; completion docs on process | District 1
95 | New Balamban | Tagum City | Rehab. of Evacuation Center | ok |  | ok |  | 20% DF CY 2019 | 500000 | Contract |  |  | PROJECT IMPLEMENTATION ONGOING | Winning Contractor for issuance of NTP | District 1
96 | Cuambogan | Tagum City | Rehab. of Multi-purpose Hall | ok |  | ok |  | 20% DF CY 2019 | 500000 | Contract |  |  | PROJECT IMPLEMENTATION ONGOING | Winning Contractor for issuance of NTP | District 1
97 | Nueva Fuerza | Tagum City | Completion of Evacuation Center | ok |  | ok |  | 20% DF CY 2019 | 500000 | Contract |  |  | PROJECT IMPLEMENTATION ONGOING | Winning Contractor for issuance of NTP | District 1
98 | San Agustin | Tagum City | Construction of Water System |  |  |  |  | 20% DF CY 2019 | 500000 | Declared savings |  |  | NO BUDGET/DECLARED AS SAVINGS/CANCELLED | Declared as savings and re aligned to other stimulus projects that need additional funds since there is no deed of donation for the proposed site (SB No. 4 CY 2019)
99 | Magugpo South | Tagum City | Const. of Brgy. Health Center | ok |  | ok |  | SB No. 4 CY 2019 (20% DF CY 2019) | 1,550,000.00 500,000.00 | Contract |  |  | PROCUREMENT | Abstract on Process Contractor: Royal Summit Infinity Dev't. Corp. | SMAD
100 | San Isidro | Tagum City | Const. of Women Livelihood Center | ok |  | ok |  | 20% DF CY 2019 | 500000 | Contract | Jan. 2, 2020 |  | COMPLETED BUT COMPLETION DOCS STILL FOR SUBMISSION | Completed physically; completion docs on process | District 1
101 | Busaon | Tagum City | Completion of Water System | ok |  | ok |  | 20% DF CY 2019 | 500000 | Contract |  |  | PROJECT IMPLEMENTATION ONGOING | Winning Contractor for issuance of NTP | District 1
102 | Apokon | Tagum City | Rehab. of Brgy. Health Center | ok |  | ok |  | 20% DF CY 2019 | 500000 | By admin |  |  | PENDING/ FOR ACTION | For Implementation; On hold due to resistance of Brgy. Apokon since the fund cannot complete the project. Report from District 1 to be resubmitted to SMAD. | District 1
103 | Bincungan | Tagum City | Const. of Drainage Canal | ok |  | ok |  | 20% DF CY 2019 | 500000 | Contract |  |  | PROJECT IMPLEMENTATION ONGOING | Winning Contractor for issuance of NTP; Project must be relocated; Joint Survey was conducted by PEO & Brgy. Officials last July 9, 2020, awaiting for the Resolution from the Brgy. For the relocation. | District 1
104 | Mankilam | Tagum City | Rehab. of Evacuation Center | ok |  | ok |  | 20% DF CY 2019 | 500000 | By admin |  |  | PROJECT IMPLEMENTATION ONGOING | For Implementation | A. Chua - District 1
105 | Magugpo North | Tagum City | Rehab. of Evacuation Center | ok |  | ok |  | 20% DF CY 2019 | 500000 | Contract |  |  | PROJECT IMPLEMENTATION ONGOING | Winning Contractor for issuance of NTP | District 1
106 | Sawata | San Isidro | Rehab. of Sawata Gymnasium | ok |  | ok |  | 20% DF CY 2017 | 500000 | By admin |  | 2018-07-25 | PROJECT COMPLETED | COMPLETED
107 | Libuton | San Isidro | Const. of Covered Court Bleachers | ok |  | ok |  | 20% DF CY 2017 | 500000 | By admin |  | Aug. 22, 2018 | PROJECT COMPLETED | COMPLETED
108 | San Miguel | San Isidro | Compl. of Pipeline Level Ii - Continuing Stimulus 2015 | ok |  | ok |  | 20% DF CY 2017 | 500000 | By admin |  | 2018-07-25 | PROJECT COMPLETED | COMPLETED
109 | Kipalili | San Isidro | Compl. of Multi-Purpose Bldg. | ok |  | ok |  | 20% DF CY 2017 | 500000 | By admin |  | Jan. 5, 2019 | PROJECT COMPLETED | COMPLETED
110 | Datu-Balong | San Isidro | Amended AIP - Construction of Covered Court (1 Bay) Datu Balong Nat'l. High School | ok |  | ok |  | SB No. 4 CY 2018 | 500000 | By admin |  |  | PROJECT COMPLETED | COMPLETED |  | Original AIP - Const. of Covered Court | 20% DF CY 2017
111 | Linao | San Isidro | Const. of Brgy. Stage | ok |  | ok |  | 20% DF CY 2017 | 500000 | By admin |  |  | PROJECT COMPLETED | COMPLETED
112 | Monte Dujali | San Isidro | Amended Aip - Const. of Potable Water System | ok |  | ok |  | SB No. 4 CY 2018 | 500000 | By admin |  |  | PROJECT COMPLETED | COMPLETED |  | Original AIP - Const. of Intake Box & Water Impounding System | 20% DF CY 2017
113 | Dakudao | San Isidro | Const. of Brgy. Hall Perimeter Fence | ok |  | ok |  | GF CY 2018 | 500000 | By admin |  |  | PROJECT COMPLETED | COMPLETED
114 | Sabangan | San Isidro | Impvt. of Water System |  |  |  |  | GF CY 2018 | 500000 | Declared savings |  |  | NO BUDGET/DECLARED AS SAVINGS/CANCELLED | Declared as savings and re aligned to other stimulus projects that need additional funds since there is no deed of donation for the proposed site (SB No. 4 CY 2019)
115 | Mamangan | San Isidro | Rehab. & Flooring of Gymnasium Basketball Court | ok |  | ok |  | GF CY 2018 | 500000 | By admin | Nov. 18, 2019 |  | COMPLETED BUT COMPLETION DOCS STILL FOR SUBMISSION | Completed physically; completion docs on process | N. Ambrosio - District 1
116 | Sto. Nino | San Isidro | Rehab. of Multi - Purpose Hall | ok |  | ok |  | 20% DF CY 2019 | 500000 | By admin |  |  | PROJECT IMPLEMENTATION ONGOING | On - going
117 | Pinamuno | San Isidro | Rehab. of Water System at Purok Cabang & Mangga | ok |  | ok |  | 20% DF CY 2019 | 500000 | Contract |  |  | PENDING/ FOR ACTION | Project implementation ongoing but suspended due to COVID-19
118 | Igangon | San Isidro | Rehab. of Water System | ok |  | ok |  | 20% DF CY 2019 | 500000 | By admin |  |  | PROJECT IMPLEMENTATION ONGOING | Ongoing | F. Kabingue - District 1
119 | Tibulao | Carmen | Const. of Concrete Pavement to Concreting of FMR | ok |  | ok |  | 20% DF CY 2017 | 500000 | Declared as savings |  |  | NO BUDGET/DECLARED AS SAVINGS/CANCELLED | Declared as savings and re-aligned to fund projects in SB No. 5 CY 2018
120 | Asuncion | Carmen | Const of Evacuation Center at Prk. 1 | ok |  | ok |  | 20% DF CY 2017 | 500000 | Transfer of funds |  |  | PROJECT COMPLETED | COMPLETED
121 | Taba | Carmen | Amended AIP - Completion of Evacuation Center Building Phase 3 | ok |  | ok |  | 20% DF CY 2017 | 500000 | Transfer of funds |  | Sept. 19, 2018 | PROJECT COMPLETED | COMPLETED |  | Original AIP - Completion of Evacuation Center Bldg.
122 | Salvacion | Carmen | Const. of Multi-Purpose Stage @ Prk. 2 | ok |  | ok |  | 20% DF CY 2017 | 500000 | Transfer of funds |  |  | PROJECT COMPLETED | COMPLETED
123 | Anibongan | Carmen | Evacuation Center to Rehab. of Evacuation Center |  |  |  |  | 20% DF CY 2017 | 500000 | Declared as savings |  |  | NO BUDGET/DECLARED AS SAVINGS/CANCELLED | Declared as savings and re-aligned to fund projects in SB No. 5 CY 2018
124 | Magsaysay | Carmen | Const. of Multi-Purpose Bldg. | ok |  | ok |  | 20% DF CY 2017 | 500000 | Transfer of funds |  |  | PROJECT COMPLETED | COMPLETED
125 | Tubod | Carmen | Const. of Canal Lining @ Brgy. Site | ok |  | ok |  | 20% DF CY 2017 | 500000 | Declared as savings |  |  | NO BUDGET/DECLARED AS SAVINGS/CANCELLED | Declared as savings and re-aligned to fund projects in SB No. 5 CY 2018
126 | New Camiling | Carmen | Completion of Covered Court/Stage | ok |  | ok |  | 20% DF CY 2017 | 500000 | Transfer of funds |  |  | PROJECT COMPLETED | COMPLETED
127 | Minda | Carmen | Rehab./Impvt. of Minda Brgy. Hall to Rehab. of Multi-Purpose Hall |  |  |  |  | 20% DF CY 2017 | 500000 | Declared as savings |  |  | NO BUDGET/DECLARED AS SAVINGS/CANCELLED | Declared as savings and re-aligned to fund projects in SB No. 5 CY 2018
128 | San Isidro | Carmen | Completion of Evacuation Center Building | NO PLAN |  | NO POW |  | GF CY 2018 | 500000 | Contract |  |  | PROJECT IMPLEMENTATION ONGOING | Ongoing
129 | La Paz | Carmen | Const.of Multi-purpose Hall | ok |  | ok |  | 20% DF CY 2019 | 500000 | Transfer of funds |  |  | PROJECT COMPLETED | COMPLETED
130 | Sto. Nino | Carmen | Const. of Evacuation Center at Purok 1-C | ok |  | ok |  | SB No. 4 CY 2019 (20% DF CY 2019 | 500000 | Contract |  |  | PROCUREMENT | Procurement on Process
131 | Mangalcal | Carmen | Const. of Multi-purpose Hall | ok |  | ok |  | 20% DF CY 2019 | 500000 | Transfer of funds |  |  | PROJECT COMPLETED | COMPLETED
132 | Guadalupe | Carmen | Rehab. of Multi-purpose Hall | ok |  | ok |  | 20% DF CY 2019 | 500000 | Transfer of funds |  |  | PROJECT COMPLETED | COMPLETED
133 | Mabuhay | Carmen | Const. of Multi-purpose Hall | ok |  | ok |  | 20% DF CY 2019 | 500000 | Transfer of funds |  |  | PROJECT COMPLETED | COMPLETED
134 | Mabaus | Carmen | Const. of Canal Lining | ok |  | ok |  | 20% DF CY 2019 | 500000 | Transfer of funds |  |  | PROJECT COMPLETED | COMPLETED
135 | Alejal | Carmen | Rehab. of Evacuation Center | ok |  | ok |  | 20% DF CY 2019 | 500000 | Transfer of funds |  |  | PROJECT COMPLETED | COMPLETED
136 | Tuganay | Carmen | Completion of Evacuation Center | ok |  | ok |  | 20% DF CY 2019 | 500000 | Transfer of funds |  |  | PROJECT COMPLETED | COMPLETED
137 | Ising | Carmen | Const. of Multi-purpose Hall | ok |  | ok |  | 20% DF CY 2019 | 500000 | Transfer of funds |  |  | PROJECT COMPLETED | COMPLETED
138 | Cebulano | Carmen | Rehab. of Multi-purpose Hall | ok |  | ok |  | 20% DF CY 2019 | 500000 | Transfer of funds |  |  | PROJECT COMPLETED | COMPLETED
139 | Consolacion | Panabo City | Amended AIP - Const. Of Market Stall/Bldg. | ok |  | ok |  | SB No. 4 CY 2018 | 500000 | Transfer of funds | 2019-05-28 |  | PENDING/ FOR ACTION | Project for termination as per accomplishment report submitted |  | Original AIP - Additional Market Bldg.
140 | Upper Licanan | Panabo City | Amended AIP - Rehab. of Multi-Purpose Hall (Covered Court) | ok |  | ok |  | SB No. 4 CY 2018 | 500000 | Transfer of funds |  | Nov. 16, 2019 | PROJECT COMPLETED | COMPLETED |  | Original AIP - Const. of Footbridge
141 | Sta. Cruz | Panabo City | Brgy. Covered Court Fencing | ok |  | ok |  | 20% DF CY 2017 | 500000 | Transfer of funds | 2019-05-15 | 2019-06-14 | PROJECT COMPLETED | COMPLETED
142 | Katualan | Panabo City | Const. of Multi-Purpose Bldg. | ok |  | ok |  | 20% DF CY 2017 | 500000 | Transfer of funds | Sept. 20, 2019 | Oct. 12, 2018 | PROJECT COMPLETED | COMPLETED
143 | Kauswagan | Panabo City | Amended AIP - Impvt. Of Multi-Purpose Gym | ok |  | ok |  | SB No. 4 CY 2018 | 500000 | Transfer of funds |  | Feb. 3, 2020 | PROJECT COMPLETED | COMPLETED |  | Original AIP - FMR
144 | Katipunan | Panabo City | Const. of Covered Court Bleacher | ok |  | ok |  | 20% DF CY 2017 | 500000 | Transfer of funds | 2018-07-18 | Sept. 10, 2019 | PROJECT COMPLETED | COMPLETED
145 | Mabunao | Panabo City | Constructionof Brgy. Gymnasium | ok |  | ok |  | 20% DF CY 2017 | 500000 | Transfer of funds | 2019-03-11 | April 10 ,2019 | PROJECT COMPLETED | COMPLETED
146 | Tibungol | Panabo City | Completion of Footbridge at Prk. 1 | ok |  | ok |  | 20% DF CY 2017 | 500000 | Transfer of funds | Dec. 13, 2018 | Feb. 11, 2019 | PROJECT COMPLETED | COMPLETED
147 | San Roque | Panabo City | Amended AIP - Construction Of Multi-Purpose Building W/ Eletrical Installation | ok |  | ok |  | SB No. 4 CY 2018 | 500000 | Transfer of funds | 2019-05-15 | 2019-06-10 | PROJECT COMPLETED | COMPLETED |  | Original AIP - Multi-Purpose Bldg. W/ Electrical | 20% DF CY 2017
148 | Lower Panaga | Panabo City | Const. of Multi Purpose Building | ok |  | ok |  | 20% DF CY 2017 | 500000 | Transfer of funds | Oct. 1, 2018 | Nov. 30, 2018 | PROJECT COMPLETED | COMPLETED
149 | Sindaton | Panabo City | Completion of Bleachers @ Brgy. Gym | ok |  | ok |  | 20% DF CY 2017 | 500000 | Transfer of funds | Oct. 1, 2018 | Oct. 31, 2018 | PROJECT COMPLETED | COMPLETED
150 | San Vicente | Panabo City | Const. of Concrete Pavement | ok |  | ok |  | 20% DF CY 2017 | 500000 | Transfer of funds |  | 2019-05-15 | PROJECT COMPLETED | COMPLETED
151 | Tagpore | Panabo City | Const. of Stage @ Prk. 3 | ok |  | ok |  | 20% DF CY 2017 | 500000 | Transfer of funds | 2018-07-18 | Sept. 14, 2018 | PROJECT COMPLETED | COMPLETED
152 | San Nicolas | Panabo City | Amended AIP - Construction of Multi-Purpose Building (Backstage/ Office) | ok |  | ok |  | SB No. 4 CY 2018 | 500000 | Transfer of funds | 2019-05-21 | 2019-06-19 | PROJECT COMPLETED | COMPLETED |  | Original AIP - Const. of Multi Purpose Bldg. | 20% DF CY 2017
153 | Manay | Panabo City | Const. of Bleachers @ Brgy. Manay Gym | ok |  | ok |  | 20% DF CY 2017 | 500000 | Transfer of funds | Dec. 6, 2018 | Dec. 14, 2018 | PROJECT COMPLETED | COMPLETED
154 | Cacao | Panabo City | Const. of Multi Purpose Bldg. |  |  |  |  | 20% DF CY 2017 | 500000 | Transfer of funds | Dec. 14, 2018 |  | PROJECT IMPLEMENTATION ONGOING | On-going
155 | A.O. Floirendo | Panabo City | Ammended AIP - Construction of Multi-Purpose Bldg. at A. O. Floirendo Nat'l. High School | ok |  | ok |  | SB No. 4 CY 2018 | 500000 | Transfer of funds |  |  | PROJECT IMPLEMENTATION ONGOING | On-going |  | Original AIP - Multi-Purpose Bldg. | 20% DF CY 2017
156 | Kiotoy | Panabo City | Rehab. of Evacuation Center |  |  |  |  | SB No. 4 CY 2019 (20% DF CY 2017 | 650,000.00 (500,000.00) | Contract |  |  | PROCUREMENT | Procurement on Process
157 | San Pedro | Panabo City | Const. of New Brgy. Stage Phase 2 | ok | dolor | ok |  | SB No. 4 CY 2019 20% DF CY 2019 | 500000 | Contract |  |  | PLAN AND POW PREPARATION ONGOING | Plan and POW Preparation Ongoing | J. Lumosbog - PDPM
158 | Malativas | Panabo City | Impvt. of Brgy. Covered Court | ok | dolor | ok |  | SB No. 4 CY 2019 20% DF CY 2019 | 607,800.00 500,000.00 | Contract |  |  | PROCUREMENT | Procurement on Process
159 | Maduao | Panabo City | Rehab. of Multi-Purpose Gym & Facilities | NO PLAN | dolor | NO POW |  | GF CY 2018 | 500000 | Contract |  |  | PROCUREMENT | Procurement on Process
160 | Sto. Niño | Panabo City | Const. of Multi Purpose Bldg. | NO PLAN | dolor | NO POW |  | GF CY 2018 | 500000 | Contract |  |  | PROCUREMENT | Procurement on Process
161 | Dapco | Panabo City | Completion of Canopy At Dapco Covered Court | ok | dolor | ok |  | GF CY 2018 | 500000 | Contract |  |  | PROJECT IMPLEMENTATION ONGOING | For implementation
162 | Nanyo | Panabo City | Const. of Perimeter Fence At Day Care Center 1 | ok | torres | ok | torres | SB No. 4 CY 2019 20% DF CY 2019 | 500000 | Contract |  |  | PROJECT IMPLEMENTATION ONGOING | Ongoing | Y. Estorco - District 2
163 | Kasilak | Panabo City | Rehab. of Multi-purpose Hall | ok | Dolorito | ok |  | SB No. 4 CY 2019 (20% DF CY 2019 | 650,000.00 (500,000.00) | Contract |  |  | PROJECT IMPLEMENTATION ONGOING | Ongoing | Y. Estorco - District 2
164 | New Malitbog | Panabo City | Const. of Potable Water System | ok | maw | ok |  | SB No. 4 CY 2019 (20% DF CY 2019 | 500000 | Contract |  |  | NO BUDGET/DECLARED AS SAVINGS/CANCELLED | Re-aligned due to COVID-19
165 | New Pandan | Panabo City | Desilting of Canal | ok |  | ok |  | 20% DF CY 2019 | 500000 | Contract |  |  | NO BUDGET/DECLARED AS SAVINGS/CANCELLED | Re-aligned due to COVID-19
166 | Waterfall | Panabo City | Const. of Multi-purpose Hall | ok | Llanera | ok |  | SB No. 4 CY 2019 (20% DF CY 2019 | 1,050,000.00 500,000.00 | Contract |  |  | PROCUREMENT | Procurement on Process
167 | Cagangohan | Panabo City | Rehab. of Evacuation Center Previous project name :Concreting of Brgy. Road Purok Guyabano | ok | Dolorito | ok |  | SB No. 4 CY 2019 (20% DF CY 2019 | 500000 | Contract |  |  | PROCUREMENT | Procurement on Process
168 | J.P. Laurel | Panabo City | Rehab. of Evacuation Center | ok | Dolorito | ok |  | 20% DF CY 2019 | 500000 | Contract |  |  | PROCUREMENT | Procurement on Process
169 | Buenavista | Panabo City | Const. of Multi-purpose Hall | ok | Llanera | ok |  | SB No. 4 CY 2019 (20% DF CY 2019 | 1,050,000.00 500,000.00 | Contract |  |  | PROCUREMENT | Procurement on Process
170 | San Francisco | Panabo City | Rehab. of Multi-purpose Hall | ok | Llanera | ok |  | SB No. 4 CY 2019 (20% DF CY 2019 | 600,000.00 500,000.00 | Contract |  |  | PROCUREMENT | Procurement on Process
171 | Datu Abdul Dadia | Panabo City | Rehab. of Evacuation Center | ok | Dolorito | ok |  | SB No. 4 CY 2019 (20% DF CY 2019 | 650,000.00 500,000.00 | Contract |  |  | PROCUREMENT | Procurement on Process
172 | Quezon | Panabo City | Impvt./Beautification of Brgy. Grounds | ok | Llanera | ok |  | 20% DF CY 2019 | 500000 | Declared savings |  |  | NO BUDGET/DECLARED AS SAVINGS/CANCELLED | Declared savings and re aligned in AIP 3rd revision CY 2019 to add funds to projects that need additional funding
173 | Gredu | Panabo City | Const. of Women Livelihood Bldg. | ok |  | ok |  | 20% DF CY 2019 | 500000 | Transfer of funds |  |  | PROJECT COMPLETED | COMPLETED
174 | Salvacion | Panabo City | Const. of Canal Lining at Purok 5 | ok |  | ok |  | SB No. 4 CY 2019 (20% DF CY 2019 | 600,000.00 500,000.00 | Contract |  |  | PROCUREMENT | Procurement on Process | I. Piad - District 2
175 | New Visayas | Panabo City | Rehab. of Health Center | ok | Dolorito | ok |  | 20% DF CY 2019 | 500000 | Declared savings |  |  | NO BUDGET/DECLARED AS SAVINGS/CANCELLED | Declared savings and re aligned in AIP 3rd revision CY 2019 to add funds to projects that need additional funding
176 | Little Panay | Panabo City | Rehab. of Multi-purpose Hall | ok | Dolorito | ok |  | SB No. 4 CY 2019 (20% DF CY 2019 | 550,000.00 500,000.00 | Contract |  |  | PROCUREMENT | Procurement on Process
177 | Dalisay | Panabo City | Rehab. of Brgy. Health Center | ok | Dolorito | ok |  | SB No. 4 CY 2019 (20% DF CY 2019 | 550,000.00 500,000.00 | Contract |  |  | PROCUREMENT | Procurement on Process
178 | Southern Davao | Panabo City | Const. of Multi-purpose Hall | ok | Llanera | ok |  |  | 500000 | Contract |  |  | PROCUREMENT | Procurement on Process
179 | Esperanza | Sto. Tomas | Renov. of Brgy. Hall | ok |  | ok |  |  | 500000 |  |  |  | NO BUDGET/DECLARED AS SAVINGS/CANCELLED | Declared as savings (Old structure need to construct new) The brgy. capt submitted a resolution for a 2 storey Multi-Purpose Hall Recommended for AIP CY 2021 - Construction of Multi-Purpose Hall - P1,200,000.00
180 | Kimamon | Sto. Tomas | Const. of Concrete Drainage Canal | ok |  | ok |  | 20% DF CY 2017 | 500000 | Transfer of funds |  |  | PROJECT IMPLEMENTATION ONGOING | On-going
181 | Tulalian | Sto. Tomas | Const. of Violence Against Women and Children Center | ok |  | ok |  | 20% DF CY 2017 | 500000 | Transfer of funds | Dec. 18, 2018 | 2019-03-19 | PROJECT COMPLETED | COMPLETED
182 | Balagunan | Sto. Tomas | Const. of Multi-Purpose Bldg. | ok |  | ok |  | SB No. 4 CY 2019 20% DF CY 2019 | 500000 | Contract |  |  | PROCUREMENT | Procurement on Process
183 | Kinamayan | Sto. Tomas | Const. of Perimeter Fence of Kinamayan Integ. School | ok |  | ok |  | GF CY 2018 | 500000 | Contract |  |  | PROJECT IMPLEMENTATION ONGOING | NTP: April 7, 2020 For implementation
184 | Casig-ang | Sto. Tomas | Rehab. of Evacuation Center | ok |  | ok |  | 20% DF CY 2019 | 500000 | Contract |  |  | PROCUREMENT | Procurement on Process
185 | Tibal-og | Sto. Tomas | Const. of Brgy. Tibal-og Health Center | ok |  | ok |  | 20% DF CY 2019 | 500000 | Contract |  |  | PENDING/ FOR ACTION | POW completed. Need additional fund to complete the project, total project cost P 1,550,000.00. Will recommend in the AIP CY 2021 for Completion of Brgy. Tibal-og Health Center
186 | La Libertad | Sto. Tomas | Completion of Brgy. Public Market | ok |  | ok |  | 20% DF CY 2019 | 500000 | Transfer of funds | Nov. 4, 2019 | Nov. 30, 2019 | PROJECT COMPLETED | COMPLETED
187 | New Visayas | Sto. Tomas | Rehab. of Evacuation Center | ok |  | ok |  | 20% DF CY 2019 | 500000 | Transfer of funds |  |  | PROJECT IMPLEMENTATION ONGOING | On-going Fund transferred to LGU - June 26, 2019 with check no. 2575132 and OR no. 0557455
188 | San Vicente | Sto. Tomas | Rehab. of Multi-purpose Hall | ok |  | ok |  | 20% DF CY 2019 | 500000 | Transfer of funds | Nov. 18, 2019 | Nov. 30, 2019 | PROJECT COMPLETED | COMPLETED
189 | Salvacion | Sto. Tomas | Rehab. of Multi-purpose Hall | ok |  | ok |  | SB No. 4 CY 2019 20% DF CY 2019 | 1,000,000.00 500,000.00 | Contract |  |  | NO BUDGET/DECLARED AS SAVINGS/CANCELLED | Re-aligned due to COVID-19
190 | Pantaron | Sto. Tomas | Rehab. of Multi-purpose Hall | ok |  | ok |  | SB No. 4 CY 2019 20% DF CY 2019 | 550,000.00 500,000.00 | Contract |  |  | PROCUREMENT | Procurement on Process
191 | Magwawa | Sto. Tomas | Rehab. of Multi-purpose Hall | ok |  | ok |  | 20% DF CY 2019 | 500000 | Contract |  |  | PROJECT IMPLEMENTATION ONGOING | On-going JJR Construction & Supply | Y. Estorco - District 2
192 | San Jose | Sto. Tomas | Completion of Multi-purpose Hall | ok |  | ok |  | SB No. 4 CY 2019 20% DF CY 2019 | 600,000.00 500,000.00 | Contract |  |  | PROJECT IMPLEMENTATION ONGOING | On-going JJR Construction & Supply | Y. Estorco - District 2
193 | Bobongon | Sto. Tomas | Const. of Evacuation Center | ok |  | ok |  | 20% DF CY 2019 | 500000 | Declared savings |  |  | NO BUDGET/DECLARED AS SAVINGS/CANCELLED | Declared savings to fund stimulus project in the LGU that needs additional funds (Rehab. of Multi-Purpose Hall at Salvacion, Sto. Tomas). Recommended for AIP CY 2021 with complete funding up to completion since the amount of P500,000.00 in the stimulus fund can not complete the project Const of Evacuation Center.
194 | Lungaog | Sto. Tomas | Rehab. of Brgy. Road | ok |  | ok |  | SB No. 4 CY 2019 (20% DF CY 2019 | 600,000.00 500,000.00 | Contract |  |  | PROCUREMENT | For issuance of NTP. Target date: Aug. 5, 2020 | I. Piad - District 2
195 | New Katipunan | Sto. Tomas | Rehab. of Multi-purpose Hall | ok |  | ok |  | 20% DF CY 2019 | 500000 | Contract |  |  | PROCUREMENT | Procurement on Process
196 | San Miguel | Sto. Tomas | Const. of Multi-purpose Hall | ok |  | ok |  | 20% DF CY 2019 | 500000 | Contract |  |  | PROJECT IMPLEMENTATION ONGOING | On-going JJR Construction & Supply | Y. Estorco - District 2
197 | Talomo | Sto. Tomas | Rehab. of Multi-purpose Hall | ok |  | ok |  | 20% DF CY 2019 | 500000 | Transfer of funds |  |  | PROJECT IMPLEMENTATION ONGOING | On-going Fund transferred to LGU - June 26, 2019 with check no. 2575130 and OR no. 0557456
198 | Dujali | B.E. Dujali | Concreting of Brgy. Road Canal | ok |  | ok |  | SB No. 4 CY 2019 (20% DF CY 2019 | 650,000.00 500,000.00 | Contract |  |  | PROCUREMENT | Procurement on Process
199 | New Casay | B.E. Dujali | Desilting And Concreting of Drainage-Main Collector Canal | ok |  | ok |  | SB No. 4 CY 2019 (20% DF CY 2019) | 650,000.00 500,000.00 | Contract |  |  | NO BUDGET/DECLARED AS SAVINGS/CANCELLED | Re-aligned due to COVID-19
200 | Tanglaw | B.E. Dujali | Concreting of Drainage | ok |  | ok |  | SB No. 4 CY 2019 (20% DF CY 2019 | 1,200,000.00 500,000.00 | Contract |  |  | PROCUREMENT | Procurement on Process
201 | Magupising | B.E. Dujali | Construction of Multi-Purpose Covered Court | NO PLAN |  | NO POW |  | GF CY 2018 | 600,000.00 500,000.00 | Contract |  |  | PROCUREMENT | Procurement on Process
202 | Cabay-Angan | B.E. Dujali | Construction of Bleacher With Canopy (Phase II) and Upgrading of Flooring | NO PLAN |  | NO POW |  | GF CY 2018 | 500000 | Transfer of funds |  |  | COMPLETED BUT COMPLETION DOCS STILL FOR SUBMISSION | COMPLETED - PCR & other completion documents for submission PCR, SWA, Before and after Pictures | Engr. Colaljo - MLGU B.E. Dujali
203 | Sto. Niño | IGACOS | Impvt. of Water System | ok |  | ok |  | 20% DF CY 2017 | 500000 | By admin. |  |  | PROJECT COMPLETED | COMPLETED
204 | San Agustin | IGACOS | Amended AIP - Impvt. of Covered Court (Bleacher) | ok |  | ok |  | 20% DF CY 2017 | 500000 | By admin. |  |  | PROJECT COMPLETED | COMPLETED |  | Original AIP - Impvt. of Multi-Purpose Gym
205 | Caliclic | IGACOS | Impvt. of Water System | ok |  | ok |  | 20% DF CY 2017 | 500000 | By admin. |  | 2018-07-12 | PROJECT COMPLETED | COMPLETED
206 | Sion | IGACOS | Rehab. of Water System | ok |  | ok |  | 20% DF CY 2017 | 500000 | By admin. |  |  | PROJECT COMPLETED | COMPLETED
207 | Toril | IGACOS | Electrification of Prk. 4 & 6 | NO PLAN |  | NO POW |  | 20% DF CY 2017 | 500000 | By admin. |  | Oct. 5, 2018 | PROJECT IMPLEMENTATION ONGOING | For implementation
208 | Anonang | IGACOS | Impv't. of Brgy. Street Electrification | ok |  | ok |  | 20% DF CY 2017 | 500000 | By admin. |  |  | PENDING/ FOR ACTION | Verified at PBO 7/18/2019 that fund is not available.
209 | Camudmud | IGACOS | Amended AIP - Const. of Concrete Pavement Of Brgy. Camudmud Access Road | ok |  | ok |  | 20% DF CY 2017 | 500000 | By admin. |  |  | PROJECT COMPLETED | COMPLETED |  | Original AIP - Concreting Of The Brgy. Road
210 | Balet | IGACOS | Amended AIP - Improvement of Evacuation Center | ok |  | ok |  | 20% DF CY 2017 | 500000 | By admin. | 2019-05-01 | 2019-06-06 | PROJECT COMPLETED | COMPLETED |  | Original AIP - Const. of Elevated Tank With Submersible Pump
211 | Limao | IGACOS | Const. of Senior Citizen Bldg. | ok |  | ok |  | 20% DF CY 2017 | 500000 | By admin. |  | 2018-07-13 | PROJECT COMPLETED | COMPLETED
212 | Tagpopongan | IGACOS | Construction of Tribal House | ok |  | ok |  | 20% DF CY 2017 | 500000 | By admin. |  | 2018-07-14 | PROJECT COMPLETED | COMPLETED
213 | Pichon | IGACOS | Impvt. Of Brgy. Water System | ok |  | ok |  | GF CY 2018 | 500000 | By admin. |  |  | PROJECT COMPLETED | COMPLETED
214 | Cogon | IGACOS | Powerline Expansion Project | NO PLAN |  | NO POW |  | GF CY 2018 | 500000 | Contract |  |  | PROJECT IMPLEMENTATION ONGOING | For implementation; waiting for NTP
215 | Tagbay | IGACOS | Water System Frm. Prk. 6 - Prk. 2 - Prk. 5a | ok |  | ok |  | GF CY 2018 | 500000 | By admin. |  |  | PROJECT IMPLEMENTATION ONGOING | For implementation
216 | Tagdaliao | IGACOS | Amended AIP - Const. of 2 Storey Multi- Purpose Hall Phase 2 |  |  |  |  | GF CY 2018 | 500000 | By admin. |  |  | PENDING/ FOR ACTION | Approved Supplemental Budget for checking |  | Original AIP - Const. of Brgy. Health Station POW - Improvement of Brgy. Hall
217 | Kanaan | IGACOS | Electrification Project | NO PLAN |  | NO POW |  | GF CY 2018 | 500000 |  |  |  | NO BUDGET/DECLARED AS SAVINGS/CANCELLED | Declared savings; The fund can not complete the project
218 | Adecor | IGACOS | Const. of New Brgy. Hall | ok |  | ok |  | GF CY 2018 | 500000 | By admin. | Feb. 21, 2019 | 2019-03-03 | PROJECT COMPLETED | COMPLETED
219 | Guilon | IGACOS | Const. of Public Toilet | ok |  | ok |  | GF CY 2018 | 500000 | By admin. |  | Oct. 19, 2018 | PROJECT COMPLETED | COMPLETED
220 | Kinawitnon | IGACOS | Improvement of Barangay Hall | ok |  | ok |  | GF CY 2018 | 500000 | By admin. |  |  | PROJECT COMPLETED | COMPLETED
221 | Cawag | IGACOS | Impvt. of Brgy. Hall | ok |  | ok |  | GF CY 2018 | 500000 | By admin. |  | Dec. 2018 | PROJECT COMPLETED | COMPLETED
222 | Tambo | IGACOS | Powerline Expansion Project | NO PLAN |  | NO POW |  | GF CY 2018 | 500000 | Contract |  |  | PROCUREMENT | Procurement on Process
223 | Tagbitan-Ag | IGACOS | Impvt. of Multi-Purpose Bldg. (Covered Court) | ok |  | ok |  | GF CY 2018 | 500000 | By admin. |  |  | PROJECT COMPLETED | COMPLETED
224 | Peñaplata | IGACOS | Const. of MP Pavement, Homeowners Association at Purok 5-A Previous Project Name -Improvement Of Barangay Hall | ok |  | ok |  | SB No. 4 CY 2019 GF CY 2018 | 500000 | By admin. |  |  | PROCUREMENT | Procurement on Process
225 | Sta. Cruz | IGACOS | Completion of Kasilak Day Care Center | ok |  | ok |  | GF CY 2018 | 500000 | By admin. |  |  | PROJECT IMPLEMENTATION ONGOING | On-going
226 | San Isidro | IGACOS | Const. of Concrete Fence of a New Brgy. Site | ok |  | ok |  | GF CY 2018 | 500000 | By admin. |  |  | PROJECT IMPLEMENTATION ONGOING | On-going | F. Andoy - PDPM
227 | Dadatan | IGACOS | Electrification Of Sitio Baongon-Diamond-Mansanitas | NO PLAN |  | NO POW |  | GF CY 2018 | 500000 | Contract |  |  | PROCUREMENT | Procurement on Process
228 | Linusotan | IGACOS | Drilling Of Water System | NO PLAN |  | NO POW |  | GF CY 2018 | 500000 | By admin. |  |  | NO BUDGET/DECLARED AS SAVINGS/CANCELLED | Re-aligned due to COVID-19
229 | Aumbay | IGACOS | Rehab. of Health Center | ok |  | ok |  | 20% DF CY 2019 | 500000 | By admin. |  | Oct. 7, 2019 | PROJECT COMPLETED | COMPLETED
230 | Catagman | IGACOS | Concreting of Brgy. Road from Prk. 3 to Prk. 5 | ok |  | ok |  | 20% DF CY 2019 | 500000 | Contract |  |  | PROJECT COMPLETED | COMPLETED
231 | San Jose | IGACOS | Rehab. of Multi-purpose Hall | ok |  | ok |  | 20% DF CY 2019 | 500000 | By admin. |  |  | PROJECT COMPLETED | COMPLETED
232 | Bandera | IGACOS | Electrification at Sitio Trinidad | ok |  | ok |  | 20% DF CY 2019 | 500000 | Contract |  |  | PROCUREMENT | For re-bid due to non compliance in requirement
233 | Mambago-A | IGACOS | Rehab. of Brgy. Health Center | ok |  | ok |  | 20% DF CY 2019 | 500000 | By admin. | 2019-07-01 | Aug. 23, 2019 | PROJECT COMPLETED | COMPLETED
234 | Del Monte | IGACOS | Rehab. of Multi-purpose Hall | ok |  | ok |  | 20% DF CY 2019 | 500000 | By admin. |  |  | PENDING/ FOR ACTION | Pending/activity undertaken by DPWH Waiting for the report from project in charge. Alloted - May 29, 2019
235 | Aundanao | IGACOS | Rehab. of Multi-purpose Hall | ok |  | ok |  | 20% DF CY 2019 | 500000 | By admin. | Nov. 18, 2019 |  | PROJECT COMPLETED | COMPLETED
236 | Tagbaobo | IGACOS | Electrification at Upper Purok Rosal | ok |  | ok |  | 20% DF CY 2019 | 500000 | By admin. |  |  | PROCUREMENT | Procurement on Process
237 | Mambago-B | IGACOS | Const. of Multi-purpose Hall | ok |  | ok |  | 20% DF CY 2019 | 500000 | By admin. |  |  | PROJECT COMPLETED | COMPLETED
238 | San Antonio | IGACOS | Const. of Multi-purpose Hall | ok |  | ok |  | 20% DF CY 2019 | 500000 | By admin. |  |  | PROJECT IMPLEMENTATION ONGOING | On-going | R. Obar - PDPM
239 | Villarica | IGACOS | Concreting of Brgy. Road from Prk. 1 to Prk. 2 | ok |  | ok |  | 20% DF CY 2019 | 500000 | Contract |  |  | PROJECT COMPLETED | COMPLETED
240 | Pangubatan | IGACOS | Rehab. of Water System Intake Box & Pipeline | ok |  | ok |  | 20% DF CY 2019 | 500000 | By admin. |  |  | PROJECT IMPLEMENTATION ONGOING | For implementation
241 | Cogon (Talicud) | IGACOS | Const. of Multi-purpose Hall | ok |  | ok |  | 20% DF CY 2019 | 500000 | By admin. |  |  | PROCUREMENT | Procurement on Process
242 | Libertad | IGACOS | Installation of Pipelines | ok |  | ok |  | 20% DF CY 2019 | 500000 | By admin. |  |  | PROJECT IMPLEMENTATION ONGOING | For implementation
243 | Libuak | IGACOS | Rehab. of Evacuation Center | ok |  | ok |  | 20% DF CY 2019 | 500000 | By admin. |  |  | PROJECT IMPLEMENTATION ONGOING | For implementation
244 | Pob. Kaputian | IGACOS | Const. of Water System Project | ok |  | ok |  | SB No. 4 CY 2019 (20% DF CY 2019 | 500000 | Contract |  |  | PROJECT IMPLEMENTATION ONGOING | For implementation
245 | San Isidro, Babak | IGACOS | Rehab. of Potable Water System | ok |  | ok |  | 20% DF CY 2019 | 500000 | Admin |  |  | PROJECT IMPLEMENTATION ONGOING | For implementation
246 | San Miguel | IGACOS | Rehab. of Potable Water System | ok |  | ok |  | 20% DF CY 2019 | 500000 | Admin |  |  | PENDING/ FOR ACTION | Project suspended (change of project location for drilling since the previous is not feasible)
247 | San Remegio | IGACOS | Const. of Water System Phase II | ok |  | ok |  | 20% DF CY 2019 | 500000 | By admin. |  |  | PROJECT IMPLEMENTATION ONGOING | For implementation
248 | Licup | IGACOS | Electrification at Prk.1,3,4,6,7 & 8 | ok |  | ok |  | 20% DF CY 2019 | 500000 | Contract |  |  | PROCUREMENT | Procurement on Process
| Prepared by: | [6 empty] | Checked by:
|  | THESSA R. DELA CRUZ, CE | [6 empty] | ARSENIO T. CANILLADA III, CE |  |  | JULMANDY D. LUMOSBOG, UAP |  | JULMANDY LUMOSBOG
|  | Engineer - I | [6 empty] | Engineer - III |  |  | Architect - III |  | Engineer - III
| Reviewed by: | [6 empty] | Attested by: |  |  |  | Submitted to: | Submitted to:
|  | EDWIN S. MISA, CE | [6 empty] | JIVELLYN B. CO, CE, MPA |  |  | GLENN A. OLANDRIA, CE |  | GLENN A. OLANDRIA,CE
|  | Engineer - IV | [6 empty] | Asst. PG-Dept. Head |  |  | PG-Dept. Head |  | PG-Dept. Head

## Annual Report CY 2020 (Compl.)
[14 empty] | 0 |  |  |  | 0 |  |  |  | 0 | [11 empty] | 0
[10 empty] | ` | ECONOMIC (INFRASTRUCTURE DEV'T. PROGRAM)
[10 empty] | OFFICE/AGENCY: | PROVINCIAL ENGINEER'S OFFICE
[10 empty] | AREA: | 1ST ENGINEERING DISTRICT - COMPLETED, ON-GOING AND FOR IMPLEMENTATION PROJECTS | [7 empty] | Total extended
#REF!
#REF!
MUNICIPALITY | BARANGAY | AREA | REMARKS | DATE STARTED | DATE COMPLETED | YEAR | IMPLEMENTATED | APPRO- PRIATION | NOMEN- CLATURE | NAME OF PROJECT |  | SOURCE OF FUND | TYPE OF PROJECT | PHYSICAL TARGET (DESCRIPTION) |  | MODE OF IMPLEMENTATION | PROJECT DATA |  |  |  | FINANCIAL |  | PHYSICAL ACCOMPLISHMENT (JULY) |  | PHYSICAL ACCOMPLISHMENT (AUGUST) |  | PHYSICAL ACCOMPLISHMENT (SEPTEMBER) |  | PHYSICAL ACCOMPLISHMENT (OCTOBER) |  | PHYSICAL ACCOMPLISHMENT |  | EMPLOYMENT GENERATED |  | REMARKS (JULY) | REMARKS (AUGUST) | REMARKS (SEPTEMBER) | REMARKS (OCTOBER | REMARKS (NOVEMBER) | REMARKS
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | Completed | 2020-06-25 | 2020-08-03 | 2012 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | Const. of Veterinary Quarantine Station |  | Continuing Appropriation CY 2012 | Bldg |  |  | Contract | Project Cost: | 185360 | Target Completion Date: | 2020-08-03 23:46 | Program: | 185360 | Planned: | 100% | No. of Persons: | 0 | Completed August 3, 2020 |  | Planned: | 100% | Planned: | 100% | No. of Persons: | 0 |  |  |  | Completed August 3, 2020 | Completed August 3, 2020 | Completed as per Program of Works
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | Completed | 2020-06-25 | 2020-08-03 | 2012 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Project Engineer: | Azotes | Revised Completion Date: |  | Allotment: | 185360 | Revised: |  | No. of Man-days: | 0 |  |  | Revised: |  | Revised: |  | No. of Man-days: | 0
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | Completed | 2020-06-25 | 2020-08-03 | 2012 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Implementor: | Allbrycar Const. and Eng'g. Services | No. of days suspended: |  | Disbursement: |  | Actual: | 100% |  |  |  |  | Actual: | 100% | Actual: | 100%
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | Completed | 2020-06-25 | 2020-08-03 | 2012 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Duration: | 40 | No. of days extended: |  |  |  | Slippage: | 0% |  |  |  |  | Slippage: | 0% | Slippage: | 0%
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | Completed | 2020-06-25 | 2020-08-03 | 2012 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Allotment Released: |  | Date completed: | 2020-08-03
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | Completed | 2020-06-25 | 2020-08-03 | 2012 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Started: | 2020-06-25
Sto. Tomas | Esperanza | 2nd Eng'g. Dist. | Completed | 2017-03-22 | 2020-10-23 | 2014 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PRDP | Rehab. of Esperanza-Pob. Sto. Tomas, FMR, DDN |  | PRDP CY 2014 | Road Concreting | 12.774 | km | Contract | Project Cost: | 117410426.3 | Target Completion Date: | 2019-07-22 23:59 | Program: | 117410426.3 | Planned: | 100% | Planned: | 100% | Planned: | 100% | Planned: | 100% | Planned: | 100% | No. of Persons: | 20 | On-going (Waiting for approve Variation order for billing) | On-going (Waiting for approve Variation order for billing) | On-going (Waiting for approve Variation order for billing) | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per Program of Works
Sto. Tomas | Esperanza | 2nd Eng'g. Dist. | Completed | 2017-03-22 | 2020-10-23 | 2014 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PRDP | [7 empty] | Project Engineer: | Palero | Revised Completion Date: | 2020-09-23 23:59 | Allotment: | 117410426.3 | Revised: | 95.53% | Revised: | 100% | Revised: | 100% | Revised: | 100% | Revised: | 100% | No. of Man-days: | 600
Sto. Tomas | Esperanza | 2nd Eng'g. Dist. | Completed | 2017-03-22 | 2020-10-23 | 2014 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PRDP | [7 empty] | Implementor: | ALZAM | No. of days suspended: |  | Disbursement: | 105669383.67 | Actual: | 87.82% | Actual: | 97% | Actual: | 97% | Actual: | 100% | Actual: | 100%
Sto. Tomas | Esperanza | 2nd Eng'g. Dist. | Completed | 2017-03-22 | 2020-10-23 | 2014 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PRDP | [7 empty] | Duration: | 853 | No. of days extended: | 429 |  |  | Slippage: | -7.705% | Slippage: | -3% | Slippage: | -3% | Slippage: | 0% | Slippage: | 0%
Sto. Tomas | Esperanza | 2nd Eng'g. Dist. | Completed | 2017-03-22 | 2020-10-23 | 2014 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PRDP | [7 empty] | Date Allotment Released: | CY 2014 | Date completed: | 2020-10-23
Sto. Tomas | Esperanza | 2nd Eng'g. Dist. | Completed | 2017-03-22 | 2020-10-23 | 2014 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PRDP | [7 empty] | Date Started: | 2017-03-22
Panabo | Dalisay | 2nd Eng'g. Dist. | Completed | 2018-01-29 | 2020-02-11 | 2014 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PRDP | Construction of Dalisay Potable Water System, Panabo City |  | PRDP CY 2014 | Road Concreting |  |  | Contract | Project Cost: | 4664033.76 | Target Completion Date: | 2018-07-23 23:59 | Program: | 4664033.76 | Planned: | 100% | Planned: | 100% | Planned: | 100% | Planned: | 100% | Planned: | 100% | No. of Persons: | 20 | On-going (Waiting for approve Variation order for billing) | On-going (Waiting for approve Variation order for billing) | On-going (Waiting for approve Variation order for billing) | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per Program of Works
Panabo | Dalisay | 2nd Eng'g. Dist. | Completed | 2018-01-29 | 2020-02-11 | 2014 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PRDP | [7 empty] | Project Engineer: | Estorco | Revised Completion Date: | 2020-02-11 23:59 | Allotment: | 4664033.76 | Revised: | 95.53% | Revised: | 100% | Revised: | 100% | Revised: | 100% | Revised: | 100% | No. of Man-days: | 600
Panabo | Dalisay | 2nd Eng'g. Dist. | Completed | 2018-01-29 | 2020-02-11 | 2014 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PRDP | [7 empty] | Implementor: | ANCOR WATER RESOURCES | No. of days suspended: | 568 | Disbursement: | 4197630.384 | Actual: | 87.82% | Actual: | 97% | Actual: | 97% | Actual: | 100% | Actual: | 100%
Panabo | Dalisay | 2nd Eng'g. Dist. | Completed | 2018-01-29 | 2020-02-11 | 2014 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PRDP | [7 empty] | Duration: | 176 | No. of days extended: |  |  |  | Slippage: | -7.705% | Slippage: | -3% | Slippage: | -3% | Slippage: | 0% | Slippage: | 0%
Panabo | Dalisay | 2nd Eng'g. Dist. | Completed | 2018-01-29 | 2020-02-11 | 2014 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PRDP | [7 empty] | Date Allotment Released: | CY 2014 | Date completed: | 2020-02-11
Panabo | Dalisay | 2nd Eng'g. Dist. | Completed | 2018-01-29 | 2020-02-11 | 2014 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PRDP | [7 empty] | Date Started: | 2018-01-29
Panabo | Kasilak | 2nd Eng'g. Dist. | Completed | 2018-01-29 | 2020-02-18 | 2014 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PRDP | Construction of Kasilak Potable Water System, Panabo City |  | PRDP CY 2014 | Road Concreting |  |  | Contract | Project Cost: | 7046856.27 | Target Completion Date: | 2018-07-23 23:59 | Program: | 7046856.27 | Planned: | 100% | Planned: | 100% | Planned: | 100% | Planned: | 100% | Planned: | 100% | No. of Persons: | 20 | On-going (Waiting for approve Variation order for billing) | On-going (Waiting for approve Variation order for billing) | On-going (Waiting for approve Variation order for billing) | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per Program of Works
Panabo | Kasilak | 2nd Eng'g. Dist. | Completed | 2018-01-29 | 2020-02-18 | 2014 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PRDP | [7 empty] | Project Engineer: | Estorco | Revised Completion Date: | 2020-02-18 23:59 | Allotment: | 7046856.27 | Revised: | 95.53% | Revised: | 100% | Revised: | 100% | Revised: | 100% | Revised: | 100% | No. of Man-days: | 600
Panabo | Kasilak | 2nd Eng'g. Dist. | Completed | 2018-01-29 | 2020-02-18 | 2014 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PRDP | [7 empty] | Implementor: | ANCOR WATER RESOURCES | No. of days suspended: | 575 | Disbursement: | 6342170.643 | Actual: | 87.82% | Actual: | 97% | Actual: | 97% | Actual: | 100% | Actual: | 100%
Panabo | Kasilak | 2nd Eng'g. Dist. | Completed | 2018-01-29 | 2020-02-18 | 2014 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PRDP | [7 empty] | Duration: | 176 | No. of days extended: |  |  |  | Slippage: | -7.705% | Slippage: | -3% | Slippage: | -3% | Slippage: | 0% | Slippage: | 0%
Panabo | Kasilak | 2nd Eng'g. Dist. | Completed | 2018-01-29 | 2020-02-18 | 2014 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PRDP | [7 empty] | Date Allotment Released: | CY 2014 | Date completed: | 2020-02-18
Panabo | Kasilak | 2nd Eng'g. Dist. | Completed | 2018-01-29 | 2020-02-18 | 2014 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PRDP | [7 empty] | Date Started: | 2018-01-29
Kapalong |  | 1st Eng'g. Dist. | Completed | 2016-06-01 | 2020-08-27 | 2014 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPPAP-PAMANA | Construction of Biga Bridges, Kapalong (Original Contract Cost: P 24,959,503.45; Variation Order: P 4,067,412.00) |  | OPPAP-PAMANA CY 2014 | Road |  | km | Contract | Project Cost: | 29026915.45 | Target Completion Date: | 2018-07-30 23:59 | Program: | 29026915.45 | Planned: | 100% | Planned: | 100% | Planned: | 100% | Planned: | 100% | Planned: | 100% | No. of Persons: | 20 | On-going (Waiting for approve Variation order for billing) | On-going (Waiting for approve Variation order for billing) | On-going (Waiting for approve Variation order for billing) | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per Program of Works
Kapalong |  | 1st Eng'g. Dist. | Completed | 2016-06-01 | 2020-08-27 | 2014 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPPAP-PAMANA | [7 empty] | Project Engineer: | Limpo | Revised Completion Date: | 2020-03-25 23:59 | Allotment: | 29026915.45 | Revised: | 99.7% | Revised: | 99.7% | Revised: | 100% | Revised: | 100% | Revised: | 100% | No. of Man-days: | 600
Kapalong |  | 1st Eng'g. Dist. | Completed | 2016-06-01 | 2020-08-27 | 2014 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPPAP-PAMANA | [7 empty] | Implementor: | Davao Rock Mixer | No. of days suspended: | 604 | Disbursement: | 18489834.55 | Actual: | 85.37% | Actual: | 85.37% | Actual: | 100% | Actual: | 100% | Actual: | 100%
Kapalong |  | 1st Eng'g. Dist. | Completed | 2016-06-01 | 2020-08-27 | 2014 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPPAP-PAMANA | [7 empty] | Duration: | 760 | No. of days extended: |  |  |  | Slippage: | -14.33% | Slippage: | -14.33% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Kapalong |  | 1st Eng'g. Dist. | Completed | 2016-06-01 | 2020-08-27 | 2014 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPPAP-PAMANA | [7 empty] | Date Allotment Released: | CY 2014 | Date completed: | 2020-08-27
Kapalong |  | 1st Eng'g. Dist. | Completed | 2016-06-01 | 2020-08-27 | 2014 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPPAP-PAMANA | [7 empty] | Date Started: | 2016-07-01
Kapalong | Capungagan | 1st Eng'g. Dist. | Completed | 2016-04-06 | 2020-07-03 | 2015 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PRDP | Rehab. Of Capungagan-Boundary San Miguel FMR, Kapalong, |  | PRDP CY 2015 | Road Concreting | 10.6 | km | Contract | Project Cost: | 108303841.7 | Target Completion Date: | 2020-02-14 23:46 | Program: | 108303841.7 | Planned: | 100% | Planned: | 100% | Planned: | 100% | Planned: | 100% | Planned: | 100% | No. of Persons: | 19 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | Completed as per physical accomplishment. | Completed as per physical accomplishment. | Completed as per Program of Works
Kapalong | Capungagan | 1st Eng'g. Dist. | Completed | 2016-04-06 | 2020-07-03 | 2015 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PRDP | [7 empty] | Project Engineer: | Nasol | Revised Completion Date: | 2020-03-06 23:46 | Allotment: | 108303841.7 | Revised: | 97.28% | Revised: | 97.28% | Revised: | 97.28% | Revised: | 100% | Revised: | 100% | No. of Man-days: | 570
Kapalong | Capungagan | 1st Eng'g. Dist. | Completed | 2016-04-06 | 2020-07-03 | 2015 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PRDP | [7 empty] | Implementor: | VICLAO | No. of days suspended: | 21 | Disbursement: | 60050673.93 | Actual: | 93.8% | Actual: | 93.8% | Actual: | 93.8% | Actual: | 100% | Actual: | 100%
Kapalong | Capungagan | 1st Eng'g. Dist. | Completed | 2016-04-06 | 2020-07-03 | 2015 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PRDP | [7 empty] | Duration: | 1410 | No. of days extended: |  |  |  | Slippage: | -3.48% | Slippage: | -3.48% | Slippage: | -3.48% | Slippage: | 0% | Slippage: | 0%
Kapalong | Capungagan | 1st Eng'g. Dist. | Completed | 2016-04-06 | 2020-07-03 | 2015 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PRDP | [7 empty] | Date Allotment Released: | CY 2015 | Date completed: | 2020-07-03
Kapalong | Capungagan | 1st Eng'g. Dist. | Completed | 2016-04-06 | 2020-07-03 | 2015 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PRDP | [7 empty] | Date Started: | 2016-04-06
New Corella | Limbaan | 1st Eng'g. Dist. | On-going | 2016-04-08 |  | 2015 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PRDP | Rehab. Of Pob.-Limbaan-Suawon-Macgum FMR w/ Bridge (42 ln.m), New Corella, Davao del Norte |  | PRDP CY 2015 | Road Concreting | 15.01 | km | Contract | Project Cost: | 205202114.16 | Target Completion Date: | 2018-11-06 23:46 | Program: | 205202114.16 | Planned: | 100% | Planned: | 100% | Planned: | 100% | Planned: | 100% | Planned: | 100% | No. of Persons: | 40 | On-going (Increase of Project Cost due to Variation Order Php 14,948,622.18, Partial suspension due to soft soil from sta. 8+000 - 10+000); (Suspended last April 5, 2020 due to COVID; Resumption Order dated June 1, 2020) | On-going (Increase of Project Cost due to Variation Order Php 14,948,622.18, Partial suspension due to soft soil from sta. 8+000 - 10+000); (Suspended last April 5, 2020 due to COVID; Resumption Order dated June 1, 2020) | On-going (Increase of Project Cost due to Variation Order Php 14,948,622.18, Partial suspension due to soft soil from sta. 8+000 - 10+000); (Suspended last April 5, 2020 due to COVID; Resumption Order dated June 1, 2020) | On-going (Increase of Project Cost due to Variation Order Php 14,948,622.18, Partial suspension due to soft soil from sta. 8+000 - 10+000); (Suspended last April 5, 2020 due to COVID; Resumption Order dated June 1, 2020) | On-going (Increase of Project Cost due to Variation Order Php 14,948,622.18, Partial suspension due to soft soil from sta. 8+000 - 10+000); (Suspended last April 5, 2020 due to COVID; Resumption Order dated June 1, 2020) | Suspended due to variation order dated November 2020
New Corella | Limbaan | 1st Eng'g. Dist. | On-going | 2016-04-08 |  | 2015 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PRDP | [7 empty] | Project Engineer: | Madrigal | Revised Completion Date: | 2020-10-25 23:46 | Allotment: | 205202114.16 | Revised: | 86.35% | Revised: | 87.69% | Revised: | 87.69% | Revised: | 87.69% | Revised: | 88.78% | No. of Man-days: | 1200
New Corella | Limbaan | 1st Eng'g. Dist. | On-going | 2016-04-08 |  | 2015 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PRDP | [7 empty] | Implementor: | Dvo. Rock Mixer | No. of days suspended: | 229 | Disbursement: | 141497191.47 | Actual: | 79.97% | Actual: | 81.21% | Actual: | 81.21% | Actual: | 81.21% | Actual: | 83.08%
New Corella | Limbaan | 1st Eng'g. Dist. | On-going | 2016-04-08 |  | 2015 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PRDP | [7 empty] | Duration: | 943 | No. of days extended: | 490 |  |  | Slippage: | -6.385% | Slippage: | -6.487% | Slippage: | -6.487% | Slippage: | -6.487% | Slippage: | -5.705%
New Corella | Limbaan | 1st Eng'g. Dist. | On-going | 2016-04-08 |  | 2015 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PRDP | [7 empty] | Date Allotment Released: | CY 2015 | Date completed:
New Corella | Limbaan | 1st Eng'g. Dist. | On-going | 2016-04-08 |  | 2015 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PRDP | [7 empty] | Date Started: | 2016-04-08
Panabo City | Lasang | 2nd Eng'g. Dist. | Suspended | 2015-05-30 |  | 2015 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOV'T. BLDG. & FAC. DEV'T. PROJECT | Proposed Davao del Norte Tourism Billboard, Brgy. Lasang, Panabo City |  | SB # 1 CY 2015 | Billboard |  | sq.m | Admin | Project Cost: | 756400 | Target Completion Date: | 2015-05-10 23:59 | Program: | 756400 | Planned: | 11.78% | Planned: | 11.78% | Planned: | 11.78% | Planned: | 11.78% | Planned: | 11.78% | No. of Persons: |  | delay due to change location & design code. For AIP amendment from Panabo City to Gov't Center, Mankilam | delay due to change location & design code. For AIP amendment from Panabo City to Gov't Center, Mankilam | delay due to change location & design code. For AIP amendment from Panabo City to Gov't Center, Mankilam | delay due to change location & design code. For AIP amendment from Panabo City to Gov't Center, Mankilam | delay due to change location & design code. For AIP amendment from Panabo City to Gov't Center, Mankilam | delay due to change location & design code. For AIP amendment from Panabo City to Gov't Center, Mankilam
Panabo City | Lasang | 2nd Eng'g. Dist. | Suspended | 2015-05-30 |  | 2015 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOV'T. BLDG. & FAC. DEV'T. PROJECT | [7 empty] | Project Engineer: | Porras | Revised Completion Date: |  | Allotment: | 756400 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
Panabo City | Lasang | 2nd Eng'g. Dist. | Suspended | 2015-05-30 |  | 2015 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOV'T. BLDG. & FAC. DEV'T. PROJECT | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: | 332087.3 | Actual: | 11.78% | Actual: | 11.78% | Actual: | 11.78% | Actual: | 11.78% | Actual: | 11.78%
Panabo City | Lasang | 2nd Eng'g. Dist. | Suspended | 2015-05-30 |  | 2015 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOV'T. BLDG. & FAC. DEV'T. PROJECT | [7 empty] | Duration: | 42 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Panabo City | Lasang | 2nd Eng'g. Dist. | Suspended | 2015-05-30 |  | 2015 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOV'T. BLDG. & FAC. DEV'T. PROJECT | [7 empty] | Date Allotment Released: | 2015-05-06 | Date completed:
Panabo City | Lasang | 2nd Eng'g. Dist. | Suspended | 2015-05-30 |  | 2015 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOV'T. BLDG. & FAC. DEV'T. PROJECT | [7 empty] | Date Started: | 2015-03-30
IGCS | Kinawitnon | 2nd Eng'g. Dist. | For verification |  |  |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | RURAL ELECTRIFICATION PROJECT | Inst. of transformer and accessories, Brgy. Kinawitnon |  | PRDP CY 2016 | Electrification |  |  | Admin | Project Cost: | 150000 | Target Completion Date: |  | Program: | 150000 | Planned: |  | No. of Persons: |  | Purchase Order # 2019103228 - Transformer; Purchase Order # 2019102931 - Billboard; Purchase Order # 2019103227 - Lumber |  |  |  | Planned: |  | No. of Persons: | [6 empty] | For verification
IGCS | Kinawitnon | 2nd Eng'g. Dist. | For verification |  |  |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | RURAL ELECTRIFICATION PROJECT | [7 empty] | Project Engineer: | Porras | Revised Completion Date: |  | Allotment: | 150000 | Revised: |  | No. of Man-days: | [5 empty] | Revised: |  | No. of Man-days:
IGCS | Kinawitnon | 2nd Eng'g. Dist. | For verification |  |  |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | RURAL ELECTRIFICATION PROJECT | [7 empty] | Implementor: | Contract | No. of days suspended: |  | Disbursement: |  | Actual: | [7 empty] | Actual:
IGCS | Kinawitnon | 2nd Eng'g. Dist. | For verification |  |  |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | RURAL ELECTRIFICATION PROJECT | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | [6 empty] | Slippage: | 0%
IGCS | Kinawitnon | 2nd Eng'g. Dist. | For verification |  |  |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | RURAL ELECTRIFICATION PROJECT | [7 empty] | Date Allotment Released: | 2018-07-31 | Date completed:
IGCS | Kinawitnon | 2nd Eng'g. Dist. | For verification |  |  |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | RURAL ELECTRIFICATION PROJECT | [7 empty] | Date Started:
IGCS | Guilion | 2nd Eng'g. Dist. | Completed | 2019-10-31 |  | 2018 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various of Rural Electrification | Electrification expansion to Purok 7, Brgy. Guilon, samal Dist. IGCS |  | 20% Development Fund CY 2016 | Electrification |  |  | Contract | Project Cost: | 1537404.57 | Target Completion Date: |  | Program: | 1537404.57 | Planned: |  | Planned: |  | Planned: |  | Planned: | 100% | Planned: | 100% | No. of Persons: |  | Waiting for NTP (3E Electrical) | Waiting for NTP (3E Electrical) | Waiting for NTP (3E Electrical) | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per Program of Works
IGCS | Guilion | 2nd Eng'g. Dist. | Completed | 2019-10-31 |  | 2018 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various of Rural Electrification | [7 empty] | Project Engineer: | Porras | Revised Completion Date: |  | Allotment: | 1537404.57 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
IGCS | Guilion | 2nd Eng'g. Dist. | Completed | 2019-10-31 |  | 2018 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various of Rural Electrification | [7 empty] | Implementor: | LR Eng'g Services | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: | 100% | Actual: | 100%
IGCS | Guilion | 2nd Eng'g. Dist. | Completed | 2019-10-31 |  | 2018 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various of Rural Electrification | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
IGCS | Guilion | 2nd Eng'g. Dist. | Completed | 2019-10-31 |  | 2018 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various of Rural Electrification | [7 empty] | Date Allotment Released: |  | Date completed: | 0
IGCS | Guilion | 2nd Eng'g. Dist. | Completed | 2019-10-31 |  | 2018 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various of Rural Electrification | [7 empty] | Date Started: | 2019-10-31
Samal | Sta. Cruz | 2nd Eng'g. Dist. | Completed |  |  | 2016 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | RURAL ELECTRIFICATION PROJECT | Rural Electrification at brgy. Sta. Cruz, talikud, Samal |  | 20% DF CY 2016 | Electrification |  |  | Contract | Project Cost: | 2000000 | Target Completion Date: |  | Program: | 2000000 | Planned: |  | Planned: |  | Planned: | 100% | Planned: | 100% | Planned: | 100% | No. of Persons: |  | Delay due to slow action of Daneco for staking. c/o Engr. Kim | Delay due to slow action of Daneco for staking. c/o Engr. Kim | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per Program of Works
Samal | Sta. Cruz | 2nd Eng'g. Dist. | Completed |  |  | 2016 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | RURAL ELECTRIFICATION PROJECT | [7 empty] | Project Engineer: | Lu | Revised Completion Date: |  | Allotment: | 2000000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
Samal | Sta. Cruz | 2nd Eng'g. Dist. | Completed |  |  | 2016 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | RURAL ELECTRIFICATION PROJECT | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: | 100% | Actual: | 100% | Actual: | 100%
Samal | Sta. Cruz | 2nd Eng'g. Dist. | Completed |  |  | 2016 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | RURAL ELECTRIFICATION PROJECT | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Samal | Sta. Cruz | 2nd Eng'g. Dist. | Completed |  |  | 2016 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | RURAL ELECTRIFICATION PROJECT | [7 empty] | Date Allotment Released: |  | Date completed: | 2020-09-22
Samal | Sta. Cruz | 2nd Eng'g. Dist. | Completed |  |  | 2016 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | RURAL ELECTRIFICATION PROJECT | [7 empty] | Date Started:
BABAK | Kinawitnon | 2nd Eng'g. Dist. | On-going | 2018-03-12 |  | 2016 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) LS - P9,000,000.00 | Construction of Provincial Training Center , Compound Fence, Kinawitnon, Babak District, IGCS |  | 20% DF CY 2016 | Fence |  | sq.m | Admin | Project Cost: | 940000 | Target Completion Date: | 2018-06-19 23:59 | Program: | 940000 | Planned: | 68% | Planned: | 68% | Planned: | 68% | Planned: | 68% | Planned: | 68% | No. of Persons: |  | Temporarily suspended 4/23/18 due to undemolished structures of illegal settlers | Temporarily suspended 4/23/18 due to undemolished structures of illegal settlers | Temporarily suspended April 23, 2018 due to undemolished structures of illegal settlers(For resumption) | Temporarily suspended April 23, 2018 due to undemolished structures of illegal settlers(For resumption) | Temporarily suspended April 23, 2018 due to undemolished structures of illegal settlers(For resumption) | Temporarily suspended April 23, 2018 due to undemolished structures of illegal settlers(For resumption)
BABAK | Kinawitnon | 2nd Eng'g. Dist. | On-going | 2018-03-12 |  | 2016 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) LS - P9,000,000.00 | [7 empty] | Project Engineer: | Pacquiao | Revised Completion Date: |  | Allotment: | 940000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
BABAK | Kinawitnon | 2nd Eng'g. Dist. | On-going | 2018-03-12 |  | 2016 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) LS - P9,000,000.00 | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: | 933418.8 | Actual: | 75% | Actual: | 75% | Actual: | 75% | Actual: | 75% | Actual: | 75%
BABAK | Kinawitnon | 2nd Eng'g. Dist. | On-going | 2018-03-12 |  | 2016 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) LS - P9,000,000.00 | [7 empty] | Duration: | 100 | No. of days extended: |  |  |  | Slippage: | 7% | Slippage: | 7% | Slippage: | 7% | Slippage: | 7% | Slippage: | 7%
BABAK | Kinawitnon | 2nd Eng'g. Dist. | On-going | 2018-03-12 |  | 2016 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) LS - P9,000,000.00 | [7 empty] | Date Allotment Released: | 2017-09-19 | Date completed:
BABAK | Kinawitnon | 2nd Eng'g. Dist. | On-going | 2018-03-12 |  | 2016 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) LS - P9,000,000.00 | [7 empty] | Date Started: | 2018-03-12
Kapalong | Mabantao-Florida | 1st Eng'g. Dist. | completed | 2019-11-11 | 2020-09-30 | 2016 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | QRF | Rehab. Of Slope Protection of Libuganon River Along Kapalong - Mabantao - Florida Prov'l. Road Phase I |  | QRF CY 2016 | Slope Protection |  |  |  | Project Cost: | 900000 | Target Completion Date: | 2020-09-30 23:59 | Program: | 900000 | Planned: |  | Planned: |  | Planned: | 100% | Planned: | 100% | Planned: | 100% | No. of Persons: | 13 | For AIP Amendment | For AIP Amendment | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per Program of Works
Kapalong | Mabantao-Florida | 1st Eng'g. Dist. | completed | 2019-11-11 | 2020-09-30 | 2016 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | QRF | [7 empty] | Project Engineer: | Bacaron | Revised Completion Date: |  | Allotment: | 900000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 169
Kapalong | Mabantao-Florida | 1st Eng'g. Dist. | completed | 2019-11-11 | 2020-09-30 | 2016 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | QRF | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: | 100% | Actual: | 100% | Actual: | 100%
Kapalong | Mabantao-Florida | 1st Eng'g. Dist. | completed | 2019-11-11 | 2020-09-30 | 2016 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | QRF | [7 empty] | Duration: | 325 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Kapalong | Mabantao-Florida | 1st Eng'g. Dist. | completed | 2019-11-11 | 2020-09-30 | 2016 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | QRF | [7 empty] | Date Allotment Released: |  | Date completed: | 2020-09-30
Kapalong | Mabantao-Florida | 1st Eng'g. Dist. | completed | 2019-11-11 | 2020-09-30 | 2016 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | QRF | [7 empty] | Date Started: | 2019-11-11
Tagum City | Timog | 1st Eng'g. Dist. | completed | 2019-11-11 | 2020-09-30 | 2015&2016 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | QRF | Repair of Damaged/Creeks Along Timog Creek, Tagum City |  | QRF CY 2015 & 2016 | Slope Protection |  |  |  | Project Cost: | 810000 | Target Completion Date: | 2020-03-21 23:46 | Program: | 810000 | Planned: |  | Planned: |  | Planned: | 100% | Planned: | 100% | Planned: | 100% | No. of Persons: | 13 | For AIP Amendment | For AIP Amendment | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per Program of Works
Tagum City | Timog | 1st Eng'g. Dist. | completed | 2019-11-11 | 2020-09-30 | 2015&2016 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | QRF | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 810000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 169
Tagum City | Timog | 1st Eng'g. Dist. | completed | 2019-11-11 | 2020-09-30 | 2015&2016 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | QRF | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: | 100% | Actual: | 100% | Actual: | 100%
Tagum City | Timog | 1st Eng'g. Dist. | completed | 2019-11-11 | 2020-09-30 | 2015&2016 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | QRF | [7 empty] | Duration: | 80 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Tagum City | Timog | 1st Eng'g. Dist. | completed | 2019-11-11 | 2020-09-30 | 2015&2016 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | QRF | [7 empty] | Date Allotment Released: |  | Date completed: | 2020-02-15
Tagum City | Timog | 1st Eng'g. Dist. | completed | 2019-11-11 | 2020-09-30 | 2015&2016 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | QRF | [7 empty] | Date Started: | 2020-01-02
Tagum City | Timog | 1st Eng'g. Dist. | On-going | 2020-01-06 |  | 2015&2016 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | QRF | Repair of Damaged/Creeks Along Mankilam Creek, Tagum City |  | QRF CY 2015 & 2016 | Slope Protection |  |  |  | Project Cost: | 1050000 | Target Completion Date: | 2020-04-04 23:46 | Program: | 1050000 | Planned: |  | Planned: |  | Planned: | 100% | Planned: | 100% | Planned: | 63.85% | No. of Persons: | 10 | For AIP Amendment | For AIP Amendment | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | On-going
Tagum City | Timog | 1st Eng'g. Dist. | On-going | 2020-01-06 |  | 2015&2016 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | QRF | [7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-01-30 23:46 | Allotment: | 1050000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 169
Tagum City | Timog | 1st Eng'g. Dist. | On-going | 2020-01-06 |  | 2015&2016 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | QRF | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: | 100% | Actual: | 100% | Actual: | 63.85%
Tagum City | Timog | 1st Eng'g. Dist. | On-going | 2020-01-06 |  | 2015&2016 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | QRF | [7 empty] | Duration: | 90 | No. of days extended: | 301 |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Tagum City | Timog | 1st Eng'g. Dist. | On-going | 2020-01-06 |  | 2015&2016 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | QRF | [7 empty] | Date Allotment Released: |  | Date completed:
Tagum City | Timog | 1st Eng'g. Dist. | On-going | 2020-01-06 |  | 2015&2016 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | QRF | [7 empty] | Date Started: | 2020-01-06
Tagum City | Mankilam | 1st Eng'g. Dist. | Completed | 2019-11-04 | 2020-08-26 | 2015&2016 | Administration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | QRF | Ground Development and landscape @ PDRRMD, Gov't. Center, Mankilam, Tagum City |  | QRF CY 2015 & 2016 | landscaping |  | km | Admin | Project Cost: | 1000000 | Target Completion Date: | 2020-08-26 23:59 | Program: | 1000000 | Planned: |  | Planned: |  | Planned: |  | Planned: | 100% | Planned: | 100% | No. of Persons: |  | Final Abstract # 0320200900 (Alpebel Builders & Supply Corp.) | Final Abstract # 0320200900 (Alpebel Builders & Supply Corp.) | Final Abstract # 0320200900 (Alpebel Builders & Supply Corp.) | Completed as per physical accomplishment. | Completed as per physical accomplishment. | Completed as per Program of Works
Tagum City | Mankilam | 1st Eng'g. Dist. | Completed | 2019-11-04 | 2020-08-26 | 2015&2016 | Administration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | QRF | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 1000000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
Tagum City | Mankilam | 1st Eng'g. Dist. | Completed | 2019-11-04 | 2020-08-26 | 2015&2016 | Administration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | QRF | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: | 100% | Actual: | 100%
Tagum City | Mankilam | 1st Eng'g. Dist. | Completed | 2019-11-04 | 2020-08-26 | 2015&2016 | Administration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | QRF | [7 empty] | Duration: | 297 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Tagum City | Mankilam | 1st Eng'g. Dist. | Completed | 2019-11-04 | 2020-08-26 | 2015&2016 | Administration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | QRF | [7 empty] | Date Allotment Released: |  | Date completed: | 2020-08-26
Tagum City | Mankilam | 1st Eng'g. Dist. | Completed | 2019-11-04 | 2020-08-26 | 2015&2016 | Administration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | QRF | [7 empty] | Date Started: | 2019-11-04
Asuncion | Saug | 1st Eng'g. Dist. | On-going | 2019-01-03 |  | 2015&2016 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | QRF | Rehab. Of Saug Bridge of Slope Protection, New Corella |  | QRF CY 2015 & 2016 | Slope Protection | 356.4 | ln.m | Admin | Project Cost: | 4850000 | Target Completion Date: | 2019-05-02 23:46 | Program: | 4850000 | Planned: | 84.06% | Planned: | 100% | Planned: | 100% | Planned: | 100% | Planned: | 100% | No. of Persons: | 7 | Final Abstract # 0320200900 (Alpebel Builders & Supply Corp.) | Final Abstract # 0320200900 (Alpebel Builders & Supply Corp.) | Final Abstract # 0320200900 (Alpebel Builders & Supply Corp.) | Completed as per physical accomplishment. | Completed as per physical accomplishment. | Completed as per Program of Works
Asuncion | Saug | 1st Eng'g. Dist. | On-going | 2019-01-03 |  | 2015&2016 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | QRF | [7 empty] | Project Engineer: | Gone | Revised Completion Date: | 2020-12-30 23:46 | Allotment: | 4850000 | Revised: |  | Revised: | 77.89% | Revised: | 77.89% | Revised: | 77.89% | Revised: |  | No. of Man-days: | 182
Asuncion | Saug | 1st Eng'g. Dist. | On-going | 2019-01-03 |  | 2015&2016 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | QRF | [7 empty] | Implementor: | PEO | No. of days suspended: | 533 | Disbursement: | 1628912.92 | Actual: | 77.63% | Actual: | 86.91% | Actual: | 86.91% | Actual: | 86.91% | Actual: | 100%
Asuncion | Saug | 1st Eng'g. Dist. | On-going | 2019-01-03 |  | 2015&2016 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | QRF | [7 empty] | Duration: | 120 | No. of days extended: | 75 |  |  | Slippage: | -6.43% | Slippage: | 9.02% | Slippage: | 9.02% | Slippage: | 9.02% | Slippage: | 0%
Asuncion | Saug | 1st Eng'g. Dist. | On-going | 2019-01-03 |  | 2015&2016 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | QRF | [7 empty] | Date Allotment Released: | 2018-05-25 | Date completed:
Asuncion | Saug | 1st Eng'g. Dist. | On-going | 2019-01-03 |  | 2015&2016 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | QRF | [7 empty] | Date Started: | 2019-01-03
Kapalong | Mamacao | 1st Eng'g. Dist. | On-going | 2020-12-01 |  | 2015&2016 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | QRF | Rehab./Repair of Mamacao Bailey Bridge (Retrofitting of Pier and Substructure) |  | QRF CY 2015 & 2016 | Slope Protection | 356.4 | ln.m | Admin | Project Cost: | 2000000 | Target Completion Date: | 2021-03-30 23:46 | Program: | 2000000 | Planned: | 84.06% | Planned: | 100% | Planned: | 100% | Planned: | 100% | Planned: | 3.86% | No. of Persons: | 13 | Final Abstract # 0320200900 (Alpebel Builders & Supply Corp.) | Final Abstract # 0320200900 (Alpebel Builders & Supply Corp.) | Final Abstract # 0320200900 (Alpebel Builders & Supply Corp.) | Completed as per physical accomplishment. | Completed as per physical accomplishment. | On-going
Kapalong | Mamacao | 1st Eng'g. Dist. | On-going | 2020-12-01 |  | 2015&2016 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | QRF | [7 empty] | Project Engineer: | Lumapat | Revised Completion Date: |  | Allotment: | 2000000 | Revised: |  | Revised: | 77.89% | Revised: | 77.89% | Revised: | 77.89% | Revised: |  | No. of Man-days: | 338
Kapalong | Mamacao | 1st Eng'g. Dist. | On-going | 2020-12-01 |  | 2015&2016 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | QRF | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: | 77.63% | Actual: | 86.91% | Actual: | 86.91% | Actual: | 86.91% | Actual: | 1.56%
Kapalong | Mamacao | 1st Eng'g. Dist. | On-going | 2020-12-01 |  | 2015&2016 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | QRF | [7 empty] | Duration: | 120 | No. of days extended: |  |  |  | Slippage: | -6.43% | Slippage: | 9.02% | Slippage: | 9.02% | Slippage: | 9.02% | Slippage: | -2.3%
Kapalong | Mamacao | 1st Eng'g. Dist. | On-going | 2020-12-01 |  | 2015&2016 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | QRF | [7 empty] | Date Allotment Released: |  | Date completed:
Kapalong | Mamacao | 1st Eng'g. Dist. | On-going | 2020-12-01 |  | 2015&2016 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | QRF | [7 empty] | Date Started: | 2020-12-01
Kapalong | Capungagan | 1st Eng'g. Dist. | Completed | 2019-03-19 | 2020-07-20 | 2016 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PRDP | Cacao Production and Beans Marketing, Capungagan, Kapalong, Davao del Norte |  | PRDP CY 2016 | Building | 3610 | sq.m | Contract | Project Cost: | 5873626.8 | Target Completion Date: | 2019-11-24 | Program: | 5873626.8 | Planned: | 100% | Planned: | 100% | Planned: | 100% | Planned: | 100% | Planned: | 100% | No. of Persons: |  | Fund already transferred at Municipality of Talaingod with ChecK No. 2445181 and OR # 7955667, dated March 16, 2018 . Amended from Electrification @ Prk. 1A-Prk. 5A) | On-going (Implemented by MLGU, since transfer of fund ) | On-going (Implemented by MLGU, since transfer of fund ) | Completed as per physical accomplishment. | Completed as per physical accomplishment. | Completed as per Program of Works
Kapalong | Capungagan | 1st Eng'g. Dist. | Completed | 2019-03-19 | 2020-07-20 | 2016 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PRDP | [7 empty] | Project Engineer: | Delos Reyes | Revised Completion Date: | 2020-07-20 | Allotment: | 5873626.8 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
Kapalong | Capungagan | 1st Eng'g. Dist. | Completed | 2019-03-19 | 2020-07-20 | 2016 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PRDP | [7 empty] | Implementor: | MICAH CONST. & SUPPLY | No. of days suspended: | 239 | Disbursement: | 4698901.44 | Actual: | 100% | Actual: | 100% | Actual: | 100% | Actual: | 100% | Actual: | 100%
Kapalong | Capungagan | 1st Eng'g. Dist. | Completed | 2019-03-19 | 2020-07-20 | 2016 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PRDP | [7 empty] | Duration: | 250 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Kapalong | Capungagan | 1st Eng'g. Dist. | Completed | 2019-03-19 | 2020-07-20 | 2016 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PRDP | [7 empty] | Date Allotment Released: | CY 2016 | Date completed: | 2020-07-20
Kapalong | Capungagan | 1st Eng'g. Dist. | Completed | 2019-03-19 | 2020-07-20 | 2016 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PRDP | [7 empty] | Date Started: | 2019-03-19
New Corella | Poblacion | 1st Eng'g. Dist. | Completed | 2019-01-17 | 2020-10-31 | 2016 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PRDP | Improvement of New Corella Nursery with Organic Input Production & Common Facility, Davao del Norte |  | PRDP CY 2016 | Building | 1901 | sq.m | Contract | Project Cost: | 9889628.45 | Target Completion Date: | 2019-11-23 | Program: | 9889628.45 | Planned: | 94.55% | Planned: | 100% | Planned: | 100% | Planned: | 100% | Planned: | 100% | No. of Persons: |  | Fund already transferred at Municipality of Talaingod with ChecK No. 2445181 and OR # 7955667, dated March 16, 2018 . Amended from Electrification @ Prk. 1A-Prk. 5A) | On-going (Implemented by MLGU, since transfer of fund ) | On-going (Implemented by MLGU, since transfer of fund ) | Completed as per physical accomplishment. | Completed as per physical accomplishment. | Completed as per Program of Works
New Corella | Poblacion | 1st Eng'g. Dist. | Completed | 2019-01-17 | 2020-10-31 | 2016 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PRDP | [7 empty] | Project Engineer: | Delos Reyes/Cabañero | Revised Completion Date: | 2020-08-09 | Allotment: | 9889628.45 | Revised: | 78.32% | Revised: | 83.43% | Revised: | 83.43% | Revised: | 83.43% | Revised: |  | No. of Man-days:
New Corella | Poblacion | 1st Eng'g. Dist. | Completed | 2019-01-17 | 2020-10-31 | 2016 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PRDP | [7 empty] | Implementor: | SOUTH IRONROCK CORPORATION | No. of days suspended: | 260 | Disbursement: | 5933777.07 | Actual: | 71.89% | Actual: | 75.19% | Actual: | 75.19% | Actual: | 75.19% | Actual: | 100%
New Corella | Poblacion | 1st Eng'g. Dist. | Completed | 2019-01-17 | 2020-10-31 | 2016 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PRDP | [7 empty] | Duration: | 310 | No. of days extended: |  |  |  | Slippage: | -6.424% | Slippage: | -8.238% | Slippage: | -8.238% | Slippage: | -8.238% | Slippage: | 0%
New Corella | Poblacion | 1st Eng'g. Dist. | Completed | 2019-01-17 | 2020-10-31 | 2016 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PRDP | [7 empty] | Date Allotment Released: | CY 2016 | Date completed: | 2020-10-31
New Corella | Poblacion | 1st Eng'g. Dist. | Completed | 2019-01-17 | 2020-10-31 | 2016 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PRDP | [7 empty] | Date Started: | 2019-01-17
Sto. Tomas |  | 2nd Eng'g. Dist. | On-going | 2018-01-29 |  | 2016 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PRDP | Improvement of Sto. Tomas Production Center with Common Facility, Sto. Tomas |  | PRDP CY 2016 | Building | 1901 | sq.m | Contract | Project Cost: | 9825000 | Target Completion Date: | 2018-12-24 23:59 | Program: | 9825000 | Planned: | 94.55% | Planned: | 100% | Planned: | 100% | Planned: | 100% | Planned: | 100% | No. of Persons: | 20 | On-going | Final Abstract # 0320200900 (Alpebel Builders & Supply Corp.) | Final Abstract # 0320200900 (Alpebel Builders & Supply Corp.) | Completed as per physical accomplishment. | Completed as per physical accomplishment. | On-going
Sto. Tomas |  | 2nd Eng'g. Dist. | On-going | 2018-01-29 |  | 2016 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PRDP | [7 empty] | Project Engineer: | Azotes | Revised Completion Date: | May 24, 2021 | Allotment: | 9825000 | Revised: | 78.32% | Revised: | 83.43% | Revised: | 83.43% | Revised: | 83.43% | Revised: | 22.53% | No. of Man-days: | 500
Sto. Tomas |  | 2nd Eng'g. Dist. | On-going | 2018-01-29 |  | 2016 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PRDP | [7 empty] | Implementor: | Manantan | No. of days suspended: | 501 | Disbursement: |  | Actual: | 71.89% | Actual: | 75.19% | Actual: | 75.19% | Actual: | 75.19% | Actual: | 30.33%
Sto. Tomas |  | 2nd Eng'g. Dist. | On-going | 2018-01-29 |  | 2016 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PRDP | [7 empty] | Duration: | 330 | No. of days extended: |  |  |  | Slippage: | -6.424% | Slippage: | -8.238% | Slippage: | -8.238% | Slippage: | -8.238% | Slippage: | 7.8%
Sto. Tomas |  | 2nd Eng'g. Dist. | On-going | 2018-01-29 |  | 2016 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PRDP | [7 empty] | Date Allotment Released: | CY 2014 | Date completed:
Sto. Tomas |  | 2nd Eng'g. Dist. | On-going | 2018-01-29 |  | 2016 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PRDP | [7 empty] | Date Started: | 2018-01-29
New Corella | Sta. Fe | 1st Eng'g. Dist. | Completed | 2019-11-04 | 2020-01-24 | 2017 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various of Rural Electrification | Electrification of Purok 1-4, Sta. Cruz, New Corella |  | 20% DF CY 2017 | Electrification |  |  | Contract | Project Cost: | 2500000 | Target Completion Date: | 2020-01-24 23:59 | Program: | 2500000 | Planned: |  | Planned: |  | Planned: |  | Planned: | 100% | Planned: | 100% | No. of Persons: |  | Fund already transferred at Municipality of Talaingod with ChecK No. 2445181 and OR # 7955667, dated March 16, 2018 . Amended from Electrification @ Prk. 1A-Prk. 5A) | On-going (Implemented by MLGU, since transfer of fund ) | On-going (Implemented by MLGU, since transfer of fund ) | Completed as per physical accomplishment. | Completed as per physical accomplishment. | Completed as per Program of Works
New Corella | Sta. Fe | 1st Eng'g. Dist. | Completed | 2019-11-04 | 2020-01-24 | 2017 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various of Rural Electrification | [7 empty] | Project Engineer: | Lu | Revised Completion Date: | 2020-01-24 23:59 | Allotment: | 2500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
New Corella | Sta. Fe | 1st Eng'g. Dist. | Completed | 2019-11-04 | 2020-01-24 | 2017 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various of Rural Electrification | [7 empty] | Implementor: | LR ENG'G. SERVICES | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: | 100% | Actual: | 100%
New Corella | Sta. Fe | 1st Eng'g. Dist. | Completed | 2019-11-04 | 2020-01-24 | 2017 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various of Rural Electrification | [7 empty] | Duration: | 82 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
New Corella | Sta. Fe | 1st Eng'g. Dist. | Completed | 2019-11-04 | 2020-01-24 | 2017 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various of Rural Electrification | [7 empty] | Date Allotment Released: |  | Date completed: | 2020-01-24
New Corella | Sta. Fe | 1st Eng'g. Dist. | Completed | 2019-11-04 | 2020-01-24 | 2017 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various of Rural Electrification | [7 empty] | Date Started: | 2019-11-04
Asuncion | Sagayen | 1st Eng'g. Dist. | Suspended | 2018-11-15 |  | 2017 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various of Water System | Construction of Water Reservoir & Purchase of P.E. Pipelines, Sagayen, Asuncion |  | 20% DF CY 2017 (STIMULUS) | Water System |  |  | MLGU | Project Cost: | 500000 | Target Completion Date: | 2018-11-15 | Program: | 500000 | Planned: | 90% | Planned: | 90% | Planned: | 90% | Planned: | 90% | Planned: | 90% | No. of Persons: |  | Suspended due to non availability of water source during drilling.Find another location. Fund already transferred at Municipality of Asuncion with ChecK No. 2445174 and OR # 9238468, | Suspended due to non availability of water source during drilling.Find another location. Fund already transferred at Municipality of Asuncion with ChecK No. 2445174 and OR # 9238468, | Project not implemented due to non availability of water source during drilling. Awaiting for the official documents from Brgy. Sagayen and MLGU - Asuncion for the cancellation of the project. | Project not implemented due to non availability of water source during drilling. Awaiting for the official documents from Brgy. Sagayen and MLGU - Asuncion for the cancellation of the project. | Project not implemented due to non availability of water source during drilling. Awaiting for the official documents from Brgy. Sagayen and MLGU - Asuncion for the cancellation of the project. | Project not implemented due to non availability of water source during drilling. Awaiting for the official documents from Brgy. Sagayen and MLGU - Asuncion for the cancellation of the project.
Asuncion | Sagayen | 1st Eng'g. Dist. | Suspended | 2018-11-15 |  | 2017 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various of Water System | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
Asuncion | Sagayen | 1st Eng'g. Dist. | Suspended | 2018-11-15 |  | 2017 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various of Water System | [7 empty] | Implementor: | MEO | No. of days suspended: |  | Disbursement: |  | Actual: | 90% | Actual: | 90% | Actual: | 90% | Actual: | 90% | Actual: | 90%
Asuncion | Sagayen | 1st Eng'g. Dist. | Suspended | 2018-11-15 |  | 2017 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various of Water System | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Asuncion | Sagayen | 1st Eng'g. Dist. | Suspended | 2018-11-15 |  | 2017 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various of Water System | [7 empty] | Date Allotment Released: | 2017-12-28 | Date completed:
Asuncion | Sagayen | 1st Eng'g. Dist. | Suspended | 2018-11-15 |  | 2017 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various of Water System | [7 empty] | Date Started: | 2018-11-15
New Corella | Sta. Fe | 1st Eng'g. Dist. | On-going | 2020-08-25 |  | 2017 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2017 | Road Rehabilitation at Prk. 1-Prk. 5, Sta. Fe, New Corella |  | 20% DF CY 2017 (STIMULUS) | Court |  |  | MLGU | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Fund already transferred at Municipality of Talaingod with ChecK No. 2445181 and OR # 7955667, dated March 16, 2018 . Amended from Electrification @ Prk. 1A-Prk. 5A) | On-going (Implemented by MLGU, since transfer of fund ) | On-going (Implemented by MLGU, since transfer of fund ) | On-going (Implemented by MLGU, since transfer of fund ) | On-going (Implemented by MLGU, since transfer of fund ) | On-going (Implemented by MLGU, since transfer of fund )
New Corella | Sta. Fe | 1st Eng'g. Dist. | On-going | 2020-08-25 |  | 2017 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2017 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
New Corella | Sta. Fe | 1st Eng'g. Dist. | On-going | 2020-08-25 |  | 2017 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2017 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
New Corella | Sta. Fe | 1st Eng'g. Dist. | On-going | 2020-08-25 |  | 2017 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2017 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
New Corella | Sta. Fe | 1st Eng'g. Dist. | On-going | 2020-08-25 |  | 2017 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2017 | [7 empty] | Date Allotment Released: | 2017-12-28 | Date completed:
New Corella | Sta. Fe | 1st Eng'g. Dist. | On-going | 2020-08-25 |  | 2017 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2017 | [7 empty] | Date Started: | 2020-08-25
Carmen | Tibulao | 2nd Eng'g. Dist. | Hold in Abeyance |  |  | 2017 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2017 | Construction of Concrete Pavement, Tibulao, Carmen |  | 20% DF CY 2017 (STIMULUS) | Pavement |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Fund already transferred at Municipality of Talaingod with ChecK No. 2445181 and OR # 7955667, dated March 16, 2018 . Amended from Electrification @ Prk. 1A-Prk. 5A) | On-going (Implemented by MLGU, since transfer of fund ) | On-going (Implemented by MLGU, since transfer of fund ) | Hold in abeyance | Hold in abeyance | Hold in abeyance
Carmen | Tibulao | 2nd Eng'g. Dist. | Hold in Abeyance |  |  | 2017 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2017 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
Carmen | Tibulao | 2nd Eng'g. Dist. | Hold in Abeyance |  |  | 2017 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2017 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
Carmen | Tibulao | 2nd Eng'g. Dist. | Hold in Abeyance |  |  | 2017 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2017 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Carmen | Tibulao | 2nd Eng'g. Dist. | Hold in Abeyance |  |  | 2017 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2017 | [7 empty] | Date Allotment Released: |  | Date completed:
Carmen | Tibulao | 2nd Eng'g. Dist. | Hold in Abeyance |  |  | 2017 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2017 | [7 empty] | Date Started:
Panabo City | San Nicolas | 2nd Eng'g. Dist. | Completed |  |  | 2017 | MLGU | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2017 | Const. of Multi-Purpose Bldg. (Back Stage/Office), San Nicolas, San Nicolas, Panabo City |  | 20% DF CY 2017 (STIMULUS) | Pavement |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: | 100% | No. of Persons: |  | Fund already transferred at Municipality of Talaingod with ChecK No. 2445181 and OR # 7955667, dated March 16, 2018 . Amended from Electrification @ Prk. 1A-Prk. 5A) | On-going (Implemented by MLGU, since transfer of fund ) | On-going (Implemented by MLGU, since transfer of fund ) |  |  | Completed (Implemented by MLGU, since transfer of fund )
Panabo City | San Nicolas | 2nd Eng'g. Dist. | Completed |  |  | 2017 | MLGU | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2017 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
Panabo City | San Nicolas | 2nd Eng'g. Dist. | Completed |  |  | 2017 | MLGU | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2017 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual: | 100%
Panabo City | San Nicolas | 2nd Eng'g. Dist. | Completed |  |  | 2017 | MLGU | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2017 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Panabo City | San Nicolas | 2nd Eng'g. Dist. | Completed |  |  | 2017 | MLGU | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2017 | [7 empty] | Date Allotment Released: |  | Date completed:
Panabo City | San Nicolas | 2nd Eng'g. Dist. | Completed |  |  | 2017 | MLGU | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2017 | [7 empty] | Date Started:
Panabo City | Kauswagan | 2nd Eng'g. Dist. | Completed | 2019-02-04 | 2020-02-03 | 2017 | MLGU | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2017 | Impv't. of Multi-Purpose Gym, Kauswagan, Panabo City |  | 20% DF CY 2017 (STIMULUS) | GYM |  |  | MLGU | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: | 100% | Planned: | 100% | Planned: | 100% | Planned: | 100% | Planned: | 100% | No. of Persons: |  | Completed (Implemented by MLGU, since transfer of fund ) | Completed (Implemented by MLGU, since transfer of fund ) | Completed (Implemented by MLGU, since transfer of fund ) | Completed (Implemented by MLGU, since transfer of fund ) | Completed (Implemented by MLGU, since transfer of fund ) | Completed (Implemented by MLGU, since transfer of fund )
Panabo City | Kauswagan | 2nd Eng'g. Dist. | Completed | 2019-02-04 | 2020-02-03 | 2017 | MLGU | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2017 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
Panabo City | Kauswagan | 2nd Eng'g. Dist. | Completed | 2019-02-04 | 2020-02-03 | 2017 | MLGU | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2017 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: | 100% | Actual: | 100% | Actual: | 100% | Actual: | 100% | Actual: | 100%
Panabo City | Kauswagan | 2nd Eng'g. Dist. | Completed | 2019-02-04 | 2020-02-03 | 2017 | MLGU | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2017 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Panabo City | Kauswagan | 2nd Eng'g. Dist. | Completed | 2019-02-04 | 2020-02-03 | 2017 | MLGU | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2017 | [7 empty] | Date Allotment Released: | 2019-02-04 | Date completed: | 2020-02-03
Panabo City | Kauswagan | 2nd Eng'g. Dist. | Completed | 2019-02-04 | 2020-02-03 | 2017 | MLGU | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2017 | [7 empty] | Date Started:
Panabo City | Cacao | 2nd Eng'g. Dist. | On-going |  |  | 2017 | MLGU | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2017 | Construction of 2 Rooms Comfort Room, Brgy. Cacao, Panabo City |  | 20% DF CY 2017 (STIMULUS) | Building |  | sq.m | MLGU | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | Planned: | 100% | Planned: | 100% | Planned: |  | Planned: |  | No. of Persons: |  | Issued warning for termination of the contract | Completed (Implemented by MLGU, since transfer of fund ) | Completed (Implemented by MLGU, since transfer of fund ) |  |  | On-going (Implemented by MLGU, since transfer of fund )
Panabo City | Cacao | 2nd Eng'g. Dist. | On-going |  |  | 2017 | MLGU | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2017 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
Panabo City | Cacao | 2nd Eng'g. Dist. | On-going |  |  | 2017 | MLGU | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2017 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: | 100% |  | 100%
Panabo City | Cacao | 2nd Eng'g. Dist. | On-going |  |  | 2017 | MLGU | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2017 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: |  | Slippage: |  | Slippage:
Panabo City | Cacao | 2nd Eng'g. Dist. | On-going |  |  | 2017 | MLGU | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2017 | [7 empty] | Date Allotment Released: |  | Date completed:
Panabo City | Cacao | 2nd Eng'g. Dist. | On-going |  |  | 2017 | MLGU | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2017 | [7 empty] | Date Started:
Panabo City | A.O. Floreindo | 2nd Eng'g. Dist. | On-going |  |  | 2017 | MLGU | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2017 | Const. of Multi-Purpose Bldg. @ A.O. Floriendo National Highschool, Panabo City |  | 20% DF CY 2017 (STIMULUS) | Building |  |  | MLGU | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Fund transfer to LGU- 3/28/2019 with check no. 2574939 and OR no. 0166518 - Materials Delivered. Construction on-going | Materials already procured. Ongoing hiring of Admin Laborers. Target date to start the project on September 14, 2020.(Implemented by MLGU, since transfer of fund ) | On-going .(Implemented by MLGU, since transfer of fund ) | On-going .(Implemented by MLGU, since transfer of fund ) | On-going .(Implemented by MLGU, since transfer of fund ) | On-going .(Implemented by MLGU, since transfer of fund )
Panabo City | A.O. Floreindo | 2nd Eng'g. Dist. | On-going |  |  | 2017 | MLGU | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2017 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
Panabo City | A.O. Floreindo | 2nd Eng'g. Dist. | On-going |  |  | 2017 | MLGU | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2017 | [7 empty] | Implementor: | MLGU | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
Panabo City | A.O. Floreindo | 2nd Eng'g. Dist. | On-going |  |  | 2017 | MLGU | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2017 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Panabo City | A.O. Floreindo | 2nd Eng'g. Dist. | On-going |  |  | 2017 | MLGU | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2017 | [7 empty] | Date Allotment Released: | 2017-12-19 | Date completed:
Panabo City | A.O. Floreindo | 2nd Eng'g. Dist. | On-going |  |  | 2017 | MLGU | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2017 | [7 empty] | Date Started:
Panabo City | Kimamon | 2nd Eng'g. Dist. | On-going |  |  | 2017 | MLGU | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Drainage | Const. of Concrete Drainage Canal, Kimamon, Panabo City |  | 20% DF CY 2017 (STIMULUS) | Drainage |  |  | MLGU | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | For Implementation | For Implementation | For Implementation | For Implementation | For Implementation | For Implementation
Panabo City | Kimamon | 2nd Eng'g. Dist. | On-going |  |  | 2017 | MLGU | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Drainage | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
Panabo City | Kimamon | 2nd Eng'g. Dist. | On-going |  |  | 2017 | MLGU | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Drainage | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
Panabo City | Kimamon | 2nd Eng'g. Dist. | On-going |  |  | 2017 | MLGU | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Drainage | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Panabo City | Kimamon | 2nd Eng'g. Dist. | On-going |  |  | 2017 | MLGU | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Drainage | [7 empty] | Date Allotment Released: | 2017-12-19 | Date completed:
Panabo City | Kimamon | 2nd Eng'g. Dist. | On-going |  |  | 2017 | MLGU | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Drainage | [7 empty] | Date Started:
Sto. Tomas | Tulalian | 2nd Eng'g. Dist. | Completed | 2018-12-18 | 2019-03-19 | 2017 | MLGU | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Drainage | Const. of Violence Against Women and Children Center, Tulalian |  | 20% DF CY 2017 (STIMULUS) | Drainage |  |  | MLGU | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | Planned: |  | Planned: |  | Planned: | 100% | Planned: | 100% | No. of Persons: |  | For Implementation | For Implementation | For Implementation | Completed | Completed | Completed as per Program of Works
Sto. Tomas | Tulalian | 2nd Eng'g. Dist. | Completed | 2018-12-18 | 2019-03-19 | 2017 | MLGU | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Drainage | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
Sto. Tomas | Tulalian | 2nd Eng'g. Dist. | Completed | 2018-12-18 | 2019-03-19 | 2017 | MLGU | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Drainage | [7 empty] | Implementor: | MLGU | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: | 100% | Actual: | 100%
Sto. Tomas | Tulalian | 2nd Eng'g. Dist. | Completed | 2018-12-18 | 2019-03-19 | 2017 | MLGU | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Drainage | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Sto. Tomas | Tulalian | 2nd Eng'g. Dist. | Completed | 2018-12-18 | 2019-03-19 | 2017 | MLGU | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Drainage | [7 empty] | Date Allotment Released: | 2017-12-19 | Date completed: | 2019-03-19
Sto. Tomas | Tulalian | 2nd Eng'g. Dist. | Completed | 2018-12-18 | 2019-03-19 | 2017 | MLGU | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Drainage | [7 empty] | Date Started: | Dec. 18, 2018
IGCS | Toril | 2nd Eng'g. Dist. | Completed | 2020-08-05 | 2020-08-21 | 2017 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various of Rural Electrification | Electrification of Prk. 4 & 6, Brgy. Toril, IGCS |  | 20% DF CY 2017 (STIMULUS) | Electrification |  |  | Contract | Project Cost: | 500000 | Target Completion Date: | 2020-09-03 23:59 | Program: | 500000 | Planned: |  | Planned: |  | Planned: |  | Planned: | 100% | Planned: | 100% | No. of Persons: |  | Fund already transferred at Municipality of Talaingod with ChecK No. 2445181 and OR # 7955667, dated March 16, 2018 . Amended from Electrification @ Prk. 1A-Prk. 5A) | On-going (Implemented by MLGU, since transfer of fund ) | On-going (Implemented by MLGU, since transfer of fund ) | Completed | Completed | Completed as per Program of Works
IGCS | Toril | 2nd Eng'g. Dist. | Completed | 2020-08-05 | 2020-08-21 | 2017 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various of Rural Electrification | [7 empty] | Project Engineer: | Lu | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
IGCS | Toril | 2nd Eng'g. Dist. | Completed | 2020-08-05 | 2020-08-21 | 2017 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various of Rural Electrification | [7 empty] | Implementor: | 3E Electrical Sales & Services | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: | 100% | Actual: | 100%
IGCS | Toril | 2nd Eng'g. Dist. | Completed | 2020-08-05 | 2020-08-21 | 2017 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various of Rural Electrification | [7 empty] | Duration: | 30 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
IGCS | Toril | 2nd Eng'g. Dist. | Completed | 2020-08-05 | 2020-08-21 | 2017 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various of Rural Electrification | [7 empty] | Date Allotment Released: |  | Date completed: | 2020-08-21
IGCS | Toril | 2nd Eng'g. Dist. | Completed | 2020-08-05 | 2020-08-21 | 2017 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various of Rural Electrification | [7 empty] | Date Started: | 2020-08-05
IGCS | Anonang | 2nd Eng'g. Dist. | Completed |  |  |  | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various of Rural Electrification | Impv't. of Brgy. Street Electrification at Brgy. Anonang, IGCS |  | 20% DF CY 2017 (STIMULUS) | Electrification |  |  | Contract | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | Planned: |  | Planned: |  | Planned: | 100% | Planned: | 100% | No. of Persons: |  | Fund already transferred at Municipality of Talaingod with ChecK No. 2445181 and OR # 7955667, dated March 16, 2018 . Amended from Electrification @ Prk. 1A-Prk. 5A) | On-going (Implemented by MLGU, since transfer of fund ) | On-going (Implemented by MLGU, since transfer of fund ) | Completed | Completed | Completed as per Program of Works
IGCS | Anonang | 2nd Eng'g. Dist. | Completed |  |  |  | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various of Rural Electrification | [7 empty] | Project Engineer: | Lu | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
IGCS | Anonang | 2nd Eng'g. Dist. | Completed |  |  |  | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various of Rural Electrification | [7 empty] | Implementor: | 3E Electrical Sales & Services | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: | 100% | Actual: | 100%
IGCS | Anonang | 2nd Eng'g. Dist. | Completed |  |  |  | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various of Rural Electrification | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
IGCS | Anonang | 2nd Eng'g. Dist. | Completed |  |  |  | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various of Rural Electrification | [7 empty] | Date Allotment Released: |  | Date completed:
IGCS | Anonang | 2nd Eng'g. Dist. | Completed |  |  |  | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various of Rural Electrification | [7 empty] | Date Started:
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2018-07-17 |  | 2017 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./REHAB./COMP. OF VARIOUS GOV'T. BLDGS. STRUCT., FAC (Provincewide) LS - P9,000,000.00 | Upgrading of DDNSTC (Basketball/Voleyball MP Covered Court),Sports Center, Mankilam, Tagum City |  | SB # 4 CY 2017 | Covered Court | 2252.69 | sq.m | Contract | Project Cost: | 99992356.64 | Target Completion Date: | 2019-07-11 | Program: | 99992356.64 | Planned: | 100% | Planned: | 100% | Planned: | 100% | Planned: | 100% | Planned: | 100% | No. of Persons: | 10 | On-going (Suspended last April 5, 2020 due to COVID; Resumption Order dated May 4, 2020) | On-going | On-going | On-going | On-going | Suspended as of April 7, 2019
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2018-07-17 |  | 2017 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./REHAB./COMP. OF VARIOUS GOV'T. BLDGS. STRUCT., FAC (Provincewide) LS - P9,000,000.00 | [7 empty] | Project Engineer: | Daral | Revised Completion Date: |  | Allotment: | 99992356.64 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 310
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2018-07-17 |  | 2017 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./REHAB./COMP. OF VARIOUS GOV'T. BLDGS. STRUCT., FAC (Provincewide) LS - P9,000,000.00 | [7 empty] | Implementor: | YBC | No. of days suspended: |  | Disbursement: | 18280402.33 | Actual: | 73.04% | Actual: | 80.54% | Actual: | 80.54% | Actual: | 80.54% | Actual: | 90%
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2018-07-17 |  | 2017 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./REHAB./COMP. OF VARIOUS GOV'T. BLDGS. STRUCT., FAC (Provincewide) LS - P9,000,000.00 | [7 empty] | Duration: | 360 | No. of days extended: | 20 |  |  | Slippage: | -26.96% | Slippage: | -19.46% | Slippage: | -19.46% | Slippage: | -19.46% | Slippage: | -10%
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2018-07-17 |  | 2017 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./REHAB./COMP. OF VARIOUS GOV'T. BLDGS. STRUCT., FAC (Provincewide) LS - P9,000,000.00 | [7 empty] | Date Allotment Released: | 2018-10-16 | Date completed:
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2018-07-17 |  | 2017 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./REHAB./COMP. OF VARIOUS GOV'T. BLDGS. STRUCT., FAC (Provincewide) LS - P9,000,000.00 | [7 empty] | Date Started: | 2018-07-17
San Isidro | Sagayen | 1st Eng'g. Dist. | Completed | 2018-10-01 | 2020-04-02 | 2017 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CMGP | Road upgrading Km. 9 Sagayen-Sawata (Sagayen-Jct. San Miguel Section) |  | CMGP CY 2017 | Road Concreting | 10.2 | km | Contract | Project Cost: | 139761975.14 | Target Completion Date: | 2019-08-22 23:46 | Program: | 139761975.14 | Planned: | 100% | Planned: | 100% | Planned: | 100% | Planned: | 100% | Planned: | 100% | No. of Persons: | 28 | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per Program of Works
San Isidro | Sagayen | 1st Eng'g. Dist. | Completed | 2018-10-01 | 2020-04-02 | 2017 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CMGP | [7 empty] | Project Engineer: | Avila | Revised Completion Date: | 2019-08-22 23:46 | Allotment: | 139761975.14 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 11170
San Isidro | Sagayen | 1st Eng'g. Dist. | Completed | 2018-10-01 | 2020-04-02 | 2017 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CMGP | [7 empty] | Implementor: | Legacy Const. Corp. | No. of days suspended: | 209 | Disbursement: | 63100753.7 | Actual: | 100% | Actual: | 100% | Actual: | 100% | Actual: | 100% | Actual: | 100%
San Isidro | Sagayen | 1st Eng'g. Dist. | Completed | 2018-10-01 | 2020-04-02 | 2017 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CMGP | [7 empty] | Duration: | 326 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
San Isidro | Sagayen | 1st Eng'g. Dist. | Completed | 2018-10-01 | 2020-04-02 | 2017 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CMGP | [7 empty] | Date Allotment Released: | CY 2017 | Date completed: | 2020-04-03
San Isidro | Sagayen | 1st Eng'g. Dist. | Completed | 2018-10-01 | 2020-04-02 | 2017 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CMGP | [7 empty] | Date Started: | 2018-10-01
Sto. Tomas |  | 2nd Eng'g. Dist. | Completed | 2020-05-22 | 2020-06-30 | 2017 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPPAP-PAMANA | Construction of Tribal Hall, Sto. Tomas |  | OPPAP-PAMANA CY 2017 | Building |  | sq.m | Admin | Project Cost: | 500000 | Target Completion Date: | 2020-06-30 23:59 | Program: | 500000 | Planned: | 82.55% | Planned: | 100% | Planned: | 82.55% | Planned: |  | Planned: | 100% | No. of Persons: |  | On-going (Suspended last April 5, 2020 due to COVID; resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID; resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID; resumption order dated May 4, 2020) |  |  | Completed as per Program of Works
Sto. Tomas |  | 2nd Eng'g. Dist. | Completed | 2020-05-22 | 2020-06-30 | 2017 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPPAP-PAMANA | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
Sto. Tomas |  | 2nd Eng'g. Dist. | Completed | 2020-05-22 | 2020-06-30 | 2017 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPPAP-PAMANA | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: | 77.72% | Actual: | 93.61% | Actual: | 77.72% | Actual: |  | Actual:
Sto. Tomas |  | 2nd Eng'g. Dist. | Completed | 2020-05-22 | 2020-06-30 | 2017 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPPAP-PAMANA | [7 empty] | Duration: | 40 | No. of days extended: |  |  |  | Slippage: | -4.83% | Slippage: | -6.39% | Slippage: | -4.83% | Slippage: | 0% | Slippage: | -100%
Sto. Tomas |  | 2nd Eng'g. Dist. | Completed | 2020-05-22 | 2020-06-30 | 2017 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPPAP-PAMANA | [7 empty] | Date Allotment Released: |  | Date completed: | 2020-06-30
Sto. Tomas |  | 2nd Eng'g. Dist. | Completed | 2020-05-22 | 2020-06-30 | 2017 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPPAP-PAMANA | [7 empty] | Date Started: | 2020-05-22
Panabo City | Datu Abdul | 2nd Eng'g. Dist. | On-going | 2019-11-21 |  | 2017 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPPAP-PAMANA | Const. of Trading Post, Storage Building with (1) unit Hauling Truck, Prk. Ramihan Datu Abdul, Panabo City |  | OPPAP-PAMANA CY 2017 | Building |  | sq.m | Contract | Project Cost: | 3975000 | Target Completion Date: | 2020-04-05 23:59 | Program: | 3975000 | Planned: | 100% | Planned: | 100% | Planned: | 100% | Planned: | 100% | Planned: | 100% | No. of Persons: | 10 | On-going | On-going | On-going | On-going | On-going/ Subject for Liquidated damages | Suspended
Panabo City | Datu Abdul | 2nd Eng'g. Dist. | On-going | 2019-11-21 |  | 2017 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPPAP-PAMANA | [7 empty] | Project Engineer: | Azotes | Revised Completion Date: | August 24, 2020 | Allotment: | 3975000 | Revised: | 41.6% | Revised: | 100% | Revised: | 100% | Revised: | 100% | Revised: | 100% | No. of Man-days: | 260
Panabo City | Datu Abdul | 2nd Eng'g. Dist. | On-going | 2019-11-21 |  | 2017 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPPAP-PAMANA | [7 empty] | Implementor: | Ultra Core | No. of days suspended: | 71 | Disbursement: |  | Actual: | 41.6% | Actual: | 56.88% | Actual: | 56.88% | Actual: | 56.88% | Actual: | 43.12%
Panabo City | Datu Abdul | 2nd Eng'g. Dist. | On-going | 2019-11-21 |  | 2017 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPPAP-PAMANA | [7 empty] | Duration: | 137 | No. of days extended: | 100 |  |  | Slippage: | 0% | Slippage: | -43.12% | Slippage: | -43.12% | Slippage: | -43.12% | Slippage: | -56.88%
Panabo City | Datu Abdul | 2nd Eng'g. Dist. | On-going | 2019-11-21 |  | 2017 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPPAP-PAMANA | [7 empty] | Date Allotment Released: | CY 2017 | Date completed:
Panabo City | Datu Abdul | 2nd Eng'g. Dist. | On-going | 2019-11-21 |  | 2017 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPPAP-PAMANA | [7 empty] | Date Started: | 2019-11-21
Samal | Kinawitnon | 2nd Eng'g. Dist. | On-going | 2020-09-03 |  | 2017 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPPAP-PAMANA | Trading Post, Storage and Hauling Truck Libuak, Island Garden City of Samal (IGACOS) |  | OPPAP-PAMANA CY 2017 | Building |  |  |  | Project Cost: | 4000000 | Target Completion Date: | 2021-01-31 | Program: | 4000000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: | 27.42% | No. of Persons: | 8 | For awarding ALPEBEL | For awarding ALPEBEL | For awarding ALPEBEL | For awarding ALPEBEL | Mobilization on-going | On-going
Samal | Kinawitnon | 2nd Eng'g. Dist. | On-going | 2020-09-03 |  | 2017 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPPAP-PAMANA | [7 empty] | Project Engineer: | Andoy/Porras | Revised Completion Date: |  | Allotment: | 4000000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 176
Samal | Kinawitnon | 2nd Eng'g. Dist. | On-going | 2020-09-03 |  | 2017 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPPAP-PAMANA | [7 empty] | Implementor: | Alpebel Builders | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual: | 27.42%
Samal | Kinawitnon | 2nd Eng'g. Dist. | On-going | 2020-09-03 |  | 2017 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPPAP-PAMANA | [7 empty] | Duration: | 150 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Samal | Kinawitnon | 2nd Eng'g. Dist. | On-going | 2020-09-03 |  | 2017 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPPAP-PAMANA | [7 empty] | Date Allotment Released: | CY 2018 | Date completed:
Samal | Kinawitnon | 2nd Eng'g. Dist. | On-going | 2020-09-03 |  | 2017 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPPAP-PAMANA | [7 empty] | Date Started: | 2020-09-03
IGCS | Tambo | 2nd Eng'g. Dist. | PR on process (Waiting for the 2nd tranche) |  |  | 2017 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPPAP-PAMANA | Agricultural Productivity Support Project-Fishing Net with Pump Boat, Tambo,IGACOS |  | OPPAP-PAMANA CY 2017 |  |  |  |  | Project Cost: | 1500000 | Target Completion Date: |  | Program: | 1500000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | For PR | For PR | For PR | For PR | For PR | PR on process (Waiting for the 2nd tranche)
IGCS | Tambo | 2nd Eng'g. Dist. | PR on process (Waiting for the 2nd tranche) |  |  | 2017 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPPAP-PAMANA | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 1500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
IGCS | Tambo | 2nd Eng'g. Dist. | PR on process (Waiting for the 2nd tranche) |  |  | 2017 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPPAP-PAMANA | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
IGCS | Tambo | 2nd Eng'g. Dist. | PR on process (Waiting for the 2nd tranche) |  |  | 2017 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPPAP-PAMANA | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
IGCS | Tambo | 2nd Eng'g. Dist. | PR on process (Waiting for the 2nd tranche) |  |  | 2017 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPPAP-PAMANA | [7 empty] | Date Allotment Released: |  | Date completed:
IGCS | Tambo | 2nd Eng'g. Dist. | PR on process (Waiting for the 2nd tranche) |  |  | 2017 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPPAP-PAMANA | [7 empty] | Date Started:
IGCS | Tambo | 2nd Eng'g. Dist. | PR on process (Waiting for the 2nd tranche) |  |  | 2017 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPPAP-PAMANA | Agricultural Productivity Support Project-Fishing Net with Pump Boat, Limao, Peñaplata District, IGACOS |  | OPPAP-PAMANA CY 2017 |  |  |  |  | Project Cost: | 1500000 | Target Completion Date: |  | Program: | 1500000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | For PR | For PR | For PR | For PR | For PR | PR on process (Waiting for the 2nd tranche)
IGCS | Tambo | 2nd Eng'g. Dist. | PR on process (Waiting for the 2nd tranche) |  |  | 2017 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPPAP-PAMANA | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 1500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
IGCS | Tambo | 2nd Eng'g. Dist. | PR on process (Waiting for the 2nd tranche) |  |  | 2017 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPPAP-PAMANA | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
IGCS | Tambo | 2nd Eng'g. Dist. | PR on process (Waiting for the 2nd tranche) |  |  | 2017 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPPAP-PAMANA | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
IGCS | Tambo | 2nd Eng'g. Dist. | PR on process (Waiting for the 2nd tranche) |  |  | 2017 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPPAP-PAMANA | [7 empty] | Date Allotment Released: |  | Date completed:
IGCS | Tambo | 2nd Eng'g. Dist. | PR on process (Waiting for the 2nd tranche) |  |  | 2017 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPPAP-PAMANA | [7 empty] | Date Started:
IGCS | Tambo | 2nd Eng'g. Dist. | PR on process (Waiting for the 2nd tranche) |  |  | 2017 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPPAP-PAMANA | Agricultural Productivity Support Project-Fishing Net with Pump Boat, Kinawitnon, Babak District, IGCAOS |  | OPPAP-PAMANA CY 2017 |  |  |  |  | Project Cost: | 1500000 | Target Completion Date: |  | Program: | 1500000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | For PR | For PR | For PR | For PR | For PR | PR on process (Waiting for the 2nd tranche)
IGCS | Tambo | 2nd Eng'g. Dist. | PR on process (Waiting for the 2nd tranche) |  |  | 2017 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPPAP-PAMANA | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 1500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
IGCS | Tambo | 2nd Eng'g. Dist. | PR on process (Waiting for the 2nd tranche) |  |  | 2017 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPPAP-PAMANA | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
IGCS | Tambo | 2nd Eng'g. Dist. | PR on process (Waiting for the 2nd tranche) |  |  | 2017 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPPAP-PAMANA | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
IGCS | Tambo | 2nd Eng'g. Dist. | PR on process (Waiting for the 2nd tranche) |  |  | 2017 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPPAP-PAMANA | [7 empty] | Date Allotment Released: |  | Date completed:
IGCS | Tambo | 2nd Eng'g. Dist. | PR on process (Waiting for the 2nd tranche) |  |  | 2017 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPPAP-PAMANA | [7 empty] | Date Started:
Tagum City | Pandapan | 1st Eng'g. Dist. | Waiting for approval of Notice of Award |  |  | 2017 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPPAP-PAMANA | Const. of Trading Post, Storage Building with (1) unit Hauling Truck, Brgy. Pandapan |  | OPPAP-PAMANA CY 2017 | Building |  | sq.m |  | Project Cost: | 3975000 | Target Completion Date: | 0 | Program: | 3975000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Abstract 1220194004 (Tagum Builders);PO # 2019102828 - Truck | Abstract 1220194004 (Tagum Builders);PO # 2019102828 - Truck | Abstract 1220194004 (Tagum Builders);PO # 2019102828 - Truck | Waiting for approval of Notice of Award | Waiting for approval of Notice of Award | PR on process (Waiting for the 2nd tranche)
Tagum City | Pandapan | 1st Eng'g. Dist. | Waiting for approval of Notice of Award |  |  | 2017 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPPAP-PAMANA | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 3975000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
Tagum City | Pandapan | 1st Eng'g. Dist. | Waiting for approval of Notice of Award |  |  | 2017 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPPAP-PAMANA | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
Tagum City | Pandapan | 1st Eng'g. Dist. | Waiting for approval of Notice of Award |  |  | 2017 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPPAP-PAMANA | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Tagum City | Pandapan | 1st Eng'g. Dist. | Waiting for approval of Notice of Award |  |  | 2017 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPPAP-PAMANA | [7 empty] | Date Allotment Released: | CY 2017 | Date completed:
Tagum City | Pandapan | 1st Eng'g. Dist. | Waiting for approval of Notice of Award |  |  | 2017 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPPAP-PAMANA | [7 empty] | Date Started:
Talaingod | Palma Gil | 1st Eng'g. Dist. | Completed | 2019-11-12 | 2020-03-30 | 2017 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPPAP-PAMANA | Construction of PWS Level II in Sitio Upper Dulyan, Palma Gil, Talaingod |  | OPPAP-PAMANA CY 2017 | Building |  | sq.m | Admin | Project Cost: | 1000000 | Target Completion Date: | 2020-03-30 23:59 | Program: | 1000000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Abstract 1220194004 (Tagum Builders);PO # 2019102828 - Truck | Abstract 1220194004 (Tagum Builders);PO # 2019102828 - Truck | Abstract 1220194004 (Tagum Builders);PO # 2019102828 - Truck | Waiting for approval of Notice of Award | Waiting for approval of Notice of Award | Completed as per Program of Works
Talaingod | Palma Gil | 1st Eng'g. Dist. | Completed | 2019-11-12 | 2020-03-30 | 2017 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPPAP-PAMANA | [7 empty] | Project Engineer: | Kabingue | Revised Completion Date: | 2020-03-30 23:59 | Allotment: | 1000000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
Talaingod | Palma Gil | 1st Eng'g. Dist. | Completed | 2019-11-12 | 2020-03-30 | 2017 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPPAP-PAMANA | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
Talaingod | Palma Gil | 1st Eng'g. Dist. | Completed | 2019-11-12 | 2020-03-30 | 2017 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPPAP-PAMANA | [7 empty] | Duration: | 140 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Talaingod | Palma Gil | 1st Eng'g. Dist. | Completed | 2019-11-12 | 2020-03-30 | 2017 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPPAP-PAMANA | [7 empty] | Date Allotment Released: | CY 2017 | Date completed: | 2020-03-30
Talaingod | Palma Gil | 1st Eng'g. Dist. | Completed | 2019-11-12 | 2020-03-30 | 2017 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPPAP-PAMANA | [7 empty] | Date Started: | 2019-11-12
Kapalong | Gupitan | 1st Eng'g. Dist. | completed | 2019-08-16 | 2020-03-28 | 2017 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPPAP-PAMANA | Upgrading of Existing PWS Level II in Sitio Langan, Gupitan, Kapalong |  | OPPAP-PAMANA CY 2017 | Building |  | sq.m | Admin | Project Cost: | 2500000 | Target Completion Date: | 2020-03-28 23:59 | Program: | 2500000 | Planned: |  | Planned: |  | Planned: |  | Planned: | 100% | Planned: | 100% | No. of Persons: |  | Abstract 1220194004 (Tagum Builders);PO # 2019102828 - Truck | Abstract 1220194004 (Tagum Builders);PO # 2019102828 - Truck | Abstract 1220194004 (Tagum Builders);PO # 2019102828 - Truck | Completed as per physical accomplishment. | Completed as per physical accomplishment. | Completed as per Program of Works
Kapalong | Gupitan | 1st Eng'g. Dist. | completed | 2019-08-16 | 2020-03-28 | 2017 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPPAP-PAMANA | [7 empty] | Project Engineer: | Kabingue | Revised Completion Date: |  | Allotment: | 2500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
Kapalong | Gupitan | 1st Eng'g. Dist. | completed | 2019-08-16 | 2020-03-28 | 2017 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPPAP-PAMANA | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: | 2500000 | Actual: |  | Actual: |  | Actual: |  | Actual: | 100% | Actual: | 100%
Kapalong | Gupitan | 1st Eng'g. Dist. | completed | 2019-08-16 | 2020-03-28 | 2017 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPPAP-PAMANA | [7 empty] | Duration: | 226 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Kapalong | Gupitan | 1st Eng'g. Dist. | completed | 2019-08-16 | 2020-03-28 | 2017 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPPAP-PAMANA | [7 empty] | Date Allotment Released: |  | Date completed: | 2020-03-28
Kapalong | Gupitan | 1st Eng'g. Dist. | completed | 2019-08-16 | 2020-03-28 | 2017 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPPAP-PAMANA | [7 empty] | Date Started: | 2019-08-16
Talaingod | Dagohoy | 1st Eng'g. Dist. | completed | 2019-11-17 | 2020-07-30 | 2018 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPPAP-PAMANA | Const. of Processing and Bagsakan Center, Brgy. Dagohoy, Talaingod |  | OPPAP-PAMANA CY 2017 | Building |  | sq.m | Contract | Project Cost: | 2500000 | Target Completion Date: | 2020-04-09 23:59 | Program: | 2500000 | Planned: | 100% | Planned: | 100% | Planned: | 100% | Planned: | 100% | Planned: | 100% | No. of Persons: | 8 | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per Program of Works
Talaingod | Dagohoy | 1st Eng'g. Dist. | completed | 2019-11-17 | 2020-07-30 | 2018 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPPAP-PAMANA | [7 empty] | Project Engineer: | Dadula | Revised Completion Date: | 2020-07-30 23:59 | Allotment: | 2500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 200
Talaingod | Dagohoy | 1st Eng'g. Dist. | completed | 2019-11-17 | 2020-07-30 | 2018 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPPAP-PAMANA | [7 empty] | Implementor: | RLHV | No. of days suspended: |  | Disbursement: | 2500000 | Actual: | 100% | Actual: | 100% | Actual: | 100% | Actual: | 100% | Actual: | 100%
Talaingod | Dagohoy | 1st Eng'g. Dist. | completed | 2019-11-17 | 2020-07-30 | 2018 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPPAP-PAMANA | [7 empty] | Duration: | 145 | No. of days extended: | 112 |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Talaingod | Dagohoy | 1st Eng'g. Dist. | completed | 2019-11-17 | 2020-07-30 | 2018 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPPAP-PAMANA | [7 empty] | Date Allotment Released: | 2019-11-25 | Date completed: | 2020-07-30
Talaingod | Dagohoy | 1st Eng'g. Dist. | completed | 2019-11-17 | 2020-07-30 | 2018 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPPAP-PAMANA | [7 empty] | Date Started: | 2019-11-17
Kapalong | Gupitan | 1st Eng'g. Dist. | Completed | 2019-11-18 | 2020-06-15 | 2018 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPPAP-PAMANA | Post Harvest Facilities (Corn Mill, Solar Dryer, Corn Sheller), Sitio Dugayan, Brgy. Gupitan, Kapalong |  | OPPAP-PAMANA CY 2017 | Building |  | sq.m | Admin | Project Cost: | 1850000 | Target Completion Date: | 2020-02-27 | Program: | 1850000 | Planned: | 100% | Planned: | 100% | Planned: | 100% | Planned: | 100% | Planned: | 100% | No. of Persons: | 7 | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per Program of Works
Kapalong | Gupitan | 1st Eng'g. Dist. | Completed | 2019-11-18 | 2020-06-15 | 2018 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPPAP-PAMANA | [7 empty] | Project Engineer: | Ambrosio | Revised Completion Date: | 2020-06-15 | Allotment: | 1850000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 175
Kapalong | Gupitan | 1st Eng'g. Dist. | Completed | 2019-11-18 | 2020-06-15 | 2018 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPPAP-PAMANA | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 1114654.45 | Actual: | 100% | Actual: | 100% | Actual: | 100% | Actual: | 100% | Actual: | 100%
Kapalong | Gupitan | 1st Eng'g. Dist. | Completed | 2019-11-18 | 2020-06-15 | 2018 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPPAP-PAMANA | [7 empty] | Duration: | 101 | No. of days extended: | 82 |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Kapalong | Gupitan | 1st Eng'g. Dist. | Completed | 2019-11-18 | 2020-06-15 | 2018 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPPAP-PAMANA | [7 empty] | Date Allotment Released: | 2019-11-18 | Date completed: | 2020-06-15
Kapalong | Gupitan | 1st Eng'g. Dist. | Completed | 2019-11-18 | 2020-06-15 | 2018 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPPAP-PAMANA | [7 empty] | Date Started: | 2019-11-18
Kapalong | Gupitan | 1st Eng'g. Dist. | Completed | 2019-07-16 | 2020-03-31 | 2018 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPPAP-PAMANA | Post Harvest Facilities (Corn Mill, Solar Dryer, Corn Sheller), Sitio Butay, Palma Gil, Talaingod |  | OPPAP-PAMANA CY 2017 | Building |  | sq.m | Admin | Project Cost: | 1850000 | Target Completion Date: | 2020-03-31 23:59 | Program: | 1850000 | Planned: | 100% | Planned: | 100% | Planned: | 100% | Planned: | 100% | Planned: | 100% | No. of Persons: | 7 | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per Program of Works
Kapalong | Gupitan | 1st Eng'g. Dist. | Completed | 2019-07-16 | 2020-03-31 | 2018 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPPAP-PAMANA | [7 empty] | Project Engineer: | Ambrosio | Revised Completion Date: |  | Allotment: | 1850000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 175
Kapalong | Gupitan | 1st Eng'g. Dist. | Completed | 2019-07-16 | 2020-03-31 | 2018 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPPAP-PAMANA | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: | 1114654.45 | Actual: | 100% | Actual: | 100% | Actual: | 100% | Actual: | 100% | Actual: | 100%
Kapalong | Gupitan | 1st Eng'g. Dist. | Completed | 2019-07-16 | 2020-03-31 | 2018 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPPAP-PAMANA | [7 empty] | Duration: | 260 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Kapalong | Gupitan | 1st Eng'g. Dist. | Completed | 2019-07-16 | 2020-03-31 | 2018 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPPAP-PAMANA | [7 empty] | Date Allotment Released: | 2019-11-18 | Date completed: | 2020-03-31
Kapalong | Gupitan | 1st Eng'g. Dist. | Completed | 2019-07-16 | 2020-03-31 | 2018 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPPAP-PAMANA | [7 empty] | Date Started: | 2019-07-16
Kapalong | Capungagan | 1st Eng'g. Dist. | Suspended | 2019-11-25 |  | 2018 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPPAP-PAMANA | Construction of PWS Level II in Purok 7-A and 7-B, Capungagan, Kapalong |  | OPPAP-PAMANA CY 2017 | Potable Water System |  |  | Admin | Project Cost: | 1760000 | Target Completion Date: | 2020-02-03 | Program: | 1760000 | Planned: | 100% | Planned: | 100% | Planned: | 100% | Planned: | 100% | Planned: | 100% | No. of Persons: | 25 | Suspended due to elecrical permits | Suspended dsted July 30, 2020 due to elecrical permits | Suspended dsted July 30, 2020 due to elecrical permits | Suspended dsted July 30, 2020 due to elecrical permits | Suspended dsted July 30, 2020 due to elecrical permits | Suspended dsted July 30, 2020 due to elecrical permits
Kapalong | Capungagan | 1st Eng'g. Dist. | Suspended | 2019-11-25 |  | 2018 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPPAP-PAMANA | [7 empty] | Project Engineer: | Kabinge | Revised Completion Date: | 2020-04-15 | Allotment: | 1760000 | Revised: | 100% | Revised: | 95.08% | Revised: | 95.08% | Revised: | 95.08% | Revised: | 95.08% | No. of Man-days: | 375
Kapalong | Capungagan | 1st Eng'g. Dist. | Suspended | 2019-11-25 |  | 2018 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPPAP-PAMANA | [7 empty] | Implementor: | PEO | No. of days suspended: | 28 | Disbursement: | 1235344 | Actual: | 95.57% | Actual: | 98% | Actual: | 98% | Actual: | 98% | Actual: | 98%
Kapalong | Capungagan | 1st Eng'g. Dist. | Suspended | 2019-11-25 |  | 2018 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPPAP-PAMANA | [7 empty] | Duration: | 70 | No. of days extended: | 44 |  |  | Slippage: | -4.43% | Slippage: | 2.92% | Slippage: | 2.92% | Slippage: | 2.92% | Slippage: | 2.92%
Kapalong | Capungagan | 1st Eng'g. Dist. | Suspended | 2019-11-25 |  | 2018 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPPAP-PAMANA | [7 empty] | Date Allotment Released: | 2019-11-25 | Date completed:
Kapalong | Capungagan | 1st Eng'g. Dist. | Suspended | 2019-11-25 |  | 2018 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPPAP-PAMANA | [7 empty] | Date Started: | 2019-11-25
Kapalong | Pag-Asa | 1st Eng'g. Dist. | Suspended | 2019-12-16 |  | 2018 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPPAP-PAMANA | Construction of PWS Level II in Purok 2, Pag-Asa, kapalong |  | OPPAP-PAMANA CY 2017 | Potable Water System |  |  | Admin | Project Cost: | 2310000 | Target Completion Date: | 2020-04-09 | Program: | 2310000 | Planned: | 100% | Planned: | 100% | Planned: | 100% | Planned: | 100% | Planned: | 100% | No. of Persons: | 23 | On-going (Suspended last April 5, 2020 due to COVID; resumption order dated May 4, 2020) | Suspended dated August 26, 2020 due to elecrical permits and delivery of water tank | Suspended dated August 26, 2020 due to elecrical permits and delivery of water tank | Suspended dated August 26, 2020 due to elecrical permits and delivery of water tank | Suspended dated August 26, 2020 due to elecrical permits and delivery of water tank | Suspended dated August 26, 2020 due to elecrical permits and delivery of water tank
Kapalong | Pag-Asa | 1st Eng'g. Dist. | Suspended | 2019-12-16 |  | 2018 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPPAP-PAMANA | [7 empty] | Project Engineer: | Dadula | Revised Completion Date: | 2020-08-20 | Allotment: | 2310000 | Revised: | 100% | Revised: | 81.57% | Revised: | 81.57% | Revised: | 81.57% | Revised: | 100% | No. of Man-days: | 713
Kapalong | Pag-Asa | 1st Eng'g. Dist. | Suspended | 2019-12-16 |  | 2018 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPPAP-PAMANA | [7 empty] | Implementor: | PEO | No. of days suspended: | 28 | Disbursement: | 1678908 | Actual: | 72.68% | Actual: | 76.39% | Actual: | 76.39% | Actual: | 76.39% | Actual: | 100%
Kapalong | Pag-Asa | 1st Eng'g. Dist. | Suspended | 2019-12-16 |  | 2018 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPPAP-PAMANA | [7 empty] | Duration: | 115 | No. of days extended: | 105 |  |  | Slippage: | -27.32% | Slippage: | -5.179% | Slippage: | -5.179% | Slippage: | -5.179% | Slippage: | 0%
Kapalong | Pag-Asa | 1st Eng'g. Dist. | Suspended | 2019-12-16 |  | 2018 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPPAP-PAMANA | [7 empty] | Date Allotment Released: | 2019-11-25 | Date completed: | 2020-08-20
Kapalong | Pag-Asa | 1st Eng'g. Dist. | Suspended | 2019-12-16 |  | 2018 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPPAP-PAMANA | [7 empty] | Date Started: | 2019-12-16
Kapalong | Gupitan | 1st Eng'g. Dist. | completed | 2019-07-17 | 2020-08-15 | 2018 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPPAP-PAMANA | Rice Mill for Upland Rice,Gupitan , Kapalong |  | OPPAP-PAMANA CY 2017 | Rice Mill |  |  | Admin | Project Cost: | 1000000 | Target Completion Date: |  | Program: | 1000000 | Planned: | 42.65% | Planned: | 42.65% | Planned: | 42.65% | Planned: |  | Planned: | 100% | No. of Persons: |  | On-going | On-going | On-going |  |  | Completed as per Program of Works
Kapalong | Gupitan | 1st Eng'g. Dist. | completed | 2019-07-17 | 2020-08-15 | 2018 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPPAP-PAMANA | [7 empty] | Project Engineer: | Ambrosio | Revised Completion Date: | 0 | Allotment: | 1000000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
Kapalong | Gupitan | 1st Eng'g. Dist. | completed | 2019-07-17 | 2020-08-15 | 2018 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPPAP-PAMANA | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: | 42.65% | Actual: | 42.65% | Actual: | 42.65% | Actual: |  | Actual: | 100%
Kapalong | Gupitan | 1st Eng'g. Dist. | completed | 2019-07-17 | 2020-08-15 | 2018 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPPAP-PAMANA | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Kapalong | Gupitan | 1st Eng'g. Dist. | completed | 2019-07-17 | 2020-08-15 | 2018 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPPAP-PAMANA | [7 empty] | Date Allotment Released: |  | Date completed: | 2019-08-15
Kapalong | Gupitan | 1st Eng'g. Dist. | completed | 2019-07-17 | 2020-08-15 | 2018 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPPAP-PAMANA | [7 empty] | Date Started: | 2019-07-17
Talaingod | Palma Gil | 1st Eng'g. Dist. | On-going | 2020-06-01 |  | 2018 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPPAP-PAMANA | Rice Mill for Upland Rice, Palma Gil, Talaingod |  | OPPAP-PAMANA CY 2017 | Rice Mill |  |  | Admin | Project Cost: | 1000000 | Target Completion Date: | 2020-07-30 23:46 | Program: | 1000000 | Planned: | 42.65% | Planned: | 42.65% | Planned: | 42.65% | Planned: | 42.65% | Planned: | 42.65% | No. of Persons: | 6 | On-going | On-going | On-going | On-going | On-going | Suspended last July 25, 2020. Still waiting for the delivery of Rice Mill as part of the Program.
Talaingod | Palma Gil | 1st Eng'g. Dist. | On-going | 2020-06-01 |  | 2018 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPPAP-PAMANA | [7 empty] | Project Engineer: | Torrecampo | Revised Completion Date: | 2020-07-30 23:46 | Allotment: | 1000000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 90
Talaingod | Palma Gil | 1st Eng'g. Dist. | On-going | 2020-06-01 |  | 2018 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPPAP-PAMANA | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: | 426500 | Actual: | 42.65% | Actual: | 42.65% | Actual: | 42.65% | Actual: | 42.65% | Actual: | 42.65%
Talaingod | Palma Gil | 1st Eng'g. Dist. | On-going | 2020-06-01 |  | 2018 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPPAP-PAMANA | [7 empty] | Duration: | 60 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Talaingod | Palma Gil | 1st Eng'g. Dist. | On-going | 2020-06-01 |  | 2018 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPPAP-PAMANA | [7 empty] | Date Allotment Released: |  | Date completed:
Talaingod | Palma Gil | 1st Eng'g. Dist. | On-going | 2020-06-01 |  | 2018 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPPAP-PAMANA | [7 empty] | Date Started: | 2020-06-01
Kapalong | Semong | 1st Eng'g. Dist. | For re-PR |  |  | 2018 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPPAP-PAMANA | Cattle Production- Brgy. Tiburcia, Gupitan and Semong, Kapalong |  | OPPAP-PAMANA CY 2017 | Building |  | sq.m |  | Project Cost: | 1500000 | Target Completion Date: |  | Program: | 1500000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | For RE-PR | For RE-PR | For RE-PR |  |  | Procurement on process. Waiting for the 2nd tranch.
Kapalong | Semong | 1st Eng'g. Dist. | For re-PR |  |  | 2018 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPPAP-PAMANA | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 1500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
Kapalong | Semong | 1st Eng'g. Dist. | For re-PR |  |  | 2018 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPPAP-PAMANA | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
Kapalong | Semong | 1st Eng'g. Dist. | For re-PR |  |  | 2018 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPPAP-PAMANA | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Kapalong | Semong | 1st Eng'g. Dist. | For re-PR |  |  | 2018 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPPAP-PAMANA | [7 empty] | Date Allotment Released: |  | Date completed:
Kapalong | Semong | 1st Eng'g. Dist. | For re-PR |  |  | 2018 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPPAP-PAMANA | [7 empty] | Date Started:
Talaingod | Dagohoy | 1st Eng'g. Dist. | For re-PR |  |  | 2018 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPPAP-PAMANA | Cattle Production, Brgy. Palma Gil, Brgy. Sto. Nino, Brgy. Dagohoy, Talaingod, Davao del Norte |  | OPPAP-PAMANA CY 2017 | Building |  | sq.m |  | Project Cost: | 1500000 | Target Completion Date: |  | Program: | 1500000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | For RE-PR | For RE-PR | For RE-PR |  |  | Procurement on process. Waiting for the 2nd tranch.
Talaingod | Dagohoy | 1st Eng'g. Dist. | For re-PR |  |  | 2018 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPPAP-PAMANA | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 1500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
Talaingod | Dagohoy | 1st Eng'g. Dist. | For re-PR |  |  | 2018 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPPAP-PAMANA | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
Talaingod | Dagohoy | 1st Eng'g. Dist. | For re-PR |  |  | 2018 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPPAP-PAMANA | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Talaingod | Dagohoy | 1st Eng'g. Dist. | For re-PR |  |  | 2018 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPPAP-PAMANA | [7 empty] | Date Allotment Released: |  | Date completed:
Talaingod | Dagohoy | 1st Eng'g. Dist. | For re-PR |  |  | 2018 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPPAP-PAMANA | [7 empty] | Date Started:
Sto. Tomas | Tibal-og | 2nd Eng'g. Dist. | Re-aligned to COVID |  |  | 2020 |  | . | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | Construction of Municipal Triball Hall, Sto. Tomas |  | GENERAL FUND CY 2020 | Building |  | sq.m | Admin | Project Cost: | 500000 | Target Completion Date: | 2019-07-31 | Program: | 500000 | Planned: | 100% | Planned: | 100% | Planned: | 100% | Planned: | 100% | Planned: | 100% | No. of Persons: | 7 | Suspended June 28, 2019. Waiting for the delivery of JO Materials | Suspended June 28, 2019. Waiting for the delivery of JO Materials | Suspended June 28, 2019. Waiting for the delivery of JO Materials | Suspended June 28, 2019. Waiting for the delivery of JO Materials | Suspended June 28, 2019. Waiting for the delivery of JO Materials | Suspended June 28, 2019. Waiting for the delivery of JO Materials
Sto. Tomas | Tibal-og | 2nd Eng'g. Dist. | Re-aligned to COVID |  |  | 2020 |  | . | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Project Engineer: | Roque | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 110
Sto. Tomas | Tibal-og | 2nd Eng'g. Dist. | Re-aligned to COVID |  |  | 2020 |  | . | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: | 85% | Actual: | 85% | Actual: | 85% | Actual: | 85% | Actual: | 85%
Sto. Tomas | Tibal-og | 2nd Eng'g. Dist. | Re-aligned to COVID |  |  | 2020 |  | . | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Duration: | 70 | No. of days extended: |  |  |  | Slippage: | -15% | Slippage: | -15% | Slippage: | -15% | Slippage: | -15% | Slippage: | -15%
Sto. Tomas | Tibal-og | 2nd Eng'g. Dist. | Re-aligned to COVID |  |  | 2020 |  | . | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Date Allotment Released: | CY 2018 | Date completed:
Sto. Tomas | Tibal-og | 2nd Eng'g. Dist. | Re-aligned to COVID |  |  | 2020 |  | . | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Date Started: | 2019-05-22
San Isidro | Mamalian | 1st Eng'g. Dist. | Re-aligned to COVID |  |  | 2018 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | WATER SYSTEM LS - P 10,000,000.00 | Const. of PWS Mamalian, San Isidro |  | 20% DF CY 2018 | geo-resistivty/drillig |  |  | Admin | Project Cost: | 62000 | Target Completion Date: |  | Program: | 62000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | For declaration of savings because the spring water source is not feasible for development. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
San Isidro | Mamalian | 1st Eng'g. Dist. | Re-aligned to COVID |  |  | 2018 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | WATER SYSTEM LS - P 10,000,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 62000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
San Isidro | Mamalian | 1st Eng'g. Dist. | Re-aligned to COVID |  |  | 2018 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | WATER SYSTEM LS - P 10,000,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
San Isidro | Mamalian | 1st Eng'g. Dist. | Re-aligned to COVID |  |  | 2018 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | WATER SYSTEM LS - P 10,000,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
San Isidro | Mamalian | 1st Eng'g. Dist. | Re-aligned to COVID |  |  | 2018 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | WATER SYSTEM LS - P 10,000,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
San Isidro | Mamalian | 1st Eng'g. Dist. | Re-aligned to COVID |  |  | 2018 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | WATER SYSTEM LS - P 10,000,000.00 | [7 empty] | Date Started:
San Isidro | Sagayen | 1st Eng'g. Dist. | Re-aligned to COVID |  |  | 2018 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | WATER SYSTEM LS - P 10,000,000.00 | Const. of PWS Sagayen, San Isidro |  | 20% DF CY 2018 | geo-resistivty/drillig |  |  | Admin | Project Cost: | 62000 | Target Completion Date: |  | Program: | 62000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
San Isidro | Sagayen | 1st Eng'g. Dist. | Re-aligned to COVID |  |  | 2018 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | WATER SYSTEM LS - P 10,000,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 62000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
San Isidro | Sagayen | 1st Eng'g. Dist. | Re-aligned to COVID |  | 0 | 2018 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | WATER SYSTEM LS - P 10,000,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
San Isidro | Sagayen | 1st Eng'g. Dist. | Re-aligned to COVID |  |  | 2018 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | WATER SYSTEM LS - P 10,000,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
San Isidro | Sagayen | 1st Eng'g. Dist. | Re-aligned to COVID |  |  | 2018 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | WATER SYSTEM LS - P 10,000,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
San Isidro | Sagayen | 1st Eng'g. Dist. | Re-aligned to COVID |  |  | 2018 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | WATER SYSTEM LS - P 10,000,000.00 | [7 empty] | Date Started:
Tagum City | Pandapan | 1st Eng'g. Dist. | Plan preparation |  |  | 2018 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | WATER SYSTEM LS - P 10,000,000.00 | Installation of potable water System at Purok Nangka, Pandapan, Tagum City |  | 20% DF CY 2018 | Water System |  |  | Admin | Project Cost: | 1125000 | Target Completion Date: |  | Program: | 1125000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Waiting for deed of donation. Follow-up letter was already issued | Waiting for deed of donation. Follow-up letter was already issued | Plan preparation on-going | Plan preparation on-going | Plan preparation on-going | Plan preparation on-going
Tagum City | Pandapan | 1st Eng'g. Dist. | Plan preparation |  |  | 2018 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | WATER SYSTEM LS - P 10,000,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 1125000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
Tagum City | Pandapan | 1st Eng'g. Dist. | Plan preparation |  |  | 2018 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | WATER SYSTEM LS - P 10,000,000.00 | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
Tagum City | Pandapan | 1st Eng'g. Dist. | Plan preparation |  |  | 2018 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | WATER SYSTEM LS - P 10,000,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Tagum City | Pandapan | 1st Eng'g. Dist. | Plan preparation |  |  | 2018 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | WATER SYSTEM LS - P 10,000,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Tagum City | Pandapan | 1st Eng'g. Dist. | Plan preparation |  |  | 2018 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | WATER SYSTEM LS - P 10,000,000.00 | [7 empty] | Date Started:
Asuncion | San Vicente | 1st Eng'g. Dist. | Procurement on process |  |  | 2018 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | WATER SYSTEM LS - P 10,000,000.00 | Rehab./Impv't. of San Vicente Water System, Asuncion |  | 20% DF CY 2018 | Water System |  |  | Admin | Project Cost: | 1125000 | Target Completion Date: |  | Program: | 1125000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Waiting for deed of donation. Follow-up letter was already issued | Waiting for deed of donation. Follow-up letter was already issued | Plan preparation on-going | Plan preparation on-going | Plan preparation on-going | Procurement on process.
Asuncion | San Vicente | 1st Eng'g. Dist. | Procurement on process |  |  | 2018 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | WATER SYSTEM LS - P 10,000,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 1125000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
Asuncion | San Vicente | 1st Eng'g. Dist. | Procurement on process |  |  | 2018 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | WATER SYSTEM LS - P 10,000,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
Asuncion | San Vicente | 1st Eng'g. Dist. | Procurement on process |  |  | 2018 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | WATER SYSTEM LS - P 10,000,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Asuncion | San Vicente | 1st Eng'g. Dist. | Procurement on process |  |  | 2018 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | WATER SYSTEM LS - P 10,000,000.00 | [7 empty] | Date Allotment Released: | 2018-10-26 | Date completed:
Asuncion | San Vicente | 1st Eng'g. Dist. | Procurement on process |  |  | 2018 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | WATER SYSTEM LS - P 10,000,000.00 | [7 empty] | Date Started:
IGCS | Kaputian | 2nd Eng'g. Dist. | Procurement on process |  |  | 2018 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | WATER SYSTEM LS - P 10,000,000.00 | Impv't. of Water System, Brgy. Poblacion, Kaputian (Level II) |  | 20% DF CY 2018 | Water System |  |  | Admin | Project Cost: | 1250000 | Target Completion Date: |  | Program: | 1250000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Waiting for deed of donation. Follow-up letter was already issued | Waiting for deed of donation. Follow-up letter was already issued | Plan preparation on-going |  |  | Procurement on process.
IGCS | Kaputian | 2nd Eng'g. Dist. | Procurement on process |  |  | 2018 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | WATER SYSTEM LS - P 10,000,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 1250000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
IGCS | Kaputian | 2nd Eng'g. Dist. | Procurement on process |  |  | 2018 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | WATER SYSTEM LS - P 10,000,000.00 | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
IGCS | Kaputian | 2nd Eng'g. Dist. | Procurement on process |  |  | 2018 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | WATER SYSTEM LS - P 10,000,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
IGCS | Kaputian | 2nd Eng'g. Dist. | Procurement on process |  |  | 2018 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | WATER SYSTEM LS - P 10,000,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
IGCS | Kaputian | 2nd Eng'g. Dist. | Procurement on process |  |  | 2018 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | WATER SYSTEM LS - P 10,000,000.00 | [7 empty] | Date Started:
Panabo City | Malativas | 2nd Eng'g. Dist. | For Implementation |  |  | 2018 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Construction of Water System Projects in Component LGUs LS - 9,750,000.00 | Water System at brgy. Malativas, Panabo City |  | 20% DF CY 2018 | Water System |  |  | Admin | Project Cost: | 1250000 | Target Completion Date: |  | Program: | 1250000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | For preparation of POW & Plan c/o PDPM - POSSIBLE TRANSFER OF SITE SUBJECT FOR TRANSFER OF LOCATION . NO DEED OF DONATION | For preparation of POW & Plan c/o PDPM - POSSIBLE TRANSFER OF SITE SUBJECT FOR TRANSFER OF LOCATION . NO DEED OF DONATION | For preparation of POW & Plan c/o PDPM - POSSIBLE TRANSFER OF SITE SUBJECT FOR TRANSFER OF LOCATION . NO DEED OF DONATION | For preparation of POW & Plan c/o PDPM - POSSIBLE TRANSFER OF SITE SUBJECT FOR TRANSFER OF LOCATION . NO DEED OF DONATION | For preparation of POW & Plan c/o PDPM - POSSIBLE TRANSFER OF SITE SUBJECT FOR TRANSFER OF LOCATION . NO DEED OF DONATION | For preparation of POW & Plan c/o PDPM - POSSIBLE TRANSFER OF SITE SUBJECT FOR TRANSFER OF LOCATION . NO DEED OF DONATION
Panabo City | Malativas | 2nd Eng'g. Dist. | For Implementation |  |  | 2018 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Construction of Water System Projects in Component LGUs LS - 9,750,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 1250000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
Panabo City | Malativas | 2nd Eng'g. Dist. | For Implementation |  |  | 2018 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Construction of Water System Projects in Component LGUs LS - 9,750,000.00 | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
Panabo City | Malativas | 2nd Eng'g. Dist. | For Implementation |  |  | 2018 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Construction of Water System Projects in Component LGUs LS - 9,750,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Panabo City | Malativas | 2nd Eng'g. Dist. | For Implementation |  |  | 2018 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Construction of Water System Projects in Component LGUs LS - 9,750,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Panabo City | Malativas | 2nd Eng'g. Dist. | For Implementation |  |  | 2018 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Construction of Water System Projects in Component LGUs LS - 9,750,000.00 | [7 empty] | Date Started:
Panabo City | Tibungol | 2nd Eng'g. Dist. | On-going | 2020-01-20 |  | 2018 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Construction of Water System Projects in Component LGUs LS - 9,750,000.00 | Const. of Potable Water System at Brgy. Tibungol, Panabo City |  | 20% DF CY 2018 | Water System |  | ln.m | Admin | Project Cost: | 1250000 | Target Completion Date: | 2020-04-15 23:59 | Program: | 1250000 | Planned: | 2.13% | Planned: | 2.13% | Planned: | 2.13% | Planned: | 2.13% | Planned: | 2.13% | No. of Persons: | 3 | Suspended dated February 19, 2020 undelivered hardware materials (Supplier refused to deliver. Letter already submitted to BAC.) | Suspended dated February 19, 2020 undelivered hardware materials (materials re-bid) | Suspended dated February 19, 2020 undelivered hardware materials (materials re-bid) | Suspended dated February 19, 2020 undelivered hardware materials (materials re-bid) | Suspended dated February 19, 2020 undelivered hardware materials (materials re-bid) | Suspended dated February 19, 2020 undelivered hardware materials (Supplier refused to deliver. Letter already submitted to BAC.)
Panabo City | Tibungol | 2nd Eng'g. Dist. | On-going | 2020-01-20 |  | 2018 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Construction of Water System Projects in Component LGUs LS - 9,750,000.00 | [7 empty] | Project Engineer: | Andoy | Revised Completion Date: |  | Allotment: | 1250000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 15
Panabo City | Tibungol | 2nd Eng'g. Dist. | On-going | 2020-01-20 |  | 2018 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Construction of Water System Projects in Component LGUs LS - 9,750,000.00 | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: | 0.76% | Actual: | 0.76% | Actual: | 0.76% | Actual: | 0.76% | Actual: | 0.76%
Panabo City | Tibungol | 2nd Eng'g. Dist. | On-going | 2020-01-20 |  | 2018 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Construction of Water System Projects in Component LGUs LS - 9,750,000.00 | [7 empty] | Duration: | 87 | No. of days extended: |  |  |  | Slippage: | -1.37% | Slippage: | -1.37% | Slippage: | -1.37% | Slippage: | -1.37% | Slippage: | -1.37%
Panabo City | Tibungol | 2nd Eng'g. Dist. | On-going | 2020-01-20 |  | 2018 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Construction of Water System Projects in Component LGUs LS - 9,750,000.00 | [7 empty] | Date Allotment Released: | 2018-11-21 | Date completed:
Panabo City | Tibungol | 2nd Eng'g. Dist. | On-going | 2020-01-20 |  | 2018 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Construction of Water System Projects in Component LGUs LS - 9,750,000.00 | [7 empty] | Date Started: | 2020-01-20
Samal, Kaputian | San Remegio | 2nd Eng'g. Dist. | Completed | 2019-07-16 | 2020-06-30 | 2018 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Construction of Water System Projects in Component LGUs LS - 9,750,000.00 | Potable Water System at Brgy. San Remegio Kaputian (Level II WS), Samal |  | 20% DF CY 2018 | Water System |  |  | Admin | Project Cost: | 3625000 | Target Completion Date: | 2020-02-01 | Program: | 3625000 | Planned: | 100% | Planned: | 100% | Planned: | 100% | Planned: | 100% | Planned: | 100% | No. of Persons: | 4 | On-going/ Resumption 5/4/2020 | On-going/ Resumption 5/4/2020 | On-going/ Resumption 5/4/2020 | On-going/ Resumption 5/4/2020 | On-going/ Resumption 5/4/2020 | Completed as per Program of Works
Samal, Kaputian | San Remegio | 2nd Eng'g. Dist. | Completed | 2019-07-16 | 2020-06-30 | 2018 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Construction of Water System Projects in Component LGUs LS - 9,750,000.00 | [7 empty] | Project Engineer: | Andoy | Revised Completion Date: | 2020-07-31 | Allotment: | 3625000 | Revised: | 72.04% | Revised: | 72.04% | Revised: | 98.86% | Revised: | 98.86% | Revised: | 100% | No. of Man-days: | 88
Samal, Kaputian | San Remegio | 2nd Eng'g. Dist. | Completed | 2019-07-16 | 2020-06-30 | 2018 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Construction of Water System Projects in Component LGUs LS - 9,750,000.00 | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: | 2702800 | Actual: | 74.56% | Actual: | 74.56% | Actual: | 98.86% | Actual: | 98.86% | Actual: | 100%
Samal, Kaputian | San Remegio | 2nd Eng'g. Dist. | Completed | 2019-07-16 | 2020-06-30 | 2018 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Construction of Water System Projects in Component LGUs LS - 9,750,000.00 | [7 empty] | Duration: | 200 | No. of days extended: | 181 |  |  | Slippage: | 2.52% | Slippage: | 2.52% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Samal, Kaputian | San Remegio | 2nd Eng'g. Dist. | Completed | 2019-07-16 | 2020-06-30 | 2018 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Construction of Water System Projects in Component LGUs LS - 9,750,000.00 | [7 empty] | Date Allotment Released: | 2018-10-25 | Date completed: | 2020-06-30
Samal, Kaputian | San Remegio | 2nd Eng'g. Dist. | Completed | 2019-07-16 | 2020-06-30 | 2018 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Construction of Water System Projects in Component LGUs LS - 9,750,000.00 | [7 empty] | Date Started: | 2019-07-16
Asuncion | Camansa | 1st Eng'g. Dist. | Re-aligned to COVID |  |  | 2018 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./REHAB./COMP. OF VARIOUS GOV'T. BLDGS. STRUCT., FAC (Provincewide) LS - LS - P13,523,124.00 | Construction of IP Tribal Council of Women at Brgy. Camansa, Asuncion |  | 20% DF CY 2018 | Building |  | sq.m | Admin | Project Cost: | 560000 | Target Completion Date: |  | Program: | 560000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Purchase Request # 20032714 | PR cancelled due to To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | PR cancelled due to To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | PR cancelled due to To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | PR cancelled due to To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | PR cancelled due to To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
Asuncion | Camansa | 1st Eng'g. Dist. | Re-aligned to COVID |  |  | 2018 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./REHAB./COMP. OF VARIOUS GOV'T. BLDGS. STRUCT., FAC (Provincewide) LS - P13,523,124.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 560000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
Asuncion | Camansa | 1st Eng'g. Dist. | Re-aligned to COVID |  |  | 2018 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./REHAB./COMP. OF VARIOUS GOV'T. BLDGS. STRUCT., FAC (Provincewide) LS - P13,523,124.00 | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
Asuncion | Camansa | 1st Eng'g. Dist. | Re-aligned to COVID |  |  | 2018 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./REHAB./COMP. OF VARIOUS GOV'T. BLDGS. STRUCT., FAC (Provincewide) LS - P13,523,124.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Asuncion | Camansa | 1st Eng'g. Dist. | Re-aligned to COVID |  |  | 2018 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./REHAB./COMP. OF VARIOUS GOV'T. BLDGS. STRUCT., FAC (Provincewide) LS - P13,523,124.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Asuncion | Camansa | 1st Eng'g. Dist. | Re-aligned to COVID |  |  | 2018 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./REHAB./COMP. OF VARIOUS GOV'T. BLDGS. STRUCT., FAC (Provincewide) LS - P13,523,124.00 | [7 empty] | Date Started:
New Corella | Del Monte | 1st Eng'g. Dist. | Completed | 2020-11-20 | 2020-12-03 | 2018 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | RURAL ELECTRIFICATION (Provincewide) LS - P5,000,000.00 | Rural Electrification at Del Monte, New Corella |  | 20% DF CY 2018 | Electrification |  |  | Contract | Project Cost: | 1000000 | Target Completion Date: |  | Program: | 1000000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: | 100% | No. of Persons: |  | Post Qualification on process | Post Qualification on process | For implementation (Awarded to 3E Electirical and Engineering) | For implementation (Awarded to 3E Electirical and Engineering) | For implementation (Awarded to 3E Electirical and Engineering) | Completed as per Program of Works
New Corella | Del Monte | 1st Eng'g. Dist. | Completed | 2020-11-20 | 2020-12-03 | 2018 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | RURAL ELECTRIFICATION (Provincewide) LS - P5,000,000.00 | [7 empty] | Project Engineer: | Bueno | Revised Completion Date: | 0 | Allotment: | 1000000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
New Corella | Del Monte | 1st Eng'g. Dist. | Completed | 2020-11-20 | 2020-12-03 | 2018 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | RURAL ELECTRIFICATION (Provincewide) LS - P5,000,000.00 | [7 empty] | Implementor: | 3E Electirical and Engineering | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual: | 100%
New Corella | Del Monte | 1st Eng'g. Dist. | Completed | 2020-11-20 | 2020-12-03 | 2018 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | RURAL ELECTRIFICATION (Provincewide) LS - P5,000,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
New Corella | Del Monte | 1st Eng'g. Dist. | Completed | 2020-11-20 | 2020-12-03 | 2018 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | RURAL ELECTRIFICATION (Provincewide) LS - P5,000,000.00 | [7 empty] | Date Allotment Released: |  | Date completed: | 2020-12-03
New Corella | Del Monte | 1st Eng'g. Dist. | Completed | 2020-11-20 | 2020-12-03 | 2018 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | RURAL ELECTRIFICATION (Provincewide) LS - P5,000,000.00 | [7 empty] | Date Started: | 2020-11-20
Asuncion | Camansa | 1st Eng'g. Dist. | On-going | 2020-08-06 |  | 2018 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | RURAL ELECTRIFICATION (Provincewide) LS - P5,000,000.00 | Const. of Distribution Line in Sitio Prk. 1,3,4, 11 and 7, Camansa, Asuncion |  | 20% DF CY 2018 | Electrification |  |  | Contract | Project Cost: | 4000000 | Target Completion Date: |  | Program: | 4000000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: | 78% | No. of Persons: |  | Awarded to 3E ELECTRICAL SALES & SERVICES | Awarded to 3E ELECTRICAL SALES & SERVICES | For impelementation (Awarded to 3E ELECTRICAL SALES & SERVICES) | For impelementation (Awarded to 3E ELECTRICAL SALES & SERVICES) | For impelementation (Awarded to 3E ELECTRICAL SALES & SERVICES) | On-going
Asuncion | Camansa | 1st Eng'g. Dist. | On-going | 2020-08-06 |  | 2018 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | RURAL ELECTRIFICATION (Provincewide) LS - P5,000,000.00 | [7 empty] | Project Engineer: | Bueno | Revised Completion Date: | 0 | Allotment: | 4000000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
Asuncion | Camansa | 1st Eng'g. Dist. | On-going | 2020-08-06 |  | 2018 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | RURAL ELECTRIFICATION (Provincewide) LS - P5,000,000.00 | [7 empty] | Implementor: | 3E Electirical and Engineering | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual: | 78%
Asuncion | Camansa | 1st Eng'g. Dist. | On-going | 2020-08-06 |  | 2018 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | RURAL ELECTRIFICATION (Provincewide) LS - P5,000,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Asuncion | Camansa | 1st Eng'g. Dist. | On-going | 2020-08-06 |  | 2018 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | RURAL ELECTRIFICATION (Provincewide) LS - P5,000,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Asuncion | Camansa | 1st Eng'g. Dist. | On-going | 2020-08-06 |  | 2018 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | RURAL ELECTRIFICATION (Provincewide) LS - P5,000,000.00 | [7 empty] | Date Started: | 2020-08-06
Carmen | San Isidro | 2nd Eng'g. Dist. | Completed | 2019-04-07 | 2020-09-01 | 2018 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | Completion of Evacuation Center Building, San Isidro, Carmen |  | 20% DF CY 2018(STIMULUS) | Building |  | sq.m | Contract | Project Cost: | 500000 | Target Completion Date: | 2019-06-06 | Program: | 500000 | Planned: |  | Planned: | 100% | Planned: | 100% | Planned: | 100% | Planned: | 100% | No. of Persons: | 6 | On-going | On-going/Subject for liquidated damages/Noactivity on site. | On-going/Subject for liquidated damages/Noactivity on site. | On-going/Subject for liquidated damages/Noactivity on site. | On-going/Subject for liquidated damages/Noactivity on site. | Completed as per Program of Works
Carmen | San Isidro | 2nd Eng'g. Dist. | Completed | 2019-04-07 | 2020-09-01 | 2018 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Project Engineer: | Abayon | Revised Completion Date: | 2019-09-01 | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 36
Carmen | San Isidro | 2nd Eng'g. Dist. | Completed | 2019-04-07 | 2020-09-01 | 2018 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Implementor: | RLHV | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: | 10.2% | Actual: | 10.2% | Actual: | 10.2% | Actual: | 100%
Carmen | San Isidro | 2nd Eng'g. Dist. | Completed | 2019-04-07 | 2020-09-01 | 2018 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Duration: | 60 | No. of days extended: | 87 |  |  | Slippage: | 0% | Slippage: | -89.8% | Slippage: | -89.8% | Slippage: | -89.8% | Slippage: | 0%
Carmen | San Isidro | 2nd Eng'g. Dist. | Completed | 2019-04-07 | 2020-09-01 | 2018 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Date Allotment Released: |  | Date completed: | 2020-09-01
Carmen | San Isidro | 2nd Eng'g. Dist. | Completed | 2019-04-07 | 2020-09-01 | 2018 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Date Started: | 2019-04-07
Panabo City | San Pedro | 2nd Eng'g. Dist. | Plan and POW Preparation Ongoing |  |  | 2018 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | Const. of New Brgy. Stage, San Pedro, Panabo City |  | 20% DF CY 2018 (STIMULUS) | Building |  | sq.m | Contract | Project Cost: | 500000 | Target Completion Date: | 0 | Program: | 500000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Plan and POW Preparation for preparation | Plan and POW Preparation for preparation | Plan and POW Preparation Ongoing | Plan and POW Preparation Ongoing | Plan and POW Preparation Ongoing | Plan and POW Preparation Ongoing
Panabo City | San Pedro | 2nd Eng'g. Dist. | Plan and POW Preparation Ongoing |  |  | 2018 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
Panabo City | San Pedro | 2nd Eng'g. Dist. | Plan and POW Preparation Ongoing |  |  | 2018 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
Panabo City | San Pedro | 2nd Eng'g. Dist. | Plan and POW Preparation Ongoing |  |  | 2018 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Panabo City | San Pedro | 2nd Eng'g. Dist. | Plan and POW Preparation Ongoing |  |  | 2018 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Date Allotment Released: |  | Date completed:
Panabo City | San Pedro | 2nd Eng'g. Dist. | Plan and POW Preparation Ongoing |  |  | 2018 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Date Started:
Panabo City | Maduao | 2nd Eng'g. Dist. | Suspended | 2020-09-03 |  | 2018 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | Rehab. Of Multi-Purpose Gym & Facililies Maduao, Panabo City |  | 20% DF CY 2018 (STIMULUS) | Gym |  |  |  | Project Cost: | 500000 | Target Completion Date: | 2020-10-07 | Program: | 500000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Post qualification on process | Post qualification on process | Suspended due to overlapping of activity. (DIGOS CONTRAK CORP.) | Suspended due to overlapping of activity. (DIGOS CONTRAK CORP.) | Suspended due to overlapping of activity. (DIGOS CONTRAK CORP.) | Suspended due to overlapping of activity. (DIGOS CONTRAK CORP.)
Panabo City | Maduao | 2nd Eng'g. Dist. | Suspended | 2020-09-03 |  | 2018 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
Panabo City | Maduao | 2nd Eng'g. Dist. | Suspended | 2020-09-03 |  | 2018 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Implementor: | Digos Constrak Corp/ | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
Panabo City | Maduao | 2nd Eng'g. Dist. | Suspended | 2020-09-03 |  | 2018 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Duration: | 34 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Panabo City | Maduao | 2nd Eng'g. Dist. | Suspended | 2020-09-03 |  | 2018 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Date Allotment Released: |  | Date completed:
Panabo City | Maduao | 2nd Eng'g. Dist. | Suspended | 2020-09-03 |  | 2018 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Date Started: | 2020-09-03
Panabo City | Sto. Niño | 2nd Eng'g. Dist. | Hold in Abeyance |  |  | 2018 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | Const. of Multi-Purpose Bldg. Sto. Nino, Panabo City |  | 20% DF CY 2018 (STIMULUS) | Court |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | PR # 20032818 | PR # 20032818 | Procurement on process | Hold in abeyance | Hold in abeyance | Hold in abeyance
Panabo City | Sto. Niño | 2nd Eng'g. Dist. | Hold in Abeyance |  |  | 2018 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
Panabo City | Sto. Niño | 2nd Eng'g. Dist. | Hold in Abeyance |  |  | 2018 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
Panabo City | Sto. Niño | 2nd Eng'g. Dist. | Hold in Abeyance |  |  | 2018 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Panabo City | Sto. Niño | 2nd Eng'g. Dist. | Hold in Abeyance |  |  | 2018 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Date Allotment Released: |  | Date completed:
Panabo City | Sto. Niño | 2nd Eng'g. Dist. | Hold in Abeyance |  |  | 2018 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Date Started:
Panabo City | Dapco | 2nd Eng'g. Dist. | Completed | 2020-04-07 | 2020-10-08 | 2018 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | Completion of Canopy at DAPCO Covered Court, Dapco, Panabo City |  | 20% DF CY 2018 (STIMULUS) | Court |  |  | Contract | Project Cost: | 500000 | Target Completion Date: | 2020-10-08 | Program: | 500000 | Planned: |  | Planned: |  | Planned: |  | Planned: | 100% | Planned: | 100% | No. of Persons: |  | (RLHV Design & Build) Winning Bidder | (RLHV Design & Build) Winning Bidder | For implementation (RLHV Design & Build) | Completed as per physical accomplishment. | Completed as per physical accomplishment. | Completed as per Program of Works
Panabo City | Dapco | 2nd Eng'g. Dist. | Completed | 2020-04-07 | 2020-10-08 | 2018 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Project Engineer: | Estorco | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
Panabo City | Dapco | 2nd Eng'g. Dist. | Completed | 2020-04-07 | 2020-10-08 | 2018 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Implementor: | RLHV | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: | 100% | Actual: | 100%
Panabo City | Dapco | 2nd Eng'g. Dist. | Completed | 2020-04-07 | 2020-10-08 | 2018 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Duration: | 184 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Panabo City | Dapco | 2nd Eng'g. Dist. | Completed | 2020-04-07 | 2020-10-08 | 2018 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Date Allotment Released: |  | Date completed: | 2020-10-08
Panabo City | Dapco | 2nd Eng'g. Dist. | Completed | 2020-04-07 | 2020-10-08 | 2018 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Date Started: | 2020-04-07
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | Completed | 2020-04-07 | 2020-09-16 | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | Const. of Perimeter Fence at Kinamayan Integrated School, Kinamayan, Sto. Tomas |  | 20% DF CY 2018 (STIMULUS) | Bldg |  |  | Contract | Project Cost: | 431751.89 | Target Completion Date: | 2020-06-06 | Program: | 431751.89 | Planned: | 100% | No. of Persons: | 0 | Completed September 16, 2020/ Subject for Liquidated Damages |  | Planned: | 100% | Planned: | 100% | No. of Persons: | 0 |  |  |  | Completed as per physical accomplishment. | Completed as per physical accomplishment. | Completed as per Program of Works
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | Completed | 2020-04-07 | 2020-09-16 | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Project Engineer: | Abayon | Revised Completion Date: | Sept. 1, 2020 | Allotment: | 431751.89 | Revised: | 100% | No. of Man-days: | 0 |  |  | Revised: | 100% | Revised: | 100% | No. of Man-days: | 0
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | Completed | 2020-04-07 | 2020-09-16 | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Implementor: | RLHV | No. of days suspended: | 86 | Disbursement: |  | Actual: | 91.3% |  |  |  |  | Actual: | 100% | Actual: | 100%
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | Completed | 2020-04-07 | 2020-09-16 | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Duration: | 60 | No. of days extended: |  |  |  | Slippage: | -8.7% |  |  |  |  | Slippage: | 0% | Slippage: | 0%
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | Completed | 2020-04-07 | 2020-09-16 | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Date Allotment Released: |  | Date completed: | 2020-09-16
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | Completed | 2020-04-07 | 2020-09-16 | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Date Started: | 2020-04-07
IGCS | Pichon | 2nd Eng'g. Dist. | Completed | 2020-01-13 | 2020-09-08 | 2018 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | Impv't. of Brgy. Water System, Pichon, IGCS (Construction of Elevated Tank) |  | 20% DF CY 2018 (STIMULUS) | Water System |  |  | Admin | Project Cost: | 500000 | Target Completion Date: | 2020-03-13 | Program: | 500000 | Planned: | 100% | Planned: | 100% | Planned: | 100% | Planned: | 100% | Planned: | 100% | No. of Persons: | 5 | On-going | On-going | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per Program of Works
IGCS | Pichon | 2nd Eng'g. Dist. | Completed | 2020-01-13 | 2020-09-08 | 2018 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Project Engineer: | Andoy | Revised Completion Date: | 2020-09-08 | Allotment: | 500000 | Revised: | 86% | Revised: | 86% | Revised: | 100% | Revised: | 100% | Revised: | 100% | No. of Man-days: | 110
IGCS | Pichon | 2nd Eng'g. Dist. | Completed | 2020-01-13 | 2020-09-08 | 2018 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: | 423575.63 | Actual: | 83.5% | Actual: | 83.5% | Actual: | 100% | Actual: | 100% | Actual: | 100%
IGCS | Pichon | 2nd Eng'g. Dist. | Completed | 2020-01-13 | 2020-09-08 | 2018 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Duration: | 60 | No. of days extended: | 179 |  |  | Slippage: | -2.5% | Slippage: | -2.5% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
IGCS | Pichon | 2nd Eng'g. Dist. | Completed | 2020-01-13 | 2020-09-08 | 2018 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Date Allotment Released: | 2018-05-31 | Date completed: | 2020-09-08
IGCS | Pichon | 2nd Eng'g. Dist. | Completed | 2020-01-13 | 2020-09-08 | 2018 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Date Started: | 2020-01-13
IGCS | Tagbay | 2nd Eng'g. Dist. | For Implementation |  |  | 2018 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | Water System From Prk. 6 - Prk. 2 - Prk. 5A, Tagbay, IGCS |  | 20% DF CY 2018 (STIMULUS) | Water System |  |  | Admin | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | For Implementation | For Implementation | For Implementation | For Implementation | For Implementation | For Implementation
IGCS | Tagbay | 2nd Eng'g. Dist. | For Implementation |  |  | 2018 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
IGCS | Tagbay | 2nd Eng'g. Dist. | For Implementation |  |  | 2018 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
IGCS | Tagbay | 2nd Eng'g. Dist. | For Implementation |  |  | 2018 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
IGCS | Tagbay | 2nd Eng'g. Dist. | For Implementation |  |  | 2018 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Date Allotment Released: |  | Date completed:
IGCS | Tagbay | 2nd Eng'g. Dist. | For Implementation |  |  | 2018 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Date Started:
IGCS | Linusotan | 2nd Eng'g. Dist. | Re-aligned to COVID |  |  | 2018 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | Drilling of Water System, Linusotan, IGCS |  | 20% DF CY 2018(STIMULUS) | Water System |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
IGCS | Linusotan | 2nd Eng'g. Dist. | Re-aligned to COVID |  |  | 2018 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
IGCS | Linusotan | 2nd Eng'g. Dist. | Re-aligned to COVID |  |  | 2018 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
IGCS | Linusotan | 2nd Eng'g. Dist. | Re-aligned to COVID |  |  | 2018 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
IGCS | Linusotan | 2nd Eng'g. Dist. | Re-aligned to COVID |  |  | 2018 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Date Allotment Released: |  | Date completed:
IGCS | Linusotan | 2nd Eng'g. Dist. | Re-aligned to COVID |  |  | 2018 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Date Started:
IGCS | Cogon | 2nd Eng'g. Dist. | Completed | 2020-08-05 | 2020-12-12 | 2018 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | Powerline Expansion Project, Cogon, IGACOS |  | 20% DF CY 2018 (STIMULUS) | Water System |  |  | Contract | Project Cost: | 500000 | Target Completion Date: | 2020-08-21 | Program: | 500000 | Planned: |  | Planned: |  | Planned: |  | Planned: | 100% | Planned: | 100% | No. of Persons: |  | Waiting for NTP (3E Electrical) | Waiting for NTP (3E Electrical) | Waiting for NTP (3E Electrical) | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per Program of Works
IGCS | Cogon | 2nd Eng'g. Dist. | Completed | 2020-08-05 | 2020-12-12 | 2018 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Project Engineer: | Porras | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
IGCS | Cogon | 2nd Eng'g. Dist. | Completed | 2020-08-05 | 2020-12-12 | 2018 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Implementor: | 3E Electrical Sales | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: | 100% | Actual: | 100%
IGCS | Cogon | 2nd Eng'g. Dist. | Completed | 2020-08-05 | 2020-12-12 | 2018 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
IGCS | Cogon | 2nd Eng'g. Dist. | Completed | 2020-08-05 | 2020-12-12 | 2018 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Date Allotment Released: |  | Date completed: | 2020-12-12
IGCS | Cogon | 2nd Eng'g. Dist. | Completed | 2020-08-05 | 2020-12-12 | 2018 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Date Started: | 2020-08-05
IGCS | Tambo | 2nd Eng'g. Dist. | Completed | 2020-04-04 | 2020-08-12 | 2018 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | RURAL ELECTRIFICATION PROJECT | Powerline Expansion Project, Tambo, IGCS |  | GENERAL FUND PROPER CY 2018 (STIMULUS) | Electrification |  |  | Contract | Project Cost: | 500000 | Target Completion Date: | 2020-07-02 23:46 | Program: | 500000 | Planned: |  | Planned: | 100% | Planned: | 100% | Planned: | 100% | Planned: | 100% | No. of Persons: |  | Waiting for NTP (3E Electrical) | Waiting for NTP (3E Electrical) | Waiting for NTP (3E Electrical) | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per Program of Works
IGCS | Tambo | 2nd Eng'g. Dist. | Completed | 2020-04-04 | 2020-08-12 | 2018 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | RURAL ELECTRIFICATION PROJECT | [7 empty] | Project Engineer: | Lu | Revised Completion Date: | 2020-08-30 23:46 | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
IGCS | Tambo | 2nd Eng'g. Dist. | Completed | 2020-04-04 | 2020-08-12 | 2018 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | RURAL ELECTRIFICATION PROJECT | [7 empty] | Implementor: | 3E Electrical Sales | No. of days suspended: | 59 | Disbursement: |  | Actual: |  | Actual: | 100% | Actual: | 100% | Actual: | 100% | Actual: | 100%
IGCS | Tambo | 2nd Eng'g. Dist. | Completed | 2020-04-04 | 2020-08-12 | 2018 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | RURAL ELECTRIFICATION PROJECT | [7 empty] | Duration: | 90 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
IGCS | Tambo | 2nd Eng'g. Dist. | Completed | 2020-04-04 | 2020-08-12 | 2018 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | RURAL ELECTRIFICATION PROJECT | [7 empty] | Date Allotment Released: |  | Date completed: | 2020-08-12
IGCS | Tambo | 2nd Eng'g. Dist. | Completed | 2020-04-04 | 2020-08-12 | 2018 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | RURAL ELECTRIFICATION PROJECT | [7 empty] | Date Started: | 2020-04-04
IGCS | Dadatan | 2nd Eng'g. Dist. | On-going | 2020-03-10 |  | 2018 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | Electrification of Sitio Baongon-Diamond-Mansanitas, Dadatan, IGCS |  | 20% DF CY 2018 (STIMULUS) | Electrification |  |  |  | Project Cost: | 500000 | Target Completion Date: | 2020-05-09 | Program: | 500000 | Planned: |  | Planned: |  | Planned: | 100% | Planned: | 100% | Planned: | 100% | No. of Persons: |  | On-going (Subject for Liquidated damages) | On-going (Subject for Liquidated damages) | On-going (Subject for Liquidated damages) | On-going (Subject for Liquidated damages) | On-going (Subject for Liquidated damages) | On-going (Subject for Liquidated damages)
IGCS | Dadatan | 2nd Eng'g. Dist. | On-going | 2020-03-10 |  | 2018 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Project Engineer: | Lu | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: | 100% | Revised: | 100% | Revised: | 100% | No. of Man-days:
IGCS | Dadatan | 2nd Eng'g. Dist. | On-going | 2020-03-10 |  | 2018 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Implementor: | 3E Electrical Sales | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: | 65.1% | Actual: | 65.1% | Actual: | 65.1%
IGCS | Dadatan | 2nd Eng'g. Dist. | On-going | 2020-03-10 |  | 2018 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Duration: | 60 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | -34.9% | Slippage: | -34.9% | Slippage: | -34.9%
IGCS | Dadatan | 2nd Eng'g. Dist. | On-going | 2020-03-10 |  | 2018 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Date Allotment Released: |  | Date completed:
IGCS | Dadatan | 2nd Eng'g. Dist. | On-going | 2020-03-10 |  | 2018 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Date Started: | 2020-03-10
IGCS | Tagdaliao | 2nd Eng'g. Dist. | Completed | 2020-08-05 | 2020-08-21 | 2018 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | Const. of Brgy. Health Station, Tagdaliao, IGCS |  | 20% DF CY 2018 (STIMULUS) | Water System |  |  | Contract | Project Cost: | 500000 | Target Completion Date: | 2020-08-21 | Program: | 500000 | Planned: |  | Planned: |  | Planned: |  | Planned: | 100% | Planned: | 100% | No. of Persons: |  | Waiting for NTP (3E Electrical) | Waiting for NTP (3E Electrical) | Waiting for NTP (3E Electrical) | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per Program of Works
IGCS | Tagdaliao | 2nd Eng'g. Dist. | Completed | 2020-08-05 | 2020-08-21 | 2018 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Project Engineer: | Porras | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
IGCS | Tagdaliao | 2nd Eng'g. Dist. | Completed | 2020-08-05 | 2020-08-21 | 2018 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Implementor: | 3E Electrical Sales | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: | 100% | Actual: | 100%
IGCS | Tagdaliao | 2nd Eng'g. Dist. | Completed | 2020-08-05 | 2020-08-21 | 2018 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
IGCS | Tagdaliao | 2nd Eng'g. Dist. | Completed | 2020-08-05 | 2020-08-21 | 2018 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Date Allotment Released: |  | Date completed: | 2020-08-21
IGCS | Tagdaliao | 2nd Eng'g. Dist. | Completed | 2020-08-05 | 2020-08-21 | 2018 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Date Started: | 2020-08-05
San Isidro | Mamangan | 1st Eng'g. Dist. | Completed | 2019-11-18 | 2020-01-31 | 2019 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | Rehabilitation & Flooring of Gymnasium Basketball Court, Mamangan, San Isidro |  | 20% DF CY 2018 (STIMULUS) | Building |  |  |  | Project Cost: | 500000 | Target Completion Date: | 2020-01-31 23:59 | Program: | 500000 | Planned: |  | Planned: |  | Planned: |  | Planned: | 100% | Planned: | 100% | No. of Persons: |  | PROJECT Was funded by LGU, Kapalong | PROJECT Was funded by LGU, Kapalong | PROJECT Was funded by LGU, Kapalong | Completed as per physical accomplishment. | Completed as per physical accomplishment. | Completed as per Program of Works
San Isidro | Mamangan | 1st Eng'g. Dist. | Completed | 2019-11-18 | 2020-01-31 | 2019 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Project Engineer: | Kabingue | Revised Completion Date: | 2020-01-31 23:59 | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
San Isidro | Mamangan | 1st Eng'g. Dist. | Completed | 2019-11-18 | 2020-01-31 | 2019 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: | 100% | Actual: | 100%
San Isidro | Mamangan | 1st Eng'g. Dist. | Completed | 2019-11-18 | 2020-01-31 | 2019 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Duration: | 75 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
San Isidro | Mamangan | 1st Eng'g. Dist. | Completed | 2019-11-18 | 2020-01-31 | 2019 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Allotment Released: |  | Date completed: | 2020-01-31
San Isidro | Mamangan | 1st Eng'g. Dist. | Completed | 2019-11-18 | 2020-01-31 | 2019 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Started: | 2019-11-18
San Isidro | Mamangan | 1st Eng'g. Dist. | Procurement on process |  |  |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | Grouted Riprap on Embankment Sto. Ñino, Talaingod |  | 20% DF CY 2018 (STIMULUS) | Embankment |  |  |  | Project Cost: |  | Target Completion Date: |  | Program: | 0 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | PROJECT Was funded by LGU, Kapalong | PROJECT Was funded by LGU, Kapalong | PROJECT Was funded by LGU, Kapalong | Procurment on process | Procurment on process | Procurment on process
San Isidro | Mamangan | 1st Eng'g. Dist. | Procurement on process |  |  |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 0 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
San Isidro | Mamangan | 1st Eng'g. Dist. | Procurement on process |  |  |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
San Isidro | Mamangan | 1st Eng'g. Dist. | Procurement on process |  |  |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
San Isidro | Mamangan | 1st Eng'g. Dist. | Procurement on process |  |  |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Allotment Released: |  | Date completed:
San Isidro | Mamangan | 1st Eng'g. Dist. | Procurement on process |  |  |  |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Started:
Talaingod | Dagohoy | 1st Eng'g. Dist. | On-going | 2020-12-07 |  | 2018 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | Barangay Hall Improvement, Dagohoy, Talaingod |  | 20% DF CY 2018 (STIMULUS) | Building |  |  | Contract | Project Cost: | 500000 | Target Completion Date: | 2021-01-20 23:59 | Program: | 500000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | For amendment to Construction of Retaining Wall as per recommendation by Engr. Misa during site re-evaluation. Plan & POW completed.Resolution from the Brgy. Council to support the amendment c/o Engr. Canillada | For amendment to Construction of Retaining Wall as per recommendation by Engr. Misa during site re-evaluation. Plan & POW completed.Resolution from the Brgy. Council to support the amendment c/o Engr. Canillada | Awarded to Alpebels Builders & Supply Corporation | For implementation | For implementation | On-going
Talaingod | Dagohoy | 1st Eng'g. Dist. | On-going | 2020-12-07 |  | 2018 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Project Engineer: | Kabingue | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
Talaingod | Dagohoy | 1st Eng'g. Dist. | On-going | 2020-12-07 |  | 2018 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Implementor: | Alpebels Builders & Supply Corporation | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
Talaingod | Dagohoy | 1st Eng'g. Dist. | On-going | 2020-12-07 |  | 2018 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Duration: | 45 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Talaingod | Dagohoy | 1st Eng'g. Dist. | On-going | 2020-12-07 |  | 2018 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Date Allotment Released: |  | Date completed:
Talaingod | Dagohoy | 1st Eng'g. Dist. | On-going | 2020-12-07 |  | 2018 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Date Started: | 2020-12-07
Tagum City | Libuganon | 1st Eng'g. Dist. | Completed | 2020-06-16 | 2020-08-18 | 2018 | Administartion | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | Construction of Drainage Canal, Libuganon, Tagum City |  | GF CY 2018 (STIMULUS) | Drainage |  |  | Admin | Project Cost: | 500000 | Target Completion Date: | 2020-08-18 23:59 | Program: | 500000 | Planned: | 53.04% | Planned: | 100% | Planned: | 100% | Planned: | 100% | No. of Persons: | 14 | No. of Persons: |  | For amendment to Construction of Retaining Wall as per recommendation by Engr. Misa during site re-evaluation. Plan & POW completed.Resolution from the Brgy. Council to support the amendment c/o Engr. Canillada | For amendment to Construction of Retaining Wall as per recommendation by Engr. Misa during site re-evaluation. Plan & POW completed.Resolution from the Brgy. Council to support the amendment c/o Engr. Canillada | Awarded to Alpebels Builders & Supply Corporation | For implementation | For implementation | Completed as per Program of Works
Tagum City | Libuganon | 1st Eng'g. Dist. | Completed | 2020-06-16 | 2020-08-18 | 2018 | Administartion | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Project Engineer: | Quirante | Revised Completion Date: | 2020-08-18 23:59 | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 434 | No. of Man-days:
Tagum City | Libuganon | 1st Eng'g. Dist. | Completed | 2020-06-16 | 2020-08-18 | 2018 | Administartion | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: | 53.04% | Actual: | 100% | Actual: | 100% | Actual: | 100%
Tagum City | Libuganon | 1st Eng'g. Dist. | Completed | 2020-06-16 | 2020-08-18 | 2018 | Administartion | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Duration: | 64 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Tagum City | Libuganon | 1st Eng'g. Dist. | Completed | 2020-06-16 | 2020-08-18 | 2018 | Administartion | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Date Allotment Released: |  | Date completed: | 2020-08-18
Tagum City | Libuganon | 1st Eng'g. Dist. | Completed | 2020-06-16 | 2020-08-18 | 2018 | Administartion | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Date Started: | 2020-06-16
Kapalong | Mamacao | 1st Eng'g. Dist. | Completed | 2020-02-05 | 2020-06-15 | 2018 | Administartion | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | Construction of Bleacher, Mamacao, Kapalong |  | GF CY 2018 (STIMULUS) | Bleacher |  | sq.m | Admin | Project Cost: | 500000 | Target Completion Date: | 2020-04-19 23:46 | Program: | 500000 | Planned: | 100% | Planned: | 100% | Planned: | 100% | Planned: | 100% | Planned: | 100% | No. of Persons: |  | For amendment to Construction of Retaining Wall as per recommendation by Engr. Misa during site re-evaluation. Plan & POW completed.Resolution from the Brgy. Council to support the amendment c/o Engr. Canillada | For amendment to Construction of Retaining Wall as per recommendation by Engr. Misa during site re-evaluation. Plan & POW completed.Resolution from the Brgy. Council to support the amendment c/o Engr. Canillada | Awarded to Alpebels Builders & Supply Corporation | For implementation | For implementation | Completed as per Program of Works
Kapalong | Mamacao | 1st Eng'g. Dist. | Completed | 2020-02-05 | 2020-06-15 | 2018 | Administartion | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Project Engineer: | Ambrosio | Revised Completion Date: | 2020-06-15 23:46 | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
Kapalong | Mamacao | 1st Eng'g. Dist. | Completed | 2020-02-05 | 2020-06-15 | 2018 | Administartion | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: |  | Actual: | 100% | Actual: | 100% | Actual: | 100% | Actual: | 100% | Actual: | 100%
Kapalong | Mamacao | 1st Eng'g. Dist. | Completed | 2020-02-05 | 2020-06-15 | 2018 | Administartion | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Duration: | 75 | No. of days extended: | 30 |  |  | Slippage: |  | Slippage: |  | Slippage: |  | Slippage: |  | Slippage:
Kapalong | Mamacao | 1st Eng'g. Dist. | Completed | 2020-02-05 | 2020-06-15 | 2018 | Administartion | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Date Allotment Released: |  | Date completed: | 2020-06-15
Kapalong | Mamacao | 1st Eng'g. Dist. | Completed | 2020-02-05 | 2020-06-15 | 2018 | Administartion | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Date Started: | 2020-02-05
Kapalong | Luna | 1st Eng'g. Dist. | completed | 2020-06-01 | 2020-07-25 | 2018 | Administartion | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | Construction of Concrete Perimeter Fence, Luna, Kapalaong |  | GF CY 2018 (STIMULUS) | Fence |  | sq.m | Admin | Project Cost: | 500000 | Target Completion Date: | 2020-07-21 | Program: | 500000 | Planned: | 100% | Planned: | 100% | Planned: | 100% | Planned: | 100% | Planned: | 100% | No. of Persons: | 8 | For amendment to Construction of Retaining Wall as per recommendation by Engr. Misa during site re-evaluation. Plan & POW completed.Resolution from the Brgy. Council to support the amendment c/o Engr. Canillada | For amendment to Construction of Retaining Wall as per recommendation by Engr. Misa during site re-evaluation. Plan & POW completed.Resolution from the Brgy. Council to support the amendment c/o Engr. Canillada | Awarded to Alpebels Builders & Supply Corporation | For implementation | For implementation | Completed as per Program of Works
Kapalong | Luna | 1st Eng'g. Dist. | completed | 2020-06-01 | 2020-07-25 | 2018 | Administartion | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Project Engineer: | Ambrosio | Revised Completion Date: | 2020-07-21 | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 120
Kapalong | Luna | 1st Eng'g. Dist. | completed | 2020-06-01 | 2020-07-25 | 2018 | Administartion | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: | 100% | Actual: | 100% | Actual: | 100% | Actual: | 100% | Actual: | 100%
Kapalong | Luna | 1st Eng'g. Dist. | completed | 2020-06-01 | 2020-07-25 | 2018 | Administartion | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Duration: | 50 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Kapalong | Luna | 1st Eng'g. Dist. | completed | 2020-06-01 | 2020-07-25 | 2018 | Administartion | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Date Allotment Released: |  | Date completed: | 2020-07-25
Kapalong | Luna | 1st Eng'g. Dist. | completed | 2020-06-01 | 2020-07-25 | 2018 | Administartion | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Date Started: | 2020-06-01
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2020-03-30 |  | 2018 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./COMPL./IMPV'T. OF VARIOUS GOV'T. BLDGS., STRUCTURES & FACILITIES (Const. in Progress - Bldgs. & Other Structures | Construction of SP/Legislative Building, Gov't. Center, Mankilam, Tagum City |  | SB # 3 CY 2018 | Building |  |  | Contract | Project Cost: | 147262698.81 | Target Completion Date: | 2021-04-04 | Program: | 147262698.81 | Planned: | 5.78% | Planned: | 5.78% | Planned: | 14.98% | Planned: | 14.98% | Planned: | 58.3% | No. of Persons: | 34 | For amendment to Construction of Retaining Wall as per recommendation by Engr. Misa during site re-evaluation. Plan & POW completed.Resolution from the Brgy. Council to support the amendment c/o Engr. Canillada | For amendment to Construction of Retaining Wall as per recommendation by Engr. Misa during site re-evaluation. Plan & POW completed.Resolution from the Brgy. Council to support the amendment c/o Engr. Canillada | Awarded to Alpebels Builders & Supply Corporation | For implementation | For implementation | On-going
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2020-03-30 |  | 2018 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./COMPL./IMPV'T. OF VARIOUS GOV'T. BLDGS., STRUCTURES & FACILITIES (Const. in Progress - Bldgs. & Other Structures | [7 empty] | Project Engineer: | Japay/Albaracin | Revised Completion Date: | 2021-05-01 | Allotment: | 147262698.81 | Revised: | 3.15% | Revised: | 4.777% | Revised: | 7.387% | Revised: | 7.387% | Revised: | 38.89% | No. of Man-days: | 884
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2020-03-30 |  | 2018 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./COMPL./IMPV'T. OF VARIOUS GOV'T. BLDGS., STRUCTURES & FACILITIES (Const. in Progress - Bldgs. & Other Structures | [7 empty] | Implementor: | Tagum Builders | No. of days suspended: | 27 | Disbursement: |  | Actual: | 5.28% | Actual: | 7.37% | Actual: | 8.971% | Actual: | 8.971% | Actual: | 26.56%
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2020-03-30 |  | 2018 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./COMPL./IMPV'T. OF VARIOUS GOV'T. BLDGS., STRUCTURES & FACILITIES (Const. in Progress - Bldgs. & Other Structures | [7 empty] | Duration: | 370 | No. of days extended: |  |  |  | Slippage: | 2.13% |  | 2.594% |  | 1.584% |  | 1.584% | Slippage: | -12.33%
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2020-03-30 |  | 2018 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./COMPL./IMPV'T. OF VARIOUS GOV'T. BLDGS., STRUCTURES & FACILITIES (Const. in Progress - Bldgs. & Other Structures | [7 empty] | Date Allotment Released: |  | Date completed:
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2020-03-30 |  | 2018 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./COMPL./IMPV'T. OF VARIOUS GOV'T. BLDGS., STRUCTURES & FACILITIES (Const. in Progress - Bldgs. & Other Structures | [7 empty] | Date Started: | 2020-03-30
Asuncion | Sonlon | 1st Eng'g. Dist. | Completed | 2019-09-16 | 2020-02-29 | 2018 | Administration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | DISASTER PREVENTION AND MITIGATION PROGRAM - FLOOD CONTROL AND SLOPE PROTECTION PROJECT (Improvement of Bridges and Cross Drainage) | Rehab./Impv't. of Sonlon-Longanapan Road |  | 5% CALAMITY FUND CY 2018 | Road |  | km | Admin | Project Cost: | 1500000 | Target Completion Date: | 2020-02-29 23:59 | Program: | 1500000 | Planned: |  | Planned: |  | Planned: |  | Planned: | 100% | Planned: | 100% | No. of Persons: |  | Final Abstract # 0320200900 (Alpebel Builders & Supply Corp.) | Final Abstract # 0320200900 (Alpebel Builders & Supply Corp.) | Final Abstract # 0320200900 (Alpebel Builders & Supply Corp.) | Completed as per physical accomplishment. | Completed as per physical accomplishment. | Completed as per Program of Works
Asuncion | Sonlon | 1st Eng'g. Dist. | Completed | 2019-09-16 | 2020-02-29 | 2018 | Administration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | DISASTER PREVENTION AND MITIGATION PROGRAM - FLOOD CONTROL AND SLOPE PROTECTION PROJECT (Improvement of Bridges and Cross Drainage) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 1500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
Asuncion | Sonlon | 1st Eng'g. Dist. | Completed | 2019-09-16 | 2020-02-29 | 2018 | Administration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | DISASTER PREVENTION AND MITIGATION PROGRAM - FLOOD CONTROL AND SLOPE PROTECTION PROJECT (Improvement of Bridges and Cross Drainage) | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: | 100% | Actual: | 100%
Asuncion | Sonlon | 1st Eng'g. Dist. | Completed | 2019-09-16 | 2020-02-29 | 2018 | Administration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | DISASTER PREVENTION AND MITIGATION PROGRAM - FLOOD CONTROL AND SLOPE PROTECTION PROJECT (Improvement of Bridges and Cross Drainage) | [7 empty] | Duration: | 167 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Asuncion | Sonlon | 1st Eng'g. Dist. | Completed | 2019-09-16 | 2020-02-29 | 2018 | Administration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | DISASTER PREVENTION AND MITIGATION PROGRAM - FLOOD CONTROL AND SLOPE PROTECTION PROJECT (Improvement of Bridges and Cross Drainage) | [7 empty] | Date Allotment Released: |  | Date completed: | 2020-02-29
Asuncion | Sonlon | 1st Eng'g. Dist. | Completed | 2019-09-16 | 2020-02-29 | 2018 | Administration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | DISASTER PREVENTION AND MITIGATION PROGRAM - FLOOD CONTROL AND SLOPE PROTECTION PROJECT (Improvement of Bridges and Cross Drainage) | [7 empty] | Date Started: | 2019-09-16
Carmen | Mabaus | 2nd Eng'g. Dist. |  |  |  | 2018 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | DESILTATION/EXCAVATION | Impv't. of Mabaus Cross Drainage |  | 5% CALAMITY FUND CY 2018 | Improvement |  | ln.m |  | Project Cost: | 3000000 | Target Completion Date: | 0 | Program: | 3000000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Plan On-going | Plan On-going | Plan On-going |  |  | For verification
Carmen | Mabaus | 2nd Eng'g. Dist. |  |  |  | 2018 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | DESILTATION/EXCAVATION | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 3000000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
Carmen | Mabaus | 2nd Eng'g. Dist. |  |  |  | 2018 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | DESILTATION/EXCAVATION | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
Carmen | Mabaus | 2nd Eng'g. Dist. |  |  |  | 2018 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | DESILTATION/EXCAVATION | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: |  | Slippage:
Carmen | Mabaus | 2nd Eng'g. Dist. |  |  |  | 2018 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | DESILTATION/EXCAVATION | [7 empty] | Date Allotment Released: |  | Date completed:
Carmen | Mabaus | 2nd Eng'g. Dist. |  |  |  | 2018 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | DESILTATION/EXCAVATION | [7 empty] | Date Started:
Carmen | Ising | 2nd Eng'g. Dist. | Completed | 2020-03-19 | 2020-10-12 | 2018 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | Const. of DDN Hospital Carmen Zone Annex Bldg. |  | SB # 1 CY 2018 | Building |  | sq.m | Contract | Project Cost: | 5500000 | Target Completion Date: | 2020-07-15 | Program: | 5500000 | Planned: | 95.2% | Planned: | 100% | Planned: | 100% | Planned: | 100% | Planned: | 100% | No. of Persons: | 10 | On-going | On-going | On-going | Completed as per physical accomplishment. | Completed as per physical accomplishment. | Completed as per Program of Works
Carmen | Ising | 2nd Eng'g. Dist. | Completed | 2020-03-19 | 2020-10-12 | 2018 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | [7 empty] | Project Engineer: | Azotes | Revised Completion Date: | 2020-09-10 | Allotment: | 5500000 | Revised: | 40.5% | Revised: | 99.09% | Revised: | 100% | Revised: | 100% | Revised: | 100% | No. of Man-days: | 260
Carmen | Ising | 2nd Eng'g. Dist. | Completed | 2020-03-19 | 2020-10-12 | 2018 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | [7 empty] | Implementor: | Digos Constrak Corp/ | No. of days suspended: | 57 | Disbursement: | 1650000 | Actual: | 68.25% | Actual: | 90.62% | Actual: | 94.99% | Actual: | 100% | Actual: | 100%
Carmen | Ising | 2nd Eng'g. Dist. | Completed | 2020-03-19 | 2020-10-12 | 2018 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | [7 empty] | Duration: | 120 | No. of days extended: |  |  |  | Slippage: | 27.75% | Slippage: | -8.47% | Slippage: | -5.01% | Slippage: | 0% | Slippage: | 0%
Carmen | Ising | 2nd Eng'g. Dist. | Completed | 2020-03-19 | 2020-10-12 | 2018 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | [7 empty] | Date Allotment Released: |  | Date completed: | 2020-10-12
Carmen | Ising | 2nd Eng'g. Dist. | Completed | 2020-03-19 | 2020-10-12 | 2018 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Rehab./Comp. of Various Gov't. Bldgs. Struct., Fac. (Provincewide) | [7 empty] | Date Started: | 2020-03-17
New Corella | Mesaoy | 1st Eng'g. Dist. | Completed | 2018-11-16 | 2020-02-29 | 2018 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REHABILITATION OF VARIOUS PROVINCIAL ROADS | Mesaoy - Jct. Mahayahay |  | SB # 1 CY 2018 | Road Rehabilitation |  | km | Admin | Project Cost: | 1534000 | Target Completion Date: | 2018-12-15 23:46 | Program: | 1534000 | Planned: | 100% | Planned: | 100% | Planned: | 100% | Planned: | 100% | Planned: | 100% | No. of Persons: | 6 | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. |  |  | Completed as per Program of Works
New Corella | Mesaoy | 1st Eng'g. Dist. | Completed | 2018-11-16 | 2020-02-29 | 2018 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REHABILITATION OF VARIOUS PROVINCIAL ROADS | [7 empty] | Project Engineer: | Pilotos | Revised Completion Date: |  | Allotment: | 1534000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: | 100% | No. of Man-days: | 150
New Corella | Mesaoy | 1st Eng'g. Dist. | Completed | 2018-11-16 | 2020-02-29 | 2018 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REHABILITATION OF VARIOUS PROVINCIAL ROADS | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: | 100% | Actual: | 100% | Actual: | 100% | Actual: | 100% | Actual: | 100%
New Corella | Mesaoy | 1st Eng'g. Dist. | Completed | 2018-11-16 | 2020-02-29 | 2018 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REHABILITATION OF VARIOUS PROVINCIAL ROADS | [7 empty] | Duration: | 30 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
New Corella | Mesaoy | 1st Eng'g. Dist. | Completed | 2018-11-16 | 2020-02-29 | 2018 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REHABILITATION OF VARIOUS PROVINCIAL ROADS | [7 empty] | Date Allotment Released: | 2018-07-19 | Date completed: | 2020-02-29
New Corella | Mesaoy | 1st Eng'g. Dist. | Completed | 2018-11-16 | 2020-02-29 | 2018 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REHABILITATION OF VARIOUS PROVINCIAL ROADS | [7 empty] | Date Started: | 2018-11-16
New Corella | Poblacion | 1st Eng'g. Dist. | Completed | 2019-10-09 | 2020-06-26 | 2018 | Administration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | DISASTER PREVENTION AND MITIGATION PROGRAM - FLOOD CONTROL AND SLOPE PROTECTION PROJECT (Improvement of Bridges and Cross Drainage) | Improvement of 5 CL at New Corella Central ES, Poblacion, New Corella |  | SEF-SB No. 2 CY 2018 | Building |  |  | Admin | Project Cost: | 750000 | Target Completion Date: | 2020-06-26 23:59 | Program: | 750000 | Planned: |  | Planned: |  | Planned: |  | Planned: | 100% | Planned: | 100% | No. of Persons: |  | Final Abstract # 0320200900 (Alpebel Builders & Supply Corp.) | Final Abstract # 0320200900 (Alpebel Builders & Supply Corp.) | Final Abstract # 0320200900 (Alpebel Builders & Supply Corp.) | Completed as per physical accomplishment. | Completed as per physical accomplishment. | Completed as per Program of Works
New Corella | Poblacion | 1st Eng'g. Dist. | Completed | 2019-10-09 | 2020-06-26 | 2018 | Administration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | DISASTER PREVENTION AND MITIGATION PROGRAM - FLOOD CONTROL AND SLOPE PROTECTION PROJECT (Improvement of Bridges and Cross Drainage) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 750000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
New Corella | Poblacion | 1st Eng'g. Dist. | Completed | 2019-10-09 | 2020-06-26 | 2018 | Administration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | DISASTER PREVENTION AND MITIGATION PROGRAM - FLOOD CONTROL AND SLOPE PROTECTION PROJECT (Improvement of Bridges and Cross Drainage) | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: | 100% | Actual: | 100%
New Corella | Poblacion | 1st Eng'g. Dist. | Completed | 2019-10-09 | 2020-06-26 | 2018 | Administration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | DISASTER PREVENTION AND MITIGATION PROGRAM - FLOOD CONTROL AND SLOPE PROTECTION PROJECT (Improvement of Bridges and Cross Drainage) | [7 empty] | Duration: | 262 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
New Corella | Poblacion | 1st Eng'g. Dist. | Completed | 2019-10-09 | 2020-06-26 | 2018 | Administration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | DISASTER PREVENTION AND MITIGATION PROGRAM - FLOOD CONTROL AND SLOPE PROTECTION PROJECT (Improvement of Bridges and Cross Drainage) | [7 empty] | Date Allotment Released: |  | Date completed: | 2020-06-26
New Corella | Poblacion | 1st Eng'g. Dist. | Completed | 2019-10-09 | 2020-06-26 | 2018 | Administration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | DISASTER PREVENTION AND MITIGATION PROGRAM - FLOOD CONTROL AND SLOPE PROTECTION PROJECT (Improvement of Bridges and Cross Drainage) | [7 empty] | Date Started: | 2019-10-09
Kapalong | Maniki | 1st Eng'g. Dist. | Completed | 2019-11-02 | 2020-07-07 | 2018 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./COMPL./IMPV'T. OF VARIOUS GOV'T. BLDGS., STRUCTURES & FACILITIES (Const. in Progress - Bldgs. & Other Structures | Const./Impv't. of DDN Hospital Kapalong Zone |  | SB # 2 CY 2018 | Building |  | sq.m | Contract | Project Cost: | 5000000 | Target Completion Date: | 2020-06-09 | Program: | 5000000 | Planned: | 100% | Planned: | 100% | Planned: | 100% | Planned: | 100% | Planned: | 100% | No. of Persons: | 7 | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per Program of Works
Kapalong | Maniki | 1st Eng'g. Dist. | Completed | 2019-11-02 | 2020-07-07 | 2018 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./COMPL./IMPV'T. OF VARIOUS GOV'T. BLDGS., STRUCTURES & FACILITIES (Const. in Progress - Bldgs. & Other Structures | [7 empty] | Project Engineer: | Ambrosio | Revised Completion Date: | 2020-07-07 | Allotment: | 5000000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 217
Kapalong | Maniki | 1st Eng'g. Dist. | Completed | 2019-11-02 | 2020-07-07 | 2018 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./COMPL./IMPV'T. OF VARIOUS GOV'T. BLDGS., STRUCTURES & FACILITIES (Const. in Progress - Bldgs. & Other Structures | [7 empty] | Implementor: | MAG CORP. | No. of days suspended: | 28 | Disbursement: | 4781000 | Actual: | 100% | Actual: | 100% | Actual: | 100% | Actual: | 100% | Actual: | 100%
Kapalong | Maniki | 1st Eng'g. Dist. | Completed | 2019-11-02 | 2020-07-07 | 2018 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./COMPL./IMPV'T. OF VARIOUS GOV'T. BLDGS., STRUCTURES & FACILITIES (Const. in Progress - Bldgs. & Other Structures | [7 empty] | Duration: | 220 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Kapalong | Maniki | 1st Eng'g. Dist. | Completed | 2019-11-02 | 2020-07-07 | 2018 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./COMPL./IMPV'T. OF VARIOUS GOV'T. BLDGS., STRUCTURES & FACILITIES (Const. in Progress - Bldgs. & Other Structures | [7 empty] | Date Allotment Released: | 2018-09-04 | Date completed: | 2020-07-07
Kapalong | Maniki | 1st Eng'g. Dist. | Completed | 2019-11-02 | 2020-07-07 | 2018 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./COMPL./IMPV'T. OF VARIOUS GOV'T. BLDGS., STRUCTURES & FACILITIES (Const. in Progress - Bldgs. & Other Structures | [7 empty] | Date Started: | 2019-11-02
New Corella | Poblacion | 1st Eng'g. Dist. | On-going | 2020-06-17 |  | 2018 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./COMPL./IMPV'T. OF VARIOUS GOV'T. BLDGS., STRUCTURES & FACILITIES (Const. in Progress - Bldgs. & Other Structures | Compl. Of Bahay Pag-Asa for Minors, New Corella |  | SB # 2 CY 2018 | Building |  |  | Admin | Project Cost: | 3450000 | Target Completion Date: | 2020-11-07 23:46 | Program: | 3450000 | Planned: | 15.75% | Planned: | 55.46% | Planned: | 71.45% | Planned: | 100% | Planned: | 98.48% | No. of Persons: | 20 | On-going | On-going | On-going | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | On-going
New Corella | Poblacion | 1st Eng'g. Dist. | On-going | 2020-06-17 |  | 2018 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./COMPL./IMPV'T. OF VARIOUS GOV'T. BLDGS., STRUCTURES & FACILITIES (Const. in Progress - Bldgs. & Other Structures | [7 empty] | Project Engineer: | Cahayag | Revised Completion Date: | 2021-01-15 23:46 | Allotment: | 3450000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 620
New Corella | Poblacion | 1st Eng'g. Dist. | On-going | 2020-06-17 |  | 2018 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./COMPL./IMPV'T. OF VARIOUS GOV'T. BLDGS., STRUCTURES & FACILITIES (Const. in Progress - Bldgs. & Other Structures | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: | 5.04% | Actual: | 42.41% | Actual: | 64.16% | Actual: | 100% | Actual: | 97.2%
New Corella | Poblacion | 1st Eng'g. Dist. | On-going | 2020-06-17 |  | 2018 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./COMPL./IMPV'T. OF VARIOUS GOV'T. BLDGS., STRUCTURES & FACILITIES (Const. in Progress - Bldgs. & Other Structures | [7 empty] | Duration: | 144 | No. of days extended: | 69 |  |  | Slippage: | -10.71% | Slippage: | -13.05% | Slippage: | -7.29% | Slippage: | 0% | Slippage: | -1.28%
New Corella | Poblacion | 1st Eng'g. Dist. | On-going | 2020-06-17 |  | 2018 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./COMPL./IMPV'T. OF VARIOUS GOV'T. BLDGS., STRUCTURES & FACILITIES (Const. in Progress - Bldgs. & Other Structures | [7 empty] | Date Allotment Released: |  | Date completed:
New Corella | Poblacion | 1st Eng'g. Dist. | On-going | 2020-06-17 |  | 2018 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./COMPL./IMPV'T. OF VARIOUS GOV'T. BLDGS., STRUCTURES & FACILITIES (Const. in Progress - Bldgs. & Other Structures | [7 empty] | Date Started: | 2020-06-17
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2020-01-09 |  | 2018 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./COMPL./IMPV'T. OF VARIOUS GOV'T. BLDGS., STRUCTURES & FACILITIES (Const. in Progress - Bldgs. & Other Structures | Const. of Add'l. 2nd Level Multi-Purpose HalI, PGSO warehouse,Bldg., Mankilam |  | SB # 2 CY 2018 | Building |  |  | Contract | Project Cost: | 7483756.22 | Target Completion Date: | 2020-07-06 23:46 | Program: | 7483756.22 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: | 99.07% | No. of Persons: | 19 | On-going | On-going | On-going | On-going | On-going | On-going
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2020-01-09 |  | 2018 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./COMPL./IMPV'T. OF VARIOUS GOV'T. BLDGS., STRUCTURES & FACILITIES (Const. in Progress - Bldgs. & Other Structures | [7 empty] | Project Engineer: | Mabanglo | Revised Completion Date: | 2020-09-13 23:46 | Allotment: | 7483756.22 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: | 40.05% | No. of Man-days: | 589
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2020-01-09 |  | 2018 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./COMPL./IMPV'T. OF VARIOUS GOV'T. BLDGS., STRUCTURES & FACILITIES (Const. in Progress - Bldgs. & Other Structures | [7 empty] | Implementor: | FZI CONSTRUCTION AND PARTS SUPPLY | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: | 9.68% | Actual: | 9.68% | Actual: | 30.17%
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2020-01-09 |  | 2018 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./COMPL./IMPV'T. OF VARIOUS GOV'T. BLDGS., STRUCTURES & FACILITIES (Const. in Progress - Bldgs. & Other Structures | [7 empty] | Duration: | 180 | No. of days extended: | 69 |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 9.68% | Slippage: | 9.68% | Slippage: | -9.88%
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2020-01-09 |  | 2018 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./COMPL./IMPV'T. OF VARIOUS GOV'T. BLDGS., STRUCTURES & FACILITIES (Const. in Progress - Bldgs. & Other Structures | [7 empty] | Date Allotment Released: |  | Date completed:
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2020-01-09 |  | 2018 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CONST./COMPL./IMPV'T. OF VARIOUS GOV'T. BLDGS., STRUCTURES & FACILITIES (Const. in Progress - Bldgs. & Other Structures | [7 empty] | Date Started: | 2020-01-09
Panabo City | Dalisay | 2nd Eng'g. Dist. | For Implementation |  |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Local Roads and Drainage Development Project Construction in Progress- Infrastructure Assets | Rehabilitation of Local Roads at Dalisay-Manay Road Section, Panabo City |  | SB # 4 CY 2019 | Road |  |  | Admin | Project Cost: | 246100 | Target Completion Date: |  | Program: | 246100 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | For implementation | For implementation | For implementation | For implementation | For implementation | For implementation
Panabo City | Dalisay | 2nd Eng'g. Dist. | For Implementation |  |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Local Roads and Drainage Development Project Construction in Progress- Infrastructure Assets | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 246100 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
Panabo City | Dalisay | 2nd Eng'g. Dist. | For Implementation |  |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Local Roads and Drainage Development Project Construction in Progress- Infrastructure Assets | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
Panabo City | Dalisay | 2nd Eng'g. Dist. | For Implementation |  |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Local Roads and Drainage Development Project Construction in Progress- Infrastructure Assets | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Panabo City | Dalisay | 2nd Eng'g. Dist. | For Implementation |  |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Local Roads and Drainage Development Project Construction in Progress- Infrastructure Assets | [7 empty] | Date Allotment Released: |  | Date completed:
Panabo City | Dalisay | 2nd Eng'g. Dist. | For Implementation |  |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Local Roads and Drainage Development Project Construction in Progress- Infrastructure Assets | [7 empty] | Date Started:
Asuncion | Canatan-Doña Andrea | 1st Eng'g. Dist. | On-going | 2020-06-16 |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Rehabilitation Of Various Prov'l. Roads and Bridges | Jct. Highway Canatan - Doña Andrea |  | 20% DF CY 2019 | Road Rehabilitation | 4.34 | km | Admin | Project Cost: | 2000000 | Target Completion Date: | 2020-08-11 23:46 | Program: | 2000000 | Planned: | 60% | Planned: | 75% | Planned: | 75% | Planned: | 75% | Planned: | 75% | No. of Persons: |  | On-going | On-going | On-going | On-going | On-going | On-going
Asuncion | Canatan-Doña Andrea | 1st Eng'g. Dist. | On-going | 2020-06-16 |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Rehabilitation Of Various Prov'l. Roads and Bridges | [7 empty] | Project Engineer: | Pilotos | Revised Completion Date: | 2020-08-11 23:46 | Allotment: | 2000000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
Asuncion | Canatan-Doña Andrea | 1st Eng'g. Dist. | On-going | 2020-06-16 |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Rehabilitation Of Various Prov'l. Roads and Bridges | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: | 1200000 | Actual: | 60% | Actual: | 75% | Actual: | 75% | Actual: | 75% | Actual: | 75%
Asuncion | Canatan-Doña Andrea | 1st Eng'g. Dist. | On-going | 2020-06-16 |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Rehabilitation Of Various Prov'l. Roads and Bridges | [7 empty] | Duration: | 57 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Asuncion | Canatan-Doña Andrea | 1st Eng'g. Dist. | On-going | 2020-06-16 |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Rehabilitation Of Various Prov'l. Roads and Bridges | [7 empty] | Date Allotment Released: | 2019-06-12 | Date completed:
Asuncion | Canatan-Doña Andrea | 1st Eng'g. Dist. | On-going | 2020-06-16 |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Rehabilitation Of Various Prov'l. Roads and Bridges | [7 empty] | Date Started: | 2020-06-16
Asuncion | Pamacaun | 1st Eng'g. Dist. | Suspended | 2020-08-19 |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Rehabilitation Of Various Prov'l. Roads and Bridges | Pamacaun - Lasang Banate |  | 20% DF CY 2019 | Road Rehabilitation | 4.34 |  | Admin | Project Cost: | 2000000 | Target Completion Date: | 2020-11-10 23:46 | Program: | 2000000 | Planned: |  | Planned: | 52.32% | Planned: |  | Planned: |  | Planned: | 52.32% | No. of Persons: |  | For implementation (Waiting for the delivery of geo-grid materials. An approved request letter dated Dec. 3, 2019 for the extension of 50 days from Provincial Administrator Engr. Rabanoz is on file | Suspended due to continous rain. Waiting for the stability of swamp area. | Suspended due to continous rain. Waiting for the stability of swamp area. | Suspended due to continous rain. Waiting for the stability of swamp area. | Suspended due to continous rain. Waiting for the stability of swamp area. | Suspended Oct.5, 2020
Asuncion | Pamacaun | 1st Eng'g. Dist. | Suspended | 2020-08-19 |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Rehabilitation Of Various Prov'l. Roads and Bridges | [7 empty] | Project Engineer: | Gone | Revised Completion Date: | 2020-11-10 23:46 | Allotment: | 2000000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
Asuncion | Pamacaun | 1st Eng'g. Dist. | Suspended | 2020-08-19 |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Rehabilitation Of Various Prov'l. Roads and Bridges | [7 empty] | Implementor: | Admin | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: | 52.32% | Actual: |  | Actual: |  | Actual: | 52.32%
Asuncion | Pamacaun | 1st Eng'g. Dist. | Suspended | 2020-08-19 |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Rehabilitation Of Various Prov'l. Roads and Bridges | [7 empty] | Duration: | 84 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Asuncion | Pamacaun | 1st Eng'g. Dist. | Suspended | 2020-08-19 |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Rehabilitation Of Various Prov'l. Roads and Bridges | [7 empty] | Date Allotment Released: | 2019-06-27 | Date completed:
Asuncion | Pamacaun | 1st Eng'g. Dist. | Suspended | 2020-08-19 |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Rehabilitation Of Various Prov'l. Roads and Bridges | [7 empty] | Date Started: | 2020-08-19
Kapalong | Mabantao-Florida | 1st Eng'g. Dist. | Completed | 2019-10-01 | 2020-01-15 | 2019 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Rehabilitation Of Various Prov'l. Roads and Bridges | Kapalong - Mabantao - Florida |  | 20% DF CY 2019 | Road Rehabilitation | 4.34 |  | Admin | Project Cost: | 1231000 | Target Completion Date: | 2020-01-15 23:46 | Program: | 1231000 | Planned: |  | Planned: | 52.32% | Planned: |  | Planned: |  | Planned: | 100% | No. of Persons: |  | For implementation (Waiting for the delivery of geo-grid materials. An approved request letter dated Dec. 3, 2019 for the extension of 50 days from Provincial Administrator Engr. Rabanoz is on file | Suspended due to continous rain. Waiting for the stability of swamp area. | Suspended due to continous rain. Waiting for the stability of swamp area. | Completed as per physical accomplishment. | Completed as per physical accomplishment. | Completed as per Program of Works
Kapalong | Mabantao-Florida | 1st Eng'g. Dist. | Completed | 2019-10-01 | 2020-01-15 | 2019 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Rehabilitation Of Various Prov'l. Roads and Bridges | [7 empty] | Project Engineer: | Gone | Revised Completion Date: |  | Allotment: | 1231000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
Kapalong | Mabantao-Florida | 1st Eng'g. Dist. | Completed | 2019-10-01 | 2020-01-15 | 2019 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Rehabilitation Of Various Prov'l. Roads and Bridges | [7 empty] | Implementor: | Admin | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: | 52.32% | Actual: |  | Actual: |  | Actual: | 100%
Kapalong | Mabantao-Florida | 1st Eng'g. Dist. | Completed | 2019-10-01 | 2020-01-15 | 2019 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Rehabilitation Of Various Prov'l. Roads and Bridges | [7 empty] | Duration: | 107 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage:
Kapalong | Mabantao-Florida | 1st Eng'g. Dist. | Completed | 2019-10-01 | 2020-01-15 | 2019 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Rehabilitation Of Various Prov'l. Roads and Bridges | [7 empty] | Date Allotment Released: | 2019-06-27 | Date completed: | 2020-01-15
Kapalong | Mabantao-Florida | 1st Eng'g. Dist. | Completed | 2019-10-01 | 2020-01-15 | 2019 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Rehabilitation Of Various Prov'l. Roads and Bridges | [7 empty] | Date Started: | 2019-10-01
Kapalong | Semong | 1st Eng'g. Dist. |  |  |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Rehabilitation Of Various Prov'l. Roads and Bridges | Jct. Highway Gabuyan - Semong - Dagohoy |  | 20% DF CY 2019 | Road Rehabilitation | 4.34 |  | Admin | Project Cost: | 2492000 | Target Completion Date: |  | Program: | 2492000 | Planned: |  | Planned: | 52.32% | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | For implementation (Waiting for the delivery of geo-grid materials. An approved request letter dated Dec. 3, 2019 for the extension of 50 days from Provincial Administrator Engr. Rabanoz is on file | Suspended due to continous rain. Waiting for the stability of swamp area. | Suspended due to continous rain. Waiting for the stability of swamp area. |  |  | For implementation
Kapalong | Semong | 1st Eng'g. Dist. |  |  |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Rehabilitation Of Various Prov'l. Roads and Bridges | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 2492000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
Kapalong | Semong | 1st Eng'g. Dist. |  |  |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Rehabilitation Of Various Prov'l. Roads and Bridges | [7 empty] | Implementor: | Admin | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: | 52.32% | Actual: |  | Actual: |  | Actual:
Kapalong | Semong | 1st Eng'g. Dist. |  |  |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Rehabilitation Of Various Prov'l. Roads and Bridges | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Kapalong | Semong | 1st Eng'g. Dist. |  |  |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Rehabilitation Of Various Prov'l. Roads and Bridges | [7 empty] | Date Allotment Released: |  | Date completed:
Kapalong | Semong | 1st Eng'g. Dist. |  |  |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Rehabilitation Of Various Prov'l. Roads and Bridges | [7 empty] | Date Started:
Talaingod | Sto.Niño-Palma Gil | 1st Eng'g. Dist. | Completed | 2020-03-06 | 2020-07-06 | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Rehabilitation Of Various Prov'l. Roads and Bridges | Sto. Niño - Palma Gil - Sitio Opao |  | 20% DF CY 2019 | Road Rehabilitation | 11.6 | km | Contract | Project Cost: | 1901000 | Target Completion Date: | 2020-04-18 23:46 | Program: | 1901000 | Planned: | 100% | Planned: | 100% | Planned: | 100% | Planned: | 100% | Planned: | 100% | No. of Persons: |  | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per Program of Works
Talaingod | Sto.Niño-Palma Gil | 1st Eng'g. Dist. | Completed | 2020-03-06 | 2020-07-06 | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Rehabilitation Of Various Prov'l. Roads and Bridges | [7 empty] | Project Engineer: | Lumapat | Revised Completion Date: | 2020-06-29 23:46 | Allotment: | 1901000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
Talaingod | Sto.Niño-Palma Gil | 1st Eng'g. Dist. | Completed | 2020-03-06 | 2020-07-06 | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Rehabilitation Of Various Prov'l. Roads and Bridges | [7 empty] | Implementor: | Tagum Constrak | No. of days suspended: | 72 | Disbursement: | 1901000 | Actual: | 100% | Actual: | 100% | Actual: | 100% | Actual: | 100% | Actual: | 100%
Talaingod | Sto.Niño-Palma Gil | 1st Eng'g. Dist. | Completed | 2020-03-06 | 2020-07-06 | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Rehabilitation Of Various Prov'l. Roads and Bridges | [7 empty] | Duration: | 44 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Talaingod | Sto.Niño-Palma Gil | 1st Eng'g. Dist. | Completed | 2020-03-06 | 2020-07-06 | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Rehabilitation Of Various Prov'l. Roads and Bridges | [7 empty] | Date Allotment Released: | 2019-06-19 | Date completed: | 2020-07-13
Talaingod | Sto.Niño-Palma Gil | 1st Eng'g. Dist. | Completed | 2020-03-06 | 2020-07-06 | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Rehabilitation Of Various Prov'l. Roads and Bridges | [7 empty] | Date Started: | 2020-03-06
Talaingod | Sto. Niño-Daligdigon-Paiton | 1st Eng'g. Dist. | On-going | 2020-01-16 | 2020-06-30 | 2019 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Rehabilitation Of Various Prov'l. Roads and Bridges | Sto. Niño - Daligdigon - Paiton |  | 20% DF CY 2019 | Road Rehabilitation | 11.6 | km | Contract | Project Cost: | 3000000 | Target Completion Date: | 2020-05-14 23:46 | Program: | 3000000 | Planned: | 66% | Planned: | 71% | Planned: | 75.29% | Planned: | 75.29% | Planned: | 100% | No. of Persons: | 7 | On-going; Resumption Order dated May 4, 2020 | On-going; Resumption Order dated May 4, 2020 | On-going; Resumption Order dated May 4, 2020 | On-going; Resumption Order dated May 4, 2020 | On-going; Resumption Order dated May 4, 2020 | Completed as per Program of Works
Talaingod | Sto. Niño-Daligdigon-Paiton | 1st Eng'g. Dist. | On-going | 2020-01-16 | 2020-06-30 | 2019 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Rehabilitation Of Various Prov'l. Roads and Bridges | [7 empty] | Project Engineer: | Lumapat | Revised Completion Date: | 2020-06-11 23:46 | Allotment: | 3000000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 217
Talaingod | Sto. Niño-Daligdigon-Paiton | 1st Eng'g. Dist. | On-going | 2020-01-16 | 2020-06-30 | 2019 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Rehabilitation Of Various Prov'l. Roads and Bridges | [7 empty] | Implementor: | PEO | No. of days suspended: | 28 | Disbursement: | 1980000 | Actual: | 66% | Actual: | 71% | Actual: | 75.29% | Actual: | 75.29% | Actual: | 100%
Talaingod | Sto. Niño-Daligdigon-Paiton | 1st Eng'g. Dist. | On-going | 2020-01-16 | 2020-06-30 | 2019 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Rehabilitation Of Various Prov'l. Roads and Bridges | [7 empty] | Duration: | 120 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Talaingod | Sto. Niño-Daligdigon-Paiton | 1st Eng'g. Dist. | On-going | 2020-01-16 | 2020-06-30 | 2019 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Rehabilitation Of Various Prov'l. Roads and Bridges | [7 empty] | Date Allotment Released: | 2019-10-03 | Date completed: | 2020-06-30
Talaingod | Sto. Niño-Daligdigon-Paiton | 1st Eng'g. Dist. | On-going | 2020-01-16 | 2020-06-30 | 2019 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Rehabilitation Of Various Prov'l. Roads and Bridges | [7 empty] | Date Started: | 2020-01-16
Talaingod | Jct. Paiton-Mibolo | 1st Eng'g. Dist. | On-going | 2019-08-01 |  | 2019 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Rehabilitation Of Various Prov'l. Roads and Bridges | Jct. Paiton - Mibolo |  | 20% DF CY 2019 | Road Rehabilitation | 23.9 | km | Contract | Project Cost: | 6000000 | Target Completion Date: | 2020-10-05 23:46 | Program: | 6000000 | Planned: | 21.05% | Planned: | 21.05% | Planned: | 34.1% | Planned: | 34.1% | Planned: | 100% | No. of Persons: | 14 | Temporary suspended because the materials for the box culvert procurement on process wth PO # 2019061674 | Temporary suspended because the materials for the box culvert procurement on process wth PO # 2019061674 | On-going | On-going | On-going | On-going
Talaingod | Jct. Paiton-Mibolo | 1st Eng'g. Dist. | On-going | 2019-08-01 |  | 2019 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Rehabilitation Of Various Prov'l. Roads and Bridges | [7 empty] | Project Engineer: | Lumapat | Revised Completion Date: | 2020-12-27 23:46 | Allotment: | 6000000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: | 56.28% | No. of Man-days: | 434
Talaingod | Jct. Paiton-Mibolo | 1st Eng'g. Dist. | On-going | 2019-08-01 |  | 2019 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Rehabilitation Of Various Prov'l. Roads and Bridges | [7 empty] | Implementor: | PEO | No. of days suspended: | 83 | Disbursement: | 1263000 | Actual: | 21.05% | Actual: | 21.05% | Actual: | 31.25% | Actual: | 31.25% | Actual: | 56.28%
Talaingod | Jct. Paiton-Mibolo | 1st Eng'g. Dist. | On-going | 2019-08-01 |  | 2019 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Rehabilitation Of Various Prov'l. Roads and Bridges | [7 empty] | Duration: | 218 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | -2.85% | Slippage: | -2.85% | Slippage: | 0%
Talaingod | Jct. Paiton-Mibolo | 1st Eng'g. Dist. | On-going | 2019-08-01 |  | 2019 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Rehabilitation Of Various Prov'l. Roads and Bridges | [7 empty] | Date Allotment Released: | 2019-03-25 | Date completed:
Talaingod | Jct. Paiton-Mibolo | 1st Eng'g. Dist. | On-going | 2019-08-01 |  | 2019 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Rehabilitation Of Various Prov'l. Roads and Bridges | [7 empty] | Date Started: | 2020-03-02
Talaingod | Monte Dujali-Gupitan | 1st Eng'g. Dist. | Completed | 2020-01-31 | 2020-06-30 | 2019 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Rehabilitation Of Various Prov'l. Roads and Bridges | Monte Dujali - Gupitan |  | 20% DF CY 2019 | Road Rehabilitation | 4.58 | km | Admin | Project Cost: | 1200000 | Target Completion Date: | 2020-03-31 23:46 | Program: | 1200000 | Planned: | 100% | Planned: | 100% | Planned: | 100% | Planned: | 100% | Planned: | 100% | No. of Persons: | 10 | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per Program of Works
Talaingod | Monte Dujali-Gupitan | 1st Eng'g. Dist. | Completed | 2020-01-31 | 2020-06-30 | 2019 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Rehabilitation Of Various Prov'l. Roads and Bridges | [7 empty] | Project Engineer: | Bacaron | Revised Completion Date: | 2020-06-30 23:46 | Allotment: | 1200000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 240
Talaingod | Monte Dujali-Gupitan | 1st Eng'g. Dist. | Completed | 2020-01-31 | 2020-06-30 | 2019 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Rehabilitation Of Various Prov'l. Roads and Bridges | [7 empty] | Implementor: | PEO | No. of days suspended: | 30 | Disbursement: | 1200000 | Actual: | 100% | Actual: | 100% | Actual: | 100% | Actual: | 100% | Actual: | 100%
Talaingod | Monte Dujali-Gupitan | 1st Eng'g. Dist. | Completed | 2020-01-31 | 2020-06-30 | 2019 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Rehabilitation Of Various Prov'l. Roads and Bridges | [7 empty] | Duration: | 61 | No. of days extended: | 61 |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Talaingod | Monte Dujali-Gupitan | 1st Eng'g. Dist. | Completed | 2020-01-31 | 2020-06-30 | 2019 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Rehabilitation Of Various Prov'l. Roads and Bridges | [7 empty] | Date Allotment Released: | 2019-12-06 | Date completed: | 2020-06-30
Talaingod | Monte Dujali-Gupitan | 1st Eng'g. Dist. | Completed | 2020-01-31 | 2020-06-30 | 2019 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Rehabilitation Of Various Prov'l. Roads and Bridges | [7 empty] | Date Started: | 2020-01-31
San Isidro | Sawata | 1st Eng'g. Dist. | Completed | 2020-02-03 | 2020-03-31 | 2019 | Administration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation Of Various Prov'l. Roads and Bridges | Jct. Sawata - Bdry. Binasbas |  | 20% DF CY 2019 | Maintenance | 0.46 | km | Admin | Project Cost: | 500000 | Target Completion Date: | 2020-03-31 | Program: | 500000 | Planned: | 16.23% | Planned: | 30.75% | Planned: | 63.48% | Planned: | 100% | Planned: | 100% | No. of Persons: | 10 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per Program of Works
San Isidro | Sawata | 1st Eng'g. Dist. | Completed | 2020-02-03 | 2020-03-31 | 2019 | Administration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation Of Various Prov'l. Roads and Bridges | [7 empty] | Project Engineer: | Crucio | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 240
San Isidro | Sawata | 1st Eng'g. Dist. | Completed | 2020-02-03 | 2020-03-31 | 2019 | Administration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation Of Various Prov'l. Roads and Bridges | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: | 16.23% | Actual: | 30.75% | Actual: | 63.48% | Actual: | 100% | Actual: | 100%
San Isidro | Sawata | 1st Eng'g. Dist. | Completed | 2020-02-03 | 2020-03-31 | 2019 | Administration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation Of Various Prov'l. Roads and Bridges | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
San Isidro | Sawata | 1st Eng'g. Dist. | Completed | 2020-02-03 | 2020-03-31 | 2019 | Administration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation Of Various Prov'l. Roads and Bridges | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed: | 2020-03-31
San Isidro | Sawata | 1st Eng'g. Dist. | Completed | 2020-02-03 | 2020-03-31 | 2019 | Administration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation Of Various Prov'l. Roads and Bridges | [7 empty] | Date Started: | 2020-02-03
New Corella | Saug | 1st Eng'g. Dist. | Completed | 2019-03-26 | 2020-06-30 | 2019 | Administartion | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES | New Corella - Saug |  | 20% DF CY 2019 | Road Rehabilitation | 12.52 | km | Contract | Project Cost: | 6500000 | Target Completion Date: | 2019-03-26 | Program: | 6500000 | Planned: | 100% | Planned: | 100% | Planned: | 100% | Planned: | 100% | Planned: | 100% | No. of Persons: | 19 | Completed as per physical accomplishment. Financial documents still on process | Completed as per physical accomplishment. Financial documents still on process | Completed as per physical accomplishment. Financial documents still on process | Completed as per physical accomplishment. Financial documents still on process | Completed as per physical accomplishment. Financial documents still on process | Completed as per Program of Works
New Corella | Saug | 1st Eng'g. Dist. | Completed | 2019-03-26 | 2020-06-30 | 2019 | Administartion | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES | [7 empty] | Project Engineer: | Pilotos | Revised Completion Date: | 2019-06-10 | Allotment: | 6500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 570
New Corella | Saug | 1st Eng'g. Dist. | Completed | 2019-03-26 | 2020-06-30 | 2019 | Administartion | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES | [7 empty] | Implementor: | PEO | No. of days suspended: | 28 | Disbursement: | 6500000 | Actual: | 100% | Actual: | 100% | Actual: | 100% | Actual: | 100% | Actual: | 100%
New Corella | Saug | 1st Eng'g. Dist. | Completed | 2019-03-26 | 2020-06-30 | 2019 | Administartion | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES | [7 empty] | Duration: |  | No. of days extended: | 48 |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
New Corella | Saug | 1st Eng'g. Dist. | Completed | 2019-03-26 | 2020-06-30 | 2019 | Administartion | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES | [7 empty] | Date Allotment Released: |  | Date completed: | 2020-06-30
New Corella | Saug | 1st Eng'g. Dist. | Completed | 2019-03-26 | 2020-06-30 | 2019 | Administartion | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES | [7 empty] | Date Started: | 2019-03-26
Asuncion | Cabaywa | 1st Eng'g. Dist. | Completed | 2019-03-26 | 2020-06-30 | 2019 | Administartion | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES | Jct. Monte Carlo - Upper Cabaywa - Canatan |  | 20% DF CY 2019 | Road Rehabilitation | 4.61 | km | Contract | Project Cost: | 8838000 | Target Completion Date: | 2019-03-26 | Program: | 8838000 | Planned: | 100% | Planned: | 100% | Planned: | 100% | Planned: | 100% | Planned: | 100% | No. of Persons: | 19 | Completed as per physical accomplishment. Financial documents still on process | Completed as per physical accomplishment. Financial documents still on process | Completed as per physical accomplishment. Financial documents still on process | Completed as per physical accomplishment. Financial documents still on process | Completed as per physical accomplishment. Financial documents still on process | Completed as per Program of Works
Asuncion | Cabaywa | 1st Eng'g. Dist. | Completed | 2019-03-26 | 2020-06-30 | 2019 | Administartion | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES | [7 empty] | Project Engineer: | Garcia | Revised Completion Date: | 2019-03-26 | Allotment: | 8838000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 570
Asuncion | Cabaywa | 1st Eng'g. Dist. | Completed | 2019-03-26 | 2020-06-30 | 2019 | Administartion | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES | [7 empty] | Implementor: | PEO | No. of days suspended: | 28 | Disbursement: | 8838000 | Actual: | 100% | Actual: | 100% | Actual: | 100% | Actual: | 100% | Actual: | 100%
Asuncion | Cabaywa | 1st Eng'g. Dist. | Completed | 2019-03-26 | 2020-06-30 | 2019 | Administartion | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Asuncion | Cabaywa | 1st Eng'g. Dist. | Completed | 2019-03-26 | 2020-06-30 | 2019 | Administartion | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES | [7 empty] | Date Allotment Released: | 2019-01-31 | Date completed: | 2020-06-30
Asuncion | Cabaywa | 1st Eng'g. Dist. | Completed | 2019-03-26 | 2020-06-30 | 2019 | Administartion | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES | [7 empty] | Date Started: | 2019-03-26
Carmen | Cebulano | 2nd Eng'g. Dist. | Completed | 2019-05-21 | 2020-05-31 | 2019 | Administartion | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Rehabilitation Of Various Prov'l. Roads and Bridges | Jct. Highway Sto. Niño - Cebulano |  | 20% DF CY 2019 | Road Rehabilitation | 2.09 | km | Admin | Project Cost: | 1045000 | Target Completion Date: | 2019-10-04 | Program: | 1045000 | Planned: | 100% | Planned: | 100% | Planned: | 100% | Planned: | 100% | Planned: | 100% | No. of Persons: | 6 | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. (Furtherance on-going) | Completed as per physical accomplishment. Financial documents still on process. (Furtherance on-going) | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per Program of Works
Carmen | Cebulano | 2nd Eng'g. Dist. | Completed | 2019-05-21 | 2020-05-31 | 2019 | Administartion | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Rehabilitation Of Various Prov'l. Roads and Bridges | [7 empty] | Project Engineer: | Obar/ Nasol | Revised Completion Date: | 2020-06-15 | Allotment: | 1045000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 132
Carmen | Cebulano | 2nd Eng'g. Dist. | Completed | 2019-05-21 | 2020-05-31 | 2019 | Administartion | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Rehabilitation Of Various Prov'l. Roads and Bridges | [7 empty] | Implementor: | PEO | No. of days suspended: | 194 | Disbursement: | 1045000 | Actual: | 100% | Actual: | 100% | Actual: | 100% | Actual: | 100% | Actual: | 100%
Carmen | Cebulano | 2nd Eng'g. Dist. | Completed | 2019-05-21 | 2020-05-31 | 2019 | Administartion | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Rehabilitation Of Various Prov'l. Roads and Bridges | [7 empty] | Duration: | 136 | No. of days extended: | 61 |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Carmen | Cebulano | 2nd Eng'g. Dist. | Completed | 2019-05-21 | 2020-05-31 | 2019 | Administartion | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Rehabilitation Of Various Prov'l. Roads and Bridges | [7 empty] | Date Allotment Released: | 2019-01-03 | Date completed: | 2020-05-31
Carmen | Cebulano | 2nd Eng'g. Dist. | Completed | 2019-05-21 | 2020-05-31 | 2019 | Administartion | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Rehabilitation Of Various Prov'l. Roads and Bridges | [7 empty] | Date Started: | 2019-05-21
Carmen | Tubod | 2nd Eng'g. Dist. | Completed | 2019-11-11 | 2020-06-30 | 2019 | Administartion | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | ROAD ID 076 - Basa - Tubod |  | 20% DF CY 2019 | Road Rehabilitation | 1.56 | km | Admin | Project Cost: | 1000000 | Target Completion Date: | 2020-03-19 23:59 | Program: | 1000000 | Planned: | 100% | Planned: | 100% | Planned: | 100% | Planned: | 100% | Planned: | 100% | No. of Persons: | 3 | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. |  |  | Completed as per Program of Works
Carmen | Tubod | 2nd Eng'g. Dist. | Completed | 2019-11-11 | 2020-06-30 | 2019 | Administartion | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | [7 empty] | Project Engineer: | PIAD | Revised Completion Date: | 2020-06-30 23:59 | Allotment: | 1000000 | Revised: | 100% | Revised: | 100% | Revised: | 100% | Revised: | 100% | Revised: |  | No. of Man-days: | 30
Carmen | Tubod | 2nd Eng'g. Dist. | Completed | 2019-11-11 | 2020-06-30 | 2019 | Administartion | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | [7 empty] | Implementor: | PEO | No. of days suspended: | 103 | Disbursement: |  | Actual: | 100% | Actual: | 100% | Actual: | 100% | Actual: | 100% | Actual: | 100%
Carmen | Tubod | 2nd Eng'g. Dist. | Completed | 2019-11-11 | 2020-06-30 | 2019 | Administartion | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | [7 empty] | Duration: | 130 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Carmen | Tubod | 2nd Eng'g. Dist. | Completed | 2019-11-11 | 2020-06-30 | 2019 | Administartion | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | [7 empty] | Date Allotment Released: | 2019-01-03 | Date completed: | 2020-06-30 23:59
Carmen | Tubod | 2nd Eng'g. Dist. | Completed | 2019-11-11 | 2020-06-30 | 2019 | Administartion | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | [7 empty] | Date Started: | 2019-11-11
Carmen | Tubod | 2nd Eng'g. Dist. | On-going | 2019-12-18 |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | ROAD ID 077 - Tubod - Pilar |  | 20% DF CY 2019 | Road Rehabilitation | 1.55 | km | Admin | Project Cost: | 16000000 | Target Completion Date: | 2020-11-05 | Program: | 16000000 | Planned: | 62.5% | Planned: | 69.85% | Planned: | 69.85% | Planned: | 69.85% | Planned: | 100% | No. of Persons: | 18 | On-going | On-going | On-going |  |  | On-going
Carmen | Tubod | 2nd Eng'g. Dist. | On-going | 2019-12-18 |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | [7 empty] | Project Engineer: | Agang | Revised Completion Date: |  | Allotment: | 16000000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 396
Carmen | Tubod | 2nd Eng'g. Dist. | On-going | 2019-12-18 |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: | 4046971.2 | Actual: | 58.23% | Actual: | 71.98% | Actual: | 71.98% | Actual: | 71.98% | Actual: | 78.08%
Carmen | Tubod | 2nd Eng'g. Dist. | On-going | 2019-12-18 |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | [7 empty] | Duration: | 323 | No. of days extended: |  |  |  | Slippage: | -4.27% | Slippage: | 2.13% | Slippage: | 2.13% | Slippage: | 2.13% | Slippage: | -21.92%
Carmen | Tubod | 2nd Eng'g. Dist. | On-going | 2019-12-18 |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | [7 empty] | Date Allotment Released: | 2019-11-26 | Date completed:
Carmen | Tubod | 2nd Eng'g. Dist. | On-going | 2019-12-18 |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Maintenance of Various Provincial Roads and Bridges at District LS - 46,740,177.00; road lenght - 115.620 km | [7 empty] | Date Started: | 2019-12-18
Carmen | Mabuhay | 2nd Eng'g. Dist. | Completed | 2019-06-17 | 2020-02-29 | 2019 | Administartion | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Rehabilitation Of Various Prov'l. Roads and Bridges | Dalisay - Mabuhay |  | 20% DF CY 2019 | Road Rehabilitation | 2.09 | km | Admin | Project Cost: | 1000000 | Target Completion Date: | 2020-02-29 | Program: | 1000000 | Planned: | 100% | Planned: | 100% | Planned: | 100% | Planned: | 100% | Planned: | 100% | No. of Persons: | 6 | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. (Furtherance on-going) | Completed as per physical accomplishment. Financial documents still on process. (Furtherance on-going) | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per Program of Works
Carmen | Mabuhay | 2nd Eng'g. Dist. | Completed | 2019-06-17 | 2020-02-29 | 2019 | Administartion | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Rehabilitation Of Various Prov'l. Roads and Bridges | [7 empty] | Project Engineer: | Obar/ Nasol | Revised Completion Date: |  | Allotment: | 1000000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 132
Carmen | Mabuhay | 2nd Eng'g. Dist. | Completed | 2019-06-17 | 2020-02-29 | 2019 | Administartion | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Rehabilitation Of Various Prov'l. Roads and Bridges | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: | 1000000 | Actual: | 100% | Actual: | 100% | Actual: | 100% | Actual: | 100% | Actual: | 100%
Carmen | Mabuhay | 2nd Eng'g. Dist. | Completed | 2019-06-17 | 2020-02-29 | 2019 | Administartion | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Rehabilitation Of Various Prov'l. Roads and Bridges | [7 empty] | Duration: | 257 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Carmen | Mabuhay | 2nd Eng'g. Dist. | Completed | 2019-06-17 | 2020-02-29 | 2019 | Administartion | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Rehabilitation Of Various Prov'l. Roads and Bridges | [7 empty] | Date Allotment Released: | 2019-01-03 | Date completed: | 2020-02-29
Carmen | Mabuhay | 2nd Eng'g. Dist. | Completed | 2019-06-17 | 2020-02-29 | 2019 | Administartion | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Rehabilitation Of Various Prov'l. Roads and Bridges | [7 empty] | Date Started: | 2019-06-17
Carmen | Tibulao | 2nd Eng'g. Dist. | Completed | 2019-05-15 | 2020-07-31 | 2019 | Administartion | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Rehabilitation Of Various Prov'l. Roads and Bridges | Sitio Malaga - Tibulao |  | 20% DF CY 2019 | Road Rehabilitation | 3.22 | km | Admin | Project Cost: | 1000000 | Target Completion Date: | 2019-09-27 23:46 | Program: | 1000000 | Planned: | 78.5% | Planned: | 78.5% | Planned: | 78.5% | Planned: | 78.5% | Planned: | 100% | No. of Persons: | 5 | On-going | On-going | On-going | On-going | On-going | Completed as per Program of Works
Carmen | Tibulao | 2nd Eng'g. Dist. | Completed | 2019-05-15 | 2020-07-31 | 2019 | Administartion | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Rehabilitation Of Various Prov'l. Roads and Bridges | [7 empty] | Project Engineer: | Obar | Revised Completion Date: |  | Allotment: | 1000000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 110
Carmen | Tibulao | 2nd Eng'g. Dist. | Completed | 2019-05-15 | 2020-07-31 | 2019 | Administartion | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Rehabilitation Of Various Prov'l. Roads and Bridges | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: | 54.8% | Actual: | 54.8% | Actual: | 54.8% | Actual: | 54.8% | Actual: | 100%
Carmen | Tibulao | 2nd Eng'g. Dist. | Completed | 2019-05-15 | 2020-07-31 | 2019 | Administartion | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Rehabilitation Of Various Prov'l. Roads and Bridges | [7 empty] | Duration: | 136 | No. of days extended: |  |  |  | Slippage: | -23.7% | Slippage: | -23.7% | Slippage: | -23.7% | Slippage: | -23.7% | Slippage: | 0%
Carmen | Tibulao | 2nd Eng'g. Dist. | Completed | 2019-05-15 | 2020-07-31 | 2019 | Administartion | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Rehabilitation Of Various Prov'l. Roads and Bridges | [7 empty] | Date Allotment Released: | 2019-01-03 | Date completed: | 2020-07-31
Carmen | Tibulao | 2nd Eng'g. Dist. | Completed | 2019-05-15 | 2020-07-31 | 2019 | Administartion | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Rehabilitation Of Various Prov'l. Roads and Bridges | [7 empty] | Date Started: | 2019-05-15
B.E. Dujali | Tanglaw | 2nd Eng'g. Dist. | Completed | 2019-12-28 | 2020-07-31 | 2019 | Administartion | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Rehabilitation Of Various Prov'l. Roads and Bridges | Dujali - Tanglaw |  | 20% DF CY 2019 | Road Rehabilitation | 3.6 | km | Admin | Project Cost: | 2075000 | Target Completion Date: | 2020-04-16 | Program: | 2075000 | Planned: | 60% | Planned: | 60% | Planned: | 60% | Planned: | 60% | Planned: | 100% | No. of Persons: | 6 | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. (Furtherance on-going) | Completed as per physical accomplishment. Financial documents still on process. (Furtherance on-going) | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per Program of Works
B.E. Dujali | Tanglaw | 2nd Eng'g. Dist. | Completed | 2019-12-28 | 2020-07-31 | 2019 | Administartion | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Rehabilitation Of Various Prov'l. Roads and Bridges | [7 empty] | Project Engineer: | Balbastro | Revised Completion Date: | 2020-08-30 | Allotment: | 2075000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 132
B.E. Dujali | Tanglaw | 2nd Eng'g. Dist. | Completed | 2019-12-28 | 2020-07-31 | 2019 | Administartion | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Rehabilitation Of Various Prov'l. Roads and Bridges | [7 empty] | Implementor: | PEO | No. of days suspended: | 28 | Disbursement: |  | Actual: | 65% | Actual: | 65% | Actual: | 65% | Actual: | 65% | Actual: | 100%
B.E. Dujali | Tanglaw | 2nd Eng'g. Dist. | Completed | 2019-12-28 | 2020-07-31 | 2019 | Administartion | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Rehabilitation Of Various Prov'l. Roads and Bridges | [7 empty] | Duration: | 110 | No. of days extended: | 108 |  |  | Slippage: | 5% | Slippage: | 5% | Slippage: | 5% | Slippage: | 5% | Slippage: | 0%
B.E. Dujali | Tanglaw | 2nd Eng'g. Dist. | Completed | 2019-12-28 | 2020-07-31 | 2019 | Administartion | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Rehabilitation Of Various Prov'l. Roads and Bridges | [7 empty] | Date Allotment Released: | 2019-01-03 | Date completed: | 2020-07-31
B.E. Dujali | Tanglaw | 2nd Eng'g. Dist. | Completed | 2019-12-28 | 2020-07-31 | 2019 | Administartion | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Rehabilitation Of Various Prov'l. Roads and Bridges | [7 empty] | Date Started: | 2019-12-28
Sto. Tomas | Esperanza | 2nd Eng'g. Dist. | Completed | 2019-07-17 | 2020-02-15 | 2019 | Administartion | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Rehabilitation Of Various Prov'l. Roads and Bridges | Cabay-angan Esperanza |  | 20% DF CY 2020 | Road Rehabilitation |  |  | MBA | Project Cost: | 1300000 | Target Completion Date: | 2019-09-30 | Program: | 1300000 | Planned: | 2.1% | No. of Persons: | 0 | Suspended June 13, 2020 due to unavailability of heavy equipment |  | Planned: | 100% | Planned: | 100% | No. of Persons: | 6 | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. (Furtherance on-going) | Completed as per physical accomplishment. Financial documents still on process. (Furtherance on-going) | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per Program of Works
Sto. Tomas | Esperanza | 2nd Eng'g. Dist. | Completed | 2019-07-17 | 2020-02-15 | 2019 | Administartion | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Rehabilitation Of Various Prov'l. Roads and Bridges | [7 empty] | Project Engineer: | Obar | Revised Completion Date: | 2020-02-15 | Allotment: | 1300000 | Revised: |  | No. of Man-days: | 0 |  |  | Revised: |  | Revised: |  | No. of Man-days: | 132
Sto. Tomas | Esperanza | 2nd Eng'g. Dist. | Completed | 2019-07-17 | 2020-02-15 | 2019 | Administartion | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Rehabilitation Of Various Prov'l. Roads and Bridges | [7 empty] | Implementor: | PEO | No. of days suspended: | 28 | Disbursement: |  | Actual: | 1.3% |  |  |  |  | Actual: | 100% | Actual: | 100%
Sto. Tomas | Esperanza | 2nd Eng'g. Dist. | Completed | 2019-07-17 | 2020-02-15 | 2019 | Administartion | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Rehabilitation Of Various Prov'l. Roads and Bridges | [7 empty] | Duration: | 105 | No. of days extended: | 110 |  |  | Slippage: | -0.8% |  |  |  |  | Slippage: | 0% | Slippage: | 0%
Sto. Tomas | Esperanza | 2nd Eng'g. Dist. | Completed | 2019-07-17 | 2020-02-15 | 2019 | Administartion | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Rehabilitation Of Various Prov'l. Roads and Bridges | [7 empty] | Date Allotment Released: | 2019-01-03 | Date completed: | 2020-02-15
Sto. Tomas | Esperanza | 2nd Eng'g. Dist. | Completed | 2019-07-17 | 2020-02-15 | 2019 | Administartion | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Rehabilitation Of Various Prov'l. Roads and Bridges | [7 empty] | Date Started: | 2019-06-17
Sto. Tomas | Libertad | 2nd Eng'g. Dist. | Completed | 2019-06-17 | 2020-02-29 | 2019 | Administartion | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Rehabilitation Of Various Prov'l. Roads and Bridges | San Miguel - Libertad |  | 20% DF CY 2019 | Road Rehabilitation | 6.2 | km | Admin | Project Cost: | 1240000 | Target Completion Date: | 2019-10-31 | Program: | 1240000 | Planned: | 59.41% | Planned: | 59.41% | Planned: | 59.41% | Planned: | 59.41% | Planned: | 100% | No. of Persons: | 9 | On-going | On-going | On-going | On-going | On-going | Completed as per Program of Works
Sto. Tomas | Libertad | 2nd Eng'g. Dist. | Completed | 2019-06-17 | 2020-02-29 | 2019 | Administartion | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Rehabilitation Of Various Prov'l. Roads and Bridges | [7 empty] | Project Engineer: | Gamad | Revised Completion Date: | 2020-02-29 | Allotment: | 1240000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 36
Sto. Tomas | Libertad | 2nd Eng'g. Dist. | Completed | 2019-06-17 | 2020-02-29 | 2019 | Administartion | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Rehabilitation Of Various Prov'l. Roads and Bridges | [7 empty] | Implementor: | PEO | No. of days suspended: | 86 | Disbursement: |  | Actual: | 59.41% | Actual: | 59.41% | Actual: | 59.41% | Actual: | 59.41% | Actual: | 100%
Sto. Tomas | Libertad | 2nd Eng'g. Dist. | Completed | 2019-06-17 | 2020-02-29 | 2019 | Administartion | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Rehabilitation Of Various Prov'l. Roads and Bridges | [7 empty] | Duration: | 136 | No. of days extended: | 35 |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Sto. Tomas | Libertad | 2nd Eng'g. Dist. | Completed | 2019-06-17 | 2020-02-29 | 2019 | Administartion | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Rehabilitation Of Various Prov'l. Roads and Bridges | [7 empty] | Date Allotment Released: | 2019-01-03 | Date completed: | 2020-02-29
Sto. Tomas | Libertad | 2nd Eng'g. Dist. | Completed | 2019-06-17 | 2020-02-29 | 2019 | Administartion | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Rehabilitation Of Various Prov'l. Roads and Bridges | [7 empty] | Date Started: | 2019-06-17
Sto. Tomas | Casig-ang | 2nd Eng'g. Dist. | Completed | 2019-06-27 | 2020-02-29 | 2019 | Administartion | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Rehabilitation Of Various Prov'l. Roads and Bridges | Bacali - Casig-ang - Libertad |  | 20% DF CY 2019 | Road Rehabilitation | 4.7 | km | Admin | Project Cost: | 940000 | Target Completion Date: | 2019-09-15 | Program: | 940000 | Planned: | 62.1% | Planned: | 62.1% | Planned: | 62.1% | Planned: | 100% | Planned: | 100% | No. of Persons: | 6 | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. (Furtherance on-going) | Completed as per physical accomplishment. Financial documents still on process. (Furtherance on-going) | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per Program of Works
Sto. Tomas | Casig-ang | 2nd Eng'g. Dist. | Completed | 2019-06-27 | 2020-02-29 | 2019 | Administartion | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Rehabilitation Of Various Prov'l. Roads and Bridges | [7 empty] | Project Engineer: | Gamad | Revised Completion Date: | 2020-02-29 | Allotment: | 940000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 132
Sto. Tomas | Casig-ang | 2nd Eng'g. Dist. | Completed | 2019-06-27 | 2020-02-29 | 2019 | Administartion | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Rehabilitation Of Various Prov'l. Roads and Bridges | [7 empty] | Implementor: | PEO | No. of days suspended: | 132 | Disbursement: |  | Actual: | 62% | Actual: | 62% | Actual: | 62% | Actual: | 100% | Actual: | 100%
Sto. Tomas | Casig-ang | 2nd Eng'g. Dist. | Completed | 2019-06-27 | 2020-02-29 | 2019 | Administartion | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Rehabilitation Of Various Prov'l. Roads and Bridges | [7 empty] | Duration: | 80 | No. of days extended: | 35 |  |  | Slippage: | -0.1% | Slippage: | -0.1% | Slippage: | -0.1% | Slippage: | 0% | Slippage: | 0%
Sto. Tomas | Casig-ang | 2nd Eng'g. Dist. | Completed | 2019-06-27 | 2020-02-29 | 2019 | Administartion | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Rehabilitation Of Various Prov'l. Roads and Bridges | [7 empty] | Date Allotment Released: | 2019-06-07 | Date completed: | 2020-02-29
Sto. Tomas | Casig-ang | 2nd Eng'g. Dist. | Completed | 2019-06-27 | 2020-02-29 | 2019 | Administartion | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Rehabilitation Of Various Prov'l. Roads and Bridges | [7 empty] | Date Started: | 2019-06-27
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | Completed | 2019-06-17 | 2020-02-29 | 2019 | Administartion | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Rehabilitation Of Various Prov'l. Roads and Bridges | San Miguel - Moslog - Kinamayan |  | 20% DF CY 2019 | Road Rehabilitation | 2.9 | km | Admin | Project Cost: | 1000000 | Target Completion Date: | 2019-09-16 | Program: | 1000000 | Planned: | 100% | Planned: | 100% | Planned: | 100% | Planned: | 100% | Planned: | 100% | No. of Persons: | 6 | On-going | On-going | On-going | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per Program of Works
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | Completed | 2019-06-17 | 2020-02-29 | 2019 | Administartion | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Rehabilitation Of Various Prov'l. Roads and Bridges | [7 empty] | Project Engineer: | Gamad | Revised Completion Date: | 2020-02-29 | Allotment: | 1000000 | Revised: | 73.59% | Revised: | 73.59% | Revised: | 73.59% | Revised: |  | Revised: |  | No. of Man-days: | 30
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | Completed | 2019-06-17 | 2020-02-29 | 2019 | Administartion | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Rehabilitation Of Various Prov'l. Roads and Bridges | [7 empty] | Implementor: | PEO | No. of days suspended: | 137 | Disbursement: |  | Actual: | 80% | Actual: | 80% | Actual: | 80% | Actual: | 100% | Actual: | 100%
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | Completed | 2019-06-17 | 2020-02-29 | 2019 | Administartion | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Rehabilitation Of Various Prov'l. Roads and Bridges | [7 empty] | Duration: | 91 | No. of days extended: | 29 |  |  | Slippage: | 6.41% | Slippage: | 6.41% | Slippage: | 6.41% | Slippage: | 0% | Slippage: | 0%
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | Completed | 2019-06-17 | 2020-02-29 | 2019 | Administartion | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Rehabilitation Of Various Prov'l. Roads and Bridges | [7 empty] | Date Allotment Released: | 2019-05-20 | Date completed: | 2020-02-29
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | Completed | 2019-06-17 | 2020-02-29 | 2019 | Administartion | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Rehabilitation Of Various Prov'l. Roads and Bridges | [7 empty] | Date Started: | 2019-06-17
Sto. Tomas | New katipunan Pantaron | 2nd Eng'g. Dist. | On-going | 2019-12-27 |  | 2019 | Adminsitration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Rehabilitation Of Various Prov'l. Roads and Bridges | New Katipunan - Pantaron |  | 20% DF CY 2019 | Road Rehabilitation | 1.96 | km | Admin | Project Cost: | 395000 | Target Completion Date: | 2020-02-25 | Program: | 395000 | Planned: | 60% | Planned: | 60% | Planned: | 60% | Planned: | 60% | Planned: | 60% | No. of Persons: | 4 | On-going | On-going | On-going | On-going | On-going | On-going
Sto. Tomas | New katipunan Pantaron | 2nd Eng'g. Dist. | On-going | 2019-12-27 |  | 2019 | Adminsitration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Rehabilitation Of Various Prov'l. Roads and Bridges | [7 empty] | Project Engineer: | Gamad/Clar | Revised Completion Date: |  | Allotment: | 395000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 24
Sto. Tomas | New katipunan Pantaron | 2nd Eng'g. Dist. | On-going | 2019-12-27 |  | 2019 | Adminsitration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Rehabilitation Of Various Prov'l. Roads and Bridges | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: | 60% | Actual: | 60% | Actual: | 60% | Actual: | 60% | Actual: | 60%
Sto. Tomas | New katipunan Pantaron | 2nd Eng'g. Dist. | On-going | 2019-12-27 |  | 2019 | Adminsitration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Rehabilitation Of Various Prov'l. Roads and Bridges | [7 empty] | Duration: | 60 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Sto. Tomas | New katipunan Pantaron | 2nd Eng'g. Dist. | On-going | 2019-12-27 |  | 2019 | Adminsitration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Rehabilitation Of Various Prov'l. Roads and Bridges | [7 empty] | Date Allotment Released: | 2019-01-03 | Date completed:
Sto. Tomas | New katipunan Pantaron | 2nd Eng'g. Dist. | On-going | 2019-12-27 |  | 2019 | Adminsitration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Rehabilitation Of Various Prov'l. Roads and Bridges | [7 empty] | Date Started: | 2019-12-27
Sto. Tomas | Magwawa | 2nd Eng'g. Dist. | Completed | 2019-08-27 | 2020-03-31 | 2019 | Adminsitration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | Fd Rd 2 - Sto. Tomas - Magwawa |  | 20% DF CY 2019 | Road Rehabilitation | 10.21 | km | Admin | Project Cost: | 3575000 | Target Completion Date: | 2019-10-26 | Program: | 3575000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: | 100% | No. of Persons: |  | Plan and POW Approved | Plan and POW Approved | Plan and POW Approved | Plan and POW Approved | Plan and POW Approved | Completed as per Program of Works
Sto. Tomas | Magwawa | 2nd Eng'g. Dist. | Completed | 2019-08-27 | 2020-03-31 | 2019 | Adminsitration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Project Engineer: | Gamad/Clar | Revised Completion Date: |  | Allotment: | 3575000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
Sto. Tomas | Magwawa | 2nd Eng'g. Dist. | Completed | 2019-08-27 | 2020-03-31 | 2019 | Adminsitration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual: | 100%
Sto. Tomas | Magwawa | 2nd Eng'g. Dist. | Completed | 2019-08-27 | 2020-03-31 | 2019 | Adminsitration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Duration: | 60 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Sto. Tomas | Magwawa | 2nd Eng'g. Dist. | Completed | 2019-08-27 | 2020-03-31 | 2019 | Adminsitration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Date Allotment Released: | 2019-01-03 | Date completed: | 2020-03-31
Sto. Tomas | Magwawa | 2nd Eng'g. Dist. | Completed | 2019-08-27 | 2020-03-31 | 2019 | Adminsitration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Date Started: | 2019-08-27
B.E. Dujali | Tanglaw | 2nd Eng'g. Dist. | Completed | 2019-06-17 | 2020-02-15 | 2019 | Adminsitration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | Jct. Highway - Tanglaw |  | 20% DF CY 2019 | Road Rehabilitation | 3.98 | km | Admin | Project Cost: | 1100000 | Target Completion Date: | 2019-09-16 | Program: | 1100000 | Planned: | 100% | Planned: | 100% | Planned: | 100% | Planned: | 100% | Planned: | 100% | No. of Persons: | 10 | On-going | On-going | On-going | On-going | On-going | Completed as per Program of Works
B.E. Dujali | Tanglaw | 2nd Eng'g. Dist. | Completed | 2019-06-17 | 2020-02-15 | 2019 | Adminsitration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Project Engineer: | Gamad/Clar | Revised Completion Date: | 2020-02-29 | Allotment: | 1100000 | Revised: | 73.59% | Revised: | 73.59% | Revised: | 73.59% | Revised: | 73.59% | Revised: |  | No. of Man-days: | 50
B.E. Dujali | Tanglaw | 2nd Eng'g. Dist. | Completed | 2019-06-17 | 2020-02-15 | 2019 | Adminsitration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Implementor: | PEO | No. of days suspended: | 137 | Disbursement: |  | Actual: | 85% | Actual: | 85% | Actual: | 85% | Actual: | 85% | Actual: | 100%
B.E. Dujali | Tanglaw | 2nd Eng'g. Dist. | Completed | 2019-06-17 | 2020-02-15 | 2019 | Adminsitration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Duration: | 91 | No. of days extended: | 29 |  |  | Slippage: | 11.41% | Slippage: | 11.41% | Slippage: | 11.41% | Slippage: | 11.41% | Slippage: | 0%
B.E. Dujali | Tanglaw | 2nd Eng'g. Dist. | Completed | 2019-06-17 | 2020-02-15 | 2019 | Adminsitration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Date Allotment Released: | 2019-05-16 | Date completed: | 2020-02-15
B.E. Dujali | Tanglaw | 2nd Eng'g. Dist. | Completed | 2019-06-17 | 2020-02-15 | 2019 | Adminsitration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Date Started: | 2019-06-17
Carmen | Asuncion | 2nd Eng'g. Dist. | Re-aligned to COVID |  |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | Lower Asuncion - Upper Asuncion |  | 20% DF CY 2019 | Road Rehabilitation | 1.02 | km | Admin | Project Cost: |  | Target Completion Date: |  | Program: | 0 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. |  |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
Carmen | Asuncion | 2nd Eng'g. Dist. | Re-aligned to COVID |  |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 0 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
Carmen | Asuncion | 2nd Eng'g. Dist. | Re-aligned to COVID |  |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
Carmen | Asuncion | 2nd Eng'g. Dist. | Re-aligned to COVID |  |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Carmen | Asuncion | 2nd Eng'g. Dist. | Re-aligned to COVID |  |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Date Allotment Released: |  | Date completed:
Carmen | Asuncion | 2nd Eng'g. Dist. | Re-aligned to COVID |  |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Date Started:
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | On-going | 2019-12-27 |  | 2019 | Adminsitration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | Bdry. Tagum - Crossing Kinamayan Sto. Tomas |  | 20% DF CY 2019 | Road Rehabilitation | 0.75 | km | Admin | Project Cost: | 3700000 | Target Completion Date: | 2020-04-25 | Program: | 3700000 | Planned: | 100% | Planned: | 100% | Planned: | 100% | Planned: | 100% | Planned: | 100% | No. of Persons: | 15 | On-going | On-going | On-going | On-going | On-going | On-going
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | On-going | 2019-12-27 |  | 2019 | Adminsitration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Project Engineer: | Gamad/Clar | Revised Completion Date: | 2020-08-23 | Allotment: | 3700000 | Revised: | 15.43% | Revised: | 15.43% | Revised: | 15.43% | Revised: | 15.43% | Revised: | 15.43% | No. of Man-days: | 225
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | On-going | 2019-12-27 |  | 2019 | Adminsitration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Implementor: |  | No. of days suspended: | 20 | Disbursement: |  | Actual: | 16.37% | Actual: | 16.37% | Actual: | 16.37% | Actual: | 16.37% | Actual: | 16.37%
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | On-going | 2019-12-27 |  | 2019 | Adminsitration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Duration: | 120 | No. of days extended: | 100 |  |  | Slippage: | 0.94% | Slippage: | 0.94% | Slippage: | 0.94% | Slippage: | 0.94% | Slippage: | 0.94%
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | On-going | 2019-12-27 |  | 2019 | Adminsitration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Date Allotment Released: | 2019-01-03 | Date completed:
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | On-going | 2019-12-27 |  | 2019 | Adminsitration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Date Started: | 2019-12-27
Carmen | Anibongan | 2nd Eng'g. Dist. | Completed | 2019-05-22 | 2020-01-31 | 2019 | Adminsitration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | Rehab. of Anibongan-Salvacion-Cabay-angan Provincial Road with Drainage |  | 20% DF CY 2019 | Road Drainage rehabiliated |  | km | Admin | Project Cost: | 2000000 | Target Completion Date: | 2019-08-04 23:59 | Program: | 2000000 | Planned: | 100% | Planned: | 100% | Planned: | 100% | Planned: | 100% | Planned: | 100% | No. of Persons: | 1 | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per Program of Works
Carmen | Anibongan | 2nd Eng'g. Dist. | Completed | 2019-05-22 | 2020-01-31 | 2019 | Adminsitration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Project Engineer: | Toquero | Revised Completion Date: | 2019-12-31 23:59 | Allotment: | 2000000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 4
Carmen | Anibongan | 2nd Eng'g. Dist. | Completed | 2019-05-22 | 2020-01-31 | 2019 | Adminsitration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: | 100% | Actual: | 100% | Actual: | 100% | Actual: | 100% | Actual: | 100%
Carmen | Anibongan | 2nd Eng'g. Dist. | Completed | 2019-05-22 | 2020-01-31 | 2019 | Adminsitration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Duration: | 75 | No. of days extended: | 149 |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Carmen | Anibongan | 2nd Eng'g. Dist. | Completed | 2019-05-22 | 2020-01-31 | 2019 | Adminsitration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Date Allotment Released: | 2019-01-14 | Date completed: | 2020-01-31
Carmen | Anibongan | 2nd Eng'g. Dist. | Completed | 2019-05-22 | 2020-01-31 | 2019 | Adminsitration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Date Started: | 2019-05-22
B.E. Dujali | Dujali | 2nd Eng'g. Dist. | Completed | 2019-11-04 | 2020-09-15 | 2019 | Adminsitration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various of Local Roads & Drainage Development Project (Provincewide) LS - 15,000,000.00 | Rehab. Of Dujali-Pawas-San Vicente Provincial Road |  | 20% DF CY 2019 (SB # 3 CY 2019) | Road Drainage rehabiliated |  | km | Admin | Project Cost: | 1102900 | Target Completion Date: |  | Program: | 1102900 | Planned: | 80% | Planned: | 100% | Planned: | 100% | Planned: | 100% | Planned: | 100% | No. of Persons: | 1 | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per Program of Works
B.E. Dujali | Dujali | 2nd Eng'g. Dist. | Completed | 2019-11-04 | 2020-09-15 | 2019 | Adminsitration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various of Local Roads & Drainage Development Project (Provincewide) LS - 15,000,000.00 | [7 empty] | Project Engineer: | Toquero | Revised Completion Date: |  | Allotment: | 1102900 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 4
B.E. Dujali | Dujali | 2nd Eng'g. Dist. | Completed | 2019-11-04 | 2020-09-15 | 2019 | Adminsitration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various of Local Roads & Drainage Development Project (Provincewide) LS - 15,000,000.00 | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: | 80% | Actual: | 91.4% | Actual: | 99.96% | Actual: | 100% | Actual: | 100%
B.E. Dujali | Dujali | 2nd Eng'g. Dist. | Completed | 2019-11-04 | 2020-09-15 | 2019 | Adminsitration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various of Local Roads & Drainage Development Project (Provincewide) LS - 15,000,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | -8.6% | Slippage: | -0.04% | Slippage: | 0% | Slippage: | 0%
B.E. Dujali | Dujali | 2nd Eng'g. Dist. | Completed | 2019-11-04 | 2020-09-15 | 2019 | Adminsitration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various of Local Roads & Drainage Development Project (Provincewide) LS - 15,000,000.00 | [7 empty] | Date Allotment Released: |  | Date completed: | 2020-09-15
B.E. Dujali | Dujali | 2nd Eng'g. Dist. | Completed | 2019-11-04 | 2020-09-15 | 2019 | Adminsitration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various of Local Roads & Drainage Development Project (Provincewide) LS - 15,000,000.00 | [7 empty] | Date Started: | 2019-11-04
B.E. Dujali | Ising | 2nd Eng'g. Dist. | Completed | 2020-07-01 | 2020-12-31 | 2019 | Adminsitration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various of Local Roads & Drainage Development Project (Provincewide) LS - 15,000,000.00 | Rehab./Impv't. of Jct. highway Ising-Magsaysay Provincial Road with Drainage |  | 20% DF CY 2019 | Road Drainage rehabiliated |  | km | Admin | Project Cost: | 1500000 | Target Completion Date: | 2020-08-31 | Program: | 1500000 | Planned: |  | Planned: |  | Planned: | 100% | Planned: | 100% | Planned: | 100% | No. of Persons: | 1 | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per Program of Works
B.E. Dujali | Ising | 2nd Eng'g. Dist. | Completed | 2020-07-01 | 2020-12-31 | 2019 | Adminsitration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various of Local Roads & Drainage Development Project (Provincewide) LS - 15,000,000.00 | [7 empty] | Project Engineer: | Toquero | Revised Completion Date: | 2020-12-31 | Allotment: | 1500000 | Revised: |  | Revised: |  | Revised: | 32.32% | Revised: |  | Revised: |  | No. of Man-days: | 4
B.E. Dujali | Ising | 2nd Eng'g. Dist. | Completed | 2020-07-01 | 2020-12-31 | 2019 | Adminsitration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various of Local Roads & Drainage Development Project (Provincewide) LS - 15,000,000.00 | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: | 35.6% | Actual: | 100% | Actual: | 100%
B.E. Dujali | Ising | 2nd Eng'g. Dist. | Completed | 2020-07-01 | 2020-12-31 | 2019 | Adminsitration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various of Local Roads & Drainage Development Project (Provincewide) LS - 15,000,000.00 | [7 empty] | Duration: | 61 | No. of days extended: | 122 |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 3.28% | Slippage: | 0% | Slippage: | 0%
B.E. Dujali | Ising | 2nd Eng'g. Dist. | Completed | 2020-07-01 | 2020-12-31 | 2019 | Adminsitration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various of Local Roads & Drainage Development Project (Provincewide) LS - 15,000,000.00 | [7 empty] | Date Allotment Released: | 2019-01-16 | Date completed: | 2020-12-31
B.E. Dujali | Ising | 2nd Eng'g. Dist. | Completed | 2020-07-01 | 2020-12-31 | 2019 | Adminsitration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various of Local Roads & Drainage Development Project (Provincewide) LS - 15,000,000.00 | [7 empty] | Date Started: | 2020-07-01
New Corella | San Juan-New Talisay | 1st Eng'g. Dist. | Completed | 2019-11-04 | 2020-09-15 | 2019 | Adminsitration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS OF LOCAL ROADS & DRAINAGE DEVELOPMENT PROJECT(Provincewide) LS - 15,000,000.00 | Rehab./Impv't. of San Juan-New Talisay Provincial Road with Drainage |  | 20% DF CY 2019 | Road Drainage rehabiliated |  | km | Admin | Project Cost: | 1000000 | Target Completion Date: | 2019-12-18 | Program: | 1000000 | Planned: | 57.41% | Planned: | 76.06% | Planned: | 76.06% | Planned: | 76.06% | Planned: | 100% | No. of Persons: | 1 | On- going (Resume August 17, 2020) | On- going (Resume August 17, 2020) | On- going (Resume August 17, 2020) |  |  | Completed as per Program of Works
New Corella | San Juan-New Talisay | 1st Eng'g. Dist. | Completed | 2019-11-04 | 2020-09-15 | 2019 | Adminsitration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS OF LOCAL ROADS & DRAINAGE DEVELOPMENT PROJECT(Provincewide) LS - 15,000,000.00 | [7 empty] | Project Engineer: | Pilotos | Revised Completion Date: | 2019-12-18 | Allotment: | 1000000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 4
New Corella | San Juan-New Talisay | 1st Eng'g. Dist. | Completed | 2019-11-04 | 2020-09-15 | 2019 | Adminsitration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS OF LOCAL ROADS & DRAINAGE DEVELOPMENT PROJECT(Provincewide) LS - 15,000,000.00 | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: | 741100 | Actual: | 74.11% | Actual: | 76.06% | Actual: | 76.06% | Actual: | 76.06% | Actual: | 100%
New Corella | San Juan-New Talisay | 1st Eng'g. Dist. | Completed | 2019-11-04 | 2020-09-15 | 2019 | Adminsitration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS OF LOCAL ROADS & DRAINAGE DEVELOPMENT PROJECT(Provincewide) LS - 15,000,000.00 | [7 empty] | Duration: | 44 | No. of days extended: |  |  |  | Slippage: | 16.7% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
New Corella | San Juan-New Talisay | 1st Eng'g. Dist. | Completed | 2019-11-04 | 2020-09-15 | 2019 | Adminsitration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS OF LOCAL ROADS & DRAINAGE DEVELOPMENT PROJECT(Provincewide) LS - 15,000,000.00 | [7 empty] | Date Allotment Released: | 2019-01-31 | Date completed: | 2020-09-15
New Corella | San Juan-New Talisay | 1st Eng'g. Dist. | Completed | 2019-11-04 | 2020-09-15 | 2019 | Adminsitration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS OF LOCAL ROADS & DRAINAGE DEVELOPMENT PROJECT(Provincewide) LS - 15,000,000.00 | [7 empty] | Date Started: | 2019-11-04
Asuncion | Saug-Sonlon Longanapan | 1st Eng'g. Dist. | completed | 2019-08-06 | 2020-01-17 | 2019 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS OF LOCAL ROADS & DRAINAGE DEVELOPMENT PROJECT(Provincewide) LS - 15,000,000.00 | Impv't. of Cross Drainage along Saug-Sonlon-Bdry. Longanapan |  | 20% DF CY 2019 | Road Drainage rehabiliated |  | ln.m | Admin | Project Cost: | 3000000 | Target Completion Date: | 2020-01-17 23:46 | Program: | 3000000 | Planned: |  | Planned: |  | Planned: |  | Planned: | 100% | Planned: | 100% | No. of Persons: | 1 | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per Program of Works
Asuncion | Saug-Sonlon Longanapan | 1st Eng'g. Dist. | completed | 2019-08-06 | 2020-01-17 | 2019 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS OF LOCAL ROADS & DRAINAGE DEVELOPMENT PROJECT(Provincewide) LS - 15,000,000.00 | [7 empty] | Project Engineer: | Pilotos | Revised Completion Date: |  | Allotment: | 3000000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 4
Asuncion | Saug-Sonlon Longanapan | 1st Eng'g. Dist. | completed | 2019-08-06 | 2020-01-17 | 2019 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS OF LOCAL ROADS & DRAINAGE DEVELOPMENT PROJECT(Provincewide) LS - 15,000,000.00 | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: | 100% | Actual: | 100%
Asuncion | Saug-Sonlon Longanapan | 1st Eng'g. Dist. | completed | 2019-08-06 | 2020-01-17 | 2019 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS OF LOCAL ROADS & DRAINAGE DEVELOPMENT PROJECT(Provincewide) LS - 15,000,000.00 | [7 empty] | Duration: | 165 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Asuncion | Saug-Sonlon Longanapan | 1st Eng'g. Dist. | completed | 2019-08-06 | 2020-01-17 | 2019 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS OF LOCAL ROADS & DRAINAGE DEVELOPMENT PROJECT(Provincewide) LS - 15,000,000.00 | [7 empty] | Date Allotment Released: |  | Date completed: | 2020-01-17 23:46
Asuncion | Saug-Sonlon Longanapan | 1st Eng'g. Dist. | completed | 2019-08-06 | 2020-01-17 | 2019 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS OF LOCAL ROADS & DRAINAGE DEVELOPMENT PROJECT(Provincewide) LS - 15,000,000.00 | [7 empty] | Date Started: | 2019-08-06
B.E. Dujali | Magupising | 2nd Eng'g. Dist. | Completed | 2019-12-02 | 2020-05-29 | 2019 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | Rehab.of Dujali - Balisong - Magupising Provincial Road |  | 20% DF CY 2019 | Road Rehabilitation | 19.16 | km | MBA | Project Cost: | 1280000 | Target Completion Date: | 2020-01-15 23:59 | Program: | 1280000 | Planned: | 100% | Planned: | 100% | Planned: | 100% | Planned: | 100% | Planned: | 100% | No. of Persons: | 1 | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per Program of Works
B.E. Dujali | Magupising | 2nd Eng'g. Dist. | Completed | 2019-12-02 | 2020-05-29 | 2019 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Project Engineer: | Mellomida | Revised Completion Date: | 2020-05-31 23:59 | Allotment: | 1280000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 4
B.E. Dujali | Magupising | 2nd Eng'g. Dist. | Completed | 2019-12-02 | 2020-05-29 | 2019 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Implementor: | PEO | No. of days suspended: | 137 | Disbursement: | 14331.6 | Actual: | 100% | Actual: | 100% | Actual: | 100% | Actual: | 100% | Actual: | 100%
B.E. Dujali | Magupising | 2nd Eng'g. Dist. | Completed | 2019-12-02 | 2020-05-29 | 2019 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Duration: | 45 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
B.E. Dujali | Magupising | 2nd Eng'g. Dist. | Completed | 2019-12-02 | 2020-05-29 | 2019 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Date Allotment Released: |  | Date completed: | 2020-05-29
B.E. Dujali | Magupising | 2nd Eng'g. Dist. | Completed | 2019-12-02 | 2020-05-29 | 2019 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Road Rehabilitation of Provincial Roads | [7 empty] | Date Started: | 2019-12-02
Panabo City | Kiotoy | 2nd Eng'g. Dist. | Re-aligned to COVID |  |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) | Construction of PWS, Brgy. Brgy. Kiotoy, Panabo City |  | 20% DF CY 2019 | Georesistivity |  |  |  | Project Cost: | 62500 | Target Completion Date: |  | Program: | 62500 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
Panabo City | Kiotoy | 2nd Eng'g. Dist. | Re-aligned to COVID |  |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 62500 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
Panabo City | Kiotoy | 2nd Eng'g. Dist. | Re-aligned to COVID |  |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
Panabo City | Kiotoy | 2nd Eng'g. Dist. | Re-aligned to COVID |  |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Panabo City | Kiotoy | 2nd Eng'g. Dist. | Re-aligned to COVID |  |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) | [7 empty] | Date Allotment Released: |  | Date completed:
Panabo City | Kiotoy | 2nd Eng'g. Dist. | Re-aligned to COVID |  |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) | [7 empty] | Date Started:
IGCS | Linusotan | 2nd Eng'g. Dist. | Re-aligned to COVID |  |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | Construction of PWS, Brgy. Linosutan, Talikud, IGCS |  | 20% DF CY 2019 | Water System |  |  |  | Project Cost: | 62500 | Target Completion Date: |  | Program: | 62500 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Procurement on process | Procurement on process | Procurement on process | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No 1 | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No 1 | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No 1
IGCS | Linusotan | 2nd Eng'g. Dist. | Re-aligned to COVID |  |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 62500 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
IGCS | Linusotan | 2nd Eng'g. Dist. | Re-aligned to COVID |  |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
IGCS | Linusotan | 2nd Eng'g. Dist. | Re-aligned to COVID |  |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
IGCS | Linusotan | 2nd Eng'g. Dist. | Re-aligned to COVID |  |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
IGCS | Linusotan | 2nd Eng'g. Dist. | Re-aligned to COVID |  |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | [7 empty] | Date Started:
Babak, IGCS | San Miguel | 2nd Eng'g. Dist. | Re-aligned to COVID |  |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | Construction of PWS, Brgy. San Miguel, Samal, IGCS |  | 20% DF CY 2019 | Water System |  |  |  | Project Cost: | 62500 | Target Completion Date: |  | Program: | 62500 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
Babak, IGCS | San Miguel | 2nd Eng'g. Dist. | Re-aligned to COVID |  |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 62500 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
Babak, IGCS | San Miguel | 2nd Eng'g. Dist. | Re-aligned to COVID |  |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
Babak, IGCS | San Miguel | 2nd Eng'g. Dist. | Re-aligned to COVID |  |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Babak, IGCS | San Miguel | 2nd Eng'g. Dist. | Re-aligned to COVID |  |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Babak, IGCS | San Miguel | 2nd Eng'g. Dist. | Re-aligned to COVID |  |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | [7 empty] | Date Started:
Panabo City | Cacao | 2nd Eng'g. Dist. | Re-aligned to COVID |  |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | Construction of PWS, Cacao, Panabo City |  | 20% DF CY 2019 | Water System |  |  |  | Project Cost: | 62500 | Target Completion Date: |  | Program: | 62500 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | For cancellation. Purchase of Geo-resistivity equipment but procurement still on process | For cancellation. Purchase of Geo-resistivity equipment but procurement still on process | For amendment indicating phase 2 since the project title is the same with stimulus project (letter will be submitted by Mr. Amamio-focal person for water system for explanation) | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
Panabo City | Cacao | 2nd Eng'g. Dist. | Re-aligned to COVID |  |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 62500 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
Panabo City | Cacao | 2nd Eng'g. Dist. | Re-aligned to COVID |  |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
Panabo City | Cacao | 2nd Eng'g. Dist. | Re-aligned to COVID |  |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Panabo City | Cacao | 2nd Eng'g. Dist. | Re-aligned to COVID |  |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Panabo City | Cacao | 2nd Eng'g. Dist. | Re-aligned to COVID |  |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | [7 empty] | Date Started:
San Isidro | Linao | 1st Eng'g. Dist. | Completed | 2020-02-24 | 2020-07-31 | 2019 | Adminsitration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - P 10,000,000.00 | Construction of PWS, Bgry. Linao, San Isidro |  | 20% DF CY 2019 | Water System |  | ln.m | Admin | Project Cost: | 500000 | Target Completion Date: | 2020-04-23 23:46 | Program: | 500000 | Planned: | 100% | Planned: | 100% | Planned: | 100% | Planned: | 100% | Planned: | 100% | No. of Persons: | 8 | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per Program of Works
San Isidro | Linao | 1st Eng'g. Dist. | Completed | 2020-02-24 | 2020-07-31 | 2019 | Adminsitration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - P 10,000,000.00 | [7 empty] | Project Engineer: | Aclaracion | Revised Completion Date: | 2020-07-05 23:46 | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 120
San Isidro | Linao | 1st Eng'g. Dist. | Completed | 2020-02-24 | 2020-07-31 | 2019 | Adminsitration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - P 10,000,000.00 | [7 empty] | Implementor: | PEO | No. of days suspended: | 73 | Disbursement: | 216100 | Actual: | 100% | Actual: | 100% | Actual: | 100% | Actual: | 100% | Actual: | 100%
San Isidro | Linao | 1st Eng'g. Dist. | Completed | 2020-02-24 | 2020-07-31 | 2019 | Adminsitration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - P 10,000,000.00 | [7 empty] | Duration: | 60 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
San Isidro | Linao | 1st Eng'g. Dist. | Completed | 2020-02-24 | 2020-07-31 | 2019 | Adminsitration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - P 10,000,000.00 | [7 empty] | Date Allotment Released: | 2019-06-19 | Date completed: | 2020-07-31
San Isidro | Linao | 1st Eng'g. Dist. | Completed | 2020-02-24 | 2020-07-31 | 2019 | Adminsitration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - P 10,000,000.00 | [7 empty] | Date Started: | 2020-02-24
San Isidro | Mamalian | 1st Eng'g. Dist. | Re-aligned to COVID |  |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - P 10,000,000.00 | Const. of PWS Mamalian, San Isidro |  | 20% DF CY 2019 | Water System |  |  | Admin | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | For declaration of savings because the spring water source is not feasible for development. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
San Isidro | Mamalian | 1st Eng'g. Dist. | Re-aligned to COVID |  |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - P 10,000,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
San Isidro | Mamalian | 1st Eng'g. Dist. | Re-aligned to COVID |  |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - P 10,000,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
San Isidro | Mamalian | 1st Eng'g. Dist. | Re-aligned to COVID |  |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - P 10,000,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
San Isidro | Mamalian | 1st Eng'g. Dist. | Re-aligned to COVID |  |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - P 10,000,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
San Isidro | Mamalian | 1st Eng'g. Dist. | Re-aligned to COVID |  |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - P 10,000,000.00 | [7 empty] | Date Started:
San Isidro | Sagayen | 1st Eng'g. Dist. |  |  |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - P 10,000,000.00 | Const. of PWS Sagayen, San Isidro |  | 20% DF CY 2019 | Water System |  |  | Admin | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. |  |  | For implementation
San Isidro | Sagayen | 1st Eng'g. Dist. |  |  |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - P 10,000,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
San Isidro | Sagayen | 1st Eng'g. Dist. |  |  | 0 | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - P 10,000,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
San Isidro | Sagayen | 1st Eng'g. Dist. |  |  |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - P 10,000,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
San Isidro | Sagayen | 1st Eng'g. Dist. |  |  |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - P 10,000,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
San Isidro | Sagayen | 1st Eng'g. Dist. |  |  |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - P 10,000,000.00 | [7 empty] | Date Started:
kapalong | Capungagan | 1st Eng'g. Dist. |  |  |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - P 10,000,000.00 | Construction of PWS, Brgy. Purok 7-A and B, Brgy. Capungagan, kapalong |  | 20% DF CY 2019 | Water System |  |  | Admin | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. |  |  | For implementation
kapalong | Capungagan | 1st Eng'g. Dist. |  |  |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - P 10,000,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
kapalong | Capungagan | 1st Eng'g. Dist. |  |  | 0 | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - P 10,000,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
kapalong | Capungagan | 1st Eng'g. Dist. |  |  |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - P 10,000,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
kapalong | Capungagan | 1st Eng'g. Dist. |  |  |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - P 10,000,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
kapalong | Capungagan | 1st Eng'g. Dist. |  |  |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - P 10,000,000.00 | [7 empty] | Date Started:
Kapalong | Pag-Asa | 1st Eng'g. Dist. |  |  |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - P 10,000,000.00 | Construction of PWS Level II in Purok 2, Pag-Asa, kapalong |  | 20% DF CY 2019 | Potable Water System |  |  | Admin | Project Cost: | 500000 | Target Completion Date: | 0 | Program: | 500000 | Planned: | 100% | Planned: | 100% | Planned: | 100% | Planned: |  | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. |  |  | For implementation
Kapalong | Pag-Asa | 1st Eng'g. Dist. |  |  |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - P 10,000,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: | 100% | Revised: | 81.57% | Revised: | 81.57% | Revised: |  | Revised: |  | No. of Man-days:
Kapalong | Pag-Asa | 1st Eng'g. Dist. |  |  |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - P 10,000,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: | 72.68% | Actual: | 76.39% | Actual: | 76.39% | Actual: |  | Actual:
Kapalong | Pag-Asa | 1st Eng'g. Dist. |  |  |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - P 10,000,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | -27.32% | Slippage: | -5.179% | Slippage: | -5.179% | Slippage: | 0% | Slippage: | 0%
Kapalong | Pag-Asa | 1st Eng'g. Dist. |  |  |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - P 10,000,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Kapalong | Pag-Asa | 1st Eng'g. Dist. |  |  |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - P 10,000,000.00 | [7 empty] | Date Started:
Panabo City | Consolacion | 2nd Eng'g. Dist. | On-going | 2020-04-07 |  | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - P 10,000,000.00 | Impv't. of Potable Water System, Consolacion, Panabo City |  | 20% DF CY 2019 | Water System |  |  |  | Project Cost: | 500000 | Target Completion Date: | 2020-06-06 | Program: | 500000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: | 100% | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. |  |  | Subject for LD, no activity on site/ Issued 2nd warning letter
Panabo City | Consolacion | 2nd Eng'g. Dist. | On-going | 2020-04-07 |  | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - P 10,000,000.00 | [7 empty] | Project Engineer: | Abayon | Revised Completion Date: | September 1, 2020 | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: | 56.5% | No. of Man-days:
Panabo City | Consolacion | 2nd Eng'g. Dist. | On-going | 2020-04-07 |  | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - P 10,000,000.00 | [7 empty] | Implementor: | RLHV | No. of days suspended: | 86 | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual: | 1.2%
Panabo City | Consolacion | 2nd Eng'g. Dist. | On-going | 2020-04-07 |  | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - P 10,000,000.00 | [7 empty] | Duration: | 60 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | -55.3%
Panabo City | Consolacion | 2nd Eng'g. Dist. | On-going | 2020-04-07 |  | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - P 10,000,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Panabo City | Consolacion | 2nd Eng'g. Dist. | On-going | 2020-04-07 |  | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - P 10,000,000.00 | [7 empty] | Date Started: | 2020-04-07
Samal | Tagbitan-ag | 2nd Eng'g. Dist. | For Implementation |  |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - P 10,000,000.00 | Impv't. of Potable Water System, Tagbitan-ag, Samal Dist. |  | 20% DF CY 2019 | Water System |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | For implementation | For implementation | For implementation | For implementation | For implementation | For implementation
Samal | Tagbitan-ag | 2nd Eng'g. Dist. | For Implementation |  |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - P 10,000,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
Samal | Tagbitan-ag | 2nd Eng'g. Dist. | For Implementation |  |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - P 10,000,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
Samal | Tagbitan-ag | 2nd Eng'g. Dist. | For Implementation |  |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - P 10,000,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Samal | Tagbitan-ag | 2nd Eng'g. Dist. | For Implementation |  |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - P 10,000,000.00 | [7 empty] | Date Allotment Released: | 2019-06-19 | Date completed:
Samal | Tagbitan-ag | 2nd Eng'g. Dist. | For Implementation |  |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - P 10,000,000.00 | [7 empty] | Date Started:
Babak | San Antonio | 2nd Eng'g. Dist. | Re-aligned to COVID |  |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - P 10,000,000.00 | Impv't. of Potable Water System, San Antonio, babak, IGCS |  | 20% DF CY 2019 | Water System |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
Babak | San Antonio | 2nd Eng'g. Dist. | Re-aligned to COVID |  |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - P 10,000,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
Babak | San Antonio | 2nd Eng'g. Dist. | Re-aligned to COVID |  |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - P 10,000,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
Babak | San Antonio | 2nd Eng'g. Dist. | Re-aligned to COVID |  |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - P 10,000,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Babak | San Antonio | 2nd Eng'g. Dist. | Re-aligned to COVID |  |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - P 10,000,000.00 | [7 empty] | Date Allotment Released: | 2019-06-25 | Date completed:
Babak | San Antonio | 2nd Eng'g. Dist. | Re-aligned to COVID |  |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - P 10,000,000.00 | [7 empty] | Date Started:
Panabo City | Buenavista | 2nd Eng'g. Dist. | For Implementation |  |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - P 10,000,000.00 | Construction of PWS, Brgy. Buenavista, Panabo City |  | 20% DF CY 2019 | Water System |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | For implementation | For implementation | For implementation | For implementation | For implementation | For implementation
Panabo City | Buenavista | 2nd Eng'g. Dist. | For Implementation |  |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - P 10,000,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
Panabo City | Buenavista | 2nd Eng'g. Dist. | For Implementation |  |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - P 10,000,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
Panabo City | Buenavista | 2nd Eng'g. Dist. | For Implementation |  |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - P 10,000,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Panabo City | Buenavista | 2nd Eng'g. Dist. | For Implementation |  |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - P 10,000,000.00 | [7 empty] | Date Allotment Released: | June 19 ,2019 | Date completed:
Panabo City | Buenavista | 2nd Eng'g. Dist. | For Implementation |  |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - P 10,000,000.00 | [7 empty] | Date Started:
Panabo City | Kiotoy | 2nd Eng'g. Dist. | Re-aligned to COVID |  |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - P 10,000,000.00 | Construction of PWS, Brgy. Brgy. Kiotoy, Panabo City |  | 20% DF CY 2019 | Water System |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
Panabo City | Kiotoy | 2nd Eng'g. Dist. | Re-aligned to COVID |  |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - P 10,000,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
Panabo City | Kiotoy | 2nd Eng'g. Dist. | Re-aligned to COVID |  |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - P 10,000,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
Panabo City | Kiotoy | 2nd Eng'g. Dist. | Re-aligned to COVID |  |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - P 10,000,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Panabo City | Kiotoy | 2nd Eng'g. Dist. | Re-aligned to COVID |  |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - P 10,000,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Panabo City | Kiotoy | 2nd Eng'g. Dist. | Re-aligned to COVID |  |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - P 10,000,000.00 | [7 empty] | Date Started:
Babak, IGCS | San Miguel | 2nd Eng'g. Dist. | Re-aligned to COVID |  |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - P 10,000,000.00 | Rehab. of PWS, Brgy. San Miguel, Babak, IGCS |  | 20% DF CY 2019 | Water System |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
Babak, IGCS | San Miguel | 2nd Eng'g. Dist. | Re-aligned to COVID |  |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - P 10,000,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
Babak, IGCS | San Miguel | 2nd Eng'g. Dist. | Re-aligned to COVID |  |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - P 10,000,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
Babak, IGCS | San Miguel | 2nd Eng'g. Dist. | Re-aligned to COVID |  |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - P 10,000,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Babak, IGCS | San Miguel | 2nd Eng'g. Dist. | Re-aligned to COVID |  |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - P 10,000,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Babak, IGCS | San Miguel | 2nd Eng'g. Dist. | Re-aligned to COVID |  |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - P 10,000,000.00 | [7 empty] | Date Started:
Panabo City | Cacao | 2nd Eng'g. Dist. | Pending |  |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - P 10,000,000.00 | Construction of PWS, Brgy. Cacao, Panabo City |  | 20% DF CY 2019 | Water System |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | For cancellation. Purchase of Geo-resistivity equipment but procurement still on process | For cancellation. Purchase of Geo-resistivity equipment but procurement still on process | For amendment indicating phase 2 since the project title is the same with stimulus project (letter will be submitted by Mr. Amamio-focal person for water system for explanation) | For amendment indicating phase 2 since the project title is the same with stimulus project (letter will be submitted by Mr. Amamio-focal person for water system for explanation) | For amendment indicating phase 2 since the project title is the same with stimulus project (letter will be submitted by Mr. Amamio-focal person for water system for explanation) | For amendment indicating phase 2 since the project title is the same with stimulus project (letter will be submitted by Mr. Amamio-focal person for water system for explanation)
Panabo City | Cacao | 2nd Eng'g. Dist. | Pending |  |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - P 10,000,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
Panabo City | Cacao | 2nd Eng'g. Dist. | Pending |  |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - P 10,000,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
Panabo City | Cacao | 2nd Eng'g. Dist. | Pending |  |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - P 10,000,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Panabo City | Cacao | 2nd Eng'g. Dist. | Pending |  |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - P 10,000,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Panabo City | Cacao | 2nd Eng'g. Dist. | Pending |  |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - P 10,000,000.00 | [7 empty] | Date Started:
Kaputian, IGCS | Pangubatan | 2nd Eng'g. Dist. | Declared savings |  |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - P 10,000,000.00 | Rehabilitation of Potable Water System, Brgy. Pangubatan, kaputian Dist. IGCS |  | 20% DF CY 2019 | Water System |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | For implementation | Declared as savings in the AIP 2nd Revision to fund for the Construction of PWS in Brgy Linusotan, Kaputian Dist. IGACOS (Project was funded by OPAPP CY 2018) | Declared as savings in the AIP 2nd Revision to fund for the Construction of PWS in Brgy Linusotan, Kaputian Dist. IGACOS (Project was funded by OPAPP CY 2018) | Declared as savings in the AIP 2nd Revision to fund for the Construction of PWS in Brgy Linusotan, Kaputian Dist. IGACOS (Project was funded by OPAPP CY 2018) | Declared as savings in the AIP 2nd Revision to fund for the Construction of PWS in Brgy Linusotan, Kaputian Dist. IGACOS (Project was funded by OPAPP CY 2018) | Declared as savings in the AIP 2nd Revision to fund for the Construction of PWS in Brgy Linusotan, Kaputian Dist. IGACOS (Project was funded by OPAPP CY 2018)
Kaputian, IGCS | Pangubatan | 2nd Eng'g. Dist. | Declared savings |  |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - P 10,000,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
Kaputian, IGCS | Pangubatan | 2nd Eng'g. Dist. | Declared savings |  |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - P 10,000,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
Kaputian, IGCS | Pangubatan | 2nd Eng'g. Dist. | Declared savings |  |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - P 10,000,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Kaputian, IGCS | Pangubatan | 2nd Eng'g. Dist. | Declared savings |  |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - P 10,000,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Kaputian, IGCS | Pangubatan | 2nd Eng'g. Dist. | Declared savings |  |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - P 10,000,000.00 | [7 empty] | Date Started:
Tagum City | Mankilam | 1st Eng'g. Dist. | Completed | 2020-08-03 | 2020-12-15 | 2019 | Admistration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS WATER SYSTEM DEVELOPMENT LS - P 9,750,000.00 | Installation of Shallow Tube Wells & Const. of Machinery Shed |  | 20% DF CY 2019 | Water System |  |  | Admin | Project Cost: | 1600000 | Target Completion Date: | 2020-11-30 23:59 | Program: | 1600000 | Planned: |  | Planned: | 10.59% | Planned: |  | Planned: | 100% | Planned: | 100% | No. of Persons: | 7 | Opening of BID for Negotiated 6/18,2020 to alpebel | On-going | On-going | Completed as per physical accomplishment. | Completed as per physical accomplishment. | Completed as per Program of Works
Tagum City | Mankilam | 1st Eng'g. Dist. | Completed | 2020-08-03 | 2020-12-15 | 2019 | Admistration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS WATER SYSTEM DEVELOPMENT LS - P 9,750,000.00 | [7 empty] | Project Engineer: | Aclaracion | Revised Completion Date: |  | Allotment: | 1600000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 95
Tagum City | Mankilam | 1st Eng'g. Dist. | Completed | 2020-08-03 | 2020-12-15 | 2019 | Admistration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS WATER SYSTEM DEVELOPMENT LS - P 9,750,000.00 | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: | 9.73% | Actual: |  | Actual: | 100% | Actual: | 100%
Tagum City | Mankilam | 1st Eng'g. Dist. | Completed | 2020-08-03 | 2020-12-15 | 2019 | Admistration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS WATER SYSTEM DEVELOPMENT LS - P 9,750,000.00 | [7 empty] | Duration: | 120 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | -0.86% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Tagum City | Mankilam | 1st Eng'g. Dist. | Completed | 2020-08-03 | 2020-12-15 | 2019 | Admistration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS WATER SYSTEM DEVELOPMENT LS - P 9,750,000.00 | [7 empty] | Date Allotment Released: |  | Date completed: | 2020-12-15
Tagum City | Mankilam | 1st Eng'g. Dist. | Completed | 2020-08-03 | 2020-12-15 | 2019 | Admistration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS WATER SYSTEM DEVELOPMENT LS - P 9,750,000.00 | [7 empty] | Date Started: | 2020-08-03
IGCS | Kaputian | 2nd Eng'g. Dist. | For Implementation |  |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Rural Electrification Project (Provincewide) | Rural Electrification at Sitio Sagrada, Pob. Kaputian, IGCS |  | 20% DF CY 2019 | Electrification |  |  |  | Project Cost: | 1000000 | Target Completion Date: |  | Program: | 1000000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Purchase Request # 19031251 | Purchase Request # 19031251 | For implementation | For implementation | For implementation | For implementation
IGCS | Kaputian | 2nd Eng'g. Dist. | For Implementation |  |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Rural Electrification Project (Provincewide) | [7 empty] | Project Engineer: | Buena | Revised Completion Date: |  | Allotment: | 1000000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
IGCS | Kaputian | 2nd Eng'g. Dist. | For Implementation |  |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Rural Electrification Project (Provincewide) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
IGCS | Kaputian | 2nd Eng'g. Dist. | For Implementation |  |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Rural Electrification Project (Provincewide) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
IGCS | Kaputian | 2nd Eng'g. Dist. | For Implementation |  |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Rural Electrification Project (Provincewide) | [7 empty] | Date Allotment Released: |  | Date completed:
IGCS | Kaputian | 2nd Eng'g. Dist. | For Implementation |  |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Rural Electrification Project (Provincewide) | [7 empty] | Date Started:
Tagum City | Mankilam | 1st Eng'g. Dist. | Completed | 2019-12-02 | 2020-07-31 | 2019 | Admistration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | Repair Bay of Disaster Quick Response Equipment @ PEO Compound, Gov't. Center, Mankilam, Tagum City |  | 20% DF CY 2019 | Building | 66 | sq.m | Admin | Project Cost: | 1000000 | Target Completion Date: | 2020-04-19 23:46 | Program: | 1000000 | Planned: | 100% | Planned: | 100% | Planned: | 100% | Planned: | 100% | Planned: | 100% | No. of Persons: | 5 | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per Program of Works
Tagum City | Mankilam | 1st Eng'g. Dist. | Completed | 2019-12-02 | 2020-07-31 | 2019 | Admistration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | [7 empty] | Project Engineer: | Chua/Mucas | Revised Completion Date: | 2020-05-17 23:46 | Allotment: | 1000000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 95
Tagum City | Mankilam | 1st Eng'g. Dist. | Completed | 2019-12-02 | 2020-07-31 | 2019 | Admistration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | [7 empty] | Implementor: | PEO | No. of days suspended: | 28 | Disbursement: |  | Actual: | 100% | Actual: | 100% | Actual: | 100% | Actual: | 100% | Actual: | 100%
Tagum City | Mankilam | 1st Eng'g. Dist. | Completed | 2019-12-02 | 2020-07-31 | 2019 | Admistration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | [7 empty] | Duration: | 140 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Tagum City | Mankilam | 1st Eng'g. Dist. | Completed | 2019-12-02 | 2020-07-31 | 2019 | Admistration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | [7 empty] | Date Allotment Released: | 2019-01-31 | Date completed: | 2020-06-01
Tagum City | Mankilam | 1st Eng'g. Dist. | Completed | 2019-12-02 | 2020-07-31 | 2019 | Admistration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | [7 empty] | Date Started: | 2019-12-02
New Corella | Poblacion | 1st Eng'g. Dist. | Completed | 2020-03-02 | 2020-09-10 | 2019 | Admistration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | Repair/Impv't. of Municipal Triball Hall, New Corella |  | 20% DF CY 2019 | Building |  | sq.m | Contract | Project Cost: | 500000 | Target Completion Date: | 2020-09-10 | Program: | 500000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: | 100% | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | Completed as per Program of Works
New Corella | Poblacion | 1st Eng'g. Dist. | Completed | 2020-03-02 | 2020-09-10 | 2019 | Admistration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
New Corella | Poblacion | 1st Eng'g. Dist. | Completed | 2020-03-02 | 2020-09-10 | 2019 | Admistration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual: | 100%
New Corella | Poblacion | 1st Eng'g. Dist. | Completed | 2020-03-02 | 2020-09-10 | 2019 | Admistration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Duration: | 192 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
New Corella | Poblacion | 1st Eng'g. Dist. | Completed | 2020-03-02 | 2020-09-10 | 2019 | Admistration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Date Allotment Released: |  | Date completed: | 2020-09-10
New Corella | Poblacion | 1st Eng'g. Dist. | Completed | 2020-03-02 | 2020-09-10 | 2019 | Admistration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Date Started: | 2020-03-02
Talaingod | STo. Niño | 1st Eng'g. Dist. | Completed | 2020-03-02 | 2020-10-15 | 2019 | Admistration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | Const. of Perimeter Fence at Sto. Niño Naseco Integrated School w/ Tugas Extension, Sto. Niño, Talaingod |  | 20% DF CY 2019 | Building |  | sq.m | Admin | Project Cost: | 2000000 | Target Completion Date: | 2020-06-09 23:46 | Program: | 2000000 | Planned: | 100% | Planned: | 100% | Planned: | 100% | Planned: | 100% | Planned: | 100% | No. of Persons: | 12 | On-going (Suspended last April 5, 2020 due to COVID; resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID; resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID; resumption order dated May 4, 2020) | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per Program of Works
Talaingod | STo. Niño | 1st Eng'g. Dist. | Completed | 2020-03-02 | 2020-10-15 | 2019 | Admistration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | [7 empty] | Project Engineer: | Torrecampo | Revised Completion Date: | 2020-10-15 23:46 | Allotment: | 2000000 | Revised: | 55.86% | Revised: | 78.13% | Revised: | 92% | Revised: |  | Revised: |  | No. of Man-days: | 180
Talaingod | STo. Niño | 1st Eng'g. Dist. | Completed | 2020-03-02 | 2020-10-15 | 2019 | Admistration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | [7 empty] | Implementor: | PEO | No. of days suspended: | 28 | Disbursement: | 1117200 | Actual: | 55.86% | Actual: | 78.13% | Actual: | 98.96% | Actual: | 100% | Actual: | 100%
Talaingod | STo. Niño | 1st Eng'g. Dist. | Completed | 2020-03-02 | 2020-10-15 | 2019 | Admistration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | [7 empty] | Duration: | 100 | No. of days extended: | 100 |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 6.96% | Slippage: | 0% | Slippage: | 0%
Talaingod | STo. Niño | 1st Eng'g. Dist. | Completed | 2020-03-02 | 2020-10-15 | 2019 | Admistration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | [7 empty] | Date Allotment Released: | 2019-06-19 | Date completed: | 2020-10-15
Talaingod | STo. Niño | 1st Eng'g. Dist. | Completed | 2020-03-02 | 2020-10-15 | 2019 | Admistration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | [7 empty] | Date Started: | 2020-03-02
Talaingod | Sto. Niño | 1st Eng'g. Dist. | On-going | 2020-08-24 |  | 2019 | Admistration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | Const. of IP Women's Multi-Purpose Bldg., Cabidiangan, Sto. Niño, Talaingod |  | 20% DF CY 2019 | Building |  |  | Admin | Project Cost: | 2000000 | Target Completion Date: | 2020-12-07 | Program: | 2000000 | Planned: |  | Planned: |  | Planned: | 14.65% | Planned: | 14.65% | Planned: | 100% | No. of Persons: | 10 | Awarded to Alpebel Builders | On-going | On-going | On-going | On-going | Slippage is due to intermittent rain on site
Talaingod | Sto. Niño | 1st Eng'g. Dist. | On-going | 2020-08-24 |  | 2019 | Admistration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | [7 empty] | Project Engineer: | Torrecampo | Revised Completion Date: | 2021-01-11 | Allotment: | 2000000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: | 89.76% | No. of Man-days: | 300
Talaingod | Sto. Niño | 1st Eng'g. Dist. | On-going | 2020-08-24 |  | 2019 | Admistration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | [7 empty] | Implementor: | ALPEBEL BUILDERS & SUPPLY CORP. | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: | 14.65% | Actual: | 14.65% | Actual: | 47.74%
Talaingod | Sto. Niño | 1st Eng'g. Dist. | On-going | 2020-08-24 |  | 2019 | Admistration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | [7 empty] | Duration: | 105 | No. of days extended: | 35 |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | -42.02%
Talaingod | Sto. Niño | 1st Eng'g. Dist. | On-going | 2020-08-24 |  | 2019 | Admistration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | [7 empty] | Date Allotment Released: | 2019-05-15 | Date completed:
Talaingod | Sto. Niño | 1st Eng'g. Dist. | On-going | 2020-08-24 |  | 2019 | Admistration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | [7 empty] | Date Started: | 2020-08-24
Talaingod | Gupitan | 1st Eng'g. Dist. | Re-aligned GIDAS |  |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | Const. of Multi-Purpose Hall Center (Cultural Heritage in Ancestral Domain of Ata-Manobo) |  | 20% DF CY 2019 | Building |  |  | Admin | Project Cost: | 3000000 | Target Completion Date: |  | Program: | 3000000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Fund re-aligned to GIDAS projects | Fund re-aligned to GIDAS projects | Fund re-aligned to GIDAS projects |  |  | Fund re-aligned to GIDAS projects
Talaingod | Gupitan | 1st Eng'g. Dist. | Re-aligned GIDAS |  |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 3000000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
Talaingod | Gupitan | 1st Eng'g. Dist. | Re-aligned GIDAS |  |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
Talaingod | Gupitan | 1st Eng'g. Dist. | Re-aligned GIDAS |  |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Talaingod | Gupitan | 1st Eng'g. Dist. | Re-aligned GIDAS |  |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Talaingod | Gupitan | 1st Eng'g. Dist. | Re-aligned GIDAS |  |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | [7 empty] | Date Started:
Tagum City | Mankilam | 1st Eng'g. Dist. | Completed | 2020-02-03 | 2020-08-14 | 2019 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | Extension of PAGRO Training Center & Ground Dev't., Gov't. Center, Mankilam, Tagum City |  | 20% DF CY 2019 | Building |  | sq.m | Admin | Project Cost: | 1000000 | Target Completion Date: | 2020-04-23 | Program: | 1000000 | Planned: | 100% | Planned: | 100% | Planned: | 100% | Planned: | 100% | Planned: | 100% | No. of Persons: | 5 | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per Program of Works
Tagum City | Mankilam | 1st Eng'g. Dist. | Completed | 2020-02-03 | 2020-08-14 | 2019 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | [7 empty] | Project Engineer: | Chua/Mugas | Revised Completion Date: | 2020-05-21 | Allotment: | 1000000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 57
Tagum City | Mankilam | 1st Eng'g. Dist. | Completed | 2020-02-03 | 2020-08-14 | 2019 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | [7 empty] | Implementor: | PEO | No. of days suspended: | 28 | Disbursement: |  | Actual: | 100% | Actual: | 100% | Actual: | 100% | Actual: | 100% | Actual: | 100%
Tagum City | Mankilam | 1st Eng'g. Dist. | Completed | 2020-02-03 | 2020-08-14 | 2019 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | [7 empty] | Duration: | 80 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Tagum City | Mankilam | 1st Eng'g. Dist. | Completed | 2020-02-03 | 2020-08-14 | 2019 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | [7 empty] | Date Allotment Released: | 2019-07-26 | Date completed: | 2020-08-14
Tagum City | Mankilam | 1st Eng'g. Dist. | Completed | 2020-02-03 | 2020-08-14 | 2019 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | [7 empty] | Date Started: | 2020-02-03
Tagum City | Mankilam | 1st Eng'g. Dist. | Re-aligned GIDAS |  |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | Construction of Abilidad Training Center, Gov't. Center, Mankilam, Tagum City |  | 20% DF CY 2019 | Building |  |  |  | Project Cost: | 7000000 | Target Completion Date: |  | Program: | 7000000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Fund re-aligned to GIDAS projects | Fund re-aligned to GIDAS projects | Fund re-aligned to GIDAS projects | Fund re-aligned to GIDAS projects | Fund re-aligned to GIDAS projects | Fund re-aligned to GIDAS projects
Tagum City | Mankilam | 1st Eng'g. Dist. | Re-aligned GIDAS |  |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 7000000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
Tagum City | Mankilam | 1st Eng'g. Dist. | Re-aligned GIDAS |  |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
Tagum City | Mankilam | 1st Eng'g. Dist. | Re-aligned GIDAS |  |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Tagum City | Mankilam | 1st Eng'g. Dist. | Re-aligned GIDAS |  |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Tagum City | Mankilam | 1st Eng'g. Dist. | Re-aligned GIDAS |  |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | [7 empty] | Date Started:
New Corella | Suawon | 1st Eng'g. Dist. | Completed | 2019-12-09 | 2020-07-31 | 2019 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | Const. of 1 CL Bldg. @ Suawon ES, New Corella |  | 20% DF CY 2019 | Building | 82.65 | sq.m | Admin | Project Cost: | 1000000 | Target Completion Date: | 2020-04-21 23:46 | Program: | 1000000 | Planned: | 60.44% | Planned: | 60.44% | Planned: | 60.44% | Planned: | 100% | Planned: | 100% | No. of Persons: | 7 | On-going (Suspended last April 5, 2020 due to COVID; resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID; resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID; resumption order dated May 4, 2020) | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per Program of Works
New Corella | Suawon | 1st Eng'g. Dist. | Completed | 2019-12-09 | 2020-07-31 | 2019 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | [7 empty] | Project Engineer: | Miraflor | Revised Completion Date: | 2020-05-19 23:46 | Allotment: | 1000000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 147
New Corella | Suawon | 1st Eng'g. Dist. | Completed | 2019-12-09 | 2020-07-31 | 2019 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | [7 empty] | Implementor: | PEO | No. of days suspended: | 28 | Disbursement: |  | Actual: | 60.44% | Actual: | 60.44% | Actual: | 60.44% | Actual: | 100% | Actual: | 100%
New Corella | Suawon | 1st Eng'g. Dist. | Completed | 2019-12-09 | 2020-07-31 | 2019 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | [7 empty] | Duration: | 135 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
New Corella | Suawon | 1st Eng'g. Dist. | Completed | 2019-12-09 | 2020-07-31 | 2019 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | [7 empty] | Date Allotment Released: | 2020-06-07 | Date completed: | 2020-07-31
New Corella | Suawon | 1st Eng'g. Dist. | Completed | 2019-12-09 | 2020-07-31 | 2019 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | [7 empty] | Date Started: | 2019-12-09
San Isidro | Sabangan | 1st Eng'g. Dist. | Completed | 2019-12-02 | 2020-06-15 | 2019 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | Const. of Municipal Tribal Hall, San Isidro |  | 20% DF CY 2019 | Building | 42 | sq.m | Admin | Project Cost: | 500000 | Target Completion Date: | 2020-02-19 23:46 | Program: | 500000 | Planned: | 100% | Planned: | 100% | Planned: | 100% | Planned: | 100% | Planned: | 100% | No. of Persons: | 8 | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per Program of Works
San Isidro | Sabangan | 1st Eng'g. Dist. | Completed | 2019-12-02 | 2020-06-15 | 2019 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | [7 empty] | Project Engineer: | Aclaracion | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 176
San Isidro | Sabangan | 1st Eng'g. Dist. | Completed | 2019-12-02 | 2020-06-15 | 2019 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | [7 empty] | Implementor: | PEO | No. of days suspended: | 28 | Disbursement: |  | Actual: | 100% | Actual: | 100% | Actual: | 100% | Actual: | 100% | Actual: | 100%
San Isidro | Sabangan | 1st Eng'g. Dist. | Completed | 2019-12-02 | 2020-06-15 | 2019 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | [7 empty] | Duration: | 80 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
San Isidro | Sabangan | 1st Eng'g. Dist. | Completed | 2019-12-02 | 2020-06-15 | 2019 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | [7 empty] | Date Allotment Released: | 2019-01-15 | Date completed: | 2020-06-15
San Isidro | Sabangan | 1st Eng'g. Dist. | Completed | 2019-12-02 | 2020-06-15 | 2019 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | [7 empty] | Date Started: | 2019-12-02
San Isidro | Sabangan | 1st Eng'g. Dist. | Completed | 2019-12-02 | 2020-03-31 | 2019 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | Const. of Quail House (PDNSC Ext. Campus), Sto. Niño, Talaingod |  | 20% DF CY 2019 | Building | 42 | sq.m | Admin | Project Cost: | 750000 | Target Completion Date: | 2020-02-19 23:46 | Program: | 750000 | Planned: | 100% | Planned: | 100% | Planned: | 100% | Planned: | 100% | Planned: | 100% | No. of Persons: | 8 | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per Program of Works
San Isidro | Sabangan | 1st Eng'g. Dist. | Completed | 2019-12-02 | 2020-03-31 | 2019 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | [7 empty] | Project Engineer: | Aclaracion | Revised Completion Date: |  | Allotment: | 750000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 176
San Isidro | Sabangan | 1st Eng'g. Dist. | Completed | 2019-12-02 | 2020-03-31 | 2019 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: | 100% | Actual: | 100% | Actual: | 100% | Actual: | 100% | Actual: | 100%
San Isidro | Sabangan | 1st Eng'g. Dist. | Completed | 2019-12-02 | 2020-03-31 | 2019 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | [7 empty] | Duration: | 80 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
San Isidro | Sabangan | 1st Eng'g. Dist. | Completed | 2019-12-02 | 2020-03-31 | 2019 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | [7 empty] | Date Allotment Released: | 2019-01-15 | Date completed: | 2020-03-31
San Isidro | Sabangan | 1st Eng'g. Dist. | Completed | 2019-12-02 | 2020-03-31 | 2019 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | [7 empty] | Date Started: | 2019-12-02
Sto. Tomas | Lunga-og | 2nd Eng'g. Dist. | Completed | 2019-10-16 | 2020-02-29 | 2019 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | Completion of Perimeter Steel Fence at Lunga-og ES Perimeter Fence, Sto. Tomas |  | 20% DF CY 2019 | Fence |  | km | Admin | Project Cost: | 1630000 | Target Completion Date: | 2020-02-29 | Program: | 1630000 | Planned: | 100% | Planned: | 100% | Planned: | 100% | Planned: | 100% | Planned: | 100% | No. of Persons: | 1 | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per Program of Works
Sto. Tomas | Lunga-og | 2nd Eng'g. Dist. | Completed | 2019-10-16 | 2020-02-29 | 2019 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | [7 empty] | Project Engineer: | Azotes | Revised Completion Date: |  | Allotment: | 1630000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 4
Sto. Tomas | Lunga-og | 2nd Eng'g. Dist. | Completed | 2019-10-16 | 2020-02-29 | 2019 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: | 100% | Actual: | 100% | Actual: | 100% | Actual: | 100% | Actual: | 100%
Sto. Tomas | Lunga-og | 2nd Eng'g. Dist. | Completed | 2019-10-16 | 2020-02-29 | 2019 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Sto. Tomas | Lunga-og | 2nd Eng'g. Dist. | Completed | 2019-10-16 | 2020-02-29 | 2019 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | [7 empty] | Date Allotment Released: |  | Date completed: | 2020-02-29
Sto. Tomas | Lunga-og | 2nd Eng'g. Dist. | Completed | 2019-10-16 | 2020-02-29 | 2019 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | [7 empty] | Date Started: | 2019-10-16
Carmen | Ising | 2nd Eng'g. Dist. | On-going | 2020-07-24 |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | Const. of DDN Hospital Carmen Zone Annex Bldg. Phase 2, |  | 20% DF CY 2019 | Building |  | sq.m | Contract | Project Cost: | 3620000 | Target Completion Date: | 2020-10-24 | Program: | 3620000 | Planned: |  | Planned: |  | Planned: | 10.51% | Planned: | 10.15% | Planned: | 10.15% | No. of Persons: | 15 | On-going | On-going | On-going | On-going | On-going | On-going
Carmen | Ising | 2nd Eng'g. Dist. | On-going | 2020-07-24 |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | [7 empty] | Project Engineer: | Azotes | Revised Completion Date: |  | Allotment: | 3620000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 330
Carmen | Ising | 2nd Eng'g. Dist. | On-going | 2020-07-24 |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | [7 empty] | Implementor: | Digos Constrak Corp/ | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: | 8.12% | Actual: | 8.12% | Actual: | 8.12%
Carmen | Ising | 2nd Eng'g. Dist. | On-going | 2020-07-24 |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | [7 empty] | Duration: | 92 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | -2.39% | Slippage: | -2.03% | Slippage: | -2.03%
Carmen | Ising | 2nd Eng'g. Dist. | On-going | 2020-07-24 |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | [7 empty] | Date Allotment Released: | 2019-06-28 | Date completed:
Carmen | Ising | 2nd Eng'g. Dist. | On-going | 2020-07-24 |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | [7 empty] | Date Started: | 2020-07-24
New Corella | Poblacion | 1st Eng'g. Dist. | Procurement on process |  |  | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Residential Care Facilities | Const. of Multi-Purpose Covered Court/Evacuation Center Ph. I, Duterte St., Poblacion, New Corella |  | 20% DF CY 2019 | Building |  | sq.m | Admin | Project Cost: | 2000000 | Target Completion Date: | 0 | Program: | 2000000 | Planned: | 84.4% | Planned: | 100% | Planned: | 100% | Planned: |  | Planned: |  | No. of Persons: |  | On-going | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. |  |  | Procurement on process
New Corella | Poblacion | 1st Eng'g. Dist. | Procurement on process |  |  | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Residential Care Facilities | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 2000000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
New Corella | Poblacion | 1st Eng'g. Dist. | Procurement on process |  |  | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Residential Care Facilities | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: | 84.4% | Actual: | 100% | Actual: | 100% | Actual: |  | Actual:
New Corella | Poblacion | 1st Eng'g. Dist. | Procurement on process |  |  | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Residential Care Facilities | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
New Corella | Poblacion | 1st Eng'g. Dist. | Procurement on process |  |  | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Residential Care Facilities | [7 empty] | Date Allotment Released: |  | Date completed:
New Corella | Poblacion | 1st Eng'g. Dist. | Procurement on process |  |  | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Residential Care Facilities | [7 empty] | Date Started:
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2020-10-05 |  | 2019 | Contract | . | Anti - Crime & Government Itegration Project | Construction of Bahay Silangan for Reformation of Drug Personalities within The Military Camp/barracks, Brgy. Mankilam, Tagum City |  | 20% DF CY 2019 | Building | 126 | sq.m | Contract | Project Cost: | 5000000 | Target Completion Date: | 2021-04-13 | Program: | 5000000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: | 34.66% | No. of Persons: | 16 | Abstract #0620202232 - Post Qualification on process (ZULAR-A) | Abstract #0620202232 - Post Qualification on process (ZULAR-A) | Abstract #0620202232 - Post Qualification on process (ZULAR-A) | Abstract #0620202232 - Post Qualification on process (ZULAR-A) | Abstract #0620202232 - Post Qualification on process (ZULAR-A) | On-going
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2020-10-05 |  | 2019 | Contract | . | Anti - Crime & Government Itegration Project | [7 empty] | Project Engineer: | Torrecampo | Revised Completion Date: |  | Allotment: | 5000000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 330
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2020-10-05 |  | 2019 | Contract | . | Anti - Crime & Government Itegration Project | [7 empty] | Implementor: | Zular-AZ Const. and Suppy | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual: | 53.71%
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2020-10-05 |  | 2019 | Contract | . | Anti - Crime & Government Itegration Project | [7 empty] | Duration: | 190 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 19.05%
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2020-10-05 |  | 2019 | Contract | . | Anti - Crime & Government Itegration Project | [7 empty] | Date Allotment Released: |  | Date completed:
Tagum City | Mankilam | 1st Eng'g. Dist. | On-going | 2020-10-05 |  | 2019 | Contract | . | Anti - Crime & Government Itegration Project | [7 empty] | Date Started: | 2020-10-05
Panabo City | Quezon | 2nd Eng'g. Dist. | Re-aligned |  |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | Impv't./Beautification of Brgy. Grounds, Quezon, Panabo City |  | 20% DF CY 2019 (STIMULUS | Ground dev't. |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Re aligned to other stimulus projects that needs additional funding | Re aligned to other stimulus projects that needs additional funding | Re aligned to other stimulus projects that needs additional funding | Re aligned to other stimulus projects that needs additional funding | Re aligned to other stimulus projects that needs additional funding | Re aligned to other stimulus projects that needs additional funding
Panabo City | Quezon | 2nd Eng'g. Dist. | Re-aligned |  |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
Panabo City | Quezon | 2nd Eng'g. Dist. | Re-aligned |  |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
Panabo City | Quezon | 2nd Eng'g. Dist. | Re-aligned |  |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Panabo City | Quezon | 2nd Eng'g. Dist. | Re-aligned |  |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Panabo City | Quezon | 2nd Eng'g. Dist. | Re-aligned |  |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Started:
Panabo City | New Pandan | 2nd Eng'g. Dist. | Re-aligned to COVID |  |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | Desilting of Canal, New Pandan, Panabo City |  | 20% DF CY 2019 (STIMULUS | Desiltation |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
Panabo City | New Pandan | 2nd Eng'g. Dist. | Re-aligned to COVID |  |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
Panabo City | New Pandan | 2nd Eng'g. Dist. | Re-aligned to COVID |  |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
Panabo City | New Pandan | 2nd Eng'g. Dist. | Re-aligned to COVID |  |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: |  | Slippage: |  | Slippage:
Panabo City | New Pandan | 2nd Eng'g. Dist. | Re-aligned to COVID |  |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Panabo City | New Pandan | 2nd Eng'g. Dist. | Re-aligned to COVID |  |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Started:
San Isidro | Sabangan | 1st Eng'g. Dist. | Re-aligned to COVID |  |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | Const. of 2 Storey Multi-Purpose Hall Ph. 3 (Brgy. Hall), Poblacion, New Corella |  | SB NO. 4 CY 2019 (STIMULUS) | Building | 42 | sq.m | Admin | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: | 100% | Planned: | 100% | Planned: | 100% | Planned: | 100% | Planned: |  | No. of Persons: |  | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
San Isidro | Sabangan | 1st Eng'g. Dist. | Re-aligned to COVID |  |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
San Isidro | Sabangan | 1st Eng'g. Dist. | Re-aligned to COVID |  |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: | 100% | Actual: | 100% | Actual: | 100% | Actual: | 100% | Actual:
San Isidro | Sabangan | 1st Eng'g. Dist. | Re-aligned to COVID |  |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
San Isidro | Sabangan | 1st Eng'g. Dist. | Re-aligned to COVID |  |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
San Isidro | Sabangan | 1st Eng'g. Dist. | Re-aligned to COVID |  |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | [7 empty] | Date Started:
Carmen | Mabaus | 2nd Eng'g. Dist. | Completed | 2019-02-20 |  | 2019 | MLGU | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | Const. Canal Lining , Mabaus, Carmen |  | 20% DF CY 2019 (STIMULUS) | Canal lining |  |  | MLGU | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Fund transferred to LGU March 28, 2019 | Fund transferred to LGU March 28, 2019 | Completed (Implemented by MLGU, since transfer of fund ) | Completed (Implemented by MLGU, since transfer of fund ) | Completed (Implemented by MLGU, since transfer of fund ) | Completed (Implemented by MLGU, since transfer of fund )
Carmen | Mabaus | 2nd Eng'g. Dist. | Completed | 2019-02-20 |  | 2019 | MLGU | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
Carmen | Mabaus | 2nd Eng'g. Dist. | Completed | 2019-02-20 |  | 2019 | MLGU | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
Carmen | Mabaus | 2nd Eng'g. Dist. | Completed | 2019-02-20 |  | 2019 | MLGU | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Carmen | Mabaus | 2nd Eng'g. Dist. | Completed | 2019-02-20 |  | 2019 | MLGU | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Allotment Released: | 2019-02-20 | Date completed:
Carmen | Mabaus | 2nd Eng'g. Dist. | Completed | 2019-02-20 |  | 2019 | MLGU | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Started:
Tagum City | Cuambogan | 1st Eng'g. Dist. | Completed | 2020-07-15 | 2020-08-07 | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | Rehab. Of Multi-Purpose Hall, Cuambogan, Tagum City |  | 20% DF CY 2019 (STIMULUS) | Building |  |  | Contract | Project Cost: | 500000 | Target Completion Date: | 2020-12-12 | Program: | 500000 | Planned: |  | Planned: | 100% | Planned: | 100% | Planned: | 100% | Planned: | 100% | No. of Persons: |  | On-going | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per Program of Works
Tagum City | Cuambogan | 1st Eng'g. Dist. | Completed | 2020-07-15 | 2020-08-07 | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Project Engineer: | Juan | Revised Completion Date: | 2020-12-12 | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
Tagum City | Cuambogan | 1st Eng'g. Dist. | Completed | 2020-07-15 | 2020-08-07 | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Implementor: | JJR Construction | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: | 100% | Actual: | 100% | Actual: | 100% | Actual: | 100%
Tagum City | Cuambogan | 1st Eng'g. Dist. | Completed | 2020-07-15 | 2020-08-07 | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Duration: | 150 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Tagum City | Cuambogan | 1st Eng'g. Dist. | Completed | 2020-07-15 | 2020-08-07 | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Allotment Released: | 2019-09-10 | Date completed: | 2020-08-07
Tagum City | Cuambogan | 1st Eng'g. Dist. | Completed | 2020-07-15 | 2020-08-07 | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Started: | 2020-07-15
San Isidro | Sto. Niño | 1st Eng'g. Dist. | Completed | 2020-01-06 | 2020-05-27 | 2019 | MLGU | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | Rehab. Of Multi-Purpose Hall , Sto. Niño, San Isidro |  | 20% DF CY 2019 (STIMULUS) | Building |  |  | Contract | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | Planned: | 100% | Planned: | 100% | Planned: | 100% | Planned: | 100% | No. of Persons: |  | On-going | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed (Implemented by MLGU, since transfer of fund ) | Completed (Implemented by MLGU, since transfer of fund ) | Completed (Implemented by MLGU, since transfer of fund )
San Isidro | Sto. Niño | 1st Eng'g. Dist. | Completed | 2020-01-06 | 2020-05-27 | 2019 | MLGU | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
San Isidro | Sto. Niño | 1st Eng'g. Dist. | Completed | 2020-01-06 | 2020-05-27 | 2019 | MLGU | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: | 100% | Actual: | 100% | Actual: | 100% | Actual: | 100%
San Isidro | Sto. Niño | 1st Eng'g. Dist. | Completed | 2020-01-06 | 2020-05-27 | 2019 | MLGU | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
San Isidro | Sto. Niño | 1st Eng'g. Dist. | Completed | 2020-01-06 | 2020-05-27 | 2019 | MLGU | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Allotment Released: |  | Date completed: | 2020-05-27
San Isidro | Sto. Niño | 1st Eng'g. Dist. | Completed | 2020-01-06 | 2020-05-27 | 2019 | MLGU | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Started: | 2020-01-06
Tagum City | San Isidro | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-06-05 | 2019 | Administartion | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | Const. of Women Livelihood Center, San Isidro, Tagum City |  | 20% DF CY 2019 (STIMULUS) | Building | 36.5 | sq.m | Admin | Project Cost: | 500000 | Target Completion Date: | 2020-03-21 23:46 | Program: | 500000 | Planned: | 100% | Planned: | 100% | Planned: | 100% | Planned: | 100% | Planned: | 100% | No. of Persons: | 10 | Completed as per physical accomplishment. Financial documents still on process | Completed as per physical accomplishment. Financial documents still on process | Completed as per physical accomplishment. Financial documents still on process | Completed as per physical accomplishment. Financial documents still on process | Completed as per physical accomplishment. Financial documents still on process | Completed as per Program of Works
Tagum City | San Isidro | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-06-05 | 2019 | Administartion | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Project Engineer: | Juan | Revised Completion Date: | 2020-06-05 23:46 | Allotment: | 500000 | Revised: | 100% | Revised: | 100% | Revised: | 100% | Revised: | 100% | Revised: | 100% | No. of Man-days: | 150
Tagum City | San Isidro | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-06-05 | 2019 | Administartion | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Implementor: | PEO | No. of days suspended: | 28 | Disbursement: |  | Actual: | 100% | Actual: | 100% | Actual: | 100% | Actual: | 100% | Actual: | 100%
Tagum City | San Isidro | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-06-05 | 2019 | Administartion | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Duration: | 80 | No. of days extended: | 48 |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Tagum City | San Isidro | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-06-05 | 2019 | Administartion | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Allotment Released: | 2019-05-29 | Date completed: | 2020-06-05
Tagum City | San Isidro | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-06-05 | 2019 | Administartion | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Started: | 2020-01-02
Tagum City | Apokon | 1st Eng'g. Dist. | On-going | 2020-10-19 |  | 2019 | Administartion | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | Rehab. Of Brgy. Health Center, Apokon, Tagum City |  | 20% DF CY 2019 (STIMULUS) | Building |  |  |  | Project Cost: | 500000 | Target Completion Date: | 2020-12-07 23:46 | Program: | 500000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: | 100% | No. of Persons: | 8 | For implementation (The brgy. council agreed not to pursue with the project if it will not be completed and needs additional funds) | For implementation (The brgy. council agreed not to pursue with the project if it will not be completed and needs additional funds) | For implementation (The brgy. council agreed not to pursue with the project if it will not be completed and needs additional funds) | For implementation (The brgy. council agreed not to pursue with the project if it will not be completed and needs additional funds) | For implementation (The brgy. council agreed not to pursue with the project if it will not be completed and needs additional funds) | On-going (Slippage due to pending of installation of roofing works. (Job Order)
Tagum City | Apokon | 1st Eng'g. Dist. | On-going | 2020-10-19 |  | 2019 | Administartion | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Project Engineer: | Torrecampo | Revised Completion Date: | 2021-01-16 23:46 | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: | 76.13% | No. of Man-days: | 120
Tagum City | Apokon | 1st Eng'g. Dist. | On-going | 2020-10-19 |  | 2019 | Administartion | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual: | 75.11%
Tagum City | Apokon | 1st Eng'g. Dist. | On-going | 2020-10-19 |  | 2019 | Administartion | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Duration: | 50 | No. of days extended: | 40 |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | -1.02%
Tagum City | Apokon | 1st Eng'g. Dist. | On-going | 2020-10-19 |  | 2019 | Administartion | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Allotment Released: | 2019-03-25 | Date completed:
Tagum City | Apokon | 1st Eng'g. Dist. | On-going | 2020-10-19 |  | 2019 | Administartion | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Started: | 2020-10-19
Sto. Tomas | Bobongon | 2nd Eng'g. Dist. | Re-aligned |  |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | Const. of Evacuation Center, Bobongon, Sto. Tomas |  | 20% DF CY 2019 (STIMULUS | Building |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: | 100% | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Re aligned to other stimulus projects that needs additional funding | Re aligned to other stimulus projects that needs additional funding | Re aligned to other stimulus projects that needs additional funding | Re aligned to other stimulus projects that needs additional funding | Re aligned to other stimulus projects that needs additional funding | Re aligned to other stimulus projects that needs additional funding
Sto. Tomas | Bobongon | 2nd Eng'g. Dist. | Re-aligned |  |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
Sto. Tomas | Bobongon | 2nd Eng'g. Dist. | Re-aligned |  |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: | 100% | Actual: |  | Actual: |  | Actual: |  | Actual:
Sto. Tomas | Bobongon | 2nd Eng'g. Dist. | Re-aligned |  |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Sto. Tomas | Bobongon | 2nd Eng'g. Dist. | Re-aligned |  |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Sto. Tomas | Bobongon | 2nd Eng'g. Dist. | Re-aligned |  |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Started:
San Isidro | Pinamuno | 1st Eng'g. Dist. | Procurement on process |  |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | Rehab. Of Water System at Purok Cabang & Mangga , Pinamuno, San Isidro |  | 20% DF CY 2019 (STIMULUS) | Water System |  |  | Contract | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | PO# 2020010025 (RLHV) | PO# 2020010025 (RLHV) | PO# 2020010025 (RLHV) | PO# 2020010025 (RLHV) | PO# 2020010025 (RLHV) | PO# 2020010025 (RLHV)
San Isidro | Pinamuno | 1st Eng'g. Dist. | Procurement on process |  |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
San Isidro | Pinamuno | 1st Eng'g. Dist. | Procurement on process |  |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
San Isidro | Pinamuno | 1st Eng'g. Dist. | Procurement on process |  |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
San Isidro | Pinamuno | 1st Eng'g. Dist. | Procurement on process |  |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Allotment Released: | 2019-12-06 | Date completed:
San Isidro | Pinamuno | 1st Eng'g. Dist. | Procurement on process |  |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Started:
Tagum City | Bincungan | 1st Eng'g. Dist. | Completed | 2020-09-16 | 2020-10-08 | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | Const. of Drainage Canal, Bincungan, Tagum City |  | 20% DF CY 2019 (STIMULUS) | Drainage |  |  | Contract | Project Cost: | 500000 | Target Completion Date: | 2021-02-13 | Program: | 500000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: | 100% | No. of Persons: |  | For implementation | For implementation | For implementation | For implementation | For implementation | Completed as per Program of Works
Tagum City | Bincungan | 1st Eng'g. Dist. | Completed | 2020-09-16 | 2020-10-08 | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Project Engineer: | Quirante | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
Tagum City | Bincungan | 1st Eng'g. Dist. | Completed | 2020-09-16 | 2020-10-08 | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Implementor: | JJR Construction | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual: | 100%
Tagum City | Bincungan | 1st Eng'g. Dist. | Completed | 2020-09-16 | 2020-10-08 | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Duration: | 150 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Tagum City | Bincungan | 1st Eng'g. Dist. | Completed | 2020-09-16 | 2020-10-08 | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Allotment Released: | 2019-09-10 | Date completed: | 2020-10-08
Tagum City | Bincungan | 1st Eng'g. Dist. | Completed | 2020-09-16 | 2020-10-08 | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Started: | 2020-09-16
Tagum City | Busaon | 1st Eng'g. Dist. | Completed | 2020-07-15 | 2020-11-04 | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | Completion. of Water System , Busaon, Tagum City |  | 20% DF CY 2019 (STIMULUS) | Water System |  |  | Contract | Project Cost: | 500000 | Target Completion Date: | 2020-12-12 | Program: | 500000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: | 100% | No. of Persons: |  | For implementation | For implementation | For implementation | For implementation | For implementation | Completed as per Program of Works
Tagum City | Busaon | 1st Eng'g. Dist. | Completed | 2020-07-15 | 2020-11-04 | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Project Engineer: | Quirante | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
Tagum City | Busaon | 1st Eng'g. Dist. | Completed | 2020-07-15 | 2020-11-04 | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Implementor: | JJR Construction | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual: | 100%
Tagum City | Busaon | 1st Eng'g. Dist. | Completed | 2020-07-15 | 2020-11-04 | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Duration: | 150 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Tagum City | Busaon | 1st Eng'g. Dist. | Completed | 2020-07-15 | 2020-11-04 | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Allotment Released: | 2019-09-10 | Date completed: | 2020-11-04
Tagum City | Busaon | 1st Eng'g. Dist. | Completed | 2020-07-15 | 2020-11-04 | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Started: | 2020-07-15
Tagum City | Magugpo North | 1st Eng'g. Dist. | Completed | 2020-07-15 | 2020-07-30 | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | Rehab. of Evacuation Center, Magugpo North, Tagum City |  | 20% DF CY 2019 (STIMULUS) | Building |  |  | Contract | Project Cost: | 500000 | Target Completion Date: | 2020-12-12 | Program: | 500000 | Planned: | 100% | Planned: | 100% | Planned: | 100% | Planned: | 100% | Planned: | 100% | No. of Persons: |  | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per Program of Works
Tagum City | Magugpo North | 1st Eng'g. Dist. | Completed | 2020-07-15 | 2020-07-30 | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Project Engineer: | Juan | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
Tagum City | Magugpo North | 1st Eng'g. Dist. | Completed | 2020-07-15 | 2020-07-30 | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Implementor: | JJR Construction | No. of days suspended: |  | Disbursement: |  | Actual: | 100% | Actual: | 100% | Actual: | 100% | Actual: | 100% | Actual: | 100%
Tagum City | Magugpo North | 1st Eng'g. Dist. | Completed | 2020-07-15 | 2020-07-30 | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Duration: | 150 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Tagum City | Magugpo North | 1st Eng'g. Dist. | Completed | 2020-07-15 | 2020-07-30 | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Allotment Released: | 2019-09-10 | Date completed: | 2020-07-30
Tagum City | Magugpo North | 1st Eng'g. Dist. | Completed | 2020-07-15 | 2020-07-30 | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Started: | 2020-07-15
Tagum City | Magugpo North | 1st Eng'g. Dist. | Completed | 2020-07-16 | 2020-10-30 | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | Rehab. of Evacuation Center, Mankilam, Tagum City |  | 20% DF CY 2019 (STIMULUS) | Building |  |  | Contract | Project Cost: | 500000 | Target Completion Date: | 2020-10-30 | Program: | 500000 | Planned: | 100% | Planned: | 100% | Planned: | 100% | Planned: | 100% | Planned: | 100% | No. of Persons: |  | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per Program of Works
Tagum City | Magugpo North | 1st Eng'g. Dist. | Completed | 2020-07-16 | 2020-10-30 | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Project Engineer: | Juan | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
Tagum City | Magugpo North | 1st Eng'g. Dist. | Completed | 2020-07-16 | 2020-10-30 | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Implementor: | JJR Construction | No. of days suspended: |  | Disbursement: |  | Actual: | 100% | Actual: | 100% | Actual: | 100% | Actual: | 100% | Actual: | 100%
Tagum City | Magugpo North | 1st Eng'g. Dist. | Completed | 2020-07-16 | 2020-10-30 | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Duration: | 106 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Tagum City | Magugpo North | 1st Eng'g. Dist. | Completed | 2020-07-16 | 2020-10-30 | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Allotment Released: |  | Date completed: | 2020-10-30
Tagum City | Magugpo North | 1st Eng'g. Dist. | Completed | 2020-07-16 | 2020-10-30 | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Started: | 2020-07-16
madaum | Tagum | 1st Eng'g. Dist. | Completed | 2019-11-18 | 2020-01-24 | 2019 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | Rehab. of Evacuation Center, Madaum, Tagum City |  | 20% DF CY 2019 (STIMULUS) | Building |  | sq.m | Admin | Project Cost: | 500000 | Target Completion Date: | 2020-01-24 | Program: | 500000 | Planned: | 100% | Planned: | 100% | Planned: | 100% | Planned: | 100% | Planned: | 100% | No. of Persons: | 4 | For implementation | On-going | On-going | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per Program of Works
madaum | Tagum | 1st Eng'g. Dist. | Completed | 2019-11-18 | 2020-01-24 | 2019 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 88
madaum | Tagum | 1st Eng'g. Dist. | Completed | 2019-11-18 | 2020-01-24 | 2019 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: | 100% | Actual: | 100% | Actual: | 100% | Actual: | 100% | Actual: | 100%
madaum | Tagum | 1st Eng'g. Dist. | Completed | 2019-11-18 | 2020-01-24 | 2019 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | [7 empty] | Duration: | 67 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
madaum | Tagum | 1st Eng'g. Dist. | Completed | 2019-11-18 | 2020-01-24 | 2019 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | [7 empty] | Date Allotment Released: |  | Date completed: | 2020-01-24
madaum | Tagum | 1st Eng'g. Dist. | Completed | 2019-11-18 | 2020-01-24 | 2019 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | [7 empty] | Date Started: | 2019-11-18
Tagum City | New Balamban | 1st Eng'g. Dist. | Completed | 2020-09-01 | 2020-10-02 | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | Rehab. of Evacuation Center, New Balambam, Tagum City |  | 20% DF CY 2019 (STIMULUS) | Building |  |  | Contract | Project Cost: | 500000 | Target Completion Date: | 2021-01-29 | Program: | 500000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: | 100% | No. of Persons: |  | For implementation | For implementation | For implementation | For implementation | For implementation | Completed as per Program of Works
Tagum City | New Balamban | 1st Eng'g. Dist. | Completed | 2020-09-01 | 2020-10-02 | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Project Engineer: | Juan | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
Tagum City | New Balamban | 1st Eng'g. Dist. | Completed | 2020-09-01 | 2020-10-02 | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Implementor: | JJR Construction | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual: | 100%
Tagum City | New Balamban | 1st Eng'g. Dist. | Completed | 2020-09-01 | 2020-10-02 | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Duration: | 150 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Tagum City | New Balamban | 1st Eng'g. Dist. | Completed | 2020-09-01 | 2020-10-02 | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Allotment Released: | 2019-09-10 | Date completed: | 2020-10-02
Tagum City | New Balamban | 1st Eng'g. Dist. | Completed | 2020-09-01 | 2020-10-02 | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Started: | 2020-09-01
Tagum City | Nueva Fuerza | 1st Eng'g. Dist. | Completed | 2020-08-04 | 2020-09-15 | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | Completion of Evacuation Center, Nueva Fuerza, Tagum City |  | 20% DF CY 2019 (STIMULUS) | Building |  |  | Contract | Project Cost: | 500000 | Target Completion Date: | 2021-01-01 | Program: | 500000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: | 100% | No. of Persons: |  | For implementation | For implementation | For implementation | For implementation | For implementation | Completed as per Program of Works
Tagum City | Nueva Fuerza | 1st Eng'g. Dist. | Completed | 2020-08-04 | 2020-09-15 | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Project Engineer: | JUan | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
Tagum City | Nueva Fuerza | 1st Eng'g. Dist. | Completed | 2020-08-04 | 2020-09-15 | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Implementor: | JJR Construction | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual: | 100%
Tagum City | Nueva Fuerza | 1st Eng'g. Dist. | Completed | 2020-08-04 | 2020-09-15 | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Duration: | 150 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Tagum City | Nueva Fuerza | 1st Eng'g. Dist. | Completed | 2020-08-04 | 2020-09-15 | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Allotment Released: | 2019-09-10 | Date completed: | 2020-09-15
Tagum City | Nueva Fuerza | 1st Eng'g. Dist. | Completed | 2020-08-04 | 2020-09-15 | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Started: | 2020-08-04
Carmen | Alejal | 2nd Eng'g. Dist. | Completed | 2019-08-16 |  | 2019 | MLGU | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | Rehab. Of Evacuation Center, Alejal, Carmen |  | 20% DF CY 2019 (STIMULUS | Building |  | sq.m | MLGU | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Fund transfer to LGU Carmen, 3/28/2019 with check no.2574949 and OR no. 0118991 | Fund transfer to LGU Carmen, 3/28/2019 with check no.2574949 and OR no. 0118991 | Completed (Implemented by MLGU, since transfer of fund ) | Completed (Implemented by MLGU, since transfer of fund ) | Completed (Implemented by MLGU, since transfer of fund ) | Completed (Implemented by MLGU, since transfer of fund )
Carmen | Alejal | 2nd Eng'g. Dist. | Completed | 2019-08-16 |  | 2019 | MLGU | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
Carmen | Alejal | 2nd Eng'g. Dist. | Completed | 2019-08-16 |  | 2019 | MLGU | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
Carmen | Alejal | 2nd Eng'g. Dist. | Completed | 2019-08-16 |  | 2019 | MLGU | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Carmen | Alejal | 2nd Eng'g. Dist. | Completed | 2019-08-16 |  | 2019 | MLGU | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Allotment Released: | 2019-02-20 | Date completed:
Carmen | Alejal | 2nd Eng'g. Dist. | Completed | 2019-08-16 |  | 2019 | MLGU | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Started: | 2019-08-16
Carmen | Tuganay | 2nd Eng'g. Dist. | Completed | 2019-08-16 |  | 2019 | MLGU | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | Compl. Of Evacuation Center, Tuganay, Carmen |  | 20% DF CY 2019 (STIMULUS | Building |  | sq.m | MLGU | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Fund transfer to LGU Carmen, 3/28/2019 with check no. 2574947 and OR no. 0118995 | Fund transfer to LGU Carmen, 3/28/2019 with check no. 2574947 and OR no. 0118995 | Completed (Implemented by MLGU, since transfer of fund ) | Completed (Implemented by MLGU, since transfer of fund ) | Completed (Implemented by MLGU, since transfer of fund ) | Completed (Implemented by MLGU, since transfer of fund )
Carmen | Tuganay | 2nd Eng'g. Dist. | Completed | 2019-08-16 |  | 2019 | MLGU | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
Carmen | Tuganay | 2nd Eng'g. Dist. | Completed | 2019-08-16 |  | 2019 | MLGU | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
Carmen | Tuganay | 2nd Eng'g. Dist. | Completed | 2019-08-16 |  | 2019 | MLGU | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Carmen | Tuganay | 2nd Eng'g. Dist. | Completed | 2019-08-16 |  | 2019 | MLGU | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Allotment Released: | 2019-02-20 | Date completed:
Carmen | Tuganay | 2nd Eng'g. Dist. | Completed | 2019-08-16 |  | 2019 | MLGU | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Started: | 2019-08-16
Sto. Tomas | Casig-ang | 2nd Eng'g. Dist. | Completed | 2020-10-08 | 2020-11-13 | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | Rehab. Of Evacuation Center, Casig-ang, Sto. Tomas |  | 20% DF CY 2019 (STIMULUS | Building |  |  | Contract | Project Cost: | 500000 | Target Completion Date: | 2021-01-16 | Program: | 500000 | Planned: |  | Planned: |  | Planned: |  | Planned: | 12.3% | Planned: | 100% | No. of Persons: | 5 | On-going | PR #20063670 | Revision of POW on-going | On-going | On-going | Completed as per Program of Works
Sto. Tomas | Casig-ang | 2nd Eng'g. Dist. | Completed | 2020-10-08 | 2020-11-13 | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Project Engineer: | Estorco | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 110
Sto. Tomas | Casig-ang | 2nd Eng'g. Dist. | Completed | 2020-10-08 | 2020-11-13 | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Implementor: | JJR Const. & Supply | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: | 13.6% | Actual: | 100%
Sto. Tomas | Casig-ang | 2nd Eng'g. Dist. | Completed | 2020-10-08 | 2020-11-13 | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Duration: | 100 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 1.3% | Slippage: | 0%
Sto. Tomas | Casig-ang | 2nd Eng'g. Dist. | Completed | 2020-10-08 | 2020-11-13 | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Allotment Released: |  | Date completed: | 2020-11-13
Sto. Tomas | Casig-ang | 2nd Eng'g. Dist. | Completed | 2020-10-08 | 2020-11-13 | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Started: | 2020-10-08
Sto. Tomas | Casig-ang | 2nd Eng'g. Dist. | On-going | 2020-10-08 |  | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | Rehab. Of Evacuation Center, Casig-ang, Sto. Tomas |  | 20% DF CY 2019 (STIMULUS | Building |  |  | Contract | Project Cost: | 500000 | Target Completion Date: | 2021-01-16 | Program: | 500000 | Planned: |  | Planned: |  | Planned: |  | Planned: | 12.3% | Planned: | 12.3% | No. of Persons: | 5 | On-going | PR #20063670 | Revision of POW on-going | On-going | On-going | On-going
Sto. Tomas | Casig-ang | 2nd Eng'g. Dist. | On-going | 2020-10-08 |  | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Project Engineer: | Estorco | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 110
Sto. Tomas | Casig-ang | 2nd Eng'g. Dist. | On-going | 2020-10-08 |  | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Implementor: | JJR Const. & Supply | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: | 13.6% | Actual: | 13.6%
Sto. Tomas | Casig-ang | 2nd Eng'g. Dist. | On-going | 2020-10-08 |  | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Duration: | 100 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 1.3% | Slippage: | 1.3%
Sto. Tomas | Casig-ang | 2nd Eng'g. Dist. | On-going | 2020-10-08 |  | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Sto. Tomas | Casig-ang | 2nd Eng'g. Dist. | On-going | 2020-10-08 |  | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Started: | 2020-10-08
Sto. Tomas | Casig-ang | 2nd Eng'g. Dist. | Completed | 2020-08-27 | 2020-12-02 | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | Rehab. Of Evacuation Center, JP Laurel, Panabo City |  | 20% DF CY 2019 (STIMULUS | Building |  |  |  | Project Cost: | 500000 | Target Completion Date: | 2020-12-05 | Program: | 500000 | Planned: |  | Planned: |  | Planned: |  | Planned: | 100% | Planned: | 100% | No. of Persons: | 5 | On-going | PR #20063670 | Revision of POW on-going | Completed as per physical accomplishment. | Completed as per physical accomplishment. | Completed as per Program of Works
Sto. Tomas | Casig-ang | 2nd Eng'g. Dist. | Completed | 2020-08-27 | 2020-12-02 | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Project Engineer: | Andoy | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 110
Sto. Tomas | Casig-ang | 2nd Eng'g. Dist. | Completed | 2020-08-27 | 2020-12-02 | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Implementor: | Digos Constrak Corp | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: | 100% | Actual: | 100%
Sto. Tomas | Casig-ang | 2nd Eng'g. Dist. | Completed | 2020-08-27 | 2020-12-02 | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Duration: | 100 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Sto. Tomas | Casig-ang | 2nd Eng'g. Dist. | Completed | 2020-08-27 | 2020-12-02 | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Allotment Released: |  | Date completed: | 2020-12-02
Sto. Tomas | Casig-ang | 2nd Eng'g. Dist. | Completed | 2020-08-27 | 2020-12-02 | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Started: | 2020-08-27
IGCS | Libuak | 2nd Eng'g. Dist. | For Implementation |  |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | Rehab. Of Evacuation Center, Libuak, IGCS |  | 20% DF CY 2019 (STIMULUS | Building |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | For implementation | For implementation | For implementation | For implementation | For implementation | For implementation
IGCS | Libuak | 2nd Eng'g. Dist. | For Implementation |  |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
IGCS | Libuak | 2nd Eng'g. Dist. | For Implementation |  |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
IGCS | Libuak | 2nd Eng'g. Dist. | For Implementation |  |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
IGCS | Libuak | 2nd Eng'g. Dist. | For Implementation |  |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Allotment Released: | 2019-05-29 | Date completed:
IGCS | Libuak | 2nd Eng'g. Dist. | For Implementation |  |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Started:
Carmen | Cebulano | 2nd Eng'g. Dist. | Completed | 2019-08-16 |  | 2019 | MLGU | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | Rehab. of Multi-Purpose hall, Cebulano, Carmen |  | 20% DF CY 2019 (STIMULUS | Building |  | sq.m | MLGU | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Fund transferred to LGU March 28, 2019 | Fund transferred to LGU March 28, 2019 | Completed (Implemented by MLGU, since transfer of fund ) | Completed (Implemented by MLGU, since transfer of fund ) | Completed (Implemented by MLGU, since transfer of fund ) | Completed (Implemented by MLGU, since transfer of fund )
Carmen | Cebulano | 2nd Eng'g. Dist. | Completed | 2019-08-16 |  | 2019 | MLGU | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
Carmen | Cebulano | 2nd Eng'g. Dist. | Completed | 2019-08-16 |  | 2019 | MLGU | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
Carmen | Cebulano | 2nd Eng'g. Dist. | Completed | 2019-08-16 |  | 2019 | MLGU | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Carmen | Cebulano | 2nd Eng'g. Dist. | Completed | 2019-08-16 |  | 2019 | MLGU | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Allotment Released: | 2019-02-20 | Date completed:
Carmen | Cebulano | 2nd Eng'g. Dist. | Completed | 2019-08-16 |  | 2019 | MLGU | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Started: | 2019-08-16
Carmen | Guadalupe | 2nd Eng'g. Dist. | Completed | 2019-08-15 |  | 2019 | MLGU | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | Rehab. of Multi-Purpose Hall, Guadalupe, Carmen |  | 20% DF CY 2019 (STIMULUS | Building |  |  | MLGU | Project Cost: | 500000 | Target Completion Date: | 2019-11-13 23:59 | Program: | 500000 | Planned: |  | Planned: |  | Planned: | 100% | Planned: | 100% | Planned: | 100% | No. of Persons: |  | Completed (Implemented by MLGU, since transfer of fund ) | Completed (Implemented by MLGU, since transfer of fund ) | Completed (Implemented by MLGU, since transfer of fund ) | Completed (Implemented by MLGU, since transfer of fund ) | Completed (Implemented by MLGU, since transfer of fund ) | Completed (Implemented by MLGU, since transfer of fund )
Carmen | Guadalupe | 2nd Eng'g. Dist. | Completed | 2019-08-15 |  | 2019 | MLGU | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
Carmen | Guadalupe | 2nd Eng'g. Dist. | Completed | 2019-08-15 |  | 2019 | MLGU | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: | 100% | Actual: | 100% | Actual: | 100%
Carmen | Guadalupe | 2nd Eng'g. Dist. | Completed | 2019-08-15 |  | 2019 | MLGU | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Duration: | 91 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Carmen | Guadalupe | 2nd Eng'g. Dist. | Completed | 2019-08-15 |  | 2019 | MLGU | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Allotment Released: | 2019-02-20 | Date completed:
Carmen | Guadalupe | 2nd Eng'g. Dist. | Completed | 2019-08-15 |  | 2019 | MLGU | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Started: | 2019-08-15
Carmen | Ising | 2nd Eng'g. Dist. | Completed | 2019-08-16 |  | 2019 | MLGU | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | Const. of Multi-Purpose hall, Ising, Carmen |  | 20% DF CY 2019 (STIMULUS | Building |  |  | MLGU | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Fund transferred to LGU March 28, 2019 | Fund transferred to LGU March 28, 2019 | Completed (Implemented by MLGU, since transfer of fund ) | Completed (Implemented by MLGU, since transfer of fund ) | Completed (Implemented by MLGU, since transfer of fund ) | Completed (Implemented by MLGU, since transfer of fund )
Carmen | Ising | 2nd Eng'g. Dist. | Completed | 2019-08-16 |  | 2019 | MLGU | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
Carmen | Ising | 2nd Eng'g. Dist. | Completed | 2019-08-16 |  | 2019 | MLGU | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
Carmen | Ising | 2nd Eng'g. Dist. | Completed | 2019-08-16 |  | 2019 | MLGU | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Carmen | Ising | 2nd Eng'g. Dist. | Completed | 2019-08-16 |  | 2019 | MLGU | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Allotment Released: | 2019-02-20 | Date completed:
Carmen | Ising | 2nd Eng'g. Dist. | Completed | 2019-08-16 |  | 2019 | MLGU | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Started:
Carmen | La Paz | 2nd Eng'g. Dist. | Completed | 2019-08-16 |  | 2019 | MLGU | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | Const. of Multi-Purpose Hall, La Paz, Carmen |  | 20% DF CY 2019 (STIMULUS | Building |  | sq.m | MLGU | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Fund transferred to LGU March 28, 2019 | Fund transferred to LGU March 28, 2019 | Fund transferred to LGU March 28, 2019 | Fund transferred to LGU March 28, 2019 | Fund transferred to LGU March 28, 2019 | Completed (Implemented by MLGU, since transfer of fund )
Carmen | La Paz | 2nd Eng'g. Dist. | Completed | 2019-08-16 |  | 2019 | MLGU | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
Carmen | La Paz | 2nd Eng'g. Dist. | Completed | 2019-08-16 |  | 2019 | MLGU | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
Carmen | La Paz | 2nd Eng'g. Dist. | Completed | 2019-08-16 |  | 2019 | MLGU | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Carmen | La Paz | 2nd Eng'g. Dist. | Completed | 2019-08-16 |  | 2019 | MLGU | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Allotment Released: | 2019-02-20 | Date completed:
Carmen | La Paz | 2nd Eng'g. Dist. | Completed | 2019-08-16 |  | 2019 | MLGU | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Started: | 2019-08-16
Carmen | Mabuhay | 2nd Eng'g. Dist. | Completed | 2019-08-16 |  | 2019 | MLGU | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | Const. of Multi-Purpose Hall, Mabuhay, Carmen |  | 20% DF CY 2019 (STIMULUS | Building |  | sq.m | MLGU | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Completed (Implemented by MLGU, since transfer of fund ) | Completed (Implemented by MLGU, since transfer of fund ) | Completed (Implemented by MLGU, since transfer of fund ) | Completed (Implemented by MLGU, since transfer of fund ) | Completed (Implemented by MLGU, since transfer of fund ) | Completed (Implemented by MLGU, since transfer of fund )
Carmen | Mabuhay | 2nd Eng'g. Dist. | Completed | 2019-08-16 |  | 2019 | MLGU | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
Carmen | Mabuhay | 2nd Eng'g. Dist. | Completed | 2019-08-16 |  | 2019 | MLGU | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
Carmen | Mabuhay | 2nd Eng'g. Dist. | Completed | 2019-08-16 |  | 2019 | MLGU | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Carmen | Mabuhay | 2nd Eng'g. Dist. | Completed | 2019-08-16 |  | 2019 | MLGU | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Allotment Released: | 2019-02-20 | Date completed:
Carmen | Mabuhay | 2nd Eng'g. Dist. | Completed | 2019-08-16 |  | 2019 | MLGU | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Started: | 2019-08-16
Carmen | Mangalcal | 2nd Eng'g. Dist. | Completed | 2019-09-16 |  | 2019 | MLGU | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | Const. of Multi-Purpose Hall, Mangalcal, Carmen |  | 20% DF CY 2019 (STIMULUS | Building |  | sq.m | MLGU | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | Planned: |  | Planned: | 100% | Planned: | 100% | Planned: | 100% | No. of Persons: |  | Fund transfer to LGU Carmen, 3/28/2019 with check no. 2574953 and OR no. 0118982 | Fund transfer to LGU Carmen, 3/28/2019 with check no. 2574953 and OR no. 0118982 | Completed (Implemented by MLGU, since transfer of fund ) | Completed (Implemented by MLGU, since transfer of fund ) | Completed (Implemented by MLGU, since transfer of fund ) | Completed (Implemented by MLGU, since transfer of fund )
Carmen | Mangalcal | 2nd Eng'g. Dist. | Completed | 2019-09-16 |  | 2019 | MLGU | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
Carmen | Mangalcal | 2nd Eng'g. Dist. | Completed | 2019-09-16 |  | 2019 | MLGU | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: | 100% | Actual: | 100% | Actual: | 100%
Carmen | Mangalcal | 2nd Eng'g. Dist. | Completed | 2019-09-16 |  | 2019 | MLGU | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Carmen | Mangalcal | 2nd Eng'g. Dist. | Completed | 2019-09-16 |  | 2019 | MLGU | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Allotment Released: | 2019-02-20 | Date completed:
Carmen | Mangalcal | 2nd Eng'g. Dist. | Completed | 2019-09-16 |  | 2019 | MLGU | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Started: | 2019-09-16
IGCS | Bandera | 2nd Eng'g. Dist. | Procurement on process |  |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | Electrification at Sitio Trinidad, Bandera, IGCS |  | 20% DF CY 2019 (STIMULUS | Electrification |  |  | Contract | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | PO #2020072352 - (3E Electrical Sales & Services) | PO #2020072352 - (3E Electrical Sales & Services) | Re-bid due to non-compliance in requirement | Re-bid due to non-compliance in requirement | Re-bid due to non-compliance in requirement | Re-bid due to non-compliance in requirement
IGCS | Bandera | 2nd Eng'g. Dist. | Procurement on process |  |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
IGCS | Bandera | 2nd Eng'g. Dist. | Procurement on process |  |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
IGCS | Bandera | 2nd Eng'g. Dist. | Procurement on process |  |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
IGCS | Bandera | 2nd Eng'g. Dist. | Procurement on process |  |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Allotment Released: | 2019-03-25 | Date completed:
IGCS | Bandera | 2nd Eng'g. Dist. | Procurement on process |  |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Started:
IGCS | Licup | 2nd Eng'g. Dist. | For Implementation |  |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | Electrificatio at Prk. 1,3,4, 6,7 & 8, Licup, IGCS |  | 20% DF CY 2019 (STIMULUS | Electrification |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | For implementation | For implementation | For implementation | For implementation | For implementation | For implementation
IGCS | Licup | 2nd Eng'g. Dist. | For Implementation |  |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
IGCS | Licup | 2nd Eng'g. Dist. | For Implementation |  |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
IGCS | Licup | 2nd Eng'g. Dist. | For Implementation |  |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
IGCS | Licup | 2nd Eng'g. Dist. | For Implementation |  |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Allotment Released: | 2019-02-20 | Date completed:
IGCS | Licup | 2nd Eng'g. Dist. | For Implementation |  |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Started:
IGCS | Tagbaobo | 2nd Eng'g. Dist. | Completed | 2020-03-10 | 2020-08-20 | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | Electrification at Upper Purok Rosal, Tagbaobo, IGCS |  | 20% DF CY 2019 (STIMULUS | Electrification |  |  |  | Project Cost: | 500000 | Target Completion Date: | 2020-05-09 | Program: | 500000 | Planned: |  | Planned: |  | Planned: | 100% | Planned: | 100% | Planned: | 100% | No. of Persons: |  | Purchase Order # 2020010002 (3E Electrical Sales & Services) | Purchase Order # 2020010002 (3E Electrical Sales & Services) | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per Program of Works
IGCS | Tagbaobo | 2nd Eng'g. Dist. | Completed | 2020-03-10 | 2020-08-20 | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Project Engineer: | Porras | Revised Completion Date: | 2020-08-30 | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
IGCS | Tagbaobo | 2nd Eng'g. Dist. | Completed | 2020-03-10 | 2020-08-20 | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Implementor: | 3E Electrical Sales | No. of days suspended: | 59 | Disbursement: |  | Actual: |  | Actual: |  | Actual: | 100% | Actual: | 100% | Actual: | 100%
IGCS | Tagbaobo | 2nd Eng'g. Dist. | Completed | 2020-03-10 | 2020-08-20 | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Duration: | 60 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
IGCS | Tagbaobo | 2nd Eng'g. Dist. | Completed | 2020-03-10 | 2020-08-20 | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Allotment Released: |  | Date completed: | 2020-08-20
IGCS | Tagbaobo | 2nd Eng'g. Dist. | Completed | 2020-03-10 | 2020-08-20 | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Started: | 2020-03-10
IGCS | Libertad | 2nd Eng'g. Dist. | On-going | 2020-08-24 |  | 2019 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | Installation of Pipelines, Libertad, IGCS |  | 20% DF CY 2019 (STIMULUS | Pipelines |  |  |  | Project Cost: | 500000 | Target Completion Date: | 2020-09-17 | Program: | 500000 | Planned: |  | Planned: |  | Planned: | 100% | Planned: | 100% | Planned: | 100% | No. of Persons: | 4 | For implementation | On-going | On-going | On-going | On-going | On-going
IGCS | Libertad | 2nd Eng'g. Dist. | On-going | 2020-08-24 |  | 2019 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Project Engineer: | Porras | Revised Completion Date: | 2020-11-01 | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: | 42.1% | Revised: | 56.4% | Revised: | 56.4% | No. of Man-days: | 88
IGCS | Libertad | 2nd Eng'g. Dist. | On-going | 2020-08-24 |  | 2019 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Implementor: | Admin | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: | 56.1% | Actual: | 62.4% | Actual: | 62.4%
IGCS | Libertad | 2nd Eng'g. Dist. | On-going | 2020-08-24 |  | 2019 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Duration: | 25 | No. of days extended: | 45 |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 14% | Slippage: | 6% | Slippage: | 6%
IGCS | Libertad | 2nd Eng'g. Dist. | On-going | 2020-08-24 |  | 2019 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Allotment Released: | 2019-03-25 | Date completed:
IGCS | Libertad | 2nd Eng'g. Dist. | On-going | 2020-08-24 |  | 2019 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Started: | 2020-08-24
Babak, IGCS | San Isidro | 2nd Eng'g. Dist. | For Implementation |  |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | Rehab. Of Potable Water System, San Isidro, Babak, IGCS |  | 20% DF CY 2019 (STIMULUS | Water System |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | For implementation | For implementation | For implementation | For implementation | For implementation | For implementation
Babak, IGCS | San Isidro | 2nd Eng'g. Dist. | For Implementation |  |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
Babak, IGCS | San Isidro | 2nd Eng'g. Dist. | For Implementation |  |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
Babak, IGCS | San Isidro | 2nd Eng'g. Dist. | For Implementation |  |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Babak, IGCS | San Isidro | 2nd Eng'g. Dist. | For Implementation |  |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Allotment Released: | 2019-06-19 | Date completed:
Babak, IGCS | San Isidro | 2nd Eng'g. Dist. | For Implementation |  |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Started:
IGCS | San Miguel | 2nd Eng'g. Dist. | For Implementation |  |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | Rehab. Of Potable Water System, San Miguel, IGCS |  | 20% DF CY 2019 (STIMULUS | Water System |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | For implementation | For implementation | For implementation | For implementation | For implementation | For implementation
IGCS | San Miguel | 2nd Eng'g. Dist. | For Implementation |  |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
IGCS | San Miguel | 2nd Eng'g. Dist. | For Implementation |  |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
IGCS | San Miguel | 2nd Eng'g. Dist. | For Implementation |  |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
IGCS | San Miguel | 2nd Eng'g. Dist. | For Implementation |  |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Allotment Released: | 2019-02-28 | Date completed:
IGCS | San Miguel | 2nd Eng'g. Dist. | For Implementation |  |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Started:
IGCS | San Remegio | 2nd Eng'g. Dist. | For Implementation |  |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | Const. of Water System Ph.II, San Remegio, IGCS |  | 20% DF CY 2019 (STIMULUS | Water System |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | For implementation | For implementation | For implementation | For implementation | For implementation | For implementation
IGCS | San Remegio | 2nd Eng'g. Dist. | For Implementation |  |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
IGCS | San Remegio | 2nd Eng'g. Dist. | For Implementation |  |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
IGCS | San Remegio | 2nd Eng'g. Dist. | For Implementation |  |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
IGCS | San Remegio | 2nd Eng'g. Dist. | For Implementation |  |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Allotment Released: | 2019-05-29 | Date completed:
IGCS | San Remegio | 2nd Eng'g. Dist. | For Implementation |  |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Started:
Kaputian, IGCS | Pangubatan | 2nd Eng'g. Dist. | Declared savings |  |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | Rehabilitation of Potable Water System, Brgy. Pangubatan, kaputian Dist. IGCS |  | 20% DF CY 2019 | Water System |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | For implementation | Declared as savings in the AIP 2nd Revision to fund for the Construction of PWS in Brgy Linusotan, Kaputian Dist. IGACOS (Project was funded by OPAPP CY 2018) | Declared as savings in the AIP 2nd Revision to fund for the Construction of PWS in Brgy Linusotan, Kaputian Dist. IGACOS (Project was funded by OPAPP CY 2018) | Declared as savings in the AIP 2nd Revision to fund for the Construction of PWS in Brgy Linusotan, Kaputian Dist. IGACOS (Project was funded by OPAPP CY 2018) | Declared as savings in the AIP 2nd Revision to fund for the Construction of PWS in Brgy Linusotan, Kaputian Dist. IGACOS (Project was funded by OPAPP CY 2018) | Declared as savings in the AIP 2nd Revision to fund for the Construction of PWS in Brgy Linusotan, Kaputian Dist. IGACOS (Project was funded by OPAPP CY 2018)
Kaputian, IGCS | Pangubatan | 2nd Eng'g. Dist. | Declared savings |  |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
Kaputian, IGCS | Pangubatan | 2nd Eng'g. Dist. | Declared savings |  |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
Kaputian, IGCS | Pangubatan | 2nd Eng'g. Dist. | Declared savings |  |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Kaputian, IGCS | Pangubatan | 2nd Eng'g. Dist. | Declared savings |  |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Kaputian, IGCS | Pangubatan | 2nd Eng'g. Dist. | Declared savings |  |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Water System Development Project (Provincewide) LS - 9,750,000.00 | [7 empty] | Date Started:
IGCS | Catagman | 2nd Eng'g. Dist. | Completed | 2029-11-11 | 2020-03-20 | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | Concreting of Brgy. Road From Prk. 3 to Prk. 5, Catagman, IGCS |  | 20% DF CY 2019 (STIMULUS | Concreting |  |  | Contract | Project Cost: | 500000 | Target Completion Date: | 2020-04-23 | Program: | 500000 | Planned: | 100% | Planned: | 100% | Planned: | 100% | Planned: | 100% | Planned: | 100% | No. of Persons: |  | Completed | Completed | Completed | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per Program of Works
IGCS | Catagman | 2nd Eng'g. Dist. | Completed | 2029-11-11 | 2020-03-20 | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Project Engineer: | Porras | Revised Completion Date: | 2020-04-13 | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
IGCS | Catagman | 2nd Eng'g. Dist. | Completed | 2029-11-11 | 2020-03-20 | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Implementor: | J-One | No. of days suspended: | 96 | Disbursement: |  | Actual: | 100% | Actual: | 100% | Actual: | 100% | Actual: | 100% | Actual: | 100%
IGCS | Catagman | 2nd Eng'g. Dist. | Completed | 2029-11-11 | 2020-03-20 | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Duration: | 50 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
IGCS | Catagman | 2nd Eng'g. Dist. | Completed | 2029-11-11 | 2020-03-20 | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Allotment Released: | 2019-01-14 | Date completed: | 2020-03-20
IGCS | Catagman | 2nd Eng'g. Dist. | Completed | 2029-11-11 | 2020-03-20 | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Started: | 2020-03-04
IGCS | Catagman | 2nd Eng'g. Dist. | Completed | 2029-11-11 | 2020-03-20 | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | Concreting of Brgy. Road from Prk. 1 to Prk. 2, Villarica, ICGS |  | 20% DF CY 2019 (STIMULUS | Concreting |  |  | Contract | Project Cost: | 500000 | Target Completion Date: | 2020-01-08 | Program: | 500000 | Planned: | 100% | Planned: | 100% | Planned: | 100% | Planned: | 100% | Planned: | 100% | No. of Persons: |  | Completed | Completed | Completed | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per Program of Works
IGCS | Catagman | 2nd Eng'g. Dist. | Completed | 2029-11-11 | 2020-03-20 | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Project Engineer: | Porras | Revised Completion Date: | 2020-04-13 | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
IGCS | Catagman | 2nd Eng'g. Dist. | Completed | 2029-11-11 | 2020-03-20 | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Implementor: | J-One | No. of days suspended: | 96 | Disbursement: |  | Actual: | 100% | Actual: | 100% | Actual: | 100% | Actual: | 100% | Actual: | 100%
IGCS | Catagman | 2nd Eng'g. Dist. | Completed | 2029-11-11 | 2020-03-20 | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Duration: | 50 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
IGCS | Catagman | 2nd Eng'g. Dist. | Completed | 2029-11-11 | 2020-03-20 | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Allotment Released: | 2019-01-14 | Date completed: | 2020-03-03
IGCS | Catagman | 2nd Eng'g. Dist. | Completed | 2029-11-11 | 2020-03-20 | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Started: | 2019-11-19
New Corella | Del Monte | 1st Eng'g. Dist. | Completed | 2020-02-09 | 2020-12-03 | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Rural Electrification Project (Provincewide) | Rural Electrification , Del Monte, New Corella |  | 20% DF CY 2019 | Electrification |  |  |  | Project Cost: | 3000000 | Target Completion Date: | 2020-09-20 23:46 | Program: | 3000000 | Planned: | 43% | Planned: | 43% | Planned: | 43% | Planned: | 43% | Planned: | 100% | No. of Persons: |  | On-going | On-going | On-going | On-going | On-going | Completed as per Program of Works
New Corella | Del Monte | 1st Eng'g. Dist. | Completed | 2020-02-09 | 2020-12-03 | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Rural Electrification Project (Provincewide) | [7 empty] | Project Engineer: | P.Bueno | Revised Completion Date: | 2020-09-20 23:46 | Allotment: | 3000000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
New Corella | Del Monte | 1st Eng'g. Dist. | Completed | 2020-02-09 | 2020-12-03 | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Rural Electrification Project (Provincewide) | [7 empty] | Implementor: | Tagum Builders | No. of days suspended: |  | Disbursement: |  | Actual: | 43% | Actual: | 43% | Actual: | 43% | Actual: | 43% | Actual: | 100%
New Corella | Del Monte | 1st Eng'g. Dist. | Completed | 2020-02-09 | 2020-12-03 | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Rural Electrification Project (Provincewide) | [7 empty] | Duration: | 225 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
New Corella | Del Monte | 1st Eng'g. Dist. | Completed | 2020-02-09 | 2020-12-03 | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Rural Electrification Project (Provincewide) | [7 empty] | Date Allotment Released: |  | Date completed: | 2020-12-03
New Corella | Del Monte | 1st Eng'g. Dist. | Completed | 2020-02-09 | 2020-12-03 | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Rural Electrification Project (Provincewide) | [7 empty] | Date Started: | 2020-02-09
New Corella | Del Monte | 1st Eng'g. Dist. | On-going | 2020-11-24 |  | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Rural Electrification Project (Provincewide) | Rural Electrification at Sitio Bundok San Roque, Brgy. New Cortez, New Corella |  | 20% DF CY 2019 | Electrification |  |  |  | Project Cost: | 1000000 | Target Completion Date: | 2021-01-05 23:46 | Program: | 1000000 | Planned: | 43% | Planned: | 43% | Planned: | 43% | Planned: | 43% | Planned: | 98% | No. of Persons: |  | On-going | On-going | On-going | On-going | On-going | On-going
New Corella | Del Monte | 1st Eng'g. Dist. | On-going | 2020-11-24 |  | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Rural Electrification Project (Provincewide) | [7 empty] | Project Engineer: | P.Bueno | Revised Completion Date: | 2021-01-05 23:46 | Allotment: | 1000000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
New Corella | Del Monte | 1st Eng'g. Dist. | On-going | 2020-11-24 |  | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Rural Electrification Project (Provincewide) | [7 empty] | Implementor: | Tagum Builders | No. of days suspended: |  | Disbursement: |  | Actual: | 43% | Actual: | 43% | Actual: | 43% | Actual: | 43% | Actual: | 98%
New Corella | Del Monte | 1st Eng'g. Dist. | On-going | 2020-11-24 |  | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Rural Electrification Project (Provincewide) | [7 empty] | Duration: | 43 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
New Corella | Del Monte | 1st Eng'g. Dist. | On-going | 2020-11-24 |  | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Rural Electrification Project (Provincewide) | [7 empty] | Date Allotment Released: |  | Date completed:
New Corella | Del Monte | 1st Eng'g. Dist. | On-going | 2020-11-24 |  | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Rural Electrification Project (Provincewide) | [7 empty] | Date Started: | 2020-11-24
IGCS | Poblacion | 1st Eng'g. Dist. |  |  |  | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Rural Electrification Project (Provincewide) | Rural Electrification at Brgy. Poblacion, Kaputian, IGACOS ( Sitio Sagrada) |  | 20% DF CY 2019 | Electrification |  |  |  | Project Cost: | 1000000 | Target Completion Date: |  | Program: | 1000000 | Planned: | 43% | Planned: | 43% | Planned: | 43% | Planned: | 43% | Planned: |  | No. of Persons: |  | On-going | On-going | On-going | On-going | On-going | For implementation
IGCS | Poblacion | 1st Eng'g. Dist. |  |  |  | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Rural Electrification Project (Provincewide) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 1000000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
IGCS | Poblacion | 1st Eng'g. Dist. |  |  |  | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Rural Electrification Project (Provincewide) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: | 43% | Actual: | 43% | Actual: | 43% | Actual: | 43% | Actual:
IGCS | Poblacion | 1st Eng'g. Dist. |  |  |  | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Rural Electrification Project (Provincewide) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
IGCS | Poblacion | 1st Eng'g. Dist. |  |  |  | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Rural Electrification Project (Provincewide) | [7 empty] | Date Allotment Released: |  | Date completed:
IGCS | Poblacion | 1st Eng'g. Dist. |  |  |  | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Rural Electrification Project (Provincewide) | [7 empty] | Date Started:
Panabo City | Southern Davao | 2nd Eng'g. Dist. | Completed | 2020-08-27 | 2020-10-05 | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | Const. of Multi-Purpose Hall, Southern Davao, Panabo City |  | 20% DF CY 2019 (STIMULUS | Building |  |  | Contract | Project Cost: | 500000 | Target Completion Date: | 2020-12-25 | Program: | 500000 | Planned: |  | Planned: |  | Planned: | 42.3% | Planned: | 100% | Planned: | 100% | No. of Persons: | 4 | Abstract #0520201798 | On-going | On-going | Completed as per physical accomplishment. Financial documents still on process | Completed as per physical accomplishment. Financial documents still on process | Completed as per Program of Works
Panabo City | Southern Davao | 2nd Eng'g. Dist. | Completed | 2020-08-27 | 2020-10-05 | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Project Engineer: | Abayon | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 88
Panabo City | Southern Davao | 2nd Eng'g. Dist. | Completed | 2020-08-27 | 2020-10-05 | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Implementor: | Digos Constrak Corp/ | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: | 50.1% | Actual: | 100% | Actual: | 100%
Panabo City | Southern Davao | 2nd Eng'g. Dist. | Completed | 2020-08-27 | 2020-10-05 | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Duration: | 120 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 7.8% | Slippage: | 0% | Slippage: | 0%
Panabo City | Southern Davao | 2nd Eng'g. Dist. | Completed | 2020-08-27 | 2020-10-05 | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Allotment Released: |  | Date completed: | 2020-10-07
Panabo City | Southern Davao | 2nd Eng'g. Dist. | Completed | 2020-08-27 | 2020-10-05 | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Started: | 2020-08-27
Sto. Tomas | Magwawa | 2nd Eng'g. Dist. | Completed | 2020-07-14 | 2020-01-09 | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | Rehab. Of Multi-Purpose Hall, Magwawa, Sto. Tomas |  | 20% DF CY 2019 (STIMULUS | Building |  |  | Contract | Project Cost: | 500000 | Target Completion Date: | 2020-11-11 | Program: | 500000 | Planned: | 100% | Planned: | 100% | Planned: | 100% | Planned: | 100% | Planned: | 100% | No. of Persons: |  | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per Program of Works
Sto. Tomas | Magwawa | 2nd Eng'g. Dist. | Completed | 2020-07-14 | 2020-01-09 | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
Sto. Tomas | Magwawa | 2nd Eng'g. Dist. | Completed | 2020-07-14 | 2020-01-09 | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Implementor: | JJR Const. & Supply | No. of days suspended: |  | Disbursement: |  | Actual: | 100% | Actual: | 100% | Actual: | 100% | Actual: | 100% | Actual: | 100%
Sto. Tomas | Magwawa | 2nd Eng'g. Dist. | Completed | 2020-07-14 | 2020-01-09 | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Duration: | 120 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Sto. Tomas | Magwawa | 2nd Eng'g. Dist. | Completed | 2020-07-14 | 2020-01-09 | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Allotment Released: | June 19 2019 | Date completed: | 2020-01-09
Sto. Tomas | Magwawa | 2nd Eng'g. Dist. | Completed | 2020-07-14 | 2020-01-09 | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Started: | 2020-07-14
Sto. Tomas | San Vicente | 2nd Eng'g. Dist. | Completed | 2020-08-27 | 2020-11-24 | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | Rehab. Of Multi-Purpose Hall, San Vicente, Sto. Tomas |  | 20% DF CY 2019 (STIMULUS | Building |  |  | Contract | Project Cost: | 500000 | Target Completion Date: | 2020-12-25 | Program: | 500000 | Planned: |  | Planned: |  | Planned: | 23.2% | Planned: | 100% | Planned: | 100% | No. of Persons: |  | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per Program of Works
Sto. Tomas | San Vicente | 2nd Eng'g. Dist. | Completed | 2020-08-27 | 2020-11-24 | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Project Engineer: | Comidoy | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
Sto. Tomas | San Vicente | 2nd Eng'g. Dist. | Completed | 2020-08-27 | 2020-11-24 | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Implementor: | Digos Constrak Corp | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: | 5% | Actual: | 100% | Actual: | 100%
Sto. Tomas | San Vicente | 2nd Eng'g. Dist. | Completed | 2020-08-27 | 2020-11-24 | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Duration: | 120 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | -18.2% | Slippage: | 0% | Slippage: | 0%
Sto. Tomas | San Vicente | 2nd Eng'g. Dist. | Completed | 2020-08-27 | 2020-11-24 | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Allotment Released: | 2019-06-07 | Date completed: | 2020-11-24
Sto. Tomas | San Vicente | 2nd Eng'g. Dist. | Completed | 2020-08-27 | 2020-11-24 | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Started: | 2020-08-27
Sto. Tomas | New Katipunan | 2nd Eng'g. Dist. | Completed | 2020-08-27 | 2020-11-24 | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | Rehab. Of Multi-Purpose Hall, New Katipunan, Sto. Tomas |  | 20% DF CY 2019 (STIMULUS | Building |  |  | Contract | Project Cost: | 500000 | Target Completion Date: | 2020-12-05 | Program: | 500000 | Planned: |  | Planned: |  | Planned: | 23.2% | Planned: |  | Planned: | 100% | No. of Persons: |  | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. |  |  | Completed as per Program of Works
Sto. Tomas | New Katipunan | 2nd Eng'g. Dist. | Completed | 2020-08-27 | 2020-11-24 | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Project Engineer: | Abayon | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
Sto. Tomas | New Katipunan | 2nd Eng'g. Dist. | Completed | 2020-08-27 | 2020-11-24 | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Implementor: | Digos Constrak Corp | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: | 5% | Actual: |  | Actual: | 100%
Sto. Tomas | New Katipunan | 2nd Eng'g. Dist. | Completed | 2020-08-27 | 2020-11-24 | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Duration: | 120 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | -18.2% | Slippage: | 0% | Slippage: | 0%
Sto. Tomas | New Katipunan | 2nd Eng'g. Dist. | Completed | 2020-08-27 | 2020-11-24 | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Allotment Released: | 2019-06-07 | Date completed: | 2020-11-24
Sto. Tomas | New Katipunan | 2nd Eng'g. Dist. | Completed | 2020-08-27 | 2020-11-24 | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Started: | 2020-08-07
Sto. Tomas | Talomo | 2nd Eng'g. Dist. | On-going |  |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | Rehab. Of Multi-Purpose Hall, Talomo, Sto. Tomas |  | 20% DF CY 2019 (STIMULUS | Building |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Fund transfer to LGU - 6/26/2019 with check no. 2575130 and OR no. 0557456 For implementation | Fund transfer to LGU - 6/26/2019 with check no. 2575130 and OR no. 0557456 For implementation | On-going (Implemented by MLGU, since transfer of fund ) | On-going (Implemented by MLGU, since transfer of fund ) | On-going (Implemented by MLGU, since transfer of fund ) | On-going (Implemented by MLGU, since transfer of fund )
Sto. Tomas | Talomo | 2nd Eng'g. Dist. | On-going |  |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
Sto. Tomas | Talomo | 2nd Eng'g. Dist. | On-going |  |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
Sto. Tomas | Talomo | 2nd Eng'g. Dist. | On-going |  |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Sto. Tomas | Talomo | 2nd Eng'g. Dist. | On-going |  |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Sto. Tomas | Talomo | 2nd Eng'g. Dist. | On-going |  |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Started:
Sto. Tomas | Talomo | 2nd Eng'g. Dist. | Completed | 2019-12-07 | 2020-02-29 | 2019 | Administartion | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | Rehab. Of Multi-Purpose Hall, Aundanao, IGCS |  | 20% DF CY 2019 (STIMULUS | Building |  |  | Admin | Project Cost: | 500000 | Target Completion Date: | 2020-02-29 | Program: | 500000 | Planned: |  | Planned: |  | Planned: |  | Planned: | 100% | Planned: | 100% | No. of Persons: |  | Fund transfer to LGU - 6/26/2019 with check no. 2575130 and OR no. 0557456 For implementation | Fund transfer to LGU - 6/26/2019 with check no. 2575130 and OR no. 0557456 For implementation | On-going (Implemented by MLGU, since transfer of fund ) | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per Program of Works
Sto. Tomas | Talomo | 2nd Eng'g. Dist. | Completed | 2019-12-07 | 2020-02-29 | 2019 | Administartion | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Project Engineer: | Andoy | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
Sto. Tomas | Talomo | 2nd Eng'g. Dist. | Completed | 2019-12-07 | 2020-02-29 | 2019 | Administartion | 0 | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: | 100% | Actual: | 100%
Sto. Tomas | Talomo | 2nd Eng'g. Dist. | Completed | 2019-12-07 | 2020-02-29 | 2019 | Administartion | . | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Duration: | 64 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Sto. Tomas | Talomo | 2nd Eng'g. Dist. | Completed | 2019-12-07 | 2020-02-29 | 2019 | Administartion | . | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Allotment Released: |  | Date completed: | 2020-02-29
Sto. Tomas | Talomo | 2nd Eng'g. Dist. | Completed | 2019-12-07 | 2020-02-29 | 2019 | Administartion | . | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Started: | 2019-12-27
IGCS | Cogon | 2nd Eng'g. Dist. | For Implementation |  |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | Const. Of Multi-Purpose Hall, Cogon (Talicud), IGCS |  | 20% DF CY 2019 (STIMULUS | Building |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | For implementation | For implementation | For implementation | For implementation | For implementation | For implementation
IGCS | Cogon | 2nd Eng'g. Dist. | For Implementation |  |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
IGCS | Cogon | 2nd Eng'g. Dist. | For Implementation |  |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
IGCS | Cogon | 2nd Eng'g. Dist. | For Implementation |  |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
IGCS | Cogon | 2nd Eng'g. Dist. | For Implementation |  |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
IGCS | Cogon | 2nd Eng'g. Dist. | For Implementation |  |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Started:
IGCS | Del Monte | 2nd Eng'g. Dist. | Pending |  |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | Rehab. Of Multi-Purpose Hall, Del Monte, IGCS |  | 20% DF CY 2019 (STIMULUS | Building |  |  | Admin | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Pending/ activity undertaken by DPWH | Pending/ activity undertaken by DPWH | Pending/ activity undertaken by DPWH | Pending/ activity undertaken by DPWH | Pending/ activity undertaken by DPWH | Pending/ activity undertaken by DPWH
IGCS | Del Monte | 2nd Eng'g. Dist. | Pending |  |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
IGCS | Del Monte | 2nd Eng'g. Dist. | Pending |  |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
IGCS | Del Monte | 2nd Eng'g. Dist. | Pending |  |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
IGCS | Del Monte | 2nd Eng'g. Dist. | Pending |  |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Allotment Released: | 2019-05-29 | Date completed:
IGCS | Del Monte | 2nd Eng'g. Dist. | Pending |  |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Started:
IGCS | Mambago-B | 2nd Eng'g. Dist. | Completed | 2019-10-18 | 2020-03-30 | 2019 | Administartion | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | Const. Of Multi-Purpose Hall, Mambago-B, IGCS |  | 20% DF CY 2019 (STIMULUS | Building |  | sq.m | Admin | Project Cost: | 500000 | Target Completion Date: | 2019-12-27 | Program: | 500000 | Planned: | 100% | Planned: | 100% | Planned: | 100% | Planned: | 100% | Planned: | 100% | No. of Persons: | 5 | Completed | Completed | Completed | Completed | Completed | Completed as per Program of Works
IGCS | Mambago-B | 2nd Eng'g. Dist. | Completed | 2019-10-18 | 2020-03-30 | 2019 | Administartion | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Project Engineer: | Roque | Revised Completion Date: | 2020-03-30 | Allotment: | 500000 | Revised: | 100% | Revised: | 100% | Revised: | 100% | Revised: | 100% | Revised: | 100% | No. of Man-days: | 22
IGCS | Mambago-B | 2nd Eng'g. Dist. | Completed | 2019-10-18 | 2020-03-30 | 2019 | Administartion | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Implementor: | PEO | No. of days suspended: | 29 | Disbursement: |  | Actual: | 100% | Actual: | 100% | Actual: | 100% | Actual: | 100% | Actual: | 100%
IGCS | Mambago-B | 2nd Eng'g. Dist. | Completed | 2019-10-18 | 2020-03-30 | 2019 | Administartion | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Duration: | 70 | No. of days extended: | 65 |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
IGCS | Mambago-B | 2nd Eng'g. Dist. | Completed | 2019-10-18 | 2020-03-30 | 2019 | Administartion | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Allotment Released: |  | Date completed: | 2020-03-30
IGCS | Mambago-B | 2nd Eng'g. Dist. | Completed | 2019-10-18 | 2020-03-30 | 2019 | Administartion | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Started: | 2019-10-18
Sto. Tomas | San Jose | 2nd Eng'g. Dist. | Completed | 2020-07-14 | 2020-09-07 | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | Completion of Multi-Purpose Hall, San Jose, Sto. Tomas |  | 20% DF CY 2019 (STIMULUS | Building |  |  |  | Project Cost: | 600000 | Target Completion Date: | 2020-05-01 | Program: | 600000 | Planned: |  | Planned: |  | Planned: |  | Planned: | 100% | Planned: | 100% | No. of Persons: | 5 | For implementation | For implementation | For implementation | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per Program of Works
Sto. Tomas | San Jose | 2nd Eng'g. Dist. | Completed | 2020-07-14 | 2020-09-07 | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Project Engineer: | Estorco | Revised Completion Date: |  | Allotment: | 600000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 115
Sto. Tomas | San Jose | 2nd Eng'g. Dist. | Completed | 2020-07-14 | 2020-09-07 | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Implementor: | JJR Const. & Supply | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: | 100% | Actual: | 100%
Sto. Tomas | San Jose | 2nd Eng'g. Dist. | Completed | 2020-07-14 | 2020-09-07 | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Duration: | 120 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Sto. Tomas | San Jose | 2nd Eng'g. Dist. | Completed | 2020-07-14 | 2020-09-07 | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Date Allotment Released: |  | Date completed: | 2020-03-22
Sto. Tomas | San Jose | 2nd Eng'g. Dist. | Completed | 2020-07-14 | 2020-09-07 | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Date Started: | 2020-01-02
IGCS | San Antonio | 2nd Eng'g. Dist. | Completed | 2020-03-23 | 2020-10-15 | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | Const. Of Multi-Purpose Hall, San Antonio, IGCS |  | 20% DF CY 2019 (STIMULUS | Building |  |  | Admin | Project Cost: | 500000 | Target Completion Date: | 2020-05-12 | Program: | 500000 | Planned: |  | Planned: |  | Planned: | 100% | Planned: | 100% | Planned: | 100% | No. of Persons: | 5 | Resume 5/11/2020 Time extension on process | Resume 5/11/2020 Time extension on process | Resume 5/11/2020 Time extension on process | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per Program of Works
IGCS | San Antonio | 2nd Eng'g. Dist. | Completed | 2020-03-23 | 2020-10-15 | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Project Engineer: | Obar | Revised Completion Date: | 2020-06-14 | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 50
IGCS | San Antonio | 2nd Eng'g. Dist. | Completed | 2020-03-23 | 2020-10-15 | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Implementor: | Admin | No. of days suspended: | 34 | Disbursement: |  | Actual: |  | Actual: |  | Actual: | 47.87% | Actual: | 100% | Actual: | 100%
IGCS | San Antonio | 2nd Eng'g. Dist. | Completed | 2020-03-23 | 2020-10-15 | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Duration: | 50 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | -52.13% | Slippage: | 0% | Slippage: | 0%
IGCS | San Antonio | 2nd Eng'g. Dist. | Completed | 2020-03-23 | 2020-10-15 | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Allotment Released: | 2019-06-19 | Date completed: | 2020-10-15
IGCS | San Antonio | 2nd Eng'g. Dist. | Completed | 2020-03-23 | 2020-10-15 | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Started: | 2020-03-23
Carmen | Alejal | 2nd Eng'g. Dist. | Completed | 2019-08-16 |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | Rehab. Of Evacuation Center, Alejal, Carmen |  | 20% DF CY 2019 (STIMULUS | Building |  | sq.m | MLGU | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Fund transfer to LGU Carmen, 3/28/2019 with check no.2574949 and OR no. 0118991 | Fund transfer to LGU Carmen, 3/28/2019 with check no.2574949 and OR no. 0118991 | Completed (Implemented by MLGU, since transfer of fund ) | Completed (Implemented by MLGU, since transfer of fund ) | Completed (Implemented by MLGU, since transfer of fund ) | Completed (Implemented by MLGU, since transfer of fund )
Carmen | Alejal | 2nd Eng'g. Dist. | Completed | 2019-08-16 |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
Carmen | Alejal | 2nd Eng'g. Dist. | Completed | 2019-08-16 |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
Carmen | Alejal | 2nd Eng'g. Dist. | Completed | 2019-08-16 |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Carmen | Alejal | 2nd Eng'g. Dist. | Completed | 2019-08-16 |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Allotment Released: | 2019-02-20 | Date completed:
Carmen | Alejal | 2nd Eng'g. Dist. | Completed | 2019-08-16 |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Started: | 2019-08-16
Panabo City | Gredu | 2nd Eng'g. Dist. | Completed |  |  | 2019 | MLGU | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | Const. of Women Livelihood Center Bldg. , Gredu, Panabo City |  | 20% DF CY 2019 (STIMULUS | Building |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | Planned: |  | Planned: | 100% | Planned: | 100% | Planned: | 100% | No. of Persons: |  | Fund transfer to LGU - 3/28/2019 with check no. 2574926 and OR no. 0166517 - March 28, 2019 | Fund transfer to LGU - 3/28/2019 with check no. 2574926 and OR no. 0166517 - March 28, 2019 | Completed (Implemented by MLGU, since transfer of fund ) | Completed (Implemented by MLGU, since transfer of fund ) | Completed (Implemented by MLGU, since transfer of fund ) | Completed (Implemented by MLGU, since transfer of fund )
Panabo City | Gredu | 2nd Eng'g. Dist. | Completed |  |  | 2019 | MLGU | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
Panabo City | Gredu | 2nd Eng'g. Dist. | Completed |  |  | 2019 | MLGU | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: | 100% | Actual: | 100% | Actual: | 100%
Panabo City | Gredu | 2nd Eng'g. Dist. | Completed |  |  | 2019 | MLGU | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Panabo City | Gredu | 2nd Eng'g. Dist. | Completed |  |  | 2019 | MLGU | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Allotment Released: | 2019-03-28 | Date completed:
Panabo City | Gredu | 2nd Eng'g. Dist. | Completed |  |  | 2019 | MLGU | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Started:
Panabo City | New Visayas | 2nd Eng'g. Dist. | Re-aligned |  |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | Rehab. Of Health Center, New Visayas, Panabo City |  | 20% DF CY 2019 (STIMULUS | Building |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Re aligned to other stimulus projects that needs additional funding | Re aligned to other stimulus projects that needs additional funding | Re aligned to other stimulus projects that needs additional funding | Re aligned to other stimulus projects that needs additional funding | Re aligned to other stimulus projects that needs additional funding | Re aligned to other stimulus projects that needs additional funding
Panabo City | New Visayas | 2nd Eng'g. Dist. | Re-aligned |  |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
Panabo City | New Visayas | 2nd Eng'g. Dist. | Re-aligned |  |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
Panabo City | New Visayas | 2nd Eng'g. Dist. | Re-aligned |  |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Panabo City | New Visayas | 2nd Eng'g. Dist. | Re-aligned |  |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Panabo City | New Visayas | 2nd Eng'g. Dist. | Re-aligned |  |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Started:
Panabo City | New Visayas | 2nd Eng'g. Dist. | Completed | 2019-07-10 | 2019-10-31 | 2019 | Administartion | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | Rehab. Of Health Center, Aumbay, IGCS |  | 20% DF CY 2019 (STIMULUS | Building |  |  |  | Project Cost: | 500000 | Target Completion Date: | 2019-10-31 | Program: | 500000 | Planned: |  | Planned: |  | Planned: |  | Planned: | 100% | Planned: | 100% | No. of Persons: |  | Re aligned to other stimulus projects that needs additional funding | Re aligned to other stimulus projects that needs additional funding | Re aligned to other stimulus projects that needs additional funding | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per Program of Works
Panabo City | New Visayas | 2nd Eng'g. Dist. | Completed | 2019-07-10 | 2019-10-31 | 2019 | Administartion | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Project Engineer: | Estorco | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
Panabo City | New Visayas | 2nd Eng'g. Dist. | Completed | 2019-07-10 | 2019-10-31 | 2019 | Administartion | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: | 100% | Actual: | 100%
Panabo City | New Visayas | 2nd Eng'g. Dist. | Completed | 2019-07-10 | 2019-10-31 | 2019 | Administartion | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Duration: | 113 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Panabo City | New Visayas | 2nd Eng'g. Dist. | Completed | 2019-07-10 | 2019-10-31 | 2019 | Administartion | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Allotment Released: |  | Date completed: | 2019-10-31
Panabo City | New Visayas | 2nd Eng'g. Dist. | Completed | 2019-07-10 | 2019-10-31 | 2019 | Administartion | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Started: | 2019-07-10
IGCS | Mambago-A | 2nd Eng'g. Dist. | Completed | 2019-07-10 | 2019-10-25 | 2019 | Administartion | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | Rehab. Of Brgy. Health Center, Mambago-A, IGCS |  | 20% DF CY 2019 (STIMULUS | Building |  |  |  | Project Cost: | 500000 | Target Completion Date: | 2019-10-25 | Program: | 500000 | Planned: |  | Planned: |  | Planned: |  | Planned: | 100% | Planned: | 100% | No. of Persons: |  | Re aligned to other stimulus projects that needs additional funding | Re aligned to other stimulus projects that needs additional funding | Re aligned to other stimulus projects that needs additional funding | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per Program of Works
IGCS | Mambago-A | 2nd Eng'g. Dist. | Completed | 2019-07-10 | 2019-10-25 | 2019 | Administartion | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Project Engineer: | Estorco | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
IGCS | Mambago-A | 2nd Eng'g. Dist. | Completed | 2019-07-10 | 2019-10-25 | 2019 | Administartion | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: | 100% | Actual: | 100%
IGCS | Mambago-A | 2nd Eng'g. Dist. | Completed | 2019-07-10 | 2019-10-25 | 2019 | Administartion | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Duration: | 107 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
IGCS | Mambago-A | 2nd Eng'g. Dist. | Completed | 2019-07-10 | 2019-10-25 | 2019 | Administartion | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Allotment Released: |  | Date completed: | 2019-10-25
IGCS | Mambago-A | 2nd Eng'g. Dist. | Completed | 2019-07-10 | 2019-10-25 | 2019 | Administartion | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Started: | 2019-07-10
Sto. Tomas | La Libertad | 2nd Eng'g. Dist. | Completed | 2019-11-04 | 2019-11-30 | 2019 | Administartion | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | Compl.of Brgy. Public Market, La Libertad, Sto. Tomas |  | 20% DF CY 2019 (STIMULUS | Building |  |  |  | Project Cost: | 500000 | Target Completion Date: | 2019-11-30 | Program: | 500000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Fund transfer to LGU - 6/26/219 with check no. 2575131 and OR no. 0557457 Completed/ PCR for submission by LGU | Fund transfer to LGU - 6/26/219 with check no. 2575131 and OR no. 0557457 Completed/ PCR for submission by LGU | Completed (Implemented by MLGU, since transfer of fund ) | Completed (Implemented by MLGU, since transfer of fund ) | Completed (Implemented by MLGU, since transfer of fund ) | Completed (Implemented by MLGU, since transfer of fund )
Sto. Tomas | La Libertad | 2nd Eng'g. Dist. | Completed | 2019-11-04 | 2019-11-30 | 2019 | Administartion | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
Sto. Tomas | La Libertad | 2nd Eng'g. Dist. | Completed | 2019-11-04 | 2019-11-30 | 2019 | Administartion | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
Sto. Tomas | La Libertad | 2nd Eng'g. Dist. | Completed | 2019-11-04 | 2019-11-30 | 2019 | Administartion | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Duration: | 26 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Sto. Tomas | La Libertad | 2nd Eng'g. Dist. | Completed | 2019-11-04 | 2019-11-30 | 2019 | Administartion | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Allotment Released: |  | Date completed: | 2019-11-30
Sto. Tomas | La Libertad | 2nd Eng'g. Dist. | Completed | 2019-11-04 | 2019-11-30 | 2019 | Administartion | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Started: | 2019-11-04
B.E. Dujali | Pawas | 2nd Eng'g. Dist. | Completed | 2019-08-05 | 2020-01-30 | 2019 | Administration | . | Rehabilitation of Provincial Roads & Bridges | Rehab/ Impvt of Prk 1 - Prk 2 Sitio Pawas Provincial Road |  | SB No. 1 CY 2019 | Rehabilitation |  | km | Admin | Project Cost: | 1500000 | Target Completion Date: | 2020-01-30 23:59 | Program: | 1500000 | Planned: |  | Planned: |  | Planned: |  | Planned: | 100% | Planned: | 100% | No. of Persons: |  | Plan On-going | Plan On-going | Plan On-going | Completed as per physical accomplishment. | Completed as per physical accomplishment. | Completed as per Program of Works
B.E. Dujali | Pawas | 2nd Eng'g. Dist. | Completed | 2019-08-05 | 2020-01-30 | 2019 | Administration | . | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 1500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
B.E. Dujali | Pawas | 2nd Eng'g. Dist. | Completed | 2019-08-05 | 2020-01-30 | 2019 | Administration | . | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: | 100% | Actual: | 100%
B.E. Dujali | Pawas | 2nd Eng'g. Dist. | Completed | 2019-08-05 | 2020-01-30 | 2019 | Administration | . | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Duration: | 179 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
B.E. Dujali | Pawas | 2nd Eng'g. Dist. | Completed | 2019-08-05 | 2020-01-30 | 2019 | Administration | . | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Date Allotment Released: |  | Date completed: | 2020-01-30
B.E. Dujali | Pawas | 2nd Eng'g. Dist. | Completed | 2019-08-05 | 2020-01-30 | 2019 | Administration | . | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Date Started: | 2019-08-05
Kapalong | Suaon-Libuton | 1st Eng'g. Dist. | On-going | 2019-11-18 |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS OF LOCAL ROADS & DRAINAGE DEVELOPMENT PROJECT(Provincewide) LS - 15,000,000.00 | Repair/Rehab. Of Concrete Road Jct. Suaon-Libuton, Kapalong |  | SB NO. 3 CY 2019 | Road Drainage rehabiliated |  | km | Admin | Project Cost: | 1000000 | Target Completion Date: | 2020-02-15 23:46 | Program: | 1000000 | Planned: | 14.73% | Planned: | 14.73% | Planned: | 30.27% | Planned: | 30.27% | Planned: | 100% | No. of Persons: |  | Plan On-going | Plan On-going | Plan On-going | Completed as per physical accomplishment. | Completed as per physical accomplishment. | Completed as per Program of Works
Kapalong | Suaon-Libuton | 1st Eng'g. Dist. | On-going | 2019-11-18 |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS OF LOCAL ROADS & DRAINAGE DEVELOPMENT PROJECT(Provincewide) LS - 15,000,000.00 | [7 empty] | Project Engineer: | Bacaron | Revised Completion Date: | 2020-11-15 23:46 | Allotment: | 1000000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
Kapalong | Suaon-Libuton | 1st Eng'g. Dist. | On-going | 2019-11-18 |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS OF LOCAL ROADS & DRAINAGE DEVELOPMENT PROJECT(Provincewide) LS - 15,000,000.00 | [7 empty] | Implementor: | PEO | No. of days suspended: | 228 | Disbursement: | 142000 | Actual: | 14.2% | Actual: | 14.2% | Actual: | 30.27% | Actual: | 30.27% | Actual: | 100%
Kapalong | Suaon-Libuton | 1st Eng'g. Dist. | On-going | 2019-11-18 |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS OF LOCAL ROADS & DRAINAGE DEVELOPMENT PROJECT(Provincewide) LS - 15,000,000.00 | [7 empty] | Duration: | 90 | No. of days extended: | 46 |  |  | Slippage: | -0.53% | Slippage: | -0.53% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Kapalong | Suaon-Libuton | 1st Eng'g. Dist. | On-going | 2019-11-18 |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS OF LOCAL ROADS & DRAINAGE DEVELOPMENT PROJECT(Provincewide) LS - 15,000,000.00 | [7 empty] | Date Allotment Released: | 2019-03-12 | Date completed: | 2020-11-15
Kapalong | Suaon-Libuton | 1st Eng'g. Dist. | On-going | 2019-11-18 |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | VARIOUS OF LOCAL ROADS & DRAINAGE DEVELOPMENT PROJECT(Provincewide) LS - 15,000,000.00 | [7 empty] | Date Started: | 2019-11-18
New Corella | Poblacion | 1st Eng'g. Dist. | Completed | 2019-12-02 | 2020-08-31 | 2019 | Administration | . | Residential Care Facilities | Construction of Multi-Purpose Covered Court/Evacuation, Bahay Pag-Asa, New Corella, Ph.II |  | 20% DF CY 2019 & TRUST FUND | Building |  | sq.m | Admin | Project Cost: | 2500000 | Target Completion Date: | 2020-04-15 | Program: | 2500000 | Planned: | 84.4% | Planned: | 100% | Planned: | 100% | Planned: | 100% | Planned: | 100% | No. of Persons: | 12 | On-going | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per Program of Works
New Corella | Poblacion | 1st Eng'g. Dist. | Completed | 2019-12-02 | 2020-08-31 | 2019 | Administration | . | Residential Care Facilities | [7 empty] | Project Engineer: | Mayang | Revised Completion Date: | 2020-08-30 | Allotment: | 2500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 180
New Corella | Poblacion | 1st Eng'g. Dist. | Completed | 2019-12-02 | 2020-08-31 | 2019 | Administration | . | Residential Care Facilities | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: |  | Actual: | 84.4% | Actual: | 100% | Actual: | 100% | Actual: | 100% | Actual: | 100%
New Corella | Poblacion | 1st Eng'g. Dist. | Completed | 2019-12-02 | 2020-08-31 | 2019 | Administration | . | Residential Care Facilities | [7 empty] | Duration: | 135 | No. of days extended: | 110 |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
New Corella | Poblacion | 1st Eng'g. Dist. | Completed | 2019-12-02 | 2020-08-31 | 2019 | Administration | . | Residential Care Facilities | [7 empty] | Date Allotment Released: | 2019-06-19 | Date completed: | 2020-08-31
New Corella | Poblacion | 1st Eng'g. Dist. | Completed | 2019-12-02 | 2020-08-31 | 2019 | Administration | . | Residential Care Facilities | [7 empty] | Date Started: | 2019-12-02
B.E. Dujali | Pawas | 2nd Eng'g. Dist. | Completed | 2019-08-05 | 2020-01-30 | 2019 | Administration | . | Rehabilitation of Provincial Roads & Bridges | Installation of Bleacher for the Brgy. Gym, Concepcion |  | SB No. 1 CY 2019 (STIMULUS PROJECT) | Bleacher |  |  | MLGU | Project Cost: | 1000000 | Target Completion Date: | 1900-06-26 23:59 | Program: | 1000000 | Planned: |  | Planned: |  | Planned: |  | Planned: | 100% | Planned: | 100% | No. of Persons: |  | Plan On-going | Plan On-going | Plan On-going | Completed (Implemented by MLGU, since transfer of fund ) | Completed (Implemented by MLGU, since transfer of fund ) | Completed (Implemented by MLGU, since transfer of fund )
B.E. Dujali | Pawas | 2nd Eng'g. Dist. | Completed | 2019-08-05 | 2020-01-30 | 2019 | Administration | . | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 1000000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
B.E. Dujali | Pawas | 2nd Eng'g. Dist. | Completed | 2019-08-05 | 2020-01-30 | 2019 | Administration | . | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Implementor: | MLGU | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: | 100% | Actual: | 100%
B.E. Dujali | Pawas | 2nd Eng'g. Dist. | Completed | 2019-08-05 | 2020-01-30 | 2019 | Administration | . | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Duration: | 179 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
B.E. Dujali | Pawas | 2nd Eng'g. Dist. | Completed | 2019-08-05 | 2020-01-30 | 2019 | Administration | . | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Date Allotment Released: |  | Date completed:
B.E. Dujali | Pawas | 2nd Eng'g. Dist. | Completed | 2019-08-05 | 2020-01-30 | 2019 | Administration | . | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Date Started:
Asuncion | Sagayen | 1st Eng'g. Dist. | Completed | 2020-07-17 | 2020-10-01 | 2019 | Contract | . | STIMULUS 2019 | Rehab/Impvt of Gymnasium, Sagayen, Asuncion |  | SB No. 1 CY 2019 (STIMULUS) | Building |  |  | Contract | Project Cost: | 1500000 | Target Completion Date: | 2020-10-01 23:59 | Program: | 1500000 | Planned: |  | Planned: |  | Planned: |  | Planned: | 100% | Planned: | 100% | No. of Persons: |  | Final Abstract # 0320200900 (Alpebel Builders & Supply Corp.) | Final Abstract # 0320200900 (Alpebel Builders & Supply Corp.) | Final Abstract # 0320200900 (Alpebel Builders & Supply Corp.) | Completed as per physical accomplishment. | Completed as per physical accomplishment. | Completed as per Program of Works
Asuncion | Sagayen | 1st Eng'g. Dist. | Completed | 2020-07-17 | 2020-10-01 | 2019 | Contract | . | STIMULUS 2019 | [7 empty] | Project Engineer: | Kabingue | Revised Completion Date: |  | Allotment: | 1500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
Asuncion | Sagayen | 1st Eng'g. Dist. | Completed | 2020-07-17 | 2020-10-01 | 2019 | Contract | . | STIMULUS 2019 | [7 empty] | Implementor: | Alpebel Builders and Const. Supply | No. of days suspended: |  | Disbursement: | 1500000 | Actual: |  | Actual: |  | Actual: |  | Actual: | 100% | Actual: | 100%
Asuncion | Sagayen | 1st Eng'g. Dist. | Completed | 2020-07-17 | 2020-10-01 | 2019 | Contract | . | STIMULUS 2019 | [7 empty] | Duration: | 77 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Asuncion | Sagayen | 1st Eng'g. Dist. | Completed | 2020-07-17 | 2020-10-01 | 2019 | Contract | . | STIMULUS 2019 | [7 empty] | Date Allotment Released: |  | Date completed: | 2020-10-01 23:59
Asuncion | Sagayen | 1st Eng'g. Dist. | Completed | 2020-07-17 | 2020-10-01 | 2019 | Contract | . | STIMULUS 2019 | [7 empty] | Date Started: | 2020-07-17
New Corella | New Sambog | 1st Eng'g. Dist. |  |  |  | 2019 |  | . | STIMULUS 2019 | Purchase of Lot Cemetery, San Roque, New Corella |  | SB No. 1 CY 2019 (STIMULUS) | Land |  |  |  | Project Cost: | 1500000 | Target Completion Date: |  | Program: | 1500000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | for fund transfer. Waiting for LGU documents. Liquidation of previous fund transfer for the water system project of LGU. | for fund transfer. Waiting for LGU documents. Liquidation of previous fund transfer for the water system project of LGU. | for fund transfer. Waiting for LGU documents. Liquidation of previous fund transfer for the water system project of LGU. | for fund transfer. Waiting for LGU documents. Liquidation of previous fund transfer for the water system project of LGU. | for fund transfer. Waiting for LGU documents. Liquidation of previous fund transfer for the water system project of LGU. | Lot already purchased by Brgy. San Roque, New Corella. For ammendment for new project of the same location. Resolution already submitted by Brgy. San Roque; Energization of Purok-3 Sitio Libas, Brgy. San Roque. POW preparation ongoing.
New Corella | New Sambog | 1st Eng'g. Dist. |  |  |  | 2019 |  | . | STIMULUS 2019 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 1500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
New Corella | New Sambog | 1st Eng'g. Dist. |  |  |  | 2019 |  | . | STIMULUS 2019 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
New Corella | New Sambog | 1st Eng'g. Dist. |  |  |  | 2019 |  | . | STIMULUS 2019 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
New Corella | New Sambog | 1st Eng'g. Dist. |  |  |  | 2019 |  | . | STIMULUS 2019 | [7 empty] | Date Allotment Released: |  | Date completed:
New Corella | New Sambog | 1st Eng'g. Dist. |  |  |  | 2019 |  | . | STIMULUS 2019 | [7 empty] | Date Started:
Asuncion | New Corella | 1st Eng'g. Dist. |  |  |  | 2019 |  | . | STIMULUS 2019 | Purchase of Lot Cemetery, Cambanogoy, Asuncion |  | SB No. 1 CY 2019 (STIMULUS) | Land |  |  |  | Project Cost: | 1500000 | Target Completion Date: |  | Program: | 1500000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | for fund transfer. Waiting for LGU documents. Liquidation of previous fund transfer for the water system project of LGU. | for fund transfer. Waiting for LGU documents. Liquidation of previous fund transfer for the water system project of LGU. | for fund transfer. Waiting for LGU documents. Liquidation of previous fund transfer for the water system project of LGU. | for fund transfer. Waiting for LGU documents. Liquidation of previous fund transfer for the water system project of LGU. | for fund transfer. Waiting for LGU documents. Liquidation of previous fund transfer for the water system project of LGU. | Documents for the fund transfer to be complied by the LGUs. Letter sent dated June 18, 2019 Follow up for the requirements last July 20, 2020
Asuncion | New Corella | 1st Eng'g. Dist. |  |  |  | 2019 |  | . | STIMULUS 2019 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 1500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
Asuncion | New Corella | 1st Eng'g. Dist. |  |  |  | 2019 |  | . | STIMULUS 2019 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
Asuncion | New Corella | 1st Eng'g. Dist. |  |  |  | 2019 |  | . | STIMULUS 2019 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Asuncion | New Corella | 1st Eng'g. Dist. |  |  |  | 2019 |  | . | STIMULUS 2019 | [7 empty] | Date Allotment Released: |  | Date completed:
Asuncion | New Corella | 1st Eng'g. Dist. |  |  |  | 2019 |  | . | STIMULUS 2019 | [7 empty] | Date Started:
Asuncion | Sagayen | 1st Eng'g. Dist. | Completed | 2020-01-27 | 2020-02-05 | 2019 |  | . | STIMULUS 2019 | Installation of Street Lights at Prk 1,2,3,4, Sagayen, Asuncion |  | SB No. 1 CY 2019 (STIMULUS) | Electrification |  |  |  | Project Cost: | 1000000 | Target Completion Date: | 2020-02-05 23:59 | Program: | 1000000 | Planned: | 100% | Planned: | 100% | Planned: | 100% | Planned: | 100% | Planned: | 100% | No. of Persons: |  | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per Program of Works
Asuncion | Sagayen | 1st Eng'g. Dist. | Completed | 2020-01-27 | 2020-02-05 | 2019 |  | . | STIMULUS 2019 | [7 empty] | Project Engineer: | Bueno | Revised Completion Date: | 2020-02-05 23:59 | Allotment: | 1000000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
Asuncion | Sagayen | 1st Eng'g. Dist. | Completed | 2020-01-27 | 2020-02-05 | 2019 |  | . | STIMULUS 2019 | [7 empty] | Implementor: | Tagum Builders | No. of days suspended: |  | Disbursement: |  | Actual: | 100% | Actual: | 100% | Actual: | 100% | Actual: | 100% | Actual: | 100%
Asuncion | Sagayen | 1st Eng'g. Dist. | Completed | 2020-01-27 | 2020-02-05 | 2019 |  | . | STIMULUS 2019 | [7 empty] | Duration: | 10 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Asuncion | Sagayen | 1st Eng'g. Dist. | Completed | 2020-01-27 | 2020-02-05 | 2019 |  | . | STIMULUS 2019 | [7 empty] | Date Allotment Released: |  | Date completed: | 2020-02-05
Asuncion | Sagayen | 1st Eng'g. Dist. | Completed | 2020-01-27 | 2020-02-05 | 2019 |  | . | STIMULUS 2019 | [7 empty] | Date Started: | 2020-01-27
Asuncion | Concepcion | 1st Eng'g. Dist. | Completed |  |  | 2019 | MLGU | . | STIMULUS 2019 | Concreting of FMR, New Santiago, Asuncion |  | SB No. 1 CY 2019 (STIMULUS) | Electrification |  |  | MLGU | Project Cost: | 2500000 | Target Completion Date: |  | Program: | 2500000 | Planned: | 100% | Planned: | 100% | Planned: | 100% | Planned: |  | Planned: |  | No. of Persons: |  | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | COMPLETED - PCR & other completion documents for submission PCR, SWA, Before and after Pictures | COMPLETED - PCR & other completion documents for submission PCR, SWA, Before and after Pictures | COMPLETED - PCR & other completion documents for submission PCR, SWA, Before and after Pictures
Asuncion | Concepcion | 1st Eng'g. Dist. | Completed |  |  | 2019 | MLGU | . | STIMULUS 2019 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 2500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
Asuncion | Concepcion | 1st Eng'g. Dist. | Completed |  |  | 2019 | MLGU | . | STIMULUS 2019 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: | 100% | Actual: | 100% | Actual: | 100% | Actual: |  | Actual:
Asuncion | Concepcion | 1st Eng'g. Dist. | Completed |  |  | 2019 | MLGU | . | STIMULUS 2019 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Asuncion | Concepcion | 1st Eng'g. Dist. | Completed |  |  | 2019 | MLGU | . | STIMULUS 2019 | [7 empty] | Date Allotment Released: |  | Date completed:
Asuncion | Concepcion | 1st Eng'g. Dist. | Completed |  |  | 2019 | MLGU | . | STIMULUS 2019 | [7 empty] | Date Started:
New Corella | Patrocenio | 1st Eng'g. Dist. | Completed | 2020-06-12 | 2020-07-08 | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | Expansion of Multi-Purpose Hall ( Brgy. Hall), Patrocenio, New Corella |  | SB NO. 1 CY 2019 (STIMULUS) | Building |  |  |  | Project Cost: | 500000 | Target Completion Date: | 2020-07-08 23:46 | Program: | 500000 | Planned: |  | Planned: |  | Planned: |  | Planned: | 100% | Planned: | 100% | No. of Persons: |  | POW preparation on going c/o PDPM | POW preparation on going c/o PDPM | Abstract on Process Contractor: Royal Summit Infinity Dev't. Corp. | For implementation | For implementation | Completed as per Program of Works
New Corella | Patrocenio | 1st Eng'g. Dist. | Completed | 2020-06-12 | 2020-07-08 | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Project Engineer: | Cabañero | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
New Corella | Patrocenio | 1st Eng'g. Dist. | Completed | 2020-06-12 | 2020-07-08 | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Implementor: | JJR Construction | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual: | 100%
New Corella | Patrocenio | 1st Eng'g. Dist. | Completed | 2020-06-12 | 2020-07-08 | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Duration: | 27 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 100% | Slippage: | 0%
New Corella | Patrocenio | 1st Eng'g. Dist. | Completed | 2020-06-12 | 2020-07-08 | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Allotment Released: |  | Date completed: | 2020-07-08 23:46
New Corella | Patrocenio | 1st Eng'g. Dist. | Completed | 2020-06-12 | 2020-07-08 | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Started: | 2020-06-12
New Corella | Patrocenio | 1st Eng'g. Dist. | Re-aligned to COVID |  |  | 2019 |  | . | STIMULUS 2019 | Const. of FMR from Prk 1 to Sitio Magsaysay via Pundol & Prk 4, Patrocenio, New Corella |  | SB NO. 1 CY 2019 (STIMULUS) | Road |  |  |  | Project Cost: | 2000000 | Target Completion Date: |  | Program: | 2000000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
New Corella | Patrocenio | 1st Eng'g. Dist. | Re-aligned to COVID |  |  | 2019 |  | . | STIMULUS 2019 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 2000000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
New Corella | Patrocenio | 1st Eng'g. Dist. | Re-aligned to COVID |  |  | 2019 |  | . | STIMULUS 2019 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
New Corella | Patrocenio | 1st Eng'g. Dist. | Re-aligned to COVID |  |  | 2019 |  | . | STIMULUS 2019 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
New Corella | Patrocenio | 1st Eng'g. Dist. | Re-aligned to COVID |  |  | 2019 |  | . | STIMULUS 2019 | [7 empty] | Date Allotment Released: |  | Date completed:
New Corella | Patrocenio | 1st Eng'g. Dist. | Re-aligned to COVID |  |  | 2019 |  | . | STIMULUS 2019 | [7 empty] | Date Started:
New Corella | Limbaan | 1st Eng'g. Dist. | For Implementation |  |  | 2019 | Contract | . | STIMULUS 2019 | Const. of Drainage Canal from Prk. 3, 1-A, 2-A to Prk 1-B, Brgy Site (Ph. 2), Limbaan, New Corella |  | SB NO. 1 CY 2019 (STIMULUS) | Flood Control - Drainage |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | POW preparation on going c/o PDPM | POW preparation on going c/o PDPM | Abstract on Process Contractor: Royal Summit Infinity Dev't. Corp. | For implementation | For implementation | For implementation
New Corella | Limbaan | 1st Eng'g. Dist. | For Implementation |  |  | 2019 | Contract | . | STIMULUS 2019 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
New Corella | Limbaan | 1st Eng'g. Dist. | For Implementation |  |  | 2019 | Contract | . | STIMULUS 2019 | [7 empty] | Implementor: | Royal Summit Infinity | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
New Corella | Limbaan | 1st Eng'g. Dist. | For Implementation |  |  | 2019 | Contract | . | STIMULUS 2019 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
New Corella | Limbaan | 1st Eng'g. Dist. | For Implementation |  |  | 2019 | Contract | . | STIMULUS 2019 | [7 empty] | Date Allotment Released: |  | Date completed:
New Corella | Limbaan | 1st Eng'g. Dist. | For Implementation |  |  | 2019 | Contract | . | STIMULUS 2019 | [7 empty] | Date Started:
New Corella | Poblacion | 1st Eng'g. Dist. | Re-aligned to COVID |  |  | 2019 |  | . | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | Const. of 2 Storey Multi-Purpose Hall Ph. 1 (Brgy. Hall), Poblacion, New Corella |  | SB No. 1 CY 2019 (STIMULUS) | Building |  | sq.m | Admin | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: | 100% | Planned: | 100% | Planned: | 100% | Planned: |  | Planned: |  | No. of Persons: |  | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1 | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1 | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1
New Corella | Poblacion | 1st Eng'g. Dist. | Re-aligned to COVID |  |  | 2019 |  | . | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
New Corella | Poblacion | 1st Eng'g. Dist. | Re-aligned to COVID |  |  | 2019 |  | . | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: | 100% | Actual: | 100% | Actual: | 100% | Actual: |  | Actual:
New Corella | Poblacion | 1st Eng'g. Dist. | Re-aligned to COVID |  |  | 2019 |  | . | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage:
New Corella | Poblacion | 1st Eng'g. Dist. | Re-aligned to COVID |  |  | 2019 |  | . | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
New Corella | Poblacion | 1st Eng'g. Dist. | Re-aligned to COVID |  |  | 2019 |  | . | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT (Provincewide) LS - P27,000,000.00 | [7 empty] | Date Started:
IGCS | Mambago | 2nd Eng'g. Dist. | For Implementation |  |  | 2019 |  | . | Various Water System Development Project (Provincewide) LS - P 10,000,000.00 | Impv't. of Potable Water System, Mambago-A, IGCS |  | SB NO. 3 CY 2019 | Water System |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | For Implementation | For Implementation | For Implementation | For Implementation | For Implementation | For Implementation
IGCS | Mambago | 2nd Eng'g. Dist. | For Implementation |  |  | 2019 |  | . | Various Water System Development Project (Provincewide) LS - P 10,000,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
IGCS | Mambago | 2nd Eng'g. Dist. | For Implementation |  |  | 2019 |  | . | Various Water System Development Project (Provincewide) LS - P 10,000,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
IGCS | Mambago | 2nd Eng'g. Dist. | For Implementation |  |  | 2019 |  | . | Various Water System Development Project (Provincewide) LS - P 10,000,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
IGCS | Mambago | 2nd Eng'g. Dist. | For Implementation |  |  | 2019 |  | . | Various Water System Development Project (Provincewide) LS - P 10,000,000.00 | [7 empty] | Date Allotment Released: | 2019-09-10 | Date completed:
IGCS | Mambago | 2nd Eng'g. Dist. | For Implementation |  |  | 2019 |  | . | Various Water System Development Project (Provincewide) LS - P 10,000,000.00 | [7 empty] | Date Started:
IGCS | Linusotan | 2nd Eng'g. Dist. | For Implementation |  |  | 2019 |  | . | Various Water System Development Project (Provincewide) LS - P 10,000,000.00 | Construction of PWS, Brgy. Linusotan, Talikud, District, IGCS |  | SB NO. 3 CY 2019 | Water System |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Procurement on process | Procurement on process | Procurement on process | Procurement on process | Procurement on process | Procurement on process
IGCS | Linusotan | 2nd Eng'g. Dist. | For Implementation |  |  | 2019 |  | . | Various Water System Development Project (Provincewide) LS - P 10,000,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
IGCS | Linusotan | 2nd Eng'g. Dist. | For Implementation |  |  | 2019 |  | . | Various Water System Development Project (Provincewide) LS - P 10,000,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
IGCS | Linusotan | 2nd Eng'g. Dist. | For Implementation |  |  | 2019 |  | . | Various Water System Development Project (Provincewide) LS - P 10,000,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
IGCS | Linusotan | 2nd Eng'g. Dist. | For Implementation |  |  | 2019 |  | . | Various Water System Development Project (Provincewide) LS - P 10,000,000.00 | [7 empty] | Date Allotment Released: | 2019-10-23 | Date completed:
IGCS | Linusotan | 2nd Eng'g. Dist. | For Implementation |  |  | 2019 |  | . | Various Water System Development Project (Provincewide) LS - P 10,000,000.00 | [7 empty] | Date Started:
Talaingod | Salawao-Sto. Niño | 1st Eng'g. Dist. | On-going | 2019-03-16 |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION |  | Provincial Livestock & Poultry Multiplier Farm Road Network Construction, Sitio Salawao, Sto. Niño, Talaingod |  | SB NO. 4 CY 2019 | Conc. Pavement |  | sq.m | Admin | Project Cost: | 5500000 | Target Completion Date: | 2020-07-13 23:46 | Program: | 5500000 | Planned: | 30.06% | Planned: | 56.09% | Planned: | 56.09% | Planned: | 56.09% | Planned: | 100% | No. of Persons: | 28 | Plan On-going | Plan On-going | Plan On-going | Completed (Implemented by MLGU, since transfer of fund ) | Completed (Implemented by MLGU, since transfer of fund ) | On-going
Talaingod | Salawao-Sto. Niño | 1st Eng'g. Dist. | On-going | 2019-03-16 |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | [8 empty] | Project Engineer: | Pasiona/Juan | Revised Completion Date: | 2021-01-29 23:46 | Allotment: | 5500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: | 87.29% | No. of Man-days: | 420
Talaingod | Salawao-Sto. Niño | 1st Eng'g. Dist. | On-going | 2019-03-16 |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | [8 empty] | Implementor: | PEO | No. of days suspended: | 28 | Disbursement: | 4704199.85 | Actual: | 30.06% | Actual: | 45.48% | Actual: | 45.48% | Actual: | 45.48% | Actual: | 81.94%
Talaingod | Salawao-Sto. Niño | 1st Eng'g. Dist. | On-going | 2019-03-16 |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | [8 empty] | Duration: | 120 | No. of days extended: | 172 |  |  | Slippage: | 0% | Slippage: | -10.61% | Slippage: | -10.61% | Slippage: | -10.61% | Slippage: | -5.35%
Talaingod | Salawao-Sto. Niño | 1st Eng'g. Dist. | On-going | 2019-03-16 |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | [8 empty] | Date Allotment Released: | CY 2019 | Date completed:
Talaingod | Salawao-Sto. Niño | 1st Eng'g. Dist. | On-going | 2019-03-16 |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | [8 empty] | Date Started: | 2020-03-16
Panabo City | Nanyo | 2nd Eng'g. Dist. | Completed | 2020-04-07 | 2020-09-07 | 2018 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | Const. of Perimeter Fence of Day Care Center 1, Nanyo, Panabo City |  | SB No. 4 CY 2019 (STIMULUS) | Building |  | sq.m | Contract | Project Cost: | 500000 | Target Completion Date: | 2020-06-06 | Program: | 500000 | Planned: | 5% | Planned: | 100% | Planned: | 100% | Planned: | 100% | Planned: | 100% | No. of Persons: |  | (RLHV Design & Build) Winning Bidder | On-going; subject to LD | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per Program of Works
Panabo City | Nanyo | 2nd Eng'g. Dist. | Completed | 2020-04-07 | 2020-09-07 | 2018 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Project Engineer: | Estorco | Revised Completion Date: | September 1, 2020 | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
Panabo City | Nanyo | 2nd Eng'g. Dist. | Completed | 2020-04-07 | 2020-09-07 | 2018 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Implementor: | RLHV | No. of days suspended: | 86 | Disbursement: |  | Actual: | 5% | Actual: | 95.6% | Actual: | 100% | Actual: | 100% | Actual: | 100%
Panabo City | Nanyo | 2nd Eng'g. Dist. | Completed | 2020-04-07 | 2020-09-07 | 2018 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Duration: | 60 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | -4.4% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Panabo City | Nanyo | 2nd Eng'g. Dist. | Completed | 2020-04-07 | 2020-09-07 | 2018 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Date Allotment Released: |  | Date completed: | 2020-09-07
Panabo City | Nanyo | 2nd Eng'g. Dist. | Completed | 2020-04-07 | 2020-09-07 | 2018 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Date Started: | 2020-04-07
Sto. Tomas | Balagunan | 2nd Eng'g. Dist. | Completed | 2020-08-27 | 2020-10-02 | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | Construction of Multi-Purpose Building, Balagunan, Sto. Tomas |  | SB # 4 CY 2019 (STIMULUS) | Building |  |  |  | Project Cost: | 500000 | Target Completion Date: | 2020-12-25 | Program: | 500000 | Planned: |  | Planned: | 65.93% | Planned: | 65.1% | Planned: | 100% | Planned: | 100% | No. of Persons: | 6 | For implementation | On-going | On-going | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per Program of Works
Sto. Tomas | Balagunan | 2nd Eng'g. Dist. | Completed | 2020-08-27 | 2020-10-02 | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Project Engineer: | Azotes | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 132
Sto. Tomas | Balagunan | 2nd Eng'g. Dist. | Completed | 2020-08-27 | 2020-10-02 | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Implementor: | Digos Constrak Corp | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: | 65.93% | Actual: | 74.25% | Actual: | 100% | Actual: | 100%
Sto. Tomas | Balagunan | 2nd Eng'g. Dist. | Completed | 2020-08-27 | 2020-10-02 | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Duration: | 120 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 9.15% | Slippage: | 0% | Slippage: | 0%
Sto. Tomas | Balagunan | 2nd Eng'g. Dist. | Completed | 2020-08-27 | 2020-10-02 | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Date Allotment Released: |  | Date completed: | 2020-10-02
Sto. Tomas | Balagunan | 2nd Eng'g. Dist. | Completed | 2020-08-27 | 2020-10-02 | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Date Started: | 2020-08-27
B.E. Dujali | Dujali | 2nd Eng'g. Dist. | Completed | 2020-08-31 | 2020-09-30 | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | Concreting of Brgy. Road Canal, Dujali, B.E. Dujali (Note: Additional Fund Php150,000.00) |  | SB No. 4 CY 2019 (STIMULUS) | Concreting |  |  | Contract | Project Cost: | 650000 | Target Completion Date: | 2020-12-29 | Program: | 650000 | Planned: |  | Planned: |  | Planned: | 41.2% | Planned: | 100% | Planned: | 100% | No. of Persons: | 0 | For implementation | On-going | On-going | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per Program of Works
B.E. Dujali | Dujali | 2nd Eng'g. Dist. | Completed | 2020-08-31 | 2020-09-30 | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Project Engineer: | Estorco | Revised Completion Date: |  | Allotment: | 650000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 0
B.E. Dujali | Dujali | 2nd Eng'g. Dist. | Completed | 2020-08-31 | 2020-09-30 | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Implementor: | DANIMERH CONST. & SUPPLY | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: | 68.6% | Actual: | 100% | Actual: | 100%
B.E. Dujali | Dujali | 2nd Eng'g. Dist. | Completed | 2020-08-31 | 2020-09-30 | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Duration: | 120 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 27.4% | Slippage: | 0% | Slippage: | 0%
B.E. Dujali | Dujali | 2nd Eng'g. Dist. | Completed | 2020-08-31 | 2020-09-30 | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Date Allotment Released: |  | Date completed: | 2020-09-30
B.E. Dujali | Dujali | 2nd Eng'g. Dist. | Completed | 2020-08-31 | 2020-09-30 | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Date Started: | 2020-08-31
Tagum City | Magugpo South | 1st Eng'g. Dist. | For Implementation |  |  | 2019 |  | . | STIMULUS 2019 | Const. of Brgy. Health Center, Magugpo South, Tagum City |  | SB No. 4 CY 2019 (STIMULUS) | Building |  |  |  | Project Cost: | 1550000 | Target Completion Date: |  | Program: | 1550000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Amended in the AIP 3rd revision CY 2019 /SB No. 4 CY 2019 changing the total project cost to P1,550,000.00 | For implementation (Awarded to Royal Summit Infinity Dev't. Corp.), ; (Note: Additional Fund Php P1,050,000.00) | For implementation (Awarded to Royal Summit Infinity Dev't. Corp.), ; (Note: Additional Fund Php P1,050,000.00) | For implementation (Awarded to Royal Summit Infinity Dev't. Corp.), ; (Note: Additional Fund Php P1,050,000.00) | For implementation (Awarded to Royal Summit Infinity Dev't. Corp.), ; (Note: Additional Fund Php P1,050,000.00) | For implementation (Awarded to Royal Summit Infinity Dev't. Corp.), ; (Note: Additional Fund Php P1,050,000.00)
Tagum City | Magugpo South | 1st Eng'g. Dist. | For Implementation |  |  | 2019 |  | . | STIMULUS 2019 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 1550000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
Tagum City | Magugpo South | 1st Eng'g. Dist. | For Implementation |  |  | 2019 |  | . | STIMULUS 2019 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
Tagum City | Magugpo South | 1st Eng'g. Dist. | For Implementation |  |  | 2019 |  | . | STIMULUS 2019 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Tagum City | Magugpo South | 1st Eng'g. Dist. | For Implementation |  |  | 2019 |  | . | STIMULUS 2019 | [7 empty] | Date Allotment Released: |  | Date completed:
Tagum City | Magugpo South | 1st Eng'g. Dist. | For Implementation |  |  | 2019 |  | . | STIMULUS 2019 | [7 empty] | Date Started:
kapalong | Maniki | 1st Eng'g. Dist. | Pending |  |  | 2019 |  | . | STIMULUS 2019 | Completion of Brgy. Health Center, Maniki, Kapalong |  | SB No. 4 CY 2019 (STIMULUS) | Building |  |  |  | Project Cost: | 627000 | Target Completion Date: |  | Program: | 627000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | PROJECT Was funded by LGU, Kapalong | PROJECT Was funded by LGU, Kapalong | PROJECT Was funded by LGU, Kapalong | For amendment.To submit a new resolution for another priority project which is the Const. of Multi-Purpose Pavement but the propose site is not is donated because the previous project Completion of Brgy. Health Center was funded by the LGU of Kapalong | For amendment.To submit a new resolution for another priority project which is the Const. of Multi-Purpose Pavement but the propose site is not is donated because the previous project Completion of Brgy. Health Center was funded by the LGU of Kapalong | For amendment.To submit a new resolution for another priority project which is the Const. of Multi-Purpose Pavement but the propose site is not is donated because the previous project Completion of Brgy. Health Center was funded by the LGU of Kapalong
kapalong | Maniki | 1st Eng'g. Dist. | Pending |  |  | 2019 |  | . | STIMULUS 2019 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 627000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
kapalong | Maniki | 1st Eng'g. Dist. | Pending |  |  | 2019 |  | . | STIMULUS 2019 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
kapalong | Maniki | 1st Eng'g. Dist. | Pending |  |  | 2019 |  | . | STIMULUS 2019 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
kapalong | Maniki | 1st Eng'g. Dist. | Pending |  |  | 2019 |  | . | STIMULUS 2019 | [7 empty] | Date Allotment Released: |  | Date completed:
kapalong | Maniki | 1st Eng'g. Dist. | Pending |  |  | 2019 |  | . | STIMULUS 2019 | [7 empty] | Date Started:
Asuncion | New Santiago | 1st Eng'g. Dist. | Procurement on process |  |  | 2019 |  | . | STIMULUS 2019 | Construction of Potable Water System at Purok 6, New Santiago, Asuncion |  | SB No. 4 CY 2019 (STIMULUS) | Water System |  |  | contract | Project Cost: | 1000000 | Target Completion Date: |  | Program: | 1000000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Change of POW to Contract Procurement on process ( Amended in AIP 3rd revision CY 2019 increasing the amount to complete the project For plan preparation c/o Amamio) Additional fund Php 500,000 | Procurement on process ( Amended in AIP 3rd revision CY 2019 increasing the amount to complete the project For plan preparation c/o Amamio) Additional fund Php 500,000 | Awarded to Two Degrees Construction & Supply | Awarded to Two Degrees Construction & Supply | Awarded to Two Degrees Construction & Supply | Awarded to Two Degrees Construction & Supply
Asuncion | New Santiago | 1st Eng'g. Dist. | Procurement on process |  |  | 2019 |  | . | STIMULUS 2019 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 1000000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
Asuncion | New Santiago | 1st Eng'g. Dist. | Procurement on process |  |  | 2019 |  | . | STIMULUS 2019 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
Asuncion | New Santiago | 1st Eng'g. Dist. | Procurement on process |  |  | 2019 |  | . | STIMULUS 2019 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Asuncion | New Santiago | 1st Eng'g. Dist. | Procurement on process |  |  | 2019 |  | . | STIMULUS 2019 | [7 empty] | Date Allotment Released: |  | Date completed:
Asuncion | New Santiago | 1st Eng'g. Dist. | Procurement on process |  |  | 2019 |  | . | STIMULUS 2019 | [7 empty] | Date Started:
New Corella | Poblacion | 1st Eng'g. Dist. | On-going | 2019-11-25 |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | Construction of Children's Playground with Amenities, Poblacion, New Corella |  | SB No. 4 CY 2019 (STIMULUS) | Building |  | sq.m | Admin | Project Cost: | 2500000 | Target Completion Date: | 2020-03-03 23:59 | Program: | 2500000 | Planned: | 57.9% | Planned: | 64.73% | Planned: | 64.73% | Planned: | 64.73% | Planned: | 64.73% | No. of Persons: | 10 | On-going (Suspended effective April 5, 2020 due to COVID; resumption order dated May 4, 2020) | On-going (Suspended effective April 5, 2020 due to COVID; resumption order dated May 4, 2020) | On-going (Suspended effective April 5, 2020 due to COVID; resumption order dated May 4, 2020) |  |  | On-going
New Corella | Poblacion | 1st Eng'g. Dist. | On-going | 2019-11-25 |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Project Engineer: | Mayang | Revised Completion Date: | 2020-04-30 23:59 | Allotment: | 2500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 150
New Corella | Poblacion | 1st Eng'g. Dist. | On-going | 2019-11-25 |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Implementor: | PEO | No. of days suspended: | 28 | Disbursement: | 1029250 | Actual: | 57.9% | Actual: | 64.73% | Actual: | 64.73% | Actual: | 64.73% | Actual: | 64.73%
New Corella | Poblacion | 1st Eng'g. Dist. | On-going | 2019-11-25 |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Duration: | 100 | No. of days extended: | 30 |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
New Corella | Poblacion | 1st Eng'g. Dist. | On-going | 2019-11-25 |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Allotment Released: | 2019-12-06 | Date completed:
New Corella | Poblacion | 1st Eng'g. Dist. | On-going | 2019-11-25 |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Started: | 2019-11-25
B.E. Dujali | Tanglaw | 2nd Eng'g. Dist. | Completed | 2020-08-31 | 2020-10-30 | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | Concreting of Drainage, Tanglaw, B.E., Dujali (Note: Additional Fund Php700,000.00) |  | SB # 4 CY 2019 (STIMULUS | Concreting |  |  | Contract | Project Cost: | 1200000 | Target Completion Date: | 2020-12-29 | Program: | 1200000 | Planned: |  | Planned: |  | Planned: | 43.5% | Planned: | 100% | Planned: | 100% | No. of Persons: | 4 | For implementation | On-going | On-going | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per Program of Works
B.E. Dujali | Tanglaw | 2nd Eng'g. Dist. | Completed | 2020-08-31 | 2020-10-30 | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Project Engineer: | Estorco | Revised Completion Date: |  | Allotment: | 1200000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 88
B.E. Dujali | Tanglaw | 2nd Eng'g. Dist. | Completed | 2020-08-31 | 2020-10-30 | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Implementor: | DANIMERH CONST. & SUPPLY | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: | 12.3% | Actual: | 100% | Actual: | 100%
B.E. Dujali | Tanglaw | 2nd Eng'g. Dist. | Completed | 2020-08-31 | 2020-10-30 | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Duration: | 120 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | -31.2% | Slippage: | 0% | Slippage: | 0%
B.E. Dujali | Tanglaw | 2nd Eng'g. Dist. | Completed | 2020-08-31 | 2020-10-30 | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Allotment Released: |  | Date completed: | 2020-10-30
B.E. Dujali | Tanglaw | 2nd Eng'g. Dist. | Completed | 2020-08-31 | 2020-10-30 | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Started: | 2020-08-31
B.E. Dujali | New Casay | 2nd Eng'g. Dist. | Re-aligned to COVID |  |  | 2019 |  | . | STIMULUS 2019 | Desilting and Concreting of Drainage-Main Collector Canal, New Casay, B.E. Dujali |  | SB # 4 CY 2019 (STIMULUS | Desiltation |  |  | Contract | Project Cost: | 650000 | Target Completion Date: | 0 | Program: | 650000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
B.E. Dujali | New Casay | 2nd Eng'g. Dist. | Re-aligned to COVID |  |  | 2019 |  | . | STIMULUS 2019 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 650000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
B.E. Dujali | New Casay | 2nd Eng'g. Dist. | Re-aligned to COVID |  |  | 2019 |  | . | STIMULUS 2019 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
B.E. Dujali | New Casay | 2nd Eng'g. Dist. | Re-aligned to COVID |  |  | 2019 |  | . | STIMULUS 2019 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: |  | Slippage: |  | Slippage:
B.E. Dujali | New Casay | 2nd Eng'g. Dist. | Re-aligned to COVID |  |  | 2019 |  | . | STIMULUS 2019 | [7 empty] | Date Allotment Released: |  | Date completed:
B.E. Dujali | New Casay | 2nd Eng'g. Dist. | Re-aligned to COVID |  |  | 2019 |  | . | STIMULUS 2019 | [7 empty] | Date Started:
Tagum City | Magugpo Poblacion | 1st Eng'g. Dist. | Completed | 2020-06-12 | 2020-07-02 | 2019 | Contract | . | STIMULUS 2019 | Rehabilitation of Evacuation Center at Magugpo Pob., Tagum City |  | SB # 4 CY 2019 (STIMULUS | Building |  |  |  | Project Cost: | 600000 | Target Completion Date: | 2020-08-20 23:59 | Program: | 600000 | Planned: | 100% | Planned: | 100% | Planned: | 100% | Planned: | 100% | Planned: | 100% | No. of Persons: |  | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per Program of Works
Tagum City | Magugpo Poblacion | 1st Eng'g. Dist. | Completed | 2020-06-12 | 2020-07-02 | 2019 | Contract | . | STIMULUS 2019 | [7 empty] | Project Engineer: | Juan | Revised Completion Date: |  | Allotment: | 600000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
Tagum City | Magugpo Poblacion | 1st Eng'g. Dist. | Completed | 2020-06-12 | 2020-07-02 | 2019 | Contract | . | STIMULUS 2019 | [7 empty] | Implementor: | JJR Construction | No. of days suspended: |  | Disbursement: |  | Actual: | 100% | Actual: | 100% | Actual: | 100% | Actual: | 100% | Actual: | 100%
Tagum City | Magugpo Poblacion | 1st Eng'g. Dist. | Completed | 2020-06-12 | 2020-07-02 | 2019 | Contract | . | STIMULUS 2019 | [7 empty] | Duration: | 70 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Tagum City | Magugpo Poblacion | 1st Eng'g. Dist. | Completed | 2020-06-12 | 2020-07-02 | 2019 | Contract | . | STIMULUS 2019 | [7 empty] | Date Allotment Released: |  | Date completed: | 2020-07-02
Tagum City | Magugpo Poblacion | 1st Eng'g. Dist. | Completed | 2020-06-12 | 2020-07-02 | 2019 | Contract | . | STIMULUS 2019 | [7 empty] | Date Started: | 2020-06-12
Panabo City | Salvacion | 2nd Eng'g. Dist. | Completed | 2020-08-31 | 2020-11-16 | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | Const. of Canal Lining at Purok 5, Salvacion, Panabo City (Note: Additional Fund Php 100,000.00) |  | SB # 4 (20% DF CY 2019 STIMULUS) | Building |  |  | Contract | Project Cost: | 600000 | Target Completion Date: | 2020-12-29 | Program: | 600000 | Planned: |  | Planned: |  | Planned: | 33.2% | Planned: | 100% | Planned: | 100% | No. of Persons: | 5 | PO #2020041516- DANIMERH CONSTRUCTION & SUPPLY | On-going | On-going | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per Program of Works
Panabo City | Salvacion | 2nd Eng'g. Dist. | Completed | 2020-08-31 | 2020-11-16 | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Project Engineer: | Estorco | Revised Completion Date: |  | Allotment: | 600000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 110
Panabo City | Salvacion | 2nd Eng'g. Dist. | Completed | 2020-08-31 | 2020-11-16 | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Implementor: | DANIMERH CONST. & SUPPLY | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: | 65.3% | Actual: | 100% | Actual: | 100%
Panabo City | Salvacion | 2nd Eng'g. Dist. | Completed | 2020-08-31 | 2020-11-16 | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Duration: | 120 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 32.1% | Slippage: | 0% | Slippage: | 0%
Panabo City | Salvacion | 2nd Eng'g. Dist. | Completed | 2020-08-31 | 2020-11-16 | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Allotment Released: | 2019-10-18 | Date completed: | 2020-11-16
Panabo City | Salvacion | 2nd Eng'g. Dist. | Completed | 2020-08-31 | 2020-11-16 | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Started: | 2020-08-31
New Corella | Limbaan | 1st Eng'g. Dist. | Procurement on process |  |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | Rehab. Of Multi-Purpose Building (Evacuation Center), Limbaan, New Corella |  | SB NO. 4 CY 2019 (STIMULUS) | Building |  |  |  | Project Cost: | 600000 | Target Completion Date: |  | Program: | 600000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | From SB # 1 to SB # 4 CY 2019 (Transfer to Contract) Procurement on process | From SB # 1 to SB # 4 CY 2019 (Transfer to Contract) Procurement on process | From SB # 1 to SB # 4 CY 2019 (Transfer to Contract) Procurement on process |  |  | From SB # 1 to SB # 4 CY 2019 (Transfer to Contract) Procurement on process
New Corella | Limbaan | 1st Eng'g. Dist. | Procurement on process |  |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 600000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
New Corella | Limbaan | 1st Eng'g. Dist. | Procurement on process |  |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
New Corella | Limbaan | 1st Eng'g. Dist. | Procurement on process |  |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
New Corella | Limbaan | 1st Eng'g. Dist. | Procurement on process |  |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Allotment Released: |  | Date completed:
New Corella | Limbaan | 1st Eng'g. Dist. | Procurement on process |  |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Started:
Panabo City | Waterfall | 2nd Eng'g. Dist. | Completed | 2020-09-02 | 2020-10-26 | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | Construction of Multi-Purpose Hall, Waterfall, Panabo City (Note: Additional Fund Php 550,000.00) |  | SB # 4 CY 2019 (STIMULUS | Building |  |  |  | Project Cost: | 1050000 | Target Completion Date: | 2020-10-26 23:59 | Program: | 1050000 | Planned: |  | Planned: |  | Planned: |  | Planned: | 100% | Planned: | 100% | No. of Persons: |  | For implementation | For implementation | For implementation | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per Program of Works
Panabo City | Waterfall | 2nd Eng'g. Dist. | Completed | 2020-09-02 | 2020-10-26 | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Project Engineer: | Abayon | Revised Completion Date: |  | Allotment: | 1050000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
Panabo City | Waterfall | 2nd Eng'g. Dist. | Completed | 2020-09-02 | 2020-10-26 | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Implementor: | Digos Constrak Corp | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: | 100% | Actual: | 100%
Panabo City | Waterfall | 2nd Eng'g. Dist. | Completed | 2020-09-02 | 2020-10-26 | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Duration: | 55 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Panabo City | Waterfall | 2nd Eng'g. Dist. | Completed | 2020-09-02 | 2020-10-26 | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Date Allotment Released: |  | Date completed: | 2020-10-26 23:59
Panabo City | Waterfall | 2nd Eng'g. Dist. | Completed | 2020-09-02 | 2020-10-26 | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Date Started: | 2020-09-02
Panabo City | Dalisay | 2nd Eng'g. Dist. | Completed | 2020-09-02 | 2020-10-05 | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | Rehabilitation of Brgy. Health Center, Dalisay, Panabo City (Noted: Additional Fund Php 50,000.00) |  | SB # 4 CY 2019 (STIMULUS | Building |  |  |  | Project Cost: | 550000 | Target Completion Date: | 2020-10-05 | Program: | 550000 | Planned: |  | Planned: |  | Planned: |  | Planned: | 100% | Planned: | 100% | No. of Persons: |  | For implementation | For implementation | For implementation | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per Program of Works
Panabo City | Dalisay | 2nd Eng'g. Dist. | Completed | 2020-09-02 | 2020-10-05 | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Project Engineer: | Abayon | Revised Completion Date: |  | Allotment: | 550000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
Panabo City | Dalisay | 2nd Eng'g. Dist. | Completed | 2020-09-02 | 2020-10-05 | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Implementor: | Digos Constrak Corp | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: | 100% | Actual: | 100%
Panabo City | Dalisay | 2nd Eng'g. Dist. | Completed | 2020-09-02 | 2020-10-05 | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Panabo City | Dalisay | 2nd Eng'g. Dist. | Completed | 2020-09-02 | 2020-10-05 | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Date Allotment Released: |  | Date completed: | 2020-10-05
Panabo City | Dalisay | 2nd Eng'g. Dist. | Completed | 2020-09-02 | 2020-10-05 | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Date Started: | 2020-09-02
Sto. Tomas | San Miguel | 2nd Eng'g. Dist. | Completed | 2020-07-14 | 2020-10-28 | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | Rehab. Of Multi-Purpose Hall, San Miguel, Sto. Tomas |  | SB # 4 CY 2019 (STIMULUS | Building |  |  | Contract | Project Cost: | 500000 | Target Completion Date: | 2020-11-11 | Program: | 500000 | Planned: |  | Planned: |  | Planned: | 68.5% | Planned: | 68.5% | Planned: | 100% | No. of Persons: | 6 | For implementation | On-going | On-going | On-going | On-going | Completed as per Program of Works
Sto. Tomas | San Miguel | 2nd Eng'g. Dist. | Completed | 2020-07-14 | 2020-10-28 | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Project Engineer: | Estorco | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 132
Sto. Tomas | San Miguel | 2nd Eng'g. Dist. | Completed | 2020-07-14 | 2020-10-28 | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Implementor: | JJR Const. & Supply | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: | 75.6% | Actual: | 75.6% | Actual: | 100%
Sto. Tomas | San Miguel | 2nd Eng'g. Dist. | Completed | 2020-07-14 | 2020-10-28 | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Duration: | 120 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 7.1% | Slippage: | 7.1% | Slippage: | 0%
Sto. Tomas | San Miguel | 2nd Eng'g. Dist. | Completed | 2020-07-14 | 2020-10-28 | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Allotment Released: | 2019-06-07 | Date completed: | 2020-10-28
Sto. Tomas | San Miguel | 2nd Eng'g. Dist. | Completed | 2020-07-14 | 2020-10-28 | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Started: | 2020-07-14
Sto. Tomas | San Jose | 2nd Eng'g. Dist. | Completed | 2020-07-14 | 2020-09-21 | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | Completion of Multi-Purpose Hall, San Jose, Sto. Tomas |  | SB # 4 CY 2019 (STIMULUS | Building |  |  |  | Project Cost: | 600000 | Target Completion Date: | 2020-11-11 | Program: | 600000 | Planned: |  | Planned: |  | Planned: |  | Planned: | 100% | Planned: | 100% | No. of Persons: | 5 | For implementation | For implementation | For implementation | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per Program of Works
Sto. Tomas | San Jose | 2nd Eng'g. Dist. | Completed | 2020-07-14 | 2020-09-21 | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Project Engineer: | Estorco | Revised Completion Date: |  | Allotment: | 600000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 115
Sto. Tomas | San Jose | 2nd Eng'g. Dist. | Completed | 2020-07-14 | 2020-09-21 | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Implementor: | JJR Const. & Supply | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: | 100% | Actual: | 100%
Sto. Tomas | San Jose | 2nd Eng'g. Dist. | Completed | 2020-07-14 | 2020-09-21 | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Duration: | 120 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Sto. Tomas | San Jose | 2nd Eng'g. Dist. | Completed | 2020-07-14 | 2020-09-21 | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Date Allotment Released: |  | Date completed: | September 21, 2020
Sto. Tomas | San Jose | 2nd Eng'g. Dist. | Completed | 2020-07-14 | 2020-09-21 | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Date Started: | 2020-07-14
Sto. Tomas | Pantaron | 2nd Eng'g. Dist. | For Implementation |  |  | 2019 |  | . | Stimulus Projects for Various Barangays | Rehabilitation of Multi-Purpose Hall, Pantaron, Sto. Tomas |  | SB # 4 CY 2019 (STIMULUS | Building |  |  |  | Project Cost: | 550000 | Target Completion Date: |  | Program: | 550000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | For implementation | For implementation | For implementation | For implementation | For implementation | For implementation
Sto. Tomas | Pantaron | 2nd Eng'g. Dist. | For Implementation |  |  | 2019 |  | . | Stimulus Projects for Various Barangays | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 550000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
Sto. Tomas | Pantaron | 2nd Eng'g. Dist. | For Implementation |  |  | 2019 |  | . | Stimulus Projects for Various Barangays | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
Sto. Tomas | Pantaron | 2nd Eng'g. Dist. | For Implementation |  |  | 2019 |  | . | Stimulus Projects for Various Barangays | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Sto. Tomas | Pantaron | 2nd Eng'g. Dist. | For Implementation |  |  | 2019 |  | . | Stimulus Projects for Various Barangays | [7 empty] | Date Allotment Released: |  | Date completed:
Sto. Tomas | Pantaron | 2nd Eng'g. Dist. | For Implementation |  |  | 2019 |  | . | Stimulus Projects for Various Barangays | [7 empty] | Date Started:
Sto. Tomas | salvacion | 2nd Eng'g. Dist. | Re-aligned to COVID |  |  | 2019 |  | . | Stimulus Projects for Various Barangays | Rehabilitation of Multi-Purpose Hall, Salvacion, Sto. Tomas |  | SB # 4 CY 2019 (STIMULUS | Building |  |  |  | Project Cost: | 1000000 | Target Completion Date: |  | Program: | 1000000 | Planned: |  | Planned: |  | Planned: |  | Planned: | 100% | Planned: | 100% | No. of Persons: |  | PR #20032281 | PR #20032281 | PR #20032281 | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
Sto. Tomas | salvacion | 2nd Eng'g. Dist. | Re-aligned to COVID |  |  | 2019 |  | . | Stimulus Projects for Various Barangays | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 1000000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
Sto. Tomas | salvacion | 2nd Eng'g. Dist. | Re-aligned to COVID |  |  | 2019 |  | . | Stimulus Projects for Various Barangays | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: | 100% | Actual: | 100%
Sto. Tomas | salvacion | 2nd Eng'g. Dist. | Re-aligned to COVID |  |  | 2019 |  | . | Stimulus Projects for Various Barangays | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Sto. Tomas | salvacion | 2nd Eng'g. Dist. | Re-aligned to COVID |  |  | 2019 |  | . | Stimulus Projects for Various Barangays | [7 empty] | Date Allotment Released: |  | Date completed:
Sto. Tomas | salvacion | 2nd Eng'g. Dist. | Re-aligned to COVID |  |  | 2019 |  | . | Stimulus Projects for Various Barangays | [7 empty] | Date Started:
IGCS | Tagpopongan | 2nd Eng'g. Dist. | For Implementation |  |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | Rehabilitation of Multi-Purpose Bldg. (Brgy. Hall) Tagpopongan, IGACOS |  | SB # 4 CY 2019 (STIMULUS | Building |  |  |  | Project Cost: | 174460.33 | Target Completion Date: |  | Program: | 174460.33 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Procurement on process | Procurement on process | Procurement on process |  |  | Procurement on process
IGCS | Tagpopongan | 2nd Eng'g. Dist. | For Implementation |  |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 174460.33 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
IGCS | Tagpopongan | 2nd Eng'g. Dist. | For Implementation |  |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
IGCS | Tagpopongan | 2nd Eng'g. Dist. | For Implementation |  |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
IGCS | Tagpopongan | 2nd Eng'g. Dist. | For Implementation |  |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Date Allotment Released: |  | Date completed:
IGCS | Tagpopongan | 2nd Eng'g. Dist. | For Implementation |  |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Date Started:
Carmen | Sto. Niño | 2nd Eng'g. Dist. | Completed | 2020-08-27 | 2020-11-13 | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | Construction of Evacuation Center at Purok 1-C Brgy. Sto. Niño, Carmen |  | SB # 4 CY 2019 (STIMULUS | Building |  |  |  | Project Cost: | 500000 | Target Completion Date: | 2020-12-25 | Program: | 500000 | Planned: |  | Planned: |  | Planned: |  | Planned: | 36.15% | Planned: | 100% | No. of Persons: | 5 | For implementation | For implementation | For implementation | On-going | On-going | Completed as per Program of Works
Carmen | Sto. Niño | 2nd Eng'g. Dist. | Completed | 2020-08-27 | 2020-11-13 | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Project Engineer: | Estorco | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 110
Carmen | Sto. Niño | 2nd Eng'g. Dist. | Completed | 2020-08-27 | 2020-11-13 | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Implementor: | Digos Constrak Corp | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: | 30.6% | Actual: | 100%
Carmen | Sto. Niño | 2nd Eng'g. Dist. | Completed | 2020-08-27 | 2020-11-13 | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Duration: | 120 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | -5.55% | Slippage: | 0%
Carmen | Sto. Niño | 2nd Eng'g. Dist. | Completed | 2020-08-27 | 2020-11-13 | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Date Allotment Released: |  | Date completed: | 2020-11-13
Carmen | Sto. Niño | 2nd Eng'g. Dist. | Completed | 2020-08-27 | 2020-11-13 | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Date Started: | 2020-08-27
Panabo City | Datu Abdul | 2nd Eng'g. Dist. | Completed | 2020-08-27 | 2020-12-02 | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | Rehab. Of Evacuation Center, Datu Abdul Dadia, Panabo City (Note: Additional Fund Php 150,000.00) |  | SB # 4 (20% DF CY 2019 (STIMULUS) | Building |  |  | Contract | Project Cost: | 650000 | Target Completion Date: | 2021-02-03 | Program: | 650000 | Planned: |  | Planned: |  | Planned: | 5% | Planned: | 21.2% | Planned: | 100% | No. of Persons: | 6 | Purchase Order # 2020031248- DIGOS CONSTRAK | For implementation (DIGOS CONSTRAK) | On-going | On-going | On-going | Completed as per Program of Works
Panabo City | Datu Abdul | 2nd Eng'g. Dist. | Completed | 2020-08-27 | 2020-12-02 | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Project Engineer: | Andoy | Revised Completion Date: |  | Allotment: | 650000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 132
Panabo City | Datu Abdul | 2nd Eng'g. Dist. | Completed | 2020-08-27 | 2020-12-02 | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Implementor: | Digos Constrak Corp/ | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: | 5% | Actual: | 8.26% | Actual: | 100%
Panabo City | Datu Abdul | 2nd Eng'g. Dist. | Completed | 2020-08-27 | 2020-12-02 | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Duration: | 160 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | -12.94% | Slippage: | 0%
Panabo City | Datu Abdul | 2nd Eng'g. Dist. | Completed | 2020-08-27 | 2020-12-02 | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Allotment Released: | 2019-10-18 | Date completed: | 2020-12-02
Panabo City | Datu Abdul | 2nd Eng'g. Dist. | Completed | 2020-08-27 | 2020-12-02 | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Started: | 2020-08-27
Tagum City | Magugpo Poblacion | 1st Eng'g. Dist. | Completed | 2020-06-12 | 2020-07-02 | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | Rehab. of Evacuation Center, Magugpo Poblacion, Tagum City |  | SB # 4 (20% DF CY 2019 (STIMULUS) | Building |  |  |  | Project Cost: | 500000 | Target Completion Date: | 2020-08-20 23:46 | Program: | 500000 | Planned: | 100% | Planned: | 100% | Planned: | 100% | Planned: | 100% | Planned: | 100% | No. of Persons: |  | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. |  |  | Completed as per Program of Works
Tagum City | Magugpo Poblacion | 1st Eng'g. Dist. | Completed | 2020-06-12 | 2020-07-02 | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Project Engineer: | JJR Const. & Supply | Revised Completion Date: | 2020-08-20 23:46 | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
Tagum City | Magugpo Poblacion | 1st Eng'g. Dist. | Completed | 2020-06-12 | 2020-07-02 | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: | 100% | Actual: | 100% | Actual: | 100% | Actual: | 100% | Actual: | 100%
Tagum City | Magugpo Poblacion | 1st Eng'g. Dist. | Completed | 2020-06-12 | 2020-07-02 | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Duration: | 70 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Tagum City | Magugpo Poblacion | 1st Eng'g. Dist. | Completed | 2020-06-12 | 2020-07-02 | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Allotment Released: |  | Date completed: | 2020-07-02
Tagum City | Magugpo Poblacion | 1st Eng'g. Dist. | Completed | 2020-06-12 | 2020-07-02 | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Started: | 2020-06-12
Kaputian, IGCS | Poblacion | 2nd Eng'g. Dist. | For Implementation |  |  | 2019 |  | . | Stimulus Projects for Various Barangays | Construction of Water System Project, Poblacion Kaputian, Samal |  | SB # 4 CY 2019 (20% DF -STIMULUS) | Water System |  |  | Contract | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | For implementation | For implementation | For implementation | For implementation | For implementation | For implementation
Kaputian, IGCS | Poblacion | 2nd Eng'g. Dist. | For Implementation |  |  | 2019 |  | . | Stimulus Projects for Various Barangays | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
Kaputian, IGCS | Poblacion | 2nd Eng'g. Dist. | For Implementation |  |  | 2019 |  | . | Stimulus Projects for Various Barangays | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
Kaputian, IGCS | Poblacion | 2nd Eng'g. Dist. | For Implementation |  |  | 2019 |  | . | Stimulus Projects for Various Barangays | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Kaputian, IGCS | Poblacion | 2nd Eng'g. Dist. | For Implementation |  |  | 2019 |  | . | Stimulus Projects for Various Barangays | [7 empty] | Date Allotment Released: |  | Date completed:
Kaputian, IGCS | Poblacion | 2nd Eng'g. Dist. | For Implementation |  |  | 2019 |  | . | Stimulus Projects for Various Barangays | [7 empty] | Date Started:
Panabo City | Cagangohan | 2nd Eng'g. Dist. | Completed | 2020-08-27 | 2020-10-15 | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | Rehabilitation of Evacuation Center, Cagangohan, Panabo City |  | SB # 4 CY 2019 (20% DF -STIMULUS) | Building |  |  |  | Project Cost: | 500000 | Target Completion Date: | 2020-12-25 | Program: | 500000 | Planned: |  | Planned: | 69.53% | Planned: | 54.2% | Planned: | 100% | Planned: | 100% | No. of Persons: | 6 | Abstract #0520201798 - Digos constrak | On-going (DIGOS CONSTRAK CORP.) | On-going (DIGOS CONSTRAK CORP.) | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per Program of Works
Panabo City | Cagangohan | 2nd Eng'g. Dist. | Completed | 2020-08-27 | 2020-10-15 | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Project Engineer: | Andoy | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 132
Panabo City | Cagangohan | 2nd Eng'g. Dist. | Completed | 2020-08-27 | 2020-10-15 | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Implementor: | Digos Constrak Corp | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: | 69.53% | Actual: | 69.53% | Actual: | 100% | Actual: | 100%
Panabo City | Cagangohan | 2nd Eng'g. Dist. | Completed | 2020-08-27 | 2020-10-15 | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Duration: | 120 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 15.33% | Slippage: | 0% | Slippage: | 0%
Panabo City | Cagangohan | 2nd Eng'g. Dist. | Completed | 2020-08-27 | 2020-10-15 | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Date Allotment Released: |  | Date completed: | 2020-10-15
Panabo City | Cagangohan | 2nd Eng'g. Dist. | Completed | 2020-08-27 | 2020-10-15 | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Date Started: | 2020-08-27
Sto. Tomas | Lunga-og | 2nd Eng'g. Dist. | Completed | 2020-08-05 | 2020-12-31 | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | Rehab. Of Brgy. Road, Lunga-og, Sto. Tomas |  | SB # 4 CY 2019 (STIMULUS) | Building |  |  |  | Project Cost: | 600000 | Target Completion Date: | 2020-09-04 | Program: | 600000 | Planned: |  | Planned: | 14.05% | Planned: | 100% | Planned: | 100% | Planned: | 100% | No. of Persons: | 7 | Amended in AIP 3rd revision CY 2019 / SB No. 4 CY 2019 increasing the project cost to P600,000.00 | On-going ( project cost increase to P600,000.00 | On-going ( project cost increase to P600,000.00 | On-going ( project cost increase to P600,000.00 | On-going ( project cost increase to P600,000.00 | Completed as per Program of Works
Sto. Tomas | Lunga-og | 2nd Eng'g. Dist. | Completed | 2020-08-05 | 2020-12-31 | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: | 2020-10-04 | Allotment: | 600000 | Revised: |  | Revised: |  | Revised: | 40.1% | Revised: | 77.4% | Revised: | 100% | No. of Man-days: | 154
Sto. Tomas | Lunga-og | 2nd Eng'g. Dist. | Completed | 2020-08-05 | 2020-12-31 | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: | 16.27% | Actual: | 26.93% | Actual: | 61.04% | Actual: | 100%
Sto. Tomas | Lunga-og | 2nd Eng'g. Dist. | Completed | 2020-08-05 | 2020-12-31 | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Duration: | 30 | No. of days extended: | 30 |  |  | Slippage: | 0% | Slippage: |  | Slippage: | -13.17% | Slippage: | -16.36% | Slippage: | 0%
Sto. Tomas | Lunga-og | 2nd Eng'g. Dist. | Completed | 2020-08-05 | 2020-12-31 | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Allotment Released: |  | Date completed: | 2020-12-31
Sto. Tomas | Lunga-og | 2nd Eng'g. Dist. | Completed | 2020-08-05 | 2020-12-31 | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Started: | 2020-08-05
Panabo City | Buenavista | 2nd Eng'g. Dist. | On-going | 2020-08-27 |  | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | Const. Of Multi-Purpose Hall, Buenavista, Panabo City |  | SB # 4 CY 2019 (STIMULUS) | Building |  |  | Contract | Project Cost: | 500000 | Target Completion Date: | 2021-02-03 | Program: | 500000 | Planned: |  | Planned: |  | Planned: | 5% | Planned: | 28.54% | Planned: | 28.54% | No. of Persons: | 7 | Purchase Order # 2020031248- DIGOS CONSTRAK | For implementation (DIGOS CONSTRAK) | On-going | On-going | On-going | On-going
Panabo City | Buenavista | 2nd Eng'g. Dist. | On-going | 2020-08-27 |  | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Project Engineer: | Andoy | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 154
Panabo City | Buenavista | 2nd Eng'g. Dist. | On-going | 2020-08-27 |  | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Implementor: | Digos Constrak Corp/ | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: | 5% | Actual: | 32.17% | Actual: | 32.17%
Panabo City | Buenavista | 2nd Eng'g. Dist. | On-going | 2020-08-27 |  | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Duration: | 160 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 3.63% | Slippage: | 3.63%
Panabo City | Buenavista | 2nd Eng'g. Dist. | On-going | 2020-08-27 |  | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Allotment Released: | 2019-10-18 | Date completed:
Panabo City | Buenavista | 2nd Eng'g. Dist. | On-going | 2020-08-27 |  | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Started: | 2020-08-27
Panabo City | Kasilak | 2nd Eng'g. Dist. | On-going | 2020-07-14 |  | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | Rehab. Of Multi-Purpose Hall, Kasilak, Panabo City |  | SB # 4 CY 2019 (STIMULUS) | Building |  |  | Contract | Project Cost: | 650000 | Target Completion Date: | 2020-11-11 | Program: | 650000 | Planned: |  | Planned: |  | Planned: | 56.3% | Planned: | 60.18% | Planned: | 60.18% | No. of Persons: | 4 | On-going | On-going | On-going | On-going | On-going | On-going
Panabo City | Kasilak | 2nd Eng'g. Dist. | On-going | 2020-07-14 |  | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Project Engineer: | Estorco | Revised Completion Date: |  | Allotment: | 650000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 88
Panabo City | Kasilak | 2nd Eng'g. Dist. | On-going | 2020-07-14 |  | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Implementor: | JJR Const. & Supply | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: | 45.3% | Actual: | 58.4% | Actual: | 58.4%
Panabo City | Kasilak | 2nd Eng'g. Dist. | On-going | 2020-07-14 |  | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Duration: | 120 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | -11% | Slippage: | -1.78% | Slippage: | -1.78%
Panabo City | Kasilak | 2nd Eng'g. Dist. | On-going | 2020-07-14 |  | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Panabo City | Kasilak | 2nd Eng'g. Dist. | On-going | 2020-07-14 |  | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Started: | 2020-07-14
Panabo City | Little Panay | 2nd Eng'g. Dist. | Completed | 2020-09-02 | 2020-10-06 | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | Rehabilitation of Multi-Purpose Hall, Llittle Panay, Panabo City (Note: Additional Fund Php 50,000.00) |  | SB # 4 CY 2019 (STIMULUS) | Building |  |  |  | Project Cost: | 550000 | Target Completion Date: | 2020-10-06 23:59 | Program: | 550000 | Planned: |  | Planned: |  | Planned: |  | Planned: | 100% | Planned: | 100% | No. of Persons: |  | For implementation | For implementation | For implementation | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per Program of Works
Panabo City | Little Panay | 2nd Eng'g. Dist. | Completed | 2020-09-02 | 2020-10-06 | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Project Engineer: | Andoy | Revised Completion Date: |  | Allotment: | 550000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
Panabo City | Little Panay | 2nd Eng'g. Dist. | Completed | 2020-09-02 | 2020-10-06 | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Implementor: | Digos Constrak Corp | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: | 100% | Actual: | 100%
Panabo City | Little Panay | 2nd Eng'g. Dist. | Completed | 2020-09-02 | 2020-10-06 | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Duration: | 35 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Panabo City | Little Panay | 2nd Eng'g. Dist. | Completed | 2020-09-02 | 2020-10-06 | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Date Allotment Released: |  | Date completed: | 2020-10-06 23:59
Panabo City | Little Panay | 2nd Eng'g. Dist. | Completed | 2020-09-02 | 2020-10-06 | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Date Started: | 2020-09-02
Panabo City | New Malitbog | 2nd Eng'g. Dist. | Re-aligned to COVID |  |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | Rehab. Of Multi-Purpose Hall, New Malitbog, Panabo City |  | SB # 4 CY 2019 (STIMULUS) | Building |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Amended in AIP 3rd revsion CY 2019 to change the project to Construction of Potable Water System because the original project will be funded by LGU, Panabo City (Brgy. resolution no. 25 series of 2019 dated Aug. 13, 2019 submitted) | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
Panabo City | New Malitbog | 2nd Eng'g. Dist. | Re-aligned to COVID |  |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
Panabo City | New Malitbog | 2nd Eng'g. Dist. | Re-aligned to COVID |  |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
Panabo City | New Malitbog | 2nd Eng'g. Dist. | Re-aligned to COVID |  |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Panabo City | New Malitbog | 2nd Eng'g. Dist. | Re-aligned to COVID |  |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Panabo City | New Malitbog | 2nd Eng'g. Dist. | Re-aligned to COVID |  |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Started:
Panabo City | San Francisco | 2nd Eng'g. Dist. | Completed | 2020-08-27 | 2020-12-04 | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | Rehab. Of Multi-Purpose Hall, San Francisco, Panabo City |  | SB NO. 4 CY 2019 (STIMULUS | Building |  |  | Contract | Project Cost: | 650000 | Target Completion Date: | 2021-02-03 | Program: | 650000 | Planned: |  | Planned: |  | Planned: | 5% | Planned: | 5% | Planned: | 100% | No. of Persons: |  | Purchase Order # 2020031248- DIGOS CONSTRAK | For implementation (DIGOS CONSTRAK) | On-going | On-going | On-going | Completed as per Program of Works
Panabo City | San Francisco | 2nd Eng'g. Dist. | Completed | 2020-08-27 | 2020-12-04 | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Project Engineer: | Andoy | Revised Completion Date: |  | Allotment: | 650000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
Panabo City | San Francisco | 2nd Eng'g. Dist. | Completed | 2020-08-27 | 2020-12-04 | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Implementor: | Digos Constrak Corp/ | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: | 5% | Actual: | 5% | Actual: | 100%
Panabo City | San Francisco | 2nd Eng'g. Dist. | Completed | 2020-08-27 | 2020-12-04 | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Duration: | 160 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Panabo City | San Francisco | 2nd Eng'g. Dist. | Completed | 2020-08-27 | 2020-12-04 | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Allotment Released: | 2019-10-18 | Date completed: | 2020-12-04
Panabo City | San Francisco | 2nd Eng'g. Dist. | Completed | 2020-08-27 | 2020-12-04 | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Started: | 2020-08-27
Panabo City | Kiotoy | 2nd Eng'g. Dist. | Completed | 2020-08-27 | 2020-11-10 | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | Rehabilitation of Evacuation Center, Kiotoy, Panabo City (Note: Additional Fund Php 150,000.00) |  | SB # 4 CY 2019 (20% DF CY 2017 -STIMULUS) | Building |  |  |  | Project Cost: | 650000 | Target Completion Date: | 2021-02-03 | Program: | 650000 | Planned: |  | Planned: |  | Planned: | 19.5% | Planned: | 100% | Planned: | 100% | No. of Persons: | 8 | For implementation | On-going | On-going | Completed | Completed | Completed as per Program of Works
Panabo City | Kiotoy | 2nd Eng'g. Dist. | Completed | 2020-08-27 | 2020-11-10 | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Project Engineer: | Andoy | Revised Completion Date: |  | Allotment: | 650000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 176
Panabo City | Kiotoy | 2nd Eng'g. Dist. | Completed | 2020-08-27 | 2020-11-10 | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Implementor: | Digos Constrak Corp | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: | 15.8% | Actual: | 100% | Actual: | 100%
Panabo City | Kiotoy | 2nd Eng'g. Dist. | Completed | 2020-08-27 | 2020-11-10 | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Duration: | 160 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | -3.7% | Slippage: | 0% | Slippage: | 0%
Panabo City | Kiotoy | 2nd Eng'g. Dist. | Completed | 2020-08-27 | 2020-11-10 | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Date Allotment Released: |  | Date completed: | 2020-11-10
Panabo City | Kiotoy | 2nd Eng'g. Dist. | Completed | 2020-08-27 | 2020-11-10 | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Stimulus Projects for Various Barangays | [7 empty] | Date Started: | 2020-08-27
B.E. Dujali | Magupising | 2nd Eng'g. Dist. | Completed | 2020-09-02 | 2020-11-20 | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | Construction of Multi-Purpose Covered Court, Magupising,B.E. Dujali |  | SB # 4 CY 2019 (STIMULUS | Construction |  |  |  | Project Cost: | 600000 | Target Completion Date: | 2020-11-20 23:59 | Program: | 600000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Procurement on process | Procurement on process | Abstract on Process as of August 17, 2020 | Abstract on Process as of August 17, 2020 | Abstract on Process as of August 17, 2020 | Completed as per Program of Works
B.E. Dujali | Magupising | 2nd Eng'g. Dist. | Completed | 2020-09-02 | 2020-11-20 | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 600000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
B.E. Dujali | Magupising | 2nd Eng'g. Dist. | Completed | 2020-09-02 | 2020-11-20 | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Implementor: | Digos Constrak Corp | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
B.E. Dujali | Magupising | 2nd Eng'g. Dist. | Completed | 2020-09-02 | 2020-11-20 | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Duration: | 80 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: |  | Slippage: |  | Slippage:
B.E. Dujali | Magupising | 2nd Eng'g. Dist. | Completed | 2020-09-02 | 2020-11-20 | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Date Allotment Released: |  | Date completed: | 2020-11-20
B.E. Dujali | Magupising | 2nd Eng'g. Dist. | Completed | 2020-09-02 | 2020-11-20 | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Date Started: | 2020-09-02
Panabo City | Malativas | 2nd Eng'g. Dist. | Completed | 2020-09-02 | 2020-10-05 | 2018 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | Impv't. of Brgy. Road Covered Court, Malativas, Panabo City (Note: Additional Fund Php 107,800.00) |  | SB NO. 4 CY 2019 (STIMULUS | Court |  |  |  | Project Cost: | 607800 | Target Completion Date: | 2020-10-06 | Program: | 607800 | Planned: |  | Planned: |  | Planned: | 38.15% | Planned: | 100% | Planned: | 100% | No. of Persons: | 6 | Procurement on process | Awarded to Digos Constrak Corp/ | On-going (Awarded to Digos Constrak Corp/) | Completed as per physical accomplishment. | Completed as per physical accomplishment. | Completed as per Program of Works
Panabo City | Malativas | 2nd Eng'g. Dist. | Completed | 2020-09-02 | 2020-10-05 | 2018 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Project Engineer: | Abayon | Revised Completion Date: |  | Allotment: | 607800 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 132
Panabo City | Malativas | 2nd Eng'g. Dist. | Completed | 2020-09-02 | 2020-10-05 | 2018 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Implementor: | Digos Constrak Corp/ | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: | 54.74% | Actual: | 100% | Actual: | 100%
Panabo City | Malativas | 2nd Eng'g. Dist. | Completed | 2020-09-02 | 2020-10-05 | 2018 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Duration: | 34 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 16.59% | Slippage: | 0% | Slippage: | 0%
Panabo City | Malativas | 2nd Eng'g. Dist. | Completed | 2020-09-02 | 2020-10-05 | 2018 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Date Allotment Released: |  | Date completed: | 2020-10-05
Panabo City | Malativas | 2nd Eng'g. Dist. | Completed | 2020-09-02 | 2020-10-05 | 2018 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | STIMULUS 2018 | [7 empty] | Date Started: | 2020-09-02
San Isidro | Sagayen-Sawata | 1st Eng'g. Dist. | Suspended | 2019-09-09 |  | 2019 |  | . | STIMULUS 2019 | Improvement of Km. 9 Sagayen-Sawata Provincial Road, San Isidro, Ph. II |  | SB NO. 4 CY 2019 | Road |  | ln.m | Admin | Project Cost: | 4591029 | Target Completion Date: | 2020-03-27 | Program: | 4591029 | Planned: | 45% | Planned: | 45% | Planned: | 45% | Planned: | 45% | Planned: | 45% | No. of Persons: | 6 | Suspended | Suspended | Suspended | Suspended | Suspended | Suspended
San Isidro | Sagayen-Sawata | 1st Eng'g. Dist. | Suspended | 2019-09-09 |  | 2019 |  | . | STIMULUS 2019 | [7 empty] | Project Engineer: | Limpo | Revised Completion Date: |  | Allotment: | 4591029 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 138
San Isidro | Sagayen-Sawata | 1st Eng'g. Dist. | Suspended | 2019-09-09 |  | 2019 |  | . | STIMULUS 2019 | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: | 1609155.6645 | Actual: | 35.05% | Actual: | 35.05% | Actual: | 35.05% | Actual: | 35.05% | Actual: | 35.05%
San Isidro | Sagayen-Sawata | 1st Eng'g. Dist. | Suspended | 2019-09-09 |  | 2019 |  | . | STIMULUS 2019 | [7 empty] | Duration: | 200 | No. of days extended: |  |  |  | Slippage: | -9.95% | Slippage: | -9.95% | Slippage: | -9.95% | Slippage: | -9.95% | Slippage: | -9.95%
San Isidro | Sagayen-Sawata | 1st Eng'g. Dist. | Suspended | 2019-09-09 |  | 2019 |  | . | STIMULUS 2019 | [7 empty] | Date Allotment Released: | 2019-12-12 | Date completed:
San Isidro | Sagayen-Sawata | 1st Eng'g. Dist. | Suspended | 2019-09-09 |  | 2019 |  | . | STIMULUS 2019 | [7 empty] | Date Started: | 2019-09-09
Panabo City | Dalisay | 2nd Eng'g. Dist. | For Implementation |  |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Local Roads and Drainage Development Project Construction in Progress- Infrastructure Assets | Rehabilitation of Local Roads at Dalisay-Manay Road Section, Panabo City |  | SB NO. 4 CY 2019 | Road |  |  | Admin | Project Cost: | 246100 | Target Completion Date: |  | Program: | 246100 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | For implementation | For implementation | For implementation | For implementation | For implementation | For implementation
Panabo City | Dalisay | 2nd Eng'g. Dist. | For Implementation |  |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Local Roads and Drainage Development Project Construction in Progress- Infrastructure Assets | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 246100 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
Panabo City | Dalisay | 2nd Eng'g. Dist. | For Implementation |  |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Local Roads and Drainage Development Project Construction in Progress- Infrastructure Assets | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
Panabo City | Dalisay | 2nd Eng'g. Dist. | For Implementation |  |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Local Roads and Drainage Development Project Construction in Progress- Infrastructure Assets | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Panabo City | Dalisay | 2nd Eng'g. Dist. | For Implementation |  |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Local Roads and Drainage Development Project Construction in Progress- Infrastructure Assets | [7 empty] | Date Allotment Released: |  | Date completed:
Panabo City | Dalisay | 2nd Eng'g. Dist. | For Implementation |  |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Local Roads and Drainage Development Project Construction in Progress- Infrastructure Assets | [7 empty] | Date Started:
Panabo City | Buenavista | 2nd Eng'g. Dist. | For Implementation |  |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Local Roads and Drainage Development Project Construction in Progress- Infrastructure Assets | Rehabilitation of Local Roads at Sta. Cruz-Jct. Tagpore-Buenavista Raod Section, Panabo City |  | SB NO. 4 CY 2019 | Road |  |  | Admin | Project Cost: | 431000 | Target Completion Date: |  | Program: | 431000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | For implementation | For implementation | For implementation | For implementation | For implementation | For implementation
Panabo City | Buenavista | 2nd Eng'g. Dist. | For Implementation |  |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Local Roads and Drainage Development Project Construction in Progress- Infrastructure Assets | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 431000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
Panabo City | Buenavista | 2nd Eng'g. Dist. | For Implementation |  |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Local Roads and Drainage Development Project Construction in Progress- Infrastructure Assets | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
Panabo City | Buenavista | 2nd Eng'g. Dist. | For Implementation |  |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Local Roads and Drainage Development Project Construction in Progress- Infrastructure Assets | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Panabo City | Buenavista | 2nd Eng'g. Dist. | For Implementation |  |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Local Roads and Drainage Development Project Construction in Progress- Infrastructure Assets | [7 empty] | Date Allotment Released: |  | Date completed:
Panabo City | Buenavista | 2nd Eng'g. Dist. | For Implementation |  |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Local Roads and Drainage Development Project Construction in Progress- Infrastructure Assets | [7 empty] | Date Started:
Talaingod | Tapayanon | 1st Eng'g. Dist. | On-going | 2019-11-18 |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Local Roads and Drainage Development Project Construction in Progress- Infrastructure Assets | Proposed Road Opening of Tawinian-Tapayanon Road Section |  | SB NO. 4 CY 2019 | Road |  | km | Admin | Project Cost: | 10000000 | Target Completion Date: | 2020-10-01 23:46 | Program: | 10000000 | Planned: | 34.2% | Planned: | 41.6% | Planned: | 41.6% | Planned: | 41.6% | Planned: | 100% | No. of Persons: | 8 | On-going (Suspended last April 5, 2020 due to COVID; resumption order dated May 4, 2020); Equipment Rental 1 unit Backhoe (Bidding July 16, 2020) | On-going (Suspended last April 5, 2020 due to COVID; resumption order dated May 4, 2020); Equipment Rental 1 unit Backhoe (Bidding July 16, 2020) | On-going (Suspended last April 5, 2020 due to COVID; resumption order dated May 4, 2020); Equipment Rental 1 unit Backhoe (Bidding July 16, 2020) |  |  | On-going
Talaingod | Tapayanon | 1st Eng'g. Dist. | On-going | 2019-11-18 |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Local Roads and Drainage Development Project Construction in Progress- Infrastructure Assets | [7 empty] | Project Engineer: | Garcia | Revised Completion Date: | 2020-10-29 23:46 | Allotment: | 10000000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: | 65.52% | No. of Man-days: | 138
Talaingod | Tapayanon | 1st Eng'g. Dist. | On-going | 2019-11-18 |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Local Roads and Drainage Development Project Construction in Progress- Infrastructure Assets | [7 empty] | Implementor: | PEO | No. of days suspended: | 28 | Disbursement: |  | Actual: | 34.2% | Actual: | 41.6% | Actual: | 41.6% | Actual: | 41.6% | Actual: | 70.86%
Talaingod | Tapayanon | 1st Eng'g. Dist. | On-going | 2019-11-18 |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Local Roads and Drainage Development Project Construction in Progress- Infrastructure Assets | [7 empty] | Duration: | 319 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 5.34%
Talaingod | Tapayanon | 1st Eng'g. Dist. | On-going | 2019-11-18 |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Local Roads and Drainage Development Project Construction in Progress- Infrastructure Assets | [7 empty] | Date Allotment Released: | 2019-11-15 | Date completed:
Talaingod | Tapayanon | 1st Eng'g. Dist. | On-going | 2019-11-18 |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Local Roads and Drainage Development Project Construction in Progress- Infrastructure Assets | [7 empty] | Date Started: | 2019-11-18
Carmen | Taba | 2nd Eng'g. Dist. | For Implementation |  |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Local Roads and Drainage Development Project Construction in Progress- Infrastructure Assets | Rehabilitation of Local Roads at Taba-Bucana Road Section, Taba, Carmen |  | SB # 4 CY 2019 | Road |  |  | Admin | Project Cost: | 220000 | Target Completion Date: |  | Program: | 220000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | For implementation | For implementation | For implementation | For implementation | For implementation | For implementation
Carmen | Taba | 2nd Eng'g. Dist. | For Implementation |  |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Local Roads and Drainage Development Project Construction in Progress- Infrastructure Assets | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 220000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
Carmen | Taba | 2nd Eng'g. Dist. | For Implementation |  |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Local Roads and Drainage Development Project Construction in Progress- Infrastructure Assets | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
Carmen | Taba | 2nd Eng'g. Dist. | For Implementation |  |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Local Roads and Drainage Development Project Construction in Progress- Infrastructure Assets | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Carmen | Taba | 2nd Eng'g. Dist. | For Implementation |  |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Local Roads and Drainage Development Project Construction in Progress- Infrastructure Assets | [7 empty] | Date Allotment Released: |  | Date completed:
Carmen | Taba | 2nd Eng'g. Dist. | For Implementation |  |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Various Local Roads and Drainage Development Project Construction in Progress- Infrastructure Assets | [7 empty] | Date Started:
Tagum City | San Agustin | 1st Eng'g. Dist. |  |  |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DISASTER REHABILITATION & RECOVERY PROGRAM - Building Back Better Project | Rehab. Of Canal Lining and Slope Protection at San Agustin E/S, San Agustin, Tagum City |  | SB NO. 4 FUND CY 2019 | Road |  | km | Admin | Project Cost: | 350000 | Target Completion Date: |  | Program: | 350000 | Planned: | 81.11% | Planned: | 81.11% | Planned: | 81.11% | Planned: | 81.11% | Planned: |  | No. of Persons: |  | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | For verification
Tagum City | San Agustin | 1st Eng'g. Dist. |  |  |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DISASTER REHABILITATION & RECOVERY PROGRAM - Building Back Better Project | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 350000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
Tagum City | San Agustin | 1st Eng'g. Dist. |  |  |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DISASTER REHABILITATION & RECOVERY PROGRAM - Building Back Better Project | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: | 81.11% | Actual: | 81.11% | Actual: | 81.11% | Actual: | 81.11% | Actual:
Tagum City | San Agustin | 1st Eng'g. Dist. |  |  |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DISASTER REHABILITATION & RECOVERY PROGRAM - Building Back Better Project | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Tagum City | San Agustin | 1st Eng'g. Dist. |  |  |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DISASTER REHABILITATION & RECOVERY PROGRAM - Building Back Better Project | [7 empty] | Date Allotment Released: |  | Date completed:
Tagum City | San Agustin | 1st Eng'g. Dist. |  |  |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DISASTER REHABILITATION & RECOVERY PROGRAM - Building Back Better Project | [7 empty] | Date Started:
|  | 1st Eng'g. Dist. | On-going | 2020-10-01 |  | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | SPECIAL EDUCATION FUND | Construction of 2 Classroom Building Datu Jose Libayao NHS Ext, Natulian, Palma Gil, Talaingod |  | SEF-AB CY 2019 | Building |  | km |  | Project Cost: | 2000000 | Target Completion Date: |  | Program: | 2000000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: | 20% | No. of Persons: |  | PO#2020061983 - FL2 LUMBER & CONST. SUPPLY; PO #2020062164 - jkle enterprises | PO#2020061983 - FL2 LUMBER & CONST. SUPPLY; PO #2020062164 - jkle enterprises | PO#2020061983 - FL2 LUMBER & CONST. SUPPLY; PO #2020062164 - jkle enterprises |  |  | On-going
|  | 1st Eng'g. Dist. | On-going | 2020-10-01 |  | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | SPECIAL EDUCATION FUND | [7 empty] | Project Engineer: | Ambrosio | Revised Completion Date: |  | Allotment: | 2000000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
|  | 1st Eng'g. Dist. | On-going | 2020-10-01 |  | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | SPECIAL EDUCATION FUND | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual: | 20%
|  | 1st Eng'g. Dist. | On-going | 2020-10-01 |  | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | SPECIAL EDUCATION FUND | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
|  | 1st Eng'g. Dist. | On-going | 2020-10-01 |  | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | SPECIAL EDUCATION FUND | [7 empty] | Date Allotment Released: |  | Date completed:
|  | 1st Eng'g. Dist. | On-going | 2020-10-01 |  | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | SPECIAL EDUCATION FUND | [7 empty] | Date Started: | 2020-10-01
Kapalong | Gupitan | 1st Eng'g. Dist. | On-going | 2020-10-01 |  | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | Const. of 1 Classroom @ Tawinian E/S, Gupitan, kapalong |  | SEF-SB No. 2 CY 2019 | Building |  | sq.m |  | Project Cost: | 500000 | Target Completion Date: | 2020-12-14 23:59 | Program: | 500000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: | 80% | No. of Persons: |  | Opening of Shopping on June 25, 2020 | Opening of Shopping on June 25, 2020 | Opening of Shopping on June 25, 2020 | Opening of Shopping on June 25, 2020 | Opening of Shopping on June 25, 2020 | On-going
Kapalong | Gupitan | 1st Eng'g. Dist. | On-going | 2020-10-01 |  | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Project Engineer: | Mabanglo | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
Kapalong | Gupitan | 1st Eng'g. Dist. | On-going | 2020-10-01 |  | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Implementor: | Alpebel Builders and Supply Corporation | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual: | 80%
Kapalong | Gupitan | 1st Eng'g. Dist. | On-going | 2020-10-01 |  | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Duration: | 75 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Kapalong | Gupitan | 1st Eng'g. Dist. | On-going | 2020-10-01 |  | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Kapalong | Gupitan | 1st Eng'g. Dist. | On-going | 2020-10-01 |  | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Date Started: | 2020-10-01
Kapalong | Gupitan | 1st Eng'g. Dist. | On-going | 2020-10-01 |  | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | Const. of 1 Classroom @ Moling E/S, Gupitan, kapalong |  | SEF-SB No. 2 CY 2019 | Building |  | sq.m |  | Project Cost: | 500000 | Target Completion Date: | 2020-12-14 23:59 | Program: | 500000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: | 90% | No. of Persons: |  | Opening of Shopping on June 25, 2020 | Opening of Shopping on June 25, 2020 | Opening of Shopping on June 25, 2020 | Opening of Shopping on June 25, 2020 | Opening of Shopping on June 25, 2020 | On-going
Kapalong | Gupitan | 1st Eng'g. Dist. | On-going | 2020-10-01 |  | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Project Engineer: | Mabanglo | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
Kapalong | Gupitan | 1st Eng'g. Dist. | On-going | 2020-10-01 |  | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Implementor: | Alpebel Builders and Supply Corporation | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual: | 90%
Kapalong | Gupitan | 1st Eng'g. Dist. | On-going | 2020-10-01 |  | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Duration: | 75 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Kapalong | Gupitan | 1st Eng'g. Dist. | On-going | 2020-10-01 |  | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Kapalong | Gupitan | 1st Eng'g. Dist. | On-going | 2020-10-01 |  | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Date Started: | 2020-10-01
Kapalong | Gupitan | 1st Eng'g. Dist. | On-going | 2020-10-01 |  | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | Const. of 1 Classroom @ Kawayan ES, Gupitan, Kapalong |  | SEF-SB No. 2 CY 2019 | Building |  | sq.m |  | Project Cost: | 500000 | Target Completion Date: | 2020-12-14 23:59 | Program: | 500000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: | 50% | No. of Persons: |  | Opening of Shopping on June 25, 2020 | Opening of Shopping on June 25, 2020 | Opening of Shopping on June 25, 2020 | Opening of Shopping on June 25, 2020 | Opening of Shopping on June 25, 2020 | On-going
Kapalong | Gupitan | 1st Eng'g. Dist. | On-going | 2020-10-01 |  | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Project Engineer: | Mabanglo | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
Kapalong | Gupitan | 1st Eng'g. Dist. | On-going | 2020-10-01 |  | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Implementor: | Alpebel Builders and Supply Corporation | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual: | 50%
Kapalong | Gupitan | 1st Eng'g. Dist. | On-going | 2020-10-01 |  | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Duration: | 75 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Kapalong | Gupitan | 1st Eng'g. Dist. | On-going | 2020-10-01 |  | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Kapalong | Gupitan | 1st Eng'g. Dist. | On-going | 2020-10-01 |  | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Date Started: | 2020-10-01
Kapalong | Gupitan | 1st Eng'g. Dist. | On-going | 2020-10-01 |  | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | Const. of 1 Classroom @ Matol ES, Gupitan, Kapalong |  | SEF-SB No. 2 CY 2019 | Building |  | sq.m |  | Project Cost: | 500000 | Target Completion Date: | 2020-12-14 23:59 | Program: | 500000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: | 90% | No. of Persons: |  | Opening of Shopping on June 25, 2020 | Opening of Shopping on June 25, 2020 | Opening of Shopping on June 25, 2020 | Opening of Shopping on June 25, 2020 | Opening of Shopping on June 25, 2020 | On-going
Kapalong | Gupitan | 1st Eng'g. Dist. | On-going | 2020-10-01 |  | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Project Engineer: | Mabanglo | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
Kapalong | Gupitan | 1st Eng'g. Dist. | On-going | 2020-10-01 |  | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Implementor: | Alpebel Builders and Supply Corporation | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual: | 90%
Kapalong | Gupitan | 1st Eng'g. Dist. | On-going | 2020-10-01 |  | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Duration: | 75 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Kapalong | Gupitan | 1st Eng'g. Dist. | On-going | 2020-10-01 |  | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Kapalong | Gupitan | 1st Eng'g. Dist. | On-going | 2020-10-01 |  | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Date Started: | 2020-10-01
Kapalong | Capungagan | 1st Eng'g. Dist. | On-going | 2020-10-01 |  | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | Const. of 1 Classroom @ Hermogina Salibay ES, Capungagan, Kapalong |  | SEF-SB No. 2 CY 2019 | Building |  | sq.m |  | Project Cost: | 500000 | Target Completion Date: | 2020-12-14 23:59 | Program: | 500000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: | 50% | No. of Persons: |  | Opening of Shopping on June 25, 2020 | Opening of Shopping on June 25, 2020 | Opening of Shopping on June 25, 2020 | Opening of Shopping on June 25, 2020 | Opening of Shopping on June 25, 2020 | On-going
Kapalong | Capungagan | 1st Eng'g. Dist. | On-going | 2020-10-01 |  | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Project Engineer: | Mabanglo | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
Kapalong | Capungagan | 1st Eng'g. Dist. | On-going | 2020-10-01 |  | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Implementor: | Alpebel Builders and Supply Corporation | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual: | 50%
Kapalong | Capungagan | 1st Eng'g. Dist. | On-going | 2020-10-01 |  | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Duration: | 75 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Kapalong | Capungagan | 1st Eng'g. Dist. | On-going | 2020-10-01 |  | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Kapalong | Capungagan | 1st Eng'g. Dist. | On-going | 2020-10-01 |  | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Date Started: | 2020-10-01
Talaingod | Sto. Niño | 1st Eng'g. Dist. | Completed | 2020-10-01 | 2020-10-16 | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | Const. of 1 Classroom @ Lambid ES, Sto. Niño, Talaingod |  | SEF-SB No. 2 CY 2019 | Building |  | sq.m |  | Project Cost: | 500000 | Target Completion Date: | 2020-10-31 | Program: | 500000 | Planned: |  | Planned: |  | Planned: |  | Planned: | 100% | Planned: | 100% | No. of Persons: | 15 | Opening of Shopping on June 25, 2020 | Opening of Shopping on June 25, 2020 | Opening of Shopping on June 25, 2020 | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per Program of Works
Talaingod | Sto. Niño | 1st Eng'g. Dist. | Completed | 2020-10-01 | 2020-10-16 | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Project Engineer: | Mabanglo | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 169
Talaingod | Sto. Niño | 1st Eng'g. Dist. | Completed | 2020-10-01 | 2020-10-16 | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Implementor: | Alpebel Builders and Supply Corporation | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: | 100% | Actual: | 100%
Talaingod | Sto. Niño | 1st Eng'g. Dist. | Completed | 2020-10-01 | 2020-10-16 | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Duration: | 30 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Talaingod | Sto. Niño | 1st Eng'g. Dist. | Completed | 2020-10-01 | 2020-10-16 | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Date Allotment Released: |  | Date completed: | 2020-10-16
Talaingod | Sto. Niño | 1st Eng'g. Dist. | Completed | 2020-10-01 | 2020-10-16 | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Date Started: | 2020-10-01
Talaingod | Sto. Niño | 1st Eng'g. Dist. | On-going | 2020-10-01 |  | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | Const. of 1 Classroom @ Dulyan ES, Palma Gil, Talaingod |  | SEF-SB No. 2 CY 2019 | Building |  | sq.m |  | Project Cost: | 500000 | Target Completion Date: | 2020-12-14 23:59 | Program: | 500000 | Planned: |  | Planned: |  | Planned: |  | Planned: | 100% | Planned: | 75% | No. of Persons: |  | Opening of Shopping on June 25, 2020 | Opening of Shopping on June 25, 2020 | Opening of Shopping on June 25, 2020 | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | On-going
Talaingod | Sto. Niño | 1st Eng'g. Dist. | On-going | 2020-10-01 |  | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Project Engineer: | Mabanglo | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
Talaingod | Sto. Niño | 1st Eng'g. Dist. | On-going | 2020-10-01 |  | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Implementor: | Alpebel Builders and Supply Corporation | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: | 100% | Actual: | 75%
Talaingod | Sto. Niño | 1st Eng'g. Dist. | On-going | 2020-10-01 |  | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Duration: | 75 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Talaingod | Sto. Niño | 1st Eng'g. Dist. | On-going | 2020-10-01 |  | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Talaingod | Sto. Niño | 1st Eng'g. Dist. | On-going | 2020-10-01 |  | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Date Started: | 2020-10-01
Talaingod | Palma Gil | 1st Eng'g. Dist. | Completed | 2020-10-01 | 2020-12-11 | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | Const. of 1 Classroom @ Sambulongan ES, Palma Gil, Talaingod |  | SEF-SB No. 2 CY 2019 | Building |  | sq.m |  | Project Cost: | 500000 | Target Completion Date: | 2020-12-14 23:59 | Program: | 500000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: | 100% | No. of Persons: | 14 | Opening of Shopping on June 25, 2020 | Opening of Shopping on June 25, 2020 | Opening of Shopping on June 25, 2020 | Opening of Shopping on June 25, 2020 | Opening of Shopping on June 25, 2020 | Completed as per Program of Works
Talaingod | Palma Gil | 1st Eng'g. Dist. | Completed | 2020-10-01 | 2020-12-11 | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Project Engineer: | Mabanglo | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 169
Talaingod | Palma Gil | 1st Eng'g. Dist. | Completed | 2020-10-01 | 2020-12-11 | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Implementor: | Alpebel Builders and Supply Corporation | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual: | 100%
Talaingod | Palma Gil | 1st Eng'g. Dist. | Completed | 2020-10-01 | 2020-12-11 | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Duration: | 75 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Talaingod | Palma Gil | 1st Eng'g. Dist. | Completed | 2020-10-01 | 2020-12-11 | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Date Allotment Released: |  | Date completed: | 2020-12-11
Talaingod | Palma Gil | 1st Eng'g. Dist. | Completed | 2020-10-01 | 2020-12-11 | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Date Started: | 2020-10-01
Talaingod | Dagohoy | 1st Eng'g. Dist. | On-going | 2020-10-01 |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | Const. of 1 Classroom @ Pongpong ES, Dagohoy, Talaingod |  | SEF-SB No. 2 CY 2019 | Building |  | sq.m |  | Project Cost: | 500000 | Target Completion Date: | 2020-12-14 23:59 | Program: | 500000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: | 100% | No. of Persons: | 14 | Opening of Shopping on June 25, 2020 | Opening of Shopping on June 25, 2020 | Opening of Shopping on June 25, 2020 | Opening of Shopping on June 25, 2020 | Opening of Shopping on June 25, 2020 | Completed as per Program of Works
Talaingod | Dagohoy | 1st Eng'g. Dist. | On-going | 2020-10-01 |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Project Engineer: | Mabanglo | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 169
Talaingod | Dagohoy | 1st Eng'g. Dist. | On-going | 2020-10-01 |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Implementor: | Alpebel Builders and Supply Corporation | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual: | 100%
Talaingod | Dagohoy | 1st Eng'g. Dist. | On-going | 2020-10-01 |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Duration: | 75 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Talaingod | Dagohoy | 1st Eng'g. Dist. | On-going | 2020-10-01 |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Talaingod | Dagohoy | 1st Eng'g. Dist. | On-going | 2020-10-01 |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Date Started: | 2020-10-01
Talaingod | Palma Gil | 1st Eng'g. Dist. | On-going | 2020-10-01 |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | Const. of 1 Classroom @ Dalingding ES, Palma Gil, Talaingod |  | SEF-SB No. 2 CY 2019 | Building |  | sq.m |  | Project Cost: | 500000 | Target Completion Date: | 2020-12-14 23:59 | Program: | 500000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: | 100% | No. of Persons: | 15 | Opening of Shopping on June 25, 2020 | Opening of Shopping on June 25, 2020 | Opening of Shopping on June 25, 2020 | Opening of Shopping on June 25, 2020 | Opening of Shopping on June 25, 2020 | Completed as per Program of Works
Talaingod | Palma Gil | 1st Eng'g. Dist. | On-going | 2020-10-01 |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Project Engineer: | Mabanglo | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
Talaingod | Palma Gil | 1st Eng'g. Dist. | On-going | 2020-10-01 |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Implementor: | Alpebel Builders and Supply Corporation | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual: | 100%
Talaingod | Palma Gil | 1st Eng'g. Dist. | On-going | 2020-10-01 |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Duration: | 75 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Talaingod | Palma Gil | 1st Eng'g. Dist. | On-going | 2020-10-01 |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Date Allotment Released: |  | Date completed: | 2020-11-30
Talaingod | Palma Gil | 1st Eng'g. Dist. | On-going | 2020-10-01 |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Date Started: | 2020-10-01
New Corella | Limbaan | 1st Eng'g. Dist. | Suspended | 2019-03-20 |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DISASTER PREVENTION AND MITIGATION - Flood Control and Slope Protection LS - P3,000,000.00 | Desilting of Limbaan Creek, New Corella |  | 5% CALAMITY FUND CY 2019 | creeks and canals deislted |  | ln.m | Admin | Project Cost: | 2000000 | Target Completion Date: | 2019-12-02 | Program: | 2000000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Suspended | Suspended | Suspended | Suspended | Suspended | Suspended
New Corella | Limbaan | 1st Eng'g. Dist. | Suspended | 2019-03-20 |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DISASTER PREVENTION AND MITIGATION - Flood Control and Slope Protection LS - P3,000,000.00 | [7 empty] | Project Engineer: | Pilotos | Revised Completion Date: | 2019-12-02 | Allotment: | 2000000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
New Corella | Limbaan | 1st Eng'g. Dist. | Suspended | 2019-03-20 |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DISASTER PREVENTION AND MITIGATION - Flood Control and Slope Protection LS - P3,000,000.00 | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
New Corella | Limbaan | 1st Eng'g. Dist. | Suspended | 2019-03-20 |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DISASTER PREVENTION AND MITIGATION - Flood Control and Slope Protection LS - P3,000,000.00 | [7 empty] | Duration: | 257 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
New Corella | Limbaan | 1st Eng'g. Dist. | Suspended | 2019-03-20 |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DISASTER PREVENTION AND MITIGATION - Flood Control and Slope Protection LS - P3,000,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
New Corella | Limbaan | 1st Eng'g. Dist. | Suspended | 2019-03-20 |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DISASTER PREVENTION AND MITIGATION - Flood Control and Slope Protection LS - P3,000,000.00 | [7 empty] | Date Started: | 2019-03-20
Asuncion | New Boholano-New Loon | 1st Eng'g. Dist. | Suspended | 2019-11-18 |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Improvement of bridges and cross drainage LS - P3,000,000.00 | Impv't. of Jct. New Boholano - New Loon Cross Drainage |  | 5% CALAMITY FUND CY 2019 | Drainage |  | km | Admin | Project Cost: | 2000000 | Target Completion Date: | 2020-02-16 | Program: | 2000000 | Planned: | 42.27% | Planned: | 42.27% | Planned: | 42.27% | Planned: | 42.27% | Planned: | 70% | No. of Persons: |  | Suspended due to availability of equipment | Suspended due to availability of equipment | Suspended due to availability of equipment | Suspended due to availability of equipment | Suspended due to availability of equipment | On-going
Asuncion | New Boholano-New Loon | 1st Eng'g. Dist. | Suspended | 2019-11-18 |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Improvement of bridges and cross drainage LS - P3,000,000.00 | [7 empty] | Project Engineer: | Pilotos | Revised Completion Date: | 2020-02-16 | Allotment: | 2000000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
Asuncion | New Boholano-New Loon | 1st Eng'g. Dist. | Suspended | 2019-11-18 |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Improvement of bridges and cross drainage LS - P3,000,000.00 | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: | 31.7% | Actual: | 31.7% | Actual: | 31.7% | Actual: | 31.7% | Actual: | 70%
Asuncion | New Boholano-New Loon | 1st Eng'g. Dist. | Suspended | 2019-11-18 |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Improvement of bridges and cross drainage LS - P3,000,000.00 | [7 empty] | Duration: | 90 | No. of days extended: |  |  |  | Slippage: | -10.57% | Slippage: | -10.57% | Slippage: | -10.57% | Slippage: | -10.57% | Slippage: | 0%
Asuncion | New Boholano-New Loon | 1st Eng'g. Dist. | Suspended | 2019-11-18 |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Improvement of bridges and cross drainage LS - P3,000,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Asuncion | New Boholano-New Loon | 1st Eng'g. Dist. | Suspended | 2019-11-18 |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Improvement of bridges and cross drainage LS - P3,000,000.00 | [7 empty] | Date Started: | 2019-11-18
Asuncion | Saug Sonlon-Longanapan | 1st Eng'g. Dist. | Completed | 2019-11-18 | 2020-01-07 | 2019 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Improvement of bridges and cross drainage LS - P3,000,000.00 | Impv't. of Jct. Saug-Sonlon-Bdry. Longanapan |  | 5% CALAMITY FUND CY 2019 | Road |  |  |  | Project Cost: | 1000000 | Target Completion Date: | 2020-01-07 | Program: | 1000000 | Planned: |  | Planned: |  | Planned: |  | Planned: | 100% | Planned: | 100% | No. of Persons: |  | For implementation | For implementation | For implementation | Completed as per physical accomplishment. | For implementation | Completed as per Program of Works
Asuncion | Saug Sonlon-Longanapan | 1st Eng'g. Dist. | Completed | 2019-11-18 | 2020-01-07 | 2019 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Improvement of bridges and cross drainage LS - P3,000,000.00 | [7 empty] | Project Engineer: | Bataller | Revised Completion Date: |  | Allotment: | 1000000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
Asuncion | Saug Sonlon-Longanapan | 1st Eng'g. Dist. | Completed | 2019-11-18 | 2020-01-07 | 2019 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Improvement of bridges and cross drainage LS - P3,000,000.00 | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: | 100% | Actual: | 100%
Asuncion | Saug Sonlon-Longanapan | 1st Eng'g. Dist. | Completed | 2019-11-18 | 2020-01-07 | 2019 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Improvement of bridges and cross drainage LS - P3,000,000.00 | [7 empty] | Duration: | 50 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Asuncion | Saug Sonlon-Longanapan | 1st Eng'g. Dist. | Completed | 2019-11-18 | 2020-01-07 | 2019 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Improvement of bridges and cross drainage LS - P3,000,000.00 | [7 empty] | Date Allotment Released: |  | Date completed: | 2020-01-07
Asuncion | Saug Sonlon-Longanapan | 1st Eng'g. Dist. | Completed | 2019-11-18 | 2020-01-07 | 2019 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | Improvement of bridges and cross drainage LS - P3,000,000.00 | [7 empty] | Date Started: | 2019-11-18
Carmen | Tuganay | 2nd Eng'g. Dist. | Completed | 2020-07-26 | 2020-07-31 | 2019 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REVITMENT OF DIKE | Repair/Rehab. Of Lower Tuganay Dike |  | 5% CALAMITY FUND CY 2019 | Dike |  |  |  | Project Cost: | 1000000 | Target Completion Date: | 2019-09-23 | Program: | 1000000 | Planned: |  | Planned: |  | Planned: | 100% | Planned: |  | Planned: | 100% | No. of Persons: | 9 | For AIP Amendment | For AIP Amendment | Completed as per physical accomplishment. Financial documents still on process. |  |  | Completed as per Program of Works
Carmen | Tuganay | 2nd Eng'g. Dist. | Completed | 2020-07-26 | 2020-07-31 | 2019 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REVITMENT OF DIKE | [7 empty] | Project Engineer: | Toquero | Revised Completion Date: |  | Allotment: | 1000000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: | 100% | No. of Man-days: | 80
Carmen | Tuganay | 2nd Eng'g. Dist. | Completed | 2020-07-26 | 2020-07-31 | 2019 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REVITMENT OF DIKE | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: | 100% | Actual: |  | Actual: | 100%
Carmen | Tuganay | 2nd Eng'g. Dist. | Completed | 2020-07-26 | 2020-07-31 | 2019 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REVITMENT OF DIKE | [7 empty] | Duration: | 59 | No. of days extended: | 312 |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Carmen | Tuganay | 2nd Eng'g. Dist. | Completed | 2020-07-26 | 2020-07-31 | 2019 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REVITMENT OF DIKE | [7 empty] | Date Allotment Released: | 2019-08-15 | Date completed: | July 31, 2020
Carmen | Tuganay | 2nd Eng'g. Dist. | Completed | 2020-07-26 | 2020-07-31 | 2019 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REVITMENT OF DIKE | [7 empty] | Date Started: | July 26, 2019
Carmen | Tuganay | 2nd Eng'g. Dist. | Completed | 2019-07-26 | 2020-07-31 | 2019 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REVITMENT OF DIKE | Repair/Rehab. Of Upper Tuganay Dike |  | 5% CALAMITY FUND CY 2019 | Dike |  |  |  | Project Cost: | 1000000 | Target Completion Date: | 2019-09-23 | Program: | 1000000 | Planned: |  | Planned: |  | Planned: | 100% | Planned: |  | Planned: | 100% | No. of Persons: | 9 | For AIP Amendment | For AIP Amendment | Completed as per physical accomplishment. Financial documents still on process. |  |  | Completed as per Program of Works
Carmen | Tuganay | 2nd Eng'g. Dist. | Completed | 2019-07-26 | 2020-07-31 | 2019 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REVITMENT OF DIKE | [7 empty] | Project Engineer: | Toquero | Revised Completion Date: |  | Allotment: | 1000000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: | 100% | No. of Man-days: | 80
Carmen | Tuganay | 2nd Eng'g. Dist. | Completed | 2019-07-26 | 2020-07-31 | 2019 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REVITMENT OF DIKE | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: | 100% | Actual: |  | Actual: | 100%
Carmen | Tuganay | 2nd Eng'g. Dist. | Completed | 2019-07-26 | 2020-07-31 | 2019 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REVITMENT OF DIKE | [7 empty] | Duration: | 59 | No. of days extended: | 312 |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Carmen | Tuganay | 2nd Eng'g. Dist. | Completed | 2019-07-26 | 2020-07-31 | 2019 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REVITMENT OF DIKE | [7 empty] | Date Allotment Released: | 2019-08-15 | Date completed: | July 31, 2020
Carmen | Tuganay | 2nd Eng'g. Dist. | Completed | 2019-07-26 | 2020-07-31 | 2019 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REVITMENT OF DIKE | [7 empty] | Date Started: | July 26, 2019
Panabo City | Lasang | 2nd Eng'g. Dist. | Completed | 2019-08-01 | 2020-05-28 | 2019 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPLAN CANAL | Repair of Damaged Drainage/ Creeks along San Miguel NIA Road |  | 5% CALAMITY FUND | Creek |  | ln.m | Admin | Project Cost: | 470000 | Target Completion Date: | 2019-09-16 | Program: | 470000 | Planned: | 100% | Planned: | 100% | Planned: | 100% | Planned: | 100% | Planned: | 100% | No. of Persons: | 3 | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per Program of Works
Panabo City | Lasang | 2nd Eng'g. Dist. | Completed | 2019-08-01 | 2020-05-28 | 2019 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPLAN CANAL | [7 empty] | Project Engineer: | Nasol | Revised Completion Date: | 2020-05-28 | Allotment: | 470000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 66
Panabo City | Lasang | 2nd Eng'g. Dist. | Completed | 2019-08-01 | 2020-05-28 | 2019 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPLAN CANAL | [7 empty] | Implementor: | PEO | No. of days suspended: | 255 | Disbursement: |  | Actual: | 100% | Actual: | 100% | Actual: | 100% | Actual: | 100% | Actual: | 100%
Panabo City | Lasang | 2nd Eng'g. Dist. | Completed | 2019-08-01 | 2020-05-28 | 2019 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPLAN CANAL | [7 empty] | Duration: | 46 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Panabo City | Lasang | 2nd Eng'g. Dist. | Completed | 2019-08-01 | 2020-05-28 | 2019 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPLAN CANAL | [7 empty] | Date Allotment Released: |  | Date completed: | 2020-05-28
Panabo City | Lasang | 2nd Eng'g. Dist. | Completed | 2019-08-01 | 2020-05-28 | 2019 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPLAN CANAL | [7 empty] | Date Started: | 2019-08-01
Panabo City | Lasang | 2nd Eng'g. Dist. | Completed | 2019-07-26 | 2020-09-15 | 2019 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPLAN CANAL | Repair/Rehab. Of Upper Tunagay Dike Along Casig-ang Section, Sto. Tomas |  | 5% CALAMITY FUND | Creek |  | ln.m | Admin | Project Cost: | 1000000 | Target Completion Date: | 2019-09-10 | Program: | 1000000 | Planned: | 100% | Planned: | 100% | Planned: | 100% | Planned: | 100% | Planned: | 100% | No. of Persons: | 3 | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per Program of Works
Panabo City | Lasang | 2nd Eng'g. Dist. | Completed | 2019-07-26 | 2020-09-15 | 2019 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPLAN CANAL | [7 empty] | Project Engineer: | Nasol | Revised Completion Date: | 2020-05-22 | Allotment: | 1000000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 66
Panabo City | Lasang | 2nd Eng'g. Dist. | Completed | 2019-07-26 | 2020-09-15 | 2019 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPLAN CANAL | [7 empty] | Implementor: | PEO | No. of days suspended: | 255 | Disbursement: |  | Actual: | 100% | Actual: | 100% | Actual: | 100% | Actual: | 100% | Actual: | 100%
Panabo City | Lasang | 2nd Eng'g. Dist. | Completed | 2019-07-26 | 2020-09-15 | 2019 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPLAN CANAL | [7 empty] | Duration: | 46 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Panabo City | Lasang | 2nd Eng'g. Dist. | Completed | 2019-07-26 | 2020-09-15 | 2019 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPLAN CANAL | [7 empty] | Date Allotment Released: |  | Date completed: | 2020-09-15
Panabo City | Lasang | 2nd Eng'g. Dist. | Completed | 2019-07-26 | 2020-09-15 | 2019 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPLAN CANAL | [7 empty] | Date Started: | 2019-07-26
Carmen | Ising | 2nd Eng'g. Dist. | Completed | 2020-11-15 | 2020-12-31 | 2019 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPLAN CANAL | Repair of Damaged Drainage/Creek along Tuganay-Ising River |  | 5% CALAMITY FUND | Creek |  |  | Admin | Project Cost: | 1540500 | Target Completion Date: | 2020-05-15 | Program: | 1540500 | Planned: | 25.6% | No. of Persons: | 3 | Completed 12/31/2020 |  |  |  | Planned: | 100% | No. of Persons: | 3 | Completed 12/31/2020 |  |  |  |  | Completed as per Program of Works
Carmen | Ising | 2nd Eng'g. Dist. | Completed | 2020-11-15 | 2020-12-31 | 2019 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPLAN CANAL | [7 empty] | Project Engineer: | Ganaba | Revised Completion Date: | 12/31/2020 | Allotment: | 1540500 | Revised: |  | No. of Man-days: | 66 |  |  |  |  | Revised: |  | No. of Man-days: | 66
Carmen | Ising | 2nd Eng'g. Dist. | Completed | 2020-11-15 | 2020-12-31 | 2019 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPLAN CANAL | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: | 23.6% | [6 empty] | Actual: | 100%
Carmen | Ising | 2nd Eng'g. Dist. | Completed | 2020-11-15 | 2020-12-31 | 2019 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPLAN CANAL | [7 empty] | Duration: | 182 | No. of days extended: |  |  |  | Slippage: | -2% | [6 empty] | Slippage: | 0%
Carmen | Ising | 2nd Eng'g. Dist. | Completed | 2020-11-15 | 2020-12-31 | 2019 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPLAN CANAL | [7 empty] | Date Allotment Released: |  | Date completed: | 2020-12-31
Carmen | Ising | 2nd Eng'g. Dist. | Completed | 2020-11-15 | 2020-12-31 | 2019 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | OPLAN CANAL | [7 empty] | Date Started: | 2019-11-15
kapalong | Pamacaun-Lasang-banate | 1st Eng'g. Dist. | On-going | 2020-08-03 |  | 2019 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DISASTER REHABILITATION & RECOVERY PROGRAM - Building Back Better Project | Rehabilitation of Pamacaun-Lasang-Banate Provincial Road |  | SB NO. 3 CY 2019 (5% CALAMITY FUND) | Road |  |  | Admin | Project Cost: | 1500000 | Target Completion Date: | 2020-11-10 23:46 | Program: | 1500000 | Planned: |  | Planned: |  | Planned: | 41.21% | Planned: | 41.21% | Planned: | 41.21% | No. of Persons: |  | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | On-going (Suspended Oct.5, 2020)
kapalong | Pamacaun-Lasang-banate | 1st Eng'g. Dist. | On-going | 2020-08-03 |  | 2019 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DISASTER REHABILITATION & RECOVERY PROGRAM - Building Back Better Project | [7 empty] | Project Engineer: | Gone | Revised Completion Date: |  | Allotment: | 1500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
kapalong | Pamacaun-Lasang-banate | 1st Eng'g. Dist. | On-going | 2020-08-03 |  | 2019 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DISASTER REHABILITATION & RECOVERY PROGRAM - Building Back Better Project | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: | 17.82% | Actual: | 52.32% | Actual: | 52.32% | Actual: | 52.32%
kapalong | Pamacaun-Lasang-banate | 1st Eng'g. Dist. | On-going | 2020-08-03 |  | 2019 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DISASTER REHABILITATION & RECOVERY PROGRAM - Building Back Better Project | [7 empty] | Duration: | 100 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 17.82% | Slippage: | 11.11% | Slippage: | 11.11% | Slippage: | 11.11%
kapalong | Pamacaun-Lasang-banate | 1st Eng'g. Dist. | On-going | 2020-08-03 |  | 2019 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DISASTER REHABILITATION & RECOVERY PROGRAM - Building Back Better Project | [7 empty] | Date Allotment Released: |  | Date completed:
kapalong | Pamacaun-Lasang-banate | 1st Eng'g. Dist. | On-going | 2020-08-03 |  | 2019 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DISASTER REHABILITATION & RECOVERY PROGRAM - Building Back Better Project | [7 empty] | Date Started: | 2020-08-03
New Corella | Del Pilar | 1st Eng'g. Dist. | On-going | 2020-02-17 |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DISASTER REHABILITATION & RECOVERY PROGRAM - Building Back Better Project | Rehabilitation of Del Pilar Jct. Silangan |  | SB NO. 3 CY 2019 (5% CALAMITY FUND) | Road |  | km | Admin | Project Cost: | 1500000 | Target Completion Date: | 2020-03-27 23:46 | Program: | 1500000 | Planned: | 81.11% | Planned: | 81.11% | Planned: | 81.11% | Planned: | 81.11% | Planned: | 100% | No. of Persons: | 4 | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | On-going (Resumption date Dec. 7, 2020)
New Corella | Del Pilar | 1st Eng'g. Dist. | On-going | 2020-02-17 |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DISASTER REHABILITATION & RECOVERY PROGRAM - Building Back Better Project | [7 empty] | Project Engineer: | Gone | Revised Completion Date: | 2021-01-15 23:46 | Allotment: | 1500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: | 92.61% | No. of Man-days: | 40
New Corella | Del Pilar | 1st Eng'g. Dist. | On-going | 2020-02-17 |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DISASTER REHABILITATION & RECOVERY PROGRAM - Building Back Better Project | [7 empty] | Implementor: | PEO | No. of days suspended: | 243 | Disbursement: |  | Actual: | 81.11% | Actual: | 81.11% | Actual: | 81.11% | Actual: | 81.11% | Actual: | 90.42%
New Corella | Del Pilar | 1st Eng'g. Dist. | On-going | 2020-02-17 |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DISASTER REHABILITATION & RECOVERY PROGRAM - Building Back Better Project | [7 empty] | Duration: | 40 | No. of days extended: | 51 |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | -2.19%
New Corella | Del Pilar | 1st Eng'g. Dist. | On-going | 2020-02-17 |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DISASTER REHABILITATION & RECOVERY PROGRAM - Building Back Better Project | [7 empty] | Date Allotment Released: | 2019-07-26 | Date completed:
New Corella | Del Pilar | 1st Eng'g. Dist. | On-going | 2020-02-17 |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DISASTER REHABILITATION & RECOVERY PROGRAM - Building Back Better Project | [7 empty] | Date Started: | 2020-02-17
New Corella | Del Pilar | 1st Eng'g. Dist. | Completed | 2020-11-18 | 2020-02-29 | 2019 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DISASTER REHABILITATION & RECOVERY PROGRAM - Building Back Better Project | Rehab. Of Mesaoy-Jct. Mahayahay Road |  | SB NO. 3 CY 2019 (5% CALAMITY FUND) | Road |  | km | Admin | Project Cost: | 1000000 | Target Completion Date: | 2019-12-27 23:46 | Program: | 1000000 | Planned: | 81.11% | Planned: | 81.11% | Planned: | 81.11% | Planned: | 81.11% | Planned: | 100% | No. of Persons: | 4 | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per Program of Works
New Corella | Del Pilar | 1st Eng'g. Dist. | Completed | 2020-11-18 | 2020-02-29 | 2019 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DISASTER REHABILITATION & RECOVERY PROGRAM - Building Back Better Project | [7 empty] | Project Engineer: | Gone | Revised Completion Date: |  | Allotment: | 1000000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 40
New Corella | Del Pilar | 1st Eng'g. Dist. | Completed | 2020-11-18 | 2020-02-29 | 2019 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DISASTER REHABILITATION & RECOVERY PROGRAM - Building Back Better Project | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: | 81.11% | Actual: | 81.11% | Actual: | 81.11% | Actual: | 81.11% | Actual: | 100%
New Corella | Del Pilar | 1st Eng'g. Dist. | Completed | 2020-11-18 | 2020-02-29 | 2019 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DISASTER REHABILITATION & RECOVERY PROGRAM - Building Back Better Project | [7 empty] | Duration: | 40 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
New Corella | Del Pilar | 1st Eng'g. Dist. | Completed | 2020-11-18 | 2020-02-29 | 2019 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DISASTER REHABILITATION & RECOVERY PROGRAM - Building Back Better Project | [7 empty] | Date Allotment Released: |  | Date completed: | 2020-02-29
New Corella | Del Pilar | 1st Eng'g. Dist. | Completed | 2020-11-18 | 2020-02-29 | 2019 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DISASTER REHABILITATION & RECOVERY PROGRAM - Building Back Better Project | [7 empty] | Date Started: | 2019-11-18
New Corella | Sta. Fe - Mambing | 1st Eng'g. Dist. | Completed | 2020-07-01 | 2020-08-30 | 2019 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DISASTER REHABILITATION & RECOVERY PROGRAM - Building Back Better Project | Rehabilitation of Sta. Fe- Mambing Road & Slope Protection |  | SB NO. 3 CY 2019 (5% CALAMITY FUND) | Road |  |  | Admin | Project Cost: | 1320000 | Target Completion Date: | 2020-08-30 | Program: | 1320000 | Planned: |  | Planned: | 100% | Planned: | 100% | Planned: | 100% | Planned: | 100% | No. of Persons: |  | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per Program of Works
New Corella | Sta. Fe - Mambing | 1st Eng'g. Dist. | Completed | 2020-07-01 | 2020-08-30 | 2019 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DISASTER REHABILITATION & RECOVERY PROGRAM - Building Back Better Project | [7 empty] | Project Engineer: | Pilotos | Revised Completion Date: |  | Allotment: | 1320000 | Revised: |  | Revised: | . | Revised: | . | Revised: | . | Revised: |  | No. of Man-days:
New Corella | Sta. Fe - Mambing | 1st Eng'g. Dist. | Completed | 2020-07-01 | 2020-08-30 | 2019 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DISASTER REHABILITATION & RECOVERY PROGRAM - Building Back Better Project | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: | 100% | Actual: | 100% | Actual: | 100% | Actual: | 100%
New Corella | Sta. Fe - Mambing | 1st Eng'g. Dist. | Completed | 2020-07-01 | 2020-08-30 | 2019 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DISASTER REHABILITATION & RECOVERY PROGRAM - Building Back Better Project | [7 empty] | Duration: | 60 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: |  | Slippage: |  | Slippage: |  | Slippage: | 0%
New Corella | Sta. Fe - Mambing | 1st Eng'g. Dist. | Completed | 2020-07-01 | 2020-08-30 | 2019 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DISASTER REHABILITATION & RECOVERY PROGRAM - Building Back Better Project | [7 empty] | Date Allotment Released: |  | Date completed: | 2020-08-30
New Corella | Sta. Fe - Mambing | 1st Eng'g. Dist. | Completed | 2020-07-01 | 2020-08-30 | 2019 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | DISASTER REHABILITATION & RECOVERY PROGRAM - Building Back Better Project | [7 empty] | Date Started: | 2020-07-01
Asuncion | Sonlon-Camansa | 1st Eng'g. Dist. | On-going | 2019-03-28 |  | 2015 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PRDP | Rehab. Of Sonlon - Camansa FMR Asuncion, Davao del Norte |  | PRDP CY 2015 | Road Concreting | 10.23 | km | Contract | Project Cost: | 215125015.81 | Target Completion Date: | 2021-01-01 | Program: | 215125015.81 | Planned: | 39.51% | Planned: | 40.75% | Planned: | 40.75% | Planned: |  | Planned: | 49.13% | No. of Persons: |  | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. |  |  | On-going
Asuncion | Sonlon-Camansa | 1st Eng'g. Dist. | On-going | 2019-03-28 |  | 2015 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PRDP | [7 empty] | Project Engineer: | Fabiala | Revised Completion Date: | 2021-03-05 | Allotment: | 215125015.81 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
Asuncion | Sonlon-Camansa | 1st Eng'g. Dist. | On-going | 2019-03-28 |  | 2015 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PRDP | [7 empty] | Implementor: | Three w/Builders, Inc/Davao Rock Mixer Enterprises (JV) | No. of days suspended: | 56 | Disbursement: | 40523099.23 | Actual: | 31.6% | Actual: | 33.45% | Actual: | 33.45% | Actual: |  | Actual: | 42.68%
Asuncion | Sonlon-Camansa | 1st Eng'g. Dist. | On-going | 2019-03-28 |  | 2015 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PRDP | [7 empty] | Duration: | 584 | No. of days extended: | 7 |  |  | Slippage: | -7.91% | Slippage: | -7.306% | Slippage: | -7.306% | Slippage: | 0% | Slippage: | -6.452%
Asuncion | Sonlon-Camansa | 1st Eng'g. Dist. | On-going | 2019-03-28 |  | 2015 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PRDP | [7 empty] | Date Allotment Released: | 2018-09-18 | Date completed:
Asuncion | Sonlon-Camansa | 1st Eng'g. Dist. | On-going | 2019-03-28 |  | 2015 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | PRDP | [7 empty] | Date Started: | 2019-05-28
Carmen | La Paz | 1st Eng'g. Dist. | Procurement on process |  |  | 2019 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | PCF | Construction of Evacuation Facility (Const. of Multi-Purpose/Evacuation Center), New Corella |  | PCF CY 2019 | Road |  | km | Contract | Project Cost: | 2500000 | Target Completion Date: | 0 | Program: | 53991806 | Planned: | [7 empty] | No. of Persons: |  | No. of Persons: |  | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Procurement on process
Carmen | La Paz | 1st Eng'g. Dist. | Procurement on process |  |  | 2019 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | PCF | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 53991806 | Revised: | [7 empty] | No. of Man-days: |  | No. of Man-days:
Carmen | La Paz | 1st Eng'g. Dist. | Procurement on process |  |  | 2019 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | PCF | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Carmen | La Paz | 1st Eng'g. Dist. | Procurement on process |  |  | 2019 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | PCF | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage:
Carmen | La Paz | 1st Eng'g. Dist. | Procurement on process |  |  | 2019 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | PCF | [7 empty] | Date Allotment Released: |  | Date completed:
Carmen | La Paz | 1st Eng'g. Dist. | Procurement on process |  |  | 2019 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | PCF | [7 empty] | Date Started:
Carmen | La Paz | 1st Eng'g. Dist. | For turn-over |  |  | 2019 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | PCF | Purchase of Rescue Vehicle |  | PCF CY 2019 | Road |  | km | Contract | Project Cost: | 2000000 | Target Completion Date: | 0 | Program: | 53991806 | Planned: | [7 empty] | No. of Persons: |  | No. of Persons: |  | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | For turn-over
Carmen | La Paz | 1st Eng'g. Dist. | For turn-over |  |  | 2019 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | PCF | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 53991806 | Revised: | [7 empty] | No. of Man-days: |  | No. of Man-days:
Carmen | La Paz | 1st Eng'g. Dist. | For turn-over |  |  | 2019 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | PCF | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Carmen | La Paz | 1st Eng'g. Dist. | For turn-over |  |  | 2019 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | PCF | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage:
Carmen | La Paz | 1st Eng'g. Dist. | For turn-over |  |  | 2019 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | PCF | [7 empty] | Date Allotment Released: |  | Date completed:
Carmen | La Paz | 1st Eng'g. Dist. | For turn-over |  |  | 2019 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | PCF | [7 empty] | Date Started:
Talaingod | Sto. Niño | 1st Eng'g. Dist. | Completed | 2020-03-25 | 2020-04-23 | 2019 | Administration | . | Department of Agriculture | Establishment of Livestock and Poultry Mutiplier Farm, Sitio Salawao, Sto. Niño, Talaingod |  | Department of Agriculture - Regional Field Office XI CY 2019 | Building |  |  |  | Project Cost: | 600000 | Target Completion Date: | 2020-04-23 23:59 | Program: | 600000 | Planned: |  | Planned: |  | Planned: |  | Planned: | 100% | Planned: | 100% | No. of Persons: |  | Final Abstract # 012020012 (Alpebel Builders & Supply Corp.) | Final Abstract # 012020012 (Alpebel Builders & Supply Corp.) | Final Abstract # 012020012 (Alpebel Builders & Supply Corp.) | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per Program of Works
Talaingod | Sto. Niño | 1st Eng'g. Dist. | Completed | 2020-03-25 | 2020-04-23 | 2019 | Administration | . | Department of Agriculture | [7 empty] | Project Engineer: | Dadula | Revised Completion Date: | 2020-04-23 23:59 | Allotment: | 600000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
Talaingod | Sto. Niño | 1st Eng'g. Dist. | Completed | 2020-03-25 | 2020-04-23 | 2019 | Administration | . | Department of Agriculture | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: | 100% | Actual: | 100%
Talaingod | Sto. Niño | 1st Eng'g. Dist. | Completed | 2020-03-25 | 2020-04-23 | 2019 | Administration | . | Department of Agriculture | [7 empty] | Duration: | 30 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Talaingod | Sto. Niño | 1st Eng'g. Dist. | Completed | 2020-03-25 | 2020-04-23 | 2019 | Administration | . | Department of Agriculture | [7 empty] | Date Allotment Released: |  | Date completed: | 2020-03-30
Talaingod | Sto. Niño | 1st Eng'g. Dist. | Completed | 2020-03-25 | 2020-04-23 | 2019 | Administration | . | Department of Agriculture | [7 empty] | Date Started: | 2020-03-25
Talaingod | Sto. Niño | 1st Eng'g. Dist. | Completed | 2020-03-10 | 2020-03-15 | 2019 | Contract | . | VARIOUS GOV'T. BLDG. & FAC. DEV'T. PROJECT | Establishment of Multiplier Farm (Poultry House)Project, Brgy. Sto. Niño, Talaingod |  | Department of Agriculture - Regional Field Office XI CY 2019 | Building |  | sq.m |  | Project Cost: | 1000000 | Target Completion Date: | 2020-04-08 23:59 | Program: | 1000000 | Planned: |  | Planned: |  | Planned: |  | Planned: | 100% | Planned: | 100% | No. of Persons: |  | For bidding on June 30, 2020; Re-bid July 28, 2020. | For bidding on June 30, 2020; Re-bid July 28, 2020. | For bidding on June 30, 2020; Re-bid July 28, 2020. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per Program of Works
Talaingod | Sto. Niño | 1st Eng'g. Dist. | Completed | 2020-03-10 | 2020-03-15 | 2019 | Contract | . | VARIOUS GOV'T. BLDG. & FAC. DEV'T. PROJECT | [7 empty] | Project Engineer: | Dadula | Revised Completion Date: |  | Allotment: | 1000000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
Talaingod | Sto. Niño | 1st Eng'g. Dist. | Completed | 2020-03-10 | 2020-03-15 | 2019 | Contract | . | VARIOUS GOV'T. BLDG. & FAC. DEV'T. PROJECT | [7 empty] | Implementor: | Aplebel Builder's & Supply Corporation | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: | 100% | Actual: | 100%
Talaingod | Sto. Niño | 1st Eng'g. Dist. | Completed | 2020-03-10 | 2020-03-15 | 2019 | Contract | . | VARIOUS GOV'T. BLDG. & FAC. DEV'T. PROJECT | [7 empty] | Duration: | 30 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Talaingod | Sto. Niño | 1st Eng'g. Dist. | Completed | 2020-03-10 | 2020-03-15 | 2019 | Contract | . | VARIOUS GOV'T. BLDG. & FAC. DEV'T. PROJECT | [7 empty] | Date Allotment Released: |  | Date completed: | 2020-03-15
Talaingod | Sto. Niño | 1st Eng'g. Dist. | Completed | 2020-03-10 | 2020-03-15 | 2019 | Contract | . | VARIOUS GOV'T. BLDG. & FAC. DEV'T. PROJECT | [7 empty] | Date Started: | 2020-03-10
Talaingod | Sto. Niño | 1st Eng'g. Dist. | Completed | 2020-03-10 | 2020-03-15 | 2019 | Contract | . | VARIOUS GOV'T. BLDG. & FAC. DEV'T. PROJECT | Poultry House and Training Center, Talaingod |  | Department of Agriculture - Regional Field Office XI CY 2019 | Building |  | sq.m |  | Project Cost: | 500000 | Target Completion Date: | 2020-04-08 23:59 | Program: | 500000 | Planned: |  | Planned: |  | Planned: |  | Planned: | 100% | Planned: | 100% | No. of Persons: |  | For bidding on June 30, 2020; Re-bid July 28, 2020. | For bidding on June 30, 2020; Re-bid July 28, 2020. | For bidding on June 30, 2020; Re-bid July 28, 2020. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per Program of Works
Talaingod | Sto. Niño | 1st Eng'g. Dist. | Completed | 2020-03-10 | 2020-03-15 | 2019 | Contract | . | VARIOUS GOV'T. BLDG. & FAC. DEV'T. PROJECT | [7 empty] | Project Engineer: | Dadula | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
Talaingod | Sto. Niño | 1st Eng'g. Dist. | Completed | 2020-03-10 | 2020-03-15 | 2019 | Contract | . | VARIOUS GOV'T. BLDG. & FAC. DEV'T. PROJECT | [7 empty] | Implementor: | Aplebel Builder's & Supply Corporation | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: | 100% | Actual: | 100%
Talaingod | Sto. Niño | 1st Eng'g. Dist. | Completed | 2020-03-10 | 2020-03-15 | 2019 | Contract | . | VARIOUS GOV'T. BLDG. & FAC. DEV'T. PROJECT | [7 empty] | Duration: | 30 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Talaingod | Sto. Niño | 1st Eng'g. Dist. | Completed | 2020-03-10 | 2020-03-15 | 2019 | Contract | . | VARIOUS GOV'T. BLDG. & FAC. DEV'T. PROJECT | [7 empty] | Date Allotment Released: |  | Date completed: | 2020-03-15
Talaingod | Sto. Niño | 1st Eng'g. Dist. | Completed | 2020-03-10 | 2020-03-15 | 2019 | Contract | . | VARIOUS GOV'T. BLDG. & FAC. DEV'T. PROJECT | [7 empty] | Date Started: | 2020-03-10
Carmen | La Paz | 2nd Eng'g. Dist. | Completed | 2019-10-07 | 2020-09-11 | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CMGP | Road Upgrading of Sto Nino - Kabankalan - La Paz Provincial Road, Carmen |  | CMGP CY 2019 | Road |  | km | Contract | Project Cost: | 44461624.67 | Target Completion Date: | 2020-05-15 23:59 | Program: | 44461624.67 | Planned: | 92.24% | Planned: | 96.53% | Planned: | 96.53% | Planned: | 100% | Planned: | 100% | No. of Persons: | 42 | On-going | On-going | On-going | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per Program of Works
Carmen | La Paz | 2nd Eng'g. Dist. | Completed | 2019-10-07 | 2020-09-11 | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CMGP | [7 empty] | Project Engineer: | Comidoy | Revised Completion Date: | September 13, 2020 | Allotment: | 44461624.67 | Revised: |  | Revised: |  | Revised: |  | Revised: | 100% | Revised: | 100% | No. of Man-days: | 610
Carmen | La Paz | 2nd Eng'g. Dist. | Completed | 2019-10-07 | 2020-09-11 | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CMGP | [7 empty] | Implementor: | GP & H CONST. | No. of days suspended: | 65 | Disbursement: | 40015462.203 | Actual: | 98.54% | Actual: | 98.95% | Actual: | 98.95% | Actual: | 100% | Actual: | 100%
Carmen | La Paz | 2nd Eng'g. Dist. | Completed | 2019-10-07 | 2020-09-11 | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CMGP | [7 empty] | Duration: | 222 | No. of days extended: | 25 |  |  | Slippage: | 6.3% | Slippage: | 2.42% | Slippage: | 2.42% | Slippage: | 0% | Slippage: | 0%
Carmen | La Paz | 2nd Eng'g. Dist. | Completed | 2019-10-07 | 2020-09-11 | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CMGP | [7 empty] | Date Allotment Released: | CY 2019 | Date completed: | 2020-09-11
Carmen | La Paz | 2nd Eng'g. Dist. | Completed | 2019-10-07 | 2020-09-11 | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CMGP | [7 empty] | Date Started: | 2019-10-07
Carmen | La Paz | 2nd Eng'g. Dist. | On-going | 2019-10-07 |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CMGP | Road Upgrading of Jct Highway - Sto Nino - La Paz - San Vicenter Provincial Road, Carmen |  | CMGP CY 2019 | Road |  | km | Contract | Project Cost: | 80481331.34 | Target Completion Date: | 2020-06-22 | Program: | 80481331.34 | Planned: | 97.44% | Planned: | 98.83% | Planned: | 98.83% | Planned: | 100% | Planned: | 100% | No. of Persons: | 10 | On-going | On-going | On-going | On-going | On-going | On-going | 94.91
Carmen | La Paz | 2nd Eng'g. Dist. | On-going | 2019-10-07 |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CMGP | [7 empty] | Project Engineer: | Fernandez | Revised Completion Date: | Oct. 19, 2020 | Allotment: | 80481331.34 | Revised: |  | Revised: |  | Revised: |  | Revised: | 99.26% | Revised: | 99.26% | No. of Man-days: | 250
Carmen | La Paz | 2nd Eng'g. Dist. | On-going | 2019-10-07 |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CMGP | [7 empty] | Implementor: | Tagum Builders | No. of days suspended: | 37 | Disbursement: | 78066891.3998 | Actual: | 97.54% | Actual: | 98.98% | Actual: | 98.98% | Actual: | 99.24% | Actual: | 99.24%
Carmen | La Paz | 2nd Eng'g. Dist. | On-going | 2019-10-07 |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CMGP | [7 empty] | Duration: | 259 | No. of days extended: | 82 |  |  | Slippage: | 0.1% | Slippage: | 0.15% | Slippage: | 0.15% | Slippage: | -0.024% | Slippage: | -0.024%
Carmen | La Paz | 2nd Eng'g. Dist. | On-going | 2019-10-07 |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CMGP | [7 empty] | Date Allotment Released: | CY 2019 | Date completed:
Carmen | La Paz | 2nd Eng'g. Dist. | On-going | 2019-10-07 |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CMGP | [7 empty] | Date Started: | 2019-10-07
kapalong | Mabantao-Florida | 1st Eng'g. Dist. | Completed | 2019-10-16 | 2020-07-03 | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CMGP | Road Upgrading of Kapalong - Mabantao - Florida Road with Bridge Component |  | CMGP CY 2019 | Concreting |  | ln.m | Contract | Project Cost: | 15435008 | Target Completion Date: | 2020-03-10 23:59 | Program: | 15435008 | Planned: | 100% | Planned: | 100% | Planned: | 100% | Planned: | 100% | Planned: | 100% | No. of Persons: |  | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. |  |  | Completed as per Program of Works
kapalong | Mabantao-Florida | 1st Eng'g. Dist. | Completed | 2019-10-16 | 2020-07-03 | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CMGP | [7 empty] | Project Engineer: | Japay/Quirante | Revised Completion Date: | 2020-07-03 23:59 | Allotment: | 15435008 | Revised: | 100% | Revised: | 100% | Revised: | 100% | Revised: | 100% | Revised: | 100% | No. of Man-days:
kapalong | Mabantao-Florida | 1st Eng'g. Dist. | Completed | 2019-10-16 | 2020-07-03 | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CMGP | [7 empty] | Implementor: | LEGACY | No. of days suspended: |  | Disbursement: | 6174003.2 | Actual: | 100% | Actual: | 100% | Actual: | 100% | Actual: | 100% | Actual: | 100%
kapalong | Mabantao-Florida | 1st Eng'g. Dist. | Completed | 2019-10-16 | 2020-07-03 | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CMGP | [7 empty] | Duration: | 147 | No. of days extended: | 115 |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
kapalong | Mabantao-Florida | 1st Eng'g. Dist. | Completed | 2019-10-16 | 2020-07-03 | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CMGP | [7 empty] | Date Allotment Released: | CY 2019 | Date completed: | 2020-07-03
kapalong | Mabantao-Florida | 1st Eng'g. Dist. | Completed | 2019-10-16 | 2020-07-03 | 2019 | Contract | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | CMGP | [7 empty] | Date Started: | 2019-10-16
New Corella | Del Pilar | 1st Eng'g. Dist. | On-going | 2020-06-24 |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | LGSF | Rehabilitation of Dasing to Monte Carlo FMR, Del Pilar, New Corella |  | LGSF CY 2019 | Concreting |  |  | Contract | Project Cost: | 40000000 | Target Completion Date: | 2021-04-04 23:59 | Program: | 40000000 | Planned: | 8.35% | Planned: | 8.35% | Planned: | 8.35% | Planned: | 8.35% | Planned: | 66.49% | No. of Persons: | 10 | On-going | On-going | On-going | On-going | On-going | On-going
New Corella | Del Pilar | 1st Eng'g. Dist. | On-going | 2020-06-24 |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | LGSF | [7 empty] | Project Engineer: | Madrigal | Revised Completion Date: | 2021-04-04 23:59 | Allotment: | 40000000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 250
New Corella | Del Pilar | 1st Eng'g. Dist. | On-going | 2020-06-24 |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | LGSF | [7 empty] | Implementor: | Rely Const. & Supply | No. of days suspended: |  | Disbursement: |  | Actual: | 8.35% | Actual: | 8.35% | Actual: | 8.35% | Actual: | 8.35% | Actual: | 71.31%
New Corella | Del Pilar | 1st Eng'g. Dist. | On-going | 2020-06-24 |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | LGSF | [7 empty] | Duration: | 285 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 4.82%
New Corella | Del Pilar | 1st Eng'g. Dist. | On-going | 2020-06-24 |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | LGSF | [7 empty] | Date Allotment Released: |  | Date completed:
New Corella | Del Pilar | 1st Eng'g. Dist. | On-going | 2020-06-24 |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | LGSF | [7 empty] | Date Started: | 2020-06-24
Tagum City | Magugpo South | 1st Eng'g. Dist. | On-going | 2020-06-23 |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | LGSF | Concreting of Visayan Village - Purok exodus - Purok Rafael, Brgy. Magugpo South, Tagum City |  | LGSF CY 2019 | Concreting |  |  | Contract | Project Cost: | 40000000 | Target Completion Date: | 2021-05-18 23:59 | Program: | 40000000 | Planned: | 14.69% | Planned: | 14.69% | Planned: | 42.57% | Planned: | 42.57% | Planned: | 59.27% | No. of Persons: | 32 | On-going | On-going | On-going | On-going | On-going | On-going
Tagum City | Magugpo South | 1st Eng'g. Dist. | On-going | 2020-06-23 |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | LGSF | [7 empty] | Project Engineer: | Avila | Revised Completion Date: | 2021-05-18 23:59 | Allotment: | 40000000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 960
Tagum City | Magugpo South | 1st Eng'g. Dist. | On-going | 2020-06-23 |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | LGSF | [7 empty] | Implementor: | Legacy Const. Corp. | No. of days suspended: |  | Disbursement: |  | Actual: | 26.73% | Actual: | 26.73% | Actual: | 48.07% | Actual: | 48.07% | Actual: | 70.21%
Tagum City | Magugpo South | 1st Eng'g. Dist. | On-going | 2020-06-23 |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | LGSF | [7 empty] | Duration: | 330 | No. of days extended: |  |  |  | Slippage: | 12.04% | Slippage: | 12.04% | Slippage: | 5.5% | Slippage: | 5.5% | Slippage: | 10.93%
Tagum City | Magugpo South | 1st Eng'g. Dist. | On-going | 2020-06-23 |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | LGSF | [7 empty] | Date Allotment Released: | CY 2019 | Date completed:
Tagum City | Magugpo South | 1st Eng'g. Dist. | On-going | 2020-06-23 |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | LGSF | [7 empty] | Date Started: | 2020-06-23
Panabo City | Buenavista | 2nd Eng'g. Dist. | On-going | 2020-06-29 |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | LGSF | Road Upgrading of Farm To Market Road at Brgy. Buenavista |  | LGSF CY 2019 | Road |  | km | Contract | Project Cost: | 40000000 | Target Completion Date: | 2021-02-04 | Program: | 40000000 | Planned: | 6.3% | Planned: | 6.3% | Planned: | 6.3% | Planned: | 41.42% | Planned: |  | No. of Persons: | 60 | On-going | On-going | On-going |  |  | On-going
Panabo City | Buenavista | 2nd Eng'g. Dist. | On-going | 2020-06-29 |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | LGSF | [7 empty] | Project Engineer: | Nasol | Revised Completion Date: |  | Allotment: | 40000000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 1320
Panabo City | Buenavista | 2nd Eng'g. Dist. | On-going | 2020-06-29 |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | LGSF | [7 empty] | Implementor: | Alpha Omega | No. of days suspended: |  | Disbursement: |  | Actual: | 9.55% | Actual: | 9.55% | Actual: | 9.55% | Actual: | 34.82% | Actual:
Panabo City | Buenavista | 2nd Eng'g. Dist. | On-going | 2020-06-29 |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | LGSF | [7 empty] | Duration: | 220 | No. of days extended: |  |  |  | Slippage: | 3.25% | Slippage: | 3.25% | Slippage: | 3.25% | Slippage: | -6.6% | Slippage:
Panabo City | Buenavista | 2nd Eng'g. Dist. | On-going | 2020-06-29 |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | LGSF | [7 empty] | Date Allotment Released: | CY 2019 | Date completed:
Panabo City | Buenavista | 2nd Eng'g. Dist. | On-going | 2020-06-29 |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | LGSF | [7 empty] | Date Started: | 2020-06-29
Sto. Tomas | New Kat-Pantaron | 2nd Eng'g. Dist. | On-going | 2020-07-08 |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | LGSF | Road Upgrading of New Katipunan-Pantaron Provincial Road |  | LGSF CY 2019 | Road |  | km | Contract | Project Cost: | 30000000 | Target Completion Date: | 2021-01-14 | Program: | 30000000 | Planned: | 1.75% | Planned: | 1.75% | Planned: | 1.75% | Planned: | 31.04% | Planned: |  | No. of Persons: | 20 | On-going | On-going | On-going |  |  | On-going
Sto. Tomas | New Kat-Pantaron | 2nd Eng'g. Dist. | On-going | 2020-07-08 |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | LGSF | [7 empty] | Project Engineer: | Sanchez | Revised Completion Date: | 2021-02-23 | Allotment: | 30000000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 440
Sto. Tomas | New Kat-Pantaron | 2nd Eng'g. Dist. | On-going | 2020-07-08 |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | LGSF | [7 empty] | Implementor: | FFJJ | No. of days suspended: | 40 | Disbursement: |  | Actual: | 1.65% | Actual: | 1.65% | Actual: | 1.65% | Actual: | 31.13% | Actual:
Sto. Tomas | New Kat-Pantaron | 2nd Eng'g. Dist. | On-going | 2020-07-08 |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | LGSF | [7 empty] | Duration: | 190 | No. of days extended: |  |  |  | Slippage: | -0.1% | Slippage: | -0.1% | Slippage: | -0.1% | Slippage: | 0.085% | Slippage:
Sto. Tomas | New Kat-Pantaron | 2nd Eng'g. Dist. | On-going | 2020-07-08 |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | LGSF | [7 empty] | Date Allotment Released: |  | Date completed:
Sto. Tomas | New Kat-Pantaron | 2nd Eng'g. Dist. | On-going | 2020-07-08 |  | 2019 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | LGSF | [7 empty] | Date Started: | 2020-07-08
Asuncion | Magatos-Bantayan | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 001 - Jct. Highway Magatos - New Bantayan |  | GENERAL FUND CY 2020 | Maintenance | 7.1 | km | MBA | Project Cost: | 564839.9739 | Target Completion Date: | 2020-12-31 23:59 | Program: | 564839.9739 | Planned: | 31.14% | Planned: | 31.14% | Planned: | 52.95% | Planned: | 52.95% | Planned: | 100% | No. of Persons: | 17 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | Completed as per Program of Works
Asuncion | Magatos-Bantayan | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 564839.9739 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 374
Asuncion | Magatos-Bantayan | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 57334.17 | Actual: | 31.14% | Actual: | 31.14% | Actual: | 52.95% | Actual: | 52.95% | Actual: | 100%
Asuncion | Magatos-Bantayan | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Asuncion | Magatos-Bantayan | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed: | 2020-12-31
Asuncion | Magatos-Bantayan | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started: | 2020-01-02
Asuncion | Magatos-Bantayan | 1st Eng'g. Dist. | On-going |  |  | 2020 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 001 - Jct. Highway Magatos - New Bantayan |  | GENERAL FUND CY 2020 | Maintenance | 7.1 | km | CBRMC | Project Cost: | 230700 | Target Completion Date: |  | Program: | 230700 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: | 25% | No. of Persons: |  | Purchase Request # 19125305 (On process) | Purchase Request # 19125305 (On process) | Purchase Request # 19125305 (On process) | Purchase Request # 19125305 (On process) | Purchase Request # 19125305 (On process) | On-going
Asuncion | Magatos-Bantayan | 1st Eng'g. Dist. | On-going |  |  | 2020 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: | Fabian | Revised Completion Date: |  | Allotment: | 230700 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
Asuncion | Magatos-Bantayan | 1st Eng'g. Dist. | On-going |  |  | 2020 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: | CALAFA | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual: | 25%
Asuncion | Magatos-Bantayan | 1st Eng'g. Dist. | On-going |  |  | 2020 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Asuncion | Magatos-Bantayan | 1st Eng'g. Dist. | On-going |  |  | 2020 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: |  | Date completed:
Asuncion | Magatos-Bantayan | 1st Eng'g. Dist. | On-going |  |  | 2020 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started:
Asuncion | Magatos-Pagsabangan | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 002 - Magatos - Bdry. Pagsabangan |  | GENERAL FUND CY 2020 | Maintenance | 8.33 | km | MBA | Project Cost: | 653221.626 | Target Completion Date: | 2020-12-31 23:59 | Program: | 653221.626 | Planned: | 28.54% | Planned: | 28.54% | Planned: | 50.33% | Planned: | 50.33% | Planned: | 100% | No. of Persons: | 17 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | Completed as per Program of Works
Asuncion | Magatos-Pagsabangan | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 653221.626 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 374
Asuncion | Magatos-Pagsabangan | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 71713.44 | Actual: | 28.54% | Actual: | 28.54% | Actual: | 50.33% | Actual: | 50.33% | Actual: | 100%
Asuncion | Magatos-Pagsabangan | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Asuncion | Magatos-Pagsabangan | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed: | 2020-12-31
Asuncion | Magatos-Pagsabangan | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started: | 2020-01-02
Asuncion | Magatos-Pagsabangan | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 002 - Magatos - Bdry. Pagsabangan |  | GENERAL FUND CY 2020 | Maintenance | 8.33 | km | CBRMC | Project Cost: | 280180.88 | Target Completion Date: |  | Program: | 280180.88 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Purchase Request # 19125306 (On process) | Purchase Request # 19125306 (On process) | Purchase Request # 19125306 (On process) | Purchase Request # 19125306 (On process) | Purchase Request # 19125306 (On process) | Procurement on process
Asuncion | Magatos-Pagsabangan | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 280180.88 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
Asuncion | Magatos-Pagsabangan | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
Asuncion | Magatos-Pagsabangan | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Asuncion | Magatos-Pagsabangan | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: |  | Date completed:
Asuncion | Magatos-Pagsabangan | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started:
Asuncion | New Bantayan | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 003 - Ilog - New Bantayan |  | GENERAL FUND CY 2020 | Maintenance | 2.68 | km | MBA | Project Cost: | 236174.847 | Target Completion Date: | 2020-12-31 23:59 | Program: | 236174.847 | Planned: | 19.56% | Planned: | 19.56% | Planned: | 57.93% | Planned: | 57.93% | Planned: | 100% | No. of Persons: | 17 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | Completed as per Program of Works
Asuncion | New Bantayan | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 236174.847 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 374
Asuncion | New Bantayan | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 22629.74 | Actual: | 19.56% | Actual: | 19.56% | Actual: | 57.93% | Actual: | 57.93% | Actual: | 100%
Asuncion | New Bantayan | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Asuncion | New Bantayan | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed: | 2020-12-31
Asuncion | New Bantayan | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started: | 2020-01-02
Asuncion | New Bantayan | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 003 - Ilog - New Bantayan |  | GENERAL FUND CY 2020 | Maintenance | 2.68 | km | CBRMC | Project Cost: | 70633.836 | Target Completion Date: |  | Program: | 70633.836 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Purchase Request # 19125307 (On process) | Purchase Request # 19125307 (On process) | Purchase Request # 19125307 (On process) | Purchase Request # 19125307 (On process) | Purchase Request # 19125307 (On process) | Procurement on process
Asuncion | New Bantayan | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 70633.836 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
Asuncion | New Bantayan | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
Asuncion | New Bantayan | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Asuncion | New Bantayan | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: |  | Date completed:
Asuncion | New Bantayan | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started:
Asuncion | Monte Carlo-Del Pilar | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 005 - Asuncion - Monte Carlo - Del Pilar |  | GENERAL FUND CY 2020 | Maintenance | 9.93 | km | MBA | Project Cost: | 716344.9167 | Target Completion Date: | 2020-12-31 23:59 | Program: | 716344.9167 | Planned: | 33.04% | Planned: | 33.04% | Planned: | 51.95% | Planned: | 51.95% | Planned: | 100% | No. of Persons: | 17 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | Completed as per Program of Works
Asuncion | Monte Carlo-Del Pilar | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 716344.9167 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 374
Asuncion | Monte Carlo-Del Pilar | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 33056.21 | Actual: | 33.04% | Actual: | 33.04% | Actual: | 51.95% | Actual: | 51.95% | Actual: | 100%
Asuncion | Monte Carlo-Del Pilar | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Asuncion | Monte Carlo-Del Pilar | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed: | 2020-12-31
Asuncion | Monte Carlo-Del Pilar | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started: | 2020-01-02
Asuncion | Monte Carlo-Del Pilar | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 005 - Asuncion - Monte Carlo - Del Pilar |  | GENERAL FUND CY 2020 | Maintenance | 9.93 | km | CBRMC | Project Cost: | 360232.5636 | Target Completion Date: |  | Program: | 360232.5636 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Awarded to Mahayahay Integrated Farmers Association | Awarded to Mahayahay Integrated Farmers Association | Awarded to Mahayahay Integrated Farmers Association | Awarded to Mahayahay Integrated Farmers Association | Awarded to Mahayahay Integrated Farmers Association | For implementation
Asuncion | Monte Carlo-Del Pilar | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 360232.5636 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
Asuncion | Monte Carlo-Del Pilar | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
Asuncion | Monte Carlo-Del Pilar | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Asuncion | Monte Carlo-Del Pilar | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: |  | Date completed:
Asuncion | Monte Carlo-Del Pilar | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started:
Asuncion | Canatan-Magatos | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 006 - Jct. Highway Canatan - Magatos |  | GENERAL FUND CY 2020 | Maintenance | 4.85 | km | MBA | Project Cost: | 391296.517 | Target Completion Date: | 2020-12-31 23:59 | Program: | 391296.517 | Planned: | 28.48% | Planned: | 28.48% | Planned: | 46.61% | Planned: | 46.61% | Planned: | 100% | No. of Persons: | 17 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | Completed as per Program of Works
Asuncion | Canatan-Magatos | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 391296.517 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 374
Asuncion | Canatan-Magatos | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 33056.21 | Actual: | 28.48% | Actual: | 28.48% | Actual: | 46.61% | Actual: | 46.61% | Actual: | 100%
Asuncion | Canatan-Magatos | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Asuncion | Canatan-Magatos | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed: | 2020-12-31
Asuncion | Canatan-Magatos | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started: | 2020-01-02
Asuncion | Canatan-Magatos | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 006 - Jct. Highway Canatan - Magatos |  | GENERAL FUND CY 2020 | Maintenance | 4.85 | km | CBRMC | Project Cost: | 164812.284 | Target Completion Date: |  | Program: | 164812.284 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Purchase Request # 19125309 (On process) | Purchase Request # 19125309 (On process) | Purchase Request # 19125309 (On process) | Purchase Request # 19125309 (On process) | Purchase Request # 19125309 (On process) | Procurement on process
Asuncion | Canatan-Magatos | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 164812.284 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
Asuncion | Canatan-Magatos | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
Asuncion | Canatan-Magatos | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Asuncion | Canatan-Magatos | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: |  | Date completed:
Asuncion | Canatan-Magatos | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started:
Asuncion | Saug-Sonlon-Longanapan | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 010 - Saug - Sonlon - Bdry. Longanapan |  | GENERAL FUND CY 2020 | Maintenance | 11.6 | km | MBA | Project Cost: | 1102041.4797 | Target Completion Date: | 2020-12-31 23:59 | Program: | 1102041.4797 | Planned: | 25.36% | Planned: | 25.36% | Planned: | 37.74% | Planned: | 37.74% | Planned: | 100% | No. of Persons: | 17 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | Completed as per Program of Works
Asuncion | Saug-Sonlon-Longanapan | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 1102041.4797 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 374
Asuncion | Saug-Sonlon-Longanapan | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 83166.18 | Actual: | 25.36% | Actual: | 25.36% | Actual: | 37.74% | Actual: | 37.74% | Actual: | 100%
Asuncion | Saug-Sonlon-Longanapan | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Asuncion | Saug-Sonlon-Longanapan | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed: | 2020-12-31
Asuncion | Saug-Sonlon-Longanapan | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started: | 2020-01-02
Asuncion | Saug-Sonlon-Longanapan | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 010 - Saug - Sonlon - Bdry. Longanapan |  | GENERAL FUND CY 2020 | Maintenance | 11.6 | km | CBRMC | Project Cost: | 197774.7408 | Target Completion Date: |  | Program: | 197774.7408 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Purchase Request # 19125310 (On process) | Purchase Request # 19125310 (On process) | Purchase Request # 19125310 (On process) | Purchase Request # 19125310 (On process) | Purchase Request # 19125310 (On process) | Procurement on process
Asuncion | Saug-Sonlon-Longanapan | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 197774.7408 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
Asuncion | Saug-Sonlon-Longanapan | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
Asuncion | Saug-Sonlon-Longanapan | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Asuncion | Saug-Sonlon-Longanapan | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: |  | Date completed:
Asuncion | Saug-Sonlon-Longanapan | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started:
Asuncion | New Visayas-Buan | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 011 - Jct. New Visayas - Buan |  | GENERAL FUND CY 2020 | Maintenance | 2.99 | km | MBA | Project Cost: | 134598.4525 | Target Completion Date: | 2020-12-31 23:59 | Program: | 134598.4525 | Planned: | 11.58% | Planned: | 11.58% | Planned: | 55.5% | Planned: | 55.5% | Planned: | 100% | No. of Persons: | 17 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | Completed as per Program of Works
Asuncion | New Visayas-Buan | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 134598.4525 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 374
Asuncion | New Visayas-Buan | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 10391.0005 | Actual: | 11.58% | Actual: | 11.58% | Actual: | 55.5% | Actual: | 55.5% | Actual: | 100%
Asuncion | New Visayas-Buan | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Asuncion | New Visayas-Buan | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed: | 2020-12-31
Asuncion | New Visayas-Buan | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started: | 2020-01-02
Asuncion | New Visayas-Buan | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 011 - Jct. New Visayas - Buan |  | GENERAL FUND CY 2020 | Maintenance | 2.99 | km | CBRMC | Project Cost: | 124786.4436 | Target Completion Date: |  | Program: | 124786.4436 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Purchase Request # 19125311 (On process) | Purchase Request # 19125311 (On process) | Purchase Request # 19125311 (On process) | Purchase Request # 19125311 (On process) | Purchase Request # 19125311 (On process) | Procurement on process
Asuncion | New Visayas-Buan | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 124786.4436 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
Asuncion | New Visayas-Buan | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
Asuncion | New Visayas-Buan | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Asuncion | New Visayas-Buan | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: |  | Date completed:
Asuncion | New Visayas-Buan | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started:
Asuncion | San Vicente-Butay | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 013 - San Vicente - Butay |  | GENERAL FUND CY 2020 | Maintenance | 7.52 | km | MBA | Project Cost: | 579541.5407 | Target Completion Date: | 2020-12-31 23:59 | Program: | 579541.5407 | Planned: | 33.79% | Planned: | 33.79% | Planned: | 51.53% | Planned: | 51.53% | Planned: | 100% | No. of Persons: | 17 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | Completed as per Program of Works
Asuncion | San Vicente-Butay | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 579541.5407 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 374
Asuncion | San Vicente-Butay | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 123616.2106 | Actual: | 33.79% | Actual: | 33.79% | Actual: | 51.53% | Actual: | 51.53% | Actual: | 100%
Asuncion | San Vicente-Butay | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Asuncion | San Vicente-Butay | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed: | 2020-12-31
Asuncion | San Vicente-Butay | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started: | 2020-01-02
Asuncion | San Vicente-Butay | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 013 - San Vicente - Butay |  | GENERAL FUND CY 2020 | Maintenance | 7.52 | km | CBRMC | Project Cost: | 235446.12 | Target Completion Date: |  | Program: | 235446.12 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Purchase Request # 19125312 (On process) | Purchase Request # 19125312 (On process) | Purchase Request # 19125312 (On process) | Purchase Request # 19125312 (On process) | Purchase Request # 19125312 (On process) | Procurement on process
Asuncion | San Vicente-Butay | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 235446.12 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
Asuncion | San Vicente-Butay | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
Asuncion | San Vicente-Butay | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Asuncion | San Vicente-Butay | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: |  | Date completed:
Asuncion | San Vicente-Butay | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started:
kapalong | Doña Andrea-Capungagan | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 014 - Jct. Highway Doña Andrea - Capungagan |  | GENERAL FUND CY 2020 | Maintenance | 8.7 | km | MBA | Project Cost: | 675845.5865 | Target Completion Date: | 2020-12-31 23:59 | Program: | 675845.5865 | Planned: | 18.55% | Planned: | 18.55% | Planned: | 44.7% | Planned: | 44.7% | Planned: | 100% | No. of Persons: | 17 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | Completed as per Program of Works
kapalong | Doña Andrea-Capungagan | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 675845.5865 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 374
kapalong | Doña Andrea-Capungagan | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 75289.1983 | Actual: | 18.55% | Actual: | 18.55% | Actual: | 44.7% | Actual: | 44.7% | Actual: | 100%
kapalong | Doña Andrea-Capungagan | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
kapalong | Doña Andrea-Capungagan | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed: | 2020-12-31
kapalong | Doña Andrea-Capungagan | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started: | 2020-01-02
kapalong | Doña Andrea-Capungagan | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 014 - Jct. Highway Doña Andrea - Capungagan |  | GENERAL FUND CY 2020 | Maintenance | 8.7 | km | CBRMC | Project Cost: | 299016.5724 | Target Completion Date: |  | Program: | 299016.5724 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Purchase Request # 19125313 (On process) | Purchase Request # 19125313 (On process) | Purchase Request # 19125313 (On process) | Purchase Request # 19125313 (On process) | Purchase Request # 19125313 (On process) | Procurement on process
kapalong | Doña Andrea-Capungagan | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 299016.5724 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
kapalong | Doña Andrea-Capungagan | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
kapalong | Doña Andrea-Capungagan | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
kapalong | Doña Andrea-Capungagan | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: |  | Date completed:
kapalong | Doña Andrea-Capungagan | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started:
kapalong | Pamacaun-Lasang-banate | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 015 - Pamacaun - Lasang - Banate |  | GENERAL FUND CY 2020 | Maintenance | 4.11 | km | MBA | Project Cost: | 180747.1933 | Target Completion Date: | 2020-12-31 23:59 | Program: | 180747.1933 | Planned: | 12.9% | Planned: | 12.9% | Planned: | 55.68% | Planned: | 55.68% | Planned: | 100% | No. of Persons: | 17 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | Completed as per Program of Works
kapalong | Pamacaun-Lasang-banate | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 180747.1933 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 374
kapalong | Pamacaun-Lasang-banate | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 15544.2586 | Actual: | 12.9% | Actual: | 12.9% | Actual: | 55.68% | Actual: | 55.68% | Actual: | 100%
kapalong | Pamacaun-Lasang-banate | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
kapalong | Pamacaun-Lasang-banate | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed: | 2020-12-31
kapalong | Pamacaun-Lasang-banate | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started: | 2020-01-02
kapalong | Pamacaun-Lasang-banate | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 015 - Pamacaun - Lasang - Banate |  | GENERAL FUND CY 2020 | Maintenance | 4.11 | km | CBRMC | Project Cost: | 129495.366 | Target Completion Date: |  | Program: | 129495.366 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Purchase Request # 19125314 (On process) | Purchase Request # 19125314 (On process) | Purchase Request # 19125314 (On process) | Purchase Request # 19125314 (On process) | Purchase Request # 19125314 (On process) | Procurement on process
kapalong | Pamacaun-Lasang-banate | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 129495.366 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
kapalong | Pamacaun-Lasang-banate | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
kapalong | Pamacaun-Lasang-banate | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
kapalong | Pamacaun-Lasang-banate | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: |  | Date completed:
kapalong | Pamacaun-Lasang-banate | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started:
kapalong | Semong-Palma Gil | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 018 - Semong - Palma Gil |  | GENERAL FUND CY 2020 | Maintenance | 2.73 | km | MBA | Project Cost: | 276301.31 | Target Completion Date: | 2020-12-31 23:59 | Program: | 276301.31 | Planned: | 50.35% | Planned: | 50.35% | Planned: | 58.18% | Planned: | 58.18% | Planned: | 100% | No. of Persons: | 14 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | Completed as per Program of Works
kapalong | Semong-Palma Gil | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 276301.31 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 210
kapalong | Semong-Palma Gil | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 139117.7096 | Actual: | 50.35% | Actual: | 50.35% | Actual: | 58.18% | Actual: | 58.18% | Actual: | 100%
kapalong | Semong-Palma Gil | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
kapalong | Semong-Palma Gil | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed: | 2020-12-31
kapalong | Semong-Palma Gil | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started: | 2020-01-02
kapalong | Semong-Palma Gil | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 018 - Semong - Palma Gil |  | GENERAL FUND CY 2020 | Maintenance | 2.73 | km | CBRMC | Project Cost: | 77697.2196 | Target Completion Date: |  | Program: | 77697.2196 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Purchase Request # 19125315 (On process) | Purchase Request # 19125315 (On process) | Purchase Request # 19125315 (On process) | Purchase Request # 19125315 (On process) | Purchase Request # 19125315 (On process) | Procurement on process
kapalong | Semong-Palma Gil | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 77697.2196 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
kapalong | Semong-Palma Gil | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
kapalong | Semong-Palma Gil | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
kapalong | Semong-Palma Gil | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: |  | Date completed:
kapalong | Semong-Palma Gil | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started:
Talaingod | Daligdigon-Dagohoy | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 020 - Daligdigon-Dagohoy |  | GENERAL FUND CY 2020 | Maintenance | 3.34 | km | MBA | Project Cost: | 161826.4 | Target Completion Date: | 2020-12-31 23:59 | Program: | 161826.4 | Planned: | 51.55% | Planned: | 51.55% | Planned: | 61.03% | Planned: | 61.03% | Planned: | 100% | No. of Persons: | 14 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | Completed as per Program of Works
Talaingod | Daligdigon-Dagohoy | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 161826.4 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 210
Talaingod | Daligdigon-Dagohoy | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 83421.5092 | Actual: | 51.55% | Actual: | 51.55% | Actual: | 61.03% | Actual: | 61.03% | Actual: | 100%
Talaingod | Daligdigon-Dagohoy | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Talaingod | Daligdigon-Dagohoy | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed: | 2020-12-31
Talaingod | Daligdigon-Dagohoy | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started: | 2020-01-02
Talaingod | Daligdigon-Dagohoy | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 020 - Daligdigon-Dagohoy |  | GENERAL FUND CY 2020 | Maintenance | 3.34 | km | CBRMC | Project Cost: | 77697.2196 | Target Completion Date: |  | Program: | 77697.2196 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Purchase Request # 19125315 (On process) | Purchase Request # 19125315 (On process) | Purchase Request # 19125315 (On process) | Purchase Request # 19125315 (On process) | Purchase Request # 19125315 (On process) | Procurement on process
Talaingod | Daligdigon-Dagohoy | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 77697.2196 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
Talaingod | Daligdigon-Dagohoy | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
Talaingod | Daligdigon-Dagohoy | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Talaingod | Daligdigon-Dagohoy | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: |  | Date completed:
Talaingod | Daligdigon-Dagohoy | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started:
Talaingod | Angelo-Dahgohoy | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 021 - Angelo - Dagohoy |  | GENERAL FUND CY 2020 | Maintenance | 2.19 | km | MBA | Project Cost: | 67286.09 | Target Completion Date: | 2020-12-31 23:59 | Program: | 67286.09 | Planned: | 43.7% | Planned: | 43.7% | Planned: | 78.17% | Planned: | 78.17% | Planned: | 100% | No. of Persons: | 14 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | Completed as per Program of Works
Talaingod | Angelo-Dahgohoy | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 67286.09 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 210
Talaingod | Angelo-Dahgohoy | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 29404.0213 | Actual: | 43.7% | Actual: | 43.7% | Actual: | 78.18% | Actual: | 78.18% | Actual: | 100%
Talaingod | Angelo-Dahgohoy | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0.01% | Slippage: | 0.01% | Slippage: | 0%
Talaingod | Angelo-Dahgohoy | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed: | 2020-12-31
Talaingod | Angelo-Dahgohoy | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started: | 2020-01-02
Talaingod | Angelo-Dahgohoy | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 021 - Angelo - Dagohoy |  | GENERAL FUND CY 2020 | Maintenance | 2.19 | km | CBRMC | Project Cost: | 40025.8404 | Target Completion Date: |  | Program: | 40025.8404 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Purchase Request # 19125317 (On process) | Purchase Request # 19125317 (On process) | Purchase Request # 19125317 (On process) | Purchase Request # 19125317 (On process) | Purchase Request # 19125317 (On process) | Procurement on process
Talaingod | Angelo-Dahgohoy | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 40025.8404 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
Talaingod | Angelo-Dahgohoy | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
Talaingod | Angelo-Dahgohoy | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Talaingod | Angelo-Dahgohoy | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: |  | Date completed:
Talaingod | Angelo-Dahgohoy | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started:
kapalong | Sampao-Mamacao | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 025 - Jct. Sampao - Bdry. Mamacao |  | GENERAL FUND CY 2020 | Maintenance | 4.98 | km | MBA | Project Cost: | 325083.1184 | Target Completion Date: | 2020-12-31 23:59 | Program: | 325083.1184 | Planned: | 27.89% | Planned: | 27.89% | Planned: | 47.54% | Planned: | 47.54% | Planned: | 100% | No. of Persons: | 17 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | Completed as per Program of Works
kapalong | Sampao-Mamacao | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 325083.1184 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 374
kapalong | Sampao-Mamacao | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 47819.7267 | Actual: | 27.89% | Actual: | 27.89% | Actual: | 47.54% | Actual: | 47.54% | Actual: | 100%
kapalong | Sampao-Mamacao | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
kapalong | Sampao-Mamacao | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed: | 2020-12-31
kapalong | Sampao-Mamacao | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started: | 2020-01-02
kapalong | Sampao-Mamacao | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 025 - Jct. Sampao - Bdry. Mamacao |  | GENERAL FUND CY 2020 | Maintenance | 4.98 | km | CBRMC | Project Cost: | 178939.0512 | Target Completion Date: |  | Program: | 178939.0512 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Purchase Request # 19125318 (On process) | Purchase Request # 19125318 (On process) | Purchase Request # 19125318 (On process) | Purchase Request # 19125318 (On process) | Purchase Request # 19125318 (On process) | Procurement on process
kapalong | Sampao-Mamacao | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 178939.0512 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
kapalong | Sampao-Mamacao | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
kapalong | Sampao-Mamacao | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
kapalong | Sampao-Mamacao | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: |  | Date completed:
kapalong | Sampao-Mamacao | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started:
kapalong | Luna-Mamacao | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 026 - Jct. Highway - Luna - Mamacao - Narra |  | GENERAL FUND CY 2020 | Maintenance | 9.17 | km | MBA | Project Cost: | 361826.1515 | Target Completion Date: | 2020-12-31 23:59 | Program: | 361826.1515 | Planned: | 20.12% | Planned: | 20.12% | Planned: | 52.72% | Planned: | 52.72% | Planned: | 100% | No. of Persons: | 17 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | Completed as per Program of Works
kapalong | Luna-Mamacao | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 361826.1515 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 374
kapalong | Luna-Mamacao | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 22433.2214 | Actual: | 20.12% | Actual: | 20.12% | Actual: | 52.72% | Actual: | 52.72% | Actual: | 100%
kapalong | Luna-Mamacao | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
kapalong | Luna-Mamacao | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed: | 2020-12-31
kapalong | Luna-Mamacao | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started: | 2020-01-02
kapalong | Luna-Mamacao | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 026 - Jct. Highway - Luna - Mamacao - Narra |  | GENERAL FUND CY 2020 | Maintenance | 9.17 | km | CBRMC | Project Cost: | 393195.0204 | Target Completion Date: |  | Program: | 393195.0204 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Purchase Request # 19125337 (On process) | Purchase Request # 19125337 (On process) | Purchase Request # 19125337 (On process) | Purchase Request # 19125337 (On process) | Purchase Request # 19125337 (On process) | Procurement on process
kapalong | Luna-Mamacao | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 393195.0204 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
kapalong | Luna-Mamacao | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
kapalong | Luna-Mamacao | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
kapalong | Luna-Mamacao | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: |  | Date completed:
kapalong | Luna-Mamacao | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started:
kapalong | Gabuyan-Katipunan | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 027 - Jct. Gabuyan - Katipunan - Bucana |  | GENERAL FUND CY 2020 | Maintenance | 5.89 | km | MBA | Project Cost: | 485762.7577 | Target Completion Date: | 2020-12-31 23:59 | Program: | 485762.7577 | Planned: | 11.79% | Planned: | 11.79% | Planned: | 37% | Planned: | 37% | Planned: | 100% | No. of Persons: | 17 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | Completed as per Program of Works
kapalong | Gabuyan-Katipunan | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 485762.7577 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 374
kapalong | Gabuyan-Katipunan | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 38180.9528 | Actual: | 11.79% | Actual: | 11.79% | Actual: | 37% | Actual: | 37% | Actual: | 100%
kapalong | Gabuyan-Katipunan | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
kapalong | Gabuyan-Katipunan | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed: | 2020-12-31
kapalong | Gabuyan-Katipunan | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started: | 2020-01-02
kapalong | Gabuyan-Katipunan | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 027 - Jct. Gabuyan - Katipunan - Bucana |  | GENERAL FUND CY 2020 | Maintenance | 5.89 | km | CBRMC | Project Cost: | 174230.1288 | Target Completion Date: |  | Program: | 174230.1288 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Purchase Request # 19125338 (On process) | Purchase Request # 19125338 (On process) | Purchase Request # 19125338 (On process) | Purchase Request # 19125338 (On process) | Purchase Request # 19125338 (On process) | Procurement on process
kapalong | Gabuyan-Katipunan | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 174230.1288 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
kapalong | Gabuyan-Katipunan | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
kapalong | Gabuyan-Katipunan | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
kapalong | Gabuyan-Katipunan | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: |  | Date completed:
kapalong | Gabuyan-Katipunan | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started:
kapalong | Capungagan-Mabuhay | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 028 - Capungagan - Mabuhay - Pandulian |  | GENERAL FUND CY 2020 | Maintenance | 5.57 | km | MBA | Project Cost: | 468741.4542 | Target Completion Date: | 2020-12-31 23:59 | Program: | 468741.4542 | Planned: | 7.71% | Planned: | 7.71% | Planned: | 32.2% | Planned: | 32.2% | Planned: | 100% | No. of Persons: | 17 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | Completed as per Program of Works
kapalong | Capungagan-Mabuhay | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 468741.4542 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 374
kapalong | Capungagan-Mabuhay | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 24093.3107 | Actual: | 7.71% | Actual: | 7.71% | Actual: | 32.02% | Actual: | 32.02% | Actual: | 100%
kapalong | Capungagan-Mabuhay | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | -0.18% | Slippage: | -0.18% | Slippage: | 0%
kapalong | Capungagan-Mabuhay | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed: | 2020-12-31
kapalong | Capungagan-Mabuhay | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started: | 2020-01-02
kapalong | Capungagan-Mabuhay | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 028 - Capungagan - Mabuhay - Pandulian |  | GENERAL FUND CY 2020 | Maintenance | 5.57 | km | CBRMC | Project Cost: | 155394.4392 | Target Completion Date: |  | Program: | 155394.4392 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Procurement on process | Purchase Request # 19125339 (On process) | Purchase Request # 19125339 (On process) | Purchase Request # 19125339 (On process) | Purchase Request # 19125339 (On process) | Procurement on process
kapalong | Capungagan-Mabuhay | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 155394.4392 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
kapalong | Capungagan-Mabuhay | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
kapalong | Capungagan-Mabuhay | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
kapalong | Capungagan-Mabuhay | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: |  | Date completed:
kapalong | Capungagan-Mabuhay | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started:
San Isidro | Kipalili-New Loon | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 034 - Km. 15, Kipalili - New Loon |  | GENERAL FUND CY 2020 | Maintenance | 6.93 | km | MBA | Project Cost: | 490709.8742 | Target Completion Date: | 2020-12-31 23:59 | Program: | 490709.8742 | Planned: | 22.39% | Planned: | 22.39% | Planned: | 43.71% | Planned: | 43.71% | Planned: | 100% | No. of Persons: | 17 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | Completed as per Program of Works
San Isidro | Kipalili-New Loon | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 490709.8742 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 374
San Isidro | Kipalili-New Loon | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 66393.046 | Actual: | 22.39% | Actual: | 22.39% | Actual: | 43.71% | Actual: | 43.71% | Actual: | 100%
San Isidro | Kipalili-New Loon | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
San Isidro | Kipalili-New Loon | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed: | 2020-12-31
San Isidro | Kipalili-New Loon | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started: | 2020-01-02
San Isidro | Kipalili-New Loon | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 034 - Km. 15, Kipalili - New Loon |  | GENERAL FUND CY 2020 | Maintenance | 6.93 | km | CBRMC | Project Cost: | 296662.1112 | Target Completion Date: |  | Program: | 296662.1112 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Procurement on process | Purchase Request # 19125340 (On process) | Purchase Request # 19125340 (On process) | Purchase Request # 19125340 (On process) | Purchase Request # 19125340 (On process) | Procurement on process
San Isidro | Kipalili-New Loon | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 296662.1112 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
San Isidro | Kipalili-New Loon | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
San Isidro | Kipalili-New Loon | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
San Isidro | Kipalili-New Loon | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: |  | Date completed:
San Isidro | Kipalili-New Loon | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started:
San Isidro | Suaon-Libuton | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 035 - Jct. Suaon - Libuton |  | GENERAL FUND CY 2020 | Maintenance | 7.26 | km | MBA | Project Cost: | 60919.7962 | Target Completion Date: | 2020-12-31 23:59 | Program: | 60919.7962 | Planned: | 10.68% | Planned: | 10.68% | Planned: | 56.31% | Planned: | 56.31% | Planned: | 100% | No. of Persons: | 17 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | Completed as per Program of Works
San Isidro | Suaon-Libuton | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 60919.7962 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 374
San Isidro | Suaon-Libuton | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: |  | Actual: | 10.68% | Actual: | 10.68% | Actual: | 56.31% | Actual: | 56.31% | Actual: | 100%
San Isidro | Suaon-Libuton | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
San Isidro | Suaon-Libuton | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed: | 2020-12-31
San Isidro | Suaon-Libuton | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started: | 2020-01-02
San Isidro | Suaon-Libuton | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 035 - Jct. Suaon - Libuton |  | GENERAL FUND CY 2020 | Maintenance | 7.26 | km | CBRMC | Project Cost: | 96532.9092 | Target Completion Date: |  | Program: | 96532.9092 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Awarded to Association of Alternative Livelihood of Libuton Inc. | Awarded to Association of Alternative Livelihood of Libuton Inc. | Awarded to Association of Alternative Livelihood of Libuton Inc. | Awarded to Association of Alternative Livelihood of Libuton Inc. | Awarded to Association of Alternative Livelihood of Libuton Inc. | Procurement on process
San Isidro | Suaon-Libuton | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 96532.9092 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
San Isidro | Suaon-Libuton | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
San Isidro | Suaon-Libuton | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
San Isidro | Suaon-Libuton | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: |  | Date completed:
San Isidro | Suaon-Libuton | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started:
San Isidro | Monte Dujali-Gupitan | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 037 - Monte Dujali - Gupitan |  | GENERAL FUND CY 2020 | Maintenance | 4.58 | km | MBA | Project Cost: | 224727.1648 | Target Completion Date: | 2020-12-31 23:59 | Program: | 224727.1648 | Planned: | 16.62% | Planned: | 35.49% | Planned: | 56.71% | Planned: | 56.71% | Planned: | 100% | No. of Persons: | 17 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | Completed as per Program of Works
San Isidro | Monte Dujali-Gupitan | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 224727.1648 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 374
San Isidro | Monte Dujali-Gupitan | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 37349.6548 | Actual: | 16.62% | Actual: | 35.49% | Actual: | 56.71% | Actual: | 56.71% | Actual: | 100%
San Isidro | Monte Dujali-Gupitan | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
San Isidro | Monte Dujali-Gupitan | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed: | 2020-12-31
San Isidro | Monte Dujali-Gupitan | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started: | 2020-01-02
San Isidro | Monte Dujali-Gupitan | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 037 - Monte Dujali - Gupitan |  | GENERAL FUND CY 2020 | Maintenance | 4.58 | km | CBRMC | Project Cost: | 134204.2884 | Target Completion Date: |  | Program: | 134204.2884 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Awarded to Association of Alternative Livelihood of Libuton Inc. | Awarded to Association of Alternative Livelihood of Libuton Inc. | Awarded to Association of Alternative Livelihood of Libuton Inc. | Awarded to Association of Alternative Livelihood of Libuton Inc. | Awarded to Association of Alternative Livelihood of Libuton Inc. | Procurement on process
San Isidro | Monte Dujali-Gupitan | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 134204.2884 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
San Isidro | Monte Dujali-Gupitan | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
San Isidro | Monte Dujali-Gupitan | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
San Isidro | Monte Dujali-Gupitan | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: |  | Date completed:
San Isidro | Monte Dujali-Gupitan | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started:
San Isidro | Sawata-Mamangan-Pinamuno | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 041 - Sawata - Mamangan - Pinamuno |  | GENERAL FUND CY 2020 | Maintenance | 14.48 | km | MBA | Project Cost: | 1636481.63 | Target Completion Date: | 2021-02-01 23:59 | Program: | 1636481.63 | Planned: | 37.11% | Planned: | 37.11% | Planned: | 43.95% | Planned: | 43.95% | Planned: | 100% | No. of Persons: | 14 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | Completed as per Program of Works
San Isidro | Sawata-Mamangan-Pinamuno | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-02-28 23:59 | Allotment: | 1636481.63 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 210
San Isidro | Sawata-Mamangan-Pinamuno | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 607298.3329 | Actual: | 37.11% | Actual: | 37.11% | Actual: | 43.95% | Actual: | 43.95% | Actual: | 100%
San Isidro | Sawata-Mamangan-Pinamuno | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
San Isidro | Sawata-Mamangan-Pinamuno | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed: | 2020-12-31
San Isidro | Sawata-Mamangan-Pinamuno | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started: | 2020-02-03
San Isidro | Sawata-Mamangan-Pinamuno | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 041 - Sawata - Mamangan - Pinamuno |  | GENERAL FUND CY 2020 | Maintenance | 14.48 | km | CBRMC | Project Cost: | 522690.3864 | Target Completion Date: |  | Program: | 522690.3864 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Procurement on process | Purchase Request # 19125343 (On process) | Purchase Request # 19125343 (On process) | Purchase Request # 19125343 (On process) | Purchase Request # 19125343 (On process) | Procurement on process
San Isidro | Sawata-Mamangan-Pinamuno | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 522690.3864 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
San Isidro | Sawata-Mamangan-Pinamuno | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
San Isidro | Sawata-Mamangan-Pinamuno | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
San Isidro | Sawata-Mamangan-Pinamuno | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: |  | Date completed:
San Isidro | Sawata-Mamangan-Pinamuno | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started:
San Isidro | Igangon-Sawata | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 042 - Igangon - Sawata |  | GENERAL FUND CY 2020 | Maintenance | 9.66 | km | MBA | Project Cost: | 314254.79 | Target Completion Date: | 2020-12-31 23:59 | Program: | 314254.79 | Planned: | 13.11% | Planned: | 33.05% | Planned: | 55.76% | Planned: | 55.76% | Planned: | 100% | No. of Persons: | 17 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | Completed as per Program of Works
San Isidro | Igangon-Sawata | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 314254.79 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 374
San Isidro | Igangon-Sawata | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 41198.803 | Actual: | 13.11% | Actual: | 33.05% | Actual: | 55.76% | Actual: | 55.76% | Actual: | 100%
San Isidro | Igangon-Sawata | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
San Isidro | Igangon-Sawata | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed: | 2020-12-31
San Isidro | Igangon-Sawata | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started: | 2020-01-02
San Isidro | Igangon-Sawata | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 042 - Igangon - Sawata |  | GENERAL FUND CY 2020 | Maintenance | 9.66 | km | CBRMC | Project Cost: | 202483.6632 | Target Completion Date: |  | Program: | 202483.6632 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Purchase Request # 19125344 (On process) | Purchase Request # 19125344 (On process) | Purchase Request # 19125344 (On process) | Purchase Request # 19125344 (On process) | Purchase Request # 19125344 (On process) | Procurement on process
San Isidro | Igangon-Sawata | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 202483.6632 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
San Isidro | Igangon-Sawata | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
San Isidro | Igangon-Sawata | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
San Isidro | Igangon-Sawata | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: |  | Date completed:
San Isidro | Igangon-Sawata | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started:
San Isidro | Sawata | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 043 - Jct. Sawata - Bdry. Binasbas |  | GENERAL FUND CY 2020 | Maintenance | 0.46 | km | MBA | Project Cost: | 46556.26 | Target Completion Date: | 2020-12-31 23:59 | Program: | 46556.26 | Planned: | 16.23% | Planned: | 30.75% | Planned: | 63.48% | Planned: | 63.48% | Planned: | 100% | No. of Persons: | 17 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | Completed as per Program of Works
San Isidro | Sawata | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 46556.26 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 374
San Isidro | Sawata | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 7556.081 | Actual: | 16.23% | Actual: | 30.75% | Actual: | 63.48% | Actual: | 63.48% | Actual: | 100%
San Isidro | Sawata | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
San Isidro | Sawata | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed: | 2020-12-31
San Isidro | Sawata | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started: | 2020-01-02
San Isidro | Sawata | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 043 - Jct. Sawata - Bdry. Binasbas |  | GENERAL FUND CY 2020 | Maintenance | 0.46 | km | CBRMC | Project Cost: | 18835.6896 | Target Completion Date: |  | Program: | 18835.6896 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Purchase Request # 19125345 (On process) | Purchase Request # 19125345 (On process) | Purchase Request # 19125345 (On process) | Purchase Request # 19125345 (On process) | Purchase Request # 19125345 (On process) | Procurement on process
San Isidro | Sawata | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 18835.6896 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
San Isidro | Sawata | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
San Isidro | Sawata | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
San Isidro | Sawata | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: |  | Date completed:
San Isidro | Sawata | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started:
Asuncion | Buan | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 045 - Tagaytay - Buan |  | GENERAL FUND CY 2020 | Maintenance | 4.92 | km | MBA | Project Cost: | 552783.35 | Target Completion Date: | 2020-12-31 23:59 | Program: | 552783.35 | Planned: | 31.49% | Planned: | 44.45% | Planned: | 58.9% | Planned: | 58.9% | Planned: | 100% | No. of Persons: | 17 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | Completed as per Program of Works
Asuncion | Buan | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 552783.35 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 374
Asuncion | Buan | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 174071.4769 | Actual: | 31.49% | Actual: | 44.45% | Actual: | 58.9% | Actual: | 58.9% | Actual: | 100%
Asuncion | Buan | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Asuncion | Buan | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed: | 2020-12-31
Asuncion | Buan | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started: | 2020-01-02
Asuncion | Buan | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 045 - Tagaytay - Buan |  | GENERAL FUND CY 2020 | Maintenance | 4.92 | km | CBRMC | Project Cost: | 174230.1288 | Target Completion Date: |  | Program: | 174230.1288 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Purchase Request # 19125346 (On process) | Purchase Request # 19125346 (On process) | Purchase Request # 19125346 (On process) | Purchase Request # 19125346 (On process) | Purchase Request # 19125346 (On process) | Procurement on process
Asuncion | Buan | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 174230.1288 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
Asuncion | Buan | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
Asuncion | Buan | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Asuncion | Buan | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: |  | Date completed:
Asuncion | Buan | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started:
New Corella | Limbann-Sto. Niño | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 049 - Limbaan - Sto. Niño |  | GENERAL FUND CY 2020 | Maintenance | 3.19 | km | MBA | Project Cost: | 322857.58 | Target Completion Date: | 2021-02-01 23:59 | Program: | 322857.58 | Planned: | 47.46% | Planned: | 47.46% | Planned: | 58.18% | Planned: | 58.18% | Planned: | 100% | No. of Persons: | 14 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | Completed as per Program of Works
New Corella | Limbann-Sto. Niño | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-02-28 23:59 | Allotment: | 322857.58 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 210
New Corella | Limbann-Sto. Niño | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 153228.2075 | Actual: | 47.46% | Actual: | 47.46% | Actual: | 58.18% | Actual: | 58.18% | Actual: | 100%
New Corella | Limbann-Sto. Niño | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
New Corella | Limbann-Sto. Niño | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed: | 2020-12-31
New Corella | Limbann-Sto. Niño | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started: | 2020-02-03
New Corella | Limbann-Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 049 - Limbaan - Sto. Niño |  | GENERAL FUND CY 2020 | Maintenance | 3.19 | km | CBRMC | Project Cost: | 127140.9048 | Target Completion Date: |  | Program: | 127140.9048 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Procurement on process | Purchase Request # 20010072 (On process) | Purchase Request # 20010072 (On process) | Purchase Request # 20010072 (On process) | Purchase Request # 20010072 (On process) | Procurement on process
New Corella | Limbann-Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 127140.9048 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
New Corella | Limbann-Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
New Corella | Limbann-Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
New Corella | Limbann-Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: |  | Date completed:
New Corella | Limbann-Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started:
New Corella | Monte Carlo | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 050 - Jct. Monte Carlo - Upper Cabaywa - Canatan |  | GENERAL FUND CY 2020 | Maintenance | 4.61 | km | MBA | Project Cost: | 482840.52 | Target Completion Date: | 2020-12-31 23:59 | Program: | 482840.52 | Planned: | 16.47% | Planned: | 34.82% | Planned: | 54.91% | Planned: | 54.91% | Planned: | 100% | No. of Persons: | 17 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | Completed as per Program of Works
New Corella | Monte Carlo | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 482840.52 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 374
New Corella | Monte Carlo | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 79523.8336 | Actual: | 16.47% | Actual: | 34.82% | Actual: | 54.91% | Actual: | 54.91% | Actual: | 100%
New Corella | Monte Carlo | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
New Corella | Monte Carlo | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed: | 2020-12-31
New Corella | Monte Carlo | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started: | 2020-01-02
New Corella | Monte Carlo | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 050 - Jct. Monte Carlo - Upper Cabaywa - Canatan |  | GENERAL FUND CY 2020 | Maintenance | 4.61 | km | CBRMC | Project Cost: | 197774.7408 | Target Completion Date: |  | Program: | 197774.7408 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Procurement on process | Purchase Request # 20010074 (On process) | Purchase Request # 20010074 (On process) | Purchase Request # 20010074 (On process) | Purchase Request # 20010074 (On process) | Procurement on process
New Corella | Monte Carlo | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 197774.7408 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
New Corella | Monte Carlo | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
New Corella | Monte Carlo | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
New Corella | Monte Carlo | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: |  | Date completed:
New Corella | Monte Carlo | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started:
New Corella | Del Pilar | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 051 - Del Pilar - Jct. Silangan |  | GENERAL FUND CY 2020 | Maintenance | 4.17 | km | MBA | Project Cost: | 467261.55 | Target Completion Date: | 2020-12-31 23:59 | Program: | 467261.55 | Planned: | 8.31% | Planned: | 20.3% | Planned: | 34.05% | Planned: | 34.05% | Planned: | 100% | No. of Persons: |  | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | Completed as per Program of Works
New Corella | Del Pilar | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 467261.55 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
New Corella | Del Pilar | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 38829.4348 | Actual: | 8.31% | Actual: | 20.3% | Actual: | 34.05% | Actual: | 34.05% | Actual: | 100%
New Corella | Del Pilar | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
New Corella | Del Pilar | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed: | 2020-12-31
New Corella | Del Pilar | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started: | 2020-01-02
New Corella | Del Pilar | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 051 - Del Pilar - Jct. Silangan |  | GENERAL FUND CY 2020 | Maintenance | 4.17 | km | CBRMC | Project Cost: | 129495.366 | Target Completion Date: |  | Program: | 129495.366 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Procurement on process | Purchase Request # 20010093 (On process) | Purchase Request # 20010093 (On process) | Purchase Request # 20010093 (On process) | Purchase Request # 20010093 (On process) | Procurement on process
New Corella | Del Pilar | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 129495.366 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
New Corella | Del Pilar | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
New Corella | Del Pilar | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
New Corella | Del Pilar | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: |  | Date completed:
New Corella | Del Pilar | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started:
New Corella | New Sambog | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 052 - New Corella - New Sambog - Silangan |  | GENERAL FUND CY 2020 | Maintenance | 5.1 | km | MBA | Project Cost: | 519781.9 | Target Completion Date: | 2020-12-31 23:59 | Program: | 519781.9 | Planned: | 13.05% | Planned: | 24.17% | Planned: | 36.87% | Planned: | 36.87% | Planned: | 100% | No. of Persons: | 17 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | Completed as per Program of Works
New Corella | New Sambog | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 519781.9 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 374
New Corella | New Sambog | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 67831.538 | Actual: | 13.05% | Actual: | 24.17% | Actual: | 36.87% | Actual: | 36.87% | Actual: | 100%
New Corella | New Sambog | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
New Corella | New Sambog | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed: | 2020-12-31
New Corella | New Sambog | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started: | 2020-01-02
New Corella | New Sambog | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 052 - New Corella - New Sambog - Silangan |  | GENERAL FUND CY 2020 | Maintenance | 5.1 | km | CBRMC | Project Cost: | 148331.0556 | Target Completion Date: |  | Program: | 148331.0556 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Purchase Request # 20010095 (On process) | Purchase Request # 20010095 (On process) | Purchase Request # 20010095 (On process) | Purchase Request # 20010095 (On process) | Purchase Request # 20010095 (On process) | Procurement on process
New Corella | New Sambog | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 148331.0556 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
New Corella | New Sambog | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
New Corella | New Sambog | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
New Corella | New Sambog | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: |  | Date completed:
New Corella | New Sambog | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started:
New Corella | Poblacion | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 053 - Pob. New Corella - Prk. 10 Pob. |  | GENERAL FUND CY 2020 | Maintenance | 1.3 | km | MBA | Project Cost: | 49339.52 | Target Completion Date: | 2020-12-31 23:59 | Program: | 49339.52 | Planned: | 20.07% | Planned: | 34.13% | Planned: | 65.18% | Planned: | 65.18% | Planned: | 100% | No. of Persons: | 17 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | Completed as per Program of Works
New Corella | Poblacion | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 49339.52 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 374
New Corella | Poblacion | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 9902.4417 | Actual: | 20.07% | Actual: | 34.13% | Actual: | 65.18% | Actual: | 65.18% | Actual: | 100%
New Corella | Poblacion | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
New Corella | Poblacion | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed: | 2020-12-31
New Corella | Poblacion | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started: | 2020-01-02
New Corella | Poblacion | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 053 - Pob. New Corella - Prk. 10 Pob. |  | GENERAL FUND CY 2020 | Maintenance | 1.3 | km | CBRMC | Project Cost: | 21190.1508 | Target Completion Date: |  | Program: | 21190.1508 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Awarded to Carcor Motor Driver's Association | Awarded to Carcor Motor Driver's Association | Awarded to Carcor Motor Driver's Association | Awarded to Carcor Motor Driver's Association | Awarded to Carcor Motor Driver's Association | Procurement on process
New Corella | Poblacion | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 21190.1508 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
New Corella | Poblacion | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
New Corella | Poblacion | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
New Corella | Poblacion | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: |  | Date completed:
New Corella | Poblacion | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started:
New Corella | New Sambog | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 054 - Prk. 7 Pob. - Jct. New Sambog |  | GENERAL FUND CY 2020 | Maintenance | 2.54 | km | MBA | Project Cost: | 284614.93 | Target Completion Date: | 2020-12-31 23:59 | Program: | 284614.93 | Planned: | 10.38% | Planned: | 31.19% | Planned: | 54.92% | Planned: | 54.92% | Planned: | 100% | No. of Persons: | 17 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | Completed as per Program of Works
New Corella | New Sambog | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2142-01-29 23:59 | Allotment: | 284614.93 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 374
New Corella | New Sambog | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 29543.0297 | Actual: | 10.38% | Actual: | 31.19% | Actual: | 54.92% | Actual: | 54.92% | Actual: | 100%
New Corella | New Sambog | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: | 365 | No. of days extended: | 44196 |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
New Corella | New Sambog | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed: | 2020-12-31
New Corella | New Sambog | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started: | 2020-01-02
New Corella | New Sambog | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 054 - Prk. 7 Pob. - Jct. New Sambog |  | GENERAL FUND CY 2020 | Maintenance | 2.54 | km | CBRMC | Project Cost: | 113014.1376 | Target Completion Date: |  | Program: | 113014.1376 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Awarded to Carcor Motor Driver's Association | Awarded to Carcor Motor Driver's Association | Awarded to Carcor Motor Driver's Association | Awarded to Carcor Motor Driver's Association | Awarded to Carcor Motor Driver's Association | Procurement on process
New Corella | New Sambog | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 113014.1376 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
New Corella | New Sambog | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
New Corella | New Sambog | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
New Corella | New Sambog | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: |  | Date completed:
New Corella | New Sambog | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started:
New Corella | Sta. Fe-Del Monte | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 056 - Sta. Fe - Del Monte |  | GENERAL FUND CY 2020 | Maintenance | 3.34 | km | MBA | Project Cost: | 169019.48 | Target Completion Date: | 2020-12-31 23:59 | Program: | 169019.48 | Planned: | 17.46% | Planned: | 35.41% | Planned: | 58.28% | Planned: | 58.28% | Planned: | 100% | No. of Persons: | 17 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | Completed as per Program of Works
New Corella | Sta. Fe-Del Monte | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 169019.48 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 374
New Corella | Sta. Fe-Del Monte | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 29510.8012 | Actual: | 17.46% | Actual: | 35.41% | Actual: | 58.28% | Actual: | 58.28% | Actual: | 100%
New Corella | Sta. Fe-Del Monte | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
New Corella | Sta. Fe-Del Monte | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed: | 2020-12-31
New Corella | Sta. Fe-Del Monte | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started: | 2020-01-02
New Corella | Sta. Fe-Del Monte | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 056 - Sta. Fe - Del Monte |  | GENERAL FUND CY 2020 | Maintenance | 3.34 | km | CBRMC | Project Cost: | 75342.7584 | Target Completion Date: |  | Program: | 75342.7584 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Purchase Request # 20010160 (On process) | Purchase Request # 20010160 (On process) | Purchase Request # 20010160 (On process) | Purchase Request # 20010160 (On process) | Purchase Request # 20010160 (On process) | Procurement on process
New Corella | Sta. Fe-Del Monte | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 75342.7584 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
New Corella | Sta. Fe-Del Monte | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
New Corella | Sta. Fe-Del Monte | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
New Corella | Sta. Fe-Del Monte | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: |  | Date completed:
New Corella | Sta. Fe-Del Monte | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started:
New Corella | New Bohol | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 058 - New Corella - New Bohol |  | GENERAL FUND CY 2020 | Maintenance | 11.54 | km | MBA | Project Cost: | 521354.26 | Target Completion Date: | 2020-12-31 23:59 | Program: | 521354.26 | Planned: | 22.18% | Planned: | 39.46% | Planned: | 52.23% | Planned: | 52.23% | Planned: | 100% | No. of Persons: | 17 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | Completed as per Program of Works
New Corella | New Bohol | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 521354.26 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 374
New Corella | New Bohol | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 115636.3749 | Actual: | 22.18% | Actual: | 39.46% | Actual: | 52.23% | Actual: | 52.23% | Actual: | 100%
New Corella | New Bohol | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
New Corella | New Bohol | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed: | 2020-12-31
New Corella | New Bohol | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started: | 2020-01-02
New Corella | New Bohol | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 058 - New Corella - New Bohol |  | GENERAL FUND CY 2020 | Maintenance | 11.54 | km | CBRMC | Project Cost: | 221319.3528 | Target Completion Date: |  | Program: | 221319.3528 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Awarded to Carcor Motor Driver's Association | Awarded to Carcor Motor Driver's Association | Awarded to Carcor Motor Driver's Association | Awarded to Carcor Motor Driver's Association | Awarded to Carcor Motor Driver's Association | For implementation
New Corella | New Bohol | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 221319.3528 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
New Corella | New Bohol | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
New Corella | New Bohol | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
New Corella | New Bohol | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: |  | Date completed:
New Corella | New Bohol | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started:
New Corella | Carcor | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 059 - Jct. Carcor - Prk. 9 Bagsak |  | GENERAL FUND CY 2020 | Maintenance | 2.5 | km | MBA | Project Cost: | 234950.09 | Target Completion Date: | 2020-12-31 23:59 | Program: | 234950.09 | Planned: | 21.94% | Planned: | 37.99% | Planned: | 57.68% | Planned: | 57.68% | Planned: | 100% | No. of Persons: | 17 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | Completed as per Program of Works
New Corella | Carcor | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 234950.09 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 374
New Corella | Carcor | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 51548.0497 | Actual: | 21.94% | Actual: | 37.99% | Actual: | 57.68% | Actual: | 57.68% | Actual: | 100%
New Corella | Carcor | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
New Corella | Carcor | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed: | 2020-12-31
New Corella | Carcor | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started: | 2020-01-02
New Corella | Carcor | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 059 - Jct. Carcor - Prk. 9 Bagsak |  | GENERAL FUND CY 2020 | Maintenance | 2.5 | km | CBRMC | Project Cost: | 72988.2972 | Target Completion Date: |  | Program: | 72988.2972 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Awarded to Carcor Motor Driver's Association | Awarded to Carcor Motor Driver's Association | Awarded to Carcor Motor Driver's Association | Awarded to Carcor Motor Driver's Association | Awarded to Carcor Motor Driver's Association | For implementation Carcor Motor Driver's Association
New Corella | Carcor | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 72988.2972 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
New Corella | Carcor | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
New Corella | Carcor | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
New Corella | Carcor | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: |  | Date completed:
New Corella | Carcor | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started:
New Corella | Carcor | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 060 - Carcor - Jct. Kauswagan |  | GENERAL FUND CY 2020 | Maintenance | 4.32 | km | MBA | Project Cost: | 405993.76 | Target Completion Date: | 2020-12-31 23:59 | Program: | 405993.76 | Planned: | 40.17% | Planned: | 51.04% | Planned: | 59.86% | Planned: | 59.86% | Planned: | 100% | No. of Persons: | 17 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | Completed as per Program of Works
New Corella | Carcor | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 405993.76 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 374
New Corella | Carcor | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 163087.6934 | Actual: | 40.17% | Actual: | 51.04% | Actual: | 59.86% | Actual: | 59.86% | Actual: | 100%
New Corella | Carcor | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
New Corella | Carcor | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed: | 2020-12-31
New Corella | Carcor | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started: | 2020-01-02
New Corella | Carcor | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 060 - Carcor - Jct. Kauswagan |  | GENERAL FUND CY 2020 | Maintenance | 4.32 | km | CBRMC | Project Cost: | 101241.8316 | Target Completion Date: |  | Program: | 101241.8316 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Awarded to Carcor Motor Driver's Association | Awarded to Carcor Motor Driver's Association | Awarded to Carcor Motor Driver's Association | Awarded to Carcor Motor Driver's Association | Awarded to Carcor Motor Driver's Association | For implementation Carcor Motor Driver's Association
New Corella | Carcor | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: | Fabian | Revised Completion Date: |  | Allotment: | 101241.8316 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
New Corella | Carcor | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
New Corella | Carcor | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
New Corella | Carcor | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: |  | Date completed:
New Corella | Carcor | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started:
New Corella | Del Pilar | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 061 - Del Pilar - Prk. 9 Bagsak - San Jose |  | GENERAL FUND CY 2020 | Maintenance |  | km | MBA | Project Cost: | 505304.267 | Target Completion Date: | 2021-01-14 23:59 | Program: | 505304.267 | Planned: | 49.18% | Planned: | 49.18% | Planned: | 54.78% | Planned: | 54.78% | Planned: | 100% | No. of Persons: | 14 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | Completed as per Program of Works
New Corella | Del Pilar | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-02-10 23:59 | Allotment: | 505304.267 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 210
New Corella | Del Pilar | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 248508.6385 | Actual: | 49.18% | Actual: | 49.18% | Actual: | 54.78% | Actual: | 54.78% | Actual: | 100%
New Corella | Del Pilar | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
New Corella | Del Pilar | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed: | 2020-12-31
New Corella | Del Pilar | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started: | 2020-01-16
New Corella | Del Pilar | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 061 - Del Pilar - Prk. 9 Bagsak - San Jose |  | GENERAL FUND CY 2020 | Maintenance |  | km | CBRMC | Project Cost: | 251927.3484 | Target Completion Date: |  | Program: | 251927.3484 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Purchase Request # 20010264 (On process) | Purchase Request # 20010264 (On process) | Purchase Request # 20010264 (On process) | Purchase Request # 20010264 (On process) | Purchase Request # 20010264 (On process) | Procurement on process
New Corella | Del Pilar | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 251927.3484 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
New Corella | Del Pilar | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
New Corella | Del Pilar | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
New Corella | Del Pilar | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: |  | Date completed:
New Corella | Del Pilar | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started:
New Corella | Del Pilar | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 062 - Del Pilar - El Unido |  | GENERAL FUND CY 2020 | Maintenance | 1.32 | km | MBA | Project Cost: | 124053.65 | Target Completion Date: | 2020-12-31 23:59 | Program: | 124053.65 | Planned: | 16.17% | Planned: | 16.17% | Planned: | 40.91% | Planned: | 40.91% | Planned: | 100% | No. of Persons: | 17 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | Completed as per Program of Works
New Corella | Del Pilar | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 124053.65 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 374
New Corella | Del Pilar | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 20059.4752 | Actual: | 16.17% | Actual: | 16.17% | Actual: | 40.91% | Actual: | 40.91% | Actual: | 100%
New Corella | Del Pilar | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
New Corella | Del Pilar | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed: | 2020-12-31
New Corella | Del Pilar | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started: | 2020-01-02
New Corella | Del Pilar | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 062 - Del Pilar - El Unido |  | GENERAL FUND CY 2020 | Maintenance | 1.32 | km | CBRMC | Project Cost: | 40025.8404 | Target Completion Date: |  | Program: | 40025.8404 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Purchase Request # 20010265 (On process) | Purchase Request # 20010265 (On process) | Purchase Request # 20010265 (On process) | Purchase Request # 20010265 (On process) | Purchase Request # 20010265 (On process) | Procurement on process
New Corella | Del Pilar | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 40025.8404 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
New Corella | Del Pilar | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
New Corella | Del Pilar | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
New Corella | Del Pilar | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: |  | Date completed:
New Corella | Del Pilar | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started:
New Corella | Del Pilar | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 063 - San Juan - New Talisay |  | GENERAL FUND CY 2020 | Maintenance | 5.13 | km | MBA | Project Cost: | 572832.52 | Target Completion Date: | 2020-12-31 23:59 | Program: | 572832.52 | Planned: | 26.84% | Planned: | 26.84% | Planned: | 39.5% | Planned: | 39.5% | Planned: | 100% | No. of Persons: | 17 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | Completed as per Program of Works
New Corella | Del Pilar | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 572832.52 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 374
New Corella | Del Pilar | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 153748.2484 | Actual: | 26.84% | Actual: | 26.84% | Actual: | 39.5% | Actual: | 39.5% | Actual: | 100%
New Corella | Del Pilar | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
New Corella | Del Pilar | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed: | 2020-12-31
New Corella | Del Pilar | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started: | 2020-01-02
New Corella | Del Pilar | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 063 - San Juan - New Talisay |  | GENERAL FUND CY 2020 | Maintenance | 5.13 | km | CBRMC | Project Cost: | 131849.8272 | Target Completion Date: |  | Program: | 131849.8272 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Awarded to Mahayahay Integrated Farmers Association | Awarded to Mahayahay Integrated Farmers Association | Awarded to Mahayahay Integrated Farmers Association | Awarded to Mahayahay Integrated Farmers Association | Awarded to Mahayahay Integrated Farmers Association | Awarded to Mahayahay Integrated Farmers Association
New Corella | Del Pilar | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 131849.8272 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
New Corella | Del Pilar | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
New Corella | Del Pilar | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
New Corella | Del Pilar | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: |  | Date completed:
New Corella | Del Pilar | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started:
New Corella | Del Pilar | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 064 - San Juan - Kauswagan - New Cortez |  | GENERAL FUND CY 2020 | Maintenance | 3.22 | km | MBA | Project Cost: | 128969.53 | Target Completion Date: | 2021-01-14 23:59 | Program: | 128969.53 | Planned: | 41.14% | Planned: | 41.14% | Planned: | 50.44% | Planned: | 50.44% | Planned: | 100% | No. of Persons: | 14 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | Completed as per Program of Works
New Corella | Del Pilar | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-02-10 23:59 | Allotment: | 128969.53 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 210
New Corella | Del Pilar | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 53058.0646 | Actual: | 41.14% | Actual: | 41.14% | Actual: | 50.44% | Actual: | 50.44% | Actual: | 100%
New Corella | Del Pilar | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: |  | Slippage: |  | Slippage: |  | Slippage: |  | Slippage:
New Corella | Del Pilar | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed: | 2020-12-31
New Corella | Del Pilar | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started: | 2020-01-16
New Corella | Del Pilar | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 064 - San Juan - Kauswagan - New Cortez |  | GENERAL FUND CY 2020 | Maintenance | 3.22 | km | CBRMC | Project Cost: | 68279.3748 | Target Completion Date: |  | Program: | 68279.3748 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Procurement on process | Procurement on process | Procurement on process | Procurement on process | Procurement on process | Procurement on process
New Corella | Del Pilar | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 68279.3748 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
New Corella | Del Pilar | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
New Corella | Del Pilar | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
New Corella | Del Pilar | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: |  | Date completed:
New Corella | Del Pilar | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started:
New Corella | New Bohol | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 065 - New Bohol - Jct. El Unido |  | GENERAL FUND CY 2020 | Maintenance | 2.12 | km | MBA | Project Cost: | 177260.81 | Target Completion Date: | 2021-01-14 23:59 | Program: | 177260.81 | Planned: | 42.46% | Planned: | 42.46% | Planned: | 52.67% | Planned: | 52.67% | Planned: | 100% | No. of Persons: | 14 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | Completed as per Program of Works
New Corella | New Bohol | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-02-10 23:59 | Allotment: | 177260.81 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 210
New Corella | New Bohol | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 74910.4183 | Actual: | 42.26% | Actual: | 42.26% | Actual: | 52.67% | Actual: | 52.67% | Actual: | 100%
New Corella | New Bohol | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | -0.2% | Slippage: | -0.2% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
New Corella | New Bohol | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed: | 2020-12-31
New Corella | New Bohol | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started: | 2020-01-16
New Corella | New Bohol | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 065 - New Bohol - Jct. El Unido |  | GENERAL FUND CY 2020 | Maintenance | 2.12 | km | CBRMC | Project Cost: | 65924.9136 | Target Completion Date: |  | Program: | 65924.9136 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Purchase Request # 20010275 (On process) | Purchase Request # 20010275 (On process) | Purchase Request # 20010275 (On process) | Purchase Request # 20010275 (On process) | Purchase Request # 20010275 (On process) | Procurement on process
New Corella | New Bohol | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 65924.9136 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
New Corella | New Bohol | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
New Corella | New Bohol | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
New Corella | New Bohol | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: |  | Date completed:
New Corella | New Bohol | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started:
New Corella | Mesaoy | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 066 - New Corella - El Unido - Jct. Mesaoy |  | GENERAL FUND CY 2020 | Maintenance | 8.63 | km | MBA | Project Cost: | 792432.45 | Target Completion Date: | 2021-01-14 23:59 | Program: | 792432.45 | Planned: | 53.98% | Planned: | 53.98% | Planned: | 63.47% | Planned: | 63.47% | Planned: | 100% | No. of Persons: | 14 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | Completed as per Program of Works
New Corella | Mesaoy | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-02-10 23:59 | Allotment: | 792432.45 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 210
New Corella | Mesaoy | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 427755.0365 | Actual: | 53.98% | Actual: | 53.98% | Actual: | 63.47% | Actual: | 63.47% | Actual: | 100%
New Corella | Mesaoy | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
New Corella | Mesaoy | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed: | 2020-12-31
New Corella | Mesaoy | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started: | 2020-01-16
New Corella | Mesaoy | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 066 - New Corella - El Unido - Jct. Mesaoy |  | GENERAL FUND CY 2020 | Maintenance | 8.63 | km | CBRMC | Project Cost: | 249572.8872 | Target Completion Date: |  | Program: | 249572.8872 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Purchase Request # 20010291 (On process) | Purchase Request # 20010291 (On process) | Purchase Request # 20010291 (On process) | Purchase Request # 20010291 (On process) | Purchase Request # 20010291 (On process) | Procurement on process
New Corella | Mesaoy | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 249572.8872 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
New Corella | Mesaoy | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
New Corella | Mesaoy | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
New Corella | Mesaoy | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: |  | Date completed:
New Corella | Mesaoy | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started:
New Corella | Mesaoy | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 067 - Mesaoy - Dasing |  | GENERAL FUND CY 2020 | Maintenance | 1.39 | km | MBA | Project Cost: | 130632.25 | Target Completion Date: | 2021-01-14 23:59 | Program: | 130632.25 | Planned: | 48.79% | Planned: | 48.79% | Planned: | 57.7% | Planned: | 57.7% | Planned: | 100% | No. of Persons: | 14 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | Completed as per Program of Works
New Corella | Mesaoy | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-02-10 23:59 | Allotment: | 130632.25 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 210
New Corella | Mesaoy | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 63735.4748 | Actual: | 48.79% | Actual: | 48.79% | Actual: | 57.7% | Actual: | 57.7% | Actual: | 100%
New Corella | Mesaoy | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
New Corella | Mesaoy | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed: | 2020-12-31
New Corella | Mesaoy | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started: | 2020-01-16
New Corella | Mesaoy | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 067 - Mesaoy - Dasing |  | GENERAL FUND CY 2020 | Maintenance | 1.39 | km | CBRMC | Project Cost: | 54152.6076 | Target Completion Date: |  | Program: | 54152.6076 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Purchase Request # 20010294 (On process) | Purchase Request # 20010294 (On process) | Purchase Request # 20010294 (On process) | Purchase Request # 20010294 (On process) | Purchase Request # 20010294 (On process) | Procurement on process
New Corella | Mesaoy | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 54152.6076 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
New Corella | Mesaoy | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
New Corella | Mesaoy | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
New Corella | Mesaoy | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: |  | Date completed:
New Corella | Mesaoy | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started:
New Corella | Del Pilar | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 068 - Jct. San Juan - Jct. Mesaoy |  | GENERAL FUND CY 2020 | Maintenance | 1.82 | km | MBA | Project Cost: | 203936.68 | Target Completion Date: | 2020-12-31 23:59 | Program: | 203936.68 | Planned: | 12.12% | Planned: | 12.12% | Planned: | 35.37% | Planned: | 35.37% | Planned: | 100% | No. of Persons: | 17 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | Completed as per Program of Works
New Corella | Del Pilar | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 203936.68 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 374
New Corella | Del Pilar | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 24717.1256 | Actual: | 12.12% | Actual: | 12.12% | Actual: | 35.37% | Actual: | 35.37% | Actual: | 100%
New Corella | Del Pilar | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
New Corella | Del Pilar | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed: | 2020-12-31
New Corella | Del Pilar | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started: | 2020-01-02
New Corella | Del Pilar | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 068 - Jct. San Juan - Jct. Mesaoy |  | GENERAL FUND CY 2020 | Maintenance | 1.82 | km | CBRMC | Project Cost: | 68279.3748 | Target Completion Date: |  | Program: | 68279.3748 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Awarded to Mahayahay Integrated Farmers Association | Awarded to Mahayahay Integrated Farmers Association | Awarded to Mahayahay Integrated Farmers Association | Awarded to Mahayahay Integrated Farmers Association | Awarded to Mahayahay Integrated Farmers Association | Procurement on process
New Corella | Del Pilar | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 68279.3748 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
New Corella | Del Pilar | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
New Corella | Del Pilar | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
New Corella | Del Pilar | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: |  | Date completed:
New Corella | Del Pilar | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started:
New Corella | Mesaoy-New Bohol | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 070 - Mesaoy - New Bohol |  | GENERAL FUND CY 2020 | Maintenance | 5.36 | km | MBA | Project Cost: | 665667.84 | Target Completion Date: | 2021-01-14 23:59 | Program: | 665667.84 | Planned: | 41.99% | Planned: | 41.99% | Planned: | 46.74% | Planned: | 46.74% | Planned: | 100% | No. of Persons: | 14 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | Completed as per Program of Works
New Corella | Mesaoy-New Bohol | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-02-10 23:59 | Allotment: | 665667.84 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 210
New Corella | Mesaoy-New Bohol | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 279513.926 | Actual: | 41.99% | Actual: | 41.99% | Actual: | 46.74% | Actual: | 46.74% | Actual: | 100%
New Corella | Mesaoy-New Bohol | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
New Corella | Mesaoy-New Bohol | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed: | 2020-12-31
New Corella | Mesaoy-New Bohol | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started: | 2020-01-16
New Corella | Mesaoy-New Bohol | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 070 - Mesaoy - New Bohol |  | GENERAL FUND CY 2020 | Maintenance | 5.36 | km | CBRMC | Project Cost: | 261345.1932 | Target Completion Date: |  | Program: | 261345.1932 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Purchase Request # 20010298 (On process) | Purchase Request # 20010298 (On process) | Purchase Request # 20010298 (On process) | Purchase Request # 20010298 (On process) | Purchase Request # 20010298 (On process) | Procurement on process
New Corella | Mesaoy-New Bohol | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 261345.1932 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
New Corella | Mesaoy-New Bohol | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
New Corella | Mesaoy-New Bohol | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
New Corella | Mesaoy-New Bohol | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: |  | Date completed:
New Corella | Mesaoy-New Bohol | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started:
Asuncion | Napungas | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 147 - Prk. 1, Maunlom-Prk. 6 Maunlom Road |  | GENERAL FUND CY 2020 | Maintenance | 3.56 | km | MBA | Project Cost: | 115812.32 | Target Completion Date: | 2021-02-15 23:59 | Program: | 115812.32 | Planned: | 38.9% | Planned: | 38.9% | Planned: | 53.76% | Planned: | 53.76% | Planned: | 100% | No. of Persons: | 14 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | Completed as per Program of Works
Asuncion | Napungas | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-03-14 23:59 | Allotment: | 115812.32 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 210
Asuncion | Napungas | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 45050.9925 | Actual: | 38.9% | Actual: | 38.9% | Actual: | 53.76% | Actual: | 53.76% | Actual: | 100%
Asuncion | Napungas | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Asuncion | Napungas | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed: | 2020-12-31
Asuncion | Napungas | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started: | 2020-02-17
Asuncion | Napungas | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 147 - Prk. 1, Maunlom-Prk. 6 Maunlom Road |  | GENERAL FUND CY 2020 | Maintenance | 3.56 | km | CBRMC | Project Cost: | 65924.9136 | Target Completion Date: |  | Program: | 65924.9136 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Purchase Request # 20010302 (On process) | Purchase Request # 20010302 (On process) | Purchase Request # 20010302 (On process) | Purchase Request # 20010302 (On process) | Purchase Request # 20010302 (On process) | Procurement on process
Asuncion | Napungas | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 65924.9136 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
Asuncion | Napungas | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
Asuncion | Napungas | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Asuncion | Napungas | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: |  | Date completed:
Asuncion | Napungas | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started:
Asuncion | Binancian | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 149 - New Visayas - Binancian |  | GENERAL FUND CY 2020 | Maintenance | 7.77 | km | MBA | Project Cost: | 196599.01 | Target Completion Date: | 2020-12-31 23:59 | Program: | 196599.01 | Planned: | 6.94% | Planned: | 6.94% | Planned: | 52.21% | Planned: | 52.21% | Planned: | 100% | No. of Persons: | 17 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | Completed as per Program of Works
Asuncion | Binancian | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 196599.01 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 374
Asuncion | Binancian | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 13643.9713 | Actual: | 6.94% | Actual: | 6.94% | Actual: | 52.21% | Actual: | 52.21% | Actual: | 100%
Asuncion | Binancian | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Asuncion | Binancian | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed: | 2020-12-31
Asuncion | Binancian | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started: | 2020-01-02
Asuncion | Binancian | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 149 - New Visayas - Binancian |  | GENERAL FUND CY 2020 | Maintenance | 7.77 | km | CBRMC | Project Cost: | 134204.2884 | Target Completion Date: |  | Program: | 134204.2884 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Purchase Request # 20010305 (On process) | Purchase Request # 20010305 (On process) | Purchase Request # 20010305 (On process) | Purchase Request # 20010305 (On process) | Purchase Request # 20010305 (On process) | Procurement on process
Asuncion | Binancian | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 134204.2884 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
Asuncion | Binancian | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
Asuncion | Binancian | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Asuncion | Binancian | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: |  | Date completed:
Asuncion | Binancian | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started:
San Isidro | Datu Balong-Mamalian | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 150 - Datu Balong - Prk. Mamalian |  | GENERAL FUND CY 2020 | Maintenance | 3.46 | km | MBA | Project Cost: | 106305.88 | Target Completion Date: | 2020-12-31 23:59 | Program: | 106305.88 | Planned: | 12.74% | Planned: | 12.74% | Planned: | 54.05% | Planned: | 54.05% | Planned: | 100% | No. of Persons: | 17 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | Completed as per Program of Works
San Isidro | Datu Balong-Mamalian | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 106305.88 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 374
San Isidro | Datu Balong-Mamalian | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 13543.3691 | Actual: | 12.74% | Actual: | 12.74% | Actual: | 54.05% | Actual: | 54.05% | Actual: | 100%
San Isidro | Datu Balong-Mamalian | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
San Isidro | Datu Balong-Mamalian | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | 2 | 2020-01-02 | Date completed: | 2020-12-31
San Isidro | Datu Balong-Mamalian | 1st Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Administration | I. PROJECTS UNDER THE CONTINUING APPROPRIATION | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started: | 2020-01-02
San Isidro | Datu Balong-Mamalian | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | ROAD ID 150 - Datu Balong - Prk. Mamalian |  | GENERAL FUND CY 2020 | Maintenance | 3.46 | km | CBRMC | Project Cost: | 61215.9912 | Target Completion Date: |  | Program: | 61215.9912 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Purchase Request # 20010306 (On process) | Purchase Request # 20010306 (On process) | Purchase Request # 20010306 (On process) | Purchase Request # 20010306 (On process) | Purchase Request # 20010306 (On process) | Procurement on process
San Isidro | Datu Balong-Mamalian | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 61215.9912 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
San Isidro | Datu Balong-Mamalian | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
San Isidro | Datu Balong-Mamalian | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
San Isidro | Datu Balong-Mamalian | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Allotment Released: |  | Date completed:
San Isidro | Datu Balong-Mamalian | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | REPAIR/MAINTENANCE OF PROVINCIAL ROADS & BRIDGES LS - P21,409,737.00 (14.084KM) | [7 empty] | Date Started:
Asuncion | Sta. Felomina | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | ROAD ID 008 - Sta. Felomina - San Roque |  | 20% Development Fund CY 2020 | Road Rehabilitaion | 7.68 | km | Admin | Project Cost: | 2304000 | Target Completion Date: |  | Program: | 2304000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Post qualification on process | Post qualification on process | Post qualification on process | Post qualification on process | Post qualification on process | Post qualification on process
Asuncion | Sta. Felomina | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 2304000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
Asuncion | Sta. Felomina | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
Asuncion | Sta. Felomina | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Asuncion | Sta. Felomina | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Asuncion | Sta. Felomina | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Date Started:
Talaingod | Sto. Niño-Palma Gil | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | ROAD ID 019 - Sto. Niño - Palma Gil - Sitio Opao |  | 20% Development Fund CY 2020 | Road Rehabilitaion | 5.99 | km | Admin | Project Cost: | 1797000 | Target Completion Date: |  | Program: | 1797000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | POW on process | POW on process | POW on process | POW on process | POW on process | POW on process
Talaingod | Sto. Niño-Palma Gil | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 1797000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
Talaingod | Sto. Niño-Palma Gil | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
Talaingod | Sto. Niño-Palma Gil | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Talaingod | Sto. Niño-Palma Gil | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Talaingod | Sto. Niño-Palma Gil | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Date Started:
Talaingod | Daligdigon-Paiton | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | ROAD ID 023 - Sto. Niño - Daligdigon - Paiton |  | 20% Development Fund CY 2020 | Road Rehabilitaion | 11.6 | km | Admin | Project Cost: | 3480000 | Target Completion Date: |  | Program: | 3480000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | POW on process | POW on process | POW on process | POW on process | POW on process | POW on process
Talaingod | Daligdigon-Paiton | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 3480000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
Talaingod | Daligdigon-Paiton | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
Talaingod | Daligdigon-Paiton | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Talaingod | Daligdigon-Paiton | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Talaingod | Daligdigon-Paiton | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Date Started:
Talaingod | Paiton | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | ROAD ID 024 - Jct. Paiton - Mibolo |  | 20% Development Fund CY 2020 | Road Rehabilitaion | 23.9 | km | Admin | Project Cost: | 7170000 | Target Completion Date: |  | Program: | 7170000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | POW on process | POW on process | POW on process | POW on process | POW on process | POW on process
Talaingod | Paiton | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 7170000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
Talaingod | Paiton | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
Talaingod | Paiton | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Talaingod | Paiton | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Talaingod | Paiton | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Date Started:
Kapalong | Florida | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | ROAD ID 024 - Florida - Suaon - Jct. Gupitan |  | 20% Development Fund CY 2020 | Road Rehabilitaion | 15.57 | km | Admin | Project Cost: | 4671000 | Target Completion Date: |  | Program: | 4671000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | PO on process - Royal Summit | PO on process - Royal Summit | PO on process - Royal Summit | PO on process - Royal Summit | PO on process - Royal Summit | PO on process - Royal Summit
Kapalong | Florida | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 4671000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
Kapalong | Florida | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
Kapalong | Florida | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Kapalong | Florida | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Kapalong | Florida | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Date Started:
San Isidro | Datu Balong | 1st Eng'g. Dist. | On-going | 2020-12-01 |  | 2020 | Administration |  | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | ROAD ID 040 - Datu Balong - Pinamuno |  | 20% Development Fund CY 2020 | Road Rehabilitaion | 2.74 | km | Admin | Project Cost: | 822000 | Target Completion Date: | 2021-02-03 23:59 | Program: | 822000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: | 30.04% | No. of Persons: | 13 | POW on process | POW on process | POW on process | POW on process | POW on process | On-going
San Isidro | Datu Balong | 1st Eng'g. Dist. | On-going | 2020-12-01 |  | 2020 | Administration |  | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Project Engineer: | Crucio | Revised Completion Date: |  | Allotment: | 822000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 374
San Isidro | Datu Balong | 1st Eng'g. Dist. | On-going | 2020-12-01 |  | 2020 | Administration |  | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual: | 30.04%
San Isidro | Datu Balong | 1st Eng'g. Dist. | On-going | 2020-12-01 |  | 2020 | Administration |  | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Duration: | 65 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
San Isidro | Datu Balong | 1st Eng'g. Dist. | On-going | 2020-12-01 |  | 2020 | Administration |  | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
San Isidro | Datu Balong | 1st Eng'g. Dist. | On-going | 2020-12-01 |  | 2020 | Administration |  | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Date Started: | 2020-12-01
New Corella | Macgum | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | ROAD ID 048 - New Corella - Saug |  | 20% Development Fund CY 2020 | Road Rehabilitaion | 12.52 | km | Admin | Project Cost: | 20571000 | Target Completion Date: |  | Program: | 20571000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | POW on process | POW on process | POW on process | POW on process | POW on process | POW on process
New Corella | Macgum | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 20571000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
New Corella | Macgum | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
New Corella | Macgum | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
New Corella | Macgum | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
New Corella | Macgum | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Date Started:
Asuncion | Canatan-Doña andrea | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | ROAD ID 074 - Jct. Highway Canatan - Doña Andrea |  | 20% Development Fund CY 2020 | Road Rehabilitaion | 4.34 | km | Admin | Project Cost: | 1302000 | Target Completion Date: |  | Program: | 1302000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | POW on process | POW on process | POW on process | POW on process | POW on process | POW on process
Asuncion | Canatan-Doña andrea | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 1302000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
Asuncion | Canatan-Doña andrea | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
Asuncion | Canatan-Doña andrea | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Asuncion | Canatan-Doña andrea | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Asuncion | Canatan-Doña andrea | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Date Started:
Kapalong | Florida | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | ROAD ID 030 - Florida - New Boholano |  | 20% Development Fund CY 2020 | Road Rehabilitaion | 2.54 | km | Admin | Project Cost: | 762000 | Target Completion Date: |  | Program: | 762000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | POW on process | POW on process | POW on process | POW on process | POW on process | POW on process
Kapalong | Florida | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 762000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
Kapalong | Florida | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
Kapalong | Florida | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Kapalong | Florida | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Kapalong | Florida | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Date Started:
Asuncion | New Loon | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | ROAD ID 031 - Jct. New Boholano - New Loon |  | 20% Development Fund CY 2020 | Road Rehabilitaion | 4.77 | km | Admin | Project Cost: | 1431000 | Target Completion Date: |  | Program: | 1431000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | POW on process | POW on process | POW on process | POW on process | POW on process | POW on process
Asuncion | New Loon | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 1431000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
Asuncion | New Loon | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
Asuncion | New Loon | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Asuncion | New Loon | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Asuncion | New Loon | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Date Started:
New Corella | Mesaoy | 1st Eng'g. Dist. | On-going | 2020-12-18 |  | 2020 | Adminsitration | . | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | ROAD ID 069 - Mesaoy - Jct. Mahayahay |  | 20% Development Fund CY 2020 | Road Rehabilitaion | 4.6 | km | Admin | Project Cost: | 1380000 | Target Completion Date: | 2021-02-15 23:59 | Program: | 1380000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: | 72.16% | No. of Persons: |  | POW on process | POW on process | POW on process | POW on process | POW on process | On--going
New Corella | Mesaoy | 1st Eng'g. Dist. | On-going | 2020-12-18 |  | 2020 | Adminsitration | . | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Project Engineer: | Pilotos | Revised Completion Date: |  | Allotment: | 1380000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
New Corella | Mesaoy | 1st Eng'g. Dist. | On-going | 2020-12-18 |  | 2020 | Adminsitration | . | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual: | 72.16%
New Corella | Mesaoy | 1st Eng'g. Dist. | On-going | 2020-12-18 |  | 2020 | Adminsitration | . | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Duration: | 60 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
New Corella | Mesaoy | 1st Eng'g. Dist. | On-going | 2020-12-18 |  | 2020 | Adminsitration | . | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
New Corella | Mesaoy | 1st Eng'g. Dist. | On-going | 2020-12-18 |  | 2020 | Adminsitration | . | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Date Started: | 2020-12-18
Asuncion | Cabaywa | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | ROAD ID 071 - Lower Asuncion - Upper Asuncion |  | 20% Development Fund CY 2020 | Road Rehabilitaion |  | km | Admin | Project Cost: | 1302000 | Target Completion Date: |  | Program: | 1302000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Plan On-going | Plan On-going | Plan On-going | Plan On-going | Plan On-going | Plan On-going
Asuncion | Cabaywa | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 1302000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
Asuncion | Cabaywa | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
Asuncion | Cabaywa | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Asuncion | Cabaywa | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Asuncion | Cabaywa | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | REHABILITATION OF PROVINCIAL ROADS & BRIDGES LS - P 14,751,000.00 | [7 empty] | Date Started:
Carmen | Mangalcal | 2nd Eng'g. Dist. | On-going | 2020-01-02 | 2020-12-31 | 2020 | Adminsitration | . | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 073 - Cebulano - Mangalcal |  | GENERAL FUND CY 2020 | Maintenance | 4.17 | km | MBA | Project Cost: | 134672.7 | Target Completion Date: | 2020-12-31 23:59 | Program: | 134672.7 | Planned: | 50% | Planned: | 50% | Planned: | 50% | Planned: | 81% | Planned: | 81% | No. of Persons: | 9 | On-going | On-going | On-going | On-going | On-going | On-going
Carmen | Mangalcal | 2nd Eng'g. Dist. | On-going | 2020-01-02 | 2020-12-31 | 2020 | Adminsitration | . | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Gamad/Clar | Revised Completion Date: |  | Allotment: | 134672.7 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 45
Carmen | Mangalcal | 2nd Eng'g. Dist. | On-going | 2020-01-02 | 2020-12-31 | 2020 | Adminsitration | . | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: | 51% | Actual: | 51% | Actual: | 51% | Actual: | 83.6% | Actual: | 83.6%
Carmen | Mangalcal | 2nd Eng'g. Dist. | On-going | 2020-01-02 | 2020-12-31 | 2020 | Adminsitration | . | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 1% | Slippage: | 1% | Slippage: | 1% | Slippage: | 2.6% | Slippage: | 2.6%
Carmen | Mangalcal | 2nd Eng'g. Dist. | On-going | 2020-01-02 | 2020-12-31 | 2020 | Adminsitration | . | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
Carmen | Mangalcal | 2nd Eng'g. Dist. | On-going | 2020-01-02 | 2020-12-31 | 2020 | Adminsitration | . | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started: | 2020-01-02
Carmen | Mangalcal | 2nd Eng'g. Dist. | Completed | 2020-05-15 | 2020-11-15 | 2020 | Contract | . | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 073 - Cebulano - Mangalcal |  | GENERAL FUND CY 2020 | Maintenance | 4.17 | km | CBRMC | Project Cost: | 131004.66 | Target Completion Date: | 2020-11-11 | Program: | 131004.66 | Planned: | 5% | Planned: | 5% | Planned: | 5% | Planned: | 42.43% | Planned: | 100% | No. of Persons: | 6 | On-going | On-going | On-going | On-going | On-going | Completed as per Program of Works
Carmen | Mangalcal | 2nd Eng'g. Dist. | Completed | 2020-05-15 | 2020-11-15 | 2020 | Contract | . | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Maligro | Revised Completion Date: |  | Allotment: | 131004.66 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 30
Carmen | Mangalcal | 2nd Eng'g. Dist. | Completed | 2020-05-15 | 2020-11-15 | 2020 | Contract | . | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: | Brgy. Mangalcal Women's Household | No. of days suspended: |  | Disbursement: |  | Actual: | 5% | Actual: | 5% | Actual: | 5% | Actual: | 42.43% | Actual: | 100%
Carmen | Mangalcal | 2nd Eng'g. Dist. | Completed | 2020-05-15 | 2020-11-15 | 2020 | Contract | . | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: | 180 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Carmen | Mangalcal | 2nd Eng'g. Dist. | Completed | 2020-05-15 | 2020-11-15 | 2020 | Contract | . | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed: | 2020-11-15
Carmen | Mangalcal | 2nd Eng'g. Dist. | Completed | 2020-05-15 | 2020-11-15 | 2020 | Contract | . | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started: | 2020-05-15
Carmen | Tubod | 2nd Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Adminsitration | . | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 074 - Tubod - basa - Mangalcal |  | GENERAL FUND CY 2020 | Maintenance | 3.93 | km | MBA | Project Cost: | 143530.25 | Target Completion Date: | 2020-12-31 23:59 | Program: | 143530.25 | Planned: | 50% | Planned: | 50% | Planned: | 50% | Planned: | 82.6% | Planned: | 100% | No. of Persons: | 3 | On-going | On-going | On-going | On-going | On-going | Completed as per Program of Works
Carmen | Tubod | 2nd Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Adminsitration | . | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Gamad/Clar | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 143530.25 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 30
Carmen | Tubod | 2nd Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Adminsitration | . | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: |  | Actual: | 52% | Actual: | 52% | Actual: | 52% | Actual: | 83.6% | Actual: | 100%
Carmen | Tubod | 2nd Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Adminsitration | . | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 2% | Slippage: | 2% | Slippage: | 2% | Slippage: | 1% | Slippage: | 0%
Carmen | Tubod | 2nd Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Adminsitration | . | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed: | 2020-12-31
Carmen | Tubod | 2nd Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Adminsitration | . | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started: | 2020-01-02
Carmen | Tubod | 2nd Eng'g. Dist. | Completed | 2020-05-15 | 2020-11-25 | 2020 | Contract | . | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 074 - Tubod - basa - Mangalcal |  | GENERAL FUND CY 2020 | Maintenance | 3.93 | km | CBRMC | Project Cost: | 106856.33 | Target Completion Date: | 2020-11-11 | Program: | 106856.33 | Planned: | 5% | Planned: | 5% | Planned: | 5% | Planned: | 100% | Planned: | 100% | No. of Persons: | 2 | On-going | On-going | On-going | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per Program of Works
Carmen | Tubod | 2nd Eng'g. Dist. | Completed | 2020-05-15 | 2020-11-25 | 2020 | Contract | . | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Maligro | Revised Completion Date: |  | Allotment: | 106856.33 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 44
Carmen | Tubod | 2nd Eng'g. Dist. | Completed | 2020-05-15 | 2020-11-25 | 2020 | Contract | . | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: | Tubod Centro Lower Irrigator's Association | No. of days suspended: |  | Disbursement: |  | Actual: | 5% | Actual: | 5% | Actual: | 5% | Actual: | 100% | Actual: | 100%
Carmen | Tubod | 2nd Eng'g. Dist. | Completed | 2020-05-15 | 2020-11-25 | 2020 | Contract | . | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: | 6 months | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Carmen | Tubod | 2nd Eng'g. Dist. | Completed | 2020-05-15 | 2020-11-25 | 2020 | Contract | . | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: |  | Date completed: | 2020-11-25
Carmen | Tubod | 2nd Eng'g. Dist. | Completed | 2020-05-15 | 2020-11-25 | 2020 | Contract | . | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started: | 2020-05-15
Carmen | Tubod | 2nd Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Adminsitration | . | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 078 - Upper Mangalcal - Lower Mangalcal |  | GENERAL FUND CY 2020 | Maintenance | 2.43 | km | MBA | Project Cost: | 82374.21 | Target Completion Date: | 2020-12-31 23:59 | Program: | 82374.21 | Planned: | 50% | Planned: | 50% | Planned: | 50% | Planned: | 86.5% | Planned: | 86.5% | No. of Persons: | 3 | On-going | On-going | On-going | On-going | On-going | Completed as per Program of Works
Carmen | Tubod | 2nd Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Adminsitration | . | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Gamad/Clar | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 82374.21 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 24
Carmen | Tubod | 2nd Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Adminsitration | . | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: |  | Actual: | 55% | Actual: | 55% | Actual: | 55% | Actual: | 84.6% | Actual: | 84.6%
Carmen | Tubod | 2nd Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Adminsitration | . | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 5% | Slippage: | 5% | Slippage: | 5% | Slippage: | -1.9% | Slippage: | -1.9%
Carmen | Tubod | 2nd Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Adminsitration | . | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed: | 2020-12-31
Carmen | Tubod | 2nd Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Adminsitration | . | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started: | 2020-01-02
Carmen | Mangalcal | 2nd Eng'g. Dist. | Completed | 2020-05-15 | 2020-11-15 | 2020 | Contract | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 078 - Upper Mangalcal - Lower Mangalcal |  | GENERAL FUND CY 2020 | Maintenance | 2.43 | km | CBRMC | Project Cost: | 72444.97 | Target Completion Date: | 2020-11-15 23:59 | Program: | 72444.97 | Planned: | 5% | Planned: | 5% | Planned: | 5% | Planned: | 100% | Planned: | 100% | No. of Persons: | 6 | On-going | On-going | On-going | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per Program of Works
Carmen | Mangalcal | 2nd Eng'g. Dist. | Completed | 2020-05-15 | 2020-11-15 | 2020 | Contract | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Maligro | Revised Completion Date: |  | Allotment: | 72444.97 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 18
Carmen | Mangalcal | 2nd Eng'g. Dist. | Completed | 2020-05-15 | 2020-11-15 | 2020 | Contract | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: | Brgy. Mangalcal Women's Homebased Association | No. of days suspended: |  | Disbursement: |  | Actual: | 5% | Actual: | 5% | Actual: | 5% | Actual: | 100% | Actual: | 100%
Carmen | Mangalcal | 2nd Eng'g. Dist. | Completed | 2020-05-15 | 2020-11-15 | 2020 | Contract | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: | 185 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Carmen | Mangalcal | 2nd Eng'g. Dist. | Completed | 2020-05-15 | 2020-11-15 | 2020 | Contract | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed: | 2020-11-15 23:59
Carmen | Mangalcal | 2nd Eng'g. Dist. | Completed | 2020-05-15 | 2020-11-15 | 2020 | Contract | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started: | 2020-05-15
Carmen | Cebulano | 2nd Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Adminsitration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 079 - Cebulano - Loceta |  | GENERAL FUND CY 2020 | Maintenance |  | km | MBA | Project Cost: | 72051.43 | Target Completion Date: | 2020-12-31 23:59 | Program: | 72051.43 | Planned: | 30% | Planned: | 30% | Planned: | 30% | Planned: | 82.6% | Planned: | 100% | No. of Persons: | 3 | On-going | On-going | On-going | On-going | On-going | Completed as per Program of Works
Carmen | Cebulano | 2nd Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Adminsitration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Gamad/Clar | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 72051.43 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 36
Carmen | Cebulano | 2nd Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Adminsitration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: |  | Actual: | 54% | Actual: | 54% | Actual: | 54% | Actual: | 84.6% | Actual: | 100%
Carmen | Cebulano | 2nd Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Adminsitration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 24% | Slippage: | 24% | Slippage: | 24% | Slippage: | 2% | Slippage: | 0%
Carmen | Cebulano | 2nd Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Adminsitration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed: | 2020-12-31
Carmen | Cebulano | 2nd Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Adminsitration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started: | 2020-01-02
Carmen | Cebulano | 2nd Eng'g. Dist. | Completed | 2020-05-15 | 2020-11-15 | 2020 | Contract | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 079 - Cebulano - Loceta |  | GENERAL FUND CY 2020 | Maintenance |  | km | CBRMC | Project Cost: | 47089.26 | Target Completion Date: | 2020-11-15 23:59 | Program: | 47089.26 | Planned: | 5% | Planned: | 5% | Planned: | 5% | Planned: | 100% | Planned: | 100% | No. of Persons: | 6 | On-going | On-going | On-going | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per Program of Works
Carmen | Cebulano | 2nd Eng'g. Dist. | Completed | 2020-05-15 | 2020-11-15 | 2020 | Contract | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Maligro | Revised Completion Date: |  | Allotment: | 47089.26 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 18
Carmen | Cebulano | 2nd Eng'g. Dist. | Completed | 2020-05-15 | 2020-11-15 | 2020 | Contract | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: | Brgy. Mangalcal Women's Homebased Association | No. of days suspended: |  | Disbursement: |  | Actual: | 5% | Actual: | 5% | Actual: | 5% | Actual: | 100% | Actual: | 100%
Carmen | Cebulano | 2nd Eng'g. Dist. | Completed | 2020-05-15 | 2020-11-15 | 2020 | Contract | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: | 185 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Carmen | Cebulano | 2nd Eng'g. Dist. | Completed | 2020-05-15 | 2020-11-15 | 2020 | Contract | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed: | 2020-11-15 23:59
Carmen | Cebulano | 2nd Eng'g. Dist. | Completed | 2020-05-15 | 2020-11-15 | 2020 | Contract | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started: | 2020-05-15
Carmen | Tubod | 2nd Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Adminsitration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 082 - Jct. Highway Carmen - Mangalcal - Tubod |  | GENERAL FUND CY 2020 | Maintenance | 11.34 | km | MBA | Project Cost: | 462895.06 | Target Completion Date: | 2020-12-31 23:59 | Program: | 462895.06 | Planned: | 50% | Planned: | 50% | Planned: | 50% | Planned: | 82.6% | Planned: | 100% | No. of Persons: | 9 | On-going | On-going | On-going | On-going | On-going | Completed as per Program of Works
Carmen | Tubod | 2nd Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Adminsitration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Gamad/Clar | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 462895.06 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 45
Carmen | Tubod | 2nd Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Adminsitration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: |  | Actual: | 50% | Actual: | 50% | Actual: | 50% | Actual: | 81.6% | Actual: | 100%
Carmen | Tubod | 2nd Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Adminsitration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | -1% | Slippage: | 0%
Carmen | Tubod | 2nd Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Adminsitration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed: | 2020-12-31
Carmen | Tubod | 2nd Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Adminsitration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started: | 2020-01-02
Carmen | Tubod | 2nd Eng'g. Dist. | On-going | 2020-08-04 |  | 2020 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 082 - Jct. Highway Carmen - Mangalcal - Tubod |  | GENERAL FUND CY 2020 | Maintenance | 11.34 | km | CBRMC | Project Cost: | 259594.46 | Target Completion Date: | 2021-02-04 | Program: | 259594.46 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: | 42.1% | No. of Persons: | 3 | PO #2020031403 - Awarded to TUBOD CENTRO LOWER IRRIGATORS ASS'T (TUCLIA) | PO #2020031403 - Awarded to TUBOD CENTRO LOWER IRRIGATORS ASS'T (TUCLIA) | PO #2020031403 - Awarded to TUBOD CENTRO LOWER IRRIGATORS ASS'T (TUCLIA) | For implementation (Winning Bidder Tubod Central Lower Irrigator Association) | For implementation (Winning Bidder Tubod Central Lower Irrigator Association) | On-going
Carmen | Tubod | 2nd Eng'g. Dist. | On-going | 2020-08-04 |  | 2020 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Maligro | Revised Completion Date: |  | Allotment: | 259594.46 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 18
Carmen | Tubod | 2nd Eng'g. Dist. | On-going | 2020-08-04 |  | 2020 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: | Tubod Central Lower Irrigator Association | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual: | 41.66%
Carmen | Tubod | 2nd Eng'g. Dist. | On-going | 2020-08-04 |  | 2020 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: | 6 months | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | -0.44%
Carmen | Tubod | 2nd Eng'g. Dist. | On-going | 2020-08-04 |  | 2020 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: |  | Date completed:
Carmen | Tubod | 2nd Eng'g. Dist. | On-going | 2020-08-04 |  | 2020 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started: | 2020-08-04
Carmen | Taba | 2nd Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Adminsitration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 086 - Ising - Sadpodon - Taba - Dila -Dila |  | GENERAL FUND CY 2020 | Maintenance | 5.68 | km | MBA | Project Cost: | 226651.27 | Target Completion Date: | 2020-12-31 23:59 | Program: | 226651.27 | Planned: | 50% | Planned: | 50% | Planned: | 50% | Planned: | 85.6% | Planned: | 100% | No. of Persons: | 3 | On-going | On-going | On-going | On-going | On-going | Completed as per Program of Works
Carmen | Taba | 2nd Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Adminsitration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Gamad/Clar | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 226651.27 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 30
Carmen | Taba | 2nd Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Adminsitration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: |  | Actual: | 50% | Actual: | 50% | Actual: | 50% | Actual: | 84.6% | Actual: | 100%
Carmen | Taba | 2nd Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Adminsitration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | -1% | Slippage: | 0%
Carmen | Taba | 2nd Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Adminsitration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed: | 2020-12-31
Carmen | Taba | 2nd Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Adminsitration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started: | 2020-01-02
Carmen | Taba | 2nd Eng'g. Dist. | On-going | 2020-08-24 |  | 2020 | Contract | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 086 - Ising - Sadpodon - Taba - Dila -Dila |  | GENERAL FUND CY 2020 | Maintenance | 5.68 | km | CBRMC | Project Cost: | 135230.61 | Target Completion Date: | 2/24/2021 | Program: | 135230.61 | Planned: | 50% | Planned: | 50% | Planned: | 50% | Planned: | 50% | Planned: | 42.1% | No. of Persons: | 4 | PO #2020031408 - Awarded to TABA COCONUT FARMERS ORGANIZATION | PO #2020031408 - Awarded to TABA COCONUT FARMERS ORGANIZATION | PO #2020031408 - Awarded to TABA COCONUT FARMERS ORGANIZATION | For implementation (Winning Bidder Taba Coconut Farmers Association) | For implementation (Winning Bidder Taba Coconut Farmers Association) | On-going
Carmen | Taba | 2nd Eng'g. Dist. | On-going | 2020-08-24 |  | 2020 | Contract | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Maligro | Revised Completion Date: |  | Allotment: | 135230.61 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 16
Carmen | Taba | 2nd Eng'g. Dist. | On-going | 2020-08-24 |  | 2020 | Contract | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: | Taba Coconut Farmers Association | No. of days suspended: |  | Disbursement: |  | Actual: | 55% | Actual: | 55% | Actual: | 55% | Actual: | 55% | Actual: | 41.68%
Carmen | Taba | 2nd Eng'g. Dist. | On-going | 2020-08-24 |  | 2020 | Contract | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: | 6 months | No. of days extended: |  |  |  | Slippage: | 5% | Slippage: | 5% | Slippage: | 5% | Slippage: | 5% | Slippage: | -0.42%
Carmen | Taba | 2nd Eng'g. Dist. | On-going | 2020-08-24 |  | 2020 | Contract | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: |  | Date completed:
Carmen | Taba | 2nd Eng'g. Dist. | On-going | 2020-08-24 |  | 2020 | Contract | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started: | 2020-08-24
Carmen | Tuganay | 2nd Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Adminsitration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 087 - Tuganay - taba |  | GENERAL FUND CY 2020 | Maintenance | 4.27 | km | MBA | Project Cost: | 169418.15 | Target Completion Date: | 2020-12-31 23:59 | Program: | 169418.15 | Planned: | 52% | Planned: | 52% | Planned: | 52% | Planned: | 82.6% | Planned: | 100% | No. of Persons: | 3 | On-going | On-going | On-going | On-going | On-going | Completed as per Program of Works
Carmen | Tuganay | 2nd Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Adminsitration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Gamad/Clar | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 169418.15 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 45
Carmen | Tuganay | 2nd Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Adminsitration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: |  | Actual: | 52% | Actual: | 52% | Actual: | 52% | Actual: | 84.6% | Actual: | 100%
Carmen | Tuganay | 2nd Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Adminsitration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 2% | Slippage: | 0%
Carmen | Tuganay | 2nd Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Adminsitration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed: | 2020-12-31
Carmen | Tuganay | 2nd Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Adminsitration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started: | 2020-01-02
Carmen | Tuganay | 2nd Eng'g. Dist. | On-going | 2020-08-24 |  | 2020 | Contract | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 087 - Tuganay - taba |  | GENERAL FUND CY 2020 | Maintenance | 4.27 | km | CBRMC | Project Cost: | 102630.37 | Target Completion Date: |  | Program: | 102630.37 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: | 42.6% | No. of Persons: | 5 | PO #2020031406 - TABA COCONUT FARMERS ORGANIZATION | PO #2020031406 - TABA COCONUT FARMERS ORGANIZATION | PO #2020031406 - TABA COCONUT FARMERS ORGANIZATION | PO #2020031406 - TABA COCONUT FARMERS ORGANIZATION | PO #2020031406 - TABA COCONUT FARMERS ORGANIZATION | On-going
Carmen | Tuganay | 2nd Eng'g. Dist. | On-going | 2020-08-24 |  | 2020 | Contract | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Maligro | Revised Completion Date: |  | Allotment: | 102630.37 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 21
Carmen | Tuganay | 2nd Eng'g. Dist. | On-going | 2020-08-24 |  | 2020 | Contract | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: | Taba Coconut Farmers Association | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual: | 42.31%
Carmen | Tuganay | 2nd Eng'g. Dist. | On-going | 2020-08-24 |  | 2020 | Contract | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: | 6 months | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | -0.29%
Carmen | Tuganay | 2nd Eng'g. Dist. | On-going | 2020-08-24 |  | 2020 | Contract | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: |  | Date completed:
Carmen | Tuganay | 2nd Eng'g. Dist. | On-going | 2020-08-24 |  | 2020 | Contract | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started: | 2020-08-24
Carmen | Tuganay | 2nd Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Adminsitration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 088 - Jct. Highway Tuganay - Taba |  | GENERAL FUND CY 2020 | Maintenance | 4.4 | km | MBA | Project Cost: | 222375.04 | Target Completion Date: | 2020-12-31 23:59 | Program: | 222375.04 | Planned: | 50% | Planned: | 50% | Planned: | 50% | Planned: | 86.6% | Planned: | 100% | No. of Persons: | 3 | On-going | On-going | On-going | On-going | On-going | Completed as per Program of Works
Carmen | Tuganay | 2nd Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Adminsitration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Gamad/Clar | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 222375.04 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 30
Carmen | Tuganay | 2nd Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Adminsitration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: |  | Actual: | 51% | Actual: | 51% | Actual: | 51% | Actual: | 85.4% | Actual: | 100%
Carmen | Tuganay | 2nd Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Adminsitration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 1% | Slippage: | 1% | Slippage: | 1% | Slippage: | -1.2% | Slippage: | 0%
Carmen | Tuganay | 2nd Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Adminsitration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed: | 2020-12-31
Carmen | Tuganay | 2nd Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Adminsitration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started: | 2020-01-02
Carmen | Tuganay | 2nd Eng'g. Dist. | Completed | 2020-05-13 | 2020-11-13 | 2020 | Contract | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 088 - Jct. Highway Tuganay - Taba |  | GENERAL FUND CY 2020 | Maintenance | 4.4 | km | CBRMC | Project Cost: | 57955.99 | Target Completion Date: | 2020-11-13 23:59 | Program: | 57955.99 | Planned: | 5% | Planned: | 5% | Planned: | 5% | Planned: | 50% | Planned: | 100% | No. of Persons: | 4 | On-going | On-going | On-going | On-going | On-going | Completed as per Program of Works
Carmen | Tuganay | 2nd Eng'g. Dist. | Completed | 2020-05-13 | 2020-11-13 | 2020 | Contract | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Maligro | Revised Completion Date: |  | Allotment: | 57955.99 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 12
Carmen | Tuganay | 2nd Eng'g. Dist. | Completed | 2020-05-13 | 2020-11-13 | 2020 | Contract | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: | Ezra Christian Minsitry For Peace, Inc. | No. of days suspended: |  | Disbursement: |  | Actual: | 5% | Actual: | 5% | Actual: | 5% | Actual: | 50% | Actual: | 100%
Carmen | Tuganay | 2nd Eng'g. Dist. | Completed | 2020-05-13 | 2020-11-13 | 2020 | Contract | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: | 185 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Carmen | Tuganay | 2nd Eng'g. Dist. | Completed | 2020-05-13 | 2020-11-13 | 2020 | Contract | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed: | 2020-11-13
Carmen | Tuganay | 2nd Eng'g. Dist. | Completed | 2020-05-13 | 2020-11-13 | 2020 | Contract | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started: | 2020-05-13
Carmen | Ising | 2nd Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Adminsitration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 089 - Jct. Highway Ising - Magsaysay |  | GENERAL FUND CY 2020 | Maintenance | 10.84 | km | MBA | Project Cost: | 478128.48 | Target Completion Date: | 2020-12-31 23:59 | Program: | 478128.48 | Planned: | 50% | Planned: | 50% | Planned: | 50% | Planned: | 85.6% | Planned: | 100% | No. of Persons: | 8 | On-going | On-going | On-going | On-going | On-going | Completed as per Program of Works
Carmen | Ising | 2nd Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Adminsitration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Gamad/Clar | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 478128.48 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 32
Carmen | Ising | 2nd Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Adminsitration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: |  | Actual: | 50% | Actual: | 50% | Actual: | 50% | Actual: | 84.7% | Actual: | 100%
Carmen | Ising | 2nd Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Adminsitration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | -0.9% | Slippage: | 0%
Carmen | Ising | 2nd Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Adminsitration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed: | 2020-12-31
Carmen | Ising | 2nd Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Adminsitration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started: | 2020-01-02
Carmen | Ising | 2nd Eng'g. Dist. | Completed | 2020-05-14 | 2020-11-14 | 2020 | Contract | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 089 - Jct. Highway Ising - Magsaysay |  | GENERAL FUND CY 2020 | Maintenance | 10.84 | km | CBRMC | Project Cost: | 212505.24 | Target Completion Date: | 2020-11-14 23:59 | Program: | 212505.24 | Planned: | 5% | Planned: | 5% | Planned: | 5% | Planned: | 50% | Planned: | 100% | No. of Persons: | 6 | On-going | On-going | On-going | On-going | On-going | Completed as per Program of Works
Carmen | Ising | 2nd Eng'g. Dist. | Completed | 2020-05-14 | 2020-11-14 | 2020 | Contract | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Maligro | Revised Completion Date: |  | Allotment: | 212505.24 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 24
Carmen | Ising | 2nd Eng'g. Dist. | Completed | 2020-05-14 | 2020-11-14 | 2020 | Contract | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: | School in the Air Integrated Farmer's Associiation | No. of days suspended: |  | Disbursement: |  | Actual: | 5% | Actual: | 5% | Actual: | 5% | Actual: | 50% | Actual: | 100%
Carmen | Ising | 2nd Eng'g. Dist. | Completed | 2020-05-14 | 2020-11-14 | 2020 | Contract | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: | 185 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Carmen | Ising | 2nd Eng'g. Dist. | Completed | 2020-05-14 | 2020-11-14 | 2020 | Contract | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed: | 2020-11-14
Carmen | Ising | 2nd Eng'g. Dist. | Completed | 2020-05-14 | 2020-11-14 | 2020 | Contract | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started: | 2020-05-14
C armen | New Camiling | 2nd Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Adminsitration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 090 - Maligaya - New Camiling |  | GENERAL FUND CY 2020 | Maintenance |  | km | MBA | Project Cost: | 51790.26 | Target Completion Date: | 2020-12-31 23:59 | Program: | 51790.26 | Planned: | 50% | Planned: | 50% | Planned: | 50% | Planned: | 81.6% | Planned: | 100% | No. of Persons: | 3 | On-going | On-going | On-going | On-going | On-going | Completed as per Program of Works
C armen | New Camiling | 2nd Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Adminsitration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Gamad/Clar | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 51790.26 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 36
C armen | New Camiling | 2nd Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Adminsitration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: |  | Actual: | 51% | Actual: | 51% | Actual: | 51% | Actual: | 84.6% | Actual: | 100%
C armen | New Camiling | 2nd Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Adminsitration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 1% | Slippage: | 1% | Slippage: | 1% | Slippage: | 3% | Slippage: | 0%
C armen | New Camiling | 2nd Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Adminsitration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed: | 2020-12-31
C armen | New Camiling | 2nd Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Adminsitration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started: | 2020-01-02
C armen | New Camiling | 2nd Eng'g. Dist. | On-going | 2020-05-14 |  | 2020 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 090 - Maligaya - New Camiling |  | GENERAL FUND CY 2020 | Maintenance |  | km | CBRMC | Project Cost: | 83915.44 | Target Completion Date: | 2020-11-14 23:59 | Program: | 83915.44 | Planned: | 5% | Planned: | 5% | Planned: | 5% | Planned: | 29.38% | Planned: | 53.1% | No. of Persons: | 6 | On-going | On-going | On-going | On-going | On-going | On-going
C armen | New Camiling | 2nd Eng'g. Dist. | On-going | 2020-05-14 |  | 2020 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Maligro | Revised Completion Date: |  | Allotment: | 83915.44 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 24
C armen | New Camiling | 2nd Eng'g. Dist. | On-going | 2020-05-14 |  | 2020 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: | School in the Air Integrated Farmer's Associiation | No. of days suspended: |  | Disbursement: |  | Actual: | 5% | Actual: | 5% | Actual: | 5% | Actual: | 29.38% | Actual: | 53.95%
C armen | New Camiling | 2nd Eng'g. Dist. | On-going | 2020-05-14 |  | 2020 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: | 185 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0.85%
C armen | New Camiling | 2nd Eng'g. Dist. | On-going | 2020-05-14 |  | 2020 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
C armen | New Camiling | 2nd Eng'g. Dist. | On-going | 2020-05-14 |  | 2020 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started: | 2020-05-14
C armen | New Camiling | 2nd Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Adminsitration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 091 - New Camiling - Alejal - Lower Magsaysay |  | GENERAL FUND CY 2020 | Maintenance | 6.73 | km | MBA | Project Cost: | 277852.05 | Target Completion Date: | 2020-12-31 23:59 | Program: | 277852.05 | Planned: | 50% | Planned: | 50% | Planned: | 50% | Planned: | 87.6% | Planned: | 87.6% | No. of Persons: | 3 | On-going | On-going | On-going | On-going | On-going | Completed as per Program of Works
C armen | New Camiling | 2nd Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Adminsitration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Gamad/Clar | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 277852.05 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 30
C armen | New Camiling | 2nd Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Adminsitration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: |  | Actual: | 50% | Actual: | 50% | Actual: | 50% | Actual: | 85.64% | Actual: | 85.64%
C armen | New Camiling | 2nd Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Adminsitration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | -1.96% | Slippage: | -1.96%
C armen | New Camiling | 2nd Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Adminsitration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed: | 2020-12-31
C armen | New Camiling | 2nd Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Adminsitration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started: | 2020-01-02
C armen | New Camiling | 2nd Eng'g. Dist. | Completed | 2020-05-14 | 2020-11-14 | 2020 | Contract | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 091 - New Camiling - Alejal - Lower Magsaysay |  | GENERAL FUND CY 2020 | Maintenance | 6.73 | km | CBRMC | Project Cost: | 150927.01 | Target Completion Date: | 2020-11-14 23:59 | Program: | 150927.01 | Planned: | 5% | Planned: | 5% | Planned: | 5% | Planned: | 100% | Planned: | 100% | No. of Persons: | 6 | On-going | On-going | On-going | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per Program of Works
C armen | New Camiling | 2nd Eng'g. Dist. | Completed | 2020-05-14 | 2020-11-14 | 2020 | Contract | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Maligro | Revised Completion Date: |  | Allotment: | 150927.01 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 18
C armen | New Camiling | 2nd Eng'g. Dist. | Completed | 2020-05-14 | 2020-11-14 | 2020 | Contract | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: | School in the Air Integrated Farmer's Association | No. of days suspended: |  | Disbursement: |  | Actual: | 5% | Actual: | 5% | Actual: | 5% | Actual: | 100% | Actual: | 100%
C armen | New Camiling | 2nd Eng'g. Dist. | Completed | 2020-05-14 | 2020-11-14 | 2020 | Contract | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: | 185 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
C armen | New Camiling | 2nd Eng'g. Dist. | Completed | 2020-05-14 | 2020-11-14 | 2020 | Contract | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed: | 2020-11-14
C armen | New Camiling | 2nd Eng'g. Dist. | Completed | 2020-05-14 | 2020-11-14 | 2020 | Contract | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started: | 2020-05-14
Carmen | Tuganay | 2nd Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Adminsitration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 094 - Jct. highway Tuganay - Anibongan |  | GENERAL FUND CY 2020 | Maintenance | 3.66 | km | MBA | Project Cost: | 139609.7 | Target Completion Date: | 2020-12-31 23:59 | Program: | 139609.7 | Planned: | 50% | Planned: | 50% | Planned: | 50% | Planned: | 81.6% | Planned: | 100% | No. of Persons: | 3 | On-going | On-going | On-going | On-going | On-going | Completed as per Program of Works
Carmen | Tuganay | 2nd Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Adminsitration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Gamad/Clar | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 139609.7 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 27
Carmen | Tuganay | 2nd Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Adminsitration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: |  | Actual: | 55% | Actual: | 55% | Actual: | 55% | Actual: | 84.6% | Actual: | 100%
Carmen | Tuganay | 2nd Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Adminsitration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 5% | Slippage: | 5% | Slippage: | 5% | Slippage: | 3% | Slippage: | 0%
Carmen | Tuganay | 2nd Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Adminsitration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed: | 2020-12-31
Carmen | Tuganay | 2nd Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Adminsitration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started: | 2020-01-02
Carmen | Tuganay | 2nd Eng'g. Dist. | Completed | 2020-05-13 | 2020-11-13 | 2020 | Contract | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 094 - Jct. highway Tuganay - Anibongan |  | GENERAL FUND CY 2020 | Maintenance | 3.66 | km | CBRMC | Project Cost: | 93574.75 | Target Completion Date: | 2020-11-13 23:59 | Program: | 93574.75 | Planned: | 5% | Planned: | 5% | Planned: | 5% | Planned: | 42.02% | Planned: | 100% | No. of Persons: | 6 | Purchase Order # 2020030977 (Ezra Christian Minsitry For Peace, Inc.) | Purchase Order # 2020030977 (Ezra Christian Minsitry For Peace, Inc.) | Purchase Order # 2020030977 (Ezra Christian Minsitry For Peace, Inc.) | On-going | On-going | Completed as per Program of Works
Carmen | Tuganay | 2nd Eng'g. Dist. | Completed | 2020-05-13 | 2020-11-13 | 2020 | Contract | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Maligro | Revised Completion Date: |  | Allotment: | 93574.75 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 6
Carmen | Tuganay | 2nd Eng'g. Dist. | Completed | 2020-05-13 | 2020-11-13 | 2020 | Contract | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: | Ezra Christian Minsitry For Peace, Inc. | No. of days suspended: |  | Disbursement: |  | Actual: | 5% | Actual: | 5% | Actual: | 5% | Actual: | 42.02% | Actual: | 100%
Carmen | Tuganay | 2nd Eng'g. Dist. | Completed | 2020-05-13 | 2020-11-13 | 2020 | Contract | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: | 185 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Carmen | Tuganay | 2nd Eng'g. Dist. | Completed | 2020-05-13 | 2020-11-13 | 2020 | Contract | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed: | 2020-11-13
Carmen | Tuganay | 2nd Eng'g. Dist. | Completed | 2020-05-13 | 2020-11-13 | 2020 | Contract | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started: | 2020-05-13
Carmen | Anibongan | 2nd Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Adminsitration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 095 - Anibongan - Guadalupe |  | GENERAL FUND CY 2020 | Maintenance | 2.48 | km | MBA | Project Cost: | 85559.79 | Target Completion Date: | 2020-12-31 23:59 | Program: | 85559.79 | Planned: | 50% | Planned: | 50% | Planned: | 50% | Planned: | 85.6% | Planned: | 100% | No. of Persons: | 4 | On-going / Time extension on process due to suspension of activity | On-going / Time extension on process due to suspension of activity | On-going / Time extension on process due to suspension of activity | On-going | On-going | Completed as per Program of Works
Carmen | Anibongan | 2nd Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Adminsitration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Gamad/Clar | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 85559.79 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 24
Carmen | Anibongan | 2nd Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Adminsitration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: |  | Actual: | 55% | Actual: | 55% | Actual: | 55% | Actual: | 84.1% | Actual: | 100%
Carmen | Anibongan | 2nd Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Adminsitration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 5% | Slippage: | 5% | Slippage: | 5% | Slippage: | -1.5% | Slippage: | 0%
Carmen | Anibongan | 2nd Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Adminsitration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed: | 2020-12-31
Carmen | Anibongan | 2nd Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Adminsitration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started: | 2020-01-02
Carmen | Anibongan | 2nd Eng'g. Dist. | On-going | 2020-08-04 |  | 2020 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 095 - Anibongan - Guadalupe |  | GENERAL FUND CY 2020 | Maintenance | 2.48 | km | CBRMC | Project Cost: | 72444.97 | Target Completion Date: |  | Program: | 72444.97 | Planned: |  | Planned: |  | Planned: |  | Planned: | 42.27% | Planned: | 42.27% | No. of Persons: | 8 | PO #2020031404 - PRK 4. ANIBONGAN CARMENT IRRIGATORS ASSN. | PO #2020031404 - PRK 4. ANIBONGAN CARMENT IRRIGATORS ASSN. | PO #2020031404 - PRK 4. ANIBONGAN CARMENT IRRIGATORS ASSN. | On-going | On-going | On-going
Carmen | Anibongan | 2nd Eng'g. Dist. | On-going | 2020-08-04 |  | 2020 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Maligro | Revised Completion Date: |  | Allotment: | 72444.97 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 40
Carmen | Anibongan | 2nd Eng'g. Dist. | On-going | 2020-08-04 |  | 2020 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: | Anibongan-Carmen Irrigators Asso. Inc | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: | 42.27% | Actual: | 42.27%
Carmen | Anibongan | 2nd Eng'g. Dist. | On-going | 2020-08-04 |  | 2020 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Carmen | Anibongan | 2nd Eng'g. Dist. | On-going | 2020-08-04 |  | 2020 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: |  | Date completed:
Carmen | Anibongan | 2nd Eng'g. Dist. | On-going | 2020-08-04 |  | 2020 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started: | 2020-08-04
Carmen | Tuganay | 2nd Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Adminsitration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 096 - Tuganay - Anibongan - San Isidro |  | GENERAL FUND CY 2020 | Maintenance | 7.22 | km | MBA | Project Cost: | 344085.79 | Target Completion Date: | 2020-12-31 23:59 | Program: | 344085.79 | Planned: | 50% | Planned: | 50% | Planned: | 50% | Planned: | 82.6% | Planned: | 100% | No. of Persons: | 3 | On-going | On-going | On-going | On-going | On-going | Completed as per Program of Works
Carmen | Tuganay | 2nd Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Adminsitration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Gamad/Clar | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 344085.79 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 24
Carmen | Tuganay | 2nd Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Adminsitration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: |  | Actual: | 50% | Actual: | 50% | Actual: | 50% | Actual: | 81.4% | Actual: | 100%
Carmen | Tuganay | 2nd Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Adminsitration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | -1.2% | Slippage: | 0%
Carmen | Tuganay | 2nd Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Adminsitration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed: | 2020-12-31
Carmen | Tuganay | 2nd Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Adminsitration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started: | 2020-01-02
Carmen | Tuganay | 2nd Eng'g. Dist. | Completed | 2020-05-13 | 2020-11-13 | 2020 | Contract | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 096 - Tuganay - Anibongan - San Isidro |  | GENERAL FUND CY 2020 | Maintenance | 7.22 | km | CBRMC | Project Cost: | 115911.95 | Target Completion Date: | 2020-11-13 23:59 | Program: | 115911.95 | Planned: | 5% | Planned: | 5% | Planned: | 5% | Planned: | 100% | Planned: | 100% | No. of Persons: | 6 | On-going | On-going | On-going | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per Program of Works
Carmen | Tuganay | 2nd Eng'g. Dist. | Completed | 2020-05-13 | 2020-11-13 | 2020 | Contract | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Maligro | Revised Completion Date: |  | Allotment: | 115911.95 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 30
Carmen | Tuganay | 2nd Eng'g. Dist. | Completed | 2020-05-13 | 2020-11-13 | 2020 | Contract | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: | Ezra Christian Minsitry For Peace, Inc. | No. of days suspended: |  | Disbursement: |  | Actual: | 5% | Actual: | 5% | Actual: | 5% | Actual: | 100% | Actual: | 100%
Carmen | Tuganay | 2nd Eng'g. Dist. | Completed | 2020-05-13 | 2020-11-13 | 2020 | Contract | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: | 185 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Carmen | Tuganay | 2nd Eng'g. Dist. | Completed | 2020-05-13 | 2020-11-13 | 2020 | Contract | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: |  | Date completed: | 2020-11-13 23:59
Carmen | Tuganay | 2nd Eng'g. Dist. | Completed | 2020-05-13 | 2020-11-13 | 2020 | Contract | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started: | 2020-05-13
Carmen | Anibongan | 2nd Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Adminsitration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 097 - Jct. Anibongan - Prk. 2, 7, 5, San Isidro |  | GENERAL FUND CY 2020 | Maintenance | 3.14 | km | MBA | Project Cost: | 89575.84 | Target Completion Date: | 2020-12-31 23:59 | Program: | 89575.84 | Planned: | 50% | Planned: | 50% | Planned: | 50% | Planned: | 84.6% | Planned: | 100% | No. of Persons: | 4 | On-going | On-going | On-going | On-going | On-going | Completed as per Program of Works
Carmen | Anibongan | 2nd Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Adminsitration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Gamad/Clar | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 89575.84 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 24
Carmen | Anibongan | 2nd Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Adminsitration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: |  | Actual: | 53% | Actual: | 53% | Actual: | 53% | Actual: | 82.6% | Actual: | 100%
Carmen | Anibongan | 2nd Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Adminsitration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 3% | Slippage: | 3% | Slippage: | 3% | Slippage: | -2% | Slippage: | 0%
Carmen | Anibongan | 2nd Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Adminsitration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed: | 2020-12-31
Carmen | Anibongan | 2nd Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Adminsitration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started: | 2020-01-02
Carmen | Anibongan | 2nd Eng'g. Dist. | On-going | 2020-09-11 |  | 2020 | Contract | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 097 - Jct. Anibongan - Prk. 2, 7, 5, San Isidro |  | GENERAL FUND CY 2020 | Maintenance | 3.14 | km | CBRMC | Project Cost: | 110478.58 | Target Completion Date: | 2021-03-11 | Program: | 110478.58 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: | 41.64% | No. of Persons: | 5 | PO #2020031378 - SAN ISIDRO FARMERS IRRIGATORS ASSN. | PO #2020031378 - SAN ISIDRO FARMERS IRRIGATORS ASSN. | PO #2020031378 - SAN ISIDRO FARMERS IRRIGATORS ASSN. | PO #2020031378 - SAN ISIDRO FARMERS IRRIGATORS ASSN. | PO #2020031378 - SAN ISIDRO FARMERS IRRIGATORS ASSN. | On-going
Carmen | Anibongan | 2nd Eng'g. Dist. | On-going | 2020-09-11 |  | 2020 | Contract | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Maligro | Revised Completion Date: |  | Allotment: | 110478.58 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 21
Carmen | Anibongan | 2nd Eng'g. Dist. | On-going | 2020-09-11 |  | 2020 | Contract | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: | San Isidro Farmers Irrigators Association | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual: | 41.64%
Carmen | Anibongan | 2nd Eng'g. Dist. | On-going | 2020-09-11 |  | 2020 | Contract | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Carmen | Anibongan | 2nd Eng'g. Dist. | On-going | 2020-09-11 |  | 2020 | Contract | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: |  | Date completed:
Carmen | Anibongan | 2nd Eng'g. Dist. | On-going | 2020-09-11 |  | 2020 | Contract | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started: | 2020-09-11
Carmen | Anibongan | 2nd Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Adminsitration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 098 - Anibongan - Salvacion - Cabay-angan |  | GENERAL FUND CY 2020 | Maintenance | 6.93 | km | MBA | Project Cost: | 279123.9 | Target Completion Date: | 2020-12-31 23:59 | Program: | 279123.9 | Planned: | 50% | Planned: | 50% | Planned: | 50% | Planned: | 82.6% | Planned: | 100% | No. of Persons: | 9 | On-going | On-going | On-going | On-going | On-going | Completed as per Program of Works
Carmen | Anibongan | 2nd Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Adminsitration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Gamad/Clar | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 279123.9 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 36
Carmen | Anibongan | 2nd Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Adminsitration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: |  | Actual: | 51% | Actual: | 51% | Actual: | 51% | Actual: | 84.61% | Actual: | 100%
Carmen | Anibongan | 2nd Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Adminsitration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 1% | Slippage: | 1% | Slippage: | 1% | Slippage: | 2.01% | Slippage: | 0%
Carmen | Anibongan | 2nd Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Adminsitration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed: | 2020-12-31
Carmen | Anibongan | 2nd Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Adminsitration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started: | 2020-01-02
Carmen | Anibongan | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | 2020 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 098 - Anibongan - Salvacion - Cabay-angan |  | GENERAL FUND CY 2020 | Maintenance | 6.93 | km | CBRMC | Project Cost: | 162397.48 | Target Completion Date: | 2021-01-31 | Program: | 162397.48 | Planned: |  | Planned: |  | Planned: |  | Planned: | 41.7% | Planned: | 41.7% | No. of Persons: | 4 | PO #2020031379 - PRK4. ANIBONGAN CARMEN IRRIGATORS ASS. | PO #2020031379 - PRK4. ANIBONGAN CARMEN IRRIGATORS ASS. | PO #2020031379 - PRK4. ANIBONGAN CARMEN IRRIGATORS ASS. | On-going | On-going | On-going
Carmen | Anibongan | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | 2020 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Maligro | Revised Completion Date: |  | Allotment: | 162397.48 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 88
Carmen | Anibongan | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | 2020 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: | Anibongan-Carmen Irrigators Asso. Inc | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: | 41.7% | Actual: | 41.7%
Carmen | Anibongan | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | 2020 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: | 6 months | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Carmen | Anibongan | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | 2020 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: | 2020-08-04 | Date completed:
Carmen | Anibongan | 2nd Eng'g. Dist. | On-going | 2020-01-02 |  | 2020 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started: | 2020-01-02
Carmen | Mabaus | 2nd Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Adminsitration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 099 - Mabaus - Cabay - angan |  | GENERAL FUND CY 2020 | Maintenance |  | km | MBA | Project Cost: | 113320.9 | Target Completion Date: | 2020-12-31 23:59 | Program: | 113320.9 | Planned: | 50% | Planned: | 50% | Planned: | 50% | Planned: | 82.4% | Planned: | 100% | No. of Persons: | 3 | On-going | On-going | On-going | On-going | On-going | Completed as per Program of Works
Carmen | Mabaus | 2nd Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Adminsitration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Gamad/Clar | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 113320.9 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 30
Carmen | Mabaus | 2nd Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Adminsitration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: |  | Actual: | 54% | Actual: | 54% | Actual: | 54% | Actual: | 81.67% | Actual: | 100%
Carmen | Mabaus | 2nd Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Adminsitration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 4% | Slippage: | 4% | Slippage: | 4% | Slippage: | -0.73% | Slippage: | 0%
Carmen | Mabaus | 2nd Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Adminsitration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed: | 2020-12-31
Carmen | Mabaus | 2nd Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Adminsitration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started: | 2020-01-02
Carmen | Mabaus | 2nd Eng'g. Dist. | On-going | 2020-10-13 |  | 2020 | Contract | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 099 - Mabaus - Cabay - angan |  | GENERAL FUND CY 2020 | Maintenance |  | km | CBRMC | Project Cost: | 90556.21 | Target Completion Date: | 2021-04-13 | Program: | 90556.21 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: | 42.39% | No. of Persons: | 3 | PO #2020031410 - LAMPIA PAG ASA IRRIGATORS ASS., INC. | PO #2020031410 - LAMPIA PAG ASA IRRIGATORS ASS., INC. | PO #2020031410 - LAMPIA PAG ASA IRRIGATORS ASS., INC. | PO #2020031410 - LAMPIA PAG ASA IRRIGATORS ASS., INC. | PO #2020031410 - LAMPIA PAG ASA IRRIGATORS ASS., INC. | On-going
Carmen | Mabaus | 2nd Eng'g. Dist. | On-going | 2020-10-13 |  | 2020 | Contract | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Maligro | Revised Completion Date: |  | Allotment: | 90556.21 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 15
Carmen | Mabaus | 2nd Eng'g. Dist. | On-going | 2020-10-13 |  | 2020 | Contract | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual: | 42.39%
Carmen | Mabaus | 2nd Eng'g. Dist. | On-going | 2020-10-13 |  | 2020 | Contract | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Carmen | Mabaus | 2nd Eng'g. Dist. | On-going | 2020-10-13 |  | 2020 | Contract | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: |  | Date completed:
Carmen | Mabaus | 2nd Eng'g. Dist. | On-going | 2020-10-13 |  | 2020 | Contract | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started: | 2020-10-13
Carmen | Guadalupe | 2nd Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Adminsitration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 101 - Jct. Highway Guadalupe - Bdry. Tagum |  | GENERAL FUND CY 2020 | Maintenance | 7.9 | km | MBA | Project Cost: | 517780.87 | Target Completion Date: | 2020-12-31 23:59 | Program: | 517780.87 | Planned: | 50% | Planned: | 50% | Planned: | 50% | Planned: | 84.5% | Planned: | 100% | No. of Persons: | 8 | On-going | On-going | On-going | On-going | On-going | Completed as per Program of Works
Carmen | Guadalupe | 2nd Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Adminsitration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Gamad/Clar | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 517780.87 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 48
Carmen | Guadalupe | 2nd Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Adminsitration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: |  | Actual: | 55% | Actual: | 55% | Actual: | 55% | Actual: | 86.4% | Actual: | 100%
Carmen | Guadalupe | 2nd Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Adminsitration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 5% | Slippage: | 5% | Slippage: | 5% | Slippage: | 1.9% | Slippage: | 0%
Carmen | Guadalupe | 2nd Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Adminsitration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed: | 2020-12-31
Carmen | Guadalupe | 2nd Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Adminsitration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started: | 2020-01-02
Carmen | Guadalupe | 2nd Eng'g. Dist. | On-going | 2020-10-13 |  | 2020 | Contract | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 101 - Jct. Highway Guadalupe - Bdry. Tagum |  | GENERAL FUND CY 2020 | Maintenance | 7.9 | km | CBRMC | Project Cost: | 231823.89 | Target Completion Date: | 2021-07-13 | Program: | 231823.89 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: | 27.75% | No. of Persons: | 4 | PO #2020031376 - LAMPIA PAG ASA IRRIGATORS ASS., INC. | PO #2020031376 - LAMPIA PAG ASA IRRIGATORS ASS., INC. | PO #2020031376 - LAMPIA PAG ASA IRRIGATORS ASS., INC. | PO #2020031376 - LAMPIA PAG ASA IRRIGATORS ASS., INC. | PO #2020031376 - LAMPIA PAG ASA IRRIGATORS ASS., INC. | On-going
Carmen | Guadalupe | 2nd Eng'g. Dist. | On-going | 2020-10-13 |  | 2020 | Contract | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Maligro | Revised Completion Date: |  | Allotment: | 231823.89 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 15
Carmen | Guadalupe | 2nd Eng'g. Dist. | On-going | 2020-10-13 |  | 2020 | Contract | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual: | 27.75%
Carmen | Guadalupe | 2nd Eng'g. Dist. | On-going | 2020-10-13 |  | 2020 | Contract | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Carmen | Guadalupe | 2nd Eng'g. Dist. | On-going | 2020-10-13 |  | 2020 | Contract | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: |  | Date completed:
Carmen | Guadalupe | 2nd Eng'g. Dist. | On-going | 2020-10-13 |  | 2020 | Contract | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started: | 2020-10-13
B.E. Dujali | Tanglaw | 2nd Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Adminsitration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 104 - Dujali - Tanglaw |  | GENERAL FUND CY 2020 | Maintenance |  | km | MBA | Project Cost: | 135183.27 | Target Completion Date: | 2020-12-31 23:59 | Program: | 135183.27 | Planned: | 50% | Planned: | 50% | Planned: | 50% | Planned: | 84.16% | Planned: | 100% | No. of Persons: | 3 | On-going | On-going | On-going | On-going | On-going | Completed as per Program of Works
B.E. Dujali | Tanglaw | 2nd Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Adminsitration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Gamad/Clar | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 135183.27 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 24
B.E. Dujali | Tanglaw | 2nd Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Adminsitration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: |  | Actual: | 52% | Actual: | 52% | Actual: | 52% | Actual: | 82.6% | Actual: | 100%
B.E. Dujali | Tanglaw | 2nd Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Adminsitration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 2% | Slippage: | 2% | Slippage: | 2% | Slippage: | -1.56% | Slippage: | 0%
B.E. Dujali | Tanglaw | 2nd Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Adminsitration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed: | 2020-12-31
B.E. Dujali | Tanglaw | 2nd Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Adminsitration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started: | 2020-01-02
B.E. Dujali | Tanglaw | 2nd Eng'g. Dist. | Completed | 2020-06-08 | 2020-12-08 | 2020 | Contract | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 104 - Dujali - Tanglaw |  | GENERAL FUND CY 2020 | Maintenance |  | km | CBRMC | Project Cost: | 94178.48 | Target Completion Date: | 2020-12-12 | Program: | 94178.48 | Planned: | 5% | Planned: | 5% | Planned: | 5% | Planned: | 41.07% | Planned: | 100% | No. of Persons: | 6 | On-going | On-going | On-going | On-going | On-going | Completed as per Program of Works
B.E. Dujali | Tanglaw | 2nd Eng'g. Dist. | Completed | 2020-06-08 | 2020-12-08 | 2020 | Contract | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Maligro | Revised Completion Date: | 2021-01-08 | Allotment: | 94178.48 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 12
B.E. Dujali | Tanglaw | 2nd Eng'g. Dist. | Completed | 2020-06-08 | 2020-12-08 | 2020 | Contract | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: | Dujali Poblacion Farmer's Irrigator's Association, Inc. | No. of days suspended: | 27 | Disbursement: |  | Actual: | 5% | Actual: | 5% | Actual: | 5% | Actual: | 41.07% | Actual: | 100%
B.E. Dujali | Tanglaw | 2nd Eng'g. Dist. | Completed | 2020-06-08 | 2020-12-08 | 2020 | Contract | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: | 187 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
B.E. Dujali | Tanglaw | 2nd Eng'g. Dist. | Completed | 2020-06-08 | 2020-12-08 | 2020 | Contract | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed: | 2020-12-08
B.E. Dujali | Tanglaw | 2nd Eng'g. Dist. | Completed | 2020-06-08 | 2020-12-08 | 2020 | Contract | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started: | 2020-06-08
B.E. Dujali | Dujali | 2nd Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Adminsitration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 105 - Poblacion Dujali - Prk. 8 Dujali |  | GENERAL FUND CY 2020 | Maintenance | 8.2 | km | MBA | Project Cost: | 329064 | Target Completion Date: | 2020-12-31 23:59 | Program: | 329064 | Planned: | 50% | Planned: | 50% | Planned: | 50% | Planned: | 82.6% | Planned: | 100% | No. of Persons: | 3 | On-going | On-going | On-going | On-going | On-going | Completed as per Program of Works
B.E. Dujali | Dujali | 2nd Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Adminsitration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Gamad/Clar | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 329064 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 36
B.E. Dujali | Dujali | 2nd Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Adminsitration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: |  | Actual: | 56% | Actual: | 56% | Actual: | 56% | Actual: | 84.15% | Actual: | 100%
B.E. Dujali | Dujali | 2nd Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Adminsitration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 6% | Slippage: | 6% | Slippage: | 6% | Slippage: | 1.55% | Slippage: | 0%
B.E. Dujali | Dujali | 2nd Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Adminsitration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed: | 2020-12-31
B.E. Dujali | Dujali | 2nd Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Adminsitration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started: | 2020-01-02
B.E. Dujali | Dujali | 2nd Eng'g. Dist. | Completed | 2020-06-08 | 2020-12-08 | 2020 | Contract | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 105 - Poblacion Dujali - Prk. 8 Dujali |  | GENERAL FUND CY 2020 | Maintenance | 8.2 | km | CBRMC | Project Cost: | 193371.11 | Target Completion Date: | 2020-12-12 | Program: | 193371.11 | Planned: | 5% | Planned: | 5% | Planned: | 5% | Planned: | 41.89% | Planned: | 100% | No. of Persons: | 2 | On-going | On-going | On-going | On-going | On-going | Completed as per Program of Works
B.E. Dujali | Dujali | 2nd Eng'g. Dist. | Completed | 2020-06-08 | 2020-12-08 | 2020 | Contract | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Maligro | Revised Completion Date: | 2021-01-08 | Allotment: | 193371.11 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 44
B.E. Dujali | Dujali | 2nd Eng'g. Dist. | Completed | 2020-06-08 | 2020-12-08 | 2020 | Contract | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: | Dujali Poblacion Farmer's Irrigator's Association, Inc. | No. of days suspended: | 27 | Disbursement: |  | Actual: | 5% | Actual: | 5% | Actual: | 5% | Actual: | 41.89% | Actual: | 100%
B.E. Dujali | Dujali | 2nd Eng'g. Dist. | Completed | 2020-06-08 | 2020-12-08 | 2020 | Contract | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: | 187 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
B.E. Dujali | Dujali | 2nd Eng'g. Dist. | Completed | 2020-06-08 | 2020-12-08 | 2020 | Contract | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed: | 2020-12-08
B.E. Dujali | Dujali | 2nd Eng'g. Dist. | Completed | 2020-06-08 | 2020-12-08 | 2020 | Contract | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started: | 2020-06-08
B.E. Dujali | Dujali | 2nd Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Adminsitration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 107 - Dujali - San Isidro |  | GENERAL FUND CY 2020 | Maintenance | 3 | km | MBA | Project Cost: | 112652.73 | Target Completion Date: | 2020-12-31 23:59 | Program: | 112652.73 | Planned: | 50% | Planned: | 50% | Planned: | 50% | Planned: | 82.4% | Planned: | 100% | No. of Persons: | 3 | On-going | On-going | On-going | On-going | On-going | Completed as per Program of Works
B.E. Dujali | Dujali | 2nd Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Adminsitration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Gamad/Clar | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 112652.73 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 30
B.E. Dujali | Dujali | 2nd Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Adminsitration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: |  | Actual: | 57% | Actual: | 57% | Actual: | 57% | Actual: | 81.6% | Actual: | 100%
B.E. Dujali | Dujali | 2nd Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Adminsitration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 7% | Slippage: | 7% | Slippage: | 7% | Slippage: | -0.8% | Slippage: | 0%
B.E. Dujali | Dujali | 2nd Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Adminsitration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed: | 2020-12-31
B.E. Dujali | Dujali | 2nd Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Adminsitration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started: | 2020-01-02
B.E. Dujali | Dujali | 2nd Eng'g. Dist. | On-going | 2020-09-11 |  | 2020 | Contract | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 107 - Dujali - San Isidro |  | GENERAL FUND CY 2020 | Maintenance | 3 | km | CBRMC | Project Cost: | 78482.06 | Target Completion Date: | 2021-03-11 | Program: | 78482.06 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: | 41.67% | No. of Persons: | 6 | PO #2020031411 - SAN ISIDRO FARMERS IRRIGATORS ASSN., INC. | PO #2020031411 - SAN ISIDRO FARMERS IRRIGATORS ASSN., INC. | PO #2020031411 - SAN ISIDRO FARMERS IRRIGATORS ASSN., INC. | PO #2020031411 - SAN ISIDRO FARMERS IRRIGATORS ASSN., INC. | PO #2020031411 - SAN ISIDRO FARMERS IRRIGATORS ASSN., INC. | On-going
B.E. Dujali | Dujali | 2nd Eng'g. Dist. | On-going | 2020-09-11 |  | 2020 | Contract | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Maligro | Revised Completion Date: |  | Allotment: | 78482.06 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 21
B.E. Dujali | Dujali | 2nd Eng'g. Dist. | On-going | 2020-09-11 |  | 2020 | Contract | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: | San Isidro Farmers Irrigators Association | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual: | 41.67%
B.E. Dujali | Dujali | 2nd Eng'g. Dist. | On-going | 2020-09-11 |  | 2020 | Contract | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: | 6 months | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
B.E. Dujali | Dujali | 2nd Eng'g. Dist. | On-going | 2020-09-11 |  | 2020 | Contract | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: |  | Date completed:
B.E. Dujali | Dujali | 2nd Eng'g. Dist. | On-going | 2020-09-11 |  | 2020 | Contract | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started: | 2020-09-11
B.E. Dujali | New Casay | 2nd Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Adminsitration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 108 - New Casay - Bugtong Talisay |  | GENERAL FUND CY 2020 | Maintenance |  | km | MBA | Project Cost: | 74294.5 | Target Completion Date: | 2020-12-31 23:59 | Program: | 74294.5 | Planned: | 50% | Planned: | 50% | Planned: | 50% | Planned: | 84.86% | Planned: | 100% | No. of Persons: | 4 | On-going | On-going | On-going | On-going | On-going | Completed as per Program of Works
B.E. Dujali | New Casay | 2nd Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Adminsitration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Gamad/Clar | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 74294.5 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 40
B.E. Dujali | New Casay | 2nd Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Adminsitration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: |  | Actual: | 50% | Actual: | 50% | Actual: | 50% | Actual: | 85.1% | Actual: | 100%
B.E. Dujali | New Casay | 2nd Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Adminsitration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0.24% | Slippage: | 0%
B.E. Dujali | New Casay | 2nd Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Adminsitration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed: | 2020-12-31
B.E. Dujali | New Casay | 2nd Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Adminsitration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started: | 2020-01-02
B.E. Dujali | New Casay | 2nd Eng'g. Dist. | Re-bid |  |  | 2020 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 108 - New Casay - Bugtong Talisay |  | GENERAL FUND CY 2020 | Maintenance |  | km | CBRMC | Project Cost: | 64596.78 | Target Completion Date: |  | Program: | 64596.78 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | For re-bid | For re-bid | For re-bid | For re-bid | For re-bid | Re-bid/ documents on process
B.E. Dujali | New Casay | 2nd Eng'g. Dist. | Re-bid |  |  | 2020 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Maligro | Revised Completion Date: |  | Allotment: | 64596.78 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
B.E. Dujali | New Casay | 2nd Eng'g. Dist. | Re-bid |  |  | 2020 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
B.E. Dujali | New Casay | 2nd Eng'g. Dist. | Re-bid |  |  | 2020 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
B.E. Dujali | New Casay | 2nd Eng'g. Dist. | Re-bid |  |  | 2020 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: |  | Date completed:
B.E. Dujali | New Casay | 2nd Eng'g. Dist. | Re-bid |  |  | 2020 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started:
B.E. Dujali | Magupising | 2nd Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Adminsitration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 113 - Dujali - Balisong - Magupising |  | GENERAL FUND CY 2020 | Maintenance | 5.52 | km | MBA | Project Cost: | 235776.07 | Target Completion Date: | 2020-12-31 23:59 | Program: | 235776.07 | Planned: | 50% | Planned: | 50% | Planned: | 50% | Planned: | 84.1% | Planned: | 100% | No. of Persons: | 3 | On-going | On-going | On-going | On-going | On-going | Completed as per Program of Works
B.E. Dujali | Magupising | 2nd Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Adminsitration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Gamad/Clar | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 235776.07 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 30
B.E. Dujali | Magupising | 2nd Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Adminsitration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: |  | Actual: | 55% | Actual: | 55% | Actual: | 55% | Actual: | 85.2% | Actual: | 100%
B.E. Dujali | Magupising | 2nd Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Adminsitration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 5% | Slippage: | 5% | Slippage: | 5% | Slippage: | 1.1% | Slippage: | 0%
B.E. Dujali | Magupising | 2nd Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Adminsitration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed: | 2020-12-31
B.E. Dujali | Magupising | 2nd Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Adminsitration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started: | 2020-01-02
B.E. Dujali | Magupising | 2nd Eng'g. Dist. | On-going | 2020-06-08 |  | 2020 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 113 - Dujali - Balisong - Magupising |  | GENERAL FUND CY 2020 | Maintenance | 5.52 | km | CBRMC | Project Cost: | 115911.95 | Target Completion Date: | 2020-12-12 | Program: | 115911.95 | Planned: | 5% | Planned: | 5% | Planned: | 5% | Planned: | 27.78% | Planned: | 55.5% | No. of Persons: | 2 | On-going | On-going | On-going | On-going | On-going | On-going
B.E. Dujali | Magupising | 2nd Eng'g. Dist. | On-going | 2020-06-08 |  | 2020 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Maligro | Revised Completion Date: | 2021-01-08 | Allotment: | 115911.95 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 2
B.E. Dujali | Magupising | 2nd Eng'g. Dist. | On-going | 2020-06-08 |  | 2020 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: | Dujali Poblacion Farmer's Irrigator's Association, Inc. | No. of days suspended: | 27 | Disbursement: |  | Actual: | 5% | Actual: | 5% | Actual: | 5% | Actual: | 27.78% | Actual: | 55.56%
B.E. Dujali | Magupising | 2nd Eng'g. Dist. | On-going | 2020-06-08 |  | 2020 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: | 187 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0.06%
B.E. Dujali | Magupising | 2nd Eng'g. Dist. | On-going | 2020-06-08 |  | 2020 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
B.E. Dujali | Magupising | 2nd Eng'g. Dist. | On-going | 2020-06-08 |  | 2020 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started: | 2020-06-08
B.E. Dujali | Dujali | 2nd Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Adminsitration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 117 - Dujali - Pawas - San Vicente |  | GENERAL FUND CY 2020 | Maintenance | 4.42 | km | MBA | Project Cost: | 141544.99 | Target Completion Date: | 2020-12-31 23:59 | Program: | 141544.99 | Planned: | 50% | Planned: | 50% | Planned: | 50% | Planned: | 86.9% | Planned: | 100% | No. of Persons: | 3 | On-going | On-going | On-going | On-going | On-going | Completed as per Program of Works
B.E. Dujali | Dujali | 2nd Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Adminsitration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Gamad/Clar | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 141544.99 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 30
B.E. Dujali | Dujali | 2nd Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Adminsitration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: |  | Actual: | 50% | Actual: | 50% | Actual: | 50% | Actual: | 87.1% | Actual: | 100%
B.E. Dujali | Dujali | 2nd Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Adminsitration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0.2% | Slippage: | 0%
B.E. Dujali | Dujali | 2nd Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Adminsitration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed: | 2020-12-31
B.E. Dujali | Dujali | 2nd Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Adminsitration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started: | 2020-01-02
B.E. Dujali | Dujali | 2nd Eng'g. Dist. | For Implementation |  |  | 2020 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 117 - Dujali - Pawas - San Vicente |  | GENERAL FUND CY 2020 | Maintenance | 4.42 | km | CBRMC | Project Cost: | 140060.27 | Target Completion Date: |  | Program: | 140060.27 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Abstract #320201344 -For post qualification | Abstract #320201344 -For post qualification | Abstract #320201344 -For post qualification | Abstract #320201344 -For post qualification | Abstract #320201344 -For post qualification | For implementation
B.E. Dujali | Dujali | 2nd Eng'g. Dist. | For Implementation |  |  | 2020 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Maligro | Revised Completion Date: |  | Allotment: | 140060.27 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
B.E. Dujali | Dujali | 2nd Eng'g. Dist. | For Implementation |  |  | 2020 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
B.E. Dujali | Dujali | 2nd Eng'g. Dist. | For Implementation |  |  | 2020 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
B.E. Dujali | Dujali | 2nd Eng'g. Dist. | For Implementation |  |  | 2020 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: |  | Date completed:
B.E. Dujali | Dujali | 2nd Eng'g. Dist. | For Implementation |  |  | 2020 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started:
Sto. Tomas | Salvacion | 2nd Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Adminsitration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 118- Jct. Salvacion - San Vicente - Cabay-angan |  | GENERAL FUND CY 2020 | Maintenance | 3.45 | km | MBA | Project Cost: | 168583.81 | Target Completion Date: | 2020-12-31 23:59 | Program: | 168583.81 | Planned: | 50% | Planned: | 50% | Planned: | 50% | Planned: | 85.15% | Planned: | 100% | No. of Persons: | 3 | On-going | On-going | On-going | On-going | On-going | Completed as per Program of Works
Sto. Tomas | Salvacion | 2nd Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Adminsitration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Gamad/Clar | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 168583.81 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 27
Sto. Tomas | Salvacion | 2nd Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Adminsitration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: |  | Actual: | 55% | Actual: | 55% | Actual: | 55% | Actual: | 84.9% | Actual: | 100%
Sto. Tomas | Salvacion | 2nd Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Adminsitration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 5% | Slippage: | 5% | Slippage: | 5% | Slippage: | -0.25% | Slippage: | 0%
Sto. Tomas | Salvacion | 2nd Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Adminsitration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed: | 2020-12-31
Sto. Tomas | Salvacion | 2nd Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Adminsitration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started: | 2020-01-02
Sto. Tomas | Salvacion | 2nd Eng'g. Dist. | Procurement on process |  |  | 2020 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 118- Jct. Salvacion - San Vicente - Cabay-angan |  | GENERAL FUND CY 2020 | Maintenance | 3.45 | km | CBRMC | Project Cost: | 158775.23 | Target Completion Date: |  | Program: | 158775.23 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Abstract #320201396 - For post qualification | Abstract #320201396 - For post qualification | Abstract #320201396 - For post qualification | Abstract #320201396 - For post qualification | Abstract #320201396 - For post qualification | Procurement on process
Sto. Tomas | Salvacion | 2nd Eng'g. Dist. | Procurement on process |  |  | 2020 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Maligro | Revised Completion Date: |  | Allotment: | 158775.23 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
Sto. Tomas | Salvacion | 2nd Eng'g. Dist. | Procurement on process |  |  | 2020 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
Sto. Tomas | Salvacion | 2nd Eng'g. Dist. | Procurement on process |  |  | 2020 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Sto. Tomas | Salvacion | 2nd Eng'g. Dist. | Procurement on process |  |  | 2020 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: |  | Date completed:
Sto. Tomas | Salvacion | 2nd Eng'g. Dist. | Procurement on process |  |  | 2020 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started:
Sto. Tomas | Casig-ang | 2nd Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Adminsitration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 123- Bacali - Casig-ang - Libertad |  | GENERAL FUND CY 2020 | Maintenance |  | km | MBA | Project Cost: | 167836.14 | Target Completion Date: | 2020-12-31 23:59 | Program: | 167836.14 | Planned: | 50% | Planned: | 50% | Planned: | 50% | Planned: | 84.12% | Planned: | 100% | No. of Persons: | 3 | On-going | On-going | On-going | On-going | On-going | Completed as per Program of Works
Sto. Tomas | Casig-ang | 2nd Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Adminsitration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Gamad/Clar | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 167836.14 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 60
Sto. Tomas | Casig-ang | 2nd Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Adminsitration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: |  | Actual: | 58% | Actual: | 58% | Actual: | 58% | Actual: | 83.6% | Actual: | 100%
Sto. Tomas | Casig-ang | 2nd Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Adminsitration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 8% | Slippage: | 8% | Slippage: | 8% | Slippage: | -0.52% | Slippage: | 0%
Sto. Tomas | Casig-ang | 2nd Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Adminsitration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed: | 2020-12-31
Sto. Tomas | Casig-ang | 2nd Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Adminsitration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started: | 2020-01-02
Sto. Tomas | Casig-ang | 2nd Eng'g. Dist. | For Implementation |  |  | 2020 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 123- Bacali - Casig-ang - Libertad |  | GENERAL FUND CY 2020 | Maintenance |  | km | CBRMC | Project Cost: | 131608.37 | Target Completion Date: |  | Program: | 131608.37 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Abstract #320201449 - For post qualification | Abstract #320201449 - For post qualification | Abstract #320201449 - For post qualification | Abstract #320201449 - For post qualification | Abstract #320201449 - For post qualification | For implementation
Sto. Tomas | Casig-ang | 2nd Eng'g. Dist. | For Implementation |  |  | 2020 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Maligro | Revised Completion Date: |  | Allotment: | 131608.37 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
Sto. Tomas | Casig-ang | 2nd Eng'g. Dist. | For Implementation |  |  | 2020 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
Sto. Tomas | Casig-ang | 2nd Eng'g. Dist. | For Implementation |  |  | 2020 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Sto. Tomas | Casig-ang | 2nd Eng'g. Dist. | For Implementation |  |  | 2020 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: |  | Date completed:
Sto. Tomas | Casig-ang | 2nd Eng'g. Dist. | For Implementation |  |  | 2020 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started:
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Adminsitration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 124 - Kinamayan - Moslog - Mahayag |  | GENERAL FUND CY 2020 | Maintenance |  | km | MBA | Project Cost: | 114628.54 | Target Completion Date: | 2020-12-31 23:59 | Program: | 114628.54 | Planned: | 50% | Planned: | 50% | Planned: | 50% | Planned: | 82.6% | Planned: | 100% | No. of Persons: | 3 | On-going | On-going | On-going | On-going | On-going | Completed as per Program of Works
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Adminsitration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Gamad/Clar | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 114628.54 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 24
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Adminsitration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: |  | Actual: | 50% | Actual: | 50% | Actual: | 50% | Actual: | 83.6% | Actual: | 100%
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Adminsitration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 1% | Slippage: | 0%
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Adminsitration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed: | 2020-12-31
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Adminsitration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started: | 2020-01-02
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | Procurement on process |  |  | 2020 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 124 - Kinamayan - Moslog - Mahayag |  | GENERAL FUND CY 2020 | Maintenance |  | km | CBRMC | Project Cost: | 91159.92 | Target Completion Date: |  | Program: | 91159.92 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | For re-bid | For re-bid | For re-bid | For re-bid | For re-bid | Procurement on process
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | Procurement on process |  |  | 2020 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Maligro | Revised Completion Date: |  | Allotment: | 91159.92 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | Procurement on process |  |  | 2020 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | Procurement on process |  |  | 2020 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | Procurement on process |  |  | 2020 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: |  | Date completed:
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | Procurement on process |  |  | 2020 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started:
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Adminsitration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 126 - Kinamayan - Lunga-og |  | GENERAL FUND CY 2020 | Maintenance |  | km | MBA | Project Cost: | 100416.26 | Target Completion Date: | 2020-12-31 23:59 | Program: | 100416.26 | Planned: | 50% | Planned: | 50% | Planned: | 50% | Planned: | 81.6% | Planned: | 100% | No. of Persons: | 3 | On-going | On-going | On-going | On-going | On-going | Completed as per Program of Works
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Adminsitration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Gamad/Clar | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 100416.26 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 24
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Adminsitration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: |  | Actual: | 52% | Actual: | 52% | Actual: | 52% | Actual: | 84.12% | Actual: | 100%
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Adminsitration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 2% | Slippage: | 2% | Slippage: | 2% | Slippage: | 2.52% | Slippage: | 0%
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Adminsitration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed: | 2020-12-31
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Adminsitration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started: | 2020-01-02
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | Completed | 2020-06-15 | 2020-12-15 | 2020 | Contract | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 126 - Kinamayan - Lunga-og |  | GENERAL FUND CY 2020 | Maintenance |  | km | CBRMC | Project Cost: | 64596.78 | Target Completion Date: | 2020-12-15 23:59 | Program: | 64596.78 | Planned: | 5% | Planned: | 5% | Planned: | 5% | Planned: | 41.87% | Planned: | 100% | No. of Persons: | 2 | On-going | On-going | On-going | On-going | On-going | Completed as per Program of Works
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | Completed | 2020-06-15 | 2020-12-15 | 2020 | Contract | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Maligro | Revised Completion Date: |  | Allotment: | 64596.78 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 20
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | Completed | 2020-06-15 | 2020-12-15 | 2020 | Contract | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: | Lunga-og Tribal Association | No. of days suspended: |  | Disbursement: |  | Actual: | 5% | Actual: | 5% | Actual: | 5% | Actual: | 41.87% | Actual: | 100%
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | Completed | 2020-06-15 | 2020-12-15 | 2020 | Contract | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: | 184 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | Completed | 2020-06-15 | 2020-12-15 | 2020 | Contract | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed: | 2020-12-15
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | Completed | 2020-06-15 | 2020-12-15 | 2020 | Contract | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started: | 2020-06-15
Sto. Tomas | La Libertad | 2nd Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Adminsitration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 128 - Prk. Apitong - Upper Balisong - Dalisay |  | GENERAL FUND CY 2020 | Maintenance | 4.6 | km | MBA | Project Cost: | 150598.24 | Target Completion Date: | 2020-12-31 23:59 | Program: | 150598.24 | Planned: | 10% | Planned: | 10% | Planned: | 10% | Planned: | 82.5% | Planned: | 100% | No. of Persons: | 3 | On-going | On-going | On-going | On-going | On-going | Completed as per Program of Works
Sto. Tomas | La Libertad | 2nd Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Adminsitration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Gamad/Clar | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 150598.24 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 24
Sto. Tomas | La Libertad | 2nd Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Adminsitration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: |  | Actual: | 9% | Actual: | 9% | Actual: | 9% | Actual: | 84.6% | Actual: | 100%
Sto. Tomas | La Libertad | 2nd Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Adminsitration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | -1% | Slippage: | -1% | Slippage: | -1% | Slippage: | 2.1% | Slippage: | 0%
Sto. Tomas | La Libertad | 2nd Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Adminsitration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed: | 2020-12-31
Sto. Tomas | La Libertad | 2nd Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Adminsitration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started: | 2020-01-02
Sto. Tomas | La Libertad | 2nd Eng'g. Dist. | Completed | 2020-06-15 | 2020-12-15 | 2020 | Contract | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 128 - Prk. Apitong - Upper Balisong - Dalisay |  | GENERAL FUND CY 2020 | Maintenance | 4.6 | km | CBRMC | Project Cost: | 142475.11 | Target Completion Date: | 2020-12-15 23:59 | Program: | 142475.11 | Planned: | 5% | Planned: | 5% | Planned: | 5% | Planned: | 41.72% | Planned: | 100% | No. of Persons: | 4 | On-going | On-going | On-going | On-going | On-going | Completed as per Program of Works
Sto. Tomas | La Libertad | 2nd Eng'g. Dist. | Completed | 2020-06-15 | 2020-12-15 | 2020 | Contract | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Maligro | Revised Completion Date: |  | Allotment: | 142475.11 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 24
Sto. Tomas | La Libertad | 2nd Eng'g. Dist. | Completed | 2020-06-15 | 2020-12-15 | 2020 | Contract | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: | Lunga-og Tribal Association | No. of days suspended: |  | Disbursement: |  | Actual: | 5% | Actual: | 5% | Actual: | 5% | Actual: | 41.72% | Actual: | 100%
Sto. Tomas | La Libertad | 2nd Eng'g. Dist. | Completed | 2020-06-15 | 2020-12-15 | 2020 | Contract | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: | 184 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Sto. Tomas | La Libertad | 2nd Eng'g. Dist. | Completed | 2020-06-15 | 2020-12-15 | 2020 | Contract | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed: | 2020-12-15
Sto. Tomas | La Libertad | 2nd Eng'g. Dist. | Completed | 2020-06-15 | 2020-12-15 | 2020 | Contract | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started: | 2020-06-15
Sto. Tomas | Esperanza | 2nd Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Adminsitration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 130 - Los Amigos 1 - Esperanza - Los Amigos 2 |  | GENERAL FUND CY 2020 | Maintenance | 3.59 | km | MBA | Project Cost: | 97116.27 | Target Completion Date: | 2020-12-31 23:59 | Program: | 97116.27 | Planned: | 50% | Planned: | 50% | Planned: | 50% | Planned: | 82.51% | Planned: | 100% | No. of Persons: | 3 | On-going | On-going | On-going | On-going | On-going | Completed as per Program of Works
Sto. Tomas | Esperanza | 2nd Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Adminsitration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Gamad/Clar | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 97116.27 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 27
Sto. Tomas | Esperanza | 2nd Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Adminsitration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: |  | Actual: | 55% | Actual: | 55% | Actual: | 55% | Actual: | 82.4% | Actual: | 100%
Sto. Tomas | Esperanza | 2nd Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Adminsitration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 5% | Slippage: | 5% | Slippage: | 5% | Slippage: | -0.11% | Slippage: | 0%
Sto. Tomas | Esperanza | 2nd Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Adminsitration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed: | 2020-12-31
Sto. Tomas | Esperanza | 2nd Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Adminsitration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started: | 2020-01-02
Sto. Tomas | Esperanza | 2nd Eng'g. Dist. | On-going | 2020-08-31 |  | 2020 | Contract | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 130 - Los Amigos 1 - Esperanza - Los Amigos 2 |  | GENERAL FUND CY 2020 | Maintenance | 3.59 | km | CBRMC | Project Cost: | 131608.37 | Target Completion Date: | 2020-02-21 | Program: | 131608.37 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: | 41.88% | No. of Persons: | 4 | PO #2020031351 - LOS AMIGOS GROUP OF WOMEN & FARMERS ASSN. | PO #2020031351 - LOS AMIGOS GROUP OF WOMEN & FARMERS ASSN. | PO #2020031351 - LOS AMIGOS GROUP OF WOMEN & FARMERS ASSN. | PO #2020031351 - LOS AMIGOS GROUP OF WOMEN & FARMERS ASSN. | PO #2020031351 - LOS AMIGOS GROUP OF WOMEN & FARMERS ASSN. | On-going
Sto. Tomas | Esperanza | 2nd Eng'g. Dist. | On-going | 2020-08-31 |  | 2020 | Contract | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Maligro | Revised Completion Date: |  | Allotment: | 131608.37 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 16
Sto. Tomas | Esperanza | 2nd Eng'g. Dist. | On-going | 2020-08-31 |  | 2020 | Contract | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: | Los Amigos Group of Women abd Farmers Association | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual: | 41.88%
Sto. Tomas | Esperanza | 2nd Eng'g. Dist. | On-going | 2020-08-31 |  | 2020 | Contract | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: | 6 months | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Sto. Tomas | Esperanza | 2nd Eng'g. Dist. | On-going | 2020-08-31 |  | 2020 | Contract | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: |  | Date completed:
Sto. Tomas | Esperanza | 2nd Eng'g. Dist. | On-going | 2020-08-31 |  | 2020 | Contract | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started: | 2020-08-31
Sto. Tomas | Lunga-og | 2nd Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Adminsitration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 131 - Mugas - Lanatad |  | GENERAL FUND CY 2020 | Maintenance |  | km | MBA | Project Cost: | 65482.21 | Target Completion Date: | 2020-12-31 23:59 | Program: | 65482.21 | Planned: | 50% | Planned: | 50% | Planned: | 50% | Planned: | 84.98% | Planned: | 100% | No. of Persons: | 3 | On-going | On-going | On-going | On-going | On-going | Completed as per Program of Works
Sto. Tomas | Lunga-og | 2nd Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Adminsitration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Gamad/Clar | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 65482.21 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 12
Sto. Tomas | Lunga-og | 2nd Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Adminsitration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: |  | Actual: | 50% | Actual: | 50% | Actual: | 50% | Actual: | 85.4% | Actual: | 100%
Sto. Tomas | Lunga-og | 2nd Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Adminsitration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0.42% | Slippage: | 0%
Sto. Tomas | Lunga-og | 2nd Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Adminsitration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed: | 2020-12-31
Sto. Tomas | Lunga-og | 2nd Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Adminsitration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started: | 2020-01-02
Sto. Tomas | Lunga-og | 2nd Eng'g. Dist. | On-going | 2020-04-02 |  | 2020 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 131 - Mugas - Lanatad |  | GENERAL FUND CY 2020 | Maintenance |  | km | CBRMC | Project Cost: | 31996.54 | Target Completion Date: | 2021-01-20 | Program: | 31996.54 | Planned: |  | Planned: |  | Planned: |  | Planned: | 10.1% | Planned: | 41.64% | No. of Persons: | 6 | Purchase Order # 2020030961 (Katipunan Pantaron Irrigator's Association) | Purchase Order # 2020030961 (Katipunan Pantaron Irrigator's Association) | Purchase Order # 2020030961 (Katipunan Pantaron Irrigator's Association) | On-going | On-going | On-going
Sto. Tomas | Lunga-og | 2nd Eng'g. Dist. | On-going | 2020-04-02 |  | 2020 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Maligro | Revised Completion Date: |  | Allotment: | 31996.54 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 20
Sto. Tomas | Lunga-og | 2nd Eng'g. Dist. | On-going | 2020-04-02 |  | 2020 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: | Katipunan Pantaron Irrigator's Association | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: | 10.1% | Actual: | 41.64%
Sto. Tomas | Lunga-og | 2nd Eng'g. Dist. | On-going | 2020-04-02 |  | 2020 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: | 6 months | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Sto. Tomas | Lunga-og | 2nd Eng'g. Dist. | On-going | 2020-04-02 |  | 2020 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: |  | Date completed:
Sto. Tomas | Lunga-og | 2nd Eng'g. Dist. | On-going | 2020-04-02 |  | 2020 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started: | 2020-07-20
Sto. Tomas | Lunga-og | 2nd Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Adminsitration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 132 - Mugas - Lunga-og |  | GENERAL FUND CY 2020 | Maintenance | 2.68 | km | MBA | Project Cost: | 96490.97 | Target Completion Date: | 2020-12-31 23:59 | Program: | 96490.97 | Planned: | 50% | Planned: | 50% | Planned: | 50% | Planned: | 82.4% | Planned: | 100% | No. of Persons: | 6 | On-going | On-going | On-going | On-going | On-going | Completed as per Program of Works
Sto. Tomas | Lunga-og | 2nd Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Adminsitration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Gamad/Clar | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 96490.97 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 20
Sto. Tomas | Lunga-og | 2nd Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Adminsitration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: |  | Actual: | 50% | Actual: | 50% | Actual: | 50% | Actual: | 85.1% | Actual: | 100%
Sto. Tomas | Lunga-og | 2nd Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Adminsitration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 2.7% | Slippage: | 0%
Sto. Tomas | Lunga-og | 2nd Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Adminsitration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed: | 2020-12-31
Sto. Tomas | Lunga-og | 2nd Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Adminsitration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started: | 2020-01-02
Sto. Tomas | Lunga-og | 2nd Eng'g. Dist. | Completed | 2020-06-15 | 2020-12-15 | 2020 | Contract | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 132 - Mugas - Lunga-og |  | GENERAL FUND CY 2020 | Maintenance | 2.68 | km | CBRMC | Project Cost: | 74256.11 | Target Completion Date: | 2020-12-15 23:59 | Program: | 74256.11 | Planned: |  | Planned: |  | Planned: |  | Planned: | 42.13% | Planned: | 100% | No. of Persons: | 3 | On-going | On-going | On-going | On-going | On-going | Completed as per Program of Works
Sto. Tomas | Lunga-og | 2nd Eng'g. Dist. | Completed | 2020-06-15 | 2020-12-15 | 2020 | Contract | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Maligro | Revised Completion Date: | 2021-01-11 23:59 | Allotment: | 74256.11 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 18
Sto. Tomas | Lunga-og | 2nd Eng'g. Dist. | Completed | 2020-06-15 | 2020-12-15 | 2020 | Contract | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: | Lunga-og Tribal Association | No. of days suspended: | 27 | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: | 42.13% | Actual: | 100%
Sto. Tomas | Lunga-og | 2nd Eng'g. Dist. | Completed | 2020-06-15 | 2020-12-15 | 2020 | Contract | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: | 184 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Sto. Tomas | Lunga-og | 2nd Eng'g. Dist. | Completed | 2020-06-15 | 2020-12-15 | 2020 | Contract | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed: | 2020-12-15
Sto. Tomas | Lunga-og | 2nd Eng'g. Dist. | Completed | 2020-06-15 | 2020-12-15 | 2020 | Contract | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started: | 2020-06-15
Sto. Tomas | New Katipunan | 2nd Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Adminsitration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 134 - New Katipunan - Pantaron |  | GENERAL FUND CY 2020 | Maintenance |  | km | MBA | Project Cost: | 71748.41 | Target Completion Date: | 2020-12-31 23:59 | Program: | 71748.41 | Planned: | 50% | Planned: | 50% | Planned: | 50% | Planned: | 84.86% | Planned: | 100% | No. of Persons: | 2 | On-going | On-going | On-going | On-going | On-going | Completed as per Program of Works
Sto. Tomas | New Katipunan | 2nd Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Adminsitration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Gamad/Clar | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 71748.41 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 20
Sto. Tomas | New Katipunan | 2nd Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Adminsitration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: |  | Actual: | 51% | Actual: | 51% | Actual: | 51% | Actual: | 82.1% | Actual: | 100%
Sto. Tomas | New Katipunan | 2nd Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Adminsitration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 1% | Slippage: | 1% | Slippage: | 1% | Slippage: | -2.76% | Slippage: | 0%
Sto. Tomas | New Katipunan | 2nd Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Adminsitration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed: | 2020-12-31
Sto. Tomas | New Katipunan | 2nd Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Adminsitration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started: | 2020-01-02
Sto. Tomas | New Katipunan | 2nd Eng'g. Dist. | On-going | 2020-07-02 |  | 2020 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 134 - New Katipunan - Pantaron |  | GENERAL FUND CY 2020 | Maintenance |  | km | CBRMC | Project Cost: | 53126.32 | Target Completion Date: | 2021-01-20 | Program: | 53126.32 | Planned: |  | Planned: |  | Planned: |  | Planned: | 10% | Planned: | 41.04% | No. of Persons: |  | Purchase Order # 2020030964 (Katipunan Pantaron Irrigator's Association) | Purchase Order # 2020030964 (Katipunan Pantaron Irrigator's Association) | Purchase Order # 2020030964 (Katipunan Pantaron Irrigator's Association) | On-going | On-going | On-going
Sto. Tomas | New Katipunan | 2nd Eng'g. Dist. | On-going | 2020-07-02 |  | 2020 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Maligro | Revised Completion Date: |  | Allotment: | 53126.32 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
Sto. Tomas | New Katipunan | 2nd Eng'g. Dist. | On-going | 2020-07-02 |  | 2020 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: | Katipunan Pantaron Irrigator's Association | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: | 10% | Actual: | 41.04%
Sto. Tomas | New Katipunan | 2nd Eng'g. Dist. | On-going | 2020-07-02 |  | 2020 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: | 6 months | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Sto. Tomas | New Katipunan | 2nd Eng'g. Dist. | On-going | 2020-07-02 |  | 2020 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: |  | Date completed:
Sto. Tomas | New Katipunan | 2nd Eng'g. Dist. | On-going | 2020-07-02 |  | 2020 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started: | 2020-07-02
Sto. Tomas | New Katipunan | 2nd Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Adminsitration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 135 - Sto. Tomas - Bdry. Mamacao |  | GENERAL FUND CY 2020 | Maintenance | 4.9 | km | MBA | Project Cost: | 195671.17 | Target Completion Date: | 2020-12-31 23:59 | Program: | 195671.17 | Planned: | 50% | Planned: | 50% | Planned: | 50% | Planned: | 82.45% | Planned: | 100% | No. of Persons: | 3 | On-going | On-going | On-going | On-going | On-going | Completed as per Program of Works
Sto. Tomas | New Katipunan | 2nd Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Adminsitration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Gamad/Clar | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 195671.17 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 33
Sto. Tomas | New Katipunan | 2nd Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Adminsitration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: |  | Actual: | 52% | Actual: | 52% | Actual: | 52% | Actual: | 83.4% | Actual: | 100%
Sto. Tomas | New Katipunan | 2nd Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Adminsitration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 2% | Slippage: | 2% | Slippage: | 2% | Slippage: | 0.95% | Slippage: | 0%
Sto. Tomas | New Katipunan | 2nd Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Adminsitration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed: | 2020-12-31
Sto. Tomas | New Katipunan | 2nd Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Adminsitration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started: | 2020-01-02
Sto. Tomas | New Katipunan | 2nd Eng'g. Dist. | On-going | 2020-08-05 |  | 2020 | Contract | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 135 - Sto. Tomas - Bdry. Mamacao |  | GENERAL FUND CY 2020 | Maintenance | 4.9 | km | CBRMC | Project Cost: | 116515.66 | Target Completion Date: | 2021-02-05 | Program: | 116515.66 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: | 41.79% | No. of Persons: | 6 | PO #2020031353 - KATIPUNAN PANTARON IRRIGATORS ASSN. | PO #2020031353 - KATIPUNAN PANTARON IRRIGATORS ASSN. | PO #2020031353 - KATIPUNAN PANTARON IRRIGATORS ASSN. | PO #2020031353 - KATIPUNAN PANTARON IRRIGATORS ASSN. | PO #2020031353 - KATIPUNAN PANTARON IRRIGATORS ASSN. | On-going
Sto. Tomas | New Katipunan | 2nd Eng'g. Dist. | On-going | 2020-08-05 |  | 2020 | Contract | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Maligro | Revised Completion Date: |  | Allotment: | 116515.66 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 18
Sto. Tomas | New Katipunan | 2nd Eng'g. Dist. | On-going | 2020-08-05 |  | 2020 | Contract | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: | Katipunan Pantaron Irrigator's | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual: | 41.79%
Sto. Tomas | New Katipunan | 2nd Eng'g. Dist. | On-going | 2020-08-05 |  | 2020 | Contract | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: | 6 months | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Sto. Tomas | New Katipunan | 2nd Eng'g. Dist. | On-going | 2020-08-05 |  | 2020 | Contract | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: |  | Date completed:
Sto. Tomas | New Katipunan | 2nd Eng'g. Dist. | On-going | 2020-08-05 |  | 2020 | Contract | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started: | 2020-08-05
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Adminsitration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 136 - Fd. Rd. 3 - San Jose |  | GENERAL FUND CY 2020 | Maintenance | 4.55 | km | MBA | Project Cost: | 176994.35 | Target Completion Date: | 2020-12-31 23:59 | Program: | 176994.35 | Planned: | 50% | Planned: | 50% | Planned: | 50% | Planned: | 84.9% | Planned: | 100% | No. of Persons: | 2 | On-going | On-going | On-going | On-going | On-going | Completed as per Program of Works
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Adminsitration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Gamad/Clar | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 176994.35 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 10
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Adminsitration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: |  | Actual: | 55% | Actual: | 55% | Actual: | 55% | Actual: | 85.4% | Actual: | 100%
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Adminsitration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 5% | Slippage: | 5% | Slippage: | 5% | Slippage: | 0.5% | Slippage: | 0%
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Adminsitration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed: | 2020-12-31
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Adminsitration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started: | 2020-01-02
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | On-going | 2020-08-05 |  | 2020 | Contract | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 136 - Fd. Rd. 3 - San Jose |  | GENERAL FUND CY 2020 | Maintenance | 4.55 | km | CBRMC | Project Cost: | 112893.42 | Target Completion Date: | 2021-02-05 | Program: | 112893.42 | Planned: |  | Planned: |  | Planned: |  | Planned: | 42.25% | Planned: | 42.25% | No. of Persons: | 3 | Purchase Order # 2020030974 (Brgy. San Jose Upland Farmer's Assocaition) | Purchase Order # 2020030974 (Brgy. San Jose Upland Farmer's Assocaition) | Purchase Order # 2020030974 (Brgy. San Jose Upland Farmer's Assocaition) | On-going | On-going | On-going
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | On-going | 2020-08-05 |  | 2020 | Contract | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Maligro | Revised Completion Date: |  | Allotment: | 112893.42 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 66
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | On-going | 2020-08-05 |  | 2020 | Contract | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: | Brgy. San Jose Upland Farmer's Assocaition | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: | 42.25% | Actual: | 42.25%
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | On-going | 2020-08-05 |  | 2020 | Contract | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: | 6 months | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | On-going | 2020-08-05 |  | 2020 | Contract | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: |  | Date completed:
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | On-going | 2020-08-05 |  | 2020 | Contract | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started: | 2020-08-05
Sto. Tomas | Bobongon | 2nd Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Adminsitration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 139 - Nafco - Bobongon |  | GENERAL FUND CY 2020 | Maintenance |  | km | MBA | Project Cost: | 89179.68 | Target Completion Date: | 2020-12-31 23:59 | Program: | 89179.68 | Planned: | 50% | Planned: | 50% | Planned: | 50% | Planned: | 84.61% | Planned: | 100% | No. of Persons: | 3 | On-going | On-going | On-going | On-going | On-going | Completed as per Program of Works
Sto. Tomas | Bobongon | 2nd Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Adminsitration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Gamad/Clar | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 89179.68 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 56
Sto. Tomas | Bobongon | 2nd Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Adminsitration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: |  | Actual: | 55% | Actual: | 55% | Actual: | 55% | Actual: | 85.12% | Actual: | 100%
Sto. Tomas | Bobongon | 2nd Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Adminsitration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 5% | Slippage: | 5% | Slippage: | 5% | Slippage: | 0.51% | Slippage: | 0%
Sto. Tomas | Bobongon | 2nd Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Adminsitration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed: | 2020-12-31
Sto. Tomas | Bobongon | 2nd Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Adminsitration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started: | 2020-01-02
Sto. Tomas | Bobongon | 2nd Eng'g. Dist. | Completed | 2020-08-03 | 2020-12-09 | 2020 | Contract | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 139 - Nafco - Bobongon |  | GENERAL FUND CY 2020 | Maintenance |  | km | CBRMC | Project Cost: | 80293.17 | Target Completion Date: | 2021-02-03 | Program: | 80293.17 | Planned: |  | Planned: |  | Planned: |  | Planned: | 42.5% | Planned: | 100% | No. of Persons: | 2 | Purchase Order # 2020030968 (Bobongon Rural Waterworks & Sanitation Association, Inc.) | Purchase Order # 2020030968 (Bobongon Rural Waterworks & Sanitation Association, Inc.) | Purchase Order # 2020030968 (Bobongon Rural Waterworks & Sanitation Association, Inc.) | On-going | On-going | Completed as per Program of Works
Sto. Tomas | Bobongon | 2nd Eng'g. Dist. | Completed | 2020-08-03 | 2020-12-09 | 2020 | Contract | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Maligro | Revised Completion Date: |  | Allotment: | 80293.17 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 2
Sto. Tomas | Bobongon | 2nd Eng'g. Dist. | Completed | 2020-08-03 | 2020-12-09 | 2020 | Contract | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: | Bobongon Rural Waterworks & Sanitation Association, Inc. | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: | 42.5% | Actual: | 100%
Sto. Tomas | Bobongon | 2nd Eng'g. Dist. | Completed | 2020-08-03 | 2020-12-09 | 2020 | Contract | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: | 6 months | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Sto. Tomas | Bobongon | 2nd Eng'g. Dist. | Completed | 2020-08-03 | 2020-12-09 | 2020 | Contract | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: |  | Date completed: | 2020-12-09
Sto. Tomas | Bobongon | 2nd Eng'g. Dist. | Completed | 2020-08-03 | 2020-12-09 | 2020 | Contract | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started: | 2020-08-03
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Adminsitration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 146 - Bdry. Tagum - Crossing Kinamayan Sto. Tomas |  | GENERAL FUND CY 2020 | Maintenance |  | km | MBA | Project Cost: | 790874.1 | Target Completion Date: | 2020-12-31 23:59 | Program: | 790874.1 | Planned: | 50% | Planned: | 50% | Planned: | 50% | Planned: | 82.48% | Planned: | 100% | No. of Persons: | 3 | On-going | On-going | On-going | On-going | On-going | Completed as per Program of Works
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Adminsitration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Gamad/Clar | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 790874.1 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 66
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Adminsitration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: |  | Actual: | 50% | Actual: | 50% | Actual: | 50% | Actual: | 82.4% | Actual: | 100%
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Adminsitration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | -0.08% | Slippage: | 0%
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Adminsitration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed: | 2020-12-31
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Adminsitration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started: | 2020-01-02
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | On-going | 2020-08-21 |  | 2020 | Contract | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 146 - Bdry. Tagum - Crossing Kinamayan Sto. Tomas |  | GENERAL FUND CY 2020 | Maintenance |  | km | CBRMC | Project Cost: | 429840.12 | Target Completion Date: | 2021-05-21 | Program: | 429840.12 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: | 27.71% | No. of Persons: | 4 | PO #2020031407 - LOS AMIGOS GROUP OF WOMEN & FARMERS ASSN. | PO #2020031407 - LOS AMIGOS GROUP OF WOMEN & FARMERS ASSN. | PO #2020031407 - LOS AMIGOS GROUP OF WOMEN & FARMERS ASSN. | PO #2020031407 - LOS AMIGOS GROUP OF WOMEN & FARMERS ASSN. | PO #2020031407 - LOS AMIGOS GROUP OF WOMEN & FARMERS ASSN. | On-going
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | On-going | 2020-08-21 |  | 2020 | Contract | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Maligro | Revised Completion Date: |  | Allotment: | 429840.12 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 84
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | On-going | 2020-08-21 |  | 2020 | Contract | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: | Bobongon Rural Waterworks & Sanitation Association, Inc. | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual: | 27.71%
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | On-going | 2020-08-21 |  | 2020 | Contract | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: | 6 months | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | On-going | 2020-08-21 |  | 2020 | Contract | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: |  | Date completed:
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | On-going | 2020-08-21 |  | 2020 | Contract | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started: | 2020-08-21
Sto. Tomas | Magwawa | 2nd Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Adminsitration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 151 - San Jose - Sitio Mahayahay, Magwawa |  | GENERAL FUND CY 2020 | Maintenance | 0.84 | km | MBA | Project Cost: | 22943.54 | Target Completion Date: | 2020-12-31 23:59 | Program: | 22943.54 | Planned: | 50% | Planned: | 57.05% | Planned: | 57.05% | Planned: | 81.5% | Planned: | 100% | No. of Persons: | 3 | On-going | On-going | On-going | On-going | On-going | Completed as per Program of Works
Sto. Tomas | Magwawa | 2nd Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Adminsitration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Gamad/Clar | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 22943.54 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 18
Sto. Tomas | Magwawa | 2nd Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Adminsitration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: |  | Actual: | 50% | Actual: | 58.79% | Actual: | 58.79% | Actual: | 82.4% | Actual: | 100%
Sto. Tomas | Magwawa | 2nd Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Adminsitration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 1.74% | Slippage: | 1.74% | Slippage: | 0.9% | Slippage: | 0%
Sto. Tomas | Magwawa | 2nd Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Adminsitration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed: | 2020-12-31
Sto. Tomas | Magwawa | 2nd Eng'g. Dist. | Completed | 2020-01-02 | 2020-12-31 | 2020 | Adminsitration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started: | 2020-01-02
Sto. Tomas | Magwawa | 2nd Eng'g. Dist. | On-going | 2020-08-03 |  | 2020 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | ROAD ID 151 - San Jose - Sitio Mahayahay, Magwawa |  | GENERAL FUND CY 2020 | Maintenance | 0.84 | km | CBRMC | Project Cost: | 30789.12 | Target Completion Date: | 2021-02-03 | Program: | 30789.12 | Planned: |  | Planned: |  | Planned: |  | Planned: | 27.78% | Planned: | 27.78% | No. of Persons: |  | Purchase Order # 2020030972 (Brgy. San Jose Upland Farmer's Assocaition) | Purchase Order # 2020030972 (Brgy. San Jose Upland Farmer's Assocaition) | Purchase Order # 2020030972 (Brgy. San Jose Upland Farmer's Assocaition) | On-going | On-going | On-going
Sto. Tomas | Magwawa | 2nd Eng'g. Dist. | On-going | 2020-08-03 |  | 2020 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Project Engineer: | Maligro | Revised Completion Date: |  | Allotment: | 30789.12 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
Sto. Tomas | Magwawa | 2nd Eng'g. Dist. | On-going | 2020-08-03 |  | 2020 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Implementor: | Brgy. San Jose Upland Farmer's Assocaition | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: | 27.78% | Actual: | 27.78%
Sto. Tomas | Magwawa | 2nd Eng'g. Dist. | On-going | 2020-08-03 |  | 2020 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Duration: | 6 months | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Sto. Tomas | Magwawa | 2nd Eng'g. Dist. | On-going | 2020-08-03 |  | 2020 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Allotment Released: |  | Date completed:
Sto. Tomas | Magwawa | 2nd Eng'g. Dist. | On-going | 2020-08-03 |  | 2020 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Maintenance Of Various Prov'l. Roads and Bridges 2 | [7 empty] | Date Started: | 2020-08-03
Carmen | Asuncion | 2nd Eng'g. Dist. | For Implementation |  |  | 2020 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | ROAD ID 007 - Lower Asuncion - Upper Asuncion (Phase I) |  | 20% DF CY 2020 | Rehabilitation |  | km |  | Project Cost: | 1302000 | Target Completion Date: |  | Program: | 1302000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No
Carmen | Asuncion | 2nd Eng'g. Dist. | For Implementation |  |  | 2020 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 1302000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
Carmen | Asuncion | 2nd Eng'g. Dist. | For Implementation |  |  | 2020 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
Carmen | Asuncion | 2nd Eng'g. Dist. | For Implementation |  |  | 2020 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Carmen | Asuncion | 2nd Eng'g. Dist. | For Implementation |  |  | 2020 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Date Allotment Released: |  | Date completed:
Carmen | Asuncion | 2nd Eng'g. Dist. | For Implementation |  |  | 2020 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Date Started:
Carmen | Mangalcal | 2nd Eng'g. Dist. | Suspended | 2020-06-15 |  | 2020 | Administration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | ROAD ID 030 - Jct. Highway - Carmen - Mangalcal - Tubod (Phase I) |  | 20% DF CY 2020 | Rehabilitation |  | km |  | Project Cost: | 1323000 | Target Completion Date: | 2021-02-03 | Program: | 1323000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: | 100% | No. of Persons: | 2 | Plan On-going | Plan On-going | Plan On-going | Plan On-going | Plan On-going | Suspended 10/1/2020
Carmen | Mangalcal | 2nd Eng'g. Dist. | Suspended | 2020-06-15 |  | 2020 | Administration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Project Engineer: | Obar | Revised Completion Date: |  | Allotment: | 1323000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 44
Carmen | Mangalcal | 2nd Eng'g. Dist. | Suspended | 2020-06-15 |  | 2020 | Administration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual: | 68.83%
Carmen | Mangalcal | 2nd Eng'g. Dist. | Suspended | 2020-06-15 |  | 2020 | Administration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Duration: | 90 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | -31.17%
Carmen | Mangalcal | 2nd Eng'g. Dist. | Suspended | 2020-06-15 |  | 2020 | Administration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
Carmen | Mangalcal | 2nd Eng'g. Dist. | Suspended | 2020-06-15 |  | 2020 | Administration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Date Started: | 2020-06-15
Carmen | Tuganay | 2nd Eng'g. Dist. | Suspended | 2020-05-18 |  | 2020 | Administration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | ROAD ID 031 - Tuganay - Taba (Phase I) |  | 20% DF CY 2020 | Rehabilitation |  | km |  | Project Cost: | 507500 | Target Completion Date: | 2020-06-17 | Program: | 507500 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: | 100% | No. of Persons: | 2 | Plan On-going | Plan On-going | Plan On-going | Plan On-going | Plan On-going | Suspended 6/13/2020
Carmen | Tuganay | 2nd Eng'g. Dist. | Suspended | 2020-05-18 |  | 2020 | Administration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Project Engineer: | Obar | Revised Completion Date: | 2020-08-21 | Allotment: | 507500 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 44
Carmen | Tuganay | 2nd Eng'g. Dist. | Suspended | 2020-05-18 |  | 2020 | Administration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Implementor: | PEO | No. of days suspended: | 65 | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual: | 68.87%
Carmen | Tuganay | 2nd Eng'g. Dist. | Suspended | 2020-05-18 |  | 2020 | Administration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Duration: | 30 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | -31.13%
Carmen | Tuganay | 2nd Eng'g. Dist. | Suspended | 2020-05-18 |  | 2020 | Administration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
Carmen | Tuganay | 2nd Eng'g. Dist. | Suspended | 2020-05-18 |  | 2020 | Administration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Date Started: | 2020-05-18
Carmen | Ising | 2nd Eng'g. Dist. | Re-aligned to COVID |  |  | 2020 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | ROAD ID 069 - Jct. Highway - Ising - Magsaysay (Phase I) |  | 20% DF CY 2020 | Rehabilitation |  | km |  | Project Cost: | 6000000 | Target Completion Date: |  | Program: | 6000000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No
Carmen | Ising | 2nd Eng'g. Dist. | Re-aligned to COVID |  |  | 2020 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 6000000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
Carmen | Ising | 2nd Eng'g. Dist. | Re-aligned to COVID |  |  | 2020 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
Carmen | Ising | 2nd Eng'g. Dist. | Re-aligned to COVID |  |  | 2020 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Carmen | Ising | 2nd Eng'g. Dist. | Re-aligned to COVID |  |  | 2020 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Date Allotment Released: |  | Date completed:
Carmen | Ising | 2nd Eng'g. Dist. | Re-aligned to COVID |  |  | 2020 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Date Started:
Carmen | Guadalupe | 2nd Eng'g. Dist. | Suspended | 2020-05-18 |  | 2020 | Administration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | Jct. Highway - Guadalupe - Bdry. Tagum (Phase I) |  | 20% DF CY 2020 | Rehabilitation |  | km |  | Project Cost: | 910000 | Target Completion Date: | 2020-08-06 | Program: | 910000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: | 3.2% | No. of Persons: | 2 | Suspended June 13, 2020 due to unavailability of heavy equipment | Plan On-going | Plan On-going | Plan On-going | Plan On-going | Suspended June 13, 2020 due to unavailability of heavy equipment
Carmen | Guadalupe | 2nd Eng'g. Dist. | Suspended | 2020-05-18 |  | 2020 | Administration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Project Engineer: | Obar | Revised Completion Date: |  | Allotment: | 910000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 52
Carmen | Guadalupe | 2nd Eng'g. Dist. | Suspended | 2020-05-18 |  | 2020 | Administration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual: | 1.2%
Carmen | Guadalupe | 2nd Eng'g. Dist. | Suspended | 2020-05-18 |  | 2020 | Administration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Duration: | 80 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | -2%
Carmen | Guadalupe | 2nd Eng'g. Dist. | Suspended | 2020-05-18 |  | 2020 | Administration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
Carmen | Guadalupe | 2nd Eng'g. Dist. | Suspended | 2020-05-18 |  | 2020 | Administration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Date Started: | 2020-05-18
Carmen | Tibulao | 2nd Eng'g. Dist. | Suspended | 2020-05-18 |  | 2020 | Administration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | Sitio Malaga - Tibulao (Phase I) |  | 20% DF CY 2020 | Rehabilitation |  | km |  | Project Cost: | 350000 | Target Completion Date: | 2020-06-17 | Program: | 350000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: | 3.5% | No. of Persons: | 2 | Plan On-going | Plan On-going | Plan On-going | Plan On-going | Plan On-going | Suspended June 13, 2020 due to unavailability of heavy equipment
Carmen | Tibulao | 2nd Eng'g. Dist. | Suspended | 2020-05-18 |  | 2020 | Administration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Project Engineer: | Obar | Revised Completion Date: |  | Allotment: | 350000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 44
Carmen | Tibulao | 2nd Eng'g. Dist. | Suspended | 2020-05-18 |  | 2020 | Administration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual: | 1.2%
Carmen | Tibulao | 2nd Eng'g. Dist. | Suspended | 2020-05-18 |  | 2020 | Administration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Duration: | 30 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | -2.3%
Carmen | Tibulao | 2nd Eng'g. Dist. | Suspended | 2020-05-18 |  | 2020 | Administration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
Carmen | Tibulao | 2nd Eng'g. Dist. | Suspended | 2020-05-18 |  | 2020 | Administration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Date Started: | 2020-05-18
Carmen-Dujali | Cabay-angan-Esperanza | 2nd Eng'g. Dist. | For Implementation |  |  | 2020 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | Rehablilitation of Cabay-angan-Esperanza Provincial Road, Carmen-B.E. Dujali (Phase I) |  | 20% DF CY 2020 | Rehabilitation |  | km |  | Project Cost: | 350000 | Target Completion Date: |  | Program: | 350000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Plan On-going | Plan On-going | Plan On-going | Plan On-going | Plan On-going | Plan On-going
Carmen-Dujali | Cabay-angan-Esperanza | 2nd Eng'g. Dist. | For Implementation |  |  | 2020 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 350000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
Carmen-Dujali | Cabay-angan-Esperanza | 2nd Eng'g. Dist. | For Implementation |  |  | 2020 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
Carmen-Dujali | Cabay-angan-Esperanza | 2nd Eng'g. Dist. | For Implementation |  |  | 2020 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Carmen-Dujali | Cabay-angan-Esperanza | 2nd Eng'g. Dist. | For Implementation |  |  | 2020 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Date Allotment Released: |  | Date completed:
Carmen-Dujali | Cabay-angan-Esperanza | 2nd Eng'g. Dist. | For Implementation |  |  | 2020 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Date Started:
B.E. Dujali | Pawas | 2nd Eng'g. Dist. | Suspended | 2020-05-18 |  | 2020 | Administration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | Dujali - Pawas - San Vicente (Phase I) |  | 20% DF CY 2020 | Rehabilitation |  | km |  | Project Cost: | 525000 | Target Completion Date: | 2020-07-02 | Program: | 525000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: | 6.5% | No. of Persons: | 2 | Plan On-going | Plan On-going | Plan On-going | Plan On-going | Plan On-going | PTemporarily Suspended June 13, 2020 due to unavailability of heavy equipment
B.E. Dujali | Pawas | 2nd Eng'g. Dist. | Suspended | 2020-05-18 |  | 2020 | Administration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Project Engineer: | Obar | Revised Completion Date: |  | Allotment: | 525000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 42
B.E. Dujali | Pawas | 2nd Eng'g. Dist. | Suspended | 2020-05-18 |  | 2020 | Administration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual: | 1.2%
B.E. Dujali | Pawas | 2nd Eng'g. Dist. | Suspended | 2020-05-18 |  | 2020 | Administration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Duration: | 45 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | -5.3%
B.E. Dujali | Pawas | 2nd Eng'g. Dist. | Suspended | 2020-05-18 |  | 2020 | Administration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
B.E. Dujali | Pawas | 2nd Eng'g. Dist. | Suspended | 2020-05-18 |  | 2020 | Administration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Date Started: | 2020-05-18
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | Completed | 2020-05-18 | 2020-08-31 | 2020 | Administration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | San Miguel - Crossing Kinamayan (Phase I) |  | 20% DF CY 2020 | Rehabilitation |  | km |  | Project Cost: | 350000 | Target Completion Date: | 2020-07-17 | Program: | 350000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: | 100% | No. of Persons: | 3 | Plan On-going | Plan On-going | Plan On-going | Plan On-going | Plan On-going | Completed as per Program of Works
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | Completed | 2020-05-18 | 2020-08-31 | 2020 | Administration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Project Engineer: | Obar/Piad | Revised Completion Date: | 8/31/2020 | Allotment: | 350000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 66
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | Completed | 2020-05-18 | 2020-08-31 | 2020 | Administration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual: | 100%
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | Completed | 2020-05-18 | 2020-08-31 | 2020 | Administration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Duration: | 60 | No. of days extended: | 45 |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | Completed | 2020-05-18 | 2020-08-31 | 2020 | Administration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed: | 2020-08-31
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | Completed | 2020-05-18 | 2020-08-31 | 2020 | Administration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Date Started: | 2020-05-18
Sto. Tomas | Esperanza | 2nd Eng'g. Dist. | Re-aligned to COVID |  |  | 2020 |  | . | Rehabilitation of Provincial Roads & Bridges | Los Amigos 1 - Esperanza - Los Amigos 2 (Phase I) |  | 20% DF CY 2020 | Rehabilitation |  | km |  | Project Cost: | 350000 | Target Completion Date: |  | Program: | 350000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No
Sto. Tomas | Esperanza | 2nd Eng'g. Dist. | Re-aligned to COVID |  |  | 2020 |  | . | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 350000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
Sto. Tomas | Esperanza | 2nd Eng'g. Dist. | Re-aligned to COVID |  |  | 2020 |  | . | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
Sto. Tomas | Esperanza | 2nd Eng'g. Dist. | Re-aligned to COVID |  |  | 2020 |  | . | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Sto. Tomas | Esperanza | 2nd Eng'g. Dist. | Re-aligned to COVID |  |  | 2020 |  | . | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Date Allotment Released: |  | Date completed:
Sto. Tomas | Esperanza | 2nd Eng'g. Dist. | Re-aligned to COVID |  |  | 2020 |  | . | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Date Started:
Sto. Tomas | Magwawa | 2nd Eng'g. Dist. | On-going | 2020-05-18 |  | 2020 | Administration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | Fd. Rd. 2 - Sto. Tomas - Magwawa (Phase I) |  | 20% DF CY 2020 | Rehabilitation |  | km |  | Project Cost: | 300000 | Target Completion Date: | 2020-06-17 | Program: | 300000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: | 100% | No. of Persons: | 3 | Plan On-going | Plan On-going | Plan On-going | Plan On-going | Plan On-going | Suspended 10/15/2020
Sto. Tomas | Magwawa | 2nd Eng'g. Dist. | On-going | 2020-05-18 |  | 2020 | Administration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Project Engineer: | Obar | Revised Completion Date: | 10/31/2020 | Allotment: | 300000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 66
Sto. Tomas | Magwawa | 2nd Eng'g. Dist. | On-going | 2020-05-18 |  | 2020 | Administration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Implementor: | PEO | No. of days suspended: | 80 | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual: | 61.3%
Sto. Tomas | Magwawa | 2nd Eng'g. Dist. | On-going | 2020-05-18 |  | 2020 | Administration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Duration: | 30 | No. of days extended: | 56 |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | -38.7%
Sto. Tomas | Magwawa | 2nd Eng'g. Dist. | On-going | 2020-05-18 |  | 2020 | Administration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
Sto. Tomas | Magwawa | 2nd Eng'g. Dist. | On-going | 2020-05-18 |  | 2020 | Administration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Date Started: | 2020-05-18
Sto. Tomas | Balagunan | 2nd Eng'g. Dist. | Re-aligned to COVID |  |  | 2020 |  | . | Rehabilitation of Provincial Roads & Bridges | Menzi - Balagunan - Tulalian (Phase I) |  | 20% DF CY 2020 | Rehabilitation |  | km |  | Project Cost: | 3720500 | Target Completion Date: |  | Program: | 3720500 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No
Sto. Tomas | Balagunan | 2nd Eng'g. Dist. | Re-aligned to COVID |  |  | 2020 |  | . | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 3720500 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
Sto. Tomas | Balagunan | 2nd Eng'g. Dist. | Re-aligned to COVID |  |  | 2020 |  | . | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
Sto. Tomas | Balagunan | 2nd Eng'g. Dist. | Re-aligned to COVID |  |  | 2020 |  | . | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Sto. Tomas | Balagunan | 2nd Eng'g. Dist. | Re-aligned to COVID |  |  | 2020 |  | . | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Date Allotment Released: |  | Date completed:
Sto. Tomas | Balagunan | 2nd Eng'g. Dist. | Re-aligned to COVID |  |  | 2020 |  | . | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Date Started:
B.E. Dujali | Magupising | 2nd Eng'g. Dist. | Suspended | 2020-05-18 |  | 2020 | Administration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | Jct,. Bdry. Tagum- Talomo (Phase I) |  | 20% DF CY 2020 | Rehabilitation |  | km |  | Project Cost: | 1400000 | Target Completion Date: | 2020-09-15 | Program: | 1400000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: | 41.2% | No. of Persons: | 4 | POW for approval with the Governor | POW for approval with the Governor | POW for approval with the Governor | POW for approval with the Governor | POW for approval with the Governor | Suspended June 13, 2020
B.E. Dujali | Magupising | 2nd Eng'g. Dist. | Suspended | 2020-05-18 |  | 2020 | Administration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Project Engineer: | Obar | Revised Completion Date: |  | Allotment: | 1400000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 88
B.E. Dujali | Magupising | 2nd Eng'g. Dist. | Suspended | 2020-05-18 |  | 2020 | Administration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Implementor: | Admin | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual: | 39.6%
B.E. Dujali | Magupising | 2nd Eng'g. Dist. | Suspended | 2020-05-18 |  | 2020 | Administration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Duration: | 120 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | -1.6%
B.E. Dujali | Magupising | 2nd Eng'g. Dist. | Suspended | 2020-05-18 |  | 2020 | Administration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Date Allotment Released: |  | Date completed:
B.E. Dujali | Magupising | 2nd Eng'g. Dist. | Suspended | 2020-05-18 |  | 2020 | Administration | I. PROJECTS UNDER THE CURRENT APPROPRIATION | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Date Started: | 2020-05-18
Carmen | New Casay | 2nd Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | Rehabilitation of Provincial Roads & Bridges | Prk. 5 RJS - Prk. 6 New Casay (Phase I) |  | 20% DF CY 2020 | Rehabilitation |  | km |  | Project Cost: | 350000 | Target Completion Date: |  | Program: | 350000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Plan On-going | Plan On-going | Plan On-going | Plan On-going | Plan On-going | Plan On-going
Carmen | New Casay | 2nd Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 350000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
Carmen | New Casay | 2nd Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
Carmen | New Casay | 2nd Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Carmen | New Casay | 2nd Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Date Allotment Released: |  | Date completed:
Carmen | New Casay | 2nd Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Date Started:
Sto. Tomas | San Jose | 2nd Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | Rehabilitation of Provincial Roads & Bridges | ROAD ID 008 - Fr. Rd. 3 - San Jose |  | 20% DF CY 2020 | Rehabilitation |  | km |  | Project Cost: | 8000000 | Target Completion Date: |  | Program: | 8000000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Plan On-going | Plan On-going | Plan On-going | Plan On-going | Plan On-going | Plan On-going
Sto. Tomas | San Jose | 2nd Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 8000000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
Sto. Tomas | San Jose | 2nd Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
Sto. Tomas | San Jose | 2nd Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Sto. Tomas | San Jose | 2nd Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Date Allotment Released: |  | Date completed:
Sto. Tomas | San Jose | 2nd Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | Rehabilitation of Provincial Roads & Bridges | [7 empty] | Date Started:
Tagum City | Cuambogan | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | RURAL ELECTRIFICATION PROJECT LS - P 5,000,000.00 | Rural Electrification at RAMADA Compound Purok Sto. Niño, Brgy. Cuambogan, Tagum City |  | 20% Development Fund CY 2020 | Electrification |  | km |  | Project Cost: | 1000000 | Target Completion Date: |  | Program: | 1000000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | PO on process - Tagum Constrak | PO on process - Tagum Constrak | PO on process - Tagum Constrak | PO on process - Tagum Constrak | PO on process - Tagum Constrak | For implementation Tagum Constrak
Tagum City | Cuambogan | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | RURAL ELECTRIFICATION PROJECT LS - P 5,000,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 1000000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
Tagum City | Cuambogan | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | RURAL ELECTRIFICATION PROJECT LS - P 5,000,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
Tagum City | Cuambogan | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | RURAL ELECTRIFICATION PROJECT LS - P 5,000,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Tagum City | Cuambogan | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | RURAL ELECTRIFICATION PROJECT LS - P 5,000,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Tagum City | Cuambogan | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | RURAL ELECTRIFICATION PROJECT LS - P 5,000,000.00 | [7 empty] | Date Started:
Asuncion | Camansa | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | RURAL ELECTRIFICATION PROJECT LS - P 5,000,000.00 | Rural Electrification at Lower Camansa, Prk.5 to 6 Lower, Brgy. Camansa, Asuncion |  | 20% Development Fund CY 2020 | Electrification |  | km |  | Project Cost: | 3000000 | Target Completion Date: |  | Program: | 3000000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | PO on process - Tagum Constrak | PO on process - Tagum Constrak | PO on process - Tagum Constrak | PO on process - Tagum Constrak | PO on process - Tagum Constrak | For implementation Tagum Constrak
Asuncion | Camansa | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | RURAL ELECTRIFICATION PROJECT LS - P 5,000,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 3000000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
Asuncion | Camansa | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | RURAL ELECTRIFICATION PROJECT LS - P 5,000,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
Asuncion | Camansa | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | RURAL ELECTRIFICATION PROJECT LS - P 5,000,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Asuncion | Camansa | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | RURAL ELECTRIFICATION PROJECT LS - P 5,000,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Asuncion | Camansa | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | RURAL ELECTRIFICATION PROJECT LS - P 5,000,000.00 | [7 empty] | Date Started:
Asuncion | Doña Andrea | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | RURAL ELECTRIFICATION PROJECT LS - P 5,000,000.00 | Completion of Electrification at at Purok 10 and Purok 9, Phase 2, Brgy. Doña Andrea, Asuncion |  | 20% Development Fund CY 2020 | Electrification |  | km |  | Project Cost: | 1000000 | Target Completion Date: |  | Program: | 1000000 | Planned: |  | Planned: | 100% | Planned: | 100% | Planned: | 100% | Planned: | 100% | No. of Persons: |  | For preparation of POW and Plans | Completed (Implemented by MLGU, since transfer of fund ) | Completed (Implemented by MLGU, since transfer of fund ) | Completed (Implemented by MLGU, since transfer of fund ) | Completed (Implemented by MLGU, since transfer of fund ) | Completed (Implemented by MLGU, since transfer of fund )
Asuncion | Doña Andrea | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | RURAL ELECTRIFICATION PROJECT LS - P 5,000,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 1000000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
Asuncion | Doña Andrea | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | RURAL ELECTRIFICATION PROJECT LS - P 5,000,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: | 100% | Actual: | 100% | Actual: | 100% | Actual: | 100%
Asuncion | Doña Andrea | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | RURAL ELECTRIFICATION PROJECT LS - P 5,000,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Asuncion | Doña Andrea | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | RURAL ELECTRIFICATION PROJECT LS - P 5,000,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Asuncion | Doña Andrea | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | RURAL ELECTRIFICATION PROJECT LS - P 5,000,000.00 | [7 empty] | Date Started:
Babak, IGCS | Cogon | 2nd Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | RURAL ELECTRIFICATION | Completion of Single Phase Line at Purok 6 and Purok 7, Brgy. Cogon, Babak Distirct, IGACOS |  | 20% DF CY 2020 | Electrificaton |  | km |  | Project Cost: | 1000000 | Target Completion Date: |  | Program: | 1000000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | PR #20063965 | PR #20063965 | PR #20063965 | PR #20063965 | PR #20063965 | PR #20063965
Babak, IGCS | Cogon | 2nd Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | RURAL ELECTRIFICATION | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 1000000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
Babak, IGCS | Cogon | 2nd Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | RURAL ELECTRIFICATION | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
Babak, IGCS | Cogon | 2nd Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | RURAL ELECTRIFICATION | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Babak, IGCS | Cogon | 2nd Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | RURAL ELECTRIFICATION | [7 empty] | Date Allotment Released: |  | Date completed:
Babak, IGCS | Cogon | 2nd Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | RURAL ELECTRIFICATION | [7 empty] | Date Started:
IGCS | Sta. Cruz | 2nd Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | RURAL ELECTRIFICATION | Completion of Single Phase Line at Purok Perlas, Brgy. Sta. Cruz, Talicud (Day Care Center), IGACOS |  | 20% DF CY 2020 | Electrificaton |  | km |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | POW preparation on-going c/o Engr. Kim Pao Lu | POW preparation on-going c/o Engr. Kim Pao Lu | POW preparation on-going c/o Engr. Kim Pao Lu | POW preparation on-going c/o Engr. Kim Pao Lu | POW preparation on-going c/o Engr. Kim Pao Lu | POW preparation on-going c/o Engr. Kim Pao Lu
IGCS | Sta. Cruz | 2nd Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | RURAL ELECTRIFICATION | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
IGCS | Sta. Cruz | 2nd Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | RURAL ELECTRIFICATION | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
IGCS | Sta. Cruz | 2nd Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | RURAL ELECTRIFICATION | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
IGCS | Sta. Cruz | 2nd Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | RURAL ELECTRIFICATION | [7 empty] | Date Allotment Released: |  | Date completed:
IGCS | Sta. Cruz | 2nd Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | RURAL ELECTRIFICATION | [7 empty] | Date Started:
Kapalong | Gupitan | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | VARIOUS WATER SYSTEM | Const. of Potable Water System, Brgy. Gupitan, Kapalong |  | 20% DF CY 2020 | PWS |  | km |  | Project Cost: | 3000000 | Target Completion Date: |  | Program: | 3000000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | POW preparation on-going c/o Engr. Kim Pao Lu | POW preparation on-going c/o Engr. Kim Pao Lu | POW preparation on-going c/o Engr. Kim Pao Lu |  |  | Plan On-going
Kapalong | Gupitan | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | VARIOUS WATER SYSTEM | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 3000000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
Kapalong | Gupitan | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | VARIOUS WATER SYSTEM | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
Kapalong | Gupitan | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | VARIOUS WATER SYSTEM | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Kapalong | Gupitan | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | VARIOUS WATER SYSTEM | [7 empty] | Date Allotment Released: |  | Date completed:
Kapalong | Gupitan | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | VARIOUS WATER SYSTEM | [7 empty] | Date Started:
Kapalong | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | VARIOUS WATER SYSTEM | Const. of Potable Water System, Brgy. Sto. Niño, Kapalong |  | 20% DF CY 2020 | PWS |  | km |  | Project Cost: | 1000000 | Target Completion Date: |  | Program: | 1000000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | POW preparation on-going c/o Engr. Kim Pao Lu | POW preparation on-going c/o Engr. Kim Pao Lu | POW preparation on-going c/o Engr. Kim Pao Lu |  |  | Plan On-going
Kapalong | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | VARIOUS WATER SYSTEM | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 1000000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
Kapalong | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | VARIOUS WATER SYSTEM | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
Kapalong | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | VARIOUS WATER SYSTEM | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Kapalong | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | VARIOUS WATER SYSTEM | [7 empty] | Date Allotment Released: |  | Date completed:
Kapalong | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | VARIOUS WATER SYSTEM | [7 empty] | Date Started:
Talaingod | Dagohoy | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | VARIOUS WATER SYSTEM | Const. of Potable Water System, Brgy. Dagohoy, Talaingod |  | 20% DF CY 2020 | PWS |  | km |  | Project Cost: | 1000000 | Target Completion Date: |  | Program: | 1000000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | POW preparation on-going c/o Engr. Kim Pao Lu | POW preparation on-going c/o Engr. Kim Pao Lu | POW preparation on-going c/o Engr. Kim Pao Lu |  |  | Plan On-going
Talaingod | Dagohoy | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | VARIOUS WATER SYSTEM | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 1000000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
Talaingod | Dagohoy | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | VARIOUS WATER SYSTEM | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
Talaingod | Dagohoy | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | VARIOUS WATER SYSTEM | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Talaingod | Dagohoy | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | VARIOUS WATER SYSTEM | [7 empty] | Date Allotment Released: |  | Date completed:
Talaingod | Dagohoy | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | VARIOUS WATER SYSTEM | [7 empty] | Date Started:
Talaingod | Palma Gil | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | VARIOUS WATER SYSTEM | Const. of Potable Water System, Brgy. Palma Gil, Talaingod |  | 20% DF CY 2020 | PWS |  | km |  | Project Cost: | 1000000 | Target Completion Date: |  | Program: | 1000000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | POW preparation on-going c/o Engr. Kim Pao Lu | POW preparation on-going c/o Engr. Kim Pao Lu | POW preparation on-going c/o Engr. Kim Pao Lu |  |  | Plan On-going
Talaingod | Palma Gil | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | VARIOUS WATER SYSTEM | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 1000000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
Talaingod | Palma Gil | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | VARIOUS WATER SYSTEM | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
Talaingod | Palma Gil | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | VARIOUS WATER SYSTEM | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Talaingod | Palma Gil | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | VARIOUS WATER SYSTEM | [7 empty] | Date Allotment Released: |  | Date completed:
Talaingod | Palma Gil | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | VARIOUS WATER SYSTEM | [7 empty] | Date Started:
Panabo City | Kiotoy | 2nd Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | VARIOUS WATER SYSTEM | Impv't. of Potable Water System, Brgy. Kiotoy, Panabo City |  | 20% DF CY 2020 | PWS |  | km |  | Project Cost: | 1000000 | Target Completion Date: |  | Program: | 1000000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | POW preparation on-going c/o Engr. Kim Pao Lu | POW preparation on-going c/o Engr. Kim Pao Lu | POW preparation on-going c/o Engr. Kim Pao Lu |  |  | Plan On-going
Panabo City | Kiotoy | 2nd Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | VARIOUS WATER SYSTEM | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 1000000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
Panabo City | Kiotoy | 2nd Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | VARIOUS WATER SYSTEM | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
Panabo City | Kiotoy | 2nd Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | VARIOUS WATER SYSTEM | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Panabo City | Kiotoy | 2nd Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | VARIOUS WATER SYSTEM | [7 empty] | Date Allotment Released: |  | Date completed:
Panabo City | Kiotoy | 2nd Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | VARIOUS WATER SYSTEM | [7 empty] | Date Started:
Panabo City | Consolacion | 2nd Eng'g. Dist. | Re-aligned to COVID |  |  | 2020 |  | . | VARIOUS WATER SYSTEM | Impv't. of Potable Water System, Consolacion, Panabo City |  | 20% DF CY 2020 | Water System |  |  |  | Project Cost: | 10000000 | Target Completion Date: |  | Program: | 10000000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. |  |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No 1
Panabo City | Consolacion | 2nd Eng'g. Dist. | Re-aligned to COVID |  |  | 2020 |  | . | VARIOUS WATER SYSTEM | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 10000000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
Panabo City | Consolacion | 2nd Eng'g. Dist. | Re-aligned to COVID |  |  | 2020 |  | . | VARIOUS WATER SYSTEM | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
Panabo City | Consolacion | 2nd Eng'g. Dist. | Re-aligned to COVID |  |  | 2020 |  | . | VARIOUS WATER SYSTEM | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Panabo City | Consolacion | 2nd Eng'g. Dist. | Re-aligned to COVID |  |  | 2020 |  | . | VARIOUS WATER SYSTEM | [7 empty] | Date Allotment Released: |  | Date completed:
Panabo City | Consolacion | 2nd Eng'g. Dist. | Re-aligned to COVID |  |  | 2020 |  | . | VARIOUS WATER SYSTEM | [7 empty] | Date Started:
Samal | Tagbitan-ag | 2nd Eng'g. Dist. | Plan on going |  |  | 2020 |  | . | VARIOUS WATER SYSTEM | Impv't. of Potable Water System, Tagbitan-ag, Samal Dist. |  | 20% DF CY 2020 | Water System |  |  |  | Project Cost: | 1000000 | Target Completion Date: |  | Program: | 1000000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | For implementation | For implementation | For implementation |  |  | Plan On-going
Samal | Tagbitan-ag | 2nd Eng'g. Dist. | Plan on going |  |  | 2020 |  | . | VARIOUS WATER SYSTEM | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 1000000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
Samal | Tagbitan-ag | 2nd Eng'g. Dist. | Plan on going |  |  | 2020 |  | . | VARIOUS WATER SYSTEM | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
Samal | Tagbitan-ag | 2nd Eng'g. Dist. | Plan on going |  |  | 2020 |  | . | VARIOUS WATER SYSTEM | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Samal | Tagbitan-ag | 2nd Eng'g. Dist. | Plan on going |  |  | 2020 |  | . | VARIOUS WATER SYSTEM | [7 empty] | Date Allotment Released: |  | Date completed:
Samal | Tagbitan-ag | 2nd Eng'g. Dist. | Plan on going |  |  | 2020 |  | . | VARIOUS WATER SYSTEM | [7 empty] | Date Started:
Babak | San Antonio | 2nd Eng'g. Dist. | Re-aligned to COVID |  |  | 2020 |  | . | VARIOUS WATER SYSTEM | Impv't. of Potable Water System, San Antonio, babak, IGCS |  | 20% DF CY 2020 | Water System |  |  |  | Project Cost: | 1000000 | Target Completion Date: |  | Program: | 1000000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. |  |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No 1
Babak | San Antonio | 2nd Eng'g. Dist. | Re-aligned to COVID |  |  | 2020 |  | . | VARIOUS WATER SYSTEM | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 1000000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
Babak | San Antonio | 2nd Eng'g. Dist. | Re-aligned to COVID |  |  | 2020 |  | . | VARIOUS WATER SYSTEM | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
Babak | San Antonio | 2nd Eng'g. Dist. | Re-aligned to COVID |  |  | 2020 |  | . | VARIOUS WATER SYSTEM | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Babak | San Antonio | 2nd Eng'g. Dist. | Re-aligned to COVID |  |  | 2020 |  | . | VARIOUS WATER SYSTEM | [7 empty] | Date Allotment Released: |  | Date completed:
Babak | San Antonio | 2nd Eng'g. Dist. | Re-aligned to COVID |  |  | 2020 |  | . | VARIOUS WATER SYSTEM | [7 empty] | Date Started:
Carmen | Magsaysay | 2nd Eng'g. Dist. | Completed | 2020-10-08 | 2020-11-27 | 2020 | Contract | . | Stimulus Projects for Various Barangays LS - P41,500,000.00 | Improvement of Potable Water System, Brgy. Magsaysay, Carmen |  | 20% DF CY 2020 | Water System |  |  | Contract | Project Cost: | 1000000 | Target Completion Date: | 2021-01-16 | Program: | 1000000 | Planned: | 13.2% | No. of Persons: | 3 | On-going |  | Planned: | 100% | Planned: | 100% | No. of Persons: | 3 |  |  |  | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per Program of Works
Carmen | Magsaysay | 2nd Eng'g. Dist. | Completed | 2020-10-08 | 2020-11-27 | 2020 | Contract | . | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Project Engineer: | Estorco | Revised Completion Date: |  | Allotment: | 1000000 | Revised: |  | No. of Man-days: | 66 |  |  | Revised: |  | Revised: |  | No. of Man-days: | 66
Carmen | Magsaysay | 2nd Eng'g. Dist. | Completed | 2020-10-08 | 2020-11-27 | 2020 | Contract | . | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Implementor: | JJR Const. & Supply | No. of days suspended: |  | Disbursement: |  | Actual: | 2.3% |  |  |  |  | Actual: | 100% | Actual: | 100%
Carmen | Magsaysay | 2nd Eng'g. Dist. | Completed | 2020-10-08 | 2020-11-27 | 2020 | Contract | . | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Duration: | 100 | No. of days extended: |  |  |  | Slippage: | -10.9% |  |  |  |  | Slippage: | 0% | Slippage: | 0%
Carmen | Magsaysay | 2nd Eng'g. Dist. | Completed | 2020-10-08 | 2020-11-27 | 2020 | Contract | . | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Allotment Released: |  | Date completed: | 2020-11-27
Carmen | Magsaysay | 2nd Eng'g. Dist. | Completed | 2020-10-08 | 2020-11-27 | 2020 | Contract | . | Stimulus Projects for Various Barangays LS - P41,500,000.00 | [7 empty] | Date Started: | 2020-10-08
Babak | San Isidro | 2nd Eng'g. Dist. | Plan on going |  |  | 2020 |  | . | VARIOUS WATER SYSTEM | Impv't. of Potable Water System, San Isidro, Babak, IGCS |  | 20% DF CY 2020 | Water System |  |  |  | Project Cost: | 1000000 | Target Completion Date: |  | Program: | 1000000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. |  |  | Plan On-going
Babak | San Isidro | 2nd Eng'g. Dist. | Plan on going |  |  | 2020 |  | . | VARIOUS WATER SYSTEM | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 1000000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
Babak | San Isidro | 2nd Eng'g. Dist. | Plan on going |  |  | 2020 |  | . | VARIOUS WATER SYSTEM | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
Babak | San Isidro | 2nd Eng'g. Dist. | Plan on going |  |  | 2020 |  | . | VARIOUS WATER SYSTEM | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Babak | San Isidro | 2nd Eng'g. Dist. | Plan on going |  |  | 2020 |  | . | VARIOUS WATER SYSTEM | [7 empty] | Date Allotment Released: |  | Date completed:
Babak | San Isidro | 2nd Eng'g. Dist. | Plan on going |  |  | 2020 |  | . | VARIOUS WATER SYSTEM | [7 empty] | Date Started:
Samal | Licup | 2nd Eng'g. Dist. | Re-aligned to COVID |  |  | 2020 |  | . | VARIOUS WATER SYSTEM | Impv't. of Potable Water System,Licup, Samal, IGCS |  | 20% DF CY 2020 | Water System |  |  |  | Project Cost: | 2000000 | Target Completion Date: |  | Program: | 2000000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. |  |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No 1
Samal | Licup | 2nd Eng'g. Dist. | Re-aligned to COVID |  |  | 2020 |  | . | VARIOUS WATER SYSTEM | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 2000000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
Samal | Licup | 2nd Eng'g. Dist. | Re-aligned to COVID |  |  | 2020 |  | . | VARIOUS WATER SYSTEM | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
Samal | Licup | 2nd Eng'g. Dist. | Re-aligned to COVID |  |  | 2020 |  | . | VARIOUS WATER SYSTEM | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Samal | Licup | 2nd Eng'g. Dist. | Re-aligned to COVID |  |  | 2020 |  | . | VARIOUS WATER SYSTEM | [7 empty] | Date Allotment Released: |  | Date completed:
Samal | Licup | 2nd Eng'g. Dist. | Re-aligned to COVID |  |  | 2020 |  | . | VARIOUS WATER SYSTEM | [7 empty] | Date Started:
Carmen |  | 2nd Eng'g. Dist. | Re-aligned to COVID |  |  | 2020 |  | . | VARIOUS WATER SYSTEM | Const. of Water System at Provincial Engineer's Office 2nd District Carmen |  | 20% DF CY 2020 | Water System |  |  |  | Project Cost: | 1000000 | Target Completion Date: |  | Program: | 1000000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. |  |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No 1
Carmen |  | 2nd Eng'g. Dist. | Re-aligned to COVID |  |  | 2020 |  | . | VARIOUS WATER SYSTEM | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 1000000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
Carmen |  | 2nd Eng'g. Dist. | Re-aligned to COVID |  |  | 2020 |  | . | VARIOUS WATER SYSTEM | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
Carmen |  | 2nd Eng'g. Dist. | Re-aligned to COVID |  |  | 2020 |  | . | VARIOUS WATER SYSTEM | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Carmen |  | 2nd Eng'g. Dist. | Re-aligned to COVID |  |  | 2020 |  | . | VARIOUS WATER SYSTEM | [7 empty] | Date Allotment Released: |  | Date completed:
Carmen |  | 2nd Eng'g. Dist. | Re-aligned to COVID |  |  | 2020 |  | . | VARIOUS WATER SYSTEM | [7 empty] | Date Started:
Talaingod | Dagohoy | 1st Eng'g. Dist. | Procurement on process |  |  | 2020 |  | . | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | Construction Women Development Center, Dagohoy, Talaingod |  | 20% Development Fund CY 2020 | Building |  | sq.m |  | Project Cost: | 1000000 | Target Completion Date: |  | Program: | 1000000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Post qualification on process | Post qualification on process | Post qualification on process | Post qualification on process | Post qualification on process | Procurement on process
Talaingod | Dagohoy | 1st Eng'g. Dist. | Procurement on process |  |  | 2020 |  | . | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 1000000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
Talaingod | Dagohoy | 1st Eng'g. Dist. | Procurement on process |  |  | 2020 |  | . | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
Talaingod | Dagohoy | 1st Eng'g. Dist. | Procurement on process |  |  | 2020 |  | . | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Talaingod | Dagohoy | 1st Eng'g. Dist. | Procurement on process |  |  | 2020 |  | . | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Talaingod | Dagohoy | 1st Eng'g. Dist. | Procurement on process |  |  | 2020 |  | . | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Date Started:
Talaingod | Sto. Niño | 1st Eng'g. Dist. | Procurement on process |  |  | 2020 |  | . | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | Const. of Native Chicken Production House at Sitio Salawao, Brgy. Sto. Niño, Talaingod |  | 20% Development Fund CY 2020 | Building |  | sq.m |  | Project Cost: | 2000000 | Target Completion Date: |  | Program: | 2000000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Post qualification on process | Post qualification on process | Post qualification on process | Post qualification on process | Post qualification on process | Procurement on process
Talaingod | Sto. Niño | 1st Eng'g. Dist. | Procurement on process |  |  | 2020 |  | . | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 2000000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
Talaingod | Sto. Niño | 1st Eng'g. Dist. | Procurement on process |  |  | 2020 |  | . | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
Talaingod | Sto. Niño | 1st Eng'g. Dist. | Procurement on process |  |  | 2020 |  | . | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Talaingod | Sto. Niño | 1st Eng'g. Dist. | Procurement on process |  |  | 2020 |  | . | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Talaingod | Sto. Niño | 1st Eng'g. Dist. | Procurement on process |  |  | 2020 |  | . | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Date Started:
Sto. Tomas | Tulalian | 2nd Eng'g. Dist. | Re-aligned to COVID |  |  | 2020 |  | . | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | Construction of Fence at Tulalian National High School, Tulalian, Sto. Tomas |  | GENERAL FUND CY 2020 | Fence |  | sq.m |  | Project Cost: | 1500000 | Target Completion Date: |  | Program: | 1500000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
Sto. Tomas | Tulalian | 2nd Eng'g. Dist. | Re-aligned to COVID |  |  | 2020 |  | . | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 1500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
Sto. Tomas | Tulalian | 2nd Eng'g. Dist. | Re-aligned to COVID |  |  | 2020 |  | . | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
Sto. Tomas | Tulalian | 2nd Eng'g. Dist. | Re-aligned to COVID |  |  | 2020 |  | . | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Sto. Tomas | Tulalian | 2nd Eng'g. Dist. | Re-aligned to COVID |  |  | 2020 |  | . | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Sto. Tomas | Tulalian | 2nd Eng'g. Dist. | Re-aligned to COVID |  |  | 2020 |  | . | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Date Started:
Babak, IGCS | AB | 2nd Eng'g. Dist. | Re-aligned to COVID |  |  | 2020 |  | . | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | Construction of Commercial Building at Kinawitnon, IGACOS, Babak |  | 20% DF CY 2020 | Building |  | sq.m |  | Project Cost: | 2000000 | Target Completion Date: |  | Program: | 2000000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
Babak, IGCS | AB | 2nd Eng'g. Dist. | Re-aligned to COVID |  |  | 2020 |  | . | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 2000000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
Babak, IGCS | AB | 2nd Eng'g. Dist. | Re-aligned to COVID |  |  | 2020 |  | . | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
Babak, IGCS | AB | 2nd Eng'g. Dist. | Re-aligned to COVID |  |  | 2020 |  | . | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Babak, IGCS | AB | 2nd Eng'g. Dist. | Re-aligned to COVID |  |  | 2020 |  | . | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Babak, IGCS | AB | 2nd Eng'g. Dist. | Re-aligned to COVID |  |  | 2020 |  | . | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Date Started:
Carmen | Ising | 2nd Eng'g. Dist. | Plan on going |  |  | 2020 |  | . | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | Improvement of Provincial Engineer's Office 2nd District Office Phase 2, Carmen |  | 20% DF CY 2020 | Building |  | sq.m |  | Project Cost: | 1590000 | Target Completion Date: |  | Program: | 1590000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Plan and DED On-going | Plan and DED On-going | Plan and DED On-going | Plan and DED On-going | Plan and DED On-going | Plan and DED On-going
Carmen | Ising | 2nd Eng'g. Dist. | Plan on going |  |  | 2020 |  | . | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 1590000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
Carmen | Ising | 2nd Eng'g. Dist. | Plan on going |  |  | 2020 |  | . | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
Carmen | Ising | 2nd Eng'g. Dist. | Plan on going |  |  | 2020 |  | . | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Carmen | Ising | 2nd Eng'g. Dist. | Plan on going |  |  | 2020 |  | . | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Carmen | Ising | 2nd Eng'g. Dist. | Plan on going |  |  | 2020 |  | . | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Date Started:
Tagum City | Mankilam | 1st Eng'g. Dist. | Re-aligned to COVID |  |  | 2020 |  | . | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | Construction of DAVNOR Tech-Vocational Center, Government Center, Mankilam, Tagum City |  | 20% Development Fund CY 2020 | Building |  | sq.m | Admin | Project Cost: | 8000000 | Target Completion Date: |  | Program: | 8000000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
Tagum City | Mankilam | 1st Eng'g. Dist. | Re-aligned to COVID |  |  | 2020 |  | . | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 8000000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
Tagum City | Mankilam | 1st Eng'g. Dist. | Re-aligned to COVID |  |  | 2020 |  | . | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
Tagum City | Mankilam | 1st Eng'g. Dist. | Re-aligned to COVID |  |  | 2020 |  | . | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Tagum City | Mankilam | 1st Eng'g. Dist. | Re-aligned to COVID |  |  | 2020 |  | . | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Tagum City | Mankilam | 1st Eng'g. Dist. | Re-aligned to COVID |  |  | 2020 |  | . | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Date Started:
B.E. Dujali | Ising | 2nd Eng'g. Dist. | Procurement on process |  |  | 2020 |  | . | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | Construction of DDN hospital Carmen Zone Annex Building Phase 3, Carmen |  | GENERAL FUND CY 2020 | Building |  | sq.m |  | Project Cost: | 800000 | Target Completion Date: |  | Program: | 800000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Abstract #0420201476 | Abstract #0420201476 | Abstract #0420201476 | Abstract #0420201476 | Abstract #0420201476 | Procurement on process
B.E. Dujali | Ising | 2nd Eng'g. Dist. | Procurement on process |  |  | 2020 |  | . | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 800000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
B.E. Dujali | Ising | 2nd Eng'g. Dist. | Procurement on process |  |  | 2020 |  | . | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
B.E. Dujali | Ising | 2nd Eng'g. Dist. | Procurement on process |  |  | 2020 |  | . | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
B.E. Dujali | Ising | 2nd Eng'g. Dist. | Procurement on process |  |  | 2020 |  | . | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
B.E. Dujali | Ising | 2nd Eng'g. Dist. | Procurement on process |  |  | 2020 |  | . | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Date Started:
Tagum City | Mankilam | 1st Eng'g. Dist. | Plan on going |  |  | 2020 |  | . | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | Improvement of PSWDO Bodega Government Cente, Mankilam, Tagum City |  | 20% Development Fund CY 2020 | Building |  | sq.m | Admin | Project Cost: | 1000000 | Target Completion Date: |  | Program: | 1000000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | POW and Plans on-going | POW and Plans on-going | POW and Plans on-going | POW and Plans on-going | POW and Plans on-going | POW and Plans on-going
Tagum City | Mankilam | 1st Eng'g. Dist. | Plan on going |  |  | 2020 |  | . | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 1000000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
Tagum City | Mankilam | 1st Eng'g. Dist. | Plan on going |  |  | 2020 |  | . | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
Tagum City | Mankilam | 1st Eng'g. Dist. | Plan on going |  |  | 2020 |  | . | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Tagum City | Mankilam | 1st Eng'g. Dist. | Plan on going |  |  | 2020 |  | . | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Tagum City | Mankilam | 1st Eng'g. Dist. | Plan on going |  |  | 2020 |  | . | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Date Started:
San Isidro | Mamangan | 1st Eng'g. Dist. | Re-aligned to COVID |  |  | 2020 |  | . | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | Renovation/Improvement of MAFAMCO Consumer's Bldg., Brgy. Mamangan, San Isidro |  | 20% Development Fund CY 2020 | Building |  | sq.m | Contract | Project Cost: | 800000 | Target Completion Date: |  | Program: | 800000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
San Isidro | Mamangan | 1st Eng'g. Dist. | Re-aligned to COVID |  |  | 2020 |  | . | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 800000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
San Isidro | Mamangan | 1st Eng'g. Dist. | Re-aligned to COVID |  |  | 2020 |  | . | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
San Isidro | Mamangan | 1st Eng'g. Dist. | Re-aligned to COVID |  |  | 2020 |  | . | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
San Isidro | Mamangan | 1st Eng'g. Dist. | Re-aligned to COVID |  |  | 2020 |  | . | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
San Isidro | Mamangan | 1st Eng'g. Dist. | Re-aligned to COVID |  |  | 2020 |  | . | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Date Started:
Asuncion | Camansa | 1st Eng'g. Dist. | Re-aligned to COVID |  |  | 2020 |  | . | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | Construction of IP Council of Women Training Center, Camansa Kamadi District, Asuncion |  | 20% Development Fund CY 2020 | Building |  | sq.m | Admin | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
Asuncion | Camansa | 1st Eng'g. Dist. | Re-aligned to COVID |  |  | 2020 |  | . | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
Asuncion | Camansa | 1st Eng'g. Dist. | Re-aligned to COVID |  |  | 2020 |  | . | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
Asuncion | Camansa | 1st Eng'g. Dist. | Re-aligned to COVID |  |  | 2020 |  | . | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Asuncion | Camansa | 1st Eng'g. Dist. | Re-aligned to COVID |  |  | 2020 |  | . | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Asuncion | Camansa | 1st Eng'g. Dist. | Re-aligned to COVID |  |  | 2020 |  | . | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Date Started:
Asuncion | Cambanogoy | 1st Eng'g. Dist. | Re-aligned to COVID |  |  | 2020 |  | . | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | Construction of Municipal Triball Hall, Asuncion |  | 20% Development Fund CY 2020 | Building |  | sq.m | Contract | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
Asuncion | Cambanogoy | 1st Eng'g. Dist. | Re-aligned to COVID |  |  | 2020 |  | . | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
Asuncion | Cambanogoy | 1st Eng'g. Dist. | Re-aligned to COVID |  |  | 2020 |  | . | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
Asuncion | Cambanogoy | 1st Eng'g. Dist. | Re-aligned to COVID |  |  | 2020 |  | . | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Asuncion | Cambanogoy | 1st Eng'g. Dist. | Re-aligned to COVID |  |  | 2020 |  | . | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Asuncion | Cambanogoy | 1st Eng'g. Dist. | Re-aligned to COVID |  |  | 2020 |  | . | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Date Started:
Kapalong | Maniki | 1st Eng'g. Dist. | Re-aligned to COVID |  |  | 2020 |  | . | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | Construction of Municipal Triball Hall, Kapalong |  | 20% Development Fund CY 2020 | Building |  | sq.m | Contract | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
Kapalong | Maniki | 1st Eng'g. Dist. | Re-aligned to COVID |  |  | 2020 |  | . | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
Kapalong | Maniki | 1st Eng'g. Dist. | Re-aligned to COVID |  |  | 2020 |  | . | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
Kapalong | Maniki | 1st Eng'g. Dist. | Re-aligned to COVID |  |  | 2020 |  | . | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Kapalong | Maniki | 1st Eng'g. Dist. | Re-aligned to COVID |  |  | 2020 |  | . | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Kapalong | Maniki | 1st Eng'g. Dist. | Re-aligned to COVID |  |  | 2020 |  | . | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Date Started:
Talaingod | Sto. Niño | 1st Eng'g. Dist. | Re-aligned to COVID |  |  | 2020 |  | . | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | Construction of Municipal Triball Hall, Talaingod |  | 20% Development Fund CY 2020 | Building |  | sq.m | Contract | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
Talaingod | Sto. Niño | 1st Eng'g. Dist. | Re-aligned to COVID |  |  | 2020 |  | . | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
Talaingod | Sto. Niño | 1st Eng'g. Dist. | Re-aligned to COVID |  |  | 2020 |  | . | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
Talaingod | Sto. Niño | 1st Eng'g. Dist. | Re-aligned to COVID |  |  | 2020 |  | . | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Talaingod | Sto. Niño | 1st Eng'g. Dist. | Re-aligned to COVID |  |  | 2020 |  | . | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Talaingod | Sto. Niño | 1st Eng'g. Dist. | Re-aligned to COVID |  |  | 2020 |  | . | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Date Started:
Carmen | Carmen | 2nd Eng'g. Dist. | Re-aligned to COVID |  |  | 2020 |  | . | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | Construction of Municipal Triball Hall, Carmen |  | GENERAL FUND CY 2020 | Building |  | sq.m |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
Carmen | Carmen | 2nd Eng'g. Dist. | Re-aligned to COVID |  |  | 2020 |  | . | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
Carmen | Carmen | 2nd Eng'g. Dist. | Re-aligned to COVID |  |  | 2020 |  | . | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
Carmen | Carmen | 2nd Eng'g. Dist. | Re-aligned to COVID |  |  | 2020 |  | . | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Carmen | Carmen | 2nd Eng'g. Dist. | Re-aligned to COVID |  |  | 2020 |  | . | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Carmen | Carmen | 2nd Eng'g. Dist. | Re-aligned to COVID |  |  | 2020 |  | . | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Date Started:
B.E. Dujali | Dujali | 2nd Eng'g. Dist. | Re-aligned to COVID |  |  | 2020 |  | . | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | Construction of Municipal Triball Hall, B.E. Dujali |  | GENERAL FUND CY 2020 | Building |  | sq.m |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
B.E. Dujali | Dujali | 2nd Eng'g. Dist. | Re-aligned to COVID |  |  | 2020 |  | . | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
B.E. Dujali | Dujali | 2nd Eng'g. Dist. | Re-aligned to COVID |  |  | 2020 |  | . | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
B.E. Dujali | Dujali | 2nd Eng'g. Dist. | Re-aligned to COVID |  |  | 2020 |  | . | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
B.E. Dujali | Dujali | 2nd Eng'g. Dist. | Re-aligned to COVID |  |  | 2020 |  | . | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
B.E. Dujali | Dujali | 2nd Eng'g. Dist. | Re-aligned to COVID |  |  | 2020 |  | . | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Date Started:
Sto. Tomas | Tibal-og | 2nd Eng'g. Dist. | Re-aligned to COVID |  |  | 2020 |  | . | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | Construction of Municipal Triball Hall, Sto. Tomas |  | GENERAL FUND CY 2020 | Building |  | sq.m | Admin | Project Cost: | 500000 | Target Completion Date: | 2019-07-31 | Program: | 500000 | Planned: | 100% | Planned: | 100% | Planned: | 100% | Planned: | 100% | Planned: | 100% | No. of Persons: | 7 | Suspended June 28, 2019. Waiting for the delivery of JO Materials | Suspended June 28, 2019. Waiting for the delivery of JO Materials | Suspended June 28, 2019. Waiting for the delivery of JO Materials | Suspended June 28, 2019. Waiting for the delivery of JO Materials | Suspended June 28, 2019. Waiting for the delivery of JO Materials | Suspended June 28, 2019. Waiting for the delivery of JO Materials
Sto. Tomas | Tibal-og | 2nd Eng'g. Dist. | Re-aligned to COVID |  |  | 2020 |  | . | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Project Engineer: | Roque | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 110
Sto. Tomas | Tibal-og | 2nd Eng'g. Dist. | Re-aligned to COVID |  |  | 2020 |  | . | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: | 85% | Actual: | 85% | Actual: | 85% | Actual: | 85% | Actual: | 85%
Sto. Tomas | Tibal-og | 2nd Eng'g. Dist. | Re-aligned to COVID |  |  | 2020 |  | . | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Duration: | 70 | No. of days extended: |  |  |  | Slippage: | -15% | Slippage: | -15% | Slippage: | -15% | Slippage: | -15% | Slippage: | -15%
Sto. Tomas | Tibal-og | 2nd Eng'g. Dist. | Re-aligned to COVID |  |  | 2020 |  | . | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Date Allotment Released: | CY 2018 | Date completed:
Sto. Tomas | Tibal-og | 2nd Eng'g. Dist. | Re-aligned to COVID |  |  | 2020 |  | . | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Date Started: | 2019-05-22
New Corella | Cabidianan | 1st Eng'g. Dist. | Re-aligned to COVID |  |  | 2020 |  | . | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | Construction of One(1) unit School Building at Cabidianan E/S, New Corella |  | 20% Development Fund CY 2020 | Building |  | sq.m | Contract | Project Cost: | 1300000 | Target Completion Date: |  | Program: | 1300000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: | [6 empty] | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No 1
New Corella | Cabidianan | 1st Eng'g. Dist. | Re-aligned to COVID |  |  | 2020 |  | . | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 1300000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
New Corella | Cabidianan | 1st Eng'g. Dist. | Re-aligned to COVID |  |  | 2020 |  | . | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
New Corella | Cabidianan | 1st Eng'g. Dist. | Re-aligned to COVID |  |  | 2020 |  | . | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
New Corella | Cabidianan | 1st Eng'g. Dist. | Re-aligned to COVID |  |  | 2020 |  | . | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
New Corella | Cabidianan | 1st Eng'g. Dist. | Re-aligned to COVID |  |  | 2020 |  | . | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Date Started:
Kapalong | Florida | 1st Eng'g. Dist. | Realigned to COVID |  |  | 2020 |  | . | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | Construction of one(1) unit School Building at Kamansi Integrated School, Florida, kapalong |  | 20% Development Fund CY 2020 | Building |  | sq.m | Contract | Project Cost: | 1300000 | Target Completion Date: |  | Program: | 1300000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
Kapalong | Florida | 1st Eng'g. Dist. | Realigned to COVID |  |  | 2020 |  | . | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 1300000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
Kapalong | Florida | 1st Eng'g. Dist. | Realigned to COVID |  |  | 2020 |  | . | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
Kapalong | Florida | 1st Eng'g. Dist. | Realigned to COVID |  |  | 2020 |  | . | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Kapalong | Florida | 1st Eng'g. Dist. | Realigned to COVID |  |  | 2020 |  | . | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Kapalong | Florida | 1st Eng'g. Dist. | Realigned to COVID |  |  | 2020 |  | . | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Date Started:
Asuncion | Magatos | 1st Eng'g. Dist. | Realigned to COVID |  |  | 2020 |  | . | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | Construction of one(1) unit School Building at Magatos E/S, Magatos, Asuncion |  | 20% Development Fund CY 2020 | Building |  | sq.m | Contract | Project Cost: | 1300000 | Target Completion Date: |  | Program: | 1300000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
Asuncion | Magatos | 1st Eng'g. Dist. | Realigned to COVID |  |  | 2020 |  | . | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 1300000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
Asuncion | Magatos | 1st Eng'g. Dist. | Realigned to COVID |  |  | 2020 |  | . | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
Asuncion | Magatos | 1st Eng'g. Dist. | Realigned to COVID |  |  | 2020 |  | . | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Asuncion | Magatos | 1st Eng'g. Dist. | Realigned to COVID |  |  | 2020 |  | . | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Asuncion | Magatos | 1st Eng'g. Dist. | Realigned to COVID |  |  | 2020 |  | . | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Date Started:
Talaingod | Sta. Cruz | 1st Eng'g. Dist. | Realigned to COVID |  |  | 2020 |  | . | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | Construction of one(1) unit School Building at Sta. Cruz E/S, New Corella |  | 20% Development Fund CY 2020 | Building |  | sq.m |  | Project Cost: | 1300000 | Target Completion Date: |  | Program: | 1300000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
Talaingod | Sta. Cruz | 1st Eng'g. Dist. | Realigned to COVID |  |  | 2020 |  | . | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 1300000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
Talaingod | Sta. Cruz | 1st Eng'g. Dist. | Realigned to COVID |  |  | 2020 |  | . | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
Talaingod | Sta. Cruz | 1st Eng'g. Dist. | Realigned to COVID |  |  | 2020 |  | . | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Talaingod | Sta. Cruz | 1st Eng'g. Dist. | Realigned to COVID |  |  | 2020 |  | . | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Talaingod | Sta. Cruz | 1st Eng'g. Dist. | Realigned to COVID |  |  | 2020 |  | . | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Date Started:
Carmen | Tibulao | 2nd Eng'g. Dist. | Realigned to COVID |  |  | 2020 |  | . | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | Construction of Two(2) Classroom at Tibulao Elem. School, Tibulao, Carmen |  | 20% Development Fund CY 2020 | Building |  | sq.m |  | Project Cost: | 2900000 | Target Completion Date: |  | Program: | 2900000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
Carmen | Tibulao | 2nd Eng'g. Dist. | Realigned to COVID |  |  | 2020 |  | . | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 2900000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
Carmen | Tibulao | 2nd Eng'g. Dist. | Realigned to COVID |  |  | 2020 |  | . | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
Carmen | Tibulao | 2nd Eng'g. Dist. | Realigned to COVID |  |  | 2020 |  | . | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Carmen | Tibulao | 2nd Eng'g. Dist. | Realigned to COVID |  |  | 2020 |  | . | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Carmen | Tibulao | 2nd Eng'g. Dist. | Realigned to COVID |  |  | 2020 |  | . | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Date Started:
Tagum City | Mankilam | 1st Eng'g. Dist. | Realigned to COVID |  |  | 2020 |  | . | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | Expansion of Balay Silangan (Phase 2), Gov't. Center, Mankilam |  | 20% Development Fund CY 2020 | Building |  | sq.m |  | Project Cost: | 5000000 | Target Completion Date: |  | Program: | 5000000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
Tagum City | Mankilam | 1st Eng'g. Dist. | Realigned to COVID |  |  | 2020 |  | . | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 5000000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
Tagum City | Mankilam | 1st Eng'g. Dist. | Realigned to COVID |  |  | 2020 |  | . | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
Tagum City | Mankilam | 1st Eng'g. Dist. | Realigned to COVID |  |  | 2020 |  | . | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Tagum City | Mankilam | 1st Eng'g. Dist. | Realigned to COVID |  |  | 2020 |  | . | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Tagum City | Mankilam | 1st Eng'g. Dist. | Realigned to COVID |  |  | 2020 |  | . | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT LS - 17,500,000.00 | [7 empty] | Date Started:
New Corella | Limbaan | 1st Eng'g. Dist. | Realigned to COVID |  |  | 2020 |  | . | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | Const. of Day Care Center, Limbaan, New Corella |  | 20% DF CY 2020 | Building |  | sq.m |  | Project Cost: | 1000000 | Target Completion Date: |  | Program: | 1000000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
New Corella | Limbaan | 1st Eng'g. Dist. | Realigned to COVID |  |  | 2020 |  | . | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 1000000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
New Corella | Limbaan | 1st Eng'g. Dist. | Realigned to COVID |  |  | 2020 |  | . | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
New Corella | Limbaan | 1st Eng'g. Dist. | Realigned to COVID |  |  | 2020 |  | . | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
New Corella | Limbaan | 1st Eng'g. Dist. | Realigned to COVID |  |  | 2020 |  | . | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
New Corella | Limbaan | 1st Eng'g. Dist. | Realigned to COVID |  |  | 2020 |  | . | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Date Started:
Kapalong | Gabuyan | 1st Eng'g. Dist. | Realigned to COVID |  |  | 2020 |  | . | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | Const. of Day Care Center, Gabuyan, kapalong |  | 20% DF CY 2020 | Building |  | sq.m |  | Project Cost: | 1000000 | Target Completion Date: |  | Program: | 1000000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
Kapalong | Gabuyan | 1st Eng'g. Dist. | Realigned to COVID |  |  | 2020 |  | . | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 1000000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
Kapalong | Gabuyan | 1st Eng'g. Dist. | Realigned to COVID |  |  | 2020 |  | . | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
Kapalong | Gabuyan | 1st Eng'g. Dist. | Realigned to COVID |  |  | 2020 |  | . | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Kapalong | Gabuyan | 1st Eng'g. Dist. | Realigned to COVID |  |  | 2020 |  | . | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Kapalong | Gabuyan | 1st Eng'g. Dist. | Realigned to COVID |  |  | 2020 |  | . | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Date Started:
Asuncion | Canatan | 1st Eng'g. Dist. | Realigned to COVID |  |  | 2020 |  | . | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | Compl./Rep. Day Care Center,Canatan, Asuncion |  | 20% DF CY 2020 | Building |  | sq.m |  | Project Cost: | 300000 | Target Completion Date: |  | Program: | 300000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
Asuncion | Canatan | 1st Eng'g. Dist. | Realigned to COVID |  |  | 2020 |  | . | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 300000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
Asuncion | Canatan | 1st Eng'g. Dist. | Realigned to COVID |  |  | 2020 |  | . | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
Asuncion | Canatan | 1st Eng'g. Dist. | Realigned to COVID |  |  | 2020 |  | . | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Asuncion | Canatan | 1st Eng'g. Dist. | Realigned to COVID |  |  | 2020 |  | . | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Asuncion | Canatan | 1st Eng'g. Dist. | Realigned to COVID |  |  | 2020 |  | . | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Date Started:
Asuncion | Cambanogoy | 1st Eng'g. Dist. | Realigned to COVID |  |  | 2020 |  | . | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | Compl./Rep. Day Care Center,Cambanogoy, Asuncion |  | 20% DF CY 2020 | Building |  | sq.m |  | Project Cost: | 300000 | Target Completion Date: |  | Program: | 300000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
Asuncion | Cambanogoy | 1st Eng'g. Dist. | Realigned to COVID |  |  | 2020 |  | . | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 300000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
Asuncion | Cambanogoy | 1st Eng'g. Dist. | Realigned to COVID |  |  | 2020 |  | . | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
Asuncion | Cambanogoy | 1st Eng'g. Dist. | Realigned to COVID |  |  | 2020 |  | . | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Asuncion | Cambanogoy | 1st Eng'g. Dist. | Realigned to COVID |  |  | 2020 |  | . | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Asuncion | Cambanogoy | 1st Eng'g. Dist. | Realigned to COVID |  |  | 2020 |  | . | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Date Started:
Kapalong | Gabuyan | 1st Eng'g. Dist. | Realigned to COVID |  |  | 2020 |  | . | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | Compl./Rep. Day Care Center,Gabuyan, kapalong |  | 20% DF CY 2020 | Building |  | sq.m |  | Project Cost: | 600000 | Target Completion Date: |  | Program: | 600000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
Kapalong | Gabuyan | 1st Eng'g. Dist. | Realigned to COVID |  |  | 2020 |  | . | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 600000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
Kapalong | Gabuyan | 1st Eng'g. Dist. | Realigned to COVID |  |  | 2020 |  | . | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
Kapalong | Gabuyan | 1st Eng'g. Dist. | Realigned to COVID |  |  | 2020 |  | . | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Kapalong | Gabuyan | 1st Eng'g. Dist. | Realigned to COVID |  |  | 2020 |  | . | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Kapalong | Gabuyan | 1st Eng'g. Dist. | Realigned to COVID |  |  | 2020 |  | . | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Date Started:
New Corella | New Sambog | 1st Eng'g. Dist. | Realigned to COVID |  |  | 2020 |  | . | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | Compl./Rep. Day Care Center,New Sambog, New Corella |  | 20% DF CY 2020 | Building |  | sq.m |  | Project Cost: | 300000 | Target Completion Date: |  | Program: | 300000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
New Corella | New Sambog | 1st Eng'g. Dist. | Realigned to COVID |  |  | 2020 |  | . | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 300000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
New Corella | New Sambog | 1st Eng'g. Dist. | Realigned to COVID |  |  | 2020 |  | . | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
New Corella | New Sambog | 1st Eng'g. Dist. | Realigned to COVID |  |  | 2020 |  | . | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
New Corella | New Sambog | 1st Eng'g. Dist. | Realigned to COVID |  |  | 2020 |  | . | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
New Corella | New Sambog | 1st Eng'g. Dist. | Realigned to COVID |  |  | 2020 |  | . | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Date Started:
New Corella | Cabidianan | 1st Eng'g. Dist. | Realigned to COVID |  |  | 2020 |  | . | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | Compl./Rep. Day Care Center, Cabidianan, New Corella |  | 20% DF CY 2020 | Building |  | sq.m |  | Project Cost: | 300000 | Target Completion Date: |  | Program: | 300000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
New Corella | Cabidianan | 1st Eng'g. Dist. | Realigned to COVID |  |  | 2020 |  | . | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 300000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
New Corella | Cabidianan | 1st Eng'g. Dist. | Realigned to COVID |  |  | 2020 |  | . | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
New Corella | Cabidianan | 1st Eng'g. Dist. | Realigned to COVID |  |  | 2020 |  | . | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
New Corella | Cabidianan | 1st Eng'g. Dist. | Realigned to COVID |  |  | 2020 |  | . | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
New Corella | Cabidianan | 1st Eng'g. Dist. | Realigned to COVID |  |  | 2020 |  | . | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Date Started:
San Isidro | Igangon | 1st Eng'g. Dist. | Realigned to COVID |  |  | 2020 |  | . | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | Compl./Rep. Day Care Center, Igangon, San Isidro |  | 20% DF CY 2020 | Building |  | sq.m |  | Project Cost: | 300000 | Target Completion Date: |  | Program: | 300000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
San Isidro | Igangon | 1st Eng'g. Dist. | Realigned to COVID |  |  | 2020 |  | . | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 300000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
San Isidro | Igangon | 1st Eng'g. Dist. | Realigned to COVID |  |  | 2020 |  | . | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
San Isidro | Igangon | 1st Eng'g. Dist. | Realigned to COVID |  |  | 2020 |  | . | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
San Isidro | Igangon | 1st Eng'g. Dist. | Realigned to COVID |  |  | 2020 |  | . | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
San Isidro | Igangon | 1st Eng'g. Dist. | Realigned to COVID |  |  | 2020 |  | . | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Date Started:
Tagum City | Madaum | 1st Eng'g. Dist. | Realigned to COVID |  |  | 2020 |  | . | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | Compl./Rep. Day Care Center, Madaum, Tagum City |  | 20% DF CY 2020 | Building |  | sq.m |  | Project Cost: | 300000 | Target Completion Date: |  | Program: | 300000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
Tagum City | Madaum | 1st Eng'g. Dist. | Realigned to COVID |  |  | 2020 |  | . | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 300000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
Tagum City | Madaum | 1st Eng'g. Dist. | Realigned to COVID |  |  | 2020 |  | . | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
Tagum City | Madaum | 1st Eng'g. Dist. | Realigned to COVID |  |  | 2020 |  | . | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Tagum City | Madaum | 1st Eng'g. Dist. | Realigned to COVID |  |  | 2020 |  | . | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Tagum City | Madaum | 1st Eng'g. Dist. | Realigned to COVID |  |  | 2020 |  | . | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Date Started:
Tagum City | Apokon | 1st Eng'g. Dist. | Realigned to COVID |  |  | 2020 |  | . | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | Compl./Rep. Day Care Center, Apokon, Tagum City |  | 20% DF CY 2020 | Building |  | sq.m |  | Project Cost: | 300000 | Target Completion Date: |  | Program: | 300000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
Tagum City | Apokon | 1st Eng'g. Dist. | Realigned to COVID |  |  | 2020 |  | . | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 300000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
Tagum City | Apokon | 1st Eng'g. Dist. | Realigned to COVID |  |  | 2020 |  | . | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
Tagum City | Apokon | 1st Eng'g. Dist. | Realigned to COVID |  |  | 2020 |  | . | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Tagum City | Apokon | 1st Eng'g. Dist. | Realigned to COVID |  |  | 2020 |  | . | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Tagum City | Apokon | 1st Eng'g. Dist. | Realigned to COVID |  |  | 2020 |  | . | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Date Started:
Talaingod | Sto. Niño | 1st Eng'g. Dist. | Realigned to COVID |  |  | 2020 |  | . | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | Compl./Rep. Day Care Center, Sto. Niño, Talaingod |  | 20% DF CY 2020 | Building |  | sq.m |  | Project Cost: | 300000 | Target Completion Date: |  | Program: | 300000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
Talaingod | Sto. Niño | 1st Eng'g. Dist. | Realigned to COVID |  |  | 2020 |  | . | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 300000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
Talaingod | Sto. Niño | 1st Eng'g. Dist. | Realigned to COVID |  |  | 2020 |  | . | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
Talaingod | Sto. Niño | 1st Eng'g. Dist. | Realigned to COVID |  |  | 2020 |  | . | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Talaingod | Sto. Niño | 1st Eng'g. Dist. | Realigned to COVID |  |  | 2020 |  | . | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Talaingod | Sto. Niño | 1st Eng'g. Dist. | Realigned to COVID |  |  | 2020 |  | . | SOCIAL WELFARE AND DEVELOPMENT (CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) LS - P5,000,000.00 | [7 empty] | Date Started:
Panabo City | J.P. Laurel | 2nd Eng'g. Dist. | Realigned to COVID |  |  | 2020 |  | . | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | Const. of Day Care Center, JP Laurel, Panabo City |  | AB CY 2020 | Building |  | sq.m |  | Project Cost: | 1000000 | Target Completion Date: |  | Program: | 1000000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
Panabo City | J.P. Laurel | 2nd Eng'g. Dist. | Realigned to COVID |  |  | 2020 |  | . | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 1000000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
Panabo City | J.P. Laurel | 2nd Eng'g. Dist. | Realigned to COVID |  |  | 2020 |  | . | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
Panabo City | J.P. Laurel | 2nd Eng'g. Dist. | Realigned to COVID |  |  | 2020 |  | . | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Panabo City | J.P. Laurel | 2nd Eng'g. Dist. | Realigned to COVID |  |  | 2020 |  | . | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | [7 empty] | Date Allotment Released: |  | Date completed:
Panabo City | J.P. Laurel | 2nd Eng'g. Dist. | Realigned to COVID |  |  | 2020 |  | . | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | [7 empty] | Date Started:
B.E. Dujali | Dujali | 2nd Eng'g. Dist. | Realigned to COVID |  |  | 2020 |  | . | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | Const. of Day Care Center, Dujali, B.E. Dujali |  | AB CY 2020 | Building |  | sq.m |  | Project Cost: | 1000000 | Target Completion Date: |  | Program: | 1000000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
B.E. Dujali | Dujali | 2nd Eng'g. Dist. | Realigned to COVID |  |  | 2020 |  | . | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 1000000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
B.E. Dujali | Dujali | 2nd Eng'g. Dist. | Realigned to COVID |  |  | 2020 |  | . | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
B.E. Dujali | Dujali | 2nd Eng'g. Dist. | Realigned to COVID |  |  | 2020 |  | . | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
B.E. Dujali | Dujali | 2nd Eng'g. Dist. | Realigned to COVID |  |  | 2020 |  | . | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | [7 empty] | Date Allotment Released: |  | Date completed:
B.E. Dujali | Dujali | 2nd Eng'g. Dist. | Realigned to COVID |  |  | 2020 |  | . | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | [7 empty] | Date Started:
Sto. Tomas | Tibal-og | 2nd Eng'g. Dist. | Realigned to COVID |  |  | 2020 |  | . | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | Const. of Day Care Center, Tibal-og, Sto Tomas |  | AB CY 2020 | Building |  | sq.m |  | Project Cost: | 1000000 | Target Completion Date: |  | Program: | 1000000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
Sto. Tomas | Tibal-og | 2nd Eng'g. Dist. | Realigned to COVID |  |  | 2020 |  | . | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 1000000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
Sto. Tomas | Tibal-og | 2nd Eng'g. Dist. | Realigned to COVID |  |  | 2020 |  | . | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
Sto. Tomas | Tibal-og | 2nd Eng'g. Dist. | Realigned to COVID |  |  | 2020 |  | . | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Sto. Tomas | Tibal-og | 2nd Eng'g. Dist. | Realigned to COVID |  |  | 2020 |  | . | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | [7 empty] | Date Allotment Released: |  | Date completed:
Sto. Tomas | Tibal-og | 2nd Eng'g. Dist. | Realigned to COVID |  |  | 2020 |  | . | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | [7 empty] | Date Started:
B.E. Dujali | Cabay-angan | 2nd Eng'g. Dist. | Realigned to COVID |  |  | 2020 |  | . | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | Compl./Rep. Day Care Center, Cabay-angan, B.E. Dujali |  | AB CY 2020 | Building |  | sq.m |  | Project Cost: | 300000 | Target Completion Date: |  | Program: | 300000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
B.E. Dujali | Cabay-angan | 2nd Eng'g. Dist. | Realigned to COVID |  |  | 2020 |  | . | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 300000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
B.E. Dujali | Cabay-angan | 2nd Eng'g. Dist. | Realigned to COVID |  |  | 2020 |  | . | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
B.E. Dujali | Cabay-angan | 2nd Eng'g. Dist. | Realigned to COVID |  |  | 2020 |  | . | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
B.E. Dujali | Cabay-angan | 2nd Eng'g. Dist. | Realigned to COVID |  |  | 2020 |  | . | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | [7 empty] | Date Allotment Released: |  | Date completed:
B.E. Dujali | Cabay-angan | 2nd Eng'g. Dist. | Realigned to COVID |  |  | 2020 |  | . | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | [7 empty] | Date Started:
B.E. Dujali | Tanglaw | 2nd Eng'g. Dist. | Realigned to COVID |  |  | 2020 |  | . | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | Compl./Rep. Day Care Center, Tanglaw, B.E. Dujali |  | AB CY 2020 | Building |  | sq.m |  | Project Cost: | 300000 | Target Completion Date: |  | Program: | 300000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
B.E. Dujali | Tanglaw | 2nd Eng'g. Dist. | Realigned to COVID |  |  | 2020 |  | . | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 300000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
B.E. Dujali | Tanglaw | 2nd Eng'g. Dist. | Realigned to COVID |  |  | 2020 |  | . | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
B.E. Dujali | Tanglaw | 2nd Eng'g. Dist. | Realigned to COVID |  |  | 2020 |  | . | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
B.E. Dujali | Tanglaw | 2nd Eng'g. Dist. | Realigned to COVID |  |  | 2020 |  | . | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | [7 empty] | Date Allotment Released: |  | Date completed:
B.E. Dujali | Tanglaw | 2nd Eng'g. Dist. | Realigned to COVID |  |  | 2020 |  | . | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | [7 empty] | Date Started:
Carmen | Salvacion | 2nd Eng'g. Dist. | Realigned to COVID |  |  | 2020 |  | . | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | Compl./Rep. Day Care Center, Salvacion, Carmen |  | AB CY 2020 | Building |  | sq.m |  | Project Cost: | 300000 | Target Completion Date: |  | Program: | 300000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
Carmen | Salvacion | 2nd Eng'g. Dist. | Realigned to COVID |  |  | 2020 |  | . | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 300000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
Carmen | Salvacion | 2nd Eng'g. Dist. | Realigned to COVID |  |  | 2020 |  | . | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
Carmen | Salvacion | 2nd Eng'g. Dist. | Realigned to COVID |  |  | 2020 |  | . | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Carmen | Salvacion | 2nd Eng'g. Dist. | Realigned to COVID |  |  | 2020 |  | . | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | [7 empty] | Date Allotment Released: |  | Date completed:
Carmen | Salvacion | 2nd Eng'g. Dist. | Realigned to COVID |  |  | 2020 |  | . | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | [7 empty] | Date Started:
IGCS | San Agustin | 2nd Eng'g. Dist. | Realigned to COVID |  |  | 2020 |  | . | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | Compl./Rep. Day Care Center, San Agustin, IGCS |  | AB CY 2020 | Building |  | sq.m |  | Project Cost: | 300000 | Target Completion Date: |  | Program: | 300000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
IGCS | San Agustin | 2nd Eng'g. Dist. | Realigned to COVID |  |  | 2020 |  | . | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 300000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
IGCS | San Agustin | 2nd Eng'g. Dist. | Realigned to COVID |  |  | 2020 |  | . | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
IGCS | San Agustin | 2nd Eng'g. Dist. | Realigned to COVID |  |  | 2020 |  | . | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
IGCS | San Agustin | 2nd Eng'g. Dist. | Realigned to COVID |  |  | 2020 |  | . | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | [7 empty] | Date Allotment Released: |  | Date completed:
IGCS | San Agustin | 2nd Eng'g. Dist. | Realigned to COVID |  |  | 2020 |  | . | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | [7 empty] | Date Started:
IGCS | Toril | 2nd Eng'g. Dist. | Realigned to COVID |  |  | 2020 |  | . | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | Compl./Rep. Day Care Center, Toril, IGCS |  | AB CY 2020 | Building |  | sq.m |  | Project Cost: | 300000 | Target Completion Date: |  | Program: | 300000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
IGCS | Toril | 2nd Eng'g. Dist. | Realigned to COVID |  |  | 2020 |  | . | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 300000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
IGCS | Toril | 2nd Eng'g. Dist. | Realigned to COVID |  |  | 2020 |  | . | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
IGCS | Toril | 2nd Eng'g. Dist. | Realigned to COVID |  |  | 2020 |  | . | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
IGCS | Toril | 2nd Eng'g. Dist. | Realigned to COVID |  |  | 2020 |  | . | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | [7 empty] | Date Allotment Released: |  | Date completed:
IGCS | Toril | 2nd Eng'g. Dist. | Realigned to COVID |  |  | 2020 |  | . | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | [7 empty] | Date Started:
Sto. Tomas | Tibal-og | 2nd Eng'g. Dist. | Realigned to COVID |  |  | 2020 |  | . | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | Compl./Rep. Day Care Center, Tibal-og, Sto. Tomas |  | AB CY 2020 | Building |  | sq.m |  | Project Cost: | 600000 | Target Completion Date: |  | Program: | 600000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
Sto. Tomas | Tibal-og | 2nd Eng'g. Dist. | Realigned to COVID |  |  | 2020 |  | . | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 600000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
Sto. Tomas | Tibal-og | 2nd Eng'g. Dist. | Realigned to COVID |  |  | 2020 |  | . | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
Sto. Tomas | Tibal-og | 2nd Eng'g. Dist. | Realigned to COVID |  |  | 2020 |  | . | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Sto. Tomas | Tibal-og | 2nd Eng'g. Dist. | Realigned to COVID |  |  | 2020 |  | . | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | [7 empty] | Date Allotment Released: |  | Date completed:
Sto. Tomas | Tibal-og | 2nd Eng'g. Dist. | Realigned to COVID |  |  | 2020 |  | . | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | [7 empty] | Date Started:
Sto. Tomas | Talomo | 2nd Eng'g. Dist. | Realigned to COVID |  |  | 2020 |  | . | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | Compl./Rep. Day Care Center, Talomo, Sto. Tomas |  | AB CY 2020 | Building |  | sq.m |  | Project Cost: | 300000 | Target Completion Date: |  | Program: | 300000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
Sto. Tomas | Talomo | 2nd Eng'g. Dist. | Realigned to COVID |  |  | 2020 |  | . | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 300000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
Sto. Tomas | Talomo | 2nd Eng'g. Dist. | Realigned to COVID |  |  | 2020 |  | . | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
Sto. Tomas | Talomo | 2nd Eng'g. Dist. | Realigned to COVID |  |  | 2020 |  | . | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Sto. Tomas | Talomo | 2nd Eng'g. Dist. | Realigned to COVID |  |  | 2020 |  | . | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | [7 empty] | Date Allotment Released: |  | Date completed:
Sto. Tomas | Talomo | 2nd Eng'g. Dist. | Realigned to COVID |  |  | 2020 |  | . | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | [7 empty] | Date Started:
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | Realigned to COVID |  |  | 2020 |  | . | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | Compl./Rep. Day Care Center, Kinamayan, Sto. Tomas |  | AB CY 2020 | Building |  | sq.m |  | Project Cost: | 300000 | Target Completion Date: |  | Program: | 300000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | Realigned to COVID |  |  | 2020 |  | . | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 300000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | Realigned to COVID |  |  | 2020 |  | . | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | Realigned to COVID |  |  | 2020 |  | . | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | Realigned to COVID |  |  | 2020 |  | . | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | [7 empty] | Date Allotment Released: |  | Date completed:
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | Realigned to COVID |  |  | 2020 |  | . | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | [7 empty] | Date Started:
Sto. Tomas | La Libertad | 2nd Eng'g. Dist. | Realigned to COVID |  |  | 2020 |  | . | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | Compl./Rep. Day Care Center, La Libertad, Sto. Tomas |  | AB CY 2020 | Building |  | sq.m |  | Project Cost: | 300000 | Target Completion Date: |  | Program: | 300000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
Sto. Tomas | La Libertad | 2nd Eng'g. Dist. | Realigned to COVID |  |  | 2020 |  | . | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 300000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
Sto. Tomas | La Libertad | 2nd Eng'g. Dist. | Realigned to COVID |  |  | 2020 |  | . | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
Sto. Tomas | La Libertad | 2nd Eng'g. Dist. | Realigned to COVID |  |  | 2020 |  | . | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Sto. Tomas | La Libertad | 2nd Eng'g. Dist. | Realigned to COVID |  |  | 2020 |  | . | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | [7 empty] | Date Allotment Released: |  | Date completed:
Sto. Tomas | La Libertad | 2nd Eng'g. Dist. | Realigned to COVID |  |  | 2020 |  | . | CHILD DEVELOPMENT CENTER (Const./Compl. & Repair of Day Care Center) | [7 empty] | Date Started:
New Corella | Poblacion | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | HEALTH CARE SERVICES PROGRAM (PEEDO) | Improvement/Rehab. Of Luntiang Paraiso, New Corella |  | 20% DF CY 2020 | Building |  | km |  | Project Cost: | 3000000 | Target Completion Date: |  | Program: | 3000000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | For Purchase Request | For Purchase Request | For Purchase Request | For Purchase Request | For Purchase Request | Procurement on process
New Corella | Poblacion | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | HEALTH CARE SERVICES PROGRAM (PEEDO) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 3000000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
New Corella | Poblacion | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | HEALTH CARE SERVICES PROGRAM (PEEDO) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
New Corella | Poblacion | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | HEALTH CARE SERVICES PROGRAM (PEEDO) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
New Corella | Poblacion | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | HEALTH CARE SERVICES PROGRAM (PEEDO) | [7 empty] | Date Allotment Released: |  | Date completed:
New Corella | Poblacion | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | HEALTH CARE SERVICES PROGRAM (PEEDO) | [7 empty] | Date Started:
Tagum City | AAT | 1st Eng'g. Dist. | On-going | 2020-05-18 |  | 2020 |  | . | VARIOUS LOCAL ROADS & DRAINAGE DEV'T. PROJECT - LS P15,590,910.00 | Rehab. Of Various Local Roads @ Tagum City |  | 20% Development Fund CY 2020 | Rehabilitaion |  | km | Admin | Project Cost: | 2518182 | Target Completion Date: | 2020-10-20 | Program: | 2518182 | Planned: | 48.18% | Planned: | 48.18% | Planned: | 87.52% | Planned: | 87.52% | Planned: | 98.14% | No. of Persons: | 8 | On-going | On-going | On-going | On-going | On-going | On-going
Tagum City | AAT | 1st Eng'g. Dist. | On-going | 2020-05-18 |  | 2020 |  | . | VARIOUS LOCAL ROADS & DRAINAGE DEV'T. PROJECT - LS P15,590,910.00 | [7 empty] | Project Engineer: | Bataller | Revised Completion Date: |  | Allotment: | 2518182 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 120
Tagum City | AAT | 1st Eng'g. Dist. | On-going | 2020-05-18 |  | 2020 |  | . | VARIOUS LOCAL ROADS & DRAINAGE DEV'T. PROJECT - LS P15,590,910.00 | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: | 48.18% | Actual: | 48.18% | Actual: | 87.65% | Actual: | 87.65% | Actual: | 84.78%
Tagum City | AAT | 1st Eng'g. Dist. | On-going | 2020-05-18 |  | 2020 |  | . | VARIOUS LOCAL ROADS & DRAINAGE DEV'T. PROJECT - LS P15,590,910.00 | [7 empty] | Duration: | 155 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0.13% | Slippage: | 0.13% | Slippage: | -13.36%
Tagum City | AAT | 1st Eng'g. Dist. | On-going | 2020-05-18 |  | 2020 |  | . | VARIOUS LOCAL ROADS & DRAINAGE DEV'T. PROJECT - LS P15,590,910.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Tagum City | AAT | 1st Eng'g. Dist. | On-going | 2020-05-18 |  | 2020 |  | . | VARIOUS LOCAL ROADS & DRAINAGE DEV'T. PROJECT - LS P15,590,910.00 | [7 empty] | Date Started: | 2020-05-18
Asuncion | AAA | 1st Eng'g. Dist. | On-going | 2020-05-18 |  | 2020 |  | . | VARIOUS LOCAL ROADS & DRAINAGE DEV'T. PROJECT - LS P15,590,910.00 | Rehab. Of Various Local Roads @ Asuncion |  | 20% Development Fund CY 2020 | Rehabilitaion |  | km | Admin | Project Cost: | 2518182 | Target Completion Date: | 2020-10-20 | Program: | 2518182 | Planned: | 37.83% | Planned: | 37.83% | Planned: | 37.83% | Planned: | 37.83% | Planned: | 88.98% | No. of Persons: | 12 | On-going | On-going | On-going | On-going | On-going | On-going
Asuncion | AAA | 1st Eng'g. Dist. | On-going | 2020-05-18 |  | 2020 |  | . | VARIOUS LOCAL ROADS & DRAINAGE DEV'T. PROJECT - LS P15,590,910.00 | [7 empty] | Project Engineer: | Bataller | Revised Completion Date: |  | Allotment: | 2518182 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 372
Asuncion | AAA | 1st Eng'g. Dist. | On-going | 2020-05-18 |  | 2020 |  | . | VARIOUS LOCAL ROADS & DRAINAGE DEV'T. PROJECT - LS P15,590,910.00 | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: | 37.82% | Actual: | 37.82% | Actual: | 37.82% | Actual: | 37.82% | Actual: | 45%
Asuncion | AAA | 1st Eng'g. Dist. | On-going | 2020-05-18 |  | 2020 |  | . | VARIOUS LOCAL ROADS & DRAINAGE DEV'T. PROJECT - LS P15,590,910.00 | [7 empty] | Duration: | 155 | No. of days extended: |  |  |  | Slippage: | -0.01% | Slippage: | -0.01% | Slippage: | -0.01% | Slippage: | -0.01% | Slippage: | -43.98%
Asuncion | AAA | 1st Eng'g. Dist. | On-going | 2020-05-18 |  | 2020 |  | . | VARIOUS LOCAL ROADS & DRAINAGE DEV'T. PROJECT - LS P15,590,910.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Asuncion | AAA | 1st Eng'g. Dist. | On-going | 2020-05-18 |  | 2020 |  | . | VARIOUS LOCAL ROADS & DRAINAGE DEV'T. PROJECT - LS P15,590,910.00 | [7 empty] | Date Started: | 2020-05-18
Kapalong | AAK | 1st Eng'g. Dist. | On-going | 2020-07-15 |  | 2020 |  | . | VARIOUS LOCAL ROADS & DRAINAGE DEV'T. PROJECT - LS P15,590,910.00 | Rehab. Of Various Local Roads @ Kapalong |  | 20% Development Fund CY 2020 | Rehabilitaion |  | km | Admin | Project Cost: | 2518182 | Target Completion Date: | 2020-10-07 | Program: | 2518182 | Planned: | 18.24% | Planned: | 36.22% | Planned: | 91.3% | Planned: | 76.61% | Planned: | 100% | No. of Persons: | 12 | On-going | On-going | On-going | On-going | On-going | On-going
Kapalong | AAK | 1st Eng'g. Dist. | On-going | 2020-07-15 |  | 2020 |  | . | VARIOUS LOCAL ROADS & DRAINAGE DEV'T. PROJECT - LS P15,590,910.00 | [7 empty] | Project Engineer: | Bataller | Revised Completion Date: |  | Allotment: | 2518182 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 180
Kapalong | AAK | 1st Eng'g. Dist. | On-going | 2020-07-15 |  | 2020 |  | . | VARIOUS LOCAL ROADS & DRAINAGE DEV'T. PROJECT - LS P15,590,910.00 | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: | 18.24% | Actual: | 36.22% | Actual: | 91.28% | Actual: | 76.61% | Actual: | 81.61%
Kapalong | AAK | 1st Eng'g. Dist. | On-going | 2020-07-15 |  | 2020 |  | . | VARIOUS LOCAL ROADS & DRAINAGE DEV'T. PROJECT - LS P15,590,910.00 | [7 empty] | Duration: | 84 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | -0.02% | Slippage: | 0% | Slippage: | -18.39%
Kapalong | AAK | 1st Eng'g. Dist. | On-going | 2020-07-15 |  | 2020 |  | . | VARIOUS LOCAL ROADS & DRAINAGE DEV'T. PROJECT - LS P15,590,910.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Kapalong | AAK | 1st Eng'g. Dist. | On-going | 2020-07-15 |  | 2020 |  | . | VARIOUS LOCAL ROADS & DRAINAGE DEV'T. PROJECT - LS P15,590,910.00 | [7 empty] | Date Started: | 2020-07-15
New Corella | AAN | 1st Eng'g. Dist. | On-going | 2020-08-03 |  | 2020 |  | . | VARIOUS LOCAL ROADS & DRAINAGE DEV'T. PROJECT - LS P15,590,910.00 | Rehab. Of Various Local Roads @ New Corella |  | 20% Development Fund CY 2020 | Rehabilitaion |  | km | Admin | Project Cost: | 2518182 | Target Completion Date: | 2020-10-21 23:59 | Program: | 2518182 | Planned: |  | Planned: | 35.54% | Planned: |  | Planned: |  | Planned: | 100% | No. of Persons: | 13 | POW on process | On-going | POW on process | POW on process | POW on process | On-going
New Corella | AAN | 1st Eng'g. Dist. | On-going | 2020-08-03 |  | 2020 |  | . | VARIOUS LOCAL ROADS & DRAINAGE DEV'T. PROJECT - LS P15,590,910.00 | [7 empty] | Project Engineer: | Bataller | Revised Completion Date: |  | Allotment: | 2518182 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 403
New Corella | AAN | 1st Eng'g. Dist. | On-going | 2020-08-03 |  | 2020 |  | . | VARIOUS LOCAL ROADS & DRAINAGE DEV'T. PROJECT - LS P15,590,910.00 | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: | 15.46% | Actual: |  | Actual: |  | Actual: | 79.92%
New Corella | AAN | 1st Eng'g. Dist. | On-going | 2020-08-03 |  | 2020 |  | . | VARIOUS LOCAL ROADS & DRAINAGE DEV'T. PROJECT - LS P15,590,910.00 | [7 empty] | Duration: | 80 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | -20.08% | Slippage: | 0% | Slippage: | 0% | Slippage: | -20.08%
New Corella | AAN | 1st Eng'g. Dist. | On-going | 2020-08-03 |  | 2020 |  | . | VARIOUS LOCAL ROADS & DRAINAGE DEV'T. PROJECT - LS P15,590,910.00 | [7 empty] | Date Allotment Released: |  | Date completed:
New Corella | AAN | 1st Eng'g. Dist. | On-going | 2020-08-03 |  | 2020 |  | . | VARIOUS LOCAL ROADS & DRAINAGE DEV'T. PROJECT - LS P15,590,910.00 | [7 empty] | Date Started: | 2020-08-03
San Isidro | AAS | 1st Eng'g. Dist. | On-going | 2020-08-03 |  | 2020 |  | . | VARIOUS LOCAL ROADS & DRAINAGE DEV'T. PROJECT - LS P15,590,910.00 | Rehab. Of Various Local Roads @ San Isidro |  | 20% Development Fund CY 2020 | Rehabilitaion |  | km | Admin | Project Cost: | 2518182 | Target Completion Date: | 2020-10-21 23:59 | Program: | 2518182 | Planned: |  | Planned: | 35.54% | Planned: | 73.27% | Planned: | 73.27% | Planned: | 100% | No. of Persons: | 10 | For implementation | On-going | On-going | On-going | On-going | On-going
San Isidro | AAS | 1st Eng'g. Dist. | On-going | 2020-08-03 |  | 2020 |  | . | VARIOUS LOCAL ROADS & DRAINAGE DEV'T. PROJECT - LS P15,590,910.00 | [7 empty] | Project Engineer: | Bataller | Revised Completion Date: |  | Allotment: | 2518182 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 150
San Isidro | AAS | 1st Eng'g. Dist. | On-going | 2020-08-03 |  | 2020 |  | . | VARIOUS LOCAL ROADS & DRAINAGE DEV'T. PROJECT - LS P15,590,910.00 | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: | 35.54% | Actual: | 73.26% | Actual: | 73.26% | Actual: | 79.92%
San Isidro | AAS | 1st Eng'g. Dist. | On-going | 2020-08-03 |  | 2020 |  | . | VARIOUS LOCAL ROADS & DRAINAGE DEV'T. PROJECT - LS P15,590,910.00 | [7 empty] | Duration: | 80 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | -0.01% | Slippage: | -0.01% | Slippage: | -20.08%
San Isidro | AAS | 1st Eng'g. Dist. | On-going | 2020-08-03 |  | 2020 |  | . | VARIOUS LOCAL ROADS & DRAINAGE DEV'T. PROJECT - LS P15,590,910.00 | [7 empty] | Date Allotment Released: |  | Date completed:
San Isidro | AAS | 1st Eng'g. Dist. | On-going | 2020-08-03 |  | 2020 |  | . | VARIOUS LOCAL ROADS & DRAINAGE DEV'T. PROJECT - LS P15,590,910.00 | [7 empty] | Date Started: | 2020-08-03
Talaingod | AAT | 1st Eng'g. Dist. | On-going | 2020-07-15 |  | 2020 |  | . | VARIOUS LOCAL ROADS & DRAINAGE DEV'T. PROJECT - LS P15,590,910.00 | Rehab. Of Various Local Roads @ Talaingod |  | 20% Development Fund CY 2020 | Rehabilitaion |  | km | Admin | Project Cost: | 2518182 | Target Completion Date: | 2020-12-12 | Program: | 2518182 | Planned: | 10.3% | Planned: | 10.3% | Planned: | 51.1% | Planned: | 51.1% | Planned: | 91.91% | No. of Persons: | 9 | On-going | On-going | On-going | On-going | On-going | On-going
Talaingod | AAT | 1st Eng'g. Dist. | On-going | 2020-07-15 |  | 2020 |  | . | VARIOUS LOCAL ROADS & DRAINAGE DEV'T. PROJECT - LS P15,590,910.00 | [7 empty] | Project Engineer: | Bataller | Revised Completion Date: |  | Allotment: | 2518182 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 135
Talaingod | AAT | 1st Eng'g. Dist. | On-going | 2020-07-15 |  | 2020 |  | . | VARIOUS LOCAL ROADS & DRAINAGE DEV'T. PROJECT - LS P15,590,910.00 | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: | 10.3% | Actual: | 10.3% | Actual: | 51.11% | Actual: | 51.11% | Actual: | 91.91%
Talaingod | AAT | 1st Eng'g. Dist. | On-going | 2020-07-15 |  | 2020 |  | . | VARIOUS LOCAL ROADS & DRAINAGE DEV'T. PROJECT - LS P15,590,910.00 | [7 empty] | Duration: | 150 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0.01% | Slippage: | 0.01% | Slippage: | 0%
Talaingod | AAT | 1st Eng'g. Dist. | On-going | 2020-07-15 |  | 2020 |  | . | VARIOUS LOCAL ROADS & DRAINAGE DEV'T. PROJECT - LS P15,590,910.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Talaingod | AAT | 1st Eng'g. Dist. | On-going | 2020-07-15 |  | 2020 |  | . | VARIOUS LOCAL ROADS & DRAINAGE DEV'T. PROJECT - LS P15,590,910.00 | [7 empty] | Date Started: | 2020-07-15
IGCS | AI | 2nd Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | Various Local Roads & Drainage Dev't. Project | Rehab. Of Various Local Roads @ Island Garden City of Samal |  | 20% DF CY 2020 | Rehabilitation |  | km |  | Project Cost: | 2518182 | Target Completion Date: |  | Program: | 2518182 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Plan On-going | Plan On-going | Plan On-going | Plan On-going | Plan On-going | Plan On-going
IGCS | AI | 2nd Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | Various Local Roads & Drainage Dev't. Project | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 2518182 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
IGCS | AI | 2nd Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | Various Local Roads & Drainage Dev't. Project | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
IGCS | AI | 2nd Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | Various Local Roads & Drainage Dev't. Project | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
IGCS | AI | 2nd Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | Various Local Roads & Drainage Dev't. Project | [7 empty] | Date Allotment Released: |  | Date completed:
IGCS | AI | 2nd Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | Various Local Roads & Drainage Dev't. Project | [7 empty] | Date Started:
Panabo City | APC | 2nd Eng'g. Dist. | On-going | 2020-05-15 |  | 2020 |  | . | Various Local Roads & Drainage Dev't. Project | Rehab. Of Various Local Roads @ Panabo City |  | 20% DF CY 2020 | Rehabilitation |  | km |  | Project Cost: | 2518182 | Target Completion Date: | 2020-10-12 | Program: | 2518182 | Planned: |  | Planned: |  | Planned: |  | Planned: | 75% | Planned: | 75% | No. of Persons: | 5 | Abstract # 0420201633 - Billboard; Abstract 0520201661 - hardware | Abstract # 0420201633 - Billboard; Abstract 0520201661 - hardware | Abstract # 0420201633 - Billboard; Abstract 0520201661 - hardware | On-going | On-going | On-going
Panabo City | APC | 2nd Eng'g. Dist. | On-going | 2020-05-15 |  | 2020 |  | . | Various Local Roads & Drainage Dev't. Project | [7 empty] | Project Engineer: | Gamad/Clar | Revised Completion Date: |  | Allotment: | 2518182 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 110
Panabo City | APC | 2nd Eng'g. Dist. | On-going | 2020-05-15 |  | 2020 |  | . | Various Local Roads & Drainage Dev't. Project | [7 empty] | Implementor: | Admin | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: | 80% | Actual: | 80%
Panabo City | APC | 2nd Eng'g. Dist. | On-going | 2020-05-15 |  | 2020 |  | . | Various Local Roads & Drainage Dev't. Project | [7 empty] | Duration: | 150 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 5% | Slippage: | 5%
Panabo City | APC | 2nd Eng'g. Dist. | On-going | 2020-05-15 |  | 2020 |  | . | Various Local Roads & Drainage Dev't. Project | [7 empty] | Date Allotment Released: |  | Date completed:
Panabo City | APC | 2nd Eng'g. Dist. | On-going | 2020-05-15 |  | 2020 |  | . | Various Local Roads & Drainage Dev't. Project | [7 empty] | Date Started: | 2020-05-15
B.E. Dujali | ABD | 2nd Eng'g. Dist. | On-going | 2020-07-16 |  | 2020 |  | . | Various Local Roads & Drainage Dev't. Project | Rehab. Of Various Local Roads @ B.E Dujali |  | 20% DF CY 2020 | Rehabilitation |  | km |  | Project Cost: | 2518182 | Target Completion Date: | 2020-12-13 | Program: | 2518182 | Planned: |  | Planned: |  | Planned: |  | Planned: | 35% | Planned: | 35% | No. of Persons: | 4 | Purchase Request # 20053256 - Hardware; PR # 20053255 - Billboard | Purchase Request # 20053256 - Hardware; PR # 20053255 - Billboard | Purchase Request # 20053256 - Hardware; PR # 20053255 - Billboard | On-going | On-going | On-going
B.E. Dujali | ABD | 2nd Eng'g. Dist. | On-going | 2020-07-16 |  | 2020 |  | . | Various Local Roads & Drainage Dev't. Project | [7 empty] | Project Engineer: | Gamad/Clar | Revised Completion Date: |  | Allotment: | 2518182 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 88
B.E. Dujali | ABD | 2nd Eng'g. Dist. | On-going | 2020-07-16 |  | 2020 |  | . | Various Local Roads & Drainage Dev't. Project | [7 empty] | Implementor: | Admin | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: | 52% | Actual: | 52%
B.E. Dujali | ABD | 2nd Eng'g. Dist. | On-going | 2020-07-16 |  | 2020 |  | . | Various Local Roads & Drainage Dev't. Project | [7 empty] | Duration: | 150 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 17% | Slippage: | 17%
B.E. Dujali | ABD | 2nd Eng'g. Dist. | On-going | 2020-07-16 |  | 2020 |  | . | Various Local Roads & Drainage Dev't. Project | [7 empty] | Date Allotment Released: |  | Date completed:
B.E. Dujali | ABD | 2nd Eng'g. Dist. | On-going | 2020-07-16 |  | 2020 |  | . | Various Local Roads & Drainage Dev't. Project | [7 empty] | Date Started: | 2020-07-16
Carmen | AC | 2nd Eng'g. Dist. | On-going | 2020-05-18 |  | 2020 |  | . | Various Local Roads & Drainage Dev't. Project | Rehab. Of Various Local Roads @ Carmen |  | 20% DF CY 2020 | Rehabilitation |  | km |  | Project Cost: | 2518182 | Target Completion Date: | 2020-10-15 | Program: | 2518182 | Planned: |  | Planned: |  | Planned: |  | Planned: | 35% | Planned: | 35% | No. of Persons: | 3 | Abstract # 0420201633 - Billboard; Abstract 0520201661 - hardware | Abstract # 0420201633 - Billboard; Abstract 0520201661 - hardware | Abstract # 0420201633 - Billboard; Abstract 0520201661 - hardware | On-going | On-going | On-going
Carmen | AC | 2nd Eng'g. Dist. | On-going | 2020-05-18 |  | 2020 |  | . | Various Local Roads & Drainage Dev't. Project | [7 empty] | Project Engineer: | Gamad/Clar | Revised Completion Date: |  | Allotment: | 2518182 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 66
Carmen | AC | 2nd Eng'g. Dist. | On-going | 2020-05-18 |  | 2020 |  | . | Various Local Roads & Drainage Dev't. Project | [7 empty] | Implementor: | Admin | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: | 52% | Actual: | 52%
Carmen | AC | 2nd Eng'g. Dist. | On-going | 2020-05-18 |  | 2020 |  | . | Various Local Roads & Drainage Dev't. Project | [7 empty] | Duration: | 150 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 17% | Slippage: | 17%
Carmen | AC | 2nd Eng'g. Dist. | On-going | 2020-05-18 |  | 2020 |  | . | Various Local Roads & Drainage Dev't. Project | [7 empty] | Date Allotment Released: |  | Date completed:
Carmen | AC | 2nd Eng'g. Dist. | On-going | 2020-05-18 |  | 2020 |  | . | Various Local Roads & Drainage Dev't. Project | [7 empty] | Date Started: | 2020-05-18
Sto. Tomas | AST | 2nd Eng'g. Dist. | On-going | 2020-07-16 |  | 2020 |  | . | Various Local Roads & Drainage Dev't. Project | Rehab. Of Various Local Roads @ Sto. Tomas |  | 20% DF CY 2020 | Rehabilitation |  | km |  | Project Cost: | 2518182 | Target Completion Date: | 2020-12-13 | Program: | 2518182 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: | 60% | No. of Persons: | 3 | Plan On-going | Plan On-going | Plan On-going | Plan On-going | Plan On-going | On-going
Sto. Tomas | AST | 2nd Eng'g. Dist. | On-going | 2020-07-16 |  | 2020 |  | . | Various Local Roads & Drainage Dev't. Project | [7 empty] | Project Engineer: | Gamad/Clar | Revised Completion Date: |  | Allotment: | 2518182 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 66
Sto. Tomas | AST | 2nd Eng'g. Dist. | On-going | 2020-07-16 |  | 2020 |  | . | Various Local Roads & Drainage Dev't. Project | [7 empty] | Implementor: | Admin | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual: | 65%
Sto. Tomas | AST | 2nd Eng'g. Dist. | On-going | 2020-07-16 |  | 2020 |  | . | Various Local Roads & Drainage Dev't. Project | [7 empty] | Duration: | 150 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 5%
Sto. Tomas | AST | 2nd Eng'g. Dist. | On-going | 2020-07-16 |  | 2020 |  | . | Various Local Roads & Drainage Dev't. Project | [7 empty] | Date Allotment Released: |  | Date completed:
Sto. Tomas | AST | 2nd Eng'g. Dist. | On-going | 2020-07-16 |  | 2020 |  | . | Various Local Roads & Drainage Dev't. Project | [7 empty] | Date Started: | 2020-07-16
Carmen |  | 2nd Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | Desiltation/Excavation of Rivers & Creeks | Improvement and Desiltation of Camoning Creek |  | 5% Calamity Fund CY 2020 | Desiltation |  | ln.m |  | Project Cost: | 2500000 | Target Completion Date: |  | Program: | 2500000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Abstract # 0520201658 | Abstract # 0520201658 | Abstract # 0520201658 | Abstract # 0520201658 | Abstract # 0520201658 | Abstract # 0520201658
Carmen |  | 2nd Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | Desiltation/Excavation of Rivers & Creeks | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 2500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
Carmen |  | 2nd Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | Desiltation/Excavation of Rivers & Creeks | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
Carmen |  | 2nd Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | Desiltation/Excavation of Rivers & Creeks | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Carmen |  | 2nd Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | Desiltation/Excavation of Rivers & Creeks | [7 empty] | Date Allotment Released: |  | Date completed:
Carmen |  | 2nd Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | Desiltation/Excavation of Rivers & Creeks | [7 empty] | Date Started:
Carmen | Ising | 2nd Eng'g. Dist. | On-going | 2020-07-16 |  | 2020 |  | . | Desiltation/Excavation of Rivers & Creeks | Improvement and Desiltation of Ising Creek |  | 5% Calamity Fund CY 2020 | Desiltation |  | ln.m |  | Project Cost: | 2000000 | Target Completion Date: | 2020-10-24 | Program: | 2000000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: | 100% | No. of Persons: |  | Abstract # 0420201637; 0520201662 | Abstract # 0420201637; 0520201662 | Abstract # 0420201637; 0520201662 | On-going (Resumption date 10/23/2020) | On-going (Resumption date 10/23/2020) | On-going
Carmen | Ising | 2nd Eng'g. Dist. | On-going | 2020-07-16 |  | 2020 |  | . | Desiltation/Excavation of Rivers & Creeks | [7 empty] | Project Engineer: | Toquero | Revised Completion Date: |  | Allotment: | 2000000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
Carmen | Ising | 2nd Eng'g. Dist. | On-going | 2020-07-16 |  | 2020 |  | . | Desiltation/Excavation of Rivers & Creeks | [7 empty] | Implementor: | Admin | No. of days suspended: | 99 | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: | 1.21% | Actual: | 50%
Carmen | Ising | 2nd Eng'g. Dist. | On-going | 2020-07-16 |  | 2020 |  | . | Desiltation/Excavation of Rivers & Creeks | [7 empty] | Duration: | 100 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 1.21% | Slippage: | -50%
Carmen | Ising | 2nd Eng'g. Dist. | On-going | 2020-07-16 |  | 2020 |  | . | Desiltation/Excavation of Rivers & Creeks | [7 empty] | Date Allotment Released: |  | Date completed:
Carmen | Ising | 2nd Eng'g. Dist. | On-going | 2020-07-16 |  | 2020 |  | . | Desiltation/Excavation of Rivers & Creeks | [7 empty] | Date Started: | 2020-07-16
Carmen | Anibongan | 2nd Eng'g. Dist. | On-going | 2020-07-16 |  | 2020 |  | . | Desiltation/Excavation of Rivers & Creeks | Desiltation of Buhang Creek, Anibongan, Carmen |  | 5% Calamity Fund CY 2020 | Desiltation |  | ln.m |  | Project Cost: | 2130206 | Target Completion Date: | 2020-10-18 | Program: | 2130206 | Planned: |  | Planned: |  | Planned: |  | Planned: | 50% | Planned: | 100% | No. of Persons: | 4 | Abstract # 0520201657; 0420201626 | Abstract # 0520201657; 0420201626 | Abstract # 0520201657; 0420201626 | On-going | On-going | On-going
Carmen | Anibongan | 2nd Eng'g. Dist. | On-going | 2020-07-16 |  | 2020 |  | . | Desiltation/Excavation of Rivers & Creeks | [7 empty] | Project Engineer: | Toquero | Revised Completion Date: |  | Allotment: | 2130206 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 88
Carmen | Anibongan | 2nd Eng'g. Dist. | On-going | 2020-07-16 |  | 2020 |  | . | Desiltation/Excavation of Rivers & Creeks | [7 empty] | Implementor: | Admin | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: | 50% | Actual: | 55%
Carmen | Anibongan | 2nd Eng'g. Dist. | On-going | 2020-07-16 |  | 2020 |  | . | Desiltation/Excavation of Rivers & Creeks | [7 empty] | Duration: | 94 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | -45%
Carmen | Anibongan | 2nd Eng'g. Dist. | On-going | 2020-07-16 |  | 2020 |  | . | Desiltation/Excavation of Rivers & Creeks | [7 empty] | Date Allotment Released: |  | Date completed:
Carmen | Anibongan | 2nd Eng'g. Dist. | On-going | 2020-07-16 |  | 2020 |  | . | Desiltation/Excavation of Rivers & Creeks | [7 empty] | Date Started: | 2020-07-16
Asuncion | Sonlon | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | DISASTER PREVENTION AND MITIGATION PROGRAM - FLOOD CONTROL AND SLOPE PROTECTION PROJECT (Improvement of Bridges and Cross Drainage) | Improvement of Saug-Sonlon-Bdry. Longanapan |  | 5% CALAMITY FUND CY 2020 | Road |  | km |  | Project Cost: | 1000000 | Target Completion Date: |  | Program: | 1000000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | For preparation of POW and Plans | For preparation of POW and Plans | For preparation of POW and Plans | For preparation of POW and Plans | For preparation of POW and Plans | For preparation of POW and Plans
Asuncion | Sonlon | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | DISASTER PREVENTION AND MITIGATION PROGRAM - FLOOD CONTROL AND SLOPE PROTECTION PROJECT (Improvement of Bridges and Cross Drainage) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 1000000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
Asuncion | Sonlon | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | DISASTER PREVENTION AND MITIGATION PROGRAM - FLOOD CONTROL AND SLOPE PROTECTION PROJECT (Improvement of Bridges and Cross Drainage) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
Asuncion | Sonlon | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | DISASTER PREVENTION AND MITIGATION PROGRAM - FLOOD CONTROL AND SLOPE PROTECTION PROJECT (Improvement of Bridges and Cross Drainage) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Asuncion | Sonlon | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | DISASTER PREVENTION AND MITIGATION PROGRAM - FLOOD CONTROL AND SLOPE PROTECTION PROJECT (Improvement of Bridges and Cross Drainage) | [7 empty] | Date Allotment Released: |  | Date completed:
Asuncion | Sonlon | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | DISASTER PREVENTION AND MITIGATION PROGRAM - FLOOD CONTROL AND SLOPE PROTECTION PROJECT (Improvement of Bridges and Cross Drainage) | [7 empty] | Date Started:
Carmen | Mangalcal | 2nd Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | Improvement of Bridges and Cross Drainage | Single Barrel Box Culvert at Mangalcal-Diamond Creek, Brgy. Mangalcal, Carmen |  | 5% Calamity Fund CY 2020 | Box Culvert |  | ln.m |  | Project Cost: | 2000000 | Target Completion Date: |  | Program: | 2000000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
Carmen | Mangalcal | 2nd Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | Improvement of Bridges and Cross Drainage | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 2000000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
Carmen | Mangalcal | 2nd Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | Improvement of Bridges and Cross Drainage | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
Carmen | Mangalcal | 2nd Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | Improvement of Bridges and Cross Drainage | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Carmen | Mangalcal | 2nd Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | Improvement of Bridges and Cross Drainage | [7 empty] | Date Allotment Released: |  | Date completed:
Carmen | Mangalcal | 2nd Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | Improvement of Bridges and Cross Drainage | [7 empty] | Date Started:
Carmen | Mangalcal | 2nd Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | Improvement of Roads, Drainage and Canal | Improvement of Mangalcal to Diamond Creek Farm to Market Road Opening |  | 5% Calamity Fund CY 2020 | Improvement |  | ln.m |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
Carmen | Mangalcal | 2nd Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | Improvement of Roads, Drainage and Canal | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
Carmen | Mangalcal | 2nd Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | Improvement of Roads, Drainage and Canal | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
Carmen | Mangalcal | 2nd Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | Improvement of Roads, Drainage and Canal | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Carmen | Mangalcal | 2nd Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | Improvement of Roads, Drainage and Canal | [7 empty] | Date Allotment Released: |  | Date completed:
Carmen | Mangalcal | 2nd Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | Improvement of Roads, Drainage and Canal | [7 empty] | Date Started:
Carmen | Mabaus | 2nd Eng'g. Dist. | On-going | 2020-07-16 |  | 2020 |  | . | Improvement of Roads, Drainage and Canal | Improvement of Mabaus - Salvacion Provincial Road Continuing Road Opening |  | 5% Calamity Fund CY 2020 | Improvement |  | ln.m |  | Project Cost: | 500000 | Target Completion Date: | 2020-08-11 | Program: | 500000 | Planned: |  | Planned: |  | Planned: |  | Planned: | 100% | Planned: | 100% | No. of Persons: |  | Plan On-going | Plan On-going | Plan On-going | Suspended due to unavailability of equipment, area under stabilization | Suspended due to unavailability of equipment, area under stabilization | On-going
Carmen | Mabaus | 2nd Eng'g. Dist. | On-going | 2020-07-16 |  | 2020 |  | . | Improvement of Roads, Drainage and Canal | [7 empty] | Project Engineer: | Toquero | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
Carmen | Mabaus | 2nd Eng'g. Dist. | On-going | 2020-07-16 |  | 2020 |  | . | Improvement of Roads, Drainage and Canal | [7 empty] | Implementor: | Admin | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: | 1.3% | Actual: | 30%
Carmen | Mabaus | 2nd Eng'g. Dist. | On-going | 2020-07-16 |  | 2020 |  | . | Improvement of Roads, Drainage and Canal | [7 empty] | Duration: | 26 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | -98.7% | Slippage: | -70%
Carmen | Mabaus | 2nd Eng'g. Dist. | On-going | 2020-07-16 |  | 2020 |  | . | Improvement of Roads, Drainage and Canal | [7 empty] | Date Allotment Released: |  | Date completed:
Carmen | Mabaus | 2nd Eng'g. Dist. | On-going | 2020-07-16 |  | 2020 |  | . | Improvement of Roads, Drainage and Canal | [7 empty] | Date Started: | 2020-07-16
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | DISASTER PREVENTION AND MITIGATION PROGRAM - FLOOD CONTROL AND SLOPE PROTECTION PROJECT (Revetment of Dike and Slope Protection) | Rehab./Impv't. of Sto. Niño-Daligdigon-Paiton |  | 5% CALAMITY FUND CY 2020 | Road |  | km |  | Project Cost: | 1000000 | Target Completion Date: |  | Program: | 1000000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | DISASTER PREVENTION AND MITIGATION PROGRAM - FLOOD CONTROL AND SLOPE PROTECTION PROJECT (Revetment of Dike and Slope Protection) | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 1000000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | DISASTER PREVENTION AND MITIGATION PROGRAM - FLOOD CONTROL AND SLOPE PROTECTION PROJECT (Revetment of Dike and Slope Protection) | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | DISASTER PREVENTION AND MITIGATION PROGRAM - FLOOD CONTROL AND SLOPE PROTECTION PROJECT (Revetment of Dike and Slope Protection) | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | DISASTER PREVENTION AND MITIGATION PROGRAM - FLOOD CONTROL AND SLOPE PROTECTION PROJECT (Revetment of Dike and Slope Protection) | [7 empty] | Date Allotment Released: |  | Date completed:
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | DISASTER PREVENTION AND MITIGATION PROGRAM - FLOOD CONTROL AND SLOPE PROTECTION PROJECT (Revetment of Dike and Slope Protection) | [7 empty] | Date Started:
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | Revetment of Dike and Slope Protection | Rehab./Impv't. of San Miguel - Moslog - Kinamayan, Sto. Tomas |  | 5% Calamity Fund CY 2020 | Rehabilitation |  | ln.m |  | Project Cost: | 1000000 | Target Completion Date: |  | Program: | 1000000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | Revetment of Dike and Slope Protection | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 1000000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | Revetment of Dike and Slope Protection | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | Revetment of Dike and Slope Protection | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | Revetment of Dike and Slope Protection | [7 empty] | Date Allotment Released: |  | Date completed:
Sto. Tomas | Kinamayan | 2nd Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | Revetment of Dike and Slope Protection | [7 empty] | Date Started:
Kapalong | Gupitan | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | Const. of 1 Classroom @ Mankay Integrated School, Gupitan, kapalong |  | AB - SEF CY 2020 | Building |  | sq.m |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Opening of Shopping on June 25, 2020 | Opening of Shopping on June 25, 2020 | Opening of Shopping on June 25, 2020 | Opening of Shopping on June 25, 2020 | Opening of Shopping on June 25, 2020 | Procurement on process
Kapalong | Gupitan | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
Kapalong | Gupitan | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
Kapalong | Gupitan | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Kapalong | Gupitan | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Kapalong | Gupitan | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Date Started:
Kapalong | Gupitan | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | Const. of 1 Classroom @ Luno-luno E/S, Gupitan, kapalong |  | AB - SEF CY 2020 | Building |  | sq.m |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Opening of Shopping on June 25, 2020 | Opening of Shopping on June 25, 2020 | Opening of Shopping on June 25, 2020 | Opening of Shopping on June 25, 2020 | Opening of Shopping on June 25, 2020 | Procurement on process
Kapalong | Gupitan | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
Kapalong | Gupitan | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
Kapalong | Gupitan | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Kapalong | Gupitan | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Kapalong | Gupitan | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Date Started:
Kapalong | Gupitan | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | Const. of 1 Classroom @ Kamunuan E/S, Gupitan, kapalong |  | AB - SEF CY 2020 | Building |  | sq.m |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Opening of Shopping on June 25, 2020 | Opening of Shopping on June 25, 2020 | Opening of Shopping on June 25, 2020 | Opening of Shopping on June 25, 2020 | Opening of Shopping on June 25, 2020 | Procurement on process
Kapalong | Gupitan | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
Kapalong | Gupitan | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
Kapalong | Gupitan | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Kapalong | Gupitan | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Kapalong | Gupitan | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Date Started:
Kapalong | Gupitan | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | Const. of 1 Classroom @ Tawinian E/S, Gupitan, kapalong |  | AB - SEF CY 2020 | Building |  | sq.m |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Opening of Shopping on June 25, 2020 | Opening of Shopping on June 25, 2020 | Opening of Shopping on June 25, 2020 | Opening of Shopping on June 25, 2020 | Opening of Shopping on June 25, 2020 | Procurement on process
Kapalong | Gupitan | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
Kapalong | Gupitan | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
Kapalong | Gupitan | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Kapalong | Gupitan | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Kapalong | Gupitan | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Date Started:
Kapalong | Gupitan | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | Const. of 1 Classroom @ Aninipot E/S, Gupitan, kapalong |  | AB - SEF CY 2020 | Building |  | sq.m |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Opening of Shopping on June 25, 2020 | Opening of Shopping on June 25, 2020 | Opening of Shopping on June 25, 2020 | Opening of Shopping on June 25, 2020 | Opening of Shopping on June 25, 2020 | Procurement on process
Kapalong | Gupitan | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
Kapalong | Gupitan | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
Kapalong | Gupitan | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Kapalong | Gupitan | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Kapalong | Gupitan | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Date Started:
Kapalong | Gupitan | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | Const. of 1 Classroom @ Moling E/S, Gupitan, kapalong |  | AB - SEF CY 2020 | Building |  | sq.m |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Opening of Shopping on June 25, 2020 | Opening of Shopping on June 25, 2020 | Opening of Shopping on June 25, 2020 | Opening of Shopping on June 25, 2020 | Opening of Shopping on June 25, 2020 | Procurement on process
Kapalong | Gupitan | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
Kapalong | Gupitan | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
Kapalong | Gupitan | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Kapalong | Gupitan | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Kapalong | Gupitan | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Date Started:
Sto. Tomas | Magwawa | 2nd Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | Const. of 1 Classroom @ Mangga E/S, Magwawa, Sto. Tomas |  | AB - SEF CY 2020 | Building |  | sq.m |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Opening of Shopping on June 25, 2020 | Opening of Shopping on June 25, 2020 | Opening of Shopping on June 25, 2020 | Opening of Shopping on June 25, 2020 | Opening of Shopping on June 25, 2020 | Procurement on process
Sto. Tomas | Magwawa | 2nd Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
Sto. Tomas | Magwawa | 2nd Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
Sto. Tomas | Magwawa | 2nd Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Sto. Tomas | Magwawa | 2nd Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Sto. Tomas | Magwawa | 2nd Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Date Started:
Talaingod | Dagohoy | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | Const. of 1 Classroom @ Lomondong E/S, Dagohoy, Talaingod |  | AB - SEF CY 2020 | Building |  | sq.m |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Opening of Shopping on June 25, 2020 | Opening of Shopping on June 25, 2020 | Opening of Shopping on June 25, 2020 | Opening of Shopping on June 25, 2020 | Opening of Shopping on June 25, 2020 | Procurement on process
Talaingod | Dagohoy | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
Talaingod | Dagohoy | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
Talaingod | Dagohoy | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Talaingod | Dagohoy | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Talaingod | Dagohoy | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Date Started:
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | Const. of 1 Classroom @ Malapanit E/S, Sto. Niño, Talaingod |  | AB - SEF CY 2020 | Building |  | sq.m |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Opening of Shopping on June 25, 2020 | Opening of Shopping on June 25, 2020 | Opening of Shopping on June 25, 2020 | Opening of Shopping on June 25, 2020 | Opening of Shopping on June 25, 2020 | Procurement on process
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Date Started:
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | Const. of 1 Classroom @ Laputlakan E/S, Sto. Niño, Talaingod |  | AB - SEF CY 2020 | Building |  | sq.m |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Opening of Shopping on June 25, 2020 | Opening of Shopping on June 25, 2020 | Opening of Shopping on June 25, 2020 | Opening of Shopping on June 25, 2020 | Opening of Shopping on June 25, 2020 | Procurement on process
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Date Allotment Released: |  | Date completed:
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | Const./Impv't./Compl. Of School Bldgs, Struct. & Fac. LS - P4,000,000.00 | [7 empty] | Date Started:
Tagum City | Mankilam | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | PSYDO YOUTH DEV'T. PROGRAM - TEEN TAMBAYAN PROJECT | Renovation of Teen Tambayan |  | 20% DF CY 2020 | Building |  | sq.m | Contract | Project Cost: | 500000 | Target Completion Date: | 2020-12-22 | Program: | 500000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: | 100% | No. of Persons: |  | Date of procurement June 30, 2020 | Date of procurement June 30, 2020 | Date of procurement June 30, 2020 | Date of procurement June 30, 2020 | Date of procurement June 30, 2020 | Procurement on process
Tagum City | Mankilam | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | PSYDO YOUTH DEV'T. PROGRAM - TEEN TAMBAYAN PROJECT | [7 empty] | Project Engineer: | Quirante | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
Tagum City | Mankilam | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | PSYDO YOUTH DEV'T. PROGRAM - TEEN TAMBAYAN PROJECT | [7 empty] | Implementor: | JJR Const. & Supply | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual: | 100%
Tagum City | Mankilam | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | PSYDO YOUTH DEV'T. PROGRAM - TEEN TAMBAYAN PROJECT | [7 empty] | Duration: | 69 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Tagum City | Mankilam | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | PSYDO YOUTH DEV'T. PROGRAM - TEEN TAMBAYAN PROJECT | [7 empty] | Date Allotment Released: |  | Date completed: | 2020-12-22
Tagum City | Mankilam | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | PSYDO YOUTH DEV'T. PROGRAM - TEEN TAMBAYAN PROJECT | [7 empty] | Date Started: | 2020-10-14
Talaingod | Palma Gil | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | PEACE AND ORDER PROGRAM | Proposed Road Opening of Nasilaban - Pongpong Road Section, Talaingod |  | SB # 1 CY 2020 | Road |  | km |  | Project Cost: | 5500000 | Target Completion Date: |  | Program: | 5500000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | PO #2020062105 - M3C CONSTRUCTION & SUPPLY; PO #2020061966 - FL2 LUMBER & CONSTRUCTION SUPPLY; PO #2020062217 - Alpebel Builders and Supply Corporation, PO #DIOCESAN PRINTING PRESS | PO #2020062105 - M3C CONSTRUCTION & SUPPLY; PO #2020061966 - FL2 LUMBER & CONSTRUCTION SUPPLY; PO #2020062217 - Alpebel Builders and Supply Corporation, PO #DIOCESAN PRINTING PRESS | PO #2020062105 - M3C CONSTRUCTION & SUPPLY; PO #2020061966 - FL2 LUMBER & CONSTRUCTION SUPPLY; PO #2020062217 - Alpebel Builders and Supply Corporation, PO #DIOCESAN PRINTING PRESS | PO #2020062105 - M3C CONSTRUCTION & SUPPLY; PO #2020061966 - FL2 LUMBER & CONSTRUCTION SUPPLY; PO #2020062217 - Alpebel Builders and Supply Corporation, PO #DIOCESAN PRINTING PRESS | PO #2020062105 - M3C CONSTRUCTION & SUPPLY; PO #2020061966 - FL2 LUMBER & CONSTRUCTION SUPPLY; PO #2020062217 - Alpebel Builders and Supply Corporation, PO #DIOCESAN PRINTING PRESS | Procurement on process
Talaingod | Palma Gil | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | PEACE AND ORDER PROGRAM | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 5500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
Talaingod | Palma Gil | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | PEACE AND ORDER PROGRAM | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
Talaingod | Palma Gil | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | PEACE AND ORDER PROGRAM | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Talaingod | Palma Gil | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | PEACE AND ORDER PROGRAM | [7 empty] | Date Allotment Released: |  | Date completed:
Talaingod | Palma Gil | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | PEACE AND ORDER PROGRAM | [7 empty] | Date Started:
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | VARIOUS GOV'T. BLDG. & FAC. DEV'T. PROJECT | Establishment of Multiplier Farm Phase 2, Brgy. Sto. Niño, Talaingod |  | SB # 1 CY 2020 | Building |  | sq.m |  | Project Cost: | 380000 | Target Completion Date: |  | Program: | 380000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | For bidding on June 30, 2020; Re-bid July 28, 2020. | For bidding on June 30, 2020; Re-bid July 28, 2020. | For bidding on June 30, 2020; Re-bid July 28, 2020. | For bidding on June 30, 2020; Re-bid July 28, 2020. | For bidding on June 30, 2020; Re-bid July 28, 2020. | Procurement on process
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | VARIOUS GOV'T. BLDG. & FAC. DEV'T. PROJECT | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 380000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | VARIOUS GOV'T. BLDG. & FAC. DEV'T. PROJECT | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | VARIOUS GOV'T. BLDG. & FAC. DEV'T. PROJECT | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | VARIOUS GOV'T. BLDG. & FAC. DEV'T. PROJECT | [7 empty] | Date Allotment Released: |  | Date completed:
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | VARIOUS GOV'T. BLDG. & FAC. DEV'T. PROJECT | [7 empty] | Date Started:
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | VARIOUS GOV'T. BLDG. & FAC. DEV'T. PROJECT | Establishment of Multiplier Farm (Poultry House), Phase 2, Brgy. Sto. Niño, Talaingod |  | SB # 1 CY 2020 | Building |  | sq.m |  | Project Cost: | 110000 | Target Completion Date: |  | Program: | 110000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | For bidding on June 30, 2020; Re-bid July 28, 2020. | For bidding on June 30, 2020; Re-bid July 28, 2020. | For bidding on June 30, 2020; Re-bid July 28, 2020. | For bidding on June 30, 2020; Re-bid July 28, 2020. | For bidding on June 30, 2020; Re-bid July 28, 2020. | Procurement on process
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | VARIOUS GOV'T. BLDG. & FAC. DEV'T. PROJECT | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 110000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | VARIOUS GOV'T. BLDG. & FAC. DEV'T. PROJECT | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | VARIOUS GOV'T. BLDG. & FAC. DEV'T. PROJECT | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | VARIOUS GOV'T. BLDG. & FAC. DEV'T. PROJECT | [7 empty] | Date Allotment Released: |  | Date completed:
Talaingod | Sto. Niño | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | . | VARIOUS GOV'T. BLDG. & FAC. DEV'T. PROJECT | [7 empty] | Date Started:
Talaingod | Sto. Niño | 1st Eng'g. Dist. | Completed | 2020-10-01 | 2020-11-16 | 2020 | Contract | . | VARIOUS GOV'T. BLDG. & FAC. DEV'T. PROJECT | Poultry House and Training Center Phase 2, Talaingod |  | SB # 1 CY 2020 | Building |  | sq.m |  | Project Cost: | 500000 | Target Completion Date: | 2020-11-16 23:59 | Program: | 500000 | Planned: |  | Planned: |  | Planned: |  | Planned: | 100% | Planned: | 100% | No. of Persons: |  | For bidding on June 30, 2020; Re-bid July 28, 2020. | For bidding on June 30, 2020; Re-bid July 28, 2020. | For bidding on June 30, 2020; Re-bid July 28, 2020. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per Program of Works
Talaingod | Sto. Niño | 1st Eng'g. Dist. | Completed | 2020-10-01 | 2020-11-16 | 2020 | Contract | . | VARIOUS GOV'T. BLDG. & FAC. DEV'T. PROJECT | [7 empty] | Project Engineer: | Dadula | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
Talaingod | Sto. Niño | 1st Eng'g. Dist. | Completed | 2020-10-01 | 2020-11-16 | 2020 | Contract | . | VARIOUS GOV'T. BLDG. & FAC. DEV'T. PROJECT | [7 empty] | Implementor: | JJR Const. & Supply | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: | 100% | Actual: | 100%
Talaingod | Sto. Niño | 1st Eng'g. Dist. | Completed | 2020-10-01 | 2020-11-16 | 2020 | Contract | . | VARIOUS GOV'T. BLDG. & FAC. DEV'T. PROJECT | [7 empty] | Duration: | 47 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Talaingod | Sto. Niño | 1st Eng'g. Dist. | Completed | 2020-10-01 | 2020-11-16 | 2020 | Contract | . | VARIOUS GOV'T. BLDG. & FAC. DEV'T. PROJECT | [7 empty] | Date Allotment Released: |  | Date completed: | 2020-11-16 23:59
Talaingod | Sto. Niño | 1st Eng'g. Dist. | Completed | 2020-10-01 | 2020-11-16 | 2020 | Contract | . | VARIOUS GOV'T. BLDG. & FAC. DEV'T. PROJECT | [7 empty] | Date Started: | 2020-10-01
Asuncion | Concepcion | 1st Eng'g. Dist. | Completed | 2020-01-27 | 2020-02-05 | 2019 | Contract | I. PROJECTS UNDER THE CURRENT APPROPRIATION | STIMULUS 2019 | Rural Electrification Project, Purok 6, Concepcion, Asuncion |  | SB No. 1 CY 2020(STIMULUS) | Electrification |  |  |  | Project Cost: | 500000 | Target Completion Date: | 2020-02-05 23:59 | Program: | 500000 | Planned: | 100% | Planned: | 100% | Planned: | 100% | Planned: |  | Planned: | 100% | No. of Persons: |  | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Php 500,000 - Declared savings to fund new project Construction of Children Playground with amenities at Poblacion, New Corella (SB # 4 CY 2019)- Php500,000 To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1 | Php 500,000 - Declared savings to fund new project Construction of Children Playground with amenities at Poblacion, New Corella (SB # 4 CY 2019)- Php500,000 To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1 | Completed as per Program of Works
Asuncion | Concepcion | 1st Eng'g. Dist. | Completed | 2020-01-27 | 2020-02-05 | 2019 | Contract | I. PROJECTS UNDER THE CURRENT APPROPRIATION | STIMULUS 2019 | [7 empty] | Project Engineer: | Bueno | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
Asuncion | Concepcion | 1st Eng'g. Dist. | Completed | 2020-01-27 | 2020-02-05 | 2019 | Contract | I. PROJECTS UNDER THE CURRENT APPROPRIATION | STIMULUS 2019 | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: | 100% | Actual: | 100% | Actual: | 100% | Actual: |  | Actual: | 100%
Asuncion | Concepcion | 1st Eng'g. Dist. | Completed | 2020-01-27 | 2020-02-05 | 2019 | Contract | I. PROJECTS UNDER THE CURRENT APPROPRIATION | STIMULUS 2019 | [7 empty] | Duration: | 10 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Asuncion | Concepcion | 1st Eng'g. Dist. | Completed | 2020-01-27 | 2020-02-05 | 2019 | Contract | I. PROJECTS UNDER THE CURRENT APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Allotment Released: |  | Date completed: | 2020-02-05
Asuncion | Concepcion | 1st Eng'g. Dist. | Completed | 2020-01-27 | 2020-02-05 | 2019 | Contract | I. PROJECTS UNDER THE CURRENT APPROPRIATION | STIMULUS 2019 | [7 empty] | Date Started: | 2020-01-27
Carmen | Ising | 2nd Eng'g. Dist. | Completed | 2020-03-30 | 2020-04-27 | 2020 | Administration | . | BAYANIHAN | Installaton of 15 units pre-fabricated isolation room w/ completed amenities & accessories, ddn hospital - carmen zone |  | SB # 2 CY 2020 (BAYANIHAN GRANT) | Building |  |  | Admin | Project Cost: | 8314856 | Target Completion Date: | 2020-04-27 | Program: | 8314856 | Planned: | 100% | Planned: | 100% | Planned: | 100% | Planned: | 100% | Planned: | 100% | No. of Persons: |  | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per Program of Works
Carmen | Ising | 2nd Eng'g. Dist. | Completed | 2020-03-30 | 2020-04-27 | 2020 | Administration | . | BAYANIHAN | [7 empty] | Project Engineer: | Azotes | Revised Completion Date: | 2020-04-27 | Allotment: | 8314856 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
Carmen | Ising | 2nd Eng'g. Dist. | Completed | 2020-03-30 | 2020-04-27 | 2020 | Administration | . | BAYANIHAN | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: | 8314856 | Actual: | 100% | Actual: | 100% | Actual: | 100% | Actual: | 100% | Actual: | 100%
Carmen | Ising | 2nd Eng'g. Dist. | Completed | 2020-03-30 | 2020-04-27 | 2020 | Administration | . | BAYANIHAN | [7 empty] | Duration: | 28 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Carmen | Ising | 2nd Eng'g. Dist. | Completed | 2020-03-30 | 2020-04-27 | 2020 | Administration | . | BAYANIHAN | [7 empty] | Date Allotment Released: | CY 2020 | Date completed: | 2020-04-27
Carmen | Ising | 2nd Eng'g. Dist. | Completed | 2020-03-30 | 2020-04-27 | 2020 | Administration | . | BAYANIHAN | [7 empty] | Date Started: | 2020-03-30
Carmen | Ising | 2nd Eng'g. Dist. | Completed | 2020-05-11 | 2020-07-20 | 2020 | Administration | . | BAYANIHAN | Rehab of DavNor Pharmacy into Isolation Room Phase I |  | SB # 2 CY 2020 (BAYANIHAN GRANT) | Building |  | sq.m | Admin | Project Cost: | 1480000 | Target Completion Date: | 2020-07-20 | Program: | 1480000 | Planned: | 100% | Planned: | 100% | Planned: | 100% | Planned: | 100% | Planned: | 100% | No. of Persons: | 10 | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per Program of Works
Carmen | Ising | 2nd Eng'g. Dist. | Completed | 2020-05-11 | 2020-07-20 | 2020 | Administration | . | BAYANIHAN | [7 empty] | Project Engineer: | Andoy | Revised Completion Date: |  | Allotment: | 1480000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 260
Carmen | Ising | 2nd Eng'g. Dist. | Completed | 2020-05-11 | 2020-07-20 | 2020 | Administration | . | BAYANIHAN | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: | 1137930.67 | Actual: | 100% | Actual: | 100% | Actual: | 100% | Actual: | 100% | Actual: | 100%
Carmen | Ising | 2nd Eng'g. Dist. | Completed | 2020-05-11 | 2020-07-20 | 2020 | Administration | . | BAYANIHAN | [7 empty] | Duration: | 83 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Carmen | Ising | 2nd Eng'g. Dist. | Completed | 2020-05-11 | 2020-07-20 | 2020 | Administration | . | BAYANIHAN | [7 empty] | Date Allotment Released: |  | Date completed: | 2020-07-20
Carmen | Ising | 2nd Eng'g. Dist. | Completed | 2020-05-11 | 2020-07-20 | 2020 | Administration | . | BAYANIHAN | [7 empty] | Date Started: | 2020-04-28
Carmen | Ising | 2nd Eng'g. Dist. | Completed | 2020-05-11 | 2020-08-15 | 2020 | Administration | . | BAYANIHAN | Rehab of DavNor Pharmacy into Isolation Room Phase II |  | SB # 2 CY 2020 (BAYANIHAN GRANT) | Building |  | sq.m | Admin | Project Cost: | 1000000 | Target Completion Date: | 2020-07-24 | Program: | 1000000 | Planned: | 97% | Planned: | 100% | Planned: | 100% | Planned: | 100% | Planned: | 100% | No. of Persons: | 6 | On-going | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per Program of Works
Carmen | Ising | 2nd Eng'g. Dist. | Completed | 2020-05-11 | 2020-08-15 | 2020 | Administration | . | BAYANIHAN | [7 empty] | Project Engineer: | Andoy | Revised Completion Date: | 2020-08-15 | Allotment: | 1000000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 132
Carmen | Ising | 2nd Eng'g. Dist. | Completed | 2020-05-11 | 2020-08-15 | 2020 | Administration | . | BAYANIHAN | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: | 664107.16 | Actual: | 97% | Actual: | 100% | Actual: | 100% | Actual: | 100% | Actual: | 100%
Carmen | Ising | 2nd Eng'g. Dist. | Completed | 2020-05-11 | 2020-08-15 | 2020 | Administration | . | BAYANIHAN | [7 empty] | Duration: | 74 | No. of days extended: | 22 |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Carmen | Ising | 2nd Eng'g. Dist. | Completed | 2020-05-11 | 2020-08-15 | 2020 | Administration | . | BAYANIHAN | [7 empty] | Date Allotment Released: |  | Date completed: | 2020-08-15
Carmen | Ising | 2nd Eng'g. Dist. | Completed | 2020-05-11 | 2020-08-15 | 2020 | Administration | . | BAYANIHAN | [7 empty] | Date Started: | 2020-05-11
Kapalong | Maniki | 1st Eng'g. Dist. | Completed | 2020-05-11 | 2020-09-30 | 2020 | Administration | . | BAYANIHAN GRANT TO PROVINCES | Improvement of Hospital facilities (Isolation/ICU), Kapalong Dist. Hospital |  | SB # 2 CY 2020 (BAYANIHAN GRANT) | Isolation |  | sq.m | Admin | Project Cost: | 6000000 | Target Completion Date: | 2021-01-10 23:59 | Program: | 6000000 | Planned: | 60.08% | Planned: | 60.08% | Planned: | 60.08% | Planned: | 100% | Planned: | 100% | No. of Persons: | 34 | On-going | On-going | On-going | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per Program of Works
Kapalong | Maniki | 1st Eng'g. Dist. | Completed | 2020-05-11 | 2020-09-30 | 2020 | Administration | . | BAYANIHAN GRANT TO PROVINCES | [7 empty] | Project Engineer: | Pasiona/Aclaracion | Revised Completion Date: |  | Allotment: | 6000000 | Revised: |  | Revised: | 30.27% | Revised: | 30.27% | Revised: | 100% | Revised: | 100% | No. of Man-days: | 1054
Kapalong | Maniki | 1st Eng'g. Dist. | Completed | 2020-05-11 | 2020-09-30 | 2020 | Administration | . | BAYANIHAN GRANT TO PROVINCES | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: | 60.08% | Actual: | 85.92% | Actual: | 85.92% | Actual: | 100% | Actual: | 100%
Kapalong | Maniki | 1st Eng'g. Dist. | Completed | 2020-05-11 | 2020-09-30 | 2020 | Administration | . | BAYANIHAN GRANT TO PROVINCES | [7 empty] | Duration: | 245 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 55.65% | Slippage: | 55.65% | Slippage: | 0% | Slippage: | 0%
Kapalong | Maniki | 1st Eng'g. Dist. | Completed | 2020-05-11 | 2020-09-30 | 2020 | Administration | . | BAYANIHAN GRANT TO PROVINCES | [7 empty] | Date Allotment Released: | 2020-05-07 | Date completed: | 2020-09-30
Kapalong | Maniki | 1st Eng'g. Dist. | Completed | 2020-05-11 | 2020-09-30 | 2020 | Administration | . | BAYANIHAN GRANT TO PROVINCES | [7 empty] | Date Started: | 2020-05-11
Carmen | Ising | 2nd Eng'g. Dist. | Completed | 2020-05-11 | 2020-08-14 | 2020 | Administration | . | BAYANIHAN | Impv't of Hospital Facilities (Isolation/ICU Room) Carmen District Hospital |  | SB # 2 CY 2020 (BAYANIHAN GRANT) | Building |  | sq.m | Admin | Project Cost: | 3000000 | Target Completion Date: | 2020-08-09 | Program: | 3000000 | Planned: | 90% | Planned: | 100% | Planned: | 100% | Planned: | 100% | Planned: | 100% | No. of Persons: | 8 | On-going | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per Program of Works
Carmen | Ising | 2nd Eng'g. Dist. | Completed | 2020-05-11 | 2020-08-14 | 2020 | Administration | . | BAYANIHAN | [7 empty] | Project Engineer: | Estorco | Revised Completion Date: |  | Allotment: | 3000000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 240
Carmen | Ising | 2nd Eng'g. Dist. | Completed | 2020-05-11 | 2020-08-14 | 2020 | Administration | . | BAYANIHAN | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: | 90% | Actual: | 100% | Actual: | 100% | Actual: | 100% | Actual: | 100%
Carmen | Ising | 2nd Eng'g. Dist. | Completed | 2020-05-11 | 2020-08-14 | 2020 | Administration | . | BAYANIHAN | [7 empty] | Duration: | 90 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Carmen | Ising | 2nd Eng'g. Dist. | Completed | 2020-05-11 | 2020-08-14 | 2020 | Administration | . | BAYANIHAN | [7 empty] | Date Allotment Released: |  | Date completed: | 2020-08-14
Carmen | Ising | 2nd Eng'g. Dist. | Completed | 2020-05-11 | 2020-08-14 | 2020 | Administration | . | BAYANIHAN | [7 empty] | Date Started: | 2020-05-11
Samal | Peñaplata | 2nd Eng'g. Dist. | Completed | 2020-05-11 | 2020-07-12 | 2020 | Administration | . | BAYANIHAN | Impv't of Hospital Facilities (Isolation/ICU Room) Samal District Hospital |  | SB # 2 CY 2020 (BAYANIHAN GRANT) | Building |  | sq.m | Admin | Project Cost: | 1000000 | Target Completion Date: | 2020-08-09 | Program: | 1000000 | Planned: | 100% | Planned: | 100% | Planned: | 100% | Planned: | 100% | Planned: | 100% | No. of Persons: | 6 | Completed as per physical accomplishment. Financial documents still on process. |  |  | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per Program of Works
Samal | Peñaplata | 2nd Eng'g. Dist. | Completed | 2020-05-11 | 2020-07-12 | 2020 | Administration | . | BAYANIHAN | [7 empty] | Project Engineer: | Porras/Obar | Revised Completion Date: |  | Allotment: | 1000000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 60
Samal | Peñaplata | 2nd Eng'g. Dist. | Completed | 2020-05-11 | 2020-07-12 | 2020 | Administration | . | BAYANIHAN | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: | 100% | Actual: | 100% | Actual: | 100% | Actual: | 100% | Actual: | 100%
Samal | Peñaplata | 2nd Eng'g. Dist. | Completed | 2020-05-11 | 2020-07-12 | 2020 | Administration | . | BAYANIHAN | [7 empty] | Duration: | 90 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Samal | Peñaplata | 2nd Eng'g. Dist. | Completed | 2020-05-11 | 2020-07-12 | 2020 | Administration | . | BAYANIHAN | [7 empty] | Date Allotment Released: |  | Date completed: | 2020-07-12
Samal | Peñaplata | 2nd Eng'g. Dist. | Completed | 2020-05-11 | 2020-07-12 | 2020 | Administration | . | BAYANIHAN | [7 empty] | Date Started: | 2020-05-11
Kapalong | Mabantao-Florida | 1st Eng'g. Dist. |  |  |  | 2020 |  | . | PEACE AND ORDER PROGRAM | Proposed of 1 Barrel Culvert Along Kapalong-Mabantao-Florida Provincial Road |  | SB # 4 CY 2020 | Building |  | sq.m | Admin | Project Cost: | 1900000 | Target Completion Date: | 0 | Program: | 1900000 | Planned: | 100% | Planned: | 100% | Planned: | 100% | Planned: |  | Planned: |  | No. of Persons: |  | Completed as per physical accomplishment. Financial documents still on process. |  |  |  |  | For preparation of Plan
Kapalong | Mabantao-Florida | 1st Eng'g. Dist. |  |  |  | 2020 |  | . | PEACE AND ORDER PROGRAM | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 1900000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
Kapalong | Mabantao-Florida | 1st Eng'g. Dist. |  |  |  | 2020 |  | . | PEACE AND ORDER PROGRAM | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: | 100% | Actual: | 100% | Actual: | 100% | Actual: |  | Actual:
Kapalong | Mabantao-Florida | 1st Eng'g. Dist. |  |  |  | 2020 |  | . | PEACE AND ORDER PROGRAM | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Kapalong | Mabantao-Florida | 1st Eng'g. Dist. |  |  |  | 2020 |  | . | PEACE AND ORDER PROGRAM | [7 empty] | Date Allotment Released: |  | Date completed:
Kapalong | Mabantao-Florida | 1st Eng'g. Dist. |  |  |  | 2020 |  | . | PEACE AND ORDER PROGRAM | [7 empty] | Date Started:
San Isidro | Mabantao-Florida | 1st Eng'g. Dist. |  |  |  | 2020 |  | . | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT | Const. of Igangon ES Integrated School (PREFAB), San Isidro |  | SB # 4 CY 2020 | Building |  | sq.m | Admin | Project Cost: | 500000 | Target Completion Date: | 0 | Program: | 500000 | Planned: | 100% | Planned: | 100% | Planned: | 100% | Planned: |  | Planned: |  | No. of Persons: |  | Completed as per physical accomplishment. Financial documents still on process. |  |  |  |  | For preparation of Plan
San Isidro | Mabantao-Florida | 1st Eng'g. Dist. |  |  |  | 2020 |  | . | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
San Isidro | Mabantao-Florida | 1st Eng'g. Dist. |  |  |  | 2020 |  | . | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: | 100% | Actual: | 100% | Actual: | 100% | Actual: |  | Actual:
San Isidro | Mabantao-Florida | 1st Eng'g. Dist. |  |  |  | 2020 |  | . | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
San Isidro | Mabantao-Florida | 1st Eng'g. Dist. |  |  |  | 2020 |  | . | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT | [7 empty] | Date Allotment Released: |  | Date completed:
San Isidro | Mabantao-Florida | 1st Eng'g. Dist. |  |  |  | 2020 |  | . | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT | [7 empty] | Date Started:
Samal | Samal Dist. | 2nd Eng'g. Dist. |  |  |  | 2020 |  | . | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT | Inst. Of Automatic Fire Sprinkler, Smoke Detection & Fire Alarm System, Old Main Hospitals Bldg, Samal Dist. Hospital |  | SB # 4 CY 2020 | Building |  | sq.m | Admin | Project Cost: | 3000000 | Target Completion Date: | 0 | Program: | 3000000 | Planned: | 100% | Planned: | 100% | Planned: | 100% | Planned: |  | Planned: |  | No. of Persons: |  | Completed as per physical accomplishment. Financial documents still on process. |  |  |  |  | For preparation of Plan
Samal | Samal Dist. | 2nd Eng'g. Dist. |  |  |  | 2020 |  | . | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 3000000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
Samal | Samal Dist. | 2nd Eng'g. Dist. |  |  |  | 2020 |  | . | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: | 100% | Actual: | 100% | Actual: | 100% | Actual: |  | Actual:
Samal | Samal Dist. | 2nd Eng'g. Dist. |  |  |  | 2020 |  | . | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Samal | Samal Dist. | 2nd Eng'g. Dist. |  |  |  | 2020 |  | . | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT | [7 empty] | Date Allotment Released: |  | Date completed:
Samal | Samal Dist. | 2nd Eng'g. Dist. |  |  |  | 2020 |  | . | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT | [7 empty] | Date Started:
New Corella | Poblacion | 1st Eng'g. Dist. |  |  |  | 2020 |  | . | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT | Const. of 2-Storey Rural Health Unit Bldg, w/safe Birthing Facility, New Corella |  | SB # 4 CY 2020 | Building |  | sq.m | Admin | Project Cost: | 10000000 | Target Completion Date: | 0 | Program: | 10000000 | Planned: | 100% | Planned: | 100% | Planned: | 100% | Planned: |  | Planned: |  | No. of Persons: |  | Completed as per physical accomplishment. Financial documents still on process. |  |  |  |  | For preparation of Plan
New Corella | Poblacion | 1st Eng'g. Dist. |  |  |  | 2020 |  | . | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 10000000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
New Corella | Poblacion | 1st Eng'g. Dist. |  |  |  | 2020 |  | . | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: | 100% | Actual: | 100% | Actual: | 100% | Actual: |  | Actual:
New Corella | Poblacion | 1st Eng'g. Dist. |  |  |  | 2020 |  | . | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
New Corella | Poblacion | 1st Eng'g. Dist. |  |  |  | 2020 |  | . | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT | [7 empty] | Date Allotment Released: |  | Date completed:
New Corella | Poblacion | 1st Eng'g. Dist. |  |  |  | 2020 |  | . | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT | [7 empty] | Date Started:
Asuncion |  | 1st Eng'g. Dist. |  |  |  | 2020 |  | . | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT | Const. of 2-Storey Rural Health Unit Bldg, w/safe Birthing Facility, Asuncion |  | SB # 4 CY 2020 | Building |  | sq.m | Admin | Project Cost: | 10000000 | Target Completion Date: | 0 | Program: | 10000000 | Planned: | 100% | Planned: | 100% | Planned: | 100% | Planned: |  | Planned: |  | No. of Persons: |  | Completed as per physical accomplishment. Financial documents still on process. |  |  |  |  | For preparation of Plan
Asuncion |  | 1st Eng'g. Dist. |  |  |  | 2020 |  | . | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 10000000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
Asuncion |  | 1st Eng'g. Dist. |  |  |  | 2020 |  | . | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: | 100% | Actual: | 100% | Actual: | 100% | Actual: |  | Actual:
Asuncion |  | 1st Eng'g. Dist. |  |  |  | 2020 |  | . | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Asuncion |  | 1st Eng'g. Dist. |  |  |  | 2020 |  | . | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT | [7 empty] | Date Allotment Released: |  | Date completed:
Asuncion |  | 1st Eng'g. Dist. |  |  |  | 2020 |  | . | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT | [7 empty] | Date Started:
Talaingod |  | 1st Eng'g. Dist. |  |  |  | 2020 |  | . | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT | Const. of 2-Storey Rural Health Unit Bldg, w/safe Birthing Facility, Talaingod |  | SB # 4 CY 2020 | Building |  | sq.m | Admin | Project Cost: | 10000000 | Target Completion Date: | 0 | Program: | 10000000 | Planned: | 100% | Planned: | 100% | Planned: | 100% | Planned: |  | Planned: |  | No. of Persons: |  | Completed as per physical accomplishment. Financial documents still on process. |  |  |  |  | For preparation of Plan
Talaingod |  | 1st Eng'g. Dist. |  |  |  | 2020 |  | . | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 10000000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
Talaingod |  | 1st Eng'g. Dist. |  |  |  | 2020 |  | . | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: | 100% | Actual: | 100% | Actual: | 100% | Actual: |  | Actual:
Talaingod |  | 1st Eng'g. Dist. |  |  |  | 2020 |  | . | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Talaingod |  | 1st Eng'g. Dist. |  |  |  | 2020 |  | . | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT | [7 empty] | Date Allotment Released: |  | Date completed:
Talaingod |  | 1st Eng'g. Dist. |  |  |  | 2020 |  | . | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT | [7 empty] | Date Started:
Sto. Tomas |  | 2nd Eng'g. Dist. |  |  |  | 2020 |  | . | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT | Const. of 2-Storey Rural Health Unit Bldg, w/safe Birthing Facility, Sto. Tomas |  | SB # 4 CY 2020 | Building |  | sq.m | Admin | Project Cost: | 10000000 | Target Completion Date: | 0 | Program: | 10000000 | Planned: | 100% | Planned: | 100% | Planned: | 100% | Planned: |  | Planned: |  | No. of Persons: |  | Completed as per physical accomplishment. Financial documents still on process. |  |  |  |  | For preparation of Plan
Sto. Tomas |  | 2nd Eng'g. Dist. |  |  |  | 2020 |  | . | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 10000000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
Sto. Tomas |  | 2nd Eng'g. Dist. |  |  |  | 2020 |  | . | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: | 100% | Actual: | 100% | Actual: | 100% | Actual: |  | Actual:
Sto. Tomas |  | 2nd Eng'g. Dist. |  |  |  | 2020 |  | . | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Sto. Tomas |  | 2nd Eng'g. Dist. |  |  |  | 2020 |  | . | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT | [7 empty] | Date Allotment Released: |  | Date completed:
Sto. Tomas |  | 2nd Eng'g. Dist. |  |  |  | 2020 |  | . | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT | [7 empty] | Date Started:
Panabo City |  | 2nd Eng'g. Dist. |  |  |  | 2020 |  | . | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT | Const. of Infirmary Hospital, Panabo City |  | SB # 4 CY 2020 | Building |  | sq.m | Admin | Project Cost: | 15000000 | Target Completion Date: | 0 | Program: | 15000000 | Planned: | 100% | Planned: | 100% | Planned: | 100% | Planned: |  | Planned: |  | No. of Persons: |  | Completed as per physical accomplishment. Financial documents still on process. |  |  |  |  | For preparation of Plan
Panabo City |  | 2nd Eng'g. Dist. |  |  |  | 2020 |  | . | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 15000000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
Panabo City |  | 2nd Eng'g. Dist. |  |  |  | 2020 |  | . | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: | 100% | Actual: | 100% | Actual: | 100% | Actual: |  | Actual:
Panabo City |  | 2nd Eng'g. Dist. |  |  |  | 2020 |  | . | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Panabo City |  | 2nd Eng'g. Dist. |  |  |  | 2020 |  | . | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT | [7 empty] | Date Allotment Released: |  | Date completed:
Panabo City |  | 2nd Eng'g. Dist. |  |  |  | 2020 |  | . | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT | [7 empty] | Date Started:
Kapalong |  | 1st Eng'g. Dist. |  |  |  | 2020 |  | . | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT | Const. of Dialysis Center with Equipments - Kapalong Hospital |  | SB # 4 CY 2020 | Building |  | sq.m | Admin | Project Cost: | 30000000 | Target Completion Date: | 0 | Program: | 30000000 | Planned: | 100% | Planned: | 100% | Planned: | 100% | Planned: |  | Planned: |  | No. of Persons: |  | Completed as per physical accomplishment. Financial documents still on process. |  |  |  |  | For preparation of Plan
Kapalong |  | 1st Eng'g. Dist. |  |  |  | 2020 |  | . | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 30000000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
Kapalong |  | 1st Eng'g. Dist. |  |  |  | 2020 |  | . | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: | 100% | Actual: | 100% | Actual: | 100% | Actual: |  | Actual:
Kapalong |  | 1st Eng'g. Dist. |  |  |  | 2020 |  | . | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Kapalong |  | 1st Eng'g. Dist. |  |  |  | 2020 |  | . | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT | [7 empty] | Date Allotment Released: |  | Date completed:
Kapalong |  | 1st Eng'g. Dist. |  |  |  | 2020 |  | . | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT | [7 empty] | Date Started:
Samal |  | 2nd Eng'g. Dist. |  |  |  | 2020 |  | . | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT | Const. of Dialysis Center with Equipments - Samal Hospital |  | SB # 4 CY 2020 | Building |  | sq.m | Admin | Project Cost: | 30000000 | Target Completion Date: | 0 | Program: | 30000000 | Planned: | 100% | Planned: | 100% | Planned: | 100% | Planned: |  | Planned: |  | No. of Persons: |  | Completed as per physical accomplishment. Financial documents still on process. |  |  |  |  | For preparation of Plan
Samal |  | 2nd Eng'g. Dist. |  |  |  | 2020 |  | . | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 30000000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
Samal |  | 2nd Eng'g. Dist. |  |  |  | 2020 |  | . | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: | 100% | Actual: | 100% | Actual: | 100% | Actual: |  | Actual:
Samal |  | 2nd Eng'g. Dist. |  |  |  | 2020 |  | . | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Samal |  | 2nd Eng'g. Dist. |  |  |  | 2020 |  | . | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT | [7 empty] | Date Allotment Released: |  | Date completed:
Samal |  | 2nd Eng'g. Dist. |  |  |  | 2020 |  | . | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT | [7 empty] | Date Started:
Sto. Tomas |  | 2nd Eng'g. Dist. |  |  |  | 2020 |  | . | AGRI-AQUACULTURE ENHANCEMENT PROGRAM | Impv't. of Sto. Tomas Organic Prod'n. Center with Common Service facility, Sto. Tomas |  | SB # 4 CY 2020 | Building |  | sq.m | Admin | Project Cost: | 951204.81 | Target Completion Date: | 2018-12-24 23:59 | Program: | 951204.81 | Planned: | 94.55% | Planned: | 100% | Planned: | 100% | Planned: | 100% | Planned: | 100% | No. of Persons: | 20 | Completed as per physical accomplishment. Financial documents still on process. |  |  |  |  | On-going
Sto. Tomas |  | 2nd Eng'g. Dist. |  |  |  | 2020 |  | . | AGRI-AQUACULTURE ENHANCEMENT PROGRAM | [7 empty] | Project Engineer: | Azotes | Revised Completion Date: | May 24, 2021 | Allotment: | 951204.81 | Revised: | 78.32% | Revised: | 83.43% | Revised: | 83.43% | Revised: | 83.43% | Revised: | 22.53% | No. of Man-days:
Sto. Tomas |  | 2nd Eng'g. Dist. |  |  |  | 2020 |  | . | AGRI-AQUACULTURE ENHANCEMENT PROGRAM | [7 empty] | Implementor: | Manantan | No. of days suspended: | 501 | Disbursement: |  | Actual: | 71.89% | Actual: | 75.19% | Actual: | 75.19% | Actual: | 75.19% | Actual: | 30.33%
Sto. Tomas |  | 2nd Eng'g. Dist. |  |  |  | 2020 |  | . | AGRI-AQUACULTURE ENHANCEMENT PROGRAM | [7 empty] | Duration: | 330 | No. of days extended: |  |  |  | Slippage: | -6.424% | Slippage: | -8.238% | Slippage: | -8.238% | Slippage: | -8.238% | Slippage: | 7.8%
Sto. Tomas |  | 2nd Eng'g. Dist. |  |  |  | 2020 |  | . | AGRI-AQUACULTURE ENHANCEMENT PROGRAM | [7 empty] | Date Allotment Released: | CY 2014 | Date completed:
Sto. Tomas |  | 2nd Eng'g. Dist. |  |  |  | 2020 |  | . | AGRI-AQUACULTURE ENHANCEMENT PROGRAM | [7 empty] | Date Started: | 2018-01-29
Panabo City | San Francisco | 2nd Eng'g. Dist. |  |  |  | 2020 |  | . | AGRI-AQUACULTURE ENHANCEMENT PROGRAM | Chocolate Processing, RACO, San Francisco, Panabo City |  | SB # 4 CY 2020 | Building |  | sq.m | Admin | Project Cost: | 3199294.6 | Target Completion Date: | 0 | Program: | 3199294.6 | Planned: | 100% | Planned: | 100% | Planned: | 100% | Planned: |  | Planned: |  | No. of Persons: |  | Completed as per physical accomplishment. Financial documents still on process. |  |  |  |  | Procurement on process
Panabo City | San Francisco | 2nd Eng'g. Dist. |  |  |  | 2020 |  | . | AGRI-AQUACULTURE ENHANCEMENT PROGRAM | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 3199294.6 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
Panabo City | San Francisco | 2nd Eng'g. Dist. |  |  |  | 2020 |  | . | AGRI-AQUACULTURE ENHANCEMENT PROGRAM | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: | 100% | Actual: | 100% | Actual: | 100% | Actual: |  | Actual:
Panabo City | San Francisco | 2nd Eng'g. Dist. |  |  |  | 2020 |  | . | AGRI-AQUACULTURE ENHANCEMENT PROGRAM | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Panabo City | San Francisco | 2nd Eng'g. Dist. |  |  |  | 2020 |  | . | AGRI-AQUACULTURE ENHANCEMENT PROGRAM | [7 empty] | Date Allotment Released: |  | Date completed:
Panabo City | San Francisco | 2nd Eng'g. Dist. |  |  |  | 2020 |  | . | AGRI-AQUACULTURE ENHANCEMENT PROGRAM | [7 empty] | Date Started:
Mankilam | Tagum City | 1st Eng'g. Dist. |  |  |  | 2020 |  | . | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT | Rep/Rehab. Of Civil Service Commission Field Office |  | SB # 4 CY 2020 | Building |  | sq.m | Admin | Project Cost: | 290000 | Target Completion Date: | 0 | Program: | 290000 | Planned: | 100% | Planned: | 100% | Planned: | 100% | Planned: |  | Planned: |  | No. of Persons: |  | Completed as per physical accomplishment. Financial documents still on process. |  |  |  |  | For preparation of Plan
Mankilam | Tagum City | 1st Eng'g. Dist. |  |  |  | 2020 |  | . | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 290000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
Mankilam | Tagum City | 1st Eng'g. Dist. |  |  |  | 2020 |  | . | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: | 100% | Actual: | 100% | Actual: | 100% | Actual: |  | Actual:
Mankilam | Tagum City | 1st Eng'g. Dist. |  |  |  | 2020 |  | . | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Mankilam | Tagum City | 1st Eng'g. Dist. |  |  |  | 2020 |  | . | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT | [7 empty] | Date Allotment Released: |  | Date completed:
Mankilam | Tagum City | 1st Eng'g. Dist. |  |  |  | 2020 |  | . | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT | [7 empty] | Date Started:
Kapalong | Gupitan-Palma Gil | 1st Eng'g. Dist. |  |  |  | 2020 |  | . | RURAL ELECTRIFICATION | Const. and Inst. Of One (1) unit Community-Based Micro Hydropower System and 1,308 units Solar Photovoltaic Homelihtning System in Gupitan, Kapalong & Palma Gil, Talaingod (Improving the Lives of People in Off-Grid Communities in mindanao through the Provinsion of Sustainable Energy) |  | SB # 4 CY 2020 | Building |  | sq.m | Admin | Project Cost: | 2707680 | Target Completion Date: | 0 | Program: | 2707680 | Planned: | 100% | Planned: | 100% | Planned: | 100% | Planned: |  | Planned: |  | No. of Persons: |  | Completed as per physical accomplishment. Financial documents still on process. |  |  |  |  | For preparation of Plan
Kapalong | Gupitan-Palma Gil | 1st Eng'g. Dist. |  |  |  | 2020 |  | . | RURAL ELECTRIFICATION | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 2707680 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
Kapalong | Gupitan-Palma Gil | 1st Eng'g. Dist. |  |  |  | 2020 |  | . | RURAL ELECTRIFICATION | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: | 100% | Actual: | 100% | Actual: | 100% | Actual: |  | Actual:
Kapalong | Gupitan-Palma Gil | 1st Eng'g. Dist. |  |  |  | 2020 |  | . | RURAL ELECTRIFICATION | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Kapalong | Gupitan-Palma Gil | 1st Eng'g. Dist. |  |  |  | 2020 |  | . | RURAL ELECTRIFICATION | [7 empty] | Date Allotment Released: |  | Date completed:
Kapalong | Gupitan-Palma Gil | 1st Eng'g. Dist. |  |  |  | 2020 |  | . | RURAL ELECTRIFICATION | [7 empty] | Date Started:
Carmen |  | 2nd Eng'g. Dist. |  |  |  | 2020 |  | . | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT | Rehab. Of Manpower Dev't. Center, PEO Sub-Office Bldg., |  | SB # 4 CY 2020 | Building |  | sq.m | Admin | Project Cost: | 1590000 | Target Completion Date: | 0 | Program: | 1590000 | Planned: | 100% | Planned: | 100% | Planned: | 100% | Planned: |  | Planned: |  | No. of Persons: |  | Completed as per physical accomplishment. Financial documents still on process. |  |  |  |  | For preparation of Plan
Carmen |  | 2nd Eng'g. Dist. |  |  |  | 2020 |  | . | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 1590000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
Carmen |  | 2nd Eng'g. Dist. |  |  |  | 2020 |  | . | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: | 100% | Actual: | 100% | Actual: | 100% | Actual: |  | Actual:
Carmen |  | 2nd Eng'g. Dist. |  |  |  | 2020 |  | . | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Carmen |  | 2nd Eng'g. Dist. |  |  |  | 2020 |  | . | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT | [7 empty] | Date Allotment Released: |  | Date completed:
Carmen |  | 2nd Eng'g. Dist. |  |  |  | 2020 |  | . | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT | [7 empty] | Date Started:
Talaingod | Sto. Niño | 1st Eng'g. Dist. |  |  |  | 2020 |  | . | STIMULUS PROJECTS | Const. of retaining Wall, Brgy. Sto. Niño, Talaingod |  | SB # 4 CY 2020 | Building |  | sq.m | Admin | Project Cost: | 500000 | Target Completion Date: | 0 | Program: | 500000 | Planned: | 100% | Planned: | 100% | Planned: | 100% | Planned: |  | Planned: |  | No. of Persons: |  | Completed as per physical accomplishment. Financial documents still on process. |  |  |  |  | For preparation of Plan
Talaingod | Sto. Niño | 1st Eng'g. Dist. |  |  |  | 2020 |  | . | STIMULUS PROJECTS | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
Talaingod | Sto. Niño | 1st Eng'g. Dist. |  |  |  | 2020 |  | . | STIMULUS PROJECTS | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: | 100% | Actual: | 100% | Actual: | 100% | Actual: |  | Actual:
Talaingod | Sto. Niño | 1st Eng'g. Dist. |  |  |  | 2020 |  | . | STIMULUS PROJECTS | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Talaingod | Sto. Niño | 1st Eng'g. Dist. |  |  |  | 2020 |  | . | STIMULUS PROJECTS | [7 empty] | Date Allotment Released: |  | Date completed:
Talaingod | Sto. Niño | 1st Eng'g. Dist. |  |  |  | 2020 |  | . | STIMULUS PROJECTS | [7 empty] | Date Started:
Tagum City | Pagsabangan | 1st Eng'g. Dist. |  |  |  | 2020 |  | . | STIMULUS PROJECTS | Const. of Satellite market, Brgy. Pagsabangan, Tagum City |  | SB # 4 CY 2020 | Building |  | sq.m | Admin | Project Cost: | 238125 | Target Completion Date: | 0 | Program: | 238125 | Planned: | 100% | Planned: | 100% | Planned: | 100% | Planned: |  | Planned: |  | No. of Persons: |  | Completed as per physical accomplishment. Financial documents still on process. |  |  |  |  | For preparation of Plan
Tagum City | Pagsabangan | 1st Eng'g. Dist. |  |  |  | 2020 |  | . | STIMULUS PROJECTS | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 238125 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
Tagum City | Pagsabangan | 1st Eng'g. Dist. |  |  |  | 2020 |  | . | STIMULUS PROJECTS | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: | 100% | Actual: | 100% | Actual: | 100% | Actual: |  | Actual:
Tagum City | Pagsabangan | 1st Eng'g. Dist. |  |  |  | 2020 |  | . | STIMULUS PROJECTS | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Tagum City | Pagsabangan | 1st Eng'g. Dist. |  |  |  | 2020 |  | . | STIMULUS PROJECTS | [7 empty] | Date Allotment Released: |  | Date completed:
Tagum City | Pagsabangan | 1st Eng'g. Dist. |  |  |  | 2020 |  | . | STIMULUS PROJECTS | [7 empty] | Date Started:
Tagum City | Mankilam | 1st Eng'g. Dist. |  |  |  | 2020 |  | . | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT | Const. of DAVNOR Tech-Vocational Training Center |  | SB # 4 CY 2020 | Building |  | sq.m | Admin | Project Cost: | 29000000 | Target Completion Date: | 0 | Program: | 29000000 | Planned: | 100% | Planned: | 100% | Planned: | 100% | Planned: |  | Planned: |  | No. of Persons: |  | Completed as per physical accomplishment. Financial documents still on process. |  |  |  |  | For preparation of Plan
Tagum City | Mankilam | 1st Eng'g. Dist. |  |  |  | 2020 |  | . | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 29000000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
Tagum City | Mankilam | 1st Eng'g. Dist. |  |  |  | 2020 |  | . | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: | 100% | Actual: | 100% | Actual: | 100% | Actual: |  | Actual:
Tagum City | Mankilam | 1st Eng'g. Dist. |  |  |  | 2020 |  | . | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Tagum City | Mankilam | 1st Eng'g. Dist. |  |  |  | 2020 |  | . | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT | [7 empty] | Date Allotment Released: |  | Date completed:
Tagum City | Mankilam | 1st Eng'g. Dist. |  |  |  | 2020 |  | . | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT | [7 empty] | Date Started:
Tagum City |  | 1st Eng'g. Dist. |  |  |  | 2020 |  | . | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT | Const./Establishment of Integrated Solid Waste Management Facility |  | SB # 4 CY 2020 | Building |  | sq.m | Admin | Project Cost: | 50000000 | Target Completion Date: | 0 | Program: | 50000000 | Planned: | 100% | Planned: | 100% | Planned: | 100% | Planned: |  | Planned: |  | No. of Persons: |  | Completed as per physical accomplishment. Financial documents still on process. |  |  |  |  | For preparation of Plan
Tagum City |  | 1st Eng'g. Dist. |  |  |  | 2020 |  | . | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 50000000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
Tagum City |  | 1st Eng'g. Dist. |  |  |  | 2020 |  | . | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: | 100% | Actual: | 100% | Actual: | 100% | Actual: |  | Actual:
Tagum City |  | 1st Eng'g. Dist. |  |  |  | 2020 |  | . | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Tagum City |  | 1st Eng'g. Dist. |  |  |  | 2020 |  | . | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT | [7 empty] | Date Allotment Released: |  | Date completed:
Tagum City |  | 1st Eng'g. Dist. |  |  |  | 2020 |  | . | VARIOUS GOVERNMENT BUILDINGS AND FACILITIES DEVELOPMENT PROJECT | [7 empty] | Date Started:
|  | 1st Eng'g. Dist. | Completed | 2020-06-25 | 2020-08-03 | 2020 | Contract | . |  | Construction of Veterinary Quarantine |  | 20% Development CY 2020 |  |  |  | Contract | Project Cost: | 185360 | Target Completion Date: | 2020-08-03 23:59 | Program: | 185360 | [6 empty] | Planned: | 100% | Planned: | 100% | No. of Persons: |  |  |  |  | Completed as per physical accomplishment | Completed as per physical accomplishment | Completed as per Program of Works
|  | 1st Eng'g. Dist. | Completed | 2020-06-25 | 2020-08-03 | 2020 | Contract | . | [8 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 185360 | [6 empty] | Revised: |  | Revised: |  | No. of Man-days:
|  | 1st Eng'g. Dist. | Completed | 2020-06-25 | 2020-08-03 | 2020 | Contract | . | [8 empty] | Implementor: | Allbrycar Const. and Eng'g. Services | No. of days suspended: |  | Disbursement: | [7 empty] | Actual: | 100% | Actual: | 100%
|  | 1st Eng'g. Dist. | Completed | 2020-06-25 | 2020-08-03 | 2020 | Contract | . | [8 empty] | Duration: | 40 | No. of days extended: | [9 empty] | Slippage: |  | Slippage:
|  | 1st Eng'g. Dist. | Completed | 2020-06-25 | 2020-08-03 | 2020 | Contract | . | [8 empty] | Date Allotment Released: |  | Date completed: | 2020-08-03
|  | 1st Eng'g. Dist. | Completed | 2020-06-25 | 2020-08-03 | 2020 | Contract | . | [8 empty] | Date Started: | 2020-06-25
Tagum City | Mankilam | 1st Eng'g. Dist. | Completed | 2020-06-15 | 2020-07-15 | 2020 | Administration | . | SPECIAL TRUST FUND (PDRRMC) | Installation of 20 units Isolation Room, Sports Academy Dormitory, DNSTC |  | SPECIAL TRUST FUND | Isolation | 20 | sq.m | Admin | Project Cost: | 170000 | Target Completion Date: | 2020-07-29 23:59 | Program: | 170000 | Planned: | 100% | Planned: | 100% | Planned: | 100% | Planned: | 100% | Planned: | 100% | No. of Persons: |  | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per Program of Works
Tagum City | Mankilam | 1st Eng'g. Dist. | Completed | 2020-06-15 | 2020-07-15 | 2020 | Administration | . | SPECIAL TRUST FUND (PDRRMC) | [7 empty] | Project Engineer: | Chua | Revised Completion Date: | 2020-07-29 23:59 | Allotment: | 170000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
Tagum City | Mankilam | 1st Eng'g. Dist. | Completed | 2020-06-15 | 2020-07-15 | 2020 | Administration | . | SPECIAL TRUST FUND (PDRRMC) | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: | 100% | Actual: | 100% | Actual: | 100% | Actual: | 100% | Actual: | 100%
Tagum City | Mankilam | 1st Eng'g. Dist. | Completed | 2020-06-15 | 2020-07-15 | 2020 | Administration | . | SPECIAL TRUST FUND (PDRRMC) | [7 empty] | Duration: | 45 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Tagum City | Mankilam | 1st Eng'g. Dist. | Completed | 2020-06-15 | 2020-07-15 | 2020 | Administration | . | SPECIAL TRUST FUND (PDRRMC) | [7 empty] | Date Allotment Released: | 2020-06-15 | Date completed: | 2020-07-15
Tagum City | Mankilam | 1st Eng'g. Dist. | Completed | 2020-06-15 | 2020-07-15 | 2020 | Administration | . | SPECIAL TRUST FUND (PDRRMC) | [7 empty] | Date Started: | 2020-06-15
Tagum City | Mankilam | 1st Eng'g. Dist. | Completed | 2020-06-01 | 2020-07-15 | 2020 | Administration | . | SPECIAL TRUST FUND (PDRRMC) | Installation of 100 units isolation room (2.0 x 3.0m), DAVNOR GYM |  | SPECIAL TRUST FUND | Isolation | 100 | sq.m | Admin | Project Cost: | 750000 | Target Completion Date: | 2020-07-15 23:59 | Program: | 750000 | Planned: | 100% | Planned: | 100% | Planned: | 100% | Planned: | 100% | Planned: | 100% | No. of Persons: |  | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per Program of Works
Tagum City | Mankilam | 1st Eng'g. Dist. | Completed | 2020-06-01 | 2020-07-15 | 2020 | Administration | . | SPECIAL TRUST FUND (PDRRMC) | [7 empty] | Project Engineer: | Chua | Revised Completion Date: | 2020-07-15 23:59 | Allotment: | 750000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
Tagum City | Mankilam | 1st Eng'g. Dist. | Completed | 2020-06-01 | 2020-07-15 | 2020 | Administration | . | SPECIAL TRUST FUND (PDRRMC) | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: | 100% | Actual: | 100% | Actual: | 100% | Actual: | 100% | Actual: | 100%
Tagum City | Mankilam | 1st Eng'g. Dist. | Completed | 2020-06-01 | 2020-07-15 | 2020 | Administration | . | SPECIAL TRUST FUND (PDRRMC) | [7 empty] | Duration: | 45 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Tagum City | Mankilam | 1st Eng'g. Dist. | Completed | 2020-06-01 | 2020-07-15 | 2020 | Administration | . | SPECIAL TRUST FUND (PDRRMC) | [7 empty] | Date Allotment Released: | 2020-06-01 | Date completed: | 2020-07-15
Tagum City | Mankilam | 1st Eng'g. Dist. | Completed | 2020-06-01 | 2020-07-15 | 2020 | Administration | . | SPECIAL TRUST FUND (PDRRMC) | [7 empty] | Date Started: | 2020-06-01
Tagum City | Mankilam | 1st Eng'g. Dist. | Completed | 2020-06-22 | 2020-07-15 | 2020 | Administration | . | SPECIAL TRUST FUND (PDRRMC) | Installation of 40 units Isolation Room, Sports Academy Dormitory, DNSTC |  | SPECIAL TRUST FUND | Isolation | 40 | sq.m | Admin | Project Cost: | 320000 | Target Completion Date: | 2020-07-29 23:59 | Program: | 320000 | Planned: | 100% | Planned: | 100% | Planned: | 100% | Planned: | 100% | Planned: | 100% | No. of Persons: |  | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per Program of Works
Tagum City | Mankilam | 1st Eng'g. Dist. | Completed | 2020-06-22 | 2020-07-15 | 2020 | Administration | . | SPECIAL TRUST FUND (PDRRMC) | [7 empty] | Project Engineer: | Chua | Revised Completion Date: | 2020-07-29 23:59 | Allotment: | 320000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
Tagum City | Mankilam | 1st Eng'g. Dist. | Completed | 2020-06-22 | 2020-07-15 | 2020 | Administration | . | SPECIAL TRUST FUND (PDRRMC) | [7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: | 100% | Actual: | 100% | Actual: | 100% | Actual: | 100% | Actual: | 100%
Tagum City | Mankilam | 1st Eng'g. Dist. | Completed | 2020-06-22 | 2020-07-15 | 2020 | Administration | . | SPECIAL TRUST FUND (PDRRMC) | [7 empty] | Duration: | 45 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Tagum City | Mankilam | 1st Eng'g. Dist. | Completed | 2020-06-22 | 2020-07-15 | 2020 | Administration | . | SPECIAL TRUST FUND (PDRRMC) | [7 empty] | Date Allotment Released: | 2020-05-28 | Date completed: | 2020-07-15
Tagum City | Mankilam | 1st Eng'g. Dist. | Completed | 2020-06-22 | 2020-07-15 | 2020 | Administration | . | SPECIAL TRUST FUND (PDRRMC) | [7 empty] | Date Started: | 2020-06-15
Kapalong | Gabuyan | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | CMGP | Road Improvement of Jct. Highway Gabuyan – Semong – Dagohoy Provincial Road |  | CMGP CY 2020 | Road |  | km |  | Project Cost: | 63458000 | Target Completion Date: |  | Program: | 63458000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | No. of Persons: |  | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | For implementtation
Kapalong | Gabuyan | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | CMGP | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 63458000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: |  | No. of Man-days:
Kapalong | Gabuyan | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | CMGP | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
Kapalong | Gabuyan | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | CMGP | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
Kapalong | Gabuyan | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | CMGP | [7 empty] | Date Allotment Released: |  | Date completed:
Kapalong | Gabuyan | 1st Eng'g. Dist. | For Implementation |  |  | 2020 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | CMGP | [7 empty] | Date Started:
Carmen | La Paz | 2nd Eng'g. Dist. | For Implementation |  |  | 2020 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | CMGP | Road Improvement of Feeder Road 3- San Jose Provincial Road |  | CMGP CY 2020 | Road |  | km | Contract | Project Cost: | 53991806 | Target Completion Date: | 0 | Program: | 53991806 | Planned: | [7 empty] | No. of Persons: |  | No. of Persons: |  | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | For implementtation
Carmen | La Paz | 2nd Eng'g. Dist. | For Implementation |  |  | 2020 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | CMGP | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 53991806 | Revised: | [7 empty] | No. of Man-days: |  | No. of Man-days:
Carmen | La Paz | 2nd Eng'g. Dist. | For Implementation |  |  | 2020 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | CMGP | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Carmen | La Paz | 2nd Eng'g. Dist. | For Implementation |  |  | 2020 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | CMGP | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage:
Carmen | La Paz | 2nd Eng'g. Dist. | For Implementation |  |  | 2020 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | CMGP | [7 empty] | Date Allotment Released: |  | Date completed:
Carmen | La Paz | 2nd Eng'g. Dist. | For Implementation |  |  | 2020 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | CMGP | [7 empty] | Date Started:
Carmen | La Paz | 2nd Eng'g. Dist. | POW and DED on-going review (c/o RPCO) |  |  | 2020 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | PRDP | Rehabilitation of New Visayas - Tulalian, Sto. Tomas |  | PRDP CY 2020 | Road |  | km | Contract | Project Cost: | 215000000 | Target Completion Date: | 0 | Program: | 215000000 | Planned: | [7 empty] | No. of Persons: |  | No. of Persons: |  | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | POW and DED on-going review (c/o RPCO)
Carmen | La Paz | 2nd Eng'g. Dist. | POW and DED on-going review (c/o RPCO) |  |  | 2020 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | PRDP | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 215000000 | Revised: | [7 empty] | No. of Man-days: |  | No. of Man-days:
Carmen | La Paz | 2nd Eng'g. Dist. | POW and DED on-going review (c/o RPCO) |  |  | 2020 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | PRDP | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Carmen | La Paz | 2nd Eng'g. Dist. | POW and DED on-going review (c/o RPCO) |  |  | 2020 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | PRDP | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage:
Carmen | La Paz | 2nd Eng'g. Dist. | POW and DED on-going review (c/o RPCO) |  |  | 2020 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | PRDP | [7 empty] | Date Allotment Released: |  | Date completed:
Carmen | La Paz | 2nd Eng'g. Dist. | POW and DED on-going review (c/o RPCO) |  |  | 2020 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | PRDP | [7 empty] | Date Started:
Carmen | La Paz | 2nd Eng'g. Dist. | For bidding |  |  | 2020 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | PRDP-I-REAP | Const. of Chocolate Pprocessing Building, San Francisco, Panabo City (REHOBOTH) |  | PRDP - I-REAP CY 2020 | Road |  | km | Contract | Project Cost: | 6072010.87 | Target Completion Date: | 0 | Program: | 6072010.87 | Planned: | [7 empty] | No. of Persons: |  | No. of Persons: |  | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | For bidding
Carmen | La Paz | 2nd Eng'g. Dist. | For bidding |  |  | 2020 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | PRDP-I-REAP | [7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 6072010.87 | Revised: | [7 empty] | No. of Man-days: |  | No. of Man-days:
Carmen | La Paz | 2nd Eng'g. Dist. | For bidding |  |  | 2020 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | PRDP-I-REAP | [7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
Carmen | La Paz | 2nd Eng'g. Dist. | For bidding |  |  | 2020 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | PRDP-I-REAP | [7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage:
Carmen | La Paz | 2nd Eng'g. Dist. | For bidding |  |  | 2020 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | PRDP-I-REAP | [7 empty] | Date Allotment Released: |  | Date completed:
Carmen | La Paz | 2nd Eng'g. Dist. | For bidding |  |  | 2020 |  | I. PROJECTS UNDER THE CURRENT APPROPRIATION | PRDP-I-REAP | [7 empty] | Date Started:
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
….
.
.
.
.
.
.
.
…
.
..
.
.
..
.
..
.
…
.
…
.
.
.
.
..
.
.
..
.
…
..
.
.
..
….
.
…
.
…
..
.
…
.
.
.
…..
.
..
.
..
.
.
..
.
..
.
.
..
.
..
.
..
.
…
.
..
.
..
.
.
..
….
.
…
.
..
.
..
.
.
..
.
..
….
.
…
.
..
.
…
.
..
.
..
.
…
.
..
.
.
.
.
…
….
.
.
.
.
…
.
..
.
…
.
..
.
.
.
.
…
.
..
.
.
…
…
….
..
..
.
..
.
..
…
..
.
..
..
..
.
….
.
…
Note on L167: chai: Previously FMR
Note on AD605: Cerela Montes: as of sept. 15
Note on AF605: Cerela Montes: as of sept. 15
Note on T737: chai: Previously 2,000,000.00
Note on N977: Cerela Montes: Previously 20% DF CY 2019 (STIMULUS)
Note on N1325: Cerela Montes: Previously 20% DF CY 2019
Note on L1331: chai: Php2,000,000.00 - 20% DF CY 2020, Php500,000.00-TF
Note on N1367: chai: SB No. 1 CY 2019 (STIMULUS PROJECT)
Note on L1391: chai: Previously Concreting of Drainage Canal, Poblacion, New Corella
Note on N1397: previously 20% DF CY 2019
Note on N1403: previously 20% DF CY 2019
Note on N1415: chai: Previously Perimeter Fence of Day Care Center I & II, Nanyo, Panabo City (20% Development Fund CY 2018 (STIMULUS 2018)
Note on N1427: chai: Previously Perimeter Fence of Day Care Center I & II, Nanyo, Panabo City (20% Development Fund CY 2018 (STIMULUS 2018)
Note on N1433: chai: Previously Perimeter Fence of Day Care Center I & II, Nanyo, Panabo City (20% Development Fund CY 2018 (STIMULUS 2018)
Note on N1439: chai: Previously Perimeter Fence of Day Care Center I & II, Nanyo, Panabo City (20% Development Fund CY 2018 (STIMULUS 2018)
Note on N1445: chai: Previously Perimeter Fence of Day Care Center I & II, Nanyo, Panabo City (20% Development Fund CY 2018 (STIMULUS 2018)
Note on N1451: chai: Previously Perimeter Fence of Day Care Center I & II, Nanyo, Panabo City (20% Development Fund CY 2018 (STIMULUS 2018)
Note on N1487: chai: previously 20% DF
Note on N1493: chai: previously 20% DF
Note on N1499: chai: previously 20% DF
Note on N1505: chai: previously 20% DF
Note on N1511: chai: previously 20% DF
Note on N1517: chai: previously 20% DF
Note on N1529: chai: previously 20% DF
Note on N1541: Cerela Montes: Previously 20% DF
Note on N1559: chai: 20% DF CY 2019
Note on N1565: chai: 20% DF CY 2019
Note on N1571: chai: 20% DF CY 2019
Note on N1577: chai: 20% DF CY 2019
Note on N1583: chai: 20% DF CY 2019
Note on N1589: chai: previously 20% DF CY 2019 (500,000.)
Note on N1607: chai: previously 20% DF CY 2019 (500,000.)
Note on AP1763: Cerela Montes: suspended 10/05/20
Note on AP1769: Cerela Montes:
Note on T1787: chai: 20% Development Fund CY 2018 Variation Order - 21,512,501.5 - 1,408,112.95
Note on K1865: chai: PEO Account
Note on K2417: chai: PGO Account
Note on K2423: chai: Account - PGO
Note on K2429: chai: Account - PGO
Note on K2435: chai: Account - PGO
Note on K2441: chai: Account - PGO
Note on K2447: chai: Account - PGO
Note on K2453: chai: Account - PGO
Note on K2489: chai: PEO Account
Note on K3029: chai: PGO Account
Note on K3035: chai: PEO Account
Note on K3065: chai: PEO Account
Note on K3095: chai: PEO Account
Note on K3137: chai: PGO Account
Note on K3149: chai: PEO Account
Note on K3269: chai: Account-PSWDO
Note on K3407: chai: Account-PEO
Note on K3479: chai: PDRRMC Account
Note on K3533: chai: SEF Account
Note on K3599: chai: PEO Account
Note on N3623: chai: SB No. 1 CY 2019 (STIMULUS PROJECT)
Note on AP3623: Cerela Montes: Php 500,000 - Declared savings to fund new project Construction of Children Playground with amenities at Poblacion, New Corella (SB # 4 CY 2019)- Php500,000 To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1
Note on K3629: chai: PEO Account
Note on K3665: chai: PEO Account (20% DF) (Rehab. Of Prov'l. Roads & Bridges)
Note on K3671: chai: PEO Account (20% DF) (Buildings and Other Structures School Buildings)
Note on K3677: chai: PEO Account (20% DF) (Buildings and Other Structures Hospital and Health Centers)
Note on K3683: chai: PEO Account (20% DF) (Buildings and Other Structures Hospital and Health Centers) OTLF - LBP BORROWINGS
Note on K3689: chai: PEO Account (20% DF) (Buildings and Other Structures Hospital and Health Centers) OTLF - LBP BORROWINGS
Note on K3695: chai: PEO Account (20% DF) (Buildings and Other Structures Hospital and Health Centers) OTLF - LBP BORROWINGS
Note on K3701: chai: PEO Account (20% DF) (Buildings and Other Structures Hospital and Health Centers) OTLF - LBP BORROWINGS
Note on K3707: chai: PEO Account (20% DF) (Buildings and Other Structures Hospital and Health Centers) OTLF - LBP BORROWINGS
Note on K3713: chai: PEO Account (20% DF) (Buildings and Other Structures Hospital and Health Centers) OTLF - LBP BORROWINGS
Note on K3719: chai: PEO Account (20% DF) (Buildings and Other Structures Hospital and Health Centers) OTLF - LBP BORROWINGS
Note on K3725: chai: PEO Account (20% DF) (Subsidy to Other Funds) PRDP Counterpart
Note on K3731: chai: PEO Account (20% DF) (Subsidy to Other Funds) PRDP Counterpart
Note on K3743: chai: PEO Account (Transfers for Project Equity Share/Prov'l. Counterpart)
Note on K3779: chai: PEO Account

## Annual CY 2020 (On-going
|  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | [11 empty] | 0
` | ECONOMIC (INFRASTRUCTURE DEV'T. PROGRAM)
OFFICE/AGENCY: | PROVINCIAL ENGINEER'S OFFICE
AREA: | 1ST ENGINEERING DISTRICT - COMPLETED, ON-GOING AND FOR IMPLEMENTATION PROJECTS | [7 empty] | Total extended
#REF!
#REF!
NAME OF PROJECT |  | SOURCE OF FUND | TYPE OF PROJECT | PHYSICAL TARGET (DESCRIPTION) |  | MODE OF IMPLEMENTATION | PROJECT DATA |  |  |  | FINANCIAL |  | PHYSICAL ACCOMPLISHMENT (JULY) |  | PHYSICAL ACCOMPLISHMENT (AUGUST) |  | PHYSICAL ACCOMPLISHMENT (SEPTEMBER) |  | PHYSICAL ACCOMPLISHMENT (OCTOBER) |  | PHYSICAL ACCOMPLISHMENT |  | EMPLOYMENT GENERATED |  | REMARKS (JULY) | REMARKS (AUGUST) | REMARKS (SEPTEMBER) | REMARKS (OCTOBER | REMARKS (NOVEMBER) | REMARKS
Rehab. Of Pob.-Limbaan-Suawon-Macgum FMR w/ Bridge (42 ln.m), New Corella, Davao del Norte |  | PRDP CY 2015 | Road Concreting | 15.01 | km | Contract | Project Cost: | 205202114.16 | Target Completion Date: | 2018-11-06 23:46 | Program: | 205202114.16 | Planned: | 100% | Planned: | 100% | Planned: | 100% | Planned: | 100% | Planned: | 100% | No. of Persons: | 40 | On-going (Increase of Project Cost due to Variation Order Php 14,948,622.18, Partial suspension due to soft soil from sta. 8+000 - 10+000); (Suspended last April 5, 2020 due to COVID; Resumption Order dated June 1, 2020) | On-going (Increase of Project Cost due to Variation Order Php 14,948,622.18, Partial suspension due to soft soil from sta. 8+000 - 10+000); (Suspended last April 5, 2020 due to COVID; Resumption Order dated June 1, 2020) | On-going (Increase of Project Cost due to Variation Order Php 14,948,622.18, Partial suspension due to soft soil from sta. 8+000 - 10+000); (Suspended last April 5, 2020 due to COVID; Resumption Order dated June 1, 2020) | On-going (Increase of Project Cost due to Variation Order Php 14,948,622.18, Partial suspension due to soft soil from sta. 8+000 - 10+000); (Suspended last April 5, 2020 due to COVID; Resumption Order dated June 1, 2020) | On-going (Increase of Project Cost due to Variation Order Php 14,948,622.18, Partial suspension due to soft soil from sta. 8+000 - 10+000); (Suspended last April 5, 2020 due to COVID; Resumption Order dated June 1, 2020) | Suspended due to variation order dated November 2020
[7 empty] | Project Engineer: | Madrigal | Revised Completion Date: | 2020-10-25 23:46 | Allotment: | 205202114.16 | Revised: | 86.35% | Revised: | 87.69% | Revised: | 87.69% | Revised: | 87.69% | Revised: | 88.78% | No. of Man-days: | 1200
[7 empty] | Implementor: | Dvo. Rock Mixer | No. of days suspended: | 229 | Disbursement: | 141497191.47 | Actual: | 79.97% | Actual: | 81.21% | Actual: | 81.21% | Actual: | 81.21% | Actual: | 83.08%
[7 empty] | Duration: | 943 | No. of days extended: | 490 |  |  | Slippage: | -6.385% | Slippage: | -6.487% | Slippage: | -6.487% | Slippage: | -6.487% | Slippage: | -5.705%
[7 empty] | Date Allotment Released: | CY 2015 | Date completed:
[7 empty] | Date Started: | 2016-04-08
Proposed Davao del Norte Tourism Billboard, Brgy. Lasang, Panabo City |  | SB # 1 CY 2015 | Billboard |  | sq.m | Admin | Project Cost: | 756400 | Target Completion Date: | 2015-05-10 23:59 | Program: | 756400 | Planned: | 11.78% | Planned: | 11.78% | Planned: | 11.78% | Planned: | 11.78% | Planned: | 11.78% | No. of Persons: |  | delay due to change location & design code. For AIP amendment from Panabo City to Gov't Center, Mankilam | delay due to change location & design code. For AIP amendment from Panabo City to Gov't Center, Mankilam | delay due to change location & design code. For AIP amendment from Panabo City to Gov't Center, Mankilam | delay due to change location & design code. For AIP amendment from Panabo City to Gov't Center, Mankilam | delay due to change location & design code. For AIP amendment from Panabo City to Gov't Center, Mankilam | delay due to change location & design code. For AIP amendment from Panabo City to Gov't Center, Mankilam
[7 empty] | Project Engineer: | Porras | Revised Completion Date: |  | Allotment: | 756400 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: | 332087.3 | Actual: | 11.78% | Actual: | 11.78% | Actual: | 11.78% | Actual: | 11.78% | Actual: | 11.78%
[7 empty] | Duration: | 42 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: | 2015-05-06 | Date completed:
[7 empty] | Date Started: | 2015-03-30
Construction of Provincial Training Center , Compound Fence, Kinawitnon, Babak District, IGCS |  | 20% DF CY 2016 | Fence |  | sq.m | Admin | Project Cost: | 940000 | Target Completion Date: | 2018-06-19 23:59 | Program: | 940000 | Planned: | 68% | Planned: | 68% | Planned: | 68% | Planned: | 68% | Planned: | 68% | No. of Persons: |  | Temporarily suspended 4/23/18 due to undemolished structures of illegal settlers | Temporarily suspended 4/23/18 due to undemolished structures of illegal settlers | Temporarily suspended April 23, 2018 due to undemolished structures of illegal settlers(For resumption) | Temporarily suspended April 23, 2018 due to undemolished structures of illegal settlers(For resumption) | Temporarily suspended April 23, 2018 due to undemolished structures of illegal settlers(For resumption) | Temporarily suspended April 23, 2018 due to undemolished structures of illegal settlers(For resumption)
[7 empty] | Project Engineer: | Pacquiao | Revised Completion Date: |  | Allotment: | 940000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: | 933418.8 | Actual: | 75% | Actual: | 75% | Actual: | 75% | Actual: | 75% | Actual: | 75%
[7 empty] | Duration: | 100 | No. of days extended: |  |  |  | Slippage: | 7% | Slippage: | 7% | Slippage: | 7% | Slippage: | 7% | Slippage: | 7%
[7 empty] | Date Allotment Released: | 2017-09-19 | Date completed:
[7 empty] | Date Started: | 2018-03-12
Repair of Damaged/Creeks Along Mankilam Creek, Tagum City |  | QRF CY 2015 & 2016 | Slope Protection |  |  |  | Project Cost: | 1050000 | Target Completion Date: | 2020-04-04 23:46 | Program: | 1050000 | Planned: |  | Planned: |  | Planned: | 100% | Planned: | 100% | Planned: | 63.85% | No. of Persons: | 10 | For AIP Amendment | For AIP Amendment | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | On-going
[7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-01-30 23:46 | Allotment: | 1050000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 169
[7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: | 100% | Actual: | 100% | Actual: | 63.85%
[7 empty] | Duration: | 90 | No. of days extended: | 301 |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
[7 empty] | Date Started: | 2020-01-06
Rehab. Of Saug Bridge of Slope Protection, New Corella |  | QRF CY 2015 & 2016 | Slope Protection | 356.4 | ln.m | Admin | Project Cost: | 4850000 | Target Completion Date: | 2019-05-02 23:46 | Program: | 4850000 | Planned: | 84.06% | Planned: | 100% | Planned: | 100% | Planned: | 100% | Planned: | 100% | No. of Persons: | 7 | Final Abstract # 0320200900 (Alpebel Builders & Supply Corp.) | Final Abstract # 0320200900 (Alpebel Builders & Supply Corp.) | Final Abstract # 0320200900 (Alpebel Builders & Supply Corp.) | Completed as per physical accomplishment. | Completed as per physical accomplishment. | Completed as per Program of Works
[7 empty] | Project Engineer: | Gone | Revised Completion Date: | 2020-12-30 23:46 | Allotment: | 4850000 | Revised: |  | Revised: | 77.89% | Revised: | 77.89% | Revised: | 77.89% | Revised: |  | No. of Man-days: | 182
[7 empty] | Implementor: | PEO | No. of days suspended: | 533 | Disbursement: | 1628912.92 | Actual: | 77.63% | Actual: | 86.91% | Actual: | 86.91% | Actual: | 86.91% | Actual: | 100%
[7 empty] | Duration: | 120 | No. of days extended: | 75 |  |  | Slippage: | -6.43% | Slippage: | 9.02% | Slippage: | 9.02% | Slippage: | 9.02% | Slippage: | 0%
[7 empty] | Date Allotment Released: | 2018-05-25 | Date completed:
[7 empty] | Date Started: | 2019-01-03
Rehab./Repair of Mamacao Bailey Bridge (Retrofitting of Pier and Substructure) |  | QRF CY 2015 & 2016 | Slope Protection | 356.4 | ln.m | Admin | Project Cost: | 2000000 | Target Completion Date: | 2021-03-30 23:46 | Program: | 2000000 | Planned: | 84.06% | Planned: | 100% | Planned: | 100% | Planned: | 100% | Planned: | 3.86% | No. of Persons: | 13 | Final Abstract # 0320200900 (Alpebel Builders & Supply Corp.) | Final Abstract # 0320200900 (Alpebel Builders & Supply Corp.) | Final Abstract # 0320200900 (Alpebel Builders & Supply Corp.) | Completed as per physical accomplishment. | Completed as per physical accomplishment. | On-going
[7 empty] | Project Engineer: | Lumapat | Revised Completion Date: |  | Allotment: | 2000000 | Revised: |  | Revised: | 77.89% | Revised: | 77.89% | Revised: | 77.89% | Revised: |  | No. of Man-days: | 338
[7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: | 77.63% | Actual: | 86.91% | Actual: | 86.91% | Actual: | 86.91% | Actual: | 1.56%
[7 empty] | Duration: | 120 | No. of days extended: |  |  |  | Slippage: | -6.43% | Slippage: | 9.02% | Slippage: | 9.02% | Slippage: | 9.02% | Slippage: | -2.3%
[7 empty] | Date Allotment Released: |  | Date completed:
[7 empty] | Date Started: | 2020-12-01
Improvement of Sto. Tomas Production Center with Common Facility, Sto. Tomas |  | PRDP CY 2016 | Building | 1901 | sq.m | Contract | Project Cost: | 9825000 | Target Completion Date: | 2018-12-24 23:59 | Program: | 9825000 | Planned: | 94.55% | Planned: | 100% | Planned: | 100% | Planned: | 100% | Planned: | 100% | No. of Persons: | 20 | On-going | Final Abstract # 0320200900 (Alpebel Builders & Supply Corp.) | Final Abstract # 0320200900 (Alpebel Builders & Supply Corp.) | Completed as per physical accomplishment. | Completed as per physical accomplishment. | On-going
[7 empty] | Project Engineer: | Azotes | Revised Completion Date: | May 24, 2021 | Allotment: | 9825000 | Revised: | 78.32% | Revised: | 83.43% | Revised: | 83.43% | Revised: | 83.43% | Revised: | 22.53% | No. of Man-days: | 500
[7 empty] | Implementor: | Manantan | No. of days suspended: | 501 | Disbursement: |  | Actual: | 71.89% | Actual: | 75.19% | Actual: | 75.19% | Actual: | 75.19% | Actual: | 30.33%
[7 empty] | Duration: | 330 | No. of days extended: |  |  |  | Slippage: | -6.424% | Slippage: | -8.238% | Slippage: | -8.238% | Slippage: | -8.238% | Slippage: | 7.8%
[7 empty] | Date Allotment Released: | CY 2014 | Date completed:
[7 empty] | Date Started: | 2018-01-29
Construction of Water Reservoir & Purchase of P.E. Pipelines, Sagayen, Asuncion |  | 20% DF CY 2017 (STIMULUS) | Water System |  |  | MLGU | Project Cost: | 500000 | Target Completion Date: | 2018-11-15 | Program: | 500000 | Planned: | 90% | Planned: | 90% | Planned: | 90% | Planned: | 90% | Planned: | 90% | No. of Persons: |  | Suspended due to non availability of water source during drilling.Find another location. Fund already transferred at Municipality of Asuncion with ChecK No. 2445174 and OR # 9238468, | Suspended due to non availability of water source during drilling.Find another location. Fund already transferred at Municipality of Asuncion with ChecK No. 2445174 and OR # 9238468, | Project not implemented due to non availability of water source during drilling. Awaiting for the official documents from Brgy. Sagayen and MLGU - Asuncion for the cancellation of the project. | Project not implemented due to non availability of water source during drilling. Awaiting for the official documents from Brgy. Sagayen and MLGU - Asuncion for the cancellation of the project. | Project not implemented due to non availability of water source during drilling. Awaiting for the official documents from Brgy. Sagayen and MLGU - Asuncion for the cancellation of the project. | Project not implemented due to non availability of water source during drilling. Awaiting for the official documents from Brgy. Sagayen and MLGU - Asuncion for the cancellation of the project.
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: | MEO | No. of days suspended: |  | Disbursement: |  | Actual: | 90% | Actual: | 90% | Actual: | 90% | Actual: | 90% | Actual: | 90%
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: | 2017-12-28 | Date completed:
[7 empty] | Date Started: | 2018-11-15
Road Rehabilitation at Prk. 1-Prk. 5, Sta. Fe, New Corella |  | 20% DF CY 2017 (STIMULUS) | Court |  |  | MLGU | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Fund already transferred at Municipality of Talaingod with ChecK No. 2445181 and OR # 7955667, dated March 16, 2018 . Amended from Electrification @ Prk. 1A-Prk. 5A) | On-going (Implemented by MLGU, since transfer of fund ) | On-going (Implemented by MLGU, since transfer of fund ) | On-going (Implemented by MLGU, since transfer of fund ) | On-going (Implemented by MLGU, since transfer of fund ) | On-going (Implemented by MLGU, since transfer of fund )
[7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: | 2017-12-28 | Date completed:
[7 empty] | Date Started: | 2020-08-25
Construction of 2 Rooms Comfort Room, Brgy. Cacao, Panabo City |  | 20% DF CY 2017 (STIMULUS) | Building |  | sq.m | MLGU | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | Planned: | 100% | Planned: | 100% | Planned: |  | Planned: |  | No. of Persons: |  | Issued warning for termination of the contract | Completed (Implemented by MLGU, since transfer of fund ) | Completed (Implemented by MLGU, since transfer of fund ) |  |  | On-going (Implemented by MLGU, since transfer of fund )
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: | 100% |  | 100%
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: |  | Slippage: |  | Slippage:
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Const. of Multi-Purpose Bldg. @ A.O. Floriendo National Highschool, Panabo City |  | 20% DF CY 2017 (STIMULUS) | Building |  |  | MLGU | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Fund transfer to LGU- 3/28/2019 with check no. 2574939 and OR no. 0166518 - Materials Delivered. Construction on-going | Materials already procured. Ongoing hiring of Admin Laborers. Target date to start the project on September 14, 2020.(Implemented by MLGU, since transfer of fund ) | On-going .(Implemented by MLGU, since transfer of fund ) | On-going .(Implemented by MLGU, since transfer of fund ) | On-going .(Implemented by MLGU, since transfer of fund ) | On-going .(Implemented by MLGU, since transfer of fund )
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: | MLGU | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: | 2017-12-19 | Date completed:
Date Started:
Const. of Concrete Drainage Canal, Kimamon, Panabo City |  | 20% DF CY 2017 (STIMULUS) | Drainage |  |  | MLGU | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | For Implementation | For Implementation | For Implementation | For Implementation | For Implementation | For Implementation
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: | 2017-12-19 | Date completed:
Date Started:
Upgrading of DDNSTC (Basketball/Voleyball MP Covered Court),Sports Center, Mankilam, Tagum City |  | SB # 4 CY 2017 | Covered Court | 2252.69 | sq.m | Contract | Project Cost: | 99992356.64 | Target Completion Date: | 2019-07-11 | Program: | 99992356.64 | Planned: | 100% | Planned: | 100% | Planned: | 100% | Planned: | 100% | Planned: | 100% | No. of Persons: | 10 | On-going (Suspended last April 5, 2020 due to COVID; Resumption Order dated May 4, 2020) | On-going | On-going | On-going | On-going | Suspended as of April 7, 2019
[7 empty] | Project Engineer: | Daral | Revised Completion Date: |  | Allotment: | 99992356.64 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 310
[7 empty] | Implementor: | YBC | No. of days suspended: |  | Disbursement: | 18280402.33 | Actual: | 73.04% | Actual: | 80.54% | Actual: | 80.54% | Actual: | 80.54% | Actual: | 90%
[7 empty] | Duration: | 360 | No. of days extended: | 20 |  |  | Slippage: | -26.96% | Slippage: | -19.46% | Slippage: | -19.46% | Slippage: | -19.46% | Slippage: | -10%
[7 empty] | Date Allotment Released: | 2018-10-16 | Date completed:
[7 empty] | Date Started: | 2018-07-17
Const. of Trading Post, Storage Building with (1) unit Hauling Truck, Prk. Ramihan Datu Abdul, Panabo City |  | OPPAP-PAMANA CY 2017 | Building |  | sq.m | Contract | Project Cost: | 3975000 | Target Completion Date: | 2020-04-05 23:59 | Program: | 3975000 | Planned: | 100% | Planned: | 100% | Planned: | 100% | Planned: | 100% | Planned: | 100% | No. of Persons: | 10 | On-going | On-going | On-going | On-going | On-going/ Subject for Liquidated damages | Suspended
[7 empty] | Project Engineer: | Azotes | Revised Completion Date: | August 24, 2020 | Allotment: | 3975000 | Revised: | 41.6% | Revised: | 100% | Revised: | 100% | Revised: | 100% | Revised: | 100% | No. of Man-days: | 260
[7 empty] | Implementor: | Ultra Core | No. of days suspended: | 71 | Disbursement: |  | Actual: | 41.6% | Actual: | 56.88% | Actual: | 56.88% | Actual: | 56.88% | Actual: | 43.12%
[7 empty] | Duration: | 137 | No. of days extended: | 100 |  |  | Slippage: | 0% | Slippage: | -43.12% | Slippage: | -43.12% | Slippage: | -43.12% | Slippage: | -56.88%
[7 empty] | Date Allotment Released: | CY 2017 | Date completed:
[7 empty] | Date Started: | 2019-11-21
Trading Post, Storage and Hauling Truck Libuak, Island Garden City of Samal (IGACOS) |  | OPPAP-PAMANA CY 2017 | Building |  |  |  | Project Cost: | 4000000 | Target Completion Date: | 2021-01-31 | Program: | 4000000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: | 27.42% | No. of Persons: | 8 | For awarding ALPEBEL | For awarding ALPEBEL | For awarding ALPEBEL | For awarding ALPEBEL | Mobilization on-going | On-going
[7 empty] | Project Engineer: | Andoy/Porras | Revised Completion Date: |  | Allotment: | 4000000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 176
[7 empty] | Implementor: | Alpebel Builders | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual: | 27.42%
[7 empty] | Duration: | 150 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: | CY 2018 | Date completed:
[7 empty] | Date Started: | 2020-09-03
Construction of PWS Level II in Purok 7-A and 7-B, Capungagan, Kapalong |  | OPPAP-PAMANA CY 2017 | Potable Water System |  |  | Admin | Project Cost: | 1760000 | Target Completion Date: | 2020-02-03 | Program: | 1760000 | Planned: | 100% | Planned: | 100% | Planned: | 100% | Planned: | 100% | Planned: | 100% | No. of Persons: | 25 | Suspended due to elecrical permits | Suspended dsted July 30, 2020 due to elecrical permits | Suspended dsted July 30, 2020 due to elecrical permits | Suspended dsted July 30, 2020 due to elecrical permits | Suspended dsted July 30, 2020 due to elecrical permits | Suspended dsted July 30, 2020 due to elecrical permits
[7 empty] | Project Engineer: | Kabinge | Revised Completion Date: | 2020-04-15 | Allotment: | 1760000 | Revised: | 100% | Revised: | 95.08% | Revised: | 95.08% | Revised: | 95.08% | Revised: | 95.08% | No. of Man-days: | 375
[7 empty] | Implementor: | PEO | No. of days suspended: | 28 | Disbursement: | 1235344 | Actual: | 95.57% | Actual: | 98% | Actual: | 98% | Actual: | 98% | Actual: | 98%
[7 empty] | Duration: | 70 | No. of days extended: | 44 |  |  | Slippage: | -4.43% | Slippage: | 2.92% | Slippage: | 2.92% | Slippage: | 2.92% | Slippage: | 2.92%
[7 empty] | Date Allotment Released: | 2019-11-25 | Date completed:
[7 empty] | Date Started: | 2019-11-25
Construction of PWS Level II in Purok 2, Pag-Asa, kapalong |  | OPPAP-PAMANA CY 2017 | Potable Water System |  |  | Admin | Project Cost: | 2310000 | Target Completion Date: | 2020-04-09 | Program: | 2310000 | Planned: | 100% | Planned: | 100% | Planned: | 100% | Planned: | 100% | Planned: | 100% | No. of Persons: | 23 | On-going (Suspended last April 5, 2020 due to COVID; resumption order dated May 4, 2020) | Suspended dated August 26, 2020 due to elecrical permits and delivery of water tank | Suspended dated August 26, 2020 due to elecrical permits and delivery of water tank | Suspended dated August 26, 2020 due to elecrical permits and delivery of water tank | Suspended dated August 26, 2020 due to elecrical permits and delivery of water tank | Suspended dated August 26, 2020 due to elecrical permits and delivery of water tank
[7 empty] | Project Engineer: | Dadula | Revised Completion Date: | 2020-08-20 | Allotment: | 2310000 | Revised: | 100% | Revised: | 81.57% | Revised: | 81.57% | Revised: | 81.57% | Revised: | 100% | No. of Man-days: | 713
[7 empty] | Implementor: | PEO | No. of days suspended: | 28 | Disbursement: | 1678908 | Actual: | 72.68% | Actual: | 76.39% | Actual: | 76.39% | Actual: | 76.39% | Actual: | 100%
[7 empty] | Duration: | 115 | No. of days extended: | 105 |  |  | Slippage: | -27.32% | Slippage: | -5.179% | Slippage: | -5.179% | Slippage: | -5.179% | Slippage: | 0%
[7 empty] | Date Allotment Released: | 2019-11-25 | Date completed: | 2020-08-20
[7 empty] | Date Started: | 2019-12-16
Rice Mill for Upland Rice, Palma Gil, Talaingod |  | OPPAP-PAMANA CY 2017 | Rice Mill |  |  | Admin | Project Cost: | 1000000 | Target Completion Date: | 2020-07-30 23:46 | Program: | 1000000 | Planned: | 42.65% | Planned: | 42.65% | Planned: | 42.65% | Planned: | 42.65% | Planned: | 42.65% | No. of Persons: | 6 | On-going | On-going | On-going | On-going | On-going | Suspended last July 25, 2020. Still waiting for the delivery of Rice Mill as part of the Program.
[7 empty] | Project Engineer: | Torrecampo | Revised Completion Date: | 2020-07-30 23:46 | Allotment: | 1000000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 90
[7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: | 426500 | Actual: | 42.65% | Actual: | 42.65% | Actual: | 42.65% | Actual: | 42.65% | Actual: | 42.65%
[7 empty] | Duration: | 60 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
[7 empty] | Date Started: | 2020-06-01
Const. of Potable Water System at Brgy. Tibungol, Panabo City |  | 20% DF CY 2018 | Water System |  | ln.m | Admin | Project Cost: | 1250000 | Target Completion Date: | 2020-04-15 23:59 | Program: | 1250000 | Planned: | 2.13% | Planned: | 2.13% | Planned: | 2.13% | Planned: | 2.13% | Planned: | 2.13% | No. of Persons: | 3 | Suspended dated February 19, 2020 undelivered hardware materials (Supplier refused to deliver. Letter already submitted to BAC.) | Suspended dated February 19, 2020 undelivered hardware materials (materials re-bid) | Suspended dated February 19, 2020 undelivered hardware materials (materials re-bid) | Suspended dated February 19, 2020 undelivered hardware materials (materials re-bid) | Suspended dated February 19, 2020 undelivered hardware materials (materials re-bid) | Suspended dated February 19, 2020 undelivered hardware materials (Supplier refused to deliver. Letter already submitted to BAC.)
[7 empty] | Project Engineer: | Andoy | Revised Completion Date: |  | Allotment: | 1250000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 15
[7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: | 0.76% | Actual: | 0.76% | Actual: | 0.76% | Actual: | 0.76% | Actual: | 0.76%
[7 empty] | Duration: | 87 | No. of days extended: |  |  |  | Slippage: | -1.37% | Slippage: | -1.37% | Slippage: | -1.37% | Slippage: | -1.37% | Slippage: | -1.37%
[7 empty] | Date Allotment Released: | 2018-11-21 | Date completed:
[7 empty] | Date Started: | 2020-01-20
Const. of Distribution Line in Sitio Prk. 1,3,4, 11 and 7, Camansa, Asuncion |  | 20% DF CY 2018 | Electrification |  |  | Contract | Project Cost: | 4000000 | Target Completion Date: |  | Program: | 4000000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: | 78% | No. of Persons: |  | Awarded to 3E ELECTRICAL SALES & SERVICES | Awarded to 3E ELECTRICAL SALES & SERVICES | For impelementation (Awarded to 3E ELECTRICAL SALES & SERVICES) | For impelementation (Awarded to 3E ELECTRICAL SALES & SERVICES) | For impelementation (Awarded to 3E ELECTRICAL SALES & SERVICES) | On-going
[7 empty] | Project Engineer: | Bueno | Revised Completion Date: | 0 | Allotment: | 4000000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: | 3E Electirical and Engineering | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual: | 78%
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
[7 empty] | Date Started: | 2020-08-06
Rehab. Of Multi-Purpose Gym & Facililies Maduao, Panabo City |  | 20% DF CY 2018 (STIMULUS) | Gym |  |  |  | Project Cost: | 500000 | Target Completion Date: | 2020-10-07 | Program: | 500000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Post qualification on process | Post qualification on process | Suspended due to overlapping of activity. (DIGOS CONTRAK CORP.) | Suspended due to overlapping of activity. (DIGOS CONTRAK CORP.) | Suspended due to overlapping of activity. (DIGOS CONTRAK CORP.) | Suspended due to overlapping of activity. (DIGOS CONTRAK CORP.)
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: | Digos Constrak Corp/ | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: | 34 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
[7 empty] | Date Started: | 2020-09-03
Electrification of Sitio Baongon-Diamond-Mansanitas, Dadatan, IGCS |  | 20% DF CY 2018 (STIMULUS) | Electrification |  |  |  | Project Cost: | 500000 | Target Completion Date: | 2020-05-09 | Program: | 500000 | Planned: |  | Planned: |  | Planned: | 100% | Planned: | 100% | Planned: | 100% | No. of Persons: |  | On-going (Subject for Liquidated damages) | On-going (Subject for Liquidated damages) | On-going (Subject for Liquidated damages) | On-going (Subject for Liquidated damages) | On-going (Subject for Liquidated damages) | On-going (Subject for Liquidated damages)
[7 empty] | Project Engineer: | Lu | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: | 100% | Revised: | 100% | Revised: | 100% | No. of Man-days:
[7 empty] | Implementor: | 3E Electrical Sales | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: | 65.1% | Actual: | 65.1% | Actual: | 65.1%
[7 empty] | Duration: | 60 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | -34.9% | Slippage: | -34.9% | Slippage: | -34.9%
[7 empty] | Date Allotment Released: |  | Date completed:
[7 empty] | Date Started: | 2020-03-10
Barangay Hall Improvement, Dagohoy, Talaingod |  | 20% DF CY 2018 (STIMULUS) | Building |  |  | Contract | Project Cost: | 500000 | Target Completion Date: | 2021-01-20 23:59 | Program: | 500000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | For amendment to Construction of Retaining Wall as per recommendation by Engr. Misa during site re-evaluation. Plan & POW completed.Resolution from the Brgy. Council to support the amendment c/o Engr. Canillada | For amendment to Construction of Retaining Wall as per recommendation by Engr. Misa during site re-evaluation. Plan & POW completed.Resolution from the Brgy. Council to support the amendment c/o Engr. Canillada | Awarded to Alpebels Builders & Supply Corporation | For implementation | For implementation | On-going
[7 empty] | Project Engineer: | Kabingue | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: | Alpebels Builders & Supply Corporation | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: | 45 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
[7 empty] | Date Started: | 2020-12-07
Construction of SP/Legislative Building, Gov't. Center, Mankilam, Tagum City |  | SB # 3 CY 2018 | Building |  |  | Contract | Project Cost: | 147262698.81 | Target Completion Date: | 2021-04-04 | Program: | 147262698.81 | Planned: | 5.78% | Planned: | 5.78% | Planned: | 14.98% | Planned: | 14.98% | Planned: | 58.3% | No. of Persons: | 34 | For amendment to Construction of Retaining Wall as per recommendation by Engr. Misa during site re-evaluation. Plan & POW completed.Resolution from the Brgy. Council to support the amendment c/o Engr. Canillada | For amendment to Construction of Retaining Wall as per recommendation by Engr. Misa during site re-evaluation. Plan & POW completed.Resolution from the Brgy. Council to support the amendment c/o Engr. Canillada | Awarded to Alpebels Builders & Supply Corporation | For implementation | For implementation | On-going
[7 empty] | Project Engineer: | Japay/Albaracin | Revised Completion Date: | 2021-05-01 | Allotment: | 147262698.81 | Revised: | 3.15% | Revised: | 4.777% | Revised: | 7.387% | Revised: | 7.387% | Revised: | 38.89% | No. of Man-days: | 884
[7 empty] | Implementor: | Tagum Builders | No. of days suspended: | 27 | Disbursement: |  | Actual: | 5.28% | Actual: | 7.37% | Actual: | 8.971% | Actual: | 8.971% | Actual: | 26.56%
[7 empty] | Duration: | 370 | No. of days extended: |  |  |  | Slippage: | 2.13% |  | 2.594% |  | 1.584% |  | 1.584% | Slippage: | -12.33%
[7 empty] | Date Allotment Released: |  | Date completed:
[7 empty] | Date Started: | 2020-03-30
Compl. Of Bahay Pag-Asa for Minors, New Corella |  | SB # 2 CY 2018 | Building |  |  | Admin | Project Cost: | 3450000 | Target Completion Date: | 2020-11-07 23:46 | Program: | 3450000 | Planned: | 15.75% | Planned: | 55.46% | Planned: | 71.45% | Planned: | 100% | Planned: | 98.48% | No. of Persons: | 20 | On-going | On-going | On-going | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | On-going
[7 empty] | Project Engineer: | Cahayag | Revised Completion Date: | 2021-01-15 23:46 | Allotment: | 3450000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 620
[7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: | 5.04% | Actual: | 42.41% | Actual: | 64.16% | Actual: | 100% | Actual: | 97.2%
[7 empty] | Duration: | 144 | No. of days extended: | 69 |  |  | Slippage: | -10.71% | Slippage: | -13.05% | Slippage: | -7.29% | Slippage: | 0% | Slippage: | -1.28%
[7 empty] | Date Allotment Released: |  | Date completed:
[7 empty] | Date Started: | 2020-06-17
Const. of Add'l. 2nd Level Multi-Purpose HalI, PGSO warehouse,Bldg., Mankilam |  | SB # 2 CY 2018 | Building |  |  | Contract | Project Cost: | 7483756.22 | Target Completion Date: | 2020-07-06 23:46 | Program: | 7483756.22 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: | 99.07% | No. of Persons: | 19 | On-going | On-going | On-going | On-going | On-going | On-going
[7 empty] | Project Engineer: | Mabanglo | Revised Completion Date: | 2020-09-13 23:46 | Allotment: | 7483756.22 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: | 40.05% | No. of Man-days: | 589
[7 empty] | Implementor: | FZI CONSTRUCTION AND PARTS SUPPLY | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: | 9.68% | Actual: | 9.68% | Actual: | 30.17%
[7 empty] | Duration: | 180 | No. of days extended: | 69 |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 9.68% | Slippage: | 9.68% | Slippage: | -9.88%
[7 empty] | Date Allotment Released: |  | Date completed:
[7 empty] | Date Started: | 2020-01-09
Jct. Highway Canatan - Doña Andrea |  | 20% DF CY 2019 | Road Rehabilitation | 4.34 | km | Admin | Project Cost: | 2000000 | Target Completion Date: | 2020-08-11 23:46 | Program: | 2000000 | Planned: | 60% | Planned: | 75% | Planned: | 75% | Planned: | 75% | Planned: | 75% | No. of Persons: |  | On-going | On-going | On-going | On-going | On-going | On-going
[7 empty] | Project Engineer: | Pilotos | Revised Completion Date: | 2020-08-11 23:46 | Allotment: | 2000000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: | 1200000 | Actual: | 60% | Actual: | 75% | Actual: | 75% | Actual: | 75% | Actual: | 75%
[7 empty] | Duration: | 57 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: | 2019-06-12 | Date completed:
[7 empty] | Date Started: | 2020-06-16
Pamacaun - Lasang Banate |  | 20% DF CY 2019 | Road Rehabilitation | 4.34 |  | Admin | Project Cost: | 2000000 | Target Completion Date: | 2020-11-10 23:46 | Program: | 2000000 | Planned: |  | Planned: | 52.32% | Planned: |  | Planned: |  | Planned: | 52.32% | No. of Persons: |  | For implementation (Waiting for the delivery of geo-grid materials. An approved request letter dated Dec. 3, 2019 for the extension of 50 days from Provincial Administrator Engr. Rabanoz is on file | Suspended due to continous rain. Waiting for the stability of swamp area. | Suspended due to continous rain. Waiting for the stability of swamp area. | Suspended due to continous rain. Waiting for the stability of swamp area. | Suspended due to continous rain. Waiting for the stability of swamp area. | Suspended Oct.5, 2020
[7 empty] | Project Engineer: | Gone | Revised Completion Date: | 2020-11-10 23:46 | Allotment: | 2000000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: | Admin | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: | 52.32% | Actual: |  | Actual: |  | Actual: | 52.32%
[7 empty] | Duration: | 84 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: | 2019-06-27 | Date completed:
[7 empty] | Date Started: | 2020-08-19
Jct. Paiton - Mibolo |  | 20% DF CY 2019 | Road Rehabilitation | 23.9 | km | Contract | Project Cost: | 6000000 | Target Completion Date: | 2020-10-05 23:46 | Program: | 6000000 | Planned: | 21.05% | Planned: | 21.05% | Planned: | 34.1% | Planned: | 34.1% | Planned: | 100% | No. of Persons: | 14 | Temporary suspended because the materials for the box culvert procurement on process wth PO # 2019061674 | Temporary suspended because the materials for the box culvert procurement on process wth PO # 2019061674 | On-going | On-going | On-going | On-going
[7 empty] | Project Engineer: | Lumapat | Revised Completion Date: | 2020-12-27 23:46 | Allotment: | 6000000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: | 56.28% | No. of Man-days: | 434
[7 empty] | Implementor: | PEO | No. of days suspended: | 83 | Disbursement: | 1263000 | Actual: | 21.05% | Actual: | 21.05% | Actual: | 31.25% | Actual: | 31.25% | Actual: | 56.28%
[7 empty] | Duration: | 218 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | -2.85% | Slippage: | -2.85% | Slippage: | 0%
[7 empty] | Date Allotment Released: | 2019-03-25 | Date completed:
[7 empty] | Date Started: | 2020-03-02
ROAD ID 077 - Tubod - Pilar |  | 20% DF CY 2019 | Road Rehabilitation | 1.55 | km | Admin | Project Cost: | 16000000 | Target Completion Date: | 2020-11-05 | Program: | 16000000 | Planned: | 62.5% | Planned: | 69.85% | Planned: | 69.85% | Planned: | 69.85% | Planned: | 100% | No. of Persons: | 18 | On-going | On-going | On-going |  |  | On-going
[7 empty] | Project Engineer: | Agang | Revised Completion Date: |  | Allotment: | 16000000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 396
[7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: | 4046971.2 | Actual: | 58.23% | Actual: | 71.98% | Actual: | 71.98% | Actual: | 71.98% | Actual: | 78.08%
[7 empty] | Duration: | 323 | No. of days extended: |  |  |  | Slippage: | -4.27% | Slippage: | 2.13% | Slippage: | 2.13% | Slippage: | 2.13% | Slippage: | -21.92%
[7 empty] | Date Allotment Released: | 2019-11-26 | Date completed:
[7 empty] | Date Started: | 2019-12-18
New Katipunan - Pantaron |  | 20% DF CY 2019 | Road Rehabilitation | 1.96 | km | Admin | Project Cost: | 395000 | Target Completion Date: | 2020-02-25 | Program: | 395000 | Planned: | 60% | Planned: | 60% | Planned: | 60% | Planned: | 60% | Planned: | 60% | No. of Persons: | 4 | On-going | On-going | On-going | On-going | On-going | On-going
[7 empty] | Project Engineer: | Gamad/Clar | Revised Completion Date: |  | Allotment: | 395000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 24
[7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: | 60% | Actual: | 60% | Actual: | 60% | Actual: | 60% | Actual: | 60%
[7 empty] | Duration: | 60 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: | 2019-01-03 | Date completed:
[7 empty] | Date Started: | 2019-12-27
Bdry. Tagum - Crossing Kinamayan Sto. Tomas |  | 20% DF CY 2019 | Road Rehabilitation | 0.75 | km | Admin | Project Cost: | 3700000 | Target Completion Date: | 2020-04-25 | Program: | 3700000 | Planned: | 100% | Planned: | 100% | Planned: | 100% | Planned: | 100% | Planned: | 100% | No. of Persons: | 15 | On-going | On-going | On-going | On-going | On-going | On-going
[7 empty] | Project Engineer: | Gamad/Clar | Revised Completion Date: | 2020-08-23 | Allotment: | 3700000 | Revised: | 15.43% | Revised: | 15.43% | Revised: | 15.43% | Revised: | 15.43% | Revised: | 15.43% | No. of Man-days: | 225
[7 empty] | Implementor: |  | No. of days suspended: | 20 | Disbursement: |  | Actual: | 16.37% | Actual: | 16.37% | Actual: | 16.37% | Actual: | 16.37% | Actual: | 16.37%
[7 empty] | Duration: | 120 | No. of days extended: | 100 |  |  | Slippage: | 0.94% | Slippage: | 0.94% | Slippage: | 0.94% | Slippage: | 0.94% | Slippage: | 0.94%
[7 empty] | Date Allotment Released: | 2019-01-03 | Date completed:
[7 empty] | Date Started: | 2019-12-27
Impv't. of Potable Water System, Consolacion, Panabo City |  | 20% DF CY 2019 | Water System |  |  |  | Project Cost: | 500000 | Target Completion Date: | 2020-06-06 | Program: | 500000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: | 100% | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. |  |  | Subject for LD, no activity on site/ Issued 2nd warning letter
[7 empty] | Project Engineer: | Abayon | Revised Completion Date: | September 1, 2020 | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: | 56.5% | No. of Man-days:
[7 empty] | Implementor: | RLHV | No. of days suspended: | 86 | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual: | 1.2%
[7 empty] | Duration: | 60 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | -55.3%
[7 empty] | Date Allotment Released: |  | Date completed:
[7 empty] | Date Started: | 2020-04-07
Const. of IP Women's Multi-Purpose Bldg., Cabidiangan, Sto. Niño, Talaingod |  | 20% DF CY 2019 | Building |  |  | Admin | Project Cost: | 2000000 | Target Completion Date: | 2020-12-07 | Program: | 2000000 | Planned: |  | Planned: |  | Planned: | 14.65% | Planned: | 14.65% | Planned: | 100% | No. of Persons: | 10 | Awarded to Alpebel Builders | On-going | On-going | On-going | On-going | Slippage is due to intermittent rain on site
[7 empty] | Project Engineer: | Torrecampo | Revised Completion Date: | 2021-01-11 | Allotment: | 2000000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: | 89.76% | No. of Man-days: | 300
[7 empty] | Implementor: | ALPEBEL BUILDERS & SUPPLY CORP. | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: | 14.65% | Actual: | 14.65% | Actual: | 47.74%
[7 empty] | Duration: | 105 | No. of days extended: | 35 |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | -42.02%
[7 empty] | Date Allotment Released: | 2019-05-15 | Date completed:
[7 empty] | Date Started: | 2020-08-24
Const. of DDN Hospital Carmen Zone Annex Bldg. Phase 2, |  | 20% DF CY 2019 | Building |  | sq.m | Contract | Project Cost: | 3620000 | Target Completion Date: | 2020-10-24 | Program: | 3620000 | Planned: |  | Planned: |  | Planned: | 10.51% | Planned: | 10.15% | Planned: | 10.15% | No. of Persons: | 15 | On-going | On-going | On-going | On-going | On-going | On-going
[7 empty] | Project Engineer: | Azotes | Revised Completion Date: |  | Allotment: | 3620000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 330
[7 empty] | Implementor: | Digos Constrak Corp/ | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: | 8.12% | Actual: | 8.12% | Actual: | 8.12%
[7 empty] | Duration: | 92 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | -2.39% | Slippage: | -2.03% | Slippage: | -2.03%
[7 empty] | Date Allotment Released: | 2019-06-28 | Date completed:
[7 empty] | Date Started: | 2020-07-24
Construction of Bahay Silangan for Reformation of Drug Personalities within The Military Camp/barracks, Brgy. Mankilam, Tagum City |  | 20% DF CY 2019 | Building | 126 | sq.m | Contract | Project Cost: | 5000000 | Target Completion Date: | 2021-04-13 | Program: | 5000000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: | 34.66% | No. of Persons: | 16 | Abstract #0620202232 - Post Qualification on process (ZULAR-A) | Abstract #0620202232 - Post Qualification on process (ZULAR-A) | Abstract #0620202232 - Post Qualification on process (ZULAR-A) | Abstract #0620202232 - Post Qualification on process (ZULAR-A) | Abstract #0620202232 - Post Qualification on process (ZULAR-A) | On-going
[7 empty] | Project Engineer: | Torrecampo | Revised Completion Date: |  | Allotment: | 5000000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 330
[7 empty] | Implementor: | Zular-AZ Const. and Suppy | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual: | 53.71%
[7 empty] | Duration: | 190 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 19.05%
[7 empty] | Date Allotment Released: |  | Date completed:
[7 empty] | Date Started: | 2020-10-05
Rehab. Of Brgy. Health Center, Apokon, Tagum City |  | 20% DF CY 2019 (STIMULUS) | Building |  |  |  | Project Cost: | 500000 | Target Completion Date: | 2020-12-07 23:46 | Program: | 500000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: | 100% | No. of Persons: | 8 | For implementation (The brgy. council agreed not to pursue with the project if it will not be completed and needs additional funds) | For implementation (The brgy. council agreed not to pursue with the project if it will not be completed and needs additional funds) | For implementation (The brgy. council agreed not to pursue with the project if it will not be completed and needs additional funds) | For implementation (The brgy. council agreed not to pursue with the project if it will not be completed and needs additional funds) | For implementation (The brgy. council agreed not to pursue with the project if it will not be completed and needs additional funds) | On-going (Slippage due to pending of installation of roofing works. (Job Order)
[7 empty] | Project Engineer: | Torrecampo | Revised Completion Date: | 2021-01-16 23:46 | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: | 76.13% | No. of Man-days: | 120
[7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual: | 75.11%
[7 empty] | Duration: | 50 | No. of days extended: | 40 |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | -1.02%
[7 empty] | Date Allotment Released: | 2019-03-25 | Date completed:
[7 empty] | Date Started: | 2020-10-19
Rehab. Of Evacuation Center, Casig-ang, Sto. Tomas |  | 20% DF CY 2019 (STIMULUS | Building |  |  | Contract | Project Cost: | 500000 | Target Completion Date: | 2021-01-16 | Program: | 500000 | Planned: |  | Planned: |  | Planned: |  | Planned: | 12.3% | Planned: | 12.3% | No. of Persons: | 5 | On-going | PR #20063670 | Revision of POW on-going | On-going | On-going | On-going
[7 empty] | Project Engineer: | Estorco | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 110
[7 empty] | Implementor: | JJR Const. & Supply | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: | 13.6% | Actual: | 13.6%
[7 empty] | Duration: | 100 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 1.3% | Slippage: | 1.3%
[7 empty] | Date Allotment Released: |  | Date completed:
[7 empty] | Date Started: | 2020-10-08
Installation of Pipelines, Libertad, IGCS |  | 20% DF CY 2019 (STIMULUS | Pipelines |  |  |  | Project Cost: | 500000 | Target Completion Date: | 2020-09-17 | Program: | 500000 | Planned: |  | Planned: |  | Planned: | 100% | Planned: | 100% | Planned: | 100% | No. of Persons: | 4 | For implementation | On-going | On-going | On-going | On-going | On-going
[7 empty] | Project Engineer: | Porras | Revised Completion Date: | 2020-11-01 | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: | 42.1% | Revised: | 56.4% | Revised: | 56.4% | No. of Man-days: | 88
[7 empty] | Implementor: | Admin | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: | 56.1% | Actual: | 62.4% | Actual: | 62.4%
[7 empty] | Duration: | 25 | No. of days extended: | 45 |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 14% | Slippage: | 6% | Slippage: | 6%
[7 empty] | Date Allotment Released: | 2019-03-25 | Date completed:
[7 empty] | Date Started: | 2020-08-24
Rural Electrification at Sitio Bundok San Roque, Brgy. New Cortez, New Corella |  | 20% DF CY 2019 | Electrification |  |  |  | Project Cost: | 1000000 | Target Completion Date: | 2021-01-05 23:46 | Program: | 1000000 | Planned: | 43% | Planned: | 43% | Planned: | 43% | Planned: | 43% | Planned: | 98% | No. of Persons: |  | On-going | On-going | On-going | On-going | On-going | On-going
[7 empty] | Project Engineer: | P.Bueno | Revised Completion Date: | 2021-01-05 23:46 | Allotment: | 1000000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: | Tagum Builders | No. of days suspended: |  | Disbursement: |  | Actual: | 43% | Actual: | 43% | Actual: | 43% | Actual: | 43% | Actual: | 98%
[7 empty] | Duration: | 43 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
[7 empty] | Date Started: | 2020-11-24
Rehab. Of Multi-Purpose Hall, Talomo, Sto. Tomas |  | 20% DF CY 2019 (STIMULUS | Building |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Fund transfer to LGU - 6/26/2019 with check no. 2575130 and OR no. 0557456 For implementation | Fund transfer to LGU - 6/26/2019 with check no. 2575130 and OR no. 0557456 For implementation | On-going (Implemented by MLGU, since transfer of fund ) | On-going (Implemented by MLGU, since transfer of fund ) | On-going (Implemented by MLGU, since transfer of fund ) | On-going (Implemented by MLGU, since transfer of fund )
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Repair/Rehab. Of Concrete Road Jct. Suaon-Libuton, Kapalong |  | SB NO. 3 CY 2019 | Road Drainage rehabiliated |  | km | Admin | Project Cost: | 1000000 | Target Completion Date: | 2020-02-15 23:46 | Program: | 1000000 | Planned: | 14.73% | Planned: | 14.73% | Planned: | 30.27% | Planned: | 30.27% | Planned: | 100% | No. of Persons: |  | Plan On-going | Plan On-going | Plan On-going | Completed as per physical accomplishment. | Completed as per physical accomplishment. | Completed as per Program of Works
[7 empty] | Project Engineer: | Bacaron | Revised Completion Date: | 2020-11-15 23:46 | Allotment: | 1000000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: | PEO | No. of days suspended: | 228 | Disbursement: | 142000 | Actual: | 14.2% | Actual: | 14.2% | Actual: | 30.27% | Actual: | 30.27% | Actual: | 100%
[7 empty] | Duration: | 90 | No. of days extended: | 46 |  |  | Slippage: | -0.53% | Slippage: | -0.53% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: | 2019-03-12 | Date completed: | 2020-11-15
[7 empty] | Date Started: | 2019-11-18
Provincial Livestock & Poultry Multiplier Farm Road Network Construction, Sitio Salawao, Sto. Niño, Talaingod |  | SB NO. 4 CY 2019 | Conc. Pavement |  | sq.m | Admin | Project Cost: | 5500000 | Target Completion Date: | 2020-07-13 23:46 | Program: | 5500000 | Planned: | 30.06% | Planned: | 56.09% | Planned: | 56.09% | Planned: | 56.09% | Planned: | 100% | No. of Persons: | 28 | Plan On-going | Plan On-going | Plan On-going | Completed (Implemented by MLGU, since transfer of fund ) | Completed (Implemented by MLGU, since transfer of fund ) | On-going
[7 empty] | Project Engineer: | Pasiona/Juan | Revised Completion Date: | 2021-01-29 23:46 | Allotment: | 5500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: | 87.29% | No. of Man-days: | 420
[7 empty] | Implementor: | PEO | No. of days suspended: | 28 | Disbursement: | 4704199.85 | Actual: | 30.06% | Actual: | 45.48% | Actual: | 45.48% | Actual: | 45.48% | Actual: | 81.94%
[7 empty] | Duration: | 120 | No. of days extended: | 172 |  |  | Slippage: | 0% | Slippage: | -10.61% | Slippage: | -10.61% | Slippage: | -10.61% | Slippage: | -5.35%
[7 empty] | Date Allotment Released: | CY 2019 | Date completed:
[7 empty] | Date Started: | 2020-03-16
Construction of Children's Playground with Amenities, Poblacion, New Corella |  | SB No. 4 CY 2019 (STIMULUS) | Building |  | sq.m | Admin | Project Cost: | 2500000 | Target Completion Date: | 2020-03-03 23:59 | Program: | 2500000 | Planned: | 57.9% | Planned: | 64.73% | Planned: | 64.73% | Planned: | 64.73% | Planned: | 64.73% | No. of Persons: | 10 | On-going (Suspended effective April 5, 2020 due to COVID; resumption order dated May 4, 2020) | On-going (Suspended effective April 5, 2020 due to COVID; resumption order dated May 4, 2020) | On-going (Suspended effective April 5, 2020 due to COVID; resumption order dated May 4, 2020) |  |  | On-going
[7 empty] | Project Engineer: | Mayang | Revised Completion Date: | 2020-04-30 23:59 | Allotment: | 2500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 150
[7 empty] | Implementor: | PEO | No. of days suspended: | 28 | Disbursement: | 1029250 | Actual: | 57.9% | Actual: | 64.73% | Actual: | 64.73% | Actual: | 64.73% | Actual: | 64.73%
[7 empty] | Duration: | 100 | No. of days extended: | 30 |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: | 2019-12-06 | Date completed:
[7 empty] | Date Started: | 2019-11-25
Const. Of Multi-Purpose Hall, Buenavista, Panabo City |  | SB # 4 CY 2019 (STIMULUS) | Building |  |  | Contract | Project Cost: | 500000 | Target Completion Date: | 2021-02-03 | Program: | 500000 | Planned: |  | Planned: |  | Planned: | 5% | Planned: | 28.54% | Planned: | 28.54% | No. of Persons: | 7 | Purchase Order # 2020031248- DIGOS CONSTRAK | For implementation (DIGOS CONSTRAK) | On-going | On-going | On-going | On-going
[7 empty] | Project Engineer: | Andoy | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 154
[7 empty] | Implementor: | Digos Constrak Corp/ | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: | 5% | Actual: | 32.17% | Actual: | 32.17%
[7 empty] | Duration: | 160 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 3.63% | Slippage: | 3.63%
[7 empty] | Date Allotment Released: | 2019-10-18 | Date completed:
[7 empty] | Date Started: | 2020-08-27
Rehab. Of Multi-Purpose Hall, Kasilak, Panabo City |  | SB # 4 CY 2019 (STIMULUS) | Building |  |  | Contract | Project Cost: | 650000 | Target Completion Date: | 2020-11-11 | Program: | 650000 | Planned: |  | Planned: |  | Planned: | 56.3% | Planned: | 60.18% | Planned: | 60.18% | No. of Persons: | 4 | On-going | On-going | On-going | On-going | On-going | On-going
[7 empty] | Project Engineer: | Estorco | Revised Completion Date: |  | Allotment: | 650000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 88
[7 empty] | Implementor: | JJR Const. & Supply | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: | 45.3% | Actual: | 58.4% | Actual: | 58.4%
[7 empty] | Duration: | 120 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | -11% | Slippage: | -1.78% | Slippage: | -1.78%
[7 empty] | Date Allotment Released: |  | Date completed:
[7 empty] | Date Started: | 2020-07-14
Proposed Road Opening of Tawinian-Tapayanon Road Section |  | SB NO. 4 CY 2019 | Road |  | km | Admin | Project Cost: | 10000000 | Target Completion Date: | 2020-10-01 23:46 | Program: | 10000000 | Planned: | 34.2% | Planned: | 41.6% | Planned: | 41.6% | Planned: | 41.6% | Planned: | 100% | No. of Persons: | 8 | On-going (Suspended last April 5, 2020 due to COVID; resumption order dated May 4, 2020); Equipment Rental 1 unit Backhoe (Bidding July 16, 2020) | On-going (Suspended last April 5, 2020 due to COVID; resumption order dated May 4, 2020); Equipment Rental 1 unit Backhoe (Bidding July 16, 2020) | On-going (Suspended last April 5, 2020 due to COVID; resumption order dated May 4, 2020); Equipment Rental 1 unit Backhoe (Bidding July 16, 2020) |  |  | On-going
[7 empty] | Project Engineer: | Garcia | Revised Completion Date: | 2020-10-29 23:46 | Allotment: | 10000000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: | 65.52% | No. of Man-days: | 138
[7 empty] | Implementor: | PEO | No. of days suspended: | 28 | Disbursement: |  | Actual: | 34.2% | Actual: | 41.6% | Actual: | 41.6% | Actual: | 41.6% | Actual: | 70.86%
[7 empty] | Duration: | 319 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 5.34%
[7 empty] | Date Allotment Released: | 2019-11-15 | Date completed:
[7 empty] | Date Started: | 2019-11-18
Improvement of Km. 9 Sagayen-Sawata Provincial Road, San Isidro, Ph. II |  | SB NO. 4 CY 2019 | Road |  | ln.m | Admin | Project Cost: | 4591029 | Target Completion Date: | 2020-03-27 | Program: | 4591029 | Planned: | 45% | Planned: | 45% | Planned: | 45% | Planned: | 45% | Planned: | 45% | No. of Persons: | 6 | Suspended | Suspended | Suspended | Suspended | Suspended | Suspended
[7 empty] | Project Engineer: | Limpo | Revised Completion Date: |  | Allotment: | 4591029 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 138
[7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: | 1609155.6645 | Actual: | 35.05% | Actual: | 35.05% | Actual: | 35.05% | Actual: | 35.05% | Actual: | 35.05%
[7 empty] | Duration: | 200 | No. of days extended: |  |  |  | Slippage: | -9.95% | Slippage: | -9.95% | Slippage: | -9.95% | Slippage: | -9.95% | Slippage: | -9.95%
[7 empty] | Date Allotment Released: | 2019-12-12 | Date completed:
[7 empty] | Date Started: | 2019-09-09
Construction of 2 Classroom Building Datu Jose Libayao NHS Ext, Natulian, Palma Gil, Talaingod |  | SEF-AB CY 2019 | Building |  | km |  | Project Cost: | 2000000 | Target Completion Date: |  | Program: | 2000000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: | 20% | No. of Persons: |  | PO#2020061983 - FL2 LUMBER & CONST. SUPPLY; PO #2020062164 - jkle enterprises | PO#2020061983 - FL2 LUMBER & CONST. SUPPLY; PO #2020062164 - jkle enterprises | PO#2020061983 - FL2 LUMBER & CONST. SUPPLY; PO #2020062164 - jkle enterprises |  |  | On-going
[7 empty] | Project Engineer: | Ambrosio | Revised Completion Date: |  | Allotment: | 2000000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual: | 20%
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
[7 empty] | Date Started: | 2020-10-01
Const. of 1 Classroom @ Tawinian E/S, Gupitan, kapalong |  | SEF-SB No. 2 CY 2019 | Building |  | sq.m |  | Project Cost: | 500000 | Target Completion Date: | 2020-12-14 23:59 | Program: | 500000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: | 80% | No. of Persons: |  | Opening of Shopping on June 25, 2020 | Opening of Shopping on June 25, 2020 | Opening of Shopping on June 25, 2020 | Opening of Shopping on June 25, 2020 | Opening of Shopping on June 25, 2020 | On-going
[7 empty] | Project Engineer: | Mabanglo | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: | Alpebel Builders and Supply Corporation | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual: | 80%
[7 empty] | Duration: | 75 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
[7 empty] | Date Started: | 2020-10-01
Const. of 1 Classroom @ Moling E/S, Gupitan, kapalong |  | SEF-SB No. 2 CY 2019 | Building |  | sq.m |  | Project Cost: | 500000 | Target Completion Date: | 2020-12-14 23:59 | Program: | 500000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: | 90% | No. of Persons: |  | Opening of Shopping on June 25, 2020 | Opening of Shopping on June 25, 2020 | Opening of Shopping on June 25, 2020 | Opening of Shopping on June 25, 2020 | Opening of Shopping on June 25, 2020 | On-going
[7 empty] | Project Engineer: | Mabanglo | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: | Alpebel Builders and Supply Corporation | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual: | 90%
[7 empty] | Duration: | 75 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
[7 empty] | Date Started: | 2020-10-01
Const. of 1 Classroom @ Kawayan ES, Gupitan, Kapalong |  | SEF-SB No. 2 CY 2019 | Building |  | sq.m |  | Project Cost: | 500000 | Target Completion Date: | 2020-12-14 23:59 | Program: | 500000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: | 50% | No. of Persons: |  | Opening of Shopping on June 25, 2020 | Opening of Shopping on June 25, 2020 | Opening of Shopping on June 25, 2020 | Opening of Shopping on June 25, 2020 | Opening of Shopping on June 25, 2020 | On-going
[7 empty] | Project Engineer: | Mabanglo | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: | Alpebel Builders and Supply Corporation | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual: | 50%
[7 empty] | Duration: | 75 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
[7 empty] | Date Started: | 2020-10-01
Const. of 1 Classroom @ Matol ES, Gupitan, Kapalong |  | SEF-SB No. 2 CY 2019 | Building |  | sq.m |  | Project Cost: | 500000 | Target Completion Date: | 2020-12-14 23:59 | Program: | 500000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: | 90% | No. of Persons: |  | Opening of Shopping on June 25, 2020 | Opening of Shopping on June 25, 2020 | Opening of Shopping on June 25, 2020 | Opening of Shopping on June 25, 2020 | Opening of Shopping on June 25, 2020 | On-going
[7 empty] | Project Engineer: | Mabanglo | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: | Alpebel Builders and Supply Corporation | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual: | 90%
[7 empty] | Duration: | 75 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
[7 empty] | Date Started: | 2020-10-01
Const. of 1 Classroom @ Hermogina Salibay ES, Capungagan, Kapalong |  | SEF-SB No. 2 CY 2019 | Building |  | sq.m |  | Project Cost: | 500000 | Target Completion Date: | 2020-12-14 23:59 | Program: | 500000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: | 50% | No. of Persons: |  | Opening of Shopping on June 25, 2020 | Opening of Shopping on June 25, 2020 | Opening of Shopping on June 25, 2020 | Opening of Shopping on June 25, 2020 | Opening of Shopping on June 25, 2020 | On-going
[7 empty] | Project Engineer: | Mabanglo | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: | Alpebel Builders and Supply Corporation | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual: | 50%
[7 empty] | Duration: | 75 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
[7 empty] | Date Started: | 2020-10-01
Const. of 1 Classroom @ Dulyan ES, Palma Gil, Talaingod |  | SEF-SB No. 2 CY 2019 | Building |  | sq.m |  | Project Cost: | 500000 | Target Completion Date: | 2020-12-14 23:59 | Program: | 500000 | Planned: |  | Planned: |  | Planned: |  | Planned: | 100% | Planned: | 75% | No. of Persons: |  | Opening of Shopping on June 25, 2020 | Opening of Shopping on June 25, 2020 | Opening of Shopping on June 25, 2020 | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | On-going
[7 empty] | Project Engineer: | Mabanglo | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: | Alpebel Builders and Supply Corporation | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: | 100% | Actual: | 75%
[7 empty] | Duration: | 75 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
[7 empty] | Date Started: | 2020-10-01
Desilting of Limbaan Creek, New Corella |  | 5% CALAMITY FUND CY 2019 | creeks and canals deislted |  | ln.m | Admin | Project Cost: | 2000000 | Target Completion Date: | 2019-12-02 | Program: | 2000000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Suspended | Suspended | Suspended | Suspended | Suspended | Suspended
[7 empty] | Project Engineer: | Pilotos | Revised Completion Date: | 2019-12-02 | Allotment: | 2000000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: | 257 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
[7 empty] | Date Started: | 2019-03-20
Impv't. of Jct. New Boholano - New Loon Cross Drainage |  | 5% CALAMITY FUND CY 2019 | Drainage |  | km | Admin | Project Cost: | 2000000 | Target Completion Date: | 2020-02-16 | Program: | 2000000 | Planned: | 42.27% | Planned: | 42.27% | Planned: | 42.27% | Planned: | 42.27% | Planned: | 70% | No. of Persons: |  | Suspended due to availability of equipment | Suspended due to availability of equipment | Suspended due to availability of equipment | Suspended due to availability of equipment | Suspended due to availability of equipment | On-going
[7 empty] | Project Engineer: | Pilotos | Revised Completion Date: | 2020-02-16 | Allotment: | 2000000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: | 31.7% | Actual: | 31.7% | Actual: | 31.7% | Actual: | 31.7% | Actual: | 70%
[7 empty] | Duration: | 90 | No. of days extended: |  |  |  | Slippage: | -10.57% | Slippage: | -10.57% | Slippage: | -10.57% | Slippage: | -10.57% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
[7 empty] | Date Started: | 2019-11-18
Rehabilitation of Pamacaun-Lasang-Banate Provincial Road |  | SB NO. 3 CY 2019 (5% CALAMITY FUND) | Road |  |  | Admin | Project Cost: | 1500000 | Target Completion Date: | 2020-11-10 23:46 | Program: | 1500000 | Planned: |  | Planned: |  | Planned: | 41.21% | Planned: | 41.21% | Planned: | 41.21% | No. of Persons: |  | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | On-going (Suspended Oct.5, 2020)
[7 empty] | Project Engineer: | Gone | Revised Completion Date: |  | Allotment: | 1500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: | 17.82% | Actual: | 52.32% | Actual: | 52.32% | Actual: | 52.32%
[7 empty] | Duration: | 100 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 17.82% | Slippage: | 11.11% | Slippage: | 11.11% | Slippage: | 11.11%
[7 empty] | Date Allotment Released: |  | Date completed:
[7 empty] | Date Started: | 2020-08-03
Rehabilitation of Del Pilar Jct. Silangan |  | SB NO. 3 CY 2019 (5% CALAMITY FUND) | Road |  | km | Admin | Project Cost: | 1500000 | Target Completion Date: | 2020-03-27 23:46 | Program: | 1500000 | Planned: | 81.11% | Planned: | 81.11% | Planned: | 81.11% | Planned: | 81.11% | Planned: | 100% | No. of Persons: | 4 | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | On-going (Resumption date Dec. 7, 2020)
[7 empty] | Project Engineer: | Gone | Revised Completion Date: | 2021-01-15 23:46 | Allotment: | 1500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: | 92.61% | No. of Man-days: | 40
[7 empty] | Implementor: | PEO | No. of days suspended: | 243 | Disbursement: |  | Actual: | 81.11% | Actual: | 81.11% | Actual: | 81.11% | Actual: | 81.11% | Actual: | 90.42%
[7 empty] | Duration: | 40 | No. of days extended: | 51 |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | -2.19%
[7 empty] | Date Allotment Released: | 2019-07-26 | Date completed:
[7 empty] | Date Started: | 2020-02-17
Rehab. Of Sonlon - Camansa FMR Asuncion, Davao del Norte |  | PRDP CY 2015 | Road Concreting | 10.23 | km | Contract | Project Cost: | 215125015.81 | Target Completion Date: | 2021-01-01 | Program: | 215125015.81 | Planned: | 39.51% | Planned: | 40.75% | Planned: | 40.75% | Planned: |  | Planned: | 49.13% | No. of Persons: |  | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. |  |  | On-going
[7 empty] | Project Engineer: | Fabiala | Revised Completion Date: | 2021-03-05 | Allotment: | 215125015.81 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: | Three w/Builders, Inc/Davao Rock Mixer Enterprises (JV) | No. of days suspended: | 56 | Disbursement: | 40523099.23 | Actual: | 31.6% | Actual: | 33.45% | Actual: | 33.45% | Actual: |  | Actual: | 42.68%
[7 empty] | Duration: | 584 | No. of days extended: | 7 |  |  | Slippage: | -7.91% | Slippage: | -7.306% | Slippage: | -7.306% | Slippage: | 0% | Slippage: | -6.452%
[7 empty] | Date Allotment Released: | 2018-09-18 | Date completed:
[7 empty] | Date Started: | 2019-05-28
Road Upgrading of Jct Highway - Sto Nino - La Paz - San Vicenter Provincial Road, Carmen |  | CMGP CY 2019 | Road |  | km | Contract | Project Cost: | 80481331.34 | Target Completion Date: | 2020-06-22 | Program: | 80481331.34 | Planned: | 97.44% | Planned: | 98.83% | Planned: | 98.83% | Planned: | 100% | Planned: | 100% | No. of Persons: | 10 | On-going | On-going | On-going | On-going | On-going | On-going | 94.91
[7 empty] | Project Engineer: | Fernandez | Revised Completion Date: | Oct. 19, 2020 | Allotment: | 80481331.34 | Revised: |  | Revised: |  | Revised: |  | Revised: | 99.26% | Revised: | 99.26% | No. of Man-days: | 250
[7 empty] | Implementor: | Tagum Builders | No. of days suspended: | 37 | Disbursement: | 78066891.3998 | Actual: | 97.54% | Actual: | 98.98% | Actual: | 98.98% | Actual: | 99.24% | Actual: | 99.24%
[7 empty] | Duration: | 259 | No. of days extended: | 82 |  |  | Slippage: | 0.1% | Slippage: | 0.15% | Slippage: | 0.15% | Slippage: | -0.024% | Slippage: | -0.024%
[7 empty] | Date Allotment Released: | CY 2019 | Date completed:
[7 empty] | Date Started: | 2019-10-07
Rehabilitation of Dasing to Monte Carlo FMR, Del Pilar, New Corella |  | LGSF CY 2019 | Concreting |  |  | Contract | Project Cost: | 40000000 | Target Completion Date: | 2021-04-04 23:59 | Program: | 40000000 | Planned: | 8.35% | Planned: | 8.35% | Planned: | 8.35% | Planned: | 8.35% | Planned: | 66.49% | No. of Persons: | 10 | On-going | On-going | On-going | On-going | On-going | On-going
[7 empty] | Project Engineer: | Madrigal | Revised Completion Date: | 2021-04-04 23:59 | Allotment: | 40000000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 250
[7 empty] | Implementor: | Rely Const. & Supply | No. of days suspended: |  | Disbursement: |  | Actual: | 8.35% | Actual: | 8.35% | Actual: | 8.35% | Actual: | 8.35% | Actual: | 71.31%
[7 empty] | Duration: | 285 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 4.82%
[7 empty] | Date Allotment Released: |  | Date completed:
[7 empty] | Date Started: | 2020-06-24
Concreting of Visayan Village - Purok exodus - Purok Rafael, Brgy. Magugpo South, Tagum City |  | LGSF CY 2019 | Concreting |  |  | Contract | Project Cost: | 40000000 | Target Completion Date: | 2021-05-18 23:59 | Program: | 40000000 | Planned: | 14.69% | Planned: | 14.69% | Planned: | 42.57% | Planned: | 42.57% | Planned: | 59.27% | No. of Persons: | 32 | On-going | On-going | On-going | On-going | On-going | On-going
[7 empty] | Project Engineer: | Avila | Revised Completion Date: | 2021-05-18 23:59 | Allotment: | 40000000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 960
[7 empty] | Implementor: | Legacy Const. Corp. | No. of days suspended: |  | Disbursement: |  | Actual: | 26.73% | Actual: | 26.73% | Actual: | 48.07% | Actual: | 48.07% | Actual: | 70.21%
[7 empty] | Duration: | 330 | No. of days extended: |  |  |  | Slippage: | 12.04% | Slippage: | 12.04% | Slippage: | 5.5% | Slippage: | 5.5% | Slippage: | 10.93%
[7 empty] | Date Allotment Released: | CY 2019 | Date completed:
[7 empty] | Date Started: | 2020-06-23
Road Upgrading of Farm To Market Road at Brgy. Buenavista |  | LGSF CY 2019 | Road |  | km | Contract | Project Cost: | 40000000 | Target Completion Date: | 2021-02-04 | Program: | 40000000 | Planned: | 6.3% | Planned: | 6.3% | Planned: | 6.3% | Planned: | 41.42% | Planned: |  | No. of Persons: | 60 | On-going | On-going | On-going |  |  | On-going
[7 empty] | Project Engineer: | Nasol | Revised Completion Date: |  | Allotment: | 40000000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 1320
[7 empty] | Implementor: | Alpha Omega | No. of days suspended: |  | Disbursement: |  | Actual: | 9.55% | Actual: | 9.55% | Actual: | 9.55% | Actual: | 34.82% | Actual:
[7 empty] | Duration: | 220 | No. of days extended: |  |  |  | Slippage: | 3.25% | Slippage: | 3.25% | Slippage: | 3.25% | Slippage: | -6.6% | Slippage:
[7 empty] | Date Allotment Released: | CY 2019 | Date completed:
[7 empty] | Date Started: | 2020-06-29
Road Upgrading of New Katipunan-Pantaron Provincial Road |  | LGSF CY 2019 | Road |  | km | Contract | Project Cost: | 30000000 | Target Completion Date: | 2021-01-14 | Program: | 30000000 | Planned: | 1.75% | Planned: | 1.75% | Planned: | 1.75% | Planned: | 31.04% | Planned: |  | No. of Persons: | 20 | On-going | On-going | On-going |  |  | On-going
[7 empty] | Project Engineer: | Sanchez | Revised Completion Date: | 2021-02-23 | Allotment: | 30000000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 440
[7 empty] | Implementor: | FFJJ | No. of days suspended: | 40 | Disbursement: |  | Actual: | 1.65% | Actual: | 1.65% | Actual: | 1.65% | Actual: | 31.13% | Actual:
[7 empty] | Duration: | 190 | No. of days extended: |  |  |  | Slippage: | -0.1% | Slippage: | -0.1% | Slippage: | -0.1% | Slippage: | 0.085% | Slippage:
[7 empty] | Date Allotment Released: |  | Date completed:
[7 empty] | Date Started: | 2020-07-08
ROAD ID 001 - Jct. Highway Magatos - New Bantayan |  | GENERAL FUND CY 2020 | Maintenance | 7.1 | km | CBRMC | Project Cost: | 230700 | Target Completion Date: |  | Program: | 230700 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: | 25% | No. of Persons: |  | Purchase Request # 19125305 (On process) | Purchase Request # 19125305 (On process) | Purchase Request # 19125305 (On process) | Purchase Request # 19125305 (On process) | Purchase Request # 19125305 (On process) | On-going
[7 empty] | Project Engineer: | Fabian | Revised Completion Date: |  | Allotment: | 230700 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: | CALAFA | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual: | 25%
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
ROAD ID 040 - Datu Balong - Pinamuno |  | 20% Development Fund CY 2020 | Road Rehabilitaion | 2.74 | km | Admin | Project Cost: | 822000 | Target Completion Date: | 2021-02-03 23:59 | Program: | 822000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: | 30.04% | No. of Persons: | 13 | POW on process | POW on process | POW on process | POW on process | POW on process | On-going
[7 empty] | Project Engineer: | Crucio | Revised Completion Date: |  | Allotment: | 822000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 374
[7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual: | 30.04%
[7 empty] | Duration: | 65 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
[7 empty] | Date Started: | 2020-12-01
ROAD ID 069 - Mesaoy - Jct. Mahayahay |  | 20% Development Fund CY 2020 | Road Rehabilitaion | 4.6 | km | Admin | Project Cost: | 1380000 | Target Completion Date: | 2021-02-15 23:59 | Program: | 1380000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: | 72.16% | No. of Persons: |  | POW on process | POW on process | POW on process | POW on process | POW on process | On--going
[7 empty] | Project Engineer: | Pilotos | Revised Completion Date: |  | Allotment: | 1380000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual: | 72.16%
[7 empty] | Duration: | 60 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
[7 empty] | Date Started: | 2020-12-18
ROAD ID 073 - Cebulano - Mangalcal |  | GENERAL FUND CY 2020 | Maintenance | 4.17 | km | MBA | Project Cost: | 134672.7 | Target Completion Date: | 2020-12-31 23:59 | Program: | 134672.7 | Planned: | 50% | Planned: | 50% | Planned: | 50% | Planned: | 81% | Planned: | 81% | No. of Persons: | 9 | On-going | On-going | On-going | On-going | On-going | On-going
[7 empty] | Project Engineer: | Gamad/Clar | Revised Completion Date: |  | Allotment: | 134672.7 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 45
[7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: | 51% | Actual: | 51% | Actual: | 51% | Actual: | 83.6% | Actual: | 83.6%
[7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 1% | Slippage: | 1% | Slippage: | 1% | Slippage: | 2.6% | Slippage: | 2.6%
[7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
[7 empty] | Date Started: | 2020-01-02
ROAD ID 082 - Jct. Highway Carmen - Mangalcal - Tubod |  | GENERAL FUND CY 2020 | Maintenance | 11.34 | km | CBRMC | Project Cost: | 259594.46 | Target Completion Date: | 2021-02-04 | Program: | 259594.46 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: | 42.1% | No. of Persons: | 3 | PO #2020031403 - Awarded to TUBOD CENTRO LOWER IRRIGATORS ASS'T (TUCLIA) | PO #2020031403 - Awarded to TUBOD CENTRO LOWER IRRIGATORS ASS'T (TUCLIA) | PO #2020031403 - Awarded to TUBOD CENTRO LOWER IRRIGATORS ASS'T (TUCLIA) | For implementation (Winning Bidder Tubod Central Lower Irrigator Association) | For implementation (Winning Bidder Tubod Central Lower Irrigator Association) | On-going
[7 empty] | Project Engineer: | Maligro | Revised Completion Date: |  | Allotment: | 259594.46 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 18
[7 empty] | Implementor: | Tubod Central Lower Irrigator Association | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual: | 41.66%
[7 empty] | Duration: | 6 months | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | -0.44%
[7 empty] | Date Allotment Released: |  | Date completed:
[7 empty] | Date Started: | 2020-08-04
ROAD ID 086 - Ising - Sadpodon - Taba - Dila -Dila |  | GENERAL FUND CY 2020 | Maintenance | 5.68 | km | CBRMC | Project Cost: | 135230.61 | Target Completion Date: | 2/24/2021 | Program: | 135230.61 | Planned: | 50% | Planned: | 50% | Planned: | 50% | Planned: | 50% | Planned: | 42.1% | No. of Persons: | 4 | PO #2020031408 - Awarded to TABA COCONUT FARMERS ORGANIZATION | PO #2020031408 - Awarded to TABA COCONUT FARMERS ORGANIZATION | PO #2020031408 - Awarded to TABA COCONUT FARMERS ORGANIZATION | For implementation (Winning Bidder Taba Coconut Farmers Association) | For implementation (Winning Bidder Taba Coconut Farmers Association) | On-going
[7 empty] | Project Engineer: | Maligro | Revised Completion Date: |  | Allotment: | 135230.61 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 16
[7 empty] | Implementor: | Taba Coconut Farmers Association | No. of days suspended: |  | Disbursement: |  | Actual: | 55% | Actual: | 55% | Actual: | 55% | Actual: | 55% | Actual: | 41.68%
[7 empty] | Duration: | 6 months | No. of days extended: |  |  |  | Slippage: | 5% | Slippage: | 5% | Slippage: | 5% | Slippage: | 5% | Slippage: | -0.42%
[7 empty] | Date Allotment Released: |  | Date completed:
[7 empty] | Date Started: | 2020-08-24
ROAD ID 087 - Tuganay - taba |  | GENERAL FUND CY 2020 | Maintenance | 4.27 | km | CBRMC | Project Cost: | 102630.37 | Target Completion Date: |  | Program: | 102630.37 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: | 42.6% | No. of Persons: | 5 | PO #2020031406 - TABA COCONUT FARMERS ORGANIZATION | PO #2020031406 - TABA COCONUT FARMERS ORGANIZATION | PO #2020031406 - TABA COCONUT FARMERS ORGANIZATION | PO #2020031406 - TABA COCONUT FARMERS ORGANIZATION | PO #2020031406 - TABA COCONUT FARMERS ORGANIZATION | On-going
[7 empty] | Project Engineer: | Maligro | Revised Completion Date: |  | Allotment: | 102630.37 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 21
[7 empty] | Implementor: | Taba Coconut Farmers Association | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual: | 42.31%
[7 empty] | Duration: | 6 months | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | -0.29%
[7 empty] | Date Allotment Released: |  | Date completed:
[7 empty] | Date Started: | 2020-08-24
ROAD ID 090 - Maligaya - New Camiling |  | GENERAL FUND CY 2020 | Maintenance |  | km | CBRMC | Project Cost: | 83915.44 | Target Completion Date: | 2020-11-14 23:59 | Program: | 83915.44 | Planned: | 5% | Planned: | 5% | Planned: | 5% | Planned: | 29.38% | Planned: | 53.1% | No. of Persons: | 6 | On-going | On-going | On-going | On-going | On-going | On-going
[7 empty] | Project Engineer: | Maligro | Revised Completion Date: |  | Allotment: | 83915.44 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 24
[7 empty] | Implementor: | School in the Air Integrated Farmer's Associiation | No. of days suspended: |  | Disbursement: |  | Actual: | 5% | Actual: | 5% | Actual: | 5% | Actual: | 29.38% | Actual: | 53.95%
[7 empty] | Duration: | 185 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0.85%
[7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
[7 empty] | Date Started: | 2020-05-14
ROAD ID 095 - Anibongan - Guadalupe |  | GENERAL FUND CY 2020 | Maintenance | 2.48 | km | CBRMC | Project Cost: | 72444.97 | Target Completion Date: |  | Program: | 72444.97 | Planned: |  | Planned: |  | Planned: |  | Planned: | 42.27% | Planned: | 42.27% | No. of Persons: | 8 | PO #2020031404 - PRK 4. ANIBONGAN CARMENT IRRIGATORS ASSN. | PO #2020031404 - PRK 4. ANIBONGAN CARMENT IRRIGATORS ASSN. | PO #2020031404 - PRK 4. ANIBONGAN CARMENT IRRIGATORS ASSN. | On-going | On-going | On-going
[7 empty] | Project Engineer: | Maligro | Revised Completion Date: |  | Allotment: | 72444.97 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 40
[7 empty] | Implementor: | Anibongan-Carmen Irrigators Asso. Inc | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: | 42.27% | Actual: | 42.27%
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
[7 empty] | Date Started: | 2020-08-04
ROAD ID 097 - Jct. Anibongan - Prk. 2, 7, 5, San Isidro |  | GENERAL FUND CY 2020 | Maintenance | 3.14 | km | CBRMC | Project Cost: | 110478.58 | Target Completion Date: | 2021-03-11 | Program: | 110478.58 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: | 41.64% | No. of Persons: | 5 | PO #2020031378 - SAN ISIDRO FARMERS IRRIGATORS ASSN. | PO #2020031378 - SAN ISIDRO FARMERS IRRIGATORS ASSN. | PO #2020031378 - SAN ISIDRO FARMERS IRRIGATORS ASSN. | PO #2020031378 - SAN ISIDRO FARMERS IRRIGATORS ASSN. | PO #2020031378 - SAN ISIDRO FARMERS IRRIGATORS ASSN. | On-going
[7 empty] | Project Engineer: | Maligro | Revised Completion Date: |  | Allotment: | 110478.58 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 21
[7 empty] | Implementor: | San Isidro Farmers Irrigators Association | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual: | 41.64%
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
[7 empty] | Date Started: | 2020-09-11
ROAD ID 098 - Anibongan - Salvacion - Cabay-angan |  | GENERAL FUND CY 2020 | Maintenance | 6.93 | km | CBRMC | Project Cost: | 162397.48 | Target Completion Date: | 2021-01-31 | Program: | 162397.48 | Planned: |  | Planned: |  | Planned: |  | Planned: | 41.7% | Planned: | 41.7% | No. of Persons: | 4 | PO #2020031379 - PRK4. ANIBONGAN CARMEN IRRIGATORS ASS. | PO #2020031379 - PRK4. ANIBONGAN CARMEN IRRIGATORS ASS. | PO #2020031379 - PRK4. ANIBONGAN CARMEN IRRIGATORS ASS. | On-going | On-going | On-going
[7 empty] | Project Engineer: | Maligro | Revised Completion Date: |  | Allotment: | 162397.48 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 88
[7 empty] | Implementor: | Anibongan-Carmen Irrigators Asso. Inc | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: | 41.7% | Actual: | 41.7%
[7 empty] | Duration: | 6 months | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: | 2020-08-04 | Date completed:
[7 empty] | Date Started: | 2020-01-02
ROAD ID 099 - Mabaus - Cabay - angan |  | GENERAL FUND CY 2020 | Maintenance |  | km | CBRMC | Project Cost: | 90556.21 | Target Completion Date: | 2021-04-13 | Program: | 90556.21 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: | 42.39% | No. of Persons: | 3 | PO #2020031410 - LAMPIA PAG ASA IRRIGATORS ASS., INC. | PO #2020031410 - LAMPIA PAG ASA IRRIGATORS ASS., INC. | PO #2020031410 - LAMPIA PAG ASA IRRIGATORS ASS., INC. | PO #2020031410 - LAMPIA PAG ASA IRRIGATORS ASS., INC. | PO #2020031410 - LAMPIA PAG ASA IRRIGATORS ASS., INC. | On-going
[7 empty] | Project Engineer: | Maligro | Revised Completion Date: |  | Allotment: | 90556.21 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 15
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual: | 42.39%
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
[7 empty] | Date Started: | 2020-10-13
ROAD ID 101 - Jct. Highway Guadalupe - Bdry. Tagum |  | GENERAL FUND CY 2020 | Maintenance | 7.9 | km | CBRMC | Project Cost: | 231823.89 | Target Completion Date: | 2021-07-13 | Program: | 231823.89 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: | 27.75% | No. of Persons: | 4 | PO #2020031376 - LAMPIA PAG ASA IRRIGATORS ASS., INC. | PO #2020031376 - LAMPIA PAG ASA IRRIGATORS ASS., INC. | PO #2020031376 - LAMPIA PAG ASA IRRIGATORS ASS., INC. | PO #2020031376 - LAMPIA PAG ASA IRRIGATORS ASS., INC. | PO #2020031376 - LAMPIA PAG ASA IRRIGATORS ASS., INC. | On-going
[7 empty] | Project Engineer: | Maligro | Revised Completion Date: |  | Allotment: | 231823.89 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 15
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual: | 27.75%
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
[7 empty] | Date Started: | 2020-10-13
ROAD ID 107 - Dujali - San Isidro |  | GENERAL FUND CY 2020 | Maintenance | 3 | km | CBRMC | Project Cost: | 78482.06 | Target Completion Date: | 2021-03-11 | Program: | 78482.06 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: | 41.67% | No. of Persons: | 6 | PO #2020031411 - SAN ISIDRO FARMERS IRRIGATORS ASSN., INC. | PO #2020031411 - SAN ISIDRO FARMERS IRRIGATORS ASSN., INC. | PO #2020031411 - SAN ISIDRO FARMERS IRRIGATORS ASSN., INC. | PO #2020031411 - SAN ISIDRO FARMERS IRRIGATORS ASSN., INC. | PO #2020031411 - SAN ISIDRO FARMERS IRRIGATORS ASSN., INC. | On-going
[7 empty] | Project Engineer: | Maligro | Revised Completion Date: |  | Allotment: | 78482.06 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 21
[7 empty] | Implementor: | San Isidro Farmers Irrigators Association | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual: | 41.67%
[7 empty] | Duration: | 6 months | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
[7 empty] | Date Started: | 2020-09-11
ROAD ID 113 - Dujali - Balisong - Magupising |  | GENERAL FUND CY 2020 | Maintenance | 5.52 | km | CBRMC | Project Cost: | 115911.95 | Target Completion Date: | 2020-12-12 | Program: | 115911.95 | Planned: | 5% | Planned: | 5% | Planned: | 5% | Planned: | 27.78% | Planned: | 55.5% | No. of Persons: | 2 | On-going | On-going | On-going | On-going | On-going | On-going
[7 empty] | Project Engineer: | Maligro | Revised Completion Date: | 2021-01-08 | Allotment: | 115911.95 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 2
[7 empty] | Implementor: | Dujali Poblacion Farmer's Irrigator's Association, Inc. | No. of days suspended: | 27 | Disbursement: |  | Actual: | 5% | Actual: | 5% | Actual: | 5% | Actual: | 27.78% | Actual: | 55.56%
[7 empty] | Duration: | 187 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0.06%
[7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
[7 empty] | Date Started: | 2020-06-08
ROAD ID 130 - Los Amigos 1 - Esperanza - Los Amigos 2 |  | GENERAL FUND CY 2020 | Maintenance | 3.59 | km | CBRMC | Project Cost: | 131608.37 | Target Completion Date: | 2020-02-21 | Program: | 131608.37 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: | 41.88% | No. of Persons: | 4 | PO #2020031351 - LOS AMIGOS GROUP OF WOMEN & FARMERS ASSN. | PO #2020031351 - LOS AMIGOS GROUP OF WOMEN & FARMERS ASSN. | PO #2020031351 - LOS AMIGOS GROUP OF WOMEN & FARMERS ASSN. | PO #2020031351 - LOS AMIGOS GROUP OF WOMEN & FARMERS ASSN. | PO #2020031351 - LOS AMIGOS GROUP OF WOMEN & FARMERS ASSN. | On-going
[7 empty] | Project Engineer: | Maligro | Revised Completion Date: |  | Allotment: | 131608.37 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 16
[7 empty] | Implementor: | Los Amigos Group of Women abd Farmers Association | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual: | 41.88%
[7 empty] | Duration: | 6 months | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
[7 empty] | Date Started: | 2020-08-31
ROAD ID 131 - Mugas - Lanatad |  | GENERAL FUND CY 2020 | Maintenance |  | km | CBRMC | Project Cost: | 31996.54 | Target Completion Date: | 2021-01-20 | Program: | 31996.54 | Planned: |  | Planned: |  | Planned: |  | Planned: | 10.1% | Planned: | 41.64% | No. of Persons: | 6 | Purchase Order # 2020030961 (Katipunan Pantaron Irrigator's Association) | Purchase Order # 2020030961 (Katipunan Pantaron Irrigator's Association) | Purchase Order # 2020030961 (Katipunan Pantaron Irrigator's Association) | On-going | On-going | On-going
[7 empty] | Project Engineer: | Maligro | Revised Completion Date: |  | Allotment: | 31996.54 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 20
[7 empty] | Implementor: | Katipunan Pantaron Irrigator's Association | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: | 10.1% | Actual: | 41.64%
[7 empty] | Duration: | 6 months | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
[7 empty] | Date Started: | 2020-07-20
ROAD ID 134 - New Katipunan - Pantaron |  | GENERAL FUND CY 2020 | Maintenance |  | km | CBRMC | Project Cost: | 53126.32 | Target Completion Date: | 2021-01-20 | Program: | 53126.32 | Planned: |  | Planned: |  | Planned: |  | Planned: | 10% | Planned: | 41.04% | No. of Persons: |  | Purchase Order # 2020030964 (Katipunan Pantaron Irrigator's Association) | Purchase Order # 2020030964 (Katipunan Pantaron Irrigator's Association) | Purchase Order # 2020030964 (Katipunan Pantaron Irrigator's Association) | On-going | On-going | On-going
[7 empty] | Project Engineer: | Maligro | Revised Completion Date: |  | Allotment: | 53126.32 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: | Katipunan Pantaron Irrigator's Association | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: | 10% | Actual: | 41.04%
[7 empty] | Duration: | 6 months | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
[7 empty] | Date Started: | 2020-07-02
ROAD ID 135 - Sto. Tomas - Bdry. Mamacao |  | GENERAL FUND CY 2020 | Maintenance | 4.9 | km | CBRMC | Project Cost: | 116515.66 | Target Completion Date: | 2021-02-05 | Program: | 116515.66 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: | 41.79% | No. of Persons: | 6 | PO #2020031353 - KATIPUNAN PANTARON IRRIGATORS ASSN. | PO #2020031353 - KATIPUNAN PANTARON IRRIGATORS ASSN. | PO #2020031353 - KATIPUNAN PANTARON IRRIGATORS ASSN. | PO #2020031353 - KATIPUNAN PANTARON IRRIGATORS ASSN. | PO #2020031353 - KATIPUNAN PANTARON IRRIGATORS ASSN. | On-going
[7 empty] | Project Engineer: | Maligro | Revised Completion Date: |  | Allotment: | 116515.66 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 18
[7 empty] | Implementor: | Katipunan Pantaron Irrigator's | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual: | 41.79%
[7 empty] | Duration: | 6 months | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
[7 empty] | Date Started: | 2020-08-05
ROAD ID 136 - Fd. Rd. 3 - San Jose |  | GENERAL FUND CY 2020 | Maintenance | 4.55 | km | CBRMC | Project Cost: | 112893.42 | Target Completion Date: | 2021-02-05 | Program: | 112893.42 | Planned: |  | Planned: |  | Planned: |  | Planned: | 42.25% | Planned: | 42.25% | No. of Persons: | 3 | Purchase Order # 2020030974 (Brgy. San Jose Upland Farmer's Assocaition) | Purchase Order # 2020030974 (Brgy. San Jose Upland Farmer's Assocaition) | Purchase Order # 2020030974 (Brgy. San Jose Upland Farmer's Assocaition) | On-going | On-going | On-going
[7 empty] | Project Engineer: | Maligro | Revised Completion Date: |  | Allotment: | 112893.42 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 66
[7 empty] | Implementor: | Brgy. San Jose Upland Farmer's Assocaition | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: | 42.25% | Actual: | 42.25%
[7 empty] | Duration: | 6 months | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
[7 empty] | Date Started: | 2020-08-05
ROAD ID 146 - Bdry. Tagum - Crossing Kinamayan Sto. Tomas |  | GENERAL FUND CY 2020 | Maintenance |  | km | CBRMC | Project Cost: | 429840.12 | Target Completion Date: | 2021-05-21 | Program: | 429840.12 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: | 27.71% | No. of Persons: | 4 | PO #2020031407 - LOS AMIGOS GROUP OF WOMEN & FARMERS ASSN. | PO #2020031407 - LOS AMIGOS GROUP OF WOMEN & FARMERS ASSN. | PO #2020031407 - LOS AMIGOS GROUP OF WOMEN & FARMERS ASSN. | PO #2020031407 - LOS AMIGOS GROUP OF WOMEN & FARMERS ASSN. | PO #2020031407 - LOS AMIGOS GROUP OF WOMEN & FARMERS ASSN. | On-going
[7 empty] | Project Engineer: | Maligro | Revised Completion Date: |  | Allotment: | 429840.12 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 84
[7 empty] | Implementor: | Bobongon Rural Waterworks & Sanitation Association, Inc. | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual: | 27.71%
[7 empty] | Duration: | 6 months | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
[7 empty] | Date Started: | 2020-08-21
ROAD ID 151 - San Jose - Sitio Mahayahay, Magwawa |  | GENERAL FUND CY 2020 | Maintenance | 0.84 | km | CBRMC | Project Cost: | 30789.12 | Target Completion Date: | 2021-02-03 | Program: | 30789.12 | Planned: |  | Planned: |  | Planned: |  | Planned: | 27.78% | Planned: | 27.78% | No. of Persons: |  | Purchase Order # 2020030972 (Brgy. San Jose Upland Farmer's Assocaition) | Purchase Order # 2020030972 (Brgy. San Jose Upland Farmer's Assocaition) | Purchase Order # 2020030972 (Brgy. San Jose Upland Farmer's Assocaition) | On-going | On-going | On-going
[7 empty] | Project Engineer: | Maligro | Revised Completion Date: |  | Allotment: | 30789.12 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: | Brgy. San Jose Upland Farmer's Assocaition | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: | 27.78% | Actual: | 27.78%
[7 empty] | Duration: | 6 months | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
[7 empty] | Date Started: | 2020-08-03
ROAD ID 030 - Jct. Highway - Carmen - Mangalcal - Tubod (Phase I) |  | 20% DF CY 2020 | Rehabilitation |  | km |  | Project Cost: | 1323000 | Target Completion Date: | 2021-02-03 | Program: | 1323000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: | 100% | No. of Persons: | 2 | Plan On-going | Plan On-going | Plan On-going | Plan On-going | Plan On-going | Suspended 10/1/2020
[7 empty] | Project Engineer: | Obar | Revised Completion Date: |  | Allotment: | 1323000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 44
[7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual: | 68.83%
[7 empty] | Duration: | 90 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | -31.17%
[7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
[7 empty] | Date Started: | 2020-06-15
ROAD ID 031 - Tuganay - Taba (Phase I) |  | 20% DF CY 2020 | Rehabilitation |  | km |  | Project Cost: | 507500 | Target Completion Date: | 2020-06-17 | Program: | 507500 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: | 100% | No. of Persons: | 2 | Plan On-going | Plan On-going | Plan On-going | Plan On-going | Plan On-going | Suspended 6/13/2020
[7 empty] | Project Engineer: | Obar | Revised Completion Date: | 2020-08-21 | Allotment: | 507500 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 44
[7 empty] | Implementor: | PEO | No. of days suspended: | 65 | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual: | 68.87%
[7 empty] | Duration: | 30 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | -31.13%
[7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
[7 empty] | Date Started: | 2020-05-18
Jct. Highway - Guadalupe - Bdry. Tagum (Phase I) |  | 20% DF CY 2020 | Rehabilitation |  | km |  | Project Cost: | 910000 | Target Completion Date: | 2020-08-06 | Program: | 910000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: | 3.2% | No. of Persons: | 2 | Suspended June 13, 2020 due to unavailability of heavy equipment | Plan On-going | Plan On-going | Plan On-going | Plan On-going | Suspended June 13, 2020 due to unavailability of heavy equipment
[7 empty] | Project Engineer: | Obar | Revised Completion Date: |  | Allotment: | 910000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 52
[7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual: | 1.2%
[7 empty] | Duration: | 80 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | -2%
[7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
[7 empty] | Date Started: | 2020-05-18
Sitio Malaga - Tibulao (Phase I) |  | 20% DF CY 2020 | Rehabilitation |  | km |  | Project Cost: | 350000 | Target Completion Date: | 2020-06-17 | Program: | 350000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: | 3.5% | No. of Persons: | 2 | Plan On-going | Plan On-going | Plan On-going | Plan On-going | Plan On-going | Suspended June 13, 2020 due to unavailability of heavy equipment
[7 empty] | Project Engineer: | Obar | Revised Completion Date: |  | Allotment: | 350000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 44
[7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual: | 1.2%
[7 empty] | Duration: | 30 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | -2.3%
[7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
[7 empty] | Date Started: | 2020-05-18
Dujali - Pawas - San Vicente (Phase I) |  | 20% DF CY 2020 | Rehabilitation |  | km |  | Project Cost: | 525000 | Target Completion Date: | 2020-07-02 | Program: | 525000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: | 6.5% | No. of Persons: | 2 | Plan On-going | Plan On-going | Plan On-going | Plan On-going | Plan On-going | PTemporarily Suspended June 13, 2020 due to unavailability of heavy equipment
[7 empty] | Project Engineer: | Obar | Revised Completion Date: |  | Allotment: | 525000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 42
[7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual: | 1.2%
[7 empty] | Duration: | 45 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | -5.3%
[7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
[7 empty] | Date Started: | 2020-05-18
Fd. Rd. 2 - Sto. Tomas - Magwawa (Phase I) |  | 20% DF CY 2020 | Rehabilitation |  | km |  | Project Cost: | 300000 | Target Completion Date: | 2020-06-17 | Program: | 300000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: | 100% | No. of Persons: | 3 | Plan On-going | Plan On-going | Plan On-going | Plan On-going | Plan On-going | Suspended 10/15/2020
[7 empty] | Project Engineer: | Obar | Revised Completion Date: | 10/31/2020 | Allotment: | 300000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 66
[7 empty] | Implementor: | PEO | No. of days suspended: | 80 | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual: | 61.3%
[7 empty] | Duration: | 30 | No. of days extended: | 56 |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | -38.7%
[7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
[7 empty] | Date Started: | 2020-05-18
Jct,. Bdry. Tagum- Talomo (Phase I) |  | 20% DF CY 2020 | Rehabilitation |  | km |  | Project Cost: | 1400000 | Target Completion Date: | 2020-09-15 | Program: | 1400000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: | 41.2% | No. of Persons: | 4 | POW for approval with the Governor | POW for approval with the Governor | POW for approval with the Governor | POW for approval with the Governor | POW for approval with the Governor | Suspended June 13, 2020
[7 empty] | Project Engineer: | Obar | Revised Completion Date: |  | Allotment: | 1400000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 88
[7 empty] | Implementor: | Admin | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual: | 39.6%
[7 empty] | Duration: | 120 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | -1.6%
[7 empty] | Date Allotment Released: |  | Date completed:
[7 empty] | Date Started: | 2020-05-18
Rehab. Of Various Local Roads @ Tagum City |  | 20% Development Fund CY 2020 | Rehabilitaion |  | km | Admin | Project Cost: | 2518182 | Target Completion Date: | 2020-10-20 | Program: | 2518182 | Planned: | 48.18% | Planned: | 48.18% | Planned: | 87.52% | Planned: | 87.52% | Planned: | 98.14% | No. of Persons: | 8 | On-going | On-going | On-going | On-going | On-going | On-going
[7 empty] | Project Engineer: | Bataller | Revised Completion Date: |  | Allotment: | 2518182 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 120
[7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: | 48.18% | Actual: | 48.18% | Actual: | 87.65% | Actual: | 87.65% | Actual: | 84.78%
[7 empty] | Duration: | 155 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0.13% | Slippage: | 0.13% | Slippage: | -13.36%
[7 empty] | Date Allotment Released: |  | Date completed:
[7 empty] | Date Started: | 2020-05-18
Rehab. Of Various Local Roads @ Asuncion |  | 20% Development Fund CY 2020 | Rehabilitaion |  | km | Admin | Project Cost: | 2518182 | Target Completion Date: | 2020-10-20 | Program: | 2518182 | Planned: | 37.83% | Planned: | 37.83% | Planned: | 37.83% | Planned: | 37.83% | Planned: | 88.98% | No. of Persons: | 12 | On-going | On-going | On-going | On-going | On-going | On-going
[7 empty] | Project Engineer: | Bataller | Revised Completion Date: |  | Allotment: | 2518182 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 372
[7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: | 37.82% | Actual: | 37.82% | Actual: | 37.82% | Actual: | 37.82% | Actual: | 45%
[7 empty] | Duration: | 155 | No. of days extended: |  |  |  | Slippage: | -0.01% | Slippage: | -0.01% | Slippage: | -0.01% | Slippage: | -0.01% | Slippage: | -43.98%
[7 empty] | Date Allotment Released: |  | Date completed:
[7 empty] | Date Started: | 2020-05-18
Rehab. Of Various Local Roads @ Kapalong |  | 20% Development Fund CY 2020 | Rehabilitaion |  | km | Admin | Project Cost: | 2518182 | Target Completion Date: | 2020-10-07 | Program: | 2518182 | Planned: | 18.24% | Planned: | 36.22% | Planned: | 91.3% | Planned: | 76.61% | Planned: | 100% | No. of Persons: | 12 | On-going | On-going | On-going | On-going | On-going | On-going
[7 empty] | Project Engineer: | Bataller | Revised Completion Date: |  | Allotment: | 2518182 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 180
[7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: | 18.24% | Actual: | 36.22% | Actual: | 91.28% | Actual: | 76.61% | Actual: | 81.61%
[7 empty] | Duration: | 84 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | -0.02% | Slippage: | 0% | Slippage: | -18.39%
[7 empty] | Date Allotment Released: |  | Date completed:
[7 empty] | Date Started: | 2020-07-15
Rehab. Of Various Local Roads @ New Corella |  | 20% Development Fund CY 2020 | Rehabilitaion |  | km | Admin | Project Cost: | 2518182 | Target Completion Date: | 2020-10-21 23:59 | Program: | 2518182 | Planned: |  | Planned: | 35.54% | Planned: |  | Planned: |  | Planned: | 100% | No. of Persons: | 13 | POW on process | On-going | POW on process | POW on process | POW on process | On-going
[7 empty] | Project Engineer: | Bataller | Revised Completion Date: |  | Allotment: | 2518182 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 403
[7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: | 15.46% | Actual: |  | Actual: |  | Actual: | 79.92%
[7 empty] | Duration: | 80 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | -20.08% | Slippage: | 0% | Slippage: | 0% | Slippage: | -20.08%
[7 empty] | Date Allotment Released: |  | Date completed:
[7 empty] | Date Started: | 2020-08-03
Rehab. Of Various Local Roads @ San Isidro |  | 20% Development Fund CY 2020 | Rehabilitaion |  | km | Admin | Project Cost: | 2518182 | Target Completion Date: | 2020-10-21 23:59 | Program: | 2518182 | Planned: |  | Planned: | 35.54% | Planned: | 73.27% | Planned: | 73.27% | Planned: | 100% | No. of Persons: | 10 | For implementation | On-going | On-going | On-going | On-going | On-going
[7 empty] | Project Engineer: | Bataller | Revised Completion Date: |  | Allotment: | 2518182 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 150
[7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: | 35.54% | Actual: | 73.26% | Actual: | 73.26% | Actual: | 79.92%
[7 empty] | Duration: | 80 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | -0.01% | Slippage: | -0.01% | Slippage: | -20.08%
[7 empty] | Date Allotment Released: |  | Date completed:
[7 empty] | Date Started: | 2020-08-03
Rehab. Of Various Local Roads @ Talaingod |  | 20% Development Fund CY 2020 | Rehabilitaion |  | km | Admin | Project Cost: | 2518182 | Target Completion Date: | 2020-12-12 | Program: | 2518182 | Planned: | 10.3% | Planned: | 10.3% | Planned: | 51.1% | Planned: | 51.1% | Planned: | 91.91% | No. of Persons: | 9 | On-going | On-going | On-going | On-going | On-going | On-going
[7 empty] | Project Engineer: | Bataller | Revised Completion Date: |  | Allotment: | 2518182 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 135
[7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: | 10.3% | Actual: | 10.3% | Actual: | 51.11% | Actual: | 51.11% | Actual: | 91.91%
[7 empty] | Duration: | 150 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0.01% | Slippage: | 0.01% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
[7 empty] | Date Started: | 2020-07-15
Rehab. Of Various Local Roads @ Panabo City |  | 20% DF CY 2020 | Rehabilitation |  | km |  | Project Cost: | 2518182 | Target Completion Date: | 2020-10-12 | Program: | 2518182 | Planned: |  | Planned: |  | Planned: |  | Planned: | 75% | Planned: | 75% | No. of Persons: | 5 | Abstract # 0420201633 - Billboard; Abstract 0520201661 - hardware | Abstract # 0420201633 - Billboard; Abstract 0520201661 - hardware | Abstract # 0420201633 - Billboard; Abstract 0520201661 - hardware | On-going | On-going | On-going
[7 empty] | Project Engineer: | Gamad/Clar | Revised Completion Date: |  | Allotment: | 2518182 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 110
[7 empty] | Implementor: | Admin | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: | 80% | Actual: | 80%
[7 empty] | Duration: | 150 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 5% | Slippage: | 5%
[7 empty] | Date Allotment Released: |  | Date completed:
[7 empty] | Date Started: | 2020-05-15
Rehab. Of Various Local Roads @ B.E Dujali |  | 20% DF CY 2020 | Rehabilitation |  | km |  | Project Cost: | 2518182 | Target Completion Date: | 2020-12-13 | Program: | 2518182 | Planned: |  | Planned: |  | Planned: |  | Planned: | 35% | Planned: | 35% | No. of Persons: | 4 | Purchase Request # 20053256 - Hardware; PR # 20053255 - Billboard | Purchase Request # 20053256 - Hardware; PR # 20053255 - Billboard | Purchase Request # 20053256 - Hardware; PR # 20053255 - Billboard | On-going | On-going | On-going
[7 empty] | Project Engineer: | Gamad/Clar | Revised Completion Date: |  | Allotment: | 2518182 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 88
[7 empty] | Implementor: | Admin | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: | 52% | Actual: | 52%
[7 empty] | Duration: | 150 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 17% | Slippage: | 17%
[7 empty] | Date Allotment Released: |  | Date completed:
[7 empty] | Date Started: | 2020-07-16
Rehab. Of Various Local Roads @ Carmen |  | 20% DF CY 2020 | Rehabilitation |  | km |  | Project Cost: | 2518182 | Target Completion Date: | 2020-10-15 | Program: | 2518182 | Planned: |  | Planned: |  | Planned: |  | Planned: | 35% | Planned: | 35% | No. of Persons: | 3 | Abstract # 0420201633 - Billboard; Abstract 0520201661 - hardware | Abstract # 0420201633 - Billboard; Abstract 0520201661 - hardware | Abstract # 0420201633 - Billboard; Abstract 0520201661 - hardware | On-going | On-going | On-going
[7 empty] | Project Engineer: | Gamad/Clar | Revised Completion Date: |  | Allotment: | 2518182 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 66
[7 empty] | Implementor: | Admin | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: | 52% | Actual: | 52%
[7 empty] | Duration: | 150 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 17% | Slippage: | 17%
[7 empty] | Date Allotment Released: |  | Date completed:
[7 empty] | Date Started: | 2020-05-18
Rehab. Of Various Local Roads @ Sto. Tomas |  | 20% DF CY 2020 | Rehabilitation |  | km |  | Project Cost: | 2518182 | Target Completion Date: | 2020-12-13 | Program: | 2518182 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: | 60% | No. of Persons: | 3 | Plan On-going | Plan On-going | Plan On-going | Plan On-going | Plan On-going | On-going
[7 empty] | Project Engineer: | Gamad/Clar | Revised Completion Date: |  | Allotment: | 2518182 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 66
[7 empty] | Implementor: | Admin | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual: | 65%
[7 empty] | Duration: | 150 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 5%
[7 empty] | Date Allotment Released: |  | Date completed:
[7 empty] | Date Started: | 2020-07-16
Improvement and Desiltation of Ising Creek |  | 5% Calamity Fund CY 2020 | Desiltation |  | ln.m |  | Project Cost: | 2000000 | Target Completion Date: | 2020-10-24 | Program: | 2000000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: | 100% | No. of Persons: |  | Abstract # 0420201637; 0520201662 | Abstract # 0420201637; 0520201662 | Abstract # 0420201637; 0520201662 | On-going (Resumption date 10/23/2020) | On-going (Resumption date 10/23/2020) | On-going
[7 empty] | Project Engineer: | Toquero | Revised Completion Date: |  | Allotment: | 2000000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: | Admin | No. of days suspended: | 99 | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: | 1.21% | Actual: | 50%
[7 empty] | Duration: | 100 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 1.21% | Slippage: | -50%
[7 empty] | Date Allotment Released: |  | Date completed:
[7 empty] | Date Started: | 2020-07-16
Desiltation of Buhang Creek, Anibongan, Carmen |  | 5% Calamity Fund CY 2020 | Desiltation |  | ln.m |  | Project Cost: | 2130206 | Target Completion Date: | 2020-10-18 | Program: | 2130206 | Planned: |  | Planned: |  | Planned: |  | Planned: | 50% | Planned: | 100% | No. of Persons: | 4 | Abstract # 0520201657; 0420201626 | Abstract # 0520201657; 0420201626 | Abstract # 0520201657; 0420201626 | On-going | On-going | On-going
[7 empty] | Project Engineer: | Toquero | Revised Completion Date: |  | Allotment: | 2130206 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 88
[7 empty] | Implementor: | Admin | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: | 50% | Actual: | 55%
[7 empty] | Duration: | 94 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | -45%
[7 empty] | Date Allotment Released: |  | Date completed:
[7 empty] | Date Started: | 2020-07-16
Improvement of Mabaus - Salvacion Provincial Road Continuing Road Opening |  | 5% Calamity Fund CY 2020 | Improvement |  | ln.m |  | Project Cost: | 500000 | Target Completion Date: | 2020-08-11 | Program: | 500000 | Planned: |  | Planned: |  | Planned: |  | Planned: | 100% | Planned: | 100% | No. of Persons: |  | Plan On-going | Plan On-going | Plan On-going | Suspended due to unavailability of equipment, area under stabilization | Suspended due to unavailability of equipment, area under stabilization | On-going
[7 empty] | Project Engineer: | Toquero | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: | Admin | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: | 1.3% | Actual: | 30%
[7 empty] | Duration: | 26 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | -98.7% | Slippage: | -70%
[7 empty] | Date Allotment Released: |  | Date completed:
[7 empty] | Date Started: | 2020-07-16
Note on D257: Cerela Montes: Previously 20% DF CY 2019
Note on D269: chai: Previously Perimeter Fence of Day Care Center I & II, Nanyo, Panabo City (20% Development Fund CY 2018 (STIMULUS 2018)
Note on D275: chai: 20% DF CY 2019
Note on D281: chai: 20% DF CY 2019
Note on AF353: Cerela Montes: suspended 10/05/20
Note on AF359: Cerela Montes:
Note on J365: chai: 20% Development Fund CY 2018 Variation Order - 21,512,501.5 - 1,408,112.95

## Annual CY 2020 (For Impl
|  |  |  | 0 |  |  |  | 275063816.87 |  |  |  | 550127633.74 | [11 empty] | 0
` | ECONOMIC (INFRASTRUCTURE DEV'T. PROGRAM)
OFFICE/AGENCY: | PROVINCIAL ENGINEER'S OFFICE
AREA: | 1ST ENGINEERING DISTRICT - COMPLETED, ON-GOING AND FOR IMPLEMENTATION PROJECTS | [7 empty] | Total extended
#REF!
#REF!
NAME OF PROJECT |  | SOURCE OF FUND | TYPE OF PROJECT | PHYSICAL TARGET (DESCRIPTION) |  | MODE OF IMPLEMENTATION | PROJECT DATA |  |  |  | FINANCIAL |  | PHYSICAL ACCOMPLISHMENT (JULY) |  | PHYSICAL ACCOMPLISHMENT (AUGUST) |  | PHYSICAL ACCOMPLISHMENT (SEPTEMBER) |  | PHYSICAL ACCOMPLISHMENT (OCTOBER) |  | PHYSICAL ACCOMPLISHMENT |  | EMPLOYMENT GENERATED |  | REMARKS (JULY) | REMARKS (AUGUST) | REMARKS (SEPTEMBER) | REMARKS (OCTOBER | REMARKS (NOVEMBER) | REMARKS
Inst. of transformer and accessories, Brgy. Kinawitnon |  | PRDP CY 2016 | Electrification |  |  | Admin | Project Cost: | 150000 | Target Completion Date: |  | Program: | 150000 | Planned: |  | No. of Persons: |  | Purchase Order # 2019103228 - Transformer; Purchase Order # 2019102931 - Billboard; Purchase Order # 2019103227 - Lumber |  |  |  | Planned: |  | No. of Persons: | [6 empty] | For verification
[7 empty] | Project Engineer: | Porras | Revised Completion Date: |  | Allotment: | 150000 | Revised: |  | No. of Man-days: | [5 empty] | Revised: |  | No. of Man-days:
[7 empty] | Implementor: | Contract | No. of days suspended: |  | Disbursement: |  | Actual: | [7 empty] | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | [6 empty] | Slippage: | 0%
[7 empty] | Date Allotment Released: | 2018-07-31 | Date completed:
Date Started:
Construction of Concrete Pavement, Tibulao, Carmen |  | 20% DF CY 2017 (STIMULUS) | Pavement |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Fund already transferred at Municipality of Talaingod with ChecK No. 2445181 and OR # 7955667, dated March 16, 2018 . Amended from Electrification @ Prk. 1A-Prk. 5A) | On-going (Implemented by MLGU, since transfer of fund ) | On-going (Implemented by MLGU, since transfer of fund ) | Hold in abeyance | Hold in abeyance | Hold in abeyance
[7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Agricultural Productivity Support Project-Fishing Net with Pump Boat, Tambo,IGACOS |  | OPPAP-PAMANA CY 2017 |  |  |  |  | Project Cost: | 1500000 | Target Completion Date: |  | Program: | 1500000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | For PR | For PR | For PR | For PR | For PR | PR on process (Waiting for the 2nd tranche)
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 1500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Agricultural Productivity Support Project-Fishing Net with Pump Boat, Limao, Peñaplata District, IGACOS |  | OPPAP-PAMANA CY 2017 |  |  |  |  | Project Cost: | 1500000 | Target Completion Date: |  | Program: | 1500000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | For PR | For PR | For PR | For PR | For PR | PR on process (Waiting for the 2nd tranche)
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 1500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Agricultural Productivity Support Project-Fishing Net with Pump Boat, Kinawitnon, Babak District, IGCAOS |  | OPPAP-PAMANA CY 2017 |  |  |  |  | Project Cost: | 1500000 | Target Completion Date: |  | Program: | 1500000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | For PR | For PR | For PR | For PR | For PR | PR on process (Waiting for the 2nd tranche)
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 1500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Const. of Trading Post, Storage Building with (1) unit Hauling Truck, Brgy. Pandapan |  | OPPAP-PAMANA CY 2017 | Building |  | sq.m |  | Project Cost: | 3975000 | Target Completion Date: | 0 | Program: | 3975000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Abstract 1220194004 (Tagum Builders);PO # 2019102828 - Truck | Abstract 1220194004 (Tagum Builders);PO # 2019102828 - Truck | Abstract 1220194004 (Tagum Builders);PO # 2019102828 - Truck | Waiting for approval of Notice of Award | Waiting for approval of Notice of Award | PR on process (Waiting for the 2nd tranche)
[7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 3975000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: | CY 2017 | Date completed:
Date Started:
Cattle Production- Brgy. Tiburcia, Gupitan and Semong, Kapalong |  | OPPAP-PAMANA CY 2017 | Building |  | sq.m |  | Project Cost: | 1500000 | Target Completion Date: |  | Program: | 1500000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | For RE-PR | For RE-PR | For RE-PR |  |  | Procurement on process. Waiting for the 2nd tranch.
[7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 1500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Cattle Production, Brgy. Palma Gil, Brgy. Sto. Nino, Brgy. Dagohoy, Talaingod, Davao del Norte |  | OPPAP-PAMANA CY 2017 | Building |  | sq.m |  | Project Cost: | 1500000 | Target Completion Date: |  | Program: | 1500000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | For RE-PR | For RE-PR | For RE-PR |  |  | Procurement on process. Waiting for the 2nd tranch.
[7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 1500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Installation of potable water System at Purok Nangka, Pandapan, Tagum City |  | 20% DF CY 2018 | Water System |  |  | Admin | Project Cost: | 1125000 | Target Completion Date: |  | Program: | 1125000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Waiting for deed of donation. Follow-up letter was already issued | Waiting for deed of donation. Follow-up letter was already issued | Plan preparation on-going | Plan preparation on-going | Plan preparation on-going | Plan preparation on-going
[7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 1125000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Rehab./Impv't. of San Vicente Water System, Asuncion |  | 20% DF CY 2018 | Water System |  |  | Admin | Project Cost: | 1125000 | Target Completion Date: |  | Program: | 1125000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Waiting for deed of donation. Follow-up letter was already issued | Waiting for deed of donation. Follow-up letter was already issued | Plan preparation on-going | Plan preparation on-going | Plan preparation on-going | Procurement on process.
[7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 1125000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: | 2018-10-26 | Date completed:
Date Started:
Impv't. of Water System, Brgy. Poblacion, Kaputian (Level II) |  | 20% DF CY 2018 | Water System |  |  | Admin | Project Cost: | 1250000 | Target Completion Date: |  | Program: | 1250000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Waiting for deed of donation. Follow-up letter was already issued | Waiting for deed of donation. Follow-up letter was already issued | Plan preparation on-going |  |  | Procurement on process.
[7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 1250000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Water System at brgy. Malativas, Panabo City |  | 20% DF CY 2018 | Water System |  |  | Admin | Project Cost: | 1250000 | Target Completion Date: |  | Program: | 1250000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | For preparation of POW & Plan c/o PDPM - POSSIBLE TRANSFER OF SITE SUBJECT FOR TRANSFER OF LOCATION . NO DEED OF DONATION | For preparation of POW & Plan c/o PDPM - POSSIBLE TRANSFER OF SITE SUBJECT FOR TRANSFER OF LOCATION . NO DEED OF DONATION | For preparation of POW & Plan c/o PDPM - POSSIBLE TRANSFER OF SITE SUBJECT FOR TRANSFER OF LOCATION . NO DEED OF DONATION | For preparation of POW & Plan c/o PDPM - POSSIBLE TRANSFER OF SITE SUBJECT FOR TRANSFER OF LOCATION . NO DEED OF DONATION | For preparation of POW & Plan c/o PDPM - POSSIBLE TRANSFER OF SITE SUBJECT FOR TRANSFER OF LOCATION . NO DEED OF DONATION | For preparation of POW & Plan c/o PDPM - POSSIBLE TRANSFER OF SITE SUBJECT FOR TRANSFER OF LOCATION . NO DEED OF DONATION
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 1250000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Construction of IP Tribal Council of Women at Brgy. Camansa, Asuncion |  | 20% DF CY 2018 | Building |  | sq.m | Admin | Project Cost: | 560000 | Target Completion Date: |  | Program: | 560000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Purchase Request # 20032714 | PR cancelled due to To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | PR cancelled due to To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | PR cancelled due to To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | PR cancelled due to To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | PR cancelled due to To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
[7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 560000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Const. of New Brgy. Stage, San Pedro, Panabo City |  | 20% DF CY 2018 (STIMULUS) | Building |  | sq.m | Contract | Project Cost: | 500000 | Target Completion Date: | 0 | Program: | 500000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Plan and POW Preparation for preparation | Plan and POW Preparation for preparation | Plan and POW Preparation Ongoing | Plan and POW Preparation Ongoing | Plan and POW Preparation Ongoing | Plan and POW Preparation Ongoing
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Const. of Multi-Purpose Bldg. Sto. Nino, Panabo City |  | 20% DF CY 2018 (STIMULUS) | Court |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | PR # 20032818 | PR # 20032818 | Procurement on process | Hold in abeyance | Hold in abeyance | Hold in abeyance
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Water System From Prk. 6 - Prk. 2 - Prk. 5A, Tagbay, IGCS |  | 20% DF CY 2018 (STIMULUS) | Water System |  |  | Admin | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | For Implementation | For Implementation | For Implementation | For Implementation | For Implementation | For Implementation
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Drilling of Water System, Linusotan, IGCS |  | 20% DF CY 2018(STIMULUS) | Water System |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Grouted Riprap on Embankment Sto. Ñino, Talaingod |  | 20% DF CY 2018 (STIMULUS) | Embankment |  |  |  | Project Cost: |  | Target Completion Date: |  | Program: | 0 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | PROJECT Was funded by LGU, Kapalong | PROJECT Was funded by LGU, Kapalong | PROJECT Was funded by LGU, Kapalong | Procurment on process | Procurment on process | Procurment on process
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 0 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Rehabilitation of Local Roads at Dalisay-Manay Road Section, Panabo City |  | SB # 4 CY 2019 | Road |  |  | Admin | Project Cost: | 246100 | Target Completion Date: |  | Program: | 246100 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | For implementation | For implementation | For implementation | For implementation | For implementation | For implementation
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 246100 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Jct. Highway Gabuyan - Semong - Dagohoy |  | 20% DF CY 2019 | Road Rehabilitation | 4.34 |  | Admin | Project Cost: | 2492000 | Target Completion Date: |  | Program: | 2492000 | Planned: |  | Planned: | 52.32% | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | For implementation (Waiting for the delivery of geo-grid materials. An approved request letter dated Dec. 3, 2019 for the extension of 50 days from Provincial Administrator Engr. Rabanoz is on file | Suspended due to continous rain. Waiting for the stability of swamp area. | Suspended due to continous rain. Waiting for the stability of swamp area. |  |  | For implementation
[7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 2492000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: | Admin | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: | 52.32% | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Lower Asuncion - Upper Asuncion |  | 20% DF CY 2019 | Road Rehabilitation | 1.02 | km | Admin | Project Cost: |  | Target Completion Date: |  | Program: | 0 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. |  |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 0 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Construction of PWS, Brgy. Brgy. Kiotoy, Panabo City |  | 20% DF CY 2019 | Georesistivity |  |  |  | Project Cost: | 62500 | Target Completion Date: |  | Program: | 62500 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 62500 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Construction of PWS, Brgy. Linosutan, Talikud, IGCS |  | 20% DF CY 2019 | Water System |  |  |  | Project Cost: | 62500 | Target Completion Date: |  | Program: | 62500 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Procurement on process | Procurement on process | Procurement on process | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No 1 | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No 1 | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No 1
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 62500 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Construction of PWS, Brgy. San Miguel, Samal, IGCS |  | 20% DF CY 2019 | Water System |  |  |  | Project Cost: | 62500 | Target Completion Date: |  | Program: | 62500 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 62500 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Construction of PWS, Cacao, Panabo City |  | 20% DF CY 2019 | Water System |  |  |  | Project Cost: | 62500 | Target Completion Date: |  | Program: | 62500 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | For cancellation. Purchase of Geo-resistivity equipment but procurement still on process | For cancellation. Purchase of Geo-resistivity equipment but procurement still on process | For amendment indicating phase 2 since the project title is the same with stimulus project (letter will be submitted by Mr. Amamio-focal person for water system for explanation) | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 62500 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Const. of PWS Mamalian, San Isidro |  | 20% DF CY 2019 | Water System |  |  | Admin | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | For declaration of savings because the spring water source is not feasible for development. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
[7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Const. of PWS Sagayen, San Isidro |  | 20% DF CY 2019 | Water System |  |  | Admin | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. |  |  | For implementation
[7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Construction of PWS, Brgy. Purok 7-A and B, Brgy. Capungagan, kapalong |  | 20% DF CY 2019 | Water System |  |  | Admin | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. |  |  | For implementation
[7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Construction of PWS Level II in Purok 2, Pag-Asa, kapalong |  | 20% DF CY 2019 | Potable Water System |  |  | Admin | Project Cost: | 500000 | Target Completion Date: | 0 | Program: | 500000 | Planned: | 100% | Planned: | 100% | Planned: | 100% | Planned: |  | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. |  |  | For implementation
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: | 100% | Revised: | 81.57% | Revised: | 81.57% | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: | 72.68% | Actual: | 76.39% | Actual: | 76.39% | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | -27.32% | Slippage: | -5.179% | Slippage: | -5.179% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Impv't. of Potable Water System, Tagbitan-ag, Samal Dist. |  | 20% DF CY 2019 | Water System |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | For implementation | For implementation | For implementation | For implementation | For implementation | For implementation
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: | 2019-06-19 | Date completed:
Date Started:
Impv't. of Potable Water System, San Antonio, babak, IGCS |  | 20% DF CY 2019 | Water System |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: | 2019-06-25 | Date completed:
Date Started:
Construction of PWS, Brgy. Buenavista, Panabo City |  | 20% DF CY 2019 | Water System |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | For implementation | For implementation | For implementation | For implementation | For implementation | For implementation
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: | June 19 ,2019 | Date completed:
Date Started:
Construction of PWS, Brgy. Brgy. Kiotoy, Panabo City |  | 20% DF CY 2019 | Water System |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Rehab. of PWS, Brgy. San Miguel, Babak, IGCS |  | 20% DF CY 2019 | Water System |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Construction of PWS, Brgy. Cacao, Panabo City |  | 20% DF CY 2019 | Water System |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | For cancellation. Purchase of Geo-resistivity equipment but procurement still on process | For cancellation. Purchase of Geo-resistivity equipment but procurement still on process | For amendment indicating phase 2 since the project title is the same with stimulus project (letter will be submitted by Mr. Amamio-focal person for water system for explanation) | For amendment indicating phase 2 since the project title is the same with stimulus project (letter will be submitted by Mr. Amamio-focal person for water system for explanation) | For amendment indicating phase 2 since the project title is the same with stimulus project (letter will be submitted by Mr. Amamio-focal person for water system for explanation) | For amendment indicating phase 2 since the project title is the same with stimulus project (letter will be submitted by Mr. Amamio-focal person for water system for explanation)
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Rehabilitation of Potable Water System, Brgy. Pangubatan, kaputian Dist. IGCS |  | 20% DF CY 2019 | Water System |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | For implementation | Declared as savings in the AIP 2nd Revision to fund for the Construction of PWS in Brgy Linusotan, Kaputian Dist. IGACOS (Project was funded by OPAPP CY 2018) | Declared as savings in the AIP 2nd Revision to fund for the Construction of PWS in Brgy Linusotan, Kaputian Dist. IGACOS (Project was funded by OPAPP CY 2018) | Declared as savings in the AIP 2nd Revision to fund for the Construction of PWS in Brgy Linusotan, Kaputian Dist. IGACOS (Project was funded by OPAPP CY 2018) | Declared as savings in the AIP 2nd Revision to fund for the Construction of PWS in Brgy Linusotan, Kaputian Dist. IGACOS (Project was funded by OPAPP CY 2018) | Declared as savings in the AIP 2nd Revision to fund for the Construction of PWS in Brgy Linusotan, Kaputian Dist. IGACOS (Project was funded by OPAPP CY 2018)
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Rural Electrification at Sitio Sagrada, Pob. Kaputian, IGCS |  | 20% DF CY 2019 | Electrification |  |  |  | Project Cost: | 1000000 | Target Completion Date: |  | Program: | 1000000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Purchase Request # 19031251 | Purchase Request # 19031251 | For implementation | For implementation | For implementation | For implementation
[7 empty] | Project Engineer: | Buena | Revised Completion Date: |  | Allotment: | 1000000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Const. of Multi-Purpose Hall Center (Cultural Heritage in Ancestral Domain of Ata-Manobo) |  | 20% DF CY 2019 | Building |  |  | Admin | Project Cost: | 3000000 | Target Completion Date: |  | Program: | 3000000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Fund re-aligned to GIDAS projects | Fund re-aligned to GIDAS projects | Fund re-aligned to GIDAS projects |  |  | Fund re-aligned to GIDAS projects
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 3000000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Construction of Abilidad Training Center, Gov't. Center, Mankilam, Tagum City |  | 20% DF CY 2019 | Building |  |  |  | Project Cost: | 7000000 | Target Completion Date: |  | Program: | 7000000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Fund re-aligned to GIDAS projects | Fund re-aligned to GIDAS projects | Fund re-aligned to GIDAS projects | Fund re-aligned to GIDAS projects | Fund re-aligned to GIDAS projects | Fund re-aligned to GIDAS projects
[7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 7000000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Const. of Multi-Purpose Covered Court/Evacuation Center Ph. I, Duterte St., Poblacion, New Corella |  | 20% DF CY 2019 | Building |  | sq.m | Admin | Project Cost: | 2000000 | Target Completion Date: | 0 | Program: | 2000000 | Planned: | 84.4% | Planned: | 100% | Planned: | 100% | Planned: |  | Planned: |  | No. of Persons: |  | On-going | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. |  |  | Procurement on process
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 2000000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: | 84.4% | Actual: | 100% | Actual: | 100% | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Impv't./Beautification of Brgy. Grounds, Quezon, Panabo City |  | 20% DF CY 2019 (STIMULUS | Ground dev't. |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Re aligned to other stimulus projects that needs additional funding | Re aligned to other stimulus projects that needs additional funding | Re aligned to other stimulus projects that needs additional funding | Re aligned to other stimulus projects that needs additional funding | Re aligned to other stimulus projects that needs additional funding | Re aligned to other stimulus projects that needs additional funding
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Desilting of Canal, New Pandan, Panabo City |  | 20% DF CY 2019 (STIMULUS | Desiltation |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
[7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: |  | Slippage: |  | Slippage:
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Const. of 2 Storey Multi-Purpose Hall Ph. 3 (Brgy. Hall), Poblacion, New Corella |  | SB NO. 4 CY 2019 (STIMULUS) | Building | 42 | sq.m | Admin | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: | 100% | Planned: | 100% | Planned: | 100% | Planned: | 100% | Planned: |  | No. of Persons: |  | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: | 100% | Actual: | 100% | Actual: | 100% | Actual: | 100% | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Const. of Evacuation Center, Bobongon, Sto. Tomas |  | 20% DF CY 2019 (STIMULUS | Building |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: | 100% | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Re aligned to other stimulus projects that needs additional funding | Re aligned to other stimulus projects that needs additional funding | Re aligned to other stimulus projects that needs additional funding | Re aligned to other stimulus projects that needs additional funding | Re aligned to other stimulus projects that needs additional funding | Re aligned to other stimulus projects that needs additional funding
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: | 100% | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Rehab. Of Water System at Purok Cabang & Mangga , Pinamuno, San Isidro |  | 20% DF CY 2019 (STIMULUS) | Water System |  |  | Contract | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | PO# 2020010025 (RLHV) | PO# 2020010025 (RLHV) | PO# 2020010025 (RLHV) | PO# 2020010025 (RLHV) | PO# 2020010025 (RLHV) | PO# 2020010025 (RLHV)
[7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: | 2019-12-06 | Date completed:
Date Started:
Rehab. Of Evacuation Center, Libuak, IGCS |  | 20% DF CY 2019 (STIMULUS | Building |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | For implementation | For implementation | For implementation | For implementation | For implementation | For implementation
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: | 2019-05-29 | Date completed:
Date Started:
Electrification at Sitio Trinidad, Bandera, IGCS |  | 20% DF CY 2019 (STIMULUS | Electrification |  |  | Contract | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | PO #2020072352 - (3E Electrical Sales & Services) | PO #2020072352 - (3E Electrical Sales & Services) | Re-bid due to non-compliance in requirement | Re-bid due to non-compliance in requirement | Re-bid due to non-compliance in requirement | Re-bid due to non-compliance in requirement
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: | 2019-03-25 | Date completed:
Date Started:
Electrificatio at Prk. 1,3,4, 6,7 & 8, Licup, IGCS |  | 20% DF CY 2019 (STIMULUS | Electrification |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | For implementation | For implementation | For implementation | For implementation | For implementation | For implementation
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: | 2019-02-20 | Date completed:
Date Started:
Rehab. Of Potable Water System, San Isidro, Babak, IGCS |  | 20% DF CY 2019 (STIMULUS | Water System |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | For implementation | For implementation | For implementation | For implementation | For implementation | For implementation
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: | 2019-06-19 | Date completed:
Date Started:
Rehab. Of Potable Water System, San Miguel, IGCS |  | 20% DF CY 2019 (STIMULUS | Water System |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | For implementation | For implementation | For implementation | For implementation | For implementation | For implementation
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: | 2019-02-28 | Date completed:
Date Started:
Const. of Water System Ph.II, San Remegio, IGCS |  | 20% DF CY 2019 (STIMULUS | Water System |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | For implementation | For implementation | For implementation | For implementation | For implementation | For implementation
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: | 2019-05-29 | Date completed:
Date Started:
Rehabilitation of Potable Water System, Brgy. Pangubatan, kaputian Dist. IGCS |  | 20% DF CY 2019 | Water System |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | For implementation | Declared as savings in the AIP 2nd Revision to fund for the Construction of PWS in Brgy Linusotan, Kaputian Dist. IGACOS (Project was funded by OPAPP CY 2018) | Declared as savings in the AIP 2nd Revision to fund for the Construction of PWS in Brgy Linusotan, Kaputian Dist. IGACOS (Project was funded by OPAPP CY 2018) | Declared as savings in the AIP 2nd Revision to fund for the Construction of PWS in Brgy Linusotan, Kaputian Dist. IGACOS (Project was funded by OPAPP CY 2018) | Declared as savings in the AIP 2nd Revision to fund for the Construction of PWS in Brgy Linusotan, Kaputian Dist. IGACOS (Project was funded by OPAPP CY 2018) | Declared as savings in the AIP 2nd Revision to fund for the Construction of PWS in Brgy Linusotan, Kaputian Dist. IGACOS (Project was funded by OPAPP CY 2018)
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Rural Electrification at Brgy. Poblacion, Kaputian, IGACOS ( Sitio Sagrada) |  | 20% DF CY 2019 | Electrification |  |  |  | Project Cost: | 1000000 | Target Completion Date: |  | Program: | 1000000 | Planned: | 43% | Planned: | 43% | Planned: | 43% | Planned: | 43% | Planned: |  | No. of Persons: |  | On-going | On-going | On-going | On-going | On-going | For implementation
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 1000000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: | 43% | Actual: | 43% | Actual: | 43% | Actual: | 43% | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Const. Of Multi-Purpose Hall, Cogon (Talicud), IGCS |  | 20% DF CY 2019 (STIMULUS | Building |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | For implementation | For implementation | For implementation | For implementation | For implementation | For implementation
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Rehab. Of Multi-Purpose Hall, Del Monte, IGCS |  | 20% DF CY 2019 (STIMULUS | Building |  |  | Admin | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Pending/ activity undertaken by DPWH | Pending/ activity undertaken by DPWH | Pending/ activity undertaken by DPWH | Pending/ activity undertaken by DPWH | Pending/ activity undertaken by DPWH | Pending/ activity undertaken by DPWH
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: | 2019-05-29 | Date completed:
Date Started:
Rehab. Of Health Center, New Visayas, Panabo City |  | 20% DF CY 2019 (STIMULUS | Building |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Re aligned to other stimulus projects that needs additional funding | Re aligned to other stimulus projects that needs additional funding | Re aligned to other stimulus projects that needs additional funding | Re aligned to other stimulus projects that needs additional funding | Re aligned to other stimulus projects that needs additional funding | Re aligned to other stimulus projects that needs additional funding
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Purchase of Lot Cemetery, San Roque, New Corella |  | SB No. 1 CY 2019 (STIMULUS) | Land |  |  |  | Project Cost: | 1500000 | Target Completion Date: |  | Program: | 1500000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | for fund transfer. Waiting for LGU documents. Liquidation of previous fund transfer for the water system project of LGU. | for fund transfer. Waiting for LGU documents. Liquidation of previous fund transfer for the water system project of LGU. | for fund transfer. Waiting for LGU documents. Liquidation of previous fund transfer for the water system project of LGU. | for fund transfer. Waiting for LGU documents. Liquidation of previous fund transfer for the water system project of LGU. | for fund transfer. Waiting for LGU documents. Liquidation of previous fund transfer for the water system project of LGU. | Lot already purchased by Brgy. San Roque, New Corella. For ammendment for new project of the same location. Resolution already submitted by Brgy. San Roque; Energization of Purok-3 Sitio Libas, Brgy. San Roque. POW preparation ongoing.
[7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 1500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Purchase of Lot Cemetery, Cambanogoy, Asuncion |  | SB No. 1 CY 2019 (STIMULUS) | Land |  |  |  | Project Cost: | 1500000 | Target Completion Date: |  | Program: | 1500000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | for fund transfer. Waiting for LGU documents. Liquidation of previous fund transfer for the water system project of LGU. | for fund transfer. Waiting for LGU documents. Liquidation of previous fund transfer for the water system project of LGU. | for fund transfer. Waiting for LGU documents. Liquidation of previous fund transfer for the water system project of LGU. | for fund transfer. Waiting for LGU documents. Liquidation of previous fund transfer for the water system project of LGU. | for fund transfer. Waiting for LGU documents. Liquidation of previous fund transfer for the water system project of LGU. | Documents for the fund transfer to be complied by the LGUs. Letter sent dated June 18, 2019 Follow up for the requirements last July 20, 2020
[7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 1500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Const. of FMR from Prk 1 to Sitio Magsaysay via Pundol & Prk 4, Patrocenio, New Corella |  | SB NO. 1 CY 2019 (STIMULUS) | Road |  |  |  | Project Cost: | 2000000 | Target Completion Date: |  | Program: | 2000000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
[7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 2000000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Const. of Drainage Canal from Prk. 3, 1-A, 2-A to Prk 1-B, Brgy Site (Ph. 2), Limbaan, New Corella |  | SB NO. 1 CY 2019 (STIMULUS) | Flood Control - Drainage |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | POW preparation on going c/o PDPM | POW preparation on going c/o PDPM | Abstract on Process Contractor: Royal Summit Infinity Dev't. Corp. | For implementation | For implementation | For implementation
[7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: | Royal Summit Infinity | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Const. of 2 Storey Multi-Purpose Hall Ph. 1 (Brgy. Hall), Poblacion, New Corella |  | SB No. 1 CY 2019 (STIMULUS) | Building |  | sq.m | Admin | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: | 100% | Planned: | 100% | Planned: | 100% | Planned: |  | Planned: |  | No. of Persons: |  | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1 | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1 | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: | 100% | Actual: | 100% | Actual: | 100% | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage:
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Impv't. of Potable Water System, Mambago-A, IGCS |  | SB NO. 3 CY 2019 | Water System |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | For Implementation | For Implementation | For Implementation | For Implementation | For Implementation | For Implementation
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: | 2019-09-10 | Date completed:
Date Started:
Construction of PWS, Brgy. Linusotan, Talikud, District, IGCS |  | SB NO. 3 CY 2019 | Water System |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Procurement on process | Procurement on process | Procurement on process | Procurement on process | Procurement on process | Procurement on process
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: | 2019-10-23 | Date completed:
Date Started:
Const. of Brgy. Health Center, Magugpo South, Tagum City |  | SB No. 4 CY 2019 (STIMULUS) | Building |  |  |  | Project Cost: | 1550000 | Target Completion Date: |  | Program: | 1550000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Amended in the AIP 3rd revision CY 2019 /SB No. 4 CY 2019 changing the total project cost to P1,550,000.00 | For implementation (Awarded to Royal Summit Infinity Dev't. Corp.), ; (Note: Additional Fund Php P1,050,000.00) | For implementation (Awarded to Royal Summit Infinity Dev't. Corp.), ; (Note: Additional Fund Php P1,050,000.00) | For implementation (Awarded to Royal Summit Infinity Dev't. Corp.), ; (Note: Additional Fund Php P1,050,000.00) | For implementation (Awarded to Royal Summit Infinity Dev't. Corp.), ; (Note: Additional Fund Php P1,050,000.00) | For implementation (Awarded to Royal Summit Infinity Dev't. Corp.), ; (Note: Additional Fund Php P1,050,000.00)
[7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 1550000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Completion of Brgy. Health Center, Maniki, Kapalong |  | SB No. 4 CY 2019 (STIMULUS) | Building |  |  |  | Project Cost: | 627000 | Target Completion Date: |  | Program: | 627000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | PROJECT Was funded by LGU, Kapalong | PROJECT Was funded by LGU, Kapalong | PROJECT Was funded by LGU, Kapalong | For amendment.To submit a new resolution for another priority project which is the Const. of Multi-Purpose Pavement but the propose site is not is donated because the previous project Completion of Brgy. Health Center was funded by the LGU of Kapalong | For amendment.To submit a new resolution for another priority project which is the Const. of Multi-Purpose Pavement but the propose site is not is donated because the previous project Completion of Brgy. Health Center was funded by the LGU of Kapalong | For amendment.To submit a new resolution for another priority project which is the Const. of Multi-Purpose Pavement but the propose site is not is donated because the previous project Completion of Brgy. Health Center was funded by the LGU of Kapalong
[7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 627000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Construction of Potable Water System at Purok 6, New Santiago, Asuncion |  | SB No. 4 CY 2019 (STIMULUS) | Water System |  |  | contract | Project Cost: | 1000000 | Target Completion Date: |  | Program: | 1000000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Change of POW to Contract Procurement on process ( Amended in AIP 3rd revision CY 2019 increasing the amount to complete the project For plan preparation c/o Amamio) Additional fund Php 500,000 | Procurement on process ( Amended in AIP 3rd revision CY 2019 increasing the amount to complete the project For plan preparation c/o Amamio) Additional fund Php 500,000 | Awarded to Two Degrees Construction & Supply | Awarded to Two Degrees Construction & Supply | Awarded to Two Degrees Construction & Supply | Awarded to Two Degrees Construction & Supply
[7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 1000000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Desilting and Concreting of Drainage-Main Collector Canal, New Casay, B.E. Dujali |  | SB # 4 CY 2019 (STIMULUS | Desiltation |  |  | Contract | Project Cost: | 650000 | Target Completion Date: | 0 | Program: | 650000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 650000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: |  | Slippage: |  | Slippage:
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Rehab. Of Multi-Purpose Building (Evacuation Center), Limbaan, New Corella |  | SB NO. 4 CY 2019 (STIMULUS) | Building |  |  |  | Project Cost: | 600000 | Target Completion Date: |  | Program: | 600000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | From SB # 1 to SB # 4 CY 2019 (Transfer to Contract) Procurement on process | From SB # 1 to SB # 4 CY 2019 (Transfer to Contract) Procurement on process | From SB # 1 to SB # 4 CY 2019 (Transfer to Contract) Procurement on process |  |  | From SB # 1 to SB # 4 CY 2019 (Transfer to Contract) Procurement on process
[7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 600000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Rehabilitation of Multi-Purpose Hall, Pantaron, Sto. Tomas |  | SB # 4 CY 2019 (STIMULUS | Building |  |  |  | Project Cost: | 550000 | Target Completion Date: |  | Program: | 550000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | For implementation | For implementation | For implementation | For implementation | For implementation | For implementation
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 550000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Rehabilitation of Multi-Purpose Hall, Salvacion, Sto. Tomas |  | SB # 4 CY 2019 (STIMULUS | Building |  |  |  | Project Cost: | 1000000 | Target Completion Date: |  | Program: | 1000000 | Planned: |  | Planned: |  | Planned: |  | Planned: | 100% | Planned: | 100% | No. of Persons: |  | PR #20032281 | PR #20032281 | PR #20032281 | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 1000000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: | 100% | Actual: | 100%
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Rehabilitation of Multi-Purpose Bldg. (Brgy. Hall) Tagpopongan, IGACOS |  | SB # 4 CY 2019 (STIMULUS | Building |  |  |  | Project Cost: | 174460.33 | Target Completion Date: |  | Program: | 174460.33 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Procurement on process | Procurement on process | Procurement on process |  |  | Procurement on process
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 174460.33 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Construction of Water System Project, Poblacion Kaputian, Samal |  | SB # 4 CY 2019 (20% DF -STIMULUS) | Water System |  |  | Contract | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | For implementation | For implementation | For implementation | For implementation | For implementation | For implementation
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Rehab. Of Multi-Purpose Hall, New Malitbog, Panabo City |  | SB # 4 CY 2019 (STIMULUS) | Building |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Amended in AIP 3rd revsion CY 2019 to change the project to Construction of Potable Water System because the original project will be funded by LGU, Panabo City (Brgy. resolution no. 25 series of 2019 dated Aug. 13, 2019 submitted) | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Rehabilitation of Local Roads at Dalisay-Manay Road Section, Panabo City |  | SB NO. 4 CY 2019 | Road |  |  | Admin | Project Cost: | 246100 | Target Completion Date: |  | Program: | 246100 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | For implementation | For implementation | For implementation | For implementation | For implementation | For implementation
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 246100 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Rehabilitation of Local Roads at Sta. Cruz-Jct. Tagpore-Buenavista Raod Section, Panabo City |  | SB NO. 4 CY 2019 | Road |  |  | Admin | Project Cost: | 431000 | Target Completion Date: |  | Program: | 431000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | For implementation | For implementation | For implementation | For implementation | For implementation | For implementation
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 431000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Rehabilitation of Local Roads at Taba-Bucana Road Section, Taba, Carmen |  | SB # 4 CY 2019 | Road |  |  | Admin | Project Cost: | 220000 | Target Completion Date: |  | Program: | 220000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | For implementation | For implementation | For implementation | For implementation | For implementation | For implementation
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 220000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Rehab. Of Canal Lining and Slope Protection at San Agustin E/S, San Agustin, Tagum City |  | SB NO. 4 FUND CY 2019 | Road |  | km | Admin | Project Cost: | 350000 | Target Completion Date: |  | Program: | 350000 | Planned: | 81.11% | Planned: | 81.11% | Planned: | 81.11% | Planned: | 81.11% | Planned: |  | No. of Persons: |  | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | For verification
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 350000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: | 81.11% | Actual: | 81.11% | Actual: | 81.11% | Actual: | 81.11% | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Desilting of Limbaan Creek, New Corella |  | 5% CALAMITY FUND CY 2019 | creeks and canals deislted |  | ln.m | Admin | Project Cost: | 2000000 | Target Completion Date: | 2019-12-02 | Program: | 2000000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Suspended | Suspended | Suspended | Suspended | Suspended | Suspended
[7 empty] | Project Engineer: | Pilotos | Revised Completion Date: | 2019-12-02 | Allotment: | 2000000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: | 257 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
[7 empty] | Date Started: | 2019-03-20
Impv't. of Jct. New Boholano - New Loon Cross Drainage |  | 5% CALAMITY FUND CY 2019 | Drainage |  | km | Admin | Project Cost: | 2000000 | Target Completion Date: | 2020-02-16 | Program: | 2000000 | Planned: | 42.27% | Planned: | 42.27% | Planned: | 42.27% | Planned: | 42.27% | Planned: | 70% | No. of Persons: |  | Suspended due to availability of equipment | Suspended due to availability of equipment | Suspended due to availability of equipment | Suspended due to availability of equipment | Suspended due to availability of equipment | On-going
[7 empty] | Project Engineer: | Pilotos | Revised Completion Date: | 2020-02-16 | Allotment: | 2000000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: | 31.7% | Actual: | 31.7% | Actual: | 31.7% | Actual: | 31.7% | Actual: | 70%
[7 empty] | Duration: | 90 | No. of days extended: |  |  |  | Slippage: | -10.57% | Slippage: | -10.57% | Slippage: | -10.57% | Slippage: | -10.57% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
[7 empty] | Date Started: | 2019-11-18
Construction of Evacuation Facility (Const. of Multi-Purpose/Evacuation Center), New Corella |  | PCF CY 2019 | Road |  | km | Contract | Project Cost: | 2500000 | Target Completion Date: | 0 | Program: | 53991806 | Planned: | [7 empty] | No. of Persons: |  | No. of Persons: |  | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Procurement on process
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 53991806 | Revised: | [7 empty] | No. of Man-days: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage:
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
ROAD ID 002 - Magatos - Bdry. Pagsabangan |  | GENERAL FUND CY 2020 | Maintenance | 8.33 | km | CBRMC | Project Cost: | 280180.88 | Target Completion Date: |  | Program: | 280180.88 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Purchase Request # 19125306 (On process) | Purchase Request # 19125306 (On process) | Purchase Request # 19125306 (On process) | Purchase Request # 19125306 (On process) | Purchase Request # 19125306 (On process) | Procurement on process
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 280180.88 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
ROAD ID 003 - Ilog - New Bantayan |  | GENERAL FUND CY 2020 | Maintenance | 2.68 | km | CBRMC | Project Cost: | 70633.836 | Target Completion Date: |  | Program: | 70633.836 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Purchase Request # 19125307 (On process) | Purchase Request # 19125307 (On process) | Purchase Request # 19125307 (On process) | Purchase Request # 19125307 (On process) | Purchase Request # 19125307 (On process) | Procurement on process
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 70633.836 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
ROAD ID 005 - Asuncion - Monte Carlo - Del Pilar |  | GENERAL FUND CY 2020 | Maintenance | 9.93 | km | CBRMC | Project Cost: | 360232.5636 | Target Completion Date: |  | Program: | 360232.5636 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Awarded to Mahayahay Integrated Farmers Association | Awarded to Mahayahay Integrated Farmers Association | Awarded to Mahayahay Integrated Farmers Association | Awarded to Mahayahay Integrated Farmers Association | Awarded to Mahayahay Integrated Farmers Association | For implementation
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 360232.5636 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
ROAD ID 006 - Jct. Highway Canatan - Magatos |  | GENERAL FUND CY 2020 | Maintenance | 4.85 | km | CBRMC | Project Cost: | 164812.284 | Target Completion Date: |  | Program: | 164812.284 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Purchase Request # 19125309 (On process) | Purchase Request # 19125309 (On process) | Purchase Request # 19125309 (On process) | Purchase Request # 19125309 (On process) | Purchase Request # 19125309 (On process) | Procurement on process
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 164812.284 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
ROAD ID 010 - Saug - Sonlon - Bdry. Longanapan |  | GENERAL FUND CY 2020 | Maintenance | 11.6 | km | CBRMC | Project Cost: | 197774.7408 | Target Completion Date: |  | Program: | 197774.7408 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Purchase Request # 19125310 (On process) | Purchase Request # 19125310 (On process) | Purchase Request # 19125310 (On process) | Purchase Request # 19125310 (On process) | Purchase Request # 19125310 (On process) | Procurement on process
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 197774.7408 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
ROAD ID 011 - Jct. New Visayas - Buan |  | GENERAL FUND CY 2020 | Maintenance | 2.99 | km | CBRMC | Project Cost: | 124786.4436 | Target Completion Date: |  | Program: | 124786.4436 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Purchase Request # 19125311 (On process) | Purchase Request # 19125311 (On process) | Purchase Request # 19125311 (On process) | Purchase Request # 19125311 (On process) | Purchase Request # 19125311 (On process) | Procurement on process
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 124786.4436 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
ROAD ID 013 - San Vicente - Butay |  | GENERAL FUND CY 2020 | Maintenance | 7.52 | km | CBRMC | Project Cost: | 235446.12 | Target Completion Date: |  | Program: | 235446.12 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Purchase Request # 19125312 (On process) | Purchase Request # 19125312 (On process) | Purchase Request # 19125312 (On process) | Purchase Request # 19125312 (On process) | Purchase Request # 19125312 (On process) | Procurement on process
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 235446.12 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
ROAD ID 014 - Jct. Highway Doña Andrea - Capungagan |  | GENERAL FUND CY 2020 | Maintenance | 8.7 | km | CBRMC | Project Cost: | 299016.5724 | Target Completion Date: |  | Program: | 299016.5724 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Purchase Request # 19125313 (On process) | Purchase Request # 19125313 (On process) | Purchase Request # 19125313 (On process) | Purchase Request # 19125313 (On process) | Purchase Request # 19125313 (On process) | Procurement on process
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 299016.5724 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
ROAD ID 015 - Pamacaun - Lasang - Banate |  | GENERAL FUND CY 2020 | Maintenance | 4.11 | km | CBRMC | Project Cost: | 129495.366 | Target Completion Date: |  | Program: | 129495.366 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Purchase Request # 19125314 (On process) | Purchase Request # 19125314 (On process) | Purchase Request # 19125314 (On process) | Purchase Request # 19125314 (On process) | Purchase Request # 19125314 (On process) | Procurement on process
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 129495.366 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
ROAD ID 018 - Semong - Palma Gil |  | GENERAL FUND CY 2020 | Maintenance | 2.73 | km | CBRMC | Project Cost: | 77697.2196 | Target Completion Date: |  | Program: | 77697.2196 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Purchase Request # 19125315 (On process) | Purchase Request # 19125315 (On process) | Purchase Request # 19125315 (On process) | Purchase Request # 19125315 (On process) | Purchase Request # 19125315 (On process) | Procurement on process
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 77697.2196 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
ROAD ID 020 - Daligdigon-Dagohoy |  | GENERAL FUND CY 2020 | Maintenance | 3.34 | km | CBRMC | Project Cost: | 77697.2196 | Target Completion Date: |  | Program: | 77697.2196 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Purchase Request # 19125315 (On process) | Purchase Request # 19125315 (On process) | Purchase Request # 19125315 (On process) | Purchase Request # 19125315 (On process) | Purchase Request # 19125315 (On process) | Procurement on process
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 77697.2196 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
ROAD ID 021 - Angelo - Dagohoy |  | GENERAL FUND CY 2020 | Maintenance | 2.19 | km | CBRMC | Project Cost: | 40025.8404 | Target Completion Date: |  | Program: | 40025.8404 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Purchase Request # 19125317 (On process) | Purchase Request # 19125317 (On process) | Purchase Request # 19125317 (On process) | Purchase Request # 19125317 (On process) | Purchase Request # 19125317 (On process) | Procurement on process
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 40025.8404 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
ROAD ID 025 - Jct. Sampao - Bdry. Mamacao |  | GENERAL FUND CY 2020 | Maintenance | 4.98 | km | CBRMC | Project Cost: | 178939.0512 | Target Completion Date: |  | Program: | 178939.0512 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Purchase Request # 19125318 (On process) | Purchase Request # 19125318 (On process) | Purchase Request # 19125318 (On process) | Purchase Request # 19125318 (On process) | Purchase Request # 19125318 (On process) | Procurement on process
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 178939.0512 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
ROAD ID 026 - Jct. Highway - Luna - Mamacao - Narra |  | GENERAL FUND CY 2020 | Maintenance | 9.17 | km | CBRMC | Project Cost: | 393195.0204 | Target Completion Date: |  | Program: | 393195.0204 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Purchase Request # 19125337 (On process) | Purchase Request # 19125337 (On process) | Purchase Request # 19125337 (On process) | Purchase Request # 19125337 (On process) | Purchase Request # 19125337 (On process) | Procurement on process
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 393195.0204 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
ROAD ID 027 - Jct. Gabuyan - Katipunan - Bucana |  | GENERAL FUND CY 2020 | Maintenance | 5.89 | km | CBRMC | Project Cost: | 174230.1288 | Target Completion Date: |  | Program: | 174230.1288 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Purchase Request # 19125338 (On process) | Purchase Request # 19125338 (On process) | Purchase Request # 19125338 (On process) | Purchase Request # 19125338 (On process) | Purchase Request # 19125338 (On process) | Procurement on process
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 174230.1288 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
ROAD ID 028 - Capungagan - Mabuhay - Pandulian |  | GENERAL FUND CY 2020 | Maintenance | 5.57 | km | CBRMC | Project Cost: | 155394.4392 | Target Completion Date: |  | Program: | 155394.4392 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Procurement on process | Purchase Request # 19125339 (On process) | Purchase Request # 19125339 (On process) | Purchase Request # 19125339 (On process) | Purchase Request # 19125339 (On process) | Procurement on process
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 155394.4392 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
ROAD ID 034 - Km. 15, Kipalili - New Loon |  | GENERAL FUND CY 2020 | Maintenance | 6.93 | km | CBRMC | Project Cost: | 296662.1112 | Target Completion Date: |  | Program: | 296662.1112 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Procurement on process | Purchase Request # 19125340 (On process) | Purchase Request # 19125340 (On process) | Purchase Request # 19125340 (On process) | Purchase Request # 19125340 (On process) | Procurement on process
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 296662.1112 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
ROAD ID 035 - Jct. Suaon - Libuton |  | GENERAL FUND CY 2020 | Maintenance | 7.26 | km | CBRMC | Project Cost: | 96532.9092 | Target Completion Date: |  | Program: | 96532.9092 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Awarded to Association of Alternative Livelihood of Libuton Inc. | Awarded to Association of Alternative Livelihood of Libuton Inc. | Awarded to Association of Alternative Livelihood of Libuton Inc. | Awarded to Association of Alternative Livelihood of Libuton Inc. | Awarded to Association of Alternative Livelihood of Libuton Inc. | Procurement on process
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 96532.9092 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
ROAD ID 037 - Monte Dujali - Gupitan |  | GENERAL FUND CY 2020 | Maintenance | 4.58 | km | CBRMC | Project Cost: | 134204.2884 | Target Completion Date: |  | Program: | 134204.2884 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Awarded to Association of Alternative Livelihood of Libuton Inc. | Awarded to Association of Alternative Livelihood of Libuton Inc. | Awarded to Association of Alternative Livelihood of Libuton Inc. | Awarded to Association of Alternative Livelihood of Libuton Inc. | Awarded to Association of Alternative Livelihood of Libuton Inc. | Procurement on process
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 134204.2884 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
ROAD ID 041 - Sawata - Mamangan - Pinamuno |  | GENERAL FUND CY 2020 | Maintenance | 14.48 | km | CBRMC | Project Cost: | 522690.3864 | Target Completion Date: |  | Program: | 522690.3864 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Procurement on process | Purchase Request # 19125343 (On process) | Purchase Request # 19125343 (On process) | Purchase Request # 19125343 (On process) | Purchase Request # 19125343 (On process) | Procurement on process
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 522690.3864 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
ROAD ID 042 - Igangon - Sawata |  | GENERAL FUND CY 2020 | Maintenance | 9.66 | km | CBRMC | Project Cost: | 202483.6632 | Target Completion Date: |  | Program: | 202483.6632 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Purchase Request # 19125344 (On process) | Purchase Request # 19125344 (On process) | Purchase Request # 19125344 (On process) | Purchase Request # 19125344 (On process) | Purchase Request # 19125344 (On process) | Procurement on process
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 202483.6632 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
ROAD ID 043 - Jct. Sawata - Bdry. Binasbas |  | GENERAL FUND CY 2020 | Maintenance | 0.46 | km | CBRMC | Project Cost: | 18835.6896 | Target Completion Date: |  | Program: | 18835.6896 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Purchase Request # 19125345 (On process) | Purchase Request # 19125345 (On process) | Purchase Request # 19125345 (On process) | Purchase Request # 19125345 (On process) | Purchase Request # 19125345 (On process) | Procurement on process
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 18835.6896 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
ROAD ID 045 - Tagaytay - Buan |  | GENERAL FUND CY 2020 | Maintenance | 4.92 | km | CBRMC | Project Cost: | 174230.1288 | Target Completion Date: |  | Program: | 174230.1288 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Purchase Request # 19125346 (On process) | Purchase Request # 19125346 (On process) | Purchase Request # 19125346 (On process) | Purchase Request # 19125346 (On process) | Purchase Request # 19125346 (On process) | Procurement on process
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 174230.1288 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
ROAD ID 049 - Limbaan - Sto. Niño |  | GENERAL FUND CY 2020 | Maintenance | 3.19 | km | CBRMC | Project Cost: | 127140.9048 | Target Completion Date: |  | Program: | 127140.9048 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Procurement on process | Purchase Request # 20010072 (On process) | Purchase Request # 20010072 (On process) | Purchase Request # 20010072 (On process) | Purchase Request # 20010072 (On process) | Procurement on process
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 127140.9048 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
ROAD ID 050 - Jct. Monte Carlo - Upper Cabaywa - Canatan |  | GENERAL FUND CY 2020 | Maintenance | 4.61 | km | CBRMC | Project Cost: | 197774.7408 | Target Completion Date: |  | Program: | 197774.7408 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Procurement on process | Purchase Request # 20010074 (On process) | Purchase Request # 20010074 (On process) | Purchase Request # 20010074 (On process) | Purchase Request # 20010074 (On process) | Procurement on process
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 197774.7408 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
ROAD ID 051 - Del Pilar - Jct. Silangan |  | GENERAL FUND CY 2020 | Maintenance | 4.17 | km | CBRMC | Project Cost: | 129495.366 | Target Completion Date: |  | Program: | 129495.366 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Procurement on process | Purchase Request # 20010093 (On process) | Purchase Request # 20010093 (On process) | Purchase Request # 20010093 (On process) | Purchase Request # 20010093 (On process) | Procurement on process
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 129495.366 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
ROAD ID 052 - New Corella - New Sambog - Silangan |  | GENERAL FUND CY 2020 | Maintenance | 5.1 | km | CBRMC | Project Cost: | 148331.0556 | Target Completion Date: |  | Program: | 148331.0556 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Purchase Request # 20010095 (On process) | Purchase Request # 20010095 (On process) | Purchase Request # 20010095 (On process) | Purchase Request # 20010095 (On process) | Purchase Request # 20010095 (On process) | Procurement on process
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 148331.0556 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
ROAD ID 053 - Pob. New Corella - Prk. 10 Pob. |  | GENERAL FUND CY 2020 | Maintenance | 1.3 | km | CBRMC | Project Cost: | 21190.1508 | Target Completion Date: |  | Program: | 21190.1508 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Awarded to Carcor Motor Driver's Association | Awarded to Carcor Motor Driver's Association | Awarded to Carcor Motor Driver's Association | Awarded to Carcor Motor Driver's Association | Awarded to Carcor Motor Driver's Association | Procurement on process
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 21190.1508 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
ROAD ID 054 - Prk. 7 Pob. - Jct. New Sambog |  | GENERAL FUND CY 2020 | Maintenance | 2.54 | km | CBRMC | Project Cost: | 113014.1376 | Target Completion Date: |  | Program: | 113014.1376 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Awarded to Carcor Motor Driver's Association | Awarded to Carcor Motor Driver's Association | Awarded to Carcor Motor Driver's Association | Awarded to Carcor Motor Driver's Association | Awarded to Carcor Motor Driver's Association | Procurement on process
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 113014.1376 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
ROAD ID 056 - Sta. Fe - Del Monte |  | GENERAL FUND CY 2020 | Maintenance | 3.34 | km | CBRMC | Project Cost: | 75342.7584 | Target Completion Date: |  | Program: | 75342.7584 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Purchase Request # 20010160 (On process) | Purchase Request # 20010160 (On process) | Purchase Request # 20010160 (On process) | Purchase Request # 20010160 (On process) | Purchase Request # 20010160 (On process) | Procurement on process
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 75342.7584 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
ROAD ID 058 - New Corella - New Bohol |  | GENERAL FUND CY 2020 | Maintenance | 11.54 | km | CBRMC | Project Cost: | 221319.3528 | Target Completion Date: |  | Program: | 221319.3528 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Awarded to Carcor Motor Driver's Association | Awarded to Carcor Motor Driver's Association | Awarded to Carcor Motor Driver's Association | Awarded to Carcor Motor Driver's Association | Awarded to Carcor Motor Driver's Association | For implementation
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 221319.3528 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
ROAD ID 059 - Jct. Carcor - Prk. 9 Bagsak |  | GENERAL FUND CY 2020 | Maintenance | 2.5 | km | CBRMC | Project Cost: | 72988.2972 | Target Completion Date: |  | Program: | 72988.2972 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Awarded to Carcor Motor Driver's Association | Awarded to Carcor Motor Driver's Association | Awarded to Carcor Motor Driver's Association | Awarded to Carcor Motor Driver's Association | Awarded to Carcor Motor Driver's Association | For implementation Carcor Motor Driver's Association
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 72988.2972 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
ROAD ID 060 - Carcor - Jct. Kauswagan |  | GENERAL FUND CY 2020 | Maintenance | 4.32 | km | CBRMC | Project Cost: | 101241.8316 | Target Completion Date: |  | Program: | 101241.8316 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Awarded to Carcor Motor Driver's Association | Awarded to Carcor Motor Driver's Association | Awarded to Carcor Motor Driver's Association | Awarded to Carcor Motor Driver's Association | Awarded to Carcor Motor Driver's Association | For implementation Carcor Motor Driver's Association
[7 empty] | Project Engineer: | Fabian | Revised Completion Date: |  | Allotment: | 101241.8316 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
ROAD ID 061 - Del Pilar - Prk. 9 Bagsak - San Jose |  | GENERAL FUND CY 2020 | Maintenance |  | km | CBRMC | Project Cost: | 251927.3484 | Target Completion Date: |  | Program: | 251927.3484 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Purchase Request # 20010264 (On process) | Purchase Request # 20010264 (On process) | Purchase Request # 20010264 (On process) | Purchase Request # 20010264 (On process) | Purchase Request # 20010264 (On process) | Procurement on process
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 251927.3484 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
ROAD ID 062 - Del Pilar - El Unido |  | GENERAL FUND CY 2020 | Maintenance | 1.32 | km | CBRMC | Project Cost: | 40025.8404 | Target Completion Date: |  | Program: | 40025.8404 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Purchase Request # 20010265 (On process) | Purchase Request # 20010265 (On process) | Purchase Request # 20010265 (On process) | Purchase Request # 20010265 (On process) | Purchase Request # 20010265 (On process) | Procurement on process
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 40025.8404 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
ROAD ID 063 - San Juan - New Talisay |  | GENERAL FUND CY 2020 | Maintenance | 5.13 | km | CBRMC | Project Cost: | 131849.8272 | Target Completion Date: |  | Program: | 131849.8272 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Awarded to Mahayahay Integrated Farmers Association | Awarded to Mahayahay Integrated Farmers Association | Awarded to Mahayahay Integrated Farmers Association | Awarded to Mahayahay Integrated Farmers Association | Awarded to Mahayahay Integrated Farmers Association | Awarded to Mahayahay Integrated Farmers Association
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 131849.8272 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
ROAD ID 064 - San Juan - Kauswagan - New Cortez |  | GENERAL FUND CY 2020 | Maintenance | 3.22 | km | CBRMC | Project Cost: | 68279.3748 | Target Completion Date: |  | Program: | 68279.3748 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Procurement on process | Procurement on process | Procurement on process | Procurement on process | Procurement on process | Procurement on process
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 68279.3748 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
ROAD ID 065 - New Bohol - Jct. El Unido |  | GENERAL FUND CY 2020 | Maintenance | 2.12 | km | CBRMC | Project Cost: | 65924.9136 | Target Completion Date: |  | Program: | 65924.9136 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Purchase Request # 20010275 (On process) | Purchase Request # 20010275 (On process) | Purchase Request # 20010275 (On process) | Purchase Request # 20010275 (On process) | Purchase Request # 20010275 (On process) | Procurement on process
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 65924.9136 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
ROAD ID 066 - New Corella - El Unido - Jct. Mesaoy |  | GENERAL FUND CY 2020 | Maintenance | 8.63 | km | CBRMC | Project Cost: | 249572.8872 | Target Completion Date: |  | Program: | 249572.8872 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Purchase Request # 20010291 (On process) | Purchase Request # 20010291 (On process) | Purchase Request # 20010291 (On process) | Purchase Request # 20010291 (On process) | Purchase Request # 20010291 (On process) | Procurement on process
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 249572.8872 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
ROAD ID 067 - Mesaoy - Dasing |  | GENERAL FUND CY 2020 | Maintenance | 1.39 | km | CBRMC | Project Cost: | 54152.6076 | Target Completion Date: |  | Program: | 54152.6076 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Purchase Request # 20010294 (On process) | Purchase Request # 20010294 (On process) | Purchase Request # 20010294 (On process) | Purchase Request # 20010294 (On process) | Purchase Request # 20010294 (On process) | Procurement on process
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 54152.6076 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
ROAD ID 068 - Jct. San Juan - Jct. Mesaoy |  | GENERAL FUND CY 2020 | Maintenance | 1.82 | km | CBRMC | Project Cost: | 68279.3748 | Target Completion Date: |  | Program: | 68279.3748 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Awarded to Mahayahay Integrated Farmers Association | Awarded to Mahayahay Integrated Farmers Association | Awarded to Mahayahay Integrated Farmers Association | Awarded to Mahayahay Integrated Farmers Association | Awarded to Mahayahay Integrated Farmers Association | Procurement on process
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 68279.3748 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
ROAD ID 070 - Mesaoy - New Bohol |  | GENERAL FUND CY 2020 | Maintenance | 5.36 | km | CBRMC | Project Cost: | 261345.1932 | Target Completion Date: |  | Program: | 261345.1932 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Purchase Request # 20010298 (On process) | Purchase Request # 20010298 (On process) | Purchase Request # 20010298 (On process) | Purchase Request # 20010298 (On process) | Purchase Request # 20010298 (On process) | Procurement on process
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 261345.1932 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
ROAD ID 147 - Prk. 1, Maunlom-Prk. 6 Maunlom Road |  | GENERAL FUND CY 2020 | Maintenance | 3.56 | km | CBRMC | Project Cost: | 65924.9136 | Target Completion Date: |  | Program: | 65924.9136 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Purchase Request # 20010302 (On process) | Purchase Request # 20010302 (On process) | Purchase Request # 20010302 (On process) | Purchase Request # 20010302 (On process) | Purchase Request # 20010302 (On process) | Procurement on process
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 65924.9136 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
ROAD ID 149 - New Visayas - Binancian |  | GENERAL FUND CY 2020 | Maintenance | 7.77 | km | CBRMC | Project Cost: | 134204.2884 | Target Completion Date: |  | Program: | 134204.2884 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Purchase Request # 20010305 (On process) | Purchase Request # 20010305 (On process) | Purchase Request # 20010305 (On process) | Purchase Request # 20010305 (On process) | Purchase Request # 20010305 (On process) | Procurement on process
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 134204.2884 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
ROAD ID 150 - Datu Balong - Prk. Mamalian |  | GENERAL FUND CY 2020 | Maintenance | 3.46 | km | CBRMC | Project Cost: | 61215.9912 | Target Completion Date: |  | Program: | 61215.9912 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Purchase Request # 20010306 (On process) | Purchase Request # 20010306 (On process) | Purchase Request # 20010306 (On process) | Purchase Request # 20010306 (On process) | Purchase Request # 20010306 (On process) | Procurement on process
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 61215.9912 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
ROAD ID 008 - Sta. Felomina - San Roque |  | 20% Development Fund CY 2020 | Road Rehabilitaion | 7.68 | km | Admin | Project Cost: | 2304000 | Target Completion Date: |  | Program: | 2304000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Post qualification on process | Post qualification on process | Post qualification on process | Post qualification on process | Post qualification on process | Post qualification on process
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 2304000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
ROAD ID 019 - Sto. Niño - Palma Gil - Sitio Opao |  | 20% Development Fund CY 2020 | Road Rehabilitaion | 5.99 | km | Admin | Project Cost: | 1797000 | Target Completion Date: |  | Program: | 1797000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | POW on process | POW on process | POW on process | POW on process | POW on process | POW on process
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 1797000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
ROAD ID 023 - Sto. Niño - Daligdigon - Paiton |  | 20% Development Fund CY 2020 | Road Rehabilitaion | 11.6 | km | Admin | Project Cost: | 3480000 | Target Completion Date: |  | Program: | 3480000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | POW on process | POW on process | POW on process | POW on process | POW on process | POW on process
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 3480000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
ROAD ID 024 - Jct. Paiton - Mibolo |  | 20% Development Fund CY 2020 | Road Rehabilitaion | 23.9 | km | Admin | Project Cost: | 7170000 | Target Completion Date: |  | Program: | 7170000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | POW on process | POW on process | POW on process | POW on process | POW on process | POW on process
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 7170000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
ROAD ID 024 - Florida - Suaon - Jct. Gupitan |  | 20% Development Fund CY 2020 | Road Rehabilitaion | 15.57 | km | Admin | Project Cost: | 4671000 | Target Completion Date: |  | Program: | 4671000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | PO on process - Royal Summit | PO on process - Royal Summit | PO on process - Royal Summit | PO on process - Royal Summit | PO on process - Royal Summit | PO on process - Royal Summit
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 4671000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
ROAD ID 048 - New Corella - Saug |  | 20% Development Fund CY 2020 | Road Rehabilitaion | 12.52 | km | Admin | Project Cost: | 20571000 | Target Completion Date: |  | Program: | 20571000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | POW on process | POW on process | POW on process | POW on process | POW on process | POW on process
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 20571000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
ROAD ID 074 - Jct. Highway Canatan - Doña Andrea |  | 20% Development Fund CY 2020 | Road Rehabilitaion | 4.34 | km | Admin | Project Cost: | 1302000 | Target Completion Date: |  | Program: | 1302000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | POW on process | POW on process | POW on process | POW on process | POW on process | POW on process
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 1302000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
ROAD ID 030 - Florida - New Boholano |  | 20% Development Fund CY 2020 | Road Rehabilitaion | 2.54 | km | Admin | Project Cost: | 762000 | Target Completion Date: |  | Program: | 762000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | POW on process | POW on process | POW on process | POW on process | POW on process | POW on process
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 762000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
ROAD ID 031 - Jct. New Boholano - New Loon |  | 20% Development Fund CY 2020 | Road Rehabilitaion | 4.77 | km | Admin | Project Cost: | 1431000 | Target Completion Date: |  | Program: | 1431000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | POW on process | POW on process | POW on process | POW on process | POW on process | POW on process
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 1431000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
ROAD ID 071 - Lower Asuncion - Upper Asuncion |  | 20% Development Fund CY 2020 | Road Rehabilitaion |  | km | Admin | Project Cost: | 1302000 | Target Completion Date: |  | Program: | 1302000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Plan On-going | Plan On-going | Plan On-going | Plan On-going | Plan On-going | Plan On-going
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 1302000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
ROAD ID 108 - New Casay - Bugtong Talisay |  | GENERAL FUND CY 2020 | Maintenance |  | km | CBRMC | Project Cost: | 64596.78 | Target Completion Date: |  | Program: | 64596.78 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | For re-bid | For re-bid | For re-bid | For re-bid | For re-bid | Re-bid/ documents on process
[7 empty] | Project Engineer: | Maligro | Revised Completion Date: |  | Allotment: | 64596.78 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
ROAD ID 118- Jct. Salvacion - San Vicente - Cabay-angan |  | GENERAL FUND CY 2020 | Maintenance | 3.45 | km | CBRMC | Project Cost: | 158775.23 | Target Completion Date: |  | Program: | 158775.23 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Abstract #320201396 - For post qualification | Abstract #320201396 - For post qualification | Abstract #320201396 - For post qualification | Abstract #320201396 - For post qualification | Abstract #320201396 - For post qualification | Procurement on process
[7 empty] | Project Engineer: | Maligro | Revised Completion Date: |  | Allotment: | 158775.23 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
ROAD ID 123- Bacali - Casig-ang - Libertad |  | GENERAL FUND CY 2020 | Maintenance |  | km | CBRMC | Project Cost: | 131608.37 | Target Completion Date: |  | Program: | 131608.37 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Abstract #320201449 - For post qualification | Abstract #320201449 - For post qualification | Abstract #320201449 - For post qualification | Abstract #320201449 - For post qualification | Abstract #320201449 - For post qualification | For implementation
[7 empty] | Project Engineer: | Maligro | Revised Completion Date: |  | Allotment: | 131608.37 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
ROAD ID 124 - Kinamayan - Moslog - Mahayag |  | GENERAL FUND CY 2020 | Maintenance |  | km | CBRMC | Project Cost: | 91159.92 | Target Completion Date: |  | Program: | 91159.92 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | For re-bid | For re-bid | For re-bid | For re-bid | For re-bid | Procurement on process
[7 empty] | Project Engineer: | Maligro | Revised Completion Date: |  | Allotment: | 91159.92 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
ROAD ID 007 - Lower Asuncion - Upper Asuncion (Phase I) |  | 20% DF CY 2020 | Rehabilitation |  | km |  | Project Cost: | 1302000 | Target Completion Date: |  | Program: | 1302000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 1302000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
ROAD ID 030 - Jct. Highway - Carmen - Mangalcal - Tubod (Phase I) |  | 20% DF CY 2020 | Rehabilitation |  | km |  | Project Cost: | 1323000 | Target Completion Date: | 2021-02-03 | Program: | 1323000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: | 100% | No. of Persons: | 2 | Plan On-going | Plan On-going | Plan On-going | Plan On-going | Plan On-going | Suspended 10/1/2020
[7 empty] | Project Engineer: | Obar | Revised Completion Date: |  | Allotment: | 1323000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 44
[7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual: | 68.83%
[7 empty] | Duration: | 90 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | -31.17%
[7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
[7 empty] | Date Started: | 2020-06-15
ROAD ID 031 - Tuganay - Taba (Phase I) |  | 20% DF CY 2020 | Rehabilitation |  | km |  | Project Cost: | 507500 | Target Completion Date: | 2020-06-17 | Program: | 507500 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: | 100% | No. of Persons: | 2 | Plan On-going | Plan On-going | Plan On-going | Plan On-going | Plan On-going | Suspended 6/13/2020
[7 empty] | Project Engineer: | Obar | Revised Completion Date: | 2020-08-21 | Allotment: | 507500 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 44
[7 empty] | Implementor: | PEO | No. of days suspended: | 65 | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual: | 68.87%
[7 empty] | Duration: | 30 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | -31.13%
[7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
[7 empty] | Date Started: | 2020-05-18
ROAD ID 069 - Jct. Highway - Ising - Magsaysay (Phase I) |  | 20% DF CY 2020 | Rehabilitation |  | km |  | Project Cost: | 6000000 | Target Completion Date: |  | Program: | 6000000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 6000000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Jct. Highway - Guadalupe - Bdry. Tagum (Phase I) |  | 20% DF CY 2020 | Rehabilitation |  | km |  | Project Cost: | 910000 | Target Completion Date: | 2020-08-06 | Program: | 910000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: | 3.2% | No. of Persons: | 2 | Suspended June 13, 2020 due to unavailability of heavy equipment | Plan On-going | Plan On-going | Plan On-going | Plan On-going | Suspended June 13, 2020 due to unavailability of heavy equipment
[7 empty] | Project Engineer: | Obar | Revised Completion Date: |  | Allotment: | 910000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 52
[7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual: | 1.2%
[7 empty] | Duration: | 80 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | -2%
[7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
[7 empty] | Date Started: | 2020-05-18
Sitio Malaga - Tibulao (Phase I) |  | 20% DF CY 2020 | Rehabilitation |  | km |  | Project Cost: | 350000 | Target Completion Date: | 2020-06-17 | Program: | 350000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: | 3.5% | No. of Persons: | 2 | Plan On-going | Plan On-going | Plan On-going | Plan On-going | Plan On-going | Suspended June 13, 2020 due to unavailability of heavy equipment
[7 empty] | Project Engineer: | Obar | Revised Completion Date: |  | Allotment: | 350000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 44
[7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual: | 1.2%
[7 empty] | Duration: | 30 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | -2.3%
[7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
[7 empty] | Date Started: | 2020-05-18
Rehablilitation of Cabay-angan-Esperanza Provincial Road, Carmen-B.E. Dujali (Phase I) |  | 20% DF CY 2020 | Rehabilitation |  | km |  | Project Cost: | 350000 | Target Completion Date: |  | Program: | 350000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Plan On-going | Plan On-going | Plan On-going | Plan On-going | Plan On-going | Plan On-going
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 350000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Dujali - Pawas - San Vicente (Phase I) |  | 20% DF CY 2020 | Rehabilitation |  | km |  | Project Cost: | 525000 | Target Completion Date: | 2020-07-02 | Program: | 525000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: | 6.5% | No. of Persons: | 2 | Plan On-going | Plan On-going | Plan On-going | Plan On-going | Plan On-going | PTemporarily Suspended June 13, 2020 due to unavailability of heavy equipment
[7 empty] | Project Engineer: | Obar | Revised Completion Date: |  | Allotment: | 525000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 42
[7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual: | 1.2%
[7 empty] | Duration: | 45 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | -5.3%
[7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
[7 empty] | Date Started: | 2020-05-18
Los Amigos 1 - Esperanza - Los Amigos 2 (Phase I) |  | 20% DF CY 2020 | Rehabilitation |  | km |  | Project Cost: | 350000 | Target Completion Date: |  | Program: | 350000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 350000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Menzi - Balagunan - Tulalian (Phase I) |  | 20% DF CY 2020 | Rehabilitation |  | km |  | Project Cost: | 3720500 | Target Completion Date: |  | Program: | 3720500 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 3720500 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Jct,. Bdry. Tagum- Talomo (Phase I) |  | 20% DF CY 2020 | Rehabilitation |  | km |  | Project Cost: | 1400000 | Target Completion Date: | 2020-09-15 | Program: | 1400000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: | 41.2% | No. of Persons: | 4 | POW for approval with the Governor | POW for approval with the Governor | POW for approval with the Governor | POW for approval with the Governor | POW for approval with the Governor | Suspended June 13, 2020
[7 empty] | Project Engineer: | Obar | Revised Completion Date: |  | Allotment: | 1400000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 88
[7 empty] | Implementor: | Admin | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual: | 39.6%
[7 empty] | Duration: | 120 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | -1.6%
[7 empty] | Date Allotment Released: |  | Date completed:
[7 empty] | Date Started: | 2020-05-18
Prk. 5 RJS - Prk. 6 New Casay (Phase I) |  | 20% DF CY 2020 | Rehabilitation |  | km |  | Project Cost: | 350000 | Target Completion Date: |  | Program: | 350000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Plan On-going | Plan On-going | Plan On-going | Plan On-going | Plan On-going | Plan On-going
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 350000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
ROAD ID 008 - Fr. Rd. 3 - San Jose |  | 20% DF CY 2020 | Rehabilitation |  | km |  | Project Cost: | 8000000 | Target Completion Date: |  | Program: | 8000000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Plan On-going | Plan On-going | Plan On-going | Plan On-going | Plan On-going | Plan On-going
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 8000000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Rural Electrification at RAMADA Compound Purok Sto. Niño, Brgy. Cuambogan, Tagum City |  | 20% Development Fund CY 2020 | Electrification |  | km |  | Project Cost: | 1000000 | Target Completion Date: |  | Program: | 1000000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | PO on process - Tagum Constrak | PO on process - Tagum Constrak | PO on process - Tagum Constrak | PO on process - Tagum Constrak | PO on process - Tagum Constrak | For implementation Tagum Constrak
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 1000000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Rural Electrification at Lower Camansa, Prk.5 to 6 Lower, Brgy. Camansa, Asuncion |  | 20% Development Fund CY 2020 | Electrification |  | km |  | Project Cost: | 3000000 | Target Completion Date: |  | Program: | 3000000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | PO on process - Tagum Constrak | PO on process - Tagum Constrak | PO on process - Tagum Constrak | PO on process - Tagum Constrak | PO on process - Tagum Constrak | For implementation Tagum Constrak
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 3000000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Completion of Single Phase Line at Purok 6 and Purok 7, Brgy. Cogon, Babak Distirct, IGACOS |  | 20% DF CY 2020 | Electrificaton |  | km |  | Project Cost: | 1000000 | Target Completion Date: |  | Program: | 1000000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | PR #20063965 | PR #20063965 | PR #20063965 | PR #20063965 | PR #20063965 | PR #20063965
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 1000000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Completion of Single Phase Line at Purok Perlas, Brgy. Sta. Cruz, Talicud (Day Care Center), IGACOS |  | 20% DF CY 2020 | Electrificaton |  | km |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | POW preparation on-going c/o Engr. Kim Pao Lu | POW preparation on-going c/o Engr. Kim Pao Lu | POW preparation on-going c/o Engr. Kim Pao Lu | POW preparation on-going c/o Engr. Kim Pao Lu | POW preparation on-going c/o Engr. Kim Pao Lu | POW preparation on-going c/o Engr. Kim Pao Lu
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Const. of Potable Water System, Brgy. Gupitan, Kapalong |  | 20% DF CY 2020 | PWS |  | km |  | Project Cost: | 3000000 | Target Completion Date: |  | Program: | 3000000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | POW preparation on-going c/o Engr. Kim Pao Lu | POW preparation on-going c/o Engr. Kim Pao Lu | POW preparation on-going c/o Engr. Kim Pao Lu |  |  | Plan On-going
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 3000000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Const. of Potable Water System, Brgy. Sto. Niño, Kapalong |  | 20% DF CY 2020 | PWS |  | km |  | Project Cost: | 1000000 | Target Completion Date: |  | Program: | 1000000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | POW preparation on-going c/o Engr. Kim Pao Lu | POW preparation on-going c/o Engr. Kim Pao Lu | POW preparation on-going c/o Engr. Kim Pao Lu |  |  | Plan On-going
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 1000000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Const. of Potable Water System, Brgy. Dagohoy, Talaingod |  | 20% DF CY 2020 | PWS |  | km |  | Project Cost: | 1000000 | Target Completion Date: |  | Program: | 1000000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | POW preparation on-going c/o Engr. Kim Pao Lu | POW preparation on-going c/o Engr. Kim Pao Lu | POW preparation on-going c/o Engr. Kim Pao Lu |  |  | Plan On-going
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 1000000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Const. of Potable Water System, Brgy. Palma Gil, Talaingod |  | 20% DF CY 2020 | PWS |  | km |  | Project Cost: | 1000000 | Target Completion Date: |  | Program: | 1000000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | POW preparation on-going c/o Engr. Kim Pao Lu | POW preparation on-going c/o Engr. Kim Pao Lu | POW preparation on-going c/o Engr. Kim Pao Lu |  |  | Plan On-going
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 1000000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Impv't. of Potable Water System, Brgy. Kiotoy, Panabo City |  | 20% DF CY 2020 | PWS |  | km |  | Project Cost: | 1000000 | Target Completion Date: |  | Program: | 1000000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | POW preparation on-going c/o Engr. Kim Pao Lu | POW preparation on-going c/o Engr. Kim Pao Lu | POW preparation on-going c/o Engr. Kim Pao Lu |  |  | Plan On-going
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 1000000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Impv't. of Potable Water System, Consolacion, Panabo City |  | 20% DF CY 2020 | Water System |  |  |  | Project Cost: | 10000000 | Target Completion Date: |  | Program: | 10000000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. |  |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No 1
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 10000000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Impv't. of Potable Water System, Tagbitan-ag, Samal Dist. |  | 20% DF CY 2020 | Water System |  |  |  | Project Cost: | 1000000 | Target Completion Date: |  | Program: | 1000000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | For implementation | For implementation | For implementation |  |  | Plan On-going
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 1000000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Impv't. of Potable Water System, San Antonio, babak, IGCS |  | 20% DF CY 2020 | Water System |  |  |  | Project Cost: | 1000000 | Target Completion Date: |  | Program: | 1000000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. |  |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No 1
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 1000000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Impv't. of Potable Water System, San Isidro, Babak, IGCS |  | 20% DF CY 2020 | Water System |  |  |  | Project Cost: | 1000000 | Target Completion Date: |  | Program: | 1000000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. |  |  | Plan On-going
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 1000000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Impv't. of Potable Water System,Licup, Samal, IGCS |  | 20% DF CY 2020 | Water System |  |  |  | Project Cost: | 2000000 | Target Completion Date: |  | Program: | 2000000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. |  |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No 1
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 2000000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Const. of Water System at Provincial Engineer's Office 2nd District Carmen |  | 20% DF CY 2020 | Water System |  |  |  | Project Cost: | 1000000 | Target Completion Date: |  | Program: | 1000000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. |  |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No 1
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 1000000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Construction Women Development Center, Dagohoy, Talaingod |  | 20% Development Fund CY 2020 | Building |  | sq.m |  | Project Cost: | 1000000 | Target Completion Date: |  | Program: | 1000000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Post qualification on process | Post qualification on process | Post qualification on process | Post qualification on process | Post qualification on process | Procurement on process
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 1000000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Const. of Native Chicken Production House at Sitio Salawao, Brgy. Sto. Niño, Talaingod |  | 20% Development Fund CY 2020 | Building |  | sq.m |  | Project Cost: | 2000000 | Target Completion Date: |  | Program: | 2000000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Post qualification on process | Post qualification on process | Post qualification on process | Post qualification on process | Post qualification on process | Procurement on process
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 2000000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Construction of Fence at Tulalian National High School, Tulalian, Sto. Tomas |  | GENERAL FUND CY 2020 | Fence |  | sq.m |  | Project Cost: | 1500000 | Target Completion Date: |  | Program: | 1500000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 1500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Construction of Commercial Building at Kinawitnon, IGACOS, Babak |  | 20% DF CY 2020 | Building |  | sq.m |  | Project Cost: | 2000000 | Target Completion Date: |  | Program: | 2000000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 2000000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Improvement of Provincial Engineer's Office 2nd District Office Phase 2, Carmen |  | 20% DF CY 2020 | Building |  | sq.m |  | Project Cost: | 1590000 | Target Completion Date: |  | Program: | 1590000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Plan and DED On-going | Plan and DED On-going | Plan and DED On-going | Plan and DED On-going | Plan and DED On-going | Plan and DED On-going
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 1590000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Construction of DAVNOR Tech-Vocational Center, Government Center, Mankilam, Tagum City |  | 20% Development Fund CY 2020 | Building |  | sq.m | Admin | Project Cost: | 8000000 | Target Completion Date: |  | Program: | 8000000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 8000000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Construction of DDN hospital Carmen Zone Annex Building Phase 3, Carmen |  | GENERAL FUND CY 2020 | Building |  | sq.m |  | Project Cost: | 800000 | Target Completion Date: |  | Program: | 800000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Abstract #0420201476 | Abstract #0420201476 | Abstract #0420201476 | Abstract #0420201476 | Abstract #0420201476 | Procurement on process
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 800000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Improvement of PSWDO Bodega Government Cente, Mankilam, Tagum City |  | 20% Development Fund CY 2020 | Building |  | sq.m | Admin | Project Cost: | 1000000 | Target Completion Date: |  | Program: | 1000000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | POW and Plans on-going | POW and Plans on-going | POW and Plans on-going | POW and Plans on-going | POW and Plans on-going | POW and Plans on-going
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 1000000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Renovation/Improvement of MAFAMCO Consumer's Bldg., Brgy. Mamangan, San Isidro |  | 20% Development Fund CY 2020 | Building |  | sq.m | Contract | Project Cost: | 800000 | Target Completion Date: |  | Program: | 800000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 800000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Construction of IP Council of Women Training Center, Camansa Kamadi District, Asuncion |  | 20% Development Fund CY 2020 | Building |  | sq.m | Admin | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Construction of Municipal Triball Hall, Asuncion |  | 20% Development Fund CY 2020 | Building |  | sq.m | Contract | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Construction of Municipal Triball Hall, Kapalong |  | 20% Development Fund CY 2020 | Building |  | sq.m | Contract | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Construction of Municipal Triball Hall, Talaingod |  | 20% Development Fund CY 2020 | Building |  | sq.m | Contract | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Construction of Municipal Triball Hall, Carmen |  | GENERAL FUND CY 2020 | Building |  | sq.m |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Construction of Municipal Triball Hall, B.E. Dujali |  | GENERAL FUND CY 2020 | Building |  | sq.m |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Construction of Municipal Triball Hall, Sto. Tomas |  | GENERAL FUND CY 2020 | Building |  | sq.m | Admin | Project Cost: | 500000 | Target Completion Date: | 2019-07-31 | Program: | 500000 | Planned: | 100% | Planned: | 100% | Planned: | 100% | Planned: | 100% | Planned: | 100% | No. of Persons: | 7 | Suspended June 28, 2019. Waiting for the delivery of JO Materials | Suspended June 28, 2019. Waiting for the delivery of JO Materials | Suspended June 28, 2019. Waiting for the delivery of JO Materials | Suspended June 28, 2019. Waiting for the delivery of JO Materials | Suspended June 28, 2019. Waiting for the delivery of JO Materials | Suspended June 28, 2019. Waiting for the delivery of JO Materials
[7 empty] | Project Engineer: | Roque | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 110
[7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: | 85% | Actual: | 85% | Actual: | 85% | Actual: | 85% | Actual: | 85%
[7 empty] | Duration: | 70 | No. of days extended: |  |  |  | Slippage: | -15% | Slippage: | -15% | Slippage: | -15% | Slippage: | -15% | Slippage: | -15%
[7 empty] | Date Allotment Released: | CY 2018 | Date completed:
[7 empty] | Date Started: | 2019-05-22
Construction of One(1) unit School Building at Cabidianan E/S, New Corella |  | 20% Development Fund CY 2020 | Building |  | sq.m | Contract | Project Cost: | 1300000 | Target Completion Date: |  | Program: | 1300000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: | [6 empty] | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No 1
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 1300000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Construction of one(1) unit School Building at Kamansi Integrated School, Florida, kapalong |  | 20% Development Fund CY 2020 | Building |  | sq.m | Contract | Project Cost: | 1300000 | Target Completion Date: |  | Program: | 1300000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 1300000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Construction of one(1) unit School Building at Magatos E/S, Magatos, Asuncion |  | 20% Development Fund CY 2020 | Building |  | sq.m | Contract | Project Cost: | 1300000 | Target Completion Date: |  | Program: | 1300000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 1300000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Construction of one(1) unit School Building at Sta. Cruz E/S, New Corella |  | 20% Development Fund CY 2020 | Building |  | sq.m |  | Project Cost: | 1300000 | Target Completion Date: |  | Program: | 1300000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 1300000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Construction of Two(2) Classroom at Tibulao Elem. School, Tibulao, Carmen |  | 20% Development Fund CY 2020 | Building |  | sq.m |  | Project Cost: | 2900000 | Target Completion Date: |  | Program: | 2900000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 2900000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Expansion of Balay Silangan (Phase 2), Gov't. Center, Mankilam |  | 20% Development Fund CY 2020 | Building |  | sq.m |  | Project Cost: | 5000000 | Target Completion Date: |  | Program: | 5000000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 5000000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Const. of Day Care Center, Limbaan, New Corella |  | 20% DF CY 2020 | Building |  | sq.m |  | Project Cost: | 1000000 | Target Completion Date: |  | Program: | 1000000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 1000000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Const. of Day Care Center, Gabuyan, kapalong |  | 20% DF CY 2020 | Building |  | sq.m |  | Project Cost: | 1000000 | Target Completion Date: |  | Program: | 1000000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 1000000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Compl./Rep. Day Care Center,Canatan, Asuncion |  | 20% DF CY 2020 | Building |  | sq.m |  | Project Cost: | 300000 | Target Completion Date: |  | Program: | 300000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 300000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Compl./Rep. Day Care Center,Cambanogoy, Asuncion |  | 20% DF CY 2020 | Building |  | sq.m |  | Project Cost: | 300000 | Target Completion Date: |  | Program: | 300000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 300000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Compl./Rep. Day Care Center,Gabuyan, kapalong |  | 20% DF CY 2020 | Building |  | sq.m |  | Project Cost: | 600000 | Target Completion Date: |  | Program: | 600000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 600000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Compl./Rep. Day Care Center,New Sambog, New Corella |  | 20% DF CY 2020 | Building |  | sq.m |  | Project Cost: | 300000 | Target Completion Date: |  | Program: | 300000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 300000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Compl./Rep. Day Care Center, Cabidianan, New Corella |  | 20% DF CY 2020 | Building |  | sq.m |  | Project Cost: | 300000 | Target Completion Date: |  | Program: | 300000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 300000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Compl./Rep. Day Care Center, Igangon, San Isidro |  | 20% DF CY 2020 | Building |  | sq.m |  | Project Cost: | 300000 | Target Completion Date: |  | Program: | 300000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 300000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Compl./Rep. Day Care Center, Madaum, Tagum City |  | 20% DF CY 2020 | Building |  | sq.m |  | Project Cost: | 300000 | Target Completion Date: |  | Program: | 300000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 300000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Compl./Rep. Day Care Center, Apokon, Tagum City |  | 20% DF CY 2020 | Building |  | sq.m |  | Project Cost: | 300000 | Target Completion Date: |  | Program: | 300000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 300000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Compl./Rep. Day Care Center, Sto. Niño, Talaingod |  | 20% DF CY 2020 | Building |  | sq.m |  | Project Cost: | 300000 | Target Completion Date: |  | Program: | 300000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 300000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Const. of Day Care Center, JP Laurel, Panabo City |  | AB CY 2020 | Building |  | sq.m |  | Project Cost: | 1000000 | Target Completion Date: |  | Program: | 1000000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 1000000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Const. of Day Care Center, Dujali, B.E. Dujali |  | AB CY 2020 | Building |  | sq.m |  | Project Cost: | 1000000 | Target Completion Date: |  | Program: | 1000000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 1000000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Const. of Day Care Center, Tibal-og, Sto Tomas |  | AB CY 2020 | Building |  | sq.m |  | Project Cost: | 1000000 | Target Completion Date: |  | Program: | 1000000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 1000000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Compl./Rep. Day Care Center, Cabay-angan, B.E. Dujali |  | AB CY 2020 | Building |  | sq.m |  | Project Cost: | 300000 | Target Completion Date: |  | Program: | 300000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 300000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Compl./Rep. Day Care Center, Tanglaw, B.E. Dujali |  | AB CY 2020 | Building |  | sq.m |  | Project Cost: | 300000 | Target Completion Date: |  | Program: | 300000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 300000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Compl./Rep. Day Care Center, Salvacion, Carmen |  | AB CY 2020 | Building |  | sq.m |  | Project Cost: | 300000 | Target Completion Date: |  | Program: | 300000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 300000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Compl./Rep. Day Care Center, San Agustin, IGCS |  | AB CY 2020 | Building |  | sq.m |  | Project Cost: | 300000 | Target Completion Date: |  | Program: | 300000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 300000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Compl./Rep. Day Care Center, Toril, IGCS |  | AB CY 2020 | Building |  | sq.m |  | Project Cost: | 300000 | Target Completion Date: |  | Program: | 300000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 300000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Compl./Rep. Day Care Center, Tibal-og, Sto. Tomas |  | AB CY 2020 | Building |  | sq.m |  | Project Cost: | 600000 | Target Completion Date: |  | Program: | 600000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 600000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Compl./Rep. Day Care Center, Talomo, Sto. Tomas |  | AB CY 2020 | Building |  | sq.m |  | Project Cost: | 300000 | Target Completion Date: |  | Program: | 300000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 300000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Compl./Rep. Day Care Center, Kinamayan, Sto. Tomas |  | AB CY 2020 | Building |  | sq.m |  | Project Cost: | 300000 | Target Completion Date: |  | Program: | 300000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 300000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Compl./Rep. Day Care Center, La Libertad, Sto. Tomas |  | AB CY 2020 | Building |  | sq.m |  | Project Cost: | 300000 | Target Completion Date: |  | Program: | 300000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 300000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Improvement/Rehab. Of Luntiang Paraiso, New Corella |  | 20% DF CY 2020 | Building |  | km |  | Project Cost: | 3000000 | Target Completion Date: |  | Program: | 3000000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | For Purchase Request | For Purchase Request | For Purchase Request | For Purchase Request | For Purchase Request | Procurement on process
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 3000000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Rehab. Of Various Local Roads @ Island Garden City of Samal |  | 20% DF CY 2020 | Rehabilitation |  | km |  | Project Cost: | 2518182 | Target Completion Date: |  | Program: | 2518182 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Plan On-going | Plan On-going | Plan On-going | Plan On-going | Plan On-going | Plan On-going
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 2518182 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Improvement and Desiltation of Camoning Creek |  | 5% Calamity Fund CY 2020 | Desiltation |  | ln.m |  | Project Cost: | 2500000 | Target Completion Date: |  | Program: | 2500000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Abstract # 0520201658 | Abstract # 0520201658 | Abstract # 0520201658 | Abstract # 0520201658 | Abstract # 0520201658 | Abstract # 0520201658
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 2500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Improvement of Saug-Sonlon-Bdry. Longanapan |  | 5% CALAMITY FUND CY 2020 | Road |  | km |  | Project Cost: | 1000000 | Target Completion Date: |  | Program: | 1000000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | For preparation of POW and Plans | For preparation of POW and Plans | For preparation of POW and Plans | For preparation of POW and Plans | For preparation of POW and Plans | For preparation of POW and Plans
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 1000000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Single Barrel Box Culvert at Mangalcal-Diamond Creek, Brgy. Mangalcal, Carmen |  | 5% Calamity Fund CY 2020 | Box Culvert |  | ln.m |  | Project Cost: | 2000000 | Target Completion Date: |  | Program: | 2000000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 2000000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Improvement of Mangalcal to Diamond Creek Farm to Market Road Opening |  | 5% Calamity Fund CY 2020 | Improvement |  | ln.m |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Rehab./Impv't. of Sto. Niño-Daligdigon-Paiton |  | 5% CALAMITY FUND CY 2020 | Road |  | km |  | Project Cost: | 1000000 | Target Completion Date: |  | Program: | 1000000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 1000000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Rehab./Impv't. of San Miguel - Moslog - Kinamayan, Sto. Tomas |  | 5% Calamity Fund CY 2020 | Rehabilitation |  | ln.m |  | Project Cost: | 1000000 | Target Completion Date: |  | Program: | 1000000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 1000000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Const. of 1 Classroom @ Mankay Integrated School, Gupitan, kapalong |  | AB - SEF CY 2020 | Building |  | sq.m |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Opening of Shopping on June 25, 2020 | Opening of Shopping on June 25, 2020 | Opening of Shopping on June 25, 2020 | Opening of Shopping on June 25, 2020 | Opening of Shopping on June 25, 2020 | Procurement on process
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Const. of 1 Classroom @ Luno-luno E/S, Gupitan, kapalong |  | AB - SEF CY 2020 | Building |  | sq.m |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Opening of Shopping on June 25, 2020 | Opening of Shopping on June 25, 2020 | Opening of Shopping on June 25, 2020 | Opening of Shopping on June 25, 2020 | Opening of Shopping on June 25, 2020 | Procurement on process
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Const. of 1 Classroom @ Kamunuan E/S, Gupitan, kapalong |  | AB - SEF CY 2020 | Building |  | sq.m |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Opening of Shopping on June 25, 2020 | Opening of Shopping on June 25, 2020 | Opening of Shopping on June 25, 2020 | Opening of Shopping on June 25, 2020 | Opening of Shopping on June 25, 2020 | Procurement on process
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Const. of 1 Classroom @ Tawinian E/S, Gupitan, kapalong |  | AB - SEF CY 2020 | Building |  | sq.m |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Opening of Shopping on June 25, 2020 | Opening of Shopping on June 25, 2020 | Opening of Shopping on June 25, 2020 | Opening of Shopping on June 25, 2020 | Opening of Shopping on June 25, 2020 | Procurement on process
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Const. of 1 Classroom @ Aninipot E/S, Gupitan, kapalong |  | AB - SEF CY 2020 | Building |  | sq.m |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Opening of Shopping on June 25, 2020 | Opening of Shopping on June 25, 2020 | Opening of Shopping on June 25, 2020 | Opening of Shopping on June 25, 2020 | Opening of Shopping on June 25, 2020 | Procurement on process
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Const. of 1 Classroom @ Moling E/S, Gupitan, kapalong |  | AB - SEF CY 2020 | Building |  | sq.m |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Opening of Shopping on June 25, 2020 | Opening of Shopping on June 25, 2020 | Opening of Shopping on June 25, 2020 | Opening of Shopping on June 25, 2020 | Opening of Shopping on June 25, 2020 | Procurement on process
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Const. of 1 Classroom @ Mangga E/S, Magwawa, Sto. Tomas |  | AB - SEF CY 2020 | Building |  | sq.m |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Opening of Shopping on June 25, 2020 | Opening of Shopping on June 25, 2020 | Opening of Shopping on June 25, 2020 | Opening of Shopping on June 25, 2020 | Opening of Shopping on June 25, 2020 | Procurement on process
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Const. of 1 Classroom @ Lomondong E/S, Dagohoy, Talaingod |  | AB - SEF CY 2020 | Building |  | sq.m |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Opening of Shopping on June 25, 2020 | Opening of Shopping on June 25, 2020 | Opening of Shopping on June 25, 2020 | Opening of Shopping on June 25, 2020 | Opening of Shopping on June 25, 2020 | Procurement on process
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Const. of 1 Classroom @ Malapanit E/S, Sto. Niño, Talaingod |  | AB - SEF CY 2020 | Building |  | sq.m |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Opening of Shopping on June 25, 2020 | Opening of Shopping on June 25, 2020 | Opening of Shopping on June 25, 2020 | Opening of Shopping on June 25, 2020 | Opening of Shopping on June 25, 2020 | Procurement on process
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Const. of 1 Classroom @ Laputlakan E/S, Sto. Niño, Talaingod |  | AB - SEF CY 2020 | Building |  | sq.m |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Opening of Shopping on June 25, 2020 | Opening of Shopping on June 25, 2020 | Opening of Shopping on June 25, 2020 | Opening of Shopping on June 25, 2020 | Opening of Shopping on June 25, 2020 | Procurement on process
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Renovation of Teen Tambayan |  | 20% DF CY 2020 | Building |  | sq.m | Contract | Project Cost: | 500000 | Target Completion Date: | 2020-12-22 | Program: | 500000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: | 100% | No. of Persons: |  | Date of procurement June 30, 2020 | Date of procurement June 30, 2020 | Date of procurement June 30, 2020 | Date of procurement June 30, 2020 | Date of procurement June 30, 2020 | Procurement on process
[7 empty] | Project Engineer: | Quirante | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: | JJR Const. & Supply | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual: | 100%
[7 empty] | Duration: | 69 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed: | 2020-12-22
[7 empty] | Date Started: | 2020-10-14
Proposed Road Opening of Nasilaban - Pongpong Road Section, Talaingod |  | SB # 1 CY 2020 | Road |  | km |  | Project Cost: | 5500000 | Target Completion Date: |  | Program: | 5500000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | PO #2020062105 - M3C CONSTRUCTION & SUPPLY; PO #2020061966 - FL2 LUMBER & CONSTRUCTION SUPPLY; PO #2020062217 - Alpebel Builders and Supply Corporation, PO #DIOCESAN PRINTING PRESS | PO #2020062105 - M3C CONSTRUCTION & SUPPLY; PO #2020061966 - FL2 LUMBER & CONSTRUCTION SUPPLY; PO #2020062217 - Alpebel Builders and Supply Corporation, PO #DIOCESAN PRINTING PRESS | PO #2020062105 - M3C CONSTRUCTION & SUPPLY; PO #2020061966 - FL2 LUMBER & CONSTRUCTION SUPPLY; PO #2020062217 - Alpebel Builders and Supply Corporation, PO #DIOCESAN PRINTING PRESS | PO #2020062105 - M3C CONSTRUCTION & SUPPLY; PO #2020061966 - FL2 LUMBER & CONSTRUCTION SUPPLY; PO #2020062217 - Alpebel Builders and Supply Corporation, PO #DIOCESAN PRINTING PRESS | PO #2020062105 - M3C CONSTRUCTION & SUPPLY; PO #2020061966 - FL2 LUMBER & CONSTRUCTION SUPPLY; PO #2020062217 - Alpebel Builders and Supply Corporation, PO #DIOCESAN PRINTING PRESS | Procurement on process
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 5500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Establishment of Multiplier Farm Phase 2, Brgy. Sto. Niño, Talaingod |  | SB # 1 CY 2020 | Building |  | sq.m |  | Project Cost: | 380000 | Target Completion Date: |  | Program: | 380000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | For bidding on June 30, 2020; Re-bid July 28, 2020. | For bidding on June 30, 2020; Re-bid July 28, 2020. | For bidding on June 30, 2020; Re-bid July 28, 2020. | For bidding on June 30, 2020; Re-bid July 28, 2020. | For bidding on June 30, 2020; Re-bid July 28, 2020. | Procurement on process
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 380000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Establishment of Multiplier Farm (Poultry House), Phase 2, Brgy. Sto. Niño, Talaingod |  | SB # 1 CY 2020 | Building |  | sq.m |  | Project Cost: | 110000 | Target Completion Date: |  | Program: | 110000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | For bidding on June 30, 2020; Re-bid July 28, 2020. | For bidding on June 30, 2020; Re-bid July 28, 2020. | For bidding on June 30, 2020; Re-bid July 28, 2020. | For bidding on June 30, 2020; Re-bid July 28, 2020. | For bidding on June 30, 2020; Re-bid July 28, 2020. | Procurement on process
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 110000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Proposed of 1 Barrel Culvert Along Kapalong-Mabantao-Florida Provincial Road |  | SB # 4 CY 2020 | Building |  | sq.m | Admin | Project Cost: | 1900000 | Target Completion Date: | 0 | Program: | 1900000 | Planned: | 100% | Planned: | 100% | Planned: | 100% | Planned: |  | Planned: |  | No. of Persons: |  | Completed as per physical accomplishment. Financial documents still on process. |  |  |  |  | For preparation of Plan
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 1900000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: | 100% | Actual: | 100% | Actual: | 100% | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Const. of Igangon ES Integrated School (PREFAB), San Isidro |  | SB # 4 CY 2020 | Building |  | sq.m | Admin | Project Cost: | 500000 | Target Completion Date: | 0 | Program: | 500000 | Planned: | 100% | Planned: | 100% | Planned: | 100% | Planned: |  | Planned: |  | No. of Persons: |  | Completed as per physical accomplishment. Financial documents still on process. |  |  |  |  | For preparation of Plan
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: | 100% | Actual: | 100% | Actual: | 100% | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Inst. Of Automatic Fire Sprinkler, Smoke Detection & Fire Alarm System, Old Main Hospitals Bldg, Samal Dist. Hospital |  | SB # 4 CY 2020 | Building |  | sq.m | Admin | Project Cost: | 3000000 | Target Completion Date: | 0 | Program: | 3000000 | Planned: | 100% | Planned: | 100% | Planned: | 100% | Planned: |  | Planned: |  | No. of Persons: |  | Completed as per physical accomplishment. Financial documents still on process. |  |  |  |  | For preparation of Plan
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 3000000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: | 100% | Actual: | 100% | Actual: | 100% | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Const. of 2-Storey Rural Health Unit Bldg, w/safe Birthing Facility, New Corella |  | SB # 4 CY 2020 | Building |  | sq.m | Admin | Project Cost: | 10000000 | Target Completion Date: | 0 | Program: | 10000000 | Planned: | 100% | Planned: | 100% | Planned: | 100% | Planned: |  | Planned: |  | No. of Persons: |  | Completed as per physical accomplishment. Financial documents still on process. |  |  |  |  | For preparation of Plan
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 10000000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: | 100% | Actual: | 100% | Actual: | 100% | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Const. of 2-Storey Rural Health Unit Bldg, w/safe Birthing Facility, Asuncion |  | SB # 4 CY 2020 | Building |  | sq.m | Admin | Project Cost: | 10000000 | Target Completion Date: | 0 | Program: | 10000000 | Planned: | 100% | Planned: | 100% | Planned: | 100% | Planned: |  | Planned: |  | No. of Persons: |  | Completed as per physical accomplishment. Financial documents still on process. |  |  |  |  | For preparation of Plan
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 10000000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: | 100% | Actual: | 100% | Actual: | 100% | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Const. of 2-Storey Rural Health Unit Bldg, w/safe Birthing Facility, Talaingod |  | SB # 4 CY 2020 | Building |  | sq.m | Admin | Project Cost: | 10000000 | Target Completion Date: | 0 | Program: | 10000000 | Planned: | 100% | Planned: | 100% | Planned: | 100% | Planned: |  | Planned: |  | No. of Persons: |  | Completed as per physical accomplishment. Financial documents still on process. |  |  |  |  | For preparation of Plan
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 10000000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: | 100% | Actual: | 100% | Actual: | 100% | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Const. of 2-Storey Rural Health Unit Bldg, w/safe Birthing Facility, Sto. Tomas |  | SB # 4 CY 2020 | Building |  | sq.m | Admin | Project Cost: | 10000000 | Target Completion Date: | 0 | Program: | 10000000 | Planned: | 100% | Planned: | 100% | Planned: | 100% | Planned: |  | Planned: |  | No. of Persons: |  | Completed as per physical accomplishment. Financial documents still on process. |  |  |  |  | For preparation of Plan
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 10000000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: | 100% | Actual: | 100% | Actual: | 100% | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Const. of Infirmary Hospital, Panabo City |  | SB # 4 CY 2020 | Building |  | sq.m | Admin | Project Cost: | 15000000 | Target Completion Date: | 0 | Program: | 15000000 | Planned: | 100% | Planned: | 100% | Planned: | 100% | Planned: |  | Planned: |  | No. of Persons: |  | Completed as per physical accomplishment. Financial documents still on process. |  |  |  |  | For preparation of Plan
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 15000000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: | 100% | Actual: | 100% | Actual: | 100% | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Const. of Dialysis Center with Equipments - Kapalong Hospital |  | SB # 4 CY 2020 | Building |  | sq.m | Admin | Project Cost: | 30000000 | Target Completion Date: | 0 | Program: | 30000000 | Planned: | 100% | Planned: | 100% | Planned: | 100% | Planned: |  | Planned: |  | No. of Persons: |  | Completed as per physical accomplishment. Financial documents still on process. |  |  |  |  | For preparation of Plan
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 30000000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: | 100% | Actual: | 100% | Actual: | 100% | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Const. of Dialysis Center with Equipments - Samal Hospital |  | SB # 4 CY 2020 | Building |  | sq.m | Admin | Project Cost: | 30000000 | Target Completion Date: | 0 | Program: | 30000000 | Planned: | 100% | Planned: | 100% | Planned: | 100% | Planned: |  | Planned: |  | No. of Persons: |  | Completed as per physical accomplishment. Financial documents still on process. |  |  |  |  | For preparation of Plan
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 30000000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: | 100% | Actual: | 100% | Actual: | 100% | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Impv't. of Sto. Tomas Organic Prod'n. Center with Common Service facility, Sto. Tomas |  | SB # 4 CY 2020 | Building |  | sq.m | Admin | Project Cost: | 951204.81 | Target Completion Date: | 2018-12-24 23:59 | Program: | 951204.81 | Planned: | 94.55% | Planned: | 100% | Planned: | 100% | Planned: | 100% | Planned: | 100% | No. of Persons: | 20 | Completed as per physical accomplishment. Financial documents still on process. |  |  |  |  | On-going
[7 empty] | Project Engineer: | Azotes | Revised Completion Date: | May 24, 2021 | Allotment: | 951204.81 | Revised: | 78.32% | Revised: | 83.43% | Revised: | 83.43% | Revised: | 83.43% | Revised: | 22.53% | No. of Man-days:
[7 empty] | Implementor: | Manantan | No. of days suspended: | 501 | Disbursement: |  | Actual: | 71.89% | Actual: | 75.19% | Actual: | 75.19% | Actual: | 75.19% | Actual: | 30.33%
[7 empty] | Duration: | 330 | No. of days extended: |  |  |  | Slippage: | -6.424% | Slippage: | -8.238% | Slippage: | -8.238% | Slippage: | -8.238% | Slippage: | 7.8%
[7 empty] | Date Allotment Released: | CY 2014 | Date completed:
[7 empty] | Date Started: | 2018-01-29
Chocolate Processing, RACO, San Francisco, Panabo City |  | SB # 4 CY 2020 | Building |  | sq.m | Admin | Project Cost: | 3199294.6 | Target Completion Date: | 0 | Program: | 3199294.6 | Planned: | 100% | Planned: | 100% | Planned: | 100% | Planned: |  | Planned: |  | No. of Persons: |  | Completed as per physical accomplishment. Financial documents still on process. |  |  |  |  | Procurement on process
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 3199294.6 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: | 100% | Actual: | 100% | Actual: | 100% | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Rep/Rehab. Of Civil Service Commission Field Office |  | SB # 4 CY 2020 | Building |  | sq.m | Admin | Project Cost: | 290000 | Target Completion Date: | 0 | Program: | 290000 | Planned: | 100% | Planned: | 100% | Planned: | 100% | Planned: |  | Planned: |  | No. of Persons: |  | Completed as per physical accomplishment. Financial documents still on process. |  |  |  |  | For preparation of Plan
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 290000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: | 100% | Actual: | 100% | Actual: | 100% | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Const. and Inst. Of One (1) unit Community-Based Micro Hydropower System and 1,308 units Solar Photovoltaic Homelihtning System in Gupitan, Kapalong & Palma Gil, Talaingod (Improving the Lives of People in Off-Grid Communities in mindanao through the Provinsion of Sustainable Energy) |  | SB # 4 CY 2020 | Building |  | sq.m | Admin | Project Cost: | 2707680 | Target Completion Date: | 0 | Program: | 2707680 | Planned: | 100% | Planned: | 100% | Planned: | 100% | Planned: |  | Planned: |  | No. of Persons: |  | Completed as per physical accomplishment. Financial documents still on process. |  |  |  |  | For preparation of Plan
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 2707680 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: | 100% | Actual: | 100% | Actual: | 100% | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Rehab. Of Manpower Dev't. Center, PEO Sub-Office Bldg., |  | SB # 4 CY 2020 | Building |  | sq.m | Admin | Project Cost: | 1590000 | Target Completion Date: | 0 | Program: | 1590000 | Planned: | 100% | Planned: | 100% | Planned: | 100% | Planned: |  | Planned: |  | No. of Persons: |  | Completed as per physical accomplishment. Financial documents still on process. |  |  |  |  | For preparation of Plan
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 1590000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: | 100% | Actual: | 100% | Actual: | 100% | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Const. of retaining Wall, Brgy. Sto. Niño, Talaingod |  | SB # 4 CY 2020 | Building |  | sq.m | Admin | Project Cost: | 500000 | Target Completion Date: | 0 | Program: | 500000 | Planned: | 100% | Planned: | 100% | Planned: | 100% | Planned: |  | Planned: |  | No. of Persons: |  | Completed as per physical accomplishment. Financial documents still on process. |  |  |  |  | For preparation of Plan
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: | 100% | Actual: | 100% | Actual: | 100% | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Const. of Satellite market, Brgy. Pagsabangan, Tagum City |  | SB # 4 CY 2020 | Building |  | sq.m | Admin | Project Cost: | 238125 | Target Completion Date: | 0 | Program: | 238125 | Planned: | 100% | Planned: | 100% | Planned: | 100% | Planned: |  | Planned: |  | No. of Persons: |  | Completed as per physical accomplishment. Financial documents still on process. |  |  |  |  | For preparation of Plan
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 238125 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: | 100% | Actual: | 100% | Actual: | 100% | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Const. of DAVNOR Tech-Vocational Training Center |  | SB # 4 CY 2020 | Building |  | sq.m | Admin | Project Cost: | 29000000 | Target Completion Date: | 0 | Program: | 29000000 | Planned: | 100% | Planned: | 100% | Planned: | 100% | Planned: |  | Planned: |  | No. of Persons: |  | Completed as per physical accomplishment. Financial documents still on process. |  |  |  |  | For preparation of Plan
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 29000000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: | 100% | Actual: | 100% | Actual: | 100% | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Const./Establishment of Integrated Solid Waste Management Facility |  | SB # 4 CY 2020 | Building |  | sq.m | Admin | Project Cost: | 50000000 | Target Completion Date: | 0 | Program: | 50000000 | Planned: | 100% | Planned: | 100% | Planned: | 100% | Planned: |  | Planned: |  | No. of Persons: |  | Completed as per physical accomplishment. Financial documents still on process. |  |  |  |  | For preparation of Plan
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 50000000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: | 100% | Actual: | 100% | Actual: | 100% | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Road Improvement of Jct. Highway Gabuyan – Semong – Dagohoy Provincial Road |  | CMGP CY 2020 | Road |  | km |  | Project Cost: | 63458000 | Target Completion Date: |  | Program: | 63458000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | No. of Persons: |  | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | For implementtation
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 63458000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Road Improvement of Feeder Road 3- San Jose Provincial Road |  | CMGP CY 2020 | Road |  | km | Contract | Project Cost: | 53991806 | Target Completion Date: | 0 | Program: | 53991806 | Planned: | [7 empty] | No. of Persons: |  | No. of Persons: |  | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | For implementtation
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 53991806 | Revised: | [7 empty] | No. of Man-days: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage:
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Rehabilitation of New Visayas - Tulalian, Sto. Tomas |  | PRDP CY 2020 | Road |  | km | Contract | Project Cost: | 215000000 | Target Completion Date: | 0 | Program: | 215000000 | Planned: | [7 empty] | No. of Persons: |  | No. of Persons: |  | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | POW and DED on-going review (c/o RPCO)
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 215000000 | Revised: | [7 empty] | No. of Man-days: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage:
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Const. of Chocolate Pprocessing Building, San Francisco, Panabo City (REHOBOTH) |  | PRDP - I-REAP CY 2020 | Road |  | km | Contract | Project Cost: | 6072010.87 | Target Completion Date: | 0 | Program: | 6072010.87 | Planned: | [7 empty] | No. of Persons: |  | No. of Persons: |  | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | For bidding
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 6072010.87 | Revised: | [7 empty] | No. of Man-days: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage:
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Note on D263: Cerela Montes: Previously 20% DF CY 2019 (STIMULUS)
Note on B371: chai: Previously Concreting of Drainage Canal, Poblacion, New Corella
Note on D377: previously 20% DF CY 2019
Note on D383: previously 20% DF CY 2019
Note on D389: chai: Previously Perimeter Fence of Day Care Center I & II, Nanyo, Panabo City (20% Development Fund CY 2018 (STIMULUS 2018)
Note on D395: chai: Previously Perimeter Fence of Day Care Center I & II, Nanyo, Panabo City (20% Development Fund CY 2018 (STIMULUS 2018)
Note on D401: chai: Previously Perimeter Fence of Day Care Center I & II, Nanyo, Panabo City (20% Development Fund CY 2018 (STIMULUS 2018)
Note on D419: chai: previously 20% DF
Note on D425: chai: previously 20% DF
Note on D443: chai: 20% DF CY 2019

## 4th Quarter CY 2020 (Completed)
|  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | [11 empty] | 0
` | ECONOMIC (INFRASTRUCTURE DEV'T. PROGRAM)
OFFICE/AGENCY: | PROVINCIAL ENGINEER'S OFFICE
AREA: | 1ST ENGINEERING DISTRICT - COMPLETED, ON-GOING AND FOR IMPLEMENTATION PROJECTS | [7 empty] | Total extended
#REF!
#REF!
NAME OF PROJECT |  | SOURCE OF FUND | TYPE OF PROJECT | PHYSICAL TARGET (DESCRIPTION) |  | MODE OF IMPLEMENTATION | PROJECT DATA |  |  |  | FINANCIAL |  | PHYSICAL ACCOMPLISHMENT (JULY) |  | PHYSICAL ACCOMPLISHMENT (AUGUST) |  | PHYSICAL ACCOMPLISHMENT (SEPTEMBER) |  | PHYSICAL ACCOMPLISHMENT (OCTOBER) |  | PHYSICAL ACCOMPLISHMENT |  | EMPLOYMENT GENERATED |  | REMARKS (JULY) | REMARKS (AUGUST) | REMARKS (SEPTEMBER) | REMARKS (OCTOBER | REMARKS (NOVEMBER) | REMARKS
Rehab. of Esperanza-Pob. Sto. Tomas, FMR, DDN |  | PRDP CY 2014 | Road Concreting | 12.774 | km | Contract | Project Cost: | 117410426.3 | Target Completion Date: | 2019-07-22 23:59 | Program: | 117410426.3 | Planned: | 100% | Planned: | 100% | Planned: | 100% | Planned: | 100% | Planned: | 100% | No. of Persons: | 20 | On-going (Waiting for approve Variation order for billing) | On-going (Waiting for approve Variation order for billing) | On-going (Waiting for approve Variation order for billing) | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per Program of Works
[7 empty] | Project Engineer: | Palero | Revised Completion Date: | 2020-09-23 23:59 | Allotment: | 117410426.3 | Revised: | 95.53% | Revised: | 100% | Revised: | 100% | Revised: | 100% | Revised: | 100% | No. of Man-days: | 600
[7 empty] | Implementor: | ALZAM | No. of days suspended: |  | Disbursement: | 105669383.67 | Actual: | 87.82% | Actual: | 97% | Actual: | 97% | Actual: | 100% | Actual: | 100%
[7 empty] | Duration: | 853 | No. of days extended: | 429 |  |  | Slippage: | -7.705% | Slippage: | -3% | Slippage: | -3% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: | CY 2014 | Date completed: | 2020-10-23
[7 empty] | Date Started: | 2017-03-22
Improvement of New Corella Nursery with Organic Input Production & Common Facility, Davao del Norte |  | PRDP CY 2016 | Building | 1901 | sq.m | Contract | Project Cost: | 9889628.45 | Target Completion Date: | 2019-11-23 | Program: | 9889628.45 | Planned: | 94.55% | Planned: | 100% | Planned: | 100% | Planned: | 100% | Planned: | 100% | No. of Persons: |  | Fund already transferred at Municipality of Talaingod with ChecK No. 2445181 and OR # 7955667, dated March 16, 2018 . Amended from Electrification @ Prk. 1A-Prk. 5A) | On-going (Implemented by MLGU, since transfer of fund ) | On-going (Implemented by MLGU, since transfer of fund ) | Completed as per physical accomplishment. | Completed as per physical accomplishment. | Completed as per Program of Works
[7 empty] | Project Engineer: | Delos Reyes/Cabañero | Revised Completion Date: | 2020-08-09 | Allotment: | 9889628.45 | Revised: | 78.32% | Revised: | 83.43% | Revised: | 83.43% | Revised: | 83.43% | Revised: |  | No. of Man-days:
[7 empty] | Implementor: | SOUTH IRONROCK CORPORATION | No. of days suspended: | 260 | Disbursement: | 5933777.07 | Actual: | 71.89% | Actual: | 75.19% | Actual: | 75.19% | Actual: | 75.19% | Actual: | 100%
[7 empty] | Duration: | 310 | No. of days extended: |  |  |  | Slippage: | -6.424% | Slippage: | -8.238% | Slippage: | -8.238% | Slippage: | -8.238% | Slippage: | 0%
[7 empty] | Date Allotment Released: | CY 2016 | Date completed: | 2020-10-31
[7 empty] | Date Started: | 2019-01-17
Rural Electrification at Del Monte, New Corella |  | 20% DF CY 2018 | Electrification |  |  | Contract | Project Cost: | 1000000 | Target Completion Date: |  | Program: | 1000000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: | 100% | No. of Persons: |  | Post Qualification on process | Post Qualification on process | For implementation (Awarded to 3E Electirical and Engineering) | For implementation (Awarded to 3E Electirical and Engineering) | For implementation (Awarded to 3E Electirical and Engineering) | Completed as per Program of Works
[7 empty] | Project Engineer: | Bueno | Revised Completion Date: | 0 | Allotment: | 1000000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: | 3E Electirical and Engineering | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual: | 100%
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed: | 2020-12-03
[7 empty] | Date Started: | 2020-11-20
Completion of Canopy at DAPCO Covered Court, Dapco, Panabo City |  | 20% DF CY 2018 (STIMULUS) | Court |  |  | Contract | Project Cost: | 500000 | Target Completion Date: | 2020-10-08 | Program: | 500000 | Planned: |  | Planned: |  | Planned: |  | Planned: | 100% | Planned: | 100% | No. of Persons: |  | (RLHV Design & Build) Winning Bidder | (RLHV Design & Build) Winning Bidder | For implementation (RLHV Design & Build) | Completed as per physical accomplishment. | Completed as per physical accomplishment. | Completed as per Program of Works
[7 empty] | Project Engineer: | Estorco | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: | RLHV | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: | 100% | Actual: | 100%
[7 empty] | Duration: | 184 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed: | 2020-10-08
[7 empty] | Date Started: | 2020-04-07
Powerline Expansion Project, Cogon, IGACOS |  | 20% DF CY 2018 (STIMULUS) | Water System |  |  | Contract | Project Cost: | 500000 | Target Completion Date: | 2020-08-21 | Program: | 500000 | Planned: |  | Planned: |  | Planned: |  | Planned: | 100% | Planned: | 100% | No. of Persons: |  | Waiting for NTP (3E Electrical) | Waiting for NTP (3E Electrical) | Waiting for NTP (3E Electrical) | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per Program of Works
[7 empty] | Project Engineer: | Porras | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: | 3E Electrical Sales | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: | 100% | Actual: | 100%
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed: | 2020-12-12
[7 empty] | Date Started: | 2020-08-05
Const. of DDN Hospital Carmen Zone Annex Bldg. |  | SB # 1 CY 2018 | Building |  | sq.m | Contract | Project Cost: | 5500000 | Target Completion Date: | 2020-07-15 | Program: | 5500000 | Planned: | 95.2% | Planned: | 100% | Planned: | 100% | Planned: | 100% | Planned: | 100% | No. of Persons: | 10 | On-going | On-going | On-going | Completed as per physical accomplishment. | Completed as per physical accomplishment. | Completed as per Program of Works
[7 empty] | Project Engineer: | Azotes | Revised Completion Date: | 2020-09-10 | Allotment: | 5500000 | Revised: | 40.5% | Revised: | 99.09% | Revised: | 100% | Revised: | 100% | Revised: | 100% | No. of Man-days: | 260
[7 empty] | Implementor: | Digos Constrak Corp/ | No. of days suspended: | 57 | Disbursement: | 1650000 | Actual: | 68.25% | Actual: | 90.62% | Actual: | 94.99% | Actual: | 100% | Actual: | 100%
[7 empty] | Duration: | 120 | No. of days extended: |  |  |  | Slippage: | 27.75% | Slippage: | -8.47% | Slippage: | -5.01% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed: | 2020-10-12
[7 empty] | Date Started: | 2020-03-17
Rehab./Impv't. of Jct. highway Ising-Magsaysay Provincial Road with Drainage |  | 20% DF CY 2019 | Road Drainage rehabiliated |  | km | Admin | Project Cost: | 1500000 | Target Completion Date: | 2020-08-31 | Program: | 1500000 | Planned: |  | Planned: |  | Planned: | 100% | Planned: | 100% | Planned: | 100% | No. of Persons: | 1 | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per Program of Works
[7 empty] | Project Engineer: | Toquero | Revised Completion Date: | 2020-12-31 | Allotment: | 1500000 | Revised: |  | Revised: |  | Revised: | 32.32% | Revised: |  | Revised: |  | No. of Man-days: | 4
[7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: | 35.6% | Actual: | 100% | Actual: | 100%
[7 empty] | Duration: | 61 | No. of days extended: | 122 |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 3.28% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: | 2019-01-16 | Date completed: | 2020-12-31
[7 empty] | Date Started: | 2020-07-01
Installation of Shallow Tube Wells & Const. of Machinery Shed |  | 20% DF CY 2019 | Water System |  |  | Admin | Project Cost: | 1600000 | Target Completion Date: | 2020-11-30 23:59 | Program: | 1600000 | Planned: |  | Planned: | 10.59% | Planned: |  | Planned: | 100% | Planned: | 100% | No. of Persons: | 7 | Opening of BID for Negotiated 6/18,2020 to alpebel | On-going | On-going | Completed as per physical accomplishment. | Completed as per physical accomplishment. | Completed as per Program of Works
[7 empty] | Project Engineer: | Aclaracion | Revised Completion Date: |  | Allotment: | 1600000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 95
[7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: | 9.73% | Actual: |  | Actual: | 100% | Actual: | 100%
[7 empty] | Duration: | 120 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | -0.86% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed: | 2020-12-15
[7 empty] | Date Started: | 2020-08-03
Const. of Perimeter Fence at Sto. Niño Naseco Integrated School w/ Tugas Extension, Sto. Niño, Talaingod |  | 20% DF CY 2019 | Building |  | sq.m | Admin | Project Cost: | 2000000 | Target Completion Date: | 2020-06-09 23:46 | Program: | 2000000 | Planned: | 100% | Planned: | 100% | Planned: | 100% | Planned: | 100% | Planned: | 100% | No. of Persons: | 12 | On-going (Suspended last April 5, 2020 due to COVID; resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID; resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID; resumption order dated May 4, 2020) | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per Program of Works
[7 empty] | Project Engineer: | Torrecampo | Revised Completion Date: | 2020-10-15 23:46 | Allotment: | 2000000 | Revised: | 55.86% | Revised: | 78.13% | Revised: | 92% | Revised: |  | Revised: |  | No. of Man-days: | 180
[7 empty] | Implementor: | PEO | No. of days suspended: | 28 | Disbursement: | 1117200 | Actual: | 55.86% | Actual: | 78.13% | Actual: | 98.96% | Actual: | 100% | Actual: | 100%
[7 empty] | Duration: | 100 | No. of days extended: | 100 |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 6.96% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: | 2019-06-19 | Date completed: | 2020-10-15
[7 empty] | Date Started: | 2020-03-02
Const. of Drainage Canal, Bincungan, Tagum City |  | 20% DF CY 2019 (STIMULUS) | Drainage |  |  | Contract | Project Cost: | 500000 | Target Completion Date: | 2021-02-13 | Program: | 500000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: | 100% | No. of Persons: |  | For implementation | For implementation | For implementation | For implementation | For implementation | Completed as per Program of Works
[7 empty] | Project Engineer: | Quirante | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: | JJR Construction | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual: | 100%
[7 empty] | Duration: | 150 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: | 2019-09-10 | Date completed: | 2020-10-08
[7 empty] | Date Started: | 2020-09-16
Completion. of Water System , Busaon, Tagum City |  | 20% DF CY 2019 (STIMULUS) | Water System |  |  | Contract | Project Cost: | 500000 | Target Completion Date: | 2020-12-12 | Program: | 500000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: | 100% | No. of Persons: |  | For implementation | For implementation | For implementation | For implementation | For implementation | Completed as per Program of Works
[7 empty] | Project Engineer: | Quirante | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: | JJR Construction | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual: | 100%
[7 empty] | Duration: | 150 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: | 2019-09-10 | Date completed: | 2020-11-04
[7 empty] | Date Started: | 2020-07-15
Rehab. of Evacuation Center, Mankilam, Tagum City |  | 20% DF CY 2019 (STIMULUS) | Building |  |  | Contract | Project Cost: | 500000 | Target Completion Date: | 2020-10-30 | Program: | 500000 | Planned: | 100% | Planned: | 100% | Planned: | 100% | Planned: | 100% | Planned: | 100% | No. of Persons: |  | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per Program of Works
[7 empty] | Project Engineer: | Juan | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: | JJR Construction | No. of days suspended: |  | Disbursement: |  | Actual: | 100% | Actual: | 100% | Actual: | 100% | Actual: | 100% | Actual: | 100%
[7 empty] | Duration: | 106 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed: | 2020-10-30
[7 empty] | Date Started: | 2020-07-16
Rehab. of Evacuation Center, New Balambam, Tagum City |  | 20% DF CY 2019 (STIMULUS) | Building |  |  | Contract | Project Cost: | 500000 | Target Completion Date: | 2021-01-29 | Program: | 500000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: | 100% | No. of Persons: |  | For implementation | For implementation | For implementation | For implementation | For implementation | Completed as per Program of Works
[7 empty] | Project Engineer: | Juan | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: | JJR Construction | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual: | 100%
[7 empty] | Duration: | 150 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: | 2019-09-10 | Date completed: | 2020-10-02
[7 empty] | Date Started: | 2020-09-01
Rehab. Of Evacuation Center, Casig-ang, Sto. Tomas |  | 20% DF CY 2019 (STIMULUS | Building |  |  | Contract | Project Cost: | 500000 | Target Completion Date: | 2021-01-16 | Program: | 500000 | Planned: |  | Planned: |  | Planned: |  | Planned: | 12.3% | Planned: | 100% | No. of Persons: | 5 | On-going | PR #20063670 | Revision of POW on-going | On-going | On-going | Completed as per Program of Works
[7 empty] | Project Engineer: | Estorco | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 110
[7 empty] | Implementor: | JJR Const. & Supply | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: | 13.6% | Actual: | 100%
[7 empty] | Duration: | 100 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 1.3% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed: | 2020-11-13
[7 empty] | Date Started: | 2020-10-08
Rehab. Of Evacuation Center, JP Laurel, Panabo City |  | 20% DF CY 2019 (STIMULUS | Building |  |  |  | Project Cost: | 500000 | Target Completion Date: | 2020-12-05 | Program: | 500000 | Planned: |  | Planned: |  | Planned: |  | Planned: | 100% | Planned: | 100% | No. of Persons: | 5 | On-going | PR #20063670 | Revision of POW on-going | Completed as per physical accomplishment. | Completed as per physical accomplishment. | Completed as per Program of Works
[7 empty] | Project Engineer: | Andoy | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 110
[7 empty] | Implementor: | Digos Constrak Corp | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: | 100% | Actual: | 100%
[7 empty] | Duration: | 100 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed: | 2020-12-02
[7 empty] | Date Started: | 2020-08-27
Rural Electrification , Del Monte, New Corella |  | 20% DF CY 2019 | Electrification |  |  |  | Project Cost: | 3000000 | Target Completion Date: | 2020-09-20 23:46 | Program: | 3000000 | Planned: | 43% | Planned: | 43% | Planned: | 43% | Planned: | 43% | Planned: | 100% | No. of Persons: |  | On-going | On-going | On-going | On-going | On-going | Completed as per Program of Works
[7 empty] | Project Engineer: | P.Bueno | Revised Completion Date: | 2020-09-20 23:46 | Allotment: | 3000000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: | Tagum Builders | No. of days suspended: |  | Disbursement: |  | Actual: | 43% | Actual: | 43% | Actual: | 43% | Actual: | 43% | Actual: | 100%
[7 empty] | Duration: | 225 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed: | 2020-12-03
[7 empty] | Date Started: | 2020-02-09
Const. of Multi-Purpose Hall, Southern Davao, Panabo City |  | 20% DF CY 2019 (STIMULUS | Building |  |  | Contract | Project Cost: | 500000 | Target Completion Date: | 2020-12-25 | Program: | 500000 | Planned: |  | Planned: |  | Planned: | 42.3% | Planned: | 100% | Planned: | 100% | No. of Persons: | 4 | Abstract #0520201798 | On-going | On-going | Completed as per physical accomplishment. Financial documents still on process | Completed as per physical accomplishment. Financial documents still on process | Completed as per Program of Works
[7 empty] | Project Engineer: | Abayon | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 88
[7 empty] | Implementor: | Digos Constrak Corp/ | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: | 50.1% | Actual: | 100% | Actual: | 100%
[7 empty] | Duration: | 120 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 7.8% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed: | 2020-10-07
[7 empty] | Date Started: | 2020-08-27
Rehab. Of Multi-Purpose Hall, San Vicente, Sto. Tomas |  | 20% DF CY 2019 (STIMULUS | Building |  |  | Contract | Project Cost: | 500000 | Target Completion Date: | 2020-12-25 | Program: | 500000 | Planned: |  | Planned: |  | Planned: | 23.2% | Planned: | 100% | Planned: | 100% | No. of Persons: |  | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per Program of Works
[7 empty] | Project Engineer: | Comidoy | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: | Digos Constrak Corp | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: | 5% | Actual: | 100% | Actual: | 100%
[7 empty] | Duration: | 120 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | -18.2% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: | 2019-06-07 | Date completed: | 2020-11-24
[7 empty] | Date Started: | 2020-08-27
Rehab. Of Multi-Purpose Hall, New Katipunan, Sto. Tomas |  | 20% DF CY 2019 (STIMULUS | Building |  |  | Contract | Project Cost: | 500000 | Target Completion Date: | 2020-12-05 | Program: | 500000 | Planned: |  | Planned: |  | Planned: | 23.2% | Planned: |  | Planned: | 100% | No. of Persons: |  | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. |  |  | Completed as per Program of Works
[7 empty] | Project Engineer: | Abayon | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: | Digos Constrak Corp | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: | 5% | Actual: |  | Actual: | 100%
[7 empty] | Duration: | 120 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | -18.2% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: | 2019-06-07 | Date completed: | 2020-11-24
[7 empty] | Date Started: | 2020-08-07
Const. Of Multi-Purpose Hall, San Antonio, IGCS |  | 20% DF CY 2019 (STIMULUS | Building |  |  | Admin | Project Cost: | 500000 | Target Completion Date: | 2020-05-12 | Program: | 500000 | Planned: |  | Planned: |  | Planned: | 100% | Planned: | 100% | Planned: | 100% | No. of Persons: | 5 | Resume 5/11/2020 Time extension on process | Resume 5/11/2020 Time extension on process | Resume 5/11/2020 Time extension on process | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per Program of Works
[7 empty] | Project Engineer: | Obar | Revised Completion Date: | 2020-06-14 | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 50
[7 empty] | Implementor: | Admin | No. of days suspended: | 34 | Disbursement: |  | Actual: |  | Actual: |  | Actual: | 47.87% | Actual: | 100% | Actual: | 100%
[7 empty] | Duration: | 50 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | -52.13% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: | 2019-06-19 | Date completed: | 2020-10-15
[7 empty] | Date Started: | 2020-03-23
Rehab. Of Health Center, Aumbay, IGCS |  | 20% DF CY 2019 (STIMULUS | Building |  |  |  | Project Cost: | 500000 | Target Completion Date: | 2019-10-31 | Program: | 500000 | Planned: |  | Planned: |  | Planned: |  | Planned: | 100% | Planned: | 100% | No. of Persons: |  | Re aligned to other stimulus projects that needs additional funding | Re aligned to other stimulus projects that needs additional funding | Re aligned to other stimulus projects that needs additional funding | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per Program of Works
[7 empty] | Project Engineer: | Estorco | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: | 100% | Actual: | 100%
[7 empty] | Duration: | 113 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed: | 2019-10-31
[7 empty] | Date Started: | 2019-07-10
Rehab. Of Brgy. Health Center, Mambago-A, IGCS |  | 20% DF CY 2019 (STIMULUS | Building |  |  |  | Project Cost: | 500000 | Target Completion Date: | 2019-10-25 | Program: | 500000 | Planned: |  | Planned: |  | Planned: |  | Planned: | 100% | Planned: | 100% | No. of Persons: |  | Re aligned to other stimulus projects that needs additional funding | Re aligned to other stimulus projects that needs additional funding | Re aligned to other stimulus projects that needs additional funding | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per Program of Works
[7 empty] | Project Engineer: | Estorco | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: | 100% | Actual: | 100%
[7 empty] | Duration: | 107 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed: | 2019-10-25
[7 empty] | Date Started: | 2019-07-10
Compl.of Brgy. Public Market, La Libertad, Sto. Tomas |  | 20% DF CY 2019 (STIMULUS | Building |  |  |  | Project Cost: | 500000 | Target Completion Date: | 2019-11-30 | Program: | 500000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: | 100% | No. of Persons: |  | Fund transfer to LGU - 6/26/219 with check no. 2575131 and OR no. 0557457 Completed/ PCR for submission by LGU | Fund transfer to LGU - 6/26/219 with check no. 2575131 and OR no. 0557457 Completed/ PCR for submission by LGU | Completed (Implemented by MLGU, since transfer of fund ) | Completed (Implemented by MLGU, since transfer of fund ) | Completed (Implemented by MLGU, since transfer of fund ) | Completed (Implemented by MLGU, since transfer of fund )
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual: | 100%
[7 empty] | Duration: | 26 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed: | 2019-11-30
[7 empty] | Date Started: | 2019-11-04
Completion of Electrification at at Purok 10 and Purok 9, Phase 2, Brgy. Doña Andrea, Asuncion |  | 20% Development Fund CY 2020 | Electrification |  | km |  | Project Cost: | 1000000 | Target Completion Date: |  | Program: | 1000000 | Planned: |  | Planned: | 100% | Planned: | 100% | Planned: | 100% | Planned: | 100% | No. of Persons: |  | For preparation of POW and Plans | Completed (Implemented by MLGU, since transfer of fund ) | Completed (Implemented by MLGU, since transfer of fund ) | Completed (Implemented by MLGU, since transfer of fund ) | Completed (Implemented by MLGU, since transfer of fund ) | Completed (Implemented by MLGU, since transfer of fund )
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 1000000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: | 100% | Actual: | 100% | Actual: | 100% | Actual: | 100%
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Rehab/Impvt of Gymnasium, Sagayen, Asuncion |  | SB No. 1 CY 2019 (STIMULUS) | Building |  |  | Contract | Project Cost: | 1500000 | Target Completion Date: | 2020-10-01 23:59 | Program: | 1500000 | Planned: |  | Planned: |  | Planned: |  | Planned: | 100% | Planned: | 100% | No. of Persons: |  | Final Abstract # 0320200900 (Alpebel Builders & Supply Corp.) | Final Abstract # 0320200900 (Alpebel Builders & Supply Corp.) | Final Abstract # 0320200900 (Alpebel Builders & Supply Corp.) | Completed as per physical accomplishment. | Completed as per physical accomplishment. | Completed as per Program of Works
[7 empty] | Project Engineer: | Kabingue | Revised Completion Date: |  | Allotment: | 1500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: | Alpebel Builders and Const. Supply | No. of days suspended: |  | Disbursement: | 1500000 | Actual: |  | Actual: |  | Actual: |  | Actual: | 100% | Actual: | 100%
[7 empty] | Duration: | 77 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed: | 2020-10-01 23:59
[7 empty] | Date Started: | 2020-07-17
Concreting of FMR, New Santiago, Asuncion |  | SB No. 1 CY 2019 (STIMULUS) | Electrification |  |  | MLGU | Project Cost: | 2500000 | Target Completion Date: |  | Program: | 2500000 | Planned: | 100% | Planned: | 100% | Planned: | 100% | Planned: |  | Planned: | 100% | No. of Persons: |  | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | COMPLETED - PCR & other completion documents for submission PCR, SWA, Before and after Pictures | COMPLETED - PCR & other completion documents for submission PCR, SWA, Before and after Pictures | COMPLETED - PCR & other completion documents for submission PCR, SWA, Before and after Pictures
[7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 2500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: | 100% | Actual: | 100% | Actual: | 100% | Actual: |  | Actual: | 100%
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Construction of Multi-Purpose Building, Balagunan, Sto. Tomas |  | SB # 4 CY 2019 (STIMULUS) | Building |  |  |  | Project Cost: | 500000 | Target Completion Date: | 2020-12-25 | Program: | 500000 | Planned: |  | Planned: | 65.93% | Planned: | 65.1% | Planned: | 100% | Planned: | 100% | No. of Persons: | 6 | For implementation | On-going | On-going | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per Program of Works
[7 empty] | Project Engineer: | Azotes | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 132
[7 empty] | Implementor: | Digos Constrak Corp | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: | 65.93% | Actual: | 74.25% | Actual: | 100% | Actual: | 100%
[7 empty] | Duration: | 120 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 9.15% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed: | 2020-10-02
[7 empty] | Date Started: | 2020-08-27
Concreting of Drainage, Tanglaw, B.E., Dujali (Note: Additional Fund Php700,000.00) |  | SB # 4 CY 2019 (STIMULUS | Concreting |  |  | Contract | Project Cost: | 1200000 | Target Completion Date: | 2020-12-29 | Program: | 1200000 | Planned: |  | Planned: |  | Planned: | 43.5% | Planned: | 100% | Planned: | 100% | No. of Persons: | 4 | For implementation | On-going | On-going | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per Program of Works
[7 empty] | Project Engineer: | Estorco | Revised Completion Date: |  | Allotment: | 1200000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 88
[7 empty] | Implementor: | DANIMERH CONST. & SUPPLY | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: | 12.3% | Actual: | 100% | Actual: | 100%
[7 empty] | Duration: | 120 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | -31.2% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed: | 2020-10-30
[7 empty] | Date Started: | 2020-08-31
Const. of Canal Lining at Purok 5, Salvacion, Panabo City (Note: Additional Fund Php 100,000.00) |  | SB # 4 (20% DF CY 2019 STIMULUS) | Building |  |  | Contract | Project Cost: | 600000 | Target Completion Date: | 2020-12-29 | Program: | 600000 | Planned: |  | Planned: |  | Planned: | 33.2% | Planned: | 100% | Planned: | 100% | No. of Persons: | 5 | PO #2020041516- DANIMERH CONSTRUCTION & SUPPLY | On-going | On-going | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per Program of Works
[7 empty] | Project Engineer: | Estorco | Revised Completion Date: |  | Allotment: | 600000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 110
[7 empty] | Implementor: | DANIMERH CONST. & SUPPLY | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: | 65.3% | Actual: | 100% | Actual: | 100%
[7 empty] | Duration: | 120 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 32.1% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: | 2019-10-18 | Date completed: | 2020-11-16
[7 empty] | Date Started: | 2020-08-31
Construction of Multi-Purpose Hall, Waterfall, Panabo City (Note: Additional Fund Php 550,000.00) |  | SB # 4 CY 2019 (STIMULUS | Building |  |  |  | Project Cost: | 1050000 | Target Completion Date: | 2020-10-26 23:59 | Program: | 1050000 | Planned: |  | Planned: |  | Planned: |  | Planned: | 100% | Planned: | 100% | No. of Persons: |  | For implementation | For implementation | For implementation | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per Program of Works
[7 empty] | Project Engineer: | Abayon | Revised Completion Date: |  | Allotment: | 1050000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: | Digos Constrak Corp | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: | 100% | Actual: | 100%
[7 empty] | Duration: | 55 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed: | 2020-10-26 23:59
[7 empty] | Date Started: | 2020-09-02
Rehabilitation of Brgy. Health Center, Dalisay, Panabo City (Noted: Additional Fund Php 50,000.00) |  | SB # 4 CY 2019 (STIMULUS | Building |  |  |  | Project Cost: | 550000 | Target Completion Date: | 2020-10-05 | Program: | 550000 | Planned: |  | Planned: |  | Planned: |  | Planned: | 100% | Planned: | 100% | No. of Persons: |  | For implementation | For implementation | For implementation | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per Program of Works
[7 empty] | Project Engineer: | Abayon | Revised Completion Date: |  | Allotment: | 550000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: | Digos Constrak Corp | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: | 100% | Actual: | 100%
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed: | 2020-10-05
[7 empty] | Date Started: | 2020-09-02
Rehab. Of Multi-Purpose Hall, San Miguel, Sto. Tomas |  | SB # 4 CY 2019 (STIMULUS | Building |  |  | Contract | Project Cost: | 500000 | Target Completion Date: | 2020-11-11 | Program: | 500000 | Planned: |  | Planned: |  | Planned: | 68.5% | Planned: | 68.5% | Planned: | 100% | No. of Persons: | 6 | For implementation | On-going | On-going | On-going | On-going | Completed as per Program of Works
[7 empty] | Project Engineer: | Estorco | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 132
[7 empty] | Implementor: | JJR Const. & Supply | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: | 75.6% | Actual: | 75.6% | Actual: | 100%
[7 empty] | Duration: | 120 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 7.1% | Slippage: | 7.1% | Slippage: | 0%
[7 empty] | Date Allotment Released: | 2019-06-07 | Date completed: | 2020-10-28
[7 empty] | Date Started: | 2020-07-14
Construction of Evacuation Center at Purok 1-C Brgy. Sto. Niño, Carmen |  | SB # 4 CY 2019 (STIMULUS | Building |  |  |  | Project Cost: | 500000 | Target Completion Date: | 2020-12-25 | Program: | 500000 | Planned: |  | Planned: |  | Planned: |  | Planned: | 36.15% | Planned: | 100% | No. of Persons: | 5 | For implementation | For implementation | For implementation | On-going | On-going | Completed as per Program of Works
[7 empty] | Project Engineer: | Estorco | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 110
[7 empty] | Implementor: | Digos Constrak Corp | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: | 30.6% | Actual: | 100%
[7 empty] | Duration: | 120 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | -5.55% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed: | 2020-11-13
[7 empty] | Date Started: | 2020-08-27
Rehab. Of Evacuation Center, Datu Abdul Dadia, Panabo City (Note: Additional Fund Php 150,000.00) |  | SB # 4 (20% DF CY 2019 (STIMULUS) | Building |  |  | Contract | Project Cost: | 650000 | Target Completion Date: | 2021-02-03 | Program: | 650000 | Planned: |  | Planned: |  | Planned: | 5% | Planned: | 21.2% | Planned: | 100% | No. of Persons: | 6 | Purchase Order # 2020031248- DIGOS CONSTRAK | For implementation (DIGOS CONSTRAK) | On-going | On-going | On-going | Completed as per Program of Works
[7 empty] | Project Engineer: | Andoy | Revised Completion Date: |  | Allotment: | 650000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 132
[7 empty] | Implementor: | Digos Constrak Corp/ | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: | 5% | Actual: | 8.26% | Actual: | 100%
[7 empty] | Duration: | 160 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | -12.94% | Slippage: | 0%
[7 empty] | Date Allotment Released: | 2019-10-18 | Date completed: | 2020-12-02
[7 empty] | Date Started: | 2020-08-27
Rehabilitation of Evacuation Center, Cagangohan, Panabo City |  | SB # 4 CY 2019 (20% DF -STIMULUS) | Building |  |  |  | Project Cost: | 500000 | Target Completion Date: | 2020-12-25 | Program: | 500000 | Planned: |  | Planned: | 69.53% | Planned: | 54.2% | Planned: | 100% | Planned: | 100% | No. of Persons: | 6 | Abstract #0520201798 - Digos constrak | On-going (DIGOS CONSTRAK CORP.) | On-going (DIGOS CONSTRAK CORP.) | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per Program of Works
[7 empty] | Project Engineer: | Andoy | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 132
[7 empty] | Implementor: | Digos Constrak Corp | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: | 69.53% | Actual: | 69.53% | Actual: | 100% | Actual: | 100%
[7 empty] | Duration: | 120 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 15.33% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed: | 2020-10-15
[7 empty] | Date Started: | 2020-08-27
Rehab. Of Brgy. Road, Lunga-og, Sto. Tomas |  | SB # 4 CY 2019 (STIMULUS) | Building |  |  |  | Project Cost: | 600000 | Target Completion Date: | 2020-09-04 | Program: | 600000 | Planned: |  | Planned: | 14.05% | Planned: | 100% | Planned: | 100% | Planned: | 100% | No. of Persons: | 7 | Amended in AIP 3rd revision CY 2019 / SB No. 4 CY 2019 increasing the project cost to P600,000.00 | On-going ( project cost increase to P600,000.00 | On-going ( project cost increase to P600,000.00 | On-going ( project cost increase to P600,000.00 | On-going ( project cost increase to P600,000.00 | Completed as per Program of Works
[7 empty] | Project Engineer: |  | Revised Completion Date: | 2020-10-04 | Allotment: | 600000 | Revised: |  | Revised: |  | Revised: | 40.1% | Revised: | 77.4% | Revised: |  | No. of Man-days: | 154
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: | 16.27% | Actual: | 26.93% | Actual: | 61.04% | Actual: | 100%
[7 empty] | Duration: | 30 | No. of days extended: | 30 |  |  | Slippage: | 0% | Slippage: |  | Slippage: | -13.17% | Slippage: | -16.36% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed: | 2020-12-31
[7 empty] | Date Started: | 2020-08-05
Rehabilitation of Multi-Purpose Hall, Llittle Panay, Panabo City (Note: Additional Fund Php 50,000.00) |  | SB # 4 CY 2019 (STIMULUS) | Building |  |  |  | Project Cost: | 550000 | Target Completion Date: | 2020-10-06 23:59 | Program: | 550000 | Planned: |  | Planned: |  | Planned: |  | Planned: | 100% | Planned: | 100% | No. of Persons: |  | For implementation | For implementation | For implementation | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per Program of Works
[7 empty] | Project Engineer: | Andoy | Revised Completion Date: |  | Allotment: | 550000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: | Digos Constrak Corp | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: | 100% | Actual: | 100%
[7 empty] | Duration: | 35 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed: | 2020-10-06 23:59
[7 empty] | Date Started: | 2020-09-02
Rehab. Of Multi-Purpose Hall, San Francisco, Panabo City |  | SB NO. 4 CY 2019 (STIMULUS | Building |  |  | Contract | Project Cost: | 650000 | Target Completion Date: | 2021-02-03 | Program: | 650000 | Planned: |  | Planned: |  | Planned: | 5% | Planned: | 5% | Planned: | 100% | No. of Persons: |  | Purchase Order # 2020031248- DIGOS CONSTRAK | For implementation (DIGOS CONSTRAK) | On-going | On-going | On-going | Completed as per Program of Works
[7 empty] | Project Engineer: | Andoy | Revised Completion Date: |  | Allotment: | 650000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: | Digos Constrak Corp/ | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: | 5% | Actual: | 5% | Actual: | 100%
[7 empty] | Duration: | 160 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: | 2019-10-18 | Date completed: | 2020-12-04
[7 empty] | Date Started: | 2020-08-27
Rehabilitation of Evacuation Center, Kiotoy, Panabo City (Note: Additional Fund Php 150,000.00) |  | SB # 4 CY 2019 (20% DF CY 2017 -STIMULUS) | Building |  |  |  | Project Cost: | 650000 | Target Completion Date: | 2021-02-03 | Program: | 650000 | Planned: |  | Planned: |  | Planned: | 19.5% | Planned: | 100% | Planned: | 100% | No. of Persons: | 8 | For implementation | On-going | On-going | Completed | Completed | Completed as per Program of Works
[7 empty] | Project Engineer: | Andoy | Revised Completion Date: |  | Allotment: | 650000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 176
[7 empty] | Implementor: | Digos Constrak Corp | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: | 15.8% | Actual: | 100% | Actual: | 100%
[7 empty] | Duration: | 160 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | -3.7% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed: | 2020-11-10
[7 empty] | Date Started: | 2020-08-27
Construction of Multi-Purpose Covered Court, Magupising,B.E. Dujali |  | SB # 4 CY 2019 (STIMULUS | Construction |  |  |  | Project Cost: | 600000 | Target Completion Date: | 2020-11-20 23:59 | Program: | 600000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: | 100% | No. of Persons: |  | Procurement on process | Procurement on process | Abstract on Process as of August 17, 2020 | Abstract on Process as of August 17, 2020 | Abstract on Process as of August 17, 2020 | Completed as per Program of Works
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 600000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: | Digos Constrak Corp | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual: | 100%
[7 empty] | Duration: | 80 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: |  | Slippage: |  | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed: | 2020-11-20
[7 empty] | Date Started: | 2020-09-02
Impv't. of Brgy. Road Covered Court, Malativas, Panabo City (Note: Additional Fund Php 107,800.00) |  | SB NO. 4 CY 2019 (STIMULUS | Court |  |  |  | Project Cost: | 607800 | Target Completion Date: | 2020-10-06 | Program: | 607800 | Planned: |  | Planned: |  | Planned: | 38.15% | Planned: | 100% | Planned: | 100% | No. of Persons: | 6 | Procurement on process | Awarded to Digos Constrak Corp/ | On-going (Awarded to Digos Constrak Corp/) | Completed as per physical accomplishment. | Completed as per physical accomplishment. | Completed as per Program of Works
[7 empty] | Project Engineer: | Abayon | Revised Completion Date: |  | Allotment: | 607800 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 132
[7 empty] | Implementor: | Digos Constrak Corp/ | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: | 54.74% | Actual: | 100% | Actual: | 100%
[7 empty] | Duration: | 34 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 16.59% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed: | 2020-10-05
[7 empty] | Date Started: | 2020-09-02
Const. of 1 Classroom @ Lambid ES, Sto. Niño, Talaingod |  | SEF-SB No. 2 CY 2019 | Building |  | sq.m |  | Project Cost: | 500000 | Target Completion Date: | 2020-10-31 | Program: | 500000 | Planned: |  | Planned: |  | Planned: |  | Planned: | 100% | Planned: | 100% | No. of Persons: | 15 | Opening of Shopping on June 25, 2020 | Opening of Shopping on June 25, 2020 | Opening of Shopping on June 25, 2020 | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per Program of Works
[7 empty] | Project Engineer: | Mabanglo | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 169
[7 empty] | Implementor: | Alpebel Builders and Supply Corporation | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: | 100% | Actual: | 100%
[7 empty] | Duration: | 30 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed: | 2020-10-16
[7 empty] | Date Started: | 2020-10-01
Const. of 1 Classroom @ Pongpong ES, Dagohoy, Talaingod |  | SEF-SB No. 2 CY 2019 | Building |  | sq.m |  | Project Cost: | 500000 | Target Completion Date: | 2020-12-14 23:59 | Program: | 500000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: | 100% | No. of Persons: | 14 | Opening of Shopping on June 25, 2020 | Opening of Shopping on June 25, 2020 | Opening of Shopping on June 25, 2020 | Opening of Shopping on June 25, 2020 | Opening of Shopping on June 25, 2020 | Completed as per Program of Works
[7 empty] | Project Engineer: | Mabanglo | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 169
[7 empty] | Implementor: | Alpebel Builders and Supply Corporation | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual: | 100%
[7 empty] | Duration: | 75 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
[7 empty] | Date Started: | 2020-10-01
Const. of 1 Classroom @ Dalingding ES, Palma Gil, Talaingod |  | SEF-SB No. 2 CY 2019 | Building |  | sq.m |  | Project Cost: | 500000 | Target Completion Date: | 2020-12-14 23:59 | Program: | 500000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: | 100% | No. of Persons: | 15 | Opening of Shopping on June 25, 2020 | Opening of Shopping on June 25, 2020 | Opening of Shopping on June 25, 2020 | Opening of Shopping on June 25, 2020 | Opening of Shopping on June 25, 2020 | Completed as per Program of Works
[7 empty] | Project Engineer: | Mabanglo | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: | Alpebel Builders and Supply Corporation | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual: | 100%
[7 empty] | Duration: | 75 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed: | 2020-11-30
[7 empty] | Date Started: | 2020-10-01
Const. of 1 Classroom @ Sambulongan ES, Palma Gil, Talaingod |  | SEF-SB No. 2 CY 2019 | Building |  | sq.m |  | Project Cost: | 500000 | Target Completion Date: | 2020-12-14 23:59 | Program: | 500000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: | 100% | No. of Persons: | 14 | Opening of Shopping on June 25, 2020 | Opening of Shopping on June 25, 2020 | Opening of Shopping on June 25, 2020 | Opening of Shopping on June 25, 2020 | Opening of Shopping on June 25, 2020 | Completed as per Program of Works
[7 empty] | Project Engineer: | Mabanglo | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 169
[7 empty] | Implementor: | Alpebel Builders and Supply Corporation | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual: | 100%
[7 empty] | Duration: | 75 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed: | 2020-12-11
[7 empty] | Date Started: | 2020-10-01
Repair of Damaged Drainage/Creek along Tuganay-Ising River |  | 5% CALAMITY FUND | Creek |  |  | Admin | Project Cost: | 1540500 | Target Completion Date: | 2020-05-15 | Program: | 1540500 | Planned: | 25.6% | No. of Persons: | 3 | Completed 12/31/2020 |  |  |  | Planned: | 100% | No. of Persons: | 3 | Completed 12/31/2020 |  |  |  |  | Completed as per Program of Works
[7 empty] | Project Engineer: | Ganaba | Revised Completion Date: | 12/31/2020 | Allotment: | 1540500 | Revised: |  | No. of Man-days: | 66 |  |  |  |  | Revised: |  | No. of Man-days: | 66
[7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: | 23.6% | [6 empty] | Actual: | 100%
[7 empty] | Duration: | 182 | No. of days extended: |  |  |  | Slippage: | -2% | [6 empty] | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed: | 2020-12-31
[7 empty] | Date Started: | 2019-11-15
ROAD ID 001 - Jct. Highway Magatos - New Bantayan |  | GENERAL FUND CY 2020 | Maintenance | 7.1 | km | MBA | Project Cost: | 564839.9739 | Target Completion Date: | 2020-12-31 23:59 | Program: | 564839.9739 | Planned: | 31.14% | Planned: | 31.14% | Planned: | 52.95% | Planned: | 52.95% | Planned: | 100% | No. of Persons: | 17 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | Completed as per Program of Works
[7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 564839.9739 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 374
[7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 57334.17 | Actual: | 31.14% | Actual: | 31.14% | Actual: | 52.95% | Actual: | 52.95% | Actual: | 100%
[7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: | 2020-01-02 | Date completed: | 2020-12-31
[7 empty] | Date Started: | 2020-01-02
ROAD ID 002 - Magatos - Bdry. Pagsabangan |  | GENERAL FUND CY 2020 | Maintenance | 8.33 | km | MBA | Project Cost: | 653221.626 | Target Completion Date: | 2020-12-31 23:59 | Program: | 653221.626 | Planned: | 28.54% | Planned: | 28.54% | Planned: | 50.33% | Planned: | 50.33% | Planned: | 100% | No. of Persons: | 17 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | Completed as per Program of Works
[7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 653221.626 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 374
[7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 71713.44 | Actual: | 28.54% | Actual: | 28.54% | Actual: | 50.33% | Actual: | 50.33% | Actual: | 100%
[7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: | 2020-01-02 | Date completed: | 2020-12-31
[7 empty] | Date Started: | 2020-01-02
ROAD ID 003 - Ilog - New Bantayan |  | GENERAL FUND CY 2020 | Maintenance | 2.68 | km | MBA | Project Cost: | 236174.847 | Target Completion Date: | 2020-12-31 23:59 | Program: | 236174.847 | Planned: | 19.56% | Planned: | 19.56% | Planned: | 57.93% | Planned: | 57.93% | Planned: | 100% | No. of Persons: | 17 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | Completed as per Program of Works
[7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 236174.847 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 374
[7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 22629.74 | Actual: | 19.56% | Actual: | 19.56% | Actual: | 57.93% | Actual: | 57.93% | Actual: | 100%
[7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: | 2020-01-02 | Date completed: | 2020-12-31
[7 empty] | Date Started: | 2020-01-02
ROAD ID 005 - Asuncion - Monte Carlo - Del Pilar |  | GENERAL FUND CY 2020 | Maintenance | 9.93 | km | MBA | Project Cost: | 716344.9167 | Target Completion Date: | 2020-12-31 23:59 | Program: | 716344.9167 | Planned: | 33.04% | Planned: | 33.04% | Planned: | 51.95% | Planned: | 51.95% | Planned: | 100% | No. of Persons: | 17 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | Completed as per Program of Works
[7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 716344.9167 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 374
[7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 33056.21 | Actual: | 33.04% | Actual: | 33.04% | Actual: | 51.95% | Actual: | 51.95% | Actual: | 100%
[7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: | 2020-01-02 | Date completed: | 2020-12-31
[7 empty] | Date Started: | 2020-01-02
ROAD ID 006 - Jct. Highway Canatan - Magatos |  | GENERAL FUND CY 2020 | Maintenance | 4.85 | km | MBA | Project Cost: | 391296.517 | Target Completion Date: | 2020-12-31 23:59 | Program: | 391296.517 | Planned: | 28.48% | Planned: | 28.48% | Planned: | 46.61% | Planned: | 46.61% | Planned: | 100% | No. of Persons: | 17 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | Completed as per Program of Works
[7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 391296.517 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 374
[7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 33056.21 | Actual: | 28.48% | Actual: | 28.48% | Actual: | 46.61% | Actual: | 46.61% | Actual: | 100%
[7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: | 2020-01-02 | Date completed: | 2020-12-31
[7 empty] | Date Started: | 2020-01-02
ROAD ID 010 - Saug - Sonlon - Bdry. Longanapan |  | GENERAL FUND CY 2020 | Maintenance | 11.6 | km | MBA | Project Cost: | 1102041.4797 | Target Completion Date: | 2020-12-31 23:59 | Program: | 1102041.4797 | Planned: | 25.36% | Planned: | 25.36% | Planned: | 37.74% | Planned: | 37.74% | Planned: | 100% | No. of Persons: | 17 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | Completed as per Program of Works
[7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 1102041.4797 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 374
[7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 83166.18 | Actual: | 25.36% | Actual: | 25.36% | Actual: | 37.74% | Actual: | 37.74% | Actual: | 100%
[7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: | 2020-01-02 | Date completed: | 2020-12-31
[7 empty] | Date Started: | 2020-01-02
ROAD ID 011 - Jct. New Visayas - Buan |  | GENERAL FUND CY 2020 | Maintenance | 2.99 | km | MBA | Project Cost: | 134598.4525 | Target Completion Date: | 2020-12-31 23:59 | Program: | 134598.4525 | Planned: | 11.58% | Planned: | 11.58% | Planned: | 55.5% | Planned: | 55.5% | Planned: | 100% | No. of Persons: | 17 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | Completed as per Program of Works
[7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 134598.4525 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 374
[7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 10391.0005 | Actual: | 11.58% | Actual: | 11.58% | Actual: | 55.5% | Actual: | 55.5% | Actual: | 100%
[7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: | 2020-01-02 | Date completed: | 2020-12-31
[7 empty] | Date Started: | 2020-01-02
ROAD ID 013 - San Vicente - Butay |  | GENERAL FUND CY 2020 | Maintenance | 7.52 | km | MBA | Project Cost: | 579541.5407 | Target Completion Date: | 2020-12-31 23:59 | Program: | 579541.5407 | Planned: | 33.79% | Planned: | 33.79% | Planned: | 51.53% | Planned: | 51.53% | Planned: | 100% | No. of Persons: | 17 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | Completed as per Program of Works
[7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 579541.5407 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 374
[7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 123616.2106 | Actual: | 33.79% | Actual: | 33.79% | Actual: | 51.53% | Actual: | 51.53% | Actual: | 100%
[7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: | 2020-01-02 | Date completed: | 2020-12-31
[7 empty] | Date Started: | 2020-01-02
ROAD ID 014 - Jct. Highway Doña Andrea - Capungagan |  | GENERAL FUND CY 2020 | Maintenance | 8.7 | km | MBA | Project Cost: | 675845.5865 | Target Completion Date: | 2020-12-31 23:59 | Program: | 675845.5865 | Planned: | 18.55% | Planned: | 18.55% | Planned: | 44.7% | Planned: | 44.7% | Planned: | 100% | No. of Persons: | 17 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | Completed as per Program of Works
[7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 675845.5865 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 374
[7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 75289.1983 | Actual: | 18.55% | Actual: | 18.55% | Actual: | 44.7% | Actual: | 44.7% | Actual: | 100%
[7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: | 2020-01-02 | Date completed: | 2020-12-31
[7 empty] | Date Started: | 2020-01-02
ROAD ID 015 - Pamacaun - Lasang - Banate |  | GENERAL FUND CY 2020 | Maintenance | 4.11 | km | MBA | Project Cost: | 180747.1933 | Target Completion Date: | 2020-12-31 23:59 | Program: | 180747.1933 | Planned: | 12.9% | Planned: | 12.9% | Planned: | 55.68% | Planned: | 55.68% | Planned: | 100% | No. of Persons: | 17 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | Completed as per Program of Works
[7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 180747.1933 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 374
[7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 15544.2586 | Actual: | 12.9% | Actual: | 12.9% | Actual: | 55.68% | Actual: | 55.68% | Actual: | 100%
[7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: | 2020-01-02 | Date completed: | 2020-12-31
[7 empty] | Date Started: | 2020-01-02
ROAD ID 018 - Semong - Palma Gil |  | GENERAL FUND CY 2020 | Maintenance | 2.73 | km | MBA | Project Cost: | 276301.31 | Target Completion Date: | 2020-12-31 23:59 | Program: | 276301.31 | Planned: | 50.35% | Planned: | 50.35% | Planned: | 58.18% | Planned: | 58.18% | Planned: | 100% | No. of Persons: | 14 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | Completed as per Program of Works
[7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 276301.31 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 210
[7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 139117.7096 | Actual: | 50.35% | Actual: | 50.35% | Actual: | 58.18% | Actual: | 58.18% | Actual: | 100%
[7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: | 2020-01-02 | Date completed: | 2020-12-31
[7 empty] | Date Started: | 2020-01-02
ROAD ID 020 - Daligdigon-Dagohoy |  | GENERAL FUND CY 2020 | Maintenance | 3.34 | km | MBA | Project Cost: | 161826.4 | Target Completion Date: | 2020-12-31 23:59 | Program: | 161826.4 | Planned: | 51.55% | Planned: | 51.55% | Planned: | 61.03% | Planned: | 61.03% | Planned: | 100% | No. of Persons: | 14 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | Completed as per Program of Works
[7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 161826.4 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 210
[7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 83421.5092 | Actual: | 51.55% | Actual: | 51.55% | Actual: | 61.03% | Actual: | 61.03% | Actual: | 100%
[7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: | 2020-01-02 | Date completed: | 2020-12-31
[7 empty] | Date Started: | 2020-01-02
ROAD ID 021 - Angelo - Dagohoy |  | GENERAL FUND CY 2020 | Maintenance | 2.19 | km | MBA | Project Cost: | 67286.09 | Target Completion Date: | 2020-12-31 23:59 | Program: | 67286.09 | Planned: | 43.7% | Planned: | 43.7% | Planned: | 78.17% | Planned: | 78.17% | Planned: | 100% | No. of Persons: | 14 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | Completed as per Program of Works
[7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 67286.09 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 210
[7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 29404.0213 | Actual: | 43.7% | Actual: | 43.7% | Actual: | 78.18% | Actual: | 78.18% | Actual: | 100%
[7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0.01% | Slippage: | 0.01% | Slippage: | 0%
[7 empty] | Date Allotment Released: | 2020-01-02 | Date completed: | 2020-12-31
[7 empty] | Date Started: | 2020-01-02
ROAD ID 025 - Jct. Sampao - Bdry. Mamacao |  | GENERAL FUND CY 2020 | Maintenance | 4.98 | km | MBA | Project Cost: | 325083.1184 | Target Completion Date: | 2020-12-31 23:59 | Program: | 325083.1184 | Planned: | 27.89% | Planned: | 27.89% | Planned: | 47.54% | Planned: | 47.54% | Planned: | 100% | No. of Persons: | 17 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | Completed as per Program of Works
[7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 325083.1184 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 374
[7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 47819.7267 | Actual: | 27.89% | Actual: | 27.89% | Actual: | 47.54% | Actual: | 47.54% | Actual: | 100%
[7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: | 2020-01-02 | Date completed: | 2020-12-31
[7 empty] | Date Started: | 2020-01-02
ROAD ID 026 - Jct. Highway - Luna - Mamacao - Narra |  | GENERAL FUND CY 2020 | Maintenance | 9.17 | km | MBA | Project Cost: | 361826.1515 | Target Completion Date: | 2020-12-31 23:59 | Program: | 361826.1515 | Planned: | 20.12% | Planned: | 20.12% | Planned: | 52.72% | Planned: | 52.72% | Planned: | 100% | No. of Persons: | 17 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | Completed as per Program of Works
[7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 361826.1515 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 374
[7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 22433.2214 | Actual: | 20.12% | Actual: | 20.12% | Actual: | 52.72% | Actual: | 52.72% | Actual: | 100%
[7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: | 2020-01-02 | Date completed: | 2020-12-31
[7 empty] | Date Started: | 2020-01-02
ROAD ID 027 - Jct. Gabuyan - Katipunan - Bucana |  | GENERAL FUND CY 2020 | Maintenance | 5.89 | km | MBA | Project Cost: | 485762.7577 | Target Completion Date: | 2020-12-31 23:59 | Program: | 485762.7577 | Planned: | 11.79% | Planned: | 11.79% | Planned: | 37% | Planned: | 37% | Planned: | 100% | No. of Persons: | 17 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | Completed as per Program of Works
[7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 485762.7577 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 374
[7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 38180.9528 | Actual: | 11.79% | Actual: | 11.79% | Actual: | 37% | Actual: | 37% | Actual: | 100%
[7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: | 2020-01-02 | Date completed: | 2020-12-31
[7 empty] | Date Started: | 2020-01-02
ROAD ID 028 - Capungagan - Mabuhay - Pandulian |  | GENERAL FUND CY 2020 | Maintenance | 5.57 | km | MBA | Project Cost: | 468741.4542 | Target Completion Date: | 2020-12-31 23:59 | Program: | 468741.4542 | Planned: | 7.71% | Planned: | 7.71% | Planned: | 32.2% | Planned: | 32.2% | Planned: | 100% | No. of Persons: | 17 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | Completed as per Program of Works
[7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 468741.4542 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 374
[7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 24093.3107 | Actual: | 7.71% | Actual: | 7.71% | Actual: | 32.02% | Actual: | 32.02% | Actual: | 100%
[7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | -0.18% | Slippage: | -0.18% | Slippage: | 0%
[7 empty] | Date Allotment Released: | 2020-01-02 | Date completed: | 2020-12-31
[7 empty] | Date Started: | 2020-01-02
ROAD ID 034 - Km. 15, Kipalili - New Loon |  | GENERAL FUND CY 2020 | Maintenance | 6.93 | km | MBA | Project Cost: | 490709.8742 | Target Completion Date: | 2020-12-31 23:59 | Program: | 490709.8742 | Planned: | 22.39% | Planned: | 22.39% | Planned: | 43.71% | Planned: | 43.71% | Planned: | 100% | No. of Persons: | 17 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | Completed as per Program of Works
[7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 490709.8742 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 374
[7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 66393.046 | Actual: | 22.39% | Actual: | 22.39% | Actual: | 43.71% | Actual: | 43.71% | Actual: | 100%
[7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: | 2020-01-02 | Date completed: | 2020-12-31
[7 empty] | Date Started: | 2020-01-02
ROAD ID 035 - Jct. Suaon - Libuton |  | GENERAL FUND CY 2020 | Maintenance | 7.26 | km | MBA | Project Cost: | 60919.7962 | Target Completion Date: | 2020-12-31 23:59 | Program: | 60919.7962 | Planned: | 10.68% | Planned: | 10.68% | Planned: | 56.31% | Planned: | 56.31% | Planned: | 100% | No. of Persons: | 17 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | Completed as per Program of Works
[7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 60919.7962 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 374
[7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: |  | Actual: | 10.68% | Actual: | 10.68% | Actual: | 56.31% | Actual: | 56.31% | Actual: | 100%
[7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: | 2020-01-02 | Date completed: | 2020-12-31
[7 empty] | Date Started: | 2020-01-02
ROAD ID 037 - Monte Dujali - Gupitan |  | GENERAL FUND CY 2020 | Maintenance | 4.58 | km | MBA | Project Cost: | 224727.1648 | Target Completion Date: | 2020-12-31 23:59 | Program: | 224727.1648 | Planned: | 16.62% | Planned: | 35.49% | Planned: | 56.71% | Planned: | 56.71% | Planned: | 100% | No. of Persons: | 17 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | Completed as per Program of Works
[7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 224727.1648 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 374
[7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 37349.6548 | Actual: | 16.62% | Actual: | 35.49% | Actual: | 56.71% | Actual: | 56.71% | Actual: | 100%
[7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: | 2020-01-02 | Date completed: | 2020-12-31
[7 empty] | Date Started: | 2020-01-02
ROAD ID 041 - Sawata - Mamangan - Pinamuno |  | GENERAL FUND CY 2020 | Maintenance | 14.48 | km | MBA | Project Cost: | 1636481.63 | Target Completion Date: | 2021-02-01 23:59 | Program: | 1636481.63 | Planned: | 37.11% | Planned: | 37.11% | Planned: | 43.95% | Planned: | 43.95% | Planned: | 100% | No. of Persons: | 14 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | Completed as per Program of Works
[7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-02-28 23:59 | Allotment: | 1636481.63 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 210
[7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 607298.3329 | Actual: | 37.11% | Actual: | 37.11% | Actual: | 43.95% | Actual: | 43.95% | Actual: | 100%
[7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: | 2020-01-02 | Date completed: | 2020-12-31
[7 empty] | Date Started: | 2020-02-03
ROAD ID 042 - Igangon - Sawata |  | GENERAL FUND CY 2020 | Maintenance | 9.66 | km | MBA | Project Cost: | 314254.79 | Target Completion Date: | 2020-12-31 23:59 | Program: | 314254.79 | Planned: | 13.11% | Planned: | 33.05% | Planned: | 55.76% | Planned: | 55.76% | Planned: | 100% | No. of Persons: | 17 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | Completed as per Program of Works
[7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 314254.79 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 374
[7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 41198.803 | Actual: | 13.11% | Actual: | 33.05% | Actual: | 55.76% | Actual: | 55.76% | Actual: | 100%
[7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: | 2020-01-02 | Date completed: | 2020-12-31
[7 empty] | Date Started: | 2020-01-02
ROAD ID 043 - Jct. Sawata - Bdry. Binasbas |  | GENERAL FUND CY 2020 | Maintenance | 0.46 | km | MBA | Project Cost: | 46556.26 | Target Completion Date: | 2020-12-31 23:59 | Program: | 46556.26 | Planned: | 16.23% | Planned: | 30.75% | Planned: | 63.48% | Planned: | 63.48% | Planned: | 100% | No. of Persons: | 17 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | Completed as per Program of Works
[7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 46556.26 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 374
[7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 7556.081 | Actual: | 16.23% | Actual: | 30.75% | Actual: | 63.48% | Actual: | 63.48% | Actual: | 100%
[7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: | 2020-01-02 | Date completed: | 2020-12-31
[7 empty] | Date Started: | 2020-01-02
ROAD ID 045 - Tagaytay - Buan |  | GENERAL FUND CY 2020 | Maintenance | 4.92 | km | MBA | Project Cost: | 552783.35 | Target Completion Date: | 2020-12-31 23:59 | Program: | 552783.35 | Planned: | 31.49% | Planned: | 44.45% | Planned: | 58.9% | Planned: | 58.9% | Planned: | 100% | No. of Persons: | 17 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | Completed as per Program of Works
[7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 552783.35 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 374
[7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 174071.4769 | Actual: | 31.49% | Actual: | 44.45% | Actual: | 58.9% | Actual: | 58.9% | Actual: | 100%
[7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: | 2020-01-02 | Date completed: | 2020-12-31
[7 empty] | Date Started: | 2020-01-02
ROAD ID 049 - Limbaan - Sto. Niño |  | GENERAL FUND CY 2020 | Maintenance | 3.19 | km | MBA | Project Cost: | 322857.58 | Target Completion Date: | 2021-02-01 23:59 | Program: | 322857.58 | Planned: | 47.46% | Planned: | 47.46% | Planned: | 58.18% | Planned: | 58.18% | Planned: | 100% | No. of Persons: | 14 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | Completed as per Program of Works
[7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-02-28 23:59 | Allotment: | 322857.58 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 210
[7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 153228.2075 | Actual: | 47.46% | Actual: | 47.46% | Actual: | 58.18% | Actual: | 58.18% | Actual: | 100%
[7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: | 2020-01-02 | Date completed: | 2020-12-31
[7 empty] | Date Started: | 2020-02-03
ROAD ID 050 - Jct. Monte Carlo - Upper Cabaywa - Canatan |  | GENERAL FUND CY 2020 | Maintenance | 4.61 | km | MBA | Project Cost: | 482840.52 | Target Completion Date: | 2020-12-31 23:59 | Program: | 482840.52 | Planned: | 16.47% | Planned: | 34.82% | Planned: | 54.91% | Planned: | 54.91% | Planned: | 100% | No. of Persons: | 17 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | Completed as per Program of Works
[7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 482840.52 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 374
[7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 79523.8336 | Actual: | 16.47% | Actual: | 34.82% | Actual: | 54.91% | Actual: | 54.91% | Actual: | 100%
[7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: | 2020-01-02 | Date completed: | 2020-12-31
[7 empty] | Date Started: | 2020-01-02
ROAD ID 051 - Del Pilar - Jct. Silangan |  | GENERAL FUND CY 2020 | Maintenance | 4.17 | km | MBA | Project Cost: | 467261.55 | Target Completion Date: | 2020-12-31 23:59 | Program: | 467261.55 | Planned: | 8.31% | Planned: | 20.3% | Planned: | 34.05% | Planned: | 34.05% | Planned: | 100% | No. of Persons: |  | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | Completed as per Program of Works
[7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 467261.55 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 38829.4348 | Actual: | 8.31% | Actual: | 20.3% | Actual: | 34.05% | Actual: | 34.05% | Actual: | 100%
[7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: | 2020-01-02 | Date completed: | 2020-12-31
[7 empty] | Date Started: | 2020-01-02
ROAD ID 052 - New Corella - New Sambog - Silangan |  | GENERAL FUND CY 2020 | Maintenance | 5.1 | km | MBA | Project Cost: | 519781.9 | Target Completion Date: | 2020-12-31 23:59 | Program: | 519781.9 | Planned: | 13.05% | Planned: | 24.17% | Planned: | 36.87% | Planned: | 36.87% | Planned: | 100% | No. of Persons: | 17 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | Completed as per Program of Works
[7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 519781.9 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 374
[7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 67831.538 | Actual: | 13.05% | Actual: | 24.17% | Actual: | 36.87% | Actual: | 36.87% | Actual: | 100%
[7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: | 2020-01-02 | Date completed: | 2020-12-31
[7 empty] | Date Started: | 2020-01-02
ROAD ID 053 - Pob. New Corella - Prk. 10 Pob. |  | GENERAL FUND CY 2020 | Maintenance | 1.3 | km | MBA | Project Cost: | 49339.52 | Target Completion Date: | 2020-12-31 23:59 | Program: | 49339.52 | Planned: | 20.07% | Planned: | 34.13% | Planned: | 65.18% | Planned: | 65.18% | Planned: | 100% | No. of Persons: | 17 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | Completed as per Program of Works
[7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 49339.52 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 374
[7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 9902.4417 | Actual: | 20.07% | Actual: | 34.13% | Actual: | 65.18% | Actual: | 65.18% | Actual: | 100%
[7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: | 2020-01-02 | Date completed: | 2020-12-31
[7 empty] | Date Started: | 2020-01-02
ROAD ID 054 - Prk. 7 Pob. - Jct. New Sambog |  | GENERAL FUND CY 2020 | Maintenance | 2.54 | km | MBA | Project Cost: | 284614.93 | Target Completion Date: | 2020-12-31 23:59 | Program: | 284614.93 | Planned: | 10.38% | Planned: | 31.19% | Planned: | 54.92% | Planned: | 54.92% | Planned: | 100% | No. of Persons: | 17 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | Completed as per Program of Works
[7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2142-01-29 23:59 | Allotment: | 284614.93 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 374
[7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 29543.0297 | Actual: | 10.38% | Actual: | 31.19% | Actual: | 54.92% | Actual: | 54.92% | Actual: | 100%
[7 empty] | Duration: | 365 | No. of days extended: | 44196 |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: | 2020-01-02 | Date completed: | 2020-12-31
[7 empty] | Date Started: | 2020-01-02
ROAD ID 056 - Sta. Fe - Del Monte |  | GENERAL FUND CY 2020 | Maintenance | 3.34 | km | MBA | Project Cost: | 169019.48 | Target Completion Date: | 2020-12-31 23:59 | Program: | 169019.48 | Planned: | 17.46% | Planned: | 35.41% | Planned: | 58.28% | Planned: | 58.28% | Planned: | 100% | No. of Persons: | 17 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | Completed as per Program of Works
[7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 169019.48 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 374
[7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 29510.8012 | Actual: | 17.46% | Actual: | 35.41% | Actual: | 58.28% | Actual: | 58.28% | Actual: | 100%
[7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: | 2020-01-02 | Date completed: | 2020-12-31
[7 empty] | Date Started: | 2020-01-02
ROAD ID 058 - New Corella - New Bohol |  | GENERAL FUND CY 2020 | Maintenance | 11.54 | km | MBA | Project Cost: | 521354.26 | Target Completion Date: | 2020-12-31 23:59 | Program: | 521354.26 | Planned: | 22.18% | Planned: | 39.46% | Planned: | 52.23% | Planned: | 52.23% | Planned: | 100% | No. of Persons: | 17 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | Completed as per Program of Works
[7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 521354.26 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 374
[7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 115636.3749 | Actual: | 22.18% | Actual: | 39.46% | Actual: | 52.23% | Actual: | 52.23% | Actual: | 100%
[7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: | 2020-01-02 | Date completed: | 2020-12-31
[7 empty] | Date Started: | 2020-01-02
ROAD ID 059 - Jct. Carcor - Prk. 9 Bagsak |  | GENERAL FUND CY 2020 | Maintenance | 2.5 | km | MBA | Project Cost: | 234950.09 | Target Completion Date: | 2020-12-31 23:59 | Program: | 234950.09 | Planned: | 21.94% | Planned: | 37.99% | Planned: | 57.68% | Planned: | 57.68% | Planned: | 100% | No. of Persons: | 17 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | Completed as per Program of Works
[7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 234950.09 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 374
[7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 51548.0497 | Actual: | 21.94% | Actual: | 37.99% | Actual: | 57.68% | Actual: | 57.68% | Actual: | 100%
[7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: | 2020-01-02 | Date completed: | 2020-12-31
[7 empty] | Date Started: | 2020-01-02
ROAD ID 060 - Carcor - Jct. Kauswagan |  | GENERAL FUND CY 2020 | Maintenance | 4.32 | km | MBA | Project Cost: | 405993.76 | Target Completion Date: | 2020-12-31 23:59 | Program: | 405993.76 | Planned: | 40.17% | Planned: | 51.04% | Planned: | 59.86% | Planned: | 59.86% | Planned: | 100% | No. of Persons: | 17 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | Completed as per Program of Works
[7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 405993.76 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 374
[7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 163087.6934 | Actual: | 40.17% | Actual: | 51.04% | Actual: | 59.86% | Actual: | 59.86% | Actual: | 100%
[7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: | 2020-01-02 | Date completed: | 2020-12-31
[7 empty] | Date Started: | 2020-01-02
ROAD ID 061 - Del Pilar - Prk. 9 Bagsak - San Jose |  | GENERAL FUND CY 2020 | Maintenance |  | km | MBA | Project Cost: | 505304.267 | Target Completion Date: | 2021-01-14 23:59 | Program: | 505304.267 | Planned: | 49.18% | Planned: | 49.18% | Planned: | 54.78% | Planned: | 54.78% | Planned: | 100% | No. of Persons: | 14 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | Completed as per Program of Works
[7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-02-10 23:59 | Allotment: | 505304.267 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 210
[7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 248508.6385 | Actual: | 49.18% | Actual: | 49.18% | Actual: | 54.78% | Actual: | 54.78% | Actual: | 100%
[7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: | 2020-01-02 | Date completed: | 2020-12-31
[7 empty] | Date Started: | 2020-01-16
ROAD ID 062 - Del Pilar - El Unido |  | GENERAL FUND CY 2020 | Maintenance | 1.32 | km | MBA | Project Cost: | 124053.65 | Target Completion Date: | 2020-12-31 23:59 | Program: | 124053.65 | Planned: | 16.17% | Planned: | 16.17% | Planned: | 40.91% | Planned: | 40.91% | Planned: | 100% | No. of Persons: | 17 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | Completed as per Program of Works
[7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 124053.65 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 374
[7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 20059.4752 | Actual: | 16.17% | Actual: | 16.17% | Actual: | 40.91% | Actual: | 40.91% | Actual: | 100%
[7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: | 2020-01-02 | Date completed: | 2020-12-31
[7 empty] | Date Started: | 2020-01-02
ROAD ID 063 - San Juan - New Talisay |  | GENERAL FUND CY 2020 | Maintenance | 5.13 | km | MBA | Project Cost: | 572832.52 | Target Completion Date: | 2020-12-31 23:59 | Program: | 572832.52 | Planned: | 26.84% | Planned: | 26.84% | Planned: | 39.5% | Planned: | 39.5% | Planned: | 100% | No. of Persons: | 17 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | Completed as per Program of Works
[7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 572832.52 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 374
[7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 153748.2484 | Actual: | 26.84% | Actual: | 26.84% | Actual: | 39.5% | Actual: | 39.5% | Actual: | 100%
[7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: | 2020-01-02 | Date completed: | 2020-12-31
[7 empty] | Date Started: | 2020-01-02
ROAD ID 064 - San Juan - Kauswagan - New Cortez |  | GENERAL FUND CY 2020 | Maintenance | 3.22 | km | MBA | Project Cost: | 128969.53 | Target Completion Date: | 2021-01-14 23:59 | Program: | 128969.53 | Planned: | 41.14% | Planned: | 41.14% | Planned: | 50.44% | Planned: | 50.44% | Planned: | 100% | No. of Persons: | 14 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | Completed as per Program of Works
[7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-02-10 23:59 | Allotment: | 128969.53 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 210
[7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 53058.0646 | Actual: | 41.14% | Actual: | 41.14% | Actual: | 50.44% | Actual: | 50.44% | Actual: | 100%
[7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: |  | Slippage: |  | Slippage: |  | Slippage: |  | Slippage:
[7 empty] | Date Allotment Released: | 2020-01-02 | Date completed: | 2020-12-31
[7 empty] | Date Started: | 2020-01-16
ROAD ID 065 - New Bohol - Jct. El Unido |  | GENERAL FUND CY 2020 | Maintenance | 2.12 | km | MBA | Project Cost: | 177260.81 | Target Completion Date: | 2021-01-14 23:59 | Program: | 177260.81 | Planned: | 42.46% | Planned: | 42.46% | Planned: | 52.67% | Planned: | 52.67% | Planned: | 100% | No. of Persons: | 14 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | Completed as per Program of Works
[7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-02-10 23:59 | Allotment: | 177260.81 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 210
[7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 74910.4183 | Actual: | 42.26% | Actual: | 42.26% | Actual: | 52.67% | Actual: | 52.67% | Actual: | 100%
[7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | -0.2% | Slippage: | -0.2% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: | 2020-01-02 | Date completed: | 2020-12-31
[7 empty] | Date Started: | 2020-01-16
ROAD ID 066 - New Corella - El Unido - Jct. Mesaoy |  | GENERAL FUND CY 2020 | Maintenance | 8.63 | km | MBA | Project Cost: | 792432.45 | Target Completion Date: | 2021-01-14 23:59 | Program: | 792432.45 | Planned: | 53.98% | Planned: | 53.98% | Planned: | 63.47% | Planned: | 63.47% | Planned: | 100% | No. of Persons: | 14 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | Completed as per Program of Works
[7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-02-10 23:59 | Allotment: | 792432.45 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 210
[7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 427755.0365 | Actual: | 53.98% | Actual: | 53.98% | Actual: | 63.47% | Actual: | 63.47% | Actual: | 100%
[7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: | 2020-01-02 | Date completed: | 2020-12-31
[7 empty] | Date Started: | 2020-01-16
ROAD ID 067 - Mesaoy - Dasing |  | GENERAL FUND CY 2020 | Maintenance | 1.39 | km | MBA | Project Cost: | 130632.25 | Target Completion Date: | 2021-01-14 23:59 | Program: | 130632.25 | Planned: | 48.79% | Planned: | 48.79% | Planned: | 57.7% | Planned: | 57.7% | Planned: | 100% | No. of Persons: | 14 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | Completed as per Program of Works
[7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-02-10 23:59 | Allotment: | 130632.25 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 210
[7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 63735.4748 | Actual: | 48.79% | Actual: | 48.79% | Actual: | 57.7% | Actual: | 57.7% | Actual: | 100%
[7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: | 2020-01-02 | Date completed: | 2020-12-31
[7 empty] | Date Started: | 2020-01-16
ROAD ID 068 - Jct. San Juan - Jct. Mesaoy |  | GENERAL FUND CY 2020 | Maintenance | 1.82 | km | MBA | Project Cost: | 203936.68 | Target Completion Date: | 2020-12-31 23:59 | Program: | 203936.68 | Planned: | 12.12% | Planned: | 12.12% | Planned: | 35.37% | Planned: | 35.37% | Planned: | 100% | No. of Persons: | 17 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | Completed as per Program of Works
[7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 203936.68 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 374
[7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 24717.1256 | Actual: | 12.12% | Actual: | 12.12% | Actual: | 35.37% | Actual: | 35.37% | Actual: | 100%
[7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: | 2020-01-02 | Date completed: | 2020-12-31
[7 empty] | Date Started: | 2020-01-02
ROAD ID 070 - Mesaoy - New Bohol |  | GENERAL FUND CY 2020 | Maintenance | 5.36 | km | MBA | Project Cost: | 665667.84 | Target Completion Date: | 2021-01-14 23:59 | Program: | 665667.84 | Planned: | 41.99% | Planned: | 41.99% | Planned: | 46.74% | Planned: | 46.74% | Planned: | 100% | No. of Persons: | 14 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | Completed as per Program of Works
[7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-02-10 23:59 | Allotment: | 665667.84 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 210
[7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 279513.926 | Actual: | 41.99% | Actual: | 41.99% | Actual: | 46.74% | Actual: | 46.74% | Actual: | 100%
[7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: | 2020-01-02 | Date completed: | 2020-12-31
[7 empty] | Date Started: | 2020-01-16
ROAD ID 147 - Prk. 1, Maunlom-Prk. 6 Maunlom Road |  | GENERAL FUND CY 2020 | Maintenance | 3.56 | km | MBA | Project Cost: | 115812.32 | Target Completion Date: | 2021-02-15 23:59 | Program: | 115812.32 | Planned: | 38.9% | Planned: | 38.9% | Planned: | 53.76% | Planned: | 53.76% | Planned: | 100% | No. of Persons: | 14 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | Completed as per Program of Works
[7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-03-14 23:59 | Allotment: | 115812.32 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 210
[7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 45050.9925 | Actual: | 38.9% | Actual: | 38.9% | Actual: | 53.76% | Actual: | 53.76% | Actual: | 100%
[7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: | 2020-01-02 | Date completed: | 2020-12-31
[7 empty] | Date Started: | 2020-02-17
ROAD ID 149 - New Visayas - Binancian |  | GENERAL FUND CY 2020 | Maintenance | 7.77 | km | MBA | Project Cost: | 196599.01 | Target Completion Date: | 2020-12-31 23:59 | Program: | 196599.01 | Planned: | 6.94% | Planned: | 6.94% | Planned: | 52.21% | Planned: | 52.21% | Planned: | 100% | No. of Persons: | 17 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | Completed as per Program of Works
[7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 196599.01 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 374
[7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 13643.9713 | Actual: | 6.94% | Actual: | 6.94% | Actual: | 52.21% | Actual: | 52.21% | Actual: | 100%
[7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: | 2020-01-02 | Date completed: | 2020-12-31
[7 empty] | Date Started: | 2020-01-02
ROAD ID 150 - Datu Balong - Prk. Mamalian |  | GENERAL FUND CY 2020 | Maintenance | 3.46 | km | MBA | Project Cost: | 106305.88 | Target Completion Date: | 2020-12-31 23:59 | Program: | 106305.88 | Planned: | 12.74% | Planned: | 12.74% | Planned: | 54.05% | Planned: | 54.05% | Planned: | 100% | No. of Persons: | 17 | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | On-going (Suspended last April 5, 2020 due to COVID, resumption order dated May 4, 2020) | Completed as per Program of Works
[7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 106305.88 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 374
[7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: | 13543.3691 | Actual: | 12.74% | Actual: | 12.74% | Actual: | 54.05% | Actual: | 54.05% | Actual: | 100%
[7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | 2 | 2020-01-02 | Date completed: | 2020-12-31
[7 empty] | Date Started: | 2020-01-02
ROAD ID 073 - Cebulano - Mangalcal |  | GENERAL FUND CY 2020 | Maintenance | 4.17 | km | MBA | Project Cost: | 134672.7 | Target Completion Date: | 2020-12-31 23:59 | Program: | 134672.7 | Planned: | 50% | Planned: | 50% | Planned: | 50% | Planned: | 81% | Planned: | 100% | No. of Persons: | 9 | On-going | On-going | On-going | On-going | On-going | Completed as per Program of Works
[7 empty] | Project Engineer: | Gamad/Clar | Revised Completion Date: |  | Allotment: | 134672.7 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 45
[7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: | 51% | Actual: | 51% | Actual: | 51% | Actual: | 83.6% | Actual: | 100%
[7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 1% | Slippage: | 1% | Slippage: | 1% | Slippage: | 2.6% | Slippage: | 0%
[7 empty] | Date Allotment Released: | 2020-01-02 | Date completed: | 2020-12-31
[7 empty] | Date Started: | 2020-01-02
ROAD ID 073 - Cebulano - Mangalcal |  | GENERAL FUND CY 2020 | Maintenance | 4.17 | km | CBRMC | Project Cost: | 131004.66 | Target Completion Date: | 2020-11-11 | Program: | 131004.66 | Planned: | 5% | Planned: | 5% | Planned: | 5% | Planned: | 42.43% | Planned: | 100% | No. of Persons: | 6 | On-going | On-going | On-going | On-going | On-going | Completed as per Program of Works
[7 empty] | Project Engineer: | Maligro | Revised Completion Date: |  | Allotment: | 131004.66 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 30
[7 empty] | Implementor: | Brgy. Mangalcal Women's Household | No. of days suspended: |  | Disbursement: |  | Actual: | 5% | Actual: | 5% | Actual: | 5% | Actual: | 42.43% | Actual: | 100%
[7 empty] | Duration: | 180 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: | 2020-01-02 | Date completed: | 2020-11-15
[7 empty] | Date Started: | 2020-05-15
ROAD ID 074 - Tubod - basa - Mangalcal |  | GENERAL FUND CY 2020 | Maintenance | 3.93 | km | MBA | Project Cost: | 143530.25 | Target Completion Date: | 2020-12-31 23:59 | Program: | 143530.25 | Planned: | 50% | Planned: | 50% | Planned: | 50% | Planned: | 82.6% | Planned: | 100% | No. of Persons: | 3 | On-going | On-going | On-going | On-going | On-going | Completed as per Program of Works
[7 empty] | Project Engineer: | Gamad/Clar | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 143530.25 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 30
[7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: |  | Actual: | 52% | Actual: | 52% | Actual: | 52% | Actual: | 83.6% | Actual: | 100%
[7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 2% | Slippage: | 2% | Slippage: | 2% | Slippage: | 1% | Slippage: | 0%
[7 empty] | Date Allotment Released: | 2020-01-02 | Date completed: | 2020-12-31
[7 empty] | Date Started: | 2020-01-02
ROAD ID 074 - Tubod - basa - Mangalcal |  | GENERAL FUND CY 2020 | Maintenance | 3.93 | km | CBRMC | Project Cost: | 106856.33 | Target Completion Date: | 2020-11-11 | Program: | 106856.33 | Planned: | 5% | Planned: | 5% | Planned: | 5% | Planned: | 100% | Planned: | 100% | No. of Persons: | 2 | On-going | On-going | On-going | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per Program of Works
[7 empty] | Project Engineer: | Maligro | Revised Completion Date: |  | Allotment: | 106856.33 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 44
[7 empty] | Implementor: | Tubod Centro Lower Irrigator's Association | No. of days suspended: |  | Disbursement: |  | Actual: | 5% | Actual: | 5% | Actual: | 5% | Actual: | 100% | Actual: | 100%
[7 empty] | Duration: | 6 months | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed: | 2020-11-25
[7 empty] | Date Started: | 2020-05-15
ROAD ID 078 - Upper Mangalcal - Lower Mangalcal |  | GENERAL FUND CY 2020 | Maintenance | 2.43 | km | MBA | Project Cost: | 82374.21 | Target Completion Date: | 2020-12-31 23:59 | Program: | 82374.21 | Planned: | 50% | Planned: | 50% | Planned: | 50% | Planned: | 86.5% | Planned: | 86.5% | No. of Persons: | 3 | On-going | On-going | On-going | On-going | On-going | Completed as per Program of Works
[7 empty] | Project Engineer: | Gamad/Clar | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 82374.21 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 24
[7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: |  | Actual: | 55% | Actual: | 55% | Actual: | 55% | Actual: | 84.6% | Actual: | 84.6%
[7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 5% | Slippage: | 5% | Slippage: | 5% | Slippage: | -1.9% | Slippage: | -1.9%
[7 empty] | Date Allotment Released: | 2020-01-02 | Date completed: | 2020-12-31
[7 empty] | Date Started: | 2020-01-02
ROAD ID 078 - Upper Mangalcal - Lower Mangalcal |  | GENERAL FUND CY 2020 | Maintenance | 2.43 | km | CBRMC | Project Cost: | 72444.97 | Target Completion Date: | 2020-11-15 23:59 | Program: | 72444.97 | Planned: | 5% | Planned: | 5% | Planned: | 5% | Planned: | 100% | Planned: | 100% | No. of Persons: | 6 | On-going | On-going | On-going | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per Program of Works
[7 empty] | Project Engineer: | Maligro | Revised Completion Date: |  | Allotment: | 72444.97 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 18
[7 empty] | Implementor: | Brgy. Mangalcal Women's Homebased Association | No. of days suspended: |  | Disbursement: |  | Actual: | 5% | Actual: | 5% | Actual: | 5% | Actual: | 100% | Actual: | 100%
[7 empty] | Duration: | 185 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: | 2020-01-02 | Date completed: | 2020-11-15 23:59
[7 empty] | Date Started: | 2020-05-15
ROAD ID 079 - Cebulano - Loceta |  | GENERAL FUND CY 2020 | Maintenance |  | km | MBA | Project Cost: | 72051.43 | Target Completion Date: | 2020-12-31 23:59 | Program: | 72051.43 | Planned: | 30% | Planned: | 30% | Planned: | 30% | Planned: | 82.6% | Planned: | 100% | No. of Persons: | 3 | On-going | On-going | On-going | On-going | On-going | Completed as per Program of Works
[7 empty] | Project Engineer: | Gamad/Clar | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 72051.43 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 36
[7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: |  | Actual: | 54% | Actual: | 54% | Actual: | 54% | Actual: | 84.6% | Actual: | 100%
[7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 24% | Slippage: | 24% | Slippage: | 24% | Slippage: | 2% | Slippage: | 0%
[7 empty] | Date Allotment Released: | 2020-01-02 | Date completed: | 2020-12-31
[7 empty] | Date Started: | 2020-01-02
ROAD ID 079 - Cebulano - Loceta |  | GENERAL FUND CY 2020 | Maintenance |  | km | CBRMC | Project Cost: | 47089.26 | Target Completion Date: | 2020-11-15 23:59 | Program: | 47089.26 | Planned: | 5% | Planned: | 5% | Planned: | 5% | Planned: | 100% | Planned: | 100% | No. of Persons: | 6 | On-going | On-going | On-going | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per Program of Works
[7 empty] | Project Engineer: | Maligro | Revised Completion Date: |  | Allotment: | 47089.26 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 18
[7 empty] | Implementor: | Brgy. Mangalcal Women's Homebased Association | No. of days suspended: |  | Disbursement: |  | Actual: | 5% | Actual: | 5% | Actual: | 5% | Actual: | 100% | Actual: | 100%
[7 empty] | Duration: | 185 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: | 2020-01-02 | Date completed: | 2020-11-15 23:59
[7 empty] | Date Started: | 2020-05-15
ROAD ID 082 - Jct. Highway Carmen - Mangalcal - Tubod |  | GENERAL FUND CY 2020 | Maintenance | 11.34 | km | MBA | Project Cost: | 462895.06 | Target Completion Date: | 2020-12-31 23:59 | Program: | 462895.06 | Planned: | 50% | Planned: | 50% | Planned: | 50% | Planned: | 82.6% | Planned: | 100% | No. of Persons: | 9 | On-going | On-going | On-going | On-going | On-going | Completed as per Program of Works
[7 empty] | Project Engineer: | Gamad/Clar | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 462895.06 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 45
[7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: |  | Actual: | 50% | Actual: | 50% | Actual: | 50% | Actual: | 81.6% | Actual: | 100%
[7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | -1% | Slippage: | 0%
[7 empty] | Date Allotment Released: | 2020-01-02 | Date completed: | 2020-12-31
[7 empty] | Date Started: | 2020-01-02
ROAD ID 086 - Ising - Sadpodon - Taba - Dila -Dila |  | GENERAL FUND CY 2020 | Maintenance | 5.68 | km | MBA | Project Cost: | 226651.27 | Target Completion Date: | 2020-12-31 23:59 | Program: | 226651.27 | Planned: | 50% | Planned: | 50% | Planned: | 50% | Planned: | 85.6% | Planned: | 100% | No. of Persons: | 3 | On-going | On-going | On-going | On-going | On-going | Completed as per Program of Works
[7 empty] | Project Engineer: | Gamad/Clar | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 226651.27 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 30
[7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: |  | Actual: | 50% | Actual: | 50% | Actual: | 50% | Actual: | 84.6% | Actual: | 100%
[7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | -1% | Slippage: | 0%
[7 empty] | Date Allotment Released: | 2020-01-02 | Date completed: | 2020-12-31
[7 empty] | Date Started: | 2020-01-02
ROAD ID 087 - Tuganay - taba |  | GENERAL FUND CY 2020 | Maintenance | 4.27 | km | MBA | Project Cost: | 169418.15 | Target Completion Date: | 2020-12-31 23:59 | Program: | 169418.15 | Planned: | 52% | Planned: | 52% | Planned: | 52% | Planned: | 82.6% | Planned: | 100% | No. of Persons: | 3 | On-going | On-going | On-going | On-going | On-going | Completed as per Program of Works
[7 empty] | Project Engineer: | Gamad/Clar | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 169418.15 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 45
[7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: |  | Actual: | 52% | Actual: | 52% | Actual: | 52% | Actual: | 84.6% | Actual: | 100%
[7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 2% | Slippage: | 0%
[7 empty] | Date Allotment Released: | 2020-01-02 | Date completed: | 2020-12-31
[7 empty] | Date Started: | 2020-01-02
ROAD ID 088 - Jct. Highway Tuganay - Taba |  | GENERAL FUND CY 2020 | Maintenance | 4.4 | km | MBA | Project Cost: | 222375.04 | Target Completion Date: | 2020-12-31 23:59 | Program: | 222375.04 | Planned: | 50% | Planned: | 50% | Planned: | 50% | Planned: | 86.6% | Planned: | 100% | No. of Persons: | 3 | On-going | On-going | On-going | On-going | On-going | Completed as per Program of Works
[7 empty] | Project Engineer: | Gamad/Clar | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 222375.04 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 30
[7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: |  | Actual: | 51% | Actual: | 51% | Actual: | 51% | Actual: | 85.4% | Actual: | 100%
[7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 1% | Slippage: | 1% | Slippage: | 1% | Slippage: | -1.2% | Slippage: | 0%
[7 empty] | Date Allotment Released: | 2020-01-02 | Date completed: | 2020-12-31
[7 empty] | Date Started: | 2020-01-02
ROAD ID 088 - Jct. Highway Tuganay - Taba |  | GENERAL FUND CY 2020 | Maintenance | 4.4 | km | CBRMC | Project Cost: | 57955.99 | Target Completion Date: | 2020-11-13 23:59 | Program: | 57955.99 | Planned: | 5% | Planned: | 5% | Planned: | 5% | Planned: | 50% | Planned: | 100% | No. of Persons: | 4 | On-going | On-going | On-going | On-going | On-going | Completed as per Program of Works
[7 empty] | Project Engineer: | Maligro | Revised Completion Date: |  | Allotment: | 57955.99 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 12
[7 empty] | Implementor: | Ezra Christian Minsitry For Peace, Inc. | No. of days suspended: |  | Disbursement: |  | Actual: | 5% | Actual: | 5% | Actual: | 5% | Actual: | 50% | Actual: | 100%
[7 empty] | Duration: | 185 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: | 2020-01-02 | Date completed: | 2020-11-13
[7 empty] | Date Started: | 2020-05-13
ROAD ID 089 - Jct. Highway Ising - Magsaysay |  | GENERAL FUND CY 2020 | Maintenance | 10.84 | km | MBA | Project Cost: | 478128.48 | Target Completion Date: | 2020-12-31 23:59 | Program: | 478128.48 | Planned: | 50% | Planned: | 50% | Planned: | 50% | Planned: | 85.6% | Planned: | 100% | No. of Persons: | 8 | On-going | On-going | On-going | On-going | On-going | Completed as per Program of Works
[7 empty] | Project Engineer: | Gamad/Clar | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 478128.48 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 32
[7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: |  | Actual: | 50% | Actual: | 50% | Actual: | 50% | Actual: | 84.7% | Actual: | 100%
[7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | -0.9% | Slippage: | 0%
[7 empty] | Date Allotment Released: | 2020-01-02 | Date completed: | 2020-12-31
[7 empty] | Date Started: | 2020-01-02
ROAD ID 089 - Jct. Highway Ising - Magsaysay |  | GENERAL FUND CY 2020 | Maintenance | 10.84 | km | CBRMC | Project Cost: | 212505.24 | Target Completion Date: | 2020-11-14 23:59 | Program: | 212505.24 | Planned: | 5% | Planned: | 5% | Planned: | 5% | Planned: | 50% | Planned: | 100% | No. of Persons: | 6 | On-going | On-going | On-going | On-going | On-going | Completed as per Program of Works
[7 empty] | Project Engineer: | Maligro | Revised Completion Date: |  | Allotment: | 212505.24 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 24
[7 empty] | Implementor: | School in the Air Integrated Farmer's Associiation | No. of days suspended: |  | Disbursement: |  | Actual: | 5% | Actual: | 5% | Actual: | 5% | Actual: | 50% | Actual: | 100%
[7 empty] | Duration: | 185 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: | 2020-01-02 | Date completed: | 2020-11-14
[7 empty] | Date Started: | 2020-05-14
ROAD ID 090 - Maligaya - New Camiling |  | GENERAL FUND CY 2020 | Maintenance |  | km | MBA | Project Cost: | 51790.26 | Target Completion Date: | 2020-12-31 23:59 | Program: | 51790.26 | Planned: | 50% | Planned: | 50% | Planned: | 50% | Planned: | 81.6% | Planned: | 100% | No. of Persons: | 3 | On-going | On-going | On-going | On-going | On-going | Completed as per Program of Works
[7 empty] | Project Engineer: | Gamad/Clar | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 51790.26 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 36
[7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: |  | Actual: | 51% | Actual: | 51% | Actual: | 51% | Actual: | 84.6% | Actual: | 100%
[7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 1% | Slippage: | 1% | Slippage: | 1% | Slippage: | 3% | Slippage: | 0%
[7 empty] | Date Allotment Released: | 2020-01-02 | Date completed: | 2020-12-31
[7 empty] | Date Started: | 2020-01-02
ROAD ID 091 - New Camiling - Alejal - Lower Magsaysay |  | GENERAL FUND CY 2020 | Maintenance | 6.73 | km | MBA | Project Cost: | 277852.05 | Target Completion Date: | 2020-12-31 23:59 | Program: | 277852.05 | Planned: | 50% | Planned: | 50% | Planned: | 50% | Planned: | 87.6% | Planned: | 100% | No. of Persons: | 3 | On-going | On-going | On-going | On-going | On-going | Completed as per Program of Works
[7 empty] | Project Engineer: | Gamad/Clar | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 277852.05 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 30
[7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: |  | Actual: | 50% | Actual: | 50% | Actual: | 50% | Actual: | 85.64% | Actual: | 100%
[7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | -1.96% | Slippage: | 0%
[7 empty] | Date Allotment Released: | 2020-01-02 | Date completed: | 2020-12-31
[7 empty] | Date Started: | 2020-01-02
ROAD ID 091 - New Camiling - Alejal - Lower Magsaysay |  | GENERAL FUND CY 2020 | Maintenance | 6.73 | km | CBRMC | Project Cost: | 150927.01 | Target Completion Date: | 2020-11-14 23:59 | Program: | 150927.01 | Planned: | 5% | Planned: | 5% | Planned: | 5% | Planned: | 100% | Planned: | 100% | No. of Persons: | 6 | On-going | On-going | On-going | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per Program of Works
[7 empty] | Project Engineer: | Maligro | Revised Completion Date: |  | Allotment: | 150927.01 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 18
[7 empty] | Implementor: | School in the Air Integrated Farmer's Association | No. of days suspended: |  | Disbursement: |  | Actual: | 5% | Actual: | 5% | Actual: | 5% | Actual: | 100% | Actual: | 100%
[7 empty] | Duration: | 185 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: | 2020-01-02 | Date completed: | 2020-11-14
[7 empty] | Date Started: | 2020-05-14
ROAD ID 094 - Jct. highway Tuganay - Anibongan |  | GENERAL FUND CY 2020 | Maintenance | 3.66 | km | MBA | Project Cost: | 139609.7 | Target Completion Date: | 2020-12-31 23:59 | Program: | 139609.7 | Planned: | 50% | Planned: | 50% | Planned: | 50% | Planned: | 81.6% | Planned: | 100% | No. of Persons: | 3 | On-going | On-going | On-going | On-going | On-going | Completed as per Program of Works
[7 empty] | Project Engineer: | Gamad/Clar | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 139609.7 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 27
[7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: |  | Actual: | 55% | Actual: | 55% | Actual: | 55% | Actual: | 84.6% | Actual: | 100%
[7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 5% | Slippage: | 5% | Slippage: | 5% | Slippage: | 3% | Slippage: | 0%
[7 empty] | Date Allotment Released: | 2020-01-02 | Date completed: | 2020-12-31
[7 empty] | Date Started: | 2020-01-02
ROAD ID 094 - Jct. highway Tuganay - Anibongan |  | GENERAL FUND CY 2020 | Maintenance | 3.66 | km | CBRMC | Project Cost: | 93574.75 | Target Completion Date: | 2020-11-13 23:59 | Program: | 93574.75 | Planned: | 5% | Planned: | 5% | Planned: | 5% | Planned: | 42.02% | Planned: | 100% | No. of Persons: | 6 | Purchase Order # 2020030977 (Ezra Christian Minsitry For Peace, Inc.) | Purchase Order # 2020030977 (Ezra Christian Minsitry For Peace, Inc.) | Purchase Order # 2020030977 (Ezra Christian Minsitry For Peace, Inc.) | On-going | On-going | Completed as per Program of Works
[7 empty] | Project Engineer: | Maligro | Revised Completion Date: |  | Allotment: | 93574.75 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 6
[7 empty] | Implementor: | Ezra Christian Minsitry For Peace, Inc. | No. of days suspended: |  | Disbursement: |  | Actual: | 5% | Actual: | 5% | Actual: | 5% | Actual: | 42.02% | Actual: | 100%
[7 empty] | Duration: | 185 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: | 2020-01-02 | Date completed: | 2020-11-13
[7 empty] | Date Started: | 2020-05-13
ROAD ID 095 - Anibongan - Guadalupe |  | GENERAL FUND CY 2020 | Maintenance | 2.48 | km | MBA | Project Cost: | 85559.79 | Target Completion Date: | 2020-12-31 23:59 | Program: | 85559.79 | Planned: | 50% | Planned: | 50% | Planned: | 50% | Planned: | 85.6% | Planned: | 100% | No. of Persons: | 4 | On-going / Time extension on process due to suspension of activity | On-going / Time extension on process due to suspension of activity | On-going / Time extension on process due to suspension of activity | On-going | On-going | Completed as per Program of Works
[7 empty] | Project Engineer: | Gamad/Clar | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 85559.79 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 24
[7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: |  | Actual: | 55% | Actual: | 55% | Actual: | 55% | Actual: | 84.1% | Actual: | 100%
[7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 5% | Slippage: | 5% | Slippage: | 5% | Slippage: | -1.5% | Slippage: | 0%
[7 empty] | Date Allotment Released: | 2020-01-02 | Date completed: | 2020-12-31
[7 empty] | Date Started: | 2020-01-02
ROAD ID 096 - Tuganay - Anibongan - San Isidro |  | GENERAL FUND CY 2020 | Maintenance | 7.22 | km | MBA | Project Cost: | 344085.79 | Target Completion Date: | 2020-12-31 23:59 | Program: | 344085.79 | Planned: | 50% | Planned: | 50% | Planned: | 50% | Planned: | 82.6% | Planned: | 100% | No. of Persons: | 3 | On-going | On-going | On-going | On-going | On-going | Completed as per Program of Works
[7 empty] | Project Engineer: | Gamad/Clar | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 344085.79 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 24
[7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: |  | Actual: | 50% | Actual: | 50% | Actual: | 50% | Actual: | 81.4% | Actual: | 100%
[7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | -1.2% | Slippage: | 0%
[7 empty] | Date Allotment Released: | 2020-01-02 | Date completed: | 2020-12-31
[7 empty] | Date Started: | 2020-01-02
ROAD ID 096 - Tuganay - Anibongan - San Isidro |  | GENERAL FUND CY 2020 | Maintenance | 7.22 | km | CBRMC | Project Cost: | 115911.95 | Target Completion Date: | 2020-11-13 23:59 | Program: | 115911.95 | Planned: | 5% | Planned: | 5% | Planned: | 5% | Planned: | 100% | Planned: | 100% | No. of Persons: | 6 | On-going | On-going | On-going | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per Program of Works
[7 empty] | Project Engineer: | Maligro | Revised Completion Date: |  | Allotment: | 115911.95 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 30
[7 empty] | Implementor: | Ezra Christian Minsitry For Peace, Inc. | No. of days suspended: |  | Disbursement: |  | Actual: | 5% | Actual: | 5% | Actual: | 5% | Actual: | 100% | Actual: | 100%
[7 empty] | Duration: | 185 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed: | 2020-11-13 23:59
[7 empty] | Date Started: | 2020-05-13
ROAD ID 097 - Jct. Anibongan - Prk. 2, 7, 5, San Isidro |  | GENERAL FUND CY 2020 | Maintenance | 3.14 | km | MBA | Project Cost: | 89575.84 | Target Completion Date: | 2020-12-31 23:59 | Program: | 89575.84 | Planned: | 50% | Planned: | 50% | Planned: | 50% | Planned: | 84.6% | Planned: | 100% | No. of Persons: | 4 | On-going | On-going | On-going | On-going | On-going | Completed as per Program of Works
[7 empty] | Project Engineer: | Gamad/Clar | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 89575.84 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 24
[7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: |  | Actual: | 53% | Actual: | 53% | Actual: | 53% | Actual: | 82.6% | Actual: | 100%
[7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 3% | Slippage: | 3% | Slippage: | 3% | Slippage: | -2% | Slippage: | 0%
[7 empty] | Date Allotment Released: | 2020-01-02 | Date completed: | 2020-12-31
[7 empty] | Date Started: | 2020-01-02
ROAD ID 098 - Anibongan - Salvacion - Cabay-angan |  | GENERAL FUND CY 2020 | Maintenance | 6.93 | km | MBA | Project Cost: | 279123.9 | Target Completion Date: | 2020-12-31 23:59 | Program: | 279123.9 | Planned: | 50% | Planned: | 50% | Planned: | 50% | Planned: | 82.6% | Planned: | 100% | No. of Persons: | 9 | On-going | On-going | On-going | On-going | On-going | Completed as per Program of Works
[7 empty] | Project Engineer: | Gamad/Clar | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 279123.9 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 36
[7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: |  | Actual: | 51% | Actual: | 51% | Actual: | 51% | Actual: | 84.61% | Actual: | 100%
[7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 1% | Slippage: | 1% | Slippage: | 1% | Slippage: | 2.01% | Slippage: | 0%
[7 empty] | Date Allotment Released: | 2020-01-02 | Date completed: | 2020-12-31
[7 empty] | Date Started: | 2020-01-02
ROAD ID 099 - Mabaus - Cabay - angan |  | GENERAL FUND CY 2020 | Maintenance |  | km | MBA | Project Cost: | 113320.9 | Target Completion Date: | 2020-12-31 23:59 | Program: | 113320.9 | Planned: | 50% | Planned: | 50% | Planned: | 50% | Planned: | 82.4% | Planned: | 100% | No. of Persons: | 3 | On-going | On-going | On-going | On-going | On-going | Completed as per Program of Works
[7 empty] | Project Engineer: | Gamad/Clar | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 113320.9 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 30
[7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: |  | Actual: | 54% | Actual: | 54% | Actual: | 54% | Actual: | 81.67% | Actual: | 100%
[7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 4% | Slippage: | 4% | Slippage: | 4% | Slippage: | -0.73% | Slippage: | 0%
[7 empty] | Date Allotment Released: | 2020-01-02 | Date completed: | 2020-12-31
[7 empty] | Date Started: | 2020-01-02
ROAD ID 101 - Jct. Highway Guadalupe - Bdry. Tagum |  | GENERAL FUND CY 2020 | Maintenance | 7.9 | km | MBA | Project Cost: | 517780.87 | Target Completion Date: | 2020-12-31 23:59 | Program: | 517780.87 | Planned: | 50% | Planned: | 50% | Planned: | 50% | Planned: | 84.5% | Planned: | 100% | No. of Persons: | 8 | On-going | On-going | On-going | On-going | On-going | Completed as per Program of Works
[7 empty] | Project Engineer: | Gamad/Clar | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 517780.87 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 48
[7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: |  | Actual: | 55% | Actual: | 55% | Actual: | 55% | Actual: | 86.4% | Actual: | 100%
[7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 5% | Slippage: | 5% | Slippage: | 5% | Slippage: | 1.9% | Slippage: | 0%
[7 empty] | Date Allotment Released: | 2020-01-02 | Date completed: | 2020-12-31
[7 empty] | Date Started: | 2020-01-02
ROAD ID 104 - Dujali - Tanglaw |  | GENERAL FUND CY 2020 | Maintenance |  | km | MBA | Project Cost: | 135183.27 | Target Completion Date: | 2020-12-31 23:59 | Program: | 135183.27 | Planned: | 50% | Planned: | 50% | Planned: | 50% | Planned: | 84.16% | Planned: | 100% | No. of Persons: | 3 | On-going | On-going | On-going | On-going | On-going | Completed as per Program of Works
[7 empty] | Project Engineer: | Gamad/Clar | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 135183.27 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 24
[7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: |  | Actual: | 52% | Actual: | 52% | Actual: | 52% | Actual: | 82.6% | Actual: | 100%
[7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 2% | Slippage: | 2% | Slippage: | 2% | Slippage: | -1.56% | Slippage: | 0%
[7 empty] | Date Allotment Released: | 2020-01-02 | Date completed: | 2020-12-31
[7 empty] | Date Started: | 2020-01-02
ROAD ID 104 - Dujali - Tanglaw |  | GENERAL FUND CY 2020 | Maintenance |  | km | CBRMC | Project Cost: | 94178.48 | Target Completion Date: | 2020-12-12 | Program: | 94178.48 | Planned: | 5% | Planned: | 5% | Planned: | 5% | Planned: | 41.07% | Planned: | 100% | No. of Persons: | 6 | On-going | On-going | On-going | On-going | On-going | Completed as per Program of Works
[7 empty] | Project Engineer: | Maligro | Revised Completion Date: | 2021-01-08 | Allotment: | 94178.48 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 12
[7 empty] | Implementor: | Dujali Poblacion Farmer's Irrigator's Association, Inc. | No. of days suspended: | 27 | Disbursement: |  | Actual: | 5% | Actual: | 5% | Actual: | 5% | Actual: | 41.07% | Actual: | 100%
[7 empty] | Duration: | 187 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: | 2020-01-02 | Date completed: | 2020-12-08
[7 empty] | Date Started: | 2020-06-08
ROAD ID 105 - Poblacion Dujali - Prk. 8 Dujali |  | GENERAL FUND CY 2020 | Maintenance | 8.2 | km | MBA | Project Cost: | 329064 | Target Completion Date: | 2020-12-31 23:59 | Program: | 329064 | Planned: | 50% | Planned: | 50% | Planned: | 50% | Planned: | 82.6% | Planned: | 100% | No. of Persons: | 3 | On-going | On-going | On-going | On-going | On-going | Completed as per Program of Works
[7 empty] | Project Engineer: | Gamad/Clar | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 329064 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 36
[7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: |  | Actual: | 56% | Actual: | 56% | Actual: | 56% | Actual: | 84.15% | Actual: | 100%
[7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 6% | Slippage: | 6% | Slippage: | 6% | Slippage: | 1.55% | Slippage: | 0%
[7 empty] | Date Allotment Released: | 2020-01-02 | Date completed: | 2020-12-31
[7 empty] | Date Started: | 2020-01-02
ROAD ID 105 - Poblacion Dujali - Prk. 8 Dujali |  | GENERAL FUND CY 2020 | Maintenance | 8.2 | km | CBRMC | Project Cost: | 193371.11 | Target Completion Date: | 2020-12-12 | Program: | 193371.11 | Planned: | 5% | Planned: | 5% | Planned: | 5% | Planned: | 41.89% | Planned: | 100% | No. of Persons: | 2 | On-going | On-going | On-going | On-going | On-going | Completed as per Program of Works
[7 empty] | Project Engineer: | Maligro | Revised Completion Date: | 2021-01-08 | Allotment: | 193371.11 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 44
[7 empty] | Implementor: | Dujali Poblacion Farmer's Irrigator's Association, Inc. | No. of days suspended: | 27 | Disbursement: |  | Actual: | 5% | Actual: | 5% | Actual: | 5% | Actual: | 41.89% | Actual: | 100%
[7 empty] | Duration: | 187 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: | 2020-01-02 | Date completed: | 2020-12-08
[7 empty] | Date Started: | 2020-06-08
ROAD ID 107 - Dujali - San Isidro |  | GENERAL FUND CY 2020 | Maintenance | 3 | km | MBA | Project Cost: | 112652.73 | Target Completion Date: | 2020-12-31 23:59 | Program: | 112652.73 | Planned: | 50% | Planned: | 50% | Planned: | 50% | Planned: | 82.4% | Planned: | 100% | No. of Persons: | 3 | On-going | On-going | On-going | On-going | On-going | Completed as per Program of Works
[7 empty] | Project Engineer: | Gamad/Clar | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 112652.73 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 30
[7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: |  | Actual: | 57% | Actual: | 57% | Actual: | 57% | Actual: | 81.6% | Actual: | 100%
[7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 7% | Slippage: | 7% | Slippage: | 7% | Slippage: | -0.8% | Slippage: | 0%
[7 empty] | Date Allotment Released: | 2020-01-02 | Date completed: | 2020-12-31
[7 empty] | Date Started: | 2020-01-02
ROAD ID 108 - New Casay - Bugtong Talisay |  | GENERAL FUND CY 2020 | Maintenance |  | km | MBA | Project Cost: | 74294.5 | Target Completion Date: | 2020-12-31 23:59 | Program: | 74294.5 | Planned: | 50% | Planned: | 50% | Planned: | 50% | Planned: | 84.86% | Planned: | 100% | No. of Persons: | 4 | On-going | On-going | On-going | On-going | On-going | Completed as per Program of Works
[7 empty] | Project Engineer: | Gamad/Clar | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 74294.5 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 40
[7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: |  | Actual: | 50% | Actual: | 50% | Actual: | 50% | Actual: | 85.1% | Actual: | 100%
[7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0.24% | Slippage: | 0%
[7 empty] | Date Allotment Released: | 2020-01-02 | Date completed: | 2020-12-31
[7 empty] | Date Started: | 2020-01-02
ROAD ID 113 - Dujali - Balisong - Magupising |  | GENERAL FUND CY 2020 | Maintenance | 5.52 | km | MBA | Project Cost: | 235776.07 | Target Completion Date: | 2020-12-31 23:59 | Program: | 235776.07 | Planned: | 50% | Planned: | 50% | Planned: | 50% | Planned: | 84.1% | Planned: | 100% | No. of Persons: | 3 | On-going | On-going | On-going | On-going | On-going | Completed as per Program of Works
[7 empty] | Project Engineer: | Gamad/Clar | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 235776.07 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 30
[7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: |  | Actual: | 55% | Actual: | 55% | Actual: | 55% | Actual: | 85.2% | Actual: | 100%
[7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 5% | Slippage: | 5% | Slippage: | 5% | Slippage: | 1.1% | Slippage: | 0%
[7 empty] | Date Allotment Released: | 2020-01-02 | Date completed: | 2020-12-31
[7 empty] | Date Started: | 2020-01-02
ROAD ID 117 - Dujali - Pawas - San Vicente |  | GENERAL FUND CY 2020 | Maintenance | 4.42 | km | MBA | Project Cost: | 141544.99 | Target Completion Date: | 2020-12-31 23:59 | Program: | 141544.99 | Planned: | 50% | Planned: | 50% | Planned: | 50% | Planned: | 86.9% | Planned: | 100% | No. of Persons: | 3 | On-going | On-going | On-going | On-going | On-going | Completed as per Program of Works
[7 empty] | Project Engineer: | Gamad/Clar | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 141544.99 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 30
[7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: |  | Actual: | 50% | Actual: | 50% | Actual: | 50% | Actual: | 87.1% | Actual: | 100%
[7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0.2% | Slippage: | 0%
[7 empty] | Date Allotment Released: | 2020-01-02 | Date completed: | 2020-12-31
[7 empty] | Date Started: | 2020-01-02
ROAD ID 118- Jct. Salvacion - San Vicente - Cabay-angan |  | GENERAL FUND CY 2020 | Maintenance | 3.45 | km | MBA | Project Cost: | 168583.81 | Target Completion Date: | 2020-12-31 23:59 | Program: | 168583.81 | Planned: | 50% | Planned: | 50% | Planned: | 50% | Planned: | 85.15% | Planned: | 100% | No. of Persons: | 3 | On-going | On-going | On-going | On-going | On-going | Completed as per Program of Works
[7 empty] | Project Engineer: | Gamad/Clar | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 168583.81 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 27
[7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: |  | Actual: | 55% | Actual: | 55% | Actual: | 55% | Actual: | 84.9% | Actual: | 100%
[7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 5% | Slippage: | 5% | Slippage: | 5% | Slippage: | -0.25% | Slippage: | 0%
[7 empty] | Date Allotment Released: | 2020-01-02 | Date completed: | 2020-12-31
[7 empty] | Date Started: | 2020-01-02
ROAD ID 123- Bacali - Casig-ang - Libertad |  | GENERAL FUND CY 2020 | Maintenance |  | km | MBA | Project Cost: | 167836.14 | Target Completion Date: | 2020-12-31 23:59 | Program: | 167836.14 | Planned: | 50% | Planned: | 50% | Planned: | 50% | Planned: | 84.12% | Planned: | 100% | No. of Persons: | 3 | On-going | On-going | On-going | On-going | On-going | Completed as per Program of Works
[7 empty] | Project Engineer: | Gamad/Clar | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 167836.14 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 60
[7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: |  | Actual: | 58% | Actual: | 58% | Actual: | 58% | Actual: | 83.6% | Actual: | 100%
[7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 8% | Slippage: | 8% | Slippage: | 8% | Slippage: | -0.52% | Slippage: | 0%
[7 empty] | Date Allotment Released: | 2020-01-02 | Date completed: | 2020-12-31
[7 empty] | Date Started: | 2020-01-02
ROAD ID 124 - Kinamayan - Moslog - Mahayag |  | GENERAL FUND CY 2020 | Maintenance |  | km | MBA | Project Cost: | 114628.54 | Target Completion Date: | 2020-12-31 23:59 | Program: | 114628.54 | Planned: | 50% | Planned: | 50% | Planned: | 50% | Planned: | 82.6% | Planned: | 100% | No. of Persons: | 3 | On-going | On-going | On-going | On-going | On-going | Completed as per Program of Works
[7 empty] | Project Engineer: | Gamad/Clar | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 114628.54 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 24
[7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: |  | Actual: | 50% | Actual: | 50% | Actual: | 50% | Actual: | 83.6% | Actual: | 100%
[7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 1% | Slippage: | 0%
[7 empty] | Date Allotment Released: | 2020-01-02 | Date completed: | 2020-12-31
[7 empty] | Date Started: | 2020-01-02
ROAD ID 126 - Kinamayan - Lunga-og |  | GENERAL FUND CY 2020 | Maintenance |  | km | MBA | Project Cost: | 100416.26 | Target Completion Date: | 2020-12-31 23:59 | Program: | 100416.26 | Planned: | 50% | Planned: | 50% | Planned: | 50% | Planned: | 81.6% | Planned: | 100% | No. of Persons: | 3 | On-going | On-going | On-going | On-going | On-going | Completed as per Program of Works
[7 empty] | Project Engineer: | Gamad/Clar | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 100416.26 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 24
[7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: |  | Actual: | 52% | Actual: | 52% | Actual: | 52% | Actual: | 84.12% | Actual: | 100%
[7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 2% | Slippage: | 2% | Slippage: | 2% | Slippage: | 2.52% | Slippage: | 0%
[7 empty] | Date Allotment Released: | 2020-01-02 | Date completed: | 2020-12-31
[7 empty] | Date Started: | 2020-01-02
ROAD ID 126 - Kinamayan - Lunga-og |  | GENERAL FUND CY 2020 | Maintenance |  | km | CBRMC | Project Cost: | 64596.78 | Target Completion Date: | 2020-12-15 23:59 | Program: | 64596.78 | Planned: | 5% | Planned: | 5% | Planned: | 5% | Planned: | 41.87% | Planned: | 100% | No. of Persons: | 2 | On-going | On-going | On-going | On-going | On-going | Completed as per Program of Works
[7 empty] | Project Engineer: | Maligro | Revised Completion Date: |  | Allotment: | 64596.78 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 20
[7 empty] | Implementor: | Lunga-og Tribal Association | No. of days suspended: |  | Disbursement: |  | Actual: | 5% | Actual: | 5% | Actual: | 5% | Actual: | 41.87% | Actual: | 100%
[7 empty] | Duration: | 184 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: | 2020-01-02 | Date completed: | 2020-12-15
[7 empty] | Date Started: | 2020-06-15
ROAD ID 128 - Prk. Apitong - Upper Balisong - Dalisay |  | GENERAL FUND CY 2020 | Maintenance | 4.6 | km | MBA | Project Cost: | 150598.24 | Target Completion Date: | 2020-12-31 23:59 | Program: | 150598.24 | Planned: | 10% | Planned: | 10% | Planned: | 10% | Planned: | 82.5% | Planned: | 100% | No. of Persons: | 3 | On-going | On-going | On-going | On-going | On-going | Completed as per Program of Works
[7 empty] | Project Engineer: | Gamad/Clar | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 150598.24 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 24
[7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: |  | Actual: | 9% | Actual: | 9% | Actual: | 9% | Actual: | 84.6% | Actual: | 100%
[7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | -1% | Slippage: | -1% | Slippage: | -1% | Slippage: | 2.1% | Slippage: | 0%
[7 empty] | Date Allotment Released: | 2020-01-02 | Date completed: | 2020-12-31
[7 empty] | Date Started: | 2020-01-02
ROAD ID 128 - Prk. Apitong - Upper Balisong - Dalisay |  | GENERAL FUND CY 2020 | Maintenance | 4.6 | km | CBRMC | Project Cost: | 142475.11 | Target Completion Date: | 2020-12-15 23:59 | Program: | 142475.11 | Planned: | 5% | Planned: | 5% | Planned: | 5% | Planned: | 41.72% | Planned: | 100% | No. of Persons: | 4 | On-going | On-going | On-going | On-going | On-going | Completed as per Program of Works
[7 empty] | Project Engineer: | Maligro | Revised Completion Date: |  | Allotment: | 142475.11 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 24
[7 empty] | Implementor: | Lunga-og Tribal Association | No. of days suspended: |  | Disbursement: |  | Actual: | 5% | Actual: | 5% | Actual: | 5% | Actual: | 41.72% | Actual: | 100%
[7 empty] | Duration: | 184 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: | 2020-01-02 | Date completed: | 2020-12-15
[7 empty] | Date Started: | 2020-06-15
ROAD ID 130 - Los Amigos 1 - Esperanza - Los Amigos 2 |  | GENERAL FUND CY 2020 | Maintenance | 3.59 | km | MBA | Project Cost: | 97116.27 | Target Completion Date: | 2020-12-31 23:59 | Program: | 97116.27 | Planned: | 50% | Planned: | 50% | Planned: | 50% | Planned: | 82.51% | Planned: | 100% | No. of Persons: | 3 | On-going | On-going | On-going | On-going | On-going | Completed as per Program of Works
[7 empty] | Project Engineer: | Gamad/Clar | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 97116.27 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 27
[7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: |  | Actual: | 55% | Actual: | 55% | Actual: | 55% | Actual: | 82.4% | Actual: | 100%
[7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 5% | Slippage: | 5% | Slippage: | 5% | Slippage: | -0.11% | Slippage: | 0%
[7 empty] | Date Allotment Released: | 2020-01-02 | Date completed: | 2020-12-31
[7 empty] | Date Started: | 2020-01-02
ROAD ID 131 - Mugas - Lanatad |  | GENERAL FUND CY 2020 | Maintenance |  | km | MBA | Project Cost: | 65482.21 | Target Completion Date: | 2020-12-31 23:59 | Program: | 65482.21 | Planned: | 50% | Planned: | 50% | Planned: | 50% | Planned: | 84.98% | Planned: | 100% | No. of Persons: | 3 | On-going | On-going | On-going | On-going | On-going | Completed as per Program of Works
[7 empty] | Project Engineer: | Gamad/Clar | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 65482.21 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 12
[7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: |  | Actual: | 50% | Actual: | 50% | Actual: | 50% | Actual: | 85.4% | Actual: | 100%
[7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0.42% | Slippage: | 0%
[7 empty] | Date Allotment Released: | 2020-01-02 | Date completed: | 2020-12-31
[7 empty] | Date Started: | 2020-01-02
ROAD ID 132 - Mugas - Lunga-og |  | GENERAL FUND CY 2020 | Maintenance | 2.68 | km | MBA | Project Cost: | 96490.97 | Target Completion Date: | 2020-12-31 23:59 | Program: | 96490.97 | Planned: | 50% | Planned: | 50% | Planned: | 50% | Planned: | 82.4% | Planned: | 100% | No. of Persons: | 6 | On-going | On-going | On-going | On-going | On-going | Completed as per Program of Works
[7 empty] | Project Engineer: | Gamad/Clar | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 96490.97 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 20
[7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: |  | Actual: | 50% | Actual: | 50% | Actual: | 50% | Actual: | 85.1% | Actual: | 100%
[7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 2.7% | Slippage: | 0%
[7 empty] | Date Allotment Released: | 2020-01-02 | Date completed: | 2020-12-31
[7 empty] | Date Started: | 2020-01-02
ROAD ID 132 - Mugas - Lunga-og |  | GENERAL FUND CY 2020 | Maintenance | 2.68 | km | CBRMC | Project Cost: | 74256.11 | Target Completion Date: | 2020-12-15 23:59 | Program: | 74256.11 | Planned: |  | Planned: |  | Planned: |  | Planned: | 42.13% | Planned: | 100% | No. of Persons: | 3 | On-going | On-going | On-going | On-going | On-going | Completed as per Program of Works
[7 empty] | Project Engineer: | Maligro | Revised Completion Date: | 2021-01-11 23:59 | Allotment: | 74256.11 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 18
[7 empty] | Implementor: | Lunga-og Tribal Association | No. of days suspended: | 27 | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: | 42.13% | Actual: | 100%
[7 empty] | Duration: | 184 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: | 2020-01-02 | Date completed: | 2020-12-15
[7 empty] | Date Started: | 2020-06-15
ROAD ID 134 - New Katipunan - Pantaron |  | GENERAL FUND CY 2020 | Maintenance |  | km | MBA | Project Cost: | 71748.41 | Target Completion Date: | 2020-12-31 23:59 | Program: | 71748.41 | Planned: | 50% | Planned: | 50% | Planned: | 50% | Planned: | 84.86% | Planned: | 100% | No. of Persons: | 2 | On-going | On-going | On-going | On-going | On-going | Completed as per Program of Works
[7 empty] | Project Engineer: | Gamad/Clar | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 71748.41 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 20
[7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: |  | Actual: | 51% | Actual: | 51% | Actual: | 51% | Actual: | 82.1% | Actual: | 100%
[7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 1% | Slippage: | 1% | Slippage: | 1% | Slippage: | -2.76% | Slippage: | 0%
[7 empty] | Date Allotment Released: | 2020-01-02 | Date completed: | 2020-12-31
[7 empty] | Date Started: | 2020-01-02
ROAD ID 135 - Sto. Tomas - Bdry. Mamacao |  | GENERAL FUND CY 2020 | Maintenance | 4.9 | km | MBA | Project Cost: | 195671.17 | Target Completion Date: | 2020-12-31 23:59 | Program: | 195671.17 | Planned: | 50% | Planned: | 50% | Planned: | 50% | Planned: | 82.45% | Planned: | 100% | No. of Persons: | 3 | On-going | On-going | On-going | On-going | On-going | Completed as per Program of Works
[7 empty] | Project Engineer: | Gamad/Clar | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 195671.17 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 33
[7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: |  | Actual: | 52% | Actual: | 52% | Actual: | 52% | Actual: | 83.4% | Actual: | 100%
[7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 2% | Slippage: | 2% | Slippage: | 2% | Slippage: | 0.95% | Slippage: | 0%
[7 empty] | Date Allotment Released: | 2020-01-02 | Date completed: | 2020-12-31
[7 empty] | Date Started: | 2020-01-02
ROAD ID 136 - Fd. Rd. 3 - San Jose |  | GENERAL FUND CY 2020 | Maintenance | 4.55 | km | MBA | Project Cost: | 176994.35 | Target Completion Date: | 2020-12-31 23:59 | Program: | 176994.35 | Planned: | 50% | Planned: | 50% | Planned: | 50% | Planned: | 84.9% | Planned: | 100% | No. of Persons: | 2 | On-going | On-going | On-going | On-going | On-going | Completed as per Program of Works
[7 empty] | Project Engineer: | Gamad/Clar | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 176994.35 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 10
[7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: |  | Actual: | 55% | Actual: | 55% | Actual: | 55% | Actual: | 85.4% | Actual: | 100%
[7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 5% | Slippage: | 5% | Slippage: | 5% | Slippage: | 0.5% | Slippage: | 0%
[7 empty] | Date Allotment Released: | 2020-01-02 | Date completed: | 2020-12-31
[7 empty] | Date Started: | 2020-01-02
ROAD ID 139 - Nafco - Bobongon |  | GENERAL FUND CY 2020 | Maintenance |  | km | MBA | Project Cost: | 89179.68 | Target Completion Date: | 2020-12-31 23:59 | Program: | 89179.68 | Planned: | 50% | Planned: | 50% | Planned: | 50% | Planned: | 84.61% | Planned: | 100% | No. of Persons: | 3 | On-going | On-going | On-going | On-going | On-going | Completed as per Program of Works
[7 empty] | Project Engineer: | Gamad/Clar | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 89179.68 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 56
[7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: |  | Actual: | 55% | Actual: | 55% | Actual: | 55% | Actual: | 85.12% | Actual: | 100%
[7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 5% | Slippage: | 5% | Slippage: | 5% | Slippage: | 0.51% | Slippage: | 0%
[7 empty] | Date Allotment Released: | 2020-01-02 | Date completed: | 2020-12-31
[7 empty] | Date Started: | 2020-01-02
ROAD ID 139 - Nafco - Bobongon |  | GENERAL FUND CY 2020 | Maintenance |  | km | CBRMC | Project Cost: | 80293.17 | Target Completion Date: | 2021-02-03 | Program: | 80293.17 | Planned: |  | Planned: |  | Planned: |  | Planned: | 42.5% | Planned: | 100% | No. of Persons: | 2 | Purchase Order # 2020030968 (Bobongon Rural Waterworks & Sanitation Association, Inc.) | Purchase Order # 2020030968 (Bobongon Rural Waterworks & Sanitation Association, Inc.) | Purchase Order # 2020030968 (Bobongon Rural Waterworks & Sanitation Association, Inc.) | On-going | On-going | Completed as per Program of Works
[7 empty] | Project Engineer: | Maligro | Revised Completion Date: |  | Allotment: | 80293.17 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 2
[7 empty] | Implementor: | Bobongon Rural Waterworks & Sanitation Association, Inc. | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: | 42.5% | Actual: | 100%
[7 empty] | Duration: | 6 months | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed: | 2020-12-09
[7 empty] | Date Started: | 2020-08-03
ROAD ID 146 - Bdry. Tagum - Crossing Kinamayan Sto. Tomas |  | GENERAL FUND CY 2020 | Maintenance |  | km | MBA | Project Cost: | 790874.1 | Target Completion Date: | 2020-12-31 23:59 | Program: | 790874.1 | Planned: | 50% | Planned: | 50% | Planned: | 50% | Planned: | 82.48% | Planned: | 100% | No. of Persons: | 3 | On-going | On-going | On-going | On-going | On-going | Completed as per Program of Works
[7 empty] | Project Engineer: | Gamad/Clar | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 790874.1 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 66
[7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: |  | Actual: | 50% | Actual: | 50% | Actual: | 50% | Actual: | 82.4% | Actual: | 100%
[7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | -0.08% | Slippage: | 0%
[7 empty] | Date Allotment Released: | 2020-01-02 | Date completed: | 2020-12-31
[7 empty] | Date Started: | 2020-01-02
ROAD ID 151 - San Jose - Sitio Mahayahay, Magwawa |  | GENERAL FUND CY 2020 | Maintenance | 0.84 | km | MBA | Project Cost: | 22943.54 | Target Completion Date: | 2020-12-31 23:59 | Program: | 22943.54 | Planned: | 50% | Planned: | 57.05% | Planned: | 57.05% | Planned: | 81.5% | Planned: | 100% | No. of Persons: | 3 | On-going | On-going | On-going | On-going | On-going | Completed as per Program of Works
[7 empty] | Project Engineer: | Gamad/Clar | Revised Completion Date: | 2021-01-27 23:59 | Allotment: | 22943.54 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 18
[7 empty] | Implementor: | PEO | No. of days suspended: | 27 | Disbursement: |  | Actual: | 50% | Actual: | 58.79% | Actual: | 58.79% | Actual: | 82.4% | Actual: | 100%
[7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 1.74% | Slippage: | 1.74% | Slippage: | 0.9% | Slippage: | 0%
[7 empty] | Date Allotment Released: | 2020-01-02 | Date completed: | 2020-12-31
[7 empty] | Date Started: | 2020-01-02
Improvement of Potable Water System, Brgy. Magsaysay, Carmen |  | 20% DF CY 2020 | Water System |  |  | Contract | Project Cost: | 1000000 | Target Completion Date: | 2021-01-16 | Program: | 1000000 | Planned: | 13.2% | No. of Persons: | 3 | On-going |  | Planned: | 100% | Planned: | 100% | No. of Persons: | 3 |  |  |  | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per Program of Works
[7 empty] | Project Engineer: | Estorco | Revised Completion Date: |  | Allotment: | 1000000 | Revised: |  | No. of Man-days: | 66 |  |  | Revised: |  | Revised: |  | No. of Man-days: | 66
[7 empty] | Implementor: | JJR Const. & Supply | No. of days suspended: |  | Disbursement: |  | Actual: | 2.3% |  |  |  |  | Actual: | 100% | Actual: | 100%
[7 empty] | Duration: | 100 | No. of days extended: |  |  |  | Slippage: | -10.9% |  |  |  |  | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed: | 2020-11-27
[7 empty] | Date Started: | 2020-10-08
Poultry House and Training Center Phase 2, Talaingod |  | SB # 1 CY 2020 | Building |  | sq.m |  | Project Cost: | 500000 | Target Completion Date: | 2020-11-16 23:59 | Program: | 500000 | Planned: |  | Planned: |  | Planned: |  | Planned: | 100% | Planned: | 100% | No. of Persons: |  | For bidding on June 30, 2020; Re-bid July 28, 2020. | For bidding on June 30, 2020; Re-bid July 28, 2020. | For bidding on June 30, 2020; Re-bid July 28, 2020. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per Program of Works
[7 empty] | Project Engineer: | Dadula | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: | JJR Const. & Supply | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: | 100% | Actual: | 100%
[7 empty] | Duration: | 47 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed: | 2020-11-16 23:59
[7 empty] | Date Started: | 2020-10-01
Repair/Rehab. Of Concrete Road Jct. Suaon-Libuton, Kapalong |  | SB NO. 3 CY 2019 | Road Drainage rehabiliated |  | km | Admin | Project Cost: | 1000000 | Target Completion Date: | 2020-02-15 23:46 | Program: | 1000000 | Planned: | 14.73% | Planned: | 14.73% | Planned: | 30.27% | Planned: | 30.27% | Planned: | 100% | No. of Persons: |  | Plan On-going | Plan On-going | Plan On-going | Completed as per physical accomplishment. | Completed as per physical accomplishment. | Completed as per Program of Works
[7 empty] | Project Engineer: | Bacaron | Revised Completion Date: | 2020-11-15 23:46 | Allotment: | 1000000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: | PEO | No. of days suspended: | 228 | Disbursement: | 142000 | Actual: | 14.2% | Actual: | 14.2% | Actual: | 30.27% | Actual: | 30.27% | Actual: | 100%
[7 empty] | Duration: | 90 | No. of days extended: | 46 |  |  | Slippage: | -0.53% | Slippage: | -0.53% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: | 2019-03-12 | Date completed: | 2020-11-15
[7 empty] | Date Started: | 2019-11-18
Rehab. Of Saug Bridge of Slope Protection, New Corella |  | QRF CY 2015 & 2016 | Slope Protection | 356.4 | ln.m | Admin | Project Cost: | 4850000 | Target Completion Date: | 2019-05-02 23:46 | Program: | 4850000 | Planned: | 84.06% | Planned: | 100% | Planned: | 100% | Planned: | 100% | Planned: | 100% | No. of Persons: | 7 | Final Abstract # 0320200900 (Alpebel Builders & Supply Corp.) | Final Abstract # 0320200900 (Alpebel Builders & Supply Corp.) | Final Abstract # 0320200900 (Alpebel Builders & Supply Corp.) | Completed as per physical accomplishment. | Completed as per physical accomplishment. | Completed as per Program of Works
[7 empty] | Project Engineer: | Gone | Revised Completion Date: | 2020-12-30 23:46 | Allotment: | 4850000 | Revised: |  | Revised: | 77.89% | Revised: | 77.89% | Revised: | 77.89% | Revised: |  | No. of Man-days: | 182
[7 empty] | Implementor: | PEO | No. of days suspended: | 533 | Disbursement: | 1628912.92 | Actual: | 77.63% | Actual: | 86.91% | Actual: | 86.91% | Actual: | 86.91% | Actual: | 100%
[7 empty] | Duration: | 120 | No. of days extended: | 75 |  |  | Slippage: | -6.43% | Slippage: | 9.02% | Slippage: | 9.02% | Slippage: | 9.02% | Slippage: | 0%
[7 empty] | Date Allotment Released: | 2018-05-25 | Date completed:
[7 empty] | Date Started: | 2019-01-03
Note on D161: chai: SB No. 1 CY 2019 (STIMULUS PROJECT)
Note on D185: chai: previously 20% DF
Note on D191: chai: previously 20% DF
Note on D197: chai: previously 20% DF
Note on D203: chai: previously 20% DF
Note on D221: chai: 20% DF CY 2019
Note on D227: chai: 20% DF CY 2019
Note on D233: chai: previously 20% DF CY 2019 (500,000.)
Note on D251: chai: previously 20% DF CY 2019 (500,000.)
Note on D893: Cerela Montes: Previously 20% DF CY 2019

## 4th Quarter CY 2020 (On-going)
|  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | [11 empty] | 0
` | ECONOMIC (INFRASTRUCTURE DEV'T. PROGRAM)
OFFICE/AGENCY: | PROVINCIAL ENGINEER'S OFFICE
AREA: | 1ST ENGINEERING DISTRICT - COMPLETED, ON-GOING AND FOR IMPLEMENTATION PROJECTS | [7 empty] | Total extended
#REF!
#REF!
NAME OF PROJECT |  | SOURCE OF FUND | TYPE OF PROJECT | PHYSICAL TARGET (DESCRIPTION) |  | MODE OF IMPLEMENTATION | PROJECT DATA |  |  |  | FINANCIAL |  | PHYSICAL ACCOMPLISHMENT (JULY) |  | PHYSICAL ACCOMPLISHMENT (AUGUST) |  | PHYSICAL ACCOMPLISHMENT (SEPTEMBER) |  | PHYSICAL ACCOMPLISHMENT (OCTOBER) |  | PHYSICAL ACCOMPLISHMENT |  | EMPLOYMENT GENERATED |  | REMARKS (JULY) | REMARKS (AUGUST) | REMARKS (SEPTEMBER) | REMARKS (OCTOBER | REMARKS (NOVEMBER) | REMARKS
Rehab. Of Pob.-Limbaan-Suawon-Macgum FMR w/ Bridge (42 ln.m), New Corella, Davao del Norte |  | PRDP CY 2015 | Road Concreting | 15.01 | km | Contract | Project Cost: | 205202114.16 | Target Completion Date: | 2018-11-06 23:46 | Program: | 205202114.16 | Planned: | 100% | Planned: | 100% | Planned: | 100% | Planned: | 100% | Planned: | 100% | No. of Persons: | 40 | On-going (Increase of Project Cost due to Variation Order Php 14,948,622.18, Partial suspension due to soft soil from sta. 8+000 - 10+000); (Suspended last April 5, 2020 due to COVID; Resumption Order dated June 1, 2020) | On-going (Increase of Project Cost due to Variation Order Php 14,948,622.18, Partial suspension due to soft soil from sta. 8+000 - 10+000); (Suspended last April 5, 2020 due to COVID; Resumption Order dated June 1, 2020) | On-going (Increase of Project Cost due to Variation Order Php 14,948,622.18, Partial suspension due to soft soil from sta. 8+000 - 10+000); (Suspended last April 5, 2020 due to COVID; Resumption Order dated June 1, 2020) | On-going (Increase of Project Cost due to Variation Order Php 14,948,622.18, Partial suspension due to soft soil from sta. 8+000 - 10+000); (Suspended last April 5, 2020 due to COVID; Resumption Order dated June 1, 2020) | On-going (Increase of Project Cost due to Variation Order Php 14,948,622.18, Partial suspension due to soft soil from sta. 8+000 - 10+000); (Suspended last April 5, 2020 due to COVID; Resumption Order dated June 1, 2020) | Suspended due to variation order dated November 2020
[7 empty] | Project Engineer: | Madrigal | Revised Completion Date: | 2020-10-25 23:46 | Allotment: | 205202114.16 | Revised: | 86.35% | Revised: | 87.69% | Revised: | 87.69% | Revised: | 87.69% | Revised: | 88.78% | No. of Man-days: | 1200
[7 empty] | Implementor: | Dvo. Rock Mixer | No. of days suspended: | 229 | Disbursement: | 141497191.47 | Actual: | 79.97% | Actual: | 81.21% | Actual: | 81.21% | Actual: | 81.21% | Actual: | 83.08%
[7 empty] | Duration: | 943 | No. of days extended: | 490 |  |  | Slippage: | -6.385% | Slippage: | -6.487% | Slippage: | -6.487% | Slippage: | -6.487% | Slippage: | -5.705%
[7 empty] | Date Allotment Released: | CY 2015 | Date completed:
[7 empty] | Date Started: | 2016-04-08
Proposed Davao del Norte Tourism Billboard, Brgy. Lasang, Panabo City |  | SB # 1 CY 2015 | Billboard |  | sq.m | Admin | Project Cost: | 756400 | Target Completion Date: | 2015-05-10 23:59 | Program: | 756400 | Planned: | 11.78% | Planned: | 11.78% | Planned: | 11.78% | Planned: | 11.78% | Planned: | 11.78% | No. of Persons: |  | delay due to change location & design code. For AIP amendment from Panabo City to Gov't Center, Mankilam | delay due to change location & design code. For AIP amendment from Panabo City to Gov't Center, Mankilam | delay due to change location & design code. For AIP amendment from Panabo City to Gov't Center, Mankilam | delay due to change location & design code. For AIP amendment from Panabo City to Gov't Center, Mankilam | delay due to change location & design code. For AIP amendment from Panabo City to Gov't Center, Mankilam | delay due to change location & design code. For AIP amendment from Panabo City to Gov't Center, Mankilam
[7 empty] | Project Engineer: | Porras | Revised Completion Date: |  | Allotment: | 756400 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: | 332087.3 | Actual: | 11.78% | Actual: | 11.78% | Actual: | 11.78% | Actual: | 11.78% | Actual: | 11.78%
[7 empty] | Duration: | 42 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: | 2015-05-06 | Date completed:
[7 empty] | Date Started: | 2015-03-30
Construction of Provincial Training Center , Compound Fence, Kinawitnon, Babak District, IGCS |  | 20% DF CY 2016 | Fence |  | sq.m | Admin | Project Cost: | 940000 | Target Completion Date: | 2018-06-19 23:59 | Program: | 940000 | Planned: | 68% | Planned: | 68% | Planned: | 68% | Planned: | 68% | Planned: | 68% | No. of Persons: |  | Temporarily suspended 4/23/18 due to undemolished structures of illegal settlers | Temporarily suspended 4/23/18 due to undemolished structures of illegal settlers | Temporarily suspended April 23, 2018 due to undemolished structures of illegal settlers(For resumption) | Temporarily suspended April 23, 2018 due to undemolished structures of illegal settlers(For resumption) | Temporarily suspended April 23, 2018 due to undemolished structures of illegal settlers(For resumption) | Temporarily suspended April 23, 2018 due to undemolished structures of illegal settlers(For resumption)
[7 empty] | Project Engineer: | Pacquiao | Revised Completion Date: |  | Allotment: | 940000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: | 933418.8 | Actual: | 75% | Actual: | 75% | Actual: | 75% | Actual: | 75% | Actual: | 75%
[7 empty] | Duration: | 100 | No. of days extended: |  |  |  | Slippage: | 7% | Slippage: | 7% | Slippage: | 7% | Slippage: | 7% | Slippage: | 7%
[7 empty] | Date Allotment Released: | 2017-09-19 | Date completed:
[7 empty] | Date Started: | 2018-03-12
Repair of Damaged/Creeks Along Mankilam Creek, Tagum City |  | QRF CY 2015 & 2016 | Slope Protection |  |  |  | Project Cost: | 1050000 | Target Completion Date: | 2020-04-04 23:46 | Program: | 1050000 | Planned: |  | Planned: |  | Planned: | 100% | Planned: | 100% | Planned: | 63.85% | No. of Persons: | 10 | For AIP Amendment | For AIP Amendment | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | On-going
[7 empty] | Project Engineer: | Crucio | Revised Completion Date: | 2021-01-30 23:46 | Allotment: | 1050000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 169
[7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: | 100% | Actual: | 100% | Actual: | 63.85%
[7 empty] | Duration: | 90 | No. of days extended: | 301 |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
[7 empty] | Date Started: | 2020-01-06
Rehab./Repair of Mamacao Bailey Bridge (Retrofitting of Pier and Substructure) |  | QRF CY 2015 & 2016 | Slope Protection | 356.4 | ln.m | Admin | Project Cost: | 2000000 | Target Completion Date: | 2021-03-30 23:46 | Program: | 2000000 | Planned: | 84.06% | Planned: | 100% | Planned: | 100% | Planned: | 100% | Planned: | 3.86% | No. of Persons: | 13 | Final Abstract # 0320200900 (Alpebel Builders & Supply Corp.) | Final Abstract # 0320200900 (Alpebel Builders & Supply Corp.) | Final Abstract # 0320200900 (Alpebel Builders & Supply Corp.) | Completed as per physical accomplishment. | Completed as per physical accomplishment. | On-going
[7 empty] | Project Engineer: | Lumapat | Revised Completion Date: |  | Allotment: | 2000000 | Revised: |  | Revised: | 77.89% | Revised: | 77.89% | Revised: | 77.89% | Revised: |  | No. of Man-days: | 338
[7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: | 77.63% | Actual: | 86.91% | Actual: | 86.91% | Actual: | 86.91% | Actual: | 1.56%
[7 empty] | Duration: | 120 | No. of days extended: |  |  |  | Slippage: | -6.43% | Slippage: | 9.02% | Slippage: | 9.02% | Slippage: | 9.02% | Slippage: | -2.3%
[7 empty] | Date Allotment Released: |  | Date completed:
[7 empty] | Date Started: | 2020-12-01
Improvement of Sto. Tomas Production Center with Common Facility, Sto. Tomas |  | PRDP CY 2016 | Building | 1901 | sq.m | Contract | Project Cost: | 9825000 | Target Completion Date: | 2018-12-24 23:59 | Program: | 9825000 | Planned: | 94.55% | Planned: | 100% | Planned: | 100% | Planned: | 100% | Planned: | 100% | No. of Persons: | 20 | On-going | Final Abstract # 0320200900 (Alpebel Builders & Supply Corp.) | Final Abstract # 0320200900 (Alpebel Builders & Supply Corp.) | Completed as per physical accomplishment. | Completed as per physical accomplishment. | On-going
[7 empty] | Project Engineer: | Azotes | Revised Completion Date: | May 24, 2021 | Allotment: | 9825000 | Revised: | 78.32% | Revised: | 83.43% | Revised: | 83.43% | Revised: | 83.43% | Revised: | 22.53% | No. of Man-days: | 500
[7 empty] | Implementor: | Manantan | No. of days suspended: | 501 | Disbursement: |  | Actual: | 71.89% | Actual: | 75.19% | Actual: | 75.19% | Actual: | 75.19% | Actual: | 30.33%
[7 empty] | Duration: | 330 | No. of days extended: |  |  |  | Slippage: | -6.424% | Slippage: | -8.238% | Slippage: | -8.238% | Slippage: | -8.238% | Slippage: | 7.8%
[7 empty] | Date Allotment Released: | CY 2014 | Date completed:
[7 empty] | Date Started: | 2018-01-29
Construction of Water Reservoir & Purchase of P.E. Pipelines, Sagayen, Asuncion |  | 20% DF CY 2017 (STIMULUS) | Water System |  |  | MLGU | Project Cost: | 500000 | Target Completion Date: | 2018-11-15 | Program: | 500000 | Planned: | 90% | Planned: | 90% | Planned: | 90% | Planned: | 90% | Planned: | 90% | No. of Persons: |  | Suspended due to non availability of water source during drilling.Find another location. Fund already transferred at Municipality of Asuncion with ChecK No. 2445174 and OR # 9238468, | Suspended due to non availability of water source during drilling.Find another location. Fund already transferred at Municipality of Asuncion with ChecK No. 2445174 and OR # 9238468, | Project not implemented due to non availability of water source during drilling. Awaiting for the official documents from Brgy. Sagayen and MLGU - Asuncion for the cancellation of the project. | Project not implemented due to non availability of water source during drilling. Awaiting for the official documents from Brgy. Sagayen and MLGU - Asuncion for the cancellation of the project. | Project not implemented due to non availability of water source during drilling. Awaiting for the official documents from Brgy. Sagayen and MLGU - Asuncion for the cancellation of the project. | Project not implemented due to non availability of water source during drilling. Awaiting for the official documents from Brgy. Sagayen and MLGU - Asuncion for the cancellation of the project.
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: | MEO | No. of days suspended: |  | Disbursement: |  | Actual: | 90% | Actual: | 90% | Actual: | 90% | Actual: | 90% | Actual: | 90%
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: | 2017-12-28 | Date completed:
[7 empty] | Date Started: | 2018-11-15
Road Rehabilitation at Prk. 1-Prk. 5, Sta. Fe, New Corella |  | 20% DF CY 2017 (STIMULUS) | Court |  |  | MLGU | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Fund already transferred at Municipality of Talaingod with ChecK No. 2445181 and OR # 7955667, dated March 16, 2018 . Amended from Electrification @ Prk. 1A-Prk. 5A) | On-going (Implemented by MLGU, since transfer of fund ) | On-going (Implemented by MLGU, since transfer of fund ) | On-going (Implemented by MLGU, since transfer of fund ) | On-going (Implemented by MLGU, since transfer of fund ) | On-going (Implemented by MLGU, since transfer of fund )
[7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: | 2017-12-28 | Date completed:
[7 empty] | Date Started: | 2020-08-25
Construction of 2 Rooms Comfort Room, Brgy. Cacao, Panabo City |  | 20% DF CY 2017 (STIMULUS) | Building |  | sq.m | MLGU | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | Planned: | 100% | Planned: | 100% | Planned: |  | Planned: |  | No. of Persons: |  | Issued warning for termination of the contract | Completed (Implemented by MLGU, since transfer of fund ) | Completed (Implemented by MLGU, since transfer of fund ) |  |  | On-going (Implemented by MLGU, since transfer of fund )
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: | 100% |  | 100%
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: |  | Slippage: |  | Slippage:
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Const. of Multi-Purpose Bldg. @ A.O. Floriendo National Highschool, Panabo City |  | 20% DF CY 2017 (STIMULUS) | Building |  |  | MLGU | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Fund transfer to LGU- 3/28/2019 with check no. 2574939 and OR no. 0166518 - Materials Delivered. Construction on-going | Materials already procured. Ongoing hiring of Admin Laborers. Target date to start the project on September 14, 2020.(Implemented by MLGU, since transfer of fund ) | On-going .(Implemented by MLGU, since transfer of fund ) | On-going .(Implemented by MLGU, since transfer of fund ) | On-going .(Implemented by MLGU, since transfer of fund ) | On-going .(Implemented by MLGU, since transfer of fund )
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: | MLGU | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: | 2017-12-19 | Date completed:
Date Started:
Const. of Concrete Drainage Canal, Kimamon, Panabo City |  | 20% DF CY 2017 (STIMULUS) | Drainage |  |  | MLGU | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | For Implementation | For Implementation | For Implementation | For Implementation | For Implementation | For Implementation
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: | 2017-12-19 | Date completed:
Date Started:
Upgrading of DDNSTC (Basketball/Voleyball MP Covered Court),Sports Center, Mankilam, Tagum City |  | SB # 4 CY 2017 | Covered Court | 2252.69 | sq.m | Contract | Project Cost: | 99992356.64 | Target Completion Date: | 2019-07-11 | Program: | 99992356.64 | Planned: | 100% | Planned: | 100% | Planned: | 100% | Planned: | 100% | Planned: | 100% | No. of Persons: | 10 | On-going (Suspended last April 5, 2020 due to COVID; Resumption Order dated May 4, 2020) | On-going | On-going | On-going | On-going | Suspended as of April 7, 2019
[7 empty] | Project Engineer: | Daral | Revised Completion Date: |  | Allotment: | 99992356.64 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 310
[7 empty] | Implementor: | YBC | No. of days suspended: |  | Disbursement: | 18280402.33 | Actual: | 73.04% | Actual: | 80.54% | Actual: | 80.54% | Actual: | 80.54% | Actual: | 90%
[7 empty] | Duration: | 360 | No. of days extended: | 20 |  |  | Slippage: | -26.96% | Slippage: | -19.46% | Slippage: | -19.46% | Slippage: | -19.46% | Slippage: | -10%
[7 empty] | Date Allotment Released: | 2018-10-16 | Date completed:
[7 empty] | Date Started: | 2018-07-17
Const. of Trading Post, Storage Building with (1) unit Hauling Truck, Prk. Ramihan Datu Abdul, Panabo City |  | OPPAP-PAMANA CY 2017 | Building |  | sq.m | Contract | Project Cost: | 3975000 | Target Completion Date: | 2020-04-05 23:59 | Program: | 3975000 | Planned: | 100% | Planned: | 100% | Planned: | 100% | Planned: | 100% | Planned: | 100% | No. of Persons: | 10 | On-going | On-going | On-going | On-going | On-going/ Subject for Liquidated damages | Suspended
[7 empty] | Project Engineer: | Azotes | Revised Completion Date: | August 24, 2020 | Allotment: | 3975000 | Revised: | 41.6% | Revised: | 100% | Revised: | 100% | Revised: | 100% | Revised: | 100% | No. of Man-days: | 260
[7 empty] | Implementor: | Ultra Core | No. of days suspended: | 71 | Disbursement: |  | Actual: | 41.6% | Actual: | 56.88% | Actual: | 56.88% | Actual: | 56.88% | Actual: | 43.12%
[7 empty] | Duration: | 137 | No. of days extended: | 100 |  |  | Slippage: | 0% | Slippage: | -43.12% | Slippage: | -43.12% | Slippage: | -43.12% | Slippage: | -56.88%
[7 empty] | Date Allotment Released: | CY 2017 | Date completed:
[7 empty] | Date Started: | 2019-11-21
Trading Post, Storage and Hauling Truck Libuak, Island Garden City of Samal (IGACOS) |  | OPPAP-PAMANA CY 2017 | Building |  |  |  | Project Cost: | 4000000 | Target Completion Date: | 2021-01-31 | Program: | 4000000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: | 27.42% | No. of Persons: | 8 | For awarding ALPEBEL | For awarding ALPEBEL | For awarding ALPEBEL | For awarding ALPEBEL | Mobilization on-going | On-going
[7 empty] | Project Engineer: | Andoy/Porras | Revised Completion Date: |  | Allotment: | 4000000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 176
[7 empty] | Implementor: | Alpebel Builders | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual: | 27.42%
[7 empty] | Duration: | 150 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: | CY 2018 | Date completed:
[7 empty] | Date Started: | 2020-09-03
Construction of PWS Level II in Purok 7-A and 7-B, Capungagan, Kapalong |  | OPPAP-PAMANA CY 2017 | Potable Water System |  |  | Admin | Project Cost: | 1760000 | Target Completion Date: | 2020-02-03 | Program: | 1760000 | Planned: | 100% | Planned: | 100% | Planned: | 100% | Planned: | 100% | Planned: | 100% | No. of Persons: | 25 | Suspended due to elecrical permits | Suspended dsted July 30, 2020 due to elecrical permits | Suspended dsted July 30, 2020 due to elecrical permits | Suspended dsted July 30, 2020 due to elecrical permits | Suspended dsted July 30, 2020 due to elecrical permits | Suspended dsted July 30, 2020 due to elecrical permits
[7 empty] | Project Engineer: | Kabinge | Revised Completion Date: | 2020-04-15 | Allotment: | 1760000 | Revised: | 100% | Revised: | 95.08% | Revised: | 95.08% | Revised: | 95.08% | Revised: | 95.08% | No. of Man-days: | 375
[7 empty] | Implementor: | PEO | No. of days suspended: | 28 | Disbursement: | 1235344 | Actual: | 95.57% | Actual: | 98% | Actual: | 98% | Actual: | 98% | Actual: | 98%
[7 empty] | Duration: | 70 | No. of days extended: | 44 |  |  | Slippage: | -4.43% | Slippage: | 2.92% | Slippage: | 2.92% | Slippage: | 2.92% | Slippage: | 2.92%
[7 empty] | Date Allotment Released: | 2019-11-25 | Date completed:
[7 empty] | Date Started: | 2019-11-25
Construction of PWS Level II in Purok 2, Pag-Asa, kapalong |  | OPPAP-PAMANA CY 2017 | Potable Water System |  |  | Admin | Project Cost: | 2310000 | Target Completion Date: | 2020-04-09 | Program: | 2310000 | Planned: | 100% | Planned: | 100% | Planned: | 100% | Planned: | 100% | Planned: | 100% | No. of Persons: | 23 | On-going (Suspended last April 5, 2020 due to COVID; resumption order dated May 4, 2020) | Suspended dated August 26, 2020 due to elecrical permits and delivery of water tank | Suspended dated August 26, 2020 due to elecrical permits and delivery of water tank | Suspended dated August 26, 2020 due to elecrical permits and delivery of water tank | Suspended dated August 26, 2020 due to elecrical permits and delivery of water tank | Suspended dated August 26, 2020 due to elecrical permits and delivery of water tank
[7 empty] | Project Engineer: | Dadula | Revised Completion Date: | 2020-08-20 | Allotment: | 2310000 | Revised: | 100% | Revised: | 81.57% | Revised: | 81.57% | Revised: | 81.57% | Revised: | 100% | No. of Man-days: | 713
[7 empty] | Implementor: | PEO | No. of days suspended: | 28 | Disbursement: | 1678908 | Actual: | 72.68% | Actual: | 76.39% | Actual: | 76.39% | Actual: | 76.39% | Actual: | 100%
[7 empty] | Duration: | 115 | No. of days extended: | 105 |  |  | Slippage: | -27.32% | Slippage: | -5.179% | Slippage: | -5.179% | Slippage: | -5.179% | Slippage: | 0%
[7 empty] | Date Allotment Released: | 2019-11-25 | Date completed: | 2020-08-20
[7 empty] | Date Started: | 2019-12-16
Rice Mill for Upland Rice, Palma Gil, Talaingod |  | OPPAP-PAMANA CY 2017 | Rice Mill |  |  | Admin | Project Cost: | 1000000 | Target Completion Date: | 2020-07-30 23:46 | Program: | 1000000 | Planned: | 42.65% | Planned: | 42.65% | Planned: | 42.65% | Planned: | 42.65% | Planned: | 42.65% | No. of Persons: | 6 | On-going | On-going | On-going | On-going | On-going | Suspended last July 25, 2020. Still waiting for the delivery of Rice Mill as part of the Program.
[7 empty] | Project Engineer: | Torrecampo | Revised Completion Date: | 2020-07-30 23:46 | Allotment: | 1000000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 90
[7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: | 426500 | Actual: | 42.65% | Actual: | 42.65% | Actual: | 42.65% | Actual: | 42.65% | Actual: | 42.65%
[7 empty] | Duration: | 60 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
[7 empty] | Date Started: | 2020-06-01
Const. of Potable Water System at Brgy. Tibungol, Panabo City |  | 20% DF CY 2018 | Water System |  | ln.m | Admin | Project Cost: | 1250000 | Target Completion Date: | 2020-04-15 23:59 | Program: | 1250000 | Planned: | 2.13% | Planned: | 2.13% | Planned: | 2.13% | Planned: | 2.13% | Planned: | 2.13% | No. of Persons: | 3 | Suspended dated February 19, 2020 undelivered hardware materials (Supplier refused to deliver. Letter already submitted to BAC.) | Suspended dated February 19, 2020 undelivered hardware materials (materials re-bid) | Suspended dated February 19, 2020 undelivered hardware materials (materials re-bid) | Suspended dated February 19, 2020 undelivered hardware materials (materials re-bid) | Suspended dated February 19, 2020 undelivered hardware materials (materials re-bid) | Suspended dated February 19, 2020 undelivered hardware materials (Supplier refused to deliver. Letter already submitted to BAC.)
[7 empty] | Project Engineer: | Andoy | Revised Completion Date: |  | Allotment: | 1250000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 15
[7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: | 0.76% | Actual: | 0.76% | Actual: | 0.76% | Actual: | 0.76% | Actual: | 0.76%
[7 empty] | Duration: | 87 | No. of days extended: |  |  |  | Slippage: | -1.37% | Slippage: | -1.37% | Slippage: | -1.37% | Slippage: | -1.37% | Slippage: | -1.37%
[7 empty] | Date Allotment Released: | 2018-11-21 | Date completed:
[7 empty] | Date Started: | 2020-01-20
Const. of Distribution Line in Sitio Prk. 1,3,4, 11 and 7, Camansa, Asuncion |  | 20% DF CY 2018 | Electrification |  |  | Contract | Project Cost: | 4000000 | Target Completion Date: |  | Program: | 4000000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: | 78% | No. of Persons: |  | Awarded to 3E ELECTRICAL SALES & SERVICES | Awarded to 3E ELECTRICAL SALES & SERVICES | For impelementation (Awarded to 3E ELECTRICAL SALES & SERVICES) | For impelementation (Awarded to 3E ELECTRICAL SALES & SERVICES) | For impelementation (Awarded to 3E ELECTRICAL SALES & SERVICES) | On-going
[7 empty] | Project Engineer: | Bueno | Revised Completion Date: | 0 | Allotment: | 4000000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: | 3E Electirical and Engineering | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual: | 78%
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
[7 empty] | Date Started: | 2020-08-06
Rehab. Of Multi-Purpose Gym & Facililies Maduao, Panabo City |  | 20% DF CY 2018 (STIMULUS) | Gym |  |  |  | Project Cost: | 500000 | Target Completion Date: | 2020-10-07 | Program: | 500000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Post qualification on process | Post qualification on process | Suspended due to overlapping of activity. (DIGOS CONTRAK CORP.) | Suspended due to overlapping of activity. (DIGOS CONTRAK CORP.) | Suspended due to overlapping of activity. (DIGOS CONTRAK CORP.) | Suspended due to overlapping of activity. (DIGOS CONTRAK CORP.)
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: | Digos Constrak Corp/ | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: | 34 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
[7 empty] | Date Started: | 2020-09-03
Electrification of Sitio Baongon-Diamond-Mansanitas, Dadatan, IGCS |  | 20% DF CY 2018 (STIMULUS) | Electrification |  |  |  | Project Cost: | 500000 | Target Completion Date: | 2020-05-09 | Program: | 500000 | Planned: |  | Planned: |  | Planned: | 100% | Planned: | 100% | Planned: | 100% | No. of Persons: |  | On-going (Subject for Liquidated damages) | On-going (Subject for Liquidated damages) | On-going (Subject for Liquidated damages) | On-going (Subject for Liquidated damages) | On-going (Subject for Liquidated damages) | On-going (Subject for Liquidated damages)
[7 empty] | Project Engineer: | Lu | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: | 100% | Revised: | 100% | Revised: | 100% | No. of Man-days:
[7 empty] | Implementor: | 3E Electrical Sales | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: | 65.1% | Actual: | 65.1% | Actual: | 65.1%
[7 empty] | Duration: | 60 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | -34.9% | Slippage: | -34.9% | Slippage: | -34.9%
[7 empty] | Date Allotment Released: |  | Date completed:
[7 empty] | Date Started: | 2020-03-10
Barangay Hall Improvement, Dagohoy, Talaingod |  | 20% DF CY 2018 (STIMULUS) | Building |  |  | Contract | Project Cost: | 500000 | Target Completion Date: | 2021-01-20 23:59 | Program: | 500000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | For amendment to Construction of Retaining Wall as per recommendation by Engr. Misa during site re-evaluation. Plan & POW completed.Resolution from the Brgy. Council to support the amendment c/o Engr. Canillada | For amendment to Construction of Retaining Wall as per recommendation by Engr. Misa during site re-evaluation. Plan & POW completed.Resolution from the Brgy. Council to support the amendment c/o Engr. Canillada | Awarded to Alpebels Builders & Supply Corporation | For implementation | For implementation | On-going
[7 empty] | Project Engineer: | Kabingue | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: | Alpebels Builders & Supply Corporation | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: | 45 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
[7 empty] | Date Started: | 2020-12-07
Construction of SP/Legislative Building, Gov't. Center, Mankilam, Tagum City |  | SB # 3 CY 2018 | Building |  |  | Contract | Project Cost: | 147262698.81 | Target Completion Date: | 2021-04-04 | Program: | 147262698.81 | Planned: | 5.78% | Planned: | 5.78% | Planned: | 14.98% | Planned: | 14.98% | Planned: | 58.3% | No. of Persons: | 34 | For amendment to Construction of Retaining Wall as per recommendation by Engr. Misa during site re-evaluation. Plan & POW completed.Resolution from the Brgy. Council to support the amendment c/o Engr. Canillada | For amendment to Construction of Retaining Wall as per recommendation by Engr. Misa during site re-evaluation. Plan & POW completed.Resolution from the Brgy. Council to support the amendment c/o Engr. Canillada | Awarded to Alpebels Builders & Supply Corporation | For implementation | For implementation | On-going
[7 empty] | Project Engineer: | Japay/Albaracin | Revised Completion Date: | 2021-05-01 | Allotment: | 147262698.81 | Revised: | 3.15% | Revised: | 4.777% | Revised: | 7.387% | Revised: | 7.387% | Revised: | 38.89% | No. of Man-days: | 884
[7 empty] | Implementor: | Tagum Builders | No. of days suspended: | 27 | Disbursement: |  | Actual: | 5.28% | Actual: | 7.37% | Actual: | 8.971% | Actual: | 8.971% | Actual: | 26.56%
[7 empty] | Duration: | 370 | No. of days extended: |  |  |  | Slippage: | 2.13% |  | 2.594% |  | 1.584% |  | 1.584% | Slippage: | -12.33%
[7 empty] | Date Allotment Released: |  | Date completed:
[7 empty] | Date Started: | 2020-03-30
Compl. Of Bahay Pag-Asa for Minors, New Corella |  | SB # 2 CY 2018 | Building |  |  | Admin | Project Cost: | 3450000 | Target Completion Date: | 2020-11-07 23:46 | Program: | 3450000 | Planned: | 15.75% | Planned: | 55.46% | Planned: | 71.45% | Planned: | 100% | Planned: | 98.48% | No. of Persons: | 20 | On-going | On-going | On-going | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | On-going
[7 empty] | Project Engineer: | Cahayag | Revised Completion Date: | 2021-01-15 23:46 | Allotment: | 3450000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 620
[7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: | 5.04% | Actual: | 42.41% | Actual: | 64.16% | Actual: | 100% | Actual: | 97.2%
[7 empty] | Duration: | 144 | No. of days extended: | 69 |  |  | Slippage: | -10.71% | Slippage: | -13.05% | Slippage: | -7.29% | Slippage: | 0% | Slippage: | -1.28%
[7 empty] | Date Allotment Released: |  | Date completed:
[7 empty] | Date Started: | 2020-06-17
Const. of Add'l. 2nd Level Multi-Purpose HalI, PGSO warehouse,Bldg., Mankilam |  | SB # 2 CY 2018 | Building |  |  | Contract | Project Cost: | 7483756.22 | Target Completion Date: | 2020-07-06 23:46 | Program: | 7483756.22 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: | 99.07% | No. of Persons: | 19 | On-going | On-going | On-going | On-going | On-going | On-going
[7 empty] | Project Engineer: | Mabanglo | Revised Completion Date: | 2020-09-13 23:46 | Allotment: | 7483756.22 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: | 40.05% | No. of Man-days: | 589
[7 empty] | Implementor: | FZI CONSTRUCTION AND PARTS SUPPLY | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: | 9.68% | Actual: | 9.68% | Actual: | 30.17%
[7 empty] | Duration: | 180 | No. of days extended: | 69 |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 9.68% | Slippage: | 9.68% | Slippage: | -9.88%
[7 empty] | Date Allotment Released: |  | Date completed:
[7 empty] | Date Started: | 2020-01-09
Jct. Highway Canatan - Doña Andrea |  | 20% DF CY 2019 | Road Rehabilitation | 4.34 | km | Admin | Project Cost: | 2000000 | Target Completion Date: | 2020-08-11 23:46 | Program: | 2000000 | Planned: | 60% | Planned: | 75% | Planned: | 75% | Planned: | 75% | Planned: | 75% | No. of Persons: |  | On-going | On-going | On-going | On-going | On-going | On-going
[7 empty] | Project Engineer: | Pilotos | Revised Completion Date: | 2020-08-11 23:46 | Allotment: | 2000000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: | 1200000 | Actual: | 60% | Actual: | 75% | Actual: | 75% | Actual: | 75% | Actual: | 75%
[7 empty] | Duration: | 57 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: | 2019-06-12 | Date completed:
[7 empty] | Date Started: | 2020-06-16
Pamacaun - Lasang Banate |  | 20% DF CY 2019 | Road Rehabilitation | 4.34 |  | Admin | Project Cost: | 2000000 | Target Completion Date: | 2020-11-10 23:46 | Program: | 2000000 | Planned: |  | Planned: | 52.32% | Planned: |  | Planned: |  | Planned: | 52.32% | No. of Persons: |  | For implementation (Waiting for the delivery of geo-grid materials. An approved request letter dated Dec. 3, 2019 for the extension of 50 days from Provincial Administrator Engr. Rabanoz is on file | Suspended due to continous rain. Waiting for the stability of swamp area. | Suspended due to continous rain. Waiting for the stability of swamp area. | Suspended due to continous rain. Waiting for the stability of swamp area. | Suspended due to continous rain. Waiting for the stability of swamp area. | Suspended Oct.5, 2020
[7 empty] | Project Engineer: | Gone | Revised Completion Date: | 2020-11-10 23:46 | Allotment: | 2000000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: | Admin | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: | 52.32% | Actual: |  | Actual: |  | Actual: | 52.32%
[7 empty] | Duration: | 84 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: | 2019-06-27 | Date completed:
[7 empty] | Date Started: | 2020-08-19
Jct. Paiton - Mibolo |  | 20% DF CY 2019 | Road Rehabilitation | 23.9 | km | Contract | Project Cost: | 6000000 | Target Completion Date: | 2020-10-05 23:46 | Program: | 6000000 | Planned: | 21.05% | Planned: | 21.05% | Planned: | 34.1% | Planned: | 34.1% | Planned: | 100% | No. of Persons: | 14 | Temporary suspended because the materials for the box culvert procurement on process wth PO # 2019061674 | Temporary suspended because the materials for the box culvert procurement on process wth PO # 2019061674 | On-going | On-going | On-going | On-going
[7 empty] | Project Engineer: | Lumapat | Revised Completion Date: | 2020-12-27 23:46 | Allotment: | 6000000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: | 56.28% | No. of Man-days: | 434
[7 empty] | Implementor: | PEO | No. of days suspended: | 83 | Disbursement: | 1263000 | Actual: | 21.05% | Actual: | 21.05% | Actual: | 31.25% | Actual: | 31.25% | Actual: | 56.28%
[7 empty] | Duration: | 218 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | -2.85% | Slippage: | -2.85% | Slippage: | 0%
[7 empty] | Date Allotment Released: | 2019-03-25 | Date completed:
[7 empty] | Date Started: | 2020-03-02
ROAD ID 077 - Tubod - Pilar |  | 20% DF CY 2019 | Road Rehabilitation | 1.55 | km | Admin | Project Cost: | 16000000 | Target Completion Date: | 2020-11-05 | Program: | 16000000 | Planned: | 62.5% | Planned: | 69.85% | Planned: | 69.85% | Planned: | 69.85% | Planned: | 100% | No. of Persons: | 18 | On-going | On-going | On-going |  |  | On-going
[7 empty] | Project Engineer: | Agang | Revised Completion Date: |  | Allotment: | 16000000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 396
[7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: | 4046971.2 | Actual: | 58.23% | Actual: | 71.98% | Actual: | 71.98% | Actual: | 71.98% | Actual: | 78.08%
[7 empty] | Duration: | 323 | No. of days extended: |  |  |  | Slippage: | -4.27% | Slippage: | 2.13% | Slippage: | 2.13% | Slippage: | 2.13% | Slippage: | -21.92%
[7 empty] | Date Allotment Released: | 2019-11-26 | Date completed:
[7 empty] | Date Started: | 2019-12-18
New Katipunan - Pantaron |  | 20% DF CY 2019 | Road Rehabilitation | 1.96 | km | Admin | Project Cost: | 395000 | Target Completion Date: | 2020-02-25 | Program: | 395000 | Planned: | 60% | Planned: | 60% | Planned: | 60% | Planned: | 60% | Planned: | 60% | No. of Persons: | 4 | On-going | On-going | On-going | On-going | On-going | On-going
[7 empty] | Project Engineer: | Gamad/Clar | Revised Completion Date: |  | Allotment: | 395000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 24
[7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: | 60% | Actual: | 60% | Actual: | 60% | Actual: | 60% | Actual: | 60%
[7 empty] | Duration: | 60 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: | 2019-01-03 | Date completed:
[7 empty] | Date Started: | 2019-12-27
Bdry. Tagum - Crossing Kinamayan Sto. Tomas |  | 20% DF CY 2019 | Road Rehabilitation | 0.75 | km | Admin | Project Cost: | 3700000 | Target Completion Date: | 2020-04-25 | Program: | 3700000 | Planned: | 100% | Planned: | 100% | Planned: | 100% | Planned: | 100% | Planned: | 100% | No. of Persons: | 15 | On-going | On-going | On-going | On-going | On-going | On-going
[7 empty] | Project Engineer: | Gamad/Clar | Revised Completion Date: | 2020-08-23 | Allotment: | 3700000 | Revised: | 15.43% | Revised: | 15.43% | Revised: | 15.43% | Revised: | 15.43% | Revised: | 15.43% | No. of Man-days: | 225
[7 empty] | Implementor: |  | No. of days suspended: | 20 | Disbursement: |  | Actual: | 16.37% | Actual: | 16.37% | Actual: | 16.37% | Actual: | 16.37% | Actual: | 16.37%
[7 empty] | Duration: | 120 | No. of days extended: | 100 |  |  | Slippage: | 0.94% | Slippage: | 0.94% | Slippage: | 0.94% | Slippage: | 0.94% | Slippage: | 0.94%
[7 empty] | Date Allotment Released: | 2019-01-03 | Date completed:
[7 empty] | Date Started: | 2019-12-27
Impv't. of Potable Water System, Consolacion, Panabo City |  | 20% DF CY 2019 | Water System |  |  |  | Project Cost: | 500000 | Target Completion Date: | 2020-06-06 | Program: | 500000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: | 100% | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. |  |  | Subject for LD, no activity on site/ Issued 2nd warning letter
[7 empty] | Project Engineer: | Abayon | Revised Completion Date: | September 1, 2020 | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: | 56.5% | No. of Man-days:
[7 empty] | Implementor: | RLHV | No. of days suspended: | 86 | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual: | 1.2%
[7 empty] | Duration: | 60 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | -55.3%
[7 empty] | Date Allotment Released: |  | Date completed:
[7 empty] | Date Started: | 2020-04-07
Const. of IP Women's Multi-Purpose Bldg., Cabidiangan, Sto. Niño, Talaingod |  | 20% DF CY 2019 | Building |  |  | Admin | Project Cost: | 2000000 | Target Completion Date: | 2020-12-07 | Program: | 2000000 | Planned: |  | Planned: |  | Planned: | 14.65% | Planned: | 14.65% | Planned: | 100% | No. of Persons: | 10 | Awarded to Alpebel Builders | On-going | On-going | On-going | On-going | Slippage is due to intermittent rain on site
[7 empty] | Project Engineer: | Torrecampo | Revised Completion Date: | 2021-01-11 | Allotment: | 2000000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: | 89.76% | No. of Man-days: | 300
[7 empty] | Implementor: | ALPEBEL BUILDERS & SUPPLY CORP. | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: | 14.65% | Actual: | 14.65% | Actual: | 47.74%
[7 empty] | Duration: | 105 | No. of days extended: | 35 |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | -42.02%
[7 empty] | Date Allotment Released: | 2019-05-15 | Date completed:
[7 empty] | Date Started: | 2020-08-24
Const. of DDN Hospital Carmen Zone Annex Bldg. Phase 2, |  | 20% DF CY 2019 | Building |  | sq.m | Contract | Project Cost: | 3620000 | Target Completion Date: | 2020-10-24 | Program: | 3620000 | Planned: |  | Planned: |  | Planned: | 10.51% | Planned: | 10.15% | Planned: | 10.15% | No. of Persons: | 15 | On-going | On-going | On-going | On-going | On-going | On-going
[7 empty] | Project Engineer: | Azotes | Revised Completion Date: |  | Allotment: | 3620000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 330
[7 empty] | Implementor: | Digos Constrak Corp/ | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: | 8.12% | Actual: | 8.12% | Actual: | 8.12%
[7 empty] | Duration: | 92 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | -2.39% | Slippage: | -2.03% | Slippage: | -2.03%
[7 empty] | Date Allotment Released: | 2019-06-28 | Date completed:
[7 empty] | Date Started: | 2020-07-24
Construction of Bahay Silangan for Reformation of Drug Personalities within The Military Camp/barracks, Brgy. Mankilam, Tagum City |  | 20% DF CY 2019 | Building | 126 | sq.m | Contract | Project Cost: | 5000000 | Target Completion Date: | 2021-04-13 | Program: | 5000000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: | 34.66% | No. of Persons: | 16 | Abstract #0620202232 - Post Qualification on process (ZULAR-A) | Abstract #0620202232 - Post Qualification on process (ZULAR-A) | Abstract #0620202232 - Post Qualification on process (ZULAR-A) | Abstract #0620202232 - Post Qualification on process (ZULAR-A) | Abstract #0620202232 - Post Qualification on process (ZULAR-A) | On-going
[7 empty] | Project Engineer: | Torrecampo | Revised Completion Date: |  | Allotment: | 5000000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 330
[7 empty] | Implementor: | Zular-AZ Const. and Suppy | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual: | 53.71%
[7 empty] | Duration: | 190 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 19.05%
[7 empty] | Date Allotment Released: |  | Date completed:
[7 empty] | Date Started: | 2020-10-05
Rehab. Of Brgy. Health Center, Apokon, Tagum City |  | 20% DF CY 2019 (STIMULUS) | Building |  |  |  | Project Cost: | 500000 | Target Completion Date: | 2020-12-07 23:46 | Program: | 500000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: | 100% | No. of Persons: | 8 | For implementation (The brgy. council agreed not to pursue with the project if it will not be completed and needs additional funds) | For implementation (The brgy. council agreed not to pursue with the project if it will not be completed and needs additional funds) | For implementation (The brgy. council agreed not to pursue with the project if it will not be completed and needs additional funds) | For implementation (The brgy. council agreed not to pursue with the project if it will not be completed and needs additional funds) | For implementation (The brgy. council agreed not to pursue with the project if it will not be completed and needs additional funds) | On-going (Slippage due to pending of installation of roofing works. (Job Order)
[7 empty] | Project Engineer: | Torrecampo | Revised Completion Date: | 2021-01-16 23:46 | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: | 76.13% | No. of Man-days: | 120
[7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual: | 75.11%
[7 empty] | Duration: | 50 | No. of days extended: | 40 |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | -1.02%
[7 empty] | Date Allotment Released: | 2019-03-25 | Date completed:
[7 empty] | Date Started: | 2020-10-19
Rehab. Of Evacuation Center, Casig-ang, Sto. Tomas |  | 20% DF CY 2019 (STIMULUS | Building |  |  | Contract | Project Cost: | 500000 | Target Completion Date: | 2021-01-16 | Program: | 500000 | Planned: |  | Planned: |  | Planned: |  | Planned: | 12.3% | Planned: | 12.3% | No. of Persons: | 5 | On-going | PR #20063670 | Revision of POW on-going | On-going | On-going | On-going
[7 empty] | Project Engineer: | Estorco | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 110
[7 empty] | Implementor: | JJR Const. & Supply | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: | 13.6% | Actual: | 13.6%
[7 empty] | Duration: | 100 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 1.3% | Slippage: | 1.3%
[7 empty] | Date Allotment Released: |  | Date completed:
[7 empty] | Date Started: | 2020-10-08
Installation of Pipelines, Libertad, IGCS |  | 20% DF CY 2019 (STIMULUS | Pipelines |  |  |  | Project Cost: | 500000 | Target Completion Date: | 2020-09-17 | Program: | 500000 | Planned: |  | Planned: |  | Planned: | 100% | Planned: | 100% | Planned: | 100% | No. of Persons: | 4 | For implementation | On-going | On-going | On-going | On-going | On-going
[7 empty] | Project Engineer: | Porras | Revised Completion Date: | 2020-11-01 | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: | 42.1% | Revised: | 56.4% | Revised: | 56.4% | No. of Man-days: | 88
[7 empty] | Implementor: | Admin | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: | 56.1% | Actual: | 62.4% | Actual: | 62.4%
[7 empty] | Duration: | 25 | No. of days extended: | 45 |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 14% | Slippage: | 6% | Slippage: | 6%
[7 empty] | Date Allotment Released: | 2019-03-25 | Date completed:
[7 empty] | Date Started: | 2020-08-24
Rural Electrification at Sitio Bundok San Roque, Brgy. New Cortez, New Corella |  | 20% DF CY 2019 | Electrification |  |  |  | Project Cost: | 1000000 | Target Completion Date: | 2021-01-05 23:46 | Program: | 1000000 | Planned: | 43% | Planned: | 43% | Planned: | 43% | Planned: | 43% | Planned: | 98% | No. of Persons: |  | On-going | On-going | On-going | On-going | On-going | On-going
[7 empty] | Project Engineer: | P.Bueno | Revised Completion Date: | 2021-01-05 23:46 | Allotment: | 1000000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: | Tagum Builders | No. of days suspended: |  | Disbursement: |  | Actual: | 43% | Actual: | 43% | Actual: | 43% | Actual: | 43% | Actual: | 98%
[7 empty] | Duration: | 43 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
[7 empty] | Date Started: | 2020-11-24
Rehab. Of Multi-Purpose Hall, Talomo, Sto. Tomas |  | 20% DF CY 2019 (STIMULUS | Building |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Fund transfer to LGU - 6/26/2019 with check no. 2575130 and OR no. 0557456 For implementation | Fund transfer to LGU - 6/26/2019 with check no. 2575130 and OR no. 0557456 For implementation | On-going (Implemented by MLGU, since transfer of fund ) | On-going (Implemented by MLGU, since transfer of fund ) | On-going (Implemented by MLGU, since transfer of fund ) | On-going (Implemented by MLGU, since transfer of fund )
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Provincial Livestock & Poultry Multiplier Farm Road Network Construction, Sitio Salawao, Sto. Niño, Talaingod |  | SB NO. 4 CY 2019 | Conc. Pavement |  | sq.m | Admin | Project Cost: | 5500000 | Target Completion Date: | 2020-07-13 23:46 | Program: | 5500000 | Planned: | 30.06% | Planned: | 56.09% | Planned: | 56.09% | Planned: | 56.09% | Planned: | 100% | No. of Persons: | 28 | Plan On-going | Plan On-going | Plan On-going | Completed (Implemented by MLGU, since transfer of fund ) | Completed (Implemented by MLGU, since transfer of fund ) | On-going
[7 empty] | Project Engineer: | Pasiona/Juan | Revised Completion Date: | 2021-01-29 23:46 | Allotment: | 5500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: | 87.29% | No. of Man-days: | 420
[7 empty] | Implementor: | PEO | No. of days suspended: | 28 | Disbursement: | 4704199.85 | Actual: | 30.06% | Actual: | 45.48% | Actual: | 45.48% | Actual: | 45.48% | Actual: | 81.94%
[7 empty] | Duration: | 120 | No. of days extended: | 172 |  |  | Slippage: | 0% | Slippage: | -10.61% | Slippage: | -10.61% | Slippage: | -10.61% | Slippage: | -5.35%
[7 empty] | Date Allotment Released: | CY 2019 | Date completed:
[7 empty] | Date Started: | 2020-03-16
Construction of Children's Playground with Amenities, Poblacion, New Corella |  | SB No. 4 CY 2019 (STIMULUS) | Building |  | sq.m | Admin | Project Cost: | 2500000 | Target Completion Date: | 2020-03-03 23:59 | Program: | 2500000 | Planned: | 57.9% | Planned: | 64.73% | Planned: | 64.73% | Planned: | 64.73% | Planned: | 64.73% | No. of Persons: | 10 | On-going (Suspended effective April 5, 2020 due to COVID; resumption order dated May 4, 2020) | On-going (Suspended effective April 5, 2020 due to COVID; resumption order dated May 4, 2020) | On-going (Suspended effective April 5, 2020 due to COVID; resumption order dated May 4, 2020) |  |  | On-going
[7 empty] | Project Engineer: | Mayang | Revised Completion Date: | 2020-04-30 23:59 | Allotment: | 2500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 150
[7 empty] | Implementor: | PEO | No. of days suspended: | 28 | Disbursement: | 1029250 | Actual: | 57.9% | Actual: | 64.73% | Actual: | 64.73% | Actual: | 64.73% | Actual: | 64.73%
[7 empty] | Duration: | 100 | No. of days extended: | 30 |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: | 2019-12-06 | Date completed:
[7 empty] | Date Started: | 2019-11-25
Const. Of Multi-Purpose Hall, Buenavista, Panabo City |  | SB # 4 CY 2019 (STIMULUS) | Building |  |  | Contract | Project Cost: | 500000 | Target Completion Date: | 2021-02-03 | Program: | 500000 | Planned: |  | Planned: |  | Planned: | 5% | Planned: | 28.54% | Planned: | 28.54% | No. of Persons: | 7 | Purchase Order # 2020031248- DIGOS CONSTRAK | For implementation (DIGOS CONSTRAK) | On-going | On-going | On-going | On-going
[7 empty] | Project Engineer: | Andoy | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 154
[7 empty] | Implementor: | Digos Constrak Corp/ | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: | 5% | Actual: | 32.17% | Actual: | 32.17%
[7 empty] | Duration: | 160 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 3.63% | Slippage: | 3.63%
[7 empty] | Date Allotment Released: | 2019-10-18 | Date completed:
[7 empty] | Date Started: | 2020-08-27
Rehab. Of Multi-Purpose Hall, Kasilak, Panabo City |  | SB # 4 CY 2019 (STIMULUS) | Building |  |  | Contract | Project Cost: | 650000 | Target Completion Date: | 2020-11-11 | Program: | 650000 | Planned: |  | Planned: |  | Planned: | 56.3% | Planned: | 60.18% | Planned: | 60.18% | No. of Persons: | 4 | On-going | On-going | On-going | On-going | On-going | On-going
[7 empty] | Project Engineer: | Estorco | Revised Completion Date: |  | Allotment: | 650000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 88
[7 empty] | Implementor: | JJR Const. & Supply | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: | 45.3% | Actual: | 58.4% | Actual: | 58.4%
[7 empty] | Duration: | 120 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | -11% | Slippage: | -1.78% | Slippage: | -1.78%
[7 empty] | Date Allotment Released: |  | Date completed:
[7 empty] | Date Started: | 2020-07-14
Proposed Road Opening of Tawinian-Tapayanon Road Section |  | SB NO. 4 CY 2019 | Road |  | km | Admin | Project Cost: | 10000000 | Target Completion Date: | 2020-10-01 23:46 | Program: | 10000000 | Planned: | 34.2% | Planned: | 41.6% | Planned: | 41.6% | Planned: | 41.6% | Planned: | 100% | No. of Persons: | 8 | On-going (Suspended last April 5, 2020 due to COVID; resumption order dated May 4, 2020); Equipment Rental 1 unit Backhoe (Bidding July 16, 2020) | On-going (Suspended last April 5, 2020 due to COVID; resumption order dated May 4, 2020); Equipment Rental 1 unit Backhoe (Bidding July 16, 2020) | On-going (Suspended last April 5, 2020 due to COVID; resumption order dated May 4, 2020); Equipment Rental 1 unit Backhoe (Bidding July 16, 2020) |  |  | On-going
[7 empty] | Project Engineer: | Garcia | Revised Completion Date: | 2020-10-29 23:46 | Allotment: | 10000000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: | 65.52% | No. of Man-days: | 138
[7 empty] | Implementor: | PEO | No. of days suspended: | 28 | Disbursement: |  | Actual: | 34.2% | Actual: | 41.6% | Actual: | 41.6% | Actual: | 41.6% | Actual: | 70.86%
[7 empty] | Duration: | 319 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 5.34%
[7 empty] | Date Allotment Released: | 2019-11-15 | Date completed:
[7 empty] | Date Started: | 2019-11-18
Improvement of Km. 9 Sagayen-Sawata Provincial Road, San Isidro, Ph. II |  | SB NO. 4 CY 2019 | Road |  | ln.m | Admin | Project Cost: | 4591029 | Target Completion Date: | 2020-03-27 | Program: | 4591029 | Planned: | 45% | Planned: | 45% | Planned: | 45% | Planned: | 45% | Planned: | 45% | No. of Persons: | 6 | Suspended | Suspended | Suspended | Suspended | Suspended | Suspended
[7 empty] | Project Engineer: | Limpo | Revised Completion Date: |  | Allotment: | 4591029 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 138
[7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: | 1609155.6645 | Actual: | 35.05% | Actual: | 35.05% | Actual: | 35.05% | Actual: | 35.05% | Actual: | 35.05%
[7 empty] | Duration: | 200 | No. of days extended: |  |  |  | Slippage: | -9.95% | Slippage: | -9.95% | Slippage: | -9.95% | Slippage: | -9.95% | Slippage: | -9.95%
[7 empty] | Date Allotment Released: | 2019-12-12 | Date completed:
[7 empty] | Date Started: | 2019-09-09
Construction of 2 Classroom Building Datu Jose Libayao NHS Ext, Natulian, Palma Gil, Talaingod |  | SEF-AB CY 2019 | Building |  | km |  | Project Cost: | 2000000 | Target Completion Date: |  | Program: | 2000000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: | 20% | No. of Persons: |  | PO#2020061983 - FL2 LUMBER & CONST. SUPPLY; PO #2020062164 - jkle enterprises | PO#2020061983 - FL2 LUMBER & CONST. SUPPLY; PO #2020062164 - jkle enterprises | PO#2020061983 - FL2 LUMBER & CONST. SUPPLY; PO #2020062164 - jkle enterprises |  |  | On-going
[7 empty] | Project Engineer: | Ambrosio | Revised Completion Date: |  | Allotment: | 2000000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual: | 20%
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
[7 empty] | Date Started: | 2020-10-01
Const. of 1 Classroom @ Tawinian E/S, Gupitan, kapalong |  | SEF-SB No. 2 CY 2019 | Building |  | sq.m |  | Project Cost: | 500000 | Target Completion Date: | 2020-12-14 23:59 | Program: | 500000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: | 80% | No. of Persons: |  | Opening of Shopping on June 25, 2020 | Opening of Shopping on June 25, 2020 | Opening of Shopping on June 25, 2020 | Opening of Shopping on June 25, 2020 | Opening of Shopping on June 25, 2020 | On-going
[7 empty] | Project Engineer: | Mabanglo | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: | Alpebel Builders and Supply Corporation | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual: | 80%
[7 empty] | Duration: | 75 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
[7 empty] | Date Started: | 2020-10-01
Const. of 1 Classroom @ Moling E/S, Gupitan, kapalong |  | SEF-SB No. 2 CY 2019 | Building |  | sq.m |  | Project Cost: | 500000 | Target Completion Date: | 2020-12-14 23:59 | Program: | 500000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: | 90% | No. of Persons: |  | Opening of Shopping on June 25, 2020 | Opening of Shopping on June 25, 2020 | Opening of Shopping on June 25, 2020 | Opening of Shopping on June 25, 2020 | Opening of Shopping on June 25, 2020 | On-going
[7 empty] | Project Engineer: | Mabanglo | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: | Alpebel Builders and Supply Corporation | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual: | 90%
[7 empty] | Duration: | 75 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
[7 empty] | Date Started: | 2020-10-01
Const. of 1 Classroom @ Kawayan ES, Gupitan, Kapalong |  | SEF-SB No. 2 CY 2019 | Building |  | sq.m |  | Project Cost: | 500000 | Target Completion Date: | 2020-12-14 23:59 | Program: | 500000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: | 50% | No. of Persons: |  | Opening of Shopping on June 25, 2020 | Opening of Shopping on June 25, 2020 | Opening of Shopping on June 25, 2020 | Opening of Shopping on June 25, 2020 | Opening of Shopping on June 25, 2020 | On-going
[7 empty] | Project Engineer: | Mabanglo | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: | Alpebel Builders and Supply Corporation | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual: | 50%
[7 empty] | Duration: | 75 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
[7 empty] | Date Started: | 2020-10-01
Const. of 1 Classroom @ Matol ES, Gupitan, Kapalong |  | SEF-SB No. 2 CY 2019 | Building |  | sq.m |  | Project Cost: | 500000 | Target Completion Date: | 2020-12-14 23:59 | Program: | 500000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: | 90% | No. of Persons: |  | Opening of Shopping on June 25, 2020 | Opening of Shopping on June 25, 2020 | Opening of Shopping on June 25, 2020 | Opening of Shopping on June 25, 2020 | Opening of Shopping on June 25, 2020 | On-going
[7 empty] | Project Engineer: | Mabanglo | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: | Alpebel Builders and Supply Corporation | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual: | 90%
[7 empty] | Duration: | 75 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
[7 empty] | Date Started: | 2020-10-01
Const. of 1 Classroom @ Hermogina Salibay ES, Capungagan, Kapalong |  | SEF-SB No. 2 CY 2019 | Building |  | sq.m |  | Project Cost: | 500000 | Target Completion Date: | 2020-12-14 23:59 | Program: | 500000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: | 50% | No. of Persons: |  | Opening of Shopping on June 25, 2020 | Opening of Shopping on June 25, 2020 | Opening of Shopping on June 25, 2020 | Opening of Shopping on June 25, 2020 | Opening of Shopping on June 25, 2020 | On-going
[7 empty] | Project Engineer: | Mabanglo | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: | Alpebel Builders and Supply Corporation | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual: | 50%
[7 empty] | Duration: | 75 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
[7 empty] | Date Started: | 2020-10-01
Const. of 1 Classroom @ Dulyan ES, Palma Gil, Talaingod |  | SEF-SB No. 2 CY 2019 | Building |  | sq.m |  | Project Cost: | 500000 | Target Completion Date: | 2020-12-14 23:59 | Program: | 500000 | Planned: |  | Planned: |  | Planned: |  | Planned: | 100% | Planned: | 75% | No. of Persons: |  | Opening of Shopping on June 25, 2020 | Opening of Shopping on June 25, 2020 | Opening of Shopping on June 25, 2020 | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | On-going
[7 empty] | Project Engineer: | Mabanglo | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: | Alpebel Builders and Supply Corporation | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: | 100% | Actual: | 75%
[7 empty] | Duration: | 75 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
[7 empty] | Date Started: | 2020-10-01
Desilting of Limbaan Creek, New Corella |  | 5% CALAMITY FUND CY 2019 | creeks and canals deislted |  | ln.m | Admin | Project Cost: | 2000000 | Target Completion Date: | 2019-12-02 | Program: | 2000000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Suspended | Suspended | Suspended | Suspended | Suspended | Suspended
[7 empty] | Project Engineer: | Pilotos | Revised Completion Date: | 2019-12-02 | Allotment: | 2000000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: | 257 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
[7 empty] | Date Started: | 2019-03-20
Impv't. of Jct. New Boholano - New Loon Cross Drainage |  | 5% CALAMITY FUND CY 2019 | Drainage |  | km | Admin | Project Cost: | 2000000 | Target Completion Date: | 2020-02-16 | Program: | 2000000 | Planned: | 42.27% | Planned: | 42.27% | Planned: | 42.27% | Planned: | 42.27% | Planned: | 70% | No. of Persons: |  | Suspended due to availability of equipment | Suspended due to availability of equipment | Suspended due to availability of equipment | Suspended due to availability of equipment | Suspended due to availability of equipment | On-going
[7 empty] | Project Engineer: | Pilotos | Revised Completion Date: | 2020-02-16 | Allotment: | 2000000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: | 31.7% | Actual: | 31.7% | Actual: | 31.7% | Actual: | 31.7% | Actual: | 70%
[7 empty] | Duration: | 90 | No. of days extended: |  |  |  | Slippage: | -10.57% | Slippage: | -10.57% | Slippage: | -10.57% | Slippage: | -10.57% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
[7 empty] | Date Started: | 2019-11-18
Rehabilitation of Pamacaun-Lasang-Banate Provincial Road |  | SB NO. 3 CY 2019 (5% CALAMITY FUND) | Road |  |  | Admin | Project Cost: | 1500000 | Target Completion Date: | 2020-11-10 23:46 | Program: | 1500000 | Planned: |  | Planned: |  | Planned: | 41.21% | Planned: | 41.21% | Planned: | 41.21% | No. of Persons: |  | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | On-going (Suspended Oct.5, 2020)
[7 empty] | Project Engineer: | Gone | Revised Completion Date: |  | Allotment: | 1500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: | 17.82% | Actual: | 52.32% | Actual: | 52.32% | Actual: | 52.32%
[7 empty] | Duration: | 100 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 17.82% | Slippage: | 11.11% | Slippage: | 11.11% | Slippage: | 11.11%
[7 empty] | Date Allotment Released: |  | Date completed:
[7 empty] | Date Started: | 2020-08-03
Rehabilitation of Del Pilar Jct. Silangan |  | SB NO. 3 CY 2019 (5% CALAMITY FUND) | Road |  | km | Admin | Project Cost: | 1500000 | Target Completion Date: | 2020-03-27 23:46 | Program: | 1500000 | Planned: | 81.11% | Planned: | 81.11% | Planned: | 81.11% | Planned: | 81.11% | Planned: | 100% | No. of Persons: | 4 | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | On-going (Resumption date Dec. 7, 2020)
[7 empty] | Project Engineer: | Gone | Revised Completion Date: | 2021-01-15 23:46 | Allotment: | 1500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: | 92.61% | No. of Man-days: | 40
[7 empty] | Implementor: | PEO | No. of days suspended: | 243 | Disbursement: |  | Actual: | 81.11% | Actual: | 81.11% | Actual: | 81.11% | Actual: | 81.11% | Actual: | 90.42%
[7 empty] | Duration: | 40 | No. of days extended: | 51 |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | -2.19%
[7 empty] | Date Allotment Released: | 2019-07-26 | Date completed:
[7 empty] | Date Started: | 2020-02-17
Rehab. Of Sonlon - Camansa FMR Asuncion, Davao del Norte |  | PRDP CY 2015 | Road Concreting | 10.23 | km | Contract | Project Cost: | 215125015.81 | Target Completion Date: | 2021-01-01 | Program: | 215125015.81 | Planned: | 39.51% | Planned: | 40.75% | Planned: | 40.75% | Planned: |  | Planned: | 49.13% | No. of Persons: |  | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. |  |  | On-going
[7 empty] | Project Engineer: | Fabiala | Revised Completion Date: | 2021-03-05 | Allotment: | 215125015.81 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: | Three w/Builders, Inc/Davao Rock Mixer Enterprises (JV) | No. of days suspended: | 56 | Disbursement: | 40523099.23 | Actual: | 31.6% | Actual: | 33.45% | Actual: | 33.45% | Actual: |  | Actual: | 42.68%
[7 empty] | Duration: | 584 | No. of days extended: | 7 |  |  | Slippage: | -7.91% | Slippage: | -7.306% | Slippage: | -7.306% | Slippage: | 0% | Slippage: | -6.452%
[7 empty] | Date Allotment Released: | 2018-09-18 | Date completed:
[7 empty] | Date Started: | 2019-05-28
Road Upgrading of Jct Highway - Sto Nino - La Paz - San Vicenter Provincial Road, Carmen |  | CMGP CY 2019 | Road |  | km | Contract | Project Cost: | 80481331.34 | Target Completion Date: | 2020-06-22 | Program: | 80481331.34 | Planned: | 97.44% | Planned: | 98.83% | Planned: | 98.83% | Planned: | 100% | Planned: | 100% | No. of Persons: | 10 | On-going | On-going | On-going | On-going | On-going | On-going | 94.91
[7 empty] | Project Engineer: | Fernandez | Revised Completion Date: | Oct. 19, 2020 | Allotment: | 80481331.34 | Revised: |  | Revised: |  | Revised: |  | Revised: | 99.26% | Revised: | 99.26% | No. of Man-days: | 250
[7 empty] | Implementor: | Tagum Builders | No. of days suspended: | 37 | Disbursement: | 78066891.3998 | Actual: | 97.54% | Actual: | 98.98% | Actual: | 98.98% | Actual: | 99.24% | Actual: | 99.24%
[7 empty] | Duration: | 259 | No. of days extended: | 82 |  |  | Slippage: | 0.1% | Slippage: | 0.15% | Slippage: | 0.15% | Slippage: | -0.024% | Slippage: | -0.024%
[7 empty] | Date Allotment Released: | CY 2019 | Date completed:
[7 empty] | Date Started: | 2019-10-07
Rehabilitation of Dasing to Monte Carlo FMR, Del Pilar, New Corella |  | LGSF CY 2019 | Concreting |  |  | Contract | Project Cost: | 40000000 | Target Completion Date: | 2021-04-04 23:59 | Program: | 40000000 | Planned: | 8.35% | Planned: | 8.35% | Planned: | 8.35% | Planned: | 8.35% | Planned: | 66.49% | No. of Persons: | 10 | On-going | On-going | On-going | On-going | On-going | On-going
[7 empty] | Project Engineer: | Madrigal | Revised Completion Date: | 2021-04-04 23:59 | Allotment: | 40000000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 250
[7 empty] | Implementor: | Rely Const. & Supply | No. of days suspended: |  | Disbursement: |  | Actual: | 8.35% | Actual: | 8.35% | Actual: | 8.35% | Actual: | 8.35% | Actual: | 71.31%
[7 empty] | Duration: | 285 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 4.82%
[7 empty] | Date Allotment Released: |  | Date completed:
[7 empty] | Date Started: | 2020-06-24
Concreting of Visayan Village - Purok exodus - Purok Rafael, Brgy. Magugpo South, Tagum City |  | LGSF CY 2019 | Concreting |  |  | Contract | Project Cost: | 40000000 | Target Completion Date: | 2021-05-18 23:59 | Program: | 40000000 | Planned: | 14.69% | Planned: | 14.69% | Planned: | 42.57% | Planned: | 42.57% | Planned: | 59.27% | No. of Persons: | 32 | On-going | On-going | On-going | On-going | On-going | On-going
[7 empty] | Project Engineer: | Avila | Revised Completion Date: | 2021-05-18 23:59 | Allotment: | 40000000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 960
[7 empty] | Implementor: | Legacy Const. Corp. | No. of days suspended: |  | Disbursement: |  | Actual: | 26.73% | Actual: | 26.73% | Actual: | 48.07% | Actual: | 48.07% | Actual: | 70.21%
[7 empty] | Duration: | 330 | No. of days extended: |  |  |  | Slippage: | 12.04% | Slippage: | 12.04% | Slippage: | 5.5% | Slippage: | 5.5% | Slippage: | 10.93%
[7 empty] | Date Allotment Released: | CY 2019 | Date completed:
[7 empty] | Date Started: | 2020-06-23
Road Upgrading of Farm To Market Road at Brgy. Buenavista |  | LGSF CY 2019 | Road |  | km | Contract | Project Cost: | 40000000 | Target Completion Date: | 2021-02-04 | Program: | 40000000 | Planned: | 6.3% | Planned: | 6.3% | Planned: | 6.3% | Planned: | 41.42% | Planned: |  | No. of Persons: | 60 | On-going | On-going | On-going |  |  | On-going
[7 empty] | Project Engineer: | Nasol | Revised Completion Date: |  | Allotment: | 40000000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 1320
[7 empty] | Implementor: | Alpha Omega | No. of days suspended: |  | Disbursement: |  | Actual: | 9.55% | Actual: | 9.55% | Actual: | 9.55% | Actual: | 34.82% | Actual:
[7 empty] | Duration: | 220 | No. of days extended: |  |  |  | Slippage: | 3.25% | Slippage: | 3.25% | Slippage: | 3.25% | Slippage: | -6.6% | Slippage:
[7 empty] | Date Allotment Released: | CY 2019 | Date completed:
[7 empty] | Date Started: | 2020-06-29
Road Upgrading of New Katipunan-Pantaron Provincial Road |  | LGSF CY 2019 | Road |  | km | Contract | Project Cost: | 30000000 | Target Completion Date: | 2021-01-14 | Program: | 30000000 | Planned: | 1.75% | Planned: | 1.75% | Planned: | 1.75% | Planned: | 31.04% | Planned: |  | No. of Persons: | 20 | On-going | On-going | On-going |  |  | On-going
[7 empty] | Project Engineer: | Sanchez | Revised Completion Date: | 2021-02-23 | Allotment: | 30000000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 440
[7 empty] | Implementor: | FFJJ | No. of days suspended: | 40 | Disbursement: |  | Actual: | 1.65% | Actual: | 1.65% | Actual: | 1.65% | Actual: | 31.13% | Actual:
[7 empty] | Duration: | 190 | No. of days extended: |  |  |  | Slippage: | -0.1% | Slippage: | -0.1% | Slippage: | -0.1% | Slippage: | 0.085% | Slippage:
[7 empty] | Date Allotment Released: |  | Date completed:
[7 empty] | Date Started: | 2020-07-08
ROAD ID 001 - Jct. Highway Magatos - New Bantayan |  | GENERAL FUND CY 2020 | Maintenance | 7.1 | km | CBRMC | Project Cost: | 230700 | Target Completion Date: |  | Program: | 230700 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: | 25% | No. of Persons: |  | Purchase Request # 19125305 (On process) | Purchase Request # 19125305 (On process) | Purchase Request # 19125305 (On process) | Purchase Request # 19125305 (On process) | Purchase Request # 19125305 (On process) | On-going
[7 empty] | Project Engineer: | Fabian | Revised Completion Date: |  | Allotment: | 230700 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: | CALAFA | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual: | 25%
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
ROAD ID 040 - Datu Balong - Pinamuno |  | 20% Development Fund CY 2020 | Road Rehabilitaion | 2.74 | km | Admin | Project Cost: | 822000 | Target Completion Date: | 2021-02-03 23:59 | Program: | 822000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: | 30.04% | No. of Persons: | 13 | POW on process | POW on process | POW on process | POW on process | POW on process | On-going
[7 empty] | Project Engineer: | Crucio | Revised Completion Date: |  | Allotment: | 822000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 374
[7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual: | 30.04%
[7 empty] | Duration: | 65 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
[7 empty] | Date Started: | 2020-12-01
ROAD ID 069 - Mesaoy - Jct. Mahayahay |  | 20% Development Fund CY 2020 | Road Rehabilitaion | 4.6 | km | Admin | Project Cost: | 1380000 | Target Completion Date: | 2021-02-15 23:59 | Program: | 1380000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: | 72.16% | No. of Persons: |  | POW on process | POW on process | POW on process | POW on process | POW on process | On--going
[7 empty] | Project Engineer: | Pilotos | Revised Completion Date: |  | Allotment: | 1380000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual: | 72.16%
[7 empty] | Duration: | 60 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
[7 empty] | Date Started: | 2020-12-18
ROAD ID 073 - Cebulano - Mangalcal |  | GENERAL FUND CY 2020 | Maintenance | 4.17 | km | MBA | Project Cost: | 134672.7 | Target Completion Date: | 2020-12-31 23:59 | Program: | 134672.7 | Planned: | 50% | Planned: | 50% | Planned: | 50% | Planned: | 81% | Planned: | 81% | No. of Persons: | 9 | On-going | On-going | On-going | On-going | On-going | On-going
[7 empty] | Project Engineer: | Gamad/Clar | Revised Completion Date: |  | Allotment: | 134672.7 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 45
[7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: | 51% | Actual: | 51% | Actual: | 51% | Actual: | 83.6% | Actual: | 83.6%
[7 empty] | Duration: | 365 | No. of days extended: |  |  |  | Slippage: | 1% | Slippage: | 1% | Slippage: | 1% | Slippage: | 2.6% | Slippage: | 2.6%
[7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
[7 empty] | Date Started: | 2020-01-02
ROAD ID 082 - Jct. Highway Carmen - Mangalcal - Tubod |  | GENERAL FUND CY 2020 | Maintenance | 11.34 | km | CBRMC | Project Cost: | 259594.46 | Target Completion Date: | 2021-02-04 | Program: | 259594.46 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: | 42.1% | No. of Persons: | 3 | PO #2020031403 - Awarded to TUBOD CENTRO LOWER IRRIGATORS ASS'T (TUCLIA) | PO #2020031403 - Awarded to TUBOD CENTRO LOWER IRRIGATORS ASS'T (TUCLIA) | PO #2020031403 - Awarded to TUBOD CENTRO LOWER IRRIGATORS ASS'T (TUCLIA) | For implementation (Winning Bidder Tubod Central Lower Irrigator Association) | For implementation (Winning Bidder Tubod Central Lower Irrigator Association) | On-going
[7 empty] | Project Engineer: | Maligro | Revised Completion Date: |  | Allotment: | 259594.46 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 18
[7 empty] | Implementor: | Tubod Central Lower Irrigator Association | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual: | 41.66%
[7 empty] | Duration: | 6 months | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | -0.44%
[7 empty] | Date Allotment Released: |  | Date completed:
[7 empty] | Date Started: | 2020-08-04
ROAD ID 086 - Ising - Sadpodon - Taba - Dila -Dila |  | GENERAL FUND CY 2020 | Maintenance | 5.68 | km | CBRMC | Project Cost: | 135230.61 | Target Completion Date: | 2/24/2021 | Program: | 135230.61 | Planned: | 50% | Planned: | 50% | Planned: | 50% | Planned: | 50% | Planned: | 42.1% | No. of Persons: | 4 | PO #2020031408 - Awarded to TABA COCONUT FARMERS ORGANIZATION | PO #2020031408 - Awarded to TABA COCONUT FARMERS ORGANIZATION | PO #2020031408 - Awarded to TABA COCONUT FARMERS ORGANIZATION | For implementation (Winning Bidder Taba Coconut Farmers Association) | For implementation (Winning Bidder Taba Coconut Farmers Association) | On-going
[7 empty] | Project Engineer: | Maligro | Revised Completion Date: |  | Allotment: | 135230.61 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 16
[7 empty] | Implementor: | Taba Coconut Farmers Association | No. of days suspended: |  | Disbursement: |  | Actual: | 55% | Actual: | 55% | Actual: | 55% | Actual: | 55% | Actual: | 41.68%
[7 empty] | Duration: | 6 months | No. of days extended: |  |  |  | Slippage: | 5% | Slippage: | 5% | Slippage: | 5% | Slippage: | 5% | Slippage: | -0.42%
[7 empty] | Date Allotment Released: |  | Date completed:
[7 empty] | Date Started: | 2020-08-24
ROAD ID 087 - Tuganay - taba |  | GENERAL FUND CY 2020 | Maintenance | 4.27 | km | CBRMC | Project Cost: | 102630.37 | Target Completion Date: |  | Program: | 102630.37 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: | 42.6% | No. of Persons: | 5 | PO #2020031406 - TABA COCONUT FARMERS ORGANIZATION | PO #2020031406 - TABA COCONUT FARMERS ORGANIZATION | PO #2020031406 - TABA COCONUT FARMERS ORGANIZATION | PO #2020031406 - TABA COCONUT FARMERS ORGANIZATION | PO #2020031406 - TABA COCONUT FARMERS ORGANIZATION | On-going
[7 empty] | Project Engineer: | Maligro | Revised Completion Date: |  | Allotment: | 102630.37 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 21
[7 empty] | Implementor: | Taba Coconut Farmers Association | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual: | 42.31%
[7 empty] | Duration: | 6 months | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | -0.29%
[7 empty] | Date Allotment Released: |  | Date completed:
[7 empty] | Date Started: | 2020-08-24
ROAD ID 090 - Maligaya - New Camiling |  | GENERAL FUND CY 2020 | Maintenance |  | km | CBRMC | Project Cost: | 83915.44 | Target Completion Date: | 2020-11-14 23:59 | Program: | 83915.44 | Planned: | 5% | Planned: | 5% | Planned: | 5% | Planned: | 29.38% | Planned: | 53.1% | No. of Persons: | 6 | On-going | On-going | On-going | On-going | On-going | On-going
[7 empty] | Project Engineer: | Maligro | Revised Completion Date: |  | Allotment: | 83915.44 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 24
[7 empty] | Implementor: | School in the Air Integrated Farmer's Associiation | No. of days suspended: |  | Disbursement: |  | Actual: | 5% | Actual: | 5% | Actual: | 5% | Actual: | 29.38% | Actual: | 53.95%
[7 empty] | Duration: | 185 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0.85%
[7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
[7 empty] | Date Started: | 2020-05-14
ROAD ID 095 - Anibongan - Guadalupe |  | GENERAL FUND CY 2020 | Maintenance | 2.48 | km | CBRMC | Project Cost: | 72444.97 | Target Completion Date: |  | Program: | 72444.97 | Planned: |  | Planned: |  | Planned: |  | Planned: | 42.27% | Planned: | 42.27% | No. of Persons: | 8 | PO #2020031404 - PRK 4. ANIBONGAN CARMENT IRRIGATORS ASSN. | PO #2020031404 - PRK 4. ANIBONGAN CARMENT IRRIGATORS ASSN. | PO #2020031404 - PRK 4. ANIBONGAN CARMENT IRRIGATORS ASSN. | On-going | On-going | On-going
[7 empty] | Project Engineer: | Maligro | Revised Completion Date: |  | Allotment: | 72444.97 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 40
[7 empty] | Implementor: | Anibongan-Carmen Irrigators Asso. Inc | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: | 42.27% | Actual: | 42.27%
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
[7 empty] | Date Started: | 2020-08-04
ROAD ID 097 - Jct. Anibongan - Prk. 2, 7, 5, San Isidro |  | GENERAL FUND CY 2020 | Maintenance | 3.14 | km | CBRMC | Project Cost: | 110478.58 | Target Completion Date: | 2021-03-11 | Program: | 110478.58 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: | 41.64% | No. of Persons: | 5 | PO #2020031378 - SAN ISIDRO FARMERS IRRIGATORS ASSN. | PO #2020031378 - SAN ISIDRO FARMERS IRRIGATORS ASSN. | PO #2020031378 - SAN ISIDRO FARMERS IRRIGATORS ASSN. | PO #2020031378 - SAN ISIDRO FARMERS IRRIGATORS ASSN. | PO #2020031378 - SAN ISIDRO FARMERS IRRIGATORS ASSN. | On-going
[7 empty] | Project Engineer: | Maligro | Revised Completion Date: |  | Allotment: | 110478.58 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 21
[7 empty] | Implementor: | San Isidro Farmers Irrigators Association | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual: | 41.64%
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
[7 empty] | Date Started: | 2020-09-11
ROAD ID 098 - Anibongan - Salvacion - Cabay-angan |  | GENERAL FUND CY 2020 | Maintenance | 6.93 | km | CBRMC | Project Cost: | 162397.48 | Target Completion Date: | 2021-01-31 | Program: | 162397.48 | Planned: |  | Planned: |  | Planned: |  | Planned: | 41.7% | Planned: | 41.7% | No. of Persons: | 4 | PO #2020031379 - PRK4. ANIBONGAN CARMEN IRRIGATORS ASS. | PO #2020031379 - PRK4. ANIBONGAN CARMEN IRRIGATORS ASS. | PO #2020031379 - PRK4. ANIBONGAN CARMEN IRRIGATORS ASS. | On-going | On-going | On-going
[7 empty] | Project Engineer: | Maligro | Revised Completion Date: |  | Allotment: | 162397.48 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 88
[7 empty] | Implementor: | Anibongan-Carmen Irrigators Asso. Inc | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: | 41.7% | Actual: | 41.7%
[7 empty] | Duration: | 6 months | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: | 2020-08-04 | Date completed:
[7 empty] | Date Started: | 2020-01-02
ROAD ID 099 - Mabaus - Cabay - angan |  | GENERAL FUND CY 2020 | Maintenance |  | km | CBRMC | Project Cost: | 90556.21 | Target Completion Date: | 2021-04-13 | Program: | 90556.21 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: | 42.39% | No. of Persons: | 3 | PO #2020031410 - LAMPIA PAG ASA IRRIGATORS ASS., INC. | PO #2020031410 - LAMPIA PAG ASA IRRIGATORS ASS., INC. | PO #2020031410 - LAMPIA PAG ASA IRRIGATORS ASS., INC. | PO #2020031410 - LAMPIA PAG ASA IRRIGATORS ASS., INC. | PO #2020031410 - LAMPIA PAG ASA IRRIGATORS ASS., INC. | On-going
[7 empty] | Project Engineer: | Maligro | Revised Completion Date: |  | Allotment: | 90556.21 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 15
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual: | 42.39%
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
[7 empty] | Date Started: | 2020-10-13
ROAD ID 101 - Jct. Highway Guadalupe - Bdry. Tagum |  | GENERAL FUND CY 2020 | Maintenance | 7.9 | km | CBRMC | Project Cost: | 231823.89 | Target Completion Date: | 2021-07-13 | Program: | 231823.89 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: | 27.75% | No. of Persons: | 4 | PO #2020031376 - LAMPIA PAG ASA IRRIGATORS ASS., INC. | PO #2020031376 - LAMPIA PAG ASA IRRIGATORS ASS., INC. | PO #2020031376 - LAMPIA PAG ASA IRRIGATORS ASS., INC. | PO #2020031376 - LAMPIA PAG ASA IRRIGATORS ASS., INC. | PO #2020031376 - LAMPIA PAG ASA IRRIGATORS ASS., INC. | On-going
[7 empty] | Project Engineer: | Maligro | Revised Completion Date: |  | Allotment: | 231823.89 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 15
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual: | 27.75%
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
[7 empty] | Date Started: | 2020-10-13
ROAD ID 107 - Dujali - San Isidro |  | GENERAL FUND CY 2020 | Maintenance | 3 | km | CBRMC | Project Cost: | 78482.06 | Target Completion Date: | 2021-03-11 | Program: | 78482.06 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: | 41.67% | No. of Persons: | 6 | PO #2020031411 - SAN ISIDRO FARMERS IRRIGATORS ASSN., INC. | PO #2020031411 - SAN ISIDRO FARMERS IRRIGATORS ASSN., INC. | PO #2020031411 - SAN ISIDRO FARMERS IRRIGATORS ASSN., INC. | PO #2020031411 - SAN ISIDRO FARMERS IRRIGATORS ASSN., INC. | PO #2020031411 - SAN ISIDRO FARMERS IRRIGATORS ASSN., INC. | On-going
[7 empty] | Project Engineer: | Maligro | Revised Completion Date: |  | Allotment: | 78482.06 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 21
[7 empty] | Implementor: | San Isidro Farmers Irrigators Association | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual: | 41.67%
[7 empty] | Duration: | 6 months | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
[7 empty] | Date Started: | 2020-09-11
ROAD ID 113 - Dujali - Balisong - Magupising |  | GENERAL FUND CY 2020 | Maintenance | 5.52 | km | CBRMC | Project Cost: | 115911.95 | Target Completion Date: | 2020-12-12 | Program: | 115911.95 | Planned: | 5% | Planned: | 5% | Planned: | 5% | Planned: | 27.78% | Planned: | 55.5% | No. of Persons: | 2 | On-going | On-going | On-going | On-going | On-going | On-going
[7 empty] | Project Engineer: | Maligro | Revised Completion Date: | 2021-01-08 | Allotment: | 115911.95 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 2
[7 empty] | Implementor: | Dujali Poblacion Farmer's Irrigator's Association, Inc. | No. of days suspended: | 27 | Disbursement: |  | Actual: | 5% | Actual: | 5% | Actual: | 5% | Actual: | 27.78% | Actual: | 55.56%
[7 empty] | Duration: | 187 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0.06%
[7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
[7 empty] | Date Started: | 2020-06-08
ROAD ID 130 - Los Amigos 1 - Esperanza - Los Amigos 2 |  | GENERAL FUND CY 2020 | Maintenance | 3.59 | km | CBRMC | Project Cost: | 131608.37 | Target Completion Date: | 2020-02-21 | Program: | 131608.37 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: | 41.88% | No. of Persons: | 4 | PO #2020031351 - LOS AMIGOS GROUP OF WOMEN & FARMERS ASSN. | PO #2020031351 - LOS AMIGOS GROUP OF WOMEN & FARMERS ASSN. | PO #2020031351 - LOS AMIGOS GROUP OF WOMEN & FARMERS ASSN. | PO #2020031351 - LOS AMIGOS GROUP OF WOMEN & FARMERS ASSN. | PO #2020031351 - LOS AMIGOS GROUP OF WOMEN & FARMERS ASSN. | On-going
[7 empty] | Project Engineer: | Maligro | Revised Completion Date: |  | Allotment: | 131608.37 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 16
[7 empty] | Implementor: | Los Amigos Group of Women abd Farmers Association | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual: | 41.88%
[7 empty] | Duration: | 6 months | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
[7 empty] | Date Started: | 2020-08-31
ROAD ID 131 - Mugas - Lanatad |  | GENERAL FUND CY 2020 | Maintenance |  | km | CBRMC | Project Cost: | 31996.54 | Target Completion Date: | 2021-01-20 | Program: | 31996.54 | Planned: |  | Planned: |  | Planned: |  | Planned: | 10.1% | Planned: | 41.64% | No. of Persons: | 6 | Purchase Order # 2020030961 (Katipunan Pantaron Irrigator's Association) | Purchase Order # 2020030961 (Katipunan Pantaron Irrigator's Association) | Purchase Order # 2020030961 (Katipunan Pantaron Irrigator's Association) | On-going | On-going | On-going
[7 empty] | Project Engineer: | Maligro | Revised Completion Date: |  | Allotment: | 31996.54 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 20
[7 empty] | Implementor: | Katipunan Pantaron Irrigator's Association | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: | 10.1% | Actual: | 41.64%
[7 empty] | Duration: | 6 months | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
[7 empty] | Date Started: | 2020-07-20
ROAD ID 134 - New Katipunan - Pantaron |  | GENERAL FUND CY 2020 | Maintenance |  | km | CBRMC | Project Cost: | 53126.32 | Target Completion Date: | 2021-01-20 | Program: | 53126.32 | Planned: |  | Planned: |  | Planned: |  | Planned: | 10% | Planned: | 41.04% | No. of Persons: |  | Purchase Order # 2020030964 (Katipunan Pantaron Irrigator's Association) | Purchase Order # 2020030964 (Katipunan Pantaron Irrigator's Association) | Purchase Order # 2020030964 (Katipunan Pantaron Irrigator's Association) | On-going | On-going | On-going
[7 empty] | Project Engineer: | Maligro | Revised Completion Date: |  | Allotment: | 53126.32 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: | Katipunan Pantaron Irrigator's Association | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: | 10% | Actual: | 41.04%
[7 empty] | Duration: | 6 months | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
[7 empty] | Date Started: | 2020-07-02
ROAD ID 135 - Sto. Tomas - Bdry. Mamacao |  | GENERAL FUND CY 2020 | Maintenance | 4.9 | km | CBRMC | Project Cost: | 116515.66 | Target Completion Date: | 2021-02-05 | Program: | 116515.66 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: | 41.79% | No. of Persons: | 6 | PO #2020031353 - KATIPUNAN PANTARON IRRIGATORS ASSN. | PO #2020031353 - KATIPUNAN PANTARON IRRIGATORS ASSN. | PO #2020031353 - KATIPUNAN PANTARON IRRIGATORS ASSN. | PO #2020031353 - KATIPUNAN PANTARON IRRIGATORS ASSN. | PO #2020031353 - KATIPUNAN PANTARON IRRIGATORS ASSN. | On-going
[7 empty] | Project Engineer: | Maligro | Revised Completion Date: |  | Allotment: | 116515.66 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 18
[7 empty] | Implementor: | Katipunan Pantaron Irrigator's | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual: | 41.79%
[7 empty] | Duration: | 6 months | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
[7 empty] | Date Started: | 2020-08-05
ROAD ID 136 - Fd. Rd. 3 - San Jose |  | GENERAL FUND CY 2020 | Maintenance | 4.55 | km | CBRMC | Project Cost: | 112893.42 | Target Completion Date: | 2021-02-05 | Program: | 112893.42 | Planned: |  | Planned: |  | Planned: |  | Planned: | 42.25% | Planned: | 42.25% | No. of Persons: | 3 | Purchase Order # 2020030974 (Brgy. San Jose Upland Farmer's Assocaition) | Purchase Order # 2020030974 (Brgy. San Jose Upland Farmer's Assocaition) | Purchase Order # 2020030974 (Brgy. San Jose Upland Farmer's Assocaition) | On-going | On-going | On-going
[7 empty] | Project Engineer: | Maligro | Revised Completion Date: |  | Allotment: | 112893.42 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 66
[7 empty] | Implementor: | Brgy. San Jose Upland Farmer's Assocaition | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: | 42.25% | Actual: | 42.25%
[7 empty] | Duration: | 6 months | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
[7 empty] | Date Started: | 2020-08-05
ROAD ID 146 - Bdry. Tagum - Crossing Kinamayan Sto. Tomas |  | GENERAL FUND CY 2020 | Maintenance |  | km | CBRMC | Project Cost: | 429840.12 | Target Completion Date: | 2021-05-21 | Program: | 429840.12 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: | 27.71% | No. of Persons: | 4 | PO #2020031407 - LOS AMIGOS GROUP OF WOMEN & FARMERS ASSN. | PO #2020031407 - LOS AMIGOS GROUP OF WOMEN & FARMERS ASSN. | PO #2020031407 - LOS AMIGOS GROUP OF WOMEN & FARMERS ASSN. | PO #2020031407 - LOS AMIGOS GROUP OF WOMEN & FARMERS ASSN. | PO #2020031407 - LOS AMIGOS GROUP OF WOMEN & FARMERS ASSN. | On-going
[7 empty] | Project Engineer: | Maligro | Revised Completion Date: |  | Allotment: | 429840.12 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 84
[7 empty] | Implementor: | Bobongon Rural Waterworks & Sanitation Association, Inc. | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual: | 27.71%
[7 empty] | Duration: | 6 months | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
[7 empty] | Date Started: | 2020-08-21
ROAD ID 151 - San Jose - Sitio Mahayahay, Magwawa |  | GENERAL FUND CY 2020 | Maintenance | 0.84 | km | CBRMC | Project Cost: | 30789.12 | Target Completion Date: | 2021-02-03 | Program: | 30789.12 | Planned: |  | Planned: |  | Planned: |  | Planned: | 27.78% | Planned: | 27.78% | No. of Persons: |  | Purchase Order # 2020030972 (Brgy. San Jose Upland Farmer's Assocaition) | Purchase Order # 2020030972 (Brgy. San Jose Upland Farmer's Assocaition) | Purchase Order # 2020030972 (Brgy. San Jose Upland Farmer's Assocaition) | On-going | On-going | On-going
[7 empty] | Project Engineer: | Maligro | Revised Completion Date: |  | Allotment: | 30789.12 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: | Brgy. San Jose Upland Farmer's Assocaition | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: | 27.78% | Actual: | 27.78%
[7 empty] | Duration: | 6 months | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
[7 empty] | Date Started: | 2020-08-03
ROAD ID 030 - Jct. Highway - Carmen - Mangalcal - Tubod (Phase I) |  | 20% DF CY 2020 | Rehabilitation |  | km |  | Project Cost: | 1323000 | Target Completion Date: | 2021-02-03 | Program: | 1323000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: | 100% | No. of Persons: | 2 | Plan On-going | Plan On-going | Plan On-going | Plan On-going | Plan On-going | Suspended 10/1/2020
[7 empty] | Project Engineer: | Obar | Revised Completion Date: |  | Allotment: | 1323000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 44
[7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual: | 68.83%
[7 empty] | Duration: | 90 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | -31.17%
[7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
[7 empty] | Date Started: | 2020-06-15
ROAD ID 031 - Tuganay - Taba (Phase I) |  | 20% DF CY 2020 | Rehabilitation |  | km |  | Project Cost: | 507500 | Target Completion Date: | 2020-06-17 | Program: | 507500 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: | 100% | No. of Persons: | 2 | Plan On-going | Plan On-going | Plan On-going | Plan On-going | Plan On-going | Suspended 6/13/2020
[7 empty] | Project Engineer: | Obar | Revised Completion Date: | 2020-08-21 | Allotment: | 507500 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 44
[7 empty] | Implementor: | PEO | No. of days suspended: | 65 | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual: | 68.87%
[7 empty] | Duration: | 30 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | -31.13%
[7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
[7 empty] | Date Started: | 2020-05-18
Jct. Highway - Guadalupe - Bdry. Tagum (Phase I) |  | 20% DF CY 2020 | Rehabilitation |  | km |  | Project Cost: | 910000 | Target Completion Date: | 2020-08-06 | Program: | 910000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: | 3.2% | No. of Persons: | 2 | Suspended June 13, 2020 due to unavailability of heavy equipment | Plan On-going | Plan On-going | Plan On-going | Plan On-going | Suspended June 13, 2020 due to unavailability of heavy equipment
[7 empty] | Project Engineer: | Obar | Revised Completion Date: |  | Allotment: | 910000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 52
[7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual: | 1.2%
[7 empty] | Duration: | 80 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | -2%
[7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
[7 empty] | Date Started: | 2020-05-18
Sitio Malaga - Tibulao (Phase I) |  | 20% DF CY 2020 | Rehabilitation |  | km |  | Project Cost: | 350000 | Target Completion Date: | 2020-06-17 | Program: | 350000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: | 3.5% | No. of Persons: | 2 | Plan On-going | Plan On-going | Plan On-going | Plan On-going | Plan On-going | Suspended June 13, 2020 due to unavailability of heavy equipment
[7 empty] | Project Engineer: | Obar | Revised Completion Date: |  | Allotment: | 350000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 44
[7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual: | 1.2%
[7 empty] | Duration: | 30 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | -2.3%
[7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
[7 empty] | Date Started: | 2020-05-18
Dujali - Pawas - San Vicente (Phase I) |  | 20% DF CY 2020 | Rehabilitation |  | km |  | Project Cost: | 525000 | Target Completion Date: | 2020-07-02 | Program: | 525000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: | 6.5% | No. of Persons: | 2 | Plan On-going | Plan On-going | Plan On-going | Plan On-going | Plan On-going | PTemporarily Suspended June 13, 2020 due to unavailability of heavy equipment
[7 empty] | Project Engineer: | Obar | Revised Completion Date: |  | Allotment: | 525000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 42
[7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual: | 1.2%
[7 empty] | Duration: | 45 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | -5.3%
[7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
[7 empty] | Date Started: | 2020-05-18
Fd. Rd. 2 - Sto. Tomas - Magwawa (Phase I) |  | 20% DF CY 2020 | Rehabilitation |  | km |  | Project Cost: | 300000 | Target Completion Date: | 2020-06-17 | Program: | 300000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: | 100% | No. of Persons: | 3 | Plan On-going | Plan On-going | Plan On-going | Plan On-going | Plan On-going | Suspended 10/15/2020
[7 empty] | Project Engineer: | Obar | Revised Completion Date: | 10/31/2020 | Allotment: | 300000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 66
[7 empty] | Implementor: | PEO | No. of days suspended: | 80 | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual: | 61.3%
[7 empty] | Duration: | 30 | No. of days extended: | 56 |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | -38.7%
[7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
[7 empty] | Date Started: | 2020-05-18
Jct,. Bdry. Tagum- Talomo (Phase I) |  | 20% DF CY 2020 | Rehabilitation |  | km |  | Project Cost: | 1400000 | Target Completion Date: | 2020-09-15 | Program: | 1400000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: | 41.2% | No. of Persons: | 4 | POW for approval with the Governor | POW for approval with the Governor | POW for approval with the Governor | POW for approval with the Governor | POW for approval with the Governor | Suspended June 13, 2020
[7 empty] | Project Engineer: | Obar | Revised Completion Date: |  | Allotment: | 1400000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 88
[7 empty] | Implementor: | Admin | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual: | 39.6%
[7 empty] | Duration: | 120 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | -1.6%
[7 empty] | Date Allotment Released: |  | Date completed:
[7 empty] | Date Started: | 2020-05-18
Rehab. Of Various Local Roads @ Tagum City |  | 20% Development Fund CY 2020 | Rehabilitaion |  | km | Admin | Project Cost: | 2518182 | Target Completion Date: | 2020-10-20 | Program: | 2518182 | Planned: | 48.18% | Planned: | 48.18% | Planned: | 87.52% | Planned: | 87.52% | Planned: | 98.14% | No. of Persons: | 8 | On-going | On-going | On-going | On-going | On-going | On-going
[7 empty] | Project Engineer: | Bataller | Revised Completion Date: |  | Allotment: | 2518182 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 120
[7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: | 48.18% | Actual: | 48.18% | Actual: | 87.65% | Actual: | 87.65% | Actual: | 84.78%
[7 empty] | Duration: | 155 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0.13% | Slippage: | 0.13% | Slippage: | -13.36%
[7 empty] | Date Allotment Released: |  | Date completed:
[7 empty] | Date Started: | 2020-05-18
Rehab. Of Various Local Roads @ Asuncion |  | 20% Development Fund CY 2020 | Rehabilitaion |  | km | Admin | Project Cost: | 2518182 | Target Completion Date: | 2020-10-20 | Program: | 2518182 | Planned: | 37.83% | Planned: | 37.83% | Planned: | 37.83% | Planned: | 37.83% | Planned: | 88.98% | No. of Persons: | 12 | On-going | On-going | On-going | On-going | On-going | On-going
[7 empty] | Project Engineer: | Bataller | Revised Completion Date: |  | Allotment: | 2518182 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 372
[7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: | 37.82% | Actual: | 37.82% | Actual: | 37.82% | Actual: | 37.82% | Actual: | 45%
[7 empty] | Duration: | 155 | No. of days extended: |  |  |  | Slippage: | -0.01% | Slippage: | -0.01% | Slippage: | -0.01% | Slippage: | -0.01% | Slippage: | -43.98%
[7 empty] | Date Allotment Released: |  | Date completed:
[7 empty] | Date Started: | 2020-05-18
Rehab. Of Various Local Roads @ Kapalong |  | 20% Development Fund CY 2020 | Rehabilitaion |  | km | Admin | Project Cost: | 2518182 | Target Completion Date: | 2020-10-07 | Program: | 2518182 | Planned: | 18.24% | Planned: | 36.22% | Planned: | 91.3% | Planned: | 76.61% | Planned: | 100% | No. of Persons: | 12 | On-going | On-going | On-going | On-going | On-going | On-going
[7 empty] | Project Engineer: | Bataller | Revised Completion Date: |  | Allotment: | 2518182 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 180
[7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: | 18.24% | Actual: | 36.22% | Actual: | 91.28% | Actual: | 76.61% | Actual: | 81.61%
[7 empty] | Duration: | 84 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | -0.02% | Slippage: | 0% | Slippage: | -18.39%
[7 empty] | Date Allotment Released: |  | Date completed:
[7 empty] | Date Started: | 2020-07-15
Rehab. Of Various Local Roads @ New Corella |  | 20% Development Fund CY 2020 | Rehabilitaion |  | km | Admin | Project Cost: | 2518182 | Target Completion Date: | 2020-10-21 23:59 | Program: | 2518182 | Planned: |  | Planned: | 35.54% | Planned: |  | Planned: |  | Planned: | 100% | No. of Persons: | 13 | POW on process | On-going | POW on process | POW on process | POW on process | On-going
[7 empty] | Project Engineer: | Bataller | Revised Completion Date: |  | Allotment: | 2518182 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 403
[7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: | 15.46% | Actual: |  | Actual: |  | Actual: | 79.92%
[7 empty] | Duration: | 80 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | -20.08% | Slippage: | 0% | Slippage: | 0% | Slippage: | -20.08%
[7 empty] | Date Allotment Released: |  | Date completed:
[7 empty] | Date Started: | 2020-08-03
Rehab. Of Various Local Roads @ San Isidro |  | 20% Development Fund CY 2020 | Rehabilitaion |  | km | Admin | Project Cost: | 2518182 | Target Completion Date: | 2020-10-21 23:59 | Program: | 2518182 | Planned: |  | Planned: | 35.54% | Planned: | 73.27% | Planned: | 73.27% | Planned: | 100% | No. of Persons: | 10 | For implementation | On-going | On-going | On-going | On-going | On-going
[7 empty] | Project Engineer: | Bataller | Revised Completion Date: |  | Allotment: | 2518182 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 150
[7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: | 35.54% | Actual: | 73.26% | Actual: | 73.26% | Actual: | 79.92%
[7 empty] | Duration: | 80 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | -0.01% | Slippage: | -0.01% | Slippage: | -20.08%
[7 empty] | Date Allotment Released: |  | Date completed:
[7 empty] | Date Started: | 2020-08-03
Rehab. Of Various Local Roads @ Talaingod |  | 20% Development Fund CY 2020 | Rehabilitaion |  | km | Admin | Project Cost: | 2518182 | Target Completion Date: | 2020-12-12 | Program: | 2518182 | Planned: | 10.3% | Planned: | 10.3% | Planned: | 51.1% | Planned: | 51.1% | Planned: | 91.91% | No. of Persons: | 9 | On-going | On-going | On-going | On-going | On-going | On-going
[7 empty] | Project Engineer: | Bataller | Revised Completion Date: |  | Allotment: | 2518182 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 135
[7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: | 10.3% | Actual: | 10.3% | Actual: | 51.11% | Actual: | 51.11% | Actual: | 91.91%
[7 empty] | Duration: | 150 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0.01% | Slippage: | 0.01% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
[7 empty] | Date Started: | 2020-07-15
Rehab. Of Various Local Roads @ Panabo City |  | 20% DF CY 2020 | Rehabilitation |  | km |  | Project Cost: | 2518182 | Target Completion Date: | 2020-10-12 | Program: | 2518182 | Planned: |  | Planned: |  | Planned: |  | Planned: | 75% | Planned: | 75% | No. of Persons: | 5 | Abstract # 0420201633 - Billboard; Abstract 0520201661 - hardware | Abstract # 0420201633 - Billboard; Abstract 0520201661 - hardware | Abstract # 0420201633 - Billboard; Abstract 0520201661 - hardware | On-going | On-going | On-going
[7 empty] | Project Engineer: | Gamad/Clar | Revised Completion Date: |  | Allotment: | 2518182 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 110
[7 empty] | Implementor: | Admin | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: | 80% | Actual: | 80%
[7 empty] | Duration: | 150 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 5% | Slippage: | 5%
[7 empty] | Date Allotment Released: |  | Date completed:
[7 empty] | Date Started: | 2020-05-15
Rehab. Of Various Local Roads @ B.E Dujali |  | 20% DF CY 2020 | Rehabilitation |  | km |  | Project Cost: | 2518182 | Target Completion Date: | 2020-12-13 | Program: | 2518182 | Planned: |  | Planned: |  | Planned: |  | Planned: | 35% | Planned: | 35% | No. of Persons: | 4 | Purchase Request # 20053256 - Hardware; PR # 20053255 - Billboard | Purchase Request # 20053256 - Hardware; PR # 20053255 - Billboard | Purchase Request # 20053256 - Hardware; PR # 20053255 - Billboard | On-going | On-going | On-going
[7 empty] | Project Engineer: | Gamad/Clar | Revised Completion Date: |  | Allotment: | 2518182 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 88
[7 empty] | Implementor: | Admin | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: | 52% | Actual: | 52%
[7 empty] | Duration: | 150 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 17% | Slippage: | 17%
[7 empty] | Date Allotment Released: |  | Date completed:
[7 empty] | Date Started: | 2020-07-16
Rehab. Of Various Local Roads @ Carmen |  | 20% DF CY 2020 | Rehabilitation |  | km |  | Project Cost: | 2518182 | Target Completion Date: | 2020-10-15 | Program: | 2518182 | Planned: |  | Planned: |  | Planned: |  | Planned: | 35% | Planned: | 35% | No. of Persons: | 3 | Abstract # 0420201633 - Billboard; Abstract 0520201661 - hardware | Abstract # 0420201633 - Billboard; Abstract 0520201661 - hardware | Abstract # 0420201633 - Billboard; Abstract 0520201661 - hardware | On-going | On-going | On-going
[7 empty] | Project Engineer: | Gamad/Clar | Revised Completion Date: |  | Allotment: | 2518182 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 66
[7 empty] | Implementor: | Admin | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: | 52% | Actual: | 52%
[7 empty] | Duration: | 150 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 17% | Slippage: | 17%
[7 empty] | Date Allotment Released: |  | Date completed:
[7 empty] | Date Started: | 2020-05-18
Rehab. Of Various Local Roads @ Sto. Tomas |  | 20% DF CY 2020 | Rehabilitation |  | km |  | Project Cost: | 2518182 | Target Completion Date: | 2020-12-13 | Program: | 2518182 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: | 60% | No. of Persons: | 3 | Plan On-going | Plan On-going | Plan On-going | Plan On-going | Plan On-going | On-going
[7 empty] | Project Engineer: | Gamad/Clar | Revised Completion Date: |  | Allotment: | 2518182 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 66
[7 empty] | Implementor: | Admin | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual: | 65%
[7 empty] | Duration: | 150 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 5%
[7 empty] | Date Allotment Released: |  | Date completed:
[7 empty] | Date Started: | 2020-07-16
Improvement and Desiltation of Ising Creek |  | 5% Calamity Fund CY 2020 | Desiltation |  | ln.m |  | Project Cost: | 2000000 | Target Completion Date: | 2020-10-24 | Program: | 2000000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: | 100% | No. of Persons: |  | Abstract # 0420201637; 0520201662 | Abstract # 0420201637; 0520201662 | Abstract # 0420201637; 0520201662 | On-going (Resumption date 10/23/2020) | On-going (Resumption date 10/23/2020) | On-going
[7 empty] | Project Engineer: | Toquero | Revised Completion Date: |  | Allotment: | 2000000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: | Admin | No. of days suspended: | 99 | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: | 1.21% | Actual: | 50%
[7 empty] | Duration: | 100 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 1.21% | Slippage: | -50%
[7 empty] | Date Allotment Released: |  | Date completed:
[7 empty] | Date Started: | 2020-07-16
Desiltation of Buhang Creek, Anibongan, Carmen |  | 5% Calamity Fund CY 2020 | Desiltation |  | ln.m |  | Project Cost: | 2130206 | Target Completion Date: | 2020-10-18 | Program: | 2130206 | Planned: |  | Planned: |  | Planned: |  | Planned: | 50% | Planned: | 100% | No. of Persons: | 4 | Abstract # 0520201657; 0420201626 | Abstract # 0520201657; 0420201626 | Abstract # 0520201657; 0420201626 | On-going | On-going | On-going
[7 empty] | Project Engineer: | Toquero | Revised Completion Date: |  | Allotment: | 2130206 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 88
[7 empty] | Implementor: | Admin | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: | 50% | Actual: | 55%
[7 empty] | Duration: | 94 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | -45%
[7 empty] | Date Allotment Released: |  | Date completed:
[7 empty] | Date Started: | 2020-07-16
Improvement of Mabaus - Salvacion Provincial Road Continuing Road Opening |  | 5% Calamity Fund CY 2020 | Improvement |  | ln.m |  | Project Cost: | 500000 | Target Completion Date: | 2020-08-11 | Program: | 500000 | Planned: |  | Planned: |  | Planned: |  | Planned: | 100% | Planned: | 100% | No. of Persons: |  | Plan On-going | Plan On-going | Plan On-going | Suspended due to unavailability of equipment, area under stabilization | Suspended due to unavailability of equipment, area under stabilization | On-going
[7 empty] | Project Engineer: | Toquero | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: | Admin | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: | 1.3% | Actual: | 30%
[7 empty] | Duration: | 26 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | -98.7% | Slippage: | -70%
[7 empty] | Date Allotment Released: |  | Date completed:
[7 empty] | Date Started: | 2020-07-16
Note on D257: chai: Previously Perimeter Fence of Day Care Center I & II, Nanyo, Panabo City (20% Development Fund CY 2018 (STIMULUS 2018)
Note on D263: chai: 20% DF CY 2019
Note on D269: chai: 20% DF CY 2019
Note on AF341: Cerela Montes: suspended 10/05/20
Note on AF347: Cerela Montes:
Note on J353: chai: 20% Development Fund CY 2018 Variation Order - 21,512,501.5 - 1,408,112.95

## 4th Quarter CY 2020 (For Imple)
|  |  |  | 0 |  |  |  | 275063816.87 |  |  |  | 550127633.74 | [11 empty] | 0
` | ECONOMIC (INFRASTRUCTURE DEV'T. PROGRAM)
OFFICE/AGENCY: | PROVINCIAL ENGINEER'S OFFICE
AREA: | 1ST ENGINEERING DISTRICT - COMPLETED, ON-GOING AND FOR IMPLEMENTATION PROJECTS | [7 empty] | Total extended
#REF!
#REF!
NAME OF PROJECT |  | SOURCE OF FUND | TYPE OF PROJECT | PHYSICAL TARGET (DESCRIPTION) |  | MODE OF IMPLEMENTATION | PROJECT DATA |  |  |  | FINANCIAL |  | PHYSICAL ACCOMPLISHMENT (JULY) |  | PHYSICAL ACCOMPLISHMENT (AUGUST) |  | PHYSICAL ACCOMPLISHMENT (SEPTEMBER) |  | PHYSICAL ACCOMPLISHMENT (OCTOBER) |  | PHYSICAL ACCOMPLISHMENT |  | EMPLOYMENT GENERATED |  | REMARKS (JULY) | REMARKS (AUGUST) | REMARKS (SEPTEMBER) | REMARKS (OCTOBER | REMARKS (NOVEMBER) | REMARKS
Inst. of transformer and accessories, Brgy. Kinawitnon |  | PRDP CY 2016 | Electrification |  |  | Admin | Project Cost: | 150000 | Target Completion Date: |  | Program: | 150000 | Planned: |  | No. of Persons: |  | Purchase Order # 2019103228 - Transformer; Purchase Order # 2019102931 - Billboard; Purchase Order # 2019103227 - Lumber |  |  |  | Planned: |  | No. of Persons: | [6 empty] | For verification
[7 empty] | Project Engineer: | Porras | Revised Completion Date: |  | Allotment: | 150000 | Revised: |  | No. of Man-days: | [5 empty] | Revised: |  | No. of Man-days:
[7 empty] | Implementor: | Contract | No. of days suspended: |  | Disbursement: |  | Actual: | [7 empty] | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | [6 empty] | Slippage: | 0%
[7 empty] | Date Allotment Released: | 2018-07-31 | Date completed:
Date Started:
Construction of Concrete Pavement, Tibulao, Carmen |  | 20% DF CY 2017 (STIMULUS) | Pavement |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Fund already transferred at Municipality of Talaingod with ChecK No. 2445181 and OR # 7955667, dated March 16, 2018 . Amended from Electrification @ Prk. 1A-Prk. 5A) | On-going (Implemented by MLGU, since transfer of fund ) | On-going (Implemented by MLGU, since transfer of fund ) | Hold in abeyance | Hold in abeyance | Hold in abeyance
[7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Agricultural Productivity Support Project-Fishing Net with Pump Boat, Tambo,IGACOS |  | OPPAP-PAMANA CY 2017 |  |  |  |  | Project Cost: | 1500000 | Target Completion Date: |  | Program: | 1500000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | For PR | For PR | For PR | For PR | For PR | PR on process (Waiting for the 2nd tranche)
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 1500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Agricultural Productivity Support Project-Fishing Net with Pump Boat, Limao, Peñaplata District, IGACOS |  | OPPAP-PAMANA CY 2017 |  |  |  |  | Project Cost: | 1500000 | Target Completion Date: |  | Program: | 1500000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | For PR | For PR | For PR | For PR | For PR | PR on process (Waiting for the 2nd tranche)
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 1500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Agricultural Productivity Support Project-Fishing Net with Pump Boat, Kinawitnon, Babak District, IGCAOS |  | OPPAP-PAMANA CY 2017 |  |  |  |  | Project Cost: | 1500000 | Target Completion Date: |  | Program: | 1500000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | For PR | For PR | For PR | For PR | For PR | PR on process (Waiting for the 2nd tranche)
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 1500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Const. of Trading Post, Storage Building with (1) unit Hauling Truck, Brgy. Pandapan |  | OPPAP-PAMANA CY 2017 | Building |  | sq.m |  | Project Cost: | 3975000 | Target Completion Date: | 0 | Program: | 3975000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Abstract 1220194004 (Tagum Builders);PO # 2019102828 - Truck | Abstract 1220194004 (Tagum Builders);PO # 2019102828 - Truck | Abstract 1220194004 (Tagum Builders);PO # 2019102828 - Truck | Waiting for approval of Notice of Award | Waiting for approval of Notice of Award | PR on process (Waiting for the 2nd tranche)
[7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 3975000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: | CY 2017 | Date completed:
Date Started:
Cattle Production- Brgy. Tiburcia, Gupitan and Semong, Kapalong |  | OPPAP-PAMANA CY 2017 | Building |  | sq.m |  | Project Cost: | 1500000 | Target Completion Date: |  | Program: | 1500000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | For RE-PR | For RE-PR | For RE-PR |  |  | Procurement on process. Waiting for the 2nd tranch.
[7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 1500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Cattle Production, Brgy. Palma Gil, Brgy. Sto. Nino, Brgy. Dagohoy, Talaingod, Davao del Norte |  | OPPAP-PAMANA CY 2017 | Building |  | sq.m |  | Project Cost: | 1500000 | Target Completion Date: |  | Program: | 1500000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | For RE-PR | For RE-PR | For RE-PR |  |  | Procurement on process. Waiting for the 2nd tranch.
[7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 1500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Installation of potable water System at Purok Nangka, Pandapan, Tagum City |  | 20% DF CY 2018 | Water System |  |  | Admin | Project Cost: | 1125000 | Target Completion Date: |  | Program: | 1125000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Waiting for deed of donation. Follow-up letter was already issued | Waiting for deed of donation. Follow-up letter was already issued | Plan preparation on-going | Plan preparation on-going | Plan preparation on-going | Plan preparation on-going
[7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 1125000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Rehab./Impv't. of San Vicente Water System, Asuncion |  | 20% DF CY 2018 | Water System |  |  | Admin | Project Cost: | 1125000 | Target Completion Date: |  | Program: | 1125000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Waiting for deed of donation. Follow-up letter was already issued | Waiting for deed of donation. Follow-up letter was already issued | Plan preparation on-going | Plan preparation on-going | Plan preparation on-going | Procurement on process.
[7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 1125000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: | 2018-10-26 | Date completed:
Date Started:
Impv't. of Water System, Brgy. Poblacion, Kaputian (Level II) |  | 20% DF CY 2018 | Water System |  |  | Admin | Project Cost: | 1250000 | Target Completion Date: |  | Program: | 1250000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Waiting for deed of donation. Follow-up letter was already issued | Waiting for deed of donation. Follow-up letter was already issued | Plan preparation on-going |  |  | Procurement on process.
[7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 1250000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Water System at brgy. Malativas, Panabo City |  | 20% DF CY 2018 | Water System |  |  | Admin | Project Cost: | 1250000 | Target Completion Date: |  | Program: | 1250000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | For preparation of POW & Plan c/o PDPM - POSSIBLE TRANSFER OF SITE SUBJECT FOR TRANSFER OF LOCATION . NO DEED OF DONATION | For preparation of POW & Plan c/o PDPM - POSSIBLE TRANSFER OF SITE SUBJECT FOR TRANSFER OF LOCATION . NO DEED OF DONATION | For preparation of POW & Plan c/o PDPM - POSSIBLE TRANSFER OF SITE SUBJECT FOR TRANSFER OF LOCATION . NO DEED OF DONATION | For preparation of POW & Plan c/o PDPM - POSSIBLE TRANSFER OF SITE SUBJECT FOR TRANSFER OF LOCATION . NO DEED OF DONATION | For preparation of POW & Plan c/o PDPM - POSSIBLE TRANSFER OF SITE SUBJECT FOR TRANSFER OF LOCATION . NO DEED OF DONATION | For preparation of POW & Plan c/o PDPM - POSSIBLE TRANSFER OF SITE SUBJECT FOR TRANSFER OF LOCATION . NO DEED OF DONATION
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 1250000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Construction of IP Tribal Council of Women at Brgy. Camansa, Asuncion |  | 20% DF CY 2018 | Building |  | sq.m | Admin | Project Cost: | 560000 | Target Completion Date: |  | Program: | 560000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Purchase Request # 20032714 | PR cancelled due to To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | PR cancelled due to To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | PR cancelled due to To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | PR cancelled due to To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | PR cancelled due to To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
[7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 560000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Const. of New Brgy. Stage, San Pedro, Panabo City |  | 20% DF CY 2018 (STIMULUS) | Building |  | sq.m | Contract | Project Cost: | 500000 | Target Completion Date: | 0 | Program: | 500000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Plan and POW Preparation for preparation | Plan and POW Preparation for preparation | Plan and POW Preparation Ongoing | Plan and POW Preparation Ongoing | Plan and POW Preparation Ongoing | Plan and POW Preparation Ongoing
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Const. of Multi-Purpose Bldg. Sto. Nino, Panabo City |  | 20% DF CY 2018 (STIMULUS) | Court |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | PR # 20032818 | PR # 20032818 | Procurement on process | Hold in abeyance | Hold in abeyance | Hold in abeyance
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Water System From Prk. 6 - Prk. 2 - Prk. 5A, Tagbay, IGCS |  | 20% DF CY 2018 (STIMULUS) | Water System |  |  | Admin | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | For Implementation | For Implementation | For Implementation | For Implementation | For Implementation | For Implementation
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Drilling of Water System, Linusotan, IGCS |  | 20% DF CY 2018(STIMULUS) | Water System |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Grouted Riprap on Embankment Sto. Ñino, Talaingod |  | 20% DF CY 2018 (STIMULUS) | Embankment |  |  |  | Project Cost: |  | Target Completion Date: |  | Program: | 0 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | PROJECT Was funded by LGU, Kapalong | PROJECT Was funded by LGU, Kapalong | PROJECT Was funded by LGU, Kapalong | Procurment on process | Procurment on process | Procurment on process
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 0 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Rehabilitation of Local Roads at Dalisay-Manay Road Section, Panabo City |  | SB # 4 CY 2019 | Road |  |  | Admin | Project Cost: | 246100 | Target Completion Date: |  | Program: | 246100 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | For implementation | For implementation | For implementation | For implementation | For implementation | For implementation
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 246100 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Jct. Highway Gabuyan - Semong - Dagohoy |  | 20% DF CY 2019 | Road Rehabilitation | 4.34 |  | Admin | Project Cost: | 2492000 | Target Completion Date: |  | Program: | 2492000 | Planned: |  | Planned: | 52.32% | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | For implementation (Waiting for the delivery of geo-grid materials. An approved request letter dated Dec. 3, 2019 for the extension of 50 days from Provincial Administrator Engr. Rabanoz is on file | Suspended due to continous rain. Waiting for the stability of swamp area. | Suspended due to continous rain. Waiting for the stability of swamp area. |  |  | For implementation
[7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 2492000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: | Admin | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: | 52.32% | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Lower Asuncion - Upper Asuncion |  | 20% DF CY 2019 | Road Rehabilitation | 1.02 | km | Admin | Project Cost: |  | Target Completion Date: |  | Program: | 0 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. |  |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 0 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Construction of PWS, Brgy. Brgy. Kiotoy, Panabo City |  | 20% DF CY 2019 | Georesistivity |  |  |  | Project Cost: | 62500 | Target Completion Date: |  | Program: | 62500 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 62500 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Construction of PWS, Brgy. Linosutan, Talikud, IGCS |  | 20% DF CY 2019 | Water System |  |  |  | Project Cost: | 62500 | Target Completion Date: |  | Program: | 62500 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Procurement on process | Procurement on process | Procurement on process | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No 1 | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No 1 | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No 1
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 62500 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Construction of PWS, Brgy. San Miguel, Samal, IGCS |  | 20% DF CY 2019 | Water System |  |  |  | Project Cost: | 62500 | Target Completion Date: |  | Program: | 62500 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 62500 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Construction of PWS, Cacao, Panabo City |  | 20% DF CY 2019 | Water System |  |  |  | Project Cost: | 62500 | Target Completion Date: |  | Program: | 62500 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | For cancellation. Purchase of Geo-resistivity equipment but procurement still on process | For cancellation. Purchase of Geo-resistivity equipment but procurement still on process | For amendment indicating phase 2 since the project title is the same with stimulus project (letter will be submitted by Mr. Amamio-focal person for water system for explanation) | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 62500 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Const. of PWS Mamalian, San Isidro |  | 20% DF CY 2019 | Water System |  |  | Admin | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | For declaration of savings because the spring water source is not feasible for development. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
[7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Const. of PWS Sagayen, San Isidro |  | 20% DF CY 2019 | Water System |  |  | Admin | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. |  |  | For implementation
[7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Construction of PWS, Brgy. Purok 7-A and B, Brgy. Capungagan, kapalong |  | 20% DF CY 2019 | Water System |  |  | Admin | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. |  |  | For implementation
[7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Construction of PWS Level II in Purok 2, Pag-Asa, kapalong |  | 20% DF CY 2019 | Potable Water System |  |  | Admin | Project Cost: | 500000 | Target Completion Date: | 0 | Program: | 500000 | Planned: | 100% | Planned: | 100% | Planned: | 100% | Planned: |  | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. |  |  | For implementation
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: | 100% | Revised: | 81.57% | Revised: | 81.57% | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: | 72.68% | Actual: | 76.39% | Actual: | 76.39% | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | -27.32% | Slippage: | -5.179% | Slippage: | -5.179% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Impv't. of Potable Water System, Tagbitan-ag, Samal Dist. |  | 20% DF CY 2019 | Water System |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | For implementation | For implementation | For implementation | For implementation | For implementation | For implementation
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: | 2019-06-19 | Date completed:
Date Started:
Impv't. of Potable Water System, San Antonio, babak, IGCS |  | 20% DF CY 2019 | Water System |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: | 2019-06-25 | Date completed:
Date Started:
Construction of PWS, Brgy. Buenavista, Panabo City |  | 20% DF CY 2019 | Water System |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | For implementation | For implementation | For implementation | For implementation | For implementation | For implementation
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: | June 19 ,2019 | Date completed:
Date Started:
Construction of PWS, Brgy. Brgy. Kiotoy, Panabo City |  | 20% DF CY 2019 | Water System |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Rehab. of PWS, Brgy. San Miguel, Babak, IGCS |  | 20% DF CY 2019 | Water System |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Construction of PWS, Brgy. Cacao, Panabo City |  | 20% DF CY 2019 | Water System |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | For cancellation. Purchase of Geo-resistivity equipment but procurement still on process | For cancellation. Purchase of Geo-resistivity equipment but procurement still on process | For amendment indicating phase 2 since the project title is the same with stimulus project (letter will be submitted by Mr. Amamio-focal person for water system for explanation) | For amendment indicating phase 2 since the project title is the same with stimulus project (letter will be submitted by Mr. Amamio-focal person for water system for explanation) | For amendment indicating phase 2 since the project title is the same with stimulus project (letter will be submitted by Mr. Amamio-focal person for water system for explanation) | For amendment indicating phase 2 since the project title is the same with stimulus project (letter will be submitted by Mr. Amamio-focal person for water system for explanation)
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Rehabilitation of Potable Water System, Brgy. Pangubatan, kaputian Dist. IGCS |  | 20% DF CY 2019 | Water System |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | For implementation | Declared as savings in the AIP 2nd Revision to fund for the Construction of PWS in Brgy Linusotan, Kaputian Dist. IGACOS (Project was funded by OPAPP CY 2018) | Declared as savings in the AIP 2nd Revision to fund for the Construction of PWS in Brgy Linusotan, Kaputian Dist. IGACOS (Project was funded by OPAPP CY 2018) | Declared as savings in the AIP 2nd Revision to fund for the Construction of PWS in Brgy Linusotan, Kaputian Dist. IGACOS (Project was funded by OPAPP CY 2018) | Declared as savings in the AIP 2nd Revision to fund for the Construction of PWS in Brgy Linusotan, Kaputian Dist. IGACOS (Project was funded by OPAPP CY 2018) | Declared as savings in the AIP 2nd Revision to fund for the Construction of PWS in Brgy Linusotan, Kaputian Dist. IGACOS (Project was funded by OPAPP CY 2018)
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Rural Electrification at Sitio Sagrada, Pob. Kaputian, IGCS |  | 20% DF CY 2019 | Electrification |  |  |  | Project Cost: | 1000000 | Target Completion Date: |  | Program: | 1000000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Purchase Request # 19031251 | Purchase Request # 19031251 | For implementation | For implementation | For implementation | For implementation
[7 empty] | Project Engineer: | Buena | Revised Completion Date: |  | Allotment: | 1000000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Const. of Multi-Purpose Hall Center (Cultural Heritage in Ancestral Domain of Ata-Manobo) |  | 20% DF CY 2019 | Building |  |  | Admin | Project Cost: | 3000000 | Target Completion Date: |  | Program: | 3000000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Fund re-aligned to GIDAS projects | Fund re-aligned to GIDAS projects | Fund re-aligned to GIDAS projects |  |  | Fund re-aligned to GIDAS projects
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 3000000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Construction of Abilidad Training Center, Gov't. Center, Mankilam, Tagum City |  | 20% DF CY 2019 | Building |  |  |  | Project Cost: | 7000000 | Target Completion Date: |  | Program: | 7000000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Fund re-aligned to GIDAS projects | Fund re-aligned to GIDAS projects | Fund re-aligned to GIDAS projects | Fund re-aligned to GIDAS projects | Fund re-aligned to GIDAS projects | Fund re-aligned to GIDAS projects
[7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 7000000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Const. of Multi-Purpose Covered Court/Evacuation Center Ph. I, Duterte St., Poblacion, New Corella |  | 20% DF CY 2019 | Building |  | sq.m | Admin | Project Cost: | 2000000 | Target Completion Date: | 0 | Program: | 2000000 | Planned: | 84.4% | Planned: | 100% | Planned: | 100% | Planned: |  | Planned: |  | No. of Persons: |  | On-going | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. |  |  | Procurement on process
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 2000000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: | 84.4% | Actual: | 100% | Actual: | 100% | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Impv't./Beautification of Brgy. Grounds, Quezon, Panabo City |  | 20% DF CY 2019 (STIMULUS | Ground dev't. |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Re aligned to other stimulus projects that needs additional funding | Re aligned to other stimulus projects that needs additional funding | Re aligned to other stimulus projects that needs additional funding | Re aligned to other stimulus projects that needs additional funding | Re aligned to other stimulus projects that needs additional funding | Re aligned to other stimulus projects that needs additional funding
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Desilting of Canal, New Pandan, Panabo City |  | 20% DF CY 2019 (STIMULUS | Desiltation |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
[7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: |  | Slippage: |  | Slippage:
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Const. of 2 Storey Multi-Purpose Hall Ph. 3 (Brgy. Hall), Poblacion, New Corella |  | SB NO. 4 CY 2019 (STIMULUS) | Building | 42 | sq.m | Admin | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: | 100% | Planned: | 100% | Planned: | 100% | Planned: | 100% | Planned: |  | No. of Persons: |  | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: | 100% | Actual: | 100% | Actual: | 100% | Actual: | 100% | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Const. of Evacuation Center, Bobongon, Sto. Tomas |  | 20% DF CY 2019 (STIMULUS | Building |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: | 100% | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Re aligned to other stimulus projects that needs additional funding | Re aligned to other stimulus projects that needs additional funding | Re aligned to other stimulus projects that needs additional funding | Re aligned to other stimulus projects that needs additional funding | Re aligned to other stimulus projects that needs additional funding | Re aligned to other stimulus projects that needs additional funding
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: | 100% | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Rehab. Of Water System at Purok Cabang & Mangga , Pinamuno, San Isidro |  | 20% DF CY 2019 (STIMULUS) | Water System |  |  | Contract | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | PO# 2020010025 (RLHV) | PO# 2020010025 (RLHV) | PO# 2020010025 (RLHV) | PO# 2020010025 (RLHV) | PO# 2020010025 (RLHV) | PO# 2020010025 (RLHV)
[7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: | 2019-12-06 | Date completed:
Date Started:
Rehab. Of Evacuation Center, Libuak, IGCS |  | 20% DF CY 2019 (STIMULUS | Building |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | For implementation | For implementation | For implementation | For implementation | For implementation | For implementation
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: | 2019-05-29 | Date completed:
Date Started:
Electrification at Sitio Trinidad, Bandera, IGCS |  | 20% DF CY 2019 (STIMULUS | Electrification |  |  | Contract | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | PO #2020072352 - (3E Electrical Sales & Services) | PO #2020072352 - (3E Electrical Sales & Services) | Re-bid due to non-compliance in requirement | Re-bid due to non-compliance in requirement | Re-bid due to non-compliance in requirement | Re-bid due to non-compliance in requirement
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: | 2019-03-25 | Date completed:
Date Started:
Electrificatio at Prk. 1,3,4, 6,7 & 8, Licup, IGCS |  | 20% DF CY 2019 (STIMULUS | Electrification |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | For implementation | For implementation | For implementation | For implementation | For implementation | For implementation
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: | 2019-02-20 | Date completed:
Date Started:
Rehab. Of Potable Water System, San Isidro, Babak, IGCS |  | 20% DF CY 2019 (STIMULUS | Water System |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | For implementation | For implementation | For implementation | For implementation | For implementation | For implementation
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: | 2019-06-19 | Date completed:
Date Started:
Rehab. Of Potable Water System, San Miguel, IGCS |  | 20% DF CY 2019 (STIMULUS | Water System |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | For implementation | For implementation | For implementation | For implementation | For implementation | For implementation
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: | 2019-02-28 | Date completed:
Date Started:
Const. of Water System Ph.II, San Remegio, IGCS |  | 20% DF CY 2019 (STIMULUS | Water System |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | For implementation | For implementation | For implementation | For implementation | For implementation | For implementation
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: | 2019-05-29 | Date completed:
Date Started:
Rehabilitation of Potable Water System, Brgy. Pangubatan, kaputian Dist. IGCS |  | 20% DF CY 2019 | Water System |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | For implementation | Declared as savings in the AIP 2nd Revision to fund for the Construction of PWS in Brgy Linusotan, Kaputian Dist. IGACOS (Project was funded by OPAPP CY 2018) | Declared as savings in the AIP 2nd Revision to fund for the Construction of PWS in Brgy Linusotan, Kaputian Dist. IGACOS (Project was funded by OPAPP CY 2018) | Declared as savings in the AIP 2nd Revision to fund for the Construction of PWS in Brgy Linusotan, Kaputian Dist. IGACOS (Project was funded by OPAPP CY 2018) | Declared as savings in the AIP 2nd Revision to fund for the Construction of PWS in Brgy Linusotan, Kaputian Dist. IGACOS (Project was funded by OPAPP CY 2018) | Declared as savings in the AIP 2nd Revision to fund for the Construction of PWS in Brgy Linusotan, Kaputian Dist. IGACOS (Project was funded by OPAPP CY 2018)
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Rural Electrification at Brgy. Poblacion, Kaputian, IGACOS ( Sitio Sagrada) |  | 20% DF CY 2019 | Electrification |  |  |  | Project Cost: | 1000000 | Target Completion Date: |  | Program: | 1000000 | Planned: | 43% | Planned: | 43% | Planned: | 43% | Planned: | 43% | Planned: |  | No. of Persons: |  | On-going | On-going | On-going | On-going | On-going | For implementation
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 1000000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: | 43% | Actual: | 43% | Actual: | 43% | Actual: | 43% | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Const. Of Multi-Purpose Hall, Cogon (Talicud), IGCS |  | 20% DF CY 2019 (STIMULUS | Building |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | For implementation | For implementation | For implementation | For implementation | For implementation | For implementation
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Rehab. Of Multi-Purpose Hall, Del Monte, IGCS |  | 20% DF CY 2019 (STIMULUS | Building |  |  | Admin | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Pending/ activity undertaken by DPWH | Pending/ activity undertaken by DPWH | Pending/ activity undertaken by DPWH | Pending/ activity undertaken by DPWH | Pending/ activity undertaken by DPWH | Pending/ activity undertaken by DPWH
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: | 2019-05-29 | Date completed:
Date Started:
Rehab. Of Health Center, New Visayas, Panabo City |  | 20% DF CY 2019 (STIMULUS | Building |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Re aligned to other stimulus projects that needs additional funding | Re aligned to other stimulus projects that needs additional funding | Re aligned to other stimulus projects that needs additional funding | Re aligned to other stimulus projects that needs additional funding | Re aligned to other stimulus projects that needs additional funding | Re aligned to other stimulus projects that needs additional funding
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Purchase of Lot Cemetery, San Roque, New Corella |  | SB No. 1 CY 2019 (STIMULUS) | Land |  |  |  | Project Cost: | 1500000 | Target Completion Date: |  | Program: | 1500000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | for fund transfer. Waiting for LGU documents. Liquidation of previous fund transfer for the water system project of LGU. | for fund transfer. Waiting for LGU documents. Liquidation of previous fund transfer for the water system project of LGU. | for fund transfer. Waiting for LGU documents. Liquidation of previous fund transfer for the water system project of LGU. | for fund transfer. Waiting for LGU documents. Liquidation of previous fund transfer for the water system project of LGU. | for fund transfer. Waiting for LGU documents. Liquidation of previous fund transfer for the water system project of LGU. | Lot already purchased by Brgy. San Roque, New Corella. For ammendment for new project of the same location. Resolution already submitted by Brgy. San Roque; Energization of Purok-3 Sitio Libas, Brgy. San Roque. POW preparation ongoing.
[7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 1500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Purchase of Lot Cemetery, Cambanogoy, Asuncion |  | SB No. 1 CY 2019 (STIMULUS) | Land |  |  |  | Project Cost: | 1500000 | Target Completion Date: |  | Program: | 1500000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | for fund transfer. Waiting for LGU documents. Liquidation of previous fund transfer for the water system project of LGU. | for fund transfer. Waiting for LGU documents. Liquidation of previous fund transfer for the water system project of LGU. | for fund transfer. Waiting for LGU documents. Liquidation of previous fund transfer for the water system project of LGU. | for fund transfer. Waiting for LGU documents. Liquidation of previous fund transfer for the water system project of LGU. | for fund transfer. Waiting for LGU documents. Liquidation of previous fund transfer for the water system project of LGU. | Documents for the fund transfer to be complied by the LGUs. Letter sent dated June 18, 2019 Follow up for the requirements last July 20, 2020
[7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 1500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Const. of FMR from Prk 1 to Sitio Magsaysay via Pundol & Prk 4, Patrocenio, New Corella |  | SB NO. 1 CY 2019 (STIMULUS) | Road |  |  |  | Project Cost: | 2000000 | Target Completion Date: |  | Program: | 2000000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
[7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 2000000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Const. of Drainage Canal from Prk. 3, 1-A, 2-A to Prk 1-B, Brgy Site (Ph. 2), Limbaan, New Corella |  | SB NO. 1 CY 2019 (STIMULUS) | Flood Control - Drainage |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | POW preparation on going c/o PDPM | POW preparation on going c/o PDPM | Abstract on Process Contractor: Royal Summit Infinity Dev't. Corp. | For implementation | For implementation | For implementation
[7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: | Royal Summit Infinity | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Const. of 2 Storey Multi-Purpose Hall Ph. 1 (Brgy. Hall), Poblacion, New Corella |  | SB No. 1 CY 2019 (STIMULUS) | Building |  | sq.m | Admin | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: | 100% | Planned: | 100% | Planned: | 100% | Planned: |  | Planned: |  | No. of Persons: |  | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1 | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1 | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: | 100% | Actual: | 100% | Actual: | 100% | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage:
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Impv't. of Potable Water System, Mambago-A, IGCS |  | SB NO. 3 CY 2019 | Water System |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | For Implementation | For Implementation | For Implementation | For Implementation | For Implementation | For Implementation
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: | 2019-09-10 | Date completed:
Date Started:
Construction of PWS, Brgy. Linusotan, Talikud, District, IGCS |  | SB NO. 3 CY 2019 | Water System |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Procurement on process | Procurement on process | Procurement on process | Procurement on process | Procurement on process | Procurement on process
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: | 2019-10-23 | Date completed:
Date Started:
Const. of Brgy. Health Center, Magugpo South, Tagum City |  | SB No. 4 CY 2019 (STIMULUS) | Building |  |  |  | Project Cost: | 1550000 | Target Completion Date: |  | Program: | 1550000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Amended in the AIP 3rd revision CY 2019 /SB No. 4 CY 2019 changing the total project cost to P1,550,000.00 | For implementation (Awarded to Royal Summit Infinity Dev't. Corp.), ; (Note: Additional Fund Php P1,050,000.00) | For implementation (Awarded to Royal Summit Infinity Dev't. Corp.), ; (Note: Additional Fund Php P1,050,000.00) | For implementation (Awarded to Royal Summit Infinity Dev't. Corp.), ; (Note: Additional Fund Php P1,050,000.00) | For implementation (Awarded to Royal Summit Infinity Dev't. Corp.), ; (Note: Additional Fund Php P1,050,000.00) | For implementation (Awarded to Royal Summit Infinity Dev't. Corp.), ; (Note: Additional Fund Php P1,050,000.00)
[7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 1550000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Completion of Brgy. Health Center, Maniki, Kapalong |  | SB No. 4 CY 2019 (STIMULUS) | Building |  |  |  | Project Cost: | 627000 | Target Completion Date: |  | Program: | 627000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | PROJECT Was funded by LGU, Kapalong | PROJECT Was funded by LGU, Kapalong | PROJECT Was funded by LGU, Kapalong | For amendment.To submit a new resolution for another priority project which is the Const. of Multi-Purpose Pavement but the propose site is not is donated because the previous project Completion of Brgy. Health Center was funded by the LGU of Kapalong | For amendment.To submit a new resolution for another priority project which is the Const. of Multi-Purpose Pavement but the propose site is not is donated because the previous project Completion of Brgy. Health Center was funded by the LGU of Kapalong | For amendment.To submit a new resolution for another priority project which is the Const. of Multi-Purpose Pavement but the propose site is not is donated because the previous project Completion of Brgy. Health Center was funded by the LGU of Kapalong
[7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 627000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Construction of Potable Water System at Purok 6, New Santiago, Asuncion |  | SB No. 4 CY 2019 (STIMULUS) | Water System |  |  | contract | Project Cost: | 1000000 | Target Completion Date: |  | Program: | 1000000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Change of POW to Contract Procurement on process ( Amended in AIP 3rd revision CY 2019 increasing the amount to complete the project For plan preparation c/o Amamio) Additional fund Php 500,000 | Procurement on process ( Amended in AIP 3rd revision CY 2019 increasing the amount to complete the project For plan preparation c/o Amamio) Additional fund Php 500,000 | Awarded to Two Degrees Construction & Supply | Awarded to Two Degrees Construction & Supply | Awarded to Two Degrees Construction & Supply | Awarded to Two Degrees Construction & Supply
[7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 1000000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Desilting and Concreting of Drainage-Main Collector Canal, New Casay, B.E. Dujali |  | SB # 4 CY 2019 (STIMULUS | Desiltation |  |  | Contract | Project Cost: | 650000 | Target Completion Date: | 0 | Program: | 650000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 650000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: |  | Slippage: |  | Slippage:
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Rehab. Of Multi-Purpose Building (Evacuation Center), Limbaan, New Corella |  | SB NO. 4 CY 2019 (STIMULUS) | Building |  |  |  | Project Cost: | 600000 | Target Completion Date: |  | Program: | 600000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | From SB # 1 to SB # 4 CY 2019 (Transfer to Contract) Procurement on process | From SB # 1 to SB # 4 CY 2019 (Transfer to Contract) Procurement on process | From SB # 1 to SB # 4 CY 2019 (Transfer to Contract) Procurement on process |  |  | From SB # 1 to SB # 4 CY 2019 (Transfer to Contract) Procurement on process
[7 empty] | Project Engineer: |  | Revised Completion Date: | 0 | Allotment: | 600000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Rehabilitation of Multi-Purpose Hall, Pantaron, Sto. Tomas |  | SB # 4 CY 2019 (STIMULUS | Building |  |  |  | Project Cost: | 550000 | Target Completion Date: |  | Program: | 550000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | For implementation | For implementation | For implementation | For implementation | For implementation | For implementation
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 550000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Rehabilitation of Multi-Purpose Hall, Salvacion, Sto. Tomas |  | SB # 4 CY 2019 (STIMULUS | Building |  |  |  | Project Cost: | 1000000 | Target Completion Date: |  | Program: | 1000000 | Planned: |  | Planned: |  | Planned: |  | Planned: | 100% | Planned: | 100% | No. of Persons: |  | PR #20032281 | PR #20032281 | PR #20032281 | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 1000000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: | 100% | Actual: | 100%
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Rehabilitation of Multi-Purpose Bldg. (Brgy. Hall) Tagpopongan, IGACOS |  | SB # 4 CY 2019 (STIMULUS | Building |  |  |  | Project Cost: | 174460.33 | Target Completion Date: |  | Program: | 174460.33 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Procurement on process | Procurement on process | Procurement on process |  |  | Procurement on process
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 174460.33 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Construction of Water System Project, Poblacion Kaputian, Samal |  | SB # 4 CY 2019 (20% DF -STIMULUS) | Water System |  |  | Contract | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | For implementation | For implementation | For implementation | For implementation | For implementation | For implementation
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Rehab. Of Multi-Purpose Hall, New Malitbog, Panabo City |  | SB # 4 CY 2019 (STIMULUS) | Building |  |  |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Amended in AIP 3rd revsion CY 2019 to change the project to Construction of Potable Water System because the original project will be funded by LGU, Panabo City (Brgy. resolution no. 25 series of 2019 dated Aug. 13, 2019 submitted) | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Rehabilitation of Local Roads at Dalisay-Manay Road Section, Panabo City |  | SB NO. 4 CY 2019 | Road |  |  | Admin | Project Cost: | 246100 | Target Completion Date: |  | Program: | 246100 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | For implementation | For implementation | For implementation | For implementation | For implementation | For implementation
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 246100 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Rehabilitation of Local Roads at Sta. Cruz-Jct. Tagpore-Buenavista Raod Section, Panabo City |  | SB NO. 4 CY 2019 | Road |  |  | Admin | Project Cost: | 431000 | Target Completion Date: |  | Program: | 431000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | For implementation | For implementation | For implementation | For implementation | For implementation | For implementation
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 431000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Rehabilitation of Local Roads at Taba-Bucana Road Section, Taba, Carmen |  | SB # 4 CY 2019 | Road |  |  | Admin | Project Cost: | 220000 | Target Completion Date: |  | Program: | 220000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | For implementation | For implementation | For implementation | For implementation | For implementation | For implementation
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 220000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Rehab. Of Canal Lining and Slope Protection at San Agustin E/S, San Agustin, Tagum City |  | SB NO. 4 FUND CY 2019 | Road |  | km | Admin | Project Cost: | 350000 | Target Completion Date: |  | Program: | 350000 | Planned: | 81.11% | Planned: | 81.11% | Planned: | 81.11% | Planned: | 81.11% | Planned: |  | No. of Persons: |  | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | For verification
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 350000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: | 81.11% | Actual: | 81.11% | Actual: | 81.11% | Actual: | 81.11% | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Desilting of Limbaan Creek, New Corella |  | 5% CALAMITY FUND CY 2019 | creeks and canals deislted |  | ln.m | Admin | Project Cost: | 2000000 | Target Completion Date: | 2019-12-02 | Program: | 2000000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Suspended | Suspended | Suspended | Suspended | Suspended | Suspended
[7 empty] | Project Engineer: | Pilotos | Revised Completion Date: | 2019-12-02 | Allotment: | 2000000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: | 257 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
[7 empty] | Date Started: | 2019-03-20
Impv't. of Jct. New Boholano - New Loon Cross Drainage |  | 5% CALAMITY FUND CY 2019 | Drainage |  | km | Admin | Project Cost: | 2000000 | Target Completion Date: | 2020-02-16 | Program: | 2000000 | Planned: | 42.27% | Planned: | 42.27% | Planned: | 42.27% | Planned: | 42.27% | Planned: | 70% | No. of Persons: |  | Suspended due to availability of equipment | Suspended due to availability of equipment | Suspended due to availability of equipment | Suspended due to availability of equipment | Suspended due to availability of equipment | On-going
[7 empty] | Project Engineer: | Pilotos | Revised Completion Date: | 2020-02-16 | Allotment: | 2000000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: | 31.7% | Actual: | 31.7% | Actual: | 31.7% | Actual: | 31.7% | Actual: | 70%
[7 empty] | Duration: | 90 | No. of days extended: |  |  |  | Slippage: | -10.57% | Slippage: | -10.57% | Slippage: | -10.57% | Slippage: | -10.57% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
[7 empty] | Date Started: | 2019-11-18
Construction of Evacuation Facility (Const. of Multi-Purpose/Evacuation Center), New Corella |  | PCF CY 2019 | Road |  | km | Contract | Project Cost: | 2500000 | Target Completion Date: | 0 | Program: | 53991806 | Planned: | [7 empty] | No. of Persons: |  | No. of Persons: |  | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Procurement on process
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 53991806 | Revised: | [7 empty] | No. of Man-days: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage:
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
ROAD ID 002 - Magatos - Bdry. Pagsabangan |  | GENERAL FUND CY 2020 | Maintenance | 8.33 | km | CBRMC | Project Cost: | 280180.88 | Target Completion Date: |  | Program: | 280180.88 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Purchase Request # 19125306 (On process) | Purchase Request # 19125306 (On process) | Purchase Request # 19125306 (On process) | Purchase Request # 19125306 (On process) | Purchase Request # 19125306 (On process) | Procurement on process
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 280180.88 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
ROAD ID 003 - Ilog - New Bantayan |  | GENERAL FUND CY 2020 | Maintenance | 2.68 | km | CBRMC | Project Cost: | 70633.836 | Target Completion Date: |  | Program: | 70633.836 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Purchase Request # 19125307 (On process) | Purchase Request # 19125307 (On process) | Purchase Request # 19125307 (On process) | Purchase Request # 19125307 (On process) | Purchase Request # 19125307 (On process) | Procurement on process
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 70633.836 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
ROAD ID 005 - Asuncion - Monte Carlo - Del Pilar |  | GENERAL FUND CY 2020 | Maintenance | 9.93 | km | CBRMC | Project Cost: | 360232.5636 | Target Completion Date: |  | Program: | 360232.5636 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Awarded to Mahayahay Integrated Farmers Association | Awarded to Mahayahay Integrated Farmers Association | Awarded to Mahayahay Integrated Farmers Association | Awarded to Mahayahay Integrated Farmers Association | Awarded to Mahayahay Integrated Farmers Association | For implementation
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 360232.5636 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
ROAD ID 006 - Jct. Highway Canatan - Magatos |  | GENERAL FUND CY 2020 | Maintenance | 4.85 | km | CBRMC | Project Cost: | 164812.284 | Target Completion Date: |  | Program: | 164812.284 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Purchase Request # 19125309 (On process) | Purchase Request # 19125309 (On process) | Purchase Request # 19125309 (On process) | Purchase Request # 19125309 (On process) | Purchase Request # 19125309 (On process) | Procurement on process
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 164812.284 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
ROAD ID 010 - Saug - Sonlon - Bdry. Longanapan |  | GENERAL FUND CY 2020 | Maintenance | 11.6 | km | CBRMC | Project Cost: | 197774.7408 | Target Completion Date: |  | Program: | 197774.7408 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Purchase Request # 19125310 (On process) | Purchase Request # 19125310 (On process) | Purchase Request # 19125310 (On process) | Purchase Request # 19125310 (On process) | Purchase Request # 19125310 (On process) | Procurement on process
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 197774.7408 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
ROAD ID 011 - Jct. New Visayas - Buan |  | GENERAL FUND CY 2020 | Maintenance | 2.99 | km | CBRMC | Project Cost: | 124786.4436 | Target Completion Date: |  | Program: | 124786.4436 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Purchase Request # 19125311 (On process) | Purchase Request # 19125311 (On process) | Purchase Request # 19125311 (On process) | Purchase Request # 19125311 (On process) | Purchase Request # 19125311 (On process) | Procurement on process
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 124786.4436 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
ROAD ID 013 - San Vicente - Butay |  | GENERAL FUND CY 2020 | Maintenance | 7.52 | km | CBRMC | Project Cost: | 235446.12 | Target Completion Date: |  | Program: | 235446.12 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Purchase Request # 19125312 (On process) | Purchase Request # 19125312 (On process) | Purchase Request # 19125312 (On process) | Purchase Request # 19125312 (On process) | Purchase Request # 19125312 (On process) | Procurement on process
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 235446.12 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
ROAD ID 014 - Jct. Highway Doña Andrea - Capungagan |  | GENERAL FUND CY 2020 | Maintenance | 8.7 | km | CBRMC | Project Cost: | 299016.5724 | Target Completion Date: |  | Program: | 299016.5724 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Purchase Request # 19125313 (On process) | Purchase Request # 19125313 (On process) | Purchase Request # 19125313 (On process) | Purchase Request # 19125313 (On process) | Purchase Request # 19125313 (On process) | Procurement on process
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 299016.5724 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
ROAD ID 015 - Pamacaun - Lasang - Banate |  | GENERAL FUND CY 2020 | Maintenance | 4.11 | km | CBRMC | Project Cost: | 129495.366 | Target Completion Date: |  | Program: | 129495.366 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Purchase Request # 19125314 (On process) | Purchase Request # 19125314 (On process) | Purchase Request # 19125314 (On process) | Purchase Request # 19125314 (On process) | Purchase Request # 19125314 (On process) | Procurement on process
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 129495.366 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
ROAD ID 018 - Semong - Palma Gil |  | GENERAL FUND CY 2020 | Maintenance | 2.73 | km | CBRMC | Project Cost: | 77697.2196 | Target Completion Date: |  | Program: | 77697.2196 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Purchase Request # 19125315 (On process) | Purchase Request # 19125315 (On process) | Purchase Request # 19125315 (On process) | Purchase Request # 19125315 (On process) | Purchase Request # 19125315 (On process) | Procurement on process
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 77697.2196 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
ROAD ID 020 - Daligdigon-Dagohoy |  | GENERAL FUND CY 2020 | Maintenance | 3.34 | km | CBRMC | Project Cost: | 77697.2196 | Target Completion Date: |  | Program: | 77697.2196 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Purchase Request # 19125315 (On process) | Purchase Request # 19125315 (On process) | Purchase Request # 19125315 (On process) | Purchase Request # 19125315 (On process) | Purchase Request # 19125315 (On process) | Procurement on process
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 77697.2196 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
ROAD ID 021 - Angelo - Dagohoy |  | GENERAL FUND CY 2020 | Maintenance | 2.19 | km | CBRMC | Project Cost: | 40025.8404 | Target Completion Date: |  | Program: | 40025.8404 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Purchase Request # 19125317 (On process) | Purchase Request # 19125317 (On process) | Purchase Request # 19125317 (On process) | Purchase Request # 19125317 (On process) | Purchase Request # 19125317 (On process) | Procurement on process
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 40025.8404 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
ROAD ID 025 - Jct. Sampao - Bdry. Mamacao |  | GENERAL FUND CY 2020 | Maintenance | 4.98 | km | CBRMC | Project Cost: | 178939.0512 | Target Completion Date: |  | Program: | 178939.0512 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Purchase Request # 19125318 (On process) | Purchase Request # 19125318 (On process) | Purchase Request # 19125318 (On process) | Purchase Request # 19125318 (On process) | Purchase Request # 19125318 (On process) | Procurement on process
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 178939.0512 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
ROAD ID 026 - Jct. Highway - Luna - Mamacao - Narra |  | GENERAL FUND CY 2020 | Maintenance | 9.17 | km | CBRMC | Project Cost: | 393195.0204 | Target Completion Date: |  | Program: | 393195.0204 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Purchase Request # 19125337 (On process) | Purchase Request # 19125337 (On process) | Purchase Request # 19125337 (On process) | Purchase Request # 19125337 (On process) | Purchase Request # 19125337 (On process) | Procurement on process
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 393195.0204 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
ROAD ID 027 - Jct. Gabuyan - Katipunan - Bucana |  | GENERAL FUND CY 2020 | Maintenance | 5.89 | km | CBRMC | Project Cost: | 174230.1288 | Target Completion Date: |  | Program: | 174230.1288 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Purchase Request # 19125338 (On process) | Purchase Request # 19125338 (On process) | Purchase Request # 19125338 (On process) | Purchase Request # 19125338 (On process) | Purchase Request # 19125338 (On process) | Procurement on process
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 174230.1288 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
ROAD ID 028 - Capungagan - Mabuhay - Pandulian |  | GENERAL FUND CY 2020 | Maintenance | 5.57 | km | CBRMC | Project Cost: | 155394.4392 | Target Completion Date: |  | Program: | 155394.4392 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Procurement on process | Purchase Request # 19125339 (On process) | Purchase Request # 19125339 (On process) | Purchase Request # 19125339 (On process) | Purchase Request # 19125339 (On process) | Procurement on process
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 155394.4392 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
ROAD ID 034 - Km. 15, Kipalili - New Loon |  | GENERAL FUND CY 2020 | Maintenance | 6.93 | km | CBRMC | Project Cost: | 296662.1112 | Target Completion Date: |  | Program: | 296662.1112 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Procurement on process | Purchase Request # 19125340 (On process) | Purchase Request # 19125340 (On process) | Purchase Request # 19125340 (On process) | Purchase Request # 19125340 (On process) | Procurement on process
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 296662.1112 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
ROAD ID 035 - Jct. Suaon - Libuton |  | GENERAL FUND CY 2020 | Maintenance | 7.26 | km | CBRMC | Project Cost: | 96532.9092 | Target Completion Date: |  | Program: | 96532.9092 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Awarded to Association of Alternative Livelihood of Libuton Inc. | Awarded to Association of Alternative Livelihood of Libuton Inc. | Awarded to Association of Alternative Livelihood of Libuton Inc. | Awarded to Association of Alternative Livelihood of Libuton Inc. | Awarded to Association of Alternative Livelihood of Libuton Inc. | Procurement on process
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 96532.9092 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
ROAD ID 037 - Monte Dujali - Gupitan |  | GENERAL FUND CY 2020 | Maintenance | 4.58 | km | CBRMC | Project Cost: | 134204.2884 | Target Completion Date: |  | Program: | 134204.2884 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Awarded to Association of Alternative Livelihood of Libuton Inc. | Awarded to Association of Alternative Livelihood of Libuton Inc. | Awarded to Association of Alternative Livelihood of Libuton Inc. | Awarded to Association of Alternative Livelihood of Libuton Inc. | Awarded to Association of Alternative Livelihood of Libuton Inc. | Procurement on process
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 134204.2884 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
ROAD ID 041 - Sawata - Mamangan - Pinamuno |  | GENERAL FUND CY 2020 | Maintenance | 14.48 | km | CBRMC | Project Cost: | 522690.3864 | Target Completion Date: |  | Program: | 522690.3864 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Procurement on process | Purchase Request # 19125343 (On process) | Purchase Request # 19125343 (On process) | Purchase Request # 19125343 (On process) | Purchase Request # 19125343 (On process) | Procurement on process
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 522690.3864 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
ROAD ID 042 - Igangon - Sawata |  | GENERAL FUND CY 2020 | Maintenance | 9.66 | km | CBRMC | Project Cost: | 202483.6632 | Target Completion Date: |  | Program: | 202483.6632 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Purchase Request # 19125344 (On process) | Purchase Request # 19125344 (On process) | Purchase Request # 19125344 (On process) | Purchase Request # 19125344 (On process) | Purchase Request # 19125344 (On process) | Procurement on process
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 202483.6632 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
ROAD ID 043 - Jct. Sawata - Bdry. Binasbas |  | GENERAL FUND CY 2020 | Maintenance | 0.46 | km | CBRMC | Project Cost: | 18835.6896 | Target Completion Date: |  | Program: | 18835.6896 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Purchase Request # 19125345 (On process) | Purchase Request # 19125345 (On process) | Purchase Request # 19125345 (On process) | Purchase Request # 19125345 (On process) | Purchase Request # 19125345 (On process) | Procurement on process
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 18835.6896 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
ROAD ID 045 - Tagaytay - Buan |  | GENERAL FUND CY 2020 | Maintenance | 4.92 | km | CBRMC | Project Cost: | 174230.1288 | Target Completion Date: |  | Program: | 174230.1288 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Purchase Request # 19125346 (On process) | Purchase Request # 19125346 (On process) | Purchase Request # 19125346 (On process) | Purchase Request # 19125346 (On process) | Purchase Request # 19125346 (On process) | Procurement on process
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 174230.1288 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
ROAD ID 049 - Limbaan - Sto. Niño |  | GENERAL FUND CY 2020 | Maintenance | 3.19 | km | CBRMC | Project Cost: | 127140.9048 | Target Completion Date: |  | Program: | 127140.9048 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Procurement on process | Purchase Request # 20010072 (On process) | Purchase Request # 20010072 (On process) | Purchase Request # 20010072 (On process) | Purchase Request # 20010072 (On process) | Procurement on process
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 127140.9048 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
ROAD ID 050 - Jct. Monte Carlo - Upper Cabaywa - Canatan |  | GENERAL FUND CY 2020 | Maintenance | 4.61 | km | CBRMC | Project Cost: | 197774.7408 | Target Completion Date: |  | Program: | 197774.7408 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Procurement on process | Purchase Request # 20010074 (On process) | Purchase Request # 20010074 (On process) | Purchase Request # 20010074 (On process) | Purchase Request # 20010074 (On process) | Procurement on process
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 197774.7408 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
ROAD ID 051 - Del Pilar - Jct. Silangan |  | GENERAL FUND CY 2020 | Maintenance | 4.17 | km | CBRMC | Project Cost: | 129495.366 | Target Completion Date: |  | Program: | 129495.366 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Procurement on process | Purchase Request # 20010093 (On process) | Purchase Request # 20010093 (On process) | Purchase Request # 20010093 (On process) | Purchase Request # 20010093 (On process) | Procurement on process
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 129495.366 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
ROAD ID 052 - New Corella - New Sambog - Silangan |  | GENERAL FUND CY 2020 | Maintenance | 5.1 | km | CBRMC | Project Cost: | 148331.0556 | Target Completion Date: |  | Program: | 148331.0556 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Purchase Request # 20010095 (On process) | Purchase Request # 20010095 (On process) | Purchase Request # 20010095 (On process) | Purchase Request # 20010095 (On process) | Purchase Request # 20010095 (On process) | Procurement on process
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 148331.0556 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
ROAD ID 053 - Pob. New Corella - Prk. 10 Pob. |  | GENERAL FUND CY 2020 | Maintenance | 1.3 | km | CBRMC | Project Cost: | 21190.1508 | Target Completion Date: |  | Program: | 21190.1508 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Awarded to Carcor Motor Driver's Association | Awarded to Carcor Motor Driver's Association | Awarded to Carcor Motor Driver's Association | Awarded to Carcor Motor Driver's Association | Awarded to Carcor Motor Driver's Association | Procurement on process
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 21190.1508 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
ROAD ID 054 - Prk. 7 Pob. - Jct. New Sambog |  | GENERAL FUND CY 2020 | Maintenance | 2.54 | km | CBRMC | Project Cost: | 113014.1376 | Target Completion Date: |  | Program: | 113014.1376 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Awarded to Carcor Motor Driver's Association | Awarded to Carcor Motor Driver's Association | Awarded to Carcor Motor Driver's Association | Awarded to Carcor Motor Driver's Association | Awarded to Carcor Motor Driver's Association | Procurement on process
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 113014.1376 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
ROAD ID 056 - Sta. Fe - Del Monte |  | GENERAL FUND CY 2020 | Maintenance | 3.34 | km | CBRMC | Project Cost: | 75342.7584 | Target Completion Date: |  | Program: | 75342.7584 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Purchase Request # 20010160 (On process) | Purchase Request # 20010160 (On process) | Purchase Request # 20010160 (On process) | Purchase Request # 20010160 (On process) | Purchase Request # 20010160 (On process) | Procurement on process
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 75342.7584 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
ROAD ID 058 - New Corella - New Bohol |  | GENERAL FUND CY 2020 | Maintenance | 11.54 | km | CBRMC | Project Cost: | 221319.3528 | Target Completion Date: |  | Program: | 221319.3528 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Awarded to Carcor Motor Driver's Association | Awarded to Carcor Motor Driver's Association | Awarded to Carcor Motor Driver's Association | Awarded to Carcor Motor Driver's Association | Awarded to Carcor Motor Driver's Association | For implementation
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 221319.3528 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
ROAD ID 059 - Jct. Carcor - Prk. 9 Bagsak |  | GENERAL FUND CY 2020 | Maintenance | 2.5 | km | CBRMC | Project Cost: | 72988.2972 | Target Completion Date: |  | Program: | 72988.2972 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Awarded to Carcor Motor Driver's Association | Awarded to Carcor Motor Driver's Association | Awarded to Carcor Motor Driver's Association | Awarded to Carcor Motor Driver's Association | Awarded to Carcor Motor Driver's Association | For implementation Carcor Motor Driver's Association
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 72988.2972 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
ROAD ID 060 - Carcor - Jct. Kauswagan |  | GENERAL FUND CY 2020 | Maintenance | 4.32 | km | CBRMC | Project Cost: | 101241.8316 | Target Completion Date: |  | Program: | 101241.8316 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Awarded to Carcor Motor Driver's Association | Awarded to Carcor Motor Driver's Association | Awarded to Carcor Motor Driver's Association | Awarded to Carcor Motor Driver's Association | Awarded to Carcor Motor Driver's Association | For implementation Carcor Motor Driver's Association
[7 empty] | Project Engineer: | Fabian | Revised Completion Date: |  | Allotment: | 101241.8316 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
ROAD ID 061 - Del Pilar - Prk. 9 Bagsak - San Jose |  | GENERAL FUND CY 2020 | Maintenance |  | km | CBRMC | Project Cost: | 251927.3484 | Target Completion Date: |  | Program: | 251927.3484 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Purchase Request # 20010264 (On process) | Purchase Request # 20010264 (On process) | Purchase Request # 20010264 (On process) | Purchase Request # 20010264 (On process) | Purchase Request # 20010264 (On process) | Procurement on process
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 251927.3484 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
ROAD ID 062 - Del Pilar - El Unido |  | GENERAL FUND CY 2020 | Maintenance | 1.32 | km | CBRMC | Project Cost: | 40025.8404 | Target Completion Date: |  | Program: | 40025.8404 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Purchase Request # 20010265 (On process) | Purchase Request # 20010265 (On process) | Purchase Request # 20010265 (On process) | Purchase Request # 20010265 (On process) | Purchase Request # 20010265 (On process) | Procurement on process
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 40025.8404 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
ROAD ID 063 - San Juan - New Talisay |  | GENERAL FUND CY 2020 | Maintenance | 5.13 | km | CBRMC | Project Cost: | 131849.8272 | Target Completion Date: |  | Program: | 131849.8272 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Awarded to Mahayahay Integrated Farmers Association | Awarded to Mahayahay Integrated Farmers Association | Awarded to Mahayahay Integrated Farmers Association | Awarded to Mahayahay Integrated Farmers Association | Awarded to Mahayahay Integrated Farmers Association | Awarded to Mahayahay Integrated Farmers Association
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 131849.8272 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
ROAD ID 064 - San Juan - Kauswagan - New Cortez |  | GENERAL FUND CY 2020 | Maintenance | 3.22 | km | CBRMC | Project Cost: | 68279.3748 | Target Completion Date: |  | Program: | 68279.3748 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Procurement on process | Procurement on process | Procurement on process | Procurement on process | Procurement on process | Procurement on process
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 68279.3748 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
ROAD ID 065 - New Bohol - Jct. El Unido |  | GENERAL FUND CY 2020 | Maintenance | 2.12 | km | CBRMC | Project Cost: | 65924.9136 | Target Completion Date: |  | Program: | 65924.9136 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Purchase Request # 20010275 (On process) | Purchase Request # 20010275 (On process) | Purchase Request # 20010275 (On process) | Purchase Request # 20010275 (On process) | Purchase Request # 20010275 (On process) | Procurement on process
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 65924.9136 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
ROAD ID 066 - New Corella - El Unido - Jct. Mesaoy |  | GENERAL FUND CY 2020 | Maintenance | 8.63 | km | CBRMC | Project Cost: | 249572.8872 | Target Completion Date: |  | Program: | 249572.8872 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Purchase Request # 20010291 (On process) | Purchase Request # 20010291 (On process) | Purchase Request # 20010291 (On process) | Purchase Request # 20010291 (On process) | Purchase Request # 20010291 (On process) | Procurement on process
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 249572.8872 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
ROAD ID 067 - Mesaoy - Dasing |  | GENERAL FUND CY 2020 | Maintenance | 1.39 | km | CBRMC | Project Cost: | 54152.6076 | Target Completion Date: |  | Program: | 54152.6076 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Purchase Request # 20010294 (On process) | Purchase Request # 20010294 (On process) | Purchase Request # 20010294 (On process) | Purchase Request # 20010294 (On process) | Purchase Request # 20010294 (On process) | Procurement on process
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 54152.6076 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
ROAD ID 068 - Jct. San Juan - Jct. Mesaoy |  | GENERAL FUND CY 2020 | Maintenance | 1.82 | km | CBRMC | Project Cost: | 68279.3748 | Target Completion Date: |  | Program: | 68279.3748 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Awarded to Mahayahay Integrated Farmers Association | Awarded to Mahayahay Integrated Farmers Association | Awarded to Mahayahay Integrated Farmers Association | Awarded to Mahayahay Integrated Farmers Association | Awarded to Mahayahay Integrated Farmers Association | Procurement on process
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 68279.3748 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
ROAD ID 070 - Mesaoy - New Bohol |  | GENERAL FUND CY 2020 | Maintenance | 5.36 | km | CBRMC | Project Cost: | 261345.1932 | Target Completion Date: |  | Program: | 261345.1932 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Purchase Request # 20010298 (On process) | Purchase Request # 20010298 (On process) | Purchase Request # 20010298 (On process) | Purchase Request # 20010298 (On process) | Purchase Request # 20010298 (On process) | Procurement on process
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 261345.1932 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
ROAD ID 147 - Prk. 1, Maunlom-Prk. 6 Maunlom Road |  | GENERAL FUND CY 2020 | Maintenance | 3.56 | km | CBRMC | Project Cost: | 65924.9136 | Target Completion Date: |  | Program: | 65924.9136 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Purchase Request # 20010302 (On process) | Purchase Request # 20010302 (On process) | Purchase Request # 20010302 (On process) | Purchase Request # 20010302 (On process) | Purchase Request # 20010302 (On process) | Procurement on process
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 65924.9136 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
ROAD ID 149 - New Visayas - Binancian |  | GENERAL FUND CY 2020 | Maintenance | 7.77 | km | CBRMC | Project Cost: | 134204.2884 | Target Completion Date: |  | Program: | 134204.2884 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Purchase Request # 20010305 (On process) | Purchase Request # 20010305 (On process) | Purchase Request # 20010305 (On process) | Purchase Request # 20010305 (On process) | Purchase Request # 20010305 (On process) | Procurement on process
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 134204.2884 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
ROAD ID 150 - Datu Balong - Prk. Mamalian |  | GENERAL FUND CY 2020 | Maintenance | 3.46 | km | CBRMC | Project Cost: | 61215.9912 | Target Completion Date: |  | Program: | 61215.9912 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Purchase Request # 20010306 (On process) | Purchase Request # 20010306 (On process) | Purchase Request # 20010306 (On process) | Purchase Request # 20010306 (On process) | Purchase Request # 20010306 (On process) | Procurement on process
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 61215.9912 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
ROAD ID 008 - Sta. Felomina - San Roque |  | 20% Development Fund CY 2020 | Road Rehabilitaion | 7.68 | km | Admin | Project Cost: | 2304000 | Target Completion Date: |  | Program: | 2304000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Post qualification on process | Post qualification on process | Post qualification on process | Post qualification on process | Post qualification on process | Post qualification on process
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 2304000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
ROAD ID 019 - Sto. Niño - Palma Gil - Sitio Opao |  | 20% Development Fund CY 2020 | Road Rehabilitaion | 5.99 | km | Admin | Project Cost: | 1797000 | Target Completion Date: |  | Program: | 1797000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | POW on process | POW on process | POW on process | POW on process | POW on process | POW on process
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 1797000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
ROAD ID 023 - Sto. Niño - Daligdigon - Paiton |  | 20% Development Fund CY 2020 | Road Rehabilitaion | 11.6 | km | Admin | Project Cost: | 3480000 | Target Completion Date: |  | Program: | 3480000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | POW on process | POW on process | POW on process | POW on process | POW on process | POW on process
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 3480000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
ROAD ID 024 - Jct. Paiton - Mibolo |  | 20% Development Fund CY 2020 | Road Rehabilitaion | 23.9 | km | Admin | Project Cost: | 7170000 | Target Completion Date: |  | Program: | 7170000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | POW on process | POW on process | POW on process | POW on process | POW on process | POW on process
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 7170000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
ROAD ID 024 - Florida - Suaon - Jct. Gupitan |  | 20% Development Fund CY 2020 | Road Rehabilitaion | 15.57 | km | Admin | Project Cost: | 4671000 | Target Completion Date: |  | Program: | 4671000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | PO on process - Royal Summit | PO on process - Royal Summit | PO on process - Royal Summit | PO on process - Royal Summit | PO on process - Royal Summit | PO on process - Royal Summit
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 4671000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
ROAD ID 048 - New Corella - Saug |  | 20% Development Fund CY 2020 | Road Rehabilitaion | 12.52 | km | Admin | Project Cost: | 20571000 | Target Completion Date: |  | Program: | 20571000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | POW on process | POW on process | POW on process | POW on process | POW on process | POW on process
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 20571000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
ROAD ID 074 - Jct. Highway Canatan - Doña Andrea |  | 20% Development Fund CY 2020 | Road Rehabilitaion | 4.34 | km | Admin | Project Cost: | 1302000 | Target Completion Date: |  | Program: | 1302000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | POW on process | POW on process | POW on process | POW on process | POW on process | POW on process
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 1302000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
ROAD ID 030 - Florida - New Boholano |  | 20% Development Fund CY 2020 | Road Rehabilitaion | 2.54 | km | Admin | Project Cost: | 762000 | Target Completion Date: |  | Program: | 762000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | POW on process | POW on process | POW on process | POW on process | POW on process | POW on process
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 762000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
ROAD ID 031 - Jct. New Boholano - New Loon |  | 20% Development Fund CY 2020 | Road Rehabilitaion | 4.77 | km | Admin | Project Cost: | 1431000 | Target Completion Date: |  | Program: | 1431000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | POW on process | POW on process | POW on process | POW on process | POW on process | POW on process
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 1431000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
ROAD ID 071 - Lower Asuncion - Upper Asuncion |  | 20% Development Fund CY 2020 | Road Rehabilitaion |  | km | Admin | Project Cost: | 1302000 | Target Completion Date: |  | Program: | 1302000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Plan On-going | Plan On-going | Plan On-going | Plan On-going | Plan On-going | Plan On-going
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 1302000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
ROAD ID 108 - New Casay - Bugtong Talisay |  | GENERAL FUND CY 2020 | Maintenance |  | km | CBRMC | Project Cost: | 64596.78 | Target Completion Date: |  | Program: | 64596.78 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | For re-bid | For re-bid | For re-bid | For re-bid | For re-bid | Re-bid/ documents on process
[7 empty] | Project Engineer: | Maligro | Revised Completion Date: |  | Allotment: | 64596.78 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
ROAD ID 118- Jct. Salvacion - San Vicente - Cabay-angan |  | GENERAL FUND CY 2020 | Maintenance | 3.45 | km | CBRMC | Project Cost: | 158775.23 | Target Completion Date: |  | Program: | 158775.23 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Abstract #320201396 - For post qualification | Abstract #320201396 - For post qualification | Abstract #320201396 - For post qualification | Abstract #320201396 - For post qualification | Abstract #320201396 - For post qualification | Procurement on process
[7 empty] | Project Engineer: | Maligro | Revised Completion Date: |  | Allotment: | 158775.23 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
ROAD ID 123- Bacali - Casig-ang - Libertad |  | GENERAL FUND CY 2020 | Maintenance |  | km | CBRMC | Project Cost: | 131608.37 | Target Completion Date: |  | Program: | 131608.37 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Abstract #320201449 - For post qualification | Abstract #320201449 - For post qualification | Abstract #320201449 - For post qualification | Abstract #320201449 - For post qualification | Abstract #320201449 - For post qualification | For implementation
[7 empty] | Project Engineer: | Maligro | Revised Completion Date: |  | Allotment: | 131608.37 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
ROAD ID 124 - Kinamayan - Moslog - Mahayag |  | GENERAL FUND CY 2020 | Maintenance |  | km | CBRMC | Project Cost: | 91159.92 | Target Completion Date: |  | Program: | 91159.92 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | For re-bid | For re-bid | For re-bid | For re-bid | For re-bid | Procurement on process
[7 empty] | Project Engineer: | Maligro | Revised Completion Date: |  | Allotment: | 91159.92 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
ROAD ID 007 - Lower Asuncion - Upper Asuncion (Phase I) |  | 20% DF CY 2020 | Rehabilitation |  | km |  | Project Cost: | 1302000 | Target Completion Date: |  | Program: | 1302000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 1302000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
ROAD ID 030 - Jct. Highway - Carmen - Mangalcal - Tubod (Phase I) |  | 20% DF CY 2020 | Rehabilitation |  | km |  | Project Cost: | 1323000 | Target Completion Date: | 2021-02-03 | Program: | 1323000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: | 100% | No. of Persons: | 2 | Plan On-going | Plan On-going | Plan On-going | Plan On-going | Plan On-going | Suspended 10/1/2020
[7 empty] | Project Engineer: | Obar | Revised Completion Date: |  | Allotment: | 1323000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 44
[7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual: | 68.83%
[7 empty] | Duration: | 90 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | -31.17%
[7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
[7 empty] | Date Started: | 2020-06-15
ROAD ID 031 - Tuganay - Taba (Phase I) |  | 20% DF CY 2020 | Rehabilitation |  | km |  | Project Cost: | 507500 | Target Completion Date: | 2020-06-17 | Program: | 507500 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: | 100% | No. of Persons: | 2 | Plan On-going | Plan On-going | Plan On-going | Plan On-going | Plan On-going | Suspended 6/13/2020
[7 empty] | Project Engineer: | Obar | Revised Completion Date: | 2020-08-21 | Allotment: | 507500 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 44
[7 empty] | Implementor: | PEO | No. of days suspended: | 65 | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual: | 68.87%
[7 empty] | Duration: | 30 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | -31.13%
[7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
[7 empty] | Date Started: | 2020-05-18
ROAD ID 069 - Jct. Highway - Ising - Magsaysay (Phase I) |  | 20% DF CY 2020 | Rehabilitation |  | km |  | Project Cost: | 6000000 | Target Completion Date: |  | Program: | 6000000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 6000000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Jct. Highway - Guadalupe - Bdry. Tagum (Phase I) |  | 20% DF CY 2020 | Rehabilitation |  | km |  | Project Cost: | 910000 | Target Completion Date: | 2020-08-06 | Program: | 910000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: | 3.2% | No. of Persons: | 2 | Suspended June 13, 2020 due to unavailability of heavy equipment | Plan On-going | Plan On-going | Plan On-going | Plan On-going | Suspended June 13, 2020 due to unavailability of heavy equipment
[7 empty] | Project Engineer: | Obar | Revised Completion Date: |  | Allotment: | 910000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 52
[7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual: | 1.2%
[7 empty] | Duration: | 80 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | -2%
[7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
[7 empty] | Date Started: | 2020-05-18
Sitio Malaga - Tibulao (Phase I) |  | 20% DF CY 2020 | Rehabilitation |  | km |  | Project Cost: | 350000 | Target Completion Date: | 2020-06-17 | Program: | 350000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: | 3.5% | No. of Persons: | 2 | Plan On-going | Plan On-going | Plan On-going | Plan On-going | Plan On-going | Suspended June 13, 2020 due to unavailability of heavy equipment
[7 empty] | Project Engineer: | Obar | Revised Completion Date: |  | Allotment: | 350000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 44
[7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual: | 1.2%
[7 empty] | Duration: | 30 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | -2.3%
[7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
[7 empty] | Date Started: | 2020-05-18
Rehablilitation of Cabay-angan-Esperanza Provincial Road, Carmen-B.E. Dujali (Phase I) |  | 20% DF CY 2020 | Rehabilitation |  | km |  | Project Cost: | 350000 | Target Completion Date: |  | Program: | 350000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Plan On-going | Plan On-going | Plan On-going | Plan On-going | Plan On-going | Plan On-going
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 350000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Dujali - Pawas - San Vicente (Phase I) |  | 20% DF CY 2020 | Rehabilitation |  | km |  | Project Cost: | 525000 | Target Completion Date: | 2020-07-02 | Program: | 525000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: | 6.5% | No. of Persons: | 2 | Plan On-going | Plan On-going | Plan On-going | Plan On-going | Plan On-going | PTemporarily Suspended June 13, 2020 due to unavailability of heavy equipment
[7 empty] | Project Engineer: | Obar | Revised Completion Date: |  | Allotment: | 525000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 42
[7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual: | 1.2%
[7 empty] | Duration: | 45 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | -5.3%
[7 empty] | Date Allotment Released: | 2020-01-02 | Date completed:
[7 empty] | Date Started: | 2020-05-18
Los Amigos 1 - Esperanza - Los Amigos 2 (Phase I) |  | 20% DF CY 2020 | Rehabilitation |  | km |  | Project Cost: | 350000 | Target Completion Date: |  | Program: | 350000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 350000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Menzi - Balagunan - Tulalian (Phase I) |  | 20% DF CY 2020 | Rehabilitation |  | km |  | Project Cost: | 3720500 | Target Completion Date: |  | Program: | 3720500 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 3720500 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Jct,. Bdry. Tagum- Talomo (Phase I) |  | 20% DF CY 2020 | Rehabilitation |  | km |  | Project Cost: | 1400000 | Target Completion Date: | 2020-09-15 | Program: | 1400000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: | 41.2% | No. of Persons: | 4 | POW for approval with the Governor | POW for approval with the Governor | POW for approval with the Governor | POW for approval with the Governor | POW for approval with the Governor | Suspended June 13, 2020
[7 empty] | Project Engineer: | Obar | Revised Completion Date: |  | Allotment: | 1400000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 88
[7 empty] | Implementor: | Admin | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual: | 39.6%
[7 empty] | Duration: | 120 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | -1.6%
[7 empty] | Date Allotment Released: |  | Date completed:
[7 empty] | Date Started: | 2020-05-18
Prk. 5 RJS - Prk. 6 New Casay (Phase I) |  | 20% DF CY 2020 | Rehabilitation |  | km |  | Project Cost: | 350000 | Target Completion Date: |  | Program: | 350000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Plan On-going | Plan On-going | Plan On-going | Plan On-going | Plan On-going | Plan On-going
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 350000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
ROAD ID 008 - Fr. Rd. 3 - San Jose |  | 20% DF CY 2020 | Rehabilitation |  | km |  | Project Cost: | 8000000 | Target Completion Date: |  | Program: | 8000000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Plan On-going | Plan On-going | Plan On-going | Plan On-going | Plan On-going | Plan On-going
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 8000000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Rural Electrification at RAMADA Compound Purok Sto. Niño, Brgy. Cuambogan, Tagum City |  | 20% Development Fund CY 2020 | Electrification |  | km |  | Project Cost: | 1000000 | Target Completion Date: |  | Program: | 1000000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | PO on process - Tagum Constrak | PO on process - Tagum Constrak | PO on process - Tagum Constrak | PO on process - Tagum Constrak | PO on process - Tagum Constrak | For implementation Tagum Constrak
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 1000000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Rural Electrification at Lower Camansa, Prk.5 to 6 Lower, Brgy. Camansa, Asuncion |  | 20% Development Fund CY 2020 | Electrification |  | km |  | Project Cost: | 3000000 | Target Completion Date: |  | Program: | 3000000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | PO on process - Tagum Constrak | PO on process - Tagum Constrak | PO on process - Tagum Constrak | PO on process - Tagum Constrak | PO on process - Tagum Constrak | For implementation Tagum Constrak
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 3000000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Completion of Single Phase Line at Purok 6 and Purok 7, Brgy. Cogon, Babak Distirct, IGACOS |  | 20% DF CY 2020 | Electrificaton |  | km |  | Project Cost: | 1000000 | Target Completion Date: |  | Program: | 1000000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | PR #20063965 | PR #20063965 | PR #20063965 | PR #20063965 | PR #20063965 | PR #20063965
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 1000000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Completion of Single Phase Line at Purok Perlas, Brgy. Sta. Cruz, Talicud (Day Care Center), IGACOS |  | 20% DF CY 2020 | Electrificaton |  | km |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | POW preparation on-going c/o Engr. Kim Pao Lu | POW preparation on-going c/o Engr. Kim Pao Lu | POW preparation on-going c/o Engr. Kim Pao Lu | POW preparation on-going c/o Engr. Kim Pao Lu | POW preparation on-going c/o Engr. Kim Pao Lu | POW preparation on-going c/o Engr. Kim Pao Lu
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Const. of Potable Water System, Brgy. Gupitan, Kapalong |  | 20% DF CY 2020 | PWS |  | km |  | Project Cost: | 3000000 | Target Completion Date: |  | Program: | 3000000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | POW preparation on-going c/o Engr. Kim Pao Lu | POW preparation on-going c/o Engr. Kim Pao Lu | POW preparation on-going c/o Engr. Kim Pao Lu |  |  | Plan On-going
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 3000000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Const. of Potable Water System, Brgy. Sto. Niño, Kapalong |  | 20% DF CY 2020 | PWS |  | km |  | Project Cost: | 1000000 | Target Completion Date: |  | Program: | 1000000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | POW preparation on-going c/o Engr. Kim Pao Lu | POW preparation on-going c/o Engr. Kim Pao Lu | POW preparation on-going c/o Engr. Kim Pao Lu |  |  | Plan On-going
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 1000000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Const. of Potable Water System, Brgy. Dagohoy, Talaingod |  | 20% DF CY 2020 | PWS |  | km |  | Project Cost: | 1000000 | Target Completion Date: |  | Program: | 1000000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | POW preparation on-going c/o Engr. Kim Pao Lu | POW preparation on-going c/o Engr. Kim Pao Lu | POW preparation on-going c/o Engr. Kim Pao Lu |  |  | Plan On-going
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 1000000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Const. of Potable Water System, Brgy. Palma Gil, Talaingod |  | 20% DF CY 2020 | PWS |  | km |  | Project Cost: | 1000000 | Target Completion Date: |  | Program: | 1000000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | POW preparation on-going c/o Engr. Kim Pao Lu | POW preparation on-going c/o Engr. Kim Pao Lu | POW preparation on-going c/o Engr. Kim Pao Lu |  |  | Plan On-going
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 1000000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Impv't. of Potable Water System, Brgy. Kiotoy, Panabo City |  | 20% DF CY 2020 | PWS |  | km |  | Project Cost: | 1000000 | Target Completion Date: |  | Program: | 1000000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | POW preparation on-going c/o Engr. Kim Pao Lu | POW preparation on-going c/o Engr. Kim Pao Lu | POW preparation on-going c/o Engr. Kim Pao Lu |  |  | Plan On-going
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 1000000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Impv't. of Potable Water System, Consolacion, Panabo City |  | 20% DF CY 2020 | Water System |  |  |  | Project Cost: | 10000000 | Target Completion Date: |  | Program: | 10000000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. |  |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No 1
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 10000000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Impv't. of Potable Water System, Tagbitan-ag, Samal Dist. |  | 20% DF CY 2020 | Water System |  |  |  | Project Cost: | 1000000 | Target Completion Date: |  | Program: | 1000000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | For implementation | For implementation | For implementation |  |  | Plan On-going
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 1000000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Impv't. of Potable Water System, San Antonio, babak, IGCS |  | 20% DF CY 2020 | Water System |  |  |  | Project Cost: | 1000000 | Target Completion Date: |  | Program: | 1000000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. |  |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No 1
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 1000000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Impv't. of Potable Water System, San Isidro, Babak, IGCS |  | 20% DF CY 2020 | Water System |  |  |  | Project Cost: | 1000000 | Target Completion Date: |  | Program: | 1000000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. |  |  | Plan On-going
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 1000000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Impv't. of Potable Water System,Licup, Samal, IGCS |  | 20% DF CY 2020 | Water System |  |  |  | Project Cost: | 2000000 | Target Completion Date: |  | Program: | 2000000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. |  |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No 1
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 2000000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Const. of Water System at Provincial Engineer's Office 2nd District Carmen |  | 20% DF CY 2020 | Water System |  |  |  | Project Cost: | 1000000 | Target Completion Date: |  | Program: | 1000000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. |  |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No 1
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 1000000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Construction Women Development Center, Dagohoy, Talaingod |  | 20% Development Fund CY 2020 | Building |  | sq.m |  | Project Cost: | 1000000 | Target Completion Date: |  | Program: | 1000000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Post qualification on process | Post qualification on process | Post qualification on process | Post qualification on process | Post qualification on process | Procurement on process
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 1000000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Const. of Native Chicken Production House at Sitio Salawao, Brgy. Sto. Niño, Talaingod |  | 20% Development Fund CY 2020 | Building |  | sq.m |  | Project Cost: | 2000000 | Target Completion Date: |  | Program: | 2000000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Post qualification on process | Post qualification on process | Post qualification on process | Post qualification on process | Post qualification on process | Procurement on process
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 2000000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Construction of Fence at Tulalian National High School, Tulalian, Sto. Tomas |  | GENERAL FUND CY 2020 | Fence |  | sq.m |  | Project Cost: | 1500000 | Target Completion Date: |  | Program: | 1500000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 1500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Construction of Commercial Building at Kinawitnon, IGACOS, Babak |  | 20% DF CY 2020 | Building |  | sq.m |  | Project Cost: | 2000000 | Target Completion Date: |  | Program: | 2000000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 2000000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Improvement of Provincial Engineer's Office 2nd District Office Phase 2, Carmen |  | 20% DF CY 2020 | Building |  | sq.m |  | Project Cost: | 1590000 | Target Completion Date: |  | Program: | 1590000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Plan and DED On-going | Plan and DED On-going | Plan and DED On-going | Plan and DED On-going | Plan and DED On-going | Plan and DED On-going
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 1590000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Construction of DAVNOR Tech-Vocational Center, Government Center, Mankilam, Tagum City |  | 20% Development Fund CY 2020 | Building |  | sq.m | Admin | Project Cost: | 8000000 | Target Completion Date: |  | Program: | 8000000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 8000000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Construction of DDN hospital Carmen Zone Annex Building Phase 3, Carmen |  | GENERAL FUND CY 2020 | Building |  | sq.m |  | Project Cost: | 800000 | Target Completion Date: |  | Program: | 800000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Abstract #0420201476 | Abstract #0420201476 | Abstract #0420201476 | Abstract #0420201476 | Abstract #0420201476 | Procurement on process
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 800000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Improvement of PSWDO Bodega Government Cente, Mankilam, Tagum City |  | 20% Development Fund CY 2020 | Building |  | sq.m | Admin | Project Cost: | 1000000 | Target Completion Date: |  | Program: | 1000000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | POW and Plans on-going | POW and Plans on-going | POW and Plans on-going | POW and Plans on-going | POW and Plans on-going | POW and Plans on-going
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 1000000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Renovation/Improvement of MAFAMCO Consumer's Bldg., Brgy. Mamangan, San Isidro |  | 20% Development Fund CY 2020 | Building |  | sq.m | Contract | Project Cost: | 800000 | Target Completion Date: |  | Program: | 800000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 800000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Construction of IP Council of Women Training Center, Camansa Kamadi District, Asuncion |  | 20% Development Fund CY 2020 | Building |  | sq.m | Admin | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Construction of Municipal Triball Hall, Asuncion |  | 20% Development Fund CY 2020 | Building |  | sq.m | Contract | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Construction of Municipal Triball Hall, Kapalong |  | 20% Development Fund CY 2020 | Building |  | sq.m | Contract | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Construction of Municipal Triball Hall, Talaingod |  | 20% Development Fund CY 2020 | Building |  | sq.m | Contract | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Construction of Municipal Triball Hall, Carmen |  | GENERAL FUND CY 2020 | Building |  | sq.m |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Construction of Municipal Triball Hall, B.E. Dujali |  | GENERAL FUND CY 2020 | Building |  | sq.m |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Construction of Municipal Triball Hall, Sto. Tomas |  | GENERAL FUND CY 2020 | Building |  | sq.m | Admin | Project Cost: | 500000 | Target Completion Date: | 2019-07-31 | Program: | 500000 | Planned: | 100% | Planned: | 100% | Planned: | 100% | Planned: | 100% | Planned: | 100% | No. of Persons: | 7 | Suspended June 28, 2019. Waiting for the delivery of JO Materials | Suspended June 28, 2019. Waiting for the delivery of JO Materials | Suspended June 28, 2019. Waiting for the delivery of JO Materials | Suspended June 28, 2019. Waiting for the delivery of JO Materials | Suspended June 28, 2019. Waiting for the delivery of JO Materials | Suspended June 28, 2019. Waiting for the delivery of JO Materials
[7 empty] | Project Engineer: | Roque | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: | 110
[7 empty] | Implementor: | PEO | No. of days suspended: |  | Disbursement: |  | Actual: | 85% | Actual: | 85% | Actual: | 85% | Actual: | 85% | Actual: | 85%
[7 empty] | Duration: | 70 | No. of days extended: |  |  |  | Slippage: | -15% | Slippage: | -15% | Slippage: | -15% | Slippage: | -15% | Slippage: | -15%
[7 empty] | Date Allotment Released: | CY 2018 | Date completed:
[7 empty] | Date Started: | 2019-05-22
Construction of One(1) unit School Building at Cabidianan E/S, New Corella |  | 20% Development Fund CY 2020 | Building |  | sq.m | Contract | Project Cost: | 1300000 | Target Completion Date: |  | Program: | 1300000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: | [6 empty] | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No 1
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 1300000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Construction of one(1) unit School Building at Kamansi Integrated School, Florida, kapalong |  | 20% Development Fund CY 2020 | Building |  | sq.m | Contract | Project Cost: | 1300000 | Target Completion Date: |  | Program: | 1300000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 1300000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Construction of one(1) unit School Building at Magatos E/S, Magatos, Asuncion |  | 20% Development Fund CY 2020 | Building |  | sq.m | Contract | Project Cost: | 1300000 | Target Completion Date: |  | Program: | 1300000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 1300000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Construction of one(1) unit School Building at Sta. Cruz E/S, New Corella |  | 20% Development Fund CY 2020 | Building |  | sq.m |  | Project Cost: | 1300000 | Target Completion Date: |  | Program: | 1300000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 1300000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Construction of Two(2) Classroom at Tibulao Elem. School, Tibulao, Carmen |  | 20% Development Fund CY 2020 | Building |  | sq.m |  | Project Cost: | 2900000 | Target Completion Date: |  | Program: | 2900000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 2900000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Expansion of Balay Silangan (Phase 2), Gov't. Center, Mankilam |  | 20% Development Fund CY 2020 | Building |  | sq.m |  | Project Cost: | 5000000 | Target Completion Date: |  | Program: | 5000000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 5000000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Const. of Day Care Center, Limbaan, New Corella |  | 20% DF CY 2020 | Building |  | sq.m |  | Project Cost: | 1000000 | Target Completion Date: |  | Program: | 1000000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 1000000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Const. of Day Care Center, Gabuyan, kapalong |  | 20% DF CY 2020 | Building |  | sq.m |  | Project Cost: | 1000000 | Target Completion Date: |  | Program: | 1000000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 1000000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Compl./Rep. Day Care Center,Canatan, Asuncion |  | 20% DF CY 2020 | Building |  | sq.m |  | Project Cost: | 300000 | Target Completion Date: |  | Program: | 300000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 300000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Compl./Rep. Day Care Center,Cambanogoy, Asuncion |  | 20% DF CY 2020 | Building |  | sq.m |  | Project Cost: | 300000 | Target Completion Date: |  | Program: | 300000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 300000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Compl./Rep. Day Care Center,Gabuyan, kapalong |  | 20% DF CY 2020 | Building |  | sq.m |  | Project Cost: | 600000 | Target Completion Date: |  | Program: | 600000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 600000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Compl./Rep. Day Care Center,New Sambog, New Corella |  | 20% DF CY 2020 | Building |  | sq.m |  | Project Cost: | 300000 | Target Completion Date: |  | Program: | 300000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 300000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Compl./Rep. Day Care Center, Cabidianan, New Corella |  | 20% DF CY 2020 | Building |  | sq.m |  | Project Cost: | 300000 | Target Completion Date: |  | Program: | 300000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 300000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Compl./Rep. Day Care Center, Igangon, San Isidro |  | 20% DF CY 2020 | Building |  | sq.m |  | Project Cost: | 300000 | Target Completion Date: |  | Program: | 300000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 300000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Compl./Rep. Day Care Center, Madaum, Tagum City |  | 20% DF CY 2020 | Building |  | sq.m |  | Project Cost: | 300000 | Target Completion Date: |  | Program: | 300000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 300000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Compl./Rep. Day Care Center, Apokon, Tagum City |  | 20% DF CY 2020 | Building |  | sq.m |  | Project Cost: | 300000 | Target Completion Date: |  | Program: | 300000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 300000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Compl./Rep. Day Care Center, Sto. Niño, Talaingod |  | 20% DF CY 2020 | Building |  | sq.m |  | Project Cost: | 300000 | Target Completion Date: |  | Program: | 300000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 300000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Const. of Day Care Center, JP Laurel, Panabo City |  | AB CY 2020 | Building |  | sq.m |  | Project Cost: | 1000000 | Target Completion Date: |  | Program: | 1000000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 1000000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Const. of Day Care Center, Dujali, B.E. Dujali |  | AB CY 2020 | Building |  | sq.m |  | Project Cost: | 1000000 | Target Completion Date: |  | Program: | 1000000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 1000000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Const. of Day Care Center, Tibal-og, Sto Tomas |  | AB CY 2020 | Building |  | sq.m |  | Project Cost: | 1000000 | Target Completion Date: |  | Program: | 1000000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 1000000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Compl./Rep. Day Care Center, Cabay-angan, B.E. Dujali |  | AB CY 2020 | Building |  | sq.m |  | Project Cost: | 300000 | Target Completion Date: |  | Program: | 300000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 300000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Compl./Rep. Day Care Center, Tanglaw, B.E. Dujali |  | AB CY 2020 | Building |  | sq.m |  | Project Cost: | 300000 | Target Completion Date: |  | Program: | 300000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 300000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Compl./Rep. Day Care Center, Salvacion, Carmen |  | AB CY 2020 | Building |  | sq.m |  | Project Cost: | 300000 | Target Completion Date: |  | Program: | 300000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 300000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Compl./Rep. Day Care Center, San Agustin, IGCS |  | AB CY 2020 | Building |  | sq.m |  | Project Cost: | 300000 | Target Completion Date: |  | Program: | 300000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 300000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Compl./Rep. Day Care Center, Toril, IGCS |  | AB CY 2020 | Building |  | sq.m |  | Project Cost: | 300000 | Target Completion Date: |  | Program: | 300000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 300000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Compl./Rep. Day Care Center, Tibal-og, Sto. Tomas |  | AB CY 2020 | Building |  | sq.m |  | Project Cost: | 600000 | Target Completion Date: |  | Program: | 600000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 600000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Compl./Rep. Day Care Center, Talomo, Sto. Tomas |  | AB CY 2020 | Building |  | sq.m |  | Project Cost: | 300000 | Target Completion Date: |  | Program: | 300000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 300000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Compl./Rep. Day Care Center, Kinamayan, Sto. Tomas |  | AB CY 2020 | Building |  | sq.m |  | Project Cost: | 300000 | Target Completion Date: |  | Program: | 300000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 300000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Compl./Rep. Day Care Center, La Libertad, Sto. Tomas |  | AB CY 2020 | Building |  | sq.m |  | Project Cost: | 300000 | Target Completion Date: |  | Program: | 300000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 300000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Improvement/Rehab. Of Luntiang Paraiso, New Corella |  | 20% DF CY 2020 | Building |  | km |  | Project Cost: | 3000000 | Target Completion Date: |  | Program: | 3000000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | For Purchase Request | For Purchase Request | For Purchase Request | For Purchase Request | For Purchase Request | Procurement on process
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 3000000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Rehab. Of Various Local Roads @ Island Garden City of Samal |  | 20% DF CY 2020 | Rehabilitation |  | km |  | Project Cost: | 2518182 | Target Completion Date: |  | Program: | 2518182 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Plan On-going | Plan On-going | Plan On-going | Plan On-going | Plan On-going | Plan On-going
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 2518182 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Improvement and Desiltation of Camoning Creek |  | 5% Calamity Fund CY 2020 | Desiltation |  | ln.m |  | Project Cost: | 2500000 | Target Completion Date: |  | Program: | 2500000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Abstract # 0520201658 | Abstract # 0520201658 | Abstract # 0520201658 | Abstract # 0520201658 | Abstract # 0520201658 | Abstract # 0520201658
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 2500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Improvement of Saug-Sonlon-Bdry. Longanapan |  | 5% CALAMITY FUND CY 2020 | Road |  | km |  | Project Cost: | 1000000 | Target Completion Date: |  | Program: | 1000000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | For preparation of POW and Plans | For preparation of POW and Plans | For preparation of POW and Plans | For preparation of POW and Plans | For preparation of POW and Plans | For preparation of POW and Plans
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 1000000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Single Barrel Box Culvert at Mangalcal-Diamond Creek, Brgy. Mangalcal, Carmen |  | 5% Calamity Fund CY 2020 | Box Culvert |  | ln.m |  | Project Cost: | 2000000 | Target Completion Date: |  | Program: | 2000000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 2000000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Improvement of Mangalcal to Diamond Creek Farm to Market Road Opening |  | 5% Calamity Fund CY 2020 | Improvement |  | ln.m |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Rehab./Impv't. of Sto. Niño-Daligdigon-Paiton |  | 5% CALAMITY FUND CY 2020 | Road |  | km |  | Project Cost: | 1000000 | Target Completion Date: |  | Program: | 1000000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 1000000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Rehab./Impv't. of San Miguel - Moslog - Kinamayan, Sto. Tomas |  | 5% Calamity Fund CY 2020 | Rehabilitation |  | ln.m |  | Project Cost: | 1000000 | Target Completion Date: |  | Program: | 1000000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1. | To support for the re-alignment of the said fund to be used in the response measures against Corona Virus Disease (COVID 19) in the CY 2020 Supplemental Budget No. 1.
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 1000000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Const. of 1 Classroom @ Mankay Integrated School, Gupitan, kapalong |  | AB - SEF CY 2020 | Building |  | sq.m |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Opening of Shopping on June 25, 2020 | Opening of Shopping on June 25, 2020 | Opening of Shopping on June 25, 2020 | Opening of Shopping on June 25, 2020 | Opening of Shopping on June 25, 2020 | Procurement on process
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Const. of 1 Classroom @ Luno-luno E/S, Gupitan, kapalong |  | AB - SEF CY 2020 | Building |  | sq.m |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Opening of Shopping on June 25, 2020 | Opening of Shopping on June 25, 2020 | Opening of Shopping on June 25, 2020 | Opening of Shopping on June 25, 2020 | Opening of Shopping on June 25, 2020 | Procurement on process
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Const. of 1 Classroom @ Kamunuan E/S, Gupitan, kapalong |  | AB - SEF CY 2020 | Building |  | sq.m |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Opening of Shopping on June 25, 2020 | Opening of Shopping on June 25, 2020 | Opening of Shopping on June 25, 2020 | Opening of Shopping on June 25, 2020 | Opening of Shopping on June 25, 2020 | Procurement on process
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Const. of 1 Classroom @ Tawinian E/S, Gupitan, kapalong |  | AB - SEF CY 2020 | Building |  | sq.m |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Opening of Shopping on June 25, 2020 | Opening of Shopping on June 25, 2020 | Opening of Shopping on June 25, 2020 | Opening of Shopping on June 25, 2020 | Opening of Shopping on June 25, 2020 | Procurement on process
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Const. of 1 Classroom @ Aninipot E/S, Gupitan, kapalong |  | AB - SEF CY 2020 | Building |  | sq.m |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Opening of Shopping on June 25, 2020 | Opening of Shopping on June 25, 2020 | Opening of Shopping on June 25, 2020 | Opening of Shopping on June 25, 2020 | Opening of Shopping on June 25, 2020 | Procurement on process
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Const. of 1 Classroom @ Moling E/S, Gupitan, kapalong |  | AB - SEF CY 2020 | Building |  | sq.m |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Opening of Shopping on June 25, 2020 | Opening of Shopping on June 25, 2020 | Opening of Shopping on June 25, 2020 | Opening of Shopping on June 25, 2020 | Opening of Shopping on June 25, 2020 | Procurement on process
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Const. of 1 Classroom @ Mangga E/S, Magwawa, Sto. Tomas |  | AB - SEF CY 2020 | Building |  | sq.m |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Opening of Shopping on June 25, 2020 | Opening of Shopping on June 25, 2020 | Opening of Shopping on June 25, 2020 | Opening of Shopping on June 25, 2020 | Opening of Shopping on June 25, 2020 | Procurement on process
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Const. of 1 Classroom @ Lomondong E/S, Dagohoy, Talaingod |  | AB - SEF CY 2020 | Building |  | sq.m |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Opening of Shopping on June 25, 2020 | Opening of Shopping on June 25, 2020 | Opening of Shopping on June 25, 2020 | Opening of Shopping on June 25, 2020 | Opening of Shopping on June 25, 2020 | Procurement on process
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Const. of 1 Classroom @ Malapanit E/S, Sto. Niño, Talaingod |  | AB - SEF CY 2020 | Building |  | sq.m |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Opening of Shopping on June 25, 2020 | Opening of Shopping on June 25, 2020 | Opening of Shopping on June 25, 2020 | Opening of Shopping on June 25, 2020 | Opening of Shopping on June 25, 2020 | Procurement on process
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Const. of 1 Classroom @ Laputlakan E/S, Sto. Niño, Talaingod |  | AB - SEF CY 2020 | Building |  | sq.m |  | Project Cost: | 500000 | Target Completion Date: |  | Program: | 500000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | Opening of Shopping on June 25, 2020 | Opening of Shopping on June 25, 2020 | Opening of Shopping on June 25, 2020 | Opening of Shopping on June 25, 2020 | Opening of Shopping on June 25, 2020 | Procurement on process
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Renovation of Teen Tambayan |  | 20% DF CY 2020 | Building |  | sq.m | Contract | Project Cost: | 500000 | Target Completion Date: | 2020-12-22 | Program: | 500000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: | 100% | No. of Persons: |  | Date of procurement June 30, 2020 | Date of procurement June 30, 2020 | Date of procurement June 30, 2020 | Date of procurement June 30, 2020 | Date of procurement June 30, 2020 | Procurement on process
[7 empty] | Project Engineer: | Quirante | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: | JJR Const. & Supply | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual: | 100%
[7 empty] | Duration: | 69 | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed: | 2020-12-22
[7 empty] | Date Started: | 2020-10-14
Proposed Road Opening of Nasilaban - Pongpong Road Section, Talaingod |  | SB # 1 CY 2020 | Road |  | km |  | Project Cost: | 5500000 | Target Completion Date: |  | Program: | 5500000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | PO #2020062105 - M3C CONSTRUCTION & SUPPLY; PO #2020061966 - FL2 LUMBER & CONSTRUCTION SUPPLY; PO #2020062217 - Alpebel Builders and Supply Corporation, PO #DIOCESAN PRINTING PRESS | PO #2020062105 - M3C CONSTRUCTION & SUPPLY; PO #2020061966 - FL2 LUMBER & CONSTRUCTION SUPPLY; PO #2020062217 - Alpebel Builders and Supply Corporation, PO #DIOCESAN PRINTING PRESS | PO #2020062105 - M3C CONSTRUCTION & SUPPLY; PO #2020061966 - FL2 LUMBER & CONSTRUCTION SUPPLY; PO #2020062217 - Alpebel Builders and Supply Corporation, PO #DIOCESAN PRINTING PRESS | PO #2020062105 - M3C CONSTRUCTION & SUPPLY; PO #2020061966 - FL2 LUMBER & CONSTRUCTION SUPPLY; PO #2020062217 - Alpebel Builders and Supply Corporation, PO #DIOCESAN PRINTING PRESS | PO #2020062105 - M3C CONSTRUCTION & SUPPLY; PO #2020061966 - FL2 LUMBER & CONSTRUCTION SUPPLY; PO #2020062217 - Alpebel Builders and Supply Corporation, PO #DIOCESAN PRINTING PRESS | Procurement on process
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 5500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Establishment of Multiplier Farm Phase 2, Brgy. Sto. Niño, Talaingod |  | SB # 1 CY 2020 | Building |  | sq.m |  | Project Cost: | 380000 | Target Completion Date: |  | Program: | 380000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | For bidding on June 30, 2020; Re-bid July 28, 2020. | For bidding on June 30, 2020; Re-bid July 28, 2020. | For bidding on June 30, 2020; Re-bid July 28, 2020. | For bidding on June 30, 2020; Re-bid July 28, 2020. | For bidding on June 30, 2020; Re-bid July 28, 2020. | Procurement on process
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 380000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Establishment of Multiplier Farm (Poultry House), Phase 2, Brgy. Sto. Niño, Talaingod |  | SB # 1 CY 2020 | Building |  | sq.m |  | Project Cost: | 110000 | Target Completion Date: |  | Program: | 110000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | For bidding on June 30, 2020; Re-bid July 28, 2020. | For bidding on June 30, 2020; Re-bid July 28, 2020. | For bidding on June 30, 2020; Re-bid July 28, 2020. | For bidding on June 30, 2020; Re-bid July 28, 2020. | For bidding on June 30, 2020; Re-bid July 28, 2020. | Procurement on process
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 110000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Proposed of 1 Barrel Culvert Along Kapalong-Mabantao-Florida Provincial Road |  | SB # 4 CY 2020 | Building |  | sq.m | Admin | Project Cost: | 1900000 | Target Completion Date: | 0 | Program: | 1900000 | Planned: | 100% | Planned: | 100% | Planned: | 100% | Planned: |  | Planned: |  | No. of Persons: |  | Completed as per physical accomplishment. Financial documents still on process. |  |  |  |  | For preparation of Plan
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 1900000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: | 100% | Actual: | 100% | Actual: | 100% | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Const. of Igangon ES Integrated School (PREFAB), San Isidro |  | SB # 4 CY 2020 | Building |  | sq.m | Admin | Project Cost: | 500000 | Target Completion Date: | 0 | Program: | 500000 | Planned: | 100% | Planned: | 100% | Planned: | 100% | Planned: |  | Planned: |  | No. of Persons: |  | Completed as per physical accomplishment. Financial documents still on process. |  |  |  |  | For preparation of Plan
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: | 100% | Actual: | 100% | Actual: | 100% | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Inst. Of Automatic Fire Sprinkler, Smoke Detection & Fire Alarm System, Old Main Hospitals Bldg, Samal Dist. Hospital |  | SB # 4 CY 2020 | Building |  | sq.m | Admin | Project Cost: | 3000000 | Target Completion Date: | 0 | Program: | 3000000 | Planned: | 100% | Planned: | 100% | Planned: | 100% | Planned: |  | Planned: |  | No. of Persons: |  | Completed as per physical accomplishment. Financial documents still on process. |  |  |  |  | For preparation of Plan
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 3000000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: | 100% | Actual: | 100% | Actual: | 100% | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Const. of 2-Storey Rural Health Unit Bldg, w/safe Birthing Facility, New Corella |  | SB # 4 CY 2020 | Building |  | sq.m | Admin | Project Cost: | 10000000 | Target Completion Date: | 0 | Program: | 10000000 | Planned: | 100% | Planned: | 100% | Planned: | 100% | Planned: |  | Planned: |  | No. of Persons: |  | Completed as per physical accomplishment. Financial documents still on process. |  |  |  |  | For preparation of Plan
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 10000000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: | 100% | Actual: | 100% | Actual: | 100% | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Const. of 2-Storey Rural Health Unit Bldg, w/safe Birthing Facility, Asuncion |  | SB # 4 CY 2020 | Building |  | sq.m | Admin | Project Cost: | 10000000 | Target Completion Date: | 0 | Program: | 10000000 | Planned: | 100% | Planned: | 100% | Planned: | 100% | Planned: |  | Planned: |  | No. of Persons: |  | Completed as per physical accomplishment. Financial documents still on process. |  |  |  |  | For preparation of Plan
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 10000000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: | 100% | Actual: | 100% | Actual: | 100% | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Const. of 2-Storey Rural Health Unit Bldg, w/safe Birthing Facility, Talaingod |  | SB # 4 CY 2020 | Building |  | sq.m | Admin | Project Cost: | 10000000 | Target Completion Date: | 0 | Program: | 10000000 | Planned: | 100% | Planned: | 100% | Planned: | 100% | Planned: |  | Planned: |  | No. of Persons: |  | Completed as per physical accomplishment. Financial documents still on process. |  |  |  |  | For preparation of Plan
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 10000000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: | 100% | Actual: | 100% | Actual: | 100% | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Const. of 2-Storey Rural Health Unit Bldg, w/safe Birthing Facility, Sto. Tomas |  | SB # 4 CY 2020 | Building |  | sq.m | Admin | Project Cost: | 10000000 | Target Completion Date: | 0 | Program: | 10000000 | Planned: | 100% | Planned: | 100% | Planned: | 100% | Planned: |  | Planned: |  | No. of Persons: |  | Completed as per physical accomplishment. Financial documents still on process. |  |  |  |  | For preparation of Plan
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 10000000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: | 100% | Actual: | 100% | Actual: | 100% | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Const. of Infirmary Hospital, Panabo City |  | SB # 4 CY 2020 | Building |  | sq.m | Admin | Project Cost: | 15000000 | Target Completion Date: | 0 | Program: | 15000000 | Planned: | 100% | Planned: | 100% | Planned: | 100% | Planned: |  | Planned: |  | No. of Persons: |  | Completed as per physical accomplishment. Financial documents still on process. |  |  |  |  | For preparation of Plan
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 15000000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: | 100% | Actual: | 100% | Actual: | 100% | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Const. of Dialysis Center with Equipments - Kapalong Hospital |  | SB # 4 CY 2020 | Building |  | sq.m | Admin | Project Cost: | 30000000 | Target Completion Date: | 0 | Program: | 30000000 | Planned: | 100% | Planned: | 100% | Planned: | 100% | Planned: |  | Planned: |  | No. of Persons: |  | Completed as per physical accomplishment. Financial documents still on process. |  |  |  |  | For preparation of Plan
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 30000000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: | 100% | Actual: | 100% | Actual: | 100% | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Const. of Dialysis Center with Equipments - Samal Hospital |  | SB # 4 CY 2020 | Building |  | sq.m | Admin | Project Cost: | 30000000 | Target Completion Date: | 0 | Program: | 30000000 | Planned: | 100% | Planned: | 100% | Planned: | 100% | Planned: |  | Planned: |  | No. of Persons: |  | Completed as per physical accomplishment. Financial documents still on process. |  |  |  |  | For preparation of Plan
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 30000000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: | 100% | Actual: | 100% | Actual: | 100% | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Impv't. of Sto. Tomas Organic Prod'n. Center with Common Service facility, Sto. Tomas |  | SB # 4 CY 2020 | Building |  | sq.m | Admin | Project Cost: | 951204.81 | Target Completion Date: | 2018-12-24 23:59 | Program: | 951204.81 | Planned: | 94.55% | Planned: | 100% | Planned: | 100% | Planned: | 100% | Planned: | 100% | No. of Persons: | 20 | Completed as per physical accomplishment. Financial documents still on process. |  |  |  |  | On-going
[7 empty] | Project Engineer: | Azotes | Revised Completion Date: | May 24, 2021 | Allotment: | 951204.81 | Revised: | 78.32% | Revised: | 83.43% | Revised: | 83.43% | Revised: | 83.43% | Revised: | 22.53% | No. of Man-days:
[7 empty] | Implementor: | Manantan | No. of days suspended: | 501 | Disbursement: |  | Actual: | 71.89% | Actual: | 75.19% | Actual: | 75.19% | Actual: | 75.19% | Actual: | 30.33%
[7 empty] | Duration: | 330 | No. of days extended: |  |  |  | Slippage: | -6.424% | Slippage: | -8.238% | Slippage: | -8.238% | Slippage: | -8.238% | Slippage: | 7.8%
[7 empty] | Date Allotment Released: | CY 2014 | Date completed:
[7 empty] | Date Started: | 2018-01-29
Chocolate Processing, RACO, San Francisco, Panabo City |  | SB # 4 CY 2020 | Building |  | sq.m | Admin | Project Cost: | 3199294.6 | Target Completion Date: | 0 | Program: | 3199294.6 | Planned: | 100% | Planned: | 100% | Planned: | 100% | Planned: |  | Planned: |  | No. of Persons: |  | Completed as per physical accomplishment. Financial documents still on process. |  |  |  |  | Procurement on process
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 3199294.6 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: | 100% | Actual: | 100% | Actual: | 100% | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Rep/Rehab. Of Civil Service Commission Field Office |  | SB # 4 CY 2020 | Building |  | sq.m | Admin | Project Cost: | 290000 | Target Completion Date: | 0 | Program: | 290000 | Planned: | 100% | Planned: | 100% | Planned: | 100% | Planned: |  | Planned: |  | No. of Persons: |  | Completed as per physical accomplishment. Financial documents still on process. |  |  |  |  | For preparation of Plan
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 290000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: | 100% | Actual: | 100% | Actual: | 100% | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Const. and Inst. Of One (1) unit Community-Based Micro Hydropower System and 1,308 units Solar Photovoltaic Homelihtning System in Gupitan, Kapalong & Palma Gil, Talaingod (Improving the Lives of People in Off-Grid Communities in mindanao through the Provinsion of Sustainable Energy) |  | SB # 4 CY 2020 | Building |  | sq.m | Admin | Project Cost: | 2707680 | Target Completion Date: | 0 | Program: | 2707680 | Planned: | 100% | Planned: | 100% | Planned: | 100% | Planned: |  | Planned: |  | No. of Persons: |  | Completed as per physical accomplishment. Financial documents still on process. |  |  |  |  | For preparation of Plan
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 2707680 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: | 100% | Actual: | 100% | Actual: | 100% | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Rehab. Of Manpower Dev't. Center, PEO Sub-Office Bldg., |  | SB # 4 CY 2020 | Building |  | sq.m | Admin | Project Cost: | 1590000 | Target Completion Date: | 0 | Program: | 1590000 | Planned: | 100% | Planned: | 100% | Planned: | 100% | Planned: |  | Planned: |  | No. of Persons: |  | Completed as per physical accomplishment. Financial documents still on process. |  |  |  |  | For preparation of Plan
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 1590000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: | 100% | Actual: | 100% | Actual: | 100% | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Const. of retaining Wall, Brgy. Sto. Niño, Talaingod |  | SB # 4 CY 2020 | Building |  | sq.m | Admin | Project Cost: | 500000 | Target Completion Date: | 0 | Program: | 500000 | Planned: | 100% | Planned: | 100% | Planned: | 100% | Planned: |  | Planned: |  | No. of Persons: |  | Completed as per physical accomplishment. Financial documents still on process. |  |  |  |  | For preparation of Plan
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 500000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: | 100% | Actual: | 100% | Actual: | 100% | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Const. of Satellite market, Brgy. Pagsabangan, Tagum City |  | SB # 4 CY 2020 | Building |  | sq.m | Admin | Project Cost: | 238125 | Target Completion Date: | 0 | Program: | 238125 | Planned: | 100% | Planned: | 100% | Planned: | 100% | Planned: |  | Planned: |  | No. of Persons: |  | Completed as per physical accomplishment. Financial documents still on process. |  |  |  |  | For preparation of Plan
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 238125 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: | 100% | Actual: | 100% | Actual: | 100% | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Const. of DAVNOR Tech-Vocational Training Center |  | SB # 4 CY 2020 | Building |  | sq.m | Admin | Project Cost: | 29000000 | Target Completion Date: | 0 | Program: | 29000000 | Planned: | 100% | Planned: | 100% | Planned: | 100% | Planned: |  | Planned: |  | No. of Persons: |  | Completed as per physical accomplishment. Financial documents still on process. |  |  |  |  | For preparation of Plan
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 29000000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: | 100% | Actual: | 100% | Actual: | 100% | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Const./Establishment of Integrated Solid Waste Management Facility |  | SB # 4 CY 2020 | Building |  | sq.m | Admin | Project Cost: | 50000000 | Target Completion Date: | 0 | Program: | 50000000 | Planned: | 100% | Planned: | 100% | Planned: | 100% | Planned: |  | Planned: |  | No. of Persons: |  | Completed as per physical accomplishment. Financial documents still on process. |  |  |  |  | For preparation of Plan
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 50000000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: | 100% | Actual: | 100% | Actual: | 100% | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Road Improvement of Jct. Highway Gabuyan – Semong – Dagohoy Provincial Road |  | CMGP CY 2020 | Road |  | km |  | Project Cost: | 63458000 | Target Completion Date: |  | Program: | 63458000 | Planned: |  | Planned: |  | Planned: |  | Planned: |  | No. of Persons: |  | No. of Persons: |  | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | For implementtation
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 63458000 | Revised: |  | Revised: |  | Revised: |  | Revised: |  | No. of Man-days: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual: |  | Actual: |  | Actual: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage: | 0% | Slippage: | 0% | Slippage: | 0% | Slippage: | 0%
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Road Improvement of Feeder Road 3- San Jose Provincial Road |  | CMGP CY 2020 | Road |  | km | Contract | Project Cost: | 53991806 | Target Completion Date: | 0 | Program: | 53991806 | Planned: | [7 empty] | No. of Persons: |  | No. of Persons: |  | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | For implementtation
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 53991806 | Revised: | [7 empty] | No. of Man-days: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage:
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Rehabilitation of New Visayas - Tulalian, Sto. Tomas |  | PRDP CY 2020 | Road |  | km | Contract | Project Cost: | 215000000 | Target Completion Date: | 0 | Program: | 215000000 | Planned: | [7 empty] | No. of Persons: |  | No. of Persons: |  | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | POW and DED on-going review (c/o RPCO)
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 215000000 | Revised: | [7 empty] | No. of Man-days: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage:
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Const. of Chocolate Pprocessing Building, San Francisco, Panabo City (REHOBOTH) |  | PRDP - I-REAP CY 2020 | Road |  | km | Contract | Project Cost: | 6072010.87 | Target Completion Date: | 0 | Program: | 6072010.87 | Planned: | [7 empty] | No. of Persons: |  | No. of Persons: |  | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | Completed as per physical accomplishment. Financial documents still on process. | For bidding
[7 empty] | Project Engineer: |  | Revised Completion Date: |  | Allotment: | 6072010.87 | Revised: | [7 empty] | No. of Man-days: |  | No. of Man-days:
[7 empty] | Implementor: |  | No. of days suspended: |  | Disbursement: |  | Actual:
[7 empty] | Duration: |  | No. of days extended: |  |  |  | Slippage:
[7 empty] | Date Allotment Released: |  | Date completed:
Date Started:
Note on D263: Cerela Montes: Previously 20% DF CY 2019 (STIMULUS)
Note on B371: chai: Previously Concreting of Drainage Canal, Poblacion, New Corella
Note on D377: previously 20% DF CY 2019
Note on D383: previously 20% DF CY 2019
Note on D389: chai: Previously Perimeter Fence of Day Care Center I & II, Nanyo, Panabo City (20% Development Fund CY 2018 (STIMULUS 2018)
Note on D395: chai: Previously Perimeter Fence of Day Care Center I & II, Nanyo, Panabo City (20% Development Fund CY 2018 (STIMULUS 2018)
Note on D401: chai: Previously Perimeter Fence of Day Care Center I & II, Nanyo, Panabo City (20% Development Fund CY 2018 (STIMULUS 2018)
Note on D419: chai: previously 20% DF
Note on D425: chai: previously 20% DF
Note on D443: chai: 20% DF CY 2019