## 1st quarter 2024
FDP Form 14a - Supplemental Procurement Plan, by Office or Department
SUPPLEMENTAL PROCUREMENT PLAN
( 1st QUARTER )
REGION: | REGION XI - DAVAO REGION | CALENDAR YEAR: |  | 2024
PROVINCE: | DAVAO DEL NORTE | OFFICE:
CITY/MUNICIPALITY:
Code (PAP) | Procurement Project | PMO/ End-User | Is this an Early Procurement Activity? (Yes/No) | Mode of Procurement | Schedule for Each Procurement Activity |  |  |  | Source of Funds | Estimated Budget (PhP)
[5 empty] | Advertisement/Posting of IB/REI | Submission/Opening of Bids | Notice of Award | Contract Signing |  | Total | MOOE | CO
PEO-S-24-03-037 | DESILTATION OF ISING- CAMILING CREEK REVISED, CARMEN, DAVAO DEL NORTE | PEO | NO | Competitive Bidding | 1st Quarter | 1st Quarter | 2nd Quarter | 2nd Quarter | 5% CALAMITY FUND CY2024 - FLOOD CONTROL AND SLOPE PROTECTION PROJECT | 500000
PEO-S-24-04-039 | REPAIR & MAINTENANCE OF VARIOUS PROVINCIAL ROADS AND BRIDGES. WITHIN DIST 2 OF DAVAO DEL NORTE | PEO | NO | Competitive Bidding | 1st Quarter | 1st Quarter | 2nd Quarter | 2nd Quarter | 20% DEVELOPMENT FUND CY2024 | 713382.63
PEO-S-24-04-040 | IMPROVEMENT OF BRIDGE BACKWALL PROTECTION ALONG FEEDER RD3 KINAMON-LUNA PROVINCIAL ROAD (KATIPUNAN-SECTION) , MUN. OF STO.TOMAS, PROVINCE OF DDN | PEO | NO | Competitive Bidding | 1st Quarter | 1st Quarter | 2nd Quarter | 2nd Quarter | 5% CALAMITY FUND CY2024 - FLOOD CONTROL AND SLOPE PROTECTION PROJECT | 1500000
PEO-S-24-03-035 | DESILTATION OF MATIN-AW CREEK (CASIGAN-SECTION) -RESIVED B.E. DUJALI, DAVAO DEL NORTE | PEO | NO | Competitive Bidding | 1st Quarter | 1st Quarter | 2nd Quarter | 2nd Quarter | 5% CALAMITY FUND CY2024 - FLOOD CONTROL AND SLOPE PROTECTION PROJECT | 500000
PEO-S-24-03-034 | REHAB. OF DUJALI-BALISONG MAGUPISING PROVINCIAL ROAD, B.E. DUJALI, DAVAO DEL NORTE | PEO | NO | Competitive Bidding | 1st Quarter | 1st Quarter | 2nd Quarter | 2nd Quarter | 5% CALAMITY FUND CY2024 - BUILDING BACK BETTER | 1000000
PEO-S-24-03-033 | REPAIR OF DIKE ALONG JCT. BDRY. TAGUM TALOMO PROVINCIAL ROAD. B.E. DUJALI -SANTO TOMAS, DAVAO DEL NORTE | PEO | NO | Competitive Bidding | 1st Quarter | 1st Quarter | 2nd Quarter | 2nd Quarter | 5% CALAMITY FUND CY2024 - BUILDING BACK BETTER | 1500000
PEO-S-24-01-009 | SLOPE PROTECTION ALONG KINAMAYAN LUNGAOG PROV'. ROAD MUN. OF STO.TOMAS, PROVINCIAL OF DDN | PEO | NO | Competitive Bidding | 1st Quarter | 1st Quarter | 2nd Quarter | 2nd Quarter | 5% CALAMITY FUND CY2024 - (DISASTER PREVENTION MITIGATION PROGRAM, FLOOD CONTROL AND SLOPE PROTECTION PROJECT) | 400000
PEO-S-24-01-011 | SLOPE PROTECTION ALONG SAN MIGUEL - MOSLOG - KINAMAYAN (PHASE 3) MUN. OF STO TOMAS, DAVAO DEL NORTE | PEO | NO | Competitive Bidding | 1st Quarter | 1st Quarter | 2nd Quarter | 2nd Quarter | 5% CALAMITY FUND CY 2024 ( FLOOD CONTROL & SLOPE PROTECTION PROJECTS) | 2600000
PEO-A-24-02-036 | IMPV'T./ REHAB. OF PPDO BUILDING (PHASE II), GOVERNMENT CENTER BRGY. MANKILAM, TAGUM CITY, DDN | PEO | NO | Competitive Bidding | 1st Quarter | 1st Quarter | 2nd Quarter | 2nd Quarter | 20% DP CY2024 - VARIOUS GOVERNMENT BUILDINGS & FACILITIES PROJECT | 1967181
PEO-S-24-03-032 | REPAIR & MAINTENANCE OF VARIOUS PROVINCIAL ROADS AND BRIDGES WITHIN DISTRICT 2 OF DDN | PEO | NO | Competitive Bidding | 1st Quarter | 1st Quarter | 2nd Quarter | 2nd Quarter | 20% DEVELOPMENT FUND CY2024 | 744617.97
PEO-A-24-02-038 | ROAD OPENING OF BDRY. SUA-ON TO PUROK 10, BRGY. FLORIDA, KAPALONG DDN | PEO | NO | Competitive Bidding | 1st Quarter | 1st Quarter | 2nd Quarter | 2nd Quarter | 20% DEVELOPMENT FUND CY2024 ROAD OPENING PROJECT | 2000000
PEO-S-24-02-026 | CONSTRUCTIONOF MULTI-PURPOSE BUILDING IN DAVAO DEL NORTE DISTRICT HOSPITAL-CARMEN ZONE, BRGY. ISING CARMEN,DDN | PEO | NO | Competitive Bidding | 1st Quarter | 1st Quarter | 2nd Quarter | 2nd Quarter | LOCAL GOVERNMENT SUPPORT FUND FY2023 | 25000000
PEO-S-24-01-014 | CONSTRUCTION OF 10.0 IN.M FLAT STAB BRIDGE KINAMAYAN, STO.TOMAS, DDN | PEO | NO | Competitive Bidding | 1st Quarter | 1st Quarter | 2nd Quarter | 2nd Quarter | 20% DF CY2024 (VARIOUS OF LOCAL ROADS & DRAINAGE DEV'T. PROJECT) | 9500000
PEO-S-24-01-013 | DREDGING OF TUGANAY RIVER, CARMEN, DDN. | PEO | NO | Competitive Bidding | 1st Quarter | 1st Quarter | 2nd Quarter | 2nd Quarter | 5% CALAMITY FUND CY 2024 ( FLOOD CONTROL & SLOPE PROTECTION PROJECTS) | 1000000
PEO-S-24-01-008 | IMPROVEMENT OF ROAD AND CROSS DRAINAGE ALONG CEBULANO-MANGALCAL PROV'L. ROAD, CARMEN, DDN | PEO | NO | Competitive Bidding | 1st Quarter | 1st Quarter | 2nd Quarter | 2nd Quarter | 5% CALAMITY FUND CY 2024 (IMPROVEMENT OF ROADS DRAINAGE AND CANAL) | 250000
PEO-S-24-01-013 | DESILTATION OF ISING-CAMILING CREEK CARMEN, DDN | PEO | NO | Competitive Bidding | 1st Quarter | 1st Quarter | 2nd Quarter | 2nd Quarter | 5% CALAMITY FUND CY 2024 (FLOOD CONTROL & SLOPE PROTECTION PROJECTS) | 500000
PEO-S-24-01-006 | SLOPE PROTECTION ALONG ISING-SADPODON-TABA-DILADILA PROV'L. ROA, CARMEN, DDN | PEO | NO | Competitive Bidding | 1st Quarter | 1st Quarter | 2nd Quarter | 2nd Quarter | 20% DF CY2024 (SLOPE PROTECTION & LAND DEVELOPMENT PROJECT) | 3800000
PEO-A-24-01-005A | REPAIR & MAINTENANCE OF VARIOUS PROVINCIAL ROADS AND BRIDGES, MUNICIPALITY OF NEW CORELLA, DDN | PEO | NO | Competitive Bidding | 1st Quarter | 1st Quarter | 2nd Quarter | 2nd Quarter | REPAIRS & MAINTENANCE OF PROVINCIAL ROADS - DIST.1 FUEL, OIL, AND LUBRICANTS EXPENSES | 6137180
PEO-A-24-01-001A | REPAIR & MAINTENANCE OF VARIOUS PROVINCIAL ROADS AND BRIDGES, MUNICIPALITY OF ASUNCION, DDN | PEO | NO | Competitive Bidding | 1st Quarter | 1st Quarter | 2nd Quarter | 2nd Quarter | REPAIRS & MAINTENANCE OF PROVINCIAL ROADS - DIST.1 FUEL, OIL, AND LUBRICANTS EXPENSES | 3212280
PEO-A-24-01-003 | REPAIR & MAINTENANCE OF VARIOUS PROVINCIAL ROADS AND BRIDGES, MUNICIPALITY OF TALAINGOD , DDN | PEO | NO | Competitive Bidding | 1st Quarter | 1st Quarter | 2nd Quarter | 2nd Quarter | REPAIRS & MAINTENANCE OF PROVINCIAL ROADS - DIST.1 FUEL, OIL, AND LUBRICANTS EXPENSES | 3765900.58
PEO-S-24-01-010 | REHABILATION OF DUJALI-BALISONG MAGUPISING PROV'L. ROAD BRIDGES APPROACH A&B, B.E. DUJALI, DDN | PEO | NO | Competitive Bidding | 1st Quarter | 1st Quarter | 2nd Quarter | 2nd Quarter | 5% CALAMITY FUND CY 2024 (FLOOD CONTROL & SLOPE PROTECTION PROJECTS) | 1500000
PEO-S-24-01-007 | IMPROVEMENT OF ROAD AND CROSS DRAIN ALONG UPPER LOWER MANGALCAL PROV'L. ROAD, CARMEN, DDN | PEO | NO | Competitive Bidding | 1st Quarter | 1st Quarter | 2nd Quarter | 2nd Quarter | 5% CALAMITY FUND CY2024 (IMPROVEMENT OF ROADS DRAINAGE AND CANAL) | 250000
PEO-S-24-01-005 | ROAD UPGRADING OF JCT. HIGHWAY-ISING MAGSAYSAY PROV'L. ROAD (PH II) CARMEN, DDN | PEO | NO | Competitive Bidding | 1st Quarter | 1st Quarter | 2nd Quarter | 2nd Quarter | 20% DF CY2024 (IMPROVEMENT OF PROV'L. ROAD AND BRIDGES | 5700385
PEO-A-24-01-015 | DREDGING OF SAUG RIVER MUNICIPALITY OF ASUNCION, DDN | PEO | NO | Competitive Bidding | 1st Quarter | 1st Quarter | 2nd Quarter | 2nd Quarter | 5% CALAMITY FUND CY 2024 (FLOOD CONTROL & SLOPE PROTECTION PROJECTS) | 1000000
PEO-A-24-01-014 | SLOPE PROTECTION ILOG BRIDGE, Municipality of Asuncion, DDN | PEO | NO | Competitive Bidding | 1st Quarter | 1st Quarter | 2nd Quarter | 2nd Quarter | 5% CALAMITY FUND CY 2024 (FLOOD CONTROL & SLOPE PROTECTION PROJECTS) | 2000000
PEO-A-24-01-013 | UPGRADING OF JCT. NEW VISAYAS - BUAN PROVINCIAL ROAD, Municipality of Asuncion, DDN | PEO | NO | Competitive Bidding | 1st Quarter | 1st Quarter | 2nd Quarter | 2nd Quarter | 20% DF CY2024 (IMPROVEMENT OF PROV'L. ROAD AND BRIDGES | 15000000
PEO-A-24-01-012 | ROAD UPGRADING OF MESAOY JCT. MAHAYAHAY PROVINCIAL ROAD (PHASE II), Municipality of New Corella, DDN | PEO | NO | Competitive Bidding | 1st Quarter | 1st Quarter | 2nd Quarter | 2nd Quarter | 20% DF CY2024 (IMPROVEMENT OF PROV'L. ROAD AND BRIDGES | 15000000
PEO-A-24-01-011 | UPGRADING OF DALIGDIGON-LUMABAS PROVINCIAL ROAD, TALAINGOD, DAVAO DEL NORTE | PEO | NO | Competitive Bidding | 1st Quarter | 1st Quarter | 2nd Quarter | 2nd Quarter | 20% DF CY2024 (IMPROVEMENT OF PROV'L. ROAD AND BRIDGES | 15000000
PEO-A-24-01-010 | CONSTRUCTION OF BARANGAY HALL (PHASE II) Brgy. Magatos, Municipality of Asuncion, DDN | PEO | NO | Competitive Bidding | 1st Quarter | 1st Quarter | 2nd Quarter | 2nd Quarter | 20% DF CY 2024 | 1000000
PEO-A-24-01-009 | CONSTRUCTION OF COMELEC BUILDING (PHASE III) Brgy. Mankilam, Tagum City, DDN. | PEO | NO | Competitive Bidding | 1st Quarter | 1st Quarter | 2nd Quarter | 2nd Quarter | 20% DF CY 2024 VARIOUS GOVERNMENT BUILDING & FACILITIES DEVELOPMENT PROGRAM | 1000000
PEO-A-24-01-008 | IMPROVEMENT OF BARANGAY HALL (PHASE II) Brgy. Kipalili, Municipality of San. Isidro, DDN | PEO | NO | Competitive Bidding | 1st Quarter | 1st Quarter | 2nd Quarter | 2nd Quarter | 20% DF CY 2024 VARIOUS GOVERNMENT BUILDING & FACILITIES DEVELOPMENT PROGRAM | 42500000
PEO-A-24-01-007 | CONSTRUCTION OF LEGISLATIVE BUILDING (PHASE 2), Brgy. Sto Niño, Municipality of Talaingod DDN | PEO | NO | Competitive Bidding | 1st Quarter | 1st Quarter | 2nd Quarter | 2nd Quarter | 20% DF CY 2024 VARIOUS GOVERNMENT BUILDING & FACILITIES DEVELOPMENT PROGRAM | 3000000
PEO-A-24-01-006 | CONSTRUCTION OF BARANGAY HALL (PHASE II) Brgy. Doña Andrea, Municipality of Asuncion, DDN | PEO | NO | Competitive Bidding | 1st Quarter | 1st Quarter | 2nd Quarter | 2nd Quarter | 20% DF CY 2024 VARIOUS GOVERNMENT BUILDING & FACILITIES DEVELOPMENT PROGRAM | 1000000
PEO-A-24-01-004 | REPAIR & MAINTENANCE OF VARIOUS PROVINCIAL ROADS AND BRIDGES Municipality of San Isidro, DDN | PEO | NO | Competitive Bidding | 1st Quarter | 1st Quarter | 2nd Quarter | 2nd Quarter | REPAIRS & MAINTENANCE OF PROVINCIAL ROADS - DIST.1 FUEL, OIL, AND LUBRICANTS EXPENSES | 3388405
PEO-A-24-01-002A | REPAIR & MAINTENANCE OF VARIOUS PROVINCIAL ROADS AND BRIDGES Municipality of Kapalong, DDN | PEO | NO | Competitive Bidding | 1st Quarter | 1st Quarter | 2nd Quarter | 2nd Quarter | REPAIRS & MAINTENANCE OF PROVINCIAL ROADS - DIST.1 FUEL, OIL, AND LUBRICANTS EXPENSES | 2982086.8
PEO-S-24-01-024 | IMPRVT. OF ROAD AND DRAINAGE ALONG DUJALI-PAWAS SAN VICENTE PROV'L. ROAD, Municipality of B.E. Dujali, DDN | PEO | NO | Competitive Bidding | 1st Quarter | 1st Quarter | 2nd Quarter | 2nd Quarter | 5% CALAMITY FUND CY 2024 (IMPROVEMENT OF ROADS DRAINAGE AND CANAL) | 2982086.8
PEO-S-24-01-025 | IMPVT OF ROAD AND CANAL ALONG SITIO PARADISE MAGKAKAISA- ESPERANZE PROV'L. ROAD, Municipality of Sto. Tomas, DDN | PEO | NO | Competitive Bidding | 1st Quarter | 1st Quarter | 2nd Quarter | 2nd Quarter | 5% CALAMITY FUND CY 2024 (IMPROVEMENT OF ROADS DRAINAGE AND CANAL) | 250000
PEO-S-24-01-022 | CONSTRUCTION OF BARANGAY HALL, BRGY. ESPERANZA, Sto. Tomas, DDN | PEO | NO | Competitive Bidding | 1st Quarter | 1st Quarter | 2nd Quarter | 2nd Quarter | 20% DF CY 2024 VARIOUS GOVERNMENT BUILDING & FACILITIES DEVELOPMENT PROGRAM | 2000000
PEO-S-24-01-021 | REPAIR AND MAINTENANCE OF VARIOUS PROV'L. ROADS AND BRIDGES ,District 2, DDN | PEO | NO | Competitive Bidding | 1st Quarter | 1st Quarter | 2nd Quarter | 2nd Quarter | 20% Development Fund CY 2024 | 29700000
PEO-S-24-01-023 | ROAD OPENING OF TAYAPOC-TAGBITAN-AG TAGBITINAO GUILON, IGACOS, DDN | PEO | NO | Competitive Bidding | 1st Quarter | 1st Quarter | 2nd Quarter | 2nd Quarter | 20% Development Funf CY 2024 ( Road Opening Project) | 1000000
PEO-A-24-01-024 | ROAD OPENING OF SITION MILYONG TO SITIO BAUGAN | PEO | NO | Competitive Bidding | 1st Quarter | 1st Quarter | 2nd Quarter | 2nd Quarter | 20% Development Funf CY 2024 ( Road Opening Project) | 1940524.03
PEO-A-24-01-026 | CONSTRUCTION OF RAINWATER COLLECTOR AT KABAUYAN TU DIBABAWON, Brgy. Sto. Niño, Municipality of New Corella, DDN | PEO | NO | Competitive Bidding | 1st Quarter | 1st Quarter | 2nd Quarter | 2nd Quarter | 20% OF CY2024 (Various Water System Development) | 2413109.06
PEO-A-24-01-025 | CONSTRUCTION OF RAINWATER COLLECTOR AT BALAI LUPOWANAN, Sitio Nasilaban, Brgy. Palma Gil, Talaingod, DDN | PEO | NO | Competitive Bidding | 1st Quarter | 1st Quarter | 2nd Quarter | 2nd Quarter | 20% OF CY2024 (Various Water System Development) | 2486178.26
PEO-A-24-01-016 | CONSTRUCTION OF PEO Sub-OFFICE COMM'L. BLDG. (PHASE 2) BRGY. KINWITNON | PEO | NO | Competitive Bidding | 1st Quarter | 1st Quarter | 2nd Quarter | 2nd Quarter | 20% DF CY 2024 VARIOUS GOVERNMENT BUILDING & FACILITIES DEVELOPMENT PROGRAM | 1500000
PEO-A-24-01-019 | REHABILITATION/IMPROVEMENT OF ADMINISTRATION BUILDING (LUNTIANG PARAISO REGIONAL REHABILITATION CENTER) P-2 Brgy. Pob. Municipality of New Corella, DDN | PEO | NO | Competitive Bidding | 1st Quarter | 1st Quarter | 2nd Quarter | 2nd Quarter | SPECIAL ACCOUNT IN THE GENERAL FUND | 12000000
PEO-A-24-01-028 | CONSTRUCTION OF SINGLE PHASE LINE AND REMOVAL OF EXISTING LINE, Bahay Pag-asa, Poblacion, Municipality of New Corella, DDN | PEO | NO | Competitive Bidding | 1st Quarter | 1st Quarter | 2nd Quarter | 2nd Quarter | PSWDO BAHAY PAG-ASA GENERAL TRUST FUND AND LIABILITY COLLECTION | 350000
PEO-A-24-01-018 | CONSTRUCTION OF TRIBAL HALL (PHASE II), Brgy. San Agustin, Tagum City, DDN | PEO | NO | Competitive Bidding | 1st Quarter | 1st Quarter | 2nd Quarter | 2nd Quarter | SB# CY 2023 VARIOUS GOVERNMENT BUILDING & FACILITIES PROJECT | 1000000
PEO-A-24-01-022 | REHABILITATION/IMPROVEMENT OF 1.00 KM FARM TO MARKET ROAD AT JUNCTION PRK 1 TO PRK 6, Brgy. Luna, Kapalong, DDN | PEO | NO | Competitive Bidding | 1st Quarter | 1st Quarter | 2nd Quarter | 2nd Quarter | LOCAL GOVERNMENT SUPPORT FUND FY2023 | 20000000
PEO-A-24-01-021 | SLOPE PROTECTION AT KABUYAN TU DIBABAWON SITE, Brgy. Sto Niño, New Corella, DDN | PEO | NO | Competitive Bidding | 1st Quarter | 1st Quarter | 2nd Quarter | 2nd Quarter | 20% DF CY 2024 - SLOPE PROTECTION & LAND DEVELOPMENT PROJECT | 2143363.45
PEO-A-24-01-0020 | CONSTRUCTIONOF CANAL LINING AT KABAUYAN TU DIBABAWON Brgy. Sto Niño, New Corella, DDN | PEO | NO | Competitive Bidding | 1st Quarter | 1st Quarter | 2nd Quarter | 2nd Quarter | 20% DF CY 2024, VARIOUS LOCAL ROADS & DRAINAGE DEV'T. PROJECT | 1936651.59
PEO-S-24-0-019 | IMPVT OF BRGY ROAD AND DRAINAGE ALONG MABAUS-SALVACION PROVINCIAL ROAD, Carmen, DDN | PEO | NO | Competitive Bidding | 1st Quarter | 1st Quarter | ` | 2nd Quarter | 5% CALAMITY FUND CY 2024 (IMPROVEMENT OF ROADS DRAINAGE AND CANAL) | 350000
PEO-A-24-01-023 | CONSTRUCTION OF BARANGAY HALL (PHASE II) Brgy. Canatan, Asuncion, DDN | PEO | NO | Competitive Bidding | 1st Quarter | 1st Quarter | 2nd Quarter | 2nd Quarter | SB# CY 2023 VARIOUS GOVERNMENT BUILDING & FACILITIES PROJECT | 880000
PEO-C-24-10 | MAINTENANCE OF VARIOUS PROV'L. ROAD & BRIDGES DIST. 1 | PEO | NO | Competitive Bidding | 1st Quarter | 1st Quarter | 2nd Quarter | 2nd Quarter | 20% DF CY 2024 | 50600000
PEO-C-24-04-038 | REHABILITATION OF KM. 15 KIPALILI-NEW LOON FMR WITH BRIDGE, Brgy. Concepcion, Brgy. New Loon, Municipality of Asuncion & Brgy. Kipalili, Municipality of San Isidro, DDN | PEO | NO | Competitive Bidding | 1st Quarter | 1st Quarter | 2nd Quarter | 2nd Quarter | PRDP | 208760000
PEO-A-24-01-029 | IMPV'T. OF ROAD & DRAINAGE ALONG NEW VISAYAS BINANCIAN PROV'L. PHASE 1, Municipality of Asuncion, DDN | PEO | NO | Competitive Bidding | 1st Quarter | 1st Quarter | 2nd Quarter | 2nd Quarter | 5% CALAMITY FUND CY 2024 (FLOOD CONTROL & SLOPE PROTECTION PROJECTS) | 985775.93
PEO-A-24-02-035 | IMPV'T. REHAB. OF PPDO BUILDING (REVISED)Government Center, Brgy. Mankilam,Tagum City, DDN | PEO | NO | Competitive Bidding | 1st Quarter | 1st Quarter | 2nd Quarter | 2nd Quarter | SB # 1 CY 2023 | 1499419.15
PEO-S-24-01-015 | UPGRADING OF BARANGAY ROAD Brgy. Tagdaliao, IGACOS, DDN | PEO | NO | Competitive Bidding | 1st Quarter | 1st Quarter | 2nd Quarter | 2nd Quarter | 20% DF CY 2024, VARIOUS LOCAL ROADS & DRAINAGE DEV'T. PROJECT | 3000000
PEO-S-24-01-020 | IMPRVT. OF BRGY. ROAD AND CROSS DRAINAGE ALONG STO NIÑO-ASUNCIONPROV'L. ROAD, Carmen, DDN | PEO | NO | Competitive Bidding | 1st Quarter | 1st Quarter | 2nd Quarter | 2nd Quarter | 5% CALAMITY FUND CY 2024 (IMPROVEMENT OF ROADS DRAINAGE AND CANAL) | 250000
PEO-S-24-01-018 | IMPRVT. OF BRGY. ROAD AND DRAINAGE AT PUROK 4 Brgy. San Isidro, Carmen, DDN | PEO | NO | Competitive Bidding | 1st Quarter | 1st Quarter | 2nd Quarter | 2nd Quarter | 5% CALAMITY FUND CY 2024 (IMPROVEMENT OF ROADS DRAINAGE AND CANAL) | 400000
PEO-A-24-01-016 | DESILTATION OF SUAWON CREEK, Municipality of New Corella, DDN | PEO | NO | Competitive Bidding | 1st Quarter | 1st Quarter | 2nd Quarter | 2nd Quarter | 5% CALAMITY FUND CY 2024 (FLOOD CONTROL & SLOPE PROTECTION PROJECTS) | 500000
PEO-A-24-01-017 | DESILTATION OF SAN AGUSTIN-NUEVA FUEZA-MESAOY CREEK (PHASE II) Municipality of New Corella, DDN | PEO | NO | Competitive Bidding | 1st Quarter | 1st Quarter | 2nd Quarter | 2nd Quarter | MOOE CY 2024 | 1500000
PEO-S-24-01-012 | DESILTATION OF MATIN--AW CREEK (CASIG-ANG SECTION) B.E. Dujalim DDN | PEO | NO | Competitive Bidding | 1st Quarter | 1st Quarter | 2nd Quarter | 2nd Quarter | 5% CALAMITY FUND CY 2024 (FLOOD CONTROL & SLOPE PROTECTION PROJECTS) | 500000.01
527838527.26
This is to certify that the above procurement plan is in accordance with the objective of this Office.
ENGR. JOSIE JEAN R. RABANOZ, MPA, EnP
Provincial Administrator - BAC Chairperson

## summary 1st quarter
FDPP Form 14b - Supplemental Procurement Plan or Procurement List, Summary
SUPPLEMENTAL PROCUREMENT PLAN
( 1st Quarter )
REGION: | REGION XI - DAVAO REGION | CALENDAR YEAR: | 2024
PROVINCE: | DAVAO DEL NORTE
CITY/MUNICIPALITY:
Summary by Office
Department |  | Head of Department / Office | Total Cost
PEO |  | GLENN A. OLANDRIA | 527838527.26
Prepared by:
JUDETH M. MADELO
Supervising Administrative Officer
Noted by:
ENGR. JOSIE JEAN R. RABANOZ, MPA, EnP
Provincial Administrator - BAC Chairperson
Approved By:
EDWIN I. JUBAHIB
Governor
Province of Davao del Norte